|  |  |  |
| --- | --- | --- |
| **Project Name: Abu Ghaleb bridge** | | |
| **Location:** | | |
| **Contractor**  **Rowad Modern Engineering** | **Consultant**  **Penta** | **Employer**  **General Authority for Roads and Bridges** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Project Code** | **0157** | **Date:** | **04/12/2023** | **Report No.** | **3** |
| **Phase** | **1** | **Ref.** |  | **Attached doc.** |  |

# A. Management Staff *(Input by Timekeeper)*

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| ID | Position | Day Shift | Night Shift | Notes |
| 1 | **مشرف تنفيذ** |  |  | **2** |
| 2 | **مشرف امن** |  |  | **2** |
| 3 | **امن اداري** |  |  | **8** |
| 4 | **مساعد سباك** |  |  | **1** |
| 5 | **ريس بحرى** |  |  | **1** |
| 6 | **عامل** |  |  | **13** |
| 78 | **عامل معمل** |  |  | **1** |
| 9 | **مشرف الصحة والسلامة** |  |  | **0** |
| 10 | **فرد الصحة والسلامة** |  |  | **3** |
| 11 | **منسق وثائق** |  |  | **1** |
| 12 | **فنى تصوير** |  |  | **1** |
| 13 | **فورمجى خرسانة** |  |  | **1** |
| 14 | **نحات** |  |  | **1** |
| 15 | **كهربائى تركيبات** |  |  | **1** |
| 16 | **كهربائى صيانه** |  |  | **1** |
| 17 | **مساعد كهربائى** |  |  | **1** |
| 18 | **مساعد امين مخزن** |  |  | **1** |
| 19 | **لحام** |  |  | **3** |
| 20 | **مساعد لحام** |  |  | **1** |
| 21 | **مبيض** |  |  | **2** |
| 22 | **مساح** |  |  | **2** |
| 23 | **مساعد مساح** |  |  | **2** |
| 24 | **مساعد مشرف سكن** |  |  | **0** |
| *Totals of management staff* | | 49 | |  |

# B. Site Workers (Labors) *(Input by Construction Manager)*

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Trade / Position | Subcontractor/Supplier Name | Location | No. of workers | Day Shift | Hours | | Night Shift | Hours | | Notes |
| 1 | ------------ |  |  |  |  | |  |  | |  |  |
| 2 |  |  |  |  |  | |  |  | |  |  |

# C. Activities on Site *(Input by Project Control Engineer in coordination with Construction Manager)*

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Location | On site activities description | Date | | % complete previous | % Complete this day | To date % complete | Notes |
| Started | Planned Completion |
| 1 | L10 | تركيب ركائز | 9/6/22 | 11/6/22 | 50 | 50 | 100 |  |
| 2 | R11 | حدادة أعمدة فوق الخوازيق المفرد | 9/6/22 | 11/6/22 | 80 | 20 | 100 |  |
| 3 | R7 to R4 | فك بلاطة | 9/6/22 | 16/6/22 | 20 | 5 | 25 |  |
| 4 | L1 | ردم قاعدة لاعمال الخوازيق | 11/6/22 | 12/6/22 | 80 | 10 | 90 |  |
| 5 | R4 to R3 | شد معدني الباكية الصندوقية | 9/6/22 | 18/6/22 | 10 | 0 | 10 |  |
| 6 | L7to L10 | أعمال حدادة البلاطة | 9/6/22 | 19/6/22 | 25 | 10 | 35 |  |
| 7 | R11 | تقفيل فرم | 11/6/22 | 11/6/22 | 0 | 100 | 100 |  |
| 8 | R12 | حدادة أعمدة فوق الخوازيق المفرد | 11/6/22 | 11/6/22 | 0 | 100 | 100 |  |
| 9 | L7to L10 | استكمال نجارة قاع الكمرة العرضية فوق فريم 10 وتقويات الكمر الطولي | 11/6/22 | 19/6/22 | 50 | 10 | 60 |  |
|  |  |  |  |  |  |  |  |  |

# D. Equipment and tools list *(Input by Equipment Supervisor)*

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Equipment *(heavy/small tools)* | Subcontractor Name | Type *(Rented/owned)* | Model | In use hours | Stand by hours | Notes |
| 1 | ونش | According to site needs | Rented |  | 8 |  |  |
| 2 | ونش | According to site needs | Rented |  | 8 |  |  |
| 3 | لودر | According to site needs | Rented |  | 8 |  |  |
| 4 | شوكه | According to site needs | Rented |  | 8 |  |  |
| 5 | بطاحه | According to site needs | Rented |  | 8 |  |  |
| 6 | حفار | According to site needs | Rented |  | 8 |  |  |

# Formwork *(Input by Formwork)*

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Item Description | System | Subcontractor Name | Items Code | QTY | Location | Notes |
| 1 | ------------ |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |

# F. Delivered Material *(Input by site QC)*

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ID | Material description | Material on site (Qty) *if applicable* | Delivered Qty Today | MIR No. | Supplier | Notes |
| 1 | ------------ |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

# G. Area of Concerns *(Input by Project Control Engineer)*

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ID | Concern description *(i.e., weather condition, delay, obstructions)* | Duration | Location | Impact | Notes |
| 1 | Delay of concrete pouring due to Nile station | 1 | Sadat city | Delay of time |  |
| 2 | Delay of cup-lock scaffolding delivery for L10-L12 | 6 | Khatatba bridge | Delay of time |  |
| 3 | Payment for Backfilling subcontractor | 10 | Axis-A17 | Delay 10 d |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

Prepared by: Approved by: Approved by:

Project control engineer Construction Manager Project Manager

Signature Signature Signature

Date Date Date