| Project Name: Abu Ghaleb bridge |  |  |
| --- | --- | --- |
| Location: |  |  |
| Contractor Rowad Modern Engineering | Consultant Penta | Employer General Authority for Roads and Bridges |

| Project Code | 0167 | Date: | 28/12/2022 | Report No. | 62 |
| --- | --- | --- | --- | --- | --- |
| Phase | 1 | Ref. |  | Attached doc. |  |

# A. Management Staff 
(Input by Timekeeper)

| ID | Position | Day Shift | Night Shift | Notes |
| --- | --- | --- | --- | --- |
| 1 | عمال ذاتى | 6 |  |  |
| 2 | كهربائى تركيبات | 1 |  |  |
| 3 | فورمجيه خرسانه | 5 |  |  |
| 4 | لحامين | 2 |  |  |
| 5 | شده معدنيه | 0 |  |  |
| 7 | مساحه | 1 |  |  |
| 8 | مشرفين | 1 |  |  |
| 9 | الصحة والسلامة | 2 |  |  |
| 10 | مشرف امن ادارى | 1 |  |  |
| 11 | امن ادارى | 4 |  |  |
| 12 | مخزن | 1 |  |  |
| 13 | مشتريات | 1 |  |  |
| 14 | عامل سكن | 1 |  |  |
| 15 | مراقب وقت | 1 |  |  |
| Totals of management staff |  | 32 |  |  |

# B. Site Workers (Labors)
(Input by Construction Manager)

| ID | Trade / Position | Subcontractor/Supplier Name | Location | No. of workers | Day Shift | Hours |  | Night Shift | Hours |  | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Steel fixing | Sherbieny |  | 3 | ☐ |  |  | ☐ |  |  |  |
| 2 | Formwork | Gohary |  | 6 | ☐ |  |  | ☐ |  |  |  |
| 3 | Pile head demolishing | Mohamed Saber |  | 0 |  |  |  |  |  |  |  |

# C. Activities on Site
(Input by Project Control Engineer in coordination with Construction Manager)

| ID | Location | On site activities description | Date |  | % complete previous | % Complete this day | To date % complete | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Started | Planned Completion |  |  |  |  |
| 1 | Axis-P10-P12 | حفر و صب خازوقين | 25/12/2022 | 28/12/2022 | 100 | 100 | 100 | جارى حفر وتسليم خازوقين واجمالى الصب 162 خازوق |
| 2 | P04 | حدادة العمود | 11/10/2022 | 28/12/2022 | 20 | 0 | 20 |  |
| 3 | P03 | حدادة العمود | 12/10/2022 | 28/12/2022 | 20 | 0 | 20 |  |
| 4 | P02 | حدادة العمود | 12/10/2022 | 28/12/2022 | 30 | 0 | 30 |  |
| 5 | P20 | صب العمود | 16/11/2022 | 28/12/2022 | 95 | 5 | 100 |  |
| 5 | P22 | صب العمود | 16/11/2022 | 28/12/2022 | 80 | 5 | 85 |  |
| 6 | P23 | شدة العمود | 04/12/2022 | 28/12/2022 | 80 | 0 | 80 |  |
| 7 | P36 | حدادة القاعدة | 28/12/2022 | 28/12/2022 | 0 | 20 | 20 |  |
| 8 | P35 | حدادة القاعدة | 22/12/2022 | 28/12/2022 | 50 | 20 | 70 |  |
| 9 | P34 | حدادة القاعدة | 23/12/2022 | 28/12/2022 | 30 | 20 | 50 |  |
| 11 | P33-P34 | تكسير رؤوس خوازيق | 17/12/2022 | 28/12/2022 | 80 | 20 | 100 | تم ترتيب التكسير يوم السبت القادم |

# D. Equipment and tools list
(Input by Equipment Supervisor)

| ID | Equipment (heavy/small tools) | Subcontractor Name | Type (Rented/owned) | Model | In use hours | Stand by hours | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 Loader | Mobilization | Rented |  | 8 |  |  |
| 2 | Tractor | Removal | Rented |  | 8 |  |  |
| 3 | Excavator | Excavation | Rented |  | 8 |  |  |
| 4 | Mobile crane | Mobilization | Rented |  | 8 |  |  |
| 6 | 3 Water truck | Piles | Rented |  | 8 |  |  |

# Formwork 
(Input by Formwork)

| ID | Item Description | System | Subcontractor Name | Items Code | QTY | Location | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ------------ |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |

# F. Delivered Material 
(Input by site QC)

| ID | Material description | Material on site (Qty) if applicable | Delivered Qty Today | MIR No. | Supplier | Notes |
| --- | --- | --- | --- | --- | --- | --- |

# G. Area of Concerns 
(Input by Project Control Engineer)

| ID | Concern description (i.e., weather condition, delay, obstructions) | Duration | Location | Impact | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Shortage of concrete supply from ready mix stations (Payment issue, availability of sim 3) |  | General | Delay of piles works & Claims from driller on site | Settled |
| 3 | Mockup of mass concrete not started |  |  | Delay of all mass concrete works (Especially Pile caps) | Poured 24/9/22 |
| 5 | All requirements for Pile cap works ( Thermo cables-Earthing Drawing -qualified station for mass concrete) |  | Piles Caps |  | Settled |
| 6 | Pier forms |  |  | Delay of pier works | Deliverd |
| 7 | Bearings vendor not determined |  |  | Delay of piers & pier head |  |
| 8 | Forms of U-precast beam is top urgent to be procured |  |  | Delay of project as it’s critical activity. |  |
| 9 | Removal of 6 Residential buildings |  | P13-P19 | Delay of piles works |  |
| 10 | Removal of Water station fence |  | P5-P8 | Delay of piles works |  |

Prepared by:                                                  Approved by:                                      Approved by:

Project control engineer                                Construction Manager                        Project Manager

Signature                                                       Signature                                            Signature

Date                                                               Date                                                    Date

# H. Site photos:

Steel fixing of pile cap P-35

Steel fixing of pile cap P-35

Pouring of column P-20

Pouring piles P19-P12

Demolishing Water station fence for piles work