## eslam.data
project | Opr | invoice no. | Gross | Gross From ERP | Gross Cases | Collection | Collection from ERP | Collection Cases | dp amount | on account amount | other amount (comment) | Net | invoice month | cut off date | submittal date | duration of pay | pay due date | approval_date | cummulative amount approved | material on site cummulative amount approved | v.o. cummulative amount approved | ncr cummulative amount approved | escalation cummulative amount approved | 1st retention cummulative amount approved | 2nd retention cummulative amount approved | total deductions | consultant gross | consultant gross cumulative | consultant net | project name in invoicing | Notes | Gross - Material on Site (both eslam) | Gross Cases (MOS Deducted) | concact eslam name with invoice no | concat invoicing name with invoice no
6TH October tunnel | 2 | 1 | 842930 | 1605581.42 | 762651.42 | 1520548 | 1520548 | 0 |  |  |  | 1520548 | 2022-05-31 | 2022-06-08 | 2022-06-15 | 60 | 2022-08-14 | 2022-09-11 | 842930 | 1367190 | [5 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel1 | October Under-Railway Tunnel1
6TH October tunnel | 2 | 2 | 3756426.15 | 8760678.38 | 5004252.23 | 3508372.9 | 3508352.9 | -20 |  |  |  | 3208372.9 | 2022-07-31 | 2022-08-10 | 2022-08-21 | 60 | 2022-10-20 | 2022-09-25 | 4599356.15 | 921846.75 | [5 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel2 | October Under-Railway Tunnel2
6TH October tunnel | 2 | 3 |  | 5911928.1 | 5911928.1 | 0.001 | 5155347.1955 | 5155347.1945 |  |  |  |  | 2022-08-31 | 2022-09-06 | 2022-09-07 | 60 | 2022-11-06 | [8 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel3 | October Under-Railway Tunnel3
6TH October tunnel | 2 | 4 | 7050454.75 | 0 | -7050454.75 | 5155347 | 0 | -5155347 |  |  |  | 5155347.5 | 2022-09-30 | 2022-10-01 | 2022-11-13 | 60 | 2023-01-12 | 2022-11-14 | 11649810.9 | 750750 | [5 empty] | 0 | 7663602.64 | 12262958.79 | 3604450.6683 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel4 | October Under-Railway Tunnel4
6TH October tunnel | 2 | 5 | 3846689.4 | 3663513.71 | -183175.69 | 2856009 | 2856009 | 0 |  |  |  | 3524900.34 | 2022-10-31 | 2022-11-15 | 2022-11-17 | 60 | 2023-01-16 | 2022-11-25 | 15496500.3 | 298295 | [5 empty] | 0 | 6157467.55 | 17807278.45 | 3524900.34 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel5 | October Under-Railway Tunnel5
6TH October tunnel | 2 | 6 | 1899766.7 | 1809302.29 | -90464.41 | 1337162.6 | 1337162.5545 | -0.0455 |  |  |  | 1337162.6 | 2022-12-31 | 2022-12-15 | 2023-01-09 | 60 | 2023-03-10 | 2023-02-12 | 17396267 | [6 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel6 | October Under-Railway Tunnel6
Abo Ghaleb Bridge | 2 | 1 |  | 0 | 0 | 175270.85 | 0 | -175270.85 |  |  |  |  | 2022-01-31 | 2022-01-31 | 2022-02-03 | 60 | 2022-04-04 | [8 empty] | 0 | 0 | 0 | 0 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge1 | Abo Ghaleb1
Abo Ghaleb Bridge | 2 | 2 | 3079766.7 | 1428000 | -1651766.7 | 2494611.027 | 142483.6 | -2352127.427 |  |  |  | 2494611.027 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 15845653.7 | [6 empty] | 0 | 3079766.7 | 15845653.7 | 2494611.027 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge2 | Abo Ghaleb2
Abo Ghaleb Bridge | 2 | 3 | 3857104.5 | 0 | -3857104.5 | 2045810.923 | 0 | -2045810.923 |  |  |  | 3124254.645 | 2022-03-31 | 2022-03-31 | 2022-04-04 | 60 | 2022-06-03 | 2022-04-04 | 19702758.2 | [6 empty] | 0 | 3857104.5 | 19702758.2 | 3124254.645 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge3 | Abo Ghaleb3
Abo Ghaleb Bridge | 2 | 4 | 17739438 | 0 | -17739438 | 12711007.22 | 0 | -12711007.22 |  |  |  | 6555212.9406 | 2022-04-30 | 2022-04-30 | 2022-04-15 | 60 | 2022-06-14 | 2022-08-09 | 37442196.2 | [6 empty] | 0 | 17739438 | 37442196.2 | 6555212.9406 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge4 | Abo Ghaleb4
Abo Ghaleb Bridge | 2 | 5 | 2031888 | 0 | -2031888 | 1645829.28 | 0 | -1645829.28 |  |  |  | 1645829.28 | 2022-07-31 | 2022-07-31 | 2022-08-21 | 60 | 2022-10-20 | 2022-08-21 | 39474084.2 | [6 empty] | 0 | 2031888 | 39474084.2 | 1645829.28 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge5 | Abo Ghaleb5
Abo Ghaleb Bridge | 2 | 6 |  | 0 | 0 | 0.0001 | 0 | -0.0001 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 | [8 empty] | 0 | 0 | 0 | 0 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge6 | Abo Ghaleb6
AEON | 0 | 1 | 1325211.2762 | 0 | -1325211.2762 | 1264914.16 | 0 | -1264914.16 |  |  |  | 1264914.16 | 2020-09-30 | 2020-09-16 | 2020-09-20 | 56 | 2020-11-15 | 2020-09-22 | 1325211.2762 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | AEON1 | 01
AEON | 0 | 2 | 1613181.4 | 0 | -1613181.4 | 1513146.56 | 0 | -1513146.56 |  |  |  | 1513146.56 | 2020-10-31 | 2020-11-03 | 2020-11-03 | 56 | 2020-12-29 | 2020-12-15 | 2938392.6762 | [6 empty] | 0 | 1300835.2032 | 2626046.4794 | 1610113.5212 | 0 |  |  |  | AEON2 | 02
AEON | 0 | 3 | 799158.9955 | 0 | -799158.9955 | 780253.07 | 0 | -780253.07 |  |  |  | 780253.0677 | 2020-12-31 | 2020-12-20 | 2020-12-21 | 56 | 2021-02-15 | 2021-01-04 | 3737551.6717 | 20153.7514 | [5 empty] | 27500 | 799158.9955 | 3737551.6717 | 780253.0677 | 0 |  |  |  | AEON3 | 03
AEON | 0 | 4 |  | 0 | 0 | 484406.35 | 0 | -484406.35 |  |  |  |  | 2021-02-28 | 2021-02-28 | 2021-06-24 | 56 | 2021-08-19 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | AEON4 | 04
Al Jazi | 1 | 1 | 9888666.63 | 278661 | -9610005.63 | 55324495 | 230795 | -55093700 | 53125000 |  |  | 2199496 | 2018-04-30 | 2018-05-21 | 2018-05-21 | 15 | 2018-06-05 | 2018-06-03 | 9888666.63 | 0 | [5 empty] | 5395000 | 9888666.63 | 9888666.63 | 2462056.64 | Aljazi Project |  |  |  | Al Jazi1 | Aljazi Project1
Al Jazi | 1 | 2 | 6959342.1 | 322383 | -6636959.1 | 2330066 | 151797.77 | -2178268.23 |  |  |  | 2330066 | 2018-05-31 | 2018-06-05 | 2018-06-07 | 15 | 2018-06-22 | 2018-06-26 | 16848008.73 | 0 | [5 empty] | 8409664 | 6959342.1 | 16848008.73 | 3686157.94 | Aljazi Project |  |  |  | Al Jazi2 | Aljazi Project2
Al Jazi | 1 | 3 | 6863084.68 | 121070 | -6742014.68 | 3090062.9 | 58174.3 | -3031888.6 |  |  |  | 3357056.9 | 2018-06-30 | 2018-07-04 | 2018-07-07 | 15 | 2018-07-22 | 2018-07-25 | 23711093.41 | 0 | [5 empty] | 10989780.0001 | 6863158.19 | 23711166.92 | 3748572.21 | Aljazi Project |  |  |  | Al Jazi3 | Aljazi Project3
Al Jazi | 1 | 4 | 6873217.27 | 0 | -6873217.27 | 3867947.36 | 0 | -3867947.36 |  |  |  | 3867947.36 | 2018-07-31 | 2018-07-24 | 2018-07-24 | 15 | 2018-08-08 | 2018-07-29 | 30584310.68 | 0 | [5 empty] | 12001158.5 | 6873307.38 | 30584400.79 | 4444997.23 | Aljazi Project |  |  |  | Al Jazi4 | Aljazi Project4
Al Jazi | 1 | 5 | 7893070.92 | 0 | -7893070.92 | 4039155 | 0 | -4039155 |  |  |  | 4039155 | 2018-07-31 | 2018-08-08 | 2018-08-11 | 15 | 2018-08-26 | 2018-08-30 | 38477381.6 | 1152162.9504 | [5 empty] | 15549196.5 | 7893373.579 | 38477684.259 | 4854984.5363 | Aljazi Project |  |  |  | Al Jazi5 | Aljazi Project5
Al Jazi | 1 | 6 | 4850391.56 | 0 | -4850391.56 | 2383592 | 0 | -2383592 |  |  |  | 2965400.21 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 15 | 2018-09-21 | 2018-09-10 | 43327773.16 | 1152162.95 | [5 empty] | 16838621.5 | 4850391.56 | 43327773.16 | 2965400.21 | Aljazi Project |  |  |  | Al Jazi6 | Aljazi Project6
Al Jazi | 1 | 7 | 9360993.26 | 0 | -9360993.26 | 4138160 | 0 | -4138160 |  |  |  | 4138160 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 15 | 2018-10-17 | 2018-10-16 | 52688766.42 | 782387 | [5 empty] | 19429378.5 | 9361764.45 | 52689537.61 | 5019788.5 | Aljazi Project |  |  |  | Al Jazi7 | Aljazi Project7
Al Jazi | 1 | 8 | 13305889.63 | 0 | -13305889.63 | 6905844.19 | 0 | -6905844.19 |  |  |  | 7730375.21 | 2018-10-31 | 2018-10-28 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-06 | 65994656.05 | 684096.75 | [5 empty] | 22966415.34 | 13305889.63 | 65994656.05 | 7730375.21 | Aljazi Project |  |  |  | Al Jazi8 | Aljazi Project8
Al Jazi | 1 | 9 | 11249079.12 | 0 | -11249079.12 | 1762571 | 0 | -1762571 |  |  |  | 3297350.06 | 2018-11-30 | 2018-11-19 | 2018-11-19 | 15 | 2018-12-04 | 2018-11-28 | 77243735.17 | 504071.29 | [5 empty] | 28710343.34 | 11249079.12 | 77243735.17 | 3297350.06 | Aljazi Project |  |  |  | Al Jazi9 | Aljazi Project9
Al Jazi | 1 | 10 | 7201307.23 | 0 | -7201307.23 | 2302251 | 0 | -2302251 |  |  |  | 3398127.58 | 2018-12-31 | 2018-12-04 | 2018-12-04 | 15 | 2018-12-19 | 2018-12-19 | 84445042.4 | 324045.83 | [5 empty] | 32846001.3 | 7201307.23 | 84445042.4 | 3398127.58 | Aljazi Project |  |  |  | Al Jazi10 | Aljazi Project10
Al Jazi | 1 | 11 | 10407080.28 | 0 | -10407080.28 | 3838772.36 | 0 | -3838772.36 |  |  |  | 4227710.49 | 2018-12-31 | 2018-12-24 | 2018-12-24 | 15 | 2019-01-08 | 2019-01-08 | 94852122.68 | 0.001 | [5 empty] | 37611714.98 | 10407080.28 | 94852122.68 | 4227710.49 | Aljazi Project |  |  |  | Al Jazi11 | Aljazi Project11
Al Jazi | 1 | 12 | 8329656 | 0 | -8329656 | 922154 | 0 | -922154 |  |  |  | 2264521.51 | 2019-01-31 | 2019-01-21 | 2019-01-22 | 15 | 2019-02-06 | 2019-02-04 | 103181778.68 | 0.001 | [5 empty] | 42316559.84 | 8329656 | 103181778.68 | 2264521.51 | Aljazi Project |  |  |  | Al Jazi12 | Aljazi Project12
Al Jazi | 1 | 13 | 8749208.76 | 0 | -8749208.76 | 2994292.79 | 0 | -2994292.79 |  |  |  | 3848045.61 | 2019-02-28 | 2019-02-17 | 2019-02-19 | 15 | 2019-03-06 | 2019-03-04 | 111930987.44 | 347539.5 | [5 empty] | 47070296.16 | 8749208.76 | 111930987.44 | 3848045.61 | Aljazi Project |  |  |  | Al Jazi13 | Aljazi Project13
Al Jazi | 1 | 14 | 9382086.37 | 0 | -9382086.37 | 1629015.64 | 0 | -1629015.64 |  |  |  | 1995238.89 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-08 | 121313073.81 | 104261.85 | [5 empty] | 52347380.67 | 9382086.37 | 121313073.81 | 1995238.89 | Aljazi Project |  |  |  | Al Jazi14 | Aljazi Project14
Al Jazi | 1 | 15 | 9011217.19 | 0 | -9011217.19 | 2107757 | 0 | -2107757 |  |  |  | 2738501.15 | 2019-04-30 | 2019-04-21 | 2019-04-24 | 15 | 2019-05-09 | 2019-05-09 | 130324291 | 208523.7 | [5 empty] | 56948226.2 | 9011217.19 | 130324291 | 2738501.15 | Aljazi Project |  |  |  | Al Jazi15 | Aljazi Project15
Al Jazi | 1 | 16 | 9502208.88 | 0 | -9502208.88 | 120989.08 | 0 | -120989.08 |  |  |  | 1009779.23 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-06-01 | 139826499.88 | 0.0001 | [5 empty] | 63851171.86 | 9502208.88 | 139826499.88 | 1009779.23 | Aljazi Project |  |  |  | Al Jazi16 | Aljazi Project16
Al Jazi | 1 | 17 | 7664029.32 | 0 | -7664029.32 | 2935343.72 | 0 | -2935343.72 |  |  |  | 3577364.85 | 2019-06-30 | 2019-06-16 | 2019-06-18 | 15 | 2019-07-03 | 2019-07-06 | 147490529.2 | 0 | [5 empty] | 67191637.78 | 7664029.32 | 147490529.2 | 3577364.85 | Aljazi Project |  |  |  | Al Jazi17 | Aljazi Project17
Al Jazi | 1 | 18 | 7401622.43 | 0 | -7401622.43 | 2748544.1 | 0 | -2748544.1 |  |  |  | 3297235.7 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-07-27 | 154892151.63 | [6 empty] | 70366044.94 | 7401622.43 | 154892151.63 | 3297235.7 | Aljazi Project |  |  |  | Al Jazi18 | Aljazi Project18
Al Jazi | 1 | 19 | 9504587.63 | 0 | -9504587.63 | 3100493.11 | 0 | -3100493.11 |  |  |  | 4336532.29 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 164396739.26 | [6 empty] | 74067058.47 | 9504587.63 | 164396739.26 | 4336532.29 | Aljazi Project |  |  |  | Al Jazi19 | Aljazi Project19
Al Jazi | 1 | 20 | 8799095.49 | 0 | -8799095.49 | 371543.5 | 0 | -371543.5 |  |  |  | 2000000 | 2019-09-30 | 2019-09-30 | 2019-10-07 | 15 | 2019-10-22 | 2019-11-03 | 173195834.75 | [6 empty] | 80216713.09 | 8799095.49 | 173195834.75 | 2000000 | Aljazi Project |  |  |  | Al Jazi20 | Aljazi Project20
Al Jazi | 1 | 21 | 33097306.6205 | 0 | -33097306.6205 | 0.0001 | 0 | -0.0001 |  |  |  | 5243962.1948 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 206293141.3705 | [6 empty] | 93639432.282 | 33097306.6205 | 206293141.3705 | 5243962.1948 | Aljazi Project |  |  |  | Al Jazi21 | Aljazi Project21
Al Jazi | 1 | 22 | 4356240.1195 | 0 | -4356240.1195 | 8591440.49 | 0 | -8591440.49 |  |  |  | 8742870.72 | 2020-04-30 | 2020-04-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 210649381.49 | [7 empty] | 0 | 0 | 0 | Aljazi Project |  |  |  | Al Jazi22 | Aljazi Project22
Al Jazi - Center Zone | 1 | 1 | 2348807.6 | 278661 | -2070146.6 | 14757189.01 | 230795 | -14526394.01 | 14666580.12 |  |  | 90608.89 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-24 | 2348807.6 | [6 empty] | 1554730.83 | 2377467.23 | 2377467.23 | 909309.25 | Aljazi Project |  |  |  | Al Jazi - Center Zone1 | Aljazi Project1
Al Jazi - Center Zone | 1 | 2 | 6291718.01 | 322383 | -5969335.01 | 1686320.29 | 151797.77 | -1534522.52 |  |  |  | 2035039.03 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-05-29 | 8640525.61 | [6 empty] | 4268341.03 | 6291718.01 | 8640525.61 | 2035039.03 | Aljazi Project |  |  |  | Al Jazi - Center Zone2 | Aljazi Project2
Al Jazi - Center Zone | 1 | 3 | 12038668.84 | 121070 | -11917598.84 | 360179.68 | 58174.3 | -302005.38 |  |  |  | 360179.68 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-09-01 | 20679194.45 | [6 empty] | 12373789.15 | 12038969.26 | 20679494.87 | 1152186.95 | Aljazi Project |  |  |  | Al Jazi - Center Zone3 | Aljazi Project3
Al Jazi - Center Zone | 1 | 4 | 4840645.74 | 0 | -4840645.74 | 370581.69 | 0 | -370581.69 |  |  |  | 1090291.72 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 25519840.19 | [6 empty] | 15657190.5 | 4840645.74 | 25519840.19 | 1090291.72 | Aljazi Project |  |  |  | Al Jazi - Center Zone4 | Aljazi Project4
Al Jazi - Center Zone | 1 | 5 | 7051826.31 | 0 | -7051826.31 | 858100 | 0 | -858100 |  |  |  | 1000000 | 2019-09-30 | 2019-09-30 | 2019-10-08 | 15 | 2019-10-23 | 2019-11-03 | 32571666.5 | [6 empty] | 20595342.09 | 7051826.31 | 32571666.5 | 1000000 | Aljazi Project |  |  |  | Al Jazi - Center Zone5 | Aljazi Project5
Al Jazi - Center Zone | 1 | 6 | 6082957.03 | 0 | -6082957.03 | -0.01 | 0 | 0.01 |  |  |  | -2446690.14 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 38654623.53 | [6 empty] | 22479352.29 | 6082957.03 | 38654623.53 | -2446690.14 | Aljazi Project |  |  |  | Al Jazi - Center Zone6 | Aljazi Project6
Al Jazi - Center Zone | 1 | 7 | 966768.0649 | 0 | -966768.0649 | 151431.32 | 0 | -151431.32 |  |  |  | 151431.3187 | 2020-03-31 | 2020-03-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 39621391.5949 | [7 empty] | 0 | 0 | 0 | Aljazi Project |  |  |  | Al Jazi - Center Zone7 | Aljazi Project7
Alfa Lab | 1 | 1 |  | 1403211.67 | 1403211.67 | 1459340 | 1459340 | 0 |  |  |  |  | 2021-10-31 | 2021-10-31 | 2021-12-05 | 30 | 2022-01-04 | [8 empty] | 0 | 0 | 0 | 0 | Alfa New Central Labs |  |  |  | Alfa Lab1 | Alfa New Central Labs1
Allegria-New Modifications | 1 | 1 |  | 0 | 0 | 659568.2 | 0 | -659568.2 |  |  |  |  | 2019-06-30 | 2019-07-02 | 2019-08-22 | 31 | 2019-09-22 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Allegria-New Modifications1 | 01
Astoria - Sharm | 1 | 2 | 1243970 | 401082.65 | -842887.35 | 837813.8 | 269728 | -568085.8 |  |  |  | 836570 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 42 | 2022-08-16 | 2022-07-06 | 1243970 |  |  |  |  | 65308.425 | 65308.425 | 0 | 1243970 | 1243970 | 836570 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm2 | Astoria Sharm elSheikh2
Astoria - Sharm | 1 | 3 | 401082.65 | 2440310 | 2039227.35 | 269728 | 1641108 | 1371380 |  |  |  | 269728 | 2022-07-31 | 2022-07-31 | 2022-08-03 | 42 | 2022-09-14 | 2022-08-09 | 1645052.65 |  | 98567.65 |  |  | 21056.84 | 21056.84 | 0 | 401082.65 | 1645052.65 | 269728 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm3 | Astoria Sharm elSheikh3
Astoria - Sharm | 1 | 4 | 2440310 | 1055208 | -1385102 | 1641108 | 709627 | -931481 |  |  |  | 1641108 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 42 | 2022-10-12 | 2022-09-05 | 4085362.65 |  | 98567.65 |  |  | 128116.275 | 128116.275 | 0 | 2440310 | 4085362.65 | 1641108 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm4 | Astoria Sharm elSheikh4
Astoria - Sharm | 1 | 5 | 1055208 | 314831.49 | -740376.51 | 709627 | 278242.2245 | -431384.7755 |  |  |  | 709627 | 2022-09-30 | 2022-09-30 | 2022-10-04 | 42 | 2022-11-15 | 2022-10-06 | 5140570.65 |  | 98567.65 |  | 33170 | 55398 | 55398 | 0 | 1055208 | 5140570.65 | 709627 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm5 | Astoria Sharm elSheikh5
Astoria - Sharm | 1 | 6 | 314831.49 | 172304.78 | -142526.71 | 244817 | 621397.339 | 376580.339 |  |  |  | 244817 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 42 | 2022-12-09 | 2022-10-30 | 5455402.14 |  | 98567.65 |  |  | 221100 | 221100 | 0 | 314831.49 | 5455402.14 | 244817 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm6 | Astoria Sharm elSheikh6
Astoria - Sharm | 1 | 7 |  | 1116626 | 1116626 | 654151 | 1160163.51 | 506012.51 |  |  |  |  | 2022-11-30 | 2022-11-28 | 2022-11-28 | 42 | 2023-01-09 | [8 empty] | 0 | 0 | 0 | 0 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm7 | Astoria Sharm elSheikh7
Astoria - Sharm | 1 | 8 |  | 0 | 0 | 1160836 | 0 | -1160836 |  |  |  |  | 2023-01-31 | 2023-02-01 | 2023-02-01 | 42 | 2023-03-15 | [8 empty] | 0 | 0 | 0 | 0 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm8 | Astoria Sharm elSheikh8
Astoria Hotel | 1 | 1 | 6707988.52 | 8415906.06 | 1707917.54 | 6511122 | 6441068.119 | -70053.881 | 46039744.5 | 2000000 |  | 4511122 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 42 | 2022-03-29 | 2022-02-28 | 6707988.52 | [6 empty] | 0 | 6707988.52 | 6707988.52 | 4511122 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel1 | Waldorf Astoria Cairo1
Astoria Hotel | 1 | 2 | 3507480.42 | 3507480.42 | 0 | 2448868 | 2448867.881 | -0.119 | 18415897.8 |  |  | 2448868 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 42 | 2022-04-20 | 2022-03-23 | 10215468.94 | 140761.4 |  |  |  | 191180.79 | 191180.79 | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel2 | Waldorf Astoria Cairo2
Astoria Hotel | 1 | 3 | 6522225.37 | 6522225.37 | 0 | 5421697 | 5421697.4285 | 0.4285 | 9207948.9 |  |  | 5421697 | 2022-03-31 | 2022-03-31 | 2022-04-07 | 42 | 2022-05-19 | 2022-04-21 | 16737694.31 | 3185804.68 |  |  |  | 501707.065 | 501707.065 | 0 | 6522225.37 | 16737694.31 | 5421697 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel3 | Waldorf Astoria Cairo3
Astoria Hotel | 1 | 4 | 5466647.24 | 5452379.98 | -14267.26 | 13842213.9 | 4634265 | -9207948.9 |  |  |  | 4634265 | 2022-04-30 | 2022-05-10 | 2022-05-17 | 42 | 2022-06-28 | 2022-05-31 | 22204341.55 | 4790259 | 987281.94 |  |  | 1171022.63 | 1171022.63 | 0 | 5466647.24 | 22204341.55 | 4634265 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel4 | Waldorf Astoria Cairo4
Astoria Hotel | 1 | 5 | 3030560.1014 | 3030560.1 | -0.0014405 | 5818860 | 5818860.175 | 0.175 |  |  |  | 5818860 | 2022-05-31 | 2022-06-01 | 2022-06-05 | 42 | 2022-07-17 | 2022-06-28 | 25234901.6514 | 9900984.5198 | 1091283.222 |  |  | 538643.0456 | 538643.0456 | 0 | 3030560.1014 | 25234901.6514 | 5818860 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel5 | Waldorf Astoria Cairo5
Astoria Hotel | 1 | 6 | 14829494.3486 | 14843761.8 | 14267.4514 | 8446328.13 | 8446327.45 | -0.68 |  |  |  | 8446328.13 | 2022-06-30 | 2022-06-28 | 2022-06-29 | 42 | 2022-08-10 | 2022-07-06 | 40064396 | 11427302 | 2183203.94 |  |  | 2103380.5 | 2103380.5 | 0 | 14829494.3486 | 40064396 | 8446328.13 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel6 | Waldorf Astoria Cairo6
Astoria Hotel | 1 | 7 | 11030217.63 | 14720271.03 | 3690053.4 | 8710615 | 8710614.8515 | -0.1485 |  |  |  | 8710615 | 2022-07-31 | 2022-08-03 | 2022-08-04 | 42 | 2022-09-15 | 2022-08-08 | 51094613.63 | 12186248.36 | 2194500 |  |  | 849101.84 | 849101.84 | 0 | 11030217.63 | 51094613.63 | 8710615 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel7 | Waldorf Astoria Cairo7
Astoria Hotel | 1 | 8 | 14516248.37 | 9001222.98 | -5515025.39 | 2805916 | 2805915.699 | -0.301 |  |  |  | 2805916 | 2022-08-31 | 2022-08-20 | 2022-08-25 | 42 | 2022-10-06 | 2022-09-08 | 65610862 | 13343046 | 6856879.13 |  |  | 3444570.26 | 3444570.26 | 0 | 14516248.37 | 65610862 | 2805916 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel8 | Waldorf Astoria Cairo8
Astoria Hotel | 1 | 9 | 10555127.63 | 16070153.02 | 5515025.39 | 6286403 | 6286403 | 0 |  |  |  | 6286403 | 2022-09-30 | 2022-09-15 | 2022-09-21 | 42 | 2022-11-02 | 2022-09-26 | 76165989.63 | 6497174.95 | 1117474.28 |  |  | 713450.5 | 713450.5 | 0 | 10555127.63 | 76165989.63 | 6286403 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel9 | Waldorf Astoria Cairo9
Astoria Hotel | 1 | 10 | 9739259.16 | 9739259.16 | 0 | 4982321 | 4982321 | 0 |  |  |  | 4982321 | 2022-09-30 | 2022-09-27 | 2022-10-03 | 42 | 2022-11-14 | 2022-10-06 | 85905248.79 | 7583343.27 | 4748282.13 |  |  | 565619.52 | 565619.52 | 0 | 9739259.16 | 85905248.79 | 4982321 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel10 | Waldorf Astoria Cairo10
Astoria Hotel | 1 | 11 | 22454296.86 | 22454296.86 | 0 | 10757000 | 10757000 | 0 |  |  |  | 10757000 | 2022-10-31 | 2022-10-17 | 2022-10-23 | 42 | 2022-12-04 | 2022-10-31 | 108359545.65 | 9996725.48 | 8116978.46 |  |  | 6188712.42 | 6188712.42 | 0 | 22454296.86 | 108359545.65 | 10757000 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel11 | Waldorf Astoria Cairo11
Astoria Hotel | 1 | 12 | 7707398.94 | 7707398.93 | -0.01 | 2603000 | 2602999.7165 | -0.2835 |  |  |  | 2603000 | 2022-10-31 | 2022-10-31 | 2022-11-03 | 42 | 2022-12-15 | 2022-11-10 | 116066944.59 | 7811106.63 | 9547937.37 |  |  | 6484069.92 | 6484069.92 | 0 | 7707398.94 | 116066944.59 | 2603000 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel12 | Waldorf Astoria Cairo12
Astoria Hotel | 1 | 13 | 11273556.71 | 11273556.71 | 0 | 5389256 | 5389256 | 0 |  |  |  | 5389256 | 2022-11-30 | 2022-11-19 | 2022-11-22 | 42 | 2023-01-03 | 2022-11-28 | 127340501.3 | 8209371.3 | 13101564.96 |  |  | 7095844.885 | 7095844.885 | 0 | 11273556.71 | 127340501.3 | 5389256 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel13 | Waldorf Astoria Cairo13
Astoria Hotel | 1 | 14 | 13597376.25 | 13597376.25 | 0 | 6216098 | 6216098 | 0 |  |  |  | 6216098 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2022-12-20 | 140937877.55 | 8044171.13 | 13024305.91 |  |  | 7801447.13 | 7801447.13 | 0 | 13597376.25 | 140937877.55 | 6216098 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel14 | Waldorf Astoria Cairo14
Astoria Hotel | 1 | 15 | 9032753.11 | 9032753.1 | -0.01 | 4185662 | 0 | -4185662 |  |  |  | 4185662 | 2022-12-31 | 2022-12-31 | 2022-12-26 | 42 | 2023-02-06 | 2023-01-25 | 149970630.66 | 8062383.03 | 14785109.7 |  |  | 8276577.26 | 8276577.26 | 0 | 9032753.11 | 149970630.66 | 4185662 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel15 | Waldorf Astoria Cairo15
Astoria Hotel | 1 | 16 | 9372213.83 | 9372213.84 | 0.01 | 3225683 | 0 | -3225683 |  |  |  | 3225683 | 2023-01-31 | 2023-02-08 | 2023-02-09 | 42 | 2023-03-23 | 2023-02-25 | 159342844.49 | 5542006.23 | 15892420.28 |  |  | 8642599.645 | 8642599.645 | 0 | 9372213.83 | 159342844.49 | 3225683 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel16 | Waldorf Astoria Cairo16
Astoria Hotel | 1 | 17 | 7818140.35 | 7818140.35 | 0 | 2804159 | 0 | -2804159 |  |  |  | 2804159 | 2023-02-28 | 2023-03-09 | 2023-03-13 | 42 | 2023-04-24 | 2023-04-02 | 167160984.84 | 3697164.11 | 15797479.81 |  |  | 8960809.91 | 8960809.91 | 0 | 7818140.35 | 167160984.84 | 2804159 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel17 | Waldorf Astoria Cairo17
Astoria Hotel | 1 | 18 | 10420915.55 | 10421093.88 | 178.33 | 4819756 | 3217413.914 | -1602342.086 |  |  |  | 4819756 | 2023-04-30 | 2023-04-19 | 2023-04-19 | 42 | 2023-05-31 | 2023-05-10 | 177581900.39 | 3697164.11 | 22952907.31 |  |  | 9507907.975 | 9507907.975 | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel18 | Waldorf Astoria Cairo18
Astoria Hotel | 1 | 19 | 12873774.1358 | 22057316.41 | 9183542.2742 | 1511334.24 | 1409611.34 | -101722.9 |  |  |  | 1511334.2104 | 2023-05-31 | 2023-06-07 | 2023-06-08 | 42 | 2023-07-20 | 2023-06-19 | 190455674.5258 |  | 28856915.5258 |  |  | 10019924.47 | 10019924.47 | 0 | 12873774.1358 | 190455674.5258 | 1511334.2104 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel19 | Waldorf Astoria Cairo19
Astoria Hotel | 1 | 20 | 3956219.0142 | 7912437.94 | 3956218.9258 | 0.0001 | 0 | -0.0001 |  |  |  | 3400772 | 2023-06-30 | 2023-07-13 | 2023-07-13 | 42 | 2023-08-24 | 2023-08-02 | 194411893.54 | 84871.19 | 34031882.79 |  |  | 10210867.97 | 10210867.97 | 0 | 3956219.0142 | 194411893.54 | 3400772 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel20 | Waldorf Astoria Cairo20
Astoria Hotel | 1 | 21 | 1422437.2 | 1422437.2 | -1.8161e-08 | 0.0001 | 0 | -0.0001 |  |  |  | 854979 | 2023-07-31 | 2023-08-15 | 2023-08-15 | 42 | 2023-09-26 | 2023-09-14 | 195834330.74 | 84871.19 | 37786420.4 |  |  | 10285545.925 | 10285545.925 | 0 | 1422437.2 | 195834330.74 | 854979 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel21 | Waldorf Astoria Cairo21
Astoria Hotel | 1 | 22 | 10800888.71 | 10800888.32 | -0.39 | 1e-05 | 1999998.286 | 1999998.286 |  |  |  | 9327545.58 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 42 | 2023-11-13 | 2023-10-14 | 206635219.45 |  | 43324930.66 |  |  | 10848349.02 | 10848349.02 | 1170750 | 13661357.26 | 209495688 | 44838437.05 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel22 | Waldorf Astoria Cairo22
Astoria Hotel | 1 | 23 | 13277404.55 | 13277404.76 | 0.21 | 17286732.59 | 20506021.05 | 3219288.46 |  |  |  | 17286732.59 | 2023-10-31 | 2023-11-12 | 2023-11-12 | 42 | 2023-12-24 | 2023-11-23 | 219912624 |  | 44280344.8 |  | 10667080 | 10985391.04 | 10985391.04 | 8403824.77 | 13277404.55 | 219912624 | 17286732.59 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel23 | Waldorf Astoria Cairo23
Astoria Hotel | 1 | 24 |  | 10000000 | 10000000 | 10400000 | 22455841.54 | 12055841.54 |  |  |  |  | 2023-11-30 | 2023-11-28 | 2023-11-28 | 42 | 2024-01-09 | [8 empty] | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel24 | Waldorf Astoria Cairo24
Astoria Hotel | 1 | 25 |  | 0 | 0 | 3117985 | 0 | -3117985 |  |  |  |  | 2023-11-30 | 2023-11-30 | 2024-02-07 | 42 | 2024-03-20 | [8 empty] | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel25 | Waldorf Astoria Cairo25
#N/A
Baraka Land Fence | 1 | 1 | 3575400 | 0 | -3575400 | 2467026 | 0 | -2467026 |  |  |  | 2645796 | 2023-10-31 | 2023-10-30 | 2023-11-06 | 42 | 2023-12-18 | 2023-11-06 | 3575400 | [6 empty] | 0 | 3575400 | 3575400 | 2645796 | 0 |  |  |  | Baraka Land Fence1 | 01
Baraka Land Fence | 1 | 2 |  | 0 | 0 | 8497787.46 | 0 | -8497787.46 |  |  |  |  | 2023-11-30 | 2023-11-30 | 2023-12-04 | 42 | 2024-01-15 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Baraka Land Fence2 | 02
Baraka Land Fence | 1 | 3 | 23602796 | 0 | -23602796 | 15418299.78 | 0 | -15418299.78 |  |  |  | 16535567.88 | 2024-02-29 | 2024-03-11 | 2024-03-11 | 42 | 2024-04-22 | 2024-03-20 | 38236396 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Baraka Land Fence3 | 03
Baraka Land Fence | 1 | 4 | 11760884 | 0 | -11760884 | 6072172.61 | 0 | -6072172.61 |  |  |  | 8703054.16 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-05-21 | 49997280 | [6 empty] | 0 | 11760884 | 49997280 | 8703054.16 | 0 |  |  |  | Baraka Land Fence4 | 04
Baraka Land Fence | 1 | 5 | 7617134 | 0 | -7617134 | 0 | 0 | 0 |  |  |  | 5636679.16 | 2024-08-31 | 2024-08-20 | 2024-08-20 | 42 | 2024-10-01 | 2024-08-20 | 57614414 | [6 empty] | 0 | 7617134 | 57614414 | 5636679.16 | 0 |  |  |  | Baraka Land Fence5 | 05
#N/A
Benban - Aswan | 1 | 2 | 22287932.1928 | 0 | -22287932.1928 | 21842173.61 | 0 | -21842173.61 |  |  |  | 21953613.1594 | 2018-06-30 | 2018-07-11 | 2018-07-11 | 60 | 2018-09-09 | 2018-07-26 | 22287932.1928 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan2 | 02
Benban - Aswan | 1 | 3 | 10786951.8956 | 0 | -10786951.8956 | 10577813.02 | 0 | -10577813.02 |  |  |  | 10577813.1577 | 2018-07-31 | 2018-07-31 | 2018-08-05 | 60 | 2018-10-04 | 2018-09-11 | 33074884.0884 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan3 | 03
Benban - Aswan | 1 | 4 | 15307380.738 | 0 | -15307380.738 | 15006351.74 | 0 | -15006351.74 |  |  |  | 15006351.7412 | 2018-08-31 | 2018-08-31 | 2018-09-05 | 60 | 2018-11-04 | 2018-09-20 | 48382264.8264 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan4 | 04
Benban - Aswan | 1 | 5 | 36144803.3444 | 0 | -36144803.3444 | 37440497.15 | 0 | -37440497.15 |  |  |  | 37440886.7444 | 2018-09-30 | 2018-09-30 | 2018-10-08 | 60 | 2018-12-07 | 2018-10-30 | 84527068.1708 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan5 | 05
Benban - Aswan | 1 | 6 | 23770609.3964 | 0 | -23770609.3964 | 23886898.7775 | 0 | -23886898.7775 |  |  |  | 23958997.0448 | 2018-10-31 | 2018-10-31 | 2018-11-11 | 60 | 2019-01-10 | 2018-11-28 | 108297677.5672 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan6 | 06
Benban - Aswan | 1 | 7 | 25005235.2928 | 0 | -25005235.2928 | 25237199.4694 | 0 | -25237199.4694 |  |  |  | 25352621.3844 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 60 | 2019-02-03 | 2018-12-08 | 133302912.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan7 | 07
Benban - Aswan | 1 | 8 | 27760540.7682 | 0 | -27760540.7682 | 28236383.5819 | 0 | -28236383.5819 |  |  |  | 28073115.5265 | 2018-12-31 | 2019-01-03 | 2019-01-03 | 60 | 2019-03-04 | 2019-01-06 | 161063453.6282 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan8 | 08
Benban - Aswan | 1 | 9 | 31169325.9933 | 0 | -31169325.9933 | 33103432.2978 | 0 | -33103432.2978 |  |  |  | 33103432.2978 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 60 | 2019-04-01 | 2019-02-03 | 192232779.6215 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan9 | 09
Benban - Aswan | 1 | 10 | 12107665.0539 | 0 | -12107665.0539 | 12102732.036 | 0 | -12102732.036 |  |  |  | 12014082.9225 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 60 | 2019-05-05 | 2019-03-10 | 204340444.6754 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan10 | 010
Benban - Aswan | 1 | 11 | 2235914.343 | 0 | -2235914.343 | 2222964.1737 | 0 | -2222964.1737 |  |  |  | 2314903.9752 | 2019-03-31 | 2019-03-31 | 2019-04-01 | 60 | 2019-05-31 | 2019-04-07 | 206576359.0184 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan11 | 011
Benban - Aswan | 1 | 12 | 15216014.8348 | 0 | -15216014.8348 | 16625097.353 | 0 | -16625097.353 |  |  |  | 16690051.1455 | 2019-04-30 | 2019-05-01 | 2019-05-01 | 60 | 2019-06-30 | 2019-05-09 | 221792373.8532 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan12 | 012
Benban - Aswan | 1 | 13 | 1724157.1613 | 0 | -1724157.1613 | 36700.14 | 0 | -36700.14 |  |  |  | 36947.2012 | 2019-05-31 | 2019-05-31 | 2019-05-30 | 60 | 2019-07-29 | 2019-07-11 | 223516531.0145 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan13 | 013
Benban - Aswan | 1 | 14 | 30114 | 0 | -30114 | 1174778.08 | 0 | -1174778.08 |  |  |  | 1206378.8856 | 2019-06-30 | 2019-07-02 | 2019-07-02 | 60 | 2019-08-31 | 2019-07-11 | 223546645.0145 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan14 | 014
#N/A
Cement Plant | 1 | 14 | 6421251.87 | 0 | -6421251.87 | 7309725 | 0 | -7309725 |  |  |  | 7309725 | 2017-09-30 | 2017-09-25 | 2017-10-03 | 45 | 2017-11-17 | 2017-10-19 | 219688342.71 | [6 empty] | 0 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant14 | Cement Factory-Beni Suef14
Cement Plant | 1 | 15 | 8583366.193 | 0 | -8583366.193 | 6696657.1239 | 0 | -6696657.1239 |  |  |  | 6696657.1239 | 2017-10-31 | 2017-10-25 | 2017-11-02 | 45 | 2017-12-17 | 2017-11-15 | 228271708.9079 | [6 empty] | 139900 | 8583366.193 | 228271708.9079 | 6696657.1239 | Cement Factory-Beni Suef |  |  |  | Cement Plant15 | Cement Factory-Beni Suef15
Cement Plant | 1 | 16 | 6621784.9509 | 0 | -6621784.9509 | 6990595.3607 | 0 | -6990595.3607 |  |  |  | 6990595.3607 | 2017-11-30 | 2017-11-25 | 2017-12-05 | 45 | 2018-01-19 | 2017-12-14 | 234893493.8588 | [6 empty] | 149900 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant16 | Cement Factory-Beni Suef16
Cement Plant | 1 | 17 | 6642565.2352 | 0 | -6642565.2352 | 7424114.8339 | 0 | -7424114.8339 |  |  |  | 7424114.8339 | 2017-12-31 | 2017-12-25 | 2018-01-04 | 45 | 2018-02-18 | 2018-01-15 | 241536059.094 | [6 empty] | 159900 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant17 | Cement Factory-Beni Suef17
Cement Plant | 1 | 18 | 5438078.8724 | 0 | -5438078.8724 | 6925479.9129 | 0 | -6925479.9129 |  |  |  | 6925479.9129 | 2018-01-31 | 2018-01-25 | 2018-01-23 | 45 | 2018-03-09 | 2018-01-29 | 246974137.9664 | 0 | [5 empty] | 185884 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant18 | Cement Factory-Beni Suef18
Cement Plant | 1 | 19 | 12265173.6434 | 0 | -12265173.6434 | 12791497.7957 | 0 | -12791497.7957 |  |  |  | 12791498.7957 | 2018-02-28 | 2018-02-25 | 2018-02-28 | 45 | 2018-04-14 | 2018-03-17 | 269687311.6098 | 0 | [5 empty] | 195884 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant19 | Cement Factory-Beni Suef19
Cement Plant | 1 | 20 | 4976388.8902 | 0 | -4976388.8902 | 10152661.36 | 0 | -10152661.36 |  |  |  | 10152661.36 | 2018-06-30 | 2018-06-25 | 2018-12-04 |  | 2019-01-30 | 2019-01-20 | 274663700.5 | [7 empty] | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant20 | Cement Factory-Beni Suef20
#N/A
CFC | 1 | 1 | 6586123.18 | 6586123.18 | 0 | 6200445.37 | 6200445.359 | -0.011 | 62134944.55 |  |  | 6200445.37 | 2019-11-30 | 2019-11-25 | 2019-12-10 | 60 | 2020-02-08 | 2020-01-12 | 6586123.18 | 553645.74 | [5 empty] | 0 | 6586123.18 | 6586123.18 | 6200445.37 | CFC Podium 2 |  | 6032477.44 | 553645.74 | CFC1 | CFC Podium 21
CFC | 1 | 2 | 16003200.38 | 15707266.4 | -295933.98 | 17105598.33 | 17105451.15 | -147.18 | 31067472 |  |  | 17323666.18 | 2019-12-31 | 2019-12-25 | 2020-01-09 | 60 | 2020-03-09 | 2020-02-11 | 22589323.56 | 4441799.42 | [5 empty] | 143549.58 | 16003200.38 | 22589323.56 | 17323666.18 | CFC Podium 2 |  | 11561400.96 | 4145865.44 | CFC2 | CFC Podium 22
CFC | 1 | 3 | 16743766.83 | 17039700.42 | 295933.59 | 12263695.26 | 12263842.721 | 147.461 |  |  |  | 12263695.26 | 2020-01-31 | 2020-01-25 | 2020-02-05 | 60 | 2020-04-05 | 2020-03-11 | 39333090.39 | 3876592.5 | [5 empty] | 60000 | 16743766.83 | 39333090.39 | 12263695.26 | CFC Podium 2 |  | 12867174.33 | 4172526.09 | CFC3 | CFC Podium 23
CFC | 1 | 4 | 35226223.2 | 35226223.59 | 0.39 | 32660833.58 | 32660832.57 | -1.01 |  |  |  | 32660833.58 | 2020-02-29 | 2020-02-25 | 2020-03-11 | 60 | 2020-05-10 | 2020-04-02 | 74559313.59 | 8287526.25 | [5 empty] | 60000 | 35226223.2 | 74559313.59 | 32660833.58 | CFC Podium 2 |  | 26938696.95 | 8287526.64 | CFC4 | CFC Podium 24
CFC | 1 | 5 | 30502560.31 | 30502560 | -0.31 | 24749111.95 | 24749111.52 | -0.43 |  |  |  | 24749111.95 | 2020-03-31 | 2020-03-17 | 2020-03-21 | 60 | 2020-05-20 | 2020-04-22 | 105061873.9 | 7691894.47 | [5 empty] | 0 | 30502560.31 | 105061873.9 | 24749111.95 | CFC Podium 2 |  | 22810665.84 | 7691894.16 | CFC5 | CFC Podium 25
CFC | 1 | 6 | 42011127.9851 | 42011128.3 | 0.31492 | 31500278.62 | 31500278.46 | -0.16 |  |  |  | 31500278.62 | 2020-03-31 | 2020-03-25 | 2020-04-07 | 60 | 2020-06-06 | 2020-05-04 | 147073001.8851 | 3638239.2055 | [5 empty] | 60000 | 42011127.9851 | 147073001.8851 | 31500278.62 | CFC Podium 2 |  | 38372888.7796 | 3638239.5204 | CFC6 | CFC Podium 26
CFC | 1 | 7 | 17879880.0649 | 17879880.11 | 0.045077 | 19510038 | 19510039.82 | 1.82 |  |  |  | 19510038 | 2020-04-30 | 2020-04-25 | 2020-05-07 | 60 | 2020-07-06 | 2020-06-04 | 164952881.95 | 9650322 | [5 empty] | 0 | 17879880.0649 | 164952881.95 | 19510038 | CFC Podium 2 |  | 8229558.0649 | 9650322.0451 | CFC7 | CFC Podium 27
CFC | 1 | 8 | 31008098.6054 | 31008097.6 | -1.0054 | 21459124.497 | 21459123.66 | -0.83704 |  |  |  | 21459124.497 | 2020-05-31 | 2020-05-25 | 2020-06-08 | 60 | 2020-08-07 | 2020-07-07 | 195960980.5554 | 4559164.5 | [5 empty] | 0 | 31008098.6054 | 195960980.5554 | 21459124.497 | CFC Podium 2 |  | 26448934.1054 | 4559163.4946 | CFC8 | CFC Podium 28
CFC | 1 | 9 | 29660399.8248 | 29660400.78 | 0.95519 | 24499895.82 | 24499896.0885 | 0.2685 |  |  |  | 24499895.52 | 2020-06-30 | 2020-06-25 | 2020-07-01 | 60 | 2020-08-30 | 2020-07-27 | 225621380.3802 | 4522595.5868 | [5 empty] | 0 | 29660399.8248 | 225621380.3802 | 24499895.52 | CFC Podium 2 |  | 25137804.2381 | 4522596.5419 | CFC9 | CFC Podium 29
CFC | 1 | 10 | 46257284.4262 | 52098964.43 | 5841680.0038 | 39448595.84 | 39448595.5715 | -0.2685 |  |  |  | 39448595.5711 | 2020-07-31 | 2020-07-25 | 2020-07-28 | 60 | 2020-09-26 | 2020-08-26 | 271878664.8064 | [6 empty] | 353049.48 | 46257284.4262 | 271878664.8064 | 39448595.5711 | CFC Podium 2 |  | 46257284.4262 | 5841680.0038 | CFC10 | CFC Podium 210
CFC | 1 | 11 | 22706553.5236 | 16864873.52 | -5841680.0036 | 18030565.73 | 18030566.05 | 0.32 |  |  |  | 18030565.73 | 2020-08-31 | 2020-08-25 | 2020-08-31 | 60 | 2020-10-30 | 2020-09-29 | 294585218.33 | 5378850.75 | [5 empty] | 0 | 22706553.5236 | 294585218.33 | 18030565.73 | CFC Podium 2 |  | 17327702.7736 | -462829.2536 | CFC11 | CFC Podium 211
CFC | 1 | 12 | 35304714.2417 | 34817130.72 | -487583.5217 | 29691194.9757 | 29691195.016 | 0.040322 |  |  |  | 29691194.9757 | 2020-09-30 | 2020-09-25 | 2020-10-07 | 60 | 2020-12-06 | 2020-11-04 | 329889932.5717 | 5192537.25 | [5 empty] | 0 | 35304714.2417 | 329889932.5717 | 29691194.9757 | CFC Podium 2 |  | 30112176.9917 | 4704953.7283 | CFC12 | CFC Podium 212
CFC | 1 | 13 | 13502068.4452 | 13989651.96 | 487583.5148 | 23213756.67 | 23213755.8 | -0.87 |  |  |  | 23213755.7909 | 2020-10-31 | 2020-10-25 | 2020-11-05 | 60 | 2021-01-04 | 2020-12-09 | 343392001.0169 | 19923580.7274 | [5 empty] | 0 | 13502068.4452 | 343392001.0169 | 23213755.7909 | CFC Podium 2 |  | -6421512.2822 | 20411164.2422 | CFC13 | CFC Podium 213
CFC | 1 | 14 | 29172801.673 | 29172801.68 | 0.0070295 | 19708943.72 | 19708944.274 | 0.554 |  |  |  | 19708944.2711 | 2020-11-30 | 2020-11-25 | 2020-12-05 | 60 | 2021-02-03 | 2021-01-11 | 372564802.6899 | 14613590.8525 | [5 empty] | 0 | 29172801.673 | 372564802.6899 | 19708944.2711 | CFC Podium 2 |  | 14559210.8205 | 14613590.8595 | CFC14 | CFC Podium 214
CFC | 1 | 15 | 46288367.9197 | 42273319.3 | -4015048.6197 | 40379659.8985 | 40379659.08 | -0.81848 |  |  |  | 40379659.8985 | 2020-12-31 | 2020-12-25 | 2021-01-06 | 60 | 2021-03-07 | 2021-02-22 | 418853170.6096 | 17260909.7245 | [5 empty] | 1045046 | 46288367.9197 | 418853170.6096 | 40379659.8985 | CFC Podium 2 |  | 29027458.1953 | 13245861.1047 | CFC15 | CFC Podium 215
CFC | 1 | 16 | 25170121.1048 | 29185169.72 | 4015048.6152 | 22871121.16 | 22871121.156 | -0.004 |  |  |  | 22871121.15 | 2021-01-31 | 2021-01-25 | 2021-02-03 | 60 | 2021-04-04 | 2021-03-21 | 444023291.7144 | 19535751.2059 | [5 empty] | 0 | 25170121.1048 | 444023291.7144 | 22871121.15 | CFC Podium 2 |  | 5634369.899 | 23550799.821 | CFC16 | CFC Podium 216
CFC | 1 | 17 | 23196101.9456 | 23196101.95 | 0.0044488 | 15047803.35 | 15047803.35 | 0 |  |  |  | 15047803.36 | 2021-01-31 | 2021-02-10 | 2021-02-15 | 60 | 2021-04-16 | 2021-03-25 | 467219393.66 | 14368442.92 | [5 empty] | 0 | 23196101.9456 | 467219393.66 | 15047803.36 | CFC Podium 2 |  | 8827659.0256 | 14368442.9244 | CFC17 | CFC Podium 217
CFC | 1 | 18 | 16880809.49 | 16880809.49 | 4.8429e-08 | 12196441.12 | 12196441.12 | 0 |  |  |  | 12196441.11 | 2021-02-28 | 2021-02-25 | 2021-03-02 | 60 | 2021-05-01 | 2021-04-06 | 484100203.15 | 14078602.67 | [5 empty] | 0 | 16880809.49 | 484100203.15 | 12196441.11 | CFC Podium 2 |  | 2802206.82 | 14078602.67 | CFC18 | CFC Podium 218
CFC | 1 | 19 | 20398722.16 | 20398722.15 | -0.01 | 14008565.7 | 14008565.7 | 0 |  |  |  | 14008565.71 | 2021-03-31 | 2021-03-10 | 2021-03-17 | 60 | 2021-05-16 | 2021-04-20 | 504498925.31 | 10502130.78 | [5 empty] | 0 | 20398722.16 | 504498925.31 | 14008565.71 | CFC Podium 2 |  | 9896591.38 | 10502130.77 | CFC19 | CFC Podium 219
CFC | 1 | 20 | 23102145.85 | 23105145.86 | 3000.01 | 23721354.77 | 23721354.77 | 0 |  |  |  | 23721354.77 | 2021-03-31 | 2021-03-25 | 2021-03-29 | 60 | 2021-05-28 | 2021-05-24 | 527601071.16 | 16161812.22 | [5 empty] | 992616.34 | 23102145.85 | 527601071.16 | 23721354.77 | CFC Podium 2 |  | 6940333.63 | 16164812.23 | CFC20 | CFC Podium 220
CFC | 1 | 21 | 23568050.8 | 23565050.79 | -3000.01 | 17156725.12 | 19156725.1095 | 1999999.9895 |  |  |  | 17156225.13 | 2021-04-30 | 2021-04-10 | 2021-04-15 | 60 | 2021-06-14 | 2021-06-17 | 551169121.96 | 15788492.2694 | [5 empty] | 3023908.26 | 23568050.8 | 551169121.96 | 17156225.13 | CFC Podium 2 |  | 7779558.5306 | 15785492.2594 | CFC21 | CFC Podium 221
CFC | 1 | 22 | 19833699.32 | 19833699.33 | 0.01 | 13410069.82 | 13410069.82 | 0 |  |  |  | 13410069.82 | 2021-04-30 | 2021-04-25 | 2021-05-06 | 60 | 2021-07-05 | 2021-06-29 | 571002821.28 | 12047992.86 | [5 empty] | 0 | 19833699.32 | 571002821.28 | 13410069.82 | CFC Podium 2 |  | 7785706.46 | 12047992.87 | CFC22 | CFC Podium 222
CFC | 1 | 23 | 19569971.41 | 19569971.41 | -8.9407e-08 | 15440459.23 | 15440458.9205 | -0.3095 |  |  |  | 15440458.92 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 60 | 2021-08-29 | 2021-08-18 | 590572792.69 | 9696296.63 | [5 empty] | 0 | 19569971.41 | 590572792.69 | 15440458.92 | CFC Podium 2 |  | 9873674.78 | 9696296.63 | CFC23 | CFC Podium 223
CFC | 1 | 24 | 14455028.52 | 14455028.51 | -0.01 | 7464480.35 | 9889480.3655 | 2425000.0155 |  |  |  | 7464840.35 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 60 | 2021-09-13 | 2021-09-23 | 605027821.21 | 5161877.98 | [5 empty] | 5612498.72 | 14455028.52 | 605027821.21 | 7464840.35 | CFC Podium 2 |  | 9293150.54 | 5161877.97 | CFC24 | CFC Podium 224
CFC | 1 | 25 | 13190112.67 | 13190112.67 | 3.9116e-08 | 9682524.46 | 9682524.4635 | 0.0035 |  |  |  | 9682524.47 | 2021-07-31 | 2021-08-10 | 2021-08-16 | 60 | 2021-10-15 | 2021-10-25 | 618217933.88 | 1715079.08 | [5 empty] | 0 | 13190112.67 | 618217933.88 | 9682524.47 | CFC Podium 2 |  | 11475033.59 | 1715079.08 | CFC25 | CFC Podium 225
CFC | 1 | 26 | 6460765.9427 | 6460765.95 | 0.0073488 | 2397254.3033 | 4897254.2975 | 2499999.9942 |  |  |  | 2397254.3033 | 2021-08-31 | 2021-08-25 | 2021-09-02 | 60 | 2021-11-01 | 2021-11-18 | 624678699.8227 | 200294.3722 | [5 empty] | 0 | 6460765.9427 | 624678699.8227 | 2397254.3033 | CFC Podium 2 |  | 6260471.5705 | 200294.3795 | CFC26 | CFC Podium 226
CFC | 1 | 27 | 7714993.7673 | 7714993.76 | -0.0073489 | 10793868.64 | 7405131.708 | -3388736.932 |  |  |  | 10793868.55 | 2021-09-30 | 2021-09-10 | 2021-09-19 | 60 | 2021-11-18 | 2021-11-22 | 632393693.59 | [6 empty] | 4776768.68 | 7714993.7673 | 632393693.59 | 10793868.55 | CFC Podium 2 |  | 7714993.7673 | -0.0073489 | CFC27 | CFC Podium 227
CFC | 1 | 28 | 5026145.47 | 5026145.48 | 0.01 | 10367935.31 | 34503065.494 | 24135130.184 |  |  |  | 10367935.42 | 2021-09-30 | 2021-09-14 | 2022-03-07 | 60 | 2022-05-06 | 2022-05-09 | 637419839.06 |  |  |  |  | 16732270.78 | 16732270.78 | 0 | 5026145.47 | 637419839.06 | 10367935.42 | CFC Podium 2 |  | 5026145.47 | 0.01 | CFC28 | CFC Podium 228
CFC | 1 | 29 |  | 0 | 0 | 15034318.2703 | 0 | -15034318.2703 |  |  |  |  | 2021-09-30 | 2021-09-14 | 2022-10-03 | 60 | 2022-12-02 | [8 empty] | 0 | 0 | 0 | 0 | CFC Podium 2 |  |  |  | CFC29 | CFC Podium 229
#N/A
Comoros - Off Shore | 1 | 1 |  | 0 | 0 | 2555388 | 0 | -2555388 |  |  |  |  | 2022-06-30 | 2022-06-23 | 2022-06-23 | 45 | 2022-08-07 | [8 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - Off Shore1 | Le Galawa Hotel Resort1
Comoros - Off Shore | 1 | 2 | 1137692.89 | 0 | -1137692.89 | 910154 | 0 | -910154 |  |  |  | 910154.31 | 2023-01-31 | 2023-01-28 | 2023-03-21 | 45 | 2023-05-05 | 2023-03-21 | 4331928.01 | [6 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - Off Shore2 | Le Galawa Hotel Resort2
Comoros - Off Shore | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 | [8 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - Off Shore3 | Le Galawa Hotel Resort3
Comoros - On Shore | 1 | 1 | 1038550.94 | 0 | -1038550.94 | 1094549.01 | 0 | -1094549.01 |  | 263708.26 |  | 830840.75 | 2023-01-31 | 2023-01-28 | 2023-03-23 | 45 | 2023-05-07 | 2023-03-23 | 1038550.94 | [6 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - On Shore1 | Le Galawa Hotel Resort1
Comoros - On Shore | 1 | 2 | 506813.73 | 0 | -506813.73 | 405450.99 | 0 | -405450.99 |  |  |  | 405450.99 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 | 2023-10-12 | 1545364.67 | [6 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - On Shore2 | Le Galawa Hotel Resort2
#N/A
Creeks - URBN K | 1 | 1 | 6070824.52 | 10988694.51 | 4917869.99 | 10729515 | 10729515 | 0 | 25000000 | 57750000 |  | 10729515.71 | 2023-03-31 | 2023-04-10 | 2023-04-13 | 54 | 2023-06-06 | 2023-05-17 | 6070824.52 | 4917870 |  |  | 1412647.23 | 116454.43 | 116454.43 | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 1152954.52 | 9835739.99 | Creeks - URBN K1 | Creeks URBN-K1
Creeks - URBN K | 1 | 2 | 24895588.2 | 19977718.2 | -4917870 | 3863139 | 3863139 | 0 |  |  |  | 3863139.56 | 2023-04-30 | 2023-05-10 | 2023-05-17 | 54 | 2023-07-10 | 2023-06-01 | 30966412.72 |  |  |  | 9774769.5 | 529152.325 | 529152.325 | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 24895588.2 | -4917870 | Creeks - URBN K2 | Creeks URBN-K2
Creeks - URBN K | 1 | 3 | 40661954.88 | 40661954.89 | 0.01 | 21808950 | 0 | -21808950 |  |  |  | 21808950.42 | 2023-05-31 | 2023-06-10 | 2023-06-13 | 54 | 2023-08-06 | 2023-06-18 | 71628367.6 |  |  |  | 10182390.98 | 1536149.435 | 1536149.435 | 0 | 40661954.88 | 71628367.6 | 21808950.42 | Creeks URBN-K |  | 40661954.88 | 0.01 | Creeks - URBN K3 | Creeks URBN-K3
Creeks - URBN K | 1 | 4 | 25969563.12 | 25969563.12 | 0 | 8830426 | 8830426 | 0 |  |  |  | 8830426.33 | 2023-06-30 | 2023-07-10 | 2023-07-11 | 54 | 2023-09-03 | 2023-07-19 | 97597930.72 |  |  |  | 11215823.74 | 2159552.5 | 2159552.5 | 0 | 0 | 0 | 8830426.33 | Creeks URBN-K |  | 25969563.12 | 0 | Creeks - URBN K4 | Creeks URBN-K4
Creeks - URBN K | 1 | 5 | 21068069.1 | 29818122.52 | 8750053.42 | 13533059 | 13533059 | 0 |  |  |  | 13533059.96 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 54 | 2023-10-07 | 2023-08-23 | 118665999.82 | 8750053.42 |  |  | 12015310.55 | 2666267.23 | 2666267.23 | 0 | 21068069.1 | 118665999.82 | 13533059.96 | Creeks URBN-K |  | 12318015.68 | 17500106.84 | Creeks - URBN K5 | Creeks URBN-K5
Creeks - URBN K | 1 | 6 | 18829649.55 | 21266246.93 | 2436597.38 | 19608847 | 19608846.9472 | -0.0528 |  |  |  | 19608846.96 | 2023-08-31 | 2023-09-13 | 2023-09-14 | 54 | 2023-11-07 | 2023-09-27 | 137495649.37 | 11186650.81 |  |  | 14124627.7 | 3084275.5 | 3084275.5 | 0 | 18829649.55 | 137495649.37 | 19608846.96 | Creeks URBN-K |  | 7642998.74 | 13623248.19 | Creeks - URBN K6 | Creeks URBN-K6
Creeks - URBN K | 1 | 7 | 18845217.25 | 18657407.33 | -187809.92 | 16761479 | 16761479 | 0 |  |  |  | 16761479.32 | 2023-09-30 | 2023-10-13 | 2023-10-15 | 54 | 2023-12-08 | 2023-11-02 | 156340866.62 | 10998840.9 |  |  | 15355016.01 | 3524646.26 | 3524646.26 | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 7846376.35 | 10811030.98 | Creeks - URBN K7 | Creeks URBN-K7
Creeks - URBN K | 1 | 8 | 21024971.71 | 18875663.98 | -2149307.73 | 16707965 | 16707944.9992 | -20.0008 |  |  |  | 16707965 | 2023-10-31 | 2023-10-13 | 2023-11-15 | 54 | 2024-01-08 | 2023-12-02 | 177365838.33 | 8849533.16 | 524238 |  | 16370912 | 8023534 |  | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 12175438.55 | 6700225.43 | Creeks - URBN K8 | Creeks URBN-K8
Creeks - URBN K | 1 | 9 | 18661864.22 | 18620717.8 | -41146.42 | 16997068 | 16997068 | 0 |  |  |  | 16997068.33 | 2023-11-30 | 2023-12-13 | 2023-12-17 | 54 | 2024-02-09 | 2023-12-28 | 196027702.55 | 8808386.74 | 549978 |  | 19145680.99 | 8813027.1 |  | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 9853477.48 | 8767240.32 | Creeks - URBN K9 | Creeks URBN-K9
Creeks - URBN K | 1 | 10 | 32359750.94 | 40231853.45 | 7872102.51 | 19246723 | 19246723 | 0 |  |  |  | 19246723.67 | 2023-12-31 | 2024-01-13 | 2024-01-15 | 54 | 2024-03-09 | 2024-03-15 | 228387453.49 | 16680489.26 | 713540 |  | 34117344 | 9677828.4 |  | 0 | 21707049.44 | 217734751.99 | 18357105.31 | Creeks URBN-K | 2 lines in invoicing | 15679261.68 | 24552591.77 | Creeks - URBN K10 | Creeks URBN-K10
Creeks - URBN K | 1 | 11 | 19399852.91 | 13885723.37 | -5514129.54 | 11569432 | 11569432 | 0 |  |  |  | 11569432.7 | 2024-01-31 | 2024-02-13 | 2024-02-15 | 54 | 2024-04-09 | 2024-03-10 | 247787306.4 | 11166359.72 | 713540 |  | 34372400 | 10635068.27 |  | 0 | 19399852.91 | 247787306.4 | 11569432.7 | Creeks URBN-K |  | 8233493.19 | 5652230.18 | Creeks - URBN K11 | Creeks URBN-K11
Creeks - URBN K | 1 | 12 | 13939506.69 | 10141133.17 | -3798373.52 | 8618325 | 8618325 | 0 |  |  |  | 8618325.74 | 2024-02-29 | 2024-03-13 | 2024-03-16 | 54 | 2024-05-09 | 2024-04-03 | 261726813.09 | 7367986.2 | 777032.73 |  | 35392063.88 | 11277885.86 |  | 0 | 13939506.69 | 261726813.09 | 8618325.74 | Creeks URBN-K |  | 6571520.49 | 3569612.68 | Creeks - URBN K12 | Creeks URBN-K12
Creeks - URBN K | 1 | 13 | 17837569.29 | 23806990.16 | 5969420.87 | 23221916 | 23221916 | 0 |  |  |  | 23221916.29 | 2024-03-31 | 2024-03-13 | 2024-04-17 | 54 | 2024-06-10 | 2024-04-24 | 279564382.38 | 13337407.07 | 777032 |  | 42980609.88 | 11790337 |  | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 4500162.22 | 19306827.94 | Creeks - URBN K13 | Creeks URBN-K13
Creeks - URBN K | 1 | 14 | 11923940.57 | 7646354.5 | -4277586.07 | 6223873.19 | 6223872.155 | -1.035 |  |  |  | 6223873.19 | 2024-04-30 | 2024-05-13 | 2024-05-16 | 54 | 2024-07-09 | 2024-05-22 | 291488322.95 | 9059823 | 777032.73 |  | 43382302 | 12366449.19 |  | 0 | 0 | 0 | 0 | Creeks URBN-K | collection with creeks | 2864117.57 | 4782236.93 | Creeks - URBN K14 | Creeks URBN-K14
Creeks - URBN K | 1 | 15 | 15151516.49 | 10771231.15 | -4380285.34 | 10206848 | 10206848 | 0 |  |  |  | 10206848.68 | 2024-05-31 | 2024-06-13 | 2024-06-11 | 54 | 2024-08-04 | 2024-06-12 | 306639839.44 | 4679535.56 | 777032 |  | 43540689 | 13094578 |  | 0 | 15151516.49 | 306639839.44 | 10206848.68 | Creeks URBN-K |  | 10471980.93 | 299250.22 | Creeks - URBN K15 | Creeks URBN-K15
Creeks - URBN K | 1 | 16 | 8934038.52 | 6516046.61 | -2417991.91 | 6345314 | 6345313.6705 | -0.3295 |  |  |  | 6345313.67 | 2024-06-30 | 2024-07-13 | 2024-07-15 | 54 | 2024-09-07 | 2024-07-29 | 315573877.96 | 2261543.76 | 777032.73 |  | 44277783.1705 | 13525953 |  | 0 | 8934038.52 | 315573877.96 | 6345313.67 | Creeks URBN-K |  | 6672494.76 | -156448.15 | Creeks - URBN K16 | Creeks URBN-K16
Creeks - URBN K | 1 | 17 | 8615746.66 | 8554341.9 | -61404.76 | 8554807 | 8554807.445 | 0.445 |  |  |  | 8554807.45 | 2024-07-31 | 2024-08-13 | 2024-08-15 | 54 | 2024-10-08 | 2024-09-05 | 324189624.62 | 2200139 | 777032 |  | 46059367 | 13867661 |  | 0 | 8615746.66 | 324189624.62 | 8554807.45 | Creeks URBN-K | 17,18 togeather | 6415607.66 | 2138734.24 | Creeks - URBN K17 | Creeks URBN-K17
Creeks - URBN K | 1 | 18 | 9557078 | 9384875.1 | -172202.9 | 9363450 | 9363449.555 | -0.445 |  |  |  | 9363449.62 | 2024-08-31 | 2024-09-13 | 2024-09-15 | 54 | 2024-11-08 | 2024-09-25 | 333746702.62 | 2027936.1 | 777032 |  | 47680035 | 7132240.5 | 7132240.5 | 0 | 9557078 | 333746702.62 | 9363449.62 | Creeks URBN-K |  | 7529141.9 | 1855733.2 | Creeks - URBN K18 | Creeks URBN-K18
Creeks - URBN K | 1 | 19 | 6248543.66 | 0 | -6248543.66 | 0 | 0 | 0 |  |  |  | 6696306.5 | 2024-10-31 | 2024-10-13 | 2024-10-15 | 54 | 2024-12-08 | 2024-11-02 | 339995246.28 | 2452144.43 | 777032 |  | 49061466 | 7253918.5 | 7253918.5 | 0 | 6248543.66 | 339995246.28 | 6696306.5 | Creeks URBN-K |  |  |  | Creeks - URBN K19 | Creeks URBN-K19
Creeks - URBN K | 1 | 20 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-11-30 | 2024-11-13 | 2024-11-14 | 54 | 2025-01-07 | [8 empty] | 0 | 0 | 0 | 0 | Creeks URBN-K |  |  |  | Creeks - URBN K20 | Creeks URBN-K20
#N/A
Damietta Port - Civil | 1 | 2 |  | 1592229.98 | 1592229.98 | 1520770.91 | 1496696.18 | -24074.73 |  |  |  |  | 2024-10-31 | 2024-10-17 | 2024-10-17 | 42 | 2024-11-28 | [8 empty] | 0 | 0 | 0 | 0 | Damietta Container Termin |  |  |  | Damietta Port - Civil2 | Damietta Container Termin2
Damietta Port - Civil | 1 | 3 |  | 0 | 0 | 1496696.18 | 0 | -1496696.18 |  |  |  |  | 2024-10-31 | 2024-10-30 | 2024-10-30 | 42 | 2024-12-11 | [8 empty] | 0 | 0 | 0 | 0 | Damietta Container Termin |  |  |  | Damietta Port - Civil3 | Damietta Container Termin3
Damietta Port - Civil | 1 | 1 |  | 1617841.39 | 1617841.39 | 4058690.9 | 1520770.9061 | -2537919.9939 | 4058690.9 |  |  |  | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 | [8 empty] | 0 | 0 | 0 | 0 | Damietta Container Termin |  |  |  | Damietta Port - Civil1 | Damietta Container Termin1
Damietta Port - Infra | #N/A | 1 |  | 45343.38 | 45343.38 | 6541975.22 | 40545.08 | -6501430.14 | 6541975.22 |  |  |  | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 | [8 empty] | 0 | 0 | 0 | 0 | #N/A |  |  |  | Damietta Port - Infra1 | #N/A
#N/A
DP World Sokhna | 1 | 1 | 21619523.77 | 21619523.77 | 0 | 257561970.68 | 15998139 | -241563831.68 |  |  |  | 16214642.83 | 2019-01-31 | 2019-02-04 | 2019-02-04 | 56 | 2019-04-01 | 2019-02-11 | 21619523.77 | 0 | [5 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna1 | DPW Onshore Port & Terminal1
DP World Sokhna | 1 | 2 | 24408793.91 | 24408793.92 | 0.01 | 18062199.23 | 18062199.23 | 0 |  |  |  | 18306595.43 | 2019-02-28 | 2019-02-28 | 2019-03-04 | 56 | 2019-04-29 | 2019-03-05 | 46028317.68 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna2 | DPW Onshore Port & Terminal2
DP World Sokhna | 1 | 3 | 20754393.51 | 0 | -20754393.51 | 15357944.03 | 0 | -15357944.03 |  |  |  | 15565795.14 | 2019-03-31 | 2019-03-31 | 2019-04-02 | 56 | 2019-05-28 | 2019-04-11 | 66782711.19 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna3 | DPW Onshore Port & Terminal3
DP World Sokhna | 1 | 4 | 37757872.09 | 20754393.51 | -17003478.58 | 27940477.28 | 15357944.03 | -12582533.25 |  |  |  | 28318404.08 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 56 | 2019-06-30 | 2019-05-16 | 104540583.28 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna4 | DPW Onshore Port & Terminal4
DP World Sokhna | 1 | 5 | 17786446.66 | 37757872.1 | 19971425.44 | 13161622.85 | 27940477.28 | 14778854.43 |  |  |  | 13339835 | 2019-05-31 | 2019-05-31 | 2019-06-02 | 56 | 2019-07-28 | 2019-06-16 | 122327029.94 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna5 | DPW Onshore Port & Terminal5
DP World Sokhna | 1 | 6 | 33097932.28 | 84569157.85 | 51471225.57 | 24492163.72 | 13161622.85 | -11330540.87 |  |  |  | 24823449.22 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 56 | 2019-09-07 | 2019-08-06 | 155424962.22 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna6 | DPW Onshore Port & Terminal6
DP World Sokhna | 1 | 7 | 40506959.47 | 33097932.28 | -7409027.19 | 29974844.16 | 24492163.72 | -5482680.44 |  |  |  | 30380219.6 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 56 | 2019-10-01 | 2019-08-22 | 195931921.69 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna7 | DPW Onshore Port & Terminal7
DP World Sokhna | 1 | 8 | 39363674.8 | 79870634.27 | 40506959.47 | 29128813.98 | 59103658.14 | 29974844.16 |  |  |  | 29522756.11 | 2019-08-31 | 2019-09-05 | 2019-09-05 | 56 | 2019-10-31 | 2019-09-17 | 235295596.49 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna8 | DPW Onshore Port & Terminal8
DP World Sokhna | 1 | 9 | 54097551.55 | 54097551.55 | 0 | 40031882.73 | 40031882.73 | 0 |  |  |  | 40573163.66 | 2019-09-30 | 2019-10-06 | 2019-10-08 | 56 | 2019-12-03 | 2019-10-23 | 289393148.04 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna9 | DPW Onshore Port & Terminal9
DP World Sokhna | 1 | 10 | 90533235.47 | 90533235.47 | 0 | 66994289.3 | 66994289.3 | 0 |  |  |  | 67899926.6 | 2019-10-31 | 2019-11-17 | 2019-11-11 | 56 | 2020-01-06 | 2019-11-24 | 379926383.51 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna10 | DPW Onshore Port & Terminal10
DP World Sokhna | 1 | 11 | 102020049.91 | 102020049.91 | 0 | 76494532.33 | 75494532.33 | -1000000 |  |  |  | 76515037.44 | 2019-11-30 | 2019-12-12 | 2019-12-12 | 56 | 2020-02-06 | 2019-12-22 | 481946433.42 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna11 | DPW Onshore Port & Terminal11
DP World Sokhna | 1 | 12 | 148210852.7 | 148210852.69 | -0.01 | 109675422.28 | 109675422.28 | 0 |  |  |  | 111158139.52 | 2019-12-31 | 2020-01-15 | 2020-01-15 | 56 | 2020-03-11 | 2020-02-16 | 630157286.12 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna12 | DPW Onshore Port & Terminal12
DP World Sokhna | 1 | 13 | 124566872.96 | 124566873.87 | 0.91 | 92179486 | 92179486 | 0 |  |  |  | 93425154.72 | 2020-01-31 | 2020-02-15 | 2020-02-18 | 56 | 2020-04-14 | 2020-03-16 | 754724159.08 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna13 | DPW Onshore Port & Terminal13
DP World Sokhna | 1 | 14 | 141052143.0757 | 141052143.07 | -0.0056975 | 104378585.88 | 104378585.87 | -0.01 |  |  |  | 105789107.3061 | 2020-02-29 | 2020-03-17 | 2020-03-17 | 56 | 2020-05-12 | 2020-04-14 | 895776302.1557 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna14 | DPW Onshore Port & Terminal14
DP World Sokhna | 1 | 15 | 110730132.4543 | 110730132.45 | -0.0043024 | 81940298.01 | 81940298.01 | 0 |  |  |  | 83047599.34 | 2020-03-31 | 2020-04-15 | 2020-04-19 | 56 | 2020-06-14 | 2020-05-17 | 1006506434.61 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna15 | DPW Onshore Port & Terminal15
DP World Sokhna | 1 | 16 | 86484919.88 | 86484919.88 | 0 | 63998840.71 | 63998840.71 | 0 |  |  |  | 64863689.91 | 2020-04-30 | 2020-05-19 | 2020-05-19 | 56 | 2020-07-14 | 2020-06-21 | 1092991354.49 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna16 | DPW Onshore Port & Terminal16
DP World Sokhna | 1 | 17 | 56454657.9 | 56454657.9 | -1.0431e-07 | 41776446.85 | 41776446.84 | -0.01 |  |  |  | 42340993.43 | 2020-05-31 | 2020-06-18 | 2020-06-18 | 56 | 2020-08-13 | 2020-07-22 | 1149446012.39 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna17 | DPW Onshore Port & Terminal17
DP World Sokhna | 1 | 18 | 59878397.73 | 59878397.73 | 2.1607e-07 | 44310014.32 | 44310014.32 | 0 |  |  |  | 44908798.3 | 2020-06-30 | 2020-07-23 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-19 | 1209324410.12 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna18 | DPW Onshore Port & Terminal18
DP World Sokhna | 1 | 19 | 34366362.95 | 34366362.95 | 0 | 25431108.58 | 25431108.58 | 0 |  |  |  | 25774772.21 | 2020-07-31 | 2020-08-19 | 2020-08-19 | 56 | 2020-10-14 | 2020-09-16 | 1243690773.07 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna19 | DPW Onshore Port & Terminal19
DP World Sokhna | 1 | 20 | 42996289.46 | 42996289.46 | 0 | 31817254.2 | 31817254.2 | 0 |  |  |  | 32247217.1 | 2020-08-31 | 2020-09-17 | 2020-09-17 | 56 | 2020-11-12 | 2020-10-13 | 1286687062.53 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna20 | DPW Onshore Port & Terminal20
DP World Sokhna | 1 | 21 | 34792442.43 | 34792442.42 | -0.01 | 25746407.39 | 25746407.4 | 0.01 |  |  |  | 26094331.82 | 2020-09-30 | 2020-10-15 | 2020-10-15 | 56 | 2020-12-10 | 2020-10-28 | 1321479504.96 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna21 | DPW Onshore Port & Terminal21
DP World Sokhna | 1 | 22 | 23946448.24 | 23946448.25 | 0.01 | 17720371 | 17720371.7 | 0.7 |  |  |  | 17959836.19 | 2020-10-31 | 2020-11-13 | 2020-11-13 | 56 | 2021-01-08 | 2020-12-20 | 1345425953.2 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna22 | DPW Onshore Port & Terminal22
DP World Sokhna | 1 | 23 | 35871966.38 | 35871966.38 | 1.1921e-07 | 26545255.12 | 26545255.12 | 0 |  |  |  | 26903974.78 | 2020-11-30 | 2020-12-10 | 2020-12-15 | 56 | 2021-02-09 | 2021-01-19 | 1381297919.58 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna23 | DPW Onshore Port & Terminal23
DP World Sokhna | 1 | 24 | 28199021.24 | 28199021.24 | 0 | 20867275.72 | 20867275.72 | 0 |  |  |  | 21149265.93 | 2020-12-31 | 2021-01-10 | 2021-01-10 | 56 | 2021-03-07 | 2021-02-15 | 1409496940.82 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna24 | DPW Onshore Port & Terminal24
DP World Sokhna | 1 | 25 | 13937299.51 | 13937299.51 | 0 | 10313601.64 | 10313601.63 | -0.01 |  |  |  | 10452974.64 | 2021-01-31 | 2021-02-16 | 2021-02-17 | 56 | 2021-04-14 | 2021-03-21 | 1423434240.33 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna25 | DPW Onshore Port & Terminal25
DP World Sokhna | 1 | 26 | 30564756.18 | 30564756.18 | -7.0781e-08 | 22617919.57 | 22617919.57 | 0 |  |  |  | 22923567.13 | 2021-02-28 | 2021-03-17 | 2021-03-25 | 56 | 2021-05-20 | 2021-04-14 | 1453998996.51 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna26 | DPW Onshore Port & Terminal26
DP World Sokhna | 1 | 27 | 21307969.76 | 21307969.76 | 0 | 15718793.62 | 15718793.62 | 0 |  |  |  | 15980977.32 | 2021-03-31 | 2021-04-15 | 2021-04-15 | 56 | 2021-06-10 | 2021-05-19 | 1475306966.27 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna27 | DPW Onshore Port & Terminal27
DP World Sokhna | 1 | 28 | 27099548.45 | 27099548.46 | 0.0099999 | 19977105.85 | 19977105.85 | 0 |  |  |  | 20324661.34 | 2021-05-31 | 2021-05-23 | 2021-05-23 | 56 | 2021-07-18 | 2021-06-24 | 1502406514.72 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna28 | DPW Onshore Port & Terminal28
DP World Sokhna | 1 | 29 | 27690935.6 | 27690935.6 | 1.0058e-07 | 20394668.34 | 20394668.34 | 0 |  |  |  | 20768201.7 | 2021-06-30 | 2021-06-24 | 2021-06-24 | 56 | 2021-08-19 | 2021-07-30 | 1530097450.32 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna29 | DPW Onshore Port & Terminal29
DP World Sokhna | 1 | 30 | 14579181.6 | 14579181.6 | -1.397e-07 | 10739490.38 | 10739490.38 | 0 |  |  |  | 10934386.2 | 2021-07-31 | 2021-07-29 | 2021-07-29 | 56 | 2021-09-23 | 2021-09-07 | 1544676631.92 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna30 | DPW Onshore Port & Terminal30
DP World Sokhna | 1 | 31 | 13597917.64 | 13597917.63 | -0.0099999 | 10014939.05 | 10014939.05 | 0 |  |  |  | 10198438.22 | 2021-08-31 | 2021-09-02 | 2021-09-02 | 56 | 2021-10-28 | 2021-10-11 | 1558274549.56 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna31 | DPW Onshore Port & Terminal31
DP World Sokhna | 1 | 32 | 16694467.33 | 16694467.33 | -1.6019e-07 | 12304801.83 | 12304801.83 | 0 |  |  |  | 12520850.5 | 2021-09-30 | 2021-10-05 | 2021-10-13 | 56 | 2021-12-08 | 2021-12-19 | 1574969016.89 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna32 | DPW Onshore Port & Terminal32
DP World Sokhna | 1 | 33 | 20335452.71 | 20335452.72 | 0.01 | 15048235.01 | 15048235.01 | 0 |  |  |  | 15251589.54 | 2021-12-31 | 2021-12-22 | 2021-12-22 | 56 | 2022-02-16 | 2022-01-11 | 1595304469.6 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna33 | DPW Onshore Port & Terminal33
DP World Sokhna | 1 | 34 | 12548237.84 | 12548237.84 | -1.4901e-07 | 8899770.44 | 8899770.35 | -0.09 |  |  |  | 9025252.81 | 2022-03-31 | 2022-04-06 | 2022-04-06 | 56 | 2022-06-01 | 2022-04-12 | 1607852707.44 |  |  |  |  | 80392635.37 | 80392635.37 | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna34 | DPW Onshore Port & Terminal34
DP World Sokhna | 1 | 35 | 3275655.02 | 3275655.01 | -0.01 | 2915333 | 83471391.43 | 80556058.43 |  |  |  | 2948089.53 | 2022-04-30 | 2022-05-15 | 2022-05-15 | 56 | 2022-07-10 | 2022-06-08 | 1611128362.46 |  | 37040890.72 |  |  | 80556418.125 | 80556418.125 | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna35 | DPW Onshore Port & Terminal35
DP World Sokhna | 1 | 36 |  | 0 | 0 | 80556058.47 | 0 | -80556058.47 |  |  |  |  | 2022-05-31 | 2022-06-08 | 2022-06-08 | 56 | 2022-08-03 | [8 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna36 | DPW Onshore Port & Terminal36
DP World Sokhna | 1 | 37 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-02-28 | 2023-02-19 | 2023-02-19 | 56 | 2023-04-16 | [8 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna37 | DPW Onshore Port & Terminal37
#N/A
DPW - Ph.02 | 1 | 1 | 23907099.3 | 24448993.55 | 541894.25 | 21783711.58 | 21759604.25 | -24107.33 |  |  |  | 21516389.4 | 2023-01-31 | 2023-01-25 | 2023-01-31 | 56 | 2023-03-28 | 2023-02-16 | 23907099.3 |  |  |  |  | 1195354.95 | 1195354.95 | 0 | 23907099.3 | 23907099.3 | 21516389.4 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.021 | DP World Basin 2 Ph21
DPW - Ph.02 | 1 | 2 | 30365704.8 | 62640096.58 | 32274391.78 | 84506660.86 | 19472869.78 | -65033791.08 |  |  |  | 19188213.6 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 56 | 2023-04-27 | 2023-03-22 | 54272804.1 |  |  |  |  | 2713640.25 | 2713640.25 | 0 | 30365704.8 | 54272804.1 | 19188213.6 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.022 | DP World Basin 2 Ph22
DPW - Ph.02 | 1 | 3 | 1809093.47 | 38504541.13 | 36695447.66 | 28493360.54 | 28493360.4387 | -0.1013 |  |  |  | 19827820.72 | 2023-03-31 | 2023-03-25 | 2023-04-03 | 56 | 2023-05-29 | 2023-03-27 | 56081897.57 |  |  |  |  | 2804094.925 | 2804094.925 | 0 | 1809093.47 | 56081897.57 | 19827820.72 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.023 | DP World Basin 2 Ph23
DPW - Ph.02 | 1 | 4 | 38567084.81 | 37025201.2 | -1541883.61 | 27398639.54 | 27398648.888 | 9.348 |  |  |  | 28925313.53 | 2023-04-30 | 2023-04-25 | 2023-05-08 | 56 | 2023-07-03 | 2023-06-08 | 94648982.38 |  |  |  |  | 9464898.3 | 9464898.3 | 0 | 38567084.81 | 94648982.38 | 28925313.53 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.024 | DP World Basin 2 Ph24
DPW - Ph.02 | 1 | 5 | 77833745.07 | 40682207.5 | -37151537.57 | 30104833.54 | 30104833.54 | 0 |  |  |  | 30561302.57 | 2023-05-31 | 2023-05-25 | 2023-06-03 | 56 | 2023-07-29 | 2023-06-25 | 172482727.45 |  |  |  |  | 8624122.5 | 8624122.5 | 0 | 77833745.07 | 172482727.45 | 30561302.57 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.025 | DP World Basin 2 Ph25
DPW - Ph.02 | 1 | 6 | 32227821.34 | 32175841.3 | -51980.04 | 23809772.84 | 23809772.84 | 0 |  |  |  | 24170866.16 | 2023-06-30 | 2023-06-25 | 2023-06-26 | 56 | 2023-08-21 | 2023-07-31 | 204710548.79 |  |  |  |  | 10235527.455 | 10235527.455 | 0 | 32227821.34 | 204710548.79 | 24170866.16 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.026 | DP World Basin 2 Ph26
DPW - Ph.02 | 1 | 7 | 21546507.22 | 21511754.48 | -34752.74 | 15918348.27 | 15918423.282 | 75.012 |  |  |  | 16159880.26 | 2023-07-31 | 2023-07-25 | 2023-08-01 | 56 | 2023-09-26 | 2023-08-28 | 226257056.01 |  |  |  |  | 11312852.785 | 11312852.785 | 0 | 21546507.22 | 226257056.01 | 16159880.26 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.027 | DP World Basin 2 Ph27
DPW - Ph.02 | 1 | 8 | 27781672.69 | 0 | -27781672.69 | 20524928.94 | 0 | -20524928.94 |  |  |  | 20836254.44 | 2023-08-31 | 2023-08-25 | 2023-09-04 | 56 | 2023-10-30 | 2023-09-04 | 254038728.7 |  |  |  |  | 12701936.435 | 12701936.435 | 0 | 27781672.69 | 254038728.7 | 20836254.44 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.028 | DP World Basin 2 Ph28
DPW - Ph.02 | 1 | 9 | 66926760.56 | 27736619.9 | -39190140.66 | 49445572.72 | 20524928.94 | -28920643.78 |  |  |  | 50195070.42 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 56 | 2023-11-28 | 2023-10-31 | 320965489.26 |  |  |  |  | 16048266 | 16048266 | 0 | 66926760.56 | 320965489.26 | 50195070.42 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.029 | DP World Basin 2 Ph29
DPW - Ph.02 | 1 | 10 | 59028304.35 | 66818227.5 | 7789923.15 | 34610141.8 | 49445488.36 | 14835346.56 |  |  |  | 44271228.34 | 2023-10-31 | 2023-10-25 | 2023-11-01 | 56 | 2023-12-27 | 2023-11-29 | 379993793.61 |  |  |  |  | 18999683 | 18999683 | 0 | 59028304.35 | 379993793.61 | 44271228.34 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0210 | DP World Basin 2 Ph210
DPW - Ph.02 | 1 | 11 | 54711779.1 | 58932579.7 | 4220800.6 | 40236573.85 | 43610108.98 | 3373535.13 |  |  |  | 40849045.03 | 2023-11-30 | 2023-11-25 | 2023-11-30 | 56 | 2024-01-25 | 2023-12-31 | 434705572.71 |  |  |  |  | 21735278.62 | 21735278.62 | 0 | 54711779.1 | 434705572.71 | 40849045.03 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0211 | DP World Basin 2 Ph211
DPW - Ph.02 | 1 | 12 | 17644384.08 | 54623534 | 36979149.92 | 15678173.8779 | 40236573.85 | 24558399.9721 |  |  |  | 15879945.92 | 2023-12-31 | 2023-12-25 | 2024-01-01 | 56 | 2024-02-26 | 2024-02-04 | 452349956.79 |  | 25824647.96 |  |  | 22617497.855 | 22617497.855 | 0 | 17644384.08 | 452349956.79 | 15879945.92 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0212 | DP World Basin 2 Ph212
DPW - Ph.02 | 1 | 13 | 13655091.11 | 17615925.7 | 3960834.59 | 18805485.48 | 15678173.87 | -3127311.61 |  |  |  | 18632592.11 | 2024-02-29 | 2024-03-09 | 2024-03-09 | 56 | 2024-05-04 | 2024-04-01 | 466005047.9 |  | 44215690.5 |  |  | 33822947.025 | 33822947.025 | 0 | 13655091.11 | 466005047.9 | 18632592.11 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0213 | DP World Basin 2 Ph213
DPW - Ph.02 | 1 | 14 | -0.0001 | 21130152.28 | 21130152.2801 | 35568315.9 | 18805485.48 | -16762830.42 |  |  |  | 35418927.4 | 2024-02-29 | 2024-03-10 | 2024-03-13 | 56 | 2024-05-08 | 2024-05-14 | 466005047.9 |  | 30459697.9 |  |  | 23300252.395 | 23300252.395 | 0 | -0.0001 | 466005047.9 | 35418927.4 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0214 | DP World Basin 2 Ph214
#N/A
EGAT Pelletizing Plant | 1 | 1 | 5145072.89 | 120259964.16 | 115114891.27 | 16605643.54 | 83153826.7838 | 66548183.2438 | 10000000 |  |  | 4887819.25 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-15 | 5145072.89 | [6 empty] | 0 | 5145072.89 | 5145072.89 | 4887819.25 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant | 1 | 2 | 10496612.58 | 70957037.06 | 60460424.48 | 27019256.26 | 39460085.8972 | 12440829.6372 | 2000000 |  |  | 10124222.67 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 15641685.47 | [6 empty] | 0 | 10496612.58 | 15641685.47 | 10124222.67 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant | 1 | 3 | 4383722.29 | 18154275.33 | 13770553.04 | 59114716.8 | 7687509.5247 | -51427207.2753 | 5000000 |  |  | 4165165.88 | 2021-07-31 | 2021-07-31 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 20025407.76 | [6 empty] | 0 | 4383722.29 | 20025407.76 | 4165165.88 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant | 1 | 4 | 6320391.6 | 11231401.59 | 4911009.99 | 50190590.75 | 10595646.6638 | -39594944.0862 | 20500000 |  |  | 6104444.17 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-27 | 26345799.36 | [6 empty] | 0 | 6320391.6 | 26345799.36 | 6104444.17 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant4 | EGAT Pelletizing Plant4
EGAT Pelletizing Plant | 1 | 5 | 14624189 | 15488991.77 | 864802.77 | 142794796.93 | 14877796.7585 | -127917000.1715 | 28804143.3 |  |  | 14109093.06 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-20 | 40969988.36 | [6 empty] | 0 | 14624189 | 40969988.36 | 14109093.06 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant5 | EGAT Pelletizing Plant5
EGAT Pelletizing Plant | 1 | 6 | 11102739.54 | 12567056.14 | 1464316.6 | 160253665.39 | 11723923.507 | -148529741.883 | 100000000 |  |  | 10385277.48 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-14 | 52072727.9 | [6 empty] | 0 | 11102739.54 | 52072727.9 | 10385277.48 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant6 | EGAT Pelletizing Plant6
EGAT Pelletizing Plant | 1 | 7 | 14005522.66 | 14405251.96 | 399729.3 | 163147791.3 | 13543523.308 | -149604267.992 | 100000000 |  |  | 13304274.45 | 2021-11-30 | 2021-12-05 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-20 | 66078250.56 | [6 empty] | 0 | 14005522.66 | 66078250.56 | 13304274.45 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant7 | EGAT Pelletizing Plant7
EGAT Pelletizing Plant | 1 | 8 | 12121253.25 | 12428479.44 | 307226.19 | 241455129.95 | 11759283.892 | -229695846.058 | 200000000 |  |  | 11576342.49 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-18 | 78199503.81 | [6 empty] | 0 | 12121253.25 | 78199503.81 | 11576342.49 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant8 | EGAT Pelletizing Plant8
EGAT Pelletizing Plant | 1 | 9 | 15797419.96 | 16727419.96 | 930000 | 71197856.25 | 15809146.998 | -55388709.252 | 26309409.25 |  |  | 15046421.2 | 2022-01-31 | 2022-02-05 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 93996923.77 | [6 empty] | 0 | 15797419.96 | 93996923.77 | 15046421.2 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant9 | EGAT Pelletizing Plant9
EGAT Pelletizing Plant | 1 | 10 | 13671163.11 | 20568627.09 | 6897463.98 | 41034098.6 | 19539421.1 | -21494677.5 |  |  |  | 13017478.47 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-04-12 | 107668086.88 | [6 empty] | 0 | 13671163.11 | 107668086.88 | 13017478.47 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant10 | EGAT Pelletizing Plant10
EGAT Pelletizing Plant | 1 | 11 | 14893958.07 | 18647708.09 | 3753750.02 | 34151886.79 | 17868099.3045 | -16283787.4855 |  |  |  | 14300826.37 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-21 | 122562044.95 | [6 empty] | 0 | 14893958.07 | 122562044.95 | 14300826.37 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant11 | EGAT Pelletizing Plant11
EGAT Pelletizing Plant | 1 | 12 | 8116943.05 | 8815883.11 | 698940.06 | 23500000 | 8787503.2355 | -14712496.7645 |  |  |  | 7722438.9 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-23 | 130678988 |  | 5987660 |  |  |  |  | 0 | 8116943.05 | 130678988 | 7722438.9 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant12 | EGAT Pelletizing Plant12
EGAT Pelletizing Plant | 1 | 13 | 13958441.79 | 22599332.95 | 8640891.16 | 53397068.58 | 21971546.5175 | -31425522.0625 |  |  |  | 13285393.01 | 2022-05-31 | 2022-06-05 | 2022-06-12 | 42 | 2022-07-24 | 2022-07-05 | 144637429.79 |  | 6236391 |  |  |  |  | 0 | 13958441.79 | 144637429.79 | 13285393.01 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant13 | EGAT Pelletizing Plant13
EGAT Pelletizing Plant | 1 | 14 | 8283062.84 | 10176085.16 | 1893022.32 | 17794639.63 | 10704026.928 | -7090612.702 |  |  |  | 7877469.99 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-23 | 152920492.63 |  | 6321993.82 |  |  |  |  | 0 | 8283062.84 | 152920492.63 | 7877469.99 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant14 | EGAT Pelletizing Plant14
EGAT Pelletizing Plant | 1 | 15 | 20298475.01 | 20298475.24 | 0.23 | 29186530.1 | 19186530.252 | -9999999.848 |  |  |  | 19389514.84 | 2022-07-31 | 2022-08-10 | 2022-08-15 | 42 | 2022-09-26 | 2022-08-24 | 173218967.64 |  | 7381629.61 |  |  |  |  | 0 | 20298475.01 | 173218967.64 | 19389514.84 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant15 | EGAT Pelletizing Plant15
EGAT Pelletizing Plant | 1 | 16 | 14282809.35 | 14282809.35 | 0 | 23336148.65 | 14096166.6275 | -9239982.0225 |  |  |  | 14238994.72 | 2022-08-31 | 2022-09-10 | 2022-09-20 | 42 | 2022-11-01 | 2022-10-10 | 187501776.99 |  | 14084887.93 |  |  |  |  | 0 | 14282809.35 | 187501776.99 | 14238994.72 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant16 | EGAT Pelletizing Plant16
EGAT Pelletizing Plant | 1 | 17 | 16943574.98 | 37539699.74 | 20596124.76 | 39257376.65 | 15969082.719 | -23288293.931 |  |  |  | 16138518.46 | 2022-10-31 | 2022-10-25 | 2022-10-27 | 42 | 2022-12-08 | 2022-11-23 | 204445351.97 |  | 14506110.34 |  |  |  |  | 0 | 16943574.98 | 204445351.97 | 16138518.46 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant17 | EGAT Pelletizing Plant17
EGAT Pelletizing Plant | 1 | 18 | 13727755.25 | 930523.4 | -12797231.85 | 35000000 | 0 | -35000000 |  |  |  | 12845007.22 | 2022-11-30 | 2022-11-20 | 2022-11-24 | 42 | 2023-01-05 | 2022-12-19 | 218173107.22 |  | 14925857.7 |  |  |  |  | 0 | 13727755.25 | 218173107.22 | 12845007.22 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant18 | EGAT Pelletizing Plant18
EGAT Pelletizing Plant | 1 | 19 | 20329650.19 | 20329650.19 | 0 | 42197351.2 | 19169766.1895 | -23027585.0105 |  |  |  | 19373062.69 | 2022-12-31 | 2022-12-27 | 2022-12-27 | 42 | 2023-02-07 | 2023-02-14 | 238502757.41 |  | 15524807.77 |  |  |  |  | 0 | 20329650.19 | 238502757.41 | 19373062.69 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant19 | EGAT Pelletizing Plant19
EGAT Pelletizing Plant | 1 | 20 |  | 0 | 0 | 40000000 | 0 | -40000000 |  |  |  |  | 2023-03-31 | 2023-03-30 | 2023-03-30 | 42 | 2023-05-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant20 | EGAT Pelletizing Plant20
EGAT Pelletizing Plant | 1 | 21 |  | 37437141.5 | 37437141.5 | 20000000 | 38934627.165 | 18934627.165 |  |  |  |  | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant21 | EGAT Pelletizing Plant21
EGAT Pelletizing Plant | 1 | 22 |  | 0 | 0 | 50000000 | 0 | -50000000 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant22 | EGAT Pelletizing Plant22
EGAT Pelletizing Plant | 1 | 23 | 165505167.47 | 0 | -165505167.47 | 15000000 | 0 | -15000000 |  |  |  | 284426280.45 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 533590339.98 |  | 85167648 |  | 7000000 |  |  | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant23 | EGAT Pelletizing Plant23
EGAT Pelletizing Plant | 1 | 24 | 65988515.57 | 0 | -65988515.57 | 10000000 | 0 | -10000000 |  |  |  | 38934626.46 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 599578855.55 |  | 96518287.15 |  | 7000000 |  |  | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant24 | EGAT Pelletizing Plant24
EGAT Pelletizing Plant | 1 | 25 |  | 0 | 0 | 10000000 | 0 | -10000000 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant25 | EGAT Pelletizing Plant25
EGAT Pelletizing Plant - Admin Building | 1 | 1 | 61566718.68 | 120259964.16 | 58693245.48 | 0 | 83153826.7838 | 83153826.7838 |  |  |  | 27089356.22 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 61566718.68 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Admin Building1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant - Admin Building | 1 | 2 | 53673231.5 | 70957037.06 | 17283805.56 | 0 | 39460085.8972 | 39460085.8972 |  |  |  | 23616221.86 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 115239950.18 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Admin Building2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant - Admin Building | 1 | 3 |  | 18154275.33 | 18154275.33 | 0 | 7687509.5247 | 7687509.5247 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Admin Building3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant - Supply | 1 | 1 | 1390180.36 | 120259964.16 | 118869783.8 | 1570903.44 | 83153826.7838 | 81582923.3438 |  |  |  | 1584805.61 | 2023-07-31 | 2023-07-26 | 2023-07-26 | 42 | 2023-09-06 | 2023-07-26 | 1390180.36 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Supply1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Concrete Infra | 1 | 1 |  | 120259964.16 | 120259964.16 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Concrete Infra1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Mechanical Installation | 1 | 1 |  | 120259964.16 | 120259964.16 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installation1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-MEP | 1 | 1 | 2011978.5 | 120259964.16 | 118247985.66 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  | 2112577.42 | 2021-04-30 | 2021-04-30 | 2021-05-11 | 42 | 2021-06-22 | 2021-08-25 | 2011978.5 | [6 empty] | 0 | 2011978.5 | 2011978.5 | 2112577.42 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-MEP | 1 | 2 | 112937.5 | 70957037.06 | 70844099.56 | 1e-05 | 39460085.8972 | 39460085.8972 |  |  |  | 118584.38 | 2022-02-28 | 2022-02-22 | 2022-02-24 | 42 | 2022-04-07 | 2022-02-22 | 2124916 | [6 empty] | 0 | 112937.5 | 2124916 | 118584.38 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant-MEP | 1 | 3 | 1723067.19 | 18154275.33 | 16431208.14 | 1e-05 | 7687509.5247 | 7687509.5247 |  |  |  | 1329462.73 | 2022-05-31 | 2022-06-05 | 2022-06-06 | 42 | 2022-07-18 | 2023-02-12 | 3847983.19 | [6 empty] | 0 | 1723067.19 | 3847983.19 | 1329462.73 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant-MEP Coordination | 1 | 1 |  | 120259964.16 | 120259964.16 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP Coordination1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Water Tank | 1 | 1 | 3274479.04 | 120259964.16 | 116985485.12 | 3241734.16 | 83153826.7838 | 79912092.6238 |  |  |  | 3438202.99 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-22 | 3274479.04 | [6 empty] | 0 | 3274479.04 | 3274479.04 | 3438202.99 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Water Tank | 1 | 2 | 2028589.79 | 70957037.06 | 68928447.27 | 2008304.1 | 39460085.8972 | 37451781.7972 |  |  |  | 2130019.28 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 5303068.83 | [6 empty] | 0 | 2028589.79 | 5303068.83 | 2130019.28 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant-Water Tank | 1 | 3 | 725357.85 | 18154275.33 | 17428917.48 | 718104.27 | 7687509.5247 | 6969405.2547 |  |  |  | 761625.75 | 2021-07-31 | 2021-08-04 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 6028426.68 | [6 empty] | 0 | 725357.85 | 6028426.68 | 761625.75 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant-Water Tank | 1 | 4 | 766173.48 | 11231401.59 | 10465228.11 | 758512.36 | 10595646.6638 | 9837134.3038 |  |  |  | 804482.15 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-05 | 6794600.16 | [6 empty] | 0 | 766173.48 | 6794600.16 | 804482.15 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank4 | EGAT Pelletizing Plant4
EGAT Pelletizing Plant-Water Tank | 1 | 5 | 923594.34 | 15488991.77 | 14565397.43 | 914358.66 | 14877796.7585 | 13963438.0985 |  |  |  | 969774.05 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-12 | 7718194.5 | [6 empty] | 0 | 923594.34 | 7718194.5 | 969774.05 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank5 | EGAT Pelletizing Plant5
EGAT Pelletizing Plant-Water Tank | 1 | 6 | 1464316.6 | 12567056.14 | 11102739.54 | 1449673.43 | 11723923.507 | 10274250.077 |  |  |  | 1537532.43 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-09 | 9182511.1 | [6 empty] | 0 | 1464316.6 | 9182511.1 | 1537532.43 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank6 | EGAT Pelletizing Plant6
EGAT Pelletizing Plant-Water Tank | 1 | 7 | 399729.3 | 14405251.96 | 14005522.66 | 395732.02 | 13543523.308 | 13147791.288 |  |  |  | 419715.76 | 2021-11-30 | 2021-12-06 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-09 | 9582240.4 | [6 empty] | 0 | 399729.3 | 9582240.4 | 419715.76 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank7 | EGAT Pelletizing Plant7
EGAT Pelletizing Plant-Water Tank | 1 | 8 | 307226.2 | 12428479.44 | 12121253.24 | 304153.94 | 11759283.892 | 11455129.952 |  |  |  | 322587.51 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-06 | 9889466.6 | [6 empty] | 0 | 307226.2 | 9889466.6 | 322587.51 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank8 | EGAT Pelletizing Plant8
EGAT Pelletizing Plant-Water Tank | 1 | 9 | 1064224 | 16727419.96 | 15663195.96 | 967200 | 15809146.998 | 14841946.998 |  |  |  | 1117435.2 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-03-02 | 10953690.6 | [6 empty] | 0 | 1064224 | 10953690.6 | 1117435.2 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank9 | EGAT Pelletizing Plant9
EGAT Pelletizing Plant-Water Tank | 1 | 10 | 3540729.8 | 20568627.09 | 17027897.29 | 3505322.5 | 19539421.1 | 16034098.6 |  |  |  | 3717766.29 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-14 | 14494420.4 | [6 empty] | 0 | 3540729.8 | 14494420.4 | 3717766.29 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank10 | EGAT Pelletizing Plant10
EGAT Pelletizing Plant-Water Tank | 1 | 11 | 3753750.32 | 18647708.09 | 14893957.77 | 3903900.34 | 17868099.3045 | 13964198.9645 |  |  |  | 3941437.84 | 2022-03-31 | 2022-03-05 | 2022-06-06 | 42 | 2022-07-18 | 2022-08-23 | 18248170.72 | [6 empty] | 0 | 3753750.32 | 18248170.72 | 3941437.84 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank11 | EGAT Pelletizing Plant11
EGAT Pelletizing Plant-Water Tank | 1 | 12 |  | 8815883.11 | 8815883.11 | 1e-05 | 8787503.2355 | 8787503.2355 |  |  |  |  | 2022-09-30 | 2022-09-15 | 2022-09-19 | 42 | 2022-10-31 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank12 | EGAT Pelletizing Plant12
EGAT Pelletizing Plant-Water Tank | 1 | 13 |  | 22599332.95 | 22599332.95 | 391272.95 | 21971546.5175 | 21580273.5675 |  |  |  |  | 2022-10-31 | 2022-10-10 | 2022-11-01 | 42 | 2022-12-13 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank13 | EGAT Pelletizing Plant13
EGAT Pelletizing Plant-Water Tank | 1 | 14 |  | 10176085.16 | 10176085.16 | 1e-05 | 10704026.928 | 10704026.928 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank14 | EGAT Pelletizing Plant14
EGAT Pelletizing Plant-Water Tank | 1 | 15 | 0.19 | 20298475.24 | 20298475.05 | 0 | 19186530.252 | 19186530.252 |  |  |  | 2909387.53 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 21082133.03 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank15 | EGAT Pelletizing Plant15
EGAT-Asphalt | 1 | 1 |  | 0 | 0 | 598688 | 0 | -598688 |  |  |  |  | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Asphalt1 | 01
EGAT-Fence | 1 | 1 |  | 0 | 0 | 195752.6 | 0 | -195752.6 |  |  |  |  | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence1 | 01
EGAT-Fence | 1 | 2 | -616810.92 | 0 | 616810.92 | 0.001 | 0 | -0.001 |  |  |  | -575046.5692 | 2019-08-31 | 2019-08-31 | 2019-09-10 | 15 | 2019-09-25 | 2019-10-08 | 18362278.12 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence2 | 02
EGAT-Fence | 1 | 3 |  | 0 | 0 | 695045.6828 | 0 | -695045.6828 |  |  |  |  | 2019-09-30 | 2019-09-30 | 2019-10-14 | 15 | 2019-10-29 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence3 | 03
EGAT-Fence | 1 | 4 |  | 0 | 0 | 2891036.0622 | 0 | -2891036.0622 |  |  |  |  | 2019-10-31 | 2019-12-19 | 2020-02-09 | 15 | 2020-02-24 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence4 | 04
EGAT-HeliPad | 1 | 1 |  | 0 | 0 | 755798.13 | 0 | -755798.13 |  |  |  |  | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-HeliPad1 | 01
EGAT-HeliPad | 1 | 2 |  | 0 | 0 | 500000 | 0 | -500000 |  |  |  |  | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-HeliPad2 | 02
EGAT-Lock & Load | 1 | 1 | 5018202.5 | 5018202.5 | 0 | 10117110.35 | 4717110.345 | -5400000.005 |  |  |  | 4767292.38 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 5018202.5 | [6 empty] | 0 | 5018202.5 | 5018202.5 | 4767292.38 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load1 | EGAT Lock & Load1
EGAT-Lock & Load | 1 | 2 | 2362059.16 | 2362059.16 | 0 | 2773213.88 | 2220335.608 | -552878.272 |  |  |  | 2243956.2 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-06 | 7380261.66 | [6 empty] | 0 | 2362059.16 | 7380261.66 | 2243956.2 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load2 | EGAT Lock & Load2
EGAT-Lock & Load | 1 | 3 | 1772326.51 | 1772326.5 | -0.01 | 1665986.92 | 1665986.905 | -0.015 |  |  |  | 1683710.18 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-12 | 9152588.17 | [6 empty] | 0 | 1772326.51 | 9152588.17 | 1683710.18 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load3 | EGAT Lock & Load3
EGAT-Lock & Load | 1 | 4 |  | 879124 | 879124 | 747255.39 | 826376.56 | 79121.17 |  |  |  |  | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load4 | EGAT Lock & Load4
EGAT-Lock & Load | 1 | 5 | 3180176.34 | 3180176.34 | 0 | 2436487.51 | 2989365.767 | 552878.257 |  |  |  | 3021167.52 | 2022-05-31 | 2022-05-28 | 2022-06-06 | 42 | 2022-07-18 | 2022-06-07 | 13211888.51 | [6 empty] | 0 | 3180176.34 | 13211888.51 | 3021167.52 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load5 | EGAT Lock & Load5
EGAT-Lock & Load | 1 | 6 | 3378839.59 | 3378839.59 | 0 | 3176089.21 | 3176109.2095 | 19.9995 |  |  |  | 3209897.61 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-07-06 | 16590728.1 | [6 empty] | 0 | 3378839.59 | 16590728.1 | 3209897.61 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load6 | EGAT Lock & Load6
EGAT-Lock & Load | 1 | 7 | 1415984.07 | 1415984.07 | -1.8626e-09 | 1319107.49 | 1331025.0235 | 11917.5335 |  |  |  | 1345184.87 | 2022-07-31 | 2022-08-10 | 2022-08-16 | 42 | 2022-09-27 | 2022-08-16 | 18006712.17 | [6 empty] | 0 | 1415984.07 | 18006712.17 | 1345184.87 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load7 | EGAT Lock & Load7
EGAT-Lock & Load | 1 | 8 | 2786604.1 | 2786604.1 | 0 | 2619387.85 | 2619407.855 | 20.005 |  |  |  | 2647273.89 | 2022-08-31 | 2022-09-10 | 2022-09-11 | 42 | 2022-10-23 | 2022-09-11 | 20793316.27 | [6 empty] | 0 | 2786604.1 | 20793316.27 | 2647273.89 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load8 | EGAT Lock & Load8
EGAT-Lock & Load | 1 | 9 | 3980460.75 | 3980460.75 | 0 | 3741613.11 | 3741633.0975 | 19.9875 |  |  |  | 3781437.71 | 2022-09-30 | 2022-09-10 | 2022-10-17 | 42 | 2022-11-28 | 2022-10-18 | 24773777.02 | [6 empty] | 0 | 3980460.75 | 24773777.02 | 3781437.71 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load9 | EGAT Lock & Load9
EGAT-Lock & Load | 1 | 10 | 1157252.56 | 1157252.56 | 0 | 1099389.93 | 1087817.398 | -11572.532 |  |  |  | 1099389.93 | 2022-10-31 | 2022-10-31 | 2022-11-01 | 42 | 2022-12-13 | 2022-11-03 | 25931029.58 | [6 empty] | 0 | 1157252.56 | 25931029.58 | 1099389.93 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load10 | EGAT Lock & Load10
EGAT-Lock & Load | 1 | 11 | 1992889.65 | 1992889.65 | -2.3283e-09 | 1873296.27 | 1873316.2725 | 20.0025 |  |  |  | 1893245.16 | 2022-11-30 | 2022-11-30 | 2022-11-30 | 42 | 2023-01-11 | 2022-12-07 | 27923919.23 | [6 empty] | 0 | 1992889.65 | 27923919.23 | 1893245.16 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load11 | EGAT Lock & Load11
EGAT-Lock & Load | 1 | 12 | 1778896.47 | 1778896.47 | 0 | 1672142.68 | 1672162.6835 | 20.0035 |  |  |  | 1689951.65 | 2022-12-31 | 2022-12-25 | 2022-12-28 | 42 | 2023-02-08 | 2022-12-28 | 29702815.7 | [6 empty] | 0 | 1778896.47 | 29702815.7 | 1689951.65 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load12 | EGAT Lock & Load12
EGAT-Lock & Load | 1 | 13 | 2116780.43 | 2116780.44 | 0.01 | 1e-05 | 1989773.622 | 1989773.622 |  |  |  | 2010941.41 | 2023-01-31 | 2023-01-31 | 2023-02-01 | 42 | 2023-03-15 | 2023-02-07 | 31819596.13 | [6 empty] | 0 | 2116780.43 | 31819596.13 | 2010941.41 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load13 | EGAT Lock & Load13
EGAT-Lock & Load | 1 | 14 | 2768145.62 | 2768145.62 | 0 | 1e-05 | 2602056.8848 | 2602056.8848 |  |  |  | 2629738.34 | 2023-02-28 | 2023-02-28 | 2023-03-02 | 42 | 2023-04-13 | 2023-03-08 | 34587741.75 | [6 empty] | 0 | 2768145.62 | 34587741.75 | 2629738.34 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load14 | EGAT Lock & Load14
EGAT-Lock & Load | 1 | 15 |  | 19312258.25 | 19312258.25 | 1e-05 | 18153522.75 | 18153522.75 |  |  |  |  | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load15 | EGAT Lock & Load15
EGAT-Lock & Load | 1 | 16 |  | 1100000 | 1100000 | 1e-05 | 1134000.01 | 1134000.01 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load16 | EGAT Lock & Load16
EGAT-Lock & Load | 1 | 17 | -100000 | 0 | 100000 | 0 | 0 | 0 |  |  |  | 18153522.75 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-02-28 | 53900000 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load17 | EGAT Lock & Load17
EGAT-Lock & Load | 1 | 18 | 1100000 | 0 | -1100000 | 0 | 0 | 0 |  |  |  | 1134000 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 55000000 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load18 | EGAT Lock & Load18
EGAT-SZ | 1 | 1 | 6085108 | 0 | -6085108 | 4624356.65 | 0 | -4624356.65 |  |  |  | 4624356.65 | 2019-03-31 | 2019-03-27 | 2019-03-27 | 15 | 2019-04-11 | 2019-04-01 | 6085108 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-SZ1 | 01
EGAT-SZ | 1 | 2 |  | 0 | 0 | 10000000 | 0 | -10000000 |  |  |  |  | 2019-03-31 | 2019-04-10 | 2019-04-03 | 15 | 2019-04-18 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-SZ2 | 02
EGAT-SZ | 1 | 3 |  | 0 | 0 | 6070502.71 | 0 | -6070502.71 |  |  |  |  | 2019-06-30 | 2019-06-26 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-SZ3 | 03
EGAT-Warehouse | 1 | 1 |  | 0 | 0 | 923651.335 | 0 | -923651.335 |  |  |  |  | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Warehouse1 | 01
#N/A
EIPICO | 1 | 1 | 9332911.16 | 12192163.2 | 2859252.04 | 180532933.37 | 12050858.57 | -168482074.8 | 83482074.8 |  |  | 12050858.57 | 2022-11-30 | 2022-11-25 | 2022-12-19 | 35 | 2023-01-23 | 2022-12-25 | 9332911.16 | 2859252.04 | 393834.3 |  |  | 304804.08 | 304804.08 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO1 | EPICO 3 Facility1
EIPICO | 1 | 2 | 13142288.21 | 13487203.1 | 344914.89 | 23338534.97 | 13338534.97 | -10000000 |  |  |  | 13338534.97 | 2022-12-31 | 2022-12-25 | 2022-12-27 | 35 | 2023-01-31 | 2023-02-20 | 22475199.37 | 3204166.92 | 795852.42 |  |  | 641984.155 | 641984.155 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO2 | EPICO 3 Facility2
EIPICO | 1 | 3 | 11426647.21 | 17810265.88 | 6383618.67 | 13033885 | 13033885 | 0 |  |  |  | 13033884.61 | 2023-01-31 | 2023-01-25 | 2023-02-12 | 35 | 2023-03-19 | 2023-03-14 | 33901846.58 | 4910817.01 | 1876208.86 |  | 611410.75 | 847546.165 | 847546.165 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO3 | EPICO 3 Facility3
EIPICO | 1 | 4 | 8374674.1725 | 8374674.18 | 0.0075 | 7344659 | 7344658.43 | -0.57 |  |  |  | 7345011.2 | 2023-02-28 | 2023-02-28 | 2023-02-27 | 35 | 2023-04-03 | 2023-03-15 | 42276520.7525 | 6456809.6644 | 3032593.7925 |  | 611410.7518 | 1056913.015 | 1056913.015 | 0 | 8374674.1725 | 42276520.7525 | 7345011.2 | EPICO 3 Facility |  |  |  | EIPICO4 | EPICO 3 Facility4
EIPICO | 1 | 5 | 13210447.2775 | 13210447.27 | -0.0075 | 10064340.12 | 10064340.12 | 0 |  |  |  | 10066271.07 | 2023-03-31 | 2023-03-31 | 2023-03-28 | 35 | 2023-05-02 | 2023-04-10 | 55486968.03 | 6862783.17 | 3640633.73 |  | 4882891.89 | 1387174.2 | 1387174.2 | 0 | 13210447.2775 | 55486968.03 | 10066271.07 | EPICO 3 Facility |  |  |  | EIPICO5 | EPICO 3 Facility5
EIPICO | 1 | 6 | 6910722.77 | 6910722.77 | 0 | 5949568.74 | 5949568.74 | 0 |  |  |  | 5949977.84 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 35 | 2023-06-05 | 2023-05-17 | 62397690.8 | 8009743.26 | 3788186.81 |  | 4882891.89 | 1559942.27 | 1559942.27 | 0 | 6910722.77 | 62397690.8 | 5949977.84 | EPICO 3 Facility |  |  |  | EIPICO6 | EPICO 3 Facility6
EIPICO | 1 | 7 | 1928406.33 | 7955142.87 | 6026736.54 | 6395645.73 | 6395645.73 | 0 |  |  |  | 6395645.73 | 2023-05-31 | 2023-05-30 | 2023-06-13 | 35 | 2023-07-18 | 2023-07-16 | 64326097.13 | 8718966.12 | 6026736.54 |  | 4882891.89 | 1758820.84 | 1758820.84 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO7 | EPICO 3 Facility7
EIPICO | 1 | 8 | 24151774.29 | 18125037.75 | -6026736.54 | 20317361.34 | 20317361.34 | 0 |  |  |  | 20317361.34 | 2023-06-30 | 2023-06-30 | 2023-07-06 | 35 | 2023-08-10 | 2023-08-31 | 88477871.42 | 17971072.1 | 8593156.6 |  | 15010831.83 | 2211946.785 | 2211946.785 | 0 | 24151774.29 | 88477871.42 | 20317779.3 | EPICO 3 Facility |  |  |  | EIPICO8 | EPICO 3 Facility8
EIPICO | 1 | 9 | 35000000 | 35000000 | 0 | 34650000 | 34650000 | 0 |  |  |  | 34650000 | 2023-07-31 | 2023-07-31 | 2023-08-02 | 35 | 2023-09-06 | 2023-08-22 | 123477871.42 | 17971072.1 | 43593156.6 |  | 15010831.83 | 3086946.785 | 3086946.785 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO9 | EPICO 3 Facility9
EIPICO | 1 | 10 | 9818518.79 | 9818518.79 | 0 | 1e-05 | 0 | -1e-05 |  |  |  | 6328465.78 | 2023-07-31 | 2023-07-31 | 2023-08-28 | 35 | 2023-10-02 | 2023-10-29 | 133296390.21 | 16843609 | 47694027.06 |  | 15663610.71 | 3332409.755 | 3332409.755 | 0 | 9818518.79 | 133296390.21 | 6328837.05 | EPICO 3 Facility |  |  |  | EIPICO10 | EPICO 3 Facility10
EIPICO | 1 | 11 | 27259074.64 | 27259074.64 | 0 | 23263190.12 | 23263190.12 | 0 |  |  |  | 30654533.46 | 2023-09-30 | 2023-09-30 | 2023-10-10 | 35 | 2023-11-14 | 2023-11-28 | 160555464.85 | 30897743.79 | 49443090.43 |  | 24919582.39 | 4013886.62 | 4013886.62 | 0 | 27259074.64 | 160555464.85 | 30655535.07 | EPICO 3 Facility |  |  |  | EIPICO11 | EPICO 3 Facility11
EIPICO | 1 | 12 | 13086699.85 | 13086699.86 | 0.01 | 25548194.95 | 25548194.95 | 0 |  |  |  | 25548194.95 | 2023-10-31 | 2023-10-31 | 2023-10-29 | 35 | 2023-12-03 | 2024-01-02 | 173642164.7 | 56153346.77 | 51092750.03 |  | 24919582.39 | 4341054.12 | 4341054.12 | 0 | 13086699.85 | 173642164.7 | 28595406.99 | EPICO 3 Facility |  |  |  | EIPICO12 | EPICO 3 Facility12
EIPICO | 1 | 13 | 50645327.08 | 50645327.08 | 0 | 2882568.41 | 2882568.41 | 0 |  |  |  | 3870916.75 | 2023-11-30 | 2023-11-30 | 2023-12-03 | 35 | 2024-01-07 | 2024-01-01 | 224287491.78 | 34066592.92 | 51710056.53 |  | 25596151.45 | 5607188.795 | 5607188.795 | 1e-05 | 50645387.03 | 224287551.73 | 3870961.12 | EPICO 3 Facility |  |  |  | EIPICO13 | EPICO 3 Facility13
EIPICO | 1 | 14 | 69127504.85 | 69127444.9 | -59.95 | 26305980.07 | 36305980.07 | 10000000 |  |  |  | 26305980.07 | 2023-12-31 | 2023-12-31 | 2024-01-06 | 35 | 2024-02-10 | 2024-03-07 | 293414996.63 | 36975442.25 | 57799027.37 |  | 60908341.96 | 7335374.915 | 7335374.915 | 0 | 69127444.9 | 293414996.63 | 26305980.07 | EPICO 3 Facility |  |  |  | EIPICO14 | EPICO 3 Facility14
EIPICO | 1 | 15 | 41894786.25 | 41894786.25 | 0 | 29236256.89 | 29236255.9825 | -0.9075 |  |  |  | 29236256.02 | 2024-01-31 | 2024-01-31 | 2024-02-04 | 35 | 2024-03-10 | 2024-03-20 | 335309782.88 | 34393385.98 | 69350170.39 |  | 63104446.32 | 8382744.57 | 8382744.57 | 0 | 41894786.25 | 335309782.88 | 58472512.04 | EPICO 3 Facility |  |  |  | EIPICO15 | EPICO 3 Facility15
EIPICO | 1 | 16 | 54812520.11 | 54812520.18 | 0.07 | 26363887.4 | 26363887.4 | 0 |  |  |  | 26365248.98 | 2024-03-31 | 2024-03-31 | 2024-04-03 | 35 | 2024-05-08 | 2024-04-24 | 390122302.99 | 33031508.83 | 74589819.54 |  | 94064398.16 | 9753057.575 | 9753057.575 | 0 | 54812520.11 | 390122302.99 | 26365248.98 | EPICO 3 Facility |  |  |  | EIPICO16 | EPICO 3 Facility16
EIPICO | 1 | 17 | 30260072.01 | 30615959.94 | 355887.93 | 13161378.75 | 13161378.737 | -0.013 |  |  |  | 13161378 | 2024-04-30 | 2024-04-30 | 2024-05-28 | 35 | 2024-07-02 | 2024-06-13 | 420382375 | 32932557 | 81926235 |  | 110270621 | 10518279.5 | 10518279.5 | 0 | 30260072.01 | 420382375 | 13161378 | EPICO 3 Facility |  |  |  | EIPICO17 | EPICO 3 Facility17
EIPICO | 1 | 18 | 61471115.83 | 61115227.87 | -355887.96 | 35188037.3 | 35188037.3 | 0 |  |  |  | 38010351.15 | 2024-06-30 | 2024-06-30 | 2024-07-15 | 35 | 2024-08-19 | 2024-07-30 | 481853490.83 | 27876972.92 | 86364959.21 |  | 143970319.09 | 12046337.27 | 12046337.27 | 0 | 61471115.83 | 481853490.83 | 38010351.15 | EPICO 3 Facility |  |  |  | EIPICO18 | EPICO 3 Facility18
EIPICO | 1 | 19 | 35463786.17 | 35463786.32 | 0.15 | 22436578.36 | 22436578.356 | -0.004 |  |  |  | 22436578.36 | 2024-08-31 | 2024-08-31 | 2024-09-03 | 35 | 2024-10-08 | 2024-10-26 | 517317277 | 23341078 | 95950976 |  | 145234855 | 12932931.5 | 12932931.5 | 17754935 | 35463786.17 | 517317277 | 29978125.14 | EPICO 3 Facility |  |  |  | EIPICO19 | EPICO 3 Facility19
EIPICO | 1 | 20 |  | 71749002.23 | 71749002.23 | 20000000 | 62225320.01 | 42225320.01 |  |  |  |  | 2024-09-30 | 2024-09-30 | 2024-10-29 | 35 | 2024-12-03 | [8 empty] | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO20 | EPICO 3 Facility20
#N/A
El Sewedy Uni.-PKG.1 | 1 | 1 | 2762087.0381 | 1805053.36 | -957033.6781 | 1917993.24 | 1727255.568 | -190737.672 |  |  |  | 2002513.1 | 2018-07-31 | 2018-08-31 | 2018-09-03 | 4 | 2018-10-19 | 2018-10-15 | 2762087.0381 | 0 | [5 empty] | 0 | 2762087.0381 | 2762087.0381 | 2002513.1 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.11 | Elsewedy Univ - Enabling Works1
El Sewedy Uni.-PKG.1 | 1 | 2 | 1370079.6319 | 9832451.04 | 8462371.4081 | 881744.36 | 9096115.222 | 8214370.862 |  |  |  | 951383.3 | 2018-09-30 | 2018-10-15 | 2018-10-18 | 4 | 2018-10-29 | 2018-10-25 | 4132166.67 | [6 empty] | 0 | 1370079.6319 | 4132166.67 | 951383.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.12 | Elsewedy Univ - Enabling Works2
El Sewedy Uni.-PKG.1 | 1 | 3 | 1749696.33 | 10413552.39 | 8663856.06 | 1214989 | 10213661.2305 | 8998672.2305 |  |  |  | 1214989.1272 | 2018-10-31 | 2018-11-15 | 2018-11-14 | 4 | 2018-12-01 | 2018-11-27 | 5881863 | [6 empty] | 0 | 1749696.33 | 5881863 | 1214989.1272 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.13 | Elsewedy Univ - Enabling Works3
El Sewedy Uni.-PKG.1 | 1 | 4 | 1734033.5 | 2548899.1 | 814865.6 | 1204112.8596 | 1785482.76 | 581369.9004 |  |  |  | 1204112.8596 | 2018-11-30 | 2018-11-30 | 2018-12-02 | 4 | 2018-12-14 | 2018-12-10 | 7615896.5 | [6 empty] | 0 | 807197.6524 | 7615896.5 | 1204112.8596 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.14 | Elsewedy Univ - Enabling Works4
El Sewedy Uni.-PKG.1 | 1 | 5 | 267331.59 | 26249903.38 | 25982571.79 | 185635.0557 | 125621602.973 | 125435967.9173 |  |  |  | 185635.0557 | 2018-12-31 | 2018-12-15 | 2018-12-17 | 4 | 2018-12-22 | 2018-12-18 | 7883228.09 | [6 empty] | 0 | 267331.59 | 7883228.09 | 185635.0557 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.15 | Elsewedy Univ - Enabling Works5
El Sewedy Uni.-PKG.1 | 1 | 6 | 205504.28 | 41901505.6 | 41696001.32 | 142702.12 | 27378382.8135 | 27235680.6935 |  |  |  | 142702.1677 | 2018-12-31 | 2018-12-25 | 2018-12-29 | 4 | 2019-01-12 | 2019-01-08 | 8088732.37 | [6 empty] | 0 | 205504.28 | 8088732.37 | 142702.1677 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.16 | Elsewedy Univ - Enabling Works6
El Sewedy Uni.-PKG.1 | 1 | 7 | 410253.12 | 46029832.92 | 45619579.8 | 284879.77 | 39973819.3095 | 39688939.5395 |  |  |  | 284879.76 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 4 | 2019-01-26 | 2019-01-22 | 8498985.49 | [6 empty] | 0 | 410253.12 | 8498985.49 | 284879.76 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.17 | Elsewedy Univ - Enabling Works7
El Sewedy Uni.-PKG.1 | 1 | 8 | 339720.12 | 23803040.59 | 23463320.47 | 235901.48 | 14971243.825 | 14735342.345 |  |  |  | 235901.6556 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 4 | 2019-02-10 | 2019-02-06 | 8838705.61 | [6 empty] | 0 | 339720.12 | 8838705.61 | 235901.6556 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.18 | Elsewedy Univ - Enabling Works8
El Sewedy Uni.-PKG.1 | 1 | 9 | 104805.89 | 43474156.5 | 43369350.61 | 72777.3 | 19546532.045 | 19473754.745 |  |  |  | 72777.3 | 2019-03-31 | 2019-03-25 | 2019-03-26 | 4 | 2019-04-14 | 2019-04-10 | 8943511.5 | [6 empty] | 0 | 104805.89 | 8943511.5 | 72777.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.19 | Elsewedy Univ - Enabling Works9
El Sewedy Uni.-PKG.1 | 1 | 10 | 2360 | 30617684.7 | 30615324.7 | -8913.92 | 20919758.826 | 20928672.746 |  |  |  | -8913.92 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 4 | 2019-08-11 | 2019-08-07 | 8945871.5 | [6 empty] | 0 | 2360 | 8945871.5 | -8913.92 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.110 | Elsewedy Univ - Enabling Works10
El Sewedy Uni.-PKG.2 | 1 | 1 | 4165158.06 | 1805053.36 | -2360104.7 | 3110956.56 | 1727255.568 | -1383700.992 |  |  |  | 3110956.56 | 2018-09-30 | 2018-09-25 | 2018-09-27 | 17 | 2018-10-14 | 2018-10-18 | 4165158.06 | [6 empty] | 0 | 4165158.06 | 4165158.06 | 3110956.56 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.21 | Elsewedy Univ - Enabling Works1
El Sewedy Uni.-PKG.2 | 1 | 2 | 5976536.23 | 9832451.04 | 3855914.81 | 6754267.57 | 9096115.222 | 2341847.652 |  |  |  | 6088678.96 | 2018-10-31 | 2018-10-31 | 2018-10-31 | 17 | 2018-11-17 | 2018-11-08 | 10141694.29 | [6 empty] | 0 | 5976536.23 | 10141694.29 | 6088678.96 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.22 | Elsewedy Univ - Enabling Works2
El Sewedy Uni.-PKG.2 | 1 | 3 | 4458367.3606 | 10413552.39 | 5955185.0294 | 3212953.45 | 10213661.2305 | 7000707.7805 |  |  |  | 3212953.6168 | 2018-11-30 | 2018-11-25 | 2018-11-27 | 17 | 2018-12-14 | 2018-12-10 | 14600061.6506 | 2173392 | [5 empty] | 0 | 0 | 0 | 0 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.23 | Elsewedy Univ - Enabling Works3
El Sewedy Uni.-PKG.2 | 1 | 4 | 5121900.2295 | 2548899.1 | -2573001.1295 | 3208255.76 | 1785482.76 | -1422773 |  |  |  | 3208255.2815 | 2018-12-31 | 2018-12-25 | 2018-12-31 | 17 | 2019-01-17 | 2019-01-10 | 19721961.8801 | 1556100 | [5 empty] | 0 | 5121900.2295 | 19721961.8801 | 3208255.2815 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.24 | Elsewedy Univ - Enabling Works4
El Sewedy Uni.-PKG.2 | 1 | 5 | 8018043.8084 | 26249903.38 | 18231859.5716 | 4527299.68 | 125621602.973 | 121094303.293 |  |  |  | 4527299.6695 | 2019-01-31 | 2019-01-25 | 2019-01-31 | 17 | 2019-02-17 | 2019-02-10 | 27740005.6885 | [6 empty] | 0 | 8018043.8084 | 27740005.6885 | 4527299.6695 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.25 | Elsewedy Univ - Enabling Works5
El Sewedy Uni.-PKG.2 | 1 | 6 | 8105230.8115 | 41901505.6 | 33796274.7885 | 7457797.24 | 27378382.8135 | 19920585.5735 |  |  |  | 7457797.2 | 2019-02-28 | 2019-02-25 | 2019-03-02 | 17 | 2019-03-19 | 2019-03-11 | 35845236.5 | 1404000 | [5 empty] | 0 | 8105230.8115 | 35845236.5 | 7457797.2 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.26 | Elsewedy Univ - Enabling Works6
El Sewedy Uni.-PKG.2 | 1 | 7 | 4929812 | 46029832.92 | 41100020.92 | 2278076.64 | 39973819.3095 | 37695742.6695 |  |  |  | 2278076.6 | 2019-03-31 | 2019-03-25 | 2019-04-08 | 17 | 2019-04-25 | 2019-04-10 | 40775048.5 | 0 | [5 empty] | 0 | 4929812 | 40775048.5 | 2278076.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.27 | Elsewedy Univ - Enabling Works7
El Sewedy Uni.-PKG.2 | 1 | 8 | 1755356.8 | 23803040.59 | 22047683.79 | 2625161.63 | 14971243.825 | 12346082.195 |  |  |  | 2625161.5 | 2019-05-31 | 2019-05-23 | 2019-05-23 | 17 | 2019-06-09 | 2019-08-07 | 42530405.3 | [6 empty] | 50000 | 1755356.8 | 42530405.3 | 2625161.5 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.28 | Elsewedy Univ - Enabling Works8
El Sewedy Uni.-PKG.2 | 1 | 9 | 0 | 43474156.5 | 43474156.5 | 1116423 | 19546532.045 | 18430109.045 |  |  |  | 1116423.1 | 2020-03-31 | 2020-07-31 | 2020-03-22 |  | 2020-03-31 | 2020-03-23 | 42530405.3 | [6 empty] | 0 | 0 | 0 | 1116423.1 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.29 | Elsewedy Univ - Enabling Works9
El Sewedy Uni.-PKG.3 | 1 | 1 | 1805053.3662 | 1805053.36 | -0.00625 | 41698321.35 | 1727255.568 | -39971065.782 | 24971065.75 | 15000000 |  | 1727255.5662 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 14 | 2019-02-14 | 2019-02-18 | 1805053.3662 | [6 empty] | 0 | 1805053.3662 | 1805053.3662 | 1727255.5662 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.31 | Elsewedy Univ - Enabling Works1
El Sewedy Uni.-PKG.3 | 1 | 2 | 3340179.702 | 9832451.04 | 6492271.338 | 11185421.17 | 9096115.222 | -2089305.948 | 8000000 |  |  | 3185421.0011 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 14 | 2019-02-16 | 2019-02-19 | 3340179.702 | [6 empty] | 0 | 3340179.702 | 3340179.702 | 3185421.0011 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.32 | Elsewedy Univ - Enabling Works2
El Sewedy Uni.-PKG.3 | 1 | 3 | 2400436.8318 | 10413552.39 | 8013115.5582 | 17785718.63 | 10213661.2305 | -7572057.3995 | 12000000 |  |  | 5785718.6 | 2019-02-28 | 2019-02-21 | 2019-02-27 | 14 | 2019-03-13 | 2019-03-12 | 7545669.9 | 3477943.8 | [5 empty] | 0 | 2400436.8318 | 7545669.9 | 5785718.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.33 | Elsewedy Univ - Enabling Works3
El Sewedy Uni.-PKG.3 | 1 | 4 | 6026842.9 | 2548899.1 | -3477943.8 | 6716669.76 | 1785482.76 | -4931187 | 4931187 |  |  | 1785483.1 | 2019-03-31 | 2019-03-21 | 2019-03-24 | 14 | 2019-04-07 | 2019-04-10 | 13572512.8 | 4077447.9 | [5 empty] | 0 | 6026842.9 | 13572512.8 | 1785483.1 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.34 | Elsewedy Univ - Enabling Works4
El Sewedy Uni.-PKG.3 | 1 | 5 | 27458064.6 | 26249903.38 | -1208161.22 | 24218860.6 | 125621602.973 | 101402742.373 |  |  |  | 24218860.6 | 2019-04-30 | 2019-04-21 | 2019-04-23 | 14 | 2019-05-07 | 2019-05-05 | 41030577.4 | 16291927.3 | [5 empty] | 0 | 27458064.6 | 41030577.4 | 24218860.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.35 | Elsewedy Univ - Enabling Works5
El Sewedy Uni.-PKG.3 | 1 | 6 | 30765208.3 | 41901505.6 | 11136297.3 | 26716091.61 | 27378382.8135 | 662291.2035 |  |  |  | 26656864.3 | 2019-05-31 | 2019-05-25 | 2019-06-01 | 14 | 2019-06-15 | 2019-06-16 | 71795785.7 | 10815243.6 | [5 empty] | 0 | 30765208.3 | 71795785.7 | 26656864.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.36 | Elsewedy Univ - Enabling Works6
El Sewedy Uni.-PKG.3 | 1 | 7 | 41332921.1 | 46029832.92 | 4696911.82 | 22410862.51 | 39973819.3095 | 17562956.7995 |  |  |  | 22410862.51 | 2019-06-30 | 2019-07-04 | 2019-07-08 | 14 | 2019-07-22 | 2019-07-25 | 113128706.8 | 20405227.9 | [5 empty] | 0 | 41332921.1 | 113128706.8 | 22410862.51 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.37 | Elsewedy Univ - Enabling Works7
El Sewedy Uni.-PKG.3 | 1 | 8 | 23588218.3 | 23803040.59 | 214822.29 | 12292368.36 | 14971243.825 | 2678875.465 |  |  |  | 13598061.6 | 2019-07-31 | 2019-07-31 | 2019-08-08 | 14 | 2019-08-22 | 2019-08-24 | 136716925.1 | 16590818.6 | [5 empty] | 0 | 23588218.3 | 136716925.1 | 13598061.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.38 | Elsewedy Univ - Enabling Works8
El Sewedy Uni.-PKG.3 | 1 | 9 | 30130968 | 43474156.5 | 13343188.5 | 19287810.69 | 19546532.045 | 258721.355 |  |  |  | 19410255.3 | 2019-08-31 | 2019-08-21 | 2019-08-24 | 14 | 2019-09-07 | 2019-08-28 | 166847893.1 | 4696608.5 | [5 empty] | 0 | 30130968 | 166847893.1 | 19410255.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.39 | Elsewedy Univ - Enabling Works9
El Sewedy Uni.-PKG.3 | 1 | 10 | 28039187.7 | 30617684.7 | 2578497 | 20919758.8 | 20919758.826 | 0.026 |  |  |  | 20919758.8 | 2019-08-31 | 2019-09-10 | 2019-09-16 | 14 | 2019-09-30 | 2019-09-29 | 194887080.8 | 1904733.1 | [5 empty] | 0 | 28039187.7 | 194887080.8 | 20919758.8 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.310 | Elsewedy Univ - Enabling Works10
El Sewedy Uni.-PKG.3 | 1 | 11 | 16304632.1 | 17614054.86 | 1309422.76 | 2318161.39 | 16620031.47 | 14301870.08 |  |  |  | 2318168.2 | 2019-10-31 | 2019-10-31 | 2019-12-22 | 14 | 2020-01-05 | 2020-01-01 | 211191712.9 | [6 empty] | 3221774.75 | 0 | 0 | 0 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.311 | Elsewedy Univ - Enabling Works11
El Sewedy Uni.-PKG.3 | 1 | 12 | 0 | 0 | 0 | 1515470 | 0 | -1515470 |  |  |  | 1515470 | 2019-10-31 | 2019-10-31 | 2020-06-08 | 14 | 2020-06-22 | 2020-06-21 | 211191712.9 | [6 empty] | 1706304.8 | 0 | 0 | 1515470 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.312 | Elsewedy Univ - Enabling Works12
El Sewedy Uni.-PKG.3 | 1 | 13 |  | 0 | 0 | 6845790.3 | 0 | -6845790.3 |  |  |  |  | 2020-09-30 | 2020-09-17 | 2020-11-15 | 14 | 2020-11-29 | [8 empty] | 0 | 0 | 0 | 0 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.313 | Elsewedy Univ - Enabling Works13
#N/A
Elco Steel | 1 | 1 | 17022109.47 | 0 | -17022109.47 | 13532577.04 | 0 | -13532577.04 |  |  |  | 13617687.58 | 2017-09-30 | 2017-10-01 | 2017-10-01 | 15 | 2017-10-16 | 2017-10-08 | 17022109.47 | [6 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel1 | Substation Elco Steel1
Elco Steel | 1 | 2 | 54045554.24 | 1669926.8 | -52375627.44 | 42881105.07 | 1160599.13 | -41720505.94 |  |  |  | 42881105.07 | 2017-10-31 | 2017-10-25 | 2017-10-25 | 15 | 2017-11-09 | 2017-10-29 | 71067663.71 | [6 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel2 | Substation Elco Steel2
Elco Steel | 1 | 3 | 68968024.81 | 2658220.39 | -66309804.42 | 54829579.72 | 1834172.07 | -52995407.65 |  |  |  | 54829579.72 | 2017-11-30 | 2017-11-30 | 2017-11-27 | 15 | 2017-12-12 | 2017-11-28 | 140035688.52 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel3 | Substation Elco Steel3
Elco Steel | 1 | 4 | 45198074.67 | 1838590.86 | -43359483.81 | 35932469.35 | 1268627.7 | -34663841.65 |  |  |  | 35932469.36 | 2017-12-31 | 2017-12-31 | 2017-12-27 | 15 | 2018-01-11 | 2018-01-02 | 185233763.18 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel4 | Substation Elco Steel4
Elco Steel | 1 | 5 | 15262763.5 | 5784479.69 | -9478283.81 | 12038252.26 | 4588851.87 | -7449400.39 |  |  |  | 12133896.98 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 200496526.68 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel5 | Substation Elco Steel5
Elco Steel | 1 | 6 | 23107300.22 | 3766431.24 | -19340868.98 | 20100303 | 2598837.56 | -17501465.44 |  |  |  | 19914658.95 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 223603826.9 | 0 | [5 empty] | 95644.72 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel6 | Substation Elco Steel6
Elco Steel | 1 | 7 | 9962100.82 | 3187107.5 | -6774993.32 | 7919870.17 | 2228843.15 | -5691027.02 |  |  |  | 7919870.15 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 233565927.72 | 0 | [5 empty] | 95644.72 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel7 | Substation Elco Steel7
Elco Steel | 1 | 8 | 7984975.64 | 2651758.28 | -5333217.36 | 6348055.64 | 1829713.22 | -4518342.42 |  |  |  | 6348055.64 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 241550903.36 | 0 | [5 empty] | 95644.72 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel8 | Substation Elco Steel8
Elco Steel | 1 | 9 | 1027177.94 | 1904763.72 | 877585.78 | 740665.09 | 1314286.96 | 573621.87 |  |  |  | 740665.1 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 242578081.3 | 0 | [5 empty] | 171586.08 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel9 | Substation Elco Steel9
Elco Steel | 1 | 10 | 5032217.21 | 4730762.03 | -301455.18 | 4000000 | 3744490.63 | -255509.37 |  |  |  | 4000612.68 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 247610298.51 | 0 | [5 empty] | 171586.08 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel10 | Substation Elco Steel10
Elco Steel | 1 | 11 | 8902176.76 | 4095222.62 | -4806954.14 | 7075101.66 | 3142902.52 | -3932199.14 |  |  |  | 7077230.5163 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 256512475.27 | 0 | [5 empty] | 171586.08 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel11 | Substation Elco Steel11
Elco Steel | 1 | 12 |  | 0 | 0 | 2485656 | 0 | -2485656 |  |  |  |  | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel12 | Substation Elco Steel12
Elco Steel | 1 | 13 |  | 0 | 0 | 2518616.18 | 0 | -2518616.18 |  |  |  |  | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel13 | Substation Elco Steel13
Elco Steel | 1 | 14 |  | 0 | 0 | 2857649.27 | 0 | -2857649.27 |  |  |  |  | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel14 | Substation Elco Steel14
Elco Steel | 1 | 15 |  | 0 | 0 | 1595365.5 | 0 | -1595365.5 |  |  |  |  | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel15 | Substation Elco Steel15
Elco Steel | 1 | 16 |  | 0 | 0 | 310509.31 | 0 | -310509.31 |  |  |  |  | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel16 | Substation Elco Steel16
Elco Steel | 1 | 17 |  | 0 | 0 | 1079101.72 | 0 | -1079101.72 |  |  |  |  | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel17 | Substation Elco Steel17
Elco Steel - ADMIN. | 1 | 1 | 1576783.88 | 0 | -1576783.88 | 1253543.1806 | 0 | -1253543.1806 |  |  |  | 1253543.1806 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 1576783.88 | [6 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.1 | Substation Elco Steel1
Elco Steel - ADMIN. | 1 | 2 | 3644932.88 | 1669926.8 | -1975006.08 | 2897721.63 | 1160599.13 | -1737122.5 |  |  |  | 2897721.64 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 5221716.76 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.2 | Substation Elco Steel2
Elco Steel - ADMIN. | 1 | 3 | 4011218.17 | 2658220.39 | -1352997.78 | 3188918.44 | 1834172.07 | -1354746.37 |  |  |  | 3188918.45 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 9232934.93 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.3 | Substation Elco Steel3
Elco Steel - ADMIN. | 1 | 4 | 4549688.44 | 1838590.86 | -2711097.58 | 3617002.31 | 1268627.7 | -2348374.61 |  |  |  | 3617002.31 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 13782623.37 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.4 | Substation Elco Steel4
Elco Steel - ADMIN. | 1 | 5 | 2288094.62 | 5784479.69 | 3496385.07 | 1819035.22 | 4588851.87 | 2769816.65 |  |  |  | 1819035.23 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 16070717.99 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.5 | Substation Elco Steel5
Elco Steel - ADMIN. | 1 | 6 | 6362324.03 | 3766431.24 | -2595892.79 | 5058047.58 | 2598837.56 | -2459210.02 |  |  |  | 5094386.24 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 22433042.02 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.6 | Substation Elco Steel6
Elco Steel - ADMIN. | 1 | 7 | 7233482.49 | 3187107.5 | -4046374.99 | 5750618.5816 | 2228843.15 | -3521775.4316 |  |  |  | 5750618.5816 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 29666524.51 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.7 | Substation Elco Steel7
Elco Steel - ADMIN. | 1 | 8 |  | 2651758.28 | 2651758.28 | 3289926.92 | 1829713.22 | -1460213.7 |  |  |  |  | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.8 | Substation Elco Steel8
Elco Steel - ADMIN. | 1 | 9 |  | 1904763.72 | 1904763.72 | 1940428 | 1314286.96 | -626141.04 |  |  |  |  | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.9 | Substation Elco Steel9
Elco Steel - ADMIN. | 1 | 10 |  | 4730762.03 | 4730762.03 | 2335545.55 | 3744490.63 | 1408945.08 |  |  |  |  | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.10 | Substation Elco Steel10
Elco Steel - ADMIN. | 1 | 11 |  | 4095222.62 | 4095222.62 | 2179703.08 | 3142902.52 | 963199.44 |  |  |  |  | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.11 | Substation Elco Steel11
Elco Steel - ADMIN. | 1 | 12 |  | 0 | 0 | 1394236.8 | 0 | -1394236.8 |  |  |  |  | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.12 | Substation Elco Steel12
Elco Steel - ADMIN. | 1 | 13 |  | 0 | 0 | 117652.86 | 0 | -117652.86 |  |  |  |  | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.13 | Substation Elco Steel13
Elco Steel - ADMIN. | 1 | 14 |  | 0 | 0 | 105992.48 | 0 | -105992.48 |  |  |  |  | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.14 | Substation Elco Steel14
Elco Steel - ADMIN. | 1 | 15 |  | 0 | 0 | 259861.3 | 0 | -259861.3 |  |  |  |  | 2019-03-31 | 2019-04-10 | 2019-04-16 | 15 | 2019-05-01 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.15 | Substation Elco Steel15
Elco Steel - MEP | 1 | 1 | 444736.0027 | 0 | -444736.0027 | 331328.322 | 0 | -331328.322 |  |  |  | 331328.322 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 444736.0027 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP1 | Substation Elco Steel1
Elco Steel - MEP | 1 | 2 | 2764965.97 | 1669926.8 | -1095039.17 | 2059899.63 | 1160599.13 | -899300.5 |  |  |  | 2059899.65 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 3209701.97 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP2 | Substation Elco Steel2
Elco Steel - MEP | 1 | 3 | 2666446.92 | 2658220.39 | -8226.53 | 1986502.95 | 1834172.07 | -152330.88 |  |  |  | 1986502.96 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 5876148.87 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP3 | Substation Elco Steel3
Elco Steel - MEP | 1 | 4 | 3362790.38 | 1838590.86 | -1524199.52 | 2505278.83 | 1268627.7 | -1236651.13 |  |  |  | 2505278.83 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 9238939.25 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP4 | Substation Elco Steel4
Elco Steel - MEP | 1 | 5 | 3275304.26 | 5784479.69 | 2509175.43 | 2440101.67 | 4588851.87 | 2148750.2 |  |  |  | 2440101.69 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 12514243.51 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP5 | Substation Elco Steel5
Elco Steel - MEP | 1 | 6 | 2863596.99 | 3766431.24 | 902834.25 | 2133379.76 | 2598837.56 | 465457.8 |  |  |  | 2133379.78 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 15377840.5 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP6 | Substation Elco Steel6
Elco Steel - MEP | 1 | 7 | 3498188.3161 | 3187107.5 | -311080.8161 | 2606150.307 | 2228843.15 | -377307.157 |  |  |  | 2606150.307 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 18876028.8161 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP7 | Substation Elco Steel7
Elco Steel - MEP | 1 | 8 |  | 2651758.28 | 2651758.28 | 1980608.55 | 1829713.22 | -150895.33 |  |  |  |  | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP8 | Substation Elco Steel8
Elco Steel - MEP | 1 | 9 |  | 1904763.72 | 1904763.72 | 2178754.66 | 1314286.96 | -864467.7 |  |  |  |  | 2018-09-30 | 2018-10-09 | 2018-10-10 | 15 | 2018-10-25 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP9 | Substation Elco Steel9
Elco Steel - MEP | 1 | 10 |  | 4730762.03 | 4730762.03 | 2629432.67 | 3744490.63 | 1115057.96 |  |  |  |  | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP10 | Substation Elco Steel10
Elco Steel - MEP | 1 | 11 |  | 4095222.62 | 4095222.62 | 1720441.01 | 3142902.52 | 1422461.51 |  |  |  |  | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP11 | Substation Elco Steel11
Elco Steel - MEP | 1 | 12 |  | 0 | 0 | 1037321.78 | 0 | -1037321.78 |  |  |  |  | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP12 | Substation Elco Steel12
Elco Steel - MEP | 1 | 13 |  | 0 | 0 | 388339.4 | 0 | -388339.4 |  |  |  |  | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP13 | Substation Elco Steel13
Elco Steel - MEP | 1 | 14 |  | 0 | 0 | 317040.71 | 0 | -317040.71 |  |  |  |  | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP14 | Substation Elco Steel14
Elco Steel V.O-Infra. Network | 1 | 1 |  | 0 | 0 | 1060000 | 0 | -1060000 |  |  |  |  | 2019-06-30 | 2019-07-03 | 2019-07-03 | 15 | 2019-07-18 | [9 empty] | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel V.O-Infra. Network1 | Substation Elco Steel1
#N/A
El-Gouna | 1 | 1 | 3393576.42 | 3474451.4 | 80874.98 | 2327690.6 | 2401503.7825 | 73813.1825 | 13625000 |  |  | 2338174.15 | 2019-09-30 | 2019-10-15 | 2019-11-04 | 21 | 2019-11-25 | 2019-11-24 | 3393576.42 | [6 empty] | 0 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna1 | DoubleTree Mangroovy ElGouna1
El-Gouna | 1 | 2 | 3546875.03 | 6040168.01 | 2493292.98 | 3867767.27 | 4293335.2605 | 425567.9905 |  |  |  | 3879736.97 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 21 | 2019-12-08 | 2019-11-24 | 6940451.45 | 2084092.99 | [5 empty] | 0 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna2 | DoubleTree Mangroovy ElGouna2
El-Gouna | 1 | 3 | 4290021.36 | 685050 | -3604971.36 | 2286139.86 | 680952 | -1605187.86 |  |  |  | 2286139.86 | 2019-11-30 | 2019-12-15 | 2019-12-16 | 21 | 2020-01-06 | 2019-12-19 | 11230472.81 | 1112126.59 | [5 empty] | 10483.55 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna3 | DoubleTree Mangroovy ElGouna3
El-Gouna | 1 | 4 | 2686069.3 | 3767828.94 | 1081759.64 | 2572404.48 | 2597585.492 | 25181.012 |  |  |  | 2572404.48 | 2019-12-31 | 2020-01-15 | 2020-01-21 | 21 | 2020-02-11 | 2020-01-21 | 13916542.11 | 2169673.66 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna4 | DoubleTree Mangroovy ElGouna4
El-Gouna | 1 | 5 | 3430037.61 | 2653452.18 | -776585.43 | 1808595.27 | 1828998.833 | 20403.563 |  |  |  | 1815739.6 | 2020-01-31 | 2020-02-15 | 2020-02-19 | 21 | 2020-03-11 | 2020-02-23 | 17346579.72 | 1374961.99 | [5 empty] | 10483.55 | 3430037.61 | 17346579.72 | 1815739.6 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna5 | DoubleTree Mangroovy ElGouna5
El-Gouna | 1 | 6 | 6540676.19 | 6170230.65 | -370445.54 | 4246133.4 | 8251289.2525 | 4005155.8525 |  |  |  | 4271724.93 | 2020-02-29 | 2020-03-15 | 2020-03-18 | 21 | 2020-04-08 | 2020-03-18 | 23887255.91 | 1023807.82 | [5 empty] | 29400.49 | 6540676.19 | 23887255.91 | 6823693.4 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna6 | DoubleTree Mangroovy ElGouna6
El-Gouna | 1 | 7 | 3114205.16 | 3133496.53 | 19291.37 | 2145687.36 | 2166123.4165 | 20436.0565 |  |  |  | 2145687.36 | 2020-03-31 | 2020-04-15 | 2020-04-18 | 21 | 2020-05-09 | 2020-04-21 | 27001461.07 | 1023807.82 | [5 empty] | 29400.49 | 3114205.16 | 27001461.07 | 2158979.11 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna7 | DoubleTree Mangroovy ElGouna7
El-Gouna | 1 | 8 | 3250029.8 | 2806757.16 | -443272.64 | 1922134.77 | 1896543.798 | -25590.972 |  |  |  | 1922134.77 | 2020-06-30 | 2020-07-01 | 2020-07-05 | 21 | 2020-07-26 | 2020-07-06 | 30251490.87 | 580535.19 | [5 empty] | 29400.49 | 3250029.8 | 30251490.87 | 1933855.68 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna8 | DoubleTree Mangroovy ElGouna8
El-Gouna | 1 | 9 | 1882490 | 1505090.04 | -377399.96 | 1030964.27 | 1030964.272 | 0.002 |  |  |  | 1037007.36 | 2020-07-31 | 2020-08-01 | 2020-07-26 | 21 | 2020-08-16 | 2020-07-27 | 32133980.87 | 203135.69 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna9 | DoubleTree Mangroovy ElGouna9
El-Gouna | 1 | 10 | 1889241.5387 | 1714004.8 | -175236.7387 | 1173489.52 | 1173489.49 | -0.03 |  |  |  | 1180949.3351 | 2020-08-31 | 2020-09-01 | 2020-09-05 | 21 | 2020-09-26 | 2020-09-05 | 34023222.4087 | 27898.992 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna10 | DoubleTree Mangroovy ElGouna10
El-Gouna | 1 | 11 | 881976.7757 | 2596008.28 | 1714031.5043 | 1750027.3 | 1750027.305 | 0.005 |  |  |  | 1788649.6992 | 2020-11-30 | 2020-11-30 | 2020-12-09 | 21 | 2020-12-30 | 2020-12-19 | 34905199.1844 | 1741930.488 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna11 | DoubleTree Mangroovy ElGouna11
El-Gouna | 1 | 12 | -0.0044313 | 1904761.9 | 1904761.9044 | 1942857.14 | 1942857.135 | -0.005 |  |  |  | 2000000 | 2020-11-30 | 2020-11-30 | 2020-12-23 | 21 | 2021-01-13 | 2020-12-23 | 34905199.18 | 1741930.49 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna12 | DoubleTree Mangroovy ElGouna12
El-Gouna | 1 | 13 | 2225492.71 | 2664148.65 | 438655.94 | 1951940.18 | 1951940.1825 | 0.0025 |  |  |  | 1964526.99 | 2020-12-31 | 2020-12-31 | 2021-01-10 | 21 | 2021-01-31 | 2021-01-12 | 37130691.89 | 1823017.32 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna13 | DoubleTree Mangroovy ElGouna13
El-Gouna | 1 | 14 | 3901532.2 | 4271693.53 | 370161.33 | 3058799.81 | 3058799.81 | 0 |  |  |  | 3061707.07 | 2021-01-31 | 2021-01-31 | 2021-02-14 | 21 | 2021-03-07 | 2021-03-03 | 41032224.09 | 1836465.31 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna14 | DoubleTree Mangroovy ElGouna14
El-Gouna | 1 | 15 | 4440680.41 | 4199870.68 | -240809.73 | 3002136.21 | 3002136.214 | 0.004 |  |  |  | 3011925.18 | 2021-02-28 | 2021-03-11 | 2021-03-13 | 21 | 2021-04-03 | 2021-04-17 | 45472904.5 | 1238512.71 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna15 | DoubleTree Mangroovy ElGouna15
El-Gouna | 1 | 16 | 4113209.61 | 4424891.64 | 311682.03 | 3166964.63 | 3166964.612 | -0.018 |  |  |  | 3166964.63 | 2021-03-31 | 2021-04-12 | 2021-04-15 | 21 | 2021-05-06 | 2021-04-27 | 49586114.11 | 1193051.88 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna16 | DoubleTree Mangroovy ElGouna16
El-Gouna | 1 | 17 | 3640319.41 | 2987451.96 | -652867.45 | 2526942.2 | 4581335.978 | 2054393.778 |  |  |  | 2547089.28 | 2021-05-31 | 2021-05-31 | 2021-06-03 | 21 | 2021-06-24 | 2021-06-14 | 53226433.52 | 540181.99 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna17 | DoubleTree Mangroovy ElGouna17
El-Gouna | 1 | 18 | 3384789.31 | 2844607.33 | -540181.98 | 5636281.25 | 5619891.3535 | -16389.8965 |  |  |  | 5636285.41 | 2021-08-31 | 2021-08-26 | 2021-08-26 | 21 | 2021-09-16 | 2021-08-26 | 56611222.83 | [6 empty] | 195708.06 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna18 | DoubleTree Mangroovy ElGouna18
El-Gouna - Equip. Rental | 1 | 1 | 80875 | 3474451.4 | 3393576.4 | 73813.12 | 2401503.7825 | 2327690.6625 |  |  |  | 73813.12 | 2019-12-31 | 2019-12-31 | 2019-12-12 | 21 | 2020-01-02 | 2020-02-02 | 80875 | [7 empty] | 80875 | 80875 | 73813.12 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental1 | DoubleTree Mangroovy ElGouna1
El-Gouna - Equip. Rental | 1 | 2 |  | 6040168.01 | 6040168.01 | 16757 | 4293335.2605 | 4276578.2605 |  |  |  |  | 2020-03-31 | 2020-03-31 | 2020-03-18 | 21 | 2020-04-08 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental2 | DoubleTree Mangroovy ElGouna2
El-Gouna - Equip. Rental | 1 | 3 |  | 685050 | 685050 | 74100 | 680952 | 606852 |  |  |  |  | 2020-06-30 | 2020-07-09 | 2020-07-09 | 21 | 2020-07-30 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental3 | DoubleTree Mangroovy ElGouna3
El-Gouna - Equip. Rental | 1 | 4 |  | 3767828.94 | 3767828.94 | 3281.25 | 2597585.492 | 2594304.242 |  |  |  |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 21 | 2021-04-21 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental4 | DoubleTree Mangroovy ElGouna4
El-Gouna - Equip. Rental | 1 | 5 | 15000 | 2653452.18 | 2638452.18 | 15750 | 1828998.833 | 1813248.833 |  |  |  | 15750 | 2021-05-31 | 2021-05-24 | 2021-05-24 | 21 | 2021-06-14 | 2021-06-24 | 186362.5 | [7 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental5 | DoubleTree Mangroovy ElGouna5
El-Gouna - Temp. Fence | 1 | 1 | 409200 | 3474451.4 | 3065251.4 | 425568 | 2401503.7825 | 1975935.7825 |  |  |  | 429660 | 2019-12-31 | 2020-01-15 | 2020-01-18 | 21 | 2020-02-08 | 2020-03-01 | 409200 | [7 empty] | 409200 | 409200 | 429660 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Temp. Fence1 | DoubleTree Mangroovy ElGouna1
El-Gouna - Temp. Fence | 1 | 2 |  | 6040168.01 | 6040168.01 | 441526.8 | 4293335.2605 | 3851808.4605 |  |  |  |  | 2020-01-31 | 2020-02-15 | 2020-02-23 | 21 | 2020-03-15 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Temp. Fence2 | DoubleTree Mangroovy ElGouna2
El-Gouna - Temp. Fence | 1 | 3 |  | 685050 | 685050 | 173749.2 | 680952 | 507202.8 |  |  |  |  | 2020-05-31 | 2020-06-06 | 2020-06-06 | 21 | 2020-06-27 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Temp. Fence3 | DoubleTree Mangroovy ElGouna3
Existing Intake Apply -SSC-Mech | 1 | 1 | 573500 | 0 | -573500 | 1e-05 | 0 | -1e-05 |  |  |  | 636585 | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-30 | 573500 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Existing Intake Apply -SSC-Mech1 | 01
Existing Intake Supply -SSC-Mech | 1 | 1 | 2140488 | 0 | -2140488 | 2311727.07 | 0 | -2311727.07 |  |  |  | 2418751.44 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 2140488 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Existing Intake Supply -SSC-Mech1 | 01
#N/A
FIEM | 1 | 210 | 2236443.87 | 0 | -2236443.87 | 1523916.51 | 0 | -1523916.51 |  |  |  | 1524934.13 | 2017-10-31 | 2017-10-20 | 2017-10-20 | 60 | 2017-12-19 | 2017-10-23 | 69807649.46 | [6 empty] | 0 | 2236443.87 | 69808024.8 | 1524934.13 | 0 |  |  |  | FIEM210 | 0210
FIEM | 1 | 211 | 342199.52 | 0 | -342199.52 | 218510 | 0 | -218510 |  |  |  | 221255.83 | 2017-11-30 | 2017-12-04 | 2018-01-02 | 60 | 2018-03-03 | 2018-01-19 | 70149848.98 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | FIEM211 | 0211
FIEM | 1 | 212 | 1955183.63 | 0 | -1955183.63 | 1205285.3 | 0 | -1205285.3 |  |  |  | 1546005.35 | 2018-05-31 | 2018-06-12 | 2018-07-12 | 60 | 2018-09-10 | 2018-10-24 | 72105032.61 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | FIEM212 | 0212
FIEM | 1 | 213 | 336328.97 | 0 | -336328.97 | 335237.946 | 0 | -335237.946 |  |  |  | 335237.946 | 2018-08-31 | 2018-08-15 | 2018-10-21 | 60 | 2018-12-20 | 2018-10-24 | 72441361.58 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | FIEM213 | 0213
#N/A
HQ - CFC | 1 | 1 | 1435679.4 | 1435679.43 | 0.03 | 6847513.64 | 6886276.98 | 38763.34 | 103231218.3 |  |  | 6847513.7311 | 2021-01-31 | 2021-01-31 | 2021-02-03 | 21 | 2021-02-24 | 2021-02-22 | 1435679.4 | 5469259.14 | [5 empty] | 0 | 1435679.4 | 1435679.4 | 6847513.7311 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC1 | ElSewedy HQ Internal Finishing1
HQ - CFC | 1 | 2 | 7766126.7 | 7766126.67 | -0.03 | 8021127.82 | 8230813.242 | 209685.422 |  |  |  | 8021127.94 | 2021-02-28 | 2021-02-28 | 2021-03-08 | 21 | 2021-03-29 | 2021-03-22 | 9201806.1 | 7106192.52 | [5 empty] | 0 | 7766126.7 | 9201806.1 | 8021127.94 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC2 | ElSewedy HQ Internal Finishing2
HQ - CFC | 1 | 3 | 12533035.1 | 12533035.14 | 0.04 | 8213720.11 | 8552112.06 | 338391.95 |  |  |  | 8213719.76 | 2021-03-31 | 2021-03-31 | 2021-04-10 | 21 | 2021-05-01 | 2021-04-15 | 21734841.2 | 6815308.56 | [5 empty] | 50000 | 12533035.1 | 21734841.2 | 8213719.76 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC3 | ElSewedy HQ Internal Finishing3
HQ - CFC | 1 | 4 | 11480730.2 | 11480730.19 | -0.01 | 7815807.73 | 7530697.05 | -285110.68 |  |  |  | 7815807.64 | 2021-04-30 | 2021-04-30 | 2021-05-06 | 21 | 2021-05-27 | 2021-05-26 | 33215571.4 | 6784708.63 | [5 empty] | 50000 | 11480730.2 | 33215571.4 | 7815807.64 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC4 | ElSewedy HQ Internal Finishing4
HQ - CFC | 1 | 5 | 6032812.4 | 6032812.38 | -0.02 | 3447418.19 | 3447418.189 | -0.001 |  |  |  | 3447418.19 | 2021-06-30 | 2021-06-30 | 2021-07-06 | 21 | 2021-07-27 | 2021-07-14 | 39248383.8 | 6043914.88 | [5 empty] | 298842.16 | 0 | 0 | 0 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC5 | ElSewedy HQ Internal Finishing5
HQ - CFC | 1 | 6 | 5418722.3 | 5418722.29 | -0.01 | 13157200.99 | 8157201.3445 | -4999999.6455 |  |  |  | 13157201.34 | 2021-07-31 | 2021-07-31 | 2021-08-04 | 21 | 2021-08-25 | 2021-08-17 | 44667106.1 | 15536980.84 | [5 empty] | 258842.16 | 0 | 0 | 0 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC6 | ElSewedy HQ Internal Finishing6
HQ - CFC | 1 | 7 | 14463563.8 | 14463563.81 | 0.01 | 14942810.84 | 9724934.81 | -5217876.03 |  |  |  | 14942810.8492 | 2021-08-31 | 2021-09-06 | 2021-09-07 | 21 | 2021-09-28 | 2021-09-09 | 59130669.9 | 20740314.76 | [5 empty] | 258842.16 | 14463563.8 | 59130669.9 | 14942810.8492 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC7 | ElSewedy HQ Internal Finishing7
HQ - CFC | 1 | 8 | 12855494 | 12855494 | 0 | 10012745.7 | 10012746.11 | 0.41 |  |  |  | 10012746.11 | 2021-09-30 | 2021-10-06 | 2021-10-09 | 21 | 2021-10-30 | 2021-10-17 | 71986163.9 | 21760696.01 | [5 empty] | 253842.16 | 12903651.6 | 72034321.5 | 10059001.5 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC8 | ElSewedy HQ Internal Finishing8
HQ - CFC | 1 | 9 | 11039038.4 | 11039038.38 | -0.02 | 17174919.84 | 10415313.809 | -6759606.031 |  |  |  | 17174919.86 | 2021-10-31 | 2021-11-03 | 2021-11-04 | 21 | 2021-11-25 | 2021-11-11 | 83025202.3 | 31225957.6 | [5 empty] | 253842.16 | 11039038.4 | 83025202.3 | 17174919.86 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC9 | ElSewedy HQ Internal Finishing9
HQ - CFC | 1 | 10 | 10645458.9 | 10645458.95 | 0.05 | 7981881.94 | 0 | -7981881.94 |  |  |  | 7981881.9284 | 2021-11-30 | 2021-12-04 | 2021-12-07 | 21 | 2021-12-28 | 2021-12-16 | 93670661.2 | 32240807.02 | [5 empty] | 673673.38 | 10645458.9 | 93670661.2 | 7981881.9284 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC10 | ElSewedy HQ Internal Finishing10
HQ - CFC | 1 | 11 | 21606398.42 | 21606397.82 | -0.6 | 27417402.1 | 17417402.071 | -10000000.029 |  |  |  | 17417402.06 | 2021-12-31 | 2022-01-09 | 2022-01-10 | 21 | 2022-01-31 | 2022-10-20 | 115277059.62 | 33736026.89 | [5 empty] | 673673.38 | 21606397.9 | 115277059.1 | 17417402.1321 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC11 | ElSewedy HQ Internal Finishing11
HQ - CFC | 1 | 12 | 11990804.88 | 11990805.42 | 0.54 | 11342066.99 | 8175767.971 | -3166299.019 |  |  |  | 11342067.06 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 21 | 2022-03-08 | 2022-02-24 | 127267864.5 | 36548454.91 | [5 empty] | 0 | 11990804.88 | 127267864.5 | 11342067.06 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC12 | ElSewedy HQ Internal Finishing12
HQ - CFC | 1 | 13 | 23373232.3 | 23373232.29 | -0.01 | 10869511.32 | 869511.3245 | -9999999.9955 |  |  |  | 869511.3183 | 2022-02-28 | 2022-03-10 | 2022-03-15 | 21 | 2022-04-05 | 2022-03-28 | 150641096.8 | 40068734.4 |  |  |  | 3954328.79 | 3954328.79 | 0 | 23373232.3 | 150641096.8 | 869511.3183 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC13 | ElSewedy HQ Internal Finishing13
HQ - CFC | 1 | 14 |  | 15411463.14 | 15411463.14 | 6179916.44 | 1748564.937 | -4431351.503 |  |  |  | 1748564.91 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 21 | 2022-05-04 | [8 empty] | 0 | 0 | 0 | 1748564.91 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC14 | ElSewedy HQ Internal Finishing14
HQ - CFC | 1 | 15 | 16353901 | 16126527.14 | -227373.86 | 10437699.8 | 10437709.627 | 9.827 |  |  |  | 10437709.6267 | 2022-04-30 | 2022-04-30 | 2022-05-10 | 21 | 2022-05-31 | 2022-05-17 | 182179087 | 36127505.39 | 42019925.8 |  | 380603 | 4782201.035 | 4782201.035 | 28096 | 16353901 | 182179087 | 10437709.6267 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC15 | ElSewedy HQ Internal Finishing15
HQ - CFC | 1 | 16 | 8911604.3 | 8911604.29 | -0.01 | 1064612.28 | 0.0045 | -1064612.2755 |  |  |  | 1064612.35 | 2022-05-31 | 2022-05-31 | 2022-06-12 | 21 | 2022-07-03 | 2022-06-15 | 191090691.3 | 35019448 | 44132357 |  | 534156.21 | 5016130.5 | 5016130.5 | 1429217 | 8911604.3 | 191090691.3 | 1064612.35 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC16 | ElSewedy HQ Internal Finishing16
HQ - CFC | 1 | 17 | 17076484.2 | 17076484.19 | -0.01 | 8013147.43 | 2847047.2295 | -5166100.2005 |  |  |  | 8013147.4 | 2022-06-30 | 2022-06-30 | 2022-07-04 | 21 | 2022-07-25 | 2022-07-18 | 208167175.5 | 34368331.94 | 46825994 |  | 855446.95 | 5464388 | 5464388 | 28096.4 | 17076484.2 | 208167175.5 | 8013147.4 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC17 | ElSewedy HQ Internal Finishing17
HQ - CFC | 1 | 18 | 15625697.2 | 15535743.72 | -89953.48 | 12964666.86 | 11331892.376 | -1632774.484 |  |  |  | 13019444.4 | 2022-07-31 | 2022-07-31 | 2022-08-06 | 21 | 2022-08-27 | 2022-08-17 | 223792872.7 | 42794128.97 | 51289544.4 |  | 1216434.1435 | 5874504.1475 | 5874504.1475 | 28096.4 | 15625697.2 | 223792872.7 | 13019444.4 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC18 | ElSewedy HQ Internal Finishing18
HQ - CFC | 1 | 19 | 11070593.3 | 11160546.75 | 89953.45 | 2123375.29 | 0 | -2123375.29 |  |  |  | 2123376.4 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 21 | 2022-09-28 | 2022-10-16 | 234863466 | 43167126 | 53959703 |  | 1482872 | 6165165.5 | 6165165.5 | 23096 | 11070593.3 | 234863466 | 2123376.4 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC19 | ElSewedy HQ Internal Finishing19
HQ - CFC | 1 | 20 | 43687204.7 | 43687204.67 | -0.03 | 9324446.8 | 10136401.93 | 811955.13 |  |  |  | 9324446.7637 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 21 | 2022-11-01 | 2022-10-17 | 278550670.7 | 25330248.86 | 72413577.8 |  | 2630548.1069 | 7311955.105 | 7311955.105 | 23096.4 | 43687204.7 | 278550670.7 | 9324446.7637 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC20 | ElSewedy HQ Internal Finishing20
HQ - CFC | 1 | 21 | 6969185.9 | 6969185.9 | 2.4214e-08 | 1704646.05 | 0 | -1704646.05 |  |  |  | 1704646.05 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 21 | 2022-11-29 | 2022-11-20 | 285519856.6 | 22835242 | 75563462.2 |  | 2846115 | 7494896 | 7494896 | 0 | 6969185.9 | 285519856.6 | 1704646.05 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC21 | ElSewedy HQ Internal Finishing21
HQ - CFC | 1 | 23 | 9615384.7 | 25519032.04 | 15903647.34 | 10000000 | 1915761.653 | -8084238.347 |  |  |  | 10000000.1524 | 2022-11-30 | 2022-11-30 | 2022-12-07 | 21 | 2022-12-28 | 2022-12-14 | 295135241.3 | 22835242.98 | 85178846.6 |  | 2846115.9564 | 7494896.235 | 7494896.235 | 2085744.58 | 0 | 0 | 0 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC23 | ElSewedy HQ Internal Finishing23
HQ - CFC | 1 | 24 | 25568878.3 | 25519032.04 | -49846.26 | 5681250.46 | 0 | -5681250.46 |  |  |  | 5979128.01 | 2022-11-30 | 2022-11-30 | 2022-12-13 | 21 | 2023-01-03 | 2022-12-27 | 320704119.6 | 12624923 | 98574568 |  | 4317722 | 7311955.09 | 9525011.19 | 325973.55 | 25568878.3 | 320704119.6 | 5979128.01 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC24 | ElSewedy HQ Internal Finishing24
HQ - CFC | 1 | 25 | 17887580.019 | 17937426.6 | 49846.581 | 9125697.43 | 4987239.22 | -4138458.21 |  |  |  | 10125697.7641 | 2022-12-31 | 2022-12-31 | 2023-01-11 | 21 | 2023-02-01 | 2023-01-30 | 338591699.619 | 5521723.78 | 103716174.2 |  | 5354076.6018 | 7311955.09 | 10464109.14 | 297877.55 | 17887580.019 | 338591699.619 | 10125697.7641 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC25 | ElSewedy HQ Internal Finishing25
HQ - CFC | 1 | 26 | 15848994.2857 | 15848994.31 | 0.024286 | 11231097.41 | 11230610.0055 | -487.4045 |  |  |  | 24450753.15 | 2023-01-31 | 2023-01-31 | 2023-11-22 | 21 | 2023-12-13 | 2024-02-15 | 354440693.9048 | 2203336.47 | 119098372.4 |  | 6380098.57 | 9304068.215 | 9304068.215 | 0 | 15848994.2857 | 354440693.9048 | 24450753.15 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC26 | ElSewedy HQ Internal Finishing26
#N/A
HyperOne | 1 | 1 | 1684523.66 | 1684524 | 0.34 | 36249090 | 2583316 | -33665774 | 33750000 |  |  | 2673900.95 | 2019-10-31 | 2019-11-10 | 2019-11-11 | 14 | 2019-11-25 | 2019-11-24 | 1684523.66 | 1191900 | [5 empty] | 0 | 1684523.66 | 1684523.66 | 2673900.95 | HyperOne Zayed Extension |  |  |  | HyperOne1 | HyperOne Zayed Extension1
HyperOne | 1 | 2 | 11473372.17 | 11473371.43 | -0.74 | 8063620 | 8637288.8615 | 573668.8615 |  |  |  | 8554552.61 | 2019-11-30 | 2019-12-07 | 2019-12-08 | 14 | 2019-12-22 | 2019-12-12 | 13157895.83 | 478500 | [5 empty] | 0 | 11473372.17 | 13157895.83 | 8554552.61 | HyperOne Zayed Extension |  |  |  | HyperOne2 | HyperOne Zayed Extension2
HyperOne | 1 | 3 | 10276217.5887 | 10276217.14 | -0.4487 | 6681009 | 7194819.68 | 513810.68 |  |  |  | 7194819.7145 | 2019-12-31 | 2019-12-31 | 2020-01-02 | 14 | 2020-01-16 | 2020-01-13 | 23434113.4187 | 478500 | [5 empty] | 1194684.3216 | 10276217.5887 | 23434113.4187 | 7194819.7145 | HyperOne Zayed Extension |  |  |  | HyperOne3 | HyperOne Zayed Extension3
HyperOne | 1 | 4 | 12451224.3668 | 12451225.71 | 1.3432 | 6318712 | 6318712 | 0 |  |  |  | 6318712 | 2020-01-31 | 2020-01-31 | 2020-02-06 | 14 | 2020-02-20 | 2020-02-23 | 35885337.7855 | [6 empty] | 4562652.7636 | 12451224.3668 | 35885337.7855 | 7092200.1311 | HyperOne Zayed Extension |  |  |  | HyperOne4 | HyperOne Zayed Extension4
HyperOne | 1 | 5 | 5616638.2145 | 5616447.62 | -190.5945 | 3307335 | 3307335 | 0 |  |  |  | 3307335 | 2020-02-29 | 2020-02-14 | 2020-02-18 | 14 | 2020-03-03 | 2020-02-23 | 41501976 | [6 empty] | 5067252 | 5616638.2145 | 41501976 | 3307335 | HyperOne Zayed Extension |  |  |  | HyperOne5 | HyperOne Zayed Extension5
HyperOne | 1 | 6 | 10976157.5052 | 10976158 | 0.4948 | 8598544 | 8598918.82 | 374.82 |  |  |  | 8598545.1487 | 2020-02-29 | 2020-02-29 | 2020-03-03 | 14 | 2020-03-17 | 2020-03-07 | 52478133.5052 | [6 empty] | 6203130.8054 | 10976157.5052 | 52478133.5052 | 8598545.1487 | HyperOne Zayed Extension |  |  |  | HyperOne6 | HyperOne Zayed Extension6
HyperOne | 1 | 7 | 12354446.4948 | 12419046 | 64599.5052 | 8960935 | 8960289.48 | -645.52 |  |  |  | 8896507 | 2020-03-31 | 2020-03-16 | 2020-03-19 | 14 | 2020-04-02 | 2020-03-23 | 64832580 | [6 empty] | 7392793.3392 | 12354446.4948 | 64832580 | 8896507 | HyperOne Zayed Extension |  |  |  | HyperOne7 | HyperOne Zayed Extension7
HyperOne | 1 | 8 | 7228560.7301 | 7092750.29 | -135810.4401 | 3276433 | 3276433 | 0 |  |  |  | 3400669 | 2020-03-31 | 2020-03-31 | 2020-04-04 | 14 | 2020-04-18 | 2020-04-12 | 72061140.7301 | [6 empty] | 9893521.3392 | 7228560.7301 | 72061140.7301 | 3400669 | HyperOne Zayed Extension |  |  |  | HyperOne8 | HyperOne Zayed Extension8
HyperOne | 1 | 9 | 2029339.2699 | 2100740 | 71400.7301 | 1277872 | 9493853 | 8215981 |  |  |  | 1277872 | 2020-04-30 | 2020-04-16 | 2020-04-19 | 14 | 2020-05-03 | 2020-04-26 | 74090480 | [6 empty] | 10272402 | 2029339.2699 | 74090480 | 1277872 | HyperOne Zayed Extension |  |  |  | HyperOne9 | HyperOne Zayed Extension9
HyperOne | 1 | 10 | 7741768.3647 | 7629179.05 | -112589.3147 | 4688664 | 4688663.2125 | -0.7875 |  |  |  | 4810581.9155 | 2020-05-31 | 2020-05-15 | 2020-05-17 | 14 | 2020-05-31 | 2020-06-01 | 81832248.3647 | [6 empty] | 11782199.7246 | 7741768.3647 | 81832248.3647 | 4810581.9155 | HyperOne Zayed Extension |  |  |  | HyperOne10 | HyperOne Zayed Extension10
HyperOne | 1 | 11 | 9960645.6353 | 10073235.24 | 112589.6047 | 6700148 | 6700148 | 0 |  |  |  | 6700151 | 2020-06-30 | 2020-06-15 | 2020-06-18 | 14 | 2020-07-02 | 2020-06-23 | 91792894 | [6 empty] | 13305539 | 9960645.6353 | 91792894 | 6700151 | HyperOne Zayed Extension |  |  |  | HyperOne11 | HyperOne Zayed Extension11
HyperOne | 1 | 12 | 3093528.5715 | 3093527.62 | -0.95152 | 1896315 | 1896313.721 | -1.279 |  |  |  | 1896314.4172 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 14 | 2020-07-18 | 2020-07-11 | 94886422.5715 | [6 empty] | 13935080.9072 | 3093528.5715 | 94886422.5715 | 1896314.4172 | HyperOne Zayed Extension |  |  |  | HyperOne12 | HyperOne Zayed Extension12
HyperOne | 1 | 13 | 9161230.539 | 9161231 | 0.46098 | 6738702 | 6738702 | 0 |  |  |  | 6738701.3468 | 2020-07-31 | 2020-07-31 | 2020-08-09 | 14 | 2020-08-23 | 2020-08-19 | 104047653.1105 | [6 empty] | 14675608.1725 | 9161230.539 | 104047653.1105 | 6738701.3468 | HyperOne Zayed Extension |  |  |  | HyperOne13 | HyperOne Zayed Extension13
HyperOne | 1 | 14 | 5698538.8895 | 5698546.6 | 7.7105 | 4476191 | 4476191 | 0 |  |  |  | 4476191 | 2020-08-31 | 2020-08-31 | 2020-09-02 | 14 | 2020-09-16 | 2020-09-13 | 109746192 | [6 empty] | 14851704 | 5698538.8895 | 109746192 | 4476191 | HyperOne Zayed Extension |  |  |  | HyperOne14 | HyperOne Zayed Extension14
HyperOne | 1 | 15 | 16067546 | 0 | -16067546 | 2754557 | 0 | -2754557 |  |  |  | 2800899.62 | 2020-12-31 | 2020-12-31 | 2021-07-10 | 14 | 2021-07-24 | 2021-09-08 | 125813738 | [6 empty] | 18113646 | 16067546 | 125813738 | 2800899.62 | HyperOne Zayed Extension |  |  |  | HyperOne15 | HyperOne Zayed Extension15
#N/A
IKEA | 1 | 1 | 2651353.89 | 3976564.28 | 1325210.39 | 9032556.9 | 5297470.32 | -3735086.58 | 5000000 |  |  | 4032556.9 | 2019-10-31 | 2019-10-24 | 2019-10-29 | 56 | 2019-12-24 | 2019-11-13 | 2651353.89 | 2149309.09 | [5 empty] | 0 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA1 | IKEA Extension MoA1
IKEA | 1 | 2 | 11255708.29 | 12332989.3 | 1077281.01 | 11062702.45 | 12202085.97 | 1139383.52 | 428986.9 |  |  | 10633715.55 | 2019-11-30 | 2019-11-30 | 2019-12-01 | 56 | 2020-01-26 | 2019-12-23 | 13907062.18 | 4289692.08 | [5 empty] | 619021.13 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA2 | IKEA Extension MoA2
IKEA | 1 | 3 | 10066585.32 | 10925856.01 | 859270.69 | 12136068.98 | 8007384.775 | -4128684.205 | 4951900.8 |  |  | 7184168.18 | 2019-12-31 | 2019-12-31 | 2019-12-29 | 56 | 2020-02-23 | 2020-01-27 | 23973647.5 | 2903747.63 | [5 empty] | 726571.28 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA3 | IKEA Extension MoA3
IKEA | 1 | 4 | 12574283.5677 | 12901940.25 | 327656.6823 | 10394851.44 | 8955635.564 | -1439215.876 | 2116049.37 |  |  | 8278802.0663 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 56 | 2020-03-30 | 2020-02-26 | 36547931.0677 | 465407.831 | [5 empty] | 919175.0927 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA4 | IKEA Extension MoA4
IKEA | 1 | 5 | 9421690.8414 | 9421690.84 | -0.001378 | 29492459.808 | 7739970.29 | -21752489.518 | 21562500 |  |  | 7929959.808 | 2020-02-29 | 2020-02-29 | 2020-03-02 | 56 | 2020-04-27 | 2020-03-29 | 45969621.9091 | 371420 | [5 empty] | 847495.2609 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA5 | IKEA Extension MoA5
IKEA | 1 | 6 | 5112809.0459 | 5112809.05 | 0.0041118 | 5718130.68 | 4141935.79 | -1576194.89 | 1818917 |  |  | 3899213.6765 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 56 | 2020-05-26 | 2020-04-23 | 51082430.955 | 371420 | [5 empty] | 1125963.2758 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA6 | IKEA Extension MoA6
IKEA | 1 | 7 | 9400137.0091 | 9400137.01 | 0.00085056 | 9913732.53 | 6567550.07 | -3346182.46 | 3751873.62 |  |  | 6161858.9082 | 2020-04-30 | 2020-05-03 | 2020-05-05 | 56 | 2020-06-30 | 2020-06-07 | 60482567.9642 | [6 empty] | 1472106.3608 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA7 | IKEA Extension MoA7
IKEA | 1 | 8 | 17657618.9509 | 18401730.5 | 744111.5491 | 13605824.96 | 13497644.42 | -108180.54 | 525633.83 |  |  | 13080191.1331 | 2020-06-30 | 2020-06-23 | 2020-06-23 | 56 | 2020-08-18 | 2020-07-15 | 78140186.9151 | 5848353.145 | [5 empty] | 2079486.5167 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA8 | IKEA Extension MoA8
IKEA | 1 | 9 | 19939473.9502 | 19195362.4 | -744111.5502 | 21936362.84 | 21335051.85 | -601310.99 |  |  |  | 21936362.8422 | 2020-07-31 | 2020-07-22 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-13 | 98079660.8653 | 17006675.991 | [5 empty] | 1611811.9037 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA9 | IKEA Extension MoA9
IKEA | 1 | 10 | 16241524.1447 | 16241435.02 | -89.1247 | 10981834.92 | 10892925.95 | -88908.97 |  |  |  | 10981834.92 | 2020-08-31 | 2020-08-15 | 2020-08-18 | 56 | 2020-10-13 | 2020-09-27 | 114321185.01 | 16856139.28 | [5 empty] | 2394063.2 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA10 | IKEA Extension MoA10
IKEA | 1 | 11 | 40022086.8222 | 40022086.82 | -0.00225 | 16592416.38 | 16989482.64 | 397066.26 |  |  |  | 16592416.38 | 2020-09-30 | 2020-10-12 | 2020-10-14 | 56 | 2020-12-09 | 2020-11-15 | 154343271.8322 | 2685460.4477 | [5 empty] | 3391607 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA11 | IKEA Extension MoA11
IKEA | 1 | 12 | 27619584.4178 | 27691689.43 | 72105.0123 | 15898929.26 | 15913350.29 | 14421.03 |  |  |  | 15898929.26 | 2020-11-30 | 2020-11-25 | 2020-11-29 | 56 | 2021-01-24 | 2021-12-30 | 181962856.25 | -4332571 | [5 empty] | 0 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA12 | IKEA Extension MoA12
IKEA | 1 | 13 | 3981119.65 | 3981119.65 | -6.0536e-09 | 5400893.31 | 4064871.9 | -1336021.41 |  |  |  | 5400893.31 | 2020-12-31 | 2021-01-10 | 2021-01-13 | 56 | 2021-03-10 | 2021-02-18 | 185943975.9 | [6 empty] | 4547790.9 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA13 | IKEA Extension MoA13
IKEA | 1 | 14 | 10525422.84 | 10453317.84 | -72105 | 15116863.46 | 20582119.9 | 5465256.44 |  |  |  | 15116863.46 | 2021-04-30 | 2021-04-19 | 2021-06-24 | 56 | 2021-08-19 | 2021-08-09 | 196469398.74 | [6 empty] | 0 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA14 | IKEA Extension MoA14
JICA | 1 | 19 | 1210863.76 | 0 | -1210863.76 | 1141675.91 | 0 | -1141675.91 |  |  |  | 1141675.91 | 2017-10-31 | 2017-10-28 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-30 | 117203462.77 | 0 | [5 empty] | 0 | 1210863.76 | 117203462.77 | 1141675.91 | 0 |  |  |  | JICA19 | 019
JICA | 1 | 20 | 283125.01 | 0 | -283125.01 | 413014.8 | 0 | -413014.8 |  |  |  | 413014.8 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 117486587.78 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | JICA20 | 020
#N/A
Kafr Shokr | 2 | 1 |  | 98312039.43 | 98312039.43 | 28845197.4 | 29730005.7605 | 884808.3605 |  |  |  |  | 2021-03-31 | 2021-03-14 | 2021-03-17 | 60 | 2021-05-16 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 1 | Kafr Shokr Bridge1
Kafr Shokr | 2 | 2 |  | 21005491.44 | 21005491.44 | 6242742.2 | 6242742.164 | -0.036 |  |  |  |  | 2021-03-31 | 2021-03-31 | 2021-04-07 | 60 | 2021-06-06 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 2 | Kafr Shokr Bridge2
Kafr Shokr | 2 | 3 |  | 9630317.86 | 9630317.86 | 8372664.9 | 8372664.936 | 0.036 |  |  |  |  | 2021-04-30 | 2021-04-30 | 2021-05-23 | 60 | 2021-07-22 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 3 | Kafr Shokr Bridge3
Kafr Shokr | 2 | 4 |  | 14900014.29 | 14900014.29 | 8190447.9 | 8190447.9 | 0 |  |  |  |  | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 4 | Kafr Shokr Bridge4
Kafr Shokr | 2 | 5 |  | 6107250 | 6107250 | 5371513.65 | 5371513.65 | 0 |  |  |  |  | 2021-07-31 | 2021-07-31 | 2021-08-12 | 60 | 2021-10-11 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 5 | Kafr Shokr Bridge5
Kafr Shokr | 2 | 6 |  | 2805242.86 | 2805242.86 | 444257.7 | 444257.73 | 0.03 |  |  |  |  | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 6 | Kafr Shokr Bridge6
Kafr Shokr | 2 | 7 | 31881474.95 | 30363309.48 | -1518165.47 | 26652960.08 | 27070646.13 | 417686.05 |  |  |  | 25823994.7095 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 60 | 2021-12-09 |  | 108184525 | [6 empty] | 0 | 31881474.95 | 108184525 | 25823994.7095 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 7 | Kafr Shokr Bridge7
Kafr Shokr | 2 | 8 | 2504502 | 1839476.19 | -665025.81 | 2028646.62 | 1610960.6295 | -417685.9905 |  |  |  | 2028646.62 | 2021-11-30 | 2021-11-30 | 2021-11-30 | 60 | 2022-01-29 | 2021-12-25 | 110689027 | [6 empty] | 0 | 2504502 | 110689027 | 2028646.62 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 8 | Kafr Shokr Bridge8
Kafr Shokr | 2 | 9 | 5785188 | 11019405.72 | 5234217.72 | 4811891.1 | 4811892.2 | 1.1 |  |  |  | 0 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-08-07 | 116474215 | [6 empty] | 0 | 5785188 | 116474215 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 9 | Kafr Shokr Bridge9
Kafr Shokr | 2 | 10 | 2841975 | 5413285.72 | 2571310.72 | 2390708.7 | 2390708.77 | 0.07 |  |  |  | 2301999.75 | 2021-12-31 | 2021-12-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-09-26 | 119316190 | [6 empty] | 0 | 2841975 | 119316190 | 2301999.75 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 10 | Kafr Shokr Bridge10
#N/A
Katameya - Creeks | 1 | 1 | 2910883.3063 | 2919397.4 | 8514.0937 | 2741191.29 | 2748675.4515 | 7484.1615 | 200000000 |  |  | 2741191.2884 | 2020-12-31 | 2020-12-31 | 2021-01-14 | 40 | 2021-02-23 | 2021-01-31 | 2910883.3063 | [6 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks1 | Kattameya Creeks1
Katameya - Creeks | 1 | 2 | 11780609.6823 | 12368012.17 | 587402.4877 | 56302769.9409 | 11295285.7785 | -45007484.1624 |  | 45000000 |  | 11302769.9409 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 40 | 2021-03-16 | 2021-02-18 | 14691492.9885 | 595916.5854 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks2 | Kattameya Creeks2
Katameya - Creeks | 1 | 3 | 36329559.9323 | 41751425.71 | 5421865.7777 | 84570120.9 | 39570120.8955 | -45000000.0045 |  | 45000000 |  | 39570120.8973 | 2021-02-28 | 2021-02-28 | 2021-03-06 | 40 | 2021-04-15 | 2021-03-21 | 51021052.9208 | 6017782.3615 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks3 | Kattameya Creeks3
Katameya - Creeks | 1 | 4 | 30128591.4792 | 31881858.16 | 1753266.6808 | 49688637.31 | 29687637.308 | -20001000.002 |  | 20000000 |  | 29688637.31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 40 | 2021-05-16 | 2021-04-22 | 81149644.4 | 7771049.05 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks4 | Kattameya Creeks4
Katameya - Creeks | 1 | 5 | 41641437.57 | 43155172.94 | 1513735.37 | 40006572.36 | 40007572.367 | 1000.007 |  |  |  | 40006572.36 | 2021-04-30 | 2021-05-06 | 2021-05-06 | 40 | 2021-06-15 | 2021-05-23 | 122791081.97 | 9284784.42 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks5 | Kattameya Creeks5
Katameya - Creeks | 1 | 6 | 35290109.98 | 32255415.11 | -3034694.87 | 29363826.77 | 29363826.7655 | -0.0045 |  |  |  | 29363826.77 | 2021-05-31 | 2021-06-06 | 2021-06-06 | 40 | 2021-07-16 | 2021-06-29 | 158081191.95 | 6250089.55 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks6 | Kattameya Creeks6
Katameya - Creeks | 1 | 7 | 46826693.78 | 48280873.42 | 1454179.64 | 44380443 | 44380444.2275 | 1.2275 |  |  |  | 44596069.78 | 2021-06-30 | 2021-07-06 | 2021-07-06 | 40 | 2021-08-15 | 2021-07-27 | 204907885.73 | 7704269.19 | [5 empty] | 523000 | 46826693.78 | 204907885.73 | 44596069.78 | Kattameya Creeks |  |  |  | Katameya - Creeks7 | Kattameya Creeks7
Katameya - Creeks | 1 | 8 | 41480221.37 | 43370006.73 | 1889785.36 | 40343227.98 | 40343227.9665 | -0.0135 |  |  |  | 40343227.98 | 2021-07-31 | 2021-08-07 | 2021-08-07 | 40 | 2021-09-16 | 2021-08-07 | 246388107.1 | 9594054.56 | [5 empty] | 777600 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks8 | Kattameya Creeks8
Katameya - Creeks | 1 | 9 | 44965022.45 | 45658900.57 | 693878.12 | 43056438.19 | 43056438.1785 | -0.0115 |  |  |  | 43056438.19 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 40 | 2021-10-15 | 2021-09-23 | 291353129.55 | 10287932.68 | [5 empty] | 800600 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks9 | Kattameya Creeks9
Katameya - Creeks | 1 | 10 | 37520387.97 | 38757548.53 | 1237160.56 | 61159972.97 | 36159161.9365 | -25000811.0335 |  |  |  | 36159161.93 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 40 | 2021-11-15 | 2021-10-28 | 328873517.52 | 11525093.24 | [5 empty] | 813250 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks10 | Kattameya Creeks10
Katameya - Creeks | 1 | 11 |  | 46662391.16 | 46662391.16 | 43214038.28 | 43214038.288 | 0.008 |  |  |  | 43214038.28 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 40 | 2021-12-16 | 2021-11-22 | 379505848.55 | 7555153.37 | [5 empty] | 823370 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks11 | Kattameya Creeks11
Katameya - Creeks | 1 | 12 | 40810274.28 | 39536093.61 | -1274180.67 | 36461301.55 | 36461301.5305 | -0.0195 |  |  |  | 36461301.55 | 2021-11-30 | 2021-11-30 | 2021-12-06 | 40 | 2022-01-15 | 2021-12-27 | 420316122.83 | 6280972.71 | [5 empty] | 841080 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks12 | Kattameya Creeks12
Katameya - Creeks | 1 | 13 | 39636501.96 | 41829784.58 | 2193282.62 | 39353596.01 | 39353596.009 | -0.00099999 |  |  |  | 39353596.01 | 2021-12-31 | 2021-12-31 | 2022-01-08 | 40 | 2022-02-17 | 2022-01-27 | 459952624.79 | 8474255.32 | [5 empty] | 863850 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks13 | Kattameya Creeks13
Katameya - Creeks | 1 | 14 | 45239351.95 | 48574512.67 | 3335160.72 | 45904629.98 | 45904629.9935 | 0.0135 |  |  |  | 45904629.98 | 2022-01-31 | 2022-01-31 | 2022-02-07 | 40 | 2022-03-19 | 2022-02-24 | 505191976.74 | 11809416.04 | [5 empty] | 0 | 45239351.95 | 505191976.74 | 45904629.98 | Kattameya Creeks |  |  |  | Katameya - Creeks14 | Kattameya Creeks14
Katameya - Creeks | 1 | 15 | 47493723.66 | 51903318.98 | 4409595.32 | 49567395 | 49567394.569 | -0.431 |  |  |  | 49567394.59 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 40 | 2022-04-14 | 2022-03-14 | 552685700.4 | 16219011.36 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks15 | Kattameya Creeks15
Katameya - Creeks | 1 | 16 | 48315079.39 | 47021445.38 | -1293634.01 | 44583744 | 44583744.0045 | 0.0045 |  |  |  | 44583744.4 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 40 | 2022-05-16 | 2022-04-17 | 601000779.79 | 14925377.35 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks16 | Kattameya Creeks16
Katameya - Creeks | 1 | 17 | 37444918.46 | 37521775.17 | 76856.71 | 36501027.74 | 36571027.7485 | 70000.0085 |  |  |  | 36501027.74 | 2022-04-30 | 2022-04-30 | 2022-05-07 | 40 | 2022-06-16 | 2022-05-29 | 638445698.25 | 15002234.06 | 50675010 |  | 97675643 |  |  | 1009270 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks17 | Kattameya Creeks17
Katameya - Creeks | 1 | 18 | 37748158.21 | 42935687.01 | 5187528.8 | 41565441.8 | 41641258.1345 | 75816.3345 |  |  |  | 41565441.8 | 2022-05-31 | 2022-05-31 | 2022-06-05 | 40 | 2022-07-15 | 2022-06-05 | 676193856.46 | 20189762.86 | 59495615 |  | 103801771 |  |  | 1085086 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks18 | Kattameya Creeks18
Katameya - Creeks | 1 | 19 | 37876838.61 | 37484144.91 | -392693.7 | 36081249.47 | 36075433.1155 | -5816.3545 |  |  |  | 36081249.47 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-03 | 714070695.07 | 19797069.17 | 71508662.79 |  | 108653109.7 |  |  | 1084330 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks19 | Kattameya Creeks19
Katameya - Creeks | 1 | 20 | 23863809.78 | 25275496.94 | 1411687.16 | 24569045 | 24429045.007 | -139999.993 |  |  |  | 24569045.01 | 2022-07-31 | 2022-07-31 | 2022-08-07 | 40 | 2022-09-16 | 2022-08-21 | 737934504.85 | 21208756.33 | 79759027 |  | 110507501 |  |  | 944330 | 23863809.78 | 737934504.85 | 24569045.01 | Kattameya Creeks |  |  |  | Katameya - Creeks20 | Kattameya Creeks20
Katameya - Creeks | 1 | 21 | 37145495.17 | 36255948.47 | -889546.7 | 35259435.93 | 35259435.93 | 0 |  |  |  | 35259435.93 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 40 | 2022-10-15 | 2022-09-20 | 775080000.02 | 20319209.63 | 93957089.31 |  | 115330857 |  |  | 944330 | 37145495.17 | 775080000.02 | 35259435.93 | Kattameya Creeks |  |  |  | Katameya - Creeks21 | Kattameya Creeks21
Katameya - Creeks | 1 | 22 | 28622135.19 | 32375932.35 | 3753797.16 | 31299260.01 | 31299260.0175 | 0.0075 |  |  |  | 31299260.01 | 2022-09-30 | 2022-09-30 | 2022-10-06 | 40 | 2022-11-15 | 2022-10-22 | 803702135.21 | 24073006.79 | 104402623 |  | 118783626 |  |  | 944330 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks22 | Kattameya Creeks22
Katameya - Creeks | 1 | 23 | 24245600.88 | 30664402.09 | 6418801.21 | 29834733.07 | 29834733.0645 | -0.0055 |  |  |  | 29834733.07 | 2022-10-31 | 2022-10-25 | 2022-11-06 | 40 | 2022-12-16 | 2022-11-28 | 827947736.09 | 30491808 | 110827191.37 |  | 121373214 |  |  | 944330 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks23 | Kattameya Creeks23
Katameya - Creeks | 1 | 24 | 30975620.82 | 38710056.01 | 7734435.19 | 37876579.92 | 37876579.918 | -0.002 |  |  |  | 37876581.29 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 40 | 2023-01-14 | 2022-12-26 | 858923356.91 | 38226243.19 | 123338828 |  | 123817551 |  |  | 944330 | 30975620.82 | 858923356.91 | 37876581.29 | Kattameya Creeks |  |  |  | Katameya - Creeks24 | Kattameya Creeks24
Katameya - Creeks | 1 | 25 | 21870157.41 | 45327391.41 | 23457234 | 45191848.31 | 45191848.31 | 0 |  |  |  | 45191848.32 | 2022-12-31 | 2022-12-31 | 2023-01-03 | 40 | 2023-02-12 | 2023-01-25 | 880793514.32 | 61683477.19 | 133104770 |  | 126424933 |  |  | 944330 | 21870157.41 | 880793514.32 | 45191848.32 | Kattameya Creeks |  |  |  | Katameya - Creeks25 | Kattameya Creeks25
Katameya - Creeks | 1 | 26 | 41254688.36 | 73494584.17 | 32239895.81 | 74263221 | 74263221 | 0 |  |  |  | 74263221.64 | 2023-01-31 | 2023-01-31 | 2023-02-05 | 40 | 2023-03-17 | 2023-02-28 | 922048202.68 | 93923373 | 158579085 |  | 130310913 |  |  | 975300.2 | 41254688.36 | 922048202.68 | 74263221.64 | Kattameya Creeks |  |  |  | Katameya - Creeks26 | Kattameya Creeks26
Katameya - Creeks | 1 | 27 | 23948941.02 | 35445373.6 | 11496432.58 | 35452924 | 35452924 | 0 |  |  |  | 35452924.06 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 40 | 2023-04-14 | 2023-03-30 | 945997143.7 | 105419805.57 | 170052796 |  | 133396502 |  |  | 975300 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks27 | Kattameya Creeks27
Katameya - Creeks | 1 | 28 | 26373696.19 | 28889381.89 | 2515685.7 | 28650459 | 28650459 | 0 |  |  |  | 28650459.02 | 2023-03-31 | 2023-03-30 | 2023-04-06 | 40 | 2023-05-16 | 2023-05-04 | 972370839.89 | 107935491.27 | 183454579.15 |  | 136180192 |  |  | 975300 | 26373696.19 | 972370839.89 | 28650459.02 | Kattameya Creeks |  |  |  | Katameya - Creeks28 | Kattameya Creeks28
Katameya - Creeks | 1 | 29 | 23994845.49 | 40212630.08 | 16217784.59 | 40904481 | 40904481 | 0 |  |  |  | 40904481.77 | 2023-04-30 | 2023-04-30 | 2023-05-10 | 40 | 2023-06-19 | 2023-06-03 | 996365685.38 | 124153275.86 | 196775586 |  | 138759517 |  |  | 1187195.2 | 23994845.49 | 996365685.38 | 40904481.77 | Kattameya Creeks |  |  |  | Katameya - Creeks29 | Kattameya Creeks29
Katameya - Creeks | 1 | 30 | 81851684.98 | 55298315.11 | -26553369.87 | 43084120 | 43084120 | 0 |  |  |  | 43084120.03 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 40 | 2023-07-17 | 2023-06-22 | 1078217370.36 | 97599905.99 | 269087133.95 |  | 142922586 |  |  | 1474123.2 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks30 | Kattameya Creeks30
Katameya - Creeks | 1 | 31 | 34090513.58 | 49290024.52 | 15199510.94 | 37106226 | 37106226 | 0 |  |  |  | 37106226.16 | 2023-06-30 | 2023-06-30 | 2023-07-09 | 40 | 2023-08-18 | 2023-07-31 | 1112307883.94 | 112799416.94 | 291661196 |  | 146035580.84 |  |  | 1474123.2 | 34090513.58 | 1112307883.94 | 37106226.16 | Kattameya Creeks |  |  |  | Katameya - Creeks31 | Kattameya Creeks31
Katameya - Creeks | 1 | 32 | 36694395.36 | 52360770.17 | 15666374.81 | 41216438 | 41216438 | 0 |  |  |  | 53216438.64 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 40 | 2023-09-17 | 2023-09-04 | 1149002279.3 | 128465791.75 | 319241513 |  | 149874135 |  |  | 1474123.2 | 0 | 0 | 53390542.82 | Kattameya Creeks |  |  |  | Katameya - Creeks32 | Kattameya Creeks32
Katameya - Creeks | 1 | 33 | 61801377.92 | 61236907.71 | -564470.21 | 47329833 | 47329832.9684 | -0.0316 |  |  |  | 47329832.99 | 2023-08-31 | 2023-08-31 | 2023-09-07 | 40 | 2023-10-17 | 2023-10-01 | 1210803657.22 | 127901321.55 | 370075065.87 |  | 154477701.6 |  |  | 1474123.2 | 61801377.92 | 1210803657.22 | 47329832.99 | Kattameya Creeks |  |  |  | Katameya - Creeks33 | Kattameya Creeks33
Katameya - Creeks | 1 | 34 | 67431952.34 | 82997244.56 | 15565292.22 | 70308953 | 70308953 | 0 |  |  |  | 70308953.76 | 2023-09-30 | 2023-09-30 | 2023-10-08 | 40 | 2023-11-17 | 2023-11-02 | 1278235609.56 | 143466613.76 | 421285092.94 |  | 161880059 |  |  | 2286300.2 | 67431952.34 | 1278235609.56 | 70308953.76 | Kattameya Creeks |  |  |  | Katameya - Creeks34 | Kattameya Creeks34
Katameya - Creeks | 1 | 35 | 61247331.12 | 59094596.48 | -2152734.64 | 46816344 | 46816344 | 0 |  |  |  | 46816344.41 | 2023-10-31 | 2023-10-31 | 2023-11-08 | 40 | 2023-12-18 | 2023-12-06 | 1339482940.68 | 141313879.12 | 467826001.19 |  | 169260713.53 |  |  | 2593710.2 | 61247331.12 | 1339482940.68 | 46816344.41 | Kattameya Creeks |  |  |  | Katameya - Creeks35 | Kattameya Creeks35
Katameya - Creeks | 1 | 36 | 74463161.12 | 64452457.92 | -10010703.2 | 50530224.78 | 50530224.78 | 0 |  |  |  | 50530225.45 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 40 | 2024-01-16 | 2023-12-30 | 1413946101.8 | 131303175.93 | 514457815.28 |  | 175537623 |  |  | 2835674.2 | 74463161.12 | 1413946101.8 | 50530225.45 | Kattameya Creeks |  |  |  | Katameya - Creeks36 | Kattameya Creeks36
Katameya - Creeks | 1 | 37 | 53331460.14 | 60819348.36 | 7487888.22 | 62109565 | 62109565 | 0 |  |  |  | 62109565.07 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-01-22 | 1467277561.94 | 138791064.14 | 557616767.77 |  | 179660456 |  |  | 3087279.2 | 53331460.14 | 1467277561.94 | 62109565.07 | Kattameya Creeks |  |  |  | Katameya - Creeks37 | Kattameya Creeks37
Katameya - Creeks | 1 | 38 | 83842743.6 | 78865309.72 | -4977433.88 | 79235150 | 79235149.8888 | -0.1112 |  |  |  | 79235149.9 | 2024-01-31 | 2024-01-31 | 2024-02-08 | 40 | 2024-03-19 | 2024-03-06 | 1551120305.54 | 133813630.27 | 619119624.83 |  | 194495708 |  |  | 3385105 | 83842743.6 | 1551120305.54 | 79235149.9 | Kattameya Creeks |  |  |  | Katameya - Creeks38 | Kattameya Creeks38
Katameya - Creeks | 1 | 39 | 81688930.92 | 66379928.69 | -15309002.23 | 66261026 | 66261026 | 0 |  |  |  | 66261026.21 | 2024-02-29 | 2024-02-29 | 2024-03-10 | 40 | 2024-04-19 | 2024-04-02 | 1632809236.46 | 118504628.04 | 681574347 |  | 206803236 |  |  | 3583708 | 81688930.92 | 1632809236.46 | 66261026.21 | Kattameya Creeks |  |  |  | Katameya - Creeks39 | Kattameya Creeks39
Katameya - Creeks | 1 | 40 | 66582662.04 | 52383248.29 | -14199413.75 | 52039038 | 52039038 | 0 |  |  |  | 52039038.12 | 2024-03-31 | 2024-03-31 | 2024-04-06 | 40 | 2024-05-16 | 2024-05-02 | 1699391898.5 | 104305214.28 | 732184516 |  | 217702929 |  |  | 3885490.2 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks40 | Kattameya Creeks40
Katameya - Creeks | 1 | 41 | 47455342.03 | 44558913.7 | -2896428.33 | 45340678.81 | 45340679.808 | 0.998 |  |  |  | 45340679.8 | 2024-04-30 | 2024-04-30 | 2024-05-08 | 40 | 2024-06-17 | 2024-05-25 | 1746847240.53 | 101408785.94 | 771118051 |  | 224726984.46 |  |  | 4067349.2 | 47455342.03 | 1746847240.53 | 45340679.8 | Kattameya Creeks |  |  |  | Katameya - Creeks41 | Kattameya Creeks41
Katameya - Creeks | 1 | 42 | 56995945.47 | 52161798.49 | -4834146.98 | 52791233 | 52791233 | 0 |  |  |  | 52791233.92 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 40 | 2024-07-19 | 2024-07-07 | 1803843186 | 96574638 | 816861989 |  | 232964321 |  |  | 4370002 | 56995945.47 | 1803843186 | 52791233.92 | Kattameya Creeks |  |  |  | Katameya - Creeks42 | Kattameya Creeks42
Katameya - Creeks | 1 | 43 | 56437240.4362 | 42016089.18 | -14421151.2562 | 21224102 | 21224102 | 0 |  |  |  | 30082113.9462 | 2024-06-30 | 2024-06-30 | 2024-07-10 | 40 | 2024-08-19 | 2024-07-27 | 1860280426.4362 | 90480931.8131 | 861619431.0834 |  | 241015625.4571 |  |  | 4370002.2 | 56437240.4362 | 1860280426.4362 | 30082113.9462 | Kattameya Creeks |  |  |  | Katameya - Creeks43 | Kattameya Creeks43
Katameya - Creeks | 1 | 44 | 49427006.6938 | 34374886.21 | -15052120.4838 | 8345106.3 | 8345106.3084 | 0.0084 |  |  |  | 8345106.3 | 2024-07-31 | 2024-07-31 | 2024-08-10 | 40 | 2024-09-19 | 2024-08-31 | 1909707433.13 | 67101367.22 | 899419335 |  | 247392879 |  |  | 4855643.2 | 49427006.6938 | 1909707433.13 | 8345106.3 | Kattameya Creeks |  |  |  | Katameya - Creeks44 | Kattameya Creeks44
Katameya - Creeks | 1 | 45 | 67801530.87 | 50790503.79 | -17011027.08 | 8654893.7 | 24274088.3716 | 15619194.6716 |  |  |  | 24274088.38 | 2024-08-31 | 2024-08-31 | 2024-09-09 | 40 | 2024-10-19 | 2024-10-03 | 1977508964 | 50090340 | 947220416 |  | 256761214 |  |  | 5144638 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks45 | Kattameya Creeks45
Katameya - Creeks | 1 | 46 | 42454238 | 0 | -42454238 | 0 | 0 | 0 |  |  |  | 22007540.78 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 40 | 2024-11-19 | 2024-11-04 | 2019963202 | 39951618 | 976799080 |  | 264112905 |  |  | 5327913 | 42454238 | 2019963202 | 22007540.78 | Kattameya Creeks |  |  |  | Katameya - Creeks46 | Kattameya Creeks46
Katameya - Creeks | 1 | 47 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-11-09 | 40 | 2024-12-19 | [8 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks47 | Kattameya Creeks47
KFW | 1 | 109 | 156311.35 | 0 | -156311.35 | 128570.36 | 0 | -128570.36 |  |  |  | 128570.36 | 2017-09-30 | 2017-10-09 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-23 | 20308378.88 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KFW109 | 0109
KFW | 1 | 110 | 357187.5 | 0 | -357187.5 | 377225.16 | 0 | -377225.16 |  |  |  | 377225.16 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 20665566.38 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KFW110 | 0110
Khatatba Bridge | 2 | 1 | 42898060 | 40855295.24 | -2042764.76 | 803531.75 | 6931826.092 | 6128294.342 |  |  |  | 8313070.05 | 2022-01-31 | 2022-01-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-02-08 | 42898060 | [6 empty] | 0 | 0 | 0 | 0 | El Khatatba Bridge |  |  |  | Khatatba Bridge1 | El Khatatba Bridge1
Khatatba Bridge | 2 | 2 | 10581515 | 2437694.05 | -8143820.95 | 7509538.3 | 1381244.0525 | -6128294.2475 |  |  |  | 10363626.0758 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 53479575 | [6 empty] | 0 | 0 | 0 | 0 | El Khatatba Bridge |  |  |  | Khatatba Bridge2 | El Khatatba Bridge2
Khatatba Bridge | 2 | 4 | 50062250 | 0 | -50062250 | 36303482.3 | 0 | -36303482.3 |  |  |  | 49031394.797 | 2022-07-31 | 2022-08-01 | 2022-08-15 | 60 | 2022-10-14 | 2022-08-15 | 103541825 | [6 empty] | 0 | 0 | 0 | 0 | El Khatatba Bridge |  |  |  | Khatatba Bridge4 | El Khatatba Bridge4
KSA-Tarek AbdelHakim Center | 1 | 1 | 1174788.1 | 0 | -1174788.1 | 1183249.5731 | 0 | -1183249.5731 |  |  |  | 951578.36 | 2023-02-28 | 2023-02-28 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 1174788.1 |  |  |  |  | 117478.81 |  | 0 | 1174788.1 | 1174788.1 | 951578.36 | 0 |  |  |  | KSA-Tarek AbdelHakim Center1 | 01
KSA-Tarek AbdelHakim Center | 1 | 2 | 2619891.03 | 0 | -2619891.03 | 562894.3581 | 0 | -562894.3581 |  |  |  | 2122111.73 | 2023-03-31 | 2023-03-31 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 3794679.13 |  |  |  |  | 379467.91 |  | 0 | 2619891.03 | 3794679.13 | 2122111.73 | 0 |  |  |  | KSA-Tarek AbdelHakim Center2 | 02
KSA-Tarek AbdelHakim Center | 1 | 3 | 1124829.43 | 0 | -1124829.43 | 194180.7389 | 0 | -194180.7389 |  |  |  | 911111.84 | 2023-04-30 | 2023-04-30 | 2023-06-22 | 75 | 2023-09-05 | 2023-07-25 | 4919508.56 |  |  |  |  | 491950.85 |  | 0 | 1124829.43 | 4919508.56 | 911111.84 | 0 |  |  |  | KSA-Tarek AbdelHakim Center3 | 03
KSA-Tarek AbdelHakim Center | 1 | 4 | 1181749.35 | 0 | -1181749.35 | 242494.97 | 0 | -242494.97 |  |  |  | 957216.97 | 2023-05-31 | 2023-05-31 | 2023-07-24 | 75 | 2023-10-07 | 2023-07-25 | 6101257.91 |  |  |  |  | 610125.78 |  | 0 | 1181749.35 | 6101257.91 | 957216.97 | 0 |  |  |  | KSA-Tarek AbdelHakim Center4 | 04
KSA-Tarek AbdelHakim Center | 1 | 5 |  | 0 | 0 | 260811.86 | 0 | -260811.86 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-09-14 | 75 | 2023-11-28 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center5 | 05
KSA-Tarek AbdelHakim Center | 1 | 6 |  | 0 | 0 | 253333.77 | 0 | -253333.77 |  |  |  |  | 2023-07-31 | 2023-07-31 | 2023-09-14 | 75 | 2023-11-28 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center6 | 06
KSA-Tarek AbdelHakim Center | 1 | 7 |  | 0 | 0 | 450546.16 | 0 | -450546.16 |  |  |  |  | 2023-08-31 | 2023-08-31 | 2023-09-14 | 75 | 2023-11-28 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center7 | 07
KSA-Tarek AbdelHakim Center | 1 | 8 |  | 0 | 0 | 630195.46 | 0 | -630195.46 |  |  |  |  | 2023-09-30 | 2023-09-30 | 2023-10-17 | 75 | 2023-12-31 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center8 | 08
KSA-Tarek AbdelHakim Center | 1 | 9 |  | 0 | 0 | 1513478.59 | 0 | -1513478.59 |  |  |  |  | 2023-10-31 | 2023-11-06 | 2023-11-06 | 75 | 2024-01-20 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center9 | 09
KSA-Tarek AbdelHakim Center | 1 | 10 |  | 0 | 0 | 1468894.06 | 0 | -1468894.06 |  |  |  |  | 2023-11-30 | 2023-11-21 | 2023-11-21 | 75 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center10 | 010
KSA-Tarek AbdelHakim Center | 1 | 11 | 6272151.58 | 0 | -6272151.58 | 0 | 0 | 0 |  |  |  | 5080442.78 | 2023-12-31 | 2023-12-24 | 2023-12-24 | 75 | 2024-03-08 | 2024-01-04 | 34906557.56 |  |  |  |  | 3367198.74 |  | 0 | 6272151.58 | 34906557.56 | 5080442.78 | 0 |  |  |  | KSA-Tarek AbdelHakim Center11 | 011
KSA-Tarek AbdelHakim Center | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-05-09 | 2024-09-24 | 75 | 2024-12-08 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center12 | 012
#N/A
LEKELA | 1 | 1 |  | 17769330.58 | 17769330.58 | 37970902.46 | 4795487.799 | -33175414.661 | 36300000 |  |  |  | 2020-03-31 | 2020-03-15 | 2020-07-19 | 60 | 2020-09-17 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA1 | Lekela 250MW Wind Farm1
LEKELA | 1 | 2 |  | 7425139.15 | 7425139.15 | 1067868.0976 | 7467890.397 | 6400022.2994 |  |  |  |  | 2020-06-30 | 2020-06-30 | 2020-07-19 | 60 | 2020-09-17 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA2 | Lekela 250MW Wind Farm2
LEKELA | 1 | 3 |  | 2093986.78 | 2093986.78 | 1758948.8952 | 1758948.889 | -0.0062 |  |  |  |  | 2020-07-31 | 2020-07-27 | 2020-07-27 | 60 | 2020-09-25 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA3 | Lekela 250MW Wind Farm3
LEKELA | 1 | 4 |  | 777289.9 | 777289.9 | 652923.5 | 652923.515 | 0.015 |  |  |  |  | 2020-08-31 | 2020-08-31 | 2020-09-12 | 60 | 2020-11-11 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA4 | Lekela 250MW Wind Farm4
LEKELA | 1 | 5 | 8446374.726 | 8446374.72 | -0.006 | 7094954.7715 | 7094954.766 | -0.00552 |  |  |  | 7094954.7715 | 2020-09-30 | 2020-09-29 | 2020-09-30 | 60 | 2020-11-29 | 2020-10-08 | 14578092.546 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA5 | Lekela 250MW Wind Farm5
LEKELA | 1 | 6 | 20620363.18 | 17262367.14 | -3357996.04 | 14840272.4231 | 14840272.417 | -0.006116 |  |  |  | 14840272.4231 | 2020-10-31 | 2020-10-28 | 2020-10-28 | 60 | 2020-12-27 | 2020-11-12 | 35198455.726 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA6 | Lekela 250MW Wind Farm6
LEKELA | 1 | 7 | 19433463.8412 | 17619865.65 | -1813598.1912 | 15073158.35 | 15073158.3375 | -0.0125 |  |  |  | 15073158.3499 | 2020-11-30 | 2020-11-22 | 2020-11-23 | 60 | 2021-01-22 | 2020-12-02 | 54631919.5672 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA7 | Lekela 250MW Wind Farm7
LEKELA | 1 | 8 | 41700595.0348 | 38206684.39 | -3493910.6448 | 33357157.2169 | 33513527.4795 | 156370.2626 |  |  |  | 33513527.4715 | 2020-12-31 | 2020-12-28 | 2020-12-28 | 60 | 2021-02-26 | 2021-01-19 | 96332514.602 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA8 | Lekela 250MW Wind Farm8
LEKELA | 1 | 9 | 23169483.21 | 21219483.49 | -1949999.72 | 18594958.1925 | 18594958.1945 | 0.001976 |  |  |  | 18594958.1925 | 2021-01-31 | 2021-01-15 | 2021-01-31 | 60 | 2021-04-01 | 2021-02-05 | 119501997.812 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA9 | Lekela 250MW Wind Farm9
LEKELA | 1 | 10 | 27064762.4727 | 24782925.38 | -2281837.0927 | 21709399.51 | 21709399.519 | 0.009 |  |  |  | 21709399.51 | 2021-02-28 | 2021-02-15 | 2021-02-17 | 60 | 2021-04-18 | 2021-03-11 | 146566760.2847 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA10 | Lekela 250MW Wind Farm10
LEKELA | 1 | 11 | 18055279.9362 | 16648813.83 | -1406466.1062 | 14896483.6 | 14823033.5915 | -73450.0085 |  |  |  | 14823033.596 | 2021-03-31 | 2021-03-15 | 2021-03-16 | 60 | 2021-05-15 | 2021-05-20 | 164622040.2209 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA11 | Lekela 250MW Wind Farm11
LEKELA | 1 | 12 | 26449156.1285 | 24308181.24 | -2140974.8885 | 21477147.745 | 21477147.752 | 0.0069623 |  |  |  | 21477147.745 | 2021-04-30 | 2021-04-15 | 2021-04-20 | 60 | 2021-06-19 | 2021-05-24 | 191071196.3494 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA12 | Lekela 250MW Wind Farm12
LEKELA | 1 | 13 | 6179424.4906 | 2899145.1 | -3280279.3906 | 2329136.4958 | 2329136.495 | -0.00080502 |  |  |  | 2329136.4958 | 2021-05-31 | 2021-05-15 | 2021-05-24 | 60 | 2021-07-23 | 2021-08-01 | 197250620.84 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA13 | Lekela 250MW Wind Farm13
LEKELA | 1 | 14 |  | 18187988.27 | 18187988.27 | 12951636.6142 | 12931636.6285 | -19999.9857 |  |  |  |  | 2021-06-30 | 2021-06-15 | 2021-07-26 | 60 | 2021-09-24 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA14 | Lekela 250MW Wind Farm14
LEKELA | 1 | 15 | 6597023.32 | 15041907.67 | 8444884.35 | 3839081.19 | 8754195.8235 | 4915114.6335 |  |  |  | 3229199.86 | 2021-10-31 | 2021-10-15 | 2022-11-15 | 60 | 2023-01-14 | 2022-12-14 | 207000000 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA15 | Lekela 250MW Wind Farm15
LEKELA | 1 | 16 | -0.0001 | 0 | 0.0001 | 8212932 | 0 | -8212932 |  |  |  | 8212932.01 | 2022-11-30 | 2022-11-20 | 2023-02-22 | 60 | 2023-04-23 | 2023-03-31 | 207000000 | [6 empty] | 0 | -0.0001 | 207000000 | 8212932.01 | Lekela 250MW Wind Farm |  |  |  | LEKELA16 | Lekela 250MW Wind Farm16
LEKELA Remedial | 1 | 2 |  | 7425139.15 | 7425139.15 | 7000000.52 | 7467890.397 | 467889.877 |  |  |  |  | 2024-01-31 | 2024-01-30 | 2024-02-26 | 60 | 2024-04-26 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA Remedial2 | Lekela 250MW Wind Farm2
LEKELA Remedial | 1 | 3 | 2884958.98 | 2093986.78 | -790972.2 | 3000357.34 | 1758948.889 | -1241408.451 |  |  |  | 3000357.86 | 2024-05-31 | 2024-05-19 | 2024-08-19 | 60 | 2024-10-18 | 2024-08-21 | 15655160.98 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA Remedial3 | Lekela 250MW Wind Farm3
LEKELA Remedial | 1 | 4 | 6153867.61 | 777289.9 | -5376577.71 | 6400022.32 | 652923.515 | -5747098.805 |  |  |  | 6400022.32 | 2024-08-31 | 2024-08-20 | 2024-08-21 | 60 | 2024-10-20 | 2024-10-20 | 21809028.59 |  |  |  | 2290980.91 |  |  | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA Remedial4 | Lekela 250MW Wind Farm4
#N/A
MDF Factory | 1 | 1 | 3709029.4 | 4162769.76 | 453740.36 | 47854244.4 | 7639890.6466 | -40214353.7534 | 41622365.4 |  |  | 6231879.24 | 2021-06-30 | 2021-06-30 | 2021-07-05 | 28 | 2021-08-02 | 2021-08-17 | 3709029.4 | 4472196.39 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory1 | MDF Factory1
MDF Factory | 1 | 2 | 5178414.72 | 14246453.58 | 9068038.86 | 13393735 | 10804321.9583 | -2589413.0417 | 6300000 |  |  | 7093735 | 2021-07-31 | 2021-08-08 | 2021-08-08 | 28 | 2021-09-05 | 2021-08-31 | 8887444.12 | 7086056.01 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory2 | MDF Factory2
MDF Factory | 1 | 3 | 9214079.17 | 12892747.34 | 3678668.17 | 18410664.56 | 11956077.4667 | -6454587.0933 | 2000000 |  |  | 8598866.23 | 2021-08-31 | 2021-08-31 | 2021-09-06 | 28 | 2021-10-04 | 2021-09-22 | 18101523.29 | 8983935.87 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory3 | MDF Factory3
MDF Factory | 1 | 4 | 9266652.88 | 12068060.73 | 2801407.85 | 19359615 | 11048205.3073 | -8311409.6927 | 2000000 |  |  | 8359615.97 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 28 | 2021-11-03 | 2021-10-27 | 27368176.17 | 10661948.66 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory4 | MDF Factory4
MDF Factory | 1 | 5 | 23662523.0739 | 28836911.51 | 5174388.4361 | 38802133.78 | 26370472.8636 | -12431660.9164 | 10016624.86 |  |  | 21785509.71 | 2021-10-31 | 2021-10-31 | 2021-11-07 | 28 | 2021-12-05 | 2021-12-05 | 51030699.2439 | 10195623.7568 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory5 | MDF Factory5
MDF Factory | 1 | 6 | 17937654.1261 | 21669465.7 | 3731811.5739 | 28503193.33 | 20230205.9677 | -8272987.3623 | 7332000 |  |  | 17171193.3155 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 28 | 2022-01-06 | 2022-01-20 | 68968353.37 | 11973915.52 | [5 empty] | 0 | 17937654.1261 | 68968353.37 | 17171193.3155 | MDF Factory |  |  |  | MDF Factory6 | MDF Factory6
MDF Factory | 1 | 7 | 16080953.7816 | 31404222.49 | 15323268.7084 | 59606480 | 15247412.6383 | -44359067.3617 | 6000000 |  |  | 14452550.5619 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 28 | 2022-02-08 | 2022-02-14 | 85049307.1516 | 12658184.96 | [5 empty] | 0 | 16588591.02 | 85556944.39 | 14851309.99 | MDF Factory |  |  |  | MDF Factory7 | MDF Factory7
MDF Factory | 1 | 8 | 12291002.2884 | 7933985.43 | -4357016.8584 | 29352571.68 | 13514522.7416 | -15838048.9384 | 11000000 |  |  | 12391060.05 | 2022-01-31 | 2022-01-31 | 2022-02-09 | 28 | 2022-03-09 | 2022-03-01 | 97340309.44 | 14426942.06 | [5 empty] | 0 | 12291002.2884 | 97340309.44 | 12391060.05 | MDF Factory |  |  |  | MDF Factory8 | MDF Factory8
MDF Factory | 1 | 9 | 8038787.77 | 10331670.72 | 2292882.95 | 18942922.65 | 8739856.8749 | -10203065.7751 | 13754630 |  |  | 7655361.33 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 28 | 2022-04-06 | 2022-04-07 | 105379097.21 | 14289033.25 |  |  |  | 2526800.69 | 2526800.69 | 0 | 8038787.77 | 105379097.21 | 7655361.33 | MDF Factory |  |  |  | MDF Factory9 | MDF Factory9
MDF Factory | 1 | 10 | 6155129.99 | 12252037.93 | 6096907.94 | 11719330.26 | 14703215.5981 | 2983885.3381 | 1488562.75 |  |  | 11119452.63 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 28 | 2022-05-11 | 2022-04-27 | 111534227.2 | 19004034.21 | [5 empty] | 0 | 6155129.99 | 111534227.2 | 11119452.63 | MDF Factory |  |  |  | MDF Factory10 | MDF Factory10
MDF Factory | 1 | 11 | 9364100.8 | 11285215.73 | 1921114.93 | 11835349.23 | 10374106.9038 | -1461242.3262 | 3000000 |  |  | 9991684.94 | 2022-04-30 | 2022-04-30 | 2022-04-28 | 28 | 2022-05-26 | 2022-06-07 | 120898328 | 19378872 | 6694496.17 |  | 8943366.16 | 2938817.5 | 2938817.5 | 985000 | 9364100.8 | 120898328 | 9991684.94 | MDF Factory |  |  |  | MDF Factory11 | MDF Factory11
MDF Factory | 1 | 12 | 27509389.27 | 37291327.43 | 9781938.16 | 25380982.3 | 25882723.2211 | 501740.9211 |  |  |  | 29337407.23 | 2022-05-31 | 2022-05-31 | 2022-06-11 | 28 | 2022-07-09 | 2022-06-29 | 148407717.27 | 21048487.96 | 9413326 |  | 14867864 | 3374171 | 3374171 | 0 | 27509389.27 | 148407717.27 | 29337407.23 | MDF Factory |  |  |  | MDF Factory12 | MDF Factory12
MDF Factory | 1 | 13 | 15343913.47 | 35534076.91 | 20190163.44 | 2351273.22 | 2860119.7471 | 508846.5271 |  |  |  | 19866888.03 | 2022-06-30 | 2022-06-30 | 2022-07-06 | 28 | 2022-08-03 | 2022-08-07 | 163751630.74 | 25112316.18 | 10650525.16 |  | 15407262.1 | 3894039.675 | 3894039.675 | 1300000 | 15343913.47 | 163751630.74 | 19866888.03 | MDF Factory |  |  |  | MDF Factory13 | MDF Factory13
MDF Factory | 1 | 14 | 11905906.3968 | 25805203.92 | 13899297.5232 | 11219362.36 | 23227533.8875 | 12008171.5275 |  |  |  | 11219361.6633 | 2022-07-31 | 2022-07-25 | 2022-08-14 | 28 | 2022-09-11 | 2022-09-25 | 175657537.1368 | 28064532.2963 | 10473927.4807 |  | 17096495.4946 | 4266369.805 | 4266369.805 | 3250000 | 12301138.79 | 176052769.53 | 15316196.46 | MDF Factory |  |  |  | MDF Factory14 | MDF Factory14
MDF Factory | 1 | 15 | 8651043.7332 | 15085332.3 | 6434288.5668 | 10812468.25 | 15790368.0492 | 4977899.7992 |  |  |  | 15409194.69 | 2022-08-31 | 2022-08-31 | 2022-09-08 | 28 | 2022-10-06 | 2022-10-09 | 184308580.87 | 33441117.05 | 10616746 |  | 16229441.88 | 4412077.4 | 4412077.4 | 1350000 | 8651043.7332 | 184308580.87 | 15409194.69 | MDF Factory |  |  |  | MDF Factory15 | MDF Factory15
MDF Factory | 1 | 16 | 21753082.06 | 13891677.72 | -7861404.34 | 10601848.06 | 12827443.3694 | 2225595.3094 |  |  |  | 22014291.85 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 28 | 2022-11-08 | 2022-11-06 | 206061662.93 | 35882692.55 | 10827826.68 |  | 16039161.03 | 4776541.575 | 4776541.575 | 3300000 | 21753082.06 | 206061662.93 | 22014291.85 | MDF Factory |  |  |  | MDF Factory16 | MDF Factory16
MDF Factory | 1 | 17 | 3503748.7 | 13012853.94 | 9509105.24 | 13701835.53 | 13738045.4627 | 36209.9327 |  |  |  | 15156893.21 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 28 | 2022-12-06 | 2022-11-23 | 209565411.63 | 38117303.52 | 12364842.71 |  | 20883147.71 | 5114135 | 5114135 | 2890000 | 3503748.7 | 209565411.63 | 15156893.21 | MDF Factory |  |  |  | MDF Factory17 | MDF Factory17
MDF Factory | 1 | 18 | 4093790.13 | 8557464.69 | 4463674.56 | 3474417.48 | 8046794.6243 | 4572377.1443 |  |  |  | 5028798.98 | 2022-11-30 | 2022-11-15 | 2022-11-27 | 28 | 2022-12-25 | 2022-12-11 | 213659201.76 | 38907634.85 | 12512881.83 |  | 19805682.68 | 5216480 | 5216480 | 2840000 | 4093790.13 | 213659201.76 | 5028798.98 | MDF Factory |  |  |  | MDF Factory18 | MDF Factory18
MDF Factory | 1 | 19 | 12077854.33 | 18177972.44 | 6100118.11 | 8855940.16 | 13406399.725 | 4550459.565 |  |  |  | 9756751.36 | 2022-11-30 | 2022-11-30 | 2022-12-12 | 28 | 2023-01-09 | 2022-12-28 | 225737056.09 | 37074813.73 | 17269270.26 |  | 19805682.68 | 5518426.4 | 5518426.4 | 1240000 | 12077854.33 | 225737056.09 | 9756751.36 | MDF Factory |  |  |  | MDF Factory19 | MDF Factory19
MDF Factory | 1 | 20 | 10662163.65 | 12424707.76 | 1762544.11 | 1506264.66 | 3607979.0847 | 2101714.4247 |  |  |  | 14838164.52 | 2022-12-31 | 2022-12-25 | 2022-12-22 | 28 | 2023-01-19 | 2023-01-12 | 236399219.74 | 44141114.86 | 18934354.95 |  | 21551157.34 | 5784980.495 | 5784980.495 | 1240000 | 10662163.65 | 236399219.74 | 14838164.52 | MDF Factory |  |  |  | MDF Factory20 | MDF Factory20
MDF Factory | 1 | 21 | 18933899.86 | 14221356.8 | -4712543.06 | 16783340.22 | 7032766.641 | -9750573.579 |  |  |  | 18749752.53 | 2023-01-31 | 2023-01-12 | 2023-01-19 | 28 | 2023-02-16 | 2023-02-06 | 255333119.6 | 44152242.9 | 21222761.6 |  | 32601298.43 | 6258327.99 | 6258327.99 | 890000 | 18933899.86 | 255333119.6 | 18749752.53 | MDF Factory |  |  |  | MDF Factory21 | MDF Factory21
MDF Factory | 1 | 22 | 3256087.31 | 9643470.77 | 6387383.46 | 9454487.21 | 9336218.2731 | -118268.9369 |  |  |  | 3016784.72 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 28 | 2023-03-08 | 2023-02-25 | 258589206.91 | 44812446.87 | 22595375.04 | 400000 | 31182122.08 | 6339730 | 6339730 | 490000 | 3256087.31 | 258589206.91 | 3016784.72 | MDF Factory |  |  |  | MDF Factory22 | MDF Factory22
MDF Factory | 1 | 23 | 38888289.8 | 37819950.25 | -1068339.55 | 10035885.59 | 14557763.9768 | 4521878.3868 |  |  |  | 26140854.32 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 28 | 2023-04-02 | 2023-03-22 | 297477496.71 | 41744854.59 | 37403483.04 | 400000 | 31433209.86 | 7311937.42 | 7311937.42 | 470000 | 38888289.8 | 297477496.71 | 26140854.32 | MDF Factory |  |  |  | MDF Factory23 | MDF Factory23
MDF Factory | 1 | 24 | 18681389.16 | 20607720.2 | 1926331.04 | 5923051.17 | 2441794.1756 | -3481256.9944 |  |  |  | 13504786.11 | 2023-03-31 | 2023-03-31 | 2023-04-04 | 28 | 2023-05-02 | 2023-04-30 | 316158885.87 | 36725913.89 | 48869956.89 | 400000 | 31459228.76 | 7778972.145 | 7778972.145 | 470000 | 18681389.16 | 316158885.87 | 13504786.11 | MDF Factory |  |  |  | MDF Factory24 | MDF Factory24
MDF Factory | 1 | 25 | 10484631.76 | 11020344.59 | 535712.83 | 4519315.77 | 5060375.9885 | 541060.2185 |  |  |  | 14874774.09 | 2023-04-30 | 2023-04-30 | 2023-05-08 | 28 | 2023-06-05 | 2023-06-05 | 326643517.63 | 41744047.17 | 58047371.04 | 650000 | 31459228.76 | 8041087.94 | 8041087.94 | 400000 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory25 | MDF Factory25
MDF Factory | 1 | 26 | 21011393.06 | 21659546.55 | 648153.49 | 12901160.06 | 13730860.297 | 829700.237 |  |  |  | 18123054.07 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 28 | 2023-07-06 | 2023-06-21 | 347654910.69 | 39628505.18 | 73625314.2 | 200000 | 33225314.57 | 8566372.765 | 8566372.765 | 450000 | 21011393.06 | 347654910.69 | 18123054.07 | MDF Factory |  |  |  | MDF Factory26 | MDF Factory26
MDF Factory | 1 | 27 | 10160280.74 | 7649824.31 | -2510456.43 | 19177600.34 | 19177600.34 | 0 |  |  |  | 21231778.46 | 2023-06-30 | 2023-06-30 | 2023-06-26 | 28 | 2023-07-24 | 2023-07-12 | 357815191.43 | 54504636.34 | 81071518.94 | 250000 | 33210812.42 | 8820379.785 | 8820379.785 | 450000 | 10160280.74 | 357815191.43 | 21231778.46 | MDF Factory |  |  |  | MDF Factory27 | MDF Factory27
MDF Factory | 1 | 28 | 4632219.77 | 4537395.02 | -94824.75 | 5380287.99 | 5380287.99 | 0 |  |  |  | 5471658.1245 | 2023-07-31 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 | 2023-07-31 | 362447411.2 | 57298682.38 | 84101651.16 | 200000 | 33299495.32 | 8936185.28 | 8936185.28 | 500000 | 4632219.77 | 362447411.2 | 5471658.1245 | MDF Factory |  |  |  | MDF Factory28 | MDF Factory28
MDF Factory | 1 | 29 | 7201895.8 | 6882776.19 | -319119.61 | 10038430.32 | 10041845.6384 | 3415.3184 |  |  |  | 13138195.96 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 28 | 2023-09-05 | 2023-09-10 | 369649307 | 63433973.15 | 88923223.93 | 200000 | 35138135.49 | 9116232.675 | 9116232.675 | 520000 | 7201895.8 | 369649307 | 13138195.96 | MDF Factory |  |  |  | MDF Factory29 | MDF Factory29
MDF Factory | 1 | 30 | 42878737.92 | 46563799.32 | 3685061.4 | 11530799.53 | 11554812.9428 | 24013.4128 |  |  |  | 12581507.75 | 2023-08-31 | 2023-08-30 | 2023-09-10 | 28 | 2023-10-08 | 2023-09-19 | 412528044.92 | 48447410.77 | 120743192.13 | 200000 | 35183358.23 | 10188201.125 | 10188201.125 | 550000 | 42878737.92 | 412528044.92 | 12581507.75 | MDF Factory |  |  |  | MDF Factory30 | MDF Factory30
MDF Factory | 1 | 31 | 26984773 | 25781281.67 | -1203491.33 | 18846610.6 | 18542599.6668 | -304010.9332 |  |  |  | 20429584.53 | 2023-09-30 | 2023-09-30 | 2023-10-05 | 28 | 2023-11-02 | 2023-10-07 | 439512817.92 | 52299084.09 | 141277943.84 | 200000 | 34937145.36 | 10862820.45 | 10862820.45 | 250000 | 26984773 | 439512817.92 | 20429584.53 | MDF Factory |  |  |  | MDF Factory31 | MDF Factory31
MDF Factory | 1 | 32 | 2754000 | 2754000 | 0 | 2726460 | 2726460 | 0 |  |  |  | 2726460 | 2023-10-31 | 2023-10-25 | 2023-10-26 | 28 | 2023-11-23 | 2023-10-26 | 442266817.92 | 52299084.09 | 144031943.84 | 200000 | 34937145.36 | 10931670.45 | 10931670.45 | 250000 | 2754000 | 442266817.92 | 2726460 | MDF Factory |  |  |  | MDF Factory32 | MDF Factory32
MDF Factory | 1 | 33 | 20665276.54 | 18965945.93 | -1699330.61 | 8808260.33 | 10638561.7072 | 1830301.3772 |  |  |  | 12154985.64 | 2023-10-31 | 2023-10-31 | 2023-11-07 | 28 | 2023-12-05 | 2023-11-25 | 462932094.46 | 52125340.59 | 161100913.16 | 250000 | 35201311.24 | 11448302 | 11448302 | 200000 | 20665276.54 | 462932094.46 | 12154985.64 | MDF Factory |  |  |  | MDF Factory33 | MDF Factory33
MDF Factory | 1 | 34 | 25469525.62 | 27337098.5 | 1867572.88 | 12466636.78 | 12636241.38 | 169604.6 |  |  |  | 13093494.9 | 2023-11-30 | 2023-11-30 | 2023-12-09 | 28 | 2024-01-06 | 2023-12-20 | 488401620.08 | 49181191.79 | 181875990.6 | 250000 | 35200228.82 | 12085040.5 | 12085040.5 | 200000 | 25469525.62 | 488401620.08 | 13093494.9 | MDF Factory |  |  |  | MDF Factory34 | MDF Factory34
MDF Factory | 1 | 35 | 7460561 | 8184195.01 | 723634.01 | 11964736.84 | 11964736.84 | 0 |  |  |  | 14005346.87 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 28 | 2024-01-28 | 2024-01-21 | 495862181.08 | 56480937.48 | 187067355.65 | 100000 | 35200149.54 | 12271554.525 | 12271554.525 | 350000 | 7460561 | 495862181.08 | 14005346.87 | MDF Factory |  |  |  | MDF Factory35 | MDF Factory35
MDF Factory | 1 | 36 | 24220349.75 | 24401575.22 | 181225.47 | 10194821.77 | 10167393.0388 | -27428.7312 |  |  |  | 12150509.06 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-28 | 520082530.83 | 52738337.77 | 208687659.78 | 200000 | 35240386.14 | 12877063.27 | 12877063.27 | 220000 | 24220349.75 | 520082530.83 | 12150509.06 | MDF Factory |  |  |  | MDF Factory36 | MDF Factory36
MDF Factory | 1 | 37 | 18799337.86 | 18482561.46 | -316776.4 | 4465149.39 | 4465149.39 | 0 |  |  |  | 7449862.86 | 2024-02-29 | 2024-02-29 | 2024-03-11 | 28 | 2024-04-08 | 2024-04-02 | 538881868.69 | 47546890.76 | 225598759.07 | 1500000 | 35240386.14 | 13347046.715 | 13347046.715 | 700000 | 18799337.86 | 538881868.69 | 7449862.86 | MDF Factory |  |  |  | MDF Factory37 | MDF Factory37
MDF Factory | 1 | 38 | 25264630.57 | 25020067.65 | -244562.92 | 9539881.65 | 9539881.65 | 0 |  |  |  | 10129299.6901 | 2024-03-31 | 2024-03-31 | 2024-04-08 | 28 | 2024-05-06 | 2024-04-24 | 564146499.26 | 42828938.17 | 247874489.5 | 200000 | 35240386.14 | 13978662.48 | 13978662.48 | 253450 | 25264630.57 | 564146499.26 | 10129299.6901 | MDF Factory |  |  |  | MDF Factory38 | MDF Factory38
MDF Factory | 1 | 39 | 17461783.47 | 17738610.9 | 276827.43 | 6984174.92 | 6984174.92 | 0 |  |  |  | 7951387.28 | 2024-04-30 | 2024-04-30 | 2024-05-07 | 28 | 2024-06-04 | 2024-05-22 | 581608282.73 | 39702840.21 | 261893208.84 | 200000 | 35240386.14 | 14415207 | 14415207 | 253450 | 17461783.47 | 581608282.73 | 7951387.28 | MDF Factory |  |  |  | MDF Factory39 | MDF Factory39
MDF Factory | 1 | 40 | -0.73 | 759488.56 | 759489.29 | 13054639.6 | 14022964.76 | 968325.16 |  |  |  | 13055049.84 | 2024-04-30 | 2024-04-30 | 2024-05-26 | 28 | 2024-06-23 | 2024-06-12 | 581608282 | 39702840 | 261893208 |  | 35240386 | 6101647 |  | 453450 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory40 | MDF Factory40
MDF Factory | 1 | 41 | 26553112.48 | 12031521.12 | -14521591.36 | 8347962.7 | 7229637.5348 | -1118325.1652 |  |  |  | 25000718.68 | 2024-05-31 | 2024-05-31 | 2024-06-06 | 28 | 2024-07-04 | 2024-06-13 | 608161394.48 | 40071589.73 | 273875725.24 |  | 35240386.14 | 7033092.855 | 7033092.855 | 303450 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory41 | MDF Factory41
MDF Factory | 1 | 42 | 750284.2 | 19536964.22 | 18786680.02 | 7602001.04 | 7602001.04 | 0 |  |  |  | 7547918.7 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 28 | 2024-08-04 | 2024-07-24 | 608911678.68 | 33497125 | 289636214 |  | 35240386 | 7100876.5 | 7100876.5 | 453450 | 750284.2 | 608911678.68 | 7547918.7 | MDF Factory |  |  |  | MDF Factory42 | MDF Factory42
MDF Factory | 1 | 43 | 11210135.32 | 0 | -11210135.32 | 45999180 | 0 | -45999180 |  |  |  | 57977475.46 | 2024-07-31 | 2024-07-31 | 2024-08-06 | 28 | 2024-09-03 | 2024-08-21 | 620121814 | 31321429 | 299419159 |  | 35243045 | 7887682 | 7887682 | 553450 | 11210135.32 | 620121814 | 57977475.46 | MDF Factory |  |  |  | MDF Factory43 | MDF Factory43
MDF Factory | 1 | 44 | 10205950.6 | 0 | -10205950.6 | 0 | 0 | 0 |  |  |  | 13417821.66 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 28 | 2024-10-03 | 2024-09-26 | 630327764.6 | 30187176.6062 | 308819628.409 |  | 35266531.1337 | 15775364.249 |  | 4593450 | 10205950.6 | 630327764.6 | 13417821.66 | MDF Factory |  |  |  | MDF Factory44 | MDF Factory44
MDF Factory | 1 | 45 | 16259922.8 | 0 | -16259922.8 | 0 | 0 | 0 |  |  |  | 21518034.22 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 28 | 2024-11-07 | 2024-11-04 | 646587687.4 | 21616659 | 325129806 |  | 34015260 | 15775364 |  | 3833450 | 16259922.8 | 646587687.4 | 21518034.22 | MDF Factory |  |  |  | MDF Factory45 | MDF Factory45
MDF Factory - Equip. | 1 | 1 | 474511.19 | 4162769.76 | 3688258.57 | 479255 | 7639890.6466 | 7160635.6466 |  |  |  | 487660.4 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-16 | 474511.19 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.1 | MDF Factory1
MDF Factory - Equip. | 1 | 2 | 2969783.71 | 14246453.58 | 11276669.87 | 2957905.39 | 10804321.9583 | 7846416.5683 |  |  |  | 2999481.54 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-18 | 3444294.9 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.2 | MDF Factory2
MDF Factory - Equip. | 1 | 3 | 2443276.13 | 12892747.34 | 10449471.21 | 2467707.5 | 11956077.4667 | 9488369.9667 |  |  |  | 2478572.15 | 2022-01-31 | 2022-02-15 | 2022-02-22 | 28 | 2022-03-22 | 2022-03-01 | 5887571.03 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.3 | MDF Factory3
MDF Factory - Equip. | 1 | 4 |  | 12068060.73 | 12068060.73 | 2118826 | 11048205.3073 | 8929379.3073 |  |  |  |  | 2022-03-31 | 2022-03-15 | 2022-03-29 | 28 | 2022-04-26 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.4 | MDF Factory4
MDF Factory - Equip. | 1 | 5 |  | 28836911.51 | 28836911.51 | 2067056 | 26370472.8636 | 24303416.8636 |  |  |  |  | 2022-04-30 | 2022-04-15 | 2022-04-24 | 28 | 2022-05-22 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.5 | MDF Factory5
MDF Factory - Equip. | 1 | 6 |  | 21669465.7 | 21669465.7 | 569764 | 20230205.9677 | 19660441.9677 |  |  |  |  | 2022-05-31 | 2022-05-15 | 2022-05-24 | 28 | 2022-06-21 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.6 | MDF Factory6
MDF Factory - Equip. | 1 | 7 |  | 31404222.49 | 31404222.49 | 795032 | 15247412.6383 | 14452380.6383 |  |  |  |  | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.7 | MDF Factory7
MDF Factory - Equip. | 1 | 8 | 340101.34 | 7933985.43 | 7593884.09 | 322760 | 13514522.7416 | 13191762.7416 |  |  |  | 324002.35 | 2022-07-31 | 2022-07-15 | 2022-07-25 | 28 | 2022-08-22 | 2022-08-02 | 11819751.78 | [6 empty] | 0 | 340101.34 | 11819751.78 | 324002.35 | MDF Factory |  |  |  | MDF Factory - Equip.8 | MDF Factory8
MDF Factory - Equip. | 1 | 9 |  | 10331670.72 | 10331670.72 | 1546900 | 8739856.8749 | 7192956.8749 |  |  |  |  | 2022-08-31 | 2022-08-15 | 2022-08-29 | 28 | 2022-09-26 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.9 | MDF Factory9
MDF Factory - Equip. | 1 | 10 |  | 12252037.93 | 12252037.93 | 362327.85 | 14703215.5981 | 14340887.7481 |  |  |  |  | 2022-09-30 | 2022-09-15 | 2022-09-20 | 28 | 2022-10-18 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.10 | MDF Factory10
MDF Factory - Equip. | 1 | 11 |  | 11285215.73 | 11285215.73 | 115740.16 | 10374106.9038 | 10258366.7438 |  |  |  |  | 2022-10-31 | 2022-10-15 | 2022-11-01 | 28 | 2022-11-29 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.11 | MDF Factory11
MDF Factory - Equip. | 1 | 12 |  | 37291327.43 | 37291327.43 | 617997.99 | 25882723.2211 | 25264725.2311 |  |  |  |  | 2022-11-30 | 2022-11-15 | 2022-11-30 | 28 | 2022-12-28 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.12 | MDF Factory12
MDF Factory - Equip. | 1 | 13 |  | 35534076.91 | 35534076.91 | 1033353.65 | 2860119.7471 | 1826766.0971 |  |  |  |  | 2022-12-31 | 2022-12-15 | 2023-01-04 | 28 | 2023-02-01 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.13 | MDF Factory13
MDF Factory - Equip. | 1 | 14 |  | 25805203.92 | 25805203.92 | 1342515 | 23227533.8875 | 21885018.8875 |  |  |  |  | 2023-01-31 | 2023-01-15 | 2023-02-05 | 28 | 2023-03-05 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.14 | MDF Factory14
MDF Factory - Equip. | 1 | 15 |  | 15085332.3 | 15085332.3 | 1508230 | 15790368.0492 | 14282138.0492 |  |  |  |  | 2023-02-28 | 2023-02-15 | 2023-03-05 | 28 | 2023-04-02 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.15 | MDF Factory15
MDF Factory - Equip. | 1 | 16 |  | 13891677.72 | 13891677.72 | 963455.46 | 12827443.3694 | 11863987.9094 |  |  |  |  | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.16 | MDF Factory16
MDF Factory - Equip. | 1 | 17 |  | 13012853.94 | 13012853.94 | 359356.67 | 13738045.4627 | 13378688.7927 |  |  |  |  | 2023-05-31 | 2023-06-15 | 2023-06-18 | 28 | 2023-07-16 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.17 | MDF Factory17
MDF Factory - Equip. | 1 | 18 |  | 8557464.69 | 8557464.69 | 536737.62 | 8046794.6243 | 7510057.0043 |  |  |  |  | 2023-06-30 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.18 | MDF Factory18
MDF Factory - Equip. | 1 | 19 | 461776.49 | 18177972.44 | 17716195.95 | 1190791 | 13406399.725 | 12215608.725 |  |  |  | 1199203.75 | 2023-08-31 | 2023-08-30 | 2023-09-09 | 28 | 2023-10-07 | 2023-10-02 | 21352041.9 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.19 | MDF Factory19
MDF Factory - Equip. | 1 | 20 |  | 12424707.76 | 12424707.76 | 606416.12 | 3607979.0847 | 3001562.9647 |  |  |  |  | 2023-09-30 | 2023-09-30 | 2023-10-16 | 28 | 2023-11-13 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.20 | MDF Factory20
MDF Factory - Equip. | 1 | 21 | 540952.41 | 14221356.8 | 13680404.39 | 600370.17 | 7032766.641 | 6432396.471 |  |  |  | 592013.93 | 2023-12-31 | 2023-12-20 | 2023-12-25 | 28 | 2024-01-22 | 2024-02-06 | 22578347.52 | [6 empty] | 0 | 540952.41 | 22578347.52 | 592013.93 | MDF Factory |  |  |  | MDF Factory - Equip.21 | MDF Factory21
MDF Factory - Equip. | 1 | 22 |  | 9643470.77 | 9643470.77 | 205199.38 | 9336218.2731 | 9131018.8931 |  |  |  |  | 2024-03-31 | 2024-03-31 | 2024-03-31 | 28 | 2024-04-28 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.22 | MDF Factory22
MDF Factory - Equip. | 1 | 23 | 539934.96 | 37819950.25 | 37280015.29 | 545334.31 | 14557763.9768 | 14012429.6668 |  |  |  | 638068.17 | 2024-04-30 | 2024-04-15 | 2024-05-02 | 28 | 2024-05-30 | 2024-05-08 | 23413265.89 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.23 | MDF Factory23
MDF Factory - Equip. | 1 | 24 | 250311 | 20607720.2 | 20357409.2 | 345289.58 | 2441794.1756 | 2096504.5956 |  |  |  | 252814.11 | 2024-04-30 | 2024-04-15 | 2024-05-08 | 28 | 2024-06-05 | 2024-05-21 | 23663576.89 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.24 | MDF Factory24
MDF Factory - Equip. | 1 | 25 | 631287.83 | 11020344.59 | 10389056.76 | 637190.72 | 5060375.9885 | 4423185.2685 |  |  |  | 637600.71 | 2024-06-30 | 2024-06-30 | 2024-06-26 | 28 | 2024-07-24 | 2024-07-01 | 24294864.72 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.25 | MDF Factory25
MDF Factory - Equip. | 1 | 26 | 1237289.1 | 21659546.55 | 20422257.45 | 0 | 13730860.297 | 13730860.297 |  |  |  | 1250071.98 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 28 | 2024-09-29 | 2024-10-02 | 25532153.82 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.26 | MDF Factory26
MDF Factory - Equip. | 1 | 27 | 20666.66 | 7649824.31 | 7629157.65 | 0 | 19177600.34 | 19177600.34 |  |  |  | 2574782 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 28 | 2024-10-28 | 2024-10-17 | 25552820.48 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.27 | MDF Factory27
MDF Factory - Local Fabrication | 1 | 1 |  | 4162769.76 | 4162769.76 | 920351.25 | 7639890.6466 | 6719539.3966 |  |  |  |  | 2022-02-28 | 2022-02-15 | 2022-03-03 | 28 | 2022-03-31 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication1 | MDF Factory1
MDF Factory - Local Fabrication | 1 | 2 |  | 14246453.58 | 14246453.58 | 711105.4 | 10804321.9583 | 10093216.5583 |  |  |  |  | 2022-03-31 | 2022-03-15 | 2022-03-21 | 28 | 2022-04-18 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication2 | MDF Factory2
MDF Factory - Local Fabrication | 1 | 3 | 1275030.41 | 12892747.34 | 11617716.93 | 897908 | 11956077.4667 | 11058169.4667 |  |  |  | 926763.57 | 2022-03-31 | 2022-04-10 | 2022-04-13 | 28 | 2022-05-11 | 2022-05-10 | 7663208.07 |  |  |  |  | 330996.915 | 330996.915 | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication3 | MDF Factory3
MDF Factory - Local Fabrication | 1 | 4 |  | 12068060.73 | 12068060.73 | 667444 | 11048205.3073 | 10380761.3073 |  |  |  |  | 2022-05-31 | 2022-05-15 | 2022-05-26 | 28 | 2022-06-23 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication4 | MDF Factory4
MDF Factory - Local Fabrication | 1 | 5 | 3437985.57 | 28836911.51 | 25398925.94 | 2517907.41 | 26370472.8636 | 23852565.4536 |  |  |  | 2517906.93 | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 | 2022-06-20 | 11948651.83 |  |  |  |  | 597432.59 | 597432.59 | 45737 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication5 | MDF Factory5
MDF Factory - Local Fabrication | 1 | 6 | 1016613.3233 | 21669465.7 | 20652852.3767 | 737043.71 | 20230205.9677 | 19493162.2577 |  |  |  | 737044.172 | 2022-07-31 | 2022-07-15 | 2022-08-11 | 28 | 2022-09-08 | 2022-09-22 | 12965265.1533 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication6 | MDF Factory6
MDF Factory - Local Fabrication | 1 | 7 | 2281868.7949 | 31404222.49 | 29122353.6951 | 785269 | 15247412.6383 | 14462143.6383 |  |  |  | 785269.1906 | 2022-08-31 | 2022-08-15 | 2022-08-30 | 28 | 2022-09-27 | 2022-09-22 | 15247133.9482 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication7 | MDF Factory7
MDF Factory - Local Fabrication | 1 | 8 | 619278.6162 | 7933985.43 | 7314706.8138 | 381060.37 | 13514522.7416 | 13133462.3716 |  |  |  | 1318063.6318 | 2022-09-30 | 2022-09-15 | 2022-09-22 | 28 | 2022-10-20 | 2022-09-22 | 15866412.5644 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication8 | MDF Factory8
MDF Factory - Local Fabrication | 1 | 9 |  | 10331670.72 | 10331670.72 | 1752018.76 | 8739856.8749 | 6987838.1149 |  |  |  |  | 2022-10-31 | 2022-11-15 | 2022-11-16 | 28 | 2022-12-14 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication9 | MDF Factory9
MDF Factory - Local Fabrication | 1 | 10 |  | 12252037.93 | 12252037.93 | 2881529.05 | 14703215.5981 | 11821686.5481 |  |  |  |  | 2022-11-30 | 2022-12-15 | 2022-12-26 | 28 | 2023-01-23 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication10 | MDF Factory10
MDF Factory - Local Fabrication | 1 | 11 |  | 11285215.73 | 11285215.73 | 2412700.43 | 10374106.9038 | 7961406.4738 |  |  |  |  | 2023-01-31 | 2023-01-15 | 2023-02-18 | 28 | 2023-03-18 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication11 | MDF Factory11
MDF Factory - Local Fabrication | 1 | 12 |  | 37291327.43 | 37291327.43 | 0 | 25882723.2211 | 25882723.2211 |  |  |  |  | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication12 | MDF Factory12
MDF Factory - Local Fabrication | 1 | 13 |  | 35534076.91 | 35534076.91 | 0 | 2860119.7471 | 2860119.7471 |  |  |  |  | 2023-06-30 | 2023-06-15 | 2023-06-21 | 28 | 2023-07-19 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication13 | MDF Factory13
MDF Factory - Local Fabrication | 1 | 14 | 12083527.18 | 25805203.92 | 13721676.74 | 10315795 | 23227533.8875 | 12911738.8875 |  |  |  | 11829412.85 | 2023-07-31 | 2023-08-15 | 2023-08-29 | 28 | 2023-09-26 | 2023-10-02 | 41889851.51 |  | 24971308.61 |  |  | 2094492.575 | 2094492.575 | 112541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication14 | MDF Factory14
MDF Factory - Local Fabrication | 1 | 15 | 5403242.47 | 15085332.3 | 9682089.83 | 2970230 | 15790368.0492 | 12820138.0492 |  |  |  | 5457274.9 | 2023-08-31 | 2023-10-15 | 2023-11-08 | 28 | 2023-12-06 | 2023-12-18 | 47293093.98 |  |  |  |  | 2364654.7 | 2364654.7 | 112541 | 5403242.47 | 47293093.98 | 5457274.9 | MDF Factory |  |  |  | MDF Factory - Local Fabrication15 | MDF Factory15
MDF Factory - Local Fabrication | 1 | 16 | 1250000 | 13891677.72 | 12641677.72 | 1262500 | 12827443.3694 | 11564943.3694 |  |  |  | 1262500 | 2023-11-30 | 2023-11-15 | 2023-12-03 | 28 | 2023-12-31 | 2024-02-11 | 48543093.98 |  |  |  |  | 2427154.7 | 2427154.7 | 66804 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication16 | MDF Factory16
MDF Factory - Local Fabrication | 1 | 17 | -0.001 | 13012853.94 | 13012853.941 | 0 | 13738045.4627 | 13738045.4627 |  |  |  | 0.0001 | 2023-12-31 | 2023-12-25 | 2023-12-25 | 28 | 2024-01-22 | 2024-04-22 | 48543093.98 |  |  |  |  | 2427154.7 | 2427154.7 | 112541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication17 | MDF Factory17
MDF Factory - Local Fabrication | 1 | 18 | 4414101.95 | 8557464.69 | 4143362.74 | 4265111 | 8046794.6243 | 3781683.6243 |  |  |  | 4458904.86 | 2024-01-31 | 2024-01-15 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-22 | 52957195.93 |  |  |  |  | 2647859.795 | 2647859.795 | 112541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication18 | MDF Factory18
MDF Factory - Local Fabrication | 1 | 19 | 4220898.94 | 18177972.44 | 13957073.5 | 3358613 | 13406399.725 | 10047786.725 |  |  |  | 4456901.8 | 2024-02-29 | 2024-03-15 | 2024-03-20 | 28 | 2024-04-17 | 2024-04-04 | 57178094.87 |  |  |  |  | 2858904.5 | 2858904.5 | 882541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication19 | MDF Factory19
MDF Factory - Local Fabrication | 1 | 20 | 1196029.38 | 12424707.76 | 11228678.38 | 0 | 3607979.0847 | 3607979.0847 |  |  |  | 2286278.72 | 2024-05-31 | 2024-05-15 | 2024-07-03 | 28 | 2024-07-31 | 2024-07-29 | 58374124.25 |  |  |  |  | 2918706 | 2918706 | 66804 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication20 | MDF Factory20
#N/A
Mechanical Installation | 1 | 1 | 96641266.36 | 4758315.53 | -91882950.83 | 15000000 | 3615843.9682 | -11384156.0318 | 15000000 |  |  | 2845427.8 | 2024-01-31 | 2024-01-31 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 96641266.36 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Mechanical Installations |  |  |  | Mechanical Installation1 | EGAT Mechanical Installations1
Mechanical Installation | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-31 | 2024-06-01 | 42 | 2024-07-13 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Mechanical Installations |  |  |  | Mechanical Installation9 | EGAT Mechanical Installations9
Mintra | 1 | 1 | 26487256.44 | 0 | -26487256.44 | 15500000 | 0 | -15500000 | 10000000 |  |  | 2860852.09 | 2018-05-31 | 2018-05-29 | 2018-07-09 | 15 | 2018-07-24 | 2018-09-18 | 26487256.44 | 0 | [5 empty] | 17226261.898 | 26487256.44 | 26487256.44 | 2860852.09 | 0 |  |  |  | Mintra1 | 01
Mintra | 1 | 2 | 16295714.9 | 0 | -16295714.9 | 3000000 | 0 | -3000000 |  |  |  | 1791407.73 | 2018-07-31 | 2018-07-21 | 2018-07-25 | 15 | 2018-08-09 | 2018-09-23 | 42782971.34 | 3426213 | [5 empty] | 31002926.91 | 16295714.9 | 42782971.34 | 1791407.73 | 0 |  |  |  | Mintra2 | 02
Mintra | 1 | 3 | 19469085.79 | 0 | -19469085.79 | 2220782.14 | 0 | -2220782.14 |  |  |  | 2220782.14 | 2018-08-31 | 2018-09-15 | 2018-09-23 | 15 | 2018-10-08 | 2018-10-15 | 62252057.13 | 0 | [5 empty] | 41220014.7 | 19469085.79 | 62252057.13 | 2220782.14 | 0 |  |  |  | Mintra3 | 03
Mintra | 1 | 4 | 9723925.4204 | 0 | -9723925.4204 | 3500000 | 0 | -3500000 |  |  |  | 2907075.5801 | 2018-09-30 | 2018-10-10 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-18 | 71975982.5504 | [6 empty] | 47988244.922 | 9723925.4204 | 71975982.5504 | 2907075.5801 | 0 |  |  |  | Mintra4 | 04
Mintra | 1 | 5 |  | 0 | 0 | 8000000 | 0 | -8000000 |  |  |  |  | 2018-11-30 | 2018-12-10 | 2018-12-18 | 15 | 2019-01-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mintra5 | 05
Mintra | 1 | 6 |  | 0 | 0 | 6000000 | 0 | -6000000 |  |  |  |  | 2019-03-31 | 2019-03-28 | 2019-04-15 | 15 | 2019-04-30 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mintra6 | 06
Mintra | 1 | 7 |  | 0 | 0 | 2005948.91 | 0 | -2005948.91 |  |  |  |  | 2019-09-30 | 2019-11-17 | 2021-02-03 | 15 | 2021-02-18 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | Mintra7 | 07
Mintra-Hanger 1200m2 | 1 | 1 | 1411985.3421 | 0 | -1411985.3421 | 531998.67 | 0 | -531998.67 |  |  |  | 531998.6721 | 2018-10-31 | 2018-10-18 | 2018-10-21 | 15 | 2018-11-05 | 2018-10-29 | 1411985.3421 | [6 empty] | 879986.67 | 1411985.3421 | 1411985.3421 | 531998.6721 | 0 |  |  |  | Mintra-Hanger 1200m21 | 01
Mintra-Hanger 1200m2 | 1 | 2 |  | 0 | 0 | -6217.18 | 0 | 6217.18 |  |  |  |  | 2019-09-30 | 2019-09-30 | 2021-02-03 | 15 | 2021-02-18 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mintra-Hanger 1200m22 | 02
#N/A
Mivida-PK#140 | 1 | 1 | 4797449.5194 | 4797449.52 | 0.0006 | 18101272.3255 | 2533668.016 | -15567604.3095 | 15567604.3 |  |  | 2533668.0255 | 2019-05-31 | 2019-05-31 | 2019-06-10 | 40 | 2019-07-20 | 2019-06-27 | 4797449.5194 | 0 | [5 empty] | 45335.898 | 4797449.5194 | 4797449.5194 | 2533668.0255 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1401 | EMAAR- Pkg 140-ITP-Mivida1
Mivida-PK#140 | 1 | 2 | 4911239.0806 | 4911239.08 | -0.0006 | 9934857.73 | 2620895.13 | -7313962.6 | 7313962.6 |  |  | 2620895.13 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 40 | 2019-08-13 | 2019-07-21 | 9708688.6 | [6 empty] | 91747.11 | 4911239.0806 | 9708688.6 | 2620895.13 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1402 | EMAAR- Pkg 140-ITP-Mivida2
Mivida-PK#140 | 1 | 3 | 6244069.8629 | 6247225.23 | 3155.3671 | 4070832.3885 | 4070832.4 | 0.011547 |  |  |  | 4070832.3885 | 2019-07-31 | 2019-07-31 | 2019-08-04 | 40 | 2019-09-13 | 2019-08-20 | 15952758.4629 | 207615.6315 | [5 empty] | 152651.9264 | 6244069.8629 | 15952758.4629 | 4070832.3885 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1403 | EMAAR- Pkg 140-ITP-Mivida3
Mivida-PK#140 | 1 | 4 | 2442385.7689 | 2442385.78 | 0.011145 | 999645.4398 | 999645.44 | 0.00017344 |  |  |  | 999645.4398 | 2019-08-31 | 2019-08-31 | 2019-09-01 | 40 | 2019-10-11 | 2019-09-17 | 18395144.2317 | 207615.6315 | [5 empty] | 175732.4719 | 2442385.7689 | 18395144.2317 | 999645.4398 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1404 | EMAAR- Pkg 140-ITP-Mivida4
Mivida-PK#140 | 1 | 5 | 1994559.8383 | 1994559.84 | 0.0017124 | 1337507.07 | 1337507.07 | 0 |  |  |  | 1337507.07 | 2019-09-30 | 2019-09-30 | 2019-10-02 | 40 | 2019-11-11 | 2019-10-23 | 20389704.07 | 207615.63 | [5 empty] | 194581.06 | 1994559.8383 | 20389704.07 | 1337507.07 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1405 | EMAAR- Pkg 140-ITP-Mivida5
Mivida-PK#140 | 1 | 6 | 12232780.54 | 0 | -12232780.54 | 10719905.22 | 0 | -10719905.22 |  |  |  | 10719905.2391 | 2019-10-31 | 2019-11-06 | 2019-11-06 | 40 | 2019-12-16 | 2019-12-10 | 32622484.61 | 1084016.3529 | [5 empty] | 318038.6268 | 12232780.5437 | 32622484.6137 | 10719905.2391 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1406 | EMAAR- Pkg 140-ITP-Mivida6
Mivida-PK#140 | 1 | 7 | 7170532.1164 | 12232780.52 | 5062248.4036 | 6547225.82 | 10719905.22 | 4172679.4 |  |  |  | 6547225.8223 | 2019-11-30 | 2019-12-05 | 2019-12-05 | 40 | 2020-01-14 | 2019-12-19 | 39793016.7264 | 1960077.2048 | [5 empty] | 414859.7029 | 7170532.1164 | 39793016.7264 | 6547225.8223 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1407 | EMAAR- Pkg 140-ITP-Mivida7
Mivida-PK#140 | 1 | 8 | 6113446.7536 | 6113446.74 | -0.013553 | 4740517.5525 | 5253107.1475 | 512589.595 |  |  |  | 4740517.5525 | 2019-12-31 | 2020-01-06 | 2020-01-06 | 40 | 2020-02-15 | 2020-02-13 | 45906463.48 | 1612694.6715 | [5 empty] | 473905.3319 | 6113446.7507 | 45906463.4771 | 4740517.5525 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1408 | EMAAR- Pkg 140-ITP-Mivida8
Mivida-PK#140 | 1 | 9 | 4233335.7568 | 4233335.77 | 0.013195 | 4559999.09 | 6237430.1585 | 1677431.0685 |  |  |  | 4559999.0726 | 2020-01-31 | 2020-02-05 | 2020-02-06 | 40 | 2020-03-17 | 2020-03-18 | 50139799.2368 | 3026730.6056 | [5 empty] | 545336.6782 | 4233335.7568 | 50139799.2368 | 4559999.0726 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1409 | EMAAR- Pkg 140-ITP-Mivida9
Mivida-PK#140 | 1 | 10 | 6612227.7834 | 6612227.79 | 0.0065658 | 5679423.0614 | 5679423.0695 | 0.0081432 |  |  |  | 5679423.0614 | 2020-02-29 | 2020-03-05 | 2020-03-05 | 40 | 2020-04-14 | 2020-04-29 | 56752027.0202 | 3351448.8206 | [5 empty] | 610744.6947 | 6612227.7834 | 56752027.0202 | 5679423.0614 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14010 | EMAAR- Pkg 140-ITP-Mivida10
Mivida-PK#140 | 1 | 11 | 3124627.5928 | 3121472.23 | -3155.3628 | 2647674.17 | 2644790.7215 | -2883.4485 |  |  |  | 2647674.1799 | 2020-03-31 | 2020-04-02 | 2020-04-02 | 40 | 2020-05-12 | 2020-04-29 | 59876654.613 | 3468836.925 | [5 empty] | 649303.9184 | 3124627.5928 | 59876654.613 | 2647674.1799 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14011 | EMAAR- Pkg 140-ITP-Mivida11
Mivida-PK#140 | 1 | 12 | 1875813.048 | 1875812.84 | -0.20801 | 4687303.44 | 4687303.232 | -0.208 |  |  |  | 4687303.4253 | 2020-04-30 | 2020-05-02 | 2020-05-03 | 40 | 2020-06-12 | 2020-05-21 | 61752467.661 | 7497245.0417 | [5 empty] | 703286.0248 | 1875813.048 | 61752467.661 | 4687303.4253 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14012 | EMAAR- Pkg 140-ITP-Mivida12
Mivida-PK#140 | 1 | 13 | 1425866.309 | 1425866.3 | -0.008997 | 1169770.65 | 1169767.915 | -2.735 |  |  |  | 1169770.65 | 2020-05-31 | 2020-06-01 | 2020-06-01 | 40 | 2020-07-11 | 2020-06-21 | 63178333.97 | 7496958.47 | [5 empty] | 52250 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14013 | EMAAR- Pkg 140-ITP-Mivida13
Mivida-PK#140 | 1 | 14 | 2429362.3736 | 2429362.37 | -0.0035546 | 7336701.1 | 7336701.0985 | -0.0015 |  |  |  | 7336701.0997 | 2020-06-30 | 2020-07-01 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-21 | 65607696.3436 | 14334387.2636 | [5 empty] | 52250 | 2429362.3736 | 65607696.3436 | 7336701.0997 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14014 | EMAAR- Pkg 140-ITP-Mivida14
Mivida-PK#140 | 1 | 15 | 16266667.6714 | 16266667.66 | -0.011359 | 10305723.52 | 10902262.273 | 596538.753 |  |  |  | 10305723.5244 | 2020-07-31 | 2020-07-28 | 2020-08-06 | 40 | 2020-09-15 | 2020-08-24 | 81874364.0149 | 10470685.8866 | [5 empty] | 74750 | 16266667.6714 | 81874364.0149 | 10305723.5244 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14015 | EMAAR- Pkg 140-ITP-Mivida15
Mivida-PK#140 | 1 | 16 | 19380294.5984 | 19380294.6 | 0.0016493 | 10553431.24 | 13266917.76 | 2713486.52 |  |  |  | 10553431.2394 | 2020-08-31 | 2020-09-01 | 2020-09-01 | 40 | 2020-10-11 | 2020-09-15 | 101254658.6133 | 3625858.6756 | [5 empty] | 74750 | 19380294.5984 | 101254658.6133 | 10553431.2394 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14016 | EMAAR- Pkg 140-ITP-Mivida16
Mivida-PK#140 | 1 | 17 | 16610857.3328 | 16610857.34 | 0.0072358 | 11726998.43 | 11726998.4315 | 0.0015 |  |  |  | 11726998.4266 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 40 | 2020-11-13 | 2020-10-19 | 117865515.946 | 808207.3196 | [5 empty] | 74750 | 16610857.3328 | 117865515.946 | 11726998.4266 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14017 | EMAAR- Pkg 140-ITP-Mivida17
Mivida-PK#140 | 1 | 18 | 4603925.7609 | 4603925.77 | 0.0090585 | 3831058.93 | 3831058.9285 | -0.0015 |  |  |  | 3831058.93 | 2020-10-31 | 2020-11-04 | 2020-11-09 | 40 | 2020-12-19 | 2020-11-29 | 122469441.707 | 876421.358 | [5 empty] | 74750 | 4603925.7609 | 122469441.707 | 3831058.93 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14018 | EMAAR- Pkg 140-ITP-Mivida18
Mivida-PK#140 | 1 | 19 | 11459315.8636 | 11459315.86 | -0.0036022 | 8885358.62 | 8885358.623 | 0.003 |  |  |  | 8885358.6191 | 2020-11-30 | 2020-12-03 | 2020-12-06 | 40 | 2021-01-15 | 2020-12-21 | 133928757.5706 | 214106.8575 | [5 empty] | 74750 | 11459315.8636 | 133928757.5706 | 8885358.6191 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14019 | EMAAR- Pkg 140-ITP-Mivida19
Mivida-PK#140 | 1 | 20 | 5957491.0722 | 5957491.28 | 0.20777 | 5084359.83 | 6060664.08 | 976304.25 |  |  |  | 5084359.8248 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-04 | 139886248.6428 | 17194.8 | [5 empty] | 85700 | 5957491.0722 | 139886248.6428 | 5084359.8248 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14020 | EMAAR- Pkg 140-ITP-Mivida20
Mivida-PK#140 | 1 | 21 | 9991628.9772 | 9991628.97 | -0.0071991 | 8185193.83 | 8185193.8285 | -0.0015 |  |  |  | 8185193.8344 | 2021-01-31 | 2021-02-04 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-18 | 149877877.62 | [6 empty] | 85700 | 9991628.9775 | 149877877.6203 | 8185193.8344 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14021 | EMAAR- Pkg 140-ITP-Mivida21
Mivida-PK#140 | 1 | 22 | 5467007.07 | 5467007.05 | -0.02 | 4603109.14 | 4603109.1525 | 0.0125 |  |  |  | 4603109.16 | 2021-02-28 | 2021-03-04 | 2021-03-15 | 40 | 2021-04-24 | 2021-04-01 | 155344884.69 | [6 empty] | 85700 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14022 | EMAAR- Pkg 140-ITP-Mivida22
Mivida-PK#140 | 1 | 23 | 4716911.44 | 4716911.47 | 0.03 | 3870461.7 | 3870461.7235 | 0.0235 |  |  |  | 3870461.69 | 2021-03-31 | 2021-04-04 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-26 | 160061796.13 | [6 empty] | 85700 | 1777689.2863 | 157122573.9763 | 1458682.9494 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14023 | EMAAR- Pkg 140-ITP-Mivida23
Mivida-PK#140 | 1 | 24 | 4573435.8657 | 4573435.86 | -0.0057481 | 3732732.7981 | 4604153.83 | 871421.0319 |  |  |  | 3732732.7981 | 2021-05-31 | 2021-06-04 | 2021-06-30 | 40 | 2021-08-09 | 2021-07-15 | 164635231.9957 | [6 empty] | 105700 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14024 | EMAAR- Pkg 140-ITP-Mivida24
Mivida-PK#140 | 1 | 25 | 5220299.9543 | 5220299.96 | 0.0057481 | 9016182.24 | 9290247.798 | 274065.558 |  |  |  | 9016182.24 | 2021-06-30 | 2021-06-29 | 2021-08-18 | 40 | 2021-09-27 | 2021-08-31 | 169855531.95 | [6 empty] | 623487.51 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14025 | EMAAR- Pkg 140-ITP-Mivida25
Mivida-PK#140 | 1 | 26 | 3380977.62 | 3380977.62 | -4.6566e-09 | 3143991.8 | 3321493.111 | 177501.311 |  |  |  | 3143991.79 | 2021-10-31 | 2021-10-31 | 2021-11-02 | 40 | 2021-12-12 | 2021-11-21 | 173236509.57 | [6 empty] | 623487.51 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14026 | EMAAR- Pkg 140-ITP-Mivida26
Mivida-PK#140 | 1 | 27 | 825139.1896 | 825139.18 | -0.0095798 | 5157960.04 | 6499741.709 | 1341781.669 |  |  |  | 5157960.0562 | 2022-01-31 | 2022-01-15 | 2022-01-25 | 40 | 2022-03-06 | 2022-03-01 | 174061648.7596 |  |  |  |  | 4569118.28 | 4569118.28 | 0 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14027 | EMAAR- Pkg 140-ITP-Mivida27
Mivida-PK#140 | 1 | 28 | 924592.0104 | 0 | -924592.0104 | 0 | 0 | 0 |  |  |  | 1576397.44 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 40 | 2023-07-18 | 2024-07-09 | 174986240.77 |  |  |  |  | 4593388.82 | 4593388.82 | 909436.51 | 924591.9704 | 174986240.73 | 1577397.44 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14028 | EMAAR- Pkg 140-ITP-Mivida28
Mivida-PK#189 | 1 | 1 | 15323108.5333 | 0 | -15323108.5333 | 117695262.89 | 0 | -117695262.89 | 99600000 |  |  | 18095262.89 | 2022-05-31 | 2022-05-25 | 2022-05-26 | 40 | 2022-07-05 | 2022-06-16 | 15323108.5333 | 5493727.64 |  |  |  | 559686.37 | 559686.37 | 100000 | 15323108.5333 | 15323108.5333 | 18095262.89 | Mivida BP#189 |  |  |  | Mivida-PK#1891 | Mivida BP#1891
Mivida-PK#189 | 1 | 2 | 28497042.4952 | 16089263.96 | -12407778.5352 | 22529255.88 | 19214635.628 | -3314620.252 |  |  |  | 22529255.8764 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-06 | 43820151.0286 | 5215901.19 |  |  | 1210923 | 1280676.495 | 1280676.495 | 108208.75 | 28497042.4952 | 43820151.0286 | 22529255.8764 | Mivida BP#189 |  |  |  | Mivida-PK#1892 | Mivida BP#1892
Mivida-PK#189 | 1 | 3 | 24279069.6762 | 27730887.07 | 3451817.3938 | 19800407.88 | 23971236.1335 | 4170828.2535 |  |  |  | 19800407.88 | 2022-07-31 | 2022-08-06 | 2022-08-06 | 40 | 2022-09-15 | 2022-09-04 | 68099220.7048 | 5069769.75 |  |  | 4205865.52 | 1914348.785 | 1914348.785 | 115793.25 | 24279069.6762 | 68099220.7048 | 19800407.88 | Mivida BP#189 |  |  |  | Mivida-PK#1893 | Mivida BP#1893
Mivida-PK#189 | 1 | 4 | 28546026.8476 | 24279069.68 | -4266957.1676 | 27644756.83 | 21067752.4505 | -6577004.3795 |  |  |  | 27644756.83 | 2022-08-31 | 2022-09-05 | 2022-09-06 | 40 | 2022-10-16 | 2022-10-09 | 96645247.5524 | 10542311 |  |  | 4205865.52 | 2800495.535 | 2800495.535 | 171139 | 28546026.8476 | 96645247.5524 | 27644756.83 | Mivida BP#189 |  |  |  | Mivida-PK#1894 | Mivida BP#1894
Mivida-PK#189 | 1 | 5 | 57245166.7876 | 28546026.85 | -28699139.9376 | 46638711.45 | 29417050.3325 | -17221661.1175 |  |  |  | 46638711.45 | 2022-09-30 | 2022-10-12 | 2022-10-12 | 40 | 2022-11-21 | 2022-11-05 | 153890414.34 | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759 | 57245166.7876 | 153890414.34 | 46638711.45 | Mivida BP#189 |  |  |  | Mivida-PK#1895 | Mivida BP#1895
Mivida-PK#189 | 1 | 6 | -0.0001 | 57254690.6 | 57254690.6001 | 70000000 | 49630186.51 | -20369813.49 |  |  |  | 70000000 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | 153890414.34 | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759 | -0.0001 | 153890414.34 | 70000000 | Mivida BP#189 |  |  |  | Mivida-PK#1896 | Mivida BP#1896
Mivida-PK#189 | 1 | 7 | 39773865.3076 | 49447555.48 | 9673690.1724 | 38664242.89 | 41131640.064 | 2467397.174 |  |  |  | 38664242.9 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | 193664279.6476 | 7682397 |  |  | 14543436.55 | 5529931.65 | 5529931.65 | 187759 | 39773865.3076 | 193664279.6476 | 38664242.9 | Mivida BP#189 |  |  |  | Mivida-PK#1897 | Mivida BP#1897
Mivida-PK#189 | 1 | 8 | 90047890.8024 | 80364676.81 | -9683213.9924 | 62566272.8 | 66596247.2075 | 4029974.4075 |  |  |  | 62566272.81 | 2022-11-30 | 2022-12-12 | 2022-12-14 | 40 | 2023-01-23 | 2023-01-01 | 283712170.45 | 3898975.5 |  |  | 19923003.68 | 7544918.86 | 7544918.86 | 608067.35 | 90047890.8024 | 283712170.45 | 62566272.81 | Mivida BP#189 |  |  |  | Mivida-PK#1898 | Mivida BP#1898
Mivida-PK#189 | 1 | 9 | 42271935.09 | 42271935.1 | 0.01 | 37089198 | 39465389.045 | 2376191.045 |  |  |  | 37089197.56 | 2022-12-31 | 2023-01-05 | 2023-01-09 | 40 | 2023-02-18 | 2023-01-24 | 325984105.54 | 7037273.25 |  |  | 24970230.92 | 8733014.6 | 8733014.6 | 657611 | 42271935.09 | 325984105.54 | 37089197.56 | Mivida BP#189 |  |  |  | Mivida-PK#1899 | Mivida BP#1899
Mivida-PK#189 | 1 | 10 | 29038558.46 | 29038558.46 | 0 | 22123110.41 | 23647399.753 | 1524289.343 |  |  |  | 22123110.41 | 2023-01-31 | 2023-02-01 | 2023-02-01 | 40 | 2023-03-13 | 2023-02-26 | 355022664 | 7032573.83 |  | 285000 | 27238935.45 | 9495159.275 | 9495159.275 | 573417.35 | 29038558.46 | 355022664 | 22123110.41 | Mivida BP#189 |  |  |  | Mivida-PK#18910 | Mivida BP#18910
Mivida-PK#189 | 1 | 11 | 23000800.56 | 23000800.56 | 0 | 18794302.39 | 19983996.088 | 1189693.698 |  |  |  | 18794302.38 | 2023-02-28 | 2023-03-01 | 2023-03-08 | 40 | 2023-04-17 | 2023-04-10 | 378023464.56 | 6675607.4 |  | 55000 | 34635720.71 | 10090006.13 | 10090006.13 | 603461 | 23000800.56 | 378023464.56 | 18794302.38 | Mivida BP#189 |  |  |  | Mivida-PK#18911 | Mivida BP#18911
Mivida-PK#189 | 1 | 12 | 15682494.86 | 15682494.86 | 5.0291e-08 | 16890748.06 | 17976827.49 | 1086079.43 |  |  |  | 16890748.07 | 2023-03-31 | 2023-04-01 | 2023-04-09 | 40 | 2023-05-19 | 2023-05-08 | 393705959.42 | 11930576.4 |  | 90000 | 36499853.4 | 10633045.845 | 10633045.845 | 652617.35 | 15682494.86 | 393705959.42 | 16890748.07 | Mivida BP#189 |  |  |  | Mivida-PK#18912 | Mivida BP#18912
Mivida-PK#189 | 1 | 13 | 16636045.76 | 16636045.76 | -5.0291e-08 | 50032149.11 | 53623446.998 | 3591297.888 |  |  |  | 50032149.1 | 2023-04-30 | 2023-05-05 | 2023-05-09 | 40 | 2023-06-18 | 2023-06-06 | 410342005.18 | 58593047.95 | 1714555.5 | 140000 | 38456764.67 | 12236303.835 | 12236303.835 | 686786.1 | 16636045.76 | 410342005.18 | 50032149.1 | Mivida BP#189 |  |  |  | Mivida-PK#18913 | Mivida BP#18913
Mivida-PK#189 | 1 | 14 | 22729528.92 | 22729528.92 | 0 | 22045664.4 | 23637153.386 | 1591488.986 |  |  |  | 22045664.4 | 2023-05-31 | 2023-06-05 | 2023-06-05 | 40 | 2023-07-15 | 2023-07-15 | 433071534.1 | 63146488.9 | 3995594.72 | 240000 | 42393533.94 | 12946789.995 | 12946789.995 | 750242.35 | 22729528.92 | 433071534.1 | 22045664.4 | Mivida BP#189 |  |  |  | Mivida-PK#18914 | Mivida BP#18914
Mivida-PK#189 | 1 | 15 | 18379426.49 | 18379426.48 | -0.0099999 | 20013901.02 | 20013901.014 | -0.006 |  |  |  | 20013901.03 | 2023-06-30 | 2023-07-13 | 2023-07-18 | 40 | 2023-08-27 | 2023-08-07 | 451450960.59 | 71534780.44 | 7645358.03 | 330000 | 45605336.83 | 13638957.225 | 13638957.225 | 782829.85 | 18379426.49 | 451450960.59 | 20013901.03 | Mivida BP#189 |  |  |  | Mivida-PK#18915 | Mivida BP#18915
Mivida-PK#189 | 1 | 16 | 24459783.7762 | 24459783.78 | 0.003758 | 22512171.88 | 22512171.879 | -0.001 |  |  |  | 22512171.8728 | 2023-07-31 | 2023-08-15 | 2023-08-17 | 40 | 2023-09-26 | 2023-09-20 | 475910744.3662 | 78434225.1876 | 8773118.9707 | 230000 | 50069955.0917 | 14453512.665 | 14453512.665 | 832885.35 | 24459783.7762 | 475910744.3662 | 22512171.8728 | Mivida BP#189 |  |  |  | Mivida-PK#18916 | Mivida BP#18916
Mivida-PK#189 | 1 | 17 | 30434807.7338 | 30434807.73 | -0.003758 | 47104890.0563 | 47104890.0565 | 0.00022 |  |  |  | 47104890.06 | 2023-09-30 | 2023-09-25 | 2023-09-27 | 40 | 2023-11-06 | 2023-10-17 | 506345552.1 | 73723080.15 | 9982715.55 | 390000 | 53354142.27 | 15134647.745 | 15134647.745 | 859629.1 | 30434807.7338 | 506345552.1 | 47104890.06 | Mivida BP#189 |  |  |  | Mivida-PK#18917 | Mivida BP#18917
Mivida-PK#189 | 1 | 18 | 18563752.6 | 37127505.2 | 18563752.6 | 20024965.62 | 20024965.62 | 0 |  |  |  | 20024965.62 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 40 | 2023-12-10 | 2023-12-02 | 524909304.7 | 79805243.6 | 11738051.38 | 340000 | 54783582.6 | 15774000.34 | 15774000.34 | 870216.6 | 18563752.6 | 524909304.7 | 20024965.62 | Mivida BP#189 |  |  |  | Mivida-PK#18918 | Mivida BP#18918
Mivida-PK#189 | 1 | 19 | 21710553.3095 | 21710553.31 | 0.0004763 | 23323710.11 | 23323710.1055 | -0.0045 |  |  |  | 23323710.1 | 2023-11-30 | 2023-11-25 | 2023-12-02 | 40 | 2024-01-11 | 2024-01-02 | 546619858.0095 | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1 | 21710553.3095 | 546619858.0095 | 23323710.1 | Mivida BP#189 |  |  |  | Mivida-PK#18919 | Mivida BP#18919
Mivida-PK#189 | 1 | 20 | -0.0003 | 0 | 0.0003 | 135145955 | 0 | -135145955 |  | 135145955 |  |  | 2023-11-30 | 2023-11-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-11 | 546619858.0095 | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1 | -0.0003 | 546619858.0095 | 0 | Mivida BP#189 |  |  |  | Mivida-PK#18920 | Mivida BP#18920
Mivida-PK#189 | 1 | 21 | 22586754.7048 | 22586754.17 | -0.53476 | 14476604.63 | 14476604.0585 | -0.5715 |  |  |  | 14476604.63 | 2023-12-31 | 2023-12-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-24 | 569206612.7143 | 81314246.26 | 16546391.27 | 130000 | 59318989.42 | 16974529.74 | 16974529.74 | 807307.6 | 22586754.7048 | 569206612.7143 | 14476604.63 | Mivida BP#189 |  |  |  | Mivida-PK#18921 | Mivida BP#18921
Mivida-PK#189 | 1 | 22 | 23140993.5357 | 23140993.33 | -0.20571 | 17552608.99 | 17552608.8365 | -0.1535 |  |  |  | 17552609 | 2024-01-31 | 2024-01-30 | 2024-02-04 | 40 | 2024-03-15 | 2024-02-27 | 592347606.25 | 88194427.7 | 17630743.31 | 130000 | 61582414.39 | 17753985.355 | 17753985.355 | 900122.85 | 23140993.5357 | 592347606.25 | 17552609 | Mivida BP#189 |  |  |  | Mivida-PK#18922 | Mivida BP#18922
Mivida-PK#189 | 1 | 23 | 30858954.27 | 30858954.29 | 0.02 | 14242173.09 | 14242173.0845 | -0.0055 |  |  |  | 14242173.08 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 40 | 2024-04-15 | 2024-04-21 | 623206560.52 | 84128553.28 | 31879195.04 | 260000 | 64992287.15 | 18462386.045 | 18462386.045 | 912222.85 | 30858954.27 | 623206560.52 | 14242173.08 | Mivida BP#189 |  |  |  | Mivida-PK#18923 | Mivida BP#18923
Mivida-PK#189 | 1 | 24 | 16112816.1181 | 16112816.1 | -0.018095 | 13803484.92 | 13803484.915 | -0.005 |  |  |  | 13803484.93 | 2024-03-31 | 2024-03-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-05-22 | 639319376.6381 | 96423729.78 | 32655160.1 | 130000 | 66746916.67 | 19192726.88 | 19192726.88 | 1304406.85 | 16112816.1181 | 639319376.6381 | 13803484.93 | Mivida BP#189 |  |  |  | Mivida-PK#18924 | Mivida BP#18924
Mivida-PK#189 | 1 | 25 | 29437278.3119 | 29437278.32 | 0.0080952 | 28360739.45 | 28360739.446 | -0.004 |  |  |  | 28360739.45 | 2024-04-30 | 2024-04-30 | 2024-05-09 | 40 | 2024-06-18 | 2024-06-06 | 668756654.95 | 101680151.25 | 44526060.5 | 30000 | 69988148.31 | 20096865.975 | 20096865.975 | 1306194.35 | 29437278.3119 | 668756654.95 | 28360739.45 | Mivida BP#189 |  |  |  | Mivida-PK#18925 | Mivida BP#18925
Mivida-PK#189 | 1 | 26 | 16876594.42 | 16876594.44 | 0.02 | 14177811.26 | 14177811.26 | 0 |  |  |  | 14177811.24 | 2024-05-31 | 2024-05-30 | 2024-06-01 | 40 | 2024-07-11 | 2024-07-03 | 685633249.37 | 113839940.35 | 49627280.83 | 230000 | 71860776.18 | 20843871.305 | 20843871.305 | 1314994.35 | 16876594.42 | 685633249.37 | 14177811.24 | Mivida BP#189 |  |  |  | Mivida-PK#18926 | Mivida BP#18926
Mivida-PK#189 | 1 | 27 | 14919836.13 | 14919836.12 | -0.01 | 4389859.04 | 4389859.036 | -0.004 |  |  |  | 4389859.04 | 2024-06-30 | 2024-06-30 | 2024-07-01 | 40 | 2024-08-10 | 2024-08-01 | 700553085.5 | 115715406.16 | 55352768.73 | 130000 | 73509397.76 | 21282403.65 | 21282403.65 | 5470850.6 | 14919836.13 | 700553085.5 | 4389859.04 | Mivida BP#189 |  |  |  | Mivida-PK#18927 | Mivida BP#18927
Mivida-PK#189 | 1 | 28 | 3487392.66 | 3487392.64 | -0.02 | 2409288.21 | 2409288.192 | -0.018 |  |  |  | 2409288.21 | 2024-07-31 | 2024-07-30 | 2024-08-01 | 40 | 2024-09-10 | 2024-08-31 | 704040478.16 | 115148780.66 | 49698695.44 | 130000 | 73901796.57 | 21359782.07 | 21359782.07 | 5480338.1 | 3487392.66 | 704040478.16 | 2409288.21 | Mivida BP#189 |  |  |  | Mivida-PK#18928 | Mivida BP#18928
Mivida-PK#189 | 1 | 29 | 369049.79 | 369049.79 | 3.8068e-08 | 2690517.47 | 2690517.4595 | -0.0105 |  |  |  | 2690517.47 | 2024-08-31 | 2024-08-31 | 2024-09-18 | 40 | 2024-10-28 | 2024-09-26 | 704409527.95 | 118334746.14 | 36219473.08 | 230000 | 73927905.13 | 21449118.76 | 21449118.76 | 5482400 | 369049.79 | 704409527.95 | 2690517.47 | Mivida BP#189 |  |  |  | Mivida-PK#18929 | Mivida BP#18929
Mivida-PK#189 | 1 | 30 | 17653522.66 | 22415427.41 | 4761904.75 | 14412191.12 | 14412191.1105 | -0.0095 |  |  |  | 14412191.13 | 2024-09-30 | 2024-09-30 | 2024-10-09 | 40 | 2024-11-18 | 2024-11-12 | 722063050.61 | 118972314.89 | 37380637.32 | 230000 | 80926432.97 | 22053462.95 | 22053462.95 | 9961433.24 | 17653522.66 | 722063050.61 | 14412191.13 | Mivida BP#189 |  |  |  | Mivida-PK#18930 | Mivida BP#18930
Mivida-PK#189 | 1 | 31 |  | 19514716.97 | 19514716.97 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-11-01 | 40 | 2024-12-11 | [8 empty] | 0 | 0 | 0 | 0 | Mivida BP#189 |  |  |  | Mivida-PK#18931 | Mivida BP#18931
Mobilization | 0 | 1 | 3847983.19 | 0 | -3847983.19 | 0 | 0 | 0 |  |  |  | 475188.5 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-02-28 | 3847983.19 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mobilization1 | 01
MOC | 1 | 1 |  | 32863813 | 32863813 | 33350000 | 0 | -33350000 |  |  |  |  | 2024-05-31 | 2024-06-08 | 2024-05-05 | 40 | 2024-06-14 | [8 empty] | 0 | 0 | 0 | 0 | MOC HQ at Diriyah |  |  |  | MOC1 | MOC HQ at Diriyah1
MOC | 1 | 2 |  | 2521761.64 | 2521761.64 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-07-15 | 2024-07-15 | 40 | 2024-08-24 | [8 empty] | 0 | 0 | 0 | 0 | MOC HQ at Diriyah |  |  |  | MOC2 | MOC HQ at Diriyah2
MOC - DP | 1 | 1 |  | 32863813 | 32863813 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-01 | 2024-04-01 | 40 | 2024-05-11 | [8 empty] | 0 | 0 | 0 | 0 | MOC HQ at Diriyah |  |  |  | MOC - DP1 | MOC HQ at Diriyah1
New Gas Station | 1 | 1 | 3190160 | 34312846.59 | 31122686.59 | 2201210.4 | 24876813.7695 | 22675603.3695 |  |  |  | 2360718.4 | 2023-10-31 | 2023-10-31 | 2023-11-02 | 42 | 2023-12-14 | 2023-11-02 | 3190160 | [6 empty] | 0 | 3190160 | 3190160 | 2360718.4 | New Giza Teaching Hospital |  |  |  | New Gas Station1 | New Giza Teaching Hospital1
New Gas Station | 1 | 2 |  | 20687718.13 | 20687718.13 | 1419355.25 | 14998595.6465 | 13579240.3965 |  |  |  |  | 2023-12-31 | 2023-12-31 | 2024-01-01 | 42 | 2024-02-12 | [8 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Gas Station2 | New Giza Teaching Hospital2
New Gas Station | 1 | 3 | 2793703.2 | 7560552.29 | 4766849.09 | 0 | 7466045.3845 | 7466045.3845 |  |  |  | 1433129.44 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 42 | 2024-03-14 | 2024-02-07 | 7183858 | [6 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Gas Station3 | New Giza Teaching Hospital3
New Gas Station | 1 | 4 | 6707619.99 | 36077726.42 | 29370106.43 | 0 | 27335611.781 | 27335611.781 |  |  |  | 4963638.79 | 2024-04-30 | 2024-04-21 | 2024-04-21 | 42 | 2024-06-02 | 2024-04-28 | 13891477.99 | [6 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Gas Station4 | New Giza Teaching Hospital4
#N/A
New Giza Hospital | 1 | 1 | 34312846.6 | 34312846.59 | -0.01 | 111673736 | 24876813.7695 | -86796922.2305 | 73512565 |  |  | 23504299.92 | 2022-01-31 | 2022-01-30 | 2022-02-01 | 51 | 2022-03-24 | 2022-02-14 | 34312846.6 | [6 empty] | 0 | 34312846.6 | 34312846.6 | 23504299.92 | New Giza Teaching Hospital |  |  |  | New Giza Hospital1 | New Giza Teaching Hospital1
New Giza Hospital | 1 | 2 | 20701192.62 | 20687718.13 | -13474.49 | 16948027.1724 | 14998595.6465 | -1949431.5259 |  |  |  | 13966904.63 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 51 | 2022-04-25 | 2022-03-21 | 55014039.22 | [6 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital2 | New Giza Teaching Hospital2
New Giza Hospital | 1 | 3 | -0.0001 | 7560552.29 | 7560552.2901 | 7088017 | 7466045.3845 | 378028.3845 |  |  |  | 7088017.77 | 2022-03-31 | 2022-03-15 | 2022-03-20 | 51 | 2022-05-10 | 2022-03-28 | 55014039.22 |  |  |  |  | 1642229.32 | 1642229.32 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital3 | New Giza Teaching Hospital3
New Giza Hospital | 1 | 4 | 43472048.71 | 36077726.42 | -7394322.29 | 25531752 | 27335611.781 | 1803859.781 |  |  |  | 25608972.36 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 51 | 2022-05-27 | 2022-04-24 | 98486087.93 |  |  |  |  | 2584225.375 | 2584225.375 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital4 | New Giza Teaching Hospital4
New Giza Hospital | 1 | 5 | 15040366.17 | 14819091.38 | -221274.79 | 9692684 | 10433639.459 | 740955.459 |  |  |  | 10219240.4 | 2022-04-30 | 2022-05-10 | 2022-05-10 | 51 | 2022-06-30 | 2022-05-25 | 113526454.1 |  |  |  | 12821619 | 2978829.635 | 2978829.635 | 447088.63 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital5 | New Giza Teaching Hospital5
New Giza Hospital | 1 | 6 | 21219859 | 21174583.68 | -45275.32 | 12645886 | 13704613.324 | 1058727.324 |  |  |  | 14292844 | 2022-05-31 | 2022-05-31 | 2022-06-15 | 51 | 2022-08-05 | 2022-06-21 | 134746313.1 |  |  |  | 12821619 | 3534103.595 | 3534103.595 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital6 | New Giza Teaching Hospital6
New Giza Hospital | 1 | 7 | 20073764.28 | 20034184.42 | -39579.86 | 12694720 | 13696429.151 | 1001709.151 |  |  |  | 13315074.93 | 2022-06-30 | 2022-06-30 | 2022-06-23 | 51 | 2022-08-13 | 2022-07-04 | 154820077.38 |  |  |  | 12821619.84 | 4060000.94 | 4060000.94 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital7 | New Giza Teaching Hospital7
New Giza Hospital | 1 | 8 | 18180164.07 | 18146654.72 | -33509.35 | 11865059 | 12772392.376 | 907333.376 |  |  |  | 12573205.03 | 2022-07-31 | 2022-08-07 | 2022-08-23 | 51 | 2022-10-13 | 2022-08-28 | 173000241.45 |  |  |  | 12821619 | 4536350.625 | 4536350.625 | 2987283.85 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital8 | New Giza Teaching Hospital8
New Giza Hospital | 1 | 9 | 23318711.12 | 23282485.08 | -36226.04 | 15594713 | 16758838.084 | 1164125.084 |  |  |  | 15620677.42 | 2022-08-31 | 2022-09-11 | 2022-09-14 | 51 | 2022-11-04 | 2022-09-22 | 196318952.57 |  |  |  | 12821619.84 | 5147515.86 | 5147515.86 | 3790429.25 | 23318711.12 | 196318952.57 | 15620677.42 | New Giza Teaching Hospital |  |  |  | New Giza Hospital9 | New Giza Teaching Hospital9
New Giza Hospital | 1 | 10 | 22254898.64 | 22234302.84 | -20595.8 | 14931468 | 16043183.482 | 1111715.482 |  |  |  | 14944068.34 | 2022-09-30 | 2022-10-15 | 2022-10-18 | 51 | 2022-12-08 | 2022-11-03 | 218573851.21 |  |  |  | 12821619.84 | 5731166.305 | 5731166.305 | 3910342.85 | 22254898.64 | 218573851.21 | 14944068.34 | New Giza Teaching Hospital |  |  |  | New Giza Hospital10 | New Giza Teaching Hospital10
New Giza Hospital | 1 | 11 | 29701638.2 | 29644027.2 | -57611 | 19979218 | 21461419.72 | 1482201.72 |  |  |  | 19999087.83 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 51 | 2022-12-31 | 2022-12-07 | 248275489.41 |  | 47447.2 |  | 12821619.84 | 6509322.02 | 6509322.02 | 3819797.85 | 29701638.2 | 248275489.41 | 19999087.83 | New Giza Teaching Hospital |  |  |  | New Giza Hospital11 | New Giza Teaching Hospital11
New Giza Hospital | 1 | 12 | 25988546.64 | 30417445.78 | 4428899.14 | 21023839 | 22544712.249 | 1520873.249 |  |  |  | 21046664.64 | 2022-11-30 | 2022-12-06 | 2022-12-08 | 51 | 2023-01-28 | 2022-12-29 | 274264036.05 | 4878335.3 | 1113844.57 |  | 12821619.84 | 7307779.5 | 7307779.5 | 3966447.85 | 25988546.64 | 274264036.05 | 21046664.64 | New Giza Teaching Hospital |  |  |  | New Giza Hospital12 | New Giza Teaching Hospital12
New Giza Hospital | 1 | 13 | 24670486.27 | 26683802.78 | 2013316.51 | 17903308 | 19237495.901 | 1334187.901 |  |  |  | 18169651.25 | 2022-12-31 | 2023-01-05 | 2023-01-08 | 51 | 2023-02-28 | 2023-02-06 | 298934522.32 | 7074573 | 1237105.25 |  | 12821619.84 | 8008229.795 | 8008229.795 | 3886497.85 | 24670486.27 | 298934522.32 | 18169651.25 | New Giza Teaching Hospital |  |  |  | New Giza Hospital13 | New Giza Teaching Hospital13
New Giza Hospital | 1 | 14 | 21692266.85 | 21572565.8 | -119701.05 | 15197022 | 16275653.05 | 1078631.05 |  |  |  | 14731551.62 | 2023-01-31 | 2023-02-11 | 2023-02-09 | 51 | 2023-04-01 | 2023-03-14 | 320626789.17 | 6879606.09 | 1773014.33 |  | 12821619.84 | 8574509.66 | 8574509.66 | 4107797.85 | 21692266.85 | 320626789.17 | 14731551.62 | New Giza Teaching Hospital |  |  |  | New Giza Hospital14 | New Giza Teaching Hospital14
New Giza Hospital | 1 | 15 | 23725978.81 | 22076508.27 | -1649470.54 | 7535461 | 8639287.3435 | 1103826.3435 |  |  |  | 14839693.08 | 2023-02-28 | 2023-03-14 | 2023-03-16 | 51 | 2023-05-06 | 2023-04-18 | 344352767.98 | 5193267.92 | 2584321.32 |  | 12821619.84 | 9154018.005 | 9154018.005 | 4143497.85 | 23725978.81 | 344352767.98 | 14839693.08 | New Giza Teaching Hospital |  |  |  | New Giza Hospital15 | New Giza Teaching Hospital15
New Giza Hospital | 1 | 16 | 22492246.1 | 22109235.45 | -383010.65 | 7643976 | 8749433.6065 | 1105457.6065 |  |  |  | 15222233.72 | 2023-04-30 | 2023-04-19 | 2023-04-30 | 51 | 2023-06-20 | 2023-05-14 | 366845014.08 | 4834698.32 | 3206608.76 |  | 12821619.84 | 9734385.435 | 9734385.435 | 3938997.85 | 22492246.1 | 366845014.08 | 15222233.72 | New Giza Teaching Hospital |  |  |  | New Giza Hospital16 | New Giza Teaching Hospital16
New Giza Hospital | 1 | 17 | 21612019.52 | 21552600.91 | -59418.61 | 0 | 1077630.05 | 1077630.05 |  |  |  | 12680990.84 | 2023-05-31 | 2023-05-31 | 2023-06-03 | 51 | 2023-07-24 | 2023-07-04 | 388457033.6 | 4817538.46 | 3364840.52 |  | 12821619.84 | 10300141.21 | 10300141.21 | 6117327.71 | 21612019.52 | 388457033.6 | 12680990.84 | New Giza Teaching Hospital |  |  |  | New Giza Hospital17 | New Giza Teaching Hospital17
New Giza Hospital | 1 | 18 | 9332664.78 | 24967998.04 | 15635333.26 | 14511461 | 15759862.1875 | 1248401.1875 |  |  |  | 14934202.65 | 2023-06-30 | 2023-07-09 | 2023-07-12 | 51 | 2023-09-01 | 2023-08-06 | 397789698.38 | 21298296.55 | 3366900.3 |  | 12821619.84 | 10955551.155 | 10955551.155 | 6117327.71 | 9332664.78 | 397789698.38 | 14934202.65 | New Giza Teaching Hospital |  |  |  | New Giza Hospital18 | New Giza Teaching Hospital18
New Giza Hospital | 1 | 19 | 18985757.51 | 8254281.5 | -10731476.01 | 3705542 | 4118256.08 | 412714.08 |  |  |  | 5705542.36 | 2023-08-31 | 2023-08-12 | 2023-08-13 | 51 | 2023-10-03 | 2023-09-14 | 416775455.89 | 10041623.17 | 3890054.47 |  | 12821619.84 | 11172226.045 | 11172226.045 | 6117327.71 | 18985757.51 | 416775455.89 | 5705542.36 | New Giza Teaching Hospital |  |  |  | New Giza Hospital19 | New Giza Teaching Hospital19
New Giza Hospital | 1 | 20 | -1e-07 | 0 | 1e-07 | 18995740 | 0 | -18995740 |  |  |  | 18995740.42 | 2023-09-30 | 2023-09-30 | 2023-09-27 | 51 | 2023-11-17 | 2023-10-03 | 416775455.89 | 10041623.17 | 3890054.47 |  | 12821619.84 | 22344452.09 |  | 6117327.71 | -1e-07 | 416775455.89 | 18995740.42 | New Giza Teaching Hospital |  |  |  | New Giza Hospital20 | New Giza Teaching Hospital20
New Giza Hospital | 1 | 21 | 12758386.3 | 12130160.82 | -628225.48 | 4008305 | 4614812.92 | 606507.92 |  |  |  | 8010369.24 | 2023-09-30 | 2023-09-30 | 2023-10-16 | 51 | 2023-12-06 | 2023-10-16 | 429533842.19 | 9402295.53 | 3259999.96 |  | 12821619 | 22981285.53 |  | 6117327.71 | 12758386.3 | 429533842.19 | 8010369.24 | New Giza Teaching Hospital |  |  |  | New Giza Hospital21 | New Giza Teaching Hospital21
New Giza Hospital | 1 | 22 | 18598623.84 | 12179338.16 | -6419285.68 | 6681249 | 7290216.108 | 608967.108 |  |  |  | 8695249.6 | 2023-10-31 | 2023-11-05 | 2023-11-08 | 51 | 2023-12-29 | 2023-11-30 | 448132466.03 | 2678290.23 | 4983458.07 |  | 12821619.84 | 23620700.79 |  | 6119391.71 | 18598623.84 | 448132466.03 | 8695249.6 | New Giza Teaching Hospital |  |  |  | New Giza Hospital22 | New Giza Teaching Hospital22
New Giza Hospital | 1 | 23 | 9056705.71 | 8466924.1 | -589781.61 | 3104562 | 3527907.892 | 423345.892 |  |  |  | 4604562.68 | 2023-11-30 | 2023-12-10 | 2023-12-12 | 51 | 2024-02-01 | 2024-01-27 | 457189171.74 | 2083276.16 | 4983458.07 |  | 12821619.84 | 24065214.3 |  | 6133391.71 | 9056705.71 | 457189171.74 | 4604562.68 | New Giza Teaching Hospital |  |  |  | New Giza Hospital23 | New Giza Teaching Hospital23
New Giza Hospital | 1 | 24 | 30645299.93 | 29604524.13 | -1040775.8 | 4494905.88 | 4494905.8665 | -0.0135 |  |  |  | 5494905.78 | 2024-01-31 | 2024-02-12 | 2024-02-13 | 51 | 2024-04-04 | 2024-04-01 | 487834471.67 | 1034048.23 | 5018947.83 |  | 12821619.84 | 25619451 |  | 8956130 | 30645299.93 | 487834471.67 | 5494905.78 | New Giza Teaching Hospital |  |  |  | New Giza Hospital24 | New Giza Teaching Hospital24
New Giza Hospital | 1 | 25 | 12955562.12 | 12359506.46 | -596055.66 | 10195246 | 10195246.193 | 0.193 |  |  |  | 10195246.28 | 2024-03-31 | 2024-04-06 | 2024-04-07 | 51 | 2024-05-28 | 2024-01-05 | 500790033.79 | 421352.25 | 12168583.45 |  | 12821619.84 | 26268325.91 |  | 8956130.8 | 12955562.12 | 500790033.79 | 10195246.28 | New Giza Teaching Hospital |  |  |  | New Giza Hospital25 | New Giza Teaching Hospital25
New Giza Hospital | 1 | 26 | 15191903.43 | 68532450.22 | 53340546.79 | 18129119.1724 | 16494091.451 | -1635027.7214 |  |  |  | 17232986.3 | 2024-04-30 | 2024-05-12 | 2024-05-29 | 51 | 2024-07-19 | 2024-06-13 | 515981937.22 | 268661.25 | 14260202.71 |  |  | 27057529.55 |  | 23641604 | 15191903.43 | 515981937.22 | 17232986.3 | New Giza Teaching Hospital |  |  |  | New Giza Hospital26 | New Giza Teaching Hospital26
New Giza Hospital | 1 | 27 | 16227230.2 | 16173467.3 | -53762.9 | 2051894 | 3376911.615 | 1325017.615 |  |  |  | 13715277.6 | 2024-06-30 | 2024-07-14 | 2024-07-16 | 51 | 2024-09-05 | 2024-08-18 | 532209167.42 | 268661.25 | 14260202 |  | 56175000 | 30715749 |  | 20879747 | 16227230.2 | 532209167.42 | 13715277.6 | New Giza Teaching Hospital |  |  |  | New Giza Hospital27 | New Giza Teaching Hospital27
New Giza Hospital | 1 | 28 | 69437921.36 | 12973500.18 | -56464421.18 | 5534314 | 5534314 | 0 |  |  |  | 6800969.24 | 2024-08-31 | 2024-09-11 | 2024-09-12 | 51 | 2024-11-02 | 2024-10-03 | 601647088.78 | 268661 | 18531949 |  | 56175000 | 15698247.5 | 15698247.5 | 9038450 | 69437921.36 | 601647088.78 | 6800969.24 | New Giza Teaching Hospital |  |  |  | New Giza Hospital28 | New Giza Teaching Hospital28
New Giza Hospital | 1 | 29 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-17 | 2024-10-19 | 51 | 2024-12-09 | [8 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital29 | New Giza Teaching Hospital29
NGU 2 | 1 | 25 | 3430150 | 3460724 | 30574 | 2468493.7 | 5457989.56 | 2989495.86 |  |  |  |  | 2017-09-30 | 2017-10-01 | 2017-09-16 | 28 | 2017-10-14 | 2017-10-11 | 140490291 | 1675290.17 | [5 empty] | 807366.8348 | 0 | 0 | 0 | New Giza 2 |  |  |  | NGU 225 | New Giza 225
NGU 2 | 1 | 26 | 10391625.25 | 6396673.25 | -3994952 | 4990186 | 4990687.1405 | 501.1405 |  |  |  | 6719251.6 | 2017-11-30 | 2017-11-30 | 2018-01-23 | 28 | 2018-02-20 | 2018-05-23 | 150881916.25 | 0 | [5 empty] | 699355.4648 | 6579666.5395 | 147069957.5395 | 3027155.9789 | New Giza 2 |  |  |  | NGU 226 | New Giza 226
NGU 2 | 1 | 27 | 3035230.3681 | 6000000 | 2964769.6319 | 2104161 | 6000000 | 3895839 |  |  |  | 1589855.1267 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 28 | 2019-08-01 | 2019-11-02 | 153917146.6181 | 734008.68 | [5 empty] | 0 | 0 | 0 | 2440072.7285 | New Giza 2 |  |  |  | NGU 227 | New Giza 227
#N/A
ORA - ZED | 1 | 1 | 2407390.5714 | 2407390.57 | -0.0014286 | 101168059.79 | 10377230.16 | -90790829.63 |  |  |  | 10345156.8 | 2020-11-30 | 2020-11-25 | 2020-11-22 | 56 | 2021-01-17 | 2021-01-17 | 2407390.5714 | 9271107.2 | [5 empty] | 0 | 2407390.5714 | 2407390.5714 | 10345156.8 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED1 | ORA ZED - Ph 01B - Pkgs A&D1
ORA - ZED | 1 | 2 | 45205427.0762 | 45205416.45 | -10.6262 | 293983829 | 39936351.7025 | -254047477.2975 |  | 256451321 |  | 37532508 | 2020-12-31 | 2020-12-31 | 2020-12-22 | 56 | 2021-02-16 | 2021-01-06 | 47612817.6476 | 9882492.63 | [5 empty] | 10718.8648 | 43865060.0886 | 46272450.66 | 37827388.6601 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED2 | ORA ZED - Ph 01B - Pkgs A&D2
ORA - ZED | 1 | 3 | 26768107.4476 | 26768118.08 | 10.6324 | 78068925.863 | 29651159.334 | -48417766.529 |  | 50172571.863 |  | 27896354 | 2021-01-31 | 2021-02-03 | 2021-01-31 | 56 | 2021-03-28 | 2021-02-17 | 74380925.0952 | 17071953.36 | [5 empty] | 24994.28 | 23073312.5238 | 70686130.1714 | 28404325.826 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED3 | ORA ZED - Ph 01B - Pkgs A&D3
ORA - ZED | 1 | 4 | 26593168.5429 | 26593168.54 | -0.0028571 | 45888247.393 | 26411905.937 | -19476341.456 |  | 25000000 |  | 20888247.393 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 56 | 2021-05-02 | 2021-03-24 | 100974093.6381 | 20604136.5 | [5 empty] | 50275.41 | 21833038.3714 | 96213963.4667 | 21185755.528 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED4 | ORA ZED - Ph 01B - Pkgs A&D4
ORA - ZED | 1 | 5 | 39594206.7048 | 41442903.7 | 1848696.9952 | 83744386.154 | 33310478.505 | -50433907.649 |  | 50000000 |  | 33744386.154 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 56 | 2021-06-01 | 2021-05-11 | 140568300.3429 | 16740725.26 | [5 empty] | 66054.2648 | 41442903.7055 | 142416997.3436 | 35278804.6637 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED5 | ORA ZED - Ph 01B - Pkgs A&D5
ORA - ZED | 1 | 6 | 13625124.4935 | 13829636.33 | 204511.8365 | 14374377.19 | 4832623.5365 | -9541753.6535 |  | 10000000 |  | 4374377.19 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 56 | 2021-07-05 | 2021-06-08 | 154193424.8364 | 7989637.5618 | [5 empty] | 83003.9348 | 15678333.3286 | 156246633.6714 | 4544122.0162 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED6 | ORA ZED - Ph 01B - Pkgs A&D6
ORA - ZED | 1 | 7 | 11321353.516 | 9268144.68 | -2053208.836 | 10782895.78 | 4340903.024 | -6441992.756 |  | 5000000 |  | 5782895.78 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 56 | 2021-08-04 | 2021-07-15 | 165514778.3524 | 3501497.22 | [5 empty] | 99063.49 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED7 | ORA ZED - Ph 01B - Pkgs A&D7
ORA - ZED | 1 | 8 | 26950096.619 | 26950096.62 | 0.00095236 | 24387331.1 | 25931572.791 | 1544241.691 |  |  |  | 24387331.1 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 56 | 2021-08-25 | 2021-08-12 | 192464874.9714 | 6088729.64 | [5 empty] | 175458.21 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED8 | ORA ZED - Ph 01B - Pkgs A&D8
ORA - ZED | 1 | 9 | 27403398.0286 | 27403398.03 | 0.0014286 | 22624923.97 | 24054179.0515 | 1429255.0815 |  |  |  | 22624923.97 | 2021-07-31 | 2021-07-25 | 2021-08-10 | 56 | 2021-10-05 | 2021-09-20 | 219868273 | 5900263.67 | [5 empty] | 146376.75 | 29833656.4571 | 222298531.4286 | 26728065.13 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED9 | ORA ZED - Ph 01B - Pkgs A&D9
ORA - ZED | 1 | 10 | 32858070.0667 | 32858070.07 | 0.0033334 | 29047725.55 | 30886238.8435 | 1838513.2935 |  |  |  | 29047725.55 | 2021-08-31 | 2021-08-25 | 2021-09-09 | 56 | 2021-11-04 | 2021-09-26 | 252726343.0667 | 8169556.06 | [5 empty] | 164670.96 | 32858070.0667 | 252726343.0667 | 29047725.55 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED10 | ORA ZED - Ph 01B - Pkgs A&D10
ORA - ZED | 1 | 11 | 34769848.6 | 34769848.6 | 0 | 0 | 33022101.84 | 33022101.84 |  |  |  | 31056565.55 | 2021-09-30 | 2021-09-25 | 2021-10-14 | 56 | 2021-12-09 | 2021-11-18 | 287496191.6667 | 10971940.82 | [5 empty] | 182298.18 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED11 | ORA ZED - Ph 01B - Pkgs A&D11
ORA - ZED | 1 | 12 | 33050531.6762 | 33050531.68 | 0.0038095 | 0 | 26088449.724 | 26088449.724 |  |  |  | 24536445.63 | 2021-10-31 | 2021-10-25 | 2021-11-24 | 56 | 2022-01-19 | 2021-12-07 | 320546723.3429 | 7308964.38 | [5 empty] | 182298.18 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED12 | ORA ZED - Ph 01B - Pkgs A&D12
ORA - ZED | 1 | 13 | 30511414.9714 | 30511414.97 | -0.0014286 | 0 | 25426794.8085 | 25426794.8085 |  |  |  | 23914152.624 | 2021-11-30 | 2021-11-25 | 2021-12-14 | 56 | 2022-02-08 | 2021-12-21 | 351058138.3143 | 5524822.34 | [5 empty] | 182298.18 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED13 | ORA ZED - Ph 01B - Pkgs A&D13
ORA - ZED | 1 | 14 | 45635766.9524 | 45635766.95 | -0.002381 | 0 | 38191818.9175 | 38191818.9175 |  |  |  | 35917954.71 | 2021-12-31 | 2021-12-25 | 2021-12-23 | 56 | 2022-02-17 | 2022-01-18 | 396693905.2667 | 3084551.02 | [5 empty] | 213053.66 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED14 | ORA ZED - Ph 01B - Pkgs A&D14
ORA - ZED | 1 | 15 | 27710999.5429 | 27710999.54 | -0.0028571 | 0 | 27179982.227 | 27179982.227 |  |  |  | 25550073.0625 | 2022-01-31 | 2022-01-25 | 2022-02-17 | 56 | 2022-04-14 | 2022-03-31 | 424404904.8095 | 6586185.1 | [5 empty] | 0 | 27710999.5475 | 424404904.8142 | 25550073.0625 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED15 | ORA ZED - Ph 01B - Pkgs A&D15
ORA - ZED | 1 | 16 | 28676537.6667 | 28676537.67 | 0.0033333 | 0 | 23357925.2135 | 23357925.2135 |  |  |  | 21942762.07 | 2022-02-28 | 2022-02-25 | 2022-03-16 | 56 | 2022-05-11 | 2022-04-12 | 453081442.4762 | 4779083.27 |  |  |  | 12012864.945 | 12012864.945 | 0 | 28676537.6669 | 453081442.4811 | 21942762.0737 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED16 | ORA ZED - Ph 01B - Pkgs A&D16
ORA - ZED | 1 | 17 | 30883724.2667 | 31100661.13 | 216936.8633 | 0 | 27837999.2465 | 27837999.2465 |  |  |  | 26002482 | 2022-03-31 | 2022-03-25 | 2022-04-06 | 56 | 2022-06-01 | 2022-05-11 | 483965166.7429 | 5232577.92 | [5 empty] | 0 | 31100661.1293 | 484182103.6103 | 26182539.8028 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED17 | ORA ZED - Ph 01B - Pkgs A&D17
ORA - ZED | 1 | 18 | 9956410.019 | 9690075.24 | -266334.779 | 0 | 7029281.442 | 7029281.442 |  |  |  | 6791166 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-05-26 | 493921576.7619 | 3421449.48 | [5 empty] | 0 | 11112905.9801 | 495295009.5905 | 9292712.69 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED18 | ORA ZED - Ph 01B - Pkgs A&D18
ORA - ZED | 1 | 19 | 21443765.7238 | 21493163.81 | 49398.0862 | 0 | 17518053.2705 | 17518053.2705 |  |  |  | 16483568.4889 | 2022-05-31 | 2022-05-25 | 2022-06-06 | 56 | 2022-08-01 | 2022-06-28 | 515365342.4857 | 1543331.93 | [5 empty] | 0 | 20070332.8941 | 515365342.4846 | 16483568.4889 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED19 | ORA ZED - Ph 01B - Pkgs A&D19
ORA - ZED | 1 | 20 | 25297815.7745 | 25297815.24 | -0.53451 | 16483569.19 | 21744431.032 | 5260861.842 |  |  |  | 8954952.87 | 2022-06-30 | 2022-06-25 | 2022-07-06 | 56 | 2022-08-31 | 2022-08-28 | 540663158.2602 | 852186.4268 | [5 empty] | 0 | 25297815.7756 | 540663158.2602 | 20010194.1812 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED20 | ORA ZED - Ph 01B - Pkgs A&D20
ORA - ZED | 1 | 21 | 9295356.7831 | 9295357.14 | 0.35693 | 7443623.53 | 8181176.157 | 737552.627 |  |  |  | 7443624.2902 | 2022-07-31 | 2022-07-25 | 2022-08-09 | 56 | 2022-10-04 | 2022-09-11 | 549958515.0433 | 836488.6182 | 81555880.4439 |  | 36726721.206 | 14457323.235 | 14457323.235 | 1401842.4693 | 9295356.7831 | 549958515.0433 | 7443624.2902 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED21 | ORA ZED - Ph 01B - Pkgs A&D21
ORA - ZED | 1 | 22 | 9997079.1377 | 9997079.14 | 0.0023408 | 8098825.75 | 8609716.257 | 510890.507 |  |  |  | 8098824.8775 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 56 | 2022-11-02 | 2022-09-28 | 559955594.181 | 557383.0572 | 85664325.1821 |  | 36749996.0022 | 14712768.92 | 14712768.92 | 1379966.9772 | 9997079.1377 | 559955594.181 | 8098824.8775 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED22 | ORA ZED - Ph 01B - Pkgs A&D22
ORA - ZED | 1 | 23 | 27314036.0095 | 51455589.8 | 24141553.7905 | 20215840.09 | 21483271.639 | 1267431.549 |  |  |  | 22964574.875 | 2022-09-30 | 2022-09-25 | 2022-10-09 | 56 | 2022-12-04 | 2022-10-27 | 587269630.1905 | 479281.1936 | 93161830.5539 |  | 36812284.0164 | 15427809.82 | 15427809.82 | 1232906.9943 | 27314036.0095 | 587269630.1905 | 22964574.875 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED23 | ORA ZED - Ph 01B - Pkgs A&D23
ORA - ZED | 1 | 24 | 11751887.1042 | 10139035.7 | -1612851.4042 | 6648903.39 | 8591385.3318 | 1942481.9418 |  |  |  | 7490234.3814 | 2022-12-31 | 2022-12-25 | 2023-01-18 | 56 | 2023-03-15 | 2023-03-22 | 599021517.2946 | 269002.8006 | 98882541.0407 |  | 36839181.7521 | 15725824.83 | 15725824.83 | 3165623.4593 | 11751887.1042 | 599021517.2946 | 7490234.3814 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED24 | ORA ZED - Ph 01B - Pkgs A&D24
ORA - ZED | 1 | 25 | 50310527.2958 | 0 | -50310527.2958 | 2e-05 | 0 | -2e-05 |  |  |  | -9163815.8569 | 2023-02-28 | 2023-02-25 | 2023-03-12 | 56 | 2023-05-07 | 2023-04-10 | 649332044.5905 | 241736.3176 | 113559937.642 | 3600000 | 36956312.6915 | 17045794.51 | 17045794.51 | 465623.4593 | 50310527.2958 | 649332044.5905 | -9163815.8569 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED25 | ORA ZED - Ph 01B - Pkgs A&D25
ORA - ZED | 1 | 26 | 19434003.5361 | 68520137.14 | 49086133.6039 | 9808194.12 | 6863669.1846 | -2944524.9354 |  |  |  | 16993731.7513 | 2023-03-31 | 2023-03-25 | 2023-04-16 | 56 | 2023-06-11 | 2023-05-01 | 668766048.1265 | 239033.6571 | 121577515.47 | 2750000 | 37000350.0494 | 17553262 | 17553262 | 465623.4593 | 19434003.5361 | 668766048.1265 | 16993731.7513 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED26 | ORA ZED - Ph 01B - Pkgs A&D26
ORA - ZED | 1 | 27 | 10662740.4195 | 10547653.65 | -115086.7695 | 8872947.14 | 8722947.15 | -149999.99 |  |  |  | 9042387.5614 | 2023-04-30 | 2023-04-25 | 2023-05-15 | 56 | 2023-07-10 | 2023-06-15 | 679428788.546 | 229309.1567 | 124928010.98 | 2550000 | 37025174.6113 | 17832915.825 | 17832915.825 | 465623.4593 | 10662740.4195 | 679428788.546 | 9042387.5614 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED27 | ORA ZED - Ph 01B - Pkgs A&D27
ORA - ZED | 1 | 28 | 24304667.5968 | 22847215.74 | -1457451.8568 | 9105384.7 | 8905384.6977 | -200000.0023 |  |  |  | 10264179.63 | 2023-05-31 | 2023-05-25 | 2023-06-15 | 56 | 2023-08-10 | 2023-07-09 | 703733456.1429 | 156183.3 | 132876310.5982 | 2350000 | 37192477.1578 | 18469085.205 | 18469085.205 | 489541.1493 | 24304667.5968 | 703733456.1429 | 10264179.63 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED28 | ORA ZED - Ph 01B - Pkgs A&D28
ORA - ZED | 1 | 29 | 27532348.019 | 23928989.08 | -3603358.939 | 10687601.99 | 10687601.99 | 0 |  |  |  | 13678389.68 | 2023-06-30 | 2023-06-25 | 2023-07-17 | 56 | 2023-09-11 | 2023-08-24 | 731265804.1619 |  | 143774737.6483 | 2400000 | 37381001.7016 | 19187904.7592 | 19187904.7592 | 489541.1493 | 27532348.019 | 731265804.1619 | 13678389.68 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED29 | ORA ZED - Ph 01B - Pkgs A&D29
ORA - ZED | 1 | 30 | 26015241.1905 | 24199949.01 | -1815292.1805 | 11585957.67 | 11085957.6804 | -499999.9896 |  |  |  | 13092650.18 | 2023-07-31 | 2023-07-25 | 2023-08-15 | 56 | 2023-10-10 | 2023-09-17 | 757281045.3524 |  | 149337289.3675 | 1900000 | 37609920.1669 | 19870804.84 | 19870804.84 | 489541.1493 | 26015241.1905 | 757281045.3524 | 13092650.18 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED30 | ORA ZED - Ph 01B - Pkgs A&D30
ORA - ZED | 1 | 31 | 26102241.2286 | 21322773.91 | -4779467.3186 | 10253641.2 | 10153641.2135 | -99999.9865 |  |  |  | 12746258.22 | 2023-08-31 | 2023-08-25 | 2023-09-17 | 56 | 2023-11-12 | 2023-09-27 | 783383286.581 |  | 156088918.0852 | 1800000 | 37790500.7321 | 20555988.67 | 20555988.67 | 508143.1541 | 26102241.2286 | 783383286.581 | 12746258.22 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED31 | ORA ZED - Ph 01B - Pkgs A&D31
ORA - ZED | 1 | 32 | 24532813.9714 | 17918865.67 | -6613948.3014 | 8010573.17 | 8010573.17 | 0 |  |  |  | 17052495.52 | 2023-09-30 | 2023-09-25 | 2023-10-12 | 56 | 2023-12-07 | 2023-11-11 | 807916100.5524 |  | 169479041.6436 | 1800000 | 37962018.2328 | 21199975.0395 | 21199975.0395 | 566244.2563 | 24532813.9714 | 807916100.5524 | 17052495.52 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED32 | ORA ZED - Ph 01B - Pkgs A&D32
ORA - ZED | 1 | 33 | 20642302.219 | 18602239.47 | -2040062.749 | 12164893.39 | 12164893.39 | 0 |  |  |  | 13971110.85 | 2023-10-31 | 2023-10-25 | 2023-11-11 | 56 | 2024-01-06 | 2023-12-17 | 828558402.7714 |  | 183850209.8662 | 1800000 | 38104925.5449 | 21741835.4727 | 21741835.4727 | 728244.2563 | 20642302.219 | 828558402.7714 | 13971110.85 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED33 | ORA ZED - Ph 01B - Pkgs A&D33
ORA - ZED | 1 | 34 | 14702199.581 | 12357935.4 | -2344264.181 | 9568963.5 | 10018963.4932 | 449999.9932 |  |  |  | 11514703.33 | 2023-11-30 | 2023-11-25 | 2023-12-17 | 56 | 2024-02-11 | 2024-01-28 | 843260602.3524 |  | 188799507.8 | 2350000 | 38207159.3831 | 22127768.21 | 22127768.21 | 866366.5763 | 14702199.581 | 843260602.3524 | 11514703.33 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED34 | ORA ZED - Ph 01B - Pkgs A&D34
ORA - ZED | 1 | 35 | 13918410.7524 | 9206608.75 | -4711802.0024 | 7391485.26 | 7391485.26 | 0 |  |  |  | 11302280.92 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-02-11 | 857179013.1048 |  | 199336628.67 | 2600000 | 40055372.1837 | 22493126.49 | 22493126.49 | 866366.5763 | 13918410.7524 | 857179013.1048 | 11302280.92 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED35 | ORA ZED - Ph 01B - Pkgs A&D35
ORA - ZED | 1 | 36 | 9427629.6762 | 9427628.57 | -1.1062 | 7054023.71 | 7054023.71 | 0 |  |  |  | 30791363.32 | 2024-01-31 | 2024-01-25 | 2024-02-11 | 56 | 2024-04-07 | 2024-03-12 | 866606642.781 |  | 202490336.7307 | 2950000 | 40124683.5553 | 22740601.77 | 22740601.77 | 1287275.408 | 9427629.6762 | 866606642.781 | 30791363.32 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED36 | ORA ZED - Ph 01B - Pkgs A&D36
ORA - ZED | 1 | 37 | 11141064.9524 | 29089779.62 | 17948714.6676 | 23554316.1 | 23554316.1 | 0 |  |  |  | 9469567.93 | 2024-02-29 | 2024-02-25 | 2024-03-12 | 56 | 2024-05-07 | 2024-04-24 | 877747707.7333 |  | 205574473.0325 | 3350000 | 40202154.5368 | 23033054.728 | 23033054.728 | 1416236.983 | 11141064.9524 | 877747707.7333 | 9469567.93 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED37 | ORA ZED - Ph 01B - Pkgs A&D37
ORA - ZED | 1 | 38 | 15909843.4381 | 23109783.65 | 7199940.2119 | 17627053.17 | 17627053.17 | 0 |  |  |  | 12665876.69 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-09 | 893657551.1714 |  | 212207212.1568 | 3550000 | 40322143.2235 | 23450688.1182 | 23450688.1182 | 1426063.9 | 15909843.4381 | 893657551.1714 | 12665876.69 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED38 | ORA ZED - Ph 01B - Pkgs A&D38
ORA - ZED | 1 | 39 | 9971577.2286 | 9971577.14 | -0.088571 | 7606231.63 | 7606231.63 | 0 |  |  |  | 7606231.5 | 2024-04-30 | 2024-04-25 | 2024-05-09 | 56 | 2024-07-04 | 2024-06-06 | 903629128.4 |  | 212836770.28 | 5150000 | 40471225.4023 | 23712442.02 | 23712442.02 | 1543257.113 | 9971577.2286 | 903629128.4 | 7606231.5 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED39 | ORA ZED - Ph 01B - Pkgs A&D39
ORA - ZED | 1 | 40 | 7576454.8952 | 4495110.55 | -3081344.3452 | 3717952.37 | 3717952.37 | 0 |  |  |  | 6599009.58 | 2024-05-31 | 2024-05-25 | 2024-06-06 | 56 | 2024-08-01 | 2024-07-01 | 911205583.2952 |  | 217295013.586 | 5311993 | 40584498.7969 | 23911323.96 | 23911323.96 | 1866239.86 | 7576454.8952 | 911205583.2952 | 6599009.58 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED40 | ORA ZED - Ph 01B - Pkgs A&D40
ORA - ZED | 1 | 41 | 4542501.819 | 8233965.99 | 3691464.171 | 4428778.21 | 6728778.2096 | 2299999.9996 |  |  |  | 3961614.17 | 2024-06-30 | 2024-06-25 | 2024-07-16 | 56 | 2024-09-10 | 2024-08-31 | 915748085.1143 |  | 218624574.9261 | 4611993 | 40652412.433 | 24038387.2343 | 24038387.2343 | 2836219.6905 | 4542501.819 | 915748085.1143 | 3961614.17 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED41 | ORA ZED - Ph 01B - Pkgs A&D41
ORA - ZED | 1 | 42 | 5377971.181 | 9191767.67 | 3813796.489 | 70851.77 | 7070851.77 | 7000000 |  |  |  | 3504951.97 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-01 | 921126056.2952 |  | 221585074.8608 | 5650000 | 40732816.931 | 24179558.9777 | 24179558.9777 | 3321663.778 | 5377971.181 | 921126056.2952 | 3504951.97 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED42 | ORA ZED - Ph 01B - Pkgs A&D42
ORA - ZED | 1 | 43 | 11538786.4 | 11538786.67 | 0.27 | 6004454.53 | 10554454.5368 | 4550000.0068 |  |  |  | 11004454.56 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-22 | 932664842.6952 |  | 225919078.57 | 5200000 | 40983305.2755 | 24482452.12 | 24482452.12 | 3555974.5005 | 11538786.4 | 932664842.6952 | 11004454.56 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED43 | ORA ZED - Ph 01B - Pkgs A&D43
ORA - ZED | 1 | 44 | 5304711.9524 | 0 | -5304711.9524 | 0 | 0 | 0 |  |  |  | 4559905.68 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 937969554.6476 |  | 231364687.5663 | 5600000 | 41098461.9713 | 24621700.8095 | 24621700.8095 | 3555974.5005 | 5304711.9524 | 937969554.6476 | 4559905.68 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED44 | ORA ZED - Ph 01B - Pkgs A&D44
ORA - ZED | 1 | 45 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 | [8 empty] | 0 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED45 | ORA ZED - Ph 01B - Pkgs A&D45
ORA - ZED - Landscape | 1 | 1 | 2611606.8286 | 2611606.83 | 0.0014286 | 11802742.07 | 2304743.0232 | -9497999.0468 |  |  |  | 2167633.6703 | 2022-11-30 | 2022-11-25 | 2022-12-11 | 56 | 2023-02-05 | 2022-12-20 | 2611606.8286 |  | 503419.5862 |  |  | 68554.675 | 68554.675 | 0 | 2611606.8286 | 2611606.8286 | 2167633.6703 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape1 | Ora Zed Landscape Ph11
ORA - ZED - Landscape | 1 | 2 | 2071867.5333 | 4143733 | 2071865.4667 | 1719649.2 | 1828422.185 | 108772.985 |  |  |  | 1719650.0563 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-01 | 4683474.3619 |  | 1329550.324 |  | 30299.3908 | 122941.2 | 122941.2 | 0 | 2071867.5333 | 4683474.3619 | 1719650.0563 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape2 | Ora Zed Landscape Ph12
ORA - ZED - Landscape | 1 | 3 | 2138801.7905 | 2138801.9 | 0.10952 | 1775205.58 | 1887492.675 | 112287.095 |  |  |  | 1775205.4809 | 2023-01-31 | 2023-01-25 | 2023-01-25 | 56 | 2023-03-22 | 2023-02-26 | 6822276.1524 |  | 2116384.0303 |  | 118260.296 | 179084.745 | 179084.745 | 0 | 2138801.7905 | 6822276.1524 | 1775205.4809 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape3 | Ora Zed Landscape Ph13
ORA - ZED - Landscape | 1 | 4 | 4909563.9143 | 4909564.83 | 0.91571 | 4074938.81 | 4332690.6 | 257751.79 |  |  |  | 4074938.0511 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-10 | 11731840.0667 |  | 4050371.3819 |  | 639071.4395 | 307960.8 | 307960.8 | 0 | 4909563.9143 | 11731840.0667 | 4074938.0511 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape4 | Ora Zed Landscape Ph14
ORA - ZED - Landscape | 1 | 5 | 3861209.6 | 3284925.66 | -576283.94 | 2726488.3 | 2898946.893 | 172458.593 |  |  |  | 3204803.968 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 15593049.6667 |  | 5404662.8768 |  | 772348.3981 | 409317.55 | 409317.55 | 0 | 3861209.6 | 15593049.6667 | 3204803.968 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape5 | Ora Zed Landscape Ph15
ORA - ZED - Landscape | 1 | 6 | 3232045.3524 | 3759868.55 | 527823.1976 | 3120690.89 | 3318083.9875 | 197393.0975 |  |  |  | 3160913.3163 | 2023-04-30 | 2023-04-25 | 2023-05-11 | 56 | 2023-07-06 | 2023-06-07 | 18825095.019 |  | 6624089.2242 |  | 816946.8694 | 494158.74 | 494158.74 | 0 | 3232045.3524 | 18825095.019 | 3160913.3163 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape6 | Ora Zed Landscape Ph16
ORA - ZED - Landscape | 1 | 7 | 1440674.7619 | 1343089.52 | -97585.2419 | 964764.3 | 1035276.496 | 70512.196 |  |  |  | 1045760.0532 | 2023-05-31 | 2023-05-25 | 2023-06-07 | 56 | 2023-08-02 | 2023-07-17 | 20265769.781 |  | 7155995.1362 |  | 835084.5832 | 531976.455 | 531976.455 | 0 | 1440674.7619 | 20265769.781 | 1045760.0532 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape7 | Ora Zed Landscape Ph17
ORA - ZED - Landscape | 1 | 8 | 11600772.2694 | 6274745.71 | -5326026.5594 | 5158038.94 | 5158038.9355 | -0.0045 |  |  |  | 9578640.9799 | 2023-06-30 | 2023-06-25 | 2023-07-09 | 56 | 2023-09-03 | 2023-08-09 | 31866542.0504 |  | 10056562.0507 | 200000 | 5892201.0451 | 836496.7288 | 836496.7288 | 0 | 11600772.2694 | 31866542.0504 | 9578640.9799 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape8 | Ora Zed Landscape Ph18
ORA - ZED - Landscape | 1 | 9 | 3994751.4353 | 4486249.0225 | 491497.5872 | 3863087.97 | 3863087.97 | 0 |  |  |  | 3636861.9198 | 2023-07-31 | 2023-07-25 | 2023-08-07 | 56 | 2023-10-02 | 2023-09-17 | 35861293.4857 |  | 10889989.7064 |  | 5974589.29 | 941358.95 | 941358.95 | 0 | 3994751.4353 | 35861293.4857 | 3636861.9198 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape9 | Ora Zed Landscape Ph19
ORA - ZED - Landscape | 1 | 10 | 3258480.2857 | 3148169.54 | -110310.7457 | 6562980.72 | 2562980.717 | -4000000.003 |  |  |  | 2654538.63 | 2023-08-31 | 2023-08-25 | 2023-09-10 | 56 | 2023-11-05 | 2023-10-10 | 39119773.7714 |  | 12128157.28 | 50000 | 6008554.2 | 1026894.06 | 1026894.06 | 0 | 3258480.2857 | 39119773.7714 | 2654538.63 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape10 | Ora Zed Landscape Ph110
ORA - ZED - Landscape | 1 | 11 | 6742108.1048 | 6460754.42 | -281353.6848 | 5312426.17 | 5312426.17 | 0 |  |  |  | 6014170.71 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-04 | 45861881.8762 |  | 14252099.55 | 100000 | 6064800 | 1203874 | 1203874 | 0 | 6742108.1048 | 45861881.8762 | 6014170.71 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape11 | Ora Zed Landscape Ph111
ORA - ZED - Landscape | 1 | 12 | 9303031.3714 | 7506327.07 | -1796704.3014 | 6030251.47 | 6030251.47 | 0 |  |  |  | 7521516.04 | 2023-10-31 | 2023-10-25 | 2023-11-06 | 56 | 2024-01-01 | 2023-11-20 | 55164913.2476 |  | 16356170.6 | 300000 | 6136800.24 | 1448078.975 | 1448078.975 | 0 | 9303031.3714 | 55164913.2476 | 7521516.04 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape12 | Ora Zed Landscape Ph112
ORA - ZED - Landscape | 1 | 13 | -692002.6286 | 1148717.83 | 1840720.4586 | 0 | 868255.79 | 868255.79 |  |  |  | -674362.19 | 2023-11-30 | 2023-11-25 | 2023-12-11 | 56 | 2024-02-05 | 2024-02-20 | 54472910.619 |  | 13854310.92 | 400000 | 6133954.27 | 1429913.905 | 1429913.905 | 0 | -692002.6286 | 54472910.619 | -674362.19 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape13 | Ora Zed Landscape Ph113
ORA - ZED - Landscape | 1 | 14 | 1197004.6952 | 0 | -1197004.6952 | 868255.79 | 0 | -868255.79 |  |  |  | 1008333.54 | 2023-12-31 | 2023-12-25 | 2024-01-16 | 56 | 2024-03-12 | 2024-03-20 | 55669915.3143 |  | 14304471.38 | 385180.36 | 6143327.5 | 1461335.275 | 1461335.275 | 0 | 1197004.6952 | 55669915.3143 | 1008333.54 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape14 | Ora Zed Landscape Ph114
ORA - ZED - Landscape | 1 | 15 | 3753240.219 | 3753240.01 | -0.20905 | 3165189.2 | 3165189.2 | 0 |  |  |  | 5175911.36 | 2024-01-31 | 2024-01-25 | 2024-02-06 | 56 | 2024-04-02 | 2024-04-20 | 59423155.5333 |  | 16680600.84 | 335180.36 | 5731208.99 | 1559857.835 | 1559857.835 | 0 | 3753240.219 | 59423155.5333 | 5175911.36 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape15 | Ora Zed Landscape Ph115
ORA - ZED - Landscape | 1 | 16 | 1773392.8381 | 1773393.33 | 0.4919 | 1521916.47 | 1521916.4665 | -0.0035 |  |  |  | 1521916.05 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-03-30 | 61196548.3714 |  | 14544514.79 | 285180.36 | 5755565.16 | 1606409.395 | 1606409.395 | 0 | 1773392.8381 | 61196548.3714 | 1521916.05 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape16 | Ora Zed Landscape Ph116
ORA - ZED - Landscape | 1 | 17 | 1582674.7048 | 1582674.29 | -0.41476 | 1313619.66 | 1313619.66 | 0 |  |  |  | 1313620 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-04-28 | 62779223.0762 |  | 15060209.78 | 285180.36 | 5766649.95 | 1647954.605 | 1647954.605 | 0 | 1582674.7048 | 62779223.0762 | 775773.82 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape17 | Ora Zed Landscape Ph117
ORA - ZED - Landscape | 1 | 18 | 1979868.8571 | 1175128.22 | -804740.6371 | 975356.43 | 975356.43 | 0 |  |  |  | 1643291.15 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-05-14 | 64759091.9333 |  | 16924136.12 | 285180.36 | 5796250.4 | 1699926.165 | 1699926.165 | 0 | 1979868.8571 | 64759091.9333 | 1643291.15 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape18 | Ora Zed Landscape Ph118
ORA - ZED - Landscape | 1 | 19 | 1453055.0476 | 1347822.27 | -105232.7776 | 618692.48 | 618692.48 | 0 |  |  |  | 168189.5 | 2024-05-31 | 2024-05-25 | 2024-06-04 | 56 | 2024-07-30 | 2024-07-07 | 66212146.981 |  | 17189828.91 | 785180.36 | 5817974.6 | 1738068.86 | 1738068.86 | 0 | 1453055.0476 | 66212146.981 | 168189.5 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape19 | Ora Zed Landscape Ph119
ORA - ZED - Landscape | 1 | 20 | 1399335.6857 | 1318831.15 | -80504.5357 | 1177303.85 | 1177303.85 | 0 |  |  |  | 1244123 | 2024-06-30 | 2024-06-25 | 2024-07-07 | 56 | 2024-09-01 | 2024-07-23 | 67611482.6667 |  | 17563515.19 | 335180.36 | 5838895.67 | 1774801.42 | 1774801.42 | 0 | 1399335.6857 | 67611482.6667 | 1244123 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape20 | Ora Zed Landscape Ph120
ORA - ZED - Landscape | 1 | 21 | 422349.9905 | 324859.52 | -97490.4705 | 108767.39 | 108767.386 | -0.004 |  |  |  | 189683.6223 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-05 | 68033832.6571 |  | 17849734.0836 | 385180.36 | 5845210.1017 | 1785888.105 | 1785888.105 | 0 | 422349.9905 | 68033832.6571 | 189683.6223 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape21 | Ora Zed Landscape Ph121
ORA - ZED - Landscape | 1 | 22 | 4226377.8476 | 0 | -4226377.8476 | 0 | 0 | 0 |  |  |  | 1388299.8 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-16 | 72260210.5048 |  | 19837405.71 | 935180.36 | 5908397.46 | 1896830.525 | 1896830.525 | 0 | 4226377.8476 | 72260210.5048 | 1388299.8 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape22 | Ora Zed Landscape Ph122
ORA - ZED - Landscape | 1 | 23 | 1124749.1714 | 0 | -1124749.1714 | 0 | 0 | 0 |  |  |  | 1551640.48 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 73384959.6762 |  | 20272182.95 | 435180.36 | 5961374.39 | 1926355.19 | 1926355.19 | 0 | 1124749.1714 | 73384959.6762 | 1551640.48 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape23 | Ora Zed Landscape Ph123
ORA - ZED - Landscape | 1 | 24 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-10 | 56 | 2025-01-05 | [8 empty] | 0 | 0 | 0 | 0 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape24 | Ora Zed Landscape Ph124
ORA - ZED - ph.02 | 1 | 1 | 13196047.2 | 13196047.2 | 0 | 14536704.19 | 15456194.14 | 919489.95 |  | 25000000 | 25000000 | 14536703 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 56 | 2021-12-01 | 2021-10-13 | 13196047.2 | 4533956.5 | [5 empty] | 0 | 13196047.2 | 13196047.2 | 14536703.8371 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.021 | ORA ZED-Ph 2-Pkgs A&D1
ORA - ZED - ph.02 | 1 | 2 | 21711682.2 | 21711682.2 | 0 | 20471935.63 | 21766847.47 | 1294911.84 |  | 15000000 | 12500000 | 20471935.87 | 2021-10-31 | 2021-10-25 | 2021-11-15 | 56 | 2022-01-10 | 2021-11-14 | 34907729.4 | 7634922.31 | [5 empty] | 0 | 21711682.2014 | 34907729.4014 | 20471935.8674 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.022 | ORA ZED-Ph 2-Pkgs A&D2
ORA - ZED - ph.02 | 1 | 3 | 15579509.1905 | 15579509.09 | -0.10048 | 12325142.71 | 9914986.5145 | -2410156.1955 |  | 3000000 |  | 9325143.2186 | 2021-11-30 | 2021-11-25 | 2021-12-05 | 56 | 2022-01-30 | 2022-01-18 | 50487238.5905 | 3073305.59 | [5 empty] | 0 | 15579509.1856 | 50487238.587 | 9325143.2186 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.023 | ORA ZED-Ph 2-Pkgs A&D3
ORA - ZED - ph.02 | 1 | 4 | 34347323.4857 | 34347323.22 | -0.26571 | 54728856.89 | 30546043.101 | -24182813.789 |  | 26000000 |  | 28728856.62 | 2021-12-31 | 2021-12-26 | 2021-12-26 | 56 | 2022-02-20 | 2022-02-15 | 84834562.0762 | 3352350.21 | [5 empty] | 0 | 34505631.6966 | 84992870.2836 | 28860252.4316 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.024 | ORA ZED-Ph 2-Pkgs A&D4
ORA - ZED - ph.02 | 1 | 5 | 10060643.6952 | 10060644.07 | 0.37476 | 12407121.98 | 13201853.2135 | 794731.2335 |  |  |  | 12407122.37 | 2022-01-31 | 2022-01-25 | 2022-02-10 | 56 | 2022-04-07 | 2022-03-23 | 94895205.7714 | 8683284.6 | [5 empty] | 0 | 9902335.4874 | 94895205.771 | 12407122.3694 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.025 | ORA ZED-Ph 2-Pkgs A&D5
ORA - ZED - ph.02 | 1 | 6 | 23225104.4643 | 23225104.47 | 0.0056804 | 16610991.38 | 17674903.7 | 1063912.32 |  |  |  | 16610990.7481 | 2022-02-28 | 2022-02-25 | 2022-03-21 | 56 | 2022-05-16 | 2022-05-10 | 118120310.2353 | 5575171.2714 |  |  |  | 3240037.4255 | 3240037.4255 | 0 | 23225104.4643 | 118120310.2353 | 16610990.7481 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.026 | ORA ZED-Ph 2-Pkgs A&D6
ORA - ZED - ph.02 | 1 | 7 | 42383851.5888 | 42383851.59 | 0.0011564 | 32100387.28 | 34124964.2595 | 2024576.9795 |  |  |  | 32100388.5958 | 2022-03-31 | 2022-03-25 | 2022-04-04 | 56 | 2022-05-30 | 2022-08-07 | 160504161.8242 | 1563640.4346 |  |  |  | 4252325.255 | 4252325.255 | 273333.59 | 42383851.5888 | 160504161.8242 | 32100388.5958 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.027 | ORA ZED-Ph 2-Pkgs A&D7
ORA - ZED - ph.02 | 1 | 8 | 8766077.2795 | 8766077.29 | 0.010467 | 8595540.37 | 9151883.2345 | 556342.8645 |  |  |  | 8595538.9026 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-06-09 | 169270239.1037 | 3486145.8511 |  |  | 32252330.5602 | 4530497.42 | 4530497.42 | 473333.59 | 8766077.2795 | 169270239.1037 | 8595538.9026 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.028 | ORA ZED-Ph 2-Pkgs A&D8
ORA - ZED - ph.02 | 1 | 9 | 8712415.4916 | 8712415.5 | 0.0083646 | 7163536.59 | 7614021.055 | 450484.465 |  |  |  | 7163536.3546 | 2022-05-31 | 2022-05-25 | 2022-06-05 | 56 | 2022-07-31 | 2022-08-08 | 177982654.5953 | 3347808.9149 | 15346414.5805 |  | 32754709.2407 | 4755739.905 | 4755739.905 | 431750.04 | 8712415.4916 | 177982654.5953 | 7163536.3546 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.029 | ORA ZED-Ph 2-Pkgs A&D9
ORA - ZED - ph.02 | 1 | 10 | 25761823.8629 | 25761823.86 | -0.0029215 | 20828447.26 | 22199070.249 | 1370622.989 |  |  |  | 20828447.3064 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 56 | 2022-08-30 | 2022-08-22 | 203744478.4582 | 2710387.4388 | 19184341.5109 |  | 44374111.2806 | 5416052.245 | 5416052.245 | 481750.04 | 25761823.8629 | 203744478.4582 | 20828447.3064 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0210 | ORA ZED-Ph 2-Pkgs A&D10
ORA - ZED - ph.02 | 1 | 11 | 10555360.8465 | 10555360.84 | -0.0065181 | 12170282.5 | 12170282.5 | 0 |  |  |  | 12170283.1854 | 2022-07-31 | 2022-07-25 | 2022-08-10 | 56 | 2022-10-05 | 2022-09-14 | 214299839.3048 | 6960146.9261 | 21459521.0485 |  | 44831361.1808 | 5799374.45 | 5799374.45 | 431750.04 | 10555360.8465 | 214299839.3048 | 12170283.1854 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0211 | ORA ZED-Ph 2-Pkgs A&D11
ORA - ZED - ph.02 | 1 | 12 | 16689354.4631 | 16689354.47 | 0.0068557 | 14759397.95 | 15225579.9035 | 466181.9535 |  |  |  | 14759398 | 2022-08-31 | 2022-08-25 | 2022-09-08 | 56 | 2022-11-03 | 2022-10-12 | 230989193.7679 | 8729597.3 | 23666966.21 |  | 45632622.2463 | 6281714.5 | 6281714.5 | 923489 | 16545380.5429 | 230845219.8476 | 14639634.3822 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0212 | ORA ZED-Ph 2-Pkgs A&D12
ORA - ZED - ph.02 | 1 | 13 | 20581919.2571 | 36051317.97 | 15469398.7129 | 13268244.56 | 13357287.557 | 89042.997 |  |  |  | 17432997.712 | 2022-09-30 | 2022-09-25 | 2022-10-02 | 56 | 2022-11-27 | 2022-10-22 | 251427139.1048 | 9285019.1626 | 25526704.6029 |  | 54138067.1729 | 6832087.88 | 6832087.88 | 1012532.93 | 20581919.2571 | 251427139.1048 | 17432997.712 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0213 | ORA ZED-Ph 2-Pkgs A&D13
ORA - ZED - ph.02 | 1 | 14 | 19311587.7934 | 12548033.06 | -6763554.7334 | 15256729.38 | 15106729.373 | -150000.007 |  |  |  | 15411600.8685 | 2022-10-31 | 2022-10-25 | 2022-11-09 | 56 | 2023-01-04 | 2022-12-15 | 270738726.8982 | 8366501.3369 | 26771100.6571 |  | 60073669.5278 | 7316054.1145 | 7316054.1145 | 862532.9342 | 19311587.7934 | 270738726.8982 | 15411600.8685 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0214 | ORA ZED-Ph 2-Pkgs A&D14
ORA - ZED - ph.02 | 1 | 15 | 14179983.4542 | 20441047.55 | 6261064.0958 | 11384143.67 | 11268654.1775 | -115489.4925 |  |  |  | 11605388.8976 | 2022-11-30 | 2022-11-25 | 2022-12-05 | 56 | 2023-01-30 | 2022-12-20 | 284918710.3524 | 8026884.6944 | 27159626.8647 |  | 63560657.3095 | 7679788.26 | 7679788.26 | 758071.44 | 14179983.4542 | 284918710.3524 | 11605388.8976 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0215 | ORA ZED-Ph 2-Pkgs A&D15
ORA - ZED - ph.02 | 1 | 16 | 11487525.8247 | 23549427.44 | 12061901.6153 | 9858410.94 | 9768410.9408 | -89999.9992 |  |  |  | 9858411.1445 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-05 | 296406236.1771 | 8322611.144 | 27430483.1297 |  | 65684472.9994 | 7988728.975 | 7988728.975 | 668071.44 | 11487525.8247 | 296406236.1771 | 9858411.1445 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0216 | ORA ZED-Ph 2-Pkgs A&D16
ORA - ZED - ph.02 | 1 | 17 | 9516947.0875 | 9516947.6 | 0.51246 | 8988166.12 | 8988166.1131 | -0.0069 |  |  |  | 8988165.9521 | 2023-01-31 | 2023-01-25 | 2023-01-28 | 56 | 2023-03-25 | 2023-03-19 | 305923183.2647 | 9631056.1321 | 28105199.965 |  | 66254957.5517 | 8271259.96 | 8271259.96 | 613266.18 | 9516947.0875 | 305923183.2647 | 8988165.9521 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0217 | ORA ZED-Ph 2-Pkgs A&D17
ORA - ZED - ph.02 | 1 | 18 | 15495416.059 | 15364644.61 | -130771.449 | 13223027.75 | 13333027.7475 | 109999.9975 |  |  |  | 13331568.0485 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-18 | 321418599.3237 | 10365262.5801 | 28915218.0403 | 400000 | 72791890.9694 | 8696369.795 | 8696369.795 | 323266.18 | 15495416.059 | 321418599.3237 | 13331568.0485 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0218 | ORA ZED-Ph 2-Pkgs A&D18
ORA - ZED - ph.02 | 1 | 19 | 8053943.7501 | 8053943.79 | 0.039909 | 6921352.11 | 7571824.5446 | 650472.4346 |  |  |  | 6921352.2914 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 329472543.0738 | 10413345.9625 | 29296490.0269 | 200000 | 76001927.9044 | 8908987.9 | 8908987.9 | 324695.97 | 8053943.7501 | 329472543.0738 | 6921352.2914 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0219 | ORA ZED-Ph 2-Pkgs A&D19
ORA - ZED - ph.02 | 1 | 20 | 4423045.841 | 4105367.03 | -317678.811 | 3038540.29 | 3188540.2834 | 149999.9934 |  |  |  | 3302213.7069 | 2023-04-30 | 2023-04-25 | 2023-05-10 | 56 | 2023-07-05 | 2023-06-01 | 333895588.9148 | 10136406.1294 | 30236499.4184 | 350000 | 76323656.7997 | 9018169.36 | 9018169.36 | 324695.97 | 4423045.841 | 333895588.9148 | 3302213.7069 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0220 | ORA ZED-Ph 2-Pkgs A&D20
ORA - ZED - ph.02 | 1 | 21 | 4766150.0757 | 4766150.56 | 0.48435 | 4532160.06 | 4432160.4921 | -99999.5679 |  |  |  | 4532159.65 | 2023-05-31 | 2023-05-25 | 2023-06-04 | 56 | 2023-07-30 | 2023-08-14 | 338661738.9905 | 10738897.52 | 27714328.99 | 250000 | 79032701.56 | 9158343.085 | 9158343.085 | 324695.97 | 4766150.0798 | 338661738.9946 | 4532159.6508 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0221 | ORA ZED-Ph 2-Pkgs A&D21
ORA - ZED - ph.02 | 1 | 22 | 11000140.3008 | 21592711.1 | 10592570.7992 | 8297638.82 | 8347638.3819 | 49999.5619 |  |  |  | 8466780.16 | 2023-06-30 | 2023-06-25 | 2023-07-12 | 56 | 2023-09-06 | 2023-08-09 | 349661879.2913 | 9962990.1626 | 30646302.9038 | 300000 | 84045575.3164 | 9427699.0855 | 9427699.0855 | 324695.97 | 11000140.3008 | 349661879.2913 | 8466780.16 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0222 | ORA ZED-Ph 2-Pkgs A&D22
ORA - ZED - ph.02 | 1 | 23 | 1051681.4414 | 1051680.08 | -1.3614 | 564270 | 534269.994 | -30000.006 |  |  |  | 564270.13 | 2023-07-31 | 2023-07-25 | 2023-08-09 | 56 | 2023-10-04 | 2023-09-17 | 350713560.7327 | 9534609.8107 | 30624495.36 | 270001 | 84127290.1745 | 9444596.21 | 9444596.21 | 324695.97 | 1051681.4414 | 350713560.7327 | 564270.13 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0223 | ORA ZED-Ph 2-Pkgs A&D23
ORA - ZED - ph.02 | 1 | 24 | 1619984.7524 | 1619984.79 | 0.037619 | 1374587.38 | 1344587.3795 | -30000.0005 |  |  |  | 1374588.34 | 2023-08-31 | 2023-08-25 | 2023-09-09 | 56 | 2023-11-04 | 2023-09-17 | 352333545.4851 | 9534609.8107 | 30639873.392 | 240000 | 84127290.1745 | 9487120.81 | 9487120.81 | 324695.97 | 1619984.7524 | 352333545.4851 | 1374588.34 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0224 | ORA ZED-Ph 2-Pkgs A&D24
ORA - ZED - ph.02 | 1 | 25 | 1429470.734 | 1429471.43 | 0.69601 | 996461.29 | 1086725.0887 | 90263.7987 |  |  |  | 996460.71 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-07 | 353763016.219 | 9534609.81 | 30639873.4 | 430000 | 84470961.01 | 9524644.42 | 9524644.42 | 324695.97 | 1429470.734 | 353763016.219 | 996460.71 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0225 | ORA ZED-Ph 2-Pkgs A&D25
ORA - ZED - ph.02 | 1 | 26 | 3475331.4095 | 3475331.25 | -0.15952 | 2944524.93 | 2884524.9425 | -59999.9875 |  |  |  | 2944525.07 | 2023-10-31 | 2023-10-25 | 2023-11-07 | 56 | 2024-01-02 | 2023-12-14 | 357238347.6286 | 9534609.81 | 30760806.2 | 370000 | 84664884.26 | 9615871.87 | 9615871.87 | 324695.97 | 3475331.4095 | 357238347.6286 | 2944525.07 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0226 | ORA ZED-Ph 2-Pkgs A&D26
ORA - ZED - ph.02 | 1 | 27 | 3041219.2755 | 6420474.62 | 3379255.3445 | 5268993.93 | 5328993.921 | 59999.991 |  |  |  | 6012429.48 | 2023-11-30 | 2023-11-25 | 2023-12-14 | 56 | 2024-02-08 | 2024-01-14 | 360279566.9041 | 9534609.8107 | 31106243.5594 | 430000 | 84803721.0331 | 9695703.875 | 9695703.875 | 324695.97 | 3041219.2755 | 360279566.9041 | 6012429.48 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0227 | ORA ZED-Ph 2-Pkgs A&D27
ORA - ZED - ph.02 | 1 | 28 | 5861894.8952 | 2340664.72 | -3521230.1752 | 1922751.71 | 1922751.71 | 0 |  |  |  | 1674078.17 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-03-03 | 366141461.7993 | 9534609.8107 | 32767206.4615 | 450000 | 88600538.3056 | 9849578.6176 | 9849578.6176 | 324695.97 | 5861894.8952 | 366141461.7993 | 1674078.17 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0228 | ORA ZED-Ph 2-Pkgs A&D28
ORA - ZED - ph.02 | 1 | 29 | 2577878.9747 | 7868267.11 | 5290388.1353 | 5009481.72 | 5059481.7155 | 49999.9955 |  |  |  | 622103 | 2024-01-31 | 2024-01-25 | 2024-02-13 | 56 | 2024-04-09 | 2024-04-15 | 368719340.774 | 7793026.7073 | 32686135.972 | 500000 | 89023126.49 | 9873708.36 | 9873708.36 | 419195.97 | 2577878.9747 | 368719340.774 | 651831.843 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0229 | ORA ZED-Ph 2-Pkgs A&D29
ORA - ZED - ph.02 | 1 | 30 | 2066668.4069 | 10058718.7 | 7992050.2931 | 73017 | 3791012.07 | 3717995.07 |  |  |  | 73017 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-04-29 | 370786009.181 | 6499733.7 | 32340261.62 | 1120000 | 89409590.24 | 9895626.085 | 9895626.085 | 419195.97 | 2066668.4036 | 370786009.1777 | -2279827.56 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0230 | ORA ZED-Ph 2-Pkgs A&D30
ORA - ZED - ph.02 | 1 | 31 | 7992050.6095 | 0 | -7992050.6095 | 3717995 | 0 | -3717995 |  |  |  | 3717995 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-15 | 378778059.7905 | 3482050.01 | 39683396.61 | 1650000 | 88674483.32 | 10029975.32 | 10029975.32 | 419195.97 | 7992050.6 | 378778059.7777 | 3758520.95 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0231 | ORA ZED-Ph 2-Pkgs A&D31
ORA - ZED - ph.02 | 1 | 32 | 2766734.981 | 2766735.75 | 0.76905 | 2836390.67 | 2836390.6675 | -0.0025 |  |  |  | 2943652.2 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-06-05 | 381544794.7714 | 3482050.01 | 39914992.15 | 1110000 | 89539810.97 | 10102602.115 | 10102602.115 | 419195.97 | 2766734.981 | 381544794.7714 | 2943652.2 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0232 | ORA ZED-Ph 2-Pkgs A&D32
ORA - ZED - ph.02 | 1 | 33 | 6575447.0667 | 7988113.29 | 1412666.2233 | 1e-05 | 5000134.02 | 5000134.02 |  |  |  | 1631186.62 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 56 | 2024-07-31 | 2024-07-01 | 388120241.8381 | 3482050.01 | 40131194.96 | 2270000 | 90446780.46 | 10188156.35 | 10188156.35 | 419195.97 | 6575447.0667 | 388120241.8381 | 1631186.62 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0233 | ORA ZED-Ph 2-Pkgs A&D33
ORA - ZED - ph.02 | 1 | 34 | 1412666.8095 | 0 | -1412666.8095 | 1e-05 | 0 | -1e-05 |  |  |  | 3368948.46 | 2024-06-30 | 2024-06-25 | 2024-07-06 | 56 | 2024-08-31 | 2024-08-06 | 389532908.6476 | 3482050.01 | 40483731.09 | 2740000 | 92888843.55 | 10312290.1 | 10312290.1 | 419195.97 | 1412666.8095 | 389532908.6476 | 3368948.46 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0234 | ORA ZED-Ph 2-Pkgs A&D34
ORA - ZED - ph.02 | 1 | 35 | 7262978.339 | 7262978.01 | -0.32896 | 1e-05 | 3820917.5505 | 3820917.5505 |  |  |  | 6454315.65 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-08-31 | 396795886.9866 | 3482050.0134 | 42071751.0265 | 2400000 | 94659153.4844 | 10502943.2837 | 10502943.2837 | 419195.97 | 7262978.339 | 396795886.9866 | 6454315.65 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0235 | ORA ZED-Ph 2-Pkgs A&D35
ORA - ZED - ph.02 | 1 | 36 | 0.003893 | 0 | -0.003893 | 4160916.8 | 0 | -4160916.8 |  |  |  | 6578211.32 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 56 | 2024-10-27 | 2024-09-05 | 396795886.9905 | 11803883.61 | 42071751.03 | 2400000 | 94659153.49 | 10710989.125 | 10710989.125 | 419195.97 | 0.003893 | 396795886.9905 | 6578211.32 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0236 | ORA ZED-Ph 2-Pkgs A&D36
ORA - ZED - ph.02 | 1 | 37 | 12000518.9238 | 12751303.62 | 750784.6962 | 8601492.56 | 12413453.42 | 3811960.86 |  |  |  | 9153293.69 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-10-07 | 408796405.9143 | 10593047.63 | 43987735.96 | 2250000 | 101066779.38 | 10995731.845 | 10995731.845 | 419195.97 | 12000518.9238 | 408796405.9143 | 9153293.69 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0237 | ORA ZED-Ph 2-Pkgs A&D37
ORA - ZED - ph.02 | 1 | 38 | -0.0095238 | 0 | 0.0095238 | 3811960.86 | 0 | -3811960.86 |  |  |  | 3851310.01 | 2024-09-30 | 2024-09-16 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-07 | 408796405.9048 | 15718197.44 | 43987735.96 | 2450000 | 101066779.38 | 11123860.59 | 11123860.59 | 419195.97 | -0.0095238 | 408796405.9048 | 3851310.01 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0238 | ORA ZED-Ph 2-Pkgs A&D38
ORA - ZED - ph.02 | 1 | 39 | 13783192.8762 | 0 | -13783192.8762 | 0 | 0 | 0 |  |  |  | 14526906.83 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-11-09 | 422579598.781 | 19699160.8 | 49807541.52 | 2510000 | 103795295.53 | 11585193.49 | 11585193.49 | 419195.97 | 13783192.8762 | 422579598.781 | 14526906.83 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0239 | ORA ZED-Ph 2-Pkgs A&D39
ORA - ZED - ph.02 | 1 | 40 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-30 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 | [8 empty] | 0 | 0 | 0 | 0 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0240 | ORA ZED-Ph 2-Pkgs A&D40
#N/A
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | 1222080 | 12938311.9 | 11716231.9 | 2832501.18 | 18468978.3325 | 15636477.1525 |  |  |  | 2841415.8 | 2019-11-30 | 2019-12-05 | 2019-12-07 | 7 | 2019-12-14 | 2019-12-11 | 1222080 | 2056962.6 | [5 empty] | 0 | 1222080 | 1222080 | 2841415.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling1 | ESU Ph2-Enabling & Struc1
PH.2-El Sewedy Uni. - Enabling | 1 | 2 | 19989408.99 | 50450016.01 | 30460607.02 | 13318143.89 | 27543185.353 | 14225041.463 |  |  |  | 13446882.5 | 2019-12-31 | 2020-01-02 | 2020-01-02 | 7 | 2020-01-09 | 2020-01-11 | 21211488.99 | 2672643.6 | [5 empty] | 0 | 19989408.99 | 21211488.99 | 13446882.5 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling2 | ESU Ph2-Enabling & Struc2
PH.2-El Sewedy Uni. - Enabling | 1 | 3 | 22171564.66 | 42202241.42 | 20030676.76 | 17089175.5 | 40351874.115 | 23262698.615 |  |  |  | 17089175.5 | 2020-01-31 | 2020-01-30 | 2020-01-30 | 7 | 2020-02-06 | 2020-02-05 | 43383053.65 | 5401152.9 | [5 empty] | 0 | 22171564.66 | 43383053.65 | 17089175.5 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling3 | ESU Ph2-Enabling & Struc3
PH.2-El Sewedy Uni. - Enabling | 1 | 4 | 17471458.95 | 45147950.09 | 27676491.14 | 14773850.81 | 33096273.5075 | 18322422.6975 |  |  |  | 14773850.7 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 7 | 2020-03-14 | 2020-03-16 | 60854512.6 | 8960074.2 | [5 empty] | 0 | 17471458.95 | 60854512.6 | 14773850.7 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling4 | ESU Ph2-Enabling & Struc4
PH.2-El Sewedy Uni. - Enabling | 1 | 5 | 7891719.6 | 61459711.62 | 53567992.02 | 2392694.9 | 66399057.54 | 64006362.64 |  |  |  | 2392694.9 | 2020-03-31 | 2020-03-15 | 2020-03-26 | 7 | 2020-04-02 | 2020-04-09 | 68746232.2 | 6287074.2 | [5 empty] | 0 | 7891719.6 | 68746232.2 | 2392694.9 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling5 | ESU Ph2-Enabling & Struc5
PH.2-El Sewedy Uni. - Enabling | 1 | 6 | 18379179.4 | 47027611.72 | 28648432.32 | 7788095.22 | 16671348.956 | 8883253.736 |  |  |  | 7788095.2 | 2020-04-30 | 2020-04-15 | 2020-04-26 | 7 | 2020-05-03 | 2020-05-06 | 87125411.6 | 2277574.2 | [5 empty] | 0 | 18379179.4 | 87125411.6 | 7788095.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling6 | ESU Ph2-Enabling & Struc6
PH.2-El Sewedy Uni. - Enabling | 1 | 7 | 9076073.5 | 65881799.31 | 56805725.81 | 3548357.43 | 29303962.2315 | 25755604.8015 |  |  |  | 3548357.4 | 2020-05-31 | 2020-05-31 | 2020-06-08 | 7 | 2020-06-15 | 2020-07-11 | 96201485.1 | 0 | [5 empty] | 0 | 9076073.5 | 96201485.1 | 3548357.4 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling7 | ESU Ph2-Enabling & Struc7
PH.2-El Sewedy Uni. - Enabling | 1 | 8 | 2504382.4 | 72131815.88 | 69627433.48 | 1607563.1 | 26734888.538 | 25127325.438 |  |  |  | 1607563.1 | 2020-06-30 | 2020-06-30 | 2020-07-07 | 7 | 2020-07-14 | 2020-07-09 | 98705867.5 | [6 empty] | 0 | 2504382.4 | 98705867.5 | 1607563.1 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling8 | ESU Ph2-Enabling & Struc8
PH.2-El Sewedy Uni. - Enabling | 1 | 9 | 9452002.7 | 85510909.33 | 76058906.63 | 8739144.88 | 20706425.9765 | 11967281.0965 |  |  |  | 8526565.2 | 2020-07-31 | 2020-08-15 | 2020-08-17 | 7 | 2020-08-24 | 2020-08-27 | 108157870.2 | [6 empty] | 0 | 9452002.7 | 108157870.2 | 8526565.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling9 | ESU Ph2-Enabling & Struc9
PH.2-El Sewedy Uni. - Enabling | 1 | 10 | 5068271.5 | 49141746.76 | 44073475.26 | 7703511.41 | 20441591.628 | 12738080.218 |  |  |  | 7703511.3 | 2020-11-30 | 2020-11-15 | 2020-11-22 | 7 | 2020-11-29 | 2020-11-22 | 113226141.7 | [6 empty] | 118504 | 0 | 0 | 0 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling10 | ESU Ph2-Enabling & Struc10
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | 39552087.9 | 12938311.9 | -26613776 | 50636298.9 | 18468978.3325 | -32167320.5675 |  | 15000000 |  | 35636298.9 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 14 | 2020-03-21 | 2020-03-22 | 39552087.9 | 27835856 | [5 empty] | 0 | 39552087.9 | 39552087.9 | 35636298.9 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes1 | ESU Ph2-Enabling & Struc1
PH.2-El Sewedy Uni. - Finishes | 1 | 2 | 33281363.92 | 50450016.01 | 17168652.09 | 26758389.8 | 27543185.353 | 784795.553 |  |  |  | 26758389.8 | 2020-03-31 | 2020-03-31 | 2020-04-05 | 14 | 2020-04-19 | 2020-04-22 | 72833451.82 | 40761852.6 | [5 empty] | 0 | 33281363.92 | 72833451.82 | 26758389.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes2 | ESU Ph2-Enabling & Struc2
PH.2-El Sewedy Uni. - Finishes | 1 | 3 | 24169965.9076 | 42202241.42 | 18032275.5124 | 23262698.8 | 40351874.115 | 17089175.315 |  |  |  | 23262698.8 | 2020-04-30 | 2020-04-30 | 2020-05-06 | 14 | 2020-05-20 | 2020-05-19 | 97003417.7276 | 51226946.1 | [5 empty] | 0 | 24169965.9076 | 97003417.7276 | 23262698.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes3 | ESU Ph2-Enabling & Struc3
PH.2-El Sewedy Uni. - Finishes | 1 | 4 | 24591514.8424 | 45147950.09 | 20556435.2476 | 18322600.95 | 33096273.5075 | 14773672.5575 |  |  |  | 18322601 | 2020-05-31 | 2020-05-31 | 2020-06-14 | 14 | 2020-06-28 | 2020-06-18 | 121594932.57 | 51695436 | [5 empty] | 0 | 24591514.8424 | 121594932.57 | 18322601 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes4 | ESU Ph2-Enabling & Struc4
PH.2-El Sewedy Uni. - Finishes | 1 | 5 | 77007398.3 | 61459711.62 | -15547686.68 | 64006362.98 | 66399057.54 | 2392694.56 |  |  |  | 64006362.8 | 2020-06-30 | 2020-06-30 | 2020-07-08 | 14 | 2020-07-22 | 2020-07-13 | 198602330.87 | 81242431.4 | [5 empty] | 0 | 77007398.3 | 198602330.87 | 64006362.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes5 | ESU Ph2-Enabling & Struc5
PH.2-El Sewedy Uni. - Finishes | 1 | 6 | 22875033.55 | 47027611.72 | 24152578.17 | 8883254.07 | 16671348.956 | 7788094.886 |  |  |  | 8883254.2 | 2020-07-31 | 2020-07-15 | 2020-07-27 | 14 | 2020-08-10 | 2020-07-29 | 221477364.42 | 71736256.5 | [5 empty] | 0 | 22875033.55 | 221477364.42 | 8883254.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes6 | ESU Ph2-Enabling & Struc6
PH.2-El Sewedy Uni. - Finishes | 1 | 7 | 54216090.64 | 65881799.31 | 11665708.67 | 25755604.75 | 29303962.2315 | 3548357.4815 |  |  |  | 30755604.9 | 2020-08-31 | 2020-08-15 | 2020-08-17 | 14 | 2020-08-31 | 2020-08-26 | 275693455.06 | 65901640.4 | [5 empty] | 0 | 54216090.64 | 275693455.06 | 30755604.9 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes7 | ESU Ph2-Enabling & Struc7
PH.2-El Sewedy Uni. - Finishes | 1 | 8 | 61814968.03 | 72131815.88 | 10316847.85 | 25127325.53 | 26734888.538 | 1607563.008 |  |  |  | 30127325.7 | 2020-08-31 | 2020-08-31 | 2020-09-10 | 14 | 2020-09-24 | 2020-09-17 | 337508423.09 | 51289431.9 | [5 empty] | 0 | 61814968.03 | 337508423.09 | 30127325.7 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes8 | ESU Ph2-Enabling & Struc8
PH.2-El Sewedy Uni. - Finishes | 1 | 9 | 56169721.37 | 85510909.33 | 29341187.96 | 20493846.09 | 20706425.9765 | 212579.8865 |  |  |  | 20493846 | 2020-09-30 | 2020-09-15 | 2020-10-18 | 14 | 2020-11-01 | 2020-10-20 | 393678144.46 | 22011525 | [5 empty] | 0 | 56169721.37 | 393678144.46 | 20493846 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes9 | ESU Ph2-Enabling & Struc9
PH.2-El Sewedy Uni. - Finishes | 1 | 10 | 33204826.41 | 49141746.76 | 15936920.35 | 9765894.8 | 20441591.628 | 10675696.828 |  |  |  | 9765894.8 | 2020-10-31 | 2020-10-25 | 2020-11-10 | 14 | 2020-11-24 | 2020-11-19 | 426882970.87 | 8412160.7 | [5 empty] | 0 | 33204826.41 | 426882970.87 | 9765894.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes10 | ESU Ph2-Enabling & Struc10
PH.2-El Sewedy Uni. - Finishes | 1 | 11 | 20698550.4 | 24045616.1 | 3347065.7 | 13851401.63 | 13851401.63 | 0 |  |  |  | 13851401.2 | 2020-11-30 | 2020-12-01 | 2020-12-15 | 14 | 2020-12-29 | 2020-12-21 | 447581521.27 | 6756406.26 | [5 empty] | 0 | 20698550.4 | 447581521.27 | 13851401.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes11 | ESU Ph2-Enabling & Struc11
PH.2-El Sewedy Uni. - Finishes | 1 | 12 | 33191485.02 | 38061417.81 | 4869932.79 | 23340124.9 | 23340124.2605 | -0.6395 |  |  |  | 23340124.9 | 2021-01-31 | 2021-02-10 | 2021-02-14 | 14 | 2021-02-28 | 2021-03-22 | 480773006.29 | [6 empty] | 0 | 36099063.7776 | 483680585.0476 | 26122387 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes12 | ESU Ph2-Enabling & Struc12
PH.2-El Sewedy Uni. - Finishes | 1 | 13 | 13891238 | 0 | -13891238 | 15069000 | 0 | -15069000 |  |  |  | 19693398.5 | 2021-05-31 | 2021-06-09 | 2022-03-28 | 14 | 2022-04-11 | 2022-04-27 | 494664244.29 |  |  |  |  | 12984936.4125 | 12984936.4125 | 0 | 13891238 | 494664244.29 | 19693398.5 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes13 | ESU Ph2-Enabling & Struc13
PI Parks - ELSEWEDY | 1 | 1 | 2947938.09 | 0 | -2947938.09 | 3779007.23 | 0 | -3779007.23 |  |  |  | 3779007.23 | 2017-09-30 | 2017-10-03 | 2017-10-18 | 15 | 2017-11-16 | 2017-11-04 | 2947938.09 | 2165254 | [5 empty] | 350000 | 3990886.7187 | 3990886.7187 | 5549711.3149 | 0 |  |  |  | PI Parks - ELSEWEDY1 | 01
PI Parks - ELSEWEDY | 1 | 2 | 4598153.29 | 0 | -4598153.29 | 3366014.15 | 0 | -3366014.15 |  |  |  | 3366014.15 | 2017-10-31 | 2017-11-04 | 2017-11-06 | 15 | 2017-12-09 | 2017-11-28 | 7546090.84 | 1128937.5 | [5 empty] | 360362.87 | 4642464.2724 | 7590402.3632 | 4153538.7944 | 0 |  |  |  | PI Parks - ELSEWEDY2 | 02
PI Parks - ELSEWEDY | 1 | 3 | 1603218.21 | 0 | -1603218.21 | 823701.85 | 0 | -823701.85 |  |  |  | 823701.84 | 2017-11-30 | 2017-12-04 | 2017-12-04 | 15 | 2018-01-09 | 2017-12-25 | 9149309.06 | 1055385.4 | [5 empty] | 360362.87 | 1837652.48 | 9383809.13 | 1754857.27 | 0 |  |  |  | PI Parks - ELSEWEDY3 | 03
PI Parks - ELSEWEDY | 1 | 4 |  | 0 | 0 | 2572231.81 | 0 | -2572231.81 |  |  |  | 2572231.81 | 2017-12-31 | 2017-12-31 | 2018-01-04 | 15 | 2018-02-17 | 2018-02-15 | 12280064.67 | 862309.875 | [5 empty] | 711378.1905 | 3758163.8696 | 12907472.9296 | 3155027.6241 | 0 |  |  |  | PI Parks - ELSEWEDY4 | 04
PI Parks - ELSEWEDY | 1 | 5 | 2043145.23 | 0 | -2043145.23 | 1175600.49 | 0 | -1175600.49 |  |  |  | 1175600.49 | 2018-01-31 | 2018-02-07 | 2018-02-07 | 15 | 2018-03-28 | 2018-04-05 | 14323209.9 | 439890.2 | [5 empty] | 110286.54 | 1927670.8 | 14835143.73 | 1692874.42 | 0 |  |  |  | PI Parks - ELSEWEDY5 | 05
PI Parks - ELSEWEDY | 1 | 6 | 662608.11 | 0 | -662608.11 | 689110.93 | 0 | -689110.93 |  |  |  | 689113.69 | 2018-02-28 | 2018-03-10 | 2018-03-11 | 15 | 2018-04-28 | 2018-04-15 | 14985818.01 | 602282.21 | [5 empty] | 0 | 694638.63 | 15017848.53 | 306624.33 | 0 |  |  |  | PI Parks - ELSEWEDY6 | 06
PI Parks - ELSEWEDY | 1 | 7 | 667972.21 | 0 | -667972.21 | 1209313.47 | 0 | -1209313.47 |  |  |  | 1938615.93 | 2018-03-31 | 2018-04-10 | 2018-04-16 | 15 | 2018-05-08 | 2018-04-21 | 15685820.74 | 1491568.3 | [5 empty] | 0 | 667972.21 | 15685820.74 | 1938615.93 | 0 |  |  |  | PI Parks - ELSEWEDY7 | 07
PI Parks - ELSEWEDY | 1 | 8 | 1859636.86 | 0 | -1859636.86 | 1492654.2 | 0 | -1492654.2 |  |  |  | 1633991.6379 | 2018-04-30 | 2018-05-09 | 2018-05-09 | 15 | 2018-06-03 | 2018-06-02 | 17545457.6 | 1274527.689 | [5 empty] | 0 | 1892096.0888 | 17577916.8288 | 1633991.6379 | 0 |  |  |  | PI Parks - ELSEWEDY8 | 08
PI Parks - ELSEWEDY | 1 | 9 | 1491159.5592 | 0 | -1491159.5592 | 1471457.2 | 0 | -1471457.2 |  |  |  | 1607545.8276 | 2018-05-31 | 2018-06-09 | 2018-06-09 | 15 | 2018-06-29 | 2018-06-12 | 19036617.1592 | 1586317.356 | [5 empty] | 0 | 1491159.5592 | 19036617.1592 | 1607545.8276 | 0 |  |  |  | PI Parks - ELSEWEDY9 | 09
PI Parks - ELSEWEDY | 1 | 10 | 3200065.7108 | 0 | -3200065.7108 | 2470019.34 | 0 | -2470019.34 |  |  |  | 2470019.34 | 2018-06-30 | 2018-07-08 | 2018-07-10 | 15 | 2018-08-08 | 2018-08-01 | 22236682.87 | 1486479.93 | [5 empty] | 115532.14 | 4758616.5674 | 23795233.7266 | 3824599.4146 | 0 |  |  |  | PI Parks - ELSEWEDY10 | 010
PI Parks - ELSEWEDY | 1 | 11 | 890276.26 | 0 | -890276.26 | 945860.23 | 0 | -945860.23 |  |  |  | 945860.23 | 2018-07-31 | 2018-08-02 | 2018-08-07 | 15 | 2018-08-25 | 2018-09-13 | 23126959.13 | 1734570.528 | [5 empty] | 125532.14 | 891495.1766 | 23128178.0466 | 442152.4951 | 0 |  |  |  | PI Parks - ELSEWEDY11 | 011
PI Parks - ELSEWEDY | 1 | 12 | 1804540.7798 | 0 | -1804540.7798 | 1347803.37 | 0 | -1347803.37 |  |  |  | 1530660.1341 | 2018-08-31 | 2018-09-06 | 2018-09-08 | 15 | 2018-10-13 | 2018-09-26 | 24932718.8264 | 1713142.271 | [5 empty] | 0 | 1804540.7798 | 24932718.8264 | 1530660.1341 | 0 |  |  |  | PI Parks - ELSEWEDY12 | 012
PI Parks - ELSEWEDY | 1 | 13 | 1076504.1197 | 0 | -1076504.1197 | 719804.13 | 0 | -719804.13 |  |  |  | 716605.5327 | 2018-09-30 | 2018-10-04 | 2018-10-04 | 15 | 2018-10-27 | 2018-10-10 | 26009222.9461 | 1579309.545 | [5 empty] | 0 | 1076504.1197 | 26009222.9461 | 716605.5327 | 0 |  |  |  | PI Parks - ELSEWEDY13 | 013
PI Parks - ELSEWEDY | 1 | 14 | 1188716.2339 | 0 | -1188716.2339 | 775351.46 | 0 | -775351.46 |  |  |  | 775351.46 | 2018-10-31 | 2018-11-05 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 27197939.18 | 1430574.85 | [5 empty] | 194651.72 | 2476006.3139 | 28485229.26 | 1986968.45 | 0 |  |  |  | PI Parks - ELSEWEDY14 | 014
PI Parks - ELSEWEDY | 1 | 15 | 6486957.62 | 0 | -6486957.62 | 4484634.14 | 0 | -4484634.14 |  |  |  | 4484634.17 | 2018-11-30 | 2018-12-06 | 2018-12-06 | 15 | 2019-01-01 | 2018-12-26 | 33684896.8 | 1125214.43 | [5 empty] | 209651.72 | 7576900.68 | 34774839.86 | 5773335.65 | 0 |  |  |  | PI Parks - ELSEWEDY15 | 015
PI Parks - ELSEWEDY | 1 | 16 | 4932880.46 | 0 | -4932880.46 | 4125986.43 | 0 | -4125986.43 |  |  |  | 4125986.43 | 2018-12-31 | 2019-01-06 | 2019-01-06 | 15 | 2019-01-31 | 2019-01-27 | 38617777.26 | 889716.88 | [5 empty] | 245586.01 | 6344223.5299 | 40029120.3299 | 5768808.1936 | 0 |  |  |  | PI Parks - ELSEWEDY16 | 016
PI Parks - ELSEWEDY | 1 | 17 | 1718123.55 | 0 | -1718123.55 | 1375431.38 | 0 | -1375431.38 |  |  |  | 1375431.38 | 2019-01-31 | 2019-02-05 | 2019-02-07 | 15 | 2019-03-05 | 2019-03-13 | 40335900.81 | 584649.66 | [5 empty] | 261703.2 | 3393993.12 | 42011770.38 | 3296251.57 | 0 |  |  |  | PI Parks - ELSEWEDY17 | 017
PI Parks - ELSEWEDY | 1 | 18 | 4308748.67 | 0 | -4308748.67 | 3699864.67 | 0 | -3699864.67 |  |  |  | 3699864.67 | 2019-02-28 | 2019-03-05 | 2019-03-06 | 15 | 2019-04-03 | 2019-03-27 | 44644649.48 | 439815.151 | [5 empty] | 261703.2 | 4573274.545 | 46585044.925 | 5638741.9194 | 0 |  |  |  | PI Parks - ELSEWEDY18 | 018
PI Parks - ELSEWEDY | 1 | 19 | 2652468.02 | 0 | -2652468.02 | 2311261.81 | 0 | -2311261.81 |  |  |  | 2311261.81 | 2019-03-31 | 2019-04-06 | 2019-04-06 | 15 | 2019-05-04 | 2019-05-14 | 47297117.5 | 171933.6095 | [5 empty] | 276703.2 | 4823264.9186 | 49467914.3986 | 4754946.3629 | 0 |  |  |  | PI Parks - ELSEWEDY19 | 019
PI Parks - ELSEWEDY | 1 | 20 | 4018450.9279 | 0 | -4018450.9279 | 1466574.4 | 0 | -1466574.4 |  |  |  | 1816746.614 | 2019-04-30 | 2019-05-05 | 2019-05-07 | 15 | 2019-06-05 | 2019-05-19 | 51315568.4279 | 161583.8345 | [5 empty] | 0 | 4018450.9279 | 51315568.4279 | 1816746.614 | 0 |  |  |  | PI Parks - ELSEWEDY20 | 020
PI Parks - ELSEWEDY | 1 | 21 | 598299.7921 | 0 | -598299.7921 | 5333565.74 | 0 | -5333565.74 |  |  |  | 5879272.6391 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 51913868.22 | 179052.64 | [5 empty] | 0 | 598299.7921 | 51913868.22 | 5879272.6391 | 0 |  |  |  | PI Parks - ELSEWEDY21 | 021
PI Parks - MEP | 1 | 1 | 4100153.37 | 0 | -4100153.37 | 7818631.64 | 0 | -7818631.64 |  |  |  | 7818631.64 | 2018-09-30 | 2018-10-04 | 2018-09-27 | 15 | 2018-10-27 | 2018-10-10 | 4100153.37 | 4989525.8132 | [5 empty] | 0 | 4100153.37 | 4100153.37 | 7818631.64 | 0 |  |  |  | PI Parks - MEP1 | 01
PI Parks - MEP | 1 | 2 | 3824663.6 | 0 | -3824663.6 | 3907009.94 | 0 | -3907009.94 |  |  |  | 3907009.94 | 2018-10-31 | 2018-11-02 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 7924816.97 | 5871509.91 | [5 empty] | 0 | 3824663.6 | 7924816.97 | 3978690.02 | 0 |  |  |  | PI Parks - MEP2 | 02
PI Parks - MEP | 1 | 3 | 2526634.86 | 0 | -2526634.86 | 3921714.73 | 0 | -3921714.73 |  |  |  | 3921714.73 | 2018-11-30 | 2018-12-10 | 2018-12-03 | 15 | 2019-01-01 | 2018-12-26 | 10451451.83 | 8435854.55 | [5 empty] | 0 | 4229682.9 | 12154499.87 | 4042223.64 | 0 |  |  |  | PI Parks - MEP3 | 03
PI Parks - MEP | 1 | 4 | 13292686.78 | 0 | -13292686.78 | 3366511.48 | 0 | -3366511.48 |  |  |  | 3514249.7617 | 2018-12-31 | 2019-01-05 | 2019-01-05 | 15 | 2019-01-31 | 2019-01-14 | 23744138.61 | 6341086.69 | [5 empty] | 0 | 13292686.78 | 23744138.61 | 3514249.7617 | 0 |  |  |  | PI Parks - MEP4 | 04
PI Parks - MEP | 1 | 5 | 8084326 | 0 | -8084326 | 6350059.5 | 0 | -6350059.5 |  |  |  | 6350059.5 | 2019-01-31 | 2019-02-05 | 2019-02-05 | 15 | 2019-03-05 | 2019-03-13 | 31828464.61 | 8184608.01 | [5 empty] | 0 | 7765619.63 | 31509758.24 | 6241537.12 | 0 |  |  |  | PI Parks - MEP5 | 05
PI Parks - MEP | 1 | 6 | 3232894.78 | 0 | -3232894.78 | 919139.23 | 0 | -919139.23 |  |  |  | 919139.23 | 2019-02-28 | 2019-03-05 | 2019-03-05 | 15 | 2019-04-03 | 2019-03-26 | 35061359.39 | 6744285.61 | [5 empty] | 0 | 3555303.77 | 35065062.01 | 2455515.29 | 0 |  |  |  | PI Parks - MEP6 | 06
PI Parks - MEP | 1 | 7 | 4908164.7341 | 0 | -4908164.7341 | 2661364.08 | 0 | -2661364.08 |  |  |  | 2661364.08 | 2019-03-31 | 2019-04-01 | 2019-04-04 | 15 | 2019-05-04 | 2019-05-14 | 39969524.1241 | 4404706.2941 | [5 empty] | 0 | 4908164.7774 | 39969524.1674 | 4844170.7079 | 0 |  |  |  | PI Parks - MEP7 | 07
PI Parks - MEP | 1 | 8 | 2655162.8183 | 0 | -2655162.8183 | 1478131.5 | 0 | -1478131.5 |  |  |  | 1686090.7908 | 2019-04-30 | 2019-05-05 | 2019-05-06 | 15 | 2019-06-05 | 2019-05-19 | 42624686.9424 | 3262993.985 | [5 empty] | 0 | 2655162.8183 | 42624686.9424 | 1686090.7908 | 0 |  |  |  | PI Parks - MEP8 | 08
PI Parks - MEP | 1 | 9 | 3596767.6976 | 0 | -3596767.6976 | 4813799.42 | 0 | -4813799.42 |  |  |  | 5081340.66 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 46221454.64 | 42070.75 | [5 empty] | 0 | 3596767.6976 | 46221454.64 | 5081340.66 | 0 |  |  |  | PI Parks - MEP9 | 09
#N/A
PK #107 | 1 | 8 |  | 4398604 | 4398604 | 3005745.85 | 3203756.07 | 198010.22 |  |  |  | 3005745.85 | 2017-09-30 | 2017-09-28 | 2017-09-28 | 30 | 2017-10-28 | 2017-10-15 | 36182581.41 | 1713544.64 | [5 empty] | 238645.64 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #1078 | EMAAR-PKG#107-MARASSI8
PK #107 | 1 | 9 | 1856322.11 | 1856943 | 620.89 | 1418090.5 | 1514267.88 | 96177.38 |  |  |  | 1418090.5 | 2017-10-31 | 2017-10-31 | 2017-11-01 | 30 | 2017-12-01 | 2017-11-28 | 38038903.52 | 1713544.64 | [5 empty] | 253179.82 | 1856322.11 | 38038903.52 | 1418090.5 | EMAAR-PKG#107-MARASSI |  |  |  | PK #1079 | EMAAR-PKG#107-MARASSI9
PK #107 | 1 | 10 | 2025124.41 | 2025522 | 397.59 | 1453205.38 | 1551018.61 | 97813.23 |  |  |  | 1453205.39 | 2017-11-30 | 2017-11-28 | 2017-11-28 | 30 | 2017-12-28 | 2017-12-27 | 40064027.93 | 1875947.9 | [5 empty] | 264974.51 | 2025124.41 | 40064027.93 | 1453205.39 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10710 | EMAAR-PKG#107-MARASSI10
PK #107 | 1 | 11 | 3591068.23 | 8556417.13 | 4965348.9 | 2354508.52 | 7227720.526 | 4873212.006 |  |  |  | 2604921.36 | 2017-12-31 | 2017-12-25 | 2017-12-27 | 30 | 2018-01-26 | 2018-01-15 | 43655096.16 | 1188936.54 | [5 empty] | 282897.2 | 3591068.23 | 43655096.16 | 2604921.36 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10711 | EMAAR-PKG#107-MARASSI11
PK #107 | 1 | 12 | 5883258.75 | 0 | -5883258.75 | 4193998 | 0 | -4193998 |  |  |  | 5012769.61 | 2018-01-31 | 2018-01-25 | 2018-01-25 | 30 | 2018-02-24 | 2018-02-26 | 49538354.91 | 366842.14 | [5 empty] | 315029.17 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10712 | EMAAR-PKG#107-MARASSI12
PK #107 | 1 | 13 | 2719252.37 | 0 | -2719252.37 | 3281572.56 | 0 | -3281572.56 |  |  |  | 2462800.95 | 2018-02-28 | 2018-03-10 | 2018-03-12 | 30 | 2018-04-11 | 2018-04-04 | 52257607.28 | 323504.14 | [5 empty] | 369537.93 | 2719252.37 | 52257607.28 | 2462800.95 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10713 | EMAAR-PKG#107-MARASSI13
PK #107 | 1 | 14 | 1449945.81 | 1449945.92 | 0.11 | 166316.41 | 2534475.77 | 2368159.36 |  |  |  | 166316.41 | 2018-03-31 | 2018-04-10 | 2018-04-11 | 30 | 2018-05-11 | 2018-04-29 | 53707553.09 | 0 | [5 empty] | 1275350.71 | 1449945.81 | 53707553.09 | 166316.41 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10714 | EMAAR-PKG#107-MARASSI14
PK #107 | 1 | 15 | 0 | 0 | 0 | 1406606.27 | 0 | -1406606.27 |  |  |  | 1406606.27 | 2018-04-30 | 2018-05-05 | 2018-05-06 | 30 | 2018-06-05 | 2018-05-23 | 53707553.09 | 0 | [5 empty] | 1275350.71 | 0 | 0 | 1406606.27 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10715 | EMAAR-PKG#107-MARASSI15
PK #107 | 1 | 16 | 0.01 | 0 | -0.01 | 131256.74 | 0 | -131256.74 |  |  |  | 131256.74 | 2018-05-31 | 2018-06-01 | 2018-05-30 | 30 | 2018-06-29 | 2018-06-28 | 53707553.1 | 0 | [5 empty] | 1292122.78 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10716 | EMAAR-PKG#107-MARASSI16
PK #107 | 1 | 17 | 0 | 0 | 0 | 763627.7 | 0 | -763627.7 |  |  |  | 763627.7 | 2018-09-30 | 2018-09-25 | 2018-09-25 | 30 | 2018-10-25 | 2018-10-21 | 53707553.1 | 0 | [5 empty] | 496495.08 | 0 | 0 | 763627.7 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10717 | EMAAR-PKG#107-MARASSI17
PK #107 | 1 | 18 | 989048.54 | 1069591.54 | 80543 | 1341459.14 | 1054265.617 | -287193.523 |  |  |  | 940988.93 | 2019-04-30 | 2019-04-25 | 2019-06-13 | 30 | 2019-07-13 | 2019-07-30 | 54696601.64 | [6 empty] | 1898258.43 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10718 | EMAAR-PKG#107-MARASSI18
PK #117 | 1 | 1 | 4130129.14 | 7803090.39 | 3672961.25 | 4130129.12 | 6865083.2495 | 2734954.1295 |  |  |  | 4130129.14 | 2017-12-31 | 2018-01-01 | 2018-01-18 | 30 | 2018-02-17 | 2018-02-13 | 4130129.14 | [6 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG117- MARASSI |  |  |  | PK #1171 | EMAAR-PKG117- MARASSI1
PK #117 | 1 | 2 | 7803090.39 | 0 | -7803090.39 | 6455421.01 | 0 | -6455421.01 |  |  |  | 6455421.01 | 2018-01-31 | 2018-02-15 | 2018-02-15 | 30 | 2018-03-17 | 2018-03-07 | 7803090.39 | 0 | [5 empty] | 60159.47 | 7803090.35 | 7803090.35 | 6466420.97 | EMAAR-PKG117- MARASSI |  |  |  | PK #1172 | EMAAR-PKG117- MARASSI2
PK #117 | 1 | 3 | 4332593.51 | 0 | -4332593.51 | 4502026.51 | 0 | -4502026.51 |  |  |  | 4502026.52 | 2018-02-28 | 2018-03-05 | 2018-03-07 | 30 | 2018-04-06 | 2018-03-29 | 12135683.86 | 1176749.78 | [5 empty] | 106021.19 | 4332593.51 | 12135683.86 | 4502026.52 | EMAAR-PKG117- MARASSI |  |  |  | PK #1173 | EMAAR-PKG117- MARASSI3
PK #117 | 1 | 4 | 4131277.1774 | 0 | -4131277.1774 | 3740180.08 | 0 | -3740180.08 |  |  |  | 3740180.271 | 2018-03-31 | 2018-04-01 | 2018-04-01 | 30 | 2018-05-01 | 2018-04-19 | 16266961.0374 | 1578005.405 | [5 empty] | 134455.7716 | 4131277.1774 | 16266961.0374 | 3740180.271 | EMAAR-PKG117- MARASSI |  |  |  | PK #1174 | EMAAR-PKG117- MARASSI4
PK #117 | 1 | 5 | 6909334.9826 | 6909335.09 | 0.10744 | 4762507.56 | 5093815.29 | 331307.73 |  |  |  | 4762507.55 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 30 | 2018-05-30 | 2018-05-22 | 23176296.02 | 364792.48 | [5 empty] | 171850.1 | 6909334.9826 | 23176296.02 | 4762507.55 | EMAAR-PKG117- MARASSI |  |  |  | PK #1175 | EMAAR-PKG117- MARASSI5
PK #117 | 1 | 6 | 6677875.24 | 6677875.14 | -0.1 | 5347404.79 | 5722280.397 | 374875.607 |  |  |  | 5347404.79 | 2018-05-31 | 2018-06-04 | 2018-06-05 | 30 | 2018-07-05 | 2018-07-12 | 29854171.26 | 229256.92 | [5 empty] | 302952.2979 | 6651333.71 | 29827629.73 | 5347404.79 | EMAAR-PKG117- MARASSI |  |  |  | PK #1176 | EMAAR-PKG117- MARASSI6
PK #117 | 1 | 7 | -0.01 | 0 | 0.01 | 118938.86 | 0 | -118938.86 |  |  |  | 119713.18 | 2018-06-30 | 2018-06-15 | 2018-06-25 | 30 | 2018-07-25 | 2018-12-30 | 29854171.25 | 384118.8 | [5 empty] | 115837.505 | -0.01 | 29854171.25 | 119713.18 | EMAAR-PKG117- MARASSI |  |  |  | PK #1177 | EMAAR-PKG117- MARASSI7
PK #117 | 1 | 8 | 4511257.49 | 0 | -4511257.49 | 3896343.98 | 0 | -3896343.98 |  |  |  | 3896343.98 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 30 | 2019-01-04 | 2018-12-30 | 34365428.74 | 79445.62 | [5 empty] | 575019.525 | 4511257.49 | 34365428.74 | 3896343.98 | EMAAR-PKG117- MARASSI |  |  |  | PK #1178 | EMAAR-PKG117- MARASSI8
PK #117 | 1 | 9 | 3153415.09 | 3150407.65 | -3007.44 | 2578109.73 | 2971025.94 | 392916.21 |  |  |  | 2578109.66 | 2018-12-31 | 2018-12-30 | 2018-12-29 | 30 | 2019-01-28 | 2019-01-30 | 37518843.83 | 48842.25 | [5 empty] | 599014.4 | 3153415.09 | 37518843.83 | 2578109.66 | EMAAR-PKG117- MARASSI |  |  |  | PK #1179 | EMAAR-PKG117- MARASSI9
PK #117 | 1 | 10 | 1068867.24 | 2201208.6 | 1132341.36 | 882296.11 | 1794005.32 | 911709.21 |  |  |  | 882296.18 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 30 | 2019-03-04 | 2019-02-28 | 38587711.07 | 48842.25 | [5 empty] | 653139.594 | 992195.9681 | 38511039.7981 | 147972.1048 | EMAAR-PKG117- MARASSI |  |  |  | PK #11710 | EMAAR-PKG117- MARASSI10
PK #117 | 1 | 11 | 1134851.86 | 0 | -1134851.86 | 809762.24 | 0 | -809762.24 |  |  |  | 810342.08 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-30 | 39722562.93 | [6 empty] | 737679.72 | 0 | 0 | 0 | EMAAR-PKG117- MARASSI |  |  |  | PK #11711 | EMAAR-PKG117- MARASSI11
PK #117 | 1 | 12 | 2921413.42 | 2921423.41 | 9.99 | 3376927.91 | 3430971.3805 | 54043.4705 |  |  |  | 3376348.1 | 2019-08-31 | 2019-08-26 | 2019-08-26 | 30 | 2019-09-25 | 2019-09-25 | 42643976.35 | 0 | [5 empty] | 1681581.22 | 2921413.42 | 42643976.35 | 3376348.1 | EMAAR-PKG117- MARASSI |  |  |  | PK #11712 | EMAAR-PKG117- MARASSI12
PK #117 | 1 | 13 | 2611652.87 | 2573072.88 | -38579.99 | 3145907.11 | 3439963.734 | 294056.624 |  |  |  | 3145779.21 | 2019-10-31 | 2019-10-30 | 2019-10-29 | 30 | 2019-11-28 | 2019-11-12 | 45255629.22 | 0 | [5 empty] | 975332.15 | 2611652.87 | 45255629.22 | 3145779.21 | EMAAR-PKG117- MARASSI |  |  |  | PK #11713 | EMAAR-PKG117- MARASSI13
PK #117 | 1 | 14 | 1659370.81 | 0 | -1659370.81 | 2483342.5 | 0 | -2483342.5 |  |  |  | 2238761.46 | 2020-04-30 | 2020-04-14 | 2020-06-24 | 30 | 2020-07-24 | 2020-09-27 | 46915000.03 | [6 empty] | 943850.91 | 1169069.6666 | 46915000.03 | 2238761.46 | EMAAR-PKG117- MARASSI |  |  |  | PK #11714 | EMAAR-PKG117- MARASSI14
PK#22 | 1 | 37 |  | 0 | 0 | 780036 | 0 | -780036 |  |  |  | 471641.26 | 2019-02-28 | 2019-02-27 | 2019-07-31 | 30 | 2019-08-30 | 2019-08-07 | 35147992.22 | [6 empty] | 990333.95 | 0 | 0 | 0 | EMAAR-PKG#22-MARASSI |  |  |  | PK#2237 | EMAAR-PKG#22-MARASSI37
PK#32 | 1 | 30 |  | 0 | 0 | 900093.35 | 0 | -900093.35 |  |  |  |  | 2017-06-30 | 2017-06-05 | 2022-03-14 | 30 | 2022-04-13 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PK#3230 | 030
PKG#101 | 1 | 1 | 1738465.6667 | 1738465.67 | 0.0033333 | 9752735.82 | 1029594.8135 | -8723141.0065 | 8723141 |  |  | 1029594.82 | 2019-01-31 | 2019-01-31 | 2019-02-03 | 40 | 2019-03-15 | 2019-02-17 | 1738465.6667 | [6 empty] | 48253.89 | 1738465.6667 | 1738465.6667 | 1124562.5468 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1011 | EMAAR-PKG# 101-UPTOWN1
PKG#101 | 1 | 2 | 1610908.8476 | 0 | -1610908.8476 | 2222206.65 | 0 | -2222206.65 |  |  |  | 2222206.65 | 2019-02-28 | 2019-02-28 | 2019-03-05 | 40 | 2019-04-14 | 2019-03-19 | 3349374.5143 | 2240156.84 | [5 empty] | 147570 | 1610908.8476 | 3349374.5143 | 2222206.65 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1012 | EMAAR-PKG# 101-UPTOWN2
PKG#101 | 1 | 3 | 4030400.2476 | 3744391.54 | -286008.7076 | 2246109.51 | 2222206.627 | -23902.883 |  |  |  | 2246109.51 | 2019-03-31 | 2019-04-11 | 2019-04-14 | 40 | 2019-05-24 | 2019-05-05 | 7379774.7619 | 1904790.84 | [5 empty] | 202283 | 4030395.5429 | 7379770.0571 | 2379437.34 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1013 | EMAAR-PKG# 101-UPTOWN3
PKG#101 | 1 | 4 | 4428897.7238 | 1896917.55 | -2531980.1738 | 2512749.68 | 2246109.51 | -266640.17 |  |  |  | 2512749.68 | 2019-04-30 | 2019-05-15 | 2019-05-20 | 40 | 2019-06-29 | 2019-05-29 | 11808672.4857 | 1592100.01 | [5 empty] | 250813.43 | 4428897.7238 | 11808672.4857 | 2512749.68 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1014 | EMAAR-PKG# 101-UPTOWN4
PKG#101 | 1 | 5 | 2224631.7143 | 4428897.72 | 2204266.0057 | 2051541.96 | 2512749.703 | 461207.743 |  |  |  | 2051541.96 | 2019-06-30 | 2019-06-30 | 2019-07-01 | 40 | 2019-08-10 | 2019-07-24 | 14033304.2 | 2808836.8 | [5 empty] | 296997.23 | 2224631.7143 | 14033304.2 | 2051541.96 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1015 | EMAAR-PKG# 101-UPTOWN5
PKG#101 | 1 | 6 | 3491880.8381 | 2226073.87 | -1265806.9681 | 1988552.05 | 2051541.97 | 62989.92 |  |  |  | 1988552.05 | 2019-07-31 | 2019-08-05 | 2019-08-07 | 40 | 2019-09-16 | 2019-08-28 | 17525185.0381 | 2620517.54 | [5 empty] | 362213.26 | 3491880.8381 | 17525185.0381 | 1988552.05 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1016 | EMAAR-PKG# 101-UPTOWN6
PKG#101 | 1 | 7 | 3123640.9905 | 3491880.84 | 368239.8495 | 1824097.57 | 1988552.05 | 164454.48 |  |  |  | 1824097.57 | 2019-08-31 | 2019-09-10 | 2019-09-15 | 40 | 2019-10-25 | 2019-09-26 | 20648826.0286 | 2373278.98 | [5 empty] | 374469.49 | 3120848.981 | 20646034.019 | 1794285.02 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1017 | EMAAR-PKG# 101-UPTOWN7
PKG#101 | 1 | 8 | 4704887.4039 | 3123640.99 | -1581246.4139 | 2104893.84 | 1824097.56 | -280796.28 |  |  |  | 2104893.8329 | 2019-09-30 | 2019-10-15 | 2019-10-17 | 40 | 2019-11-26 | 2019-11-05 | 25353713.4325 | 1078135.3004 | [5 empty] | 421854.3373 | 4703530.9524 | 25352356.981 | 2127121.14 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1018 | EMAAR-PKG# 101-UPTOWN8
PKG#101 | 1 | 9 | 3179849.8818 | 4704887.4 | 1525037.5182 | 1424816.56 | 2104893.84 | 680077.28 |  |  |  | 1424816.56 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 40 | 2019-12-27 | 2019-12-03 | 28533563.3143 | 297444.34 | [5 empty] | 505055.04 | 3179849.8818 | 28533563.3143 | 1424816.56 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1019 | EMAAR-PKG# 101-UPTOWN9
PKG#101 | 1 | 10 | 3100706.8857 | 0 | -3100706.8857 | 1976416.89 | 0 | -1976416.89 |  |  |  | 1976416.89 | 2019-11-30 | 2019-11-15 | 2019-12-18 | 40 | 2020-01-27 | 2020-01-06 | 31634270.2 | [6 empty] | 515167.31 | 3111780.0857 | 31645343.4 | 1948071.2 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10110 | EMAAR-PKG# 101-UPTOWN10
PKG#101 | 1 | 11 | 361420.4 | 3104755.66 | 2743335.26 | 1709961.04 | 1976416.883 | 266455.843 |  |  |  | 1709961.04 | 2020-01-31 | 2020-01-30 | 2020-02-08 | 40 | 2020-03-19 | 2020-02-27 | 31995690.6 | 2008107.01 | [5 empty] | 646968.58 | 382240.2571 | 32016510.4571 | 2026574.82 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10111 | EMAAR-PKG# 101-UPTOWN11
PKG#101 | 1 | 12 | 2584477.6667 | 361420.4 | -2223057.2667 | 1146998.21 | 1829340.96 | 682342.75 |  |  |  | 1146998.22 | 2020-02-29 | 2020-03-23 | 2020-03-24 | 40 | 2020-05-03 | 2020-04-08 | 34580168.2667 | 1288346.31 | [5 empty] | 677344.97 | 2584477.6667 | 34580168.2667 | 1146998.22 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10112 | EMAAR-PKG# 101-UPTOWN12
PKG#101 | 1 | 13 | 2595711.6476 | 2584477.67 | -11233.9776 | 1343055.6 | 1246695.2535 | -96360.3465 |  |  |  | 1407211.96 | 2020-03-31 | 2020-04-23 | 2020-04-23 | 40 | 2020-06-02 | 2020-05-04 | 37175879.9143 | 1005027.63 | [5 empty] | 712181.29 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10113 | EMAAR-PKG# 101-UPTOWN13
PKG#101 | 1 | 14 | 4659441.8571 | 2596223.72 | -2063218.1371 | 191421.72 | 1459609.626 | 1268187.906 |  |  |  | 191421.72 | 2020-06-30 | 2020-06-30 | 2020-07-12 | 40 | 2020-08-21 | 2020-09-09 | 41835321.7714 | [6 empty] | 763224.31 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10114 | EMAAR-PKG# 101-UPTOWN14
PKG#101 | 1 | 15 | 181866.4762 | 4658928.78 | 4477062.3038 | 303853.8 | 1268535.189 | 964681.389 |  |  |  | 303853.8 | 2020-09-30 | 2020-08-12 | 2020-12-09 | 40 | 2021-01-18 | 2021-01-20 | 42017188.2476 | [6 empty] | 174031.17 | 440607.3155 | 42275929.0869 | 1392185.4448 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10115 | EMAAR-PKG# 101-UPTOWN15
PKG#101 | 1 | 16 | 0.001 | 181866.48 | 181866.479 | 866491 | 1873125.774 | 1006634.774 |  |  |  | 866491.01 | 2020-09-30 | 2020-09-30 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-15 | 42017188.2476 | [6 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10116 | EMAAR-PKG# 101-UPTOWN16
PKG#101 | 1 | 17 | 0.001 | 0 | -0.001 | 3321316.23 | 0 | -3321316.23 |  |  |  | 3321316.23 | 2021-03-31 | 2021-04-05 | 2021-04-13 | 40 | 2021-05-23 | 2021-04-26 | 42017188.2476 | [6 empty] | 270662.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10117 | EMAAR-PKG# 101-UPTOWN17
PKG#101 | 1 | 18 | 1071378.1714 | 0 | -1071378.1714 | 1192690.23 | 0 | -1192690.23 |  |  |  | 1192690.23 | 2021-04-30 | 2021-04-05 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-05 | 43088566.419 | 949450.54 | [5 empty] | 275887.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10118 | EMAAR-PKG# 101-UPTOWN18
PKG#101 | 1 | 19 | 1322361.8352 | 1071378.16 | -250983.6752 | 596242.89 | 1296410.108 | 700167.218 |  |  |  | 596242.89 | 2021-04-30 | 2021-05-05 | 2021-05-17 | 40 | 2021-06-26 | 2021-06-03 | 44410928.2543 | 615651.133 | [5 empty] | 288697.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10119 | EMAAR-PKG# 101-UPTOWN19
PKG#101 | 1 | 20 | 952923.8886 | 1322361.65 | 369437.7614 | 759353.32 | 648976.9025 | -110376.4175 |  |  |  | 759353.31 | 2021-05-31 | 2021-06-05 | 2021-06-10 | 40 | 2021-07-20 | 2021-06-27 | 45363852.1429 | 505736.36 | [5 empty] | 238697.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10120 | EMAAR-PKG# 101-UPTOWN20
PKG#101 | 1 | 21 | 2547253.7048 | 952924.081 | -1594329.6238 | 1584188.58 | 803886.0851 | -780302.4949 |  |  |  | 1584188.57 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 40 | 2021-08-20 | 2021-08-09 | 47911105.8476 | 618555.37 | [5 empty] | 264186.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10121 | EMAAR-PKG# 101-UPTOWN21
PKG#101 | 1 | 22 | 2544618.2857 | 2547253.71 | 2635.4243 | 594123.32 | 1912651.7855 | 1318528.4655 |  |  |  | 594122.92 | 2021-08-31 | 2021-08-15 | 2021-09-20 | 40 | 2021-10-30 | 2021-10-12 | 50455724.1333 | 0 | [5 empty] | 299725.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10122 | EMAAR-PKG# 101-UPTOWN22
PKG#101 | 1 | 23 |  | 2544618.3 | 2544618.3 | 189091.52 | 594123.335 | 405031.815 |  |  |  |  | 2022-04-30 | 2022-04-10 | 2022-04-21 | 40 | 2022-05-31 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10123 | EMAAR-PKG# 101-UPTOWN23
PKG#101 | 1 | 24 |  | 270197.08 | 270197.08 | 546994.62 | 546994.614 | -0.006 |  |  |  |  | 2022-04-30 | 2022-04-10 | 2023-03-27 | 40 | 2023-05-06 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10124 | EMAAR-PKG# 101-UPTOWN24
PKG#144 | 1 | 2 | 4125990.87 | 4125990.87 | 0 | 2532120.6 | 2748735.1235 | 216614.5235 |  |  |  | 2532120.6 | 2018-12-31 | 2018-12-26 | 2018-12-26 | 30 | 2019-01-25 | 2019-01-20 | 4125990.87 | [6 empty] | 25993.74 | 4125990.87 | 4125990.87 | 2532120.6 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1442 | EMAAR-PKG# 144, Marassi2
PKG#144 | 1 | 3 | 6872046.13 | 6872046.63 | 0.5 | 6189125.05 | 6189125.0415 | -0.0085 |  |  |  | 6190737.99 | 2019-01-31 | 2019-01-30 | 2019-01-31 | 30 | 2019-03-02 | 2019-02-20 | 10998037 | 3387217.5 | [5 empty] | 95995.9412 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1443 | EMAAR-PKG# 144, Marassi3
PKG#144 | 1 | 4 | 11224614.67 | 11222644.64 | -1970.03 | 6887337.01 | 6887337.022 | 0.012 |  |  |  | 6888545.72 | 2019-02-28 | 2019-02-27 | 2019-02-27 | 30 | 2019-03-29 | 2019-03-11 | 22222651.67 | 3387217.5 | [5 empty] | 166711.01 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1444 | EMAAR-PKG# 144, Marassi4
PKG#144 | 1 | 5 | 0 | 0 | 0 | 7206339.73 | 0 | -7206339.73 |  |  |  | 7206339.73 | 2019-02-28 | 2019-03-11 | 2019-03-11 | 30 | 2019-04-10 | 2019-03-11 | 22222651.67 | 3387217.5 | [5 empty] | 166711.64 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1445 | EMAAR-PKG# 144, Marassi5
PKG#144 | 1 | 6 | 24444079.39 | 24446048.93 | 1969.54 | 14929468.44 | 14929446.3565 | -22.0835 |  |  |  | 14801921.82 | 2019-03-31 | 2019-03-14 | 2019-03-14 | 30 | 2019-04-13 | 2019-03-21 | 46666731.06 | 3262056.75 | [5 empty] | 319957.75 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1446 | EMAAR-PKG# 144, Marassi6
PKG#144 | 1 | 7 | 20465525.6228 | 20465525.62 | -0.0027857 | 12477244.23 | 12627238.511 | 149994.281 |  |  |  | 12603636.3289 | 2019-03-31 | 2019-03-30 | 2019-03-30 | 30 | 2019-04-29 | 2019-04-11 | 67132256.6828 | 3501000 | [5 empty] | 672293.8257 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1447 | EMAAR-PKG# 144, Marassi7
PKG#144 | 1 | 8 | 16379645.0372 | 16360599.32 | -19045.7172 | 8906660.63 | 8934848.896 | 28188.266 |  |  |  | 8909777.64 | 2019-04-30 | 2019-04-15 | 2019-04-15 | 30 | 2019-05-15 | 2019-05-04 | 83511901.72 | 0 | [5 empty] | 795592.47 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1448 | EMAAR-PKG# 144, Marassi8
PKG#144 | 1 | 9 | 10281327.2057 | 10299181.31 | 17854.1043 | 9782161.34 | 9830068.4255 | 47907.0855 |  |  |  | 9777923.5506 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 30 | 2019-06-04 | 2019-05-15 | 93793228.9257 | 816900 | [5 empty] | 900089.7717 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1449 | EMAAR-PKG# 144, Marassi9
PKG#144 | 1 | 10 | 13881511.5343 | 13884342.32 | 2830.7857 | 11074114.43 | 11330349.466 | 256235.036 |  |  |  | 11184527.72 | 2019-05-31 | 2019-05-20 | 2019-05-20 | 30 | 2019-06-19 | 2019-05-30 | 107674740.46 | [6 empty] | 1113537.73 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14410 | EMAAR-PKG# 144, Marassi10
PKG#144 | 1 | 11 | 9087190.46 | 8979474.51 | -107715.95 | 7386054.95 | 7386054.95 | 0 |  |  |  | 7486833.97 | 2019-06-30 | 2019-06-20 | 2019-06-18 | 30 | 2019-07-18 | 2019-07-11 | 116761930.92 | 0 | [5 empty] | 1199420.77 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14411 | EMAAR-PKG# 144, Marassi11
PKG#144 | 1 | 12 | 34717376.42 | 34831219.06 | 113842.64 | 21073691.31 | 32281831.2825 | 11208139.9725 |  |  |  | 22411649.36 | 2019-08-31 | 2019-09-05 | 2019-09-04 | 30 | 2019-10-04 | 2019-10-03 | 151479307.34 | [6 empty] | 8633180.89 | 34717376.42 | 151479307.34 | 22411649.36 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14412 | EMAAR-PKG# 144, Marassi12
PKG#144 | 1 | 13 | 11410387.23 | 0 | -11410387.23 | 14000000 | 0 | -14000000 |  |  |  | 14635108.89 | 2019-12-31 | 2019-12-25 | 2019-12-25 | 30 | 2020-01-24 | 2020-01-22 | 162889694.57 | [6 empty] | 9246101.93 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14413 | EMAAR-PKG# 144, Marassi13
PKG#144 | 1 | 14 | 10733689.1131 | 10733689.11 | -0.0031386 | 10173240.83 | 10786798.0055 | 613557.1755 |  |  |  | 10377806.9192 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 30 | 2020-03-04 | 2020-02-19 | 173623383.6831 | [6 empty] | 8262612.0833 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14414 | EMAAR-PKG# 144, Marassi14
PKG#144 | 1 | 15 | 2638692.2969 | 2638692.38 | 0.083139 | 9960243.27 | 5968624.239 | -3991619.031 |  |  |  | 10405304.53 | 2020-08-31 | 2020-08-20 | 2020-12-13 | 30 | 2021-01-12 | 2020-12-13 | 176262075.98 | [6 empty] | 2614017.44 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14415 | EMAAR-PKG# 144, Marassi15
PKG#144 | 1 | 16 | 150533.34 | 0 | -150533.34 | 1116473.97 | 0 | -1116473.97 |  |  |  | 1132971.99 | 2021-01-31 | 2021-01-20 | 2021-01-21 | 30 | 2021-02-20 | 2021-03-25 | 176412609.32 | [6 empty] | 2496617.44 | 150533.34 | 176412609.32 | 1132971.99 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14416 | EMAAR-PKG# 144, Marassi16
PKG#162 | 1 | 2 | 8785941.99 | 17264889.03 | 8478947.04 | 7794726.52 | 17974031.2815 | 10179304.7615 |  |  |  | 7794726.52 | 2020-02-29 | 2020-02-29 | 2020-03-05 | 40 | 2020-04-14 | 2020-03-22 | 8785941.99 | 749579.79 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1622 | EMAAR-Pkg#162/163- Marassi2
PKG#162 | 1 | 3 | 6446622.36 | 12082357.79 | 5635735.43 | 5119599.34 | 16268974.4395 | 11149375.0995 |  |  |  | 5119599.35 | 2020-03-31 | 2020-03-18 | 2020-03-21 | 40 | 2020-04-30 | 2020-03-30 | 15232564.35 | 531683.98 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1623 | EMAAR-Pkg#162/163- Marassi3
PKG#162 | 1 | 4 | 7314177.64 | 14694850.77 | 7380673.13 | 6336538.23 | 17742432.8485 | 11405894.6185 |  |  |  | 6336538.23 | 2020-03-31 | 2020-04-06 | 2020-04-06 | 40 | 2020-05-16 | 2020-04-22 | 22546741.99 | 1033463.45 | [5 empty] | 57000 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1624 | EMAAR-Pkg#162/163- Marassi4
PKG#162 | 1 | 5 | 8006098.57 | 8006098.571 | 0.001 | 6124877.69 | 7958142.0485 | 1833264.3585 |  |  |  | 6124877.69 | 2020-04-30 | 2020-05-05 | 2020-05-04 | 40 | 2020-06-13 | 2020-05-13 | 30552840.56 | 592328.38 | [5 empty] | 157000 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1625 | EMAAR-Pkg#162/163- Marassi5
PKG#162 | 1 | 6 | 5990865.4963 | 14622817.211 | 8631951.7147 | 4824045.39 | 13427541.4454 | 8603496.0554 |  |  |  | 4824045.381 | 2020-05-31 | 2020-06-06 | 2020-06-10 | 40 | 2020-07-20 | 2020-06-26 | 36543706.0563 | 474838.875 | [5 empty] | 157000 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1626 | EMAAR-Pkg#162/163- Marassi6
PKG#162 | 1 | 7 | 8577628.8704 | 12998247.66 | 4420618.7896 | 7215874.2121 | 12964361.5377 | 5748487.3256 |  |  |  | 7215874.2121 | 2020-06-30 | 2020-07-06 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-29 | 45121334.9266 | 834531.375 | [5 empty] | 260419 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1627 | EMAAR-Pkg#162/163- Marassi7
PKG#162 | 1 | 8 | 12161063.3859 | 27347974.52 | 15186911.1341 | 9432027.72 | 22259454.996 | 12827427.276 |  |  |  | 9432027.7177 | 2020-07-31 | 2020-08-10 | 2020-08-16 | 40 | 2020-09-25 | 2020-09-03 | 57282398.3125 | 136265.25 | [5 empty] | 261806 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1628 | EMAAR-Pkg#162/163- Marassi8
PKG#162 | 1 | 9 | 10973106.5017 | 15911837.121 | 4938730.6193 | 9889305 | 20607532.6031 | 10718227.6031 |  |  |  | 9889305.1266 | 2020-08-31 | 2020-09-05 | 2020-09-09 | 40 | 2020-10-19 | 2020-09-28 | 68255504.8142 | 1100385 | [5 empty] | 61806 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1629 | EMAAR-Pkg#162/163- Marassi9
PKG#162 | 1 | 10 | 14493217.0374 | 18387668.6001 | 3894451.5627 | 13282474.2108 | 18192775.4801 | 4910301.2693 |  |  |  | 13282474.2108 | 2020-09-30 | 2020-10-05 | 2020-10-07 | 40 | 2020-11-16 | 2020-11-03 | 82748721.8517 | 1005156.4395 | [5 empty] | 61806 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16210 | EMAAR-Pkg#162/163- Marassi10
PKG#162 | 1 | 11 | 9303551.5202 | 13136177.8201 | 3832626.2999 | 7840185.48 | 13368148.5779 | 5527963.0979 |  |  |  | 7840185.4913 | 2020-10-31 | 2020-11-05 | 2020-11-05 | 40 | 2020-12-15 | 2020-12-02 | 92052273.3719 | [6 empty] | 93807 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16211 | EMAAR-Pkg#162/163- Marassi11
PKG#162 | 1 | 12 | 7499598.7681 | 28306050.31 | 20806451.5419 | 4608392 | 21347264.7774 | 16738872.7774 |  |  |  | 4608392 | 2020-11-30 | 2020-12-01 | 2020-12-13 | 40 | 2021-01-22 | 2021-02-02 | 99551872.14 | 0 | [5 empty] | 2426668.64 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16212 | EMAAR-Pkg#162/163- Marassi12
PKG#162 | 1 | 13 | 709528.8141 | 7085309.261 | 6375780.4469 | 3429815.246 | 16955957.474 | 13526142.228 |  |  |  | 3429815.246 | 2020-12-31 | 2021-01-01 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-09 | 100261400.9541 | [6 empty] | 2376668.64 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16213 | EMAAR-Pkg#162/163- Marassi13
PKG#162 | 1 | 14 | -0.004055 | 13281620.941 | 13281620.9451 | 502581.43 | 15373453.508 | 14870872.078 |  |  |  | 502581.44 | 2021-01-31 | 2021-02-01 | 2021-02-03 | 40 | 2021-03-15 | 2021-02-24 | 100261400.95 | [6 empty] | 1926668.64 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16214 | EMAAR-Pkg#162/163- Marassi14
PKG#162 | 1 | 15 | 0.05 | 7388288.7 | 7388288.65 | 3999402.59 | 4317541.565 | 318138.975 |  |  |  | 3683579.28 | 2021-01-31 | 2021-02-01 | 2021-11-18 | 40 | 2021-12-28 | 2022-03-07 | 100261401 | [6 empty] | 926668 | 0.01 | 100261400.96 | 3683579.28 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16215 | EMAAR-Pkg#162/163- Marassi15
PKG#163 | 1 | 2 | 167514.17 | 17264889.03 | 17097374.86 | 1068966.43 | 17974031.2815 | 16905064.8515 |  |  |  | 1068966.43 | 2020-06-30 | 2020-07-07 | 2020-07-07 | 40 | 2020-08-16 | 2020-07-22 | 167514.17 | 1392714.35 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1632 | EMAAR-Pkg#162/163- Marassi2
PKG#163 | 1 | 3 | 1873525.03 | 12082357.79 | 10208832.76 | 2977091.11 | 16268974.4395 | 13291883.3295 |  |  |  | 2977091.11 | 2020-07-31 | 2020-08-10 | 2020-08-18 | 40 | 2020-09-27 | 2020-08-26 | 2041039.2 | 3794104.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1633 | EMAAR-Pkg#162/163- Marassi3
PKG#163 | 1 | 4 | 3480646.03 | 14694850.77 | 11214204.74 | 6845695.77 | 17742432.8485 | 10896737.0785 |  |  |  | 6845695.77 | 2020-08-31 | 2020-09-03 | 2020-09-03 | 40 | 2020-10-13 | 2020-09-23 | 5521685.23 | 10183594.03 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1634 | EMAAR-Pkg#162/163- Marassi4
PKG#163 | 1 | 5 | 3896848.6915 | 8006098.571 | 4109249.8795 | 3782501.29 | 7958142.0485 | 4175640.7585 |  |  |  | 3782501.2803 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 40 | 2020-11-09 | 2020-10-22 | 9418533.9215 | 11640240.8375 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1635 | EMAAR-Pkg#162/163- Marassi5
PKG#163 | 1 | 6 | 8635132.0099 | 14622817.211 | 5987685.2011 | 6255172.17 | 13427541.4454 | 7172369.2754 |  |  |  | 6255172.4375 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 40 | 2020-12-13 | 2020-11-29 | 18053665.9314 | 11614831.0892 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1636 | EMAAR-Pkg#162/163- Marassi6
PKG#163 | 1 | 7 | 4420616.8286 | 12998247.66 | 8577630.8314 | 4922193.5 | 12964361.5377 | 8042168.0377 |  |  |  | 4922193.5 | 2020-11-30 | 2020-12-07 | 2020-12-08 | 40 | 2021-01-17 | 2020-12-23 | 22474282.76 | 14196023.04 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1637 | EMAAR-Pkg#162/163- Marassi7
PKG#163 | 1 | 8 | 7415396.32 | 27347974.52 | 19932578.2 | 6050639.77 | 22259454.996 | 16208815.226 |  |  |  | 6050639.7742 | 2020-12-31 | 2021-01-05 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-02 | 29889679.08 | 15239713.55 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1638 | EMAAR-Pkg#162/163- Marassi8
PKG#163 | 1 | 9 | 5020188.6174 | 15911837.121 | 10891648.5036 | 4602212.16 | 20607532.6031 | 16005320.4431 |  |  |  | 4602212.1569 | 2021-01-31 | 2021-01-25 | 2021-02-25 | 40 | 2021-04-06 | 2021-03-08 | 34909867.6974 | 16642238.4803 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1639 | EMAAR-Pkg#162/163- Marassi9
PKG#163 | 1 | 10 | 3812993.5626 | 18387668.6001 | 14574675.0375 | 2532838.57 | 18192775.4801 | 15659936.9101 |  |  |  | 2532838.57 | 2021-02-28 | 2021-02-25 | 2021-03-03 | 40 | 2021-04-12 | 2021-10-23 | 38722861.26 | 16355289.4 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16310 | EMAAR-Pkg#162/163- Marassi10
PKG#163 | 1 | 11 | 3832626.3 | 13136177.8201 | 9303551.5201 | 3799097.57 | 13368148.5779 | 9569051.0079 |  |  |  | 3799097.57 | 2021-03-31 | 2021-03-25 | 2021-03-31 | 40 | 2021-05-10 | 2021-04-25 | 42555487.56 | 17842244.91 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16311 | EMAAR-Pkg#162/163- Marassi11
PKG#163 | 1 | 12 | 3268183.05 | 28306050.31 | 25037867.26 | 2215480.09 | 21347264.7774 | 19131784.6874 |  |  |  | 2215480.09 | 2021-04-30 | 2021-04-25 | 2021-05-04 | 40 | 2021-06-13 | 2021-06-03 | 45823670.61 | 17661654.17 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16312 | EMAAR-Pkg#162/163- Marassi12
PKG#163 | 1 | 13 | 6375780.44 | 7085309.261 | 709528.821 | 3821253.39 | 16955957.474 | 13134704.084 |  |  |  | 3821253.39 | 2021-05-31 | 2021-05-25 | 2021-05-31 | 40 | 2021-07-10 | 2021-06-21 | 52199451.05 | 16405178.95 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16313 | EMAAR-Pkg#162/163- Marassi13
PKG#163 | 1 | 14 | 13281620.95 | 13281620.941 | -0.009 | 10697999.42 | 15373453.508 | 4675454.088 |  |  |  | 10697999.42 | 2021-06-30 | 2021-06-26 | 2021-07-01 | 40 | 2021-08-10 | 2021-08-02 | 65481072 | 18157750.16 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16314 | EMAAR-Pkg#162/163- Marassi14
PKG#163 | 1 | 15 | 7388288.7 | 7388288.7 | 1.2107e-08 | 4024676.65 | 4317541.565 | 292864.915 |  |  |  | 4024675.65 | 2021-07-31 | 2021-07-25 | 2021-08-02 | 40 | 2021-09-11 | 2021-08-26 | 72869360.7 | 16257345.38 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16315 | EMAAR-Pkg#162/163- Marassi15
PKG#163 | 1 | 16 | 6043601.4 | 55287937 | 49244335.6 | 3611195.74 | 15368075.701 | 11756879.961 |  |  |  | 3611195.73 | 2021-08-31 | 2021-08-25 | 2021-09-06 | 40 | 2021-10-16 | 2021-09-30 | 78912962.1 | 15138470.41 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16316 | EMAAR-Pkg#162/163- Marassi16
PKG#163 | 1 | 17 | 5496981.8 | 5496981.8001 | 9.9988e-05 | 2445757.34 | 2956365.1601 | 510607.8201 |  |  |  | 2445757.34 | 2021-09-30 | 2021-09-25 | 2021-10-03 | 40 | 2021-11-12 | 2021-10-27 | 84409943.9 | 12955550.43 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16317 | EMAAR-Pkg#162/163- Marassi17
PKG#163 | 1 | 18 | 3301294.98 | 16225112.87 | 12923817.89 | 2445757.34 | 19270685.5835 | 16824928.2435 |  |  |  | 3026069.35 | 2021-10-31 | 2021-10-25 | 2021-11-01 | 40 | 2021-12-11 | 2021-11-15 | 87711238.88 | 13929653.03 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16318 | EMAAR-Pkg#162/163- Marassi18
PKG#163 | 1 | 19 | 9320216.47 | 9320216.4901 | 0.0201 | 6520369.14 | 15003262.3046 | 8482893.1646 |  |  |  | 7895027.24 | 2021-11-30 | 2021-11-25 | 2021-11-30 | 40 | 2022-01-09 | 2021-12-16 | 97031455.35 | 15728609.99 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16319 | EMAAR-Pkg#162/163- Marassi19
PKG#163 | 1 | 20 | 4346059.97 | 14793463.46 | 10447403.49 | 3715617.2 | 10622091.773 | 6906474.573 |  |  |  | 2340959.11 | 2021-12-31 | 2021-12-25 | 2022-01-02 | 40 | 2022-02-11 | 2022-01-19 | 101377515.32 | 14609274.92 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16320 | EMAAR-Pkg#162/163- Marassi20
PKG#163 | 1 | 21 | 5919076.73 | 16895262.31 | 10976185.58 | 5322260.63 | 11574799.0555 | 6252538.4255 |  |  |  | 5322260.63 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 40 | 2022-03-15 | 2022-03-17 | 107296592.05 | 15284733.68 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16321 | EMAAR-Pkg#162/163- Marassi21
PKG#163 | 1 | 22 | 2632588.63 | 10221216.4 | 7588627.77 | 2261775.79 | 6046552.498 | 3784776.708 |  |  |  | 2261775.79 | 2022-02-28 | 2022-02-28 | 2022-03-01 | 40 | 2022-04-10 | 2022-03-23 | 109929180.68 | 15087666.62 |  |  |  | 3262202.645 | 3262202.645 | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16322 | EMAAR-Pkg#162/163- Marassi22
PKG#163 | 1 | 23 | 6399693.2 | 11084383.47 | 4684690.27 | 3449740.5053 | 8263496.6735 | 4813756.1682 |  |  |  | 3449740.51 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 40 | 2022-05-17 | 2022-09-06 | 116328873.88 | 12447737.11 |  |  |  | 3363997.5 | 3363997.5 | 139451 | 0 | 0 | 3449740.5053 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16323 | EMAAR-Pkg#162/163- Marassi23
PKG#163 | 1 | 24 | 6669347.19 | 12620775.22 | 5951428.03 | 5681606.5237 | 11118548.566 | 5436942.0423 |  |  |  | 5681606.52 | 2022-04-30 | 2022-04-20 | 2022-04-28 | 40 | 2022-06-07 | 2022-09-06 | 122998221.07 | 11928679.08 | 79159509 |  | 106910.74 | 3526010 | 3526010 | 170264.36 | 5789760.2558 | 115718940.9358 | 5681606.5237 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16324 | EMAAR-Pkg#162/163- Marassi24
PKG#163 | 1 | 25 | 12929046.56 | 16552264.24 | 3623217.68 | 11730565.831 | 16704168.777 | 4973602.946 |  |  |  | 11730565.83 | 2022-05-31 | 2022-05-25 | 2022-06-02 | 40 | 2022-07-12 | 2022-09-06 | 135927267.63 | 11655699.31 | 84070405.07 |  | 214226.97 | 3858707 | 3858707 | 170264.36 | 22617186.6357 | 145615407.7057 | 11730565.831 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16325 | EMAAR-Pkg#162/163- Marassi25
PKG#163 | 1 | 26 | 6526578.31 | 7856344.54 | 1329766.23 | 6014332.37 | 8378952.377 | 2364620.007 |  |  |  | 6014332.37 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 40 | 2022-08-14 | 2022-09-19 | 142453845.94 | 11222354.42 | 87095709.46 |  | 214226.97 | 4019196.11 | 4019196.11 | 170264 | 20328767.6537 | 156256035.2837 | 8194504.6617 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16326 | EMAAR-Pkg#162/163- Marassi26
PKG#163 | 1 | 27 | 4132634.87 | 4132634.87 | 2.5146e-08 | 3457484.33 | 3653603.3235 | 196118.9935 |  |  |  | 3457484.33 | 2022-07-31 | 2022-07-31 | 2022-08-09 | 40 | 2022-09-18 | 2022-09-25 | 146586480.81 | 10805467.52 | 88908671.92 |  | 214226.97 | 4117255.5 | 4117255.5 | 170264 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16327 | EMAAR-Pkg#162/163- Marassi27
PKG#163 | 1 | 28 | 17622733.92 | 22582028.69 | 4959294.77 | 18331730.1 | 23295212.1945 | 4963482.0945 |  |  |  | 18331730.1 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 40 | 2022-10-22 | 2022-11-10 | 164209214.73 | 13098222.27 | 70785988.93 |  | 693580.47 | 4637171.235 | 4637171.235 | 0 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16328 | EMAAR-Pkg#162/163- Marassi28
PKG#163 | 1 | 29 | 20296742.22 | 20296742.21 | -0.01 | 18785649.76 | 19850779.098 | 1065129.338 |  |  |  | 18785649.76 | 2022-09-30 | 2022-09-30 | 2022-10-20 | 40 | 2022-11-29 | 2023-01-15 | 184505956.95 | 13098222.27 | 159762353.93 |  | 693580.47 | 5169960.72 | 5169960.72 | 170264.36 | 17622733.92 | 181831948.65 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16329 | EMAAR-Pkg#162/163- Marassi29
PKG#163 | 1 | 30 | 8788912.25 | 27617784.67 | 18828872.42 | 3193802.31 | 15359271.0135 | 12165468.7035 |  |  |  | 3193802.31 | 2023-01-31 | 2023-01-18 | 2023-01-18 | 40 | 2023-02-27 | 2023-08-09 | 193294869.2 | 8080616.05 | 66836818.15 |  | 624222.43 | 5275229.5 | 5275229.5 | 688139.36 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16330 | EMAAR-Pkg#162/163- Marassi30
PKG#163 | 1 | 31 | -406906.47 | 10357799.14 | 10764705.61 | 1079324.09 | 10109132.947 | 9029808.857 |  |  |  | 1079324.1 | 2023-02-28 | 2023-02-28 | 2023-03-15 | 40 | 2023-04-24 | 2023-08-09 | 192887962.73 | 9732318.5 | 56933789.25 |  | 1100688.83 | 5305840.78 | 5305840.78 | 688139.36 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16331 | EMAAR-Pkg#162/163- Marassi31
PKG#163 | 1 | 32 | 5753296.48 | 11583000.46 | 5829703.98 | 4562478.02 | 15273972.9335 | 10711494.9135 |  |  |  | 4562478.01 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 40 | 2023-06-23 | 2023-12-13 | 198641259.21 | 8867308.69 | 66948753.43 |  | 1100688.83 | 5435239.565 | 5435239.565 | 688139.36 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16332 | EMAAR-Pkg#162/163- Marassi32
PKG#163 | 1 | 33 |  | 4083110.28 | 4083110.28 | 0.0001 | 3354959.084 | 3354959.0839 |  |  |  | 5000000 | 2023-05-31 | 2023-05-31 | 2023-06-11 | 40 | 2023-07-21 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16333 | EMAAR-Pkg#162/163- Marassi33
PKG#163 | 1 | 34 |  | 0 | 0 | 0.0001 | 0 | -0.0001 |  |  |  | 5000000 | 2023-06-30 | 2023-07-10 | 2023-07-13 | 40 | 2023-08-22 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16334 | EMAAR-Pkg#162/163- Marassi34
PKG#163 | 1 | 35 |  | 20620247.8 | 20620247.8 | 0.0001 | 15928851.3665 | 15928851.3664 |  |  |  | 5000000 | 2023-10-31 | 2023-11-14 | 2023-11-15 | 40 | 2023-12-25 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16335 | EMAAR-Pkg#162/163- Marassi35
PKG#163 | 1 | 36 |  | 42116952.2 | 42116952.2 | 0 | 36331150.12 | 36331150.12 |  |  |  | 10852799 | 2024-05-31 | 2024-05-21 | 2024-05-26 | 40 | 2024-07-05 |  | 221749507 | [6 empty] | 0 | 0 | 0 | 10852799 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16336 | EMAAR-Pkg#162/163- Marassi36
PKG#177 | 1 | 2 | 8478947.03 | 17264889.03 | 8785942 | 10240448.36 | 17974031.2815 | 7733582.9215 |  |  |  | 10240448.36 | 2021-04-30 | 2021-04-30 | 2021-04-26 | 30 | 2021-05-26 | 2021-05-12 | 8478947.03 | 4144486.18 | [5 empty] | 16912.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1772 | EMAAR-Pkg#162/163- Marassi2
PKG#177 | 1 | 3 | 9.9998e-05 | 12082357.79 | 12082357.7899 | 3893019.54 | 16268974.4395 | 12375954.8995 |  |  |  | 3893019.54 | 2021-04-30 | 2021-04-25 | 2021-05-05 | 30 | 2021-06-04 | 2021-05-26 | 8478947.03 | 9209962.12 | [5 empty] | 16912.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1773 | EMAAR-Pkg#162/163- Marassi3
PKG#177 | 1 | 4 | 5088605.14 | 14694850.77 | 9606245.63 | 14139690.65 | 17742432.8485 | 3602742.1985 |  | 10000000 |  | 4135304.94 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 30 | 2021-06-09 | 2021-05-27 | 13567552.17 | 9209962.12 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1774 | EMAAR-Pkg#162/163- Marassi4
PKG#177 | 1 | 5 | 0.0001 | 8006098.571 | 8006098.5709 | 11890262.73 | 7958142.0485 | -3932120.6815 |  | 10000000 |  | 1889110.9 | 2021-05-31 | 2021-05-25 | 2021-05-26 | 30 | 2021-06-25 | 2021-06-03 | 13567552.17 | 11628798.1 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1775 | EMAAR-Pkg#162/163- Marassi5
PKG#177 | 1 | 6 | 0.0001 | 14622817.211 | 14622817.2109 | 12069539.45 | 13427541.4454 | 1358001.9954 |  | 10000000 |  | 2069539.45 | 2021-05-31 | 2021-05-25 | 2021-05-30 | 30 | 2021-06-29 | 2021-06-21 | 13567552.17 | 14278656.55 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1776 | EMAAR-Pkg#162/163- Marassi6
PKG#177 | 1 | 7 | 0.0001 | 12998247.66 | 12998247.6599 | 40000000 | 12964361.5377 | -27035638.4623 |  | 10000000 |  | 30000000 | 2021-05-31 | 2021-05-25 | 2021-06-02 | 30 | 2021-07-02 | 2021-06-21 | 13567552.17 | 14278656.55 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1777 | EMAAR-Pkg#162/163- Marassi7
PKG#177 | 1 | 8 | 7777231.12 | 27347974.52 | 19570743.4 | 16325726.09 | 22259454.996 | 5933728.906 |  | 10000000 |  | 6324855.08 | 2021-05-31 | 2021-05-25 | 2021-06-06 | 30 | 2021-07-06 | 2021-06-21 | 21344783.29 | 14212069.8 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1778 | EMAAR-Pkg#162/163- Marassi8
PKG#177 | 1 | 9 | 0.0001 | 15911837.121 | 15911837.1209 | 11386804.78 | 20607532.6031 | 9220727.8231 |  | 10000000 |  | 1386804.78 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 30 | 2021-07-09 | 2021-06-21 | 21344783.29 | 15987748.13 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1779 | EMAAR-Pkg#162/163- Marassi9
PKG#177 | 1 | 10 | 9.9996e-05 | 18387668.6001 | 18387668.6 | 11031892.42 | 18192775.4801 | 7160883.0601 |  | 10000000 |  | 1030274.11 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 21344783.29 | 17306921.13 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17710 | EMAAR-Pkg#162/163- Marassi10
PKG#177 | 1 | 11 | 0.00010001 | 13136177.8201 | 13136177.82 | 11623911.78 | 13368148.5779 | 1744236.7979 |  | 10000000 |  | 1623911.78 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 21344783.29 | 19386193.57 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17711 | EMAAR-Pkg#162/163- Marassi11
PKG#177 | 1 | 12 | 17543747.3405 | 28306050.31 | 10762302.9695 | 11867471.98 | 21347264.7774 | 9479792.7974 |  |  |  | 11864115.6307 | 2021-05-31 | 2021-06-10 | 2021-06-17 | 30 | 2021-07-17 | 2021-07-08 | 38888530.6305 | 16150782.833 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17712 | EMAAR-Pkg#162/163- Marassi12
PKG#177 | 1 | 13 | -0.0001 | 7085309.261 | 7085309.2611 | 4287396.18 | 16955957.474 | 12668561.294 |  |  |  | 4287396.18 | 2021-05-31 | 2021-06-10 | 2021-06-24 | 30 | 2021-07-24 | 2021-07-08 | 38888530.6305 | 21640406.623 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17713 | EMAAR-Pkg#162/163- Marassi13
PKG#177 | 1 | 14 | -0.0006304 | 13281620.941 | 13281620.9416 | 3654358.5 | 15373453.508 | 11719095.008 |  |  |  | 3654358.5 | 2021-06-30 | 2021-07-10 | 2021-07-07 | 30 | 2021-08-06 | 2021-07-08 | 38888530.63 | 26319482.8 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17714 | EMAAR-Pkg#162/163- Marassi14
PKG#177 | 1 | 15 | 0.00043038 | 7388288.7 | 7388288.6996 | 30000000 | 4317541.565 | -25682458.435 |  |  |  | 30000000 | 2021-06-30 | 2021-07-10 | 2021-07-11 | 30 | 2021-08-10 | 2021-07-15 | 38888530.6305 | 26319482.803 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17715 | EMAAR-Pkg#162/163- Marassi15
PKG#177 | 1 | 16 | 49248459.9349 | 55287937 | 6039477.0651 | 8978914.16 | 15368075.701 | 6389161.541 |  |  |  | 8979568.5092 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 30 | 2021-08-14 | 2021-08-08 | 88136990.5654 | 24945340.303 | [5 empty] | 415112.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17716 | EMAAR-Pkg#162/163- Marassi16
PKG#177 | 1 | 17 | 0.0045094 | 5496981.8001 | 5496981.7956 | 311248.17 | 2956365.1601 | 2645116.9901 |  |  |  | 311058.51 | 2021-06-30 | 2021-07-10 | 2021-07-28 | 30 | 2021-08-27 | 2021-08-10 | 88136990.57 | 25343622.64 | [5 empty] | 415112.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17717 | EMAAR-Pkg#162/163- Marassi17
PKG#177 | 1 | 18 | 12925810.52 | 16225112.87 | 3299302.35 | 15059090.32 | 19270685.5835 | 4211595.2635 |  |  |  | 15056356.09 | 2021-06-30 | 2021-07-10 | 2021-08-02 | 30 | 2021-09-01 | 2021-09-02 | 101062801.09 | 31043670.3 | [5 empty] | 415112.5 | 12925810.52 | 101062801.09 | 15056356.09 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17718 | EMAAR-Pkg#162/163- Marassi18
PKG#177 | 1 | 19 | -0.0001 | 9320216.4901 | 9320216.4902 | 6143418.31 | 15003262.3046 | 8859843.9946 |  |  |  | 6139746.33 | 2021-07-31 | 2021-07-25 | 2021-08-05 | 30 | 2021-09-04 | 2021-09-16 | 101062801.09 | 38754821.03 | [5 empty] | 528137.5 | -0.0001 | 101062801.09 | -0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17719 | EMAAR-Pkg#162/163- Marassi19
PKG#177 | 1 | 20 | 10455877.97 | 14793463.46 | 4337585.49 | 7621726.83 | 10622091.773 | 3000364.943 |  |  |  | 7622310.5 | 2021-07-31 | 2021-07-25 | 2021-08-08 | 30 | 2021-09-07 | 2021-10-19 | 111518679.06 | 37529135.79 | [5 empty] | 528137.5 | -0.001 | 101062801.09 | -0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17720 | EMAAR-Pkg#162/163- Marassi20
PKG#177 | 1 | 21 | 10986391.49 | 16895262.31 | 5908870.82 | 5553244.96 | 11574799.0555 | 6021554.0955 |  |  |  | 5555354.29 | 2021-07-31 | 2021-07-25 | 2021-08-17 | 30 | 2021-09-16 | 2021-11-18 | 122505070.55 | 33099520.87 | [5 empty] | 528137.5 | -0.0001 | 111518679.06 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17721 | EMAAR-Pkg#162/163- Marassi21
PKG#177 | 1 | 22 | 7592601.09 | 10221216.4 | 2628615.31 | 3436603.03 | 6046552.498 | 2609949.468 |  |  |  | 3438276.09 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 30 | 2021-09-30 | 2021-12-07 | 130097671.64 | 29527784.9 | [5 empty] | 528137.5 | -0.0001 | 122505070.55 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17722 | EMAAR-Pkg#162/163- Marassi22
PKG#177 | 1 | 23 | 4755868.7 | 11084383.47 | 6328514.77 | 4324164.09 | 8263496.6735 | 3939332.5835 |  |  |  | 4323818.2 | 2021-08-31 | 2021-09-05 | 2021-09-08 | 30 | 2021-10-08 | 2022-01-04 | 134853540.34 | 30254166.65 | [5 empty] | 674051.5 | -0.0001 | 130097671.64 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17723 | EMAAR-Pkg#162/163- Marassi23
PKG#177 | 1 | 24 | 5954515.89 | 12620775.22 | 6666259.33 | 4835218.42 | 11118548.566 | 6283330.146 |  |  |  | 4835550.93 | 2021-08-31 | 2021-09-05 | 2021-09-12 | 30 | 2021-10-12 | 2022-01-26 | 140808056.23 | 29555882.9 | [5 empty] | 0 | -0.0001 | 134853540.34 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17724 | EMAAR-Pkg#162/163- Marassi24
PKG#177 | 1 | 25 | 3618126.71 | 16552264.24 | 12934137.53 | 4062657.22 | 16704168.777 | 12641511.557 |  |  |  | 4062127.69 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 30 | 2021-11-05 | 2022-02-28 | 144426182.94 | 30667900.14 | [5 empty] | 0 | -0.0001 | 140808056.23 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17725 | EMAAR-Pkg#162/163- Marassi25
PKG#177 | 1 | 26 | -0.00099997 | 7856344.54 | 7856344.541 | 30000000 | 8378952.377 | -21621047.623 |  |  |  | 30000000 | 2021-10-31 | 2021-10-25 | 2021-11-03 | 30 | 2021-12-03 | 2022-03-13 | 144426182.94 | 30667900.14 | [5 empty] | 0 | 0 | 0 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17726 | EMAAR-Pkg#162/163- Marassi26
PKG#177 | 1 | 27 | 1336271.1 | 4132634.87 | 2796363.77 | 1920749.49 | 3653603.3235 | 1732853.8335 |  |  |  | 1920178.92 | 2021-11-30 | 2021-11-25 | 2021-12-07 | 30 | 2022-01-06 | 2022-03-23 | 145762454.04 | 31729493.34 | [5 empty] | 0 | 0 | 0 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17727 | EMAAR-Pkg#162/163- Marassi27
PKG#177 | 1 | 28 | 4959294.77 | 22582028.69 | 17622733.92 | 3761281.17 | 23295212.1945 | 19533931.0245 |  |  |  | 3761592.26 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-03-30 | 150721748.81 | 31076204.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17728 | EMAAR-Pkg#162/163- Marassi28
PKG#177 | 1 | 29 | -0.0001 | 20296742.21 | 20296742.2101 | 30000000 | 19850779.098 | -10149220.902 |  |  |  | 30000000 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-04-05 | 150721748.81 | 31076204.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17729 | EMAAR-Pkg#162/163- Marassi29
PKG#177 | 1 | 30 | 13573272.69 | 27617784.67 | 14044511.98 | 11174297.33 | 15359271.0135 | 4184973.6835 |  |  |  | 11173851.87 | 2021-12-31 | 2021-12-30 | 2022-01-05 | 30 | 2022-02-04 | 2022-04-18 | 164295021.5 | 32011659.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17730 | EMAAR-Pkg#162/163- Marassi30
PKG#177 | 1 | 31 | -0.0001 | 10357799.14 | 10357799.1401 | 20000000 | 10109132.947 | -9890867.053 |  |  |  | 20000000 | 2022-04-30 | 2022-04-18 | 2022-04-18 | 30 | 2022-05-18 | 2022-04-19 | 164295021.5 | 32011659.59 | [5 empty] | 1244836 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17731 | EMAAR-Pkg#162/163- Marassi31
PKG#177 | 1 | 32 | 10655190.55 | 11583000.46 | 927809.91 | 9586612.72 | 15273972.9335 | 5687360.2135 |  |  |  | 9586713.98 | 2022-01-31 | 2022-01-31 | 2022-02-10 | 30 | 2022-03-12 | 2022-05-10 | 174950212.05 | 31704142.35 | [5 empty] | 0 | 0 | 0 | 1200000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17732 | EMAAR-Pkg#162/163- Marassi32
PKG#177 | 1 | 33 |  | 4083110.28 | 4083110.28 | 9774603.63 | 3354959.084 | -6419644.546 |  |  |  |  | 2022-03-31 | 2022-03-28 | 2022-05-22 | 30 | 2022-06-21 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17733 | EMAAR-Pkg#162/163- Marassi33
PKG#177 | 1 | 34 | 4083110.25 | 0 | -4083110.25 | 3243420.79 | 0 | -3243420.79 |  |  |  | 3242747.22 | 2022-02-28 | 2022-03-01 | 2022-03-06 | 30 | 2022-04-05 | 2022-06-01 | 189971239 | 33248463 |  |  |  | 5813429 | 5813429 | 1266148 | 3016331.1152 | 188904459.8652 | 16000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17734 | EMAAR-Pkg#162/163- Marassi34
PKG#177 | 1 | 35 | 20620247 | 20620247.8 | 0.8 | 14874314 | 15928851.3665 | 1054537.3665 |  |  |  | 14874314.24 | 2022-04-30 | 2022-04-20 | 2022-06-08 | 30 | 2022-07-08 | 2022-06-08 | 210591486 | 32687951 |  |  |  | 6340697.5 | 6340697.5 | 1273436 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17735 | EMAAR-Pkg#162/163- Marassi35
PKG#177 | 1 | 36 | 41964961.54 | 42116952.2 | 151990.66 | 32974130.9 | 36331150.12 | 3357019.22 |  |  |  | 32974130.9 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 | 2022-08-04 | 252556447.54 | 55952679 |  |  |  | 8027886.035 | 8027886.035 | 2506369.82 | 2649851.22 | 213241337.22 | 15000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17736 | EMAAR-Pkg#162/163- Marassi36
PKG#177 | 1 | 37 | 3201525.38 | 3201525.38 | 6.3796e-08 | 2963171.82 | 3131251.909 | 168080.089 |  |  |  | 2963171.82 | 2022-03-31 | 2022-04-12 | 2022-04-12 | 30 | 2022-05-12 | 2022-08-14 | 255757972.92 | 55952679 |  |  |  | 8111926.08 | 8111926.08 | 1543023.5 | 3201524.52 | 255757972.06 | 2963171.8184 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17737 | EMAAR-Pkg#162/163- Marassi37
PKG#177 | 1 | 38 | 113074932.04 | 113074931.25 | -0.79 | 40830987.19 | 46024929.671 | 5193942.481 |  |  |  | 40830987.19 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 | 2022-08-15 | 368832904.96 | 41102851 |  |  | 430147 | 10708897.325 | 10708897.325 | 8967998.5 | -0.86 | 255757972.06 | 0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17738 | EMAAR-Pkg#162/163- Marassi38
PKG#177 | 1 | 39 | 62332263.27 | 62325696.1 | -6567.17 | 24380106.6 | 27439277.805 | 3059171.205 |  |  |  | 24380106.6 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 | 2022-10-03 | 431165168.23 | 36844292 | [5 empty] | 0 | -178832904.96 | 190000000 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17739 | EMAAR-Pkg#162/163- Marassi39
PKG#177 | 1 | 40 | 2265658.58 | 2265659.38 | 0.8 | 0.0001 | 118928.159 | 118928.1589 |  |  |  | 0.0001 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 30 | 2022-08-30 | 2022-11-22 | 433430826.81 | 36844292 |  |  | 430147 |  |  | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17740 | EMAAR-Pkg#162/163- Marassi40
PKG#177 | 1 | 41 | 16308262.76 | 16303582.18 | -4680.58 | 1e-05 | 180103.25 | 180103.25 |  |  |  | 0.0001 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 | 2022-11-22 | 449739089.57 | 23473659 | [5 empty] | 0 | -11904090.5837 | 421526736.2263 | 10330863.574 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17741 | EMAAR-Pkg#162/163- Marassi41
PKG#177 | 1 | 42 | 25575904.54 | 2102245.55 | -23473658.99 | 4198626.99 | 4316245.8075 | 117618.8175 |  |  |  | 4207031.92 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 30 | 2022-10-30 | 2023-02-22 | 475314994.11 | [6 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17742 | EMAAR-Pkg#162/163- Marassi42
PKG#177 | 1 | 43 | -1403499.79 | 15896560.84 | 17300060.63 | 14488992.22 | 15323561.672 | 834569.452 |  |  |  | 14488837.89 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-04-13 | 473911494.32 | 23473659 | 399954494 |  | 430147.49 | 12864128.305 | 12864128.305 | 3512870.7 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17743 | EMAAR-Pkg#162/163- Marassi43
PKG#177 | 1 | 44 | 59788309.64 | 54841445.41 | -4946864.23 | 17144236.06 | 19396451.9605 | 2252215.9005 |  |  |  | 17144236.06 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-05-25 | 533699803.96 | 11107434 | 448361770 |  | 430147.49 | 13994560.62 | 13994560.62 | 4392870.7 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17744 | EMAAR-Pkg#162/163- Marassi44
PKG#177 | 1 | 45 | 102598790.27 | 26509803.46 | -76088986.81 | 15002016.49 | 16466307.981 | 1464291.491 |  |  |  | 15002016.49 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 30 | 2022-10-07 | 2023-06-15 | 576510284.59 | 12544287.37 | 474871564.16 |  | 430147.49 | 14726364.3 | 14726364.3 | 4392870.7 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17745 | EMAAR-Pkg#162/163- Marassi45
PKG#177 | 1 | 46 | -22395666.32 | 5007444.76 | 27403111.08 | 3048300.98 | 3319156.348 | 270855.368 |  |  |  | 3056265.5 | 2022-09-30 | 2022-09-25 | 2022-10-17 | 30 | 2022-11-16 | 2023-07-16 | 554114618.27 | 12544287.37 | 479879018.92 |  | 430147 | 14857839.5 | 14857839.5 | 8396085.7 | 0 | 0 | 10000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17746 | EMAAR-Pkg#162/163- Marassi46
PKG#177 | 1 | 47 | 6780617.51 | 6785617.6 | 5000.09 | 4274072.25 | 4548162.03 | 274089.78 |  |  |  | 4274854.67 | 2023-06-30 | 2023-06-25 | 2023-02-15 | 30 | 2023-03-17 | 2023-08-03 | 560895235.78 | 10901184.51 | 486669436 |  | 430147 | 14994854.5 | 14994854.5 | 8396085.7 | 21331767.9853 | 575446386.2553 | 4375831.9851 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17747 | EMAAR-Pkg#162/163- Marassi47
PKG#177 | 1 | 48 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 4111000 | 2023-03-31 | 2023-03-25 | 2023-03-26 | 30 | 2023-04-25 | [8 empty] | 0 | 0 | 0 | 4111000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17748 | EMAAR-Pkg#162/163- Marassi48
PKG#177 | 1 | 49 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 0.0001 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 30 | 2023-06-13 | [8 empty] | 0 | 0 | 0 | 0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17749 | EMAAR-Pkg#162/163- Marassi49
PKG#177 | 1 | 50 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 0.001 | 2023-05-31 | 2023-05-31 | 2023-06-04 | 30 | 2023-07-04 | [8 empty] | 0 | 0 | 0 | 0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17750 | EMAAR-Pkg#162/163- Marassi50
PKG#177 | 1 | 51 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 0.001 | 2023-06-30 | 2023-06-25 | 2023-06-25 | 30 | 2023-07-25 | [8 empty] | 0 | 0 | 0 | 0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17751 | EMAAR-Pkg#162/163- Marassi51
PKG#177 | 1 | 52 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 45000000 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 30 | 2023-09-13 | [8 empty] | 0 | 0 | 0 | 45000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17752 | EMAAR-Pkg#162/163- Marassi52
PKG#177 | 1 | 53 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 5000000 | 2023-10-31 | 2023-11-14 | 2023-11-14 | 30 | 2023-12-14 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17753 | EMAAR-Pkg#162/163- Marassi53
PKG#177 | 1 | 54 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 14081143 | 2024-05-31 | 2024-06-04 | 2024-06-05 | 30 | 2024-07-05 |  | 626950196.89 | [6 empty] | 0 | 0 | 0 | 14081143 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17754 | EMAAR-Pkg#162/163- Marassi54
PKG#177 - DP | 1 | 1 |  | 1493908.79 | 1493908.79 | 0 | 1068966.4295 | 1068966.4295 |  |  |  | 22337274.9 | 2021-03-31 | 2021-03-24 | 2021-03-24 | 30 | 2021-04-23 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - DP1 | EMAAR-Pkg#162/163- Marassi1
PKG#177 - SWI 07 | 1 | 1 |  | 1493908.79 | 1493908.79 | 0 | 1068966.4295 | 1068966.4295 |  |  |  | 1800000 | 2021-11-30 | 2021-12-15 | 2021-12-13 | 30 | 2022-01-12 | [8 empty] | 0 | 0 | 0 | 1800000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 071 | EMAAR-Pkg#162/163- Marassi1
PKG#177 - SWI 07 | 1 | 2 |  | 17264889.03 | 17264889.03 | 0 | 17974031.2815 | 17974031.2815 |  |  |  | 4300000 | 2021-12-31 | 2021-12-31 | 2022-01-03 | 30 | 2022-02-02 | [8 empty] | 0 | 0 | 0 | 4300000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 072 | EMAAR-Pkg#162/163- Marassi2
PKG#177 - SWI 07 | 1 | 3 |  | 12082357.79 | 12082357.79 | 0 | 16268974.4395 | 16268974.4395 |  |  |  | 5800000 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 | [8 empty] | 0 | 0 | 0 | 5800000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 073 | EMAAR-Pkg#162/163- Marassi3
PKG#177 - SWI 07 | 1 | 4 |  | 14694850.77 | 14694850.77 | 0 | 17742432.8485 | 17742432.8485 |  |  |  |  | 2022-02-28 | 2022-02-28 | 2022-03-02 | 30 | 2022-04-01 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 074 | EMAAR-Pkg#162/163- Marassi4
PKG#177 - SWI 07 | 1 | 5 |  | 8006098.571 | 8006098.571 | 0 | 7958142.0485 | 7958142.0485 |  |  |  | 9500000 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 | [8 empty] | 0 | 0 | 0 | 9500000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 075 | EMAAR-Pkg#162/163- Marassi5
PKG#177 - SWI 07 | 1 | 6 | 3141613.418 | 14622817.211 | 11481203.793 | 0 | 13427541.4454 | 13427541.4454 |  |  |  | 5000000 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 |  | 31868573.268 |  |  |  | 1025274 |  |  | 0 | 3141613.418 | 31868573.268 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 076 | EMAAR-Pkg#162/163- Marassi6
PKG#177 - SWI 07 | 1 | 7 | 10847798.8446 | 12998247.66 | 2150448.8154 | 0 | 12964361.5377 | 12964361.5377 |  |  |  | 4000000 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 |  | 42716372.1126 | [6 empty] | 0 | 10847798.8446 | 42716372.1126 | 4000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 077 | EMAAR-Pkg#162/163- Marassi7
PKG#177 - SWI 07 | 1 | 8 |  | 27347974.52 | 27347974.52 | 0 | 22259454.996 | 22259454.996 |  |  |  | 500000 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 | [8 empty] | 0 | 0 | 0 | 500000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 078 | EMAAR-Pkg#162/163- Marassi8
PKG#177 - SWI 07 | 1 | 9 |  | 15911837.121 | 15911837.121 | 0 | 20607532.6031 | 20607532.6031 |  |  |  | 4000000 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 30 | 2022-09-09 | [8 empty] | 0 | 0 | 0 | 4000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 079 | EMAAR-Pkg#162/163- Marassi9
PKG#177 - SWI 07 | 1 | 10 |  | 18387668.6001 | 18387668.6001 | 1e-05 | 18192775.4801 | 18192775.4801 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-17 | 30 | 2022-11-16 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 0710 | EMAAR-Pkg#162/163- Marassi10
PKG#178 | 1 | 1 |  | 0 | 0 | 3747170.2 | 0 | -3747170.2 | 3747170.2 |  | 1276787.15 | 3747170.2 | 2021-01-31 | 2021-01-25 | 2021-01-25 | 30 | 2021-02-24 | 2021-02-02 | [7 empty] | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1781 | BKG#178-Lagoon Discharge1
PKG#178 | 1 | 2 | 16123744.18 | 15355946.84 | -767797.34 | 13230338.29 | 13230338.292 | 0.002 |  |  | 392599.98 | 13230338.29 | 2021-02-28 | 2021-02-28 | 2021-03-04 | 30 | 2021-04-03 | 2021-04-14 | 16123744.18 | [6 empty] | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1782 | BKG#178-Lagoon Discharge2
PKG#178 | 1 | 3 | 8196011.07 | 7805724.83 | -390286.24 | 6675236.88 | 7952024.0415 | 1276787.1615 |  |  | 887343.85 | 6675236.88 | 2021-03-31 | 2021-03-31 | 2021-04-04 | 30 | 2021-05-04 | 2021-04-28 | 24319755.25 | 1215987.76 | [5 empty] | 50000 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1783 | BKG#178-Lagoon Discharge3
PKG#178 | 1 | 4 | 7478094.91 | 8636178.5 | 1158083.59 | 6081013.29 | 6473613.265 | 392599.975 |  |  |  | 6081013.28 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 30 | 2021-06-04 | 2021-06-03 | 31797850.16 | [6 empty] | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1784 | BKG#178-Lagoon Discharge4
PKG#178 | 1 | 5 | 10300781.8 | 10300781.79 | -0.01 | 9125492.66 | 9666283.6995 | 540791.0395 |  |  |  | 9125492.66 | 2021-05-31 | 2021-06-07 | 2021-06-08 | 30 | 2021-07-08 | 2021-06-21 | 42098631.96 | [6 empty] | 105137.6 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1785 | BKG#178-Lagoon Discharge5
PKG#178 | 1 | 6 | 4524611.34 | 4524611.34 | 0 | 2730279.03 | 2967821.117 | 237542.087 |  |  |  | 2730279.03 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 30 | 2021-08-10 | 2021-09-21 | 46623243.3 | 0 | [5 empty] | 1562612.5 | 4524611.3442 | 46623243.3042 | 4030279.0303 | BKG#178-Lagoon Discharge |  |  |  | PKG#1786 | BKG#178-Lagoon Discharge6
PKG#178 | 1 | 7 | 686559 | 686559 | -7.4506e-09 | 1644401.99 | 1680446.34 | 36044.35 |  |  |  | 1844728.45 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 30 | 2021-12-02 | 2021-12-02 | 47309802.3 | 0 | [5 empty] | 1595537.5 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1787 | BKG#178-Lagoon Discharge7
PKG#178 | 1 | 8 | 1389835.54 | 1389835.52 | -0.02 | 595920.45 | 668886.796 | 72966.346 |  |  |  | 595920.46 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 | 2022-02-28 | 48699637.84 |  |  |  |  | 1278365.495 | 1278365.495 | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1788 | BKG#178-Lagoon Discharge8
PKG#178 | 1 | 9 | 31809.52 | 31809.53 | 0.01 | 289077.6 | 2524652.5565 | 2235574.9565 |  |  |  | 88751.13 | 2022-08-31 | 2022-08-28 | 2022-08-30 | 30 | 2022-09-29 | 2022-10-09 | 48731447.36 |  |  |  |  | 1279200.495 | 1279200.495 | 2370468.93 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1789 | BKG#178-Lagoon Discharge9
PKG#178 | 1 | 10 | -0.0001 | 0 | 0.0001 | 2235574.97 | 0 | -2235574.97 |  |  |  | 2080200.49 | 2023-01-31 | 2023-01-25 | 2023-05-29 | 30 | 2023-06-28 | 2023-06-02 | 48731447.36 |  | 12630627.58 |  | 413484.78 |  |  | 1769468.93 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#17810 | BKG#178-Lagoon Discharge10
PKG#205 | 1 | 2 | 1935314 | 0 | -1935314 | 1181605.96 | 0 | -1181605.96 |  |  |  | 1181605.96 | 2022-04-30 | 2022-04-28 | 2022-05-24 | 30 | 2022-06-23 | 2022-05-24 | 1935314 | 0 | 0 |  | 0 | 50801.99 | 50801.99 | 0 | 0 | 0 | 0 | 0 |  |  |  | PKG#2052 | 02
PKG#205 | 1 | 3 | 2048098 | 0 | -2048098 | 1250466.11 | 0 | -1250466.11 |  |  |  | 1250466.11 | 2022-05-31 | 2022-05-31 | 2022-06-13 | 30 | 2022-07-13 | 2022-06-13 | 3983412 |  |  |  | 63808.49 | 104564.5 | 104564.5 | 0 | 0 | 0 | 0 | 0 |  |  |  | PKG#2053 | 03
PKG#220B | 1 | 2 | 12159328.08 | 35084150.1 | 22924822.02 | 8261597.76 | 5980500.04 | -2281097.72 |  |  |  | 8261597.76 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 30 | 2023-07-07 | 2023-06-20 | 12159328.08 |  |  |  |  | 319182.36 | 319182.36 | 0 | 0 | 0 | 0 | SOL Town PKG.220 |  |  |  | PKG#220B2 | SOL Town PKG.2202
PKG#220B | 1 | 3 | 11462411.01 | 1345226.9 | -10117184.11 | 5980500.04 | 348202.56 | -5632297.48 |  |  |  | 5980500.04 | 2023-06-30 | 2023-07-05 | 2023-07-10 | 30 | 2023-08-09 | 2023-08-14 | 23621739.09 |  |  |  |  | 620070.65 | 620070.65 | 1017875 | 0 | 0 | 0 | SOL Town PKG.220 |  |  |  | PKG#220B3 | SOL Town PKG.2203
PKG#220B | 1 | 4 |  | 1274131.45 | 1274131.45 | 2300000 | 1849642.29 | -450357.71 |  |  |  | 2300000 | 2023-07-31 | 2023-08-05 | 2023-08-07 | 30 | 2023-09-06 | [8 empty] | 0 | 0 | 0 | 2300000 | SOL Town PKG.220 |  |  |  | PKG#220B4 | SOL Town PKG.2204
PKG#220B - DP | 1 | 1 |  | 12159328.08 | 12159328.08 | 0 | 8261597.76 | 8261597.76 |  |  |  |  | 2023-05-31 | 2023-05-21 | 2023-05-21 | 30 | 2023-06-20 | [8 empty] | 0 | 0 | 0 | 0 | SOL Town PKG.220 |  |  |  | PKG#220B - DP1 | SOL Town PKG.2201
PKG#45 | 1 | 46 |  | 0 | 0 | 1844931.02 | 0 | -1844931.02 |  |  |  | 1069392.54 | 2018-06-30 | 2018-07-15 | 2018-09-18 |  | 2018-12-15 | 2018-11-21 | 59167173.46 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | PKG#4546 | 046
PKG#58 | 1 | 22 | 0 | 0 | 0 | 327696.29 | 0 | -327696.29 |  |  |  | 317558.66 | 2015-12-31 | 2015-12-29 | 2015-12-29 |  | 2018-11-15 | 2018-10-21 | 4831971.92 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | PKG#5822 | 022
PKG#85 | 1 | 5 |  | 0 | 0 | 1729285.15 | 0 | -1729285.15 |  |  |  |  | 2018-10-31 | 2018-10-17 | 2018-11-11 | 30 | 2018-12-11 | [9 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#855 | EMAAR-PKG#85-UPTOWN5
PKG#85 | 1 | 6 | 2033193.5852 | 0 | -2033193.5852 | 768766.59 | 0 | -768766.59 |  |  |  | 768766.5752 | 2019-02-28 | 2019-02-28 | 2019-03-09 | 30 | 2019-04-08 | 2019-05-20 | 8147064.8613 | [7 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#856 | EMAAR-PKG#85-UPTOWN6
PKG#85 | 1 | 7 |  | 0 | 0 | 29830.3 | 0 | -29830.3 |  |  |  |  | 2019-05-31 | 2019-05-15 | 2019-06-10 | 30 | 2019-07-10 | [9 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#857 | EMAAR-PKG#85-UPTOWN7
PKG#85 | 1 | 8 |  | 0 | 0 | 1391898.96 | 0 | -1391898.96 |  |  |  |  | 2019-10-31 | 2019-10-11 | 2019-11-18 | 30 | 2019-12-18 | [9 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#858 | EMAAR-PKG#85-UPTOWN8
PO#11687 | 1 | 1 |  | 0 | 0 | 1090584 | 0 | -1090584 |  |  |  |  | 2018-12-31 | 2019-01-10 | 2019-01-10 | 15 | 2019-01-25 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116871 | 01
PO#11687 | 1 | 2 |  | 0 | 0 | 451528 | 0 | -451528 |  |  |  |  | 2019-02-28 | 2019-02-28 | 2019-02-28 | 15 | 2019-03-15 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116872 | 02
PO#11687 | 1 | 3 |  | 0 | 0 | 293788 | 0 | -293788 |  |  |  |  | 2019-03-31 | 2019-04-14 | 2019-08-22 | 15 | 2019-09-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116873 | 03
PO#11687 | 1 | 5 |  | 0 | 0 | 343200 | 0 | -343200 |  |  |  |  | 2019-11-30 | 2019-12-18 | 2019-12-19 | 15 | 2020-01-03 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116875 | 05
Port Said Silos | 1 | 1 | 9011475.2 | 21214607.02 | 12203131.82 | 37788892.4 | 16089595.0422 | -21699297.3578 | 26540249.4 |  |  | 5248643 | 2022-03-31 | 2022-03-25 | 2022-03-05 | 21 | 2022-03-26 | 2022-04-24 | 9011475.2 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos1 | Port Said Port Silos1
Port Said Silos | 1 | 2 | 2334108.9048 | 1883535.14 | -450573.7648 | 21773106 | 1586748.547 | -20186357.453 | 15000000 |  |  | 1688672.941 | 2022-04-30 | 2022-04-25 | 2022-04-28 | 21 | 2022-05-19 | 2022-05-17 | 11345584.1048 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos2 | Port Said Port Silos2
Port Said Silos | 1 | 3 |  | 9057943.58 | 9057943.58 | 14623869 | 14589360.9503 | -34508.0497 |  |  |  |  | 2022-05-31 | 2022-05-25 | 2022-06-02 | 21 | 2022-06-23 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos3 | Port Said Port Silos3
Port Said Silos | 1 | 4 |  | 3348506.91 | 3348506.91 | 22560435 | 2971799.8855 | -19588635.1145 |  |  |  |  | 2022-06-30 | 2022-06-29 | 2022-06-29 | 21 | 2022-07-20 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos4 | Port Said Port Silos4
Port Said Silos | 1 | 5 | 5318356.3714 | 8597357.386 | 3279001.0146 | 14009921 | 14928020.4333 | 918099.4333 |  |  |  | 4009921 | 2022-07-31 | 2022-07-31 | 2022-08-02 | 21 | 2022-08-23 | 2022-08-09 | 25985299.3429 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos5 | Port Said Port Silos5
Port Said Silos | 1 | 6 | 9017880.2762 | 10082374.64 | 1064494.3638 | 21842722 | 19981317.606 | -1861404.394 |  |  |  | 6842722 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 21 | 2022-09-21 | 2022-09-13 | 35003179.619 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos6 | Port Said Port Silos6
Port Said Silos | 1 | 7 | 4021476.8571 | 9573941.61 | 5552464.7529 | 3061822 | 44244322.128 | 41182500.128 |  |  |  | 3061822 | 2022-09-30 | 2022-09-30 | 2022-10-02 | 21 | 2022-10-23 | 2022-10-18 | 39024656.4762 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos7 | Port Said Port Silos7
Port Said Silos | 1 | 8 | 22573115.9429 | 25167994.38 | 2594878.4371 | 17260533 | 29006884.597 | 11746351.597 |  |  |  | 17260533 | 2022-10-31 | 2022-10-31 | 2022-11-07 | 21 | 2022-11-28 | 2022-11-21 | 61597772.419 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos8 | Port Said Port Silos8
Port Said Silos | 1 | 9 | 3139225.2286 | 3139228.09 | 2.8614 | 2370710 | 2756360.9335 | 385650.9335 |  |  |  | 2370710 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 21 | 2022-12-26 | 2022-12-19 | 64736997.6476 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos9 | Port Said Port Silos9
Port Said Silos | 1 | 10 | 8366928.5333 | 8366928.53 | -0.0033333 | 6384571 | 7412449.0665 | 1027878.0665 |  |  |  | 6384571 | 2022-12-31 | 2022-12-30 | 2023-01-01 | 21 | 2023-01-22 | 2023-01-22 | 73103926.19 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos10 | Port Said Port Silos10
Port Said Silos | 1 | 11 | 5057462.5238 | 5057462.52 | -0.0038095 | 3852337 | 4473647.986 | 621310.986 |  |  |  | 3852337 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-02-15 | 78161388.7138 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos11 | Port Said Port Silos11
Port Said Silos | 1 | 12 | 2086813.5333 | 5974560.53 | 3887746.9967 | 1587432 | 1843797.0112 | 256365.0112 |  |  |  | 1587432 | 2023-02-28 | 2023-02-28 | 2023-03-01 | 21 | 2023-03-22 | 2023-03-20 | 80248202.2471 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos12 | Port Said Port Silos12
Port Said Silos | 1 | 13 | 612060.8329 | 612060 | -0.83286 | 460093 | 535282.8844 | 75189.8844 |  |  |  | 451211.246 | 2023-03-31 | 2023-03-31 | 2023-04-02 | 21 | 2023-04-23 | 2023-04-02 | 80860263.08 | [6 empty] | 0 | 612060.8329 | 80860263.08 | 451211.246 | Port Said Port Silos |  |  |  | Port Said Silos13 | Port Said Port Silos13
Port Said Silos | 1 | 14 |  | 2803566.38 | 2803566.38 | 2136487 | 2480905.1552 | 344418.1552 |  |  |  |  | 2023-04-30 | 2023-04-30 | 2023-05-02 | 21 | 2023-05-23 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos14 | Port Said Port Silos14
Port Said Silos | 1 | 15 | 10044463.5619 | 10044463.56 | -0.0019048 | 7663669 | 8897631.4024 | 1233962.4024 |  |  |  | 7663669 | 2023-05-31 | 2023-05-30 | 2023-06-03 | 21 | 2023-06-24 | 2023-07-05 | 93708293.0229 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos15 | Port Said Port Silos15
Port Said Silos | 1 | 16 | 12501707.0667 | 12501707.07 | 0.0033333 | 9649102 | 11072420.0228 | 1423318.0228 |  |  |  | 9649102 | 2023-06-30 | 2023-06-30 | 2023-07-08 | 21 | 2023-07-29 | 2023-07-17 | 106210000.0895 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos16 | Port Said Port Silos16
Port Said Silos | 1 | 17 | 7676679.5524 | 7676679.55 | -0.002381 | 5738977 | 6794573.092 | 1055596.092 |  |  |  | 5738977 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 21 | 2023-08-21 | 2023-08-15 | 113886679.6419 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos17 | Port Said Port Silos17
Port Said Silos | 1 | 18 | 7866196.5143 | 7866196.51 | -0.0042857 | 2991787 | 3958149.4004 | 966362.4004 |  |  |  | 2991787 | 2023-08-31 | 2023-08-31 | 2023-09-03 | 21 | 2023-09-24 | 2023-10-03 | 121752876.1562 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos18 | Port Said Port Silos18
Port Said Silos | 1 | 19 | 17118439.2571 | 17118439.26 | 0.0028571 | 12748959 | 14851957.9104 | 2102998.9104 |  |  |  | 12748959 | 2023-09-30 | 2023-09-30 | 2023-10-01 | 21 | 2023-10-22 | 2023-10-16 | 138871315.4133 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos19 | Port Said Port Silos19
Port Said Silos | 1 | 20 | 12988784 | 12988783.81 | -0.19 | 6593857 | 8189528.9592 | 1595671.9592 |  |  |  | 6593857 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 21 | 2023-11-22 | 2023-11-22 | 151860099.4133 | [6 empty] | 0 | 13732229.2267 | 152603544.64 | 10123399.3859 | Port Said Port Silos |  |  |  | Port Said Silos20 | Port Said Port Silos20
Port Said Silos | 1 | 21 | 15886446.6476 | 15886445.71 | -0.93762 | 11818794 | 13770443.8984 | 1951649.8984 |  |  |  | 11818794 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 21 | 2023-12-21 | 2023-12-23 | 167746546.061 | [6 empty] | 0 | 15886446.6567 | 167746546.07 | 11711488.4753 | Port Said Port Silos |  |  |  | Port Said Silos21 | Port Said Port Silos21
Port Said Silos | 1 | 22 | 6713332.6667 | 6713332.67 | 0.0033333 | 4826684 | 5651416.0035 | 824732.0035 |  |  |  | 4826684 | 2023-12-31 | 2023-12-13 | 2023-12-14 | 21 | 2024-01-04 | 2023-12-27 | 174459878.7276 | [6 empty] | 0 | 6713332.669 | 174459878.73 | 4949068.8436 | Port Said Port Silos |  |  |  | Port Said Silos22 | Port Said Port Silos22
Port Said Silos | 1 | 23 | 3587901.4571 | 3587901.46 | 0.0028571 | 2411082.19 | 2851855.8684 | 440773.6784 |  |  |  | 2411082.19 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 21 | 2024-01-25 | 2024-01-18 | 178047780.1848 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos23 | Port Said Port Silos23
Port Said Silos | 1 | 24 | 4764115.7714 | 4764115.24 | -0.53143 | 3306186 | 3891455.9996 | 585269.9996 |  |  |  | 3306186 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 21 | 2024-02-27 | 2024-02-21 | 182811895.9562 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos24 | Port Said Port Silos24
Port Said Silos | 1 | 25 | 4504742.6762 | 4504741.9 | -0.77619 | 3280048 | 3280047.566 | -0.434 |  |  |  | 3280048 | 2024-02-29 | 2024-02-29 | 2024-03-04 | 21 | 2024-03-25 | 2024-04-07 | 187316638.6324 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos25 | Port Said Port Silos25
Port Said Silos | 1 | 26 | 2227046.781 | 2227046.78 | -0.00095238 | 426108 | 426108.0312 | 0.0312 |  |  |  | 426108 | 2024-03-31 | 2024-03-31 | 2024-04-04 | 21 | 2024-04-25 | 2024-05-07 | 189543685.4133 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos26 | Port Said Port Silos26
Port Said Silos | 1 | 27 | 1522665.14 | 1478728.71 | -43936.43 | 0 | 0 | 0 |  |  |  | 0.0001 | 2024-04-30 | 2024-05-01 | 2024-05-01 | 21 | 2024-05-22 | 2024-05-27 | 191066350.5533 | [6 empty] | 0 | 1478728.71 | 191022414.13 | 1090118.805 | Port Said Port Silos |  |  |  | Port Said Silos27 | Port Said Port Silos27
Port Said Silos | 1 | 28 | 3379589.9429 | 3379589.94 | -0.0028571 | 1239632 | 2663473.997 | 1423841.997 |  |  |  | 1239632 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 21 | 2024-06-23 | 2024-07-01 | 194445940.4962 | [6 empty] | 0 | 3335653.5067 | 194402004.06 | 2459043.7651 | Port Said Port Silos |  |  |  | Port Said Silos28 | Port Said Port Silos28
Port Said Silos | 1 | 29 | 2107663.7333 | 2107663.51 | -0.22333 | 337130 | 596055.2424 | 258925.2424 |  |  |  | 337130 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 21 | 2024-07-28 | 2024-08-07 | 196553604.2295 | [6 empty] | 0 | 2063726.5038 | 196509667 | 1521379.1786 | Port Said Port Silos |  |  |  | Port Said Silos29 | Port Said Port Silos29
Port Said Silos | 1 | 30 | 3191368.2381 | 3191368.24 | 0.0019048 | 100641 | 100639.5696 | -1.4304 |  |  |  | 100641 | 2024-07-31 | 2024-07-31 | 2024-08-03 | 21 | 2024-08-24 | 2024-08-22 | 199744972.4676 | [6 empty] | 0 | 3191369.04 | 199701036.04 | 2352677.2563 | Port Said Port Silos |  |  |  | Port Said Silos30 | Port Said Port Silos30
Port Said Silos | 1 | 31 | 2906595.6404 | 3155732.38 | 249136.7396 | 727554 | 2284436.52 | 1556882.52 |  |  |  | 727554 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 202651568.108 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos31 | Port Said Port Silos31
Port Said Silos | 1 | 32 | 4167368.41 | 3968922.29 | -198446.12 | 2193035.35 | 2296974.7655 | 103939.4155 |  |  |  | 2193035.35 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-11-03 | 206818936.518 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos32 | Port Said Port Silos32
Port Said Silos | 1 | 33 |  | 4525360.97 | 4525360.97 | 2711136 | 2711136 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos33 | Port Said Port Silos33
Port Said Silos - Foreigner Supply | 1 | 1 | 5539353.23 | 21214607.02 | 15675253.79 | 5206992 | 16089595.0422 | 10882603.0422 |  |  |  | 5206992.0362 | 2023-09-30 | 2023-09-30 | 2023-09-24 | 21 | 2023-10-15 | 2023-11-06 | 5539353.23 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Foreigner Supply1 | Port Said Port Silos1
Port Said Silos - Foreigner Supply | 1 | 2 |  | 1883535.14 | 1883535.14 | 775509.45 | 1586748.547 | 811239.097 |  |  |  |  | 2023-10-31 | 2023-10-31 | 2023-12-05 | 21 | 2023-12-26 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Foreigner Supply2 | Port Said Port Silos2
Port Said Silos - Local Supply | 1 | 1 | 673851.6 | 21214607.02 | 20540755.42 | 655657.61 | 16089595.0422 | 15433937.4322 |  |  |  | 438003.54 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-03-16 | 673851.6 | [6 empty] | 0 | 673851.6 | 673851.6 | 438003.54 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply1 | Port Said Port Silos1
Port Said Silos - Local Supply | 1 | 2 | 1194976.6491 | 1883535.14 | 688558.4909 | 1162711.94 | 1586748.547 | 424036.607 |  |  |  | 1162711.94 | 2023-09-30 | 2023-09-30 | 2023-10-18 | 21 | 2023-11-08 | 2023-11-06 | 1868828.2491 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply2 | Port Said Port Silos2
Port Said Silos - Local Supply | 1 | 3 | 3085091.6316 | 9057943.58 | 5972851.9484 | 2307930.88 | 14589360.9503 | 12281430.0703 |  |  |  | 2307930.88 | 2024-02-29 | 2024-02-29 | 2024-03-13 | 21 | 2024-04-03 | 2024-03-31 | 4953919.8807 | [6 empty] | 0 | 3085091.6309 | 4953919.88 | 2005309.5601 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply3 | Port Said Port Silos3
Port Said Silos - Local Supply | 1 | 4 | 4365732.3333 | 3348506.91 | -1017225.4233 | 3416710 | 2971799.8855 | -444910.1145 |  |  |  | 3416710 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 21 | 2024-04-28 | 2024-05-07 | 9319652.214 | [6 empty] | 0 | 4365732.3293 | 9319652.21 | 2837726.014 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply4 | Port Said Port Silos4
Port Said Silos - Local Supply | 1 | 5 | 3278709.2807 | 8597357.386 | 5318648.1053 | 2565984 | 14928020.4333 | 12362036.4333 |  |  |  | 2565984 | 2024-04-30 | 2024-04-30 | 2024-05-12 | 21 | 2024-06-02 | 2024-05-27 | 12598361.4947 | [6 empty] | 0 | 3278709.276 | 12598361.49 | 2131161.0294 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply5 | Port Said Port Silos5
Port Said Silos - Local Supply | 1 | 6 | 1064669.3947 | 10082374.64 | 9017705.2453 | 833240 | 19981317.606 | 19148077.606 |  |  |  | 833240 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 21 | 2024-06-30 | 2024-07-01 | 13663030.8895 | [6 empty] | 0 | 1064669.3953 | 13663030.89 | 692035.1069 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply6 | Port Said Port Silos6
Port Said Silos - Local Supply | 1 | 7 | 5552464.7544 | 9573941.61 | 4021476.8556 | 4345468 | 44244322.128 | 39898854.128 |  |  |  | 4345468 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 21 | 2024-08-06 | 2024-08-06 | 19215495.6439 | [6 empty] | 0 | 5552464.1105 | 19215495 | 3609101.6718 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply7 | Port Said Port Silos7
Port Said Silos - Local Supply | 1 | 8 | 2594878.4386 | 25167994.38 | 22573115.9414 | 1794648.84 | 29006884.597 | 27212235.757 |  |  |  | 1794648.84 | 2024-07-31 | 2024-07-31 | 2024-08-18 | 21 | 2024-09-08 | 2024-09-01 | 21810374.0825 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply8 | Port Said Port Silos8
Port Said Silos - Local Supply | 1 | 9 | 3231641.7018 | 3139228.09 | -92413.6118 | 2529147 | 2756360.9335 | 227213.9335 |  |  |  | 2529147 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 25042015.7842 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply9 | Port Said Port Silos9
Port Said Silos - Local Supply | 1 | 10 | 622795.91 | 8366928.53 | 7744132.62 | 494192 | 7412449.0665 | 6918257.0665 |  |  |  | 494192 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-10-03 | 25664811.6942 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply10 | Port Said Port Silos10
Port Said Silos - Local Supply | 1 | 11 |  | 5057462.52 | 5057462.52 | 833789.82 | 4473647.986 | 3639858.166 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply11 | Port Said Port Silos11
PSP Substation | 1 | 2 | 1669926.8 | 0 | -1669926.8 | 1160599 | 0 | -1160599 |  |  |  | 1244095.47 | 2018-06-30 | 2018-07-03 | 2018-07-05 | 30 | 2018-08-04 | 2018-07-22 | 1669926.8 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation2 | 02
PSP Substation | 1 | 3 | 2696322.9906 | 0 | -2696322.9906 | 1834172.07 | 0 | -1834172.07 |  |  |  | 1834172.07 | 2018-07-31 | 2018-08-05 | 2018-08-06 | 30 | 2018-09-05 | 2018-10-11 | 4366249.7906 | [6 empty] | 0 | 2696322.9906 | 4366249.7906 | 1834172.07 | 0 |  |  |  | PSP Substation3 | 03
PSP Substation | 1 | 4 |  | 0 | 0 | 1268627.7 | 0 | -1268627.7 |  |  |  |  | 2018-08-31 | 2018-09-10 | 2018-09-11 | 30 | 2018-10-11 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation4 | 04
PSP Substation | 1 | 5 | 6439927.8 | 0 | -6439927.8 | 3991290.99 | 0 | -3991290.99 |  |  |  | 5046458.33 | 2018-09-30 | 2018-10-08 | 2018-10-08 | 30 | 2018-11-07 | 2018-10-16 | 12694557.6 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation5 | 05
PSP Substation | 1 | 6 | 4012970.52 | 0 | -4012970.52 | 3047586.1 | 0 | -3047586.1 |  |  |  | 3047586.1 | 2018-10-31 | 2018-11-10 | 2018-11-11 | 30 | 2018-12-11 | 2018-11-21 | 16707528.12 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation6 | 06
PSP Substation | 1 | 7 | 3355601.28 | 0 | -3355601.28 | 1780094.35 | 0 | -1780094.35 |  |  |  | 2548357.58 | 2018-11-30 | 2018-12-10 | 2018-12-10 | 30 | 2019-01-09 | 2019-01-06 | 20063129.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation7 | 07
PSP Substation | 1 | 8 | 2786776.25 | 0 | -2786776.25 | 1829713.21 | 0 | -1829713.21 |  |  |  | 2116372.52 | 2018-12-31 | 2019-01-12 | 2019-01-16 | 30 | 2019-02-15 | 2019-02-05 | 22849905.65 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation8 | 08
PSP Substation | 1 | 9 | 2055054.9 | 0 | -2055054.9 | 1314287.28 | 0 | -1314287.28 |  |  |  | 1560678.78 | 2019-01-31 | 2019-02-10 | 2019-02-23 | 30 | 2019-03-25 | 2019-04-11 | 24904960.55 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation9 | 09
PSP Substation | 1 | 10 | 4978707.75 | 0 | -4978707.75 | 3264225.8 | 0 | -3264225.8 |  |  |  | 3808343.08 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-23 | 29883668.3 | [6 empty] | 0 | 4978707.75 | 29883668.3 | 3808343.08 | 0 |  |  |  | PSP Substation10 | 010
PSP Substation | 1 | 11 |  | 0 | 0 | 2606365.14 | 0 | -2606365.14 |  |  |  |  | 2019-06-30 | 2019-06-25 | 2019-12-22 | 30 | 2020-01-21 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation11 | 011
PSP Substation | 1 | 12 | 54510.7209 | 0 | -54510.7209 | 28515 | 0 | -28515 |  |  |  | 28515 | 2019-06-30 | 2019-06-25 | 2020-12-06 | 30 | 2021-01-05 | 2020-12-09 | 32341773.9509 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation12 | 012
Rabigh Ext. - Piles | 1 | 1 | 1098993.1 | 824244.82 | -274748.28 | 947881.6 | 2843644.65 | 1895763.05 |  |  |  | 947881.6 | 2024-02-29 | 2024-02-29 | 2024-03-05 | 57 | 2024-05-01 | 2024-03-18 | 1098993.1 |  |  |  |  | 54949.66 |  | 0 | 1098993.1 | 1098993.1 | 947881.6 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles1 | Rabigh PP - Piling Works1
Rabigh Ext. - Piles | 1 | 2 | 1361202.3 | 1020901.72 | -340300.58 | 1174037 | 3091630.75 | 1917593.75 |  |  |  | 1174036.98 | 2024-04-30 | 2024-04-24 | 2024-04-24 | 57 | 2024-06-20 | 2024-05-02 | 2460195.4 |  |  |  |  | 123009.77 |  | 0 | 1361202.3 | 2460195.4 | 1174036.98 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles2 | Rabigh PP - Piling Works2
Rabigh Ext. - Piles | 1 | 3 |  | 840198 | 840198 | 966227 | 2898683.1 | 1932456.1 |  |  |  |  | 2024-04-30 | 2024-05-14 | 2024-05-14 | 57 | 2024-07-10 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles3 | Rabigh PP - Piling Works3
Rabigh Ext. - Piles | 1 | 4 | 2071949.5 | 1553962.12 | -517987.38 | 1787056 | 5361169.32 | 3574113.32 |  |  |  | 1787056.4438 | 2024-05-31 | 2024-06-01 | 2024-06-10 | 57 | 2024-08-06 | 2024-07-08 | 5652409 |  |  |  |  | 282620.45 |  | 0 | 2071949.5 | 5652409 | 1787056.4437 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles4 | Rabigh PP - Piling Works4
Rabigh Ext. - Piles | 1 | 5 |  | 983150.55 | 983150.55 | 1130623 | 3391869.39 | 2261246.39 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-10 | 57 | 2024-09-05 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles5 | Rabigh PP - Piling Works5
Rabigh Ext. - Piles | 1 | 6 |  | 1751171.77 | 1751171.77 | 2013847.54 | 6041514.12 | 4027666.58 |  |  |  |  | 2024-07-31 | 2024-07-31 | 2024-08-14 | 57 | 2024-10-10 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles6 | Rabigh PP - Piling Works6
Rabigh Ext. - Piles | 1 | 7 |  | 2703528.67 | 2703528.67 | 0 | 9327173.91 | 9327173.91 |  |  |  |  | 2024-08-31 | 2024-08-31 | 2024-09-07 | 57 | 2024-11-03 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles7 | Rabigh PP - Piling Works7
Rabigh Ext. - Piles | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-30 | 2024-10-19 | 57 | 2024-12-15 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles8 | Rabigh PP - Piling Works8
Rabigh Ext. -Building | 1 | 1 | 2561755.35 | 2313265.08 | -248490.27 | 2660254.84 | 7980764.49 | 5320509.65 |  |  |  | 2283164.46 | 2024-06-30 | 2024-06-30 | 2024-07-09 | 75 | 2024-09-22 | 2024-07-10 | 2561755.35 |  |  |  |  | 128087.77 |  | 0 | 0 | 0 | 0 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building1 | Rabigh CCPP-Civil1
Rabigh Ext. -Building | 1 | 2 | 5727560.34 | 4110954.32 | -1616606.02 | 4708047.77 | 14182792.41 | 9474744.64 |  |  |  | 4957387.2204 | 2024-07-31 | 2024-07-31 | 2024-08-05 | 75 | 2024-10-19 | 2024-08-25 | 8289315.69 |  |  |  |  | 414465.7845 |  | 0 | 5727560.34 | 8289315.69 | 4957387.2204 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building2 | Rabigh CCPP-Civil2
Rabigh Ext. -Building | 1 | 3 | 5121658.33 | 3935285.21 | -1186373.12 | 0 | 18102311.96 | 18102311.96 |  |  |  | 4088042.3344 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 75 | 2024-11-19 | 2024-09-19 | 13410974.02 |  |  |  |  | 670548.701 |  | 0 | 5121658.33 | 13410974.02 | 4088042.3344 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building3 | Rabigh CCPP-Civil3
Rabigh Ext. -Building | 1 | 4 | 6246650.22 | 0 | -6246650.22 | 0 | 0 | 0 |  |  |  | 4796196.0024 | 2024-09-30 | 2024-09-30 | 2024-10-06 | 75 | 2024-12-20 | 2024-10-23 | 19657624.24 |  |  |  |  | 982881.212 |  | 0 | 6246650.22 | 19657624.24 | 4796196.0024 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building4 | Rabigh CCPP-Civil4
Rabigh Ext. -Building | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-11-03 | 75 | 2025-01-17 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building5 | Rabigh CCPP-Civil5
Radamis-Concrete | 1 | 1 |  | 0 | 0 | 10000000 | 0 | -10000000 | 10000000 |  |  |  | 2022-04-30 | 2022-04-25 | 2022-04-25 | 30 | 2022-05-25 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete1 | 01
Radamis-Concrete | 1 | 2 |  | 0 | 0 | 10000000 | 0 | -10000000 | 10000000 |  |  |  | 2022-05-31 | 2022-05-25 | 2022-05-26 | 30 | 2022-06-25 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete2 | 02
Radamis-Concrete | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-06-30 | 2022-07-07 | 2022-07-03 | 30 | 2022-08-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete3 | 03
Radamis-Concrete | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-07-31 | 2022-07-31 | 2022-08-14 | 30 | 2022-09-13 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete4 | 04
Radamis-Concrete | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete5 | 05
Radamis-Concrete | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete6 | 06
Radamis-Concrete | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete7 | 07
Radamis-Concrete | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete8 | 08
Radamis-Concrete | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-01-31 | 2023-01-25 | 2023-01-30 | 30 | 2023-03-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete9 | 09
Radamis-Concrete | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete10 | 010
Radamis-Concrete | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete11 | 011
Radamis-Concrete | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete12 | 012
Radamis-Concrete | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete13 | 013
Radamis-Concrete | 1 | 14 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete14 | 014
Radamis-Concrete | 1 | 15 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete15 | 015
Radamis-Concrete | 1 | 16 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete16 | 016
Radamis-Concrete | 1 | 17 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete17 | 017
Radamis-Concrete | 1 | 18 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete18 | 018
Radamis-Concrete | 1 | 19 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete19 | 019
Radamis-Concrete | 1 | 20 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete20 | 020
Radamis-Concrete | 1 | 21 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete21 | 021
Radamis-Concrete | 1 | 22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete22 | 022
Radamis-Concrete | 1 | 23 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete23 | 023
Radamis-Concrete | 1 | 24 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete24 | 024
Radamis-Concrete | 1 | 25 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete25 | 025
Radamis-Concrete | 1 | 26 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete26 | 026
Radamis-Concrete | 1 | 27 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete27 | 027
Radamis-Concrete | 1 | 28 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete28 | 028
Radamis-Concrete | 1 | 29 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete29 | 029
Radamis-Concrete | 1 | 30 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete30 | 030
Radamis-H1 Main Builidng | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng1 | 01
Radamis-H1 Main Builidng | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng2 | 02
Radamis-H1 Main Builidng | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng3 | 03
Radamis-H1 Main Builidng | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng4 | 04
Radamis-H1 Main Builidng | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng5 | 05
Radamis-H1 Main Builidng | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng6 | 06
Radamis-H1 Main Builidng | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng7 | 07
Radamis-H1 Main Builidng | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng8 | 08
Radamis-H1 Main Builidng | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng9 | 09
Radamis-H1 Main Builidng | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng10 | 010
Radamis-H1 Main Builidng | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng11 | 011
Radamis-H1 Main Builidng | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng12 | 012
Radamis-H1 Main Builidng | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng13 | 013
Radamis-Rooms Fitout | 1 | 1 |  | 0 | 0 | 250000 | 0 | -250000 | 250000 |  |  |  | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout1 | 01
Radamis-Rooms Fitout | 1 | 2 |  | 0 | 0 | 500000 | 0 | -500000 | 500000 |  |  |  | 2023-07-31 | 2023-07-20 | 2023-08-05 | 30 | 2023-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout2 | 02
Radamis-Rooms Fitout | 1 | 3 |  | 0 | 0 | 15000000 | 0 | -15000000 | 15000000 |  |  |  | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout3 | 03
Radamis-Rooms Fitout | 1 | 4 |  | 0 | 0 | 4000000 | 0 | -4000000 | 4000000 |  |  |  | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout4 | 04
Radamis-Rooms Fitout | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout5 | 05
Radamis-Rooms Fitout | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout6 | 06
Radamis-Rooms Fitout | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout7 | 07
Radamis-Rooms Fitout | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-07 | 30 | 2024-03-08 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout8 | 08
Radamis-Rooms Fitout | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout9 | 09
Radamis-Rooms Fitout | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout10 | 010
Radamis-Rooms Fitout | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout11 | 011
Radamis-Rooms Fitout | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout12 | 012
Radamis-Rooms Fitout | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout13 | 013
Radamis-Rooms Fitout | 1 | 14 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout14 | 014
Radamis-Rooms Fitout | 1 | 15 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout15 | 015
Radamis-Rooms Fitout | 1 | 16 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout16 | 016
Radamis-Rooms Fitout | 1 | 17 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout17 | 017
Radamis-Villas Finishes | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes1 | 01
Radamis-Villas Finishes | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes2 | 02
Radamis-Villas Finishes | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes3 | 03
Radamis-Villas Finishes | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes4 | 04
Radamis-Villas Finishes | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-01-31 | 2023-01-30 | 2023-01-30 | 30 | 2023-03-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes5 | 05
Radamis-Villas Finishes | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes6 | 06
Radamis-Villas Finishes | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes7 | 07
Radamis-Villas Finishes | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes8 | 08
Radamis-Villas Finishes | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes9 | 09
Radamis-Villas Finishes | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes10 | 010
Radamis-Villas Finishes | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes11 | 011
Radamis-Villas Finishes | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes12 | 012
Radamis-Villas Finishes | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes13 | 013
Radamis-Villas Finishes | 1 | 14 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes14 | 014
Radamis-Villas Finishes | 1 | 15 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes15 | 015
Radamis-Villas Finishes | 1 | 16 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes16 | 016
Radamis-Villas Finishes | 1 | 17 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes17 | 017
Radamis-Villas Finishes | 1 | 18 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes18 | 018
Radamis-Villas Finishes | 1 | 19 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes19 | 019
Radamis-Villas Finishes | 1 | 20 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes20 | 020
Radamis-Villas Finishes | 1 | 21 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes21 | 021
Radamis-Villas Finishes | 1 | 22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes22 | 022
Radamis-Villas Finishes | 1 | 23 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes23 | 023
Radamis-Villas Finishes | 1 | 24 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes24 | 024
Radamis-Villas Finishes | 1 | 25 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes25 | 025
Radamis-Villas Finishes | 1 | 26 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes26 | 026
Red Sea Museum | 1 | 1 | 3172518.7149 | 2538014.97 | -634503.7449 | 5218717 | 8756151.66 | 3537434.66 |  |  |  | 3648396.5221 | 2024-04-30 | 2024-04-30 | 2024-05-23 | 70 | 2024-08-01 | 2024-05-23 | 3172518.7149 | [6 empty] | 0 | 3172518.7149 | 3172518.7149 | 3648396.5221 | Red Sea Museum-Bab El-Bunt |  |  |  | Red Sea Museum1 | Red Sea Museum-Bab El-Bunt1
Red Sea Museum | 1 | 2 | 2298644.2851 | 1838915.59 | -459728.6951 | 4414752.93 | 6344258.76 | 1929505.83 |  |  |  | 2114752.93 | 2024-05-31 | 2024-05-31 | 2024-05-23 | 70 | 2024-08-01 | 2024-08-21 | 5471163 |  |  |  |  | 114932 | 114932 | 0 | 2298644.2851 | 5471163 | 2114752.93 | Red Sea Museum-Bab El-Bunt |  |  |  | Red Sea Museum2 | Red Sea Museum-Bab El-Bunt2
Red Sea Museum | 1 | 3 | 1331566 | 1065253.06 | -266312.94 | 4443406 | 3675123.09 | -768282.91 |  |  |  | 1225041 | 2024-08-31 | 2024-09-02 | 2024-09-02 | 70 | 2024-11-11 | 2024-09-02 | 6802729 | [6 empty] | 0 | 1331566 | 6802729 | 1225041 | Red Sea Museum-Bab El-Bunt |  |  |  | Red Sea Museum3 | Red Sea Museum-Bab El-Bunt3
Ring Road - El Marg | 2 | 1 |  | 82038369.78 | 82038369.78 | 45719198.4 | 63763876.2605 | 18044677.8605 |  |  |  |  | 2021-02-28 | 2021-02-20 | 2021-02-20 | 60 | 2021-04-21 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg1 | RING ROAD MARYOTIA EXPANSION1
Ring Road - El Marg | 2 | 2 |  | 33380372.87 | 33380372.87 | 9576635.3 | 19829292.129 | 10252656.829 |  |  |  |  | 2021-03-31 | 2021-04-15 | 2021-04-15 | 60 | 2021-06-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg2 | RING ROAD MARYOTIA EXPANSION2
Ring Road - El Marg | 2 | 3 |  | 28745170.99 | 28745170.99 | 13773926.1 | 25943818.8695 | 12169892.7695 |  |  |  |  | 2021-04-30 | 2021-05-15 | 2021-05-15 | 60 | 2021-07-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg3 | RING ROAD MARYOTIA EXPANSION3
Ring Road - El Marg | 2 | 4 |  | 11371133.17 | 11371133.17 | 4525661.3 | 10132951.9 | 5607290.6 |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-08 | 60 | 2021-08-07 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg4 | RING ROAD MARYOTIA EXPANSION4
Ring Road - El Marg | 2 | 5 |  | 15036563.72 | 15036563.72 | 2097964.3 | 8684506.216 | 6586541.916 |  |  |  |  | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg5 | RING ROAD MARYOTIA EXPANSION5
Ring Road - El Marg | 2 | 6 |  | 8863613 | 8863613 | 1156719 | 7129991.824 | 5973272.824 |  |  |  |  | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg6 | RING ROAD MARYOTIA EXPANSION6
Ring Road - El Marg | 2 | 7 |  | 32591663.95 | 32591663.95 | 2151897.3 | 4667862.096 | 2515964.796 |  |  |  | 25237352 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | [8 empty] | 0 | 0 | 0 | 25237352 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg7 | RING ROAD MARYOTIA EXPANSION7
Ring Road - El Marg | 2 | 8 | 4446069.4 | 7329890.16 | 2883820.76 | 3742254.85 | 6443416.8 | 2701161.95 |  |  |  | 3601316.214 | 2021-09-30 | 2021-09-30 | 2021-10-05 | 60 | 2021-12-04 | 2021-10-24 | 142263915.035 | [6 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg8 | RING ROAD MARYOTIA EXPANSION8
Ring Road - El Marg | 2 | 9 | 4763028.235 | 14419705.47 | 9656677.235 | 4020500.85 | 7876622.257 | 3856121.407 |  |  |  | 3858052.8704 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 60 | 2022-01-05 | 2021-11-24 | 147026943.27 | [6 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg9 | RING ROAD MARYOTIA EXPANSION9
Ring Road - El Marg | 2 | 10 | 3312818.46 | 20599647.58 | 17286829.12 | 2795847.4 | 13738602.73 | 10942755.33 |  |  |  | 2683382.9526 | 2021-11-30 | 2021-11-30 | 2021-12-08 | 60 | 2022-02-06 | 2022-01-25 | 150339761.73 | [6 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg10 | RING ROAD MARYOTIA EXPANSION10
Ring Road - El Marg | 2 | 11 |  | 29094868.16 | 29094868.16 | 0.0001 | 3708396.57 | 3708396.5699 |  |  |  |  | 2022-01-31 | 2022-01-31 | 2022-02-02 | 60 | 2022-04-03 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg11 | RING ROAD MARYOTIA EXPANSION11
Ring Road - El Marg | 2 | 12 |  | 19159167.62 | 19159167.62 | 0.0001 | 18678770.82 | 18678770.8199 |  |  |  |  | 2022-02-28 | 2022-02-28 | 2022-03-02 | 60 | 2022-05-01 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg12 | RING ROAD MARYOTIA EXPANSION12
Ring Road - El Marg | 2 | 13 |  | 53815173.27 | 53815173.27 | 0.0001 | 41457209.53 | 41457209.5299 |  |  |  |  | 2022-05-31 | 2022-05-30 | 2022-06-02 | 60 | 2022-08-01 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg13 | RING ROAD MARYOTIA EXPANSION13
Ring Road - Mounib | 2 | 1 |  | 82038369.78 | 82038369.78 | 26333646.7391 | 63763876.2605 | 37430229.5214 |  |  |  |  | 2020-08-31 | 2020-08-31 | 2020-08-31 | 60 | 2020-10-30 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib1 | RING ROAD MARYOTIA EXPANSION1
Ring Road - Mounib | 2 | 2 |  | 33380372.87 | 33380372.87 | 7157243.6 | 19829292.129 | 12672048.529 |  |  |  |  | 2020-10-31 | 2020-10-31 | 2020-10-31 | 60 | 2020-12-30 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib2 | RING ROAD MARYOTIA EXPANSION2
Ring Road - Mounib | 2 | 3 |  | 28745170.99 | 28745170.99 | 10759736.15 | 25943818.8695 | 15184082.7195 |  |  |  |  | 2020-12-31 | 2020-12-31 | 2020-12-31 | 60 | 2021-03-01 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib3 | RING ROAD MARYOTIA EXPANSION3
Ring Road - Mounib | 2 | 4 |  | 11371133.17 | 11371133.17 | 4521989.75 | 10132951.9 | 5610962.15 |  |  |  |  | 2021-01-31 | 2021-01-31 | 2021-02-08 | 60 | 2021-04-09 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib4 | RING ROAD MARYOTIA EXPANSION4
Ring Road - Mounib | 2 | 5 |  | 15036563.72 | 15036563.72 | 6026340.35 | 8684506.216 | 2658165.866 |  |  |  |  | 2021-02-28 | 2021-02-28 | 2021-03-17 | 60 | 2021-05-16 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib5 | RING ROAD MARYOTIA EXPANSION5
Ring Road - Mounib | 2 | 6 |  | 8863613 | 8863613 | 4751540.0144 | 7129991.824 | 2378451.8096 |  |  |  |  | 2021-03-31 | 2021-03-31 | 2021-04-15 | 60 | 2021-06-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib6 | RING ROAD MARYOTIA EXPANSION6
Ring Road - Mounib | 2 | 7 |  | 32591663.95 | 32591663.95 | 3640291.7356 | 4667862.096 | 1027570.3604 |  |  |  |  | 2021-04-30 | 2021-04-30 | 2021-05-15 | 60 | 2021-07-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib7 | RING ROAD MARYOTIA EXPANSION7
Ring Road - Mounib | 2 | 8 |  | 7329890.16 | 7329890.16 | 2701161.75 | 6443416.8 | 3742255.05 |  |  |  |  | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib8 | RING ROAD MARYOTIA EXPANSION8
Ring Road - Mounib | 2 | 9 | 4536613.5882 | 14419705.47 | 9883091.8818 | 3856121.55 | 7876622.257 | 4020500.707 |  |  |  | 3856121.55 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 |  | 98438363.943 | [6 empty] | 0 | 4536613.5882 | 98438363.943 | 3856121.55 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib9 | RING ROAD MARYOTIA EXPANSION9
Ring Road - Mounib | 2 | 10 | 18316815 | 20599647.58 | 2282832.58 | 10942755.35 | 13738602.73 | 2795847.38 |  |  |  | 12662306 | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 |  | 116755178.943 | [6 empty] | 0 | 18316815 | 116755178.943 | 12662306 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib10 | RING ROAD MARYOTIA EXPANSION10
Ring Road - Mounib | 2 | 11 | 30549611.057 | 29094868.16 | -1454742.897 | 3708396 | 3708396.57 | 0.57 |  |  |  | 19857247.187 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | 2021-09-07 | 147304790 | [6 empty] | 0 | 30549611.057 | 147304790 | 19857247.187 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib11 | RING ROAD MARYOTIA EXPANSION11
Ring Road - Mounib | 2 | 12 | 20117126 | 19159167.62 | -957958.38 | 14886673.24 | 18678770.82 | 3792097.58 |  |  |  | 14886673.24 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-10-16 | 167421916 | [6 empty] | 0 | 20117126 | 167421916 | 14886673.24 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib12 | RING ROAD MARYOTIA EXPANSION12
Ring Road - Mounib | 2 | 13 | 56505929 | 53815173.27 | -2690755.73 | 32998633.21 | 41457209.53 | 8458576.32 |  |  |  | 41814387.46 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 60 | 2022-01-07 | 2021-11-13 | 223927845 | [6 empty] | 0 | 56505929 | 223927845 | 41814387.46 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib13 | RING ROAD MARYOTIA EXPANSION13
Ring Road - Mounib | 2 | 14 | 46948185.4 | 44712557.52 | -2235627.88 | 14957307.9 | 14554103.9 | -403204 |  |  |  | 0 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 60 | 2022-02-07 | 2022-12-29 | 270876030.4 | [6 empty] | 0 | 46948185.4 | 270876030.4 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib14 | RING ROAD MARYOTIA EXPANSION14
Ring Road - Mounib | 2 | 15 | 30552404.425 | 29097528.02 | -1454876.405 | 10950094.1 | 11321780.291 | 371686.191 |  |  |  | 0 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-01-20 | 301428434.825 | [6 empty] | 0 | 30552404.425 | 301428434.825 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib15 | RING ROAD MARYOTIA EXPANSION15
Ring Road - Mounib | 2 | 16 | 161507041.625 | 40484939.8 | -121022101.825 | 131490711.85 | 40080090.4 | -91410621.45 |  |  |  | 0 | 2022-06-30 | 2022-07-10 | 2022-07-27 | 60 | 2022-09-25 | 2022-07-27 | 462935476.45 | [6 empty] | 0 | 161507041.625 | 462935476.45 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib16 | RING ROAD MARYOTIA EXPANSION16
Ring Road - Mounib | 2 | 17 | 6933306.55 | 48376193.13 | 41442886.58 | 1170803.2 | 46456883.7495 | 45286080.5495 |  |  |  | 5130646.847 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 60 | 2022-10-09 | 2022-08-10 | 469868783 | [6 empty] | 0 | 6933306.55 | 469868783 | 5130646.847 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib17 | RING ROAD MARYOTIA EXPANSION17
Ring Road - Mounib | 2 | 18 | 4715315.145 | 31753157.62 | 27037842.475 | 2897048.5 | 30929623.491 | 28032574.991 |  |  |  | 3489333.2073 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 | 2022-09-12 | 474584098.145 | [6 empty] | 0 | 4715315.145 | 474584098.145 | 3489333.2073 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib18 | RING ROAD MARYOTIA EXPANSION18
Ring Road - Mounib | 2 | 19 |  | 17982890.24 | 17982890.24 | 1351162.1 | 17532860.3445 | 16181698.2445 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-17 | 60 | 2022-12-16 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib19 | RING ROAD MARYOTIA EXPANSION19
RO Apply -Mech- SSC | 1 | 1 | 2250265.4 | 0 | -2250265.4 | 1730229.07 | 0 | -1730229.07 |  |  |  | 1730229.07 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 2250265.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Apply -Mech- SSC1 | 01
RO Apply -Mech- SSC | 1 | 2 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Apply -Mech- SSC2 | 02
RO Apply -Mech- SSC | 1 | 4 | 4449602.38 | 0 | -4449602.38 | 0.001 | 0 | -0.001 |  |  |  | 1195633.38 | 2023-11-30 | 2023-11-12 | 2023-11-12 | 15 | 2023-11-27 | 2023-12-25 | 8242992.05 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Apply -Mech- SSC4 | 04
RO Eriction | 1 | 1 | 6000000 | 0 | -6000000 | 0 | 0 | 0 |  |  |  | 6660000 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 6000000 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Eriction1 | 01
RO Pump Room | 1 | 1 | 22392582.54 | 0 | -22392582.54 | 0 | 0 | 0 |  |  |  | 2216012.07 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 22392582.54 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump Room1 | 01
RO - Supply - Electric | 1 | 1 | 5322406.46 | 0 | -5322406.46 | 1e-05 | 0 | -1e-05 |  |  |  | 745136.9 | 2023-01-31 | 2023-01-16 | 2023-01-17 | 15 | 2023-02-01 | 2023-01-17 | 5322406.46 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO - Supply - Electric1 | 01
RO - Supply - Electric | 1 | 2 | 3040804.44 | 0 | -3040804.44 | 1e-05 | 0 | -1e-05 |  |  |  | 1847082.53 | 2023-02-28 | 2023-02-16 | 2023-03-08 | 15 | 2023-03-23 | 2023-03-15 | 8363210.9 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO - Supply - Electric2 | 02
RO - Supply - Electric | 1 | 3 | 11778923.84 | 0 | -11778923.84 | 2225665.9095 | 0 | -2225665.9095 |  |  |  | 1649065.6 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 15 | 2023-04-25 | 2023-04-10 | 20142134.74 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO - Supply - Electric3 | 03
RO Supply -Mech- SSC | 1 | 1 | 16503981 | 0 | -16503981 | 13698304.23 | 0 | -13698304.23 |  |  |  | 13698304.23 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-07 | 16503981 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC1 | 01
RO Supply -Mech- SSC | 1 | 2 | 1896616.8 | 0 | -1896616.8 | 1574191.94 | 0 | -1574191.94 |  |  |  | 1574191.94 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-14 | 18400597.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC2 | 02
RO Supply -Mech- SSC | 1 | 3 | 28179089.25 | 0 | -28179089.25 | 8116147.9035 | 0 | -8116147.9035 |  |  |  | 8116147.9 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 28179089.25 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC3 | 03
RO Supply -Mech- SSC | 1 | 4 | 7605000 | 0 | -7605000 | 6312150 | 0 | -6312150 |  |  |  | 6312150 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 15 | 2023-05-16 | 2023-05-08 | 35784089.25 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC4 | 04
RO Supply -Mech- SSC | 1 | 5 | 4510403.17 | 0 | -4510403.17 | 2149698.33 | 0 | -2149698.33 |  |  |  | 3743634.63 | 2023-07-31 | 2023-07-31 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-26 | 40294492.42 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC5 | 05
RO Supply -Mech- SSC | 1 | 8 | 14223589.16 | 0 | -14223589.16 | 0 | 0 | 0 |  |  |  | 1418035.09 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 15 | 2024-03-11 | 2024-02-27 | 54518081.58 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC8 | 08
RO 2 | 1 | 1 | 35549128.54 | 0 | -35549128.54 | 0 | 0 | 0 |  |  |  | 28083811.55 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 35549128.54 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO 21 | 01
RO 2 | 1 | 2 | 1807831.26 | 0 | -1807831.26 | 0 | 0 | 0 |  |  |  | 1880144.51 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 15 | 2024-05-16 | 2024-05-02 | 37356959.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO 22 | 02
RO 2 | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-01 | 15 | 2024-07-16 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO 23 | 03
RO Pump room - SSC - price diff. | 1 | 1 | 14675847.72 | 0 | -14675847.72 | 15849915.53 | 0 | -15849915.53 |  |  |  | 16583707.92 | 2023-02-28 | 2023-03-08 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-13 | 14675847.72 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.1 | 01
RO Pump room - SSC - price diff. | 1 | 2 | 1686530.02 | 0 | -1686530.02 | 918959 | 0 | -918959 |  |  |  | 1905778.92 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-15 | 16362377.74 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.2 | 02
RO Pump room - SSC - price diff. | 1 | 3 | 8704005.47 | 0 | -8704005.47 | 9400325.92 | 0 | -9400325.92 |  |  |  | 9835526.19 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 25066383.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.3 | 03
RO Pump room - SSC - price diff. | 1 | 4 | 6762600 | 0 | -6762600 | 7294244.17 | 0 | -7294244.17 |  |  |  | 7303608 | 2023-04-30 | 2023-05-01 | 2023-05-09 | 15 | 2023-05-24 | 2023-05-09 | 31828983.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.4 | 04
RO.2 | 1 | 1 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 15 | 2023-07-15 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO.21 | 01
Rolling Mill #4-TRAESUEZ | 1 | 1 | 21476647.48 | 1143460 | -20333187.48 | 125716551.51 | 823066.73 | -124893484.78 |  |  |  | 17181317.99 | 2021-12-31 | 2022-01-10 | 2022-01-11 | 42 | 2022-02-22 | 2022-02-28 | 21476647.48 | [6 empty] | 0 | 21476647.48 | 21476647.48 | 17181317.99 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ1 | EGAT New Rolling Mill 41
Rolling Mill #4-TRAESUEZ | 1 | 2 | 13583921.53 | 0 | -13583921.53 | 12106800.04 | 0 | -12106800.04 |  |  |  | 11564103.96 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-22 | 35060569.01 | [6 empty] | 0 | 13583921.53 | 35060569.01 | 11564103.96 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ2 | EGAT New Rolling Mill 42
Rolling Mill #4-TRAESUEZ | 1 | 3 | 12117327 | 0 | -12117327 | 10231445.3 | 0 | -10231445.3 |  |  |  | 10352618.57 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-20 | 47177896.01 | [6 empty] | 0 | 12117327 | 47177896.01 | 10352618.57 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ3 | EGAT New Rolling Mill 43
Rolling Mill #4-TRAESUEZ | 1 | 4 | 8075015.79 | 0 | -8075015.79 | 6596541.38 | 0 | -6596541.38 |  |  |  | 6677291.55 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-17 | 55252911.8 | [6 empty] | 0 | 8075015.79 | 55252911.8 | 6677291.55 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ4 | EGAT New Rolling Mill 44
Rolling Mill #4-TRAESUEZ | 1 | 5 | 9905844.43 | 0 | -9905844.43 | 9293714.72 | 0 | -9293714.72 |  |  |  | 8140659.04 | 2022-05-31 | 2022-06-05 | 2022-06-07 | 42 | 2022-07-19 | 2022-07-06 | 65158756.23 | 7155944.45 | [5 empty] | 0 | 9905844.43 | 65158756.23 | 8140659.04 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ5 | EGAT New Rolling Mill 45
Rolling Mill #4-TRAESUEZ | 1 | 6 | 5743581.36 | 0 | -5743581.36 | 4622509.21 | 0 | -4622509.21 |  |  |  | 4679965.02 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-07 | 70902337.59 |  | 7496344.15 |  |  |  |  | 0 | 5743581.36 | 70902337.59 | 4679965.02 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ6 | EGAT New Rolling Mill 46
Rolling Mill #4-TRAESUEZ | 1 | 7 | 16796950.93 | 0 | -16796950.93 | 13289718.96 | 0 | -13289718.96 |  |  |  | 13457708.47 | 2022-07-31 | 2022-08-05 | 2022-08-06 | 42 | 2022-09-17 | 2022-08-24 | 87699288.52 |  | 7576935.06 |  |  |  |  | 0 | 16796950.93 | 87699288.52 | 13457708.47 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ7 | EGAT New Rolling Mill 47
Rolling Mill #4-TRAESUEZ | 1 | 8 | 18519200.97 | 0 | -18519200.97 | 16970562.32 | 0 | -16970562.32 |  |  |  | 14944026.92 | 2022-08-31 | 2022-09-10 | 2022-09-12 | 42 | 2022-10-24 | 2022-09-27 | 106218489.49 |  | 8091599.65 |  |  |  |  | 0 | 18519200.97 | 106218489.49 | 14944026.92 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ8 | EGAT New Rolling Mill 48
Rolling Mill #4-TRAESUEZ | 1 | 9 | 17686791.21 | 0 | -17686791.21 | 15728855.47 | 0 | -15728855.47 |  |  |  | 14162374.17 | 2022-09-30 | 2022-10-10 | 2022-10-12 | 42 | 2022-11-23 | 2022-11-07 | 123905280.7 |  | 8143364.44 |  |  |  |  | 0 | 17686791.21 | 123905280.7 | 14162374.17 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ9 | EGAT New Rolling Mill 49
Rolling Mill #4-TRAESUEZ | 1 | 10 | 15395023.2 | 0 | -15395023.2 | 10380808.5 | 0 | -10380808.5 |  |  |  | 12338644.38 | 2022-10-31 | 2022-11-07 | 2022-11-08 | 42 | 2022-12-20 | 2022-12-14 | 139300303.9 |  | 8233867.7 |  |  |  |  | 0 | 15395023.2 | 139300303.9 | 12338644.38 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ10 | EGAT New Rolling Mill 410
Rolling Mill #4-TRAESUEZ | 1 | 11 | 16145745 | 0 | -16145745 | 9072857.69 | 0 | -9072857.69 |  |  |  | 13316234.88 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2023-01-17 | 155446048.9 |  | 9832423.2 |  |  |  |  | 0 | 16145745 | 155446048.9 | 13316234.88 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ11 | EGAT New Rolling Mill 411
Rolling Mill #4-TRAESUEZ | 1 | 12 | 16694409.39 | 0 | -16694409.39 | 13213191.25 | 0 | -13213191.25 |  |  |  | 13380155.34 | 2022-12-31 | 2023-01-15 | 2023-01-18 | 42 | 2023-03-01 | 2023-02-07 | 172140458.29 |  | 9930934.56 |  |  |  |  | 0 | 16694409.39 | 172140458.29 | 13380155.34 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ12 | EGAT New Rolling Mill 412
Rolling Mill #4-TRAESUEZ | 1 | 13 | 14485776.58 | 0 | -14485776.58 | 1e-05 | 0 | -1e-05 |  |  |  | 11700102.46 | 2023-01-31 | 2023-02-15 | 2023-02-16 | 42 | 2023-03-30 | 2023-03-08 | 186626234.87 |  | 10376859 |  |  |  |  | 0 | 14485776.58 | 186626234.87 | 11700102.46 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ13 | EGAT New Rolling Mill 413
Rolling Mill #4-TRAESUEZ | 1 | 14 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-02-28 | 2023-03-10 | 2023-03-20 | 42 | 2023-05-01 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ14 | EGAT New Rolling Mill 414
Rolling Mill #4-TRAESUEZ | 1 | 15 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ15 | EGAT New Rolling Mill 415
Rolling Mill #4-TRAESUEZ | 1 | 16 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ16 | EGAT New Rolling Mill 416
Rolling Mill #4-TRAESUEZ | 1 | 17 | 619836241 | 0 | -619836241 | 0 | 0 | 0 |  |  |  | 385850750.2 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 619836241 | [6 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ17 | EGAT New Rolling Mill 417
Rolling Mill #4-TRAESUEZ | 1 | 18 | 16836028.82 | 0 | -16836028.82 | 0 | 0 | 0 |  |  |  | 17509470.02 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 636672269.82 |  | 105081618.32 |  |  |  |  | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ18 | EGAT New Rolling Mill 418
Rolling Mill #4-TRAESUEZ | 1 | 19 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ19 | EGAT New Rolling Mill 419
Royal City | 1 | 2 | 8875548.87 | 6435307.71 | -2440241.16 | 4892835.45 | 8900359.4055 | 4007523.9555 |  |  |  | 5235331.6 | 2017-09-30 | 2017-09-30 | 2017-10-01 | 34 | 2017-11-04 | 2017-10-11 | 8875548.87 | 3953206.73 | [5 empty] | 34013.75 | 5127541.59 | 9046023.16 | 5203476.09 | Royal City |  |  |  | Royal City2 | Royal City2
Royal City | 1 | 3 | 8111601.4206 | 9780613.71 | 1669012.2894 | 7926742.1 | 10347291.0455 | 2420548.9455 |  |  |  | 7926742.1 | 2017-10-31 | 2017-10-31 | 2017-11-04 | 34 | 2017-12-08 | 2017-11-14 | 16987150.2906 | 5848040.712 | [5 empty] | 103062.25 | 8536189.79 | 17411738.66 | 8396278.07 | Royal City |  |  |  | Royal City3 | Royal City3
Royal City | 1 | 4 | 10259671.7094 | 4548914.9 | -5710756.8094 | 10437271.65 | 4400341.915 | -6036929.735 |  |  |  | 10437271.65 | 2017-11-30 | 2017-12-03 | 2017-12-03 | 34 | 2018-01-06 | 2017-12-24 | 27246822 | 8775298.38 | [5 empty] | 103062.25 | 0 | 0 | 0 | Royal City |  |  |  | Royal City4 | Royal City4
Royal City | 1 | 5 | 11565536.4187 | 9626900.5 | -1938635.9187 | 5169557.65 | 7170078.235 | 2000520.585 |  |  |  | 6381832.9445 | 2017-12-31 | 2017-12-30 | 2018-01-03 | 34 | 2018-02-06 | 2018-01-22 | 38812358.4187 | 5702856.6 | [5 empty] | 166539 | 11565536.4187 | 38812358.4187 | 6381832.9445 | Royal City |  |  |  | Royal City5 | Royal City5
Royal City | 1 | 6 | 15834199.4413 | 29417027.49 | 13582828.0487 | 12495801.4 | 21736703.6495 | 9240902.2495 |  |  |  | 12495801.39 | 2018-03-31 | 2018-03-31 | 2018-02-20 | 34 | 2018-03-26 | 2018-05-21 | 54646557.86 | 3811475.98 | [5 empty] | 348145 | 17361811.89 | 54716858.14 | 11493260.03 | Royal City |  |  |  | Royal City6 | Royal City6
Royal City | 1 | 7 | 11881365.61 | 17794057.54 | 5912691.93 | 8703262.4 | 15145986.237 | 6442723.837 |  |  |  | 8703262.41 | 2018-04-30 | 2018-04-30 | 2018-05-07 | 34 | 2018-06-10 | 2018-06-11 | 66527923.47 | 3172251.35 | [5 empty] | 582017.44 | 11988097.7 | 66634655.56 | 8439569.37 | Royal City |  |  |  | Royal City7 | Royal City7
Royal City | 1 | 8 | 7845708.0075 | 24651268.82 | 16805560.8125 | 6085844.5 | 18753229.9225 | 12667385.4225 |  |  |  | 7600061.0338 | 2018-05-31 | 2018-05-31 | 2018-06-05 | 34 | 2018-07-09 | 2018-06-24 | 74373631.4775 | 5502031.137 | [5 empty] | 2646288.4432 | 7845708.0075 | 74373631.4775 | 7600061.0338 | Royal City |  |  |  | Royal City8 | Royal City8
Royal City | 1 | 9 | 7890492.132 | 13776239.27 | 5885747.138 | 6397146.2 | 13382223.5235 | 6985077.3235 |  |  |  | 6018082.2865 | 2018-06-30 | 2018-06-30 | 2018-07-10 | 34 | 2018-08-13 | 2018-07-26 | 82264123.6095 | 5685747.237 | [5 empty] | 3049998.998 | 7890492.132 | 82264123.6095 | 6018082.2865 | Royal City |  |  |  | Royal City9 | Royal City9
Royal City | 1 | 10 | 8199169.349 | 11745905.81 | 3546736.461 | 5786688.5 | 8903897.6715 | 3117209.1715 |  |  |  | 5554331.9836 | 2018-07-31 | 2018-07-31 | 2018-08-08 | 34 | 2018-09-11 | 2018-08-27 | 90463292.9586 | 4944412.0842 | [5 empty] | 3422890.7078 | 8199169.349 | 90463292.9586 | 5554331.9836 | Royal City |  |  |  | Royal City10 | Royal City10
Royal City | 1 | 11 | 2707034.9014 | 7770604.14 | 5063569.2386 | 61982306.95 | 8393935.087 | -53588371.863 |  |  |  | 3237608.64 | 2018-08-31 | 2018-08-31 | 2018-09-12 | 34 | 2018-10-16 | 2018-09-24 | 93170327.86 | 6546266.4 | [5 empty] | 3614328.412 | 2707034.9014 | 93170327.86 | 3237608.64 | Royal City |  |  |  | Royal City11 | Royal City11
Royal City | 1 | 12 | 12651464.27 | 21173807.09 | 8522342.82 | 9822648.05 | 16099158.9745 | 6276510.9245 |  |  |  | 8503935.74 | 2018-09-30 | 2018-09-30 | 2018-10-09 | 34 | 2018-11-12 | 2018-11-07 | 105821792.13 | 8045747.81 | [5 empty] | 669617.5401 | 9032801.23 | 102203129.09 | 7860724.87 | Royal City |  |  |  | Royal City12 | Royal City12
Royal City | 1 | 13 | 11315357.62 | 14375270.26 | 3059912.64 | 6339338.45 | 8476906.9292 | 2137568.4792 |  |  |  | 6339338.47 | 2018-10-31 | 2018-10-31 | 2018-11-07 | 34 | 2018-12-11 | 2018-12-04 | 117137149.75 | 6383924.621 | [5 empty] | 0 | 7318551.3313 | 113140343.4613 | 5548576.504 | Royal City |  |  |  | Royal City13 | Royal City13
Royal City | 1 | 14 | 3293171.7405 | 9094787.68 | 5801615.9395 | 5980045.3 | 7268872.3764 | 1288827.0764 |  |  |  | 13062023.4527 | 2018-11-30 | 2018-11-30 | 2018-12-06 | 34 | 2019-01-09 | 2018-12-29 | 120430321.4905 | 8435330.6159 | [5 empty] | 558453.95 | 3293171.7405 | 120430321.4905 | 13062023.4527 | Royal City |  |  |  | Royal City14 | Royal City14
Royal City | 1 | 15 | 16384822.4548 | 11859360.39 | -4525462.0648 | 6570751.8 | 8843457.1828 | 2272705.3828 |  |  |  | 9343372.736 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 34 | 2019-02-09 | 2019-01-20 | 136815143.9453 | 9384080.2453 | [5 empty] | 653055.6603 | 16384822.4548 | 136815143.9453 | 9343372.736 | Royal City |  |  |  | Royal City15 | Royal City15
Royal City | 1 | 16 | 11488490.3339 | 10225071.97 | -1263418.3639 | 7847127.4 | 8700605.8785 | 853478.4785 |  |  |  | 10141562.9942 | 2019-01-31 | 2019-01-31 | 2019-02-07 | 34 | 2019-03-13 | 2019-02-25 | 148303634.2792 | 12235459.3471 | [5 empty] | 320713.8483 | 11488490.3339 | 148303634.2792 | 10141562.9942 | Royal City |  |  |  | Royal City16 | Royal City16
Royal City | 1 | 17 | 9063503.9339 | 9888548.33 | 825044.3961 | 5868379.55 | 7926704.1265 | 2058324.5765 |  |  |  | 6226878.8549 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 34 | 2019-04-09 | 2019-04-01 | 157367138.2131 | 15116649.6688 | [5 empty] | 370976.9746 | 9063503.9339 | 157367138.2131 | 6226878.8549 | Royal City |  |  |  | Royal City17 | Royal City17
Royal City | 1 | 18 | 8621924.8043 | 11007990.23 | 2386065.4257 | 4501953.5 | 5608968.3915 | 1107014.8915 |  |  |  | 6196039.396 | 2019-03-31 | 2019-03-31 | 2019-04-09 | 34 | 2019-05-13 | 2019-04-18 | 165989063.0174 | 14343940.1395 | [5 empty] | 296046.8071 | 8621924.8043 | 165989063.0174 | 6196039.396 | Royal City |  |  |  | Royal City18 | Royal City18
Royal City | 1 | 19 | 15549148.0486 | 15449696.42 | -99451.6286 | 9999974.75 | 11100376.271 | 1100401.521 |  |  |  | 10933183.0202 | 2019-04-30 | 2019-04-30 | 2019-05-08 | 34 | 2019-06-11 | 2019-05-23 | 181538211.066 | 16047073.0222 | [5 empty] | 222365.6932 | 15549148.0486 | 181538211.066 | 10933183.0202 | Royal City |  |  |  | Royal City19 | Royal City19
Royal City | 1 | 20 | 7876990.4815 | 9923971.4 | 2046980.9185 | 5072118 | 6164410 | 1092292 |  |  |  | 5643448.8191 | 2019-05-31 | 2019-05-31 | 2019-06-01 | 34 | 2019-07-05 | 2019-06-26 | 189415201.5475 | 15380569.1286 | [5 empty] | 176894.1812 | 7876990.4815 | 189415201.5475 | 5643448.8191 | Royal City |  |  |  | Royal City20 | Royal City20
Royal City | 1 | 21 | 7532294.3265 | 9561619.77 | 2029325.4435 | 5000000 | 7420122.4285 | 2420122.4285 |  |  |  | 5151160.3487 | 2019-06-30 | 2019-06-30 | 2019-07-08 | 34 | 2019-08-11 | 2019-07-18 | 196947495.8739 | 17429947.3127 | [5 empty] | 252279.4582 | 7532294.3265 | 196947495.8739 | 5151160.3487 | Royal City |  |  |  | Royal City21 | Royal City21
Royal City | 1 | 22 | 24265130.1959 | 21793392.51 | -2471737.6859 | 36824453.7 | 20152080.9255 | -16672372.7745 |  |  |  | 17540056.799 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 34 | 2019-09-08 | 2019-09-02 | 221212626.0698 | 24953179.7402 | [5 empty] | 327502.3224 | 24265130.1959 | 221212626.0698 | 17540056.799 | Royal City |  |  |  | Royal City22 | Royal City22
Royal City | 1 | 23 | 6268692.5562 | 19425445.08 | 13156752.5238 | 6453450.6 | 16168444.0197 | 9714993.4197 |  |  |  | 4319851.8787 | 2019-08-31 | 2019-08-31 | 2019-09-11 |  | 2019-10-18 | 2019-09-28 | 227481318.626 | 25361645.3681 | [5 empty] | 418117.1746 | 6268692.5562 | 227481318.626 | 4319851.8787 | Royal City |  |  |  | Royal City23 | Royal City23
Royal City | 1 | 24 | 17799666.736 | 18486909.34 | 687242.604 | 9088642.9 | 9213642.983 | 125000.083 |  |  |  | 10214838.0645 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-24 | 245280985.3621 | 23478699.1038 | [5 empty] | 383536.5601 | 17799666.736 | 245280985.3621 | 10214838.0645 | Royal City |  |  |  | Royal City24 | Royal City24
Royal City | 1 | 25 | 17503083.0268 | 17584623.17 | 81540.1432 | 9972683.95 | 9972683.9685 | 0.0185 |  |  |  | 12249365.624 | 2019-10-31 | 2019-10-31 | 2019-11-07 | 34 | 2019-12-11 | 2019-11-27 | 262784068.3888 | 23043660.2023 | [5 empty] | 462163.6487 | 17503083.0268 | 262784068.3888 | 12249365.624 | Royal City |  |  |  | Royal City25 | Royal City25
Royal City | 1 | 26 | 10595979.9301 | 0 | -10595979.9301 | 8025338.3 | 0 | -8025338.3 |  |  |  | 7456675.6367 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 273380048.3189 | 22399832.276 | [5 empty] | 481328.1283 | 10595979.9301 | 273380048.3189 | 7456675.6367 | Royal City |  |  |  | Royal City26 | Royal City26
Royal City | 1 | 27 | 20586377.6301 | 23615681.47 | 3029303.8399 | 11895943.7 | 11636419.9 | -259523.8 |  |  |  | 14587648.3106 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 293966425.9491 | 19245051.8837 | [5 empty] | 481881.6236 | 20586377.6301 | 293966425.9491 | 14587648.3106 | Royal City |  |  |  | Royal City27 | Royal City27
Royal City | 1 | 28 | 15640549.4851 | 18900076.14 | 3259526.6549 | 10500306.77 | 10500306.76 | -0.01 |  |  |  | 10986396.5553 | 2020-01-31 | 2020-01-31 | 2020-02-17 | 34 | 2020-03-22 | 2020-03-16 | 309606975.4342 | 16026544.9251 | [5 empty] | 606431.6143 | 15640549.4851 | 309606975.4342 | 10986396.5553 | Royal City |  |  |  | Royal City28 | Royal City28
Royal City | 1 | 29 | 18804604.7977 | 17649893.88 | -1154710.9177 | 12838209.35 | 12838209.344 | -0.006 |  |  |  | 13166441.5288 | 2020-02-29 | 2020-02-29 | 2020-03-18 | 34 | 2020-04-21 | 2020-04-05 | 328411580.2319 | 16972896.7219 | [5 empty] | 637326.7814 | 18804604.7977 | 328411580.2319 | 13166441.5288 | Royal City |  |  |  | Royal City29 | Royal City29
Royal City | 1 | 30 | 13862319.0142 | 16056421.67 | 2194102.6558 | 9831952.135 | 9421690.2835 | -410261.8515 |  |  |  | 9831952.135 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 342273899.2462 | 14581690.3962 | [5 empty] | 637621.4818 | 13862319.0142 | 342273899.2462 | 9831952.135 | Royal City |  |  |  | Royal City30 | Royal City30
Royal City | 1 | 31 | 10234077.8776 | 12028045.18 | 1793967.3024 | 6475508.58 | 6475509.799 | 1.219 |  |  |  | 7550426.1692 | 2020-04-30 | 2020-04-30 | 2020-05-14 | 34 | 2020-06-17 | 2020-07-02 | 352507977.1238 | 12931292.2437 | [5 empty] | 0 | 10234077.8776 | 352507977.1238 | 7550426.1692 | Royal City |  |  |  | Royal City31 | Royal City31
Royal City | 1 | 32 | 3761397.6023 | 4150837.54 | 389439.9377 | 2151533.38 | 2151533.367 | -0.013 |  |  |  | 2648440.2256 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 356269374.7261 | 12829313.7893 | [5 empty] | 0 | 3761397.6023 | 356269374.7261 | 2648440.2256 | Royal City |  |  |  | Royal City32 | Royal City32
Royal City | 1 | 33 | 13830917.4352 | 11787102.13 | -2043815.3052 | 9101413.8171 | 8559155.6765 | -542258.1406 |  |  |  | 9101413.8171 | 2020-06-30 | 2020-06-30 | 2020-07-20 | 34 | 2020-08-23 | 2020-08-12 | 370100292.1612 | 14873462.0847 | [5 empty] | 1198898.3783 | 13830917.4352 | 370100292.1612 | 9101413.8171 | Royal City |  |  |  | Royal City33 | Royal City33
Royal City | 1 | 34 | 7811639.6921 | 0 | -7811639.6921 | 5373442.9261 | 0 | -5373442.9261 |  |  |  | 5373442.9261 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-14 | 377911931.8534 | 13214988.4567 | [5 empty] | 1376502.8422 | 7811639.6921 | 377911931.8534 | 5373442.9261 | Royal City |  |  |  | Royal City34 | Royal City34
Royal City | 1 | 35 | 3980750.5222 | 6572349.74 | 2591599.2178 | 3237336.5863 | 2752213.4436 | -485123.1427 |  |  |  | 3237336.5863 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 381892682.3756 | 10629015.9927 | [5 empty] | 1052872.9373 | 3980750.5222 | 381892682.3756 | 3237336.5863 | Royal City |  |  |  | Royal City35 | Royal City35
Royal City | 1 | 36 | 8343396.9284 | 8120768.31 | -222628.6184 | 5231425.19 | 5231425.2055 | 0.0155 |  |  |  | 5231425.19 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 390236079.304 | 10856647.4404 | [5 empty] | 1034872.9373 | 8343396.9284 | 390236079.304 | 4982664.9588 | Royal City |  |  |  | Royal City36 | Royal City36
Royal City | 1 | 37 | 5412454.8663 | 8335559.1 | 2923104.2337 | 3663343.67 | 3663301.675 | -41.995 |  |  |  | 5574033.5344 | 2020-10-31 | 2020-10-31 | 2020-11-07 | 34 | 2020-12-11 | 2020-11-26 | 395648534.1703 | 7933674.7404 | [5 empty] | 998604.3353 | 5412454.8663 | 395648534.1703 | 5574033.5344 | Royal City |  |  |  | Royal City37 | Royal City37
Royal City | 1 | 38 | 3712322.3219 | 4991557.65 | 1279235.3281 | 2267127.88 | 3951088.5025 | 1683960.6225 |  |  |  | 3838809.8865 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 399360856.4923 | 6223962.4617 | [5 empty] | 944047.2982 | 3712322.3219 | 399360856.4923 | 3838809.8865 | Royal City |  |  |  | Royal City38 | Royal City38
Royal City | 1 | 39 | 1174176.5076 | 1409870.69 | 235694.1824 | 1002773.1926 | 872368.1645 | -130405.0281 |  |  |  | 1002773.1926 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 400535032.9999 | 6288699.0447 | [5 empty] | 899047.2982 | 1174176.5076 | 400535032.9999 | 1002773.1926 | Royal City |  |  |  | Royal City39 | Royal City39
Royal City | 1 | 40 | 5847326.4556 | 7356711.98 | 1509385.5244 | 5979686.67 | 5481051.519 | -498635.151 |  |  |  | 5979686.6716 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 406382359.4555 | 4784431.8697 | [5 empty] | 823521.4569 | 5847326.4556 | 406382359.4555 | 5979686.6716 | Royal City |  |  |  | Royal City40 | Royal City40
Royal City | 1 | 41 | 5256684.0377 | 6547385.9 | 1290701.8623 | 5714023.3138 | 5167630.645 | -546392.6688 |  |  |  | 5714023.3138 | 2021-08-31 | 2021-09-01 | 2021-09-19 | 34 | 2021-10-23 | 2021-11-01 | 411639043.4932 | 3493730 | [5 empty] | 414348.8107 | 5256684.0377 | 411639043.4932 | 5714023.3138 | Royal City |  |  |  | Royal City41 | Royal City41
Royal City | 1 | 42 | 7571387.8468 | 10349949.34 | 2778561.4932 | 35161782.8 | 20407465.3582 | -14754317.4418 |  |  |  | 29397549.59 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 419210431.34 | 715168.5 | 18621503.12 |  | 45928934.7 |  |  | 225000 | 7571387.8468 | 419210431.34 | 29397549.59 | Royal City |  |  |  | Royal City42 | Royal City42
Royal City | 1 | 43 | 13484961.26 | 14387671.43 | 902710.17 | 0 | 0 | 0 |  |  |  | 13488633.46 | 2023-07-31 | 2023-08-08 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 432695392.6 |  | 18307280.08 |  | 46946119.05 |  |  | 225000 | 13484961.26 | 432695392.6 | 13488633.46 | Royal City |  |  |  | Royal City43 | Royal City43
Royal City - Landscape | 1 | 1 |  | 5446175.71 | 5446175.71 | 1782000 | 7019124.6455 | 5237124.6455 |  |  |  | 1800000 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 34 | 2019-09-09 | [8 empty] | 0 | 0 | 0 | 1800000 | Royal City |  |  |  | Royal City - Landscape1 | Royal City1
Royal City - Landscape | 1 | 2 |  | 6435307.71 | 6435307.71 | 4014037.5 | 8900359.4055 | 4886321.9055 |  |  |  | 4032037.5 | 2019-08-31 | 2019-08-31 | 2019-09-11 | 34 | 2019-10-15 | 2019-09-25 |  | 2976050 | [5 empty] | 0 | 0 | 0 | 4032037.5 | Royal City |  |  |  | Royal City - Landscape2 | Royal City2
Royal City - Landscape | 1 | 3 | 341000 | 9780613.71 | 9439613.71 | 2421804.9 | 10347291.0455 | 7925486.1455 |  |  |  | 2443214.8875 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-23 | 341000 | 3475619.85 | [5 empty] | 0 | 341000 | 341000 | 2443214.8875 | Royal City |  |  |  | Royal City - Landscape3 | Royal City3
Royal City - Landscape | 1 | 4 | 2839877.7881 | 4548914.9 | 1709037.1119 | 4390934.75 | 4400341.915 | 9407.165 |  |  |  | 4441415.442 | 2019-10-31 | 2019-10-30 | 2019-11-07 | 34 | 2019-12-11 | 2019-12-25 | 3180877.7881 | 4015635.4285 | [5 empty] | 0 | 2839877.7881 | 3180877.7881 | 4441415.442 | Royal City |  |  |  | Royal City - Landscape4 | Royal City4
Royal City - Landscape | 1 | 5 | 5896802.2265 | 9626900.5 | 3730098.2735 | 7060326.8 | 7170078.235 | 109751.435 |  |  |  | 7147476.0332 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 9077680.0146 | 4953961.135 | [5 empty] | 0 | 5896802.2265 | 9077680.0146 | 7147476.0332 | Royal City |  |  |  | Royal City - Landscape5 | Royal City5
Royal City - Landscape | 1 | 6 | 12932194.6154 | 29417027.49 | 16484832.8746 | 9240902.25 | 21736703.6495 | 12495801.3995 |  |  |  | 9619287.67 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 22009874.63 | 4200873.67 | [5 empty] | 0 | 12932194.6154 | 22009874.63 | 9619287.67 | Royal City |  |  |  | Royal City - Landscape6 | Royal City6
Royal City - Landscape | 1 | 7 | 6479189.8549 | 17794057.54 | 11314867.6851 | 6442723.35 | 15145986.237 | 8703262.887 |  |  |  | 6246175.7955 | 2020-01-31 | 2020-01-31 | 2020-02-11 | 34 | 2020-03-16 | 2020-03-16 | 28489064.4849 | 5725958.7255 | [5 empty] | 0 | 6479189.8549 | 28489064.4849 | 6246175.7955 | Royal City |  |  |  | Royal City - Landscape7 | Royal City7
Royal City - Landscape | 1 | 8 | 17137734.2822 | 24651268.82 | 7513534.5378 | 12356243.75 | 18753229.9225 | 6396986.1725 |  |  |  | 12899186.0747 | 2020-02-29 | 2020-02-29 | 2020-03-17 | 34 | 2020-04-20 | 2020-04-05 | 45626798.7671 | 4930252.4954 | [5 empty] | 0 | 17137734.2822 | 45626798.7671 | 12899186.0747 | Royal City |  |  |  | Royal City - Landscape8 | Royal City8
Royal City - Landscape | 1 | 9 | 6296234.5253 | 13776239.27 | 7480004.7447 | 4886117.91 | 13382223.5235 | 8496105.6135 |  |  |  | 4988413.7416 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 51923033.2924 | 4970424.566 | [5 empty] | 0 | 6296234.5253 | 51923033.2924 | 4988413.7416 | Royal City |  |  |  | Royal City - Landscape9 | Royal City9
Royal City - Landscape | 1 | 10 | 3937848.897 | 11745905.81 | 7808056.913 | 3061010.97 | 8903897.6715 | 5842886.7015 |  |  |  | 3101056.0064 | 2020-04-30 | 2020-04-30 | 2020-05-18 | 34 | 2020-06-21 | 2020-07-02 | 55860882.1894 | 4970424.566 | [5 empty] | 0 | 3937848.897 | 55860882.1894 | 3101056.0064 | Royal City |  |  |  | Royal City - Landscape10 | Royal City10
Royal City - Landscape | 1 | 11 | 5192701.4937 | 7770604.14 | 2577902.6463 | 4947910.42 | 8393935.087 | 3446024.667 |  |  |  | 3973857.736 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 61053583.6831 | 4816564.979 | [5 empty] | 0 | 5192701.4937 | 61053583.6831 | 3973857.736 | Royal City |  |  |  | Royal City - Landscape11 | Royal City11
Royal City - Landscape | 1 | 12 | 8940402.3014 | 21173807.09 | 12233404.7886 | 7029456.4155 | 16099158.9745 | 9069702.559 |  |  |  | 7029456.4155 | 2020-06-30 | 2020-06-30 | 2020-07-19 | 34 | 2020-08-22 | 2020-08-12 | 69993985.9845 | 6160052.1105 | [5 empty] | 0 | 8940402.3014 | 69993985.9845 | 7029456.4155 | Royal City |  |  |  | Royal City - Landscape12 | Royal City12
Royal City - Landscape | 1 | 13 | 3598777.1179 | 14375270.26 | 10776493.1421 | 2173267.6157 | 8476906.9292 | 6303639.3135 |  |  |  | 2173267.6157 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-07 | 73592763.1024 | 4428817.741 | [5 empty] | 0 | 3598777.1179 | 73592763.1024 | 2173267.6157 | Royal City |  |  |  | Royal City - Landscape13 | Royal City13
Royal City - Landscape | 1 | 14 | 2137131.084 | 9094787.68 | 6957656.596 | 1308214.7555 | 7268872.3764 | 5960657.6209 |  |  |  | 1308214.7555 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 75729894.1864 | 3929116.4435 | [5 empty] | 0 | 2137131.084 | 75729894.1864 | 1308214.7555 | Royal City |  |  |  | Royal City - Landscape14 | Royal City14
Royal City - Landscape | 1 | 15 | 3135305.5981 | 11859360.39 | 8724054.7919 | 2272705.37 | 8843457.1828 | 6570751.8128 |  |  |  | 2272705.37 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 78865199.7846 | 3708912.5587 | [5 empty] | 0 | 3135305.5981 | 78865199.7846 | 2303900.245 | Royal City |  |  |  | Royal City - Landscape15 | Royal City15
Royal City - Landscape | 1 | 16 | 1582061.2622 | 10225071.97 | 8643010.7078 | 650222.9433 | 8700605.8785 | 8050382.9352 |  |  |  | 853478.48 | 2020-10-31 | 2020-10-31 | 2020-11-09 | 34 | 2020-12-13 | 2020-11-26 | 80447261.0467 | 3206907.765 | [5 empty] | 0 | 1582061.2622 | 80447261.0467 | 869369.6486 | Royal City |  |  |  | Royal City - Landscape16 | Royal City16
Royal City - Landscape | 1 | 17 | 3716309.8261 | 9888548.33 | 6172238.5039 | 2820044.2305 | 7926704.1265 | 5106659.896 |  |  |  | 2058324.55 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 84163570.8728 | 1876563.015 | [5 empty] | 45000 | 3716309.8261 | 84163570.8728 | 1883835.4255 | Royal City |  |  |  | Royal City - Landscape17 | Royal City17
Royal City - Landscape | 1 | 18 | 1163660.8736 | 11007990.23 | 9844329.3564 | 819297.0816 | 5608968.3915 | 4789671.3099 |  |  |  | 819297.0816 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 85327231.7464 | 1969454.449 | [5 empty] | 0 | 1163660.8736 | 85327231.7464 | 819297.0816 | Royal City |  |  |  | Royal City - Landscape18 | Royal City18
Royal City - Landscape | 1 | 19 | 2029657.8338 | 15449696.42 | 13420038.5862 | 1116339.8935 | 11100376.271 | 9984036.3775 |  |  |  | 1116339.8935 | 2021-01-31 | 2021-01-31 | 2021-02-09 | 34 | 2021-03-15 | 2021-03-02 | 87356889.5802 | 1814848.008 | [5 empty] | 60000 | 2029657.8338 | 87356889.5802 | 1116339.8935 | Royal City |  |  |  | Royal City - Landscape19 | Royal City19
Royal City - Landscape | 1 | 20 | 1366613.9629 | 9923971.4 | 8557357.4371 | 1105876.6944 | 6164410 | 5058533.3056 |  |  |  | 1105876.6944 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 88723503.543 | 1854405.6062 | [5 empty] | 60000 | 1366613.9629 | 88723503.543 | 1105876.6944 | Royal City |  |  |  | Royal City - Landscape20 | Royal City20
Royal City - Landscape | 1 | 21 | 4112536.457 | 9561619.77 | 5449083.313 | 2806313.404 | 7420122.4285 | 4613809.0245 |  |  |  | 3011690.98 | 2021-05-31 | 2021-05-31 | 2021-06-13 | 34 | 2021-07-17 | 2021-07-13 | 92836040 | 1631829.995 | [5 empty] | 120000 | 4112536.457 | 92836040 | 3011690.98 | Royal City |  |  |  | Royal City - Landscape21 | Royal City21
Royal City - Landscape | 1 | 22 | 3299640.8 | 21793392.51 | 18493751.71 | 1838217.2 | 20152080.9255 | 18313863.7255 |  |  |  | 2526109.9 | 2021-08-31 | 2021-09-01 | 2021-09-14 | 34 | 2021-10-18 | 2021-11-01 | 96135680.8 | 1159231.18 | [5 empty] | 165000 | 3299640.8 | 96135680.8 | 2526109.9 | Royal City |  |  |  | Royal City - Landscape22 | Royal City22
Royal City - Landscape | 1 | 23 | 10826725.43 | 19425445.08 | 8598719.65 | 13000000 | 16168444.0197 | 3168444.0197 |  |  |  | 15313915.32 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 106962406.23 | [6 empty] | 165000 | 10826725.43 | 106962406.23 | 15313915.32 | Royal City |  |  |  | Royal City - Landscape23 | Royal City23
Royal City - Landscape | 1 | 24 | 3256136.08 | 18486909.34 | 15230773.26 | 0 | 9213642.983 | 9213642.983 |  |  |  | 3247942.88 | 2023-06-30 | 2023-07-11 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 110218542.31 | [6 empty] | 0 | 3256136.08 | 110218542.31 | 3247942.88 | Royal City |  |  |  | Royal City - Landscape24 | Royal City24
Saint Gobain Factory - DP | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-09-25 | 28 | 2024-10-23 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Saint Gobain Factory - DP1 | 01
SIEMENS - Sokhna | 1 | 1 |  | 0 | 0 | 93300000 | 0 | -93300000 |  |  |  | 93300000 | 2017-11-30 | 2017-11-30 | 2017-11-29 | 45 | 2018-01-13 | 2017-12-06 | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna1 | 01
SIEMENS - Sokhna | 1 | 2 | 4401847.1 | 0 | -4401847.1 | 3059283.73 | 0 | -3059283.73 |  |  |  | 3059283.73 | 2017-12-31 | 2017-12-25 | 2018-01-16 | 45 | 2018-03-02 | 2018-01-16 | 4401847.1 | 0 | [5 empty] | 0 | 4401847.1 | 4401847.1 | 3059283.73 | 0 |  |  |  | SIEMENS - Sokhna2 | 02
SIEMENS - Sokhna | 1 | 3 | 10401972.73 | 0 | -10401972.73 | 7201577.05 | 0 | -7201577.05 |  |  |  | 7201577.05 | 2018-01-31 | 2018-02-03 | 2018-02-05 | 45 | 2018-03-22 | 2018-02-05 | 14803819.83 | 0 | [5 empty] | 27794 | 10401972.73 | 14803819.83 | 7201577.05 | 0 |  |  |  | SIEMENS - Sokhna3 | 03
SIEMENS - Sokhna | 1 | 4 | 15960664.31 | 0 | -15960664.31 | 11065687.7 | 0 | -11065687.7 |  |  |  | 11065687.7 | 2018-02-28 | 2018-03-04 | 2018-03-05 | 45 | 2018-04-19 | 2018-03-14 | 30764484.14 | 0 | [5 empty] | 54768 | 15960664.31 | 30764484.14 | 11065687.7 | 0 |  |  |  | SIEMENS - Sokhna4 | 04
SIEMENS - Sokhna | 1 | 5 | 19051976.33 | 0 | -19051976.33 | 13218163.56 | 0 | -13218163.56 |  |  |  | 13218163.55 | 2018-03-31 | 2018-04-08 | 2018-04-10 | 45 | 2018-05-25 | 2018-04-15 | 49816460.47 | 0 | [5 empty] | 77728 | 19051976.33 | 49816460.47 | 13218163.55 | 0 |  |  |  | SIEMENS - Sokhna5 | 05
SIEMENS - Sokhna | 1 | 6 | 10481549.5128 | 0 | -10481549.5128 | 7060448.908 | 0 | -7060448.908 |  |  |  | 7060448.908 | 2018-04-30 | 2018-05-03 | 2018-05-07 | 45 | 2018-06-21 | 2018-05-20 | 60298009.9828 | 0 | [5 empty] | 301956 | 10481549.5128 | 60298009.9828 | 7060448.908 | 0 |  |  |  | SIEMENS - Sokhna6 | 06
SIEMENS - Sokhna | 1 | 7 | 12587450.0972 | 0 | -12587450.0972 | 8833159.82 | 0 | -8833159.82 |  |  |  | 8833159.82 | 2018-05-31 | 2018-06-06 | 2018-06-14 | 45 | 2018-07-29 | 2018-07-04 | 72885460.08 | 0 | [5 empty] | 217074 | 12587450.0972 | 72885460.08 | 8833159.82 | 0 |  |  |  | SIEMENS - Sokhna7 | 07
SIEMENS - Sokhna | 1 | 8 | 18208993.38 | 0 | -18208993.38 | 12641621.4 | 0 | -12641621.4 |  |  |  | 12641621.4 | 2018-06-30 | 2018-07-05 | 2018-06-28 | 45 | 2018-08-12 | 2018-07-19 | 91094453.46 | 0 | [5 empty] | 230703 | 18208993.38 | 91094453.46 | 12641621.4 | 0 |  |  |  | SIEMENS - Sokhna8 | 08
SIEMENS - Sokhna | 1 | 9 | 19922320.61 | 0 | -19922320.61 | 13673026.82 | 0 | -13673026.82 |  |  |  | 13673026.82 | 2018-07-31 | 2018-08-01 | 2018-08-05 | 45 | 2018-09-19 | 2018-09-03 | 111016774.07 | 0 | [5 empty] | 403689 | 19922320.61 | 111016774.07 | 13673026.82 | 0 |  |  |  | SIEMENS - Sokhna9 | 09
SIEMENS - Sokhna | 1 | 10 | 9128690.32 | 0 | -9128690.32 | 6271528.33 | 0 | -6271528.33 |  |  |  | 6271528.33 | 2018-08-31 | 2018-09-06 | 2018-09-17 | 45 | 2018-11-01 | 2018-09-25 | 120145464.39 | 0 | [5 empty] | 430957 | 9128690.32 | 120145464.39 | 6271528.33 | 0 |  |  |  | SIEMENS - Sokhna10 | 010
SIEMENS - Sokhna | 1 | 11 | 7601906.76 | 0 | -7601906.76 | 5230123.67 | 0 | -5230123.67 |  |  |  | 5230123.66 | 2018-09-30 | 2018-09-30 | 2018-10-01 | 45 | 2018-11-15 | 2018-11-05 | 127747371.15 | 0 | [5 empty] | 446149 | 7601906.76 | 127747371.15 | 5230123.66 | 0 |  |  |  | SIEMENS - Sokhna11 | 011
SIEMENS - Sokhna | 1 | 12 | 28930012.4 | 0 | -28930012.4 | 20041232.56 | 0 | -20041232.56 |  |  |  | 20041232.56 | 2018-10-31 | 2018-10-28 | 2018-10-28 | 45 | 2018-12-12 | 2018-11-07 | 156677383.55 | [6 empty] | 366625 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna12 | 012
SIEMENS - Sokhna | 1 | 13 | 25830140.07 | 0 | -25830140.07 | 17822796.65 | 0 | -17822796.65 |  |  |  | 17822796.65 | 2018-11-30 | 2018-11-22 | 2018-11-22 | 45 | 2019-01-06 | 2018-11-27 | 182507523.62 | [6 empty] | 366625 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna13 | 013
SIEMENS - Sokhna | 1 | 14 | 28983532 | 0 | -28983532 | 20002003.08 | 0 | -20002003.08 |  |  |  | 20002003.08 | 2018-12-31 | 2018-12-09 | 2018-12-19 | 45 | 2019-02-02 | 2019-02-05 | 211491055.62 | [6 empty] | 363259 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna14 | 014
SIEMENS - Sokhna | 1 | 15 | 10573229.89 | 0 | -10573229.89 | 2699428.63 | 0 | -2699428.63 |  |  |  | 2699428.63 | 2018-12-31 | 2018-12-27 | 2019-01-05 | 45 | 2019-02-19 | 2019-02-05 | 222064285.51 | [6 empty] | 4959359 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna15 | 015
SIEMENS - Sokhna | 1 | 16 | 32022484.92 | 0 | -32022484.92 | 25271545.73 | 0 | -25271545.73 |  |  |  | 25271545.73 | 2018-12-31 | 2018-12-30 | 2019-01-15 | 45 | 2019-03-01 | 2019-01-23 | 254086770.43 | [6 empty] | 4959359 | 32022484.92 | 254086770.43 | 25271545.73 | 0 |  |  |  | SIEMENS - Sokhna16 | 016
SIEMENS - Sokhna | 1 | 17 | 57817326.87 | 0 | -57817326.87 | 20418831.59 | 0 | -20418831.59 |  |  |  | 20418831.59 | 2019-02-28 | 2019-02-21 | 2019-01-31 | 45 | 2019-03-17 | 2019-04-22 | 311904097.3 | [6 empty] | 26029681 | 57817326.87 | 311904097.3 | 20418831.59 | 0 |  |  |  | SIEMENS - Sokhna17 | 017
SIEMENS - Sokhna | 1 | 18 | 11495973.02 | 0 | -11495973.02 | 12124718 | 0 | -12124718 |  |  |  | 12124718 | 2019-07-31 | 2019-08-07 | 2019-08-20 | 45 | 2019-10-04 | 2019-10-02 | 323400070.32 | [6 empty] | 20785977 | 0 | 0 | 15000000 | 0 |  |  |  | SIEMENS - Sokhna18 | 018
SIEMENS - Sokhna | 1 | 19 |  | 0 | 0 | 25672200.91 | 0 | -25672200.91 |  |  |  |  | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna19 | 019
SIEMENS - Sokhna | 1 | 20 |  | 0 | 0 | 15319191.73 | 0 | -15319191.73 |  |  |  |  | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 | 2023-10-25 | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna20 | 020
SIEMENS - Sokhna | 1 | 21 |  | 0 | 0 | 888628.7 | 0 | -888628.7 |  |  |  |  | 2020-07-31 | 2020-07-15 | 2020-07-15 | 45 | 2020-08-29 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna21 | 021
SMP1 - Revamp | 1 | 1 | 3199345.21 | 0 | -3199345.21 | 13906048.2 | 0 | -13906048.2 |  |  |  | 2399508.91 | 2022-12-31 | 2023-01-02 | 2023-01-04 | 42 | 2023-02-15 | 2023-02-02 | 3199345.21 | [6 empty] | 0 | 3199345.21 | 3199345.21 | 2399508.91 | 0 |  |  |  | SMP1 - Revamp1 | 01
SMP1 - Revamp | 1 | 2 | 1797569.47 | 0 | -1797569.47 | 25693427.5 | 0 | -25693427.5 |  |  |  | 1348177.1 | 2023-01-31 | 2023-02-14 | 2023-02-15 | 42 | 2023-03-29 | 2023-05-02 | 4996914.68 | [6 empty] | 0 | 1797569.47 | 4996914.68 | 1348177.1 | 0 |  |  |  | SMP1 - Revamp2 | 02
SMP1 - Revamp | 1 | 3 | 2879525.92 | 0 | -2879525.92 | 16806572.5 | 0 | -16806572.5 |  |  |  | 2159644.45 | 2023-04-30 | 2023-05-03 | 2023-05-24 | 42 | 2023-07-05 |  | 7876440.6 | [6 empty] | 0 | 2879525.92 | 7876440.6 | 2159644.45 | 0 |  |  |  | SMP1 - Revamp3 | 03
SMP1 - Revamp | 1 | 4 | 3836789.63 | 0 | -3836789.63 | 2647384.8437 | 0 | -2647384.8437 |  |  |  | 2877592.22 | 2023-05-31 | 2023-06-06 | 2023-07-13 | 42 | 2023-08-24 | 2023-09-01 | 11713230.23 | [6 empty] | 0 | 3836789.63 | 11713230.23 | 2877592.22 | 0 |  |  |  | SMP1 - Revamp4 | 04
SMP1 - Revamp | 1 | 5 | 4135898.1 | 0 | -4135898.1 | 2853769.6857 | 0 | -2853769.6857 |  |  |  | 3101923.57 | 2023-07-31 | 2023-07-25 | 2023-07-25 | 42 | 2023-09-05 | 2023-09-12 | 15849128.33 | [6 empty] | 0 | 4135898.1 | 15849128.33 | 3101923.57 | 0 |  |  |  | SMP1 - Revamp5 | 05
SMP1 - Revamp | 1 | 6 | 8858061.69 | 0 | -8858061.69 | 6112062.5631 | 0 | -6112062.5631 |  |  |  | 6643546.26 | 2023-08-31 | 2023-08-30 | 2023-09-06 | 42 | 2023-10-18 | 2023-10-10 | 24707190.02 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Revamp6 | 06
SMP1 - Revamp | 1 | 7 | 4571797.25 | 0 | -4571797.25 | 3154540.1 | 0 | -3154540.1 |  |  |  | 3428847.94 | 2023-10-31 | 2023-10-15 | 2023-10-15 | 42 | 2023-11-26 | 2023-11-21 | 29278987.27 | [6 empty] | 0 | 4571797.25 | 29278987.27 | 3428847.94 | 0 |  |  |  | SMP1 - Revamp7 | 07
SMP1 - Revamp | 1 | 8 | 2887080.34 | 0 | -2887080.34 | 1992085.4366 | 0 | -1992085.4366 |  |  |  | 2165310.25 | 2023-12-31 | 2023-12-06 | 2023-12-06 | 42 | 2024-01-17 | 2024-01-15 | 32166067.61 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Revamp8 | 08
SMP1 - Revamp | 1 | 9 | 1572976.38 | 0 | -1572976.38 | 0 | 0 | 0 |  |  |  | 1179732.3 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-28 | 33739043.99 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Revamp9 | 09
SMP1 - Revamp | 1 | 10 | 5011477.79 | 0 | -5011477.79 | 0 | 0 | 0 |  |  |  | 3758608.34 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-06-04 | 38750521.78 | [6 empty] | 0 | 5011477.79 | 38750521.78 | 3758608.34 | 0 |  |  |  | SMP1 - Revamp10 | 010
SMP1 - Shut Down | 1 | 1 | 15192302.49 | 0 | -15192302.49 | 5388381.94 | 0 | -5388381.94 |  |  |  | 8203843.34 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2023-10-18 | 15192302.49 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Shut Down1 | 01
SMP1 - Shut Down | 1 | 2 | 17650842.77 | 0 | -17650842.77 | 15140879.8914 | 0 | -15140879.8914 |  |  |  | 9531455.1 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2024-04-07 | 32843145.26 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Shut Down2 | 02
SMP1 - Shut Down | 1 | 3 |  | 0 | 0 | 8648912.9484 | 0 | -8648912.9484 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-04-24 | 42 | 2024-06-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Shut Down3 | 03
SMP2 - Shut Down | 1 | 2 | 17053490.95 | 0 | -17053490.95 | 5426194.9513 | 0 | -5426194.9513 |  |  |  | 5979888.32 | 2023-12-31 | 2023-12-09 | 2023-12-09 | 42 | 2024-01-20 | 2024-01-07 | 49896636.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP2 - Shut Down2 | 02
SMP2 - Shut Down | 1 | 3 | 1490218.79 | 0 | -1490218.79 | 581185.34 | 0 | -581185.34 |  |  |  | 804718.15 | 2024-02-29 | 2024-02-27 | 2024-02-27 | 42 | 2024-04-09 | 2024-04-07 | 51386855 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP2 - Shut Down3 | 03
Sodic Club House | 1 | 23 | 10526350.27 | 4559187 | -5967163.27 | 2727407.25 | 2843967.14 | 116559.89 |  |  |  | 2727407.23 | 2017-09-30 | 2017-09-19 | 2017-11-01 | 35 | 2017-12-06 | 2017-11-05 | 55308912.13 | 10641245.16 | [5 empty] | 83598.95 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House23 | Sodic Club House23
Sodic Club House | 1 | 24 | 6326663.77 | 5827019 | -499644.77 | 4528572.66 | 4702936.55 | 174363.89 |  |  |  | 4528572.66 | 2017-10-31 | 2017-11-01 | 2017-11-03 | 35 | 2017-12-08 | 2017-12-17 | 61635575.9 | 10347994.62 | [5 empty] | 33598.95 | 7208751.86 | 64461008.2542 | 4713913.05 | Sodic Club House |  |  |  | Sodic Club House24 | Sodic Club House24
Sodic Club House | 1 | 25 | 3617825.39 | 1334415.96 | -2283409.43 | 894280.83 | 992455.088 | 98174.258 |  |  |  | 894280.74 | 2017-11-30 | 2017-12-01 | 2017-12-10 | 35 | 2018-01-14 | 2018-01-24 | 65253401.29 | 8215432.94 | [5 empty] | 33598.95 | 4060848.9478 | 65696424.8478 | 1796642.04 | Sodic Club House |  |  |  | Sodic Club House25 | Sodic Club House25
Sodic Club House | 1 | 26 | 4263027.4013 | 2960542.86 | -1302484.5413 | 2563543.65 | 2678644.803 | 115101.153 |  |  |  | 2563543.8087 | 2017-12-31 | 2018-01-16 | 2018-01-16 | 35 | 2018-02-20 | 2018-02-22 | 69516428.6913 | 7922726.9562 | [5 empty] | 33598.95 | 5215631.634 | 70469032.924 | 3193789.29 | Sodic Club House |  |  |  | Sodic Club House26 | Sodic Club House26
Sodic Club House | 1 | 27 | 6447136.9087 | 5615979.81 | -831157.0987 | 7171420.81 | 4546610.8405 | -2624809.9695 |  |  |  | 7171420.74 | 2018-02-28 | 2018-02-20 | 2018-03-01 | 35 | 2018-04-05 | 2018-04-01 | 86100596.85 | 8271503.62 | [5 empty] | 133598.95 | 6347559.6681 | 86021988.3593 | 4891559.01 | Sodic Club House |  |  |  | Sodic Club House27 | Sodic Club House27
Sodic Club House | 1 | 28 | 3235550.4912 | 5110738.79 | 1875188.2988 | 3643251.2 | 5960049.8995 | 2316798.6995 |  |  |  | 3643251.21 | 2018-03-31 | 2018-03-20 | 2018-03-20 | 35 | 2018-04-24 | 2018-05-08 | 89336147.3412 | 10814924.0552 | [5 empty] | 133598.95 | 4455128.7309 | 90555725.5809 | 4314232.28 | Sodic Club House |  |  |  | Sodic Club House28 | Sodic Club House28
Sodic Club House | 1 | 29 | 5735280.6088 | 6355200.49 | 619919.8812 | 2927170 | 6349192.7245 | 3422022.7245 |  |  |  | 2949189.68 | 2018-04-30 | 2018-04-20 | 2018-04-21 | 35 | 2018-05-26 | 2018-05-17 | 95071427.95 | 13429692.21 | [5 empty] | 133598.95 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House29 | Sodic Club House29
Sodic Club House | 1 | 30 | 5753955.1349 | 3864214.5 | -1889740.6349 | 1523667.33 | 3772207.955 | 2248540.625 |  |  |  | 1501648.1708 | 2018-05-31 | 2018-05-25 | 2018-05-28 | 35 | 2018-07-02 | 2018-06-26 | 100825383.0849 | 13579694.3883 | [5 empty] | 39041.91 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House30 | Sodic Club House30
Sodic Club House | 1 | 31 | 4997405.8346 | 2806299.13 | -2191106.7046 | 3752933.22 | 6752933.2165 | 2999999.9965 |  |  |  | 1752933.23 | 2018-06-30 | 2018-07-02 | 2018-07-04 | 35 | 2018-08-08 | 2018-08-02 | 105822788.9195 | 13390603.7948 | [5 empty] | 41801.91 | 9473412.9251 | 110298796.01 | 4843252.93 | Sodic Club House |  |  |  | Sodic Club House31 | Sodic Club House31
Sodic Club House | 1 | 32 | 7298776.2492 | 6867125.7 | -431650.5492 | 1851323.25 | 1852842.635 | 1519.385 |  |  |  | 1851323.2394 | 2018-07-31 | 2018-08-01 | 2018-07-30 | 35 | 2018-09-03 | 2018-09-04 | 113121565.1688 | 11999237.9332 | [5 empty] | 45521.91 | 11500368.6175 | 117323157.537 | 5655167.4 | Sodic Club House |  |  |  | Sodic Club House32 | Sodic Club House32
Sodic Club House | 1 | 33 | 6841826.5835 | 6742632.54 | -99194.0435 | 5028067.13 | 5855002.737 | 826935.607 |  |  |  | 5028067.13 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 35 | 2018-10-11 | 2018-10-09 | 119963391.7522 | 12452865.1519 | [5 empty] | 76081.91 | 7276853.7793 | 124600011.3163 | 7190786.09 | Sodic Club House |  |  |  | Sodic Club House33 | Sodic Club House33
Sodic Club House | 1 | 34 | 9547045.4302 | 7360347.44 | -2186697.9902 | 1372787.19 | 6269587.212 | 4896800.022 |  |  |  | 1372787.19 | 2018-09-30 | 2018-10-15 | 2018-10-15 | 35 | 2018-11-19 | 2018-11-21 | 129510437.1825 | 9699552.55 | [5 empty] | 541161.91 | 14426802.9732 | 134390194.7255 | 10029446.47 | Sodic Club House |  |  |  | Sodic Club House34 | Sodic Club House34
Sodic Club House | 1 | 35 | 17370468.2779 | 4583109.75 | -12787358.5279 | 2061960.96 | 2565043.8775 | 503082.9175 |  |  |  | 2061960.9553 | 2018-11-30 | 2018-11-25 | 2018-11-25 | 35 | 2018-12-30 | 2019-12-20 | 146880905.4603 | 8284813.5766 | [5 empty] | 557361.91 | 10886083.2297 | 140396520.4122 | 6956090.906 | Sodic Club House |  |  |  | Sodic Club House35 | Sodic Club House35
Sodic Club House | 1 | 36 | 15653205.9497 | 29270095.76 | 13616889.8103 | 9516540.66 | 10543541.848 | 1027001.188 |  |  |  | 3000000 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 56 | 2019-08-27 | 2019-12-19 | 162534111.41 | [6 empty] | 4804784.65 | 0 | 0 | 7000000 | Sodic Club House |  |  |  | Sodic Club House36 | Sodic Club House36
Sodic Club House | 1 | 37 |  | 0 | 0 | 4028521 | 0 | -4028521 |  |  |  |  | 2020-08-31 | 2020-08-11 | 2020-08-11 | 56 | 2020-10-06 | [8 empty] | 0 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House37 | Sodic Club House37
Sodic Eastown | 1 | 1 | 9063098.3369 | 9063098.33 | -0.0068571 | 138789620.12 | 6789620.1165 | -132000000.0035 | 122000000 | 10000000 |  | 6785088.5699 | 2019-03-31 | 2019-03-17 | 2019-03-17 | 42 | 2019-04-28 | 2019-03-20 | 9063098.3369 | [6 empty] | 0 | 9063098.3369 | 9063098.3369 | 6785088.5699 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown1 | EDNC Retail & Offices Civil1
Sodic Eastown | 1 | 2 | 20887437.3108 | 20887437.31 | -0.00076191 | 21566541.66 | 15638373.6555 | -5928168.0045 | 5928168 |  |  | 15652355.21 | 2019-04-30 | 2019-04-20 | 2019-04-16 | 42 | 2019-05-28 | 2019-04-18 | 29950535.6476 | [6 empty] | 0 | 20887437.3108 | 29950535.6476 | 15652355.21 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown2 | EDNC Retail & Offices Civil2
Sodic Eastown | 1 | 3 | 2101069.4381 | 2101069.44 | 0.0019048 | 1574016.18 | 1574016.182 | 0.002 |  |  |  | 1574016.17 | 2019-05-31 | 2019-05-20 | 2019-05-19 | 42 | 2019-06-30 | 2019-05-23 | 32051605.0857 | [6 empty] | 0 | 2101069.4381 | 32051605.0857 | 1574016.17 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown3 | EDNC Retail & Offices Civil3
Sodic Eastown | 1 | 4 | 22270031.4 | 36280262.26 | 14010230.86 | 25688338.61 | 26537436.313 | 849097.703 |  |  |  | 26267292.44 | 2019-06-30 | 2019-06-25 | 2019-06-23 | 42 | 2019-08-04 | 2019-07-08 | 54321636.4857 | [6 empty] | 0 | 22270031.4 | 54321636.4857 | 26267292.44 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown4 | EDNC Retail & Offices Civil4
Sodic Eastown | 1 | 5 | 45005158.6118 | 50370296.9 | 5365138.2882 | 37056568.4 | 37056568.405 | 0.005 |  |  |  | 22056568.4027 | 2019-07-31 | 2019-07-25 | 2019-07-25 | 42 | 2019-09-05 | 2019-08-01 | 99326795.0975 | 20344137.6 | [5 empty] | 144395.63 | 45005158.6118 | 99326795.0975 | 22056568.4027 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown5 | EDNC Retail & Offices Civil5
Sodic Eastown | 1 | 6 | 38734277.1501 | 38734277.15 | -9.5248e-05 | 28554847.67 | 28614412.9875 | 59565.3175 |  |  |  | 28554847.68 | 2019-08-31 | 2019-08-25 | 2019-08-19 | 42 | 2019-09-30 | 2019-09-08 | 138061072.2476 | 20344137.6 | [5 empty] | 607331.68 | 38734277.1501 | 138061072.2476 | 28554847.68 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown6 | EDNC Retail & Offices Civil6
Sodic Eastown | 1 | 7 | 65627417.1905 | 46252048.05 | -19375369.1405 | 38197130.95 | 38197130.9705 | 0.0205 |  |  |  |  | 2019-09-30 | 2019-09-25 | 2019-09-16 | 42 | 2019-10-28 | 2019-11-03 | 203688489.4381 | 5537718 | [5 empty] | 921272.68 | 0 | 0 | 38890621.0473 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown7 | EDNC Retail & Offices Civil7
Sodic Eastown | 1 | 8 | 85059782.1524 | 82004688.27 | -3055093.8824 | 55532397.61 | 59087057.7335 | 3554660.1235 |  |  |  | 58794871.95 | 2019-10-31 | 2019-10-30 | 2019-11-02 | 42 | 2019-12-14 | 2019-11-14 | 288748271.5905 | 1266429.46 | [5 empty] | 707331.68 | 85059782.1524 | 288748271.5905 | 58794871.95 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown8 | EDNC Retail & Offices Civil8
Sodic Eastown | 1 | 9 | 16046909.9143 | 19102003.8 | 3055093.8857 | 40504812.26 | 40883545.558 | 378733.298 |  |  |  | 40504812.26 | 2019-11-30 | 2019-11-30 | 2019-12-03 | 42 | 2020-01-14 | 2019-12-30 | 304795181.5048 | 39767000.8 | [5 empty] | 2750976.18 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown9 | EDNC Retail & Offices Civil9
Sodic Eastown | 1 | 10 | 82638241.0762 | 82638241.08 | 0.0038105 | 32553581.24 | 33486093.464 | 932512.224 |  |  |  | 32553581.24 | 2019-12-31 | 2019-12-31 | 2020-01-07 | 42 | 2020-02-18 | 2020-01-20 | 387433422.581 | 1e-06 | [5 empty] | 3038523.68 | 88119712.7238 | 392914894.2286 | 36785436.36 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown10 | EDNC Retail & Offices Civil10
Sodic Eastown | 1 | 11 | 36710088.5775 | 36710088.58 | 0.0025457 | 27179529.3929 | 29504362.289 | 2324832.8961 |  |  |  | 27179529.3929 | 2020-01-31 | 2020-01-31 | 2020-02-03 | 42 | 2020-03-16 | 2020-02-19 | 424143511.1584 | [6 empty] | 3038523.68 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown11 | EDNC Retail & Offices Civil11
Sodic Eastown | 1 | 12 | 26833421.413 | 33309635.84 | 6476214.427 | 19553108.79 | 24940111.3195 | 5387002.5295 |  |  |  | 19553108.77 | 2020-02-29 | 2020-02-29 | 2020-03-04 | 42 | 2020-04-15 | 2020-03-29 | 450976932.5714 | [6 empty] | 3314791.44 | 26833421.413 | 450976932.5714 | 19553108.77 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown12 | EDNC Retail & Offices Civil12
Sodic Eastown | 1 | 13 | 22228765.6121 | 15752551.19 | -6476214.4221 | 16201534.04 | 13698867.9095 | -2502666.1305 |  |  |  | 16201534.04 | 2020-03-31 | 2020-03-24 | 2020-03-25 | 42 | 2020-05-06 | 2020-05-17 | 473205698.1835 | [6 empty] | 2704423.44 | 26192906.0286 | 477169838.6 | 19217788.54 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown13 | EDNC Retail & Offices Civil13
Sodic Eastown | 1 | 14 | 24418089.9689 | 24418089.97 | 0.00114 | 16537461.58 | 17859899.4785 | 1322437.8985 |  |  |  | 16537461.58 | 2020-04-30 | 2020-05-07 | 2020-05-10 | 42 | 2020-06-21 | 2020-06-15 | 497623788.1524 | [6 empty] | 3495935.44 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown14 | EDNC Retail & Offices Civil14
Sodic Eastown | 1 | 15 | 19101976.1176 | 19101976.12 | 0.0023695 | 12895954 | 12895954 | 0 |  |  |  | 12895953.9558 | 2020-05-31 | 2020-06-02 | 2020-06-06 | 42 | 2020-07-18 | 2020-06-23 | 516725764.27 | [6 empty] | 4174771.13 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown15 | EDNC Retail & Offices Civil15
Sodic Eastown | 1 | 16 | 42785902.7013 | 42785902.69 | -0.01126 | 30145771.57 | 31947230.0345 | 1801458.4645 |  |  |  | 30145771.5315 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 42 | 2020-08-15 | 2020-08-10 | 559511666.9713 | [6 empty] | 4707294.52 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown16 | EDNC Retail & Offices Civil16
Sodic Eastown | 1 | 17 | 30425304.0673 | 30425304.07 | 0.00268 | 20899381.34 | 23516460.0735 | 2617078.7335 |  |  |  | 20899381.3823 | 2020-07-31 | 2020-08-08 | 2020-08-10 | 42 | 2020-09-21 | 2020-09-07 | 589936971.0386 | [6 empty] | 5466992.46 | 33693489.0097 | 593205155.981 | 22896073.3381 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown17 | EDNC Retail & Offices Civil17
Sodic Eastown | 1 | 18 | 36663335.5424 | 39729323.85 | 3065988.3076 | 22406610.78 | 26361312.3025 | 3954701.5225 |  |  |  | 22406610.78 | 2020-08-31 | 2020-08-31 | 2020-09-03 | 42 | 2020-10-15 | 2020-10-11 | 626600306.581 | [6 empty] | 5860427.46 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown18 | EDNC Retail & Offices Civil18
Sodic Eastown | 1 | 19 | 48818243.381 | 45752255.09 | -3065988.291 | 34417592.72 | 30462891.204 | -3954701.516 |  |  |  | 34417592.72 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 42 | 2020-11-15 | 2020-11-15 | 675418549.9619 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown19 | EDNC Retail & Offices Civil19
Sodic Eastown | 1 | 20 | 81649174.4522 | 45598330.5 | -36050843.9522 | 31197031.83 | 31197031.845 | 0.015 |  |  |  | 31197031.7827 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 42 | 2020-12-15 | 2020-12-14 | 757067724.4141 | [6 empty] | 6575145.76 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown20 | EDNC Retail & Offices Civil20
Sodic Eastown | 1 | 21 | 8971634.0811 | 45022478.11 | 36050844.0289 | 29743783.32 | 32167186.0755 | 2423402.7555 |  |  |  | 29743783.27 | 2020-11-30 | 2020-11-30 | 2020-12-03 | 42 | 2021-01-14 | 2021-01-20 | 766039358.4952 | [6 empty] | 7317323.76 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown21 | EDNC Retail & Offices Civil21
Sodic Eastown | 1 | 22 | 29539477.0571 | 29539476.98 | -0.077143 | 19964135.7 | 19964135.699 | -0.001 |  |  |  | 19964135.7 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 42 | 2021-02-16 | 2021-02-09 | 795578835.5524 | [6 empty] | 7664787.88 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown22 | EDNC Retail & Offices Civil22
Sodic Eastown | 1 | 23 | 23832998.7215 | 23832998.72 | -0.0014571 | 19672746.63 | 15672746.626 | -4000000.004 |  |  |  | 19672746.6443 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 42 | 2021-03-18 | 2021-03-04 | 819411834.2738 | [6 empty] | 8075062.48 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown23 | EDNC Retail & Offices Civil23
Sodic Eastown | 1 | 24 | 24555503.3928 | 24555503.39 | -0.0028286 | 14713744.17 | 18782844.0895 | 4069099.9195 |  |  |  | 14713744.16 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 42 | 2021-04-18 | 2021-04-11 | 843967337.6667 | [6 empty] | 8705062.48 | 25445155.6214 | 844856989.8952 | 17436083.38 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown24 | EDNC Retail & Offices Civil24
Sodic Eastown | 1 | 25 | 29789861.881 | 29789862.02 | 0.13897 | 18632387.16 | 22686187.95 | 4053800.79 |  |  |  | 18632387.0541 | 2021-03-31 | 2021-03-31 | 2021-04-05 | 42 | 2021-05-17 | 2021-05-18 | 873757199.5477 | [6 empty] | 9572854.12 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown25 | EDNC Retail & Offices Civil25
Sodic Eastown | 1 | 26 | 45459659.9094 | 45459659.77 | -0.13945 | 32407888.61 | 33907888.6085 | 1499999.9985 |  |  |  | 32407888.61 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 42 | 2021-06-16 | 2021-06-17 | 919216859.4571 | [6 empty] | 9252854.12 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown26 | EDNC Retail & Offices Civil26
Sodic Eastown | 1 | 27 | 30032935.1619 | 30032935.16 | -0.0019049 | 21101612.82 | 23241827.868 | 2140215.048 |  |  |  | 21101612.82 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-07-11 | 949249794.619 | [6 empty] | 8752562.48 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown27 | EDNC Retail & Offices Civil27
Sodic Eastown | 1 | 28 | 37125243.7619 | 37125243.76 | -0.0019046 | 41708616.23 | 26708616.218 | -15000000.012 |  |  |  | 41708616.23 | 2021-06-30 | 2021-06-30 | 2021-07-07 | 42 | 2021-08-18 | 2021-08-09 | 986375038.381 | [6 empty] | 11397821.25 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown28 | EDNC Retail & Offices Civil28
Sodic Eastown | 1 | 29 | 26258236.2286 | 26258236.23 | 0.0014285 | 10880905.48 | 20811984.9815 | 9931079.5015 |  |  |  | 10880905.48 | 2021-07-31 | 2021-07-24 | 2021-08-07 | 42 | 2021-09-18 | 2021-09-06 | 1012633274.6095 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown29 | EDNC Retail & Offices Civil29
Sodic Eastown | 1 | 30 | 27535188.381 | 27535188.38 | -0.00095248 | 25479297.36 | 24351196.859 | -1128100.501 |  |  |  | 25479297.36 | 2021-08-31 | 2021-08-31 | 2021-09-07 | 42 | 2021-10-19 | 2021-10-17 | 1040168462.9905 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown30 | EDNC Retail & Offices Civil30
Sodic Eastown | 1 | 31 | 20856328.3905 | 20856328.39 | -0.00047611 | 22493923.41 | 17493923.131 | -5000000.279 |  |  |  | 22493923.51 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 42 | 2021-11-21 | 2021-11-14 | 1061024791.381 | [6 empty] | 9824319.61 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown31 | EDNC Retail & Offices Civil31
Sodic Eastown | 1 | 32 | 17472419.8762 | 17472419.88 | 0.0038096 | 15680621.74 | 19068785.824 | 3388164.084 |  |  |  | 15680621.74 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 42 | 2021-12-20 | 2021-12-07 | 1078497211.2571 | [6 empty] | 9524319.61 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown32 | EDNC Retail & Offices Civil32
Sodic Eastown | 1 | 33 | 15003172.5524 | 15003172.55 | -0.002381 | 19311419.98 | 13807649.9075 | -5503770.0725 |  |  |  | 19311419.98 | 2021-11-30 | 2021-11-30 | 2021-12-07 | 42 | 2022-01-18 | 2021-12-14 | 1093500383.8095 | [6 empty] | 10022759.48 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown33 | EDNC Retail & Offices Civil33
Sodic Eastown | 1 | 34 | 4991381.7048 | 4991381.7 | -0.0047617 | 4602037.61 | 2767127.555 | -1834910.055 |  |  |  | 4602037.62 | 2021-12-31 | 2021-12-31 | 2021-12-27 | 42 | 2022-02-07 | 2022-03-10 | 1098491765.5143 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown34 | EDNC Retail & Offices Civil34
Sodic Eastown | 1 | 35 | 46695355.6476 | 46695355.64 | -0.0076193 | 12555804.9 | 45515831.938 | 32960027.038 |  |  |  | 12555805.27 | 2022-04-30 | 2022-04-30 | 2022-05-18 | 42 | 2022-06-29 | 2022-06-14 | 1145187121.1619 |  | 110343302 |  | -4596809 | 30061161 | 30061161 | 28213034 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown35 | EDNC Retail & Offices Civil35
Sodic Eastown | 1 | 36 | -0.0001 | 0 | 0.0001 | 6254389.49 | 0 | -6254389.49 |  |  |  | 3904269.49 | 2022-07-31 | 2022-08-13 | 2022-08-15 | 42 | 2022-09-26 | 2022-09-12 | 1145187121.1619 |  | 110343302.03 |  | -2378666.59 | 30061161.93 | 30061161.93 | 32117303 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown36 | EDNC Retail & Offices Civil36
Sodic Eastown | 1 | 37 | -1e-05 | 0 | 1e-05 | 5035428.4 | 0 | -5035428.4 |  |  |  | 5035428.4 | 2022-12-31 | 2022-12-26 | 2023-01-01 | 42 | 2023-02-12 | 2023-01-22 | 1145187121.1619 |  | 110343302.03 |  | -2378666.59 | 18874299.6215 | 18874299.6215 | 19273337.4308 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown37 | EDNC Retail & Offices Civil37
Sodic Eastown | 1 | 38 | -0.00011 | 0 | 0.00011 | 2231188 | 0 | -2231188 |  |  |  | 2231188.43 | 2022-06-30 | 2022-06-12 | 2023-06-22 | 42 | 2023-08-03 | 2023-08-01 | 1145187121.1619 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown38 | EDNC Retail & Offices Civil38
Sodic Eastown | 1 | 39 |  | 0 | 0 | 17894573 | 0 | -17894573 |  |  |  | 28315194.9811 | 2023-06-30 | 2023-06-30 | 2023-10-22 | 42 | 2023-12-03 | 2023-10-29 | 1145187121.1619 |  | 110343302.92 |  | -4596809.26 | 30061161.9302 | 30061161.9302 | -12704609.7849 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown39 | EDNC Retail & Offices Civil39
Sodic Eastown - Landscape | 1 | 1 | 1310241.4095 | 1310241.41 | 0.00047619 | 1545976.54 | 1589312.7705 | 43336.2305 |  |  |  | 1545976.52 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 42 | 2022-02-20 | 2022-02-14 | 1310241.4095 | 710231.1 | [5 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape1 | EDNC Hardscape Package1
Sodic Eastown - Landscape | 1 | 2 | 3185965.6857 | 3188822.83 | 2857.1443 | 2689319.17 | 2794789.4915 | 105470.3215 |  |  |  | 2689319.17 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 42 | 2022-03-17 | 2022-03-10 | 4496207.0952 | 1064088.68 | [5 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape2 | EDNC Hardscape Package2
Sodic Eastown - Landscape | 1 | 3 | 5417455.381 | 5414598.24 | -2857.141 | 5060960.68 | 5240048.512 | 179087.832 |  |  |  | 8060960.68 | 2022-03-31 | 2022-03-15 | 2022-03-17 | 42 | 2022-04-28 | 2022-03-31 | 9913662.4762 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape3 | EDNC Hardscape Package3
Sodic Eastown - Landscape | 1 | 4 | 1923818.4 | 1923818.4 | 0 | 4237695.68 | 4301325.99 | 63630.31 |  |  |  | 4237695.69 | 2022-04-30 | 2022-04-13 | 2022-04-13 | 42 | 2022-05-25 | 2022-04-14 | 11837480.8762 | 7645419.29 | [5 empty] | 433157 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape4 | EDNC Hardscape Package4
Sodic Eastown - Landscape | 1 | 5 | 8146275.9524 | 8146275.95 | -0.002381 | 2847434.11 | 3116872.1575 | 269438.0475 |  |  |  | 2847434.08 | 2022-04-30 | 2022-05-10 | 2022-05-11 | 42 | 2022-06-22 | 2022-05-11 | 19983756.8286 | 4687295.11 | 494379.4 |  |  | 641755.99 | 641755.99 | 477225 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape5 | EDNC Hardscape Package5
Sodic Eastown - Landscape | 1 | 6 | 2241713.4381 | 2241713.44 | 0.0019048 | 1865468.85 | 1939613.522 | 74144.672 |  |  |  | 1865468.85 | 2022-05-31 | 2022-05-17 | 2022-05-22 | 42 | 2022-07-03 | 2022-05-24 | 22225470.2667 | 4887618.75 | 704722.2 |  |  | 705609.06 | 705609.06 | 477225 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape6 | EDNC Hardscape Package6
Sodic Eastown - Landscape | 1 | 7 |  | 5611542.56 | 5611542.56 | 2249247.81 | 2434849.578 | 185601.768 |  |  |  |  | 2022-05-31 | 2022-06-10 | 2022-06-14 | 42 | 2022-07-26 | [8 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape7 | EDNC Hardscape Package7
Sodic Eastown - Landscape | 1 | 8 | 19106378.3905 | 16821952.2 | -2284426.1905 | 8937999.74 | 9494386.1475 | 556386.4075 |  |  |  | 13407927.22 | 2022-06-30 | 2022-06-26 | 2022-07-03 | 42 | 2022-08-14 | 2022-07-27 | 46943391.219 | 2302349.81 | 17134472.44 |  |  | 1289822.765 | 1289822.765 | 380000 | 19106378.3905 | 46943391.219 | 13407927.22 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape8 | EDNC Hardscape Package8
Sodic Eastown - Landscape | 1 | 9 | 2763176 | 5047602.19 | 2284426.19 | 837296.03 | 1004245.4695 | 166949.4395 |  |  |  | 837296.04 | 2022-08-31 | 2022-08-25 | 2022-08-30 | 42 | 2022-10-11 | 2022-09-13 | 49706567.219 |  | 17105387 |  |  | 1304797 | 1304797 | 489137 | 2763176 | 49706567.219 | 837296.04 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape9 | EDNC Hardscape Package9
Sodic Eastown - Landscape | 1 | 10 | 3106667.3429 | 3106667.35 | 0.0071429 | 2965081 | 3067833.9875 | 102752.9875 |  |  |  | 2965080.9889 | 2022-08-31 | 2022-08-28 | 2022-10-19 | 42 | 2022-11-30 | 2022-10-20 | 52813234.5619 | [6 empty] | 0 | 1723810.5333 | 51430377.7524 | 5311032.49 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape10 | EDNC Hardscape Package10
Sodic Eastown - Landscape | 1 | 11 | 2478048.6476 | 1095191.83 | -1382856.8176 | 970278.45 | 1006501.9215 | 36223.4715 |  |  |  | 970278.46 | 2022-09-30 | 2022-09-28 | 2022-11-05 | 42 | 2022-12-17 | 2022-11-15 | 53908426.4 |  | 20753354 |  |  |  |  | 581609 | 1095191.5143 | 52525569.2667 | 7657014.05 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape11 | EDNC Hardscape Package11
Sodic Eastown - Landscape | 1 | 12 | 2146120.2476 | 2146120.25 | 0.002381 | 2038310.81 | 2109293.391 | 70982.581 |  |  |  | 2038310.82 | 2022-10-31 | 2022-10-28 | 2022-11-15 | 42 | 2022-12-27 | 2022-11-22 | 56054546.6476 |  | 23518667 |  |  | 1471431.85 | 1471431.85 | 591609 | 1256657.1048 | 55165083.5048 | 8902796.13 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape12 | EDNC Hardscape Package12
Sodic Eastown - Landscape | 1 | 13 |  | 0 | 0 | 4532604.51 | 0 | -4532604.51 |  |  |  |  | 2023-05-31 | 2023-06-01 | 2023-10-16 | 42 | 2023-11-27 | [8 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape13 | EDNC Hardscape Package13
Sokhna Port Expansion | 1 | 1 | 28642092.8 | 86955688.28 | 58313595.48 | 201618177 | 58103513.543 | -143514663.457 |  |  |  | 16602157.8 | 2022-01-31 | 2022-01-31 | 2022-03-14 | 53 | 2022-05-06 | 2022-03-24 | 28642092.8 | [6 empty] | 0 | 28642092.8 | 28642092.8 | 16602157.8 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion1 | Sokhna Port Expansion1
Sokhna Port Expansion | 1 | 2 | 30329196.74 | 52581626.44 | 22252429.7 | 52996310.3 | 29716122.1035 | -23280188.1965 |  |  |  | 19713977.881 | 2022-02-28 | 2022-02-28 | 2022-03-31 | 53 | 2022-05-23 | 2022-04-17 | 58971289.54 | [6 empty] | 0 | 30329196.74 | 58971289.54 | 19713977.881 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion2 | Sokhna Port Expansion2
Sokhna Port Expansion | 1 | 3 |  | 109972559.74 | 109972559.74 | 55802951.65 | 66267866.722 | 10464915.072 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-14 | 53 | 2022-06-06 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion3 | Sokhna Port Expansion3
Sokhna Port Expansion | 1 | 4 | 26384347.91 | 36792580.1 | 10408232.19 | 16604871.85 | 24902787.955 | 8297916.105 |  |  |  | 16604871.85 | 2022-04-30 | 2022-04-30 | 2022-05-25 | 53 | 2022-07-17 | 2022-07-31 | 174022377.11 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion4 | Sokhna Port Expansion4
Sokhna Port Expansion | 1 | 5 | 90184360.23 | 89304785.57 | -879574.66 | 59014964.55 | 62315765.265 | 3300800.715 |  |  |  | 58619834.1495 | 2022-06-30 | 2022-06-30 | 2022-07-28 | 53 | 2022-09-19 | 2022-09-30 | 264206737.34 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion5 | Sokhna Port Expansion5
Sokhna Port Expansion | 1 | 6 | 41088510.15 | 68200901.21 | 27112391.06 | 26209033.35 | 46645772.6455 | 20436739.2955 |  |  |  | 26707531.5975 | 2022-07-31 | 2022-07-31 | 2022-09-19 | 53 | 2022-11-11 | 2022-10-19 | 305295247.49 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion6 | Sokhna Port Expansion6
Sokhna Port Expansion | 1 | 7 |  | 59895486.55 | 59895486.55 | 36803665.95 | 40780441.31 | 3976775.36 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-10-23 | 53 | 2022-12-15 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion7 | Sokhna Port Expansion7
Sokhna Port Expansion | 1 | 8 | 55834648.2 | 52378217.65 | -3456430.55 | 36284090.45 | 36284089.65 | -0.8 |  |  |  | 36284090.45 | 2022-09-30 | 2022-09-30 | 2022-11-16 | 53 | 2023-01-08 | 2022-12-20 | 418825805.92 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion8 | Sokhna Port Expansion8
Sokhna Port Expansion | 1 | 9 | 46210885.16 | 43350211.2 | -2860673.96 | 30030028.45 | 30030028.52 | 0.07 |  |  |  | 30030028.45 | 2022-10-31 | 2022-10-31 | 2022-12-15 | 53 | 2023-02-06 | 2023-01-02 | 465036691.08 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion9 | Sokhna Port Expansion9
Sokhna Port Expansion | 1 | 10 | 42258919.66 | 39642891.35 | -2616028.31 | 27461819.5 | 27461819.55 | 0.05 |  |  |  | 27468297.779 | 2022-11-30 | 2022-11-30 | 2023-01-08 | 53 | 2023-03-02 | 2023-01-24 | 507295610.74 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion10 | Sokhna Port Expansion10
Sokhna Port Expansion | 1 | 11 | 69343976.76 | 73288962.77 | 3944986.01 | 50769799.2 | 50769799.2 | 0 |  |  |  | 50769799.2 | 2022-12-31 | 2022-12-31 | 2023-01-25 | 53 | 2023-03-19 | 2023-07-05 | 576639587.5 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion11 | Sokhna Port Expansion11
Sokhna Port Expansion | 1 | 12 | 106701066.13 | 101620062.95 | -5081003.18 | 70395885.55 | 70395885.55 | 0 |  |  |  | 70395885.55 | 2023-01-31 | 2023-01-31 | 2023-02-13 | 53 | 2023-04-07 | 2023-07-05 | 683340653.63 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion12 | Sokhna Port Expansion12
Sokhna Port Expansion | 1 | 13 | 41939163.73 | 29580920.45 | -12358243.28 | 491489.95 | 491489.95 | 0 |  |  |  | 27260456.4245 | 2023-02-28 | 2023-02-28 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 725279817.36 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion13 | Sokhna Port Expansion13
Sokhna Port Expansion | 1 | 14 | 18010876.44 | 31141539.9 | 13130663.46 | 6704080.85 | 6704080.85 | 0 |  |  |  | 11707069.686 | 2023-03-31 | 2023-03-31 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 743290693.8 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion14 | Sokhna Port Expansion14
Sokhna Port Expansion | 1 | 15 | 15185688.98 | 14245622.5 | -940066.48 | 4368115.65 | 4368115.65 | 0 |  |  |  | 9870697.837 | 2023-04-30 | 2023-04-30 | 2023-07-01 | 53 | 2023-08-23 | 2023-07-15 | 758476382.78 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion15 | Sokhna Port Expansion15
Sokhna Port Expansion | 1 | 16 | 37404208.29 | 35088709.6 | -2315498.69 | 23966243.5 | 23966243.524 | 0.024 |  |  |  | 24312735.3885 | 2023-05-31 | 2023-05-31 | 2023-08-07 | 53 | 2023-09-29 | 2023-08-07 | 795880591.07 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion16 | Sokhna Port Expansion16
Sokhna Port Expansion | 1 | 17 | 22411649.53 | 0 | -22411649.53 | 14567572.19 | 0 | -14567572.19 |  |  |  | 14567572.1945 | 2023-06-30 | 2023-06-30 | 2023-08-27 | 53 | 2023-10-19 | 2023-08-27 | 818292240.6 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion17 | Sokhna Port Expansion17
Sokhna Port Expansion | 1 | 18 |  | 0 | 0 | 14135207.0055 | 0 | -14135207.0055 |  |  |  |  | 2023-07-31 | 2023-07-31 | 2023-07-31 | 53 | 2023-09-22 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion18 | Sokhna Port Expansion18
Sokhna Port Expansion | 1 | 19 | 15685272.2 | 14714279.15 | -970993.05 | 10049896.61 | 10049896.6085 | -0.0015 |  |  |  | 10195426.93 | 2023-08-31 | 2023-08-31 | 2023-08-31 | 53 | 2023-10-23 | 2023-10-17 | 856365557.7 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion19 | Sokhna Port Expansion19
Sokhna Port Expansion | 1 | 20 | 20920498.28 | 19625420 | -1295078.28 | 13204353 | 13204354.1 | 1.1 |  |  |  | 13598323.882 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 53 | 2023-12-17 | 2023-11-20 | 877286055.98 | [6 empty] | 0 | 20920498.28 | 877286055.98 | 13598323.882 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion20 | Sokhna Port Expansion20
Sokhna Port Expansion | 1 | 21 | 9034186.8 | 8474927 | -559259.8 | 5788234 | 5788233.11 | -0.89 |  |  |  | 5872221.42 | 2023-10-31 | 2023-10-31 | 2023-12-27 | 53 | 2024-02-18 | 2023-12-27 | 886320242.78 | [6 empty] | 0 | 9034186.8 | 886320242.78 | 5872221.42 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion21 | Sokhna Port Expansion21
Sokhna Port Expansion | 1 | 22 | 3862923.74 | 3517168 | -345755.74 | 2510900.431 | 2087493.15 | -423407.281 |  |  |  | 2510900.431 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 53 | 2024-04-05 | 2024-02-05 | 890183166.52 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion22 | Sokhna Port Expansion22
Sokhna Port Expansion | 1 | 23 | 943826.94 | 0 | -943826.94 | 568614.519 | 0 | -568614.519 |  |  |  | 613487.511 | 2023-12-31 | 2023-12-31 | 2024-03-09 | 53 | 2024-05-01 | 2024-02-25 | 891126993.46 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion23 | Sokhna Port Expansion23
Sokhna Port Expansion- 100m | 1 | 1 |  | 86955688.28 | 86955688.28 | 39700885.25 | 58103513.543 | 18402628.293 |  |  |  |  | 2023-02-28 | 2023-02-28 | 2023-02-28 | 60 | 2023-04-29 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m1 | Sokhna Port Expansion1
Sokhna Port Expansion- 100m | 1 | 2 | 24129951.39 | 52581626.44 | 28451675.05 | 10628517.75 | 29716122.1035 | 19087604.3535 |  |  |  | 15684468.4035 | 2023-03-31 | 2023-03-31 | 2023-07-01 | 60 | 2023-08-30 | 2023-07-01 | 82118084.22 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m2 | Sokhna Port Expansion2
Sokhna Port Expansion- 100m | 1 | 3 | 26794714.09 | 109972559.74 | 83177845.65 | 10464912.35 | 66267866.722 | 55802954.372 |  |  |  | 17416564.1585 | 2023-04-30 | 2023-04-30 | 2023-08-07 | 60 | 2023-10-06 | 2023-08-07 | 108912798.31 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m3 | Sokhna Port Expansion3
Sokhna Port Expansion- 100m | 1 | 4 | 13246168.7303 | 36792580.1 | 23546411.3697 | 8297916 | 24902787.955 | 16604871.955 |  |  |  | 8610009.6747 | 2023-09-30 | 2023-09-30 | 2023-09-07 | 60 | 2023-11-06 | 2023-10-17 | 122158967.0403 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m4 | Sokhna Port Expansion4
Sokhna Port Expansion- 100m | 1 | 5 | 4703266.4897 | 89304785.57 | 84601519.0803 | 3240800 | 62315765.265 | 59074965.265 |  |  |  | 3057123.2183 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 60 | 2023-12-24 | 2023-11-20 | 126862233.53 | [6 empty] | 0 | 4703266.4897 | 126862233.53 | 3057123.2183 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m5 | Sokhna Port Expansion5
Sokhna Port Expansion- 100m | 1 | 6 | 29655965.57 | 68200901.21 | 38544935.64 | 20436714.5 | 46645772.6455 | 26209058.1455 |  |  |  | 29655965 | 2023-10-31 | 2023-10-31 | 2023-10-25 | 60 | 2023-12-24 | 2023-12-27 | 156518199.1 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m6 | Sokhna Port Expansion6
Sokhna Port Expansion- 100m | 1 | 7 | 4532607.67 | 59895486.55 | 55362878.88 | 3976775.9 | 40780441.31 | 36803665.41 |  |  |  | 2946194.9855 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 60 | 2024-04-12 | 2024-02-05 | 161050806.77 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m7 | Sokhna Port Expansion7
Sokhna Port Expansion-internal roads | 1 | 1 |  | 86955688.28 | 86955688.28 | 1800470.45 | 58103513.543 | 56303043.093 |  |  |  |  | 2022-07-31 | 2022-07-19 | 2022-10-31 | 60 | 2022-12-30 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion-internal roads1 | Sokhna Port Expansion1
Sokhna Port Expansion-internal roads | 1 | 2 |  | 52581626.44 | 52581626.44 | 3219.75 | 29716122.1035 | 29712902.3535 |  |  |  |  | 2022-08-31 | 2022-08-01 | 2022-11-28 | 60 | 2023-01-27 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion-internal roads2 | Sokhna Port Expansion2
Sports Hall - Civil Works | 2 | 3 |  | 142963649.2 | 142963649.2 | 2493330 | 9602955 | 7109625 |  |  |  |  | 2021-01-31 | 2021-01-17 | 2021-01-17 | 60 | 2021-03-18 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works3 | Olympic Multi – Sports Hall3
Sports Hall - Civil Works | 2 | 4 |  | 61004415.08 | 61004415.08 | 10576930 | 14275990 | 3699060 |  |  |  |  | 2021-03-31 | 2021-03-17 | 2021-03-18 | 60 | 2021-05-17 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works4 | Olympic Multi – Sports Hall4
Sports Hall - Civil Works | 2 | 5 | 47849709.5 | 104965807.38 | 57116097.88 | 17108045 | 28228654.99 | 11120609.99 |  |  |  | 17108050 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 60 | 2021-07-30 | 2021-09-13 | 381426324.58 | [6 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works5 | Olympic Multi – Sports Hall5
Sports Hall - Civil Works | 2 | 6 | 51027855.5 | 63397792.5 | 12369937 | 414025 | 10835295 | 10421270 |  |  |  | 414030 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-11-23 | 432454180.08 | [6 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works6 | Olympic Multi – Sports Hall6
Sports Hall - Civil Works | 2 | 7 |  | 16168000 | 16168000 | 0 | 14222372.5 | 14222372.5 |  |  |  | 12888184 | 2021-11-30 | 2021-11-30 | 2021-12-14 | 60 | 2022-02-12 | [8 empty] | 0 | 0 | 0 | 12888184 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works7 | Olympic Multi – Sports Hall7
Sports Hall - Civil Works | 2 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works8 | Olympic Multi – Sports Hall8
Sports Hall - Finishes | 2 | 1 |  | 421069815.32 | 421069815.32 | 1388840 | 62661946.02 | 61273106.02 |  |  |  |  | 2021-05-31 | 2021-05-23 | 2021-05-23 | 60 | 2021-07-22 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes1 | Olympic Multi – Sports Hall1
Sports Hall - Finishes | 2 | 2 |  | 195957824.35 | 195957824.35 | 13091760 | 45292969.02 | 32201209.02 |  |  |  |  | 2021-08-31 | 2021-09-02 | 2021-09-11 | 60 | 2021-11-10 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes2 | Olympic Multi – Sports Hall2
Sports Hall - Finishes | 2 | 3 | 91998353.75 | 142963649.2 | 50965295.45 | 7109625 | 9602955 | 2493330 |  |  |  | 77278617 | 2021-10-31 | 2021-10-31 | 2021-10-11 | 60 | 2021-12-10 | 2021-11-17 | 178494684.93 | [6 empty] | 0 | 91998353.75 | 178494684.93 | 77278617 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes3 | Olympic Multi – Sports Hall3
Sports Hall - Finishes | 2 | 4 |  | 61004415.08 | 61004415.08 | 3699060 | 14275990 | 10576930 |  |  |  |  | 2022-07-31 | 2022-07-31 | 2022-08-09 | 60 | 2022-10-08 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes4 | Olympic Multi – Sports Hall4
Sports Hall - Finishes - ADD.01 | 2 | 1 | 9145259 | 421069815.32 | 411924556.32 | 5941290 | 62661946.02 | 56720656.02 |  |  |  | 5944418.35 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 60 | 2022-03-12 | 2022-02-22 | 9145259 | [6 empty] | 0 | 9145259 | 9145259 | 5944418.35 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes - ADD.011 | Olympic Multi – Sports Hall1
Sports Hall - Finishes - ADD.01 | 2 | 2 |  | 195957824.35 | 195957824.35 | 2631750 | 45292969.02 | 42661219.02 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes - ADD.012 | Olympic Multi – Sports Hall2
Sports Hall - Finishes - Landscape | 2 | 1 |  | 421069815.32 | 421069815.32 | 0.0003 | 62661946.02 | 62661946.0197 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes - Landscape1 | Olympic Multi – Sports Hall1
Sports Hall - MEP | 2 | 1 |  | 421069815.32 | 421069815.32 | 67417715 | 62661946.02 | -4755768.98 |  |  |  |  | 2022-02-28 | 2022-02-24 | 2022-02-24 | 60 | 2022-04-25 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - MEP1 | Olympic Multi – Sports Hall1
Sports Hall - MEP | 2 | 2 |  | 195957824.35 | 195957824.35 | 1103175 | 45292969.02 | 44189794.02 |  |  |  | 13327738 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 13327738 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - MEP2 | Olympic Multi – Sports Hall2
Suez Intake & P Stations-ABB apply | 1 | 1 | 779997.07 | 0 | -779997.07 | 509186.43 | 0 | -509186.43 |  |  |  | 524786.37 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 779997.07 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply1 | 01
Suez Intake & P Stations-ABB apply | 1 | 2 | 1514111.97 | 0 | -1514111.97 | 988420.71 | 0 | -988420.71 |  |  |  | 988420.71 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 2294109.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply2 | 02
Suez Intake & P Stations-ABB apply | 1 | 3 | 1605876.32 | 0 | -1605876.32 | 1048324.9964 | 0 | -1048324.9964 |  |  |  | 1048325 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 3899985.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply3 | 03
Suez Intake & P Stations-ABB apply | 1 | 6 | 6098633.64 | 0 | -6098633.64 | 0 | 0 | 0 |  |  |  | 573225.5 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 9998619 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply6 | 06
Suez Intake & P Stations-ABB supply | 1 | 1 | 5874834 | 0 | -5874834 | 5134498.57 | 0 | -5134498.57 |  |  |  | 5134498.57 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 5874834 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply1 | 01
Suez Intake & P Stations-ABB supply | 1 | 2 | 8551701.56 | 0 | -8551701.56 | 7437727.82 | 0 | -7437727.82 |  |  |  | 7437727.82 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 14426535.56 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply2 | 02
Suez Intake & P Stations-ABB supply | 1 | 3 | 1037578.56 | 0 | -1037578.56 | 814872.95 | 0 | -814872.95 |  |  |  | 814872.96 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 15464114.12 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply3 | 03
Suez Intake & P Stations-ABB supply | 1 | 4 |  | 0 | 0 | 3667977.98 | 0 | -3667977.98 |  |  |  |  | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply4 | 04
Suez Intake & P Stations-ABB supply | 1 | 8 | 24332063.94 | 0 | -24332063.94 | 1e-05 | 0 | -1e-05 |  |  |  | 817934.28 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 40613282 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply8 | 08
Suez Intake & P Stations-SSC apply | 1 | 1 | 1124419.48 | 0 | -1124419.48 | 1102291.62 | 0 | -1102291.62 |  |  |  | 1102291.62 | 2023-01-31 | 2023-01-16 | 2023-01-15 | 42 | 2023-02-26 | 2023-01-16 | 1124419.48 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply1 | 01
Suez Intake & P Stations-SSC apply | 1 | 2 | 3081346.71 | 0 | -3081346.71 | 3020707.78 | 0 | -3020707.78 |  |  |  | 3020707.78 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 4205766.19 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply2 | 02
Suez Intake & P Stations-SSC apply | 1 | 3 | 788338.19 | 0 | -788338.19 | 772824.1924 | 0 | -772824.1924 |  |  |  | 772824.19 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 4994104.38 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply3 | 03
Suez Intake & P Stations-SSC apply | 1 | 7 | 12349144.72 | 0 | -12349144.72 | 0 | 0 | 0 |  |  |  | 6963227.52 | 2024-02-29 | 2024-02-26 | 2024-02-26 | 42 | 2024-04-08 | 2024-02-27 | 17343249.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply7 | 07
Suez Intake & P Stations-SSC apply | 1 | 8 | 1924769.3 | 0 | -1924769.3 | 1886891.07 | 0 | -1886891.07 |  |  |  | 1886891.07 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 19268018.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply8 | 08
Suez Intake & P Stations-SSC supply | 1 | 1 | 10223133.6 | 0 | -10223133.6 | 8726326.42 | 0 | -8726326.42 |  |  |  | 8726335.42 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 10223133.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply1 | 01
Suez Intake & P Stations-SSC supply | 1 | 2 | 3765789.87 | 0 | -3765789.87 | 3190893.09 | 0 | -3190893.09 |  |  |  | 3190884.06 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 13988923.47 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply2 | 02
Suez Intake & P Stations-SSC supply | 1 | 3 | 374122.68 | 0 | -374122.68 | 283552.06 | 0 | -283552.06 |  |  |  | 283552.06 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 14363046.15 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply3 | 03
Suez Intake & P Stations-SSC supply | 1 | 4 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply4 | 04
Suez Intake & P Stations-SSC supply | 1 | 8 | 9321912.4 | 0 | -9321912.4 | 0 | 0 | 0 |  |  |  | 1886800.52 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 24074956.74 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply8 | 08
SVC | 1 | 1 | 3212437.04 | 0 | -3212437.04 | 3375312.6616 | 0 | -3375312.6616 | 1158731.1 |  |  | 2377203.41 | 2024-02-29 | 2024-02-17 | 2024-04-01 | 42 | 2024-05-13 | 2024-04-01 | 3212437.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SVC1 | 01
SVC | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-12 | 42 | 2024-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SVC2 | 02
Uptown PK #53 | 1 | 25 |  | 16867950 | 16867950 | 12009168.61 | 12929508.46 | 920339.85 |  |  |  | 12105864.365 | 2017-09-30 | 2017-10-10 | 2017-11-11 | 40 | 2017-12-21 | 2017-11-28 | 210168675.9558 | 8286463.8075 | [5 empty] | 1299409.2216 | 0 | 0 | 12023138.6423 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5325 | EMAAR-PKG#53-UPTOWN25
Uptown PK #53 | 1 | 26 | 18341001.0169 | 18120127 | -220874.0169 | 13124888.11 | 14111649.09 | 986760.98 |  |  |  | 13230735.7159 | 2017-10-31 | 2017-11-10 | 2017-11-28 | 40 | 2018-01-07 | 2017-12-21 | 228815469.9927 | 6928080.7619 | [5 empty] | 1215618.2216 | 18228071.6884 | 228353712.8741 | 12833527.9648 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5326 | EMAAR-PKG#53-UPTOWN26
Uptown PK #53 | 1 | 27 | 11525442.3347 | 11200624.22 | -324818.1147 | 9593936.7945 | 10524733.29 | 930796.4955 |  |  |  | 9723398.7945 | 2017-11-30 | 2017-12-10 | 2017-12-26 | 40 | 2018-02-04 | 2018-01-08 | 240340912.3274 | 8309746.418 | [5 empty] | 1307409.2216 | 11525442.3347 | 240340912.3274 | 9723398.7945 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5327 | EMAAR-PKG#53-UPTOWN27
Uptown PK #53 | 1 | 28 | 13381649.8939 | 13004518.87 | -377131.0239 | 13320601.43 | 556642.39 | -12763959.04 |  |  |  | 13380241.7057 | 2017-12-31 | 2018-01-10 | 2018-01-16 | 40 | 2018-02-25 | 2018-02-15 | 253722562.2213 | 4669320.168 | [5 empty] | 1464327.5816 | 13381649.8939 | 253722562.2213 | 7567160.0657 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5328 | EMAAR-PKG#53-UPTOWN28
Uptown PK #53 | 1 | 29 | 17500846.4172 | 17007596.13 | -493250.2872 | 10942287.56 | 11883297.1 | 941009.54 |  |  |  | 11043112.6231 | 2018-01-31 | 2018-02-10 | 2018-02-15 | 40 | 2018-03-27 | 2018-03-06 | 271223408.6385 | 3636537.0679 | [5 empty] | 1444327.5816 | 17114848.1247 | 270837410.346 | 10749580.8339 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5329 | EMAAR-PKG#53-UPTOWN29
Uptown PK #53 | 1 | 30 | 15321007.8734 | 0 | -15321007.8734 | 11348802.26 | 0 | -11348802.26 |  |  |  | 11437376.0467 | 2018-02-28 | 2018-03-10 | 2018-03-17 | 40 | 2018-04-26 | 2018-04-04 | 286544416.4997 | 2782555.8001 | [5 empty] | 3125936.127 | 15380090.6234 | 286603499.2497 | 9526356.8077 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5330 | EMAAR-PKG#53-UPTOWN30
Uptown PK #53 | 1 | 31 | 11220346.2103 | 17457747.57 | 6237401.3597 | 7033824.83 | 11753104.21 | 4719279.38 |  |  |  | 7091661.81 | 2018-03-31 | 2018-04-10 | 2018-04-18 | 40 | 2018-05-28 | 2018-05-20 | 297764762.71 | 1008898.49 | [5 empty] | 4001808.9907 | 10847277.7132 | 297391694.2129 | 6774937.5373 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5331 | EMAAR-PKG#53-UPTOWN31
Uptown PK #53 | 1 | 32 | 4916024.5037 | 4777477.68 | -138546.8237 | 2358051.13 | 2883132.62 | 525081.49 |  |  |  | 2387351.5744 | 2018-04-30 | 2018-05-10 | 2018-05-17 | 40 | 2018-06-26 | 2018-05-29 | 302680787.2137 | 878601.9171 | [5 empty] | 4488322.2907 | 4916024.5037 | 302680787.2137 | 2387351.5744 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5332 | EMAAR-PKG#53-UPTOWN32
Uptown PK #53 | 1 | 33 | 3312628.1623 | 3219269.97 | -93358.1923 | 2690853.59 | 2214577.5 | -476276.09 |  |  |  | 2709512.38 | 2018-05-31 | 2018-06-15 | 2018-06-24 | 40 | 2018-08-03 | 2018-07-10 | 305993415.376 | 613573.28 | [5 empty] | 4562822.2907 | 3312628.1576 | 305993415.3712 | 3964599.8564 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5333 | EMAAR-PKG#53-UPTOWN33
Uptown PK #53 | 1 | 34 | 73574.6923 | 62924.2 | -10650.4923 | 1431626.0807 | 1344501.4 | -87124.6807 |  |  |  | 1431626.0807 | 2018-06-30 | 2018-07-10 | 2018-07-17 | 40 | 2018-08-26 | 2018-07-26 | 306066990.0683 | 613573.2833 | [5 empty] | 4285977.9307 | 73574.6923 | 306066990.0683 | 1431626.0807 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5334 | EMAAR-PKG#53-UPTOWN34
Uptown PK #53 | 1 | 35 | 3416261.3696 | 3328558.25 | -87703.1196 | 2466454.76 | 2331143.99 | -135310.77 |  |  |  | 2488623.0127 | 2018-07-31 | 2018-08-10 | 2018-08-16 | 40 | 2018-09-25 | 2018-09-12 | 309483251.4379 | 385285.6486 | [5 empty] | 4958858.9291 | 3416261.3696 | 309483251.4379 | 2488623.0127 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5335 | EMAAR-PKG#53-UPTOWN35
Uptown PK #53 | 1 | 36 | 2041348.5871 | 1983817.89 | -57530.6971 | 2490213.39 | 3652834.8365 | 1162621.4465 |  |  |  | 2502552.38 | 2018-08-31 | 2018-09-10 | 2018-09-19 | 40 | 2018-10-29 | 2018-10-20 | 311524600.025 | 359304.445 | [5 empty] | 4948858.9291 | 2041348.5942 | 311524600.0321 | 4689979.7631 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5336 | EMAAR-PKG#53-UPTOWN36
Uptown PK #53 | 1 | 37 | 1273110.6827 | 0 | -1273110.6827 | 1746850.68 | 0 | -1746850.68 |  |  |  | 1753673.2424 | 2018-09-30 | 2018-10-10 | 2018-10-22 | 40 | 2018-12-01 | 2018-12-16 | 312797710.7077 | 200543.77 | [5 empty] | 5687765.7473 | 1273110.6827 | 312797710.7077 | 1753673.2424 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5337 | EMAAR-PKG#53-UPTOWN37
Uptown PK #53 | 1 | 38 | 747405.6143 | 944067.24 | 196661.6257 | 1902092.11 | 3125949.802 | 1223857.692 |  |  |  | 1048789.58 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 40 | 2019-02-25 | 2019-02-18 | 313545116.322 | 200543.77 | [5 empty] | 6192106.3873 | 747405.6143 | 313545116.322 | 1048789.58 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5338 | EMAAR-PKG#53-UPTOWN38
Uptown PK #53 | 1 | 39 | 32300.9957 | 0 | -32300.9957 | 943725.79 | 0 | -943725.79 |  |  |  | 929614.0301 | 2019-03-31 | 2019-04-10 | 2019-04-11 | 40 | 2019-05-21 | 2019-04-21 | 313577417.3177 | 200543.77 | [5 empty] | 5191842.6873 | 32300.9957 | 313577417.3177 | 929614.0301 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5339 | EMAAR-PKG#53-UPTOWN39
Uptown PK #53 | 1 | 40 | 52815.0023 | 51326.53 | -1488.4723 | 1435222.17 | 11242137.74 | 9806915.57 |  |  |  | 1435222.17 | 2019-05-31 | 2019-06-15 | 2019-06-18 | 40 | 2019-07-28 | 2019-07-16 | 313630232.32 | 200543.77 | [5 empty] | 0 | 52815.0023 | 313630232.32 | 1435222.17 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5340 | EMAAR-PKG#53-UPTOWN40
Uptown PK #53 | 1 | 41 | 0 | 0 | 0 | 4202366.45 | 0 | -4202366.45 |  |  |  | 4202366.45 | 2019-08-31 | 2019-08-15 | 2019-08-20 | 40 | 2019-09-29 | 2019-08-20 | 313630232.32 | 200543.77 | [5 empty] | 0 | 0 | 0 | 4202366.45 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5341 | EMAAR-PKG#53-UPTOWN41
Uptown PK #53 | 1 | 42 | 4356349.94 | 0 | -4356349.94 | 1380970.95 | 0 | -1380970.95 |  |  |  | 1380970.95 | 2019-12-31 | 2019-12-15 | 2019-12-19 | 40 | 2020-01-28 | 2020-01-26 | 317986582.26 | 200543.77 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5342 | EMAAR-PKG#53-UPTOWN42
Uptown PK #53 | 1 | 43 | 3411373.56 | 0 | -3411373.56 | 4834138.97 | 0 | -4834138.97 |  |  |  | 3747539.31 | 2020-02-29 | 2020-02-25 | 2020-03-10 | 40 | 2020-04-19 | 2020-04-15 | 321397955.82 | 200543.77 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5343 | EMAAR-PKG#53-UPTOWN43
Uptown PK #62 | 1 | 7 |  | 2975812 | 2975812 | 1684908.09 | 1863217.83 | 178309.74 |  |  |  | 1684908.08 | 2017-09-30 | 2017-09-30 | 2017-10-04 | 40 | 2017-11-13 | 2017-10-18 | 18419996.59 | 0 | [5 empty] | 136775.69 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #627 | EMAAR-PKG#62-UPTOWN7
Uptown PK #62 | 1 | 8 | 4024169.64 | 3910757 | -113412.64 | 2970870.89 | 3300873.4 | 330002.51 |  |  |  | 2970870.89 | 2017-10-31 | 2017-10-31 | 2017-11-02 | 40 | 2017-12-12 | 2017-11-14 | 22444166.23 | 1403336.04 | [5 empty] | 169833.53 | 4024169.64 | 22444166.23 | 2970870.89 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #628 | EMAAR-PKG#62-UPTOWN8
Uptown PK #62 | 1 | 9 | 3353637.028 | 3259122 | -94515.028 | 2124952.16 | 2334147.17 | 209195.01 |  |  |  | 2124952.16 | 2017-11-30 | 2017-11-30 | 2017-12-04 | 40 | 2018-01-13 | 2017-12-21 | 25797803.258 | 1883218.402 | [5 empty] | 193475.95 | 3353637.028 | 25797803.258 | 2124952.16 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #629 | EMAAR-PKG#62-UPTOWN9
Uptown PK #62 | 1 | 10 | 3315629.905 | 3222186.55 | -93443.355 | 2207449.91 | 2427820.0525 | 220370.1425 |  |  |  | 2207449.91 | 2017-12-31 | 2017-12-27 | 2017-12-30 | 40 | 2018-02-08 | 2018-01-18 | 29113433.163 | 2376274.377 | [5 empty] | 216794.47 | 3315629.905 | 29113433.163 | 2207449.91 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6210 | EMAAR-PKG#62-UPTOWN10
Uptown PK #62 | 1 | 11 | 3273536.577 | 3181279.48 | -92257.097 | 1524280.94 | 1665617.5 | 141336.56 |  |  |  | 1524280.94 | 2018-01-31 | 2018-01-31 | 2018-02-03 | 40 | 2018-03-15 | 2018-02-15 | 32386969.74 | 1872928.9681 | [5 empty] | 233754.86 | 3260036.5785 | 32373469.7415 | 1516852.746 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6211 | EMAAR-PKG#62-UPTOWN11
Uptown PK #62 | 1 | 12 | 2806216.291 | 0 | -2806216.291 | 1565019.14 | 0 | -1565019.14 |  |  |  | 1565019.15 | 2018-02-28 | 2018-02-28 | 2018-03-01 | 40 | 2018-04-10 | 2018-03-18 | 35193186.031 | 1983635.499 | [5 empty] | 291613.6 | 2806216.291 | 35193186.031 | 1565019.15 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6212 | EMAAR-PKG#62-UPTOWN12
Uptown PK #62 | 1 | 13 | 6967775.654 | 0 | -6967775.654 | 2219134.03 | 0 | -2219134.03 |  |  |  | 2219134.03 | 2018-03-31 | 2018-03-31 | 2018-04-02 | 40 | 2018-05-12 | 2018-05-08 | 42160961.685 | 301154.885 | [5 empty] | 1040317.09 | 6967775.65 | 42160961.681 | 3417923.56 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6213 | EMAAR-PKG#62-UPTOWN13
Uptown PK #62 | 1 | 14 | 3891325.445 | 3683223.04 | -208102.405 | 854854.29 | 815558.87 | -39295.42 |  |  |  | 854854.3 | 2018-04-30 | 2018-05-08 | 2018-05-08 | 40 | 2018-06-17 | 2018-06-26 | 46052287.13 | 0 | [5 empty] | 2182913.11 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6214 | EMAAR-PKG#62-UPTOWN14
Uptown PK #62 | 1 | 15 | 1266868.51 | 1329599.07 | 62730.56 | 2299870.99 | 5710409.5735 | 3410538.5835 |  |  |  | 2299870.97 | 2018-07-31 | 2018-07-24 | 2018-08-14 | 40 | 2018-09-23 | 2018-09-06 | 47319155.64 | 0 | [5 empty] | 2396855.11 | 1266868.51 | 47319155.64 | 2299870.97 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6215 | EMAAR-PKG#62-UPTOWN15
Uptown PK #62 | 1 | 16 | -245868.22 | 0 | 245868.22 | 931895.88 | 0 | -931895.88 |  |  |  | 931895.88 | 2018-09-30 | 2018-10-03 | 2018-10-04 | 40 | 2018-11-13 | 2018-11-25 | 47073287.42 | [6 empty] | 1241550.872 | -245868.22 | 47073287.42 | 931895.88 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6216 | EMAAR-PKG#62-UPTOWN16
Uptown PK #62 | 1 | 17 | 0 | 0 | 0 | 419078.79 | 0 | -419078.79 |  |  |  | 419078.79 | 2019-03-31 | 2019-03-25 | 2019-03-24 | 40 | 2019-05-03 | 2019-04-11 | 47073287.42 | [6 empty] | 928608.274 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6217 | EMAAR-PKG#62-UPTOWN17
Uptown PK #62 | 1 | 18 | 0 | 0 | 0 | 864260.36 | 0 | -864260.36 |  |  |  | 864260.36 | 2019-09-30 | 2019-10-09 | 2019-10-09 | 40 | 2019-11-18 | 2019-11-03 | 47073287.42 | [6 empty] | 987399.24 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6218 | EMAAR-PKG#62-UPTOWN18
Uptown PK #62 | 1 | 19 | 22437 | 1831902.3 | 1809465.3 | 1416810.93 | 1275390.455 | -141420.475 |  |  |  | 1195853.88 | 2019-12-31 | 2019-12-18 | 2019-12-19 | 40 | 2020-01-28 | 2020-07-19 | 47095724.42 | [6 empty] | 990172.52 | 22437 | 47095724.42 | 1195853.88 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6219 | EMAAR-PKG#62-UPTOWN19
Wady Halfa | 1 | 1 | 3078932.9 | 64486200.86 | 61407267.96 | 22733360.9 | 22733362.34 | 1.44 | 19000000 |  |  | 33029517.9 | 2022-11-30 | 2022-11-30 | 2022-12-11 | 30 | 2023-01-10 | 2022-12-18 | 3078932.9 | 33200100 | [5 empty] | 0 | 3078932.9 | 3078932.9 | 33029517.9 | Wadi Halfa Port |  |  |  | Wady Halfa1 | Wadi Halfa Port1
Wady Halfa | 1 | 2 | 23601516.1 | 11905090.1 | -11696426 | 8196261.85 | 8196261.45 | -0.4 | 11000000 |  |  | 11905091.98 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 30 | 2023-03-10 | 2023-02-14 | 26680449 | 18254159 | [5 empty] | 0 | 23601516.1 | 26680449 | 11905091.98 | Wadi Halfa Port |  |  |  | Wady Halfa2 | Wadi Halfa Port2
Wady Halfa | 1 | 3 | 17962793.18 | 4077802.86 | -13884990.32 | 2807166.9 | 2807168.5814 | 1.6814 |  |  |  | 14516628.581 | 2023-02-28 | 2023-02-28 | 2023-03-16 | 30 | 2023-04-15 | 2023-03-16 | 44643242.18 | 4370481.56 | [5 empty] | 0 | 17962793.18 | 44643242.18 | 14516628.581 | Wadi Halfa Port |  |  |  | Wady Halfa3 | Wadi Halfa Port3
Wady Halfa | 1 | 4 | 8749053.22 | 4379885.32 | -4369167.9 | 3015154.3 | 3015154.5668 | 0.2668 |  |  |  | 3679103.55 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 30 | 2023-05-10 | 2023-05-08 | 53392295.4 | [6 empty] | 0 | 0 | 0 | 0 | Wadi Halfa Port |  |  |  | Wady Halfa4 | Wadi Halfa Port4
Wady Halfa | 1 | 5 |  | 10144199.04 | 10144199.04 | 2984537.1 | 2984537.1 | 0 |  |  |  |  | 2024-03-31 | 2024-03-15 | 2024-03-15 | 30 | 2024-04-14 | [8 empty] | 0 | 0 | 0 | 0 | Wadi Halfa Port |  |  |  | Wady Halfa5 | Wadi Halfa Port5
Western Fence | 1 | 1 | 762742.21 | 0 | -762742.21 | 418218.39 | 0 | -418218.39 |  |  |  | 792870.53 | 2023-10-31 | 2023-10-31 | 2023-10-30 | 42 | 2023-12-11 | 2023-11-02 | 762742.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Western Fence1 | 01
Zayed Park | 0 | 1 | 191006.802 | 0 | -191006.802 | 505797 | 0 | -505797 |  |  |  | 505797.14 | 2019-10-31 | 2019-10-28 | 2019-10-28 | 30 | 2019-11-27 | 2019-11-07 | 191006.802 | 410791.498 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Zayed Park1 | 01
Zayed Park | 0 | 2 | 842290.974 | 0 | -842290.974 | 264423.21 | 0 | -264423.21 |  |  |  | 352690.39 | 2019-12-31 | 2019-12-31 | 2020-01-11 | 30 | 2020-02-10 | 2020-09-21 | 1033297.776 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Zayed Park2 | 02
|  |  | 19805227693.4556 | 26100751043.7646 | 6295523350.309 | 18501728387.8624 | 18029592404.4756 | -472135983.3868 | 1901673988.52 | 890783556.123 | 40056730.98 | 15454594032.6016 | [7 empty] | 11199832140.5956 | 28218786789.695 | 107915790.6 | 12523278641.5813 | 2970327920.4235 | 2614672939.897 | 2165045374.0028 | [7 empty] | 0
Note on N881: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Claims
Note on N882: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Claims
Note on N1155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Social Insurance
Note on N1156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Social Insurance
Note on N1157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Social Insurance

## inv no new
INV_NUM | inv no. extracted from code | inv no. extracted new
Cls.Adv.Algeria.Old
Guinea9-2016-8 | 2016 | 2016
013/2019
006/2018
029/2021
023/202+L9+L7:Q7
Other Charge/J003
Supply/H009
7-132KVA- H | 132 | 132
6-132KVA | 132 | 132
57001563/4
DEC ADJ 72
542
524
180103
180099
180092
180090
180042
180030
180029
180024
Inv 29 Shabab Egy | 29 | 29
23 EGP - West Domiat
8 EGP - West D. 117
Balance 2016
13 EGP - Shabab 117
17 EGP - Shabab 117
7 EGP - West D. 117
7 USD - West D. 117
3 USD - Shabab 117
180047
16 EGP-progress repo
Inv 4 EGP VO SG | 4 | 4
8 EGP Suez Gulf
481
14 USD Suez Gulf
14 USD - Suez Gulf
11 USD - Suez Gulf
Inv. 16 PIP EAST | 16 | 16
Abo Matamir 1
Inv 63 P15 Banha Fin | 63 | 63
Itay 10 inv.34 | 34 | 34
Itay 11 inv 40 | 40 | 40
Inv.25 Barwa | 25 | 25
Inv 29 Barwa | 29 | 29
Inv 19 Barwa | 19 | 19
7 Barwa
Barwa 13
Inv 27 Damac | 27 | 27
8 damac
inv 18 Damac | 18 | 18
6 USD - Hitachi
1011
1/2013
3920
OB 3925
1
8
9
1
4-
(1) elmostsmrin |  | 1
(4)CW elmostsmrin |  | 4
(14) |  | 14
1pkg#62
Ghana25
OB-7 | 7 | 7
1-
Balance 2
Colse Unupplied uppe
2 EGP - South Helwan
7B
421 EGP abu qeir 118
418 EGP Avice ZTPC
416 EGP Avice ZTPC
430 EURO Avice ZTPC
1056
448 EGP - Avice
11 EGP - Shabab 117
10 EGP - Shabab 117
edepc cose un applie
Inv. 4 ElTebeen | 4 | 4
33
31
32
14 Zona
1009
1080
1066
1065
2
1077
OB 3928
3917
Balance 9
30 banha 5
17052.18
180066
Balance 8
close unappl. hitach
8 barwa
TF-C4-589 | 589 | 589
ختامى
Gheleon 7
7
8 Etay
Adv. Balance 8
3 gheleon
DEC ADJ 74
OB 2- 9B | 9 | 9
13B
15B
close unappl. alstom
OB-5B | 5 | 5
44/1/1/2017
ISE-CW-EGP-19 | 19 | 19
ISE-SD-EURO-02 | 2 | 2
TAM-SW-EGP-10 | 10 | 10
TAM-CW-EURO-07 | 7 | 7
TAM-CW-EGP-16 | 16 | 16
ISE-SW-EGP-03 | 3 | 3
BSF-CW-EGP-16 | 16 | 16
TAM-SW-EGP-06 | 6 | 6
ISE-CW-EGP-13 | 13 | 13
19100029
19100018
TAM-SW-EGP-03 | 3 | 3
BSF-CW-EUR-04 | 4 | 4
MOS-SD-EURO-09 | 9 | 9
TAM-SD-EURO-02 | 2 | 2
BSF-CW-EGP-9 | 9 | 9
BINI SUEF SD-EG-IPC2 | 2 | 2
(4)cw beni suif |  | 4
19sd mosstasmreen
12 cw mosstasmreen
MOS (2) |  | 2
(14)SD EGP |  | 14
Wadi 9 inv.36 | 36 | 36
ٍAssuit 1 inv.38 | 38 | 38
180129
24 EGP - Shabab
21 EGP - West Domiat
Balance 4
Adv. 6 USD - Domiat
180032
19
5 EUR - Iskraemco
inv no(2 Euro-Comcav | 2 | 2
SODIC CLUB-IPC 30 | 30 | 30
(24) SODIC CLUB |  | 24
2 ghelion
Gheleon 8
Gheleon 9
(18) SODIC CLUB |  | 18
(22)new giza 2 |  | 22
(24)pkg#53 |  | 24
(4) pkg#62 |  | 4
(2) pkg#62 |  | 2
(2) PKG#107 |  | 2
close unappl. hysong
20
5
DEC ADJ 45
Inv. 14 Oewon Mousa | 14 | 14
Inv. 3 Oewon Mousa | 3 | 3
Inv No 1 Abo matamir | 1 | 1
inv 3 ABO ZAABL | 3 | 3
6 EGP - Shabab 117
5 EGP - West D. 117
OB-ST-Geo Grid
inv 43 P 11 maghaha | 43 | 43
H,A/IPC03/PO52/323 | 3 | 3
(1)elkayan mep |  | 1
36 EGP-Giza No. I&II
Inv 38 Giza I,II EGP | 38 | 38
5 EGP - South Helwan
Inv. 25 Asec | 25 | 25
OB-ST-5-03-2017 | 5 | 5
Inv. No.14 KWD Floor |  | 14
Inv. NO.6 KWT Floor |  | 6
Inv NO.4 KWT Flor | 4 | 4
OB-ST-Sodic Club
royal city-ipc21 | 21 | 21
ROYAL CITY-IPC19 | 19 | 19
ROYAL CITY- IPC 16 | 16 | 16
royal city- ipc(6) | 6 | 6
4 royal city
(20) SODIC CLUB |  | 20
OB-ST-Attaqa-2 | 2 | 2
10083
Inv. 14 Heliopolise | 14 | 14
Inv. 12 Heliopolise | 12 | 12
Inv. 11 Heliopolise | 11 | 11
Inv. 9 Heliopolise | 9 | 9
Inv.3 Heliopolis | 3 | 3
Inv.2 Heliopolis | 2 | 2
4
Invo No 66 Diwanya
Inv. 1 Wattany 220 | 1 | 1
Inv 47 P10 Banha | 47 | 47
Soc. 48 Wadi 13
Soci.Inv.52Banah12 | 52 | 52
11
Inv 29 Damac | 29 | 29
10072
inv 45 P 9 Banha | 45 | 45
12 East
Inv 27 Barwa | 27 | 27
OB 4
2009210004
Inv 11 USD | 11 | 11
DEC ADJ 73
12 USD - West Domiat
10 USD-Shabab 117
180139
180072
180071
180062
19 EGP Rev. 2
14 EGP - South Helwa
13 USD Suez Gulf
6 USD Suez Gulf
20 EGP- West Domiat
21 EGP- Shabab
Iskra Inv 7 | 7 | 7
Inv No AC017454 Avic
Apachi Inv No PC.#25
Inv. NO.1 KWT Floor |  | 1
Inv NO.1 KWT Flor | 1 | 1
(20)bine seuf 2 |  | 20
(23) sodic culb |  | 23
SOKHNA TUNNLE-FINAL
OB-ST-El Mosstas
cw (7) mosstasmreen |  | 7
30/P/10/ER/2017/USDD
Inv. no 1 DZD
9 USD- West Domiat
10024
7 EuroSouth Helwan
(5) pkg#62 |  | 5
OB-ST-PKG#32
OB-ST-Hyper One
10134
10011
14 EGP - Suez Gulf
10166
Inv No1 ElKean 220 | 1 | 1
(21)BINE SUIF 2 |  | 21
Inv No2 Wattanya220 | 2 | 2
remaining advance
5 USD- Shabab
10006
Inv 2 SG VO | 2 | 2
(7) pkg#62 |  | 7
(2) royal city |  | 2
10487
(11) CW |  | 11
35/P/10/ER/2017/USD
2-132KVA-H | 132 | 132
(1) ALAMAL BRIDGE |  | 1
23 EGP - Shabab
19 EGP -Shabab
19 EGP- Shabab
Inv GPC
Inv.41 Assuit Akhmem | 41 | 41
Inv.29 Assuit Akhmem | 29 | 29
Inv.23 Assuit Akhmem | 23 | 23
Inv.1 Assuit / Akhme | 1 | 1
Inv.42 Qena Akhmem | 42 | 42
Inv.31 Akhmem Qena | 31 | 31
Inv.24 Akhmem Qena | 24 | 24
Inv.19 Qena - Akhmem | 19 | 19
Inv.13 Qena - Akhmem | 13 | 13
(23-24) bine suef2 | 24 | 24
OB-ST-Mozambique
10350
26 EGP - West Domiat
28 EGP - West Domiat
16 EGP - South Helwa
OB-SI-PKG#62
IPC 25 Sodic club | 25 | 25
(27) pkg#53 |  | 27
Ret. Maghaghah
(2)CW esma3liya |  | 2
12-132KVA | 132 | 132
OB-12B | 12 | 12
OB 3-10B | 10 | 10
8B
32A
38/P/10/ER/2017/USD
5-132KVA | 132 | 132
OB-SI-Sodic Club
SODIC CLUB-IPC(29) | 29 | 29
Inv101 P13- Sammound | 101 | 101
Inv102 P14- Sammound | 102 | 102
Inv 90 P8- Sammound | 90 | 90
Inv 89P10Abo Matamir | 89 | 89
Abo Matamir 2
63 Social 15 Bnha
Inv. 14 Mostakbal | 14 | 14
Inv. 13 Mostakbal | 13 | 13
soc.67/8assuit
(3) p.o52/156** |  | 3
(26)pkg#53 |  | 26
10214
inv. 2 Assuit Akhmem | 2 | 2
Inv. 26 Badr | 26 | 26
Inv. 18 Badr | 18 | 18
Inv. 11 Badr | 11 | 11
Inv. 7 Badr | 7 | 7
inv.27 Asec | 27 | 27
10265
10210
(22)sodic club |  | 22
Inv 66 P19El Natroun | 66 | 66
Soc. Inv 70 Asuit 9 | 70 | 70
Inv 70 P9 Assuit | 70 | 70
(10) pkg#107 |  | 10
PKG#53-IPC 32 | 32 | 32
10330
180088
Inv 72 P10 Assuit | 72 | 72
Inv. 8 Elkayan | 8 | 8
Inv. 9 Elkayan | 9 | 9
5 EGP-VO Shipping
6-132KVA- H | 132 | 132
k(m.khalifa)3
29sd elmostsmrin
MOHAMED ALY-IPC01 | 1 | 1
SODIC CLUB-IPC34 | 34 | 34
11B
Inv.7 Assuit Akhmem | 7 | 7
Inv.5 Heliopolis | 5 | 5
Inv. 4 Akhmem Qena | 4 | 4
Inv.4 Heliopolis | 4 | 4
18100062
Kanten-MMansur-Kayan
K ( Moustafa Khlifa)
sodic culb-ipc36fin | 36 | 36
14sd EURO
220721005
2110210007
2105210005
2006210003
510
509
1903210004
2110210001
2108210005
2105210001
2101210001
2107210001
1905210004
12588
11072
180015
Dr-Memo-Inv#18+20EGP | 18 | 18
180095
Inv.66 Borg Alarab | 66 | 66
Inv.58 Borg Alarab | 58 | 58
Inv.57 Borg Alarab | 57 | 57
Inv.42 Borg Alarab | 42 | 42
Inv.39 Borg Alarab | 39 | 39
Inv.26 Borg Alarab | 26 | 26
Inv.19 Borg Alarab | 19 | 19
Inv.21Usd borg alarb | 21 | 21
Inv.9 Borg Alarab | 9 | 9
Inv. 4 Borg Alarab | 4 | 4
Inv. 3 Borg Alarab | 3 | 3
Inv. 3 usd Borg Arab | 3 | 3
(1) royal city |  | 1
k-a.osman-royal
Inv.10 Assuit Akhmem | 10 | 10
Inv 78 P11 Assuit | 78 | 78
Inv. No.13 KWD Floor |  | 13
insurance Refund S.G
Inv.11 Qena - Akhmem | 11 | 11
Inv.10 Qena - Akhmem | 10 | 10
10412
201
200
KAYAN FINSHING-IPC 4 | 4 | 4
212
10 sd euro mostsmrin
11030
10707
Cr. 1%
Final Credit
18100063
18100065
MinisAlocation IPC08 | 8 | 8
(1) pkg#117 |  | 1
NEW GIZA2- IPC 26 | 26 | 26
10400
10401
remaining Inv. 1 USD | 1 | 1
Ret.Part1 EGP
18100050
Inv.3 Assuit Akhmem$ | 3 | 3
Inv.6 Qena - Akhmem$ | 6 | 6
10405
Inv.1 Qena - Akhmem$ | 1 | 1
Inv.13 Assuit Akhmem | 13 | 13
Inv.16 Assuit Akhmem | 16 | 16
Inv.11 Assuit Akhmem | 11 | 11
180054
PSP ELCO-IPC 02 | 2 | 2
Soc 7 aboelmatamer
soc 8 abo-elmatamer
IPC31-SODIC CLUB | 31 | 31
18100061
Inv.25 Akhmem Qena | 25 | 25
Inv.22 Akhmem Qena | 22 | 22
Inv.30 Akhmem Qena | 30 | 30
Mohamed Aly - IPC04 | 4 | 4
ELHEGAZ-IPC FINAL
NFISHA BRIDGE-IPC01 | 1 | 1
18100067
18100066
Inv.2 Qena - Akhmem$ | 2 | 2
Inv.20 Qena- Akhmem$ | 20 | 20
Inv.37 Akhmem Qena | 37 | 37
Inv.28 Assuit Akhmem | 28 | 28
Inv. 12 Balat lot 3 | 12 | 12
Inv. 7 Balat lot 3 | 7 | 7
Inv. 5 Balat lot 3 | 5 | 5
Inv. 1 Balat lot 3 | 1 | 1
14B
16B
59/2142/2015
OB 1 -29A | 29 | 29
Deposit reda gas
19100032
ELSEWEDY UNY-IPC03 | 3 | 3
ELSWEDY-UN-MEP-IPC02 | 2 | 2
EL SEWEDY UNI-IPC-02 | 2 | 2
R5-IPC27 | 27 | 27
R5 - IPC20 | 20 | 20
R5 - IPC 19 | 19 | 19
R5 - IPC14 | 14 | 14
R5-IPC013 | 13 | 13
R5 - IPC11 | 11 | 11
R5 ZONE1- IPC05 | 5 | 5
R5-ZONE1-IPC 01 | 1 | 1
South Helwan inv.ded
180134
ROYAL CITY -IPC 10 | 10 | 10
k-a.osman-asmaaliya
PO - Mohamed Aly 107
MIN-FIT OUT-IPC04 | 4 | 4
Inv.19 Assuit Akhmem | 19 | 19
Inv.18 Assuit Akhmem | 18 | 18
Inv.20 Qena - Akhmem | 20 | 20
Inv.5 Beni Souf 358 | 5 | 5
MINISTIRY-IPC 1 | 1 | 1
Inv.8. Heliopolis | 8 | 8
kantenRoyalOsman
Inv.16Assuit Akhmem$ | 16 | 16
180117
K-MINTRA-M.BADWY
Inv.4 Usd borg alarb | 4 | 4
Inv.9 Rcc | 9 | 9
Inv.6 Usd borg alarb | 6 | 6
Inv.7 Usd borg alarb | 7 | 7
10351
10515
Inv. 16 Balat Lot 2 | 16 | 16
Inv. 14 Balat Lot 2 | 14 | 14
SODIC CLUB-IPC-33 | 33 | 33
10004
Inv. 2 Balat Lot 2 | 2 | 2
ints 20%Q3-11-22-41ض | 11 | 11
Inv.38 Akhmem Qena | 38 | 38
Soc Inv 9 Samanoud | 9 | 9
Inv.19 Qena- Akhmem$ | 19 | 19
Inv.18 Qena- Akhmem$ | 18 | 18
Inv.17 Qena- Akhmem$ | 17 | 17
Inv.4 Qena - Akhmem$ | 4 | 4
180146
Sett. Inv. Zona
Soci.29:33EGP Assuit
Inv.19Assuit Akhmem$ | 19 | 19
Inv.4 Assuit Akhmem$ | 4 | 4
PSP ELCO-IPC04 | 4 | 4
R05 - IPC028 | 28 | 28
Inv.43 Assuit Akhmem | 43 | 43
(1) CW .TAM |  | 1
K-A.OSMAN-M.ISMALIA
10542
LOC/025
IMP/070
LOC/020
LOC/021
IMP/065
CON/023
CON/018
10408
10407
10327
10328
10287
10172
Inv. 3 Balat lot 3 | 3 | 3
Inv. 3 Balat Lot 2 | 3 | 3
ret.col.18/13/12/18
IPC#16 |  | 16
Sodic Soreal IPC028 | 28 | 28
SOREAL-IPC20 | 20 | 20
SOREAL-IPC19 | 19 | 19
SOREAL-IPC05 | 5 | 5
SOREAL-IPC03 | 3 | 3
Social 13 Matamir
10523
Inv.14Usd borg alarb | 14 | 14
JPSS-17 | 17 | 17
K-M.Mansor-Kayan-dec
BSF-CW-10 | 10 | 10
BSF-CW-EUR-03 | 3 | 3
M.B.Z TUNNLE-IPC5 | 5 | 5
PKG#101 -IPC04 | 4 | 4
MALL EGYPT-FINAL 2
TAM-CW-EGP-09 | 9 | 9
PKG#62-IPC-15 | 15 | 15
Social 14 Matamir
10518
Inv 1 EUR Asec Spare | 1 | 1
13 ُEast
DP WORLD-IPC04 | 4 | 4
DP WORLD -IPC02 | 2 | 2
DPW IPC34 | 34 | 34
DP WORLD-IPC25 | 25 | 25
DP WORLD-IPC19 | 19 | 19
DP WORLD -IPC18 | 18 | 18
IPC# 1 |  | 1
Inv.45 Qena Akhmem | 45 | 45
180164
Inv.10 Borg Alarab | 10 | 10
Inv.7 Borg Alarab | 7 | 7
180173
Advance invoice due
Ras Ghareeb Inst
UNI FI&MEP -IPC06 | 6 | 6
SEWEDY UNI MEP-IPC06 | 6 | 6
MOS-SD-EGP-28 | 28 | 28
19100028
Inv.6 Assuit Akhmem | 6 | 6
Inv.35 Assuit Akhmem | 35 | 35
Niger9-2016-3934 | 2016 | 2016
Civil/H011
Ref. Insral 1 $ Qena
19100016
19100046
Abu soultan -ipc 1 | 1 | 1
Inv. 5 Balat Lot 2 | 5 | 5
Inv.26 Qena- Akhmem$ | 26 | 26
10049
IPC#3 |  | 3
Final Invice
KAYAN RADM2-IPC01 | 1 | 1
FPC
PSP-ELCO-IPC07 | 7 | 7
PSP-ELCO-IPC 06 | 6 | 6
Inv. 6 Balat lot 3 | 6 | 6
PKG#140 - IPC12 | 12 | 12
PKG#140 -IPC08 | 8 | 8
IPC#9 |  | 9
EL KAYAN-IPC FINAL
ELSEWEDY UNI-IPC 07 | 7 | 7
19100024
TAM-CW-EURO-04 | 4 | 4
10531
2008210010
2002210022
2001210019
1901210017
1908210019
Inv. 2 Mostakbal | 2 | 2
Inv.36 Assuit Akhmem | 36 | 36
Inv.32 Assuit Akhmem | 32 | 32
Inv.26 Assuit Akhmem | 26 | 26
Inv.17 Assuit Akhmem | 17 | 17
K-M.khlifa-minis-mar
Inv. 6 Eltbeen | 6 | 6
PKG#144 - IPC07 | 7 | 7
PKG#144 - IPC8 | 8 | 8
10464
Inv. 9 Abo Zabal | 9 | 9
10025
UNI -FIN&MEP-IPC02 | 2 | 2
Inv. 7 Balat Lot 2 | 7 | 7
10537
10721
10565
10639
Inv.7 – Lot 2 | 7 | 7
Inv.7 - Lot 1 | 7 | 7
PSP ELCO-IPC-08 | 8 | 8
IPC#18 |  | 18
10641
007/2018
K-Mansor-kayan-April
K-Hashem-jazimall-04 | 4 | 4
ELSEWEDY UNI-IPC09 | 9 | 9
air defense(2) ipc01 | 1 | 1
Alamein bridge ipc01 | 1 | 1
KAYAN SAHY-IPC03 | 3 | 3
MIN.ALLOCATION-IPC04 | 4 | 4
MIN-ELCTROMIK-IPC02 | 2 | 2
KAYAN MEP- IPC5 | 5 | 5
228
1901210012
PKG#101 - IPC05 | 5 | 5
Benban Lot 2 Inv. 20 | 20 | 20
Benban Lot 2 Inv. 28 | 28 | 28
Benban Lot 2 Inv. 27 | 27 | 27
Benban Lot 1 Inv. 29 | 29 | 29
Benban Lot 1 Inv. 23 | 23 | 23
Benban Lot 1 Inv. 10 | 10 | 10
Benban Lot 1 Inv. 9 | 9 | 9
10703
E&W-ELSWEDYUNI-MAY05
1903210003
016/2019
Inv.16 Borg Alarab | 16 | 16
OB-RE-PKG#45
PKG#117-IPC 6 | 6 | 6
Inv.02 Sugar OHTL | 2 | 2
Inv 1 Sugar S/s | 1 | 1
Inv.20 Borg Alarab | 20 | 20
Inv. 2 USD. | 2 | 2
Social Inv. 47 Qena | 47 | 47
221
IPC#12 |  | 12
PKG#144 - IPC10 | 10 | 10
Benban Lot 1 Inv. 1 | 1 | 1
Benban Lot1 Inv15USD | 15 | 15
Benban Lot1 Inv 3USD | 3 | 3
Benban Lot2 Inv 14 $ | 14 | 14
Benban Lot2 Inv 4 $ | 4 | 4
PKG #140 IPC023 | 23 | 23
PKG#140-IPC21 | 21 | 21
SOKHNA TU 2 -IPC01 | 1 | 1
R5-ZONE2-IPC04 | 4 | 4
240
OTHRE INCOME GAMISA
1903210013
1903210017
1902210008
1901210019
1903210016
1904210006
1904210007
20100005
ROYAL CITY-IC34
ABU SULTAN2-IPC 1 | 1 | 1
Inv. 4 Mostakbal | 4 | 4
Inv.02 $ Sugar OHTL | 2 | 2
Inv 3 $ Sugar S/s | 3 | 3
Kanteen-Jazi-June-
10786
Kanteen-Jazi-July-19 | 19 | 19
Inv. 10 Balat lot 3 | 10 | 10
Benban Lot2 Inv1 $ | 1 | 1
Inv 98 P11- Sammound | 98 | 98
Inv.10 Samanod 95 | 10 | 10
10970
IPC# 4&5 |  | 4
10003
Port Said Inv. 2 | 2 | 2
OB-st PKG#62
DP WORLD-IPC05 | 5 | 5
Inv. 11 Balat Lot 2 | 11 | 11
4B
Inv.42 Assuit Akhmem | 42 | 42
Inv.34 Assuit Akhmem | 34 | 34
inv. 5 Assuit Akhmem | 5 | 5
PKG#140 -IPC 02 | 2 | 2
242
Inv.47 Qena Akhmem | 47 | 47
Inv. 9 Qena - Akhmem | 9 | 9
Inv.8 Qena Akhmem | 8 | 8
Inv.7 Qena Akhmem | 7 | 7
Inv.33 Akhmem Qena | 33 | 33
Inv.28 Akhmem Qena | 28 | 28
Inv.23 Akhmem Qena | 23 | 23
Inv.17 Qena - Akhmem | 17 | 17
Inv.14 Qena - Akhmem | 14 | 14
Inv.12 Qena - Akhmem | 12 | 12
MI.ALLOCATION-IPC01 | 1 | 1
SCD4/004
Kanteen-Royalcit-AUG
Kanteen-jazimaal-AUG
Kanteen-Uni-Aug-2019 | 2019 | 2019
1908210009
IPC#6 |  | 6
10832
Inv.8 Usd borg alarb | 8 | 8
258
250
10785
R5-ZONE 2-IPC6 | 6 | 6
inv ( 2 ) 28-11-2020 | 2 | 2
INV(1-8)010420 | 1 | 1
SCD1/004
SAFIER BRIDGE-IPC02F | 2 | 2
MINISTRIY CORE-IPC01 | 1 | 1
504
H,A/IPC04/PO52/323 | 4 | 4
MANGROVE-IPC13 | 13 | 13
MANGOROVE-IPC05 | 5 | 5
20100007
MANGORVE-IPC02 | 2 | 2
7-19-April | 19 | 19
10132
3
Benban Lot 2 Inv. 4 | 4 | 4
Inv.37 Borg Alarab | 37 | 37
ISE-CW-EGP-17 | 17 | 17
10309
10187
Naga Hmdy Inv.1 Equ | 1 | 1
Nagaa Hamady Inv. 2 | 2 | 2
SOUQ ELSAMAK-IPC01 | 1 | 1
2-19Feb | 19 | 19
19-19June | 19 | 19
25-19Aug | 19 | 19
12-19-may | 19 | 19
26-19Aug | 19 | 19
Benban Lot 2 Inv. 9 | 9 | 9
Marsa Alam Equ Inv 3 | 3 | 3
Marsa Alam USD Inv 2 | 2 | 2
Inv.48 Qena Akhmem | 48 | 48
Marsa Alam EGP Inv 5 | 5 | 5
IPC#1 |  | 1
Kanteen-sep-sodic
Inv. 4 Sugar 33 OHTL | 4 | 4
Inv. 15 Farm | 15 | 15
Port Said Inv. 3 | 3 | 3
Inv 1 Asec Sparepart | 1 | 1
1-19Feb | 19 | 19
Inv.2 RCC | 2 | 2
Benban Lot1 Inv 4USD | 4 | 4
Benban Lot2 Inv 9 $ | 9 | 9
11000
IPC#3 |  | 3
1906210010
HYPER ONE- IPC10 | 10 | 10
HYPER ONE- IPC07 | 7 | 7
HYPER ONE2-IPC03 | 3 | 3
HYPER -IPC01 | 1 | 1
R5-ZONE 1- IPC7 | 7 | 7
IPC#1 |  | 1
6-2019 | 2019 | 2019
10 - sales
16 EGP VO Shippment
ISE-SW-EGP-04 | 4 | 4
AlAsher Brdg 2 Final
MIN.ANASER WATER-02 | 2 | 2
MIN-SHELL-IPC02 | 2 | 2
royal city-ipc22 | 22 | 22
ROYAL ZONE-IPC02 | 2 | 2
31-19-sep | 19 | 19
14-2020 | 2020 | 2020
PKG#101 - IPC08 | 8 | 8
Benban Lot1 Inv10USD | 10 | 10
Benban Lot1 Inv13USD | 13 | 13
Benban Lot2 Inv 5 $ | 5 | 5
10792
1908210017
265
508
496
490
Inv. 01 Future OHTL | 1 | 1
Inv 4 Asec Sparepart | 4 | 4
Istill.4 lot 1 Akhme
10850
10789
inv(6)100320 | 6 | 6
inv(3)251219 | 3 | 3
inv(1)101119 | 1 | 1
10998
273
IPC#3 |  | 3
IPC#2 |  | 2
R05 PH2 IPC013 | 13 | 13
R5 FINSHING-IPC08 | 8 | 8
R5 FINSHING-IPC07 | 7 | 7
R5 FINSHING-IPC06 | 6 | 6
Inv.1 - Lot 1 | 1 | 1
54-19 nov | 19 | 19
51-19 nov | 19 | 19
IPC#1 |  | 1
22 EGP VO TOAC
290
ISE-SW-EGP-05 | 5 | 5
10932
ESU PHASE2-IPC08 | 8 | 8
SEWEDY UNI 2- IPC04 | 4 | 4
E.S.U PH2-IPC01 | 1 | 1
Tunnel Inv. 11 | 11 | 11
Tunnel Inv. 3 | 3 | 3
Tunnel Inv. 2 + | 2 | 2
SOREAL-IPC08 | 8 | 8
491
38-19 oct | 19 | 19
ABUSOULTAN 1 -FINAL
MIN.LONG LIGHT-IPC01 | 1 | 1
10711
528
KAYAN MEP2-IPC01 | 1 | 1
1903210018
1902210012
ROYAL CENTER-IPC04 | 4 | 4
HYPER ONE-IPC02 | 2 | 2
Inv.1 Temmay Amded | 1 | 1
180169
180168
Inv. 02 Future OHTL | 2 | 2
Inv.01 $ Sugar OHTL | 1 | 1
1903210010
Kanteen-wezrat-Jan20
IKEA-IPC02 | 2 | 2
Inv 103P16Abo Matami | 103 | 103
aboelmatamir 8inv.86 | 86 | 86
Toshka Lot 4 Inv .23 | 23 | 23
Toshka Lot 4 Inv .15 | 15 | 15
Toshka Lot 4 Inv .20 | 20 | 20
Toshka Lot 4 Inv .14 | 14 | 14
Toshka Lot 4 Inv .8 | 8 | 8
Toshka Lot 6 Inv .10 | 10 | 10
Toshka Lot 6 Inv .5 | 5 | 5
Toshka Lot 4 Inv $3 | 3 | 3
Toshka Lot 6 Inv $9 | 9 | 9
Toshka Lot 6 Inv .8 | 8 | 8
Toshka Lot 6 Inv $6 | 6 | 6
IPC-03-CFC Podium | 3 | 3
11221
ROYAL CITY-IPC23 | 23 | 23
Badr-Zizenia Inv.3 | 3 | 3
294
296
IPC#5 |  | 5
ISE-SD-EURO-04 | 4 | 4
98% Susp/penalety
Inv.Scrap 33/2019
Lot. 04
Inv. 20 Badr | 20 | 20
IKEA-IPC03 | 3 | 3
10060
2002210002
11023
Inv 6 EUR Asec Spare | 6 | 6
Inv 5 EUR Asec Spare | 5 | 5
MP-06 | 6 | 6
IPC#5 |  | 5
CFC-IPC19 | 19 | 19
25/13/03/2020
INV(1)250620 | 1 | 1
IPC#23 |  | 23
IPC#24 |  | 24
IPC#1 |  | 1
10081
IPC#5 |  | 5
ORA ZED-IPC02 | 2 | 2
13 feb 20
8-19-April | 19 | 19
5 Jan 2020
2001210008
Kanteen-Olmpic-Feb20
Kanteen-Minis-Feb-20 | 20 | 20
530
IPC#7 |  | 7
Toshka Sub Inv. 22 $ | 22 | 22
PKG#162 - IPC07 | 7 | 7
PKG#162-IPC06 | 6 | 6
IKEA-IPC09 | 9 | 9
H,A-IPC09-PO52/323 | 9 | 9
Inv. No.1- Juba Proj |  | 1
Inv.6 kafr zeat itay | 6 | 6
E.S.U2-MEP-IPC07 | 7 | 7
11082
10062
302
KAYAN-MEP2-IPC02 | 2 | 2
11186
CFC IPC022 | 22 | 22
CFC-IPC02 | 2 | 2
DP WORLD-IPC12 | 12 | 12
ROYAL CITY -IPC27 | 27 | 27
IPC#2 |  | 2
6 Jan 2020
10018
Kanteen-Sodic-Feb-20 | 20 | 20
Kanteen-minist-Mar-2 | 2 | 2
10028
10027
10002
IPC002 | 2 | 2
IPC#3 |  | 3
Inv.05 Sugar OHTL | 5 | 5
ISE-SD-EGP-01 | 1 | 1
Inv.29 Borg Alarab | 29 | 29
Inv.25 Borg Alarab | 25 | 25
PKG #163 IPC019 | 19 | 19
PKG #163 IPC017 | 17 | 17
PKG#163-IPC01 | 1 | 1
10026
Inv.26Usd borg alarb | 26 | 26
11014
PKG#144 -IPC14 | 14 | 14
MANGOROVE RENT-IPC3 | 3 | 3
Inv.65 Borg Alarab | 65 | 65
Inv.63 Borg Alarab | 63 | 63
MIN.SHELL-IPC03 | 3 | 3
10011
10012
325
333
332
310
336
334
20100004
2003210013
HYPER ONE- IPC08 | 8 | 8
Eng-25 rev0 | 25 | 25
10007
TR46 IPC 11 | 11 | 11
ROYAL CITY-IPC28 | 28 | 28
E.S.U-PHASE2-MEP-01 | 1 | 1
Inv.42 deductions | 42 | 42
SOREAL - IPC13 | 13 | 13
024/2020 FCV
DP WORLD- IPC13 | 13 | 13
11088
ANG-Cam-Inv 6 - Ints | 6 | 6
11321
11543
PKG#162 -IPC02 | 2 | 2
IMP-036prog for 35 | 36 | 36
PKG#101 - IPC13 | 13 | 13
IPC#8 |  | 8
H.A-IPC005-PO181/148 | 5 | 5
ROYAL CENTR ZONE-07 | 7 | 7
Inv. 8 Balat Lot 2 | 8 | 8
Inv. 6 Balat Lot 2 | 6 | 6
11542
IMP-042 Rev0 | 42 | 42
IEKA-IPC12 | 12 | 12
Toshka Lot 6 Inv .3 | 3 | 3
11743
10722
10662
10604
10583
10442
10302
10263
10150
CFC-IPC06 | 6 | 6
inv(6)050320 | 6 | 6
IPC#1&2 |  | 1
PKG#140 - IPC11 | 11 | 11
ENG/026 Rev0 adj
30 - Apr 20
64-19 Dec | 19 | 19
25 Mar 20
29 - Apr 20
28 Mar 20
Olympic IPC Final
2005210005
348
337
338
10095
10193
IPC#4 |  | 4
SewedyUNi 2- IPC03 | 3 | 3
11103
13-2020 | 2020 | 2020
11-2020 | 2020 | 2020
2005210001
29-Mar20
PKG#101 - IPC14 | 14 | 14
ROYAL C.ZONE- IPC08 | 8 | 8
10195
Inv.09 Sugar OHTL | 9 | 9
353
352
Ref.37-38-41-43-44 | 38 | 38
Inv.35 Borg Alarab | 35 | 35
52-19 nov | 19 | 19
ESU2-IPC4-MEP | 4 | 4
Benban Lot2 Inv 15 $ | 15 | 15
68 - 19 Dec | 19 | 19
Suez S4 Inv. 08 | 8 | 8
Suez S4 Inv. 07 | 7 | 7
Inv. 38 Damac | 38 | 38
Inv(6)200620 | 6 | 6
356
20 Mar 20
Final
11443
Retention Inv.
10121
Inv.52 Assuit Akhmem | 52 | 52
10133
ROYAL CITY-IPC31 | 31 | 31
358
inv(9)150720 | 9 | 9
200023
ANG-Cam-Inv 5 | 5 | 5
11/13/07/2020-KwdRet
10253
44-Jun-2020 | 2020 | 2020
40B/P/10/ER/2017/USD
OB 3932
10004
IPC#1 |  | 1
IPC-FINAL-HYPER MEP
362
60-aug-2020 | 2020 | 2020
23-2020 | 2020 | 2020
10102
368
K-Royal-Apr-May-2020 | 2020 | 2020
SOREAL-IPC16 | 16 | 16
ROYAL ZONE-IPC10 | 10 | 10
Toshka Lot 4 Inv .6 | 6 | 6
inv(7)100320 | 7 | 7
Badr-Zizenia Inv.1 | 1 | 1
ANG-Mor-Inv.-5 | 5 | 5
ANG-Mor-Inv.-3 | 3 | 3
Toshka Lot 6 Inv .4 | 4 | 4
10149
11403
OB EHV1000
11541
PKG#163-IPC04 | 4 | 4
Inv. 08 Farm | 8 | 8
ISE-SD-EURO-06 | 6 | 6
Toshka Lot 6 Inv $5 | 5 | 5
R05(2) IPC 51 | 51 | 51
R052 ipc40 | 40 | 40
R5 2 IPC37 | 37 | 37
IPC_5_gama_ministry
2006210001
361
367
Mostakbal-8 Inv.05 | 5 | 5
Mostakbal-8 Inv.02 | 2 | 2
37-2020 | 2020 | 2020
OLYMPIC-IPC02 | 2 | 2
SOREAL-IPC17 | 17 | 17
11503
IMP-049 | 49 | 49
Ref Retention USD Bo
BSF-CW-EGP-15 | 15 | 15
BSF-SW-06 | 6 | 6
TAM-CW-EGP-21 | 21 | 21
Mostakbal-8 Inv.07 | 7 | 7
2008210007
inv ( 11 ) 15-9-2020 | 11 | 11
Kanteen-Kayan-Oct-20 | 20 | 20
10028
10031
10030
Inv.22Usd borg alarb | 22 | 22
41-Jun-2020 | 2020 | 2020
PKG#101-IPC15 | 15 | 15
10293
S-003 | 3 | 3
PSP ELCO-IPC11 | 11 | 11
ENG/035
IMP- 056/058 | 56 | 56
Reailway PSP Inv. 01 | 1 | 1
IPC#1 |  | 1
PKG#163 -IPC03 | 3 | 3
Toshka Lot 6 Inv .14 | 14 | 14
IPC#1 |  | 1
IKEA-IPC10 | 10 | 10
Con-015 | 15 | 15
inv(14 ) 10-2020 | 14 | 14
Nagaa Hamady Inv. 1 | 1 | 1
MANGROVE-IPC10 | 10 | 10
IPC#1 |  | 1
Inv.6 – Lot 2 | 6 | 6
Cairo-alex ipc32 | 32 | 32
cairo-alex ipc 25 | 25 | 25
cairo-alex ipc22 | 22 | 22
cairo-alex ipc21 | 21 | 21
CAIRO-ALEX IPC18 | 18 | 18
Cairo-Alex IPC014 | 14 | 14
Cairo-Alex IPC09 | 9 | 9
IPC_15_Rowad_SEast
11640
11288
10949
10203
Nagaa Hamady Inv.6 | 6 | 6
370
11602
42-2020 | 2020 | 2020
11544
10122
493
LEKELA-IPC10 | 10 | 10
11445
11501
E.S.U 2-MEP-IPC09 | 9 | 9
68-Oct-2020 | 2020 | 2020
11642
11641
12064
PKG#22-IPC FINAL
inv ( 20) 9-12-2020 | 20 | 20
IPC#7 |  | 7
MIN.FIT OUT-IPC02 | 2 | 2
ORA ZED IPC 17 | 17 | 17
ora zed ipc14 | 14 | 14
ORa zed ipc13 | 13 | 13
ORA ZED PH1 IPC010 | 10 | 10
Ora Zed IPC08 | 8 | 8
ORA ZED 1- IPC02 | 2 | 2
IPC-Fabio
JV-AC-EE-Inv-003 | 3 | 3
IKEA - IPC11 | 11 | 11
ANG-Mor-Inv 5 - Ints | 5 | 5
Toshka Sub Inv. 12 $ | 12 | 12
Toshka Sub Inv. 09 $ | 9 | 9
Toshka Lot 6 Inv .9 | 9 | 9
10M RMADAN BRIDGE-01 | 1 | 1
Con-017 | 17 | 17
2009210014
IPC#7 - HAC |  | 7
IPC#5 10 of Ramadan |  | 5
375
384
Toshka Lot 6 Inv $7 | 7 | 7
scarp lot no 13
IPC_16_Rowad_Poly
Lot 7 & 12
PKG#162-IPC09 | 9 | 9
Kantin-Wezrat-Nov-20 | 20 | 20
Ref.Rete . Borg arab
PKG#162-IPC10 | 10 | 10
2012210002
IPC#2 PhaseII |  | 2
Marytia-R-R-IPC01* | 1 | 1
Olympic
Ministries district
11549
Toshka Lot 6 Inv .2 | 2 | 2
IPC_17_Rowad_Roly
inv ( 25 )20/12/2020 | 25 | 25
elsewedy HQ-IPC04 | 4 | 4
El-Nayba Inv. 1 | 1 | 1
Port Said Inv. 1 | 1 | 1
Inv.21 Final Ghelion | 21 | 21
Toshka Sub 4 Inv. 01 | 1 | 1
Suez S4 Inv. 04 | 4 | 4
F - Drug Possession
28-2020 | 2020 | 2020
48-2020 | 2020 | 2020
IPC_1_Rowad_Ora
scrap iraq villa
MIN.ELCTROM-IPC03 | 3 | 3
Inv 8 Zambia man2 | 8 | 8
MIN-ANASER SAHY-IPC1 | 1 | 1
11723
TETRA-IPC01-PO30189 | 1 | 1
Suez S4 Inv. 02 | 2 | 2
Toshka Lot 4 Inv $8 | 8 | 8
Inv. 03 Farm | 3 | 3
Inv. 06 Farm | 6 | 6
Inv. 02 Farm | 2 | 2
Inv 7 Sugar S/s | 7 | 7
Inv 5 Sugar S/s | 5 | 5
DP WORLD-IPC21 | 21 | 21
Katamya Creeks ipc41 | 41 | 41
Katameya ipc 29 | 29 | 29
katameya IPC 28 | 28 | 28
katameya ipc15 | 15 | 15
Katmeya Creeks IPC08 | 8 | 8
IPC_5_Gama_Salary
inv ( 2 ) 18-2-2021 | 2 | 2
kayan 110 -1 | 1 | 1
Al-Lahoon Sub Inv 03 | 3 | 3
MR3L&L-IPC1FINAL | 1 | 1
ROYAL CITY-IPC37 | 37 | 37
BSF-CW-EGP-17 FINAL | 17 | 17
200122
IPC-1-2B3 | 1 | 1
IPC_5_Mivida
IMP-063 | 63 | 63
11806
11665
11668
IPC_3_RME_Gouna
IPC_3_Rowad_ORA
IPC_2_Rowad_ORA
2007210003
R05-01 | 1 | 1
R05 - CONCRETE
PKG#144 - IPC12 | 12 | 12
385
389
Adv.Adv.ITS Inv. 01 | 1 | 1
1st & FPC
IPC#6 Coastal Road |  | 6
IPC#25 |  | 25
8
497
PKG #178 IPC04 | 4 | 4
ANG-Mor-Inv 6 - Ints | 6 | 6
200123
2006210006
م 1 كوبرى حسن المأمو | 1 | 1
IPC_3_LRT |  | 3
10422
MANGROVE WALL-IPC4 | 4 | 4
DP WORLD-IPC23 | 23 | 23
inv ( 23 )15-12-2020 | 23 | 23
tr0025
OLYMPIC-IPC03 | 3 | 3
32-April-20 | 20 | 20
Elco EGAT-IPC17 | 17 | 17
IPC#2 - LRT |  | 2
IPC#1 |  | 1
Invoice 01/2021 | 1 | 1
Invoice 02/2021 | 2 | 2
IKEA-IPC08 | 8 | 8
IKEA - IPC07 | 7 | 7
ROYAL CITY-IPC39 | 39 | 39
inv ( 17 ) 3-12-2020 | 17 | 17
Inv(7)270820 | 7 | 7
394
396
Toshka Lot 4 Inv $4 | 4 | 4
P-45-Portsaid Inv.01 | 1 | 1
2103210004
21
Sodic Soreal IPC025 | 25 | 25
IPC#4 PII |  | 4
CancelDeb.Tosh OHTL4
Deb .adv.Toshka 4
Cancel DebToshka 4
12042
R5-IPC25 | 25 | 25
KATAMEYA CREEKS-IPC1 | 1 | 1
10142
200160
CFC-IPC15 | 15 | 15
PKG162#IPC12 | 12 | 12
IPC#4 |  | 4
ELSEWEDY HQ-IPC01 | 1 | 1
10466
10465
10463
Olympic - 3 | 3 | 3
Suez S4 USD Inv. 01 | 1 | 1
TITRA-OVM-PO 41624
TETRA-IPC01/PO26597 | 1 | 1
11862
Ref Ret Balat Lot 2
South Valley Inv. 09 | 9 | 9
South Valley Inv. 03 | 3 | 3
South Valley Inv. 02 | 2 | 2
406
391
403
R5-IPC24 | 24 | 24
ANG-Cam-Inv 4 | 4 | 4
IPC#2 Ahl Misr |  | 2
11945
18
17
MIN-SHELL-IPC07 | 7 | 7
12068
10003
11-2021 | 2021 | 2021
GOV 2 IPC 27+28 | 27 | 27
GOV2 IPC06 | 6 | 6
IPC_6_MohamedAli
ROYAL CITY-IPC40 | 40 | 40
12070
12073
inv(9)300620 | 9 | 9
sewedy uni-mep-08 | 8 | 8
39
PKG #177 IPC013 | 13 | 13
PKG #177 IPC012 | 12 | 12
CFC - IPC018 | 18 | 18
12222
Sadat Indust Inv. 01 | 1 | 1
Inv.5 Qena Akhmem | 5 | 5
Toshka Sub Inv. 06 | 6 | 6
Ref.Ret Asuit akh
Inv ( 1 ) montazha | 1 | 1
Gov2 ipc 17 | 17 | 17
GOV 2 IPC08 | 8 | 8
2103210008
2103210007
inv- ( 1 ) |  | 1
Invoice 25& 26 EGP | 25 | 25
58
IPC#4 |  | 4
IPC#1 - Monorail |  | 1
ora zed ph1 ipc11 | 11 | 11
ora Zed2-ipc01 | 1 | 1
ORA ZED Ph1 IPC06 | 6 | 6
IPC#07 -Madkour |  | 7
IPC#4 - Madkour |  | 4
IPC#1 - Madkour |  | 1
IPC#1 Shenzo Aby |  | 1
Kanteen-May2021(R05)
PKG#177-IPC02 | 2 | 2
Inv.16 - Lot 1 | 16 | 16
Inv.11 - Lot 1 | 11 | 11
Inv.10 - Lot 1 | 10 | 10
Inv.3 - Lot 1 | 3 | 3
Inv. 9 – Lot 2 | 9 | 9
Inv.1 - Lot 2 | 1 | 1
Inv.5 – Lot 2 | 5 | 5
Inv. 10 – Lot 2 | 10 | 10
Inv. 8 – Lot 2 | 8 | 8
Inv.2 - Lot 2 | 2 | 2
ANG-Mor-Inv 6 | 6 | 6
Toshka Lot4OH Inv.02 | 2 | 2
PKG#178-IPC03 | 3 | 3
PKG #101 IPC023 | 23 | 23
LEKELA-IPC11 | 11 | 11
2104210002
2105210017
Sadat Indust Inv. 02 | 2 | 2
Inv.32 Akhmem Qena | 32 | 32
Inv.21 Qena - Akhmem | 21 | 21
200205
200202
200199
PKG #163 IPC012 | 12 | 12
Diplomatic ipc15 | 15 | 15
diplomatic ipc11 | 11 | 11
10161
Air Force Inv . 16 | 16 | 16
12102
12071
12342
PKG #177 IPC016 | 16 | 16
ALAASHER BRIDGE-FINA
mansora ipc11 | 11 | 11
Mansoura UNI IPC05 | 5 | 5
Mansoura Uni IPC02 | 2 | 2
R5 FINSHING-IPC02 | 2 | 2
تخليص جمركى IPC05 | 5 | 5
R5 - IPC15 | 15 | 15
R5-ZONE1-IPC04 | 4 | 4
Dry Port Inv. 10 | 10 | 10
Gov2 ipc 21+22 | 21 | 21
gov2 ipc 20 | 20 | 20
Marsa Alam USD Inv 1 | 1 | 1
Maryotya IPC07 | 7 | 7
Maryotya IPC06 | 6 | 6
D.M شحنةالسكةالحديد-
IPC_10_Saray
Scrap Inv. 05/2021 | 5 | 5
Dry Port Inv. 02 | 2 | 2
10141
Hosh Essa Inv. 07 | 7 | 7
Hosh Essa Inv. 03 | 3 | 3
Toshka Sub Inv. 21 $ | 21 | 21
PKG#177 IPC (44) | 44 | 44
Sodic Soreal IPC029 | 29 | 29
IPC#4 - Gharably |  | 4
ELSAWEP-IPC01 | 1 | 1
10607
IPC-4-PLAYA | 4 | 4
Ora-Kanten July21
FPC Marassi
inv ( 2 ) 1-8-2021 | 2 | 2
INV ( 2 ) | 2 | 2
12402
12065
EGATpelletizingIPC19 | 19 | 19
R05 IPC030 | 30 | 30
512
LRT 10Ramadan Inv.03 | 3 | 3
PKG #163 IPC014 | 14 | 14
R05 Zone 2 IPC015 | 15 | 15
10164
Dry Port Inv. 01 | 1 | 1
ANG-Mor-Inv.-7 | 7 | 7
ANG-Mor-Inv 4 | 4 | 4
Toshka Lot 6 Inv .26 | 26 | 26
Toshka Lot 6 Inv .24 | 24 | 24
CFC IPC021 | 21 | 21
CON/024
ENG/042
422
Al-Lahoon Sub Inv 02 | 2 | 2
2007210009
Ora zed ph.1 IPC18 | 18 | 18
ORA ZED IPC 16 | 16 | 16
ora ph2 ipc 27 | 27 | 27
IPC#6 |  | 6
Inv. 14 Farm | 14 | 14
10245
12166
19-2021 | 2021 | 2021
El Marg IPC04 | 4 | 4
PKG #101 IPC022 | 22 | 22
514
2107210001
Mansoura UNI IPC04 | 4 | 4
Railway IPC06 | 6 | 6
Invoice 06/2021 | 6 | 6
PKG #140 IPC024 | 24 | 24
12444
IPC#2 - Mansura Proj |  | 2
Kanten Sodic AUG 21
GOV 2 IPC07 | 7 | 7
429
10287
10160
10013
PIP indust Inv.01 | 1 | 1
Reailway PSP Inv. 05 | 5 | 5
21000005
East Owainat Inv.1 V | 1 | 1
24-2021 | 2021 | 2021
IPC#4 - Fianl Museum |  | 4
FPC - Egy Museum
IPC-3-PLAYA | 3 | 3
IPC#1 |  | 1
IPC02 Madkour | 2 | 2
27-2021 | 2021 | 2021
Benban Lot 1 Inv. 12 | 12 | 12
kanten kayan Sep 21
Kanten Katmeya Sep21
INV ( 4 ) | 4 | 4
inv ( 1 ) T0020 | 1 | 1
IPC#3 Assuit |  | 3
elsewedy hq-ipc06 | 6 | 6
10903
10783
10782
IPC#1 |  | 1
2107210003
2108210002
MDF IPC04 | 4 | 4
Royal city ipc (41) | 41 | 41
royal center ipc 22 | 22 | 22
10862
IPC#04 - Sokhna Port |  | 4
RasElTeenHangarIPC04 | 4 | 4
Ras El Teen IPC03 | 3 | 3
Ras El Teen IPC02 | 2 | 2
220621002
220221003
MDF3- IPC 10 | 10 | 10
MDF FACTORY3 IPC 6+7 | 6 | 6
MDF FACTORY3 IPC04 | 4 | 4
MDF FACTORY3 IPC02 | 2 | 2
IPC-1-Margirgs | 1 | 1
10802
ESU2 MEP IPC-Final
IPC#3 |  | 3
LEKELA-IPC08 | 8 | 8
inv ( 4 ) Captal 1 | 4 | 4
ENR-Sign Inst Inv01 | 1 | 1
Toshka Lot4OH Inv.06 | 6 | 6
IPC#2 - Monorail |  | 2
Kanten OCT/21 Sodic
Kanten OCT/21 Kayan
LRT 10Ramadan Inv.02 | 2 | 2
inv ( 2 ) ULA | 2 | 2
inv ( 6 ) Captal one | 6 | 6
Toshka Farm Inv. 02 | 2 | 2
ANG-MOR-Inv 7 - Ints | 7 | 7
ANG-Cam-Inv 7 | 7 | 7
10922
IPC#3 Ahl Misr Zamal |  | 3
200265
200264
200306
200309
ELSEWEDY HQ IPC08 | 8 | 8
Katamya creeks ipc45 | 45 | 45
Katamya Creeks ipc44 | 44 | 44
katamye creeks ipc43 | 43 | 43
Katameya ipc 40 | 40 | 40
ipc27 katameya creek | 27 | 27
Katameya Creks IPC09 | 9 | 9
IPC#8 Sokhna Bridge |  | 8
IPC#2 -Sokhna Bridge |  | 2
R6 L&L ipc1(final) | 1 | 1
29
31
30
433
10948
Astoria IPC8 | 8 | 8
inv ( 4 ) montazha | 4 | 4
LEKELA IPC015 | 15 | 15
2111210001
Kanten Sodic NOV 21
Katmeya-Kanten-11/21 | 11 | 11
Toshka Lot4OH Inv.09 | 9 | 9
Extension kayn Inv 2 | 2 | 2
Dry Port Inv. 04 | 4 | 4
Ref.Ret Qen-akh 5
Ret Qen-akh 5 T
FacultyMedcine IPC06 | 6 | 6
11162
35-2021 | 2021 | 2021
10983
Ref.2 benban Lot 2
EGAT WaterTank IPC03 | 3 | 3
EGAT WaterTank IPC05 | 5 | 5
IPC#01 |  | 1
inv ( 1 Fina ) pridg | 1 | 1
Minist Core IPC08 | 8 | 8
inv ( 6 ) Montazha | 6 | 6
Collection-R05-11/21 | 11 | 11
INV ( 12 ) GET | 12 | 12
soreal-ipc32 | 32 | 32
10th Ind Park Inv.04 | 4 | 4
Kanteen DEC21 R05
Kanteen DEC21 ORA
Kanteen DEC21 Kayan
inv ( 1 ) | 1 | 1
2112210003
2112210002
517
MinistSHELL IPC08 | 8 | 8
005/2022
12614
12609
12567
SPX.1 ipc 22+23 | 22 | 22
sokhna port ex ipc03 | 3 | 3
Olympic MEP IPC2 | 2 | 2
Maryotia IPC013 | 13 | 13
IPC-1-PLAYA | 1 | 1
Invoice EURO 15/2021
IPC#4 GSCC PortSaeid |  | 4
IPC7 PORTSAID | 7 | 7
INV ( 4 ) Ring R | 4 | 4
ENG/045
ENG/049
427
449
رد تامين2بنبان لوط 1
IPC#3 Taamer Axis |  | 3
ELSEWEDY HQ IPC 10 | 10 | 10
11142
11143
Nagaa Hamady Inv.8 | 8 | 8
RING ROAD ELMARG-01 | 1 | 1
new giza hos ipc 23 | 23 | 23
New giza IPC7 | 7 | 7
newgizahospital ipc6 | 6 | 6
2111210002
Rolling mill-IPC10 | 10 | 10
ROLLING MILL IPC05 | 5 | 5
ROLLING MILL IPC 02 | 2 | 2
Lock& Load ipc 16 | 16 | 16
EGAT L&L ipc 09 | 9 | 9
EGAT L&L IPC04 | 4 | 4
2112210005
Elsewedy HQIPC23(24) | 23 | 23
IPC#5 - Sokhna Port |  | 5
200545
Ministry-Jan-2022 | 2022 | 2022
k-air defence-jan22
Railway IPC05 | 5 | 5
Railway IPC04 | 4 | 4
CAIRO-ALEX-IPC01 | 1 | 1
11662
IPC-3-BORSA | 3 | 3
IPC-1-BORSA | 1 | 1
Ref-Ret-benban 1 $ T
Tam CW Final
port said ipc18 | 18 | 18
port said ipc12 | 12 | 12
portsaid soils ipc32 | 32 | 32
supply egp ipc 3 | 3 | 3
200504
ANG-Mor-Inv 3 - Ints | 3 | 3
ANG-Cam-Inv 8 - Ints | 8 | 8
IPC07-MDF | 7 | 7
IPC-3-PLAYA ROOF | 3 | 3
k-kayan feb2022
k-ora zed feb2022
k-sodic feb2022
IPC#5 SOKHNA BRIDG |  | 5
IPC#2 |  | 2
IPC#6 Sokhna Bridge |  | 6
Rolling Mill ipc 01 | 1 | 1
Port said OHTL Inv.1 | 1 | 1
2112210009
11456
mdf factory2 ipc02 | 2 | 2
IPC#4 - Taamer Axis |  | 4
sodic soreal ipc34 | 34 | 34
200546
200547
12933
10392
435
441
11302
Houd Negaih Inv.01 | 1 | 1
Scrap Lot No:14
Selling Scrap Lot 2
Selling Scrap Lot 5
Scrap Lot No:13
Selling Scrap Lot12
10382
CON/028
Commission invoice
EGAT L&L IPC02 | 2 | 2
11366
ROYAL CITY2-IPC17 | 17 | 17
LOC/023
Hosh Essa Inv. 2 Equ | 2 | 2
IPC#8 Sokhna Port |  | 8
IPC-5-PLAYA ROOF | 5 | 5
006/2022
11425
11384
EGAT WATER TANK IPC9 | 9 | 9
T 3-2022 | 2022 | 2022
12908
MDF ipc12 | 12 | 12
PKG#177-IPC38 | 38 | 38
200585
Suez S4 Inv. 11 | 11 | 11
Suez S4 Inv. 16 | 16 | 16
10162
474
CON/030
IPC#5 - Luxor Onshor |  | 5
ipc 22 Mdf Factory | 22 | 22
521
MDF Factory ipc 41 | 41 | 41
MDF IPC 17 | 17 | 17
East Owainat Inv. 06 | 6 | 6
k-salim-apr22
IPC-7-PLAYA ROOF | 7 | 7
11458
IKEA Final IPC014 | 14 | 14
007/2022
13012
sokhna port ex ipc01 | 1 | 1
OLYMPIC MEP IPC01 | 1 | 1
air devance ipc02 | 2 | 2
Dry Port Inv. 03 | 3 | 3
waldorf- IPC 14 | 14 | 14
waldorf- IPC13 | 13 | 13
Waldorf_IPC 11 | 11 | 11
220321002
EL SEWEDY HQ IPC14+ | 14 | 14
pkg#177 ipc 26+27 | 26 | 26
PKG#177 IPC30 | 30 | 30
ipc 10 Emaar pkg#189 | 10 | 10
Emaar pkg #189ipc16 | 16 | 16
Emaar PKG#189-IPC 13 | 13 | 13
pkg#189- IPC8 | 8 | 8
ISE-CW-EGP-27 | 27 | 27
giza hospital ipc04 | 4 | 4
Abo Ghaleb ipc03 | 3 | 3
el sewedy HQ ipc14 | 14 | 14
Inv.4988/Sp/H&J-01 | 4988 | 4988
IPC#10 - Sokhna Port |  | 10
IPC#13 - Sokhna Port |  | 13
mansora finish ipc20 | 20 | 20
mansura finish ipc16 | 16 | 16
mansura finish ipc14 | 14 | 14
mansora finish ipc 5 | 5 | 5
mansora finish ipc04 | 4 | 4
12996
200544
Benban Lot 1 Inv. 16 | 16 | 16
Mostakbal-8 Inv.06 | 6 | 6
inv ( 5 ) Captal 1 | 5 | 5
IPC#12 - Sokhna port |  | 12
IPC#9 Monorail |  | 9
220621001
Marsa Alam EGP Inv 7 | 7 | 7
IPC#11 Sokhna Port |  | 11
Toshka Lot 4 Inv .21 | 21 | 21
Open chanel1 IPC fin
mohamed aly 4 ipc01 | 1 | 1
Ora landscape ipc 17 | 17 | 17
Ora landsacape ipc 8 | 8 | 8
Ora Landscap ipc (5) | 5 | 5
Ora landscape ipc3 | 3 | 3
PKG#205 IPC02 | 2 | 2
Emar Pkg#177 ipc(45) | 45 | 45
ora zed2 ipc06 | 6 | 6
Maryotia IPC011 | 11 | 11
SOKHNA PORT EX IPC02 | 2 | 2
West Domiatte Inv.01 | 1 | 1
Hosh Essa Inv. 08 | 8 | 8
INV ( 5 ) FINAL | 5 | 5
MIDA Sply. Inv.1 4 | 1 | 1
IPC#2-Luxoroffshore |  | 2
473
Toshka Lot 4 Inv $10 | 10 | 10
Marsa Alam USD Inv 3 | 3 | 3
Toshka Sub 4 Inv. 04 | 4 | 4
02/13/06/2022 KwtRet
200630
200605
200767
200689
200606
Toshka Lot 6 Inv .25 | 25 | 25
Toshka Lot 6 Inv .23 | 23 | 23
Toshka Lot 6 Inv .19 | 19 | 19
Inv.01 Po 28/21 | 1 | 1
Ref-Ret-Benban lot2
501
220421006
IPC#1 EGAT |  | 1
10021
MDF factory ipc(28) | 28 | 28
IPC#14 - Sokhna Port |  | 14
11765
DPW IPC 35 | 35 | 35
IPC#06 - Assuit |  | 6
Soreal hardscapeipc6 | 6 | 6
IPC-11-Playa Roof | 11 | 11
IPC-12-PLAYA | 12 | 12
IPC-6-BORSA | 6 | 6
pkg#177 IPC 28 | 28 | 28
PKG #177 IPC020 | 20 | 20
PKG #163 IPC016 | 16 | 16
IPC#1 Wadi ElNatroun |  | 1
IPC#2 Port saeid |  | 2
25 EGP - West Domiat
180158
Air defence3 IPC1 | 1 | 1
T13-2022 | 2022 | 2022
Waldorf Astoria IPC6 | 6 | 6
Air Defense2 IPC2 | 2 | 2
11770
inv ( 1 ) LINX | 1 | 1
T 12-2022 | 2022 | 2022
SUEZ STEEL ABB IPC 1 | 1 | 1
inte&retu app ipc 3 | 3 | 3
In&Re apply abb ipc6 | 6 | 6
i&r apply (Abb)ipc4 | 4 | 4
201051
200685
200665
200813
port said silos ipc6 | 6 | 6
astoria sharm IPC2 | 2 | 2
Eipico ipc 14 | 14 | 14
Eipico ipc( 7) |  | 7
IPC#3 Wadi ElNatroun |  | 3
soreal ipc35 | 35 | 35
Rolling mill ipc07 | 7 | 7
IPC#2 Wadi ElNatroun |  | 2
Air Defence 4 ipc1 | 1 | 1
k-hassan SEP2022
IPC#7 Bahr Elbaqar |  | 7
5-2023 | 2023 | 2023
IPC#3 Taamer PII |  | 3
AbasAlaqad2 IPCFinal
inv ( 4:12 ) CS-20 | 4 | 4
katameya IPC19 | 19 | 19
IPC004-KAIFENG DAFAN | 4 | 4
elsewedy HQ ipc18 | 18 | 18
IPC#6 ElHammam |  | 6
GOV2 IPC 11 | 11 | 11
21
Minist MEP IPC05 | 5 | 5
Elsokhna 4.5 ipc 3+4 | 3 | 3
pkg#189- IPC 5 | 5 | 5
IPC#3 Offshore |  | 3
IPC#20 Sokhna Port |  | 20
EDNC HARDESCAPE IPC4 | 4 | 4
ednc sodic ipc33 | 33 | 33
PKG#163- IPC26 | 26 | 26
Olympic Finsh IPC3+ | 3 | 3
min mep ipc 6 | 6 | 6
CFC IPC024 | 24 | 24
FPC - Ameria Project
Rolling mill ipc 04 | 4 | 4
rolling mill- IPC10 | 10 | 10
MDF FACTORY2 IPC06 | 6 | 6
MDF FACTORY IPC09 | 9 | 9
IPC#1 - HST Mahager |  | 1
FPC - Sokhna Bridge
mohamed aly3 Ipc2 | 2 | 2
Air def IPC4 | 4 | 4
waldorf Astoria IPC9 | 9 | 9
IPC014-Playa Roof | 14 | 14
port said silos ipc8 | 8 | 8
IPC 6 WADIELNATRON | 6 | 6
ELSEWEDY HQ IPC 20 | 20 | 20
New giza - IPC10 | 10 | 10
200725
new giza IPC9 | 9 | 9
IPC#1 - NRCC |  | 1
200766
PKG#101-IPC16 | 16 | 16
MDF Local - IPC8 | 8 | 8
K-MUSTAFA OCT.2022
Defense6 IPC1 | 1 | 1
Mini MEP IPC6 | 6 | 6
cairo-alex ipc 26 | 26 | 26
MDF - IPC 16 | 16 | 16
230000007
Defense5 IPC1 | 1 | 1
Urbnk- ipc 1 | 1 | 1
EGAT IPC06 | 6 | 6
IPC 5 PORT SAID | 5 | 5
IPC 8 WADI ELNATRON | 8 | 8
revamp ipc(5) | 5 | 5
IPC#7 Portsaid |  | 7
ORA ZED IPC09 | 9 | 9
Royal city ipc (42) | 42 | 42
000008-2022Playa | 2022 | 2022
pkg#177-IPC37 | 37 | 37
PKG#178- IPC 9 | 9 | 9
EGAT L&L-IPC11 | 11 | 11
EGAT L&L IPC12 | 12 | 12
Cairo-alex ipc 35 | 35 | 35
4-2023 | 2023 | 2023
Gov2 ipc(12) | 12 | 12
181022
Royal centerzone(23) |  | 23
Diplomatic ipc12 | 12 | 12
Diplo Dist. IPC05 | 5 | 5
INV ( 1 ) GET | 1 | 1
IPC#7 - Assuit |  | 7
inv ( 6-7-8 ) kemet | 6 | 6
IPC#00015 |  | 15
INV (2 ) AL Mansorya | 2 | 2
IPC#7 - Sokhna Bridg |  | 7
katameyacreeks-IPC26 | 26 | 26
ABOGHALEB 6+7+8+9+10
INV ( 3 ) GET | 3 | 3
INV ( 2 ) GET | 2 | 2
200786
carrefour RBS IPC 4 | 4 | 4
Carrefour RBS IPC(2) | 2 | 2
IPC3 TR60 | 3 | 3
MDF FACTORY IPC (26) | 26 | 26
Min long lead Ipc4 | 4 | 4
FPC Monorail
Gov2 ipc18+19 | 18 | 18
IPC#18 Sokhna Port |  | 18
inv ( 8 ) Captal one | 8 | 8
IPC00000003 | 3 | 3
IPC#1&2 |  | 1
IPC# 12 WADI |  | 12
Air7 Fin IPC2 | 2 | 2
ORA Ph.2 - IPC 14 | 14 | 14
MDF - IPC 25 | 25 | 25
k-hussain Jan.2023
INV ( 10 ) Hipper | 10 | 10
MDF - IPC19 | 19 | 19
MDF 2 - IPC11 | 11 | 11
IPC#1 HSR ARAB |  | 1
rolling mill- IPC11 | 11 | 11
IPC000009 | 9 | 9
katameyacreeks-IPC25 | 25 | 25
Ora ph1 ipc 26 | 26 | 26
IPC2-TR55 | 2 | 2
IPC007 TR60 | 7 | 7
IPC001 Tank | 1 | 1
ipc42 Emar PKG177 | 42 | 42
IPC#7 HSR |  | 7
24000003
Egat Mechnical ipc 7 | 7 | 7
INV ( 1 ) HY Bark | 1 | 1
inv ( 7 ) Captal one | 7 | 7
MDF FACTORY IPC10 | 10 | 10
Dp world ipc 12 | 12 | 12
MDF Factory IPC23 | 23 | 23
RO Eriction ipc 1 | 1 | 1
Ora ph.2 - IPC12 | 12 | 12
ipc 1 Ora landscape | 1 | 1
ipc 3 | 3 | 3
Spx.2 ipc 07 | 7 | 7
WADY ELNATRON IPC 01 | 1 | 1
200854
200832
Katamya Creeks ipc30 | 30 | 30
Minis Core IPC12 | 12 | 12
Mryotia - IPC02 | 2 | 2
ElMarg IPC03 | 3 | 3
El-Marg IPC05 | 5 | 5
Mdf factory ipc 42 | 42 | 42
Air Dev sihi IPC1 | 1 | 1
port said silosipc11 | 11 | 11
INV ( 5 ) GET | 5 | 5
200810
DM-Comoros Dec.23
IPC007 | 7 | 7
Katamya Creeks ipc36 | 36 | 36
Admin Building ipc 2 | 2 | 2
IPC00010 | 10 | 10
IPC001TR0060 | 1 | 1
IPC000007 | 7 | 7
IPC0000008 | 8 | 8
abo shanab ipc 3 | 3 | 3
ABO SHANAB IPC2 | 2 | 2
Ora Zed (2) ipc 17 | 17 | 17
sorealhardscapeIPC12 | 12 | 12
mansora finish ipc09 | 9 | 9
Playa c038 - ipc 2 | 2 | 2
Minis Core IPC13 | 13 | 13
Eipico - ipc 6 | 6 | 6
IPC0015 TR46 | 15 | 15
Air Dev Alum IPC1 | 1 | 1
FPC Orascom HA JV
Air Dev finsh IPC1 | 1 | 1
Egat mech Equip ipc1 | 1 | 1
ipc 14 port said | 14 | 14
portsaid silos ipc17 | 17 | 17
EL KHATTBA IPC 7+8+9 | 7 | 7
Emaar pkg#177 ipc 46 | 46 | 46
mansora finish ipc10 | 10 | 10
200876
pgk#220 ipc (1) | 1 | 1
bis ipc 4 | 4 | 4
BIS IPC 3+ | 3 | 3
IPC0003TR65 | 3 | 3
wady halfa esc.1
IPC007 TR53 | 7 | 7
MARIOTYA IPC 17 | 17 | 17
Cairo-alex ipc 36 | 36 | 36
cairo-alex ipc 27 | 27 | 27
inv ( 2 ) sixty | 2 | 2
INV ( 4 ) ALparco | 4 | 4
inv ( 1 ) vensia | 1 | 1
OLYMPIC FIN-IPC01 | 1 | 1
port said silosipc16 | 16 | 16
EGAT L&L IPC7 | 7 | 7
230000012
k-hassan aug.2023
mdf factory ipc 33 | 33 | 33
KatamUrbnk ipc ( 2) | 2 | 2
mansora finish ipc11 | 11 | 11
mansora finish ipc12 | 12 | 12
esc.1:10 spx1
New Giza ipc ( 18) |  | 18
sokhna port ex ipc14 | 14 | 14
200931
TAH ipc 10 | 10 | 10
TAH ipc 6 | 6 | 6
TAH ipc02 | 2 | 2
IPC 2 HSR ARAB | 2 | 2
TR46-IPC1FEB | 1 | 1
sokhna port ex ipc15 | 15 | 15
Ora ph2 ipc 18 | 18 | 18
R.O IPC (2) | 2 | 2
inv ( 2 ) monoril | 2 | 2
Playa -c038 ipc 6 | 6 | 6
Rolling Mill ipc 14 | 14 | 14
IPC03TR0069 | 3 | 3
IPC 001 TR0069 | 1 | 1
IPC02TR0069 | 2 | 2
Olympic Elec IPC1 | 1 | 1
13-2023 | 2023 | 2023
Escalation ipc 29:39 | 29 | 29
IPC01TR0081 | 1 | 1
1 final bani suef
Ora ph2 ipc 23 | 23 | 23
201032
New Giza Hos ipc 24 | 24 | 24
IPC2&3TR0078 | 2 | 2
IPC01TR0078 | 1 | 1
IPC05TR0077 | 5 | 5
IPC14TR0055 | 14 | 14
Mohamed Ali IPC02 | 2 | 2
Rent 9/2023
new giza IPC8 | 8 | 8
new giza- IPC12 | 12 | 12
Gawhara IPC7 | 7 | 7
mansora finish ipc15 | 15 | 15
IPC01TR0082 | 1 | 1
Egat Peletizing ip20
Egat Mech Equip ipc3 | 3 | 3
k-salim oct.23
IPC03TR0075 | 3 | 3
K-HASSAN NOV.23
IPC 01/PO30336 | 1 | 1
New Giza Hosp ipc15 | 15 | 15
82-canteen
k-hassan oct.23
IPC01TR0073 | 1 | 1
IPC11TR0048 | 11 | 11
24000002
Inv ( 3 ) A.S | 3 | 3
sokhna ipc11+12+13 | 11 | 11
230000013
mansora finish ipc13 | 13 | 13
Mansoura UNI IPC07 | 7 | 7
GOV2 IPC13+14 | 13 | 13
R05(2) ipc 29+30 | 29 | 29
IPC04 TR0054 | 4 | 4
playa-c045 ipc 6 | 6 | 6
IPC11TR0064 | 11 | 11
Woldorf sharm ipc 6 | 6 | 6
New Giza ipc (21) | 21 | 21
IPC26 elsokhna | 26 | 26
Dp world PH2 ipc (9) | 9 | 9
QASRRASHWANLOT BIPC2 | 2 | 2
Playa c038 ipc 8 | 8 | 8
playa 77
IPC29TR0038 | 29 | 29
cars-lot.2 jan.24
R05(2) ipc 33 | 33 | 33
Driller sales Nov.23
Troysales inv.Dec.23
Rent 12/2023
IPC13 TR51 | 13 | 13
IPC04TR0068 | 4 | 4
ipc 15- MDF Local | 15 | 15
INV ( 2 ) Central Ca | 2 | 2
201052
Revamp 2 SMP2- IPC 1 | 1 | 1
Dp world ipc (4) | 4 | 4
Emaar pkg#189 ipc 18 | 18 | 18
inv ( 5 ) Montazha | 5 | 5
IPC04TR0062 | 4 | 4
201331
201252
201131
201053
IPC final HA luxor o
Acwa Power ipc 1. | 1 | 1
Emaar Pkg#189 ipc22 | 22 | 22
ora landscape ipc 12 | 12 | 12
IPC12TR0048 | 12 | 12
IPC06TR0059 | 6 | 6
IPC20TR0046 | 20 | 20
IPC12&13 TR39 | 12 | 12
Woldorf Astor ipc 22 | 22 | 22
inv ( 3 ) Baragill B | 3 | 3
IPC01TR0084 | 1 | 1
pkg#189-IPC 7 | 7 | 7
k-Abdelwahab feb.24
Air Dev Elec IPC3 | 3 | 3
PORT SAID IPC 22 | 22 | 22
IPC14TR0051 | 14 | 14
Harmain ipc01 | 1 | 1
playa-c038 ipc 10 | 10 | 10
201071
K0001,2
Playa C045- IPC 8 | 8 | 8
IPC06TR0062 | 6 | 6
Emaar pkg#205 ipc7 | 7 | 7
Gawhara IPC2 | 2 | 2
k-gov2-jan22
IPC01TR0092 | 1 | 1
Acwa power ipc 2 | 2 | 2
diplo ipc 16:25 | 16 | 16
201112
Rent 3/2024
sokhna bri esc.17+18
IPC005TR0054 | 5 | 5
Open chanel2 IPC1 | 1 | 1
201272
201151
IPC07TR0061 | 7 | 7
Emaar pkg#163 ipc 32 | 32 | 32
Dp World ipc 13 | 13 | 13
201212
201352
201092
carrefour RBS IPC 5 | 5 | 5
IPC05TR0074 | 5 | 5
IPC23TR0046 | 23 | 23
IPC02TR0084 | 2 | 2
mdf local -ipc 18 | 18 | 18
Rent-001 | 1 | 1
INV 5 | 5 | 5
Rent 7 floor maadi
24000009
EIPICO ipc 16 | 16 | 16
IPC02TR0096 | 2 | 2
R05 2 IPC38 | 38 | 38
Inv ( 1 ) Sentor | 1 | 1
Ora ph2 ipc 30+31 | 30 | 30
ora ph1 ipc 38 | 38 | 38
R05(2) ipc 43 | 43 | 43
WADY HALFA IPC05 | 5 | 5
INV no7 | 7 | 7
201237
201192
201294
201271
RO2 ipc 2 | 2 | 2
IPC#4 Offshore |  | 4
IPC 5 luxoroff | 5 | 5
Egat Lock&Load ipc15 | 15 | 15
PO 3100077862
Dp World ipc 14 | 14 | 14
IPC#1 Marina Towers |  | 1
PKG#189 IPC 24 | 24 | 24
NEW Gas station ipc4 | 4 | 4
MDf Equip -ipc 22 | 22 | 22
MDF Factory ipc 37 | 37 | 37
Playa c469 - ipc 1 | 1 | 1
IPC001 | 1 | 1
inv.1 HSR-oct2-5-24 | 1 | 1
INV ( 8 ) ALparco | 8 | 8
INV ( 6 ) ALparco | 6 | 6
201373
IPC07TR0068 | 7 | 7
IPC04TR0079 | 4 | 4
INV no8 | 8 | 8
IPC10TR0061 | 10 | 10
sokhna port ex 17+18
Escalation13:19.
elmarg 11 final
SOKHNABRI.IPC21FINAL | 21 | 21
spx.2 ipc 4 | 4 | 4
Mariotya ipc20+21+22 | 20 | 20
Mariotya Rem.esc1:22
Abo ghaleb ipc 11:18 | 11 | 11
mariotya ipc15 | 15 | 15
IPC#1-Luxor onshore |  | 1
MDF Equip ipc 25 | 25 | 25
24000013
IPC23FINISH MANSOURA | 23 | 23
SERVICE ROAD IPC 1 | 1 | 1
IPC#1#Roubiky |  | 1
IPC# 002 RABAGH |  | 2
RO5(2) IPC 50 | 50 | 50
ora ph1 ipc 39 | 39 | 39
IPC09TR0068 | 9 | 9
Society Build ipc1 | 1 | 1
wady halfa claim
IPC#3#Roubiky |  | 3
201413
Ora Ph2 ipc 37+38 | 37 | 37
IPC#2#Roubiky |  | 2
IPC#3 - Monorail |  | 3
IPC#6 - Monorai |  | 6
Inv-02 Civil | 2 | 2
Sales Sep.24 KSA
IPC#2 Taamer PII |  | 2
IPC01TR0099 | 1 | 1
201375
WADYELNATRONIPC11+12 | 11 | 11
kanten
Inv 2 HSR | 2 | 2
CAIRO-ALEX IPC19 | 19 | 19
Sultana Ma Zer Final
IPC05TR0084 | 5 | 5
IPC07TR0054 | 7 | 7
IPC22TR0064 | 22 | 22
supply egp ipc8 | 8 | 8
IPC 5 SUPPLY PORT SA | 5 | 5
RME-RS inv.3 | 3 | 3
New Giza ipc 28 | 28 | 28
K-HASSAN-10-24 | 10 | 10
IPC12TR0068 | 12 | 12
IPC007 - Gharably | 7 | 7
Revamp ipc 10 | 10 | 10
SERVICE ROAD IPC 2 | 2 | 2
SPX.2 ESC 1:7
IPC03TR0081(1) | 3 | 3
PORT SAID IPC 29 | 29 | 29
air dev finish ipc1 | 1 | 1
Inv-02 RS | 2 | 2
IPC07TR0079 | 7 | 7
IPC02TR0101 | 2 | 2
IPC02TR0094 | 2 | 2
IPC19TR0053 | 19 | 19
IPC23TR0053 | 23 | 23
IPC02TR0093 | 2 | 2
OCTOBER TUNNELIPC10 | 10 | 10
IPC#5 |  | 5
Katamya Urbnk ipc 3 | 3 | 3
201452
201472
Playa C-469 ipc 5 | 5 | 5
Playa c469 ipc 6 | 6 | 6
PORT SAID SUP. 10
HSR-OCT4
IPC16TR0051 | 16 | 16
IPC14TR0068 | 14 | 14
Inv ( 3 ) T. Pushing | 3 | 3
IPC#4 Ahl Misr Zamal |  | 4
Playa C469 ipc 10 | 10 | 10
201473
Kafr Shokr 11 final
Libya Eqpt.Adv Co.4
IPC#7` |  | 7
IPC1TR74 | 1 | 1
inv ( 12 ) 12-2020 | 12 | 12
K0006 Inv-03 | 3 | 3
K0003 Inv-03 | 3 | 3
OB-RE-PKG#22
cr INV ( 3 ) ALparco | 3 | 3
Cr.Compensation
D0009-OB-Dec-2020/Cr | 2020 | 2020
D0044-OB-Dec-2020/Cr | 2020 | 2020
OB-Final R2
-1 | 1 | 1
Balance Feb 17
10068
Dividend Netting off
OB-MOS-PKG#53
Credit - IPC2 | 2 | 2
DEC ADJ 30
Screap Inv 4/2019 | 4 | 4
1076
SG VAT EGP Invoices
Cr.INV ( 13 ) GET | 13 | 13
cr sd2
Cr Adj. Inv. 22 | 22 | 22
Abuqir inv deduction
68
CR - INV ( 6 ) GET | 6 | 6
ref.1
Cr-40 EGP - Giza III | 40 | 40
kafr shokr ipc9+ | 9 | 9
10185
TETRA - IPC -01-CR | 1 | 1
CR- VAT Coll.2
10020
IPC09TR0066 | 9 | 9
7 EGP - Cairo North
201513
259
1122
OB-ST-6-03-2017 | 6 | 6
8 USD - West Domiat
IPC#FINAL#D0073
Scrap Inv. 04/2020 | 4 | 4
D0038-OB-Dec-2020/Cr | 2020 | 2020
69
opening balance.
CR 180057
Cr.91
10519
Deduct Stmaps/civil
66-Oct-2020 | 2020 | 2020
CR_inv.6 | 6 | 6
180005
CAN.IPC02TR0099(02) | 2 | 2
OB RT 011
rent_004
16 closed
SCD4/003AdjCnl
DEC ADJ14
CR.CR.Soc Inv44/47 | 44 | 44
CR-5-Euro-South helw | 5 | 5
cr81-Dec-2020 | 2020 | 2020
55-Agu-2020 | 2020 | 2020
Cr-Memo-Inv#18+20EGP | 18 | 18
Retention bal. ded.
close 34
DEC ADJ 22
CR Waldorf IPC 20 | 20 | 20
101
CR.TR0015CLOSING.DEC
200404
10075
Cr 4
1132
Cancel(190903-190913 | 190913 | 190913
CR-IPC#1 |  | 1
14 EGP - West Domiat
Ref.soci 53 Assuit
cr29-Apr-20 | 20 | 20
Cr Rent 4th maadi
CR D.m Orange
closing EGP attaqa
Adj ET balance Giza
CR - Scrap
adj commercial fees
15 EGP - Beni Suef
IPC09TR0062 | 9 | 9
10463
220621006
cm 12
DEC ADJ 52
close 16
JPSS-020 /2 | 20 | 20
CR.TR0028CLOSING.DEC
91
P-44-EGY Hاتحاد تشيد | 44 | 44
Cancel the invoice12 | 12 | 12
1 Transmission
D.N Jun 2021
crk-hassan2 nov.2022
Cancel Inv#190921001 | 190921001 | 190921001
106
DEC ADJ 56
CR Waldorf IPC 19 | 19 | 19
DebToshka 4
86
12443
63
reverse
CR-IPC#1. |  | 1
D0037-OB-Dec-2020/Cr | 2020 | 2020
D0045-OB-Dec-2020/Cr | 2020 | 2020
11521
ِِCr.Scrap Inv32/19 | 32 | 32
CR adj inv. 3 | 3 | 3
CR INV 1 | 1 | 1
Inv 68 Iraq | 68 | 68
rev.( 16 EGP-Shabab
8 EGP - South Helwan
rev.( 2 EGP - Sou. H
12929
cr3
Cr.P-2S-10 | 2 | 2
Scrap Inv. 10/2022 | 10 | 10
Cr. Ref Retention M$
INV ( 4 ) HY Bark CR | 4 | 4
2103220002
Cr.Sadat Indust Inv2 | 2 | 2
OB-Retention 4
Cr (4EGP-South.Helw)
Cr-10Captal 1 | 10 | 10
10012
opening balance
478
10182
cr cw4
15
ref.3
Scrap Inv. 11/2022 | 11 | 11
2104220005
Cr-Tah ipc 5 | 5 | 5
cr50-19 nov | 19 | 19
اتحاد تشيد و بناء
09/13/12/2021
Cr-S.Tax- 8 invoices | 8 | 8
Inv ( 8) sixty | 8 | 8
CRToshka Sub Inv. 24 | 24 | 24
10421
Mohamed aly3 3final
1
22/13/03/2022
10005
OB003
CR-005 | 5 | 5
MOC Inv-04 Final | 4 | 4
11583
opening balance 2
OB004
7 USD - Shabab
CR-IPC#2 |  | 2
10362
2008210011
IPC#FINAL#Roubiky
CR.TR0004CLOSING.DEC
Close orascom bal
10+10+12closed
180077
81-Dec-2020. | 2020 | 2020
closing10
Close ASF Balance
CR_inv.9 | 9 | 9
79
close 65
Cr-(WHT+Stamp)
201512
Cr -(WHT + Stamp) 2
51-JUL-2020 | 2020 | 2020
CR - Mahager Project
cr22
CR-S003
47
inv 4 kwt flr cancle | 4 | 4
Egytech balance
216
final_closed
CR.Ret Benban Lot 2
10369
CR-IPC#5 GSCC |  | 5
1130
CR 13
CR 82
10208
11222
inv 6 kwt flr cancle | 6 | 6
10100
Ded Eng Stamps
CR 122
242
OB-SI-PKG#17
21f
DEC ADJ 12
close 70
Deb.adv. $ Toshka 4.
13 EUR Rev. 2
16 EGP - West Domiat
CR-55/2 | 55 | 55
DEC ADJ 51
CR-VAT-2018 Inv. | 2018 | 2018
5 EGP- Suez Gulf
59-Aug-2020 | 2020 | 2020
CR-18-W.hold-Stamp | 18 | 18
OB-Retention 3
D2. West Port said
2105210014
72
INV ( 2 ) Berty Badr | 2 | 2
1072
Ded Inv22 EGP Assuit | 22 | 22
close49
CR K0001-3 | 3 | 3
220421002
D.M 04-2022 | 2022 | 2022
Inv.54 Assuit Akhmem | 54 | 54
Cr 2-2023 | 2023 | 2023
13053
CR17-19jun | 19 | 19
CN Abo Quir Electri
10361
Suez Gulf
close 74
Cr.Tos Lot6 Inv.9 | 9 | 9
CR Acwa ipc 2 | 2 | 2
267
OB 2-Sud-eur
Ref Settlement
50
CR-IPC#3 |  | 3
Libya Eqpt.Adv Co.1
INV ( 12 ) Hyper | 12 | 12
CR- W. Dom invs 2018 | 2018 | 2018
PORTSAID SUPPLYIPC12 | 12 | 12
cr-mariotya ipc17 z | 17 | 17
cr-oct.tunnel ipc 1 | 1 | 1
CR.P-09-13 AccRev | 9 | 9
1124
Cr-for WHT-Four invs
1901220004
opening balance R
cr82-Dec-2020 | 2020 | 2020
295
cr-mini core ipc 11 | 11 | 11
CR-42-19 oct | 42 | 42
Inv.68 Bank charges | 68 | 68
10191
Balance 6
1904220002
D0021-OB-Dec-2020/CR | 2020 | 2020
245
9closed
CR - 9 EGP - Shabab | 9 | 9
CR IPC-12-Saray | 12 | 12
220621005
20 closed
OB-SI-New Giza 2
Cr 12-2023 | 2023 | 2023
Compensation B & D
12103
Cr Adj Inv 11 | 11 | 11
Cr for-other-deduct
84
Cr -5-Euro-South hel | 5 | 5
CM1USD/123/2011/2012
Soci.Timay.358K.M
Royal Cen Zone ipc24 | 24 | 24
SPX ROADS 2 FINAL
Mariotya ESC.19 est
Inv ( 1 ) S05 | 1 | 1
INV ( 1 ) R08-K12 | 1 | 1
INV ( 5 ) Central Ca | 5 | 5
INV ( 15 ) GET | 15 | 15
INV ( 13 ) GET | 13 | 13
20/12/2023
IPC15TR0053 | 15 | 15
ايجار شهر 1 الى 6
3-2023 | 2023 | 2023
IPC001 | 1 | 1
فروق اسعار المريوطية
Egy Exch IPC1 | 1 | 1
IPC#5Port Said 2 |  | 5
220421001
457
Selling Scrap Lot14
220321003
62
21000004
Ref.Ret Benban Lot 2
Ref.Ret Qen-akh 7
21000002
426
10943
33
420
IPC-12-Saray | 12 | 12
399
2105210002
LOC/014
FPC - Mohamed Kamel
2012210036
Inv. 27 Usd | 27 | 27
MIDA Sply. Inv. 5 | 5 | 5
D0025-OB-Dec-2020 | 2020 | 2020
D0029-OB-Dec-2020 | 2020 | 2020
D0040-OB-Dec-2020 | 2020 | 2020
D0048 OB-Dec-2020 | 2020 | 2020
TR0021DEC.Clocing
D0020-OB-Dec-2020 | 2020 | 2020
D0012-OB-Dec-2020 | 2020 | 2020
IPC#22 |  | 22
IPC_1_SARAYA_GAMA
2010210004
cancel credit memo
IPC0006 | 6 | 6
2010210001
2004210012
2002210019
44-2020 | 2020 | 2020
2004210010
2004210009
2002210027
JPSS-020 | 20 | 20
2002210018
10097
Inv.1 Temmay 500 k.v | 1 | 1
2001210004
533
Scrap Lot. 19
180155
471
6 EGP - Aedco
14 EGP - October
63-19 Dec | 19 | 19
Ret... Balance..
Scrap Lot. 03
TETERA-خرسانة-IPC01 | 1 | 1
125/9
10 EGP - Suez Gulf
16 EGP VO Progress
19 EGP MRR Main
36-19 oct | 19 | 19
Refund 06/13/07/2019
180172
1906210009
IPC#1 |  | 1
1909210013
1906210016
1906210017
SCD4/003
3-19-mar. | 19 | 19
Adj. 180178
Soc Inv 26 $ Quna | 26 | 26
180132
Ref . Soc Inv 48Asui | 48 | 48
Insu. Inv.13 Samnood | 13 | 13
TETRA - IPC -01 | 1 | 1
1901210008
Refund Retention Kay
28 EGP - Shabab
26 EGP - Shabab
29 EGP - West Domiat
11 USD- Shabab
204
180163
180162
180106
180154
Inv, 6 usd Borg Arab | 6 | 6
MVR Accomodation
DR - VAT- Egytech 06
Abo Quir Invces
Inv. No.15 KWD Floor |  | 15
Adj. Inv.18 | 18 | 18
Inv 68 Iraq Dewania | 68 | 68
Inv 90 P8 Sammound | 90 | 90
103
Retention USD
180123
89
180043
180039
180038
reverse Attaqa PV am
24
23
180045
DR - VAT- Egytech 03
410498064/0&2
Samanoud 5 inv.81 | 81 | 81
scrab
6 USD - Cairo South
Inv 20 Qatar | 20 | 20
Inv NO.5 KWT Flor | 5 | 5
Inv. 1 | 1 | 1
final kobry el3asma
HYPer
Inv 18 Ghelion | 18 | 18
(2)CW elmostsmrin |  | 2
(11) bni suef |  | 11
(11) biny suef 1 |  | 11
12 zona
Final\
mos 1
OB-ST- PKG#32
1 Elegict
3
4 EGP - Shabab 117
3 EGP - Shabab 117
7 EGP - Shabab 117
DEC ADJ 34
Balance Feb
9 USD - Shabab 117
Balance 11
1 EGP - Suez Gulf
final
DEC ADJ67
(1) elkayan |  | 1
4 - palm hills
3 USD/123/2011/2012
1078
OB 7
Closing Adv. DZD
17/13/07/2021
018/2019
014/2019
011/2019
027/2020 FCV
026/2020 FCV
025/2020 FCV
35-132KVA(9H) | 132 | 132
31-132KVA-J | 132 | 132
7-132KVA- J | 132 | 132
6-132KVA- J | 132 | 132
Close Old Adv Ezz
Close Old Advance
180108
180105
180104
180094
10 EGP - West D. 117
6 EGP - West D. 117
Adv. Balance 9
543
527
180113
5 USD - Shabab 117
9 EGP - Shabab 117
Adj Adv Dec 2017
7 EGP - (VO)progress
6 EGP - VO MRR
Inv 1 EGP VO SG | 1 | 1
6 EGP - Suez Gulf
1 USD - Suez Gulf
14newgiza2
Inv 62 P5Assuit | 62 | 62
Inv.60 Banah 14 | 60 | 60
Inv.57 Banah 13 | 57 | 57
Inv.56 Assuit 3 | 56 | 56
Banha 37 inv.6 | 6 | 6
Inv 28 Damac | 28 | 28
Inv. 26 Damac | 26 | 26
Inv. 25 Damac | 25 | 25
Damac 11
Damac 17
Damac 16
Damac 13
16 Euro-Abo Qeir 117
3571
3926
OB 3927
OB 3929
12
20-
34pkg#22
Ghana24A
25
OB-8 | 8 | 8
DEC ADJ 71
180149
4 EGP - South Helwan
427 EGP abu qeir 118
11
434 EGP abu qeir 118
443 EGP Avice ZTPC
425 EURO Avice ZTPC
401 EGP Avice ZTPC
Clos. east Delta ADV
Balance Adv Feb
23
Inv. 7 Abozabaal | 7 | 7
6
30
1047
1064
1067
1031
OB 2543
3915
2/2013
3593
32 EGP- Giza North 3
7 Euro- South Helwan
180007
3916
(44)pkg#45 |  | 44
42
Barwa 11
OB-28A | 28 | 28
10129
10069
10047
TAM-CW-EGP-13 | 13 | 13
TAM-SW-EGP-07 | 7 | 7
19100023
19100020
BSF-SW-EGP-08 | 8 | 8
BSF-SW-04 | 4 | 4
ISE-CW-EGP-08 | 8 | 8
ISE-CW-EGP-07 | 7 | 7
TAM-SD-EGP-02 | 2 | 2
TAM-SD-EURO-01 | 1 | 1
MOS-CW-EURO-IPC3 F | 3 | 3
BSF-SW-IPC2 | 2 | 2
18100069
16 sd euro mostsmrin
(3)cw elasmailya |  | 3
15sd EURO
15 sd mosstasmreen
SD(11) |  | 11
22050210.7295
180130
180046
10019
ٍSocial 34 Etay 10
DEC ADJ 98
17
Inv 12 Ghelion | 12 | 12
41 Euro - Sokhna 117
(19) sodic club |  | 19
Inv 17 Ghelion | 17 | 17
OB-ST-PKG#17
OB-ST-EL Kayaan
(24)new giza 2 |  | 24
(23) new giza 2 |  | 23
(22) pkg#53 |  | 22
OB-RE-PKG#58
(10)pkg#62 |  | 10
(11)pkg#107 |  | 11
40 EGP-Giza N. III
37 EGP-Giza North 3
39 EGP-Giza N. I&II
Inv. 15 Oewon Mousa | 15 | 15
Inv.4 Temmay Amded | 4 | 4
Inv.3 Temmay Amded | 3 | 3
Inv. 6 Oewon Mousa | 6 | 6
Inv. 2 Oewon Mousa | 2 | 2
Inv.4kafr zeat itay | 4 | 4
Inv.Banysouf 4-358 | 358 | 358
Inv No1 Abo Kirr | 1 | 1
ANG-Cam-Inv 2 | 2 | 2
ANG-Caz-Inv 2 | 2 | 2
OB-ST5
OB-ADJ 1
(1) blagat asmaaliya |  | 1
(1) Ismailia U 4 |  | 1
(1) Ismailia U 3 |  | 1
inv no(3 Euro-Iskrae | 3 | 3
001 - inv - 0004 | 4 | 4
close unappl. east d
17 EGP - West D. 117
2/4/3/2017
Inv No5 Wattanya220 | 5 | 5
Inv No3 Wattanya220 | 3 | 3
Inv. NO.8 KWT Floor |  | 8
Inv NO.2 KWT Flor | 2 | 2
(20)PKG#53 |  | 20
(17)beni suif 2 |  | 17
Royal city fin ipc43 | 43 | 43
12 ZONA
(1) PKG#107 |  | 1
OB-ST- Beni Suif
(3) ELKAYAN |  | 3
Inv.5 Zona 2 | 5 | 5
Inv.04 zona2 | 4 | 4
close unppl cepc
Soci.Inv.50Banah11 | 50 | 50
Inv.24 Damac | 24 | 24
DEC ADJ 13
Inv.1 PIP west | 1 | 1
Soc. 45 Bnha 9
Inv 46 P12El Natroun | 46 | 46
Inv 28 Barwa | 28 | 28
Inv. 26 Barwa | 26 | 26
Inv. 24 Barwa | 24 | 24
INV 3 El Teben | 3 | 3
Inv 4 Abo Zaabl | 4 | 4
Inv 5 Abo Zaabl | 5 | 5
Attka Sand Feb
Inv. 2 PIP West | 2 | 2
2009210005
14 USD - West Domiat
10082
2009210007
2001210003
180143
180124
180009
180008
Inv 10,11,13 SH | 10 | 10
(1) Kanteen |  | 1
OB-ST-Mall Of Egypt
Collec 13,14,15 WD
18 EGP- Shabab
(22) bine suef 2 |  | 22
PO.1 Kayan Healthy
(1) M.B.ZAYID |  | 1
SD (12) |  | 12
SD (9) MOSSTASMREEN |  | 9
Inv 12 Qatar | 12 | 12
22 EGP - Shabab
Abu Quir march
(6) pkg#62 |  | 6
(5)pkg#107 |  | 5
Inv. 8 Civil Final | 8 | 8
Banha Advance
10085
Inv 31 Barwa | 31 | 31
Inv.51 wadi 15 | 51 | 51
Inv.1 Helepolice | 1 | 1
Soc Inv 40 Itay 11 | 40 | 40
Ret.55kafre 3 Final
Inv.55 Elzayat 3 fin | 55 | 55
(19) PKG#53 |  | 19
Inv. 26 USD | 26 | 26
1 EGP - El Tebin 124
7/2017
10022
180053
كانتين 2
Last Inv Cairo Nor $
10571
10331
(25)pkg#53 |  | 25
PKG#85 - IPC FINAL
4 EGP - El Tebin 124
10718
7 USD - Cairo South
22 EGP - West Domiat
Inv.53 Assuit Akhmem | 53 | 53
Inv.51 Assuit Akhmem | 51 | 51
Inv.48 Assuit Akhmem | 48 | 48
Inv.47 Assuit Akhmem | 47 | 47
Inv.33 Assuit Akhmem | 33 | 33
Inv.24 Assuit Akhmem | 24 | 24
inv. 3 Assuit Akhmem | 3 | 3
Inv.36 Akhmem Qena | 36 | 36
Inv.27 Akhmem Qena | 27 | 27
Inv.16 Qena - Akhmem | 16 | 16
Inv.6 Qena Akhmem | 6 | 6
OB-RE-Dp World
10211
25 EGP - Shabab
كانتين شهر 12
10263
9-132KVA | 132 | 132
Inv. NO.5 KWT Floor |  | 5
31A
OB-4B | 4 | 4
6B
41/P/10/ER/2017/USD
(21)sodic club |  | 21
(21)pkg#53 |  | 21
5-132KVA-H | 132 | 132
04-132KVA-H | 132 | 132
05-132KVA-J | 132 | 132
Inv. 5 El Kayan | 5 | 5
3-132KVA-J | 132 | 132
3-132KVA-H | 132 | 132
(004) كانتين يناير |  | 4
Inv 96 P13Abo Matami | 96 | 96
Inv 79 P6Abo Matamir | 79 | 79
Inv. 11 Mostakbal | 11 | 11
Inv. 9 Mostakbal | 9 | 9
Inv. 8 Mostakbal | 8 | 8
Inv. 5 Mostakbal | 5 | 5
10290
Inv. 19 Badr | 19 | 19
Inv. 9 Badr | 9 | 9
Inv. 6 Badr | 6 | 6
19100003
(1)elkayan fainishin |  | 1
(26)bini suif 2 |  | 26
1 EGP - ETO
K(mohamed mansour)
10329
3 feb. Invoices
180110
20 EGP VO CCC Supply
17 EGP VO MRR
180079
180048
1-132KVA-Sup | 132 | 132
10282
(27)sd elmostsmrin |  | 27
180002
KAYAN LOAK&LOAD-IPC4 | 4 | 4
(1) P.O52/323 |  | 1
180055
10268
10332
inv. 4 Assuit Akhmem | 4 | 4
180064
K(Moustafa Khalifa)
Inv. 3 Akhmem Qena | 3 | 3
Inv No 1 Bani suef | 1 | 1
2106210002
2106210001
495
1901210010
2103210014
2009210003
2110210004
2108210009
2105210007
523
12462
11741
11762
11185
10890
180100
180098
180096
ET SI inv 30 EGP-SH | 30 | 30
180020
13 USD - Shabab
12 USD - Shabab
180073
Inv.63- Borg Alarab | 63 | 63
Inv.53 Borg Alarab | 53 | 53
Inv.50 Borg Alarab | 50 | 50
Inv.23 Borg Alarab | 23 | 23
Inv.21 Borg Alarab | 21 | 21
Inv.15 Borg Alarab | 15 | 15
Inv.13 Borg Alarab | 13 | 13
10398
PKG#107-IPC (14) | 14 | 14
k-m.khalifa-suezstee
تأمينات م3&4 - م قنا | 3 | 3
Scrap Inv.3/2018 | 3 | 3
soc 6 abo el matamer
IPC4-KAYAN FAINSHING | 4 | 4
18100064
10576
10521
10520
210
(6)cw elasmaaliya |  | 6
Minis Core IPC07 | 7 | 7
Inv. 27 USD | 27 | 27
44649.31
180037
(1)alamal lock&load |  | 1
BSF-CW-IPC 7 | 7 | 7
1 USD - Lina
k-m.khalifa ministie
Inv.9 Qena - Akhmem$ | 9 | 9
Inv.80Samanood 4 | 80 | 80
Inv.1 Assuit Akhmem$ | 1 | 1
PSP ELCO-IPC 03 | 3 | 3
10217
10404
Inv.21 Assuit Akhmem | 21 | 21
Inv. No. 3 |  | 3
MOHAMED ALY-IPC02 | 2 | 2
AIR DEFENSE IPC01 | 1 | 1
SOKHNA TUNNEL-IPC1 | 1 | 1
Commercial fees SH
Inv.10 Qena- Akhmem$ | 10 | 10
Inv.34 Akhmem Qena | 34 | 34
01042018
Inv.1-2 Project Badr | 1 | 1
Inv. 13 Balat lot 3 | 13 | 13
Inv. 11 Balat lot 3 | 11 | 11
Inv. 8 | 8 | 8
Inv. 4 Balat lot 3 | 4 | 4
30A
SODIC CLUB-IPC 32 | 32 | 32
ELSEWEDY MEP-IPC05 | 5 | 5
ELSEWEDY UNI- IPC06 | 6 | 6
19100031
19100030
ELSEWEDY UNI-MEP-03 | 3 | 3
Inv.11Assuit Akhmem$ | 11 | 11
10456
10403
bani suif 2-ipc 28 | 28 | 28
PKG#53 -IPC 35 | 35 | 35
Site Foklift Rent
MinisLandscape IPC05 | 5 | 5
Hassan Mamoun Final
PO - Mohamed Aly 105
PO - Mohamed Aly 114
ELBARON-IPC FINAL
ref.soci12-16 Assuit | 16 | 16
M.B.Z.TUNNEL IPC 4 | 4 | 4
Inv.1 Borg Alarab | 1 | 1
DM 2 Borg Alarb
Cancel
Abolil Inst. Final
Inv.23 Qena- Akhmem$ | 23 | 23
JPSS-19 | 19 | 19
OB RT 007
Inv.8 Rcc | 8 | 8
Inv.5 Rcc | 5 | 5
Inv. 2 Badr | 2 | 2
10538
TAM-CW-EGP-06 | 6 | 6
2cw bine suif
Inv.44 Qena Akhmem | 44 | 44
Inv.37 Assuit Akhmem | 37 | 37
Inv. 15 Balat Lot 2 | 15 | 15
Inv.10Assuit Akhmem$ | 10 | 10
Inv. 4 Balat Lot 2 | 4 | 4
final alobour bridge
kantenMisitiryKhlifa
Inv. 1 Balat Lot 2 | 1 | 1
Inv10 Usd borg alarb | 10 | 10
Inv. No.10 KWD Floor |  | 10
Inv 94P9Abo Matami | 94 | 94
Inv.3 Qena - Akhmem$ | 3 | 3
180141
BSF-SW-05 | 5 | 5
10540
180171
180148
Inv.21Assuit Akhmem$ | 21 | 21
Inv.18Assuit Akhmem$ | 18 | 18
R05 IPC#032 |  | 32
R5-IPC23 | 23 | 23
K-HASHIM-GAZI MALL
k-m.badawy-mintra
LOC 027
LOC/019
LOC/017
CON/021
IMP-055 | 55 | 55
IMP-052 | 52 | 52
IMP-037prog for33/34 | 37 | 37
10387
10370
OB RT 003
10458
KAYAN SIHY-IPC 1 | 1 | 1
SOREAL-IPC12 | 12 | 12
SOREAL-IPC11 | 11 | 11
soreal - ipc 02 | 2 | 2
213
10489
TAM-SD-EGP-03 | 3 | 3
180150
OB TE005sp
K-A.Osman-RoyalCity
PKG#144- IPC04 | 4 | 4
MOS-SD-EURO-13 | 13 | 13
19100019
BO-001 | 1 | 1
Inv 3 EUR Asec Spare | 3 | 3
DPW IPC031 | 31 | 31
DP World IPC026 | 26 | 26
Soc Inv 42-43-44Quna | 42 | 42
Ref Soc Inv 25 quna | 25 | 25
Inv.17Usd borg alarb | 17 | 17
Inv.11 Borg Alarab | 11 | 11
ELSEWEDY UNI-IPC05 | 5 | 5
19100027
Inv.40 Assuit Akhmem | 40 | 40
Inv.46 Assuit Akhmem | 46 | 46
Inv.20Assuit Akhmem$ | 20 | 20
Inv.7 Qena - Akhmem$ | 7 | 7
10077
Sales-03 | 3 | 3
211
KAYAN LOAK&LOAD-IPC7 | 7 | 7
KAYAN SAHY- IPC02 | 2 | 2
ROYAL CITY-IPC15 | 15 | 15
BSF-CW-EURO-05 | 5 | 5
Inv. 8 Abo Zabal | 8 | 8
19100025
1902210007
10532
Refund 13/13/02/2019
PKG#117 -IPC 10 | 10 | 10
2011210002
2001210005
545
506
488
1908210016
1908210015
180175
180167
180177
Elkayan Inv.16 | 16 | 16
2004210013
505
10615
Inv. 3 Mostakbal | 3 | 3
Inv.22 Assuit Akhmem | 22 | 22
Inv.5 kafr zeat itay | 5 | 5
Insu. inv.3 itay 358 | 3 | 3
Soc 12 samanod
Inv100 P12- Sammound | 100 | 100
K-A.osman-ismlia-mar
pkg#144-IPC11 | 11 | 11
PKG#144-IPC-02 | 2 | 2
009/2019
R5-ZONE 2-IPC 01 | 1 | 1
10574
Inv. 7 Eltbeen | 7 | 7
1902210003
1902210002
10763
10759
10513
10597
223
226
Civil/J011
IPC#3 |  | 3
10534
10657
SOREAL- IPC 01 | 1 | 1
K-Hussien Mansour-04 | 4 | 4
Inv. 10 /2019 | 10 | 10
(27)bini suif 2 |  | 27
PSPELCO-IPC09 | 9 | 9
Inv. 10 Badr | 10 | 10
10675
10517
10457
10575
10637
(36) PKG#22 |  | 36
231
Inv . 01/2019 | 1 | 1
inv. 03 Scrap 2019 | 3 | 3
PKG#101-IPC03 | 3 | 3
Benban Lot 2 Inv. 34 | 34 | 34
Benban Lot 2 Inv. 15 | 15 | 15
Benban Lot 1 Inv. 32 | 32 | 32
Benban Lot 1 Inv. 17 | 17 | 17
Benban Lot 1 Inv. 30 | 30 | 30
Benban Lot 1 Inv. 22 | 22 | 22
Benban Lot 1 Inv. 27 | 27 | 27
Benban Lot 1 Inv. 25 | 25 | 25
Benban Lot 1 Inv. 5 | 5 | 5
ISE-CW-EGP-14 | 14 | 14
ISE-CW-EGP-15 | 15 | 15
Soci. 16 Fin. Matmer
Inv.08 Sugar OHTL | 8 | 8
Inv.27 Borg Alarab | 27 | 27
1901210015
1901210006
PSP ELCO-IPC10 | 10 | 10
UNI-FIN&MEP-IPC10 | 10 | 10
236
1904210016
Benban Lot1 Inv 1USD | 1 | 1
230
234
180174
ROYAL CITY-IPC35 | 35 | 35
ROYAL ZONE2-IPC18 | 18 | 18
Inv. 7 Project S 1 | 7 | 7
Kanteen-Ismalia-July
Kanteen-Sodic-June19
Kanteen-Uni-July2019
AMAL LOCK&LOAD-FINAL
Inv. 6 Project S 1 | 6 | 6
10716
SOREAL-IPC04 | 4 | 4
SCD4/003Adj
SCD4/003-ZmbShar
10788
Port Said Inv. 4 | 4 | 4
Adv.CR. Port Said
Inv.9 Assuit Akhmem | 9 | 9
Inv.8 Assuit Akhmem | 8 | 8
Inv. 13 Badr | 13 | 13
23/2019 ٍ Scrap
10127
uni fi&mep-ipc 07 | 7 | 7
10870
1907210002
sales-2 | 2 | 2
021/2019
248
Inv.35 Akhmem Qena | 35 | 35
Kanteen-Kayan-Aug10%
1908210005
2*4 EGP - Suez Steel
256
262
inv ( 3 ) 23-5-2021 | 3 | 3
INV(12)310520 | 12 | 12
SCD4/004-ZmbShar
inv ( 1 ) 21-12-2020 | 1 | 1
510
503
H,A/IPC05/PO52/323 | 5 | 5
MANGROVE-IPC09 | 9 | 9
MANGROVE-IPC08 | 8 | 8
Benban Lot 2 Inv. 5 | 5 | 5
10655
10656
BSF-SW-EGP-10 | 10 | 10
PKG#101- IPC12 | 12 | 12
247
9-19-April | 19 | 19
Benban Lot 1 Inv. 4 | 4 | 4
TAM-SW-EGP-08 | 8 | 8
Inv. 1 Sugar 33 OHTL | 1 | 1
Inv. 10 Farm | 10 | 10
PKG#53 - IPC40 | 40 | 40
Inv. 12 Balat Lot 2 | 12 | 12
ELALAMEEN ROAD-IPC01 | 1 | 1
Kanteen-R05-Sep-2019 | 2019 | 2019
Benban Lot2 Inv 6 $ | 6 | 6
4-2019 | 2019 | 2019
M.ALY FAHMY L&L-01 | 1 | 1
Kanteen-Uni-Oct-2019 | 2019 | 2019
18-2020 | 2020 | 2020
Benban Lot2 Inv 3 $ | 3 | 3
524
513
499
498
487
MIDA Ins. Inv. 2 | 2 | 2
15-sals-2019 | 2019 | 2019
Benban Lot 1 Inv. 11 | 11 | 11
32-19 -سثح | 19 | 19
10956
10910
10755
Invoice No:11
2002210001
reclass rec 1020
Inv(2)090120 | 2 | 2
1908210010
OLYMPIC-IPC01 | 1 | 1
49-19 nov | 19 | 19
47-19 nov | 19 | 19
494
IPC#2 |  | 2
R5-ZONE1-IPC08 | 8 | 8
28-19 Aug | 19 | 19
Inv.44 Borg Alarab | 44 | 44
10991
Benban Lot 2 Inv. 21 | 21 | 21
Inv. 01 Farm | 1 | 1
Inv.03 Sugar OHTL | 3 | 3
Benban Lot 2 Inv. 24 | 24 | 24
Kanteen-minis-Dec-19 | 19 | 19
3-19Mar | 19 | 19
24-19Aug | 19 | 19
15-19June | 19 | 19
IPC#1 |  | 1
30YU GALALA-L&L-1FIN | 1 | 1
MIN.ALLOCATION-IPC03 | 3 | 3
MINISTIRY OLD-IPC03 | 3 | 3
486
11086
34-19oct | 19 | 19
13-SALS
H,A/IPC07/PO52/323 | 7 | 7
inv(4)101219 | 4 | 4
MANGOROVE RENT-IPC01 | 1 | 1
R5-IPC10 | 10 | 10
48-19 nov | 19 | 19
511
1906210003
1903210008
282
Lot. 20
Scrap Lot. 11
Scrap Lot 19-1 | 1 | 1
10133
SOREAL -IPC09 | 9 | 9
Inv.24Assuit Akhmem$ | 24 | 24
Toshka Sub Inv. 09 | 9 | 9
Toshka Sub Inv. 05 | 5 | 5
Toshka Sub Inv. 03 | 3 | 3
Inv.3 – Lot 2 | 3 | 3
1100000
IKEA-IPC+02
KAYAN LOAK&LOAD08
519
Inv.4 Rcc | 4 | 4
Benban Lot 1 Inv. 26 | 26 | 26
Toshka Lot 4 Inv .19 | 19 | 19
Toshka Lot 4 Inv .3 | 3 | 3
Toshka Lot 6 Inv .21 | 21 | 21
Toshka Lot 6 Inv .12 | 12 | 12
Toshka Lot 6 Inv $3 | 3 | 3
Lot. 05 - 3 | 3 | 3
ISE-CW-EGP-20 | 20 | 20
288
IPC#1`2`3 |  | 1
ISE-SD-EURO-05 | 5 | 5
TAM-CW-EURO-08 | 8 | 8
Scrap 34/2019 united
Lot. 02 - 1 | 1 | 1
Scrap Lot 19-2 | 2 | 2
Inv.52 Borg Alarab | 52 | 52
Inv.47 Borg Alarab | 47 | 47
SAFIER BRIDGE-IPC01 | 1 | 1
305
10427
11024
10990
11016
Refund of scrap valu
Inv. 7 Mostakbal | 7 | 7
CFC-IPC16 | 16 | 16
SiemensLEKELA IPC012 | 12 | 12
LEKELA-IPC05 | 5 | 5
LEKELA-IPC04 | 4 | 4
11161
10215
S.U.PHASE2-IPC03 | 3 | 3
11027
63-19- Dec | 19 | 19
Kanteen-Kayan-Feb-20 | 20 | 20
Toshka Sub Inv. 03 $ | 3 | 3
Toshka Sub Inv. 11 $ | 11 | 11
PKG#162-IPC04 | 4 | 4
Inv 4 EUR Asec Spare | 4 | 4
amedment
Re. Soc inv 22 To 25 | 22 | 22
IPC#4 |  | 4
304
301
2003210006
10008
43-19 oct | 19 | 19
10013
10004
10034
10038
10040
PKG#140- IPC09 | 9 | 9
Inv.04 Sugar OHTL | 4 | 4
Inv 4 Sugar S/s | 4 | 4
ISE-SD-EGP-03 | 3 | 3
HYPERONE-IPC06 | 6 | 6
Inv(3)250120 | 3 | 3
PKG #163 IPC018 | 18 | 18
PKG #163 IPC015 | 15 | 15
PKG#163-IPC07 | 7 | 7
PKG#163-IPC06 | 6 | 6
10025
10030
10031
10005
10009
514
Inv.59 Borg Alarab | 59 | 59
Inv.56 Borg Alarab | 56 | 56
Inv.55 Borg Alarab | 55 | 55
MIN LAND ESCAPE-IPC1 | 1 | 1
Inv.6 Rcc | 6 | 6
330
328
313
331
311
تكيفات و تجهيزات مكا
023/2020 FCV
11281
INV(9)150420 | 9 | 9
10033
Inv. 1 Oewon Mousa | 1 | 1
Inv.74 Borg Alarab | 74 | 74
IPC#13 |  | 13
2002210016
10006
11301
ANG-Cam-Inv 4 - Ints | 4 | 4
FPC
LOC/006 Rev0
Adjust rec.qir 117
Adjust 1907210013-
21-2020 | 2020 | 2020
43/P/10/ER/2017/USD
10967
10886
10364
10222
10141
2003210003
IPC#6 |  | 6
10074
Inv(5)240320 | 5 | 5
2005210006
Kanteen-R05-May-2020 | 2020 | 2020
347
R5 - IPC16 | 16 | 16
2004210006
10042
2006210007
10194
10173
MANGROVY-IPC06 | 6 | 6
22-2020 | 2020 | 2020
PKG#162-IPC05 | 5 | 5
538
351
Inv.31 Borg Alarab | 31 | 31
Suez S4 Inv. 01 | 1 | 1
Suez S4 USD Inv. 04 | 4 | 4
East Owainat Inv. 01 | 1 | 1
Inv. Barwa 38
11621
DP WORLD - IPC15 | 15 | 15
35-May-20 | 20 | 20
37-Jun -2020 | 2020 | 2020
357
11224
Imp-041 Rev0 | 41 | 41
Con-011 | 11 | 11
inv(1)300620 | 1 | 1
Inv 2 $ Sugar S/s | 2 | 2
R5-FINSHING-IPC01 | 1 | 1
363
CFC- IPC07 | 7 | 7
359
360
200067
IMP-053 | 53 | 53
Loc-007 Rev0 | 7 | 7
ESU2-ARCH&MEP-IPC05 | 5 | 5
OB 3922
IPC_12_rowad_poly
3
SOREAL-IPC14 | 14 | 14
IMP-048 | 48 | 48
Con-014 | 14 | 14
32-2020 | 2020 | 2020
Inv 8 Sugar S/s | 8 | 8
Toshka Lot 4 Inv .5 | 5 | 5
Kanteen-Uni-Aug-2020 | 2020 | 2020
53-Jul-2020 | 2020 | 2020
Toshka Lot 4 Inv .11 | 11 | 11
50/P/10/ER/2017/USD
11542
11457
10146
Inv. 07 Farm | 7 | 7
R05(2) ipc46 | 46 | 46
R05 Zone 2 IPC019 | 19 | 19
51-2020 | 2020 | 2020
Inv.7 Rcc | 7 | 7
11441
CFC-IPC09 | 9 | 9
ELBARON-IPC01 | 1 | 1
Ref Retention Borg $
38-2020 | 2020 | 2020
inv ( 1 ) 1-2-2021 | 1 | 1
SCD1x/007
Marsa Alam EGP Inv 3 | 3 | 3
IPC-15-Saray | 15 | 15
IPC_2_Gama_Saraya
2008210008
Kanteen-Mangrovy-Oct
10064
Adjust 180177-
Inv.24Usd borg alarb | 24 | 24
58-AgU-2020 | 2020 | 2020
42-Jun-2020 | 2020 | 2020
10 feb 20
IPC_7_GAMA_A17
IPC_2_Rowad_gouna
IPC_15_Rowad_Poly
46-2020 | 2020 | 2020
R5 FINSHING-IPC05 | 5 | 5
ROYAL ZONE-IPC12 | 12 | 12
Cairo-alex ipc 38 | 38 | 38
Cairo-alex ipc 37 | 37 | 37
cairo-alex ipc 29 | 29 | 29
CAIRO-ALEX IPC24 | 24 | 24
Cairo-Alex IPC011 | 11 | 11
Cairo-Alex IPC03 | 3 | 3
11455
10663
366
382
10023
LEKELA-IPC03 | 3 | 3
LEKELA-IPC02 | 2 | 2
IPC#1 |  | 1
11701
R5 - IPC21 | 21 | 21
11864
DP WORLD -IPC20 | 20 | 20
IPC#6 |  | 6
MIN-ALLOCATION-IPC02 | 2 | 2
Ora Ph 1 ipc 37 | 37 | 37
ORA ph 1 ipc (28) | 28 | 28
Ora Zed Ph1 IPC05 | 5 | 5
18100052
Inv. 10 Mostakbal | 10 | 10
JV-AC-EE-Inv-002 | 2 | 2
10273
10204
76-Nov-2020 | 2020 | 2020
scrap lot no 16
scrap lot no 14
scrap lot no 10
Toshka Lot 4 Inv .9 | 9 | 9
10143
379
380
377
MIN-ALLOCATION-IPC5 | 5 | 5
Inv 15/2020 Transmis | 15 | 15
CFC-IPC12 | 12 | 12
6
E.U2-ENABLING-10 | 10 | 10
11781
11666
11667
PKG#117-IPC FINAL
Toshka Sub Inv. 15 $ | 15 | 15
10413
Toshka Lot 4 Inv .13 | 13 | 13
50-2020 | 2020 | 2020
383
Toshka Sub 4 Inv. 03 | 3 | 3
Toshka Sub Inv. 19 $ | 19 | 19
11261
31-2020 | 2020 | 2020
inv ( 13 ) | 13 | 13
2012210001
IPC_3_Mivida
IPC_3_Gama_Saray
10045
Inv 3 Sugar S/s | 3 | 3
IPC#1 & Final |  | 1
BNI SUEF OLD-IPC FIN
E.US2-MEP-IPC11 | 11 | 11
Katamya ipc (31) | 31 | 31
katameya-IPC23 | 23 | 23
Katameya IPC16 | 16 | 16
katmeyacreeks ipc12 | 12 | 12
KatameyaCreks IPC010 | 10 | 10
inv ( 12 ) 30-9-2020 | 12 | 12
inv (27) AL15-2-2021 | 27 | 27
soreal - 1 | 1 | 1
R05-1 | 1 | 1
ISE-SD-EGP-02 | 2 | 2
ISE-CW-EGP-25 | 25 | 25
Toshka Lot4OH Inv.01 | 1 | 1
Re Soc Inv.2 Temmay | 2 | 2
ROYALZONE2-IPC13 | 13 | 13
MANGROVY CLAIM-IPC12 | 12 | 12
SHOROUK DRIDGE-IPC02 | 2 | 2
SHOROUK BRIDGE-IPC01 | 1 | 1
Final PC
KAYAN MEP1-IPC06 | 6 | 6
11825
IPC_20_Rowad_Seast
Invoice
11922
IPC#5 - Gharably |  | 5
IPC#1` - Gharably |  | 1
IPC#26 |  | 26
ROYAL CITY2-IPC16 | 16 | 16
2007210012
Inv. 10 Oewon Mousa | 10 | 10
IPC#1 |  | 1
Mangrrovy - 2 | 2 | 2
ORA L&L-IPC03 | 3 | 3
ORA ZED-IPC01 | 1 | 1
Inv. 24 Badr | 24 | 24
PKG#140-IPC20 | 20 | 20
2102210002
2102210001
FPC closing
11783
11645
IPC_6_Mivida
elco egat ipc09 | 9 | 9
IPC_18_Rowad_Poly
6-2021 | 2021 | 2021
2012210028
Acroket Company - 03 | 3 | 3
10202
IKEA-IPC13 | 13 | 13
ROYAL CITY-IPC38 | 38 | 38
IKEA2-IPC03 | 3 | 3
IPC_8_Saray
IPC_19_Rowad_S_east
SOREAL-IPC23 | 23 | 23
200161
IPC#1 Assuit |  | 1
10382
10103
ABASELAQAD-IPC1FINAL | 1 | 1
TITRA-OVM-IPC01 | 1 | 1
11804
ELAmeed Inv. 01 Fina | 1 | 1
2012210026
2103210005
MDF - IPC 14 | 14 | 14
MDF IPC01 | 1 | 1
IPC#1 .PKG#178 |  | 1
CFC-IPC17 | 17 | 17
11950
12067
FPC
410
12075
11884
inv ( 2 ) montazha | 2 | 2
INV (17 ) Final Kat | 17 | 17
Inv 11 Sugar S/s | 11 | 11
Inv. 6 Sugar 33 OHTL | 6 | 6
Inv(3)300420 | 3 | 3
IPC#3 |  | 3
2104210005
ANG-Cam-Inv 6 | 6 | 6
M.ALY-IPC03 | 3 | 3
MIN ALLOCATION-IPC06 | 6 | 6
Ref.soci51-52 Assuit | 52 | 52
Borg Inv. 27 USD | 27 | 27
R05 - 04 | 4 | 4
East Owainat Inv. 03 | 3 | 3
PKG#178-IPC02 | 2 | 2
10570
53
60
IPC#3 Madkour |  | 3
12074
2105210012
Inv. 04 Future OHTL | 4 | 4
PKG #177 IPC010 | 10 | 10
PKG#177-IPC3,4 | 3 | 3
Inv.5 - Lot 1 | 5 | 5
Toshka Lot 4 Inv $9 | 9 | 9
Kafr Shokr_IPC02 | 2 | 2
Mostakbal-8 Inv.01 | 1 | 1
PKG#101-IPC19 | 19 | 19
200249
200248
PKG#140-IPC19 | 19 | 19
Diplo Dist IPC06 | 6 | 6
21000001
PKG #163 IPC013 | 13 | 13
Air Force Inv . 07 | 7 | 7
Mansora ipc10 | 10 | 10
faculty mansora-ipc1 | 1 | 1
R5 FINSHING-IPC7* | 7 | 7
R5-ZONE01-IPC02 | 2 | 2
Sadat Indust Inv. 07 | 7 | 7
Toshka Lot 6 Inv .18 | 18 | 18
IPC#2 Assuit |  | 2
Mangroovy IPC017 | 17 | 17
IPC-12-Saray-2 | 12 | 12
IPC_11_Saray
Ret Ref 03/13/06/21
11963
12072
Dry Port Inv. 05 | 5 | 5
ODP ipc3 | 3 | 3
ODP IPC01 | 1 | 1
Hosh Essa Inv. 05 | 5 | 5
Hosh Essa Inv. 04 | 4 | 4
Hosh Essa Inv. 3 Equ | 3 | 3
Marsa Alam EGP Inv 4 | 4 | 4
Toshka Lot4OH Inv.03 | 3 | 3
ElGouna-Apr-May21
IPC#2 |  | 2
EGAT Water Tank IPC1 | 1 | 1
Sultana Malak IPC01 | 1 | 1
Royal City IPC20 | 20 | 20
ROYAL CITY2-IPC19 | 19 | 19
Royal City IPC021 | 21 | 21
10785
IPC#2 Moneeb |  | 2
Katameya Creks IPC07 | 7 | 7
lekela-po2
lekela- po01
IPC-9-Playa | 9 | 9
IPC-8-PLAYA | 8 | 8
IPC-6-PLAYA | 6 | 6
Kayan July21 Kanteen
KantenAirDefense Jul
inv ( 3 ) Captal 1 | 3 | 3
12384
11951
11949
11942
EGAT-IPC18 | 18 | 18
GOV2 IPC05 | 5 | 5
IPC_14_IndoorHall
Inv.12 - Lot 1 | 12 | 12
10192
10822
ANG-Cam-Inv 8 | 8 | 8
Extension kayn Inv 1 | 1 | 1
21000003
inv. 30,31,33 EUR | 30 | 30
12445
2106210003
2008210003
12542
Kafr Shokr IPC04 | 4 | 4
ora ph 2 ipc 24 | 24 | 24
ORA PH.2- IPC13 | 13 | 13
Toshka Lot4OH Inv.05 | 5 | 5
IPC#4 HAC |  | 4
East Owainat Inv. 05 | 5 | 5
Air Force Inv . 05 | 5 | 5
IPC#2 Monorail |  | 2
10241
INV (1) Final | 1 | 1
R05 Zone 2 IPC016 | 16 | 16
Invoice 07/2021 | 7 | 7
12163
10824
10762
IPC03 | 3 | 3
IPC#1 - Ahl Misr Gha |  | 1
MDF IPC02 | 2 | 2
East Owainat Inv.2 V | 2 | 2
Cairo Alex IPC08 | 8 | 8
MR.ADHAM-IPC002 | 2 | 2
kanten GOV2 Sep 2021
Ref.Ret Asuit. akhm
ENG/043
10742
10904
inv ( 1 ) 30112021 | 1 | 1
PKG #177 IPC018 | 18 | 18
23000001
12447
Sodic Soreal IPC027 | 27 | 27
IPC#1 - Sokhna Port |  | 1
2108210011
IPC-13-Saray | 13 | 13
Invoice 09/2021 | 9 | 9
10321
2108210004
GOV 2 - IPC04 | 4 | 4
Toshka Lot 6 Inv .27 | 27 | 27
Inv. 15 Heliopolise | 15 | 15
FPC
SiemensLEKELA IPC013 | 13 | 13
Kanten OCT/21 Creeks
المصطفى للمقاولات
Inv 12 Sugar S/s | 12 | 12
2110210006
EGAT IPC05 | 5 | 5
IPC_1_Cement
10923
11025
11028
10942
Katamya Creeks ipc33 | 33 | 33
Katameya CreeksIPC24 | 24 | 24
IPC#1-Sokhna Bridge |  | 1
28
Wat Pump Obour Inv.7 | 7 | 7
Wat Pump Obour Inv.5 | 5 | 5
Zafra Souf Final4Ins
2107210002
WALDORF ASTORIA IPC5 | 5 | 5
El-Marg IPC07+ | 7 | 7
Maryotia IPC012 | 12 | 12
Ref.Ret Asuit akh 4
2110210002
456
467
MAHWER ELSALAM-IPC1F | 1 | 1
12788
IPC#6 - Madkour |  | 6
IPC#2 |  | 2
IPC#02 |  | 2
pkg #177 IPC021 | 21 | 21
11292
11003
Dr.adv. Kfr Naser T
Kanteen DEC21Olympic
inv ( 2 ) Ring R | 2 | 2
Mostakbal-8 Inv.04 | 4 | 4
12708
200430
PKG #140 IPC026 | 26 | 26
Toshka Sub 4 Inv. 02 | 2 | 2
12688
12750
SPX.1 IPC 21 | 21 | 21
Spx.1 ipc20 | 20 | 20
spx1 ipc19 | 19 | 19
sokhna port ipc16 | 16 | 16
HALLFINISHING2 IPC01 | 1 | 1
IPC#04 Assuit |  | 4
Kanteen DEC21 Air
2112210001
IPC#5 - Monorail |  | 5
428
Ref. Akhmem Asuit4T
Ref. Akhmem Asuit5T
41
2112210006
11263
11182
NEW GIZA HOS IPC27 | 27 | 27
New Giza Hos ipc(17) | 17 | 17
inv ( 2 ) | 2 | 2
EGAT L&L IPC6 | 6 | 6
PKG #177 IPC023 | 23 | 23
Sadat Indust Inv. 05 | 5 | 5
EGAT IPC08 | 8 | 8
200549
k-kattamya-jan2022
437
464
IPC-20-SARAY | 20 | 20
IPC-19-SARAY | 19 | 19
IPC-Final-R05
12668
460
inv 7-8-9 Montazha | 7 | 7
port said ipc21 | 21 | 21
port said silosipc19 | 19 | 19
port said silos ipc7 | 7 | 7
Port Said Silos IPC2 | 2 | 2
IPC 7 SUPPLY EGP | 7 | 7
PORT SAIED IPC 28 | 28 | 28
10308
PKG#163 IPC 20 | 20 | 20
ANG-Cam-Inv 5 - Ints | 5 | 5
k-soreal-jan22
Invoice 02/2022 | 2 | 2
12931
12828
12831
IPC#3 Luxor offshore |  | 3
ikea 2 ipc04 | 4 | 4
12690
MIDA Ins.inv.11 | 11 | 11
11405
egat water tank ipc8 | 8 | 8
11369
ELSEWEDY HQ ipc12 | 12 | 12
k-hassan-mar22
Material EES2
Scrap 19-23 | 23 | 23
11323
47
73
FacultyMedcine IPC08 | 8 | 8
Scrap Inv. 04/2022 | 4 | 4
IPC#4 Luxor Offshore |  | 4
Port Said Inv. 5 | 5 | 5
P-45-Portsaid Inv.2$ | 2 | 2
451
Inv 73 Abu Quir Badr | 73 | 73
70
11747
Suez S4 Inv. 15 | 15 | 15
Hosh Essa Inv. 06 | 6 | 6
mdf factory2 ipc01 | 1 | 1
200565
29-2021 | 2021 | 2021
inv ( final )
220421008
220321001
MDF Factory ipc 36 | 36 | 36
522
11454
Ret Phosfat T
200564
12909
Dry Port Inv. 08 | 8 | 8
Dry Port Inv. 06 | 6 | 6
Waldorf- IPC 19 | 19 | 19
waldorf IPC 12 | 12 | 12
Pkg#189 ipc02 | 2 | 2
pkg #189 ipc 11 | 11 | 11
wady halfa ipc 4 | 4 | 4
wady halfa ipc02 | 2 | 2
Wadi Halfa ipc 01 | 1 | 1
11599
11541
MIDA Sply.inv.12 | 12 | 12
abo Ghaleb ipc02 | 2 | 2
ABO GHALEB IPC01 | 1 | 1
Sadat Indust Inv. 04 | 4 | 4
Inv.4988/Sp/H&J-02 | 4988 | 4988
220421003
220421002
D0028-OB-Dec-2020D.M | 2020 | 2020
hst sokhna ipc01 | 1 | 1
Gov 2 - IPC03 | 3 | 3
MANSOURA FINISHIPC28 | 28 | 28
Mansora Finish ipc06 | 6 | 6
MDF FACTORY3 IPC03 | 3 | 3
11620
200584
Benban Lot 2 Inv. 19 | 19 | 19
Pkg#177 IPC32 | 32 | 32
Marsa Alam Equ Inv 4 | 4 | 4
Marsa Alam EGP Inv15 | 15 | 15
Marsa Alam EGP Inv12 | 12 | 12
Marsa Alam EGP Inv10 | 10 | 10
Toshka Lot 4 Inv .25 | 25 | 25
Ora landscape ipc 20 | 20 | 20
Ora Landscape ipc 19 | 19 | 19
Ora Landsca ipc13-14 | 13 | 13
Prog. for Eng. SC
LOC/026
SCD4x/0013
08/13/06/2022 Gh.Ret
2 track mach Inv.01 | 1 | 1
pkg#177-IPC35 | 35 | 35
Toshka Lot 6 Inv $10 | 10 | 10
IPC-10-PLAYA ROOF | 10 | 10
egat ipc 13 | 13 | 13
EGAT IPC04 | 4 | 4
k-olimpic-jan2022
k-hassan jun2022
new giza hos ipc05 | 5 | 5
10-2021 | 2021 | 2021
13052
31-2021 | 2021 | 2021
200629
Ref-Ret-Toshka Lot6T
Ref-Ret-Benba lot1T
505
507
502
PKG#163 IPC 22 | 22 | 22
IPC#15 - Sokhna Port |  | 15
220321001
85
469
South Valley Inv. 15 | 15 | 15
IPC-9-PLAYA ROOF | 9 | 9
IPC-01-PK177.ANTI | 1 | 1
ORAZEHD PH.2 IPC8 | 8 | 8
K-MUHAMED JUL2022
IPC-Playa Epoxy
IPC-19-Playa | 19 | 19
IPC-10-PLAYA | 10 | 10
IPC-7-Borsa | 7 | 7
IPC-4-BORSA | 4 | 4
IPC-2-PK#177Anticarb | 2 | 2
IPC-05-BORSA | 5 | 5
10093
pkg#177 ipc22 | 22 | 22
PKG #178 IPC06 | 6 | 6
MARIOTYIA IPC17 | 17 | 17
R05 Zone2 IPC017 | 17 | 17
IPC02-MEGA | 2 | 2
inv ( 2 ) LINX | 2 | 2
IPC#17 -Sokhna Port |  | 17
PKG#163-IPC25 | 25 | 25
int&ret sup sscipc 8 | 8 | 8
Int&Ret APP(ssc)ipc6 | 6 | 6
200787
200686
200707
200631
ora zed 2 ipc 7 | 7 | 7
200708
200648
200764
el sewedy hq ipc13 | 13 | 13
Katameya CreeksIPC18 | 18 | 18
Eipico ipc11 | 11 | 11
Eipico ipc 10 | 10 | 10
IPC#8 Madkour |  | 8
02
sultana malk3 ipc01 | 1 | 1
INV ( 1 ) ALparco | 1 | 1
Elco egat ipc14 | 14 | 14
Elco Egat ipc15 | 15 | 15
Diplomatic ipc 13 | 13 | 13
IPC#3 HSR |  | 3
inv ( 2 ) CS-20 | 2 | 2
IPC005-MK4 WORLD-21 | 5 | 5
El Khataba ipc3+4 | 3 | 3
sokhna port ex ipc5 | 5 | 5
IPC#1 - ElHammam Pro |  | 1
port said silos ipc4 | 4 | 4
plant supp Ro puipc4 | 4 | 4
KafrShokr Brdg IPC06 | 6 | 6
port said silos ipc5 | 5 | 5
ipc 2 mahger | 2 | 2
IPC 2 ELMAHAGER | 2 | 2
Rolling mill ipc06 | 6 | 6
pkg#163- IPC28 | 28 | 28
IPC#4 - Wadi El Natr |  | 4
sorealhardscapeIPC10 | 10 | 10
IPC01EGATINJECTION | 1 | 1
EGAT - IPC17 | 17 | 17
200769
200727
IPC#2 NRCC |  | 2
200726
Katameya IPC21 | 21 | 21
200690
waldorf IPC10 | 10 | 10
INV ( 4:9 ) Hipper | 4 | 4
mansorafinshing ipc1 | 1 | 1
Sodic VillaF100 IPC1 | 1 | 1
Air def4 IPC2 | 2 | 2
Air def2 IPC3 | 3 | 3
IPC#4 HSR |  | 4
k-mustafa nov.2022
K-Salim Nov.2022
GOV 2 IPC09 | 9 | 9
ESC.1:17 (Estsmar)
MDF 2 - IPC 12 | 12 | 12
k-hassan Dec.2022
IPC1 PVD | 1 | 1
pkg#177- IPC36 | 36 | 36
200784
GOV2 IPC010 | 10 | 10
Katameya IPC 22 | 22 | 22
DIPLOMATIC IPC10 | 10 | 10
diplomatic ipc 14 | 14 | 14
kantine 7
IPC#11 Wadinatron |  | 11
Inv ( 4 ) T. Pushing | 4 | 4
Inv ( 2 ) T. Pushing | 2 | 2
IPC9 HSR6th | 9 | 9
seashell playa-IPC3 | 3 | 3
200804
INV ( 2 ) ALparco | 2 | 2
IPC#6 HSR |  | 6
INV ( 1 ) Al-Ula-2 | 1 | 1
PKG#163 IPC (29) | 29 | 29
Ora ph1 ipc 33 | 33 | 33
Ora ph1 ipc32 | 32 | 32
K-HASSAN3 MAR.2023
DP World ph.2 IPC2 | 2 | 2
EDECS - ipc1 | 1 | 1
T15-2022 | 2022 | 2022
24000010
october tunnel ipc 5 | 5 | 5
IPC2&3TR0061 | 2 | 2
PKG#177- IPC41 | 41 | 41
MDF Factory ipc (24) | 24 | 24
ORA PH.2 - IPC15 | 15 | 15
R.O. Sup. adj. IPC4 | 4 | 4
spx2 ipc 2 | 2 | 2
IPC 7 elswedy | 7 | 7
IPC no15 wadinatroun
200891
katamya creeks ipc32 | 32 | 32
Air Def finish IPC3 | 3 | 3
new geza Hosp ipc 14 | 14 | 14
200875
IPC#3 PVD Hamam |  | 3
inv.1 playa | 1 | 1
Katamya Creeks ipc34 | 34 | 34
IPC008 | 8 | 8
IPC0006 | 6 | 6
Carrefour H off ipc3 | 3 | 3
k-hassan may.2023
200954
IPC06TR0065 | 6 | 6
Minis Alloc IPc12 | 12 | 12
Waldrof Asto ipc 18 | 18 | 18
Mdf local ipc 14 | 14 | 14
EIPICO IPC (5) | 5 | 5
Playa c045 - ipc 1 | 1 | 1
200852
200853
port saidsilos ipc15 | 15 | 15
IPC0013 TR0046 | 13 | 13
Air Dev16 IPC4 | 4 | 4
Shutdown smp2 ipc(2) | 2 | 2
Shutdown smp1 -ipc 2 | 2 | 2
R05(2) ipc 35 | 35 | 35
11
IPC009 | 9 | 9
INV ( 7 ) GET | 7 | 7
mariotya ipc20 be16 | 20 | 20
Mohamed N villa ipc1 | 1 | 1
Air dev Shapcat IPC1 | 1 | 1
Cairo-alex ipc 34 | 34 | 34
Cairo Alex IPC010 | 10 | 10
Cairo-Alex IPC013 | 13 | 13
Inv ( 3 ) sixty | 3 | 3
Ora ph 2 ipc (20) | 20 | 20
ora landscape ipc 6 | 6 | 6
Air Finsh IPC4 | 4 | 4
portsaid silos ipc20 | 20 | 20
k-mustafa july.2023
po50723
IPC1 PLANTSUPPLY RO | 1 | 1
CementPriceEscaltion
Eipico Ipc ( 8) |  | 8
Air Def finish IPC2 | 2 | 2
Eipico ipc 17 | 17 | 17
Eipico ipc 13 | 13 | 13
inv ( 1 ) A.S | 1 | 1
TAH IPC04 | 4 | 4
sokhna port ipc 13 | 13 | 13
IPC#4 - Taamer PII |  | 4
IPC no16 D0073
Playa c038 ipc 7 | 7 | 7
200996
Rent 7+8/2023
TAH ipc03 | 3 | 3
I&R apply (ssc) ipc4 | 4 | 4
playa-c234 ipc (1) | 1 | 1
mansora ipc16 final | 16 | 16
74 kantine renet
IPC08 TR60 | 8 | 8
IPC08 TR64 | 8 | 8
Haramin ipc02 | 2 | 2
IPC 11 TR53 | 11 | 11
IPC04 TR59 | 4 | 4
IPC12&13TR0055 | 12 | 12
IPC1&2 TR0077 | 1 | 1
mahager bridge ipc4 | 4 | 4
IPC07TR0069 | 7 | 7
Inv ( 4 ) sixty | 4 | 4
GOV2 IPC 23 | 23 | 23
IPC02TR0062 | 2 | 2
I&R Supply SSC-IPC5 | 5 | 5
ora ph2 ipc (22) | 22 | 22
INV ( 9 & 10) GET | 9 | 9
IPC05TR0078 | 5 | 5
IPC04TR0077 | 4 | 4
Gawhara IPC6 | 6 | 6
MDF - IPC 13 | 13 | 13
MDF Factory ipc 31 | 31 | 31
Egat Ro2 ipc 1 | 1 | 1
mdf factory ipc 32 | 32 | 32
IPC018 TR46 | 18 | 18
IPC012TR0064 | 12 | 12
K-MUSTAFA NOV.23
Air Def Elic IPC1 | 1 | 1
IPC01- PO31115 | 1 | 1
IPC (4) / PO26195 | 4 | 4
inv ( 9 ) Captal one | 9 | 9
230000014
inv ( 2 ) MAHGER Br | 2 | 2
k-abdel w oct.23
inv ( 2 ) Baragill B | 2 | 2
port said silosipc13 | 13 | 13
TAH ipc 5 | 5 | 5
Mansora Finish ipc02 | 2 | 2
R05(2) ipc 27 | 27 | 27
mahager bridge ipc06 | 6 | 6
Emar Pkg#177 ipc 47 | 47 | 47
Lekela 2 ipc 1=3 | 1 | 1
INV (1 ) S.UNI | 1 | 1
astoria sharm-IPC5 | 5 | 5
New Gas ipc 3 | 3 | 3
New Gas sta ipc2 | 2 | 2
IPC10TR0064 | 10 | 10
Egyptian exch IPC4 | 4 | 4
Revamp ipc 7 | 7 | 7
INV 2 | 2 | 2
IPC06TR0066 | 6 | 6
IPC no5 luxor off
Ora Landscape ipc 11 | 11 | 11
el mahager ipc 07 | 7 | 7
IPC009 TR53 | 9 | 9
tr0059 IPC002 | 2 | 2
IPC02 TR68 | 2 | 2
IPC001 TR49 | 1 | 1
october tunnel ipc8 | 8 | 8
ORA ph.1 IPC19 | 19 | 19
IPC22TR0046 | 22 | 22
IPC05TR0061 | 5 | 5
Waldorf astori ipc24 | 24 | 24
inv 1.2 d0081 | 1 | 1
IPC#1#LEABA |  | 1
Egy Ex awnash IPC1 | 1 | 1
IPC07TR0071 | 7 | 7
HSR-OCT-5 | 5 | 5
HSR - OCT 3
201072
New Giza Hosp ipc 22 | 22 | 22
wady elnatron ipc8 | 8 | 8
k-hassan Feb.24
Mdf Factory ipc 35 | 35 | 35
IPC06TR0088 | 6 | 6
Inv ( 5 ) sixty | 5 | 5
Playa c234 - ipc 4 | 4 | 4
Rent-7TH maadi | 7 | 7
MDF Equip ipc 21 | 21 | 21
Sokhna ipc17+18+19 | 17 | 17
IPC01TR0088 | 1 | 1
24000008
ACUD Mar.24
201111
Inv ( 7 ) sixty | 7 | 7
Katameya creek ipc37 | 37 | 37
IPC14TR0048 | 14 | 14
Mohamed aly271 IPC1 | 1 | 1
middle east inv.3 | 3 | 3
Mini Fit out IPC5 | 5 | 5
201233
K0001-3 | 3 | 3
IPC07TR0059 | 7 | 7
Sultana malak22 IPC2 | 2 | 2
mansora finish ipc18 | 18 | 18
inv ( 4 ) Baragill B | 4 | 4
INV 3 | 3 | 3
R.o 500:800 sup ipc8 | 8 | 8
IPC03TR0088 | 3 | 3
Shutdown SMP2 IPC 3 | 3 | 3
SVC- ipc 1 | 1 | 1
IPC14TR0060 | 14 | 14
IPC01TR0096 | 1 | 1
R05(2) ipc 41 | 41 | 41
R05(2)IPC48 | 48 | 48
201273
IPC02TR0086 | 2 | 2
ora zed ipc 24 | 24 | 24
IPC#2 |  | 2
Egat Water tan ipc14 | 14 | 14
IPC6 PORT SAID | 6 | 6
MDF Factory ipc 38 | 38 | 38
10040
Pelletizing ipc 21 | 21 | 21
24000012
sokhna bri.esc19
IPC11TR0062 | 11 | 11
Qani bay IPC1 | 1 | 1
INV ( 7 ) ALparco | 7 | 7
IPC25TR0041 | 25 | 25
IPC21TR0055 | 21 | 21
Rent 6/2024
supply egp ipc6 | 6 | 6
ipc4 wady elnatroon | 4 | 4
El-Marg IPC08 | 8 | 8
El Mahager ipc08 | 8 | 8
EL KHATATBA IPC03 | 3 | 3
PORT SAID IPC26 | 26 | 26
IPC#1 Luxor offshore |  | 1
IPC#2-Luxor onshore |  | 2
Gawhara IPC5 | 5 | 5
U-rbnk ipc (4) | 4 | 4
INV no.9 | 9 | 9
122-canteen
201475
Gawhara IPC1 | 1 | 1
ora ph2 ipc 35+36 | 35 | 35
Ora Ph2 ipc 33+34 | 33 | 33
Air dev 27 IPC1 | 1 | 1
134-canteen
Inv ( 4 ) Sentor | 4 | 4
FPC - Taamer Axis
Rent 1st+2nd sep.24
port said ipc 31 | 31 | 31
port said supp.9
L7776/2022
MANSOURA FINISHIPC24 | 24 | 24
Shutdown smp1 ipc 3 | 3 | 3
WADY ELNATROON IPC10 | 10 | 10
IPC07TR0078 | 7 | 7
Rent 9-2024 | 2024 | 2024
IPC#5 - Taamer Axis |  | 5
ora ph2 ipc 25 | 25 | 25
Ora ph2 ipc 29 | 29 | 29
PORT SAID IPC 33 | 33 | 33
K0004 Inv-06 | 6 | 6
INV no.12 | 12 | 12
abou ghaleb ipc25+26 | 25 | 25
IPC05TR0081 | 5 | 5
Damietta PKG#3 IPC 2 | 2 | 2
october tunnel ipc9 | 9 | 9
IPC23TR0064 | 23 | 23
Haedescape ipc final
Eipico ipc 19 | 19 | 19
k-abdelwahab-11.24 | 11 | 11
IPC03TR0091 | 3 | 3
IPC22TR0053 | 22 | 22
IPC01TR0093 | 1 | 1
IPC#8 -Coastal Roa |  | 8
IPC#2 Gharably |  | 2
K-ABDELWAHAB-10-24 | 10 | 10
Tetra sales Nov.24
WADYELNATRON ESC1:8
wadyelntron13+14+15
201454
201297
Playa c185 - ipc 4 | 4 | 4
playa C469 IPC 9 | 9 | 9
IPC25MANSOURAFINISHN | 25 | 25
IPC#1#ElMahager |  | 1
IPC#5 - Moneeb |  | 5
GAWHARA IPC8 | 8 | 8
IPC12&13TR0088 | 12 | 12
Playa C470- ipc 8 | 8 | 8
inv (12 ) Captal one | 12 | 12
IPC#10 Monorail |  | 10
close62
Cr 20/12/2023
D0033-OB-Dec-2020/Cr | 2020 | 2020
Cr.Inv 12/2019 Scrap | 12 | 12
CR Mozambique
Inv.11 Sugar OHTL | 11 | 11
10209
Inv. 01 PO 8681 | 1 | 1
SH Deductions inv.29 | 29 | 29
D.M شحنة السكةالحديد
DEC ADJ 19
IPC#5# South Dabaa |  | 5
Credit memo inv 5 El | 5 | 5
17 EGP - West Domiat
CR 9
CR-5-Euro-South he | 5 | 5
OB-RE-Wall New Giza
CR-ipc1 elalamin | 1 | 1
Cr-Lahoon Sub Inv 02 | 2 | 2
تشيد بنبان
cancel inv. 30,31,33 | 30 | 30
opening bala.
Cr. Adj Inv 19 | 19 | 19
cr.soci 72
Re Soc Inv.3 Temmay | 3 | 3
CR 14
credit scrap lot. 4
41
249
cr 34- May-2020 | 2020 | 2020
70-Oct-2020 | 2020 | 2020
34/13/09/2021
OB-RE-Beni Suif
Close AR Balance.
inv ( 3 ) monoril | 3 | 3
10105
56-Agu-2020 | 2020 | 2020
6
180067
OP 6
14 closed
IPC#5#draw |  | 5
CR_INV.8 | 8 | 8
1127
CR-IPC#1 |  | 1
Cr. Inn 49 Ass
6
DEC ADJ 28
D0025-OB-Dec-2020/Cr | 2020 | 2020
7 Euro-South Helwan
D.M 13711
Rent-008 | 8 | 8
cr-wadi halfa ipc01 | 1 | 1
Cr. Al - Jazi Inv. 2 | 2 | 2
C r .INV ( 15 ) GET | 15 | 15
DEC ADJ 69
D.m Orange Invoic e
inv.5 cancl | 5 | 5
CR.Ret Asuit akh 4
cr-kafr shokr ipc09 | 9 | 9
DEC ADJ 83
INV ( 13 ) ALparco | 13 | 13
CR-Egytech-Cost
Acwa power ipc 3 | 3 | 3
OB.Retention
180083
cr-ipc14 sokhna port | 14 | 14
Suez S4 USD Inv. 05 | 5 | 5
P-06-EGY اتحاد تشيد | 6 | 6
rev.( 5 Euro-So. Hel
40
01/13/01/2022
CR-Inv#180161 | 180161 | 180161
DEC
Balance feb 17
59
Cr.Inv,11usd Borg Ar | 11 | 11
1073
14/13/09/2021
D.M Mar. -2020 | 2020 | 2020
10126
CR-MINI-IPC05+ | 5 | 5
13074
Inv 21/2019 Scrap | 21 | 21
Cancel invoice Lot 6
10424
inv(ESC-SA-Civil-08) | 8 | 8
cr15
Close AR Bal.
477
D.N Insurance JICA+
10636
DR. 13 Oewon Mousa
opening balance 2016
CR.Ret Qen-akh 5
cr-ايجار شهر 1 الى 6
DEC ADJ 80
Ret.. balance....
90
Cr. Egytec
11585
2
Edit inv 5 | 5 | 5
crINV ( 3 )ALparco | 3 | 3
61
cr 3
Cr. Socil 4-8:19 ass | 8 | 8
Cr Soc Inv 49 Asuit | 49 | 49
Khorafi IOM
MIDA Sply. Inv.4 Ret | 4 | 4
105
IPC#1#D0083 HST |  | 1
55-CR2F
اتحاد تشيدو بناءP-81 | 81 | 81
DEC ADJ 106
VAT Collection
close
P-29-EGY اتحاد تشيد | 29 | 29
10341
OB-ST-Ismailya B
11-07-2018 | 7 | 7
CR-4HY Bark | 4 | 4
DEC ADJ 26
2103210012
DEC ADJ 17
CN last Inv Cairo N
CR- 19 EGP- Shabab | 19 | 19
OB-Retention 2
Cr-Egy Ex IPC1 | 1 | 1
244
10/13/03/2022
Adj. ET balance
CR-IPC#1 |  | 1
DEC ADJ 15
10393
INV ( 22 ) GET | 22 | 22
Cr . Adj Inv. 15 | 15 | 15
248
IPC05TR0062 | 5 | 5
452
OB - 1 | 1 | 1
08/13/09/2021
ADJUST TAX OF INV.32 | 32 | 32
close 45
Inv.3&4 deductions- | 3 | 3
D0029-OB-Dec-2020/Cr | 2020 | 2020
CR.Ret Qen-akh 6
27/13/06/2021
Reduction inv no 210 | 210 | 210
Cr. Ref Retention Ma
10071
Cancel IPC11 TR46 | 11 | 11
C.M Orange
IPC#27/28 |  | 27
74
Scrap Inv. 14/2021 | 14 | 14
IPC NRCC 3
Cr.INV ( 5 ) Central | 5 | 5
82-Dec-2020. | 2020 | 2020
Deb.Adv. Tosh 4
IPC#011#RABAGH |  | 11
WHT + Stamp + SI
Cr
credit Ref. Inst
inv.5 cancle | 5 | 5
15
537
10205
Libya Eqpt. Inv.NO.1 |  | 1
11460
IPC#5#Wadi Elnatron |  | 5
TR55-CR1
10485
251
Re soc Inv 24. Quna | 24 | 24
Cr - 5 USD - West D. | 5 | 5
Deduc Stamps
5 USD - Shabab
cr-tetra-خرسانة-01 | 1 | 1
Libya Eqpt.1st Co.4
P-65-EGY تشيد و بناء | 65 | 65
21 EGP - Shabab
10189
Scrap Inv. 19/2020 | 19 | 19
10483
11521
Deduct Eng Stamp 50/
Inv. 31/2019Scrap | 31 | 31
Adjust billing
final sharm elshikh2
OB-MOS-PKG#22
inv ( 4 ) final CR | 4 | 4
31 EUR/Banha117
CR -15-West D. 117 | 15 | 15
CR PKG#37
D0006-OB-Dec-2020/Cr | 2020 | 2020
OB-ST-2-03-2017 | 2 | 2
CN Q3 Beni Suef
INV ( 24 ) GET | 24 | 24
Assuit Inv.2 ded- | 2 | 2
Cr Adj Inv 10 | 10 | 10
ghareb Final
DEC ADJ 90
P-42-EGY اتحاد تشيد | 42 | 42
2 Angola
inv ( 4 ) final CR2 | 4 | 4
MIDA Ins.Inv.2Ret. | 2 | 2
48
77
Elegict
P-33-EGY اتحاد تشيد | 33 | 33
CR ARMY/KYAN/1446
Mfinal kobry el3asma
CR 41-2020 | 2020 | 2020
Cr Adj inv 4 | 4 | 4
Ref.soci 54 Assuit
cr4
3 EGP - West Domiat
6 USD - Suez Gulf
Deduct 143,349.92 wd
Inv 6 $ Sugar S/s | 6 | 6
VAT deduction 13 civ
207
CRinv ( 13 )10-2020 | 13 | 13
33 closed`
Cr-Memo-Inv#19_EGP02 | 19 | 19
13 USD- Suez Gulf
Pole.Cvr.Inv.2.Cncl | 2 | 2
30/11/22 Armed force
FINALTR0039
close 68
7-2023 | 2023 | 2023
Attaqa Jun PV amorti
OB RT 009
CREDIT
DEC ADJ 86
MOC Inv 04 | 4 | 4
IPC26TR0046. | 26 | 26
IPC02TR0099(02) | 2 | 2
maf Po.0020024000370
Inv ( 1 ) S 05 | 1 | 1
IPC01TR0083 | 1 | 1
port said EUR ipc01 | 1 | 1
Inv ( 5 ) A.S | 5 | 5
IPC01TR0074 | 1 | 1
Waldorf Asto ipc(20) | 20 | 20
INV ( 2 ) S.UNIV | 2 | 2
ipc14 sokhna port ex | 14 | 14
Bis ipc (2) | 2 | 2
CAIRO-ALEX IPC40 | 40 | 40
inv ( 5 ) FINAL Ola | 5 | 5
TR55-IPC1 | 1 | 1
TR55-IPC2 | 2 | 2
TR55/IPC/03
TR55/IPC/02
wadi halfa ipc01 | 1 | 1
seashell playa- IPC1 | 1 | 1
Egy Ex IPC1 | 1 | 1
م 10 كفر شكر | 10 | 10
K.Hassan2 Nov.2022
minis MEP05+
11768
2112210003
220621002
T 4-2022 | 2022 | 2022
11560
11497
Selling Scrap Lot18
Selling Scrap Lot 6
11447
Inv. 11 Oewon Mousa | 11 | 11
220221001
Minist SHELL IPC08 | 8 | 8
2010210003
Toshka Sub Inv. 24 $ | 24 | 24
Kafr Shokr-IPC01 | 1 | 1
2012210038
2103210015
10080
GAMSA-FURNITURE
D0007-OB-Dec-2020 | 2020 | 2020
D0034-OB-Dec-2020 | 2020 | 2020
TR0020DEC.Closing
TR0019DEC.Closing
TR0015DEC.Closing
D0038-OB-Dec-2020 | 2020 | 2020
D0017-OB-Dec-2020 | 2020 | 2020
2012210030
2012210003
Al - Jazi Inv. 2 | 2 | 2
2009210008
2009210012
2004210003
scrap invoice
Close Adv balnce FX
Scrap Inv. 07/2020 | 7 | 7
Compensation Banha
485
Soc.2020 تشيد نجع
1,254,000.00
19 EGP - AL Shabab
Close El Niger
Closing PIP
Ret. Balance 2
opening ballance2016
Nubaria Siemens
remaining of 61 EGP
4 EGP united steel
11 EGP - Suez Gulf
1909210017
Scrap Inv. 32/2019 | 32 | 32
IPC#1 |  | 1
1907210016
1906210011
1909210011
1909210009
1909210008
SCD4/004Adj
2-19-feb | 19 | 19
Soc inv 4-5 Itay | 4 | 4
Inv.6 Phosfat | 6 | 6
1901210011
TETRA AMENDMENT-IPC1 | 1 | 1
P-27-09 AccRev | 27 | 27
Soc Inv 48 ASUIT | 48 | 48
1903210019
180151
Inv 8 Portsaid Final | 8 | 8
Ref.Install.1Assuit
180140
reverse.
8 USD- Shabab
7 USD- Shabab
18 EGP- West Domiat
180060
13 EGP- West Domiat
16 EGP- Shabab
180161
Inv, 5 usd Borg Arab | 5 | 5
Adj. iNV. 20 | 20 | 20
Adj. Inv. 19 | 19 | 19
Inv.68 Bank charges- | 68 | 68
180112
180127
30
81
180026
180022
180017
119
39
97
114
18
1
21
68
85
107
111
180057
49
Inv.9 Heliopolis | 9 | 9
Last Invoice Cairo N
Inv 81 P5 Sammound | 81 | 81
inv. 8 Assuit Akhmem | 8 | 8
inv. 6 Assuit Akhmem | 6 | 6
8 beni Suef - 1020 | 1020 | 1020
7 beni Suef - 1020 | 1020 | 1020
12
Inv 1 Abo Zaabel | 1 | 1
final sharm elshikh
VAT 2 PKG107
(17) pkg#53 |  | 17
43 civic center
12 s
36 EGP-Giza North 1&
12 EGP - Shabab 117
Transmission 1
DEC ADJ5
10038
2 EGP - Suez Gulf
1 USD/123/2011/2012
DEC ADJ 42
453 EGP abu qeir 118
1053
Moz inv.5 | 5 | 5
019/2019
010/2019
022/2020 FCV
6-132KVA-H | 132 | 132
8-132KVA | 132 | 132
(3)sodic blok4 |  | 3
(9) |  | 9
2002210017
525
180109
180102
180040
18 EGP - Shabab 117
11 EGP - West D. 117
180006
10 USD- West Domiat
9 USD - West D. 117
8 USD - West D. 117
4 USD - West D. 117
17 EGP Main Progress
180049
8 EGP - Suez Gulf
7 EGP - Suez Gulf
Refu,Adv.
Inv 65 P7 Assuit | 65 | 65
Inv.50 Banah 11 | 50 | 50
31 itay 9
Inv 49 P14El Natroun | 49 | 49
inv 42 P 8 Banha | 42 | 42
ًُwadi 10 inv41 | 41 | 41
Inv 21 Barwa | 21 | 21
Inv 18 Barwa | 18 | 18
Inv 31 Damac | 31 | 31
9 damac
Refund Retention
OB 3931
Adv. Balance 3
21
10+11+12
(14)sodic club |  | 14
(4)SD elmostsmrin |  | 4
Balance
433 EGP abu qeir 118
new acpital zabaal 2
inv 2 Eltbeen | 2 | 2
446 USD Avice ZTPC
1004
3321
26
4 BAnha
29 Bnha 4
15
Zona franka inv.17 F | 17 | 17
1052
8 ًWadi
Inv 12,13 SH | 12 | 12
Balance Adv Feb17
Adv. Balance 5
inv(ESC-SA-Civil-06) | 6 | 6
inv(ESC-SA-Civil-05) | 5 | 5
Adv. Balance
OB 3933
4 gheleon
29/P/10/ER/2016/USD
29 Euro - Giza N.12
(19)BINE SUIF2 |  | 19
(18) bine suif 2 |  | 18
10414
10212
1-Saurimo
TAM-CW-EGP-23 | 23 | 23
BSF-CW-EURO-08 | 8 | 8
TAM-SW-EGP-12 | 12 | 12
TAM-SW-EGP-11 | 11 | 11
BSF-CW-EURO-06 | 6 | 6
ISE-CW-EGP-10 | 10 | 10
ISE-CW-EGP-09 | 9 | 9
MOS-SD-EURO-11 | 11 | 11
30sd elmostsmrin
24sd elmostsmrin
16sd mosstasmreen
(6)SD EURO |  | 6
Gheleon 10
new capital zabal 1
10 USD- Shabab
inv 11 Ghalion | 11 | 11
DEC ADJ 41
180004
6 EUR Iskraemco
6 EUR - Iskraemco
remain(2 Euro-Iskrae
(26) sodic club |  | 26
Gheleon 19
Inv. 18 Gheleon | 18 | 18
19 new giza 2
NEW GIZA2 -IPC 27 | 27 | 27
18100054
(11) pkg#62 |  | 11
(9) pkg#107 |  | 9
31 Euro -Giza N.I&II
Banha-Zagazg Inv.03 | 3 | 3
Inv No 3 Bani swif | 3 | 3
Barwa 14
8 EGP - Shabab 117
10070
ANG-Cam-Inv 2 intrst | 2 | 2
(20)NEW GIZA 2 |  | 20
2alblagat
3 EGP - South Helwan
Asec Inv.29 | 29 | 29
Inv no 12 | 12 | 12
(4)156/52 H.A |  | 4
Inv No8 Wattanya220 | 8 | 8
Inv NO.3 KWT Flor | 3 | 3
Beni Swef Inv March
Payment No.5
(4) new giza wall |  | 4
ROYAL CITY-IPC24 | 24 | 24
Royal City -IPC14 | 14 | 14
ROYALCITY-IPC13 | 13 | 13
ROYALCITY-IPC-11 | 11 | 11
SHOBRE/BANHA-NILL FI
Inv.2 Zona 2 | 2 | 2
Inv,1 ZONA 2 | 1 | 1
matrial
Inv 48 P13 El Natrun | 48 | 48
Inv.52 Banah 12 | 52 | 52
Soci.Inv.54Assuit2 | 54 | 54
10
Ref. Ret Elgagalah
10026
5 EGP - Shabab 117
14 EGP - Shabab 117
DM- CSI
180133
180063
Inv Abu Quir
1 EGP - GPC Gupco
Apachi Inv No P.C#15 |  | 15
(13)SD EGP |  | 13
SD EURO (5) |  | 5
SD(10) mosstsmareen |  | 10
10017
32/P/10/ER/2017/USD
Inv. no 1 DZD VAT
Inv April Qatar
OB-RE-PKG#32
Iraq JV Inv 67 | 67 | 67
(8) PKG#107 |  | 8
10078
Inv. 28 Asec | 28 | 28
Soci.Inv.51wadi15 | 51 | 51
Inv.53 Wadi 16 | 53 | 53
Soc. 58 Wadi 17
ret40 itay 11
Inv.1 Almaza | 1 | 1
Inv No2 ElKean 220 | 2 | 2
22 USD - Banha 118
Inv No1 Itay | 1 | 1
Inv. 22 USD | 22 | 22
Inv No 2 Bani swif | 2 | 2
Inv.61 Wadi 18 | 61 | 61
1-132KVA-J | 132 | 132
Social inv.64/6 Assu | 64 | 64
Inv No2 Itay | 2 | 2
10187
10390
10389
(4) kayan |  | 4
1cw beni suif
17sd mosstasmreen
18 EGP-West Domiat
10701
Min.long lead Ipc3 | 3 | 3
Inv Abu Quir Oct
Inv.25 Assuit Akhmem | 25 | 25
Inv.18 Qena - Akhmem | 18 | 18
كانتين شهر 10
10188
OB-RE-GEO Grid
(23) pkg#53 |  | 23
(9)PKG#62 |  | 9
(5) كانتين يناير |  | 5
Inv 93P12Abo Matami | 93 | 93
Inv 91P11Abo Matamir | 91 | 91
aboelmatamir 9inv.87 | 87 | 87
aboelmatamir 7inv.83 | 83 | 83
Inv 76 P3 Sammound | 76 | 76
Inv. 6 Zona Franka | 6 | 6
Soc.Inv.60Banah14 | 60 | 60
Inv. 6 Mostakbal | 6 | 6
Damac
(25)bini suif 2 |  | 25
Inv. Barwa 34
Inv. Barwa 35
Petrofac Mobilisatio
Inv. 35 Damac | 35 | 35
Soc 73 Abo almat3
180080
180051
k(ahmed osman/sodic)
SODIC CLUB-IPC35 | 35 | 35
(27) sodic club |  | 27
180001
180011
4101505764/1&2
soc 74 abo elmatamer
Kanten-A.Osman-Sodic
31sd elmostsmrin
Adj Invoice.25 EUR
2002210003
1907210003
1903210001
2108210003
2007210001
2006210002
2005210003
492
12022
11843
180014
Inv No 15 Sokhna 111 | 15 | 15
Inv.67 Borg Alarab | 67 | 67
Inv.60 Borg Alarab | 60 | 60
Inv.51 Borg Alarab | 51 | 51
Inv.36 Borg Alarab | 36 | 36
Inv.30 Borg Alarab | 30 | 30
Inv.24 Borg Alarab | 24 | 24
Inv.15Usd borg alarb | 15 | 15
Inv.18Usd borg alarb | 18 | 18
Inv.8 Borg Alarab | 8 | 8
Inv.19Usd borg alarb | 19 | 19
Inv. 2 usd Borg Arab | 2 | 2
PO 57002361 CT Analy
PKG#117-IPC(5) | 5 | 5
k-m.mansour kayan110
Elkayan Inv. 11 | 11 | 11
IPC3-KAYAN LOAK&LOAD | 3 | 3
(5) ROYAL CITY |  | 5
(29) pkg#53 |  | 29
KAYAN LOCK&LOAD-IPC2 | 2 | 2
10577
214
Inv. 8 Project S 1 | 8 | 8
Inv. 5 Project S 1 | 5 | 5
soc 5-6-7-8 quna akh | 6 | 6
PKG#53-IPC(31) | 31 | 31
Mini Alocation IPC07 | 7 | 7
180074
OB-SI-GEO Grid
180050
57000228-57000229 | 57000229 | 57000229
M.B.Z-IPC (2) | 2 | 2
2 USD - Lina
PV Sep
10402
18100047
Inv.12 Qena- Akhmem$ | 12 | 12
soc 4 samanod
Inv. 3 Project S 1 | 3 | 3
soc 13 assuit siemen
Inv.11 Qena- Akhmem$ | 11 | 11
180125
IPC (34) - PKG#53 | 34 | 34
Kayan finishing-ipc5 | 5 | 5
ET por. paid by PSP
TAM-CW-IPC5 | 5 | 5
BSF-CW-IPC 8 | 8 | 8
Inv.14 Qena- Akhmem$ | 14 | 14
Inv.15 Qena- Akhmem$ | 15 | 15
Inv.13 Qena- Akhmem$ | 13 | 13
Inv.8 Assuit Akhmem$ | 8 | 8
SH Comm fees inv.29 | 29 | 29
180131
Inv.39 Akhmem Qena | 39 | 39
soc 7 samanod
K-M.KHALIFA-ELCO-SEP
els-uni-fin&mep-11 F | 11 | 11
10410
R5 ZONE 2- IPC05 | 5 | 5
Commercial fees SH/
South Helwan insuran
Clos.Adv.Algeria.Old
MIN-OLD-IPC04 | 4 | 4
PO - Mohamed Aly 113
MIN-LONGLEAD-IPC02 | 2 | 2
KAYAN FIER-IPC01 | 1 | 1
ALAWSATY L&L-1 FINAL | 1 | 1
Inv.12 Assuit Akhmem | 12 | 12
Ref.Instil No,1 Assu
10525
D/M.1 Borg Alarab
DM 3 Borg Alarb
DM 4 Borg Alarb
Soc.Inv.9 Samanood | 9 | 9
DM 9 Samanoud
Inv, 1 usd Borg Arab | 1 | 1
Inv.17Assuit Akhmem$ | 17 | 17
Inv.21 Qena- Akhmem$ | 21 | 21
OB RT 006
Inv.3 Rcc | 3 | 3
MOS-SD-EGP-IPC 33 | 33 | 33
Inv11 Usd borg alarb | 11 | 11
Inv. 2 Project S 1 | 2 | 2
Inv.25 Qena- Akhmem$ | 25 | 25
10003
Soc Inv 12 Abo Almat | 12 | 12
Inv.16 Qena- Akhmem$ | 16 | 16
Inv.5 Qena - Akhmem$ | 5 | 5
180170
TAM-CW-EGP-08 | 8 | 8
Inv.31 Assuit Akhmem | 31 | 31
ref Instill 3 Assuit
(4)cw elasmailya |  | 4
Inv.9 Usd borg alarb | 9 | 9
Inv12 Usd borg alarb | 12 | 12
CON 034
CON/031
LOC/022
CON/027
LOC/011
10207
10566
Inv. 2 Borg Alarab | 2 | 2
Inv. 1 Borg Alarab | 1 | 1
Sodic Soreal - IPC24 | 24 | 24
SOREAL-IPC21 | 21 | 21
SOREA-IPC18 | 18 | 18
Inv 92- P14 Assuit | 92 | 92
SOKHNA TUNNLE-IPC 2 | 2 | 2
SH Inv.37 ded&comm | 37 | 37
10490
MOS-SW-EGP- IPC 5 | 5 | 5
180138
Coll of scrap in PMI
PKG#101 -IPC09 | 9 | 9
K-A.M.Osman-ismalia
Inv. 6/2018 | 6 | 6
Inv 5 Asec Sparepart | 5 | 5
DP WORLD-IPC16 | 16 | 16
DP WORLD-IPC08 | 8 | 8
DP WORLD-IPC006 | 6 | 6
DP WORLD-IPC24 | 24 | 24
DP WORLD-IPC22 | 22 | 22
DP WORLD-IPC17 | 17 | 17
Inv.46 Qena Akhmem | 46 | 46
IPC#8 |  | 8
uni-fin&mep-ipc08 | 8 | 8
Inv.44 Assuit Akhmem | 44 | 44
Other Charge/J002
SCD3/002
39/P/10/ER/2017/USD
19100022
BSF-SD-EUR-03 | 3 | 3
K-H.mahmoud-gazimall
10370
19100021
PKG#140-IPC14 | 14 | 14
PKG#140 -IPC07 | 7 | 7
PKG#140 - IPC04 | 4 | 4
Inv 5 El Tbeen | 5 | 5
SCD4/0012
Inv 8 Zambia | 8 | 8
SCD1/003
BSF-SW-07 | 7 | 7
10 EGP - Metro
515
499
498
Inv.27 Assuit Akhmem | 27 | 27
Inv.20 Assuit Akhmem | 20 | 20
K-M.mansor-kayan-(3) | 3 | 3
K-H.Mansor-sew-uni-3 | 3 | 3
ABU SOULTAN2-IPC02FI | 2 | 2
1902210013
1902210010
10399
008/2019
218
SEWEDY UNI-FI&MEP-03 | 3 | 3
10578
10757
10573
Ref.Ret 2 assuit akh
225
Ref.Ret 4 Qena akh
IPC#11 |  | 11
IPC# 1&2 |  | 1
012/2019
inv. 3 USD. | 3 | 3
Inv 7/2019 Transmiss | 7 | 7
Inv.5 Assuit Akhmem$ | 5 | 5
1902210006
hyper eltemsah-IPC01 | 1 | 1
KAYAN RAWDA-IPC01 | 1 | 1
KAYAN LOAK&LOAD-IPC6 | 6 | 6
1902210009
PKG#53-VO-IPC02 | 2 | 2
sales-1 | 1 | 1
TAM-CW-EURO-06 | 6 | 6
ISE-CW-EGP-11 | 11 | 11
Benban Lot 2 Inv. 36 | 36 | 36
Benban Lot 1 Inv. 35 | 35 | 35
Benban Lot 1 Inv. 34 | 34 | 34
Benban Lot 1 Inv. 33 | 33 | 33
Benban Lot 1 Inv. 21 | 21 | 21
Benban Lot 1 Inv. 15 | 15 | 15
10533
1904210003
Fines-Royal-ismlia
Erection/J001
Inv. 12 Badr | 12 | 12
Inv. 9 Balat lot 3 | 9 | 9
Inv 9 Sugar S/s | 9 | 9
Inv.28 Borg Alarab | 28 | 28
1904210005
1905210002
K-Ministries-June-19 | 19 | 19
233
K-A.Osman-Ismlia-jun
E&W-Royalcity-June06
1904210009
Benban Lot2 Inv 13 $ | 13 | 13
Benban Lot2 Inv 10 $ | 10 | 10
10720
custom clearance
1905210003
1906210012
Eng stamp shipp 7/4
10104
IPC#21 |  | 21
10658
E&W-consumption-JULY
royal city- ipc20 | 20 | 20
Inv. 10 Balat Lot 2 | 10 | 10
10715
10702
PKG#117 - IPC10 | 10 | 10
Inv. 9 Balat Lot 2 | 9 | 9
1906210006
Inv.49 Assuit Akhmem | 49 | 49
Inv.50 Assuit Akhmem | 50 | 50
10130
10138
ٍSoc inv 9 Quana | 9 | 9
Inv.26 Akhmem Qena | 26 | 26
Inv.15 Qena - Akhmem | 15 | 15
Scrap inv 30/2019 | 30 | 30
Kanteen-Ministre-aug
1908210008
1907210011
1907210010
Inv16 Usd borg alarb | 16 | 16
Soc inv 4-5 Itay T | 4 | 4
249
217
10764
10790
inv ( 18 ) 5-12-2020 | 18 | 18
inv ( 16 ) 2-12-2020 | 16 | 16
516
515
509
500
495
10147
Benban Lot 2 Inv. 6 | 6 | 6
Benban Lot 1 Inv. 6 | 6 | 6
Inv.34 Borg Alarab | 34 | 34
Adj.180119-180120 | 180120 | 180120
10004
264
275
Naga Hmdy Inv.2 Equ | 2 | 2
Nagaa Hamady Inv.7 | 7 | 7
Nagaa Hamady Inv. 4 | 4 | 4
Nagaa Hamady Inv. 3 | 3 | 3
10-19-April | 19 | 19
18-19June | 19 | 19
Marsa Alam Equ Inv 2 | 2 | 2
Kanteen-Ministre-sep
Inv. 2 Sugar 33 OHTL | 2 | 2
Inv. 09 Farm | 9 | 9
(28) PKG#53 |  | 28
MINISTRIY OLD-IPC02 | 2 | 2
Inv. 02 Almaza | 2 | 2
1904210017
HYPER ONE-IPC04 | 4 | 4
1908210001
TAM-CW-EURO-09 | 9 | 9
MIN.FIT OUT- PC01
Ismailia U4-ipc 2 | 2 | 2
MIN-CORE- IPC02 | 2 | 2
10791
1908210018
10995
Inv 2 EUR Asec Spare | 2 | 2
MIDA Sply. Inv. 4 | 4 | 4
inv 5 Sup | 5 | 5
10308
11020
KAYAN FINSH-IPC07 | 7 | 7
Invoice No:12
2010210005
inv ( 9 ) | 9 | 9
inv ( 13 ) final | 13 | 13
Inv(4)240220 | 4 | 4
inv(7)150320 | 7 | 7
513
45-19 nov | 19 | 19
ORA-IPC01 | 1 | 1
11036
10249
295
266
Inv.40 Borg Alarab | 40 | 40
Inv.41 Borg Alarab | 41 | 41
Inv.43 Borg Alarab | 43 | 43
Benban Lot 1 Inv. 20 | 20 | 20
SOREAL-IPC07 | 7 | 7
VO-SODIC CULB-IPC01 | 1 | 1
Kanteen-Soreal-Nov19
Kanteen-Olmpic-Dec19
Kanteen-Kayan-Dec-19 | 19 | 19
65-19 Dec | 19 | 19
MIN SHELL-IPC04 | 4 | 4
SOUQ ELSAMEK ELCTROF
MIN.SHELL-IPC05 | 5 | 5
522
10930
10931
11075
512
1903210007
521
1904210010
Kanteen-Helton-Jan20
70-19 Dec | 19 | 19
Inv.23Assuit Akhmem$ | 23 | 23
Toshka Sub Inv. 08 | 8 | 8
Toshka Sub Inv. 07 | 7 | 7
Toshka Sub Inv. 04 | 4 | 4
FPC
MOS-VO-CLAIM
Inv.20Usd borg alarb | 20 | 20
Toshka Lot 4 Inv .18 | 18 | 18
Toshka Lot 4 Inv .4 | 4 | 4
Toshka Lot 6 Inv .7 | 7 | 7
Ref-Ret-Toshka Lot4$
Toshka Lot 6 Inv $1 | 1 | 1
Scrap Lot. 10
Lot. 05 - 1 | 1 | 1
CFC IPC023 | 23 | 23
Kanteen-ismlia-Jan20
Kanteen-Olympic-Jan-
541
11104
ROYAL CITY-IPC(7) | 7 | 7
ROYAL CITY-IPC25 | 25 | 25
ISE-CW-EGP-21 | 21 | 21
299
ISE-SD-EURO-03 | 3 | 3
Lot. 03
Lot 01 Caravan Sales
535
DP WORLD-IPC11 | 11 | 11
Inv.49 Qena Akhmem | 49 | 49
10388
Inv.06 Sugar OHTL | 6 | 6
LEKELA IPC014 | 14 | 14
LEKELA-IPC09 | 9 | 9
LEKELA-IPC07 | 7 | 7
11032
Toshka Sub Inv. 20 $ | 20 | 20
Toshka Sub Inv. 14 $ | 14 | 14
Toshka Sub Inv. 13 $ | 13 | 13
PKG#162 - IPC03 | 3 | 3
H.A-IPC003-PO181/148 | 3 | 3
2002210024
IKEA-IPC04 | 4 | 4
11087
303
IMP-031 | 31 | 31
23 Mar 20
10014
10016
10015
10021
10041
22 Mar 20
10003
TETRA-خرسانة-IPC01 | 1 | 1
TETRA-01/3 | 1 | 1
11073
pkg#163 ipc 21 | 21 | 21
11013
Marsa Alam Equ Inv 1 | 1 | 1
306
315
319
Scrap Sales
Inv.69 Borg Alarab | 69 | 69
11262
531
PKG#140- IPC10 | 10 | 10
2004210008
8-2024 | 2024 | 2024
3-2020 | 2020 | 2020
11182
Inv.73 Borg Alarab | 73 | 73
IKEA - IPC 05 | 5 | 5
2004210004
11341
Cr. Adv MILITARY Ext
Compensation Banha-
11323
200000
Tunnel Inv. 2 | 2 | 2
11546
15-2020 | 2020 | 2020
11744
10462
10223
E.S.U-PH2-IPC02 | 2 | 2
IPC_4_Mivida
Adjust receivable
adjust rec.180137
350
339
2006210008
mangrove rent-ipc04 | 4 | 4
2002210020
INV(10)300420 | 10 | 10
inv(10 )29720 | 10 | 10
2001210014
2002210028
2002210026
Toshka Lot 4 Inv .1 | 1 | 1
INV(1)Fainal12-2020 | 1 | 1
OB AR 001
345
53-19 nov | 19 | 19
Benban Lot1 Inv14USD | 14 | 14
KAYAN ROUDA-IPC02 | 2 | 2
Suez S4 Inv. 09 | 9 | 9
Suez S4 Inv. 05 | 5 | 5
East Owainat Inv. 04 | 4 | 4
11401
38-Jun-2020 | 2020 | 2020
45-Jun-2020 | 2020 | 2020
30-Mar20
ROYAL CITY- IPC32 | 32 | 32
Scrap Inv. 08/2020 | 8 | 8
10216
Eng-28 | 28 | 28
11444
IPC#1 |  | 1
200082
10233
27-2020 | 2020 | 2020
Ref.2 06/13/07/2019
11461
OB 3930
2004210007
Kanteen-Remaining
Kanteen-R05-June-20 | 20 | 20
29-2020 | 2020 | 2020
MANGROOVE-IPC07 | 7 | 7
11522
Inv.46 Borg Alarab | 46 | 46
10214
444
54-Agu-2020 | 2020 | 2020
Toshka Lot 4 Inv .10 | 10 | 10
40A/P/10/ER/2017/USD
11367
11293
11024
11023
10144
IPC_13_rowad_s_east
IPC_13_Rowad_poly
Inv. 22 Badr | 22 | 22
Toshka Lot 4 Inv $5 | 5 | 5
R05(2) ipc 36 | 36 | 36
IPC#3 |  | 3
IPC#3 |  | 3
INV(11)100520 | 11 | 11
inv(4)260120 | 4 | 4
Toshka Lot 6 Inv .6 | 6 | 6
E.S.U2-MEP-IPC08 | 8 | 8
Inv.2 Temmay Amded | 2 | 2
CFC-IPC10 | 10 | 10
Inv. 03 Future OHTL | 3 | 3
Ref Retention Matro$
IPC_9_Saray
IPC_6_gama_ministry
Kanteen-R05-Sep-2020 | 2020 | 2020
371
49-JUL-2020 | 2020 | 2020
inv ( 11 ) 11-11-20 | 11 | 11
64-Sep 2020
381
FPC
IMP051-50 | 50 | 50
Cairo-alex ipc 39 | 39 | 39
Cairo-Alex ipc 31 | 31 | 31
CAIRO-ALEX IPC20 | 20 | 20
43-2020 | 2020 | 2020
11540
11450
11289
10243
11882
inv ( 10 ) 20-10-20 | 10 | 10
PKG#163 - IPC04 | 4 | 4
Ora ph1 ipc 31 | 31 | 31
ORA ph1 ipc (29) | 29 | 29
ORA ZED IPC12 | 12 | 12
R5 FINSHING-IPC05** | 5 | 5
Toshka Sub Inv. 04 $ | 4 | 4
Toshka Sub Inv. 08 $ | 8 | 8
Close of Scrap Sales
Car Sales 239
2009210011
2007210011
2007210010
Ref. Reten Marsa Alm
MIN.ANASER WATER-03 | 3 | 3
IPC_17_Rowad_S_east
2008210009
Toshka Sub Inv. 02 | 2 | 2
ROYAL CITY-IPC33 | 33 | 33
kamtin
2007210004
R05
5
PKG#140-IPC18 | 18 | 18
Toshka Sub Inv. 18 $ | 18 | 18
11763
IPC-7 | 7 | 7
inv ( 15 ) 12-2020 | 15 | 15
388
M.A.FAHMYL&L-FINAL
IMP-059 | 59 | 59
El-Nayba Inv. 2 | 2 | 2
inv ( 15 )25-12-2020 | 15 | 15
IPC_3_Rowad_M.Ali
MOSTQBALL&L-IPC02F | 2 | 2
Ref-Ret Ghana12/2020
Toshka Lot 6 Inv $4 | 4 | 4
Toshka Lot 4 Inv $6 | 6 | 6
IPC#9 |  | 9
11
KATAMYA CREEKS IPC14 | 14 | 14
Kattameya IPC04 | 4 | 4
2-2021 | 2021 | 2021
Toshka Lot4OH Inv.10 | 10 | 10
Inv.03 $ Sugar OHTL | 3 | 3
ROYAL CITY-IPC36 | 36 | 36
IPC#3 PhaseII |  | 3
IPC#2 |  | 2
PKG#140-IPC16 | 16 | 16
IPC#1 Ahl Misr |  | 1
CFC-IPC14 | 14 | 14
2011210007
Adj.06-2022 | 2022 | 2022
9
Olympic - 2 | 2 | 2
PKG #178 IPC05 | 5 | 5
5MIDA Sply. Inv.
Inv.9Project S1Fina | 9 | 9
Inv 5 $ Sugar S/s | 5 | 5
MANGROVE WALL-IPC03 | 3 | 3
inv ( 21 ) 11-12-20 | 21 | 21
11722
Toshka Sub 4 Inv.3 $ | 3 | 3
EGAT IPC07+ | 7 | 7
11866
IPC_4_Rowad_M.Ali
13-2021 | 2021 | 2021
ISE-SW-EGP-09 | 9 | 9
BSF-SD-EURO-03 | 3 | 3
IKEA - IPC06 | 6 | 6
395
IPC_22_Rowad_Seast
2
FPC
Deb.adv.Tosh OHTL4
CCre.adv. $ Toshka 4
FPC
PKG#162-IPC11 | 11 | 11
12
Ministries - 3 | 3 | 3
R05 - 3 | 3 | 3
Suez S4 Equ Inv. +1
LOC-013 | 13 | 13
Suez S4 USD Inv. 03 | 3 | 3
MIN.SAHY&N-IPC02 | 2 | 2
South Valley Inv. 14 | 14 | 14
South Valley Inv. 05 | 5 | 5
11869
11802
R5PHASE2-IPC09 | 9 | 9
12-2021 | 2021 | 2021
MDF FACTORY IPC11 | 11 | 11
12066
IPC_23_SodicEast
2103210016
10527
inv(8)100620 | 8 | 8
inv(17)28-2-21-R5 | 17 | 17
inv ( 16 ) R511-2-21 | 16 | 16
Inv(4)300620 | 4 | 4
Inv(2)150420 | 2 | 2
RING MARYITIA-IPC05 | 5 | 5
12122
E.S.U2-ARC&MEP-IPC12 | 12 | 12
PKG #177 IPC011 | 11 | 11
PKG #177 IPC05 | 5 | 5
PKG#163-IPC10 | 10 | 10
12202
46
Kattameya IPC05 | 5 | 5
Katameya - IPC03 | 3 | 3
Ref-soci51-52 Assuit | 52 | 52
Sodic Soreal IPC026 | 26 | 26
ORA ZED PH.1 IPC07 | 7 | 7
Kanten-May21 GOV2
Kanteen-May 2021
Ref Retention fosfat
Inv.9 - Lot 1 | 9 | 9
Inv.8 - Lot 1 | 8 | 8
506
DM-ADV-COMOROS
Mangrove - IPC015 | 15 | 15
12302
200246
200203
200189
200181
200180
200163
Diplo. Dist. IPC08 | 8 | 8
CollectionR05-010621 | 10621 | 10621
10322
Air Force Inv . 14 | 14 | 14
Air Force Inv . 13 | 13 | 13
Air Force Inv . 09 | 9 | 9
Air Force Inv . 02 | 2 | 2
mansora uni ipc 15 | 15 | 15
R5-ZONE1-IPC6 | 6 | 6
inv. 19-20 USD | 19 | 19
R5-ZONE 02- IPC02 | 2 | 2
R5 - IPC17 | 17 | 17
GOV2 ipc25 | 25 | 25
Reailway PSP Inv. 04 | 4 | 4
10602
Hosh Essa Inv. 1 Equ | 1 | 1
Toshka Sub Inv. 10 $ | 10 | 10
413
Inv. +12 Farm
Olympic Hall Jun2021
Kanten-Sodic-Jun21
PKG #177 IPC014 | 14 | 14
PKG #101 IPC021.C | 21 | 21
EGAT IPC02 | 2 | 2
10603
10624
IPC-13-Playa | 13 | 13
IPC#2 - Marassi#178 |  | 2
12691
12649
12628
12383
EGAT-IPC16 | 16 | 16
LRT 10Ramadan Inv.01 | 1 | 1
IPC_1_R5_RME
IMP/064
2009210016
2009210015
ora zed ipc15 | 15 | 15
ORA PH2 IPC 19 | 19 | 19
Mansoura UNI IPC03 | 3 | 3
R05 Zone1 IPC031 | 31 | 31
IPC_4_LRT |  | 4
10159
22-2021 | 2021 | 2021
Diplo Dist IPC03 | 3 | 3
IPC001 Kilo 21 | 1 | 1
IPC002-OVM-2021 | 2 | 2
Maryotia IPC09 | 9 | 9
Kanten Minist Sep 21
Kantn OlmpicHal 9/21
South Valley Inv. 08 | 8 | 8
Ref.Ret marsa Alam
Mostakbal-8 Inv.03 | 3 | 3
Collection R05-09/21 | 9 | 9
ELSEWEDY HQ IPC05 | 5 | 5
IPC03 - Mansoura | 3 | 3
Sodic Soreal IPC031 | 31 | 31
IPC05RENT-MANGROVY | 5 | 5
PKG #177 IPC017 | 17 | 17
12563
IPC#6 Sokhna Port |  | 6
IPC#2 - Sokhna Port |  | 2
2108210010
Maryotia IPC010 | 10 | 10
424
ENG/047
2108210008
10823
BSF-SD-EGP-03 | 3 | 3
ENR-Sign Inst Inv02 | 2 | 2
Kanten OCT/21 R05 2
Kanten OCT/21 GOV2
33-2021 | 2021 | 2021
10883
10882
10944
200288
Invoice 12/2021 | 12 | 12
28-2021 | 2021 | 2021
Wat Pump Obour Inv.1 | 1 | 1
386
415
Olymipc Hall IPC06 | 6 | 6
IPC#3 - Ain Sokhna P |  | 3
Air Force Inv . 17 | 17 | 17
10966
430
44
42
IPC#1 |  | 1
12442
10000
Ret Qen-akh 8 T
Cr.adv. Kfr Naser
ENR-Sign Inst Inv03 | 3 | 3
Kanteen DEC21 Sodic
Kanteen DEC21 Creeks
2112210001
Diplo Dist IPC07 | 7 | 7
Ref.1 benban Lot 1 T
11027
12613
12566
MDF IPC06 | 6 | 6
11042
10307
IPC003-BENINCA-2021 | 3 | 3
12283
75
Ref. Capital S 1 T
11083
2112210008
Inv.15 – Lot 2 | 15 | 15
new giza Hos ipc 25 | 25 | 25
ipc13 New giza HOS | 13 | 13
new giza - ipc 11 | 11 | 11
INV ( 1 ) Fianl | 1 | 1
12910
Rolling mill IPC13 | 13 | 13
ipc14 Egad lock&load | 14 | 14
EGAT L&L - IPC 13 | 13 | 13
EGAT L&L-IPC 10+ | 10 | 10
EGAT L&L IPC 05 | 5 | 5
EGAT L&L IPC03 | 3 | 3
EGAT L&L ipc 01 | 1 | 1
alfa lab ipc1(final) | 1 | 1
2112210007
ELTEMSAH MEP-IPC01 | 1 | 1
IPC1 Supply Sokhna B | 1 | 1
200610
CAIRO-ALEX-IPC02 | 2 | 2
IPC-18-SARAY | 18 | 18
12748
448
Port Said Silos ipc1 | 1 | 1
PORTSAID IPCSUPPLY11
49
MIDA Sply. Inv.9 | 9 | 9
MIDA Ins. Inv.9 | 9 | 9
k-katamya feb2022
k-air defence-feb22
43
10563
440
439
431
ora zed ph2 ipc03 | 3 | 3
ORA ZED 2 IPC04 | 4 | 4
Scrap Lot No:18
Selling Scrap 6
Ret Asuit akh USD T
ENG/051
220221002
11365
IPC-14-PLAYA | 14 | 14
200548
newgizahospital ipc2 | 2 | 2
11404
11383
462
Port said OHTL Inv.2 | 2 | 2
12648
453
Wat Pump Obour Inv.4 | 4 | 4
Suez S4 Inv. 10 | 10 | 10
تعويضات الاسماعلية
ENG/053
MDF-ipc 21 | 21 | 21
k-mustafa-apr22
IPC-15-PLAYA | 15 | 15
11503
ora zed2 ipc5 | 5 | 5
200525
Suez S4 Inv. 14 | 14 | 14
Wat Pump Obour Inv.3 | 3 | 3
East Owainat Inv. 07 | 7 | 7
PKG#177 IPC31 | 31 | 31
Emaar Pkg#189 ipc 26 | 26 | 26
pkg#189 ipc 25 | 25 | 25
Emaar PKG#189 IPC12 | 12 | 12
IMP/068
11539
MIDA Sply.inv.13 | 13 | 13
ANG-Cam-Inv 7 - Int. | 7 | 7
ELCO EGAT IPC03 | 3 | 3
CFC IPC 28 | 28 | 28
MIDA Ins.inv.13 | 13 | 13
Sadat Indust Inv. 06 | 6 | 6
EL KHATATBA ipc01 | 1 | 1
MANSOURAFINSH IPC 26 | 26 | 26
Mansora finish ipc21 | 21 | 21
mansora finish ipc07 | 7 | 7
mansora finish ipc03 | 3 | 3
200650
200612
inv ( 10 ) montazha | 10 | 10
Inv.16 - Lot 2 | 16 | 16
م 1 سوق السمك صحى/حر | 1 | 1
R05 Zone2 IPC018 | 18 | 18
R05 Finishing IPC014 | 14 | 14
sodichardescape ipc1 | 1 | 1
EDNC hardscape IPC05 | 5 | 5
11660
PKG#177-IPC39 | 39 | 39
Port Said Silos ipc3 | 3 | 3
Astoria sharm IPC3 | 3 | 3
T 6-2022 | 2022 | 2022
CON/033
MIDA SPLY.7
Diplomatic ipc09 | 9 | 9
Ref-Ret-Toshka Lot6$
kyan L&L final
K-HASSAN MAY2022
Wat Pump Obour Inv.6 | 6 | 6
PKG#205 IPC03 | 3 | 3
461
INV ( 6-9 ) HY Bark | 6 | 6
INV ( 5 ) HY Bark | 5 | 5
200604
200628
Inv.01 Po 24/21 | 1 | 1
Benban Lot 2 Inv. 35 | 35 | 35
11683
IPC#1 - HSR |  | 1
220621009
MDF - IPC 20 | 20 | 20
Sadat City Inv. 01 | 1 | 1
Compensation B & D 3
IPC-17-PLAYA | 17 | 17
IPC#8 Monorail |  | 8
220721003
East Owainat Inv.3 V | 3 | 3
IPC#1 - Tiger |  | 1
SODIC HARD IPC02 | 2 | 2
IPC-2-PLAYA | 2 | 2
IPC-2-PKG#177 Water | 2 | 2
IPC_18_Rowad_Seast
pkg#177 ipc 24 | 24 | 24
IPC#2 HSR |  | 2
15 EGP- West Domiat
220721004
MANSOURA IPC12 | 12 | 12
sewedy HQ IPC17 | 17 | 17
Waldorf Astoria IPC3 | 3 | 3
IPC#3 GSCC Port |  | 3
Inv ( Final ) Linx
11703
In&ReSupply(ssc)IPC3 | 3 | 3
int&ret supAbb ipc8 | 8 | 8
In&ReApply(ABB)IPC2 | 2 | 2
in&re.app abb ipc 3 | 3 | 3
200624
waldorf - IPC16 | 16 | 16
Waldorf- IPC 15 | 15 | 15
TR0046-IPC002 | 2 | 2
200684
ipc17woldoef astoria | 17 | 17
Eipico 3 ipc 12 | 12 | 12
ora ph.2 ipc9 | 9 | 9
k-hassan aug2022
inv ( 11 ) montazha | 11 | 11
Soreal HardscapeIPC7 | 7 | 7
IPC#1 Taamer PII |  | 1
inv ( 3 ) CS-20 | 3 | 3
PKG#189 IPC3 | 3 | 3
230000006
R05(2) ipc26 | 26 | 26
PKG#162-IPC13 | 13 | 13
SOKHNA BRIDGE 8+9+10
sorealhardscape IPC8 | 8 | 8
INV ( FINAL ) USA S
INV ( 1 ) USA S | 1 | 1
PKG#189- IPC6 | 6 | 6
Ari Dev3 IPC2 | 2 | 2
IPC9 WADI | 9 | 9
scrap 200730
mariotya ipc 18 | 18 | 18
elsokhna ipc5+6+7 | 5 | 5
200666
INV ( 21 ) GET | 21 | 21
IPC22-AIN SOKHNA | 22 | 22
K-MUSTAFA DEC.2022
Revamp- IPC 6 | 6 | 6
Revamp ipc(2) | 2 | 2
kafr shokr ipc 10 | 10 | 10
k-hassan Jan.2023
Min Core ipc 11 | 11 | 11
Egy Ex ipc 01 | 1 | 1
sokhna port ex ipc09 | 9 | 9
R.o(50:80) supp ipc7 | 7 | 7
ro(5000:800)app ipc3 | 3 | 3
IPC00004 | 4 | 4
Olympic finsh IPC2 | 2 | 2
IPC0000017 | 17 | 17
port said silosipc10 | 10 | 10
200807
200785
october tunnel ipc2 | 2 | 2
Carrefour H Off ipc4 | 4 | 4
Kayan fin Ipc fin
IPC000001 | 1 | 1
Eg Exchge IPC2 | 2 | 2
k-hassan2 mar.2023
IPC006 | 6 | 6
R.O. - SUPPLY IPC 1 | 1 | 1
Dp world IPC10 | 10 | 10
k-ahmed april.2023
inv ( 1 ) monoril | 1 | 1
IPC 1 head office | 1 | 1
spx.2 ipc 03 | 3 | 3
carrefour H off ipc2 | 2 | 2
port said inv.1-supp | 1 | 1
IPC#13 WADI |  | 13
playa -c185 ipc 3 | 3 | 3
Playa - C185 ipc 2 | 2 | 2
IPC004 | 4 | 4
FPC - Tamer Axis PII
sahilil IPC final
Eipico ipc 4 | 4 | 4
k-salim may.2023
IPC#11 Monorail |  | 11
IPC#3 HSR ARAB |  | 3
200872
k-salim-mar22
IPC09 TR55 | 9 | 9
IPC005 TR55 | 5 | 5
200856
PLAYA c045 - ipc 2 | 2 | 2
playa c038- ipc 1 | 1 | 1
IPC004 TR60 | 4 | 4
IPC002 TR64 | 2 | 2
IPC005 TR60 | 5 | 5
IPC00027TR38 | 27 | 27
wady halfa esc.2
wadi halfa ipc 03 | 3 | 3
IPC003 TR59 | 3 | 3
mariotya ipc19 | 19 | 19
007-2022 | 2022 | 2022
INV ( 3 ) S.UNIV | 3 | 3
ipc 3 wady elnatroon | 3 | 3
ORA PH.1 - IPC 21 | 21 | 21
Rolling Mill- IPC12 | 12 | 12
Ora landscape ipc 7 | 7 | 7
Olympic Finsh3 IPC1 | 1 | 1
pkg#163- Inv. 27 | 27 | 27
CR INV ( 09 ) KEMET | 9 | 9
TAH ipc09 | 9 | 9
200972
Rent invoice 1:6 | 1 | 1
ora ph2 ipc (21) | 21 | 21
i&R apply (ssc)ipc 1 | 1 | 1
intake&return S ipc4 | 4 | 4
playa-c038ipc(5) | 5 | 5
IPC08TR0069 | 8 | 8
IPC04TR0081 | 4 | 4
Rent 1st+2nd maadi
Rent2 1st+2nd maadi
200995
URBN-K IPC (5) | 5 | 5
In.&Re. Sup.SSC-IPC6 | 6 | 6
R.O. Supply- IPC 6 | 6 | 6
MOHAMED ALY2 IPC03 | 3 | 3
MohamedAly 2 - IPC01 | 1 | 1
Ora Landscape ipc 9 | 9 | 9
Admin Building ipc 1 | 1 | 1
23i1650
portsaid 2-supp.EGP
INV ( 5 ) ALparco | 5 | 5
IPC01/PO-30777 | 1 | 1
IPC 02- BALATAT | 2 | 2
24000004
Air dev Finish3 IPC3 | 3 | 3
Inv ( 2 ) A.S | 2 | 2
201033
woldorf astori ipc23 | 23 | 23
revamp(smp1)ipc1 | 1 | 1
IPC02TR0083 | 2 | 2
Emaar pkg#189ipc17 | 17 | 17
IPC16TR0055 | 16 | 16
ELTAMSAH-كهرو MEP-01 | 1 | 1
Mohamed Aly IPC05 | 5 | 5
Ora Landscape ipc 4 | 4 | 4
201057
k-hassan Dec.23
sales dec.23
Air Dev Elec IPC1 | 1 | 1
R5 (2) ipc34 | 34 | 34
ipc 1 south dabaa | 1 | 1
IPC final elwaraq
PKG#163 IPC (30) | 30 | 30
201058
201056
int&ret sup ssc ipc7 | 7 | 7
int&ret sup abb ipc7 | 7 | 7
Mariotya ipc24 zomor | 24 | 24
Mariotya ipc 24 | 24 | 24
IPC02 TR66 | 2 | 2
IPC 2 TR71 | 2 | 2
ipc006 TR66 | 6 | 6
IPC04TR0066 | 4 | 4
Woldorf Asto ipc 21 | 21 | 21
october tunnelipc3+4 | 3 | 3
october tunnel ipc7 | 7 | 7
PKG#220- IPC3 | 3 | 3
Hussein Mos IPC1 | 1 | 1
Rent 2/2024
201091
IPC05TR0088 | 5 | 5
Inv ( 1 ) S07 | 1 | 1
Olym Finish IPC1 | 1 | 1
Playa C045- IPC 9 | 9 | 9
Air Dev Elic IPC1 | 1 | 1
sokhna esc.14+15
Gawhara IPC3 | 3 | 3
k-Abdelwahab apr.24
Rent 4/2024
201191
PO 3100076938
2-2024 | 2024 | 2024
100-canteen
201113
sokhna esc.14+15 (2) |  | 2
IPC02TR0088 | 2 | 2
201234
Gawhar LALA IPC1 | 1 | 1
Inv ( 6 ) sixty | 6 | 6
Ora ph2 ipc 28 | 28 | 28
IPC02TR0079 | 2 | 2
Mansora finish ipc19 | 19 | 19
IPC04TR0074 | 4 | 4
IPC15TR0060 | 15 | 15
IPC05TR0069 | 5 | 5
201251
New Giza Hosp ipc 26 | 26 | 26
201236
Egat Mechnical ipc 6 | 6 | 6
esc.spx1 11+12
IPC17TR0064 | 17 | 17
port said silo ipc24 | 24 | 24
RENT-006 | 6 | 6
MDF Equip ipc 24 | 24 | 24
Ora Landscap ipc 16 | 16 | 16
R-7th floor madi6-24 | 7 | 7
IPC16TR0060 | 16 | 16
IPC15TR0039 | 15 | 15
IPC15TR0048 | 15 | 15
IPC10TR0068 | 10 | 10
Jawhara IPC4 | 4 | 4
Aboghaleb Esc.1:20 p
ABOGHALEBIPC19+20 | 19 | 19
olympic mic IPC1 | 1 | 1
In&Re apply ssc ipc7 | 7 | 7
Ora ph2 ipc 32 | 32 | 32
V.O SMP1 IPC 1 | 1 | 1
Emaar Pkg#189 ipc 27 | 27 | 27
PORT SAID IPC 30 | 30 | 30
IPC01TR0100 | 1 | 1
IPC#001 |  | 1
IPC08TR0068 | 8 | 8
IPC06TR0068 | 6 | 6
201392
IPC06TR0069 | 6 | 6
Ednc Saudi ipc 2 | 2 | 2
IPC09TR0059 | 9 | 9
IPC06TR0079 | 6 | 6
IPC03TR0084 | 3 | 3
INV (11-12 ) ALparco | 11 | 11
Exch EGY BIM1
Ora ph1 ipc 43 | 43 | 43
IPC09TR0084 | 9 | 9
IPC13TR0068 | 13 | 13
IPC17TR0039 | 17 | 17
IPC16TR0048 | 16 | 16
IPC18TR0053 | 18 | 18
IPC02TR0099(01) | 2 | 2
Abo Ghaleb ipc 24 | 24 | 24
El Marg Esc.1:11 fin
Urbn-k ipc 6 | 6 | 6
INV no.11 | 11 | 11
Rent 10-24 | 24 | 24
Playa c469 ipc 7 | 7 | 7
IPC#06 Moneeb |  | 6
Eipico ipc 20 | 20 | 20
ipc 9 D0051 | 9 | 9
IPC#2 Ahl Misr Zamal |  | 2
IPC#2 ElHammam |  | 2
201492
MDF-Local ipc 20 | 20 | 20
QASR RASHWAN A IPC 2 | 2 | 2
IPC#12 Monorail |  | 12
HSR SOHAG IPC 1 | 1 | 1
17 EGP- West Domiat
240
RME-OC Po 649
final*closed
IPC_3_Rowad_Kayan
Adjust 1907210013
1
DEC ADJ 93
2105210019
10284
Cr. Inv. Retent. USD
Balance 2016 10
Cr Soc inv 4-5 Itay | 4 | 4
cr 58-Aug-2020 | 2020 | 2020
inv 3 kwt flr cancle | 3 | 3
Green Power EGP
CR 5
D.M Orange Invoice--
Close AR Balance
cr17+18+19
1--fin
close 73
83-Dec-2020 | 2020 | 2020
03/13/05/2021
Cr.Social
32 closed adj
Soc.2020 تشيد سكر مح
28-C028
ADJ RECEPR
Inv.35&36 deductions | 35 | 35
02/13/05/2021
IPC27TR0046// | 27 | 27
CR_inv.7 | 7 | 7
75-Nov-2020 | 2020 | 2020
11-19-April | 19 | 19
DEC ADJ 9
inv 1.2 d0080 | 1 | 1
21/13/03/2022
CR inv ( 9 ) Kemt | 9 | 9
CR_INV. 9 | 9 | 9
CR.Inv 44 to 47 | 44 | 44
Inv.16 - Lot 1 Rduc. | 16 | 16
MIDA Sply.Inv.5 Ret | 5 | 5
D.N Insurance JICA-
D.M Orange Invoice-
OB-SI-PKG#32
Sadat City Inv. 02 | 2 | 2
31/13/09/2021
024/2020adj
ded custom inv 23-24 | 23 | 23
cr-sewedy uni-mep-07 | 7 | 7
Scrap Inv. 17/2020 | 17 | 17
Close AR Balances
close31
Air Def Fini5 IPC1 | 1 | 1
245
ref.2
STF Credit memo
CR-PKG#17
tetra cr2
Transmission 1.
تشيد وبناء بنبان ل 2
Adj.Hitachi diff bal
33/13/09/2021
63
27
CM Ghana25
1070
CR_INV.6 | 6 | 6
1102
crIPC12_sodic_east | 12 | 12
cr-k-youssef feb.23
CR Ora LandscapeIPC2 | 2 | 2
Cr Royal Zone ipc24 | 24 | 24
CR-(10+11) USD-Shaba | 10 | 10
1125
DM 13167 Holding
Cancellation
10201
OB-SI-Ezz Factory
reverse
DEC ADJ
62 closed
OB.Ret. Cobra500
9-2024 | 2024 | 2024
cr 80-Dec-2020 | 2020 | 2020
CR_inv.11 | 11 | 11
11586
Credit Lot. 19
crk-salim nov.2022
Ret. Balance.
IPC 4 Aswan | 4 | 4
DEC ADJ 59
MIDA Ins. Inv.4 Ret | 4 | 4
tetra-cr03
Cr, Inv.13 sam socia | 13 | 13
Suez S4 USD Inv. 07 | 7 | 7
Cr. 1 Sett. West
10505
OB-SI PKG#58
Balance 2016 11
Cancel Inv: 13 Nueab | 13 | 13
52
239
Cr 19
07/13/12/21
6
D0046 OB-Dec-2020/Cr | 2020 | 2020
Close inv.180135 | 180135 | 180135
220621010
cr6
Inv. 30 EUR/Banha117 | 30 | 30
D0028-OB-Dec-2020Can | 2020 | 2020
Manshit Nasser
CR-IPC#1 |  | 1
cr-mariotya ipc16 z | 16 | 16
cr-Inv-01 MOC | 1 | 1
DEC ADJ 77
1069
close billing reclas
Reten.OB Zafrasouf
01/13/05/2021
Cr. Ref Retention B$
CN Cairo South
13 EGP - West Domiat
180065
تشيد النقره
Libya Eqpt.1+2 Co.3
Material EES7
Rent 002
9 EGP - Shabab
OB RT 008
IPC03TR0094 | 3 | 3
10063
close 56
CR2-19-feb | 19 | 19
74-nov-2020 | 2020 | 2020
283
61
12952
110
Inv.20 - Lot 1 | 20 | 20
Ref 2
close 23
cr30 - Apr 20
Inv.1 Temmay Cancel | 1 | 1
10221
wht & stam -mainshie
Scrap Inv. 21/2020 | 21 | 21
VAT receipts / 39-40 | 40 | 40
scrap invoice.
last inv. (4 EGP)113
8 closed
Addition Work IPC07 | 7 | 7
cr (23+24)
1 USD -El Tebein 113
CR.TR0009CLOSING.DEC
205
CM 24 B
266
45
CrMemo W.hold 12-EGP
10432
cr 21 Mar 20
4-19-mar. | 19 | 19
Deduct inv.19 EGP | 19 | 19
Egy Ex awnash 2final
Balance 2016 7
Closing Old Assuit
adv (24+29+41) Euro
88
RME-OC Po 648
reclass of rec. acco
Cancel invoice Lot15
OB-RE-Sodic Club
CR.P-50-12 AccRev | 50 | 50
Credit 22/2019 Sampl
Marsa Alam USD Inv 5 | 5 | 5
OB-SI-Beni Suif
Car-Dep AUG. 2021
close 25
libya sales oct.24
Stamps inv.38 EGP | 38 | 38
CR-K-HASSAN FEB.2023
OB-SI-Wall New Giza
Inv. 20 Farm | 20 | 20
CR - 15 EGP - Shabab | 15 | 15
10535
10546
DEC10
07/13/08/2021
DEC ADJ 39
88
CR_inv.10 | 10 | 10
Tax 73-74 cobra | 74 | 74
CR-MOC Inv 04 | 4 | 4
53
10 EGP - West Domiat
2012220007
198
18/13/03/2021
OB-ST-Sodic Dahsh-2 | 2 | 2
CR 81
CR.refund ret.
Cr.( 6-9 ) HY Bark | 9 | 9
1
41.
CR 12
Inv 19/2019 Scrap | 19 | 19
0008-2022 | 2022 | 2022
اتحاد تشيد P-62 | 62 | 62
2112220001
Cr 17
CM 11-19-April | 19 | 19
10037
Cr. Ins. Abolila
CR-17 | 17 | 17
OB-ST-3-03-2017 | 3 | 3
close 55
CR-IPC005 | 5 | 5
48-JUL-2020 | 2020 | 2020
476
Cancel Inv#10 USD VO | 10 | 10
SG EGP Inv Deduction
84-Dec-2020 | 2020 | 2020
4 cars for sale
Part Inv 14 USD Shab | 14 | 14
10225
OB005
CR IPC3 elwaraq | 3 | 3
C..IPC13TR53 | 13 | 13
Cr-S.Tax- 2 invoices | 2 | 2
10001
Scrap selling Nwabaa
10206
Eng Stamp and other
Sodic Kanten July21
Scrap Inv. 10/2021 | 10 | 10
CR ora landscapeIPC9 | 9 | 9
IPC26TR0046 | 26 | 26
Eipico material ipc3 | 3 | 3
k-huissen-mar22
Material On Site
CAN.INV.
IPC03TR0081 | 3 | 3
wady halfa ipc 5 | 5 | 5
Inv ( 1 ) S09 | 1 | 1
TAH ipc05 | 5 | 5
12-2023 | 2023 | 2023
IPC05TR54 | 5 | 5
Mariotya ipc16 zomor | 16 | 16
INV ( 3 ) ALparco | 3 | 3
inv ( 9 ) Kemt | 9 | 9
INV ( 4 ) HY Bark | 4 | 4
TR55-IPC3 | 3 | 3
kantine 6
IPC000010 | 10 | 10
IPC 1 HSR ARAB CONST | 1 | 1
inv ( 1 ) pridg 5 | 1 | 1
220621004
Selling Scrap 19-23 | 23 | 23
Selling Scrap Lot13
220321003
Ref. Akhme Asuit T
MDF FACTORY IPC07 | 7 | 7
2201210001
1st invoice Eng. SC
36
10946
32
Sadat Indust Inv. 03 | 3 | 3
2105210003
Kafr Shokr-IPC02 | 2 | 2
2012210039
2012210035
10041
4-2021 | 2021 | 2021
TR0028DEC.Closing
TR0025DEC.Closing
TR0018DEC.Closing
IPC_5_Gama_Saray
D0019-OB-Dec-2020 | 2020 | 2020
D0008-OB-Dec-2020 | 2020 | 2020
D0036-OB-Dec-2020 | 2020 | 2020
82-Dec-2020 | 2020 | 2020
141
40-2020 | 2020 | 2020
2009210006
2009210002
50-JUL-2020 | 2020 | 2020
2005210009
1-2020 | 2020 | 2020
2001210013
10035
544
1907210015
472
Adjust orascom balan
Inv. 1 EGP | 1 | 1
Scrap Lot. 01
Inv. 2 EUR 17500 | 2 | 2
Inv. 1 Final ElNokra | 1 | 1
20 EGP TOAC Main
Amend - Ras Ghareb
1901210016
17-19June | 19 | 19
1909210006
1909210001
SCD4/002
10167
1 -19 -feb | 19 | 19
1907210008
180135
180119
180136
Inv 12/2019 Scrap | 12 | 12
TETRA - 001 | 1 | 1
Soc In 49 Asuit
180107
27 EGP - Shabab
5004 ADJ
16 EGP- West Domiat
16 USD - Suez Gulf
19 EGP- West Domiat
7 EGP - Lina
13-12-2018 | 12 | 12
SH Inv.35&36 comm | 35 | 35
Inv, 4 usd Borg Arab | 4 | 4
6 EGP Cement
DR - VAT- Egytech 05
Soci.11-16:23$Qena | 16 | 16
Adj Inv 7 | 7 | 7
Adj inv 1 | 1 | 1
121
91
87
123
15
118
36
116
12
104
71
108
DR - VAT- Egytech 01
5 EGP - Lina
Discount USD Reverse
close interest
close discointerests
Inv.8 Heliopolis | 8 | 8
Inv. 7 Akhmem Qena | 7 | 7
inv. 9 Assuit Akhmem | 9 | 9
inv. 7 Assuit Akhmem | 7 | 7
Settlement
Ret.Inv.4 PIP West | 4 | 4
Inv.3 PIP West | 3 | 3
18/1
1
(1)SD elmostsmrin |  | 1
13 N.G 2
(3) new giza wall |  | 3
(45)pkg#45 |  | 45
mos 3
16-
Amend VAT PKG#62(1) |  | 1
DEC ADJ 101
4 EGP - Suez Gulf
final'
final"
9 USD - Suez Gulf
DEC ADJ 35
7 USD - Shabab 117
ADJ RECEIPT
8 USD/123/2011/2012
10 USD - Suez Gulf
1045
1043
40
OB Advanced 8
M-D-003 | 3 | 3
Cam/EDC/5/2016
Erection/H001
29-132KVA-H | 132 | 132
2-132KVA-Sup | 132 | 132
10-132KVA | 132 | 132
15 pkg#53
15 EGP - West D. 117
13 EGP - West D. 117
180035
180025
24 EGP - West Domiat
20 EGP - Shabab 117
14 EGP - West D. 117
2002210029
11 USD -Shabab
11 USD - Shabab 117
6 USD - Shabab 117
4 USD - Shabab 117
2 USD - Shabab 117
( 2 ) |  | 2
5 USD - Hitachi
Inv 2 EGP VO SG | 2 | 2
5EGP rema Tax Balanc
3 EGP - Suez Gulf
13 USD - Suez Gulf
7 USD/123/2011/2012
Inv 67 P8 Assuit | 67 | 67
inv 44 P11El Natroun | 44 | 44
Barwa 16
Inv. 33 Damac | 33 | 33
6 Damac
Inv 20 Damac | 20 | 20
Damac 15
137/9
13sodic club
17+18+19
16 pkg#53
8 EGP South Helwan
408 EGP Avice ZTPC
1061
449 Euro - Avice
405 EGP Avice ZTPC
1 Ghelion
Inv 6 Abo Zaabl | 6 | 6
Inv. 16 Zona franka | 16 | 16
1010
1008
OB 3923
40 EGP-Giza No III
38 EGP-Giza N. III
5 Banha
32 wadi 8
8 Euro- South Helwan
colose alstom unappl
6 Euro- South Helwan
3918
final-
10218
10014
10137
10079
01 - March -scr
(16)new giza 2 |  | 16
1-Cazenga
TAM-CW-EURO-10 | 10 | 10
TAM-CW-EGP-18 | 18 | 18
TAM-CW-EGP-20 | 20 | 20
ISE-CW-EGP-16 | 16 | 16
TAM-CW-EGP-15 | 15 | 15
TAM-CW-EURO-05 | 5 | 5
19100026
BSF-CW-EGP-13 | 13 | 13
MOS-SD-EGP-IPC 25 | 25 | 25
18sd mosstasmreen
MOS (3) |  | 3
20 EGP- Shabab
17 EGP -West Domiat
180111
Banah 7 inv 39 | 39 | 39
Soc 41 Wadi 10
Inv 13 Ghelion | 13 | 13
Gheleon 5
9
Gheleon 6
(5) pkg#107 |  | 5
10076
26 EUR - Giza N. III
37 EGP-Giza North 1&
close un appl. egyte
Inv. 17 Oewon Mousa | 17 | 17
Inv. 13 Oewon Mousa | 13 | 13
44 Wadi 11
3 EGP - West D. 117
10016
Inv 21 Damac | 21 | 21
Inv 19 Damac | 19 | 19
Inv 42 EGP giza III | 42 | 42
close un appl sak
Inv 11 Qatar accrual | 11 | 11
16 EGP - Shabab 117
Inv NO.6 KWT Flor | 6 | 6
Inv No 65 Dewania | 65 | 65
Beni Swef Inv April
(21)new giza 2 |  | 21
ROYAL CITY-IPC17 | 17 | 17
Sand Attaqa May
14
Inv 24 Asec | 24 | 24
10073
Invoices Abo Quer,
Banha 118 Invoice
1905210007
180142
180157
13 USD - West Domiat
12 EGP - West D. 117
10105
1906210008
180012
180010
Apachi Inv No P.C#17 |  | 17
5 EGP - Suez 106
Inv. NO.2 KWT Floor |  | 2
OB-SI-PKG#53
cw (8) mosstsmren |  | 8
9 Euro-South Helwan
8 EuroSouth Helwan
10 Euro-South Helwan
Invoice 26 & 31 EUR | 26 | 26
(9) CW |  | 9
20 USD - Banha 118
Inv 23 USD | 23 | 23
3 EGP - El Tebin 124
Last Invoice 6 Octob | 6 | 6
10135
487
Inv Qatar (13 to 18)
Inv. NO.4 KWT Floor |  | 4
Inv 19 Qatar | 19 | 19
10417
10349
10280
new giza2-ipc 26+ | 26 | 26
IPC 01 PKG#85 | 1 | 1
8sd euro mosstsmreen
4sw mosstsmreen
1cw ismailya
Allocation IPC10+ | 10 | 10
Inv.45 Assuit Akhmem | 45 | 45
Inv.39 Assuit Akhmem | 39 | 39
Inv.38 Assuit Akhmem | 38 | 38
Inv.43 Qena Akhmem | 43 | 43
Inv. 2 Akhmem Qena | 2 | 2
14 USD - Shabab
refund CSI
retention
34/P/10/ER/2017/USD
7-132KVA | 132 | 132
04-132KVA-J | 132 | 132
(1) كانتين يناير |  | 1
Inv 88 P7 Sammound | 88 | 88
Inv 74 P2 Sammound | 74 | 74
48515.5
Ret. Banh refund
Inv. 17 Badr | 17 | 17
Inv. 16 Badr | 16 | 16
Inv. 15 Badr | 15 | 15
Asec.Paymen req.2
10/4/12/2017
10216
10267
Inv No4 Wattanya220 | 4 | 4
Social 69/1Samanood
180087
180052
ref.reten wadi elnat
k (mohamed mansour)3
k(m.khalifa) 3
23sd elmostsmrin
inv no (Comm/001)EGP
Inv 75 P4Abo Matamir | 75 | 75
Itay inv.4 -358- | 4 | 4
Elkayan Inv.10 | 10 | 10
180059
(2)cw almansora |  | 2
SODIC CLUB-IPC (28) | 28 | 28
Soci. Proj.358K.M
2105210004
1906210013
1904210004
2007210005
2001210015
2005210002
1908210002
10334
11201
Inv.64 Borg Alarab | 64 | 64
Inv.45 Borg Alarab | 45 | 45
Inv.38 Borg Alarab | 38 | 38
Inv.5 Usd borg alarb | 5 | 5
10397
Scarp inv.2/2018 | 2 | 2
01/2018
k-m.mansour jun2018
k-m.khalifa-elco-jun
10992
ALAMAL BRIDGE- FINAL
3 EGP - Lina
C.R 1-2% | 2 | 2
Heliopolise 6
199
Inv. 28 USD | 28 | 28
Apachi Inv No PC.#28
Inv. 4 Project S 1 | 4 | 4
180126
180122
Inv.7. Heliopolis | 7 | 7
Kanten-Suiz-Khalifa
18100068
BSF-SW-IPC3 | 3 | 3
IPC9-ROYAL CITY | 9 | 9
Inv 1 Kuraiamte | 1 | 1
R5-IPC26 | 26 | 26
R5 - IPC18 | 18 | 18
Kanten.A.Osman.Royal
امر توريد حسن المأمو
Inv.14 Assuit Akhmem | 14 | 14
soc 22-25 quna akhmi | 25 | 25
soc 14-21 quna akhmi | 21 | 21
10526
TAM-CW-EURO-01 | 1 | 1
180089
Inv.5 Borg Alarab | 5 | 5
DM 10 Samanoud
KantenAOsman.Ismalya
Inv.22 Qena- Akhmem$ | 22 | 22
OB RT 004
JPSS-16 | 16 | 16
ELSEWEDY UNI-IPC2 | 2 | 2
Inv.1 Phosfat | 1 | 1
Inv. 13 Balat Lot 2 | 13 | 13
Inv. No.11 KWD Floor |  | 11
TUNNLE- IPC FINAL
K-m.badawy-mntra-dec
K-H.MAHMOUD-JAZI
So.$4-8:19Assuit | 8 | 8
Inv.14Assuit Akhmem$ | 14 | 14
R5 (1) ipc 33 final | 33 | 33
CON/032
LOC/024
Con-012 Rev0 | 12 | 12
10389
10371
10514
Inv. 5 Borg Alarab | 5 | 5
Soreal IPC030 | 30 | 30
MOS-CW-EGP-IPC14 F | 14 | 14
Refund Retention K
10569
DP WORLD - IPC14 | 14 | 14
ELSWEDYUNI-MEP-IPC07 | 7 | 7
ELSWEDYUNI-F&M-IPC04 | 4 | 4
10582
uni-fin&mep-ipc09 | 9 | 9
k-HASSAN-R5-JAN
Coll Ansaldo
Inv. 8 Badr | 8 | 8
K-M.khlifa-ministrie
10002
PKG#117- IPC 09 | 9 | 9
28/13/08/2021
1907210014
180176
516
Inv. 1 Mostakbal | 1 | 1
SOUQ ELSAMAK-PO01
UNI-FIN&MEP-IPC1 | 1 | 1
10564
10596
224
219
1901210018
K-Ahmed.Osman-Ismali
KAYAN FINSH1-IPC08 | 8 | 8
Ref. Ret. Borolls
10567
Benban Lot 2 Inv. 32 | 32 | 32
Benban Lot 2 Inv. 31 | 31 | 31
Benban Lot 2 Inv. 23 | 23 | 23
Benban Lot 2 Inv. 14 | 14 | 14
Benban Lot 2 Inv. 12 | 12 | 12
Benban Lot 2 Inv. 7 | 7 | 7
Benban Lot 2 Inv. 3 | 3 | 3
Benban Lot 1 Inv. 28 | 28 | 28
10706
E&W-Consumption-Apri
adv. refund
Supply/J009
Inv.01 Sugar OHTL | 1 | 1
Inv 2 Sugar S/s | 2 | 2
Re.Inst6-7-11-29asui | 7 | 7
1904210008
1903210006
237
017/2019
R05-ZONE02-IPC03 | 3 | 3
IPC#4 |  | 4
Hussien.mansour.June
K-A.Osman-Royal-June
Benban Lot1 Inv 6USD | 6 | 6
Benban Lot1 Inv 2USD | 2 | 2
Benban Lot2 Inv 2 $ | 2 | 2
10710
PKG#140-IPC17 | 17 | 17
ISE-CW-EURO-02 | 2 | 2
10635
Center Zone final 24
ROYAL CITY2-IPC15 | 15 | 15
NFISHA BRIDGE-FINAL
Inv 1 + $ Sugar S/s | 1 | 1
Inv 1 $ Sugar S/s | 1 | 1
Kanteen-R05-july2019
Soc inv 14 Sammanoud | 14 | 14
1906210001
1906210015
244
Inv. 14 Badr | 14 | 14
251
252
259
10735
10761
10640
M.Z TUNNLE-FINAL
Kanteen-R05-Aug-2019 | 2019 | 2019
inv ( 15 ) 1-12-2020 | 15 | 15
10188
10133
10134
10128
511
491
OF/MP-04 | 4 | 4
H,A/IPC06/PO52/323 | 6 | 6
MANGROVY-IPC11 | 11 | 11
mangrove-IPC04 | 4 | 4
6-19-April | 19 | 19
Inv.33 Borg Alarab | 33 | 33
22/2019 Sampl T&D1
30-19 Aug | 19 | 19
PKG#101-IPC11 | 11 | 11
10106
257
268
1908210013
SOREAL - IPC06 | 6 | 6
4-19Mar | 19 | 19
13-19-June | 19 | 19
21-19Jul | 19 | 19
Inv 8 Portsaid.final | 8 | 8
Kanteen-SEP-UNI
PO-PKG#53-IPC03 | 3 | 3
kanteen-sep-royal
ALALAMEN ROAD-IPC02 | 2 | 2
hyper one- IPC09 | 9 | 9
Hyperone-IPC05 | 5 | 5
IKEA-IPC01 | 1 | 1
39-19 oct | 19 | 19
Kanteen-Sodic-Aug019
9 sales 2019
20_2020
1907210018
Benban Lot2 Inv 11 $ | 11 | 11
Benban Lot2 Inv 7 $ | 7 | 7
10810
284
278
40-19 oct | 19 | 19
494
inv 5 Ghana | 5 | 5
10189
10953
Kantee-Sodic-Oct-019 | 19 | 19
46-19 nov | 19 | 19
pkg#140 - ipc 05 | 5 | 5
18 EGP Shipping Main
13 EGP - Suez Gulf
R5 ZONE2-IPC09 | 9 | 9
11031
ALAMEEN SUPPLY-IPC02 | 2 | 2
10248
29-19 Aug | 19 | 19
283
287
Coll Scrap A08
Benban Lot 1 Inv. 13 | 13 | 13
Benban Lot 2 Inv. 22 | 22 | 22
TETRA-MK4-IPC01 | 1 | 1
484
483
529
10329
PKG#117-IPC13 | 13 | 13
1902210005
-3,460.69 | 3 | 3
11076
55-19 nov | 19 | 19
1908210007
1904210001
1901210001
300
Scrap Lot. 13
Scrap Lot. 12
5-2019 | 2019 | 2019
Inv.24 Qena- Akhmem$ | 24 | 24
Scrap Inv. 35/2019 | 35 | 35
Scrap Lot. 06
Rf.retention Samanod
Benban Lot 2 Inv. 25 | 25 | 25
Benban Lot 1 Inv. 24 | 24 | 24
Toshka Lot 4 Inv .17 | 17 | 17
Toshka Lot 4 Inv .7 | 7 | 7
Toshka Lot 4 Inv .2 | 2 | 2
Scrap Commission
Lot. 05 - 2 | 2 | 2
CFC- IPC04 | 4 | 4
Kanteen-Royal-Jan-20 | 20 | 20
Kanteen-Sodic-Dec-19 | 19 | 19
534
20100003
ROYAL CENTER-IPC03 | 3 | 3
ISE-SW-EGP-07 | 7 | 7
ISE-SW-EGP-06 | 6 | 6
inv. Ghareeb 98%
Lot 16 Scrap Sales
500
489
Inv.49 Borg Alarab | 49 | 49
Scrap Inv. 37/2019 | 37 | 37
10430
11141
MP-07 | 7 | 7
Inv(1)131219 | 1 | 1
inv(2)251119 | 2 | 2
8 Jan 2020
Toshka Sub Inv. 23 $ | 23 | 23
Toshka Sub Inv. 02 $ | 2 | 2
11077
11122
58-19 Dec | 19 | 19
57-19 Dec | 19 | 19
KAYAN RADM1-FINAL
H,A-IPC10-PO52/323 | 10 | 10
Social Inv.24$Qen 2 | 24 | 24
11052
Inv.25Assuit Akhmem$ | 25 | 25
10851
508
R5-IPC012 | 12 | 12
Kanteen-R05-Mar-2020 | 2020 | 2020
Kanteen-Royal-Mar-20 | 20 | 20
Inv.22 Borg Alarab | 22 | 22
Inv.14 Borg Alarab | 14 | 14
Inv.12 Borg Alarab | 12 | 12
532
Inv.61 Borg Alarab | 61 | 61
Toshka Lot 6 Inv $2 | 2 | 2
329
323
340
335
Inv.70 Borg Alarab | 70 | 70
39-2020 | 2020 | 2020
inv(5)250220 | 5 | 5
11663
ELALAMEN ROAD-IPC3F | 3 | 3
Inv. 14 Balat lot 3 | 14 | 14
2003210010
10362
10-2020 | 2020 | 2020
ENG/026 Rev0
346
2008210005
2002210021
12-2020 | 2020 | 2020
526
East Owainat Inv. 02 | 2 | 2
11601
11502
ROYAL CITY-IPC30 | 30 | 30
ELHEGAZ BRIDGE-IPC01 | 1 | 1
SOREAL-IPC15 | 15 | 15
Claim-01 | 1 | 1
IPC#1 |  | 1
2007210007
2007210008
Nagaa Hamady Inv.5 | 5 | 5
Scrap invoice12 K SA | 12 | 12
355
Con-013 Rev0 | 13 | 13
2004210011
ELALAMEEN SUPPLAY-03 | 3 | 3
11524
Inv.54 Borg Alarab | 54 | 54
R5 FINSHING-IPC03 | 3 | 3
ESU2-ARCH&MEP-IPC06 | 6 | 6
IPC#3 |  | 3
HYPER ONE-IPC13 | 13 | 13
Kanteen-Sodic-Aug-20 | 20 | 20
36-May-20 | 20 | 20
47-Jul-2020 | 2020 | 2020
52-JUL-2020 | 2020 | 2020
11639
10145
10147
Scrap Inv. 10/2020 | 10 | 10
ROYAL ZONE-IPC11 | 11 | 11
R05(2) ipc 39 | 39 | 39
R5(2) ipc25 | 25 | 25
R05(2) ipc24 | 24 | 24
R5(2) ipc(22) | 22 | 22
R05(2) ipc21 | 21 | 21
11561
Inv.12/2020 -Transmi | 12 | 12
11582
ISE-CW-EGP-26 | 26 | 26
ISE-CW-EGP-24 | 24 | 24
PKG#162-IPC08 | 8 | 8
10180
10061
369
57-AUG-2020 | 2020 | 2020
Toshka Farm Inv. 01 | 1 | 1
2008210001
IPC#6 |  | 6
11506
Toshka Lot 6 Inv .11 | 11 | 11
MIN-CORE-IPC05 | 5 | 5
MIN.LAND SCAPE-IPC02 | 2 | 2
final new giza1
11442
Cairo-alex ipc 33 | 33 | 33
cairo-alex ipc23 | 23 | 23
45-2020 | 2020 | 2020
11502
11223
11222
11291
10605
373
Kanteen-Olympic-2020 | 2020 | 2020
364
RINING ROAD-IPC02 | 2 | 2
2010210008
11644
2010210006
inv ( 16)30-12-2020 | 16 | 16
IPC_1_Gama_Saraya
ora ph1 ipc 34 | 34 | 34
ora ph1 ipc 30 | 30 | 30
ora ph.1 - ipc 23 | 23 | 23
ANG-Mor-Inv 4 - Ints | 4 | 4
2009210017
2010210002
IPC#2 |  | 2
Toshka Lot 6 Inv $8 | 8 | 8
Tunnel Inv. 6 | 6 | 6
11782
MARIYTIA-R.R-IPC01 | 1 | 1
El Sewedy University
Tunnel Inv. 7 | 7 | 7
19100004
EL SEWEDY HQ IPC16 | 16 | 16
ELSEWEDY IPC 11 | 11 | 11
Inv.75 Borg Alarab | 75 | 75
Inv.76 Borg Alarab | 76 | 76
Ref Retention Ghlion
Inv. 15 Balat lot 3 | 15 | 15
Inv. 9 Oewon Mousa | 9 | 9
11622
11548
Inv. 3 Sugar 33 OHTL | 3 | 3
Katamya chreek ipc39 | 39 | 39
KATAMEYA GREEKS-IPC6 | 6 | 6
Inv.25Usd borg alarb | 25 | 25
30-2020 | 2020 | 2020
Toshka Lot 6 Inv .15 | 15 | 15
ministires-1 | 1 | 1
BSF-CW-EURO-9FINAL | 9 | 9
IKEA2-IPC02 | 2 | 2
ROYAL ZONE-IPC14 | 14 | 14
10366
10365
IPC_1_LRT |  | 1
IPC#1 |  | 1
SOUQ ELSAMAK-IPC02 | 2 | 2
MR.ADHAM-IPC001 | 1 | 1
Cre.adv. $ Toshka 4
10163
392
12002
Sweedy Uni. 2
Soreal - 2 | 2 | 2
R05 - 2 | 2 | 2
5-2021 | 2021 | 2021
Ref Ret Sugar 33OHTL
7
IPC-Condo
2012210004
P-45-Portsaid Inv.05 | 5 | 5
2103210002
De. West Port said
RING MARYOTUA-IPC03 | 3 | 3
SOREAL-IPC22 | 22 | 22
11 feb 20
GOV2-IPC 1MOS+2 | 1 | 1
PKG#163-IPC09 | 9 | 9
10464
10
Mangroovy - 3 | 3 | 3
Inv.51 Qena Akhmem | 51 | 51
Tunnel Inv. 9 | 9 | 9
South Valley Inv. 06 | 6 | 6
11823
11824
401
400
ISE-SW-EGP-08 | 8 | 8
Inv.50 Qena Akhmem | 50 | 50
404
12076
11870
Ret-Ref32/13/03/2021
MANROVE-IPC14 | 14 | 14
PKG#177 IPC 25 | 25 | 25
PKG #177 IPC019 | 19 | 19
PKG #177 IPC09 | 9 | 9
R5 FINSHING-IPC11 | 11 | 11
Sodic - 04 | 4 | 4
Inv.19 - Lot 1 | 19 | 19
Inv.17 - Lot 2 | 17 | 17
Inv.14 – Lot 2 | 14 | 14
Inv. 11 – Lot 2 | 11 | 11
elco egat ipc10 | 10 | 10
11982
PKG #101 IPC020 | 20 | 20
Acroket Company - 04 | 4 | 4
19
2105210016
INV( 1 ) 21-6-2021 | 1 | 1
R05 Finishng - IPC12 | 12 | 12
200245
200209
200162
Diplo Dist IPC04 | 4 | 4
Air Force Inv . 04 | 4 | 4
12164
11721
mansoura ipc 09 | 9 | 9
R5 - IPC22 | 22 | 22
Kafr Shokr IPC03 | 3 | 3
South Valley Inv. 04 | 4 | 4
10582
Midor Inv. 01 | 1 | 1
ODP ipc03 | 3 | 3
Hosh Essa Inv. 11 | 11 | 11
Toshka Sub Inv. 01 $ | 1 | 1
2101210005
Kanten-Jun21-R05
DP World IPC028 | 28 | 28
OLYMPIC CIVIL-IPC04 | 4 | 4
FPC - Shenzo Aby
10623
20
IPC-7-PLAYA | 7 | 7
Kanten katmeya Jul21
LRT 10Ramadan Inv.04 | 4 | 4
فاتورة تكسير خردة
25
TAM-CW-EGP-24 | 24 | 24
10181
414
12165
Scrap Inv. 08/2021 | 8 | 8
12385
2012210013
10266
Inv. 13 Heliopolise | 13 | 13
Katameya-Kanten-8/21 | 8 | 8
Kanten Kayan AUG/21
IPC#3 - ElMoneeb |  | 3
FPC - PKG#178
INV ( 3 ) | 3 | 3
21-2021 | 2021 | 2021
LOC/018
Ref.Ret Asuit akhm
Ref.Ret Sugar Sub $
IPC-FINAL-HYPER ONE
South Valley Inv. 01 | 1 | 1
18-2021 | 2021 | 2021
10902
PKG #140 IPC025 | 25 | 25
Olympic Hall IPC05 | 5 | 5
South Valley Inv. 07 | 7 | 7
Air Force Inv . 12 | 12 | 12
MDF FACTORY3 IPC01 | 1 | 1
Invoice 2 to JV | 2 | 2
Engineering SC Inv
10804
11723
30-2021 | 2021 | 2021
IPC4 - Monorail | 4 | 4
10884
MDF IPC05 | 5 | 5
200268
200328
200410
IPC#6` |  | 6
425
Olympic Hall IPC02 | 2 | 2
Waldorf IPC7 | 7 | 7
CFC IPC027 | 27 | 27
2108210001
Ref.Ret Zafra-B-Suef
10962
10982
Ret Qen-akh 7 T
Ref.Ret Asuit akh 5
CFC IPC026 | 26 | 26
12768
12808
Scrap Inv. 17/2021 | 17 | 17
Air Force Inv . 19 | 19 | 19
Air Force Inv . 18 | 18 | 18
INV ( 4 ) GET | 4 | 4
EGAT WaterTank IPC06 | 6 | 6
katamya ipc11 | 11 | 11
519
Minist Core IPC09 | 9 | 9
443
12889
sokhna port ipc 12 | 12 | 12
sokhna port ex ipc06 | 6 | 6
Inv.15 - Lot 1 | 15 | 15
IPC#5 GSCC Port Said |  | 5
IPC#1-Port Saeid |  | 1
120721
ODP IPC02 | 2 | 2
Ref. Akhmem Asuit2T
11082
11144
ENR-Sign Inst Inv04 | 4 | 4
Rolling mill ipc 03 | 3 | 3
Wat Pump Obour Inv.2 | 2 | 2
12610
12611
12651
Benban Lot2 Inv 12 $ | 12 | 12
Tam SW Final
SW Final
PORT SAID IPC 27 | 27 | 27
IPC-4-Playa Roof | 4 | 4
k-sport hall feb2022
k-MINISTRIES feb2022
k-R05 feb2022
Hosh Essa Inv. 02 | 2 | 2
INV ( 3 )ALparco | 3 | 3
11283
11282
11286
54
JPSS-20 | 20 | 20
Repeated test -2 | 2 | 2
T 10-2022 | 2022 | 2022
Scrap Lot No:25
cairo-alex ipc 17 | 17 | 17
IPC#9 - Spkhna port |  | 9
MDF FACTORY IPC08 | 8 | 8
11363
10th Ind Park Inv.02 | 2 | 2
egat watertank ipc10 | 10 | 10
Material EES6
Material EES5
HYPER ELCTRO-FINAL
FPC - Tiger
11746
220421005
520
ELCO EGAT IPC 11 | 11 | 11
11519
WALDORF astoria IPC1 | 1 | 1
220321001
Emaar pkg#189 ipc 31 | 31 | 31
Emaar PKG#189 IPC28 | 28 | 28
Emaar pkg#189 ipc 14 | 14 | 14
IPC-16-PLAYA | 16 | 16
IMP/069
Elco EGAT IPC12 | 12 | 12
PIP indust Inv.02 | 2 | 2
mansora finish ipc22 | 22 | 22
Mdf factory2 ipc05 | 5 | 5
Ora landscape ipc 10 | 10 | 10
astoria sharm ipc 01 | 1 | 1
523
Toshka Lot 6 Inv $11 | 11 | 11
IPC-18-PLAYA | 18 | 18
K-SALIM JUN2022
12992
air devance ipc03 | 3 | 3
10th Ind Park Inv.03 | 3 | 3
T 7-2022 | 2022 | 2022
200709
200664
Toshka Lot 6 Inv .16 | 16 | 16
11682
10020
ENG/055
220421003
220321002
10342
64
220621008
71
MDF Factory ipc (27) | 27 | 27
220721001
220721004
K-ALI JUL2022
R5(2) ipc 23 | 23 | 23
180056
IPC#4 |  | 4
MDF (2) - IPC 8 | 8 | 8
inv ( final ) T0022
inv ( 3 ) montazha | 3 | 3
olmpiclandscape ipc1 | 1 | 1
New Giza Hosp ipc16 | 16 | 16
11619
SUEZ STEEL SSC IPC 1 | 1 | 1
In&ReApply(SSC)IPC2 | 2 | 2
intak&ret apply ipc5 | 5 | 5
In&reApply(ABB)ipc1 | 1 | 1
200808
200645
200626
TR0048-00002 | 2 | 2
200710
200649
200644
k-hussain Dec.2022
Gov2 ipc 15+16 | 15 | 15
EGAT Watertank-IPC12 | 12 | 12
minis shel ipc09 | 9 | 9
MDF (2) - IPC9 | 9 | 9
INV ( 1 ) ALmansorya | 1 | 1
inv ( 15 ) CS-20 | 15 | 15
inv ( 16 ) CS-20 | 16 | 16
inv ( 1 ) CS-20 | 1 | 1
k-mustafa sep2022
kafr shokr ipc#9 |  | 9
Min MEP. IPC5 | 5 | 5
FPC - LRT ARABCo
ROLLING MILL IPC 09 | 9 | 9
Finishing IPC02 | 2 | 2
Astoria sharm- IPC4 | 4 | 4
new giza hos ipc3 | 3 | 3
IPC#1&2 -Assuit Rent |  | 1
IPC001 Dewalling | 1 | 1
Elsewedy HQ IPC19 | 19 | 19
200770
PKG #101 IPC021. | 21 | 21
MDF IPC15 | 15 | 15
INV ( 17 ) GET | 17 | 17
K-SALIM OCT.200
sokhna port ex ipc07 | 7 | 7
elsewedy HQ- IPC21 | 21 | 21
IPC00001 | 1 | 1
43- kantine 5
T16-2022 | 2022 | 2022
Urbn-k IPC 7 | 7 | 7
sokhna port ex ipc 8 | 8 | 8
Revamp ipc(4) | 4 | 4
IPC#00002 |  | 2
IPC004 Air Defense | 4 | 4
port said silos ipc9 | 9 | 9
EIPICO3 - IPC1 | 1 | 1
IPC0000001 | 1 | 1
INV ( 2-3-4 ) KEMET | 2 | 2
IPC#000015 |  | 15
K-HASSAN FEB.2023
ELSEWEDY HQ-IPC25 | 25 | 25
IPC#5 WADI |  | 5
IPC#7 WADI |  | 7
IPC006 TR60 | 6 | 6
Olypic sehe IPC1 | 1 | 1
Dp world ph.2-IPC 2 | 2 | 2
ipc 2 elmahager | 2 | 2
Ora ph landscap ipc2 | 2 | 2
IPC#10 WADI |  | 10
230000005
IPC# 1 WARAAQ |  | 1
MDF 2 IPC (15) | 15 | 15
sokhna port ex ipc11 | 11 | 11
in.&ret.sup sscipc1 | 1 | 1
R.O.SU.PRIC.ADJ.IPC3 | 3 | 3
playa-c185 pic 1
playa c-204 ipc 2 | 2 | 2
seashell playa ipc04 | 4 | 4
seashell playa ipc 6 | 6 | 6
october tunnel ipc06 | 6 | 6
200994
200830
Urbn-k ipc (8) | 8 | 8
Katameya Creek ipc35 | 35 | 35
IPC005 | 5 | 5
sorealhardscapeIPC11 | 11 | 11
K-MUSTAFA MAY.2023
200912
IPC03 TR64 | 3 | 3
Katameya urbnk ipc9 | 9 | 9
Egat Piping ipc 2 | 2 | 2
MDF Factory ipc 29 | 29 | 29
seashell playa ipc 5 | 5 | 5
IPC001 TR64 | 1 | 1
inv ( final) montazh
Minis MEP IPC8 | 8 | 8
IPC0011 | 11 | 11
INV ( 1 ) Central Ca | 1 | 1
MARIOTYIA IPC16 | 16 | 16
200871
11-2023 | 2023 | 2023
200811
Olympic fins ipc5 | 5 | 5
air def finish4 IPC1 | 1 | 1
Bis school ipc (1) | 1 | 1
inv ( 1 ) T. Pushing | 1 | 1
Royal City Final 43
IPC FINAL 26th
IPC#002 - Kilo21 |  | 2
IPC#2 Bahr El Baqar |  | 2
IPC09 TR60 | 9 | 9
IPC6&7TR0064 | 6 | 6
Egy Exchange IPC3 | 3 | 3
k-abdel w sep.2023
IPC04TR0069 | 4 | 4
IPC10,11 TR51 | 10 | 10
Mdf Factory ipc 30 | 30 | 30
Rent1st+2nd madi6-24 | 24 | 24
int&rut sup ABB ipc6 | 6 | 6
Waldorf IPC 20 | 20 | 20
IPC06TR0078 | 6 | 6
Mohamed Aly IPC Fin
Carrefour Head ipc 5 | 5 | 5
IPC15TR0055 | 15 | 15
Air Dev fire IPC2 | 2 | 2
Air dev elec IPC2 | 2 | 2
IPC001 TR59 | 1 | 1
K-SALIM NOV.23
IPC(3) / PO 26195 | 3 | 3
IPC 001-PO 31948 | 1 | 1
IPC-007-DEXTRA | 7 | 7
New Giza ipc 19 | 19 | 19
sokhna Br. ipc14+15 | 14 | 14
mansora finish ipc08 | 8 | 8
MANSOURA IPC13 | 13 | 13
R05(2) ipc 28 | 28 | 28
playa c072- ipc 5 | 5 | 5
Woldorf sharm ipc 7 | 7 | 7
Baraka Fance ipc 2 | 2 | 2
Baraka Fance ipc 1 | 1 | 1
New Gas Station ipc1 | 1 | 1
svc ipc 2 | 2 | 2
inv ( 11 ) Captal 1 | 11 | 11
Air dif finish4 IPC2 | 2 | 2
IPC02TR0075 | 2 | 2
IPC04TR0078 | 4 | 4
R05(2) ipc 42 | 42 | 42
Driller inv2.dec.23 | 2 | 2
IPC 3 elwaraq | 3 | 3
Wady elnatroon ipc07 | 7 | 7
Carrefour RBS IPC 3 | 3 | 3
Sokhna Bri esc.1:13
Emaar pkg#189 ipc 23 | 23 | 23
IPC09&10 TR48 | 9 | 9
IPC 12 TR53 | 12 | 12
IPC03TR0071 | 3 | 3
IPC14TR0039 | 14 | 14
ora zed ph2 ipc02 | 2 | 2
Alamein L&L IPCFin
R05(2) ipc44 | 44 | 44
Silos supp.EUR ipc01 | 1 | 1
PKG#220-IPC5=6 | 5 | 5
IPC#003 |  | 3
IPC no14..
IPC1TR0083 | 1 | 1
INV ( 3 ) Central Ca | 3 | 3
IPC18TR0055 | 18 | 18
24000007
220002024
IPC13TR0048 | 13 | 13
201211
IPC11TR0060 | 11 | 11
Eipico ipc 15 | 15 | 15
201171
El ROUDA Final
port said ipc23 | 23 | 23
pkg#189-IPC9 | 9 | 9
01 Solid
201231
Ora ph.1 - IPC 22 | 22 | 22
Final
Rolling Mill ipc 15 | 15 | 15
Inv-02 | 2 | 2
Cairo-alex Esc.20:41
SPX.2 ipc06 | 6 | 6
Egat Mechnical ipc 4 | 4 | 4
IPC08TR0061 | 8 | 8
QASRRASHWAN A 1
L4283/2024
L 4291/2024
ABOGHALEBIPC21+22+23 | 21 | 21
QASR RASHWAN B IPC1 | 1 | 1
IPC17TR0060 | 17 | 17
IPC11TR0061 | 11 | 11
IPC08TR0059 | 8 | 8
el khatatba ipc05 | 5 | 5
Elmahager esc.2:7
Rent 7-2024 | 2024 | 2024
K-HASSAN AUG.24
Playa - C470 ipc 2 | 2 | 2
Inv ( 6 ) A.S | 6 | 6
K-ABDELWAHAB-AUG.24
201295
201376
201296
201274
Eipico ipc 18 | 18 | 18
IPC#4#Roubiky |  | 4
K-HASSAN-9-24 | 9 | 9
LEKELA IPC2=4 | 2 | 2
201412
Inv-05 | 5 | 5
Sales Sep.24 Tetra
201374
EL KHATBA ESC 1:12
ABO GHALEB ESC 1:20
IPC06TR0084 | 6 | 6
2200002024
Damietta Pkg 3 ipc 1 | 1 | 1
IPC11TR0068 | 11 | 11
IPC13TR0061 | 13 | 13
k-abdelwahab-
IPC08 TR48 | 8 | 8
middle east inv.5 | 5 | 5
Tetra sales oct.24
IPC01TR0072 | 1 | 1
IPC#3 |  | 3
201455
Playa c470 ipc 5 | 5 | 5
playa C469 IPC 8 | 8 | 8
Playa c470 ipc 4 | 4 | 4
IPC #1 Abo Ghaleb
IPC02TR0095 | 2 | 2
IPC14TR0088 | 14 | 14
IPC20TR0060 | 20 | 20
201474
k-hassan-11.24 | 11 | 11
RME-RS inv.4 | 4 | 4
13120
180082
9 EGP South Helwan
CR 22050210.73
Libya Eqpt.8 Co.2
close11
Cr.P-10-14 | 10 | 10
Scrap Inv. 05/2022 | 5 | 5
CN Semeins
10238
10391
IPC4 elwaraq | 4 | 4
5001-3 | 3 | 3
Credit closing pip
Ref. 06/13/07/2019
60
2sas
CR-Inv#180163 | 180163 | 180163
close69
credit Lot. 3
Inv 11/2019 | 11 | 11
close68
Adj balance
cr50-JUL-2020 | 2020 | 2020
DEC ADJ 94
D.M APR & MAY 2020
CR - IPC#23 |  | 23
Cr-S.Tax- 5 invoices | 5 | 5
D.N Railway16-6-2021 | 6 | 6
CR.Toshka Farm Inv.3 | 3 | 3
Soc.2020 تشيد سكرخط
Ref.Settl.
cr11
1-2023 | 2023 | 2023
D0040-OB-Dec-2020/Cr | 2020 | 2020
34
Sales Aug.24
close 53
Hosh Essa USD Inv.01 | 1 | 1
Scrap 7/2018
INV ( 20 ) GET | 20 | 20
5
10461
close 59
Balance 5
Libya Eqpt.Adv Co.3
P-30-EGY اتحاد تشيد | 30 | 30
10120
final inv Assuit
cr-abo shanab ipc01 | 1 | 1
11 EGP - Shabab
Credit Sales Scrap
cr tetra salesoct.24
4-132KVA-H-del | 132 | 132
Scrap 2/2019 Copy2
Inv 15/2019 Scrap | 15 | 15
Zafra Souf Final7civ
1126
13/13/06/2022
L965/2024
180086
Vat deductin Vat 13
Inv 17/2019 Scrap | 17 | 17
1907220003
IPC-3 | 3 | 3
12848
deduct. inv. 21 EGP | 21 | 21
تجديد تشيد وبناء2020
64
Cr. Inv ( 1 ) S 09 | 1 | 1
10947
Pole.Cvr.Inv.1.Cncl | 1 | 1
CR_inv12 | 12 | 12
16-closed
Adj.180132
ref inv. 1 | 1 | 1
cr.inv.4 | 4 | 4
Inv ( 2 ) K 10 | 2 | 2
OB-RE HUB
DEC ADJ 37
Cr 19, 95, 96
06/13/11/2021
CR-MinistSHELLIPC08 | 8 | 8
CR IPC#7 Madkour |  | 7
66
Cr-1-2021 | 1 | 1
Credit Memo FPC
Cr. 4 Sugar 33 OHTL
ipc no2 aswan
settlement divedend
Scrap Inv.09/2020 | 9 | 9
2103220003
Libya Eqpt.4 Co.1
10431
DEC ADJ69
Cr.Adj Inv. 18 | 18 | 18
31 EGP-Giza Nor.III
OB-RE-PKG#62
18/13/07/2021
cr7
CR ipc4 aswan | 4 | 4
9-2023 | 2023 | 2023
cr2
OB-MOS-Sodic
CAN. IPC26TR0046 | 26 | 26
kantenRoyalOsman-CR
CR-IPC#8 |  | 8
1044
P-47-EGY تشيد و بناء | 47 | 47
Inv.16 PIP EAST | 16 | 16
ENG 056
Ret. Balance...
01/13/10/2021
Inv 16/2019 Scrap | 16 | 16
Inv. 01 PO 5491 | 1 | 1
close 71
Deduct. inv. 20 EGP | 20 | 20
closing proj. FLR
per closed
11544
CR_INV.10 | 10 | 10
Cr-20-2020 | 20 | 20
Credit Refund
MOC Inv-03 | 3 | 3
Cr. Inv 02 | 2 | 2
CR 11
Cr -7-EGP-West D.117 | 7 | 7
BSF-SW-EGP-12 FINAL | 12 | 12
close60
DEC ADJ 32
10008
11343
DEC ADJ 55
close51
180085
10261
Credit
OB RT 012
Ded inv. 44 WD | 44 | 44
Proj-CR Adj. Inv. 15 | 15 | 15
8 USD - Shabab
final/ closed
DebitNote#12979#
06/13/082021
D.NRailway22-03-2022 | 3 | 3
Close khrafi USD Bal
SCD4/004Cnl
2104210004
IPC-21-SARAY | 21 | 21
1079
Cr. Inv. 27 Usd | 27 | 27
19 EGP - West Domiat
D0024-OB-Dec-2020/Cr | 2020 | 2020
6 Euro-South Helwan
180023
OB002
MIDA Sply. Inv.5 Ret | 5 | 5
470
inv ( 5 ) Baragill B | 5 | 5
inv. 3 USD | 3 | 3
10459
cr-1-9-FEB | 1 | 1
D.M Railway Exp.
271
CR.10-16(2) | 16 | 16
346
Ref.1 samanud-mat T
10225
01/13/06/2021
10140
10007
mos 1 closed
CM 11-19-April- | 19 | 19
SH inv.32 deductions | 32 | 32
15 EGP - Shabab
7
475
Scrap Inv. 08/2022 | 8 | 8
Scrap Inv. 13/2020 | 13 | 13
inv. Ghareeb 98%..
CR.Ref Akhmm Asuit2T
05/13/03/2021-c
Credit Retention
CR.10Ramadan Inv.02 | 2 | 2
Libya Eqpt.1st Co.1
IPC#3# FINAL#TAHYA M |  | 3
opening ba.
468
credit ipc 11 | 11 | 11
D0048 OB-Dec-2020/Cr | 2020 | 2020
284
Inv.5 Deductions | 5 | 5
Cr Adj Inv 5 | 5 | 5
OPEN CHANEL IPC 2 | 2 | 2
EQP-Rent Charges
39 closed
D.m Q2-2022 | 2022 | 2022
2
11661
D.N Insurance JICA--
CR44-2020 | 2020 | 2020
D0042-OB-Dec-2020/Cr | 2020 | 2020
CR-55/1 | 55 | 55
CR.TR0014CLOSING.DEC
OB-ST
CR-Closing #180162
Dm.Rai-EGP22-03-2022 | 3 | 3
ipc05 tr0054 | 5 | 5
018-2020 | 2020 | 2020
CMsewedy uni-mep-07 | 7 | 7
2104220007
Cr.P-14-12 | 14 | 14
1907220004
CR IPC4 elwaraq | 4 | 4
Vat Deduction
Inv. 2 USD | 2 | 2
254
15 closed
Credit inv5 El Tbeen | 5 | 5
252
cr ( inv 5 ) ola | 5 | 5
Ret,OB SharkOenat
SCD4/003Cnl
TR55-CR3
Ret.OB Siemiens
2008220003
10469
Close Khorafi bal.
5 EGP El Sanad Libya
Discount int.
20/13/07/2021
close 33
Refund reten.closing
10113
2012210007
Cancel inv. 7 | 7 | 7
CR 7
OB-Final R
Cr Adj Inv 7 | 7 | 7
CR.p-10-16 | 10 | 10
Close Frequentis Bal
TR055-Cr 1
ipc 8 hsr | 8 | 8
2 EGP - Asuit
2112210002
05/13/01/2022
rev. ( 8 EGP-West D.
Cancel Inv:29 Assuit | 29 | 29
Cr-Sales Tax- 4 invs | 4 | 4
close61
Ins. Egytec
Soc.2020 تشيدسكر 33
CREDITIPC15 | 15 | 15
Inv.12 Fi Sugar OHTL | 12 | 12
Ref.soci 53-54 Asut | 54 | 54
Close Aedco AR Balan
1030
DEC ADJ 89
Cr - 2 USD - Shabab | 2 | 2
close3
Cr.Sadat Indust Inv3 | 3 | 3
Material EES9
K-H.mahmod.ElcoSteel
CR-ODP ipc03 | 3 | 3
Closing Abu quir 118
2104220004
Write off Bemco bal.
02/13/12/2021
10125
CR. 1 Final ElNokra
CR-KAFR SHOKR1
10036
Cr-egy exch Ipc1 | 1 | 1
Vat Deduction Shabab
CR-Kafr shokr-IPC02 | 2 | 2
material ipc 3 | 3 | 3
3-2024 | 2024 | 2024
IPC02TR0099 | 2 | 2
IPC#2#Abo Ghaleb |  | 2
IPC02TR0089 | 2 | 2
IPC01TR00074 | 1 | 1
IPC12TR0064 | 12 | 12
IPC00022 TR41 | 22 | 22
INV ( 9 ) Kemet | 9 | 9
inv ( 4 ) final | 4 | 4
TR0055
ORA PH.1- IPC23 | 23 | 23
Mini Core IPC11 | 11 | 11
K.salim Nov.2022
30/11/22Armed Force
220721002
D.M ORANG
MCBs inv. No.1 |  | 1
Pole. Cvr. Inv.1 | 1 | 1
Selling Scrap Lot17
Selling Scrap Lot15
11459
11448
Scrap Newabaa
Inv. PO 7100088079
IPC#7 - Monorail |  | 7
Dr.adv. Kfr Naser
2110210003
IPC#5 Zamalek |  | 5
IPC_1_R5
Kafr Shokr - IPC02 | 2 | 2
Fayoum Street Inv.01 | 1 | 1
TR0029DEC.Closing
D0043-OB-Dec-2020 | 2020 | 2020
D0044-OB-Dec-2020 | 2020 | 2020
TR0014DEC.Closing
TR0012DEC.Closing
D0022-OB-Dec-2020 | 2020 | 2020
D0011-OB-Dec-2020 | 2020 | 2020
D0023-OB-Dec-2020 | 2020 | 2020
inv. 27 EUR Assuit | 27 | 27
81-Dec-2020 | 2020 | 2020
IPC_3_RedSea
41-2020 | 2020 | 2020
39-Jun-2020 | 2020 | 2020
34- May-2020 | 2020 | 2020
مد وثيقة تامين P-76 | 76 | 76
496
473
24 EGP - AL Shabab
21 EGP - AL Shabab
20 EGP - Al shabab
IPC005 | 5 | 5
50-19 nov | 19 | 19
12 EGP - Suez Gulf
19 EGP VO Progress
41-19 oct | 19 | 19
1903210014
1907210013
1909210010
Inv 2 Almaza City | 2 | 2
5-19-mar | 19 | 19
22/2019 Sample
custom release inv.
reclass of rec acc
180137
14 Egp - Beni Suef
INV 11,12,13 | 11 | 11
tetra-ipc01 | 1 | 1
Soc Inv 44 To 47 Asu | 44 | 44
PKG#85/53- IPC5 | 5 | 5
Cancel Cr no. 227
P-14-12 ADJ | 14 | 14
P-13-2016 ADJ | 13 | 13
5007 ADJ
180097
180160
DM for wrong CR
14 EGP- West Domiat
180159
5 USD - West D. 117
180101
Debit Note #7 Wukair
9 EGP- Shabab
3 EGP - Cement
Adj. Inv. 13 | 13 | 13
Adj. Inv. 12 | 12 | 12
Adj Inv 11 | 11 | 11
Adjust
180128
Inv 92 P14 Assuit | 92 | 92
Inv. 1 S1 | 1 | 1
Scarp inv.4/2018 | 4 | 4
17
180114
29
180027
115
102
72
92
86
25
80
180091
76
43
46
NPV of attaqa
Closing STF Balance
5+ EGP / STF(Italy)
15-3 EGP / STF ( Ita | 3 | 3
15-2 EGP / STF (Ital | 2 | 2
1 EGP - Asuit
Scrap - inv
Inv. 9 Akhmem Qena | 9 | 9
Inv 7 Abo Zaabl | 7 | 7
Soc73 abo almatamer
4-132KVA-H | 132 | 132
Balance Electro
nfinal kobry el3asma
22 newgiza 1
mos 4
mos 2
2 Elegict
4 EGP - West D. 117
Angola 2
10007
Mozabique
5
ADJ RECEPIT
4 USD/123/2011/2012
18
22
015/2019
Civil/H010
Other Charge/H003
Other Charge/H002
32-132KVA-H | 132 | 132
4-132KVA | 132 | 132
Adv. Balance 4
Aply Advance Memo
539
180093
18 EGP - West D. 117
10 USD - Shabab 117
2 USD - West D. 117
9 EGP - Suez Gulf
5 USD/123/2011/2012
Inv. 58 Wadi 17 | 58 | 58
26 Wadi 7
33 maghagh 9
Inv. Barwa 36
Barwa 32
Inv 20 Barwa | 20 | 20
29
9 barwa
Barwa 17
Inv. 34 Damac | 34 | 34
7 Damac
(3)CW elmostsmrin |  | 3
(2)SD elmostsmrin |  | 2
3 Euro- South Helwan
9 EGP - South Helwan
7 EGP South Helwan
437 EGP abu qeir 118
436 USD Avice ZTPC
9 EGP - West D. 117
2 EGP - East Delta
24
439 USD Avice ZTPC
1068
3914
11 Euro-South Helwan
Balance Adv. Feb17
inv(ESC-SA-Civil-04) | 4 | 4
Aply advance -Memo
(15)new giza2 |  | 15
7 ًWadi
Moz-inv.2-local | 2 | 2
Moz-inv.1-local | 1 | 1
Final-inv.
close unappl.sak
(16) bani suf 2 |  | 16
10048
BSF-CW-EURO-07 | 7 | 7
ISE-CW-EGP-18 | 18 | 18
TAM-SW-EGP-09 | 9 | 9
TAM-CW-EGP-14 | 14 | 14
BSF-CW-12 | 12 | 12
BSF-CW-11 | 11 | 11
Social 35 Wadi 9
38 Asuit 1
Adv. Balance 6
16
Soc. Inv 39 Bnha 7 | 39 | 39
remain(3 Euro-Iskrae
180116
Adv. Balance 7
10043
Inv.20 Ghelion | 20 | 20
(25)new giza 2 |  | 25
Inv 41 Giza I,II | 41 | 41
31 EGP - Giza N. III
Inv. 18 Oewon Mousa | 18 | 18
Inv. 5 Oewon Mousa | 5 | 5
Inv. 4 Oewon Mousa | 4 | 4
Barwa 15
close un appl. avice
10042
Inv No6 Wattanya220 | 6 | 6
Inv. NO.9 KWT Floor |  | 9
(3)PKG#62 |  | 3
(12) BENI SUIF1 |  | 12
(2)shobra/banha |  | 2
Inv. 6 | 6 | 6
socil 47 banha 10
Inv.54 Assuit 2 | 54 | 54
Inv No 2 Suez Gulf | 2 | 2
OB C3
Close Old Adv
11 USD - West Domiat
beni suif 2 (1) |  | 1
2009210010
1905210001
1902210004
(3) Kanteen |  | 3
(4) Kanteen |  | 4
Apachi Inv No PC,21
Apachi Inv No P.C#20 |  | 20
OB-SI-New Giza 1
19100047
Adjusr Power advance
كانتين
Inv.59 Assuit 4 | 59 | 59
Inv Rent Abu quir
1-132KVA-H | 132 | 132
10186
10010
10009
Soc. 26 Asuit 5
Inv 64 P6 Assuit | 64 | 64
10488
10309
10289
10285
alloccation ipc10 | 10 | 10
mohamed aly ipc06 | 6 | 6
Inv.1 Quna Akhmem | 1 | 1
refund CSI - SH
120/5/6/2017
(8) pkg#62 |  | 8
36/P/10/ER/2017/USD
Inv 97 P14Abo Matami | 97 | 97
Inv 91P11Abo Matami | 91 | 91
Inv. 7 Elkayan | 7 | 7
Inv. 25 Badr | 25 | 25
10291
Soci.1/2-68/71matamr | 68 | 68
K(mostafa mohamed)2
(3)cw beni suif |  | 3
15EGP/on-shore train
20sd elmostsmrin
MIN.ELECTRO-IPC01 | 1 | 1
2108210006
2108210002
1905210008
1908210003
12503
Inv.48 Borg Alarab | 48 | 48
10310
k-m.khalifa-ministre
Soc 3 samanod
Refund 31/13/5/2018
Inv. No.12 KWD Floor |  | 12
10352
203
19100015
new giza2 vo-ipc1 | 1 | 1
ELKAYAM MEP-IPC (2) | 2 | 2
12 sd euro mostsmrin
10954
10705
10638
MIN-OLD-IPC05 | 5 | 5
Apachi Inv No PC.#27
Green power balance
k-m.mansour-kayan
k-m.khalifa elco jul
Insurance Refund
soc 12 siemen assuit
Inv.15 Assuit Akhmem | 15 | 15
Inv 1 VO SG | 1 | 1
IPC8-ROYAL CITY | 8 | 8
34-132KVA(8J) | 132 | 132
33-132KVA(8H) | 132 | 132
Inv.8 Qena - Akhmem$ | 8 | 8
Inv. 40 Akhmem Qena | 40 | 40
Inv. 16 Balat lot 3 | 16 | 16
m.m.kanteen kayan
Inv.6 Assuit Akhmem$ | 6 | 6
R05-ZONE01-IPC03 | 3 | 3
10509
scrap/inv.04 | 4 | 4
Socil 8 Samanood 90
Inv.30 Assuit Akhmem | 30 | 30
soc 17-18 assuit akh | 18 | 18
Inv. 41 Akhmem Qena | 41 | 41
Inv.29 Akhmem Qena | 29 | 29
soc 30-32 quna akhmi | 32 | 32
Inv.3 Borg Alarab | 3 | 3
DM 6 Borg Alarb
Cancel1
4 EGP - Lina
K-KAYAN110-M.MANSOUR
Inv.1 RCC | 1 | 1
10527
10493
TAM-CW-EGP-07 | 7 | 7
MOS-SD-EGP-21 | 21 | 21
ROYAL ZONE-IPC09 | 9 | 9
10530
Soc33-40Quana Akhmem | 40 | 40
ISMAILIA BLAJT-IPC03 | 3 | 3
180147
Soc22-28Asuit Akhmem | 28 | 28
Ref Ret. Inst 2 Asut
PKG#53-IPC-36 | 36 | 36
Inv13 Usd borg alarb | 13 | 13
CON/029
IMP/066
CON/019
Loc-009 | 9 | 9
IMP047-39 | 39 | 39
Con/009
10137
10411
Inv. 9 Borg Alarab | 9 | 9
Inv. 10 Heliopolise | 10 | 10
TAM-SW-EGP-02 | 2 | 2
PKG#144 -IPC3 | 3 | 3
PKG#101 - IPC07 | 7 | 7
PKG#101-IPC-01 | 1 | 1
61/13/12/2018
215
19100002
19100017
OB007
DP WORLD -IPC10 | 10 | 10
DP WORLD-IPC008 | 8 | 8
DP World IPC030 | 30 | 30
DPW IPC027 | 27 | 27
(1) shobra/banha |  | 1
ref. reten.zafra gha
Ras ghareeb Final ci
Soc Inv 34To37 Asuit | 34 | 34
Soc Inv 20-21 Asuit | 20 | 20
K-A.Osman-ismlia-Jan
K-M.Khlefa-ministrie
K-H.Mansour-SwedyUni
MINISTRIY SHELL-IPC1 | 1 | 1
IPC#10 |  | 10
K-H.Mansor-elsewdyun
K-A.Osman-Royalcity2
PKG#140 - IPC03 | 3 | 3
PKG#140-IPC01 | 1 | 1
1901210009
Social 11 Samanood
K-A.osman-royalcit-3 | 3 | 3
Inv. 8 Eltbeen | 8 | 8
MIN-SHELL-IPC06 | 6 | 6
SUEZ ROADL&L- FINAL
PKG#144 -IPC06 | 6 | 6
10784
10598
Inv.6 - Lot 1 | 6 | 6
IPC#19 |  | 19
K-M.khlifa-minis-04 | 4 | 4
hassan alam-ipc2/323 | 2 | 2
Benban Lot 2 Inv. 11 | 11 | 11
Benban Lot 2 Inv. 2 | 2 | 2
Benban Lot 1 Inv. 2 | 2 | 2
Benban Lot 1 Inv. 7 | 7 | 7
Benban Lot 1 Inv. 3 | 3 | 3
10704
10699
kanteen-ismaliaa-May
PKG#53 -IPC38 | 38 | 38
Inv. 5 Scrap 2019 | 5 | 5
Inv 14/2019 Scrap | 14 | 14
11001
1903210011
1901210003
Inv.6 Phosfat II | 6 | 6
Electric-kayan-May05
coll of beni suef ga
IPC#20 |  | 20
Benban Lot1 Inv 8USD | 8 | 8
Benban Lot1 Inv12USD | 12 | 12
Benban Lot1 Inv 7USD | 7 | 7
Social 44-47 Assuit | 47 | 47
Benban Lot 2 Inv. 1 | 1 | 1
Close 23180.35/shipp
Civil5 to Shipp 5
Inv.41 Deductions | 41 | 41
Elkayan Inv.17 | 17 | 17
Water-invoice-Kayan
Kanteen-Kayan110July
Inv 85 P6 Sammound | 85 | 85
10971
10760
Compensation natron
8/13/08/2019
020/2019
254
238
241
1908210006
5 EGP - Suez Steel
2*3 EGP - Suez Steel
2*1 USD - Suez Steel
253
10950
INV ( 13 ) 22-10-20 | 13 | 13
inv ( 19 ) 7-12-2020 | 19 | 19
Inv.2,3,4,Zmb.VAT | 2 | 2
minist allocat ipc09 | 9 | 9
MANGOROVE-IPC01 | 1 | 1
Benban Lot 1 Inv. 8 | 8 | 8
20100002
10543
10756
DP WORLD-IPC07 | 7 | 7
Ref. Ret. itay 358
Soc.Inv. 48 Qena | 48 | 48
Soc.Inv. 50 Assuit | 50 | 50
Inv. 17 Farm | 17 | 17
Inv. 16 Farm | 16 | 16
Inv. 05 Farm | 5 | 5
Benban Lot1 Inv 5USD | 5 | 5
10999
11121
HYPER ONE-IPC12 | 12 | 12
HYPER ONE-IPC11 | 11 | 11
21 EGP VO CCC Instal
Benban Lot1 Inv 9USD | 9 | 9
Benban Lot1 Inv11USD | 11 | 11
Inv 3 Asec Sparepart | 3 | 3
10-sales
Benban Lot 2 Inv. 17 | 17 | 17
10993
10247
10955
10994
Kanteen-R05-Oct-2019 | 2019 | 2019
270
ELMOUSTQBAL -IPC 01 | 1 | 1
Kanteen-olympc-Nov19
1-Camama
R5-ZONE2-IPC08 | 8 | 8
10307
60-19 Dec | 19 | 19
E.S.U 2-ENABLE-IPC06 | 6 | 6
Benban Lot 1 Inv. 14 | 14 | 14
Benban Lot 1 Inv. 19 | 19 | 19
Tunnel Inv. 5 | 5 | 5
Tunnel Inv. 1 | 1 | 1
Scrap2 Inv. 32/2019 | 32 | 32
12-sals
Kanteen-R05-Nov-2019 | 2019 | 2019
Kanteen-ismlia-Dec19
27-19Aug | 19 | 19
SUEZ ROAD L&L-IPC01 | 1 | 1
485
482
10831
- 664.41 | 664 | 664
10997
1901210014
493
1908210004
1907210012
1906210002
1901210007
Scrap Lot. 15
73-19 Dec | 19 | 19
JPSS/018
50-19-nov | 19 | 19
Toshka Lot 4 Inv .16 | 16 | 16
Toshka Lot 6 Inv .20 | 20 | 20
Toshka Lot 6 Inv .13 | 13 | 13
CFC-IPC08 | 8 | 8
CFC - IPC05 | 5 | 5
291
180156
24/2019 Scrap
Soc 49 Quana
10390
MP-11 | 11 | 11
Refund Ret.Port Said
LEKELA-IPC06 | 6 | 6
LEKELA-IPC01 | 1 | 1
11022
11028
9 Jan 2020
Kanteen-Sodic-Jan-20 | 20 | 20
Toshka Sub Inv. 07 $ | 7 | 7
10213
IPC08/PO52/323 | 8 | 8
MANGROVE RENT-IPC02 | 2 | 2
11019
IPC#1 |  | 1
Kanteen-Olymp-Mar-20 | 20 | 20
Kanteen-Uni-Mar-2020 | 2020 | 2020
10020
2003210002
Inv. 21 Badr | 21 | 21
3
ELHEGAZ2-IPC1FINAL | 1 | 1
PKG#163 - IPC011 | 11 | 11
PKG#163-IPC08 | 8 | 8
10032
MIN -CORE- IPC03 | 3 | 3
314
312
14 feb 20
10039
Inv.71 Borg Alarab | 71 | 71
Benban Lot 1 Inv. 31 | 31 | 31
18/13/06/2020
Marsa Alam EGP Inv 2 | 2 | 2
11361
E.S.U2- IPC 05 | 5 | 5
10036
Inv. 2 Balat lot 3 | 2 | 2
2003210009
Re. Soc Inv 1 Temay | 1 | 1
10526
ROYAL CITY-IPC29 | 29 | 29
15 feb 20
21- Mar 20
Kanteen-R05-APr-2020 | 2020 | 2020
2005210004
10196
Inv.10 Sugar OHTL | 10 | 10
33 - Apr 20
Suez S4 Inv. 03 | 3 | 3
27 Mar 20
26 Mar 20
34-MAY-2020 | 2020 | 2020
31 - Apr 20
Kanteen-Uni-April-20 | 20 | 20
Kanteen-Olymp-Apr-20 | 20 | 20
ISE-CW-EGP-23 | 23 | 23
Al - Jazi Inv. 1 | 1 | 1
MIN CORE - IPC04 | 4 | 4
11504
42/P/10/ER/2017/USD
11184
OB 3924
2006210004
24-2020 | 2020 | 2020
IPC_12_rowad_s_east
2003210004
455
IPC#6 |  | 6
10803
1
R5(2) IPC 52 | 52 | 52
R05(2) ipc45 | 45 | 45
R05(2) ipc 31 | 31 | 31
IPC#7 |  | 7
Ref Retention.Matroh
TAM-CW-EGP-22 | 22 | 22
PKG#140-IPC15 | 15 | 15
IPC_4_Gama_Saray
Kanteen-Sodic-2020 | 2020 | 2020
10067
10033
Toshka Farm Inv. 03 | 3 | 3
Cairo-Alex ipc 40* | 40 | 40
11102
Kanteen-Kayan-Apr-20 | 20 | 20
Kanteen-(M&D)-Sep-20 | 20 | 20
Kanteen-(M&D)-Oct-20 | 20 | 20
reclass PA Inv.
Inv.23Usd borg alarb | 23 | 23
10303
IPC_3_RedSea_Ministy
FPC
ora ph1 ipc (27) | 27 | 27
ORA ZED1-IPC03 | 3 | 3
IPC-05- PKG#85/53 | 5 | 5
IPC_5_Rowad_M.Ali
ENG/033
71-Oct-2020 | 2020 | 2020
Car Sales 369
Car Sales 318
MIDA Ins. Inv.1 | 1 | 1
2008210004
2000001
ESU2-MEP-IPC10 | 10 | 10
LEKELA-SUPPLY-IPC01 | 1 | 1
Toshka Sub Inv. 01 | 1 | 1
Kantin-Kayan-Nov-20 | 20 | 20
Kantin-Sodic-Nov-20 | 20 | 20
Ref.Ret.Installation
Kayan110
Toshka Sub Inv. 16 $ | 16 | 16
11761
Cre.adv.Toshka 4
inv ( 12 ) | 12 | 12
2011210004
2011210003
Inv 8 Zambia man1 | 8 | 8
Inv. 8 Oewon Mousa | 8 | 8
11842
Toshka Lot 4 Inv $7 | 7 | 7
Inv.07 Sugar OHTL | 7 | 7
Reailway PSP Inv. 02 | 2 | 2
52-2020 | 2020 | 2020
Re.Inst Asuit Akhmem
sewedy-un-1 | 1 | 1
Al-Lahoon Sub Inv 04 | 4 | 4
Al-Lahoon Sub Inv 01 | 1 | 1
SHOROUK L&L-IPC01 | 1 | 1
ISE-CW-EURO-03 | 3 | 3
Acroket Company - 02 | 2 | 2
Acroket Company
3-2021 | 2021 | 2021
LOC/012
11822
397
2007210002
IPC_8_Gama_17-18 | 18 | 18
4
2012210005
Ministries - 2 | 2 | 2
تخليص جمركى pkg#162
Inv. 1 S1 | 1 | 1
IPC_7_Saray_Gama
EGAT IPC01 | 1 | 1
11863
IPC#1` |  | 1
9-2021 | 2021 | 2021
wight - 3 | 3 | 3
P-45-Portsaid Inv.03 | 3 | 3
2103210001
Scrap Inv. 04/2021 | 4 | 4
2101210004
2103210018
Soreal - 3 | 3 | 3
Kayan 110 - 3 | 3 | 3
ENG-036 | 36 | 36
11946
11883
11805
12062
R5 FINSHING-IPC10 | 10 | 10
2102210005
IPC_5_ORA
10522
2103210017
10482
10525
2103210006
م.ك Inv.01 PO. 229 | 1 | 1
JV-AC-EE-Inv-004 | 4 | 4
200201
200185
PKG #177 IPC08 | 8 | 8
MIDA Sply. Inv.6 | 6 | 6
Scrap Sales El-Doha
405
IPC005 - Mdkour | 5 | 5
2105210011
Inv.2 - Lot 1 | 2 | 2
Ref.Ret Asuit akh 2
2105210015
Mangroovy - IPC016 | 16 | 16
200200
Tunnel Inv. 10 | 10 | 10
11952
Mansoura IPC 14 | 14 | 14
R5 ZONE1-IPC09 | 9 | 9
MIN ELCTRO-IPC04 | 4 | 4
12322
11947
CON/020
CON/022
Toshka Lot 4 Inv .24 | 24 | 24
418
Inv. 12 Farm | 12 | 12
Inv. 13 Farm | 13 | 13
Kayan-May-Jun21
Sultana Malak IPC02 | 2 | 2
10625
37
IPC-5-PLAYA | 5 | 5
12364
412
ENG/041
12446
2105210013
Toshka Lot4OH Inv.04 | 4 | 4
Ora ph2 ipc 26 | 26 | 26
ipc16 ora zed(2) | 16 | 16
ora ph.1 - IPC20 | 20 | 20
Ora ph.2 - IPC13 | 13 | 13
Ora ph.2 - inv. 11 | 11 | 11
Air Force Inv . 10 | 10 | 10
Air Force Inv . 03 | 3 | 3
12522
12523
12362
Kanten R05 AUG/2021
Compensation B & D2
IPC#3 - Mansoura |  | 3
Maryotia IPC08+ | 8 | 8
Kafr Shokr IPC05 | 5 | 5
30/13/08/2021
IPC-FINAL-PKG#144
45
Inv (1) PBadr | 1 | 1
Inv. No.1 MRT Supply |  | 1
Inv.13 – Lot 2 | 13 | 13
Inv.12 - Lot 2 | 12 | 12
Kanten Sodic Sep 21
25-2021 | 2021 | 2021
IPC#5 - Additional |  | 5
23
Mngrovy Final IPC018 | 18 | 18
MDF IPC03 | 3 | 3
11545
Ras El Teen IPC01 | 1 | 1
ELSEWEDY HQ IPC07 | 7 | 7
Ref.Ret Asuit akh 3
11022
434
11026
21000006
2107210002
Kanten ORA Zed NOV21
Kanten Kayan NOV/21
Ret Qen-akh 6 T
Ref.Ret Qen-akh 6
Ret Asuit akh 5 T
Cairo-Alex IPC012 | 12 | 12
01/13/12/2021
11002
INV ( 11 ) GET | 11 | 11
INV ( 8 ) GET | 8 | 8
Inv ( 2 ) Sentor | 2 | 2
INV ( 3 ) Ring R | 3 | 3
518
EGAT IPC07 | 7 | 7
Air Force Inv . 20 | 20 | 20
IPC#03 - Sokhna Brid |  | 3
Ref-Ret-Assuit $ T
466
رد تامين اخميم قنا
رد تامين اخميم قنا 2
11202
Kafr Shokr_IPC01 | 1 | 1
T 1-2022 | 2022 | 2022
IPC#4 - Sokhna Bridg |  | 4
Railway IPC07 | 7 | 7
t 2-2022 | 2022 | 2022
446
Ref-Ret-benban 2 $ T
12911
11344
7-2024 | 2024 | 2024
450
436
12932
11345
Maryotia IPC014 | 14 | 14
k-mostafa0mar22
T 8-2022 | 2022 | 2022
Selling Scrap Lot 4
Selling Scrap Lot 7
11163
Selling Scrap Lot 8
inv ( 1-2-3 ) Hayper | 1 | 1
MIDA Sply.inv.11 | 11 | 11
Ret Quana akh USD T
South Valley Inv. 13 | 13 | 13
k-ali-mar22
IPC-4-GOUNA | 4 | 4
IPC-2-NEW GIZA | 2 | 2
11426
Ref Ret Samanod& mat
65
220421004
12973
11501
11446
Dry Port Inv. 07 | 7 | 7
MDF FACTORY2 IPC04 | 4 | 4
PKG#189 IPC 29 | 29 | 29
MIDA Ins.inv.12 | 12 | 12
IPC-8-PLAYA ROOF | 8 | 8
EGAT WaterTank IPC07 | 7 | 7
ENG/054
mansora finish ipc17 | 17 | 17
Dry Port Inv. 09 | 9 | 9
Marsa Alam EGP Inv14 | 14 | 14
Ora Landsape ipc 21 | 21 | 21
Ora Landscape ipc 15 | 15 | 15
IPC#5 ElHammam |  | 5
Hosh Essa Inv. 09 | 9 | 9
Hosh Essa Inv. 10 | 10 | 10
hasan Mamoun 2 Final
200667
220621001
sokhna bridge ipc02 | 2 | 2
inv ( 2 ) fainal | 2 | 2
Ref-Ret-Toshka Lot4T
Ref.Abu Quir Badr-T
200608
200647
Toshka Lot 6 Inv .28 | 28 | 28
475
471
IPC-1-PK177-Waterpro | 1 | 1
pkg#178 ipc08 | 8 | 8
Ro5 (2) ipc 20 | 20 | 20
12
IPC020 | 20 | 20
sultana malak2 ipc01 | 1 | 1
pkg#163 ipc 23 | 23 | 23
pkg#163- IPC24 | 24 | 24
kattamya ipc17 | 17 | 17
Supply SSC IPC 4 | 4 | 4
I&RSUPPLY (ABB) IPC5 | 5 | 5
In&ReSupply ABB-IPC2 | 2 | 2
int&ret app(ssc)ipc5 | 5 | 5
200687
TR0046/1
TR0039-IPC0039 | 39 | 39
200646
13
k-salim aug2022
kantine 2
العناصر المائية ipc4 | 4 | 4
INV (3 ) AL Mansorya | 3 | 3
K-ALI SEP2022
IPC#4 ELHammam |  | 4
Ora ph.2 ipc10 | 10 | 10
IPC#3 ElHammam |  | 3
pkg#140 ipc27 | 27 | 27
SHELL IPC09 | 9 | 9
Rolling Mill IPC8 | 8 | 8
MDF Factory3 IPC5 | 5 | 5
IPC#8 Assuit |  | 8
ismalyia ipc28 final | 28 | 28
200728
sokh.port roads ipc1 | 1 | 1
Cr.INV ( 14 ) GET | 14 | 14
IPC00024 | 24 | 24
IPC#023 |  | 23
cairo - alex ipc 30 | 30 | 30
k.Hassan Nov.2022
IPC#22 |  | 22
URBIN-K IPC 10+ | 10 | 10
IPC#5 HSR |  | 5
Inv ( 9 ) sixty | 9 | 9
Kayan IPC4 | 4 | 4
seashell playa-IPC1 | 1 | 1
Revamp ipc 9 | 9 | 9
Revamp ipc (3) | 3 | 3
Revamp IPC1 | 1 | 1
Airdevance7 IPC1 | 1 | 1
IPC0000000015 | 15 | 15
ORA ZED1-IPC04 | 4 | 4
R.O. Supply-IPC3 | 3 | 3
IPC#00005 |  | 5
L&L IPC10 | 10 | 10
inv ( 5 ) Kemt | 5 | 5
IPC000018 | 18 | 18
200806
26
IPC002 TR60 | 2 | 2
Olym Fire IPC1 | 1 | 1
IPC0000005 | 5 | 5
IPC0000010 | 10 | 10
Kayan MEP IPC fin
R05(2) ipc 32 | 32 | 32
EL MAHAGER IPC 01 | 1 | 1
Hst Culverts ipc 01 | 1 | 1
ipc14 mdf factory2 | 14 | 14
R.Osup Pri ADJ. IPC1 | 1 | 1
200805
Dp world ph2 ipc 11 | 11 | 11
dp world ipc(7=8) | 7 | 7
Egat Mep Mobili ipc4 | 4 | 4
wady el natroon ipc2 | 2 | 2
HST CULVERTS IPC 2 | 2 | 2
inv ( 1 ) sixty | 1 | 1
R.O(5000:8000)SIPC.4
K-SALIM M DEC.2022
Oly elec IPC1 | 1 | 1
T 9-2022 | 2022 | 2022
R.O 5:8 APPLY IPC 1 | 1 | 1
R.O - supply ipc 2 | 2 | 2
El-Marg IPC06 | 6 | 6
playa c-204 ipc 1 | 1 | 1
IPC 1/2 CFA | 1 | 1
Olympic Hall IPC03 | 3 | 3
200952
200814
FPC Zamalek
IPC 2 PVD | 2 | 2
IPC05TR0066 | 5 | 5
200878
IPC04 TR64 | 4 | 4
Alamein sahely IPC1 | 1 | 1
Egat Mech Equip ipc2 | 2 | 2
playa c045- ipc 3 | 3 | 3
IPC0001TR65 | 1 | 1
230000008
IPC0023 TR41 | 23 | 23
IPC008 TR55 | 8 | 8
IPC 008 TR0055 | 8 | 8
INV ( 4 ) Central Ca | 4 | 4
spx.2 ipc 01 | 1 | 1
cairo-alex ipc 41* | 41 | 41
cairo-alex ipc15 | 15 | 15
EGAT L&L IPC8 | 8 | 8
EGAT MEP- IPC3 | 3 | 3
EGAT MEP-IPC 1 | 1 | 1
230000001
TAH ipc 01 | 1 | 1
IPC017 TR46 | 17 | 17
ipc00016 tr46 | 16 | 16
pkg#220-ipc2 | 2 | 2
Playa -c234 ipc (2) | 2 | 2
playa-c234 ipc (3) | 3 | 3
Playa-c038 ipc (3) | 3 | 3
Playa -c072 ipc (2) | 2 | 2
IPC24 TR41 | 24 | 24
IPC0019 TR46 | 19 | 19
GIG-Hisham Ibrahim.
k-salim sep.2023
IPC 24 GOV2 | 24 | 24
Rent 1st+2nd madi 9
IPC01TR0076 | 1 | 1
IPC01TR0075 | 1 | 1
Olympic Finish IPC6 | 6 | 6
Minis alloc IPC13 | 13 | 13
IPC(1) / PO27078 | 1 | 1
IPC06-DEXTRA | 6 | 6
201031
Baraka Fance ipc 3 | 3 | 3
inv ( 1 ) Baragill B | 1 | 1
IPC04TR0061 | 4 | 4
IPC12 TR51 | 12 | 12
IPC02TR0074 | 2 | 2
IPC07TR0066 | 7 | 7
ipc no3 elwaraq
k-hassan Jan.24
spx.2 ipc5 | 5 | 5
sultana IPC final
sokhna bridge ipc16+ | 16 | 16
201054
wady elnatron ipc06 | 6 | 6
IPC013 TR0053 | 13 | 13
IPC0015TR0053 | 15 | 15
tr0054
IPC004 TR0044 | 4 | 4
IPC06TR0077 | 6 | 6
IPC13TR0064 | 13 | 13
IPC#Final#Leaaba
fence western ipc 1 | 1 | 1
IPC04TR0088 | 4 | 4
Inv ( 1 ) K 10 | 1 | 1
K0001
IPC#004 |  | 4
24000006
Emaar Pkg#205 ipc6 | 6 | 6
IPC19TR0055 | 19 | 19
katamya Urbn-k ipc10 | 10 | 10
IPC07TR0062 | 7 | 7
k-hassan mar.24
HQ final ipc 26 | 26 | 26
PORT SAID IPC25 | 25 | 25
IPC24TR0046 | 24 | 24
IPC17TR0053 | 17 | 17
Katameya Creek ipc38 | 38 | 38
INV 4 | 4 | 4
INV 6 | 6 | 6
IPC09TR0061 | 9 | 9
IPC20TR0055 | 20 | 20
201393
IPC01TR0086 | 1 | 1
Eagt Mechnical ipc 5 | 5 | 5
IPC13TR0060 | 13 | 13
Rent-003 | 3 | 3
Spx.2 (7) part2 |  | 7
Sokhna bri esc.20+21
Inv-03 | 3 | 3
IPC05TR0079 | 5 | 5
IPC25TR0046 | 25 | 25
Baraka Fance ipc 4 | 4 | 4
RME-RS inv.1 | 1 | 1
Ednc saudi ipc 1 | 1 | 1
IPC08TR0071 | 8 | 8
K-ABDELWAHAB.AUG.24
MDF Factory ipc 40 | 40 | 40
Gig-Osama Mahmoud
201311
201298
katamya Creeks ipc42 | 42 | 42
K-HASSAN.9-24 | 24 | 24
Rent 8-2024 | 2024 | 2024
201433
201372
Spx.1 esc.13:23
IPC03TR0093 | 3 | 3
IPC08TR0088 | 8 | 8
144-canteen
5-2024 | 2024 | 2024
IPC01TR0101 | 1 | 1
ELSEWEDY HQ-IPC03 | 3 | 3
K0003 Inv 01 | 1 | 1
IPC10TR0059 | 10 | 10
IPC08TR0074 | 8 | 8
201453
INV no.10 | 10 | 10
IPC no14
inv ( 2 ) W. Natron | 2 | 2
Playa C470- ipc 7 | 7 | 7
inv (13 ) Captal one | 13 | 13
mansora finish ipc27 | 27 | 27
ADJ
102
Forex
180068
Vat Deductions WD
Refund LG Fees
Material EES8
16 EGP - Shabab
4
CR-(7/8/12)EGP-Domia | 7 | 7
cr 41-19 oct | 19 | 19
1 EUR Cameron
Al-Lahoon Sub Inv +1 | 1 | 1
close AR Invoice
CR(3_p.o52/156
Cr,Inv.7 | 7 | 7
تشيد سكر خط 220
cr16
Dividend Discount
Cr. Adj Inv. 13 | 13 | 13
SH Inv other ded.
CAN.CR
cesd44
CR-IPC#3 |  | 3
2 EGP - West Domiat
opening.balance
Rev (9 USD Shabab)
Ret.OB Galalah
10695
1 dzd
34
10168
59
272
final;
10381
DEC ADJ 31
Marsa Alam USD Inv 6 | 6 | 6
close 57
02/13/11/2021
12994
Al-Lahoon Sub Inv +3 | 3 | 3
D0019-OB-Dec-2020/Cr | 2020 | 2020
close9
Adjust march PV
10347
OP 7
INV ( 6 ) Central Ca | 6 | 6
Inv Q4 | 4 | 4
8 EGP- Suez Gulf
10539
15 EGP - West Domiat
IPC_7_Mivida
13/13/11/2021
ipc 23+24 elsokhna | 23 | 23
10482
DEC ADJ 25
cr-wad halfa ipc05 | 5 | 5
P-45-EGY اتحاد تشيد | 45 | 45
D0043-OB-Dec-2020/Cr | 2020 | 2020
cr-ORA PH.1-IPC23 | 23 | 23
50 - JUL-2020 | 2020 | 2020
D.m Orange Invoice
43 closed
cancelHSR oct-5 | 5 | 5
OB RT 013
CR.TR0018CLOSING.DEC
close39
CR 9 EGP-South Helw
44
Amortization of PV
246
CR.TR0019CLOSING.DEC
Refu.retention
CR.IPC_4_ORA
CR-Kafr ShokrIPC01 | 1 | 1
OB-RE-Mall Of Egypt
11451
cr 3cw
Scrap Inv. 05/2020 | 5 | 5
12467
Scrap Inv. 03/2020 | 3 | 3
CR-36 EGP-GizaN.I&II | 36 | 36
Trans.usd toegp
Alstom bank fees
Deb Note no7 wukai
Other Revenue East
OB-RE 6
IPC26TR0046.. | 26 | 26
ESS1000
Deduct Customes 32
8
IPC#4#Kilo 21 |  | 4
crsd1
OB RT 014
Soci.1 To12 Mousa358
Eng Stamps
cr-oct.tunnel ipc2 | 2 | 2
Cr. Adj Inv. 17 | 17 | 17
cr.egy ex awnash 2fi
62
220222001
Cr.So12-16 assui | 16 | 16
cr63-19Dec | 19 | 19
DEC ADJ 4
09/13/03/2022
Vat receipts
1123
Zayed Monorail Inv.1 | 1 | 1
1051
227
P-32-EGY اتحاد تشيد | 32 | 32
Balance Feb2017
208
D.M Office Exp.Mar21
D0030-OB-Dec-2020/Cr | 2020 | 2020
Invoice 23 (10) | 23 | 23
P-11-EGY اتحاد تشيد | 11 | 11
remaining of 1.5% JV
OB-ST3
close 50
CR_80
CR-3-9-MAR | 3 | 3
Cr Ora ph1 ipc(22) | 22 | 22
10227
92
10128
DEC ADJ 53
7 EGP-(VO) adjust.
Cancel Inv: 4 Cras | 4 | 4
Hosh Essa USD Inv.02 | 2 | 2
Final El Niger
13075
024/2020cncl
180033
Feb Balance
CR40-2020 | 2020 | 2020
CR_Inv 81 | 81 | 81
Close Orascom AR Bal
Inv.52 Qena Akhmem | 52 | 52
Ret.OB Barwa
CR - 20 EGP - Shabab | 20 | 20
87
cr k-ahmedapril.2023
CR - Scrab
inv no2.2 d0079 | 2 | 2
DEC ADJ 57
cr material on site
Scrap Inv. 12/2022 | 12 | 12
D0035-OB-Dec-2020/Cr | 2020 | 2020
Close Zaafarana
51
2008210002
Ref.soci 51-52 Quna | 52 | 52
9/2
Cancelling wrong inv
DEC ADJ 91
04/13/11/2021
cr VAT 2 PKG107
Suez S4 Inv. 19 | 19 | 19
OB-RE-New Giza 2
playa inv.dec.23
cr-mdfipc07 | 7 | 7
CRINV(14) 28-10-20 | 14 | 14
cr 63-ٍSEP-2020 | 2020 | 2020
CM RME-2019 | 2019 | 2019
CR_inv.5 | 5 | 5
INV ( 10 ) Ring R | 10 | 10
Cr.Memo-Expenses
DEC ADJ 40
11452
1075
CR.Ret Zafra-B-Suef
11582
IPC00000010 | 10 | 10
Cr.P 161
Scrap Inv. 16/2020 | 16 | 16
13112
180019
CR - Customs
P-30-18 تشيد و بناء | 30 | 30
Reclass Debit Note#7
10-6-2023 | 6 | 6
JICA lot 02 Inv.$ 02
test
cr-Bis ipc (2) | 2 | 2
IPC17TR0048 | 17 | 17
OB Retention 3
DEC ADJ 20
Cancle13-12-2018 | 12 | 12
89
تشيد بنبان لوط 1
MOC Inv-02 | 2 | 2
CR CW
DEC ADJ3
99
2007220004
Cancel invoice Lot18
05/13/03/2021
57
CR.P-27-09 AccRev | 27 | 27
OB Retention 2
cr33
10328
32/13/2021
D0036-OB-Dec-2020/Cr | 2020 | 2020
41
Cr. Adj Inv 14 | 14 | 14
CR.TR0005CLOSING.DEC
486
CR. D.M ORANG
180076
Cr-S.Tax- 6 invoices | 6 | 6
Cr.Inv. 11 Heliopols | 11 | 11
close19
P-12-EGY اتحاد تشيد | 12 | 12
2104220003
10035
256
DEC ADJ 61
CR-VAT for USD inv
OB-ST-EL WAHAT
DEC ADJ 78
inv ( 1 ) R.EL Monib | 1 | 1
D.N 16-06-2021 | 6 | 6
rent-005 | 5 | 5
D.m Q1-2022 | 2022 | 2022
8 Euro-South Helwan
2004220005
12382
CR 2-2021 | 2021 | 2021
12928
CR-18 EGP-West Domia | 18 | 18
clos9
CR#10 WADY
Adj .2001210018
10099
OB-ST-1-03-2017 | 1 | 1
CR-IPC#6 |  | 6
CM SOUQ-SAMAK-IPC01 | 1 | 1
2004210014
10073
OB 13
03/13/11/2021
DEC ADJ 88
7 cancel
IPC02TR0072 | 2 | 2
98
SCD4/004/adjCnl
CR/INV1 PRIDE 5 | 1 | 1
01/13/01/2021
cancel TR46 IPC 11 | 11 | 11
CR 30- 2020 | 2020 | 2020
Cr.Adv. ITS Inv. 01 | 1 | 1
CR
19 EGP - Shabab
CR IPC_3_RedSea
Soc Abo.matmr labour
57
CR-Aug 2017 install.
Decuct. inv. 21 EGP | 21 | 21
D0007-OB-Dec-2020/Cr | 2020 | 2020
Libya Eqpt.9 Co.2
CR-PKG#85/53
CR.Ma Alam Equ Inv 4 | 4 | 4
CR - 11 EGP - Shabab | 11 | 11
Vat Deduction WD
Cancel invoice Lot25
Cr-Tarekabdelhakim 1
cr-5-2020 | 5 | 5
CLOSE41
deduc inv. 23&24 EGP | 23 | 23
Inv ( 2 ) K 10 | 2 | 2
Inv ( 1 ) S 09 | 1 | 1
TAH ipc06 | 6 | 6
TAH ipc07 | 7 | 7
Tarek abdelhakim 01
Rent 4TH maadi
Waldorf astoripc(19) | 19 | 19
inv ( 13 )10-2020 | 13 | 13
ora Landscape ipc 2 | 2 | 2
cairo alex ipc41 | 41 | 41
TR55/IPC/01
port said 1-supply
200730
OCTOBER TUNNELIPC2 | 2 | 2
11763
220621003
IPC#1 Port Saeid |  | 1
220621001
FPC - Ameryia
11498
220321004
Ref. Akhmem Asuit3T
IPC#5&6 |  | 5
IPC#6 - Zamalek |  | 6
2102210004
ENG/040
JV-AC-EE-004 | 4 | 4
IPC_4_Rowad_Ora
D0035-OB-Dec-2020 | 2020 | 2020
D0042-OB-Dec-2020 | 2020 | 2020
30- 2020 | 2020 | 2020
23 - Apr 20
10043
adj. rec 180137-
Clo.مد وثيقة التامين
تشيد بنبان لوط 2
022/2020
18 USD - AL Shabab
25 EGP - AL Shabab
23 EGP - AL Shabab
MP-09 | 9 | 9
Lot. 05
inv.5 EGP/ metal bui | 5 | 5
5001/12
42-19 oct | 19 | 19
1909210012
1909210004
4-19-mar | 19 | 19
Adj inv.180132 | 180132 | 180132
DP WORLD-IPC06 | 6 | 6
Inv. 17 EGP | 17 | 17
P-50-12 AccRev | 50 | 50
P-2-10 AccRev | 2 | 2
180152
P-10-14 ADJ | 10 | 10
P 161 ADJ
180078
180061
10 EGP- West Domiat
Debit Memo -
In.1-14/2-14/3-12gha | 14 | 14
Adj Inv 3 | 3 | 3
Adjust 2017 PV
Adj Inv 2 | 2 | 2
April Scrap.
180069
5
13
122
180044
31
82
77
180036
37
4
7
84
9
Reverse May PV cr me
DR - VAT - Egytech
Closing Attaqa FX
35
Inv.7 Heliopolis | 7 | 7
Balance adjustment
VAT for USD invoices
Ret.. Balance..
Adjust cairo North b
Inv 80 P4 Sammound | 80 | 80
Inv.12 Akhmem Qena | 12 | 12
Inv.11 Akhmem Qena | 11 | 11
Inv.10 Akhmem Qena | 10 | 10
Inv. 8 Akhmem Qena | 8 | 8
Inv. 5 Akhmem Qena | 5 | 5
Dr on Sewedy Holding
5-132KVA-J | 132 | 132
Settlement west
2
rr
(1)MOS elmostsmrin |  | 1
(3)SD elmostsmrin |  | 3
4
39-
OB-SI-EL Kayaan
OB-ST- PKG#37
Balance 2016 2
65 USD - Diwaniya
7 EGP - palm hills
DEC ADJ68
2 USD/123/2011/2012
57001563/5
028/2020 FCV
180041
180028
19 EGP - Shabab 117
15 EGP -West D. 117
2 EGP - West.D 117
3 USD - West D. 117
RECEIPT ADJ
6 USD/123/2011/2012
Inv 74 Abu Quir Badr | 74 | 74
Magha 10 inv. 36 | 36 | 36
Damac 14
close unappl holding
Ghana24B
2 Euro- South Helwan
444 EGP Avice ZTPC
413 EGP Avice ZTPC
Balance Adv Feb 17
8 Maghagha
133/9
tax inv no 3 USD giz | 3 | 3
Balance 10
1055
10167
BSF-SD-EUR-02 | 2 | 2
MOS-SD-EGP-22 | 22 | 22
TAM-SW-EGP-01 | 1 | 1
(3)cw almansora |  | 3
7sd euro mosstasmree
Social 15 Maghagha
34
002 - Inv - 0004 | 4 | 4
inv no(3 Euro-Comcav | 3 | 3
Inv. 16 Oewon Mousa | 16 | 16
Inv. 7 Oewon Mousa | 7 | 7
ANG-Caz-Inv 2 intrst | 2 | 2
OB-ST-New Giza 2
11 Maghagha
10046
40 EGP-Giza N. I&II
03/2017
OB-ST- PKG#53
Inv. 3 Zona 2 | 3 | 3
13 Zona
13
Inv No 4 Iskra | 4 | 4
Balance
Colle Suez Gul 34567
Inv 7 Comcavi | 7 | 7
Apachi Inv No PC.#19
EL KAYAN MEP- IPC 3 | 3 | 3
Inv. no 1 DZD new
Soci.Inv.53wadi16 | 53 | 53
Soc.Inv.55 Elzayat3 | 55 | 55
OB-RE-PKG#53
(10) CW |  | 10
8 USD- West Domiat
Inv. NO.3 KWT Floor |  | 3
2-132KVA-J | 132 | 132
Part Inv 49 Quir EUR | 49 | 49
10579
(3)royal city |  | 3
9 USD - Cairo South
10281
37/P/10/ER/2017/USD
Inv 84 P13 Assuit | 84 | 84
Inv 73 P3Abo Matamir | 73 | 73
Inv Alestom
Inv. 23 Badr | 23 | 23
Inv. 5 Badr | 5 | 5
Ref Retention
Moz.ret.refund
K(mostafa mohamed)
Soci. 72Asuit 10
Inv 3 EGP VO SG | 3 | 3
k(ahmed asman royal2
(2)elkayan fainshing |  | 2
(32)sd elmostsmrin |  | 32
ref.siite electricit
Soci. 1&2 Qina Akhme
2110210005
2101210002
1906210014
2002210015
520
1907210001
180165
Scrab.
10333
11421
10395
10406
Dr-Memo_Inv#19-EGP02 | 19 | 19
Inv.32 Borg Alarab | 32 | 32
Ref.Social.4/5 Assui
Inv 77 P5Abo Matamir | 77 | 77
(1)elkayan lock+load |  | 1
Elkayan Inv.12 | 12 | 12
Kanteen Sodic A.Osma
m.khalifa ministiers
11029
10580
ApatchiInv No P.C#16
Ret. Balance
OB-PS-Mahala Bridge
Inv.2 Assuit Akhmem$ | 2 | 2
Elkayan Inv.13 | 13 | 13
10396
10455
10407
ET - SI INVs EGP-SH
Kanten-Ministiry
Kanteen-MMANSOUR-KAY
Inv.9 Assuit Akhmem$ | 9 | 9
soc 7 samanod-
R5-ZONE2- IPC7 | 7 | 7
IPC3-M.ZAYD TUNNLE | 3 | 3
10492
soc 19-21 assuit akh | 21 | 21
soc 26-29 quna akmim | 29 | 29
Soc.1-15Quana Akhmem | 15 | 15
Ref.InstilNo.1 Qena
El-Nayba Inv. 3 | 3 | 3
Inv.2 Borg Alarab | 2 | 2
10136
Soc.Inv.10 Samanood | 10 | 10
Abolila Zafra kharb
Inv.13Assuit Akhmem$ | 13 | 13
MOS-SD-EGP-26 | 26 | 26
Ref Installation 2 Q
k-m.mansour-sewedy u
10541
Elkayan Inv.14 | 14 | 14
Soc Inv 10 Samanoud | 10 | 10
TAM-SD-EGP-01 | 1 | 1
k-m.badwy-mintra
Inv.7 Assuit Akhmem$ | 7 | 7
PSPELCO-IPC 05 | 5 | 5
10562
Elkayan Inv.15 | 15 | 15
k-m.mansour-kayan11
ELSEWEDY UNI-MEP2
CON 035
IMP/062 Rev0
IMP/060
Loc-008 | 8 | 8
Con-010 rev0 | 10 | 10
CON-008 | 8 | 8
180153
BSF-CW-EUR-02 | 2 | 2
Inv.4 Phosfat | 4 | 4
10512
Inv 2 Asec Sparepart | 2 | 2
14 ُEast
DPW IPC029 | 29 | 29
Sus.Penalety Ghareeb
Soc.38-43 Assuit | 43 | 43
Inv.3 Phosfat | 3 | 3
Civil/J010
Ref.Instal1$ Assuit
Ismailia U3 -IPC2 | 2 | 2
Ret.. Balance.
IPC# Final
2102210003
546
1904210018
PKG#53 -IPC 38 | 38 | 38
10568
Soc 15 Abu-Elmatamer
Inv 99 P15Abo Matami | 99 | 99
K-Hassan-R05-(3)-(4) | 3 | 3
KAYAN FINISHING-IPC6 | 6 | 6
H,A (1)- po 52/51 |  | 1
hassan allam-ipc5/52 | 5 | 5
Inv.5 Phosfat | 5 | 5
10659
229
10050
Benban Lot 2 Inv. 29 | 29 | 29
Benban Lot 2 Inv. 18 | 18 | 18
Benban Lot 2 Inv. 16 | 16 | 16
Benban Lot 2 Inv. 8 | 8 | 8
Benban Lot 1 Inv. 18 | 18 | 18
10698
E&W-Royalcity-May
Inv.40 deductions | 40 | 40
Inv.17 Borg Alarab | 17 | 17
Inv.18 Borg Alarab | 18 | 18
Inv 13/2019 Scrap | 13 | 13
Inv 6 Sugar S/s | 6 | 6
1903210015
239
Ref.Ret 20%Qena
PKG#140- IPC22 | 22 | 22
Social 49 Assuit
10696
ROYAL CITY FIN-IPC06 | 6 | 6
Kanteen-RoyalCity-07 | 7 | 7
Kanteen-Sodic-May-19 | 19 | 19
10758
10911
Port Said Inv. 7 | 7 | 7
10131
TAM-CW-EGP-17 | 17 | 17
PKG#101 -IPC06 | 6 | 6
Kanteen-Kayan-Aug019
2 USD - Suez Steel
243
261
255
inv ( 22 ) 13-12-20 | 22 | 22
INV(13)150620 | 13 | 13
Inv. 1 EUR & EGP AMm | 1 | 1
1908210011
17-19-June | 19 | 19
267
14-19-June | 19 | 19
Marsa Alam EGP Inv 1 | 1 | 1
ISE-SD-EURO-01 | 1 | 1
kanteen-sep-kayan110
Inv. 11 Farm | 11 | 11
SOKHNA TUNLE2-IPC02F | 2 | 2
Kanteen-Kayan-OCT019
HYPER ONE-IPC14 | 14 | 14
Claim
10765
Kanteen-Ministri-OCT
Benban Lot2 Inv 8 $ | 8 | 8
36-19 october | 19 | 19
10811
11011
269
277
MIDA Ins. Inv.5 | 5 | 5
MIDA Ins. Inv. 4 | 4 | 4
Benban Lot 2 Inv. 13 | 13 | 13
10787
10952
Kanteen-minis-Nov-19 | 19 | 19
Kanteen-uni-Nov-2019 | 2019 | 2019
PKG#117-IPC12 | 12 | 12
41-19-oct | 19 | 19
280
279
281
11079
10951
ESU2 ENABLE-IPC2 | 2 | 2
IPC#4 |  | 4
Cr. Note reclass
1907210005
11084
11085
1901210005
286
285
Scrap Lot. 08
Scrap Lot. 14
Scrap Lot. 4
Lot. 18
71-19 Dec | 19 | 19
Toshka Lot 4 Inv .22 | 22 | 22
CFC-IPC01 | 1 | 1
Kanteen-R05-Jan-2020 | 2020 | 2020
ROYAL ZONE-IPC01 | 1 | 1
20100001
Badr-Zizenia Inv.2 | 2 | 2
Abolila Zafra kharb-
Scrap Inv. 38/2019 | 38 | 38
504
CFC-IPC13 | 13 | 13
SOREAL-IPC10 | 10 | 10
Lot. 08
2 Jan 20
Kanteen-Royal-Feb-20 | 20 | 20
Toshka Sub Inv. 24.$ | 24 | 24
H,A-IPC002-PO181/148 | 2 | 2
2002210025
Scrap inv 1/2020 | 1 | 1
Re soc Inv 24 Quna | 24 | 24
Compensation Maghagh
10017
10076
10023
320
309
324
341
318
317
316
IPC#1 |  | 1
344
Inv.1 Final ElNokra. | 1 | 1
11102
Eng-027 rev0 | 27 | 27
E.S.U2 ARCH&MEP-IPC2 | 2 | 2
4-2020 | 2020 | 2020
inv(5)100220 | 5 | 5
19 Mar 20
10153
6-2020 | 2020 | 2020
2002210030
Toshka Lot 6 Inv .1 | 1 | 1
Refund 02/13/06/2020
Scrap T&D 7/2020
39 -JUn-2020 | 2020 | 2020
10215
10213
Calim-001 | 1 | 1
Scrap invoice
11241
Inv(1)010320 | 1 | 1
33-2020 | 2020 | 2020
17-2020 | 2020 | 2020
2008210006
489
488
scrap invoice No 3
Ref Retention Matroh
365
Kanteen-Olymp-Aug-20 | 20 | 20
IPC 49 R05 (2) | 49 | 49
other income-siemens
11581
Ref.Retention Matroh
Ref Retention Simens
IPC_14_Rowad_seast
IPC_14_Rowad_poly
10032
-919 | 919 | 919
IPC_16_rowad_s_east
OB-ST- PKG#22
IPC_13_Rowad_IndoorH
Inv.14/2020 -Transmi | 14 | 14
374
Kanteen-R05-Oct-2020 | 2020 | 2020
Kanteen-Mangroovy-20 | 20 | 20
Kanteen-Kayan-Jul-20 | 20 | 20
reclass PA
2009210018
Ora ph1 ipc 36 | 36 | 36
colsing tr0015
Toshka Sub Inv. 05 $ | 5 | 5
Toshka Sub Inv. 06 $ | 6 | 6
Con-016 | 16 | 16
Lot-20 | 20 | 20
31-12-2020 | 12 | 12
scrap lot 6
MIDA Sply. Inv. 1 | 1 | 1
MIN-LAND SCAPE-IPC03 | 3 | 3
MIDA Sply. Inv. 2 | 2 | 2
67-Oct-2020 | 2020 | 2020
Inv 10 Sugar S/s | 10 | 10
inv ( 24 )17-12-2020 | 24 | 24
ELSEWEDY HQ-IPC02 | 2 | 2
Toshka Sub 4 Inv. 05 | 5 | 5
Ref Inst.6 Qena
2011210005
11844
INVOICE OVM-PO35483
78-Nov-2020 | 2020 | 2020
PSP ELCO-IPC FINAL
KATAMYA CREEKS IPC13 | 13 | 13
KATAMYA CREEKS-IPC02 | 2 | 2
inv ( 1 )3-2021 | 1 | 1
87-Dec20
200179
IPC_19_Rowad_Poly
PKG#144-IPC15 | 15 | 15
10183
11923
Kayan - 2 | 2 | 2
Suez S4 Inv. 06 | 6 | 6
MIN-LONG LEAD-IPC03 | 3 | 3
11664
11867
Toshka Sub 4 Inv.1 $ | 1 | 1
FPC - HAC CCC JV
2012210029
7-2021 | 2021 | 2021
P-45-Portsaid Inv.3$ | 3 | 3
P-45-Portsaid Inv.1$ | 1 | 1
2103210003
IPC#1` EDECS |  | 1
65-oct-2020 | 2020 | 2020
Ora - 3 | 3 | 3
Suez S4 Equ Inv. 01 | 1 | 1
South Valley Inv. 12 | 12 | 12
South Valley Inv. 10 | 10 | 10
11944
11808
11803
11953
Ret Ref 10/13/03/21
Final Inv.7 Phosfat | 7 | 7
JV-AC-EE-Inv-005 | 5 | 5
14-2021 | 2021 | 2021
Ref.soci 50 Assuit
ENG/037
PKG #177 IPC06 | 6 | 6
10502
Ref.Ret Marsa Alam 5
Ministries - 04 | 4 | 4
ENG/039
Inv. 27 Badr | 27 | 27
Inv.14 - Lot 1 | 14 | 14
Inv.13 - Lot 1 | 13 | 13
MIDA Ins.7
Ref.Ret Quana akh 2
Diplo Dist. IPC01 | 1 | 1
Air Force Inv . 06 | 6 | 6
Air Force Inv . 01 | 1 | 1
11948
12242
12262
12363
12282
12142
409
EGAT WaterTank IPC02 | 2 | 2
10622
2106210001
10606
2106210005
11868
10642
22
م 1 الطوارىء لوك لود | 1 | 1
417
2108210001
2009210013
12422
Kanten Minist 8/21
Maryotya IPC08 | 8 | 8
29/13/08/2021 RefRet
Ref.Ret Sugar Sub
Ref Ret Sugar 33 -OH
Ben Zayed Inv. 01 | 1 | 1
Kanten OCT21 Olympic
Kanten OCT/21 OraZed
Kanten OCT/21 Minist
Kanten OCT/21 Creks2
Kanteen OCT/21 R05
2104210003
EGAT WaterTank IPC04 | 4 | 4
IPC-05-LRT | 5 | 5
10885
200330
423
waldorf astoria IPC4 | 4 | 4
12728
2111210002
Air Force Inv . 15 | 15 | 15
Kanten GOV2 NOV 21
Ret Asuit akh 4 T
Toshka Lot4OH Inv.07 | 7 | 7
10964
IPC-14-Saray | 14 | 14
ElSEWEDY HQ IPC09 | 9 | 9
INV ( 16 ) GET | 16 | 16
200465
2112210004
Hosh Essa Inv. 01 | 1 | 1
IPC#5 - Assuit |  | 5
رد تامين3بنبان لوط 1
11122
newgizahospital ipc1 | 1 | 1
k-kayan-jan22
el marg ipc10 | 10 | 10
12650
supply egp ipc.4
Invoice 03/2022 | 3 | 3
Scrap Inv. 01/2022 | 1 | 1
11284
11287
52
11242
200526
10460
Scrap Lot No:15
12830
11364
Port Said Inv. 6 | 6 | 6
MDF FACTORY2 IPC03 | 3 | 3
IMP/067
Inv. 12 Oewon Mousa | 12 | 12
IPC#7 Taamer |  | 7
11/13/03/2022-KwdRet
Material EES3
IPC-Final-Sodic East
Scrap Lot No:17
watertank IPC 11 | 11 | 11
MIDA Sply. Inv.10 | 10 | 10
11476
74
Suez S4 Inv. 13 | 13 | 13
447
220321002
12972
k-mohamed-apr22
IPC-6-PLAYA ROOF | 6 | 6
220221001
Emaar Pkg#189 ipc 21 | 21 | 21
pkg #205 ipc 4 | 4 | 4
220421001
200611
EDNC HARDESCAPE IPC3 | 3 | 3
inv ( 3 ) 15-6-2022 | 3 | 3
MIDA Ins. Inv. 14 | 14 | 14
2005210008
كيان صحى م 4 | 4 | 4
Invoice # 27 Assuit
K-ALI JUN2022
32-2021 | 2021 | 2021
200607
200625
Toshka Lot 6 Inv .22 | 22 | 22
Ref-Ret-Benban lot1
11543
MDF - IPC18 | 18 | 18
Kantine.1
k-husain jul2022
IPC-2-PLAYA ROOF | 2 | 2
10024
2001220002
IPC01-MEGA | 1 | 1
MDF factory(2) IPC7 | 7 | 7
11767
T 11-2022 | 2022 | 2022
In&ReSupply(ABB)ipc3 | 3 | 3
80
mariotya ipc18 | 18 | 18
cairo-alex ipc 28 | 28 | 28
IPC#19 Sokhna Port |  | 19
Sorealhardscape IPC9 | 9 | 9
K-HUSSAIN AUG 2022
MINISTIRYFITOUT IPC4 | 4 | 4
Abo ghaleb ipc 05 | 5 | 5
october tunnel ipc1 | 1 | 1
200724
el khatatba ipc 06 | 6 | 6
IPC000024' | 24 | 24
urbn-k ipc 11 | 11 | 11
URBN-K IPC 12 | 12 | 12
seashell playa- IPC2 | 2 | 2
sokhna port ex ipc04 | 4 | 4
R.O(5:8) APP ipc 4 | 4 | 4
R.O. Supply - IPC5 | 5 | 5
IPC000003 | 3 | 3
200859
4
k-abdelwahabfeb.2023
final HSR
EIPICO3- IPC 2 | 2 | 2
IPC000002 | 2 | 2
MDF 2 - IPC 10 | 10 | 10
k-mustafa mar.2023
IPC1-TR055 | 1 | 1
200809
IPC#1 Warraq |  | 1
Carrefour RBS IPC1 | 1 | 1
MDF Factory2 ipc 16 | 16 | 16
INV ( 11 ) Hyper | 11 | 11
asmarat IPC Final
IPC0020 | 20 | 20
Eipico ipc 3 | 3 | 3
Mdf Factory 3 ipc 13 | 13 | 13
Abo shanab ipc 4 | 4 | 4
IPC0014 TR46 | 14 | 14
230000010
MDF factory ipc 34 | 34 | 34
IPC001 TR54 | 1 | 1
(29)pkg#32 |  | 29
k-mustafa june.2023
200855
IPC002TR65 | 2 | 2
200788
Egat Piping ipc 1 | 1 | 1
ipc2 supply of RO | 2 | 2
EGAT MEP- IPC2 | 2 | 2
MDF2 IPC ( 18) |  | 18
Sultana 034 IPC Fin
pkg#177- IPC 40 | 40 | 40
IPC 4 D0076 | 4 | 4
IPC#4 |  | 4
IPC#2 |  | 2
sultana malak2 final
IPC11 TR55 | 11 | 11
IPC07TR0077 | 7 | 7
IPC001 TR62 | 1 | 1
mdf equip ipc 19 | 19 | 19
pkg#189-IPC4 | 4 | 4
IPC 002- BALTAT | 2 | 2
Rent 10/2023
14-2023 | 2023 | 2023
sokhna bridge ipc16 | 16 | 16
IPC03TR0068 | 3 | 3
78-canteen
wady elnatroon ipc5 | 5 | 5
TAH ipc 7 | 7 | 7
IPC09TR0064 | 9 | 9
PLAYA - C072 IPC 4 | 4 | 4
88-canteen
201055
Van-Lot.1 jan.24
Abo Shanab ipc01 | 1 | 1
IPC05TR0054 | 5 | 5
K-mustafa Dec.23
Emaar pkg#189 ipc 19 | 19 | 19
IPC04TR0071 | 4 | 4
IPC01 TR66 | 1 | 1
IPC001 TR71 | 1 | 1
IPC001 TR70 | 1 | 1
IPC05TR0559 | 5 | 5
IPC17TR0055 | 17 | 17
PO 4500656739/German
IPC05TR0071 | 5 | 5
PO 3100075910
IPC07TR0088 | 7 | 7
Playa C038- IPC11 | 11 | 11
93-canteen
IPC17 wadyelnatroun | 17 | 17
1-2024 | 2024 | 2024
IPC05TR0068 | 5 | 5
ipc 11 | 11 | 11
IPC08TR0062 | 8 | 8
IPC15TR0064 | 15 | 15
Orient March.24
Gov2 ipc 26 | 26 | 26
TAH ipc 11 | 11 | 11
IPC#18#WADI ELNATROU |  | 18
IPC16TR0064 | 16 | 16
IPC18TR0064 | 18 | 18
IPC08TR0077 | 8 | 8
Samaya factory ( 1 ) |  | 1
Playa - c469 ipc 3 | 3 | 3
201232
Mdf Factory ipc 39 | 39 | 39
Waldorf Spare ipc 1 | 1 | 1
Rent 5/2024
Dp World PH2 ipc 15 | 15 | 15
MDF Equip ipc 23 | 23 | 23
PO 4500669893
201291
201351
Orient May.24
kafr shokr ipc08 | 8 | 8
SPX.1(22+23) part 2
118-canteen
201293
ELSEWEDY HQ- IPC 22 | 22 | 22
ELSEWEDY HQ IPC15 | 15 | 15
Ora ph1 ipc 41 | 41 | 41
IPC#2 Abo Galab |  | 2
Sales Sep.24 CIV
Escalation ipc 1:28 | 1 | 1
Katamya Urbnk ipc 13 | 13 | 13
IPC07TR0084 | 7 | 7
IPC08TR0084 | 8 | 8
Sales Sep.24 Driller
R.7th floor 10+11+12
K-HASSAN-10.24 | 10 | 10
Wady elnatron esc1:8
Ora ph1 ipc 42 | 42 | 42
IPC03TR0099 | 3 | 3
IPC20TR0053 | 20 | 20
IPC21TR0053 | 21 | 21
IPC11TR0059 | 11 | 11
IPC01TR0095 | 1 | 1
IPC02TR0073 | 2 | 2
INV no.13 | 13 | 13
PLAYA C470 IPC3 | 3 | 3
Rent 11-2024 | 2024 | 2024
Mdf Equip ipc 26 | 26 | 26
inv ( 1 ) W. Natron | 1 | 1
CR cairo alex ipc 40 | 40 | 40
CAN..
close2016
DEC ADJ 62
Scrap Inv. 09/2022 | 9 | 9
close 61
206
78
12069
CRIPC_1_SARAYA_GAMA2
ob7
Libya Eqpt.4 Co.3
D.N Railway19-12-202 | 12 | 12
Ref.Ret PIPWst inv.4 | 4 | 4
CR21000002
CR.April Scrap.
CR.Ref.Akhme Asuit T
Cr-Tah ipc07 | 7 | 7
cr.IPC_4_Rowad_Ora
CR -3-2024 | 3 | 3
Cr DPworldph.2-IPC2 | 2 | 2
cr1
Close 1st invoice
Inv. 19 Farm | 19 | 19
CR.2 مد وثيقة تامين
OB- ST
landscape ipc06 | 6 | 6
CR.OB Advanced 8
R 1 closed
cr 3-2023 | 2023 | 2023
FPC- Marina Towers
ce 1
cr11biny
10423
OB-MOS-Hyper One
Cr, Inv. 1 S1 | 1 | 1
11769
83
mos3f
17 feb 20
Cr.Inv ( 1 ) S05 | 1 | 1
DEC ADJ 67
11766
Closing Swedy cement
Inv.68 Bank charges | 68 | 68
ipc1 aswan | 1 | 1
14 USD- Suez Gulf
Cr for other-deduct
1 EGP -El Tebein 113
31/13/05/2021
1074
48
adjust billing
58
69-Oct-2020 | 2020 | 2020
13073
1 closed
Inv.3&4 deductions | 3 | 3
ADJ-Inv.15 | 15 | 15
DEC ADJ 33
Close AR Balance-
اتحاد تشيدP-16-EGY | 16 | 16
10462
Cr.P-13-2016 | 13 | 13
Cr-port said EURipc1 | 1 | 1
CR- 38 EGP- Shabab | 38 | 38
CR Close El Niger
51
Soc.2020 تشيد وبناء
Cr T 4-2022 | 2022 | 2022
Air def harek IPC1 | 1 | 1
C.IPC03TR0081 | 3 | 3
CR- 18 EGP Domiat | 18 | 18
DM 1/2022
CR R.O Sup. adj ipc4 | 4 | 4
adj. 180010 &180013
OB-ST-Dp World
Cancel inv 39 Assuit | 39 | 39
01/13/09/2021
96
7 EGP - South Helwan
474
04/13/06/2021
2Cancel IPC11 TR46 | 11 | 11
Libya Eqpt. Inv.NO.2 |  | 2
35-2020 | 2020 | 2020
CR.refund ret.kay
11663
Cr.Inv,7 usd Borg Ar | 7 | 7
11523
109
536
TR55-CR2
اتحاد تشيدP-29-EGY | 29 | 29
10529
cr114
Car-Dep SEP. 2021
Final Inv. Ghareb
5-132KVA-J-del | 132 | 132
Deduct Eng Stamp.
Credit Memo
CR.TR0021CLOSING.DEC
07/13/12/2021
8
amend inv. 27 EUR | 27 | 27
Scrap Inv. 13/2021 | 13 | 13
can IPC02TR0089 | 2 | 2
Cr Inv 10 Usd Borg | 10 | 10
رد تامين الزعفرانه غ
water instead EETC
55-CR3F
CR-rolling millIPC10 | 10 | 10
MCBs inv.No.1.Cncl |  | 1
تشيد نجع 2020
01/13/04/2021.
CR- VAT Coll.
Inv. 09 /2019 Scrap | 9 | 9
20/13/05/2022
42 closed
Cr 18
DEC ADJ 36
Cr-cars-lot2 jan.24
SH Inv deductions
Close inv.180136 | 180136 | 180136
CR1-19-FEB | 19 | 19
deduct.inv.23&24 EGP | 23 | 23
Ref.Abu Quir Badr T
10429
CM 24A
tetra amend01 -cr
45 closed
GPC inv. deductions
CR 15
CR(14)281020 |  | 14
Libya Eqpt.7 Co.2
304
Cancel the invoice
DEC ADJ 27
DEC ADJ 44
10484
16 EGP-progress adj.
CR-invs 2018 | 2018 | 2018
43-Jun-2020 | 2020 | 2020
D.M 12595
10486
DM 13086
Refund .Reten.banha
CR. 12 Oewon Mousa
CR Amend vat
ipc no3 aswan
CR IPC_1_SARAYA_GAMA
refund 1
Scrap Inv. 02/2020 | 2 | 2
DN Insurance JICA+++
11187
Scrap Inv. 20/2020 | 20 | 20
CR ACWA IPC1 | 1 | 1
CR-16 | 16 | 16
Cr 2-2023 w | 2023 | 2023
CR PKG#32
10
Ref.Ret. 8 EGP
Scrap Inv. 06/2022 | 6 | 6
D.N Insurance JICA
Ret.OB Damac
IPC12TR0059 | 12 | 12
Cr-17 EGP - Shabab | 17 | 17
Cr-TAH ipc06 | 6 | 6
260
257
OB-RE5
Settle forex
DEC ADJ 60
D.m Orange Invoice
Scrap Inv. 36/2019 | 36 | 36
close 20
CR.TR0025CLOSING.DEC
cr 23 - Apr 20
final inv elalamien
Cr.INV ( 1 ) R08-K12 | 1 | 1
180084
crفروق اسعار مريوطية
Adj .1904210014
76
Olympi Kanten July21
rev. ( 65 USD -Diwan
04/13/01/2022
258
SOKHNA BRI. ESC1:21F
LG Bank fees
ipc#2#harm city d083 |  | 2
Ret.OB Korimat500
270
CR_in 37
IPC#02 Madkour CR |  | 2
CR.TR0013CLOSING.DEC
CR - 7 USD - West D. | 7 | 7
180075
Screap 2/2019 copy
DEC ADJ 80
IPC#3 - NRCC |  | 3
Cr 2
12 closed
Adjust 2201210001
remaining of 49 EUR
inv 1.2 d0080 CR | 1 | 1
close 17
CR po 0020024000370
Adjust Alstom Ret.
CR. 11 Oewon Mousa
Inv ( 17 ) CS-20 | 17 | 17
Cr.Memo Reten.usd
Balance 2016 12
internal transaction
DEC ADJ8
IPC0022_CR | 22 | 22
12993
01/13/05/2022
DEC ADJ 84
Cr 123
CM RME- 2021 | 2021 | 2021
Scrap inv. 29/2019 | 29 | 29
Credit-inv4-final | 4 | 4
10029
5-19Mar | 19 | 19
Deduct inv.17-18 EGP | 17 | 17
Inv 29 Shaba EGP | 29 | 29
11/13/04/2021
SCD4/002Cnl
Balance 12
tetra-001 cr | 1 | 1
OB-SI-PKG#22
Libya Eqpt..3 Co.3
11322
Cr-S.Tax- 6 USD-Shab | 6 | 6
CR.مد وثيقة التامين
Deduct inv 17-18 EGP | 17 | 17
93
CR27
66-19 Dec | 19 | 19
Cr-memo W.hold 9-EGP
cr-emarpkg#189 ipc18 | 18 | 18
CR_IPC_!_Saraya_Gama
Suez S4 USD Inv. 06 | 6 | 6
CR.inv.11 Assuit Akh | 11 | 11
02/13/09/2021
D0017-OB-Dec-2020/Cr | 2020 | 2020
OB Retention 1
crEipi material ipc3 | 3 | 3
12182
OB-RE-Ezz Factory
CR.TR0012CLOSING.DEC
200284
Advance balance adj.
Deduct Eng Stamp
Ref.Ret11/13/08/2021
IPC09TR0077 | 9 | 9
Retention OB PortSai
CR 13,91
CR.10Ramadan Inv.03 | 3 | 3
close 52
CR5-19-mar | 19 | 19
CR IPC-12-Saray-2 | 12 | 12
inv (5) final CA | 5 | 5
Libya Eqpt.3 Co.1
closing 6
HSR-OCT 5
MOC Inv-01 | 1 | 1
RME/AJC/EM/11057/24
Emar PKG#189 IPC18 | 18 | 18
R.O(50:80)S adj ipc4 | 4 | 4
2-2023 | 2023 | 2023
inv ( 10 ) Captal 1 | 10 | 10
k-youssef feb.2023
elsewedy HQ- IPC24 | 24 | 24
kafr shokr ipc 9+ | 9 | 9
kafr shokr ipc09 | 9 | 9
Elco Steel
Pole. Cvr. Inv.2 | 2 | 2
11559
11496
Selling Scrap Lot25
27
IPC#02 - Madkour |  | 2
2108210012
sewedy uni-mep-07 | 7 | 7
D0028-OB-Dec-2020 | 2020 | 2020
DM-1 | 1 | 1
MIDA Ins. Inv. 5 | 5 | 5
D0030-OB-Dec-2020 | 2020 | 2020
14
D0028-OB-Dec-20202 | 20202 | 20202
IPC_4_ORA
D0021-OB-Dec-2020 | 2020 | 2020
TR0013DEC.Closing
TR0010DEC.Closing
TR0009DEC.Closing
TR0005DEC.Closing
TR0004DEC.Closing
D0024-OB-Dec-2020 | 2020 | 2020
D0027-OB-Dec-2020 | 2020 | 2020
IMP/061
IPC_1_GRowad_LRT
2011210010
2009210001
58-Aug-2020 | 2020 | 2020
10037
2001210020
7 USD - West D. Khor
23 EGP VO TOAC
IPC#1. |  | 1
30/P/10/ER/2017/USD
3-19-mar | 19 | 19
Adj Inv 8 Final | 8 | 8
180179
6 beni Suef - 1020 | 1020 | 1020
Scrap 2/2019
P-2S-10 ADJ | 2 | 2
Debit Memo
11 EGP- Shabab
Inv,11 usd Borg Arab | 11 | 11
180121
Tax - CR - Egytech
Adj Inv 10 | 10 | 10
Refund Ret 2 flor
Adj Inv 8 | 8 | 8
Adj. Inv. 14 | 14 | 14
Adj Inv. 21 | 21 | 21
soc 12-16 assuit akh | 16 | 16
11
16
90
95
6
70
73
83
75
Adj Adv $ Cairo
2 EGP - Lina
4 USD - Cairo South
10018
Final_
Balance Feb 2017
5 Euro- South Helwan
DEC ADJ 49
1002
2 USD - Banha 118
Mod. Nov.
24 B
Moz-inv.1&2-localAdv | 1 | 1
030/2021
3-132KVA | 132 | 132
11-132KVA | 132 | 132
10 Beni Suif 2
Close cost in adv.
6 EGP - Lina
Balance 3
180034
16 EGP - West D. 117
ِAdvance Memo - CEPC
103/10
DEC ADJ 70
396 EGP Avice ZTPC
441 EGP abu qeir 118
426 USD Avice ZTPC
442 USD Avice ZTPC
26/P/10/ER/2016/USD
4,
ISE-SW-EGP-02 | 2 | 2
BSF-SW-EGP-11 | 11 | 11
27 EGP - West Domiat
35
65 USD -Diwaniya
24 Euro - Giza N.III
Remaining Inv 7 | 7 | 7
Aply advance -Memo
close un appl hassan
Banha-Zagazg Inv.02 | 2 | 2
OB-SI-EL Kayaan2
(3) p.o52/156 |  | 3
10044
Inv 43 EGP Giza III | 43 | 43
6 EGP - South Helwan
2 Scrap 2017
05/2017
Inv No7 Wattanya220 | 7 | 7
(4) pkg#107 |  | 4
ROYALCITY-IPC-12 | 12 | 12
Inv.26 Asec | 26 | 26
Soc. 46 Wadi 12
Ref.Ret Bridge2
MozRetUsd
Inv. 6 USD | 6 | 6
180013
11 USD Suez Gulf
10 USD Suez Gulf
Apachi Inv No PC.#26
Abachi Inv No P.C#18
Inv June Qatar
6 EuroSouth Helwan
5 EuroSouth Helwan
10165
Social inv.49 wadi14 | 49 | 49
Soc. 57 Bnha 13
Soc.Inv.59Assuit5 | 59 | 59
36
(6) pkg#107 |  | 6
Inv. 24 USD | 24 | 24
remaining of 21USD
2 EGP - El Tebin 124
Inv No 3 Elegect | 3 | 3
31/8/2017
10260
(2) pkg#85 |  | 2
1 EGP - Scrap
Inv 11 Cairo south | 11 | 11
6-132KVA-J | 132 | 132
(2) كانتين يناير |  | 2
Assuit 82 Inv.12 | 12 | 12
Inv. 16 Mostakbal | 16 | 16
Inv. 3-4 Badr | 3 | 3
Ref. Reten 66 wadi19
soc.66/9 wadi
Sammound Inv No 1 | 1 | 1
TempInv
K(ahmed asman)
Insurance Samanood
Soc 74 samanod
180058
(11) pkg#107 |  | 11
Kanten-A.Osman-Royal
Soci 1&2 Asuit Akhme
2108210007
220721003
2105210006
1903210002
10353
Qatar Scrap Revenue
180031
OB-ST-Attaqa
10394
10354
Soc 5 abou almatamer
(5)cw elasmaaliya |  | 5
Mini Landscape IPC04 | 4 | 4
Closing Morganti USD
Closing Morganti bal
Green power EUR
PKG#53-IPC 33 | 33 | 33
36-132KVA(9J) | 132 | 132
Sco 5 samanod abo el
K-HASHM-GAZI MALL
Inv.12Assuit Akhmem$ | 12 | 12
10419
10510
MIN-CORE-IPC06 | 6 | 6
MIN-FIT OUT-IPC03 | 3 | 3
soc 9 abo elmatamer
soc 9-13 quna akhmem | 13 | 13
Forklift Rent Inv.
Inv.4 Borg Alarab | 4 | 4
DM 5 Borg Alarb
Soc.Inv.12 Matamet | 12 | 12
Inv.15Assuit Akhmem$ | 15 | 15
OB RT 005
k-m.khlifa-ministier
10511
Soci.41EGP Qena Akh
Inv.2 Phosfat | 2 | 2
SH inv.33&34 ded | 33 | 33
K-M.Khalifa-minstrie
10524
Ref Instil 4 Qena
CON/026
CON/025
LOC/015
LOC/010
OB RT 001
ret.col.19/13/12/18
Inv. 5/2018 | 5 | 5
mall masr-IPC FINAL
10516
DP WORLD- IPC 01 | 1 | 1
dpw ipc33 | 33 | 33
Social Inv.45-46 Qen | 45 | 45
SCD4/002-ZmbShar
Ref.ret.198200 krimt
K-A.Osman-ismlia-feb
PKG#140- IPC13 | 13 | 13
K-Hassan-R5-Feb
BSF-CW-EURO-04 | 4 | 4
K-Hashem-Jazimal-Mar
Ref.Ret 3 assuit akh
Ref.Ret 2-3 Qena akh | 3 | 3
Ref.reten korimat
K-Ahmed.Osman-R/C04
Water&Electricity-04 | 4 | 4
1905210010
222
10049
Benban Lot 2 Inv. 30 | 30 | 30
K-mostfa-Minis-may-5 | 5 | 5
Inv. 6 Scrap 2019 | 6 | 6
1903210012
Mohamed.mansour-June
Benban Lot2 Inv 16F$ | 16 | 16
10717
235
20100006
Inv 4 $ Sugar S/s | 4 | 4
inv 18/2019 Scrap | 18 | 18
Compensation Assuit
Kanteen-R05-june2019
Soc Inv 26 $ Quna T | 26 | 26
Soc Inv .... Quana
Soc Inv ...Quana
Kanteen-ismalia-AUG
10830
3*14 EGP- Suez Steel
10719
492
10169
263
276
271
soc inv 48 labor Qua | 48 | 48
Soc Inv 50 labor Asu | 50 | 50
22-19Jul | 19 | 19
Inv. 18 Farm | 18 | 18
1907210017
44-19 oct | 19 | 19
33-19sep | 19 | 19
Instill.Pay 5 Akhme2
Refund.Ret.Assuit
inv ( 29 ) 30-9-21 | 29 | 29
274
TAM-CW-EGP-19 | 19 | 19
11034
10267
11015
Tunnel Inv. 8 | 8 | 8
11018
518
Kanteen-Royal-Dec-19 | 19 | 19
Kanteen-UNI-Dec-2019 | 2019 | 2019
37-19 oct | 19 | 19
ABO GHZALA L&L-IPC01 | 1 | 1
11083
Adj.1904210014
180166
1903210005
1904210011
1901210002
Scrap Lot. 17
Kanteen-Helton-Dec19
Kanteen-R05-Dec-2019 | 2019 | 2019
72-19 Dec | 19 | 19
Benban Lot 2 Inv. 26 | 26 | 26
Toshka Lot 6 Inv .17 | 17 | 17
Toshka Lot 4 Inv $2 | 2 | 2
refund for Extra Scr
Kanteen-Uni-Jan-2020 | 2020 | 2020
11101
ROYAL CITY- IPC0018 | 18 | 18
NEW GIZA2-IPC FINAL
298
297
Inv. Ins10-1/15-12-3 | 1 | 1
507
11025
Scrap Lot 08 - 03 | 3 | 3
TAM-CALIM-01 | 1 | 1
10722
11026
59-19 Dec | 19 | 19
IPC#2 |  | 2
H,A-IPC001-PO181/148 | 1 | 1
So.22:25$assuit lot1
Social Ins.Itay6/358
11381
Inv.22Assuit Akhmem$ | 22 | 22
ESU2-IPC7-ENABLE | 7 | 7
ISE-CW-EGP-22 | 22 | 22
2003210007
1 Jan 2020
74-19 Dec | 19 | 19
12 feb 20
56-19 nov | 19 | 19
Kanteen-Kayan-Mar-20 | 20 | 20
Kanteen-minis-Apr-20 | 20 | 20
501
Toshka Lot 4 Inv $1 | 1 | 1
321
307
342
2003210011
Inv.68 Borg Alarab | 68 | 68
10029
Inv.72 Borg Alarab | 72 | 72
6-2024 | 2024 | 2024
11324
18 mar 20
10363
10098
24 Mar 20
2005210011
10197
2004210002
10096
42-19 october | 19 | 19
11183
62-19 Dec | 19 | 19
11223
11523
inv(10)50720 | 10 | 10
Kanteen-wezarat-July
46 Jul-2020 | 2020 | 2020
442
EL.S.U.2-ENABLE-09* | 9 | 9
Rent equipe inv.6-20 | 6 | 6
IPC#2 |  | 2
IPC#1 |  | 1
36-2020 | 2020 | 2020
11547
376
Kanteen-Unvirsity-20 | 20 | 20
10066
10065
inv ( 11 ) | 11 | 11
IEKA2-MARAKZ-IPC01 | 1 | 1
372
Kanteen-Olympic=2020
11682
IPC#4 |  | 4
scrap lot no 8
72-Nov-2020 | 2020 | 2020
Car Sales 357
Toshka Lot 4 Inv .12 | 12 | 12
Kantin-R05-Nov-2020 | 2020 | 2020
Kantin-Olympic-Nov-2 | 2 | 2
26
10262
Sodic - Soreal
79-Dec-2020 | 2020 | 2020
11661
11643
Ora - Zed
IPC#1 |  | 1
olympic-1 | 1 | 1
Cre.adv.Tosh OH 4
86-Dec20
ENG/034
390
2006210009
ENG/035 Rev0
IPC_2_LRT |  | 2
MANGROVERENT-IPC3 | 3 | 3
Cre.adv. $ Toshka 4.
2101210003
393
P-45-Portsaid Inv.04 | 4 | 4
IPC_21_Rowad_Seast
IPC_Ora_4
Suez S4 USD Inv. 02 | 2 | 2
RING MARYOTUA-IPC04 | 4 | 4
Selwa OHTL Inv . 01 | 1 | 1
Ref Ret Balat Lot 3
South Valley Inv. 11 | 11 | 11
11943
م.ك Inv.01 PO. 230 | 1 | 1
11865
IPC#1 Marazik |  | 1
MANGROVE-IPC5B RENT | 5 | 5
Kayaan - 04 | 4 | 4
Olympic Hall - 04 | 4 | 4
Eng/038
15-2021 | 2021 | 2021
Acroket Company - 05 | 5 | 5
402
Kanten-May21(Minis.)
Diplo AD.
Air Force Inv . 08 | 8 | 8
alasher bridge-f+
IPC001-OVM-2021 | 1 | 1
Hosh Essa Inv. 12 | 12 | 12
408
407
Refund retention 01
Ministries-Jun21
421
IPC#2 - Marg |  | 2
Acroket Company - 06 | 6 | 6
12608
LRT 10Ramadan Inv.05 | 5 | 5
24
419
LOC/016
Air Force Inv . 11 | 11 | 11
12502
Kanten Olympic 8/21
Kanten ORA Zed AUG21
20-2021 | 2021 | 2021
Kanten R05 Sep 2021
Kanten Ora Zed Sep21
17-9-2021 | 9 | 9
12565
12562
Ref.Ret ELAmeed
CFC IPC025 | 25 | 25
12612
12564
34-2021 | 2021 | 2021
23-2021 | 2021 | 2021
El-Marg IPC07 | 7 | 7
Kanten Minist 11/21
Ret Benban Lot 2 T
Toshka Lot4OH Inv.08 | 8 | 8
10968
Credit Memo DRCC
12615
Ref.2 sugar Farm T
Ref.3 benban Lot 2 T
Ref.8 Akhme Quana T
Kanteen DEC21 GOV2
Invoice 18/2021 | 18 | 18
R05 IPC029 | 29 | 29
sokhna port ex ipc10 | 10 | 10
11062
Air Force Inv . 21 | 21 | 21
INV ( 7 ) Ring R | 7 | 7
472
12365
463
رد تامين بنبان لوط 1
IPC-1-PLAYA ROOF | 1 | 1
200550
200527
200528
k-r5-jan2022
11074
IPC-16-SARAY | 16 | 16
IPC-2-BORSA | 2 | 2
12829
IPC-11-PLAYA | 11 | 11
IPC#7 Sokhna Port |  | 7
2201210002
200524
k-mostafa0mar22+1
10th Ind Park Inv.01 | 1 | 1
cairo-alex ipc16 | 16 | 16
11368
Selling Scrap Lot 3
MIDA Ins. Inv.10 | 10 | 10
200609
Suez S4 Inv. 17 | 17 | 17
Suez S4 Inv. 12 | 12 | 12
12888
PKG#189 IPC 30 | 30 | 30
38
Inv. 15 Mostakbal | 15 | 15
Ref.1 LRT Cable T
EL KHATATBA IPC02 | 2 | 2
Al - Jazi Inv. 3 | 3 | 3
Marsa Alam EGP Inv13 | 13 | 13
Marsa Alam EGP Inv 9 | 9 | 9
12930
Selwa - Isna Inv. 01 | 1 | 1
SOKHNA BRIDGE IPC03 | 3 | 3
200729
IPC#16 - Sokhna Port |  | 16
220721006
in&reSupply-SSC IPC2 | 2 | 2
In&ReApply(SSC)-IPC1 | 1 | 1
200651
200704
TR0047-IPC00001 | 1 | 1
inv ( 14 ) CS-20 | 14 | 14
inv ( 12 ) CS-20 | 12 | 12
k-muhammad sep2022
Kattameya IPC20 | 20 | 20
Plant supply Ro ipc3 | 3 | 3
ipc23 el maryotia | 23 | 23
Mini Core IPC10 | 10 | 10
EGAT watertank IPC13 | 13 | 13
200768
IPC005RMENEWGIZAHOSP | 5 | 5
PKG#189- IPC (15) | 15 | 15
abo ghaleb ipc04 | 4 | 4
200705
INV ( 18 ) GET | 18 | 18
K-Hassan Nov.2022
K-Muhammed Nov.2022
Katamya Urbnk ipc14 | 14 | 14
Mariotya ipc 19 | 19 | 19
MDF3 - IPC9 | 9 | 9
IPC00003 | 3 | 3
IPC#005 air defense |  | 5
IPC09-Exchange RME | 9 | 9
INV ( 3 ) HY Bark | 3 | 3
INV ( 2 ) HY Bark | 2 | 2
IPC0000016 | 16 | 16
IPC0019 | 19 | 19
k-hassan mar.2023
IPC 3 CFA | 3 | 3
DP World ph.2-IPC 1 | 1 | 1
MDF 2 - IPC 13 | 13 | 13
Minis MEP IPC7 | 7 | 7
MDF 3 IPC( 11) |  | 11
Air sihi IPC1 | 1 | 1
200812
200831
IPC0021 TR41 | 21 | 21
EMaarPKG#177 IPC 43 | 43 | 43
200873
IPC04 TR65 | 4 | 4
IPC10 TR55 | 10 | 10
ipc 3 elmahager | 3 | 3
200857
playa c104- ipc 7 | 7 | 7
IPC 3 TR0044 | 3 | 3
IPC003 TR43 | 3 | 3
Olympic L&L IPC1 | 1 | 1
200870
egat P supply ipc 1 | 1 | 1
Dp World ph2 ipc(6) | 6 | 6
mdf 2 ipc (17) | 17 | 17
k-salim aug.2023
BIS IPC (3) | 3 | 3
DP world ipc (5) | 5 | 5
Bis ipc ( 2) |  | 2
TAH ipc08 | 8 | 8
IPC 1 26th july | 1 | 1
IPC#03 Kilo 21 |  | 3
IPC#1 Credit |  | 1
310321
Playa c104 ipc 8 | 8 | 8
PLAYA - C072 IPC 3 | 3 | 3
200971
IPC10TR0060 | 10 | 10
gig-alaa aldin anwar
MOHAMED ALY2 FINAL
IPC02TR0081 | 2 | 2
sultana malak ipc03 | 3 | 3
middle east inv.4 | 4 | 4
Air dev shabkat IPC2 | 2 | 2
inv ( 2 ) vensia | 2 | 2
IPC0001 TR68 | 1 | 1
IPC01/BALTAT | 1 | 1
IPC-08 DIRLLER-FEB22 | 8 | 8
230000015
inv ( 1 ) MAHGER Br | 1 | 1
Baraka Fence ipc 5 | 5 | 5
playa-c045 ipc 5 | 5 | 5
IPC01TR0079 | 1 | 1
IPC002 TR70 | 2 | 2
Playa-c038 ipc 9 | 9 | 9
201059
Rent 11/2023
IPC14TR0053 | 14 | 14
IPC10 TR53 | 10 | 10
IPC003 TR54 | 3 | 3
PO 3100076248
pkg#220- ipc 4 | 4 | 4
Revamp ipc 8 | 8 | 8
IPC06TR0061 | 6 | 6
IPC14TR0064 | 14 | 14
IPC08TR0066 | 8 | 8
mdf local ipc 17 | 17 | 17
IPC12TR0060 | 12 | 12
ABO GHALEB ESC 1:11
Playa-c470 ipc 1 | 1 | 1
201235
wady elnatron ipc9 | 9 | 9
SPX INT.ROADS2 FINAL
MDf Local ipc 19 | 19 | 19
mariotya esc 1:22 es
Playa c469 - ipc 2 | 2 | 2
IPC21TR0064 | 21 | 21
IPC06TR0074 | 6 | 6
IPC03TR0079 | 3 | 3
Ora landscape-IPC18 | 18 | 18
V.O Smp2 ipc 1 | 1 | 1
Inv ( 3 ) Sentor | 3 | 3
Gig-el walid eid
Repair damage Gov2
Inv-04 | 4 | 4
201432
IPC09TR0088 | 9 | 9
INV ( 10 ) ALparco | 10 | 10
24000011
IPC15TR0051 | 15 | 15
Rent 10-2024 | 2024 | 2024
IPC07TR0074 | 7 | 7
IPC10TR0088 | 10 | 10
IPC18TR0060 | 18 | 18
4-2024 | 2024 | 2024
IPC24TR0053 | 24 | 24
IPC03TR0074 | 3 | 3
IPC19TR0060 | 19 | 19
IPC11TR0088 | 11 | 11
k-abdelwaha-11.24 | 11 | 11
Playa c470 ipc 6 | 6 | 6
INV(10 final ) Kemet | 10 | 10
Cr for the rest fund
JICA lot 02 Inv. 01 | 1 | 1
crMaryotya IPC06 | 6 | 6
IPC# FINAL SUHAG
3 Iskra
10001
cr-GAMSA-FURNITURE
cr5
IPC#006CR |  | 6
CR 1-2020 | 2020 | 2020
OB 1-Sud-usd
cr141
33
CR-MDF IPC13 | 13 | 13
CR.Al Lahoon Inv 01 | 1 | 1
32 closed
cr-ora zed2 ipc16 | 16 | 16
82
Angola 2.
10171
DEC ADJ 107
IPC#4&5 |  | 4
Adjust 180177
opening bal.
Cr Royal fin ipc43 | 43 | 43
cr 57-Aug
11453
97
CR. April Scrap.
Cr.Scrap. inv.7-2020 | 7 | 7
Assuit Inv.2 ded | 2 | 2
262
220621007
Cr.90
SH Inv.27&28 ded. | 27 | 27
CR.Ref-Ret-Benban2
deduct inv. 20 EGP | 20 | 20
D0011-OB-Dec-2020/Cr | 2020 | 2020
Vat Deduction526/538
CR ELCO EGAT IPC17 | 17 | 17
Egytech inv ded.
IPC#FINAL#El-Warraq
Close open inv.
17 closed
264
D.m Orange Invoice
94
Adj 180119-180120 | 180120 | 180120
sokhna credit memo
18 EGP - Shabab
80-Dec-2020. | 2020 | 2020
C.1
close 28
08/13/12/2021
close 48
CR.Ref Akhmm Asuit4T
S.Tax- (2+3 USD-Shab | 2 | 2
close10
1907220005
Ora Zed ipc 38 M | 38 | 38
Cr - inv 18 EGP rev1 | 18 | 18
01/13/08/2021
4 EUR - South Helwan
cr-haramin ipc01 | 1 | 1
Cr Adj Inv 8 Final | 8 | 8
5007 Credit
Cr.Inv ( 1 ) S09 | 1 | 1
D0034-OB-Dec-2020/Cr | 2020 | 2020
close inv.1902210011 | 1902210011 | 1902210011
close 27
Balance 2017 feb
inv 5 kwt flr cancle | 5 | 5
10441
CR.Ref Akhmm Asuit5T
06/13/03/2021
Cr.Inv ( 2 ) K 10 | 2 | 2
1103
27/13/05/2022
CR-KAFR SHOKR2
10259
CR-IPC#2 |  | 2
13092
Cr. Inv. 8 Bortsaid | 8 | 8
44 closed
DEC ADJ 65
final/closed
12082
Inv.18 - Lot 1 | 18 | 18
L967/2024
10207
IPC007TR55 | 7 | 7
DEC ADJ 23
CR- 16 EGP - West D. | 16 | 16
14/13/05/2021
10101
CRseashell playaIPC1 | 1 | 1
12868
Cancel Invoice
10428
220722001
13105
can. IPC01TR0089 | 1 | 1
RE 18
CR- 8 USD- Shabab | 8 | 8
close client
cr mariotya esc.19es
11 USD - Shabab
opening balanc
11505
INV ( 23 ) GET | 23 | 23
IPC12TR0062 | 12 | 12
1081
3480
close 47
10190
Discount interest
1131
2
D0008-OB-Dec-2020/Cr | 2020 | 2020
11021
DEC ADJ 100
cr-port said1-supply
180081
close66
C.ipc01 | 1 | 1
CR-IPC_1_R5
Inv. No. 3 - intrest |  | 3
303
JICA lot 02 Inv.$ 01
DEC ADJ 11
Cr-م 10 كفر شكر | 10 | 10
void 33 maghagh 9..
Car-Dep Mar. 2021
close 62
CR Samanoud 5 inv.81 | 81 | 81
D0014-OB-Dec-2020/Cr | 2020 | 2020
PV Dec -amortization
Inv. 17 Fin PIP EAST | 17 | 17
1007
Car-Dep APR. 2021
OB RT 015
Cancel in. 25&26 EGP
13134
2007220003
2011220006
85-Dec-2020 | 2020 | 2020
CR-IPC#4 |  | 4
15
Cr Adj inv 2 | 2 | 2
P-44-EGY اتحاد تشيد | 44 | 44
cr HY
DEC ADJ 92
2009220001
CR1IPC_5_Gama_Saray
Scrap Inv. 18/2020 | 18 | 18
Soc.2020 تشيد مرسى
DEC ADJ 46
cr99
38
DEC ADJ 85
CM
65
Balance 2016 9
ancel. inv.19-20 USD | 19 | 19
OB-RE-EL Kayaan
CR.2 benban Lot 2
close inv.180137 | 180137 | 180137
Reclass Adj. PA
ClsMozaRet
200745
63
CR.P-2-10 AccRev | 2 | 2
2008220004
Close Root steel bal
CR-INV ( 2 ) S.UNIV | 2 | 2
Cr.IPC_5_Gama_salary
11646
close18
CR-19 EGP- Shabab | 19 | 19
Close Lina balance
19/13/07/2021
cr Soc inv 48 As | 48 | 48
IPC#4 CFA |  | 4
Cr for other deduct
ANG-Cam-Inv 4 - part | 4 | 4
MIDA Sply.Inv.2Ret. | 2 | 2
DEC ADJ 48
DEC ADJ 29
DM-01 March 2021 | 1 | 1
C.INV.2 | 2 | 2
95
11520
D0027-OB-Dec-2020/Cr | 2020 | 2020
Collec Abu Quir 118
DEC ADJ 38
13113
DEC ADJ 82
Libya Eqpt.3 Co.3
IPC#22 CR |  | 22
cr-SPX ROADS 2 FINAL
Deduct.Inv25&26 EGP | 25 | 25
CR-Close.USD AR Fees
Inv.6 – Lot 2 RDC | 6 | 6
Cr. Amend - Ras Gha
250
Cr . Inv ( 1 ) S 05 | 1 | 1
10491
CR - 11 USD- Shabab | 11 | 11
2104220006
-1,254,000.00 | 1 | 1
Cr-k-huissen-mar22
Sultana mlk22 2final
close64
CR Akhmem Asuit3T
DEC ADJ 66
1032
2009220004
Cr Adj inv 1 | 1 | 1
55
Cr.Inv,4 usd Borg Ar | 4 | 4
mos4
CANCEL IPC12 | 12 | 12
Credut Memo IPC00015 | 15 | 15
CR Material ipc3 | 3 | 3
Cr.Memo-Expenses.
Ref.soci 51 Quena
close78
05/13/06/2021
10301
9
Inv.6&7 Deductions | 6 | 6
IPC no25
inv 1 kwt flr cancle | 1 | 1
cr ipc 5 luxoroff | 5 | 5
21/13/07/2021
Cr 27:31
255
Adj.180178
ENG/040 C
67
Cr for-other deduct
10258
Cr. Inv ( 5 ) A.S | 5 | 5
Cr 25/2019 Scrap
OB-ST-4-03-2017 | 4 | 4
Cr soc inv 26 $ | 26 | 26
D0020-OB-Dec-2020/Cr | 2020 | 2020
cancel inv 8 | 8 | 8
Deduct Customes
Cr adj inv12 | 12 | 12
RME-OC Po 647
close21
SH inv.39 deductions | 39 | 39
DEC ADJ 108
1006
Cr.Cr. Soc Inv. 48 | 48 | 48
2008220002
Cancel inv:Lot 19&23
Balance.
Cr-36 EGP-Giza I&II | 36 | 36
CR-IPC#3 |  | 3
CR inv ( 13 ) | 13 | 13
de. transfer to EGP.
cRME/AJC/EM/11057/24
D0028-OB-Dec-202/Cr | 202 | 202
CR-IPC#5&6 |  | 5
adjust
63-SEP -2020 | 2020 | 2020
rev.( 8 EGP-West D.)
OB 3
opening . balance
cr(OB)
200206
cr31/12/2017
Eng Stamp 39 to 43 s
180063 rev.
Inv-01 MOC | 1 | 1
Haramin ipc01 | 1 | 1
IPC01TR0089 | 1 | 1
Ora Ph1 ipc (22) | 22 | 22
PKG#220- IPC2 | 2 | 2
INV ( 6 ) GET | 6 | 6
INV ( 14 ) 28-10-20 | 14 | 14
inv ( 1) sixty | 1 | 1
41- مردودات بنكية
october tunnel ipc01 | 1 | 1
MDF_ IPC 13 | 13 | 13
Recla Debit Note#7
11745
220621003
IPC#2-Luxoroffshor |  | 2
4 carsfoe sale
11449
50
56
Kafr Shokr - IPC01 | 1 | 1
2012210037
cancell credit memo
D0033-OB-Dec-2020 | 2020 | 2020
D0015-OB-Dec-2020 | 2020 | 2020
D0006-OB-Dec-2020 | 2020 | 2020
D0046 OB-Dec-2020 | 2020 | 2020
D0009-OB-Dec-2020 | 2020 | 2020
D0045-OB-Dec-2020 | 2020 | 2020
Al Lahoon Sub Inv 01 | 1 | 1
IPC_3_Saray_Gama
IPC12_sodic_east | 12 | 12
20-2020 | 2020 | 2020
5-2020 | 2020 | 2020
497
024/2020
023/2020
1909210007
1909210005
1909210003
5001
1-19-FEB | 19 | 19
67
1907210007
1904210014
180178
Balance ASF
P-09-13 AccRev | 9 | 9
Ret. Balance..
p-10-16 ADJ | 10 | 10
DM for wrong credit
17 EGP-West Domiat
Adj.Inv. 17 | 17 | 17
Adj Inv 5 | 5 | 5
180070
180118
113
96
28
27
117
100
2
79
78
69
6+ EGP/ STF (Italy)
16-1 EGP / STF( Ital | 1 | 1
2 EGP - Asuit
10 USD - Cairo South
CLOSE 10
Inv. 6 Akhmem Qena | 6 | 6
ٍSoc 72 Asuit 10
adj. 180010 & 180013
4-132KVA-J | 132 | 132
Inv.5 PIP West | 5 | 5
Inv 1 El Tbeen | 1 | 1
Inv 2 Abo Zaabl | 2 | 2
33 maghagh 9..
Final*
R 1
Forex Receivable
DEC ADJ 103
39
amend 2 N.G
DEC ADJ 24
1005
1 USD - Banha 118
24 A
1054
ClsMozaAdv
48/13/11/2019 ٌOlsAp
30-132KVA-J | 132 | 132
Aply advance - Memo
4 EGP - EL Tebbin
5 EGP - Suez Gulf
27 Etay 8
28 Maghagha 8
7 USD - Hitachi
8 USD - Hitachi
(15) sodic club |  | 15
OB -10 | 10 | 10
424 EGP abu qeir 118
1050
431 EGP abu qeir 118
400 USD Avice ZTPC
new acpita tbeen 1
15 Zona
Adv. Balance 2
DEC ADJ 2
31 Etay 9
Social 37 Bnha 6
10288
ISE-CW-EURO-01 | 1 | 1
TAM-CW-EGP-10 | 10 | 10
(13)cw mostsmrin |  | 13
Soc Inv 42 Bnha 8 | 42 | 42
close un appl.ecot
180115
180003
inv no(2 Euro-Iskrae | 2 | 2
10015
Banha-Zagazg Inv.01 | 1 | 1
49 Euro Abo Qir 117
H,A(2)-PO52/516 |  | 2
10027
Collection
OB 2
OB 1
Inv 4,5,6 Comcavi | 4 | 4
(2) Kanteen |  | 2
6 EUR Iskraemco
Apachi Inv No PC.#24
Apachi Inv No PC.#22
مستخلص 2 كيان ردم 2 | 2 | 2
31/P/10/ER/2017/USD
4 EUR South Helwan
10084
33/P/10/ER/2017/USD
Soc. 56 Asuit
Ret.Itay sub
Soc.Inv.61wadi 18 | 61 | 61
INV PMS S.A
Inv No3 ElKean 220 | 3 | 3
10264
OB-RE-Sharm El Shikh
7 EGP - Cairo North
8 USD - Cairo South
Inv No A2017459 | 2017459 | 2017459
كانتين 11
Crane rent to Hitach
Ret. Kafr Elzayat
Banha Inv
(3) كانتين يناير |  | 3
Inv. 12 Mostakbal | 12 | 12
Inv.4 Elkayan | 4 | 4
Inv No 6 ElKean 220 | 6 | 6
Commercial fees SH-
13032
Ret... Balance...
k-a.osman- apr
Soc 3 Asuit
Soc 11 east asuit
202
Ret.. Balance
10415
soc 6-7-8-9-10-11 as | 7 | 7
14/13/6/2018
10435
PKG#62- IPC 14 | 14 | 14
1 EGP-Toyota-Helwan
CT Turns Ratio Test
K-M.KH-MANISITERS.9
10418
MVR Accomodation Exp
10494
K-AHMED OSMAN-ROYAL
Hashim.Kanteen.Jazi
Social 10 matamer 89
Soc1-7 Asuit Akhmem | 7 | 7
Inv.6 Borg Alarab | 6 | 6
DM 12 Abo Elmatamer
10409
k.khalifa.ministiry
Soci.$11-16:23Qena | 16 | 16
Soc 11 abo elmtamer
Soc14final Asuit Se
OB RT 002
10536
10420
10408
OB ME005sp
Coll of Scrap Attaqa
Kayan MEP- ipc 4 | 4 | 4
DP WORLD-IPC09 | 9 | 9
DP World IPC032 | 32 | 32
(3)Sobra-banha |  | 3
7/13/01/2019
K-M.mansor-kayan-Jan
Toyota inv.2 | 2 | 2
Toyota inv.3 | 3 | 3
K-H.mahmoud-jazimall
K-M.mansor-Kayan-Feb
503
502
490
PKG#144-IPC09 | 9 | 9
Refund 14/13/02/2019
220
10581
Insu.Inv. 13 Samnood | 13 | 13
IPC#17 |  | 17
232
Benban Lot 2 Inv. 33 | 33 | 33
Benban Lot 2 Inv. 10 | 10 | 10
K-H.mnsor-sewdyuni-5 | 5 | 5
K-M.mansour-kayan-05 | 5 | 5
K-Hassan-R05-May2019
kanten-royalcity-may
OB-SI-PKG#45
OB-MOS-PKG#45
11010
Inv. 8 Scrap 2019 | 8 | 8
10595
Inv 12/2019 Scrز | 12 | 12
1904210002
1903210009
E&W-Ministries-June
E&W-consumption-May
10697
10700
Social 48 Assuit
Ministrie-district07
10709
Compensation Itay
Soc inv 1to49 Asuit | 1 | 1
Kanteen-Sodic-July19
1 USD - Suez Steel
260
10136
10912
16-19June | 19 | 19
272
20-19Jul | 19 | 19
Inv. 04 Farm | 4 | 4
Kanteen-Olympic-Oct
Dedu stamp
ALALAMEN SUPPLY-01 | 1 | 1
10996
35-19 oct | 19 | 19
1908210014
BSF- CLIAM-EGP-01 | 1 | 1
H,A/IPC03/PO52/516 | 3 | 3
517
Kanteen-kayan-Nov-19 | 19 | 19
11035
28/13/11/2019-KwdRet
61-19 Dec | 19 | 19
11080
11017
Tunnel Inv. 4 | 4 | 4
PKG#107-IPC18 | 18 | 18
69-19 Dec | 19 | 19
H,A-IPC04-PO52/516 | 4 | 4
-664.41 | 664 | 664
10833
11078
14-sals
1907210009
1901210004
293
289
Scrap Lot. 07
Refund 12/13/12/2019
IPC#2 |  | 2
Scrap Lot 08-2 | 2 | 2
Kanteen-Kayan-Jan-20 | 20 | 20
Soci. 4-5Banysof 358 | 5 | 5
327
292
MP -09 | 9 | 9
Abolila Zafra Instal
Ref. Ghareeb
Lot. 02 - 2 | 2 | 2
Soc 49 Quana labour
CFC-IPC11 | 11 | 11
11012
67-19 Dec | 19 | 19
4 Jan 2020
3 Jan 2020
Kanteen-Uni-Feb-2020 | 2020 | 2020
Kanteen-R05-Feb-2020 | 2020 | 2020
Toshka Sub Inv. 17 $ | 17 | 17
Inv.7 Phosfat | 7 | 7
11081
CFC IPC020 | 20 | 20
75-19 Dec | 19 | 19
7 Jan 2020
10019
titra-ovm-ipc01-dec | 1 | 1
invoice (2) tetra | 2 | 2
ENG-023/Rev0 | 23 | 23
2002210023
10022
343
322
308
326
2003210012
11181
اعمال الوزن للخردة
349
2004210001
354
40-Jun-2020 | 2020 | 2020
IPC#1 |  | 1
Kanteen-Sodic-Apr-20 | 20 | 20
2006210005
34-2020 | 2020 | 2020
2007210006
Eng-029 Rev0 | 29 | 29
Eng/030
Kanteen-Wezarat-Aug
10148
1908210012
62-SEP-2020 | 2020 | 2020
61-Sep-2020 | 2020 | 2020
R05(2) IPC 47 | 47 | 47
2003210005
SCD1/007
26-2020 | 2020 | 2020
2009210009
ENG-031 | 31 | 31
11290
10242
47-2020 | 2020 | 2020
Ora ph1 ipc 35 | 35 | 35
Pkg 162- IPC 19 | 19 | 19
JV-AC-EE-Inv-001 | 1 | 1
77-Nov-2020 | 2020 | 2020
Car Sales 629
378
387
FL- invoice
49-2020 | 2020 | 2020
inv ( 26 )23-12-2020 | 26 | 26
Abo-Qair-Temay Inv.1 | 1 | 1
11647
11681
Inv. 5 Sugar 33 OHTL | 5 | 5
8-2021 | 2021 | 2021
Al-Lahoon Sub Inv 05 | 5 | 5
11807
FISH MARKER-MEP+1FIN
Qattamya - 2 | 2 | 2
2005210007
IPC#01 - Mansoura |  | 1
Scrap Inv. 22/2020 | 22 | 22
Toshka Sub 4 Inv.2 $ | 2 | 2
398
P-45-Portsaid Inv.02 | 2 | 2
Cr. Adv West Port sa
SHROUK BDRIDG-IPC03 | 3 | 3
CR-d. West Port said
200159
INVOICE(4) CLEARANCE | 4 | 4
Scrap Inv. 03/2021 | 3 | 3
Reailway PSP Inv. 03 | 3 | 3
TETRA-MK4-PO43868
10204
12063
inv ( 14 ) | 14 | 14
MIDA Ins. Inv.6 | 6 | 6
Ref.Ret Quana akh
Ora - 4 | 4 | 4
11962
Inv.17 - Lot 1 | 17 | 17
411
Ref.Ret Asuit akh 1
D.M Railway Exp-
12284
Minis-Kanten-July21
Scrap Sales El-Doha.
10682
416
16-2021 | 2021 | 2021
RefRet11/13/08/2021
12162
26-9-2021 | 9 | 9
Kanten Sodic2 Sep 21
Colection2 R05-09/21 | 9 | 9
IPC#04 Moneeb Bridge |  | 4
10924
200376
200333
WALDORF ASTORIA IPC2 | 2 | 2
Ret Zafra-B-Suef T
10965
10963
Ref.2 benban Lot 2 T
pkg#178 ipc07 | 7 | 7
Ret Qen-akh 9 T
Kanteen DEC21 Minist
ref,ret,Qena - Akhme
elmarg ipc09 | 9 | 9
454
Invoice USD 16/2021
inv ( 5 ) 12-12-2021 | 5 | 5
inv ( 1 ) 9-12-2021 | 1 | 1
12482
k-ora0jan2022
ENG/050
11902
IPC-17-SARAY | 17 | 17
445
13بشاى
11285
432
438
T14-2022 | 2022 | 2022
T 5-2022 | 2022 | 2022
11322
Selling of LOt 1
Eng/052
11445
Material EES1
Material EES4
IPC-1-New Giza | 1 | 1
11461
Suez S4 Inv. 18 | 18 | 18
11500
ITS Solar Inv. 01 | 1 | 1
001
12749
81
465
kafr shokr IPC07 | 7 | 7
11587
Marsa Alam EGP Inv 6 | 6 | 6
Marsa Alam EGP Inv11 | 11 | 11
Marsa Alam EGP Inv 8 | 8 | 8
07/13/06/2022 Gh.Ret
11662
11702
PKG#177 IPC 33+34 | 33 | 33
Invoice # 39 Assuit
200688
Ref-Ret-Benban-lot2
IPC-3-NEW GIZA | 3 | 3
220721002
K-SALIM JUL2022
IPC-4-NEW GIZA | 4 | 4
2 EGP- West Domiat
200627
200765
03
37
k-muhammed aug 2022
Water tank IPC 11+ | 11 | 11
K-HUSSAIN SEP2022
kantine.4 -40 | 40 | 40
200706
INV ( 19 ) GET | 19 | 19
IPC003 | 3 | 3
k-hussain oct.2022
katameya urbnk ipc15 | 15 | 15
IPC00006 | 6 | 6
Olympic IPC1 | 1 | 1
k-salim muh feb.2023
k-salim mar.2023
Oly fin IPC4 | 4 | 4
EDECS-ipc 3 | 3 | 3
EDECS-ipc 2 | 2 | 2
Egat piping ipc 3 | 3 | 3
R.O sup pri adj.ipc2 | 2 | 2
k-salim april.2023
200874
IPC3-TR55 | 3 | 3
SPORT HALL IPC 07 | 7 | 7
200858
IPC004 TR55 | 4 | 4
Mdf Factory 3 ipc 12 | 12 | 12
200951
200911
IPC05TR0065 | 5 | 5
k-salim june.2023
230000009
Air Tahsen IPC Fin
IPC0022 TR41 | 22 | 22
IPC06 TR0055 | 6 | 6
200851
200850
200877
bekia inv.1 | 1 | 1
230000011
k-mustafa aug.2023
Eipico ipc (9) | 9 | 9
200953
playa-c045 ipc 4 | 4 | 4
200992
200991
playa-c072 ipc (1) | 1 | 1
Playa-c038 ipc(4) | 4 | 4
Rent 7TH maadi
Air Dev Allom IPC2 | 2 | 2
ipc 5 elmahager | 5 | 5
200993
IPC03TR0077 | 3 | 3
IPC08TR0064 | 8 | 8
Mdf Equip ipc 20 | 20 | 20
Air Dev sihi IPC2 | 2 | 2
IPC(2) / PO26601 | 2 | 2
DRILLER IPC1/PO27960 | 1 | 1
Inv ( 4 ) A.S | 4 | 4
IPC03TR0062 | 3 | 3
201011
IPC006 TR48 | 6 | 6
IPC28TR0038 | 28 | 28
ipc16 katamya urbnk | 16 | 16
ODP Dry port ipc 4 | 4 | 4
ipc final..2 elwaraq
Driller inv.dec.23
Playa-c045 ipc 7 | 7 | 7
IPC21TR0046 | 21 | 21
IPC07 | 7 | 7
24000001
k-abdelwahab jan.24
Urbn-k ipc 17 | 17 | 17
Rent 1/2024
IPC16TR0053 | 16 | 16
IPC06TR0071 | 6 | 6
mdf local ipc 16 | 16 | 16
IPC30TR0038 | 30 | 30
sokhna bri ipc 20 | 20 | 20
Mini Long lead IPC5 | 5 | 5
sokhna esc.16
Urbnk ipc 18 | 18 | 18
Inv-1 | 1 | 1
IPC19TR0064 | 19 | 19
k-adel wahab june.24
Remaning Inv-2 | 2 | 2
k-hassan-june.24
24000005
RENT-007 | 7 | 7
KHATATBA IPC10+11+12 | 10 | 10
ORA PH1 IPC 40 | 40 | 40
sultana malak Damage
201292
IPC20TR0064 | 20 | 20
K-HASSAN JUL.24
playa - c469 ipc4 | 4 | 4
120-canteen
K-ABDELWAHAB JUL.24
Gig-El walid eid 2
Emaar pkg#101 ipc 24 | 24 | 24
IPC01TR0094 | 1 | 1
140-Canteen
Inv-01 | 1 | 1
Sales Sep.24 Comoros
RME-RS inv.2 | 2 | 2
IPC22TR0055 | 22 | 22
abo ghaleb esc.1:11
EDNC PO NO. (3349T)
IPC04TR0084 | 4 | 4
IPC10TR0084 | 10 | 10
IPC12TR0061 | 12 | 12
Orient Oct.24
IPC16TR0039 | 16 | 16
IPC21(1)TR0053 | 21 | 21
IPC24TR0064 | 24 | 24
IPC#19 wady elnatron |  | 19
IPC25TR0064 | 25 | 25
WADY ELNATROON IPC12 | 12 | 12
157-canteen
K0004 Inv-07 | 7 | 7
Marsa Alam USD Inv 4 | 4 | 4
DECADJ 81
CR-IPC 4 | 4 | 4
Libya Eqpt.2:6 Co.2
16
10074
4-closed
cost abu quir
CR-INV(1)LINX | 1 | 1
Close Ret. balance
30 Euro - Banha 117
INV ( 9 ) ALparco | 9 | 9
CR PKG#220- IPC 2 | 2 | 2
CR-Elsewedy HQ-IPC24 | 24 | 24
8-2023 | 2023 | 2023
DEC ADJ 102
FPC - Orascom HA
12689
022/2020cncl
cr8
Cr 16
CR-IPC#5 |  | 5
247
33/13/08/2021
CR INV ( 9 ) KEMET | 9 | 9
Cr-Sales tax USD inv
06/13/04/2022
37
CSI+WHT+Stamp
DEC ADJ6
2103220004
CR - FL invoice
5 Euro-South Helwan
2103210013
DEC ADJ 88
12995
inv ( 3 ) W. Natron | 3 | 3
003/13/01/2022
28
246
crsd3
Kanteen-Sodic-Marcr
9 USD - West Domiat
10528
01/13/06/2022
close Adj Inv 10 | 10 | 10
cr(1) ALAMAL BRIDGE |  | 1
CR MOC Inv-01 | 1 | 1
Cr-S.Tax-(3 USD-Domi | 3 | 3
IPC#4 - Maragha Brid |  | 4
Scrap Inv. 11/2021 | 11 | 11
Stamp Tax
OB-001 | 1 | 1
OB-ST-Sodic Dahshour
D0023-OB-Dec-2020/Cr | 2020 | 2020
Scrap Inv. 07/2022 | 7 | 7
CR 6
Inv 20/2019 Scrap | 20 | 20
10 USD - Shabab
cr39-Jun-2020 | 2020 | 2020
23-19JUL | 19 | 19
xx
LOC/014CR
02/13/01/2022
Advance for Shuqaiq
Cr-ORA PH.2-ipc13 | 13 | 13
CR_INV.13 | 13 | 13
18 EGP - West Domiat
DEC ADJ 18
20 EGP - Shabab
Ministiry MEP ipc09 | 9 | 9
D0041-OB-Dec-2020/Cr | 2020 | 2020
Inv-001 MOC | 1 | 1
2012220003
cr10
Adj on inv.1 lot 1 | 1 | 1
Balance 7
10433
18/13/07/2021*
10708
01/13/04/2021
CR_INV.7 | 7 | 7
DEC ADJ 47
P-53-EGY تشيد و بناء | 53 | 53
1aas
DebitNote#14616#
opening balan.
Other Revenu Zonafra
241
DR.Pump Obour Inv.6 | 6 | 6
Cr inv ( 1 ) sixty | 1 | 1
32/13/09/2021
CR.Ret Asuit akh 5
IPC#2#Abo Ghaleb cr |  | 2
10892
D0015-OB-Dec-20/Cr | 20 | 20
Inv# 21 USD | 21 | 21
66
26/2019 Scrap
220322002
IMP-61 | 61 | 61
CM-1 | 1 | 1
S.Tax-(4+6 USD-Domi | 4 | 4
35
DEC ADJ 64
Cancel IPC_1_GRowad
2105210018
476
10506
DEC ADJ 87
CR_inv. 8 | 8 | 8
mos 2 closed
2004220006
10367
Cr. Inv. 1 Temmay | 1 | 1
Cr-dividends
Cr-Memo-Inv#17 EGP | 17 | 17
Inv. No. 3 -Int.part |  | 3
Cr.Tos Lot6 Inv.4 | 4 | 4
D0012-OB-Dec-2020/Cr | 2020 | 2020
D.N Insurance JICA++
243
Fees:4101505764/1&2
CR 10
Cr 4-2021 | 2021 | 2021
6-2023 | 2023 | 2023
Cr.Inv,6 usd Borg Ar | 6 | 6
CR.TR0029DEC.Closing
265
Cancel invoice Lot14
inv no 15.2 d0073 | 15 | 15
CR17-19jun2 | 19 | 19
Attaqa PV amortize
CR.TR0010CLOSING.DEC
Cancel invoice Lot17
cr inv ( 3 ) | 3 | 3
reclass receivable
D0022-OB-Dec-2020/Cr | 2020 | 2020
42
IPC01TR0090 | 1 | 1
CR.ADJ.inv.20 | 20 | 20
cancel inv. 9 | 9 | 9
CR 8
023/2020cncl
CANCELLED
P-10-EGY اتحاد تشيد | 10 | 10
11522
Adjust Inv No:220221 | 220221 | 220221
11584
Cancel invoice Lot13
CR- CSI & LF
1 EGP - Asuit
OB0006
Cr-memo W.hold 9 EGP
10 EGP- Suez Gulf
Inv Comcavi Q4
32/13/06/2022
2005220004
08/13/12/21
34 closed
31 EUR - Banha 117 )
Cr Inv.6 Phosfat | 6 | 6
10 USD - West Domiat
Retention OB
OB-RE-El Mosstas
Scrap inv 28/2019 | 28 | 28
OB RT 010
56
DEC ADJ 16
CrAdj Inv. 21 | 21 | 21
Cr- 5 + 7 USD-Shabab | 5 | 5
close 15
CR cairo alex ipc41 | 41 | 41
Cr
P-46-18 تشيد و بناء | 46 | 46
IPC10TR0062 | 10 | 10
CR.Fayoum Inv.01 | 1 | 1
CrINV( 1 ) R08 - K12 | 1 | 1
3
D.N Railway31-8-202 | 8 | 8
CR.Ret Qen
CR-16 EGP- West D. | 16 | 16
CR.Ret Qen-akh
Car-Dep Jun. 2021
CN Siemens Inv Nubar
Inv13 SH EUR | 13 | 13
CR-40 EGP-Giza N.III | 40 | 40
7
CR IPC#1 HSR |  | 1
OB-MOS-Beni Suif
OB-Retention
cr9
CR- 5 USD - Shabab | 5 | 5
4-132KVA-J-del | 132 | 132
P-37-EGY اتحاد تشيد | 37 | 37
INV ( 13 fin ) Hyper | 13 | 13
13072
11033
180018
180016
02/13/01/2021
D.M
16 feb 20
11748
IPC#003#RABAGH |  | 3
cr-36-19 oct | 36 | 36
CR.TR0020CLOSING.DEC
inv 2 kwt flr cancle | 2 | 2
Cr Adj Inv 8 | 8 | 8
20 EGP - West Domiat
10945
CR-MDF FACTORY-IPC07 | 7 | 7
dividend settlement
Adjust 1024 billin
OB -2 | 2 | 2
Cr-S.Tax- 4 invoices | 4 | 4
CR Balance
CR3-19-mar. | 19 | 19
Abu qir Invoice
9 EGP- Suez Gulf
Balance Feb 2017
DEC ADJ 50
Invoice No: 1042/13
adv on inv(65USD-Diw | 65 | 65
Scrap 27/2019
CN DIVIDANCE
Cr.Inv,5 usd Borg Ar | 5 | 5
180021
Reclass Debit.Note#7
CR-DP WORLD-IPC06 | 6 | 6
Voiding Forklift Inv
tetra-ipc01cm | 1 | 1
close 44
اتحاد تشيد و بناء 21
Credit FPC04
100
inv ( 10 ) Captal Cr | 10 | 10
DEC ADJ 99
Cr - ( WHT + Stamp )
CR IPC#7 |  | 7
5004 Credit
INV ( 1 ) R08 - K12 | 1 | 1
Acwa Power ipc 1 | 1 | 1
ABO SHANAB IPC 2 | 2 | 2
IPC13TR53 | 13 | 13
INV 1 | 1 | 1
mariotya ipc17 zomor | 17 | 17
INV (3 ) | 3 | 3
ora zed (2) ipc 16 | 16 | 16
IPC 3 NRCC | 3 | 3
11561
Inv. 26 | 26 | 26
close cancel
D0014-OB-Dec-2020 | 2020 | 2020
D0041-OB-Dec-2020 | 2020 | 2020
Adv. ITS Inv. 01 | 1 | 1
13
D0037-OB-Dec-2020 | 2020 | 2020
1-2021 | 2021 | 2021
80-Dec-2020 | 2020 | 2020
63-ٍSEP-2020 | 2020 | 2020
57-Aug
Kanteen-Sodic-Mar-20 | 20 | 20
21 Mar 20
2001210018
2001210010
470
25/2019 Scarp
10170
1907210004
180120
1902210011
In 9+10 Beni Suef
Soc Inv 49 Asuit | 49 | 49
Soc Inv 44 To 47 Qun | 44 | 44
Adj. Inv. 15 | 15 | 15
Adj. Inv. 22 | 22 | 22
Customs Elshabab
p-10-16 ADJ 2 | 10 | 10
Close credit memo
DR-Sales tax USD inv
DM-CR-19 EGP- Shabab | 19 | 19
15 EGP- Shabab
Inv, 7 usd Borg Arab | 7 | 7
180145
180144
5 EGP Cement
4 EGP - Cement
DR - VAT- Egytech 04
Deposit for gas and
Commercial fees
Adj Inv 4 | 4 | 4
Soc.$4-8:19Assuit | 8 | 8
April Scrap. 2
441 EGP-Abo qeir 118
112
120
19
22
38
26
99
3
20
93
32
98
124
10
DR - VAT- Egytech 02
16-3 EGP/STF ( Italy | 3 | 3
5 USD - Cairo South
Inv.13 Akhmem Qena | 13 | 13
Cr. 1 Sett. W Cancel
final pkg#17
per 1
Balance Feb17
re-5-Euro-South helw | 5 | 5
452 Euro - Avice
451 USD - Avice
450 USD - Avice

## collection only
Project | Invoice No. | invoice round down | concact | Collection amount
6TH October tunnel | 1 | 1 | 6TH October tunnel1 | 1520548
6TH October tunnel | 2 | 2 | 6TH October tunnel2 | 3208372.9
6TH October tunnel | 2.1 | 2 | 6TH October tunnel2 | 300000
6TH October tunnel | 3 | 3 | 6TH October tunnel3 | 0.001
6TH October tunnel | 4 | 4 | 6TH October tunnel4 | 5155347
6TH October tunnel | 5 | 5 | 6TH October tunnel5 | 2856009
6TH October tunnel | 6 | 6 | 6TH October tunnel6 | 1337162.6
Abo Ghaleb Bridge | 1 | 1 | Abo Ghaleb Bridge1 | 175270.85
Abo Ghaleb Bridge | 2 | 2 | Abo Ghaleb Bridge2 | 2494611.027
Abo Ghaleb Bridge | 3 | 3 | Abo Ghaleb Bridge3 | 2045810.923
Abo Ghaleb Bridge | 4 | 4 | Abo Ghaleb Bridge4 | 12711007.22
Abo Ghaleb Bridge | 5 | 5 | Abo Ghaleb Bridge5 | 1645829.28
Abo Ghaleb Bridge | 6 | 6 | Abo Ghaleb Bridge6 | 0.0001
AEON | 1 | 1 | AEON1 | 1264914.16
AEON | 2 | 2 | AEON2 | 1513146.56
AEON | 3 | 3 | AEON3 | 780253.07
AEON | 4 | 4 | AEON4 | 484406.35
Al Jazi | 1 | 1 | Al Jazi1 | 2199495
Al Jazi | 2 | 2 | Al Jazi2 | 2330066
Al Jazi | 3 | 3 | Al Jazi3 | 3090062.9
Al Jazi | 4 | 4 | Al Jazi4 | 3867947.36
Al Jazi | 5 | 5 | Al Jazi5 | 4039155
Al Jazi | 6 | 6 | Al Jazi6 | 2383592
Al Jazi | 7 | 7 | Al Jazi7 | 4138160
Al Jazi | 8 | 8 | Al Jazi8 | 6905844.19
Al Jazi | 9 | 9 | Al Jazi9 | 1762571
Al Jazi | 10 | 10 | Al Jazi10 | 2302251
Al Jazi | 11 | 11 | Al Jazi11 | 3838772.36
Al Jazi | 12 | 12 | Al Jazi12 | 922154
Al Jazi | 13 | 13 | Al Jazi13 | 2994292.79
Al Jazi | 14 | 14 | Al Jazi14 | 1629015.64
Al Jazi | 15 | 15 | Al Jazi15 | 2107757
Al Jazi | 16 | 16 | Al Jazi16 | 120989.08
Al Jazi | 17 | 17 | Al Jazi17 | 2935343.72
Al Jazi | 18 | 18 | Al Jazi18 | 2748544.1
Al Jazi | 19 | 19 | Al Jazi19 | 2000000
Al Jazi | 19.1 | 19 | Al Jazi19 | 1100493.11
Al Jazi | 20 | 20 | Al Jazi20 | 371543.5
Al Jazi | 21 | 21 | Al Jazi21 | 0.0001
Al Jazi | 22 | 22 | Al Jazi22 | 2500000
Al Jazi | 22.1 | 22 | Al Jazi22 | 2000000
Al Jazi | 22.2 | 22 | Al Jazi22 | 848568.49
Al Jazi | 22.3 | 22 | Al Jazi22 | 1000000
Al Jazi | 22.4 | 22 | Al Jazi22 | 1000000
Al Jazi | 22.5 | 22 | Al Jazi22 | 1242872
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 90608.89
Al Jazi - Center Zone | 2 | 2 | Al Jazi - Center Zone2 | 1686320.29
Al Jazi - Center Zone | 3 | 3 | Al Jazi - Center Zone3 | 360179.68
Al Jazi - Center Zone | 4 | 4 | Al Jazi - Center Zone4 | 370581.69
Al Jazi - Center Zone | 5 | 5 | Al Jazi - Center Zone5 | 858100
Al Jazi - Center Zone | 6 | 6 | Al Jazi - Center Zone6 | -0.01
Al Jazi - Center Zone | 7 | 7 | Al Jazi - Center Zone7 | 151431.32
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 14666580.12
Al Jazi - Social Insurance | 1 | 1 | Al Jazi - Social Insurance1 | 266994
Al Jazi | 1 | 1 | Al Jazi1 | 53125000
Alfa Lab | 1 | 1 | Alfa Lab1 | 1459340
Allegria-New Modifications | 1 | 1 | Allegria-New Modifications1 | 659568.2
Astoria - Sharm | 2 | 2 | Astoria - Sharm2 | 837813.8
Astoria - Sharm | 3 | 3 | Astoria - Sharm3 | 269728
Astoria - Sharm | 4 | 4 | Astoria - Sharm4 | 1641108
Astoria - Sharm | 5 | 5 | Astoria - Sharm5 | 709627
Astoria - Sharm | 6 | 6 | Astoria - Sharm6 | 244817
Astoria - Sharm | 7 | 7 | Astoria - Sharm7 | 654151
Astoria - Sharm | 8 | 8 | Astoria - Sharm8 | 1160836
Astoria - Sharm | 1 | 1 | Astoria - Sharm1 | 1365525
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 4511122
Astoria Hotel | 2 | 2 | Astoria Hotel2 | 2448868
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 5421697
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 4634265
Astoria Hotel | 5 | 5 | Astoria Hotel5 | 5818860
Astoria Hotel | 6 | 6 | Astoria Hotel6 | 3446328.13
Astoria Hotel | 6.1 | 6 | Astoria Hotel6 | 5000000
Astoria Hotel | 7 | 7 | Astoria Hotel7 | 8710615
Astoria Hotel | 8 | 8 | Astoria Hotel8 | 2805916
Astoria Hotel | 9 | 9 | Astoria Hotel9 | 2000000
Astoria Hotel | 9.1 | 9 | Astoria Hotel9 | 4286403
Astoria Hotel | 10 | 10 | Astoria Hotel10 | 4982321
Astoria Hotel | 11 | 11 | Astoria Hotel11 | 10757000
Astoria Hotel | 12 | 12 | Astoria Hotel12 | 2603000
Astoria Hotel | 13 | 13 | Astoria Hotel13 | 5389256
Astoria Hotel | 14 | 14 | Astoria Hotel14 | 6216098
Astoria Hotel | 15 | 15 | Astoria Hotel15 | 4185662
Astoria Hotel | 16 | 16 | Astoria Hotel16 | 3225683
Astoria Hotel | 17 | 17 | Astoria Hotel17 | 2804159
Astoria Hotel | 18 | 18 | Astoria Hotel18 | 4819756
Astoria Hotel | 19 | 19 | Astoria Hotel19 | 1511334.24
Astoria Hotel | 20 | 20 | Astoria Hotel20 | 0.0001
Astoria Hotel | 21 | 21 | Astoria Hotel21 | 0.0001
Astoria Hotel | 22 | 22 | Astoria Hotel22 | 1e-05
Astoria Hotel | 23 | 23 | Astoria Hotel23 | 17286732.59
Astoria Hotel | 24 | 24 | Astoria Hotel24 | 10400000
Astoria Hotel | 25 | 25 | Astoria Hotel25 | 3117985
Astoria Hotel-DP | 1 | 1 | Astoria Hotel-DP1 | 46039744.5
Astoria Hotel-DP | 2 | 2 | Astoria Hotel-DP2 | 18415897.8
Astoria Hotel-DP | 3 | 3 | Astoria Hotel-DP3 | 9207948.9
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 9207948.9
Astoria Hotel - Final Retention | 1 | 1 | Astoria Hotel - Final Retention1 | 5000000
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 2000000
Astoria Hotel - Social Insurrance | 1 | 1 | Astoria Hotel - Social Insurrance1 | 959926
Astoria Hotel - Spare Parts V.O 137 | 1 | 1 | Astoria Hotel - Spare Parts V.O 1371 | 1929946
Astoria Hotel IPCs 15-20 | 1 | 1 | Astoria Hotel IPCs 15-201 | 1409611.34
Baraka Land Fence | 1 | 1 | Baraka Land Fence1 | 2467026
Baraka Land Fence | 2 | 2 | Baraka Land Fence2 | 8497787.46
Baraka Land Fence | 3 | 3 | Baraka Land Fence3 | 15418299.78
Baraka Land Fence | 4 | 4 | Baraka Land Fence4 | 6072172.61
Benban - Aswan | 2 | 2 | Benban - Aswan2 | 21842173.61
Benban - Aswan | 3 | 3 | Benban - Aswan3 | 10577813.02
Benban - Aswan | 4 | 4 | Benban - Aswan4 | 15006351.74
Benban - Aswan | 5 | 5 | Benban - Aswan5 | 37440497.15
Benban - Aswan | 6 | 6 | Benban - Aswan6 | 23886898.7775
Benban - Aswan | 7 | 7 | Benban - Aswan7 | 25237199.4694
Benban - Aswan | 8 | 8 | Benban - Aswan8 | 28236383.5819
Benban - Aswan | 9 | 9 | Benban - Aswan9 | 33103432.2978
Benban - Aswan | 10 | 10 | Benban - Aswan10 | 12102732.036
Benban - Aswan | 11 | 11 | Benban - Aswan11 | 2222964.1737
Benban - Aswan | 12 | 12 | Benban - Aswan12 | 16625097.353
Benban - Aswan | 13 | 13 | Benban - Aswan13 | 36700.14
Benban - Aswan | 14 | 14 | Benban - Aswan14 | 1174778.08
Benban - Aswan | 1 | 1 | Benban - Aswan1 | 24677038.56
Cement Plant | 14 | 14 | Cement Plant14 | 7309725
Cement Plant | 15 | 15 | Cement Plant15 | 6696657.1239
Cement Plant | 16 | 16 | Cement Plant16 | 6990595.3607
Cement Plant | 17 | 17 | Cement Plant17 | 7424114.8339
Cement Plant | 18 | 18 | Cement Plant18 | 6925479.9129
Cement Plant | 19 | 19 | Cement Plant19 | 12791497.7957
Cement Plant | 20 | 20 | Cement Plant20 | 10152661.36
Cement Plant -Last Claim | 3 | 3 | Cement Plant -Last Claim3 | 5224000
CFC | 1 | 1 | CFC1 | 6200445.37
CFC | 2 | 2 | CFC2 | 17105598.33
CFC | 3 | 3 | CFC3 | 12263695.26
CFC | 4 | 4 | CFC4 | 32660833.58
CFC | 5 | 5 | CFC5 | 24749111.95
CFC | 6 | 6 | CFC6 | 31500278.62
CFC | 7 | 7 | CFC7 | 19510038
CFC | 8 | 8 | CFC8 | 21459124.497
CFC | 9 | 9 | CFC9 | 24499895.82
CFC | 10 | 10 | CFC10 | 39448595.84
CFC | 11 | 11 | CFC11 | 18030565.73
CFC | 12 | 12 | CFC12 | 29691194.9757
CFC | 13 | 13 | CFC13 | 23213756.67
CFC | 14 | 14 | CFC14 | 19708943.72
CFC | 15 | 15 | CFC15 | 40379659.8985
CFC | 16 | 16 | CFC16 | 22871121.16
CFC | 17 | 17 | CFC17 | 15047803.35
CFC | 18 | 18 | CFC18 | 12196441.12
CFC | 19 | 19 | CFC19 | 14008565.7
CFC | 20 | 20 | CFC20 | 23721354.77
CFC | 21 | 21 | CFC21 | 17156725.12
CFC | 22 | 22 | CFC22 | 13410069.82
CFC | 23 | 23 | CFC23 | 15440459.23
CFC | 24 | 24 | CFC24 | 7464480.35
CFC | 25 | 25 | CFC25 | 9682524.46
CFC | 26 | 26 | CFC26 | 2397254.3033
CFC | 27 | 27 | CFC27 | 10793868.64
CFC | 28 | 28 | CFC28 | 10367935.31
CFC | 29 | 29 | CFC29 | 15034318.2703
CFC - Final Retention | 1 | 1 | CFC - Final Retention1 | 12637074.78
CFC-DP | 1 | 1 | CFC-DP1 | 62134944.55
Comoros | 1 | 1 | Comoros1 | 3891360.8
Comoros - Off Shore | 1 | 1 | Comoros - Off Shore1 | 2555388
Comoros - Off Shore | 2 | 2 | Comoros - Off Shore2 | 910154
Comoros - On Shore | 1 | 1 | Comoros - On Shore1 | 830840.75
Comoros - On Shore | 2 | 2 | Comoros - On Shore2 | 405450.99
Comoros - On Shore | 1 | 1 | Comoros - On Shore1 | 263708.26
Creeks - URBN K | 1 | 1 | Creeks - URBN K1 | 10729515
Creeks - URBN K | 2 | 2 | Creeks - URBN K2 | 3863139
Creeks - URBN K | 3 | 3 | Creeks - URBN K3 | 21808950
Creeks - URBN K | 4 | 4 | Creeks - URBN K4 | 8830426
Creeks - URBN K | 5 | 5 | Creeks - URBN K5 | 13533059
Creeks - URBN K | 6 | 6 | Creeks - URBN K6 | 19608847
Creeks - URBN K | 7 | 7 | Creeks - URBN K7 | 16761479
Creeks - URBN K | 8 | 8 | Creeks - URBN K8 | 16707965
Creeks - URBN K | 9 | 9 | Creeks - URBN K9 | 16997068
Creeks - URBN K | 10 | 10 | Creeks - URBN K10 | 19246723
Creeks - URBN K | 11 | 11 | Creeks - URBN K11 | 11569432
Creeks - URBN K | 12 | 12 | Creeks - URBN K12 | 8618325
Creeks - URBN K | 13 | 13 | Creeks - URBN K13 | 23221916
Creeks - URBN K | 14 | 14 | Creeks - URBN K14 | 6223873.19
Creeks - URBN K | 15 | 15 | Creeks - URBN K15 | 10206848
Creeks - URBN K | 16 | 16 | Creeks - URBN K16 | 6345314
Creeks - URBN K | 17 | 17 | Creeks - URBN K17 | 8554807
Creeks - URBN K | 18 | 18 | Creeks - URBN K18 | 9363450
Damietta Port - Civil | 2 | 2 | Damietta Port - Civil2 | 1520770.91
Damietta Port - Civil | 3 | 3 | Damietta Port - Civil3 | 1496696.18
Damietta Port - Civil | 1 | 1 | Damietta Port - Civil1 | 4058690.9
Damietta Port - Infra | 1 | 1 | Damietta Port - Infra1 | 6541975.22
DP World Sokhna | 1 | 1 | DP World Sokhna1 | 15998139
DP World Sokhna | 2 | 2 | DP World Sokhna2 | 18062199.23
DP World Sokhna | 3 | 3 | DP World Sokhna3 | 15357944.03
DP World Sokhna | 4 | 4 | DP World Sokhna4 | 27940477.28
DP World Sokhna | 5 | 5 | DP World Sokhna5 | 13161622.85
DP World Sokhna | 6 | 6 | DP World Sokhna6 | 24492163.72
DP World Sokhna | 7 | 7 | DP World Sokhna7 | 29974844.16
DP World Sokhna | 8 | 8 | DP World Sokhna8 | 29128813.98
DP World Sokhna | 9 | 9 | DP World Sokhna9 | 40031882.73
DP World Sokhna | 10 | 10 | DP World Sokhna10 | 66994289.3
DP World Sokhna | 11 | 11 | DP World Sokhna11 | 76494532.33
DP World Sokhna | 12 | 12 | DP World Sokhna12 | 59999695.78
DP World Sokhna | 12.1 | 12 | DP World Sokhna12 | 49675726.5
DP World Sokhna | 13 | 13 | DP World Sokhna13 | 46089743
DP World Sokhna | 13.1 | 13 | DP World Sokhna13 | 46089743
DP World Sokhna | 14 | 14 | DP World Sokhna14 | 52189292.94
DP World Sokhna | 14.1 | 14 | DP World Sokhna14 | 52189292.94
DP World Sokhna | 15 | 15 | DP World Sokhna15 | 81940298.01
DP World Sokhna | 16 | 16 | DP World Sokhna16 | 63998840.71
DP World Sokhna | 17 | 17 | DP World Sokhna17 | 41776446.85
DP World Sokhna | 18 | 18 | DP World Sokhna18 | 44310014.32
DP World Sokhna | 19 | 19 | DP World Sokhna19 | 25431108.58
DP World Sokhna | 20 | 20 | DP World Sokhna20 | 31817254.2
DP World Sokhna | 21 | 21 | DP World Sokhna21 | 25746407.39
DP World Sokhna | 22 | 22 | DP World Sokhna22 | 17720371
DP World Sokhna | 23 | 23 | DP World Sokhna23 | 26545255.12
DP World Sokhna | 24 | 24 | DP World Sokhna24 | 20867275.72
DP World Sokhna | 25 | 25 | DP World Sokhna25 | 10313601.64
DP World Sokhna | 26 | 26 | DP World Sokhna26 | 22617919.57
DP World Sokhna | 27 | 27 | DP World Sokhna27 | 15718793.62
DP World Sokhna | 28 | 28 | DP World Sokhna28 | 19977105.85
DP World Sokhna | 29 | 29 | DP World Sokhna29 | 20394668.34
DP World Sokhna | 30 | 30 | DP World Sokhna30 | 10739490.38
DP World Sokhna | 31 | 31 | DP World Sokhna31 | 10014939.05
DP World Sokhna | 32 | 32 | DP World Sokhna32 | 12304801.83
DP World Sokhna | 33 | 33 | DP World Sokhna33 | 15048235.01
DP World Sokhna | 34 | 34 | DP World Sokhna34 | 8899770.44
DP World Sokhna | 35 | 35 | DP World Sokhna35 | 2915333
DP World Sokhna | 36 | 36 | DP World Sokhna36 | 50000000
DP World Sokhna | 36.1 | 36 | DP World Sokhna36 | 30556058.47
DP World Sokhna | 1 | 1 | DP World Sokhna1 | 241563831.68
DPW - Ph.02 | 1 | 1 | DPW - Ph.021 | 21783711.58
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 19448762.45
DPW - Ph.02 | 3 | 3 | DPW - Ph.023 | 28493360.54
DPW - Ph.02 | 4 | 4 | DPW - Ph.024 | 27398639.54
DPW - Ph.02 | 5 | 5 | DPW - Ph.025 | 30104833.54
DPW - Ph.02 | 6 | 6 | DPW - Ph.026 | 23809772.84
DPW - Ph.02 | 7 | 7 | DPW - Ph.027 | 15918348.27
DPW - Ph.02 | 8 | 8 | DPW - Ph.028 | 20524928.94
DPW - Ph.02 | 9 | 9 | DPW - Ph.029 | 49445572.72
DPW - Ph.02 | 10 | 10 | DPW - Ph.0210 | 34610141.8
DPW - Ph.02 | 11 | 11 | DPW - Ph.0211 | 40236573.85
DPW - Ph.02 | 12 | 12 | DPW - Ph.0212 | 15678173.8779
DPW - Ph.02 | 13 | 13 | DPW - Ph.0213 | 18805485.48
DPW - Ph.02 | 14 | 14 | DPW - Ph.0214 | 35568315.9
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 63597656.14
DPW - Ph.02 | 2.1 | 2 | DPW - Ph.022 | 1460242.27
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 4836368.8
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 10019256.26
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 3347979.5
EGAT Pelletizing Plant | 3.1 | 3 | EGAT Pelletizing Plant3 | 766737.3
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 6000000
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 13990653.63
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 10253665.39
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 13147791.3
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 11455129.95
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 14888447
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 16034098.6
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 14151886.79
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 8500000
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 18397068.58
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 7794639.63
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 15000000
EGAT Pelletizing Plant | 15.1 | 15 | EGAT Pelletizing Plant15 | 4186530.1
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 13336148.65
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 19257376.65
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 10000000
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 10000000
EGAT Pelletizing Plant | 19.1 | 19 | EGAT Pelletizing Plant19 | 12197351.2
EGAT Pelletizing Plant | 20 | 20 | EGAT Pelletizing Plant20 | 1e-05
EGAT Pelletizing Plant | 21 | 21 | EGAT Pelletizing Plant21 | 1e-05
EGAT Pelletizing Plant | 22 | 22 | EGAT Pelletizing Plant22 | 1e-05
EGAT Pelletizing Plant - Supply | 1 | 1 | EGAT Pelletizing Plant - Supply1 | 1570903.44
EGAT Pelletizing Plant-Concrete Infra | 1 | 1 | EGAT Pelletizing Plant-Concrete Infra1 | 1e-05
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 10000000
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 2000000
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 5000000
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 20500000
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 28804143.3
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 100000000
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 100000000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 200000000
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 26309409.25
EGAT Pelletizing Plant-Escalation | 1 | 1 | EGAT Pelletizing Plant-Escalation1 | 7000000
EGAT Pelletizing Plant-Mechanical Installation | 1 | 1 | EGAT Pelletizing Plant-Mechanical Installation1 | 1e-05
EGAT Pelletizing Plant-MEP | 1 | 1 | EGAT Pelletizing Plant-MEP1 | 1e-05
EGAT Pelletizing Plant-MEP | 2 | 2 | EGAT Pelletizing Plant-MEP2 | 1e-05
EGAT Pelletizing Plant-MEP | 3 | 3 | EGAT Pelletizing Plant-MEP3 | 1e-05
EGAT Pelletizing Plant-MEP Coordination | 1 | 1 | EGAT Pelletizing Plant-MEP Coordination1 | 1e-05
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 1769274.74
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 15000000
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 50000000
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 23690590.75
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 100000000
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 50000000
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 50000000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 30000000
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 30000000
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 25000000
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 20000000
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 15000000
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 35000000
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 10000000
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 10000000
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 10000000
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 20000000
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 25000000
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 20000000
EGAT Pelletizing Plant | 20 | 20 | EGAT Pelletizing Plant20 | 40000000
EGAT Pelletizing Plant | 21 | 21 | EGAT Pelletizing Plant21 | 20000000
EGAT Pelletizing Plant | 22 | 22 | EGAT Pelletizing Plant22 | 50000000
EGAT Pelletizing Plant | 23 | 23 | EGAT Pelletizing Plant23 | 15000000
EGAT Pelletizing Plant | 24 | 24 | EGAT Pelletizing Plant24 | 10000000
EGAT Pelletizing Plant | 25 | 25 | EGAT Pelletizing Plant25 | 10000000
EGAT Pelletizing Plant | 26 | 26 | EGAT Pelletizing Plant26 | 15000000
EGAT Pelletizing Plant | 27 | 27 | EGAT Pelletizing Plant27 | 10000000
EGAT Pelletizing Plant | 28 | 28 | EGAT Pelletizing Plant28 | 10000000
EGAT Pelletizing Plant | 29 | 29 | EGAT Pelletizing Plant29 | 10000000
EGAT Pelletizing Plant | 30 | 30 | EGAT Pelletizing Plant30 | 15000000
EGAT Pelletizing Plant | 32 | 32 | EGAT Pelletizing Plant32 | 20000000
EGAT Pelletizing Plant | 33 | 33 | EGAT Pelletizing Plant33 | 100000000
EGAT Pelletizing Plant | 34 | 34 | EGAT Pelletizing Plant34 | 20000000
EGAT Pelletizing Plant | 35 | 35 | EGAT Pelletizing Plant35 | 15000000
EGAT Pelletizing Plant | 36 | 36 | EGAT Pelletizing Plant36 | 20000000
EGAT Pelletizing Plant | 37 | 37 | EGAT Pelletizing Plant37 | 5000000
EGAT Pelletizing Plant | 38 | 38 | EGAT Pelletizing Plant38 | 15000000
EGAT Pelletizing Plant | 39 | 39 | EGAT Pelletizing Plant39 | 25000000
EGAT Pelletizing Plant | 40 | 40 | EGAT Pelletizing Plant40 | 15000000
EGAT Pelletizing Plant | 41 | 41 | EGAT Pelletizing Plant41 | 20000000
EGAT Pelletizing Plant | 42 | 42 | EGAT Pelletizing Plant42 | 10000000
EGAT Pelletizing Plant | 43 | 43 | EGAT Pelletizing Plant43 | 35000000
EGAT Pelletizing Plant | 44 | 44 | EGAT Pelletizing Plant44 | 35000000
EGAT Pelletizing Plant | 45 | 45 | EGAT Pelletizing Plant45 | 20000000
EGAT Pelletizing Plant | 46 | 46 | EGAT Pelletizing Plant46 | 32000000
EGAT Pelletizing Plant | 47 | 47 | EGAT Pelletizing Plant47 | 10000000
EGAT Pelletizing Plant | 48 | 48 | EGAT Pelletizing Plant48 | 10000000
EGAT Pelletizing Plant | 49 | 49 | EGAT Pelletizing Plant49 | 10000000
EGAT Pelletizing Plant | 50 | 50 | EGAT Pelletizing Plant50 | 10000000
EGAT Pelletizing Plant | 51 | 51 | EGAT Pelletizing Plant51 | 10000000
EGAT Pelletizing Plant | 52 | 52 | EGAT Pelletizing Plant52 | 10000000
EGAT Pelletizing Plant | 53 | 53 | EGAT Pelletizing Plant53 | 5000000
EGAT Pelletizing Plant | 54 | 54 | EGAT Pelletizing Plant54 | 15000000
EGAT Pelletizing Plant | 55 | 55 | EGAT Pelletizing Plant55 | 7500000
EGAT Pelletizing Plant | 56 | 56 | EGAT Pelletizing Plant56 | 5000000
EGAT Pelletizing Plant-Water Tank | 1 | 1 | EGAT Pelletizing Plant-Water Tank1 | 3241734.16
EGAT Pelletizing Plant-Water Tank | 2 | 2 | EGAT Pelletizing Plant-Water Tank2 | 2008304.1
EGAT Pelletizing Plant-Water Tank | 3 | 3 | EGAT Pelletizing Plant-Water Tank3 | 718104.27
EGAT Pelletizing Plant-Water Tank | 4 | 4 | EGAT Pelletizing Plant-Water Tank4 | 758512.36
EGAT Pelletizing Plant-Water Tank | 5 | 5 | EGAT Pelletizing Plant-Water Tank5 | 914358.66
EGAT Pelletizing Plant-Water Tank | 6 | 6 | EGAT Pelletizing Plant-Water Tank6 | 1449673.43
EGAT Pelletizing Plant-Water Tank | 7 | 7 | EGAT Pelletizing Plant-Water Tank7 | 395732.02
EGAT Pelletizing Plant-Water Tank | 8 | 8 | EGAT Pelletizing Plant-Water Tank8 | 304153.94
EGAT Pelletizing Plant-Water Tank | 9 | 9 | EGAT Pelletizing Plant-Water Tank9 | 967200
EGAT Pelletizing Plant-Water Tank | 10 | 10 | EGAT Pelletizing Plant-Water Tank10 | 3505322.5
EGAT Pelletizing Plant-Water Tank | 11 | 11 | EGAT Pelletizing Plant-Water Tank11 | 3903900.34
EGAT Pelletizing Plant-Water Tank | 12 | 12 | EGAT Pelletizing Plant-Water Tank12 | 1e-05
EGAT Pelletizing Plant-Water Tank | 13 | 13 | EGAT Pelletizing Plant-Water Tank13 | 391272.95
EGAT Pelletizing Plant-Water Tank | 14 | 14 | EGAT Pelletizing Plant-Water Tank14 | 1e-05
EGAT-Asphalt | 1 | 1 | EGAT-Asphalt1 | 598688
EGAT-Asphalt - Retenion Release | 1 | 1 | EGAT-Asphalt - Retenion Release1 | 291975.34
EGAT-EGAT | 1 | 1 | EGAT-EGAT1 | 12000000
EGAT-EGAT | 2 | 2 | EGAT-EGAT2 | 6000000
EGAT-EGAT | 3 | 3 | EGAT-EGAT3 | 6000000
EGAT-EGAT | 4 | 4 | EGAT-EGAT4 | 1500000
EGAT-Fence | 1 | 1 | EGAT-Fence1 | 195752.6
EGAT-Fence | 2 | 2 | EGAT-Fence2 | 0.001
EGAT-Fence | 3 | 3 | EGAT-Fence3 | 457138.81
EGAT-Fence | 3.1 | 3 | EGAT-Fence3 | 237906.8728
EGAT-Fence | 4.1 | 4 | EGAT-Fence4 | 838441.7922
EGAT-Fence | 4.2 | 4 | EGAT-Fence4 | 1000000
EGAT-Fence | 4.3 | 4 | EGAT-Fence4 | 750000
EGAT-Fence | 4.4 | 4 | EGAT-Fence4 | 302594.27
EGAT-Fence - Retenion Release | 1 | 1 | EGAT-Fence - Retenion Release1 | 1161544.2
EGAT-Fence - Retenion Release | 1.1 | 1 | EGAT-Fence - Retenion Release1 | 1e-05
EGAT-HeliPad | 1 | 1 | EGAT-HeliPad1 | 755798.13
EGAT-HeliPad | 2 | 2 | EGAT-HeliPad2 | 500000
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 4717110.35
EGAT-Lock & Load | 2 | 2 | EGAT-Lock & Load2 | 2773213.88
EGAT-Lock & Load | 3 | 3 | EGAT-Lock & Load3 | 1665986.92
EGAT-Lock & Load | 4 | 4 | EGAT-Lock & Load4 | 747255.39
EGAT-Lock & Load | 5 | 5 | EGAT-Lock & Load5 | 2436487.51
EGAT-Lock & Load | 6 | 6 | EGAT-Lock & Load6 | 3176089.21
EGAT-Lock & Load | 7 | 7 | EGAT-Lock & Load7 | 275994.22
EGAT-Lock & Load | 7.1 | 7 | EGAT-Lock & Load7 | 1043113.27
EGAT-Lock & Load | 8 | 8 | EGAT-Lock & Load8 | 2619387.85
EGAT-Lock & Load | 9 | 9 | EGAT-Lock & Load9 | 3741613.11
EGAT-Lock & Load | 10 | 10 | EGAT-Lock & Load10 | 871396.81
EGAT-Lock & Load | 10.1 | 10 | EGAT-Lock & Load10 | 227993.12
EGAT-Lock & Load | 11 | 11 | EGAT-Lock & Load11 | 1873296.27
EGAT-Lock & Load | 12 | 12 | EGAT-Lock & Load12 | 1672142.68
EGAT-Lock & Load | 13 | 13 | EGAT-Lock & Load13 | 1e-05
EGAT-Lock & Load | 14 | 14 | EGAT-Lock & Load14 | 1e-05
EGAT-Lock & Load | 15 | 15 | EGAT-Lock & Load15 | 1e-05
EGAT-Lock & Load | 16 | 16 | EGAT-Lock & Load16 | 1e-05
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 5400000
EGAT-SZ | 1 | 1 | EGAT-SZ1 | 4624356.65
EGAT-SZ | 2 | 2 | EGAT-SZ2 | 10000000
EGAT-SZ | 3 | 3 | EGAT-SZ3 | 6070502.71
EGAT-Warehouse | 1 | 1 | EGAT-Warehouse1 | 923651.335
EIPICO | 1 | 1 | EIPICO1 | 12050858.57
EIPICO | 2 | 2 | EIPICO2 | 13338534.97
EIPICO | 3 | 3 | EIPICO3 | 13033885
EIPICO | 4 | 4 | EIPICO4 | 7344659
EIPICO | 5 | 5 | EIPICO5 | 10064340.12
EIPICO | 6 | 6 | EIPICO6 | 5949568.74
EIPICO | 7 | 7 | EIPICO7 | 6395645.73
EIPICO | 8 | 8 | EIPICO8 | 20317361.34
EIPICO | 9 | 9 | EIPICO9 | 34650000
EIPICO | 10 | 10 | EIPICO10 | 1e-05
EIPICO | 11 | 11 | EIPICO11 | 6263190.12
EIPICO | 11.1 | 11 | EIPICO11 | 17000000
EIPICO | 12 | 12 | EIPICO12 | 25548194.95
EIPICO | 13 | 13 | EIPICO13 | 2882568.41
EIPICO | 14 | 14 | EIPICO14 | 26305980.07
EIPICO | 15 | 15 | EIPICO15 | 25000000
EIPICO | 15.1 | 15 | EIPICO15 | 4236256.89
EIPICO | 16 | 16 | EIPICO16 | 26363887.4
EIPICO | 17 | 17 | EIPICO17 | 13161378.75
EIPICO | 18 | 18 | EIPICO18 | 25000000
EIPICO | 18.1 | 18 | EIPICO18 | 10188037.3
EIPICO | 19 | 19 | EIPICO19 | 10000000
EIPICO | 19.1 | 19 | EIPICO19 | 12436578.36
EIPICO | 20 | 20 | EIPICO20 | 20000000
EIPICO | 1 | 1 | EIPICO1 | 83482074.8
EIPICO | 1 | 1 | EIPICO1 | 85000000
EIPICO | 2 | 2 | EIPICO2 | 10000000
El Sewedy Uni.-PKG.1 | 1 | 1 | El Sewedy Uni.-PKG.11 | 1917993.24
El Sewedy Uni.-PKG.1 | 2 | 2 | El Sewedy Uni.-PKG.12 | 881744.36
El Sewedy Uni.-PKG.1 | 3 | 3 | El Sewedy Uni.-PKG.13 | 1214989
El Sewedy Uni.-PKG.1 | 4 | 4 | El Sewedy Uni.-PKG.14 | 1204112.8596
El Sewedy Uni.-PKG.1 | 5 | 5 | El Sewedy Uni.-PKG.15 | 185635.0557
El Sewedy Uni.-PKG.1 | 6 | 6 | El Sewedy Uni.-PKG.16 | 142702.12
El Sewedy Uni.-PKG.1 | 7 | 7 | El Sewedy Uni.-PKG.17 | 284879.77
El Sewedy Uni.-PKG.1 | 8 | 8 | El Sewedy Uni.-PKG.18 | 235901.48
El Sewedy Uni.-PKG.1 | 9 | 9 | El Sewedy Uni.-PKG.19 | 72777.3
El Sewedy Uni.-PKG.1 | 10 | 10 | El Sewedy Uni.-PKG.110 | -8913.92
El Sewedy Uni.-PKG.11 | 1 | 1 | El Sewedy Uni.-PKG.111 | 2898141.12
El Sewedy Uni.-PKG.2 | 1 | 1 | El Sewedy Uni.-PKG.21 | 3110956.56
El Sewedy Uni.-PKG.2 | 2 | 2 | El Sewedy Uni.-PKG.22 | 6754267.57
El Sewedy Uni.-PKG.2 | 3 | 3 | El Sewedy Uni.-PKG.23 | 3212953.45
El Sewedy Uni.-PKG.2 | 4 | 4 | El Sewedy Uni.-PKG.24 | 3208255.76
El Sewedy Uni.-PKG.2 | 5 | 5 | El Sewedy Uni.-PKG.25 | 4527299.68
El Sewedy Uni.-PKG.2 | 6 | 6 | El Sewedy Uni.-PKG.26 | 7457797.24
El Sewedy Uni.-PKG.2 | 7 | 7 | El Sewedy Uni.-PKG.27 | 2278076.64
El Sewedy Uni.-PKG.2 | 8 | 8 | El Sewedy Uni.-PKG.28 | 2625161.63
El Sewedy Uni.-PKG.2 | 9 | 9 | El Sewedy Uni.-PKG.29 | 1116423
El Sewedy Uni.-PKG.22 | 1 | 1 | El Sewedy Uni.-PKG.221 | 8589000
El Sewedy Uni.-PKG.2-Social Insurrance | 1 | 1 | El Sewedy Uni.-PKG.2-Social Insurrance1 | 1120262.65
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 1727255.6
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 3185421.17
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 5785718.63
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 1785482.76
El Sewedy Uni.-PKG.3 | 5 | 5 | El Sewedy Uni.-PKG.35 | 24218860.6
El Sewedy Uni.-PKG.3 | 6 | 6 | El Sewedy Uni.-PKG.36 | 26716091.61
El Sewedy Uni.-PKG.3 | 7 | 7 | El Sewedy Uni.-PKG.37 | 17000000
El Sewedy Uni.-PKG.3 | 7.1 | 7 | El Sewedy Uni.-PKG.37 | 5410862.51
El Sewedy Uni.-PKG.3 | 8 | 8 | El Sewedy Uni.-PKG.38 | 12292368.36
El Sewedy Uni.-PKG.3 | 9 | 9 | El Sewedy Uni.-PKG.39 | 19287810.69
El Sewedy Uni.-PKG.3 | 10 | 10 | El Sewedy Uni.-PKG.310 | 20919758.8
El Sewedy Uni.-PKG.3 | 11 | 11 | El Sewedy Uni.-PKG.311 | 2318161.39
El Sewedy Uni.-PKG.3 | 12 | 12 | El Sewedy Uni.-PKG.312 | 1515470
El Sewedy Uni.-PKG.3 | 13 | 13 | El Sewedy Uni.-PKG.313 | 6845790.3
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 15000000
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 24971065.75
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 8000000
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 12000000
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 4931187
El Sewedy Uni.-PKG.3-Social Insurrance | 1 | 1 | El Sewedy Uni.-PKG.3-Social Insurrance1 | 253659.18
El Sewedy Uni.-PKG.3-Social Insurrance | 2 | 2 | El Sewedy Uni.-PKG.3-Social Insurrance2 | 267208.33
El Sewedy Uni.-PKG.3-Social Insurrance | 3 | 3 | El Sewedy Uni.-PKG.3-Social Insurrance3 | 3183056.54
El Sewedy Uni.-PKG.3-Social Insurrance | 4 | 4 | El Sewedy Uni.-PKG.3-Social Insurrance4 | 185944.54
Elco Steel | 1 | 1 | Elco Steel1 | 13532577.04
Elco Steel | 2 | 2 | Elco Steel2 | 42881105.07
Elco Steel | 3 | 3 | Elco Steel3 | 54829579.72
Elco Steel | 4 | 4 | Elco Steel4 | 35932469.35
Elco Steel | 5 | 5 | Elco Steel5 | 12038252.26
Elco Steel | 6 | 6 | Elco Steel6 | 20100303
Elco Steel | 7 | 7 | Elco Steel7 | 7919870.17
Elco Steel | 8 | 8 | Elco Steel8 | 6348055.64
Elco Steel | 9 | 9 | Elco Steel9 | 740665.09
Elco Steel | 10 | 10 | Elco Steel10 | 4000000
Elco Steel | 11 | 11 | Elco Steel11 | 7075101.66
Elco Steel | 12 | 12 | Elco Steel12 | 2485656
Elco Steel | 13 | 13 | Elco Steel13 | 2518616.18
Elco Steel | 14 | 14 | Elco Steel14 | 2857649.27
Elco Steel | 15 | 15 | Elco Steel15 | 1595365.5
Elco Steel | 16 | 16 | Elco Steel16 | 310509.31
Elco Steel | 17 | 17 | Elco Steel17 | 1079101.72
Elco Steel - ADMIN. | 1 | 1 | Elco Steel - ADMIN.1 | 1253543.1806
Elco Steel - ADMIN. | 2 | 2 | Elco Steel - ADMIN.2 | 2897721.63
Elco Steel - ADMIN. | 3 | 3 | Elco Steel - ADMIN.3 | 3188918.44
Elco Steel - ADMIN. | 4 | 4 | Elco Steel - ADMIN.4 | 3617002.31
Elco Steel - ADMIN. | 5 | 5 | Elco Steel - ADMIN.5 | 1819035.22
Elco Steel - ADMIN. | 6 | 6 | Elco Steel - ADMIN.6 | 5058047.58
Elco Steel - ADMIN. | 7 | 7 | Elco Steel - ADMIN.7 | 5750618.5816
Elco Steel - ADMIN. | 8 | 8 | Elco Steel - ADMIN.8 | 3289926.92
Elco Steel - ADMIN. | 9 | 9 | Elco Steel - ADMIN.9 | 1940428
Elco Steel - ADMIN. | 10 | 10 | Elco Steel - ADMIN.10 | 2335545.55
Elco Steel - ADMIN. | 11 | 11 | Elco Steel - ADMIN.11 | 2179703.08
Elco Steel - ADMIN. | 12 | 12 | Elco Steel - ADMIN.12 | 1394236.8
Elco Steel - ADMIN. | 13 | 13 | Elco Steel - ADMIN.13 | 117652.86
Elco Steel - ADMIN. | 14 | 14 | Elco Steel - ADMIN.14 | 105992.48
Elco Steel - ADMIN. | 15 | 15 | Elco Steel - ADMIN.15 | 259861.3
Elco Steel - MEP | 1 | 1 | Elco Steel - MEP1 | 331328.322
Elco Steel - MEP | 2 | 2 | Elco Steel - MEP2 | 2059899.63
Elco Steel - MEP | 3 | 3 | Elco Steel - MEP3 | 1986502.95
Elco Steel - MEP | 4 | 4 | Elco Steel - MEP4 | 2505278.83
Elco Steel - MEP | 5 | 5 | Elco Steel - MEP5 | 2440101.67
Elco Steel - MEP | 6 | 6 | Elco Steel - MEP6 | 2133379.76
Elco Steel - MEP | 7 | 7 | Elco Steel - MEP7 | 2606150.307
Elco Steel - MEP | 8 | 8 | Elco Steel - MEP8 | 1980608.55
Elco Steel - MEP | 9 | 9 | Elco Steel - MEP9 | 2178754.66
Elco Steel - MEP | 10 | 10 | Elco Steel - MEP10 | 2629432.67
Elco Steel - MEP | 11 | 11 | Elco Steel - MEP11 | 1720441.01
Elco Steel - MEP | 12 | 12 | Elco Steel - MEP12 | 1037321.78
Elco Steel - MEP | 13 | 13 | Elco Steel - MEP13 | 388339.4
Elco Steel - MEP | 14 | 14 | Elco Steel - MEP14 | 317040.71
Elco Steel - MEP - Social Insurance | 1 | 1 | Elco Steel - MEP - Social Insurance1 | 1700000
Elco Steel - Social Insurance | 1 | 1 | Elco Steel - Social Insurance1 | 13218500
Elco Steel - Social Insurance | 2 | 2 | Elco Steel - Social Insurance2 | 2250000
Elco Steel - Social Insurance | 3 | 3 | Elco Steel - Social Insurance3 | 1573000
Elco Steel - Social Insurance | 4 | 4 | Elco Steel - Social Insurance4 | 134252.42
Elco Steel EGAT | 1 | 1 | Elco Steel EGAT1 | 10000000
Elco Steel V.O | 1 | 1 | Elco Steel V.O1 | 4160000
Elco Steel V.O | 1 | 1 | Elco Steel V.O1 | 500000
Elco Steel V.O-Infra. Network | 1 | 1 | Elco Steel V.O-Infra. Network1 | 767138.81
Elco Steel V.O-Infra. Network | 1.1 | 1 | Elco Steel V.O-Infra. Network1 | 292861.19
El-Gouna | 1 | 1 | El-Gouna1 | 2327690.6
El-Gouna | 2 | 2 | El-Gouna2 | 3867767.27
El-Gouna | 3 | 3 | El-Gouna3 | 2286139.86
El-Gouna | 4 | 4 | El-Gouna4 | 2572404.48
El-Gouna | 5 | 5 | El-Gouna5 | 1808595.27
El-Gouna | 6 | 6 | El-Gouna6 | 4246133.4
El-Gouna | 7 | 7 | El-Gouna7 | 2145687.36
El-Gouna | 8 | 8 | El-Gouna8 | 1922134.77
El-Gouna | 9 | 9 | El-Gouna9 | 1030964.27
El-Gouna | 10 | 10 | El-Gouna10 | 1173489.52
El-Gouna | 11 | 11 | El-Gouna11 | 1750027.3
El-Gouna | 12 | 12 | El-Gouna12 | 1942857.14
El-Gouna | 13 | 13 | El-Gouna13 | 1951940.18
El-Gouna | 14 | 14 | El-Gouna14 | 3058799.81
El-Gouna | 15 | 15 | El-Gouna15 | 3002136.21
El-Gouna | 16 | 16 | El-Gouna16 | 3166964.63
El-Gouna | 17 | 17 | El-Gouna17 | 2526942.2
El-Gouna | 18 | 18 | El-Gouna18 | 5636281.25
El-Gouna-DP | 1 | 1 | El-Gouna-DP1 | 13625000
El-Gouna - Equip. Rental | 1 | 1 | El-Gouna - Equip. Rental1 | 73813.12
El-Gouna - Equip. Rental | 2 | 2 | El-Gouna - Equip. Rental2 | 16757
El-Gouna - Equip. Rental | 3 | 3 | El-Gouna - Equip. Rental3 | 74100
El-Gouna - Equip. Rental | 4 | 4 | El-Gouna - Equip. Rental4 | 3281.25
El-Gouna - Equip. Rental | 5 | 5 | El-Gouna - Equip. Rental5 | 15750
El-Gouna - Temp. Fence | 1 | 1 | El-Gouna - Temp. Fence1 | 425568
El-Gouna - Temp. Fence | 2 | 2 | El-Gouna - Temp. Fence2 | 441526.8
El-Gouna - Temp. Fence | 3 | 3 | El-Gouna - Temp. Fence3 | 173749.2
EUA | 1 | 1 | EUA1 | 120000000
Existing Intake Apply -SSC-Mech | 1 | 1 | Existing Intake Apply -SSC-Mech1 | 1e-05
Existing Intake Supply -SSC-Mech | 1 | 1 | Existing Intake Supply -SSC-Mech1 | 2311727.07
FIEM | 210 | 210 | FIEM210 | 1523916.51
FIEM | 211 | 211 | FIEM211 | 218510
FIEM | 212 | 212 | FIEM212 | 1205285.3
FIEM | 213 | 213 | FIEM213 | 335237.946
FIEM - Retention | 1 | 1 | FIEM - Retention1 | 286904.18
FIEM-Site Offices Rental Payment Request | 1 | 1 | FIEM-Site Offices Rental Payment Request1 | 93000
FIEM-Site Offices Rental Payment Request | 2 | 2 | FIEM-Site Offices Rental Payment Request2 | 93000
FIEM-Site Offices Rental Payment Request | 3 | 3 | FIEM-Site Offices Rental Payment Request3 | 91140
FIEM-Site Offices Rental Payment Request | 4 | 4 | FIEM-Site Offices Rental Payment Request4 | 91140
FIEM-Site Offices Rental Payment Request | 5 | 5 | FIEM-Site Offices Rental Payment Request5 | 91140
FIEM-Site Offices Rental Payment Request | 6 | 6 | FIEM-Site Offices Rental Payment Request6 | 93000
H1 Solaymaneya-MEP | 1 | 1 | H1 Solaymaneya-MEP1 | 1165148
H1 Solaymaneya-MEP | 1 | 1 | H1 Solaymaneya-MEP1 | 4000000
HQ - CFC | 1 | 1 | HQ - CFC1 | 6847513.64
HQ - CFC | 2 | 2 | HQ - CFC2 | 8021127.82
HQ - CFC | 3 | 3 | HQ - CFC3 | 8213720.11
HQ - CFC | 4 | 4 | HQ - CFC4 | 7815807.73
HQ - CFC | 5 | 5 | HQ - CFC5 | 3447418.19
HQ - CFC | 6 | 6 | HQ - CFC6 | 13157200.99
HQ - CFC | 7 | 7 | HQ - CFC7 | 14942810.84
HQ - CFC | 8 | 8 | HQ - CFC8 | 10012745.7
HQ - CFC | 9 | 9 | HQ - CFC9 | 17174919.84
HQ - CFC | 10 | 10 | HQ - CFC10 | 7981881.94
HQ - CFC | 11 | 11 | HQ - CFC11 | 27417402.1
HQ - CFC | 12 | 12 | HQ - CFC12 | 11342066.99
HQ - CFC | 13 | 13 | HQ - CFC13 | 10869511.32
HQ - CFC | 14 | 14 | HQ - CFC14 | 6179916.44
HQ - CFC | 15 | 15 | HQ - CFC15 | 10437699.8
HQ - CFC | 16 | 16 | HQ - CFC16 | 1064612.28
HQ - CFC | 17 | 17 | HQ - CFC17 | 8013147.43
HQ - CFC | 18 | 18 | HQ - CFC18 | 12964666.86
HQ - CFC | 19 | 19 | HQ - CFC19 | 2123375.29
HQ - CFC | 20 | 20 | HQ - CFC20 | 9324446.8
HQ - CFC | 21 | 21 | HQ - CFC21 | 1704646.05
HQ - CFC | 23 | 23 | HQ - CFC23 | 10000000
HQ - CFC | 24 | 24 | HQ - CFC24 | 5681250.46
HQ - CFC | 25 | 25 | HQ - CFC25 | 9125697.43
HQ - CFC | 26 | 26 | HQ - CFC26 | 10915757.94
HQ - CFC | 26.1 | 26 | HQ - CFC26 | 315339.47
HQ - CFC-DP | 1 | 1 | HQ - CFC-DP1 | 103231218.3
HQ - CFC - Retention release | 1 | 1 | HQ - CFC - Retention release1 | 7311955.09
HQ - CFC - Social Insurrance | 1 | 1 | HQ - CFC - Social Insurrance1 | 586840.71
HyperOne | 1 | 1 | HyperOne1 | 2499090
HyperOne | 2 | 2 | HyperOne2 | 8063620
HyperOne | 3 | 3 | HyperOne3 | 6681009
HyperOne | 4 | 4 | HyperOne4 | 6318712
HyperOne | 5 | 5 | HyperOne5 | 3307335
HyperOne | 6 | 6 | HyperOne6 | 8598544
HyperOne | 7 | 7 | HyperOne7 | 8960935
HyperOne | 8 | 8 | HyperOne8 | 3276433
HyperOne | 9 | 9 | HyperOne9 | 1277872
HyperOne | 10 | 10 | HyperOne10 | 4688664
HyperOne | 11 | 11 | HyperOne11 | 6700148
HyperOne | 12 | 12 | HyperOne12 | 1896315
HyperOne | 13 | 13 | HyperOne13 | 6738702
HyperOne | 14 | 14 | HyperOne14 | 4476191
HyperOne | 15 | 15 | HyperOne15 | 2754557
HyperOne | 1 | 1 | HyperOne1 | 33750000
HyperOne-Steel Supply | 1 | 1 | HyperOne-Steel Supply1 | 4724997
HyperOne-Steel Supply | 2 | 2 | HyperOne-Steel Supply2 | 980000
HyperOne-Steel Supply | 3 | 3 | HyperOne-Steel Supply3 | 1165162
HyperOne-Steel Supply | 4 | 4 | HyperOne-Steel Supply4 | 4993651
HyperOne-Steel Supply | 5 | 5 | HyperOne-Steel Supply5 | 305602
HyperOne-Steel Supply | 6 | 6 | HyperOne-Steel Supply6 | 3490984
HyperOne-VAT 1,2,3 | 1 | 1 | HyperOne-VAT 1,2,31 | 1171706
IKEA | 1 | 1 | IKEA1 | 4032556.9
IKEA | 2 | 2 | IKEA2 | 10633715.55
IKEA | 3 | 3 | IKEA3 | 7184168.18
IKEA | 4 | 4 | IKEA4 | 8278802.07
IKEA | 5 | 5 | IKEA5 | 7929959.808
IKEA | 6 | 6 | IKEA6 | 3899213.68
IKEA | 7 | 7 | IKEA7 | 6161858.91
IKEA | 8 | 8 | IKEA8 | 13080191.13
IKEA | 9 | 9 | IKEA9 | 21936362.84
IKEA | 10 | 10 | IKEA10 | 10981834.92
IKEA | 11 | 11 | IKEA11 | 16592416.38
IKEA | 12 | 12 | IKEA12 | 15898929.26
IKEA | 13 | 13 | IKEA13 | 5400893.31
IKEA | 14 | 14 | IKEA14 | 15116863.46
IKEA | 1 | 1 | IKEA1 | 5000000
IKEA | 2 | 2 | IKEA2 | 428986.9
IKEA | 3 | 3 | IKEA3 | 4951900.8
IKEA | 4 | 4 | IKEA4 | 2116049.37
IKEA | 5 | 5 | IKEA5 | 21562500
IKEA | 6 | 6 | IKEA6 | 1818917
IKEA | 7 | 7 | IKEA7 | 3751873.62
IKEA | 8 | 8 | IKEA8 | 525633.83
IKEA-Retention Release | 1 | 1 | IKEA-Retention Release1 | 5552983.6
JICA | 19 | 19 | JICA19 | 1141675.91
JICA | 20 | 20 | JICA20 | 413014.8
JICA-Site Offices Rental Payment Request | 1 | 1 | JICA-Site Offices Rental Payment Request1 | 75000
JICA-Site Offices Rental Payment Request | 2 | 2 | JICA-Site Offices Rental Payment Request2 | 75000
JICA-Site Offices Rental Payment Request | 3 | 3 | JICA-Site Offices Rental Payment Request3 | 75000
JICA-Site Offices Rental Payment Request | 4 | 4 | JICA-Site Offices Rental Payment Request4 | 75000
Kafr Shokr | 1 | 1 | Kafr Shokr 1 | 28845197.4
Kafr Shokr | 2 | 2 | Kafr Shokr 2 | 6242742.2
Kafr Shokr | 3 | 3 | Kafr Shokr 3 | 8372664.9
Kafr Shokr | 4 | 4 | Kafr Shokr 4 | 8190447.9
Kafr Shokr | 5 | 5 | Kafr Shokr 5 | 5371513.65
Kafr Shokr | 6 | 6 | Kafr Shokr 6 | 444257.7
Kafr Shokr | 7 | 7 | Kafr Shokr 7 | 26652960.08
Kafr Shokr | 8 | 8 | Kafr Shokr 8 | 2028646.62
Kafr Shokr | 9 | 9 | Kafr Shokr 9 | 678824.25
Kafr Shokr | 9.1 | 9 | Kafr Shokr 9 | 4133066.85
Kafr Shokr | 10 | 10 | Kafr Shokr 10 | 2390708.7
Kafr Shokr - Retention Release | 1 | 1 | Kafr Shokr - Retention Release1 | 884808.35
Katameya - Creeks | 1 | 1 | Katameya - Creeks1 | 2741191.29
Katameya - Creeks | 2 | 2 | Katameya - Creeks2 | 11302769.9409
Katameya - Creeks | 3 | 3 | Katameya - Creeks3 | 39570120.9
Katameya - Creeks | 4 | 4 | Katameya - Creeks4 | 9000000
Katameya - Creeks | 4.1 | 4 | Katameya - Creeks4 | 20688637.31
Katameya - Creeks | 5 | 5 | Katameya - Creeks5 | 40006572.36
Katameya - Creeks | 6 | 6 | Katameya - Creeks6 | 29363826.77
Katameya - Creeks | 7 | 7 | Katameya - Creeks7 | 24380443
Katameya - Creeks | 7.1 | 7 | Katameya - Creeks7 | 20000000
Katameya - Creeks | 8 | 8 | Katameya - Creeks8 | 20000000
Katameya - Creeks | 8.1 | 8 | Katameya - Creeks8 | 20343227.98
Katameya - Creeks | 9 | 9 | Katameya - Creeks9 | 20000000
Katameya - Creeks | 9.1 | 9 | Katameya - Creeks9 | 10000000
Katameya - Creeks | 9.2 | 9 | Katameya - Creeks9 | 13056438.19
Katameya - Creeks | 10 | 10 | Katameya - Creeks10 | 61159972.97
Katameya - Creeks | 11 | 11 | Katameya - Creeks11 | 43214038.28
Katameya - Creeks | 12 | 12 | Katameya - Creeks12 | 36461301.55
Katameya - Creeks | 13 | 13 | Katameya - Creeks13 | 39353596.01
Katameya - Creeks | 14 | 14 | Katameya - Creeks14 | 45904629.98
Katameya - Creeks | 15 | 15 | Katameya - Creeks15 | 49567395
Katameya - Creeks | 16 | 16 | Katameya - Creeks16 | 25000000
Katameya - Creeks | 16.1 | 16 | Katameya - Creeks16 | 19583744
Katameya - Creeks | 17 | 17 | Katameya - Creeks17 | 20000000
Katameya - Creeks | 17.1 | 17 | Katameya - Creeks17 | 16501027.74
Katameya - Creeks | 18 | 18 | Katameya - Creeks18 | 21565441.8
Katameya - Creeks | 18.1 | 18 | Katameya - Creeks18 | 20000000
Katameya - Creeks | 19 | 19 | Katameya - Creeks19 | 20000000
Katameya - Creeks | 19.1 | 19 | Katameya - Creeks19 | 16081249.47
Katameya - Creeks | 20 | 20 | Katameya - Creeks20 | 15000000
Katameya - Creeks | 20.1 | 20 | Katameya - Creeks20 | 9569045
Katameya - Creeks | 21 | 21 | Katameya - Creeks21 | 20000000
Katameya - Creeks | 21.1 | 21 | Katameya - Creeks21 | 15259435.93
Katameya - Creeks | 22 | 22 | Katameya - Creeks22 | 10000000
Katameya - Creeks | 22.1 | 22 | Katameya - Creeks22 | 21299260.01
Katameya - Creeks | 23 | 23 | Katameya - Creeks23 | 8700739.99
Katameya - Creeks | 23.1 | 23 | Katameya - Creeks23 | 21133993.08
Katameya - Creeks | 24 | 24 | Katameya - Creeks24 | 3866006.92
Katameya - Creeks | 24.1 | 24 | Katameya - Creeks24 | 34010573
Katameya - Creeks | 25 | 25 | Katameya - Creeks25 | 45191848.31
Katameya - Creeks | 26 | 26 | Katameya - Creeks26 | 30000000
Katameya - Creeks | 26.1 | 26 | Katameya - Creeks26 | 44263221
Katameya - Creeks | 27 | 27 | Katameya - Creeks27 | 35452924
Katameya - Creeks | 28 | 28 | Katameya - Creeks28 | 28650459
Katameya - Creeks | 29 | 29 | Katameya - Creeks29 | 40904481
Katameya - Creeks | 30 | 30 | Katameya - Creeks30 | 43084120
Katameya - Creeks | 31 | 31 | Katameya - Creeks31 | 37106226
Katameya - Creeks | 32 | 32 | Katameya - Creeks32 | 41216438
Katameya - Creeks | 33 | 33 | Katameya - Creeks33 | 47329833
Katameya - Creeks | 34 | 34 | Katameya - Creeks34 | 40000000
Katameya - Creeks | 34.1 | 34 | Katameya - Creeks34 | 30308953
Katameya - Creeks | 35 | 35 | Katameya - Creeks35 | 46816344
Katameya - Creeks | 36 | 36 | Katameya - Creeks36 | 33146996.78
Katameya - Creeks | 36.1 | 36 | Katameya - Creeks36 | 17383228
Katameya - Creeks | 37 | 37 | Katameya - Creeks37 | 40000000
Katameya - Creeks | 37.1 | 37 | Katameya - Creeks37 | 22109565
Katameya - Creeks | 38 | 38 | Katameya - Creeks38 | 79235150
Katameya - Creeks | 39 | 39 | Katameya - Creeks39 | 66261026
Katameya - Creeks | 40 | 40 | Katameya - Creeks40 | 30000000
Katameya - Creeks | 40.1 | 40 | Katameya - Creeks40 | 22039038
Katameya - Creeks | 41 | 41 | Katameya - Creeks41 | 24776126.81
Katameya - Creeks | 41.1 | 41 | Katameya - Creeks41 | 20564552
Katameya - Creeks | 42 | 42 | Katameya - Creeks42 | 25000000
Katameya - Creeks | 42.1 | 42 | Katameya - Creeks42 | 27791233
Katameya - Creeks | 43 | 43 | Katameya - Creeks43 | 21224102
Katameya - Creeks | 44 | 44 | Katameya - Creeks44 | 8345106.3
Katameya - Creeks | 45 | 45 | Katameya - Creeks45 | 8654893.7
Katameya - Creeks-DP | 1 | 1 | Katameya - Creeks-DP1 | 200000000
Katameya - Creeks - Alu Glass | 2 | 2 | Katameya - Creeks - Alu Glass2 | 10000000
Katameya - Creeks | 2 | 2 | Katameya - Creeks2 | 45000000
Katameya - Creeks | 3 | 3 | Katameya - Creeks3 | 45000000
Katameya - Creeks | 4 | 4 | Katameya - Creeks4 | 20000000
KFW | 109 | 109 | KFW109 | 128570.36
KFW | 110 | 110 | KFW110 | 377225.16
KFW-Road Signals | 1 | 1 | KFW-Road Signals 1 | 35249.2
Khatatba Bridge | 1 | 1 | Khatatba Bridge1 | 803531.75
Khatatba Bridge | 2 | 2 | Khatatba Bridge2 | 7509538.3
Khatatba Bridge | 4 | 4 | Khatatba Bridge4 | 36303482.3
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 252408.0531
KSA-Tarek AbdelHakim Center | 2 | 2 | KSA-Tarek AbdelHakim Center2 | 562894.3581
KSA-Tarek AbdelHakim Center | 3 | 3 | KSA-Tarek AbdelHakim Center3 | 194180.7389
KSA-Tarek AbdelHakim Center | 4 | 4 | KSA-Tarek AbdelHakim Center4 | 242494.97
KSA-Tarek AbdelHakim Center | 5 | 5 | KSA-Tarek AbdelHakim Center5 | 260811.86
KSA-Tarek AbdelHakim Center | 6 | 6 | KSA-Tarek AbdelHakim Center6 | 253333.77
KSA-Tarek AbdelHakim Center | 7 | 7 | KSA-Tarek AbdelHakim Center7 | 450546.16
KSA-Tarek AbdelHakim Center | 8 | 8 | KSA-Tarek AbdelHakim Center8 | 630195.46
KSA-Tarek AbdelHakim Center | 9 | 9 | KSA-Tarek AbdelHakim Center9 | 1513478.59
KSA-Tarek AbdelHakim Center | 10 | 10 | KSA-Tarek AbdelHakim Center10 | 1468894.06
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 930841.52
LEKELA | 1 | 1 | LEKELA1 | 1670902.46
LEKELA | 2 | 2 | LEKELA2 | 1067868.0976
LEKELA | 3 | 3 | LEKELA3 | 1758948.8952
LEKELA | 4 | 4 | LEKELA4 | 652923.5
LEKELA | 5 | 5 | LEKELA5 | 7094954.7715
LEKELA | 6 | 6 | LEKELA6 | 14840272.4231
LEKELA | 7 | 7 | LEKELA7 | 15073158.35
LEKELA | 8 | 8 | LEKELA8 | 32746957.2169
LEKELA | 8.1 | 8 | LEKELA8 | 610200
LEKELA | 9 | 9 | LEKELA9 | 18594958.1925
LEKELA | 10 | 10 | LEKELA10 | 21709399.51
LEKELA | 11 | 11 | LEKELA11 | 14896483.6
LEKELA | 12 | 12 | LEKELA12 | 21477147.745
LEKELA | 13 | 13 | LEKELA13 | 2329136.4958
LEKELA | 14 | 14 | LEKELA14 | 12951636.6142
LEKELA | 15 | 15 | LEKELA15 | 203400
LEKELA | 15.1 | 15 | LEKELA15 | 406481.34
LEKELA | 15.2 | 15 | LEKELA15 | 3229199.85
LEKELA | 16 | 16 | LEKELA16 | 8212932
LEKELA - Supply Bill | 1 | 1 | LEKELA - Supply Bill1 | 124228
LEKELA- | 1 | 1 | LEKELA-1 | 3229199.85
LEKELA Remedial | 2 | 2 | LEKELA Remedial2 | 7000000.52
LEKELA Remedial | 3 | 3 | LEKELA Remedial3 | 3000357.34
LEKELA Remedial | 4 | 4 | LEKELA Remedial4 | 6400022.32
LEKELA Remedial | 1 | 1 | LEKELA Remedial1 | 6281009.56
LEKELA | 1 | 1 | LEKELA1 | 36300000
MDF Factory | 1 | 1 | MDF Factory1 | 6231879
MDF Factory | 2 | 2 | MDF Factory2 | 7093735
MDF Factory | 3 | 3 | MDF Factory3 | 8598867
MDF Factory | 4 | 4 | MDF Factory4 | 8359615
MDF Factory | 5 | 5 | MDF Factory5 | 10000000
MDF Factory | 5.1 | 5 | MDF Factory5 | 11785508.92
MDF Factory | 6 | 6 | MDF Factory6 | 10000000
MDF Factory | 6.1 | 6 | MDF Factory6 | 7171193.33
MDF Factory | 7 | 7 | MDF Factory7 | 13606480
MDF Factory | 8 | 8 | MDF Factory8 | 13352571.68
MDF Factory | 9 | 9 | MDF Factory9 | 5188292.65
MDF Factory | 10 | 10 | MDF Factory10 | 10230767.51
MDF Factory | 11 | 11 | MDF Factory11 | 8835349.23
MDF Factory | 12 | 12 | MDF Factory12 | 25380982.3
MDF Factory | 13 | 13 | MDF Factory13 | 2351273.22
MDF Factory | 14 | 14 | MDF Factory14 | 10000000
MDF Factory | 14.1 | 14 | MDF Factory14 | 1219362.36
MDF Factory | 15 | 15 | MDF Factory15 | 10000000
MDF Factory | 15.1 | 15 | MDF Factory15 | 812468.25
MDF Factory | 16 | 16 | MDF Factory16 | 10000000
MDF Factory | 16.1 | 16 | MDF Factory16 | 601848.06
MDF Factory | 17 | 17 | MDF Factory17 | 7000000
MDF Factory | 17.1 | 17 | MDF Factory17 | 6701835.53
MDF Factory | 18 | 18 | MDF Factory18 | 3474417.48
MDF Factory | 19 | 19 | MDF Factory19 | 8855940.16
MDF Factory | 20 | 20 | MDF Factory20 | 1506264.66
MDF Factory | 21 | 21 | MDF Factory21 | 10000000
MDF Factory | 21.1 | 21 | MDF Factory21 | 6783340.22
MDF Factory | 22 | 22 | MDF Factory22 | 9454487.21
MDF Factory | 23 | 23 | MDF Factory23 | 10035885.59
MDF Factory | 24 | 24 | MDF Factory24 | 5923051.17
MDF Factory | 25 | 25 | MDF Factory25 | 4519315.77
MDF Factory | 26 | 26 | MDF Factory26 | 12901160.06
MDF Factory | 27 | 27 | MDF Factory27 | 13230747.82
MDF Factory | 27.1 | 27 | MDF Factory27 | 5946852.52
MDF Factory | 28 | 28 | MDF Factory28 | 5380287.99
MDF Factory | 29 | 29 | MDF Factory29 | 10038430.32
MDF Factory | 30 | 30 | MDF Factory30 | 11530799.53
MDF Factory | 31 | 31 | MDF Factory31 | 18846610.6
MDF Factory | 32 | 32 | MDF Factory32 | 2726460
MDF Factory | 33 | 33 | MDF Factory33 | 8808260.33
MDF Factory | 34 | 34 | MDF Factory34 | 12466636.78
MDF Factory | 35 | 35 | MDF Factory35 | 11964736.84
MDF Factory | 36 | 36 | MDF Factory36 | 10194821.77
MDF Factory | 37 | 37 | MDF Factory37 | 4465149.39
MDF Factory | 38 | 38 | MDF Factory38 | 9539881.65
MDF Factory | 39 | 39 | MDF Factory39 | 6984174.92
MDF Factory | 40 | 40 | MDF Factory40 | 13054639.6
MDF Factory | 41 | 41 | MDF Factory41 | 8347962.7
MDF Factory | 42 | 42 | MDF Factory42 | 3999590
MDF Factory | 42.1 | 42 | MDF Factory42 | 3602411.04
MDF Factory | 43 | 43 | MDF Factory43 | 44999590
MDF Factory | 43.1 | 43 | MDF Factory43 | 999590
MDF Factory - Equip. | 1 | 1 | MDF Factory - Equip.1 | 479255
MDF Factory - Equip. | 2 | 2 | MDF Factory - Equip.2 | 2957905.39
MDF Factory - Equip. | 3 | 3 | MDF Factory - Equip.3 | 2467707.5
MDF Factory - Equip. | 4 | 4 | MDF Factory - Equip.4 | 2118826
MDF Factory - Equip. | 5 | 5 | MDF Factory - Equip.5 | 2067056
MDF Factory - Equip. | 6 | 6 | MDF Factory - Equip.6 | 569764
MDF Factory - Equip. | 7 | 7 | MDF Factory - Equip.7 | 795032
MDF Factory - Equip. | 8 | 8 | MDF Factory - Equip.8 | 322760
MDF Factory - Equip. | 9 | 9 | MDF Factory - Equip.9 | 1546900
MDF Factory - Equip. | 10 | 10 | MDF Factory - Equip.10 | 362327.85
MDF Factory - Equip. | 11 | 11 | MDF Factory - Equip.11 | 115740.16
MDF Factory - Equip. | 12 | 12 | MDF Factory - Equip.12 | 617997.99
MDF Factory - Equip. | 13 | 13 | MDF Factory - Equip.13 | 1033353.65
MDF Factory - Equip. | 14 | 14 | MDF Factory - Equip.14 | 1342515
MDF Factory - Equip. | 15 | 15 | MDF Factory - Equip.15 | 1508230
MDF Factory - Equip. | 16 | 16 | MDF Factory - Equip.16 | 963455.46
MDF Factory - Equip. | 17 | 17 | MDF Factory - Equip.17 | 359356.67
MDF Factory - Equip. | 18 | 18 | MDF Factory - Equip.18 | 536737.62
MDF Factory - Equip. | 19 | 19 | MDF Factory - Equip.19 | 1190791
MDF Factory - Equip. | 20 | 20 | MDF Factory - Equip.20 | 606416.12
MDF Factory - Equip. | 21 | 21 | MDF Factory - Equip.21 | 600370.17
MDF Factory - Equip. | 22 | 22 | MDF Factory - Equip.22 | 205199.38
MDF Factory - Equip. | 23 | 23 | MDF Factory - Equip.23 | 545334.31
MDF Factory - Equip. | 24 | 24 | MDF Factory - Equip.24 | 345289.58
MDF Factory - Equip. | 25 | 25 | MDF Factory - Equip.25 | 637190.72
MDF Factory - Local Fabrication | 1 | 1 | MDF Factory - Local Fabrication1 | 920351.25
MDF Factory - Local Fabrication | 2 | 2 | MDF Factory - Local Fabrication2 | 711105.4
MDF Factory - Local Fabrication | 3 | 3 | MDF Factory - Local Fabrication3 | 897908
MDF Factory - Local Fabrication | 4 | 4 | MDF Factory - Local Fabrication4 | 667444
MDF Factory - Local Fabrication | 5 | 5 | MDF Factory - Local Fabrication5 | 2517907.41
MDF Factory - Local Fabrication | 6 | 6 | MDF Factory - Local Fabrication6 | 737043.71
MDF Factory - Local Fabrication | 7 | 7 | MDF Factory - Local Fabrication7 | 785269
MDF Factory - Local Fabrication | 8 | 8 | MDF Factory - Local Fabrication8 | 381060.37
MDF Factory - Local Fabrication | 9 | 9 | MDF Factory - Local Fabrication9 | 1752018.76
MDF Factory - Local Fabrication | 10 | 10 | MDF Factory - Local Fabrication10 | 2881529.05
MDF Factory - Local Fabrication | 11 | 11 | MDF Factory - Local Fabrication11 | 2412700.43
MDF Factory - Local Fabrication | 14 | 14 | MDF Factory - Local Fabrication14 | 10315795
MDF Factory - Local Fabrication | 15 | 15 | MDF Factory - Local Fabrication15 | 2970230
MDF Factory - Local Fabrication | 16 | 16 | MDF Factory - Local Fabrication16 | 1262500
MDF Factory - Local Fabrication | 18 | 18 | MDF Factory - Local Fabrication18 | 4265111
MDF Factory - Local Fabrication | 19 | 19 | MDF Factory - Local Fabrication19 | 3358613
MDF Factory | 1 | 1 | MDF Factory1 | 41622365.4
MDF Factory | 2 | 2 | MDF Factory2 | 6300000
MDF Factory | 3 | 3 | MDF Factory3 | 2000000
MDF Factory | 4 | 4 | MDF Factory4 | 2000000
MDF Factory | 5 | 5 | MDF Factory5 | 10016624.86
MDF Factory | 6 | 6 | MDF Factory6 | 7332000
MDF Factory | 7 | 7 | MDF Factory7 | 6000000
MDF Factory | 8 | 8 | MDF Factory8 | 11000000
MDF Factory | 9 | 9 | MDF Factory9 | 13754630
MDF Factory | 10 | 10 | MDF Factory10 | 1488562.75
MDF Factory | 11 | 11 | MDF Factory11 | 3000000
MDF Factory-F.F V.O | 1 | 1 | MDF Factory-F.F V.O1 | 8500000
MDF Factory-F.F V.O | 2 | 2 | MDF Factory-F.F V.O2 | 7800000
MDF Factory-Hold Amount release | 1 | 1 | MDF Factory-Hold Amount release1 | 2000000
MDF Factory-Local Fab. | 1 | 1 | MDF Factory-Local Fab.1 | 3500000
MDF Factory | 3 | 3 | MDF Factory3 | 7811797.56
MDF Factory | 4 | 4 | MDF Factory4 | 9000000
MDF Factory | 5 | 5 | MDF Factory5 | 7000000
MDF Factory | 6 | 6 | MDF Factory6 | 4000000
MDF Factory | 7 | 7 | MDF Factory7 | 40000000
MDF Factory | 8 | 8 | MDF Factory8 | 5000000
MDF Factory solera | 1 | 1 | MDF Factory solera1 | 8000000
MDF Factory solera | 2 | 2 | MDF Factory solera2 | 18121000
MDF Factory solera | 3 | 3 | MDF Factory solera3 | 7600000
MDF Factory-P.O | 3 | 3 | MDF Factory-P.O3 | 23100000
Mechanical Installation | 1 | 1 | Mechanical Installation1 | 15000000
Mintra | 1 | 1 | Mintra1 | 5500000
Mintra | 2 | 2 | Mintra2 | 3000000
Mintra | 3 | 3 | Mintra3 | 2220782.14
Mintra | 4 | 4 | Mintra4 | 3500000
Mintra | 5 | 5 | Mintra5 | 8000000
Mintra | 6 | 6 | Mintra6 | 6000000
Mintra | 7 | 7 | Mintra7 | 2005948.91
Mintra | 1 | 1 | Mintra1 | 10000000
Mintra-Hanger 1200m2 | 1 | 1 | Mintra-Hanger 1200m21 | 531998.67
Mintra-Hanger 1200m2 | 2 | 2 | Mintra-Hanger 1200m22 | -6217.18
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 2533668.0255
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 2620895.13
Mivida-PK#140 | 3 | 3 | Mivida-PK#1403 | 4070832.3885
Mivida-PK#140 | 4 | 4 | Mivida-PK#1404 | 999645.4398
Mivida-PK#140 | 5 | 5 | Mivida-PK#1405 | 1337507.07
Mivida-PK#140 | 6 | 6 | Mivida-PK#1406 | 10719905.22
Mivida-PK#140 | 7 | 7 | Mivida-PK#1407 | 6547225.82
Mivida-PK#140 | 8 | 8 | Mivida-PK#1408 | 4740517.5525
Mivida-PK#140 | 9 | 9 | Mivida-PK#1409 | 4559999.09
Mivida-PK#140 | 10 | 10 | Mivida-PK#14010 | 5679423.0614
Mivida-PK#140 | 11 | 11 | Mivida-PK#14011 | 2647674.17
Mivida-PK#140 | 12 | 12 | Mivida-PK#14012 | 4687303.44
Mivida-PK#140 | 13 | 13 | Mivida-PK#14013 | 1169770.65
Mivida-PK#140 | 14 | 14 | Mivida-PK#14014 | 7336701.1
Mivida-PK#140 | 15 | 15 | Mivida-PK#14015 | 10305723.52
Mivida-PK#140 | 16 | 16 | Mivida-PK#14016 | 10553431.24
Mivida-PK#140 | 17 | 17 | Mivida-PK#14017 | 11726998.43
Mivida-PK#140 | 18 | 18 | Mivida-PK#14018 | 3831058.93
Mivida-PK#140 | 19 | 19 | Mivida-PK#14019 | 8885358.62
Mivida-PK#140 | 20 | 20 | Mivida-PK#14020 | 5084359.83
Mivida-PK#140 | 21 | 21 | Mivida-PK#14021 | 8185193.83
Mivida-PK#140 | 22 | 22 | Mivida-PK#14022 | 4603109.14
Mivida-PK#140 | 23 | 23 | Mivida-PK#14023 | 3870461.7
Mivida-PK#140 | 24 | 24 | Mivida-PK#14024 | 3732732.7981
Mivida-PK#140 | 25 | 25 | Mivida-PK#14025 | 9016182.24
Mivida-PK#140 | 26 | 26 | Mivida-PK#14026 | 3143991.8
Mivida-PK#140 | 27 | 27 | Mivida-PK#14027 | 5157960.04
Mivida-PK#140- Social Insurance | 1 | 1 | Mivida-PK#140- Social Insurance1 | 509706.15
Mivida-PK#140- Social Insurance | 2 | 2 | Mivida-PK#140- Social Insurance2 | 1677431
Mivida-PK#140- Social Insurance | 3 | 3 | Mivida-PK#140- Social Insurance3 | 596538.75
Mivida-PK#140- Social Insurance | 4 | 4 | Mivida-PK#140- Social Insurance4 | 908034.47
Mivida-PK#140- Social Insurance | 5 | 5 | Mivida-PK#140- Social Insurance5 | 1805452.05
Mivida-PK#140- Social Insurance | 6 | 6 | Mivida-PK#140- Social Insurance6 | 976304.25
Mivida-PK#140- Social Insurance | 7 | 7 | Mivida-PK#140- Social Insurance7 | 871421.04
Mivida-PK#140- Social Insurance | 8 | 8 | Mivida-PK#140- Social Insurance8 | 1298461.89
Mivida-PK#140- Social Insurance | 9 | 9 | Mivida-PK#140- Social Insurance9 | 494886.87
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 15567604.3
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 7313962.6
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 18095262.89
Mivida-PK#189 | 2 | 2 | Mivida-PK#1892 | 22529255.88
Mivida-PK#189 | 3 | 3 | Mivida-PK#1893 | 19800407.88
Mivida-PK#189 | 4 | 4 | Mivida-PK#1894 | 27644756.83
Mivida-PK#189 | 5 | 5 | Mivida-PK#1895 | 46638711.45
Mivida-PK#189 | 6 | 6 | Mivida-PK#1896 | 70000000
Mivida-PK#189 | 7 | 7 | Mivida-PK#1897 | 38664242.89
Mivida-PK#189 | 8 | 8 | Mivida-PK#1898 | 62566272.8
Mivida-PK#189 | 9 | 9 | Mivida-PK#1899 | 37089198
Mivida-PK#189 | 10 | 10 | Mivida-PK#18910 | 22123110.41
Mivida-PK#189 | 11 | 11 | Mivida-PK#18911 | 18794302.39
Mivida-PK#189 | 12 | 12 | Mivida-PK#18912 | 16890748.06
Mivida-PK#189 | 13 | 13 | Mivida-PK#18913 | 50032149.11
Mivida-PK#189 | 14 | 14 | Mivida-PK#18914 | 22045664.4
Mivida-PK#189 | 15 | 15 | Mivida-PK#18915 | 20013901.02
Mivida-PK#189 | 16 | 16 | Mivida-PK#18916 | 22512171.88
Mivida-PK#189 | 17 | 17 | Mivida-PK#18917 | 47104890.0563
Mivida-PK#189 | 18 | 18 | Mivida-PK#18918 | 20024965.62
Mivida-PK#189 | 19 | 19 | Mivida-PK#18919 | 23323710.11
Mivida-PK#189 | 21 | 21 | Mivida-PK#18921 | 14476604.63
Mivida-PK#189 | 22 | 22 | Mivida-PK#18922 | 17552608.99
Mivida-PK#189 | 23 | 23 | Mivida-PK#18923 | 14242173.09
Mivida-PK#189 | 24 | 24 | Mivida-PK#18924 | 13803484.92
Mivida-PK#189 | 25 | 25 | Mivida-PK#18925 | 28360739.45
Mivida-PK#189 | 26 | 26 | Mivida-PK#18926 | 14177811.26
Mivida-PK#189 | 27 | 27 | Mivida-PK#18927 | 4389859.04
Mivida-PK#189 | 28 | 28 | Mivida-PK#18928 | 2409288.21
Mivida-PK#189 | 29 | 29 | Mivida-PK#18929 | 2690517.47
Mivida-PK#189 | 30 | 30 | Mivida-PK#18930 | 14412191.12
Mivida-PK#189 | 20 | 20 | Mivida-PK#18920 | 135145955
Mivida-PK#189 - Social insurance | 1 | 1 | Mivida-PK#189 - Social insurance1 | 5182786.9
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 99600000
MOC | 1 | 1 | MOC1 | 33350000
New Gas Station | 1 | 1 | New Gas Station1 | 2201210.4
New Gas Station | 2 | 2 | New Gas Station2 | 1419355.25
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 23161171
New Giza Hospital | 2 | 2 | New Giza Hospital2 | 13964209
New Giza Hospital | 3 | 3 | New Giza Hospital3 | 7088017
New Giza Hospital | 4 | 4 | New Giza Hospital4 | 25531752
New Giza Hospital | 5 | 5 | New Giza Hospital5 | 9692684
New Giza Hospital | 6 | 6 | New Giza Hospital6 | 12645886
New Giza Hospital | 7 | 7 | New Giza Hospital7 | 12694720
New Giza Hospital | 8 | 8 | New Giza Hospital8 | 11865059
New Giza Hospital | 9 | 9 | New Giza Hospital9 | 15594713
New Giza Hospital | 10 | 10 | New Giza Hospital10 | 14931468
New Giza Hospital | 11 | 11 | New Giza Hospital11 | 19979218
New Giza Hospital | 12 | 12 | New Giza Hospital12 | 21023839
New Giza Hospital | 13 | 13 | New Giza Hospital13 | 17903308
New Giza Hospital | 14 | 14 | New Giza Hospital14 | 15197022
New Giza Hospital | 15 | 15 | New Giza Hospital15 | 7535461
New Giza Hospital | 16 | 16 | New Giza Hospital16 | 7643976
New Giza Hospital | 18 | 18 | New Giza Hospital18 | 14511461
New Giza Hospital | 19 | 19 | New Giza Hospital19 | 3705542
New Giza Hospital | 20 | 20 | New Giza Hospital20 | 18995740
New Giza Hospital | 21 | 21 | New Giza Hospital21 | 4008305
New Giza Hospital | 22 | 22 | New Giza Hospital22 | 6681249
New Giza Hospital | 23 | 23 | New Giza Hospital23 | 3104562
New Giza Hospital | 24 | 24 | New Giza Hospital24 | 4494905.88
New Giza Hospital | 25 | 25 | New Giza Hospital25 | 10195246
New Giza Hospital | 26 | 26 | New Giza Hospital26 | 2983818.1724
New Giza Hospital | 26.1 | 26 | New Giza Hospital26 | 15145301
New Giza Hospital | 27 | 27 | New Giza Hospital27 | 2051894
New Giza Hospital | 28 | 28 | New Giza Hospital28 | 5534314
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 73512565
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 15000000
New Giza Hospital | 2 | 2 | New Giza Hospital2 | 2983818.1724
New Giza Hospital-Social Insurance | 1 | 1 | New Giza Hospital-Social Insurance1 | 3128055
New Giza Hospital-Social Insurance | 2 | 2 | New Giza Hospital-Social Insurance2 | 4605279
New Giza Hospital-Social Insurance | 3 | 3 | New Giza Hospital-Social Insurance3 | 2326029.9476
New Giza Hospital-Social Insurance | 4 | 4 | New Giza Hospital-Social Insurance4 | 1019222
NGU 2 | 25 | 25 | NGU 225 | 2468493.7
NGU 2 | 26 | 26 | NGU 226 | 4990186
NGU 2 | 27 | 27 | NGU 227 | 2104161
NGU 2 - Retension release | 1 | 1 | NGU 2 - Retension release1 | 313708
Old H1 remaining IPC | 1 | 1 | Old H1 remaining IPC1 | 250000
ORA - ZED | 1 | 1 | ORA - ZED1 | 9787286.79
ORA - ZED | 2 | 2 | ORA - ZED2 | 37532508
ORA - ZED | 3 | 3 | ORA - ZED3 | 27896354
ORA - ZED | 4 | 4 | ORA - ZED4 | 20888247.393
ORA - ZED | 5 | 5 | ORA - ZED5 | 33744386.154
ORA - ZED | 6 | 6 | ORA - ZED6 | 4374377.19
ORA - ZED | 7 | 7 | ORA - ZED7 | 5782895.78
ORA - ZED | 8 | 8 | ORA - ZED8 | 24387331.1
ORA - ZED | 9 | 9 | ORA - ZED9 | 22624923.97
ORA - ZED | 10 | 10 | ORA - ZED10 | 29047725.55
ORA - ZED | 20.1 | 20 | ORA - ZED20 | 16483569.19
ORA - ZED | 21 | 21 | ORA - ZED21 | 7443623.53
ORA - ZED | 22 | 22 | ORA - ZED22 | 8098825.75
ORA - ZED | 23 | 23 | ORA - ZED23 | 20215840.09
ORA - ZED | 24 | 24 | ORA - ZED24 | 6648903.39
ORA - ZED | 25 | 25 | ORA - ZED25 | 2e-05
ORA - ZED | 26 | 26 | ORA - ZED26 | 6863669.19
ORA - ZED | 26.1 | 26 | ORA - ZED26 | 1824548.9
ORA - ZED | 26.2 | 26 | ORA - ZED26 | 1119976.03
ORA - ZED | 27 | 27 | ORA - ZED27 | 8872947.14
ORA - ZED | 28 | 28 | ORA - ZED28 | 9105384.7
ORA - ZED | 29 | 29 | ORA - ZED29 | 10687601.99
ORA - ZED | 30 | 30 | ORA - ZED30 | 11585957.67
ORA - ZED | 31 | 31 | ORA - ZED31 | 5000000
ORA - ZED | 31.1 | 31 | ORA - ZED31 | 5253641.2
ORA - ZED | 32 | 32 | ORA - ZED32 | 8010573.17
ORA - ZED | 33 | 33 | ORA - ZED33 | 12164893.39
ORA - ZED | 34 | 34 | ORA - ZED34 | 9568963.5
ORA - ZED | 35 | 35 | ORA - ZED35 | 7391485.26
ORA - ZED | 36 | 36 | ORA - ZED36 | 7054023.71
ORA - ZED | 37 | 37 | ORA - ZED37 | 23554316.1
ORA - ZED | 38 | 38 | ORA - ZED38 | 17627053.17
ORA - ZED | 39 | 39 | ORA - ZED39 | 7606231.63
ORA - ZED | 40 | 40 | ORA - ZED40 | 3717952.37
ORA - ZED | 41 | 41 | ORA - ZED41 | 4428778.21
ORA - ZED | 42 | 42 | ORA - ZED42 | 70851.77
ORA - ZED | 43 | 43 | ORA - ZED43 | 6004454.53
ORA - ZED - Compansation | 1 | 1 | ORA - ZED - Compansation1 | 12000000
ORA - ZED | 1 | 1 | ORA - ZED1 | 91380773
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 2167633.67
ORA - ZED - Landscape | 2 | 2 | ORA - ZED - Landscape2 | 1719649.2
ORA - ZED - Landscape | 3 | 3 | ORA - ZED - Landscape3 | 1775205.58
ORA - ZED - Landscape | 4 | 4 | ORA - ZED - Landscape4 | 4074938.81
ORA - ZED - Landscape | 5 | 5 | ORA - ZED - Landscape5 | 2726488.3
ORA - ZED - Landscape | 6 | 6 | ORA - ZED - Landscape6 | 3120690.89
ORA - ZED - Landscape | 7 | 7 | ORA - ZED - Landscape7 | 964764.3
ORA - ZED - Landscape | 8 | 8 | ORA - ZED - Landscape8 | 5158038.94
ORA - ZED - Landscape | 9 | 9 | ORA - ZED - Landscape9 | 3636861
ORA - ZED - Landscape | 9.1 | 9 | ORA - ZED - Landscape9 | 226226.97
ORA - ZED - Landscape | 10 | 10 | ORA - ZED - Landscape10 | 6562980.72
ORA - ZED - Landscape | 11 | 11 | ORA - ZED - Landscape11 | 5312426.17
ORA - ZED - Landscape | 12 | 12 | ORA - ZED - Landscape12 | 6030251.47
ORA - ZED - Landscape | 14 | 14 | ORA - ZED - Landscape14 | 868255.79
ORA - ZED - Landscape | 15 | 15 | ORA - ZED - Landscape15 | 3165189.2
ORA - ZED - Landscape | 16 | 16 | ORA - ZED - Landscape16 | 1521916.47
ORA - ZED - Landscape | 17 | 17 | ORA - ZED - Landscape17 | 1313619.66
ORA - ZED - Landscape | 18 | 18 | ORA - ZED - Landscape18 | 975356.43
ORA - ZED - Landscape | 19 | 19 | ORA - ZED - Landscape19 | 618692.48
ORA - ZED - Landscape | 20 | 20 | ORA - ZED - Landscape20 | 1177303.85
ORA - ZED - Landscape | 21 | 21 | ORA - ZED - Landscape21 | 108767.39
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 9635108.4
ORA - ZED | 2 | 2 | ORA - ZED2 | 256451321
ORA - ZED | 3 | 3 | ORA - ZED3 | 50172571.863
ORA - ZED | 4 | 4 | ORA - ZED4 | 25000000
ORA - ZED | 5 | 5 | ORA - ZED5 | 50000000
ORA - ZED | 6 | 6 | ORA - ZED6 | 10000000
ORA - ZED | 7 | 7 | ORA - ZED7 | 5000000
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 14536704.19
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 20471935.63
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 9325142.71
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 28728856.89
ORA - ZED - ph.02 | 5 | 5 | ORA - ZED - ph.025 | 12407121.98
ORA - ZED - ph.02 | 6 | 6 | ORA - ZED - ph.026 | 16610991.38
ORA - ZED - ph.02 | 7 | 7 | ORA - ZED - ph.027 | 8000000
ORA - ZED - ph.02 | 7.1 | 7 | ORA - ZED - ph.027 | 16000000
ORA - ZED - ph.02 | 7.2 | 7 | ORA - ZED - ph.027 | 8100387.28
ORA - ZED - ph.02 | 8 | 8 | ORA - ZED - ph.028 | 8595540.37
ORA - ZED - ph.02 | 9 | 9 | ORA - ZED - ph.029 | 7163536.59
ORA - ZED - ph.02 | 10 | 10 | ORA - ZED - ph.0210 | 20828447.26
ORA - ZED - ph.02 | 11 | 11 | ORA - ZED - ph.0211 | 12170282.5
ORA - ZED - ph.02 | 12 | 12 | ORA - ZED - ph.0212 | 14759397.95
ORA - ZED - ph.02 | 13 | 13 | ORA - ZED - ph.0213 | 13268244.56
ORA - ZED - ph.02 | 14 | 14 | ORA - ZED - ph.0214 | 15256729.38
ORA - ZED - ph.02 | 15 | 15 | ORA - ZED - ph.0215 | 11384143.67
ORA - ZED - ph.02 | 16 | 16 | ORA - ZED - ph.0216 | 9858410.94
ORA - ZED - ph.02 | 17 | 17 | ORA - ZED - ph.0217 | 8988166.12
ORA - ZED - ph.02 | 18 | 18 | ORA - ZED - ph.0218 | 13223027.75
ORA - ZED - ph.02 | 19 | 19 | ORA - ZED - ph.0219 | 6921352.11
ORA - ZED - ph.02 | 20 | 20 | ORA - ZED - ph.0220 | 3038540.29
ORA - ZED - ph.02 | 21 | 21 | ORA - ZED - ph.0221 | 4532160.06
ORA - ZED - ph.02 | 22 | 22 | ORA - ZED - ph.0222 | 8297638.82
ORA - ZED - ph.02 | 23 | 23 | ORA - ZED - ph.0223 | 564270
ORA - ZED - ph.02 | 24 | 24 | ORA - ZED - ph.0224 | 1374587.38
ORA - ZED - ph.02 | 25 | 25 | ORA - ZED - ph.0225 | 996461.29
ORA - ZED - ph.02 | 26 | 26 | ORA - ZED - ph.0226 | 2944524.93
ORA - ZED - ph.02 | 27 | 27 | ORA - ZED - ph.0227 | 5268993.93
ORA - ZED - ph.02 | 28 | 28 | ORA - ZED - ph.0228 | 1922751.71
ORA - ZED - ph.02 | 29 | 29 | ORA - ZED - ph.0229 | 5009481.72
ORA - ZED - ph.02 | 30 | 30 | ORA - ZED - ph.0230 | 73017
ORA - ZED - ph.02 | 31 | 31 | ORA - ZED - ph.0231 | 3717995
ORA - ZED - ph.02 | 32 | 32 | ORA - ZED - ph.0232 | 2836390.67
ORA - ZED - ph.02 | 33 | 33 | ORA - ZED - ph.0233 | 1e-05
ORA - ZED - ph.02 | 34 | 34 | ORA - ZED - ph.0234 | 1e-05
ORA - ZED - ph.02 | 35 | 35 | ORA - ZED - ph.0235 | 1e-05
ORA - ZED - ph.02 | 36 | 36 | ORA - ZED - ph.0236 | 4160916.8
ORA - ZED - ph.02 | 37 | 37 | ORA - ZED - ph.0237 | 8601492.56
ORA - ZED - ph.02 | 38 | 38 | ORA - ZED - ph.0238 | 3811960.86
ORA - ZED - ph.02 - DP | 1 | 1 | ORA - ZED - ph.02 - DP1 | 25000000
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 3000000
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 26000000
ORA - ZED - Social Insurrance | 1 | 1 | ORA - ZED - Social Insurrance1 | 4101935.6
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | PH.2-El Sewedy Uni. - Enabling1 | 2832501.18
PH.2-El Sewedy Uni. - Enabling | 2 | 2 | PH.2-El Sewedy Uni. - Enabling2 | 13318143.89
PH.2-El Sewedy Uni. - Enabling | 3 | 3 | PH.2-El Sewedy Uni. - Enabling3 | 17089175.5
PH.2-El Sewedy Uni. - Enabling | 4 | 4 | PH.2-El Sewedy Uni. - Enabling4 | 14773850.81
PH.2-El Sewedy Uni. - Enabling | 5 | 5 | PH.2-El Sewedy Uni. - Enabling5 | 2392694.9
PH.2-El Sewedy Uni. - Enabling | 6 | 6 | PH.2-El Sewedy Uni. - Enabling6 | 7788095.22
PH.2-El Sewedy Uni. - Enabling | 7 | 7 | PH.2-El Sewedy Uni. - Enabling7 | 3548357.43
PH.2-El Sewedy Uni. - Enabling | 8 | 8 | PH.2-El Sewedy Uni. - Enabling8 | 1607563.1
PH.2-El Sewedy Uni. - Enabling | 9 | 9 | PH.2-El Sewedy Uni. - Enabling9 | 8739144.88
PH.2-El Sewedy Uni. - Enabling | 10 | 10 | PH.2-El Sewedy Uni. - Enabling10 | 7703511.41
PH.2-El Sewedy Uni. - Enabling - Retention release | 1 | 1 | PH.2-El Sewedy Uni. - Enabling - Retention release1 | 2972186.2
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 15636298.9
PH.2-El Sewedy Uni. - Finishes | 1.1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 20000000
PH.2-El Sewedy Uni. - Finishes | 2 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 5698476.15
PH.2-El Sewedy Uni. - Finishes | 2.1 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 21059913.65
PH.2-El Sewedy Uni. - Finishes | 3 | 3 | PH.2-El Sewedy Uni. - Finishes3 | 23262698.8
PH.2-El Sewedy Uni. - Finishes | 4 | 4 | PH.2-El Sewedy Uni. - Finishes4 | 18322600.95
PH.2-El Sewedy Uni. - Finishes | 5 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 10000000
PH.2-El Sewedy Uni. - Finishes | 5.1 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 54006362.98
PH.2-El Sewedy Uni. - Finishes | 6 | 6 | PH.2-El Sewedy Uni. - Finishes6 | 8883254.07
PH.2-El Sewedy Uni. - Finishes | 7 | 7 | PH.2-El Sewedy Uni. - Finishes7 | 25755604.75
PH.2-El Sewedy Uni. - Finishes | 8 | 8 | PH.2-El Sewedy Uni. - Finishes8 | 25127325.53
PH.2-El Sewedy Uni. - Finishes | 9 | 9 | PH.2-El Sewedy Uni. - Finishes9 | 20493846.09
PH.2-El Sewedy Uni. - Finishes | 10 | 10 | PH.2-El Sewedy Uni. - Finishes10 | 9765894.8
PH.2-El Sewedy Uni. - Finishes | 11 | 11 | PH.2-El Sewedy Uni. - Finishes11 | 13851401.63
PH.2-El Sewedy Uni. - Finishes | 12 | 12 | PH.2-El Sewedy Uni. - Finishes12 | 23340124.9
PH.2-El Sewedy Uni. - Finishes | 13 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 10000000
PH.2-El Sewedy Uni. - Finishes | 13.1 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 5069000
PH.2-El Sewedy Uni. - Finishes | 13.2 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 1e-06
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 15000000
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 1 | 1 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance1 | 1023770.56
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 2 | 2 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance2 | 9146959.2
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 3 | 3 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance3 | 11400000
PH.2-El Sewedy Uni. | 1 | 1 | PH.2-El Sewedy Uni.1 | 31397824
PH.2-El Sewedy Uni. | 2 | 2 | PH.2-El Sewedy Uni.2 | 71347886
PI Parks - ELSEWEDY | 1 | 1 | PI Parks - ELSEWEDY1 | 3779007.23
PI Parks - ELSEWEDY | 2 | 2 | PI Parks - ELSEWEDY2 | 3366014.15
PI Parks - ELSEWEDY | 3 | 3 | PI Parks - ELSEWEDY3 | 823701.85
PI Parks - ELSEWEDY | 4 | 4 | PI Parks - ELSEWEDY4 | 2572231.81
PI Parks - ELSEWEDY | 5 | 5 | PI Parks - ELSEWEDY5 | 1175600.49
PI Parks - ELSEWEDY | 6 | 6 | PI Parks - ELSEWEDY6 | 689110.93
PI Parks - ELSEWEDY | 7 | 7 | PI Parks - ELSEWEDY7 | 1209313.47
PI Parks - ELSEWEDY | 8 | 8 | PI Parks - ELSEWEDY8 | 1492654.2
PI Parks - ELSEWEDY | 9 | 9 | PI Parks - ELSEWEDY9 | 1471457.2
PI Parks - ELSEWEDY | 10 | 10 | PI Parks - ELSEWEDY10 | 2470019.34
PI Parks - ELSEWEDY | 11 | 11 | PI Parks - ELSEWEDY11 | 945860.23
PI Parks - ELSEWEDY | 12 | 12 | PI Parks - ELSEWEDY12 | 1347803.37
PI Parks - ELSEWEDY | 13 | 13 | PI Parks - ELSEWEDY13 | 719804.13
PI Parks - ELSEWEDY | 14 | 14 | PI Parks - ELSEWEDY14 | 775351.46
PI Parks - ELSEWEDY | 15 | 15 | PI Parks - ELSEWEDY15 | 4484634.14
PI Parks - ELSEWEDY | 16 | 16 | PI Parks - ELSEWEDY16 | 4125986.43
PI Parks - ELSEWEDY | 17 | 17 | PI Parks - ELSEWEDY17 | 1375431.38
PI Parks - ELSEWEDY | 18 | 18 | PI Parks - ELSEWEDY18 | 3699864.67
PI Parks - ELSEWEDY | 19 | 19 | PI Parks - ELSEWEDY19 | 2311261.81
PI Parks - ELSEWEDY | 20 | 20 | PI Parks - ELSEWEDY20 | 1466574.4
PI Parks - ELSEWEDY | 21 | 21 | PI Parks - ELSEWEDY21 | 4361327.46
PI Parks - ELSEWEDY | 21.1 | 21 | PI Parks - ELSEWEDY21 | 972238.28
PI Parks - MEP | 1 | 1 | PI Parks - MEP1 | 7818631.64
PI Parks - MEP | 2 | 2 | PI Parks - MEP2 | 3907009.94
PI Parks - MEP | 3 | 3 | PI Parks - MEP3 | 3921714.73
PI Parks - MEP | 4 | 4 | PI Parks - MEP4 | 3366511.48
PI Parks - MEP | 5 | 5 | PI Parks - MEP5 | 6350059.5
PI Parks - MEP | 6 | 6 | PI Parks - MEP6 | 919139.23
PI Parks - MEP | 7 | 7 | PI Parks - MEP7 | 2661364.08
PI Parks - MEP | 8 | 8 | PI Parks - MEP8 | 1478131.5
PI Parks - MEP | 9 | 9 | PI Parks - MEP9 | 4813799.42
PI Parks - MEP1 | 1 | 1 | PI Parks - MEP11 | 5000000
PI Parks - MEP2 | 2 | 2 | PI Parks - MEP22 | 7600000
PK #107 | 8 | 8 | PK #1078 | 3005745.85
PK #107 | 9 | 9 | PK #1079 | 1418090.5
PK #107 | 10 | 10 | PK #10710 | 1453205.38
PK #107 | 11 | 11 | PK #10711 | 2354508.52
PK #107 | 12 | 12 | PK #10712 | 4193998
PK #107 | 13 | 13 | PK #10713 | 3281572.56
PK #107 | 14 | 14 | PK #10714 | 166316.41
PK #107 | 15 | 15 | PK #10715 | 1406606.27
PK #107 | 16 | 16 | PK #10716 | 131256.74
PK #107 | 17 | 17 | PK #10717 | 763627.7
PK #107 | 18 | 18 | PK #10718 | 1341459.14
PK #117 | 1 | 1 | PK #1171 | 4130129.12
PK #117 | 2 | 2 | PK #1172 | 6455421.01
PK #117 | 3 | 3 | PK #1173 | 4502026.51
PK #117 | 4 | 4 | PK #1174 | 3740180.08
PK #117 | 5 | 5 | PK #1175 | 4762507.56
PK #117 | 6 | 6 | PK #1176 | 5347404.79
PK #117 | 7 | 7 | PK #1177 | 118938.86
PK #117 | 8 | 8 | PK #1178 | 3896343.98
PK #117 | 9 | 9 | PK #1179 | 2578109.73
PK #117 | 10 | 10 | PK #11710 | 882296.11
PK #117 | 11 | 11 | PK #11711 | 809762.24
PK #117 | 12 | 12 | PK #11712 | 3376927.91
PK #117 | 13 | 13 | PK #11713 | 3145907.11
PK #117 | 14 | 14 | PK #11714 | 2483342.5
PK #117 - Social Insurance | 1 | 1 | PK #117 - Social Insurance1 | 229049.99
PK #117 - Social Insurance | 2 | 2 | PK #117 - Social Insurance2 | 163866
PK #117 - Social Insurance | 3 | 3 | PK #117 - Social Insurance3 | 56058.22
PK #117 - Social Insurance | 4 | 4 | PK #117 - Social Insurance4 | 57062.55
PK #117 - Social Insurance | 5 | 5 | PK #117 - Social Insurance5 | 285951.45
PK #22 - Social Insurance | 1 | 1 | PK #22 - Social Insurance1 | 263550
PK#22 | 37 | 37 | PK#2237 | 780036
PK#32 | 30 | 30 | PK#3230 | 900093.35
PKG#101 | 1 | 1 | PKG#1011 | 1029594.82
PKG#101 | 2 | 2 | PKG#1012 | 2222206.65
PKG#101 | 3 | 3 | PKG#1013 | 2246109.51
PKG#101 | 4 | 4 | PKG#1014 | 2512749.68
PKG#101 | 5 | 5 | PKG#1015 | 2051541.96
PKG#101 | 6 | 6 | PKG#1016 | 1988552.05
PKG#101 | 7 | 7 | PKG#1017 | 1824097.57
PKG#101 | 8 | 8 | PKG#1018 | 2104893.84
PKG#101 | 9 | 9 | PKG#1019 | 1424816.56
PKG#101 | 10 | 10 | PKG#10110 | 1976416.89
PKG#101 | 11 | 11 | PKG#10111 | 1709961.04
PKG#101 | 12 | 12 | PKG#10112 | 1146998.21
PKG#101 | 13 | 13 | PKG#10113 | 1343055.6
PKG#101 | 14 | 14 | PKG#10114 | 191421.72
PKG#101 | 15 | 15 | PKG#10115 | 303853.8
PKG#101 | 16 | 16 | PKG#10116 | 866491
PKG#101 | 17 | 17 | PKG#10117 | 3321316.23
PKG#101 | 18 | 18 | PKG#10118 | 1192690.23
PKG#101 | 19 | 19 | PKG#10119 | 596242.89
PKG#101 | 20 | 20 | PKG#10120 | 759353.32
PKG#101 | 21 | 21 | PKG#10121 | 1584188.58
PKG#101 | 22 | 22 | PKG#10122 | 594123.32
PKG#101 | 23 | 23 | PKG#10123 | 189091.52
PKG#101 | 24 | 24 | PKG#10124 | 546994.62
PKG#101- Social Insurance | 1 | 1 | PKG#101- Social Insurance1 | 877190.31
PKG#101- Social Insurance | 2 | 2 | PKG#101- Social Insurance2 | 693232.98
PKG#101 | 1 | 1 | PKG#1011 | 8723141
PKG#101-VO1&VO2 AP | 1 | 1 | PKG#101-VO1&VO2 AP1 | 7091710.52
PKG#144 | 2 | 2 | PKG#1442 | 2532120.6
PKG#144 | 3 | 3 | PKG#1443 | 6189125.05
PKG#144 | 4 | 4 | PKG#1444 | 6887337.01
PKG#144 | 5 | 5 | PKG#1445 | 7206339.73
PKG#144 | 6 | 6 | PKG#1446 | 14929468.44
PKG#144 | 7 | 7 | PKG#1447 | 12477244.23
PKG#144 | 8 | 8 | PKG#1448 | 8906660.63
PKG#144 | 9 | 9 | PKG#1449 | 9782161.34
PKG#144 | 10 | 10 | PKG#14410 | 11074114.43
PKG#144 | 11 | 11 | PKG#14411 | 7386054.95
PKG#144 | 12 | 12 | PKG#14412 | 15000000
PKG#144 | 12.1 | 12 | PKG#14412 | 6073691.31
PKG#144 | 13 | 13 | PKG#14413 | 14000000
PKG#144 | 14 | 14 | PKG#14414 | 10173240.83
PKG#144 | 15 | 15 | PKG#14415 | 9960243.27
PKG#144 | 16 | 16 | PKG#14416 | 1116473.97
PKG#144 - Social Insurance | 1 | 1 | PKG#144 - Social Insurance1 | 216614.52
PKG#144 - Social Insurance | 2 | 2 | PKG#144 - Social Insurance2 | 4748411.06
PKG#144 - Social Insurance | 3 | 3 | PKG#144 - Social Insurance3 | 506192.12
PKG#144 - Social Insurance | 4 | 4 | PKG#144 - Social Insurance4 | 687983.17
PKG#144 - Social Insurance | 5 | 5 | PKG#144 - Social Insurance5 | 2262789.43
PKG#144 - Social Insurance | 6 | 6 | PKG#144 - Social Insurance6 | 1430834.93
PKG#144 - Social Insurance | 7 | 7 | PKG#144 - Social Insurance7 | 596740.76
PKG#144 - Social Insurance | 8 | 8 | PKG#144 - Social Insurance8 | 342218.65
PKG#144 | 1 | 1 | PKG#1441 | 24600000
PKG#162 | 2 | 2 | PKG#1622 | 7794726.52
PKG#162 | 3 | 3 | PKG#1623 | 5119599.34
PKG#162 | 4 | 4 | PKG#1624 | 6336538.23
PKG#162 | 5 | 5 | PKG#1625 | 6124877.69
PKG#162 | 6 | 6 | PKG#1626 | 4824045.39
PKG#162 | 7 | 7 | PKG#1627 | 7215874.2121
PKG#162 | 8 | 8 | PKG#1628 | 9432027.72
PKG#162 | 9 | 9 | PKG#1629 | 9889305
PKG#162 | 10 | 10 | PKG#16210 | 13282474.2108
PKG#162 | 11 | 11 | PKG#16211 | 7840185.48
PKG#162 | 12 | 12 | PKG#16212 | 4608392
PKG#162 | 13 | 13 | PKG#16213 | 3429815.246
PKG#162 | 14 | 14 | PKG#16214 | 502581.43
PKG#162 | 15 | 15 | PKG#16215 | 3999402.59
PKG#162- Social Insurance | 1 | 1 | PKG#162- Social Insurance1 | 829293.83
PKG#162- Social Insurance | 2 | 2 | PKG#162- Social Insurance2 | 1584302
PKG#162- Social Insurance | 3 | 3 | PKG#162- Social Insurance3 | 1223560.05
PKG#162- Social Insurance | 4 | 4 | PKG#162- Social Insurance4 | 760409.01
PKG#162- Social Insurance | 5 | 5 | PKG#162- Social Insurance5 | 438178.63
PKG#162- Social Insurance | 6 | 6 | PKG#162- Social Insurance6 | 37250.26
PKG#162 | 1 | 1 | PKG#1621 | 7681619.5
PKG#163 | 2 | 2 | PKG#1632 | 1068966.43
PKG#163 | 3 | 3 | PKG#1633 | 2977091.11
PKG#163 | 4 | 4 | PKG#1634 | 6845695.77
PKG#163 | 5 | 5 | PKG#1635 | 3782501.29
PKG#163 | 6 | 6 | PKG#1636 | 6255172.17
PKG#163 | 7 | 7 | PKG#1637 | 4922193.5
PKG#163 | 8 | 8 | PKG#1638 | 6050639.77
PKG#163 | 9 | 9 | PKG#1639 | 4602212.16
PKG#163 | 10 | 10 | PKG#16310 | 2532838.57
PKG#163 | 11 | 11 | PKG#16311 | 3799097.57
PKG#163 | 12 | 12 | PKG#16312 | 2215480.09
PKG#163 | 13 | 13 | PKG#16313 | 3821253.39
PKG#163 | 14 | 14 | PKG#16314 | 10697999.42
PKG#163 | 15 | 15 | PKG#16315 | 4024676.65
PKG#163 | 16 | 16 | PKG#16316 | 3611195.74
PKG#163 | 17 | 17 | PKG#16317 | 2445757.34
PKG#163 | 18 | 18 | PKG#16318 | 2445757.34
PKG#163 | 19 | 19 | PKG#16319 | 6520369.14
PKG#163 | 20 | 20 | PKG#16320 | 3715617.2
PKG#163 | 21 | 21 | PKG#16321 | 5322260.63
PKG#163 | 22 | 22 | PKG#16322 | 2261775.79
PKG#163 | 23 | 23 | PKG#16323 | 3449740.5053
PKG#163 | 24 | 24 | PKG#16324 | 5681606.5237
PKG#163 | 25 | 25 | PKG#16325 | 11730565.831
PKG#163 | 26 | 26 | PKG#16326 | 6014332.37
PKG#163 | 27 | 27 | PKG#16327 | 3457484.33
PKG#163 | 28 | 28 | PKG#16328 | 18331730.1
PKG#163 | 29 | 29 | PKG#16329 | 18785649.76
PKG#163 | 30 | 30 | PKG#16330 | 3193802.31
PKG#163 | 31 | 31 | PKG#16331 | 1079324.09
PKG#163 | 32 | 32 | PKG#16332 | 4562478.02
PKG#163 | 33 | 33 | PKG#16333 | 0.0001
PKG#163 | 34 | 34 | PKG#16334 | 0.0001
PKG#163 | 35 | 35 | PKG#16335 | 0.0001
PKG#163- Social Insurance | 1 | 1 | PKG#163- Social Insurance1 | 78430
PKG#163- Social Insurance | 2 | 2 | PKG#163- Social Insurance2 | 720699.2
PKG#163- Social Insurance | 3 | 3 | PKG#163- Social Insurance3 | 277522.63
PKG#163- Social Insurance | 4 | 4 | PKG#163- Social Insurance4 | 451906.96
PKG#163- Social Insurance | 5 | 5 | PKG#163- Social Insurance5 | 754870.94
PKG#163- Social Insurance | 6 | 6 | PKG#163- Social Insurance6 | 961013.69
PKG#163- Social Insurance | 7 | 7 | PKG#163- Social Insurance7 | 275560.66
PKG#163- Social Insurance | 8 | 8 | PKG#163- Social Insurance8 | 434454.78
PKG#163- Social Insurance | 9 | 9 | PKG#163- Social Insurance9 | 2963675.17
PKG#163- Social Insurance | 10 | 10 | PKG#163- Social Insurance10 | 258797.58
PKG#163 | 1 | 1 | PKG#1631 | 24950583
PKG#177 | 2 | 2 | PKG#1772 | 10240448.36
PKG#177 | 3 | 3 | PKG#1773 | 3893019.54
PKG#177 | 4 | 4 | PKG#1774 | 4139690.65
PKG#177 | 5 | 5 | PKG#1775 | 1890262.73
PKG#177 | 6 | 6 | PKG#1776 | 2069539.45
PKG#177 | 7 | 7 | PKG#1777 | 30000000
PKG#177 | 8 | 8 | PKG#1778 | 6325726.09
PKG#177 | 9 | 9 | PKG#1779 | 1386804.78
PKG#177 | 10 | 10 | PKG#17710 | 1031892.42
PKG#177 | 11 | 11 | PKG#17711 | 1623911.78
PKG#177 | 12 | 12 | PKG#17712 | 11867471.98
PKG#177 | 13 | 13 | PKG#17713 | 4287396.18
PKG#177 | 14 | 14 | PKG#17714 | 3654358.5
PKG#177 | 15 | 15 | PKG#17715 | 30000000
PKG#177 | 16 | 16 | PKG#17716 | 8978914.16
PKG#177 | 17 | 17 | PKG#17717 | 311248.17
PKG#177 | 18 | 18 | PKG#17718 | 15059090.32
PKG#177 | 19 | 19 | PKG#17719 | 6143418.31
PKG#177 | 20 | 20 | PKG#17720 | 7621726.83
PKG#177 | 21 | 21 | PKG#17721 | 5553244.96
PKG#177 | 22 | 22 | PKG#17722 | 3436603.03
PKG#177 | 23 | 23 | PKG#17723 | 4324164.09
PKG#177 | 24 | 24 | PKG#17724 | 4835218.42
PKG#177 | 25 | 25 | PKG#17725 | 4062657.22
PKG#177 | 26 | 26 | PKG#17726 | 30000000
PKG#177 | 27 | 27 | PKG#17727 | 1920749.49
PKG#177 | 28 | 28 | PKG#17728 | 3761281.17
PKG#177 | 29 | 29 | PKG#17729 | 30000000
PKG#177 | 30 | 30 | PKG#17730 | 11174297.33
PKG#177 | 31 | 31 | PKG#17731 | 20000000
PKG#177 | 32 | 32 | PKG#17732 | 9586612.72
PKG#177 | 33 | 33 | PKG#17733 | 9774603.63
PKG#177 | 34 | 34 | PKG#17734 | 3243420.79
PKG#177 | 35 | 35 | PKG#17735 | 14874314
PKG#177 | 36 | 36 | PKG#17736 | 32974130.9
PKG#177 | 37 | 37 | PKG#17737 | 2963171.82
PKG#177 | 38 | 38 | PKG#17738 | 40830987.19
PKG#177 | 39 | 39 | PKG#17739 | 24380106.6
PKG#177 | 40 | 40 | PKG#17740 | 0.0001
PKG#177 | 41 | 41 | PKG#17741 | 1e-05
PKG#177 | 42 | 42 | PKG#17742 | 4198626.99
PKG#177 | 43 | 43 | PKG#17743 | 14488992.22
PKG#177 | 44 | 44 | PKG#17744 | 17144236.06
PKG#177 | 45 | 45 | PKG#17745 | 15002016.49
PKG#177 | 46 | 46 | PKG#17746 | 3048300.98
PKG#177 | 47 | 47 | PKG#17747 | 4274072.25
PKG#177 | 48 | 48 | PKG#17748 | 1e-06
PKG#177 | 49 | 49 | PKG#17749 | 1e-06
PKG#177 | 50 | 50 | PKG#17750 | 1e-06
PKG#177 | 51 | 51 | PKG#17751 | 1e-06
PKG#177 | 52 | 52 | PKG#17752 | 1e-06
PKG#177 | 53 | 53 | PKG#17753 | 1e-06
PKG#177 | 1 | 1 | PKG#1771 | 22337274.9
PKG#177 | 4 | 4 | PKG#1774 | 10000000
PKG#177 | 5 | 5 | PKG#1775 | 10000000
PKG#177 | 6 | 6 | PKG#1776 | 10000000
PKG#177 | 7 | 7 | PKG#1777 | 10000000
PKG#177 | 8 | 8 | PKG#1778 | 10000000
PKG#177 | 9 | 9 | PKG#1779 | 10000000
PKG#177 | 10 | 10 | PKG#17710 | 10000000
PKG#177 | 11 | 11 | PKG#17711 | 10000000
PKG#177 - SWI 07 | 10 | 10 | PKG#177 - SWI 0710 | 1e-05
PKG#177- Social Insurance | 1 | 1 | PKG#177- Social Insurance1 | 1919688.42
PKG#177- Social Insurance | 2 | 2 | PKG#177- Social Insurance2 | 8305203.5
PKG#177- Social Insurance | 3 | 3 | PKG#177- Social Insurance3 | 2456503.82
PKG#177- Social Insurance | 4 | 4 | PKG#177- Social Insurance4 | 8736398.9
PKG#177- Social Insurance | 5 | 5 | PKG#177- Social Insurance5 | 3475892.52
PKG#177- Social Insurance | 6 | 6 | PKG#177- Social Insurance6 | 274089.78
PKG#178 | 2 | 2 | PKG#1782 | 13230338.29
PKG#178 | 3 | 3 | PKG#1783 | 6675236.88
PKG#178 | 4 | 4 | PKG#1784 | 6081013.29
PKG#178 | 5 | 5 | PKG#1785 | 9125492.66
PKG#178 | 6 | 6 | PKG#1786 | 2730279.03
PKG#178 | 7 | 7 | PKG#1787 | 1644401.99
PKG#178 | 8 | 8 | PKG#1788 | 595920.45
PKG#178 | 9 | 9 | PKG#1789 | 289077.6
PKG#178 | 10 | 10 | PKG#17810 | 2235574.97
PKG#178 | 1 | 1 | PKG#1781 | 3747170.2
PKG#178- Social Insurance | 1 | 1 | PKG#178- Social Insurance1 | 1276787.15
PKG#178- Social Insurance | 2 | 2 | PKG#178- Social Insurance2 | 392599.98
PKG#178- Social Insurance | 3 | 3 | PKG#178- Social Insurance3 | 887343.85
PKG#205 | 2 | 2 | PKG#2052 | 1181605.96
PKG#205 | 3 | 3 | PKG#2053 | 1250466.11
PKG#205 | 1 | 1 | PKG#2051 | 1260000
PKG#205-Social Insurance | 1 | 1 | PKG#205-Social Insurance1 | 209129.12
PKG#220B | 2 | 2 | PKG#220B2 | 8261597.76
PKG#220B | 3 | 3 | PKG#220B3 | 5980500.04
PKG#220B | 4 | 4 | PKG#220B4 | 2300000
PKG#220B | 1 | 1 | PKG#220B1 | 7500000
PKG#45 | 46 | 46 | PKG#4546 | 1844931.02
PKG#58 | 22 | 22 | PKG#5822 | 327696.29
PKG#85 | 5 | 5 | PKG#855 | 1729285.15
PKG#85 | 6 | 6 | PKG#856 | 768766.59
PKG#85 | 7 | 7 | PKG#857 | 29830.3
PKG#85 | 8 | 8 | PKG#858 | 1391898.96
PO#11687 | 1 | 1 | PO#116871 | 1090584
PO#11687 | 2 | 2 | PO#116872 | 451528
PO#11687 | 3 | 3 | PO#116873 | 293788
PO#11687 | 5 | 5 | PO#116875 | 343200
Port Said Silos | 1 | 1 | Port Said Silos1 | 5248643
Port Said Silos | 2 | 2 | Port Said Silos2 | 1773106
Port Said Silos | 3 | 3 | Port Said Silos3 | 4623869
Port Said Silos | 4 | 4 | Port Said Silos4 | 2560435
Port Said Silos | 5 | 5 | Port Said Silos5 | 4009921
Port Said Silos | 6 | 6 | Port Said Silos6 | 6842722
Port Said Silos | 7 | 7 | Port Said Silos7 | 3061822
Port Said Silos | 8 | 8 | Port Said Silos8 | 17260533
Port Said Silos | 9 | 9 | Port Said Silos9 | 2370710
Port Said Silos | 10 | 10 | Port Said Silos10 | 6384571
Port Said Silos | 11 | 11 | Port Said Silos11 | 3852337
Port Said Silos | 12 | 12 | Port Said Silos12 | 1587432
Port Said Silos | 13 | 13 | Port Said Silos13 | 460093
Port Said Silos | 14 | 14 | Port Said Silos14 | 2136487
Port Said Silos | 15 | 15 | Port Said Silos15 | 7663669
Port Said Silos | 16 | 16 | Port Said Silos16 | 9649102
Port Said Silos | 17 | 17 | Port Said Silos17 | 5738977
Port Said Silos | 18 | 18 | Port Said Silos18 | 2991787
Port Said Silos | 19 | 19 | Port Said Silos19 | 12748959
Port Said Silos | 20 | 20 | Port Said Silos20 | 6593857
Port Said Silos | 21 | 21 | Port Said Silos21 | 11818794
Port Said Silos | 22 | 22 | Port Said Silos22 | 4826684
Port Said Silos | 23 | 23 | Port Said Silos23 | 2411082.19
Port Said Silos | 24 | 24 | Port Said Silos24 | 3306186
Port Said Silos | 25 | 25 | Port Said Silos25 | 3280048
Port Said Silos | 26 | 26 | Port Said Silos26 | 426108
Port Said Silos | 28 | 28 | Port Said Silos28 | 1239632
Port Said Silos | 29 | 29 | Port Said Silos29 | 337130
Port Said Silos | 30 | 30 | Port Said Silos30 | 100641
Port Said Silos | 31 | 31 | Port Said Silos31 | 727554
Port Said Silos | 32 | 32 | Port Said Silos32 | 2193035.35
Port Said Silos | 33 | 33 | Port Said Silos33 | 2711136
Port Said Silos - Foreigner Supply | 1 | 1 | Port Said Silos - Foreigner Supply1 | 5206992
Port Said Silos - Foreigner Supply | 2 | 2 | Port Said Silos - Foreigner Supply2 | 775509.45
Port Said Silos - Local Supply | 1 | 1 | Port Said Silos - Local Supply1 | 655657.61
Port Said Silos - Local Supply | 2 | 2 | Port Said Silos - Local Supply2 | 1162711.94
Port Said Silos - Local Supply | 3 | 3 | Port Said Silos - Local Supply3 | 2307930.88
Port Said Silos - Local Supply | 4 | 4 | Port Said Silos - Local Supply4 | 3416710
Port Said Silos - Local Supply | 5 | 5 | Port Said Silos - Local Supply5 | 2565984
Port Said Silos - Local Supply | 6 | 6 | Port Said Silos - Local Supply6 | 833240
Port Said Silos - Local Supply | 7 | 7 | Port Said Silos - Local Supply7 | 4345468
Port Said Silos - Local Supply | 8 | 8 | Port Said Silos - Local Supply8 | 1794648.84
Port Said Silos - Local Supply | 9 | 9 | Port Said Silos - Local Supply9 | 2529147
Port Said Silos - Local Supply | 10 | 10 | Port Said Silos - Local Supply10 | 494192
Port Said Silos - Local Supply | 11 | 11 | Port Said Silos - Local Supply11 | 833789.82
Port Said Silos | 1 | 1 | Port Said Silos1 | 26540249.4
Port Said Silos | 2 | 2 | Port Said Silos2 | 15000000
Port Said Silos | 1 | 1 | Port Said Silos1 | 6000000
Port Said Silos | 2 | 2 | Port Said Silos2 | 5000000
Port Said Silos | 3 | 3 | Port Said Silos3 | 10000000
Port Said Silos | 4 | 4 | Port Said Silos4 | 20000000
Port Said Silos | 5 | 5 | Port Said Silos5 | 10000000
Port Said Silos | 6 | 6 | Port Said Silos6 | 15000000
Port Said Silos-Social Insurrance | 1 | 1 | Port Said Silos-Social Insurrance1 | 2127569.59
Port Said Silos-Social Insurrance | 2 | 2 | Port Said Silos-Social Insurrance2 | 411364.07
Port Said Silos-Social Insurrance | 3 | 3 | Port Said Silos-Social Insurrance3 | 653360.08
Port Said Silos-Social Insurrance | 4 | 4 | Port Said Silos-Social Insurrance4 | 2773108
Port Said Silos-Social Insurrance | 5 | 5 | Port Said Silos-Social Insurrance5 | 344418
Port Said Silos-Social Insurrance | 6 | 6 | Port Said Silos-Social Insurrance6 | 1595672
Port Said Silos-Social Insurrance | 7 | 7 | Port Said Silos-Social Insurrance7 | 440773.7
Port Said Silos-Social Insurrance | 8 | 8 | Port Said Silos-Social Insurrance8 | 585270
Port Said Silos-Social Insurrance | 9 | 9 | Port Said Silos-Social Insurrance9 | 2996951.24
Port Said Silos-Social Insurrance | 10 | 10 | Port Said Silos-Social Insurrance10 | 999516
Port Said Silos-Social Insurrance | 11 | 11 | Port Said Silos-Social Insurrance11 | 1556882.52
PSP Substation | 2 | 2 | PSP Substation2 | 1160599
PSP Substation | 3 | 3 | PSP Substation3 | 1834172.07
PSP Substation | 4 | 4 | PSP Substation4 | 1268627.7
PSP Substation | 5 | 5 | PSP Substation5 | 3991290.99
PSP Substation | 6 | 6 | PSP Substation6 | 3047586.1
PSP Substation | 7 | 7 | PSP Substation7 | 1780094.35
PSP Substation | 8 | 8 | PSP Substation8 | 1829713.21
PSP Substation | 9 | 9 | PSP Substation9 | 1314287.28
PSP Substation | 10 | 10 | PSP Substation10 | 3264225.8
PSP Substation | 11 | 11 | PSP Substation11 | 2606365.14
PSP Substation | 12 | 12 | PSP Substation12 | 28515
PSP Substation - Beni Suef | 29 | 29 | PSP Substation - Beni Suef29 | 4326586.5
PSP Substation | 1 | 1 | PSP Substation1 | 6647052.2
PSP Substation-Retention | 1 | 1 | PSP Substation-Retention1 | 597560.88
PSP Substation-Retention | 2 | 2 | PSP Substation-Retention2 | 480264.83
PSP Substation-Retention | 3 | 3 | PSP Substation-Retention3 | 536537.44
PSP Substation-Retention | 4 | 4 | PSP Substation-Retention4 | 1617088.7
Rabigh Ext. - Piles | 1 | 1 | Rabigh Ext. - Piles1 | 947881.6
Rabigh Ext. - Piles | 2 | 2 | Rabigh Ext. - Piles2 | 1174037
Rabigh Ext. - Piles | 3 | 3 | Rabigh Ext. - Piles3 | 966227
Rabigh Ext. - Piles | 4 | 4 | Rabigh Ext. - Piles4 | 1787056
Rabigh Ext. - Piles | 5 | 5 | Rabigh Ext. - Piles5 | 1130623
Rabigh Ext. - Piles | 6 | 6 | Rabigh Ext. - Piles6 | 2013847.54
Rabigh Ext. - Piles- DP | 1 | 1 | Rabigh Ext. - Piles- DP1 | 195500
Rabigh Ext. - Piles- DP | 2 | 2 | Rabigh Ext. - Piles- DP2 | 5181540
Rabigh Ext. -Building | 1 | 1 | Rabigh Ext. -Building1 | 2660254.84
Rabigh Ext. -Building | 2 | 2 | Rabigh Ext. -Building2 | 4708047.77
Rabigh Ext. -Building- DP | 1 | 1 | Rabigh Ext. -Building- DP1 | 10000000
Rabigh Ext. -Building- DP | 2 | 2 | Rabigh Ext. -Building- DP2 | 5000000
Rabigh Ext. -Building- DP | 3 | 3 | Rabigh Ext. -Building- DP3 | 49209592.04
Radamis-Concrete | 1 | 1 | Radamis-Concrete1 | 10000000
Radamis-Concrete | 2 | 2 | Radamis-Concrete2 | 10000000
Radamis-H1 | 1 | 1 | Radamis-H11 | 5000000
Radamis-H1 | 2 | 2 | Radamis-H12 | 3000000
Radamis-H1 | 3 | 3 | Radamis-H13 | 5000000
Radamis-H1 | 4 | 4 | Radamis-H14 | 3000000
Radamis-H1 | 5 | 5 | Radamis-H15 | 10000000
Radamis-H1 | 6 | 6 | Radamis-H16 | 10000000
Radamis-H1 | 7 | 7 | Radamis-H17 | 5000000
Radamis-H1 | 8 | 8 | Radamis-H18 | 10000000
Radamis-H1 | 9 | 9 | Radamis-H19 | 10000000
Radamis-H1 | 10 | 10 | Radamis-H110 | 10000000
Radamis-H1 | 11 | 11 | Radamis-H111 | 15000000
Radamis-H1 | 13 | 13 | Radamis-H113 | 10000000
Radamis-H1 | 15 | 15 | Radamis-H115 | 10000000
Radamis-H1 | 16 | 16 | Radamis-H116 | 15000000
Radamis-H1 | 17 | 17 | Radamis-H117 | 18000000
Radamis-H1 | 18 | 18 | Radamis-H118 | 10000000
Radamis-H1 | 19 | 19 | Radamis-H119 | 16000000
Radamis-H1 | 20 | 20 | Radamis-H120 | 10000000
Radamis-H1 | 21 | 21 | Radamis-H121 | 10000000
Radamis-H1 | 22 | 22 | Radamis-H122 | 10000000
Radamis-H1 | 23 | 23 | Radamis-H123 | 10000000
Radamis-H1 | 24 | 24 | Radamis-H124 | 10000000
Radamis-H1 | 25 | 25 | Radamis-H125 | 10000000
Radamis-H1 | 26 | 26 | Radamis-H126 | 10000000
Radamis-H1 | 27 | 27 | Radamis-H127 | 10000000
Radamis-H1 | 28 | 28 | Radamis-H128 | 10000000
Radamis-H1 | 29 | 29 | Radamis-H129 | 10000000
Radamis-H1 | 30 | 30 | Radamis-H130 | 10000000
Radamis-H1 | 31 | 31 | Radamis-H131 | 20000000
Radamis-H1 | 32 | 32 | Radamis-H132 | 30000000
Radamis-H1 | 33 | 33 | Radamis-H133 | 30000000
Radamis-H1 | 34 | 34 | Radamis-H134 | 10000000
Radamis-H1 | 35 | 35 | Radamis-H135 | 20000000
Radamis-H1 | 36 | 36 | Radamis-H136 | 25000000
Radamis-H1 | 37 | 37 | Radamis-H137 | 20000000
Radamis-H1 | 38 | 38 | Radamis-H138 | 10000000
Radamis-H1 | 39 | 39 | Radamis-H139 | 20000000
Radamis-H1 | 40 | 40 | Radamis-H140 | 20000000
Radamis-Rooms Fitout | 1 | 1 | Radamis-Rooms Fitout1 | 250000
Radamis-Rooms Fitout | 2 | 2 | Radamis-Rooms Fitout2 | 500000
Radamis-Rooms Fitout | 3 | 3 | Radamis-Rooms Fitout3 | 15000000
Radamis-Rooms Fitout | 4 | 4 | Radamis-Rooms Fitout4 | 4000000
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 2918717
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 2114752.93
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 2300000
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 2300000
Red Sea Museum | 3 | 3 | Red Sea Museum3 | 4443406
Ring Road - El Marg | 1 | 1 | Ring Road - El Marg1 | 45719198.4
Ring Road - El Marg | 2 | 2 | Ring Road - El Marg2 | 9576635.3
Ring Road - El Marg | 3 | 3 | Ring Road - El Marg3 | 13773926.1
Ring Road - El Marg | 4 | 4 | Ring Road - El Marg4 | 4525661.3
Ring Road - El Marg | 5 | 5 | Ring Road - El Marg5 | 2097964.3
Ring Road - El Marg | 6 | 6 | Ring Road - El Marg6 | 1156719
Ring Road - El Marg | 7 | 7 | Ring Road - El Marg7 | 2151897.3
Ring Road - El Marg | 8 | 8 | Ring Road - El Marg8 | 3742254.85
Ring Road - El Marg | 9 | 9 | Ring Road - El Marg9 | 4020500.85
Ring Road - El Marg | 10 | 10 | Ring Road - El Marg10 | 2795847.4
Ring Road - El Marg | 11 | 11 | Ring Road - El Marg11 | 0.0001
Ring Road - El Marg | 12 | 12 | Ring Road - El Marg12 | 0.0001
Ring Road - El Marg | 13 | 13 | Ring Road - El Marg13 | 0.0001
Ring Road - El Marg - Retention Release | 1 | 1 | Ring Road - El Marg - Retention Release1 | 1436312.4
Ring Road - Mounib | 1 | 1 | Ring Road - Mounib1 | 26333646.7391
Ring Road - Mounib | 2 | 2 | Ring Road - Mounib2 | 7157243.6
Ring Road - Mounib | 3 | 3 | Ring Road - Mounib3 | 10759736.15
Ring Road - Mounib | 4 | 4 | Ring Road - Mounib4 | 4521989.75
Ring Road - Mounib | 5 | 5 | Ring Road - Mounib5 | 6026340.35
Ring Road - Mounib | 6 | 6 | Ring Road - Mounib6 | 4751540.0144
Ring Road - Mounib | 7 | 7 | Ring Road - Mounib7 | 3640291.7356
Ring Road - Mounib | 8 | 8 | Ring Road - Mounib8 | 2701161.75
Ring Road - Mounib | 9 | 9 | Ring Road - Mounib9 | 3856121.55
Ring Road - Mounib | 10 | 10 | Ring Road - Mounib10 | 10942755.35
Ring Road - Mounib | 11 | 11 | Ring Road - Mounib11 | 2713820.35
Ring Road - Mounib | 11.1 | 11 | Ring Road - Mounib11 | 994575.65
Ring Road - Mounib | 12 | 12 | Ring Road - Mounib12 | 14886673.24
Ring Road - Mounib | 13 | 13 | Ring Road - Mounib13 | 4632929.96
Ring Road - Mounib | 13.1 | 13 | Ring Road - Mounib13 | 21269971.05
Ring Road - Mounib | 13.2 | 13 | Ring Road - Mounib13 | 6375786
Ring Road - Mounib | 13.3 | 13 | Ring Road - Mounib13 | 719946.2
Ring Road - Mounib | 14 | 14 | Ring Road - Mounib14 | 5086863.5
Ring Road - Mounib | 14.1 | 14 | Ring Road - Mounib14 | 9870444.4
Ring Road - Mounib | 15 | 15 | Ring Road - Mounib15 | 10573632.35
Ring Road - Mounib | 15.1 | 15 | Ring Road - Mounib15 | 376461.75
Ring Road - Mounib | 16 | 16 | Ring Road - Mounib16 | 96448162.4
Ring Road - Mounib | 16.1 | 16 | Ring Road - Mounib16 | 35042549.45
Ring Road - Mounib | 17 | 17 | Ring Road - Mounib17 | 1170803.2
Ring Road - Mounib | 18 | 18 | Ring Road - Mounib18 | 2897048.5
Ring Road - Mounib | 19 | 19 | Ring Road - Mounib19 | 1351162.1
Ring Road - Mounib - refund | 1 | 1 | Ring Road - Mounib - refund1 | 11410289.1
Ring Road - Mounib - Social Insurance | 1 | 1 | Ring Road - Mounib - Social Insurance1 | 337945.75
RO Apply -Mech- SSC | 1 | 1 | RO Apply -Mech- SSC1 | 1730229.07
RO Apply -Mech- SSC | 2 | 2 | RO Apply -Mech- SSC2 | 1e-05
RO Apply -Mech- SSC | 4 | 4 | RO Apply -Mech- SSC4 | 0.001
RO - Supply - Electric | 1 | 1 | RO - Supply - Electric1 | 1e-05
RO - Supply - Electric | 2 | 2 | RO - Supply - Electric2 | 1e-05
RO - Supply - Electric | 3 | 3 | RO - Supply - Electric3 | 2225665.9095
RO Supply -Mech- SSC | 1 | 1 | RO Supply -Mech- SSC1 | 13698304.23
RO Supply -Mech- SSC | 2 | 2 | RO Supply -Mech- SSC2 | 1574191.94
RO Supply -Mech- SSC | 3 | 3 | RO Supply -Mech- SSC3 | 8116147.9035
RO Supply -Mech- SSC | 4 | 4 | RO Supply -Mech- SSC4 | 6312150
RO Supply -Mech- SSC | 5 | 5 | RO Supply -Mech- SSC5 | 2149698.33
RO Pump room - SSC - price diff. | 1 | 1 | RO Pump room - SSC - price diff.1 | 15849915.53
RO Pump room - SSC - price diff. | 2 | 2 | RO Pump room - SSC - price diff.2 | 918959
RO Pump room - SSC - price diff. | 3 | 3 | RO Pump room - SSC - price diff.3 | 9400325.92
RO Pump room - SSC - price diff. | 4 | 4 | RO Pump room - SSC - price diff.4 | 7294244.17
RO.2 | 1 | 1 | RO.21 | 1e-05
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 10000000
Rolling Mill #4-TRAESUEZ | 1.1 | 1 | Rolling Mill #4-TRAESUEZ1 | 6966551.51
Rolling Mill #4-TRAESUEZ | 2 | 2 | Rolling Mill #4-TRAESUEZ2 | 12106800.04
Rolling Mill #4-TRAESUEZ | 3 | 3 | Rolling Mill #4-TRAESUEZ3 | 10231445.3
Rolling Mill #4-TRAESUEZ | 4 | 4 | Rolling Mill #4-TRAESUEZ4 | 6596541.38
Rolling Mill #4-TRAESUEZ | 5 | 5 | Rolling Mill #4-TRAESUEZ5 | 9293714.72
Rolling Mill #4-TRAESUEZ | 6 | 6 | Rolling Mill #4-TRAESUEZ6 | 4622509.21
Rolling Mill #4-TRAESUEZ | 7 | 7 | Rolling Mill #4-TRAESUEZ7 | 13289718.96
Rolling Mill #4-TRAESUEZ | 8 | 8 | Rolling Mill #4-TRAESUEZ8 | 16970562.32
Rolling Mill #4-TRAESUEZ | 9 | 9 | Rolling Mill #4-TRAESUEZ9 | 15728855.47
Rolling Mill #4-TRAESUEZ | 10 | 10 | Rolling Mill #4-TRAESUEZ10 | 10380808.5
Rolling Mill #4-TRAESUEZ | 11 | 11 | Rolling Mill #4-TRAESUEZ11 | 9072857.69
Rolling Mill #4-TRAESUEZ | 12 | 12 | Rolling Mill #4-TRAESUEZ12 | 13213191.25
Rolling Mill #4-TRAESUEZ | 13 | 13 | Rolling Mill #4-TRAESUEZ13 | 1e-05
Rolling Mill #4-TRAESUEZ | 14 | 14 | Rolling Mill #4-TRAESUEZ14 | 1e-05
Rolling Mill #4-TRAESUEZ | 15 | 15 | Rolling Mill #4-TRAESUEZ15 | 1e-05
Rolling Mill #4-TRAESUEZ | 16 | 16 | Rolling Mill #4-TRAESUEZ16 | 1e-05
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 108750000
Royal City | 2 | 2 | Royal City2 | 4892835.45
Royal City | 3 | 3 | Royal City3 | 7926742.1
Royal City | 4 | 4 | Royal City4 | 10437271.65
Royal City | 5 | 5 | Royal City5 | 5169557.65
Royal City | 6 | 6 | Royal City6 | 12495801.4
Royal City | 7 | 7 | Royal City7 | 8703262.4
Royal City | 8 | 8 | Royal City8 | 6085844.5
Royal City | 9 | 9 | Royal City9 | 6397146.2
Royal City | 10 | 10 | Royal City10 | 5786688.5
Royal City | 11 | 11 | Royal City11 | 3482306.95
Royal City | 12 | 12 | Royal City12 | 9822648.05
Royal City | 13 | 13 | Royal City13 | 6339338.45
Royal City | 14 | 14 | Royal City14 | 5980045.3
Royal City | 15 | 15 | Royal City15 | 6570751.8
Royal City | 16 | 16 | Royal City16 | 7847127.4
Royal City | 17 | 17 | Royal City17 | 5868379.55
Royal City | 18 | 18 | Royal City18 | 4501953.5
Royal City | 19 | 19 | Royal City19 | 9999974.75
Royal City | 20 | 20 | Royal City20 | 5072118
Royal City | 21 | 21 | Royal City21 | 5000000
Royal City | 22 | 22 | Royal City22 | 16824453.7
Royal City | 23 | 23 | Royal City23 | 6453450.6
Royal City | 24 | 24 | Royal City24 | 9088642.9
Royal City | 25 | 25 | Royal City25 | 9972683.95
Royal City | 26 | 26 | Royal City26 | 8025338.3
Royal City | 27 | 27 | Royal City27 | 5000000
Royal City | 27.1 | 27 | Royal City27 | 5150000
Royal City | 27.2 | 27 | Royal City27 | 1745943.7
Royal City | 28 | 28 | Royal City28 | 7000000
Royal City | 28.1 | 28 | Royal City28 | 3500306.77
Royal City | 29 | 29 | Royal City29 | 12838209.35
Royal City | 30 | 30 | Royal City30 | 7400000
Royal City | 30.1 | 30 | Royal City30 | 2431952.135
Royal City | 31 | 31 | Royal City31 | 2500000
Royal City | 31.1 | 31 | Royal City31 | 3975508.58
Royal City | 32 | 32 | Royal City32 | 2151533.38
Royal City | 33 | 33 | Royal City33 | 5000000
Royal City | 33.1 | 33 | Royal City33 | 4101413.8171
Royal City | 34 | 34 | Royal City34 | 1294144.2829
Royal City | 34.1 | 34 | Royal City34 | 4079298.6432
Royal City | 35 | 35 | Royal City35 | 3237336.5863
Royal City | 36 | 36 | Royal City36 | 1578133.6205
Royal City | 36.1 | 36 | Royal City36 | 3653291.5695
Royal City | 37 | 37 | Royal City37 | 3663343.67
Royal City | 38 | 38 | Royal City38 | 2267127.88
Royal City | 39 | 39 | Royal City39 | 1002773.1926
Royal City | 40 | 40 | Royal City40 | 955713.1379
Royal City | 40.1 | 40 | Royal City40 | 5023973.5321
Royal City | 41 | 41 | Royal City41 | 5714023.3138
Royal City | 42 | 42 | Royal City42 | 15000000
Royal City | 42.1 | 42 | Royal City42 | 4161782.8
Royal City | 42.2 | 42 | Royal City42 | 16000000
Royal City - Landscape | 1 | 1 | Royal City - Landscape1 | 1782000
Royal City - Landscape | 2 | 2 | Royal City - Landscape2 | 4014037.5
Royal City - Landscape | 3 | 3 | Royal City - Landscape3 | 2421804.9
Royal City - Landscape | 4 | 4 | Royal City - Landscape4 | 4390934.75
Royal City - Landscape | 5 | 5 | Royal City - Landscape5 | 7060326.8
Royal City - Landscape | 6 | 6 | Royal City - Landscape6 | 9240902.25
Royal City - Landscape | 7 | 7 | Royal City - Landscape7 | 5000000
Royal City - Landscape | 7.1 | 7 | Royal City - Landscape7 | 1442723.35
Royal City - Landscape | 8 | 8 | Royal City - Landscape8 | 2161790.65
Royal City - Landscape | 8.1 | 8 | Royal City - Landscape8 | 10194453.1
Royal City - Landscape | 9 | 9 | Royal City - Landscape9 | 4886117.91
Royal City - Landscape | 10 | 10 | Royal City - Landscape10 | 2500000
Royal City - Landscape | 10.1 | 10 | Royal City - Landscape10 | 561010.97
Royal City - Landscape | 11 | 11 | Royal City - Landscape11 | 4947910.42
Royal City - Landscape | 12 | 12 | Royal City - Landscape12 | 5000000
Royal City - Landscape | 12.1 | 12 | Royal City - Landscape12 | 2029456.4155
Royal City - Landscape | 13 | 13 | Royal City - Landscape13 | 2173267.6157
Royal City - Landscape | 14 | 14 | Royal City - Landscape14 | 1308214.7555
Royal City - Landscape | 15 | 15 | Royal City - Landscape15 | 2272705.37
Royal City - Landscape | 16 | 16 | Royal City - Landscape16 | 650222.9433
Royal City - Landscape | 17 | 17 | Royal City - Landscape17 | 1288827.45
Royal City - Landscape | 17.1 | 17 | Royal City - Landscape17 | 1531216.7805
Royal City - Landscape | 18 | 18 | Royal City - Landscape18 | 819297.0816
Royal City - Landscape | 19 | 19 | Royal City - Landscape19 | 1116339.8935
Royal City - Landscape | 20 | 20 | Royal City - Landscape20 | 1105876.6944
Royal City - Landscape | 21 | 21 | Royal City - Landscape21 | 520336.7179
Royal City - Landscape | 21.1 | 21 | Royal City - Landscape21 | 2285976.6862
Royal City - Landscape | 22 | 22 | Royal City - Landscape22 | 1838217.2
Royal City - Landscape | 23 | 23 | Royal City - Landscape23 | 9000000
Royal City - Landscape | 23.1 | 23 | Royal City - Landscape23 | 4000000
Royal City 3 | 3 | 3 | Royal City 33 | 20000000
Royal City 4 | 4 | 4 | Royal City 44 | 20093247.4
Royal City1 | 1 | 1 | Royal City11 | 58500000
Royal City2 | 2 | 2 | Royal City22 | 20000000
Saint Gobain Factory | 1 | 1 | Saint Gobain Factory1 | 103530970.24
Saint Gobain Factory | 2 | 2 | Saint Gobain Factory2 | 26538435
SIEMENS - Sokhna | 1 | 1 | SIEMENS - Sokhna1 | 93300000
SIEMENS - Sokhna | 2 | 2 | SIEMENS - Sokhna2 | 3059283.73
SIEMENS - Sokhna | 3 | 3 | SIEMENS - Sokhna3 | 7201577.05
SIEMENS - Sokhna | 4 | 4 | SIEMENS - Sokhna4 | 11065687.7
SIEMENS - Sokhna | 5 | 5 | SIEMENS - Sokhna5 | 13218163.56
SIEMENS - Sokhna | 6 | 6 | SIEMENS - Sokhna6 | 7060448.908
SIEMENS - Sokhna | 7 | 7 | SIEMENS - Sokhna7 | 8833159.82
SIEMENS - Sokhna | 8 | 8 | SIEMENS - Sokhna8 | 12641621.4
SIEMENS - Sokhna | 9 | 9 | SIEMENS - Sokhna9 | 13673026.82
SIEMENS - Sokhna | 10 | 10 | SIEMENS - Sokhna10 | 6271528.33
SIEMENS - Sokhna | 11 | 11 | SIEMENS - Sokhna11 | 5230123.67
SIEMENS - Sokhna | 12 | 12 | SIEMENS - Sokhna12 | 20041232.56
SIEMENS - Sokhna | 13 | 13 | SIEMENS - Sokhna13 | 17822796.65
SIEMENS - Sokhna | 14 | 14 | SIEMENS - Sokhna14 | 20002003.08
SIEMENS - Sokhna | 15 | 15 | SIEMENS - Sokhna15 | 2699428.63
SIEMENS - Sokhna | 16 | 16 | SIEMENS - Sokhna16 | 25271545.73
SIEMENS - Sokhna | 17 | 17 | SIEMENS - Sokhna17 | 20418831.59
SIEMENS - Sokhna | 18 | 18 | SIEMENS - Sokhna18 | 12124718
SIEMENS - Sokhna | 19 | 19 | SIEMENS - Sokhna19 | 25672200.91
SIEMENS - Sokhna | 20 | 20 | SIEMENS - Sokhna20 | 15319191.73
SIEMENS - Sokhna | 21 | 21 | SIEMENS - Sokhna21 | 888628.7
SIEMENS - Sokhna - Bill | 1 | 1 | SIEMENS - Sokhna - Bill1 | 144907
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 2207548.2
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 1e-05
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 | 1e-05
SMP1 - Revamp | 4 | 4 | SMP1 - Revamp4 | 2647384.8437
SMP1 - Revamp | 5 | 5 | SMP1 - Revamp5 | 2853769.6857
SMP1 - Revamp | 6 | 6 | SMP1 - Revamp6 | 6112062.5631
SMP1 - Revamp | 7 | 7 | SMP1 - Revamp7 | 3154540.1
SMP1 - Revamp | 8 | 8 | SMP1 - Revamp8 | 1992085.4366
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 11698500
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 25693427.5
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 | 16806572.5
SMP1 - Shut Down | 1 | 1 | SMP1 - Shut Down1 | 5388381.94
SMP1 - Shut Down | 2 | 2 | SMP1 - Shut Down2 | 15140879.8914
SMP1 - Shut Down | 3 | 3 | SMP1 - Shut Down3 | 8648912.9484
SMP1 - Shut Down- Final Retention | 1 | 1 | SMP1 - Shut Down- Final Retention1 | 2700753.58
SMP2 - Shut Down | 2 | 2 | SMP2 - Shut Down2 | 5426194.9513
SMP2 - Shut Down | 3 | 3 | SMP2 - Shut Down3 | 581185.34
SMP2 - Shut Down- Retention release | 1 | 1 | SMP2 - Shut Down- Retention release1 | 553693.36
SMP2 - Shut Down- V.O | 1 | 1 | SMP2 - Shut Down- V.O1 | 20000000
Sodic Club House | 23 | 23 | Sodic Club House23 | 2727407.25
Sodic Club House | 24 | 24 | Sodic Club House24 | 4528572.66
Sodic Club House | 25 | 25 | Sodic Club House25 | 894280.83
Sodic Club House | 26 | 26 | Sodic Club House26 | 2563543.65
Sodic Club House | 27 | 27 | Sodic Club House27 | 7171420.81
Sodic Club House | 28 | 28 | Sodic Club House28 | 3643251.2
Sodic Club House | 29 | 29 | Sodic Club House29 | 2927170
Sodic Club House | 30 | 30 | Sodic Club House30 | 1523667.33
Sodic Club House | 31 | 31 | Sodic Club House31 | 3752933.22
Sodic Club House | 32 | 32 | Sodic Club House32 | 1851323.25
Sodic Club House | 33 | 33 | Sodic Club House33 | 5028067.13
Sodic Club House | 34 | 34 | Sodic Club House34 | 1372787.19
Sodic Club House | 35 | 35 | Sodic Club House35 | 2061960.96
Sodic Club House | 36 | 36 | Sodic Club House36 | 3000000
Sodic Club House | 36.1 | 36 | Sodic Club House36 | 6516540.66
Sodic Club House | 37 | 37 | Sodic Club House37 | 4028521
Sodic Club House - Social Insurance | 1 | 1 | Sodic Club House - Social Insurance1 | 184729.32
Sodic Club House - Social Insurance | 2 | 2 | Sodic Club House - Social Insurance2 | 503082.9
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 6789620.12
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 15638373.66
Sodic Eastown | 3 | 3 | Sodic Eastown3 | 1574016.18
Sodic Eastown | 4 | 4 | Sodic Eastown4 | 25688338.61
Sodic Eastown | 5 | 5 | Sodic Eastown5 | 37056568.4
Sodic Eastown | 6 | 6 | Sodic Eastown6 | 18000000
Sodic Eastown | 6.1 | 6 | Sodic Eastown6 | 10554847.67
Sodic Eastown | 7 | 7 | Sodic Eastown7 | 35000000
Sodic Eastown | 7.1 | 7 | Sodic Eastown7 | 3197130.95
Sodic Eastown | 8 | 8 | Sodic Eastown8 | 46000000
Sodic Eastown | 8.1 | 8 | Sodic Eastown8 | 9532397.61
Sodic Eastown | 9 | 9 | Sodic Eastown9 | 40504812.26
Sodic Eastown | 10 | 10 | Sodic Eastown10 | 32553581.24
Sodic Eastown | 11 | 11 | Sodic Eastown11 | 27179529.3929
Sodic Eastown | 12 | 12 | Sodic Eastown12 | 19553108.79
Sodic Eastown | 13 | 13 | Sodic Eastown13 | 10000000
Sodic Eastown | 13.1 | 13 | Sodic Eastown13 | 6201534.04
Sodic Eastown | 14 | 14 | Sodic Eastown14 | 15000000
Sodic Eastown | 14.1 | 14 | Sodic Eastown14 | 1537461.58
Sodic Eastown | 15 | 15 | Sodic Eastown15 | 12895954
Sodic Eastown | 16 | 16 | Sodic Eastown16 | 30145771.57
Sodic Eastown | 17 | 17 | Sodic Eastown17 | 20000000
Sodic Eastown | 17.1 | 17 | Sodic Eastown17 | 899381.34
Sodic Eastown | 18 | 18 | Sodic Eastown18 | 15000000
Sodic Eastown | 18.1 | 18 | Sodic Eastown18 | 7406610.78
Sodic Eastown | 19 | 19 | Sodic Eastown19 | 25500000
Sodic Eastown | 19.1 | 19 | Sodic Eastown19 | 8917592.72
Sodic Eastown | 20 | 20 | Sodic Eastown20 | 27000000
Sodic Eastown | 20.1 | 20 | Sodic Eastown20 | 4197031.83
Sodic Eastown | 21 | 21 | Sodic Eastown21 | 25000000
Sodic Eastown | 21.1 | 21 | Sodic Eastown21 | 4743783.32
Sodic Eastown | 22 | 22 | Sodic Eastown22 | 15000000
Sodic Eastown | 22.1 | 22 | Sodic Eastown22 | 4964135.7
Sodic Eastown | 23 | 23 | Sodic Eastown23 | 12000000
Sodic Eastown | 23.1 | 23 | Sodic Eastown23 | 7672746.63
Sodic Eastown | 24 | 24 | Sodic Eastown24 | 12000000
Sodic Eastown | 24.1 | 24 | Sodic Eastown24 | 2713744.17
Sodic Eastown | 25 | 25 | Sodic Eastown25 | 15000000
Sodic Eastown | 25.1 | 25 | Sodic Eastown25 | 3632387.16
Sodic Eastown | 26 | 26 | Sodic Eastown26 | 19000000
Sodic Eastown | 26.1 | 26 | Sodic Eastown26 | 13407888.61
Sodic Eastown | 27 | 27 | Sodic Eastown27 | 19000000
Sodic Eastown | 27.1 | 27 | Sodic Eastown27 | 2101612.82
Sodic Eastown | 28 | 28 | Sodic Eastown28 | 30000000
Sodic Eastown | 28.1 | 28 | Sodic Eastown28 | 11708616.23
Sodic Eastown | 29 | 29 | Sodic Eastown29 | 10880905.48
Sodic Eastown | 30 | 30 | Sodic Eastown30 | 20000000
Sodic Eastown | 30.1 | 30 | Sodic Eastown30 | 5479297.36
Sodic Eastown | 31 | 31 | Sodic Eastown31 | 22493923.41
Sodic Eastown | 32 | 32 | Sodic Eastown32 | 15680621.74
Sodic Eastown | 33 | 33 | Sodic Eastown33 | 19311419.98
Sodic Eastown | 34 | 34 | Sodic Eastown34 | 4602037.61
Sodic Eastown | 35 | 35 | Sodic Eastown35 | 12555804.9
Sodic Eastown | 36 | 36 | Sodic Eastown36 | 2350120
Sodic Eastown | 36.1 | 36 | Sodic Eastown36 | 3904269.49
Sodic Eastown | 37 | 37 | Sodic Eastown37 | 5035428.4
Sodic Eastown | 38 | 38 | Sodic Eastown38 | 2231188
Sodic Eastown | 39 | 39 | Sodic Eastown39 | 17894573
Sodic Eastown - Landscape | 1 | 1 | Sodic Eastown - Landscape1 | 1545976.54
Sodic Eastown - Landscape | 2 | 2 | Sodic Eastown - Landscape2 | 2689319.17
Sodic Eastown - Landscape | 3 | 3 | Sodic Eastown - Landscape3 | 5060960.68
Sodic Eastown - Landscape | 4 | 4 | Sodic Eastown - Landscape4 | 4237695.68
Sodic Eastown - Landscape | 5 | 5 | Sodic Eastown - Landscape5 | 2847434.11
Sodic Eastown - Landscape | 6 | 6 | Sodic Eastown - Landscape6 | 1865468.85
Sodic Eastown - Landscape | 7 | 7 | Sodic Eastown - Landscape7 | 2249247.81
Sodic Eastown - Landscape | 8 | 8 | Sodic Eastown - Landscape8 | 8937999.74
Sodic Eastown - Landscape | 9 | 9 | Sodic Eastown - Landscape9 | 837296.03
Sodic Eastown - Landscape | 10 | 10 | Sodic Eastown - Landscape10 | 2965081
Sodic Eastown - Landscape | 11 | 11 | Sodic Eastown - Landscape11 | 970278.45
Sodic Eastown - Landscape | 12 | 12 | Sodic Eastown - Landscape12 | 2038310.81
Sodic Eastown - Landscape | 13 | 13 | Sodic Eastown - Landscape13 | 4532604.51
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 10000000
Sodic Eastown - Social Insurance | 1 | 1 | Sodic Eastown - Social Insurance1 | 849097.69
Sodic Eastown - Social Insurance | 2 | 2 | Sodic Eastown - Social Insurance2 | 59565.32
Sodic Eastown - Social Insurance | 3 | 3 | Sodic Eastown - Social Insurance3 | 3554660.12
Sodic Eastown - Social Insurance | 4 | 4 | Sodic Eastown - Social Insurance4 | 1311245.56
Sodic Eastown - Social Insurance | 5 | 5 | Sodic Eastown - Social Insurance5 | 2324833
Sodic Eastown - Social Insurance | 6 | 6 | Sodic Eastown - Social Insurance6 | 2884335.94
Sodic Eastown - Social Insurance | 7 | 7 | Sodic Eastown - Social Insurance7 | 1801458.51
Sodic Eastown - Social Insurance | 8 | 8 | Sodic Eastown - Social Insurance8 | 1322438.36
Sodic Eastown - Social Insurance | 9 | 9 | Sodic Eastown - Social Insurance9 | 1754521.36
Sodic Eastown - Social Insurance | 10 | 10 | Sodic Eastown - Social Insurance10 | 862557.37
Sodic Eastown - Social Insurance | 11 | 11 | Sodic Eastown - Social Insurance11 | 2423402.76
Sodic Eastown - Social Insurance | 12 | 12 | Sodic Eastown - Social Insurance12 | 2569099.92
Sodic Eastown - Social Insurance | 13 | 13 | Sodic Eastown - Social Insurance13 | 1513109.68
Sodic Eastown - Social Insurance | 14 | 14 | Sodic Eastown - Social Insurance14 | 1540691.11
Sodic Eastown - Social Insurance | 15 | 15 | Sodic Eastown - Social Insurance15 | 2140215.06
Sodic Eastown - Social Insurance | 16 | 16 | Sodic Eastown - Social Insurance16 | 1796921.66
Sodic Eastown - Social Insurance | 17 | 17 | Sodic Eastown - Social Insurance17 | 1371899.5
Sodic Eastown - Social Insurance | 18 | 18 | Sodic Eastown - Social Insurance18 | 327894.39
Sodic Eastown - Social Insurance | 19 | 19 | Sodic Eastown - Social Insurance19 | 944267.32
Sodic Eastown - Social Insurance | 20 | 20 | Sodic Eastown - Social Insurance20 | 1149200.87
Sodic Eastown - Social Insurance | 21 | 21 | Sodic Eastown - Social Insurance21 | 6876328.15
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 122000000
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 5928168
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 16602157.8
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 19087604.3
Sokhna Port Expansion | 3 | 3 | Sokhna Port Expansion3 | 55802951.65
Sokhna Port Expansion | 4 | 4 | Sokhna Port Expansion4 | 16604871.85
Sokhna Port Expansion | 5 | 5 | Sokhna Port Expansion5 | 24339603.2
Sokhna Port Expansion | 5.1 | 5 | Sokhna Port Expansion5 | 19863057.3
Sokhna Port Expansion | 5.2 | 5 | Sokhna Port Expansion5 | 14812304.05
Sokhna Port Expansion | 6 | 6 | Sokhna Port Expansion6 | 4879591.2
Sokhna Port Expansion | 6.1 | 6 | Sokhna Port Expansion6 | 10735001.15
Sokhna Port Expansion | 6.2 | 6 | Sokhna Port Expansion6 | 10594441
Sokhna Port Expansion | 7 | 7 | Sokhna Port Expansion7 | 36803665.95
Sokhna Port Expansion | 8 | 8 | Sokhna Port Expansion8 | 36284090.45
Sokhna Port Expansion | 9 | 9 | Sokhna Port Expansion9 | 30030028.45
Sokhna Port Expansion | 10 | 10 | Sokhna Port Expansion10 | 27461819.5
Sokhna Port Expansion | 11 | 11 | Sokhna Port Expansion11 | 50769799.2
Sokhna Port Expansion | 12 | 12 | Sokhna Port Expansion12 | 70395885.55
Sokhna Port Expansion | 13 | 13 | Sokhna Port Expansion13 | 491489.95
Sokhna Port Expansion | 14 | 14 | Sokhna Port Expansion14 | 6704080.85
Sokhna Port Expansion | 15 | 15 | Sokhna Port Expansion15 | 4368115.65
Sokhna Port Expansion | 16 | 16 | Sokhna Port Expansion16 | 23966243.5
Sokhna Port Expansion | 17 | 17 | Sokhna Port Expansion17 | 14567572.19
Sokhna Port Expansion | 18 | 18 | Sokhna Port Expansion18 | 14135207.0055
Sokhna Port Expansion | 19 | 19 | Sokhna Port Expansion19 | 10049896.61
Sokhna Port Expansion | 20 | 20 | Sokhna Port Expansion20 | 13204353
Sokhna Port Expansion | 21 | 21 | Sokhna Port Expansion21 | 5788234
Sokhna Port Expansion | 22 | 22 | Sokhna Port Expansion22 | 2510900.431
Sokhna Port Expansion | 23 | 23 | Sokhna Port Expansion23 | 568614.519
Sokhna Port Expansion- 100m | 1 | 1 | Sokhna Port Expansion- 100m1 | 39700885.25
Sokhna Port Expansion- 100m | 2 | 2 | Sokhna Port Expansion- 100m2 | 10628517.75
Sokhna Port Expansion- 100m | 3 | 3 | Sokhna Port Expansion- 100m3 | 10464912.35
Sokhna Port Expansion- 100m | 4 | 4 | Sokhna Port Expansion- 100m4 | 8297916
Sokhna Port Expansion- 100m | 5 | 5 | Sokhna Port Expansion- 100m5 | 3240800
Sokhna Port Expansion- 100m | 6 | 6 | Sokhna Port Expansion- 100m6 | 20436714.5
Sokhna Port Expansion- 100m | 7 | 7 | Sokhna Port Expansion- 100m7 | 3976775.9
Sokhna Port Expansion 100m- Escalation | 1 | 1 | Sokhna Port Expansion 100m- Escalation1 | 11758235
Sokhna Port Expansion 100m- Escalation | 2 | 2 | Sokhna Port Expansion 100m- Escalation2 | 6484391
Sokhna Port Expansion- EDECS | 1 | 1 | Sokhna Port Expansion- EDECS1 | 478776
Sokhna Port Expansion- Escalation | 1 | 1 | Sokhna Port Expansion- Escalation1 | 20947176.65
Sokhna Port Expansion- Escalation | 2 | 2 | Sokhna Port Expansion- Escalation2 | 39132293.55
Sokhna Port Expansion- Escalation | 3 | 3 | Sokhna Port Expansion- Escalation3 | 103409321
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 185016019.2
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 33908706
Sokhna Port Expansion-internal roads | 1 | 1 | Sokhna Port Expansion-internal roads1 | 1800470.45
Sokhna Port Expansion-internal roads | 2 | 2 | Sokhna Port Expansion-internal roads2 | 3219.75
Sports Hall - Civil Works | 3 | 3 | Sports Hall - Civil Works3 | 2493330
Sports Hall - Civil Works | 4 | 4 | Sports Hall - Civil Works4 | 10576930
Sports Hall - Civil Works | 5 | 5 | Sports Hall - Civil Works5 | 17108045
Sports Hall - Civil Works | 6 | 6 | Sports Hall - Civil Works6 | 414025
Sports Hall - Finishes | 1 | 1 | Sports Hall - Finishes1 | 1388840
Sports Hall - Finishes | 2 | 2 | Sports Hall - Finishes2 | 13091760
Sports Hall - Finishes | 3 | 3 | Sports Hall - Finishes3 | 7109625
Sports Hall - Finishes | 4 | 4 | Sports Hall - Finishes4 | 3699060
Sports Hall - Finishes - ADD.01 | 1 | 1 | Sports Hall - Finishes - ADD.011 | 5941290
Sports Hall - Finishes - ADD.01 | 2 | 2 | Sports Hall - Finishes - ADD.012 | 2631750
Sports Hall - Finishes - ADD.01 - Final Retention | 1 | 1 | Sports Hall - Finishes - ADD.01 - Final Retention1 | 790505
Sports Hall - Finishes - Landscape | 1 | 1 | Sports Hall - Finishes - Landscape1 | 0.0003
Sports Hall - Finishes - Landscape - Final Retention | 1 | 1 | Sports Hall - Finishes - Landscape - Final Retention1 | 2595335
Sports Hall - Finishes - Social Insurance | 1 | 1 | Sports Hall - Finishes - Social Insurance1 | 12888786
Sports Hall - MEP | 1 | 1 | Sports Hall - MEP1 | 19417720
Sports Hall - MEP | 2 | 2 | Sports Hall - MEP2 | 1103175
Sports Hall - MEP | 1 | 1 | Sports Hall - MEP1 | 47999995
Sports Hall - MEP - Final Retention | 1 | 1 | Sports Hall - MEP - Final Retention1 | 2580450
Suez Intake & P Stations-ABB apply | 1 | 1 | Suez Intake & P Stations-ABB apply1 | 509186.43
Suez Intake & P Stations-ABB apply | 2 | 2 | Suez Intake & P Stations-ABB apply2 | 988420.71
Suez Intake & P Stations-ABB apply | 3 | 3 | Suez Intake & P Stations-ABB apply3 | 1048324.9964
Suez Intake & P Stations-ABB supply | 1 | 1 | Suez Intake & P Stations-ABB supply1 | 5134498.57
Suez Intake & P Stations-ABB supply | 2 | 2 | Suez Intake & P Stations-ABB supply2 | 7437727.82
Suez Intake & P Stations-ABB supply | 3 | 3 | Suez Intake & P Stations-ABB supply3 | 814872.95
Suez Intake & P Stations-ABB supply | 4 | 4 | Suez Intake & P Stations-ABB supply4 | 3667977.98
Suez Intake & P Stations-ABB supply | 8 | 8 | Suez Intake & P Stations-ABB supply8 | 1e-05
Suez Intake & P Stations-ABB-Escalation | 1 | 1 | Suez Intake & P Stations-ABB-Escalation1 | 35028257.79
Suez Intake & P Stations-ABB-Escalation | 2 | 2 | Suez Intake & P Stations-ABB-Escalation2 | 7725580.34
Suez Intake & P Stations-SSC apply | 1 | 1 | Suez Intake & P Stations-SSC apply1 | 1102291.62
Suez Intake & P Stations-SSC apply | 2 | 2 | Suez Intake & P Stations-SSC apply2 | 3020707.78
Suez Intake & P Stations-SSC apply | 3 | 3 | Suez Intake & P Stations-SSC apply3 | 772824.1924
Suez Intake & P Stations-SSC apply | 8 | 8 | Suez Intake & P Stations-SSC apply8 | 1886891.07
Suez Intake & P Stations-SSC supply | 1 | 1 | Suez Intake & P Stations-SSC supply1 | 8726326.42
Suez Intake & P Stations-SSC supply | 2 | 2 | Suez Intake & P Stations-SSC supply2 | 3190893.09
Suez Intake & P Stations-SSC supply | 3 | 3 | Suez Intake & P Stations-SSC supply3 | 283552.06
Suez Intake & P Stations-SSC supply | 4 | 4 | Suez Intake & P Stations-SSC supply4 | 1e-05
Suez Steel Intake & P Stations | 1 | 1 | Suez Steel Intake & P Stations1 | 19045714
Suez Steel Intake & P Stations | 2 | 2 | Suez Steel Intake & P Stations2 | 28804143
Suez Steel Intake & P Stations | 3 | 3 | Suez Steel Intake & P Stations3 | 25468559.95
Suez Steel-Al Baraka | 1 | 1 | Suez Steel-Al Baraka1 | 19326786
Suez Steel-Gas Station | 1 | 1 | Suez Steel-Gas Station1 | 5014142.1
SVC | 1 | 1 | SVC1 | 2216581.5616
SVC | 1 | 1 | SVC1 | 1158731.1
Uptown PK #53 | 25 | 25 | Uptown PK #5325 | 12009168.61
Uptown PK #53 | 26 | 26 | Uptown PK #5326 | 13124888.11
Uptown PK #53 | 27 | 27 | Uptown PK #5327 | 9593936.7945
Uptown PK #53 | 28 | 28 | Uptown PK #5328 | 13320601.43
Uptown PK #53 | 29 | 29 | Uptown PK #5329 | 10942287.56
Uptown PK #53 | 30 | 30 | Uptown PK #5330 | 11348802.26
Uptown PK #53 | 31 | 31 | Uptown PK #5331 | 7033824.83
Uptown PK #53 | 32 | 32 | Uptown PK #5332 | 2358051.13
Uptown PK #53 | 33 | 33 | Uptown PK #5333 | 2690853.59
Uptown PK #53 | 34 | 34 | Uptown PK #5334 | 1431626.0807
Uptown PK #53 | 35 | 35 | Uptown PK #5335 | 2466454.76
Uptown PK #53 | 36 | 36 | Uptown PK #5336 | 2490213.39
Uptown PK #53 | 37 | 37 | Uptown PK #5337 | 1746850.68
Uptown PK #53 | 38 | 38 | Uptown PK #5338 | 1902092.11
Uptown PK #53 | 39 | 39 | Uptown PK #5339 | 943725.79
Uptown PK #53 | 40 | 40 | Uptown PK #5340 | 1435222.17
Uptown PK #53 | 41 | 41 | Uptown PK #5341 | 4202366.45
Uptown PK #53 | 42 | 42 | Uptown PK #5342 | 1380970.95
Uptown PK #53 | 43 | 43 | Uptown PK #5343 | 4834138.97
Uptown PK #62 | 7 | 7 | Uptown PK #627 | 1684908.09
Uptown PK #62 | 8 | 8 | Uptown PK #628 | 2970870.89
Uptown PK #62 | 9 | 9 | Uptown PK #629 | 2124952.16
Uptown PK #62 | 10 | 10 | Uptown PK #6210 | 2207449.91
Uptown PK #62 | 11 | 11 | Uptown PK #6211 | 1524280.94
Uptown PK #62 | 12 | 12 | Uptown PK #6212 | 1565019.14
Uptown PK #62 | 13 | 13 | Uptown PK #6213 | 2219134.03
Uptown PK #62 | 14 | 14 | Uptown PK #6214 | 854854.29
Uptown PK #62 | 15 | 15 | Uptown PK #6215 | 2299870.99
Uptown PK #62 | 16 | 16 | Uptown PK #6216 | 931895.88
Uptown PK #62 | 17 | 17 | Uptown PK #6217 | 419078.79
Uptown PK #62 | 18 | 18 | Uptown PK #6218 | 864260.36
Uptown PK #62 | 19 | 19 | Uptown PK #6219 | 1416810.93
Uptown PK #62 - Retention | 17 | 17 | Uptown PK #62 - Retention17 | 148822.86
Uptown PK #62 - Retention | 18 | 18 | Uptown PK #62 - Retention18 | 504922.64
Wady Halfa | 1 | 1 | Wady Halfa1 | 22733360.9
Wady Halfa | 2 | 2 | Wady Halfa2 | 8196261.85
Wady Halfa | 3 | 3 | Wady Halfa3 | 2807166.9
Wady Halfa | 4 | 4 | Wady Halfa4 | 3015154.3
Wady Halfa | 5 | 5 | Wady Halfa5 | 2984537.1
Wady Halfa-DP | 1 | 1 | Wady Halfa-DP1 | 19000000
Wady Halfa-DP | 2 | 2 | Wady Halfa-DP2 | 11000000
Wady Halfa - Escalation Claim | 1 | 1 | Wady Halfa - Escalation Claim1 | 14076920.26
Wady Halfa - Escalation Claim | 2 | 2 | Wady Halfa - Escalation Claim2 | 10413528.42
Wady Halfa - Stoppage Period | 1 | 1 | Wady Halfa - Stoppage Period1 | 8364831
Western Fence | 1 | 1 | Western Fence1 | 418218.39
Western Fence-PO | 1 | 1 | Western Fence-PO1 | 5200000
Zayed Park | 1 | 1 | Zayed Park1 | 505797
Zayed Park | 2 | 2 | Zayed Park2 | 264423.21

## consultant-gross (hidden)
Project | Invoice No. | invoice round down | concact | Approval Date (By Consultant) | Monthly Amount Approved (By Consultant) | Cummulative amount Approved (By Consultant) | Approval Date (By Client)
PK #107 | 9 | 9 | PK #1079 | 43061 | 1856322.11 | 38038903.52 | 43067
JICA | 19 | 19 | JICA19 | 43038 | 1210863.76 | 117203462.77 | 43038
FIEM | 210 | 210 | FIEM210 | 43031 | 2236443.87 | 69808024.8 | 43031
Cement Plant | 15 | 15 | Cement Plant15 | 43054 | 8583366.193 | 228271708.9079 | 43054
PI Parks - ELSEWEDY | 1 | 1 | PI Parks - ELSEWEDY1 | 43038 | 3990886.7187 | 3990886.7187 | 43043
PI Parks - ELSEWEDY | 2 | 2 | PI Parks - ELSEWEDY2 | 43061 | 4642464.2724 | 7590402.3632 | 43067
Sodic Club House | 24 | 24 | Sodic Club House24 | 43065 | 7208751.86 | 64461008.2542 | 43086
Royal City | 2 | 2 | Royal City2 | 43019 | 5127541.59 | 9046023.16 | 43019
Royal City | 3 | 3 | Royal City3 | 43048 | 8536189.79 | 17411738.66 | 43053
Uptown PK #62 | 8 | 8 | Uptown PK #628 | 43047 | 4024169.64 | 22444166.23 | 43053
Uptown PK #53 | 26 | 26 | Uptown PK #5326 | 43088 | 18228071.6884 | 228353712.8741 | 43090
PK #107 | 10 | 10 | PK #10710 | 43093 | 2025124.41 | 40064027.93 | 43096
PI Parks - ELSEWEDY | 3 | 3 | PI Parks - ELSEWEDY3 | 43092 | 1837652.48 | 9383809.13 | 43094
Uptown PK #62 | 9 | 9 | Uptown PK #629 | 43087 | 3353637.028 | 25797803.258 | 43090
Sodic Club House | 25 | 25 | Sodic Club House25 | 43106 | 4060848.9478 | 65696424.8478 | 43124
SIEMENS - Sokhna | 2 | 2 | SIEMENS - Sokhna2 | 43116 | 4401847.1 | 4401847.1
PK #107 | 11 | 11 | PK #10711 | 43115 | 3591068.23 | 43655096.16
Uptown PK #62 | 10 | 10 | Uptown PK #6210 | 43118 | 3315629.905 | 29113433.163
Uptown PK #53 | 27 | 27 | Uptown PK #5327 | 43108 | 11525442.3347 | 240340912.3274
Royal City | 5 | 5 | Royal City5 | 43122 | 11565536.4187 | 38812358.4187
PI Parks - ELSEWEDY | 4 | 4 | PI Parks - ELSEWEDY4 | 43131 | 3758163.8696 | 12907472.9296 | 43146
Sodic Club House | 26 | 26 | Sodic Club House26 | 43138 | 5215631.634 | 70469032.924 | 43153
Uptown PK #53 | 28 | 28 | Uptown PK #5328 | 43135 | 13381649.8939 | 253722562.2213 | 43146
Uptown PK #62 | 11 | 11 | Uptown PK #6211 | 43138 | 3260036.5785 | 32373469.7415 | 43146
PI Parks - ELSEWEDY | 5 | 5 | PI Parks - ELSEWEDY5 | 43170 | 1927670.8 | 14835143.73 | 43195
SIEMENS - Sokhna | 3 | 3 | SIEMENS - Sokhna3 | 43136 | 10401972.73 | 14803819.83
PK #117 | 2 | 2 | PK #1172 | 43152 | 7803090.35 | 7803090.35 | 43166
Uptown PK #53 | 29 | 29 | Uptown PK #5329 | 43157 | 17114848.1247 | 270837410.346 | 43165
NGU 2 | 26 | 26 | NGU 226 | 43131 | 6579666.5395 | 147069957.5395 | 43243
Uptown PK #62 | 12 | 12 | Uptown PK #6212 | 43177 | 2806216.291 | 35193186.031
Sodic Club House | 27 | 27 | Sodic Club House27 | 43169 | 6347559.6681 | 86021988.3593 | 43191
SIEMENS - Sokhna | 4 | 4 | SIEMENS - Sokhna4 | 43173 | 15960664.31 | 30764484.14
PK #117 | 3 | 3 | PK #1173 | 43173 | 4332593.51 | 12135683.86 | 43188
PI Parks - ELSEWEDY | 6 | 6 | PI Parks - ELSEWEDY6 | 43201 | 694638.63 | 15017848.53 | 43205
PK #107 | 13 | 13 | PK #10713 | 43192 | 2719252.37 | 52257607.28 | 43194
Uptown PK #53 | 30 | 30 | Uptown PK #5330 | 43188 | 15380090.6234 | 286603499.2497 | 43194
Sodic Club House | 28 | 28 | Sodic Club House28 | 43194 | 4455128.7309 | 90555725.5809 | 43228
Uptown PK #62 | 13 | 13 | Uptown PK #6213 | 43208 | 6967775.65 | 42160961.681 | 43228
PK #117 | 4 | 4 | PK #1174 | 43200 | 4131277.1774 | 16266961.0374 | 43209
Royal City | 6 | 6 | Royal City6 | 43214 | 17361811.89 | 54716858.14 | 43241
PI Parks - ELSEWEDY | 7 | 7 | PI Parks - ELSEWEDY7 | 43211 | 667972.21 | 15685820.74
SIEMENS - Sokhna | 5 | 5 | SIEMENS - Sokhna5 | 43205 | 19051976.33 | 49816460.47
PK #107 | 14 | 14 | PK #10714 | 43219 | 1449945.81 | 53707553.09
Mintra | 1 | 1 | Mintra1 | 43361 | 26487256.44 | 26487256.44
Uptown PK #53 | 31 | 31 | Uptown PK #5331 | 43220 | 10847277.7132 | 297391694.2129 | 43240
PK #117 | 5 | 5 | PK #1175 | 43227 | 6909334.9826 | 23176296.02 | 43242
Royal City | 7 | 7 | Royal City7 | 43242 | 11988097.7 | 66634655.56 | 43262
SIEMENS - Sokhna | 6 | 6 | SIEMENS - Sokhna6 | 43240 | 10481549.5128 | 60298009.9828
PI Parks - ELSEWEDY | 8 | 8 | PI Parks - ELSEWEDY8 | 43237 | 1892096.0888 | 17577916.8288 | 43253
Uptown PK #53 | 32 | 32 | Uptown PK #5332 | 43249 | 4916024.5037 | 302680787.2137
Al Jazi | 1 | 1 | Al Jazi1 | 43249 | 9888666.63 | 9888666.63 | 43254
PK #117 | 6 | 6 | PK #1176 | 43272 | 6651333.71 | 29827629.73 | 43293
Royal City | 8 | 8 | Royal City8 | 43275 | 7845708.0075 | 74373631.4775
SIEMENS - Sokhna | 7 | 7 | SIEMENS - Sokhna7 | 43285 | 12587450.0972 | 72885460.08
PI Parks - ELSEWEDY | 9 | 9 | PI Parks - ELSEWEDY9 | 43263 | 1491159.5592 | 19036617.1592
Uptown PK #53 | 33 | 33 | Uptown PK #5333 | 43284 | 3312628.1576 | 305993415.3712 | 43291
PI Parks - ELSEWEDY | 10 | 10 | PI Parks - ELSEWEDY10 | 43303 | 4758616.5674 | 23795233.7266 | 43313
PK #117 | 7 | 7 | PK #1177 | 43464 | -0.01 | 29854171.25
Al Jazi | 2 | 2 | Al Jazi2 | 43262 | 6959342.1 | 16848008.73 | 43277
SIEMENS - Sokhna | 8 | 8 | SIEMENS - Sokhna8 | 43300 | 18208993.38 | 91094453.46 | 43300
Sodic Club House | 31 | 31 | Sodic Club House31 | 43305 | 9473412.9251 | 110298796.01 | 43314
Al Jazi | 3 | 3 | Al Jazi3 | 43292 | 6863158.19 | 23711166.92 | 43306
Royal City | 9 | 9 | Royal City9 | 43307 | 7890492.132 | 82264123.6095
Uptown PK #53 | 34 | 34 | Uptown PK #5334 | 43307 | 73574.6923 | 306066990.0683
Al Jazi | 4 | 4 | Al Jazi4 | 43305 | 6873307.38 | 30584400.79 | 43310
Mintra | 2 | 2 | Mintra2 | 43366 | 16295714.9 | 42782971.34
Sodic Club House | 32 | 32 | Sodic Club House32 | 43328 | 11500368.6175 | 117323157.537 | 43347
PI Parks - ELSEWEDY | 11 | 11 | PI Parks - ELSEWEDY11 | 43320 | 891495.1766 | 23128178.0466 | 43356
SIEMENS - Sokhna | 9 | 9 | SIEMENS - Sokhna9 | 43346 | 19922320.61 | 111016774.07
PSP Substation | 3 | 3 | PSP Substation3 | 43384 | 2696322.9906 | 4366249.7906
Royal City | 10 | 10 | Royal City10 | 43339 | 8199169.349 | 90463292.9586
Al Jazi | 5 | 5 | Al Jazi5 | 43325 | 7893373.579 | 38477684.259 | 43342
Uptown PK #62 | 15 | 15 | Uptown PK #6215 | 43349 | 1266868.51 | 47319155.64
Uptown PK #53 | 35 | 35 | Uptown PK #5335 | 43355 | 3416261.3696 | 309483251.4379
Al Jazi | 6 | 6 | Al Jazi6 | 43353 | 4850391.56 | 43327773.16
Sodic Club House | 33 | 33 | Sodic Club House33 | 43368 | 7276853.7793 | 124600011.3163 | 43382
PI Parks - ELSEWEDY | 12 | 12 | PI Parks - ELSEWEDY12 | 43369 | 1804540.7798 | 24932718.8264
El Sewedy Uni.-PKG.1 | 1 | 1 | El Sewedy Uni.-PKG.11 | 43388 | 2762087.0381 | 2762087.0381 | 43388
SIEMENS - Sokhna | 10 | 10 | SIEMENS - Sokhna10 | 43368 | 9128690.32 | 120145464.39
Royal City | 11 | 11 | Royal City11 | 43367 | 2707034.9014 | 93170327.86
Uptown PK #53 | 36 | 36 | Uptown PK #5336 | 43376 | 2041348.5942 | 311524600.0321 | 43393
Mintra | 3 | 3 | Mintra3 | 43388 | 19469085.79 | 62252057.13
El Sewedy Uni.-PKG.2 | 1 | 1 | El Sewedy Uni.-PKG.21 | 43391 | 4165158.06 | 4165158.06
PI Parks - MEP | 1 | 1 | PI Parks - MEP1 | 43383 | 4100153.37 | 4100153.37
SIEMENS - Sokhna | 11 | 11 | SIEMENS - Sokhna11 | 43409 | 7601906.76 | 127747371.15
Al Jazi | 7 | 7 | Al Jazi7 | 43383 | 9361764.45 | 52689537.61 | 43389
PI Parks - ELSEWEDY | 13 | 13 | PI Parks - ELSEWEDY13 | 43383 | 1076504.1197 | 26009222.9461
Royal City | 12 | 12 | Royal City12 | 43397 | 9032801.23 | 102203129.09 | 43411
Uptown PK #62 | 16 | 16 | Uptown PK #6216 | 43429 | -245868.22 | 47073287.42
Sodic Club House | 34 | 34 | Sodic Club House34 | 43404 | 14426802.9732 | 134390194.7255 | 43425
Mintra-Hanger 1200m2 | 1 | 1 | Mintra-Hanger 1200m21 | 43402 | 1411985.3421 | 1411985.3421
El Sewedy Uni.-PKG.1 | 2 | 2 | El Sewedy Uni.-PKG.12 | 43398 | 1370079.6319 | 4132166.67
Uptown PK #53 | 37 | 37 | Uptown PK #5337 | 43450 | 1273110.6827 | 312797710.7077
Mintra | 4 | 4 | Mintra4 | 43422 | 9723925.4204 | 71975982.5504
Al Jazi | 8 | 8 | Al Jazi8 | 43410 | 13305889.63 | 65994656.05
Royal City | 13 | 13 | Royal City13 | 43425 | 7318551.3313 | 113140343.4613 | 43438
PI Parks - ELSEWEDY | 14 | 14 | PI Parks - ELSEWEDY14 | 43419 | 2476006.3139 | 28485229.26 | 43436
PI Parks - MEP | 2 | 2 | PI Parks - MEP2 | 43419 | 3824663.6 | 7924816.97 | 43436
El Sewedy Uni.-PKG.1 | 3 | 3 | El Sewedy Uni.-PKG.13 | 43431 | 1749696.33 | 5881863
El Sewedy Uni.-PKG.2 | 2 | 2 | El Sewedy Uni.-PKG.22 | 43412 | 5976536.23 | 10141694.29
Al Jazi | 9 | 9 | Al Jazi9 | 43432 | 11249079.12 | 77243735.17
El Sewedy Uni.-PKG.1 | 4 | 4 | El Sewedy Uni.-PKG.14 | 43444 | 807197.6524 | 7615896.5 | 43444
Royal City | 14 | 14 | Royal City14 | 43463 | 3293171.7405 | 120430321.4905
PK #117 | 8 | 8 | PK #1178 | 43464 | 4511257.49 | 34365428.74
PI Parks - MEP | 3 | 3 | PI Parks - MEP3 | 43449 | 4229682.9 | 12154499.87 | 43460
PI Parks - ELSEWEDY | 15 | 15 | PI Parks - ELSEWEDY15 | 43449 | 7576900.68 | 34774839.86 | 43460
El Sewedy Uni.-PKG.1 | 5 | 5 | El Sewedy Uni.-PKG.15 | 43452 | 267331.59 | 7883228.09
Al Jazi | 10 | 10 | Al Jazi10 | 43453 | 7201307.23 | 84445042.4
Al Jazi | 11 | 11 | Al Jazi11 | 43473 | 10407080.28 | 94852122.68
El Sewedy Uni.-PKG.2 | 4 | 4 | El Sewedy Uni.-PKG.24 | 43475 | 5121900.2295 | 19721961.8801
PKG#144 | 2 | 2 | PKG#1442 | 43485 | 4125990.87 | 4125990.87
El Sewedy Uni.-PKG.1 | 6 | 6 | El Sewedy Uni.-PKG.16 | 43473 | 205504.28 | 8088732.37
PK #117 | 9 | 9 | PK #1179 | 43495 | 3153415.09 | 37518843.83
Sodic Club House | 35 | 35 | Sodic Club House35 | 43434 | 10886083.2297 | 140396520.4122 | 43819
PI Parks - MEP | 4 | 4 | PI Parks - MEP4 | 43479 | 13292686.78 | 23744138.61
PI Parks - ELSEWEDY | 16 | 16 | PI Parks - ELSEWEDY16 | 43479 | 6344223.5299 | 40029120.3299 | 43492
Royal City | 15 | 15 | Royal City15 | 43485 | 16384822.4548 | 136815143.9453
SIEMENS - Sokhna | 16 | 16 | SIEMENS - Sokhna16 | 43485 | 32022484.92 | 254086770.43 | 43488
El Sewedy Uni.-PKG.1 | 7 | 7 | El Sewedy Uni.-PKG.17 | 43487 | 410253.12 | 8498985.49
Uptown PK #53 | 38 | 38 | Uptown PK #5338 | 43514 | 747405.6143 | 313545116.322
Al Jazi | 12 | 12 | Al Jazi12 | 43500 | 8329656 | 103181778.68
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 43544 | 9063098.3369 | 9063098.3369
PK #117 | 10 | 10 | PK #11710 | 43506 | 992195.9681 | 38511039.7981 | 43524
PKG#101 | 1 | 1 | PKG#1011 | 43508 | 1738465.6667 | 1738465.6667 | 43513
El Sewedy Uni.-PKG.2 | 5 | 5 | El Sewedy Uni.-PKG.25 | 43506 | 8018043.8084 | 27740005.6885
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 43514 | 1805053.3662 | 1805053.3662
El Sewedy Uni.-PKG.1 | 8 | 8 | El Sewedy Uni.-PKG.18 | 43502 | 339720.12 | 8838705.61
PI Parks - MEP | 5 | 5 | PI Parks - MEP5 | 43512 | 7765619.63 | 31509758.24 | 43537
SIEMENS - Sokhna | 17 | 17 | SIEMENS - Sokhna17 | 43577 | 57817326.87 | 311904097.3
PI Parks - ELSEWEDY | 17 | 17 | PI Parks - ELSEWEDY17 | 43512 | 3393993.12 | 42011770.38 | 43537
Royal City | 16 | 16 | Royal City16 | 43521 | 11488490.3339 | 148303634.2792
Al Jazi | 13 | 13 | Al Jazi13 | 43528 | 8749208.76 | 111930987.44
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 43515 | 3340179.702 | 3340179.702
El Sewedy Uni.-PKG.2 | 6 | 6 | El Sewedy Uni.-PKG.26 | 43535 | 8105230.8115 | 35845236.5
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 43536 | 2400436.8318 | 7545669.9
PI Parks - MEP | 6 | 6 | PI Parks - MEP6 | 43541 | 3555303.77 | 35065062.01 | 43550
PKG#101 | 2 | 2 | PKG#1012 | 43543 | 1610908.8476 | 3349374.5143
Royal City | 17 | 17 | Royal City17 | 43556 | 9063503.9339 | 157367138.2131
PI Parks - ELSEWEDY | 18 | 18 | PI Parks - ELSEWEDY18 | 43541 | 4573274.545 | 46585044.925 | 43551
Al Jazi | 14 | 14 | Al Jazi14 | 43563 | 9382086.37 | 121313073.81
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 43563 | 2377467.23 | 2377467.23 | 43579
El Sewedy Uni.-PKG.1 | 9 | 9 | El Sewedy Uni.-PKG.19 | 43565 | 104805.89 | 8943511.5
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 43565 | 6026842.9 | 13572512.8
PI Parks - MEP | 7 | 7 | PI Parks - MEP7 | 43572 | 4908164.7774 | 39969524.1674 | 43599
PSP Substation | 10 | 10 | PSP Substation10 | 43578 | 4978707.75 | 29883668.3
Royal City | 18 | 18 | Royal City18 | 43573 | 8621924.8043 | 165989063.0174
Uptown PK #53 | 39 | 39 | Uptown PK #5339 | 43576 | 32300.9957 | 313577417.3177
El Sewedy Uni.-PKG.2 | 7 | 7 | El Sewedy Uni.-PKG.27 | 43565 | 4929812 | 40775048.5
PKG#101 | 3 | 3 | PKG#1013 | 43578 | 4030395.5429 | 7379770.0571 | 43590
PI Parks - ELSEWEDY | 19 | 19 | PI Parks - ELSEWEDY19 | 43572 | 4823264.9186 | 49467914.3986 | 43599
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 43573 | 20887437.3108 | 29950535.6476
El Sewedy Uni.-PKG.3 | 5 | 5 | El Sewedy Uni.-PKG.35 | 43590 | 27458064.6 | 41030577.4
PI Parks - MEP | 8 | 8 | PI Parks - MEP8 | 43604 | 2655162.8183 | 42624686.9424
Al Jazi | 15 | 15 | Al Jazi15 | 43594 | 9011217.19 | 130324291
PI Parks - ELSEWEDY | 20 | 20 | PI Parks - ELSEWEDY20 | 43604 | 4018450.9279 | 51315568.4279
Royal City | 19 | 19 | Royal City19 | 43608 | 15549148.0486 | 181538211.066
Al Jazi | 16 | 16 | Al Jazi16 | 43617 | 9502208.88 | 139826499.88
Al Jazi - Center Zone | 2 | 2 | Al Jazi - Center Zone2 | 43614 | 6291718.01 | 8640525.61
PKG#101 | 4 | 4 | PKG#1014 | 43614 | 4428897.7238 | 11808672.4857
Sodic Eastown | 3 | 3 | Sodic Eastown3 | 43608 | 2101069.4381 | 32051605.0857
El Sewedy Uni.-PKG.2 | 8 | 8 | El Sewedy Uni.-PKG.28 | 43684 | 1755356.8 | 42530405.3
El Sewedy Uni.-PKG.3 | 6 | 6 | El Sewedy Uni.-PKG.36 | 43632 | 30765208.3 | 71795785.7
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 43643 | 4797449.5194 | 4797449.5194
Royal City | 20 | 20 | Royal City20 | 43642 | 7876990.4815 | 189415201.5475
Uptown PK #53 | 40 | 40 | Uptown PK #5340 | 43662 | 52815.0023 | 313630232.32
PI Parks - ELSEWEDY | 21 | 21 | PI Parks - ELSEWEDY21 | 43751 | 598299.7921 | 51913868.22
PI Parks - MEP | 9 | 9 | PI Parks - MEP9 | 43751 | 3596767.6976 | 46221454.64
Al Jazi | 17 | 17 | Al Jazi17 | 43652 | 7664029.32 | 147490529.2
Sodic Eastown | 4 | 4 | Sodic Eastown4 | 43654 | 22270031.4 | 54321636.4857
PKG#101 | 5 | 5 | PKG#1015 | 43670 | 2224631.7143 | 14033304.2
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 43667 | 4911239.0806 | 9708688.6
Royal City | 21 | 21 | Royal City21 | 43664 | 7532294.3265 | 196947495.8739
El Sewedy Uni.-PKG.3 | 7 | 7 | El Sewedy Uni.-PKG.37 | 43671 | 41332921.1 | 113128706.8
Al Jazi | 18 | 18 | Al Jazi18 | 43673 | 7401622.43 | 154892151.63
Al Jazi - Center Zone | 3 | 3 | Al Jazi - Center Zone3 | 43673 | 12038969.26 | 20679494.87 | 43709
Sodic Eastown | 5 | 5 | Sodic Eastown5 | 43678 | 45005158.6118 | 99326795.0975
Mivida-PK#140 | 3 | 3 | Mivida-PK#1403 | 43697 | 6244069.8629 | 15952758.4629
Royal City | 22 | 22 | Royal City22 | 43710 | 24265130.1959 | 221212626.0698
PKG#101 | 6 | 6 | PKG#1016 | 43705 | 3491880.8381 | 17525185.0381
El Sewedy Uni.-PKG.3 | 8 | 8 | El Sewedy Uni.-PKG.38 | 43701 | 23588218.3 | 136716925.1
El Sewedy Uni.-PKG.1 | 10 | 10 | El Sewedy Uni.-PKG.110 | 43684 | 2360 | 8945871.5
Sodic Eastown | 6 | 6 | Sodic Eastown6 | 43716 | 38734277.1501 | 138061072.2476
Al Jazi | 19 | 19 | Al Jazi19 | 43718 | 9504587.63 | 164396739.26
Al Jazi - Center Zone | 4 | 4 | Al Jazi - Center Zone4 | 43718 | 4840645.74 | 25519840.19
El Sewedy Uni.-PKG.3 | 9 | 9 | El Sewedy Uni.-PKG.39 | 43705 | 30130968 | 166847893.1
PK #117 | 12 | 12 | PK #11712 | 43733 | 2921413.42 | 42643976.35
Mivida-PK#140 | 4 | 4 | Mivida-PK#1404 | 43725 | 2442385.7689 | 18395144.2317
PKG#144 | 12 | 12 | PKG#14412 | 43741 | 34717376.42 | 151479307.34
Royal City | 23 | 23 | Royal City23 | 43736 | 6268692.5562 | 227481318.626
PKG#101 | 7 | 7 | PKG#1017 | 43729 | 3120848.981 | 20646034.019 | 43734
El Sewedy Uni.-PKG.3 | 10 | 10 | El Sewedy Uni.-PKG.310 | 43737 | 28039187.7 | 194887080.8
Mivida-PK#140 | 5 | 5 | Mivida-PK#1405 | 43761 | 1994559.8383 | 20389704.07
Al Jazi | 20 | 20 | Al Jazi20 | 43772 | 8799095.49 | 173195834.75
Al Jazi - Center Zone | 5 | 5 | Al Jazi - Center Zone5 | 43772 | 7051826.31 | 32571666.5
Royal City | 24 | 24 | Royal City24 | 43762 | 17799666.736 | 245280985.3621
Royal City - Landscape | 3 | 3 | Royal City - Landscape3 | 43761 | 341000 | 341000
PKG#101 | 8 | 8 | PKG#1018 | 43772 | 4703530.9524 | 25352356.981 | 43774
PK #117 | 13 | 13 | PK #11713 | 43781 | 2611652.87 | 45255629.22
Sodic Eastown | 8 | 8 | Sodic Eastown8 | 43783 | 85059782.1524 | 288748271.5905
Royal City | 25 | 25 | Royal City25 | 43796 | 17503083.0268 | 262784068.3888
Royal City - Landscape | 4 | 4 | Royal City - Landscape4 | 43824 | 2839877.7881 | 3180877.7881
Mivida-PK#140 | 6 | 6 | Mivida-PK#1406 | 43789 | 12232780.5437 | 32622484.6137 | 43809
HyperOne | 1 | 1 | HyperOne1 | 43793 | 1684523.66 | 1684523.66
PKG#101 | 9 | 9 | PKG#1019 | 43802 | 3179849.8818 | 28533563.3143
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | PH.2-El Sewedy Uni. - Enabling1 | 43810 | 1222080 | 1222080
Mivida-PK#140 | 7 | 7 | Mivida-PK#1407 | 43818 | 7170532.1164 | 39793016.7264
HyperOne | 2 | 2 | HyperOne2 | 43811 | 11473372.17 | 13157895.83
Royal City | 26 | 26 | Royal City26 | 43835 | 10595979.9301 | 273380048.3189
Royal City - Landscape | 5 | 5 | Royal City - Landscape5 | 43835 | 5896802.2265 | 9077680.0146
PKG#101 | 10 | 10 | PKG#10110 | 43828 | 3111780.0857 | 31645343.4 | 43836
CFC | 1 | 1 | CFC1 | 43842 | 6586123.18 | 6586123.18
Uptown PK #62 | 19 | 19 | Uptown PK #6219 | 43944 | 22437 | 47095724.42 | 44031
PH.2-El Sewedy Uni. - Enabling | 2 | 2 | PH.2-El Sewedy Uni. - Enabling2 | 43841 | 19989408.99 | 21211488.99
HyperOne | 3 | 3 | HyperOne3 | 43843 | 10276217.5887 | 23434113.4187
Mivida-PK#140 | 8 | 8 | Mivida-PK#1408 | 43858 | 6113446.7507 | 45906463.4771 | 43874
Sodic Eastown | 10 | 10 | Sodic Eastown10 | 43856 | 88119712.7238 | 392914894.2286 | 43850
CFC | 2 | 2 | CFC2 | 43872 | 16003200.38 | 22589323.56
Royal City | 27 | 27 | Royal City27 | 43871 | 20586377.6301 | 293966425.9491
Royal City - Landscape | 6 | 6 | Royal City - Landscape6 | 43871 | 12932194.6154 | 22009874.63
El-Gouna - Equip. Rental | 1 | 1 | El-Gouna - Equip. Rental1 | 43863 | 80875 | 80875
El-Gouna - Temp. Fence | 1 | 1 | El-Gouna - Temp. Fence1 | 43891 | 409200 | 409200
Al Jazi | 21 | 21 | Al Jazi21 | 43914 | 33097306.6205 | 206293141.3705
CFC | 3 | 3 | CFC3 | 43901 | 16743766.83 | 39333090.39
HyperOne | 4 | 4 | HyperOne4 | 43874 | 12451224.3668 | 35885337.7855 | 43884
PH.2-El Sewedy Uni. - Enabling | 3 | 3 | PH.2-El Sewedy Uni. - Enabling3 | 43866 | 22171564.66 | 43383053.65
PKG#101 | 11 | 11 | PKG#10111 | 43874 | 382240.2571 | 32016510.4571 | 43888
Mivida-PK#140 | 9 | 9 | Mivida-PK#1409 | 43884 | 4233335.7568 | 50139799.2368 | 43908
Al Jazi - Center Zone | 6 | 6 | Al Jazi - Center Zone6 | 43914 | 6082957.03 | 38654623.53
HyperOne | 5 | 5 | HyperOne5 | 43884 | 5616638.2145 | 41501976
Royal City | 28 | 28 | Royal City28 | 43906 | 15640549.4851 | 309606975.4342
Royal City - Landscape | 7 | 7 | Royal City - Landscape7 | 43906 | 6479189.8549 | 28489064.4849
El-Gouna | 5 | 5 | El-Gouna5 | 43884 | 3430037.61 | 17346579.72
HyperOne | 6 | 6 | HyperOne6 | 43897 | 10976157.5052 | 52478133.5052
Mivida-PK#140 | 10 | 10 | Mivida-PK#14010 | 43950 | 6612227.7834 | 56752027.0202
Sodic Eastown | 12 | 12 | Sodic Eastown12 | 43919 | 26833421.413 | 450976932.5714
PH.2-El Sewedy Uni. - Enabling | 4 | 4 | PH.2-El Sewedy Uni. - Enabling4 | 43906 | 17471458.95 | 60854512.6
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 43912 | 39552087.9 | 39552087.9
CFC | 4 | 4 | CFC4 | 43923 | 35226223.2 | 74559313.59
El-Gouna | 6 | 6 | El-Gouna6 | 43908 | 6540676.19 | 23887255.91 | 43908
HyperOne | 7 | 7 | HyperOne7 | 43913 | 12354446.4948 | 64832580
CFC | 5 | 5 | CFC5 | 43943 | 30502560.31 | 105061873.9
Mivida-PK#140 | 11 | 11 | Mivida-PK#14011 | 43950 | 3124627.5928 | 59876654.613
Royal City | 29 | 29 | Royal City29 | 43926 | 18804604.7977 | 328411580.2319
Royal City - Landscape | 8 | 8 | Royal City - Landscape8 | 43926 | 17137734.2822 | 45626798.7671
PKG#101 | 12 | 12 | PKG#10112 | 43929 | 2584477.6667 | 34580168.2667
PH.2-El Sewedy Uni. - Enabling | 5 | 5 | PH.2-El Sewedy Uni. - Enabling5 | 43930 | 7891719.6 | 68746232.2
Sodic Eastown | 13 | 13 | Sodic Eastown13 | 43943 | 26192906.0286 | 477169838.6 | 43968
HyperOne | 8 | 8 | HyperOne8 | 43933 | 7228560.7301 | 72061140.7301
PH.2-El Sewedy Uni. - Finishes | 2 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 43943 | 33281363.92 | 72833451.82
CFC | 6 | 6 | CFC6 | 43955 | 42011127.9851 | 147073001.8851
Royal City | 30 | 30 | Royal City30 | 43956 | 13862319.0142 | 342273899.2462
Royal City - Landscape | 9 | 9 | Royal City - Landscape9 | 43956 | 6296234.5253 | 51923033.2924
HyperOne | 9 | 9 | HyperOne9 | 43947 | 2029339.2699 | 74090480
El-Gouna | 7 | 7 | El-Gouna7 | 43942 | 3114205.16 | 27001461.07 | 43942
PH.2-El Sewedy Uni. - Enabling | 6 | 6 | PH.2-El Sewedy Uni. - Enabling6 | 43957 | 18379179.4 | 87125411.6
Mivida-PK#140 | 12 | 12 | Mivida-PK#14012 | 43972 | 1875813.048 | 61752467.661
PH.2-El Sewedy Uni. - Finishes | 3 | 3 | PH.2-El Sewedy Uni. - Finishes3 | 43970 | 24169965.9076 | 97003417.7276
CFC | 7 | 7 | CFC7 | 43986 | 17879880.0649 | 164952881.95
Royal City - Landscape | 10 | 10 | Royal City - Landscape10 | 44014 | 3937848.897 | 55860882.1894
Royal City | 31 | 31 | Royal City31 | 44014 | 10234077.8776 | 352507977.1238
HyperOne | 10 | 10 | HyperOne10 | 43983 | 7741768.3647 | 81832248.3647
PH.2-El Sewedy Uni. - Enabling | 7 | 7 | PH.2-El Sewedy Uni. - Enabling7 | 44023 | 9076073.5 | 96201485.1
CFC | 8 | 8 | CFC8 | 44019 | 31008098.6054 | 195960980.5554
PH.2-El Sewedy Uni. - Finishes | 4 | 4 | PH.2-El Sewedy Uni. - Finishes4 | 44000 | 24591514.8424 | 121594932.57
HyperOne | 11 | 11 | HyperOne11 | 44005 | 9960645.6353 | 91792894
Royal City | 32 | 32 | Royal City32 | 44020 | 3761397.6023 | 356269374.7261
Royal City - Landscape | 11 | 11 | Royal City - Landscape11 | 44020 | 5192701.4937 | 61053583.6831
PK #117 | 14 | 14 | PK #11714 | 44082 | 1169069.6666 | 46915000.03 | 44101
CFC | 9 | 9 | CFC9 | 44039 | 29660399.8248 | 225621380.3802
HyperOne | 12 | 12 | HyperOne12 | 44023 | 3093528.5715 | 94886422.5715
El-Gouna | 8 | 8 | El-Gouna8 | 44018 | 3250029.8 | 30251490.87 | 44018
Mivida-PK#140 | 14 | 14 | Mivida-PK#14014 | 44033 | 2429362.3736 | 65607696.3436
PH.2-El Sewedy Uni. - Enabling | 8 | 8 | PH.2-El Sewedy Uni. - Enabling8 | 44021 | 2504382.4 | 98705867.5
PH.2-El Sewedy Uni. - Finishes | 5 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 44025 | 77007398.3 | 198602330.87
Royal City | 33 | 33 | Royal City33 | 44055 | 13830917.4352 | 370100292.1612
Royal City - Landscape | 12 | 12 | Royal City - Landscape12 | 44055 | 8940402.3014 | 69993985.9845
PH.2-El Sewedy Uni. - Finishes | 6 | 6 | PH.2-El Sewedy Uni. - Finishes6 | 44041 | 22875033.55 | 221477364.42
PH.2-El Sewedy Uni. - Enabling | 9 | 9 | PH.2-El Sewedy Uni. - Enabling9 | 44070 | 9452002.7 | 108157870.2
CFC | 10 | 10 | CFC10 | 44069 | 46257284.4262 | 271878664.8064
Mivida-PK#140 | 15 | 15 | Mivida-PK#14015 | 44067 | 16266667.6714 | 81874364.0149
HyperOne | 13 | 13 | HyperOne13 | 44062 | 9161230.539 | 104047653.1105
Royal City - Landscape | 13 | 13 | Royal City - Landscape13 | 44081 | 3598777.1179 | 73592763.1024
Royal City | 34 | 34 | Royal City34 | 44088 | 7811639.6921 | 377911931.8534
PH.2-El Sewedy Uni. - Finishes | 7 | 7 | PH.2-El Sewedy Uni. - Finishes7 | 44069 | 54216090.64 | 275693455.06
Sodic Eastown | 17 | 17 | Sodic Eastown17 | 44065 | 33693489.0097 | 593205155.981 | 44081
CFC | 11 | 11 | CFC11 | 44103 | 22706553.5236 | 294585218.33
Mivida-PK#140 | 16 | 16 | Mivida-PK#14016 | 44089 | 19380294.5984 | 101254658.6133
HyperOne | 14 | 14 | HyperOne14 | 44087 | 5698538.8895 | 109746192
PH.2-El Sewedy Uni. - Finishes | 8 | 8 | PH.2-El Sewedy Uni. - Finishes8 | 44091 | 61814968.03 | 337508423.09
Royal City | 35 | 35 | Royal City35 | 44109 | 3980750.5222 | 381892682.3756
Royal City - Landscape | 14 | 14 | Royal City - Landscape14 | 44109 | 2137131.084 | 75729894.1864
HyperOne | 15 | 15 | HyperOne15 | 44447 | 16067546 | 125813738
Mivida-PK#140 | 17 | 17 | Mivida-PK#14017 | 44123 | 16610857.3328 | 117865515.946
Royal City | 36 | 36 | Royal City36 | 44132 | 8343396.9284 | 390236079.304
Royal City - Landscape | 15 | 15 | Royal City - Landscape15 | 44132 | 3135305.5981 | 78865199.7846
CFC | 12 | 12 | CFC12 | 44139 | 35304714.2417 | 329889932.5717
PH.2-El Sewedy Uni. - Finishes | 9 | 9 | PH.2-El Sewedy Uni. - Finishes9 | 44124 | 56169721.37 | 393678144.46
AEON | 2 | 2 | AEON2 | 44147 | 1300835.2032 | 2626046.4794 | 44180
CFC | 13 | 13 | CFC13 | 44174 | 13502068.4452 | 343392001.0169
Royal City | 37 | 37 | Royal City37 | 44161 | 5412454.8663 | 395648534.1703
Mivida-PK#140 | 18 | 18 | Mivida-PK#14018 | 44164 | 4603925.7609 | 122469441.707
Royal City - Landscape | 16 | 16 | Royal City - Landscape16 | 44161 | 1582061.2622 | 80447261.0467
PH.2-El Sewedy Uni. - Finishes | 10 | 10 | PH.2-El Sewedy Uni. - Finishes10 | 44154 | 33204826.41 | 426882970.87
ORA - ZED | 1 | 1 | ORA - ZED1 | 44213 | 2407390.5714 | 2407390.5714
CFC | 14 | 14 | CFC14 | 44207 | 29172801.673 | 372564802.6899
PKG#101 | 15 | 15 | PKG#10115 | 44182 | 440607.3155 | 42275929.0869 | 44216
Mivida-PK#140 | 19 | 19 | Mivida-PK#14019 | 44186 | 11459315.8636 | 133928757.5706 | 44186
Royal City | 38 | 38 | Royal City38 | 44201 | 3712322.3219 | 399360856.4923
Royal City - Landscape | 17 | 17 | Royal City - Landscape17 | 44201 | 3716309.8261 | 84163570.8728
PH.2-El Sewedy Uni. - Finishes | 11 | 11 | PH.2-El Sewedy Uni. - Finishes11 | 44186 | 20698550.4 | 447581521.27
AEON | 3 | 3 | AEON3 | 44200 | 799158.9955 | 3737551.6717
ORA - ZED | 2 | 2 | ORA - ZED2 | 44202 | 43865060.0886 | 46272450.66 | 44202
Mivida-PK#140 | 20 | 20 | Mivida-PK#14020 | 44231 | 5957491.0722 | 139886248.6428
CFC | 15 | 15 | CFC15 | 44249 | 46288367.9197 | 418853170.6096
Royal City - Landscape | 18 | 18 | Royal City - Landscape18 | 44230 | 1163660.8736 | 85327231.7464
Royal City | 39 | 39 | Royal City39 | 44230 | 1174176.5076 | 400535032.9999
PKG#144 | 16 | 16 | PKG#14416 | 44256 | 150533.34 | 176412609.32 | 44280
ORA - ZED | 3 | 3 | ORA - ZED3 | 44244 | 23073312.5238 | 70686130.1714 | 44244
CFC | 16 | 16 | CFC16 | 44276 | 25170121.1048 | 444023291.7144
Mivida-PK#140 | 21 | 21 | Mivida-PK#14021 | 44244 | 9991628.9775 | 149877877.6203 | 44245
HQ - CFC | 1 | 1 | HQ - CFC1 | 44249 | 1435679.4 | 1435679.4
Royal City - Landscape | 19 | 19 | Royal City - Landscape19 | 44257 | 2029657.8338 | 87356889.5802
PH.2-El Sewedy Uni. - Finishes | 12 | 12 | PH.2-El Sewedy Uni. - Finishes12 | 44271 | 36099063.7776 | 483680585.0476 | 44277
CFC | 17 | 17 | CFC17 | 44280 | 23196101.9456 | 467219393.66
CFC | 18 | 18 | CFC18 | 44292 | 16880809.49 | 484100203.15
ORA - ZED | 4 | 4 | ORA - ZED4 | 44279 | 21833038.3714 | 96213963.4667 | 44279
HQ - CFC | 2 | 2 | HQ - CFC2 | 44277 | 7766126.7 | 9201806.1
Sodic Eastown | 24 | 24 | Sodic Eastown24 | 44284 | 25445155.6214 | 844856989.8952 | 44297
Royal City | 40 | 40 | Royal City40 | 44298 | 5847326.4556 | 406382359.4555
Royal City - Landscape | 20 | 20 | Royal City - Landscape20 | 44298 | 1366613.9629 | 88723503.543
CFC | 19 | 19 | CFC19 | 44306 | 20398722.16 | 504498925.31
CFC | 20 | 20 | CFC20 | 44340 | 23102145.85 | 527601071.16
ORA - ZED | 5 | 5 | ORA - ZED5 | 44339 | 41442903.7055 | 142416997.3436 | 44327
HQ - CFC | 3 | 3 | HQ - CFC3 | 44301 | 12533035.1 | 21734841.2
Mivida-PK#140 | 23 | 23 | Mivida-PK#14023 | 44327 | 1777689.2863 | 157122573.9763 | 44342
HQ - CFC | 4 | 4 | HQ - CFC4 | 44342 | 11480730.2 | 33215571.4
CFC | 21 | 21 | CFC21 | 44364 | 23568050.8 | 551169121.96
CFC | 22 | 22 | CFC22 | 44376 | 19833699.32 | 571002821.28
ORA - ZED | 6 | 6 | ORA - ZED6 | 44343 | 15678333.3286 | 156246633.6714 | 44355
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 44362 | 5145072.89 | 5145072.89
EGAT Pelletizing Plant-Water Tank | 1 | 1 | EGAT Pelletizing Plant-Water Tank1 | 44369 | 3274479.04 | 3274479.04
Royal City | 41 | 41 | Royal City41 | 44501 | 5256684.0377 | 411639043.4932
PH.2-El Sewedy Uni. - Finishes | 13 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 44678 | 13891238 | 494664244.29
Royal City - Landscape | 21 | 21 | Royal City - Landscape21 | 44390 | 4112536.457 | 92836040
EGAT Pelletizing Plant-MEP | 1 | 1 | EGAT Pelletizing Plant-MEP1 | 44433 | 2011978.5 | 2011978.5
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 44389 | 10496612.58 | 15641685.47
CFC | 23 | 23 | CFC23 | 44426 | 19569971.41 | 590572792.69
Katameya - Creeks | 7 | 7 | Katameya - Creeks7 | 44404 | 46826693.78 | 204907885.73
PKG#178 | 6 | 6 | PKG#1786 |  | 4524611.3442 | 46623243.3042 | 44460
EGAT Pelletizing Plant-Water Tank | 2 | 2 | EGAT Pelletizing Plant-Water Tank2 | 44389 | 2028589.79 | 5303068.83
CFC | 24 | 24 | CFC24 | 44462 | 14455028.52 | 605027821.21
PKG#177 | 18 | 18 | PKG#17718 | 44440 | 12925810.52 | 101062801.09 | 44441
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 44427 | 4383722.29 | 20025407.76
EGAT Pelletizing Plant-Water Tank | 3 | 3 | EGAT Pelletizing Plant-Water Tank3 | 44427 | 725357.85 | 6028426.68
PKG#177 | 19 | 19 | PKG#17719 |  | -0.0001 | 101062801.09 | 44455
PKG#177 | 20 | 20 | PKG#17720 |  | -0.001 | 101062801.09 | 44488
ORA - ZED | 9 | 9 | ORA - ZED9 | 44448 | 29833656.4571 | 222298531.4286 | 44459
CFC | 25 | 25 | CFC25 | 44494 | 13190112.67 | 618217933.88
PKG#177 | 21 | 21 | PKG#17721 |  | -0.0001 | 111518679.06 | 44518
Ring Road - Mounib | 9 | 9 | Ring Road - Mounib9 |  | 4536613.5882 | 98438363.943
Ring Road - Mounib | 10 | 10 | Ring Road - Mounib10 |  | 18316815 | 116755178.943
PKG#177 | 22 | 22 | PKG#17722 |  | -0.0001 | 122505070.55 | 44537
EGAT Pelletizing Plant-Water Tank | 4 | 4 | EGAT Pelletizing Plant-Water Tank4 | 44444 | 766173.48 | 6794600.16
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 44466 | 6320391.6 | 26345799.36
Ring Road - Mounib | 11 | 11 | Ring Road - Mounib11 | 44446 | 30549611.057 | 147304790
CFC | 26 | 26 | CFC26 | 44518 | 6460765.9427 | 624678699.8227
HQ - CFC | 7 | 7 | HQ - CFC7 | 44448 | 14463563.8 | 59130669.9
PKG#177 | 23 | 23 | PKG#17723 |  | -0.0001 | 130097671.64 | 44565
ORA - ZED | 10 | 10 | ORA - ZED10 | 44465 | 32858070.0667 | 252726343.0667
PKG#177 | 24 | 24 | PKG#17724 |  | -0.0001 | 134853540.34 | 44587
Royal City - Landscape | 22 | 22 | Royal City - Landscape22 | 44501 | 3299640.8 | 96135680.8
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 44489 | 14624189 | 40969988.36
EGAT Pelletizing Plant-Water Tank | 5 | 5 | EGAT Pelletizing Plant-Water Tank5 | 44481 | 923594.34 | 7718194.5
PKG#177 | 25 | 25 | PKG#17725 |  | -0.0001 | 140808056.23 | 44620
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 44482 | 13196047.2 | 13196047.2 | 44482
HQ - CFC | 8 | 8 | HQ - CFC8 | 44482 | 12903651.6 | 72034321.5 | 44486
Ring Road - Mounib | 12 | 12 | Ring Road - Mounib12 | 44485 | 20117126 | 167421916
Kafr Shokr | 7 | 7 | Kafr Shokr 7 |  | 31881474.95 | 108184525
CFC | 27 | 27 | CFC27 | 44522 | 7714993.7673 | 632393693.59
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 44514 | 11102739.54 | 52072727.9
EGAT Pelletizing Plant-Water Tank | 6 | 6 | EGAT Pelletizing Plant-Water Tank6 | 44509 | 1464316.6 | 9182511.1
HQ - CFC | 9 | 9 | HQ - CFC9 | 44511 | 11039038.4 | 83025202.3
Royal City - Landscape | 23 | 23 | Royal City - Landscape23 | 44970 | 10826725.43 | 106962406.23
Ring Road - Mounib | 13 | 13 | Ring Road - Mounib13 | 44513 | 56505929 | 223927845
Sports Hall - Finishes | 3 | 3 | Sports Hall - Finishes3 | 44517 | 91998353.75 | 178494684.93
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 44514 | 21711682.2014 | 34907729.4014 | 44514
PKG#162 | 15 | 15 | PKG#16215 | 44613 | 0.01 | 100261400.96 | 44627
Kafr Shokr | 8 | 8 | Kafr Shokr 8 | 44555 | 2504502 | 110689027
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 44579 | 15579509.1856 | 50487238.587 | 44579
HQ - CFC | 10 | 10 | HQ - CFC10 | 44546 | 10645458.9 | 93670661.2
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 44550 | 14005522.66 | 66078250.56
EGAT Pelletizing Plant-Water Tank | 7 | 7 | EGAT Pelletizing Plant-Water Tank7 | 44539 | 399729.3 | 9582240.4
MDF Factory | 6 | 6 | MDF Factory6 | 44581 | 17937654.1261 | 68968353.37
Ring Road - Mounib | 14 | 14 | Ring Road - Mounib14 | 44924 | 46948185.4 | 270876030.4
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 44570 | 34505631.6966 | 84992870.2836 | 44607
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 44579 | 12121253.25 | 78199503.81
EGAT Pelletizing Plant-Water Tank | 8 | 8 | EGAT Pelletizing Plant-Water Tank8 | 44567 | 307226.2 | 9889466.6
Kafr Shokr | 9 | 9 | Kafr Shokr 9 | 44780 | 5785188 | 116474215
Ring Road - Mounib | 15 | 15 | Ring Road - Mounib15 | 44581 | 30552404.425 | 301428434.825
HQ - CFC | 11 | 11 | HQ - CFC11 | 44578 | 21606397.9 | 115277059.1 | 44854
Sports Hall - Finishes - ADD.01 | 1 | 1 | Sports Hall - Finishes - ADD.011 | 44614 | 9145259 | 9145259
MDF Factory | 7 | 7 | MDF Factory7 | 44594 | 16588591.02 | 85556944.39 | 44606
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 44620 | 21476647.48 | 21476647.48
Ring Road - Mounib | 16 | 16 | Ring Road - Mounib16 | 44769 | 161507041.625 | 462935476.45
Kafr Shokr | 10 | 10 | Kafr Shokr 10 | 44830 | 2841975 | 119316190
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 44606 | 34312846.6 | 34312846.6
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 44616 | 15797419.96 | 93996923.77
EGAT Pelletizing Plant-Water Tank | 9 | 9 | EGAT Pelletizing Plant-Water Tank9 | 44622 | 1064224 | 10953690.6
Rolling Mill #4-TRAESUEZ | 2 | 2 | Rolling Mill #4-TRAESUEZ2 | 44642 | 13583921.53 | 35060569.01
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 44616 | 5018202.5 | 5018202.5
Katameya - Creeks | 14 | 14 | Katameya - Creeks14 | 44616 | 45239351.95 | 505191976.74
MDF Factory | 8 | 8 | MDF Factory8 | 44621 | 12291002.2884 | 97340309.44
ORA - ZED - ph.02 | 5 | 5 | ORA - ZED - ph.025 | 44617 | 9902335.4874 | 94895205.771 | 44643
HQ - CFC | 12 | 12 | HQ - CFC12 | 44616 | 11990804.88 | 127267864.5
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 44620 | 6707988.52 | 6707988.52
ORA - ZED | 15 | 15 | ORA - ZED15 |  | 27710999.5475 | 424404904.8142 | 44651
EGAT Pelletizing Plant-MEP | 2 | 2 | EGAT Pelletizing Plant-MEP2 | 44614 | 112937.5 | 2124916
CFC | 28 | 28 | CFC28 | 44690 | 5026145.47 | 637419839.06
PKG#177 | 34 | 34 | PKG#17734 |  | 3016331.1152 | 188904459.8652 | 44713
Abo Ghaleb Bridge | 2 | 2 | Abo Ghaleb Bridge2 | 44627 | 3079766.7 | 15845653.7
MDF Factory | 9 | 9 | MDF Factory9 | 44658 | 8038787.77 | 105379097.21
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 44663 | 13671163.11 | 107668086.88
EGAT-Lock & Load | 2 | 2 | EGAT-Lock & Load2 | 44626 | 2362059.16 | 7380261.66
EGAT Pelletizing Plant-Water Tank | 10 | 10 | EGAT Pelletizing Plant-Water Tank10 | 44634 | 3540729.8 | 14494420.4
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 44644 | 28642092.8 | 28642092.8
HQ - CFC | 13 | 13 | HQ - CFC13 | 44648 | 23373232.3 | 150641096.8
ORA - ZED | 16 | 16 | ORA - ZED16 |  | 28676537.6669 | 453081442.4811 | 44663
ORA - ZED - ph.02 | 6 | 6 | ORA - ZED - ph.026 | 44691 | 23225104.4643 | 118120310.2353
Abo Ghaleb Bridge | 3 | 3 | Abo Ghaleb Bridge3 | 44655 | 3857104.5 | 19702758.2
ORA - ZED - ph.02 | 7 | 7 | ORA - ZED - ph.027 | 44780 | 42383851.5888 | 160504161.8242
ORA - ZED | 17 | 17 | ORA - ZED17 | 44692 | 31100661.1293 | 484182103.6103 | 44692
PKG#177 | 36 | 36 | PKG#17736 |  | 2649851.22 | 213241337.22 | 44777
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 44672 | 6522225.37 | 16737694.31
EGAT-Lock & Load | 3 | 3 | EGAT-Lock & Load3 | 44663 | 1772326.51 | 9152588.17
Rolling Mill #4-TRAESUEZ | 3 | 3 | Rolling Mill #4-TRAESUEZ3 | 44671 | 12117327 | 47177896.01
EGAT Pelletizing Plant-Water Tank | 11 | 11 | EGAT Pelletizing Plant-Water Tank11 | 44796 | 3753750.32 | 18248170.72
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 44672 | 14893958.07 | 122562044.95
PKG#177 | 37 | 37 | PKG#17737 | 44780 | 3201524.52 | 255757972.06 | 44787
MDF Factory | 10 | 10 | MDF Factory10 | 44678 | 6155129.99 | 111534227.2
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 44668 | 30329196.74 | 58971289.54
Abo Ghaleb Bridge | 4 | 4 | Abo Ghaleb Bridge4 | 44782 | 17739438 | 37442196.2
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 44704 | 8116943.05 | 130678988
Rolling Mill #4-TRAESUEZ | 4 | 4 | Rolling Mill #4-TRAESUEZ4 | 44698 | 8075015.79 | 55252911.8
ORA - ZED - ph.02 | 8 | 8 | ORA - ZED - ph.028 | 44719 | 8766077.2795 | 169270239.1037 | 44721
ORA - ZED | 18 | 18 | ORA - ZED18 | 44707 | 11112905.9801 | 495295009.5905 | 44707
PKG#163 | 24 | 24 | PKG#16324 |  | 5789760.2558 | 115718940.9358 | 44810
PKG#177 | 38 | 38 | PKG#17738 |  | -0.86 | 255757972.06 | 44788
PKG#177 - SWI 07 | 6 | 6 | PKG#177 - SWI 076 |  | 3141613.418 | 31868573.268
HQ - CFC | 15 | 15 | HQ - CFC15 | 44698 | 16353901 | 182179087
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 44712 | 5466647.24 | 22204341.55
MDF Factory | 11 | 11 | MDF Factory11 | 44719 | 9364100.8 | 120898328
Abo Ghaleb Bridge | 5 | 5 | Abo Ghaleb Bridge5 | 44794 | 2031888 | 39474084.2
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 44728 | 15323108.5333 | 15323108.5333
PKG#177 | 39 | 39 | PKG#17739 |  | -178832904.96 | 190000000 | 44837
PKG#163 | 25 | 25 | PKG#16325 |  | 22617186.6357 | 145615407.7057 | 44810
PKG#177 - SWI 07 | 7 | 7 | PKG#177 - SWI 077 |  | 10847798.8446 | 42716372.1126
Astoria Hotel | 5 | 5 | Astoria Hotel5 | 44740 | 3030560.1014 | 25234901.6514
EGAT-Lock & Load | 5 | 5 | EGAT-Lock & Load5 | 44719 | 3180176.34 | 13211888.51
EGAT Pelletizing Plant-MEP | 3 | 3 | EGAT Pelletizing Plant-MEP3 | 44969 | 1723067.19 | 3847983.19
ORA - ZED - ph.02 | 9 | 9 | ORA - ZED - ph.029 | 44746 | 8712415.4916 | 177982654.5953 | 44781
ORA - ZED | 19 | 19 | ORA - ZED19 | 44740 | 20070332.8941 | 515365342.4846 | 44740
Rolling Mill #4-TRAESUEZ | 5 | 5 | Rolling Mill #4-TRAESUEZ5 | 44748 | 9905844.43 | 65158756.23
MDF Factory | 12 | 12 | MDF Factory12 | 44741 | 27509389.27 | 148407717.27
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 44747 | 13958441.79 | 144637429.79
HQ - CFC | 16 | 16 | HQ - CFC16 | 44727 | 8911604.3 | 191090691.3
Astoria - Sharm | 2 | 2 | Astoria - Sharm2 | 44748 | 1243970 | 1243970
Astoria Hotel | 6 | 6 | Astoria Hotel6 | 44748 | 14829494.3486 | 40064396
HQ - CFC | 17 | 17 | HQ - CFC17 | 44760 | 17076484.2 | 208167175.5
PKG#163 | 26 | 26 | PKG#16326 |  | 20328767.6537 | 156256035.2837 | 44823
PKG#177 | 41 | 41 | PKG#17741 |  | -11904090.5837 | 421526736.2263 | 44887
ORA - ZED - ph.02 | 10 | 10 | ORA - ZED - ph.0210 | 44773 | 25761823.8629 | 203744478.4582 | 44795
MDF Factory | 13 | 13 | MDF Factory13 | 44780 | 15343913.47 | 163751630.74
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 44796 | 8283062.84 | 152920492.63
EGAT-Lock & Load | 6 | 6 | EGAT-Lock & Load6 | 44748 | 3378839.59 | 16590728.1
Rolling Mill #4-TRAESUEZ | 6 | 6 | Rolling Mill #4-TRAESUEZ6 | 44780 | 5743581.36 | 70902337.59
ORA - ZED | 20 | 20 | ORA - ZED20 | 44780 | 25297815.7756 | 540663158.2602 | 44801
Mivida-PK#189 | 2 | 2 | Mivida-PK#1892 | 44779 | 28497042.4952 | 43820151.0286
Sodic Eastown - Landscape | 8 | 8 | Sodic Eastown - Landscape8 | 44769 | 19106378.3905 | 46943391.219
MDF Factory - Equip. | 8 | 8 | MDF Factory - Equip.8 | 44775 | 340101.34 | 11819751.78
Astoria - Sharm | 3 | 3 | Astoria - Sharm3 | 44782 | 401082.65 | 1645052.65
Astoria Hotel | 7 | 7 | Astoria Hotel7 | 44781 | 11030217.63 | 51094613.63
HQ - CFC | 18 | 18 | HQ - CFC18 | 44790 | 15625697.2 | 223792872.7
Katameya - Creeks | 20 | 20 | Katameya - Creeks20 | 44794 | 23863809.78 | 737934504.85
ORA - ZED | 21 | 21 | ORA - ZED21 | 44805 | 9295356.7831 | 549958515.0433 | 44815
Ring Road - Mounib | 17 | 17 | Ring Road - Mounib17 | 44783 | 6933306.55 | 469868783
ORA - ZED - ph.02 | 11 | 11 | ORA - ZED - ph.0211 | 44798 | 10555360.8465 | 214299839.3048 | 44818
MDF Factory | 14 | 14 | MDF Factory14 | 44810 | 12301138.79 | 176052769.53 | 44829
EGAT-Lock & Load | 7 | 7 | EGAT-Lock & Load7 | 44789 | 1415984.07 | 18006712.17
Mivida-PK#189 | 3 | 3 | Mivida-PK#1893 | 44808 | 24279069.6762 | 68099220.7048
Rolling Mill #4-TRAESUEZ | 7 | 7 | Rolling Mill #4-TRAESUEZ7 | 44797 | 16796950.93 | 87699288.52
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 44797 | 20298475.01 | 173218967.64
Astoria Hotel | 8 | 8 | Astoria Hotel8 | 44812 | 14516248.37 | 65610862
Astoria - Sharm | 4 | 4 | Astoria - Sharm4 | 44809 | 2440310 | 4085362.65
Katameya - Creeks | 21 | 21 | Katameya - Creeks21 | 44824 | 37145495.17 | 775080000.02
ORA - ZED | 22 | 22 | ORA - ZED22 | 44819 | 9997079.1377 | 559955594.181 | 44832
MDF Factory | 15 | 15 | MDF Factory15 | 44843 | 8651043.7332 | 184308580.87
HQ - CFC | 19 | 19 | HQ - CFC19 | 44850 | 11070593.3 | 234863466
EGAT-Lock & Load | 8 | 8 | EGAT-Lock & Load8 | 44815 | 2786604.1 | 20793316.27
Rolling Mill #4-TRAESUEZ | 8 | 8 | Rolling Mill #4-TRAESUEZ8 | 44831 | 18519200.97 | 106218489.49
Ring Road - Mounib | 18 | 18 | Ring Road - Mounib18 | 44816 | 4715315.145 | 474584098.145
ORA - ZED - ph.02 | 12 | 12 | ORA - ZED - ph.0212 | 44843 | 16545380.5429 | 230845219.8476 | 44846
New Giza Hospital | 9 | 9 | New Giza Hospital9 | 44826 | 23318711.12 | 196318952.57
Mivida-PK#189 | 4 | 4 | Mivida-PK#1894 | 44843 | 28546026.8476 | 96645247.5524
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 44844 | 14282809.35 | 187501776.99
Astoria Hotel | 9 | 9 | Astoria Hotel9 | 44830 | 10555127.63 | 76165989.63
Astoria Hotel | 10 | 10 | Astoria Hotel10 | 44840 | 9739259.16 | 85905248.79
ORA - ZED - ph.02 | 13 | 13 | ORA - ZED - ph.0213 | 44856 | 20581919.2571 | 251427139.1048
ORA - ZED | 23 | 23 | ORA - ZED23 | 44861 | 27314036.0095 | 587269630.1905
Astoria - Sharm | 5 | 5 | Astoria - Sharm5 | 44840 | 1055208 | 5140570.65
Sodic Eastown - Landscape | 9 | 9 | Sodic Eastown - Landscape9 | 44817 | 2763176 | 49706567.219
MDF Factory | 16 | 16 | MDF Factory16 | 44871 | 21753082.06 | 206061662.93
New Giza Hospital | 10 | 10 | New Giza Hospital10 | 44868 | 22254898.64 | 218573851.21
EGAT-Lock & Load | 9 | 9 | EGAT-Lock & Load9 | 44852 | 3980460.75 | 24773777.02
HQ - CFC | 20 | 20 | HQ - CFC20 | 44845 | 43687204.7 | 278550670.7 | 44851
Rolling Mill #4-TRAESUEZ | 9 | 9 | Rolling Mill #4-TRAESUEZ9 | 44872 | 17686791.21 | 123905280.7
Mivida-PK#189 | 5 | 5 | Mivida-PK#1895 | 44870 | 57245166.7876 | 153890414.34
PKG#163 | 29 | 29 | PKG#16329 |  | 17622733.92 | 181831948.65 | 44941
Astoria Hotel | 11 | 11 | Astoria Hotel11 | 44865 | 22454296.86 | 108359545.65
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 44888 | 16943574.98 | 204445351.97
Astoria - Sharm | 6 | 6 | Astoria - Sharm6 | 44864 | 314831.49 | 5455402.14
EGAT-Lock & Load | 10 | 10 | EGAT-Lock & Load10 | 44868 | 1157252.56 | 25931029.58
Astoria Hotel | 12 | 12 | Astoria Hotel12 | 44875 | 7707398.94 | 116066944.59
Rolling Mill #4-TRAESUEZ | 10 | 10 | Rolling Mill #4-TRAESUEZ10 | 44909 | 15395023.2 | 139300303.9
HQ - CFC | 21 | 21 | HQ - CFC21 | 44885 | 6969185.9 | 285519856.6
ORA - ZED - ph.02 | 14 | 14 | ORA - ZED - ph.0214 | 44910 | 19311587.7934 | 270738726.8982
MDF Factory | 17 | 17 | MDF Factory17 | 44888 | 3503748.7 | 209565411.63
Sodic Eastown - Landscape | 10 | 10 | Sodic Eastown - Landscape10 | 44854 | 1723810.5333 | 51430377.7524 | 44854
Sodic Eastown - Landscape | 11 | 11 | Sodic Eastown - Landscape11 | 44872 | 1095191.5143 | 52525569.2667 | 44880
New Giza Hospital | 11 | 11 | New Giza Hospital11 | 44902 | 29701638.2 | 248275489.41
Sodic Eastown - Landscape | 12 | 12 | Sodic Eastown - Landscape12 | 44885 | 1256657.1048 | 55165083.5048 | 44887
Mivida-PK#189 | 6 | 6 | Mivida-PK#1896 | 44900 | -0.0001 | 153890414.34
Astoria Hotel | 13 | 13 | Astoria Hotel13 | 44893 | 11273556.71 | 127340501.3
6TH October tunnel | 4 | 4 | 6TH October tunnel4 | 44878 | 7663602.64 | 12262958.79 | 44879
6TH October tunnel | 5 | 5 | 6TH October tunnel5 | 44882 | 6157467.55 | 17807278.45 | 44890
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 44914 | 13727755.25 | 218173107.22
MDF Factory | 18 | 18 | MDF Factory18 | 44906 | 4093790.13 | 213659201.76
EGAT-Lock & Load | 11 | 11 | EGAT-Lock & Load11 | 44902 | 1992889.65 | 27923919.23
Mivida-PK#189 | 7 | 7 | Mivida-PK#1897 | 44900 | 39773865.3076 | 193664279.6476
Katameya - Creeks | 24 | 24 | Katameya - Creeks24 | 44921 | 30975620.82 | 858923356.91
ORA - ZED - ph.02 | 15 | 15 | ORA - ZED - ph.0215 | 44915 | 14179983.4542 | 284918710.3524
New Giza Hospital | 12 | 12 | New Giza Hospital12 | 44924 | 25988546.64 | 274264036.05
Rolling Mill #4-TRAESUEZ | 11 | 11 | Rolling Mill #4-TRAESUEZ11 | 44943 | 16145745 | 155446048.9
Astoria Hotel | 14 | 14 | Astoria Hotel14 | 44915 | 13597376.25 | 140937877.55
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 44915 | 2611606.8286 | 2611606.8286
MDF Factory | 19 | 19 | MDF Factory19 | 44923 | 12077854.33 | 225737056.09
Wady Halfa | 1 | 1 | Wady Halfa1 | 44913 | 3078932.9 | 3078932.9
HQ - CFC | 24 | 24 | HQ - CFC24 | 44922 | 25568878.3 | 320704119.6
Mivida-PK#189 | 8 | 8 | Mivida-PK#1898 | 44927 | 90047890.8024 | 283712170.45
ORA - ZED | 24 | 24 | ORA - ZED24 | 44976 | 11751887.1042 | 599021517.2946 | 45007
MDF Factory | 20 | 20 | MDF Factory20 | 44938 | 10662163.65 | 236399219.74
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 44971 | 20329650.19 | 238502757.41
Astoria Hotel | 15 | 15 | Astoria Hotel15 | 44951 | 9032753.11 | 149970630.66
EGAT-Lock & Load | 12 | 12 | EGAT-Lock & Load12 | 44923 | 1778896.47 | 29702815.7
Katameya - Creeks | 25 | 25 | Katameya - Creeks25 | 44951 | 21870157.41 | 880793514.32
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 44959 | 3199345.21 | 3199345.21
ORA - ZED - ph.02 | 16 | 16 | ORA - ZED - ph.0216 | 44962 | 11487525.8247 | 296406236.1771
ORA - ZED - Landscape | 2 | 2 | ORA - ZED - Landscape2 | 44958 | 2071867.5333 | 4683474.3619
HQ - CFC | 25 | 25 | HQ - CFC25 | 44956 | 17887580.019 | 338591699.619
ORA - ZED | 25 | 25 | ORA - ZED25 | 45026 | 50310527.2958 | 649332044.5905
Mivida-PK#189 | 9 | 9 | Mivida-PK#1899 | 44950 | 42271935.09 | 325984105.54
New Giza Hospital | 13 | 13 | New Giza Hospital13 | 44963 | 24670486.27 | 298934522.32
Royal City | 42 | 42 | Royal City42 | 44970 | 7571387.8468 | 419210431.34
Rolling Mill #4-TRAESUEZ | 12 | 12 | Rolling Mill #4-TRAESUEZ12 | 44964 | 16694409.39 | 172140458.29
MDF Factory | 21 | 21 | MDF Factory21 | 44963 | 18933899.86 | 255333119.6
ORA - ZED - Landscape | 3 | 3 | ORA - ZED - Landscape3 | 44983 | 2138801.7905 | 6822276.1524
ORA - ZED - ph.02 | 17 | 17 | ORA - ZED - ph.0217 | 44994 | 9516947.0875 | 305923183.2647 | 45004
Port Said Silos - Local Supply | 1 | 1 | Port Said Silos - Local Supply1 | 45001 | 673851.6 | 673851.6
EGAT-Lock & Load | 13 | 13 | EGAT-Lock & Load13 | 44964 | 2116780.43 | 31819596.13
DPW - Ph.02 | 1 | 1 | DPW - Ph.021 | 44973 | 23907099.3 | 23907099.3
Katameya - Creeks | 26 | 26 | Katameya - Creeks26 | 44985 | 41254688.36 | 922048202.68
Mivida-PK#189 | 10 | 10 | Mivida-PK#18910 | 44983 | 29038558.46 | 355022664
HQ - CFC | 26 | 26 | HQ - CFC26 | 45337 | 15848994.2857 | 354440693.9048
MDF Factory | 22 | 22 | MDF Factory22 | 44982 | 3256087.31 | 258589206.91
Astoria Hotel | 16 | 16 | Astoria Hotel16 | 44982 | 9372213.83 | 159342844.49
New Giza Hospital | 14 | 14 | New Giza Hospital14 | 44999 | 21692266.85 | 320626789.17
Rolling Mill #4-TRAESUEZ | 13 | 13 | Rolling Mill #4-TRAESUEZ13 | 44993 | 14485776.58 | 186626234.87
Wady Halfa | 2 | 2 | Wady Halfa2 | 44971 | 23601516.1 | 26680449
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 45048 | 1797569.47 | 4996914.68
PKG#177 | 47 | 47 | PKG#17747 | 45141 | 21331767.9853 | 575446386.2553 | 45141
LEKELA | 16 | 16 | LEKELA16 | 45016 | -0.0001 | 207000000
ORA - ZED - ph.02 | 18 | 18 | ORA - ZED - ph.0218 | 45014 | 15495416.059 | 321418599.3237 | 45034
ORA - ZED - Landscape | 4 | 4 | ORA - ZED - Landscape4 | 45026 | 4909563.9143 | 11731840.0667
EIPICO | 4 | 4 | EIPICO4 | 45000 | 8374674.1725 | 42276520.7525
EGAT-Lock & Load | 14 | 14 | EGAT-Lock & Load14 | 44993 | 2768145.62 | 34587741.75
MDF Factory | 23 | 23 | MDF Factory23 | 45007 | 38888289.8 | 297477496.71
New Gas Station | 1 | 1 | New Gas Station1 | 45232 | 3190160 | 3190160
Mivida-PK#189 | 11 | 11 | Mivida-PK#18911 | 45026 | 23000800.56 | 378023464.56
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 45007 | 30365704.8 | 54272804.1
Astoria Hotel | 17 | 17 | Astoria Hotel17 | 45018 | 7818140.35 | 167160984.84
New Giza Hospital | 15 | 15 | New Giza Hospital15 | 45034 | 23725978.81 | 344352767.98
Wady Halfa | 3 | 3 | Wady Halfa3 | 45001 | 17962793.18 | 44643242.18
EIPICO | 5 | 5 | EIPICO5 | 45026 | 13210447.2775 | 55486968.03
Port Said Silos | 13 | 13 | Port Said Silos13 | 45018 | 612060.8329 | 80860263.08
MDF Factory | 24 | 24 | MDF Factory24 | 45046 | 18681389.16 | 316158885.87
DPW - Ph.02 | 3 | 3 | DPW - Ph.023 | 45012 | 1809093.47 | 56081897.57
Katameya - Creeks | 28 | 28 | Katameya - Creeks28 | 45050 | 26373696.19 | 972370839.89
ORA - ZED - ph.02 | 19 | 19 | ORA - ZED - ph.0219 | 45047 | 8053943.7501 | 329472543.0738
ORA - ZED - Landscape | 5 | 5 | ORA - ZED - Landscape5 | 45047 | 3861209.6 | 15593049.6667
Mivida-PK#189 | 12 | 12 | Mivida-PK#18912 | 45054 | 15682494.86 | 393705959.42
ORA - ZED | 26 | 26 | ORA - ZED26 | 45047 | 19434003.5361 | 668766048.1265
New Giza Hospital | 16 | 16 | New Giza Hospital16 | 45060 | 22492246.1 | 366845014.08
EIPICO | 6 | 6 | EIPICO6 | 45063 | 6910722.77 | 62397690.8
DPW - Ph.02 | 4 | 4 | DPW - Ph.024 | 45085 | 38567084.81 | 94648982.38
Katameya - Creeks | 29 | 29 | Katameya - Creeks29 | 45080 | 23994845.49 | 996365685.38
Mivida-PK#189 | 13 | 13 | Mivida-PK#18913 | 45083 | 16636045.76 | 410342005.18
ORA - ZED - Landscape | 6 | 6 | ORA - ZED - Landscape6 | 45084 | 3232045.3524 | 18825095.019
ORA - ZED - ph.02 | 20 | 20 | ORA - ZED - ph.0220 | 45078 | 4423045.841 | 333895588.9148
ORA - ZED | 27 | 27 | ORA - ZED27 | 45092 | 10662740.4195 | 679428788.546
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 45090 | 1174788.1 | 1174788.1
DPW - Ph.02 | 5 | 5 | DPW - Ph.025 | 45102 | 77833745.07 | 172482727.45
New Giza Hospital | 17 | 17 | New Giza Hospital17 | 45111 | 21612019.52 | 388457033.6
ORA - ZED - ph.02 | 21 | 21 | ORA - ZED - ph.0221 | 45116 | 4766150.0798 | 338661738.9946 | 45152
Astoria Hotel | 19 | 19 | Astoria Hotel19 | 45096 | 12873774.1358 | 190455674.5258
MDF Factory | 26 | 26 | MDF Factory26 | 45098 | 21011393.06 | 347654910.69
Mivida-PK#140 | 28 | 28 | Mivida-PK#14028 | 45365 | 924591.9704 | 174986240.73 | 45482
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 |  | 2879525.92 | 7876440.6
KSA-Tarek AbdelHakim Center | 2 | 2 | KSA-Tarek AbdelHakim Center2 | 45090 | 2619891.03 | 3794679.13
Mivida-PK#189 | 14 | 14 | Mivida-PK#18914 | 45122 | 22729528.92 | 433071534.1
Creeks - URBN K | 3 | 3 | Creeks - URBN K3 | 45095 | 40661954.88 | 71628367.6
ORA - ZED - Landscape | 7 | 7 | ORA - ZED - Landscape7 | 45124 | 1440674.7619 | 20265769.781
ORA - ZED | 28 | 28 | ORA - ZED28 | 45116 | 24304667.5968 | 703733456.1429
KSA-Tarek AbdelHakim Center | 3 | 3 | KSA-Tarek AbdelHakim Center3 | 45132 | 1124829.43 | 4919508.56
DPW - Ph.02 | 6 | 6 | DPW - Ph.026 | 45138 | 32227821.34 | 204710548.79
MDF Factory | 27 | 27 | MDF Factory27 | 45119 | 10160280.74 | 357815191.43
EIPICO | 8 | 8 | EIPICO8 | 45132 | 24151774.29 | 88477871.42 | 45169
ORA - ZED - Landscape | 8 | 8 | ORA - ZED - Landscape8 | 45147 | 11600772.2694 | 31866542.0504
Katameya - Creeks | 31 | 31 | Katameya - Creeks31 | 45138 | 34090513.58 | 1112307883.94
ORA - ZED - ph.02 | 22 | 22 | ORA - ZED - ph.0222 | 45147 | 11000140.3008 | 349661879.2913
New Giza Hospital | 18 | 18 | New Giza Hospital18 | 45144 | 9332664.78 | 397789698.38
Astoria Hotel | 20 | 20 | Astoria Hotel20 | 45140 | 3956219.0142 | 194411893.54
ORA - ZED | 29 | 29 | ORA - ZED29 | 45162 | 27532348.019 | 731265804.1619
MDF Factory | 28 | 28 | MDF Factory28 | 45138 | 4632219.77 | 362447411.2
Mivida-PK#189 | 15 | 15 | Mivida-PK#18915 | 45145 | 18379426.49 | 451450960.59
KSA-Tarek AbdelHakim Center | 4 | 4 | KSA-Tarek AbdelHakim Center4 | 45132 | 1181749.35 | 6101257.91
SMP1 - Revamp | 4 | 4 | SMP1 - Revamp4 | 45170 | 3836789.63 | 11713230.23
DPW - Ph.02 | 7 | 7 | DPW - Ph.027 | 45166 | 21546507.22 | 226257056.01
Astoria Hotel | 21 | 21 | Astoria Hotel21 | 45183 | 1422437.2 | 195834330.74
MDF Factory | 29 | 29 | MDF Factory29 | 45179 | 7201895.8 | 369649307
ORA - ZED - Landscape | 9 | 9 | ORA - ZED - Landscape9 | 45186 | 3994751.4353 | 35861293.4857
ORA - ZED - ph.02 | 23 | 23 | ORA - ZED - ph.0223 | 45186 | 1051681.4414 | 350713560.7327
New Giza Hospital | 19 | 19 | New Giza Hospital19 | 45183 | 18985757.51 | 416775455.89
ORA - ZED | 30 | 30 | ORA - ZED30 | 45186 | 26015241.1905 | 757281045.3524
Creeks - URBN K | 5 | 5 | Creeks - URBN K5 | 45161 | 21068069.1 | 118665999.82
Mivida-PK#189 | 16 | 16 | Mivida-PK#18916 | 45189 | 24459783.7762 | 475910744.3662
EIPICO | 10 | 10 | EIPICO10 | 45166 | 9818518.79 | 133296390.21 | 45228
Royal City - Landscape | 24 | 24 | Royal City - Landscape24 | 45173 | 3256136.08 | 110218542.31
Royal City | 43 | 43 | Royal City43 | 45173 | 13484961.26 | 432695392.6
DPW - Ph.02 | 8 | 8 | DPW - Ph.028 | 45173 | 27781672.69 | 254038728.7
EIPICO | 11 | 11 | EIPICO11 | 45209 | 27259074.64 | 160555464.85 | 45258
ORA - ZED - ph.02 | 24 | 24 | ORA - ZED - ph.0224 | 45186 | 1619984.7524 | 352333545.4851
MDF Factory | 30 | 30 | MDF Factory30 | 45188 | 42878737.92 | 412528044.92
Katameya - Creeks | 33 | 33 | Katameya - Creeks33 | 45200 | 61801377.92 | 1210803657.22
SMP1 - Revamp | 5 | 5 | SMP1 - Revamp5 | 45181 | 4135898.1 | 15849128.33
Creeks - URBN K | 6 | 6 | Creeks - URBN K6 | 45196 | 18829649.55 | 137495649.37
ORA - ZED | 31 | 31 | ORA - ZED31 | 45196 | 26102241.2286 | 783383286.581
ORA - ZED - Landscape | 10 | 10 | ORA - ZED - Landscape10 | 45209 | 3258480.2857 | 39119773.7714
MDF Factory - Local Fabrication | 15 | 15 | MDF Factory - Local Fabrication15 | 45278 | 5403242.47 | 47293093.98
DPW - Ph.02 | 9 | 9 | DPW - Ph.029 | 45230 | 66926760.56 | 320965489.26
MDF Factory | 31 | 31 | MDF Factory31 | 45206 | 26984773 | 439512817.92
EIPICO | 12 | 12 | EIPICO12 | 45251 | 13086699.85 | 173642164.7 | 45293
ORA - ZED - Landscape | 11 | 11 | ORA - ZED - Landscape11 | 45234 | 6742108.1048 | 45861881.8762
Katameya - Creeks | 34 | 34 | Katameya - Creeks34 | 45232 | 67431952.34 | 1278235609.56
ORA - ZED - ph.02 | 25 | 25 | ORA - ZED - ph.0225 | 45237 | 1429470.734 | 353763016.219
New Giza Hospital | 20 | 20 | New Giza Hospital20 | 45202 | -1e-07 | 416775455.89
Astoria Hotel | 22 | 22 | Astoria Hotel22 | 45208 | 13661357.26 | 209495688 | 45213
ORA - ZED | 32 | 32 | ORA - ZED32 | 45241 | 24532813.9714 | 807916100.5524
MDF Factory | 32 | 32 | MDF Factory32 | 45225 | 2754000 | 442266817.92
Mivida-PK#189 | 17 | 17 | Mivida-PK#18917 | 45216 | 30434807.7338 | 506345552.1
Port Said Silos | 20 | 20 | Port Said Silos20 | 45231 | 13732229.2267 | 152603544.64 | 45252
DPW - Ph.02 | 10 | 10 | DPW - Ph.0210 | 45259 | 59028304.35 | 379993793.61
Astoria Hotel | 23 | 23 | Astoria Hotel23 | 45253 | 13277404.55 | 219912624
MDF Factory | 33 | 33 | MDF Factory33 | 45255 | 20665276.54 | 462932094.46
Katameya - Creeks | 35 | 35 | Katameya - Creeks35 | 45266 | 61247331.12 | 1339482940.68
ORA - ZED - Landscape | 12 | 12 | ORA - ZED - Landscape12 | 45250 | 9303031.3714 | 55164913.2476
ORA - ZED - ph.02 | 26 | 26 | ORA - ZED - ph.0226 | 45274 | 3475331.4095 | 357238347.6286
ORA - ZED | 33 | 33 | ORA - ZED33 | 45277 | 20642302.219 | 828558402.7714
Mivida-PK#189 | 18 | 18 | Mivida-PK#18918 | 45262 | 18563752.6 | 524909304.7
Sokhna Port Expansion | 20 | 20 | Sokhna Port Expansion20 | 45224 | 20920498.28 | 877286055.98 | 45250
New Giza Hospital | 21 | 21 | New Giza Hospital21 | 45215 | 12758386.3 | 429533842.19
Sokhna Port Expansion- 100m | 5 | 5 | Sokhna Port Expansion- 100m5 | 45224 | 4703266.4897 | 126862233.53 | 45250
Baraka Land Fence | 1 | 1 | Baraka Land Fence1 | 45236 | 3575400 | 3575400
New Giza Hospital | 22 | 22 | New Giza Hospital22 | 45260 | 18598623.84 | 448132466.03
Sokhna Port Expansion | 21 | 21 | Sokhna Port Expansion21 | 45287 | 9034186.8 | 886320242.78 | 45287
SMP1 - Revamp | 7 | 7 | SMP1 - Revamp7 | 45251 | 4571797.25 | 29278987.27
Port Said Silos | 21 | 21 | Port Said Silos21 | 45260 | 15886446.6567 | 167746546.07 | 45283
DPW - Ph.02 | 11 | 11 | DPW - Ph.0211 | 45291 | 54711779.1 | 434705572.71
EIPICO | 13 | 13 | EIPICO13 | 45281 | 50645387.03 | 224287551.73 | 45292
Mivida-PK#189 | 19 | 19 | Mivida-PK#18919 | 45293 | 21710553.3095 | 546619858.0095
MDF Factory | 34 | 34 | MDF Factory34 | 45280 | 25469525.62 | 488401620.08
Katameya - Creeks | 36 | 36 | Katameya - Creeks36 | 45290 | 74463161.12 | 1413946101.8
New Giza Hospital | 23 | 23 | New Giza Hospital23 | 45318 | 9056705.71 | 457189171.74
Port Said Silos | 22 | 22 | Port Said Silos22 | 45274 | 6713332.669 | 174459878.73 | 45287
ORA - ZED | 34 | 34 | ORA - ZED34 | 45319 | 14702199.581 | 843260602.3524
ORA - ZED - ph.02 | 27 | 27 | ORA - ZED - ph.0227 | 45305 | 3041219.2755 | 360279566.9041
MDF Factory - Equip. | 21 | 21 | MDF Factory - Equip.21 | 45285 | 540952.41 | 22578347.52 | 45328
KSA-Tarek AbdelHakim Center | 11 | 11 | KSA-Tarek AbdelHakim Center11 | 45295 | 6272151.58 | 34906557.56
MDF Factory | 35 | 35 | MDF Factory35 | 45312 | 7460561 | 495862181.08
DPW - Ph.02 | 12 | 12 | DPW - Ph.0212 | 45326 | 17644384.08 | 452349956.79
Mivida-PK#189 | 20 | 20 | Mivida-PK#18920 | 45302 | -0.0003 | 546619858.0095
Mivida-PK#189 | 21 | 21 | Mivida-PK#18921 | 45315 | 22586754.7048 | 569206612.7143
EIPICO | 14 | 14 | EIPICO14 | 45326 | 69127444.9 | 293414996.63 | 45358
Katameya - Creeks | 37 | 37 | Katameya - Creeks37 | 45313 | 53331460.14 | 1467277561.94
ORA - ZED | 35 | 35 | ORA - ZED35 | 45333 | 13918410.7524 | 857179013.1048
Creeks - URBN K | 10 | 10 | Creeks - URBN K10 | 45326 | 21707049.44 | 217734751.99 | 45366
ORA - ZED - ph.02 | 28 | 28 | ORA - ZED - ph.0228 | 45354 | 5861894.8952 | 366141461.7993
ORA - ZED - Landscape | 13 | 13 | ORA - ZED - Landscape13 | 45342 | -692002.6286 | 54472910.619
ORA - ZED - Landscape | 14 | 14 | ORA - ZED - Landscape14 | 45371 | 1197004.6952 | 55669915.3143
EIPICO | 15 | 15 | EIPICO15 | 45371 | 41894786.25 | 335309782.88
Mivida-PK#189 | 22 | 22 | Mivida-PK#18922 | 45349 | 23140993.5357 | 592347606.25
MDF Factory | 36 | 36 | MDF Factory36 | 45350 | 24220349.75 | 520082530.83
ORA - ZED - Landscape | 15 | 15 | ORA - ZED - Landscape15 | 45402 | 3753240.219 | 59423155.5333
Katameya - Creeks | 38 | 38 | Katameya - Creeks38 | 45357 | 83842743.6 | 1551120305.54
ORA - ZED | 36 | 36 | ORA - ZED36 | 45363 | 9427629.6762 | 866606642.781
ORA - ZED - ph.02 | 29 | 29 | ORA - ZED - ph.0229 | 45385 | 2577878.9747 | 368719340.774 | 45397
New Giza Hospital | 24 | 24 | New Giza Hospital24 | 45383 | 30645299.93 | 487834471.67
Creeks - URBN K | 11 | 11 | Creeks - URBN K11 | 45361 | 19399852.91 | 247787306.4
Rabigh Ext. - Piles | 1 | 1 | Rabigh Ext. - Piles1 | 45369 | 1098993.1 | 1098993.1
Mivida-PK#189 | 23 | 23 | Mivida-PK#18923 | 45403 | 30858954.27 | 623206560.52
ORA - ZED - Landscape | 16 | 16 | ORA - ZED - Landscape16 | 45381 | 1773392.8381 | 61196548.3714
DPW - Ph.02 | 13 | 13 | DPW - Ph.0213 | 45383 | 13655091.11 | 466005047.9
Katameya - Creeks | 39 | 39 | Katameya - Creeks39 | 45384 | 81688930.92 | 1632809236.46
MDF Factory | 37 | 37 | MDF Factory37 | 45384 | 18799337.86 | 538881868.69
ORA - ZED | 37 | 37 | ORA - ZED37 | 45388 | 11141064.9524 | 877747707.7333 | 45406
Port Said Silos - Local Supply | 3 | 3 | Port Said Silos - Local Supply3 | 45364 | 3085091.6309 | 4953919.88 | 45382
DPW - Ph.02 | 14 | 14 | DPW - Ph.0214 | 45426 | -0.0001 | 466005047.9
Creeks - URBN K | 12 | 12 | Creeks - URBN K12 | 45385 | 13939506.69 | 261726813.09
ORA - ZED - ph.02 | 30 | 30 | ORA - ZED - ph.0230 | 45385 | 2066668.4036 | 370786009.1777 | 45411
EIPICO | 16 | 16 | EIPICO16 | 45406 | 54812520.11 | 390122302.99
New Giza Hospital | 25 | 25 | New Giza Hospital25 | 45296 | 12955562.12 | 500790033.79
ORA - ZED - Landscape | 17 | 17 | ORA - ZED - Landscape17 | 45419 | 1582674.7048 | 62779223.0762 | 45410
ORA - ZED | 38 | 38 | ORA - ZED38 | 45421 | 15909843.4381 | 893657551.1714
MDF Factory | 38 | 38 | MDF Factory38 | 45406 | 25264630.57 | 564146499.26
Port Said Silos - Local Supply | 4 | 4 | Port Said Silos - Local Supply4 | 45389 | 4365732.3293 | 9319652.21 | 45419
ORA - ZED - ph.02 | 31 | 31 | ORA - ZED - ph.0231 | 45419 | 7992050.6 | 378778059.7777 | 45427
Mivida-PK#189 | 24 | 24 | Mivida-PK#18924 | 45434 | 16112816.1181 | 639319376.6381
Port Said Silos | 27 | 27 | Port Said Silos27 | 45413 | 1478728.71 | 191022414.13 | 45439
Rabigh Ext. - Piles | 2 | 2 | Rabigh Ext. - Piles2 | 45414 | 1361202.3 | 2460195.4
ORA - ZED - Landscape | 18 | 18 | ORA - ZED - Landscape18 | 45426 | 1979868.8571 | 64759091.9333
ORA - ZED - ph.02 | 32 | 32 | ORA - ZED - ph.0232 | 45448 | 2766734.981 | 381544794.7714
MDF Factory | 39 | 39 | MDF Factory39 | 45434 | 17461783.47 | 581608282.73
Katameya - Creeks | 41 | 41 | Katameya - Creeks41 | 45437 | 47455342.03 | 1746847240.53
ORA - ZED | 39 | 39 | ORA - ZED39 | 45449 | 9971577.2286 | 903629128.4
Mivida-PK#189 | 25 | 25 | Mivida-PK#18925 | 45449 | 29437278.3119 | 668756654.95
New Giza Hospital | 26 | 26 | New Giza Hospital26 | 45456 | 15191903.43 | 515981937.22
EIPICO | 17 | 17 | EIPICO17 | 45456 | 30260072.01 | 420382375
Port Said Silos - Local Supply | 5 | 5 | Port Said Silos - Local Supply5 | 45424 | 3278709.276 | 12598361.49 | 45439
Port Said Silos | 28 | 28 | Port Said Silos28 | 45445 | 3335653.5067 | 194402004.06 | 45474
ORA - ZED - Landscape | 19 | 19 | ORA - ZED - Landscape19 | 45480 | 1453055.0476 | 66212146.981
ORA - ZED - ph.02 | 33 | 33 | ORA - ZED - ph.0233 | 45474 | 6575447.0667 | 388120241.8381
ORA - ZED | 40 | 40 | ORA - ZED40 | 45474 | 7576454.8952 | 911205583.2952
Katameya - Creeks | 42 | 42 | Katameya - Creeks42 | 45480 | 56995945.47 | 1803843186
Port Said Silos - Local Supply | 6 | 6 | Port Said Silos - Local Supply6 | 45452 | 1064669.3953 | 13663030.89 | 45474
Rabigh Ext. - Piles | 4 | 4 | Rabigh Ext. - Piles4 | 45481 | 2071949.5 | 5652409
Creeks - URBN K | 15 | 15 | Creeks - URBN K15 | 45455 | 15151516.49 | 306639839.44
Baraka Land Fence | 4 | 4 | Baraka Land Fence4 | 45433 | 11760884 | 49997280
SMP1 - Revamp | 10 | 10 | SMP1 - Revamp10 | 45447 | 5011477.79 | 38750521.78
Mivida-PK#189 | 26 | 26 | Mivida-PK#18926 | 45476 | 16876594.42 | 685633249.37
EIPICO | 18 | 18 | EIPICO18 | 45503 | 61471115.83 | 481853490.83
ORA - ZED - ph.02 | 34 | 34 | ORA - ZED - ph.0234 | 45510 | 1412666.8095 | 389532908.6476
ORA - ZED - Landscape | 20 | 20 | ORA - ZED - Landscape20 | 45496 | 1399335.6857 | 67611482.6667
MDF Factory | 42 | 42 | MDF Factory42 | 45497 | 750284.2 | 608911678.68
Port Said Silos | 29 | 29 | Port Said Silos29 | 45481 | 2063726.5038 | 196509667 | 45511
Mivida-PK#189 | 27 | 27 | Mivida-PK#18927 | 45505 | 14919836.13 | 700553085.5
Katameya - Creeks | 43 | 43 | Katameya - Creeks43 | 45500 | 56437240.4362 | 1860280426.4362
Creeks - URBN K | 16 | 16 | Creeks - URBN K16 | 45502 | 8934038.52 | 315573877.96
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 45435 | 3172518.7149 | 3172518.7149
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 45525 | 2298644.2851 | 5471163
New Giza Hospital | 27 | 27 | New Giza Hospital27 | 45522 | 16227230.2 | 532209167.42
ORA - ZED | 41 | 41 | ORA - ZED41 | 45535 | 4542501.819 | 915748085.1143
Port Said Silos - Local Supply | 7 | 7 | Port Said Silos - Local Supply7 | 45491 | 5552464.1105 | 19215495 | 45510
Mivida-PK#189 | 28 | 28 | Mivida-PK#18928 | 45535 | 3487392.66 | 704040478.16
Rabigh Ext. -Building | 2 | 2 | Rabigh Ext. -Building2 | 45529 | 5727560.34 | 8289315.69
Port Said Silos | 30 | 30 | Port Said Silos30 | 45509 | 3191369.04 | 199701036.04 | 45526
MDF Factory | 43 | 43 | MDF Factory43 | 45525 | 11210135.32 | 620121814
ORA - ZED | 42 | 42 | ORA - ZED42 | 45536 | 5377971.181 | 921126056.2952
ORA - ZED - ph.02 | 35 | 35 | ORA - ZED - ph.0235 | 45535 | 7262978.339 | 396795886.9866
Katameya - Creeks | 44 | 44 | Katameya - Creeks44 | 45535 | 49427006.6938 | 1909707433.13
Creeks - URBN K | 17 | 17 | Creeks - URBN K17 | 45540 | 8615746.66 | 324189624.62
ORA - ZED - Landscape | 21 | 21 | ORA - ZED - Landscape21 | 45540 | 422349.9905 | 68033832.6571
ORA - ZED - ph.02 | 36 | 36 | ORA - ZED - ph.0236 | 45540 | 0.003893 | 396795886.9905
EIPICO | 19 | 19 | EIPICO19 | 45557 | 35463786.17 | 517317277 | 45591
Red Sea Museum | 3 | 3 | Red Sea Museum3 | 45537 | 1331566 | 6802729
MDF Factory | 44 | 44 | MDF Factory44 | 45561 | 10205950.6 | 630327764.6
ORA - ZED - Landscape | 22 | 22 | ORA - ZED - Landscape22 | 45551 | 4226377.8476 | 72260210.5048
ORA - ZED - ph.02 | 37 | 37 | ORA - ZED - ph.0237 | 45572 | 12000518.9238 | 408796405.9143
ORA - ZED | 43 | 43 | ORA - ZED43 | 45557 | 11538786.4 | 932664842.6952
Rabigh Ext. -Building | 3 | 3 | Rabigh Ext. -Building3 | 45554 | 5121658.33 | 13410974.02
Creeks - URBN K | 18 | 18 | Creeks - URBN K18 | 45560 | 9557078 | 333746702.62
Baraka Land Fence | 5 | 5 | Baraka Land Fence5 | 45524 | 7617134 | 57614414
New Giza Hospital | 28 | 28 | New Giza Hospital28 | 45568 | 69437921.36 | 601647088.78
Mivida-PK#189 | 29 | 29 | Mivida-PK#18929 | 45561 | 369049.79 | 704409527.95
ORA - ZED - ph.02 | 38 | 38 | ORA - ZED - ph.0238 | 45572 | -0.0095238 | 408796405.9048
ORA - ZED - ph.02 | 39 | 39 | ORA - ZED - ph.0239 | 45605 | 13783192.8762 | 422579598.781
ORA - ZED | 44 | 44 | ORA - ZED44 | 45580 | 5304711.9524 | 937969554.6476
ORA - ZED - Landscape | 23 | 23 | ORA - ZED - Landscape23 | 45580 | 1124749.1714 | 73384959.6762
Rabigh Ext. -Building | 4 | 4 | Rabigh Ext. -Building4 | 45588 | 6246650.22 | 19657624.24
MDF Factory | 45 | 45 | MDF Factory45 | 45600 | 16259922.8 | 646587687.4
Katameya - Creeks | 46 | 46 | Katameya - Creeks46 | 45600 | 42454238 | 2019963202
Creeks - URBN K | 19 | 19 | Creeks - URBN K19 | 45598 | 6248543.66 | 339995246.28
Mivida-PK#189 | 30 | 30 | Mivida-PK#18930 | 45608 | 17653522.66 | 722063050.61

## consultant-net (hidden)
Project | Invoice No. | invoice round down | concact | Approval Date (By Consultant) | Monthly Amount Approved (By Consultant)
PK #107 | 9 | 9 | PK #1079 | 43061 | 1418090.5
JICA | 19 | 19 | JICA19 | 43038 | 1141675.91
FIEM | 210 | 210 | FIEM210 | 43031 | 1524934.13
Cement Plant | 15 | 15 | Cement Plant15 | 43054 | 6696657.1239
PI Parks - ELSEWEDY | 1 | 1 | PI Parks - ELSEWEDY1 | 43038 | 5549711.3149
PI Parks - ELSEWEDY | 2 | 2 | PI Parks - ELSEWEDY2 | 43061 | 4153538.7944
Sodic Club House | 24 | 24 | Sodic Club House24 | 43065 | 4713913.05
Royal City | 2 | 2 | Royal City2 | 43019 | 5203476.09
Royal City | 3 | 3 | Royal City3 | 43048 | 8396278.07
Uptown PK #62 | 8 | 8 | Uptown PK #628 | 43047 | 2970870.89
Uptown PK #53 | 25 | 25 | Uptown PK #5325 | 43052 | 12023138.6423
Uptown PK #53 | 26 | 26 | Uptown PK #5326 | 43088 | 12833527.9648
PK #107 | 10 | 10 | PK #10710 | 43093 | 1453205.39
PI Parks - ELSEWEDY | 3 | 3 | PI Parks - ELSEWEDY3 | 43092 | 1754857.27
Uptown PK #62 | 9 | 9 | Uptown PK #629 | 43087 | 2124952.16
Sodic Club House | 25 | 25 | Sodic Club House25 | 43106 | 1796642.04
SIEMENS - Sokhna | 2 | 2 | SIEMENS - Sokhna2 | 43116 | 3059283.73
PK #107 | 11 | 11 | PK #10711 | 43115 | 2604921.36
Uptown PK #62 | 10 | 10 | Uptown PK #6210 | 43118 | 2207449.91
Uptown PK #53 | 27 | 27 | Uptown PK #5327 | 43108 | 9723398.7945
Royal City | 5 | 5 | Royal City5 | 43122 | 6381832.9445
PI Parks - ELSEWEDY | 4 | 4 | PI Parks - ELSEWEDY4 | 43131 | 3155027.6241
Sodic Club House | 26 | 26 | Sodic Club House26 | 43138 | 3193789.29
Uptown PK #53 | 28 | 28 | Uptown PK #5328 | 43135 | 7567160.0657
Uptown PK #62 | 11 | 11 | Uptown PK #6211 | 43138 | 1516852.746
PI Parks - ELSEWEDY | 5 | 5 | PI Parks - ELSEWEDY5 | 43170 | 1692874.42
SIEMENS - Sokhna | 3 | 3 | SIEMENS - Sokhna3 | 43136 | 7201577.05
PK #117 | 2 | 2 | PK #1172 | 43152 | 6466420.97
Uptown PK #53 | 29 | 29 | Uptown PK #5329 | 43157 | 10749580.8339
NGU 2 | 26 | 26 | NGU 226 | 43131 | 3027155.9789
Uptown PK #62 | 12 | 12 | Uptown PK #6212 | 43177 | 1565019.15
Sodic Club House | 27 | 27 | Sodic Club House27 | 43169 | 4891559.01
SIEMENS - Sokhna | 4 | 4 | SIEMENS - Sokhna4 | 43173 | 11065687.7
PK #117 | 3 | 3 | PK #1173 | 43173 | 4502026.52
PI Parks - ELSEWEDY | 6 | 6 | PI Parks - ELSEWEDY6 | 43201 | 306624.33
PK #107 | 13 | 13 | PK #10713 | 43192 | 2462800.95
Uptown PK #53 | 30 | 30 | Uptown PK #5330 | 43188 | 9526356.8077
Sodic Club House | 28 | 28 | Sodic Club House28 | 43194 | 4314232.28
Uptown PK #62 | 13 | 13 | Uptown PK #6213 | 43208 | 3417923.56
PK #117 | 4 | 4 | PK #1174 | 43200 | 3740180.271
Royal City | 6 | 6 | Royal City6 | 43214 | 11493260.03
PI Parks - ELSEWEDY | 7 | 7 | PI Parks - ELSEWEDY7 | 43211 | 1938615.93
SIEMENS - Sokhna | 5 | 5 | SIEMENS - Sokhna5 | 43205 | 13218163.55
PK #107 | 14 | 14 | PK #10714 | 43219 | 166316.41
Mintra | 1 | 1 | Mintra1 | 43361 | 2860852.09
Uptown PK #53 | 31 | 31 | Uptown PK #5331 | 43220 | 6774937.5373
PK #117 | 5 | 5 | PK #1175 | 43227 | 4762507.55
Royal City | 7 | 7 | Royal City7 | 43242 | 8439569.37
PK #107 | 15 | 15 | PK #10715 | 43241 | 1406606.27
SIEMENS - Sokhna | 6 | 6 | SIEMENS - Sokhna6 | 43240 | 7060448.908
PI Parks - ELSEWEDY | 8 | 8 | PI Parks - ELSEWEDY8 | 43237 | 1633991.6379
Uptown PK #53 | 32 | 32 | Uptown PK #5332 | 43249 | 2387351.5744
Al Jazi | 1 | 1 | Al Jazi1 | 43249 | 2462056.64
PK #117 | 6 | 6 | PK #1176 | 43272 | 5347404.79
Royal City | 8 | 8 | Royal City8 | 43275 | 7600061.0338
SIEMENS - Sokhna | 7 | 7 | SIEMENS - Sokhna7 | 43285 | 8833159.82
PI Parks - ELSEWEDY | 9 | 9 | PI Parks - ELSEWEDY9 | 43263 | 1607545.8276
Uptown PK #53 | 33 | 33 | Uptown PK #5333 | 43284 | 3964599.8564
PI Parks - ELSEWEDY | 10 | 10 | PI Parks - ELSEWEDY10 | 43303 | 3824599.4146
PK #117 | 7 | 7 | PK #1177 | 43464 | 119713.18
Al Jazi | 2 | 2 | Al Jazi2 | 43262 | 3686157.94
SIEMENS - Sokhna | 8 | 8 | SIEMENS - Sokhna8 | 43300 | 12641621.4
Sodic Club House | 31 | 31 | Sodic Club House31 | 43305 | 4843252.93
Al Jazi | 3 | 3 | Al Jazi3 | 43292 | 3748572.21
Royal City | 9 | 9 | Royal City9 | 43307 | 6018082.2865
Uptown PK #53 | 34 | 34 | Uptown PK #5334 | 43307 | 1431626.0807
Al Jazi | 4 | 4 | Al Jazi4 | 43305 | 4444997.23
Mintra | 2 | 2 | Mintra2 | 43366 | 1791407.73
Sodic Club House | 32 | 32 | Sodic Club House32 | 43328 | 5655167.4
PI Parks - ELSEWEDY | 11 | 11 | PI Parks - ELSEWEDY11 | 43320 | 442152.4951
SIEMENS - Sokhna | 9 | 9 | SIEMENS - Sokhna9 | 43346 | 13673026.82
PSP Substation | 3 | 3 | PSP Substation3 | 43384 | 1834172.07
Royal City | 10 | 10 | Royal City10 | 43339 | 5554331.9836
Al Jazi | 5 | 5 | Al Jazi5 | 43325 | 4854984.5363
Uptown PK #62 | 15 | 15 | Uptown PK #6215 | 43349 | 2299870.97
Uptown PK #53 | 35 | 35 | Uptown PK #5335 | 43355 | 2488623.0127
Al Jazi | 6 | 6 | Al Jazi6 | 43353 | 2965400.21
Sodic Club House | 33 | 33 | Sodic Club House33 | 43368 | 7190786.09
PI Parks - ELSEWEDY | 12 | 12 | PI Parks - ELSEWEDY12 | 43369 | 1530660.1341
El Sewedy Uni.-PKG.1 | 1 | 1 | El Sewedy Uni.-PKG.11 | 43388 | 2002513.1
SIEMENS - Sokhna | 10 | 10 | SIEMENS - Sokhna10 | 43368 | 6271528.33
Royal City | 11 | 11 | Royal City11 | 43367 | 3237608.64
Uptown PK #53 | 36 | 36 | Uptown PK #5336 | 43376 | 4689979.7631
Mintra | 3 | 3 | Mintra3 | 43388 | 2220782.14
PK #107 | 17 | 17 | PK #10717 | 43394 | 763627.7
El Sewedy Uni.-PKG.2 | 1 | 1 | El Sewedy Uni.-PKG.21 | 43391 | 3110956.56
PI Parks - MEP | 1 | 1 | PI Parks - MEP1 | 43383 | 7818631.64
SIEMENS - Sokhna | 11 | 11 | SIEMENS - Sokhna11 | 43409 | 5230123.66
Al Jazi | 7 | 7 | Al Jazi7 | 43383 | 5019788.5
PI Parks - ELSEWEDY | 13 | 13 | PI Parks - ELSEWEDY13 | 43383 | 716605.5327
Royal City | 12 | 12 | Royal City12 | 43397 | 7860724.87
Uptown PK #62 | 16 | 16 | Uptown PK #6216 | 43429 | 931895.88
Sodic Club House | 34 | 34 | Sodic Club House34 | 43404 | 10029446.47
Mintra-Hanger 1200m2 | 1 | 1 | Mintra-Hanger 1200m21 | 43402 | 531998.6721
El Sewedy Uni.-PKG.1 | 2 | 2 | El Sewedy Uni.-PKG.12 | 43398 | 951383.3
Uptown PK #53 | 37 | 37 | Uptown PK #5337 | 43450 | 1753673.2424
Mintra | 4 | 4 | Mintra4 | 43422 | 2907075.5801
Al Jazi | 8 | 8 | Al Jazi8 | 43410 | 7730375.21
Royal City | 13 | 13 | Royal City13 | 43425 | 5548576.504
PI Parks - ELSEWEDY | 14 | 14 | PI Parks - ELSEWEDY14 | 43419 | 1986968.45
PI Parks - MEP | 2 | 2 | PI Parks - MEP2 | 43419 | 3978690.02
El Sewedy Uni.-PKG.1 | 3 | 3 | El Sewedy Uni.-PKG.13 | 43431 | 1214989.1272
El Sewedy Uni.-PKG.2 | 2 | 2 | El Sewedy Uni.-PKG.22 | 43412 | 6088678.96
Al Jazi | 9 | 9 | Al Jazi9 | 43432 | 3297350.06
El Sewedy Uni.-PKG.1 | 4 | 4 | El Sewedy Uni.-PKG.14 | 43444 | 1204112.8596
Royal City | 14 | 14 | Royal City14 | 43463 | 13062023.4527
PK #117 | 8 | 8 | PK #1178 | 43464 | 3896343.98
PI Parks - MEP | 3 | 3 | PI Parks - MEP3 | 43449 | 4042223.64
PI Parks - ELSEWEDY | 15 | 15 | PI Parks - ELSEWEDY15 | 43449 | 5773335.65
El Sewedy Uni.-PKG.1 | 5 | 5 | El Sewedy Uni.-PKG.15 | 43452 | 185635.0557
Al Jazi | 10 | 10 | Al Jazi10 | 43453 | 3398127.58
Al Jazi | 11 | 11 | Al Jazi11 | 43473 | 4227710.49
El Sewedy Uni.-PKG.2 | 4 | 4 | El Sewedy Uni.-PKG.24 | 43475 | 3208255.2815
PKG#144 | 2 | 2 | PKG#1442 | 43485 | 2532120.6
El Sewedy Uni.-PKG.1 | 6 | 6 | El Sewedy Uni.-PKG.16 | 43473 | 142702.1677
PK #117 | 9 | 9 | PK #1179 | 43495 | 2578109.66
Sodic Club House | 35 | 35 | Sodic Club House35 | 43434 | 6956090.906
PI Parks - MEP | 4 | 4 | PI Parks - MEP4 | 43479 | 3514249.7617
PI Parks - ELSEWEDY | 16 | 16 | PI Parks - ELSEWEDY16 | 43479 | 5768808.1936
DP World Sokhna-AP | 1 | 1 | DP World Sokhna-AP1 | 43472 | 241563831.68
Royal City | 15 | 15 | Royal City15 | 43485 | 9343372.736
SIEMENS - Sokhna | 16 | 16 | SIEMENS - Sokhna16 | 43485 | 25271545.73
El Sewedy Uni.-PKG.1 | 7 | 7 | El Sewedy Uni.-PKG.17 | 43487 | 284879.76
Uptown PK #53 | 38 | 38 | Uptown PK #5338 | 43514 | 1048789.58
Al Jazi | 12 | 12 | Al Jazi12 | 43500 | 2264521.51
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 43544 | 6785088.5699
PK #117 | 10 | 10 | PK #11710 | 43506 | 147972.1048
PKG#101 | 1 | 1 | PKG#1011 | 43508 | 1124562.5468
El Sewedy Uni.-PKG.2 | 5 | 5 | El Sewedy Uni.-PKG.25 | 43506 | 4527299.6695
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 43514 | 1727255.5662
El Sewedy Uni.-PKG.1 | 8 | 8 | El Sewedy Uni.-PKG.18 | 43502 | 235901.6556
PI Parks - MEP | 5 | 5 | PI Parks - MEP5 | 43512 | 6241537.12
SIEMENS - Sokhna | 17 | 17 | SIEMENS - Sokhna17 | 43577 | 20418831.59
PI Parks - ELSEWEDY | 17 | 17 | PI Parks - ELSEWEDY17 | 43512 | 3296251.57
Royal City | 16 | 16 | Royal City16 | 43521 | 10141562.9942
Al Jazi | 13 | 13 | Al Jazi13 | 43528 | 3848045.61
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 43515 | 3185421.0011
El Sewedy Uni.-PKG.2 | 6 | 6 | El Sewedy Uni.-PKG.26 | 43535 | 7457797.2
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 43536 | 5785718.6
PI Parks - MEP | 6 | 6 | PI Parks - MEP6 | 43541 | 2455515.29
PKG#101 | 2 | 2 | PKG#1012 | 43543 | 2222206.65
Royal City | 17 | 17 | Royal City17 | 43556 | 6226878.8549
PI Parks - ELSEWEDY | 18 | 18 | PI Parks - ELSEWEDY18 | 43541 | 5638741.9194
Al Jazi | 14 | 14 | Al Jazi14 | 43563 | 1995238.89
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 43563 | 909309.25
El Sewedy Uni.-PKG.1 | 9 | 9 | El Sewedy Uni.-PKG.19 | 43565 | 72777.3
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 43565 | 1785483.1
PI Parks - MEP | 7 | 7 | PI Parks - MEP7 | 43572 | 4844170.7079
PSP Substation | 10 | 10 | PSP Substation10 | 43578 | 3808343.08
Royal City | 18 | 18 | Royal City18 | 43573 | 6196039.396
Uptown PK #53 | 39 | 39 | Uptown PK #5339 | 43576 | 929614.0301
El Sewedy Uni.-PKG.2 | 7 | 7 | El Sewedy Uni.-PKG.27 | 43565 | 2278076.6
PKG#101 | 3 | 3 | PKG#1013 | 43578 | 2379437.34
PI Parks - ELSEWEDY | 19 | 19 | PI Parks - ELSEWEDY19 | 43572 | 4754946.3629
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 43573 | 15652355.21
El Sewedy Uni.-PKG.3 | 5 | 5 | El Sewedy Uni.-PKG.35 | 43590 | 24218860.6
PI Parks - MEP | 8 | 8 | PI Parks - MEP8 | 43604 | 1686090.7908
SIEMENS - Sokhna | 18 | 18 | SIEMENS - Sokhna18 |  | 15000000
Al Jazi | 15 | 15 | Al Jazi15 | 43594 | 2738501.15
PI Parks - ELSEWEDY | 20 | 20 | PI Parks - ELSEWEDY20 | 43604 | 1816746.614
Royal City | 19 | 19 | Royal City19 | 43608 | 10933183.0202
Al Jazi | 16 | 16 | Al Jazi16 | 43617 | 1009779.23
Al Jazi - Center Zone | 2 | 2 | Al Jazi - Center Zone2 | 43614 | 2035039.03
PKG#101 | 4 | 4 | PKG#1014 | 43614 | 2512749.68
Sodic Eastown | 3 | 3 | Sodic Eastown3 | 43608 | 1574016.17
El Sewedy Uni.-PKG.2 | 8 | 8 | El Sewedy Uni.-PKG.28 | 43684 | 2625161.5
El Sewedy Uni.-PKG.3 | 6 | 6 | El Sewedy Uni.-PKG.36 | 43632 | 26656864.3
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 43643 | 2533668.0255
Royal City | 20 | 20 | Royal City20 | 43642 | 5643448.8191
Uptown PK #53 | 40 | 40 | Uptown PK #5340 | 43662 | 1435222.17
PI Parks - ELSEWEDY | 21 | 21 | PI Parks - ELSEWEDY21 | 43751 | 5879272.6391
PI Parks - MEP | 9 | 9 | PI Parks - MEP9 | 43751 | 5081340.66
Al Jazi | 17 | 17 | Al Jazi17 | 43652 | 3577364.85
Sodic Eastown | 4 | 4 | Sodic Eastown4 | 43654 | 26267292.44
PKG#101 | 5 | 5 | PKG#1015 | 43670 | 2051541.96
Sodic Club House | 36 | 36 | Sodic Club House36 |  | 7000000
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 43667 | 2620895.13
NGU 2 | 27 | 27 | NGU 227 |  | 2440072.7285
Royal City | 21 | 21 | Royal City21 | 43664 | 5151160.3487
El Sewedy Uni.-PKG.3 | 7 | 7 | El Sewedy Uni.-PKG.37 | 43671 | 22410862.51
Al Jazi | 18 | 18 | Al Jazi18 | 43673 | 3297235.7
Al Jazi - Center Zone | 3 | 3 | Al Jazi - Center Zone3 | 43673 | 1152186.95
Sodic Eastown | 5 | 5 | Sodic Eastown5 | 43678 | 22056568.4027
Mivida-PK#140 | 3 | 3 | Mivida-PK#1403 | 43697 | 4070832.3885
Royal City | 22 | 22 | Royal City22 | 43710 | 17540056.799
PKG#101 | 6 | 6 | PKG#1016 | 43705 | 1988552.05
Royal City - Landscape | 1 | 1 | Royal City - Landscape1 |  | 1800000
El Sewedy Uni.-PKG.3 | 8 | 8 | El Sewedy Uni.-PKG.38 | 43701 | 13598061.6
El Sewedy Uni.-PKG.1 | 10 | 10 | El Sewedy Uni.-PKG.110 | 43684 | -8913.92
Sodic Eastown | 6 | 6 | Sodic Eastown6 | 43716 | 28554847.68
Uptown PK #53 | 41 | 41 | Uptown PK #5341 | 43697 | 4202366.45
Al Jazi | 19 | 19 | Al Jazi19 | 43718 | 4336532.29
Al Jazi - Center Zone | 4 | 4 | Al Jazi - Center Zone4 | 43718 | 1090291.72
El Sewedy Uni.-PKG.3 | 9 | 9 | El Sewedy Uni.-PKG.39 | 43705 | 19410255.3
PK #117 | 12 | 12 | PK #11712 | 43733 | 3376348.1
Mivida-PK#140 | 4 | 4 | Mivida-PK#1404 | 43725 | 999645.4398
PKG#144 | 12 | 12 | PKG#14412 | 43741 | 22411649.36
Royal City | 23 | 23 | Royal City23 | 43736 | 4319851.8787
Royal City - Landscape | 2 | 2 | Royal City - Landscape2 | 43733 | 4032037.5
PKG#101 | 7 | 7 | PKG#1017 | 43729 | 1794285.02
El Sewedy Uni.-PKG.3 | 10 | 10 | El Sewedy Uni.-PKG.310 | 43737 | 20919758.8
Sodic Eastown | 7 | 7 | Sodic Eastown7 | 43746 | 38890621.0473
Mivida-PK#140 | 5 | 5 | Mivida-PK#1405 | 43761 | 1337507.07
Al Jazi | 20 | 20 | Al Jazi20 | 43772 | 2000000
Al Jazi - Center Zone | 5 | 5 | Al Jazi - Center Zone5 | 43772 | 1000000
Royal City | 24 | 24 | Royal City24 | 43762 | 10214838.0645
Royal City - Landscape | 3 | 3 | Royal City - Landscape3 | 43761 | 2443214.8875
PKG#101 | 8 | 8 | PKG#1018 | 43772 | 2127121.14
PK #117 | 13 | 13 | PK #11713 | 43781 | 3145779.21
Sodic Eastown | 8 | 8 | Sodic Eastown8 | 43783 | 58794871.95
Royal City | 25 | 25 | Royal City25 | 43796 | 12249365.624
Royal City - Landscape | 4 | 4 | Royal City - Landscape4 | 43824 | 4441415.442
Mivida-PK#140 | 6 | 6 | Mivida-PK#1406 | 43789 | 10719905.2391
HyperOne | 1 | 1 | HyperOne1 | 43793 | 2673900.95
PKG#101 | 9 | 9 | PKG#1019 | 43802 | 1424816.56
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | PH.2-El Sewedy Uni. - Enabling1 | 43810 | 2841415.8
Mivida-PK#140 | 7 | 7 | Mivida-PK#1407 | 43818 | 6547225.8223
HyperOne | 2 | 2 | HyperOne2 | 43811 | 8554552.61
Royal City | 26 | 26 | Royal City26 | 43835 | 7456675.6367
Royal City - Landscape | 5 | 5 | Royal City - Landscape5 | 43835 | 7147476.0332
CFC-DP | 1 | 1 | CFC-DP1 | 43842 | 62134944.55
PKG#101 | 10 | 10 | PKG#10110 | 43828 | 1948071.2
CFC | 1 | 1 | CFC1 | 43842 | 6200445.37
Uptown PK #62 | 19 | 19 | Uptown PK #6219 | 43944 | 1195853.88
PH.2-El Sewedy Uni. - Enabling | 2 | 2 | PH.2-El Sewedy Uni. - Enabling2 | 43841 | 13446882.5
HyperOne | 3 | 3 | HyperOne3 | 43843 | 7194819.7145
Mivida-PK#140 | 8 | 8 | Mivida-PK#1408 | 43858 | 4740517.5525
Sodic Eastown | 10 | 10 | Sodic Eastown10 | 43856 | 36785436.36
CFC | 2 | 2 | CFC2 | 43872 | 17323666.18
Royal City | 27 | 27 | Royal City27 | 43871 | 14587648.3106
Royal City - Landscape | 6 | 6 | Royal City - Landscape6 | 43871 | 9619287.67
El-Gouna - Equip. Rental | 1 | 1 | El-Gouna - Equip. Rental1 | 43863 | 73813.12
El-Gouna - Temp. Fence | 1 | 1 | El-Gouna - Temp. Fence1 | 43891 | 429660
Al Jazi | 21 | 21 | Al Jazi21 | 43914 | 5243962.1948
CFC | 3 | 3 | CFC3 | 43901 | 12263695.26
HyperOne | 4 | 4 | HyperOne4 | 43874 | 7092200.1311
PH.2-El Sewedy Uni. - Enabling | 3 | 3 | PH.2-El Sewedy Uni. - Enabling3 | 43866 | 17089175.5
PKG#101 | 11 | 11 | PKG#10111 | 43874 | 2026574.82
Mivida-PK#140 | 9 | 9 | Mivida-PK#1409 | 43884 | 4559999.0726
Al Jazi - Center Zone | 6 | 6 | Al Jazi - Center Zone6 | 43914 | -2446690.14
HyperOne | 5 | 5 | HyperOne5 | 43884 | 3307335
Royal City | 28 | 28 | Royal City28 | 43906 | 10986396.5553
Royal City - Landscape | 7 | 7 | Royal City - Landscape7 | 43906 | 6246175.7955
El-Gouna | 5 | 5 | El-Gouna5 | 43884 | 1815739.6
HyperOne | 6 | 6 | HyperOne6 | 43897 | 8598545.1487
Mivida-PK#140 | 10 | 10 | Mivida-PK#14010 | 43950 | 5679423.0614
Sodic Eastown | 12 | 12 | Sodic Eastown12 | 43919 | 19553108.77
PH.2-El Sewedy Uni. - Enabling | 4 | 4 | PH.2-El Sewedy Uni. - Enabling4 | 43906 | 14773850.7
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 43912 | 35636298.9
CFC | 4 | 4 | CFC4 | 43923 | 32660833.58
El-Gouna | 6 | 6 | El-Gouna6 | 43908 | 6823693.4
HyperOne | 7 | 7 | HyperOne7 | 43913 | 8896507
CFC | 5 | 5 | CFC5 | 43943 | 24749111.95
Mivida-PK#140 | 11 | 11 | Mivida-PK#14011 | 43950 | 2647674.1799
Royal City | 29 | 29 | Royal City29 | 43926 | 13166441.5288
Royal City - Landscape | 8 | 8 | Royal City - Landscape8 | 43926 | 12899186.0747
El Sewedy Uni.-PKG.2 | 9 | 9 | El Sewedy Uni.-PKG.29 | 43913 | 1116423.1
PKG#101 | 12 | 12 | PKG#10112 | 43929 | 1146998.22
PH.2-El Sewedy Uni. - Enabling | 5 | 5 | PH.2-El Sewedy Uni. - Enabling5 | 43930 | 2392694.9
Sodic Eastown | 13 | 13 | Sodic Eastown13 | 43943 | 19217788.54
HyperOne | 8 | 8 | HyperOne8 | 43933 | 3400669
PH.2-El Sewedy Uni. - Finishes | 2 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 43943 | 26758389.8
CFC | 6 | 6 | CFC6 | 43955 | 31500278.62
Royal City | 30 | 30 | Royal City30 | 43956 | 9831952.135
Royal City - Landscape | 9 | 9 | Royal City - Landscape9 | 43956 | 4988413.7416
HyperOne | 9 | 9 | HyperOne9 | 43947 | 1277872
El-Gouna | 7 | 7 | El-Gouna7 | 43942 | 2158979.11
PH.2-El Sewedy Uni. - Enabling | 6 | 6 | PH.2-El Sewedy Uni. - Enabling6 | 43957 | 7788095.2
Mivida-PK#140 | 12 | 12 | Mivida-PK#14012 | 43972 | 4687303.4253
PH.2-El Sewedy Uni. - Finishes | 3 | 3 | PH.2-El Sewedy Uni. - Finishes3 | 43970 | 23262698.8
CFC | 7 | 7 | CFC7 | 43986 | 19510038
Royal City - Landscape | 10 | 10 | Royal City - Landscape10 | 44014 | 3101056.0064
Royal City | 31 | 31 | Royal City31 | 44014 | 7550426.1692
HyperOne | 10 | 10 | HyperOne10 | 43983 | 4810581.9155
PH.2-El Sewedy Uni. - Enabling | 7 | 7 | PH.2-El Sewedy Uni. - Enabling7 | 44023 | 3548357.4
CFC | 8 | 8 | CFC8 | 44019 | 21459124.497
PH.2-El Sewedy Uni. - Finishes | 4 | 4 | PH.2-El Sewedy Uni. - Finishes4 | 44000 | 18322601
HyperOne | 11 | 11 | HyperOne11 | 44005 | 6700151
Royal City | 32 | 32 | Royal City32 | 44020 | 2648440.2256
Royal City - Landscape | 11 | 11 | Royal City - Landscape11 | 44020 | 3973857.736
El Sewedy Uni.-PKG.3 | 12 | 12 | El Sewedy Uni.-PKG.312 | 44003 | 1515470
PK #117 | 14 | 14 | PK #11714 | 44082 | 2238761.46
CFC | 9 | 9 | CFC9 | 44039 | 24499895.52
HyperOne | 12 | 12 | HyperOne12 | 44023 | 1896314.4172
El-Gouna | 8 | 8 | El-Gouna8 | 44018 | 1933855.68
Mivida-PK#140 | 14 | 14 | Mivida-PK#14014 | 44033 | 7336701.0997
PH.2-El Sewedy Uni. - Enabling | 8 | 8 | PH.2-El Sewedy Uni. - Enabling8 | 44021 | 1607563.1
PH.2-El Sewedy Uni. - Finishes | 5 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 44025 | 64006362.8
Royal City | 33 | 33 | Royal City33 | 44055 | 9101413.8171
Royal City - Landscape | 12 | 12 | Royal City - Landscape12 | 44055 | 7029456.4155
PH.2-El Sewedy Uni. - Finishes | 6 | 6 | PH.2-El Sewedy Uni. - Finishes6 | 44041 | 8883254.2
PH.2-El Sewedy Uni. - Enabling | 9 | 9 | PH.2-El Sewedy Uni. - Enabling9 | 44070 | 8526565.2
CFC | 10 | 10 | CFC10 | 44069 | 39448595.5711
Mivida-PK#140 | 15 | 15 | Mivida-PK#14015 | 44067 | 10305723.5244
HyperOne | 13 | 13 | HyperOne13 | 44062 | 6738701.3468
Royal City - Landscape | 13 | 13 | Royal City - Landscape13 | 44081 | 2173267.6157
Royal City | 34 | 34 | Royal City34 | 44088 | 5373442.9261
PH.2-El Sewedy Uni. - Finishes | 7 | 7 | PH.2-El Sewedy Uni. - Finishes7 | 44069 | 30755604.9
Sodic Eastown | 17 | 17 | Sodic Eastown17 | 44065 | 22896073.3381
CFC | 11 | 11 | CFC11 | 44103 | 18030565.73
Mivida-PK#140 | 16 | 16 | Mivida-PK#14016 | 44089 | 10553431.2394
HyperOne | 14 | 14 | HyperOne14 | 44087 | 4476191
PH.2-El Sewedy Uni. - Finishes | 8 | 8 | PH.2-El Sewedy Uni. - Finishes8 | 44091 | 30127325.7
Royal City | 35 | 35 | Royal City35 | 44109 | 3237336.5863
Royal City - Landscape | 14 | 14 | Royal City - Landscape14 | 44109 | 1308214.7555
HyperOne | 15 | 15 | HyperOne15 | 44447 | 2800899.62
Mivida-PK#140 | 17 | 17 | Mivida-PK#14017 | 44123 | 11726998.4266
Royal City | 36 | 36 | Royal City36 | 44132 | 4982664.9588
Royal City - Landscape | 15 | 15 | Royal City - Landscape15 | 44132 | 2303900.245
CFC | 12 | 12 | CFC12 | 44139 | 29691194.9757
PH.2-El Sewedy Uni. - Finishes | 9 | 9 | PH.2-El Sewedy Uni. - Finishes9 | 44124 | 20493846
AEON | 2 | 2 | AEON2 | 44147 | 1610113.5212
CFC | 13 | 13 | CFC13 | 44174 | 23213755.7909
Royal City | 37 | 37 | Royal City37 | 44161 | 5574033.5344
Mivida-PK#140 | 18 | 18 | Mivida-PK#14018 | 44164 | 3831058.93
Royal City - Landscape | 16 | 16 | Royal City - Landscape16 | 44161 | 869369.6486
PH.2-El Sewedy Uni. - Finishes | 10 | 10 | PH.2-El Sewedy Uni. - Finishes10 | 44154 | 9765894.8
ORA - ZED | 1 | 1 | ORA - ZED1 | 44213 | 10345156.8
CFC | 14 | 14 | CFC14 | 44207 | 19708944.2711
PKG#101 | 15 | 15 | PKG#10115 | 44182 | 1392185.4448
Mivida-PK#140 | 19 | 19 | Mivida-PK#14019 | 44186 | 8885358.6191
Royal City | 38 | 38 | Royal City38 | 44201 | 3838809.8865
Royal City - Landscape | 17 | 17 | Royal City - Landscape17 | 44201 | 1883835.4255
PH.2-El Sewedy Uni. - Finishes | 11 | 11 | PH.2-El Sewedy Uni. - Finishes11 | 44186 | 13851401.2
AEON | 3 | 3 | AEON3 | 44200 | 780253.0677
ORA - ZED | 2 | 2 | ORA - ZED2 | 44202 | 37827388.6601
Mivida-PK#140 | 20 | 20 | Mivida-PK#14020 | 44231 | 5084359.8248
CFC | 15 | 15 | CFC15 | 44249 | 40379659.8985
Royal City - Landscape | 18 | 18 | Royal City - Landscape18 | 44230 | 819297.0816
Royal City | 39 | 39 | Royal City39 | 44230 | 1002773.1926
PKG#144 | 16 | 16 | PKG#14416 | 44256 | 1132971.99
ORA - ZED | 3 | 3 | ORA - ZED3 | 44244 | 28404325.826
CFC | 16 | 16 | CFC16 | 44276 | 22871121.15
Mivida-PK#140 | 21 | 21 | Mivida-PK#14021 | 44244 | 8185193.8344
HQ - CFC | 1 | 1 | HQ - CFC1 | 44249 | 6847513.7311
Royal City - Landscape | 19 | 19 | Royal City - Landscape19 | 44257 | 1116339.8935
PH.2-El Sewedy Uni. - Finishes | 12 | 12 | PH.2-El Sewedy Uni. - Finishes12 | 44271 | 26122387
CFC | 17 | 17 | CFC17 | 44280 | 15047803.36
CFC | 18 | 18 | CFC18 | 44292 | 12196441.11
ORA - ZED | 4 | 4 | ORA - ZED4 | 44279 | 21185755.528
HQ - CFC | 2 | 2 | HQ - CFC2 | 44277 | 8021127.94
Sodic Eastown | 24 | 24 | Sodic Eastown24 | 44284 | 17436083.38
Royal City | 40 | 40 | Royal City40 | 44298 | 5979686.6716
Royal City - Landscape | 20 | 20 | Royal City - Landscape20 | 44298 | 1105876.6944
CFC | 19 | 19 | CFC19 | 44306 | 14008565.71
CFC | 20 | 20 | CFC20 | 44340 | 23721354.77
ORA - ZED | 5 | 5 | ORA - ZED5 | 44339 | 35278804.6637
HQ - CFC | 3 | 3 | HQ - CFC3 | 44301 | 8213719.76
Mivida-PK#140 | 23 | 23 | Mivida-PK#14023 | 44327 | 1458682.9494
HQ - CFC | 4 | 4 | HQ - CFC4 | 44342 | 7815807.64
CFC | 21 | 21 | CFC21 | 44364 | 17156225.13
CFC | 22 | 22 | CFC22 | 44376 | 13410069.82
ORA - ZED | 6 | 6 | ORA - ZED6 | 44343 | 4544122.0162
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 44362 | 4887819.25
EGAT Pelletizing Plant-Water Tank | 1 | 1 | EGAT Pelletizing Plant-Water Tank1 | 44369 | 3438202.99
Royal City | 41 | 41 | Royal City41 | 44501 | 5714023.3138
PH.2-El Sewedy Uni. - Finishes | 13 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 44678 | 19693398.5
Royal City - Landscape | 21 | 21 | Royal City - Landscape21 | 44390 | 3011690.98
EGAT Pelletizing Plant-MEP | 1 | 1 | EGAT Pelletizing Plant-MEP1 | 44433 | 2112577.42
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 44389 | 10124222.67
CFC | 23 | 23 | CFC23 | 44426 | 15440458.92
Katameya - Creeks | 7 | 7 | Katameya - Creeks7 | 44404 | 44596069.78
PKG#178 | 6 | 6 | PKG#1786 |  | 4030279.0303
EGAT Pelletizing Plant-Water Tank | 2 | 2 | EGAT Pelletizing Plant-Water Tank2 | 44389 | 2130019.28
CFC | 24 | 24 | CFC24 | 44462 | 7464840.35
PKG#177 | 18 | 18 | PKG#17718 | 44440 | 15056356.09
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 44427 | 4165165.88
EGAT Pelletizing Plant-Water Tank | 3 | 3 | EGAT Pelletizing Plant-Water Tank3 | 44427 | 761625.75
PKG#177 | 19 | 19 | PKG#17719 |  | -0.001
PKG#177 | 20 | 20 | PKG#17720 |  | -0.001
ORA - ZED | 9 | 9 | ORA - ZED9 | 44448 | 26728065.13
CFC | 25 | 25 | CFC25 | 44494 | 9682524.47
PKG#177 | 21 | 21 | PKG#17721 |  | -0.0001
Ring Road - Mounib | 9 | 9 | Ring Road - Mounib9 |  | 3856121.55
Ring Road - Mounib | 10 | 10 | Ring Road - Mounib10 |  | 12662306
PKG#177 | 22 | 22 | PKG#17722 |  | -0.0001
EGAT Pelletizing Plant-Water Tank | 4 | 4 | EGAT Pelletizing Plant-Water Tank4 | 44444 | 804482.15
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 44466 | 6104444.17
Ring Road - Mounib | 11 | 11 | Ring Road - Mounib11 | 44446 | 19857247.187
CFC | 26 | 26 | CFC26 | 44518 | 2397254.3033
HQ - CFC | 7 | 7 | HQ - CFC7 | 44448 | 14942810.8492
PKG#177 | 23 | 23 | PKG#17723 |  | -0.0001
Ring Road - El Marg | 7 | 7 | Ring Road - El Marg7 |  | 25237352
ORA - ZED | 10 | 10 | ORA - ZED10 | 44465 | 29047725.55
PKG#177 | 24 | 24 | PKG#17724 |  | -0.0001
Royal City - Landscape | 22 | 22 | Royal City - Landscape22 | 44501 | 2526109.9
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 44489 | 14109093.06
EGAT Pelletizing Plant-Water Tank | 5 | 5 | EGAT Pelletizing Plant-Water Tank5 | 44481 | 969774.05
PKG#177 | 25 | 25 | PKG#17725 |  | -0.0001
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 44482 | 14536703.8371
HQ - CFC | 8 | 8 | HQ - CFC8 | 44482 | 10059001.5
Ring Road - Mounib | 12 | 12 | Ring Road - Mounib12 | 44485 | 14886673.24
Kafr Shokr | 7 | 7 | Kafr Shokr 7 |  | 25823994.7095
CFC | 27 | 27 | CFC27 | 44522 | 10793868.55
PKG#177 | 26 | 26 | PKG#17726 |  | -0.0001
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 44514 | 10385277.48
EGAT Pelletizing Plant-Water Tank | 6 | 6 | EGAT Pelletizing Plant-Water Tank6 | 44509 | 1537532.43
HQ - CFC | 9 | 9 | HQ - CFC9 | 44511 | 17174919.86
Royal City - Landscape | 23 | 23 | Royal City - Landscape23 | 44970 | 15313915.32
Ring Road - Mounib | 13 | 13 | Ring Road - Mounib13 | 44513 | 41814387.46
Sports Hall - Finishes | 3 | 3 | Sports Hall - Finishes3 | 44517 | 77278617
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 44514 | 20471935.8674
PKG#162 | 15 | 15 | PKG#16215 | 44613 | 3683579.28
Kafr Shokr | 8 | 8 | Kafr Shokr 8 | 44555 | 2028646.62
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 44579 | 9325143.2186
HQ - CFC | 10 | 10 | HQ - CFC10 | 44546 | 7981881.9284
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 44550 | 13304274.45
EGAT Pelletizing Plant-Water Tank | 7 | 7 | EGAT Pelletizing Plant-Water Tank7 | 44539 | 419715.76
PKG#177 | 27 | 27 | PKG#17727 |  | -0.0001
PKG#177 - SWI 07 | 1 | 1 | PKG#177 - SWI 071 |  | 1800000
MDF Factory | 6 | 6 | MDF Factory6 | 44581 | 17171193.3155
Sports Hall - Civil Works | 7 | 7 | Sports Hall - Civil Works7 |  | 12888184
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 44570 | 28860252.4316
PKG#177 - SWI 07 | 2 | 2 | PKG#177 - SWI 072 |  | 4300000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 44579 | 11576342.49
EGAT Pelletizing Plant-Water Tank | 8 | 8 | EGAT Pelletizing Plant-Water Tank8 | 44567 | 322587.51
HQ - CFC | 11 | 11 | HQ - CFC11 | 44578 | 17417402.1321
Sports Hall - Finishes - ADD.01 | 1 | 1 | Sports Hall - Finishes - ADD.011 | 44614 | 5944418.35
MDF Factory | 7 | 7 | MDF Factory7 | 44594 | 14851309.99
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 44620 | 17181317.99
PKG#177 - SWI 07 | 3 | 3 | PKG#177 - SWI 073 |  | 5800000
Kafr Shokr | 10 | 10 | Kafr Shokr 10 | 44830 | 2301999.75
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 44606 | 23504299.92
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 44616 | 15046421.2
EGAT Pelletizing Plant-Water Tank | 9 | 9 | EGAT Pelletizing Plant-Water Tank9 | 44622 | 1117435.2
Rolling Mill #4-TRAESUEZ | 2 | 2 | Rolling Mill #4-TRAESUEZ2 | 44642 | 11564103.96
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 44616 | 4767292.38
Katameya - Creeks | 14 | 14 | Katameya - Creeks14 | 44616 | 45904629.98
MDF Factory | 8 | 8 | MDF Factory8 | 44621 | 12391060.05
PKG#177 | 32 | 32 | PKG#17732 |  | 1200000
ORA - ZED - ph.02 | 5 | 5 | ORA - ZED - ph.025 | 44617 | 12407122.3694
HQ - CFC | 12 | 12 | HQ - CFC12 | 44616 | 11342067.06
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 44620 | 4511122
ORA - ZED | 15 | 15 | ORA - ZED15 |  | 25550073.0625
EGAT Pelletizing Plant-MEP | 2 | 2 | EGAT Pelletizing Plant-MEP2 | 44614 | 118584.38
CFC | 28 | 28 | CFC28 | 44690 | 10367935.42
PKG#177 | 34 | 34 | PKG#17734 |  | 16000000
Abo Ghaleb Bridge | 2 | 2 | Abo Ghaleb Bridge2 | 44627 | 2494611.027
MDF Factory | 9 | 9 | MDF Factory9 | 44658 | 7655361.33
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 44663 | 13017478.47
EGAT-Lock & Load | 2 | 2 | EGAT-Lock & Load2 | 44626 | 2243956.2
EGAT Pelletizing Plant-Water Tank | 10 | 10 | EGAT Pelletizing Plant-Water Tank10 | 44634 | 3717766.29
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 44644 | 16602157.8
HQ - CFC | 13 | 13 | HQ - CFC13 | 44648 | 869511.3183
ORA - ZED | 16 | 16 | ORA - ZED16 |  | 21942762.0737
ORA - ZED - ph.02 | 6 | 6 | ORA - ZED - ph.026 | 44691 | 16610990.7481
Abo Ghaleb Bridge | 3 | 3 | Abo Ghaleb Bridge3 | 44655 | 3124254.645
ORA - ZED - ph.02 | 7 | 7 | ORA - ZED - ph.027 | 44780 | 32100388.5958
ORA - ZED | 17 | 17 | ORA - ZED17 | 44692 | 26182539.8028
PKG#177 | 36 | 36 | PKG#17736 |  | 15000000
PKG#177 - SWI 07 | 5 | 5 | PKG#177 - SWI 075 |  | 9500000
PKG#163 | 23 | 23 | PKG#16323 |  | 3449740.5053
Sports Hall - MEP | 2 | 2 | Sports Hall - MEP2 |  | 13327738
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 44672 | 5421697
EGAT-Lock & Load | 3 | 3 | EGAT-Lock & Load3 | 44663 | 1683710.18
Rolling Mill #4-TRAESUEZ | 3 | 3 | Rolling Mill #4-TRAESUEZ3 | 44671 | 10352618.57
EGAT Pelletizing Plant-Water Tank | 11 | 11 | EGAT Pelletizing Plant-Water Tank11 | 44796 | 3941437.84
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 44672 | 14300826.37
HQ - CFC | 14 | 14 | HQ - CFC14 |  | 1748564.91
PKG#177 | 37 | 37 | PKG#17737 | 44780 | 2963171.8184
MDF Factory | 10 | 10 | MDF Factory10 | 44678 | 11119452.63
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 44668 | 19713977.881
Abo Ghaleb Bridge | 4 | 4 | Abo Ghaleb Bridge4 | 44782 | 6555212.9406
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 44704 | 7722438.9
Rolling Mill #4-TRAESUEZ | 4 | 4 | Rolling Mill #4-TRAESUEZ4 | 44698 | 6677291.55
ORA - ZED - ph.02 | 8 | 8 | ORA - ZED - ph.028 | 44719 | 8595538.9026
ORA - ZED | 18 | 18 | ORA - ZED18 | 44707 | 9292712.69
PKG#163 | 24 | 24 | PKG#16324 |  | 5681606.5237
PKG#177 | 38 | 38 | PKG#17738 |  | 0.0001
PKG#177 - SWI 07 | 6 | 6 | PKG#177 - SWI 076 |  | 5000000
HQ - CFC | 15 | 15 | HQ - CFC15 | 44698 | 10437709.6267
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 44712 | 4634265
MDF Factory | 11 | 11 | MDF Factory11 | 44719 | 9991684.94
Abo Ghaleb Bridge | 5 | 5 | Abo Ghaleb Bridge5 | 44794 | 1645829.28
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 44728 | 18095262.89
PKG#163 | 25 | 25 | PKG#16325 |  | 11730565.831
PKG#177 - SWI 07 | 7 | 7 | PKG#177 - SWI 077 |  | 4000000
Astoria Hotel | 5 | 5 | Astoria Hotel5 | 44740 | 5818860
EGAT-Lock & Load | 5 | 5 | EGAT-Lock & Load5 | 44719 | 3021167.52
EGAT Pelletizing Plant-MEP | 3 | 3 | EGAT Pelletizing Plant-MEP3 | 44969 | 1329462.73
ORA - ZED - ph.02 | 9 | 9 | ORA - ZED - ph.029 | 44746 | 7163536.3546
ORA - ZED | 19 | 19 | ORA - ZED19 | 44740 | 16483568.4889
Rolling Mill #4-TRAESUEZ | 5 | 5 | Rolling Mill #4-TRAESUEZ5 | 44748 | 8140659.04
MDF Factory | 12 | 12 | MDF Factory12 | 44741 | 29337407.23
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 44747 | 13285393.01
HQ - CFC | 16 | 16 | HQ - CFC16 | 44727 | 1064612.35
Astoria - Sharm | 2 | 2 | Astoria - Sharm2 | 44748 | 836570
Astoria Hotel | 6 | 6 | Astoria Hotel6 | 44748 | 8446328.13
HQ - CFC | 17 | 17 | HQ - CFC17 | 44760 | 8013147.4
PKG#177 - SWI 07 | 8 | 8 | PKG#177 - SWI 078 |  | 500000
PKG#163 | 26 | 26 | PKG#16326 |  | 8194504.6617
PKG#177 | 41 | 41 | PKG#17741 |  | 10330863.574
ORA - ZED - ph.02 | 10 | 10 | ORA - ZED - ph.0210 | 44773 | 20828447.3064
MDF Factory | 13 | 13 | MDF Factory13 | 44780 | 19866888.03
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 44796 | 7877469.99
EGAT-Lock & Load | 6 | 6 | EGAT-Lock & Load6 | 44748 | 3209897.61
Rolling Mill #4-TRAESUEZ | 6 | 6 | Rolling Mill #4-TRAESUEZ6 | 44780 | 4679965.02
ORA - ZED | 20 | 20 | ORA - ZED20 | 44780 | 8935027.0512
ORA - ZED | 20.1 | 20 | ORA - ZED20 | 44780 | 11075167.13
Mivida-PK#189 | 2 | 2 | Mivida-PK#1892 | 44779 | 22529255.8764
Sodic Eastown - Landscape | 8 | 8 | Sodic Eastown - Landscape8 | 44769 | 13407927.22
MDF Factory - Equip. | 8 | 8 | MDF Factory - Equip.8 | 44775 | 324002.35
Astoria - Sharm | 3 | 3 | Astoria - Sharm3 | 44782 | 269728
Astoria Hotel | 7 | 7 | Astoria Hotel7 | 44781 | 8710615
HQ - CFC | 18 | 18 | HQ - CFC18 | 44790 | 13019444.4
Katameya - Creeks | 20 | 20 | Katameya - Creeks20 | 44794 | 24569045.01
PKG#163 | 27 | 27 | PKG#16327 |  | 20000000
ORA - ZED | 21 | 21 | ORA - ZED21 | 44805 | 7443624.2902
Ring Road - Mounib | 17 | 17 | Ring Road - Mounib17 | 44783 | 5130646.847
PKG#177 - SWI 07 | 9 | 9 | PKG#177 - SWI 079 |  | 4000000
ORA - ZED - ph.02 | 11 | 11 | ORA - ZED - ph.0211 | 44798 | 12170283.1854
MDF Factory | 14 | 14 | MDF Factory14 | 44810 | 15316196.46
PKG#177 | 44 | 44 | PKG#17744 |  | 20000000
EGAT-Lock & Load | 7 | 7 | EGAT-Lock & Load7 | 44789 | 1345184.87
Mivida-PK#189 | 3 | 3 | Mivida-PK#1893 | 44808 | 19800407.88
Rolling Mill #4-TRAESUEZ | 7 | 7 | Rolling Mill #4-TRAESUEZ7 | 44797 | 13457708.47
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 44797 | 19389514.84
Astoria Hotel | 8 | 8 | Astoria Hotel8 | 44812 | 2805916
Astoria - Sharm | 4 | 4 | Astoria - Sharm4 | 44809 | 1641108
Katameya - Creeks | 21 | 21 | Katameya - Creeks21 | 44824 | 35259435.93
PKG#177 | 45 | 45 | PKG#17745 |  | 5000000
ORA - ZED | 22 | 22 | ORA - ZED22 | 44819 | 8098824.8775
MDF Factory | 15 | 15 | MDF Factory15 | 44843 | 15409194.69
HQ - CFC | 19 | 19 | HQ - CFC19 | 44850 | 2123376.4
EGAT-Lock & Load | 8 | 8 | EGAT-Lock & Load8 | 44815 | 2647273.89
PKG#163 | 28 | 28 | PKG#16328 |  | 20000000
Rolling Mill #4-TRAESUEZ | 8 | 8 | Rolling Mill #4-TRAESUEZ8 | 44831 | 14944026.92
Ring Road - Mounib | 18 | 18 | Ring Road - Mounib18 | 44816 | 3489333.2073
ORA - ZED - ph.02 | 12 | 12 | ORA - ZED - ph.0212 | 44843 | 14639634.3822
New Giza Hospital | 9 | 9 | New Giza Hospital9 | 44826 | 15620677.42
Mivida-PK#189 | 4 | 4 | Mivida-PK#1894 | 44843 | 27644756.83
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 44844 | 14238994.72
Astoria Hotel | 9 | 9 | Astoria Hotel9 | 44830 | 6286403
Astoria Hotel | 10 | 10 | Astoria Hotel10 | 44840 | 4982321
ORA - ZED - ph.02 | 13 | 13 | ORA - ZED - ph.0213 | 44856 | 17432997.712
ORA - ZED | 23 | 23 | ORA - ZED23 | 44861 | 22964574.875
Astoria - Sharm | 5 | 5 | Astoria - Sharm5 | 44840 | 709627
Sodic Eastown - Landscape | 9 | 9 | Sodic Eastown - Landscape9 | 44817 | 837296.04
MDF Factory | 16 | 16 | MDF Factory16 | 44871 | 22014291.85
New Giza Hospital | 10 | 10 | New Giza Hospital10 | 44868 | 14944068.34
EGAT-Lock & Load | 9 | 9 | EGAT-Lock & Load9 | 44852 | 3781437.71
HQ - CFC | 20 | 20 | HQ - CFC20 | 44845 | 9324446.7637
Rolling Mill #4-TRAESUEZ | 9 | 9 | Rolling Mill #4-TRAESUEZ9 | 44872 | 14162374.17
Mivida-PK#189 | 5 | 5 | Mivida-PK#1895 | 44870 | 46638711.45
PKG#177 | 46 | 46 | PKG#17746 |  | 10000000
PKG#163 | 29 | 29 | PKG#16329 |  | 20000000
Astoria Hotel | 11 | 11 | Astoria Hotel11 | 44865 | 10757000
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 44888 | 16138518.46
Astoria - Sharm | 6 | 6 | Astoria - Sharm6 | 44864 | 244817
EGAT-Lock & Load | 10 | 10 | EGAT-Lock & Load10 | 44868 | 1099389.93
Astoria Hotel | 12 | 12 | Astoria Hotel12 | 44875 | 2603000
Rolling Mill #4-TRAESUEZ | 10 | 10 | Rolling Mill #4-TRAESUEZ10 | 44909 | 12338644.38
HQ - CFC | 21 | 21 | HQ - CFC21 | 44885 | 1704646.05
ORA - ZED - ph.02 | 14 | 14 | ORA - ZED - ph.0214 | 44910 | 15411600.8685
MDF Factory | 17 | 17 | MDF Factory17 | 44888 | 15156893.21
Sodic Eastown - Landscape | 10 | 10 | Sodic Eastown - Landscape10 | 44854 | 5311032.49
Sodic Eastown - Landscape | 11 | 11 | Sodic Eastown - Landscape11 | 44872 | 7657014.05
New Giza Hospital | 11 | 11 | New Giza Hospital11 | 44902 | 19999087.83
Sodic Eastown - Landscape | 12 | 12 | Sodic Eastown - Landscape12 | 44885 | 8902796.13
Mivida-PK#189 | 6 | 6 | Mivida-PK#1896 | 44900 | 70000000
Astoria Hotel | 13 | 13 | Astoria Hotel13 | 44893 | 5389256
6TH October tunnel | 4 | 4 | 6TH October tunnel4 | 44878 | 3604450.6683
6TH October tunnel | 5 | 5 | 6TH October tunnel5 | 44882 | 3524900.34
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 44914 | 12845007.22
MDF Factory | 18 | 18 | MDF Factory18 | 44906 | 5028798.98
EGAT-Lock & Load | 11 | 11 | EGAT-Lock & Load11 | 44902 | 1893245.16
Mivida-PK#189 | 7 | 7 | Mivida-PK#1897 | 44900 | 38664242.9
Katameya - Creeks | 24 | 24 | Katameya - Creeks24 | 44921 | 37876581.29
ORA - ZED - ph.02 | 15 | 15 | ORA - ZED - ph.0215 | 44915 | 11605388.8976
New Giza Hospital | 12 | 12 | New Giza Hospital12 | 44924 | 21046664.64
Rolling Mill #4-TRAESUEZ | 11 | 11 | Rolling Mill #4-TRAESUEZ11 | 44943 | 13316234.88
Astoria Hotel | 14 | 14 | Astoria Hotel14 | 44915 | 6216098
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 44915 | 2167633.6703
MDF Factory | 19 | 19 | MDF Factory19 | 44923 | 9756751.36
Wady Halfa | 1 | 1 | Wady Halfa1 | 44913 | 33029517.9
HQ - CFC | 24 | 24 | HQ - CFC24 | 44922 | 5979128.01
Mivida-PK#189 | 8 | 8 | Mivida-PK#1898 | 44927 | 62566272.81
ORA - ZED | 24 | 24 | ORA - ZED24 | 44976 | 7490234.3814
MDF Factory | 20 | 20 | MDF Factory20 | 44938 | 14838164.52
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 44971 | 19373062.69
Astoria Hotel | 15 | 15 | Astoria Hotel15 | 44951 | 4185662
EGAT-Lock & Load | 12 | 12 | EGAT-Lock & Load12 | 44923 | 1689951.65
Katameya - Creeks | 25 | 25 | Katameya - Creeks25 | 44951 | 45191848.32
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 44959 | 2399508.91
ORA - ZED - ph.02 | 16 | 16 | ORA - ZED - ph.0216 | 44962 | 9858411.1445
ORA - ZED - Landscape | 2 | 2 | ORA - ZED - Landscape2 | 44958 | 1719650.0563
HQ - CFC | 25 | 25 | HQ - CFC25 | 44956 | 10125697.7641
ORA - ZED | 25 | 25 | ORA - ZED25 | 45026 | -9163815.8569
Mivida-PK#189 | 9 | 9 | Mivida-PK#1899 | 44950 | 37089197.56
New Giza Hospital | 13 | 13 | New Giza Hospital13 | 44963 | 18169651.25
Royal City | 42 | 42 | Royal City42 | 44970 | 29397549.59
PKG#163 | 30 | 30 | PKG#16330 |  | 20000000
Rolling Mill #4-TRAESUEZ | 12 | 12 | Rolling Mill #4-TRAESUEZ12 | 44964 | 13380155.34
MDF Factory | 21 | 21 | MDF Factory21 | 44963 | 18749752.53
ORA - ZED - Landscape | 3 | 3 | ORA - ZED - Landscape3 | 44983 | 1775205.4809
ORA - ZED - ph.02 | 17 | 17 | ORA - ZED - ph.0217 | 44994 | 8988165.9521
Port Said Silos - Local Supply | 1 | 1 | Port Said Silos - Local Supply1 | 45001 | 438003.54
EGAT-Lock & Load | 13 | 13 | EGAT-Lock & Load13 | 44964 | 2010941.41
DPW - Ph.02 | 1 | 1 | DPW - Ph.021 | 44973 | 21516389.4
Katameya - Creeks | 26 | 26 | Katameya - Creeks26 | 44985 | 74263221.64
Mivida-PK#189 | 10 | 10 | Mivida-PK#18910 | 44983 | 22123110.41
HQ - CFC | 26 | 26 | HQ - CFC26 | 45337 | 24450753.15
MDF Factory | 22 | 22 | MDF Factory22 | 44982 | 3016784.72
Astoria Hotel | 16 | 16 | Astoria Hotel16 | 44982 | 3225683
New Giza Hospital | 14 | 14 | New Giza Hospital14 | 44999 | 14731551.62
Rolling Mill #4-TRAESUEZ | 13 | 13 | Rolling Mill #4-TRAESUEZ13 | 44993 | 11700102.46
Wady Halfa | 2 | 2 | Wady Halfa2 | 44971 | 11905091.98
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 45048 | 1348177.1
DPW - Ph.02 - DP | 2 | 2 | DPW - Ph.02 - DP2 | 44978 | 63597656.25
PKG#177 | 47 | 47 | PKG#17747 | 45141 | 4375831.9851
LEKELA | 16 | 16 | LEKELA16 | 45016 | 8212932.01
ORA - ZED - ph.02 | 18 | 18 | ORA - ZED - ph.0218 | 45014 | 13331568.0485
ORA - ZED - Landscape | 4 | 4 | ORA - ZED - Landscape4 | 45026 | 4074938.0511
EIPICO | 4 | 4 | EIPICO4 | 45000 | 7345011.2
EGAT-Lock & Load | 14 | 14 | EGAT-Lock & Load14 | 44993 | 2629738.34
MDF Factory | 23 | 23 | MDF Factory23 | 45007 | 26140854.32
New Gas Station | 1 | 1 | New Gas Station1 | 45232 | 2360718.4
Mivida-PK#189 | 11 | 11 | Mivida-PK#18911 | 45026 | 18794302.38
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 45007 | 19188213.6
Astoria Hotel | 17 | 17 | Astoria Hotel17 | 45018 | 2804159
PKG#163 | 31 | 31 | PKG#16331 |  | 5000000
New Giza Hospital | 15 | 15 | New Giza Hospital15 | 45034 | 14839693.08
Wady Halfa | 3 | 3 | Wady Halfa3 | 45001 | 14516628.581
PKG#177 | 48 | 48 | PKG#17748 |  | 4111000
EIPICO | 5 | 5 | EIPICO5 | 45026 | 10066271.07
Port Said Silos | 13 | 13 | Port Said Silos13 | 45018 | 451211.246
MDF Factory | 24 | 24 | MDF Factory24 | 45046 | 13504786.11
DPW - Ph.02 | 3 | 3 | DPW - Ph.023 | 45012 | 19827820.72
Katameya - Creeks | 28 | 28 | Katameya - Creeks28 | 45050 | 28650459.02
ORA - ZED - ph.02 | 19 | 19 | ORA - ZED - ph.0219 | 45047 | 6921352.2914
ORA - ZED - Landscape | 5 | 5 | ORA - ZED - Landscape5 | 45047 | 3204803.968
Mivida-PK#189 | 12 | 12 | Mivida-PK#18912 | 45054 | 16890748.07
ORA - ZED | 26 | 26 | ORA - ZED26 | 45047 | 16993731.7513
New Giza Hospital | 16 | 16 | New Giza Hospital16 | 45060 | 15222233.72
EIPICO | 6 | 6 | EIPICO6 | 45063 | 5949977.84
DPW - Ph.02 | 4 | 4 | DPW - Ph.024 | 45085 | 28925313.53
Katameya - Creeks | 29 | 29 | Katameya - Creeks29 | 45080 | 40904481.77
Mivida-PK#189 | 13 | 13 | Mivida-PK#18913 | 45083 | 50032149.1
PKG#177 | 49 | 49 | PKG#17749 |  | 0.0001
PKG#163 | 32 | 32 | PKG#16332 |  | 5000000
ORA - ZED - Landscape | 6 | 6 | ORA - ZED - Landscape6 | 45084 | 3160913.3163
ORA - ZED - ph.02 | 20 | 20 | ORA - ZED - ph.0220 | 45078 | 3302213.7069
ORA - ZED | 27 | 27 | ORA - ZED27 | 45092 | 9042387.5614
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 45090 | 951578.36
DPW - Ph.02 | 5 | 5 | DPW - Ph.025 | 45102 | 30561302.57
New Giza Hospital | 17 | 17 | New Giza Hospital17 | 45111 | 12680990.84
ORA - ZED - ph.02 | 21 | 21 | ORA - ZED - ph.0221 | 45116 | 4532159.6508
PKG#177 | 50 | 50 | PKG#17750 |  | 0.001
Astoria Hotel | 19 | 19 | Astoria Hotel19 | 45096 | 1511334.2104
MDF Factory | 26 | 26 | MDF Factory26 | 45098 | 18123054.07
Mivida-PK#140 | 28 | 28 | Mivida-PK#14028 | 45365 | 1577397.44
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 |  | 2159644.45
PKG#163 | 33 | 33 | PKG#16333 |  | 5000000
KSA-Tarek AbdelHakim Center | 2 | 2 | KSA-Tarek AbdelHakim Center2 | 45090 | 2122111.73
Mivida-PK#189 | 14 | 14 | Mivida-PK#18914 | 45122 | 22045664.4
Creeks - URBN K | 3 | 3 | Creeks - URBN K3 | 45095 | 21808950.42
ORA - ZED - Landscape | 7 | 7 | ORA - ZED - Landscape7 | 45124 | 1045760.0532
ORA - ZED | 28 | 28 | ORA - ZED28 | 45116 | 10264179.63
KSA-Tarek AbdelHakim Center | 3 | 3 | KSA-Tarek AbdelHakim Center3 | 45132 | 911111.84
PKG#177 | 51 | 51 | PKG#17751 |  | 0.001
DPW - Ph.02 | 6 | 6 | DPW - Ph.026 | 45138 | 24170866.16
MDF Factory | 27 | 27 | MDF Factory27 | 45119 | 21231778.46
EIPICO | 8 | 8 | EIPICO8 | 45132 | 20317779.3
ORA - ZED - Landscape | 8 | 8 | ORA - ZED - Landscape8 | 45147 | 9578640.9799
Katameya - Creeks | 31 | 31 | Katameya - Creeks31 | 45138 | 37106226.16
Creeks - URBN K | 4 | 4 | Creeks - URBN K4 | 45138 | 8830426.33
ORA - ZED - ph.02 | 22 | 22 | ORA - ZED - ph.0222 | 45147 | 8466780.16
New Giza Hospital | 18 | 18 | New Giza Hospital18 | 45144 | 14934202.65
PKG#163 | 34 | 34 | PKG#16334 |  | 5000000
Astoria Hotel | 20 | 20 | Astoria Hotel20 | 45140 | 3400772
ORA - ZED | 29 | 29 | ORA - ZED29 | 45162 | 13678389.68
MDF Factory | 28 | 28 | MDF Factory28 | 45138 | 5471658.1245
Mivida-PK#189 | 15 | 15 | Mivida-PK#18915 | 45145 | 20013901.03
KSA-Tarek AbdelHakim Center | 4 | 4 | KSA-Tarek AbdelHakim Center4 | 45132 | 957216.97
SMP1 - Revamp | 4 | 4 | SMP1 - Revamp4 | 45170 | 2877592.22
DPW - Ph.02 | 7 | 7 | DPW - Ph.027 | 45166 | 16159880.26
Astoria Hotel | 21 | 21 | Astoria Hotel21 | 45183 | 854979
PKG#220B | 4 | 4 | PKG#220B4 |  | 2300000
MDF Factory | 29 | 29 | MDF Factory29 | 45179 | 13138195.96
Katameya - Creeks | 32 | 32 | Katameya - Creeks32 |  | 53390542.82
ORA - ZED - Landscape | 9 | 9 | ORA - ZED - Landscape9 | 45186 | 3636861.9198
ORA - ZED - ph.02 | 23 | 23 | ORA - ZED - ph.0223 | 45186 | 564270.13
New Giza Hospital | 19 | 19 | New Giza Hospital19 | 45183 | 5705542.36
PKG#177 | 52 | 52 | PKG#17752 |  | 45000000
ORA - ZED | 30 | 30 | ORA - ZED30 | 45186 | 13092650.18
Creeks - URBN K | 5 | 5 | Creeks - URBN K5 | 45161 | 13533059.96
Mivida-PK#189 | 16 | 16 | Mivida-PK#18916 | 45189 | 22512171.8728
EIPICO | 10 | 10 | EIPICO10 | 45166 | 6328837.05
Royal City - Landscape | 24 | 24 | Royal City - Landscape24 | 45173 | 3247942.88
Royal City | 43 | 43 | Royal City43 | 45173 | 13488633.46
DPW - Ph.02 | 8 | 8 | DPW - Ph.028 | 45173 | 20836254.44
EIPICO | 11 | 11 | EIPICO11 | 45209 | 30655535.07
ORA - ZED - ph.02 | 24 | 24 | ORA - ZED - ph.0224 | 45186 | 1374588.34
MDF Factory | 30 | 30 | MDF Factory30 | 45188 | 12581507.75
Katameya - Creeks | 33 | 33 | Katameya - Creeks33 | 45200 | 47329832.99
SMP1 - Revamp | 5 | 5 | SMP1 - Revamp5 | 45181 | 3101923.57
Creeks - URBN K | 6 | 6 | Creeks - URBN K6 | 45196 | 19608846.96
ORA - ZED | 31 | 31 | ORA - ZED31 | 45196 | 12746258.22
ORA - ZED - Landscape | 10 | 10 | ORA - ZED - Landscape10 | 45209 | 2654538.63
MDF Factory - Local Fabrication | 15 | 15 | MDF Factory - Local Fabrication15 | 45278 | 5457274.9
PKG#177 | 53 | 53 | PKG#17753 |  | 5000000
DPW - Ph.02 | 9 | 9 | DPW - Ph.029 | 45230 | 50195070.42
MDF Factory | 31 | 31 | MDF Factory31 | 45206 | 20429584.53
EIPICO | 12 | 12 | EIPICO12 | 45251 | 28595406.99
ORA - ZED - Landscape | 11 | 11 | ORA - ZED - Landscape11 | 45234 | 6014170.71
Katameya - Creeks | 34 | 34 | Katameya - Creeks34 | 45232 | 70308953.76
ORA - ZED - ph.02 | 25 | 25 | ORA - ZED - ph.0225 | 45237 | 996460.71
New Giza Hospital | 20 | 20 | New Giza Hospital20 | 45202 | 18995740.42
PKG#163 | 35 | 35 | PKG#16335 |  | 5000000
Astoria Hotel | 22 | 22 | Astoria Hotel22 | 45208 | 44838437.05
ORA - ZED | 32 | 32 | ORA - ZED32 | 45241 | 17052495.52
MDF Factory | 32 | 32 | MDF Factory32 | 45225 | 2726460
Mivida-PK#189 | 17 | 17 | Mivida-PK#18917 | 45216 | 47104890.06
Port Said Silos | 20 | 20 | Port Said Silos20 | 45231 | 10123399.3859
DPW - Ph.02 | 10 | 10 | DPW - Ph.0210 | 45259 | 44271228.34
Astoria Hotel | 23 | 23 | Astoria Hotel23 | 45253 | 17286732.59
MDF Factory | 33 | 33 | MDF Factory33 | 45255 | 12154985.64
Katameya - Creeks | 35 | 35 | Katameya - Creeks35 | 45266 | 46816344.41
ORA - ZED - Landscape | 12 | 12 | ORA - ZED - Landscape12 | 45250 | 7521516.04
ORA - ZED - ph.02 | 26 | 26 | ORA - ZED - ph.0226 | 45274 | 2944525.07
ORA - ZED | 33 | 33 | ORA - ZED33 | 45277 | 13971110.85
Mivida-PK#189 | 18 | 18 | Mivida-PK#18918 | 45262 | 20024965.62
Sokhna Port Expansion | 20 | 20 | Sokhna Port Expansion20 | 45224 | 13598323.882
CFC - Final Retention | 1 | 1 | CFC - Final Retention1 | 45213 | 12637074.78
New Giza Hospital | 21 | 21 | New Giza Hospital21 | 45215 | 8010369.24
Sokhna Port Expansion- 100m | 5 | 5 | Sokhna Port Expansion- 100m5 | 45224 | 3057123.2183
Baraka Land Fence | 1 | 1 | Baraka Land Fence1 | 45236 | 2645796
New Giza Hospital | 22 | 22 | New Giza Hospital22 | 45260 | 8695249.6
Sokhna Port Expansion | 21 | 21 | Sokhna Port Expansion21 | 45287 | 5872221.42
SMP1 - Revamp | 7 | 7 | SMP1 - Revamp7 | 45251 | 3428847.94
Port Said Silos | 21 | 21 | Port Said Silos21 | 45260 | 11711488.4753
DPW - Ph.02 | 11 | 11 | DPW - Ph.0211 | 45291 | 40849045.03
EIPICO | 13 | 13 | EIPICO13 | 45281 | 3870961.12
Mivida-PK#189 | 19 | 19 | Mivida-PK#18919 | 45293 | 23323710.1
MDF Factory | 34 | 34 | MDF Factory34 | 45280 | 13093494.9
Katameya - Creeks | 36 | 36 | Katameya - Creeks36 | 45290 | 50530225.45
New Giza Hospital | 23 | 23 | New Giza Hospital23 | 45318 | 4604562.68
Port Said Silos | 22 | 22 | Port Said Silos22 | 45274 | 4949068.8436
ORA - ZED | 34 | 34 | ORA - ZED34 | 45319 | 11514703.33
ORA - ZED - ph.02 | 27 | 27 | ORA - ZED - ph.0227 | 45305 | 6012429.48
MDF Factory - Equip. | 21 | 21 | MDF Factory - Equip.21 | 45285 | 592013.93
KSA-Tarek AbdelHakim Center | 11 | 11 | KSA-Tarek AbdelHakim Center11 | 45295 | 5080442.78
MDF Factory | 35 | 35 | MDF Factory35 | 45312 | 14005346.87
DPW - Ph.02 | 12 | 12 | DPW - Ph.0212 | 45326 | 15879945.92
Mivida-PK#189 - on account | 20 | 20 | Mivida-PK#189 - on account20 | 45302 | 135145955
Mivida-PK#189 | 21 | 21 | Mivida-PK#18921 | 45315 | 14476604.63
EIPICO | 14 | 14 | EIPICO14 | 45326 | 26305980.07
Katameya - Creeks | 37 | 37 | Katameya - Creeks37 | 45313 | 62109565.07
ORA - ZED | 35 | 35 | ORA - ZED35 | 45333 | 11302280.92
Creeks - URBN K | 10 | 10 | Creeks - URBN K10 | 45326 | 18357105.31
ORA - ZED - ph.02 | 28 | 28 | ORA - ZED - ph.0228 | 45354 | 1674078.17
ORA - ZED - Landscape | 13 | 13 | ORA - ZED - Landscape13 | 45342 | -674362.19
ORA - ZED - Landscape | 14 | 14 | ORA - ZED - Landscape14 | 45371 | 1008333.54
EIPICO | 15 | 15 | EIPICO15 | 45371 | 29236256.02
EIPICO | 15.1 | 15 | EIPICO15 |  | 29236256.02
Mivida-PK#189 | 22 | 22 | Mivida-PK#18922 | 45349 | 17552609
MDF Factory | 36 | 36 | MDF Factory36 | 45350 | 12150509.06
ORA - ZED - Landscape | 15 | 15 | ORA - ZED - Landscape15 | 45402 | 5175911.36
Katameya - Creeks | 38 | 38 | Katameya - Creeks38 | 45357 | 79235149.9
ORA - ZED | 36 | 36 | ORA - ZED36 | 45363 | 30791363.32
ORA - ZED - ph.02 | 29 | 29 | ORA - ZED - ph.0229 | 45385 | 651831.843
New Giza Hospital | 24 | 24 | New Giza Hospital24 | 45383 | 5494905.78
Creeks - URBN K | 11 | 11 | Creeks - URBN K11 | 45361 | 11569432.7
Rabigh Ext. - Piles | 1 | 1 | Rabigh Ext. - Piles1 | 45369 | 947881.6
Mivida-PK#189 | 23 | 23 | Mivida-PK#18923 | 45403 | 14242173.08
ORA - ZED - Landscape | 16 | 16 | ORA - ZED - Landscape16 | 45381 | 1521916.05
DPW - Ph.02 | 13 | 13 | DPW - Ph.0213 | 45383 | 18632592.11
Katameya - Creeks | 39 | 39 | Katameya - Creeks39 | 45384 | 66261026.21
MDF Factory | 37 | 37 | MDF Factory37 | 45384 | 7449862.86
ORA - ZED | 37 | 37 | ORA - ZED37 | 45388 | 9469567.93
Port Said Silos - Local Supply | 3 | 3 | Port Said Silos - Local Supply3 | 45364 | 2005309.5601
DPW - Ph.02 | 14 | 14 | DPW - Ph.0214 | 45426 | 35418927.4
Creeks - URBN K | 12 | 12 | Creeks - URBN K12 | 45385 | 8618325.74
ORA - ZED - ph.02 | 30 | 30 | ORA - ZED - ph.0230 | 45385 | -2279827.56
EIPICO | 16 | 16 | EIPICO16 | 45406 | 26365248.98
New Giza Hospital | 25 | 25 | New Giza Hospital25 | 45296 | 10195246.28
ORA - ZED - Landscape | 17 | 17 | ORA - ZED - Landscape17 | 45419 | 775773.82
ORA - ZED | 38 | 38 | ORA - ZED38 | 45421 | 12665876.69
MDF Factory | 38 | 38 | MDF Factory38 | 45406 | 10129299.6901
Port Said Silos - Local Supply | 4 | 4 | Port Said Silos - Local Supply4 | 45389 | 2837726.014
ORA - ZED - ph.02 | 31 | 31 | ORA - ZED - ph.0231 | 45419 | 3758520.95
Mivida-PK#189 | 24 | 24 | Mivida-PK#18924 | 45434 | 13803484.93
Port Said Silos | 27 | 27 | Port Said Silos27 | 45413 | 1090118.805
Rabigh Ext. - Piles | 2 | 2 | Rabigh Ext. - Piles2 | 45414 | 1174036.98
ORA - ZED - Landscape | 18 | 18 | ORA - ZED - Landscape18 | 45426 | 1643291.15
ORA - ZED - ph.02 | 32 | 32 | ORA - ZED - ph.0232 | 45448 | 2943652.2
MDF Factory | 39 | 39 | MDF Factory39 | 45434 | 7951387.28
Katameya - Creeks | 41 | 41 | Katameya - Creeks41 | 45437 | 45340679.8
ORA - ZED | 39 | 39 | ORA - ZED39 | 45449 | 7606231.5
Mivida-PK#189 | 25 | 25 | Mivida-PK#18925 | 45449 | 28360739.45
New Giza Hospital | 26 | 26 | New Giza Hospital26 | 45456 | 17232986.3
EIPICO | 17 | 17 | EIPICO17 | 45456 | 13161378
Port Said Silos - Local Supply | 5 | 5 | Port Said Silos - Local Supply5 | 45424 | 2131161.0294
PKG#163 | 36 | 36 | PKG#16336 |  | 10852799
PKG#177 | 54 | 54 | PKG#17754 |  | 14081143
Port Said Silos | 28 | 28 | Port Said Silos28 | 45445 | 2459043.7651
Wady Halfa - Escalation Claim | 3 | 3 | Wady Halfa - Escalation Claim3 | 45444 | 18633826.665
Wady Halfa - Escalation Claim | 3.1 | 3 | Wady Halfa - Escalation Claim3 | 45444 | 167704439.985
ORA - ZED - Landscape | 19 | 19 | ORA - ZED - Landscape19 | 45480 | 168189.5
ORA - ZED - ph.02 | 33 | 33 | ORA - ZED - ph.0233 | 45474 | 1631186.62
ORA - ZED | 40 | 40 | ORA - ZED40 | 45474 | 6599009.58
Katameya - Creeks | 42 | 42 | Katameya - Creeks42 | 45480 | 52791233.92
Port Said Silos - Local Supply | 6 | 6 | Port Said Silos - Local Supply6 | 45452 | 692035.1069
Rabigh Ext. - Piles | 4 | 4 | Rabigh Ext. - Piles4 | 45481 | 1787056.4437
Creeks - URBN K | 15 | 15 | Creeks - URBN K15 | 45455 | 10206848.68
Baraka Land Fence | 4 | 4 | Baraka Land Fence4 | 45433 | 8703054.16
SMP1 - Revamp | 10 | 10 | SMP1 - Revamp10 | 45447 | 3758608.34
Mivida-PK#189 | 26 | 26 | Mivida-PK#18926 | 45476 | 14177811.24
EIPICO | 18 | 18 | EIPICO18 | 45503 | 38010351.15
ORA - ZED - ph.02 | 34 | 34 | ORA - ZED - ph.0234 | 45510 | 3368948.46
ORA - ZED - Landscape | 20 | 20 | ORA - ZED - Landscape20 | 45496 | 1244123
MDF Factory | 42 | 42 | MDF Factory42 | 45497 | 7547918.7
Port Said Silos | 29 | 29 | Port Said Silos29 | 45481 | 1521379.1786
Mivida-PK#189 | 27 | 27 | Mivida-PK#18927 | 45505 | 4389859.04
Katameya - Creeks | 43 | 43 | Katameya - Creeks43 | 45500 | 30082113.9462
Creeks - URBN K | 16 | 16 | Creeks - URBN K16 | 45502 | 6345313.67
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 45435 | 3648396.5221
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 45525 | 2114752.93
New Giza Hospital | 27 | 27 | New Giza Hospital27 | 45522 | 13715277.6
ORA - ZED | 41 | 41 | ORA - ZED41 | 45535 | 3961614.17
Port Said Silos - Local Supply | 7 | 7 | Port Said Silos - Local Supply7 | 45491 | 3609101.6718
Mivida-PK#189 | 28 | 28 | Mivida-PK#18928 | 45535 | 2409288.21
Rabigh Ext. -Building | 2 | 2 | Rabigh Ext. -Building2 | 45529 | 4957387.2204
Port Said Silos | 30 | 30 | Port Said Silos30 | 45509 | 2352677.2563
MDF Factory | 43 | 43 | MDF Factory43 | 45525 | 57977475.46
ORA - ZED | 42 | 42 | ORA - ZED42 | 45536 | 3504951.97
ORA - ZED - ph.02 | 35 | 35 | ORA - ZED - ph.0235 | 45535 | 6454315.65
Katameya - Creeks | 44 | 44 | Katameya - Creeks44 | 45535 | 8345106.3
Creeks - URBN K | 17 | 17 | Creeks - URBN K17 | 45540 | 8554807.45
ORA - ZED - Landscape | 21 | 21 | ORA - ZED - Landscape21 | 45540 | 189683.6223
ORA - ZED - ph.02 | 36 | 36 | ORA - ZED - ph.0236 | 45540 | 6578211.32
EIPICO | 19 | 19 | EIPICO19 | 45557 | 29978125.14
Red Sea Museum | 3 | 3 | Red Sea Museum3 | 45537 | 1225041
MDF Factory | 44 | 44 | MDF Factory44 | 45561 | 13417821.66
ORA - ZED - Landscape | 22 | 22 | ORA - ZED - Landscape22 | 45551 | 1388299.8
ORA - ZED - ph.02 | 37 | 37 | ORA - ZED - ph.0237 | 45572 | 9153293.69
ORA - ZED | 43 | 43 | ORA - ZED43 | 45557 | 11004454.56
Rabigh Ext. -Building | 3 | 3 | Rabigh Ext. -Building3 | 45554 | 4088042.3344
Creeks - URBN K | 18 | 18 | Creeks - URBN K18 | 45560 | 9363449.62
Baraka Land Fence | 5 | 5 | Baraka Land Fence5 | 45524 | 5636679.16
New Giza Hospital | 28 | 28 | New Giza Hospital28 | 45568 | 6800969.24
Mivida-PK#189 | 29 | 29 | Mivida-PK#18929 | 45561 | 2690517.47
ORA - ZED - ph.02 | 38 | 38 | ORA - ZED - ph.0238 | 45572 | 3851310.01
ORA - ZED - ph.02 | 39 | 39 | ORA - ZED - ph.0239 | 45605 | 14526906.83
ORA - ZED | 44 | 44 | ORA - ZED44 | 45580 | 4559905.68
ORA - ZED - Landscape | 23 | 23 | ORA - ZED - Landscape23 | 45580 | 1551640.48
Rabigh Ext. -Building | 4 | 4 | Rabigh Ext. -Building4 | 45588 | 4796196.0024
MDF Factory | 45 | 45 | MDF Factory45 | 45600 | 21518034.22
Katameya - Creeks | 46 | 46 | Katameya - Creeks46 | 45600 | 22007540.78
Creeks - URBN K | 19 | 19 | Creeks - URBN K19 | 45598 | 6696306.5
Mivida-PK#189 | 30 | 30 | Mivida-PK#18930 | 45608 | 14412191.13

## eslam-to-invoicing
project name | must be
6TH October tunnel | October Under-Railway Tunnel
Abo Ghaleb Bridge | Abo Ghaleb
AEON
Al Jazi | Aljazi Project
Al Jazi - Center Zone | Aljazi Project
Al Jazi - Center Zone-DP | Aljazi Project
Al Jazi - Social Insurance | Aljazi Project
Al Jazi-DP | Aljazi Project
Alfa Lab | Alfa New Central Labs
Allegria-New Modifications
Astoria - Sharm | Astoria Sharm elSheikh
Astoria - Sharm-DP | Astoria Sharm elSheikh
Astoria Hotel | Waldorf Astoria Cairo
Astoria Hotel - DP | Waldorf Astoria Cairo
Astoria Hotel - Final Retention | Waldorf Astoria Cairo
Astoria Hotel - On Account | Waldorf Astoria Cairo
Astoria Hotel - Social Insurrance | Waldorf Astoria Cairo
Astoria Hotel - Spare Parts V.O 137 | Waldorf Astoria Cairo
Astoria Hotel IPCs 15-20 | Waldorf Astoria Cairo
Baraka Land Fence
Benban - Aswan
Benban - Aswan - DP
Cement Plant | Cement Factory-Beni Suef
Cement Plant -Last Claim | Cement Factory-Beni Suef
CFC | CFC Podium 2
CFC - Final Retention | CFC Podium 2
CFC-DP | CFC Podium 2
Comoros - DP | Le Galawa Hotel Resort
Comoros - Off Shore | Le Galawa Hotel Resort
Comoros - On Shore | Le Galawa Hotel Resort
Comoros - On Shore - On Account | Le Galawa Hotel Resort
Creeks - URBN K | Creeks URBN-K
Creeks - URBN K - DP | Creeks URBN-K
Creeks - URBN K - On Account | Creeks URBN-K
Damietta Port - Civil | Damietta Container Termin
Damietta Port - Civil - DP | Damietta Container Termin
Damietta Port - Infra - DP | Damietta Container Termin
DP World Sokhna | DPW Onshore Port & Terminal
DP World Sokhna-AP | DPW Onshore Port & Terminal
DPW - Ph.02 | DP World Basin 2 Ph2
DPW - Ph.02 - DP | DP World Basin 2 Ph2
EGAT Pelletizing Plant | EGAT Pelletizing Plant
EGAT Pelletizing Plant - Admin Building | EGAT Pelletizing Plant
EGAT Pelletizing Plant - Supply | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Concrete Infra | EGAT Pelletizing Plant
EGAT Pelletizing Plant-DP | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Escalation | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Mechanical Installation | EGAT Pelletizing Plant
EGAT Pelletizing Plant-MEP | EGAT Pelletizing Plant
EGAT Pelletizing Plant-MEP Coordination | EGAT Pelletizing Plant
EGAT Pelletizing Plant-On account | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Water Tank | EGAT Pelletizing Plant
EGAT-Asphalt
EGAT-Asphalt - Retenion Release
EGAT-EGAT ON Account
EGAT-Fence
EGAT-Fence - Retenion Release
EGAT-HeliPad
EGAT-Lock & Load | EGAT Lock & Load
EGAT-Lock & Load-AP | EGAT Lock & Load
EGAT-SZ
EGAT-Warehouse
EIPICO | EPICO 3 Facility
EIPICO-DP | EPICO 3 Facility
EIPICO-On Account | EPICO 3 Facility
El Sewedy Uni.-PKG.1 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.1-DP1 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2-DP2 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2-Social Insurrance | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3 - On Account | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3-DP | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3-Social Insurrance | Elsewedy Univ - Enabling Works
Elco Steel | Substation Elco Steel
Elco Steel - ADMIN. | Substation Elco Steel
Elco Steel - MEP | Substation Elco Steel
Elco Steel - MEP - Social Insurance | Substation Elco Steel
Elco Steel - Social Insurance | Substation Elco Steel
Elco Steel EGAT-DP | Substation Elco Steel
Elco Steel V.O | Substation Elco Steel
Elco Steel V.O-DP | Substation Elco Steel
Elco Steel V.O-Infra. Network | Substation Elco Steel
El-Gouna | DoubleTree Mangroovy ElGouna
El-Gouna - DP | DoubleTree Mangroovy ElGouna
El-Gouna - Equip. Rental | DoubleTree Mangroovy ElGouna
El-Gouna - Temp. Fence | DoubleTree Mangroovy ElGouna
EUA-DP
Existing Intake Apply -SSC-Mech
Existing Intake Supply -SSC-Mech
FIEM
FIEM - Retention
FIEM-Site Offices Rental Payment Request
H1 Solaymaneya-MEP
H1 Solaymaneya-MEP-DP
HQ - CFC | ElSewedy HQ Internal Finishing
HQ - CFC - DP | ElSewedy HQ Internal Finishing
HQ - CFC - Retention release | ElSewedy HQ Internal Finishing
HQ - CFC - Social Insurrance | ElSewedy HQ Internal Finishing
HyperOne | HyperOne Zayed Extension
HyperOne-DP | HyperOne Zayed Extension
HyperOne-Steel Supply | HyperOne Zayed Extension
HyperOne-VAT 1,2,3 | HyperOne Zayed Extension
IKEA | IKEA Extension MoA
IKEA-DP | IKEA Extension MoA
IKEA-Retention Release | IKEA Extension MoA
JICA
JICA-Site Offices Rental Payment Request
Kafr Shokr | Kafr Shokr Bridge
Kafr Shokr - Retention Release | Kafr Shokr Bridge
Katameya - Creeks | Kattameya Creeks
Katameya - Creeks - DP | Kattameya Creeks
Katameya - Creeks - DP - Alu Glass | Kattameya Creeks
Katameya - Creeks - On Account | Kattameya Creeks
KFW
KFW-Road Signals
Khatatba Bridge | El Khatatba Bridge
KSA-Tarek AbdelHakim Center
KSA-Tarek AbdelHakim Center - DP
LEKELA | Lekela 250MW Wind Farm
LEKELA - Supply Bill | Lekela 250MW Wind Farm
LEKELA- On Account | Lekela 250MW Wind Farm
LEKELA Remedial | Lekela 250MW Wind Farm
LEKELA Remedial-DP | Lekela 250MW Wind Farm
LEKELA-DP | Lekela 250MW Wind Farm
MDF Factory | MDF Factory
MDF Factory - Equip. | MDF Factory
MDF Factory - Local Fabrication | MDF Factory
MDF Factory-DP | MDF Factory
MDF Factory-F.F V.O-on account | MDF Factory
MDF Factory-Hold Amount release | MDF Factory
MDF Factory-Local Fab.-on account | MDF Factory
MDF Factory-on account | MDF Factory
MDF Factory-on account solera | MDF Factory
MDF Factory-P.O-on account | MDF Factory
Mechanical Installation | EGAT Mechanical Installations
Mechanical Installation-DP | EGAT Mechanical Installations
Mintra
Mintra-DP
Mintra-Hanger 1200m2
Mivida-PK#140 | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#140- Social Insurance | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#140-DP | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#189 | Mivida BP#189
Mivida-PK#189 - on account | Mivida BP#189
Mivida-PK#189 - Social insurance | Mivida BP#189
Mivida-PK#189-DP | Mivida BP#189
Mobilization
MOC | MOC HQ at Diriyah
MOC - DP | MOC HQ at Diriyah
New Gas Station | New Giza Teaching Hospital
New Giza Hospital | New Giza Teaching Hospital
New Giza Hospital-DP | New Giza Teaching Hospital
New Giza Hospital-On Account | New Giza Teaching Hospital
New Giza Hospital-Social Insurance | New Giza Teaching Hospital
NGU 2 | New Giza 2
NGU 2 - Retension release | New Giza 2
Old H1 remaining IPC
ORA - ZED | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Compansation | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Deficit | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - DP | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - On account | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Social Insurrance | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Landscape | Ora Zed Landscape Ph1
ORA - ZED - Landscape - Deficit | Ora Zed Landscape Ph1
ORA - ZED - Landscape - DP | Ora Zed Landscape Ph1
ORA - ZED - ph.02 | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - Claims | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - Deficit | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - On Account | ORA ZED-Ph 2-Pkgs A&D
PH.2-El Sewedy Uni. - Enabling | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Enabling - Retention release | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes - on account | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni.-DP | ESU Ph2-Enabling & Struc
PI Parks - ELSEWEDY
PI Parks - MEP
PI Parks - MEP-DP1
PI Parks - MEP-DP2
PK #107 | EMAAR-PKG#107-MARASSI
PK #117 | EMAAR-PKG117- MARASSI
PK #117 - Social Insurance | EMAAR-PKG117- MARASSI
PK #22 - Social Insurance | EMAAR-PKG#22-MARASSI
PK#22 | EMAAR-PKG#22-MARASSI
PK#32
PKG#101 | EMAAR-PKG# 101-UPTOWN
PKG#101- Social Insurance | EMAAR-PKG# 101-UPTOWN
PKG#101-DP | EMAAR-PKG# 101-UPTOWN
PKG#101-VO1&VO2 AP | EMAAR-PKG# 101-UPTOWN
PKG#144 | EMAAR-PKG# 144, Marassi
PKG#144 - Social Insurance | EMAAR-PKG# 144, Marassi
PKG#144-DP | EMAAR-PKG# 144, Marassi
PKG#162 | EMAAR-Pkg#162/163- Marassi
PKG#162- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#162-DP | EMAAR-Pkg#162/163- Marassi
PKG#163 | EMAAR-Pkg#162/163- Marassi
PKG#163- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#163-DP | EMAAR-Pkg#162/163- Marassi
PKG#177 | EMAAR-Pkg#162/163- Marassi
PKG#177 - DP | EMAAR-Pkg#162/163- Marassi
PKG#177 - on account | EMAAR-Pkg#162/163- Marassi
PKG#177 - SWI 07 | EMAAR-Pkg#162/163- Marassi
PKG#177- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#178 | BKG#178-Lagoon Discharge
PKG#178 - DP | BKG#178-Lagoon Discharge
PKG#178- Social Insurance | BKG#178-Lagoon Discharge
PKG#205
PKG#205 - DP
PKG#205-Social Insurance
PKG#220B | SOL Town PKG.220
PKG#220B - DP | SOL Town PKG.220
PKG#45
PKG#58
PKG#85 | EMAAR-PKG#85-UPTOWN
PO#11687
Port Said Silos | Port Said Port Silos
Port Said Silos - Foreigner Supply | Port Said Port Silos
Port Said Silos - Local Supply | Port Said Port Silos
Port Said Silos-DP | Port Said Port Silos
Port Said Silos-On account | Port Said Port Silos
Port Said Silos-Social Insurrance | Port Said Port Silos
PSP Substation
PSP Substation - Beni Suef
PSP Substation - DP
PSP Substation-Retention
Rabigh Ext. - Piles | Rabigh PP - Piling Works
Rabigh Ext. - Piles- DP | Rabigh PP - Piling Works
Rabigh Ext. -Building | Rabigh CCPP-Civil
Rabigh Ext. -Building- DP | Rabigh CCPP-Civil
Radamis-Concrete
Radamis-Concrete-DP
Radamis-H1 Main Builidng
Radamis-H1-On Account
Radamis-Rooms Fitout
Radamis-Rooms Fitout-DP
Radamis-Villas Finishes
Red Sea Museum | Red Sea Museum-Bab El-Bunt
Red Sea Museum - DP | Red Sea Museum-Bab El-Bunt
Ring Road - El Marg | RING ROAD MARYOTIA EXPANSION
Ring Road - El Marg - Retention Release | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib - refund | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib - Social Insurance | RING ROAD MARYOTIA EXPANSION
RO Apply -Mech- SSC
RO Eriction
RO Pump Room
RO - Supply - Electric
RO Supply -Mech- SSC
RO 2
RO Pump room - SSC - price diff.
RO.2
Rolling Mill #4-TRAESUEZ | EGAT New Rolling Mill 4
Rolling Mill #4-TRAESUEZ -AP | EGAT New Rolling Mill 4
Royal City | Royal City
Royal City - Landscape | Royal City
Royal City-DP 3 | Royal City
Royal City-DP 4 | Royal City
Royal City-DP1 | Royal City
Royal City-DP2 | Royal City
Saint Gobain Factory - DP
SIEMENS - Sokhna
SIEMENS - Sokhna - Bill
SMP1 - Revamp
SMP1 - Revamp - DP
SMP1 - Shut Down
SMP1 - Shut Down- Final Retention
SMP2 - Shut Down
SMP2 - Shut Down- Retention release
SMP2 - Shut Down- V.O
Sodic Club House | Sodic Club House
Sodic Club House - Social Insurance | Sodic Club House
Sodic Eastown | EDNC Retail & Offices Civil
Sodic Eastown - Landscape | EDNC Hardscape Package
Sodic Eastown - On Account | EDNC Retail & Offices Civil
Sodic Eastown - Social Insurance | EDNC Retail & Offices Civil
Sodic Eastown-DP | EDNC Retail & Offices Civil
Sokhna Port Expansion | Sokhna Port Expansion
Sokhna Port Expansion- 100m | Sokhna Port Expansion
Sokhna Port Expansion 100m- Escalation | Sokhna Port Expansion
Sokhna Port Expansion- EDECS | Sokhna Port Expansion
Sokhna Port Expansion- Escalation | Sokhna Port Expansion
Sokhna Port Expansion-AP | Sokhna Port Expansion
Sokhna Port Expansion-internal roads | Sokhna Port Expansion
Sports Hall - Civil Works | Olympic Multi – Sports Hall
Sports Hall - Finishes | Olympic Multi – Sports Hall
Sports Hall - Finishes - ADD.01 | Olympic Multi – Sports Hall
Sports Hall - Finishes - ADD.01 - Final Retention | Olympic Multi – Sports Hall
Sports Hall - Finishes - Landscape | Olympic Multi – Sports Hall
Sports Hall - Finishes - Landscape - Final Retention | Olympic Multi – Sports Hall
Sports Hall - Finishes - Social Insurance | Olympic Multi – Sports Hall
Sports Hall - MEP | Olympic Multi – Sports Hall
Sports Hall - MEP - DP | Olympic Multi – Sports Hall
Sports Hall - MEP - Final Retention | Olympic Multi – Sports Hall
Suez Intake & P Stations-ABB apply
Suez Intake & P Stations-ABB supply
Suez Intake & P Stations-ABB-Escalation
Suez Intake & P Stations-SSC apply
Suez Intake & P Stations-SSC supply
Suez Steel Intake & P Stations-DP
Suez Steel-Al Baraka-DP
Suez Steel-Gas Station-DP
SVC
SVC-DP
Uptown PK #53 | EMAAR-PKG#53-UPTOWN
Uptown PK #62 | EMAAR-PKG#62-UPTOWN
Uptown PK #62 - Retention | EMAAR-PKG#62-UPTOWN
Wady Halfa | Wadi Halfa Port
Wady Halfa - DP | Wadi Halfa Port
Wady Halfa - Escalation Claim | Wadi Halfa Port
Wady Halfa - Stoppage Period | Wadi Halfa Port
Western Fence
Western Fence-PO
Zayed Park

## data-from-invoicing
PROJECT_NAME | INV_NUM | invoice_number | concact | gross | collection from applied | on account from applied | collection
Cameron EDC | 013/2019 |  | Cameron EDC | 1465931.71 | 1464726.49 | 0 | 1464726.49
Cameron EDC | 006/2018 |  | Cameron EDC | 1261922.85 | 1260761.68 | 0 | 1260761.68
Cameron EDC | 029/2021 |  | Cameron EDC | 95747998.8 | 95747998.8 | 0 | 95747998.8
Cameron EDC | 023/202+L9+L7:Q7 |  | Cameron EDC | 69576437.45 | 13915287.49 | 0 | 34788218.49
Kuwait | Other Charge/J003 |  | Kuwait | 10656.5 | 6926.72 | 0 | 6926.72
Kuwait | Supply/H009 |  | Kuwait | 41451.49 | 26943.47 | 0 | 26943.47
Al-Shabab PP Phase II (CP-117) | 542 |  | Al-Shabab PP Phase II (CP-117) | 9940.36 | 9568.95 | 1708.5 | 11277.45
W Dam PP Phase II (CP-117) | 524 |  | W Dam PP Phase II (CP-117) | 28516.39 | 25202.32 | 4499.78 | 29702.1
W Dam PP Phase II (CP-117) | 180103 |  | W Dam PP Phase II (CP-117) | 5125.59 | 4583.19 | 808.8 | 5391.99
W Dam PP Phase II (CP-117) | 180099 |  | W Dam PP Phase II (CP-117) | 37929.47 | 33915.73 | 5985.13 | 39900.86
W Dam PP Phase II (CP-117) | 180092 | #N/A | #N/A | 45343.38 | 40545.08 | 7155.02 | 47700.1
W Dam PP Phase II (CP-117) | 180090 |  | W Dam PP Phase II (CP-117) | 81098.89 | 72516.91 | 12797.1 | 85314.01
W Dam PP Phase II (CP-117) | 180042 |  | W Dam PP Phase II (CP-117) | 351162.1333 | 0 | 0 | 368720.24
Al-Shabab PP Phase II (CP-117) | 180030 |  | Al-Shabab PP Phase II (CP-117) | 128840.419 | 0 | 0 | 135282.44
Al-Shabab PP Phase II (CP-117) | 180029 |  | Al-Shabab PP Phase II (CP-117) | 72035.2857 | 0 | 0 | 75637.05
Al-Shabab PP Phase II (CP-117) | 180024 |  | Al-Shabab PP Phase II (CP-117) | 149161.9714 | 0 | 22642.79 | 22642.79
Al-Shabab PP Phase II (CP-117) | Inv 29 Shabab Egy | 29 | Al-Shabab PP Phase II (CP-117)29 | 143493.8212 | 128309.13 | 22642.79 | 150951.92
W Dam PP Phase II (CP-117) | 23 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 341586.6381 | 304866.07 | 53799.9 | 358665.97
W Dam PP Phase II (CP-117) | 8 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 12401061.796 | 8241564.96 | 1873180.7 | 12669314.2001
Al-Shabab PP Phase II (CP-117) | 13 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2938328.9619 | -314874.28 | 462786.81 | 452339.97
Al-Shabab PP Phase II (CP-117) | 17 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 259030.0857 | 244213.97 | 40797.24 | 285011.21
W Dam PP Phase II (CP-117) | 7 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 1070847.7778 | 844130.92 | 160471.5 | 1124390.1667
Al-Shabab PP Phase II (CP-117) | 3 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2508074.5751 | 0 | 380725.72 | 2538171.47
Suez Gulf Substation | 180047 |  | Suez Gulf Substation | 336722.54 | 318808.92 | 35423.21 | 354232.13
Suez Gulf Substation | 16 EGP-progress repo |  | Suez Gulf Substation | 3142077.2571 | 0 | 0 | 0
Suez Gulf Substation | Inv 4 EGP VO SG | 4 | Suez Gulf Substation4 | 229413.8 | 216800.04 | 24084.45 | 240884.49
Suez Gulf Substation | 8 EGP Suez Gulf |  | Suez Gulf Substation | 2957422.0857 | 2791958.72 | 0 | 2791958.72
Suez Gulf Substation | 481 |  | Suez Gulf Substation | 670083.38 | 634419.9 | 70491.1 | 704911
Suez Gulf Substation | 14 USD Suez Gulf |  | Suez Gulf Substation | 296941 | 280609.24 | 31178.81 | 311788.05
Suez Gulf Substation | 14 USD - Suez Gulf |  | Suez Gulf Substation | 296940.9905 | 0 | 31178.8 | 31178.8
Suez Gulf Substation | 11 USD - Suez Gulf |  | Suez Gulf Substation | 73364.13 | 0 | 7336.41 | 73364.13
Pyramids Industrial P - East | Inv. 16 PIP EAST | 16 | Pyramids Industrial P - East16 | 18308153.18 | 7212729.5094 | 1317140.66 | 8529870.1694
Abou El Matameer and Sammanoud | Abo Matamir 1 |  | Abou El Matameer and Sammanoud | 27483009.5 | 19875810.07 | 4122451.43 | 23998261.5
Siemens 6x500/220 KV GIS-MOU | Inv 63 P15 Banha Fin | 63 | Siemens 6x500/220 KV GIS-MOU63 | 1037425.1 | 750473.31 | 155613.77 | 906087.08
Barwa 2x60/22 KV S/S | Inv 29 Barwa | 29 | Barwa 2x60/22 KV S/S29 | 1921317.79 | 1359198.33 | 288197.67 | 1647396
Barwa 2x60/22 KV S/S | Inv 19 Barwa | 19 | Barwa 2x60/22 KV S/S19 | 5822687.66 | 4119121.2 | 873403.15 | 4992524.35
Damac 2x60/22 KV S/S | Inv 27 Damac | 27 | Damac 2x60/22 KV S/S27 | 3197424.84 | 2261973.2 | 479613.73 | 2741586.93
Damac 2x60/22 KV S/S | inv 18 Damac | 18 | Damac 2x60/22 KV S/S18 | 1454300.47 | 1028483.12 | 218145.1 | 1246628.22
IRAQ - Substations Soil Invest | 6 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
Abo Quir - Badr 500KV | 1 |  | Abo Quir - Badr 500KV | 12972376.91 | 915776.51 | 0 | 986999.16
South Helwan PP (CP-117) | 2 EGP - South Helwan |  | South Helwan PP (CP-117) | 3216085.3429 | 3376889.61 | 0 | 3376889.61
Abu Qir PP (CP-118) | 448 EGP - Avice |  | Abu Qir PP (CP-118) | 50265.29 | 55291.819 | 0 | 55291.819
Al-Shabab PP Phase II (CP-117) | 11 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 200592 | 30088.8 | 0 | 30088.8
Al-Shabab PP Phase II (CP-117) | 10 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 8803626.76 | 7337016.45 | 0 | 8803626.76
New Capital | Inv. 4 ElTebeen | 4 | New Capital4 | 992670.47 | 757742.66 | 104230.41 | 861973.07
South Helwan PP (CP-117) | 180066 |  | South Helwan PP (CP-117) | -178521.44 | 0 | -28117.13 | -28117.13
Gabal Elgalalaa | ختامى |  | Gabal Elgalalaa | 2159417.2 | 2273473.76 | 0 | 1136736.88
Berket Ghelion | Gheleon 7 |  | Berket Ghelion | 14736103 | 8804450.07 | 3684025.75 | 12488475.82
Berket Ghelion | 3 gheleon |  | Berket Ghelion | 1054874.93 | 629864.1 | 263718.75 | 893582.85
Beni-Suef Power Plant EPC | DEC ADJ 74 |  | Beni-Suef Power Plant EPC | 1868344294.99 | 300000000 | 0 | 300000000
Ismailiya East Substation | ISE-CW-EGP-19 | 19 | Ismailiya East Substation19 | 2021873 | 1496186.02 | 303280.95 | 1799466.97
Ismailiya East Substation | ISE-SD-EURO-02 | 2 | Ismailiya East Substation2 | 415477.11 | 338629.09 | 31145.54 | 369774.63
Tamey El-amdeed Substation | TAM-SW-EGP-10 | 10 | Tamey El-amdeed Substation10 | 350000 | 0 | 52500 | 52500
Tamey El-amdeed Substation | TAM-CW-EURO-07 | 7 | Tamey El-amdeed Substation7 | 910634.32 | 673869.4 | 136595.15 | 810464.55
Tamey El-amdeed Substation | TAM-CW-EGP-16 | 16 | Tamey El-amdeed Substation16 | 3130125.15 | 2316292.61 | 469518.77 | 2785811.38
Ismailiya East Substation | ISE-SW-EGP-03 | 3 | Ismailiya East Substation3 | 1730063 | 1280246.62 | 259509.45 | 1539756.07
Beni Suef Substation R61 | BSF-CW-EGP-16 | 16 | Beni Suef Substation R6116 | 4519671.75 | 3344557.09 | 677950.76 | 4022507.85
Tamey El-amdeed Substation | TAM-SW-EGP-06 | 6 | Tamey El-amdeed Substation6 | 774375 | 572427.4 | 116156.25 | 688583.65
Ismailiya East Substation | ISE-CW-EGP-13 | 13 | Ismailiya East Substation13 | 2014407 | 1490661.18 | 302161.05 | 1792822.23
Tamey El-amdeed Substation | 19100029 |  | Tamey El-amdeed Substation | 7806604.04 | 6557547.39 | 1170990.61 | 7728538
Tamey El-amdeed Substation | 19100018 |  | Tamey El-amdeed Substation | 3170363.04 | 2346068.65 | 475554.46 | 2821623.11
Tamey El-amdeed Substation | TAM-SW-EGP-03 | 3 | Tamey El-amdeed Substation3 | 1662500 | 1230250 | 249375 | 1479625
Beni Suef Substation R61 | BSF-CW-EUR-04 | 4 | Beni Suef Substation R614 | 660160.21 | 491819.36 | 99024.03 | 590843.39
Al Mostathmreen GIS Substation | MOS-SD-EURO-09 | 9 | Al Mostathmreen GIS Substation9 | 1774768.17 | 1286706.92 | 266215.23 | 1552922.15
Tamey El-amdeed Substation | TAM-SD-EURO-02 | 2 | Tamey El-amdeed Substation2 | 3063622.83 | 2588761.29 | 459543.43 | 3048304.72
Beni Suef Substation R61 | BSF-CW-EGP-9 | 9 | Beni Suef Substation R619 | 2915086 | 2171210.17 | 437262.9 | 2608473.07
Beni Suef Substation R61 | BINI SUEF SD-EG-IPC2 | 2 | Beni Suef Substation R612 | 212655 | 157932.21 | 31898.25 | 189830.46
Beni Suef Substation R61 | (4)cw beni suif | 4 | Beni Suef Substation R614 | 12888090 | 9601100.35 | 1933213.5 | 11534313.85
Al Mostathmreen GIS Substation | 19sd mosstasmreen |  | Al Mostathmreen GIS Substation | 3892392 | 2899694.34 | 583939.8 | 3483634.14
Al Mostathmreen GIS Substation | 12 cw mosstasmreen |  | Al Mostathmreen GIS Substation | 3371467 | 2511742.83 | 505720.1 | 3017462.93
Al Mostathmreen GIS Substation | MOS (2) | 2 | Al Mostathmreen GIS Substation2 | 1418842 | 1057037.16 | 212826.38 | 1269863.54
Al Mostathmreen GIS Substation | (14)SD EGP | 14 | Al Mostathmreen GIS Substation14 | 4364100 | 2875908.09 | 654615 | 3530523.09
Al-Shabab PP Phase II (CP-117) | 180129 |  | Al-Shabab PP Phase II (CP-117) | 106768.36 | 95470 | 16847.65 | 112317.65
Al-Shabab PP Phase II (CP-117) | 24 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 275367.2 | 245765.23 | 43370.33 | 289135.56
W Dam PP Phase II (CP-117) | 21 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 229506.4381 | 204834.5 | 36147.26 | 240981.76
W Dam PP Phase II (CP-117) | Adv. 6 USD - Domiat |  | W Dam PP Phase II (CP-117) | 34554.57 | 0 | 34554.57 | 34554.57
Al-Shabab PP Phase II (CP-117) | 180032 |  | Al-Shabab PP Phase II (CP-117) | 283629.7048 | 0 | 0 | 297811.19
Sodic Club House | SODIC CLUB-IPC 30 | 30 | Sodic Club House30 | 3864214.5 | 3772207.955 | 457665.76 | 4229873.715
Sodic Club House | (24) SODIC CLUB | 24 | Sodic Club House24 | 5827019 | 4702936.55 | 492791.84 | 5195728.39
Berket Ghelion | 2 ghelion |  | Berket Ghelion | 1054185.23 | 374553.85 | 263546.35 | 638100.2
Berket Ghelion | Gheleon 8 |  | Berket Ghelion | 5661090 | 3382272.35 | 1415272.5 | 4797544.85
Berket Ghelion | Gheleon 9 |  | Berket Ghelion | 2168291.8 | 1295466.6 | 542072.95 | 1837539.55
Sodic Club House | (18) SODIC CLUB | 18 | Sodic Club House18 | 3502070 | 2242406.65 | 683045.8 | 2925452.45
New Giza 2 | (22)new giza 2 | 22 | New Giza 222 | 5330400 | 3766112.21 | 1119384.19 | 4885496.4
EMAAR-PKG#53-UPTOWN | (24)pkg#53 | 24 | EMAAR-PKG#53-UPTOWN24 | 10899351 | 8522042.54 | 1665924.29 | 10187966.83
EMAAR-PKG#62-UPTOWN | (4) pkg#62 | 4 | EMAAR-PKG#62-UPTOWN4 | 2488472 | 1557907.49 | 896223.49 | 2454130.98
EMAAR-PKG#62-UPTOWN | (2) pkg#62 | 2 | EMAAR-PKG#62-UPTOWN2 | 1439963.03 | 954127.9315 | 518602.69 | 1472730.6215
EMAAR-PKG#107-MARASSI | (2) PKG#107 | 2 | EMAAR-PKG#107-MARASSI2 | 7583995 | 5882564.35 | 1104841.46 | 6987405.81
Berket Ghelion | 5 |  | Berket Ghelion | 7680073.2 | 4588843.68 | 1920018.3 | 6508861.98
Beni Seuf - 358 | Inv. 14 Oewon Mousa | 14 | Beni Seuf - 35814 | 26621468.3 | 0 | 4584283.15 | 4584283.15
Beni Seuf - 358 | Inv. 3 Oewon Mousa | 3 | Beni Seuf - 3583 | 54100230.27 | 37478143.6 | 9048054.44 | 46526198.04
Beni Seuf - 358 | Inv No 1 Abo matamir | 1 | Beni Seuf - 3581 | 164349234 | 130657641.03 | 24652385.1 | 155310026.13
New Capital | inv 3 ABO ZAABL | 3 | New Capital3 | 13724989.7 | 10650512.42 | 1441123.92 | 12091636.34
Al-Shabab PP Phase II (CP-117) | 6 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2584814.8617 | 2156279.45 | 392374.9 | 2615832.64
W Dam PP Phase II (CP-117) | 5 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 80929.5238 | 70046.78 | 12746.4 | 84976
Siemens 6x500/220 KV GIS-MOU | inv 43 P 11 maghaha | 43 | Siemens 6x500/220 KV GIS-MOU43 | 5068762.7 | 4173619.21 | 760314.41 | 4933933.62
Kayan 3 New Cairo Capital City | (1)elkayan mep | 1 | Kayan 3 New Cairo Capital City1 | 42618766.5 | 23793093.25 | 11000000 | 34793093.25
Giza North PP Ph I,II (CP-117) | 36 EGP-Giza No. I&II |  | Giza North PP Ph I,II (CP-117) | 3410847.2762 | 3156334.72 | 0 | 3161444.44
Giza North PP Ph I,II (CP-117) | Inv 38 Giza I,II EGP | 38 | Giza North PP Ph I,II (CP-117)38 | 19232.0762 | 20193.68 | 0 | 20193.68
South Helwan PP (CP-117) | 5 EGP - South Helwan |  | South Helwan PP (CP-117) | 110060.2 | 115563.21 | 0 | 115563.21
K047 FDH JV | Inv. No.14 KWD Floor | 14 | K047 FDH JV14 | 46962.58 | 42266.32 | 0 | 42266.32
Royal City | royal city-ipc21 | 21 | Royal City21 | 5449100.47 | 4449615.6735 | 2171112.14 | 6620727.8135
Royal City | ROYAL CITY-IPC19 | 19 | Royal City19 | 13865958.08 | 9999974.764 | 4561622.58 | 14561597.344
Royal City | ROYAL CITY- IPC 16 | 16 | Royal City16 | 8643111 | 7847127.4 | 3339460.9 | 11186588.3
Royal City | royal city- ipc(6) | 6 | Royal City6 | 16468073.59 | 12495801.3995 | 1991776.18 | 14487577.5795
Royal City | 4 royal city |  | Royal City | 9771128.39 | 10437271.5995 | 1978041.37 | 12415312.9695
Sodic Club House | (20) SODIC CLUB | 20 | Sodic Club House20 | 6271752 | 4786483.4 | 652247.67 | 5438731.07
New Heliopolis | Inv. 14 Heliopolise | 14 | New Heliopolis14 | 9889428.05 | 7854991.7 | 971141.84 | 8826133.54
New Heliopolis | Inv. 12 Heliopolise | 12 | New Heliopolis12 | 14257265.95 | 10545252.1 | 1400063.55 | 11945315.65
New Heliopolis | Inv. 11 Heliopolise | 11 | New Heliopolis11 | 6739225.68 | 1995725.2 | 246785.55 | 6468645.38
New Heliopolis | Inv. 9 Heliopolise | 9 | New Heliopolis9 | 11369259.7 | 9026182.05 | 1116461.35 | 10142643.4
New Heliopolis | Inv.3 Heliopolis | 3 | New Heliopolis3 | 17434357.5 | 13932862.5 | 1712053.95 | 15644916.45
New Heliopolis | Inv.2 Heliopolis | 2 | New Heliopolis2 | 1307027.35 | 427219.65 | 743412.6 | 1170632.25
Berket Ghelion | 4 |  | Berket Ghelion | 783945 | 468407.13 | 195986.25 | 664393.38
Barwa and Damac 220 OHTL | Inv. 1 Wattany 220 | 1 | Barwa and Damac 220 OHTL1 | 9000846.47 | 6271671.2 | 1350127 | 7621798.2
Siemens 6x500/220 KV GIS-MOU | Inv 47 P10 Banha | 47 | Siemens 6x500/220 KV GIS-MOU47 | 859781.95 | 621966.26 | 128967.29 | 750933.55
Siemens 6x500/220 KV GIS-MOU | Soc. 48 Wadi 13 |  | Siemens 6x500/220 KV GIS-MOU | 65762.69 | 65762.68 | 0 | 65762.68
Damac 2x60/22 KV S/S | 11 |  | Damac 2x60/22 KV S/S | 4981194.27 | 3221710.1 | 683140.5 | 4331774.87
Damac 2x60/22 KV S/S | Inv 29 Damac | 29 | Damac 2x60/22 KV S/S29 | 1921317.79 | 1359197.92 | 288197.67 | 1647395.59
Flour project | 10072 |  | Flour project | 129525.085 | 129525.005 | 0 | 129525.005
Siemens 6x500/220 KV GIS-MOU | inv 45 P 9 Banha | 45 | Siemens 6x500/220 KV GIS-MOU45 | 1258161.08 | 910153.73 | 188724.16 | 1098877.89
Barwa 2x60/22 KV S/S | Inv 27 Barwa | 27 | Barwa 2x60/22 KV S/S27 | 3197424.84 | 2261955.56 | 479613.74 | 2741569.3
South Helwan PP (CP-117) | 2009210004 |  | South Helwan PP (CP-117) | 149277.25 | 133480.55 | 23555.39 | 157035.94
W Dam PP Phase II (CP-117) | 12 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 256784.1143 | 229179.82 | 40443.5 | 269623.32
Al-Shabab PP Phase II (CP-117) | 10 USD-Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 889996.619 | 794321.98 | 140174.47 | 934496.45
South Helwan PP (CP-117) | 180139 |  | South Helwan PP (CP-117) | 218299.92 | 217221.36 | 0 | 217221.36
South Helwan PP (CP-117) | 180072 |  | South Helwan PP (CP-117) | 3090453.78 | 2763418.24 | 487662.04 | 3251080.28
South Helwan PP (CP-117) | 180071 |  | South Helwan PP (CP-117) | 146028.99 | 130576.02 | 23042.83 | 153618.85
South Helwan PP (CP-117) | 180062 |  | South Helwan PP (CP-117) | -201244.72 | -179948.77 | -31755.66 | -211704.43
South Helwan PP (CP-117) | 19 EGP Rev. 2 |  | South Helwan PP (CP-117) | 186278.98 | 166253.99 | 29338.94 | 195592.93
South Helwan PP (CP-117) | 14 EGP - South Helwa |  | South Helwan PP (CP-117) | 79351.92 | 70954.8 | 12521.44 | 83476.24
Suez Gulf Substation | 13 USD Suez Gulf |  | Suez Gulf Substation | 81842.19 | 81842.19 | 0 | 81842.19
Suez Gulf Substation | 6 USD Suez Gulf |  | Suez Gulf Substation | 334563.84 | 134563.84 | 0 | 134563.84
W Dam PP Phase II (CP-117) | 20 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 466026.0571 | 415928.26 | 73399.1 | 489327.36
Al-Shabab PP Phase II (CP-117) | 21 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 362995.381 | 323973.38 | 57171.77 | 381145.15
Beni Suef ISKRA | Iskra Inv 7 | 7 | Beni Suef ISKRA7 | 139090.69 | 118227.09 | 20863.6 | 139090.69
Abu Qir PP (CP-118) | Inv No AC017454 Avic |  | Abu Qir PP (CP-118) | 528790.94 | 528790.94 | 0 | 528790.94
Apache Electrical Works | Apachi Inv No PC.#25 |  | Apache Electrical Works | 82071.34 | 82071.34 | 0 | 82071.34
Beni Suef Substation R61 | (20)bine seuf 2 | 20 | Beni Suef Substation R6120 | 10654535 | 7387528.75 | 2639340.9 | 10026869.65
Sodic Club House | (23) sodic culb | 23 | Sodic Club House23 | 4559187 | 2843967.14 | 3462410.52 | 6306377.66
Tunnel of Sokhna Road | SOKHNA TUNNLE-FINAL |  | Tunnel of Sokhna Road | 1226927.69 | 2871215 | 567657.25 | 3438872.25
Al Mostathmreen GIS Substation | cw (7) mosstasmreen | 7 | Al Mostathmreen GIS Substation7 | 1714985 | 1277663.74 | 257247.8 | 1534911.54
Ghana | 30/P/10/ER/2017/USDD |  | Ghana | 281189.93 | 281187.43 | 0 | 281187.43
W Dam PP Phase II (CP-117) | 9 USD- West Domiat |  | W Dam PP Phase II (CP-117) | 70239.86 | 70239.86 | 0 | 70239.86
South Helwan PP (CP-117) | 7 EuroSouth Helwan |  | South Helwan PP (CP-117) | 18669.41 | 18669.41 | 0 | 18669.41
EMAAR-PKG#62-UPTOWN | (5) pkg#62 | 5 | EMAAR-PKG#62-UPTOWN5 | 3571360 | 2126676.82 | 1395651.53 | 3522328.35
Suez Gulf Substation | 14 EGP - Suez Gulf |  | Suez Gulf Substation | 4048783.0476 | 3902894.09 | 348328.11 | 4251222.2
Military 110 Kayan Project | Inv No1 ElKean 220 | 1 | Military 110 Kayan Project1 | 91633182.6 | 64333443.95 | 0 | 64333443.95
Beni Suef Substation R61 | (21)BINE SUIF 2 | 21 | Beni Suef Substation R6121 | 6009985 | 3530944.84 | 1330933.16 | 4861878
Barwa and Damac 220 OHTL | Inv No2 Wattanya220 | 2 | Barwa and Damac 220 OHTL2 | 6435005.73 | 4809754.28 | 965250.9 | 5775005.18
Kuraimate - Samalot 500KV | remaining advance |  | Kuraimate - Samalot 500KV | 22053.6 | 22053.6 | 0 | 22053.6
Al-Shabab PP Phase II (CP-117) | 5 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 873061.28 | 0 | 0 | 873061.28
Suez Gulf Substation | Inv 2 SG VO | 2 | Suez Gulf Substation2 | 71428.5714 | 67500 | 7500 | 75000
EMAAR-PKG#62-UPTOWN | (7) pkg#62 | 7 | EMAAR-PKG#62-UPTOWN7 | 2975812 | 1863217.83 | 1071738.87 | 2934956.7
Royal City | (2) royal city | 2 | Royal City2 | 4721022 | 4894014.77 | 930098.25 | 5824113.02
Al Mostathmreen GIS Substation | (11) CW | 11 | Al Mostathmreen GIS Substation11 | 1411925 | 1083124.51 | 211788.86 | 1294913.37
Ghana | 35/P/10/ER/2017/USD |  | Ghana | 117167.53 | 117165.03 | 0 | 117165.03
Kuwait | 2-132KVA-H | 132 | Kuwait132 | 46009.19 | 34506.88 | 0 | 34506.88
Amal Bridge Lock & Load | (1) ALAMAL BRIDGE | 1 | Amal Bridge Lock & Load1 | 18987162 | 7381482.4 | 6000000 | 17910234.2
Al-Shabab PP Phase II (CP-117) | 23 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 340212.3048 | 303639.48 | 53583.44 | 357222.92
Al-Shabab PP Phase II (CP-117) | 19 EGP -Shabab |  | Al-Shabab PP Phase II (CP-117) | 2478340.69 | 2211919.06 | 390338.66 | 2602257.72
Al-Shabab PP Phase II (CP-117) | 19 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 2580132 | 0 | 0 | 2709138.6
Akhmem Assiut | Inv.41 Assuit Akhmem | 41 | Akhmem Assiut41 | 2815401.73 | 2139705.31 | 422310.26 | 2562015.57
Akhmem Assiut | Inv.29 Assuit Akhmem | 29 | Akhmem Assiut29 | 4146362.89 | 2466557 | 621954.44 | 3088511.44
Akhmem Assiut | Inv.23 Assuit Akhmem | 23 | Akhmem Assiut23 | 13770214.33 | 10946791.69 | 2065532.15 | 13012323.84
Akhmem Assiut | Inv.1 Assuit / Akhme | 1 | Akhmem Assiut1 | 54753996.0608 | 32578627.6108 | 8213099.42 | 40791727.0308
Akhmem - Qena | Inv.42 Qena Akhmem | 42 | Akhmem - Qena42 | 11371428.68 | 7902614.02 | 1705714.3 | 9608328.32
Akhmem - Qena | Inv.31 Akhmem Qena | 31 | Akhmem - Qena31 | 6426120.19 | 4466153.53 | 963918.03 | 5430071.56
Akhmem - Qena | Inv.24 Akhmem Qena | 24 | Akhmem - Qena24 | 697914.13 | 554841.73 | 104687.12 | 659528.85
Akhmem - Qena | Inv.19 Qena - Akhmem | 19 | Akhmem - Qena19 | 7654643.15 | 6085441.3 | 1148196.47 | 7233637.77
Akhmem - Qena | Inv.13 Qena - Akhmem | 13 | Akhmem - Qena13 | 22634732.33 | 17994612.21 | 3395209.85 | 21389822.06
Bani Suef Old Substation | (23-24) bine suef2 | 24 | Bani Suef Old Substation24 | 7945021 | 21570743.94 | 0 | 21645237.44
W Dam PP Phase II (CP-117) | 26 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 730604.419 | 652064.44 | 115070.2 | 767134.64
W Dam PP Phase II (CP-117) | 28 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 837248.1333 | 747243.96 | 131866.58 | 879110.54
South Helwan PP (CP-117) | 16 EGP - South Helwa |  | South Helwan PP (CP-117) | 135908.81 | 121526.78 | 21445.9 | 142972.68
EMAAR-PKG#62-UPTOWN | OB-SI-PKG#62 |  | EMAAR-PKG#62-UPTOWN | 136616.41 | 135307.5 | 0 | 135307.5
Sodic Club House | IPC 25 Sodic club | 25 | Sodic Club House25 | 1334415.96 | 992455.088 | 367373.93 | 1359829.018
EMAAR-PKG#53-UPTOWN | (27) pkg#53 | 27 | EMAAR-PKG#53-UPTOWN27 | 11200624.22 | 10524733.29 | 1975581.31 | 12500314.6
Siemens 6x500/220 KV GIS-MOU | Ret. Maghaghah |  | Siemens 6x500/220 KV GIS-MOU | 3027063.98 | 3027063.98 | 0 | 3027063.98
Ismailiya East Substation | (2)CW esma3liya | 2 | Ismailiya East Substation2 | 4449390 | 3314795.55 | 667408.5 | 3982204.05
Ghana | 38/P/10/ER/2017/USD |  | Ghana | 597383.57 | 597369.07 | 0 | 597369.07
Sodic Club House | SODIC CLUB-IPC(29) | 29 | Sodic Club House29 | 6355200.49 | 6349192.7245 | 1525799.46 | 7874992.1845
Abou El Matameer and Sammanoud | Inv101 P13- Sammound | 101 | Abou El Matameer and Sammanoud101 | 1134164.257 | 814759.3749 | 170124.64 | 984884.0149
Abou El Matameer and Sammanoud | Inv102 P14- Sammound | 102 | Abou El Matameer and Sammanoud102 | 4372281.31 | 3578275.03 | 655842.2 | 4234117.23
Abou El Matameer and Sammanoud | Inv 90 P8- Sammound | 90 | Abou El Matameer and Sammanoud90 | 2776641.7 | 1994739.39 | 416496.26 | 2411235.65
Abou El Matameer and Sammanoud | Inv 89P10Abo Matamir | 89 | Abou El Matameer and Sammanoud89 | 2696183.68 | 1936938.35 | 404427.55 | 2341365.9
Abou El Matameer and Sammanoud | Abo Matamir 2 |  | Abou El Matameer and Sammanoud | 22131315.02 | 16009793.28 | 3319697.25 | 19329490.53
El Mostakbal City Project | Inv. 14 Mostakbal | 14 | El Mostakbal City Project14 | 24883709.07 | 19537665 | 5225578.9 | 24763243.9
El Mostakbal City Project | Inv. 13 Mostakbal | 13 | El Mostakbal City Project13 | 56614142.4 | 46989738.2 | 11888969.9 | 58878708.1
EMAAR-PKG#53-UPTOWN | (26)pkg#53 | 26 | EMAAR-PKG#53-UPTOWN26 | 18120127 | 14111649.09 | 2646190.12 | 16757839.21
Akhmem Assiut | inv. 2 Assuit Akhmem | 2 | Akhmem Assiut2 | 97876463.87 | 58236496.0392 | 14681469.57 | 72917965.6092
Badr | Inv. 26 Badr | 26 | Badr26 | 4555798.45 | 3133978.5 | 683369.8 | 3817348.3
Badr | Inv. 18 Badr | 18 | Badr18 | 10138245.91 | 615386.2 | 1520736.89 | 2136123.09
Badr | Inv. 11 Badr | 11 | Badr11 | 8380645.68 | 6222215.2 | 1257096.9 | 7479312.1
Badr | Inv. 7 Badr | 7 | Badr7 | 4936937.6 | 3665267.2 | 740540.65 | 4405807.85
Sodic Club House | (22)sodic club | 22 | Sodic Club House22 | 2015405 | 1742662.28 | 331069.04 | 2073731.32
Siemens 6x500/220 KV GIS-MOU | Inv 66 P19El Natroun | 66 | Siemens 6x500/220 KV GIS-MOU66 | 2481044.326 | 1794787.46 | 372156.65 | 2166944.11
Siemens 6x500/220 KV GIS-MOU | Inv 70 P9 Assuit | 70 | Siemens 6x500/220 KV GIS-MOU70 | 4499678.017 | 3255067.077 | 674951.7 | 3930018.777
EMAAR-PKG#107-MARASSI | (10) pkg#107 | 10 | EMAAR-PKG#107-MARASSI10 | 2025522 | 1551018.61 | 294867.37 | 1845885.98
EMAAR-PKG#53-UPTOWN | PKG#53-IPC 32 | 32 | EMAAR-PKG#53-UPTOWN32 | 4777477.68 | 2883132.62 | 1500499.95 | 4383632.57
Suez Gulf Substation | 180088 |  | Suez Gulf Substation | 3536.21 | 3720 | 0 | 3720
Siemens 6x500/220 KV GIS-MOU | Inv 72 P10 Assuit | 72 | Siemens 6x500/220 KV GIS-MOU72 | 4810720.93 | 3480075.52 | 721608.14 | 4201683.66
Military 110 Kayan Project | Inv. 8 Elkayan | 8 | Military 110 Kayan Project8 | 40307587.08 | 33287405.75 | 0 | 33287405.75
Military 110 Kayan Project | Inv. 9 Elkayan | 9 | Military 110 Kayan Project9 | 17854430.61 | 16123682.4 | 0 | 16123682.4
Suez Gulf Substation | 5 EGP-VO Shipping |  | Suez Gulf Substation | 958678.0762 | 905950.78 | 100661.2 | 1006611.98
Al Mostathmreen GIS Substation | 29sd elmostsmrin |  | Al Mostathmreen GIS Substation | 30622.5 | 22813.76 | 4593.38 | 27407.14
Mohamed Ali Palace Restoration | MOHAMED ALY-IPC01 | 1 | Mohamed Ali Palace Restoration1 | 36588393.1 | 26154902.9 | 7848900.9 | 34003803.8
Sodic Club House | SODIC CLUB-IPC34 | 34 | Sodic Club House34 | 7360347.44 | 6269587.212 | 797297.45 | 7066884.662
Akhmem Assiut | Inv.7 Assuit Akhmem | 7 | Akhmem Assiut7 | 2346262.04 | 1396025.91 | 351939.31 | 1747965.22
New Heliopolis | Inv.5 Heliopolis | 5 | New Heliopolis5 | 5941573.01 | 4747493.5 | 583462.5 | 5330956
Akhmem - Qena | Inv. 4 Akhmem Qena | 4 | Akhmem - Qena4 | 66780125.09 | 39734174.42 | 10017018.76 | 49751193.18
New Heliopolis | Inv.4 Heliopolis | 4 | New Heliopolis4 | 3078445.11 | 2458182.91 | 302303.3 | 2760486.21
EMAAR-PKG#53-UPTOWN | 18100062 |  | EMAAR-PKG#53-UPTOWN | 8335628.58 | 6775827.66 | 2812863.86 | 9588691.52
Sodic Club House | sodic culb-ipc36fin | 36 | Sodic Club House36 | 29270095.76 | 10543541.848 | 3624395.8275 | 14167937.6755
Al Mostathmreen GIS Substation | 14sd EURO |  | Al Mostathmreen GIS Substation | 347042.64 | 251605.91 | 52056.4 | 303662.31
Assuit PP (CP-118) | 220721005 |  | Assuit PP (CP-118) | 287213.19 | 256337.7795 | 45236.07 | 301573.8495
Assuit PP (CP-118) | 2110210007 |  | Assuit PP (CP-118) | 1073141.24 | 1126798.3 | 0 | 1126798.3
Assuit PP (CP-118) | 2105210005 |  | Assuit PP (CP-118) | 8792.516 | 9255.28 | 0 | 9255.28
Assuit PP (CP-118) | 2006210003 |  | Assuit PP (CP-118) | 391200 | 349146 | 61614 | 410760
Assuit PP (CP-118) | 510 |  | Assuit PP (CP-118) | 537594.53 | 479803.12 | 84671.14 | 564474.26
Assuit PP (CP-118) | 509 |  | Assuit PP (CP-118) | 309532.08 | 276257.38 | 48751.3 | 325008.68
Assuit PP (CP-118) | 1903210004 |  | Assuit PP (CP-118) | 162829.8 | 145325.6 | 25645.69 | 170971.29
Assuit PP (CP-118) | 2110210001 |  | Assuit PP (CP-118) | 21435135.47 | 22292540.89 | 0 | 22292540.89
Assuit PP (CP-118) | 2108210005 |  | Assuit PP (CP-118) | 1095754.59 | 957141.63 | 172581.35 | 1129722.98
Assuit PP (CP-118) | 2105210001 |  | Assuit PP (CP-118) | 1666445.9 | 1754153.58 | 0 | 1754153.58
Assuit PP (CP-118) | 2101210001 |  | Assuit PP (CP-118) | 4812655.59 | 4247168.46 | 757993.25 | 5005161.71
Assuit PP (CP-118) | 2107210001 |  | Assuit PP (CP-118) | 202587.46 | 542427.93 | 95722.56 | 212716.83
Assuit PP (CP-118) | 1905210004 |  | Assuit PP (CP-118) | 1630074.72 | 1385563.51 | 244511.21 | 1630074.72
South Helwan PP (CP-117) | 180015 |  | South Helwan PP (CP-117) | 366814.29 | 327997.56 | 57881.92 | 385879.48
South Helwan PP (CP-117) | Dr-Memo-Inv#18+20EGP | 18 | South Helwan PP (CP-117)18 | 45606.6 | 45606.6 | 0 | 45606.6
W Dam PP Phase II (CP-117) | 180095 |  | W Dam PP Phase II (CP-117) | 108597.48 | 97105.56 | 17136.28 | 114241.84
Marsa Matrouh 500KV | Inv.66 Borg Alarab | 66 | Marsa Matrouh 500KV66 | 7809555.43 | 5272170.77 | 820003.32 | 6092174.09
Marsa Matrouh 500KV | Inv.58 Borg Alarab | 58 | Marsa Matrouh 500KV58 | 255947.73 | 223572.84 | 26874.51 | 250447.35
Marsa Matrouh 500KV | Inv.57 Borg Alarab | 57 | Marsa Matrouh 500KV57 | 2458523.81 | 2147519.25 | 258145 | 2405664.25
Marsa Matrouh 500KV | Inv.42 Borg Alarab | 42 | Marsa Matrouh 500KV42 | 15403211.29 | 13454709.96 | 1617337.19 | 15072047.15
Marsa Matrouh 500KV | Inv.39 Borg Alarab | 39 | Marsa Matrouh 500KV39 | 12222654.28 | 10676488.4 | 1283378.7 | 11959867.1
Marsa Matrouh 500KV | Inv.26 Borg Alarab | 26 | Marsa Matrouh 500KV26 | 655957.14 | 572981.18 | 68875.5 | 641856.68
Marsa Matrouh 500KV | Inv.19 Borg Alarab | 19 | Marsa Matrouh 500KV19 | 3554680.69 | 3105013.7 | 373241.47 | 3478255.17
Marsa Matrouh 500KV | Inv.21Usd borg alarb | 21 | Marsa Matrouh 500KV21 | 65358.6 | 56633.6324 | 6862.65 | 63496.2824
Marsa Matrouh 500KV | Inv.9 Borg Alarab | 9 | Marsa Matrouh 500KV9 | 2843745.9 | 2484012.76 | 298593.32 | 2782606.08
Marsa Matrouh 500KV | Inv. 4 Borg Alarab | 4 | Marsa Matrouh 500KV4 | 10378117.8 | 9065289.96 | 1089702.37 | 10154992.33
Marsa Matrouh 500KV | Inv. 3 Borg Alarab | 3 | Marsa Matrouh 500KV3 | 10523603.44 | 9192367.02 | 1104978.36 | 10297345.38
Marsa Matrouh 500KV | Inv. 3 usd Borg Arab | 3 | Marsa Matrouh 500KV3 | 5305066.97 | 4620578.82 | 557032.03 | 5177610.85
Royal City | (1) royal city | 1 | Royal City1 | 3731890 | 5236267.51 | 994216.1 | 6230483.61
Akhmem Assiut | Inv.10 Assuit Akhmem | 10 | Akhmem Assiut10 | 3120723.9883 | 2460471.64 | 464239.93 | 2978872.8967
Siemens 6x500/220 KV GIS-MOU | Inv 78 P11 Assuit | 78 | Siemens 6x500/220 KV GIS-MOU78 | 1986409.19 | 1436968.4 | 297961.38 | 1734929.78
K047 FDH JV | Inv. No.13 KWD Floor | 13 | K047 FDH JV13 | 62138.64 | 55924.78 | 0 | 55924.78
Akhmem - Qena | Inv.11 Qena - Akhmem | 11 | Akhmem - Qena11 | 29704926.34 | 17674431.18 | 4455738.95 | 22130170.13
Akhmem - Qena | Inv.10 Qena - Akhmem | 10 | Akhmem - Qena10 | 13530422.5 | 10756685.89 | 2029563.38 | 12786249.27
MAYSAN 400/132kV SS | 201 |  | MAYSAN 400/132kV SS | 4798431.61 | 0 | 0 | 0
MOTHANA 400/132kV SS | 200 |  | MOTHANA 400/132kV SS | 4216144.83 | 0 | 0 | 0
Kayan 3 New Cairo Capital City | KAYAN FINSHING-IPC 4 | 4 | Kayan 3 New Cairo Capital City4 | 35496295 | 11062482.8 | 21150000 | 32212482.8
SHAT Al ARAB 400/132kV SS | 212 |  | SHAT Al ARAB 400/132kV SS | 5361669.87 | 5361669.87 | 0 | 5361669.87
Al Mostathmreen GIS Substation | 10 sd euro mostsmrin |  | Al Mostathmreen GIS Substation | 173242.08 | 125600.51 | 25986.31 | 151586.82
Cairo Capital S1 | Cr. 1% |  | Cairo Capital S1 | 0 | 0 | 0 | 0
Cairo Capital S1 | Final Credit |  | Cairo Capital S1 | 0 | 0 | -12387804.45 | -12387804.45
Tamey El-amdeed Substation | 18100063 |  | Tamey El-amdeed Substation | 3295440.04 | 2454573.85 | 494316.01 | 2948889.86
Beni Suef Substation R61 | 18100065 |  | Beni Suef Substation R61 | 2992524 | 2242929.38 | 448878.6 | 2691807.98
Ministries Buildings | MinisAlocation IPC08 | 8 | Ministries Buildings8 | 19178923.72 | 653919.99 | 15653924.9 | 16307844.89
EMAAR-PKG117- MARASSI | (1) pkg#117 | 1 | EMAAR-PKG117- MARASSI1 | 7803090.39 | 6865083.2495 | 819324.49 | 7684407.7395
New Giza 2 | NEW GIZA2- IPC 26 | 26 | New Giza 226 | 5057706.62 | 3584772.179 | 835258.8 | 4420030.979
Attaqa Power Plant | remaining Inv. 1 USD | 1 | Attaqa Power Plant1 | 67573333.34 | 67573333.34 | 0 | 67573333.34
Abo Quir - Badr 500KV | Ret.Part1 EGP |  | Abo Quir - Badr 500KV | 6253944.58 | 175120.05 | 0 | 175120.05
EMAAR-PKG117- MARASSI | 18100050 |  | EMAAR-PKG117- MARASSI | 4131277.05 | 3977930.2825 | 473909.65 | 4451839.9325
Akhmem Assiut | Inv.3 Assuit Akhmem$ | 3 | Akhmem Assiut3 | 5148236.69 | 4320494.29 | 0 | 4320494.29
Akhmem - Qena | Inv.6 Qena - Akhmem$ | 6 | Akhmem - Qena6 | 3012460.29 | 2558181.18 | 0 | 2558181.18
Akhmem - Qena | Inv.1 Qena - Akhmem$ | 1 | Akhmem - Qena1 | 2270390.51 | 1604817.44 | 0 | 1604817.44
Akhmem Assiut | Inv.13 Assuit Akhmem | 13 | Akhmem Assiut13 | 9813635.49 | 7801840.21 | 1472045.32 | 9273885.53
Akhmem Assiut | Inv.16 Assuit Akhmem | 16 | Akhmem Assiut16 | 3219311.35 | 2559352.52 | 482896.7 | 3042249.22
Akhmem Assiut | Inv.11 Assuit Akhmem | 11 | Akhmem Assiut11 | 66793963.3314 | 39460547.12 | 9948037.09 | 52298252.1286
Suez Gulf Substation | 180054 |  | Suez Gulf Substation | 5090.42 | 4819.5 | 535.5 | 5355
Substation Elco Steel | PSP ELCO-IPC 02 | 2 | Substation Elco Steel2 | 1669926.8 | 1160599.13 | 333985.36 | 1494584.49
Sodic Club House | IPC31-SODIC CLUB | 31 | Sodic Club House31 | 2806299.13 | 6752933.2165 | 603924.4 | 7356857.6165
EMAAR-PKG#107-MARASSI | 18100061 |  | EMAAR-PKG#107-MARASSI | 3636142.56 | 4202126.67 | 0 | 4202126.67
Akhmem - Qena | Inv.25 Akhmem Qena | 25 | Akhmem - Qena25 | 8788664.36 | 6252137.1 | 1318299.66 | 7570436.76
Akhmem - Qena | Inv.22 Akhmem Qena | 22 | Akhmem - Qena22 | 10941173.49 | 6509998.21 | 1641176.03 | 8151174.24
Akhmem - Qena | Inv.30 Akhmem Qena | 30 | Akhmem - Qena30 | 5411732.1 | 2678807.41 | 811759.83 | 3490567.24
Mohamed Ali Palace Restoration | Mohamed Aly - IPC04 | 4 | Mohamed Ali Palace Restoration4 | 7637765.43 | 3597182.7 | 3105457.05 | 6702639.75
EL-Hegaz Square Bridge | ELHEGAZ-IPC FINAL |  | EL-Hegaz Square Bridge | 5915483.87 | 0 | 16091824.758 | 17047344.758
New bridge Ismailiya Nefisha | NFISHA BRIDGE-IPC01 | 1 | New bridge Ismailiya Nefisha1 | 51811685.08 | 12381198.65 | 3000000 | 42498928.65
Beni Suef Substation R61 | 18100067 |  | Beni Suef Substation R61 | 1837500 | 1368937.5 | 275625 | 1644562.5
Beni Suef Substation R61 | 18100066 |  | Beni Suef Substation R61 | 558884.47 | 405191.24 | 83832.67 | 489023.91
Akhmem - Qena | Inv.2 Qena - Akhmem$ | 2 | Akhmem - Qena2 | 200830.69 | 169676.91 | 0 | 169676.91
Akhmem - Qena | Inv.20 Qena- Akhmem$ | 20 | Akhmem - Qena20 | 1517387.42 | 1282168.99 | 0 | 1282168.99
Akhmem - Qena | Inv.37 Akhmem Qena | 37 | Akhmem - Qena37 | 8568.16 | 5954.86 | 1285.22 | 7240.08
Akhmem Assiut | Inv.28 Assuit Akhmem | 28 | Akhmem Assiut28 | 15695290.1 | 12477755.62 | 2354293.52 | 14832049.14
P-28-16 Balat Owinat Lot 3 | Inv. 12 Balat lot 3 | 12 | P-28-16 Balat Owinat Lot 312 | 3737851.54 | 2791779.12 | 392474.41 | 3184253.53
P-28-16 Balat Owinat Lot 3 | Inv. 7 Balat lot 3 | 7 | P-28-16 Balat Owinat Lot 37 | 2058983.71 | 1537666.88 | 216193.29 | 1753860.17
P-28-16 Balat Owinat Lot 3 | Inv. 5 Balat lot 3 | 5 | P-28-16 Balat Owinat Lot 35 | 8978757.19 | 6706735.64 | 942769.51 | 7649505.15
P-28-16 Balat Owinat Lot 3 | Inv. 1 Balat lot 3 | 1 | P-28-16 Balat Owinat Lot 31 | 11498554.02 | 8589022.06 | 1207348.17 | 9796370.23
Elsewedy Univ - Enabling Works | 19100032 |  | Elsewedy Univ - Enabling Works | 205504.2 | 142702.12 | 64733.82 | 207435.94
Elsewedy Univ - Enabling Works | ELSEWEDY UNY-IPC03 | 3 | Elsewedy Univ - Enabling Works3 | 1749696.33 | 1214989.1265 | 551154.35 | 1766143.4765
Elsewedy Univ - Enabling Works | ELSWEDY-UN-MEP-IPC02 | 2 | Elsewedy Univ - Enabling Works2 | 4165158.06 | 3110956.553 | 874683.19 | 3985639.743
Elsewedy Univ - Enabling Works | EL SEWEDY UNI-IPC-02 | 2 | Elsewedy Univ - Enabling Works2 | 2762087.04 | 1917993.242 | 870057.42 | 2788050.662
NUCA R05 - Z02 | R5-IPC27 | 27 | NUCA R05 - Z0227 | 12195893.27 | 8400109.47 | 1073714.35 | 9473823.82
NUCA R05 - Z02 | R5 - IPC20 | 20 | NUCA R05 - Z0220 | 40939275.15 | 33414942.65 | 4099408.55 | 37514351.2
NUCA R05 - Z02 | R5 - IPC 19 | 19 | NUCA R05 - Z0219 | 86399294.85 | 66398297.5 | 8301205.5 | 74699503
NUCA R05 - Z02 | R5 - IPC14 | 14 | NUCA R05 - Z0214 | 48665536.25 | 37605923.5 | 4699561.65 | 42305485.15
NUCA R05 - Z02 | R5-IPC013 | 13 | NUCA R05 - Z0213 | 35089427.4 | 21697982.73 | 2763742.75 | 24461725.48
NUCA R05 - Z02 | R5 - IPC11 | 11 | NUCA R05 - Z0211 | 35072197.95 | 29923408.95 | 3712337.3 | 33635746.25
R5 Mix-Use Complex Project | R5 ZONE1- IPC05 | 5 | R5 Mix-Use Complex Project5 | 12663442.81 | 10925527.29 | 1338513.24 | 12264040.53
R5 Mix-Use Complex Project | R5-ZONE1-IPC 01 | 1 | R5 Mix-Use Complex Project1 | 18101215.9 | 17393287.24 | 2144069.05 | 19537356.29
South Helwan PP (CP-117) | South Helwan inv.ded |  | South Helwan PP (CP-117) | 0 | -5827.6 | 0 | -5827.6
South Helwan PP (CP-117) | 180134 |  | South Helwan PP (CP-117) | 357494.32 | 386131.21 | 0 | 386131.21
Royal City | ROYAL CITY -IPC 10 | 10 | Royal City10 | 7808914.21 | 5842887.9205 | 1102431.68 | 6945319.6005
Mohamed Ali Palace Restoration | PO - Mohamed Aly 107 |  | Mohamed Ali Palace Restoration | 486912.65 | 345055 | 115022.3 | 460077.3
Ministries Buildings | MIN-FIT OUT-IPC04 | 4 | Ministries Buildings4 | 3272449.8 | 877175 | 1920769.33 | 2797944.33
Akhmem Assiut | Inv.19 Assuit Akhmem | 19 | Akhmem Assiut19 | 31146513.1 | 18532175.28 | 4671976.97 | 23204152.25
Akhmem Assiut | Inv.18 Assuit Akhmem | 18 | Akhmem Assiut18 | 10588594.32 | 8417932.49 | 1588289.15 | 10006221.64
Akhmem - Qena | Inv.20 Qena - Akhmem | 20 | Akhmem - Qena20 | 8032650.24 | 6385956.94 | 1204897.54 | 7590854.48
Beni Seuf - 358 | Inv.5 Beni Souf 358 | 5 | Beni Seuf - 3585 | 6081377.46 | 4834166.15 | 912206.65 | 5746372.8
Ministries Buildings | MINISTIRY-IPC 1 | 1 | Ministries Buildings1 | 509004396 | 54035277 | 171000000 | 456293797
New Heliopolis | Inv.8. Heliopolis | 8 | New Heliopolis8 | 11772146.9 | 9407047.7 | 1156024.85 | 10563072.55
Akhmem Assiut | Inv.16Assuit Akhmem$ | 16 | Akhmem Assiut16 | 1844140.24 | 1564199.11 | 0 | 1564199.11
Beni Suef COMCAVI | 180117 |  | Beni Suef COMCAVI | 1692.37 | 1692.36 | 0.01 | 1692.37
Marsa Matrouh 500KV | Inv.4 Usd borg alarb | 4 | Marsa Matrouh 500KV4 | 1278838.88 | 1116174 | 134278.08 | 1250452.08
Canal Regional Control Center | Inv.9 Rcc | 9 | Canal Regional Control Center9 | 7592326.84 | 4600900.6 | 1594388.64 | 6195289.24
Marsa Matrouh 500KV | Inv.6 Usd borg alarb | 6 | Marsa Matrouh 500KV6 | 1278838.88 | 1111185.2753 | 134278.08 | 1245463.3553
Marsa Matrouh 500KV | Inv.7 Usd borg alarb | 7 | Marsa Matrouh 500KV7 | 1053161.82 | 919198.7435 | 110581.99 | 1029780.7335
P-28-16 Balat Owinat Lot 2 | Inv. 16 Balat Lot 2 | 16 | P-28-16 Balat Owinat Lot 216 | 6149117.66 | 866294.3 | 3747170.08 | 4613464.38
P-28-16 Balat Owinat Lot 2 | Inv. 14 Balat Lot 2 | 14 | P-28-16 Balat Owinat Lot 214 | 17486066.67 | 11313091.93 | 1836036.996 | 13149128.926
Sodic Club House | SODIC CLUB-IPC-33 | 33 | Sodic Club House33 | 6742632.54 | 5855002.737 | 1015115.8 | 6870118.537
El Boghaz Brigde | 10004 |  | El Boghaz Brigde | 2960083.5 | 2960083.5 | 0 | 2960083.5
P-28-16 Balat Owinat Lot 2 | Inv. 2 Balat Lot 2 | 2 | P-28-16 Balat Owinat Lot 22 | 3984852.38 | 2996213.88 | 418409.5 | 3414623.38
Akhmem - Qena | ints 20%Q3-11-22-41ض | 11 | Akhmem - Qena11 | 7885398.68 | 7884869.77 | 0 | 7884869.77
Akhmem - Qena | Inv.38 Akhmem Qena | 38 | Akhmem - Qena38 | 386676.68 | 268740.28 | 58001.5 | 326741.78
Akhmem - Qena | Inv.19 Qena- Akhmem$ | 19 | Akhmem - Qena19 | 1066345.9 | 902025.21 | 0 | 902025.21
Akhmem - Qena | Inv.18 Qena- Akhmem$ | 18 | Akhmem - Qena18 | 2075250.42 | 1744206.53 | 0 | 1744206.53
Akhmem - Qena | Inv.17 Qena- Akhmem$ | 17 | Akhmem - Qena17 | 145713.66 | 117272.46 | 0 | 117272.46
Akhmem - Qena | Inv.4 Qena - Akhmem$ | 4 | Akhmem - Qena4 | 3029589.88 | 2550157.16 | 0 | 2550157.16
W Dam PP Phase II (CP-117) | 180146 |  | W Dam PP Phase II (CP-117) | 2642.57 | 2362.93 | 416.99 | 2779.92
PIP- Zonafranca | Sett. Inv. Zona |  | PIP- Zonafranca | 16936102.15 | 13174716.3368 | 0 | 13174716.3368
Akhmem Assiut | Soci.29:33EGP Assuit |  | Akhmem Assiut | 820565.8 | 820565.8 | 0 | 820565.8
Akhmem Assiut | Inv.19Assuit Akhmem$ | 19 | Akhmem Assiut19 | 695510.92 | 587529.12 | 0 | 587529.12
Akhmem Assiut | Inv.4 Assuit Akhmem$ | 4 | Akhmem Assiut4 | 2023.28 | 1198.45 | 0 | 1198.45
Substation Elco Steel | PSP ELCO-IPC04 | 4 | Substation Elco Steel4 | 1838590.86 | 1268627.7 | 367718.17 | 1636345.87
NUCA R05 - Z02 | R05 - IPC028 | 28 | NUCA R05 - Z0228 | 1730474.75 | 1265141.05 | 160837.5 | 1425978.55
Akhmem Assiut | Inv.43 Assuit Akhmem | 43 | Akhmem Assiut43 | 1314333.18 | 985138.27 | 197149.98 | 1182288.25
Tamey El-amdeed Substation | (1) CW .TAM | 1 | Tamey El-amdeed Substation1 | 7657332.77 | 5704712.91 | 1148599.92 | 6853312.83
AWEER POWER STATION 'H' Phase | LOC/025 |  | AWEER POWER STATION 'H' Phase | 612800.38 | 537902.55 | 68088.93 | 605991.48
AWEER POWER STATION 'H' Phase | IMP/070 |  | AWEER POWER STATION 'H' Phase | 72124.99 | 47782.7993 | 18031.25 | 65814.0493
AWEER POWER STATION 'H' Phase | LOC/020 |  | AWEER POWER STATION 'H' Phase | 288571.16 | 253301.3498 | 32063.46 | 285364.8098
AWEER POWER STATION 'H' Phase | LOC/021 |  | AWEER POWER STATION 'H' Phase | 2202248.84 | 1933085.09 | 244694.32 | 2177779.41
AWEER POWER STATION 'H' Phase | IMP/065 |  | AWEER POWER STATION 'H' Phase | 597697.12 | 395974.3394 | 149424.28 | 545398.6194
AWEER POWER STATION 'H' Phase | CON/023 |  | AWEER POWER STATION 'H' Phase | 425899.55 | 373845.1575 | 47322.17 | 421167.3275
AWEER POWER STATION 'H' Phase | CON/018 |  | AWEER POWER STATION 'H' Phase | 10221589.19 | 10108015.972 | 0 | 10108015.972
AWEER POWER STATION 'H' Phase | 10408 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
AWEER POWER STATION 'H' Phase | 10407 |  | AWEER POWER STATION 'H' Phase | 958273.98 | 841151.609 | 106474.89 | 947626.499
AWEER POWER STATION 'H' Phase | 10327 |  | AWEER POWER STATION 'H' Phase | 2591086.05 | 2274397.7525 | 287898.45 | 2562296.2025
AWEER POWER STATION 'H' Phase | 10328 |  | AWEER POWER STATION 'H' Phase | 2141093.13 | 1879403.9665 | 237899.24 | 2117303.2065
AWEER POWER STATION 'H' Phase | 10287 |  | AWEER POWER STATION 'H' Phase | 4321381.71 | 1272406.83 | 3000959.5238 | 4273366.3538
AWEER POWER STATION 'H' Phase | 10172 |  | AWEER POWER STATION 'H' Phase | 31169386.77 | 30823060.2485 | 0 | 30823060.2485
P-28-16 Balat Owinat Lot 3 | Inv. 3 Balat lot 3 | 3 | P-28-16 Balat Owinat Lot 33 | 16666140.62 | 12449214.67 | 1749944.77 | 14199159.44
P-28-16 Balat Owinat Lot 2 | Inv. 3 Balat Lot 2 | 3 | P-28-16 Balat Owinat Lot 23 | 138801.49 | 103289.16 | 14574.16 | 117863.32
El Boghaz Brigde | IPC#16 | 16 | El Boghaz Brigde16 | 2447010 | 2250939.4 | 0 | 2250939.4
EDNC Retail & Offices Civil | Sodic Soreal IPC028 | 28 | EDNC Retail & Offices Civil28 | 37125243.76 | 26708616.218 | 111564.97 | 26820181.188
EDNC Retail & Offices Civil | SOREAL-IPC20 | 20 | EDNC Retail & Offices Civil20 | 45598330.5 | 31197031.845 | 3213756.88 | 34410788.725
EDNC Retail & Offices Civil | SOREAL-IPC19 | 19 | EDNC Retail & Offices Civil19 | 45752255.09 | 30462891.204 | 2757896.6 | 33220787.804
EDNC Retail & Offices Civil | SOREAL-IPC05 | 5 | EDNC Retail & Offices Civil5 | 50370296.9 | 37056568.405 | 11141101.87 | 48197670.275
EDNC Retail & Offices Civil | SOREAL-IPC03 | 3 | EDNC Retail & Offices Civil3 | 2101069.44 | 1574016.182 | 441224.58 | 2015240.762
Abou El Matameer and Sammanoud | Social 13 Matamir |  | Abou El Matameer and Sammanoud | 43758.1 | 43758.08 | 0 | 43758.08
Marsa Matrouh 500KV | Inv.14Usd borg alarb | 14 | Marsa Matrouh 500KV14 | 543102.44 | 472678.5791 | 57025.76 | 529704.3391
Beni Suef Substation R61 | BSF-CW-10 | 10 | Beni Suef Substation R6110 | 1355795 | 1010067.27 | 203369.25 | 1213436.52
Beni Suef Substation R61 | BSF-CW-EUR-03 | 3 | Beni Suef Substation R613 | 1571844.23 | 1171023.96 | 235776.63 | 1406800.59
New Capital Tunnels | M.B.Z TUNNLE-IPC5 | 5 | New Capital Tunnels5 | 14354311.59 | 6080870.45 | 6080874 | 12954361.45
EMAAR-PKG# 101-UPTOWN | PKG#101 -IPC04 | 4 | EMAAR-PKG# 101-UPTOWN4 | 1896917.55 | 2246109.51 | 1168966.28 | 3415075.79
Mall Of Egypt | MALL EGYPT-FINAL 2 |  | Mall Of Egypt | 22665950.54 | 27653663.75 | 0 | 27653663.75
Tamey El-amdeed Substation | TAM-CW-EGP-09 | 9 | Tamey El-amdeed Substation9 | 2847217.55 | 2106940.99 | 427082.63 | 2534023.62
EMAAR-PKG#62-UPTOWN | PKG#62-IPC-15 | 15 | EMAAR-PKG#62-UPTOWN15 | 1329599.07 | 5710409.5735 | 0 | 5710409.5735
Abou El Matameer and Sammanoud | Social 14 Matamir |  | Abou El Matameer and Sammanoud | 78199.75 | 78199.75 | 0 | 78199.75
Asec Spare-Parts | Inv 1 EUR Asec Spare | 1 | Asec Spare-Parts1 | 332173.8 | 0 | 373175.87 | 373175.87
DPW Onshore Port & Terminal | DP WORLD-IPC04 | 4 | DPW Onshore Port & Terminal4 | 20754393.51 | 15357944.03 | 3113159.03 | 18471103.06
DPW Onshore Port & Terminal | DP WORLD -IPC02 | 2 | DPW Onshore Port & Terminal2 | 24408793.92 | 18062199.23 | 3661319.09 | 21723518.32
DPW Onshore Port & Terminal | DPW IPC34 | 34 | DPW Onshore Port & Terminal34 | 12548237.84 | 8899770.35 | 2268161.33 | 11167931.68
DPW Onshore Port & Terminal | DP WORLD-IPC25 | 25 | DPW Onshore Port & Terminal25 | 13937299.51 | 10313601.63 | 2090594.93 | 12404196.56
DPW Onshore Port & Terminal | DP WORLD-IPC19 | 19 | DPW Onshore Port & Terminal19 | 34366362.95 | 25431108.58 | 5154954.44 | 30586063.02
DPW Onshore Port & Terminal | DP WORLD -IPC18 | 18 | DPW Onshore Port & Terminal18 | 59878397.73 | 44310014.32 | 8981759.66 | 53291773.98
C5 Bridge 2 New Alamein | IPC# 1 | 1 | C5 Bridge 2 New Alamein1 | 1571000 | 1523870 | 0 | 1523870
Akhmem - Qena | Inv.45 Qena Akhmem | 45 | Akhmem - Qena45 | 10746993.68 | 7401028.2 | 1612049.05 | 9013077.25
Assuit PP (CP-118) | 180164 |  | Assuit PP (CP-118) | 125735.38 | 112218.83 | 19803.32 | 132022.15
Marsa Matrouh 500KV | Inv.10 Borg Alarab | 10 | Marsa Matrouh 500KV10 | 58454700.72 | 50858223.23 | 6137743.58 | 56995966.81
Marsa Matrouh 500KV | Inv.7 Borg Alarab | 7 | Marsa Matrouh 500KV7 | 3453119.23 | 3016303.72 | 362577.52 | 3378881.24
Manshiet Nasser Substation | 180173 |  | Manshiet Nasser Substation | 949135.31 | 996592.08 | 0 | 996592.08
Zafranaa - Ras Ghareb | Advance invoice due |  | Zafranaa - Ras Ghareb | 376090.02 | 50000 | 0 | 58034.1
Elsewedy Univ - Enabling Works | UNI FI&MEP -IPC06 | 6 | Elsewedy Univ - Enabling Works6 | 33456554.93 | 19684684.46 | 7876979.84 | 27561664.3
Elsewedy Univ - Enabling Works | SEWEDY UNI MEP-IPC06 | 6 | Elsewedy Univ - Enabling Works6 | 8105230.79 | 7457796.8695 | 1702098.47 | 9159895.3395
Al Mostathmreen GIS Substation | MOS-SD-EGP-28 | 28 | Al Mostathmreen GIS Substation28 | 10207.5 | 3205336.71 | 1531.13 | 3206867.84
Tamey El-amdeed Substation | 19100028 |  | Tamey El-amdeed Substation | 1605178.4 | 1187832.02 | 240776.76 | 1428608.78
Akhmem Assiut | Inv.6 Assuit Akhmem | 6 | Akhmem Assiut6 | 2453962.67 | 1460107.79 | 368094.4 | 1828202.19
Akhmem Assiut | Inv.35 Assuit Akhmem | 35 | Akhmem Assiut35 | 18483513.92 | 10997161.89 | 2772527.09 | 13769688.98
Kuwait | Civil/H011 |  | Kuwait | 33876.01 | 25407.01 | 0 | 25407.01
Akhmem - Qena | Ref. Insral 1 $ Qena |  | Akhmem - Qena | 1801758.09 | 1762008 | 0 | 1762008
kayan wall lock & Load | 19100016 |  | kayan wall lock & Load | 11712600 | 10570220.8 | 0 | 10570220.8
EMAAR-PKG#53-UPTOWN | 19100046 |  | EMAAR-PKG#53-UPTOWN | 1320000 | 1156584 | 0 | 1156584
Abu Sultan Road Extension | Abu soultan -ipc 1 | 1 | Abu Sultan Road Extension1 | 17732625.58 | 1785123.35 | 1721657.85 | 14787256.2
P-28-16 Balat Owinat Lot 2 | Inv. 5 Balat Lot 2 | 5 | P-28-16 Balat Owinat Lot 25 | 13925519.05 | 10401964.62 | 1462179.5 | 11864144.12
Akhmem - Qena | Inv.26 Qena- Akhmem$ | 26 | Akhmem - Qena26 | 344866.84 | 282634.2165 | 0 | 282634.2165
Flour project | 10049 |  | Flour project | 227629.106 | 227629.106 | 0 | 227629.106
RME-Abu Sultan Bridge | IPC#3 | 3 | RME-Abu Sultan Bridge3 | 1149500 | 1138005 | 0 | 1138005
RME-Abu Sultan Bridge | Final Invice |  | RME-Abu Sultan Bridge | 756050 | 736639.5 | 0 | 736639.5
kayan wall lock & Load | KAYAN RADM2-IPC01 | 1 | kayan wall lock & Load1 | 4000000 | 2503435 | 1001140 | 3504575
Development of Mahmudiyah axis | FPC |  | Development of Mahmudiyah axis | 900000 | 859800 | 0 | 859800
Substation Elco Steel | PSP-ELCO-IPC07 | 7 | Substation Elco Steel7 | 3187107.5 | 2228843.15 | 607682.54 | 2836525.69
Substation Elco Steel | PSP-ELCO-IPC 06 | 6 | Substation Elco Steel6 | 3766431.24 | 2598837.56 | 753286.25 | 3352123.81
P-28-16 Balat Owinat Lot 3 | Inv. 6 Balat lot 3 | 6 | P-28-16 Balat Owinat Lot 36 | 36165596.5 | 27015303.16 | 3797387.63 | 30812690.79
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC12 | 12 | EMAAR- Pkg 140-ITP-Mivida12 | 1875812.84 | 4687303.232 | 599801.18 | 5287104.412
EMAAR- Pkg 140-ITP-Mivida | PKG#140 -IPC08 | 8 | EMAAR- Pkg 140-ITP-Mivida8 | 6113446.74 | 5253107.1475 | 607173.66 | 5860280.8075
HAC CCC JV | IPC#9 | 9 | HAC CCC JV9 | 2004324 | 1847986.73 | 0 | 1847986.73
Kayan 3 New Cairo Capital City | EL KAYAN-IPC FINAL |  | Kayan 3 New Cairo Capital City | 179948517.95 | 74379903.95 | 0 | 161801582.45
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC 07 | 7 | Elsewedy Univ - Enabling Works7 | 410253.12 | 284879.766 | 129229.73 | 414109.496
Beni Suef Substation R61 | 19100024 |  | Beni Suef Substation R61 | 1589921 | 1176541.54 | 238488.15 | 1415029.69
Tamey El-amdeed Substation | TAM-CW-EURO-04 | 4 | Tamey El-amdeed Substation4 | 1899677.92 | 1405761.66 | 284951.69 | 1690713.35
Manshiet Nasser Substation | 2008210010 |  | Manshiet Nasser Substation | 3197756.28 | 0 | 479663.44 | 479663.44
Manshiet Nasser Substation | 2002210022 |  | Manshiet Nasser Substation | 3847.66 | 827.55 | 577.15 | 1404.7
Manshiet Nasser Substation | 2001210019 |  | Manshiet Nasser Substation | 157776.72 | 118565.85 | 25393.99 | 143959.84
Manshiet Nasser Substation | 1901210017 |  | Manshiet Nasser Substation | 5428.57 | 5089.96 | 555.75 | 5645.71
Manshiet Nasser Substation | 1908210019 |  | Manshiet Nasser Substation | 22917.97 | 18170.76 | 3437.7 | 21608.46
El Mostakbal City Project | Inv. 2 Mostakbal | 2 | El Mostakbal City Project2 | 10792497.87 | 8956071.67 | 2266424.55 | 11222496.22
Akhmem Assiut | Inv.36 Assuit Akhmem | 36 | Akhmem Assiut36 | 2816945.25 | 1676082.41 | 422541.79 | 2098624.2
Akhmem Assiut | Inv.32 Assuit Akhmem | 32 | Akhmem Assiut32 | 6237116.6 | 4958507.69 | 935567.49 | 5894075.18
Akhmem Assiut | Inv.26 Assuit Akhmem | 26 | Akhmem Assiut26 | 8568.16 | 6811.68 | 1285.22 | 8096.9
Akhmem Assiut | Inv.17 Assuit Akhmem | 17 | Akhmem Assiut17 | 25765250.1 | 15330323.81 | 3864787.52 | 19195111.33
New Capital | Inv. 6 Eltbeen | 6 | New Capital6 | 519950.32 | 377465.49 | 54594.78 | 432060.27
EMAAR-PKG# 144, Marassi | PKG#144 - IPC07 | 7 | EMAAR-PKG# 144, Marassi7 | 20465525.62 | 12627238.511 | 6479678.86 | 19106917.371
EMAAR-PKG# 144, Marassi | PKG#144 - IPC8 | 8 | EMAAR-PKG# 144, Marassi8 | 16360599.32 | 8934848.896 | 3164355.69 | 12099204.586
New Capital | Inv. 9 Abo Zabal | 9 | New Capital9 | 1629223.77 | 1182729.97 | 171068.5 | 1353798.47
Elsewedy Univ - Enabling Works | UNI -FIN&MEP-IPC02 | 2 | Elsewedy Univ - Enabling Works2 | 1535126.31 | 3185421.0755 | 0 | 3185421.0755
P-28-16 Balat Owinat Lot 2 | Inv. 7 Balat Lot 2 | 7 | P-28-16 Balat Owinat Lot 27 | 32063076.51 | 23950725.04 | 3366623.03 | 27317348.07
Mauritania-Lot 2 | Inv.7 – Lot 2 | 7 | Mauritania-Lot 27 | 268557.09 | 255129.24 | 0 | 255129.24
Mauritania Lot 1 | Inv.7 - Lot 1 | 7 | Mauritania Lot 17 | 1773715.17 | 1684999.41 | 0 | 1684999.41
Substation Elco Steel | PSP ELCO-IPC-08 | 8 | Substation Elco Steel8 | 2651758.28 | 1829713.22 | 530351.66 | 2360064.88
El Boghaz Brigde | IPC#18 | 18 | El Boghaz Brigde18 | 1141351.02 | 1072869.96 | 0 | 1072869.96
Cameron EDC | 007/2018 |  | Cameron EDC | 867905.03 | 867070.07 | 0 | 867070.07
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC09 | 9 | Elsewedy Univ - Enabling Works9 | 104806.23 | 258721.9915 | 33013.96 | 291735.9515
Air Defense College | air defense(2) ipc01 | 1 | Air Defense College1 | 50231345.82 | 13182605 | 5900000 | 41477425
Alamein Coastal Road Bridge | Alamein bridge ipc01 | 1 | Alamein Coastal Road Bridge1 | 227857516.19 | 40221875 | 46800000 | 213711604.9995
Kayan 3 New Cairo Capital City | KAYAN SAHY-IPC03 | 3 | Kayan 3 New Cairo Capital City3 | 6042938 | 874466.9 | 5341846.25 | 6216313.15
Ministries Buildings | MIN.ALLOCATION-IPC04 | 4 | Ministries Buildings4 | 22501315.97 | 7703215 | 11478750.3 | 19181965.3
Ministries Buildings | MIN-ELCTROMIK-IPC02 | 2 | Ministries Buildings2 | 184148104 | 101591695 | 55364904 | 156956599
Kayan 3 New Cairo Capital City | KAYAN MEP- IPC5 | 5 | Kayan 3 New Cairo Capital City5 | 19786515 | 18381367.45 | 12079435.45 | 30460802.9
MAYSAN 400/132kV SS | 228 |  | MAYSAN 400/132kV SS | 1126195.85 | 1125384.76 | 0 | 1125384.76
South Helwan PP (CP-117) | 1901210012 |  | South Helwan PP (CP-117) | 241539.51 | 276764.02 | 0 | 276764.02
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC05 | 5 | EMAAR-PKG# 101-UPTOWN5 | 4428897.72 | 2512749.703 | 1301295.53 | 3814045.233
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 20 | 20 | Benban 500 K.V/95 K.M20 | 16047120.51 | 13174693.03 | 1684947.65 | 14859640.68
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 28 | 28 | Benban 500 K.V/95 K.M28 | 83461.1 | 64355.64 | 8763.42 | 73119.06
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 27 | 27 | Benban 500 K.V/95 K.M27 | 2840729.66 | 2190203.14 | 298276.61 | 2488479.75
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 29 | 29 | Benban 500 K.V / 100 K.M29 | 415439.94 | 320311.16 | 43621.19 | 363932.35
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 23 | 23 | Benban 500 K.V / 100 K.M23 | 14580822.99 | 11241224.59 | 1530986.41 | 12772211
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 10 | 10 | Benban 500 K.V / 100 K.M10 | 104470 | 80553.6 | 10969.35 | 91522.95
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 9 | 9 | Benban 500 K.V / 100 K.M9 | 340490.56 | 262525.63 | 35751.51 | 298277.14
Assuit PP (CP-118) | 1903210003 |  | Assuit PP (CP-118) | 284204.9 | 253652.87 | 44762.27 | 298415.14
Cameron EDC | 016/2019 |  | Cameron EDC | 1185.83 | 1126.83 | 0 | 1126.83
Marsa Matrouh 500KV | Inv.16 Borg Alarab | 16 | Marsa Matrouh 500KV16 | 4512426.67 | 3941611.3 | 473804.8 | 4415416.1
EMAAR-PKG117- MARASSI | PKG#117-IPC 6 | 6 | EMAAR-PKG117- MARASSI6 | 6677875.14 | 5722280.397 | 687623.33 | 6409903.727
Canal Sugar OHTL | Inv.02 Sugar OHTL | 2 | Canal Sugar OHTL2 | 18349632 | 14496209.28 | 2752444.8 | 17248654.08
Canal Sugar S/s | Inv 1 Sugar S/s | 1 | Canal Sugar S/s1 | 12212036.75 | 7508017.53 | 3971297.02 | 11479314.55
Marsa Matrouh 500KV | Inv.20 Borg Alarab | 20 | Marsa Matrouh 500KV20 | 4164056.26 | 3637306.65 | 437225.91 | 4074532.56
Attaqa Power Plant | Inv. 2 USD. | 2 | Attaqa Power Plant2 | 117713333 | 117713333 | 0 | 117713333
Akhmem - Qena | Social Inv. 47 Qena | 47 | Akhmem - Qena47 | 29277.5 | 29277.5 | 0 | 29277.5
MAYSAN 400/132kV SS | 221 |  | MAYSAN 400/132kV SS | 859504.74 | 859504.74 | 0 | 859504.74
HAC CCC JV | IPC#12 | 12 | HAC CCC JV12 | 1436628.15 | 1308201.36 | 0 | 1308201.36
EMAAR-PKG# 144, Marassi | PKG#144 - IPC10 | 10 | EMAAR-PKG# 144, Marassi10 | 13884342.32 | 11330349.466 | 1033903.34 | 12364252.806
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 1 | 1 | Benban 500 K.V / 100 K.M1 | 25879088.97 | 19947781.4 | 2717304.34 | 22665085.74
Benban 500 K.V / 100 K.M | Benban Lot1 Inv15USD | 15 | Benban 500 K.V / 100 K.M15 | 96045.76 | 0 | 90763.25 | 90763.25
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 3USD | 3 | Benban 500 K.V / 100 K.M3 | 644227.92 | 541151.46 | 67643.93 | 608795.39
Benban 500 K.V/95 K.M | Benban Lot2 Inv 14 $ | 14 | Benban 500 K.V/95 K.M14 | 6491.31 | 5452.7 | 681.59 | 6134.29
Benban 500 K.V/95 K.M | Benban Lot2 Inv 4 $ | 4 | Benban 500 K.V/95 K.M4 | 206822.3 | 173730.73 | 21716.34 | 195447.07
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC023 | 23 | EMAAR- Pkg 140-ITP-Mivida23 | 4716911.47 | 3870461.7235 | 495275.7 | 4365737.4235
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC21 | 21 | EMAAR- Pkg 140-ITP-Mivida21 | 9991628.97 | 8185193.8285 | 1047401.56 | 9232595.3885
Tunnel of Sokhna Road (2) | SOKHNA TU 2 -IPC01 | 1 | Tunnel of Sokhna Road (2)1 | 17783725 | 6746486.9 | 5185204.9 | 15728967.8
NUCA R05 - Z02 | R5-ZONE2-IPC04 | 4 | NUCA R05 - Z024 | 39628486.3 | 30518029.655 | 3814812.09 | 34332841.745
4 SS - Technical Service | 240 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Manshiet Nasser Substation | 1903210013 |  | Manshiet Nasser Substation | 510317.14 | 474467.36 | 56262.47 | 530729.83
Manshiet Nasser Substation | 1903210017 |  | Manshiet Nasser Substation | 3471619.05 | 3591790.48 | 0 | 3591790.48
Manshiet Nasser Substation | 1902210008 |  | Manshiet Nasser Substation | 1378837.86 | 1433991.37 | 0 | 1433991.37
Manshiet Nasser Substation | 1901210019 |  | Manshiet Nasser Substation | 5428.57 | 5645.71 | 0 | 5645.71
Manshiet Nasser Substation | 1903210016 |  | Manshiet Nasser Substation | 2266861.89 | 1988299.43 | 357030.75 | 2345330.18
Manshiet Nasser Substation | 1904210006 |  | Manshiet Nasser Substation | 701937.71 | 616451.73 | 110555.19 | 727006.92
Manshiet Nasser Substation | 1904210007 |  | Manshiet Nasser Substation | 1350167.86 | 1398388.14 | 0 | 1398388.14
Royal City | 20100005 |  | Royal City | 11082459.93 | 8006173.81 | 3699299.17 | 11705472.98
Royal City | ROYAL CITY-IC34 |  | Royal City | 9492258.84 | 4107326.4576 | 2281723.84 | 6389050.2976
AbuSultan Rd Bridge2 Extension | ABU SULTAN2-IPC 1 | 1 | AbuSultan Rd Bridge2 Extension1 | 47855181.9 | 16049067.35 | 4000000 | 44899067.35
El Mostakbal City Project | Inv. 4 Mostakbal | 4 | El Mostakbal City Project4 | 11156975.42 | 9251512.46 | 2342964.84 | 11594477.3
Canal Sugar OHTL | Inv.02 $ Sugar OHTL | 2 | Canal Sugar OHTL2 | 1663396.09 | 1314082.91 | 249509.41 | 1563592.32
Canal Sugar S/s | Inv 3 $ Sugar S/s | 3 | Canal Sugar S/s3 | 87120.81 | 68825.44 | 13068.12 | 81893.56
P-28-16 Balat Owinat Lot 3 | Inv. 10 Balat lot 3 | 10 | P-28-16 Balat Owinat Lot 310 | 3152312.34 | 2354386.33 | 330992.8 | 2685379.13
Benban 500 K.V/95 K.M | Benban Lot2 Inv1 $ | 1 | Benban 500 K.V/95 K.M1 | 189105.54 | 158749.66 | 19856.08 | 178605.74
Abou El Matameer and Sammanoud | Inv 98 P11- Sammound | 98 | Abou El Matameer and Sammanoud98 | 3556387.0081 | 2554908.4281 | 533458.05 | 3088366.4781
Abou El Matameer and Sammanoud | Inv.10 Samanod 95 | 10 | Abou El Matameer and Sammanoud10 | 1414240.74 | 1015990.55 | 212136.11 | 1228126.66
Development of Mahmudiyah axis | IPC# 4&5 | 4 | Development of Mahmudiyah axis4 | 3195000 | 3105540 | 0 | 3105540
Road El Farag Axis | 10003 |  | Road El Farag Axis | 288778 | 264330 | 0 | 264330
Port Said Subs 220/66 | Port Said Inv. 2 | 2 | Port Said Subs 220/662 | 61841695.5 | 40351295 | 15460428.88 | 55811723.88
DPW Onshore Port & Terminal | DP WORLD-IPC05 | 5 | DPW Onshore Port & Terminal5 | 37757872.1 | 27940477.28 | 5663680.82 | 33604158.1
P-28-16 Balat Owinat Lot 2 | Inv. 11 Balat Lot 2 | 11 | P-28-16 Balat Owinat Lot 211 | 17383519.05 | 12985090.6 | 1825269.5 | 14810360.1
Akhmem Assiut | Inv.42 Assuit Akhmem | 42 | Akhmem Assiut42 | 4462784.38 | 3302460.43 | 669417.66 | 3971878.09
Akhmem Assiut | Inv.34 Assuit Akhmem | 34 | Akhmem Assiut34 | 7809897.24 | 6208868.3 | 1171484.59 | 7380352.89
Akhmem Assiut | inv. 5 Assuit Akhmem | 5 | Akhmem Assiut5 | 74172564.53 | 44132675.89 | 11125884.68 | 55258560.57
EMAAR- Pkg 140-ITP-Mivida | PKG#140 -IPC 02 | 2 | EMAAR- Pkg 140-ITP-Mivida2 | 4911239.08 | 2620895.13 | 1924702.2 | 4545597.33
MOTHANA 400/132kV SS | 242 |  | MOTHANA 400/132kV SS | 927892.49 | 927892.49 | 0 | 927892.49
Akhmem - Qena | Inv.47 Qena Akhmem | 47 | Akhmem - Qena47 | 1084342.74 | 746978.97 | 162651.41 | 909630.38
Akhmem - Qena | Inv. 9 Qena - Akhmem | 9 | Akhmem - Qena9 | 40389347.35 | 32109531.11 | 6058402.13 | 38167933.24
Akhmem - Qena | Inv.8 Qena Akhmem | 8 | Akhmem - Qena8 | 850515.9 | 676160.14 | 127577.39 | 803737.53
Akhmem - Qena | Inv.7 Qena Akhmem | 7 | Akhmem - Qena7 | 43280910.52 | 25752141.77 | 6492136.58 | 32244278.35
Akhmem - Qena | Inv.33 Akhmem Qena | 33 | Akhmem - Qena33 | 1433432.22 | 709548.94 | 215014.84 | 924563.78
Akhmem - Qena | Inv.28 Akhmem Qena | 28 | Akhmem - Qena28 | 5566802.4 | 4425607.91 | 835020.36 | 5260628.27
Akhmem - Qena | Inv.23 Akhmem Qena | 23 | Akhmem - Qena23 | 4662531.26 | 3706712.34 | 699379.69 | 4406092.03
Akhmem - Qena | Inv.17 Qena - Akhmem | 17 | Akhmem - Qena17 | 8906791.57 | 7080899.29 | 1336018.74 | 8416918.03
Akhmem - Qena | Inv.14 Qena - Akhmem | 14 | Akhmem - Qena14 | 10040812.8 | 7982446.17 | 1506121.92 | 9488568.09
Akhmem - Qena | Inv.12 Qena - Akhmem | 12 | Akhmem - Qena12 | 25588009.7 | 20342467.71 | 3838201.46 | 24180669.17
Ministries Buildings | MI.ALLOCATION-IPC01 | 1 | Ministries Buildings1 | 18644827.24 | 9798900.515 | 5233060 | 15031960.515
Zambia Project | SCD4/004 |  | Zambia Project | 83278.01 | 0 | 0 | 83278.01
Elco Steel 220/33 KV SS | 1908210009 |  | Elco Steel 220/33 KV SS | 464081.18 | 487285.14 | 0 | 487285.14
C5 Bridge 2 New Alamein | IPC#6 | 6 | C5 Bridge 2 New Alamein6 | 1975750 | 1916477.5 | 0 | 1916477.5
Marsa Matrouh 500KV | Inv.8 Usd borg alarb | 8 | Marsa Matrouh 500KV8 | 1316451.44 | 1146000.26 | 138227.4 | 1284227.66
MAYSAN 400/132kV SS | 258 |  | MAYSAN 400/132kV SS | 1997759.13 | 1997759.13 | 0 | 1997759.13
MAYSAN 400/132kV SS | 250 |  | MAYSAN 400/132kV SS | 523836.53 | 523836.53 | 0 | 523836.53
NUCA R05 - Z02 | R5-ZONE 2-IPC6 | 6 | NUCA R05 - Z026 | 28390914 | 23245614.83 | 2882582.99 | 26128197.82
Latin Quarter- New Alamein | inv ( 2 ) 28-11-2020 | 2 | Latin Quarter- New Alamein2 | 18884313.36 | 9044315.26 | 0 | 9044315.26
Latin Compound - New Alamin | INV(1-8)010420 | 1 | Latin Compound - New Alamin1 | 4686640 | 3783823.86 | 0 | 3783823.86
Zambia Project | SCD1/004 |  | Zambia Project | 1677127.55 | 1509395.98 | 0 | 1509395.98
Safeer Square Bridge | SAFIER BRIDGE-IPC02F | 2 | Safeer Square Bridge2 | 7069691 | 3478470 | 1159496.2 | 10756091.2
Ministries Buildings | MINISTRIY CORE-IPC01 | 1 | Ministries Buildings1 | 36181016.75 | 20128404 | 10452262.5 | 30580666.5
LAYYAH CCPP | 504 |  | LAYYAH CCPP | 256625 | 229037.81 | 38493.75 | 267531.56
DoubleTree Mangroovy ElGouna | MANGROVE-IPC13 | 13 | DoubleTree Mangroovy ElGouna13 | 2664148.65 | 1951940.1825 | 605589.02 | 2557529.2025
DoubleTree Mangroovy ElGouna | MANGOROVE-IPC05 | 5 | DoubleTree Mangroovy ElGouna5 | 2635327.18 | 1810211.333 | 691773.39 | 2501984.723
DoubleTree Mangroovy ElGouna | 20100007 |  | DoubleTree Mangroovy ElGouna | 3318054.9 | 2286139.795 | 870989.43 | 3157129.225
DoubleTree Mangroovy ElGouna | MANGORVE-IPC02 | 2 | DoubleTree Mangroovy ElGouna2 | 5630968.01 | 3867767.2605 | 1478129.1 | 5345896.3605
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 4 | 4 | Benban 500 K.V/95 K.M4 | 270579.14 | 208615.72 | 28410.81 | 237026.53
Marsa Matrouh 500KV | Inv.37 Borg Alarab | 37 | Marsa Matrouh 500KV37 | 40728189.49 | 29161385.37 | 4276459.9 | 33437845.27
Ismailiya East Substation | ISE-CW-EGP-17 | 17 | Ismailiya East Substation17 | 2428316 | 1796953.84 | 364247.4 | 2161201.24
AWEER POWER STATION 'H' Phase | 10309 |  | AWEER POWER STATION 'H' Phase | 2890591.9 | 851118.7096 | 2007355.5025 | 2858474.2121
AWEER POWER STATION 'H' Phase | 10187 |  | AWEER POWER STATION 'H' Phase | 3617336.637 | 3175217.7147 | 401926.293 | 3577144.0077
Nagaa Hamady/Assuit OHTL | Naga Hmdy Inv.1 Equ | 1 | Nagaa Hamady/Assuit OHTL1 | 1223014 | 875812.9 | 134399.82 | 1010212.72
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 2 | 2 | Nagaa Hamady/Assuit OHTL2 | 6553246.67 | 4724893.85 | 688090.9 | 5412984.75
Fish Market | SOUQ ELSAMAK-IPC01 | 1 | Fish Market1 | 37032038.02 | 1511734 | 18018671.05 | 25631505.05
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 9 | 9 | Benban 500 K.V/95 K.M9 | 206389.5 | 159132.8 | 21670.9 | 180803.7
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 3 | 3 | Marsa Alam/ Bernes LOT2 OHTL3 | 11819509.69 | 0 | 1294808.2 | 1294808.2
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 2 | 2 | Marsa Alam/ Bernes LOT2 OHTL2 | 45934.1 | 0 | 4823.08 | 4823.08
Akhmem - Qena | Inv.48 Qena Akhmem | 48 | Akhmem - Qena48 | 17873297.89 | 12331379.24 | 2680994.68 | 15012373.92
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 5 | 5 | Marsa Alam/ Bernes LOT2 OHTL5 | 9745824.7 | 5857233.06 | 1015174.97 | 6872408.03
Port Saad Industiral zone | IPC#1 | 1 | Port Saad Industiral zone1 | 2704500 | 2604433.5 | 0 | 2604433.5
Canal Sugar 33KV OHTL | Inv. 4 Sugar 33 OHTL | 4 | Canal Sugar 33KV OHTL4 | 9076854.62 | 6913988.49 | 855947.01 | 8336455.52
33KV Canal Farm Grid | Inv. 15 Farm | 15 | 33KV Canal Farm Grid15 | 10359130.15 | 7904016.31 | 1553869.52 | 9457885.83
Port Said Subs 220/66 | Port Said Inv. 3 | 3 | Port Said Subs 220/663 | 91810868.9 | 59217605 | 22952717.35 | 82170322.35
Asec Spare-Parts | Inv 1 Asec Sparepart | 1 | Asec Spare-Parts1 | 439525.4 | 353176 | 109881.35 | 463057.35
Canal Regional Control Center | Inv.2 RCC | 2 | Canal Regional Control Center2 | 9728408.52 | 6478491.45 | 2042965.79 | 8521457.24
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 4USD | 4 | Benban 500 K.V / 100 K.M4 | 67188.57 | 49383.6 | 14109.6 | 63493.2
Benban 500 K.V/95 K.M | Benban Lot2 Inv 9 $ | 9 | Benban 500 K.V/95 K.M9 | 251500.72 | 211001.61 | 26407.58 | 237409.19
Celia | IPC#3 | 3 | Celia3 | 216937.25 | 198063.71 | 0 | 205613.126
Manshiet Nasser Substation | 1906210010 |  | Manshiet Nasser Substation | 321986.71 | 290233.48 | 52116.03 | 342349.51
HyperOne Zayed Extension | HYPER ONE- IPC10 | 10 | HyperOne Zayed Extension10 | 7629179.05 | 4688663.2125 | 1907295 | 6595958.2125
HyperOne Zayed Extension | HYPER ONE- IPC07 | 7 | HyperOne Zayed Extension7 | 12419046 | 8960289.48 | 3088611.5 | 13214062.98
HyperOne Zayed Extension | HYPER ONE2-IPC03 | 3 | HyperOne Zayed Extension3 | 10276217.14 | 7194819.68 | 2569054.29 | 10912969.97
HyperOne Zayed Extension | HYPER -IPC01 | 1 | HyperOne Zayed Extension1 | 1684524 | 2583316 | 421131 | 3004447
R5 Mix-Use Complex Project | R5-ZONE 1- IPC7 | 7 | R5 Mix-Use Complex Project7 | 4353324 | 3418442.3 | 426675.87 | 3845118.17
Safir bridge | IPC#1 | 1 | Safir bridge1 | 1183500 | 837650 | 75000 | 1144865
Suez Gulf Substation | 16 EGP VO Shippment |  | Suez Gulf Substation | 10444.25 | 9888.38 | 1098.71 | 10987.09
Ismailiya East Substation | ISE-SW-EGP-04 | 4 | Ismailiya East Substation4 | 1297188 | 959919.12 | 194578.2 | 1154497.32
Asher Mn Ramadan Bridge No2 | AlAsher Brdg 2 Final |  | Asher Mn Ramadan Bridge No2 | 9426336.26 | 494880 | 5610484.5 | 6105364.5
Ministries Buildings | MIN.ANASER WATER-02 | 2 | Ministries Buildings2 | 2113563 | 501405 | 1300000 | 1801405
Ministries Buildings | MIN-SHELL-IPC02 | 2 | Ministries Buildings2 | 27529574.79 | 8072902 | 16772114.7 | 24845016.7
Royal City | royal city-ipc22 | 22 | Royal City22 | 18490927.23 | 17384865.3315 | 7484058.67 | 24868924.0015
Royal City | ROYAL ZONE-IPC02 | 2 | Royal City2 | 1714285.71 | 4006344.6355 | 595210 | 4601554.6355
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC08 | 8 | EMAAR-PKG# 101-UPTOWN8 | 3123640.99 | 1824097.56 | 909775.35 | 2733872.91
Benban 500 K.V / 100 K.M | Benban Lot1 Inv10USD | 10 | Benban 500 K.V / 100 K.M10 | 1077864.38 | 905406.08 | 113175.76 | 1018581.84
Benban 500 K.V / 100 K.M | Benban Lot1 Inv13USD | 13 | Benban 500 K.V / 100 K.M13 | 62875.18 | 52815.15 | 6601.89 | 59417.04
Benban 500 K.V/95 K.M | Benban Lot2 Inv 5 $ | 5 | Benban 500 K.V/95 K.M5 | 1709958.6 | 1436365.23 | 179545.65 | 1615910.88
Manshiet Nasser Substation | 1908210017 |  | Manshiet Nasser Substation | 290843.58 | 169734.67 | 0 | 169734.67
SHAT Al ARAB 400/132kV SS | 265 |  | SHAT Al ARAB 400/132kV SS | 68360.02 | 68360.02 | 0 | 68360.02
LAYYAH CCPP | 508 |  | LAYYAH CCPP | 14441700 | 12866072.1 | 2188298 | 15054370.1
LAYYAH CCPP | 496 |  | LAYYAH CCPP | 3237480 | 3380409.6 | 18328 | 3398737.6
LAYYAH CCPP | 490 |  | LAYYAH CCPP | 6538440 | 6025344 | 513096 | 6538440
OHTL Mostakable East Boundary | Inv. 01 Future OHTL | 1 | OHTL Mostakable East Boundary1 | 14461699.54 | 12003203.62 | 3036956.9 | 15040160.52
Asec Spare-Parts | Inv 4 Asec Sparepart | 4 | Asec Spare-Parts4 | 2766152 | 2353637 | 788353.46 | 3141990.46
Akhmem Assiut | Istill.4 lot 1 Akhme |  | Akhmem Assiut | 1440616.76 | 1439034 | 0 | 1439034
El Katameya Mall | inv(6)100320 | 6 | El Katameya Mall6 | 312760 | 190730.28 | 0 | 190730.28
El Katameya Mall | inv(3)251219 | 3 | El Katameya Mall3 | 585760 | 458205.31 | 0 | 458205.31
El Katameya Mall | inv(1)101119 | 1 | El Katameya Mall1 | 418387.2 | 311704.71 | 0 | 311704.71
MOTHANA 400/132kV SS | 273 |  | MOTHANA 400/132kV SS | 1318474.25 | 1318474.25 | 0 | 1318474.25
C5 Bridge 2 New Alamein | IPC#3 | 3 | C5 Bridge 2 New Alamein3 | 1933000 | 1875010 | 0 | 1875010
C5 Bridge 2 New Alamein | IPC#2 | 2 | C5 Bridge 2 New Alamein2 | 2602250 | 2522282.5 | 0 | 2522282.5
NUCA R05 - Z02 | R05 PH2 IPC013 | 13 | NUCA R05 - Z0213 | 25243578 | 20731287.35 | 2608113.2 | 23339400.55
NUCA R05 - Z02 | R5 FINSHING-IPC08 | 8 | NUCA R05 - Z028 | 16500636.8 | 12951782.63 | 1650063.7 | 14601846.33
NUCA R05 - Z02 | R5 FINSHING-IPC07 | 7 | NUCA R05 - Z027 | 10813860.39 | 8569582.89 | 1081386.05 | 9650968.94
NUCA R05 - Z02 | R5 FINSHING-IPC06 | 6 | NUCA R05 - Z026 | 15286382 | 12114056.05 | 1528638.2 | 13642694.25
Mauritania Lot 1 | Inv.1 - Lot 1 | 1 | Mauritania Lot 11 | 255854.38 | 208279.69 | 0 | 255839.38
Celia | IPC#1 | 1 | Celia1 | 664719.63 | 606889.02 | 0 | 624238.203
Suez Gulf Substation | 22 EGP VO TOAC |  | Suez Gulf Substation | 474531.48 | 434236.4 | 49919.53 | 484155.93
MOTHANA 400/132kV SS | 290 |  | MOTHANA 400/132kV SS | 194047.08 | 194047.08 | 0 | 194047.08
Ismailiya East Substation | ISE-SW-EGP-05 | 5 | Ismailiya East Substation5 | 835625 | 618362.5 | 125343.75 | 743706.25
ESU Ph2-Enabling & Struc | ESU PHASE2-IPC08 | 8 | ESU Ph2-Enabling & Struc8 | 2504382.36 | 1607563.008 | 788880.47 | 2396443.478
ESU Ph2-Enabling & Struc | SEWEDY UNI 2- IPC04 | 4 | ESU Ph2-Enabling & Struc4 | 17471458.95 | 14773672.5575 | 5503509.61 | 20277182.1675
ESU Ph2-Enabling & Struc | E.S.U PH2-IPC01 | 1 | ESU Ph2-Enabling & Struc1 | 1222080 | 2832679.4325 | 384955.2 | 3217634.6325
Cairo Capital Cables Tunnel | Tunnel Inv. 11 | 11 | Cairo Capital Cables Tunnel11 | 18539568.45 | 12291733.7 | 4634892.13 | 16926625.83
Cairo Capital Cables Tunnel | Tunnel Inv. 3 | 3 | Cairo Capital Cables Tunnel3 | 38855418.3 | 26149696.4 | 9713854.6 | 35863551
Cairo Capital Cables Tunnel | Tunnel Inv. 2 + | 2 | Cairo Capital Cables Tunnel2 | 41945.4 | 31459.05 | 10486.35 | 41945.4
EDNC Retail & Offices Civil | SOREAL-IPC08 | 8 | EDNC Retail & Offices Civil8 | 82004688.27 | 59087057.7335 | 17186679.54 | 76273737.2735
Assuit PP (CP-118) | 491 |  | Assuit PP (CP-118) | 262534.21 | 234311.78 | 41349.14 | 275660.92
Abu Sultan Road Extension | ABUSOULTAN 1 -FINAL |  | Abu Sultan Road Extension | 1040367.67 | 495270 | 495279 | 990549
Ministries Buildings | MIN.LONG LIGHT-IPC01 | 1 | Ministries Buildings1 | 78087000.75 | 18867582 | 49728549.94 | 68596131.94
Mahmoudia Additional Scope | 528 |  | Mahmoudia Additional Scope | 19798312.5 | 19798312.5 | 0 | 19798312.5
Kayan 3 New Cairo Capital City | KAYAN MEP2-IPC01 | 1 | Kayan 3 New Cairo Capital City1 | 55642027 | 20757211 | 28054365.5 | 48811576.5
Manshiet Nasser Substation | 1903210018 |  | Manshiet Nasser Substation | 11144.9 | 9473.16 | 1671.74 | 11144.9
Manshiet Nasser Substation | 1902210012 |  | Manshiet Nasser Substation | 424161.5 | 360537.28 | 63624.22 | 424161.5
Royal City | ROYAL CENTER-IPC04 | 4 | Royal City4 | 4548914.9 | 4400341.915 | 703274.95 | 5103616.865
HyperOne Zayed Extension | HYPER ONE-IPC02 | 2 | HyperOne Zayed Extension2 | 11473371.43 | 8637288.8615 | 2868342.86 | 11505631.7215
Beni Seuf - 358 | Inv.1 Temmay Amded | 1 | Beni Seuf - 3581 | 248553194.86 | 177318239.51 | 56320584.39 | 233638823.9
Manshiet Nasser Substation | 180169 |  | Manshiet Nasser Substation | 1995650.91 | 1855456.44 | 220020.51 | 2075476.95
Manshiet Nasser Substation | 180168 |  | Manshiet Nasser Substation | 1074522.15 | 1009782.19 | 118466.07 | 1128248.26
OHTL Mostakable East Boundary | Inv. 02 Future OHTL | 2 | OHTL Mostakable East Boundary2 | 3111029.43 | 2582154.43 | 653316.18 | 3235470.61
Canal Sugar OHTL | Inv.01 $ Sugar OHTL | 1 | Canal Sugar OHTL1 | 1759769.56 | 1390217.95 | 263965.43 | 1654183.38
Elco Steel 220/33 KV SS | 1903210010 |  | Elco Steel 220/33 KV SS | 572013.87 | 600614.56 | 0 | 600614.56
IKEA Extension MoA | IKEA-IPC02 | 2 | IKEA Extension MoA2 | 10719807.9 | 10688939.41 | 1339618.13 | 12028557.54
Abou El Matameer and Sammanoud | Inv 103P16Abo Matami | 103 | Abou El Matameer and Sammanoud103 | 4158694.75 | 3403475.78 | 623804.21 | 4027279.99
Abou El Matameer and Sammanoud | aboelmatamir 8inv.86 | 86 | Abou El Matameer and Sammanoud86 | 4651061.61 | 3364577.97 | 697659.24 | 4062237.21
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .23 | 23 | Benban 3/ Toshka 2 LOT 423 | 2513.14 | 1961.36 | 263.88 | 2225.24
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .15 | 15 | Benban 3/ Toshka 2 LOT 415 | 5299865.74 | 3614113.45 | 556485.9 | 4170599.35
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .20 | 20 | Benban 3/ Toshka 2 LOT 420 | 8559000.85 | 6735539.87 | 898695.09 | 7634234.96
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .14 | 14 | Benban 3/ Toshka 2 LOT 414 | 84072046.09 | 66164306.88 | 8827564.84 | 74991871.72
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .8 | 8 | Benban 3/ Toshka 2 LOT 48 | 4524558.18 | 3488147.4 | 475078.61 | 3963226.01
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .10 | 10 | Benban 3/ Toshka 2 LOT 410 | 29273363.1 | 20959734.15 | 3073703.13 | 24033437.28
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .5 | 5 | Benban 3/ Toshka 2 LOT 45 | 3823275.89 | 2947751.18 | 401443.97 | 3349195.15
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $3 | 3 | Benban 3/ Toshka 2 LOT 43 | 2188091.87 | 1837672.66 | 229749.65 | 2067422.31
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $9 | 9 | Benban 3/ Toshka 2 LOT 49 | 208365.78 | 113861.73 | 21878.41 | 135740.14
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .8 | 8 | Benban 3/ Toshka 2 LOT 48 | 31261604.28 | 25665776.55 | 3282468.45 | 28948245
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $6 | 6 | Benban 3/ Toshka 2 LOT 46 | 963603.78 | 800622.27 | 101178.4 | 901800.67
CFC Podium 2 | IPC-03-CFC Podium | 3 | CFC Podium 23 | 17039700.42 | 12263842.721 | 3991464.73 | 16255307.451
Royal City | ROYAL CITY-IPC23 | 23 | Royal City23 | 8598719.65 | 6578450.5925 | 1887253.3 | 8465703.8925
Badr 500 S/S / Zizenia 220 Kv | Badr-Zizenia Inv.3 | 3 | Badr 500 S/S / Zizenia 220 Kv3 | 5745036 | 3373685.25 | 1436259 | 4809944.25
SHAT Al ARAB 400/132kV SS | 294 |  | SHAT Al ARAB 400/132kV SS | 98101.83 | 98101.83 | 0 | 98101.83
MAYSAN 400/132kV SS | 296 |  | MAYSAN 400/132kV SS | 1205121.23 | 1205121.23 | 0 | 1205121.23
C5 Bridge 2 New Alamein | IPC#5 | 5 | C5 Bridge 2 New Alamein5 | 3805000 | 3687050 | 0 | 3687050
Ismailiya East Substation | ISE-SD-EURO-04 | 4 | Ismailiya East Substation4 | 322973.65 | 261417.57 | 26028.98 | 287446.55
Badr | Inv. 20 Badr | 20 | Badr20 | 18402201.51 | 9946520.02 | 2760330.08 | 12706850.1
IKEA Extension MoA | IKEA-IPC03 | 3 | IKEA Extension MoA3 | 10066585.31 | 7184168.17 | 868064.09 | 8052232.26
Nuweibaa (Swro) | 2002210002 |  | Nuweibaa (Swro) | 62581 | 50064.8 | 12516.2 | 62581
Asec Spare-Parts | Inv 6 EUR Asec Spare | 6 | Asec Spare-Parts6 | 180000 | 73854 | 51300 | 125154
Asec Spare-Parts | Inv 5 EUR Asec Spare | 5 | Asec Spare-Parts5 | 616545.07 | 486959 | 199827.96 | 686786.96
LAYYAH CCPP | MP-06 | 6 | LAYYAH CCPP6 | 10283760 | 0 | 10283760 | 10283760
Port Saad Industiral zone | IPC#5 | 5 | Port Saad Industiral zone5 | 10439080 | 10052834.04 | 0 | 10052834.04
CFC Podium 2 | CFC-IPC19 | 19 | CFC Podium 219 | 20398722.15 | 14008565.7 | 2676327.95 | 16684893.65
Latin Quarter- New Alamein | INV(1)250620 | 1 | Latin Quarter- New Alamein1 | 9564233.64 | 5246592.96 | 0 | 5246592.96
El Boghaz Brigde | IPC#23 | 23 | El Boghaz Brigde23 | 737330.04 | 141664.58 | 0 | 728287.62
El Boghaz Brigde | IPC#24 | 24 | El Boghaz Brigde24 | 801174.2 | 752488.75 | 0 | 752488.75
Wadi El Natroun | IPC#1 | 1 | Wadi El Natroun1 | 2585700 | 2348313.95 | 0 | 2348313.95
Museum of Egyp. Civilization | IPC#5 | 5 | Museum of Egyp. Civilization5 | 1290723.75 | 1151012.23 | 0 | 1151012.23
ORA Zed Park LOCK&LOAD | ORA ZED-IPC02 | 2 | ORA Zed Park LOCK&LOAD2 | 299629.7 | 264423.205 | 0 | 264423.205
Assuit PP (CP-118) | 2001210008 |  | Assuit PP (CP-118) | 2659221.99 | 2346725.01 | 418827.46 | 2765552.47
Manshiet Nasser Substation | 530 |  | Manshiet Nasser Substation | 1019830.46 | 766362.85 | 164140.6 | 930503.45
marassi inland marina | IPC#7 | 7 | marassi inland marina7 | 1678674.16 | 2706690.9 | 0 | 1437279.16
Toshka GIS 500 kV | Toshka Sub Inv. 22 $ | 22 | Toshka GIS 500 kV22 | 261121.27 | 97273.66 | 68544.33 | 165817.99
EMAAR-Pkg#162/163- Marassi | PKG#162 - IPC07 | 7 | EMAAR-Pkg#162/163- Marassi7 | 8577630.83 | 8042168.0415 | 936620.49 | 8978788.5315
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC06 | 6 | EMAAR-Pkg#162/163- Marassi6 | 5990865.5 | 4824045.385 | 617291.93 | 5441337.315
IKEA Extension MoA | IKEA-IPC09 | 9 | IKEA Extension MoA9 | 19195362.4 | 21335051.85 | 7587881.06 | 28922932.91
Juba PV | Inv. No.1- Juba Proj | 1 | Juba PV1 | 20000000 | 20000000 | 0 | 20000000
Beni Seuf - 358 | Inv.6 kafr zeat itay | 6 | Beni Seuf - 3586 | 7338147.52 | 6524020 | 1106466.8 | 7630486.8
ESU Ph2-Enabling & Struc | E.S.U2-MEP-IPC07 | 7 | ESU Ph2-Enabling & Struc7 | 56805725.81 | 25755604.8065 | 5532944.21 | 31288549.0165
MOTHANA 400/132kV SS | 302 |  | MOTHANA 400/132kV SS | 2954651.29 | 2954651.29 | 0 | 2954651.29
Kayan 3 New Cairo Capital City | KAYAN-MEP2-IPC02 | 2 | Kayan 3 New Cairo Capital City2 | 48674390.5 | 32946170 | 10982056.5 | 43928226.5
CFC Podium 2 | CFC IPC022 | 22 | CFC Podium 222 | 19833699.33 | 13410069.82 | 2562732.734 | 15972802.554
CFC Podium 2 | CFC-IPC02 | 2 | CFC Podium 22 | 15707266.4 | 17105451.15 | 2038078.37 | 19143529.52
DPW Onshore Port & Terminal | DP WORLD-IPC12 | 12 | DPW Onshore Port & Terminal12 | 148210852.69 | 109675422.28 | 22231627.9 | 131907050.18
Royal City | ROYAL CITY -IPC27 | 27 | Royal City27 | 23615681.47 | 11636419.9 | 5597473.3 | 17233893.2
Elmaragha Bridge - Sohag | IPC#2 | 2 | Elmaragha Bridge - Sohag2 | 252646.1538 | 451363.5 | 0 | 224855.0769
Multi Sport Hall | 10018 |  | Multi Sport Hall | 456945 | 406681.05 | 0 | 406681.05
Villa Fabio | 10028 |  | Villa Fabio | 76131.46 | 62300 | 10262.51 | 72562.51
Villa Fabio | 10027 |  | Villa Fabio | 39737.49 | 0 | 39737.49 | 39737.49
Ministries Building ROOF | 10002 |  | Ministries Building ROOF | 216236.09 | 203261.93 | 0 | 203261.93
Rail Way Tunnel Zagazig | IPC002 | 2 | Rail Way Tunnel Zagazig2 | 552520 | 514948.64 | 0 | 514948.64
Maspiro Towers | IPC#3 | 3 | Maspiro Towers3 | 538200 | 532818 | 0 | 533894.4
Canal Sugar OHTL | Inv.05 Sugar OHTL | 5 | Canal Sugar OHTL5 | 7293163.42 | 5761599.11 | 1093974.51 | 6855573.62
Ismailiya East Substation | ISE-SD-EGP-01 | 1 | Ismailiya East Substation1 | 244285 | 241842.15 | 0 | 241842.15
Marsa Matrouh 500KV | Inv.29 Borg Alarab | 29 | Marsa Matrouh 500KV29 | 31843663.25 | 22408230.01 | 3343584.64 | 25751814.65
Marsa Matrouh 500KV | Inv.25 Borg Alarab | 25 | Marsa Matrouh 500KV25 | 36010234.62 | 31454945.04 | 3781074.64 | 35236019.68
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC019 | 19 | EMAAR-Pkg#162/163- Marassi19 | 9320216.49 | 8474286.4545 | 2317036.86 | 10791323.3145
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC017 | 17 | EMAAR-Pkg#162/163- Marassi17 | 5496981.8 | 2625202.88 | 717782.18 | 3342985.06
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC01 | 1 | EMAAR-Pkg#162/163- Marassi1 | 1493908.79 | 1068966.4295 | 313720.85 | 1382687.2795
Vila Palm Hills | 10026 |  | Vila Palm Hills | 65347.64 | 3900 | 50000 | 53900
Marsa Matrouh 500KV | Inv.26Usd borg alarb | 26 | Marsa Matrouh 500KV26 | 624.47 | 369.79 | 0 | 369.79
EMAAR-PKG# 144, Marassi | PKG#144 -IPC14 | 14 | EMAAR-PKG# 144, Marassi14 | 10733689.11 | 10786798.0055 | 38643.69 | 10825441.6955
DoubleTree Mangroovy ElGouna | MANGOROVE RENT-IPC3 | 3 | DoubleTree Mangroovy ElGouna3 | 424545 | 441526.8 | 0 | 441526.8
Marsa Matrouh 500KV | Inv.65 Borg Alarab | 65 | Marsa Matrouh 500KV65 | 6452201.13 | 4619780.78 | 677481.12 | 5297261.9
Marsa Matrouh 500KV | Inv.63 Borg Alarab | 63 | Marsa Matrouh 500KV63 | 16797542.59 | 14672652.31 | 1763741.97 | 16436394.28
Ministries Buildings | MIN.SHELL-IPC03 | 3 | Ministries Buildings3 | 27623195.09 | 7792410 | 2137092.65 | 24929511.5
Sodic East | 10011 |  | Sodic East | 282795.84 | 149855.37 | 98978.54 | 248833.91
Sodic East | 10012 |  | Sodic East | 55306.44 | 33499.57 | 19357.25 | 52856.82
SHAT Al ARAB 400/132kV SS | 325 |  | SHAT Al ARAB 400/132kV SS | 218382.25 | 218382.25 | 0 | 218382.25
SHATRA 400/132kV SS | 333 |  | SHATRA 400/132kV SS | 68245.97 | 68245.97 | 0 | 68245.97
SHATRA 400/132kV SS | 332 |  | SHATRA 400/132kV SS | 925089.06 | 925089.06 | 0 | 925089.06
MAYSAN 400/132kV SS | 310 |  | MAYSAN 400/132kV SS | 419711.08 | 419711.08 | 0 | 419711.08
MOTHANA 400/132kV SS | 336 |  | MOTHANA 400/132kV SS | 130535.22 | 130535.22 | 0 | 130535.22
MOTHANA 400/132kV SS | 334 |  | MOTHANA 400/132kV SS | 30918.9 | 30918.9 | 0 | 30918.9
Ministries Buildings | 20100004 |  | Ministries Buildings | 1326870 | 965552 | 83450.9 | 1049002.9
Miscellaneous Projects | 2003210013 |  | Miscellaneous Projects | 114320.62 | 126895.89 | 0 | 126895.89
HyperOne Zayed Extension | HYPER ONE- IPC08 | 8 | HyperOne Zayed Extension8 | 7092750.29 | 3276433 | 1789290 | 5371325.34
AWEER POWER STATION 'H' Phase | Eng-25 rev0 | 25 | AWEER POWER STATION 'H' Phase25 | 226423.5 | 237672.87 | 0 | 237672.87
Sodic East | 10007 |  | Sodic East | 99314.4 | 51848.84 | 34760.04 | 86608.88
Air Defence College | TR46 IPC 11 | 11 | Air Defence College11 | 190510.2 | 0.2 | 0 | 190510.2
Royal City | ROYAL CITY-IPC28 | 28 | Royal City28 | 18900076.14 | 10500306.76 | 4655389.5 | 15155696.26
ESU Ph2-Enabling & Struc | E.S.U-PHASE2-MEP-01 | 1 | ESU Ph2-Enabling & Struc1 | 11716231.9 | 15636298.9 | 3410819.37 | 39047118.27
EDNC Retail & Offices Civil | SOREAL - IPC13 | 13 | EDNC Retail & Offices Civil13 | 15752551.19 | 13698867.9095 | 1739779.19 | 15438647.0995
Cameron EDC | 024/2020 FCV |  | Cameron EDC | 69315041.94 | 33157520.97 | 0 | 36157520.97
DPW Onshore Port & Terminal | DP WORLD- IPC13 | 13 | DPW Onshore Port & Terminal13 | 124566873.87 | 92179486 | 18685031.08 | 110864517.08
Angola Emergency fast-track | ANG-Cam-Inv 6 - Ints | 6 | Angola Emergency fast-track6 | 6921724.66 | 5075026.78 | 0 | 5075026.78
EMAAR-Pkg#162/163- Marassi | PKG#162 -IPC02 | 2 | EMAAR-Pkg#162/163- Marassi2 | 8785942 | 7794726.53 | 997481.89 | 8792208.42
AWEER POWER STATION 'H' Phase | IMP-036prog for 35 | 36 | AWEER POWER STATION 'H' Phase36 | 402668.77 | 353309.752 | 44740.97 | 398050.722
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC13 | 13 | EMAAR-PKG# 101-UPTOWN13 | 2584477.67 | 1246695.2535 | 598182.26 | 1844877.5135
Port Saad Industiral zone | IPC#8 | 8 | Port Saad Industiral zone8 | 66900 | 0 | 0 | 66900
Royal City | ROYAL CENTR ZONE-07 | 7 | Royal City7 | 6478470.72 | 6442723.346 | 1735335.48 | 8178058.826
P-28-16 Balat Owinat Lot 2 | Inv. 8 Balat Lot 2 | 8 | P-28-16 Balat Owinat Lot 28 | 13500978.1 | 10084836.64 | 1417602.7 | 11502439.34
P-28-16 Balat Owinat Lot 2 | Inv. 6 Balat Lot 2 | 6 | P-28-16 Balat Owinat Lot 26 | 5902339.3 | 4408656.71 | 619745.63 | 5028402.34
AWEER POWER STATION 'H' Phase | IMP-042 Rev0 | 42 | AWEER POWER STATION 'H' Phase42 | 3897039.52 | 3853667.08 | 0 | 3853667.08
IKEA Extension MoA | IEKA-IPC12 | 12 | IKEA Extension MoA12 | 27691689.43 | 15913350.29 | 6651541.01 | 22564891.3
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .3 | 3 | Benban 3/ Toshka 2 LOT 43 | 21849242 | 17938232.85 | 2294170.41 | 20232403.26
LAYAN Substation | 11743 |  | LAYAN Substation | 149657.2245 | 252920.7115 | 0 | 126460.3557
LAYAN Substation | 10722 |  | LAYAN Substation | 236362.4835 | 798905.2 | 0 | 199726.3
LAYAN Substation | 10662 |  | LAYAN Substation | 1033864.3999 | 8736154.2 | 0 | 873615.42
LAYAN Substation | 10604 |  | LAYAN Substation | 946488.368 | 3142341.4 | 0 | 785585.35
LAYAN Substation | 10583 |  | LAYAN Substation | 722308.48 | 1199032.08 | 0 | 599516.04
LAYAN Substation | 10442 |  | LAYAN Substation | 709095.52 | 1177098.5 | 0 | 588549.25
LAYAN Substation | 10302 |  | LAYAN Substation | 352345.6 | 292446.85 | 0 | 292446.85
LAYAN Substation | 10263 |  | LAYAN Substation | 352345.6 | 292446.85 | 0 | 292446.85
LAYAN Substation | 10150 |  | LAYAN Substation | 4542691.37 | 3770433.83 | 0 | 3770433.83
CFC Podium 2 | CFC-IPC06 | 6 | CFC Podium 26 | 42011128.3 | 31500278.46 | 6008704.37 | 37508982.83
R5 | inv(6)050320 | 6 | R56 | 841260 | 282423.4133 | 0 | 740601.9
Museum of Egyp. Civilization | IPC#1&2 | 1 | Museum of Egyp. Civilization1 | 1217123.25 | 1109107.77 | 0 | 1109107.77
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC11 | 11 | EMAAR- Pkg 140-ITP-Mivida11 | 3121472.23 | 2644790.7215 | 339824.7 | 2984615.4215
AWEER POWER STATION 'H' Phase | ENG/026 Rev0 adj |  | AWEER POWER STATION 'H' Phase | 19285.1 | 20177.541 | 0 | 20177.541
Olympic Multi – Sports Hall | Olympic IPC Final |  | Olympic Multi – Sports Hall | 36243472.6 | 28568817.5 | 19458253.1 | 48361770.6
Banha PP (CP-117) | 2005210005 |  | Banha PP (CP-117) | 29.19 | 29.19 | 0 | 29.19
SHAT Al ARAB 400/132kV SS | 348 |  | SHAT Al ARAB 400/132kV SS | 3125240.64 | 3125240.64 | 0 | 3125240.64
MOTHANA 400/132kV SS | 337 |  | MOTHANA 400/132kV SS | 26465.8 | 26465.8 | 0 | 26465.8
MOTHANA 400/132kV SS | 338 |  | MOTHANA 400/132kV SS | 447875.61 | 447875.61 | 0 | 447875.61
Minis Building(Polyurethane) | 10095 |  | Minis Building(Polyurethane) | 314193.87 | 279632.55 | 0 | 279632.55
Minis Building(Polyurethane) | 10193 |  | Minis Building(Polyurethane) | 146060.09 | 129993.49 | 0 | 129993.49
Museum of Egyp. Civilization | IPC#4 | 4 | Museum of Egyp. Civilization4 | 1111309.4643 | 1014935.73 | 0 | 1028434.0186
ESU Ph2-Enabling & Struc | SewedyUNi 2- IPC03 | 3 | ESU Ph2-Enabling & Struc3 | 19830117.9 | 23262698.715 | 6177834.6 | 29440533.315
Assuit PP (CP-118) | 2005210001 |  | Assuit PP (CP-118) | 191842.74 | 171219.65 | 30215.23 | 201434.88
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC14 | 14 | EMAAR-PKG# 101-UPTOWN14 | 2596223.72 | 1459609.626 | 699324.21 | 2158933.836
Royal City | ROYAL C.ZONE- IPC08 | 8 | Royal City8 | 17136692.17 | 12356243.75 | 3340696.2 | 15696939.95
Ministries A13-A14 | 10195 |  | Ministries A13-A14 | 860590 | 746992.12 | 0 | 746992.12
Canal Sugar OHTL | Inv.09 Sugar OHTL | 9 | Canal Sugar OHTL9 | 1904197.79 | 957352.17 | 232187.76 | 1189539.93
SHAT Al ARAB 400/132kV SS | 353 |  | SHAT Al ARAB 400/132kV SS | 1174480.63 | 1174480.63 | 0 | 1174480.63
SHATRA 400/132kV SS | 352 |  | SHATRA 400/132kV SS | 3459441.19 | 3459441.19 | 0 | 3459441.19
Marsa Matrouh 500KV | Inv.35 Borg Alarab | 35 | Marsa Matrouh 500KV35 | 1344380.95 | 1174323.24 | 141160 | 1315483.24
ESU Ph2-Enabling & Struc | ESU2-IPC4-MEP | 4 | ESU Ph2-Enabling & Struc4 | 27676491.14 | 18322600.95 | 8629523 | 26952123.95
Benban 500 K.V/95 K.M | Benban Lot2 Inv 15 $ | 15 | Benban 500 K.V/95 K.M15 | 2054162.73 | 1725397.7 | 215687.09 | 1941084.79
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 08 | 8 | Suez Gulf/S4 - 500KV OHTL8 | 2135496.86 | 1731877.41 | 224227.17 | 1956104.58
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 07 | 7 | Suez Gulf/S4 - 500KV OHTL7 | 120800.77 | 97961.63 | 12684.08 | 110645.71
Damac 2x60/22 KV S/S | Inv. 38 Damac | 38 | Damac 2x60/22 KV S/S38 | 1978003.49 | 1389391.15 | 296700.51 | 1686091.66
Oasis Buildings- New Capital | Inv(6)200620 | 6 | Oasis Buildings- New Capital6 | 2174220 | 2060723.86 | 0 | 2060723.86
MAYSAN 400/132kV SS | 356 |  | MAYSAN 400/132kV SS | 1630876.81 | 1630876.81 | 0 | 1630876.81
Elhegaz | Final |  | Elhegaz | 225520 | 0 | 0 | 223264.8
Akhmem Assiut | Inv.52 Assuit Akhmem | 52 | Akhmem Assiut52 | 5830729.68 | 4023203.47 | 874609.45 | 4897812.92
Ministries A17-A18 | 10133 |  | Ministries A17-A18 | 511215.2 | 431976.85 | 0 | 431976.85
Royal City | ROYAL CITY-IPC31 | 31 | Royal City31 | 12028045.18 | 6475509.799 | 3074149.35 | 9549659.149
SHAT Al ARAB 400/132kV SS | 358 |  | SHAT Al ARAB 400/132kV SS | 1702946.28 | 1702946.28 | 0 | 1702946.28
El Katameya Mall | inv(9)150720 | 9 | El Katameya Mall9 | 820120 | 658722.58 | 0 | 658722.58
Ain-Sokhna PP (CP-117) | 200023 |  | Ain-Sokhna PP (CP-117) | 283800 | 962082 | 0 | 320694
Angola Emergency fast-track | ANG-Cam-Inv 5 | 5 | Angola Emergency fast-track5 | 2845800 | 1926983.6 | 0 | 1926983.6
Mohamed Ali Palace | 10253 |  | Mohamed Ali Palace | 30504.6 | 23473.86 | 0 | 23473.86
Ghana | 40B/P/10/ER/2017/USD |  | Ghana | 35924.09 | 35924.09 | 0 | 35924.09
Ameria | IPC#1 | 1 | Ameria1 | 976800 | 805870 | 0 | 805870
HyperOne Zayed Extension | IPC-FINAL-HYPER MEP |  | HyperOne Zayed Extension | 5715164 | 5165148 | 0 | 5165148
SHATRA 400/132kV SS | 362 |  | SHATRA 400/132kV SS | 4709636.05 | 4709636.05 | 0 | 4709636.05
4 SS - Technical Service | 368 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
EDNC Retail & Offices Civil | SOREAL-IPC16 | 16 | EDNC Retail & Offices Civil16 | 42785902.69 | 31947230.0345 | 6235511.4 | 38182741.4345
Royal City | ROYAL ZONE-IPC10 | 10 | Royal City10 | 3936991.6 | 3061009.751 | 826768.24 | 3887777.991
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .6 | 6 | Benban 3/ Toshka 2 LOT 46 | 292365.93 | 225420.43 | 30698.42 | 256118.85
R5 | inv(7)100320 | 7 | R57 | 1697040 | 276552 | 0 | 1570563.18
Badr 500 S/S / Zizenia 220 Kv | Badr-Zizenia Inv.1 | 1 | Badr 500 S/S / Zizenia 220 Kv1 | 31255806.45 | 19814066.15 | 7813951.61 | 27628017.76
Angola Emergency fast-track | ANG-Mor-Inv.-5 | 5 | Angola Emergency fast-track5 | 10302977.71 | 6364856.45 | 0 | 6364856.45
Angola Emergency fast-track | ANG-Mor-Inv.-3 | 3 | Angola Emergency fast-track3 | 34487599.53 | 21651818.02 | 0 | 21651818.02
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .4 | 4 | Benban 3/ Toshka 2 LOT 44 | 15686510.91 | 12877553.82 | 1646945.98 | 14525810.91
LAYAN Substation | 10149 |  | LAYAN Substation | 4774415.23 | 3962764.64 | 0 | 3962764.64
Racecores 3092-16 132KV C | 11403 |  | Racecores 3092-16 132KV C | 2402432.68 | 9970095.6 | 0 | 1994019.12
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC04 | 4 | EMAAR-Pkg#162/163- Marassi4 | 3481812.47 | 6845695.7735 | 2009078.49 | 8854774.2635
33KV Canal Farm Grid | Inv. 08 Farm | 8 | 33KV Canal Farm Grid8 | 9953272.35 | 7594346.8 | 1492990.85 | 9087337.65
Ismailiya East Substation | ISE-SD-EURO-06 | 6 | Ismailiya East Substation6 | 915357.61 | 814668.27 | 0 | 814668.27
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $5 | 5 | Benban 3/ Toshka 2 LOT 45 | 781087.62 | 656012.61 | 82014.2 | 738026.81
NUCA R05 - Z02 | R05(2) IPC 51 | 51 | NUCA R05 - Z0251 | 25554941.85 | 21483828.77 | 2821079 | 24304907.77
NUCA R05 - Z02 | R052 ipc40 | 40 | NUCA R05 - Z0240 | 8606103.72 | 10606046.67 | 1301058.28 | 11907104.95
NUCA R05 - Z02 | R5 2 IPC37 | 37 | NUCA R05 - Z0237 | 8133883.45 | 3569378.99 | 492306.42 | 4061685.41
Ministries A17-A18 | IPC_5_gama_ministry |  | Ministries A17-A18 | 331014.5 | 279305.26 | 0 | 279305.26
Nuweibaa (Swro) | 2006210001 |  | Nuweibaa (Swro) | 634878.02 | 507902.42 | 126975.6 | 634878.02
SHAT Al ARAB 400/132kV SS | 361 |  | SHAT Al ARAB 400/132kV SS | 3461798.5 | 3461798.5 | 0 | 3461798.5
SHATRA 400/132kV SS | 367 |  | SHATRA 400/132kV SS | 3012885.67 | 3012885.5 | 0 | 3012885.5
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.05 | 5 | Mostakbal 2 Package No. (8)5 | 49890202.61 | 41408868.16 | 10476942.55 | 51885810.71
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.02 | 2 | Mostakbal 2 Package No. (8)2 | 1951436.55 | 1619692.34 | 409801.67 | 2029494.01
Olympic Multi – Sports Hall | OLYMPIC-IPC02 | 2 | Olympic Multi – Sports Hall2 | 85003516.9 | 13887855 | 43526899.2 | 72465094.2
EDNC Retail & Offices Civil | SOREAL-IPC17 | 17 | EDNC Retail & Offices Civil17 | 30425304.07 | 23516460.0735 | 4121239.46 | 27637699.5335
AWEER POWER STATION 'H' Phase | IMP-049 | 49 | AWEER POWER STATION 'H' Phase49 | 5375241.63 | 5315422.1115 | 0 | 5315422.1115
Beni Suef Substation R61 | BSF-CW-EGP-15 | 15 | Beni Suef Substation R6115 | 2347798.34 | 1737370.78 | 352169.75 | 2089540.53
Beni Suef Substation R61 | BSF-SW-06 | 6 | Beni Suef Substation R616 | 1004938 | 748678.81 | 150740.7 | 899419.51
Tamey El-amdeed Substation | TAM-CW-EGP-21 | 21 | Tamey El-amdeed Substation21 | 138782.46 | 102699.02 | 20817.37 | 123516.39
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.07 | 7 | Mostakbal 2 Package No. (8)7 | 13640499.21 | 10830556.37 | 2864504.83 | 13695061.2
Nuweibaa (Swro) | 2008210007 |  | Nuweibaa (Swro) | 234443.98 | 187555.18 | 46888.8 | 234443.98
El Katameya Mall | inv ( 11 ) 15-9-2020 | 11 | El Katameya Mall11 | 113960 | 50000 | 45351.14 | 95351.14
Marsa Matrouh 500KV | Inv.22Usd borg alarb | 22 | Marsa Matrouh 500KV22 | 70010.28 | 68090.37 | 0 | 68090.37
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC15 | 15 | EMAAR-PKG# 101-UPTOWN15 | 4658928.78 | 1268535.189 | 3599545.25 | 4868080.439
Mivida | 10293 |  | Mivida | 522840 | 517611.6 | 0 | 517611.6
Almaza Bridge - Safir 2 | S-003 | 3 | Almaza Bridge - Safir 23 | 501472.5 | 50000 | 0 | 457788.5
Substation Elco Steel | PSP ELCO-IPC11 | 11 | Substation Elco Steel11 | 4095222.62 | 3142902.52 | 1038383.05 | 4181285.57
AWEER POWER STATION 'H' Phase | ENG/035 |  | AWEER POWER STATION 'H' Phase | 177611.9 | 186492.495 | 0 | 186492.495
AWEER POWER STATION 'H' Phase | IMP- 056/058 | 56 | AWEER POWER STATION 'H' Phase56 | 1870689.35 | 3699807.84 | 0 | 1849903.92
Group # 1 - 25 LX | Reailway PSP Inv. 01 | 1 | Group # 1 - 25 LX1 | 1765500 | 1747845 | 0 | 1747845
Daraw Bridge | IPC#1 | 1 | Daraw Bridge1 | 1100000 | 920224.04 | 0 | 920224.04
EMAAR-Pkg#162/163- Marassi | PKG#163 -IPC03 | 3 | EMAAR-Pkg#162/163- Marassi3 | 547130.31 | 3055521.3155 | 873718.3 | 3929239.6155
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .14 | 14 | Benban 3/ Toshka 2 LOT 414 | 4391685.55 | 3561657.15 | 461126.98 | 4022784.13
El-Moneeb Bridge | IPC#1 | 1 | El-Moneeb Bridge1 | 1345000 | 1221940 | 0 | 1221940
IKEA Extension MoA | IKEA-IPC10 | 10 | IKEA Extension MoA10 | 16241435.02 | 10892925.95 | 3871917.19 | 14764843.14
AWEER POWER STATION 'H' Phase | Con-015 | 15 | AWEER POWER STATION 'H' Phase15 | 1277689.64 | 1263493 | 0 | 1263493
El Katameya Mall | inv(14 ) 10-2020 | 14 | El Katameya Mall14 | 125160 | 105711.42 | 0 | 105711.42
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 1 | 1 | Nagaa Hamady/Assuit OHTL1 | 17444824.76 | 13444963.31 | 1831706.6 | 15276669.91
DoubleTree Mangroovy ElGouna | MANGROVE-IPC10 | 10 | DoubleTree Mangroovy ElGouna10 | 1714004.8 | 1173489.49 | 449926.27 | 1623415.76
Rail Way Tunnel Zagazig | IPC#1 | 1 | Rail Way Tunnel Zagazig1 | 714780 | 666174.96 | 0 | 666174.96
Mauritania-Lot 2 | Inv.6 – Lot 2 | 6 | Mauritania-Lot 26 | 446297.21 | 422283.94 | 0 | 424071.74
Cairo-Alex Railway | Cairo-alex ipc32 | 32 | Cairo-Alex Railway32 | 33689843.81 | 1706221.9 | 3537433.6 | 5243655.5
Cairo-Alex Railway | cairo-alex ipc 25 | 25 | Cairo-Alex Railway25 | 3085109.98 | 1937782.079 | 323936.55 | 2261718.629
Cairo-Alex Railway | cairo-alex ipc22 | 22 | Cairo-Alex Railway22 | 19703504.7 | 13469137.195 | 2068867.99 | 15538005.185
Cairo-Alex Railway | cairo-alex ipc21 | 21 | Cairo-Alex Railway21 | 81561902.6 | 56387458.34 | 8563999.77 | 64951458.11
Cairo-Alex Railway | CAIRO-ALEX IPC18 | 18 | Cairo-Alex Railway18 | 17641968.1 | 12140086.085 | 1852406.65 | 13992492.735
Cairo-Alex Railway | Cairo-Alex IPC014 | 14 | Cairo-Alex Railway14 | 7078617 | 4915700.63 | 743254.8 | 5658955.43
Cairo-Alex Railway | Cairo-Alex IPC09 | 9 | Cairo-Alex Railway9 | 26297538.1 | 19182714.45 | 2629753.81 | 21812468.26
Sodic East | IPC_15_Rowad_SEast |  | Sodic East | 529135.77 | 468842.81 | 0 | 468842.81
Racecores 3092-17 132KV E | 11640 |  | Racecores 3092-17 132KV E | 96835.365 | 80373.3332 | 0 | 80373.3332
Racecores 3092-17 132KV E | 11288 |  | Racecores 3092-17 132KV E | 244946 | 203305.18 | 0 | 203305.18
Racecores 3092-17 132KV E | 10949 |  | Racecores 3092-17 132KV E | 203062.68 | 343175.94 | 0 | 171587.97
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.6 | 6 | Nagaa Hamady/Assuit OHTL6 | 281761.9 | 159480.24 | 29585 | 189065.24
SHAT Al ARAB 400/132kV SS | 370 |  | SHAT Al ARAB 400/132kV SS | 2193735.91 | 2193735.91 | 0 | 2193735.91
LAYYAH CCPP | 493 |  | LAYYAH CCPP | 15425640 | 13051321.5 | 2995810 | 16047131.5
Lekela 250MW Wind Farm | LEKELA-IPC10 | 10 | Lekela 250MW Wind Farm10 | 24782925.38 | 21709399.519 | 4107306.79 | 25816706.309
ESU Ph2-Enabling & Struc | E.S.U 2-MEP-IPC09 | 9 | ESU Ph2-Enabling & Struc9 | 85288754.95 | 20493846.4475 | 13976306.88 | 34470153.3275
EMAAR-PKG#22-MARASSI | PKG#22-IPC FINAL |  | EMAAR-PKG#22-MARASSI | 558773.62 | 408194.001 | 0 | 408194.001
Latin Compound - New Alamin | inv ( 20) 9-12-2020 | 20 | Latin Compound - New Alamin20 | 1013339.6 | 619516.54 | 202667.92 | 822184.46
Museum of Egyp. Civilization | IPC#7 | 7 | Museum of Egyp. Civilization7 | 2175660 | 1990728.9 | 0 | 1990728.9
Ministries Buildings | MIN.FIT OUT-IPC02 | 2 | Ministries Buildings2 | 6142805.64 | 3865825 | 1309079.9 | 5174904.9
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC 17 | 17 | ORA ZED - Ph 01B - Pkgs A&D17 | 31100661.13 | 27837999.2465 | 3310918.88 | 31148918.1265
ORA ZED - Ph 01B - Pkgs A&D | ora zed ipc14 | 14 | ORA ZED - Ph 01B - Pkgs A&D14 | 45635766.95 | 38191818.9175 | 4547728.4 | 42739547.3175
ORA ZED - Ph 01B - Pkgs A&D | ORa zed ipc13 | 13 | ORA ZED - Ph 01B - Pkgs A&D13 | 30511414.97 | 25426794.8085 | 3025284.37 | 28452079.1785
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED PH1 IPC010 | 10 | ORA ZED - Ph 01B - Pkgs A&D10 | 32858070.07 | 30886238.8435 | 3677026.6 | 34563265.4435
ORA ZED - Ph 01B - Pkgs A&D | Ora Zed IPC08 | 8 | ORA ZED - Ph 01B - Pkgs A&D8 | 26950096.62 | 25931572.791 | 3088483.39 | 29020056.181
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED 1- IPC02 | 2 | ORA ZED - Ph 01B - Pkgs A&D2 | 45205416.45 | 39936351.7025 | 4807707.27 | 44744058.9725
Vila Fabio (North Coast) | IPC-Fabio |  | Vila Fabio (North Coast) | 42750 | 42750 | 0 | 42750
IKEA Extension MoA | IKEA - IPC11 | 11 | IKEA Extension MoA11 | 40022086.82 | 16989482.64 | 6710363.39 | 23699846.03
Angola Emergency fast-track | ANG-Mor-Inv 5 - Ints | 5 | Angola Emergency fast-track5 | 3773923.09 | 2512234.44 | 0 | 2512234.44
Toshka GIS 500 kV | Toshka Sub Inv. 12 $ | 12 | Toshka GIS 500 kV12 | 234441.9 | 142577.6 | 61541 | 204118.6
Toshka GIS 500 kV | Toshka Sub Inv. 09 $ | 9 | Toshka GIS 500 kV9 | 86989.71 | 49666.56 | 22834.8 | 72501.36
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .9 | 9 | Benban 3/ Toshka 2 LOT 49 | 25121385.67 | 20622939.37 | 2637525.02 | 23262564.09
Asher Mn Ramadan Bridge No2 | 10M RMADAN BRIDGE-01 | 1 | Asher Mn Ramadan Bridge No21 | 72699012 | 9442270 | 7235771.2 | 64034869.2
AWEER POWER STATION 'H' Phase | Con-017 | 17 | AWEER POWER STATION 'H' Phase17 | 958273.98 | 947554.6784 | 0 | 947554.6784
Miscellaneous Projects | 2009210014 |  | Miscellaneous Projects | 204326.74 | 232932.48 | 0 | 232932.48
10th of Ramadan Railway | IPC#7 - HAC | 7 | 10th of Ramadan Railway7 | 940625 | 118618.24 | 0 | 118618.24
10th of Ramadan Railway | IPC#5 10 of Ramadan | 5 | 10th of Ramadan Railway5 | 454041 | 430203.85 | 0 | 430203.85
SHATRA 400/132kV SS | 375 |  | SHATRA 400/132kV SS | 904185.84 | 904185.84 | 0 | 904185.84
MOTHANA 400/132kV SS | 384 |  | MOTHANA 400/132kV SS | 268815.46 | 268815.46 | 0 | 268815.46
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $7 | 7 | Benban 3/ Toshka 2 LOT 47 | 226619.37 | 187860.59 | 23795.03 | 211655.62
Minis Building(Polyurethane) | IPC_16_Rowad_Poly |  | Minis Building(Polyurethane) | 59220.7 | 52706.41 | 0 | 52706.41
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC09 | 9 | EMAAR-Pkg#162/163- Marassi9 | 10891648.49 | 12697982.5806 | 1240035.07 | 13938017.6506
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC10 | 10 | EMAAR-Pkg#162/163- Marassi10 | 14574675.04 | 14201933.972 | 413306.08 | 14615240.052
Assuit PP (CP-118) | 2012210002 |  | Assuit PP (CP-118) | 204766.04 | 174051.1283 | 30714.91 | 204766.0383
Museum of Egyp. Civilization | IPC#2 PhaseII | 2 | Museum of Egyp. Civilization2 | 446310 | 408373.65 | 0 | 408373.65
RING ROAD MARYOTIA EXPANSION | Marytia-R-R-IPC01* | 1 | RING ROAD MARYOTIA EXPANSION1 | 153919.35 | 153919.33 | 0 | 153919.33
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .2 | 2 | Benban 3/ Toshka 2 LOT 42 | 17605222.78 | 12222792.55 | 1848548.39 | 14071340.94
Minis Building(Polyurethane) | IPC_17_Rowad_Roly |  | Minis Building(Polyurethane) | 143610.5 | 127813.33 | 0 | 127813.33
Latin Compound - New Alamin | inv ( 25 )20/12/2020 | 25 | Latin Compound - New Alamin25 | 592631.2 | 389051.75 | 115432.27 | 504484.02
ElSewedy HQ Internal Finishing | elsewedy HQ-IPC04 | 4 | ElSewedy HQ Internal Finishing4 | 11480730.19 | 7530697.05 | 3180833.19 | 10996640.92
El-Nyaba El-Ama | El-Nayba Inv. 1 | 1 | El-Nyaba El-Ama1 | 777826 | 630455.08 | 58336.95 | 688792.03
Port Said Subs 220/66 | Port Said Inv. 1 | 1 | Port Said Subs 220/661 | 96480795.67 | 62748290 | 24120198.92 | 86868488.92
Berket Ghelion | Inv.21 Final Ghelion | 21 | Berket Ghelion21 | 1125841.04 | 669738.6 | 281461.1005 | 951199.7005
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 01 | 1 | Toshka-04 GIS Substation1 | 16439400.55 | 14658355.1 | 1726137.06 | 16384492.16
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 04 | 4 | Suez Gulf/S4 - 500KV OHTL4 | 5712160.88 | 4346940.88 | 599776.89 | 4946717.77
ORA-ZED Towers01B | IPC_1_Rowad_Ora |  | ORA-ZED Towers01B | 191179.09 | 164127.27 | 0 | 164127.27
Ministries Buildings | MIN.ELCTROM-IPC03 | 3 | Ministries Buildings3 | 104773160.9 | 30488417.99 | 14162802 | 88751987.99
Ministries Buildings | MIN-ANASER SAHY-IPC1 | 1 | Ministries Buildings1 | 1854632 | 273930 | 1205839.96 | 1479769.96
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 02 | 2 | Suez Gulf/S4 - 500KV OHTL2 | 80012 | 60874.24 | 8401.26 | 69275.5
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $8 | 8 | Benban 3/ Toshka 2 LOT 48 | 168773.68 | 133050.03 | 17721.24 | 150771.27
33KV Canal Farm Grid | Inv. 03 Farm | 3 | 33KV Canal Farm Grid3 | 29404681.7 | 23229284.27 | 4410702.26 | 27639986.53
33KV Canal Farm Grid | Inv. 06 Farm | 6 | 33KV Canal Farm Grid6 | 21870002.84 | 17277302.24 | 3280500.43 | 20557802.67
33KV Canal Farm Grid | Inv. 02 Farm | 2 | 33KV Canal Farm Grid2 | 25824875.03 | 20401651.28 | 3873731.25 | 24275382.53
Canal Sugar S/s | Inv 7 Sugar S/s | 7 | Canal Sugar S/s7 | 13488150.68 | 10655639.03 | 2023222.6 | 12678861.63
Canal Sugar S/s | Inv 5 Sugar S/s | 5 | Canal Sugar S/s5 | 7656082.15 | 6048304.9 | 1148412.32 | 7196717.22
DPW Onshore Port & Terminal | DP WORLD-IPC21 | 21 | DPW Onshore Port & Terminal21 | 34792442.42 | 25746407.4 | 5218866.36 | 30965273.76
Kattameya Creeks | Katamya Creeks ipc41 | 41 | Kattameya Creeks41 | 44558913.7 | 45340679.808 | 818731.44 | 46159411.248
Kattameya Creeks | Katameya ipc 29 | 29 | Kattameya Creeks29 | 40212630.08 | 40904481 | 704758.51 | 41609239.51
Kattameya Creeks | katameya IPC 28 | 28 | Kattameya Creeks28 | 28889381.89 | 28650459 | 1394498.15 | 30044957.15
Kattameya Creeks | katameya ipc15 | 15 | Kattameya Creeks15 | 51903318.98 | 49567394.569 | 4401937.17 | 53969331.739
Kattameya Creeks | Katmeya Creeks IPC08 | 8 | Kattameya Creeks8 | 43370006.73 | 40343227.9665 | 4506979.03 | 44850206.9965
Taval Sarai 52 | IPC_5_Gama_Salary |  | Taval Sarai 52 | 251219 | 157993.34 | 0 | 157993.34
Azab Tex Factory | inv ( 2 ) 18-2-2021 | 2 | Azab Tex Factory2 | 651000 | 627575 | 0 | 627575
Lahoon 220/22/22 | Al-Lahoon Sub Inv 03 | 3 | Lahoon 220/22/223 | 47309215.98 | 30408055.58 | 12288108.05 | 42696163.63
MR3 Bridge L&L | MR3L&L-IPC1FINAL | 1 | MR3 Bridge L&L1 | 1778990.75 | 714789.99 | 714792.5 | 1429582.49
Royal City | ROYAL CITY-IPC37 | 37 | Royal City37 | 8335559.1 | 3663301.675 | 0 | 3663301.675
Beni Suef Substation R61 | BSF-CW-EGP-17 FINAL | 17 | Beni Suef Substation R6117 | 664622.04 | 8495990.66 | 0 | 8495990.66
2B3 | IPC-1-2B3 | 1 | 2B31 | 75000 | 75000 | 0 | 75000
Mivida | IPC_5_Mivida |  | Mivida | 121130 | 119918.7 | 0 | 119918.7
AWEER POWER STATION 'H' Phase | IMP-063 | 63 | AWEER POWER STATION 'H' Phase63 | 1050051.08 | 892543.4118 | 116672.34 | 1009215.7518
Mangrouve Hotel - Gouna | IPC_3_RME_Gouna |  | Mangrouve Hotel - Gouna | 20276.74 | 17955.04 | 0 | 17955.04
ORA-ZED Towers01B | IPC_3_Rowad_ORA |  | ORA-ZED Towers01B | 100289.08 | 86098.18 | 0 | 86098.18
ORA-ZED Towers01B | IPC_2_Rowad_ORA |  | ORA-ZED Towers01B | 111198.38 | 95463.81 | 0 | 95463.81
Miscellaneous Projects | 2007210003 |  | Miscellaneous Projects | 34725 | 39239.25 | 0 | 39239.25
EMAAR-PKG# 144, Marassi | PKG#144 - IPC12 | 12 | EMAAR-PKG# 144, Marassi12 | 34831219.06 | 32281831.2825 | 4027726.64 | 36309557.9225
SHAT Al ARAB 400/132kV SS | 385 |  | SHAT Al ARAB 400/132kV SS | 4555728.68 | 4555728.68 | 0 | 4555728.68
MAYSAN 400/132kV SS | 389 |  | MAYSAN 400/132kV SS | 29634.24 | 29634.24 | 0 | 29634.24
ITS | Adv.Adv.ITS Inv. 01 | 1 | ITS1 | 8999900 | 8999900 | 0 | 8999900
Suez Bridge | 1st & FPC |  | Suez Bridge | 193930 | 188112.1 | 0 | 188112.1
Coastal road Bridge Extension | IPC#6 Coastal Road | 6 | Coastal road Bridge Extension6 | 277830 | 243050.29 | 0 | 243050.29
El Boghaz Brigde | IPC#25 | 25 | El Boghaz Brigde25 | 621372.66 | 584090.3 | 0 | 584090.3
Koning Food V2 - LP-08-20 | 8 |  | Koning Food V2 - LP-08-20 | 54070.17 | 61640 | 0 | 61640
LAYYAH CCPP | 497 |  | LAYYAH CCPP | 10252020 | 8674025.85 | 1991043 | 10665068.85
BKG#178-Lagoon Discharge | PKG #178 IPC04 | 4 | BKG#178-Lagoon Discharge4 | 8636178.5 | 6473613.265 | 785199.97 | 7258813.235
Angola Emergency fast-track | ANG-Mor-Inv 6 - Ints | 6 | Angola Emergency fast-track6 | 734052.88 | 511511.17 | 0 | 511511.17
Babil WBS | 200123 |  | Babil WBS | 24800 | 24552 | 0 | 24552
Miscellaneous Projects | 2006210006 |  | Miscellaneous Projects | 4499.71 | 4994.6794 | 0 | 4994.6794
Hassan El Mamoun Bridge | م 1 كوبرى حسن المأمو | 1 | Hassan El Mamoun Bridge1 | 67928433.82 | 6575875 | 6575893.7 | 49850608.7
LRT Project | IPC_3_LRT | 3 | LRT Project3 | 56100 | 47488.65 | 0 | 47488.65
DoubleTree Mangroovy ElGouna | MANGROVE WALL-IPC4 | 4 | DoubleTree Mangroovy ElGouna4 | 8100 | 8424 | 0 | 8424
DPW Onshore Port & Terminal | DP WORLD-IPC23 | 23 | DPW Onshore Port & Terminal23 | 35871966.38 | 26545255.12 | 5380794.96 | 31926050.08
Latin Compound - New Alamin | inv ( 23 )15-12-2020 | 23 | Latin Compound - New Alamin23 | 747986.4 | 481829.36 | 149597.28 | 631426.64
Taval Sarai 52 | tr0025 |  | Taval Sarai 52 | 296812.8 | 234483.03 | 0 | 234483.03
Olympic Multi – Sports Hall | OLYMPIC-IPC03 | 3 | Olympic Multi – Sports Hall3 | 36935466.2 | 2493330 | 19395007.75 | 31381672.5
EGAT Pelletizing Plant | Elco EGAT-IPC17 | 17 | EGAT Pelletizing Plant17 | 20596124.76 | 0 | 0 | 21625930.998
LRT | IPC#2 - LRT | 2 | LRT2 | 1101240 | 998205.6 | 0 | 998205.6
Coastal road Bridge Extension | IPC#1 | 1 | Coastal road Bridge Extension1 | 1811040 | 1742136.52 | 0 | 1742136.52
IKEA Extension MoA | IKEA-IPC08 | 8 | IKEA Extension MoA8 | 18401730.5 | 13497644.42 | 8132475 | 21630119.42
IKEA Extension MoA | IKEA - IPC07 | 7 | IKEA Extension MoA7 | 9400137.01 | 6567550.07 | 1919443.91 | 8486993.98
Royal City | ROYAL CITY-IPC39 | 39 | Royal City39 | 1409870.69 | 872368.1645 | 0 | 872368.1645
Latin Compound - New Alamin | inv ( 17 ) 3-12-2020 | 17 | Latin Compound - New Alamin17 | 648309.2 | 416637.65 | 129661.84 | 546299.49
Oasis Buildings- New Capital | Inv(7)270820 | 7 | Oasis Buildings- New Capital7 | 1347725 | 1264758.63 | 0 | 1264758.63
MOTHANA 400/132kV SS | 394 |  | MOTHANA 400/132kV SS | 22225.68 | 22225.68 | 0 | 22225.68
SHATRA 400/132kV SS | 396 |  | SHATRA 400/132kV SS | 1283093.03 | 1283093.03 | 0 | 1283093.03
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $4 | 4 | Benban 3/ Toshka 2 LOT 44 | 442325.83 | 363503.98 | 46444.21 | 409948.19
West Port Said 220 kV GIS | P-45-Portsaid Inv.01 | 1 | West Port Said 220 kV GIS1 | 72911614.29 | 54165616.26 | 7655719.5 | 61821335.76
New Babil 400/132KV Substation | 2103210004 |  | New Babil 400/132KV Substation | 286636.43 | 286636.43 | 0 | 286636.43
National Batteries LP-05-20 | 21 |  | National Batteries LP-05-20 | 1157895 | 683539.125 | 330000.245 | 1013539.37
EDNC Retail & Offices Civil | Sodic Soreal IPC025 | 25 | EDNC Retail & Offices Civil25 | 29789862.02 | 22686187.95 | 2622078.36 | 25308266.31
Museum of Egyp. Civilization | IPC#4 PII | 4 | Museum of Egyp. Civilization4 | 151118.5 | 151118.5 | 0 | 151118.5
NUCA R05 - Z02 | R5-IPC25 | 25 | NUCA R05 - Z0225 | 20378846.31 | 18194731.96 | 2191402.15 | 20386134.11
Kattameya Creeks | KATAMEYA CREEKS-IPC1 | 1 | Kattameya Creeks1 | 2919397.4 | 2748675.4515 | 287497.83 | 3036173.2815
CFC Podium 2 | CFC-IPC15 | 15 | CFC Podium 215 | 42273319.3 | 40379659.08 | 7601026.25 | 47980685.33
EMAAR-Pkg#162/163- Marassi | PKG162#IPC12 | 12 | EMAAR-Pkg#162/163- Marassi12 | 7499598.77 | 5549152.6804 | 0 | 5549152.6804
Maspiro Towers | IPC#4 | 4 | Maspiro Towers4 | 424000 | 419760 | 0 | 419760
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC01 | 1 | ElSewedy HQ Internal Finishing1 | 1435679.43 | 6886276.98 | 715.5 | 6886992.48
LAYAN Substation | 10466 |  | LAYAN Substation | 619583.3862 | 2094191.84 | 0 | 523547.96
LAYAN Substation | 10465 |  | LAYAN Substation | 31077.615 | 52521.16 | 0 | 26260.58
LAYAN Substation | 10463 |  | LAYAN Substation | 4591717.47 | 3811125.5 | 0 | 3811125.5
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 01 | 1 | Suez Gulf/S4 - 500KV OHTL1 | 76552.57 | 64304.16 | 8038.02 | 72342.18
Zone(J) South Valley Toshka | South Valley Inv. 09 | 9 | Zone(J) South Valley Toshka9 | 54493670 | 40318258.45 | 6975189.81 | 47293448.26
Zone(J) South Valley Toshka | South Valley Inv. 03 | 3 | Zone(J) South Valley Toshka3 | 60204591 | 45875011.95 | 7706449.05 | 53581461
Zone(J) South Valley Toshka | South Valley Inv. 02 | 2 | Zone(J) South Valley Toshka2 | 53192168.25 | 40508508.25 | 6808336.2 | 47316844.45
4 SS - Technical Service | 406 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHAT Al ARAB 400/132kV SS | 391 |  | SHAT Al ARAB 400/132kV SS | 998346.38 | 998346.38 | 0 | 998346.38
MOTHANA 400/132kV SS | 403 |  | MOTHANA 400/132kV SS | 486033.93 | 486033.93 | 0 | 486033.93
NUCA R05 - Z02 | R5-IPC24 | 24 | NUCA R05 - Z0224 | 25733237.29 | 20726444.04 | 2611761.25 | 23338205.29
Angola Emergency fast-track | ANG-Cam-Inv 4 | 4 | Angola Emergency fast-track4 | 22812526.63 | 17352918.87 | 0 | 17352918.87
Ahl Misr Walkway | IPC#2 Ahl Misr | 2 | Ahl Misr Walkway2 | 894212 | 841821.26 | 0 | 841821.26
Koning Food V3 LP-09-20 | 18 |  | Koning Food V3 LP-09-20 | 3907.02 | 2227.02 | 2227 | 4454.02
Koning Food V3 LP-09-20 | 17 |  | Koning Food V3 LP-09-20 | 99912.28 | 56950 | 56950 | 113900
Ministries Buildings | MIN-SHELL-IPC07 | 7 | Ministries Buildings7 | 8605109.8 | 2174820.01 | 5074580.45 | 7249400.46
GOV2 - Infra | GOV 2 IPC 27+28 | 27 | GOV2 - Infra27 | 8993472.71 | 0 | 184362.78 | 184362.78
GOV2 - Infra | GOV2 IPC06 | 6 | GOV2 - Infra6 | 7370174.33 | 52077106.78 | 6103720.7 | 58180827.48
Mohamed Ali Palace | IPC_6_MohamedAli |  | Mohamed Ali Palace | 73816.4 | 62005.78 | 0 | 62005.78
Royal City | ROYAL CITY-IPC40 | 40 | Royal City40 | 7356711.98 | 5481051.519 | 0 | 5481051.519
R5 | inv(9)300620 | 9 | R59 | 754500 | 113175 | 0 | 683331.88
Elsewedy Univ - Enabling Works | sewedy uni-mep-08 | 8 | Elsewedy Univ - Enabling Works8 | 1755356.86 | 2678875.465 | 120962.58 | 2799838.045
Corporate Project LP-02-21 | 39 |  | Corporate Project LP-02-21 | 224640.7 | 175270.05 | 80820.35 | 256090.4
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC013 | 13 | EMAAR-Pkg#162/163- Marassi13 | 0.001 | 4564491.481 | 548962.38 | 5113453.861
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC012 | 12 | EMAAR-Pkg#162/163- Marassi12 | 17538268.49 | 12621618.3045 | 1517977.12 | 14139595.4245
CFC Podium 2 | CFC - IPC018 | 18 | CFC Podium 218 | 16880809.49 | 12196441.12 | 3936267.26 | 16132708.38
Industria Sadat | Sadat Indust Inv. 01 | 1 | Industria Sadat1 | 22759251.19 | 26600720.6 | 2531453.9 | 29132174.5
Akhmem - Qena | Inv.5 Qena Akhmem | 5 | Akhmem - Qena5 | 66637833.28 | 39649510.79 | 9995674.99 | 49645185.78
Toshka GIS 500 kV | Toshka Sub Inv. 06 | 6 | Toshka GIS 500 kV6 | 49689283.81 | 28279012.91 | 13043437 | 41322449.91
Akhmem Assiut | Ref.Ret Asuit akh |  | Akhmem Assiut | 10000000 | 10000000 | 0 | 10000000
Al Montaza Hotels - Alexandria | Inv ( 1 ) montazha | 1 | Al Montaza Hotels - Alexandria1 | 555104 | 555104 | 0 | 555104
GOV2 - Infra | Gov2 ipc 17 | 17 | GOV2 - Infra17 | 583461.9 | 145061.2825 | 32128.34 | 177189.6225
GOV2 - Infra | GOV 2 IPC08 | 8 | GOV2 - Infra8 | 51149312.9 | 17404967.45 | 2733165.6 | 20138133.05
Miscellaneous Projects | 2103210008 |  | Miscellaneous Projects | 57114.88 | 65110.9629 | 0 | 65110.9629
Miscellaneous Projects | 2103210007 |  | Miscellaneous Projects | 62144 | 70844.16 | 0 | 70844.16
Bridge Axis Firdaws | inv- ( 1 ) | 1 | Bridge Axis Firdaws1 | 4225600 | 4225600 | 0 | 4225600
UIC Project (LP-04-21) | 58 |  | UIC Project (LP-04-21) | 48750 | 0 | 0 | 48750
Coastal road Bridge Extension | IPC#4 | 4 | Coastal road Bridge Extension4 | 1400726.25 | 1348899.38 | 0 | 1348899.38
Cairo Monorail - 6th October | IPC#1 - Monorail | 1 | Cairo Monorail - 6th October1 | 2708300 | 2708300 | 0 | 2708300
ORA ZED - Ph 01B - Pkgs A&D | ora zed ph1 ipc11 | 11 | ORA ZED - Ph 01B - Pkgs A&D11 | 34769848.6 | 33022101.84 | 3931072.58 | 36953174.42
ORA ZED-Ph 2-Pkgs A&D | ora Zed2-ipc01 | 1 | ORA ZED-Ph 2-Pkgs A&D1 | 13196047.2 | 15456194.14 | 1838980.61 | 17295174.75
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED Ph1 IPC06 | 6 | ORA ZED - Ph 01B - Pkgs A&D6 | 13829636.33 | 4832623.5365 | 577003.05 | 5409626.5865
Bahr ElBakar – Power Station | IPC#07 -Madkour | 7 | Bahr ElBakar – Power Station7 | 3172890 | 0 | 0 | 3172890
Bahr ElBakar – Power Station | IPC#4 - Madkour | 4 | Bahr ElBakar – Power Station4 | 2706288 | 2679225.12 | 0 | 2679225.12
Bahr ElBakar – Power Station | IPC#1 - Madkour | 1 | Bahr ElBakar – Power Station1 | 1380900 | 1143553.68 | 0 | 1143553.68
Shenzo Aby Bridge - Haggana | IPC#1 Shenzo Aby | 1 | Shenzo Aby Bridge - Haggana1 | 1390700 | 1265346.25 | 0 | 1265346.25
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC02 | 2 | EMAAR-Pkg#162/163- Marassi2 | 8478947.03 | 10179304.7515 | 1304738.06 | 11484042.8115
Mauritania Lot 1 | Inv.16 - Lot 1 | 16 | Mauritania Lot 116 | 497882 | 425674.36 | 0 | 475462.56
Mauritania Lot 1 | Inv.11 - Lot 1 | 11 | Mauritania Lot 111 | 497200 | 472323 | 0 | 472323
Mauritania Lot 1 | Inv.10 - Lot 1 | 10 | Mauritania Lot 110 | 1318961.79 | 1252998.71 | 0 | 1252998.71
Mauritania Lot 1 | Inv.3 - Lot 1 | 3 | Mauritania Lot 13 | 1276811.56 | 1212955.98 | 0 | 1212955.98
Mauritania-Lot 2 | Inv. 9 – Lot 2 | 9 | Mauritania-Lot 29 | 2395607.55 | 2275827.17 | 0 | 2275827.17
Mauritania-Lot 2 | Inv.1 - Lot 2 | 1 | Mauritania-Lot 21 | 71899.6 | 68304.62 | 0 | 68304.62
Mauritania-Lot 2 | Inv.5 – Lot 2 | 5 | Mauritania-Lot 25 | 1284803.55 | 1220563.37 | 0 | 1220563.37
Mauritania-Lot 2 | Inv. 10 – Lot 2 | 10 | Mauritania-Lot 210 | 41450.37 | 39377.85 | 0 | 39377.85
Mauritania-Lot 2 | Inv. 8 – Lot 2 | 8 | Mauritania-Lot 28 | 52491.74 | 49867.15 | 0 | 49867.15
Mauritania-Lot 2 | Inv.2 - Lot 2 | 2 | Mauritania-Lot 22 | 622044.98 | 590942.73 | 0 | 590942.73
Angola Emergency fast-track | ANG-Mor-Inv 6 | 6 | Angola Emergency fast-track6 | 1858950 | 1295368.14 | 0 | 1295368.14
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.02 | 2 | Toshka 2/Owinat East LOT2 OHTL2 | 20597393.87 | 18372485.06 | 2162726.36 | 20535211.42
BKG#178-Lagoon Discharge | PKG#178-IPC03 | 3 | BKG#178-Lagoon Discharge3 | 7805724.83 | 7952024.0415 | 860581.16 | 8812605.2015
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC023 | 23 | EMAAR-PKG# 101-UPTOWN23 | 2544618.3 | 594123.335 | 1279165.17 | 1873288.505
Lekela 250MW Wind Farm | LEKELA-IPC11 | 11 | Lekela 250MW Wind Farm11 | 16648813.83 | 14823033.5915 | 2531638.98 | 17354672.5715
Nuweibaa (Swro) | 2104210002 |  | Nuweibaa (Swro) | 95628.61 | 76502.89 | 19125.72 | 95628.61
Miscellaneous Projects | 2105210017 |  | Miscellaneous Projects | 250000 | 285000 | 0 | 285000
Industria Sadat | Sadat Indust Inv. 02 | 2 | Industria Sadat2 | 27642440.51 | 13234888.76 | 528023.86 | 36658109.81
Akhmem - Qena | Inv.32 Akhmem Qena | 32 | Akhmem - Qena32 | 2008162.56 | 1596489.25 | 301224.38 | 1897713.63
Akhmem - Qena | Inv.21 Qena - Akhmem | 21 | Akhmem - Qena21 | 458158.19 | 364235.76 | 68723.73 | 432959.49
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC012 | 12 | EMAAR-Pkg#162/163- Marassi12 | 3268183.05 | 3176493.7925 | 650200.29 | 3826694.0825
Diplomatic District - Infra | Diplomatic ipc15 | 15 | Diplomatic District - Infra15 | 19671467.57 | 13848783.6757 | 2013157.2 | 15861940.8757
Diplomatic District - Infra | diplomatic ipc11 | 11 | Diplomatic District - Infra11 | 40616631.67 | 33118965.0735 | 4420746.2 | 37539711.2735
Air Force Project | Air Force Inv . 16 | 16 | Air Force Project16 | 34679470.06 | 19300720 | 14199224.58 | 33499944.58
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC016 | 16 | EMAAR-Pkg#162/163- Marassi16 | 49248459.94 | 11495751.178 | 35033674.049 | 46529425.227
Asher Mn Ramadan Bridge No2 | ALAASHER BRIDGE-FINA |  | Asher Mn Ramadan Bridge No2 | 11622150.08 | 7626410 | 7076659 | 14703069
Faculty of Medicine | mansora ipc11 | 11 | Faculty of Medicine11 | 6950534.29 | 5880793.8545 | 347526.71 | 6228320.5645
Faculty of Medicine | Mansoura UNI IPC05 | 5 | Faculty of Medicine5 | 20306602.86 | 17182030.01 | 1015330.14 | 18197360.15
Faculty of Medicine | Mansoura Uni IPC02 | 2 | Faculty of Medicine2 | 13705788.32 | 11596749 | 685289.42 | 12282038.42
NUCA R05 - Z02 | R5 FINSHING-IPC02 | 2 | NUCA R05 - Z022 | 4570313.65 | 4124306.65 | 0 | 4124306.65
NUCA R05 - Z02 | R5 - IPC15 | 15 | NUCA R05 - Z0215 | 48673674 | 47390161.3 | 5828144.4 | 53218305.7
R5 Mix-Use Complex Project | R5-ZONE1-IPC04 | 4 | R5 Mix-Use Complex Project4 | 4897147.5 | 3771309.275 | 471420.92 | 4242730.195
October Dry Port | Dry Port Inv. 10 | 10 | October Dry Port10 | 9358947.94 | 6331059.12 | 2456723.84 | 8787782.96
GOV2 - Infra | Gov2 ipc 21+22 | 21 | GOV2 - Infra21 | 41093940.1 | 23795284.2259 | 3851424.58 | 27646708.8059
GOV2 - Infra | gov2 ipc 20 | 20 | GOV2 - Infra20 | 21567902.14 | 11507176.8086 | 1684882.83 | 13192059.6386
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 1 | 1 | Marsa Alam/ Bernes LOT2 OHTL1 | 2753615.85 | 1733413.48 | 289129.66 | 2022543.14
RING ROAD MARYOTIA EXPANSION | Maryotya IPC07 | 7 | RING ROAD MARYOTIA EXPANSION7 | 7591896.43 | 2515964.776 | 5000000 | 7515964.776
RING ROAD MARYOTIA EXPANSION | Maryotya IPC06 | 6 | RING ROAD MARYOTIA EXPANSION6 | 9909425.48 | 5875866.974 | 0 | 5875866.974
Taval Sarai 52 | IPC_10_Saray |  | Taval Sarai 52 | 892512.2 | 678029.79 | 0 | 678029.79
October Dry Port | Dry Port Inv. 02 | 2 | October Dry Port2 | 543210.26 | 4515924.87 | 142592.69 | 4658517.56
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 07 | 7 | Hosh Essa 220 KV OHTL7 | 474026.67 | 284893.2 | 49772.8 | 334666
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 03 | 3 | Hosh Essa 220 KV OHTL3 | 9303701.3 | 5591524.8 | 976888.64 | 6568413.44
Toshka GIS 500 kV | Toshka Sub Inv. 21 $ | 21 | Toshka GIS 500 kV21 | 522242.54 | 328392.81 | 137088.67 | 465481.48
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC (44) | 44 | EMAAR-Pkg#162/163- Marassi44 | 54841445.41 | 19396451.9605 | 23114817.1 | 42511269.0605
EDNC Retail & Offices Civil | Sodic Soreal IPC029 | 29 | EDNC Retail & Offices Civil29 | 26258236.23 | 20811984.9815 | 0 | 20811984.9815
Coastal road Bridge Extension | IPC#4 - Gharably | 4 | Coastal road Bridge Extension4 | 1230941.25 | 1150131.37 | 0 | 1150131.37
AbuSultan Rd Bridge2 Extension | ELSAWEP-IPC01 | 1 | AbuSultan Rd Bridge2 Extension1 | 10957813.82 | 4381590 | 3830500 | 8212090
seashell Playa | IPC-4-PLAYA | 4 | seashell Playa4 | 92761.8 | 64757.004 | 14841.9 | 79598.904
marassi inland marina | FPC Marassi |  | marassi inland marina | 212142 | 0 | 0 | 14413.48
Capital One | inv ( 2 ) 1-8-2021 | 2 | Capital One2 | 460284.74 | 460284.74 | 0 | 460284.74
Bridge Axis Firdaws | INV ( 2 ) | 2 | Bridge Axis Firdaws2 | 820800 | 771552 | 0 | 771552
EGAT Pelletizing Plant | EGATpelletizingIPC19 | 19 | EGAT Pelletizing Plant19 | 20329650.19 | 19169766.1895 | 1973070.01 | 21142836.1995
NUCA R05 - Z02 | R05 IPC030 | 30 | NUCA R05 - Z0230 | 32070763.5 | 13912382.036 | 1902983.85 | 15815365.886
LAYYAH CCPP | 512 |  | LAYYAH CCPP | 7402941 | 6292499.85 | 1110441.15 | 7402941
10Th of Ramadan LRT | LRT 10Ramadan Inv.03 | 3 | 10Th of Ramadan LRT3 | 5789746.19 | 2460607.5 | 416709.28 | 4499970.18
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC014 | 14 | EMAAR-Pkg#162/163- Marassi14 | 13281620.94 | 11482913.077 | 3139654.64 | 14622567.717
NUCA R05 - Z02 | R05 Zone 2 IPC015 | 15 | NUCA R05 - Z0215 | 19873627.9 | 15888919.345 | 2003450.4 | 17892369.745
October Dry Port | Dry Port Inv. 01 | 1 | October Dry Port1 | 374166 | 3220148.37 | 98219.12 | 3318367.49
Angola Emergency fast-track | ANG-Mor-Inv.-7 | 7 | Angola Emergency fast-track7 | 11344616.16 | 5640030.45 | 0 | 5640030.45
Angola Emergency fast-track | ANG-Mor-Inv 4 | 4 | Angola Emergency fast-track4 | 11414314.93 | 7507137.74 | 0 | 7507137.74
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .26 | 26 | Benban 3/ Toshka 2 LOT 426 | 2767595.56 | 2468297.77 | 0 | 2468297.77
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .24 | 24 | Benban 3/ Toshka 2 LOT 424 | 4186616.13 | 3734064.31 | 0 | 3734064.31
CFC Podium 2 | CFC IPC021 | 21 | CFC Podium 221 | 23565050.79 | 19156725.1095 | 3655193.01 | 22811918.1195
AWEER POWER STATION 'H' Phase | CON/024 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.48 | 141966.52 | 1263502
AWEER POWER STATION 'H' Phase | ENG/042 |  | AWEER POWER STATION 'H' Phase | 344195.19 | 361404.9495 | 0 | 361404.9495
4 SS - Technical Service | 422 |  | 4 SS - Technical Service | 493890.57 | 493890.57 | 0 | 493890.57
Lahoon 220/22/22 | Al-Lahoon Sub Inv 02 | 2 | Lahoon 220/22/222 | 11588904.14 | 6845805.5 | 2766564.04 | 10135017.52
Miscellaneous Projects | 2007210009 |  | Miscellaneous Projects | 1111973.86 | 1267650.2004 | 0 | 1267650.2004
ORA ZED - Ph 01B - Pkgs A&D | Ora zed ph.1 IPC18 | 18 | ORA ZED - Ph 01B - Pkgs A&D18 | 9690075.24 | 7029281.442 | 836345.1 | 7865626.542
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC 16 | 16 | ORA ZED - Ph 01B - Pkgs A&D16 | 28676537.67 | 23357925.2135 | 2830326.27 | 26188251.4835
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc 27 | 27 | ORA ZED-Ph 2-Pkgs A&D27 | 6420474.62 | 5328993.921 | 674149.84 | 6003143.761
10th of Ramadan Railway | IPC#6 | 6 | 10th of Ramadan Railway6 | 932871 | 762121.31 | 0 | 762121.31
33KV Canal Farm Grid | Inv. 14 Farm | 14 | 33KV Canal Farm Grid14 | 15483945.5 | 11814250.42 | 2322591.83 | 14136842.25
RING ROAD MARYOTIA EXPANSION | El Marg IPC04 | 4 | RING ROAD MARYOTIA EXPANSION4 | 7006735.31 | 6191957.41 | 0 | 6191957.41
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC022 | 22 | EMAAR-PKG# 101-UPTOWN22 | 2547253.71 | 1912651.7855 | 836230.61 | 2748882.3955
LAYYAH CCPP | 514 |  | LAYYAH CCPP | 5428824 | 4614500.4 | 814323.6 | 5428824
New Babil 400/132KV GIS Substa | 2107210001 |  | New Babil 400/132KV GIS Substa | 444051.52 | 444051.52 | 0 | 444051.52
Faculty of Medicine | Mansoura UNI IPC04 | 4 | Faculty of Medicine4 | 10896948.57 | 9220050.36 | 544847.43 | 9764897.79
Cairo-Alex Railway | Railway IPC06 | 6 | Cairo-Alex Railway6 | 18621679.05 | 13109805.9125 | 1862167.9 | 14971973.8125
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC024 | 24 | EMAAR- Pkg 140-ITP-Mivida24 | 4573435.86 | 4604153.83 | 480210.76 | 5084364.59
Mansoura University | IPC#2 - Mansura Proj | 2 | Mansoura University2 | 808132.5 | 776190.97 | 0 | 776190.97
GOV2 - Infra | GOV 2 IPC07 | 7 | GOV2 - Infra7 | 15231382.33 | 21950412.282 | 2806208.25 | 24756620.532
TZ – Offshore E&M Procurement | 429 |  | TZ – Offshore E&M Procurement | 2181.32 | 1745.05 | 436.27 | 2181.32
P.I.Parks - Plot 10 | PIP indust Inv.01 | 1 | P.I.Parks - Plot 101 | 3919953.93 | 14845483.72 | 1878225.2 | 16723708.92
Group # 1 - 25 LX | Reailway PSP Inv. 05 | 5 | Group # 1 - 25 LX5 | 840000 | 831600 | 0 | 831600
Playa Resort | 21000005 |  | Playa Resort | 70034022.4 | 0 | 138667364.352 | 69333682.176
East Owainat 5 LOTS | East Owainat Inv.1 V | 1 | East Owainat 5 LOTS1 | 60208802.8 | 24091026.87 | 31609621.46 | 55700648.33
Museum of Egyp. Civilization | IPC#4 - Fianl Museum | 4 | Museum of Egyp. Civilization4 | 90000 | 82350 | 0 | 82350
Museum of Egyp. Civilization | FPC - Egy Museum |  | Museum of Egyp. Civilization | 519537.25 | 462531.51 | 0 | 462531.51
seashell Playa | IPC-3-PLAYA | 3 | seashell Playa3 | 66653.75 | 46530.9821 | 10664.6 | 57195.5821
El Salam Bridge | IPC#1 | 1 | El Salam Bridge1 | 2538210 | 2231281.07 | 0 | 2231281.07
Bahr ElBakar – Power Station | IPC02 Madkour | 2 | Bahr ElBakar – Power Station2 | 1357812 | 1344233.88 | 0 | 1344233.88
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 12 | 12 | Benban 500 K.V / 100 K.M12 | 87149410.25 | 70307183.38 | 9150688.08 | 79457871.46
Bridge Axis Firdaws | INV ( 4 ) | 4 | Bridge Axis Firdaws4 | 2505721.6 | 2355378.31 | 0 | 2355378.31
Transportation Hub | inv ( 1 ) T0020 | 1 | Transportation Hub1 | 2541840 | 2453890 | 0 | 2453890
Railway Bridge - Assuit | IPC#3 Assuit | 3 | Railway Bridge - Assuit3 | 1072500 | 571603.96 | 0 | 571603.96
ElSewedy HQ Internal Finishing | elsewedy hq-ipc06 | 6 | ElSewedy HQ Internal Finishing6 | 5418722.29 | 8157201.3445 | 1580547.38 | 14737748.7245
Racecores 3092-16 132KV C | 10903 |  | Racecores 3092-16 132KV C | 14571.84 | 12094.63 | 0 | 12094.63
ElMoneeb 2 | IPC#1 | 1 | ElMoneeb 21 | 677700 | 324903.16 | 0 | 670923
New Babil 400/132KV GIS Substa | 2107210003 |  | New Babil 400/132KV GIS Substa | 904549.4 | 904549.4 | 0 | 904549.4
New Babil 400/132KV GIS Substa | 2108210002 |  | New Babil 400/132KV GIS Substa | 1014974.91 | 1014974.91 | 0 | 1014974.91
MDF Factory | MDF IPC04 | 4 | MDF Factory4 | 9184332.61 | 8359615.9705 | 2410887.31 | 10770503.2805
Royal City | Royal city ipc (41) | 41 | Royal City41 | 6547385.9 | 5167630.645 | 0 | 5167630.645
Royal City | royal center ipc 22 | 22 | Royal City22 | 3302465.28 | 2767215.594 | 0 | 2767215.594
Ain Sokhna Port Development | IPC#04 - Sokhna Port | 4 | Ain Sokhna Port Development4 | 2140008 | 1963215.39 | 0 | 1963215.39
Ras El Teen Hangar | RasElTeenHangarIPC04 | 4 | Ras El Teen Hangar4 | 2573991.89 | 3007594.1505 | 42819.1 | 3050413.2505
Ras El Teen Hangar | Ras El Teen IPC03 | 3 | Ras El Teen Hangar3 | 2982066.9 | 1914188.735 | 939351.08 | 2853539.815
Ras El Teen Hangar | Ras El Teen IPC02 | 2 | Ras El Teen Hangar2 | 1926606.45 | 1843569.7125 | 0 | 1843569.7125
AMRIYA WWTP (3RD STAGE) | 220621002 |  | AMRIYA WWTP (3RD STAGE) | 4934047.47 | 4185828.48 | 493404.75 | 4801212.2
AMRIYA WWTP (3RD STAGE) | 220221003 |  | AMRIYA WWTP (3RD STAGE) | 2057234 | 1479111.1 | 411446.92 | 1933799.94
MDF Factory | MDF3- IPC 10 | 10 | MDF Factory10 | 4189749.3 | 3120120.2186 | 1044499.31 | 4164619.5286
MDF Factory | MDF FACTORY3 IPC 6+7 | 6 | MDF Factory6 | 3298482.11 | 2391399.5354 | 940067.4 | 3331466.9354
MDF Factory | MDF FACTORY3 IPC04 | 4 | MDF Factory4 | 785880.92 | 569763.6688 | 223976.06 | 793739.7288
MDF Factory | MDF FACTORY3 IPC02 | 2 | MDF Factory2 | 5118766.06 | 711105.3884 | 1458848.33 | 5169953.7184
Mar Girgis Church- R3 | IPC-1-Margirgs | 1 | Mar Girgis Church- R31 | 185600 | 185600 | 0 | 185600
ESU Ph2-Enabling & Struc | ESU2 MEP IPC-Final |  | ESU Ph2-Enabling & Struc | 14749060.76 | 35615959.8175 | 0 | 55309357.688
Museum of Egyp. Civilization | IPC#3 | 3 | Museum of Egyp. Civilization3 | 224307.5 | 206163.22 | 0 | 209943.665
Lekela 250MW Wind Farm | LEKELA-IPC08 | 8 | Lekela 250MW Wind Farm8 | 38206684.39 | 33513527.4795 | 6289039.17 | 39802566.6495
Capital One | inv ( 4 ) Captal 1 | 4 | Capital One4 | 788311.94 | 775825.97 | 0 | 775825.97
ENR-Signaling Inst. | ENR-Sign Inst Inv01 | 1 | ENR-Signaling Inst.1 | 1196205 | 1004812.57 | 119620.5 | 1124433.07
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.06 | 6 | Toshka 2/Owinat East LOT2 OHTL6 | 33344735.68 | 27992509.03 | 3501197.25 | 31493706.28
Cairo Monorail - 6th October | IPC#2 - Monorail | 2 | Cairo Monorail - 6th October2 | 1197000 | 1160780 | 0 | 1160780
10Th of Ramadan LRT | LRT 10Ramadan Inv.02 | 2 | 10Th of Ramadan LRT2 | 16485062.01 | 9190680.29 | 1496260.66 | 12209396.35
Al-Ula Towers | inv ( 2 ) ULA | 2 | Al-Ula Towers2 | 613093.2 | 637616.92 | 0 | 637616.92
Capital One | inv ( 6 ) Captal one | 6 | Capital One6 | 2030906.9 | 2010597.835 | 0 | 2010597.835
Toshka Farm | Toshka Farm Inv. 02 | 2 | Toshka Farm2 | 20313113.04 | 8632709.75 | 10664384.35 | 19297094.1
Angola Emergency fast-track | ANG-MOR-Inv 7 - Ints | 7 | Angola Emergency fast-track7 | 2363420.65 | 1231785.37 | 0 | 1231785.37
Angola Emergency fast-track | ANG-Cam-Inv 7 | 7 | Angola Emergency fast-track7 | 13411588.85 | 6782413.8 | 0 | 6782413.8
158E/2019 33kv Project | 10922 |  | 158E/2019 33kv Project | 430399.8608 | 451919.8538 | 0 | 451919.8538
Ahl Misr P3 – Zamalek Sector | IPC#3 Ahl Misr Zamal | 3 | Ahl Misr P3 – Zamalek Sector3 | 391500 | 375776.25 | 0 | 375776.25
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC08 | 8 | ElSewedy HQ Internal Finishing8 | 12855494 | 10012746.11 | 3360337.15 | 13373083.26
Kattameya Creeks | Katamya creeks ipc45 | 45 | Kattameya Creeks45 | 50790503.79 | 24274088.3716 | 28259040.56 | 52533128.9316
Kattameya Creeks | Katamya Creeks ipc44 | 44 | Kattameya Creeks44 | 34374886.21 | 8345106.3084 | 27116604.35 | 35461710.6584
Kattameya Creeks | katamye creeks ipc43 | 43 | Kattameya Creeks43 | 42016089.18 | 21224102 | 22275160.68 | 43499262.68
Kattameya Creeks | Katameya ipc 40 | 40 | Kattameya Creeks40 | 52383248.29 | 52039038 | 2137757.92 | 54176795.92
Kattameya Creeks | ipc27 katameya creek | 27 | Kattameya Creeks27 | 35445373.6 | 35452924 | 1410264.47 | 37664003.47
Kattameya Creeks | Katameya Creks IPC09 | 9 | Kattameya Creeks9 | 45658900.57 | 43056438.1785 | 4405818.41 | 47462256.5885
Ain Sokhna Bridge – RME | IPC#8 Sokhna Bridge | 8 | Ain Sokhna Bridge – RME8 | 1223300 | 907134.89 | 0 | 1124332.75
Ain Sokhna Bridge – RME | IPC#2 -Sokhna Bridge | 2 | Ain Sokhna Bridge – RME2 | 1012226.3 | 995406.31 | 0 | 995406.31
R06 Loack & Load | R6 L&L ipc1(final) | 1 | R06 Loack & Load1 | 1050000 | 997500 | 0 | 997500
Governmental Campus-N2 | 29 |  | Governmental Campus-N2 | 1024799.6 | 1024517.7776 | 0 | 1024517.7776
Governmental Campus-N2 | 31 |  | Governmental Campus-N2 | 2651.47 | 2601.1071 | 0 | 2601.1071
Governmental Campus-N2 | 30 |  | Governmental Campus-N2 | 18925.51 | 18872.8783 | 0 | 18872.8783
SHATRA 400/132kV SS | 433 |  | SHATRA 400/132kV SS | 38812.4 | 38812.4 | 0 | 38812.4
Waldorf Astoria Cairo | Astoria IPC8 | 8 | Waldorf Astoria Cairo8 | 9001222.98 | 2805915.699 | 2865083.61 | 5670999.309
Al Montaza Hotels - Alexandria | inv ( 4 ) montazha | 4 | Al Montaza Hotels - Alexandria4 | 1596381.5 | 1576281.5 | 0 | 1576281.5
Lekela 250MW Wind Farm | LEKELA IPC015 | 15 | Lekela 250MW Wind Farm15 | 15041907.67 | 8754195.8235 | 0 | 8754195.8235
New Babil 400/132KV GIS Substa | 2111210001 |  | New Babil 400/132KV GIS Substa | 1083109.8 | 1083109.8 | 0 | 1083109.8
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.09 | 9 | Toshka 2/Owinat East LOT2 OHTL9 | 1906856.72 | 1509835.43 | 200219.96 | 1710055.39
Ext.110 S. Military 220 Kv S/S | Extension kayn Inv 2 | 2 | Ext.110 S. Military 220 Kv S/S2 | 43930695.69 | 28334900 | 10982673.92 | 39317573.92
October Dry Port | Dry Port Inv. 04 | 4 | October Dry Port4 | 4494774.84 | 4307238.86 | 1179878.4 | 5487117.26
Akhmem - Qena | Ref.Ret Qen-akh 5 |  | Akhmem - Qena | 11634107.57 | 0 | 0 | 11634107.57
Akhmem - Qena | Ret Qen-akh 5 T |  | Akhmem - Qena | 11634107.57 | 11634107.57 | 0 | 11634107.57
Faculty of Medicine | FacultyMedcine IPC06 | 6 | Faculty of Medicine6 | 22540491.43 | 19072236.24 | 1127024.57 | 20199260.81
Racecores 3092-17 132KV E | 11162 |  | Racecores 3092-17 132KV E | 3031979.8732 | 7549629.9 | 0 | 2516543.3
158E/2019 33kv Project | 10983 |  | 158E/2019 33kv Project | 45900 | 48195 | 0 | 48195
EGAT Pelletizing Plant | EGAT WaterTank IPC03 | 3 | EGAT Pelletizing Plant3 | 725357.86 | 718104.283 | 0 | 718104.283
EGAT Pelletizing Plant | EGAT WaterTank IPC05 | 5 | EGAT Pelletizing Plant5 | 923594.33 | 914358.3865 | 0 | 914358.3865
El Taameer Axis Expansion | IPC#01 | 1 | El Taameer Axis Expansion1 | 490050 | 473388.3 | 0 | 473388.3
Pridge 5 | inv ( 1 Fina ) pridg | 1 | Pridge 51 | 2500000 | 1964967 | 0 | 1964967
Ministries Buildings | Minist Core IPC08 | 8 | Ministries Buildings8 | 14605110.03 | 6152200 | 6152200 | 12304400
Al Montaza Hotels - Alexandria | inv ( 6 ) Montazha | 6 | Al Montaza Hotels - Alexandria6 | 1120815.3 | 1113915.3 | 0 | 1113915.3
Get Business Complex | INV ( 12 ) GET | 12 | Get Business Complex12 | 159042.1 | 149499.58 | 0 | 149499.58
EDNC Retail & Offices Civil | soreal-ipc32 | 32 | EDNC Retail & Offices Civil32 | 17472419.88 | 19068785.824 | 0 | 19068785.824
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.04 | 4 | 10th Ramadan Indu Park Plot114 | 3650724.08 | 0 | 574989.04 | 574989.04
Ring Road Bridges Project | inv ( 1 ) | 1 | Ring Road Bridges Project1 | 345747.5 | 18843.23 | 0 | 309789.76
New Babil 400/132KV GIS Substa | 2112210003 |  | New Babil 400/132KV GIS Substa | 65899.31 | 65899.31 | 0 | 65899.31
New Babil 400/132KV GIS Substa | 2112210002 |  | New Babil 400/132KV GIS Substa | 234031.6 | 234031.6 | 0 | 234031.6
LAYYAH CCPP | 517 |  | LAYYAH CCPP | 15933480 | 12250264 | 3683216 | 15933480
Ministries Buildings | MinistSHELL IPC08 | 8 | Ministries Buildings8 | 11226263.85 | 4728860 | 4728862.5 | 9457722.5
Playa Resort | 005/2022 |  | Playa Resort | 65139712 | 0 | 128976629.76 | 64488314.88
Sokhna Port Expansion | SPX.1 ipc 22+23 | 22 | Sokhna Port Expansion22 | 3517168 | 2087493.15 | 946930 | 3034423.15
Sokhna Port Expansion | sokhna port ex ipc03 | 3 | Sokhna Port Expansion3 | 83177845.64 | 55802954.372 | 17467347.58 | 73270301.952
Olympic Multi – Sports Hall | Olympic MEP IPC2 | 2 | Olympic Multi – Sports Hall2 | 42437483 | 1103175 | 35000000.9 | 36103175.9
RING ROAD MARYOTIA EXPANSION | Maryotia IPC013 | 13 | RING ROAD MARYOTIA EXPANSION13 | 53815173.27 | 41457209.53 | 4159591.2 | 45616800.73
seashell Playa | IPC-1-PLAYA | 1 | seashell Playa1 | 70125 | 48954.26 | 11220 | 60174.26
Port Said Grain Storage | IPC#4 GSCC PortSaeid | 4 | Port Said Grain Storage4 | 1039500 | 744399.45 | 0 | 887185.95
Port Said Grain Storage | IPC7 PORTSAID | 7 | Port Said Grain Storage7 | 1270500 | 833414.09 | 0 | 875764.94
Ring Road Bridges Project | INV ( 4 ) Ring R | 4 | Ring Road Bridges Project4 | 1437004.5 | 1296029.35 | 0 | 1296029.35
AWEER POWER STATION 'H' Phase | ENG/045 |  | AWEER POWER STATION 'H' Phase | 76984.73 | 80833.9665 | 0 | 80833.9665
AWEER POWER STATION 'H' Phase | ENG/049 |  | AWEER POWER STATION 'H' Phase | 177536.41 | 186413.2305 | 0 | 186413.2305
TZ – Offshore E&M Procurement | 427 |  | TZ – Offshore E&M Procurement | 33185.28 | 26548.22 | 6637.06 | 33185.28
TZ – Offshore E&M Procurement | 449 |  | TZ – Offshore E&M Procurement | 80448.15 | 68380.93 | 12067.22 | 80448.15
Benban 500 K.V / 100 K.M | رد تامين2بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 15000000 | 15000000 | 0 | 15000000
El Taameer Axis Expansion | IPC#3 Taamer Axis | 3 | El Taameer Axis Expansion3 | 1404810 | 1329632.46 | 0 | 1329632.46
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC 10 | 10 | ElSewedy HQ Internal Finishing10 | 10645458.95 | 0 | 2838099.58 | 10819981.5175
Racecores 3092-17 132KV E | 11142 |  | Racecores 3092-17 132KV E | 3674.19 | 3674.19 | 0 | 3674.19
Racecores 3092-17 132KV E | 11143 |  | Racecores 3092-17 132KV E | 3152 | 3152 | 0 | 3152
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.8 | 8 | Nagaa Hamady/Assuit OHTL8 | 2306137.06 | 1382954.13 | 242144.39 | 1625098.52
RING ROAD MARYOTIA EXPANSION | RING ROAD ELMARG-01 | 1 | RING ROAD MARYOTIA EXPANSION1 | 53196756.68 | 47818510.6105 | 0 | 47818510.6105
New Giza Teaching Hospital | new giza hos ipc 23 | 23 | New Giza Teaching Hospital23 | 8466924.1 | 3527907.892 | 2289022.09 | 7316929.982
New Giza Teaching Hospital | New giza IPC7 | 7 | New Giza Teaching Hospital7 | 20034184.42 | 13696429.151 | 1934334.62 | 15630763.771
New Giza Teaching Hospital | newgizahospital ipc6 | 6 | New Giza Teaching Hospital6 | 21174583.68 | 13704613.324 | 1755133.01 | 15459746.334
Miscellaneous Projects | 2111210002 |  | Miscellaneous Projects | 40500 | 46170 | 0 | 46170
Egat Rolling Mill no.4 | Rolling mill-IPC10 | 10 | Egat Rolling Mill no.410 | 7998755.08 | 6084201.904 | 2234503.38 | 8318705.284
Egat Rolling Mill no.4 | ROLLING MILL IPC05 | 5 | Egat Rolling Mill no.45 | 11462591.69 | 9293714.7045 | 2627380.65 | 11921095.3545
Egat Rolling Mill no.4 | ROLLING MILL IPC 02 | 2 | Egat Rolling Mill no.42 | 14442827.29 | 12106800.3045 | 2913740.08 | 15020540.3845
EGAT Lock & Load | Lock& Load ipc 16 | 16 | EGAT Lock & Load16 | 1100000 | 1134000.01 | 9999.99 | 1144000
EGAT Lock & Load | EGAT L&L ipc 09 | 9 | EGAT Lock & Load9 | 3980460.75 | 3741633.0975 | 398046.08 | 4139679.1775
EGAT Lock & Load | EGAT L&L IPC04 | 4 | EGAT Lock & Load4 | 879124 | 826376.56 | 87912.4 | 914288.96
New Babil 400/132KV GIS Substa | 2112210005 |  | New Babil 400/132KV GIS Substa | 1644635.27 | 1644635.27 | 0 | 1644635.27
ElSewedy HQ Internal Finishing | Elsewedy HQIPC23(24) | 23 | ElSewedy HQ Internal Finishing23 | 25519032.04 | 1915761.653 | 7296526.369 | 12977797.222
Ain Sokhna Port Development | IPC#5 - Sokhna Port | 5 | Ain Sokhna Port Development5 | 1262056 | 1139198.12 | 0 | 1139198.12
Cairo-Alex Railway | Railway IPC05 | 5 | Cairo-Alex Railway5 | 22089260.95 | 15620324.6875 | 2208926.1 | 17829250.7875
Cairo-Alex Railway | Railway IPC04 | 4 | Cairo-Alex Railway4 | 9667643.81 | 6825060.3005 | 966764.38 | 7791824.6805
Cairo-Alex Railway | CAIRO-ALEX-IPC01 | 1 | Cairo-Alex Railway1 | 7627640.67 | 5389084.49 | 762764.7 | 6151849.19
Egyptian Exchange building | IPC-3-BORSA | 3 | Egyptian Exchange building3 | 80683.9 | 71445.6 | 0 | 71445.6
Egyptian Exchange building | IPC-1-BORSA | 1 | Egyptian Exchange building1 | 147272.73 | 130009.99 | 0 | 130009.99
Benban 500 K.V / 100 K.M | Ref-Ret-benban 1 $ T |  | Benban 500 K.V / 100 K.M | 1145169.37 | 964639.99 | 180529.38 | 1145169.37
Tamey El-amdeed Substation | Tam CW Final |  | Tamey El-amdeed Substation | 2457951.55 | 14135046.53 | 0 | 14135046.53
Port Said Port Silos | port said ipc18 | 18 | Port Said Port Silos18 | 7866196.51 | 3958149.4004 | 3786619.65 | 7744769.0504
Port Said Port Silos | port said ipc12 | 12 | Port Said Port Silos12 | 2086813.53 | 1843797.0112 | 208681.35 | 2052478.3612
Port Said Port Silos | portsaid soils ipc32 | 32 | Port Said Port Silos32 | 3968922.29 | 2296974.7655 | 396892.23 | 2693866.9955
Port Said Port Silos | supply egp ipc 3 | 3 | Port Said Port Silos3 | 3085091.63 | 9231726.9128 | 1234036.64 | 2616440.8882
Angola Emergency fast-track | ANG-Mor-Inv 3 - Ints | 3 | Angola Emergency fast-track3 | 13452980.7 | 8544758.08 | 0 | 8544758.08
Angola Emergency fast-track | ANG-Cam-Inv 8 - Ints | 8 | Angola Emergency fast-track8 | 630183.71 | 349104.59 | 0 | 349104.59
MDF Factory | IPC07-MDF | 7 | MDF Factory7 | 15235053.51 | 14452381.0155 | 2109738.13 | 16562119.1455
PLAYA ROOF & Wet Areas | IPC-3-PLAYA ROOF | 3 | PLAYA ROOF & Wet Areas3 | 27985.3 | 24014.18 | 0 | 24014.18
Ain Sokhna Bridge – RME | IPC#5 SOKHNA BRIDG | 5 | Ain Sokhna Bridge – RME5 | 1178375 | 929687.14 | 0 | 1132649.55
Port Saad Industiral zone | IPC#2 | 2 | Port Saad Industiral zone2 | 2861100 | 2755239.3 | 0 | 2755239.3
Ain Sokhna Bridge – RME | IPC#6 Sokhna Bridge | 6 | Ain Sokhna Bridge – RME6 | 1633000 | 1563825.52 | 0 | 1566925.77
Egat Rolling Mill no.4 | Rolling Mill ipc 01 | 1 | Egat Rolling Mill no.41 | 21476647.49 | 16966551.5245 | 5369161.87 | 22335713.3945
Port Saeed East - OHTL | Port said OHTL Inv.1 | 1 | Port Saeed East - OHTL1 | 5342562.5 | 3413080 | 0 | 3413080
New Babil 400/132KV GIS Substa | 2112210009 |  | New Babil 400/132KV GIS Substa | 138115.2 | 138115.2 | 0 | 138115.2
Racecores 3092-16 132KV C | 11456 |  | Racecores 3092-16 132KV C | 484878.9 | 804898.95 | 0 | 402449.475
MDF Factory | mdf factory2 ipc02 | 2 | MDF Factory2 | 2969783.71 | 2999481.5494 | 0 | 2999481.5494
El Taameer Axis Expansion | IPC#4 - Taamer Axis | 4 | El Taameer Axis Expansion4 | 1047618 | 1011998.99 | 0 | 1011998.99
EDNC Retail & Offices Civil | sodic soreal ipc34 | 34 | EDNC Retail & Offices Civil34 | 4991381.7 | 2767127.555 | 0 | 2767127.555
SHAT Al ARAB 400/132kV SS | 435 |  | SHAT Al ARAB 400/132kV SS | 508993.48 | 508993.48 | 0 | 508993.48
SHATRA 400/132kV SS | 441 |  | SHATRA 400/132kV SS | 4928 | 4928 | 0 | 4928
LAYAN Substation | 11302 |  | LAYAN Substation | 13800 | 14490 | 0 | 14490
Houd Negaih | Houd Negaih Inv.01 | 1 | Houd Negaih1 | 1956673.81 | 1360213 | 205450.75 | 1565663.75
AWEER POWER STATION 'H' Phase | CON/028 |  | AWEER POWER STATION 'H' Phase | 159712.34 | 140191.9385 | 17745.82 | 157937.7585
EGAT Lock & Load | EGAT L&L IPC02 | 2 | EGAT Lock & Load2 | 2362059.16 | 2220335.608 | 236205.92 | 2456541.528
Racecores 3092-16 132KV C | 11366 |  | Racecores 3092-16 132KV C | 2885225.48 | 26818170.83 | 0 | 2438015.53
Royal City | ROYAL CITY2-IPC17 | 17 | Royal City17 | 3716185.79 | 2058324.5495 | 0 | 2058324.5495
AWEER POWER STATION 'H' Phase | LOC/023 |  | AWEER POWER STATION 'H' Phase | 569423.12 | 499826.95 | 63269.24 | 563096.19
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 2 Equ | 2 | Hosh Essa 220 KV OHTL2 | 6276017.62 | 3768594.85 | 662276.76 | 4430871.61
Ain Sokhna Port Development | IPC#8 Sokhna Port | 8 | Ain Sokhna Port Development8 | 1481544 | 1147950.32 | 0 | 1384041.14
PLAYA ROOF & Wet Areas | IPC-5-PLAYA ROOF | 5 | PLAYA ROOF & Wet Areas5 | 259426.25 | 222613.67 | 0 | 222613.67
Playa Resort | 006/2022 |  | Playa Resort | 127114464 | 0 | 246119024.4 | 123059512.2
Racecores 3092-16 132KV C | 11425 |  | Racecores 3092-16 132KV C | 13800 | 14490 | 0 | 14490
158E/2019 33kv Project | 11384 |  | 158E/2019 33kv Project | 0 | -33940 | 0 | -33940
EGAT Pelletizing Plant | EGAT WATER TANK IPC9 | 9 | EGAT Pelletizing Plant9 | 930000 | 920700 | 0 | 920700
MDF Factory | MDF ipc12 | 12 | MDF Factory12 | 35128478.15 | 25430949.4775 | 4011840.31 | 29442789.7875
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC38 | 38 | EMAAR-Pkg#162/163- Marassi38 | 113074931.25 | 46024929.671 | 44314466.39 | 90339396.061
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 11 | 11 | Suez Gulf/S4 - 500KV OHTL11 | 243376.33 | 72921.11 | 0 | 72921.11
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 16 | 16 | Suez Gulf/S4 - 500KV OHTL16 | 192316.29 | 76135.36 | 0 | 76135.36
TZ – Offshore E&M Procurement | 474 |  | TZ – Offshore E&M Procurement | 3038500.01 | 2126950.01 | 303850 | 2430800.01
AWEER POWER STATION 'H' Phase | CON/030 |  | AWEER POWER STATION 'H' Phase | 2044317.83 | 1794456.76 | 227146.43 | 2021603.19
Luxor North Axis Bridge | IPC#5 - Luxor Onshor | 5 | Luxor North Axis Bridge5 | 1696950 | 1646041.5 | 0 | 1646041.5
MDF Factory | ipc 22 Mdf Factory | 22 | MDF Factory22 | 9440396.83 | 9131113.5915 | 875083.18 | 10006196.7715
LAYYAH CCPP | 521 |  | LAYYAH CCPP | 14441700 | 12253402 | 2188298 | 14441700
MDF Factory | MDF Factory ipc 41 | 41 | MDF Factory41 | 12031521.12 | 7229637.5348 | 4743990.95 | 11973628.4848
MDF Factory | MDF IPC 17 | 17 | MDF Factory17 | 12397151.01 | 13200508.7005 | 1846776.8 | 15047285.5005
East Owainat 5 LOTS | East Owainat Inv. 06 | 6 | East Owainat 5 LOTS6 | 31589348.53 | 12888446.17 | 16584407.98 | 29472854.15
PLAYA ROOF & Wet Areas | IPC-7-PLAYA ROOF | 7 | PLAYA ROOF & Wet Areas7 | 157743.65 | 95534.82 | 0 | 95534.82
Racecores 3092-17 132KV E | 11458 |  | Racecores 3092-17 132KV E | 51311.145 | 127764.72 | 0 | 42588.24
IKEA Extension MoA | IKEA Final IPC014 | 14 | IKEA Extension MoA14 | 10453317.84 | 20582119.9 | 0 | 20582119.9
Playa Resort | 007/2022 |  | Playa Resort | 260936078 | 30000000 | 475224433.8 | 252612216.9
Sokhna Port Expansion | sokhna port ex ipc01 | 1 | Sokhna Port Expansion1 | 26869010.86 | 16602157.843 | 5642492.28 | 22244650.123
Olympic Multi – Sports Hall | OLYMPIC MEP IPC01 | 1 | Olympic Multi – Sports Hall1 | 127782862.01 | 21998170 | 84159086.65 | 106157256.65
Air Defense College | air devance ipc02 | 2 | Air Defense College2 | 43054725.7 | 5061464.99 | 15184410 | 36435094.99
October Dry Port | Dry Port Inv. 03 | 3 | October Dry Port3 | 8842219.45 | 3831410.7 | 2321082.61 | 6152493.31
Waldorf Astoria Cairo | waldorf- IPC 14 | 14 | Waldorf Astoria Cairo14 | 13597376.25 | 6216098 | 6350420.2 | 12566518.2
Waldorf Astoria Cairo | waldorf- IPC13 | 13 | Waldorf Astoria Cairo13 | 11273556.71 | 5389256 | 5505974.65 | 10895230.65
Waldorf Astoria Cairo | Waldorf_IPC 11 | 11 | Waldorf Astoria Cairo11 | 22454296.86 | 10757000 | 11695677.26 | 22452677.26
New Babil 400/132KV GIS Substa | 220321002 |  | New Babil 400/132KV GIS Substa | 2062842.53 | 2062842.53 | 0 | 2062842.53
ElSewedy HQ Internal Finishing | EL SEWEDY HQ IPC14+ | 14 | ElSewedy HQ Internal Finishing14 | 227373.9 | 93658.425 | 125227.8 | 218886.225
EMAAR-Pkg#162/163- Marassi | pkg#177 ipc 26+27 | 26 | EMAAR-Pkg#162/163- Marassi26 | 1329766.23 | 2043641.8815 | 245784.77 | 2289426.6515
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC30 | 30 | EMAAR-Pkg#162/163- Marassi30 | 18828872.42 | 11954931.111 | 2185712.29 | 14140643.401
Mivida BP#189 | ipc 10 Emaar pkg#189 | 10 | Mivida BP#18910 | 29038558.46 | 23647399.753 | 4548578.7 | 28195978.453
Mivida BP#189 | Emaar pkg #189ipc16 | 16 | Mivida BP#18916 | 24459783.78 | 22512171.879 | 6258221.77 | 28770393.649
Mivida BP#189 | Emaar PKG#189-IPC 13 | 13 | Mivida BP#18913 | 16636045.76 | 53623446.998 | 6413031.96 | 60036478.958
Mivida BP#189 | pkg#189- IPC8 | 8 | Mivida BP#1898 | 80364676.81 | 66596247.2075 | 8059948.84 | 74656196.0475
Ismailiya East Substation | ISE-CW-EGP-27 | 27 | Ismailiya East Substation27 | 395246 | 10729225.46 | 0 | 10729225.46
New Giza Teaching Hospital | giza hospital ipc04 | 4 | New Giza Teaching Hospital4 | 36077726.42 | 27335611.781 | 5103959.99 | 32439571.771
Abou Ghaleb Bridge | Abo Ghaleb ipc03 | 3 | Abou Ghaleb Bridge3 | 3122399.3 | 2053971.909 | 0 | 2053971.909
ElSewedy HQ Internal Finishing | el sewedy HQ ipc14 | 14 | ElSewedy HQ Internal Finishing14 | 15184089.24 | 1654906.512 | 5800933.2 | 11887191.492
Kuwait | Inv.4988/Sp/H&J-01 | 4988 | Kuwait4988 | 39217 | 37256.15 | 0 | 37256.15
Ain Sokhna Port Development | IPC#10 - Sokhna Port | 10 | Ain Sokhna Port Development10 | 548720 | 409779.02 | 0 | 512223.77
Ain Sokhna Port Development | IPC#13 - Sokhna Port | 13 | Ain Sokhna Port Development13 | 555579 | 518768.03 | 0 | 518768.03
Faculty of Medicine | mansora finish ipc20 | 20 | Faculty of Medicine20 | 17457823.81 | 13025752 | 2618673.57 | 15644425.57
Faculty of Medicine | mansura finish ipc16 | 16 | Faculty of Medicine16 | 14959073.33 | 11161308 | 2243861 | 13405169
Faculty of Medicine | mansura finish ipc14 | 14 | Faculty of Medicine14 | 7273839.05 | 5426974.862 | 1091075.86 | 6518050.722
Faculty of Medicine | mansora finish ipc 5 | 5 | Faculty of Medicine5 | 4557213.33 | 3399965.3765 | 683582 | 4083547.3765
Faculty of Medicine | mansora finish ipc04 | 4 | Faculty of Medicine4 | 3531509.52 | 2634634.64 | 529726.43 | 3164361.07
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 16 | 16 | Benban 500 K.V / 100 K.M16 | 640951.31 | 494176.02 | 67299.89 | 561475.91
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.06 | 6 | Mostakbal 2 Package No. (8)6 | 22763756.44 | 18074422.61 | 4780388.85 | 22854811.46
Capital One | inv ( 5 ) Captal 1 | 5 | Capital One5 | 2411182.78 | 2387070.949 | 0 | 2387070.949
Ain Sokhna Port Development | IPC#12 - Sokhna port | 12 | Ain Sokhna Port Development12 | 809362 | 604055.74 | 0 | 755069.68
Cairo Monorail - 6th October | IPC#9 Monorail | 9 | Cairo Monorail - 6th October9 | 576000 | 545915 | 0 | 545915
AMRIYA WWTP (3RD STAGE) | 220621001 |  | AMRIYA WWTP (3RD STAGE) | 2816523.26 | 2436825.98 | 281652.33 | 2788358.03
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 7 | 7 | Marsa Alam/ Bernes LOT2 OHTL7 | 11944.76 | 10276.45 | 0 | 10276.45
Ain Sokhna Port Development | IPC#11 Sokhna Port | 11 | Ain Sokhna Port Development11 | 2537830 | 1874852.74 | 0 | 2375288.8
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .21 | 21 | Benban 3/ Toshka 2 LOT 421 | 5065984.71 | 3986536.02 | 531928.4 | 4518464.42
The Open Channel Project | Open chanel1 IPC fin |  | The Open Channel Project | 299730184.76 | 63060050 | 214584480.64 | 277644530.64
Mohamed Ali Palace Restoration | mohamed aly 4 ipc01 | 1 | Mohamed Ali Palace Restoration1 | 62417589.1 | 51394790.0005 | 0 | 51394790.0005
Ora Zed Landscape Ph1 | Ora landscape ipc 17 | 17 | Ora Zed Landscape Ph117 | 1582674.29 | 1313619.66 | 166180.8 | 1479800.46
Ora Zed Landscape Ph1 | Ora landsacape ipc 8 | 8 | Ora Zed Landscape Ph18 | 6274745.71 | 5158038.9355 | 658848.3 | 5816887.2355
Ora Zed Landscape Ph1 | Ora Landscap ipc (5) | 5 | Ora Zed Landscape Ph15 | 3284925.66 | 2898946.893 | 344917.19 | 3243864.083
Ora Zed Landscape Ph1 | Ora landscape ipc3 | 3 | Ora Zed Landscape Ph13 | 2138801.9 | 1887492.675 | 224574.2 | 2112066.875
Beymen Fit Out | PKG#205 IPC02 | 2 | Beymen Fit Out2 | 1935313.99 | 1283209.9395 | 609623.91 | 1892833.8495
EMAAR-Pkg#162/163- Marassi | Emar Pkg#177 ipc(45) | 45 | EMAAR-Pkg#162/163- Marassi45 | 26509803.46 | 16466307.981 | 10800000 | 27266307.981
ORA ZED-Ph 2-Pkgs A&D | ora zed2 ipc06 | 6 | ORA ZED-Ph 2-Pkgs A&D6 | 23225104.47 | 17674903.7 | 2127824.64 | 19802728.34
RING ROAD MARYOTIA EXPANSION | Maryotia IPC011 | 11 | RING ROAD MARYOTIA EXPANSION11 | 29094868.16 | 3708396.57 | 0 | 26708396.57
Sokhna Port Expansion | SOKHNA PORT EX IPC02 | 2 | Sokhna Port Expansion2 | 28451675.04 | 19087604.352 | 5974851.76 | 25062456.112
West Domiatte 500KV TowersZT60 | West Domiatte Inv.01 | 1 | West Domiatte 500KV TowersZT601 | 2452240.2 | 1873789.17 | 0 | 1873789.17
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 08 | 8 | Hosh Essa 220 KV OHTL8 | 1951059.05 | 0 | 204861.2 | 204861.2
Al-Ula Towers | INV ( 5 ) FINAL | 5 | Al-Ula Towers5 | 544770 | 539322.3 | 0 | 545859.54
Ghana Street lighting | MIDA Sply. Inv.1 4 | 1 | Ghana Street lighting1 | 105344.73 | 94747.51 | 0 | 94747.51
Luxor North Axis Bridge-Off | IPC#2-Luxoroffshore | 2 | Luxor North Axis Bridge-Off2 | 2759040 | 2200390.65 | 0 | 2200390.65
TZ – Offshore E&M Procurement | 473 |  | TZ – Offshore E&M Procurement | 496399.75 | 347479.82 | 99279.95 | 446759.77
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $10 | 10 | Benban 3/ Toshka 2 LOT 410 | -125258.82 | -131521.76 | 0 | -131521.76
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 3 | 3 | Marsa Alam/ Bernes LOT2 OHTL3 | 95885.29 | 80543.63 | 10067.96 | 90611.59
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 04 | 4 | Toshka-04 GIS Substation4 | 28562090.56 | 19907383.61 | 2999019.51 | 22906403.12
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .25 | 25 | Benban 3/ Toshka 2 LOT 425 | 10971975.5 | 9786573.09 | 0 | 9786573.09
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .23 | 23 | Benban 3/ Toshka 2 LOT 423 | 6805892.98 | 6070461.77 | 0 | 6070461.77
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .19 | 19 | Benban 3/ Toshka 2 LOT 419 | 4894980.83 | 3337982.9 | 513972.99 | 3851955.89
Benban 500 K.V/95 K.M | Ref-Ret-Benban lot2 |  | Benban 500 K.V/95 K.M | 15330832.04 | 0 | 0 | 15330832.04
LAYYAH CCPP | 501 |  | LAYYAH CCPP | 485125 | 432974.06 | 72768.75 | 505742.81
Infra Project 2524 | 220421006 |  | Infra Project 2524 | 76438931 | 76438931 | 0 | 76438931
EGAT New Rolling Mill 4 | IPC#1 EGAT | 1 | EGAT New Rolling Mill 41 | 1143460 | 823066.73 | 0 | 1028833.41
MDF Factory | MDF factory ipc(28) | 28 | MDF Factory28 | 4537395.02 | 5380287.99 | 1905652.45 | 7285940.44
Ain Sokhna Port Development | IPC#14 - Sokhna Port | 14 | Ain Sokhna Port Development14 | 1234620 | 1123032.9 | 0 | 1153791.13
DPW Onshore Port & Terminal | DPW IPC 35 | 35 | DPW Onshore Port & Terminal35 | 3275655.01 | 83471391.43 | 0 | 83471391.43
Railway Bridge - Assuit | IPC#06 - Assuit | 6 | Railway Bridge - Assuit6 | 2680410 | 2465977.2 | 0 | 2465977.2
EDNC Hardscape Package | Soreal hardscapeipc6 | 6 | EDNC Hardscape Package6 | 2241713.44 | 1939613.522 | 0 | 1939613.522
PLAYA ROOF & Wet Areas | IPC-11-Playa Roof | 11 | PLAYA ROOF & Wet Areas11 | 360191.53 | 308640.34 | 0 | 308640.34
seashell Playa | IPC-12-PLAYA | 12 | seashell Playa12 | 316449.3 | 220913.25 | 50631.89 | 271545.14
Egyptian Exchange building | IPC-6-BORSA | 6 | Egyptian Exchange building6 | 18812.7 | 16658.63 | 0 | 16658.63
EMAAR-Pkg#162/163- Marassi | pkg#177 IPC 28 | 28 | EMAAR-Pkg#162/163- Marassi28 | 4959294.77 | 3923650.8385 | 0 | 3923650.8385
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC020 | 20 | EMAAR-Pkg#162/163- Marassi20 | 10455877.96 | 8109376.158 | 975298.66 | 9084674.818
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC016 | 16 | EMAAR-Pkg#162/163- Marassi16 | 6039477.06 | 3872324.523 | 1044515.19 | 4916839.713
WADY EL-NATROUN BRIDGE(HST) | IPC#1 Wadi ElNatroun | 1 | WADY EL-NATROUN BRIDGE(HST)1 | 659470 | 568724.7 | 0 | 568724.7
Port Said Grain Storage | IPC#2 Port saeid | 2 | Port Said Grain Storage2 | 577500 | 428922.59 | 0 | 512090.25
W Dam PP Phase II (CP-117) | 25 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 565157.2762 | 477890.9595 | 89012.27 | 566903.2295
W Dam PP Phase II (CP-117) | 180158 |  | W Dam PP Phase II (CP-117) | 3803.7 | 3401.19 | 600.21 | 4001.4
Air Defense College | Air defence3 IPC1 | 1 | Air Defense College1 | 13550058.5 | 1311645 | 3700000 | 11343443
Waldorf Astoria Cairo | Waldorf Astoria IPC6 | 6 | Waldorf Astoria Cairo6 | 14843761.8 | 8446327.45 | 2880129.65 | 11326457.1
Air Defense College | Air Defense2 IPC2 | 2 | Air Defense College2 | 33237226.2 | 10422915 | 0 | 28178893
Racecores 3092-17 132KV E | 11770 |  | Racecores 3092-17 132KV E | 11700 | 12285 | 0 | 12285
LINX Tower | inv ( 1 ) LINX | 1 | LINX Tower1 | 2451943.5 | 2304826.875 | 0 | 2321173.1667
SSC Suez Steel Company Project | SUEZ STEEL ABB IPC 1 | 1 | SSC Suez Steel Company Project1 | 5874834 | 5134498.04 | 1504064.38 | 6638562.42
SSC Suez Steel Company Project | inte&retu app ipc 3 | 3 | SSC Suez Steel Company Project3 | 788338.18 | 772824.1852 | 102231.19 | 875055.3752
SSC Suez Steel Company Project | In&Re apply abb ipc6 | 6 | SSC Suez Steel Company Project6 | 878095.32 | 573224.032 | 401460.29 | 974684.322
SSC Suez Steel Company Project | i&r apply (Abb)ipc4 | 4 | SSC Suez Steel Company Project4 | 2495283.55 | 0 | 1140829.76 | 2769764.737
Port Said Port Silos | port said silos ipc6 | 6 | Port Said Port Silos6 | 9017880.28 | 7950568.754 | 901788.03 | 8852356.784
Astoria Sharm elSheikh | astoria sharm IPC2 | 2 | Astoria Sharm elSheikh2 | 401082.65 | 269728 | 105284.2 | 375012.2
EPICO 3 Facility | Eipico ipc 14 | 14 | EPICO 3 Facility14 | 69127444.9 | 36305980.07 | 35009073.56 | 71315053.63
EPICO 3 Facility | Eipico ipc( 7) | 7 | EPICO 3 Facility7 | 7955142.87 | 6395645.73 | 2166091.43 | 8561737.16
WADY EL-NATROUN BRIDGE(HST) | IPC#3 Wadi ElNatroun | 3 | WADY EL-NATROUN BRIDGE(HST)3 | 493185 | 365809.04 | 0 | 407261.3
EDNC Retail & Offices Civil | soreal ipc35 | 35 | EDNC Retail & Offices Civil35 | 46695355.64 | 45515831.938 | 34500000.284 | 90436453.782
Egat Rolling Mill no.4 | Rolling mill ipc07 | 7 | Egat Rolling Mill no.47 | 16796950.48 | 13289718.96 | 4179109.544 | 17468828.504
WADY EL-NATROUN BRIDGE(HST) | IPC#2 Wadi ElNatroun | 2 | WADY EL-NATROUN BRIDGE(HST)2 | 851865 | 733336.11 | 0 | 733336.11
Air Defense College | Air Defence 4 ipc1 | 1 | Air Defense College1 | 36699589.5 | 2794415 | 16200000 | 30756980
Bahr ElBakar – Power Station | IPC#7 Bahr Elbaqar | 7 | Bahr ElBakar – Power Station7 | 597432 | 581392.68 | 0 | 581392.68
El Taameer Axis Expansion | IPC#3 Taamer PII | 3 | El Taameer Axis Expansion3 | 803880 | 776548.08 | 0 | 776548.08
BridgeNasr Rd w Abbas El-Akkad | AbasAlaqad2 IPCFinal |  | BridgeNasr Rd w Abbas El-Akkad | 18721056.27 | 7730640.01 | 9800000 | 17530640.01
CS-20 Mall | inv ( 4:12 ) CS-20 | 4 | CS-20 Mall4 | 64469.93 | 60601.73 | 0 | 60601.73
Kattameya Creeks | katameya IPC19 | 19 | Kattameya Creeks19 | 37484144.91 | 36075433.1155 | 2903017.59 | 38978450.7055
ElSewedy HQ Internal Finishing | elsewedy HQ ipc18 | 18 | ElSewedy HQ Internal Finishing18 | 15535743.72 | 11331892.376 | 10220010 | 23184676.836
Railway Bridge - El Hammam | IPC#6 ElHammam | 6 | Railway Bridge - El Hammam6 | 767288 | 597016.89 | 0 | 597016.89
GOV2 - Infra | GOV2 IPC 11 | 11 | GOV2 - Infra11 | 23184283 | 38068615.4 | 4723524.7 | 42792140.1
seashell Playa | 21 |  | seashell Playa | 711318.54 | 610382.44 | 0 | 610382.44
Ministries Buildings | Minist MEP IPC05 | 5 | Ministries Buildings5 | 47392701.8 | 295005 | 0 | 40779504.61
HST Bridges-Sokhna & Mahager | Elsokhna 4.5 ipc 3+4 | 3 | HST Bridges-Sokhna & Mahager3 | 10960142.86 | 9099910.583 | 0 | 9099910.583
Mivida BP#189 | pkg#189- IPC 5 | 5 | Mivida BP#1895 | 28546026.85 | 29417050.3325 | 3544586.98 | 32961637.3125
Luxor North Axis Bridge-Off | IPC#3 Offshore | 3 | Luxor North Axis Bridge-Off3 | 2121585.6 | 1951150.03 | 0 | 1951150.03
Ain Sokhna Port Development | IPC#20 Sokhna Port | 20 | Ain Sokhna Port Development20 | 1111158 | 833955.58 | 0 | 1042444.47
EDNC Hardscape Package | EDNC HARDESCAPE IPC4 | 4 | EDNC Hardscape Package4 | 1923818.4 | 4301325.99 | 0 | 4301325.99
EDNC Retail & Offices Civil | ednc sodic ipc33 | 33 | EDNC Retail & Offices Civil33 | 15003172.55 | 13807649.9075 | 0 | 13807649.9075
EMAAR-Pkg#162/163- Marassi | PKG#163- IPC26 | 26 | EMAAR-Pkg#162/163- Marassi26 | 6526578.31 | 6335310.4955 | 0 | 6335310.4955
Olympic Multi – Sports Hall | Olympic Finsh IPC3+ | 3 | Olympic Multi – Sports Hall3 | 54667923.35 | -36601001.09 | 83049200 | 46448198.91
Ministries Buildings | min mep ipc 6 | 6 | Ministries Buildings6 | 40277149 | 33933085 | 0 | 33933085
CFC Podium 2 | CFC IPC024 | 24 | CFC Podium 224 | 14455028.51 | 9889480.3655 | 0 | 9889480.3655
Ameria | FPC - Ameria Project |  | Ameria | 120000 | 112800 | 0 | 112800
Egat Rolling Mill no.4 | Rolling mill ipc 04 | 4 | Egat Rolling Mill no.44 | 8075015.79 | 6811267.8195 | 1586748.6 | 8398016.4195
Egat Rolling Mill no.4 | rolling mill- IPC10 | 10 | Egat Rolling Mill no.410 | 19073639.83 | 0 | 0 | 20027321.8215
MDF Factory | MDF FACTORY2 IPC06 | 6 | MDF Factory6 | 660835.92 | 667444.2788 | 0 | 667444.2788
MDF Factory | MDF FACTORY IPC09 | 9 | MDF Factory9 | 6053905.51 | 5166802.9655 | 950994.49 | 6117797.4555
EL -mahager Bridge Ain sokhna | IPC#1 - HST Mahager | 1 | EL -mahager Bridge Ain sokhna1 | 1795000 | 0 | 0 | 1795000
Ain Sokhna Bridge – RME | FPC - Sokhna Bridge |  | Ain Sokhna Bridge – RME | 62525 | 48344.83 | 0 | 61899.75
Mohamed Ali Palace Restoration | mohamed aly3 Ipc2 | 2 | Mohamed Ali Palace Restoration2 | 1900257.14 | 1593935 | 0 | 1593935
Air Defense College | Air def IPC4 | 4 | Air Defense College4 | 2263082 | 1561455 | 0 | 1909712
Waldorf Astoria Cairo | waldorf Astoria IPC9 | 9 | Waldorf Astoria Cairo9 | 16070153.02 | 6286403 | 6421058.51 | 12707461.51
PLAYA ROOF & Wet Areas | IPC014-Playa Roof | 14 | PLAYA ROOF & Wet Areas14 | 105243.51 | 88240.2 | 0 | 88240.2
Port Said Port Silos | port said silos ipc8 | 8 | Port Said Port Silos8 | 22573115.94 | 20033640.397 | 2257311.59 | 22290951.987
WADY EL-NATROUN BRIDGE(HST) | IPC 6 WADIELNATRON | 6 | WADY EL-NATROUN BRIDGE(HST)6 | 269100 | 160767.86 | 0 | 200959.83
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC 20 | 20 | ElSewedy HQ Internal Finishing20 | 43687204.67 | 10136401.93 | 14678900.67 | 31315302.57
New Giza Teaching Hospital | New giza - IPC10 | 10 | New Giza Teaching Hospital10 | 22234302.84 | 16043183.482 | 4106456.49 | 20149639.972
New Giza Teaching Hospital | new giza IPC9 | 9 | New Giza Teaching Hospital9 | 23282485.08 | 16758838.084 | 3068734.89 | 19827572.974
Expansion of Ring Road NRCC | IPC#1 - NRCC | 1 | Expansion of Ring Road NRCC1 | 699000 | 657060 | 0 | 657060
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC16 | 16 | EMAAR-PKG# 101-UPTOWN16 | 181866.48 | 1873125.774 | 57287.94 | 1930413.714
MDF Factory | MDF Local - IPC8 | 8 | MDF Factory8 | 570451.1 | 413577.054 | 162578.56 | 576155.614
Air Defense College | Defense6 IPC1 | 1 | Air Defense College1 | 15431378 | 13555895 | 0 | 13555895
Ministries Buildings | Mini MEP IPC6 | 6 | Ministries Buildings6 | 22769892 | 17664815 | 0 | 17664815
Cairo-Alex Railway | cairo-alex ipc 26 | 26 | Cairo-Alex Railway26 | 32853592.5 | 22794741.105 | 3449627.21 | 26244368.315
MDF Factory | MDF - IPC 16 | 16 | MDF Factory16 | 11688118.01 | 10601848.06 | 3062673.45 | 13664521.51
Air Defense College | Defense5 IPC1 | 1 | Air Defense College1 | 6178705 | 1663625 | 3400000 | 5121298
Creeks URBN-K | Urbnk- ipc 1 | 1 | Creeks URBN-K1 | 10988694.51 | 10729515 | 465817.73 | 11195332.73
EGAT Pelletizing Plant | EGAT IPC06 | 6 | EGAT Pelletizing Plant6 | 11102739.54 | 10274250.077 | 1272599.04 | 11546849.117
Port Said Grain Storage | IPC 5 PORT SAID | 5 | Port Said Grain Storage5 | 1155000 | 722257.8 | 0 | 902822.25
WADY EL-NATROUN BRIDGE(HST) | IPC 8 WADI ELNATRON | 8 | WADY EL-NATROUN BRIDGE(HST)8 | 551985 | 392263.34 | 0 | 454413.58
SSC Suez Steel Company Project | revamp ipc(5) | 5 | SSC Suez Steel Company Project5 | 4135898.1 | 2853769.694 | 1240769.43 | 4094539.124
Port Said Grain Storage | IPC#7 Portsaid | 7 | Port Said Grain Storage7 | 2407900 | 1710478.54 | 0 | 1710478.54
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC09 | 9 | ORA ZED - Ph 01B - Pkgs A&D9 | 27403398.03 | 24054179.0515 | 2858510.2 | 26912689.2515
Royal City | Royal city ipc (42) | 42 | Royal City42 | 10349949.34 | 20407465.3582 | 116680.4388 | 20524145.797
EMAAR-Pkg#162/163- Marassi | pkg#177-IPC37 | 37 | EMAAR-Pkg#162/163- Marassi37 | 3201525.38 | 3131251.909 | 0 | 3131251.909
BKG#178-Lagoon Discharge | PKG#178- IPC 9 | 9 | BKG#178-Lagoon Discharge9 | 31809.53 | 2524652.5565 | 0 | 2524652.5565
EGAT Lock & Load | EGAT L&L-IPC11 | 11 | EGAT Lock & Load11 | 1992889.65 | 1873316.2725 | 199288.96 | 2072605.2325
EGAT Lock & Load | EGAT L&L IPC12 | 12 | EGAT Lock & Load12 | 1778896.47 | 1672162.6835 | 177889.65 | 1850052.3335
Cairo-Alex Railway | Cairo-alex ipc 35 | 35 | Cairo-Alex Railway35 | 3020585.71 | 2097397.78 | 317161.5 | 2414559.28
GOV2 - Infra | Gov2 ipc(12) | 12 | GOV2 - Infra12 | 42288546.24 | 23775725.082 | 3343428.6 | 27119153.682
ORA-ZED Towers P01B | 181022 |  | ORA-ZED Towers P01B | 85537.5 | 75743.46 | 0 | 75743.46
Royal City | Royal centerzone(23) | 23 | Royal City23 | 10826725.43 | 9589993.4272 | 0 | 9589993.4272
Diplomatic District - Infra | Diplomatic ipc12 | 12 | Diplomatic District - Infra12 | 13260789.9 | 18429485.685 | 2322442.3 | 20751927.985
Diplomatic District - Infra | Diplo Dist. IPC05 | 5 | Diplomatic District - Infra5 | 17394365.29 | 35617387.94 | 4410162.68 | 40027550.62
Get Business Complex | INV ( 1 ) GET | 1 | Get Business Complex1 | 716040 | 673077.6 | 0 | 673077.6
Railway Bridge - Assuit | IPC#7 - Assuit | 7 | Railway Bridge - Assuit7 | 1199450 | 1090306.8 | 0 | 1090306.8
Kemet Tower | inv ( 6-7-8 ) kemet | 6 | Kemet Tower6 | 400480 | 52023.46 | 0 | 52023.46
PLAYA ROOF & Wet Areas | IPC#00015 | 15 | PLAYA ROOF & Wet Areas15 | 176307.75 | 0 | 0 | 176307.75
Ring Road El Mansoria | INV (2 ) AL Mansorya | 2 | Ring Road El Mansoria2 | 467280 | 415879.2 | 0 | 415879.2
Ain Sokhna Bridge – RME | IPC#7 - Sokhna Bridg | 7 | Ain Sokhna Bridge – RME7 | 2211015 | 2169565.39 | 0 | 2169565.39
Kattameya Creeks | katameyacreeks-IPC26 | 26 | Kattameya Creeks26 | 73494584.17 | 74263221 | 2140175.7 | 76403396.7
Abou Ghaleb Bridge | ABOGHALEB 6+7+8+9+10 |  | Abou Ghaleb Bridge | 40668563.14 | 724954.0286 | 0 | 22208792.4286
Get Business Complex | INV ( 3 ) GET | 3 | Get Business Complex3 | 531048 | 499185.12 | 0 | 499185.12
Get Business Complex | INV ( 2 ) GET | 2 | Get Business Complex2 | 550800 | 517752 | 0 | 517752
MAF HQ Renovation | carrefour RBS IPC 4 | 4 | MAF HQ Renovation4 | 3030094 | 2037738.2 | 795399.68 | 2833137.88
MAF HQ Renovation | Carrefour RBS IPC(2) | 2 | MAF HQ Renovation2 | 1856061.8 | 1248201.56 | 487216.22 | 1735417.78
U4,U8 Seashell Playa | IPC3 TR60 | 3 | U4,U8 Seashell Playa3 | 85655.1 | 73971.06 | 0 | 73971.06
MDF Factory | MDF FACTORY IPC (26) | 26 | MDF Factory26 | 20422067.95 | 12481160.25 | 5399138.77 | 17880299.02
Ministries Buildings | Min long lead Ipc4 | 4 | Ministries Buildings4 | 9323069 | 7854280 | 0 | 7854280
Cairo Monorail - 6th October | FPC Monorail |  | Cairo Monorail - 6th October | 415000 | 392280 | 0 | 392280
GOV2 - Infra | Gov2 ipc18+19 | 18 | GOV2 - Infra18 | 18621245.71 | 44407465.9255 | 5459594.17 | 49867060.0955
Ain Sokhna Port Development | IPC#18 Sokhna Port | 18 | Ain Sokhna Port Development18 | 1481544 | 1009287.17 | 0 | 1009287.17
Capital One | inv ( 8 ) Captal one | 8 | Capital One8 | 946708.37 | 937241.2885 | 0 | 937241.2885
Katameya Creeks - RME | IPC00000003 | 3 | Katameya Creeks - RME3 | 9219.82 | 8164.15 | 0 | 8164.15
El-Herafeen brigde | IPC#1&2 | 1 | El-Herafeen brigde1 | 1263235 | 1032775.58 | 0 | 1032775.58
WADY EL-NATROUN BRIDGE(HST) | IPC# 12 WADI | 12 | WADY EL-NATROUN BRIDGE(HST)12 | 1119960 | 1017035.68 | 0 | 1017035.68
Air Defense College | Air7 Fin IPC2 | 2 | Air Defense College2 | 18663776 | 14703820 | 0 | 15734139
ORA ZED-Ph 2-Pkgs A&D | ORA Ph.2 - IPC 14 | 14 | ORA ZED-Ph 2-Pkgs A&D14 | 12548033.06 | 15106729.373 | 1911092.27 | 17017821.643
MDF Factory | MDF - IPC 25 | 25 | MDF Factory25 | 10389113.75 | 4423185.2685 | 10664897.85 | 15088083.1185
Hyper One Badr | INV ( 10 ) Hipper | 10 | Hyper One Badr10 | 1090333.7 | 970396.98 | 0 | 970396.98
MDF Factory | MDF - IPC19 | 19 | MDF Factory19 | 12911250.9 | 8856995.725 | 2093318.3 | 10950314.025
MDF Factory | MDF 2 - IPC11 | 11 | MDF Factory11 | 411623.92 | 415740.1688 | 0 | 415740.1688
HST - 6 October - Arab Cont. | IPC#1 HSR ARAB | 1 | HST - 6 October - Arab Cont.1 | 2621800 | 1040770 | 0 | 1040770
Egat Rolling Mill no.4 | rolling mill- IPC11 | 11 | Egat Rolling Mill no.411 | 16145745 | 13154777.42 | 3636797.38 | 16791574.8
Air Defence College | IPC000009 | 9 | Air Defence College9 | 1124369.82 | 954589.98 | 0 | 954589.98
Kattameya Creeks | katameyacreeks-IPC25 | 25 | Kattameya Creeks25 | 45327391.41 | 45191848.31 | 1948638.75 | 47140487.06
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 26 | 26 | ORA ZED - Ph 01B - Pkgs A&D26 | 68520137.14 | 6863669.1846 | 57181187.41 | 64044856.5946
U3 & U5 | IPC2-TR55 | 2 | U3 & U52 | 439984.49 | 375220.61 | 0 | 375220.61
U4,U8 Seashell Playa | IPC007 TR60 | 7 | U4,U8 Seashell Playa7 | 431538.63 | 372676.76 | 0 | 372676.76
Irrigation Tank | IPC001 Tank | 1 | Irrigation Tank1 | 815585.1 | 704339.29 | 0 | 704339.29
EMAAR-Pkg#162/163- Marassi | ipc42 Emar PKG177 | 42 | EMAAR-Pkg#162/163- Marassi42 | 2102245.55 | 4316245.8075 | 1120.74 | 4317366.5475
HSR-6th of October | IPC#7 HSR | 7 | HSR-6th of October7 | 1671344 | 1447805.88 | 0 | 1447805.88
EGAT Mechanical Installations | Egat Mechnical ipc 7 | 7 | EGAT Mechanical Installations7 | 3744476.64 | 2845427.8 | 936119.1704 | 3781546.9704
Business District Hyde Park | INV ( 1 ) HY Bark | 1 | Business District Hyde Park1 | 795000 | 678930 | 0 | 678930
Capital One | inv ( 7 ) Captal one | 7 | Capital One7 | 1168346.98 | 1156663.509 | 0 | 1156663.509
MDF Factory | MDF FACTORY IPC10 | 10 | MDF Factory10 | 7456023.43 | 10970767.5315 | 1032725.89 | 12003493.4215
DP World Basin 2 Ph2 | Dp world ipc 12 | 12 | DP World Basin 2 Ph212 | 54623534 | 40236573.85 | 8155016.63 | 48391590.48
MDF Factory | MDF Factory IPC23 | 23 | MDF Factory23 | 37280017.77 | 14012432.1696 | 19477192.18 | 33489624.3496
EGAT Pelletizing Plant | RO Eriction ipc 1 | 1 | EGAT Pelletizing Plant1 | 6000000 | 6660000 | 0 | 6660000
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 - IPC12 | 12 | ORA ZED-Ph 2-Pkgs A&D12 | 16689354.47 | 15225579.9035 | 1929327.26 | 17154907.1635
Ora Zed Landscape Ph1 | ipc 1 Ora landscape | 1 | Ora Zed Landscape Ph11 | 2611606.83 | 2304743.0232 | 274218.72 | 2578961.7432
DP World Basin 2 Ph2 | ipc 3 | 3 | DP World Basin 2 Ph23 | 38504541.13 | 28493360.4387 | 5775681.17 | 34269041.6087
Sokhna Port Expansion | Spx.2 ipc 07 | 7 | Sokhna Port Expansion7 | 4559269.9 | 2764829.36 | 1154245.58 | 3919074.94
Wady El Natroon Bridge | WADY ELNATRON IPC 01 | 1 | Wady El Natroon Bridge1 | 51983282.43 | 15425224.3757 | 0 | 35854126.5757
Kattameya Creeks | Katamya Creeks ipc30 | 30 | Kattameya Creeks30 | 55298315.11 | 43084120 | 14139199.7 | 57223319.7
Ministries Buildings | Minis Core IPC12 | 12 | Ministries Buildings12 | 13450696 | 11331810 | 0 | 11331810
RING ROAD MARYOTIA EXPANSION | Mryotia - IPC02 | 2 | RING ROAD MARYOTIA EXPANSION2 | 25572365.97 | 12664735.77 | 0 | 12664735.77
RING ROAD MARYOTIA EXPANSION | ElMarg IPC03 | 3 | RING ROAD MARYOTIA EXPANSION3 | 16544270.99 | 14603087.4595 | 0 | 14603087.4595
RING ROAD MARYOTIA EXPANSION | El-Marg IPC05 | 5 | RING ROAD MARYOTIA EXPANSION5 | 2520054.67 | 2231198.92 | 0 | 2231198.92
MDF Factory | Mdf factory ipc 42 | 42 | MDF Factory42 | 19536964.22 | 7602001.04 | 5864798.66 | 13466799.7
Air Defense College | Air Dev sihi IPC1 | 1 | Air Defense College1 | 7144552 | 1203150 | 4752000 | 5955150
Port Said Port Silos | port said silosipc11 | 11 | Port Said Port Silos11 | 5057462.52 | 4473647.986 | 505746.25 | 4979394.236
Get Business Complex | INV ( 5 ) GET | 5 | Get Business Complex5 | 838442.4 | 788135.86 | 0 | 788135.86
ORA-ZED Towers P01B | IPC007 | 7 | ORA-ZED Towers P01B7 | 278338.2 | 246468.48 | 0 | 246468.48
Kattameya Creeks | Katamya Creeks ipc36 | 36 | Kattameya Creeks36 | 64452457.92 | 50530224.78 | 16258366.39 | 66788591.17
EGAT Pelletizing Plant | Admin Building ipc 2 | 2 | EGAT Pelletizing Plant2 | 53673231.5 | 23616221.86 | 32203938.9 | 55820160.76
Air Defence College | IPC00010 | 10 | Air Defence College10 | 738309.8 | 626825.02 | 0 | 626825.02
U4,U8 Seashell Playa | IPC001TR0060 | 1 | U4,U8 Seashell Playa1 | 888790.35 | 767559.34 | 0 | 767559.34
Air Defence College | IPC000007 | 7 | Air Defence College7 | 914159.54 | 776121.45 | 0 | 776121.45
Air Defence College | IPC0000008 | 8 | Air Defence College8 | 37865.02 | 32147.41 | 0 | 32147.41
Abo Shanab El Agamien | abo shanab ipc 3 | 3 | Abo Shanab El Agamien3 | 16847053.46 | 15139736.4 | 4206110.44 | 19345846.84
Abo Shanab El Agamien | ABO SHANAB IPC2 | 2 | Abo Shanab El Agamien2 | 10144780.21 | 20803096.04 | 0 | 20803096.04
ORA ZED-Ph 2-Pkgs A&D | Ora Zed (2) ipc 17 | 17 | ORA ZED-Ph 2-Pkgs A&D17 | 9516947.6 | 8988166.1131 | 1130124 | 10118290.1131
EDNC Hardscape Package | sorealhardscapeIPC12 | 12 | EDNC Hardscape Package12 | 2146120.25 | 2109293.391 | 0 | 2109293.391
Faculty of Medicine | mansora finish ipc09 | 9 | Faculty of Medicine9 | 7118203.18 | 5310846.8319 | 1067730.57 | 6378577.4019
Seashell Playa 5 Villas | Playa c038 - ipc 2 | 2 | Seashell Playa 5 Villas2 | 1451.6 | 1503.85 | 0 | 1503.85
Ministries Buildings | Minis Core IPC13 | 13 | Ministries Buildings13 | 9298463 | 7833550 | 0 | 7833550
EPICO 3 Facility | Eipico - ipc 6 | 6 | EPICO 3 Facility6 | 6910722.77 | 5949568.74 | 2014420.72 | 7963989.46
Air Defence College | IPC0015 TR46 | 15 | Air Defence College15 | 462908.64 | 393009.43 | 0 | 393009.43
Air Defense College | Air Dev Alum IPC1 | 1 | Air Defense College1 | 34615195 | 7139800 | 21800000 | 28939800
East Port Said Industrial Area | FPC Orascom HA JV |  | East Port Said Industrial Area | 336092 | 199065.45 | 0 | 199065.45
Air Defense College | Air Dev finsh IPC1 | 1 | Air Defense College1 | 150765535.8 | 29417950 | 95700000 | 126015484.8
EGAT Mechanical Installations | Egat mech Equip ipc1 | 1 | EGAT Mechanical Installations1 | 4715732.2 | 3583484.902 | 1178933.05 | 4762417.952
Port Said Port Silos | ipc 14 port said | 14 | Port Said Port Silos14 | 2803566.38 | 2480905.1552 | 280356.64 | 2761261.7952
Port Said Port Silos | portsaid silos ipc17 | 17 | Port Said Port Silos17 | 7676679.55 | 6794573.092 | 767667.96 | 7562241.052
El Khatatba Bridge | EL KHATTBA IPC 7+8+9 | 7 | El Khatatba Bridge7 | 60988369.64 | 47315333.8936 | 0 | 54315333.8936
EMAAR-Pkg#162/163- Marassi | Emaar pkg#177 ipc 46 | 46 | EMAAR-Pkg#162/163- Marassi46 | 5007444.76 | 3319156.348 | 1500000 | 4819156.348
Faculty of Medicine | mansora finish ipc10 | 10 | Faculty of Medicine10 | 7295367.62 | 5443038.3238 | 1094305.14 | 6537343.4638
SOL Town PKG.220 | pgk#220 ipc (1) | 1 | SOL Town PKG.2201 | 12159328.08 | 8261597.76 | 2992468.34 | 11254066.1
British International School | bis ipc 4 | 4 | British International School4 | 8650967.52 | 9749342.807 | 2412436.23 | 12161779.037
British International School | BIS IPC 3+ | 3 | British International School3 | 7190987.06 | 1015237.193 | 2849417.81 | 3864655.003
SEASHELL TECHNICAL ROOM | IPC0003TR65 | 3 | SEASHELL TECHNICAL ROOM3 | 122521.28 | 69859.38 | 0 | 69859.38
Wadi Halfa Port | wady halfa esc.1 |  | Wadi Halfa Port | 14802651.3 | 14076920.267 | 0 | 14076920.267
Katameya Creeks - RME | IPC007 TR53 | 7 | Katameya Creeks - RME7 | 177303.61 | 158382.35 | 0 | 158382.35
RING ROAD MARYOTIA EXPANSION | MARIOTYA IPC 17 | 17 | RING ROAD MARYOTIA EXPANSION17 | 6790889.14 | 5287432.8 | 0 | 5287432.8
Cairo-Alex Railway | Cairo-alex ipc 36 | 36 | Cairo-Alex Railway36 | 16514223.81 | 11468729.61 | 1733993.5 | 13202723.11
Cairo-Alex Railway | cairo-alex ipc 27 | 27 | Cairo-Alex Railway27 | 35051897.79 | 24323344.11 | 3680449.27 | 28003793.38
Sixty Iconic Tower | inv ( 2 ) sixty | 2 | Sixty Iconic Tower2 | 1356885 | 1275471.9 | 0 | 1275471.9
Al-Parco | INV ( 4 ) ALparco | 4 | Al-Parco4 | 4279952.5 | 4023155.34 | 0 | 4023155.34
Venice Mall | inv ( 1 ) vensia | 1 | Venice Mall1 | 76160 | 75398.4 | 0 | 75398.4
Olympic Multi – Sports Hall | OLYMPIC FIN-IPC01 | 1 | Olympic Multi – Sports Hall1 | 21103731.73 | 2217431.02 | 0 | 2217431.02
Port Said Port Silos | port said silosipc16 | 16 | Port Said Port Silos16 | 12501707.07 | 11072420.0228 | 1250170.71 | 12322590.7328
EGAT Lock & Load | EGAT L&L IPC7 | 7 | EGAT Lock & Load7 | 1415984.07 | 1331025.0235 | 141598.41 | 1472623.4335
MDF Factory | mdf factory ipc 33 | 33 | MDF Factory33 | 18965945.93 | 10638561.7072 | 7963981.26 | 18602542.9672
Creeks URBN-K | KatamUrbnk ipc ( 2) | 2 | Creeks URBN-K2 | 19977718.2 | 3863139 | 16088291.57 | 19951430.57
Faculty of Medicine | mansora finish ipc11 | 11 | Faculty of Medicine11 | 4515174.29 | 3368595.1616 | 677277 | 4045872.1616
Faculty of Medicine | mansora finish ipc12 | 12 | Faculty of Medicine12 | 7819043.81 | 5833780.5619 | 1172856.57 | 7006637.1319
Sokhna Port Expansion | esc.1:10 spx1 |  | Sokhna Port Expansion | 34853225.9 | 20947176.6 | 0 | 30947176.6
New Giza Teaching Hospital | New Giza ipc ( 18) | 18 | New Giza Teaching Hospital18 | 24967998.04 | 15759862.1875 | 1871545.2245 | 17631407.412
Sokhna Port Expansion | sokhna port ex ipc14 | 14 | Sokhna Port Expansion14 | 16895917.4 | 6704080.85 | 3379183.48 | 15083264.33
Tarek Abdel-Hakim Center | TAH ipc 10 | 10 | Tarek Abdel-Hakim Center10 | 7158353.14 | 5508352.73 | 644251.78 | 6152604.51
Tarek Abdel-Hakim Center | TAH ipc 6 | 6 | Tarek Abdel-Hakim Center6 | 1234570.04 | 950001.64 | 111111.3 | 1061112.94
Tarek Abdel-Hakim Center | TAH ipc02 | 2 | Tarek Abdel-Hakim Center2 | 2619891.03 | 2016006.15 | 235790.19 | 2251796.34
HST - 6 October - Arab Cont. | IPC 2 HSR ARAB | 2 | HST - 6 October - Arab Cont.2 | 2062300 | 1769659.63 | 0 | 1769659.63
Air Defence College | TR46-IPC1FEB | 1 | Air Defence College1 | 900680 | 764677.32 | 0 | 764677.32
Sokhna Port Expansion | sokhna port ex ipc15 | 15 | Sokhna Port Expansion15 | 14245622.5 | 4368115.65 | 2849124.5 | 12217240.15
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 18 | 18 | ORA ZED-Ph 2-Pkgs A&D18 | 15364644.61 | 13333027.7475 | 1686708.33 | 15019736.0775
SSC Suez Steel Company Project | R.O IPC (2) | 2 | SSC Suez Steel Company Project2 | 1543124.26 | 0 | 526359.69 | 1712867.9264
Monoril | inv ( 2 ) monoril | 2 | Monoril2 | 2472386.9 | 462097.56 | 0 | 462097.56
Seashell Playa 5 Villas | Playa -c038 ipc 6 | 6 | Seashell Playa 5 Villas6 | 96357.37 | 27877.46 | 0 | 27877.46
Egat Rolling Mill no.4 | Rolling Mill ipc 14 | 14 | Egat Rolling Mill no.414 | 433210006.09 | 385850769.7576 | 64687636.576 | 450538406.3336
ora zed orascom | IPC03TR0069 | 3 | ora zed orascom3 | 1066558.05 | 975100.71 | 0 | 975100.71
ora zed orascom | IPC 001 TR0069 | 1 | ora zed orascom1 | 129308.62 | 73676.72 | 0 | 73676.72
ora zed orascom | IPC02TR0069 | 2 | ora zed orascom2 | 409594.56 | 374471.822 | 0 | 374471.822
Olympic Multi – Sports Hall | Olympic Elec IPC1 | 1 | Olympic Multi – Sports Hall1 | 30233454 | 4864900 | 20394000 | 25258900
Cairo-Alex Railway | Escalation ipc 29:39 | 29 | Cairo-Alex Railway29 | 40207347.22 | 32145375.561 | 0 | 32145375.561
KATAMYA GREEKS LAND SCAPE STAR | IPC01TR0081 | 1 | KATAMYA GREEKS LAND SCAPE STAR1 | 10196792 | 10080548.3125 | 0 | 10080548.3125
Beni Suef Substation R61 | 1 final bani suef |  | Beni Suef Substation R61 | 3726195.81 | 3608397.35 | 0 | 3608397.35
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 23 | 23 | ORA ZED-Ph 2-Pkgs A&D23 | 1051680.08 | 534269.994 | 67588.37 | 601858.364
New Giza Teaching Hospital | New Giza Hos ipc 24 | 24 | New Giza Teaching Hospital24 | 29604524.13 | 4494905.8665 | 15934743.3 | 21429649.1665
VILLA CLUSTER C | IPC2&3TR0078 | 2 | VILLA CLUSTER C2 | 149742 | 129317.19 | 0 | 129317.19
VILLA CLUSTER C | IPC01TR0078 | 1 | VILLA CLUSTER C1 | 182595 | 83789.04 | 0 | 83789.04
VILLA CLUSTRER B | IPC05TR0077 | 5 | VILLA CLUSTRER B5 | 76986 | 66485.11 | 0 | 66485.11
U3 & U5 | IPC14TR0055 | 14 | U3 & U514 | 67890.85 | 58630.54 | 0 | 58630.54
Mohamed Ali Palace Restoration | Mohamed Ali IPC02 | 2 | Mohamed Ali Palace Restoration2 | 2130706.9 | 1115219.3 | 891500 | 2006719.3
New Giza Teaching Hospital | new giza IPC8 | 8 | New Giza Teaching Hospital8 | 18146654.72 | 12772392.376 | 1948641.22 | 14721033.596
New Giza Teaching Hospital | new giza- IPC12 | 12 | New Giza Teaching Hospital12 | 30417445.78 | 22544712.249 | 3413984.84 | 25958697.089
Jawhara Palace Restoratio | Gawhara IPC7 | 7 | Jawhara Palace Restoratio7 | 805468.71 | 430073.04 | 201367.18 | 631440.22
Faculty of Medicine | mansora finish ipc15 | 15 | Faculty of Medicine15 | 18818900.95 | 14041319.478 | 2822835.15 | 16864154.628
Blue Planet Sharm. | IPC01TR0082 | 1 | Blue Planet Sharm.1 | 3067328.84 | 2772865.27 | 0 | 2772865.27
EGAT Pelletizing Plant | Egat Peletizing ip20 |  | EGAT Pelletizing Plant | 288087581.53 | 284426280.451 | 15202204.3355 | 299628484.7865
EGAT Mechanical Installations | Egat Mech Equip ipc3 | 3 | EGAT Mechanical Installations3 | 37089317.7 | 28184172.5069 | 9272329.43 | 37456501.9369
U6T11 PART1 Palay | IPC03TR0075 | 3 | U6T11 PART1 Palay3 | 11605 | 10602.33 | 0 | 10602.33
New Giza Teaching Hospital | New Giza Hosp ipc15 | 15 | New Giza Teaching Hospital15 | 22076508.27 | 8639287.3435 | 9433643.48 | 18072930.8235
New Giza Hos | IPC01TR0073 | 1 | New Giza Hos1 | 37026.08 | 31772.1 | 0 | 31772.1
EGAT Injection | IPC11TR0048 | 11 | EGAT Injection11 | 62266.05 | 53430.5 | 0 | 53430.5
Ain Sokhna Bridge | Inv ( 3 ) A.S | 3 | Ain Sokhna Bridge3 | 999373.19 | 829854.43 | 0 | 829854.43
HST Bridges-Sokhna & Mahager | sokhna ipc11+12+13 | 11 | HST Bridges-Sokhna & Mahager11 | 88535946.43 | 8673315.8657 | 0 | 69212368.9657
Faculty of Medicine | mansora finish ipc13 | 13 | Faculty of Medicine13 | 10289196.19 | 7676883.0381 | 1543379.43 | 9220262.4681
Faculty of Medicine | Mansoura UNI IPC07 | 7 | Faculty of Medicine7 | 20048289.52 | 16967969.04 | 1002414.48 | 17970383.52
GOV2 - Infra | GOV2 IPC13+14 | 13 | GOV2 - Infra13 | 59475220.33 | 26834651.1805 | 3939718.2 | 30774369.3805
NUCA R05 - Z02 | R05(2) ipc 29+30 | 29 | NUCA R05 - Z0229 | 43098025.9 | 32757037.12 | 4145164.9 | 36902202.02
EIPICO Factory | IPC04 TR0054 | 4 | EIPICO Factory4 | 13401.6 | 11499.91 | 0 | 11499.91
Seashell Playa 5 Villas | playa-c045 ipc 6 | 6 | Seashell Playa 5 Villas6 | 16932.79 | 13000.86 | 0 | 13000.86
U7-SEASHELL | IPC11TR0064 | 11 | U7-SEASHELL11 | 318171.36 | 274084.83 | 0 | 274084.83
Astoria Sharm elSheikh | Woldorf sharm ipc 6 | 6 | Astoria Sharm elSheikh6 | 172304.78 | 621397.339 | 0 | 621397.339
New Giza Teaching Hospital | New Giza ipc (21) | 21 | New Giza Teaching Hospital21 | 12130160.82 | 4614812.92 | 1724826.24 | 10339639.16
Ain Sokhna Port Development | IPC26 elsokhna | 26 | Ain Sokhna Port Development26 | 587716 | 143440 | 0 | 143440
DP World Basin 2 Ph2 | Dp world PH2 ipc (9) | 9 | DP World Basin 2 Ph29 | 27736619.9 | 20524928.94 | 4160492.98 | 24685421.92
Qasr Rashwan - Lot B | QASRRASHWANLOT BIPC2 | 2 | Qasr Rashwan - Lot B2 | 47683707.83 | 39817532 | 11146475.84 | 50964007.84
Seashell Playa 5 Villas | Playa c038 ipc 8 | 8 | Seashell Playa 5 Villas8 | 75415.45 | 56128.78 | 0 | 56128.78
seashell Playa | IPC29TR0038 | 29 | seashell Playa29 | 93920 | 43642.75 | 0 | 43642.75
NUCA R05 - Z02 | R05(2) ipc 33 | 33 | NUCA R05 - Z0233 | 20759999.65 | 14925414.0035 | 1906629.1 | 16832043.1035
ORA-ZED Towers P01B | IPC13 TR51 | 13 | ORA-ZED Towers P01B13 | 45403 | 40204.36 | 0 | 40204.36
EIPICO C002-23 | IPC04TR0068 | 4 | EIPICO C002-234 | 24832 | 21308.34 | 0 | 21308.34
MDF Factory | ipc 15- MDF Local | 15 | MDF Factory15 | 5402784.59 | 2970230 | 2486382.36 | 5456612.36
Central Capital | INV ( 2 ) Central Ca | 2 | Central Capital2 | 162792 | 153024.48 | 0 | 153024.48
SSC Suez Steel Company Project | Revamp 2 SMP2- IPC 1 | 1 | SSC Suez Steel Company Project1 | 38822768.95 | 20964295.228 | 19411384.48 | 40375679.708
DP World Basin 2 Ph2 | Dp world ipc (4) | 4 | DP World Basin 2 Ph24 | 37025201.2 | 27398648.888 | 5553780.18 | 32952429.068
Mivida BP#189 | Emaar pkg#189 ipc 18 | 18 | Mivida BP#18918 | 18563752.6 | 20024965.62 | 2557410.37 | 22582375.99
Al Montaza Hotels - Alexandria | inv ( 5 ) Montazha | 5 | Al Montaza Hotels - Alexandria5 | 830679.3 | 826579.297 | 0 | 826579.297
ZED Phase 2 | IPC04TR0062 | 4 | ZED Phase 24 | 9698.943 | 8239.25 | 0 | 8239.25
Luxor North Axis Bridge | IPC final HA luxor o |  | Luxor North Axis Bridge | 1134519 | 759721.91 | 0 | 759721.91
ACWA POWER & NOMAC HQ | Acwa Power ipc 1. | 1 | ACWA POWER & NOMAC HQ1 | 85714.29 | 90000 | 0 | 90000
Mivida BP#189 | Emaar Pkg#189 ipc22 | 22 | Mivida BP#18922 | 23140993.33 | 17552608.8365 | 11648218.95 | 29200827.7865
Ora Zed Landscape Ph1 | ora landscape ipc 12 | 12 | Ora Zed Landscape Ph112 | 7506327.07 | 6030251.47 | 788164.34 | 6818415.81
EGAT Injection | IPC12TR0048 | 12 | EGAT Injection12 | 421941.77 | 362068.23 | 0 | 362068.23
R05 (New) | IPC06TR0059 | 6 | R05 (New)6 | 149869 | 127103.9 | 0 | 127103.9
Air Defence College | IPC20TR0046 | 20 | Air Defence College20 | 116192.22 | 98647.2 | 0 | 98647.2
Egyptian Exchange building | IPC12&13 TR39 | 12 | Egyptian Exchange building12 | 47993.87 | 41868.58 | 0 | 41868.58
Waldorf Astoria Cairo | Woldorf Astor ipc 22 | 22 | Waldorf Astoria Cairo22 | 10800888.32 | 1999998.286 | 0 | 9327545.216
EL Baragil Bridge | inv ( 3 ) Baragill B | 3 | EL Baragil Bridge3 | 4166890 | 3916876.6 | 0 | 3916876.6
RADAMIS CITY | IPC01TR0084 | 1 | RADAMIS CITY1 | 375875.1 | 332837.39 | 0 | 332837.39
Mivida BP#189 | pkg#189-IPC 7 | 7 | Mivida BP#1897 | 49447555.48 | 41131640.064 | 4934794.35 | 46066434.414
Air Defense College | Air Dev Elec IPC3 | 3 | Air Defense College3 | 17021156 | 14339910 | 0 | 14339910
Port Said Port Silos | PORT SAID IPC 22 | 22 | Port Said Port Silos22 | 6713332.67 | 5651416.0035 | 671333.27 | 6322749.2735
ORA-ZED Towers P01B | IPC14TR0051 | 14 | ORA-ZED Towers P01B14 | 338998.03 | 300182.76 | 0 | 300182.76
Haramein Columns Transfer | Harmain ipc01 | 1 | Haramein Columns Transfer1 | 672000 | 384000 | 576000 | 672000
Seashell Playa 5 Villas | playa-c038 ipc 10 | 10 | Seashell Playa 5 Villas10 | 98071.67 | 84694.55 | 0 | 84694.55
Tarek AbdelHakim Center - KSA | K0001,2 |  | Tarek AbdelHakim Center - KSA | 8530625.81 | 0 | 0 | 8829197.72
Seashell Playa 5 Villas | Playa C045- IPC 8 | 8 | Seashell Playa 5 Villas8 | 89569.81 | 10805.81 | 0 | 10805.81
ZED Phase 2 | IPC06TR0062 | 6 | ZED Phase 26 | 71183.98 | 60470.63 | 0 | 60470.63
Beymen Fit Out | Emaar pkg#205 ipc7 | 7 | Beymen Fit Out7 | 13811986.27 | 6631409.93 | 6182724.5 | 12814134.43
Jawhara Palace Restoratio | Gawhara IPC2 | 2 | Jawhara Palace Restoratio2 | 2251351 | 1511775.91 | 562837.75 | 2074613.66
PLAYA Main Gate | IPC01TR0092 | 1 | PLAYA Main Gate1 | 155883 | 134620.56 | 0 | 134620.56
ACWA POWER & NOMAC HQ | Acwa power ipc 2 | 2 | ACWA POWER & NOMAC HQ2 | 185714.29 | 194459.5267 | 0 | 194594.6461
Diplomatic District - Infra | diplo ipc 16:25 | 16 | Diplomatic District - Infra16 | 212015193.47 | 155990435.38 | 6227631.11 | 162218066.49
HST Bridges-Sokhna & Mahager | sokhna bri esc.17+18 |  | HST Bridges-Sokhna & Mahager | 22048150.62 | 19657734.21 | 0 | 19657734.21
EIPICO Factory | IPC005TR0054 | 5 | EIPICO Factory5 | 24663.69 | 18504.54 | 0 | 6168.18
The Open Channel Project | Open chanel2 IPC1 | 1 | The Open Channel Project1 | 227652446.67 | 81660860 | 104857050.55 | 186517910.55
Irrigation Tank | IPC07TR0061 | 7 | Irrigation Tank7 | 161702.49 | 139646.29 | 0 | 139646.29
EMAAR-Pkg#162/163- Marassi | Emaar pkg#163 ipc 32 | 32 | EMAAR-Pkg#162/163- Marassi32 | 5753296.59 | 4821275.6 | 0 | 4821275.6
DP World Basin 2 Ph2 | Dp World ipc 13 | 13 | DP World Basin 2 Ph213 | 17615925.7 | 15678173.87 | 0 | 15678173.87
MAF HQ Renovation | carrefour RBS IPC 5 | 5 | MAF HQ Renovation5 | 799314.48 | 537538.96 | 209820.05 | 747359.01
Open Channal | IPC05TR0074 | 5 | Open Channal5 | 206751.68 | 178344 | 0 | 178344
Air Defence College | IPC23TR0046 | 23 | Air Defence College23 | 38601.9 | 32773 | 0 | 32773
RADAMIS CITY | IPC02TR0084 | 2 | RADAMIS CITY2 | 36031.95 | 31906.29 | 0 | 31906.29
MDF Factory | mdf local -ipc 18 | 18 | MDF Factory18 | 4222095.24 | 4264311.8578 | 0 | 4264311.8578
Port Said Grain Storage | Rent-001 | 1 | Port Said Grain Storage1 | 81050 | 89600.77 | 0 | 89600.77
Koumassi Flyover | INV 5 | 5 | Koumassi Flyover5 | 144227401 | 129804661 | 0 | 129804661
EPICO 3 Facility | EIPICO ipc 16 | 16 | EPICO 3 Facility16 | 54812520.18 | 26363887.4 | 26509463.43 | 52873350.83
Main Spine | IPC02TR0096 | 2 | Main Spine2 | 279278.12 | 220284.88 | 0 | 220284.88
NUCA R05 - Z02 | R05 2 IPC38 | 38 | NUCA R05 - Z0238 | 12550873.3 | 9307818.385 | 1244727.98 | 10552546.365
Senator | Inv ( 1 ) Sentor | 1 | Senator1 | 630091 | 0 | 0 | 0
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 30+31 | 30 | ORA ZED-Ph 2-Pkgs A&D30 | 10058718.7 | 3791012.07 | 625067.79 | 4416079.86
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 38 | 38 | ORA ZED - Ph 01B - Pkgs A&D38 | 19627458.83 | 17627053.17 | 514793.83 | 18141847
NUCA R05 - Z02 | R05(2) ipc 43 | 43 | NUCA R05 - Z0243 | 16120059.71 | 10598999.12 | 1480670.8 | 12079669.92
Wadi Halfa Port | WADY HALFA IPC05 | 5 | Wadi Halfa Port5 | 5072099.52 | 2984537.1 | 1065140.9 | 4049678
Koumassi Flyover | INV no7 | 7 | Koumassi Flyover7 | 209390747.91 | 591705701.61 | 0 | 197235233.87
EGAT Pelletizing Plant | RO2 ipc 2 | 2 | EGAT Pelletizing Plant2 | 1807831.25 | 1880144.5 | 0 | 1880144.5
Luxor North Axis Bridge-Off | IPC#4 Offshore | 4 | Luxor North Axis Bridge-Off4 | 1618800 | 1473781 | 0 | 1473781
Luxor North Axis Bridge-Off | IPC 5 luxoroff | 5 | Luxor North Axis Bridge-Off5 | 60574 | 47824 | 0 | 47824
EGAT Lock & Load | Egat Lock&Load ipc15 | 15 | EGAT Lock & Load15 | 19312258.25 | 18153522.75 | 1931225.83 | 20084748.58
DP World Basin 2 Ph2 | Dp World ipc 14 | 14 | DP World Basin 2 Ph214 | 21130152.28 | 18805485.48 | 0 | 18805485.48
Al Alamein Marina Towers | IPC#1 Marina Towers | 1 | Al Alamein Marina Towers1 | 2174997.85 | 1868125.47 | 0 | 1868125.47
Mivida BP#189 | PKG#189 IPC 24 | 24 | Mivida BP#18924 | 16112816.1 | 13803484.915 | 11685453.37 | 25488938.285
SSC Suez Steel Company Project | NEW Gas station ipc4 | 4 | SSC Suez Steel Company Project4 | 6707619.99 | 4628257.7896 | 2012286 | 6640543.7896
MDF Factory | MDf Equip -ipc 22 | 22 | MDF Factory22 | 203073.94 | 205104.6816 | 0 | 205104.6816
MDF Factory | MDF Factory ipc 37 | 37 | MDF Factory37 | 18482561.46 | 4465149.39 | 7763808.28 | 12228957.67
Seashell Playa 5 Villas | Playa c469 - ipc 1 | 1 | Seashell Playa 5 Villas1 | 345870 | 315986.83 | 0 | 315986.83
HSR | inv.1 HSR-oct2-5-24 | 1 | HSR1 | 81800571.89 | 0 | 99375886.24 | 99375886.24
Al-Parco | INV ( 8 ) ALparco | 8 | Al-Parco8 | 2102406 | 860732.04 | 0 | 860732.04
Al-Parco | INV ( 6 ) ALparco | 6 | Al-Parco6 | 1433390 | 1347386.6 | 0 | 1347386.6
EIPICO C002-23 | IPC07TR0068 | 7 | EIPICO C002-237 | 81334.5 | 69793.11 | 0 | 69793.11
Olympic MultiSport Hall | IPC04TR0079 | 4 | Olympic MultiSport Hall4 | 88250.4 | 74262.71 | 0 | 74262.71
Koumassi Flyover | INV no8 | 8 | Koumassi Flyover8 | 118967977.65 | 107071179.89 | 0 | 107071179.89
Irrigation Tank | IPC10TR0061 | 10 | Irrigation Tank10 | 188224.4 | 162550.59 | 0 | 162550.59
Sokhna Port Expansion | sokhna port ex 17+18 |  | Sokhna Port Expansion | 42026380.1 | 28702779.44 | 8825539.85 | 37528319.29
RING ROAD MARYOTIA EXPANSION | Escalation13:19. |  | RING ROAD MARYOTIA EXPANSION | 34267873.67 | 30336910.98 | 0 | 30336910.98
RING ROAD MARYOTIA EXPANSION | elmarg 11 final |  | RING ROAD MARYOTIA EXPANSION | 1786099.76 | 8888501.068 | 0 | 8888501.068
HST Bridges-Sokhna & Mahager | SOKHNABRI.IPC21FINAL | 21 | HST Bridges-Sokhna & Mahager21 | 6514011.29 | 4685138 | 0 | 4685138
Sokhna Port Expansion | spx.2 ipc 4 | 4 | Sokhna Port Expansion4 | 12041549 | 8297916.02 | 2408310 | 10706226.02
RING ROAD MARYOTIA EXPANSION | Mariotya ipc20+21+22 | 20 | RING ROAD MARYOTIA EXPANSION20 | 13407964 | 8461342.16 | 0 | 11701263.16
RING ROAD MARYOTIA EXPANSION | Mariotya Rem.esc1:22 |  | RING ROAD MARYOTIA EXPANSION | 24626471.33 | 23788774.43 | 0 | 23788774.43
Abou Ghaleb Bridge | Abo ghaleb ipc 11:18 | 11 | Abou Ghaleb Bridge11 | 39992967.52 | 24492789.55 | 0 | 35492789.55
RING ROAD MARYOTIA EXPANSION | mariotya ipc15 | 15 | RING ROAD MARYOTIA EXPANSION15 | 29097528.02 | 11321780.291 | 0 | 27321780.291
Luxor North Axis Bridge | IPC#1-Luxor onshore | 1 | Luxor North Axis Bridge1 | 1162500 | 1069500 | 0 | 1069500
MDF Factory | MDF Equip ipc 25 | 25 | MDF Factory25 | 631230.84 | 637190.72 | 0 | 637190.72
Faculty of Medicine | IPC23FINISH MANSOURA | 23 | Faculty of Medicine23 | 15044995.24 | 11225320 | 2256749.29 | 13482069.29
Ring Road - Service Road | SERVICE ROAD IPC 1 | 1 | Ring Road - Service Road1 | 42094949.9 | 16760404.48 | 0 | 36760404.48
Roubiky Hassan Allam | IPC#1#Roubiky | 1 | Roubiky Hassan Allam1 | 377625 | 328533.75 | 0 | 328533.75
NUCA R05 - Z02 | RO5(2) IPC 50 | 50 | NUCA R05 - Z0250 | 24169557.35 | 11116977.38 | 1661467.3 | 12778444.68
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 39 | 39 | ORA ZED - Ph 01B - Pkgs A&D39 | 9971577.14 | 7606231.63 | 0 | 7606231.63
EIPICO C002-23 | IPC09TR0068 | 9 | EIPICO C002-239 | 72112.1 | 61879.39 | 0 | 61879.39
BISC New Society Bldg | Society Build ipc1 | 1 | BISC New Society Bldg1 | 2946690.48 | 1732655 | 928207 | 2660862
Wadi Halfa Port | wady halfa claim |  | Wadi Halfa Port | 8796238.1 | 8364831 | 0 | 8364831
Roubiky Hassan Allam | IPC#3#Roubiky | 3 | Roubiky Hassan Allam3 | 527250 | 439726.5 | 0 | 439726.5
ORA ZED-Ph 2-Pkgs A&D | Ora Ph2 ipc 37+38 | 37 | ORA ZED-Ph 2-Pkgs A&D37 | 12751303.62 | 12413453.42 | 2944618.73 | 15358072.15
Roubiky Hassan Allam | IPC#2#Roubiky | 2 | Roubiky Hassan Allam2 | 377625 | 315782.25 | 0 | 315782.25
Cairo Monorail - 6th October | IPC#3 - Monorail | 3 | Cairo Monorail - 6th October3 | 913500 | 559140 | 0 | 559140
Cairo Monorail - 6th October | IPC#6 - Monorai | 6 | Cairo Monorail - 6th October6 | 927500 | 918225 | 0 | 918225
Rabigh CCPP-Civil | Inv-02 Civil | 2 | Rabigh CCPP-Civil2 | 4110954.32 | 14182792.41 | 0 | 4727597.47
El Taameer Axis Expansion | IPC#2 Taamer PII | 2 | El Taameer Axis Expansion2 | 832590 | 804281.94 | 0 | 804281.94
Open Channel 2 | IPC01TR0099 | 1 | Open Channel 21 | 1537200 | 1306921.67 | 0 | 1306921.67
Wady El Natroon Bridge | WADYELNATRONIPC11+12 | 11 | Wady El Natroon Bridge11 | 11132010.48 | 9924903.8 | 0 | 9924903.8
HSR | Inv 2 HSR | 2 | HSR2 | 140860565.14 | 0 | 99501314.727 | 99501314.727
Cairo-Alex Railway | CAIRO-ALEX IPC19 | 19 | Cairo-Alex Railway19 | 8739158.4 | 6068946.64 | 917611.63 | 6986558.27
Sultana Malak Restoration | Sultana Ma Zer Final |  | Sultana Malak Restoration | 1063414.29 | 1042010 | 0 | 1042010
RADAMIS CITY | IPC05TR0084 | 5 | RADAMIS CITY5 | 174292.23 | 154335.77 | 0 | 154335.77
EIPICO Factory | IPC07TR0054 | 7 | EIPICO Factory7 | 42358 | 56197.4 | 0 | 56197.4
U7-SEASHELL | IPC22TR0064 | 22 | U7-SEASHELL22 | 143143.85 | 123619.03 | 0 | 123619.03
Port Said Port Silos | supply egp ipc8 | 8 | Port Said Port Silos8 | 2594878.44 | 8973244.2 | 1297439.2 | 2054136.68
Port Said Port Silos | IPC 5 SUPPLY PORT SA | 5 | Port Said Port Silos5 | 3279001.016 | 10264739.1548 | 1311483.72 | 2894055.7187
New Giza Teaching Hospital | New Giza ipc 28 | 28 | New Giza Teaching Hospital28 | 12973500.18 | 5534314 | 497979.91 | 6429944.91
EIPICO C002-23 | IPC12TR0068 | 12 | EIPICO C002-2312 | 228534.45 | 196105.42 | 0 | 196105.42
Coastal road Bridge Extension | IPC007 - Gharably | 7 | Coastal road Bridge Extension7 | 674730 | 649764.99 | 0 | 649764.99
SSC Suez Steel Company Project | Revamp ipc 10 | 10 | SSC Suez Steel Company Project10 | 5011477.79 | 1348297.2816 | 1503443.34 | 4864487.3216
Ring Road - Service Road | SERVICE ROAD IPC 2 | 2 | Ring Road - Service Road2 | 9399923.14 | 8307635.02 | 0 | 8307635.02
Sokhna Port Expansion | SPX.2 ESC 1:7 |  | Sokhna Port Expansion | 20628970 | 18242626.1738 | 0 | 18242626.1738
KATAMYA GREEKS LAND SCAPE STAR | IPC03TR0081(1) | 3 | KATAMYA GREEKS LAND SCAPE STAR3 | 1207954.22 | 1194183.541 | 0 | 1194183.541
Port Said Port Silos | PORT SAID IPC 29 | 29 | Port Said Port Silos29 | 2107663.51 | 596055.2424 | 210766.35 | 806821.5924
Air Defense College | air dev finish ipc1 | 1 | Air Defense College1 | 47270869 | 31773530 | 0 | 39610730
Red Sea Museum-Bab El-Bunt | Inv-02 RS | 2 | Red Sea Museum-Bab El-Bunt2 | 1838915.59 | 6344258.76 | 0 | 2114752.92
Olympic MultiSport Hall | IPC07TR0079 | 7 | Olympic MultiSport Hall7 | 25709.6 | 21634.63 | 0 | 21634.63
Open Chanel Epoxy | IPC02TR0101 | 2 | Open Chanel Epoxy2 | 2210880 | 1771381 | 0 | 1771381
EGAT ADMIN (Pelletizing) | IPC02TR0094 | 2 | EGAT ADMIN (Pelletizing)2 | 102715.8 | 88140.43 | 0 | 88140.43
Katameya Creeks - RME | IPC19TR0053 | 19 | Katameya Creeks - RME19 | 152389.58 | 134940.97 | 0 | 134940.97
Katameya Creeks - RME | IPC23TR0053 | 23 | Katameya Creeks - RME23 | 183424.69 | 162422.57 | 0 | 162422.57
MDF Factory - Sadat | IPC02TR0093 | 2 | MDF Factory - Sadat2 | 138106.8 | 118509.44 | 0 | 118509.44
October Under-Railway Tunnel | OCTOBER TUNNELIPC10 | 10 | October Under-Railway Tunnel10 | 5992741.71 | 5395295.85 | 0 | 5395295.85
Ahl Misr P3 – Zamalek Sector | IPC#5 | 5 | Ahl Misr P3 – Zamalek Sector5 | 469800 | 54620.37 | 0 | 54620.37
Creeks URBN-K | Katamya Urbnk ipc 3 | 3 | Creeks URBN-K3 | 40661954.89 | 0 | 40274438.44 | 40274438.44
Seashell Playa 5 Villas | Playa C-469 ipc 5 | 5 | Seashell Playa 5 Villas5 | 19567.53 | 17876.89 | 0 | 17876.89
Seashell Playa 5 Villas | Playa c469 ipc 6 | 6 | Seashell Playa 5 Villas6 | 35218.72 | 32175.82 | 0 | 32175.82
Port Said Port Silos | PORT SAID SUP. 10 |  | Port Said Port Silos | 546312.2 | 1501265.934 | 163893.66 | 555053.198
HSR | HSR-OCT4 |  | HSR | 53545345.27 | 0 | 33769924.9835 | 33769924.9835
ORA-ZED Towers P01B | IPC16TR0051 | 16 | ORA-ZED Towers P01B16 | 1104877.42 | 803370.14 | 0 | 803370.14
EIPICO C002-23 | IPC14TR0068 | 14 | EIPICO C002-2314 | 212340.9 | 182209.72 | 0 | 182209.72
Pushing Tunnel | Inv ( 3 ) T. Pushing | 3 | Pushing Tunnel3 | 2712250 | 2191769.35 | 0 | 2191769.35
Ahl Misr P3 – Zamalek Sector | IPC#4 Ahl Misr Zamal | 4 | Ahl Misr P3 – Zamalek Sector4 | 430650 | 43065 | 0 | 43065
Seashell Playa 5 Villas | Playa C469 ipc 10 | 10 | Seashell Playa 5 Villas10 | 31559.6 | 28832.84 | 0 | 28832.84
Kafr Shokr Bridge | Kafr Shokr 11 final |  | Kafr Shokr Bridge | 5393674.1 | 9511261.9 | 0 | 9511261.9
Cairo Monorail - 6th October | IPC#7` | 7 | Cairo Monorail - 6th October7 | 1281000 | 1268190 | 0 | 1268190
Open Channal | IPC1TR74 | 1 | Open Channal1 | 322560 | 283852.8 | 0 | 283852.8
Oasis Buildings- New Capital | inv ( 12 ) 12-2020 | 12 | Oasis Buildings- New Capital12 | 1849863.6 | 1753693.64 | 0 | 1753693.64
Rabigh CCPP-Civil | K0006 Inv-03 | 3 | Rabigh CCPP-Civil3 | 3935285.21 | 18102311.96 | 0 | 4525577.99
Red Sea Museum-Bab El-Bunt | K0003 Inv-03 | 3 | Red Sea Museum-Bab El-Bunt3 | 1065253.06 | 3675123.09 | 0 | 1225041.03
EMAAR-PKG#22-MARASSI | OB-RE-PKG#22 |  | EMAAR-PKG#22-MARASSI | 441828.87 | 0 | 0 | #DIV/0!
Al-Parco | cr INV ( 3 ) ALparco | 3 | Al-Parco3 | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Cr.Compensation |  | Siemens 6x500/220 KV GIS-MOU | 0 | 0 | 0 | #DIV/0!
Roots -Kafr ElSheikh Bridge | D0009-OB-Dec-2020/Cr | 2020 | Roots -Kafr ElSheikh Bridge2020 | 0 | 0 | 0 | #DIV/0!
El Zagazig Railway P2 | D0044-OB-Dec-2020/Cr | 2020 | El Zagazig Railway P22020 | 0 | 0 | 0 | #DIV/0!
Ghana | -1 | 1 | Ghana1 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Dividend Netting off |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Luxor North Axis Bridge-Off | Credit - IPC2 | 2 | Luxor North Axis Bridge-Off2 | 0 | 0 | 0 | #DIV/0!
Get Business Complex | Cr.INV ( 13 ) GET | 13 | Get Business Complex13 | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Cr Adj. Inv. 22 | 22 | Siemens 6x500/220 KV GIS-MOU22 | 0 | 0 | 0 | #DIV/0!
FX-04-22 U.Communities-UE | 68 |  | FX-04-22 U.Communities-UE | 383620.06 | 0 | 0 | #DIV/0!
Get Business Complex | CR - INV ( 6 ) GET | 6 | Get Business Complex6 | 0 | 0 | 0 | #DIV/0!
New Capital | ref.1 |  | New Capital | 0 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | Cr-40 EGP - Giza III | 40 | Giza North PP Phase3(CP-117)40 | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | kafr shokr ipc9+ | 9 | Kafr Shokr Bridge9 | 0 | 0 | 0 | #DIV/0!
AIRDEFNSE -EPOXY | IPC09TR0066 | 9 | AIRDEFNSE -EPOXY9 | 394112.5 | 0 | 0 | #DIV/0!
Cairo North PP Rehabilitation | 7 EGP - Cairo North |  | Cairo North PP Rehabilitation | 41928.07 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 259 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 8 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 665214.6667 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | IPC#FINAL#D0073 |  | WADY EL-NATROUN BRIDGE(HST) | 9940 | 0 | 0 | #DIV/0!
El-Moneeb Bridge | D0038-OB-Dec-2020/Cr | 2020 | El-Moneeb Bridge2020 | 0 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 69 |  | FX-02-22 Decent Life-UE | 585842.11 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR 180057 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cr.91 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_inv.6 | 6 | Akhmem Assiut6 | 0 | 0 | 0 | #DIV/0!
Beni Suef COMCAVI | 180005 |  | Beni Suef COMCAVI | -198497.8 | 0 | 0 | #DIV/0!
Open Channel 2 | CAN.IPC02TR0099(02) | 2 | Open Channel 22 | 0 | 0 | 0 | #DIV/0!
Port Said Grain Storage | rent_004 |  | Port Said Grain Storage | 147900 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/003AdjCnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.CR.Soc Inv44/47 | 44 | Akhmem Assiut44 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR-5-Euro-South helw | 5 | South Helwan PP (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Palm Hill-Infra Str(Elec.Work) | Retention bal. ded. |  | Palm Hill-Infra Str(Elec.Work) | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | DEC ADJ 22 |  | Banha PP (CP-117) | 7447625.25 | 0 | 0 | #DIV/0!
Waldorf Astoria Cairo | CR Waldorf IPC 20 | 20 | Waldorf Astoria Cairo20 | 0 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 101 |  | FX-02-22 Decent Life-UE | 593161.81 | 0 | 0 | #DIV/0!
Mohamed Ali Palace | CR.TR0015CLOSING.DEC |  | Mohamed Ali Palace | 0 | 0 | 0 | #DIV/0!
Baron Palace | 10075 |  | Baron Palace | 0 | 0 | 0 | #DIV/0!
Sewage Treatment Plant | CR-IPC#1 | 1 | Sewage Treatment Plant1 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 14 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 15152.72 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | adj commercial fees |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 15 EGP - Beni Suef |  | Beni-Suef Power Plant EPC | 37500216.58 | 37541346 | 0 | 37541346
ZED Phase 2 | IPC09TR0062 | 9 | ZED Phase 29 | 14083.82 | 0 | 0 | #DIV/0!
ARAB ALMADABEG WWTP 105000 CMD | 220621006 |  | ARAB ALMADABEG WWTP 105000 CMD | 11451061.78 | 0 | 0 | #DIV/0!
New Capital | cm 12 |  | New Capital | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 52 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
LRT Project | CR.TR0028CLOSING.DEC |  | LRT Project | 0 | 0 | 0 | #DIV/0!
LP-09-22 Koning Buzz | 91 |  | LP-09-22 Koning Buzz | 635778 | 0 | 0 | #DIV/0!
Houd Negaih | P-44-EGY Hاتحاد تشيد | 44 | Houd Negaih44 | 5000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 106 |  | Al-Shabab PP Phase II (CP-117) | -29361310.7738 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 56 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Waldorf Astoria Cairo | CR Waldorf IPC 19 | 19 | Waldorf Astoria Cairo19 | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 86 |  | Governmental Campus-N2 | 225372 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | reverse |  | South Helwan PP (CP-117) | -181104.17 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | CR-IPC#1. | 1 | Elmaragha Bridge - Sohag1 | 0 | 0 | 0 | #DIV/0!
Hadaek ElAharam | D0037-OB-Dec-2020/Cr | 2020 | Hadaek ElAharam2020 | 0 | 0 | 0 | #DIV/0!
LRT | D0045-OB-Dec-2020/Cr | 2020 | LRT2020 | 0 | 0 | 0 | #DIV/0!
Barwa and Damac 220 OHTL | CR adj inv. 3 | 3 | Barwa and Damac 220 OHTL3 | 0 | 0 | 0 | #DIV/0!
Koumassi Flyover | CR INV 1 | 1 | Koumassi Flyover1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | rev.( 16 EGP-Shabab |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 8 EGP - South Helwan |  | South Helwan PP (CP-117) | 185480.3714 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | rev.( 2 EGP - Sou. H |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Guinea 2 | Cr.P-2S-10 | 2 | Guinea 22 | 0 | 0 | 0 | #DIV/0!
Business District Hyde Park | INV ( 4 ) HY Bark CR | 4 | Business District Hyde Park4 | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2103220002 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Industria Sadat | Cr.Sadat Indust Inv2 | 2 | Industria Sadat2 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Cr (4EGP-South.Helw) |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Capital One | Cr-10Captal 1 | 10 | Capital One10 | 0 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 478 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Koning Food V3 LP-09-20 | 15 |  | Koning Food V3 LP-09-20 | 0 | 0 | 0 | #DIV/0!
New Capital | ref.3 |  | New Capital | 0 | 0 | 0 | #DIV/0!
6th Oct. Ph2 PP-Elect Work | 2104220005 |  | 6th Oct. Ph2 PP-Elect Work | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-Tah ipc 5 | 5 | Tarek Abdel-Hakim Center5 | 0 | 0 | 0 | #DIV/0!
Sixty Iconic Tower | Inv ( 8) sixty | 8 | Sixty Iconic Tower8 | 280430 | 0 | 0 | #DIV/0!
Toshka GIS 500 kV | CRToshka Sub Inv. 24 | 24 | Toshka GIS 500 kV24 | 0 | 0 | 0 | #DIV/0!
Mohamed Ali Palace Restoration | Mohamed aly3 3final |  | Mohamed Ali Palace Restoration | 1493361.02 | 0 | 0 | #DIV/0!
SHUQAIQ High Voltage Works | 1 |  | SHUQAIQ High Voltage Works | 3611412.1 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-005 | 5 | Maspiro Towers5 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv-04 Final | 4 | MOC HQ at Diriyah4 | 16246137.192 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11583 |  | FURJAN Cable Works | 60494.4 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 7 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1899620.581 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC#2 | 2 | Maspiro Towers2 | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2008210011 |  | Manshiet Nasser Substation | 4193511.78 | 0 | 0 | #DIV/0!
Roubiky Hassan Allam | IPC#FINAL#Roubiky |  | Roubiky Hassan Allam | 107587.5 | 0 | 0 | #DIV/0!
Sodic East | CR.TR0004CLOSING.DEC |  | Sodic East | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180077 |  | Suez Gulf Substation | 8156.34 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.9 | 9 | Akhmem - Qena9 | 0 | 0 | 0 | #DIV/0!
FX-05-22 Close compound | 79 |  | FX-05-22 Close compound | 117784.8 | 0 | 0 | #DIV/0!
EL -mahager Bridge Ain sokhna | CR - Mahager Project |  | EL -mahager Bridge Ain sokhna | 0 | 0 | 0 | #DIV/0!
Almaza Bridge - Safir 2 | CR-S003 |  | Almaza Bridge - Safir 2 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 47 |  | Suez Gulf Substation | 631298.1144 | 0 | 0 | #DIV/0!
MOTHANA 400/132kV SS | 216 |  | MOTHANA 400/132kV SS | 0 | 0 | 0 | #DIV/0!
Benban 500 K.V/95 K.M | CR.Ret Benban Lot 2 |  | Benban 500 K.V/95 K.M | 0 | 0 | 0 | #DIV/0!
Port Said Grain Storage | CR-IPC#5 GSCC | 5 | Port Said Grain Storage5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 242 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Toshka-04 GIS Substation | Deb.adv. $ Toshka 4. |  | Toshka-04 GIS Substation | 11677.59 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 13 EUR Rev. 2 |  | South Helwan PP (CP-117) | 145002.645 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 16 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 126742.8 | 0 | 0 | #DIV/0!
U3 & U5 | CR-55/2 | 55 | U3 & U555 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 51 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 5 EGP- Suez Gulf |  | Suez Gulf Substation | 100898.24 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2105210014 |  | Miscellaneous Projects | -10500 | 0 | 0 | #DIV/0!
FX-04-22 U.Communities-UE | 72 |  | FX-04-22 U.Communities-UE | 4732.43 | 0 | 0 | #DIV/0!
Berty Badr Bridge | INV ( 2 ) Berty Badr | 2 | Berty Badr Bridge2 | 78559.31 | 0 | 0 | #DIV/0!
Tarek AbdelHakim Center - KSA | CR K0001-3 | 3 | Tarek AbdelHakim Center - KSA3 | 0 | 0 | 0 | #DIV/0!
ARAB ALMADABEG WWTP 105000 CMD | 220421002 |  | ARAB ALMADABEG WWTP 105000 CMD | 13746900.25 | 0 | 0 | #DIV/0!
Akhmem Assiut | Inv.54 Assuit Akhmem | 54 | Akhmem Assiut54 | 21492512.99 | 0 | 0 | #DIV/0!
Benban 3/ Toshka 2 LOT 4 | Cr.Tos Lot6 Inv.9 | 9 | Benban 3/ Toshka 2 LOT 49 | 0 | 0 | 0 | #DIV/0!
ACWA POWER & NOMAC HQ | CR Acwa ipc 2 | 2 | ACWA POWER & NOMAC HQ2 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 267 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 50 |  | Suez Gulf Substation | 12874016.5632 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC#3 | 3 | Maspiro Towers3 | 0 | 0 | 0 | #DIV/0!
Hyper One Badr | INV ( 12 ) Hyper | 12 | Hyper One Badr12 | 116377.44 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR- W. Dom invs 2018 | 2018 | W Dam PP Phase II (CP-117)2018 | 0 | 0 | 0 | #DIV/0!
Port Said Port Silos | PORTSAID SUPPLYIPC12 | 12 | Port Said Port Silos12 | 3887747 | 0 | 0 | #DIV/0!
October Under-Railway Tunnel | cr-oct.tunnel ipc 1 | 1 | October Under-Railway Tunnel1 | 0 | 0 | 0 | #DIV/0!
Cameroon EAR | CR.P-09-13 AccRev | 9 | Cameroon EAR9 | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 1901220004 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 295 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Ministries Buildings | cr-mini core ipc 11 | 11 | Ministries Buildings11 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 1904220002 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Safir bridge | D0021-OB-Dec-2020/CR | 2020 | Safir bridge2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 245 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 9 EGP - Shabab | 9 | Al-Shabab PP Phase II (CP-117)9 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR IPC-12-Saray | 12 | Taval Sarai 5212 | 0 | 0 | 0 | #DIV/0!
Infra Project 4514 | 220621005 |  | Infra Project 4514 | 133333333.33 | 0 | 0 | #DIV/0!
New Giza 2 | OB-SI-New Giza 2 |  | New Giza 2 | 1317483.36 | 0 | 0 | #DIV/0!
Almaza | Cr Adj Inv 11 | 11 | Almaza11 | 0 | 0 | 0 | #DIV/0!
LP-07-22 Koning GPS | 84 |  | LP-07-22 Koning GPS | 13650 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Cr -5-Euro-South hel | 5 | South Helwan PP (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Soci.Timay.358K.M |  | Beni Seuf - 358 | 300100 | 0 | 0 | #DIV/0!
Royal City | Royal Cen Zone ipc24 | 24 | Royal City24 | 3256136.08 | 0 | 0 | 3256136.08
Sokhna Port Expansion | SPX ROADS 2 FINAL |  | Sokhna Port Expansion | 56070.14 | 0 | 0 | 58873.647
RING ROAD MARYOTIA EXPANSION | Mariotya ESC.19 est |  | RING ROAD MARYOTIA EXPANSION | 2260334.86 | 0 | 0 | 2373351.603
Residence 8 ( S05 ) | Inv ( 1 ) S05 | 1 | Residence 8 ( S05 )1 | 1401400 | 0 | 0 | 1401400
Residence 8 ( k12 ) | INV ( 1 ) R08-K12 | 1 | Residence 8 ( k12 )1 | 1024100 | 0 | 0 | 1024100
Central Capital | INV ( 5 ) Central Ca | 5 | Central Capital5 | 33984 | 0 | 0 | 33984
Get Business Complex | INV ( 15 ) GET | 15 | Get Business Complex15 | 1172197.1 | 0 | 0 | 1172197.1
Get Business Complex | INV ( 13 ) GET | 13 | Get Business Complex13 | 3065708.74 | 0 | 0 | 3065708.74
Seashell Playa 5 Villas | 20/12/2023 |  | Seashell Playa 5 Villas | 33072.33 | 0 | 0 | 37702.4562
Katameya Creeks - RME | IPC15TR0053 | 15 | Katameya Creeks - RME15 | 132898.04 | 0 | 0 | 132898.04
U3 & U5 | IPC001 | 1 | U3 & U51 | 741275.46 | 0 | 0 | 741275.46
RING ROAD MARYOTIA EXPANSION | فروق اسعار المريوطية |  | RING ROAD MARYOTIA EXPANSION | 6037054.86 | 0 | 0 | 6338907.603
Egyptian Exchange Building | Egy Exch IPC1 | 1 | Egyptian Exchange Building1 | 185780585 | 0 | 0 | 185780585
Port Said Grain Storage | IPC#5Port Said 2 | 5 | Port Said Grain Storage5 | 866250 | 0 | 0 | 1155000
ARAB ALMADABEG WWTP 105000 CMD | 220421001 |  | ARAB ALMADABEG WWTP 105000 CMD | 24188122.11 | 15510764 | 4595743.2 | 21153072.35
TZ – Offshore E&M Procurement | 457 |  | TZ – Offshore E&M Procurement | 455556.64 | 0 | 0 | 455556.64
Nuweibaa (Swro) | 220321003 |  | Nuweibaa (Swro) | 846941.68 | 0 | 0 | 846941.68
UIC Project (LP-04-21) | 62 |  | UIC Project (LP-04-21) | 48750 | 0 | 0 | 48750
Playa Resort | 21000004 |  | Playa Resort | 62370158.7667 | 0 | 0 | 78586400.046
Benban 500 K.V/95 K.M | Ref.Ret Benban Lot 2 |  | Benban 500 K.V/95 K.M | 11755279.89 | 0 | 0 | 11755279.89
Akhmem - Qena | Ref.Ret Qen-akh 7 |  | Akhmem - Qena | 50000000 | 0 | 0 | 50000000
SHATRA 400/132kV SS | 426 |  | SHATRA 400/132kV SS | 772.46 | 772.46 | 0 | 772.46
Containment Data Center- | 33 |  | Containment Data Center- | 9750258 | 0 | 0 | 9750258
SHAT Al ARAB 400/132kV SS | 420 |  | SHAT Al ARAB 400/132kV SS | 1406409.99 | 1406409.99 | 0 | 1406409.99
Taval Sarai 52 | IPC-12-Saray | 12 | Taval Sarai 5212 | 1506383.64 | 1302893.97 | 0 | 1302893.975
MAYSAN 400/132kV SS | 399 |  | MAYSAN 400/132kV SS | 377377.62 | 373453.82 | 0 | 377377.62
Assuit PP (CP-118) | 2105210002 |  | Assuit PP (CP-118) | 2466531.65 | 2596349.11 | 0 | 2596349.11
AWEER POWER STATION 'H' Phase | LOC/014 |  | AWEER POWER STATION 'H' Phase | 2578692.06 | 2037166.721 | 257869.206 | 2552905.137
Railway Bridge - Alex | FPC - Mohamed Kamel |  | Railway Bridge - Alex | 1515464.85 | 0 | 0 | 1515464.85
South Helwan PP (CP-117) | 2012210036 |  | South Helwan PP (CP-117) | -4180518.1 | 0 | 0 | -4180518.1
Marsa Alam/ Bernes LOT2 OHTL | Inv. 27 Usd | 27 | Marsa Alam/ Bernes LOT2 OHTL27 | 24764.46 | 0 | 0 | 24764.46
Ghana Street lighting | MIDA Sply. Inv. 5 | 5 | Ghana Street lighting5 | 186469.51 | 0 | 0 | 186469.51
Rail Way Tunnel Zagazig | D0025-OB-Dec-2020 | 2020 | Rail Way Tunnel Zagazig2020 | 2022800 | 0 | 0 | 2022800
marassi inland marina | D0029-OB-Dec-2020 | 2020 | marassi inland marina2020 | 13255239.56 | 0 | 0 | 13255239.56
Masr ELgedeeda | D0040-OB-Dec-2020 | 2020 | Masr ELgedeeda2020 | 1720937.5 | 0 | 0 | 1720937.5
El Salam Bridge | D0048 OB-Dec-2020 | 2020 | El Salam Bridge2020 | 2538210 | 0 | 0 | 2538210
Mangrouve Hotel - Gouna | TR0021DEC.Clocing |  | Mangrouve Hotel - Gouna | 43967 | 0 | 0 | 43967
Celia | D0020-OB-Dec-2020 | 2020 | Celia2020 | 2241458.81 | 0 | 0 | 2241458.81
Development of Mahmudiyah axis | D0012-OB-Dec-2020 | 2020 | Development of Mahmudiyah axis2020 | 7537500 | 0 | 0 | 7537500
El Boghaz Brigde | IPC#22 | 22 | El Boghaz Brigde22 | 2932623.73 | 2709847.84 | 0 | 2754385.57
Taval Sarai 52 | IPC_1_SARAYA_GAMA |  | Taval Sarai 52 | 198511.2 | 0 | 0 | 198511.2
Assuit PP (CP-118) | 2010210004 |  | Assuit PP (CP-118) | 1585185.63 | 1398926.31 | 249666.74 | 1648593.05
Celia | IPC0006 | 6 | Celia6 | 797127.72 | 346249.32 | 0 | 764000.45
Assuit PP (CP-118) | 2010210001 |  | Assuit PP (CP-118) | 1732764.79 | 1529164.94 | 272910.45 | 1802075.39
Manshiet Nasser Substation | 2004210012 |  | Manshiet Nasser Substation | 591061.51 | 539289.67 | 0 | 539289.67
Al-Shabab PP Phase II (CP-117) | 2002210019 |  | Al-Shabab PP Phase II (CP-117) | 2599657.87 | 2707751.75 | 0 | 2707751.75
Manshiet Nasser Substation | 2004210010 |  | Manshiet Nasser Substation | 4193511.78 | 0 | 0 | 4193511.78
Manshiet Nasser Substation | 2004210009 |  | Manshiet Nasser Substation | 3197756.28 | 0 | 0 | 3197756.28
W Dam PP Phase II (CP-117) | 2002210027 |  | W Dam PP Phase II (CP-117) | 2107952.45 | 1965342.9 | 0 | 1965342.9
Al-Shabab PP Phase II (CP-117) | 2002210018 |  | Al-Shabab PP Phase II (CP-117) | 968202.61 | 166622.15 | 491178.51 | 657800.66
Ministries A13-A14 | 10097 |  | Ministries A13-A14 | 205000 | 0 | 0 | 205000
Beni Seuf - 358 | Inv.1 Temmay 500 k.v | 1 | Beni Seuf - 3581 | 14975339.35 | 0 | 0 | 14975339.35
Manshiet Nasser Substation | 2001210004 |  | Manshiet Nasser Substation | 1414421.75 | 1290530.76 | 0 | 1290530.76
Manshiet Nasser Substation | 533 |  | Manshiet Nasser Substation | 163356.13 | 149051.8 | 0 | 149051.8
Al-Shabab PP Phase II (CP-117) | 180155 |  | Al-Shabab PP Phase II (CP-117) | 5468.65 | 797.54 | 0 | 6266.16
LAYYAH CCPP | 471 |  | LAYYAH CCPP | 10283760 | 0 | 0 | 10283760
6th Oct. Ph2 PP-Elect Work | 14 EGP - October |  | 6th Oct. Ph2 PP-Elect Work | 157479.07 | 157479.07 | 0 | 157479.07
Suez Gulf Substation | 10 EGP - Suez Gulf |  | Suez Gulf Substation | 431640.3238 | 407900.11 | 45322.23 | 453222.34
Suez Gulf Substation | 16 EGP VO Progress |  | Suez Gulf Substation | 61047.25 | 57798.16 | 6422.02 | 64220.18
Suez Gulf Substation | 19 EGP MRR Main |  | Suez Gulf Substation | 25487.3 | 24130.8 | 2681.2 | 26812
Manshiet Nasser Substation | 180172 |  | Manshiet Nasser Substation | 1074277.06 | 1127990.91 | 0 | 1127990.91
Manshiet Nasser Substation | 1906210009 |  | Manshiet Nasser Substation | 542417.17 | 486789.72 | 87301.45 | 574091.17
Maspiro Towers | IPC#1 | 1 | Maspiro Towers1 | 892200 | 883278 | 0 | 886252
Suez Gulf Substation | 1909210013 |  | Suez Gulf Substation | 300804.72 | 300804.72 | 0 | 300804.72
Assuit PP (CP-118) | 1906210016 |  | Assuit PP (CP-118) | 1315675.08 | 1161085.37 | 207216.84 | 1368302.21
Assuit PP (CP-118) | 1906210017 |  | Assuit PP (CP-118) | 519518.29 | 458474.88 | 81824.14 | 540299.02
Zambia Project | SCD4/003 |  | Zambia Project | 175449.71 | 0 | 0 | 175449.71
Beni-Suef Power Plant EPC | Adj. 180178 |  | Beni-Suef Power Plant EPC | 427482390.92 | 427482390.92 | 0 | 427482390.92
Akhmem - Qena | Soc Inv 26 $ Quna | 26 | Akhmem - Qena26 | 159039 | 0 | 0 | 159039
Beni-Suef Power Plant EPC | 180132 |  | Beni-Suef Power Plant EPC | 283799492.53 | 283799492.53 | 0 | 283799492.53
Akhmem Assiut | Ref . Soc Inv 48Asui | 48 | Akhmem Assiut48 | 2182603.5 | 0 | 0 | 2182603.5
Assuit PP (CP-118) | 1901210008 |  | Assuit PP (CP-118) | 3183036.9747 | 0 | 0 | 3183036.9747
Military 110 Kayan Project | Refund Retention Kay |  | Military 110 Kayan Project | 19499900 | 0 | 0 | 19499900
Al-Shabab PP Phase II (CP-117) | 28 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 2957512.2381 | 2639579.67 | 465808.18 | 3105387.85
Al-Shabab PP Phase II (CP-117) | 26 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 483945.1429 | 431921.04 | 76221.36 | 508142.4
W Dam PP Phase II (CP-117) | 29 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 3185721.0095 | 2843256 | 501751.06 | 3345007.06
Al-Shabab PP Phase II (CP-117) | 11 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 434762.5333 | 0 | 0 | 456500.66
MOTHANA 400/132kV SS | 204 |  | MOTHANA 400/132kV SS | 98778.12 | 0 | 0 | 98778.12
Suez Gulf Substation | 180163 |  | Suez Gulf Substation | 3515018.46 | 3515018.46 | 0 | 3515018.46
Suez Gulf Substation | 180162 |  | Suez Gulf Substation | 31206884.82 | 31206884.82 | 0 | 31206884.82
Al-Shabab PP Phase II (CP-117) | 180106 |  | Al-Shabab PP Phase II (CP-117) | 24798.34 | 22174.15 | 3913.09 | 26087.24
Beni-Suef Power Plant EPC | 180154 |  | Beni-Suef Power Plant EPC | 92867910.38 | 0 | 0 | 92867910.38
Marsa Matrouh 500KV | Inv, 6 usd Borg Arab | 6 | Marsa Matrouh 500KV6 | 1342780.82 | 0 | 0 | 1342780.82
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 06 |  | Giza North PP Ph I,II (CP-117) | 2688.11 | 2688.11 | 0 | 2688.11
Abu Qir PP (CP-117) | Abo Quir Invces |  | Abu Qir PP (CP-117) | 235181.73 | 54746.7 | 0 | 54746.7
K047 FDH JV | Inv. No.15 KWD Floor | 15 | K047 FDH JV15 | 86543.43 | 51901.47 | 0 | 77889.09
Zafranaa - Ras Ghareb | Adj. Inv.18 | 18 | Zafranaa - Ras Ghareb18 | 42553580.77 | 0 | 0 | 42553580.77
Abou El Matameer and Sammanoud | Inv 90 P8 Sammound | 90 | Abou El Matameer and Sammanoud90 | 2776641.7 | 0 | 0 | 2776641.7
Beni-Suef Power Plant EPC | 103 |  | Beni-Suef Power Plant EPC | 5051717777.8083 | 0 | 0 | 5051717777.8083
South Helwan PP (CP-117) | 180123 |  | South Helwan PP (CP-117) | 200016.25 | 210412.1 | 0 | 210412.1
Cairo South PP Rehabilitation | 89 |  | Cairo South PP Rehabilitation | 4052526.3401 | 0 | 0 | 4052526.3401
W Dam PP Phase II (CP-117) | 180043 |  | W Dam PP Phase II (CP-117) | 39427.781 | 0 | 0 | 41399.17
W Dam PP Phase II (CP-117) | 180039 |  | W Dam PP Phase II (CP-117) | 67012.6857 | 0 | 0 | 70363.32
W Dam PP Phase II (CP-117) | 180038 |  | W Dam PP Phase II (CP-117) | 23518.0667 | 0 | 0 | 24693.97
Ain-Sokhna PP (CP-117) | 24 |  | Ain-Sokhna PP (CP-117) | 60401842 | 0 | 0 | 60401842
Banha PP (CP-117) | 23 |  | Banha PP (CP-117) | 28330354 | 0 | 0 | 28330354
W Dam PP Phase II (CP-117) | 180045 |  | W Dam PP Phase II (CP-117) | 271925.6762 | 0 | 0 | 285521.96
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 03 |  | Giza North PP Ph I,II (CP-117) | 940885.4 | 940885.4 | 0 | 940885.4
Abou El Matameer and Sammanoud | Samanoud 5 inv.81 | 81 | Abou El Matameer and Sammanoud81 | 8005328.32 | 0 | 0 | 8005328.32
Cairo South PP Rehabilitation | 6 USD - Cairo South |  | Cairo South PP Rehabilitation | 5565.27 | 5565.27 | 0 | 5565.27
Al-Wukair 11 Substation | Inv 20 Qatar | 20 | Al-Wukair 11 Substation20 | 807356.9 | 807356.9 | 0 | 807356.9
Berket Ghelion | Inv 18 Ghelion | 18 | Berket Ghelion18 | 5444747.64 | 0 | 0 | 5444747.64
Strining Lot A- Elegect | 1 Elegict |  | Strining Lot A- Elegect | 1898745.45 | 104426 | 0 | 1877346.815
Siemens 6x500/220 KV GIS-MOU | 3 |  | Siemens 6x500/220 KV GIS-MOU | 5058485.66 | 0 | 0 | 5058485.66
Al-Shabab PP Phase II (CP-117) | 4 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 7561970.1779 | 5929576.75 | 1147907.07 | 7385453.44
Al-Shabab PP Phase II (CP-117) | 3 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 7552112.2233 | 5417959.4 | 1146410.64 | 7042783.37
Al-Shabab PP Phase II (CP-117) | 7 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 13708468.4881 | 11294420.55 | 2080945.52 | 18079323.97
Al-Shabab PP Phase II (CP-117) | 9 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 380734.4762 | 339805.52 | 59965.68 | 738191.2
Suez Gulf Substation | 1 EGP - Suez Gulf |  | Suez Gulf Substation | 1604181.77 | 0 | 165070.3 | 1650703.0412
Palm Hill-Infra Str(Elec.Work) | 4 - palm hills |  | Palm Hill-Infra Str(Elec.Work) | 53794 | 0 | 0 | 59173.4
Suez Gulf Substation | 3 USD/123/2011/2012 |  | Suez Gulf Substation | 74110.6719 | 0 | 0 | 75000
Cameron EDC | 018/2019 |  | Cameron EDC | 77795 | 76040.41 | 0 | 76040.41
Cameron EDC | 014/2019 |  | Cameron EDC | 282606.67 | 282346.18 | 0 | 282346.18
Cameron EDC | 011/2019 |  | Cameron EDC | 84301.3 | 84142.91 | 0 | 84142.91
Cameron EDC | 027/2020 FCV |  | Cameron EDC | 184618730.63 | 92309365.31 | 0 | 92309365.31
Cameron EDC | 026/2020 FCV |  | Cameron EDC | 29020647.18 | 14510323.59 | 0 | 14510323.59
Cameron EDC | 025/2020 FCV |  | Cameron EDC | 30447892.13 | 15223946.43 | 0 | 15223946.43
Kuwait | 35-132KVA(9H) | 132 | Kuwait132 | 42039.91 | 31529.93 | 0 | 31529.93
Kuwait | 31-132KVA-J | 132 | Kuwait132 | 37179.26 | 27884.44 | 0 | 27884.44
Al-Shabab PP Phase II (CP-117) | 180108 |  | Al-Shabab PP Phase II (CP-117) | 31339.17 | 28022.82 | 4945.2 | 32968.02
Al-Shabab PP Phase II (CP-117) | 180105 |  | Al-Shabab PP Phase II (CP-117) | 144986.81 | 129644.13 | 22878.38 | 152522.51
W Dam PP Phase II (CP-117) | 180104 |  | W Dam PP Phase II (CP-117) | 11649.65 | 10416.87 | 1838.27 | 12255.14
W Dam PP Phase II (CP-117) | 180094 |  | W Dam PP Phase II (CP-117) | 22624.38 | 20230.24 | 3570.04 | 23800.28
W Dam PP Phase II (CP-117) | 10 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 110389.9429 | 0 | 17386.42 | 22905.92
W Dam PP Phase II (CP-117) | 6 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 39462.1429 | 32694.3 | 6215.29 | 41435.25
Al-Shabab PP Phase II (CP-117) | 543 |  | Al-Shabab PP Phase II (CP-117) | 145473.04 | 141684.68 | 25003.18 | 166687.86
W Dam PP Phase II (CP-117) | 527 |  | W Dam PP Phase II (CP-117) | 527399.68 | 513665.31 | 90646.82 | 604312.13
W Dam PP Phase II (CP-117) | 180113 |  | W Dam PP Phase II (CP-117) | 134475.89 | 120245.49 | 21219.79 | 141465.28
Al-Shabab PP Phase II (CP-117) | 5 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 1027130.92 | 0 | 0 | 1078487.466
Al-Shabab PP Phase II (CP-117) | 9 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 102943.42 | 108090.591 | 0 | 108090.591
Suez Gulf Substation | 7 EGP - (VO)progress |  | Suez Gulf Substation | 411301.5524 | 0 | 0 | 0
Suez Gulf Substation | 6 EGP - VO MRR |  | Suez Gulf Substation | 221233.4 | 209065.56 | 23229.51 | 232295.07
Suez Gulf Substation | Inv 1 EGP VO SG | 1 | Suez Gulf Substation1 | 463979.7238 | 438460.84 | 48717.87 | 487178.71
Suez Gulf Substation | 1 USD - Suez Gulf |  | Suez Gulf Substation | 342296.42 | 0 | 0 | 342296.42
Siemens 6x500/220 KV GIS-MOU | Inv 62 P5Assuit | 62 | Siemens 6x500/220 KV GIS-MOU62 | 3244052.91 | 2346747.88 | 486607.94 | 2833355.82
Damac 2x60/22 KV S/S | Inv 28 Damac | 28 | Damac 2x60/22 KV S/S28 | 1604314.25 | 1134949.53 | 240647.15 | 1375596.68
Abu Qir PP (CP-117) | 16 Euro-Abo Qeir 117 |  | Abu Qir PP (CP-117) | 139632.24 | 139632.24 | 0 | 139632.24
South Helwan PP (CP-117) | 180149 |  | South Helwan PP (CP-117) | 45702.85 | 49249.6 | 0 | 49249.6
South Helwan PP (CP-117) | 4 EGP - South Helwan |  | South Helwan PP (CP-117) | 118200.5048 | 122787.84 | 0 | 124110.52
New Capital | Inv. 7 Abozabaal | 7 | New Capital7 | 2859185.04 | 2075681.5 | 300214.43 | 2375895.93
Giza North PP Phase3(CP-117) | 32 EGP- Giza North 3 |  | Giza North PP Phase3(CP-117) | 73108.7619 | 65249.57 | 11514.63 | 76764.2
Al-Shabab PP Phase II (CP-117) | 180007 |  | Al-Shabab PP Phase II (CP-117) | 99981.77 | 89401.58 | 15776.75 | 105178.33
Tamey El-amdeed Substation | TAM-CW-EGP-13 | 13 | Tamey El-amdeed Substation13 | 5917379.64 | 4378250.65 | 887606.95 | 5265857.6
Tamey El-amdeed Substation | TAM-SW-EGP-07 | 7 | Tamey El-amdeed Substation7 | 695625 | 514762.5 | 104343.75 | 619106.25
Ismailiya East Substation | 19100023 |  | Ismailiya East Substation | 831250 | 615125 | 124687.5 | 739812.5
Tamey El-amdeed Substation | 19100020 |  | Tamey El-amdeed Substation | 875000 | 644613.98 | 131250 | 775863.98
Beni Suef Substation R61 | BSF-SW-EGP-08 | 8 | Beni Suef Substation R618 | 190312 | 140830.88 | 28546.8 | 169377.68
Beni Suef Substation R61 | BSF-SW-04 | 4 | Beni Suef Substation R614 | 695625 | 518240.62 | 104343.75 | 622584.37
Ismailiya East Substation | ISE-CW-EGP-08 | 8 | Ismailiya East Substation8 | 2301280 | 1714453.6 | 345192 | 2059645.6
Ismailiya East Substation | ISE-CW-EGP-07 | 7 | Ismailiya East Substation7 | 3492730 | 2602083.85 | 523909.5 | 3125993.35
Tamey El-amdeed Substation | TAM-SD-EGP-02 | 2 | Tamey El-amdeed Substation2 | 212655 | 158427.97 | 31898.25 | 190326.22
Tamey El-amdeed Substation | TAM-SD-EURO-01 | 1 | Tamey El-amdeed Substation1 | 3278673.89 | 2770479.44 | 491801.08 | 3262280.52
Al Mostathmreen GIS Substation | MOS-CW-EURO-IPC3 F | 3 | Al Mostathmreen GIS Substation3 | 3098157.44 | 2246164.14 | 464723.62 | 2710887.76
Beni Suef Substation R61 | BSF-SW-IPC2 | 2 | Beni Suef Substation R612 | 1478750 | 1101668.75 | 221812.5 | 1323481.25
Beni Suef Substation R61 | 18100069 |  | Beni Suef Substation R61 | 2694612.34 | 1953593.95 | 404191.85 | 2357785.8
Al Mostathmreen GIS Substation | 16 sd euro mostsmrin |  | Al Mostathmreen GIS Substation | 914791.17 | 663223.59 | 137218.68 | 800442.27
Ismailiya East Substation | (3)cw elasmailya | 3 | Ismailiya East Substation3 | 5141665.53 | 3830540.82 | 771249.83 | 4601790.65
Al Mostathmreen GIS Substation | 15sd EURO |  | Al Mostathmreen GIS Substation | 1388170.54 | 1006423.65 | 208225.58 | 1214649.23
Al Mostathmreen GIS Substation | 15 sd mosstasmreen |  | Al Mostathmreen GIS Substation | 242226 | 180458.14 | 36334.04 | 216792.18
Al Mostathmreen GIS Substation | SD(11) | 11 | Al Mostathmreen GIS Substation11 | 275602 | 205323.36 | 41340.38 | 246663.74
W Dam PP Phase II (CP-117) | 180130 |  | W Dam PP Phase II (CP-117) | 261592.5 | 233910.46 | 41278.32 | 275188.78
W Dam PP Phase II (CP-117) | 180046 |  | W Dam PP Phase II (CP-117) | 139787.8286 | 0 | 0 | 146777.22
Berket Ghelion | Inv 12 Ghelion | 12 | Berket Ghelion12 | 5871600.89 | 3507993.24 | 1467900.23 | 4975893.47
Ain-Sokhna PP (CP-117) | 41 Euro - Sokhna 117 |  | Ain-Sokhna PP (CP-117) | 556064.6 | 529860 | 0 | 529860
Sodic Club House | (19) sodic club | 19 | Sodic Club House19 | 2166022 | 1675962.94 | 426600.33 | 2102563.27
Berket Ghelion | Inv 17 Ghelion | 17 | Berket Ghelion17 | 1830141 | 1093088.28 | 457535.25 | 1550623.53
Kayan 3 New Cairo Capital City | OB-ST-EL Kayaan |  | Kayan 3 New Cairo Capital City | 58640899.2 | 50223564.95 | 0 | 53223564.95
New Giza 2 | (24)new giza 2 | 24 | New Giza 224 | 2116618 | 9060571.89 | 444489.89 | 9505061.78
New Giza 2 | (23) new giza 2 | 23 | New Giza 223 | 3256456 | 2470878.11 | 683855.77 | 3154733.88
EMAAR-PKG#53-UPTOWN | (22) pkg#53 | 22 | EMAAR-PKG#53-UPTOWN22 | 7192945 | 5904345.47 | 1122160.67 | 7026506.14
EMAAR-PKG#62-UPTOWN | (10)pkg#62 | 10 | EMAAR-PKG#62-UPTOWN10 | 3222186.55 | 2427820.0525 | 1333040.06 | 3760860.1125
EMAAR-PKG#107-MARASSI | (11)pkg#107 | 11 | EMAAR-PKG#107-MARASSI11 | 3590048.6 | 2773227.83 | 424438.28 | 3197666.11
Giza North PP Phase3(CP-117) | 40 EGP-Giza N. III |  | Giza North PP Phase3(CP-117) | 342624.2667 | 0 | 0 | 359755.48
Giza North PP Phase3(CP-117) | 37 EGP-Giza North 3 |  | Giza North PP Phase3(CP-117) | 408653.1714 | 364722.96 | 0 | 364722.96
Giza North PP Ph I,II (CP-117) | 39 EGP-Giza N. I&II |  | Giza North PP Ph I,II (CP-117) | 446737.6286 | 469074.51 | 0 | 469074.51
Beni Seuf - 358 | Inv. 15 Oewon Mousa | 15 | Beni Seuf - 35815 | 61546180.3 | 0 | 10584954.05 | 10584954.05
Beni Seuf - 358 | Inv.4 Temmay Amded | 4 | Beni Seuf - 3584 | 10937952 | 0 | 1911218.05 | 1911218.05
Beni Seuf - 358 | Inv.3 Temmay Amded | 3 | Beni Seuf - 3583 | 5651862.05 | 0 | 981389.96 | 981389.96
Beni Seuf - 358 | Inv. 6 Oewon Mousa | 6 | Beni Seuf - 3586 | 15856660.9 | 11039533.3 | 2724048.45 | 13763581.75
Beni Seuf - 358 | Inv. 2 Oewon Mousa | 2 | Beni Seuf - 3582 | 17413669.91 | 12842618.6 | 2988821 | 15831439.6
Beni Seuf - 358 | Inv.4kafr zeat itay | 4 | Beni Seuf - 3584 | 92797520.75 | 73223007.77 | 14006063.32 | 87229071.09
Beni Seuf - 358 | Inv.Banysouf 4-358 | 358 | Beni Seuf - 358358 | 29559860.57 | 23499501.26 | 4433979.08 | 27933480.34
Beni Seuf - 358 | Inv No1 Abo Kirr | 1 | Beni Seuf - 3581 | 23236416 | 18472950.72 | 3485462.4 | 21958413.12
Ismalia Bridge | (1) blagat asmaaliya | 1 | Ismalia Bridge1 | 10499675 | 2670207.95 | 2500000 | 9183028.95
Ismalia Bridge | (1) Ismailia U 4 | 1 | Ismalia Bridge1 | 7011092 | 2940613.5 | 3300000 | 6240613.5
Ismalia Bridge | (1) Ismailia U 3 | 1 | Ismalia Bridge1 | 5631432 | 2995087.15 | 2000000 | 4995087.15
W Dam PP Phase II (CP-117) | 17 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 412796.7524 | 143661.14 | 65015.49 | 208676.63
Barwa and Damac 220 OHTL | Inv No5 Wattanya220 | 5 | Barwa and Damac 220 OHTL5 | 4810035.12 | 3595090.15 | 721505.3 | 4316595.45
Barwa and Damac 220 OHTL | Inv No3 Wattanya220 | 3 | Barwa and Damac 220 OHTL3 | 6591618.8 | 4926830.75 | 988742.85 | 5915573.6
K047 FDH JV | Inv. NO.8 KWT Floor | 8 | K047 FDH JV8 | 196177.26 | 176559.53 | 0 | 176559.53
EMAAR-PKG#53-UPTOWN | (20)PKG#53 | 20 | EMAAR-PKG#53-UPTOWN20 | 12728277 | 9029077.68 | 1763984.99 | 10793062.67
Beni Suef Substation R61 | (17)beni suif 2 | 17 | Beni Suef Substation R6117 | 6481496 | 1520156.85 | 5516775.56 | 7036932.41
Royal City | Royal city fin ipc43 | 43 | Royal City43 | 14387671.43 | 0 | 0 | 14387671.43
EMAAR-PKG#107-MARASSI | (1) PKG#107 | 1 | EMAAR-PKG#107-MARASSI1 | 5089749 | 5437394.56 | 1029158.15 | 6466552.71
Kayan 3 New Cairo Capital City | (3) ELKAYAN | 3 | Kayan 3 New Cairo Capital City3 | 54597030 | 35643751.5 | 4140013 | 49546399.5
PIP Zona 2 | Inv.5 Zona 2 | 5 | PIP Zona 25 | 3906247.87 | 3671872.9935 | 0 | 3671872.9935
PIP Zona 2 | Inv.04 zona2 | 4 | PIP Zona 24 | 8593695.56 | 8078073.828 | 0 | 8078073.828
Pyramids Industrial Park | Inv.1 PIP west | 1 | Pyramids Industrial Park1 | 1674247.23 | 1573792.3915 | 0 | 1573792.3915
Siemens 6x500/220 KV GIS-MOU | Inv 46 P12El Natroun | 46 | Siemens 6x500/220 KV GIS-MOU46 | 1405349.41 | 1016629.76 | 210802.41 | 1227432.17
Barwa 2x60/22 KV S/S | Inv 28 Barwa | 28 | Barwa 2x60/22 KV S/S28 | 1058684.5 | 748945.6 | 158802.68 | 907748.28
New Capital | INV 3 El Teben | 3 | New Capital3 | 3833054.35 | 5718734.14 | 804941.42 | 3261837.78
New Capital | Inv 4 Abo Zaabl | 4 | New Capital4 | 4071533.33 | 2792988.17 | 427511 | 3220499.17
New Capital | Inv 5 Abo Zaabl | 5 | New Capital5 | 2105923.446 | 1423524.06 | 221121.96 | 1644646.02
Attaqa Power Plant | Attka Sand Feb |  | Attaqa Power Plant | 25250000 | 25250000 | 0 | 25250000
Pyramids Industrial Park | Inv. 2 PIP West | 2 | Pyramids Industrial Park2 | 5625856.05 | 1741561.87 | 0 | 5288304.68
South Helwan PP (CP-117) | 2009210005 |  | South Helwan PP (CP-117) | 1254514.12 | 1039786.63 | 279930.93 | 1319717.56
W Dam PP Phase II (CP-117) | 14 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 1256341.1524 | 1121284.48 | 197873.73 | 1319158.21
South Helwan PP (CP-117) | 2009210007 |  | South Helwan PP (CP-117) | 239840.14 | 211966.82 | 37845.88 | 249812.7
South Helwan PP (CP-117) | 2001210003 |  | South Helwan PP (CP-117) | 333734.18 | 294948.86 | 52662 | 347610.86
South Helwan PP (CP-117) | 180143 |  | South Helwan PP (CP-117) | 146691.18 | 152767.4 | 0 | 152767.4
South Helwan PP (CP-117) | 180124 |  | South Helwan PP (CP-117) | 129154.25 | 135867.05 | 0 | 135867.05
South Helwan PP (CP-117) | 180009 |  | South Helwan PP (CP-117) | 2803954.29 | 2507236.47 | 442453.49 | 2949689.96
South Helwan PP (CP-117) | 180008 |  | South Helwan PP (CP-117) | 451832.26 | 404018.82 | 71297.45 | 475316.27
South Helwan PP (CP-117) | Inv 10,11,13 SH | 10 | South Helwan PP (CP-117)10 | 705941.181 | 630052.5 | 111185.74 | 741238.24
Mall Of Egypt | OB-ST-Mall Of Egypt |  | Mall Of Egypt | 4010646.22 | 5574585.6 | 0 | 8914585.6
West Damietta PP Phase I | Collec 13,14,15 WD |  | West Damietta PP Phase I | 738082.37 | 738082.37 | 0 | 738082.37
Al-Shabab PP Phase II (CP-117) | 18 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 293419.819 | 261877.19 | 46213.62 | 308090.81
Beni Suef Substation R61 | (22) bine suef 2 | 22 | Beni Suef Substation R6122 | 27000000 | 26703000 | 0 | 26703000
Kayan 3 New Cairo Capital City | PO.1 Kayan Healthy |  | Kayan 3 New Cairo Capital City | 3608661 | 1700365 | 1700380 | 3400745
New Capital Tunnels | (1) M.B.ZAYID | 1 | New Capital Tunnels1 | 188609742 | 56697814.75 | 65000000 | 166697814.75
Al Mostathmreen GIS Substation | SD (12) | 12 | Al Mostathmreen GIS Substation12 | 1211134 | 902294.7 | 181670.18 | 1083964.88
Al Mostathmreen GIS Substation | SD (9) MOSSTASMREEN | 9 | Al Mostathmreen GIS Substation9 | 1027945 | 765818.93 | 154191.8 | 920010.73
Al-Wukair 11 Substation | Inv 12 Qatar | 12 | Al-Wukair 11 Substation12 | 1983553 | 1983553 | 0 | 1983553
Al-Shabab PP Phase II (CP-117) | 22 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 520207.3619 | 464285.07 | 81932.66 | 546217.73
Abu Qir PP (CP-117) | Abu Quir march |  | Abu Qir PP (CP-117) | 224568.65 | 224568.65 | 0 | 224568.65
EMAAR-PKG#62-UPTOWN | (6) pkg#62 | 6 | EMAAR-PKG#62-UPTOWN6 | 2621461 | 1639531.84 | 944119.35 | 2583651.19
EMAAR-PKG#107-MARASSI | (5)pkg#107 | 5 | EMAAR-PKG#107-MARASSI5 | 5459726 | 4307013.3 | 812311.36 | 5119324.66
Barwa 2x60/22 KV S/S | Inv 31 Barwa | 31 | Barwa 2x60/22 KV S/S31 | 179906.67 | 127275.43 | 26986 | 154261.43
New Heliopolis | Inv.1 Helepolice | 1 | New Heliopolis1 | 20034607.73 | 16623290.15 | 1352336 | 17975626.15
Siemens 6x500/220 KV GIS-MOU | Soc Inv 40 Itay 11 | 40 | Siemens 6x500/220 KV GIS-MOU40 | 54225.87 | 54225.87 | 0 | 54225.87
Siemens 6x500/220 KV GIS-MOU | Ret.55kafre 3 Final |  | Siemens 6x500/220 KV GIS-MOU | 25441.51 | 25441.48 | 0 | 25441.48
EMAAR-PKG#53-UPTOWN | (19) PKG#53 | 19 | EMAAR-PKG#53-UPTOWN19 | 5695269 | 8766058.58 | 1666048.58 | 10432107.16
Tebbin PP Rehabitation(CP-124) | 1 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 156965.77 | 156965.77 | 0 | 156965.77
Suez Gulf Substation | 180053 |  | Suez Gulf Substation | 52869.27 | 50055.44 | 5561.71 | 55617.15
EMAAR-PKG#53-UPTOWN | (25)pkg#53 | 25 | EMAAR-PKG#53-UPTOWN25 | 16867950 | 12929508.46 | 2415185.85 | 15344694.31
EMAAR-PKG#53-UPTOWN | PKG#85 - IPC FINAL |  | EMAAR-PKG#53-UPTOWN | 4791697.91 | 1421729.26 | 3834934.12 | 5256663.38
Tebbin PP Rehabitation(CP-124) | 4 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 6441887 | 3761593.3 | 0 | 3761593.3
Cairo South PP Rehabilitation | 7 USD - Cairo South |  | Cairo South PP Rehabilitation | 21238.01 | 21238.01 | 0 | 21238.01
W Dam PP Phase II (CP-117) | 22 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 477822.3619 | 426456.46 | 75257.02 | 501713.48
Akhmem Assiut | Inv.53 Assuit Akhmem | 53 | Akhmem Assiut53 | 51642070.07 | 38227356.19 | 0 | 38227356.19
Akhmem Assiut | Inv.51 Assuit Akhmem | 51 | Akhmem Assiut51 | 23472356.1 | 11791613.76 | 3520853.42 | 15312467.18
Akhmem Assiut | Inv.48 Assuit Akhmem | 48 | Akhmem Assiut48 | 80837160.01 | 63860746.41 | 12125574 | 75986320.41
Akhmem Assiut | Inv.47 Assuit Akhmem | 47 | Akhmem Assiut47 | 3633884.9 | 2507380.58 | 545082.74 | 3052463.32
Akhmem Assiut | Inv.33 Assuit Akhmem | 33 | Akhmem Assiut33 | 5953611.3 | 4733120.98 | 893041.7 | 5626162.68
Akhmem Assiut | Inv.24 Assuit Akhmem | 24 | Akhmem Assiut24 | 13890660.64 | 11043075.21 | 2083599.1 | 13126674.31
Akhmem Assiut | inv. 3 Assuit Akhmem | 3 | Akhmem Assiut3 | 8913441.23 | 5303497.531 | 1337016.18 | 6640513.711
Akhmem - Qena | Inv.36 Akhmem Qena | 36 | Akhmem - Qena36 | 1803910.73 | 892935.81 | 270586.61 | 1163522.42
Akhmem - Qena | Inv.27 Akhmem Qena | 27 | Akhmem - Qena27 | 8505159.06 | 6761601.44 | 1275773.86 | 8037375.3
Akhmem - Qena | Inv.16 Qena - Akhmem | 16 | Akhmem - Qena16 | 6417286.1 | 5101742.45 | 962592.92 | 6064335.37
Akhmem - Qena | Inv.6 Qena Akhmem | 6 | Akhmem - Qena6 | 17246098.29 | 13710648.14 | 2586914.74 | 16297562.88
Al-Shabab PP Phase II (CP-117) | 25 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 103603 | 92465.68 | 16317.47 | 108783.15
Ghana | 41/P/10/ER/2017/USD |  | Ghana | 424039.64 | 424025.14 | 0 | 424025.14
Sodic Club House | (21)sodic club | 21 | Sodic Club House21 | 10206715 | 3793458.2 | 717720.45 | 4511178.65
EMAAR-PKG#53-UPTOWN | (21)pkg#53 | 21 | EMAAR-PKG#53-UPTOWN21 | 14681306 | 6077165.95 | 7105289.78 | 13182455.73
Military 110 Kayan Project | Inv. 5 El Kayan | 5 | Military 110 Kayan Project5 | 10205893.83 | 8876021.5 | 0 | 8876021.5
Abou El Matameer and Sammanoud | Inv 96 P13Abo Matami | 96 | Abou El Matameer and Sammanoud96 | 2012061.48 | 1445464.97 | 301809.22 | 1747274.19
Abou El Matameer and Sammanoud | Inv 79 P6Abo Matamir | 79 | Abou El Matameer and Sammanoud79 | 5178875.91 | 3746398.833 | 776831.387 | 4523230.22
El Mostakbal City Project | Inv. 11 Mostakbal | 11 | El Mostakbal City Project11 | 42486137.44 | 35261057.1 | 8922088.86 | 44183145.96
El Mostakbal City Project | Inv. 9 Mostakbal | 9 | El Mostakbal City Project9 | 29276861.32 | 24299794.9 | 6148140.88 | 30447935.78
El Mostakbal City Project | Inv. 8 Mostakbal | 8 | El Mostakbal City Project8 | 39792585.3 | 33027845.81 | 8356442.91 | 41384288.72
El Mostakbal City Project | Inv. 5 Mostakbal | 5 | El Mostakbal City Project5 | 43065772.12 | 35741010.54 | 9043812.15 | 44784822.69
Badr | Inv. 19 Badr | 19 | Badr19 | 21523272 | 14904446.93 | 3228490.65 | 18132937.58
Badr | Inv. 9 Badr | 9 | Badr9 | 4803637.35 | 3566286.45 | 720545.6 | 4286832.05
Badr | Inv. 6 Badr | 6 | Badr6 | 69127091.1 | 51326431.75 | 10369063.7 | 61695495.45
EMAAR-PKG117- MARASSI | 19100003 |  | EMAAR-PKG117- MARASSI | 0.01 | 121416.67 | 15486.19 | 136902.86
Kayan 3 New Cairo Capital City | (1)elkayan fainishin | 1 | Kayan 3 New Cairo Capital City1 | 47740260 | 20148095.55 | 20000000 | 40148095.55
Bani Suef Old Substation | (26)bini suif 2 | 26 | Bani Suef Old Substation26 | 400000 | 395600 | 0 | 395600
Suez Gulf Substation | 180110 |  | Suez Gulf Substation | 8441.26 | 7992 | 888 | 8880
Suez Gulf Substation | 20 EGP VO CCC Supply |  | Suez Gulf Substation | 474531.48 | 449275.75 | 49919.53 | 499195.28
Suez Gulf Substation | 17 EGP VO MRR |  | Suez Gulf Substation | 2407.93 | 2279.77 | 253.31 | 2533.08
Suez Gulf Substation | 180079 |  | Suez Gulf Substation | 3598.07 | 3406.57 | 378.51 | 3785.08
Suez Gulf Substation | 180048 |  | Suez Gulf Substation | 77707.05 | 73571.29 | 8174.59 | 81745.88
Al Mostathmreen GIS Substation | (27)sd elmostsmrin | 27 | Al Mostathmreen GIS Substation27 | 13610 | 10139.45 | 2041.5 | 12180.95
Beni Suef COMCAVI | 180002 |  | Beni Suef COMCAVI | 1124820.87 | 1124820.87 | 0 | 1124820.87
kayan wall lock & Load | KAYAN LOAK&LOAD-IPC4 | 4 | kayan wall lock & Load4 | 9337500 | 5426691.7 | 3000000 | 8426691.7
Ain-Sokhna PP (CP-117) | 180055 |  | Ain-Sokhna PP (CP-117) | 561762.4 | 561762.4 | 0 | 561762.4
Akhmem Assiut | inv. 4 Assuit Akhmem | 4 | Akhmem Assiut4 | 36927133.69 | 21971652.64 | 5539067.05 | 27510719.69
South Helwan PP (CP-117) | 180064 |  | South Helwan PP (CP-117) | 108901.12 | 97377.06 | 17184.2 | 114561.26
Akhmem - Qena | Inv. 3 Akhmem Qena | 3 | Akhmem - Qena3 | 289210582.83 | 172080296.79 | 43381587.42 | 215461884.21
Beni Seuf - 358 | Inv No 1 Bani suef | 1 | Beni Seuf - 3581 | 19501875.06 | 15503384.65 | 2925281.26 | 18428665.91
Assuit PP (CP-118) | 2106210002 |  | Assuit PP (CP-118) | 138463.73 | 123578.88 | 21808.04 | 145386.92
Assuit PP (CP-118) | 2106210001 |  | Assuit PP (CP-118) | 5370.43 | 4793.11 | 845.84 | 5638.95
Assuit PP (CP-118) | 495 |  | Assuit PP (CP-118) | 148202.43 | 132270.66 | 23341.88 | 155612.54
Assuit PP (CP-118) | 1901210010 |  | Assuit PP (CP-118) | 268880.58 | 239975.92 | 42348.69 | 282324.61
Assuit PP (CP-118) | 2103210014 |  | Assuit PP (CP-118) | 2168386.48 | 0 | 0 | 2282512.08
Assuit PP (CP-118) | 2009210003 |  | Assuit PP (CP-118) | 1593564.06 | 1406314.56 | 250986.34 | 1657300.9
Assuit PP (CP-118) | 2110210004 |  | Assuit PP (CP-118) | 30111.96 | 31617.56 | 0 | 31617.56
Assuit PP (CP-118) | 2108210009 |  | Assuit PP (CP-118) | 12404.69 | 11036.19 | 1953.74 | 12989.93
Assuit PP (CP-118) | 2105210007 |  | Assuit PP (CP-118) | 37663.2345 | 39645.51 | 0 | 39645.51
Assuit PP (CP-118) | 523 |  | Assuit PP (CP-118) | 165215.06 | 147454.44 | 26021.37 | 173475.81
Al-Shabab PP Phase II (CP-117) | 180100 |  | Al-Shabab PP Phase II (CP-117) | 138618.98 | 123950.15 | 21873.56 | 145823.71
W Dam PP Phase II (CP-117) | 180098 |  | W Dam PP Phase II (CP-117) | 337817.97 | 302069.67 | 53306.41 | 355376.08
W Dam PP Phase II (CP-117) | 180096 |  | W Dam PP Phase II (CP-117) | 51479.85 | 46032.19 | 8123.33 | 54155.52
Al-Shabab PP Phase II (CP-117) | 180020 |  | Al-Shabab PP Phase II (CP-117) | 2020199.56 | 0 | 0 | 2020199.56
Al-Shabab PP Phase II (CP-117) | 13 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 225523.9143 | 201280.09 | 35520.02 | 236800.11
Al-Shabab PP Phase II (CP-117) | 12 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 329145.7714 | 293762.6 | 51840.46 | 345603.06
Al-Wukair 11 Substation | 180073 |  | Al-Wukair 11 Substation | 7641356.9 | 7641356.9 | 0 | 7641356.9
Marsa Matrouh 500KV | Inv.63- Borg Alarab | 63 | Marsa Matrouh 500KV63 | 8459991.43 | 7389805.4 | 888299.1 | 8278104.5
Marsa Matrouh 500KV | Inv.53 Borg Alarab | 53 | Marsa Matrouh 500KV53 | 9299425.66 | 6658395.6 | 976439.69 | 7634835.29
Marsa Matrouh 500KV | Inv.50 Borg Alarab | 50 | Marsa Matrouh 500KV50 | 1817057.14 | 1587202.93 | 190791 | 1777993.93
Marsa Matrouh 500KV | Inv.23 Borg Alarab | 23 | Marsa Matrouh 500KV23 | 898345.08 | 784710.53 | 94326.23 | 879036.76
Marsa Matrouh 500KV | Inv.21 Borg Alarab | 21 | Marsa Matrouh 500KV21 | 56450073.46 | 39368912.93 | 5927257.71 | 45296170.64
Marsa Matrouh 500KV | Inv.15 Borg Alarab | 15 | Marsa Matrouh 500KV15 | 255135895.46 | 222861206.65 | 26789269.02 | 249650475.67
Marsa Matrouh 500KV | Inv.13 Borg Alarab | 13 | Marsa Matrouh 500KV13 | 34848618.38 | 26978945.51 | 3659104.93 | 30638050.44
EMAAR-PKG#107-MARASSI | PKG#107-IPC (14) | 14 | EMAAR-PKG#107-MARASSI14 | 1449945.92 | 2534475.77 | 0 | 2534475.77
Kayan 3 New Cairo Capital City | IPC4-KAYAN FAINSHING | 4 | Kayan 3 New Cairo Capital City4 | 41958350 | 30076698.55 | 8000000 | 38076698.55
Beni Suef Substation R61 | 18100064 |  | Beni Suef Substation R61 | 6146056 | 4578811.72 | 921908.4 | 5500720.12
MAYSAN 400/132kV SS | 210 |  | MAYSAN 400/132kV SS | 11507875.67 | 22841165.14 | 0 | 11507875.67
Ismailiya East Substation | (6)cw elasmaaliya | 6 | Ismailiya East Substation6 | 653189 | 486625.8 | 97978.35 | 584604.15
Ministries Buildings | Minis Core IPC07 | 7 | Ministries Buildings7 | 8616849.02 | 1814815 | 5444475.65 | 7259290.65
Apache Electrical Works | 44649.31 |  | Apache Electrical Works | 44400.7 | 44400.7 | 0 | 44400.7
W Dam PP Phase II (CP-117) | 180037 |  | W Dam PP Phase II (CP-117) | 509875.4952 | 0 | 0 | 535369.27
Amal Bridge Lock & Load | (1)alamal lock&load | 1 | Amal Bridge Lock & Load1 | 6193188.7 | 5500870.85 | 0 | 5500870.85
Beni Suef Substation R61 | BSF-CW-IPC 7 | 7 | Beni Suef Substation R617 | 2536550 | 1919216.56 | 380482.5 | 2299699.06
Lina Farm Substation | 1 USD - Lina |  | Lina Farm Substation | 69591.61 | 69591.61 | 0 | 69591.61
Akhmem - Qena | Inv.9 Qena - Akhmem$ | 9 | Akhmem - Qena9 | 2103143.58 | 1785989.17 | 0 | 1785989.17
Abou El Matameer and Sammanoud | Inv.80Samanood 4 | 80 | Abou El Matameer and Sammanoud80 | 5875862.85 | 4250599.18 | 881379.43 | 5131978.61
Akhmem Assiut | Inv.1 Assuit Akhmem$ | 1 | Akhmem Assiut1 | 730800.55 | 284979.66 | 0 | 284979.66
Substation Elco Steel | PSP ELCO-IPC 03 | 3 | Substation Elco Steel3 | 2658220.39 | 1834172.07 | 531644.08 | 2365816.15
Akhmem Assiut | Inv.21 Assuit Akhmem | 21 | Akhmem Assiut21 | 8221653.7 | 6536214.69 | 1233248.06 | 7769462.75
Angola Emergency fast-track | Inv. No. 3 | 3 | Angola Emergency fast-track3 | 74095221.35 | 60981767.22 | 0 | 60981767.22
Mohamed Ali Palace Restoration | MOHAMED ALY-IPC02 | 2 | Mohamed Ali Palace Restoration2 | 878559.52 | 603154.4 | 193732.7 | 796887.1
Air Defense College | AIR DEFENSE IPC01 | 1 | Air Defense College1 | 178355894.3 | 25742460 | 39690270 | 139299631
Tunnel of Sokhna Road | SOKHNA TUNNEL-IPC1 | 1 | Tunnel of Sokhna Road1 | 40297018 | 17624309.3 | 2000000 | 36090216.3
South Helwan PP (CP-117) | Commercial fees SH |  | South Helwan PP (CP-117) | 108518.8 | 108518.8 | 0 | 108518.8
Akhmem - Qena | Inv.10 Qena- Akhmem$ | 10 | Akhmem - Qena10 | 2008306.86 | 1705453.33 | 0 | 1705453.33
Akhmem - Qena | Inv.34 Akhmem Qena | 34 | Akhmem - Qena34 | 3086479.32 | 1527278.57 | 462971.9 | 1990250.47
Abou El Matameer and Sammanoud | 01042018 |  | Abou El Matameer and Sammanoud | 7920883.43 | 5729967.07 | 1188132.52 | 6918099.59
Badr | Inv.1-2 Project Badr | 1 | Badr1 | 35625269.15 | 11608780.25 | 5343790.4 | 16952570.65
P-28-16 Balat Owinat Lot 3 | Inv. 13 Balat lot 3 | 13 | P-28-16 Balat Owinat Lot 313 | 20489981.23 | 13133684 | 2151448.03 | 15285132.03
P-28-16 Balat Owinat Lot 3 | Inv. 11 Balat lot 3 | 11 | P-28-16 Balat Owinat Lot 311 | 22018272.86 | 16447258.48 | 2311918.65 | 18759177.13
P-28-16 Balat Owinat Lot 3 | Inv. 8 | 8 | P-28-16 Balat Owinat Lot 38 | 19805695.33 | 14794457.87 | 2079598.01 | 16874055.88
P-28-16 Balat Owinat Lot 3 | Inv. 4 Balat lot 3 | 4 | P-28-16 Balat Owinat Lot 34 | 6449395.47 | 4817309.13 | 677186.52 | 5494495.65
Sodic Club House | SODIC CLUB-IPC 32 | 32 | Sodic Club House32 | 6867125.7 | 1852842.635 | 693560.3 | 2546402.935
Elsewedy Univ - Enabling Works | ELSEWEDY MEP-IPC05 | 5 | Elsewedy Univ - Enabling Works5 | 8018043.81 | 4527299.6805 | 1589066.44 | 6116366.1205
Elsewedy Univ - Enabling Works | ELSEWEDY UNI- IPC06 | 6 | Elsewedy Univ - Enabling Works6 | 339719.88 | 235901.484 | 107011.76 | 342913.244
Elsewedy Univ - Enabling Works | 19100031 |  | Elsewedy Univ - Enabling Works | 267331.59 | 185635.0495 | 84209.45 | 269844.4995
Elsewedy Univ - Enabling Works | 19100030 |  | Elsewedy Univ - Enabling Works | 5121900.87 | 3208255.7535 | 1075599.18 | 4283854.9335
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-MEP-03 | 3 | Elsewedy Univ - Enabling Works3 | 4458365.84 | 3212953.442 | 936256.83 | 4149210.272
Akhmem Assiut | Inv.11Assuit Akhmem$ | 11 | Akhmem Assiut11 | 3279975.01 | 2771864 | 0 | 2771864
Bani Suef Old Substation | bani suif 2-ipc 28 | 28 | Bani Suef Old Substation28 | 1803926.68 | 1720326.28 | 0 | 1720326.28
EMAAR-PKG#53-UPTOWN | PKG#53 -IPC 35 | 35 | EMAAR-PKG#53-UPTOWN35 | 3328558.25 | 2331143.99 | 0 | 2331143.99
Ministries Buildings | MinisLandscape IPC05 | 5 | Ministries Buildings5 | 5135274.68 | 2197700 | 2197690 | 4395390
Hassan El Mamoun Bridge | Hassan Mamoun Final |  | Hassan El Mamoun Bridge | 4216610.86 | 5441365.003 | 1875138.85 | 7316503.853
Mohamed Ali Palace Restoration | PO - Mohamed Aly 105 |  | Mohamed Ali Palace Restoration | 483986.35 | 343355 | 114455.7 | 457810.7
Mohamed Ali Palace Restoration | PO - Mohamed Aly 114 |  | Mohamed Ali Palace Restoration | 483236.15 | 342825 | 114277.5 | 457102.5
Baron Fence | ELBARON-IPC FINAL |  | Baron Fence | 3562756.1 | 2033350 | 2033370 | 4066720
Akhmem Assiut | ref.soci12-16 Assuit | 16 | Akhmem Assiut16 | 2232266.01 | 2232266.01 | 0 | 2232266.01
New Capital Tunnels | M.B.Z.TUNNEL IPC 4 | 4 | New Capital Tunnels4 | 11676873.05 | 3408205.8 | 1115000 | 9937980.8
Marsa Matrouh 500KV | Inv.1 Borg Alarab | 1 | Marsa Matrouh 500KV1 | 128259940.46 | 128259940.46 | 0 | 128259940.46
Akhmem - Qena | Inv.23 Qena- Akhmem$ | 23 | Akhmem - Qena23 | 122979.52 | 103749.29 | 0 | 103749.29
Canal Regional Control Center | Inv.8 Rcc | 8 | Canal Regional Control Center8 | 7912822.95 | 4478650.2 | 1661692.82 | 6140343.02
Canal Regional Control Center | Inv.5 Rcc | 5 | Canal Regional Control Center5 | 14317304.05 | 8102976.37 | 3006633.85 | 11109610.22
Badr | Inv. 2 Badr | 2 | Badr2 | 13460693.5 | 9994146.6 | 2019104.05 | 12013250.65
Tamey El-amdeed Substation | TAM-CW-EGP-06 | 6 | Tamey El-amdeed Substation6 | 2763337.82 | 2058686.68 | 414500.67 | 2473187.35
Beni Suef Substation R61 | 2cw bine suif |  | Beni Suef Substation R61 | 10571146.54 | 7913165.95 | 1585671.98 | 9498837.93
Akhmem - Qena | Inv.44 Qena Akhmem | 44 | Akhmem - Qena44 | 803265.02 | 558269.19 | 120489.75 | 678758.94
Akhmem Assiut | Inv.37 Assuit Akhmem | 37 | Akhmem Assiut37 | 8582153.7 | 6822812.19 | 1287323.06 | 8110135.25
P-28-16 Balat Owinat Lot 2 | Inv. 15 Balat Lot 2 | 15 | P-28-16 Balat Owinat Lot 215 | 3764174.84 | 2980834.24 | 0 | 2980834.24
Akhmem Assiut | Inv.10Assuit Akhmem$ | 10 | Akhmem Assiut10 | 3251534.26 | 2741835.94 | 0 | 2741835.94
P-28-16 Balat Owinat Lot 2 | Inv. 4 Balat Lot 2 | 4 | P-28-16 Balat Owinat Lot 24 | 6749613.52 | 5041564.14 | 708709.42 | 5750273.56
P-28-16 Balat Owinat Lot 2 | Inv. 1 Balat Lot 2 | 1 | P-28-16 Balat Owinat Lot 21 | 35668193.1 | 26643741.23 | 3745160.5 | 30388901.73
Marsa Matrouh 500KV | Inv10 Usd borg alarb | 10 | Marsa Matrouh 500KV10 | 5555561.09 | 4606754.58 | 555556.11 | 5426861.22
K047 FDH JV | Inv. No.10 KWD Floor | 10 | K047 FDH JV10 | 25274.2 | 22746.78 | 0 | 22746.78
Abou El Matameer and Sammanoud | Inv 94P9Abo Matami | 94 | Abou El Matameer and Sammanoud94 | 3180991.96 | 2285224.62 | 477148.79 | 2762373.41
Akhmem - Qena | Inv.3 Qena - Akhmem$ | 3 | Akhmem - Qena3 | 1801897.56 | 1515450.87 | 0 | 1515450.87
South Helwan PP (CP-117) | 180141 |  | South Helwan PP (CP-117) | 200061.46 | 208603.47 | 0 | 208603.47
Beni Suef Substation R61 | BSF-SW-05 | 5 | Beni Suef Substation R615 | 725375 | 539875.47 | 108806.25 | 648681.72
Manshiet Nasser Substation | 180171 |  | Manshiet Nasser Substation | 908445.29 | 953867.56 | 0 | 953867.56
South Helwan PP (CP-117) | 180148 |  | South Helwan PP (CP-117) | 233646.38 | 244575.79 | 0 | 244575.79
Akhmem Assiut | Inv.21Assuit Akhmem$ | 21 | Akhmem Assiut21 | 418013.32 | 290171.67 | 0 | 290171.67
Akhmem Assiut | Inv.18Assuit Akhmem$ | 18 | Akhmem Assiut18 | 1405814.84 | 1187878.74 | 0 | 1187878.74
NUCA R05 - Z02 | R05 IPC#032 | 32 | NUCA R05 - Z0232 | 8394775.5 | 0 | 805622.55 | 805622.55
NUCA R05 - Z02 | R5-IPC23 | 23 | NUCA R05 - Z0223 | 88626920.85 | 72093367.1 | 9076871.1 | 81170238.2
AWEER POWER STATION 'H' Phase | LOC 027 |  | AWEER POWER STATION 'H' Phase | 8676.56 | 0 | 964.06 | 964.06
AWEER POWER STATION 'H' Phase | LOC/019 |  | AWEER POWER STATION 'H' Phase | 816011.56 | 716276.81 | 90667.95 | 806944.76
AWEER POWER STATION 'H' Phase | LOC/017 |  | AWEER POWER STATION 'H' Phase | 2594016.68 | 2276970.19 | 288224.08 | 2565194.27
AWEER POWER STATION 'H' Phase | CON/021 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
AWEER POWER STATION 'H' Phase | IMP-055 | 55 | AWEER POWER STATION 'H' Phase55 | 1524830.95 | 1507601.2245 | 0 | 1507601.2245
AWEER POWER STATION 'H' Phase | IMP-052 | 52 | AWEER POWER STATION 'H' Phase52 | 554585.89 | 553663.02 | 0 | 553663.02
AWEER POWER STATION 'H' Phase | IMP-037prog for33/34 | 37 | AWEER POWER STATION 'H' Phase37 | 10012746.61 | 8788966.4705 | 1112527.4 | 9901493.8705
AWEER POWER STATION 'H' Phase | 10387 |  | AWEER POWER STATION 'H' Phase | 4152520.61 | 3644990.3105 | 461391.18 | 4106381.4905
AWEER POWER STATION 'H' Phase | 10370 |  | AWEER POWER STATION 'H' Phase | 1916547.97 | 1682303.2085 | 212949.78 | 1895252.9885
Kayan 3 New Cairo Capital City | KAYAN SIHY-IPC 1 | 1 | Kayan 3 New Cairo Capital City1 | 3060785 | 1998988.35 | 450000 | 2448988.35
EDNC Retail & Offices Civil | SOREAL-IPC12 | 12 | EDNC Retail & Offices Civil12 | 33309635.84 | 24940111.3195 | 6343196.86 | 31283308.1795
EDNC Retail & Offices Civil | SOREAL-IPC11 | 11 | EDNC Retail & Offices Civil11 | 36710088.58 | 29504362.289 | 1807968.97 | 31312331.259
EDNC Retail & Offices Civil | soreal - ipc 02 | 2 | EDNC Retail & Offices Civil2 | 20887437.31 | 15638373.6555 | 4386361.84 | 20024735.4955
SHATRA 400/132kV SS | 213 |  | SHATRA 400/132kV SS | 6339895.72 | 6339895.72 | 0 | 6339895.72
Tamey El-amdeed Substation | TAM-SD-EGP-03 | 3 | Tamey El-amdeed Substation3 | 648000 | 479520 | 97200 | 576720
South Helwan PP (CP-117) | 180150 |  | South Helwan PP (CP-117) | 791434.01 | 897916.35 | 0 | 897916.35
EMAAR-PKG# 144, Marassi | PKG#144- IPC04 | 4 | EMAAR-PKG# 144, Marassi4 | 11222644.64 | 6887337.022 | 3535133.06 | 10422470.082
Al Mostathmreen GIS Substation | MOS-SD-EURO-13 | 13 | Al Mostathmreen GIS Substation13 | 209034.12 | 3735409.96 | 31355.12 | 3766765.08
Tamey El-amdeed Substation | 19100019 |  | Tamey El-amdeed Substation | 2369397.12 | 1753353.87 | 355409.57 | 2108763.44
Asec Spare-Parts | Inv 3 EUR Asec Spare | 3 | Asec Spare-Parts3 | 5090 | 3797 | 1601.2 | 5398.2
DPW Onshore Port & Terminal | DPW IPC031 | 31 | DPW Onshore Port & Terminal31 | 13597917.63 | 10014939.05 | 2039687.64 | 12054626.69
DPW Onshore Port & Terminal | DP World IPC026 | 26 | DPW Onshore Port & Terminal26 | 30564756.18 | 22617919.57 | 4584713.43 | 27202633
Akhmem - Qena | Soc Inv 42-43-44Quna | 42 | Akhmem - Qena42 | 574975.25 | 574975.25 | 0 | 574975.25
Akhmem - Qena | Ref Soc Inv 25 quna | 25 | Akhmem - Qena25 | 91566.75 | 91566.75 | 0 | 91566.75
Marsa Matrouh 500KV | Inv.17Usd borg alarb | 17 | Marsa Matrouh 500KV17 | 332662 | 289440.57 | 34929.51 | 324370.08
Marsa Matrouh 500KV | Inv.11 Borg Alarab | 11 | Marsa Matrouh 500KV11 | 1466699.73 | 1232282.51 | 154003.47 | 1386285.98
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC05 | 5 | Elsewedy Univ - Enabling Works5 | 18231859.57 | 121094303.2925 | 27208425.8 | 29660545.8185
Tamey El-amdeed Substation | 19100027 |  | Tamey El-amdeed Substation | 734564.04 | 543577.39 | 110184.61 | 653762
Akhmem Assiut | Inv.40 Assuit Akhmem | 40 | Akhmem Assiut40 | 3239324.7 | 2545198.51 | 485898.71 | 3031097.22
Akhmem Assiut | Inv.46 Assuit Akhmem | 46 | Akhmem Assiut46 | 2857281.59 | 2000097.1 | 428592.24 | 2428689.34
Akhmem Assiut | Inv.20Assuit Akhmem$ | 20 | Akhmem Assiut20 | 1244034.52 | 1030051.79 | 0 | 1030051.79
Akhmem - Qena | Inv.7 Qena - Akhmem$ | 7 | Akhmem - Qena7 | 1482882.32 | 1259261.66 | 0 | 1259261.66
Flour project | 10077 |  | Flour project | 36786 | 36786 | 0 | 36786
RME- Marassi Sidi Abdel Rahman | Sales-03 | 3 | RME- Marassi Sidi Abdel Rahman3 | 150000 | 150000 | 0 | 150000
MOTHANA 400/132kV SS | 211 |  | MOTHANA 400/132kV SS | 6708419.33 | 6708419.33 | 0 | 6708419.33
kayan wall lock & Load | KAYAN LOAK&LOAD-IPC7 | 7 | kayan wall lock & Load7 | 9270000 | 2718297 | 5647472.9 | 8365769.9
Kayan 3 New Cairo Capital City | KAYAN SAHY- IPC02 | 2 | Kayan 3 New Cairo Capital City2 | 6155815 | 1804764 | 3750450 | 5555214
Royal City | ROYAL CITY-IPC15 | 15 | Royal City15 | 8723893.09 | 6570751.8245 | 2830535.65 | 9401287.4745
Beni Suef Substation R61 | BSF-CW-EURO-05 | 5 | Beni Suef Substation R615 | 4505119.11 | 3356313.73 | 675767.87 | 4032081.6
New Capital | Inv. 8 Abo Zabal | 8 | New Capital8 | 1565685.9 | 905936.5 | 164397.02 | 1070333.52
Beni Suef Substation R61 | 19100025 |  | Beni Suef Substation R61 | 202562 | 149895.88 | 30384.3 | 180280.18
Al-Wukair 11 Substation | 1902210007 |  | Al-Wukair 11 Substation | 5694082.79 | 5694082.79 | 0 | 5694082.79
EMAAR-PKG117- MARASSI | PKG#117 -IPC 10 | 10 | EMAAR-PKG117- MARASSI10 | 1067786.52 | 938354.286 | 112117.59 | 1050471.876
Manshiet Nasser Substation | 2011210002 |  | Manshiet Nasser Substation | 12360.29 | 2658.44 | 1854.04 | 4512.48
Manshiet Nasser Substation | 2001210005 |  | Manshiet Nasser Substation | 1090204.98 | 819235.17 | 175467.3 | 994702.47
Manshiet Nasser Substation | 545 |  | Manshiet Nasser Substation | 321701.84 | 241745.72 | 51777.56 | 293523.28
Manshiet Nasser Substation | 506 |  | Manshiet Nasser Substation | 401551.96 | 119347.17 | 60232.79 | 179579.96
Manshiet Nasser Substation | 488 |  | Manshiet Nasser Substation | 966716.73 | 792055.07 | 156470.55 | 948525.62
Manshiet Nasser Substation | 1908210016 |  | Manshiet Nasser Substation | 1206654.4 | 848817.86 | 194209.7 | 1043027.56
Manshiet Nasser Substation | 1908210015 |  | Manshiet Nasser Substation | 242625.47 | 114459.02 | 39050.3 | 153509.32
Manshiet Nasser Substation | 180175 |  | Manshiet Nasser Substation | 1243908.62 | 1168963.12 | 137140.93 | 1306104.05
Manshiet Nasser Substation | 180167 |  | Manshiet Nasser Substation | 968498.97 | 910146.91 | 106777.01 | 1016923.92
Manshiet Nasser Substation | 180177 |  | Manshiet Nasser Substation | 437296.6 | 371702.11 | 65594.49 | 437296.6
Military 110 Kayan Project | Elkayan Inv.16 | 16 | Military 110 Kayan Project16 | 3660653.12 | 3303334.3 | 0 | 3303334.3
Manshiet Nasser Substation | 2004210013 |  | Manshiet Nasser Substation | 27280.96 | 20306.88 | 4307.52 | 24614.4
Manshiet Nasser Substation | 505 |  | Manshiet Nasser Substation | 153924.49 | 0 | 23088.67 | 23088.67
El Mostakbal City Project | Inv. 3 Mostakbal | 3 | El Mostakbal City Project3 | 5587780.17 | 4637139.7 | 1173433.84 | 5810573.54
Akhmem Assiut | Inv.22 Assuit Akhmem | 22 | Akhmem Assiut22 | 9922685.59 | 7888535.04 | 1488402.84 | 9376937.88
Beni Seuf - 358 | Inv.5 kafr zeat itay | 5 | Beni Seuf - 3585 | 67332375 | 53128795.9 | 10163025 | 63291820.9
Beni Seuf - 358 | Insu. inv.3 itay 358 | 3 | Beni Seuf - 3583 | 1009906 | 1004770.86 | 0 | 1004770.86
Abou El Matameer and Sammanoud | Inv100 P12- Sammound | 100 | Abou El Matameer and Sammanoud100 | 4186152.58 | 3007332 | 627922.89 | 3635254.89
EMAAR-PKG# 144, Marassi | pkg#144-IPC11 | 11 | EMAAR-PKG# 144, Marassi11 | 8979474.51 | 7386054.95 | 924705.34 | 8310760.29
EMAAR-PKG# 144, Marassi | PKG#144-IPC-02 | 2 | EMAAR-PKG# 144, Marassi2 | 4125990.87 | 2748735.1235 | 1299687.12 | 4048422.2435
Cameron EDC | 009/2019 |  | Cameron EDC | 193370.11 | 188146.27 | 0 | 188146.27
NUCA R05 - Z02 | R5-ZONE 2-IPC 01 | 1 | NUCA R05 - Z021 | 69830383.75 | 67099356.65 | 8271331.91 | 75370688.56
New Capital | Inv. 7 Eltbeen | 7 | New Capital7 | 1754884.33 | 1320021.28 | 138268.58 | 1458289.86
Assuit PP (CP-118) | 1902210003 |  | Assuit PP (CP-118) | 72541.64 | 64743.41 | 11425.31 | 76168.72
Assuit PP (CP-118) | 1902210002 |  | Assuit PP (CP-118) | 74364.24 | 66370.08 | 11712.37 | 78082.45
MOTHANA 400/132kV SS | 223 |  | MOTHANA 400/132kV SS | 1045788.16 | 1045788.16 | 0 | 1045788.16
4 SS - Technical Service | 226 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Kuwait | Civil/J011 |  | Kuwait | 38063.33 | 28547.5 | 0 | 28547.5
Development of Mahmudiyah axis | IPC#3 | 3 | Development of Mahmudiyah axis3 | 1372500 | 1334070 | 0 | 1334070
EDNC Retail & Offices Civil | SOREAL- IPC 01 | 1 | EDNC Retail & Offices Civil1 | 9063098.33 | 6789620.1165 | 1903250.65 | 8692870.7665
Bani Suef Old Substation | (27)bini suif 2 | 27 | Bani Suef Old Substation27 | 2949400.18 | 2738736.37 | 0 | 2738736.37
Substation Elco Steel | PSPELCO-IPC09 | 9 | Substation Elco Steel9 | 1904763.72 | 1314286.96 | 380952.74 | 1695239.7
Badr | Inv. 10 Badr | 10 | Badr10 | 106542720 | 79107431.75 | 15981408 | 95088839.75
EMAAR-PKG#22-MARASSI | (36) PKG#22 | 36 | EMAAR-PKG#22-MARASSI36 | 150622 | 739720.27 | 15499.05 | 755219.32
SHATRA 400/132kV SS | 231 |  | SHATRA 400/132kV SS | 503921.87 | 503921.87 | 0 | 503921.87
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC03 | 3 | EMAAR-PKG# 101-UPTOWN3 | 3744391.54 | 2222206.627 | 1179483.34 | 3401689.967
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 34 | 34 | Benban 500 K.V/95 K.M34 | 10623483.11 | 8190712.81 | 1115465.73 | 9306178.54
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 15 | 15 | Benban 500 K.V/95 K.M15 | 21346551.17 | 16458190 | 2241387.87 | 18699577.87
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 32 | 32 | Benban 500 K.V / 100 K.M32 | 2736724.03 | 2110014.74 | 287356.02 | 2397370.76
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 17 | 17 | Benban 500 K.V / 100 K.M17 | 85828107.45 | 69189323.23 | 9011951.28 | 78201274.51
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 30 | 30 | Benban 500 K.V / 100 K.M30 | 4207664.99 | 3244109.7 | 441804.82 | 3685914.52
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 22 | 22 | Benban 500 K.V / 100 K.M22 | 40851099.66 | 28496201.74 | 4289365.46 | 32785567.2
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 27 | 27 | Benban 500 K.V / 100 K.M27 | 294497.14 | 227064.76 | 30922.2 | 257986.96
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 25 | 25 | Benban 500 K.V / 100 K.M25 | 3537359.2 | 2727310.16 | 371422.72 | 3098732.88
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 5 | 5 | Benban 500 K.V / 100 K.M5 | 705434.09 | 543896.58 | 74070.58 | 617967.16
Ismailiya East Substation | ISE-CW-EGP-14 | 14 | Ismailiya East Substation14 | 1815042 | 1343131.08 | 272256.3 | 1615387.38
Ismailiya East Substation | ISE-CW-EGP-15 | 15 | Ismailiya East Substation15 | 5774580 | 4273189.2 | 866187 | 5139376.2
Abou El Matameer and Sammanoud | Soci. 16 Fin. Matmer |  | Abou El Matameer and Sammanoud | 90443 | 90442.81 | 0 | 90442.81
Canal Sugar OHTL | Inv.08 Sugar OHTL | 8 | Canal Sugar OHTL8 | 2463262.79 | 412075.77 | 369489.42 | 781565.19
Marsa Matrouh 500KV | Inv.27 Borg Alarab | 27 | Marsa Matrouh 500KV27 | 25596171.43 | 22358260.29 | 2687598 | 25045858.29
Elco Steel 220/33 KV SS | 1901210015 |  | Elco Steel 220/33 KV SS | 4884581.7 | 5128810.79 | 0 | 5128810.79
Elco Steel 220/33 KV SS | 1901210006 |  | Elco Steel 220/33 KV SS | 2473969.04 | 2597667.49 | 0 | 2597667.49
Substation Elco Steel | PSP ELCO-IPC10 | 10 | Substation Elco Steel10 | 4730762.03 | 3744490.63 | 946152.41 | 4690643.04
Elsewedy Univ - Enabling Works | UNI-FIN&MEP-IPC10 | 10 | Elsewedy Univ - Enabling Works10 | 30617684.7 | 20919758.826 | 5586427.55 | 26506186.376
MOTHANA 400/132kV SS | 236 |  | MOTHANA 400/132kV SS | 568086.84 | 568086.84 | 0 | 568086.84
Manshiet Nasser Substation | 1904210016 |  | Manshiet Nasser Substation | 551062.32 | 468402.97 | 82659.35 | 551062.32
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 1USD | 1 | Benban 500 K.V / 100 K.M1 | 571610.74 | 480153.02 | 60019.13 | 540172.15
SHAT Al ARAB 400/132kV SS | 230 |  | SHAT Al ARAB 400/132kV SS | 673168.29 | 666703.01 | 0 | 673168.29
MOTHANA 400/132kV SS | 234 |  | MOTHANA 400/132kV SS | 547002.82 | 547002.82 | 0 | 547002.82
Manshiet Nasser Substation | 180174 |  | Manshiet Nasser Substation | 1718539.45 | 1787279.9 | 0 | 1787279.9
Royal City | ROYAL CITY-IPC35 | 35 | Royal City35 | 6572349.74 | 2752213.4436 | 1237553.21 | 3989766.6536
Royal City | ROYAL ZONE2-IPC18 | 18 | Royal City18 | 1609316.03 | 1107014.8815 | 299495.48 | 1406510.3615
Cairo Capital S1 | Inv. 7 Project S 1 | 7 | Cairo Capital S17 | 101859241.52 | 76648660.65 | 15278894.25 | 91927554.9
Amal Bridge Lock & Load | AMAL LOCK&LOAD-FINAL |  | Amal Bridge Lock & Load | 1991284.16 | 1257449.1 | 948500 | 2205949.1
Cairo Capital S1 | Inv. 6 Project S 1 | 6 | Cairo Capital S16 | 120888968.38 | 90968547.85 | 18133345.26 | 109101893.11
EDNC Retail & Offices Civil | SOREAL-IPC04 | 4 | EDNC Retail & Offices Civil4 | 36280262.26 | 26537436.313 | 9089929.31 | 35627365.623
Zambia Project | SCD4/003Adj |  | Zambia Project | 96528.24 | 0 | 0 | 96528.24
Port Said Subs 220/66 | Port Said Inv. 4 | 4 | Port Said Subs 220/664 | 39009058.49 | 25160420 | 9752264.62 | 34912684.62
Port Said Subs 220/66 | Adv.CR. Port Said |  | Port Said Subs 220/66 | 0 | 0 | -5500000 | -5500000
Akhmem Assiut | Inv.9 Assuit Akhmem | 9 | Akhmem Assiut9 | 28602698.23 | 17018605.45 | 4290404.73 | 21309010.18
Akhmem Assiut | Inv.8 Assuit Akhmem | 8 | Akhmem Assiut8 | 39473811.19 | 23486917.65 | 5921071.68 | 29407989.33
Badr | Inv. 13 Badr | 13 | Badr13 | 19087247 | 14171862.65 | 2863087.05 | 17034949.7
AWEER POWER STATION 'H' Phase | 10127 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
Elsewedy Univ - Enabling Works | uni fi&mep-ipc 07 | 7 | Elsewedy Univ - Enabling Works7 | 35759955.8 | 37410862.9635 | 6397823 | 43808685.9635
Assuit PP (CP-118) | 1907210002 |  | Assuit PP (CP-118) | 184213.03 | 164410.13 | 29013.55 | 193423.68
Cameron EDC | 021/2019 |  | Cameron EDC | 126058.47 | 125908.06 | 0 | 125908.06
MAYSAN 400/132kV SS | 248 |  | MAYSAN 400/132kV SS | 159025.9 | 159025.9 | 0 | 159025.9
Akhmem - Qena | Inv.35 Akhmem Qena | 35 | Akhmem - Qena35 | 394117 | 273911.31 | 59117.55 | 333028.86
Elco Steel 220/33 KV SS | 1908210005 |  | Elco Steel 220/33 KV SS | 364073.7 | 382277.38 | 0 | 382277.38
Suez IPB | 2*4 EGP - Suez Steel |  | Suez IPB | 10535.48 | 10535.48 | 0 | 10535.48
MAYSAN 400/132kV SS | 256 |  | MAYSAN 400/132kV SS | 252646.56 | 252646.56 | 0 | 252646.56
4 SS - Technical Service | 262 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Latin Quarter- New Alamein | inv ( 3 ) 23-5-2021 | 3 | Latin Quarter- New Alamein3 | 9566707.5 | 3832849.47 | 0 | 3832849.47
Latin Compound - New Alamin | INV(12)310520 | 12 | Latin Compound - New Alamin12 | 222020.4 | 185272.25 | 0 | 185272.25
Neighborhood New Capital R5 | inv ( 1 ) 21-12-2020 | 1 | Neighborhood New Capital R51 | 7790560 | 6219826.36 | 0 | 6219826.36
LAYYAH CCPP | 510 |  | LAYYAH CCPP | 4935294 | 4194999.9 | 740294.1 | 4935294
LAYYAH CCPP | 503 |  | LAYYAH CCPP | 335375 | 299322.19 | 50306.25 | 349628.44
DoubleTree Mangroovy ElGouna | MANGROVE-IPC09 | 9 | DoubleTree Mangroovy ElGouna9 | 1505090.04 | 1030964.272 | 395086.14 | 1426050.412
DoubleTree Mangroovy ElGouna | MANGROVE-IPC08 | 8 | DoubleTree Mangroovy ElGouna8 | 2806757.16 | 1896543.798 | 736773.76 | 2633317.558
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 5 | 5 | Benban 500 K.V/95 K.M5 | 2486577.93 | 1917150.79 | 261090.68 | 2178241.47
Beni Suef Substation R61 | BSF-SW-EGP-10 | 10 | Beni Suef Substation R6110 | 74375 | 55037.5 | 11156.25 | 66193.75
EMAAR-PKG# 101-UPTOWN | PKG#101- IPC12 | 12 | EMAAR-PKG# 101-UPTOWN12 | 361420.4 | 1829340.96 | 716279.53 | 2545620.49
MAYSAN 400/132kV SS | 247 |  | MAYSAN 400/132kV SS | 1403399.06 | 2806798.12 | 0 | 1403399.06
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 4 | 4 | Benban 500 K.V / 100 K.M4 | 56869419.86 | 43846329.48 | 5971289.09 | 49817618.57
Tamey El-amdeed Substation | TAM-SW-EGP-08 | 8 | Tamey El-amdeed Substation8 | 843500 | 348952.51 | 126525 | 475477.51
Canal Sugar 33KV OHTL | Inv. 1 Sugar 33 OHTL | 1 | Canal Sugar 33KV OHTL1 | 9703293.36 | 7665601.76 | 1455494 | 9121095.76
33KV Canal Farm Grid | Inv. 10 Farm | 10 | 33KV Canal Farm Grid10 | 535000 | 408205 | 80250 | 488455
EMAAR-PKG#53-UPTOWN | PKG#53 - IPC40 | 40 | EMAAR-PKG#53-UPTOWN40 | 51326.53 | 11242137.74 | 0 | 11242137.74
P-28-16 Balat Owinat Lot 2 | Inv. 12 Balat Lot 2 | 12 | P-28-16 Balat Owinat Lot 212 | 15855149.71 | 11843405.414 | 1664790.72 | 13508196.134
Alamein | ELALAMEEN ROAD-IPC01 | 1 | Alamein1 | 20204000 | 17014223.5 | 0 | 17976318.74
Benban 500 K.V/95 K.M | Benban Lot2 Inv 6 $ | 6 | Benban 500 K.V/95 K.M6 | 67461.72 | 56667.85 | 7083.48 | 63751.33
Mohamed Aly Fahmy Lock&Load | M.ALY FAHMY L&L-01 | 1 | Mohamed Aly Fahmy Lock&Load1 | 6313890 | 1660170 | 3652219 | 5312389
Benban 500 K.V/95 K.M | Benban Lot2 Inv 3 $ | 3 | Benban 500 K.V/95 K.M3 | 144197.92 | 121126.26 | 15140.78 | 136267.04
LAYYAH CCPP | 524 |  | LAYYAH CCPP | 9521850 | 0 | 2268593 | 2268593
LAYYAH CCPP | 513 |  | LAYYAH CCPP | 4411860 | 4171455 | 240405 | 4411860
LAYYAH CCPP | 499 |  | LAYYAH CCPP | 12854700 | 11387526.75 | 2046725 | 13434251.75
LAYYAH CCPP | 498 |  | LAYYAH CCPP | 10283760 | 8700880.65 | 1997207 | 10698087.65
LAYYAH CCPP | 487 |  | LAYYAH CCPP | 6538440 | 6483455 | 54985 | 6538440
Ghana Street lighting | MIDA Ins. Inv. 2 | 2 | Ghana Street lighting2 | 181312.03 | 181312.03 | 0 | 181312.03
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 11 | 11 | Benban 500 K.V / 100 K.M11 | 922953 | 711005.11 | 96910.07 | 807915.18
Nuweibaa (Swro) | Invoice No:11 |  | Nuweibaa (Swro) | 846941.68 | 677553.344 | 169388.336 | 846941.68
Nuweibaa (Swro) | 2002210001 |  | Nuweibaa (Swro) | 57926.6 | 46341.28 | 11585.32 | 57926.6
Beni-Suef Power Plant EPC | reclass rec 1020 |  | Beni-Suef Power Plant EPC | 986446760.8 | 535100901.48 | 0 | 986446760.8
Oasis Buildings- New Capital | Inv(2)090120 | 2 | Oasis Buildings- New Capital2 | 40551.6 | 33601.19 | 0 | 33601.19
Beni Suef Add-on Sales | 1908210010 |  | Beni Suef Add-on Sales | 381712.08 | 423700.34 | 0 | 423700.34
Olympic Multi – Sports Hall | OLYMPIC-IPC01 | 1 | Olympic Multi – Sports Hall1 | 155024274.9 | 3412855 | 65687110.54 | 134650985.79
Assuit PP (CP-118) | 494 |  | Assuit PP (CP-118) | 212481.68 | 189639.9 | 33465.86 | 223105.76
Celia | IPC#2 | 2 | Celia2 | 611543.5 | 558339.21 | 0 | 573540.4357
R5 Mix-Use Complex Project | R5-ZONE1-IPC08 | 8 | R5 Mix-Use Complex Project8 | 1463610.7 | 1229663.885 | 152720.23 | 1382384.115
Marsa Matrouh 500KV | Inv.44 Borg Alarab | 44 | Marsa Matrouh 500KV44 | 32018947.4 | 15966147.8 | 3361989.48 | 19328137.28
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 21 | 21 | Benban 500 K.V/95 K.M21 | 430790.51 | 332140.6 | 45233 | 377373.6
33KV Canal Farm Grid | Inv. 01 Farm | 1 | 33KV Canal Farm Grid1 | 31513076.75 | 24895153.72 | 4726961.51 | 29622115.23
Canal Sugar OHTL | Inv.03 Sugar OHTL | 3 | Canal Sugar OHTL3 | 27741223.11 | 21915566.26 | 4161183.47 | 26076749.73
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 24 | 24 | Benban 500 K.V/95 K.M24 | 7600808.43 | 5859632.23 | 798084.89 | 6657717.12
Sewage Treatment Plant | IPC#1 | 1 | Sewage Treatment Plant1 | 518585 | 0 | 0 | 518585
Lock&Load-30June w Sokhna Rd | 30YU GALALA-L&L-1FIN | 1 | Lock&Load-30June w Sokhna Rd1 | 1030928 | 454415 | 454429.05 | 908844.05
Ministries Buildings | MIN.ALLOCATION-IPC03 | 3 | Ministries Buildings3 | 9291713.23 | 1741265 | 6179524.33 | 7920789.33
Ministries Buildings | MINISTIRY OLD-IPC03 | 3 | Ministries Buildings3 | 20267785 | 35295710 | 7760638.6 | 43940248.6
Suez Gulf Substation | 486 |  | Suez Gulf Substation | 43989.39 | 41648.17 | 4627.57 | 46275.74
R5 | inv(4)101219 | 4 | R54 | 7087635 | 583758.67 | 0 | 1391663.81
DoubleTree Mangroovy ElGouna | MANGOROVE RENT-IPC01 | 1 | DoubleTree Mangroovy ElGouna1 | 80875 | 73813.1925 | 0 | 73813.1925
NUCA R05 - Z02 | R5-IPC10 | 10 | NUCA R05 - Z0210 | 26640996.55 | 23900162.4 | 2954891.2 | 26855053.6
Assuit PP (CP-118) | 511 |  | Assuit PP (CP-118) | 262453.06 | 234239.35 | 41336.36 | 275575.71
Elco Steel 220/33 KV SS | 1906210003 |  | Elco Steel 220/33 KV SS | 17487.27 | 17487.27 | 0 | 17487.27
Elco Steel 220/33 KV SS | 1903210008 |  | Elco Steel 220/33 KV SS | 1530321.21 | 1606837.27 | 0 | 1606837.27
SHAT Al ARAB 400/132kV SS | 282 |  | SHAT Al ARAB 400/132kV SS | 757999.5 | 757999.5 | 0 | 757999.5
EDNC Retail & Offices Civil | SOREAL -IPC09 | 9 | EDNC Retail & Offices Civil9 | 19102003.8 | 40883545.558 | 12988267.08 | 53871812.638
Akhmem Assiut | Inv.24Assuit Akhmem$ | 24 | Akhmem Assiut24 | 357869.09 | 304188.72 | 0 | 304188.72
Toshka GIS 500 kV | Toshka Sub Inv. 09 | 9 | Toshka GIS 500 kV9 | 36373061.91 | 18809143.05 | 9547928.75 | 28357071.8
Toshka GIS 500 kV | Toshka Sub Inv. 05 | 5 | Toshka GIS 500 kV5 | 15409476.01 | 9699875.6 | 4044987.45 | 13744863.05
Toshka GIS 500 kV | Toshka Sub Inv. 03 | 3 | Toshka GIS 500 kV3 | 12049713.8 | 7874488.39 | 3163049.87 | 11037538.26
Mauritania-Lot 2 | Inv.3 – Lot 2 | 3 | Mauritania-Lot 23 | 1830052.44 | 1738549.82 | 0 | 1738549.82
IKEA Extension MoA | IKEA-IPC+02 |  | IKEA Extension MoA | 535990.4 | 535990.4 | 0 | 535990.4
kayan wall lock & Load | KAYAN LOAK&LOAD08 |  | kayan wall lock & Load | 4230000 | 3785412 | 3766754.85 | 7552166.85
Assuit PP (CP-118) | 519 |  | Assuit PP (CP-118) | 3978934.7 | 3511409.88 | 626682.21 | 4138092.09
Canal Regional Control Center | Inv.4 Rcc | 4 | Canal Regional Control Center4 | 25537107.18 | 17006497.75 | 5362792.51 | 22369290.26
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 26 | 26 | Benban 500 K.V / 100 K.M26 | 43640.91 | 33646.9 | 4582.3 | 38229.2
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .19 | 19 | Benban 3/ Toshka 2 LOT 419 | 104127.38 | 81555.58 | 10933.38 | 92488.96
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .3 | 3 | Benban 3/ Toshka 2 LOT 43 | 34347471.75 | 26481907.97 | 3606484.53 | 30088392.5
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .21 | 21 | Benban 3/ Toshka 2 LOT 421 | 7997574.53 | 6931070.92 | 202367.91 | 7133438.83
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .12 | 12 | Benban 3/ Toshka 2 LOT 412 | 860775.16 | 698030.65 | 90381.39 | 788412.04
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $3 | 3 | Benban 3/ Toshka 2 LOT 43 | 203309.37 | 170779.88 | 21347.48 | 192127.36
Ismailiya East Substation | ISE-CW-EGP-20 | 20 | Ismailiya East Substation20 | 1803066 | 911386.14 | 270459.9 | 1181846.04
MAYSAN 400/132kV SS | 288 |  | MAYSAN 400/132kV SS | 860778.34 | 860778.34 | 0 | 860778.34
Sewage Treatment Plant | IPC#1`2`3 | 1 | Sewage Treatment Plant1 | 2051966 | 1260000 | 0 | 1260000
Ismailiya East Substation | ISE-SD-EURO-05 | 5 | Ismailiya East Substation5 | 5894418.46 | 5246032.43 | 0 | 5246032.43
Tamey El-amdeed Substation | TAM-CW-EURO-08 | 8 | Tamey El-amdeed Substation8 | 545955.53 | 273600.09 | 81893.33 | 355493.42
Marsa Matrouh 500KV | Inv.52 Borg Alarab | 52 | Marsa Matrouh 500KV52 | 12906921.58 | 9241358.14 | 1355226.77 | 10596584.91
Marsa Matrouh 500KV | Inv.47 Borg Alarab | 47 | Marsa Matrouh 500KV47 | 7470695.02 | 6525652.35 | 784422.98 | 7310075.33
Safeer Square Bridge | SAFIER BRIDGE-IPC01 | 1 | Safeer Square Bridge1 | 87966715.14 | 8754247 | 27885620.8 | 76674867.8
4 SS - Technical Service | 305 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
AWEER POWER STATION 'H' Phase | 10427 |  | AWEER POWER STATION 'H' Phase | 783780.49 | 822969.5145 | 0 | 822969.5145
El Mostakbal City Project | Inv. 7 Mostakbal | 7 | El Mostakbal City Project7 | 29176277.5 | 24216310.32 | 6127018.28 | 30343328.6
CFC Podium 2 | CFC-IPC16 | 16 | CFC Podium 216 | 29185169.72 | 22871121.156 | 4275462.48 | 27146583.636
Lekela 250MW Wind Farm | SiemensLEKELA IPC012 | 12 | Lekela 250MW Wind Farm12 | 24308181.24 | 21477147.752 | 3853754.81 | 25330902.562
Lekela 250MW Wind Farm | LEKELA-IPC05 | 5 | Lekela 250MW Wind Farm5 | 8446374.72 | 7094954.766 | 1689274.94 | 8784229.706
Lekela 250MW Wind Farm | LEKELA-IPC04 | 4 | Lekela 250MW Wind Farm4 | 777289.9 | 652923.515 | 155457.98 | 808381.495
ESU Ph2-Enabling & Struc | S.U.PHASE2-IPC03 | 3 | ESU Ph2-Enabling & Struc3 | 22372123.52 | 17089175.4 | 7047218.91 | 24136394.31
Toshka GIS 500 kV | Toshka Sub Inv. 03 $ | 3 | Toshka GIS 500 kV3 | 54782.86 | 36869.3 | 14380.5 | 51249.8
Toshka GIS 500 kV | Toshka Sub Inv. 11 $ | 11 | Toshka GIS 500 kV11 | 1792347.49 | 1222707.15 | 470491.22 | 1693198.37
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC04 | 4 | EMAAR-Pkg#162/163- Marassi4 | 7314175.65 | 6393536.5925 | 818166.39 | 7211702.9825
Asec Spare-Parts | Inv 4 EUR Asec Spare | 4 | Asec Spare-Parts4 | 15668.8 | 3352.4 | 5086.53 | 8438.93
Akhmem Assiut | Re. Soc inv 22 To 25 | 22 | Akhmem Assiut22 | 1630 | 1630 | 0 | 1630
marassi inland marina | IPC#4 | 4 | marassi inland marina4 | 3402063.63 | 2947834.13 | 0 | 3117937.31
SHATRA 400/132kV SS | 304 |  | SHATRA 400/132kV SS | 1836678.75 | 1836678.75 | 0 | 1836678.75
MAYSAN 400/132kV SS | 301 |  | MAYSAN 400/132kV SS | 2391478.77 | 2391478.77 | 0 | 2391478.77
Beni Suef Add-on Sales | 2003210006 |  | Beni Suef Add-on Sales | 250125 | 277638.75 | 0 | 277638.75
Sodic East | 10008 |  | Sodic East | 311151.96 | 166775.6 | 108903.18 | 275678.78
Dubai Port | 10013 |  | Dubai Port | 41020.52 | 36385.19 | 0 | 36385.19
Ministries Building ROOF | 10004 |  | Ministries Building ROOF | 65124.05 | 61216.61 | 0 | 61216.61
Multi Sport Hall | 10034 |  | Multi Sport Hall | 143453.4 | 127673.53 | 0 | 127673.53
Sodic East | 10038 |  | Sodic East | 108381 | 93918.94 | 0 | 93918.94
Mivida | 10040 |  | Mivida | 100012.5 | 12.5 | 100000 | 100012.5
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC09 | 9 | EMAAR- Pkg 140-ITP-Mivida9 | 4233335.77 | 6237430.1585 | 585903.85 | 6823334.0085
Canal Sugar OHTL | Inv.04 Sugar OHTL | 4 | Canal Sugar OHTL4 | 391185.52 | 309036.56 | 58677.83 | 367714.39
Canal Sugar S/s | Inv 4 Sugar S/s | 4 | Canal Sugar S/s4 | 8119668.06 | 6414537.76 | 1217950.21 | 7632487.97
Ismailiya East Substation | ISE-SD-EGP-03 | 3 | Ismailiya East Substation3 | 583200 | 519048 | 0 | 519048
HyperOne Zayed Extension | HYPERONE-IPC06 | 6 | HyperOne Zayed Extension6 | 10976158 | 8598918.82 | 2744039.5 | 12322958.32
Oasis Buildings- New Capital | Inv(3)250120 | 3 | Oasis Buildings- New Capital3 | 60630 | 57586.69 | 0 | 57586.69
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC018 | 18 | EMAAR-Pkg#162/163- Marassi18 | 3301294.96 | 3248092.448 | 888092.46 | 4136184.908
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC015 | 15 | EMAAR-Pkg#162/163- Marassi15 | 7388288.7 | 4317541.565 | 1171459.67 | 5489001.235
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC07 | 7 | EMAAR-Pkg#162/163- Marassi7 | 4420616.83 | 4922193.4962 | 1444568 | 6366761.4962
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC06 | 6 | EMAAR-Pkg#162/163- Marassi6 | 8631951.71 | 6532694.7794 | 1807627.83 | 8340322.6094
Mountain View | 10025 |  | Mountain View | 101817.9 | 20709 | 75000 | 95709
Albatross | 10030 |  | Albatross | 132750 | 0 | 100000 | 100000
Marsa Allam | 10031 |  | Marsa Allam | 57351.53 | 24807.06 | 40000 | 64807.06
Sodic East | 10005 |  | Sodic East | 56863.2 | 30430.55 | 19902.12 | 50332.67
Sodic East | 10009 |  | Sodic East | 79280.4 | 40006.58 | 27748.14 | 67754.72
Manshiet Nasser Substation | 514 |  | Manshiet Nasser Substation | 820387 | 541390.18 | 0 | 541390.18
Marsa Matrouh 500KV | Inv.59 Borg Alarab | 59 | Marsa Matrouh 500KV59 | 3459192.38 | 3021609.25 | 363215.2 | 3384824.45
Marsa Matrouh 500KV | Inv.56 Borg Alarab | 56 | Marsa Matrouh 500KV56 | 15166868.57 | 13248261.5 | 1592521.2 | 14840782.7
Marsa Matrouh 500KV | Inv.55 Borg Alarab | 55 | Marsa Matrouh 500KV55 | 6918384.76 | 6043215.55 | 726430.4 | 6769645.95
Ministries Buildings | MIN LAND ESCAPE-IPC1 | 1 | Ministries Buildings1 | 2983013.65 | 1782335 | 24480 | 1806815
Canal Regional Control Center | Inv.6 Rcc | 6 | Canal Regional Control Center6 | 10397764.96 | 5884648.05 | 2183530.64 | 8068178.69
SHATRA 400/132kV SS | 330 |  | SHATRA 400/132kV SS | 774447.07 | 774447.07 | 0 | 774447.07
SHATRA 400/132kV SS | 328 |  | SHATRA 400/132kV SS | 1133556.15 | 1133556.15 | 0 | 1133556.15
MOTHANA 400/132kV SS | 313 |  | MOTHANA 400/132kV SS | 138212.12 | 138212.12 | 0 | 138212.12
SHATRA 400/132kV SS | 331 |  | SHATRA 400/132kV SS | 357859.01 | 357859.01 | 0 | 357859.01
MAYSAN 400/132kV SS | 311 |  | MAYSAN 400/132kV SS | 58865.41 | 58865.41 | 0 | 58865.41
Cameron EDC | 023/2020 FCV |  | Cameron EDC | 69576437.45 | 20872931 | 0 | 34788218.49
Latin Compound - New Alamin | INV(9)150420 | 9 | Latin Compound - New Alamin9 | 392840 | 288562.49 | 37168.24 | 325730.73
Ministry Building EPOXY | 10033 |  | Ministry Building EPOXY | 10605.04 | 9968.74 | 0 | 9968.74
Beni Seuf - 358 | Inv. 1 Oewon Mousa | 1 | Beni Seuf - 3581 | 7234840.58 | 5340848.3 | 1242856.65 | 6583704.95
Marsa Matrouh 500KV | Inv.74 Borg Alarab | 74 | Marsa Matrouh 500KV74 | 1233333.33 | 1012572.65 | 0 | 1012572.65
HAC CCC JV | IPC#13 | 13 | HAC CCC JV13 | 949947.45 | 1150115.83 | 0 | 592291.964
Assuit PP (CP-118) | 2002210016 |  | Assuit PP (CP-118) | 2511298.31 | 2216220.76 | 395529.48 | 2611750.24
Sodic East | 10006 |  | Sodic East | 68304 | 33405.25 | 23906.4 | 57311.65
Angola Emergency fast-track | ANG-Cam-Inv 4 - Ints | 4 | Angola Emergency fast-track4 | 7623762.34 | 5866370.95 | 0 | 5866370.95
Elhegaz | FPC |  | Elhegaz | 438410 | -77808.5 | 0 | -77808.5
AWEER POWER STATION 'H' Phase | LOC/006 Rev0 |  | AWEER POWER STATION 'H' Phase | 1097950 | 963756.21 | 121994.346 | 1085750.556
Abu Qir PP (CP-117) | Adjust rec.qir 117 |  | Abu Qir PP (CP-117) | 196748.76 | 196748.76 | 0 | 196748.76
Abu Qir PP (CP-117) | Adjust 1907210013- |  | Abu Qir PP (CP-117) | 17136.36 | 17136.36 | 0 | 17136.36
Ghana | 43/P/10/ER/2017/USD |  | Ghana | 655736.54 | 655736.54 | 0 | 655736.54
LAYAN Substation | 10967 |  | LAYAN Substation | 132794.44 | 224422.62 | 0 | 112211.31
LAYAN Substation | 10886 |  | LAYAN Substation | 462317.3055 | 1562632.52 | 0 | 390658.13
LAYAN Substation | 10364 |  | LAYAN Substation | 298927.44 | 248109.77 | 0 | 248109.77
LAYAN Substation | 10222 |  | LAYAN Substation | 5123619.66 | 4252604.32 | 0 | 4252604.32
LAYAN Substation | 10141 |  | LAYAN Substation | 385736.25 | 651894.26 | 0 | 325947.13
Mahmoudia Additional Scope | 2003210003 |  | Mahmoudia Additional Scope | 8250000 | 8250000 | 0 | 8250000
Port Saad Industiral zone | IPC#6 | 6 | Port Saad Industiral zone6 | 8614362 | 8295630.61 | 0 | 8295630.61
Club House-Sodic Wesset | 10074 |  | Club House-Sodic Wesset | 117700 | 116523 | 0 | 116523
Oasis Buildings- New Capital | Inv(5)240320 | 5 | Oasis Buildings- New Capital5 | 620400 | 581146.2 | 0 | 581146.2
Ain-Sokhna PP (CP-117) | 2005210006 |  | Ain-Sokhna PP (CP-117) | 23.93 | 23.93 | 0 | 23.93
SHATRA 400/132kV SS | 347 |  | SHATRA 400/132kV SS | 2964376.28 | 2964376.28 | 0 | 2964376.28
NUCA R05 - Z02 | R5 - IPC16 | 16 | NUCA R05 - Z0216 | 41433707.7 | 26497123.5 | 3364474.8 | 29861598.3
Miscellaneous Projects | 2004210006 |  | Miscellaneous Projects | 140220 | 138990 | 0 | 158620.8
Minis Building(Polyurethane) | 10042 |  | Minis Building(Polyurethane) | 377685.68 | 336140.26 | 0 | 336140.26
Miscellaneous Projects | 2006210007 |  | Miscellaneous Projects | 8384.62 | 9558.4668 | 0 | 9558.4668
Minis Building(Polyurethane) | 10194 |  | Minis Building(Polyurethane) | 331477.68 | 295015.14 | 0 | 295015.14
Minis Building(Polyurethane) | 10173 |  | Minis Building(Polyurethane) | 81421.47 | 72465.12 | 0 | 72465.12
DoubleTree Mangroovy ElGouna | MANGROVY-IPC06 | 6 | DoubleTree Mangroovy ElGouna6 | 6170230.65 | 8251289.2525 | 1619685.21 | 9870974.4625
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC05 | 5 | EMAAR-Pkg#162/163- Marassi5 | 8006098.57 | 6067879.3275 | 796526.84 | 6864406.1675
W Dam PP Phase II (CP-117) | 538 |  | W Dam PP Phase II (CP-117) | 1136393.79 | 1290667.6 | 0 | 1290667.6
MOTHANA 400/132kV SS | 351 |  | MOTHANA 400/132kV SS | 1403301.15 | 1403301.15 | 0 | 1403301.15
Marsa Matrouh 500KV | Inv.31 Borg Alarab | 31 | Marsa Matrouh 500KV31 | 1466699.73 | 1281162.51 | 154003.47 | 1435165.98
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 01 | 1 | Suez Gulf/S4 - 500KV OHTL1 | 43356299.65 | 35513135.71 | 4552411.46 | 40065547.17
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 04 | 4 | Suez Gulf/S4 - 500KV OHTL4 | 115225.4 | 96789.33 | 12098.67 | 108888
East Owainat 5 LOTS | East Owainat Inv. 01 | 1 | East Owainat 5 LOTS1 | 38222459.48 | 15652082.11 | 20066791.22 | 35718873.33
Barwa 2x60/22 KV S/S | Inv. Barwa 38 |  | Barwa 2x60/22 KV S/S | 2683543.96 | 1884957.98 | 402531.59 | 2287489.57
DPW Onshore Port & Terminal | DP WORLD - IPC15 | 15 | DPW Onshore Port & Terminal15 | 110730132.45 | 81940298.01 | 16609519.87 | 98549817.88
SHATRA 400/132kV SS | 357 |  | SHATRA 400/132kV SS | 1635918.76 | 1635918.76 | 0 | 1635918.76
AWEER POWER STATION 'H' Phase | Imp-041 Rev0 | 41 | AWEER POWER STATION 'H' Phase41 | 3691844.34 | 3650823.84 | 0 | 3650823.84
AWEER POWER STATION 'H' Phase | Con-011 | 11 | AWEER POWER STATION 'H' Phase11 | 958273.98 | 947626.49 | 0 | 947626.49
Abbas El Akkad Bridge | inv(1)300620 | 1 | Abbas El Akkad Bridge1 | 800030 | 40001.5 | 0 | 748428.06
Canal Sugar S/s | Inv 2 $ Sugar S/s | 2 | Canal Sugar S/s2 | 1151235.65 | 909476.15 | 172685.35 | 1082161.5
NUCA R05 - Z02 | R5-FINSHING-IPC01 | 1 | NUCA R05 - Z021 | 4034106.35 | 3635379.6 | 0 | 3635379.6
4 SS - Technical Service | 363 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
CFC Podium 2 | CFC- IPC07 | 7 | CFC Podium 27 | 17879880.11 | 19510039.82 | 3717893.63 | 23227933.45
MAYSAN 400/132kV SS | 359 |  | MAYSAN 400/132kV SS | 844928.25 | 844928.25 | 0 | 844928.25
MOTHANA 400/132kV SS | 360 |  | MOTHANA 400/132kV SS | 1427199.69 | 1427199.69 | 0 | 1427199.69
Banha PP (CP-118) | 200067 |  | Banha PP (CP-118) | 255420 | 577249.2 | 0 | 288624.6
AWEER POWER STATION 'H' Phase | IMP-053 | 53 | AWEER POWER STATION 'H' Phase53 | 188611.15 | 181276.28 | 0 | 181276.28
AWEER POWER STATION 'H' Phase | Loc-007 Rev0 | 7 | AWEER POWER STATION 'H' Phase7 | 389235.05 | 384829.22 | 0 | 384829.22
ESU Ph2-Enabling & Struc | ESU2-ARCH&MEP-IPC05 | 5 | ESU Ph2-Enabling & Struc5 | 53567992 | 64006362.74 | 16799844.2 | 80806206.94
Minis Building(Polyurethane) | IPC_12_rowad_poly |  | Minis Building(Polyurethane) | 364117.38 | 322084.47 | 0 | 322084.47
Tanzania hydropower Project | 3 |  | Tanzania hydropower Project | 1202958.11 | 946870.06 | 0 | 946870.06
EDNC Retail & Offices Civil | SOREAL-IPC14 | 14 | EDNC Retail & Offices Civil14 | 24418089.97 | 17859899.4785 | 2751415.45 | 20611314.9285
AWEER POWER STATION 'H' Phase | IMP-048 | 48 | AWEER POWER STATION 'H' Phase48 | 3161126.03 | 3126002.41 | 0 | 3126002.41
AWEER POWER STATION 'H' Phase | Con-014 | 14 | AWEER POWER STATION 'H' Phase14 | 958273.98 | 947626.49 | 0 | 947626.49
Canal Sugar S/s | Inv 8 Sugar S/s | 8 | Canal Sugar S/s8 | 7381102.06 | 5831070.62 | 1107165.31 | 6938235.93
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .5 | 5 | Benban 3/ Toshka 2 LOT 45 | 8982538.39 | 6925535.95 | 943166.53 | 7868702.48
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .11 | 11 | Benban 3/ Toshka 2 LOT 411 | 3523015.64 | 2892398.98 | 369916.64 | 3262315.62
Ghana | 50/P/10/ER/2017/USD |  | Ghana | 588194.61 | 588207.78 | 0 | 588207.78
Racecores 3092-16 132KV C | 11542 |  | Racecores 3092-16 132KV C | 347388.21 | 1441661.1 | 0 | 288332.22
Racecores 3092-16 132KV C | 11457 |  | Racecores 3092-16 132KV C | 419038.5388 | 1416350.2628 | 0 | 354087.5657
33KV Canal Farm Grid | Inv. 07 Farm | 7 | 33KV Canal Farm Grid7 | 1120160.06 | 884926.44 | 168024.01 | 1052950.45
NUCA R05 - Z02 | R05(2) ipc46 | 46 | NUCA R05 - Z0246 | 28054197.43 | 22413765.21 | 2996461.96 | 25410227.17
NUCA R05 - Z02 | R05 Zone 2 IPC019 | 19 | NUCA R05 - Z0219 | 40013957.35 | 36068788.78 | 4689061.1 | 40757849.88
Canal Regional Control Center | Inv.7 Rcc | 7 | Canal Regional Control Center7 | 6051819.83 | 3425301.4 | 1270882.16 | 4696183.56
CFC Podium 2 | CFC-IPC09 | 9 | CFC Podium 29 | 29660400.78 | 24499896.0885 | 4666027.79 | 29165923.8785
Baron Fence | ELBARON-IPC01 | 1 | Baron Fence1 | 9980627.24 | 5993105 | 2554967.35 | 8548072.35
Azab Tex Factory | inv ( 1 ) 1-2-2021 | 1 | Azab Tex Factory1 | 620350 | 620350 | 0 | 620350
Zambia Project | SCD1x/007 |  | Zambia Project | 363025.44 | 326685.27 | 0 | 326685.27
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 3 | 3 | Marsa Alam/ Bernes LOT2 OHTL3 | 73253186.66 | 60140851.04 | 7691585.5 | 67832436.54
Taval Sarai 52 | IPC-15-Saray | 15 | Taval Sarai 5215 | 505176.7 | 381064.02 | 0 | 381064.02
Taval Sarai 52 | IPC_2_Gama_Saraya |  | Taval Sarai 52 | 125198.7 | 98529.87 | 0 | 98529.87
Manshiet Nasser Substation | 2008210008 |  | Manshiet Nasser Substation | 4538.92 | 4061.14 | 716.67 | 4777.81
Manshiet Nasser Substation | Adjust 180177- |  | Manshiet Nasser Substation | 919 | 919 | 0 | 919
Marsa Matrouh 500KV | Inv.24Usd borg alarb | 24 | Marsa Matrouh 500KV24 | 298146.74 | 214744.02 | 0 | 214744.02
Ministries A17-A18 | IPC_7_GAMA_A17 |  | Ministries A17-A18 | 544424 | 460854.92 | 0 | 460854.92
Minis Building(Polyurethane) | IPC_15_Rowad_Poly |  | Minis Building(Polyurethane) | 19944.02 | 17210.18 | 0 | 17210.18
NUCA R05 - Z02 | R5 FINSHING-IPC05 | 5 | NUCA R05 - Z025 | 14871150.8 | 11695928.75 | 1576171.85 | 13272100.6
Royal City | ROYAL ZONE-IPC12 | 12 | Royal City12 | 8940988.58 | 6296298.659 | 1702855.61 | 7999154.269
Cairo-Alex Railway | Cairo-alex ipc 38 | 38 | Cairo-Alex Railway38 | 11333077.14 | 7840424.02 | 1189973.1 | 9030397.12
Cairo-Alex Railway | Cairo-alex ipc 37 | 37 | Cairo-Alex Railway37 | 5830965.71 | 4049206.83 | 612251.4 | 4661458.23
Cairo-Alex Railway | cairo-alex ipc 29 | 29 | Cairo-Alex Railway29 | 56978233.6 | 4175868.4 | 40982714.53 | 45158582.93
Cairo-Alex Railway | CAIRO-ALEX IPC24 | 24 | Cairo-Alex Railway24 | 36781433.5 | 25544306.65 | 3862050.52 | 29406357.17
Cairo-Alex Railway | Cairo-Alex IPC011 | 11 | Cairo-Alex Railway11 | 22566567.8 | 15058027.95 | 2369489.65 | 17427517.6
Cairo-Alex Railway | Cairo-Alex IPC03 | 3 | Cairo-Alex Railway3 | 5582157.64 | 3953758.56 | 558215.76 | 4511974.32
Racecores 3092-17 132KV E | 11455 |  | Racecores 3092-17 132KV E | 257643.77 | 213844.3285 | 0 | 213844.3285
Racecores 3092-17 132KV E | 10663 |  | Racecores 3092-17 132KV E | 2768749.5 | 4596124.18 | 0 | 2298062.09
SHAT Al ARAB 400/132kV SS | 366 |  | SHAT Al ARAB 400/132kV SS | 1811715.34 | 1811715.34 | 0 | 1811715.34
MOTHANA 400/132kV SS | 382 |  | MOTHANA 400/132kV SS | 16614.19 | 16614.19 | 0 | 16614.19
Lekela 250MW Wind Farm | LEKELA-IPC03 | 3 | Lekela 250MW Wind Farm3 | 2093986.78 | 1758948.889 | 418797.36 | 2177746.249
Lekela 250MW Wind Farm | LEKELA-IPC02 | 2 | Lekela 250MW Wind Farm2 | 1271271.54 | 1067868.087 | 254254.31 | 1322122.397
Masr ELgedeeda | IPC#1 | 1 | Masr ELgedeeda1 | 1396750 | 1338784.5 | 0 | 1338784.5
NUCA R05 - Z02 | R5 - IPC21 | 21 | NUCA R05 - Z0221 | 36906800.17 | 23661440.9 | 3033508.46 | 26694949.36
DPW Onshore Port & Terminal | DP WORLD -IPC20 | 20 | DPW Onshore Port & Terminal20 | 42996289.46 | 31817254.2 | 6449443.42 | 38266697.62
LRT - El Shorouk Bridge | IPC#6 | 6 | LRT - El Shorouk Bridge6 | 1069480 | 789999.57 | 0 | 789999.57
Ministries Buildings | MIN-ALLOCATION-IPC02 | 2 | Ministries Buildings2 | 11312307.26 | 3367547 | 6841403.85 | 10208950.85
ORA ZED - Ph 01B - Pkgs A&D | Ora Ph 1 ipc 37 | 37 | ORA ZED - Ph 01B - Pkgs A&D37 | 29089779.62 | 23554316.1 | 3046679.76 | 26600995.86
ORA ZED - Ph 01B - Pkgs A&D | ORA ph 1 ipc (28) | 28 | ORA ZED - Ph 01B - Pkgs A&D28 | 22847215.74 | 8905384.6977 | 12391645.05 | 21297029.7477
ORA ZED - Ph 01B - Pkgs A&D | Ora Zed Ph1 IPC05 | 5 | ORA ZED - Ph 01B - Pkgs A&D5 | 41442903.7 | 33310478.505 | 3965163.77 | 37275642.275
EMAAR-PKG#62-UPTOWN | 18100052 |  | EMAAR-PKG#62-UPTOWN | 2727129.53 | 1778643.79 | 1001134.12 | 2779777.91
El Mostakbal City Project | Inv. 10 Mostakbal | 10 | El Mostakbal City Project10 | 12115411.8 | 10055791.79 | 2544236.48 | 12600028.27
Mohamed Ali Palace | 10273 |  | Mohamed Ali Palace | 190809 | 160279.56 | 0 | 160279.56
LAYAN Substation | 10204 |  | LAYAN Substation | 164273.805 | 272694.52 | 0 | 136347.26
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .9 | 9 | Benban 3/ Toshka 2 LOT 49 | 100778929.4 | 82739503.4 | 10581787.59 | 93321290.99
SHAT Al ARAB 400/132kV SS | 379 |  | SHAT Al ARAB 400/132kV SS | 460337.36 | 460337.36 | 0 | 460337.36
SHATRA 400/132kV SS | 380 |  | SHATRA 400/132kV SS | 306893.5 | 306893.5 | 0 | 306893.5
MAYSAN 400/132kV SS | 377 |  | MAYSAN 400/132kV SS | 1210817.35 | 1210817.35 | 0 | 1210817.35
Ministries Buildings | MIN-ALLOCATION-IPC5 | 5 | Ministries Buildings5 | 17481409.92 | 5853780 | 8873907.5 | 14727687.5
CFC Podium 2 | CFC-IPC12 | 12 | CFC Podium 212 | 34817130.72 | 29691195.016 | 4416272.34 | 34107467.356
Koning Food V2 - LP-08-20 | 6 |  | Koning Food V2 - LP-08-20 | 2642.98 | 3013 | 0 | 3013
ESU Ph2-Enabling & Struc | E.U2-ENABLING-10 | 10 | ESU Ph2-Enabling & Struc10 | 5068271.52 | 10675697.426 | 0 | 10675697.426
EMAAR-PKG117- MARASSI | PKG#117-IPC FINAL |  | EMAAR-PKG117- MARASSI | 1638134.38 | 2354224.5932 | 0 | 2354224.5932
Toshka GIS 500 kV | Toshka Sub Inv. 15 $ | 15 | Toshka GIS 500 kV15 | 46601.9 | 26327.6 | 12233 | 38560.6
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .13 | 13 | Benban 3/ Toshka 2 LOT 413 | 116650.71 | 91407.17 | 12248.33 | 103655.5
MAYSAN 400/132kV SS | 383 |  | MAYSAN 400/132kV SS | 5337437.44 | 5337437.44 | 0 | 5337437.44
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 03 | 3 | Toshka-04 GIS Substation3 | 101550754.44 | 84489796.66 | 10662829.22 | 95152625.88
Toshka GIS 500 kV | Toshka Sub Inv. 19 $ | 19 | Toshka GIS 500 kV19 | 3133454.29 | 1973556.2 | 822531.75 | 2796087.95
R5 | inv ( 13 ) | 13 | R513 | 1482000 | 297408.51 | 0 | 1368455.9
Miscellaneous Projects | 2012210001 |  | Miscellaneous Projects | 132158.8 | 150661.032 | 0 | 150661.032
Mivida | IPC_3_Mivida |  | Mivida | 212130 | 210008.7 | 0 | 210008.7
Taval Sarai 52 | IPC_3_Gama_Saray |  | Taval Sarai 52 | 158874.5 | 114823.68 | 0 | 114823.68
Canal Sugar S/s | Inv 3 Sugar S/s | 3 | Canal Sugar S/s3 | 4812648.74 | 3801992.51 | 721897.31 | 4523889.82
ElMarg | IPC#1 & Final | 1 | ElMarg1 | 1093100 | 1000000 | 0 | 1082169
Bani Suef Old Substation | BNI SUEF OLD-IPC FIN |  | Bani Suef Old Substation | 2627278.35 | 3467007.05 | 0 | 3467007.05
ESU Ph2-Enabling & Struc | E.US2-MEP-IPC11 | 11 | ESU Ph2-Enabling & Struc11 | 24045616.1 | 13851401.63 | 5913881.4 | 19765283.03
Kattameya Creeks | Katamya ipc (31) | 31 | Kattameya Creeks31 | 49290024.52 | 37106226 | 14155399.33 | 51261625.33
Kattameya Creeks | katameya-IPC23 | 23 | Kattameya Creeks23 | 30664402.09 | 29834733.0645 | 2056245.11 | 31890978.1745
Kattameya Creeks | Katameya IPC16 | 16 | Kattameya Creeks16 | 47021445.38 | 44583744.0045 | 4305908.79 | 48889652.7945
Kattameya Creeks | katmeyacreeks ipc12 | 12 | Kattameya Creeks12 | 39536093.61 | 36461301.5305 | 4638525.82 | 41099827.3505
Kattameya Creeks | KatameyaCreks IPC010 | 10 | Kattameya Creeks10 | 38757548.53 | 36159161.9365 | 4136038.53 | 40295200.4665
El Katameya Mall | inv ( 12 ) 30-9-2020 | 12 | El Katameya Mall12 | 85400 | 51371.74 | 0 | 51371.74
Latin Compound - New Alamin | inv (27) AL15-2-2021 | 27 | Latin Compound - New Alamin27 | 288078 | 244722.16 | 0 | 244722.16
Ismailiya East Substation | ISE-SD-EGP-02 | 2 | Ismailiya East Substation2 | 191389.5 | 170338 | 0 | 170338
Ismailiya East Substation | ISE-CW-EGP-25 | 25 | Ismailiya East Substation25 | 294276 | 261905.64 | 0 | 261905.64
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.01 | 1 | Toshka 2/Owinat East LOT2 OHTL1 | 33724388.22 | 30081763.99 | 3541060.76 | 33622824.75
Beni Seuf - 358 | Re Soc Inv.2 Temmay | 2 | Beni Seuf - 3582 | 580808 | 580808 | 0 | 580808
Royal City | ROYALZONE2-IPC13 | 13 | Royal City13 | 3598739.18 | 2137568.4452 | 579614.89 | 2717183.3352
DoubleTree Mangroovy ElGouna | MANGROVY CLAIM-IPC12 | 12 | DoubleTree Mangroovy ElGouna12 | 1904761.9 | 1942857.135 | 0 | 1942857.135
Shorouk Bridge-LRT | SHOROUK DRIDGE-IPC02 | 2 | Shorouk Bridge-LRT2 | 13091823.2 | 3040310.99 | 8000000 | 11040310.99
Shorouk Bridge-LRT | SHOROUK BRIDGE-IPC01 | 1 | Shorouk Bridge-LRT1 | 2491848.1 | 1959689.01 | 0 | 1959689.01
El-Moneeb Bridge | Final PC |  | El-Moneeb Bridge | 298500 | 254165 | 0 | 254165
Kayan 3 New Cairo Capital City | KAYAN MEP1-IPC06 | 6 | Kayan 3 New Cairo Capital City6 | 46122875 | 20582125 | 20582136 | 41164261
Sodic East | IPC_20_Rowad_Seast |  | Sodic East | 273153.72 | 181637.59 | 0 | 181637.59
Coastal road Bridge Extension | IPC#5 - Gharably | 5 | Coastal road Bridge Extension5 | 1553202 | 1495733.53 | 0 | 1495733.53
Coastal road Bridge Extension | IPC#1` - Gharably | 1 | Coastal road Bridge Extension1 | 1584660 | 1526027.58 | 0 | 1526027.58
El Boghaz Brigde | IPC#26 | 26 | El Boghaz Brigde26 | 564857.5 | 383976.81 | 0 | 383976.81
Royal City | ROYAL CITY2-IPC16 | 16 | Royal City16 | 1581960.97 | 853478.4785 | 0 | 853478.4785
Miscellaneous Projects | 2007210012 |  | Miscellaneous Projects | 34725 | 39239.25 | 0 | 39239.25
Beni Seuf - 358 | Inv. 10 Oewon Mousa | 10 | Beni Seuf - 35810 | 10543429.34 | 7151842.22 | 1810072.7 | 8961914.92
LRT | IPC#1 | 1 | LRT1 | 778080 | 552435.92 | 0 | 552435.92
ORA Zed Park LOCK&LOAD | ORA L&L-IPC03 | 3 | ORA Zed Park LOCK&LOAD3 | 145168.11 | 128110.8555 | 0 | 128110.8555
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED-IPC01 | 1 | ORA ZED - Ph 01B - Pkgs A&D1 | 2407390.57 | 10377230.16 | 1179886.73 | 11557116.89
Badr | Inv. 24 Badr | 24 | Badr24 | 9633352.5 | 6670347.3 | 1445002.9 | 8115350.2
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC20 | 20 | EMAAR- Pkg 140-ITP-Mivida20 | 5957491.28 | 6060664.08 | 605845.36 | 6666509.44
Manshiet Nasser Substation | 2102210002 |  | Manshiet Nasser Substation | 2889.29 | 2285.95 | 467.65 | 2753.6
Manshiet Nasser Substation | 2102210001 |  | Manshiet Nasser Substation | 115620.9524 | 82437.25 | 18210.3 | 100647.55
Development of Mahmudiyah axis | FPC closing |  | Development of Mahmudiyah axis | 26550 | 26550 | 0 | 26550
Mivida | IPC_6_Mivida |  | Mivida | 168310 | 102218 | 0 | 102218
EGAT Pelletizing Plant | elco egat ipc09 | 9 | EGAT Pelletizing Plant9 | 15797419.96 | 14888446.998 | 1540869.76 | 16429316.758
Minis Building(Polyurethane) | IPC_18_Rowad_Poly |  | Minis Building(Polyurethane) | 36617.1 | 165.96 | 0 | 32589.21
Miscellaneous Projects | 2012210028 |  | Miscellaneous Projects | 141787.4 | 161637.636 | 0 | 161637.636
IKEA Extension MoA | IKEA-IPC13 | 13 | IKEA Extension MoA13 | 3981119.65 | 4064871.9 | 0 | 4064871.9
Royal City | ROYAL CITY-IPC38 | 38 | Royal City38 | 4991557.65 | 3951088.5025 | 0 | 3951088.5025
IKEA Extension MoA | IKEA2-IPC03 | 3 | IKEA Extension MoA3 | 859270.7 | 823216.605 | 0 | 823216.605
Taval Sarai 52 | IPC_8_Saray |  | Taval Sarai 52 | 1550526.2 | 1284301.11 | 0 | 1284301.11
Sodic East | IPC_19_Rowad_S_east |  | Sodic East | 145284.8 | 92212.984 | 0 | 92212.984
EDNC Retail & Offices Civil | SOREAL-IPC23 | 23 | EDNC Retail & Offices Civil23 | 23832998.72 | 15672746.626 | 1461990.25 | 17134736.876
Railway Bridge - Assuit | IPC#1 Assuit | 1 | Railway Bridge - Assuit1 | 995880 | 679771.39 | 0 | 679771.39
158E/2019 33kv Project | 10382 |  | 158E/2019 33kv Project | 106200 | 95580 | 0 | 95580
BridgeNasr Rd w Abbas El-Akkad | ABASELAQAD-IPC1FINAL | 1 | BridgeNasr Rd w Abbas El-Akkad1 | 106237173.33 | 6904265 | 20000000 | 88369955
El Ameed 220 KV | ELAmeed Inv. 01 Fina | 1 | El Ameed 220 KV1 | 752380.95 | 690658.35 | 0 | 690658.35
Miscellaneous Projects | 2012210026 |  | Miscellaneous Projects | 10500 | 11970 | 0 | 11970
New Babil 400/132KV Substation | 2103210005 |  | New Babil 400/132KV Substation | 65785.41 | 65785.41 | 0 | 65785.41
MDF Factory | MDF - IPC 14 | 14 | MDF Factory14 | 12281779.55 | 11569223.8875 | 3542110.92 | 15111334.8075
MDF Factory | MDF IPC01 | 1 | MDF Factory1 | 2418808.57 | 6231879 | 634937.25 | 6866816.25
Marassi Inner Marina - PKG178 | IPC#1 .PKG#178 | 1 | Marassi Inner Marina - PKG1781 | 2247700 | 1967215.5 | 0 | 1967215.5
CFC Podium 2 | CFC-IPC17 | 17 | CFC Podium 217 | 23196101.95 | 15047803.35 | 2853816.14 | 17901619.49
Masr ELgedeeda | FPC |  | Masr ELgedeeda | 324187.5 | 310733.68 | 0 | 310733.68
4 SS - Technical Service | 410 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Al Montaza Hotels - Alexandria | inv ( 2 ) montazha | 2 | Al Montaza Hotels - Alexandria2 | 5399933 | 5129936.35 | 0 | 5129936.35
El Katameya Mall | INV (17 ) Final Kat | 17 | El Katameya Mall17 | 203840 | 151259.88 | 0 | 151259.88
Canal Sugar S/s | Inv 11 Sugar S/s | 11 | Canal Sugar S/s11 | 600377.29 | 458087.87 | 90056.59 | 548144.46
Canal Sugar 33KV OHTL | Inv. 6 Sugar 33 OHTL | 6 | Canal Sugar 33KV OHTL6 | 3384379.83 | 3089938.78 | 0 | 3089938.78
El Sewedy University | Inv(3)300420 | 3 | El Sewedy University3 | 962231.14 | 48111.56 | 0 | 884290.42
Wadi El Natroun | IPC#3 | 3 | Wadi El Natroun3 | 651015 | 0 | 0 | 0
Assuit PP (CP-118) | 2104210005 |  | Assuit PP (CP-118) | 3573738.67 | 7523660.34 | 0 | 3761830.17
Angola Emergency fast-track | ANG-Cam-Inv 6 | 6 | Angola Emergency fast-track6 | 21874849.84 | 14742271.02 | 0 | 14742271.02
Mohamed Ali Palace Restoration | M.ALY-IPC03 | 3 | Mohamed Ali Palace Restoration3 | 748821.44 | 488067.85 | 135600.01 | 623667.86
Ministries Buildings | MIN ALLOCATION-IPC06 | 6 | Ministries Buildings6 | 16905564.28 | 5711155 | 8598324.45 | 14309479.45
Marsa Alam/ Bernes LOT2 OHTL | Borg Inv. 27 USD | 27 | Marsa Alam/ Bernes LOT2 OHTL27 | 24764.46 | 9681.1205 | 0 | 9681.1205
East Owainat 5 LOTS | East Owainat Inv. 03 | 3 | East Owainat 5 LOTS3 | 80962475.52 | 33154132.72 | 42505299.65 | 75659432.37
BKG#178-Lagoon Discharge | PKG#178-IPC02 | 2 | BKG#178-Lagoon Discharge2 | 15355946.84 | 13230338.292 | 1692993.14 | 14923331.432
UIC Project (LP-04-21) | 53 |  | UIC Project (LP-04-21) | 858487.5 | 0 | 0 | 858487.5
EGYTEC A1,A3 ( LP-05-21) | 60 |  | EGYTEC A1,A3 ( LP-05-21) | 97500 | 0 | 65000 | 65000
Bahr ElBakar – Power Station | IPC#3 Madkour | 3 | Bahr ElBakar – Power Station3 | 994164 | 984222.36 | 0 | 984222.36
New Babil 400/132KV Substation | 2105210012 |  | New Babil 400/132KV Substation | 406584.8 | 406584.8 | 0 | 406584.8
OHTL Mostakable East Boundary | Inv. 04 Future OHTL | 4 | OHTL Mostakable East Boundary4 | 5953293.79 | 4295226.55 | 1896198.99 | 6191425.54
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC010 | 10 | EMAAR-Pkg#162/163- Marassi10 | 0.0001 | 1096860.9301 | 131917.3 | 1228778.2301
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC3,4 | 3 | EMAAR-Pkg#162/163- Marassi3 | 5088605.14 | 8093853.797 | 1040851.13 | 9134704.927
Mauritania Lot 1 | Inv.5 - Lot 1 | 5 | Mauritania Lot 15 | 78138.75 | 74231.81 | 0 | 74231.81
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $9 | 9 | Benban 3/ Toshka 2 LOT 49 | 151413.81 | 126727.6 | 15898.45 | 142626.05
Kafr Shokr Bridge | Kafr Shokr_IPC02 | 2 | Kafr Shokr Bridge2 | 7001830.48 | 6242742.164 | 0 | 6242742.164
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.01 | 1 | Mostakbal 2 Package No. (8)1 | 26909174.1 | 22334614.51 | 5650926.56 | 27985541.07
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC19 | 19 | EMAAR-PKG# 101-UPTOWN19 | 1071378.16 | 1296410.108 | 622319.28 | 1918729.388
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC19 | 19 | EMAAR- Pkg 140-ITP-Mivida19 | 11459315.86 | 8885358.623 | 1136996.72 | 10022355.343
Diplomatic District - Infra | Diplo Dist IPC06 | 6 | Diplomatic District - Infra6 | 15837044.05 | 12861043.65 | 1717677.2 | 14578720.85
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC013 | 13 | EMAAR-Pkg#162/163- Marassi13 | 6375780.45 | 4255708.1825 | 1087618.85 | 5343327.0325
Air Force Project | Air Force Inv . 07 | 7 | Air Force Project7 | 4347859.2 | 3113067.1 | 1086964.8 | 4200031.9
Faculty of Medicine | Mansora ipc10 | 10 | Faculty of Medicine10 | 11906206.67 | 10074037.3535 | 595310.33 | 10669347.6835
Faculty of Medicine | faculty mansora-ipc1 | 1 | Faculty of Medicine1 | 21437884.76 | 18134261.11 | 1071895 | 19206156.11
NUCA R05 - Z02 | R5 FINSHING-IPC7* | 7 | NUCA R05 - Z027 | 828155.16 | 656313.01 | 82815.55 | 739128.56
R5 Mix-Use Complex Project | R5-ZONE01-IPC02 | 2 | R5 Mix-Use Complex Project2 | 25863589.7 | 28409615.74 | 3473696.8 | 31883312.54
Industria Sadat | Sadat Indust Inv. 07 | 7 | Industria Sadat7 | 50462508.82 | 22076559.21 | 10597126.85 | 32673686.06
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .18 | 18 | Benban 3/ Toshka 2 LOT 418 | 4806835.46 | 3277866.47 | 504717.72 | 3782584.19
Railway Bridge - Assuit | IPC#2 Assuit | 2 | Railway Bridge - Assuit2 | 1470820 | 1234799.4 | 0 | 1234799.4
DoubleTree Mangroovy ElGouna | Mangroovy IPC017 | 17 | DoubleTree Mangroovy ElGouna17 | 2987451.96 | 4581335.978 | 295357.13 | 4876693.108
Taval Sarai 52 | IPC-12-Saray-2 | 12 | Taval Sarai 5212 | 406979.33 | 0 | 0 | 406979.33
Taval Sarai 52 | IPC_11_Saray |  | Taval Sarai 52 | 340654 | 259739.51 | 0 | 259739.51
October Dry Port | Dry Port Inv. 05 | 5 | October Dry Port5 | 5651684.01 | 3374772.3 | 1483567.05 | 4858339.35
October Dry Port Railway | ODP ipc3 | 3 | October Dry Port Railway3 | 12846917.73 | 14255254.3995 | 2774511.07 | 17029765.4695
October Dry Port Railway | ODP IPC01 | 1 | October Dry Port Railway1 | 21142097.5 | 13456945.045 | 4439840.48 | 17896785.525
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 05 | 5 | Hosh Essa 220 KV OHTL5 | 22976443.83 | 18633902.9 | 2412526.6 | 21046429.5
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 04 | 4 | Hosh Essa 220 KV OHTL4 | 2366293.31 | 1422148 | 248460.8 | 1670608.8
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 3 Equ | 3 | Hosh Essa 220 KV OHTL3 | 897994.32 | 476335 | 94792.34 | 571127.34
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 74079252.27 | 60783836.38 | 7778321.49 | 68562157.87
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.03 | 3 | Toshka 2/Owinat East LOT2 OHTL3 | 10920854.1 | 9741006.73 | 1146689.68 | 10887696.41
Wadi El Natroun | IPC#2 | 2 | Wadi El Natroun2 | 2142630 | 2000897.2 | 0 | 2000897.2
EGAT Pelletizing Plant | EGAT Water Tank IPC1 | 1 | EGAT Pelletizing Plant1 | 3274479.04 | 3241734.16 | 0 | 3241734.16
Sultana Malak Restoration | Sultana Malak IPC01 | 1 | Sultana Malak Restoration1 | 38453824.39 | 2505968.75 | 32000000 | 34505968.75
Royal City | Royal City IPC20 | 20 | Royal City20 | 1366660.7 | 1092291.595 | 294922.19 | 1387213.785
Royal City | ROYAL CITY2-IPC19 | 19 | Royal City19 | 1583738.34 | 1100401.507 | 301663.7 | 1402065.207
Royal City | Royal City IPC021 | 21 | Royal City21 | 4112519.3 | 2970506.755 | 819101.85 | 3789608.605
Racecores 3092-17 132KV E | 10785 |  | Racecores 3092-17 132KV E | 2145082.775 | 1780418.7 | 0 | 1780418.7
ElMoneeb 2 | IPC#2 Moneeb | 2 | ElMoneeb 22 | 290450 | 287545.5 | 0 | 287545.5
Kattameya Creeks | Katameya Creks IPC07 | 7 | Kattameya Creeks7 | 48280873.42 | 44380444.2275 | 5093038.59 | 49473482.8175
Lekela 250MW Wind Farm | lekela-po2 |  | Lekela 250MW Wind Farm | 342857.14 | 356571.427 | 0 | 356571.427
Lekela 250MW Wind Farm | lekela- po01 |  | Lekela 250MW Wind Farm | 171428.57 | 178285.7085 | 0 | 178285.7085
seashell Playa | IPC-9-Playa | 9 | seashell Playa9 | 385682.5 | 269244.94 | 61709.2 | 330954.14
seashell Playa | IPC-8-PLAYA | 8 | seashell Playa8 | 190902.5 | 133269.02 | 30544.4 | 163813.42
seashell Playa | IPC-6-PLAYA | 6 | seashell Playa6 | 284839.6 | 198456.51 | 45574.34 | 244030.85
Capital One | inv ( 3 ) Captal 1 | 3 | Capital One3 | 787497.0238 | 779622.055 | 0 | 779622.055
EGAT Pelletizing Plant | EGAT-IPC18 | 18 | EGAT Pelletizing Plant18 | 930523.4 | 0 | 1170012.11 | 1170012.11
GOV2 - Infra | GOV2 IPC05 | 5 | GOV2 - Infra5 | 5869423.06 | 47185643.463 | 4507237.7 | 51692881.163
Multi Sport Hall | IPC_14_IndoorHall |  | Multi Sport Hall | 98166 | 186499.29 | 0 | 186499.29
Mauritania Lot 1 | Inv.12 - Lot 1 | 12 | Mauritania Lot 112 | 331802.75 | 315197.61 | 0 | 315197.61
LAYAN Substation | 10822 |  | LAYAN Substation | 271525.22 | 450731.84 | 0 | 225365.92
Angola Emergency fast-track | ANG-Cam-Inv 8 | 8 | Angola Emergency fast-track8 | 1360018.02 | 753412.56 | 0 | 753412.56
Ext.110 S. Military 220 Kv S/S | Extension kayn Inv 1 | 1 | Ext.110 S. Military 220 Kv S/S1 | 22316542.56 | 13993725 | 5579135.6 | 19572860.6
Assuit PP (CP-118) | inv. 30,31,33 EUR | 30 | Assuit PP (CP-118)30 | 135368.9 | 364529.1 | 60916.02 | 141815.04
Assuit PP (CP-118) | 2106210003 |  | Assuit PP (CP-118) | 308474.46 | 272228.71 | 48584.73 | 320813.44
Miscellaneous Projects | 2008210003 |  | Miscellaneous Projects | 118487.2 | 135075.408 | 0 | 135075.408
Kafr Shokr Bridge | Kafr Shokr IPC04 | 4 | Kafr Shokr Bridge4 | 14900014.29 | 8190447.9 | 0 | 13190447.9
ORA ZED-Ph 2-Pkgs A&D | ora ph 2 ipc 24 | 24 | ORA ZED-Ph 2-Pkgs A&D24 | 1619984.79 | 1344587.3795 | 170098.4 | 1514685.7795
ORA ZED-Ph 2-Pkgs A&D | ORA PH.2- IPC13 | 13 | ORA ZED-Ph 2-Pkgs A&D13 | 20487173.63 | 0 | 0 | 21511532.3115
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.05 | 5 | Toshka 2/Owinat East LOT2 OHTL5 | 11321211.29 | 10093128.56 | 1188727.19 | 11281855.75
10th of Ramadan Railway | IPC#4 HAC | 4 | 10th of Ramadan Railway4 | 2237031 | 2109086.87 | 0 | 2109086.87
East Owainat 5 LOTS | East Owainat Inv. 05 | 5 | East Owainat 5 LOTS5 | 75135244.44 | 30655170.85 | 39446003.33 | 70101174.18
Air Force Project | Air Force Inv . 05 | 5 | Air Force Project5 | 8870694.64 | 6351412.1 | 2217673.66 | 8569085.76
Cairo Monorail - 6th October | IPC#2 Monorail | 2 | Cairo Monorail - 6th October2 | 661500 | 588301 | 0 | 588301
French District | INV (1) Final | 1 | French District1 | 118269 | 110271 | 0 | 110271
NUCA R05 - Z02 | R05 Zone 2 IPC016 | 16 | NUCA R05 - Z0216 | 17343363.3 | 13513254.955 | 1788090.7 | 15301345.655
LAYAN Substation | 10824 |  | LAYAN Substation | 188174.572 | 312369.82 | 0 | 156184.91
Ahl Misr Walkway | IPC03 | 3 | Ahl Misr Walkway3 | 780648 | 650681.36 | 0 | 650681.36
Ahl Misr P3 – Zamalek Sector | IPC#1 - Ahl Misr Gha | 1 | Ahl Misr P3 – Zamalek Sector1 | 1354340 | 1310323.95 | 0 | 1310323.95
MDF Factory | MDF IPC02 | 2 | MDF Factory2 | 6157903.81 | 7093735.0205 | 1616449.75 | 8710184.7705
East Owainat 5 LOTS | East Owainat Inv.2 V | 2 | East Owainat 5 LOTS2 | 48368024.66 | 19353246 | 25393212.95 | 44746458.95
Cairo-Alex Railway | Cairo Alex IPC08 | 8 | Cairo-Alex Railway8 | 10272730.48 | 7275497.89 | 1027273.05 | 8302770.94
Akhmem Assiut | Ref.Ret Asuit. akhm |  | Akhmem Assiut | 36316843.16 | 36316843.16 | 0 | 36316843.16
AWEER POWER STATION 'H' Phase | ENG/043 |  | AWEER POWER STATION 'H' Phase | 181703.73 | 190788.9165 | 0 | 190788.9165
LAYAN Substation | 10742 |  | LAYAN Substation | 109607.22 | 90973.98 | 0 | 90973.98
Racecores 3092-16 132KV C | 10904 |  | Racecores 3092-16 132KV C | 2938654.4 | 2439083.15 | 0 | 2439083.15
Central Bus Station | inv ( 1 ) 30112021 | 1 | Central Bus Station1 | 1908940 | 1908940 | 0 | 1908940
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC018 | 18 | EMAAR-Pkg#162/163- Marassi18 | 12923817.91 | 16022593.1355 | 1927005.65 | 17949598.7855
Le Galawa Hotel Resort | 23000001 |  | Le Galawa Hotel Resort | 510933569 | 510933569 | 0 | 510933569
EDNC Retail & Offices Civil | Sodic Soreal IPC027 | 27 | EDNC Retail & Offices Civil27 | 30032935.16 | 23241827.868 | 72314.2 | 23314142.068
Ain Sokhna Port Development | IPC#1 - Sokhna Port | 1 | Ain Sokhna Port Development1 | 513976 | 477312.78 | 0 | 477312.78
Assuit PP (CP-118) | 2108210011 |  | Assuit PP (CP-118) | 156485.31 | 139663.14 | 24646.44 | 164309.58
Taval Sarai 52 | IPC-13-Saray | 13 | Taval Sarai 5213 | 722955.4 | 468255.3424 | 0 | 468255.3424
Assuit PP (CP-118) | 2108210004 |  | Assuit PP (CP-118) | 1474362.89 | 1273398.7 | 232212.15 | 1505610.85
GOV2 - Infra | GOV 2 - IPC04 | 4 | GOV2 - Infra4 | 1463173.5 | 8057561.675 | 2016166 | 10073727.675
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .27 | 27 | Benban 3/ Toshka 2 LOT 427 | 538032.67 | 479531.63 | 0 | 479531.63
New Heliopolis | Inv. 15 Heliopolise | 15 | New Heliopolis15 | 3830219.65 | 3021627.35 | 376127.6 | 3397754.95
C5 Bridge 2 New Alamein | FPC |  | C5 Bridge 2 New Alamein | 342167.5 | 303527.47 | 0 | 303527.47
Lekela 250MW Wind Farm | SiemensLEKELA IPC013 | 13 | Lekela 250MW Wind Farm13 | 2899145.1 | 2329136.495 | 680919.87 | 3010056.365
Canal Sugar S/s | Inv 12 Sugar S/s | 12 | Canal Sugar S/s12 | 6246012.16 | 6327210.32 | 0 | 6327210.32
Assuit PP (CP-118) | 2110210006 |  | Assuit PP (CP-118) | 1048910.1 | 1101355.61 | 0 | 1101355.61
EGAT Pelletizing Plant | EGAT IPC05 | 5 | EGAT Pelletizing Plant5 | 14565397.44 | 13963438.372 | 1184574.97 | 15148013.342
Cement Factory-Beni Suef | IPC_1_Cement |  | Cement Factory-Beni Suef | 188320 | 177020.8 | 0 | 177020.8
Racecores 3092-17 132KV E | 11025 |  | Racecores 3092-17 132KV E | 310105.62 | 1544326.02 | 0 | 257387.67
Racecores 3092-17 132KV E | 11028 |  | Racecores 3092-17 132KV E | 68166 | 226311.12 | 0 | 56577.78
Kattameya Creeks | Katamya Creeks ipc33 | 33 | Kattameya Creeks33 | 61236907.71 | 47329832.9684 | 16356551.05 | 63686384.0184
Kattameya Creeks | Katameya CreeksIPC24 | 24 | Kattameya Creeks24 | 38710056.01 | 37876579.918 | 2381876.96 | 40258456.878
Ain Sokhna Bridge – RME | IPC#1-Sokhna Bridge | 1 | Ain Sokhna Bridge – RME1 | 1250625 | 1220827.23 | 0 | 1220827.23
Governmental Campus-N2 | 28 |  | Governmental Campus-N2 | 78507.47 | 78446.5317 | 0 | 78446.5317
Water pumping New Obour City | Wat Pump Obour Inv.7 | 7 | Water pumping New Obour City7 | 15594116.43 | 11913117.95 | 1637382.23 | 13550500.18
Water pumping New Obour City | Wat Pump Obour Inv.5 | 5 | Water pumping New Obour City5 | 15963212.25 | 12195071.5 | 1676137.3 | 13871208.8
Zafranaa - Beni Suef | Zafra Souf Final4Ins |  | Zafranaa - Beni Suef | 22452.48 | 9647.41 | 0 | 9647.41
Nuweibaa (Swro) | 2107210002 |  | Nuweibaa (Swro) | 1828538.48 | 1462830.78 | 365707.7 | 1828538.48
Waldorf Astoria Cairo | WALDORF ASTORIA IPC5 | 5 | Waldorf Astoria Cairo5 | 3030560.1 | 5818860.175 | 3770501.32 | 9589361.495
RING ROAD MARYOTIA EXPANSION | El-Marg IPC07+ | 7 | RING ROAD MARYOTIA EXPANSION7 | 18579510.81 | 364133.09 | 0 | 16364133.09
RING ROAD MARYOTIA EXPANSION | Maryotia IPC012 | 12 | RING ROAD MARYOTIA EXPANSION12 | 19159167.62 | 18678770.82 | 0 | 18678770.82
Akhmem Assiut | Ref.Ret Asuit akh 4 |  | Akhmem Assiut | 20000000 | 0 | 0 | 20000000
Assuit PP (CP-118) | 2110210002 |  | Assuit PP (CP-118) | 6599096.98 | 6863060.86 | 0 | 6863060.86
TZ – Offshore E&M Procurement | 456 |  | TZ – Offshore E&M Procurement | 497407.06 | 497407.06 | 0 | 497407.06
TZ – Offshore E&M Procurement | 467 |  | TZ – Offshore E&M Procurement | 566418.92 | 566418.92 | 0 | 566418.92
Mehwar elsalam Lock & Load | MAHWER ELSALAM-IPC1F | 1 | Mehwar elsalam Lock & Load1 | 19057081.62 | 3184783.11 | 13530390 | 16715173.11
Bahr ElBakar – Power Station | IPC#6 - Madkour | 6 | Bahr ElBakar – Power Station6 | 1901604 | 1882587.96 | 0 | 1882587.96
El-Moneeb Bridge | IPC#2 | 2 | El-Moneeb Bridge2 | 991250 | 1146244.31 | 0 | 1146244.31
El Taameer Axis Expansion | IPC#02 | 2 | El Taameer Axis Expansion2 | 457380 | 441543.08 | 0 | 441543.08
EMAAR-Pkg#162/163- Marassi | pkg #177 IPC021 | 21 | EMAAR-Pkg#162/163- Marassi21 | 10986391.5 | 5908549.745 | 710609.62 | 6619159.365
Racecores 3092-16 132KV C | 11292 |  | Racecores 3092-16 132KV C | 7050341.92 | 5851783.79 | 0 | 5851783.79
Racecores 3092-17 132KV E | 11003 |  | Racecores 3092-17 132KV E | 4969 | 4969 | 0 | 4969
Ring Road Bridges Project | inv ( 2 ) Ring R | 2 | Ring Road Bridges Project2 | 132252.5 | 64945.6 | 0 | 64945.6
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.04 | 4 | Mostakbal 2 Package No. (8)4 | 15370280.74 | 12204002.89 | 3227758.96 | 15431761.85
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC026 | 26 | EMAAR- Pkg 140-ITP-Mivida26 | 3380977.62 | 3321493.111 | 0 | 3321493.111
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 02 | 2 | Toshka-04 GIS Substation2 | 15346707.65 | 13688866.77 | 1611404.3 | 15300271.07
Sokhna Port Expansion | SPX.1 IPC 21 | 21 | Sokhna Port Expansion21 | 8474927 | 5788233.11 | 1779735 | 7567968.11
Sokhna Port Expansion | Spx.1 ipc20 | 20 | Sokhna Port Expansion20 | 19625420 | 13204354.1 | 4121338 | 17325692.1
Sokhna Port Expansion | spx1 ipc19 | 19 | Sokhna Port Expansion19 | 14714279.15 | 10049896.6085 | 3089999 | 13139895.6085
Sokhna Port Expansion | sokhna port ipc16 | 16 | Sokhna Port Expansion16 | 35088709.6 | 23966243.524 | 7368630 | 31334873.524
Olympic Multi – Sports Hall | HALLFINISHING2 IPC01 | 1 | Olympic Multi – Sports Hall1 | 9145259 | 7189055 | 809504.75 | 7998559.75
Railway Bridge - Assuit | IPC#04 Assuit | 4 | Railway Bridge - Assuit4 | 3847180 | 3179102.28 | 0 | 3179102.28
AMRIYA WWTP (3RD STAGE) | 2112210001 |  | AMRIYA WWTP (3RD STAGE) | 2057234.48 | 2036565.64 | 0 | 2036565.64
Cairo Monorail - 6th October | IPC#5 - Monorail | 5 | Cairo Monorail - 6th October5 | 1333500 | 1320165 | 0 | 1320165
TZ – Offshore E&M Procurement | 428 |  | TZ – Offshore E&M Procurement | 173418.41 | 138734.73 | 34683.68 | 173418.41
Akhmem Assiut | Ref. Akhmem Asuit4T |  | Akhmem Assiut | 5000000 | 0 | 0 | 5000000
Akhmem Assiut | Ref. Akhmem Asuit5T |  | Akhmem Assiut | 10000000 | 0 | 0 | 10000000
EGY TECH V2 LP-12-21 | 41 |  | EGY TECH V2 LP-12-21 | 4560 | 5198.4 | 0 | 5198.4
New Babil 400/132KV GIS Substa | 2112210006 |  | New Babil 400/132KV GIS Substa | 1646984.75 | 1646984.75 | 0 | 1646984.75
LAYAN Substation | 11263 |  | LAYAN Substation | 570799.88 | 947527.78 | 0 | 473763.89
LAYAN Substation | 11182 |  | LAYAN Substation | 8562 | 8562 | 0 | 8562
New Giza Teaching Hospital | NEW GIZA HOS IPC27 | 27 | New Giza Teaching Hospital27 | 16173467.3 | 3376911.615 | 891532 | 14606809.615
New Giza Teaching Hospital | New Giza Hos ipc(17) | 17 | New Giza Teaching Hospital17 | 21552600.91 | 1077630.05 | 9087007.5955 | 17664637.6455
Central Bus Station | inv ( 2 ) | 2 | Central Bus Station2 | 421520 | 421520 | 0 | 421520
EGAT Lock & Load | EGAT L&L IPC6 | 6 | EGAT Lock & Load6 | 3378839.59 | 3176109.2095 | 337883.96 | 3513993.1695
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC023 | 23 | EMAAR-Pkg#162/163- Marassi23 | 4755868.69 | 4610166.2945 | 572004.39 | 5182170.6845
Industria Sadat | Sadat Indust Inv. 05 | 5 | Industria Sadat5 | 21467211.7 | 26560136.48 | 4508114.46 | 31068250.94
EGAT Pelletizing Plant | EGAT IPC08 | 8 | EGAT Pelletizing Plant8 | 12121253.24 | 11455129.952 | 1150973.42 | 12606103.372
TZ – Offshore E&M Procurement | 437 |  | TZ – Offshore E&M Procurement | 549036.35 | 439229.08 | 109807.27 | 549036.35
TZ – Offshore E&M Procurement | 464 |  | TZ – Offshore E&M Procurement | 183666.84 | 0 | 183666.6 | 183666.6
Taval Sarai 52 | IPC-20-SARAY | 20 | Taval Sarai 5220 | 141230.9 | 19510.0478 | 0 | 19510.0478
Taval Sarai 52 | IPC-19-SARAY | 19 | Taval Sarai 5219 | 386115.9 | 321685.35 | 0 | 321685.35
R05 | IPC-Final-R05 |  | R05 | 1848 | 1533.84 | 0 | 1533.84
TZ – Offshore E&M Procurement | 460 |  | TZ – Offshore E&M Procurement | 257383.87 | 454020.96 | 1030 | 227525.48
Al Montaza Hotels - Alexandria | inv 7-8-9 Montazha | 7 | Al Montaza Hotels - Alexandria7 | 4353038.9 | 4128486.95 | 0 | 4128486.95
Port Said Port Silos | port said ipc21 | 21 | Port Said Port Silos21 | 15886445.71 | 13770443.8984 | 1588644.57 | 15359088.4684
Port Said Port Silos | port said silosipc19 | 19 | Port Said Port Silos19 | 17118439.26 | 14851957.9104 | 1711843.93 | 16563801.8404
Port Said Port Silos | port said silos ipc7 | 7 | Port Said Port Silos7 | 4021476.86 | 3555860.488 | 402147.69 | 3958008.178
Port Said Port Silos | Port Said Silos IPC2 | 2 | Port Said Port Silos2 | 1883535.14 | 1586748.547 | 245081.44 | 1831829.987
Port Said Port Silos | IPC 7 SUPPLY EGP | 7 | Port Said Port Silos7 | 5552464.75 | 40688461.64 | 4441971.84 | 5641304.185
Port Said Port Silos | PORT SAIED IPC 28 | 28 | Port Said Port Silos28 | 3379589.94 | 2663473.997 | 337959 | 3001432.997
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC 20 | 20 | EMAAR-Pkg#162/163- Marassi20 | 4337585.5 | 2512715.615 | 687025.94 | 3199741.555
Angola Emergency fast-track | ANG-Cam-Inv 5 - Ints | 5 | Angola Emergency fast-track5 | 904750.97 | 663364.14 | 0 | 663364.14
Luxor North Axis Bridge | IPC#3 Luxor offshore | 3 | Luxor North Axis Bridge3 | 843750 | 814508.97 | 0 | 814508.97
IKEA Extension MoA | ikea 2 ipc04 | 4 | IKEA Extension MoA4 | 327656.68 | 441442.804 | 0 | 441442.804
Ghana Street lighting | MIDA Ins.inv.11 | 11 | Ghana Street lighting11 | 53870.62 | 48483.56 | 0 | 48483.56
Racecores 3092-16 132KV C | 11405 |  | Racecores 3092-16 132KV C | 19200 | 20160 | 0 | 20160
EGAT Pelletizing Plant | egat water tank ipc8 | 8 | EGAT Pelletizing Plant8 | 307226.2 | 304153.94 | 0 | 304153.94
Racecores 3092-17 132KV E | 11369 |  | Racecores 3092-17 132KV E | 109587.78 | 92601.68 | 0 | 92601.68
ElSewedy HQ Internal Finishing | ELSEWEDY HQ ipc12 | 12 | ElSewedy HQ Internal Finishing12 | 11990805.42 | 8175767.971 | 2987529.52 | 14329596.631
159E | 11323 |  | 159E | 281422.51 | 281422.51 | 0 | 281422.51
Koning Food LP-04-20 | 47 |  | Koning Food LP-04-20 | 35420 | 40378.8 | 0 | 40378.8
LP-01-22 Citrix Workspace | 73 |  | LP-01-22 Citrix Workspace | 48245.58 | 26773.9404 | 0 | 26773.9404
Faculty of Medicine | FacultyMedcine IPC08 | 8 | Faculty of Medicine8 | 16934024 | 14328324.06 | 846701.2 | 15175025.26
Luxor North Axis Bridge | IPC#4 Luxor Offshore | 4 | Luxor North Axis Bridge4 | 874800 | 804816 | 0 | 804816
Port Said Subs 220/66 | Port Said Inv. 5 | 5 | Port Said Subs 220/665 | 69948870.51 | 45116620 | 17487217.63 | 62603837.63
West Port Said 220 kV GIS | P-45-Portsaid Inv.2$ | 2 | West Port Said 220 kV GIS2 | 323893.33 | 258802.4734 | 34008.8 | 292811.2734
TZ – Offshore E&M Procurement | 451 |  | TZ – Offshore E&M Procurement | 321582.39 | 241186.79 | 48237.36 | 289424.15
Abo Quir - Badr 500KV | Inv 73 Abu Quir Badr | 73 | Abo Quir - Badr 500KV73 | 972401.74 | 384098.71 | 194480.35 | 578579.06
LP-23-21 UMC – 5000 RFID | 70 |  | LP-23-21 UMC – 5000 RFID | 27650 | 31244.5 | 0 | 31244.5
LAYAN Substation | 11747 |  | LAYAN Substation | 177273.88 | 294274.628 | 0 | 147137.314
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 15 | 15 | Suez Gulf/S4 - 500KV OHTL15 | 38381.1 | 25134.23 | 0 | 25134.23
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 06 | 6 | Hosh Essa 220 KV OHTL6 | 1661546.67 | 998588.4 | 174462.4 | 1173050.8
MDF Factory | mdf factory2 ipc01 | 1 | MDF Factory1 | 474511.19 | 487660.3966 | 0 | 487660.3966
Bridge Axis Firdaws | inv ( final ) |  | Bridge Axis Firdaws | 1609889.6 | 865548.8818 | 0 | 865548.8818
Infra Project 4428 | 220421008 |  | Infra Project 4428 | -151428571.43 | -159000000.0015 | 0 | -159000000.0015
Miscellaneous Projects | 220321001 |  | Miscellaneous Projects | 131175 | 149539.5 | 0 | 149539.5
MDF Factory | MDF Factory ipc 36 | 36 | MDF Factory36 | 24401575.22 | 10167393.0388 | 10247566.72 | 20414959.7588
LAYYAH CCPP | 522 |  | LAYYAH CCPP | 2824860 | 2584455 | 240405 | 2824860
Racecores 3092-15 132KV A | 11454 |  | Racecores 3092-15 132KV A | 177580.98 | 294784.418 | 0 | 147392.209
Phosfat | Ret Phosfat T |  | Phosfat | 170472.3 | 170472.3 | 0 | 170472.3
October Dry Port | Dry Port Inv. 08 | 8 | October Dry Port8 | 21727736.72 | 14779027.61 | 5703530.89 | 20482558.5
October Dry Port | Dry Port Inv. 06 | 6 | October Dry Port6 | 12004782.93 | 13713419.57 | 3151255.52 | 16864675.09
Waldorf Astoria Cairo | Waldorf- IPC 19 | 19 | Waldorf Astoria Cairo19 | 9183542.25 | 1409611.34 | 3376215.79 | 4887548.4025
Waldorf Astoria Cairo | waldorf IPC 12 | 12 | Waldorf Astoria Cairo12 | 7707398.93 | 2602999.7165 | 2658217.51 | 5261217.2265
Mivida BP#189 | Pkg#189 ipc02 | 2 | Mivida BP#1892 | 16089263.96 | 19214635.628 | 2238745.48 | 21453381.108
Mivida BP#189 | pkg #189 ipc 11 | 11 | Mivida BP#18911 | 23000800.56 | 19983996.088 | 2379387.42 | 22363383.508
Wadi Halfa Port | wady halfa ipc 4 | 4 | Wadi Halfa Port4 | 4379885.32 | 3015154.5668 | 919775.92 | 3934930.4868
Wadi Halfa Port | wady halfa ipc02 | 2 | Wadi Halfa Port2 | 11905090.1 | 8196261.45 | 2500069.32 | 10696330.77
Wadi Halfa Port | Wadi Halfa ipc 01 | 1 | Wadi Halfa Port1 | 33029518 | 22733362.34 | 6936198.78 | 29669561.12
Racecores 3092-17 132KV E | 11599 |  | Racecores 3092-17 132KV E | 96761.48 | 160624.048 | 0 | 80312.024
Racecores 3092-17 132KV E | 11541 |  | Racecores 3092-17 132KV E | 691244.2769 | 4088709.9451 | 0 | 584101.4207
Ghana Street lighting | MIDA Sply.inv.12 | 12 | Ghana Street lighting12 | 69621.7 | 62659.53 | 0 | 62659.53
Abou Ghaleb Bridge | abo Ghaleb ipc02 | 2 | Abou Ghaleb Bridge2 | 669446.33 | 662751.87 | 0 | 662751.87
Abou Ghaleb Bridge | ABO GHALEB IPC01 | 1 | Abou Ghaleb Bridge1 | 12157987.62 | 1998969.021 | 0 | 7589747.021
Industria Sadat | Sadat Indust Inv. 04 | 4 | Industria Sadat4 | 14944151.43 | 10726695.29 | 3138271.8 | 13864967.09
Kuwait | Inv.4988/Sp/H&J-02 | 4988 | Kuwait4988 | 22585.37 | 21456.1 | 0 | 21456.1
New Babil 400/132KV GIS Substa | 220421003 |  | New Babil 400/132KV GIS Substa | 825040.8 | 825040.8 | 0 | 825040.8
New Babil 400/132KV GIS Substa | 220421002 |  | New Babil 400/132KV GIS Substa | 247512.24 | 247512.24 | 0 | 247512.24
Elhegaz | D0028-OB-Dec-2020D.M | 2020 | Elhegaz2020 | 19094677.06 | 19094677.06 | 0 | 19094677.06
HST Bridges-Sokhna & Mahager | hst sokhna ipc01 | 1 | HST Bridges-Sokhna & Mahager1 | 67034460.71 | 56136552.2355 | 0 | 59136552.2355
GOV2 - Infra | Gov 2 - IPC03 | 3 | GOV2 - Infra3 | 9273010.19 | 7895653.18 | 2158016.15 | 10053669.33
Faculty of Medicine | MANSOURA FINISHIPC28 | 28 | Faculty of Medicine28 | 39981757.14 | 0 | 5997263.57 | 5997263.57
Faculty of Medicine | Mansora Finish ipc06 | 6 | Faculty of Medicine6 | 4638751.43 | 3460801.25 | 695812.71 | 4156613.96
MDF Factory | MDF FACTORY3 IPC03 | 3 | MDF Factory3 | 1238493.58 | 897907.8412 | 352970.67 | 1250878.5112
Racecores 3092-16 132KV C | 11620 |  | Racecores 3092-16 132KV C | 2626.81 | 2626.81 | 0 | 2626.81
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 19 | 19 | Benban 500 K.V/95 K.M19 | 641158.81 | 494337.86 | 67321.68 | 561659.54
EMAAR-Pkg#162/163- Marassi | Pkg#177 IPC32 | 32 | EMAAR-Pkg#162/163- Marassi32 | 5829703.87 | 10452697.3335 | 2179865.32 | 12632562.6535
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 2490376.38 | 1682555.26 | 235322.57 | 2281542.72
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv15 | 15 | Marsa Alam/ Bernes LOT2 OHTL15 | 8912653.97 | 6717169.16 | 0 | 6717169.16
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv12 | 12 | Marsa Alam/ Bernes LOT2 OHTL12 | 148021.88 | 133009.55 | 0 | 133009.55
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv10 | 10 | Marsa Alam/ Bernes LOT2 OHTL10 | 4517079.02 | 4073899.58 | 0 | 4073899.58
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .25 | 25 | Benban 3/ Toshka 2 LOT 425 | 36459593.62 | 29137204.39 | 1814998.04 | 30952202.43
Ora Zed Landscape Ph1 | Ora landscape ipc 20 | 20 | Ora Zed Landscape Ph120 | 1318831.15 | 1177303.85 | 505803.07 | 1683106.92
Ora Zed Landscape Ph1 | Ora Landscape ipc 19 | 19 | Ora Zed Landscape Ph119 | 1347822.27 | 618692.48 | 141521.34 | 760213.82
Ora Zed Landscape Ph1 | Ora Landsca ipc13-14 | 13 | Ora Zed Landscape Ph113 | 1148717.83 | 868255.79 | 120615.37 | 988871.16
AWEER POWER STATION 'H' Phase | LOC/026 |  | AWEER POWER STATION 'H' Phase | 529432.1 | 464723.7331 | 58825.79 | 523549.5231
Zambia Project | SCD4x/0013 |  | Zambia Project | 30567.27 | 30537.52 | 0 | 30537.52
2 track mach | 2 track mach Inv.01 | 1 | 2 track mach1 | 10526315.79 | 3000000 | 1200000 | 4200000
EMAAR-Pkg#162/163- Marassi | pkg#177-IPC35 | 35 | EMAAR-Pkg#162/163- Marassi35 | 20620247.8 | 15928851.3665 | 3692100.026 | 19620951.3925
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $10 | 10 | Benban 3/ Toshka 2 LOT 410 | 150190.95 | 125704.4 | 15770.05 | 141474.45
PLAYA ROOF & Wet Areas | IPC-10-PLAYA ROOF | 10 | PLAYA ROOF & Wet Areas10 | 234166.18 | 177538 | 0 | 177538
EGAT Pelletizing Plant | egat ipc 13 | 13 | EGAT Pelletizing Plant13 | 22223108.96 | 21580273.568 | 1531759.75 | 23112033.318
EGAT Pelletizing Plant | EGAT IPC04 | 4 | EGAT Pelletizing Plant4 | 7555014.44 | 7145933.742 | 711281.28 | 7857215.022
New Giza Teaching Hospital | new giza hos ipc05 | 5 | New Giza Teaching Hospital5 | 14819091.38 | 10433639.459 | 2251618.11 | 12685257.569
Benban 3/ Toshka 2 Lot 6 | Ref-Ret-Toshka Lot6T |  | Benban 3/ Toshka 2 Lot 6 | 39490847.01 | 39490847.01 | 0 | 39490847.01
Benban 500 K.V / 100 K.M | Ref-Ret-Benba lot1T |  | Benban 500 K.V / 100 K.M | 15330832.04 | 15330832.04 | 0 | 15330832.04
LAYYAH CCPP | 505 |  | LAYYAH CCPP | 493529 | 429174.42 | 74029.35 | 503203.77
LAYYAH CCPP | 507 |  | LAYYAH CCPP | 5141880 | 4527710.6 | 842908 | 5370618.6
LAYYAH CCPP | 502 |  | LAYYAH CCPP | 256625 | 229037.81 | 38493.75 | 267531.56
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC 22 | 22 | EMAAR-Pkg#162/163- Marassi22 | 2631392.92 | 2390070.524 | 0 | 2390070.524
Ain Sokhna Port Development | IPC#15 - Sokhna Port | 15 | Ain Sokhna Port Development15 | 493848 | 365799.5 | 0 | 457249.37
Infra Project 2531 | 220321001 |  | Infra Project 2531 | 480723957.15 | 410882610 | 0 | 410882610
GSM-02-22 IHS | 85 |  | GSM-02-22 IHS | 2215649.1 | 2525839.99 | 0 | 2525839.99
TZ – Offshore E&M Procurement | 469 |  | TZ – Offshore E&M Procurement | 274863.23 | 274863.23 | 0 | 274863.23
Zone(J) South Valley Toshka | South Valley Inv. 15 | 15 | Zone(J) South Valley Toshka15 | 55134638.9 | 33347809.15 | 6205443.52 | 39553252.67
PLAYA ROOF & Wet Areas | IPC-9-PLAYA ROOF | 9 | PLAYA ROOF & Wet Areas9 | 64076.15 | 54983.74 | 0 | 54983.74
Marassi - Anti carbonation | IPC-01-PK177.ANTI | 1 | Marassi - Anti carbonation1 | 234306 | 207477.96 | 0 | 207477.96
ORA ZED-Ph 2-Pkgs A&D | ORAZEHD PH.2 IPC8 | 8 | ORA ZED-Ph 2-Pkgs A&D8 | 8766077.29 | 9151883.2345 | 1112688.66 | 10264571.8945
Playa Epoxy | IPC-Playa Epoxy |  | Playa Epoxy | 492872.4 | 422930.8889 | 0 | 422930.8889
seashell Playa | IPC-19-Playa | 19 | seashell Playa19 | 527180.57 | 452373.64 | 0 | 452373.64
seashell Playa | IPC-10-PLAYA | 10 | seashell Playa10 | 280285.45 | 195667.29 | 44845.67 | 240512.96
Egyptian Exchange building | IPC-7-Borsa | 7 | Egyptian Exchange building7 | 14146.6 | 12502.1547 | 0 | 12502.1547
Egyptian Exchange building | IPC-4-BORSA | 4 | Egyptian Exchange building4 | 126224.8 | 111772.06 | 0 | 111772.06
Marassi - Anti carbonation | IPC-2-PK#177Anticarb | 2 | Marassi - Anti carbonation2 | 17867.7 | 317.84 | 0 | 317.84
Egyptian Exchange building | IPC-05-BORSA | 5 | Egyptian Exchange building5 | 99273.45 | 87906.65 | 0 | 87906.65
Sodic East | 10093 |  | Sodic East | 180165.97 | 159807.15 | 0 | 159807.15
EMAAR-Pkg#162/163- Marassi | pkg#177 ipc22 | 22 | EMAAR-Pkg#162/163- Marassi22 | 7589823.48 | 3656481.974 | 439757.87 | 4096239.844
BKG#178-Lagoon Discharge | PKG #178 IPC06 | 6 | BKG#178-Lagoon Discharge6 | 4524611.34 | 2967821.117 | 0 | 2967821.117
RING ROAD MARYOTIA EXPANSION | MARIOTYIA IPC17 | 17 | RING ROAD MARYOTIA EXPANSION17 | 41585303.99 | 41169450.9495 | 0 | 41169450.9495
NUCA R05 - Z02 | R05 Zone2 IPC017 | 17 | NUCA R05 - Z0217 | 19906898.8 | 21166577.92 | 2865993.9 | 24032571.82
LINX Tower | inv ( 2 ) LINX | 2 | LINX Tower2 | 283672.26 | 266651.933 | 0 | 266651.933
Ain Sokhna Port Development | IPC#17 -Sokhna Port | 17 | Ain Sokhna Port Development17 | 679041 | 510216.64 | 0 | 637770.8
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC25 | 25 | EMAAR-Pkg#162/163- Marassi25 | 12934137.54 | 12395959.047 | 0 | 12395959.047
SSC Suez Steel Company Project | int&ret sup sscipc 8 | 8 | SSC Suez Steel Company Project8 | 2489471.85 | 1886800.519 | 926302.67 | 2813103.189
SSC Suez Steel Company Project | Int&Ret APP(ssc)ipc6 | 6 | SSC Suez Steel Company Project6 | 7103010.22 | 6571472.514 | 921113.82 | 7492586.334
ORA ZED-Ph 2-Pkgs A&D | ora zed 2 ipc 7 | 7 | ORA ZED-Ph 2-Pkgs A&D7 | 42383851.59 | 34124964.2595 | 4049151.33 | 38174115.5895
ElSewedy HQ Internal Finishing | el sewedy hq ipc13 | 13 | ElSewedy HQ Internal Finishing13 | 23373232.29 | 869511.3245 | 15100757.78 | 25970269.1045
Kattameya Creeks | Katameya CreeksIPC18 | 18 | Kattameya Creeks18 | 42935687.01 | 41641258.1345 | 3011856.35 | 44653114.4845
EPICO 3 Facility | Eipico ipc11 | 11 | EPICO 3 Facility11 | 27259074.64 | 23263190.12 | 10328302.36 | 33591492.48
EPICO 3 Facility | Eipico ipc 10 | 10 | EPICO 3 Facility10 | 9818518.79 | 0 | 2172763.92 | 2172763.92
Bahr ElBakar – Power Station | IPC#8 Madkour | 8 | Bahr ElBakar – Power Station8 | 2993842.95 | 2486747.58 | 0 | 2486747.58
Playa Epoxy | 02 |  | Playa Epoxy | 137956.4 | 62280.39 | 0 | 62280.39
Sultana Malak Restoration | sultana malk3 ipc01 | 1 | Sultana Malak Restoration1 | 12615078.24 | 10367530 | 0 | 10367530
Al-Parco | INV ( 1 ) ALparco | 1 | Al-Parco1 | 1879350 | 1766589 | 0 | 1766589
EGAT Pelletizing Plant | Elco egat ipc14 | 14 | EGAT Pelletizing Plant14 | 8283062.86 | 7794639.393 | 819745.98 | 8614385.373
EGAT Pelletizing Plant | Elco Egat ipc15 | 15 | EGAT Pelletizing Plant15 | 20298475.24 | 19186530.252 | 1923884 | 21110414.252
Diplomatic District - Infra | Diplomatic ipc 13 | 13 | Diplomatic District - Infra13 | 16548362.5 | 5939031.605 | 900944.24 | 6839975.845
HSR-6th of October | IPC#3 HSR | 3 | HSR-6th of October3 | 1408920 | 1225760.4 | 0 | 1225760.4
CS-20 Mall | inv ( 2 ) CS-20 | 2 | CS-20 Mall2 | 971119.35 | 912852.19 | 0 | 912852.19
El Khatatba Bridge | El Khataba ipc3+4 | 3 | El Khatatba Bridge3 | 24106000 | 20047104.85 | 0 | 20047104.85
Sokhna Port Expansion | sokhna port ex ipc5 | 5 | Sokhna Port Expansion5 | 84601518.57 | 59074965.265 | 17766318.9 | 76841284.165
Railway Bridge - El Hammam | IPC#1 - ElHammam Pro | 1 | Railway Bridge - El Hammam1 | 1803303.5 | 1694038.06 | 0 | 1694038.06
Port Said Port Silos | port said silos ipc4 | 4 | Port Said Port Silos4 | 3348506.91 | 2971799.8855 | 334850.69 | 3306650.5755
EGAT Pelletizing Plant | plant supp Ro puipc4 | 4 | EGAT Pelletizing Plant4 | 2453301.65 | 2216012.061 | 556218.8 | 2772230.861
Kafr Shokr Bridge | KafrShokr Brdg IPC06 | 6 | Kafr Shokr Bridge6 | 2805242.86 | 444257.73 | 0 | 2444257.73
Port Said Port Silos | port said silos ipc5 | 5 | Port Said Port Silos5 | 5318356.37 | 4663281.2785 | 531835.64 | 5195116.9185
EL -mahager Bridge Ain sokhna | ipc 2 mahger | 2 | EL -mahager Bridge Ain sokhna2 | 3450000 | 5737910.4 | 0 | 3058955.2
EL -mahager Bridge Ain sokhna | IPC 2 ELMAHAGER | 2 | EL -mahager Bridge Ain sokhna2 | 3450000 | 0 | 0 | 3450000
Egat Rolling Mill no.4 | Rolling mill ipc06 | 6 | Egat Rolling Mill no.46 | 5743580.95 | 4622529.1875 | 1350795 | 5973324.1875
EMAAR-Pkg#162/163- Marassi | pkg#163- IPC28 | 28 | EMAAR-Pkg#162/163- Marassi28 | 17622733.92 | 19371561.356 | 0 | 19371561.356
WADY EL-NATROUN BRIDGE(HST) | IPC#4 - Wadi El Natr | 4 | WADY EL-NATROUN BRIDGE(HST)4 | 717360 | 512147.7 | 0 | 642434.62
EDNC Hardscape Package | sorealhardscapeIPC10 | 10 | EDNC Hardscape Package10 | 3106667.35 | 3067833.9875 | 0 | 3067833.9875
EGAT Injection | IPC01EGATINJECTION | 1 | EGAT Injection1 | 175000 | 149217.5 | 0 | 149217.5
EGAT Pelletizing Plant | EGAT - IPC17 | 17 | EGAT Pelletizing Plant17 | 16943574.98 | 15969082.719 | 1652235.26 | 17621317.979
Expansion of Ring Road NRCC | IPC#2 NRCC | 2 | Expansion of Ring Road NRCC2 | 849400 | 522665.3 | 0 | 522665.3
Kattameya Creeks | Katameya IPC21 | 21 | Kattameya Creeks21 | 36255948.47 | 35259435.93 | 2446750.47 | 37706186.4
Waldorf Astoria Cairo | waldorf IPC10 | 10 | Waldorf Astoria Cairo10 | 9739259.16 | 4982321 | 5090575.7 | 10072896.7
Hyper One Badr | INV ( 4:9 ) Hipper | 4 | Hyper One Badr4 | 2586336.17 | 2301839.19 | 0 | 2301839.19
Faculty of Medicine | mansorafinshing ipc1 | 1 | Faculty of Medicine1 | 8775226.67 | 6542217.0052 | 1316284 | 7858501.0052
SODIC Allegria Villa f100 | Sodic VillaF100 IPC1 | 1 | SODIC Allegria Villa f1001 | 5146090.48 | 1600000 | 3776500 | 5376500
Air Defense College | Air def4 IPC2 | 2 | Air Defense College2 | 527000 | 443595 | 0 | 443595
Air Defense College | Air def2 IPC3 | 3 | Air Defense College3 | 6165128 | 2399535 | 0 | 5221935
HSR-6th of October | IPC#4 HSR | 4 | HSR-6th of October4 | 307440 | 267472.8 | 0 | 267472.8
GOV2 - Infra | GOV 2 IPC09 | 9 | GOV2 - Infra9 | 39828531.57 | 12242703.7 | 1976985.55 | 14219689.25
RING ROAD MARYOTIA EXPANSION | ESC.1:17 (Estsmar) |  | RING ROAD MARYOTIA EXPANSION | 14285714.29 | 13925317.49 | 0 | 13925317.49
MDF Factory | MDF 2 - IPC 12 | 12 | MDF Factory12 | 447300.74 | 451773.7436 | 0 | 451773.7436
PVD - El Hammam | IPC1 PVD | 1 | PVD - El Hammam1 | 312473.03 | 276226.16 | 0 | 276226.16
EMAAR-Pkg#162/163- Marassi | pkg#177- IPC36 | 36 | EMAAR-Pkg#162/163- Marassi36 | 42116952.2 | 36331150.12 | 26252727.91 | 62583878.03
GOV2 - Infra | GOV2 IPC010 | 10 | GOV2 - Infra10 | 19212935.81 | 23359592.71 | 2865073.75 | 26224666.46
Kattameya Creeks | Katameya IPC 22 | 22 | Kattameya Creeks22 | 32375932.35 | 31299260.0175 | 2371709.63 | 33670969.6475
Diplomatic District - Infra | DIPLOMATIC IPC10 | 10 | Diplomatic District - Infra10 | 16607651.9 | 18657092.23 | 2398226.8 | 21055319.03
Diplomatic District - Infra | diplomatic ipc 14 | 14 | Diplomatic District - Infra14 | 12173381.9 | 4045239.4587 | 678285.3 | 4723524.7587
WADY EL-NATROUN BRIDGE(HST) | IPC#11 Wadinatron | 11 | WADY EL-NATROUN BRIDGE(HST)11 | 1601250 | 1454095.12 | 0 | 1454095.12
Pushing Tunnel | Inv ( 4 ) T. Pushing | 4 | Pushing Tunnel4 | 5985000 | 4836478.37 | 0 | 4836478.37
Pushing Tunnel | Inv ( 2 ) T. Pushing | 2 | Pushing Tunnel2 | 3231900 | 2511698.39 | 0 | 2511698.39
HSR-6th of October | IPC9 HSR6th | 9 | HSR-6th of October9 | 1136000 | 918710.41 | 0 | 918710.41
Seashell Playa 5 Villas | seashell playa-IPC3 | 3 | Seashell Playa 5 Villas3 | 383747.94 | 255255.5 | 0 | 255255.5
Al-Parco | INV ( 2 ) ALparco | 2 | Al-Parco2 | 285175 | 268064.5 | 0 | 268064.5
HSR-6th of October | IPC#6 HSR | 6 | HSR-6th of October6 | 596290 | 518772.3 | 0 | 518772.3
Al-Ula Towers - ( 2 ) | INV ( 1 ) Al-Ula-2 | 1 | Al-Ula Towers - ( 2 )1 | 3385443.4 | 2800000 | 0 | 2800000
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC (29) | 29 | EMAAR-Pkg#162/163- Marassi29 | 20296742.21 | 19850779.098 | 0 | 19850779.098
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 33 | 33 | ORA ZED - Ph 01B - Pkgs A&D33 | 18602239.47 | 12164893.39 | 4938944.34 | 17103837.73
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc32 | 32 | ORA ZED - Ph 01B - Pkgs A&D32 | 17918865.67 | 8010573.17 | 10032784.1 | 18043357.27
DP World Basin 2 Ph2 | DP World ph.2 IPC2 | 2 | DP World Basin 2 Ph22 | 31312811.13 | 19472869.78 | 8394835.91 | 27867705.69
October Under-Railway Tunnel | october tunnel ipc 5 | 5 | October Under-Railway Tunnel5 | 3663513.71 | 2856009 | 0 | 2856009
Irrigation Tank | IPC2&3TR0061 | 2 | Irrigation Tank2 | 727407.2 | 591238.85 | 0 | 591238.85
EMAAR-Pkg#162/163- Marassi | PKG#177- IPC41 | 41 | EMAAR-Pkg#162/163- Marassi41 | 16303582.18 | 180103.25 | 3311188.669 | 3491291.919
MDF Factory | MDF Factory ipc (24) | 24 | MDF Factory24 | 20265495.39 | 2096504.5956 | 13271764.92 | 15368269.5156
ORA ZED-Ph 2-Pkgs A&D | ORA PH.2 - IPC15 | 15 | ORA ZED-Ph 2-Pkgs A&D15 | 20441047.55 | 11268654.1775 | 1426947.75 | 12695601.9275
SSC Suez Steel Company Project | R.O. Sup. adj. IPC4 | 4 | SSC Suez Steel Company Project4 | 6753929.79 | 7294244.1727 | 0 | 7294244.1727
Sokhna Port Expansion | spx2 ipc 2 | 2 | Sokhna Port Expansion2 | 24129951.4 | 10628517.7515 | 4825990.28 | 21454508.0315
Railway Bridge - El Hammam | IPC 7 elswedy | 7 | Railway Bridge - El Hammam7 | 949018.9 | 771783.98 | 0 | 771783.98
WADY EL-NATROUN BRIDGE(HST) | IPC no15 wadinatroun |  | WADY EL-NATROUN BRIDGE(HST) | 1853290 | 1346373.51 | 0 | 1346373.51
Kattameya Creeks | katamya creeks ipc32 | 32 | Kattameya Creeks32 | 52360770.17 | 41216438 | 13238762.34 | 54455200.34
Air Defense College | Air Def finish IPC3 | 3 | Air Defense College3 | 3051528 | 2335760 | 0 | 2572876
New Giza Teaching Hospital | new geza Hosp ipc 14 | 14 | New Giza Teaching Hospital14 | 21572565.8 | 16275653.05 | 2250467.33 | 18526120.38
PVD - El Hammam | IPC#3 PVD Hamam | 3 | PVD - El Hammam3 | 217061 | 169279.39 | 0 | 169279.39
Kattameya Creeks | Katamya Creeks ipc34 | 34 | Kattameya Creeks34 | 82997244.56 | 70308953 | 15196003.57 | 85504956.57
ORA-ZED Towers P01B | IPC008 | 8 | ORA-ZED Towers P01B8 | 360594 | 319305.99 | 0 | 319305.99
Katameya Creeks - RME | IPC0006 | 6 | Katameya Creeks - RME6 | 102468.56 | 90735.9 | 0 | 90735.9
MAF HQ Renovation | Carrefour H off ipc3 | 3 | MAF HQ Renovation3 | 8617729.61 | 5795423.13 | 2262154.02 | 8057577.15
SEASHELL TECHNICAL ROOM | IPC06TR0065 | 6 | SEASHELL TECHNICAL ROOM6 | 115200.05 | 99486.77 | 0 | 99486.77
Ministries Buildings | Minis Alloc IPc12 | 12 | Ministries Buildings12 | 13385562 | 22553870 | 0 | 11276935
Waldorf Astoria Cairo | Waldrof Asto ipc 18 | 18 | Waldorf Astoria Cairo18 | 10421093.88 | 3217413.914 | 4923966.86 | 12961136.774
MDF Factory | Mdf local ipc 14 | 14 | MDF Factory14 | 12194201.3 | 10315795 | 2000199.6458 | 12315994.6458
EPICO 3 Facility | EIPICO IPC (5) | 5 | EPICO 3 Facility5 | 13210447.27 | 10064340.12 | 3404105.19 | 13468445.31
Seashell Playa 5 Villas | Playa c045 - ipc 1 | 1 | Seashell Playa 5 Villas1 | 71198.7 | 18553.19 | 0 | 18553.19
Port Said Port Silos | port saidsilos ipc15 | 15 | Port Said Port Silos15 | 10044463.56 | 8897631.4024 | 1004446.36 | 9902077.7624
Air Defence College | IPC0013 TR0046 | 13 | Air Defence College13 | 1607066.54 | 1364399.49 | 0 | 1364399.49
Air Defense College | Air Dev16 IPC4 | 4 | Air Defense College4 | 6831127 | 462800 | 0 | 5808267
SSC Suez Steel Company Project | Shutdown smp2 ipc(2) | 2 | SSC Suez Steel Company Project2 | 11073867.25 | 5979888.32 | 5536933.62 | 11516821.94
SSC Suez Steel Company Project | Shutdown smp1 -ipc 2 | 2 | SSC Suez Steel Company Project2 | 17650842.77 | 8648912.9484 | 8825421.39 | 17474334.3384
NUCA R05 - Z02 | R05(2) ipc 35 | 35 | NUCA R05 - Z0235 | 18335541.14 | 14613599.29 | 1875883.5 | 16489482.79
Air Defence College | 11 |  | Air Defence College | 190510.2 | 161743.16 | 0 | 161743.16
ORA-ZED Towers P01B | IPC009 | 9 | ORA-ZED Towers P01B9 | 202026 | 178894.02 | 0 | 178894.02
Get Business Complex | INV ( 7 ) GET | 7 | Get Business Complex7 | 1164549.6 | 1094676.624 | 0 | 1094676.624
RING ROAD MARYOTIA EXPANSION | mariotya ipc20 be16 | 20 | RING ROAD MARYOTIA EXPANSION20 | 28422356.38 | 9762780.95 | 0 | 9762780.95
Mohamed Nader Villa's | Mohamed N villa ipc1 | 1 | Mohamed Nader Villa's1 | 4289255.33 | 2070213.9265 | 2165425.71 | 4235639.6365
Air Defense College | Air dev Shapcat IPC1 | 1 | Air Defense College1 | 23046232 | 3048570 | 16200000 | 19248570
Cairo-Alex Railway | Cairo-alex ipc 34 | 34 | Cairo-Alex Railway34 | 40544596.19 | 28066864.95 | 4257182.6 | 32324047.55
Cairo-Alex Railway | Cairo Alex IPC010 | 10 | Cairo-Alex Railway10 | 21071680 | 14375414.95 | 2107168 | 16482582.95
Cairo-Alex Railway | Cairo-Alex IPC013 | 13 | Cairo-Alex Railway13 | 22436876.43 | 13355344.72 | 3111549.1 | 16466893.82
Sixty Iconic Tower | Inv ( 3 ) sixty | 3 | Sixty Iconic Tower3 | 127635.78 | 116807.63 | 0 | 116807.63
ORA ZED-Ph 2-Pkgs A&D | Ora ph 2 ipc (20) | 20 | ORA ZED-Ph 2-Pkgs A&D20 | 4105367.03 | 3188540.2834 | 403369.56 | 3591909.8434
Ora Zed Landscape Ph1 | ora landscape ipc 6 | 6 | Ora Zed Landscape Ph16 | 3759868.55 | 3318083.9875 | 394786.2 | 3712870.1875
Air Defense College | Air Finsh IPC4 | 4 | Air Defense College4 | 2385006 | 1808529.97 | 0 | 2010982.97
Port Said Port Silos | portsaid silos ipc20 | 20 | Port Said Port Silos20 | 12988783.81 | 8189528.9592 | 4298878.38 | 12488407.3392
EGAT Pelletizing Plant | IPC1 PLANTSUPPLY RO | 1 | EGAT Pelletizing Plant1 | 5322406.46 | 691912.8398 | 5322406.46 | 6014319.2998
EGAT Pelletizing Plant | CementPriceEscaltion |  | EGAT Pelletizing Plant | 7000000.28 | 7280000.294 | 0 | 7280000.294
EPICO 3 Facility | Eipico Ipc ( 8) | 8 | EPICO 3 Facility8 | 18125037.75 | 20317361.34 | 6844285.93 | 27161647.27
Air Defense College | Air Def finish IPC2 | 2 | Air Defense College2 | 6347561 | 4905910 | 0 | 4905910
EPICO 3 Facility | Eipico ipc 17 | 17 | EPICO 3 Facility17 | 30615959.94 | 13161378.737 | 17000000 | 30161378.737
EPICO 3 Facility | Eipico ipc 13 | 13 | EPICO 3 Facility13 | 50645327.08 | 2882568.41 | 24139643.31 | 27022211.72
Ain Sokhna Bridge | inv ( 1 ) A.S | 1 | Ain Sokhna Bridge1 | 28963170 | 659833.69 | 0 | 659833.69
Tarek Abdel-Hakim Center | TAH IPC04 | 4 | Tarek Abdel-Hakim Center4 | 1181749.35 | 909356.12 | 106357.44 | 1015713.56
Sokhna Port Expansion | sokhna port ipc 13 | 13 | Sokhna Port Expansion13 | 29580920.45 | 491489.95 | 5916184.09 | 26407674.04
El Taameer Axis Expansion | IPC#4 - Taamer PII | 4 | El Taameer Axis Expansion4 | 344520 | 332806.32 | 0 | 332806.32
WADY EL-NATROUN BRIDGE(HST) | IPC no16 D0073 |  | WADY EL-NATROUN BRIDGE(HST) | 1124077.5 | 491817.82 | 0 | 491817.82
Seashell Playa 5 Villas | Playa c038 ipc 7 | 7 | Seashell Playa 5 Villas7 | 37979.47 | 32799.07 | 0 | 32799.07
Tarek Abdel-Hakim Center | TAH ipc03 | 3 | Tarek Abdel-Hakim Center3 | 1124829.43 | 865556.24 | 101234.65 | 966790.89
SSC Suez Steel Company Project | I&R apply (ssc) ipc4 | 4 | SSC Suez Steel Company Project4 | 2492009.61 | 0 | 323162.22 | 2766130.6654
Seashell Playa 5 Villas | playa-c234 ipc (1) | 1 | Seashell Playa 5 Villas1 | 353841.09 | 323269.22 | 0 | 323269.22
Faculty of Medicine | mansora ipc16 final | 16 | Faculty of Medicine16 | 34226738.1 | 44569890.39 | 230114.95 | 44800005.34
U4,U8 Seashell Playa | IPC08 TR60 | 8 | U4,U8 Seashell Playa8 | 601043.97 | 514061.57 | 0 | 514061.57
U7-SEASHELL | IPC08 TR64 | 8 | U7-SEASHELL8 | 193306.24 | 166939.27 | 0 | 166939.27
Haramein Columns Transfer | Haramin ipc02 | 2 | Haramein Columns Transfer2 | 288000 | 240000 | 0 | 240000
Katameya Creeks - RME | IPC 11 TR53 | 11 | Katameya Creeks - RME11 | 169347.16 | 149956.91 | 0 | 149956.91
R05 (New) | IPC04 TR59 | 4 | R05 (New)4 | 88932 | 75423.23 | 0 | 75423.23
U3 & U5 | IPC12&13TR0055 | 12 | U3 & U512 | 226988.84 | 153144.54 | 0 | 153144.54
VILLA CLUSTRER B | IPC1&2 TR0077 | 1 | VILLA CLUSTRER B1 | 701780.5 | 606057.55 | 0 | 606057.55
HST El Mahager Bridge | mahager bridge ipc4 | 4 | HST El Mahager Bridge4 | 6289028.57 | 1120148.4028 | 0 | 5572311.4028
ora zed orascom | IPC07TR0069 | 7 | ora zed orascom7 | 629136.31 | 570187.87 | 0 | 570187.87
Sixty Iconic Tower | Inv ( 4 ) sixty | 4 | Sixty Iconic Tower4 | 1553224.22 | 1470030.77 | 0 | 1470030.77
GOV2 - Infra | GOV2 IPC 23 | 23 | GOV2 - Infra23 | 6553172.38 | 2581681.46 | 470072.51 | 3051753.97
ZED Phase 2 | IPC02TR0062 | 2 | ZED Phase 22 | 27001.998 | 22938.21 | 0 | 22938.21
SSC Suez Steel Company Project | I&R Supply SSC-IPC5 | 5 | SSC Suez Steel Company Project5 | 2293673.98 | 2650.0808 | 853448.63 | 2280322.6996
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc (22) | 22 | ORA ZED-Ph 2-Pkgs A&D22 | 10796355.55 | 8347638.3819 | 1056026.6 | 9403664.9819
Get Business Complex | INV ( 9 & 10) GET | 9 | Get Business Complex9 | 275623.72 | 259086.29 | 0 | 259086.29
VILLA CLUSTER C | IPC05TR0078 | 5 | VILLA CLUSTER C5 | 11515.09 | 9944.44 | 0 | 9944.44
VILLA CLUSTRER B | IPC04TR0077 | 4 | VILLA CLUSTRER B4 | 47134.89 | 40705.7 | 0 | 40705.7
Jawhara Palace Restoratio | Gawhara IPC6 | 6 | Jawhara Palace Restoratio6 | 2297237.99 | 1561600 | 574309.5 | 2135909.5
MDF Factory | MDF - IPC 13 | 13 | MDF Factory13 | 16038148.23 | 2376884.4693 | 17060757.9 | 19437642.3693
MDF Factory | MDF Factory ipc 31 | 31 | MDF Factory31 | 25781281.67 | 18542599.6668 | 10832542.51 | 29375142.1768
EGAT Pelletizing Plant | Egat Ro2 ipc 1 | 1 | EGAT Pelletizing Plant1 | 35549128.54 | 36971093.6816 | 0 | 36971093.6816
MDF Factory | mdf factory ipc 32 | 32 | MDF Factory32 | 2754000 | 2726460 | 0 | 2726460
Air Defence College | IPC018 TR46 | 18 | Air Defence College18 | 330011.54 | 298679.8 | 0 | 298679.8
U7-SEASHELL | IPC012TR0064 | 12 | U7-SEASHELL12 | 24350.2 | 21028.83 | 0 | 21028.83
Air Defense College | Air Def Elic IPC1 | 1 | Air Defense College1 | 102970206 | 16646860 | 68500000 | 85146860
Capital One | inv ( 9 ) Captal one | 9 | Capital One9 | 629166.35 | 427706.6285 | 195168.059 | 622874.6875
Quarry Bridge | inv ( 2 ) MAHGER Br | 2 | Quarry Bridge2 | 548000 | 405646 | 0 | 405646
EL Baragil Bridge | inv ( 2 ) Baragill B | 2 | EL Baragil Bridge2 | 446414.15 | 419629.3 | 0 | 419629.3
Port Said Port Silos | port said silosipc13 | 13 | Port Said Port Silos13 | 612060 | 535282.8844 | 61206 | 596488.8844
Tarek Abdel-Hakim Center | TAH ipc 5 | 5 | Tarek Abdel-Hakim Center5 | 1271012.98 | 978044.48 | 114391.17 | 1092435.65
Faculty of Medicine | Mansora Finish ipc02 | 2 | Faculty of Medicine2 | 4554326.67 | 3397808.9835 | 683149 | 4080957.9835
NUCA R05 - Z02 | R05(2) ipc 27 | 27 | NUCA R05 - Z0227 | 15628361.76 | 11664288.388 | 1490079.6 | 13154367.988
HST El Mahager Bridge | mahager bridge ipc06 | 6 | HST El Mahager Bridge6 | 12916195.24 | 11444643.79 | 0 | 11444643.79
EMAAR-Pkg#162/163- Marassi | Emar Pkg#177 ipc 47 | 47 | EMAAR-Pkg#162/163- Marassi47 | 6785617.6 | 4548162.03 | 500000 | 5048162.03
Lekela 250MW Wind Farm | Lekela 2 ipc 1=3 | 1 | Lekela 250MW Wind Farm1 | 15655160.98 | 3000357.339 | 13281010.08 | 16281367.419
EL Sewedy University Tec. | INV (1 ) S.UNI | 1 | EL Sewedy University Tec.1 | 552921.6 | 459695.04 | 0 | 459695.04
Astoria Sharm elSheikh | astoria sharm-IPC5 | 5 | Astoria Sharm elSheikh5 | 314831.49 | 278242.2245 | 16125.22 | 294367.4445
SSC Suez Steel Company Project | New Gas ipc 3 | 3 | SSC Suez Steel Company Project3 | 1936661.4 | 1336296.366 | 580998.42 | 1917294.786
SSC Suez Steel Company Project | New Gas sta ipc2 | 2 | SSC Suez Steel Company Project2 | 2057036.6 | 1419355.254 | 617110.98 | 2036466.234
U7-SEASHELL | IPC10TR0064 | 10 | U7-SEASHELL10 | 235112.74 | 199846.01 | 0 | 199846.01
Egyptian Exchange Building | Egyptian exch IPC4 | 4 | Egyptian Exchange Building4 | 35233128.57 | 1076790 | 0 | 27908290
SSC Suez Steel Company Project | Revamp ipc 7 | 7 | SSC Suez Steel Company Project7 | 4571797.25 | 3154540.11 | 1371539.17 | 4526079.28
Koumassi Flyover | INV 2 | 2 | Koumassi Flyover2 | 282048968 | 253844034 | 0 | 253844034
AIRDEFNSE -EPOXY | IPC06TR0066 | 6 | AIRDEFNSE -EPOXY6 | 127428 | 108186.37 | 0 | 108186.37
Luxor North Axis Bridge-Off | IPC no5 luxor off |  | Luxor North Axis Bridge-Off | 672192 | 672192 | 0 | 672192
Ora Zed Landscape Ph1 | Ora Landscape ipc 11 | 11 | Ora Zed Landscape Ph111 | 6460754.42 | 5312426.17 | 678379.21 | 5990805.38
HST El Mahager Bridge | el mahager ipc 07 | 7 | HST El Mahager Bridge7 | 1393130.24 | 234090.6 | 0 | 1234090.6
Katameya Creeks - RME | IPC009 TR53 | 9 | Katameya Creeks - RME9 | 24448.35 | 21649.0135 | 0 | 21649.0135
R05 (New) | tr0059 IPC002 | 2 | R05 (New)2 | 33748.3667 | 74543 | 0 | 29298.0667
EIPICO C002-23 | IPC02 TR68 | 2 | EIPICO C002-232 | 71999.09 | 61782.42 | 0 | 61782.42
ORA ZED TOWER #2 | IPC001 TR49 | 1 | ORA ZED TOWER #21 | 33000 | 29221.5 | 0 | 29221.5
October Under-Railway Tunnel | october tunnel ipc8 | 8 | October Under-Railway Tunnel8 | 5216969.9 | 4696818.58 | 0 | 4696818.58
ORA ZED - Ph 01B - Pkgs A&D | ORA ph.1 IPC19 | 19 | ORA ZED - Ph 01B - Pkgs A&D19 | 21493163.81 | 17518053.2705 | 2068970.4 | 19587023.6705
Air Defence College | IPC22TR0046 | 22 | Air Defence College22 | 278157.9 | 236156.05 | 0 | 236156.05
Irrigation Tank | IPC05TR0061 | 5 | Irrigation Tank5 | 1272596.7 | 1016514.34 | 0 | 1016514.34
Waldorf Astoria Cairo | Waldorf astori ipc24 | 24 | Waldorf Astoria Cairo24 | 10000000 | 22455841.54 | 0 | 22455841.54
El-Warraq | inv 1.2 d0081 | 1 | El-Warraq1 | 1415294 | 1149573.6 | 0 | 1149573.6
El Zomor Axis (2) - Leaaba | IPC#1#LEABA | 1 | El Zomor Axis (2) - Leaaba1 | 352000 | 274596 | 0 | 274596
Egyptian Exchange Building | Egy Ex awnash IPC1 | 1 | Egyptian Exchange Building1 | 7063290.48 | 5385220 | 0 | 5385220
Kattmeya Creeks Urban | IPC07TR0071 | 7 | Kattmeya Creeks Urban7 | 103122.42 | 91314.91 | 0 | 91314.91
HSR | HSR-OCT-5 | 5 | HSR5 | 36253472.15 | 0 | 36862391.5075 | 36862391.5075
HSR | HSR - OCT 3 |  | HSR | 39650249.66 | 5947537.45 | 22750962.593 | 28698500.043
New Giza Teaching Hospital | New Giza Hosp ipc 22 | 22 | New Giza Teaching Hospital22 | 12179338.16 | 7290216.108 | 1844615.96 | 11134832.068
Wady El Natroon Bridge | wady elnatron ipc8 | 8 | Wady El Natroon Bridge8 | 11709710.48 | 1980.8 | 0 | 10439980.8
MDF Factory | Mdf Factory ipc 35 | 35 | MDF Factory35 | 8184195.01 | 11964736.84 | 3437361.19 | 15402098.03
Roof-Playa Cluster A,B,C | IPC06TR0088 | 6 | Roof-Playa Cluster A,B,C6 | 326911 | 282320.34 | 0 | 282320.34
Sixty Iconic Tower | Inv ( 5 ) sixty | 5 | Sixty Iconic Tower5 | 1765230 | 1659316.2 | 0 | 1659316.2
Seashell Playa 5 Villas | Playa c234 - ipc 4 | 4 | Seashell Playa 5 Villas4 | 56708.36 | 51808.76 | 0 | 51808.76
MDF Factory | MDF Equip ipc 21 | 21 | MDF Factory21 | 594425.9 | 600370.156 | 0 | 600370.156
HST Bridges-Sokhna & Mahager | Sokhna ipc17+18+19 | 17 | HST Bridges-Sokhna & Mahager17 | 17594286.57 | 13930069.0043 | 0 | 15142069.0043
Roof-Playa Cluster A,B,C | IPC01TR0088 | 1 | Roof-Playa Cluster A,B,C1 | 1326588 | 1145641.39 | 0 | 1145641.39
3A-L2M Building | ACUD Mar.24 |  | 3A-L2M Building | 22281960.78 | 18337374.889 | 1000000 | 19337374.889
Sixty Iconic Tower | Inv ( 7 ) sixty | 7 | Sixty Iconic Tower7 | 1771175 | 893857.65 | 0 | 893857.65
Kattameya Creeks | Katameya creek ipc37 | 37 | Kattameya Creeks37 | 60819348.36 | 62109565 | 890952.21 | 63000517.21
EGAT Injection | IPC14TR0048 | 14 | EGAT Injection14 | 98815.4 | 84793.5 | 0 | 84793.5
Mohamed Ali Palace Restoration | Mohamed aly271 IPC1 | 1 | Mohamed Ali Palace Restoration1 | 4604016.19 | 1277660 | 2547414.15 | 3825074.15
Ministries Buildings | Mini Fit out IPC5 | 5 | Ministries Buildings5 | 2752100 | 2318220 | 0 | 2318220
Tarek AbdelHakim Center - KSA | K0001-3 | 3 | Tarek AbdelHakim Center - KSA3 | 15666254.07 | 0 | 0 | 18016192.18
R05 (New) | IPC07TR0059 | 7 | R05 (New)7 | 53504.78 | 45377.4 | 0 | 45377.4
Sultana Malak Restoration | Sultana malak22 IPC2 | 2 | Sultana Malak Restoration2 | 77855043.81 | 16986360 | 43648959.61 | 60635319.61
Faculty of Medicine | mansora finish ipc18 | 18 | Faculty of Medicine18 | 14334453.33 | 10672749 | 2150168 | 12822917
EL Baragil Bridge | inv ( 4 ) Baragill B | 4 | EL Baragil Bridge4 | 3105830 | 828921.2 | 0 | 828921.2
Koumassi Flyover | INV 3 | 3 | Koumassi Flyover3 | 357151711 | 321436537 | 0 | 321436537
SSC Suez Steel Company Project | R.o 500:800 sup ipc8 | 8 | SSC Suez Steel Company Project8 | 4444683.99 | 1418034.9086 | 3604458 | 5022492.9086
Roof-Playa Cluster A,B,C | IPC03TR0088 | 3 | Roof-Playa Cluster A,B,C3 | 84568 | 73032.92 | 0 | 73032.92
SSC Suez Steel Company Project | Shutdown SMP2 IPC 3 | 3 | SSC Suez Steel Company Project3 | 1490218.8 | 730207.212 | 745109.4 | 1475316.612
SSC Suez Steel Company Project | SVC- ipc 1 | 1 | SSC Suez Steel Company Project1 | 3212437.04 | 2216581.5616 | 963731.11 | 3180312.6716
U4,U8 Seashell Playa | IPC14TR0060 | 14 | U4,U8 Seashell Playa14 | 131368.7 | 113450 | 0 | 113450
Main Spine | IPC01TR0096 | 1 | Main Spine1 | 870899.98 | 752109.22 | 0 | 752109.22
NUCA R05 - Z02 | R05(2) ipc 41 | 41 | NUCA R05 - Z0241 | 13676567.6 | 20810136.565 | 2582936.8 | 23393073.365
NUCA R05 - Z02 | R05(2)IPC48 | 48 | NUCA R05 - Z0248 | 13607864.7 | 12385600.7 | 1665704.42 | 14051305.12
Hosh Eisa Hospital | IPC02TR0086 | 2 | Hosh Eisa Hospital2 | 222500.25 | 190927.47 | 0 | 190927.47
ORA ZED - Ph 01B - Pkgs A&D | ora zed ipc 24 | 24 | ORA ZED - Ph 01B - Pkgs A&D24 | 10139035.7 | 8591385.3318 | 1085626.55 | 9677011.8818
Maspiro Towers | IPC#2 | 2 | Maspiro Towers2 | 702000 | 694980 | 0 | 696735
EGAT Pelletizing Plant | Egat Water tan ipc14 | 14 | EGAT Pelletizing Plant14 | 1893022.3 | 2909387.535 | 0 | 2909387.535
Port Said Grain Storage | IPC6 PORT SAID | 6 | Port Said Grain Storage6 | 300300 | 89493.48 | 0 | 99503.68
MDF Factory | MDF Factory ipc 38 | 38 | MDF Factory38 | 25020067.65 | 9539881.65 | 10508616.79 | 20048498.44
EGAT Pelletizing Plant | Pelletizing ipc 21 | 21 | EGAT Pelletizing Plant21 | 37437141.5 | 38934627.165 | 0 | 38934627.165
HST Bridges-Sokhna & Mahager | sokhna bri.esc19 |  | HST Bridges-Sokhna & Mahager | 2260344.86 | 2014925.441 | 0 | 2014925.441
ZED Phase 2 | IPC11TR0062 | 11 | ZED Phase 211 | 38142.25 | 28102.83 | 0 | 28102.83
Qani bay Al rammah Mosque | Qani bay IPC1 | 1 | Qani bay Al rammah Mosque1 | 8571603.81 | 6624100 | 0 | 6624100
Al-Parco | INV ( 7 ) ALparco | 7 | Al-Parco7 | 2823676 | 54255.44 | 0 | 54255.44
PLAYA ROOF & Wet Areas | IPC25TR0041 | 25 | PLAYA ROOF & Wet Areas25 | 27822.02 | 23874.08 | 0 | 23874.08
U3 & U5 | IPC21TR0055 | 21 | U3 & U521 | 556690.63 | 400758.03 | 0 | 400758.03
Port Said Port Silos | supply egp ipc6 | 6 | Port Said Port Silos6 | 1064494.36 | 12030748.852 | 532334.65 | 2512616.7004
Wady El Natroon Bridge | ipc4 wady elnatroon | 4 | Wady El Natroon Bridge4 | 11433601.9 | 10274726.196 | 0 | 10274726.196
RING ROAD MARYOTIA EXPANSION | El-Marg IPC08 | 8 | RING ROAD MARYOTIA EXPANSION8 | 4234352.07 | 3742255.05 | 0 | 3742255.05
HST El Mahager Bridge | El Mahager ipc08 | 8 | HST El Mahager Bridge8 | 47025180.48 | 41625139.7 | 0 | 41625139.7
El Khatatba Bridge | EL KHATATBA IPC03 | 3 | El Khatatba Bridge3 | 16420583.33 | 16256377.4965 | 0 | 16256377.4965
Port Said Port Silos | PORT SAID IPC26 | 26 | Port Said Port Silos26 | 2227046.78 | 426108.0312 | 222704.68 | 648812.7112
Luxor North Axis Bridge-Off | IPC#1 Luxor offshore | 1 | Luxor North Axis Bridge-Off1 | 1644720 | 1537678.4 | 0 | 1537678.4
Luxor North Axis Bridge | IPC#2-Luxor onshore | 2 | Luxor North Axis Bridge2 | 843750 | 818437 | 0 | 818437
Jawhara Palace Restoratio | Gawhara IPC5 | 5 | Jawhara Palace Restoratio5 | 2268323.02 | 1542000 | 567080.76 | 2109080.76
Creeks URBN-K | U-rbnk ipc (4) | 4 | Creeks URBN-K4 | 25969563.12 | 8830426 | 16931112.88 | 25761538.88
Koumassi Flyover | INV no.9 | 9 | Koumassi Flyover9 | 1174417959.9 | 1153318675.27 | 0 | 1153318675.27
Jawhara Palace Restoratio | Gawhara IPC1 | 1 | Jawhara Palace Restoratio1 | 1944820.33 | 1321600 | 486205.08 | 1807805.08
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc 35+36 | 35 | ORA ZED-Ph 2-Pkgs A&D35 | 7262978.01 | 3820917.5505 | 10380361.56 | 14201279.1105
ORA ZED-Ph 2-Pkgs A&D | Ora Ph2 ipc 33+34 | 33 | ORA ZED-Ph 2-Pkgs A&D33 | 7988113.29 | 5000134.02 | 838751.9 | 5838885.92
Air Defense College | Air dev 27 IPC1 | 1 | Air Defense College1 | 72686330 | 6332230 | 54350990 | 60683220
Senator | Inv ( 4 ) Sentor | 4 | Senator4 | 147888 | 122000 | 0 | 122000
El Taameer Axis Expansion | FPC - Taamer Axis |  | El Taameer Axis Expansion | 568601 | 542548.57 | 0 | 542548.57
Port Said Port Silos | port said ipc 31 | 31 | Port Said Port Silos31 | 3155732.38 | 2284436.52 | 315573.24 | 2600009.76
Port Said Port Silos | port said supp.9 |  | Port Said Port Silos | 3231641.7 | 20233176 | 2585313.36 | 2852311.17
SSC Suez Steel Company Project | L7776/2022 |  | SSC Suez Steel Company Project | 10000000 | 7082500 | 0 | 7082500
Faculty of Medicine | MANSOURA FINISHIPC24 | 24 | Faculty of Medicine24 | 5200547.62 | 3879988 | 780082.14 | 4660070.14
SSC Suez Steel Company Project | Shutdown smp1 ipc 3 | 3 | SSC Suez Steel Company Project3 | 770000 | 333693.13 | 384999.87 | 718693
Wady El Natroon Bridge | WADY ELNATROON IPC10 | 10 | Wady El Natroon Bridge10 | 9636546.67 | 8591548.13 | 0 | 8591548.13
VILLA CLUSTER C | IPC07TR0078 | 7 | VILLA CLUSTER C7 | 24246.87 | 20939.6 | 0 | 20939.6
El Taameer Axis Expansion | IPC#5 - Taamer Axis | 5 | El Taameer Axis Expansion5 | 806355 | 778938.93 | 0 | 778938.93
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc 25 | 25 | ORA ZED-Ph 2-Pkgs A&D25 | 1429471.43 | 1086725.0887 | 150094.5 | 1236819.5887
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 29 | 29 | ORA ZED-Ph 2-Pkgs A&D29 | 7868267.11 | 5059481.7155 | 652009.74 | 5711491.4555
Port Said Port Silos | PORT SAID IPC 33 | 33 | Port Said Port Silos33 | 4525360.97 | 2711136 | 452536.1 | 3163672.1
Rabigh PP - Piling Works | K0004 Inv-06 | 6 | Rabigh PP - Piling Works6 | 1751171.77 | 6041514.12 | 0 | 2013838.04
Koumassi Flyover | INV no.12 | 12 | Koumassi Flyover12 | 1141878222.44 | 1027690400.19 | 0 | 1027690400.19
Abou Ghaleb Bridge | abou ghaleb ipc25+26 | 25 | Abou Ghaleb Bridge25 | 3342110.29 | 3057591.05 | 0 | 3057591.05
KATAMYA GREEKS LAND SCAPE STAR | IPC05TR0081 | 5 | KATAMYA GREEKS LAND SCAPE STAR5 | 1438507.13 | 1422108.1465 | 0 | 1422108.1465
Damietta Container Termin | Damietta PKG#3 IPC 2 | 2 | Damietta Container Termin2 | 1592229.98 | 1496696.18 | 0 | 1496696.18
October Under-Railway Tunnel | october tunnel ipc9 | 9 | October Under-Railway Tunnel9 | 6996014.86 | 6298618.2 | 0 | 6298618.2
U7-SEASHELL | IPC23TR0064 | 23 | U7-SEASHELL23 | 276276.03 | 159591.78 | 0 | 159591.78
EDNC Hardscape Package | Haedescape ipc final |  | EDNC Hardscape Package | 14588321.68 | 4532604.51 | 0 | 11805658.06
EPICO 3 Facility | Eipico ipc 19 | 19 | EPICO 3 Facility19 | 35463786.32 | 22436578.356 | 0 | 22436578.356
Hosh Eisa | IPC03TR0091 | 3 | Hosh Eisa3 | 61151.5 | 52474.09 | 0 | 52474.09
Katameya Creeks - RME | IPC22TR0053 | 22 | Katameya Creeks - RME22 | 116200.85 | 100895.86 | 0 | 100895.86
MDF Factory - Sadat | IPC01TR0093 | 1 | MDF Factory - Sadat1 | 331476.6 | 284440.07 | 0 | 284440.07
Coastal road Bridge Extension | IPC#8 -Coastal Roa | 8 | Coastal road Bridge Extension8 | 952560 | 917315.28 | 0 | 917315.28
Coastal road Bridge Extension | IPC#2 Gharably | 2 | Coastal road Bridge Extension2 | 1797850 | 1667329.55 | 0 | 1667329.55
Wady El Natroon Bridge | WADYELNATRON ESC1:8 |  | Wady El Natroon Bridge | 6190476.19 | 911603 | 0 | 5979603
Wady El Natroon Bridge | wadyelntron13+14+15 |  | Wady El Natroon Bridge | 47518136.19 | 866773.5 | 0 | 42366773.5
Seashell Playa 5 Villas | Playa c185 - ipc 4 | 4 | Seashell Playa 5 Villas4 | 57833.47 | 49944.99 | 0 | 49944.99
Seashell Playa 5 Villas | playa C469 IPC 9 | 9 | Seashell Playa 5 Villas9 | 23166.2 | 21164.64 | 0 | 21164.64
Faculty of Medicine | IPC25MANSOURAFINISHN | 25 | Faculty of Medicine25 | 4162992.38 | 2738988.36 | 624448.86 | 3363437.22
EL -mahager Bridge Ain sokhna | IPC#1#ElMahager | 1 | EL -mahager Bridge Ain sokhna1 | 946500 | 65719.28 | 0 | 65719.28
ElMoneeb 2 | IPC#5 - Moneeb | 5 | ElMoneeb 25 | 160893 | 159284.07 | 0 | 159284.07
Jawhara Palace Restoratio | GAWHARA IPC8 | 8 | Jawhara Palace Restoratio8 | 1389436.83 | 823726.96 | 347359.21 | 1171086.17
Roof-Playa Cluster A,B,C | IPC12&13TR0088 | 12 | Roof-Playa Cluster A,B,C12 | 418018.9 | 0 | 0 | 0
Seashell Playa 5 Villas | Playa C470- ipc 8 | 8 | Seashell Playa 5 Villas8 | 176010.2 | 152002.4 | 0 | 152002.4
Capital One | inv (12 ) Captal one | 12 | Capital One12 | 911829.3 | 161150.005 | 0 | 161150.005
Cairo Monorail - 6th October | IPC#10 Monorail | 10 | Cairo Monorail - 6th October10 | 921600 | 912384 | 0 | 912384
Seashell Playa 5 Villas | Cr 20/12/2023 |  | Seashell Playa 5 Villas | 0 | 0 | 0 | #DIV/0!
Daraw Bridge | D0033-OB-Dec-2020/Cr | 2020 | Daraw Bridge2020 | 0 | 0 | 0 | #DIV/0!
Canal Sugar OHTL | Inv.11 Sugar OHTL | 11 | Canal Sugar OHTL11 | 604632.9 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Deductions inv.29 | 29 | South Helwan PP (CP-117)29 | 0 | 0 | 0 | #DIV/0!
South Dabaa Axis | IPC#5# South Dabaa | 5 | South Dabaa Axis5 | 110000 | 0 | 0 | #DIV/0!
New Capital | Credit memo inv 5 El | 5 | New Capital5 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 17 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 168175.4286 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR-5-Euro-South he | 5 | South Helwan PP (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Alamein | CR-ipc1 elalamin | 1 | Alamein1 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | Cr-Lahoon Sub Inv 02 | 2 | Lahoon 220/22/222 | 0 | 0 | 0 | #DIV/0!
Benban 500 K.V / 100 K.M | تشيد بنبان |  | Benban 500 K.V / 100 K.M | 5000 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | Cr. Adj Inv 19 | 19 | Barwa 2x60/22 KV S/S19 | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | cr.soci 72 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Re Soc Inv.3 Temmay | 3 | Beni Seuf - 3583 | 154841 | 0 | 0 | #DIV/0!
Playa Resort | 41 |  | Playa Resort | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 249 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Monoril | inv ( 3 ) monoril | 3 | Monoril3 | 273420 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10105 |  | AWEER POWER STATION 'H' Phase | 2395684.97 | 0 | 0 | #DIV/0!
Playa Resort | 6 |  | Playa Resort | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 180067 |  | South Helwan PP (CP-117) | -13638.44 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | IPC#5#draw | 5 | Aswan axis - Daraw5 | 144552 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_INV.8 | 8 | Akhmem - Qena8 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr. Inn 49 Ass |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | 6 |  | Barwa 2x60/22 KV S/S | 1126765.27 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 28 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Rail Way Tunnel Zagazig | D0025-OB-Dec-2020/Cr | 2020 | Rail Way Tunnel Zagazig2020 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 7 Euro-South Helwan |  | South Helwan PP (CP-117) | 20918.1048 | 0 | 0 | #DIV/0!
Port Said Grain Storage | Rent-008 | 8 | Port Said Grain Storage8 | 166650 | 0 | 0 | #DIV/0!
Wadi Halfa Port | cr-wadi halfa ipc01 | 1 | Wadi Halfa Port1 | 0 | 0 | 0 | #DIV/0!
Aljazi Project | Cr. Al - Jazi Inv. 2 | 2 | Aljazi Project2 | 0 | 0 | 0 | #DIV/0!
Get Business Complex | C r .INV ( 15 ) GET | 15 | Get Business Complex15 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | inv.5 cancl | 5 | Ghana Street lighting5 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ret Asuit akh 4 |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | cr-kafr shokr ipc09 | 9 | Kafr Shokr Bridge9 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 83 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Parco | INV ( 13 ) ALparco | 13 | Al-Parco13 | 394596 | 0 | 0 | #DIV/0!
ACWA POWER & NOMAC HQ | Acwa power ipc 3 | 3 | ACWA POWER & NOMAC HQ3 | 30565.84 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180083 |  | Suez Gulf Substation | 310156.26 | 0 | 0 | #DIV/0!
Sokhna Port Expansion | cr-ipc14 sokhna port | 14 | Sokhna Port Expansion14 | 0 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 05 | 5 | Suez Gulf/S4 - 500KV OHTL5 | 231265.09 | 0 | 0 | #DIV/0!
Solar ITS | P-06-EGY اتحاد تشيد | 6 | Solar ITS6 | 5000 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | rev.( 5 Euro-So. Hel |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 40 |  | Governmental Campus-N2 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 59 |  | Suez Gulf Substation | 1954696.02 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,11usd Borg Ar | 11 | Marsa Matrouh 500KV11 | 0 | 0 | 0 | #DIV/0!
Ministries Buildings | CR-MINI-IPC05+ | 5 | Ministries Buildings5 | 0 | 0 | 0 | #DIV/0!
Al-Wukair 11 Substation | inv(ESC-SA-Civil-08) | 8 | Al-Wukair 11 Substation8 | 2169739.56 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 477 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | DR. 13 Oewon Mousa |  | Beni Seuf - 358 | 4940.63 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen-akh 5 |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
LP-03-22 IIoT - UIC | 90 |  | LP-03-22 IIoT - UIC | 6750 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr. Egytec |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11585 |  | FURJAN Cable Works | 1227202.49 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 2 |  | Zafranaa - Ras Ghareb | 50000 | 0 | 0 | #DIV/0!
New Capital | Edit inv 5 | 5 | New Capital5 | 265.33 | 0 | 0 | #DIV/0!
Al-Parco | crINV ( 3 )ALparco | 3 | Al-Parco3 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 61 |  | Suez Gulf Substation | 777135.78 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr. Socil 4-8:19 ass | 8 | Akhmem Assiut8 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr Soc Inv 49 Asuit | 49 | Akhmem Assiut49 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply. Inv.4 Ret | 4 | Ghana Street lighting4 | 21465.37 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 105 |  | Al-Shabab PP Phase II (CP-117) | 203669103.2878 | 0 | 0 | #DIV/0!
HST Bridge - Arab Contractors | IPC#1#D0083 HST | 1 | HST Bridge - Arab Contractors1 | 684550 | 0 | 0 | #DIV/0!
U3 & U5 | 55-CR2F |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | اتحاد تشيدو بناءP-81 | 81 | Lahoon 220/22/2281 | 5000 | 0 | 0 | #DIV/0!
Palm Hill-Infra Str(Elec.Work) | DEC ADJ 106 |  | Palm Hill-Infra Str(Elec.Work) | 0 | 0 | 0 | #DIV/0!
Zayed Monorail 66/22 KV GIS | P-29-EGY اتحاد تشيد | 29 | Zayed Monorail 66/22 KV GIS29 | 5000 | 0 | 0 | #DIV/0!
Closed | OB-ST-Ismailya B |  | Closed | 586996.5 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | 11-07-2018 | 7 | Siemens 6x500/220 KV GIS-MOU7 | 0 | 0 | 0 | #DIV/0!
Business District Hyde Park | CR-4HY Bark | 4 | Business District Hyde Park4 | 0 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 26 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2103210012 |  | Miscellaneous Projects | -10500 | 0 | 0 | #DIV/0!
Cairo North PP Rehabilitation | CN last Inv Cairo N |  | Cairo North PP Rehabilitation | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR- 19 EGP- Shabab | 19 | Al-Shabab PP Phase II (CP-117)19 | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | Cr-Egy Ex IPC1 | 1 | Egyptian Exchange Building1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 244 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Celia | CR-IPC#1 | 1 | Celia1 | 0 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 22 ) GET | 22 | Get Business Complex22 | 1989686.7 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cr . Adj Inv. 15 | 15 | Abou El Matameer and Sammanoud15 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 248 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
ZED Phase 2 | IPC05TR0062 | 5 | ZED Phase 25 | 93654.83 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 452 |  | TZ – Offshore E&M Procurement | 274863.23 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | ADJUST TAX OF INV.32 | 32 | South Helwan PP (CP-117)32 | 0 | 10785.57 | 0 | 10785.57
marassi inland marina | D0029-OB-Dec-2020/Cr | 2020 | marassi inland marina2020 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen-akh 6 |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | Reduction inv no 210 | 210 | MAYSAN 400/132kV SS210 | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr. Ref Retention Ma |  | Marsa Matrouh 500KV | 0 | 0 | 0 | #DIV/0!
Air Defence College | Cancel IPC11 TR46 | 11 | Air Defence College11 | -190510.2 | 0 | 0 | #DIV/0!
El Boghaz Brigde | IPC#27/28 | 27 | El Boghaz Brigde27 | 1276221.84 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 74 |  | W Dam PP Phase II (CP-117) | -49628984.48 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | IPC NRCC 3 |  | Expansion of Ring Road NRCC | 0 | 0 | 0 | #DIV/0!
Central Capital | Cr.INV ( 5 ) Central | 5 | Central Capital5 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | credit Ref. Inst |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | inv.5 cancle | 5 | Ghana Street lighting5 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 15 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 537 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
LAYAN Substation | 11460 |  | LAYAN Substation | 0 | 0 | 0 | #DIV/0!
Wadi El Natroun | IPC#5#Wadi Elnatron | 5 | Wadi El Natroun5 | 745809 | 0 | 0 | #DIV/0!
U3 & U5 | TR55-CR1 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 251 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | Re soc Inv 24. Quna | 24 | Akhmem - Qena24 | 588.61 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | Cr - 5 USD - West D. | 5 | W Dam PP Phase II (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 5 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 978219.9238 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 21 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 362995.381 | 0 | 0 | #DIV/0!
Racecores 3092-15 132KV A | 11521 |  | Racecores 3092-15 132KV A | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | Adjust billing |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | inv ( 4 ) final CR | 4 | Al-Ula Towers4 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR -15-West D. 117 | 15 | W Dam PP Phase II (CP-117)15 | 0 | 0 | 0 | #DIV/0!
Road El Farag Axis | D0006-OB-Dec-2020/Cr | 2020 | Road El Farag Axis2020 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | CN Q3 Beni Suef |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 24 ) GET | 24 | Get Business Complex24 | 240090.71 | 0 | 0 | #DIV/0!
Akhmem - Qena | Cr Adj Inv 10 | 10 | Akhmem - Qena10 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 90 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
ENR-Signaling Inst. | P-42-EGY اتحاد تشيد | 42 | ENR-Signaling Inst.42 | 5000 | 0 | 0 | #DIV/0!
Al-Ula Towers | inv ( 4 ) final CR2 | 4 | Al-Ula Towers4 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Ins.Inv.2Ret. | 2 | Ghana Street lighting2 | 20145.78 | 0 | 0 | #DIV/0!
Containment Data Center- | 48 |  | Containment Data Center- | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 77 |  | Governmental Campus-N2 | 460454.41 | 0 | 0 | #DIV/0!
Strining Lot A- Elegect | Elegict |  | Strining Lot A- Elegect | 0 | 0 | 0 | #DIV/0!
P.I.Parks - Plot 10 | P-33-EGY اتحاد تشيد | 33 | P.I.Parks - Plot 1033 | 5000 | 0 | 0 | #DIV/0!
Kayan 3 New Cairo Capital City | CR ARMY/KYAN/1446 |  | Kayan 3 New Cairo Capital City | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial P - East | Cr Adj inv 4 | 4 | Pyramids Industrial P - East4 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 3 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 1188435.9048 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 6 USD - Suez Gulf |  | Suez Gulf Substation | 371737.6 | 0 | 0 | #DIV/0!
Canal Sugar S/s | Inv 6 $ Sugar S/s | 6 | Canal Sugar S/s6 | 1443919.39 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 207 |  | MAYSAN 400/132kV SS | -4798431.61 | 0 | 0 | #DIV/0!
El Katameya Mall | CRinv ( 13 )10-2020 | 13 | El Katameya Mall13 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 13 USD- Suez Gulf |  | Suez Gulf Substation | 90935.77 | 0 | 0 | #DIV/0!
Ghana Street lighting | Pole.Cvr.Inv.2.Cncl | 2 | Ghana Street lighting2 | 0 | 0 | 0 | #DIV/0!
Kayan 3 New Cairo Capital City | 30/11/22 Armed force |  | Kayan 3 New Cairo Capital City | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange building | FINALTR0039 |  | Egyptian Exchange building | 474028.93 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 86 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv 04 | 4 | MOC HQ at Diriyah4 | 16246137.77 | 0 | 0 | 23353823.04
Air Defence College | IPC26TR0046. | 26 | Air Defence College26 | 4159.68 | 0 | 0 | 4159.68
Open Channel 2 | IPC02TR0099(02) | 2 | Open Channel 22 | 2440060 | 0 | 0 | 2440060
MAF HQ Renovation | maf Po.0020024000370 |  | MAF HQ Renovation | 80510.4 | 0 | 0 | 95553.717
Residence 8 ( S05 ) | Inv ( 1 ) S 05 | 1 | Residence 8 ( S05 )1 | 69311.35 | 0 | 0 | 69311.35
TOSHKA MADKOUR | IPC01TR0083 | 1 | TOSHKA MADKOUR1 | 1127761.2 | 0 | 0 | 1127761.2
Port Said Port Silos | port said EUR ipc01 | 1 | Port Said Port Silos1 | 5539353.23 | 0 | 0 | 5539353.23
Ain Sokhna Bridge | Inv ( 5 ) A.S | 5 | Ain Sokhna Bridge5 | 333124.5 | 0 | 0 | 333124.5
Open Channal | IPC01TR0074 | 1 | Open Channal1 | 294368.26 | 0 | 0 | 294368.26
Waldorf Astoria Cairo | Waldorf Asto ipc(20) | 20 | Waldorf Astoria Cairo20 | 3956218.97 | 0 | 0 | 4154029.9185
EL Sewedy University Tec. | INV ( 2 ) S.UNIV | 2 | EL Sewedy University Tec.2 | 140678.4 | 0 | 0 | 140678.4
Sokhna Port Expansion | ipc14 sokhna port ex | 14 | Sokhna Port Expansion14 | 14245622.5 | 0 | 0 | 14245622.5
British International School | Bis ipc (2) | 2 | British International School2 | 11138109 | 0 | 0 | 12697444.26
Cairo-Alex Railway | CAIRO-ALEX IPC40 | 40 | Cairo-Alex Railway40 | 21031085.3 | 0 | 0 | 22082639.565
Al-Ula Towers | inv ( 5 ) FINAL Ola | 5 | Al-Ula Towers5 | 544770 | 0 | 0 | 572008.5
U3 & U5 | TR55-IPC1 | 1 | U3 & U51 | 741275.46 | 0 | 0 | 741275.46
U3 & U5 | TR55-IPC2 | 2 | U3 & U52 | 439984.49 | 0 | 0 | 439984.49
U3 & U5 | TR55/IPC/03 |  | U3 & U5 | 34000.72 | 0 | 0 | 34000.72
U3 & U5 | TR55/IPC/02 |  | U3 & U5 | 439984.49 | 0 | 0 | 439984.49
Wadi Halfa Port | wadi halfa ipc01 | 1 | Wadi Halfa Port1 | 31456682.86 | 0 | 0 | 33029517.003
Seashell Playa 5 Villas | seashell playa- IPC1 | 1 | Seashell Playa 5 Villas1 | 161096.6 | 0 | 0 | 169151.43
Egyptian Exchange Building | Egy Ex IPC1 | 1 | Egyptian Exchange Building1 | 185780585 | 0 | 0 | 185780585
Kafr Shokr Bridge | م 10 كفر شكر | 10 | Kafr Shokr Bridge10 | 2706642.86 | 0 | 0 | 2841975.003
Ministries Buildings | minis MEP05+ |  | Ministries Buildings | 121861476.8 | 0 | 0 | 121861476.8
Racecores 3092-17 132KV E | 11768 |  | Racecores 3092-17 132KV E | 12214.2857 | 0 | 0 | 12825
Infra Project 4428 | 2112210003 |  | Infra Project 4428 | 134285714.29 | 141000000.0045 | 0 | 141000000.0045
Assuit PP (CP-118) | 220621002 |  | Assuit PP (CP-118) | 820286.39 | 0 | 0 | 861300.7095
FURJAN Cable Works | 11560 |  | FURJAN Cable Works | 1227202.49 | 0 | 0 | 1288562.6145
Racecores 3092-15 132KV A | 11497 |  | Racecores 3092-15 132KV A | 3551.62 | 0 | 0 | 3551.62
Racecores 3092-17 132KV E | 11447 |  | Racecores 3092-17 132KV E | 5152.88 | 0 | 0 | 5152.88
Beni Seuf - 358 | Inv. 11 Oewon Mousa | 11 | Beni Seuf - 35811 | 20054291.17 | 0 | 3449628.8 | 3473303.99
Infra Project 2524 | 220221001 |  | Infra Project 2524 | 91421211.43 | 0 | 0 | 95992272
Ministries Buildings | Minist SHELL IPC08 | 8 | Ministries Buildings8 | 26226263.88 | 0 | 0 | 26226263.88
Miscellaneous Projects | 2010210003 |  | Miscellaneous Projects | 37075635 | 0 | 0 | 37075635
Toshka GIS 500 kV | Toshka Sub Inv. 24 $ | 24 | Toshka GIS 500 kV24 | 25418.1 | 0 | 0 | 25418.1
Kafr Shokr Bridge | Kafr Shokr-IPC01 | 1 | Kafr Shokr Bridge1 | 32770679.81 | 0 | 0 | 37358574.9834
Ain-Sokhna PP (CP-117) | 2012210038 |  | Ain-Sokhna PP (CP-117) | -687552.29 | 0 | 0 | -687552.29
Assuit PP (CP-118) | 2103210015 |  | Assuit PP (CP-118) | 1405352.19 | 0 | 0 | 1479318.09
El Boghaz Brigde | D0007-OB-Dec-2020 | 2020 | El Boghaz Brigde2020 | 19573481.82 | 0 | 0 | 19573481.82
LRT - El Shorouk Bridge | D0034-OB-Dec-2020 | 2020 | LRT - El Shorouk Bridge2020 | 4118500 | 0 | 0 | 4118500
Minis Building(Polyurethane) | TR0020DEC.Closing |  | Minis Building(Polyurethane) | 3085900.98 | 0 | 0 | 3085900.98
Club House-Sodic Wesset | TR0019DEC.Closing |  | Club House-Sodic Wesset | 117700 | 0 | 0 | 117700
Mohamed Ali Palace | TR0015DEC.Closing |  | Mohamed Ali Palace | 324612.4 | 0 | 0 | 324612.4
El-Moneeb Bridge | D0038-OB-Dec-2020 | 2020 | El-Moneeb Bridge2020 | 2634750 | 0 | 0 | 2634750
Suez Bridge | D0017-OB-Dec-2020 | 2020 | Suez Bridge2020 | 193930 | 0 | 0 | 193930
IRAQ - Al-Diwaniya Power Plant | 2012210030 |  | IRAQ - Al-Diwaniya Power Plant | 192535.65 | 0 | 0 | 192535.65
Miscellaneous Projects | 2012210003 |  | Miscellaneous Projects | 115548.79 | 110085.7301 | 0 | 131725.6206
Aljazi Project | Al - Jazi Inv. 2 | 2 | Aljazi Project2 | 322383 | 151797.77 | 0 | 181638.77
South Helwan PP (CP-117) | 2009210008 |  | South Helwan PP (CP-117) | 239912.09 | 212030.41 | 37857.23 | 249887.64
Miscellaneous Projects | 2009210012 |  | Miscellaneous Projects | 137787.2 | 0 | 0 | 137787.2
Miscellaneous Projects | 2004210003 |  | Miscellaneous Projects | 815592 | 0 | 0 | 929774.88
Siemens 6x500/220 KV GIS-MOU | Compensation Banha |  | Siemens 6x500/220 KV GIS-MOU | 4476190.48 | 0 | 0 | 4700000.004
LAYYAH CCPP | 485 |  | LAYYAH CCPP | 6501455 | 6501455 | 0 | 6501455
Nagaa Hamady/Assuit OHTL | Soc.2020 تشيد نجع |  | Nagaa Hamady/Assuit OHTL | 5000 | 0 | 0 | 5000
Elniger | Close El Niger |  | Elniger | 562545.476 | 0 | 0 | 562545.476
Pyramids Industrial Park | Closing PIP |  | Pyramids Industrial Park | 25345136.15 | 0 | 0 | 25345136.15
Suez Gulf Substation | 11 EGP - Suez Gulf |  | Suez Gulf Substation | 299591.8667 | 283114.31 | 31457.15 | 314571.46
Assuit PP (CP-118) | 1909210017 |  | Assuit PP (CP-118) | 3016678.67 | 2662218.93 | 475126.89 | 3137345.82
Manshiet Nasser Substation | 1907210016 |  | Manshiet Nasser Substation | 1421598.43 | 1504611.48 | 0 | 1504611.48
Manshiet Nasser Substation | 1906210011 |  | Manshiet Nasser Substation | 929969.05 | 984273.81 | 0 | 984273.81
Suez Gulf Substation | 1909210011 |  | Suez Gulf Substation | 601609.45 | 601609.45 | 0 | 601609.45
Suez Gulf Substation | 1909210009 |  | Suez Gulf Substation | 348508.68 | 348508.68 | 0 | 348508.68
Suez Gulf Substation | 1909210008 |  | Suez Gulf Substation | 2533.08 | 2533.08 | 0 | 2533.08
Zambia Project | SCD4/004Adj |  | Zambia Project | 71791.41 | 0 | 0 | 71791.41
Beni Seuf - 358 | Soc inv 4-5 Itay | 4 | Beni Seuf - 3584 | 4122636 | 0 | 0 | 4122636
Phosfat | Inv.6 Phosfat | 6 | Phosfat6 | 1426885 | 0 | 0 | 1426885
South Helwan PP (CP-117) | 1901210011 |  | South Helwan PP (CP-117) | 36546.75 | 41461.55 | 0 | 41461.55
Ethiopia S/S | P-27-09 AccRev | 27 | Ethiopia S/S27 | 103540391.93 | 0 | 0 | 103540391.93
Akhmem Assiut | Soc Inv 48 ASUIT | 48 | Akhmem Assiut48 | 2182603.5 | 0 | 0 | 2182603.5
Manshiet Nasser Substation | 1903210019 |  | Manshiet Nasser Substation | -7593753.66 | -7593753.66 | 0 | -7593753.66
Abu Qir PP (CP-117) | 180151 |  | Abu Qir PP (CP-117) | 735093.49 | 735093.49 | 0 | 735093.49
Akhmem Assiut | Ref.Install.1Assuit |  | Akhmem Assiut | 85910.91 | 0 | 0 | 85910.91
Beni-Suef Power Plant EPC | 180140 |  | Beni-Suef Power Plant EPC | 44018941.66 | 44018941.66 | 0 | 44018941.66
Al-Shabab PP Phase II (CP-117) | 8 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 1178172.06 | 0 | 0 | 1178172.06
Al-Shabab PP Phase II (CP-117) | 7 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 1695411.37 | 0 | 0 | 1695411.37
W Dam PP Phase II (CP-117) | 18 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 368421.1 | 0 | 0 | 368421.1
Suez Gulf Substation | 180060 |  | Suez Gulf Substation | 3136178.1 | 2969263.01 | 329918.11 | 3299181.12
W Dam PP Phase II (CP-117) | 13 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 12764.38 | 12764.38 | 0 | 12764.38
Al-Shabab PP Phase II (CP-117) | 16 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 430785.67 | 430785.67 | 0 | 430785.67
Al-Wukair 11 Substation | 180161 |  | Al-Wukair 11 Substation | 7641356.97 | 7641356.97 | 0 | 7641356.97
Marsa Matrouh 500KV | Inv, 5 usd Borg Arab | 5 | Marsa Matrouh 500KV5 | 1382274.01 | 0 | 0 | 1382274.01
Damac 2x60/22 KV S/S | Adj. iNV. 20 | 20 | Damac 2x60/22 KV S/S20 | 48778576.27 | 0 | 0 | 48778576.27
Barwa 2x60/22 KV S/S | Adj. Inv. 19 | 19 | Barwa 2x60/22 KV S/S19 | 46223782.89 | 0 | 0 | 46223782.89
W Dam PP Phase II (CP-117) | 180112 |  | W Dam PP Phase II (CP-117) | 276348.34 | 0 | 0 | 290711.56
South Helwan PP (CP-117) | 180127 |  | South Helwan PP (CP-117) | 157312.61 | 170906.47 | 0 | 170906.47
Abu Qir PP (CP-118) | 30 |  | Abu Qir PP (CP-118) | 2553558.4572 | 0 | 0 | 2553558.4572
Suez PP (CP-106) | 81 |  | Suez PP (CP-106) | 9471955.02 | 0 | 0 | 9471955.02
Al-Shabab PP Phase II (CP-117) | 180026 |  | Al-Shabab PP Phase II (CP-117) | 678293.2 | 0 | 0 | 712207.86
Al-Shabab PP Phase II (CP-117) | 180022 |  | Al-Shabab PP Phase II (CP-117) | 2073161.5524 | 0 | 0 | 2176819.63
Al-Shabab PP Phase II (CP-117) | 180017 |  | Al-Shabab PP Phase II (CP-117) | 156620.07 | 0 | 0 | 156620.07
Attaqa Power Plant | 119 |  | Attaqa Power Plant | -2694457109.9679 | 0 | 0 | -2694457109.9679
IRAQ - Substations Soil Invest | 39 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
Banha PP (CP-118) | 97 |  | Banha PP (CP-118) | 10569356.3243 | 0 | 0 | 10569356.3243
Ain-Sokhna PP(CP-102) | 114 |  | Ain-Sokhna PP(CP-102) | 699578 | 0 | 0 | 699578
Beni-Suef PP Site Preparation | 18 |  | Beni-Suef PP Site Preparation | 84425984.25 | 0 | 0 | 84425984.25
Beni-Suef Power Plant EPC | 1 |  | Beni-Suef Power Plant EPC | 727472080.7817 | 0 | 0 | 727472080.7817
IRAQ - Al-Diwaniya Power Plant | 21 |  | IRAQ - Al-Diwaniya Power Plant | 507140001 | 0 | 0 | 507140001
Ain-Sokhna PP (CP-117) | 68 |  | Ain-Sokhna PP (CP-117) | 54452776.9989 | 0 | 0 | 54452776.9989
Giza North PP Ph I,II (CP-117) | 85 |  | Giza North PP Ph I,II (CP-117) | 60934040.024 | 0 | 0 | 60934040.024
South Helwan PP (CP-117) | 107 |  | South Helwan PP (CP-117) | 191119874.7274 | 0 | 0 | 191119874.7274
6th Oct. Ph2 PP-Elect Work | 111 |  | 6th Oct. Ph2 PP-Elect Work | -955723.6659 | 0 | 0 | -955723.6659
South Helwan PP (CP-117) | 180057 |  | South Helwan PP (CP-117) | 346909.02 | 0 | 0 | 364939.63
W Dam PP Phase II (CP-117) | 49 |  | W Dam PP Phase II (CP-117) | 13861916.9184 | 0 | 0 | 13861916.9184
New Heliopolis | Inv.9 Heliopolis | 9 | New Heliopolis9 | 11490807.56 | 0 | 0 | 11490807.56
Cairo North PP Rehabilitation | Last Invoice Cairo N |  | Cairo North PP Rehabilitation | 232789.5273 | 217658.21 | 23278.95 | 240937.16
Abou El Matameer and Sammanoud | Inv 81 P5 Sammound | 81 | Abou El Matameer and Sammanoud81 | 11846425.95 | 0 | 0 | 11846425.95
Akhmem Assiut | inv. 8 Assuit Akhmem | 8 | Akhmem Assiut8 | 41447501.75 | 0 | 0 | 41447501.75
Akhmem Assiut | inv. 6 Assuit Akhmem | 6 | Akhmem Assiut6 | 2576660.8 | 0 | 0 | 2576660.8
Beni-Suef Power Plant EPC | 8 beni Suef - 1020 | 1020 | Beni-Suef Power Plant EPC1020 | 950809783.62 | 950809783.62 | 0 | 950809783.62
Beni-Suef Power Plant EPC | 7 beni Suef - 1020 | 1020 | Beni-Suef Power Plant EPC1020 | 1360598246 | 1360598246 | 0 | 1360598246
New Capital | 12 |  | New Capital | 3945791.24 | 0 | 0 | 3945791.24
New Capital | Inv 1 Abo Zaabel | 1 | New Capital1 | 32887642.82 | 0 | 0 | 32887642.82
EMAAR-PKG#107-MARASSI | VAT 2 PKG107 |  | EMAAR-PKG#107-MARASSI | -29967.5 | 0 | 0 | -29967.5
Giza North PP Ph I,II (CP-117) | 36 EGP-Giza North 1& |  | Giza North PP Ph I,II (CP-117) | 9865294.1714 | 0 | 0 | 10358558.88
Al-Shabab PP Phase II (CP-117) | 12 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 171306.181 | 150492.48 | 26980.72 | 179871.49
Suez Gulf Substation | 2 EGP - Suez Gulf |  | Suez Gulf Substation | 1431237.0867 | 850 | 217218.78 | 1448408.5317
Cameron EDC | 019/2019 |  | Cameron EDC | 606773.67 | 603773.77 | 0 | 603773.77
Cameron EDC | 010/2019 |  | Cameron EDC | 238190.92 | 237942.78 | 0 | 237942.78
Cameron EDC | 022/2020 FCV |  | Cameron EDC | 148684449.87 | 148684449.87 | 0 | 148684449.87
Al-Shabab PP Phase II (CP-117) | 2002210017 |  | Al-Shabab PP Phase II (CP-117) | 71210.11 | 62934.34 | 11236.69 | 74171.03
W Dam PP Phase II (CP-117) | 525 |  | W Dam PP Phase II (CP-117) | 952433.46 | 899273.1 | 11231.87 | 910504.97
Al-Shabab PP Phase II (CP-117) | 180109 |  | Al-Shabab PP Phase II (CP-117) | 123920.19 | 110806.81 | 19554.14 | 130360.95
W Dam PP Phase II (CP-117) | 180102 |  | W Dam PP Phase II (CP-117) | 10048.19 | 8984.88 | 1585.57 | 10570.45
W Dam PP Phase II (CP-117) | 180040 |  | W Dam PP Phase II (CP-117) | 53513.3619 | 0 | 0 | 56189.03
Al-Shabab PP Phase II (CP-117) | 18 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 3859716.7333 | 0 | 607905.39 | 607905.39
W Dam PP Phase II (CP-117) | 11 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 114713.0476 | 86857.13 | 18067.31 | 120448.7
Al-Shabab PP Phase II (CP-117) | 180006 |  | Al-Shabab PP Phase II (CP-117) | 296307.11 | 264951.54 | 46756.15 | 311707.69
W Dam PP Phase II (CP-117) | 10 USD- West Domiat |  | W Dam PP Phase II (CP-117) | 2928987.5048 | 2614121.35 | 461315.53 | 3075436.88
W Dam PP Phase II (CP-117) | 9 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 78700.1238 | 0 | 12395.27 | 12395.27
W Dam PP Phase II (CP-117) | 8 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 665214.67 | 0 | 104771.31 | 104771.31
W Dam PP Phase II (CP-117) | 4 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 575161.01 | 0 | 86274.15 | 603919.0605
Suez Gulf Substation | 17 EGP Main Progress |  | Suez Gulf Substation | 1500870.19 | 1420990.2 | 157887.8 | 1578878
Suez Gulf Substation | 180049 |  | Suez Gulf Substation | 321619.02 | 304501.66 | 33833.52 | 338335.18
Suez Gulf Substation | 8 EGP - Suez Gulf |  | Suez Gulf Substation | 2957422.0857 | 0 | 310529.32 | 310529.32
Siemens 6x500/220 KV GIS-MOU | Inv 65 P7 Assuit | 65 | Siemens 6x500/220 KV GIS-MOU65 | 2021471.726 | 1462332.646 | 303220.76 | 1765553.406
Siemens 6x500/220 KV GIS-MOU | Inv 49 P14El Natroun | 49 | Siemens 6x500/220 KV GIS-MOU49 | 1797920.4 | 1300615.62 | 269688.06 | 1570303.68
Siemens 6x500/220 KV GIS-MOU | inv 42 P 8 Banha | 42 | Siemens 6x500/220 KV GIS-MOU42 | 3035091.3933 | 3293377.67 | 682895.56 | 3976273.23
Barwa 2x60/22 KV S/S | Inv 21 Barwa | 21 | Barwa 2x60/22 KV S/S21 | 1280709.49 | 905860.59 | 192106.44 | 1097967.03
Barwa 2x60/22 KV S/S | Inv 18 Barwa | 18 | Barwa 2x60/22 KV S/S18 | 1446935.6 | 1023280.9 | 217040.35 | 1240321.25
Damac 2x60/22 KV S/S | Inv 31 Damac | 31 | Damac 2x60/22 KV S/S31 | 752180.07 | 532133.79 | 112827 | 644960.79
New Capital | new acpital zabaal 2 |  | New Capital | 21843369.1 | 16950369.245 | 2293553.75 | 19243922.995
New Capital | inv 2 Eltbeen | 2 | New Capital2 | 4808268.97 | 3731130.19 | 504868.24 | 4235998.43
PIP- Zonafranca | Zona franka inv.17 F | 17 | PIP- Zonafranca17 | 15307277.27 | 0 | 2635752.57 | 2635752.57
South Helwan PP (CP-117) | Inv 12,13 SH | 12 | South Helwan PP (CP-117)12 | 1964148.8 | 1596079.82 | 309353.44 | 1905433.26
Al-Wukair 11 Substation | inv(ESC-SA-Civil-06) | 6 | Al-Wukair 11 Substation6 | 2799081.89 | 0 | 0 | 0
Al-Wukair 11 Substation | inv(ESC-SA-Civil-05) | 5 | Al-Wukair 11 Substation5 | 1368448.54 | 0 | 0 | 0
Berket Ghelion | 4 gheleon |  | Berket Ghelion | 4933391 | 2947383.32 | 1233347.75 | 4180731.07
Giza North PP Ph I,II (CP-117) | 29 Euro - Giza N.12 |  | Giza North PP Ph I,II (CP-117) | 477446.8476 | 426121.31 | 0 | 426121.31
Beni Suef Substation R61 | (19)BINE SUIF2 | 19 | Beni Suef Substation R6119 | 5980776 | 3827674.29 | 1388851.53 | 5216525.82
Beni Suef Substation R61 | (18) bine suif 2 | 18 | Beni Suef Substation R6118 | 10069327 | 2929689.9 | 6136645.4 | 9066335.3
Tamey El-amdeed Substation | TAM-CW-EGP-23 | 23 | Tamey El-amdeed Substation23 | 56099.67 | 41513.75 | 8414.95 | 49928.7
Beni Suef Substation R61 | BSF-CW-EURO-08 | 8 | Beni Suef Substation R618 | 37786.41 | 27362.5 | 5667.96 | 33030.46
Tamey El-amdeed Substation | TAM-SW-EGP-12 | 12 | Tamey El-amdeed Substation12 | 203875 | 0 | 30581.25 | 30581.25
Tamey El-amdeed Substation | TAM-SW-EGP-11 | 11 | Tamey El-amdeed Substation11 | 98875 | 0 | 14831.25 | 14831.25
Beni Suef Substation R61 | BSF-CW-EURO-06 | 6 | Beni Suef Substation R616 | 1215235.59 | 851195.7 | 182285.34 | 1033481.04
Ismailiya East Substation | ISE-CW-EGP-10 | 10 | Ismailiya East Substation10 | 3542671 | 2621576.54 | 531400.65 | 3152977.19
Ismailiya East Substation | ISE-CW-EGP-09 | 9 | Ismailiya East Substation9 | 3918783 | 2919493.33 | 587817.45 | 3507310.78
Al Mostathmreen GIS Substation | MOS-SD-EURO-11 | 11 | Al Mostathmreen GIS Substation11 | 852581.03 | 618121.25 | 127887.15 | 746008.4
Al Mostathmreen GIS Substation | 30sd elmostsmrin |  | Al Mostathmreen GIS Substation | 45275.2 | 33730.02 | 6791.28 | 40521.3
Al Mostathmreen GIS Substation | 24sd elmostsmrin |  | Al Mostathmreen GIS Substation | 685296.9 | 510546.19 | 102794.54 | 613340.73
Al Mostathmreen GIS Substation | 16sd mosstasmreen |  | Al Mostathmreen GIS Substation | 2618460 | 1950752.7 | 392769 | 2343521.7
Al Mostathmreen GIS Substation | (6)SD EURO | 6 | Al Mostathmreen GIS Substation6 | 568387 | 423448.22 | 85258.1 | 508706.32
Berket Ghelion | Gheleon 10 |  | Berket Ghelion | 2368503.48 | 1415084.9 | 592125.9 | 2007210.8
New Capital | new capital zabal 1 |  | New Capital | 32887642.83 | 25520721.12 | 3453202.5 | 28973923.62
Al-Shabab PP Phase II (CP-117) | 10 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 1159738.7714 | 0 | 0 | 0
Berket Ghelion | inv 11 Ghalion | 11 | Berket Ghelion11 | 2749343.96 | 1642314.3 | 687336 | 2329650.3
Beni Suef ISKRA | 180004 |  | Beni Suef ISKRA | 653726.26 | 555667.32 | 98058.94 | 653726.26
Sodic Club House | (26) sodic club | 26 | Sodic Club House26 | 2960542.86 | 2678644.803 | 653831.8 | 3332476.603
Berket Ghelion | Gheleon 19 |  | Berket Ghelion | 1176766.28 | 702704.95 | 294191.6 | 996896.55
Berket Ghelion | Inv. 18 Gheleon | 18 | Berket Ghelion18 | 2724599.02 | 1627535.32 | 681147.5 | 2308682.82
New Giza 2 | 19 new giza 2 |  | New Giza 2 | 5851987.78 | 4160256.439 | 1228917.43 | 5389173.869
New Giza 2 | NEW GIZA2 -IPC 27 | 27 | New Giza 227 | 6000000 | 6000000 | 0 | 6000000
EMAAR-PKG#62-UPTOWN | 18100054 |  | EMAAR-PKG#62-UPTOWN | 6771404.91 | 2219134.03 | 2160771.53 | 4379905.56
EMAAR-PKG#62-UPTOWN | (11) pkg#62 | 11 | EMAAR-PKG#62-UPTOWN11 | 3181279.48 | 1665617.5 | 989355.77 | 2654973.27
EMAAR-PKG#107-MARASSI | (9) pkg#107 | 9 | EMAAR-PKG#107-MARASSI9 | 1856943 | 1514267.88 | 288382.69 | 1802650.57
Giza North PP Ph I,II (CP-117) | 31 Euro -Giza N.I&II |  | Giza North PP Ph I,II (CP-117) | 253624.381 | 226359.75 | 0 | 226359.75
Beni Seuf - 358 | Banha-Zagazg Inv.03 | 3 | Beni Seuf - 3583 | 40028672 | 0 | 6884070 | 6884070
Beni Seuf - 358 | Inv No 3 Bani swif | 3 | Beni Seuf - 3583 | 1979440.05 | 1573654.84 | 296916.01 | 1870570.85
Al-Shabab PP Phase II (CP-117) | 8 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 59558.6571 | 51550.07 | 9380.49 | 61795.06
New Giza 2 | (20)NEW GIZA 2 | 20 | New Giza 220 | 7075292 | 5821574.98 | 1485811.48 | 7307386.46
Ismalia Bridge | 2alblagat |  | Ismalia Bridge | 6537625 | 2307926.3 | 2700000 | 5932494.3
Barwa and Damac 220 OHTL | Inv No8 Wattanya220 | 8 | Barwa and Damac 220 OHTL8 | 2393557.75 | 1776805.5 | 359033.7 | 2135839.2
Beni-Suef Power Plant EPC | Beni Swef Inv March |  | Beni-Suef Power Plant EPC | 220000000 | 220000000 | 0 | 220000000
Abo Quir - Badr 500KV | Payment No.5 |  | Abo Quir - Badr 500KV | 631413.27 | 17678.88 | 0 | 17678.88
Wall - New Giza | (4) new giza wall | 4 | Wall - New Giza4 | 612721 | 664733.66 | 0 | 664733.66
Royal City | ROYAL CITY-IPC24 | 24 | Royal City24 | 15230773.26 | 9213642.983 | 3240464.39 | 12454107.373
Royal City | Royal City -IPC14 | 14 | Royal City14 | 6957536.92 | 5980044.91 | 2619847.9 | 8599892.81
Royal City | ROYALCITY-IPC13 | 13 | Royal City13 | 10776531.08 | 6339338.484 | 2702989.64 | 9042328.124
Royal City | ROYALCITY-IPC-11 | 11 | Royal City11 | 2576874.1 | 3446024.635 | 662407.85 | 4108432.485
Shubra-Banha lock&load | SHOBRE/BANHA-NILL FI |  | Shubra-Banha lock&load | 2839375.76 | 1590000 | 0 | 1590000
PIP Zona 2 | Inv.2 Zona 2 | 2 | PIP Zona 22 | 8474156.16 | 7965706.808 | 0 | 7965706.808
PIP Zona 2 | Inv,1 ZONA 2 | 1 | PIP Zona 21 | 7467710.59 | 7019647.9595 | 0 | 7019647.9595
Siemens 6x500/220 KV GIS-MOU | Inv 48 P13 El Natrun | 48 | Siemens 6x500/220 KV GIS-MOU48 | 2740112.21 | 1982197.18 | 411016.83 | 2393214.01
Barwa 2x60/22 KV S/S | 10 |  | Barwa 2x60/22 KV S/S | 4981194.27 | 2818929.29 | 597743.34 | 4412911.47
Gabal Elgalalaa | Ref. Ret Elgagalah |  | Gabal Elgalalaa | 1488429.26 | 1488429.26 | 0 | 1488429.26
Al-Shabab PP Phase II (CP-117) | 5 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2584814.8617 | 59961.44 | 392374.9 | 454205.18
Al-Shabab PP Phase II (CP-117) | 14 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 866936.2381 | 718254.94 | 136542.46 | 910283.05
South Helwan PP (CP-117) | 180133 |  | South Helwan PP (CP-117) | 254108.84 | 265995.42 | 0 | 265995.42
South Helwan PP (CP-117) | 180063 |  | South Helwan PP (CP-117) | 181104.17 | 0 | 0 | 0
Abu Qir PP (CP-117) | Inv Abu Quir |  | Abu Qir PP (CP-117) | 10613.08 | 10613.08 | 0 | 10613.08
GPC-Gupco (Automation) | 1 EGP - GPC Gupco |  | GPC-Gupco (Automation) | 58232.96 | 58232.96 | 0 | 58232.96
Apache Electrical Works | Apachi Inv No P.C#15 | 15 | Apache Electrical Works15 | 51656.33 | 51656.33 | 0 | 51656.33
Al Mostathmreen GIS Substation | (13)SD EGP | 13 | Al Mostathmreen GIS Substation13 | 438810 | 326913.35 | 65821.56 | 392734.91
Al Mostathmreen GIS Substation | SD EURO (5) | 5 | Al Mostathmreen GIS Substation5 | 3123383 | 2326920.15 | 468507.56 | 2795427.71
Al Mostathmreen GIS Substation | SD(10) mosstsmareen | 10 | Al Mostathmreen GIS Substation10 | 333395 | 248379.27 | 50009.25 | 298388.52
Al-Wukair 11 Substation | Inv April Qatar |  | Al-Wukair 11 Substation | 1952766 | 1952766 | 0 | 1952766
EMAAR-PKG#107-MARASSI | (8) PKG#107 | 8 | EMAAR-PKG#107-MARASSI8 | 4398604 | 3203756.07 | 609850.77 | 3813606.84
Flour project | 10078 |  | Flour project | 36786 | 37050.735 | 0 | 37050.735
Siemens 6x500/220 KV GIS-MOU | ret40 itay 11 |  | Siemens 6x500/220 KV GIS-MOU | 225941.11 | 225881.11 | 0 | 225881.11
Military 110 Kayan Project | Inv No2 ElKean 220 | 2 | Military 110 Kayan Project2 | 12238166.24 | 11105732.24 | 0 | 11105732.24
Banha PP (CP-118) | 22 USD - Banha 118 |  | Banha PP (CP-118) | 27229.07 | 27229.07 | 0 | 27229.07
Beni Seuf - 358 | Inv No1 Itay | 1 | Beni Seuf - 3581 | 187803669.9 | 149303317.58 | 28170550.49 | 177473868.07
Beni Seuf - 358 | Inv No 2 Bani swif | 2 | Beni Seuf - 3582 | 37272961.99 | 29632004.78 | 5590944.3 | 35222949.08
Kuwait | 1-132KVA-J | 132 | Kuwait132 | 119660.254 | 89745.2 | 0 | 89745.2
Beni Seuf - 358 | Inv No2 Itay | 2 | Beni Seuf - 3582 | 40910481.25 | 32397412.17 | 6262992.61 | 38660404.78
Kayan 3 New Cairo Capital City | (4) kayan | 4 | Kayan 3 New Cairo Capital City4 | 79493687 | 10553941.5 | 12000000 | 72140121.5
Beni Suef Substation R61 | 1cw beni suif |  | Beni Suef Substation R61 | 15153556 | 11289399.22 | 2273033.4 | 13562432.62
Al Mostathmreen GIS Substation | 17sd mosstasmreen |  | Al Mostathmreen GIS Substation | 3402 | 2534.36 | 510.38 | 3044.74
W Dam PP Phase II (CP-117) | 18 EGP-West Domiat |  | W Dam PP Phase II (CP-117) | 405120.56 | 361570.1 | 63806.49 | 425376.59
Ministries Buildings | Min.long lead Ipc3 | 3 | Ministries Buildings3 | 34860731 | 329295 | 29333800.9 | 29663095.9
Akhmem Assiut | Inv.25 Assuit Akhmem | 25 | Akhmem Assiut25 | 6024487.68 | 4789467.7 | 903673.15 | 5693140.85
Akhmem - Qena | Inv.18 Qena - Akhmem | 18 | Akhmem - Qena18 | 1166508.66 | 927374.37 | 174976.3 | 1102350.67
EMAAR-PKG#53-UPTOWN | (23) pkg#53 | 23 | EMAAR-PKG#53-UPTOWN23 | 16028014 | 14265897.01 | 2725624.69 | 16991521.7
EMAAR-PKG#62-UPTOWN | (9)PKG#62 | 9 | EMAAR-PKG#62-UPTOWN9 | 3259122 | 2334147.17 | 1341717.37 | 3675864.54
Abou El Matameer and Sammanoud | Inv 93P12Abo Matami | 93 | Abou El Matameer and Sammanoud93 | 3714366.88 | 2686973.01 | 557155.03 | 3244128.04
Abou El Matameer and Sammanoud | Inv 91P11Abo Matamir | 91 | Abou El Matameer and Sammanoud91 | 1798421.83 | 0 | 0 | 1798421.83
Abou El Matameer and Sammanoud | aboelmatamir 9inv.87 | 87 | Abou El Matameer and Sammanoud87 | 2590933.68 | 1874281.42 | 388640.05 | 2262921.47
Abou El Matameer and Sammanoud | aboelmatamir 7inv.83 | 83 | Abou El Matameer and Sammanoud83 | 4724256.33 | 3417527.03 | 708638.45 | 4126165.48
Abou El Matameer and Sammanoud | Inv 76 P3 Sammound | 76 | Abou El Matameer and Sammanoud76 | 8537190.36 | 6175803.497 | 1280578.563 | 7456382.06
PIP Zona 2 | Inv. 6 Zona Franka | 6 | PIP Zona 26 | 3651791.61 | 3432684.1305 | 0 | 3432684.1305
El Mostakbal City Project | Inv. 6 Mostakbal | 6 | El Mostakbal City Project6 | 60125306.65 | 49904004.51 | 12626314.4 | 62530318.91
Damac 2x60/22 KV S/S | Damac |  | Damac 2x60/22 KV S/S | 985085.3 | 696884.85 | 147762.78 | 844647.63
Bani Suef Old Substation | (25)bini suif 2 | 25 | Bani Suef Old Substation25 | 3992998.03 | 5924419.67 | 0 | 5924419.67
Barwa 2x60/22 KV S/S | Inv. Barwa 34 |  | Barwa 2x60/22 KV S/S | 1263037.4 | 893325.1 | 189455.6 | 1082780.7
Barwa 2x60/22 KV S/S | Inv. Barwa 35 |  | Barwa 2x60/22 KV S/S | 853918.98 | 603957.5 | 128087.85 | 732045.35
GPC-Gupco (Automation) | Petrofac Mobilisatio |  | GPC-Gupco (Automation) | 16130 | 16130 | 0 | 16130
Damac 2x60/22 KV S/S | Inv. 35 Damac | 35 | Damac 2x60/22 KV S/S35 | 640404.04 | 452909.17 | 96060.6 | 548969.77
Abou El Matameer and Sammanoud | Soc 73 Abo almat3 |  | Abou El Matameer and Sammanoud | 217153.6 | 217153.6 | 0 | 217153.6
Suez Gulf Substation | 180080 |  | Suez Gulf Substation | 830.32 | 786.13 | 87.35 | 873.48
Suez Gulf Substation | 180051 |  | Suez Gulf Substation | 903901.01 | 855793.18 | 95088.13 | 950881.31
Sodic Club House | SODIC CLUB-IPC35 | 35 | Sodic Club House35 | 4583109.75 | 2565043.8775 | 1550001.44 | 4115045.3175
Sodic Club House | (27) sodic club | 27 | Sodic Club House27 | 5615979.81 | 4546610.8405 | 404780.93 | 4951391.7705
South Helwan PP (CP-117) | 180001 |  | South Helwan PP (CP-117) | 1064344.63 | 951714.4 | 167949.6 | 1119664
Al-Wukair 11 Substation | 180011 |  | Al-Wukair 11 Substation | 1946741.9 | 1946741.9 | 0 | 1946741.9
Abou El Matameer and Sammanoud | soc 74 abo elmatamer |  | Abou El Matameer and Sammanoud | 84546.1 | 84546.05 | 0 | 84546.05
Al Mostathmreen GIS Substation | 31sd elmostsmrin |  | Al Mostathmreen GIS Substation | 33956.3 | 25297.44 | 5093.45 | 30390.89
Assuit PP (CP-118) | Adj Invoice.25 EUR |  | Assuit PP (CP-118) | 419062.41 | 374013.2 | 66002.33 | 440015.53
Assuit PP (CP-118) | 2002210003 |  | Assuit PP (CP-118) | 436928.47 | 389958.66 | 68816.23 | 458774.89
Assuit PP (CP-118) | 1907210003 |  | Assuit PP (CP-118) | 678103.04 | 605206.96 | 106801.23 | 712008.19
Assuit PP (CP-118) | 1903210001 |  | Assuit PP (CP-118) | 238723.8 | 213060.99 | 37599 | 250659.99
Assuit PP (CP-118) | 2108210003 |  | Assuit PP (CP-118) | 943539.19 | 824181.48 | 148607.42 | 972788.9
Assuit PP (CP-118) | 2007210001 |  | Assuit PP (CP-118) | 1594743.24 | 1407360.91 | 251172.06 | 1658532.97
Assuit PP (CP-118) | 2006210002 |  | Assuit PP (CP-118) | 278437.33 | 245720.95 | 43853.88 | 289574.83
Assuit PP (CP-118) | 2005210003 |  | Assuit PP (CP-118) | 1844124.47 | 1627439.84 | 290449.6 | 1917889.44
Assuit PP (CP-118) | 492 |  | Assuit PP (CP-118) | 44109.57 | 39367.79 | 6947.26 | 46315.05
South Helwan PP (CP-117) | 180014 |  | South Helwan PP (CP-117) | 366239.64 | 314696.57 | 55534.69 | 370231.26
Ain-Sokhna PP (CP-111) | Inv No 15 Sokhna 111 | 15 | Ain-Sokhna PP (CP-111)15 | 1366926.6762 | 1435273.01 | 0 | 1435273.01
Marsa Matrouh 500KV | Inv.67 Borg Alarab | 67 | Marsa Matrouh 500KV67 | 5800662.04 | 4379139.92 | 383203.54 | 4762343.46
Marsa Matrouh 500KV | Inv.60 Borg Alarab | 60 | Marsa Matrouh 500KV60 | 8205741.9 | 7167716.2 | 861602.9 | 8029319.1
Marsa Matrouh 500KV | Inv.51 Borg Alarab | 51 | Marsa Matrouh 500KV51 | 15572219.05 | 11149713.81 | 1635083 | 12784796.81
Marsa Matrouh 500KV | Inv.36 Borg Alarab | 36 | Marsa Matrouh 500KV36 | 20515172.85 | 17676141.19 | 2154093.15 | 19830234.34
Marsa Matrouh 500KV | Inv.30 Borg Alarab | 30 | Marsa Matrouh 500KV30 | 62842694.49 | 44832215.44 | 6598482.92 | 51430698.36
Marsa Matrouh 500KV | Inv.24 Borg Alarab | 24 | Marsa Matrouh 500KV24 | 2126242.02 | 1857277.58 | 223255.41 | 2080532.99
Marsa Matrouh 500KV | Inv.15Usd borg alarb | 15 | Marsa Matrouh 500KV15 | 242857.1 | 211255.95 | 25500 | 236755.95
Marsa Matrouh 500KV | Inv.18Usd borg alarb | 18 | Marsa Matrouh 500KV18 | 787370.4 | 685349.7388 | 82673.89 | 768023.6288
Marsa Matrouh 500KV | Inv.8 Borg Alarab | 8 | Marsa Matrouh 500KV8 | 3554680.7 | 3105013.72 | 373241.47 | 3478255.19
Marsa Matrouh 500KV | Inv.19Usd borg alarb | 19 | Marsa Matrouh 500KV19 | 1738927.5 | 1296421.1 | 182587.39 | 1479008.49
Marsa Matrouh 500KV | Inv. 2 usd Borg Arab | 2 | Marsa Matrouh 500KV2 | 3843466.97 | 3338972.49 | 403564.03 | 3742536.52
EMAAR-PKG117- MARASSI | PKG#117-IPC(5) | 5 | EMAAR-PKG117- MARASSI5 | 6909335.09 | 5093815.29 | 603547.82 | 5697363.11
Military 110 Kayan Project | Elkayan Inv. 11 | 11 | Military 110 Kayan Project11 | 16122958.23 | 14631191.7 | 0 | 14631191.7
kayan wall lock & Load | IPC3-KAYAN LOAK&LOAD | 3 | kayan wall lock & Load3 | 5542200 | 3329140.4 | 1700000 | 5029140.4
Royal City | (5) ROYAL CITY | 5 | Royal City5 | 9626900.5 | 7170078.235 | 1373608.88 | 8543687.115
EMAAR-PKG#53-UPTOWN | (29) pkg#53 | 29 | EMAAR-PKG#53-UPTOWN29 | 17007596.13 | 11883297.1 | 4020621.88 | 15903918.98
kayan wall lock & Load | KAYAN LOCK&LOAD-IPC2 | 2 | kayan wall lock & Load2 | 9801900 | 8894827.6 | 0 | 8894827.6
4 SS - Technical Service | 214 |  | 4 SS - Technical Service | 889003.08 | 889003.08 | 0 | 889003.08
Cairo Capital S1 | Inv. 8 Project S 1 | 8 | Cairo Capital S18 | 49197972.07 | 37021072 | 7379695.81 | 44400767.81
Cairo Capital S1 | Inv. 5 Project S 1 | 5 | Cairo Capital S15 | 294355018.7 | 221501738 | 44153252.81 | 265654990.81
EMAAR-PKG#53-UPTOWN | PKG#53-IPC(31) | 31 | EMAAR-PKG#53-UPTOWN31 | 17457747.57 | 11753104.21 | 2818389.38 | 14571493.59
Ministries Buildings | Mini Alocation IPC07 | 7 | Ministries Buildings7 | 19093536.78 | 2150095 | 14011412.8 | 16161507.8
Al-Wukair 11 Substation | 180074 |  | Al-Wukair 11 Substation | 301343 | 301343 | 0 | 301343
Suez Gulf Substation | 180050 |  | Suez Gulf Substation | 74219.77 | 70269.62 | 7807.73 | 78077.35
New Capital Tunnels | M.B.Z-IPC (2) | 2 | New Capital Tunnels2 | 72366701.1 | 2372381.85 | 0 | 65672381.85
Lina Farm Substation | 2 USD - Lina |  | Lina Farm Substation | 104405.9 | 104405.9 | 0 | 104405.9
Attaqa Power Plant | PV Sep |  | Attaqa Power Plant | 0.01 | 0.01 | 0 | 0.01
EMAAR-PKG117- MARASSI | 18100047 |  | EMAAR-PKG117- MARASSI | 4332593.54 | 4793875.01 | 571929.38 | 5365804.39
Akhmem - Qena | Inv.12 Qena- Akhmem$ | 12 | Akhmem - Qena12 | 370999.7 | 313121.63 | 0 | 313121.63
Cairo Capital S1 | Inv. 3 Project S 1 | 3 | Cairo Capital S13 | 30202891.45 | 22727273.95 | 4530433.7 | 27257707.65
Akhmem - Qena | Inv.11 Qena- Akhmem$ | 11 | Akhmem - Qena11 | 2023.28 | 1477.09 | 0 | 1477.09
South Helwan PP (CP-117) | 180125 |  | South Helwan PP (CP-117) | 52552.49 | 55283.91 | 0 | 55283.91
EMAAR-PKG#53-UPTOWN | IPC (34) - PKG#53 | 34 | EMAAR-PKG#53-UPTOWN34 | 62924.2 | 1344501.4 | 0 | 1344501.4
Kayan 3 New Cairo Capital City | Kayan finishing-ipc5 | 5 | Kayan 3 New Cairo Capital City5 | 54046053.75 | 39276155.35 | 9500000 | 48776155.35
Tamey El-amdeed Substation | TAM-CW-IPC5 | 5 | Tamey El-amdeed Substation5 | 5185072.85 | 3862879.27 | 777760.93 | 4640640.2
Beni Suef Substation R61 | BSF-CW-IPC 8 | 8 | Beni Suef Substation R618 | 1776658 | 1323610.21 | 266498.7 | 1590108.91
Akhmem - Qena | Inv.14 Qena- Akhmem$ | 14 | Akhmem - Qena14 | 221966.15 | 188492.15 | 0 | 188492.15
Akhmem - Qena | Inv.15 Qena- Akhmem$ | 15 | Akhmem - Qena15 | 1896734.28 | 1602794.48 | 0 | 1602794.48
Akhmem - Qena | Inv.13 Qena- Akhmem$ | 13 | Akhmem - Qena13 | 2370917.85 | 2008736.88 | 0 | 2008736.88
Akhmem Assiut | Inv.8 Assuit Akhmem$ | 8 | Akhmem Assiut8 | 1941363.36 | 1646606.21 | 0 | 1646606.21
South Helwan PP (CP-117) | SH Comm fees inv.29 | 29 | South Helwan PP (CP-117)29 | 9043.58 | 9043.58 | 0 | 9043.58
South Helwan PP (CP-117) | 180131 |  | South Helwan PP (CP-117) | 171275.5 | 152260.72 | 27026.63 | 179287.35
Akhmem - Qena | Inv.39 Akhmem Qena | 39 | Akhmem - Qena39 | 9958390.94 | 6921081.87 | 1493758.64 | 8414840.51
Elsewedy Univ - Enabling Works | els-uni-fin&mep-11 F | 11 | Elsewedy Univ - Enabling Works11 | 17614054.86 | 16620031.47 | 16132569 | 32752600.47
NUCA R05 - Z02 | R5 ZONE 2- IPC05 | 5 | NUCA R05 - Z025 | 33184894.04 | 28985192.51 | 3507610.12 | 32492802.63
South Helwan PP (CP-117) | Commercial fees SH/ |  | South Helwan PP (CP-117) | 41456.9 | 41456.9 | 0 | 41456.9
South Helwan PP (CP-117) | South Helwan insuran |  | South Helwan PP (CP-117) | 0 | -5724.34 | 0 | -5724.34
Ministries Buildings | MIN-OLD-IPC04 | 4 | Ministries Buildings4 | 52589933.5 | 19470465 | 19470471.05 | 41610936.05
Mohamed Ali Palace Restoration | PO - Mohamed Aly 113 |  | Mohamed Ali Palace Restoration | 483236.15 | 342825 | 114279.25 | 457104.25
Ministries Buildings | MIN-LONGLEAD-IPC02 | 2 | Ministries Buildings2 | 33902917.25 | 2019275 | 17497350 | 30529073.16
Kayan 3 New Cairo Capital City | KAYAN FIER-IPC01 | 1 | Kayan 3 New Cairo Capital City1 | 10380000 | 1712930 | 5700000 | 7412930
Middle Tunnel Lock Load | ALAWSATY L&L-1 FINAL | 1 | Middle Tunnel Lock Load1 | 1024820 | 677590 | 225865.1 | 903455.1
Akhmem Assiut | Inv.12 Assuit Akhmem | 12 | Akhmem Assiut12 | 21802696.35 | 17333143.6 | 3270404.45 | 20603548.05
Akhmem Assiut | Ref.Instil No,1 Assu |  | Akhmem Assiut | 50551945.28 | 50551945.28 | 0 | 50551945.28
Marsa Matrouh 500KV | Inv, 1 usd Borg Arab | 1 | Marsa Matrouh 500KV1 | 3897349.44 | 2595001.89 | 409221.69 | 3004223.58
Akhmem Assiut | Inv.17Assuit Akhmem$ | 17 | Akhmem Assiut17 | 1472758.41 | 1238711.97 | 0 | 1238711.97
Akhmem - Qena | Inv.21 Qena- Akhmem$ | 21 | Akhmem - Qena21 | 474183.57 | 398269.57 | 0 | 398269.57
Canal Regional Control Center | Inv.3 Rcc | 3 | Canal Regional Control Center3 | 27085715.32 | 18037871.44 | 5688000.22 | 23725871.66
Al Mostathmreen GIS Substation | MOS-SD-EGP-IPC 33 | 33 | Al Mostathmreen GIS Substation33 | 968907.6 | 721836.16 | 145336.14 | 867172.3
Marsa Matrouh 500KV | Inv11 Usd borg alarb | 11 | Marsa Matrouh 500KV11 | 543102.44 | 473023.621 | 57025.76 | 530049.381
Cairo Capital S1 | Inv. 2 Project S 1 | 2 | Cairo Capital S12 | 18225360.19 | 13714173.65 | 2733804.94 | 16447978.59
Akhmem - Qena | Inv.25 Qena- Akhmem$ | 25 | Akhmem - Qena25 | 189673.43 | 160185.42 | 0 | 160185.42
AWEER POWER STATION 'H' Phase | 10003 |  | AWEER POWER STATION 'H' Phase | 443645.36 | 443645.36 | 0 | 443645.36
Abou El Matameer and Sammanoud | Soc Inv 12 Abo Almat | 12 | Abou El Matameer and Sammanoud12 | 80779.65 | 80779.63 | 0 | 80779.63
Akhmem - Qena | Inv.16 Qena- Akhmem$ | 16 | Akhmem - Qena16 | 1807476.18 | 1533101.07 | 0 | 1533101.07
Akhmem - Qena | Inv.5 Qena - Akhmem$ | 5 | Akhmem - Qena5 | 3135559.87 | 2637502.47 | 0 | 2637502.47
Manshiet Nasser Substation | 180170 |  | Manshiet Nasser Substation | 1290995.17 | 1355544.93 | 0 | 1355544.93
Tamey El-amdeed Substation | TAM-CW-EGP-08 | 8 | Tamey El-amdeed Substation8 | 4576661.83 | 3409613.07 | 686499.27 | 4096112.34
Akhmem Assiut | Inv.31 Assuit Akhmem | 31 | Akhmem Assiut31 | 12474233.2 | 9917015.39 | 1871134.98 | 11788150.37
Akhmem Assiut | ref Instill 3 Assuit |  | Akhmem Assiut | 3232586.7 | 3232586.7 | 0 | 3232586.7
Ismailiya East Substation | (4)cw elasmailya | 4 | Ismailiya East Substation4 | 5057617 | 3798259.66 | 758642.55 | 4556902.21
Marsa Matrouh 500KV | Inv.9 Usd borg alarb | 9 | Marsa Matrouh 500KV9 | 1542129.34 | 1342501.02 | 161923.58 | 1504424.6
Marsa Matrouh 500KV | Inv12 Usd borg alarb | 12 | Marsa Matrouh 500KV12 | 1689419.1 | 1470642.726 | 177389.01 | 1648031.736
AWEER POWER STATION 'H' Phase | CON 034 |  | AWEER POWER STATION 'H' Phase | 2214677.66 | 0 | 246075.3 | 246075.3
AWEER POWER STATION 'H' Phase | CON/031 |  | AWEER POWER STATION 'H' Phase | 1107338.83 | 971997.4166 | 123037.65 | 1095035.0666
AWEER POWER STATION 'H' Phase | LOC/022 |  | AWEER POWER STATION 'H' Phase | 463333.89 | 406704.1897 | 51481.54 | 458185.7297
AWEER POWER STATION 'H' Phase | CON/027 |  | AWEER POWER STATION 'H' Phase | 266187.22 | 233653.22 | 29576.36 | 263229.58
AWEER POWER STATION 'H' Phase | LOC/011 |  | AWEER POWER STATION 'H' Phase | 37500.07 | 37011.6085 | 0 | 37011.6085
AWEER POWER STATION 'H' Phase | 10207 |  | AWEER POWER STATION 'H' Phase | 30045509.98 | 8846733.49 | 20864937.488 | 29711670.978
Marsa Matrouh 500KV | Inv. 2 Borg Alarab | 2 | Marsa Matrouh 500KV2 | 65050776.78 | 56821854.48 | 6830331.56 | 63652186.04
Marsa Matrouh 500KV | Inv. 1 Borg Alarab | 1 | Marsa Matrouh 500KV1 | 128259940.46 | 112028060.46 | 13467293.75 | 125495354.21
EDNC Retail & Offices Civil | Sodic Soreal - IPC24 | 24 | EDNC Retail & Offices Civil24 | 24555503.39 | 18782844.0895 | 2052633.3 | 20835477.3895
EDNC Retail & Offices Civil | SOREAL-IPC21 | 21 | EDNC Retail & Offices Civil21 | 45022478.11 | 32167186.0755 | 2969464.09 | 35136650.1655
EDNC Retail & Offices Civil | SOREA-IPC18 | 18 | EDNC Retail & Offices Civil18 | 39729323.85 | 26361312.3025 | 3416876.44 | 29778188.7425
Siemens 6x500/220 KV GIS-MOU | Inv 92- P14 Assuit | 92 | Siemens 6x500/220 KV GIS-MOU92 | 2399962.85 | 1720133.38 | 359994.43 | 2080127.81
Tunnel of Sokhna Road | SOKHNA TUNNLE-IPC 2 | 2 | Tunnel of Sokhna Road2 | 5115560.44 | 3305891.9 | 0 | 4616391.9
South Helwan PP (CP-117) | SH Inv.37 ded&comm | 37 | South Helwan PP (CP-117)37 | 2104.52 | 2104.52 | 0 | 2104.52
Al Mostathmreen GIS Substation | MOS-SW-EGP- IPC 5 | 5 | Al Mostathmreen GIS Substation5 | 2072122.5 | 1543731.26 | 310818.38 | 1854549.64
South Helwan PP (CP-117) | 180138 |  | South Helwan PP (CP-117) | 318759.39 | 335326.93 | 0 | 335326.93
EMAAR-PKG# 101-UPTOWN | PKG#101 -IPC09 | 9 | EMAAR-PKG# 101-UPTOWN9 | 4704887.4 | 2104893.84 | 1093496.43 | 3198390.27
Asec Spare-Parts | Inv 5 Asec Sparepart | 5 | Asec Spare-Parts5 | 115200 | 0 | 131328 | 131328
DPW Onshore Port & Terminal | DP WORLD-IPC16 | 16 | DPW Onshore Port & Terminal16 | 86484919.88 | 63998840.71 | 12972737.85 | 76971578.56
DPW Onshore Port & Terminal | DP WORLD-IPC08 | 8 | DPW Onshore Port & Terminal8 | 40506959.46 | 29974844.16 | 6076043.92 | 36050888.08
DPW Onshore Port & Terminal | DP WORLD-IPC006 | 6 | DPW Onshore Port & Terminal6 | 17786446.66 | 13161622.85 | 2667967 | 15829589.85
DPW Onshore Port & Terminal | DP WORLD-IPC24 | 24 | DPW Onshore Port & Terminal24 | 28199021.24 | 20867275.72 | 4229853.19 | 25097128.91
DPW Onshore Port & Terminal | DP WORLD-IPC22 | 22 | DPW Onshore Port & Terminal22 | 23946448.25 | 17720371.7 | 3591967.24 | 21312338.94
DPW Onshore Port & Terminal | DP WORLD-IPC17 | 17 | DPW Onshore Port & Terminal17 | 56454657.9 | 41776446.84 | 8468198.69 | 50244645.53
Akhmem - Qena | Inv.46 Qena Akhmem | 46 | Akhmem - Qena46 | 2174961.72 | 1500723.59 | 326244.26 | 1826967.85
HAC CCC JV | IPC#8 | 8 | HAC CCC JV8 | 2823626 | 2589783.17 | 0 | 2589783.17
Elsewedy Univ - Enabling Works | uni-fin&mep-ipc08 | 8 | Elsewedy Univ - Enabling Works8 | 22047683.73 | 12292368.36 | 4990650.83 | 17283019.19
Akhmem Assiut | Inv.44 Assuit Akhmem | 44 | Akhmem Assiut44 | 71871078.86 | 35934921.07 | 10780661.83 | 46715582.9
Kuwait | Other Charge/J002 |  | Kuwait | 160091.58 | 104059.53 | 0 | 104059.53
Zambia Project | SCD3/002 |  | Zambia Project | 61134.56 | 61115.75 | 0 | 61115.75
Ghana | 39/P/10/ER/2017/USD |  | Ghana | 963291.46 | 963291.46 | 0 | 963291.46
Ismailiya East Substation | 19100022 |  | Ismailiya East Substation | 2593944 | 1919518.56 | 389091.6 | 2308610.16
Beni Suef Substation R61 | BSF-SD-EUR-03 | 3 | Beni Suef Substation R613 | 2707740.55 | 2017266.71 | 406161.08 | 2423427.79
Tamey El-amdeed Substation | 19100021 |  | Tamey El-amdeed Substation | 844375 | 624537.5 | 126656.25 | 751193.75
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC14 | 14 | EMAAR- Pkg 140-ITP-Mivida14 | 2429362.37 | 7336701.0985 | 938825.93 | 8275527.0285
EMAAR- Pkg 140-ITP-Mivida | PKG#140 -IPC07 | 7 | EMAAR- Pkg 140-ITP-Mivida7 | 12232780.52 | 10719905.22 | 1371750.71 | 12091655.93
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC04 | 4 | EMAAR- Pkg 140-ITP-Mivida4 | 2442385.78 | 999645.44 | 1260904.72 | 2260550.16
New Capital | Inv 5 El Tbeen | 5 | New Capital5 | 291721.43 | 211574.23 | 30602.89 | 242707.78
Zambia Project | SCD4/0012 |  | Zambia Project | 228771.79 | 228771.79 | 0 | 228771.79
Zambia Project | Inv 8 Zambia | 8 | Zambia Project8 | 450718.84 | 405646.2 | 0 | 405646.2
Zambia Project | SCD1/003 |  | Zambia Project | 1090304.15 | 981254.93 | 0 | 981254.93
Beni Suef Substation R61 | BSF-SW-07 | 7 | Beni Suef Substation R617 | 1126562.5 | 839289.06 | 168984.38 | 1008273.44
Metro 2L Rehabitation Cable | 10 EGP - Metro |  | Metro 2L Rehabitation Cable | 803126.24 | 1591777.48 | 0 | 795888.74
Manshiet Nasser Substation | 515 |  | Manshiet Nasser Substation | 1160236 | 716945.6 | 186738.71 | 903684.31
Manshiet Nasser Substation | 499 |  | Manshiet Nasser Substation | 16207.95 | 3486 | 2431.19 | 5917.19
Manshiet Nasser Substation | 498 |  | Manshiet Nasser Substation | 197970.92 | 168275.28 | 29695.64 | 197970.92
Akhmem Assiut | Inv.27 Assuit Akhmem | 27 | Akhmem Assiut27 | 1273348.85 | 757642.61 | 191002.31 | 948644.92
Akhmem Assiut | Inv.20 Assuit Akhmem | 20 | Akhmem Assiut20 | 4701462.93 | 3737663.02 | 705219.44 | 4442882.46
AbuSultan Rd Bridge2 Extension | ABU SOULTAN2-IPC02FI | 2 | AbuSultan Rd Bridge2 Extension2 | 19900418.1 | 6214797 | 6214800 | 18954747
Manshiet Nasser Substation | 1902210013 |  | Manshiet Nasser Substation | -11569820.5395 | -11569820.5395 | 0 | -11569820.5395
Manshiet Nasser Substation | 1902210010 |  | Manshiet Nasser Substation | 11569820.5395 | 11569820.5395 | 0 | 11569820.5395
Cameron EDC | 008/2019 |  | Cameron EDC | 731475.72 | 730847.21 | 0 | 730847.21
SHAT Al ARAB 400/132kV SS | 218 |  | SHAT Al ARAB 400/132kV SS | 85444.47 | 85444.47 | 0 | 85444.47
Elsewedy Univ - Enabling Works | SEWEDY UNI-FI&MEP-03 | 3 | Elsewedy Univ - Enabling Works3 | 4205490.22 | 5785718.662 | 0 | 5785718.662
Akhmem Assiut | Ref.Ret 2 assuit akh |  | Akhmem Assiut | 308632.14 | 306443 | 0 | 306443
SHATRA 400/132kV SS | 225 |  | SHATRA 400/132kV SS | 281724.77 | 281724.77 | 0 | 281724.77
Akhmem - Qena | Ref.Ret 4 Qena akh |  | Akhmem - Qena | 434907.38 | 431946.99 | 0 | 431946.99
HAC CCC JV | IPC#11 | 11 | HAC CCC JV11 | 785640.6 | 717522.48 | 0 | 717522.48
Development of Mahmudiyah axis | IPC# 1&2 | 1 | Development of Mahmudiyah axis1 | 2070000 | 2012040 | 0 | 2012040
Cameron EDC | 012/2019 |  | Cameron EDC | 284467 | 284200.77 | 0 | 284200.77
Attaqa Power Plant | inv. 3 USD. | 3 | Attaqa Power Plant3 | 117713333 | 117397708.65 | 0 | 117397708.65
Akhmem Assiut | Inv.5 Assuit Akhmem$ | 5 | Akhmem Assiut5 | 1077242.34 | 908182.12 | 0 | 908182.12
Manshiet Nasser Substation | 1902210006 |  | Manshiet Nasser Substation | 1724596.17 | 1617024.49 | 176555.53 | 1793580.02
Hyper El-Temsah | hyper eltemsah-IPC01 | 1 | Hyper El-Temsah1 | 87773321.47 | 5986334.4505 | 51376020.75 | 74009065.2005
Kayan Landscape | KAYAN RAWDA-IPC01 | 1 | Kayan Landscape1 | 41368778 | 15494720 | 15494728.45 | 30989448.45
kayan wall lock & Load | KAYAN LOAK&LOAD-IPC6 | 6 | kayan wall lock & Load6 | 3367800 | 1519519.25 | 1519522.25 | 3039041.5
Manshiet Nasser Substation | 1902210009 |  | Manshiet Nasser Substation | 2765359.42 | 2875973.8 | 0 | 2875973.8
EMAAR-PKG#53-UPTOWN | PKG#53-VO-IPC02 | 2 | EMAAR-PKG#53-UPTOWN2 | 440000 | 451528 | 0 | 451528
Tamey El-amdeed Substation | TAM-CW-EURO-06 | 6 | Tamey El-amdeed Substation6 | 1163547.87 | 861025.42 | 174532.18 | 1035557.6
Ismailiya East Substation | ISE-CW-EGP-11 | 11 | Ismailiya East Substation11 | 3544526 | 2622949.24 | 531678.9 | 3154628.14
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 36 | 36 | Benban 500 K.V/95 K.M36 | -99992664.48 | -101703146.02 | 8110012.09 | -93593133.93
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 35 | 35 | Benban 500 K.V / 100 K.M35 | 23321019.39 | 14102819.07 | 4893750.83 | 18996569.9
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 34 | 34 | Benban 500 K.V / 100 K.M34 | 15524050.7 | 12590008.58 | 1630025.32 | 14220033.9
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 33 | 33 | Benban 500 K.V / 100 K.M33 | 11901237.74 | 9175859.44 | 1249629.96 | 10425489.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 21 | 21 | Benban 500 K.V / 100 K.M21 | 621621.59 | 479269.83 | 65270.27 | 544540.1
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 15 | 15 | Benban 500 K.V / 100 K.M15 | 894191.35 | 689426.25 | 93890.09 | 783316.34
Assuit PP (CP-118) | 1904210003 |  | Assuit PP (CP-118) | 397913.84 | 355138.1 | 62671.43 | 417809.53
Kuwait | Erection/J001 |  | Kuwait | 57389.81 | 37303.38 | 0 | 37303.38
Badr | Inv. 12 Badr | 12 | Badr12 | 9125593 | 6775339.15 | 1368838.95 | 8144178.1
P-28-16 Balat Owinat Lot 3 | Inv. 9 Balat lot 3 | 9 | P-28-16 Balat Owinat Lot 39 | 19007880.37 | 14198491.76 | 1995827.44 | 16194319.2
Canal Sugar S/s | Inv 9 Sugar S/s | 9 | Canal Sugar S/s9 | 9045358.6 | 7145812.42 | 1356803.79 | 8502616.21
Marsa Matrouh 500KV | Inv.28 Borg Alarab | 28 | Marsa Matrouh 500KV28 | 32681632.39 | 28547405.59 | 3431571.4 | 31978976.99
Assuit PP (CP-118) | 1904210005 |  | Assuit PP (CP-118) | 264451.2 | 236022.7 | 41651.06 | 277673.76
Assuit PP (CP-118) | 1905210002 |  | Assuit PP (CP-118) | 350280.73 | 297738.62 | 52542.11 | 350280.73
MAYSAN 400/132kV SS | 233 |  | MAYSAN 400/132kV SS | 17454.6 | 17454.6 | 0 | 17454.6
Elco Steel 220/33 KV SS | 1904210009 |  | Elco Steel 220/33 KV SS | 1532770.52 | 4828227.12 | 0 | 1609409.04
Benban 500 K.V/95 K.M | Benban Lot2 Inv 13 $ | 13 | Benban 500 K.V/95 K.M13 | 206501.3 | 173461.09 | 21682.64 | 195143.73
Benban 500 K.V/95 K.M | Benban Lot2 Inv 10 $ | 10 | Benban 500 K.V/95 K.M10 | 157187.95 | 132037.88 | 16504.74 | 148542.62
Suez Gulf Substation | custom clearance |  | Suez Gulf Substation | 3379.7 | 3379.7 | 0 | 3379.7
Assuit PP (CP-118) | 1905210003 |  | Assuit PP (CP-118) | 792686.09 | 673783.18 | 118902.91 | 792686.09
Manshiet Nasser Substation | 1906210012 |  | Manshiet Nasser Substation | 166472.19 | 177000.08 | 0 | 177000.08
El Boghaz Brigde | IPC#21 | 21 | El Boghaz Brigde21 | 4406158.08 | 4120470.6 | 0 | 4120470.6
Royal City | royal city- ipc20 | 20 | Royal City20 | 8557310.7 | 5072118.405 | 2329228.6 | 7401347.005
P-28-16 Balat Owinat Lot 2 | Inv. 10 Balat Lot 2 | 10 | P-28-16 Balat Owinat Lot 210 | 4458789.24 | 3330319.846 | 468172.874 | 3798492.72
EMAAR-PKG117- MARASSI | PKG#117 - IPC10 | 10 | EMAAR-PKG117- MARASSI10 | 1133422.08 | 855651.034 | 87857.74 | 943508.774
P-28-16 Balat Owinat Lot 2 | Inv. 9 Balat Lot 2 | 9 | P-28-16 Balat Owinat Lot 29 | 4160100.05 | 3107201.55 | 436810.61 | 3544012.16
Elco Steel 220/33 KV SS | 1906210006 |  | Elco Steel 220/33 KV SS | 1135836.53 | 2385256.72 | 0 | 1192628.36
Akhmem Assiut | Inv.49 Assuit Akhmem | 49 | Akhmem Assiut49 | 1803910.73 | 883291.619 | 270586.61 | 1153878.229
Akhmem Assiut | Inv.50 Assuit Akhmem | 50 | Akhmem Assiut50 | 4716318.7 | 3253660 | 707447.81 | 3961107.81
AWEER POWER STATION 'H' Phase | 10138 |  | AWEER POWER STATION 'H' Phase | 193376.33 | 56938.5945 | 134289.11 | 191227.7045
Akhmem - Qena | ٍSoc inv 9 Quana | 9 | Akhmem - Qena9 | 145402 | 145402 | 0 | 145402
Akhmem - Qena | Inv.26 Akhmem Qena | 26 | Akhmem - Qena26 | 1620414 | 964146.33 | 243062.1 | 1207208.43
Akhmem - Qena | Inv.15 Qena - Akhmem | 15 | Akhmem - Qena15 | 8195570.2 | 6515478.31 | 1229335.53 | 7744813.84
Elco Steel 220/33 KV SS | 1908210008 |  | Elco Steel 220/33 KV SS | 2384034.06 | 7509707.28 | 0 | 2503235.76
Elco Steel 220/33 KV SS | 1907210011 |  | Elco Steel 220/33 KV SS | 352785.17 | 370424.43 | 0 | 370424.43
Elco Steel 220/33 KV SS | 1907210010 |  | Elco Steel 220/33 KV SS | 106741.38 | 224156.9 | 0 | 112078.45
Marsa Matrouh 500KV | Inv16 Usd borg alarb | 16 | Marsa Matrouh 500KV16 | 1671146.66 | 1454833.25 | 175470.4 | 1630303.65
Beni Seuf - 358 | Soc inv 4-5 Itay T | 4 | Beni Seuf - 3584 | 4112636 | 4112636 | 0 | 4112636
MAYSAN 400/132kV SS | 249 |  | MAYSAN 400/132kV SS | 69890.56 | 69890.56 | 0 | 69890.56
MOTHANA 400/132kV SS | 217 |  | MOTHANA 400/132kV SS | 793142.51 | 793142.51 | 0 | 793142.51
Latin Compound - New Alamin | inv ( 18 ) 5-12-2020 | 18 | Latin Compound - New Alamin18 | 261822.4 | 168908.89 | 52364.48 | 221273.37
Latin Compound - New Alamin | inv ( 16 ) 2-12-2020 | 16 | Latin Compound - New Alamin16 | 665963.2 | 426391.14 | 133192.64 | 559583.78
LAYYAH CCPP | 516 |  | LAYYAH CCPP | 7402941 | 6292499.85 | 1110441.15 | 7402941
LAYYAH CCPP | 515 |  | LAYYAH CCPP | 3948235 | 3355999.75 | 592235.25 | 3948235
LAYYAH CCPP | 509 |  | LAYYAH CCPP | 1233824 | 1048750.4 | 185073.6 | 1233824
LAYYAH CCPP | 500 |  | LAYYAH CCPP | 571625 | 510175.31 | 85743.75 | 595919.06
LAYYAH CCPP | 495 |  | LAYYAH CCPP | 217625 | 194230.31 | 32643.75 | 226874.06
AWEER POWER STATION 'H' Phase | 10147 |  | AWEER POWER STATION 'H' Phase | 9955116.776 | 2931228.8318 | 6913275.536 | 9844504.3678
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 6 | 6 | Benban 500 K.V/95 K.M6 | 30330357.26 | 23384711.66 | 3184687.51 | 26569399.17
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 6 | 6 | Benban 500 K.V / 100 K.M6 | 196467.63 | 151483.75 | 20629.1 | 172112.85
Marsa Matrouh 500KV | Inv.34 Borg Alarab | 34 | Marsa Matrouh 500KV34 | 3164011.42 | 2763767.08 | 332221.2 | 3095988.28
Beni-Suef Power Plant EPC | Adj.180119-180120 | 180120 | Beni-Suef Power Plant EPC180120 | 514357853.75 | 195226674.9 | 0 | 514357853.75
AWEER POWER STATION 'H' Phase | 10004 |  | AWEER POWER STATION 'H' Phase | 603796 | 633985.8 | 0 | 633985.8
SHAT Al ARAB 400/132kV SS | 264 |  | SHAT Al ARAB 400/132kV SS | 103370.75 | 103370.75 | 0 | 103370.75
MAYSAN 400/132kV SS | 275 |  | MAYSAN 400/132kV SS | 764872.91 | 764872.91 | 0 | 764872.91
Nagaa Hamady/Assuit OHTL | Naga Hmdy Inv.2 Equ | 2 | Nagaa Hamady/Assuit OHTL2 | 1678008.52 | 1125946.77 | 176190.9 | 1302137.67
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.7 | 7 | Nagaa Hamady/Assuit OHTL7 | 86548.57 | 48989.48 | 9087.6 | 58077.08
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 4 | 4 | Nagaa Hamady/Assuit OHTL4 | 3302738.1 | 2381277.81 | 346787.5 | 2728065.31
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 3 | 3 | Nagaa Hamady/Assuit OHTL3 | 28754334.29 | 20731878.03 | 3019206.1 | 23751084.13
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 2 | 2 | Marsa Alam/ Bernes LOT2 OHTL2 | 1897557.22 | 1154933.67 | 203707.31 | 1358640.98
Canal Sugar 33KV OHTL | Inv. 2 Sugar 33 OHTL | 2 | Canal Sugar 33KV OHTL2 | 14000095.18 | 11060075.19 | 2100014.28 | 13160089.47
33KV Canal Farm Grid | Inv. 09 Farm | 9 | 33KV Canal Farm Grid9 | 15435576.01 | 11777344.5 | 2315336.4 | 14092680.9
EMAAR-PKG#53-UPTOWN | (28) PKG#53 | 28 | EMAAR-PKG#53-UPTOWN28 | 13004518.87 | 556642.39 | 8811607.74 | 9368250.13
Ministries Buildings | MINISTRIY OLD-IPC02 | 2 | Ministries Buildings2 | 20749090 | 5695997 | 5303248.3 | 15941317.3
Almaza | Inv. 02 Almaza | 2 | Almaza2 | 3005859.27 | 2862672 | 0 | 2862672
Manshiet Nasser Substation | 1904210017 |  | Manshiet Nasser Substation | 844020 | 844020 | 0 | 844020
HyperOne Zayed Extension | HYPER ONE-IPC04 | 4 | HyperOne Zayed Extension4 | 12451225.71 | 6318712 | 3112806.43 | 11998135.8755
Assuit PP (CP-118) | 1908210001 |  | Assuit PP (CP-118) | 155640.55 | 138909.19 | 24513.39 | 163422.58
Tamey El-amdeed Substation | TAM-CW-EURO-09 | 9 | Tamey El-amdeed Substation9 | 709911.17 | 453949.5 | 106486.68 | 560436.18
Ministries Buildings | MIN.FIT OUT- PC01 |  | Ministries Buildings | 8504450 | 4352874 | 2556654.4 | 6909528.4
Ismalia Bridge | Ismailia U4-ipc 2 | 2 | Ismalia Bridge2 | 5416102.82 | 5491516.5 | 9690 | 5501206.5
Ministries Buildings | MIN-CORE- IPC02 | 2 | Ministries Buildings2 | 14861602.7 | 4426417 | 8985770 | 13412187
Manshiet Nasser Substation | 1908210018 |  | Manshiet Nasser Substation | 1647733.85 | 1695847.04 | 0 | 1695847.04
Asec Spare-Parts | Inv 2 EUR Asec Spare | 2 | Asec Spare-Parts2 | 39684.48 | 0 | 33644.11 | 33644.11
Ghana Street lighting | MIDA Sply. Inv. 4 | 4 | Ghana Street lighting4 | 193188.28 | 193188.28 | 0 | 193188.28
Ghana Street lighting | inv 5 Sup | 5 | Ghana Street lighting5 | 204923.64 | 204923.64 | 0 | 204923.64
AWEER POWER STATION 'H' Phase | 10308 |  | AWEER POWER STATION 'H' Phase | 750671.33 | 221030.99 | 521299.5356 | 742330.5256
Kayan 3 New Cairo Capital City | KAYAN FINSH-IPC07 | 7 | Kayan 3 New Cairo Capital City7 | 30167296.25 | 9223514 | 18002052 | 27225566
Nuweibaa (Swro) | Invoice No:12 |  | Nuweibaa (Swro) | 308452.2 | 246761.76 | 61690.44 | 308452.2
Nuweibaa (Swro) | 2010210005 |  | Nuweibaa (Swro) | 489160.25 | 391328.2 | 97832.05 | 489160.25
Oasis Buildings- New Capital | inv ( 9 ) | 9 | Oasis Buildings- New Capital9 | 1607046.56 | 1338245.83 | 0 | 1338245.83
Oasis Buildings- New Capital | inv ( 13 ) final | 13 | Oasis Buildings- New Capital13 | 1082880 | 805095.09 | 0 | 805095.09
Oasis Buildings- New Capital | Inv(4)240220 | 4 | Oasis Buildings- New Capital4 | 103400 | 98374.2 | 0 | 98374.2
El Katameya Mall | inv(7)150320 | 7 | El Katameya Mall7 | 135800 | 114954.7 | 0 | 114954.7
Beni Suef Add-on Sales | 513 |  | Beni Suef Add-on Sales | 7500.2 | 8475.228 | 0 | 8475.228
ORA Zed Park LOCK&LOAD | ORA-IPC01 | 1 | ORA Zed Park LOCK&LOAD1 | 573141.24 | 505797.142 | 0 | 505797.142
AWEER POWER STATION 'H' Phase | 10249 |  | AWEER POWER STATION 'H' Phase | 4152520.61 | 3644990.31 | 461391.18 | 4106381.49
4 SS - Technical Service | 295 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHAT Al ARAB 400/132kV SS | 266 |  | SHAT Al ARAB 400/132kV SS | 1096738.5 | 1096738.5 | 0 | 1096738.5
Marsa Matrouh 500KV | Inv.40 Borg Alarab | 40 | Marsa Matrouh 500KV40 | 5469207.46 | 4777357.59 | 574266.78 | 5351624.37
Marsa Matrouh 500KV | Inv.41 Borg Alarab | 41 | Marsa Matrouh 500KV41 | 10215165.34 | 7314062.88 | 1072592.36 | 8386655.24
Marsa Matrouh 500KV | Inv.43 Borg Alarab | 43 | Marsa Matrouh 500KV43 | 23264035.62 | 16657052.82 | 2442723.74 | 19099776.56
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 20 | 20 | Benban 500 K.V / 100 K.M20 | 1542525.84 | 1188693.31 | 161965.21 | 1350658.52
EDNC Retail & Offices Civil | SOREAL-IPC07 | 7 | EDNC Retail & Offices Civil7 | 46252048.05 | 38197130.9705 | 11112412.04 | 49309543.0105
Sodic Club House | VO-SODIC CULB-IPC01 | 1 | Sodic Club House1 | 463906.48 | 13881.354 | 0 | 13881.354
Ministries Buildings | MIN SHELL-IPC04 | 4 | Ministries Buildings4 | 34298619.7 | 21929379.985 | 7309793.955 | 29239173.94
Fish Market | SOUQ ELSAMEK ELCTROF |  | Fish Market | 4026352.38 | 2008212.379 | 1715149 | 3723361.379
Ministries Buildings | MIN.SHELL-IPC05 | 5 | Ministries Buildings5 | 22857093.65 | 14328225 | 5157030.6 | 19485255.6
Elco Steel 220/33 KV SS | 522 |  | Elco Steel 220/33 KV SS | 173928.97 | 365250.84 | 0 | 182625.42
Assuit PP (CP-118) | 512 |  | Assuit PP (CP-118) | 1818894.09 | 1623362.97 | 286475.82 | 1909838.79
Elco Steel 220/33 KV SS | 1903210007 |  | Elco Steel 220/33 KV SS | 2652793.71 | 2785433.4 | 0 | 2785433.4
Elco Steel 220/33 KV SS | 521 |  | Elco Steel 220/33 KV SS | 24234.26 | 25445.97 | 0 | 25445.97
Elco Steel 220/33 KV SS | 1904210010 |  | Elco Steel 220/33 KV SS | 657082 | 689936.1 | 0 | 689936.1
Akhmem Assiut | Inv.23Assuit Akhmem$ | 23 | Akhmem Assiut23 | 762952.66 | 615405.36 | 0 | 615405.36
Toshka GIS 500 kV | Toshka Sub Inv. 08 | 8 | Toshka GIS 500 kV8 | 57678393.93 | 32847455.1 | 15140578.41 | 47988033.51
Toshka GIS 500 kV | Toshka Sub Inv. 07 | 7 | Toshka GIS 500 kV7 | 89330611.48 | 56095136.22 | 23449285.51 | 79544421.73
Toshka GIS 500 kV | Toshka Sub Inv. 04 | 4 | Toshka GIS 500 kV4 | 9162410.86 | 4502990.71 | 2405132.85 | 6908123.56
Safir bridge | FPC |  | Safir bridge | 642300 | 0 | 0 | 635877
Al Mostathmreen GIS Substation | MOS-VO-CLAIM |  | Al Mostathmreen GIS Substation | 2000000 | 2000000 | 0 | 2000000
Marsa Matrouh 500KV | Inv.20Usd borg alarb | 20 | Marsa Matrouh 500KV20 | 497761.9 | 432327.8 | 52265 | 484592.8
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .18 | 18 | Benban 3/ Toshka 2 LOT 418 | 17240856.77 | 13568145.27 | 1810289.96 | 15378435.23
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .4 | 4 | Benban 3/ Toshka 2 LOT 44 | 3108120.7 | 2396365.15 | 326352.67 | 2722717.82
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .7 | 7 | Benban 3/ Toshka 2 LOT 47 | 16280991.51 | 10843143.2 | 1709504.11 | 12552647.31
Benban 3/ Toshka 2 LOT 4 | Ref-Ret-Toshka Lot4$ |  | Benban 3/ Toshka 2 LOT 4 | 821146.29 | 787059.18 | 34087.11 | 821146.29
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $1 | 1 | Benban 3/ Toshka 2 LOT 41 | 193691.41 | 162700.78 | 20337.6 | 183038.38
CFC Podium 2 | CFC IPC023 | 23 | CFC Podium 223 | 19569971.41 | 15440458.9205 | 1462273.54 | 16902732.4605
Assuit PP (CP-118) | 541 |  | Assuit PP (CP-118) | 2960039.95 | 2612235.26 | 466206.29 | 3078441.55
Royal City | ROYAL CITY-IPC(7) | 7 | Royal City7 | 11315586.82 | 8703262.891 | 1686321.23 | 10389584.121
Royal City | ROYAL CITY-IPC25 | 25 | Royal City25 | 17584623.17 | 9972683.9685 | 5048068.09 | 15020752.0585
Ismailiya East Substation | ISE-CW-EGP-21 | 21 | Ismailiya East Substation21 | 1368194 | 1012463.56 | 205229.1 | 1217692.66
SHATRA 400/132kV SS | 299 |  | SHATRA 400/132kV SS | 762454.65 | 762454.65 | 0 | 762454.65
Ismailiya East Substation | ISE-SD-EURO-03 | 3 | Ismailiya East Substation3 | 2044384.61 | 1664874.01 | 164850.22 | 1829724.23
Manshiet Nasser Substation | 535 |  | Manshiet Nasser Substation | 702446.4 | 256448.7 | 0 | 256448.7
DPW Onshore Port & Terminal | DP WORLD-IPC11 | 11 | DPW Onshore Port & Terminal11 | 102020049.91 | 75494532.33 | 15303007.49 | 90797539.82
Akhmem - Qena | Inv.49 Qena Akhmem | 49 | Akhmem - Qena49 | 68054750.3 | 48967466.83 | 8197931.14 | 57165397.97
AWEER POWER STATION 'H' Phase | 10388 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
Canal Sugar OHTL | Inv.06 Sugar OHTL | 6 | Canal Sugar OHTL6 | 7441226.84 | 5878569.2 | 1116184.03 | 6994753.23
Lekela 250MW Wind Farm | LEKELA IPC014 | 14 | Lekela 250MW Wind Farm14 | 18187988.27 | 12931636.6285 | 6018471.255 | 18950107.8835
Lekela 250MW Wind Farm | LEKELA-IPC09 | 9 | Lekela 250MW Wind Farm9 | 21219483.49 | 18594958.1945 | 3509999.5 | 22104957.6945
Lekela 250MW Wind Farm | LEKELA-IPC07 | 7 | Lekela 250MW Wind Farm7 | 17619865.65 | 15073158.3375 | 3264476.755 | 18337635.0925
Toshka GIS 500 kV | Toshka Sub Inv. 20 $ | 20 | Toshka GIS 500 kV20 | 8473.33 | 4533.35 | 2224.25 | 6757.6
Toshka GIS 500 kV | Toshka Sub Inv. 14 $ | 14 | Toshka GIS 500 kV14 | 14498.29 | 7962.76 | 3805.8 | 11768.56
Toshka GIS 500 kV | Toshka Sub Inv. 13 $ | 13 | Toshka GIS 500 kV13 | 14498.29 | 7962.76 | 3805.8 | 11768.56
EMAAR-Pkg#162/163- Marassi | PKG#162 - IPC03 | 3 | EMAAR-Pkg#162/163- Marassi3 | 6446622.34 | 5119599.327 | 655105.77 | 5774705.097
Beni Suef Add-on Sales | 2002210024 |  | Beni Suef Add-on Sales | 45000 | 50850 | 0 | 50850
IKEA Extension MoA | IKEA-IPC04 | 4 | IKEA Extension MoA4 | 12574283.57 | 8514192.76 | 1013594.38 | 9527787.14
SHAT Al ARAB 400/132kV SS | 303 |  | SHAT Al ARAB 400/132kV SS | 2354642.18 | 2354642.18 | 0 | 2354642.18
AWEER POWER STATION 'H' Phase | IMP-031 | 31 | AWEER POWER STATION 'H' Phase31 | 627024.39 | 572087.95 | 0 | 572087.95
Dubai Port | 10014 |  | Dubai Port | 41428.63 | 36747.19 | 0 | 36747.19
Ministry Building EPOXY | 10016 |  | Ministry Building EPOXY | 76145.16 | 71576.45 | 0 | 71576.45
Ministry Building EPOXY | 10015 |  | Ministry Building EPOXY | 34960 | 32862.4 | 0 | 32862.4
Al-Kayan | 10021 |  | Al-Kayan | 27716 | 26053.04 | 0 | 26053.04
Multi Sport Hall | 10041 |  | Multi Sport Hall | 401155 | 356932.95 | 0 | 356932.95
Ministries Building ROOF | 10003 |  | Ministries Building ROOF | 138261.5 | 129965.8 | 0 | 129965.8
EMAAR-Pkg#162/163- Marassi | pkg#163 ipc 21 | 21 | EMAAR-Pkg#162/163- Marassi21 | 5908870.81 | 5666249.3105 | 742095.54 | 6408344.8505
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 1 | 1 | Marsa Alam/ Bernes LOT2 OHTL1 | 24729788.77 | 13790114.92 | 2679730.5 | 16469845.42
4 SS - Technical Service | 306 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
MOTHANA 400/132kV SS | 315 |  | MOTHANA 400/132kV SS | 38529.77 | 38529.77 | 0 | 38529.77
MOTHANA 400/132kV SS | 319 |  | MOTHANA 400/132kV SS | 46429.57 | 46429.57 | 0 | 46429.57
Marsa Matrouh 500KV | Inv.69 Borg Alarab | 69 | Marsa Matrouh 500KV69 | 8195904.76 | 6728839.95 | 0 | 6728839.95
Manshiet Nasser Substation | 531 |  | Manshiet Nasser Substation | 232430.43 | 174664.95 | 37409.42 | 212074.37
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC10 | 10 | EMAAR- Pkg 140-ITP-Mivida10 | 6612227.79 | 5679423.0695 | 726755.74 | 6406178.8095
Miscellaneous Projects | 2004210008 |  | Miscellaneous Projects | 29110.15 | 29413.9 | 0 | 29527.82
Marsa Matrouh 500KV | Inv.73 Borg Alarab | 73 | Marsa Matrouh 500KV73 | 1026992.63 | 1004915.2 | 0 | 1004915.2
IKEA Extension MoA | IKEA - IPC 05 | 5 | IKEA Extension MoA5 | 9421690.84 | 7739970.29 | 952538.84 | 8692509.13
South Helwan PP (CP-117) | 2004210004 |  | South Helwan PP (CP-117) | 35208.17 | 31116.42 | 5555.72 | 36672.14
Ext.110 S. Military 220 Kv S/S | Cr. Adv MILITARY Ext |  | Ext.110 S. Military 220 Kv S/S | 0 | 0 | -849955 | -849955
Abu Qir PP (CP-117) | 200000 |  | Abu Qir PP (CP-117) | 595980 | 2020372.2 | 0 | 673457.4
Cairo Capital Cables Tunnel | Tunnel Inv. 2 | 2 | Cairo Capital Cables Tunnel2 | 34582914.95 | 23271071.9 | 8645728.74 | 31916800.64
LAYAN Substation | 11744 |  | LAYAN Substation | 157084.49 | 265472.789 | 0 | 132736.3945
LAYAN Substation | 10462 |  | LAYAN Substation | 4777349.72 | 3965200.26 | 0 | 3965200.26
LAYAN Substation | 10223 |  | LAYAN Substation | 394584.492 | 327505.01 | 0 | 327505.01
ESU Ph2-Enabling & Struc | E.S.U-PH2-IPC02 | 2 | ESU Ph2-Enabling & Struc2 | 19788850.1 | 13318143.9085 | 6233487.78 | 19551631.6885
Mivida | IPC_4_Mivida |  | Mivida | 171950 | 170230.5 | 0 | 170230.5
Banha PP (CP-117) | Adjust receivable |  | Banha PP (CP-117) | 6111.71 | 6111.71 | 0 | 6111.71
Ain-Sokhna PP (CP-117) | adjust rec.180137 |  | Ain-Sokhna PP (CP-117) | 5000.88 | 5000.88 | 0 | 5000.88
MAYSAN 400/132kV SS | 350 |  | MAYSAN 400/132kV SS | 1949503.47 | 1949503.47 | 0 | 1949503.47
MOTHANA 400/132kV SS | 339 |  | MOTHANA 400/132kV SS | 803170.22 | 803170.22 | 0 | 803170.22
Miscellaneous Projects | 2006210008 |  | Miscellaneous Projects | -8384.62 | -9558.4668 | 0 | -9558.4668
DoubleTree Mangroovy ElGouna | mangrove rent-ipc04 | 4 | DoubleTree Mangroovy ElGouna4 | 16112.5 | 16757 | 0 | 16757
Al-Shabab PP Phase II (CP-117) | 2002210020 |  | Al-Shabab PP Phase II (CP-117) | 2104756.26 | 1532686.78 | 681464.3 | 2214151.08
Latin Compound - New Alamin | INV(10)300420 | 10 | Latin Compound - New Alamin10 | 168280 | 139591.24 | 0 | 139591.24
El Katameya Mall | inv(10 )29720 | 10 | El Katameya Mall10 | 183120 | 153277.71 | 0 | 153277.71
Giza North PP Ph I,II (CP-117) | 2001210014 |  | Giza North PP Ph I,II (CP-117) | 216000 | 216000 | 0 | 216000
W Dam PP Phase II (CP-117) | 2002210028 |  | W Dam PP Phase II (CP-117) | 10030.51 | 10447.58 | 0 | 10447.58
W Dam PP Phase II (CP-117) | 2002210026 |  | W Dam PP Phase II (CP-117) | 199624.51 | 207924.9 | 0 | 207924.9
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .1 | 1 | Benban 3/ Toshka 2 LOT 41 | 285228.43 | 214916.17 | 29948.99 | 244865.16
Samaya Electronics factory | INV(1)Fainal12-2020 | 1 | Samaya Electronics factory1 | 880000 | 880000 | 0 | 880000
MOTHANA 400/132kV SS | 345 |  | MOTHANA 400/132kV SS | 6054750.89 | 6054750.89 | 0 | 6054750.89
Benban 500 K.V / 100 K.M | Benban Lot1 Inv14USD | 14 | Benban 500 K.V / 100 K.M14 | 2939950.85 | 2461143.4 | 308694.84 | 2769838.24
Kayan Landscape | KAYAN ROUDA-IPC02 | 2 | Kayan Landscape2 | 12633326.95 | 95 | 11571630 | 11571725
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 09 | 9 | Suez Gulf/S4 - 500KV OHTL9 | 1277396.49 | 901707.68 | 134126.63 | 1035834.31
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 05 | 5 | Suez Gulf/S4 - 500KV OHTL5 | 1866661.38 | 1420520.26 | 195999.45 | 1616519.71
East Owainat 5 LOTS | East Owainat Inv. 04 | 4 | East Owainat 5 LOTS4 | 88684448.28 | 36183246.89 | 46559335.35 | 82742582.24
Royal City | ROYAL CITY- IPC32 | 32 | Royal City32 | 4150837.54 | 2151533.367 | 1027610.78 | 3179144.147
Minis Building(Polyurethane) | 10216 |  | Minis Building(Polyurethane) | 414221.73 | 368533.59 | 0 | 368533.59
AWEER POWER STATION 'H' Phase | Eng-28 | 28 | AWEER POWER STATION 'H' Phase28 | 293486.56 | 308160.888 | 0 | 308160.888
Bahr El Baqar Treatment Plant | IPC#1 | 1 | Bahr El Baqar Treatment Plant1 | 1212810.3 | 1088370 | 0 | 1088370
Sodic East | 10233 |  | Sodic East | 1030744.99 | 534792.31 | 0 | 534792.31
Nuweibaa (Swro) | 2004210007 |  | Nuweibaa (Swro) | 491518.2 | 393214.56 | 98303.64 | 491518.2
DoubleTree Mangroovy ElGouna | MANGROOVE-IPC07 | 7 | DoubleTree Mangroovy ElGouna7 | 3133496.53 | 2166123.4165 | 822542.84 | 2988666.2565
Marsa Matrouh 500KV | Inv.46 Borg Alarab | 46 | Marsa Matrouh 500KV46 | 10217560.62 | 8925038.24 | 1072843.87 | 9997882.11
Ministries A17-A18 | 10214 |  | Ministries A17-A18 | 687998.3 | 581270.76 | 0 | 581270.76
El Banna project | 444 |  | El Banna project | 591.819 | 0 | 591.819 | 591.819
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .10 | 10 | Benban 3/ Toshka 2 LOT 410 | 3039893.5 | 2495754.6 | 319188.82 | 2814943.42
Ghana | 40A/P/10/ER/2017/USD |  | Ghana | 317437.42 | 317437.42 | 0 | 317437.42
Racecores 3092-16 132KV C | 11367 |  | Racecores 3092-16 132KV C | 288932.7876 | 976592.84 | 0 | 244148.21
Racecores 3092-16 132KV C | 11293 |  | Racecores 3092-16 132KV C | 808180.13 | 4024737.06 | 0 | 670789.51
Racecores 3092-16 132KV C | 11024 |  | Racecores 3092-16 132KV C | 3197203.6 | 2653678.99 | 0 | 2653678.99
Racecores 3092-16 132KV C | 11023 |  | Racecores 3092-16 132KV C | 339157.1 | 1407501.95 | 0 | 281500.39
Sodic East | IPC_13_rowad_s_east |  | Sodic East | 558167.95 | 459462.47 | 0 | 459462.47
Minis Building(Polyurethane) | IPC_13_Rowad_poly |  | Minis Building(Polyurethane) | 246382.79 | 219280.68 | 0 | 219280.68
Badr | Inv. 22 Badr | 22 | Badr22 | 10694183 | 7940011.5 | 1604127.45 | 9544138.95
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $5 | 5 | Benban 3/ Toshka 2 LOT 45 | 2063994.43 | 1733755.31 | 216719.42 | 1950474.73
NUCA R05 - Z02 | R05(2) ipc 36 | 36 | NUCA R05 - Z0236 | 22042535.4 | 18265544.716 | 2344204 | 20609748.716
LRT - El Shorouk Bridge | IPC#3 | 3 | LRT - El Shorouk Bridge3 | 324540 | 290950.11 | 0 | 290950.11
Rail Way Tunnel Zagazig | IPC#3 | 3 | Rail Way Tunnel Zagazig3 | 755500 | 704126 | 0 | 704126
Latin Compound - New Alamin | INV(11)100520 | 11 | Latin Compound - New Alamin11 | 116760 | 95592.65 | 0 | 95592.65
El Katameya Mall | inv(4)260120 | 4 | El Katameya Mall4 | 861126 | 689960 | 0 | 689960
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .6 | 6 | Benban 3/ Toshka 2 LOT 46 | 32160469.9 | 21418880.19 | 3376849.34 | 24795729.53
ESU Ph2-Enabling & Struc | E.S.U2-MEP-IPC08 | 8 | ESU Ph2-Enabling & Struc8 | 69627433.52 | 25127325.53 | 0 | 25127325.53
Beni Seuf - 358 | Inv.2 Temmay Amded | 2 | Beni Seuf - 3582 | 21463160.11 | 15663959.2 | 3671792.45 | 19335751.65
CFC Podium 2 | CFC-IPC10 | 10 | CFC Podium 210 | 52098964.43 | 39448595.5715 | 7527197.56 | 46975793.1315
OHTL Mostakable East Boundary | Inv. 03 Future OHTL | 3 | OHTL Mostakable East Boundary3 | 11586090.14 | 9616454.81 | 2433078.93 | 12049533.74
Taval Sarai 52 | IPC_9_Saray |  | Taval Sarai 52 | 446889.6 | 325460.13 | 0 | 325460.13
Ministries A17-A18 | IPC_6_gama_ministry |  | Ministries A17-A18 | 210000 | 178395 | 0 | 178395
SHATRA 400/132kV SS | 371 |  | SHATRA 400/132kV SS | 1112566.76 | 1112566.76 | 0 | 1112566.76
Oasis Buildings- New Capital | inv ( 11 ) 11-11-20 | 11 | Oasis Buildings- New Capital11 | 2857656.4 | 2739063.67 | 0 | 2739063.67
4 SS - Technical Service | 381 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Abas El Akkad Bridge | FPC |  | Abas El Akkad Bridge | 370000 | 109010 | 0 | 109010
AWEER POWER STATION 'H' Phase | IMP051-50 | 50 | AWEER POWER STATION 'H' Phase50 | 1053708.68 | 1042000.81 | 0 | 1042000.81
Cairo-Alex Railway | Cairo-alex ipc 39 | 39 | Cairo-Alex Railway39 | 20355575.24 | 14136532.37 | 2137335.4 | 16273867.77
Cairo-Alex Railway | Cairo-Alex ipc 31 | 31 | Cairo-Alex Railway31 | 13108737.6 | 9103619.27 | 1376417.45 | 10480036.72
Cairo-Alex Railway | CAIRO-ALEX IPC20 | 20 | Cairo-Alex Railway20 | 31478677.3 | 21861542.435 | 3305261.12 | 25166803.555
Racecores 3092-17 132KV E | 11540 |  | Racecores 3092-17 132KV E | 131913.7695 | 111467.138 | 0 | 111467.138
Racecores 3092-17 132KV E | 11450 |  | Racecores 3092-17 132KV E | 331266.34 | 549901.11 | 0 | 274950.555
Racecores 3092-17 132KV E | 11289 |  | Racecores 3092-17 132KV E | 210133.33 | 174410.66 | 0 | 174410.66
Oasis Buildings- New Capital | inv ( 10 ) 20-10-20 | 10 | Oasis Buildings- New Capital10 | 2553158.44 | 2310191.58 | 0 | 2310191.58
EMAAR-Pkg#162/163- Marassi | PKG#163 - IPC04 | 4 | EMAAR-Pkg#162/163- Marassi4 | 3898862.65 | 4503200.4825 | 1110090.52 | 5613291.0025
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 31 | 31 | ORA ZED - Ph 01B - Pkgs A&D31 | 21322773.91 | 10153641.2135 | 11425404.25 | 21579045.4635
ORA ZED - Ph 01B - Pkgs A&D | ORA ph1 ipc (29) | 29 | ORA ZED - Ph 01B - Pkgs A&D29 | 23928989.08 | 10687601.99 | 11496925.55 | 22184527.54
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC12 | 12 | ORA ZED - Ph 01B - Pkgs A&D12 | 33050531.68 | 26088449.724 | 3104008.18 | 29192457.904
NUCA R05 - Z02 | R5 FINSHING-IPC05** | 5 | NUCA R05 - Z025 | 14524996.2 | 22412957.55 | 3513309.85 | 12963133.7
Toshka GIS 500 kV | Toshka Sub Inv. 04 $ | 4 | Toshka GIS 500 kV4 | 4243622.98 | 2863582.78 | 1113951.03 | 3977533.81
Toshka GIS 500 kV | Toshka Sub Inv. 08 $ | 8 | Toshka GIS 500 kV8 | 86989.71 | 49566.56 | 22834.8 | 72401.36
Miscellaneous Projects | 2009210011 |  | Miscellaneous Projects | 118487.2 | 135075.41 | 0 | 135075.41
Miscellaneous Projects | 2007210011 |  | Miscellaneous Projects | 151344.64 | 172532.8896 | 0 | 172532.8896
Miscellaneous Projects | 2007210010 |  | Miscellaneous Projects | 118487.2 | 135075.408 | 0 | 135075.408
Ministries Buildings | MIN.ANASER WATER-03 | 3 | Ministries Buildings3 | 1513476 | 956020 | 318676 | 1274696
Sodic East | IPC_17_Rowad_S_east |  | Sodic East | 341704.4 | 240579.246 | 0 | 240579.246
Manshiet Nasser Substation | 2008210009 |  | Manshiet Nasser Substation | 17607.02 | 3397.85 | 2780.06 | 6177.91
Toshka GIS 500 kV | Toshka Sub Inv. 02 | 2 | Toshka GIS 500 kV2 | 11781697.61 | 6599339.66 | 3092695.62 | 9692035.28
Royal City | ROYAL CITY-IPC33 | 33 | Royal City33 | 11787102.13 | 8559155.6765 | 4188755.42 | 12747911.0965
Miscellaneous Projects | 2007210004 |  | Miscellaneous Projects | 10895.41 | 12093.91 | 0 | 12093.91
Koning Food V2 - LP-08-20 | 5 |  | Koning Food V2 - LP-08-20 | 67587.71 | 77049.99 | 0 | 77049.99
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC18 | 18 | EMAAR- Pkg 140-ITP-Mivida18 | 4603925.77 | 3831058.9285 | 490233.61 | 4321292.5385
Toshka GIS 500 kV | Toshka Sub Inv. 18 $ | 18 | Toshka GIS 500 kV18 | 22453.52 | 12581.91 | 5894.05 | 18475.96
Port Saad Industiral zone | IPC-7 | 7 | Port Saad Industiral zone7 | 740658 | 713253.65 | 0 | 713253.65
El Katameya Mall | inv ( 15 ) 12-2020 | 15 | El Katameya Mall15 | 546000 | 447055.25 | 0 | 447055.25
4 SS - Technical Service | 388 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Mohamed Aly Fahmy Lock&Load | M.A.FAHMYL&L-FINAL |  | Mohamed Aly Fahmy Lock&Load | 332310 | 458890 | 152975 | 611865
AWEER POWER STATION 'H' Phase | IMP-059 | 59 | AWEER POWER STATION 'H' Phase59 | 1082826.83 | 1136968.1715 | 0 | 1136968.1715
El-Nyaba El-Ama | El-Nayba Inv. 2 | 2 | El-Nyaba El-Ama2 | 1719317.55 | 1405134.12 | 128948.85 | 1534082.97
R5 | inv ( 15 )25-12-2020 | 15 | R515 | 894000 | 413577.86 | 0 | 824289.25
Mohamed Ali Palace | IPC_3_Rowad_M.Ali |  | Mohamed Ali Palace | 22480.2 | 16149.368 | 0 | 16149.368
El Mostaqbal lock & load | MOSTQBALL&L-IPC02F | 2 | El Mostaqbal lock & load2 | 410006 | 182760 | 182767 | 365527
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $4 | 4 | Benban 3/ Toshka 2 LOT 44 | 1018343.2 | 855408.28 | 106926.04 | 962334.32
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $6 | 6 | Benban 3/ Toshka 2 LOT 46 | 207833.62 | 174580.24 | 21822.53 | 196402.77
marassi inland marina | IPC#9 | 9 | marassi inland marina9 | 546388.78 | 32867.96 | 0 | 306823.06
Huawei Technologies LP-11-20 | 11 |  | Huawei Technologies LP-11-20 | 220000 | 248600 | 0 | 248600
Kattameya Creeks | KATAMYA CREEKS IPC14 | 14 | Kattameya Creeks14 | 48574512.67 | 45904629.9935 | 4560213.18 | 50464843.1735
Kattameya Creeks | Kattameya IPC04 | 4 | Kattameya Creeks4 | 31881858.16 | 29687637.308 | 3469495.18 | 33157132.488
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.10 | 10 | Toshka 2/Owinat East LOT2 OHTL10 | 16006857.57 | 0 | 1680720.05 | 1680720.05
Canal Sugar OHTL | Inv.03 $ Sugar OHTL | 3 | Canal Sugar OHTL3 | 340101 | 284629.38 | 35065.56 | 319694.94
Royal City | ROYAL CITY-IPC36 | 36 | Royal City36 | 8120768.31 | 5231425.2055 | 0 | 5231425.2055
Museum of Egyp. Civilization | IPC#3 PhaseII | 3 | Museum of Egyp. Civilization3 | 496630 | 438036.45 | 0 | 438036.45
Daraw Bridge | IPC#2 | 2 | Daraw Bridge2 | 2478560 | 2029775.96 | 0 | 2029775.96
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC16 | 16 | EMAAR- Pkg 140-ITP-Mivida16 | 19380294.6 | 13266917.76 | 1350448.21 | 14617365.97
Ahl Misr Walkway | IPC#1 Ahl Misr | 1 | Ahl Misr Walkway1 | 1546834.5 | 1490375.03 | 0 | 1490375.03
CFC Podium 2 | CFC-IPC14 | 14 | CFC Podium 214 | 29172801.68 | 19708944.274 | 3762123.59 | 23471067.864
Miscellaneous Projects | 2011210007 |  | Miscellaneous Projects | 34725 | 39239.25 | 0 | 39239.25
Taval Sarai 52 | Adj.06-2022 | 2022 | Taval Sarai 522022 | 83165.78 | 63165.784 | 0 | 63165.784
Koning Food V2 - LP-08-20 | 9 |  | Koning Food V2 - LP-08-20 | 2114.38 | 2410.4 | 0 | 2410.4
BKG#178-Lagoon Discharge | PKG #178 IPC05 | 5 | BKG#178-Lagoon Discharge5 | 10300781.79 | 9666283.6995 | 408395.93 | 10074679.6295
Ghana Street lighting | 5MIDA Sply. Inv. |  | Ghana Street lighting | 280444.21 | 252399.78 | 0 | 252399.78
Cairo Capital S1 | Inv.9Project S1Fina | 9 | Cairo Capital S19 | 143454958.65 | 112402834.94 | 21518234.87 | 133921069.81
Canal Sugar S/s | Inv 5 $ Sugar S/s | 5 | Canal Sugar S/s5 | 97902.6 | 74699.68 | 14685.39 | 89385.07
DoubleTree Mangroovy ElGouna | MANGROVE WALL-IPC03 | 3 | DoubleTree Mangroovy ElGouna3 | 189255 | 165325.2 | 0 | 165325.2
Latin Compound - New Alamin | inv ( 21 ) 11-12-20 | 21 | Latin Compound - New Alamin21 | 383227.6 | 248906.33 | 76645.52 | 325551.85
Toshka-04 GIS Substation | Toshka Sub 4 Inv.3 $ | 3 | Toshka-04 GIS Substation3 | 432429.07 | 0 | 45405.05 | 45405.05
EGAT Pelletizing Plant | EGAT IPC07+ | 7 | EGAT Pelletizing Plant7 | 1175831.28 | 1088853.474 | 116611.05 | 1205464.524
Mohamed Ali Palace | IPC_4_Rowad_M.Ali |  | Mohamed Ali Palace | 80818.6 | 67887.62 | 0 | 67887.62
Ismailiya East Substation | ISE-SW-EGP-09 | 9 | Ismailiya East Substation9 | 356563 | 317341.07 | 0 | 317341.07
Beni Suef Substation R61 | BSF-SD-EURO-03 | 3 | Beni Suef Substation R613 | 7944201.1 | 4793506.78 | 0 | 4793506.78
IKEA Extension MoA | IKEA - IPC06 | 6 | IKEA Extension MoA6 | 5112809.05 | 4141935.79 | 628358.81 | 4770294.6
SHAT Al ARAB 400/132kV SS | 395 |  | SHAT Al ARAB 400/132kV SS | 1369521.06 | 1369521.06 | 0 | 1369521.06
Sodic East | IPC_22_Rowad_Seast |  | Sodic East | 228288.29 | 202149.28 | 0 | 202149.28
Tanzania hydropower Project | 2 |  | Tanzania hydropower Project | 152041.56 | 152041.56 | 0 | 152041.56
Hadaek ElAharam | FPC |  | Hadaek ElAharam | 900592.5 | 599713 | 0 | 599713
Maspiro Towers | FPC |  | Maspiro Towers | 556650 | 544124.2 | 0 | 544124.2
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC11 | 11 | EMAAR-Pkg#162/163- Marassi11 | 9303551.52 | 7840185.4928 | 0 | 7840185.4928
Koning Food V2 - LP-08-20 | 12 |  | Koning Food V2 - LP-08-20 | 13517.54 | 30820 | 0 | 15410
Suez Gulf/S4 - 500KV OHTL | Suez S4 Equ Inv. +1 |  | Suez Gulf/S4 - 500KV OHTL | 1261 | 1324.05 | 0 | 1324.05
AWEER POWER STATION 'H' Phase | LOC-013 | 13 | AWEER POWER STATION 'H' Phase13 | 1083247.22 | 827963.34 | 120360.8 | 948324.14
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 03 | 3 | Suez Gulf/S4 - 500KV OHTL3 | 444301.13 | 371196.04 | 46651.62 | 417847.66
Ministries Buildings | MIN.SAHY&N-IPC02 | 2 | Ministries Buildings2 | 168220 | 66865 | 75200 | 142065
Zone(J) South Valley Toshka | South Valley Inv. 14 | 14 | Zone(J) South Valley Toshka14 | 29992616.95 | 22473314.85 | 3839055 | 26312369.85
Zone(J) South Valley Toshka | South Valley Inv. 05 | 5 | Zone(J) South Valley Toshka5 | 37030481.2 | 28216824.15 | 4739901.6 | 32956725.75
NUCA R05 - Z02 | R5PHASE2-IPC09 | 9 | NUCA R05 - Z029 | 19752275.4 | 15653276.7 | 1975227.6 | 17628504.3
MDF Factory | MDF FACTORY IPC11 | 11 | MDF Factory11 | 9266643.76 | 8835349.208 | 683594.29 | 9518943.498
Sodic East | IPC_23_SodicEast |  | Sodic East | 278336.98 | 246467.36 | 0 | 246467.36
New Babil 400/132KV Substation | 2103210016 |  | New Babil 400/132KV Substation | 211453.11 | 211453.11 | 0 | 211453.11
LAYAN Substation | 10527 |  | LAYAN Substation | 327177.32 | 543114.38 | 0 | 271557.19
R5 | inv(8)100620 | 8 | R58 | 1842000 | 276300 | 0 | 1698022.47
R5 | inv(17)28-2-21-R5 | 17 | R517 | 1296000 | 1199448 | 0 | 1199448
R5 | inv ( 16 ) R511-2-21 | 16 | R516 | 483000 | 446766.5 | 0 | 446766.5
El Sewedy University | Inv(4)300620 | 4 | El Sewedy University4 | 292158.15 | 14607.91 | 0 | 247493.3733
El Sewedy University | Inv(2)150420 | 2 | El Sewedy University2 | 553379.86 | 27668.99 | 0 | 481256.09
RING ROAD MARYOTIA EXPANSION | RING MARYITIA-IPC05 | 5 | RING ROAD MARYOTIA EXPANSION5 | 12516509.05 | 6453307.296 | 5000000 | 11453307.296
ESU Ph2-Enabling & Struc | E.S.U2-ARC&MEP-IPC12 | 12 | ESU Ph2-Enabling & Struc12 | 38061417.81 | 23340124.2605 | 2482953.77 | 25823078.0305
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC011 | 11 | EMAAR-Pkg#162/163- Marassi11 | 0.0001 | 1728865.5301 | 207927.24 | 1936792.7701
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC05 | 5 | EMAAR-Pkg#162/163- Marassi5 | 0.001 | 1890262.721 | 241883.6 | 2132146.321
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC10 | 10 | EMAAR-Pkg#162/163- Marassi10 | 3812993.56 | 2893980.578 | 743338.83 | 3637319.408
Koning Food V4 LP-01-21 | 46 |  | Koning Food V4 LP-01-21 | 62280.7 | 71000 | 0 | 71000
Kattameya Creeks | Kattameya IPC05 | 5 | Kattameya Creeks5 | 43155172.94 | 40007572.367 | 4873807.49 | 44881379.857
Kattameya Creeks | Katameya - IPC03 | 3 | Kattameya Creeks3 | 41751425.71 | 39570120.8955 | 3851361.84 | 43421482.7355
EDNC Retail & Offices Civil | Sodic Soreal IPC026 | 26 | EDNC Retail & Offices Civil26 | 45459659.77 | 33907888.6085 | 3686071.34 | 37593959.9485
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED PH.1 IPC07 | 7 | ORA ZED - Ph 01B - Pkgs A&D7 | 9268144.68 | 4340903.024 | 524341.16 | 4865244.184
Phosfat | Ref Retention fosfat |  | Phosfat | 360062.3 | 360062.3 | 0 | 360062.3
Mauritania Lot 1 | Inv.9 - Lot 1 | 9 | Mauritania Lot 19 | 73563.54 | 69885.36 | 0 | 69885.36
Mauritania Lot 1 | Inv.8 - Lot 1 | 8 | Mauritania Lot 18 | 71454.71 | 67881.97 | 0 | 67881.97
LAYYAH CCPP | 506 |  | LAYYAH CCPP | 12854700 | 11016258.75 | 2400425 | 13416683.75
DoubleTree Mangroovy ElGouna | Mangrove - IPC015 | 15 | DoubleTree Mangroovy ElGouna15 | 4199870.68 | 3002136.214 | 1008716.05 | 4010852.264
Diplomatic District - Infra | Diplo. Dist. IPC08 | 8 | Diplomatic District - Infra8 | 21256216.29 | 14841823.49 | 2025993.3 | 16867816.79
Air Force Project | Air Force Inv . 14 | 14 | Air Force Project14 | 4524624.26 | 3239516.96 | 1131156.05 | 4370673.01
Air Force Project | Air Force Inv . 13 | 13 | Air Force Project13 | 7847514 | 5618528.04 | 1961878.5 | 7580406.54
Air Force Project | Air Force Inv . 09 | 9 | Air Force Project9 | 5241355.52 | 3752405 | 1310338.85 | 5062743.85
Air Force Project | Air Force Inv . 02 | 2 | Air Force Project2 | 11154054.56 | 8253995 | 2788513.65 | 11042508.65
Faculty of Medicine | mansora uni ipc 15 | 15 | Faculty of Medicine15 | 14787583.81 | 12512110.79 | 739379.19 | 13251489.98
R5 Mix-Use Complex Project | R5-ZONE1-IPC6 | 6 | R5 Mix-Use Complex Project6 | 5139407 | 4207989.02 | 521813.76 | 4729802.78
Assuit PP (CP-118) | inv. 19-20 USD | 19 | Assuit PP (CP-118)19 | 351753.41 | 627879.84 | 110802.32 | 369341.08
NUCA R05 - Z02 | R5-ZONE 02- IPC02 | 2 | NUCA R05 - Z022 | 4448510 | 4886423.66 | 597472.17 | 5483895.83
NUCA R05 - Z02 | R5 - IPC17 | 17 | NUCA R05 - Z0217 | 40451064.68 | 28741122.464 | 3615988 | 32357110.464
GOV2 - Infra | GOV2 ipc25 | 25 | GOV2 - Infra25 | 8593894.33 | 3564488.5967 | 543005.59 | 4107494.1867
Group # 1 - 25 LX | Reailway PSP Inv. 04 | 4 | Group # 1 - 25 LX4 | 840000 | 831600 | 0 | 831600
LAYAN Substation | 10602 |  | LAYAN Substation | 221632.06 | 749116.36 | 0 | 187279.09
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 1 Equ | 1 | Hosh Essa 220 KV OHTL1 | 7784834.86 | 4673291.85 | 822803.11 | 5496094.96
Toshka GIS 500 kV | Toshka Sub Inv. 10 $ | 10 | Toshka GIS 500 kV10 | 226768.1 | 145305.66 | 59526.63 | 204832.29
SHATRA 400/132kV SS | 413 |  | SHATRA 400/132kV SS | 4636804.66 | 4636804.66 | 0 | 4636804.66
33KV Canal Farm Grid | Inv. +12 Farm |  | 33KV Canal Farm Grid | 655399.49 | 500069.81 | 98309.92 | 598379.73
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC014 | 14 | EMAAR-Pkg#162/163- Marassi14 | 0.001 | 3890540.431 | 467907.62 | 4358448.051
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC021.C | 21 | EMAAR-PKG# 101-UPTOWN21 | 0.001 | 0.0011 | 0 | 0.0011
EGAT Pelletizing Plant | EGAT IPC02 | 2 | EGAT Pelletizing Plant2 | 10496612.58 | 10019256.4705 | 897220.53 | 10916477.0005
LAYAN Substation | 10603 |  | LAYAN Substation | 51814.4 | 87566.34 | 0 | 43783.17
158E/2019 33kv Project | 10624 |  | 158E/2019 33kv Project | 731700 | 1975590 | 0 | 658530
seashell Playa | IPC-13-Playa | 13 | seashell Playa13 | 894385.1 | 619657.06 | 97184 | 716841.06
Marassi Inner Marina - PKG178 | IPC#2 - Marassi#178 | 2 | Marassi Inner Marina - PKG1782 | 797294 | 244127.1 | 0 | 709591.66
EGAT Pelletizing Plant | EGAT-IPC16 | 16 | EGAT Pelletizing Plant16 | 14282809.35 | 14096166.6275 | 757955.1 | 14854121.7275
10Th of Ramadan LRT | LRT 10Ramadan Inv.01 | 1 | 10Th of Ramadan LRT1 | 4534198.52 | 2520041.33 | 453419.85 | 2973461.18
R05 | IPC_1_R5_RME |  | R05 | 77798.38 | 52616.82 | 0 | 52616.82
AWEER POWER STATION 'H' Phase | IMP/064 |  | AWEER POWER STATION 'H' Phase | 1172089.69 | 1230694.1693 | 0 | 1230694.1693
Miscellaneous Projects | 2009210016 |  | Miscellaneous Projects | 151344.64 | 172532.89 | 0 | 172532.89
Miscellaneous Projects | 2009210015 |  | Miscellaneous Projects | 118487.2 | 135075.41 | 0 | 135075.41
ORA ZED - Ph 01B - Pkgs A&D | ora zed ipc15 | 15 | ORA ZED - Ph 01B - Pkgs A&D15 | 27710999.54 | 27179982.227 | 3259818.36 | 30439800.587
ORA ZED-Ph 2-Pkgs A&D | ORA PH2 IPC 19 | 19 | ORA ZED-Ph 2-Pkgs A&D19 | 8053943.79 | 7571824.5446 | 0 | 7571824.5446
Faculty of Medicine | Mansoura UNI IPC03 | 3 | Faculty of Medicine3 | 25228213.33 | 21346449.9965 | 1261410.67 | 22607860.6665
NUCA R05 - Z02 | R05 Zone1 IPC031 | 31 | NUCA R05 - Z0231 | 6928611.25 | 1721656.15 | 432416.15 | 2154072.3
LRT Project | IPC_4_LRT | 4 | LRT Project4 | 48870 | 41028.55 | 0 | 41028.55
Diplomatic District - Infra | Diplo Dist IPC03 | 3 | Diplomatic District - Infra3 | 454008.2 | 3105738.66 | 366118.54 | 3471857.2
Borg El Arab Bridge - Km 21 | IPC001 Kilo 21 | 1 | Borg El Arab Bridge - Km 211 | 1450916 | 900000 | 0 | 900000
RING ROAD MARYOTIA EXPANSION | Maryotia IPC09 | 9 | RING ROAD MARYOTIA EXPANSION9 | 9883488.33 | 3856121.53 | 5000000 | 8856121.53
Zone(J) South Valley Toshka | South Valley Inv. 08 | 8 | Zone(J) South Valley Toshka8 | 29880449.15 | 22768493.05 | 3824697.5 | 26593190.55
Marsa Alam/ Bernes LOT2 OHTL | Ref.Ret marsa Alam |  | Marsa Alam/ Bernes LOT2 OHTL | 1440292.025 | 2880584.05 | 0 | 1440292.025
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.03 | 3 | Mostakbal 2 Package No. (8)3 | 22861094.86 | 18974708.73 | 4800829.92 | 23775538.65
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC05 | 5 | ElSewedy HQ Internal Finishing5 | 6032812.38 | 3447418.189 | 1357462.2 | 4804880.389
Mansoura University | IPC03 - Mansoura | 3 | Mansoura University3 | 132413.92 | 131089.78 | 0 | 131089.78
EDNC Retail & Offices Civil | Sodic Soreal IPC031 | 31 | EDNC Retail & Offices Civil31 | 20856328.39 | 17493923.131 | 1136280.1985 | 18630203.3295
DoubleTree Mangroovy ElGouna | IPC05RENT-MANGROVY | 5 | DoubleTree Mangroovy ElGouna5 | 15000 | 15600 | 0 | 15600
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC017 | 17 | EMAAR-Pkg#162/163- Marassi17 | 0.0001 | 331162.2801 | 39828.23 | 370990.5101
Ain Sokhna Port Development | IPC#6 Sokhna Port | 6 | Ain Sokhna Port Development6 | 2194880 | 1694447.36 | 0 | 2063187.2
Ain Sokhna Port Development | IPC#2 - Sokhna Port | 2 | Ain Sokhna Port Development2 | 932824 | 872648.58 | 0 | 872648.58
Assuit PP (CP-118) | 2108210010 |  | Assuit PP (CP-118) | 165003.75 | 147265.84 | 25988.09 | 173253.93
RING ROAD MARYOTIA EXPANSION | Maryotia IPC010 | 10 | RING ROAD MARYOTIA EXPANSION10 | 17444582.38 | 10942755.33 | 5000000 | 15942755.33
SHAT Al ARAB 400/132kV SS | 424 |  | SHAT Al ARAB 400/132kV SS | 4634741.62 | 4634741.62 | 0 | 4634741.62
AWEER POWER STATION 'H' Phase | ENG/047 |  | AWEER POWER STATION 'H' Phase | 459843.86 | 482836.053 | 0 | 482836.053
Assuit PP (CP-118) | 2108210008 |  | Assuit PP (CP-118) | 3107208.26 | 2714138.3 | 489385.3 | 3203523.6
LAYAN Substation | 10823 |  | LAYAN Substation | 282320.7 | 468652.36 | 0 | 234326.18
Beni Suef Substation R61 | BSF-SD-EGP-03 | 3 | Beni Suef Substation R613 | 648000 | 576720 | 0 | 576720
ENR-Signaling Inst. | ENR-Sign Inst Inv02 | 2 | ENR-Signaling Inst.2 | 2907052.4 | 2441924.02 | 290705.24 | 2732629.26
Water pumping New Obour City | Wat Pump Obour Inv.1 | 1 | Water pumping New Obour City1 | 26712563.09 | 20413018.34 | 2804819.12 | 23217837.46
SHATRA 400/132kV SS | 386 |  | SHATRA 400/132kV SS | 1908512.08 | 1908512.08 | 0 | 1908512.08
MOTHANA 400/132kV SS | 415 |  | MOTHANA 400/132kV SS | 102959.11 | 102959.11 | 0 | 102959.11
Olympic Multi – Sports Hall | Olymipc Hall IPC06 | 6 | Olympic Multi – Sports Hall6 | 51027855.5 | 414025 | 23764386.15 | 43206241.15
Ain Sokhna Port Development | IPC#3 - Ain Sokhna P | 3 | Ain Sokhna Port Development3 | 1097440 | 1027834.55 | 0 | 1027834.55
Air Force Project | Air Force Inv . 17 | 17 | Air Force Project17 | 2559995.42 | 2472550 | 0 | 2472550
Racecores 3092-16 132KV C | 10966 |  | Racecores 3092-16 132KV C | 3123917.5 | 2592851.53 | 0 | 2592851.53
TZ – Offshore E&M Procurement | 430 |  | TZ – Offshore E&M Procurement | 2050.1 | 1640.08 | 410.02 | 2050.1
EGYTEC A1,A3 ( LP-05-21) | 44 |  | EGYTEC A1,A3 ( LP-05-21) | 2597090 | 1662137.6 | 1298545 | 2960682.6
Cables Egypt (LP-03-21) | 42 |  | Cables Egypt (LP-03-21) | 579060 | 355594.4 | 304530 | 660124.4
Hadaek ElAharam | IPC#1 | 1 | Hadaek ElAharam1 | 314087.5 | 267077.56 | 0 | 267077.56
Akhmem - Qena | Ret Qen-akh 8 T |  | Akhmem - Qena | 10000000 | 10000000 | 0 | 10000000
ENR-Signaling Inst. | ENR-Sign Inst Inv03 | 3 | ENR-Signaling Inst.3 | 3591140 | 3016557.6 | 359114 | 3375671.6
New Babil 400/132KV GIS Substa | 2112210001 |  | New Babil 400/132KV GIS Substa | 352324.8 | 352324.8 | 0 | 352324.8
Diplomatic District - Infra | Diplo Dist IPC07 | 7 | Diplomatic District - Infra7 | 20531079.1428 | 12611623.7628 | 1829209.53 | 14440833.2928
Benban 500 K.V / 100 K.M | Ref.1 benban Lot 1 T |  | Benban 500 K.V / 100 K.M | 4228160.14 | 4228160.14 | 0 | 4228160.14
Racecores 3092-17 132KV E | 11027 |  | Racecores 3092-17 132KV E | 1059711.84 | 879560.82 | 0 | 879560.82
MDF Factory | MDF IPC06 | 6 | MDF Factory6 | 17710147.67 | 17171362.1535 | 2532882.9 | 19704245.0535
Racecores 3092-16 132KV C | 11042 |  | Racecores 3092-16 132KV C | 9960 | 10458 | 0 | 10458
LP-24-21 Autostrada | 75 |  | LP-24-21 Autostrada | 1742695.64 | 1990457.1666 | 0 | 1990457.1666
Cairo Capital S1 | Ref. Capital S 1 T |  | Cairo Capital S1 | 54766270 | 54766270 | 0 | 54766270
Racecores 3092-16 132KV C | 11083 |  | Racecores 3092-16 132KV C | 10500 | 11025 | 0 | 11025
New Babil 400/132KV GIS Substa | 2112210008 |  | New Babil 400/132KV GIS Substa | 3676765.6 | 3676765.6 | 0 | 3676765.6
Mauritania-Lot 2 | Inv.15 – Lot 2 | 15 | Mauritania-Lot 215 | 339125.39 | 322112.87 | 0 | 322112.87
New Giza Teaching Hospital | new giza Hos ipc 25 | 25 | New Giza Teaching Hospital25 | 12359506.46 | 10195246.193 | 370205.76 | 10565451.953
New Giza Teaching Hospital | ipc13 New giza HOS | 13 | New Giza Teaching Hospital13 | 26683802.78 | 19237495.901 | 2273488.27 | 21510984.171
New Giza Teaching Hospital | new giza - ipc 11 | 11 | New Giza Teaching Hospital11 | 29644027.2 | 21461419.72 | 2942233.57 | 24403653.29
Ring Road -General Nile Co | INV ( 1 ) Fianl | 1 | Ring Road -General Nile Co1 | 656138 | 649576.62 | 0 | 649576.62
Egat Rolling Mill no.4 | Rolling mill IPC13 | 13 | Egat Rolling Mill no.413 | 14485776.56 | 11555244.6722 | 3509962.95 | 15065207.6222
EGAT Lock & Load | ipc14 Egad lock&load | 14 | EGAT Lock & Load14 | 2768145.62 | 2602056.8848 | 276814.56 | 2878871.4448
EGAT Lock & Load | EGAT L&L - IPC 13 | 13 | EGAT Lock & Load13 | 2116780.44 | 1989773.622 | 211678.04 | 2201451.662
EGAT Lock & Load | EGAT L&L-IPC 10+ | 10 | EGAT Lock & Load10 | 225255.97 | 211740.6085 | 22525.6 | 234266.2085
EGAT Lock & Load | EGAT L&L IPC 05 | 5 | EGAT Lock & Load5 | 3180176.34 | 2989365.767 | 318017.63 | 3307383.397
EGAT Lock & Load | EGAT L&L IPC03 | 3 | EGAT Lock & Load3 | 1772326.5 | 1665986.905 | 177232.65 | 1843219.555
EGAT Lock & Load | EGAT L&L ipc 01 | 1 | EGAT Lock & Load1 | 5018202.5 | 4717110.345 | 501820.25 | 5218930.595
Alfa New Central Labs | alfa lab ipc1(final) | 1 | Alfa New Central Labs1 | 1403211.67 | 1459340 | 0 | 1459340
New Babil 400/132KV GIS Substa | 2112210007 |  | New Babil 400/132KV GIS Substa | 221036.88 | 221036.88 | 0 | 221036.88
Hyper El-Temsah | ELTEMSAH MEP-IPC01 | 1 | Hyper El-Temsah1 | 2904234.6 | 2250174.87 | 0 | 2250174.87
Ain Sokhna Bridge – RME | IPC1 Supply Sokhna B | 1 | Ain Sokhna Bridge – RME1 | 617310 | 611895 | 0 | 611895
Cairo-Alex Railway | CAIRO-ALEX-IPC02 | 2 | Cairo-Alex Railway2 | 5895813.28 | 4164802.05 | 589581.33 | 4754383.38
Taval Sarai 52 | IPC-18-SARAY | 18 | Taval Sarai 5218 | 103870.5 | 79334.97 | 0 | 79334.97
TZ – Offshore E&M Procurement | 448 |  | TZ – Offshore E&M Procurement | 65739.99 | 65739.99 | 0 | 65739.99
Port Said Port Silos | Port Said Silos ipc1 | 1 | Port Said Port Silos1 | 9462048.96 | 6828805.57 | 946204.9 | 7775010.47
Port Said Port Silos | PORTSAID IPCSUPPLY11 |  | Port Said Port Silos | 921722.52 | 5002738.92 | 553033.5 | 925962.07
LP-26-21 Koning Food V5 | 49 |  | LP-26-21 Koning Food V5 | 25264 | 28764.48 | 0 | 28764.48
Ghana Street lighting | MIDA Sply. Inv.9 | 9 | Ghana Street lighting9 | 59165.18 | 53248.66 | 0 | 53248.66
Ghana Street lighting | MIDA Ins. Inv.9 | 9 | Ghana Street lighting9 | 17260.99 | 15534.89 | 0 | 15534.89
LP-13-21 -UIC | 43 |  | LP-13-21 -UIC | 44500 | 50285 | 0 | 50285
SHAT Al ARAB 400/132kV SS | 440 |  | SHAT Al ARAB 400/132kV SS | 37913.43 | 4928 | 0 | 4928
MAYSAN 400/132kV SS | 439 |  | MAYSAN 400/132kV SS | 2772 | 2772 | 0 | 2772
MOTHANA 400/132kV SS | 431 |  | MOTHANA 400/132kV SS | 2968 | 2968 | 0 | 2968
ORA ZED-Ph 2-Pkgs A&D | ora zed ph2 ipc03 | 3 | ORA ZED-Ph 2-Pkgs A&D3 | 15579509.09 | 9914986.5145 | 1179686.78 | 11094673.2945
ORA ZED-Ph 2-Pkgs A&D | ORA ZED 2 IPC04 | 4 | ORA ZED-Ph 2-Pkgs A&D4 | 34347323.22 | 30546043.101 | 3634373.4 | 34180416.501
Akhmem Assiut | Ret Asuit akh USD T |  | Akhmem Assiut | 1229629.86 | 1228184.73 | 0 | 1228184.73
AWEER POWER STATION 'H' Phase | ENG/051 |  | AWEER POWER STATION 'H' Phase | 43581.87 | 45760.9635 | 0 | 45760.9635
New Babil 400/132KV GIS Substa | 220221002 |  | New Babil 400/132KV GIS Substa | 1367396.75 | 1367396.75 | 0 | 1367396.75
Racecores 3092-16 132KV C | 11365 |  | Racecores 3092-16 132KV C | 207125.04 | 175020.66 | 0 | 175020.66
seashell Playa | IPC-14-PLAYA | 14 | seashell Playa14 | 523173.5 | 448935.17 | 0 | 448935.17
New Giza Teaching Hospital | newgizahospital ipc2 | 2 | New Giza Teaching Hospital2 | 20687718.13 | 14998595.6465 | 4298668.01 | 19297263.6565
158E/2019 33kv Project | 11383 |  | 158E/2019 33kv Project | 55442 | 249489 | 0 | 49897.8
TZ – Offshore E&M Procurement | 462 |  | TZ – Offshore E&M Procurement | 87296.9 | 87296.9 | 0 | 87296.9
Port Saeed East - OHTL | Port said OHTL Inv.2 | 2 | Port Saeed East - OHTL2 | 11828320.9 | 10556355 | 0 | 10556355
TZ – Offshore E&M Procurement | 453 |  | TZ – Offshore E&M Procurement | 495071.03 | 495071.03 | 0 | 495071.03
Water pumping New Obour City | Wat Pump Obour Inv.4 | 4 | Water pumping New Obour City4 | 23249198.38 | 22418611.4 | 3007923.25 | 25426534.65
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 10 | 10 | Suez Gulf/S4 - 500KV OHTL10 | 14755772.95 | 6692205.17 | 0 | 6692205.17
Ismailiya East Substation | تعويضات الاسماعلية |  | Ismailiya East Substation | 5847209 | 5847209 | 0 | 5847209
AWEER POWER STATION 'H' Phase | ENG/053 |  | AWEER POWER STATION 'H' Phase | 1087021.4 | 1141372.47 | 0 | 1141372.47
MDF Factory | MDF-ipc 21 | 21 | MDF Factory21 | 13626930.9 | 6432396.485 | 6988438.9 | 13420835.385
seashell Playa | IPC-15-PLAYA | 15 | seashell Playa15 | 339333.4 | 291181.99 | 0 | 291181.99
LAYAN Substation | 11503 |  | LAYAN Substation | 942937.7179 | 3187129.48 | 0 | 796782.37
ORA ZED-Ph 2-Pkgs A&D | ora zed2 ipc5 | 5 | ORA ZED-Ph 2-Pkgs A&D5 | 10060644.07 | 13201853.2135 | 1589461.07 | 14791314.2835
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 14 | 14 | Suez Gulf/S4 - 500KV OHTL14 | 4206178.63 | 1852832.03 | 0 | 1852832.03
Water pumping New Obour City | Wat Pump Obour Inv.3 | 3 | Water pumping New Obour City3 | 13488823.98 | 10305064.43 | 1416326.52 | 11721390.95
East Owainat 5 LOTS | East Owainat Inv. 07 | 7 | East Owainat 5 LOTS7 | 25352298.03 | 10343728.9 | 13309956.47 | 23653685.37
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC31 | 31 | EMAAR-Pkg#162/163- Marassi31 | 10357799.14 | 10109132.947 | 0 | 10109132.947
Mivida BP#189 | Emaar Pkg#189 ipc 26 | 26 | Mivida BP#18926 | 16876594.44 | 14177811.26 | 11952085.3 | 26129896.56
Mivida BP#189 | pkg#189 ipc 25 | 25 | Mivida BP#18925 | 29437278.32 | 28360739.446 | 3616556.37 | 31977295.816
Mivida BP#189 | Emaar PKG#189 IPC12 | 12 | Mivida BP#18912 | 15682494.86 | 17976827.49 | 2172158.86 | 20148986.35
AWEER POWER STATION 'H' Phase | IMP/068 |  | AWEER POWER STATION 'H' Phase | 108589.53 | 31973.58 | 12065.5 | 44039.08
Racecores 3092-17 132KV E | 11539 |  | Racecores 3092-17 132KV E | 155284.9823 | 262431.6229 | 0 | 131215.8114
Ghana Street lighting | MIDA Sply.inv.13 | 13 | Ghana Street lighting13 | 69408.34 | 62467.5 | 0 | 62467.5
Angola Emergency fast-track | ANG-Cam-Inv 7 - Int. | 7 | Angola Emergency fast-track7 | 4736059.02 | 2468374.87 | 0 | 2468374.87
EGAT Pelletizing Plant | ELCO EGAT IPC03 | 3 | EGAT Pelletizing Plant3 | 4383722.29 | 4121328.6545 | 437742.53 | 4559071.1845
CFC Podium 2 | CFC IPC 28 | 28 | CFC Podium 228 | 5026145.48 | 34503065.494 | 0 | 34503065.494
Ghana Street lighting | MIDA Ins.inv.13 | 13 | Ghana Street lighting13 | 19576.71 | 17619.04 | 0 | 17619.04
Industria Sadat | Sadat Indust Inv. 06 | 6 | Industria Sadat6 | 9594113.03 | 14389560.81 | 2014763.74 | 16404324.55
El Khatatba Bridge | EL KHATATBA ipc01 | 1 | El Khatatba Bridge1 | 40855295.24 | 6931826.092 | 0 | 27828222.092
Faculty of Medicine | MANSOURAFINSH IPC 26 | 26 | Faculty of Medicine26 | 7416829.52 | 5533663 | 1112524.43 | 6646187.43
Faculty of Medicine | Mansora finish ipc21 | 21 | Faculty of Medicine21 | 9255149.52 | 6905326 | 1388272.43 | 8293598.43
Faculty of Medicine | mansora finish ipc07 | 7 | Faculty of Medicine7 | 5805872.38 | 4331651.78 | 870880.86 | 5202532.64
Faculty of Medicine | mansora finish ipc03 | 3 | Faculty of Medicine3 | 1401587.62 | 1045391.37 | 210238.14 | 1255629.51
Al Montaza Hotels - Alexandria | inv ( 10 ) montazha | 10 | Al Montaza Hotels - Alexandria10 | 587463 | 556939.85 | 0 | 556939.85
Mauritania-Lot 2 | Inv.16 - Lot 2 | 16 | Mauritania-Lot 216 | 335843.79 | 318995.35 | 0 | 318995.35
Fish Market | م 1 سوق السمك صحى/حر | 1 | Fish Market1 | 3955199.05 | 1303149.0025 | 2357104.35 | 3660253.3525
NUCA R05 - Z02 | R05 Zone2 IPC018 | 18 | NUCA R05 - Z0218 | 24098912.8 | 23625902.74 | 2928079.6 | 26553982.34
NUCA R05 - Z02 | R05 Finishing IPC014 | 14 | NUCA R05 - Z0214 | 9342241 | 9916188.05 | 1285435.7 | 11201623.75
EDNC Hardscape Package | sodichardescape ipc1 | 1 | EDNC Hardscape Package1 | 1310241.41 | 1589312.7705 | 0 | 1589312.7705
EDNC Hardscape Package | EDNC hardscape IPC05 | 5 | EDNC Hardscape Package5 | 8146275.95 | 3116872.1575 | 0 | 3116872.1575
Racecores 3092-16 132KV C | 11660 |  | Racecores 3092-16 132KV C | 5591.34 | 5591.34 | 0 | 5591.34
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC39 | 39 | EMAAR-Pkg#162/163- Marassi39 | 62325696.1 | 27439277.805 | 36110671.44 | 63549949.245
Port Said Port Silos | Port Said Silos ipc3 | 3 | Port Said Port Silos3 | 5972851.95 | 5357634.0375 | 540557.26 | 5898191.2975
Astoria Sharm elSheikh | Astoria sharm IPC3 | 3 | Astoria Sharm elSheikh3 | 2440310 | 1641108 | 640581.38 | 2281689.38
AWEER POWER STATION 'H' Phase | CON/033 |  | AWEER POWER STATION 'H' Phase | 638849.32 | 560767.73 | 70983.26 | 631750.99
Ghana Street lighting | MIDA SPLY.7 |  | Ghana Street lighting | 171991.53 | 154792.38 | 0 | 154792.38
Diplomatic District - Infra | Diplomatic ipc09 | 9 | Diplomatic District - Infra9 | 23246376.48 | 12693962.184 | 1807211.4 | 14501173.584
Benban 3/ Toshka 2 Lot 6 | Ref-Ret-Toshka Lot6$ |  | Benban 3/ Toshka 2 Lot 6 | 462416.26 | 24639.42 | 437776.84 | 462416.26
kayan wall lock & Load | kyan L&L final |  | kayan wall lock & Load | 3600000 | 3392590 | 0 | 3392590
Water pumping New Obour City | Wat Pump Obour Inv.6 | 6 | Water pumping New Obour City6 | 17761555.87 | 9755616.46 | 1360358.25 | 11115974.71
Beymen Fit Out | PKG#205 IPC03 | 3 | Beymen Fit Out3 | 2048097.8 | 1357991.24 | 645150.81 | 2003142.05
TZ – Offshore E&M Procurement | 461 |  | TZ – Offshore E&M Procurement | 71176.47 | 71176.47 | 0 | 71176.47
Business District Hyde Park | INV ( 6-9 ) HY Bark | 6 | Business District Hyde Park6 | 3114104.19 | 0 | 0 | 3114104.19
Business District Hyde Park | INV ( 5 ) HY Bark | 5 | Business District Hyde Park5 | 1536000 | 1284209.74 | 0 | 1284209.74
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 35 | 35 | Benban 500 K.V/95 K.M35 | 6264980.64 | 4602136.03 | 657822.97 | 5259959
Racecores 3092-17 132KV E | 11683 |  | Racecores 3092-17 132KV E | 99481.9048 | 104456 | 0 | 104456
HSR-6th of October | IPC#1 - HSR | 1 | HSR-6th of October1 | 285860 | 248698.2 | 0 | 248698.2
Monorail | 220621009 |  | Monorail | 1453192 | 1642106.96 | 0 | 1642106.96
MDF Factory | MDF - IPC 20 | 20 | MDF Factory20 | 10304099.23 | 1506264.6515 | 7842049.02 | 9348313.6715
El Sadat City | Sadat City Inv. 01 | 1 | El Sadat City1 | 79292831.19 | 52376438.56 | 0 | 52376438.56
seashell Playa | IPC-17-PLAYA | 17 | seashell Playa17 | 359096.5 | 254541.27 | 0 | 254541.27
Cairo Monorail - 6th October | IPC#8 Monorail | 8 | Cairo Monorail - 6th October8 | 1476000 | 1412565 | 0 | 1412565
New Babil 400/132KV GIS Substa | 220721003 |  | New Babil 400/132KV GIS Substa | 134678.4 | 134678.4 | 0 | 134678.4
East Owainat 5 LOTS | East Owainat Inv.3 V | 3 | East Owainat 5 LOTS3 | 58903586.5 | 23336380.69 | 30924382.91 | 54260763.6
Expansion of Ring Road | IPC#1 - Tiger | 1 | Expansion of Ring Road1 | 303400 | 300366 | 0 | 300366
EDNC Hardscape Package | SODIC HARD IPC02 | 2 | EDNC Hardscape Package2 | 3188822.83 | 2794789.4915 | 0 | 2794789.4915
seashell Playa | IPC-2-PLAYA | 2 | seashell Playa2 | 99925.05 | 69757.644 | 15988.05 | 85745.694
Marassi - Water proofing | IPC-2-PKG#177 Water | 2 | Marassi - Water proofing2 | 28370.27 | 25121.88 | 0 | 25121.88
Sodic East | IPC_18_Rowad_Seast |  | Sodic East | 554998.17 | 653719.408 | 0 | 653719.408
EMAAR-Pkg#162/163- Marassi | pkg#177 ipc 24 | 24 | EMAAR-Pkg#162/163- Marassi24 | 5954515.9 | 5112916.32 | 0 | 5112916.32
HSR-6th of October | IPC#2 HSR | 2 | HSR-6th of October2 | 699340 | 608425.8 | 0 | 608425.8
W Dam PP Phase II (CP-117) | 15 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 16158.31 | 16158.31 | 0 | 16158.31
Assuit PP (CP-118) | 220721004 |  | Assuit PP (CP-118) | 44375.66 | 46594.443 | 0 | 46594.443
Faculty of Medicine | MANSOURA IPC12 | 12 | Faculty of Medicine12 | 5167995.24 | 4434711.832 | 258399.76 | 4693111.592
ElSewedy HQ Internal Finishing | sewedy HQ IPC17 | 17 | ElSewedy HQ Internal Finishing17 | 17076484.19 | 2847047.2295 | 7737698.68 | 15750846.1095
Waldorf Astoria Cairo | Waldorf Astoria IPC3 | 3 | Waldorf Astoria Cairo3 | 6522225.37 | 5421697.4285 | 3511949.46 | 8933646.8885
Port Said Grain Storage | IPC#3 GSCC Port | 3 | Port Said Grain Storage3 | 693000 | 497431.1 | 0 | 592913.3
LINX Tower | Inv ( Final ) Linx |  | LINX Tower | 912123.24 | 689404.152 | 0 | 689404.152
PO3092200025 | 11703 |  | PO3092200025 | 0 | -125 | 0 | -125
SSC Suez Steel Company Project | In&ReSupply(ssc)IPC3 | 3 | SSC Suez Steel Company Project3 | 374122.68 | 283552.0652 | 139206.56 | 422758.6252
SSC Suez Steel Company Project | int&ret supAbb ipc8 | 8 | SSC Suez Steel Company Project8 | 1041476.54 | 817934.2656 | 358934.22 | 1176868.4856
SSC Suez Steel Company Project | In&ReApply(ABB)IPC2 | 2 | SSC Suez Steel Company Project2 | 1514111.96 | 988420.7044 | 692243.57 | 1680664.2744
SSC Suez Steel Company Project | in&re.app abb ipc 3 | 3 | SSC Suez Steel Company Project3 | 1605876.32 | 1048324.9852 | 734197.73 | 1782522.7152
Waldorf Astoria Cairo | waldorf - IPC16 | 16 | Waldorf Astoria Cairo16 | 9372213.84 | 0 | 3294201.48 | 6519884.48
Waldorf Astoria Cairo | Waldorf- IPC 15 | 15 | Waldorf Astoria Cairo15 | 9032753.1 | 0 | 4276171.2 | 8461832.735
Air Defence College | TR0046-IPC002 | 2 | Air Defence College2 | 223641.12 | 189871.3 | 0 | 189871.3
Waldorf Astoria Cairo | ipc17woldoef astoria | 17 | Waldorf Astoria Cairo17 | 7818140.35 | 0 | 2863892.36 | 5668051.36
EPICO 3 Facility | Eipico 3 ipc 12 | 12 | EPICO 3 Facility12 | 13086699.86 | 25548194.95 | 9585575.71 | 35133770.66
ORA ZED-Ph 2-Pkgs A&D | ora ph.2 ipc9 | 9 | ORA ZED-Ph 2-Pkgs A&D9 | 8712415.5 | 7614021.055 | 900969.93 | 8514990.985
Al Montaza Hotels - Alexandria | inv ( 11 ) montazha | 11 | Al Montaza Hotels - Alexandria11 | 426809.5 | 403719.02 | 0 | 403719.02
EDNC Hardscape Package | Soreal HardscapeIPC7 | 7 | EDNC Hardscape Package7 | 5611542.56 | 2434849.578 | 0 | 2434849.578
El Taameer Axis Expansion | IPC#1 Taamer PII | 1 | El Taameer Axis Expansion1 | 172260 | 166403.16 | 0 | 166403.16
CS-20 Mall | inv ( 3 ) CS-20 | 3 | CS-20 Mall3 | 3929643.6 | 821864.65 | 0 | 821864.65
Mivida BP#189 | PKG#189 IPC3 | 3 | Mivida BP#1893 | 27730887.07 | 23971236.1335 | 2883960.5 | 26855196.6335
NUCA R05 - Z02 | R05(2) ipc26 | 26 | NUCA R05 - Z0226 | 12786322.39 | 10853224.66 | 1359017.8 | 12212242.46
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC13 | 13 | EMAAR-Pkg#162/163- Marassi13 | 709528.81 | 8135757.8105 | 0 | 8135757.8105
HST Bridges-Sokhna & Mahager | SOKHNA BRIDGE 8+9+10 |  | HST Bridges-Sokhna & Mahager | 43660371.43 | 637790.3157 | 0 | 39637790.3157
EDNC Hardscape Package | sorealhardscape IPC8 | 8 | EDNC Hardscape Package8 | 16821952.2 | 9494386.1475 | 0 | 9494386.1475
The American School ASE | INV ( FINAL ) USA S |  | The American School ASE | 306353.5 | 303289.96 | 0 | 303289.96
The American School ASE | INV ( 1 ) USA S | 1 | The American School ASE1 | 202972.5 | 200942.77 | 0 | 200942.77
Mivida BP#189 | PKG#189- IPC6 | 6 | Mivida BP#1896 | 57254690.6 | 49630186.51 | 5982950.12 | 55613136.63
Air Defense College | Ari Dev3 IPC2 | 2 | Air Defense College2 | 679505 | 285725 | 0 | 574970
WADY EL-NATROUN BRIDGE(HST) | IPC9 WADI | 9 | WADY EL-NATROUN BRIDGE(HST)9 | 1299480 | 1140233.66 | 0 | 1140233.66
RING ROAD MARYOTIA EXPANSION | mariotya ipc 18 | 18 | RING ROAD MARYOTIA EXPANSION18 | 4431970 | 3881647.75 | 0 | 3881647.75
HST Bridges-Sokhna & Mahager | elsokhna ipc5+6+7 | 5 | HST Bridges-Sokhna & Mahager5 | 16141864.29 | 14250689.3 | 0 | 14250689.3
Get Business Complex | INV ( 21 ) GET | 21 | Get Business Complex21 | 2445777.04 | 133942.41 | 0 | 133942.41
Ain Sokhna Port Development | IPC22-AIN SOKHNA | 22 | Ain Sokhna Port Development22 | 1172898 | 1918789.58 | 0 | 991565.91
SSC Suez Steel Company Project | Revamp- IPC 6 | 6 | SSC Suez Steel Company Project6 | 8858061.69 | 6112062.5676 | 2657418.51 | 8769481.0776
SSC Suez Steel Company Project | Revamp ipc(2) | 2 | SSC Suez Steel Company Project2 | 1797569.47 | 0 | 539270.84 | 1869472.2488
Kafr Shokr Bridge | kafr shokr ipc 10 | 10 | Kafr Shokr Bridge10 | 2706642.86 | 2390708.77 | 0 | 2390708.77
Ministries Buildings | Min Core ipc 11 | 11 | Ministries Buildings11 | 21402202 | 16836655 | 0 | 16836655
Egyptian Exchange Building | Egy Ex ipc 01 | 1 | Egyptian Exchange Building1 | 176933890.48 | 36951715 | 82622000 | 155263715
Sokhna Port Expansion | sokhna port ex ipc09 | 9 | Sokhna Port Expansion9 | 43350211.2 | 30030028.52 | 8670042.24 | 38700070.76
SSC Suez Steel Company Project | R.o(50:80) supp ipc7 | 7 | SSC Suez Steel Company Project7 | 7188907.18 | 5966792.9552 | 2156672.16 | 8123465.1152
SSC Suez Steel Company Project | ro(5000:800)app ipc3 | 3 | SSC Suez Steel Company Project3 | 2894610.35 | 2225665.8924 | 987351.58 | 3213017.4724
EGAT Injection | IPC00004 | 4 | EGAT Injection4 | 546308.7 | 468787.5 | 0 | 468787.5
Olympic Multi – Sports Hall | Olympic finsh IPC2 | 2 | Olympic Multi – Sports Hall2 | 3124225 | 2631750 | 0 | 2631750
PLAYA ROOF & Wet Areas | IPC0000017 | 17 | PLAYA ROOF & Wet Areas17 | 155162.83 | 133145.22 | 0 | 133145.22
Port Said Port Silos | port said silosipc10 | 10 | Port Said Port Silos10 | 8366928.53 | 7412449.0665 | 836692.85 | 8249141.9165
October Under-Railway Tunnel | october tunnel ipc2 | 2 | October Under-Railway Tunnel2 | 4380339.19 | 3508352.9 | 0 | 3508352.9
MAF HQ Renovation | Carrefour H Off ipc4 | 4 | MAF HQ Renovation4 | 2486161.49 | 1402420.1797 | 922140.81 | 2324560.9897
Kayan 3 New Cairo Capital City | Kayan fin Ipc fin |  | Kayan 3 New Cairo Capital City | 1710756 | 1611980 | 0 | 1611980
Jawhar El-Lala Mosque | IPC000001 | 1 | Jawhar El-Lala Mosque1 | 16500 | 14008.5 | 0 | 14008.5
Egyptian Exchange Building | Eg Exchge IPC2 | 2 | Egyptian Exchange Building2 | 18198998.1 | 16187610 | 0 | 16187610
ORA-ZED Towers P01B | IPC006 | 6 | ORA-ZED Towers P01B6 | 400980.93 | 355068.61 | 0 | 355068.61
SSC Suez Steel Company Project | R.O. - SUPPLY IPC 1 | 1 | SSC Suez Steel Company Project1 | 16503981 | 13698304.23 | 4951194.3 | 18649498.53
DP World Basin 2 Ph2 | Dp world IPC10 | 10 | DP World Basin 2 Ph210 | 66818227.5 | 49445488.36 | 10022734.12 | 59468222.48
Monoril | inv ( 1 ) monoril | 1 | Monoril1 | 783613.1 | 744432.44 | 0 | 744432.44
MAF HQ Renovation | IPC 1 head office | 1 | MAF HQ Renovation1 | 4184919.24 | 2814358.19 | 1098541.3 | 3912899.49
Sokhna Port Expansion | spx.2 ipc 03 | 3 | Sokhna Port Expansion3 | 26794714.1 | 10464912.35 | 5358942.82 | 23823855.17
MAF HQ Renovation | carrefour H off ipc2 | 2 | MAF HQ Renovation2 | 4612182.33 | 3101692.62 | 1210697.86 | 4312390.48
Port Said Port Silos | port said inv.1-supp | 1 | Port Said Port Silos1 | 673851.6 | 3278288.02 | 336925.8 | 723042.764
WADY EL-NATROUN BRIDGE(HST) | IPC#13 WADI | 13 | WADY EL-NATROUN BRIDGE(HST)13 | 538020 | 482679.16 | 0 | 482679.16
Seashell Playa 5 Villas | playa -c185 ipc 3 | 3 | Seashell Playa 5 Villas3 | 70343.21 | 56077.3 | 0 | 56077.3
Seashell Playa 5 Villas | Playa - C185 ipc 2 | 2 | Seashell Playa 5 Villas2 | 23604.6 | 20384.93 | 0 | 20384.93
Katameya Creeks - RME | IPC004 | 4 | Katameya Creeks - RME4 | 11585.51 | 10258.96 | 0 | 10258.96
El Taameer Axis Expansion | FPC - Tamer Axis PII |  | El Taameer Axis Expansion | 398750 | 384917.5 | 0 | 384917.5
Alamein Coastal Road Bridge | sahilil IPC final |  | Alamein Coastal Road Bridge | 25444414.29 | 14904090 | 0 | 21361140
EPICO 3 Facility | Eipico ipc 4 | 4 | EPICO 3 Facility4 | 8374674.18 | 7344658.43 | 2480166.71 | 9824825.14
Cairo Monorail - 6th October | IPC#11 Monorail | 11 | Cairo Monorail - 6th October11 | 144000 | 142560 | 0 | 142560
HST - 6 October - Arab Cont. | IPC#3 HSR ARAB | 3 | HST - 6 October - Arab Cont.3 | 2016995 | 500000 | 0 | 500000
U3 & U5 | IPC09 TR55 | 9 | U3 & U59 | 82039.18 | 34899.03 | 0 | 34899.03
U3 & U5 | IPC005 TR55 | 5 | U3 & U55 | 280104.2 | 241897.99 | 0 | 241897.99
Seashell Playa 5 Villas | PLAYA c045 - ipc 2 | 2 | Seashell Playa 5 Villas2 | 334116.69 | 215718.58 | 0 | 215718.58
Seashell Playa 5 Villas | playa c038- ipc 1 | 1 | Seashell Playa 5 Villas1 | 145532.4 | 59531.13 | 0 | 59531.13
U4,U8 Seashell Playa | IPC004 TR60 | 4 | U4,U8 Seashell Playa4 | 496585.97 | 428851.64 | 0 | 428851.64
U7-SEASHELL | IPC002 TR64 | 2 | U7-SEASHELL2 | 62188.74 | 53706.19 | 0 | 53706.19
U4,U8 Seashell Playa | IPC005 TR60 | 5 | U4,U8 Seashell Playa5 | 404752.89 | 349544.6 | 0 | 349544.6
seashell Playa | IPC00027TR38 | 27 | seashell Playa27 | 224545.02 | 192682.08 | 0 | 192682.08
Wadi Halfa Port | wady halfa esc.2 |  | Wadi Halfa Port | 10950490.88 | 10413528.9712 | 0 | 10413528.9712
Wadi Halfa Port | wadi halfa ipc 03 | 3 | Wadi Halfa Port3 | 4077802.86 | 2807168.5814 | 856338.6 | 3663507.1814
R05 (New) | IPC003 TR59 | 3 | R05 (New)3 | 52098 | 44184.31 | 0 | 44184.31
RING ROAD MARYOTIA EXPANSION | mariotya ipc19 | 19 | RING ROAD MARYOTIA EXPANSION19 | 15814702.29 | 15656555.2745 | 0 | 15656555.2745
EL Sewedy University Tec. | INV ( 3 ) S.UNIV | 3 | EL Sewedy University Tec.3 | 69115.2 | 57950.96 | 0 | 57950.96
Wady El Natroon Bridge | ipc 3 wady elnatroon | 3 | Wady El Natroon Bridge3 | 8683485.71 | 7741398.95 | 0 | 7741398.95
ORA ZED - Ph 01B - Pkgs A&D | ORA PH.1 - IPC 21 | 21 | ORA ZED - Ph 01B - Pkgs A&D21 | 9295357.14 | 8181176.157 | 974442.67 | 9155618.827
Egat Rolling Mill no.4 | Rolling Mill- IPC12 | 12 | Egat Rolling Mill no.412 | 16694409.38 | 13213211.259 | 4148974.5 | 17362185.759
Ora Zed Landscape Ph1 | Ora landscape ipc 7 | 7 | Ora Zed Landscape Ph17 | 1343089.52 | 1035276.496 | 141024.4 | 1176300.896
Olympic Multi – Sports Hall | Olympic Finsh3 IPC1 | 1 | Olympic Multi – Sports Hall1 | 21127578 | 4019720 | 12400000.51 | 16419720.51
EMAAR-Pkg#162/163- Marassi | pkg#163- Inv. 27 | 27 | EMAAR-Pkg#162/163- Marassi27 | 4132634.87 | 3653603.3235 | 0 | 3653603.3235
Kemet Tower | CR INV ( 09 ) KEMET | 9 | Kemet Tower9 | 185120 | 158851.46 | 0 | 158851.46
Tarek Abdel-Hakim Center | TAH ipc09 | 9 | Tarek Abdel-Hakim Center9 | 7602439.9 | 5675544.71 | 684219.59 | 6359764.3
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc (21) | 21 | ORA ZED-Ph 2-Pkgs A&D21 | 4766150.56 | 4432160.4921 | 560694.95 | 4992855.4421
SSC Suez Steel Company Project | i&R apply (ssc)ipc 1 | 1 | SSC Suez Steel Company Project1 | 573500 | 0 | 0 | 636585
SSC Suez Steel Company Project | intake&return S ipc4 | 4 | SSC Suez Steel Company Project4 | 817103.94 | 0 | 281606.5 | 923327.4522
Seashell Playa 5 Villas | playa-c038ipc(5) | 5 | Seashell Playa 5 Villas5 | 205614.11 | 154045.02 | 0 | 154045.02
ora zed orascom | IPC08TR0069 | 8 | ora zed orascom8 | 343689.62 | 68737.92 | 0 | 68737.92
KATAMYA GREEKS LAND SCAPE STAR | IPC04TR0081 | 4 | KATAMYA GREEKS LAND SCAPE STAR4 | 1354395.24 | 1338955.132 | 0 | 1338955.132
Creeks URBN-K | URBN-K IPC (5) | 5 | Creeks URBN-K5 | 29818122.52 | 13533059 | 16464358.31 | 29997417.31
SSC Suez Steel Company Project | In.&Re. Sup.SSC-IPC6 | 6 | SSC Suez Steel Company Project6 | 1555469.69 | 1178909.0902 | 578771.64 | 1757680.7302
SSC Suez Steel Company Project | R.O. Supply- IPC 6 | 6 | SSC Suez Steel Company Project6 | 2589997.98 | 2149698.3272 | 776999.39 | 2926697.7172
Mohamed Ali Palace Restoration | MOHAMED ALY2 IPC03 | 3 | Mohamed Ali Palace Restoration3 | 1398734.39 | 439447.0995 | 877758.5 | 1317205.5995
Mohamed Ali Palace Restoration | MohamedAly 2 - IPC01 | 1 | Mohamed Ali Palace Restoration1 | 8726957.14 | 5993163.6 | 2023560 | 8016723.6
Ora Zed Landscape Ph1 | Ora Landscape ipc 9 | 9 | Ora Zed Landscape Ph19 | 4486249.0225 | 3863087.97 | 463402.7 | 4479909.2558
EGAT Pelletizing Plant | Admin Building ipc 1 | 1 | EGAT Pelletizing Plant1 | 61566718.68 | 27089356.2172 | 36940031.21 | 64029387.4272
Port Said Port Silos | portsaid 2-supp.EGP |  | Port Said Port Silos | 1194976.65 | 4650847.76 | 477990.64 | 1282209.6
Al-Parco | INV ( 5 ) ALparco | 5 | Al-Parco5 | 3424286 | 3187658.86 | 0 | 3187658.86
Air Defense College | Air dev Finish3 IPC3 | 3 | Air Defense College3 | 3116565 | 2122130 | 0 | 2630384
Ain Sokhna Bridge | Inv ( 2 ) A.S | 2 | Ain Sokhna Bridge2 | 2683648.47 | 2066484.69 | 0 | 2066484.69
Waldorf Astoria Cairo | woldorf astori ipc23 | 23 | Waldorf Astoria Cairo23 | 13277404.76 | 20506021.05 | 0 | 20933799.87
SSC Suez Steel Company Project | revamp(smp1)ipc1 | 1 | SSC Suez Steel Company Project1 | 15192302.49 | 7667227.3596 | 7596151.24 | 15799994.6096
TOSHKA MADKOUR | IPC02TR0083 | 2 | TOSHKA MADKOUR2 | 597774.24 | 532019.08 | 0 | 532019.08
Mivida BP#189 | Emaar pkg#189ipc17 | 17 | Mivida BP#18917 | 30434807.73 | 47104890.0565 | 2724540.31 | 49829430.3665
U3 & U5 | IPC16TR0055 | 16 | U3 & U516 | 95367.68 | 82359.53 | 0 | 82359.53
Hyper El-Temsah | ELTAMSAH-كهرو MEP-01 | 1 | Hyper El-Temsah1 | 65420317 | 24429401.35 | 30000000 | 54429401.35
Mohamed Ali Palace Restoration | Mohamed Aly IPC05 | 5 | Mohamed Ali Palace Restoration5 | 8004368.18 | 2197969.3 | 4715628.9 | 6913598.2
Ora Zed Landscape Ph1 | Ora Landscape ipc 4 | 4 | Ora Zed Landscape Ph14 | 4909564.83 | 4332690.6 | 515504.31 | 4848194.91
Air Defense College | Air Dev Elec IPC1 | 1 | Air Defense College1 | 111172167 | 48691810 | 229975490 | 92889100
NUCA R05 - Z02 | R5 (2) ipc34 | 34 | NUCA R05 - Z0234 | 15591657.65 | 12417472.88 | 1587374.7 | 14004847.58
South Dabaa Axis | ipc 1 south dabaa | 1 | South Dabaa Axis1 | 1048928 | 300348.5 | 0 | 300348.5
El-Warraq | IPC final elwaraq |  | El-Warraq | 198000 | 147117.32 | 0 | 147117.32
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC (30) | 30 | EMAAR-Pkg#162/163- Marassi30 | 8788912.25 | 3404339.9025 | 0 | 3404339.9025
SSC Suez Steel Company Project | int&ret sup ssc ipc7 | 7 | SSC Suez Steel Company Project7 | 2983296.88 | 2261076.4232 | 1110049.05 | 3371125.4732
SSC Suez Steel Company Project | int&ret sup abb ipc7 | 7 | SSC Suez Steel Company Project7 | 10394599.15 | 8151504.971 | 3582392.07 | 11733897.041
RING ROAD MARYOTIA EXPANSION | Mariotya ipc24 zomor | 24 | RING ROAD MARYOTIA EXPANSION24 | 1630460.9 | 1574628.39 | 0 | 1574628.39
RING ROAD MARYOTIA EXPANSION | Mariotya ipc 24 | 24 | RING ROAD MARYOTIA EXPANSION24 | 4972835.81 | 4218639.41 | 0 | 4218639.41
AIRDEFNSE -EPOXY | IPC02 TR66 | 2 | AIRDEFNSE -EPOXY2 | 123592.6 | 104930.11 | 0 | 104930.11
Kattmeya Creeks Urban | IPC 2 TR71 | 2 | Kattmeya Creeks Urban2 | 497936.61 | 440922.87 | 0 | 440922.87
AIRDEFNSE -EPOXY | ipc006 TR66 | 6 | AIRDEFNSE -EPOXY6 | 673170.6 | 571521.83 | 0 | 571521.83
AIRDEFNSE -EPOXY | IPC04TR0066 | 4 | AIRDEFNSE -EPOXY4 | 13737.9 | 11663.47 | 0 | 11663.47
Waldorf Astoria Cairo | Woldorf Asto ipc 21 | 21 | Waldorf Astoria Cairo21 | 1422437.2 | 0 | 0 | 854978.78
October Under-Railway Tunnel | october tunnelipc3+4 | 3 | October Under-Railway Tunnel3 | 5911928.1 | 5155347.1955 | 0 | 5155347.1955
October Under-Railway Tunnel | october tunnel ipc7 | 7 | October Under-Railway Tunnel7 | 10389360.67 | 9353909.62 | 0 | 9353909.62
SOL Town PKG.220 | PKG#220- IPC3 | 3 | SOL Town PKG.2203 | 1345226.9 | 348202.56 | 896872.19 | 1245074.75
El- Hussein Mosque | Hussein Mos IPC1 | 1 | El- Hussein Mosque1 | 5007440 | 3865320 | 0 | 3865320
Roof-Playa Cluster A,B,C | IPC05TR0088 | 5 | Roof-Playa Cluster A,B,C5 | 234659 | 202651.51 | 0 | 202651.51
Residence 8 ( S07 ) | Inv ( 1 ) S07 | 1 | Residence 8 ( S07 )1 | 1134750 | 1025814 | 0 | 1025814
Olympic Multi – Sports Hall | Olym Finish IPC1 | 1 | Olympic Multi – Sports Hall1 | 6741326 | 5145260 | 0 | 5145260
Seashell Playa 5 Villas | Playa C045- IPC 9 | 9 | Seashell Playa 5 Villas9 | 29477.74 | 10456.56 | 0 | 10456.56
Air Defense College | Air Dev Elic IPC1 | 1 | Air Defense College1 | 79552681 | 14817370 | 51678000 | 66495370
HST Bridges-Sokhna & Mahager | sokhna esc.14+15 |  | HST Bridges-Sokhna & Mahager | 29623249.9 | 26774104.45 | 0 | 26774104.45
Jawhara Palace Restoratio | Gawhara IPC3 | 3 | Jawhara Palace Restoratio3 | 4244400 | 2850324 | 1061100 | 3911424
HST Bridges-Sokhna & Mahager | sokhna esc.14+15 (2) | 2 | HST Bridges-Sokhna & Mahager2 | 5454047.52 | 4500020.22 | 0 | 4500020.22
Roof-Playa Cluster A,B,C | IPC02TR0088 | 2 | Roof-Playa Cluster A,B,C2 | 648565 | 508950.72 | 0 | 508950.72
Jawhar Al-Lala Mosque | Gawhar LALA IPC1 | 1 | Jawhar Al-Lala Mosque1 | 8815759 | 1979890 | 4951647 | 6931537
Sixty Iconic Tower | Inv ( 6 ) sixty | 6 | Sixty Iconic Tower6 | 1434485 | 1338415.9 | 0 | 1338415.9
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 28 | 28 | ORA ZED-Ph 2-Pkgs A&D28 | 2340664.72 | 1922751.71 | 245769.8 | 2168521.51
Olympic MultiSport Hall | IPC02TR0079 | 2 | Olympic MultiSport Hall2 | 9861.6 | 8298.53 | 0 | 8298.53
Faculty of Medicine | Mansora finish ipc19 | 19 | Faculty of Medicine19 | 20526102.86 | 15315146 | 3078915.43 | 18394061.43
Open Channal | IPC04TR0074 | 4 | Open Channal4 | 173568 | 149719.76 | 0 | 149719.76
U4,U8 Seashell Playa | IPC15TR0060 | 15 | U4,U8 Seashell Playa15 | 319683.13 | 156078.35 | 0 | 156078.35
ora zed orascom | IPC05TR0069 | 5 | ora zed orascom5 | 1021612.84 | 734012.43 | 0 | 734012.43
New Giza Teaching Hospital | New Giza Hosp ipc 26 | 26 | New Giza Teaching Hospital26 | 68532450.22 | 16494091.451 | 15936037.38 | 47830128.831
EGAT Mechanical Installations | Egat Mechnical ipc 6 | 6 | EGAT Mechanical Installations6 | 13673922.93 | 10390813.8998 | 3418480.8625 | 13809294.7623
Sokhna Port Expansion | esc.spx1 11+12 |  | Sokhna Port Expansion | 50432113 | 39132293.62 | 0 | 44780293.62
U7-SEASHELL | IPC17TR0064 | 17 | U7-SEASHELL17 | 96073.6 | 78411.52 | 0 | 78411.52
Port Said Port Silos | port said silo ipc24 | 24 | Port Said Port Silos24 | 4764115.24 | 3891455.9996 | 476411.52 | 4367867.5196
Port Said Grain Storage | RENT-006 | 6 | Port Said Grain Storage6 | 150400 | 166267.2 | 0 | 166267.2
MDF Factory | MDF Equip ipc 24 | 24 | MDF Factory24 | 342224.81 | 345289.58 | 0 | 345289.58
Ora Zed Landscape Ph1 | Ora Landscap ipc 16 | 16 | Ora Zed Landscape Ph116 | 1773393.33 | 1521916.4665 | 186206.3 | 1708122.7665
U4,U8 Seashell Playa | IPC16TR0060 | 16 | U4,U8 Seashell Playa16 | 274667.4 | 237202.77 | 0 | 237202.77
Egyptian Exchange building | IPC15TR0039 | 15 | Egyptian Exchange building15 | 618281.6 | 547488.35 | 0 | 547488.35
EGAT Injection | IPC15TR0048 | 15 | EGAT Injection15 | 270868.46 | 232432.23 | 0 | 232432.23
EIPICO C002-23 | IPC10TR0068 | 10 | EIPICO C002-2310 | 88548.1 | 87118.11 | 0 | 87118.11
Jawhara Palace Restoratio | Jawhara IPC4 | 4 | Jawhara Palace Restoratio4 | 1280722.15 | 859800 | 320180.54 | 1179980.54
Abou Ghaleb Bridge | Aboghaleb Esc.1:20 p |  | Abou Ghaleb Bridge | 9228962.71 | 8914781.18 | 0 | 8914781.18
Abou Ghaleb Bridge | ABOGHALEBIPC19+20 | 19 | Abou Ghaleb Bridge19 | 8316366.29 | 7383581.7645 | 0 | 7383581.7645
Olympic Multi – Sports Hall | olympic mic IPC1 | 1 | Olympic Multi – Sports Hall1 | 5172988 | 4565825 | 0 | 4565825
SSC Suez Steel Company Project | In&Re apply ssc ipc7 | 7 | SSC Suez Steel Company Project7 | 1924769.3 | 1886891.062 | 249602.86 | 2136493.922
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 32 | 32 | ORA ZED-Ph 2-Pkgs A&D32 | 2766735.75 | 2836390.6675 | 290507.25 | 3126897.9175
SSC Suez Steel Company Project | V.O SMP1 IPC 1 | 1 | SSC Suez Steel Company Project1 | 18867171.15 | 18678499.436 | 0 | 18678499.436
Mivida BP#189 | Emaar Pkg#189 ipc 27 | 27 | Mivida BP#18927 | 14919836.12 | 4389859.036 | 7016517.49 | 11406376.526
Port Said Port Silos | PORT SAID IPC 30 | 30 | Port Said Port Silos30 | 3191368.24 | 100639.5696 | 319136.82 | 419776.3896
UGC Factory | IPC01TR0100 | 1 | UGC Factory1 | 2989546 | 2810173.24 | 0 | 2810173.24
EIPICO C002-23 | IPC08TR0068 | 8 | EIPICO C002-238 | 72216.7 | 61969.13 | 0 | 61969.13
EIPICO C002-23 | IPC06TR0068 | 6 | EIPICO C002-236 | 187923.2 | 136256.9 | 0 | 136256.9
ora zed orascom | IPC06TR0069 | 6 | ora zed orascom6 | 471168.59 | 430765.86 | 0 | 430765.86
EDNC Retail - SEOUDI MODI | Ednc Saudi ipc 2 | 2 | EDNC Retail - SEOUDI MODI2 | 1783835.43 | 951910.44 | 900626.7 | 1852537.14
R05 (New) | IPC09TR0059 | 9 | R05 (New)9 | 14256 | 10660.52 | 0 | 10660.52
Olympic MultiSport Hall | IPC06TR0079 | 6 | Olympic MultiSport Hall6 | 25956 | 21841.98 | 0 | 21841.98
RADAMIS CITY | IPC03TR0084 | 3 | RADAMIS CITY3 | 328264.64 | 290680.85 | 0 | 290680.85
Al-Parco | INV (11-12 ) ALparco | 11 | Al-Parco11 | 2482854.5 | 506062.79 | 0 | 506062.79
Egyptian Exchange Building | Exch EGY BIM1 |  | Egyptian Exchange Building | 1958660 | 1696720 | 0 | 1696720
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 43 | 43 | ORA ZED - Ph 01B - Pkgs A&D43 | 11538786.67 | 10554454.5368 | 0 | 10554454.5368
RADAMIS CITY | IPC09TR0084 | 9 | RADAMIS CITY9 | 111692.66 | 98903.2 | 0 | 98903.2
EIPICO C002-23 | IPC13TR0068 | 13 | EIPICO C002-2313 | 76962.2 | 66041.27 | 0 | 66041.27
Egyptian Exchange building | IPC17TR0039 | 17 | Egyptian Exchange building17 | 198913.68 | 176138.07 | 0 | 176138.07
EGAT Injection | IPC16TR0048 | 16 | EGAT Injection16 | 1453896.97 | 1247588.98 | 0 | 1247588.98
Katameya Creeks - RME | IPC18TR0053 | 18 | Katameya Creeks - RME18 | 260398.2 | 229632.61 | 0 | 229632.61
Open Channel 2 | IPC02TR0099(01) | 2 | Open Channel 22 | 2440060 | 2086495.82 | 0 | 2086495.82
Abou Ghaleb Bridge | Abo Ghaleb ipc 24 | 24 | Abou Ghaleb Bridge24 | 954963.05 | 851501.28 | 0 | 851501.28
RING ROAD MARYOTIA EXPANSION | El Marg Esc.1:11 fin |  | RING ROAD MARYOTIA EXPANSION | 1247276.95 | 1170796.25 | 0 | 1170796.25
Creeks URBN-K | Urbn-k ipc 6 | 6 | Creeks URBN-K6 | 21266246.93 | 19608846.9472 | 1672033.24 | 21280880.1872
Koumassi Flyover | INV no.11 | 11 | Koumassi Flyover11 | 630376785.33 | 567339106.8 | 0 | 567339106.8
Seashell Playa 5 Villas | Playa c469 ipc 7 | 7 | Seashell Playa 5 Villas7 | 79103.1 | 72268.59 | 0 | 72268.59
ElMoneeb 2 | IPC#06 Moneeb | 6 | ElMoneeb 26 | 759410 | 568314.32 | 0 | 568314.32
EPICO 3 Facility | Eipico ipc 20 | 20 | EPICO 3 Facility20 | 71749002.23 | 62225320.01 | 0 | 62225320.01
Coastal road Bridge Extension | ipc 9 D0051 | 9 | Coastal road Bridge Extension9 | 1242615.5 | 1179338.8 | 0 | 1179338.8
Ahl Misr P3 – Zamalek Sector | IPC#2 Ahl Misr Zamal | 2 | Ahl Misr P3 – Zamalek Sector2 | 511560 | 491934.3 | 0 | 491934.3
Railway Bridge - El Hammam | IPC#2 ElHammam | 2 | Railway Bridge - El Hammam2 | 710698.02 | 668889.36 | 0 | 668889.36
MDF Factory | MDF-Local ipc 20 | 20 | MDF Factory20 | 1480493.38 | 1495298.3132 | 0 | 1495298.3132
Qasr Rashwan Lot A | QASR RASHWAN A IPC 2 | 2 | Qasr Rashwan Lot A2 | 18076035.38 | 22109153.08 | 5979189.16 | 28088342.24
Cairo Monorail - 6th October | IPC#12 Monorail | 12 | Cairo Monorail - 6th October12 | 412800 | 408672 | 0 | 408672
Sohag HSR Station | HSR SOHAG IPC 1 | 1 | Sohag HSR Station1 | 14703480.67 | 7843918.88 | 0 | 13008126.88
W Dam PP Phase II (CP-117) | 17 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 168175.4286 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 240 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Kayan | IPC_3_Rowad_Kayan |  | Al-Kayan | 3145.52 | 0 | 0 | #DIV/0!
Taval Sarai 52 | 1 |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 93 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2105210019 |  | Miscellaneous Projects | 10500 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Cr. Inv. Retent. USD |  | Abo Quir - Badr 500KV | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Cr Soc inv 4-5 Itay | 4 | Beni Seuf - 3584 | 0 | 0 | 0 | #DIV/0!
Lina Farm Substation | Green Power EGP |  | Lina Farm Substation | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | Cr.Social |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
Canal Sugar S/s | Soc.2020 تشيد سكر مح |  | Canal Sugar S/s | 5000 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Inv.35&36 deductions | 35 | South Helwan PP (CP-117)35 | 0 | 0 | 0 | #DIV/0!
Air Defence College | IPC27TR0046// | 27 | Air Defence College27 | 52264.8 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.7 | 7 | Akhmem - Qena7 | 0 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | inv 1.2 d0080 | 1 | Expansion of Ring Road NRCC1 | 344835 | 0 | 0 | #DIV/0!
Kemet Tower | CR inv ( 9 ) Kemt | 9 | Kemet Tower9 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_INV. 9 | 9 | Akhmem Assiut9 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Inv 44 to 47 | 44 | Akhmem Assiut44 | 0 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Inv.16 - Lot 1 Rduc. | 16 | Mauritania Lot 116 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply.Inv.5 Ret | 5 | Ghana Street lighting5 | 22769.29 | 0 | 0 | #DIV/0!
El Sadat City | Sadat City Inv. 02 | 2 | El Sadat City2 | 15265218.98 | 0 | 0 | #DIV/0!
Cameron EDC | 024/2020adj |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Elsewedy Univ - Enabling Works | cr-sewedy uni-mep-07 | 7 | Elsewedy Univ - Enabling Works7 | 0 | 0 | 0 | #DIV/0!
Air Defense College | Air Def Fini5 IPC1 | 1 | Air Defense College1 | 46112467.5 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 245 |  | MAYSAN 400/132kV SS | 0 | 0 | 0 | #DIV/0!
New Capital | ref.2 |  | New Capital | 0 | 0 | 0 | #DIV/0!
UIC Project (LP-04-21) | 63 |  | UIC Project (LP-04-21) | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_INV.6 | 6 | Akhmem - Qena6 | 0 | 0 | 0 | #DIV/0!
Sodic East | crIPC12_sodic_east | 12 | Sodic East12 | 0 | 0 | 0 | #DIV/0!
Ora Zed Landscape Ph1 | CR Ora LandscapeIPC2 | 2 | Ora Zed Landscape Ph12 | 0 | 0 | 0 | #DIV/0!
Royal City | Cr Royal Zone ipc24 | 24 | Royal City24 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR-(10+11) USD-Shaba | 10 | Al-Shabab PP Phase II (CP-117)10 | 0 | 0 | 0 | #DIV/0!
Attaqa Power Plant | reverse |  | Attaqa Power Plant | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | OB.Ret. Cobra500 |  | Abo Quir - Badr 500KV | 24491299.16 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.11 | 11 | Akhmem - Qena11 | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11586 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | IPC 4 Aswan | 4 | Aswan axis - Daraw4 | 431029.25 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 59 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Ins. Inv.4 Ret | 4 | Ghana Street lighting4 | 6106.61 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 07 | 7 | Suez Gulf/S4 - 500KV OHTL7 | 36466.19 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 52 |  | Suez Gulf Substation | 2970926.8992 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 239 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 6 |  | Zafranaa - Beni Suef | 45355.35 | 0 | 0 | #DIV/0!
10th of Ramadan Railway | D0046 OB-Dec-2020/Cr | 2020 | 10th of Ramadan Railway2020 | 0 | 0 | 0 | #DIV/0!
Infra Project 4428 | 220621010 |  | Infra Project 4428 | 133177460.95 | 0 | 0 | #DIV/0!
Elhegaz | D0028-OB-Dec-2020Can | 2020 | Elhegaz2020 | 0 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC#1 | 1 | Maspiro Towers1 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | cr-Inv-01 MOC | 1 | MOC HQ at Diriyah1 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | close billing reclas |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | Reten.OB Zafrasouf |  | Zafranaa - Beni Suef | 1114578.04 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 13 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 12764.38 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 180065 |  | South Helwan PP (CP-117) | 2832.31 | 0 | 0 | #DIV/0!
Benban 4 As El-Nakra 220 K.V | تشيد النقره |  | Benban 4 As El-Nakra 220 K.V | 3651 | 0 | 0 | #DIV/0!
Port Said Grain Storage | Rent 002 |  | Port Said Grain Storage | 79400 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 9 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 98041.3524 | 0 | 0 | #DIV/0!
EGAT ADMIN (Pelletizing) | IPC03TR0094 | 3 | EGAT ADMIN (Pelletizing)3 | 59189.6 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 283 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
UIC Project (LP-04-21) | 61 |  | UIC Project (LP-04-21) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 110 |  | Suez Gulf Substation | -10577962.952 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Inv.20 - Lot 1 | 20 | Mauritania Lot 120 | 58223.2 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | Ref 2 |  | Barwa 2x60/22 KV S/S | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Inv.1 Temmay Cancel | 1 | Beni Seuf - 3581 | 0 | 0 | 0 | #DIV/0!
Tebbin PP Rehabitation(CP-124) | last inv. (4 EGP)113 |  | Tebbin PP Rehabitation(CP-124) | 1970173.27 | 0 | 0 | #DIV/0!
EIPICO Factory | Addition Work IPC07 | 7 | EIPICO Factory7 | 19850 | 0 | 0 | #DIV/0!
Bani Suef Old Substation | cr (23+24) |  | Bani Suef Old Substation | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 1 USD -El Tebein 113 |  | Miscellaneous Projects | 24940 | 0 | 0 | #DIV/0!
Mivida | CR.TR0009CLOSING.DEC |  | Mivida | 0 | 0 | 0 | #DIV/0!
MOTHANA 400/132kV SS | 205 |  | MOTHANA 400/132kV SS | -4216144.83 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 266 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 45 |  | Al-Shabab PP Phase II (CP-117) | 6504806.75 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CrMemo W.hold 12-EGP |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | Egy Ex awnash 2final |  | Egyptian Exchange Building | 7165085.715 | 0 | 0 | 7416455.004
Governmental Campus-N2 | 88 |  | Governmental Campus-N2 | 210662 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | reclass of rec. acco |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Mozambique TL | CR.P-50-12 AccRev | 50 | Mozambique TL50 | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 5 | 5 | Marsa Alam/ Bernes LOT2 OHTL5 | 12519.37 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Stamps inv.38 EGP | 38 | South Helwan PP (CP-117)38 | 0 | 0 | 0 | #DIV/0!
33KV Canal Farm Grid | Inv. 20 Farm | 20 | 33KV Canal Farm Grid20 | 4030952.04 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 15 EGP - Shabab | 15 | Al-Shabab PP Phase II (CP-117)15 | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-118) | DEC10 |  | Banha PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Cairo North PP Rehabilitation | 88 |  | Cairo North PP Rehabilitation | -1726617.7594 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.10 | 10 | Akhmem - Qena10 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Tax 73-74 cobra | 74 | Abo Quir - Badr 500KV74 | 140024.95 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | CR-MOC Inv 04 | 4 | MOC HQ at Diriyah4 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 53 |  | Al-Shabab PP Phase II (CP-117) | 4843098.61 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 10 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 93003.52 | 0 | 0 | #DIV/0!
IRAQ - Al-Diwaniya Power Plant | 2012220007 |  | IRAQ - Al-Diwaniya Power Plant | 0 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 198 |  | MAYSAN 400/132kV SS | -37109.952 | 0 | 0 | #DIV/0!
Military 110 Kayan Project | CR.refund ret. |  | Military 110 Kayan Project | 0 | 0 | 0 | #DIV/0!
Business District Hyde Park | Cr.( 6-9 ) HY Bark | 9 | Business District Hyde Park9 | 0 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 1 |  | MAYSAN 400/132kV SS | 37109.952 | 0 | 0 | #DIV/0!
Playa Resort | 41. |  | Playa Resort | 0 | 0 | 0 | #DIV/0!
Mostakbal 2 Package No. (8) | اتحاد تشيد P-62 | 62 | Mostakbal 2 Package No. (8)62 | 5000 | 0 | 0 | #DIV/0!
Infra Project 4428 | 2112220001 |  | Infra Project 4428 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr. Ins. Abolila |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC005 | 5 | Maspiro Towers5 | 0 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 476 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | Cancel Inv#10 USD VO | 10 | Suez Gulf Substation10 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Part Inv 14 USD Shab | 14 | Al-Shabab PP Phase II (CP-117)14 | 40246.0652 | 0 | 0 | #DIV/0!
El-Warraq | CR IPC3 elwaraq | 3 | El-Warraq3 | -736709.2 | 0 | 0 | #DIV/0!
Katameya Creeks - RME | C..IPC13TR53 | 13 | Katameya Creeks - RME13 | 0 | 0 | 0 | #DIV/0!
Ora Zed Landscape Ph1 | CR ora landscapeIPC9 | 9 | Ora Zed Landscape Ph19 | 0 | 0 | 0 | #DIV/0!
Air Defence College | IPC26TR0046 | 26 | Air Defence College26 | 126903.32 | 0 | 0 | 126903.32
EPICO 3 Facility | Eipico material ipc3 | 3 | EPICO 3 Facility3 | 4676968.58 | 0 | 0 | 4910817.009
EPICO 3 Facility | Material On Site |  | EPICO 3 Facility | 57323484.33 | 0 | 0 | 60189658.5465
KATAMYA GREEKS LAND SCAPE STAR | IPC03TR0081 | 3 | KATAMYA GREEKS LAND SCAPE STAR3 | 1207954.09 | 0 | 0 | 1207954.09
Wadi Halfa Port | wady halfa ipc 5 | 5 | Wadi Halfa Port5 | 5072099.52 | 0 | 0 | 5325704.496
Residence 8 ( S09 ) | Inv ( 1 ) S09 | 1 | Residence 8 ( S09 )1 | 1390620 | 0 | 0 | 1390620
Tarek Abdel-Hakim Center | TAH ipc05 | 5 | Tarek Abdel-Hakim Center5 | 1271012.98 | 0 | 0 | 1271012.98
EIPICO Factory | IPC05TR54 | 5 | EIPICO Factory5 | 6138.09 | 0 | 0 | 6138.09
Al-Parco | INV ( 3 ) ALparco | 3 | Al-Parco3 | 2422608 | 0 | 0 | 2422608
Kemet Tower | inv ( 9 ) Kemt | 9 | Kemet Tower9 | 185120 | 0 | 0 | 185120
Business District Hyde Park | INV ( 4 ) HY Bark | 4 | Business District Hyde Park4 | 624167.75 | 0 | 0 | 624167.75
U3 & U5 | TR55-IPC3 | 3 | U3 & U53 | 34000.72 | 0 | 0 | 34000.72
Playa Resort | kantine 6 |  | Playa Resort | 35000 | 0 | 0 | 35000
Egyptian Exchange building | IPC000010 | 10 | Egyptian Exchange building10 | 85472.01 | 0 | 0 | 85472.01
HST - 6 October - Arab Cont. | IPC 1 HSR ARAB CONST | 1 | HST - 6 October - Arab Cont.1 | 2928500 | 0 | 0 | 2928500
Pridge 5 | inv ( 1 ) pridg 5 | 1 | Pridge 51 | 2100300 | 0 | 0 | 2100300
Infra Project 2531 | 220621004 |  | Infra Project 2531 | 154992519.05 | 0 | 0 | 162742145.0025
Infra Project 4428 | 220321003 |  | Infra Project 4428 | 110196949.52 | 0 | 0 | 115706796.996
Akhmem Assiut | Ref. Akhme Asuit T |  | Akhmem Assiut | 5000000 | 0 | 0 | 5000000
MDF Factory | MDF FACTORY IPC07 | 7 | MDF Factory7 | 15382008.96 | 0 | 0 | 16151109.408
New Babil 400/132KV GIS Substa | 2201210001 |  | New Babil 400/132KV GIS Substa | 2800720.76 | 2240576.61 | 0 | 2800720.76
Containment Data Center- | 36 |  | Containment Data Center- | 46429800 | 14645486 | 4875129 | 21952375.78
Containment Data Center- | 32 |  | Containment Data Center- | 19500516 | 0 | 0 | 19500516
Industria Sadat | Sadat Indust Inv. 03 | 3 | Industria Sadat3 | 10151330.88 | 10107509.75 | 4747538.81 | 15336604.57
Assuit PP (CP-118) | 2105210003 |  | Assuit PP (CP-118) | 96467.1135 | 101544.33 | 0 | 101544.33
Kafr Shokr Bridge | Kafr Shokr-IPC02 | 2 | Kafr Shokr Bridge2 | 7001830.48 | 0 | 0 | 7982086.7472
Ain-Sokhna PP(CP-102) | 2012210039 |  | Ain-Sokhna PP(CP-102) | 161718.62 | 0 | 0 | 161718.62
6th Oct. Ph2 PP-Elect Work | 2012210035 |  | 6th Oct. Ph2 PP-Elect Work | 3001868.6659 | 0 | 0 | 3001868.6659
LRT Project | TR0028DEC.Closing |  | LRT Project | 103200 | 0 | 0 | 103200
Taval Sarai 52 | TR0025DEC.Closing |  | Taval Sarai 52 | 662315.7 | 0 | 0 | 662315.7
Ministry Building EPOXY | TR0018DEC.Closing |  | Ministry Building EPOXY | 129748.87 | 0 | 0 | 129748.87
Taval Sarai 52 | IPC_5_Gama_Saray |  | Taval Sarai 52 | 251219 | 0 | 0 | 251219
Maspiro Towers | D0019-OB-Dec-2020 | 2020 | Maspiro Towers2020 | 3479650 | 0 | 0 | 3479650
HAC CCC JV | D0008-OB-Dec-2020 | 2020 | HAC CCC JV2020 | 11272720.57 | 0 | 0 | 11272720.57
Bahr El Baqar Treatment Plant | D0036-OB-Dec-2020 | 2020 | Bahr El Baqar Treatment Plant2020 | 1212810.3 | 0 | 0 | 1212810.3
South Helwan PP (CP-117) | 2009210006 |  | South Helwan PP (CP-117) | 239840.14 | 211966.82 | 37845.88 | 249812.7
Assuit PP (CP-118) | 2009210002 |  | Assuit PP (CP-118) | 2536557.0286 | 2238502.52 | 399507.73 | 2638010.25
Beni Suef Add-on Sales | 2005210009 |  | Beni Suef Add-on Sales | -1267421.32 | 0 | 0 | -1267421.32
Giza North PP Ph I,II (CP-117) | 2001210013 |  | Giza North PP Ph I,II (CP-117) | 9538.75 | 9538.75 | 0 | 9538.75
Baron Palace | 10035 |  | Baron Palace | 13094.4 | 0 | 0 | 13094.4
Manshiet Nasser Substation | 544 |  | Manshiet Nasser Substation | 258532.38 | 235887.19 | 0 | 235887.19
Manshiet Nasser Substation | 1907210015 |  | Manshiet Nasser Substation | 1226665.08 | 1105695.54 | 198545.2 | 1304240.74
LAYYAH CCPP | 472 |  | LAYYAH CCPP | 10283760 | 0 | 0 | 10283760
Benban 4 As El-Nakra 220 K.V | Inv. 1 Final ElNokra | 1 | Benban 4 As El-Nakra 220 K.V1 | 6953627.16 | 0 | 0 | 6953627.16
Suez Gulf Substation | 20 EGP TOAC Main |  | Suez Gulf Substation | 3168848.91 | 3000195 | 333355 | 3333550
Zafranaa - Ras Ghareb | Amend - Ras Ghareb |  | Zafranaa - Ras Ghareb | -3460.5 | 0 | 0 | -3460.5
Manshiet Nasser Substation | 1901210016 |  | Manshiet Nasser Substation | 640004.93 | 600084.62 | 65520.51 | 665605.13
Suez Gulf Substation | 1909210006 |  | Suez Gulf Substation | 64220.18 | 64220.18 | 0 | 64220.18
Suez Gulf Substation | 1909210001 |  | Suez Gulf Substation | 1500870.19 | 1578878 | 0 | 1578878
Zambia Project | SCD4/002 |  | Zambia Project | 78921.47 | 0 | 0 | 78921.47
AWEER POWER STATION 'H' Phase | 10167 |  | AWEER POWER STATION 'H' Phase | 211328.6 | 0 | 0 | 221895.03
Beni Suef ISKRA | 1907210008 |  | Beni Suef ISKRA | 369202415.3024 | 0 | 0 | 369202415.3024
Banha PP (CP-117) | 180135 |  | Banha PP (CP-117) | 5837.5 | 6111.71 | 0 | 6111.71
Beni-Suef Power Plant EPC | 180119 |  | Beni-Suef Power Plant EPC | 497965535.18 | 497965535.18 | 0 | 497965535.18
Ain-Sokhna PP (CP-117) | 180136 |  | Ain-Sokhna PP (CP-117) | 4785.53 | 5000.88 | 0 | 5000.88
Akhmem Assiut | Soc In 49 Asuit |  | Akhmem Assiut | 48705.75 | 0 | 0 | 48705.75
Al-Shabab PP Phase II (CP-117) | 180107 |  | Al-Shabab PP Phase II (CP-117) | 696722.97 | 622994.9 | 109940.28 | 732935.18
Al-Shabab PP Phase II (CP-117) | 27 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 32388.8762 | 28907.07 | 5101.25 | 34008.32
Elniger | 5004 ADJ |  | Elniger | 32830869.85 | 0 | 0 | 32830869.85
W Dam PP Phase II (CP-117) | 16 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 113117.95 | 0 | 0 | 113117.95
Suez Gulf Substation | 16 USD - Suez Gulf |  | Suez Gulf Substation | 704911 | 614419.9 | 70491.1 | 684911
W Dam PP Phase II (CP-117) | 19 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 370511.34 | 370511.34 | 0 | 370511.34
Lina Farm Substation | 7 EGP - Lina |  | Lina Farm Substation | 853142.14 | 853142.14 | 0 | 853142.14
Abou El Matameer and Sammanoud | 13-12-2018 | 12 | Abou El Matameer and Sammanoud12 | 4186152.58 | 0 | 0 | 4186152.58
South Helwan PP (CP-117) | SH Inv.35&36 comm | 35 | South Helwan PP (CP-117)35 | 21317.45 | 21317.45 | 0 | 21317.45
Marsa Matrouh 500KV | Inv, 4 usd Borg Arab | 4 | Marsa Matrouh 500KV4 | 1342780.82 | 0 | 0 | 1342780.82
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 05 |  | Giza North PP Ph I,II (CP-117) | 362626.33 | 362626.33 | 0 | 362626.33
Berket Ghelion | Adj Inv 7 | 7 | Berket Ghelion7 | 38242338.08 | 0 | 0 | 38242338.08
PIP Zona 2 | Adj inv 1 | 1 | PIP Zona 21 | 35598824.34 | 0 | 0 | 35598824.34
Mahmoudia Power Plant | 121 |  | Mahmoudia Power Plant | -1796304922.0321 | 0 | 0 | -1796304922.0321
Tebbin PP Rehabitation(CP-124) | 91 |  | Tebbin PP Rehabitation(CP-124) | 7260610.64 | 0 | 0 | 7260610.64
Cairo North PP Rehabilitation | 87 |  | Cairo North PP Rehabilitation | 1434708.9941 | 0 | 0 | 1434708.9941
KSA - PP-12 | 123 |  | KSA - PP-12 | 31773079.5235 | 0 | 0 | 31773079.5235
Attaqa Power Plant | 15 |  | Attaqa Power Plant | 2694458200 | 0 | 0 | 2694458200
Attaqa Power Plant | 118 |  | Attaqa Power Plant | 4536718951.9679 | 0 | 0 | 4536718951.9679
IRAQ - Substations Soil Invest | 36 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
IRAQ - Substations Soil Invest | 116 |  | IRAQ - Substations Soil Invest | 4177500 | 0 | 0 | 4177500
GPC-Gupco (Automation) | 12 |  | GPC-Gupco (Automation) | 1420317 | 0 | 0 | 1420317
Beni-Suef PP Site Preparation | 104 |  | Beni-Suef PP Site Preparation | 141694313.7565 | 0 | 0 | 141694313.7565
Banha PP (CP-117) | 71 |  | Banha PP (CP-117) | 30941490.9995 | 0 | 0 | 30941490.9995
South Helwan PP (CP-117) | 108 |  | South Helwan PP (CP-117) | 6765880.53 | 0 | 0 | 6765880.53
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 01 |  | Giza North PP Ph I,II (CP-117) | 23371.75 | 23371.75 | 0 | 23371.75
Lina Farm Substation | 5 EGP - Lina |  | Lina Farm Substation | 1337130.24 | 1337130.24 | 0 | 1337130.24
Attaqa Power Plant | Discount USD Reverse |  | Attaqa Power Plant | 2038853.32 | 2038853.32 | 0 | 2038853.32
Attaqa Power Plant | close interest |  | Attaqa Power Plant | 2038853.32 | 2038853.32 | 0 | 2038853.32
Attaqa Power Plant | close discointerests |  | Attaqa Power Plant | 2038853.32 | 2038853.32 | 0 | 2038853.32
New Heliopolis | Inv.8 Heliopolis | 8 | New Heliopolis8 | 5936553.33 | 0 | 0 | 5936553.33
Akhmem - Qena | Inv. 7 Akhmem Qena | 7 | Akhmem - Qena7 | 45444956.05 | 0 | 0 | 45444956.05
Akhmem Assiut | inv. 9 Assuit Akhmem | 9 | Akhmem Assiut9 | 30032833.14 | 0 | 0 | 30032833.14
Akhmem Assiut | inv. 7 Assuit Akhmem | 7 | Akhmem Assiut7 | 2463575.15 | 0 | 0 | 2463575.15
Pyramids Industrial Park | Ret.Inv.4 PIP West | 4 | Pyramids Industrial Park4 | 4975053.05 | 0 | 0 | 4646549.86
Pyramids Industrial Park | Inv.3 PIP West | 3 | Pyramids Industrial Park3 | 5283083.53 | 0 | 0 | 4966098.52
Pyramids Industrial Park | 18/1 |  | Pyramids Industrial Park | 755365.83 | 0 | 0 | 30000.01
Barwa 2x60/22 KV S/S | 1 |  | Barwa 2x60/22 KV S/S | 1000 | 0 | 0 | 1000
EMAAR-PKG#62-UPTOWN | Amend VAT PKG#62(1) | 1 | EMAAR-PKG#62-UPTOWN1 | 55761.79 | 0 | 0 | 55761.79
Suez Gulf Substation | 4 EGP - Suez Gulf |  | Suez Gulf Substation | 853245.26 | 0 | 86348.42 | 863484.2031
Suez Gulf Substation | 9 USD - Suez Gulf |  | Suez Gulf Substation | 130549.7 | 0 | 13054.97 | 130549.7
Al-Shabab PP Phase II (CP-117) | 7 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 1994601.61 | 0 | 0 | 2094331.6905
Suez Gulf Substation | 8 USD/123/2011/2012 |  | Suez Gulf Substation | 38468 | 0 | 0 | 38468
Suez Gulf Substation | 10 USD - Suez Gulf |  | Suez Gulf Substation | 2063047.78 | 0 | 206304.78 | 2063047.78
West Damietta PP Phase I | 40 |  | West Damietta PP Phase I | 9072886 | 0 | 0 | 18145772
Algeria S/Ss | M-D-003 | 3 | Algeria S/Ss3 | 2824154.24 | 2541738.82 | 0 | 2541738.82
Kuwait | Erection/H001 |  | Kuwait | 57389.81 | 37303.38 | 0 | 37303.38
Kuwait | 29-132KVA-H | 132 | Kuwait132 | 559622.7 | 363754.75 | 0 | 363754.75
W Dam PP Phase II (CP-117) | 180035 |  | W Dam PP Phase II (CP-117) | 94997.1048 | 0 | 0 | 99746.96
Al-Shabab PP Phase II (CP-117) | 180025 |  | Al-Shabab PP Phase II (CP-117) | 144094.5714 | 0 | 0 | 151299.3
W Dam PP Phase II (CP-117) | 24 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 134928.7048 | 120423.87 | 21251.27 | 141675.14
Al-Shabab PP Phase II (CP-117) | 20 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 43165.1619 | 0 | 6798.52 | 6798.52
W Dam PP Phase II (CP-117) | 14 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 236760.7905 | 0 | 37289.82 | 37289.82
W Dam PP Phase II (CP-117) | 2002210029 |  | W Dam PP Phase II (CP-117) | 1378109.92 | 1362246.19 | 87491.06 | 1449737.25
Al-Shabab PP Phase II (CP-117) | 11 USD -Shabab |  | Al-Shabab PP Phase II (CP-117) | 4623986.05 | 4134670.27 | 729647.7 | 4864317.97
Al-Shabab PP Phase II (CP-117) | 11 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 434762.5333 | 0 | 0 | 68475.1
Al-Shabab PP Phase II (CP-117) | 6 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 3046336.89 | 0 | 456950.53 | 3198653.7345
Al-Shabab PP Phase II (CP-117) | 4 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 434081.1364 | 0 | 65893.52 | 439290.11
Al-Shabab PP Phase II (CP-117) | 2 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 5630200.6621 | 0 | 854664.46 | 5697763.07
IRAQ - Substations Soil Invest | 5 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
Suez Gulf Substation | Inv 2 EGP VO SG | 2 | Suez Gulf Substation2 | 107072.2476 | 101183.27 | 11242.59 | 112425.86
Suez Gulf Substation | 5EGP rema Tax Balanc |  | Suez Gulf Substation | 100898.24 | 24104.13 | 76794.11 | 100898.24
Suez Gulf Substation | 3 EGP - Suez Gulf |  | Suez Gulf Substation | 3697395.95 | 0 | 374176.47 | 3741764.7014
Suez Gulf Substation | 7 USD/123/2011/2012 |  | Suez Gulf Substation | 565715.37 | 0 | 0 | 565715.37
Siemens 6x500/220 KV GIS-MOU | Inv 67 P8 Assuit | 67 | Siemens 6x500/220 KV GIS-MOU67 | 3458421.51 | 2501822.12 | 518763.23 | 3020585.35
Siemens 6x500/220 KV GIS-MOU | inv 44 P11El Natroun | 44 | Siemens 6x500/220 KV GIS-MOU44 | 2586656.06 | 1871186.99 | 387998.41 | 2259185.4
Damac 2x60/22 KV S/S | Inv. 33 Damac | 33 | Damac 2x60/22 KV S/S33 | 514651.22 | 364082.81 | 77197.67 | 441280.48
Damac 2x60/22 KV S/S | Inv 20 Damac | 20 | Damac 2x60/22 KV S/S20 | 1067206.57 | 754829.17 | 160081.01 | 914910.18
South Helwan PP (CP-117) | 8 EGP South Helwan |  | South Helwan PP (CP-117) | 185480.3714 | 194754.39 | 0 | 194754.39
Abu Qir PP (CP-118) | 449 Euro - Avice |  | Abu Qir PP (CP-118) | 257674.92 | 243948.8495 | 0 | 257674.92
Berket Ghelion | 1 Ghelion |  | Berket Ghelion | 5097870.6 | 3294440.45 | 1274468.9 | 4568909.35
New Capital | Inv 6 Abo Zaabl | 6 | New Capital6 | 168895.238 | 122537.5 | 17734 | 140271.5
PIP- Zonafranca | Inv. 16 Zona franka | 16 | PIP- Zonafranca16 | 15496914.06 | 0 | 12620915.75 | 12620915.75
Giza North PP Phase3(CP-117) | 40 EGP-Giza No III |  | Giza North PP Phase3(CP-117) | 20673.1143 | 16815.76 | 4693.13 | 21706.77
Giza North PP Phase3(CP-117) | 38 EGP-Giza N. III |  | Giza North PP Phase3(CP-117) | 5005.7524 | 4467.63 | 788.41 | 5256.04
South Helwan PP (CP-117) | 8 Euro- South Helwan |  | South Helwan PP (CP-117) | 257510.019 | 40557.83 | 0 | 40557.83
Shanghai CO. | 10079 |  | Shanghai CO. | 14140 | 14140 | 0 | 14140
Tamey El-amdeed Substation | TAM-CW-EURO-10 | 10 | Tamey El-amdeed Substation10 | 366629.05 | 0 | 54994.36 | 54994.36
Tamey El-amdeed Substation | TAM-CW-EGP-18 | 18 | Tamey El-amdeed Substation18 | 1445564.75 | 1069717.91 | 216834.71 | 1286552.62
Tamey El-amdeed Substation | TAM-CW-EGP-20 | 20 | Tamey El-amdeed Substation20 | 1522593.91 | 1126719.49 | 228389.09 | 1355108.58
Ismailiya East Substation | ISE-CW-EGP-16 | 16 | Ismailiya East Substation16 | 1655757 | 1225260.18 | 248363.55 | 1473623.73
Tamey El-amdeed Substation | TAM-CW-EGP-15 | 15 | Tamey El-amdeed Substation15 | 3498515.21 | 2588901.26 | 524777.28 | 3113678.54
Tamey El-amdeed Substation | TAM-CW-EURO-05 | 5 | Tamey El-amdeed Substation5 | 949834.91 | 702877.83 | 142475.24 | 845353.07
Beni Suef Substation R61 | 19100026 |  | Beni Suef Substation R61 | 2222634 | 1644749.16 | 333395.1 | 1978144.26
Beni Suef Substation R61 | BSF-CW-EGP-13 | 13 | Beni Suef Substation R6113 | 2287835 | 1692963.19 | 343175.25 | 2036138.44
Al Mostathmreen GIS Substation | MOS-SD-EGP-IPC 25 | 25 | Al Mostathmreen GIS Substation25 | 27165 | 20237.92 | 4074.75 | 24312.67
Al Mostathmreen GIS Substation | 18sd mosstasmreen |  | Al Mostathmreen GIS Substation | 67912 | 50594.24 | 10186.92 | 60781.16
Al Mostathmreen GIS Substation | MOS (3) | 3 | Al Mostathmreen GIS Substation3 | 571620 | 425856.9 | 85743 | 511599.9
Al-Shabab PP Phase II (CP-117) | 20 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 43165.1619 | 0 | 0 | 45323.42
W Dam PP Phase II (CP-117) | 17 EGP -West Domiat |  | W Dam PP Phase II (CP-117) | 6435.43 | 0 | 26487.63 | 26487.63
Al-Shabab PP Phase II (CP-117) | 180111 |  | Al-Shabab PP Phase II (CP-117) | 272851.77 | 243978.27 | 43054.99 | 287033.26
Berket Ghelion | Inv 13 Ghelion | 13 | Berket Ghelion13 | 2633893.65 | 1573622.06 | 658473.41 | 2232095.47
Berket Ghelion | Gheleon 5 |  | Berket Ghelion | 1683956.45 | 1006052.23 | 420989.1 | 1427041.33
Berket Ghelion | 9 |  | Berket Ghelion | 1302086.52 | 777996.67 | 325521.65 | 1103518.32
Berket Ghelion | Gheleon 6 |  | Berket Ghelion | 2204220.59 | 1316967.13 | 551055.1495 | 1868022.2795
EMAAR-PKG#107-MARASSI | (5) pkg#107 | 5 | EMAAR-PKG#107-MARASSI5 | 3207732.59 | 8441515.754 | 1667094.28 | 5054305.017
Giza North PP Phase3(CP-117) | 26 EUR - Giza N. III |  | Giza North PP Phase3(CP-117) | 338411.5429 | 302032.3 | 0 | 302032.3
Giza North PP Ph I,II (CP-117) | 37 EGP-Giza North 1& |  | Giza North PP Ph I,II (CP-117) | 564966.8762 | 593215.22 | 0 | 593215.22
Beni Seuf - 358 | Inv. 17 Oewon Mousa | 17 | Beni Seuf - 35817 | 14506308.05 | 0 | 2494851.9 | 2494851.9
Beni Seuf - 358 | Inv. 13 Oewon Mousa | 13 | Beni Seuf - 35813 | 4049842.32 | 0 | 697384.05 | 697384.05
W Dam PP Phase II (CP-117) | 3 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 1700567.1146 | 437023.56 | 258146.09 | 932288.7
Damac 2x60/22 KV S/S | Inv 21 Damac | 21 | Damac 2x60/22 KV S/S21 | 1280709.49 | 905861.84 | 192106.44 | 1097968.28
Damac 2x60/22 KV S/S | Inv 19 Damac | 19 | Damac 2x60/22 KV S/S19 | 5822687.66 | 4119121.2 | 873403.15 | 4992524.35
Al-Wukair 11 Substation | close un appl sak |  | Al-Wukair 11 Substation | 9492793.9 | 9492793.9 | 0 | 9492793.9
Al-Wukair 11 Substation | Inv 11 Qatar accrual | 11 | Al-Wukair 11 Substation11 | 11877918 | 11877918 | 0 | 11877918
Al-Shabab PP Phase II (CP-117) | 16 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 825100.019 | 305616.11 | 129953.25 | 435569.36
IRAQ - Al-Diwaniya Power Plant | Inv No 65 Dewania | 65 | IRAQ - Al-Diwaniya Power Plant65 | 1113366.44 | 1113366.44 | 0 | 1113366.44
Beni-Suef Power Plant EPC | Beni Swef Inv April |  | Beni-Suef Power Plant EPC | 175000000 | 175000000 | 0 | 175000000
New Giza 2 | (21)new giza 2 | 21 | New Giza 221 | 6348768 | 4635241.34 | 1333241.35 | 5968482.69
Royal City | ROYAL CITY-IPC17 | 17 | Royal City17 | 6172362.54 | 5868379.577 | 2768560.39 | 8636939.967
Attaqa Power Plant | Sand Attaqa May |  | Attaqa Power Plant | 25250000 | 25250000 | 0 | 25250000
ASEC-El Menya | Inv 24 Asec | 24 | ASEC-El Menya24 | 825530.61 | 532467.24 | 247659.18 | 780126.42
Abu Qir PP (CP-118) | Invoices Abo Quer, |  | Abu Qir PP (CP-118) | 796701.63 | 796701.63 | 0 | 796701.63
Banha PP (CP-118) | Banha 118 Invoice |  | Banha PP (CP-118) | 26588.39 | 0 | 0 | 0
South Helwan PP (CP-117) | 1905210007 |  | South Helwan PP (CP-117) | 15678.6 | 14019.48 | 2474.02 | 16493.5
South Helwan PP (CP-117) | 180142 |  | South Helwan PP (CP-117) | 213738.98 | 224848.07 | 0 | 224848.07
Al-Shabab PP Phase II (CP-117) | 180157 |  | Al-Shabab PP Phase II (CP-117) | 11502.34 | 0 | 0 | 12100.17
W Dam PP Phase II (CP-117) | 13 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 48329.6 | 43134.17 | 7611.91 | 50746.08
South Helwan PP (CP-117) | 1906210008 |  | South Helwan PP (CP-117) | 237562.42 | 209953.83 | 37486.46 | 247440.29
South Helwan PP (CP-117) | 180012 |  | South Helwan PP (CP-117) | -2803954.29 | -2507236.47 | -442453.49 | -2949689.96
South Helwan PP (CP-117) | 180010 |  | South Helwan PP (CP-117) | 3254690.99 | 0 | 513578.06 | 513578.06
Apache Electrical Works | Apachi Inv No P.C#17 | 17 | Apache Electrical Works17 | 60976.03 | 60976.03 | 0 | 60976.03
Suez PP (CP-106) | 5 EGP - Suez 106 |  | Suez PP (CP-106) | 947195.5 | 928251.58 | 0 | 928251.58
EMAAR-PKG#53-UPTOWN | OB-SI-PKG#53 |  | EMAAR-PKG#53-UPTOWN | 6555257.77 | 6555257.56 | 0 | 6555257.56
Al Mostathmreen GIS Substation | cw (8) mosstsmren | 8 | Al Mostathmreen GIS Substation8 | 384924 | 286768.31 | 57738.64 | 344506.95
South Helwan PP (CP-117) | 9 Euro-South Helwan |  | South Helwan PP (CP-117) | 1895104.9524 | 1989860.2 | 0 | 1989860.2
South Helwan PP (CP-117) | 8 EuroSouth Helwan |  | South Helwan PP (CP-117) | 229827.69 | 229827.69 | 0 | 229827.69
South Helwan PP (CP-117) | 10 Euro-South Helwan |  | South Helwan PP (CP-117) | 40293.5333 | 42308.21 | 0 | 42308.21
Al Mostathmreen GIS Substation | (9) CW | 9 | Al Mostathmreen GIS Substation9 | 454520 | 338617.23 | 68178.1 | 406795.33
Banha PP (CP-118) | 20 USD - Banha 118 |  | Banha PP (CP-118) | 18951.29 | 18951.29 | 0 | 18951.29
Tebbin PP Rehabitation(CP-124) | 3 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 1081541.48 | 1081541.48 | 0 | 1081541.48
Suez Gulf Substation | 487 |  | Suez Gulf Substation | 43989.39 | 41648.17 | 4627.57 | 46275.74
Al-Wukair 11 Substation | Inv Qatar (13 to 18) |  | Al-Wukair 11 Substation | 4711367.06 | 4711367.06 | 0 | 4711367.06
Al-Wukair 11 Substation | Inv 19 Qatar | 19 | Al-Wukair 11 Substation19 | 721597.55 | 721597.55 | 0 | 721597.55
New Giza 2 | new giza2-ipc 26+ | 26 | New Giza 226 | 1338966.63 | 1405914.9615 | 0 | 1405914.9615
EMAAR-PKG#85-UPTOWN | IPC 01 PKG#85 | 1 | EMAAR-PKG#85-UPTOWN1 | 2036311.19 | 813632.5095 | 850500 | 1664132.5095
Al Mostathmreen GIS Substation | 8sd euro mosstsmreen |  | Al Mostathmreen GIS Substation | 2082255 | 1509634.65 | 312338.37 | 1821973.02
Al Mostathmreen GIS Substation | 4sw mosstsmreen |  | Al Mostathmreen GIS Substation | 2504240 | 1865658.8 | 375636 | 2241294.8
Ismailiya East Substation | 1cw ismailya |  | Ismailiya East Substation | 5586802 | 4162167.49 | 838020.3 | 5000187.79
Ministries Buildings | Allocation IPC10+ | 10 | Ministries Buildings10 | 23464170 | 14358824.53 | 3231139 | 17589963.53
Akhmem Assiut | Inv.45 Assuit Akhmem | 45 | Akhmem Assiut45 | 5322395.74 | 3832124.92 | 798359.36 | 4630484.28
Akhmem Assiut | Inv.39 Assuit Akhmem | 39 | Akhmem Assiut39 | 5268473.53 | 4162094.09 | 790271.03 | 4952365.12
Akhmem Assiut | Inv.38 Assuit Akhmem | 38 | Akhmem Assiut38 | 2186851.82 | 1727084.04 | 328027.77 | 2055111.81
Akhmem - Qena | Inv.43 Qena Akhmem | 43 | Akhmem - Qena43 | 9120685.97 | 6338876.74 | 1368102.9 | 7706979.64
Akhmem - Qena | Inv. 2 Akhmem Qena | 2 | Akhmem - Qena2 | 18072311.52 | 10753025.3375 | 2710846.73 | 13463872.0675
Al-Shabab PP Phase II (CP-117) | 14 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1073779.3048 | 718392.43 | 126775.13 | 845167.56
W Dam PP Phase II (CP-117) | refund CSI |  | W Dam PP Phase II (CP-117) | 4940.27 | 4940.27 | 0 | 4940.27
Ghana | 34/P/10/ER/2017/USD |  | Ghana | 430731.22 | 430716.72 | 0 | 430716.72
Abou El Matameer and Sammanoud | Inv 88 P7 Sammound | 88 | Abou El Matameer and Sammanoud88 | 4187340.43 | 3029122.07 | 628101.07 | 3657223.14
Abou El Matameer and Sammanoud | Inv 74 P2 Sammound | 74 | Abou El Matameer and Sammanoud74 | 16166738.95 | 11695018.96 | 2425010.84 | 14120029.8
Siemens 6x500/220 KV GIS-MOU | Ret. Banh refund |  | Siemens 6x500/220 KV GIS-MOU | 3779078.8 | 3779078.8 | 0 | 3779078.8
Badr | Inv. 17 Badr | 17 | Badr17 | 7183281.24 | 5333175.13 | 1077492.19 | 6410667.32
Badr | Inv. 16 Badr | 16 | Badr16 | 7449098.4 | 5530955.56 | 1117364.76 | 6648320.32
Badr | Inv. 15 Badr | 15 | Badr15 | 26672144 | 19804066.92 | 4000821.6 | 23804888.52
Barwa and Damac 220 OHTL | Inv No4 Wattanya220 | 4 | Barwa and Damac 220 OHTL4 | 5491423.39 | 3178530.8 | 823713.54 | 4002244.34
Suez Gulf Substation | 180087 |  | Suez Gulf Substation | 5242.42 | 4963.41 | 551.49 | 5514.9
Suez Gulf Substation | 180052 |  | Suez Gulf Substation | 273875.83 | 259299.49 | 28811.05 | 288110.54
Siemens 6x500/220 KV GIS-MOU | ref.reten wadi elnat |  | Siemens 6x500/220 KV GIS-MOU | 5115619.9 | 5115619.9 | 0 | 5115619.9
Al Mostathmreen GIS Substation | 23sd elmostsmrin |  | Al Mostathmreen GIS Substation | 666790 | 496758.55 | 100018.5 | 596777.05
Abou El Matameer and Sammanoud | Inv 75 P4Abo Matamir | 75 | Abou El Matameer and Sammanoud75 | 3887553.2 | 2812255.98 | 583132.98 | 3395388.96
Beni Seuf - 358 | Itay inv.4 -358- | 4 | Beni Seuf - 3584 | 37404136.65 | 29619797.6 | 5727111.54 | 35346909.14
Military 110 Kayan Project | Elkayan Inv.10 | 10 | Military 110 Kayan Project10 | 37956407.49 | 33595160.8 | 0 | 33595160.8
South Helwan PP (CP-117) | 180059 |  | South Helwan PP (CP-117) | 181627.02 | 162407.03 | 28660.06 | 191067.09
Tamey El-amdeed Substation | (2)cw almansora | 2 | Tamey El-amdeed Substation2 | 5988139.38 | 4460637.4 | 898220.91 | 5358858.31
Sodic Club House | SODIC CLUB-IPC (28) | 28 | Sodic Club House28 | 5110738.79 | 5960049.8995 | 509871.31 | 6469921.2095
Beni Seuf - 358 | Soci. Proj.358K.M |  | Beni Seuf - 358 | 12713394.33 | 12699012.67 | 0 | 12699012.67
Assuit PP (CP-118) | 2105210004 |  | Assuit PP (CP-118) | 17216.9925 | 18123.15 | 0 | 18123.15
Assuit PP (CP-118) | 1906210013 |  | Assuit PP (CP-118) | 173545.25 | 154889.13 | 27333.38 | 182222.51
Assuit PP (CP-118) | 1904210004 |  | Assuit PP (CP-118) | 367639.92 | 328118.63 | 57903.29 | 386021.92
Assuit PP (CP-118) | 2007210005 |  | Assuit PP (CP-118) | 2666762.73 | 2353418.12 | 420015.13 | 2773433.25
Assuit PP (CP-118) | 2001210015 |  | Assuit PP (CP-118) | 3840.35 | 3427.51 | 604.86 | 4032.37
Assuit PP (CP-118) | 2005210002 |  | Assuit PP (CP-118) | 278047.9 | 248157.75 | 43792.54 | 291950.29
Assuit PP (CP-118) | 1908210002 |  | Assuit PP (CP-118) | 191141.48 | 170593.77 | 30104.78 | 200698.55
Marsa Matrouh 500KV | Inv.64 Borg Alarab | 64 | Marsa Matrouh 500KV64 | 16170508.44 | 11578082.6 | 1697903.39 | 13275985.99
Marsa Matrouh 500KV | Inv.45 Borg Alarab | 45 | Marsa Matrouh 500KV45 | 3559594.29 | 3109304.96 | 373757.4 | 3483062.36
Marsa Matrouh 500KV | Inv.38 Borg Alarab | 38 | Marsa Matrouh 500KV38 | 25694937.82 | 18397577.91 | 2697968.47 | 21095546.38
Marsa Matrouh 500KV | Inv.5 Usd borg alarb | 5 | Marsa Matrouh 500KV5 | 1316451.44 | 911498.9551 | 138227.4 | 1049726.3551
El Amal Bridge | ALAMAL BRIDGE- FINAL |  | El Amal Bridge | 10084716.7 | 6785022.95 | 0 | 9539124.95
Lina Farm Substation | 3 EGP - Lina |  | Lina Farm Substation | 1347809.11 | 1347809.11 | 0 | 1347809.11
Cairo Capital S1 | C.R 1-2% | 2 | Cairo Capital S12 | 0 | 0 | 0 | 0
New Heliopolis | Heliopolise 6 |  | New Heliopolis | 18174477.52 | 14524441.85 | 1784733.74 | 16309175.59
MAYSAN 400/132kV SS | 199 |  | MAYSAN 400/132kV SS | 98778.12 | 98778.12 | 0 | 98778.12
Apache Electrical Works | Apachi Inv No PC.#28 |  | Apache Electrical Works | 50471.54 | 50471.54 | 0 | 50471.54
Cairo Capital S1 | Inv. 4 Project S 1 | 4 | Cairo Capital S14 | 413660683.46 | 311279259.7 | 62049102.52 | 373328362.22
South Helwan PP (CP-117) | 180126 |  | South Helwan PP (CP-117) | 187204.53 | 196934.5 | 0 | 196934.5
South Helwan PP (CP-117) | 180122 |  | South Helwan PP (CP-117) | 127880.98 | 134527.6 | 0 | 134527.6
New Heliopolis | Inv.7. Heliopolis | 7 | New Heliopolis7 | 9286928 | 7420621.5 | 911976.35 | 8332597.85
Beni Suef Substation R61 | 18100068 |  | Beni Suef Substation R61 | 271650 | 202379.25 | 40747.5 | 243126.75
Beni Suef Substation R61 | BSF-SW-IPC3 | 3 | Beni Suef Substation R613 | 1063125 | 792028.12 | 159468.75 | 951496.87
Royal City | IPC9-ROYAL CITY | 9 | Royal City9 | 7480024.23 | 8085844.5015 | 1527570.78 | 9613415.2815
Kuraiamte Lot1&2 | Inv 1 Kuraiamte | 1 | Kuraiamte Lot1&21 | 263157.89 | 242528.11 | 0 | 242528.11
NUCA R05 - Z02 | R5-IPC26 | 26 | NUCA R05 - Z0226 | 16808375.6 | 14141308.65 | 1775540.1 | 15916848.75
NUCA R05 - Z02 | R5 - IPC18 | 18 | NUCA R05 - Z0218 | 28976061.4 | 23864722.8 | 2968175.15 | 26832897.95
Hassan El Mamoun Bridge | امر توريد حسن المأمو |  | Hassan El Mamoun Bridge | 6631000 | 4799695 | 1599903.15 | 6399598.15
Akhmem Assiut | Inv.14 Assuit Akhmem | 14 | Akhmem Assiut14 | 6852900.15 | 5448055.63 | 1027935.02 | 6475990.65
Tamey El-amdeed Substation | TAM-CW-EURO-01 | 1 | Tamey El-amdeed Substation1 | 583741.07 | 434887.09 | 87561.16 | 522448.25
Suez Gulf Substation | 180089 |  | Suez Gulf Substation | 8156.34 | 7722.24 | 858.03 | 8580.27
Marsa Matrouh 500KV | Inv.5 Borg Alarab | 5 | Marsa Matrouh 500KV5 | 14324722.8 | 14324722.8 | 0 | 14324722.8
Akhmem - Qena | Inv.22 Qena- Akhmem$ | 22 | Akhmem - Qena22 | 125345.85 | 105686.39 | 0 | 105686.39
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC2 | 2 | Elsewedy Univ - Enabling Works2 | 1370079.63 | 881744.3515 | 431575.08 | 1313319.4315
Phosfat | Inv.1 Phosfat | 1 | Phosfat1 | 1181861.15 | 1052493.75 | 0 | 1052493.75
P-28-16 Balat Owinat Lot 2 | Inv. 13 Balat Lot 2 | 13 | P-28-16 Balat Owinat Lot 213 | 11083923.08 | 7104400.21 | 1163811.92 | 8268212.13
New Capital Tunnels | TUNNLE- IPC FINAL |  | New Capital Tunnels | 1188000 | 1118669.8 | 0 | 1118669.8
Akhmem Assiut | So.$4-8:19Assuit | 8 | Akhmem Assiut8 | 10725414 | 10725414 | 0 | 10725414
Akhmem Assiut | Inv.14Assuit Akhmem$ | 14 | Akhmem Assiut14 | 2945516.82 | 2489224.57 | 0 | 2489224.57
NUCA R05 - Z02 | R5 (1) ipc 33 final | 33 | NUCA R05 - Z0233 | 43004105 | 0 | 81448677.66 | 81448677.66
AWEER POWER STATION 'H' Phase | CON/032 |  | AWEER POWER STATION 'H' Phase | 798561.66 | 700959.6754 | 88729.07 | 789688.7454
AWEER POWER STATION 'H' Phase | LOC/024 |  | AWEER POWER STATION 'H' Phase | 669432.45 | 587612.9257 | 74381.38 | 661994.3057
AWEER POWER STATION 'H' Phase | Con-012 Rev0 | 12 | AWEER POWER STATION 'H' Phase12 | 1597123.3 | 1579377.49 | 0 | 1579377.49
AWEER POWER STATION 'H' Phase | 10389 |  | AWEER POWER STATION 'H' Phase | 1148623.04 | 1008235.782 | 127624.78 | 1135860.562
AWEER POWER STATION 'H' Phase | 10371 |  | AWEER POWER STATION 'H' Phase | 1754426.81 | 1189996.8491 | 544936.3214 | 1734933.1705
Marsa Matrouh 500KV | Inv. 5 Borg Alarab | 5 | Marsa Matrouh 500KV5 | 14324722.8 | 12512645.87 | 1504095.89 | 14016741.76
EDNC Retail & Offices Civil | Soreal IPC030 | 30 | EDNC Retail & Offices Civil30 | 27535188.38 | 24351196.859 | 5630.52 | 24356827.379
Al Mostathmreen GIS Substation | MOS-CW-EGP-IPC14 F | 14 | Al Mostathmreen GIS Substation14 | 5028521.25 | 3753066.3 | 754278.26 | 4507344.56
Military 110 Kayan Project | Refund Retention K |  | Military 110 Kayan Project | 19499892 | 19499892 | 0 | 19499892
DPW Onshore Port & Terminal | DP WORLD - IPC14 | 14 | DPW Onshore Port & Terminal14 | 141052143.07 | 104378585.87 | 21157821.46 | 125536407.33
Elsewedy Univ - Enabling Works | ELSWEDYUNI-MEP-IPC07 | 7 | Elsewedy Univ - Enabling Works7 | 4929812 | 2278076.58 | 1035260.52 | 3313337.1
Elsewedy Univ - Enabling Works | ELSWEDYUNI-F&M-IPC04 | 4 | Elsewedy Univ - Enabling Works4 | 2548899.1 | 1785482.76 | 1253062.6 | 3038545.36
Elsewedy Univ - Enabling Works | uni-fin&mep-ipc09 | 9 | Elsewedy Univ - Enabling Works9 | 43369350.27 | 19287810.0535 | 10318111.12 | 29605921.1735
Badr | Inv. 8 Badr | 8 | Badr8 | 18293266 | 13582332.05 | 2743989.9 | 16326321.95
EMAAR-PKG117- MARASSI | PKG#117- IPC 09 | 9 | EMAAR-PKG117- MARASSI9 | 3150407.65 | 2971025.94 | 327732.45 | 3298758.39
Manshiet Nasser Substation | 1907210014 |  | Manshiet Nasser Substation | 1176546.89 | 1055886.42 | 189363.93 | 1245250.35
Manshiet Nasser Substation | 180176 |  | Manshiet Nasser Substation | 112126.2 | 95307.27 | 16818.93 | 112126.2
Manshiet Nasser Substation | 516 |  | Manshiet Nasser Substation | 12761.25 | 7059.53 | 1914.19 | 8973.72
El Mostakbal City Project | Inv. 1 Mostakbal | 1 | El Mostakbal City Project1 | 59088562.35 | 49042372.38 | 12408598.09 | 61450970.47
Fish Market | SOUQ ELSAMAK-PO01 |  | Fish Market | 13284991.95 | 9151350 | 3050451.2 | 12201801.2
Elsewedy Univ - Enabling Works | UNI-FIN&MEP-IPC1 | 1 | Elsewedy Univ - Enabling Works1 | 1805053.36 | 1727255.568 | 0 | 1727255.568
SHAT Al ARAB 400/132kV SS | 224 |  | SHAT Al ARAB 400/132kV SS | 181470.42 | 181470.42 | 0 | 181470.42
SHATRA 400/132kV SS | 219 |  | SHATRA 400/132kV SS | 482066.18 | 482066.18 | 0 | 482066.18
Manshiet Nasser Substation | 1901210018 |  | Manshiet Nasser Substation | 1010008.2 | 1050408.53 | 0 | 1050408.53
Kayan 3 New Cairo Capital City | KAYAN FINSH1-IPC08 | 8 | Kayan 3 New Cairo Capital City8 | 53003261.27 | 13840715 | 49707094.9 | 64025572.75
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 32 | 32 | Benban 500 K.V/95 K.M32 | 3122671.24 | 2407579.56 | 327880.48 | 2735460.04
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 31 | 31 | Benban 500 K.V/95 K.M31 | 396624.49 | 305212.96 | 41645.57 | 346858.53
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 23 | 23 | Benban 500 K.V/95 K.M23 | 65885.56 | 50799.73 | 6917.98 | 57717.71
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 14 | 14 | Benban 500 K.V/95 K.M14 | 989858.15 | 763182.34 | 103935.11 | 867117.45
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 12 | 12 | Benban 500 K.V/95 K.M12 | 359948.42 | 277522.77 | 37794.58 | 315317.35
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 7 | 7 | Benban 500 K.V/95 K.M7 | 37912946.57 | 29230289.22 | 3980859.39 | 33211148.61
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 3 | 3 | Benban 500 K.V/95 K.M3 | 1353959.24 | 1043905.2 | 142165.72 | 1186070.92
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 28 | 28 | Benban 500 K.V / 100 K.M28 | 83072.66 | 64052.67 | 8722.63 | 72775.3
Kuwait | Supply/J009 |  | Kuwait | 41451.49 | 26943.47 | 0 | 26943.47
Canal Sugar OHTL | Inv.01 Sugar OHTL | 1 | Canal Sugar OHTL1 | 12530046 | 9898736.34 | 1879506.9 | 11778243.24
Canal Sugar S/s | Inv 2 Sugar S/s | 2 | Canal Sugar S/s2 | 5832260.77 | 4607486 | 874839.12 | 5482325.12
Akhmem Assiut | Re.Inst6-7-11-29asui | 7 | Akhmem Assiut7 | 1240250.27 | 1239644.37 | 0 | 1239644.37
Elco Steel 220/33 KV SS | 1904210008 |  | Elco Steel 220/33 KV SS | 1901928.56 | 3994049.98 | 0 | 1997024.99
Elco Steel 220/33 KV SS | 1903210006 |  | Elco Steel 220/33 KV SS | 1678021.52 | 1761922.6 | 0 | 1761922.6
SHAT Al ARAB 400/132kV SS | 237 |  | SHAT Al ARAB 400/132kV SS | 166594.11 | 166594.11 | 0 | 166594.11
Cameron EDC | 017/2019 |  | Cameron EDC | 43120.36 | 43034.16 | 0 | 43034.16
NUCA R05 - Z02 | R05-ZONE02-IPC03 | 3 | NUCA R05 - Z023 | 22465025.75 | 23506061.7675 | 2882241.83 | 26388303.5975
C5 Bridge 2 New Alamein | IPC#4 | 4 | C5 Bridge 2 New Alamein4 | 1105500 | 1072335 | 0 | 1072335
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 6USD | 6 | Benban 500 K.V / 100 K.M6 | 2628048.26 | 2207049.53 | 275945.07 | 2482994.6
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 2USD | 2 | Benban 500 K.V / 100 K.M2 | 137265.81 | 115303.28 | 14412.91 | 129716.19
Benban 500 K.V/95 K.M | Benban Lot2 Inv 2 $ | 2 | Benban 500 K.V/95 K.M2 | 345253.77 | 289914.16 | 36251.65 | 326165.81
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC17 | 17 | EMAAR- Pkg 140-ITP-Mivida17 | 16610857.34 | 11726998.4315 | 1462374.69 | 13189373.1215
Ismailiya East Substation | ISE-CW-EURO-02 | 2 | Ismailiya East Substation2 | 2402322.37 | 1788929.4 | 60858.46 | 1849787.86
Royal City | Center Zone final 24 |  | Royal City | 3252689.52 | 0 | 155227.22 | 155227.22
Royal City | ROYAL CITY2-IPC15 | 15 | Royal City15 | 3135467.3 | 2272705.3583 | 465023.7367 | 2737729.095
New bridge Ismailiya Nefisha | NFISHA BRIDGE-FINAL |  | New bridge Ismailiya Nefisha | 19116412.92 | 11694567.55 | 9103989.25 | 20798556.8
Canal Sugar S/s | Inv 1 + $ Sugar S/s | 1 | Canal Sugar S/s1 | 1000000 | 800000 | 150000 | 950000
Canal Sugar S/s | Inv 1 $ Sugar S/s | 1 | Canal Sugar S/s1 | 2522829.2 | 1983035.07 | 378424.38 | 2361459.45
Elco Steel 220/33 KV SS | 1906210001 |  | Elco Steel 220/33 KV SS | 1474212.24 | 3095845.7 | 0 | 1547922.85
Assuit PP (CP-118) | 1906210015 |  | Assuit PP (CP-118) | 126316.7 | 112737.66 | 19894.88 | 132632.54
SHATRA 400/132kV SS | 244 |  | SHATRA 400/132kV SS | 679747.06 | 679747.06 | 0 | 679747.06
Badr | Inv. 14 Badr | 14 | Badr14 | 4102122.6 | 3045406.1 | 615318.39 | 3660724.49
SHAT Al ARAB 400/132kV SS | 251 |  | SHAT Al ARAB 400/132kV SS | 45835.53 | 45835.53 | 0 | 45835.53
SHATRA 400/132kV SS | 252 |  | SHATRA 400/132kV SS | 638589.44 | 638589.44 | 0 | 638589.44
MOTHANA 400/132kV SS | 259 |  | MOTHANA 400/132kV SS | 1994813.66 | 1994813.66 | 0 | 1994813.66
New Capital Tunnels | M.Z TUNNLE-FINAL |  | New Capital Tunnels | 16934976.78 | 24267384 | 8100000 | 32367384
Latin Compound - New Alamin | inv ( 15 ) 1-12-2020 | 15 | Latin Compound - New Alamin15 | 684160.4 | 472070.68 | 136832.08 | 608902.76
AWEER POWER STATION 'H' Phase | 10188 |  | AWEER POWER STATION 'H' Phase | 33075247.752 | 29032717.47 | 3675027.528 | 32707744.998
AWEER POWER STATION 'H' Phase | 10133 |  | AWEER POWER STATION 'H' Phase | 241518.4 | 253594.32 | 0 | 253594.32
AWEER POWER STATION 'H' Phase | 10134 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
AWEER POWER STATION 'H' Phase | 10128 |  | AWEER POWER STATION 'H' Phase | 734401.79 | 644641.5695 | 81600.2 | 726241.7695
LAYYAH CCPP | 511 |  | LAYYAH CCPP | 4935294 | 4194999.9 | 740294.1 | 4935294
LAYYAH CCPP | 491 |  | LAYYAH CCPP | 2467647 | 2097499.95 | 370147.05 | 2467647
LAYYAH CCPP | OF/MP-04 | 4 | LAYYAH CCPP4 | 1233824 | 0 | 1233809.78 | 1233809.78
DoubleTree Mangroovy ElGouna | MANGROVY-IPC11 | 11 | DoubleTree Mangroovy ElGouna11 | 2596008.28 | 1750027.305 | 681452.17 | 2431479.475
DoubleTree Mangroovy ElGouna | mangrove-IPC04 | 4 | DoubleTree Mangroovy ElGouna4 | 3743616.44 | 2572404.492 | 982699.32 | 3555103.812
Marsa Matrouh 500KV | Inv.33 Borg Alarab | 33 | Marsa Matrouh 500KV33 | 176638.1 | 154293.13 | 18547 | 172840.13
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC11 | 11 | EMAAR-PKG# 101-UPTOWN11 | 3104755.66 | 1976416.883 | 888764.73 | 2865181.613
AWEER POWER STATION 'H' Phase | 10106 |  | AWEER POWER STATION 'H' Phase | 2395684.97 | 2102879.03 | 266187.22 | 2369066.25
SHAT Al ARAB 400/132kV SS | 257 |  | SHAT Al ARAB 400/132kV SS | 205273 | 205273 | 0 | 205273
SHATRA 400/132kV SS | 268 |  | SHATRA 400/132kV SS | 85752.96 | 85752.96 | 0 | 85752.96
Beni Suef Add-on Sales | 1908210013 |  | Beni Suef Add-on Sales | 804160 | 892617.6 | 0 | 892617.6
EDNC Retail & Offices Civil | SOREAL - IPC06 | 6 | EDNC Retail & Offices Civil6 | 38734277.15 | 28614412.9875 | 8134198.2 | 36748611.1875
Port Said | Inv 8 Portsaid.final | 8 | Port Said8 | 2319220.01 | 2090205.9 | 0 | 2090205.9
EMAAR-PKG#53-UPTOWN | PO-PKG#53-IPC03 | 3 | EMAAR-PKG#53-UPTOWN3 | 335238.1 | 293735.625 | 0 | 293735.625
Alamein | ALALAMEN ROAD-IPC02 | 2 | Alamein2 | 7800501.9 | 8545086 | 0 | 8545086
HyperOne Zayed Extension | hyper one- IPC09 | 9 | HyperOne Zayed Extension9 | 2100740 | 9493853 | 525232.57 | 10019085.57
HyperOne Zayed Extension | Hyperone-IPC05 | 5 | HyperOne Zayed Extension5 | 5616447.62 | 3307335 | 1404111.9 | 5989384.521
IKEA Extension MoA | IKEA-IPC01 | 1 | IKEA Extension MoA1 | 2651353 | 4032556.16 | 480066.21 | 4512622.37
Manshiet Nasser Substation | 1907210018 |  | Manshiet Nasser Substation | 14087.45 | 11974.33 | 2113.12 | 14087.45
Benban 500 K.V/95 K.M | Benban Lot2 Inv 11 $ | 11 | Benban 500 K.V/95 K.M11 | 691626.99 | 580966.67 | 72620.83 | 653587.5
Benban 500 K.V/95 K.M | Benban Lot2 Inv 7 $ | 7 | Benban 500 K.V/95 K.M7 | 2980768.71 | 2503845.71 | 312980.72 | 2816826.43
4 SS - Technical Service | 284 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
MAYSAN 400/132kV SS | 278 |  | MAYSAN 400/132kV SS | 366953.06 | 366953.06 | 0 | 366953.06
LAYYAH CCPP | 494 |  | LAYYAH CCPP | 6538440 | 5387963.1 | 1429318 | 6817281.1
Ghana Street lighting | inv 5 Ghana | 5 | Ghana Street lighting5 | 58117.7 | 58117.7 | 0 | 58117.7
AWEER POWER STATION 'H' Phase | 10189 |  | AWEER POWER STATION 'H' Phase | 271708.2 | 285293.61 | 0 | 285293.61
EMAAR- Pkg 140-ITP-Mivida | pkg#140 - ipc 05 | 5 | EMAAR- Pkg 140-ITP-Mivida5 | 1994559.84 | 1337507.07 | 508557.79 | 1846064.86
Suez Gulf Substation | 18 EGP Shipping Main |  | Suez Gulf Substation | 110445.58 | 104567.4 | 11618.6 | 116186
Suez Gulf Substation | 13 EGP - Suez Gulf |  | Suez Gulf Substation | 1150418 | 1087145.01 | 120793.89 | 1207938.9
NUCA R05 - Z02 | R5 ZONE2-IPC09 | 9 | NUCA R05 - Z029 | 22914593.8 | 21320239.56 | 2629597.49 | 23949837.05
Alamein | ALAMEEN SUPPLY-IPC02 | 2 | Alamein2 | 8700060 | 8403859 | 0 | 8403859
AWEER POWER STATION 'H' Phase | 10248 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
SHATRA 400/132kV SS | 283 |  | SHATRA 400/132kV SS | 862182.06 | 862182.06 | 0 | 862182.06
MAYSAN 400/132kV SS | 287 |  | MAYSAN 400/132kV SS | 682124.94 | 682124.94 | 0 | 682124.94
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 13 | 13 | Benban 500 K.V / 100 K.M13 | 89987.1 | 69382.92 | 9448.65 | 78831.57
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 22 | 22 | Benban 500 K.V/95 K.M22 | 4266234.77 | 3289272.12 | 447954.65 | 3737226.77
Suez Gulf Substation | 484 |  | Suez Gulf Substation | 46341.4 | 43875 | 4875 | 48750
Suez Gulf Substation | 483 |  | Suez Gulf Substation | 2782.01 | 2633.94 | 292.66 | 2926.6
Elco Steel 220/33 KV SS | 529 |  | Elco Steel 220/33 KV SS | 86762.1 | 91100.2 | 0 | 91100.2
AWEER POWER STATION 'H' Phase | 10329 |  | AWEER POWER STATION 'H' Phase | 535245.65 | 469826.73 | 59471.74 | 529298.47
EMAAR-PKG117- MARASSI | PKG#117-IPC13 | 13 | EMAAR-PKG117- MARASSI13 | 2573072.88 | 3439963.734 | 0 | 3439963.734
Manshiet Nasser Substation | 1902210005 |  | Manshiet Nasser Substation | 1427239.89 | 1326976.29 | 157353.2 | 1484329.49
Elco Steel 220/33 KV SS | 1908210007 |  | Elco Steel 220/33 KV SS | 836902.86 | 878748 | 0 | 878748
Elco Steel 220/33 KV SS | 1904210001 |  | Elco Steel 220/33 KV SS | 392207.96 | 411818.36 | 0 | 411818.36
Elco Steel 220/33 KV SS | 1901210001 |  | Elco Steel 220/33 KV SS | 2636244 | 2636244 | 0 | 2636244
4 SS - Technical Service | 300 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Akhmem - Qena | Inv.24 Qena- Akhmem$ | 24 | Akhmem - Qena24 | 2443255.76 | 1958679.7522 | 0 | 1958679.7522
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 25 | 25 | Benban 500 K.V/95 K.M25 | 14651164.3 | 11295460.8 | 1538372.25 | 12833833.05
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 24 | 24 | Benban 500 K.V / 100 K.M24 | 838750.91 | 646677.7 | 88068.85 | 734746.55
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .17 | 17 | Benban 3/ Toshka 2 LOT 417 | 2453842.55 | 1673125.41 | 257653.47 | 1930778.88
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .7 | 7 | Benban 3/ Toshka 2 LOT 47 | 7683788.62 | 5924202.11 | 806797.81 | 6730999.92
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .2 | 2 | Benban 3/ Toshka 2 LOT 42 | 4605753.15 | 3551036.46 | 483604.08 | 4034640.54
CFC Podium 2 | CFC- IPC04 | 4 | CFC Podium 24 | 35226223.59 | 32660832.57 | 6209770.32 | 38870602.89
Manshiet Nasser Substation | 534 |  | Manshiet Nasser Substation | 304492.05 | 65489.96 | 45673.81 | 111163.77
EMAAR-PKG# 144, Marassi | 20100003 |  | EMAAR-PKG# 144, Marassi | 11410387.23 | 16262789.43 | 0 | 16262789.43
Royal City | ROYAL CENTER-IPC03 | 3 | Royal City3 | 2055285.71 | 2422662.0255 | 171523.97 | 2594185.9955
Ismailiya East Substation | ISE-SW-EGP-07 | 7 | Ismailiya East Substation7 | 564375 | 417637.5 | 84656.25 | 502293.75
Ismailiya East Substation | ISE-SW-EGP-06 | 6 | Ismailiya East Substation6 | 813750 | 602175 | 122062.5 | 724237.5
Manshiet Nasser Substation | 500 |  | Manshiet Nasser Substation | 322603.53 | 322603.53 | 0 | 322603.53
Manshiet Nasser Substation | 489 |  | Manshiet Nasser Substation | 1513677.92 | 1609404.58 | 0 | 1609404.58
Marsa Matrouh 500KV | Inv.49 Borg Alarab | 49 | Marsa Matrouh 500KV49 | 5808093.56 | 5073373.57 | 609849.82 | 5683223.39
AWEER POWER STATION 'H' Phase | 10430 |  | AWEER POWER STATION 'H' Phase | 959258.69 | 842015.9549 | 106584.299 | 948600.2539
LAYYAH CCPP | MP-07 | 7 | LAYYAH CCPP7 | 10283760 | 0 | 10283760 | 10283760
Oasis Buildings- New Capital | Inv(1)131219 | 1 | Oasis Buildings- New Capital1 | 476918.4 | 455241.42 | 0 | 455241.42
El Katameya Mall | inv(2)251119 | 2 | El Katameya Mall2 | 848332.8 | 674811.8 | 0 | 674811.8
Toshka GIS 500 kV | Toshka Sub Inv. 23 $ | 23 | Toshka GIS 500 kV23 | 179449.52 | 102912.1 | 47105.5 | 150017.6
Toshka GIS 500 kV | Toshka Sub Inv. 02 $ | 2 | Toshka GIS 500 kV2 | 133433.33 | 90488 | 35026.25 | 125514.25
kayan wall lock & Load | KAYAN RADM1-FINAL |  | kayan wall lock & Load | 1080000 | 792797 | 721500 | 1514297
Akhmem - Qena | Social Inv.24$Qen 2 | 24 | Akhmem - Qena24 | 1059445 | 1059445 | 0 | 1059445
Akhmem Assiut | Inv.25Assuit Akhmem$ | 25 | Akhmem Assiut25 | 68058.91 | 54002.8082 | 0 | 54002.8082
Manshiet Nasser Substation | 508 |  | Manshiet Nasser Substation | 92079.11 | 22875.65 | 13811.87 | 36687.52
NUCA R05 - Z02 | R5-IPC012 | 12 | NUCA R05 - Z0212 | 26622562.5 | 22980846.275 | 2848719.75 | 25829566.025
Marsa Matrouh 500KV | Inv.22 Borg Alarab | 22 | Marsa Matrouh 500KV22 | 4695452.67 | 4101484.97 | 493022.53 | 4594507.5
Marsa Matrouh 500KV | Inv.14 Borg Alarab | 14 | Marsa Matrouh 500KV14 | 14312845.4 | 12434102.74 | 1502848.77 | 13936951.51
Marsa Matrouh 500KV | Inv.12 Borg Alarab | 12 | Marsa Matrouh 500KV12 | 3453119.23 | 3016303.71 | 362577.52 | 3378881.23
Manshiet Nasser Substation | 532 |  | Manshiet Nasser Substation | 1415891.22 | 1291874.42 | 0 | 1291874.42
Marsa Matrouh 500KV | Inv.61 Borg Alarab | 61 | Marsa Matrouh 500KV61 | 16797557.46 | 14672665.43 | 1763743.53 | 16436408.96
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $2 | 2 | Benban 3/ Toshka 2 LOT 42 | 579518.63 | 486795.64 | 60849.46 | 547645.1
SHATRA 400/132kV SS | 329 |  | SHATRA 400/132kV SS | 789960.33 | 789960.33 | 0 | 789960.33
SHAT Al ARAB 400/132kV SS | 323 |  | SHAT Al ARAB 400/132kV SS | 129313.49 | 129313.49 | 0 | 129313.49
MAYSAN 400/132kV SS | 340 |  | MAYSAN 400/132kV SS | 130535.22 | 130535.22 | 0 | 130535.22
MOTHANA 400/132kV SS | 335 |  | MOTHANA 400/132kV SS | 9.6 | 9.6 | 0 | 9.6
Marsa Matrouh 500KV | Inv.70 Borg Alarab | 70 | Marsa Matrouh 500KV70 | 8198409.53 | 6632044.06 | 0 | 6632044.06
El Katameya Mall | inv(5)250220 | 5 | El Katameya Mall5 | 501354 | 376578.78 | 0 | 376578.78
Alamein | ELALAMEN ROAD-IPC3F | 3 | Alamein3 | 6519021.9 | 6296976 | 0 | 6296976
P-28-16 Balat Owinat Lot 3 | Inv. 14 Balat lot 3 | 14 | P-28-16 Balat Owinat Lot 314 | 16668938.86 | 10784409.09 | 1750238.58 | 12534647.67
Manshiet Nasser Substation | 2003210010 |  | Manshiet Nasser Substation | 1730649.42 | 1730646.22 | 0 | 1730646.22
LAYAN Substation | 10362 |  | LAYAN Substation | 616180.18 | 2082689.04 | 0 | 520672.26
AWEER POWER STATION 'H' Phase | ENG/026 Rev0 |  | AWEER POWER STATION 'H' Phase | 8359233.58 | 8777195.259 | 0 | 8777195.259
MAYSAN 400/132kV SS | 346 |  | MAYSAN 400/132kV SS | 7628130.2 | 7628130.2 | 0 | 7628130.2
New Babil 400/132KV Substation | 2008210005 |  | New Babil 400/132KV Substation | 5200000 | 0 | 5200000 | 5200000
Al-Shabab PP Phase II (CP-117) | 2002210021 |  | Al-Shabab PP Phase II (CP-117) | 18181.2 | 19126.16 | 0.01 | 19126.17
W Dam PP Phase II (CP-117) | 526 |  | W Dam PP Phase II (CP-117) | 15041.7 | 2050.71 | 0 | 2050.71
East Owainat 5 LOTS | East Owainat Inv. 02 | 2 | East Owainat 5 LOTS2 | 106378543.3 | 43557012.68 | 55848735.2 | 99405747.88
Royal City | ROYAL CITY-IPC30 | 30 | Royal City30 | 16056421.67 | 9421690.2835 | 4051126.93 | 13472817.2135
EL-Hegaz Square Bridge | ELHEGAZ BRIDGE-IPC01 | 1 | EL-Hegaz Square Bridge1 | 113016687 | 0 | 56206942.64 | 94350192.64
EDNC Retail & Offices Civil | SOREAL-IPC15 | 15 | EDNC Retail & Offices Civil15 | 19101976.12 | 12895954 | 2540503.47 | 15436457.47
Safir bridge | Claim-01 | 1 | Safir bridge1 | 204725 | 0 | 0 | 204725
marassi inland marina | IPC#1 | 1 | marassi inland marina1 | 2662846.12 | 665711.53 | 0 | 2216391.95
Elco Steel 220/33 KV SS | 2007210007 |  | Elco Steel 220/33 KV SS | 6135.73 | 6442.52 | 0 | 6442.52
Elco Steel 220/33 KV SS | 2007210008 |  | Elco Steel 220/33 KV SS | 196544.45 | 206371.67 | 0 | 206371.67
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.5 | 5 | Nagaa Hamady/Assuit OHTL5 | 7739586.67 | 4055546.71 | 812656.6 | 4868203.31
MOTHANA 400/132kV SS | 355 |  | MOTHANA 400/132kV SS | 2129638.81 | 2129638.81 | 0 | 2129638.81
AWEER POWER STATION 'H' Phase | Con-013 Rev0 | 13 | AWEER POWER STATION 'H' Phase13 | 5110794.6 | 5053945.49 | 0 | 5053945.49
Manshiet Nasser Substation | 2004210011 |  | Manshiet Nasser Substation | 402473.13 | 302441.35 | 64777.61 | 367218.96
Alamein | ELALAMEEN SUPPLAY-03 | 3 | Alamein3 | 5466463 | 5280204 | 0 | 5280204
Marsa Matrouh 500KV | Inv.54 Borg Alarab | 54 | Marsa Matrouh 500KV54 | 26482057.8 | 18695111.68 | 2780616.07 | 21475727.75
NUCA R05 - Z02 | R5 FINSHING-IPC03 | 3 | NUCA R05 - Z023 | 1781134.95 | 1602620.05 | 0 | 1602620.05
ESU Ph2-Enabling & Struc | ESU2-ARCH&MEP-IPC06 | 6 | ESU Ph2-Enabling & Struc6 | 28648432.29 | 8883253.7545 | 9024256.2 | 17907509.9545
marassi inland marina | IPC#3 | 3 | marassi inland marina3 | 663963.54 | 572187.32 | 0 | 572714.25
HyperOne Zayed Extension | HYPER ONE-IPC13 | 13 | HyperOne Zayed Extension13 | 9161231 | 6738702 | 2290307 | 9029009
Racecores 3092-16 132KV C | 11639 |  | Racecores 3092-16 132KV C | 260727.385 | 440629.2685 | 0 | 220314.6343
Royal City | ROYAL ZONE-IPC11 | 11 | Royal City11 | 5193730.04 | 4947910.452 | 1333292.73 | 6281203.182
NUCA R05 - Z02 | R05(2) ipc 39 | 39 | NUCA R05 - Z0239 | 3376069.65 | 3267429.02 | 407101.7 | 3674530.72
NUCA R05 - Z02 | R5(2) ipc25 | 25 | NUCA R05 - Z0225 | 11651556.19 | 10910719.5895 | 1356479.4 | 12267198.9895
NUCA R05 - Z02 | R05(2) ipc24 | 24 | NUCA R05 - Z0224 | 29648308.83 | 25146494.8315 | 3148906.7 | 28295401.5315
NUCA R05 - Z02 | R5(2) ipc(22) | 22 | NUCA R05 - Z0222 | 25000432.9 | 22004708.9 | 2801059.7 | 24805768.6
NUCA R05 - Z02 | R05(2) ipc21 | 21 | NUCA R05 - Z0221 | 26517040.75 | 28326949.3975 | 3491447.6 | 31818396.9975
Ismailiya East Substation | ISE-CW-EGP-26 | 26 | Ismailiya East Substation26 | 315559 | 201880.61 | 0 | 201880.61
Ismailiya East Substation | ISE-CW-EGP-24 | 24 | Ismailiya East Substation24 | 210887 | 187689.43 | 0 | 187689.43
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC08 | 8 | EMAAR-Pkg#162/163- Marassi8 | 12161063.39 | 9432027.7295 | 1207085.04 | 10639112.7695
MOTHANA 400/132kV SS | 369 |  | MOTHANA 400/132kV SS | 826943.05 | 826943.05 | 0 | 826943.05
Toshka Farm | Toshka Farm Inv. 01 | 1 | Toshka Farm1 | 65868984.38 | 27994050.29 | 34581216.8 | 62575267.09
Assuit PP (CP-118) | 2008210001 |  | Assuit PP (CP-118) | 320723.44 | 286245.67 | 50513.94 | 336759.61
marassi inland marina | IPC#6 | 6 | marassi inland marina6 | 1553205.04 | 1333389.29 | 0 | 1411049.54
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .11 | 11 | Benban 3/ Toshka 2 LOT 411 | 1071195.52 | 868744.32 | 112475.53 | 981219.85
Ministries Buildings | MIN-CORE-IPC05 | 5 | Ministries Buildings5 | 21144751.9 | 13360535 | 4453514.44 | 17814049.44
Ministries Buildings | MIN.LAND SCAPE-IPC02 | 2 | Ministries Buildings2 | 4132505.23 | 2590775 | 946244.5 | 3537019.5
Closed | final new giza1 |  | Closed | 6274164 | 4874780.03 | 0 | 4874780.03
Cairo-Alex Railway | Cairo-alex ipc 33 | 33 | Cairo-Alex Railway33 | 7420969.19 | 5153463.7795 | 779201.77 | 5932665.5495
Cairo-Alex Railway | cairo-alex ipc23 | 23 | Cairo-Alex Railway23 | 4053596.4 | 2796823.77 | 425627.62 | 3222451.39
Racecores 3092-17 132KV E | 11502 |  | Racecores 3092-17 132KV E | 328893.9222 | 818945.88 | 0 | 272981.96
Racecores 3092-17 132KV E | 11223 |  | Racecores 3092-17 132KV E | 962159.8537 | 4878150.48 | 0 | 813025.08
Racecores 3092-17 132KV E | 11222 |  | Racecores 3092-17 132KV E | 337466.7771 | 570318.86 | 0 | 285159.43
Racecores 3092-17 132KV E | 11291 |  | Racecores 3092-17 132KV E | 4974582.55 | 33031228.08 | 0 | 4128903.51
Racecores 3092-17 132KV E | 10605 |  | Racecores 3092-17 132KV E | 530278.198 | 1792340.32 | 0 | 448085.08
MOTHANA 400/132kV SS | 373 |  | MOTHANA 400/132kV SS | 4383461.53 | 4383461.53 | 0 | 4383461.53
MAYSAN 400/132kV SS | 364 |  | MAYSAN 400/132kV SS | 1748788.82 | 1748788.82 | 0 | 1748788.82
RING ROAD MARYOTIA EXPANSION | RINING ROAD-IPC02 | 2 | RING ROAD MARYOTIA EXPANSION2 | 7808006.9 | 7164556.359 | 0 | 7164556.359
Miscellaneous Projects | 2010210008 |  | Miscellaneous Projects | 2705.17 | 5410.34 | 0 | 2705.17
Beni Suef Add-on Sales | 2010210006 |  | Beni Suef Add-on Sales | -1049.8 | -1049.8 | 0 | -1049.8
El Katameya Mall | inv ( 16)30-12-2020 | 16 | El Katameya Mall16 | 182000 | 100309 | 0 | 100309
Taval Sarai 52 | IPC_1_Gama_Saraya |  | Taval Sarai 52 | 198511.2 | 140320.0476 | 0 | 140320.0476
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 34 | 34 | ORA ZED - Ph 01B - Pkgs A&D34 | 12357935.4 | 10018963.4932 | 1297583.22 | 11316546.7132
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 30 | 30 | ORA ZED - Ph 01B - Pkgs A&D30 | 24199949.01 | 11085957.6804 | 11540994.65 | 22626952.3304
ORA ZED - Ph 01B - Pkgs A&D | ora ph.1 - ipc 23 | 23 | ORA ZED - Ph 01B - Pkgs A&D23 | 24141553.78 | 21483271.639 | 2514002.85 | 23997274.489
Angola Emergency fast-track | ANG-Mor-Inv 4 - Ints | 4 | Angola Emergency fast-track4 | 4452515.49 | 2964043.81 | 0 | 2964043.81
Miscellaneous Projects | 2009210017 |  | Miscellaneous Projects | 28907.82 | 32954.91 | 0 | 32954.91
South Helwan PP (CP-117) | 2010210002 |  | South Helwan PP (CP-117) | 136989.63 | 142685.66 | 0 | 142685.66
10th of Ramadan Railway | IPC#2 | 2 | 10th of Ramadan Railway2 | 1911600 | 1811241 | 0 | 1811241
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $8 | 8 | Benban 3/ Toshka 2 LOT 48 | 79234.23 | 65619.61 | 8319.59 | 73939.2
Cairo Capital Cables Tunnel | Tunnel Inv. 6 | 6 | Cairo Capital Cables Tunnel6 | 27606172.95 | 18302892.55 | 6901543.25 | 25204435.8
RING ROAD MARYOTIA EXPANSION | MARIYTIA-R.R-IPC01 | 1 | RING ROAD MARYOTIA EXPANSION1 | 28687693.75 | 15791446.32 | 10000000 | 25791446.32
Cairo Capital Cables Tunnel | Tunnel Inv. 7 | 7 | Cairo Capital Cables Tunnel7 | 33277514.85 | 22062992.25 | 8319378.71 | 30382370.96
EMAAR-PKG117- MARASSI | 19100004 |  | EMAAR-PKG117- MARASSI | 4505534.5 | 3905373.095 | 430595.5 | 4335968.595
ElSewedy HQ Internal Finishing | EL SEWEDY HQ IPC16 | 16 | ElSewedy HQ Internal Finishing16 | 8911604.29 | 0.0045 | 5994299.1 | 7058911.3845
ElSewedy HQ Internal Finishing | ELSEWEDY IPC 11 | 11 | ElSewedy HQ Internal Finishing11 | 21606397.82 | 17417402.071 | 4830762.9 | 22248164.971
Marsa Matrouh 500KV | Inv.75 Borg Alarab | 75 | Marsa Matrouh 500KV75 | 4985146.67 | 4855331.33 | 0 | 4855331.33
Marsa Matrouh 500KV | Inv.76 Borg Alarab | 76 | Marsa Matrouh 500KV76 | 519370.87 | 483451.93 | 0 | 483451.93
P-28-16 Balat Owinat Lot 3 | Inv. 15 Balat lot 3 | 15 | P-28-16 Balat Owinat Lot 315 | 4089500.19 | 2809088.34 | 429397.52 | 3238485.86
Beni Seuf - 358 | Inv. 9 Oewon Mousa | 9 | Beni Seuf - 3589 | 42062234.7 | 29057490.98 | 7116030.86 | 36173521.84
Canal Sugar 33KV OHTL | Inv. 3 Sugar 33 OHTL | 3 | Canal Sugar 33KV OHTL3 | 23399301.19 | 18485447.83 | 3509895.18 | 21995343.01
Kattameya Creeks | Katamya chreek ipc39 | 39 | Kattameya Creeks39 | 66379928.69 | 66261026 | 2575496.63 | 68836522.63
Kattameya Creeks | KATAMEYA GREEKS-IPC6 | 6 | Kattameya Creeks6 | 32255415.11 | 29363826.7655 | 4181804.95 | 33545631.7155
Marsa Matrouh 500KV | Inv.25Usd borg alarb | 25 | Marsa Matrouh 500KV25 | 15090.57 | 14101.14 | 0 | 14101.14
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .15 | 15 | Benban 3/ Toshka 2 LOT 415 | 6329953.5 | 4981279.18 | 664645.12 | 5645924.3
Beni Suef Substation R61 | BSF-CW-EURO-9FINAL | 9 | Beni Suef Substation R619 | 16399.71 | 2415310.91 | 0 | 2415310.91
IKEA Extension MoA | IKEA2-IPC02 | 2 | IKEA Extension MoA2 | 1613181.4 | 1513146.56 | 0 | 1513146.56
Royal City | ROYAL ZONE-IPC14 | 14 | Royal City14 | 2137250.76 | 1288827.4664 | 349386.65 | 1638214.1164
LRT Project | IPC_1_LRT | 1 | LRT Project1 | 103200 | 87358.8 | 0 | 87358.8
10th of Ramadan Railway | IPC#1 | 1 | 10th of Ramadan Railway1 | 1574154 | 1491510.92 | 0 | 1491510.92
Fish Market | SOUQ ELSAMAK-IPC02 | 2 | Fish Market2 | 9650509.57 | 0.9985 | 0 | 0.9985
SHATRA 400/132kV SS | 392 |  | SHATRA 400/132kV SS | 1821535.32 | 1821535.32 | 0 | 1821535.32
Canal Sugar 33KV OHTL | Ref Ret Sugar 33OHTL |  | Canal Sugar 33KV OHTL | 5666669.06 | 5666669.06 | 0 | 5666669.06
VM Horizon Cloud LP-07-20 | 7 |  | VM Horizon Cloud LP-07-20 | 95497.83 | 108867.53 | 0 | 108867.53
Mid Town - Condo | IPC-Condo |  | Mid Town - Condo | 40000 | 40000 | 0 | 40000
Miscellaneous Projects | 2012210004 |  | Miscellaneous Projects | 237172.84 | 263261.85 | 0 | 263261.85
West Port Said 220 kV GIS | P-45-Portsaid Inv.05 | 5 | West Port Said 220 kV GIS5 | 5477475.88 | 0 | 575134.97 | 575134.97
New Babil 400/132KV Substation | 2103210002 |  | New Babil 400/132KV Substation | 9397.92 | 9397.92 | 0 | 9397.92
RING ROAD MARYOTIA EXPANSION | RING MARYOTUA-IPC03 | 3 | RING ROAD MARYOTIA EXPANSION3 | 12200900 | 11340731.41 | 0 | 11340731.41
EDNC Retail & Offices Civil | SOREAL-IPC22 | 22 | EDNC Retail & Offices Civil22 | 29539476.98 | 19964135.699 | 2567491.44 | 22531627.139
GOV2 - Infra | GOV2-IPC 1MOS+2 | 1 | GOV2 - Infra1 | 4159678.82 | 8793510.21 | 0 | 8793510.21
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC09 | 9 | EMAAR-Pkg#162/163- Marassi9 | 5020188.63 | 4602212.1515 | 1334744.6 | 5936956.7515
LAYAN Substation | 10464 |  | LAYAN Substation | 201990.6 | 341364.12 | 0 | 170682.06
Koning Food V2 - LP-08-20 | 10 |  | Koning Food V2 - LP-08-20 | 528.59 | 602.6 | 0 | 602.6
Akhmem - Qena | Inv.51 Qena Akhmem | 51 | Akhmem - Qena51 | 4985924.64 | 3958824.16 | 0 | 3958824.16
Cairo Capital Cables Tunnel | Tunnel Inv. 9 | 9 | Cairo Capital Cables Tunnel9 | 44464806.1 | 29480166.25 | 11116201.53 | 40596367.78
Zone(J) South Valley Toshka | South Valley Inv. 06 | 6 | Zone(J) South Valley Toshka6 | 40847011.3 | 31125008.3 | 5228417.45 | 36353425.75
SHAT Al ARAB 400/132kV SS | 401 |  | SHAT Al ARAB 400/132kV SS | 635924.84 | 635924.84 | 0 | 635924.84
SHATRA 400/132kV SS | 400 |  | SHATRA 400/132kV SS | 1067997.84 | 1067997.84 | 0 | 1067997.84
Ismailiya East Substation | ISE-SW-EGP-08 | 8 | Ismailiya East Substation8 | 467875 | 416408.75 | 0 | 416408.75
Akhmem - Qena | Inv.50 Qena Akhmem | 50 | Akhmem - Qena50 | 1793358.01 | 1506420.9 | 0 | 1506420.9
SHAT Al ARAB 400/132kV SS | 404 |  | SHAT Al ARAB 400/132kV SS | 1432167.03 | 1432167.03 | 0 | 1432167.03
DoubleTree Mangroovy ElGouna | MANROVE-IPC14 | 14 | DoubleTree Mangroovy ElGouna14 | 4271693.53 | 3058799.81 | 1027682.3 | 4086482.11
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC 25 | 25 | EMAAR-Pkg#162/163- Marassi25 | 3618126.7 | 4308209.73 | 80309.95 | 4388519.68
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC019 | 19 | EMAAR-Pkg#162/163- Marassi19 | 0.0001 | 6528975.8501 | 771115.07 | 7300090.9201
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC09 | 9 | EMAAR-Pkg#162/163- Marassi9 | 0.001 | 3307337.871 | 177567.83 | 3484905.701
NUCA R05 - Z02 | R5 FINSHING-IPC11 | 11 | NUCA R05 - Z0211 | 19871625.75 | 15747861.85 | 1987162.6 | 17735024.45
Mauritania Lot 1 | Inv.19 - Lot 1 | 19 | Mauritania Lot 119 | 232841.21 | 58214.53 | 0 | 58214.53
Mauritania-Lot 2 | Inv.17 - Lot 2 | 17 | Mauritania-Lot 217 | 644058.64 | 212578.18 | 0 | 212578.18
Mauritania-Lot 2 | Inv.14 – Lot 2 | 14 | Mauritania-Lot 214 | 627289.8 | 595869.06 | 0 | 595869.06
Mauritania-Lot 2 | Inv. 11 – Lot 2 | 11 | Mauritania-Lot 211 | 1364266.56 | 1296053.23 | 0 | 1296053.23
EGAT Pelletizing Plant | elco egat ipc10 | 10 | EGAT Pelletizing Plant10 | 17027897.29 | 16034098.6 | 1674914.5845 | 17709013.1845
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC020 | 20 | EMAAR-PKG# 101-UPTOWN20 | 1322361.65 | 648976.9025 | 316404.16 | 965381.0625
VM Horizon Cloud LP-07-20 | 19 |  | VM Horizon Cloud LP-07-20 | 14150 | 16131 | 0 | 16131
Miscellaneous Projects | 2105210016 |  | Miscellaneous Projects | 114299.76 | 130301.7264 | 0 | 130301.7264
Capital One | INV( 1 ) 21-6-2021 | 1 | Capital One1 | 526448.5 | 521184.025 | 0 | 521184.025
NUCA R05 - Z02 | R05 Finishng - IPC12 | 12 | NUCA R05 - Z0212 | 18550221 | 14700646.05 | 1855022.1 | 16555668.15
Diplomatic District - Infra | Diplo Dist IPC04 | 4 | Diplomatic District - Infra4 | 2419418.571 | 10569264.03 | 1258854.31 | 11828118.34
Air Force Project | Air Force Inv . 04 | 4 | Air Force Project4 | 11951632.64 | 8556972 | 2987908.16 | 11544880.16
Faculty of Medicine | mansoura ipc 09 | 9 | Faculty of Medicine9 | 18326568.57 | 15506621.9085 | 916328.43 | 16422950.3385
NUCA R05 - Z02 | R5 - IPC22 | 22 | NUCA R05 - Z0222 | 29282126.25 | 24705356.85 | 3101185.15 | 27806542
Kafr Shokr Bridge | Kafr Shokr IPC03 | 3 | Kafr Shokr Bridge3 | 9630317.86 | 8372664.936 | 0 | 8372664.936
Zone(J) South Valley Toshka | South Valley Inv. 04 | 4 | Zone(J) South Valley Toshka4 | 39115686 | 29805752.9 | 5006807.85 | 34812560.75
LAYAN Substation | 10582 |  | LAYAN Substation | 172869.56 | 286963.48 | 0 | 143481.74
MIDELEC 66 KV OHTL | Midor Inv. 01 | 1 | MIDELEC 66 KV OHTL1 | 1787986.2 | 1501908.41 | 268197.93 | 1770106.34
October Dry Port Railway | ODP ipc03 | 3 | October Dry Port Railway3 | 13511957.5 | 0 | 0 | 14187555.375
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 11 | 11 | Hosh Essa 220 KV OHTL11 | 2240000 | 0 | 235200 | 235200
Toshka GIS 500 kV | Toshka Sub Inv. 01 $ | 1 | Toshka GIS 500 kV1 | 8268188.57 | 5460447.72 | 2170399.5 | 7630847.22
Miscellaneous Projects | 2101210005 |  | Miscellaneous Projects | 10500 | 11655 | 0 | 11655
DPW Onshore Port & Terminal | DP World IPC028 | 28 | DPW Onshore Port & Terminal28 | 27099548.46 | 19977105.85 | 4064932.27 | 24042038.12
Olympic Multi – Sports Hall | OLYMPIC CIVIL-IPC04 | 4 | Olympic Multi – Sports Hall4 | 56613357.08 | 10576930 | 36483374.25 | 47964451.75
Shenzo Aby Bridge - Haggana | FPC - Shenzo Aby |  | Shenzo Aby Bridge - Haggana | 162900 | 121982.25 | 0 | 121982.25
LAYAN Substation | 10623 |  | LAYAN Substation | 138800 | 437220 | 0 | 145740
National Batteries LP-05-20 | 20 |  | National Batteries LP-05-20 | 1157895 | 683539.125 | 330000.245 | 1013539.37
seashell Playa | IPC-7-PLAYA | 7 | seashell Playa7 | 393993.05 | 273306.55 | 63038.89 | 336345.44
10Th of Ramadan LRT | LRT 10Ramadan Inv.04 | 4 | 10Th of Ramadan LRT4 | 7953536.78 | 539392.5 | 795353.68 | 1334746.18
Governmental Campus-N2 | 25 |  | Governmental Campus-N2 | 2564261.48 | 2564261.48 | 0 | 2564261.48
Tamey El-amdeed Substation | TAM-CW-EGP-24 | 24 | Tamey El-amdeed Substation24 | 112131.3 | 160139 | 0 | 160139
MOTHANA 400/132kV SS | 414 |  | MOTHANA 400/132kV SS | 43876.07 | 43876.07 | 0 | 43876.07
Miscellaneous Projects | 2012210013 |  | Miscellaneous Projects | 36431.91 | 41532.3774 | 0 | 41532.3774
New Heliopolis | Inv. 13 Heliopolise | 13 | New Heliopolis13 | 8453388 | 6563573.05 | 830122.7 | 7393695.75
ElMoneeb 2 | IPC#3 - ElMoneeb | 3 | ElMoneeb 23 | 727800 | 248132.74 | 0 | 677282.63
Marassi Inner Marina - PKG178 | FPC - PKG#178 |  | Marassi Inner Marina - PKG178 | 61650 | 54868.5 | 0 | 54868.5
Bridge Axis Firdaws | INV ( 3 ) | 3 | Bridge Axis Firdaws3 | 1601988.8 | 1505869.47 | 0 | 1505869.47
AWEER POWER STATION 'H' Phase | LOC/018 |  | AWEER POWER STATION 'H' Phase | 455396.7 | 399737.1007 | 50599.63 | 450336.7307
Akhmem Assiut | Ref.Ret Asuit akhm |  | Akhmem Assiut | 10000000 | 10000000 | 0 | 10000000
Canal Sugar S/s | Ref.Ret Sugar Sub $ |  | Canal Sugar S/s | 123689.55 | 123689.55 | 0 | 123689.55
HyperOne Zayed Extension | IPC-FINAL-HYPER ONE |  | HyperOne Zayed Extension | 16067538.5 | 2754557 | 6313451.95 | 9068008.95
Zone(J) South Valley Toshka | South Valley Inv. 01 | 1 | Zone(J) South Valley Toshka1 | 47619261.45 | 33899453.3 | 6095265.5 | 39994718.8
Racecores 3092-16 132KV C | 10902 |  | Racecores 3092-16 132KV C | 2016458.7 | 1673660.72 | 0 | 1673660.72
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC025 | 25 | EMAAR- Pkg 140-ITP-Mivida25 | 5220299.96 | 9290247.798 | 261808.31 | 9552056.108
Olympic Multi – Sports Hall | Olympic Hall IPC05 | 5 | Olympic Multi – Sports Hall5 | 89184449.38 | 17108044.99 | 57918857.35 | 75550834.84
Zone(J) South Valley Toshka | South Valley Inv. 07 | 7 | Zone(J) South Valley Toshka7 | 36376001.8 | 27718098.9 | 4656128.25 | 32374227.15
Air Force Project | Air Force Inv . 12 | 12 | Air Force Project12 | 9743768.2 | 6976135 | 2435942.05 | 9412077.05
MDF Factory | MDF FACTORY3 IPC01 | 1 | MDF Factory1 | 1269450 | 920351.25 | 361793.25 | 1282144.5
LAYAN Substation | 10804 |  | LAYAN Substation | 36500 | 268275 | 0 | 38325
BRSH-JHRC | 11723 |  | BRSH-JHRC | 506746.2476 | 50674.62 | 0 | 50674.62
Cairo Monorail - 6th October | IPC4 - Monorail | 4 | Cairo Monorail - 6th October4 | 1260000 | 1247400 | 0 | 1247400
MDF Factory | MDF IPC05 | 5 | MDF Factory5 | 23254260.42 | 21785509.721 | 1346981.76 | 23132491.481
Ahl Misr P3 – Zamalek Sector | IPC#6` | 6 | Ahl Misr P3 – Zamalek Sector6 | 234900 | 224265.75 | 0 | 224265.75
SHATRA 400/132kV SS | 425 |  | SHATRA 400/132kV SS | 105926.91 | 105926.91 | 0 | 105926.91
Olympic Multi – Sports Hall | Olympic Hall IPC02 | 2 | Olympic Multi – Sports Hall2 | 36131324.45 | 25980535.02 | 17523700 | 43504235.02
Waldorf Astoria Cairo | Waldorf IPC7 | 7 | Waldorf Astoria Cairo7 | 14720271.03 | 8710614.8515 | 5943712.87 | 14654327.7215
CFC Podium 2 | CFC IPC027 | 27 | CFC Podium 227 | 7714993.76 | 7405131.708 | 0 | 7405131.708
New Babil 400/132KV GIS Substa | 2108210001 |  | New Babil 400/132KV GIS Substa | 4032620.32 | 4032620.32 | 0 | 4032620.32
Zafranaa - Beni Suef | Ref.Ret Zafra-B-Suef |  | Zafranaa - Beni Suef | 1114579.04 | 0 | 0 | 1114579.04
Racecores 3092-17 132KV E | 10982 |  | Racecores 3092-17 132KV E | 12380.9524 | 26000 | 0 | 13000
Akhmem - Qena | Ret Qen-akh 7 T |  | Akhmem - Qena | 50000000 | 50000000 | 0 | 50000000
Akhmem Assiut | Ref.Ret Asuit akh 5 |  | Akhmem Assiut | 4316843.16 | 0 | 0 | 4316843.16
CFC Podium 2 | CFC IPC026 | 26 | CFC Podium 226 | 6460765.95 | 4897254.2975 | 0 | 4897254.2975
Air Force Project | Air Force Inv . 19 | 19 | Air Force Project19 | 1557454.2 | 1504371.53 | 0 | 1504371.53
Air Force Project | Air Force Inv . 18 | 18 | Air Force Project18 | 3225717.12 | 3115768.47 | 0 | 3115768.47
Get Business Complex | INV ( 4 ) GET | 4 | Get Business Complex4 | 126432 | 118846.08 | 0 | 118846.08
EGAT Pelletizing Plant | EGAT WaterTank IPC06 | 6 | EGAT Pelletizing Plant6 | 1464316.6 | 1449673.43 | 0 | 1449673.43
Kattameya Creeks | katamya ipc11 | 11 | Kattameya Creeks11 | 46662391.16 | 43214038.288 | 5304728.52 | 48518766.808
LAYYAH CCPP | 519 |  | LAYYAH CCPP | 11458140 | 9066879 | 2391258 | 11458137
Ministries Buildings | Minist Core IPC09 | 9 | Ministries Buildings9 | 6450238.37 | 5433920.01 | 0 | 5433920.01
TZ – Offshore E&M Procurement | 443 |  | TZ – Offshore E&M Procurement | 695957.09 | 553405.1 | 71276 | 624681.1
Sokhna Port Expansion | sokhna port ipc 12 | 12 | Sokhna Port Expansion12 | 101620062.95 | 70395885.55 | 20324012.59 | 90719898.14
Sokhna Port Expansion | sokhna port ex ipc06 | 6 | Sokhna Port Expansion6 | 38544935.71 | 26209057.4855 | 8094436.5 | 34303493.9855
Mauritania Lot 1 | Inv.15 - Lot 1 | 15 | Mauritania Lot 115 | 345052 | 327784.78 | 0 | 327784.78
Port Said Grain Storage | IPC#5 GSCC Port Said | 5 | Port Said Grain Storage5 | 1155000 | 0 | 0 | 1155000
Port Said Grain Storage | IPC#1-Port Saeid | 1 | Port Said Grain Storage1 | 1131900 | 807661.47 | 0 | 948264.64
Ahl Misr Walkway | 120721 |  | Ahl Misr Walkway | 22760 | 18473.89 | 0 | 18473.89
October Dry Port Railway | ODP IPC02 | 2 | October Dry Port Railway2 | 19648020 | 12505964.73 | 4126084.2 | 16632048.93
Akhmem Assiut | Ref. Akhmem Asuit2T |  | Akhmem Assiut | 15000000 | 0 | 0 | 15000000
Racecores 3092-16 132KV C | 11082 |  | Racecores 3092-16 132KV C | 22300 | 23415 | 0 | 23415
Racecores 3092-17 132KV E | 11144 |  | Racecores 3092-17 132KV E | 2227.22 | 2227.22 | 0 | 2227.22
ENR-Signaling Inst. | ENR-Sign Inst Inv04 | 4 | ENR-Signaling Inst.4 | 6948000.16 | 5836320.13 | 694800.02 | 6531120.15
Egat Rolling Mill no.4 | Rolling mill ipc 03 | 3 | Egat Rolling Mill no.43 | 12117327 | 10231445.3 | 2370574.78 | 12602020.08
Water pumping New Obour City | Wat Pump Obour Inv.2 | 2 | Water pumping New Obour City2 | 22613426.64 | 17284740.87 | 2374409.8 | 19659150.67
Benban 500 K.V/95 K.M | Benban Lot2 Inv 12 $ | 12 | Benban 500 K.V/95 K.M12 | 205796.67 | 172869.2 | 21608.65 | 194477.85
Tamey El-amdeed Substation | Tam SW Final |  | Tamey El-amdeed Substation | 43750.92 | 38938.32 | 0 | 38938.32
Ismailiya East Substation | SW Final |  | Ismailiya East Substation | 943311 | 7865054.79 | 0 | 7865054.79
Port Said Port Silos | PORT SAID IPC 27 | 27 | Port Said Port Silos27 | 1478728.71 | 0 | 147871.1884 | 147871.1884
PLAYA ROOF & Wet Areas | IPC-4-Playa Roof | 4 | PLAYA ROOF & Wet Areas4 | 61197.5 | 52513.56 | 0 | 52513.56
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 02 | 2 | Hosh Essa 220 KV OHTL2 | 1585131.64 | 952668.25 | 166438.82 | 1119107.07
Al-Parco | INV ( 3 )ALparco | 3 | Al-Parco3 | 2422608 | 0 | 0 | 2422608
Racecores 3092-17 132KV E | 11283 |  | Racecores 3092-17 132KV E | 769.67 | 769.67 | 0 | 769.67
Racecores 3092-17 132KV E | 11282 |  | Racecores 3092-17 132KV E | 4933.41 | 4933.41 | 0 | 4933.41
Racecores 3092-16 132KV C | 11286 |  | Racecores 3092-16 132KV C | 36036.49 | 36036.49 | 0 | 36036.49
LP-15-21 UIC | 54 |  | LP-15-21 UIC | 30000 | 33900 | 0 | 33900
Cairo-Alex Railway | cairo-alex ipc 17 | 17 | Cairo-Alex Railway17 | 34296433.2 | 23818474.05 | 3601125.49 | 27419599.54
Ain Sokhna Port Development | IPC#9 - Spkhna port | 9 | Ain Sokhna Port Development9 | 1591288 | 1454830.83 | 0 | 1483644.59
MDF Factory | MDF FACTORY IPC08 | 8 | MDF Factory8 | 7024663.54 | 12778186.187 | 807862.18 | 13586048.367
Racecores 3092-16 132KV C | 11363 |  | Racecores 3092-16 132KV C | 5210.82 | 5210.82 | 0 | 5210.82
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.02 | 2 | 10th Ramadan Indu Park Plot112 | 1 | 27960735.63 | 0 | 27960735.63
EGAT Pelletizing Plant | egat watertank ipc10 | 10 | EGAT Pelletizing Plant10 | 3540729.8 | 3505322.5 | 0 | 3505322.5
Hyper El-Temsah | HYPER ELCTRO-FINAL |  | Hyper El-Temsah | 164642.05 | 0.38 | 0 | 0.38
Expansion of Ring Road | FPC - Tiger |  | Expansion of Ring Road | 51800 | 49634 | 0 | 49634
LAYAN Substation | 11746 |  | LAYAN Substation | 177273.88 | 294274.628 | 0 | 147137.314
Infra Project 4428 | 220421005 |  | Infra Project 4428 | 285714285.72 | 300000000.006 | 0 | 300000000.006
LAYYAH CCPP | 520 |  | LAYYAH CCPP | 10283760 | 8231475 | 2052285 | 10283760
EGAT Pelletizing Plant | ELCO EGAT IPC 11 | 11 | EGAT Pelletizing Plant11 | 14893958.08 | 14151886.794 | 1337829.61 | 15489716.404
158E/2019 33kv Project | 11519 |  | 158E/2019 33kv Project | 497217.6 | 1342487.52 | 0 | 447495.84
Waldorf Astoria Cairo | WALDORF astoria IPC1 | 1 | Waldorf Astoria Cairo1 | 6707988.52 | 4511122.119 | 1760846.99 | 6271969.109
New Babil 400/132KV GIS Substa | 220321001 |  | New Babil 400/132KV GIS Substa | 1268718.64 | 1268718.64 | 0 | 1268718.64
Mivida BP#189 | Emaar pkg#189 ipc 31 | 31 | Mivida BP#18931 | 19514716.97 | 0 | 3602734.16 | 3602734.16
Mivida BP#189 | Emaar PKG#189 IPC28 | 28 | Mivida BP#18928 | 3487392.64 | 2409288.192 | 309513.68 | 2718801.872
Mivida BP#189 | Emaar pkg#189 ipc 14 | 14 | Mivida BP#18914 | 22729528.92 | 23637153.386 | 2841944.63 | 26479098.016
seashell Playa | IPC-16-PLAYA | 16 | seashell Playa16 | 1252671.35 | 1074917.34 | 0 | 1074917.34
AWEER POWER STATION 'H' Phase | IMP/069 |  | AWEER POWER STATION 'H' Phase | 90156.23 | 94664.0415 | 0 | 94664.0415
EGAT Pelletizing Plant | Elco EGAT IPC12 | 12 | EGAT Pelletizing Plant12 | 8116942.79 | 8095552.3195 | 346068.18 | 8441620.4995
P.I.Parks - Plot 10 | PIP indust Inv.02 | 2 | P.I.Parks - Plot 102 | 6152138.66 | 11344920.68 | 1453489.88 | 12798410.56
Faculty of Medicine | mansora finish ipc22 | 22 | Faculty of Medicine22 | 11782769.52 | 8785418.9948 | 1767415.43 | 10552834.4248
MDF Factory | Mdf factory2 ipc05 | 5 | MDF Factory5 | 2046589.82 | 2067055.7248 | 0 | 2067055.7248
Ora Zed Landscape Ph1 | Ora landscape ipc 10 | 10 | Ora Zed Landscape Ph110 | 3148169.54 | 2562980.717 | 330557.8 | 2893538.517
Astoria Sharm elSheikh | astoria sharm ipc 01 | 1 | Astoria Sharm elSheikh1 | 1119573 | 837813.8 | 326542.1 | 1164355.9
LAYYAH CCPP | 523 |  | LAYYAH CCPP | 10283760 | 3174000 | 1380785 | 4554785
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $11 | 11 | Benban 3/ Toshka 2 LOT 411 | -339705.29 | -356690.55 | 0 | -356690.55
seashell Playa | IPC-18-PLAYA | 18 | seashell Playa18 | 526143.1 | 451483.39 | 0 | 451483.39
Air Defense College | air devance ipc03 | 3 | Air Defense College3 | 3832891.1 | 1188779.99 | 0 | 3249422.99
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.03 | 3 | 10th Ramadan Indu Park Plot113 | 16472966.76 | 26056793.31 | 2594492.26 | 28651285.57
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .16 | 16 | Benban 3/ Toshka 2 LOT 416 | 95081746.73 | 74828938.59 | 9983583.41 | 84812522
LAYAN Substation | 11682 |  | LAYAN Substation | 47897.2472 | 50292.1096 | 0 | 50292.1096
LAYYAH CCPP | 10020 |  | LAYYAH CCPP | 0 | 5733920.97 | 0 | 5733920.97
AWEER POWER STATION 'H' Phase | ENG/055 |  | AWEER POWER STATION 'H' Phase | 22065.16 | 23168.418 | 0 | 23168.418
Infra Project 2531 | 220421003 |  | Infra Project 2531 | 69095346.19 | 43618300 | 14357670 | 57975970
Infra Project 2524 | 220321002 |  | Infra Project 2524 | 90398178.05 | 90398178.05 | 0 | 90398178.05
158E/2019 33kv Project | 10342 |  | 158E/2019 33kv Project | 2539278.61 | 2285350.75 | 0 | 2285350.75
Governmental Campus-N2 | 64 |  | Governmental Campus-N2 | 697588.06 | 697588.06 | 0 | 697588.06
Monorail | 220621008 |  | Monorail | 363298 | 410526.74 | 0 | 410526.74
LP-20-21 ACUD Fiber optics | 71 |  | LP-20-21 ACUD Fiber optics | 1166400 | 1318032 | 0 | 1318032
MDF Factory | MDF Factory ipc (27) | 27 | MDF Factory27 | 7649824.31 | 19177600.34 | 3212977.19 | 22390577.53
New Babil 400/132KV GIS Substa | 220721001 |  | New Babil 400/132KV GIS Substa | 217380.8 | 217380.8 | 0 | 217380.8
New Babil 400/132KV GIS Substa | 220721004 |  | New Babil 400/132KV GIS Substa | 1787953.49 | 1787953.49 | 0 | 1787953.49
NUCA R05 - Z02 | R5(2) ipc 23 | 23 | NUCA R05 - Z0223 | 30312335.29 | 24605476.43 | 3166889.7 | 27772366.13
South Helwan PP (CP-117) | 180056 |  | South Helwan PP (CP-117) | 201244.72 | 179948.77 | 31755.66 | 211704.43
Port Saad Industiral zone | IPC#4 | 4 | Port Saad Industiral zone4 | 1095780 | 1055236.14 | 0 | 1055236.14
MDF Factory | MDF (2) - IPC 8 | 8 | MDF Factory8 | 338870.79 | 322759.5006 | 0 | 322759.5006
Central Bus Station | inv ( final ) T0022 |  | Central Bus Station | 274780 | 274780 | 0 | 274780
Al Montaza Hotels - Alexandria | inv ( 3 ) montazha | 3 | Al Montaza Hotels - Alexandria3 | 939729 | 892742.55 | 0 | 892742.55
Olympic Multi – Sports Hall | olmpiclandscape ipc1 | 1 | Olympic Multi – Sports Hall1 | 23918543.68 | 3791250 | 17031510 | 20822760
New Giza Teaching Hospital | New Giza Hosp ipc16 | 16 | New Giza Teaching Hospital16 | 22109235.45 | 8749433.6065 | 2152996.48 | 18402430.0865
LAYAN Substation | 11619 |  | LAYAN Substation | 267278.0523 | 677549.8648 | 0 | 225849.9549
SSC Suez Steel Company Project | SUEZ STEEL SSC IPC 1 | 1 | SSC Suez Steel Company Project1 | 10223133.6 | 8726335.414 | 2825805.55 | 11552140.964
SSC Suez Steel Company Project | In&ReApply(SSC)IPC2 | 2 | SSC Suez Steel Company Project2 | 3081346.71 | 3020707.7794 | 399587.07 | 3420294.8494
SSC Suez Steel Company Project | intak&ret apply ipc5 | 5 | SSC Suez Steel Company Project5 | 2725254.77 | 1779061.4678 | 1245971.33 | 3025032.7978
SSC Suez Steel Company Project | In&reApply(ABB)ipc1 | 1 | SSC Suez Steel Company Project1 | 779997.07 | 509186.4298 | 356610.32 | 865796.7498
EGAT Injection | TR0048-00002 | 2 | EGAT Injection2 | 98000 | 84093.8 | 0 | 84093.8
GOV2 - Infra | Gov2 ipc 15+16 | 15 | GOV2 - Infra15 | 15963362.95 | 10956705.9675 | 1490940.99 | 12447646.9575
EGAT Pelletizing Plant | EGAT Watertank-IPC12 | 12 | EGAT Pelletizing Plant12 | 698940.32 | 691950.916 | 0 | 691950.916
Ministries Buildings | minis shel ipc09 | 9 | Ministries Buildings9 | 3018358 | 2542560 | 0 | 2542560
MDF Factory | MDF (2) - IPC9 | 9 | MDF Factory9 | 1654996.96 | 1671546.9244 | 0 | 1671546.9244
Ring Road El Mansoria | INV ( 1 ) ALmansorya | 1 | Ring Road El Mansoria1 | 332760 | 174309.36 | 0 | 174309.36
CS-20 Mall | inv ( 15 ) CS-20 | 15 | CS-20 Mall15 | 155689.45 | 60718.89 | 0 | 60718.89
CS-20 Mall | inv ( 16 ) CS-20 | 16 | CS-20 Mall16 | 520583.43 | 173151.91 | 0 | 173151.91
CS-20 Mall | inv ( 1 ) CS-20 | 1 | CS-20 Mall1 | 945878.85 | 889126.12 | 0 | 889126.12
Kafr Shokr Bridge | kafr shokr ipc#9 | 9 | Kafr Shokr Bridge9 | 5509702.86 | 4811892.2 | 0 | 4811892.2
Ministries Buildings | Min MEP. IPC5 | 5 | Ministries Buildings5 | 121861476.8 | 0 | 0 | 76281582.83
LRT | FPC - LRT ARABCo |  | LRT | 882948 | 829971.12 | 0 | 829971.12
Egat Rolling Mill no.4 | ROLLING MILL IPC 09 | 9 | Egat Rolling Mill no.49 | 19868885.15 | 15728875.4675 | 4934765.09 | 20663640.5575
Olympic Multi – Sports Hall | Finishing IPC02 | 2 | Olympic Multi – Sports Hall2 | 29261275 | 1689654 | 25815944.5 | 27505598.5
Astoria Sharm elSheikh | Astoria sharm- IPC4 | 4 | Astoria Sharm elSheikh4 | 1055208 | 709627 | 276992.1 | 986619.1
New Giza Teaching Hospital | new giza hos ipc3 | 3 | New Giza Teaching Hospital3 | 7560552.29 | 7466045.3845 | 0 | 7466045.3845
Railway Bridge - Assuit | IPC#1&2 -Assuit Rent | 1 | Railway Bridge - Assuit1 | 410400 | 796176 | 0 | 398088
Dwelling Villas Seashell Playa | IPC001 Dewalling | 1 | Dwelling Villas Seashell Playa1 | 75551.56 | 65246.33 | 0 | 65246.33
ElSewedy HQ Internal Finishing | Elsewedy HQ IPC19 | 19 | ElSewedy HQ Internal Finishing19 | 11160546.75 | 0 | 8749943.6 | 10873318.8875
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC021. | 21 | EMAAR-PKG# 101-UPTOWN21 | 952924.08 | 803886.084 | 446634.21 | 1250520.294
MDF Factory | MDF IPC15 | 15 | MDF Factory15 | 8189110.5 | 11311884.995 | 2340438.88 | 13652323.875
Get Business Complex | INV ( 17 ) GET | 17 | Get Business Complex17 | 3177489.8 | 179900.41 | 0 | 179900.41
Sokhna Port Expansion | sokhna port ex ipc07 | 7 | Sokhna Port Expansion7 | 54124258.65 | 36803653.95 | 11366094.32 | 48169748.27
ElSewedy HQ Internal Finishing | elsewedy HQ- IPC21 | 21 | ElSewedy HQ Internal Finishing21 | 6969185.9 | 0 | 2341646.56 | 4046292.505
Katameya Creeks - RME | IPC00001 | 1 | Katameya Creeks - RME1 | 67028.72 | 59353.94 | 0 | 59353.94
Playa Resort | 43- kantine 5 |  | Playa Resort | 35000 | 35000 | 0 | 35000
Creeks URBN-K | Urbn-k IPC 7 | 7 | Creeks URBN-K7 | 18657407.33 | 16761479 | 1761482.87 | 18522961.87
Sokhna Port Expansion | sokhna port ex ipc 8 | 8 | Sokhna Port Expansion8 | 52378217.65 | 36284089.65 | 10475643.53 | 46759733.18
SSC Suez Steel Company Project | Revamp ipc(4) | 4 | SSC Suez Steel Company Project4 | 3836789.63 | 2647384.8452 | 1151036.89 | 3798421.7352
ORA-ZED Towers P01B | IPC#00002 | 2 | ORA-ZED Towers P01B2 | 30183.08 | 26727.11 | 0 | 26727.11
Air Defence College | IPC004 Air Defense | 4 | Air Defence College4 | 247985.38 | 207914.59 | 0 | 207914.59
Port Said Port Silos | port said silos ipc9 | 9 | Port Said Port Silos9 | 3139228.09 | 2756360.9335 | 313922.81 | 3070283.7435
EPICO 3 Facility | EIPICO3 - IPC1 | 1 | EPICO 3 Facility1 | 12192163.2 | 12050858.57 | 0 | 12050858.57
ORA-ZED Towers P01B | IPC0000001 | 1 | ORA-ZED Towers P01B1 | 113671.35 | 100655.98 | 0 | 100655.98
Kemet Tower | INV ( 2-3-4 ) KEMET | 2 | Kemet Tower2 | 467520 | 401178.91 | 0 | 401178.91
seashell Playa | IPC#000015 | 15 | seashell Playa15 | 314783.01 | 270115.3 | 0 | 270115.3
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC25 | 25 | ElSewedy HQ Internal Finishing25 | 17937426.6 | 4987239.22 | 0 | 9125697.86
WADY EL-NATROUN BRIDGE(HST) | IPC#5 WADI | 5 | WADY EL-NATROUN BRIDGE(HST)5 | 328425 | 298242.74 | 0 | 298242.74
WADY EL-NATROUN BRIDGE(HST) | IPC#7 WADI | 7 | WADY EL-NATROUN BRIDGE(HST)7 | 767070 | 655166.26 | 0 | 655166.26
U4,U8 Seashell Playa | IPC006 TR60 | 6 | U4,U8 Seashell Playa6 | 87496.95 | 39612.11 | 0 | 39612.11
Olympic Multi – Sports Hall | Olypic sehe IPC1 | 1 | Olympic Multi – Sports Hall1 | 10647712 | 1893920 | 7000000 | 8893920
DP World Basin 2 Ph2 | Dp world ph.2-IPC 2 | 2 | DP World Basin 2 Ph22 | 31327285.45 | 0 | 0 | 31327285.45
HST El Mahager Bridge | ipc 2 elmahager | 2 | HST El Mahager Bridge2 | 10987767.86 | 3492288.9 | 0 | 3492288.9
Ora Zed Landscape Ph1 | Ora ph landscap ipc2 | 2 | Ora Zed Landscape Ph12 | 2071866.5 | 1828422.185 | 217545.98 | 2045968.165
WADY EL-NATROUN BRIDGE(HST) | IPC#10 WADI | 10 | WADY EL-NATROUN BRIDGE(HST)10 | 1255380 | 1214339.67 | 0 | 1214339.67
El-Warraq | IPC# 1 WARAAQ | 1 | El-Warraq1 | 1440000 | 909064 | 0 | 909064
MDF Factory | MDF 2 IPC (15) | 15 | MDF Factory15 | 1493437.21 | 1508253.0542 | 0 | 1508253.0542
Sokhna Port Expansion | sokhna port ex ipc11 | 11 | Sokhna Port Expansion11 | 73288962.77 | 50769799.2 | 14657792.55 | 65427591.75
SSC Suez Steel Company Project | in.&ret.sup sscipc1 | 1 | SSC Suez Steel Company Project1 | 2140488 | 2311727.04 | 0 | 2311727.04
SSC Suez Steel Company Project | R.O.SU.PRIC.ADJ.IPC3 | 3 | SSC Suez Steel Company Project3 | 8704005.47 | 9400325.9111 | 0 | 9400325.9111
Seashell Playa 5 Villas | playa-c185 pic 1 |  | Seashell Playa 5 Villas | 74965.5 | 48301.29 | 0 | 48301.29
Seashell Playa 5 Villas | playa c-204 ipc 2 | 2 | Seashell Playa 5 Villas2 | 24044.74 | 20765.03 | 0 | 20765.03
Seashell Playa 5 Villas | seashell playa ipc04 | 4 | Seashell Playa 5 Villas4 | 208421.31 | 89386.81 | 0 | 89386.81
Seashell Playa 5 Villas | seashell playa ipc 6 | 6 | Seashell Playa 5 Villas6 | 421226.03 | 278628.8 | 0 | 278628.8
October Under-Railway Tunnel | october tunnel ipc06 | 6 | October Under-Railway Tunnel6 | 1809302.29 | 1337162.5545 | 0 | 1337162.5545
Creeks URBN-K | Urbn-k ipc (8) | 8 | Creeks URBN-K8 | 18875663.98 | 16707944.9992 | 1948483.69 | 18656428.6892
Kattameya Creeks | Katameya Creek ipc35 | 35 | Kattameya Creeks35 | 59094596.48 | 46816344 | 14334625.91 | 61150969.91
Katameya Creeks - RME | IPC005 | 5 | Katameya Creeks - RME5 | 86893.7 | 76944.36 | 0 | 76944.36
EDNC Hardscape Package | sorealhardscapeIPC11 | 11 | EDNC Hardscape Package11 | 1095191.83 | 1006501.9215 | 0 | 1006501.9215
U7-SEASHELL | IPC03 TR64 | 3 | U7-SEASHELL3 | 113020.28 | 97604.33 | 0 | 97604.33
Creeks URBN-K | Katameya urbnk ipc9 | 9 | Creeks URBN-K9 | 18620717.8 | 16997068 | 1578985.46 | 18576053.46
EGAT Mechanical Installations | Egat Piping ipc 2 | 2 | EGAT Mechanical Installations2 | 71294.74 | 54176.8715 | 17823.68 | 72000.5515
MDF Factory | MDF Factory ipc 29 | 29 | MDF Factory29 | 6882776.19 | 10041845.6384 | 2890766 | 12932611.6384
Seashell Playa 5 Villas | seashell playa ipc 5 | 5 | Seashell Playa 5 Villas5 | 125965.27 | 94159.07 | 0 | 94159.07
U7-SEASHELL | IPC001 TR64 | 1 | U7-SEASHELL1 | 383850.75 | 331493.5 | 0 | 331493.5
Al Montaza Hotels - Alexandria | inv ( final) montazh |  | Al Montaza Hotels - Alexandria | 343024.5 | 223870.183 | 0 | 223870.183
Ministries Buildings | Minis MEP IPC8 | 8 | Ministries Buildings8 | 30376066 | 25591430 | 0 | 25591430
Egyptian Exchange building | IPC0011 | 11 | Egyptian Exchange building11 | 160250 | 127526.37 | 0 | 127526.37
Central Capital | INV ( 1 ) Central Ca | 1 | Central Capital1 | 168300 | 158202 | 0 | 158202
RING ROAD MARYOTIA EXPANSION | MARIOTYIA IPC16 | 16 | RING ROAD MARYOTIA EXPANSION16 | 40484939.8 | 40080090.4 | 0 | 40080090.4
Olympic Multi – Sports Hall | Olympic fins ipc5 | 5 | Olympic Multi – Sports Hall5 | 15781358 | 11120610 | 0 | 11120610
Air Defense College | air def finish4 IPC1 | 1 | Air Defense College1 | 29831422 | 6284750 | 18612000 | 24896750
British International School | Bis school ipc (1) | 1 | British International School1 | 6616812.11 | 8894097.5 | 4137870.4 | 13031967.9
Pushing Tunnel | inv ( 1 ) T. Pushing | 1 | Pushing Tunnel1 | 4121100 | 3330260.91 | 0 | 3330260.91
Royal City | Royal City Final 43 |  | Royal City | 13228025 | 19699829.51 | 0 | 19699829.51
26th of July Corridor New | IPC FINAL 26th |  | 26th of July Corridor New | 937500 | 804468.75 | 0 | 804468.75
Borg El Arab Bridge - Km 21 | IPC#002 - Kilo21 | 2 | Borg El Arab Bridge - Km 212 | 726647.4 | 610933.56 | 0 | 610933.56
Bahr El Baqar Treatment Plant | IPC#2 Bahr El Baqar | 2 | Bahr El Baqar Treatment Plant2 | 134756.7 | 61300 | 0 | 61300
U4,U8 Seashell Playa | IPC09 TR60 | 9 | U4,U8 Seashell Playa9 | 189602.64 | 163740.84 | 0 | 163740.84
U7-SEASHELL | IPC6&7TR0064 | 6 | U7-SEASHELL6 | 952362.67 | 734764.32 | 0 | 734764.32
Egyptian Exchange Building | Egy Exchange IPC3 | 3 | Egyptian Exchange Building3 | 67025016.19 | 8019519.9995 | 0 | 60139519.9995
ora zed orascom | IPC04TR0069 | 4 | ora zed orascom4 | 634024.87 | 573657.258 | 0 | 573657.258
ORA-ZED Towers P01B | IPC10,11 TR51 | 10 | ORA-ZED Towers P01B10 | 294299.88 | 260602.55 | 0 | 260602.55
MDF Factory | Mdf Factory ipc 30 | 30 | MDF Factory30 | 46563799.32 | 11554812.9428 | 19556786 | 31111598.9428
SSC Suez Steel Company Project | int&rut sup ABB ipc6 | 6 | SSC Suez Steel Company Project6 | 4670440.09 | 3667977.9926 | 1609619.31 | 5277597.3026
Waldorf Astoria Cairo | Waldorf IPC 20 | 20 | Waldorf Astoria Cairo20 | 3956218.97 | 0 | 0 | 3400771.9975
VILLA CLUSTER C | IPC06TR0078 | 6 | VILLA CLUSTER C6 | 180226.88 | 155643.94 | 0 | 155643.94
Mohamed Ali Palace Restoration | Mohamed Aly IPC Fin |  | Mohamed Ali Palace Restoration | 1527763.81 | 1438745 | 0 | 1438745
MAF HQ Renovation | Carrefour Head ipc 5 | 5 | MAF HQ Renovation5 | 1000709.81 | 935663.6624 | 0 | 935663.6624
U3 & U5 | IPC15TR0055 | 15 | U3 & U515 | 37130.4 | 28388.9 | 0 | 28388.9
Air Defense College | Air Dev fire IPC2 | 2 | Air Defense College2 | 402502 | 338700 | 0 | 338700
Air Defense College | Air dev elec IPC2 | 2 | Air Defense College2 | 34088309 | 28718990 | 0 | 28718990
R05 (New) | IPC001 TR59 | 1 | R05 (New)1 | 100800 | 85488.48 | 0 | 85488.48
New Giza Teaching Hospital | New Giza ipc 19 | 19 | New Giza Teaching Hospital19 | 8254281.5 | 4118256.08 | 1119307 | 7237562.975
HST Bridges-Sokhna & Mahager | sokhna Br. ipc14+15 | 14 | HST Bridges-Sokhna & Mahager14 | 84796100 | 10610468.95 | 0 | 76158305.95
Faculty of Medicine | mansora finish ipc08 | 8 | Faculty of Medicine8 | 5998094.29 | 4475076.3245 | 899714.14 | 5374790.4645
Faculty of Medicine | MANSOURA IPC13 | 13 | Faculty of Medicine13 | 2416869.52 | 2044633.986 | 120843.48 | 2165477.466
NUCA R05 - Z02 | R05(2) ipc 28 | 28 | NUCA R05 - Z0228 | 33756896.45 | 27484539.3825 | 3452627.4 | 30937166.7825
Seashell Playa 5 Villas | playa c072- ipc 5 | 5 | Seashell Playa 5 Villas5 | 16407.14 | 13662.44 | 0 | 13662.44
Astoria Sharm elSheikh | Woldorf sharm ipc 7 | 7 | Astoria Sharm elSheikh7 | 1116626 | 1160163.51 | 0 | 1160163.51
SSC Suez Steel Company Project | Baraka Fance ipc 2 | 2 | SSC Suez Steel Company Project2 | 12315634 | 8497787.46 | 3694690.2 | 12192477.66
SSC Suez Steel Company Project | Baraka Fance ipc 1 | 1 | SSC Suez Steel Company Project1 | 3575400 | 2467026 | 1072620 | 3539646
SSC Suez Steel Company Project | New Gas Station ipc1 | 1 | SSC Suez Steel Company Project1 | 3190160 | 2201210.4 | 957048 | 3158258.4
SSC Suez Steel Company Project | svc ipc 2 | 2 | SSC Suez Steel Company Project2 | 649999.96 | 438843.8784 | 194999.99 | 633843.8684
Capital One | inv ( 11 ) Captal 1 | 11 | Capital One11 | 695119.09 | 0 | 204831.941 | 204831.941
Air Defense College | Air dif finish4 IPC2 | 2 | Air Defense College2 | 2903787 | 2446040 | 0 | 2446040
U6T11 PART1 Palay | IPC02TR0075 | 2 | U6T11 PART1 Palay2 | 9785.91 | 8940.4 | 0 | 8940.4
VILLA CLUSTER C | IPC04TR0078 | 4 | VILLA CLUSTER C4 | 25709 | 19802.29 | 0 | 19802.29
NUCA R05 - Z02 | R05(2) ipc 42 | 42 | NUCA R05 - Z0242 | 11620344.48 | 18419500.05 | 2288683.38 | 20708183.43
El-Warraq | IPC 3 elwaraq | 3 | El-Warraq3 | 500000 | 250000 | 0 | 250000
Wady El Natroon Bridge | Wady elnatroon ipc07 | 7 | Wady El Natroon Bridge7 | 83651195.24 | 34583009.36 | 0 | 74583009.36
MAF HQ Renovation | Carrefour RBS IPC 3 | 3 | MAF HQ Renovation3 | 4802157.24 | 3229450.7297 | 1260566.28 | 4490017.0097
HST Bridges-Sokhna & Mahager | Sokhna Bri esc.1:13 |  | HST Bridges-Sokhna & Mahager | 60656018.52 | 54080509.31 | 0 | 54080509.31
Mivida BP#189 | Emaar pkg#189 ipc 23 | 23 | Mivida BP#18923 | 30858954.29 | 14242173.0845 | 11334411.03 | 25576584.1145
EGAT Injection | IPC09&10 TR48 | 9 | EGAT Injection9 | 645079.47 | 553542.7 | 0 | 553542.7
Katameya Creeks - RME | IPC 12 TR53 | 12 | Katameya Creeks - RME12 | 5318.22 | 4709.29 | 0 | 4709.29
Kattmeya Creeks Urban | IPC03TR0071 | 3 | Kattmeya Creeks Urban3 | 41136.72 | 36426.55 | 0 | 36426.55
Egyptian Exchange building | IPC14TR0039 | 14 | Egyptian Exchange building14 | 109001.62 | 96520.93 | 0 | 96520.93
ORA ZED-Ph 2-Pkgs A&D | ora zed ph2 ipc02 | 2 | ORA ZED-Ph 2-Pkgs A&D2 | 21711682.2 | 21766847.47 | 2589823.21 | 24356670.68
Alamein Coastal Road Bridge | Alamein L&L IPCFin |  | Alamein Coastal Road Bridge | 986396.2 | 814290 | 0 | 814290
NUCA R05 - Z02 | R05(2) ipc44 | 44 | NUCA R05 - Z0244 | 12139548.9 | 10677961.28 | 1397680.9 | 12075642.18
Port Said Port Silos | Silos supp.EUR ipc01 | 1 | Port Said Port Silos1 | 5539353.23 | 5982501.4522 | 0 | 5982501.4522
SOL Town PKG.220 | PKG#220-IPC5=6 | 5 | SOL Town PKG.2205 | 618792.62 | 1020348.63 | 0 | 1020348.63
South Dabaa Axis | IPC#003 | 3 | South Dabaa Axis3 | 985584 | 872734.53 | 0 | 872734.53
WADY EL-NATROUN BRIDGE(HST) | IPC no14.. |  | WADY EL-NATROUN BRIDGE(HST) | 1043040 | 212337.14 | 0 | 212337.14
TOSHKA MADKOUR | IPC1TR0083 | 1 | TOSHKA MADKOUR1 | 1127761.2 | 983613.269 | 0 | 983613.269
Central Capital | INV ( 3 ) Central Ca | 3 | Central Capital3 | 160704 | 151061.76 | 0 | 151061.76
U3 & U5 | IPC18TR0055 | 18 | U3 & U518 | 180942.4 | 156261.82 | 0 | 156261.82
EGAT Injection | IPC13TR0048 | 13 | EGAT Injection13 | 631336.15 | 536749.55 | 0 | 536749.55
U4,U8 Seashell Playa | IPC11TR0060 | 11 | U4,U8 Seashell Playa11 | 394380 | 340586.57 | 0 | 340586.57
EPICO 3 Facility | Eipico ipc 15 | 15 | EPICO 3 Facility15 | 41894786.25 | 29236255.9825 | 9828182.53 | 39064438.5125
Kayan Landscape | El ROUDA Final |  | Kayan Landscape | 45197888 | 22844380 | 20804601.2 | 43648981.2
Port Said Port Silos | port said ipc23 | 23 | Port Said Port Silos23 | 3587901.46 | 2851855.8684 | 358790.15 | 3210646.0184
Mivida BP#189 | pkg#189-IPC9 | 9 | Mivida BP#1899 | 42271935.1 | 39465389.045 | 4752382.96 | 44217772.005
ORA ZED - Ph 01B - Pkgs A&D | Ora ph.1 - IPC 22 | 22 | ORA ZED - Ph 01B - Pkgs A&D22 | 9997079.14 | 8609716.257 | 1021782.75 | 9631499.007
Maspiro Towers | Final |  | Maspiro Towers | 366600 | 182637.31 | 0 | 182637.31
Egat Rolling Mill no.4 | Rolling Mill ipc 15 | 15 | Egat Rolling Mill no.415 | 16836028.87 | 17509470.0248 | 0 | 17509470.0248
Rabigh PP - Piling Works | Inv-02 | 2 | Rabigh PP - Piling Works2 | 833736.43 | 2876390.67 | 0 | 958796.89
Cairo-Alex Railway | Cairo-alex Esc.20:41 |  | Cairo-Alex Railway | 53378141.9 | 33855194.7 | 0 | 33855194.7
Sokhna Port Expansion | SPX.2 ipc06 | 6 | Sokhna Port Expansion6 | 29655965.5 | 20436715.16 | 5931193.1 | 26367908.26
EGAT Mechanical Installations | Egat Mechnical ipc 4 | 4 | EGAT Mechanical Installations4 | 1192474.42 | 906161.31 | 298118.6161 | 1204279.9261
Irrigation Tank | IPC08TR0061 | 8 | Irrigation Tank8 | 14632.2 | 12618.37 | 0 | 12618.37
Qasr Rashwan Lot A | QASRRASHWAN A 1 |  | Qasr Rashwan Lot A | 14222820.57 | 28292815.4 | 0 | 28292815.4
SSC Suez Steel Company Project | L4283/2024 |  | SSC Suez Steel Company Project | 5000000 | 4450000 | 0 | 4450000
SSC Suez Steel Company Project | L 4291/2024 |  | SSC Suez Steel Company Project | 35000000 | 31150000 | 0 | 31150000
Abou Ghaleb Bridge | ABOGHALEBIPC21+22+23 | 21 | Abou Ghaleb Bridge21 | 12272074.19 | 11210771.93 | 0 | 11210771.93
Qasr Rashwan - Lot B | QASR RASHWAN B IPC1 | 1 | Qasr Rashwan - Lot B1 | 14763938.35 | 53919655.04 | 0 | 53919655.04
U4,U8 Seashell Playa | IPC17TR0060 | 17 | U4,U8 Seashell Playa17 | 413660.75 | 324493.78 | 0 | 324493.78
Irrigation Tank | IPC11TR0061 | 11 | Irrigation Tank11 | 821545.02 | 528535.34 | 0 | 528535.34
R05 (New) | IPC08TR0059 | 8 | R05 (New)8 | 252601 | 214230.91 | 0 | 214230.91
El Khatatba Bridge | el khatatba ipc05 | 5 | El Khatatba Bridge5 | 3556116.67 | 3052936.75 | 0 | 3052936.75
HST El Mahager Bridge | Elmahager esc.2:7 |  | HST El Mahager Bridge | 16043483.57 | 14216135.8443 | 0 | 14216135.8443
Seashell Playa 5 Villas | Playa - C470 ipc 2 | 2 | Seashell Playa 5 Villas2 | 23114.7 | 19961.84 | 0 | 19961.84
Ain Sokhna Bridge | Inv ( 6 ) A.S | 6 | Ain Sokhna Bridge6 | 333124.5 | 89916.11 | 0 | 89916.11
EPICO 3 Facility | Eipico ipc 18 | 18 | EPICO 3 Facility18 | 61115227.87 | 35188037.3 | 17000000 | 52188037.3
Roubiky Hassan Allam | IPC#4#Roubiky | 4 | Roubiky Hassan Allam4 | 498750 | 415957.5 | 0 | 415957.5
Lekela 250MW Wind Farm | LEKELA IPC2=4 | 2 | Lekela 250MW Wind Farm2 | 6153867.61 | 6400022.31 | 0 | 6400022.31
Rabigh PP - Piling Works | Inv-05 | 5 | Rabigh PP - Piling Works5 | 983150.55 | 3391869.39 | 0 | 1130623.13
El Khatatba Bridge | EL KHATBA ESC 1:12 |  | El Khatatba Bridge | 2221940 | 2145997.56 | 0 | 2145997.56
Abou Ghaleb Bridge | ABO GHALEB ESC 1:20 |  | Abou Ghaleb Bridge | 10360450.48 | 10007798.33 | 0 | 10007798.33
RADAMIS CITY | IPC06TR0084 | 6 | RADAMIS CITY6 | 236604.69 | 209513.46 | 0 | 209513.46
Damietta Container Termin | Damietta Pkg 3 ipc 1 | 1 | Damietta Container Termin1 | 1617841.39 | 1520770.9061 | 0 | 1520770.9061
EIPICO C002-23 | IPC11TR0068 | 11 | EIPICO C002-2311 | 45656.8 | 39178.09 | 0 | 39178.09
Irrigation Tank | IPC13TR0061 | 13 | Irrigation Tank13 | 956644.13 | 826157.86 | 0 | 826157.86
EGAT Injection | IPC08 TR48 | 8 | EGAT Injection8 | 42833.9 | 36755.76 | 0 | 36755.76
6 Octobar Stores | IPC01TR0072 | 1 | 6 Octobar Stores1 | 215768 | 60000 | 0 | 60000
Port Saad Industiral zone | IPC#3 | 3 | Port Saad Industiral zone3 | 5078250 | 4888354.75 | 0 | 4888354.75
Seashell Playa 5 Villas | Playa c470 ipc 5 | 5 | Seashell Playa 5 Villas5 | 165704.92 | 143102.76 | 0 | 143102.76
Seashell Playa 5 Villas | playa C469 IPC 8 | 8 | Seashell Playa 5 Villas8 | 75504.2 | 18980.64 | 0 | 18980.64
Seashell Playa 5 Villas | Playa c470 ipc 4 | 4 | Seashell Playa 5 Villas4 | 327640.22 | 265950.1 | 0 | 265950.1
Abo Ghaleb | IPC #1 Abo Ghaleb |  | Abo Ghaleb | 1116000 | 1007589.6 | 0 | 1007589.6
AL-JAWHARA PALACE | IPC02TR0095 | 2 | AL-JAWHARA PALACE2 | 41343.75 | 35352.85 | 0 | 35352.85
Roof-Playa Cluster A,B,C | IPC14TR0088 | 14 | Roof-Playa Cluster A,B,C14 | 484211.55 | 418165.09 | 0 | 418165.09
U4,U8 Seashell Playa | IPC20TR0060 | 20 | U4,U8 Seashell Playa20 | 193785.15 | 167352.86 | 0 | 167352.86
Suez Gulf Substation | 180082 |  | Suez Gulf Substation | -34750.14 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 9 EGP South Helwan |  | South Helwan PP (CP-117) | 306120.3143 | 0 | 0 | #DIV/0!
Kuwait | Cr.P-10-14 | 10 | Kuwait10 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | CN Semeins |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
El-Warraq | IPC4 elwaraq | 4 | El-Warraq4 | 198000 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 5001-3 | 3 | AWEER POWER STATION 'H' Phase3 | 20326473.22 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | Credit closing pip |  | Pyramids Industrial Park | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 60 |  | Suez Gulf Substation | 3367588.23 | 0 | 0 | #DIV/0!
Suez Gulf Substation | CR-Inv#180163 | 180163 | Suez Gulf Substation180163 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 94 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | CR - IPC#23 | 23 | El Boghaz Brigde23 | 0 | 0 | 0 | #DIV/0!
Toshka Farm | CR.Toshka Farm Inv.3 | 3 | Toshka Farm3 | 0 | 0 | 0 | #DIV/0!
Nagaa Hamady/Assuit OHTL | Soc.2020 تشيد سكرخط |  | Nagaa Hamady/Assuit OHTL | 5000 | 0 | 0 | #DIV/0!
Masr ELgedeeda | D0040-OB-Dec-2020/Cr | 2020 | Masr ELgedeeda2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 34 |  | Al-Shabab PP Phase II (CP-117) | 69952.76 | 0 | 0 | #DIV/0!
Hosh Essa 220 KV OHTL | Hosh Essa USD Inv.01 | 1 | Hosh Essa 220 KV OHTL1 | 148906.67 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 20 ) GET | 20 | Get Business Complex20 | 1252073.23 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 5 |  | Zafranaa - Ras Ghareb | 184627.45 | 0 | 0 | #DIV/0!
10th Ramadan Indu Park Plot11 | P-30-EGY اتحاد تشيد | 30 | 10th Ramadan Indu Park Plot1130 | 5000 | 0 | 0 | #DIV/0!
Railway Bridge - Assuit | final inv Assuit |  | Railway Bridge - Assuit | 834490 | 0 | 0 | #DIV/0!
Abo Shanab El Agamien | cr-abo shanab ipc01 | 1 | Abo Shanab El Agamien1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 11 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 191040 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | Zafra Souf Final7civ |  | Zafranaa - Beni Suef | 39761 | 0 | 0 | #DIV/0!
SSC Suez Steel Company Project | L965/2024 |  | SSC Suez Steel Company Project | 34361114 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180086 |  | Suez Gulf Substation | -314814.82 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 1907220003 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | IPC-3 | 3 | Taval Sarai 523 | 0 | 0 | 0 | #DIV/0!
Nagaa Hamady/Assuit OHTL | تجديد تشيد وبناء2020 |  | Nagaa Hamady/Assuit OHTL | 5250 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 64 |  | Al-Shabab PP Phase II (CP-117) | 43006715.6568 | 0 | 0 | #DIV/0!
Residence 8 ( S09 ) | Cr. Inv ( 1 ) S 09 | 1 | Residence 8 ( S09 )1 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | Pole.Cvr.Inv.1.Cncl | 1 | Ghana Street lighting1 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv12 | 12 | Akhmem - Qena12 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj.180132 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Residence 8 ( K10 ) | Inv ( 2 ) K 10 | 2 | Residence 8 ( K10 )2 | 125124.61 | 0 | 0 | #DIV/0!
Ministries Buildings | CR-MinistSHELLIPC08 | 8 | Ministries Buildings8 | 0 | 0 | 0 | #DIV/0!
Bahr ElBakar – Power Station | CR IPC#7 Madkour | 7 | Bahr ElBakar – Power Station7 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 66 |  | Al-Shabab PP Phase II (CP-117) | 3315761.7192 | 0 | 0 | #DIV/0!
Railway Bridge - Alex | Credit Memo FPC |  | Railway Bridge - Alex | 0 | 0 | 0 | #DIV/0!
Canal Sugar 33KV OHTL | Cr. 4 Sugar 33 OHTL |  | Canal Sugar 33KV OHTL | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | ipc no2 aswan |  | Aswan axis - Daraw | 529916 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2103220003 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr.Adj Inv. 18 | 18 | Zafranaa - Ras Ghareb18 | 0 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | 31 EGP-Giza Nor.III |  | Giza North PP Phase3(CP-117) | 613545.1238 | 0 | 0 | #DIV/0!
EMAAR-PKG#62-UPTOWN | OB-RE-PKG#62 |  | EMAAR-PKG#62-UPTOWN | 136616.41 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | CR ipc4 aswan | 4 | Aswan axis - Daraw4 | -431029.25 | 0 | 0 | #DIV/0!
Air Defence College | CAN. IPC26TR0046 | 26 | Air Defence College26 | 0 | 0 | 0 | #DIV/0!
Port Saad Industiral zone | CR-IPC#8 | 8 | Port Saad Industiral zone8 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | ENG 056 |  | AWEER POWER STATION 'H' Phase | 804156.68 | 0 | 0 | #DIV/0!
158E/2019 33kv Project | 11544 |  | 158E/2019 33kv Project | 203400 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_INV.10 | 10 | Akhmem Assiut10 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv-03 | 3 | MOC HQ at Diriyah3 | 4468396.86 | 0 | 0 | #DIV/0!
Almaza | Cr. Inv 02 | 2 | Almaza2 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | Cr -7-EGP-West D.117 | 7 | W Dam PP Phase II (CP-117)7 | 0 | 0 | 0 | #DIV/0!
Beni Suef Substation R61 | BSF-SW-EGP-12 FINAL | 12 | Beni Suef Substation R6112 | 8750 | 0 | 0 | #DIV/0!
Racecores 3092-16 132KV C | 11343 |  | Racecores 3092-16 132KV C | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 55 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180085 |  | Suez Gulf Substation | 873.48 | 0 | 0 | #DIV/0!
Port Said Grain Storage | Credit |  | Port Said Grain Storage | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Proj-CR Adj. Inv. 15 | 15 | Abou El Matameer and Sammanoud15 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 8 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1320080.7429 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/004Cnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2104210004 |  | Manshiet Nasser Substation | 130476.19 | 0 | 0 | #DIV/0!
Taval Sarai 52 | IPC-21-SARAY | 21 | Taval Sarai 5221 | 249351.7 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Cr. Inv. 27 Usd | 27 | Marsa Alam/ Bernes LOT2 OHTL27 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 19 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 415138.7619 | 0 | 0 | #DIV/0!
Sewage Treatment Plant | D0024-OB-Dec-2020/Cr | 2020 | Sewage Treatment Plant2020 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 6 Euro-South Helwan |  | South Helwan PP (CP-117) | 919171.0286 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180023 |  | Suez Gulf Substation | -336730.54 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply. Inv.5 Ret | 5 | Ghana Street lighting5 | 6457.52 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 470 |  | TZ – Offshore E&M Procurement | 1624155.5 | 0 | 0 | #DIV/0!
EL Baragil Bridge | inv ( 5 ) Baragill B | 5 | EL Baragil Bridge5 | 1052415 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 271 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
K047 FDH JV | CR.10-16(2) | 16 | K047 FDH JV16 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 346 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Ref.1 samanud-mat T |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
Aswan- Belana 60K m³/day WWTP | 10225 |  | Aswan- Belana 60K m³/day WWTP | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | 10007 |  | El Boghaz Brigde | 401882.16 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH inv.32 deductions | 32 | South Helwan PP (CP-117)32 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 15 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 146711.5048 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | 7 |  | Barwa 2x60/22 KV S/S | 1280709.49 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 475 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref Akhmm Asuit2T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Almaza | Credit Retention |  | Almaza | 0 | 0 | 0 | #DIV/0!
10Th of Ramadan LRT | CR.10Ramadan Inv.02 | 2 | 10Th of Ramadan LRT2 | 0 | 0 | 0 | #DIV/0!
Bashteel - Tahya Masr Bridge | IPC#3# FINAL#TAHYA M | 3 | Bashteel - Tahya Masr Bridge3 | 1528500 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 468 |  | TZ – Offshore E&M Procurement | 0 | 0 | 0 | #DIV/0!
Port Said Grain Storage | credit ipc 11 | 11 | Port Said Grain Storage11 | -1014666 | 0 | 0 | #DIV/0!
El Salam Bridge | D0048 OB-Dec-2020/Cr | 2020 | El Salam Bridge2020 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 284 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Inv.5 Deductions | 5 | Assuit PP (CP-118)5 | 0 | 0 | 0 | #DIV/0!
PIP- Zonafranca | Cr Adj Inv 5 | 5 | PIP- Zonafranca5 | 0 | 0 | 0 | #DIV/0!
The Open Channel Project | OPEN CHANEL IPC 2 | 2 | The Open Channel Project2 | 125541216 | 0 | 0 | #DIV/0!
SHUQAIQ High Voltage Works | 2 |  | SHUQAIQ High Voltage Works | 2881950.1 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11661 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
El-Herafeen brigde | D0042-OB-Dec-2020/Cr | 2020 | El-Herafeen brigde2020 | 0 | 0 | 0 | #DIV/0!
U3 & U5 | CR-55/1 | 55 | U3 & U555 | 0 | 0 | 0 | #DIV/0!
Baron Palace | CR.TR0014CLOSING.DEC |  | Baron Palace | 0 | 0 | 0 | #DIV/0!
Closed | OB-ST |  | Closed | 0.89 | 0 | 0 | #DIV/0!
Suez Gulf Substation | CR-Closing #180162 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
EIPICO Factory | ipc05 tr0054 | 5 | EIPICO Factory5 | 0 | 0 | 0 | #DIV/0!
Elsewedy Univ - Enabling Works | CMsewedy uni-mep-07 | 7 | Elsewedy Univ - Enabling Works7 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 2104220007 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Algeria S/Ss | Cr.P-14-12 | 14 | Algeria S/Ss14 | 0 | 0 | 0 | #DIV/0!
Beni Suef COMCAVI | 1907220004 |  | Beni Suef COMCAVI | 0 | 0 | 0 | #DIV/0!
El-Warraq | CR IPC4 elwaraq | 4 | El-Warraq4 | -198000 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 254 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
New Capital | Credit inv5 El Tbeen | 5 | New Capital5 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 252 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | cr ( inv 5 ) ola | 5 | Al-Ula Towers5 | 0 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/003Cnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
U3 & U5 | TR55-CR3 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2008220003 |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
Attaqa Power Plant | Discount int. |  | Attaqa Power Plant | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Refund reten.closing |  | Zafranaa - Ras Ghareb | 39998.65 | 0 | 0 | #DIV/0!
Sodic East | 10113 |  | Sodic East | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2012210007 |  | Manshiet Nasser Substation | 16138.58 | 0 | 0 | #DIV/0!
New Heliopolis | Cancel inv. 7 | 7 | New Heliopolis7 | 0 | 0 | 0 | #DIV/0!
Berket Ghelion | Cr Adj Inv 7 | 7 | Berket Ghelion7 | 0 | 0 | 0 | #DIV/0!
K047 FDH JV | CR.p-10-16 | 10 | K047 FDH JV10 | 0 | 0 | 0 | #DIV/0!
U3 & U5 | TR055-Cr 1 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
HSR-6th of October | ipc 8 hsr | 8 | HSR-6th of October8 | 279040 | 0 | 0 | #DIV/0!
Infra Project 2524 | 2112210002 |  | Infra Project 2524 | 86140000 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | rev. ( 8 EGP-West D. |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Canal Sugar 33KV OHTL | Soc.2020 تشيدسكر 33 |  | Canal Sugar 33KV OHTL | 5000 | 0 | 0 | #DIV/0!
Katameya Creeks - RME | CREDITIPC15 | 15 | Katameya Creeks - RME15 | 0 | 0 | 0 | #DIV/0!
Canal Sugar OHTL | Inv.12 Fi Sugar OHTL | 12 | Canal Sugar OHTL12 | 258580.7 | 0 | 0 | #DIV/0!
Akhmem Assiut | Ref.soci 53-54 Asut | 54 | Akhmem Assiut54 | 1949254 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 89 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr - 2 USD - Shabab | 2 | Al-Shabab PP Phase II (CP-117)2 | 0 | 0 | 0 | #DIV/0!
Industria Sadat | Cr.Sadat Indust Inv3 | 3 | Industria Sadat3 | 0 | 0 | 0 | #DIV/0!
October Dry Port Railway | CR-ODP ipc03 | 3 | October Dry Port Railway3 | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | 2104220004 |  | Banha PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Benban 4 As El-Nakra 220 K.V | CR. 1 Final ElNokra |  | Benban 4 As El-Nakra 220 K.V | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-KAFR SHOKR1 |  | Kafr Shokr Bridge | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | Cr-egy exch Ipc1 | 1 | Egyptian Exchange Building1 | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-Kafr shokr-IPC02 | 2 | Kafr Shokr Bridge2 | 0 | 0 | 0 | #DIV/0!
EPICO 3 Facility | material ipc 3 | 3 | EPICO 3 Facility3 | 4910817.01 | 0 | 0 | 5156357.8605
Open Channel 2 | IPC02TR0099 | 2 | Open Channel 22 | 1537200 | 0 | 0 | 1537200
Abo Ghaleb | IPC#2#Abo Ghaleb | 2 | Abo Ghaleb2 | 1272000 | 0 | 0 | 1272000
Hosh Eisa Hospit. | IPC02TR0089 | 2 | Hosh Eisa Hospit.2 | 222500.25 | 0 | 0 | 222500.25
Open Channal | IPC01TR00074 | 1 | Open Channal1 | 322560 | 0 | 0 | 0
U7-SEASHELL | IPC12TR0064 | 12 | U7-SEASHELL12 | 24635.46 | 0 | 0 | 24635.46
PLAYA ROOF & Wet Areas | IPC00022 TR41 | 22 | PLAYA ROOF & Wet Areas22 | 254226.68 | 0 | 0 | 254226.68
Kemet Tower | INV ( 9 ) Kemet | 9 | Kemet Tower9 | 185120 | 0 | 0 | 185120
Al-Ula Towers | inv ( 4 ) final | 4 | Al-Ula Towers4 | 564113.41 | 0 | 0 | 592319.0805
U3 & U5 | TR0055 |  | U3 & U5 | 439984.49 | 0 | 0 | 439984.49
ORA ZED - Ph 01B - Pkgs A&D | ORA PH.1- IPC23 | 23 | ORA ZED - Ph 01B - Pkgs A&D23 | 27314036.02 | 0 | 0 | 28679737.821
Ministries Buildings | Mini Core IPC11 | 11 | Ministries Buildings11 | 27963228 | 0 | 0 | 27963228
Kayan 3 New Cairo Capital City | 30/11/22Armed Force |  | Kayan 3 New Cairo Capital City | 313092002.03 | 0 | 0 | 313092002.03
Assuit PP (CP-118) | 220721002 |  | Assuit PP (CP-118) | 688101.53 | 0 | 0 | 720868.27
Ghana Street lighting | MCBs inv. No.1 | 1 | Ghana Street lighting1 | 37125 | 0 | 0 | 37125
Ghana Street lighting | Pole. Cvr. Inv.1 | 1 | Ghana Street lighting1 | 11690 | 0 | 0 | 11690
LAYAN Substation | 11459 |  | LAYAN Substation | 204999.08 | 0 | 0 | 215249.034
Racecores 3092-17 132KV E | 11448 |  | Racecores 3092-17 132KV E | 6625.33 | 0 | 0 | 6625.33
Cairo Monorail - 6th October | IPC#7 - Monorail | 7 | Cairo Monorail - 6th October7 | 1271000 | 0 | 0 | 1271000
Assuit PP (CP-118) | 2110210003 |  | Assuit PP (CP-118) | 13996866.29 | 14556740.94 | 0 | 14556740.94
Ahl Misr P3 – Zamalek Sector | IPC#5 Zamalek | 5 | Ahl Misr P3 – Zamalek Sector5 | 193800 | 0 | 0 | 193800
R05 | IPC_1_R5 |  | R05 | 77798.38 | 0 | 0 | 77798.38
Kafr Shokr Bridge | Kafr Shokr - IPC02 | 2 | Kafr Shokr Bridge2 | 7001830.48 | 0 | 0 | 7351922.004
Street Lighting Fayoum | Fayoum Street Inv.01 | 1 | Street Lighting Fayoum1 | 32271820 | 24688585 | 0 | 26225338.33
ORA-ZED Towers01B | TR0029DEC.Closing |  | ORA-ZED Towers01B | 402666.55 | 0 | 0 | 402666.55
ElMarg | D0043-OB-Dec-2020 | 2020 | ElMarg2020 | 1093100 | 0 | 0 | 1093100
El Zagazig Railway P2 | D0044-OB-Dec-2020 | 2020 | El Zagazig Railway P22020 | 489480 | 0 | 0 | 489480
Baron Palace | TR0014DEC.Closing |  | Baron Palace | 25484.8 | 0 | 0 | 25484.8
Al-Kayan | TR0012DEC.Closing |  | Al-Kayan | 30861.52 | 0 | 0 | 30861.52
Port Saad Industiral zone | D0022-OB-Dec-2020 | 2020 | Port Saad Industiral zone2020 | 32210212.84 | 0 | 0 | 32210212.84
C5 Bridge 2 New Alamein | D0011-OB-Dec-2020 | 2020 | C5 Bridge 2 New Alamein2020 | 13334667.5 | 0 | 0 | 13334667.5
Almaza Bridge - Safir 2 | D0023-OB-Dec-2020 | 2020 | Almaza Bridge - Safir 22020 | 444300 | 0 | 0 | 444300
Ministries A13-A14 | IPC_3_RedSea |  | Ministries A13-A14 | 48401 | 0 | 0 | 48401
El Mostakbal City Project | مد وثيقة تامين P-76 | 76 | El Mostakbal City Project76 | 279055 | 0 | 0 | 279055
Manshiet Nasser Substation | 496 |  | Manshiet Nasser Substation | 851958.87 | 73380.4 | 137121.85 | 210502.25
LAYYAH CCPP | 473 |  | LAYYAH CCPP | 1233824 | 0 | 0 | 1233824
Maspiro Towers | IPC005 | 5 | Maspiro Towers5 | 556650 | 277111.8 | 0 | -279538.2
Suez Gulf Substation | 12 EGP - Suez Gulf |  | Suez Gulf Substation | 598540.9905 | 565621.24 | 62846.8 | 628468.04
Suez Gulf Substation | 19 EGP VO Progress |  | Suez Gulf Substation | 331289.87 | 313657.81 | 34850.87 | 348508.68
Manshiet Nasser Substation | 1903210014 |  | Manshiet Nasser Substation | 952380.95 | 990476.19 | 0 | 990476.19
Abu Qir PP (CP-117) | 1907210013 |  | Abu Qir PP (CP-117) | 17136.36 | 17136.36 | 0 | 17136.36
Suez Gulf Substation | 1909210010 |  | Suez Gulf Substation | 499195.28 | 499195.28 | 0 | 499195.28
Suez Gulf Substation | custom release inv. |  | Suez Gulf Substation | 3379.7 | 0 | 0 | 3379.7
Beni-Suef Power Plant EPC | reclass of rec acc |  | Beni-Suef Power Plant EPC | 986446760.8 | 986446760.8 | 0 | 986446760.8
Ain-Sokhna PP (CP-117) | 180137 |  | Ain-Sokhna PP (CP-117) | 28054.69 | 28251.08 | 0 | 28251.08
Beni-Suef Power Plant EPC | 14 Egp - Beni Suef |  | Beni-Suef Power Plant EPC | 178425894.88 | 52519653.75 | 0 | 118140371.3333
Beni-Suef Power Plant EPC | INV 11,12,13 | 11 | Beni-Suef Power Plant EPC11 | 373718132 | 355718132.02 | 0 | 355718132.02
Akhmem Assiut | Soc Inv 44 To 47 Asu | 44 | Akhmem Assiut44 | 2259485.5 | 0 | 0 | 2259485.5
EMAAR-PKG#53-UPTOWN | PKG#85/53- IPC5 | 5 | EMAAR-PKG#53-UPTOWN5 | 1941977.98 | 0 | 0 | 1941977.98
MAYSAN 400/132kV SS | Cancel Cr no. 227 |  | MAYSAN 400/132kV SS | 87293.1 | 0 | 0 | 87293.1
Algeria S/Ss | P-14-12 ADJ | 14 | Algeria S/Ss14 | 5381425.43 | 0 | 0 | 5381425.43
Angola Emergency fast-track | P-13-2016 ADJ | 13 | Angola Emergency fast-track13 | 213247445.16 | 0 | 0 | 213247445.16
Cameron EDC | 5007 ADJ |  | Cameron EDC | 158805.85 | 0 | 0 | 158805.85
W Dam PP Phase II (CP-117) | 180097 |  | W Dam PP Phase II (CP-117) | 204014.88 | 182425.78 | 32192.78 | 214618.56
South Helwan PP (CP-117) | 180160 |  | South Helwan PP (CP-117) | 474288.1 | 474288.1 | 0 | 474288.1
W Dam PP Phase II (CP-117) | DM for wrong CR |  | W Dam PP Phase II (CP-117) | 368421.1 | 368421.1 | 0 | 368421.1
W Dam PP Phase II (CP-117) | 14 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 15152.72 | 15152.72 | 0 | 15152.72
South Helwan PP (CP-117) | 180159 |  | South Helwan PP (CP-117) | 10765415.4579 | 10765415.4579 | 0 | 10765415.4579
W Dam PP Phase II (CP-117) | 5 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 1559713.65 | 0 | 0 | 1637699.3325
Al-Shabab PP Phase II (CP-117) | 180101 |  | Al-Shabab PP Phase II (CP-117) | 763512.3 | 682716.51 | 120479.38 | 803195.89
Al-Shabab PP Phase II (CP-117) | 9 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 87501.91 | 0 | 0 | 87501.91
Zafranaa - Beni Suef | Adj. Inv. 13 | 13 | Zafranaa - Beni Suef13 | 10668740.42 | 0 | 0 | 10668740.42
Abo Quir - Badr 500KV | Adj. Inv. 12 | 12 | Abo Quir - Badr 500KV12 | 936845184.82 | 0 | 0 | 936845184.82
Almaza | Adj Inv 11 | 11 | Almaza11 | 57111431.15 | 0 | 0 | 57111431.15
IRAQ - Al-Diwaniya Power Plant | Adjust |  | IRAQ - Al-Diwaniya Power Plant | 2.48 | 2.48 | 0 | 2.48
Al-Shabab PP Phase II (CP-117) | 180128 |  | Al-Shabab PP Phase II (CP-117) | 112317.65 | 0 | 0 | 112317.65
Siemens 6x500/220 KV GIS-MOU | Inv 92 P14 Assuit | 92 | Siemens 6x500/220 KV GIS-MOU92 | 2399962.85 | 0 | 0 | 2399962.85
Cairo Capital S1 | Inv. 1 S1 | 1 | Cairo Capital S11 | 66935348.57 | 0 | 0 | 66935348.57
Cairo South PP Rehabilitation | 17 |  | Cairo South PP Rehabilitation | 4211339 | 0 | 0 | 4211339
Beni Suef ISKRA | 180114 |  | Beni Suef ISKRA | 59610.29 | 0 | 0 | 59610.29
Abu Qir PP (CP-118) | 29 |  | Abu Qir PP (CP-118) | 505247.8464 | 0 | 0 | 505247.8464
Al-Shabab PP Phase II (CP-117) | 180027 |  | Al-Shabab PP Phase II (CP-117) | 150713.9429 | 0 | 0 | 158249.64
Ain-Sokhna PP(CP-102) | 115 |  | Ain-Sokhna PP(CP-102) | -456119.6566 | 0 | 0 | -456119.6566
GPC-Gupco (Automation) | 102 |  | GPC-Gupco (Automation) | 536503 | 0 | 0 | 536503
Banha PP (CP-117) | 72 |  | Banha PP (CP-117) | 4796013 | 0 | 0 | 4796013
Abu Qir PP (CP-117) | 92 |  | Abu Qir PP (CP-117) | 37084218.9299 | 0 | 0 | 37084218.9299
Giza North PP Ph I,II (CP-117) | 86 |  | Giza North PP Ph I,II (CP-117) | -32558726.54 | 0 | 0 | -32558726.54
Ain-Sokhna PP (CP-111) | 25 |  | Ain-Sokhna PP (CP-111) | 14463227 | 0 | 0 | 14463227
Palm Hill-Infra Str(Elec.Work) | 80 |  | Palm Hill-Infra Str(Elec.Work) | 1990286.4 | 0 | 0 | 1990286.4
W Dam PP Phase II (CP-117) | 180091 |  | W Dam PP Phase II (CP-117) | 91387.21 | 81716.51 | 14420.56 | 96137.07
W Dam PP Phase II (CP-117) | 76 |  | W Dam PP Phase II (CP-117) | 25302754.0435 | 0 | 0 | 25302754.0435
W Dam PP Phase II (CP-117) | 43 |  | W Dam PP Phase II (CP-117) | 1462827.83 | 0 | 0 | 1462827.83
W Dam PP Phase II (CP-117) | 46 |  | W Dam PP Phase II (CP-117) | 34268600.208 | 0 | 0 | 34268600.208
Akhmem - Qena | Inv. 9 Akhmem Qena | 9 | Akhmem - Qena9 | 42408814.91 | 0 | 0 | 42408814.91
New Capital | Inv 7 Abo Zaabl | 7 | New Capital7 | 2859712.238 | 0 | 0 | 2859712.238
Abou El Matameer and Sammanoud | Soc73 abo almatamer |  | Abou El Matameer and Sammanoud | 217153.6 | 0 | 0 | 217153.6
W Dam PP Phase II (CP-117) | 4 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 117410.219 | -63008.75 | 18492.11 | 123280.73
Suez Gulf Substation | 4 USD/123/2011/2012 |  | Suez Gulf Substation | 78991.25 | 0 | 0 | 78991.25
Cameron EDC | 015/2019 |  | Cameron EDC | 153779165.65 | 153779165.65 | 0 | 153779165.65
Kuwait | Civil/H010 |  | Kuwait | 17126.78 | 12845.09 | 0 | 12845.09
Kuwait | Other Charge/H003 |  | Kuwait | 10656.5 | 6926.72 | 0 | 6926.72
Kuwait | Other Charge/H002 |  | Kuwait | 160091.58 | 104059.53 | 0 | 104059.53
Kuwait | 32-132KVA-H | 132 | Kuwait132 | 35058.07 | 26293.55 | 0 | 26293.55
Al-Shabab PP Phase II (CP-117) | 539 |  | Al-Shabab PP Phase II (CP-117) | 3454947.4 | 3290417.99 | 593819.09 | 3884237.08
W Dam PP Phase II (CP-117) | 180093 |  | W Dam PP Phase II (CP-117) | 490500.23 | 438594.9 | 77399.1 | 515994
W Dam PP Phase II (CP-117) | 18 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 415138.7524 | 0 | 65384.35 | 65384.35
Al-Shabab PP Phase II (CP-117) | 10 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 1159738.7714 | 0 | 0 | 182658.86
W Dam PP Phase II (CP-117) | 2 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 4486255.0593 | 0 | 681013.52 | 4540090.12
Suez Gulf Substation | 9 EGP - Suez Gulf |  | Suez Gulf Substation | 1870441.4095 | 1767567.13 | 196396.35 | 1963963.48
Suez Gulf Substation | 5 USD/123/2011/2012 |  | Suez Gulf Substation | 1610862.93 | 0 | 0 | 1610862.93
Barwa 2x60/22 KV S/S | Inv. Barwa 36 |  | Barwa 2x60/22 KV S/S | 1878094 | 1327624.65 | 281714.11 | 1609338.76
Barwa 2x60/22 KV S/S | Barwa 32 |  | Barwa 2x60/22 KV S/S | 361862.04 | 255985.36 | 54279.31 | 310264.67
Barwa 2x60/22 KV S/S | Inv 20 Barwa | 20 | Barwa 2x60/22 KV S/S20 | 1126765.28 | 796961.01 | 169014.8 | 965975.81
Damac 2x60/22 KV S/S | Inv. 34 Damac | 34 | Damac 2x60/22 KV S/S34 | 1035314.67 | 732199.48 | 155297.2 | 887496.68
South Helwan PP (CP-117) | 3 Euro- South Helwan |  | South Helwan PP (CP-117) | 2295948.56 | 344392.28 | 0 | 2410745.988
South Helwan PP (CP-117) | 9 EGP - South Helwan |  | South Helwan PP (CP-117) | 306120.3143 | 0 | 0 | 321426.33
South Helwan PP (CP-117) | 7 EGP South Helwan |  | South Helwan PP (CP-117) | 59582.1048 | 62561.21 | 0 | 62561.21
W Dam PP Phase II (CP-117) | 9 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 83661 | 12549.15 | 0 | 12549.15
Al-Shabab PP Phase II (CP-117) | 2 EGP - East Delta |  | Al-Shabab PP Phase II (CP-117) | 81321.502 | 69952.76 | 12344.6 | 82297.36
South Helwan PP (CP-117) | 11 Euro-South Helwan |  | South Helwan PP (CP-117) | 178521.4381 | 187447.51 | 0 | 187447.51
Al-Wukair 11 Substation | inv(ESC-SA-Civil-04) | 4 | Al-Wukair 11 Substation4 | 3479489.42 | 3131540 | 0 | 3131540
Al-Wukair 11 Substation | close unappl.sak |  | Al-Wukair 11 Substation | 5953437 | 5953437 | 0 | 5953437
Bani Suef Old Substation | (16) bani suf 2 | 16 | Bani Suef Old Substation16 | 20050269.42 | 9400122.62 | 8412274.32 | 17812396.94
Beni Suef Substation R61 | BSF-CW-EURO-07 | 7 | Beni Suef Substation R617 | 190702.25 | 141119.67 | 28605.34 | 169725.01
Ismailiya East Substation | ISE-CW-EGP-18 | 18 | Ismailiya East Substation18 | 4228827 | 3129331.98 | 634324.05 | 3763656.03
Tamey El-amdeed Substation | TAM-SW-EGP-09 | 9 | Tamey El-amdeed Substation9 | 743750 | 546530.01 | 111562.5 | 658092.51
Tamey El-amdeed Substation | TAM-CW-EGP-14 | 14 | Tamey El-amdeed Substation14 | 2825630.53 | 2090966.59 | 423844.58 | 2514811.17
Beni Suef Substation R61 | BSF-CW-12 | 12 | Beni Suef Substation R6112 | 1706896 | 1271637.52 | 256034.4 | 1527671.92
Beni Suef Substation R61 | BSF-CW-11 | 11 | Beni Suef Substation R6111 | 616504 | 459295.48 | 92475.6 | 551771.08
Beni Suef COMCAVI | 180116 |  | Beni Suef COMCAVI | 1064503.13 | 904573.8 | 159929.33 | 1064503.13
Berket Ghelion | Inv.20 Ghelion | 20 | Berket Ghelion20 | 2159222.36 | 1289715.1 | 539805.61 | 1829520.71
New Giza 2 | (25)new giza 2 | 25 | New Giza 225 | 3460724 | 5457989.56 | 726752.09 | 6184741.65
Giza North PP Ph I,II (CP-117) | Inv 41 Giza I,II | 41 | Giza North PP Ph I,II (CP-117)41 | 37658.6381 | 39541.57 | 0 | 39541.57
Giza North PP Phase3(CP-117) | 31 EGP - Giza N. III |  | Giza North PP Phase3(CP-117) | 613545.1238 | 547589.01 | 0 | 547589.01
Beni Seuf - 358 | Inv. 18 Oewon Mousa | 18 | Beni Seuf - 35818 | 7444976.6 | 0 | 1280375.85 | 1280375.85
Beni Seuf - 358 | Inv. 5 Oewon Mousa | 5 | Beni Seuf - 3585 | 18196108.24 | 12555353.5 | 3093299.6 | 15648653.1
Beni Seuf - 358 | Inv. 4 Oewon Mousa | 4 | Beni Seuf - 3584 | 10374574.63 | 7187026.67 | 1735107.52 | 8922134.19
Barwa and Damac 220 OHTL | Inv No6 Wattanya220 | 6 | Barwa and Damac 220 OHTL6 | 5207897.62 | 3892503.6 | 781184.97 | 4673688.57
K047 FDH JV | Inv. NO.9 KWT Floor | 9 | K047 FDH JV9 | 86916.94 | 78225.24 | 0 | 78225.24
EMAAR-PKG#62-UPTOWN | (3)PKG#62 | 3 | EMAAR-PKG#62-UPTOWN3 | 2148477 | 1345054.04 | 773773.99 | 2118828.03
Bani Suef Old Substation | (12) BENI SUIF1 | 12 | Bani Suef Old Substation12 | 1145904 | 993957.12 | 114590.41 | 1108547.53
Closed | (2)shobra/banha | 2 | Closed2 | 459012 | 413932.49 | 0 | 413932.49
Suez Gulf Substation | Inv No 2 Suez Gulf | 2 | Suez Gulf Substation2 | 390457.1429 | 409980 | 0 | 409980
W Dam PP Phase II (CP-117) | 11 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 159164.381 | 142054.21 | 25068.39 | 167122.6
Beni Suef Substation R61 | beni suif 2 (1) | 1 | Beni Suef Substation R611 | 16367759.65 | 16367759.65 | 0 | 16367759.65
South Helwan PP (CP-117) | 2009210010 |  | South Helwan PP (CP-117) | 591337.4 | 202896.33 | 413028.9 | 615925.23
South Helwan PP (CP-117) | 1905210001 |  | South Helwan PP (CP-117) | 170823.56 | 143512.05 | 25623.53 | 169135.58
South Helwan PP (CP-117) | 1902210004 |  | South Helwan PP (CP-117) | 104612.25 | 109029.61 | 0 | 109029.61
Apache Electrical Works | Apachi Inv No PC,21 |  | Apache Electrical Works | 29512.94 | 29512.94 | 0 | 29512.94
Apache Electrical Works | Apachi Inv No P.C#20 | 20 | Apache Electrical Works20 | 90792.85 | 90792.85 | 0 | 90792.85
El Amal Bridge | 19100047 |  | El Amal Bridge | 2850725 | 1178671.7 | 1178000 | 2356671.7
Abu Qir PP (CP-118) | Inv Rent Abu quir |  | Abu Qir PP (CP-118) | 37884.13 | 37884.13 | 0 | 37884.13
Kuwait | 1-132KVA-H | 132 | Kuwait132 | 136683.654 | 102512.74 | 0 | 102512.74
Siemens 6x500/220 KV GIS-MOU | Inv 64 P6 Assuit | 64 | Siemens 6x500/220 KV GIS-MOU64 | 4291540.811 | 3104500.631 | 643731.12 | 3748231.751
Ministries Buildings | alloccation ipc10 | 10 | Ministries Buildings10 | 3632523 | 3232945.47 | 0 | 3232945.47
Mohamed Ali Palace Restoration | mohamed aly ipc06 | 6 | Mohamed Ali Palace Restoration6 | 3655924.33 | 956829.8465 | 2294711.4 | 3251541.2465
Akhmem - Qena | Inv.1 Quna Akhmem | 1 | Akhmem - Qena1 | 129881572.05 | 77279535.3625 | 19482235.81 | 96761771.1725
Al-Shabab PP Phase II (CP-117) | refund CSI - SH |  | Al-Shabab PP Phase II (CP-117) | 11687 | 11687 | 0 | 11687
EMAAR-PKG#62-UPTOWN | (8) pkg#62 | 8 | EMAAR-PKG#62-UPTOWN8 | 3910757 | 3300873.4 | 1899641.41 | 5200514.81
Ghana | 36/P/10/ER/2017/USD |  | Ghana | 590122.61 | 590108.11 | 0 | 590108.11
Abou El Matameer and Sammanoud | Inv 97 P14Abo Matami | 97 | Abou El Matameer and Sammanoud97 | 3595740.3948 | 2583179.9048 | 539361.06 | 3122540.9648
Abou El Matameer and Sammanoud | Inv 91P11Abo Matami | 91 | Abou El Matameer and Sammanoud91 | 1798421.83 | 1300978.35 | 269763.28 | 1570741.63
Military 110 Kayan Project | Inv. 7 Elkayan | 7 | Military 110 Kayan Project7 | 77825867.69 | 70626580.75 | 0 | 70626580.75
Badr | Inv. 25 Badr | 25 | Badr25 | 8876075.73 | 6106319.35 | 1331411.38 | 7437730.73
Beni Suef Substation R61 | (3)cw beni suif | 3 | Beni Suef Substation R613 | 4371751.46 | 3256954.83 | 655762.72 | 3912717.55
Suez Gulf Substation | 15EGP/on-shore train |  | Suez Gulf Substation | 104823.8095 | 99058.5 | 11006.5 | 110065
Al Mostathmreen GIS Substation | 20sd elmostsmrin |  | Al Mostathmreen GIS Substation | 2595288 | 1933489.56 | 389293.2 | 2322782.76
Ministries Buildings | MIN.ELECTRO-IPC01 | 1 | Ministries Buildings1 | 71805669.2 | 47786690 | 4754005.45 | 52540695.45
Assuit PP (CP-118) | 2108210006 |  | Assuit PP (CP-118) | 1881270.96 | 1624840.3 | 296300.18 | 1921140.48
Assuit PP (CP-118) | 2108210002 |  | Assuit PP (CP-118) | 263386.67 | 230068.25 | 41483.4 | 271551.65
Assuit PP (CP-118) | 1905210008 |  | Assuit PP (CP-118) | 2656403.42 | 2344276.02 | 418383.54 | 2762659.56
Assuit PP (CP-118) | 1908210003 |  | Assuit PP (CP-118) | 62135.66 | 55456.07 | 9786.37 | 65242.44
Marsa Matrouh 500KV | Inv.48 Borg Alarab | 48 | Marsa Matrouh 500KV48 | 5514081.46 | 4816553.89 | 578978.55 | 5395532.44
K047 FDH JV | Inv. No.12 KWD Floor | 12 | K047 FDH JV12 | 110152.48 | 99137.22 | 0 | 99137.22
SHATRA 400/132kV SS | 203 |  | SHATRA 400/132kV SS | 4640388.65 | 0 | 0 | 0
kayan wall lock & Load | 19100015 |  | kayan wall lock & Load | 9720000 | 7568893 | 550000 | 8118893
New Giza 2 | new giza2 vo-ipc1 | 1 | New Giza 21 | 651117.59 | 613678.3295 | 0 | 613678.3295
Kayan 3 New Cairo Capital City | ELKAYAM MEP-IPC (2) | 2 | Kayan 3 New Cairo Capital City2 | 54383758.5 | 39352862.65 | 10000000 | 49352862.65
Al Mostathmreen GIS Substation | 12 sd euro mostsmrin |  | Al Mostathmreen GIS Substation | 278712.16 | 202066.32 | 41806.82 | 243873.14
Ministries Buildings | MIN-OLD-IPC05 | 5 | Ministries Buildings5 | 8139701.5 | 0 | 7264287.16 | 7264287.16
Apache Electrical Works | Apachi Inv No PC.#27 |  | Apache Electrical Works | 380181.56 | 380181.56 | 0 | 380181.56
Lina Farm Substation | Green power balance |  | Lina Farm Substation | 126891.55 | 126891.55 | 0 | 126891.55
Siemens 6x500/220 KV GIS-MOU | soc 12 siemen assuit |  | Siemens 6x500/220 KV GIS-MOU | 69984.65 | 69984.65 | 0 | 69984.65
Akhmem Assiut | Inv.15 Assuit Akhmem | 15 | Akhmem Assiut15 | 40987975.56 | 24387845.46 | 6148196.33 | 30536041.79
Suez Gulf Substation | Inv 1 VO SG | 1 | Suez Gulf Substation1 | 309523.8095 | 292500 | 32500 | 325000
Royal City | IPC8-ROYAL CITY | 8 | Royal City8 | 7514576.65 | 6396986.1725 | 1211103.24 | 7608089.4125
Kuwait | 34-132KVA(8J) | 132 | Kuwait132 | 108631.37 | 70610.39 | 0 | 70610.39
Kuwait | 33-132KVA(8H) | 132 | Kuwait132 | 108631.37 | 70610.39 | 0 | 70610.39
Akhmem - Qena | Inv.8 Qena - Akhmem$ | 8 | Akhmem - Qena8 | 2209137.55 | 1876320.38 | 0 | 1876320.38
Akhmem - Qena | Inv. 40 Akhmem Qena | 40 | Akhmem - Qena40 | 3352844.51 | 2330226.93 | 502926.68 | 2833153.61
P-28-16 Balat Owinat Lot 3 | Inv. 16 Balat lot 3 | 16 | P-28-16 Balat Owinat Lot 316 | 1076785.84 | 705823.98 | 0 | 705823.98
Akhmem Assiut | Inv.6 Assuit Akhmem$ | 6 | Akhmem Assiut6 | 540926.3 | 459353.32 | 0 | 459353.32
R5 Mix-Use Complex Project | R05-ZONE01-IPC03 | 3 | R5 Mix-Use Complex Project3 | 9108844 | 9530950.57 | 1168656.18 | 10699606.75
Akhmem Assiut | Inv.30 Assuit Akhmem | 30 | Akhmem Assiut30 | 1580001.39 | 1256101.11 | 237000.21 | 1493101.32
Akhmem - Qena | Inv. 41 Akhmem Qena | 41 | Akhmem - Qena41 | 2794311.34 | 1382655.21 | 419146.7 | 1801801.91
Akhmem - Qena | Inv.29 Akhmem Qena | 29 | Akhmem - Qena29 | 790778.03 | 628668.54 | 118616.7 | 747285.24
Marsa Matrouh 500KV | Inv.3 Borg Alarab | 3 | Marsa Matrouh 500KV3 | 10523603.44 | 10523603.44 | 0 | 10523603.44
Lina Farm Substation | 4 EGP - Lina |  | Lina Farm Substation | 2894707.22 | 2894707.22 | 0 | 2894707.22
Canal Regional Control Center | Inv.1 RCC | 1 | Canal Regional Control Center1 | 6034785.3 | 4018565.62 | 1267304.91 | 5285870.53
Tamey El-amdeed Substation | TAM-CW-EGP-07 | 7 | Tamey El-amdeed Substation7 | 2823851.52 | 2103769.38 | 423577.73 | 2527347.11
Al Mostathmreen GIS Substation | MOS-SD-EGP-21 | 21 | Al Mostathmreen GIS Substation21 | 270269.6 | 201350.85 | 40540.44 | 241891.29
Royal City | ROYAL ZONE-IPC09 | 9 | Royal City9 | 6296215.04 | 5296379.022 | 1429157.65 | 6725536.672
Ismalia Bridge | ISMAILIA BLAJT-IPC03 | 3 | Ismalia Bridge3 | 16962557.79 | 6056328.15 | 5204469.36 | 17008301.51
South Helwan PP (CP-117) | 180147 |  | South Helwan PP (CP-117) | 233646.38 | 244575.79 | 0 | 244575.79
Akhmem Assiut | Ref Ret. Inst 2 Asut |  | Akhmem Assiut | 18342857.27 | 18342328.37 | 0 | 18342328.37
EMAAR-PKG#53-UPTOWN | PKG#53-IPC-36 | 36 | EMAAR-PKG#53-UPTOWN36 | 1983817.89 | 3652834.8365 | 0 | 3652834.8365
Marsa Matrouh 500KV | Inv13 Usd borg alarb | 13 | Marsa Matrouh 500KV13 | 9224.32 | 6559.22 | 968.55 | 7527.77
AWEER POWER STATION 'H' Phase | CON/029 |  | AWEER POWER STATION 'H' Phase | 266187.22 | 233653.22 | 29576.36 | 263229.58
AWEER POWER STATION 'H' Phase | IMP/066 |  | AWEER POWER STATION 'H' Phase | 871641.16 | 256649.8977 | 96849.02 | 353498.9177
AWEER POWER STATION 'H' Phase | CON/019 |  | AWEER POWER STATION 'H' Phase | 425899.55 | 373845.1575 | 47322.17 | 421167.3275
AWEER POWER STATION 'H' Phase | Loc-009 | 9 | AWEER POWER STATION 'H' Phase9 | 1022976.47 | 1011610.07 | 0 | 1011610.07
AWEER POWER STATION 'H' Phase | IMP047-39 | 39 | AWEER POWER STATION 'H' Phase39 | 2089097.1 | 2068848.77 | 0 | 2068848.77
AWEER POWER STATION 'H' Phase | Con/009 |  | AWEER POWER STATION 'H' Phase | 558993.16 | 490671.77 | 62110.35 | 552782.12
AWEER POWER STATION 'H' Phase | 10137 |  | AWEER POWER STATION 'H' Phase | 1278118.38 | 376334.479 | 887582.56 | 1263917.039
Marsa Matrouh 500KV | Inv. 9 Borg Alarab | 9 | Marsa Matrouh 500KV9 | 87830687.53 | 62019089.46 | 9222222.19 | 71241311.65
New Heliopolis | Inv. 10 Heliopolise | 10 | New Heliopolis10 | 10052362 | 7984172.7 | 987141.95 | 8971314.65
Tamey El-amdeed Substation | TAM-SW-EGP-02 | 2 | Tamey El-amdeed Substation2 | 980000 | 725200 | 147000 | 872200
EMAAR-PKG# 144, Marassi | PKG#144 -IPC3 | 3 | EMAAR-PKG# 144, Marassi3 | 6872046.63 | 6189125.0415 | 3180859.94 | 9369984.9815
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC07 | 7 | EMAAR-PKG# 101-UPTOWN7 | 3491880.84 | 1988552.05 | 1042992.41 | 3031544.46
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC-01 | 1 | EMAAR-PKG# 101-UPTOWN1 | 1738465.67 | 1029594.8135 | 547616.69 | 1577211.5035
4 SS - Technical Service | 215 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
EMAAR-PKG#53-UPTOWN | 19100002 |  | EMAAR-PKG#53-UPTOWN | 1237230.98 | 1753673.249 | 0 | 1753673.249
Elsewedy Univ - Enabling Works | 19100017 |  | Elsewedy Univ - Enabling Works | 1734033.5 | 1204112.855 | 546220.55 | 1750333.405
DPW Onshore Port & Terminal | DP WORLD -IPC10 | 10 | DPW Onshore Port & Terminal10 | 90533235.47 | 66994289.3 | 13579985.32 | 80574274.62
DPW Onshore Port & Terminal | DP WORLD-IPC008 | 8 | DPW Onshore Port & Terminal8 | 39363674.81 | 29128813.98 | 5904551.22 | 35033365.2
DPW Onshore Port & Terminal | DP World IPC030 | 30 | DPW Onshore Port & Terminal30 | 14579181.6 | 10739490.38 | 2186877.24 | 12926367.62
DPW Onshore Port & Terminal | DPW IPC027 | 27 | DPW Onshore Port & Terminal27 | 21307969.76 | 15718793.62 | 3196195.46 | 18914989.08
Closed | (1) shobra/banha | 1 | Closed1 | 407864 | 234380.8 | 0 | 234380.8
Zafranaa - Ras Ghareb | ref. reten.zafra gha |  | Zafranaa - Ras Ghareb | 9785281.7 | 9785281.7 | 0 | 9785281.7
Akhmem Assiut | Soc Inv 34To37 Asuit | 34 | Akhmem Assiut34 | 1017697.8 | 1017697.8 | 0 | 1017697.8
Akhmem Assiut | Soc Inv 20-21 Asuit | 20 | Akhmem Assiut20 | 802370.5 | 802370.5 | 0 | 802370.5
Ministries Buildings | MINISTRIY SHELL-IPC1 | 1 | Ministries Buildings1 | 111319928.44 | 42783984 | 54507678.25 | 97291662.25
HAC CCC JV | IPC#10 | 10 | HAC CCC JV10 | 1144744.5 | 1043263.01 | 0 | 1043263.01
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC03 | 3 | EMAAR- Pkg 140-ITP-Mivida3 | 6247225.23 | 4070832.4 | 1894295.14 | 5965127.54
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC01 | 1 | EMAAR- Pkg 140-ITP-Mivida1 | 4797449.52 | 2533668.016 | 1906611.38 | 4440279.396
Assuit PP (CP-118) | 1901210009 |  | Assuit PP (CP-118) | 173380.07 | 154741.71 | 27307.36 | 182049.07
New Capital | Inv. 8 Eltbeen | 8 | New Capital8 | 150157.14 | 139770.72 | 0 | 139770.72
Ministries Buildings | MIN-SHELL-IPC06 | 6 | Ministries Buildings6 | 6523952.65 | 4122020 | 1374009.35 | 5496029.35
Suez Road Tunnel RES | SUEZ ROADL&L- FINAL |  | Suez Road Tunnel RES | 1959389.44 | 1311260 | 437087.5 | 1748347.5
EMAAR-PKG# 144, Marassi | PKG#144 -IPC06 | 6 | EMAAR-PKG# 144, Marassi6 | 24446048.93 | 14929446.3565 | 7662957.19 | 22592403.5465
Mauritania Lot 1 | Inv.6 - Lot 1 | 6 | Mauritania Lot 16 | 485571.01 | 461277.45 | 0 | 461277.45
El Boghaz Brigde | IPC#19 | 19 | El Boghaz Brigde19 | 1512327.9 | 1399517.22 | 0 | 1399517.22
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 11 | 11 | Benban 500 K.V/95 K.M11 | 466471.68 | 359656.9 | 48979.53 | 408636.43
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 2 | 2 | Benban 500 K.V/95 K.M2 | 24071994.55 | 18558911.74 | 2527559.43 | 21086471.17
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 2 | 2 | Benban 500 K.V / 100 K.M2 | 69743781.24 | 53771861.26 | 7323097.03 | 61094958.29
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 7 | 7 | Benban 500 K.V / 100 K.M7 | 26539062.6 | 20461620.83 | 2786601.57 | 23248222.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 3 | 3 | Benban 500 K.V / 100 K.M3 | 1353959.24 | 1043307.55 | 142165.72 | 1185473.27
EMAAR-PKG#53-UPTOWN | PKG#53 -IPC38 | 38 | EMAAR-PKG#53-UPTOWN38 | 217725.59 | 841731.1795 | 0 | 841731.1795
Elco Steel 220/33 KV SS | 1903210011 |  | Elco Steel 220/33 KV SS | 15713070.57 | 16498724.1 | 0 | 16498724.1
Elco Steel 220/33 KV SS | 1901210003 |  | Elco Steel 220/33 KV SS | 4532833.5 | 4759475.18 | 0 | 4759475.18
Phosfat | Inv.6 Phosfat II | 6 | Phosfat6 | 1426885 | 1201754.75 | 0 | 1201754.75
Beni-Suef Power Plant EPC | coll of beni suef ga |  | Beni-Suef Power Plant EPC | 158808 | 158808 | 0 | 158808
El Boghaz Brigde | IPC#20 | 20 | El Boghaz Brigde20 | 1241851.62 | 968113.12 | 0 | 968113.12
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 8USD | 8 | Benban 500 K.V / 100 K.M8 | 30502.13 | 22419.07 | 6405.45 | 28824.52
Benban 500 K.V / 100 K.M | Benban Lot1 Inv12USD | 12 | Benban 500 K.V / 100 K.M12 | 72994.38 | 61315.28 | 7664.41 | 68979.69
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 7USD | 7 | Benban 500 K.V / 100 K.M7 | 237904.83 | 199840.06 | 24980.01 | 224820.07
Akhmem Assiut | Social 44-47 Assuit | 47 | Akhmem Assiut47 | 2259485.5 | 2259485.5 | 0 | 2259485.5
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 1 | 1 | Benban 500 K.V/95 K.M1 | 211577781.63 | 163120869.42 | 22215667.07 | 185336536.49
Manshiet Nasser Substation | Civil5 to Shipp 5 |  | Manshiet Nasser Substation | 0 | -254029.86 | 0 | -254029.86
Military 110 Kayan Project | Elkayan Inv.17 | 17 | Military 110 Kayan Project17 | 4361899.16 | 3761744.4 | 0 | 3761744.4
Abou El Matameer and Sammanoud | Inv 85 P6 Sammound | 85 | Abou El Matameer and Sammanoud85 | 6990113.13 | 5056647.84 | 1048516.97 | 6105164.81
Cameron EDC | 020/2019 |  | Cameron EDC | 65260.87 | 65173.91 | 0 | 65173.91
4 SS - Technical Service | 254 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHATRA 400/132kV SS | 238 |  | SHATRA 400/132kV SS | 234988.19 | 234988.19 | 0 | 234988.19
MAYSAN 400/132kV SS | 241 |  | MAYSAN 400/132kV SS | 1603335.49 | 1603335.49 | 0 | 1603335.49
Elco Steel 220/33 KV SS | 1908210006 |  | Elco Steel 220/33 KV SS | 629653.39 | 1322272.12 | 0 | 661136.06
Suez IPB | 5 EGP - Suez Steel |  | Suez IPB | 66203.91 | 66203.91 | 0 | 66203.91
Suez IPB | 2*3 EGP - Suez Steel |  | Suez IPB | 27500 | 27500 | 0 | 27500
Suez IPB | 2*1 USD - Suez Steel |  | Suez IPB | 295 | 295 | 0 | 295
MOTHANA 400/132kV SS | 253 |  | MOTHANA 400/132kV SS | 674732.7 | 674732.7 | 0 | 674732.7
El Katameya Mall | INV ( 13 ) 22-10-20 | 13 | El Katameya Mall13 | 440720 | 152282.11 | 221563.53 | 373845.64
Latin Compound - New Alamin | inv ( 19 ) 7-12-2020 | 19 | Latin Compound - New Alamin19 | 193379.2 | 125599.79 | 38675.84 | 164275.63
Ministries Buildings | minist allocat ipc09 | 9 | Ministries Buildings9 | 8828085.8 | 507250 | 7000000 | 7507250
DoubleTree Mangroovy ElGouna | MANGOROVE-IPC01 | 1 | DoubleTree Mangroovy ElGouna1 | 3393576.4 | 2327690.59 | 890813.81 | 3218504.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 8 | 8 | Benban 500 K.V / 100 K.M8 | 46533060.33 | 35876993.06 | 4885971.34 | 40762964.4
EMAAR-PKG# 101-UPTOWN | 20100002 |  | EMAAR-PKG# 101-UPTOWN | 3175801.11 | 1424816.56 | 766170.06 | 2190986.62
DPW Onshore Port & Terminal | DP WORLD-IPC07 | 7 | DPW Onshore Port & Terminal7 | 33097932.28 | 24492163.72 | 4964689.84 | 29456853.56
Beni Seuf - 358 | Ref. Ret. itay 358 |  | Beni Seuf - 358 | 42624818.36 | 42624220.71 | 0 | 42624220.71
Akhmem - Qena | Soc.Inv. 48 Qena | 48 | Akhmem - Qena48 | 482579.5 | 482579.5 | 0 | 482579.5
Akhmem Assiut | Soc.Inv. 50 Assuit | 50 | Akhmem Assiut50 | 127340.6 | 127340.6 | 0 | 127340.6
33KV Canal Farm Grid | Inv. 17 Farm | 17 | 33KV Canal Farm Grid17 | 5700819.11 | 4349724.98 | 855122.87 | 5204847.85
33KV Canal Farm Grid | Inv. 16 Farm | 16 | 33KV Canal Farm Grid16 | 7174437 | 5474095.43 | 1076165.55 | 6550260.98
33KV Canal Farm Grid | Inv. 05 Farm | 5 | 33KV Canal Farm Grid5 | 3210869.8 | 2536587.14 | 481630.47 | 3018217.61
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 5USD | 5 | Benban 500 K.V / 100 K.M5 | 425824.1 | 357692.25 | 44711.53 | 402403.78
HyperOne Zayed Extension | HYPER ONE-IPC12 | 12 | HyperOne Zayed Extension12 | 3093527.62 | 1896313.721 | 773382 | 2669695.721
HyperOne Zayed Extension | HYPER ONE-IPC11 | 11 | HyperOne Zayed Extension11 | 10073235.24 | 6700148 | 2518309 | 9218457
Suez Gulf Substation | 21 EGP VO CCC Instal |  | Suez Gulf Substation | 571885.66 | 541448.5 | 60160.95 | 601609.45
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 9USD | 9 | Benban 500 K.V / 100 K.M9 | 1708275.44 | 1434692.37 | 179368.92 | 1614061.29
Benban 500 K.V / 100 K.M | Benban Lot1 Inv11USD | 11 | Benban 500 K.V / 100 K.M11 | 205796.67 | 151260.55 | 43217.3 | 194477.85
Asec Spare-Parts | Inv 3 Asec Sparepart | 3 | Asec Spare-Parts3 | 3106710 | 2601745 | 932474.94 | 3534219.94
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 17 | 17 | Benban 500 K.V/95 K.M17 | 9286.4 | 7165.39 | 975.07 | 8140.46
AWEER POWER STATION 'H' Phase | 10247 |  | AWEER POWER STATION 'H' Phase | 241518.4 | 253594.32 | 0 | 253594.32
SHATRA 400/132kV SS | 270 |  | SHATRA 400/132kV SS | 68360.02 | 68360.02 | 0 | 68360.02
El Mostaqbal lock & load | ELMOUSTQBAL -IPC 01 | 1 | El Mostaqbal lock & load1 | 3690070 | 1530897 | 1438657.45 | 2969554.45
NUCA R05 - Z02 | R5-ZONE2-IPC08 | 8 | NUCA R05 - Z028 | 31690867.8 | 26625328.57 | 3306778.62 | 29932107.19
AWEER POWER STATION 'H' Phase | 10307 |  | AWEER POWER STATION 'H' Phase | 211328.6 | 221895.03 | 0 | 221895.03
ESU Ph2-Enabling & Struc | E.S.U 2-ENABLE-IPC06 | 6 | ESU Ph2-Enabling & Struc6 | 18379179.43 | 7788095.2015 | 5789441.6 | 13577536.8015
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 14 | 14 | Benban 500 K.V / 100 K.M14 | 2345850.61 | 1808652.48 | 246314.31 | 2054966.79
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 19 | 19 | Benban 500 K.V / 100 K.M19 | 3761270.73 | 2899945.16 | 394933.43 | 3294878.59
Cairo Capital Cables Tunnel | Tunnel Inv. 5 | 5 | Cairo Capital Cables Tunnel5 | 32015241.75 | 21546257.6 | 8003810.44 | 29550068.04
Cairo Capital Cables Tunnel | Tunnel Inv. 1 | 1 | Cairo Capital Cables Tunnel1 | 28355172.25 | 19078030.75 | 7088793.1 | 26166823.85
Suez Road Tunnel RES | SUEZ ROAD L&L-IPC01 | 1 | Suez Road Tunnel RES1 | 5025000.75 | 2837565 | 945859.64 | 3783424.64
Suez Gulf Substation | 485 |  | Suez Gulf Substation | 10694.17 | 10125 | 1125 | 11250
Suez Gulf Substation | 482 |  | Suez Gulf Substation | 3898.86 | 3691.35 | 410.15 | 4101.5
Elco Steel 220/33 KV SS | 1901210014 |  | Elco Steel 220/33 KV SS | 1695469.23 | 1780242.69 | 0 | 1780242.69
Elco Steel 220/33 KV SS | 493 |  | Elco Steel 220/33 KV SS | 138416.67 | 145337.5 | 0 | 145337.5
Elco Steel 220/33 KV SS | 1908210004 |  | Elco Steel 220/33 KV SS | 20676.1 | 21709.9 | 0 | 21709.9
Elco Steel 220/33 KV SS | 1907210012 |  | Elco Steel 220/33 KV SS | 13493.3 | 14168 | 0 | 14168
Elco Steel 220/33 KV SS | 1906210002 |  | Elco Steel 220/33 KV SS | 25454.04 | 26726.74 | 0 | 26726.74
Elco Steel 220/33 KV SS | 1901210007 |  | Elco Steel 220/33 KV SS | 595016.75 | 624767.59 | 0 | 624767.59
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .16 | 16 | Benban 3/ Toshka 2 LOT 416 | 4739932.63 | 3232239.62 | 497692.93 | 3729932.55
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .20 | 20 | Benban 3/ Toshka 2 LOT 420 | 16284436.24 | 12815461.43 | 1709865.81 | 14525327.24
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .13 | 13 | Benban 3/ Toshka 2 LOT 413 | 6884480.29 | 5583320.82 | 722870.43 | 6306191.25
CFC Podium 2 | CFC-IPC08 | 8 | CFC Podium 28 | 31008097.6 | 21459123.66 | 4120101.75 | 25579225.41
CFC Podium 2 | CFC - IPC05 | 5 | CFC Podium 25 | 30502560 | 24749111.52 | 4714808.38 | 29463919.9
MOTHANA 400/132kV SS | 291 |  | MOTHANA 400/132kV SS | 529642.01 | 529642.01 | 0 | 529642.01
Al-Shabab PP Phase II (CP-117) | 180156 |  | Al-Shabab PP Phase II (CP-117) | 48089.64 | 46837.3 | 8265.41 | 55102.71
Akhmem - Qena | Soc 49 Quana |  | Akhmem - Qena | 1837479 | 1837479 | 0 | 1837479
AWEER POWER STATION 'H' Phase | 10390 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
LAYYAH CCPP | MP-11 | 11 | LAYYAH CCPP11 | 12854700 | 0 | 12854700 | 12854700
Port Said | Refund Ret.Port Said |  | Port Said | 2631979.65 | 2631979.65 | 0 | 2631979.65
Lekela 250MW Wind Farm | LEKELA-IPC06 | 6 | Lekela 250MW Wind Farm6 | 17262367.14 | 14840272.417 | 3128774.36 | 17969046.777
Lekela 250MW Wind Farm | LEKELA-IPC01 | 1 | Lekela 250MW Wind Farm1 | 1989169.6 | 1670902.46 | 397833.92 | 2068736.38
Toshka GIS 500 kV | Toshka Sub Inv. 07 $ | 7 | Toshka GIS 500 kV7 | 86989.71 | 49566.56 | 22834.8 | 72401.36
DoubleTree Mangroovy ElGouna | MANGROVE RENT-IPC02 | 2 | DoubleTree Mangroovy ElGouna2 | 409200 | 425568 | 0 | 425568
Elmaragha Bridge - Sohag | IPC#1 | 1 | Elmaragha Bridge - Sohag1 | 968500 | 826340 | 0 | 826340
Multi Sport Hall | 10020 |  | Multi Sport Hall | 146493 | 130378.77 | 0 | 130378.77
Mahmoudia Additional Scope | 2003210002 |  | Mahmoudia Additional Scope | 11268062.5 | 11268062.5 | 0 | 11268062.5
Badr | Inv. 21 Badr | 21 | Badr21 | 6356891.83 | 4719583.38 | 953533.8 | 5673117.18
AWEER POWER STATION 'H' Phase | 3 |  | AWEER POWER STATION 'H' Phase | 211328.6 | 221823.22 | 0 | 221823.22
EL-Hegaz Square Bridge | ELHEGAZ2-IPC1FINAL | 1 | EL-Hegaz Square Bridge1 | 12477199.24 | 0 | 10961702.722 | 10961702.722
EMAAR-Pkg#162/163- Marassi | PKG#163 - IPC011 | 11 | EMAAR-Pkg#162/163- Marassi11 | 3832626.3 | 3799097.555 | 1102242.63 | 4901340.185
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC08 | 8 | EMAAR-Pkg#162/163- Marassi8 | 7415396.3 | 6502546.725 | 1765971.33 | 8268518.055
Marsa Allam | 10032 |  | Marsa Allam | 22368.42 | 24828.9488 | 0 | 24828.9488
Ministries Buildings | MIN -CORE- IPC03 | 3 | Ministries Buildings3 | 8446258.05 | 5400020 | 1800008 | 7200028
MOTHANA 400/132kV SS | 314 |  | MOTHANA 400/132kV SS | 45864.43 | 45864.43 | 0 | 45864.43
MAYSAN 400/132kV SS | 312 |  | MAYSAN 400/132kV SS | 202057.11 | 202057.11 | 0 | 202057.11
Dubai Port | 10039 |  | Dubai Port | 9741.75 | 8240.9275 | 0 | 8240.9275
Marsa Matrouh 500KV | Inv.71 Borg Alarab | 71 | Marsa Matrouh 500KV71 | 30722273.12 | 25118658.37 | 0 | 25118658.37
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 31 | 31 | Benban 500 K.V / 100 K.M31 | 26697762.16 | 20583975.48 | 2803265.03 | 23387240.51
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 2 | 2 | Marsa Alam/ Bernes LOT2 OHTL2 | 19134441.78 | 10734410.81 | 2009116.39 | 12743527.2
ESU Ph2-Enabling & Struc | E.S.U2- IPC 05 | 5 | ESU Ph2-Enabling & Struc5 | 7891719.62 | 2392694.8 | 2485891.6 | 4878586.4
Minis Building(Polyurethane) | 10036 |  | Minis Building(Polyurethane) | 334776 | 297950.64 | 0 | 297950.64
P-28-16 Balat Owinat Lot 3 | Inv. 2 Balat lot 3 | 2 | P-28-16 Balat Owinat Lot 32 | 4181384.51 | 3144010.85 | 439045.37 | 3583056.22
Manshiet Nasser Substation | 2003210009 |  | Manshiet Nasser Substation | 1386244.94 | 1178308.2 | 207936.74 | 1386244.94
Beni Seuf - 358 | Re. Soc Inv 1 Temay | 1 | Beni Seuf - 3581 | 6287397 | 6287397 | 0 | 6287397
LAYAN Substation | 10526 |  | LAYAN Substation | 263056.2 | 218336.75 | 0 | 218336.75
Royal City | ROYAL CITY-IPC29 | 29 | Royal City29 | 17649893.88 | 12838209.344 | 5454040.89 | 18292250.234
Assuit PP (CP-118) | 2005210004 |  | Assuit PP (CP-118) | 806149.42 | 711426.86 | 126968.53 | 838395.39
Mangrouve Hotel - Gouna | 10196 |  | Mangrouve Hotel - Gouna | 11855.16 | 10551.07 | 0 | 10551.07
Canal Sugar OHTL | Inv.10 Sugar OHTL | 10 | Canal Sugar OHTL10 | 4053275.4 | 1538890.85 | 0 | 1538890.85
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 03 | 3 | Suez Gulf/S4 - 500KV OHTL3 | 24468424.76 | 18620460.06 | 2569184.6 | 21189644.66
Ismailiya East Substation | ISE-CW-EGP-23 | 23 | Ismailiya East Substation23 | 1466046 | 1304780.94 | 0 | 1304780.94
Aljazi Project | Al - Jazi Inv. 1 | 1 | Aljazi Project1 | 278661 | 230795 | 0 | 230795
Ministries Buildings | MIN CORE - IPC04 | 4 | Ministries Buildings4 | 30453148.95 | 19470665 | 6490226 | 25960891
Ghana | 42/P/10/ER/2017/USD |  | Ghana | 631405.86 | 631405.86 | 0 | 631405.86
Al-Wukair 11 Substation | 2006210004 |  | Al-Wukair 11 Substation | 1525153.7 | 1525153.7 | 0 | 1525153.7
Sodic East | IPC_12_rowad_s_east |  | Sodic East | 388943.4 | 156832.48 | 0 | 156832.48
Mahmoudia Additional Scope | 2003210004 |  | Mahmoudia Additional Scope | 8250000 | 8250000 | 0 | 8250000
El Banna project | 455 |  | El Banna project | 2825393.32 | 2825393.32 | 0 | 2825393.32
Museum of Egyp. Civilization | IPC#6 | 6 | Museum of Egyp. Civilization6 | 480649.5 | 306508.29 | 0 | 306508.29
Racecores 3092-16 132KV C | 10803 |  | Racecores 3092-16 132KV C | 284262.36 | 471875.46 | 0 | 235937.73
Iskraemeco show room | 1 |  | Iskraemeco show room | 741585.97 | 845408 | 0 | 845408
NUCA R05 - Z02 | R5(2) IPC 52 | 52 | NUCA R05 - Z0252 | 37170105.92 | 18222028.76 | 3816290.32 | 22038319.08
NUCA R05 - Z02 | R05(2) ipc45 | 45 | NUCA R05 - Z0245 | 27953981.45 | 22913073.64 | 3053354.24 | 25966427.88
NUCA R05 - Z02 | R05(2) ipc 31 | 31 | NUCA R05 - Z0231 | 25879322.45 | 22239327.6 | 2782115.7 | 25021443.3
Port Saad Industiral zone | IPC#7 | 7 | Port Saad Industiral zone7 | 676482.84 | 670548.78 | 0 | 670548.78
Marsa Matrouh 500KV | Ref Retention.Matroh |  | Marsa Matrouh 500KV | 28997790.2 | 0 | 0 | 28997790.2
Tamey El-amdeed Substation | TAM-CW-EGP-22 | 22 | Tamey El-amdeed Substation22 | 125719.78 | 93032.63 | 18857.97 | 111890.6
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC15 | 15 | EMAAR- Pkg 140-ITP-Mivida15 | 16266667.66 | 10902262.273 | 1321629.97 | 12223892.243
Taval Sarai 52 | IPC_4_Gama_Saray |  | Taval Sarai 52 | 179731.3 | 122105.01 | 0 | 122105.01
Toshka Farm | Toshka Farm Inv. 03 | 3 | Toshka Farm3 | 19732011.69 | 17360481.66 | 877900.85 | 18771715.84
Cairo-Alex Railway | Cairo-Alex ipc 40* | 40 | Cairo-Alex Railway40 | 21031085.3 | 7949386.8 | 8636872.63 | 16586259.43
Racecores 3092-17 132KV E | 11102 |  | Racecores 3092-17 132KV E | 535383.64 | 2221842.25 | 0 | 444368.45
Marsa Matrouh 500KV | Inv.23Usd borg alarb | 23 | Marsa Matrouh 500KV23 | 812.09 | 794.98 | 0 | 794.98
LAYAN Substation | 10303 |  | LAYAN Substation | 4742492.09 | 3936268.44 | 0 | 3936268.44
Ministries A13-A14 | IPC_3_RedSea_Ministy |  | Ministries A13-A14 | 55760 | 48401 | 0 | 48401
Celia | FPC |  | Celia | 105196.81 | 74516.56 | 0 | 74516.56
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc (27) | 27 | ORA ZED - Ph 01B - Pkgs A&D27 | 10547653.65 | 8722947.15 | 1106531.13 | 9829478.28
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED1-IPC03 | 3 | ORA ZED - Ph 01B - Pkgs A&D3 | 26768118.08 | 29651159.334 | 3529598.47 | 33180757.804
EMAAR-PKG#53-UPTOWN | IPC-05- PKG#85/53 | 5 | EMAAR-PKG#53-UPTOWN5 | 1849502.84 | 1729285.152 | 0 | 1729285.152
Mohamed Ali Palace | IPC_5_Rowad_M.Ali |  | Mohamed Ali Palace | 18719.6 | 15724.46 | 0 | 15724.46
AWEER POWER STATION 'H' Phase | ENG/033 |  | AWEER POWER STATION 'H' Phase | 408011.58 | 428412.159 | 0 | 428412.159
Ghana Street lighting | MIDA Ins. Inv.1 | 1 | Ghana Street lighting1 | 105593.4 | 95034.06 | 0 | 95034.06
Miscellaneous Projects | 2008210004 |  | Miscellaneous Projects | 151344.64 | 172532.8896 | 0 | 172532.8896
10th of Ramadan Railway | 2000001 |  | 10th of Ramadan Railway | 1528353 | 1448114.47 | 0 | 1448114.47
ESU Ph2-Enabling & Struc | ESU2-MEP-IPC10 | 10 | ESU Ph2-Enabling & Struc10 | 44073475.24 | 9765894.202 | 12724287.74 | 22490181.942
Lekela 250MW Wind Farm | LEKELA-SUPPLY-IPC01 | 1 | Lekela 250MW Wind Farm1 | 125000 | 124228 | 0 | 124228
Toshka GIS 500 kV | Toshka Sub Inv. 01 | 1 | Toshka GIS 500 kV1 | 28800522.23 | 18816139.97 | 7560137.09 | 26376277.06
Toshka GIS 500 kV | Toshka Sub Inv. 16 $ | 16 | Toshka GIS 500 kV16 | 179629.71 | 103266.16 | 47152.8 | 150418.96
R5 | inv ( 12 ) | 12 | R512 | 2196000 | 329400 | 0 | 2031742.96
Miscellaneous Projects | 2011210004 |  | Miscellaneous Projects | 158424.28 | 180603.6792 | 0 | 180603.6792
Miscellaneous Projects | 2011210003 |  | Miscellaneous Projects | 140230.2 | 159862.428 | 0 | 159862.428
Beni Seuf - 358 | Inv. 8 Oewon Mousa | 8 | Beni Seuf - 3588 | 12574794.7 | 8528325.5 | 2160249.89 | 10688575.39
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $7 | 7 | Benban 3/ Toshka 2 LOT 47 | 946341.06 | 794926.49 | 99365.81 | 894292.3
Canal Sugar OHTL | Inv.07 Sugar OHTL | 7 | Canal Sugar OHTL7 | 21618233.86 | 17078404.74 | 3242735.08 | 20321139.82
Group # 1 - 25 LX | Reailway PSP Inv. 02 | 2 | Group # 1 - 25 LX2 | 1212400 | 1200276 | 0 | 1200276
Lahoon 220/22/22 | Al-Lahoon Sub Inv 04 | 4 | Lahoon 220/22/224 | 17396351.17 | 0 | 4349087.79 | 4349087.79
Lahoon 220/22/22 | Al-Lahoon Sub Inv 01 | 1 | Lahoon 220/22/221 | 13414631.32 | 7899886.77 | 3484319.83 | 11384206.6
Sherouk Bridge- LOCK&LOAD | SHOROUK L&L-IPC01 | 1 | Sherouk Bridge- LOCK&LOAD1 | 728000 | 550000 | 0 | 550000
Ismailiya East Substation | ISE-CW-EURO-03 | 3 | Ismailiya East Substation3 | 4429057.2 | 3700957.79 | 0 | 3700957.79
AWEER POWER STATION 'H' Phase | LOC/012 |  | AWEER POWER STATION 'H' Phase | 192126.31 | 189991.58 | 0 | 189991.58
4 SS - Technical Service | 397 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Miscellaneous Projects | 2007210002 |  | Miscellaneous Projects | 115.06 | 0 | 0 | 0
Ministries A17-A18 | IPC_8_Gama_17-18 | 18 | Ministries A17-A1818 | 232012 | 195031.426 | 0 | 195031.426
Koning Food LP-04-20 | 4 |  | Koning Food LP-04-20 | 18900 | 21546 | 0 | 21546
Nuweibaa (Swro) | 2012210005 |  | Nuweibaa (Swro) | 1208131.98 | 966505.58 | 241626.4 | 1208131.98
Cairo Capital S1 | Inv. 1 S1 | 1 | Cairo Capital S11 | 66935348.57 | 50698102.41 | 10040302.29 | 60738404.7
Taval Sarai 52 | IPC_7_Saray_Gama |  | Taval Sarai 52 | 345987.1 | 276290.17 | 0 | 276290.17
EGAT Pelletizing Plant | EGAT IPC01 | 1 | EGAT Pelletizing Plant1 | 5145072.9 | 4836368.8 | 514507.29 | 5350876.09
LRT | IPC#1` | 1 | LRT1 | 80892 | 36288.48 | 0 | 36288.48
West Port Said 220 kV GIS | P-45-Portsaid Inv.03 | 3 | West Port Said 220 kV GIS3 | 18587846.66 | 0 | 1951723.9 | 1951723.9
New Babil 400/132KV Substation | 2103210001 |  | New Babil 400/132KV Substation | 446401 | 446401 | 0 | 446401
Assuit PP (CP-118) | 2101210004 |  | Assuit PP (CP-118) | 1956 | 1745.73 | 308.07 | 2053.8
Al-Wukair 11 Substation | 2103210018 |  | Al-Wukair 11 Substation | 284086.66 | 284086.66 | 0 | 284086.66
AWEER POWER STATION 'H' Phase | ENG-036 | 36 | AWEER POWER STATION 'H' Phase36 | 289170.02 | 303628.52 | 0 | 303628.52
NUCA R05 - Z02 | R5 FINSHING-IPC10 | 10 | NUCA R05 - Z0210 | 11021038.6 | 8733759.6 | 1102103.9 | 9835863.5
Miscellaneous Projects | 2102210005 |  | Miscellaneous Projects | 119999.34 | 136799.2476 | 0 | 136799.2476
ORA-ZED Towers01B | IPC_5_ORA |  | ORA-ZED Towers01B | 167989.23 | 123937.39 | 0 | 123937.39
New Babil 400/132KV Substation | 2103210017 |  | New Babil 400/132KV Substation | 155065.61 | 155065.61 | 0 | 155065.61
158E/2019 33kv Project | 10482 |  | 158E/2019 33kv Project | 29440 | 52992 | 0 | 26496
LAYAN Substation | 10525 |  | LAYAN Substation | 733262.83 | 4956856.24 | 0 | 619607.03
Miscellaneous Projects | 2103210006 |  | Miscellaneous Projects | 10500 | 11655 | 0 | 11655
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC08 | 8 | EMAAR-Pkg#162/163- Marassi8 | 7771514.83 | 6324880.5415 | 809350.38 | 7134230.9215
Ghana Street lighting | MIDA Sply. Inv.6 | 6 | Ghana Street lighting6 | 382165.22 | 343948.7 | 0 | 343948.7
SHATRA 400/132kV SS | 405 |  | SHATRA 400/132kV SS | 1639704.94 | 1639704.94 | 0 | 1639704.94
Bahr ElBakar – Power Station | IPC005 - Mdkour | 5 | Bahr ElBakar – Power Station5 | 1513632 | 1498495.68 | 0 | 1498495.68
New Babil 400/132KV Substation | 2105210011 |  | New Babil 400/132KV Substation | 103377.07 | 103377.07 | 0 | 103377.07
Mauritania Lot 1 | Inv.2 - Lot 1 | 2 | Mauritania Lot 12 | 222136.46 | 211029.64 | 0 | 211029.64
Akhmem Assiut | Ref.Ret Asuit akh 2 |  | Akhmem Assiut | 20000000 | 20000000 | 0 | 20000000
Miscellaneous Projects | 2105210015 |  | Miscellaneous Projects | 58260 | 66416.4 | 0 | 66416.4
DoubleTree Mangroovy ElGouna | Mangroovy - IPC016 | 16 | DoubleTree Mangroovy ElGouna16 | 4424891.64 | 3166964.612 | 1067784.06 | 4234748.672
Cairo Capital Cables Tunnel | Tunnel Inv. 10 | 10 | Cairo Capital Cables Tunnel10 | 24621268.7 | 16323901 | 6155317.2 | 22479218.2
Faculty of Medicine | Mansoura IPC 14 | 14 | Faculty of Medicine14 | 12586444.76 | 10649618.27 | 629322.24 | 11278940.51
R5 Mix-Use Complex Project | R5 ZONE1-IPC09 | 9 | R5 Mix-Use Complex Project9 | 1179207.85 | 1097160.7825 | 135321.71 | 1232482.4925
Ministries Buildings | MIN ELCTRO-IPC04 | 4 | Ministries Buildings4 | 158785151.6 | 19340990 | 52365755.85 | 134736623.85
AWEER POWER STATION 'H' Phase | CON/020 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
AWEER POWER STATION 'H' Phase | CON/022 |  | AWEER POWER STATION 'H' Phase | 425899.55 | 373845.1575 | 47322.17 | 421167.3275
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .24 | 24 | Benban 3/ Toshka 2 LOT 424 | 61292.22 | 47845.8 | 6435.68 | 54281.48
4 SS - Technical Service | 418 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
33KV Canal Farm Grid | Inv. 12 Farm | 12 | 33KV Canal Farm Grid12 | 22843959.67 | 17429941.23 | 3426593.95 | 20856535.18
33KV Canal Farm Grid | Inv. 13 Farm | 13 | 33KV Canal Farm Grid13 | 11233898.71 | 8571464.72 | 1685084.81 | 10256549.53
Sultana Malak Restoration | Sultana Malak IPC02 | 2 | Sultana Malak Restoration2 | 9278913.66 | 0 | 7562784.65 | 7562784.65
158E/2019 33kv Project | 10625 |  | 158E/2019 33kv Project | 482736 | 1303387.2 | 0 | 434462.4
Solera LP-08-21 | 37 |  | Solera LP-08-21 | 723400.12 | 704264 | 0 | 704264
seashell Playa | IPC-5-PLAYA | 5 | seashell Playa5 | 109610 | 76518.745 | 17537.6 | 94056.345
MAYSAN 400/132kV SS | 412 |  | MAYSAN 400/132kV SS | 83995.03 | 83995.03 | 0 | 83995.03
AWEER POWER STATION 'H' Phase | ENG/041 |  | AWEER POWER STATION 'H' Phase | 187950.14 | 197347.647 | 0 | 197347.647
Miscellaneous Projects | 2105210013 |  | Miscellaneous Projects | 21000 | 23940 | 0 | 11970
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.04 | 4 | Toshka 2/Owinat East LOT2 OHTL4 | 4622103.87 | 4122523.81 | 485320.91 | 4607844.72
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 26 | 26 | ORA ZED-Ph 2-Pkgs A&D26 | 3475331.25 | 2884524.9425 | 364909.78 | 3249434.7225
ORA ZED-Ph 2-Pkgs A&D | ipc16 ora zed(2) | 16 | ORA ZED-Ph 2-Pkgs A&D16 | 11487525.58 | 9768410.9408 | 1235762.83 | 11004173.7708
ORA ZED - Ph 01B - Pkgs A&D | ora ph.1 - IPC20 | 20 | ORA ZED - Ph 01B - Pkgs A&D20 | 25297815.24 | 21744431.032 | 2587156.1 | 24331587.132
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 - IPC13 | 13 | ORA ZED-Ph 2-Pkgs A&D13 | 15564144.34 | 13357287.557 | 1689777.34 | 15047064.897
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 - inv. 11 | 11 | ORA ZED-Ph 2-Pkgs A&D11 | 10555360.84 | 12170282.5 | 1533288.84 | 13703571.34
Air Force Project | Air Force Inv . 10 | 10 | Air Force Project10 | 5938733.6 | 4251725 | 1484683.4 | 5736408.4
Air Force Project | Air Force Inv . 03 | 3 | Air Force Project3 | 8572918.36 | 6138209.5 | 2143229.59 | 8281439.09
Mansoura University | IPC#3 - Mansoura | 3 | Mansoura University3 | 159601.58 | 153875.91 | 0 | 153875.91
RING ROAD MARYOTIA EXPANSION | Maryotia IPC08+ | 8 | RING ROAD MARYOTIA EXPANSION8 | 541409.52 | 172574.47 | 0 | 172574.47
Kafr Shokr Bridge | Kafr Shokr IPC05 | 5 | Kafr Shokr Bridge5 | 6107250 | 5371513.65 | 0 | 5371513.65
EMAAR-PKG# 144, Marassi | IPC-FINAL-PKG#144 |  | EMAAR-PKG# 144, Marassi | 150533.25 | 1116473.9425 | 0 | 1116473.9425
LP-07-21 Petrojet | 45 |  | LP-07-21 Petrojet | 6396932 | 3081350.89 | 1599233 | 4680583.89
Berty Badr Bridge | Inv (1) PBadr | 1 | Berty Badr Bridge1 | 707034.36 | 400000 | 0 | 400000
Supply E.S. Kit - MAUR. | Inv. No.1 MRT Supply | 1 | Supply E.S. Kit - MAUR.1 | 29938 | 29935.38 | 0 | 29935.38
Mauritania-Lot 2 | Inv.13 – Lot 2 | 13 | Mauritania-Lot 213 | 395815.79 | 375968.88 | 0 | 375968.88
Mauritania-Lot 2 | Inv.12 - Lot 2 | 12 | Mauritania-Lot 212 | 516333.64 | 490516.96 | 0 | 490516.96
ElMoneeb 2 | IPC#5 - Additional | 5 | ElMoneeb 25 | 67870 | 67870 | 0 | 67870
Koning Food LP-04-20 | 23 |  | Koning Food LP-04-20 | 51860 | 59120.4 | 0 | 59120.4
DoubleTree Mangroovy ElGouna | Mngrovy Final IPC018 | 18 | DoubleTree Mangroovy ElGouna18 | 2844607.33 | 5619891.3535 | 0 | 5619891.3535
MDF Factory | MDF IPC03 | 3 | MDF Factory3 | 9210979.01 | 8598866.2305 | 2417881.99 | 11016748.2205
TNYA-WSHP | 11545 |  | TNYA-WSHP | 740609.528 | 1877445.1332 | 0 | 625815.0444
Ras El Teen Hangar | Ras El Teen IPC01 | 1 | Ras El Teen Hangar1 | 3705155.84 | 2378339.532 | 1167124.09 | 3545463.622
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC07 | 7 | ElSewedy HQ Internal Finishing7 | 14463563.81 | 9724934.81 | 4152776.12 | 19095586.9605
Akhmem Assiut | Ref.Ret Asuit akh 3 |  | Akhmem Assiut | 22000000 | 22000000 | 0 | 22000000
Racecores 3092-16 132KV C | 11022 |  | Racecores 3092-16 132KV C | 124343 | 619228.14 | 0 | 103204.69
SHAT Al ARAB 400/132kV SS | 434 |  | SHAT Al ARAB 400/132kV SS | 38812.4 | 38812.4 | 0 | 38812.4
Racecores 3092-17 132KV E | 11026 |  | Racecores 3092-17 132KV E | 386877.49 | 2568866.64 | 0 | 321108.33
Playa Resort | 21000006 |  | Playa Resort | 30749470 | 0 | 34746901.1 | 34746901.1
New Babil 400/132KV GIS Substa | 2107210002 |  | New Babil 400/132KV GIS Substa | 1355660 | 1355660 | 0 | 1355660
Akhmem - Qena | Ret Qen-akh 6 T |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
Akhmem - Qena | Ref.Ret Qen-akh 6 |  | Akhmem - Qena | 5000000 | 0 | 0 | 5000000
Akhmem Assiut | Ret Asuit akh 5 T |  | Akhmem Assiut | 4316843.16 | 4316843.16 | 0 | 4316843.16
Cairo-Alex Railway | Cairo-Alex IPC012 | 12 | Cairo-Alex Railway12 | 29658847.99 | 19205171.1 | 3114179.04 | 22319350.14
Racecores 3092-16 132KV C | 11002 |  | Racecores 3092-16 132KV C | 105755.13 | 105755.13 | 0 | 105755.13
Get Business Complex | INV ( 11 ) GET | 11 | Get Business Complex11 | 197003.64 | 185183.42 | 0 | 185183.42
Get Business Complex | INV ( 8 ) GET | 8 | Get Business Complex8 | 896679.8 | 842879.01 | 0 | 842879.01
Senator | Inv ( 2 ) Sentor | 2 | Senator2 | 296549 | 171000 | 0 | 171000
Ring Road Bridges Project | INV ( 3 ) Ring R | 3 | Ring Road Bridges Project3 | 503859.8 | 392881.91 | 0 | 392881.91
LAYYAH CCPP | 518 |  | LAYYAH CCPP | 7712820 | 6402637 | 1310183 | 7712820
EGAT Pelletizing Plant | EGAT IPC07 | 7 | EGAT Pelletizing Plant7 | 12829691.38 | 12058937.829 | 1283941.21 | 13342879.039
Air Force Project | Air Force Inv . 20 | 20 | Air Force Project20 | 3250344.96 | 3139668 | 0 | 3139668
Ain Sokhna Bridge – RME | IPC#03 - Sokhna Brid | 3 | Ain Sokhna Bridge – RME3 | 1355125 | 135512.5 | 0 | 1334241.5
Akhmem Assiut | Ref-Ret-Assuit $ T |  | Akhmem Assiut | 3471149.12 | 3431960.96 | 0 | 3431960.96
TZ – Offshore E&M Procurement | 466 |  | TZ – Offshore E&M Procurement | 135857 | 122271.3 | 0 | 122271.3
Akhmem - Qena | رد تامين اخميم قنا |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
Akhmem - Qena | رد تامين اخميم قنا 2 |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
Racecores 3092-17 132KV E | 11202 |  | Racecores 3092-17 132KV E | 10080 | 10584 | 0 | 10584
Kafr Shokr Bridge | Kafr Shokr_IPC01 | 1 | Kafr Shokr Bridge1 | 32770679.81 | 29730005.7605 | 0 | 29730005.7605
Ain Sokhna Bridge – RME | IPC#4 - Sokhna Bridg | 4 | Ain Sokhna Bridge – RME4 | 1558625 | 360619.75 | 0 | 1543038.75
Cairo-Alex Railway | Railway IPC07 | 7 | Cairo-Alex Railway7 | 24014920 | 16990381.6 | 2401492 | 19391873.6
TZ – Offshore E&M Procurement | 446 |  | TZ – Offshore E&M Procurement | 5830.48 | 5830.48 | 0 | 5830.48
Benban 500 K.V/95 K.M | Ref-Ret-benban 2 $ T |  | Benban 500 K.V/95 K.M | 1447097.67 | 1447097.67 | 0 | 1447097.67
Racecores 3092-16 132KV C | 11344 |  | Racecores 3092-16 132KV C | 10500 | 11025 | 0 | 11025
TZ – Offshore E&M Procurement | 450 |  | TZ – Offshore E&M Procurement | 275681.7 | 192977.22 | 55136.09 | 248113.31
SHATRA 400/132kV SS | 436 |  | SHATRA 400/132kV SS | 134990.29 | 134990.29 | 0 | 134990.29
Racecores 3092-16 132KV C | 11345 |  | Racecores 3092-16 132KV C | 11400 | 11970 | 0 | 11970
RING ROAD MARYOTIA EXPANSION | Maryotia IPC014 | 14 | RING ROAD MARYOTIA EXPANSION14 | 44712557.52 | 14554103.9 | 0 | 39554103.9
Racecores 3092-17 132KV E | 11163 |  | Racecores 3092-17 132KV E | 331266.34 | 1099804.24 | 0 | 274951.06
Hyper One Badr | inv ( 1-2-3 ) Hayper | 1 | Hyper One Badr1 | 1835955 | 1633999.95 | 0 | 1633999.95
Ghana Street lighting | MIDA Sply.inv.11 | 11 | Ghana Street lighting11 | 190827.34 | 171744.6 | 0 | 171744.6
Akhmem - Qena | Ret Quana akh USD T |  | Akhmem - Qena | 283226.77 | 276511.9 | 0 | 276511.9
Zone(J) South Valley Toshka | South Valley Inv. 13 | 13 | Zone(J) South Valley Toshka13 | 81984536 | 61573816.85 | 10494020.64 | 72067837.49
Mangrouve Hotel - Gouna | IPC-4-GOUNA | 4 | Mangrouve Hotel - Gouna4 | 5069.28 | 4488.86 | 0 | 4488.86
New Giza Hospital | IPC-2-NEW GIZA | 2 | New Giza Hospital2 | 49576.04 | 42541.21 | 0 | 42541.21
Racecores 3092-16 132KV C | 11426 |  | Racecores 3092-16 132KV C | 7000 | 7350 | 0 | 7350
Abou Matamer & Samanoud | Ref Ret Samanod& mat |  | Abou Matamer & Samanoud | 4561945.18 | 4561945.18 | 0 | 4561945.18
Governmental Campus-N2 | 65 |  | Governmental Campus-N2 | 136850 | 136850 | 0 | 136850
Infra Project 4428 | 220421004 |  | Infra Project 4428 | -134285714.29 | 0 | 0 | 0
Racecores 3092-17 132KV E | 11501 |  | Racecores 3092-17 132KV E | 1452.53 | 1452.53 | 0 | 1452.53
Racecores 3092-17 132KV E | 11446 |  | Racecores 3092-17 132KV E | 58508.73 | 49440.3765 | 0 | 49440.3765
October Dry Port | Dry Port Inv. 07 | 7 | October Dry Port7 | 25984270.5 | 6366407.68 | 6820871.01 | 13187278.69
MDF Factory | MDF FACTORY2 IPC04 | 4 | MDF Factory4 | 2097847.2 | 2118825.668 | 0 | 2118825.668
Mivida BP#189 | PKG#189 IPC 29 | 29 | Mivida BP#18929 | 369049.79 | 2690517.4595 | 357346.78 | 3047864.2395
Ghana Street lighting | MIDA Ins.inv.12 | 12 | Ghana Street lighting12 | 19782.53 | 17804.28 | 0 | 17804.28
PLAYA ROOF & Wet Areas | IPC-8-PLAYA ROOF | 8 | PLAYA ROOF & Wet Areas8 | 211822.15 | 180758.74 | 0 | 180758.74
EGAT Pelletizing Plant | EGAT WaterTank IPC07 | 7 | EGAT Pelletizing Plant7 | 399729.3 | 395732.005 | 0 | 395732.005
AWEER POWER STATION 'H' Phase | ENG/054 |  | AWEER POWER STATION 'H' Phase | 1230673.4 | 1292207.07 | 0 | 1292207.07
Faculty of Medicine | mansora finish ipc17 | 17 | Faculty of Medicine17 | 33386477.14 | 24807431 | 5007971.57 | 29815402.57
October Dry Port | Dry Port Inv. 09 | 9 | October Dry Port9 | 21934548.75 | 15623254.08 | 5757819.05 | 21381073.13
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv14 | 14 | Marsa Alam/ Bernes LOT2 OHTL14 | 424162.49 | 382089.84 | 0 | 382089.84
Ora Zed Landscape Ph1 | Ora Landsape ipc 21 | 21 | Ora Zed Landscape Ph121 | 324859.52 | 108767.386 | 144976.25 | 253743.636
Ora Zed Landscape Ph1 | Ora Landscape ipc 15 | 15 | Ora Zed Landscape Ph115 | 3753240.01 | 3165189.2 | 394090.2 | 3559279.4
Railway Bridge - El Hammam | IPC#5 ElHammam | 5 | Railway Bridge - El Hammam5 | 468238 | 426786.65 | 0 | 426786.65
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 09 | 9 | Hosh Essa 220 KV OHTL9 | 7150106.67 | 1037876.75 | 750761.2 | 1788637.95
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 10 | 10 | Hosh Essa 220 KV OHTL10 | 182617.6 | 96969.45 | 19174.85 | 116144.3
Hassan El Mamoun Bridge | hasan Mamoun 2 Final |  | Hassan El Mamoun Bridge | 21747325.71 | 2283455 | 17968704.18 | 20252159.18
New Babil 400/132KV GIS Substa | 220621001 |  | New Babil 400/132KV GIS Substa | 2734793.51 | 2734793.51 | 0 | 2734793.51
HST Bridges-Sokhna & Mahager | sokhna bridge ipc02 | 2 | HST Bridges-Sokhna & Mahager2 | 15445843.81 | 13771117.5205 | 0 | 13771117.5205
Neighborhood New Capital R5 | inv ( 2 ) fainal | 2 | Neighborhood New Capital R52 | 326600 | 301125.2 | 0 | 301125.2
Benban 3/ Toshka 2 LOT 4 | Ref-Ret-Toshka Lot4T |  | Benban 3/ Toshka 2 LOT 4 | 33020632.09 | 33020632.09 | 0 | 33020632.09
Abo Quir - Badr 500KV | Ref.Abu Quir Badr-T |  | Abo Quir - Badr 500KV | 113544.93 | 113544.93 | 0 | 113544.93
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .28 | 28 | Benban 3/ Toshka 2 LOT 428 | 14932972.26 | 9369229.26 | 0 | 9369229.26
TZ – Offshore E&M Procurement | 475 |  | TZ – Offshore E&M Procurement | -274863.23 | -274863.23 | 0 | -274863.23
TZ – Offshore E&M Procurement | 471 |  | TZ – Offshore E&M Procurement | 832010.31 | 624008.19 | 124801.09 | 748809.28
Marassi - Water proofing | IPC-1-PK177-Waterpro | 1 | Marassi - Water proofing1 | 73972.36 | 65502.52 | 0 | 65502.52
BKG#178-Lagoon Discharge | pkg#178 ipc08 | 8 | BKG#178-Lagoon Discharge8 | 1389835.52 | 668886.796 | 0 | 668886.796
NUCA R05 - Z02 | Ro5 (2) ipc 20 | 20 | NUCA R05 - Z0220 | 32863219.49 | 27573057.68 | 3515743.2 | 31088800.88
PLAYA ROOF & Wet Areas | 12 |  | PLAYA ROOF & Wet Areas | 805054.453 | 690817.233 | 0 | 690817.233
seashell Playa | IPC020 | 20 | seashell Playa20 | 579335.07 | 497127.43 | 0 | 497127.43
Sultana Malak Restoration | sultana malak2 ipc01 | 1 | Sultana Malak Restoration1 | 8421662.9 | 7827175 | 0 | 7827175
EMAAR-Pkg#162/163- Marassi | pkg#163 ipc 23 | 23 | EMAAR-Pkg#162/163- Marassi23 | 6328514.78 | 3653330.379 | 0 | 3653330.379
EMAAR-Pkg#162/163- Marassi | pkg#163- IPC24 | 24 | EMAAR-Pkg#162/163- Marassi24 | 6666259.32 | 6005632.246 | 0 | 6005632.246
Kattameya Creeks | kattamya ipc17 | 17 | Kattameya Creeks17 | 37521775.17 | 36571027.7485 | 2451618.43 | 39022646.1785
SSC Suez Steel Company Project | Supply SSC IPC 4 | 4 | SSC Suez Steel Company Project4 | 389998.19 | 0 | 145113.66 | 440697.9566
SSC Suez Steel Company Project | I&RSUPPLY (ABB) IPC5 | 5 | SSC Suez Steel Company Project5 | 8225548.17 | 0 | 2834850.89 | 9294869.4338
SSC Suez Steel Company Project | In&ReSupply ABB-IPC2 | 2 | SSC Suez Steel Company Project2 | 8551701.56 | 7437728.3384 | 2225694.42 | 9663422.7584
SSC Suez Steel Company Project | int&ret app(ssc)ipc5 | 5 | SSC Suez Steel Company Project5 | 2754124.9 | 2699925.476 | 357153.16 | 3057078.636
Air Defence College | TR0046/1 |  | Air Defence College | 434589 | 368966.06 | 0 | 368966.06
Egyptian Exchange building | TR0039-IPC0039 | 39 | Egyptian Exchange building39 | 15357.47 | 12569.04 | 0 | 12569.04
PLAYA ROOF & Wet Areas | 13 |  | PLAYA ROOF & Wet Areas | 141699.04 | 121591.95 | 0 | 121591.95
Playa Resort | kantine 2 |  | Playa Resort | 35000 | 0 | 35000 | 35000
Ministries Buildings | العناصر المائية ipc4 | 4 | Ministries Buildings4 | 2124658 | 1789620 | 0 | 1789620
Ring Road El Mansoria | INV (3 ) AL Mansorya | 3 | Ring Road El Mansoria3 | 145140 | 58056 | 0 | 58056
Railway Bridge - El Hammam | IPC#4 ELHammam | 4 | Railway Bridge - El Hammam4 | 1811308 | 1523339.51 | 0 | 1523339.51
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 ipc10 | 10 | ORA ZED-Ph 2-Pkgs A&D10 | 25761823.86 | 22199070.249 | 2641249.36 | 24840319.609
Railway Bridge - El Hammam | IPC#3 ElHammam | 3 | Railway Bridge - El Hammam3 | 532834.48 | 498466.66 | 0 | 498466.66
EMAAR- Pkg 140-ITP-Mivida | pkg#140 ipc27 | 27 | EMAAR- Pkg 140-ITP-Mivida27 | 825139.18 | 6499741.709 | 0 | 6499741.709
Ministries Buildings | SHELL IPC09 | 9 | Ministries Buildings9 | 18018358 | 0 | 0 | 16036338.62
Egat Rolling Mill no.4 | Rolling Mill IPC8 | 8 | Egat Rolling Mill no.48 | 21317723 | 16970582.32 | 5199849.6 | 22170431.92
MDF Factory | MDF Factory3 IPC5 | 5 | MDF Factory5 | 3536061.27 | 2517907.4178 | 1007777.46 | 3525684.8778
Railway Bridge - Assuit | IPC#8 Assuit | 8 | Railway Bridge - Assuit8 | 1153260 | 1060999.2 | 0 | 1060999.2
Ismailiya East Substation | ismalyia ipc28 final | 28 | Ismailiya East Substation28 | 2858104.7 | 2294947.36 | 0 | 2294947.36
Sokhna Port Expansion | sokh.port roads ipc1 | 1 | Sokhna Port Expansion1 | 2098544.62 | 1800470.45 | 0 | 1800470.45
Get Business Complex | Cr.INV ( 14 ) GET | 14 | Get Business Complex14 | 230869.31 | 217017.15 | 0 | 217017.15
seashell Playa | IPC00024 | 24 | seashell Playa24 | 867016.27 | 743981.76 | 0 | 743981.76
seashell Playa | IPC#023 | 23 | seashell Playa23 | 617575.14 | 499891.23 | 0 | 499891.23
Cairo-Alex Railway | cairo - alex ipc 30 | 30 | Cairo-Alex Railway30 | 12783976.19 | 617363.65 | 9603026.5 | 10220390.15
seashell Playa | IPC#22 | 22 | seashell Playa22 | 621903.28 | 507755.22 | 0 | 507755.22
Creeks URBN-K | URBIN-K IPC 10+ | 10 | Creeks URBN-K10 | 20086171.5 | 889617.682 | 20000000 | 20889617.682
HSR-6th of October | IPC#5 HSR | 5 | HSR-6th of October5 | 1253000 | 1090110 | 0 | 1090110
Sixty Iconic Tower | Inv ( 9 ) sixty | 9 | Sixty Iconic Tower9 | 1120470 | 315202.5 | 0 | 315202.5
Kayan 3 New Cairo Capital City | Kayan IPC4 | 4 | Kayan 3 New Cairo Capital City4 | 2093783 | 1972990 | 0 | 1972990
Seashell Playa 5 Villas | seashell playa-IPC1 | 1 | Seashell Playa 5 Villas1 | 161096.6 | 130727.19 | 0 | 130727.19
SSC Suez Steel Company Project | Revamp ipc 9 | 9 | SSC Suez Steel Company Project9 | 1572976.38 | 1085353.7052 | 471892.91 | 1557246.6152
SSC Suez Steel Company Project | Revamp ipc (3) | 3 | SSC Suez Steel Company Project3 | 2879525.93 | 0 | 863857.79 | 2994706.9672
SSC Suez Steel Company Project | Revamp IPC1 | 1 | SSC Suez Steel Company Project1 | 3199345.21 | 2207548.1984 | 959803.56 | 3167351.7584
Air Defense College | Airdevance7 IPC1 | 1 | Air Defense College1 | 90222127 | 14363600 | 53500000 | 74274425
PLAYA ROOF & Wet Areas | IPC0000000015 | 15 | PLAYA ROOF & Wet Areas15 | 94886.04 | 51371.71 | 0 | 51371.71
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED1-IPC04 | 4 | ORA ZED - Ph 01B - Pkgs A&D4 | 26593168.54 | 26411905.937 | 3145501.01 | 29557406.947
SSC Suez Steel Company Project | R.O. Supply-IPC3 | 3 | SSC Suez Steel Company Project3 | 9778491.46 | 8116147.9144 | 2933547.44 | 11049695.3544
ORA-ZED Towers P01B | IPC#00005 | 5 | ORA-ZED Towers P01B5 | 189600 | 167890.8 | 0 | 167890.8
EGAT Lock & Load | L&L IPC10 | 10 | EGAT Lock & Load10 | 931996.59 | 876076.7895 | 93199.66 | 969276.4495
Kemet Tower | inv ( 5 ) Kemt | 5 | Kemet Tower5 | 237600 | 163708.56 | 0 | 163708.56
PLAYA ROOF & Wet Areas | IPC000018 | 18 | PLAYA ROOF & Wet Areas18 | 32805.45 | 26544.77 | 0 | 26544.77
seashell Playa | 26 |  | seashell Playa | 64275.61 | 55154.9 | 0 | 55154.9
U4,U8 Seashell Playa | IPC002 TR60 | 2 | U4,U8 Seashell Playa2 | 572180.64 | 353035.2 | 0 | 353035.2
Olympic Multi – Sports Hall | Olym Fire IPC1 | 1 | Olympic Multi – Sports Hall1 | 887566 | 160730 | 580000 | 740730
EGAT Injection | IPC0000005 | 5 | EGAT Injection5 | 18749.55 | 16088.99 | 0 | 16088.99
Egyptian Exchange building | IPC0000010 | 10 | Egyptian Exchange building10 | 85472.01 | 75685.47 | 0 | 75685.47
Kayan 3 New Cairo Capital City | Kayan MEP IPC fin |  | Kayan 3 New Cairo Capital City | 29771651 | 13451220 | 0 | 13451220
NUCA R05 - Z02 | R05(2) ipc 32 | 32 | NUCA R05 - Z0232 | 29719120.95 | 22951401.3805 | 2895575.5 | 25846976.8805
HST El Mahager Bridge | EL MAHAGER IPC 01 | 1 | HST El Mahager Bridge1 | 42907858.33 | 3290022.0867 | 0 | 37408234.0867
HST Culverts | Hst Culverts ipc 01 | 1 | HST Culverts1 | 39779000.76 | 22255333.2376 | 0 | 36255333.2376
MDF Factory | ipc14 mdf factory2 | 14 | MDF Factory14 | 1329223.07 | 1342515 | 0 | 1342515
SSC Suez Steel Company Project | R.Osup Pri ADJ. IPC1 | 1 | SSC Suez Steel Company Project1 | 14675847.72 | 15849915.5156 | 0 | 15849915.5156
DP World Basin 2 Ph2 | Dp world ph2 ipc 11 | 11 | DP World Basin 2 Ph211 | 58932579.7 | 43610108.98 | 8839886.95 | 52449995.93
DP World Basin 2 Ph2 | dp world ipc(7=8) | 7 | DP World Basin 2 Ph27 | 21511754.48 | 15918423.282 | 3226763.17 | 19145186.452
EGAT Pelletizing Plant | Egat Mep Mobili ipc4 | 4 | EGAT Pelletizing Plant4 | 456912.02 | 475188.5008 | 0 | 475188.5008
Wady El Natroon Bridge | wady el natroon ipc2 | 2 | Wady El Natroon Bridge2 | 10422940 | 3115862.55 | 0 | 3115862.55
HST Culverts | HST CULVERTS IPC 2 | 2 | HST Culverts2 | 524792.19 | 433670.8 | 0 | 433670.8
Sixty Iconic Tower | inv ( 1 ) sixty | 1 | Sixty Iconic Tower1 | 1454355 | 4101281.1 | 0 | 1367093.7
SSC Suez Steel Company Project | R.O(5000:8000)SIPC.4 |  | SSC Suez Steel Company Project | 7605000 | 6312150 | 2281500 | 8593650
Olympic Multi – Sports Hall | Oly elec IPC1 | 1 | Olympic Multi – Sports Hall1 | 7086895 | 1590500 | 4300000 | 5890500
SSC Suez Steel Company Project | R.O 5:8 APPLY IPC 1 | 1 | SSC Suez Steel Company Project1 | 2250265.4 | 1730229.064 | 767565.53 | 2497794.594
SSC Suez Steel Company Project | R.O - supply ipc 2 | 2 | SSC Suez Steel Company Project2 | 1896616.8 | 1574191.942 | 568985.04 | 2143176.982
RING ROAD MARYOTIA EXPANSION | El-Marg IPC06 | 6 | RING ROAD MARYOTIA EXPANSION6 | 1415139.9 | 1254124.85 | 0 | 1254124.85
Seashell Playa 5 Villas | playa c-204 ipc 1 | 1 | Seashell Playa 5 Villas1 | 106544.39 | 92011.74 | 0 | 92011.74
Expansion of Ring Road-CFA | IPC 1/2 CFA | 1 | Expansion of Ring Road-CFA1 | 1739849.5 | 110000 | 0 | 110000
Olympic Multi – Sports Hall | Olympic Hall IPC03 | 3 | Olympic Multi – Sports Hall3 | 51360259.65 | 43710626.09 | 0 | 43710626.09
Ahl Misr P3 – Zamalek Sector | FPC Zamalek |  | Ahl Misr P3 – Zamalek Sector | 587250 | 568164.37 | 0 | 568164.37
PVD - El Hammam | IPC 2 PVD | 2 | PVD - El Hammam2 | 231328.57 | 204494.45 | 0 | 204494.45
AIRDEFNSE -EPOXY | IPC05TR0066 | 5 | AIRDEFNSE -EPOXY5 | 381884.4 | 324219.86 | 0 | 324219.86
U7-SEASHELL | IPC04 TR64 | 4 | U7-SEASHELL4 | 454840.57 | 392800.31 | 0 | 392800.31
Alamein Coastal Road Bridge | Alamein sahely IPC1 | 1 | Alamein Coastal Road Bridge1 | 3743238.1 | 2832840 | 0 | 2832840
EGAT Mechanical Installations | Egat Mech Equip ipc2 | 2 | EGAT Mechanical Installations2 | 24000790.6 | 18238200.7161 | 6000197.65 | 24238398.3661
Seashell Playa 5 Villas | playa c045- ipc 3 | 3 | Seashell Playa 5 Villas3 | 49879.56 | 70606.1 | 0 | 70606.1
SEASHELL TECHNICAL ROOM | IPC0001TR65 | 1 | SEASHELL TECHNICAL ROOM1 | 74256 | 64127.43 | 0 | 64127.43
PLAYA ROOF & Wet Areas | IPC0023 TR41 | 23 | PLAYA ROOF & Wet Areas23 | 55933.7 | 47996.7 | 0 | 47996.7
U3 & U5 | IPC008 TR55 | 8 | U3 & U58 | 230620.4 | 199163.78 | 0 | 199163.78
Katameya Creeks - RME | IPC 008 TR0055 | 8 | Katameya Creeks - RME8 | 266794.69 | 236246.7 | 0 | 236246.7
Central Capital | INV ( 4 ) Central Ca | 4 | Central Capital4 | 147420 | 55211.76 | 0 | 55211.76
Sokhna Port Expansion | spx.2 ipc 01 | 1 | Sokhna Port Expansion1 | 57988132.8 | 39700885.25 | 11597626.56 | 51298511.81
Cairo-Alex Railway | cairo-alex ipc 41* | 41 | Cairo-Alex Railway41 | 6779667 | 77863291.8 | 0 | 77863291.8
Cairo-Alex Railway | cairo-alex ipc15 | 15 | Cairo-Alex Railway15 | 94581172.88 | 65617126.41 | 9931023.15 | 75548149.56
EGAT Lock & Load | EGAT L&L IPC8 | 8 | EGAT Lock & Load8 | 2786604.1 | 2619407.855 | 278660.41 | 2898068.265
EGAT Pelletizing Plant | EGAT MEP- IPC3 | 3 | EGAT Pelletizing Plant3 | 1266155.18 | 1316801.3872 | 0 | 1316801.3872
EGAT Pelletizing Plant | EGAT MEP-IPC 1 | 1 | EGAT Pelletizing Plant1 | 2011978.5 | 2092457.64 | 0 | 2092457.64
Playa Resort | 230000001 |  | Playa Resort | 35000 | 35000 | 0 | 35000
Tarek Abdel-Hakim Center | TAH ipc 01 | 1 | Tarek Abdel-Hakim Center1 | 1174788.1 | 903999.44 | 105730.93 | 1009730.37
Air Defence College | IPC017 TR46 | 17 | Air Defence College17 | 121741.26 | 103358.324 | 0 | 103358.324
Air Defence College | ipc00016 tr46 | 16 | Air Defence College16 | 51341.93 | 55089.29 | 0 | 55089.29
SOL Town PKG.220 | pkg#220-ipc2 | 2 | SOL Town PKG.2202 | 11462411.01 | 5980500.04 | 3610659.47 | 9591159.51
Seashell Playa 5 Villas | Playa -c234 ipc (2) | 2 | Seashell Playa 5 Villas2 | 251899.5 | 230135.37 | 0 | 230135.37
Seashell Playa 5 Villas | playa-c234 ipc (3) | 3 | Seashell Playa 5 Villas3 | 55618.05 | 50812.87 | 0 | 50812.87
Seashell Playa 5 Villas | Playa-c038 ipc (3) | 3 | Seashell Playa 5 Villas3 | 35410.74 | 20973.67 | 0 | 20973.67
Seashell Playa 5 Villas | Playa -c072 ipc (2) | 2 | Seashell Playa 5 Villas2 | 281581.79 | 243173.96 | 0 | 243173.96
PLAYA ROOF & Wet Areas | IPC24 TR41 | 24 | PLAYA ROOF & Wet Areas24 | 7711.2 | 6616.98 | 0 | 6616.98
Air Defence College | IPC0019 TR46 | 19 | Air Defence College19 | 160397.93 | 143427.84 | 0 | 143427.84
GOV2 - Infra | IPC 24 GOV2 | 24 | GOV2 - Infra24 | 6866553.95 | 2728755.6533 | 415258.04 | 3144013.6933
Villa Clustera Playa | IPC01TR0076 | 1 | Villa Clustera Playa1 | 874855 | 653224.78 | 0 | 653224.78
U6T11 PART1 Palay | IPC01TR0075 | 1 | U6T11 PART1 Palay1 | 19226.59 | 17565.41 | 0 | 17565.41
Olympic Multi – Sports Hall | Olympic Finish IPC6 | 6 | Olympic Multi – Sports Hall6 | 12369937 | 10421270 | 0 | 10421270
Ministries Buildings | Minis alloc IPC13 | 13 | Ministries Buildings13 | 2077967 | 1750290 | 0 | 1750290
SSC Suez Steel Company Project | Baraka Fance ipc 3 | 3 | SSC Suez Steel Company Project3 | 22345362 | 15418299.78 | 6703608.6 | 22121908.38
EL Baragil Bridge | inv ( 1 ) Baragill B | 1 | EL Baragil Bridge1 | 1685715.85 | 1584572.9 | 0 | 1584572.9
Irrigation Tank | IPC04TR0061 | 4 | Irrigation Tank4 | 69919.2 | 60382.22 | 0 | 60382.22
ORA-ZED Towers P01B | IPC12 TR51 | 12 | ORA-ZED Towers P01B12 | 110583.5 | 97921.67 | 0 | 97921.67
Open Channal | IPC02TR0074 | 2 | Open Channal2 | 78848 | 68014.28 | 0 | 68014.28
AIRDEFNSE -EPOXY | IPC07TR0066 | 7 | AIRDEFNSE -EPOXY7 | 38228.4 | 32455.91 | 0 | 32455.91
El-Warraq | ipc no3 elwaraq |  | El-Warraq | 736709.2 | 0 | 0 | 0
Sokhna Port Expansion | spx.2 ipc5 | 5 | Sokhna Port Expansion5 | 4703267 | 3240800 | 940653.4 | 4181453.4
Sultana Malak Restoration | sultana IPC final |  | Sultana Malak Restoration | 368114 | 346340 | 0 | 346340
HST Bridges-Sokhna & Mahager | sokhna bridge ipc16+ | 16 | HST Bridges-Sokhna & Mahager16 | 9873400 | 7751054.1 | 0 | 7751054.1
Wady El Natroon Bridge | wady elnatron ipc06 | 6 | Wady El Natroon Bridge6 | 21784193.33 | 4693085.97 | 0 | 19693085.97
Katameya Creeks - RME | IPC013 TR0053 | 13 | Katameya Creeks - RME13 | 36591.65 | 32401.91 | 0 | 32401.91
Katameya Creeks - RME | IPC0015TR0053 | 15 | Katameya Creeks - RME15 | 96306.39 | 85279.31 | 0 | 85279.31
EIPICO Factory | tr0054 |  | EIPICO Factory | 58672.5 | 50346.85 | 0 | 50346.85
Marassi - Water proofing | IPC004 TR0044 | 4 | Marassi - Water proofing4 | 76374.4 | 67629.54 | 0 | 67629.54
VILLA CLUSTRER B | IPC06TR0077 | 6 | VILLA CLUSTRER B6 | 47940 | 41400.98 | 0 | 41400.98
U7-SEASHELL | IPC13TR0064 | 13 | U7-SEASHELL13 | 16346.4 | 14116.75 | 0 | 14116.75
El Zomor Axis (2) - Leaaba | IPC#Final#Leaaba |  | El Zomor Axis (2) - Leaaba | 49500 | 43065 | 0 | 43065
SSC Suez Steel Company Project | fence western ipc 1 | 1 | SSC Suez Steel Company Project1 | 762742.21 | 418218.3524 | 0 | 755114.7524
Roof-Playa Cluster A,B,C | IPC04TR0088 | 4 | Roof-Playa Cluster A,B,C4 | 2177425 | 1819674.23 | 0 | 1819674.23
Residence 8 ( K10 ) | Inv ( 1 ) K 10 | 1 | Residence 8 ( K10 )1 | 802825 | 725753 | 0 | 725753
Tarek AbdelHakim Center - KSA | K0001 |  | Tarek AbdelHakim Center - KSA | 1799632.85 | 0 | 0 | 1862620
South Dabaa Axis | IPC#004 | 4 | South Dabaa Axis4 | 557198.4 | 493399.19 | 0 | 493399.19
Beymen Fit Out | Emaar Pkg#205 ipc6 | 6 | Beymen Fit Out6 | 494969.77 | 484105.18 | 0 | 484105.18
U3 & U5 | IPC19TR0055 | 19 | U3 & U519 | 100891.1 | 87129.54 | 0 | 87129.54
Creeks URBN-K | katamya Urbn-k ipc10 | 10 | Creeks URBN-K10 | 20145681.95 | 18357105.318 | 1729602.61 | 20086707.928
ZED Phase 2 | IPC07TR0062 | 7 | ZED Phase 27 | 72261.55 | 61385.8 | 0 | 61385.8
ElSewedy HQ Internal Finishing | HQ final ipc 26 | 26 | ElSewedy HQ Internal Finishing26 | 15848994.31 | 11230610.0055 | 0 | 23450753.0855
Port Said Port Silos | PORT SAID IPC25 | 25 | Port Said Port Silos25 | 4504741.9 | 3280047.566 | 450474.19 | 3730521.756
Air Defence College | IPC24TR0046 | 24 | Air Defence College24 | 33825.6 | 28717.93 | 0 | 28717.93
Katameya Creeks - RME | IPC17TR0053 | 17 | Katameya Creeks - RME17 | 137202.31 | 121492.64 | 0 | 121492.64
Kattameya Creeks | Katameya Creek ipc38 | 38 | Kattameya Creeks38 | 78865309.72 | 79235149.8888 | 2486946.22 | 81722096.1088
Koumassi Flyover | INV 4 | 4 | Koumassi Flyover4 | 161714858 | 145543371 | 0 | 145543371
Koumassi Flyover | INV 6 | 6 | Koumassi Flyover6 | 225560250 | 203004225 | 0 | 203004225
Irrigation Tank | IPC09TR0061 | 9 | Irrigation Tank9 | 1116341.1 | 964072.17 | 0 | 964072.17
U3 & U5 | IPC20TR0055 | 20 | U3 & U520 | 169727.9 | 146577.02 | 0 | 146577.02
Hosh Eisa Hospital | IPC01TR0086 | 1 | Hosh Eisa Hospital1 | 364500 | 312777.45 | 0 | 312777.45
EGAT Mechanical Installations | Eagt Mechnical ipc 5 | 5 | EGAT Mechanical Installations5 | 12224551.86 | 9289436.96 | 3056137.9746 | 12345574.9346
U4,U8 Seashell Playa | IPC13TR0060 | 13 | U4,U8 Seashell Playa13 | 147841.6 | 127676 | 0 | 127676
Port Said Grain Storage | Rent-003 | 3 | Port Said Grain Storage3 | 153350 | 141836.22 | 0 | 141836.22
Sokhna Port Expansion | Spx.2 (7) part2 | 7 | Sokhna Port Expansion7 | 1211958 | 1211958 | 0 | 1211958
HST Bridges-Sokhna & Mahager | Sokhna bri esc.20+21 |  | HST Bridges-Sokhna & Mahager | 4655327.38 | 3150292.95 | 0 | 3150292.95
Rabigh PP - Piling Works | Inv-03 | 3 | Rabigh PP - Piling Works3 | 840198 | 2898683.1 | 0 | 966227.7
Olympic MultiSport Hall | IPC05TR0079 | 5 | Olympic MultiSport Hall5 | 25760 | 21677.04 | 0 | 21677.04
Air Defence College | IPC25TR0046 | 25 | Air Defence College25 | 20217.6 | 17164.74 | 0 | 17164.74
SSC Suez Steel Company Project | Baraka Fance ipc 4 | 4 | SSC Suez Steel Company Project4 | 11760884 | 6072172.61 | 3528265.2 | 11547684.17
EDNC Retail - SEOUDI MODI | Ednc saudi ipc 1 | 1 | EDNC Retail - SEOUDI MODI1 | 1533908.63 | 622410.12 | 691590.61 | 1314000.73
Kattmeya Creeks Urban | IPC08TR0071 | 8 | Kattmeya Creeks Urban8 | 57380.28 | 50810.25 | 0 | 50810.25
MDF Factory | MDF Factory ipc 40 | 40 | MDF Factory40 | 759488.56 | 14022964.76 | 624505.64 | 14647470.4
Kattameya Creeks | katamya Creeks ipc42 | 42 | Kattameya Creeks42 | 52161798.49 | 52791233 | 1154383.5 | 53945616.5
Sokhna Port Expansion | Spx.1 esc.13:23 |  | Sokhna Port Expansion | 116453697 | 103409321 | 0 | 103409321
MDF Factory - Sadat | IPC03TR0093 | 3 | MDF Factory - Sadat3 | 200465.2 | 151770.12 | 0 | 151770.12
Roof-Playa Cluster A,B,C | IPC08TR0088 | 8 | Roof-Playa Cluster A,B,C8 | 153525 | 109906.58 | 0 | 109906.58
Open Chanel Epoxy | IPC01TR0101 | 1 | Open Chanel Epoxy1 | 470400 | 266016 | 0 | 266016
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC03 | 3 | ElSewedy HQ Internal Finishing3 | 12533035.14 | 8552112.06 | 3483377.1 | 12035489.16
Red Sea Museum-Bab El-Bunt | K0003 Inv 01 | 1 | Red Sea Museum-Bab El-Bunt1 | 2538014.97 | 8756151.66 | 0 | 2918717.22
R05 (New) | IPC10TR0059 | 10 | R05 (New)10 | 31236.6 | 33246.76 | 0 | 33246.76
Open Channal | IPC08TR0074 | 8 | Open Channal8 | 118939.8 | 102597.47 | 0 | 102597.47
Koumassi Flyover | INV no.10 | 10 | Koumassi Flyover10 | 326864217.55 | 294177795.8 | 0 | 294177795.8
WADY EL-NATROUN BRIDGE(HST) | IPC no14 |  | WADY EL-NATROUN BRIDGE(HST) | 937184.63 | 838200.28 | 0 | 838200.28
Wadi El Natroun Bridge | inv ( 2 ) W. Natron | 2 | Wadi El Natroun Bridge2 | 1931400 | 55379.88 | 0 | 55379.88
Seashell Playa 5 Villas | Playa C470- ipc 7 | 7 | Seashell Playa 5 Villas7 | 99466.1 | 85898.91 | 0 | 85898.91
Capital One | inv (13 ) Captal one | 13 | Capital One13 | 678083.6 | 108089.995 | 0 | 108089.995
Faculty of Medicine | mansora finish ipc27 | 27 | Faculty of Medicine27 | 30831221.9 | 13404311 | 4624683.29 | 18028994.29
FX-05-22 Close compound | 102 |  | FX-05-22 Close compound | 71615.63 | 0 | 0 | #DIV/0!
Suez Gulf Substation | Forex |  | Suez Gulf Substation | 0.1 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 180068 |  | Beni-Suef Power Plant EPC | -202616757 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 16 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 430785.67 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 4 |  | Zafranaa - Ras Ghareb | 21538.63 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR-(7/8/12)EGP-Domia | 7 | W Dam PP Phase II (CP-117)7 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | Al-Lahoon Sub Inv +1 | 1 | Lahoon 220/22/221 | 522647.98 | 0 | 0 | #DIV/0!
Closed | CR(3_p.o52/156 |  | Closed | 0 | 0 | 0 | #DIV/0!
New Capital | Cr,Inv.7 | 7 | New Capital7 | 0 | 0 | 0 | #DIV/0!
Canal Sugar OHTL | تشيد سكر خط 220 |  | Canal Sugar OHTL | 5000 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | Cr. Adj Inv. 13 | 13 | Zafranaa - Beni Suef13 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Inv other ded. |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Open Channal | CAN.CR |  | Open Channal | 0 | 0 | 0 | #DIV/0!
Celia | CR-IPC#3 | 3 | Celia3 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 2 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 35142.34 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Rev (9 USD Shabab) |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Gabal Elgalalaa | Ret.OB Galalah |  | Gabal Elgalalaa | 1213769.83 | 0 | 0 | #DIV/0!
Containment Data Center- | 34 |  | Containment Data Center- | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10168 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
EGYTEC A1,A3 ( LP-05-21) | 59 |  | EGYTEC A1,A3 ( LP-05-21) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 272 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 6 | 6 | Marsa Alam/ Bernes LOT2 OHTL6 | 24428.57 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | Al-Lahoon Sub Inv +3 | 3 | Lahoon 220/22/223 | 1843216.21 | 0 | 0 | #DIV/0!
Maspiro Towers | D0019-OB-Dec-2020/Cr | 2020 | Maspiro Towers2020 | 0 | 0 | 0 | #DIV/0!
Central Capital | INV ( 6 ) Central Ca | 6 | Central Capital6 | 16380 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 8 EGP- Suez Gulf |  | Suez Gulf Substation | 2957422.0857 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 15 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 16158.31 | 0 | 0 | #DIV/0!
Mivida | IPC_7_Mivida |  | Mivida | 118510 | 0 | 0 | #DIV/0!
Ain Sokhna Port Development | ipc 23+24 elsokhna | 23 | Ain Sokhna Port Development23 | 925596 | 0 | 0 | #DIV/0!
Wadi Halfa Port | cr-wad halfa ipc05 | 5 | Wadi Halfa Port5 | 0 | 0 | 0 | #DIV/0!
West Port Said 220 kV GIS | P-45-EGY اتحاد تشيد | 45 | West Port Said 220 kV GIS45 | 5000 | 0 | 0 | #DIV/0!
ElMarg | D0043-OB-Dec-2020/Cr | 2020 | ElMarg2020 | 0 | 0 | 0 | #DIV/0!
ORA ZED - Ph 01B - Pkgs A&D | cr-ORA PH.1-IPC23 | 23 | ORA ZED - Ph 01B - Pkgs A&D23 | 0 | 0 | 0 | #DIV/0!
HSR | cancelHSR oct-5 | 5 | HSR5 | 0 | 0 | 0 | #DIV/0!
Ministry Building EPOXY | CR.TR0018CLOSING.DEC |  | Ministry Building EPOXY | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR 9 EGP-South Helw |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 44 |  | Suez Gulf Substation | 666000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 246 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Club House-Sodic Wesset | CR.TR0019CLOSING.DEC |  | Club House-Sodic Wesset | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | Refu.retention |  | Pyramids Industrial Park | 2262130.78 | 0 | 0 | #DIV/0!
ORA-ZED Towers01B | CR.IPC_4_ORA |  | ORA-ZED Towers01B | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-Kafr ShokrIPC01 | 1 | Kafr Shokr Bridge1 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11451 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
Giza North PP Ph I,II (CP-117) | CR-36 EGP-GizaN.I&II | 36 | Giza North PP Ph I,II (CP-117)36 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Trans.usd toegp |  | Abo Quir - Badr 500KV | 233093.09 | 0 | 0 | #DIV/0!
Air Defence College | IPC26TR0046.. | 26 | Air Defence College26 | 135222.68 | 0 | 0 | #DIV/0!
Damac 2x60/22 KV S/S | 8 |  | Damac 2x60/22 KV S/S | 1280709.49 | 0 | 0 | #DIV/0!
Borg El Arab Bridge - Km 21 | IPC#4#Kilo 21 | 4 | Borg El Arab Bridge - Km 214 | 122668.6 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Soci.1 To12 Mousa358 |  | Beni Seuf - 358 | 8174127 | 0 | 0 | #DIV/0!
October Under-Railway Tunnel | cr-oct.tunnel ipc2 | 2 | October Under-Railway Tunnel2 | 0 | 0 | 0 | #DIV/0!
Port Said | Cr. Adj Inv. 17 | 17 | Port Said17 | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | cr.egy ex awnash 2fi |  | Egyptian Exchange Building | 0 | 0 | 0 | #DIV/0!
Infra Project 2524 | 220222001 |  | Infra Project 2524 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr.So12-16 assui | 16 | Akhmem Assiut16 | 0 | 0 | 0 | #DIV/0!
Zayed Monorail 66/22 KV GIS | Zayed Monorail Inv.1 | 1 | Zayed Monorail 66/22 KV GIS1 | 7123937.84 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 227 |  | MAYSAN 400/132kV SS | 0 | 0 | 0 | #DIV/0!
October Dry Port | P-32-EGY اتحاد تشيد | 32 | October Dry Port32 | 5000 | 0 | 0 | #DIV/0!
SHAT Al ARAB 400/132kV SS | 208 |  | SHAT Al ARAB 400/132kV SS | -4240533.36 | 0 | 0 | #DIV/0!
Ameria | D0030-OB-Dec-2020/Cr | 2020 | Ameria2020 | 0 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | Invoice 23 (10) | 23 | Barwa 2x60/22 KV S/S23 | 0 | 0 | 0 | #DIV/0!
WPS Substation 3 | P-11-EGY اتحاد تشيد | 11 | WPS Substation 311 | 5000 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | CR_80 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
ORA ZED-Ph 2-Pkgs A&D | Cr Ora ph1 ipc(22) | 22 | ORA ZED-Ph 2-Pkgs A&D22 | 0 | 0 | 0 | #DIV/0!
LP-17-21 ODP-Computing | 92 |  | LP-17-21 ODP-Computing | 211225.15 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 53 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 7 EGP-(VO) adjust. |  | Suez Gulf Substation | 20565.0776 | 0 | 0 | #DIV/0!
Hosh Essa 220 KV OHTL | Hosh Essa USD Inv.02 | 2 | Hosh Essa 220 KV OHTL2 | 13116.19 | 0 | 0 | #DIV/0!
Cameron EDC | 024/2020cncl |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 180033 |  | Al-Shabab PP Phase II (CP-117) | -2073161.5524 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | CR_Inv 81 | 81 | Abou El Matameer and Sammanoud81 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | Inv.52 Qena Akhmem | 52 | Akhmem - Qena52 | 688.6 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 20 EGP - Shabab | 20 | Al-Shabab PP Phase II (CP-117)20 | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 87 |  | Governmental Campus-N2 | 234313 | 0 | 0 | #DIV/0!
Expansion of Ring Road-CFA | inv no2.2 d0079 | 2 | Expansion of Ring Road-CFA2 | 58014 | 0 | 0 | #DIV/0!
EPICO 3 Facility | cr material on site |  | EPICO 3 Facility | 0 | 0 | 0 | #DIV/0!
Abas El Akkad Bridge | D0035-OB-Dec-2020/Cr | 2020 | Abas El Akkad Bridge2020 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Close Zaafarana |  | Zafranaa - Ras Ghareb | 8035.51 | 0 | 0 | #DIV/0!
EGYTEC A1,A3 ( LP-05-21) | 51 |  | EGYTEC A1,A3 ( LP-05-21) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2008210002 |  | Miscellaneous Projects | 815592 | 0 | 0 | #DIV/0!
Akhmem - Qena | Ref.soci 51-52 Quna | 52 | Akhmem - Qena52 | 83237 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | 9/2 |  | Pyramids Industrial Park | 551706.16 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 91 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
EMAAR-PKG#107-MARASSI | cr VAT 2 PKG107 |  | EMAAR-PKG#107-MARASSI | 0 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 19 | 19 | Suez Gulf/S4 - 500KV OHTL19 | 194271.05 | 0 | 0 | #DIV/0!
New Giza 2 | OB-RE-New Giza 2 |  | New Giza 2 | 5444916.45 | 0 | 0 | #DIV/0!
MDF Factory | cr-mdfipc07 | 7 | MDF Factory7 | 0 | 0 | 0 | #DIV/0!
El Katameya Mall | CRINV(14) 28-10-20 | 14 | El Katameya Mall14 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.5 | 5 | Akhmem - Qena5 | 0 | 0 | 0 | #DIV/0!
Ring Road Bridges Project | INV ( 10 ) Ring R | 10 | Ring Road Bridges Project10 | 6900702 | 0 | 0 | #DIV/0!
Al-Wukair 11 Substation | Cr.Memo-Expenses |  | Al-Wukair 11 Substation | 0 | 0 | 0 | #DIV/0!
Racecores 3092-15 132KV A | 11452 |  | Racecores 3092-15 132KV A | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | CR.Ret Zafra-B-Suef |  | Zafranaa - Beni Suef | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11582 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange building | IPC00000010 | 10 | Egyptian Exchange building10 | 0 | 0 | 0 | #DIV/0!
Ghana | Cr.P 161 |  | Ghana | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180019 |  | Suez Gulf Substation | 336730.54 | 0 | 0 | #DIV/0!
JICA lot 02 | JICA lot 02 Inv.$ 02 |  | JICA lot 02 | 5909653.38 | 0 | 0 | #DIV/0!
British International School | cr-Bis ipc (2) | 2 | British International School2 | 0 | 0 | 0 | #DIV/0!
EGAT Injection | IPC17TR0048 | 17 | EGAT Injection17 | 52956 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cancle13-12-2018 | 12 | Abou El Matameer and Sammanoud12 | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 89 |  | Governmental Campus-N2 | 248466 | 0 | 0 | #DIV/0!
Benban 500 K.V / 100 K.M | تشيد بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 5000 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv-02 | 2 | MOC HQ at Diriyah2 | 2521761.64 | 0 | 0 | #DIV/0!
LP-19-21 N2 Extension | 99 |  | LP-19-21 N2 Extension | 3282236 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2007220004 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 57 |  | Al-Shabab PP Phase II (CP-117) | 2530842.34 | 0 | 0 | #DIV/0!
Ethiopia S/S | CR.P-27-09 AccRev | 27 | Ethiopia S/S27 | 0 | 0 | 0 | #DIV/0!
Bahr El Baqar Treatment Plant | D0036-OB-Dec-2020/Cr | 2020 | Bahr El Baqar Treatment Plant2020 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 41 |  | Suez Gulf Substation | 2886000 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Cr. Adj Inv 14 | 14 | Siemens 6x500/220 KV GIS-MOU14 | 0 | 0 | 0 | #DIV/0!
Dubai Port | CR.TR0005CLOSING.DEC |  | Dubai Port | 0 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 486 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180076 |  | Suez Gulf Substation | 3536.21 | 0 | 0 | #DIV/0!
New Heliopolis | Cr.Inv. 11 Heliopols | 11 | New Heliopolis11 | 0 | 0 | 0 | #DIV/0!
Air Force Project | P-12-EGY اتحاد تشيد | 12 | Air Force Project12 | 5000 | 0 | 0 | #DIV/0!
Ain-Sokhna PP (CP-117) | 2104220003 |  | Ain-Sokhna PP (CP-117) | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 256 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 61 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Closed | OB-ST-EL WAHAT |  | Closed | 2320.56 | 0 | 0 | #DIV/0!
Ring Road El Monib | inv ( 1 ) R.EL Monib | 1 | Ring Road El Monib1 | 1781000 | 0 | 0 | #DIV/0!
Port Said Grain Storage | rent-005 | 5 | Port Said Grain Storage5 | 144600 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 8 Euro-South Helwan |  | South Helwan PP (CP-117) | 257510.019 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2004220005 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR-18 EGP-West Domia | 18 | W Dam PP Phase II (CP-117)18 | 0 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | CR#10 WADY |  | WADY EL-NATROUN BRIDGE(HST) | -1255380 | 0 | 0 | #DIV/0!
Ahl Misr P3 – Zamalek Sector | CR-IPC#6 | 6 | Ahl Misr P3 – Zamalek Sector6 | 0 | 0 | 0 | #DIV/0!
Fish Market | CM SOUQ-SAMAK-IPC01 | 1 | Fish Market1 | -1763430.4 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 2004210014 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Club House-Sodic Wesset | 10073 |  | Club House-Sodic Wesset | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 88 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
6 Octobar Stores | IPC02TR0072 | 2 | 6 Octobar Stores2 | 70056 | 0 | 0 | #DIV/0!
FX-03-22 Urban Communities-WD | 98 |  | FX-03-22 Urban Communities-WD | 231883.8 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/004/adjCnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
Pridge 5 | CR/INV1 PRIDE 5 | 1 | Pridge 51 | 0 | 0 | 0 | #DIV/0!
Air Defence College | cancel TR46 IPC 11 | 11 | Air Defence College11 | 0 | 0 | 0 | #DIV/0!
ITS | Cr.Adv. ITS Inv. 01 | 1 | ITS1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 19 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 2580132 | 0 | 0 | #DIV/0!
Ministries A13-A14 | CR IPC_3_RedSea |  | Ministries A13-A14 | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Soc Abo.matmr labour |  | Abou El Matameer and Sammanoud | 397908 | 0 | 0 | #DIV/0!
UIC Project (LP-04-21) | 57 |  | UIC Project (LP-04-21) | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | D0007-OB-Dec-2020/Cr | 2020 | El Boghaz Brigde2020 | 0 | 0 | 0 | #DIV/0!
EMAAR-PKG#53-UPTOWN | CR-PKG#85/53 |  | EMAAR-PKG#53-UPTOWN | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | CR.Ma Alam Equ Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 11 EGP - Shabab | 11 | Al-Shabab PP Phase II (CP-117)11 | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-Tarekabdelhakim 1 |  | Tarek Abdel-Hakim Center | 0 | 0 | 0 | #DIV/0!
Residence 8 ( K10 ) | Inv ( 2 ) K 10 | 2 | Residence 8 ( K10 )2 | 125124.61 | 0 | 0 | 125124.61
Residence 8 ( S09 ) | Inv ( 1 ) S 09 | 1 | Residence 8 ( S09 )1 | 52676.63 | 0 | 0 | 52676.63
Tarek Abdel-Hakim Center | TAH ipc06 | 6 | Tarek Abdel-Hakim Center6 | 1234570.04 | 0 | 0 | 1234570.04
Tarek Abdel-Hakim Center | TAH ipc07 | 7 | Tarek Abdel-Hakim Center7 | 2195644.04 | 0 | 0 | 2195644.04
Tarek Abdel-Hakim Center | Tarek abdelhakim 01 |  | Tarek Abdel-Hakim Center | 1021554.87 | 0 | 0 | 1021554.87
Waldorf Astoria Cairo | Waldorf astoripc(19) | 19 | Waldorf Astoria Cairo19 | 12873774.16 | 0 | 0 | 13517462.868
El Katameya Mall | inv ( 13 )10-2020 | 13 | El Katameya Mall13 | 44072 | 0 | 0 | 44072
Ora Zed Landscape Ph1 | ora Landscape ipc 2 | 2 | Ora Zed Landscape Ph12 | 2071866.5 | 0 | 0 | 2175459.825
Cairo-Alex Railway | cairo alex ipc41 | 41 | Cairo-Alex Railway41 | 6779667 | 0 | 0 | 7118650.35
U3 & U5 | TR55/IPC/01 |  | U3 & U5 | 741275.46 | 0 | 0 | 741275.46
Port Said Port Silos | port said 1-supply |  | Port Said Port Silos | 673851.6 | 0 | 0 | 768190.824
October Under-Railway Tunnel | OCTOBER TUNNELIPC2 | 2 | October Under-Railway Tunnel2 | 4380339.19 | 0 | 0 | 4599356.1495
184E Substation | 11763 |  | 184E Substation | 155857.75 | 0 | 0 | 160157.75
Infra Project 2524 | 220621003 |  | Infra Project 2524 | 81703008.09 | 0 | 0 | 85788158.4945
Port Said Grain Storage | IPC#1 Port Saeid | 1 | Port Said Grain Storage1 | 1709400 | 0 | 0 | 1709400
Assuit PP (CP-118) | 220621001 |  | Assuit PP (CP-118) | 2850495.23 | 0 | 0 | 2993019.99
Ameria | FPC - Ameryia |  | Ameria | 120000 | 0 | 0 | 120000
Racecores 3092-17 132KV E | 11498 |  | Racecores 3092-17 132KV E | 11778.21 | 0 | 0 | 12109.4765
Nuweibaa (Swro) | 220321004 |  | Nuweibaa (Swro) | 308452.2 | 0 | 0 | 308452.2
Akhmem Assiut | Ref. Akhmem Asuit3T |  | Akhmem Assiut | 5000000 | 0 | 0 | 5000000
Ahl Misr P3 – Zamalek Sector | IPC#5&6 | 5 | Ahl Misr P3 – Zamalek Sector5 | 425700 | 0 | 0 | 425700
Ahl Misr P3 – Zamalek Sector | IPC#6 - Zamalek | 6 | Ahl Misr P3 – Zamalek Sector6 | 231900 | 0 | 0 | 231900
Miscellaneous Projects | 2102210004 |  | Miscellaneous Projects | 239998.68 | 479997.36 | 0 | 239998.68
AWEER POWER STATION 'H' Phase | ENG/040 |  | AWEER POWER STATION 'H' Phase | 371821.23 | 371821.23 | 0 | 389527
ORA-ZED Towers01B | IPC_4_Rowad_Ora |  | ORA-ZED Towers01B | 132779.22 | 0 | 0 | 132779.22
Abas El Akkad Bridge | D0035-OB-Dec-2020 | 2020 | Abas El Akkad Bridge2020 | 1393425 | 0 | 0 | 1393425
El-Herafeen brigde | D0042-OB-Dec-2020 | 2020 | El-Herafeen brigde2020 | 1263235 | 0 | 0 | 1263235
Sodic East | 10043 |  | Sodic East | 180185.97 | 0 | 0 | 180185.97
Ain-Sokhna PP (CP-117) | adj. rec 180137- |  | Ain-Sokhna PP (CP-117) | 28251.08 | 28251.08 | 0 | 28251.08
El Mostakbal City Project | Clo.مد وثيقة التامين |  | El Mostakbal City Project | 279055 | 0 | 0 | 279055
Benban 500 K.V/95 K.M | تشيد بنبان لوط 2 |  | Benban 500 K.V/95 K.M | 5000 | 0 | 0 | 5000
Cameron EDC | 022/2020 |  | Cameron EDC | 148684449.87 | 0 | 0 | 148684449.87
LAYYAH CCPP | MP-09 | 9 | LAYYAH CCPP9 | 8569800 | 0 | 0 | 8569800
AWEER POWER STATION 'H' Phase | 5001/12 |  | AWEER POWER STATION 'H' Phase | 13096334.05 | 13096334.05 | 0 | 13096334.05
Suez Gulf Substation | 1909210012 |  | Suez Gulf Substation | 499195.28 | 499195.28 | 0 | 499195.28
Suez Gulf Substation | 1909210004 |  | Suez Gulf Substation | 26812 | 26812 | 0 | 26812
Beni-Suef Power Plant EPC | Adj inv.180132 | 180132 | Beni-Suef Power Plant EPC180132 | 283799492.53 | 283799492.53 | 0 | 283799492.53
DPW Onshore Port & Terminal | DP WORLD-IPC06 | 6 | DPW Onshore Port & Terminal6 | 66782711.19 | 0 | 0 | 66782711.19
Beni-Suef Power Plant EPC | Inv. 17 EGP | 17 | Beni-Suef Power Plant EPC17 | 24516559.48 | 24516559.48 | 0 | 24516559.48
Mozambique TL | P-50-12 AccRev | 50 | Mozambique TL50 | 4823630 | 0 | 0 | 4823630
Zambia | P-2-10 AccRev | 2 | Zambia2 | 146431587 | 0 | 0 | 146431587
Abu Qir PP (CP-117) | 180152 |  | Abu Qir PP (CP-117) | 4019577.17 | 4019577.17 | 0 | 4019577.17
Kuwait | P-10-14 ADJ | 10 | Kuwait10 | 10946097.72 | 0 | 0 | 10946097.72
Ghana | P 161 ADJ |  | Ghana | 86324678.53 | 0 | 0 | 86324678.53
Suez Gulf Substation | 180078 |  | Suez Gulf Substation | 294832.33 | 279140.63 | 31015.63 | 310156.26
Suez Gulf Substation | 180061 |  | Suez Gulf Substation | 410529.35 | 388679.97 | 43186.66 | 431866.63
W Dam PP Phase II (CP-117) | 10 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 93003.52 | 93003.52 | 0 | 93003.52
Zafranaa - Ras Ghareb | In.1-14/2-14/3-12gha | 14 | Zafranaa - Ras Ghareb14 | 639342.58 | 0 | 0 | 3387.56
Barwa and Damac 220 OHTL | Adj Inv 3 | 3 | Barwa and Damac 220 OHTL3 | 9000846.43 | 0 | 0 | 9000846.43
PIP West 2 | Adj Inv 2 | 2 | PIP West 22 | 21544102.56 | 0 | 0 | 21544102.56
Beni-Suef Power Plant EPC | 180069 |  | Beni-Suef Power Plant EPC | 71416141.32 | 0 | 0 | 71416141.32
Apache Electrical Works | 5 |  | Apache Electrical Works | 76066343 | 0 | 0 | 76066343
Tebbin PP Rehabitation(CP-124) | 13 |  | Tebbin PP Rehabitation(CP-124) | 12876077 | 0 | 0 | 12876077
Suez IPB | 122 |  | Suez IPB | 6959007.1398 | 0 | 0 | 6959007.1398
W Dam PP Phase II (CP-117) | 180044 |  | W Dam PP Phase II (CP-117) | 10445.3048 | 0 | 0 | 10967.57
Abu Qir PP (CP-118) | 31 |  | Abu Qir PP (CP-118) | 420405.0921 | 0 | 0 | 420405.0921
Tebbin PP Rehabitation (CP106) | 82 |  | Tebbin PP Rehabitation (CP106) | 125133.41 | 0 | 0 | 125133.41
Al-Wukair 11 Substation | 77 |  | Al-Wukair 11 Substation | 276134509.4865 | 0 | 0 | 276134509.4865
W Dam PP Phase II (CP-117) | 180036 |  | W Dam PP Phase II (CP-117) | 47134.4857 | 0 | 0 | 49491.21
IRAQ - Substations Soil Invest | 37 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
Giza North PP Ph I,II (CP-117) | 4 |  | Giza North PP Ph I,II (CP-117) | 43917116 | 0 | 0 | 43917116
Giza North PP Phase3(CP-117) | 7 |  | Giza North PP Phase3(CP-117) | 29807353.76 | 0 | 0 | 29807353.76
Giza North PP Phase3(CP-117) | 84 |  | Giza North PP Phase3(CP-117) | -24375617.1533 | 0 | 0 | -24375617.1533
6th Oct. Ph2 PP-Elect Work | 9 |  | 6th Oct. Ph2 PP-Elect Work | 11271114 | 0 | 0 | 11271114
Giza North PP Ph I,II (CP-117) | DR - VAT - Egytech |  | Giza North PP Ph I,II (CP-117) | 345309.59 | 345309.59 | 0 | 345309.59
W Dam PP Phase II (CP-117) | 35 |  | W Dam PP Phase II (CP-117) | 35639.52 | 0 | 0 | 35639.52
New Heliopolis | Inv.7 Heliopolis | 7 | New Heliopolis7 | 3631713.98 | 0 | 0 | 3631713.98
Abou El Matameer and Sammanoud | Inv 80 P4 Sammound | 80 | Abou El Matameer and Sammanoud80 | 5875862.86 | 0 | 0 | 5875862.86
Akhmem - Qena | Inv.12 Akhmem Qena | 12 | Akhmem - Qena12 | 26867410.18 | 0 | 0 | 26867410.18
Akhmem - Qena | Inv.11 Akhmem Qena | 11 | Akhmem - Qena11 | 31190172.66 | 0 | 0 | 31190172.66
Akhmem - Qena | Inv.10 Akhmem Qena | 10 | Akhmem - Qena10 | 14206943.63 | 0 | 0 | 14206943.63
Akhmem - Qena | Inv. 8 Akhmem Qena | 8 | Akhmem - Qena8 | 893041.7 | 0 | 0 | 893041.7
Akhmem - Qena | Inv. 5 Akhmem Qena | 5 | Akhmem - Qena5 | 69969724.95 | 0 | 0 | 69969724.95
Beni-Suef Power Plant EPC | Dr on Sewedy Holding |  | Beni-Suef Power Plant EPC | 232187 | 232187 | 0 | 232187
Barwa 2x60/22 KV S/S | 2 |  | Barwa 2x60/22 KV S/S | 1000 | 0 | 0 | 1000
Kayan 3 New Cairo Capital City | OB-SI-EL Kayaan |  | Kayan 3 New Cairo Capital City | 132593.05 | 0 | 0 | 132593.05
IRAQ - Al-Diwaniya Power Plant | 65 USD - Diwaniya |  | IRAQ - Al-Diwaniya Power Plant | 1178165.5524 | 0 | 0 | 1237073.83
Palm Hill-Infra Str(Elec.Work) | 7 EGP - palm hills |  | Palm Hill-Infra Str(Elec.Work) | 699577.96 | 0 | 0 | 769535.756
Suez Gulf Substation | 2 USD/123/2011/2012 |  | Suez Gulf Substation | 321146.2451 | 0 | 0 | 325000
Cameron EDC | 028/2020 FCV |  | Cameron EDC | 175964727.63 | 87982363.81 | 0 | 87982363.81
W Dam PP Phase II (CP-117) | 180041 |  | W Dam PP Phase II (CP-117) | 212073.6762 | 0 | 0 | 222677.36
Al-Shabab PP Phase II (CP-117) | 180028 |  | Al-Shabab PP Phase II (CP-117) | 25777.9143 | 0 | 0 | 27066.81
Al-Shabab PP Phase II (CP-117) | 19 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2580132 | 0 | 406370.79 | 406370.79
W Dam PP Phase II (CP-117) | 15 EGP -West D. 117 |  | W Dam PP Phase II (CP-117) | 252473.1714 | 0 | 39764.52 | 39764.52
W Dam PP Phase II (CP-117) | 2 EGP - West.D 117 |  | W Dam PP Phase II (CP-117) | 41431.67 | 35639.52 | 6289.33 | 41928.85
W Dam PP Phase II (CP-117) | 3 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 1814725.2767 | 0 | 275475.3 | 1836501.98
Suez Gulf Substation | 6 USD/123/2011/2012 |  | Suez Gulf Substation | 371737.6 | 0 | 0 | 371737.6
Abo Quir - Badr 500KV | Inv 74 Abu Quir Badr | 74 | Abo Quir - Badr 500KV74 | 1639063.13 | 0 | 327812.63 | 327812.63
Damac 2x60/22 KV S/S | Damac 14 |  | Damac 2x60/22 KV S/S | 2415534.88 | 1708800.38 | 362330.25 | 2071130.63
South Helwan PP (CP-117) | 2 Euro- South Helwan |  | South Helwan PP (CP-117) | 55261.12 | 58024.176 | 0 | 58024.176
Beni Suef Substation R61 | BSF-SD-EUR-02 | 2 | Beni Suef Substation R612 | 650978.28 | 538871.07 | 97646.74 | 636517.81
Al Mostathmreen GIS Substation | MOS-SD-EGP-22 | 22 | Al Mostathmreen GIS Substation22 | 1745640 | 1300501.8 | 261846 | 1562347.8
Tamey El-amdeed Substation | TAM-SW-EGP-01 | 1 | Tamey El-amdeed Substation1 | 634375 | 472609.37 | 95156.25 | 567765.62
Tamey El-amdeed Substation | (3)cw almansora | 3 | Tamey El-amdeed Substation3 | 3819167.14 | 2844752.9 | 572875.07 | 3417627.97
Al Mostathmreen GIS Substation | 7sd euro mosstasmree |  | Al Mostathmreen GIS Substation | 1114848 | 808264.12 | 167227.3 | 975491.42
Beni Seuf - 358 | Inv. 16 Oewon Mousa | 16 | Beni Seuf - 35816 | 5877613.75 | 0 | 1010855.15 | 1010855.15
Beni Seuf - 358 | Inv. 7 Oewon Mousa | 7 | Beni Seuf - 3587 | 3768028.61 | 2603908.97 | 636595.64 | 3240504.61
New Giza 2 | OB-ST-New Giza 2 |  | New Giza 2 | 115829.98 | 115829.98 | 0 | 115829.98
Giza North PP Ph I,II (CP-117) | 40 EGP-Giza N. I&II |  | Giza North PP Ph I,II (CP-117) | 28871.3333 | 30314.9 | 0 | 30314.9
EMAAR-PKG#53-UPTOWN | OB-ST- PKG#53 |  | EMAAR-PKG#53-UPTOWN | 308431.19 | 308431.19 | 0 | 308431.19
PIP Zona 2 | Inv. 3 Zona 2 | 3 | PIP Zona 23 | 3505222.55 | 3294909.1975 | 0 | 3294909.1975
Borolos Over Head | Balance |  | Borolos Over Head | 2100000 | 1870602.15 | 0 | 1970602.15
Suez Gulf Substation | Colle Suez Gul 34567 |  | Suez Gulf Substation | 7191000 | 7191000 | 0 | 7191000
Beni Suef COMCAVI | Inv 7 Comcavi | 7 | Beni Suef COMCAVI7 | 2036941.11 | 2036941.11 | 0 | 2036941.11
Apache Electrical Works | Apachi Inv No PC.#19 |  | Apache Electrical Works | 39634.79 | 39634.79 | 0 | 39634.79
Kayan 3 New Cairo Capital City | EL KAYAN MEP- IPC 3 | 3 | Kayan 3 New Cairo Capital City3 | 76333661 | 66272397.35 | 3000000 | 69272397.35
EMAAR-PKG#53-UPTOWN | OB-RE-PKG#53 |  | EMAAR-PKG#53-UPTOWN | 6555257.77 | 0 | 0 | 0
Al Mostathmreen GIS Substation | (10) CW | 10 | Al Mostathmreen GIS Substation10 | 670146 | 499258.57 | 100522.02 | 599780.59
W Dam PP Phase II (CP-117) | 8 USD- West Domiat |  | W Dam PP Phase II (CP-117) | 593704.09 | 593704.09 | 0 | 593704.09
Kuwait | 2-132KVA-J | 132 | Kuwait132 | 54755.32 | 41066.49 | 0 | 41066.49
Royal City | (3)royal city | 3 | Royal City3 | 7725328 | 7924629.02 | 1500964.3 | 9425593.32
Cairo South PP Rehabilitation | 9 USD - Cairo South |  | Cairo South PP Rehabilitation | 27162.77 | 27162.77 | 0 | 27162.77
Ghana | 37/P/10/ER/2017/USD |  | Ghana | 59795.74 | 59781.25 | 0 | 59781.25
Siemens 6x500/220 KV GIS-MOU | Inv 84 P13 Assuit | 84 | Siemens 6x500/220 KV GIS-MOU84 | 1473372.7 | 1056015.33 | 221005.91 | 1277021.24
Abou El Matameer and Sammanoud | Inv 73 P3Abo Matamir | 73 | Abou El Matameer and Sammanoud73 | 9985043.36 | 7223180.36 | 1497756.5 | 8720936.86
Badr | Inv. 23 Badr | 23 | Badr23 | 4554739.85 | 3381482.8 | 683211 | 4064693.8
Badr | Inv. 5 Badr | 5 | Badr5 | 7202522.86 | 5347452.7 | 1080378.45 | 6427831.15
Siemens 6x500/220 KV GIS-MOU | Soci. 72Asuit 10 |  | Siemens 6x500/220 KV GIS-MOU | 115457.3 | 115457.3 | 0 | 115457.3
Suez Gulf Substation | Inv 3 EGP VO SG | 3 | Suez Gulf Substation3 | 993961.3619 | 939293.49 | 104365.94 | 1043659.43
Kayan 3 New Cairo Capital City | (2)elkayan fainshing | 2 | Kayan 3 New Cairo Capital City2 | 26989555 | 11242619.75 | 13250000 | 24492619.75
Al Mostathmreen GIS Substation | (32)sd elmostsmrin | 32 | Al Mostathmreen GIS Substation32 | 139309 | 108531.2 | 20896.35 | 129427.55
New Heliopolis | ref.siite electricit |  | New Heliopolis | 2000 | 1998.79 | 0 | 1998.79
Akhmem - Qena | Soci. 1&2 Qina Akhme |  | Akhmem - Qena | 3994754.86 | 3994754.86 | 0 | 3994754.86
Assuit PP (CP-118) | 2110210005 |  | Assuit PP (CP-118) | 463083.99 | 486238.19 | 0 | 486238.19
Assuit PP (CP-118) | 2101210002 |  | Assuit PP (CP-118) | 70200.44 | 62653.89 | 11056.57 | 73710.46
Assuit PP (CP-118) | 1906210014 |  | Assuit PP (CP-118) | 108568.3 | 96897.21 | 17099.51 | 113996.72
Assuit PP (CP-118) | 2002210015 |  | Assuit PP (CP-118) | 2116105.4 | 1867463.02 | 333286.6 | 2200749.62
Assuit PP (CP-118) | 520 |  | Assuit PP (CP-118) | 2559390.19 | 2258661.85 | 403103.95 | 2661765.8
Assuit PP (CP-118) | 1907210001 |  | Assuit PP (CP-118) | 269254.5 | 240309.65 | 42407.58 | 282717.23
Assuit PP (CP-118) | 180165 |  | Assuit PP (CP-118) | 163099.07 | 145565.92 | 25688.1 | 171254.02
South Helwan PP (CP-117) | Dr-Memo_Inv#19-EGP02 | 19 | South Helwan PP (CP-117)19 | 23885.1 | 23885.1 | 0 | 23885.1
Marsa Matrouh 500KV | Inv.32 Borg Alarab | 32 | Marsa Matrouh 500KV32 | 95611.43 | 83516.09 | 10039.2 | 93555.29
Akhmem Assiut | Ref.Social.4/5 Assui |  | Akhmem Assiut | 2999691.3 | 2999691.3 | 0 | 2999691.3
Abou El Matameer and Sammanoud | Inv 77 P5Abo Matamir | 77 | Abou El Matameer and Sammanoud77 | 6735132.2 | 4872194.63 | 1010269.83 | 5882464.46
kayan wall lock & Load | (1)elkayan lock+load | 1 | kayan wall lock & Load1 | 21438000 | 18666574.1 | 0 | 18666574.1
Military 110 Kayan Project | Elkayan Inv.12 | 12 | Military 110 Kayan Project12 | 8621922.75 | 7462365.75 | 0 | 7462365.75
Apache Electrical Works | ApatchiInv No P.C#16 |  | Apache Electrical Works | 281018.5 | 281018.5 | 0 | 281018.5
Lina Farm Substation | Ret. Balance |  | Lina Farm Substation | 66596.54 | 66596.54 | 0 | 66596.54
Akhmem Assiut | Inv.2 Assuit Akhmem$ | 2 | Akhmem Assiut2 | 1023877.33 | 865978.87 | 0 | 865978.87
Military 110 Kayan Project | Elkayan Inv.13 | 13 | Military 110 Kayan Project13 | 11919021.38 | 10816106.25 | 0 | 10816106.25
Akhmem Assiut | Inv.9 Assuit Akhmem$ | 9 | Akhmem Assiut9 | 1110147.4 | 937877.35 | 0 | 937877.35
NUCA R05 - Z02 | R5-ZONE2- IPC7 | 7 | NUCA R05 - Z027 | 32455409 | 25485572.57 | 3181003.7 | 28666576.27
New Capital Tunnels | IPC3-M.ZAYD TUNNLE | 3 | New Capital Tunnels3 | 39415048.58 | 18748.3 | 0 | 35368748.3
Akhmem - Qena | Ref.InstilNo.1 Qena |  | Akhmem - Qena | 50866194.1 | 50866194.1 | 0 | 50866194.1
El-Nyaba El-Ama | El-Nayba Inv. 3 | 3 | El-Nyaba El-Ama3 | 3364450.65 | 2750033.55 | 252333.8 | 3002367.35
Marsa Matrouh 500KV | Inv.2 Borg Alarab | 2 | Marsa Matrouh 500KV2 | 65050776.78 | 65050776.78 | 0 | 65050776.78
Akhmem Assiut | Inv.13Assuit Akhmem$ | 13 | Akhmem Assiut13 | 1422550.68 | 1206606.61 | 0 | 1206606.61
Al Mostathmreen GIS Substation | MOS-SD-EGP-26 | 26 | Al Mostathmreen GIS Substation26 | 658215.6 | 490370.62 | 98732.34 | 589102.96
Akhmem - Qena | Ref Installation 2 Q |  | Akhmem - Qena | 35936571.43 | 35936571.43 | 0 | 35936571.43
Military 110 Kayan Project | Elkayan Inv.14 | 14 | Military 110 Kayan Project14 | 4202691.67 | 3792524.7 | 0 | 3792524.7
Tamey El-amdeed Substation | TAM-SD-EGP-01 | 1 | Tamey El-amdeed Substation1 | 271650 | 202379.25 | 40747.5 | 243126.75
Akhmem Assiut | Inv.7 Assuit Akhmem$ | 7 | Akhmem Assiut7 | 2317274.58 | 1953940.23 | 0 | 1953940.23
Substation Elco Steel | PSPELCO-IPC 05 | 5 | Substation Elco Steel5 | 5784479.69 | 4588851.87 | 1156895.94 | 5745747.81
Military 110 Kayan Project | Elkayan Inv.15 | 15 | Military 110 Kayan Project15 | 2387909.47 | 2154686.65 | 0 | 2154686.65
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-MEP2 |  | Elsewedy Univ - Enabling Works | 5976537.11 | 6754267.5655 | 1255072.79 | 8009340.3555
AWEER POWER STATION 'H' Phase | CON 035 |  | AWEER POWER STATION 'H' Phase | 319424.66 | 0 | 35491.63 | 35491.63
AWEER POWER STATION 'H' Phase | IMP/062 Rev0 |  | AWEER POWER STATION 'H' Phase | 1352629.53 | 1149663.2875 | 150292.17 | 1299955.4575
AWEER POWER STATION 'H' Phase | IMP/060 |  | AWEER POWER STATION 'H' Phase | 866261.45 | 790463.57 | 0 | 790463.57
AWEER POWER STATION 'H' Phase | Loc-008 | 8 | AWEER POWER STATION 'H' Phase8 | 1387024.56 | 1371591.18 | 0 | 1371591.18
AWEER POWER STATION 'H' Phase | Con-010 rev0 | 10 | AWEER POWER STATION 'H' Phase10 | 1419665.16 | 1263430.18 | 0 | 1405396.69
AWEER POWER STATION 'H' Phase | CON-008 | 8 | AWEER POWER STATION 'H' Phase8 | 1277698.65 | 1121535.47 | 141966.521 | 1263501.991
South Helwan PP (CP-117) | 180153 |  | South Helwan PP (CP-117) | 70286.47 | 73208.98 | 0 | 73208.98
Beni Suef Substation R61 | BSF-CW-EUR-02 | 2 | Beni Suef Substation R612 | 660897.29 | 503546.17 | 99134.59 | 602680.76
Phosfat | Inv.4 Phosfat | 4 | Phosfat4 | 400851 | 357362.9 | 0 | 357362.9
Asec Spare-Parts | Inv 2 Asec Sparepart | 2 | Asec Spare-Parts2 | 905120 | 800208 | 226280 | 1026488
DPW Onshore Port & Terminal | DPW IPC029 | 29 | DPW Onshore Port & Terminal29 | 27690935.6 | 20394668.34 | 4153640.34 | 24548308.68
Zafranaa - Ras Ghareb | Sus.Penalety Ghareeb |  | Zafranaa - Ras Ghareb | -8034.1 | 0 | 0 | -8034.1
Akhmem Assiut | Soc.38-43 Assuit | 43 | Akhmem Assiut43 | 520753.57 | 520753.57 | 0 | 520753.57
Phosfat | Inv.3 Phosfat | 3 | Phosfat3 | 1155861.3 | 1031209.75 | 0 | 1031209.75
Kuwait | Civil/J010 |  | Kuwait | 35275.18 | 26456.39 | 0 | 26456.39
Akhmem Assiut | Ref.Instal1$ Assuit |  | Akhmem Assiut | 85910.91 | 85060 | 0 | 85060
Ismalia Bridge | Ismailia U3 -IPC2 | 2 | Ismalia Bridge2 | 4468989.34 | 4256312.3 | 0 | 4256312.3
Roots -Kafr ElSheikh Bridge | IPC# Final |  | Roots -Kafr ElSheikh Bridge | 40800 | 0 | 0 | 39984
Manshiet Nasser Substation | 2102210003 |  | Manshiet Nasser Substation | 62140.65 | 13365.15 | 9321.1 | 22686.25
Manshiet Nasser Substation | 546 |  | Manshiet Nasser Substation | 3763.04 | 2801 | 594.16 | 3395.16
Manshiet Nasser Substation | 1904210018 |  | Manshiet Nasser Substation | 9322.65 | 7924.25 | 1398.4 | 9322.65
EMAAR-PKG#53-UPTOWN | PKG#53 -IPC 38 | 38 | EMAAR-PKG#53-UPTOWN38 | 726341.65 | 2284218.6225 | 0 | 2284218.6225
Abou El Matameer and Sammanoud | Inv 99 P15Abo Matami | 99 | Abou El Matameer and Sammanoud99 | 4435698.44 | 3059273.97 | 665354.77 | 3724628.74
Kayan 3 New Cairo Capital City | KAYAN FINISHING-IPC6 | 6 | Kayan 3 New Cairo Capital City6 | 44346905.25 | 20011341.75 | 20011344 | 40022685.75
Phosfat | Inv.5 Phosfat | 5 | Phosfat5 | 396824.45 | 353768.05 | 0 | 353768.05
MOTHANA 400/132kV SS | 229 |  | MOTHANA 400/132kV SS | 608929.16 | 608929.16 | 0 | 608929.16
AWEER POWER STATION 'H' Phase | 10050 |  | AWEER POWER STATION 'H' Phase | 286803.1 | 301143.255 | 0 | 301143.255
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 29 | 29 | Benban 500 K.V/95 K.M29 | 294497.14 | 227064.7 | 30922.2 | 257986.9
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 18 | 18 | Benban 500 K.V/95 K.M18 | 4365592.53 | 3365276.96 | 458387.22 | 3823664.18
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 16 | 16 | Benban 500 K.V/95 K.M16 | 2348261.32 | 1810514.82 | 246567.44 | 2057082.26
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 8 | 8 | Benban 500 K.V/95 K.M8 | 922953 | 711599.33 | 96910.07 | 808509.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 18 | 18 | Benban 500 K.V / 100 K.M18 | 609441.4 | 469886.28 | 63991.35 | 533877.63
South Helwan PP (CP-117) | Inv.40 deductions | 40 | South Helwan PP (CP-117)40 | 7459.4 | 7459.4 | 0 | 7459.4
Marsa Matrouh 500KV | Inv.17 Borg Alarab | 17 | Marsa Matrouh 500KV17 | 4562801.6 | 3985608.41 | 479094.17 | 4464702.58
Marsa Matrouh 500KV | Inv.18 Borg Alarab | 18 | Marsa Matrouh 500KV18 | 43700303.53 | 38172221.76 | 4588531.87 | 42760753.63
Canal Sugar S/s | Inv 6 Sugar S/s | 6 | Canal Sugar S/s6 | 60958313.15 | 48157067.39 | 9143746.97 | 57300814.36
Elco Steel 220/33 KV SS | 1903210015 |  | Elco Steel 220/33 KV SS | 4045768.95 | 8496114.8 | 0 | 4248057.4
4 SS - Technical Service | 239 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Akhmem - Qena | Ref.Ret 20%Qena |  | Akhmem - Qena | 1774568.26 | 1773966.11 | 0 | 1773966.11
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC22 | 22 | EMAAR- Pkg 140-ITP-Mivida22 | 5467007.05 | 4603109.1525 | 574035.74 | 5177144.8925
Akhmem Assiut | Social 49 Assuit |  | Akhmem Assiut | 48705.75 | 48705.75 | 0 | 48705.75
Royal City | ROYAL CITY FIN-IPC06 | 6 | Royal City6 | 12948953.9 | 9240902.25 | 2498771.15 | 11739673.4
Port Said Subs 220/66 | Port Said Inv. 7 | 7 | Port Said Subs 220/667 | 36684942.02 | 21827135 | 9171235.51 | 30998370.51
Tamey El-amdeed Substation | TAM-CW-EGP-17 | 17 | Tamey El-amdeed Substation17 | 3347787.42 | 2477362.7 | 502168.11 | 2979530.81
EMAAR-PKG# 101-UPTOWN | PKG#101 -IPC06 | 6 | EMAAR-PKG# 101-UPTOWN6 | 2226073.87 | 2051541.97 | 1066234.31 | 3117776.28
Suez IPB | 2 USD - Suez Steel |  | Suez IPB | 675.89 | 675.89 | 0 | 675.89
SHAT Al ARAB 400/132kV SS | 243 |  | SHAT Al ARAB 400/132kV SS | 255045.23 | 255045.23 | 0 | 255045.23
SHATRA 400/132kV SS | 261 |  | SHATRA 400/132kV SS | 544712.1 | 544712.1 | 0 | 544712.1
MOTHANA 400/132kV SS | 255 |  | MOTHANA 400/132kV SS | 608298.72 | 608298.72 | 0 | 608298.72
Latin Compound - New Alamin | inv ( 22 ) 13-12-20 | 22 | Latin Compound - New Alamin22 | 786553.6 | 49725.46 | 157310.72 | 207036.18
Latin Compound - New Alamin | INV(13)150620 | 13 | Latin Compound - New Alamin13 | 304463.6 | 249907.38 | 0 | 249907.38
Mahmoudia Additional Scope | Inv. 1 EUR & EGP AMm | 1 | Mahmoudia Additional Scope1 | 19798312.5 | 19540937.37 | 0 | 19540937.37
Beni Suef Add-on Sales | 1908210011 |  | Beni Suef Add-on Sales | 255228.8 | 283303.97 | 0 | 283303.97
SHATRA 400/132kV SS | 267 |  | SHATRA 400/132kV SS | 500773.71 | 500773.71 | 0 | 500773.71
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 1 | 1 | Marsa Alam/ Bernes LOT2 OHTL1 | 44190920.45 | 24791099.66 | 4640046.65 | 29431146.31
Ismailiya East Substation | ISE-SD-EURO-01 | 1 | Ismailiya East Substation1 | 2652366.6 | 2163351.2 | 197255.07 | 2360606.27
33KV Canal Farm Grid | Inv. 11 Farm | 11 | 33KV Canal Farm Grid11 | 16845205.87 | 12852892.08 | 2526780.88 | 15379672.96
Tunnel of Sokhna Road (2) | SOKHNA TUNLE2-IPC02F | 2 | Tunnel of Sokhna Road (2)2 | 4550425 | 2166935.25 | 2166940 | 4333875.25
HyperOne Zayed Extension | HYPER ONE-IPC14 | 14 | HyperOne Zayed Extension14 | 5698546.6 | 4476191 | 1424635 | 5900826
Gesr El suez | Claim |  | Gesr El suez | 75000 | 75000 | 0 | 75000
Benban 500 K.V/95 K.M | Benban Lot2 Inv 8 $ | 8 | Benban 500 K.V/95 K.M8 | 46035.04 | 38669.43 | 4833.68 | 43503.11
SHATRA 400/132kV SS | 269 |  | SHATRA 400/132kV SS | 147363.81 | 147363.81 | 0 | 147363.81
MAYSAN 400/132kV SS | 277 |  | MAYSAN 400/132kV SS | 872403.51 | 872403.51 | 0 | 872403.51
Ghana Street lighting | MIDA Ins. Inv.5 | 5 | Ghana Street lighting5 | 79814.12 | 71829.75 | 0 | 71829.75
Ghana Street lighting | MIDA Ins. Inv. 4 | 4 | Ghana Street lighting4 | 54959.5 | 54959.5 | 0 | 54959.5
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 13 | 13 | Benban 500 K.V/95 K.M13 | 224967.76 | 173452.84 | 23621.62 | 197074.46
EMAAR-PKG117- MARASSI | PKG#117-IPC12 | 12 | EMAAR-PKG117- MARASSI12 | 2921423.41 | 3430971.3805 | 0 | 3430971.3805
MAYSAN 400/132kV SS | 280 |  | MAYSAN 400/132kV SS | 951144.62 | 951144.62 | 0 | 951144.62
MAYSAN 400/132kV SS | 279 |  | MAYSAN 400/132kV SS | 95508.96 | 95508.96 | 0 | 95508.96
MOTHANA 400/132kV SS | 281 |  | MOTHANA 400/132kV SS | 1488764.49 | 1488764.49 | 0 | 1488764.49
ESU Ph2-Enabling & Struc | ESU2 ENABLE-IPC2 | 2 | ESU Ph2-Enabling & Struc2 | 9229848.29 | 8526565.2945 | 305476.53 | 8832041.8245
Celia | IPC#4 | 4 | Celia4 | 263685.03 | 240744.43 | 0 | 240744.43
Mahmoudia Additional Scope | Cr. Note reclass |  | Mahmoudia Additional Scope | 0 | -19798312.5 | 0 | -19798312.5
Beni-Suef Power Plant EPC | 1907210005 |  | Beni-Suef Power Plant EPC | 15575298.86 | 15575298.86 | 0 | 15575298.86
Elco Steel 220/33 KV SS | 1901210005 |  | Elco Steel 220/33 KV SS | 3867608.88 | 4060989.32 | 0 | 4060989.32
MAYSAN 400/132kV SS | 286 |  | MAYSAN 400/132kV SS | 57277.09 | 57277.09 | 0 | 57277.09
MAYSAN 400/132kV SS | 285 |  | MAYSAN 400/132kV SS | 535440.2 | 535440.2 | 0 | 535440.2
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .22 | 22 | Benban 3/ Toshka 2 LOT 422 | 1185100.78 | 932281.41 | 124435.58 | 1056716.99
CFC Podium 2 | CFC-IPC01 | 1 | CFC Podium 21 | 6586123.18 | 6200445.359 | 746907.51 | 6947352.869
Royal City | ROYAL ZONE-IPC01 | 1 | Royal City1 | 1714285.71 | 1782857.1355 | 0 | 1782857.1355
EMAAR- Pkg 140-ITP-Mivida | 20100001 |  | EMAAR- Pkg 140-ITP-Mivida | 7170532.11 | 6547225.82 | 840511.96 | 7387737.78
Badr 500 S/S / Zizenia 220 Kv | Badr-Zizenia Inv.2 | 2 | Badr 500 S/S / Zizenia 220 Kv2 | 2936556 | 1725832.9 | 734139 | 2459971.9
Zafranaa - Ras Ghareb | Abolila Zafra kharb- |  | Zafranaa - Ras Ghareb | 69944 | 66749.5 | 0 | 66749.5
Manshiet Nasser Substation | 504 |  | Manshiet Nasser Substation | 4964442.6 | 2708454.87 | 0 | 2708454.87
CFC Podium 2 | CFC-IPC13 | 13 | CFC Podium 213 | 13989651.96 | 23213755.8 | 4308604.78 | 27522360.58
EDNC Retail & Offices Civil | SOREAL-IPC10 | 10 | EDNC Retail & Offices Civil10 | 82638241.08 | 33486093.464 | 0 | 33486093.464
Toshka GIS 500 kV | Toshka Sub Inv. 24.$ | 24 | Toshka GIS 500 kV24 | 25418.1 | 14193.95 | 6672.25 | 20866.2
Miscellaneous Projects | 2002210025 |  | Miscellaneous Projects | 2705.17 | 3002.73 | 0 | 3002.73
Akhmem - Qena | Re soc Inv 24 Quna | 24 | Akhmem - Qena24 | 730.39 | 730.39 | 0 | 730.39
Ministry Building EPOXY | 10017 |  | Ministry Building EPOXY | 8038.67 | 7556.35 | 0 | 7556.35
Baron Palace | 10076 |  | Baron Palace | 13094.4 | 11654.02 | 0 | 11654.02
Sodic Wesset | 10023 |  | Sodic Wesset | 81830 | 74710.7958 | 0 | 74710.7958
SHAT Al ARAB 400/132kV SS | 320 |  | SHAT Al ARAB 400/132kV SS | 427366.81 | 427366.81 | 0 | 427366.81
MAYSAN 400/132kV SS | 309 |  | MAYSAN 400/132kV SS | 38529.77 | 38529.77 | 0 | 38529.77
SHAT Al ARAB 400/132kV SS | 324 |  | SHAT Al ARAB 400/132kV SS | 342052.44 | 342052.44 | 0 | 342052.44
SHATRA 400/132kV SS | 341 |  | SHATRA 400/132kV SS | 794555.75 | 794555.75 | 0 | 794555.75
MOTHANA 400/132kV SS | 318 |  | MOTHANA 400/132kV SS | 511828.9 | 511828.9 | 0 | 511828.9
MOTHANA 400/132kV SS | 317 |  | MOTHANA 400/132kV SS | 276832.06 | 276832.06 | 0 | 276832.06
MOTHANA 400/132kV SS | 316 |  | MOTHANA 400/132kV SS | 125524.85 | 125524.85 | 0 | 125524.85
Elhegaz | IPC#1 | 1 | Elhegaz1 | 2073000 | 77808.5 | 0 | 2052270
4 SS - Technical Service | 344 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Benban 4 As El-Nakra 220 K.V | Inv.1 Final ElNokra. | 1 | Benban 4 As El-Nakra 220 K.V1 | 6953627.16 | 6456442.88 | 0 | 6456442.88
AWEER POWER STATION 'H' Phase | Eng-027 rev0 | 27 | AWEER POWER STATION 'H' Phase27 | 35689.97 | 37474.4685 | 0 | 37474.4685
ESU Ph2-Enabling & Struc | E.S.U2 ARCH&MEP-IPC2 | 2 | ESU Ph2-Enabling & Struc2 | 21431317.62 | 5698476.15 | 6675234.63 | 33433624.13
R5 | inv(5)100220 | 5 | R55 | 1399065 | 740392.25 | 0 | 1273424.31
Multi Sport Hall | 10153 |  | Multi Sport Hall | 150313.25 | 133778.8 | 0 | 133778.8
W Dam PP Phase II (CP-117) | 2002210030 |  | W Dam PP Phase II (CP-117) | 19430.12 | 20440 | 0 | 20440
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .1 | 1 | Benban 3/ Toshka 2 LOT 41 | 4009745.48 | 3086514.46 | 421023.28 | 3507537.74
Multi Sport Hall | 10215 |  | Multi Sport Hall | 364760 | 320824 | 0 | 320824
Baron Palace | 10213 |  | Baron Palace | 1816.32 | 1616.52 | 0 | 1616.52
Elhegaz | Calim-001 | 1 | Elhegaz1 | 310102.8 | 0 | 0 | 307382.6
El Sewedy University | Inv(1)010320 | 1 | El Sewedy University1 | 628419.21 | 31420.96 | 0 | 536342.25
Miscellaneous Projects | 2008210006 |  | Miscellaneous Projects | -16071.1 | -17838.924 | 0 | -17838.924
LAYYAH CCPP | 489 |  | LAYYAH CCPP | 6538440 | 5861484.65 | 971207 | 6832691.65
LAYYAH CCPP | 488 |  | LAYYAH CCPP | 527000 | 895900 | 158100 | 527000
Marsa Matrouh 500KV | Ref Retention Matroh |  | Marsa Matrouh 500KV | 61395309.93 | 56937414.75 | 0 | 56937414.75
MOTHANA 400/132kV SS | 365 |  | MOTHANA 400/132kV SS | 1192960.62 | 1192960.62 | 0 | 1192960.62
NUCA R05 - Z02 | IPC 49 R05 (2) | 49 | NUCA R05 - Z0249 | 12129061.24 | 14397594.5 | 1885695.51 | 16283290.01
Marsa Matrouh 500KV | Ref.Retention Matroh |  | Marsa Matrouh 500KV | 77665491.48 | 77549954.22 | 0 | 77549954.22
Sodic East | IPC_14_Rowad_seast |  | Sodic East | 1150616.1 | 719286.82 | 0 | 719286.82
Minis Building(Polyurethane) | IPC_14_Rowad_poly |  | Minis Building(Polyurethane) | 140805.4 | 125316.81 | 0 | 125316.81
Sodic East | IPC_16_rowad_s_east |  | Sodic East | 509144.6 | 450847.5433 | 0 | 450847.5433
EMAAR-PKG#22-MARASSI | OB-ST- PKG#22 |  | EMAAR-PKG#22-MARASSI | 80820.93 | 80820.93 | 0 | 80820.93
Multi Sport Hall | IPC_13_Rowad_IndoorH |  | Multi Sport Hall | 49020 | 43627.8 | 0 | 43627.8
SHAT Al ARAB 400/132kV SS | 374 |  | SHAT Al ARAB 400/132kV SS | 46724.52 | 46724.52 | 0 | 46724.52
Assuit PP (CP-118) | 2009210018 |  | Assuit PP (CP-118) | 402402.68 | 359105.39 | 63378.42 | 422483.81
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 36 | 36 | ORA ZED - Ph 01B - Pkgs A&D36 | 9427628.57 | 7054023.71 | 989901 | 8043924.71
Mohamed Ali Palace | colsing tr0015 |  | Mohamed Ali Palace | 46349.8 | 16222.43 | 0 | 16222.43
Toshka GIS 500 kV | Toshka Sub Inv. 05 $ | 5 | Toshka GIS 500 kV5 | 75446.67 | 51022.35 | 19804.75 | 70827.1
Toshka GIS 500 kV | Toshka Sub Inv. 06 $ | 6 | Toshka GIS 500 kV6 | 226768.1 | 145455.66 | 59526.63 | 204982.29
AWEER POWER STATION 'H' Phase | Con-016 | 16 | AWEER POWER STATION 'H' Phase16 | 638849.32 | 631751 | 0 | 631751
Ghana Street lighting | MIDA Sply. Inv. 1 | 1 | Ghana Street lighting1 | 374376.6 | 336938.94 | 0 | 336938.94
Ministries Buildings | MIN-LAND SCAPE-IPC03 | 3 | Ministries Buildings3 | 3144575.84 | 2018500 | 672850 | 2691350
Ghana Street lighting | MIDA Sply. Inv. 2 | 2 | Ghana Street lighting2 | 640139.36 | 640139.36 | 0 | 640139.36
Canal Sugar S/s | Inv 10 Sugar S/s | 10 | Canal Sugar S/s10 | 19475165.77 | 14859551.48 | 2921274.87 | 17780826.35
Latin Compound - New Alamin | inv ( 24 )17-12-2020 | 24 | Latin Compound - New Alamin24 | 815614.8 | 487553.77 | 203903.7 | 691457.47
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC02 | 2 | ElSewedy HQ Internal Finishing2 | 7766126.67 | 8230813.242 | 1075170.11 | 9305983.352
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 05 | 5 | Toshka-04 GIS Substation5 | 5476607.65 | 0 | 575043.8 | 575043.8
Miscellaneous Projects | 2011210005 |  | Miscellaneous Projects | 4035.7 | 4600.7 | 0 | 4600.7
Substation Elco Steel | PSP ELCO-IPC FINAL |  | Substation Elco Steel | 54510.72 | 1648328.74 | 0 | 1648328.74
Kattameya Creeks | KATAMYA CREEKS IPC13 | 13 | Kattameya Creeks13 | 41829784.58 | 39353596.009 | 4126609.95 | 43480205.959
Kattameya Creeks | KATAMYA CREEKS-IPC02 | 2 | Kattameya Creeks2 | 12368012.17 | 11295285.7785 | 1567446.9 | 12862732.6785
Al-Ula Towers | inv ( 1 )3-2021 | 1 | Al-Ula Towers1 | 406211.6 | 402149.49 | 0 | 402149.49
Minis Building(Polyurethane) | IPC_19_Rowad_Poly |  | Minis Building(Polyurethane) | 75366.57 | 67076.24 | 0 | 67076.24
EMAAR-PKG# 144, Marassi | PKG#144-IPC15 | 15 | EMAAR-PKG# 144, Marassi15 | 2638692.38 | 5968624.239 | 0 | 5968624.239
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 06 | 6 | Suez Gulf/S4 - 500KV OHTL6 | 1340748.22 | 1087338.54 | 140778.56 | 1228117.1
Ministries Buildings | MIN-LONG LEAD-IPC03 | 3 | Ministries Buildings3 | 6495102.12 | 231155 | 0 | 5864232.84
Toshka-04 GIS Substation | Toshka Sub 4 Inv.1 $ | 1 | Toshka-04 GIS Substation1 | 5356664.94 | 0 | 562449.82 | 562449.82
HAC CCC JV | FPC - HAC CCC JV |  | HAC CCC JV | 260595 | 223127.83 | 0 | 223127.83
Miscellaneous Projects | 2012210029 |  | Miscellaneous Projects | 249355.92 | 284265.7488 | 0 | 284265.7488
West Port Said 220 kV GIS | P-45-Portsaid Inv.3$ | 3 | West Port Said 220 kV GIS3 | 1248647.62 | 0 | 131108 | 131108
West Port Said 220 kV GIS | P-45-Portsaid Inv.1$ | 1 | West Port Said 220 kV GIS1 | 4122810.48 | 0 | 432895.1 | 432895.1
New Babil 400/132KV Substation | 2103210003 |  | New Babil 400/132KV Substation | 225549.98 | 225549.98 | 0 | 225549.98
Ahl Misr Walkway | IPC#1` EDECS | 1 | Ahl Misr Walkway1 | 230152 | 221751.46 | 0 | 221751.46
Suez Gulf/S4 - 500KV OHTL | Suez S4 Equ Inv. 01 | 1 | Suez Gulf/S4 - 500KV OHTL1 | 724268.61 | 548598.15 | 78376.21 | 626974.36
Zone(J) South Valley Toshka | South Valley Inv. 12 | 12 | Zone(J) South Valley Toshka12 | 33976423.1 | 25600265.35 | 4348982.2 | 29949247.55
Zone(J) South Valley Toshka | South Valley Inv. 10 | 10 | Zone(J) South Valley Toshka10 | 39027367.43 | 29518000.8 | 4995503.08 | 34513503.88
Phosfat | Final Inv.7 Phosfat | 7 | Phosfat7 | 1607817.98 | 1346953.2 | 0 | 1346953.2
AWEER POWER STATION 'H' Phase | ENG/037 |  | AWEER POWER STATION 'H' Phase | 149868.45 | 157361.87 | 0 | 157361.87
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC06 | 6 | EMAAR-Pkg#162/163- Marassi6 | 0.001 | 2070801.281 | 264985.85 | 2335787.131
Marsa Alam/ Bernes LOT2 OHTL | Ref.Ret Marsa Alam 5 |  | Marsa Alam/ Bernes LOT2 OHTL | 2046623.19 | 1301246.19 | 0 | 1301246.19
AWEER POWER STATION 'H' Phase | ENG/039 |  | AWEER POWER STATION 'H' Phase | 198675.86 | 208609.653 | 0 | 208609.653
Badr | Inv. 27 Badr | 27 | Badr27 | 16367375.55 | 11259705.15 | 2455106.35 | 13714811.5
Mauritania Lot 1 | Inv.14 - Lot 1 | 14 | Mauritania Lot 114 | 242060.67 | 229943.01 | 0 | 229943.01
Mauritania Lot 1 | Inv.13 - Lot 1 | 13 | Mauritania Lot 113 | 216173.948 | 205350.63 | 0 | 205350.63
Ghana Street lighting | MIDA Ins.7 |  | Ghana Street lighting | 49881.79 | 44893.61 | 0 | 44893.61
Akhmem - Qena | Ref.Ret Quana akh 2 |  | Akhmem - Qena | 30000000 | 0 | 0 | 0
Diplomatic District - Infra | Diplo Dist. IPC01 | 1 | Diplomatic District - Infra1 | 0.001 | 1022317.681 | 123339.89 | 1145657.571
Air Force Project | Air Force Inv . 06 | 6 | Air Force Project6 | 8495366.5 | 6082682.3 | 2123841.65 | 8206523.95
Air Force Project | Air Force Inv . 01 | 1 | Air Force Project1 | 15160757.98 | 10587000 | 3790189.5 | 14377189.5
SHATRA 400/132kV SS | 409 |  | SHATRA 400/132kV SS | 758009.99 | 758009.99 | 0 | 758009.99
EGAT Pelletizing Plant | EGAT WaterTank IPC02 | 2 | EGAT Pelletizing Plant2 | 2028589.79 | 2008303.8895 | 0 | 2008303.8895
LAYAN Substation | 10622 |  | LAYAN Substation | 18500 | 19425 | 0 | 19425
New Babil 400/132KV GIS Substa | 2106210001 |  | New Babil 400/132KV GIS Substa | 136269.78 | 136269.78 | 0 | 136269.78
Elco Steel 220/33 KV SS | 2106210005 |  | Elco Steel 220/33 KV SS | 3839.94 | 4031.937 | 0 | 4031.937
Koning Food LP-04-20 | 22 |  | Koning Food LP-04-20 | 20000 | 17764.174 | 5000 | 22764.174
Mehwar elsalam Lock & Load | م 1 الطوارىء لوك لود | 1 | Mehwar elsalam Lock & Load1 | 2777108.86 | 2471626.89 | 0 | 2471626.89
SHATRA 400/132kV SS | 417 |  | SHATRA 400/132kV SS | 149957.89 | 149957.89 | 0 | 149957.89
Assuit PP (CP-118) | 2108210001 |  | Assuit PP (CP-118) | -6446.14 | -6446.14 | 0 | -6446.14
Miscellaneous Projects | 2009210013 |  | Miscellaneous Projects | 132787.2 | 151377.41 | 0 | 151377.41
RING ROAD MARYOTIA EXPANSION | Maryotya IPC08 | 8 | RING ROAD MARYOTIA EXPANSION8 | 2554128.57 | 2528587.28 | 0 | 2528587.28
Canal Sugar S/s | Ref.Ret Sugar Sub |  | Canal Sugar S/s | 11335814.58 | 11335814.58 | 0 | 11335814.58
Canal Sugar 33KV OHTL | Ref Ret Sugar 33 -OH |  | Canal Sugar 33KV OHTL | 338437.98 | 338437.98 | 0 | 338437.98
South Mohamed Ben Zayed S.L | Ben Zayed Inv. 01 | 1 | South Mohamed Ben Zayed S.L1 | 21877894.1 | 17754986.46 | 0 | 17754986.46
Manshiet Nasser Substation | 2104210003 |  | Manshiet Nasser Substation | 104206.18 | 67811.25 | 16771.87 | 84583.12
EGAT Pelletizing Plant | EGAT WaterTank IPC04 | 4 | EGAT Pelletizing Plant4 | 766173.48 | 758512.36 | 0 | 758512.36
LRT Project | IPC-05-LRT | 5 | LRT Project5 | 215928.65 | 170000 | 0 | 170000
MAYSAN 400/132kV SS | 423 |  | MAYSAN 400/132kV SS | 7852.01 | 7852.01 | 0 | 7852.01
Waldorf Astoria Cairo | waldorf astoria IPC4 | 4 | Waldorf Astoria Cairo4 | 5452379.98 | 4634265 | 4727040.72 | 9361305.72
New Babil 400/132KV GIS Substa | 2111210002 |  | New Babil 400/132KV GIS Substa | 737736.39 | 737736.39 | 0 | 737736.39
Air Force Project | Air Force Inv . 15 | 15 | Air Force Project15 | 6930616.41 | 6694570 | 0 | 6694570
Akhmem Assiut | Ret Asuit akh 4 T |  | Akhmem Assiut | 20000000 | 20000000 | 0 | 20000000
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.07 | 7 | Toshka 2/Owinat East LOT2 OHTL7 | 5119267.58 | 4297214.97 | 537523.1 | 4834738.07
Racecores 3092-17 132KV E | 10964 |  | Racecores 3092-17 132KV E | 74618.74 | 74618.74 | 0 | 74618.74
Taval Sarai 52 | IPC-14-Saray | 14 | Taval Sarai 5214 | 609504.8 | 62502.662 | 0 | 62502.662
ElSewedy HQ Internal Finishing | ElSEWEDY HQ IPC09 | 9 | ElSewedy HQ Internal Finishing9 | 11039038.38 | 10415313.809 | 2893338.07 | 20068257.919
Get Business Complex | INV ( 16 ) GET | 16 | Get Business Complex16 | 1172197.1 | 841428.096 | 0 | 841428.096
New Babil 400/132KV GIS Substa | 2112210004 |  | New Babil 400/132KV GIS Substa | 234031.6 | 234031.6 | 0 | 234031.6
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 01 | 1 | Hosh Essa 220 KV OHTL1 | 12313722.65 | 7395451.78 | 1292940.88 | 8688392.66
Railway Bridge - Assuit | IPC#5 - Assuit | 5 | Railway Bridge - Assuit5 | 1021200 | 880194 | 0 | 880194
Benban 500 K.V / 100 K.M | رد تامين3بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 5000000 | 5000000 | 0 | 5000000
Racecores 3092-15 132KV A | 11122 |  | Racecores 3092-15 132KV A | 2663.71 | 2663.71 | 0 | 2663.71
New Giza Teaching Hospital | newgizahospital ipc1 | 1 | New Giza Teaching Hospital1 | 34312846.59 | 24876813.7695 | 9007122.23 | 33883935.9995
RING ROAD MARYOTIA EXPANSION | el marg ipc10 | 10 | RING ROAD MARYOTIA EXPANSION10 | 3155065.2 | 2795847.4 | 0 | 2795847.4
Port Said Port Silos | supply egp ipc.4 |  | Port Said Port Silos | 4365761.5041 | 13666840 | 1746292.92 | 3853283.23
Racecores 3092-17 132KV E | 11284 |  | Racecores 3092-17 132KV E | 4969 | 4969 | 0 | 4969
Racecores 3092-16 132KV C | 11287 |  | Racecores 3092-16 132KV C | 733.71 | 733.71 | 0 | 733.71
LP-25-21 UIC4 Printers | 52 |  | LP-25-21 UIC4 Printers | 12719.25 | 14372.75 | 0 | 14372.75
Racecores 3092-16 132KV C | 11242 |  | Racecores 3092-16 132KV C | 10500 | 0 | 0 | 11025
DEWA 36 (OPGW) | 11364 |  | DEWA 36 (OPGW) | 50442 | 50442 | 0 | 50442
Port Said Subs 220/66 | Port Said Inv. 6 | 6 | Port Said Subs 220/666 | 103208213.09 | 61408475 | 25802053.3 | 87210528.3
MDF Factory | MDF FACTORY2 IPC03 | 3 | MDF Factory3 | 2443274.75 | 2459303.395 | 0 | 2459303.395
AWEER POWER STATION 'H' Phase | IMP/067 |  | AWEER POWER STATION 'H' Phase | 60327.52 | 63343.896 | 0 | 63343.896
Beni Seuf - 358 | Inv. 12 Oewon Mousa | 12 | Beni Seuf - 35812 | 91294935.39 | 50000000 | 15704052.4 | 65811831.08
El Taameer Axis Expansion | IPC#7 Taamer | 7 | El Taameer Axis Expansion7 | 911196 | 880215.34 | 0 | 880215.34
Sodic East | IPC-Final-Sodic East |  | Sodic East | -261545 | 120750.94 | 0 | 120750.94
EGAT Pelletizing Plant | watertank IPC 11 | 11 | EGAT Pelletizing Plant11 | 1787146.2 | 1769274.74 | 0 | 1769274.74
Ghana Street lighting | MIDA Sply. Inv.10 | 10 | Ghana Street lighting10 | 45614.39 | 41052.95 | 0 | 41052.95
Racecores 3092-17 132KV E | 11476 |  | Racecores 3092-17 132KV E | 1451.42 | 1451.42 | 0 | 1451.42
LP-27-21-Elsewedy1000RFID | 74 |  | LP-27-21-Elsewedy1000RFID | 5530 | 6304.2 | 0 | 6304.2
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 13 | 13 | Suez Gulf/S4 - 500KV OHTL13 | 5214701.88 | 1776644.04 | 0 | 1776644.04
TZ – Offshore E&M Procurement | 447 |  | TZ – Offshore E&M Procurement | 249384.72 | 174569.3 | 49876.94 | 224446.24
Miscellaneous Projects | 220321002 |  | Miscellaneous Projects | 648182 | 738927.48 | 0 | 738927.48
PLAYA ROOF & Wet Areas | IPC-6-PLAYA ROOF | 6 | PLAYA ROOF & Wet Areas6 | 156120.8 | 133577.26 | 0 | 133577.26
New Babil 400/132KV GIS Substa | 220221001 |  | New Babil 400/132KV GIS Substa | 721910.7 | 577528.56 | 0 | 721910.7
Mivida BP#189 | Emaar Pkg#189 ipc 21 | 21 | Mivida BP#18921 | 22586754.17 | 14476604.0585 | 1839999.52 | 16316603.5785
Beymen Fit Out | pkg #205 ipc 4 | 4 | Beymen Fit Out4 | 355037.33 | 323379.51 | 23864.74 | 347244.25
New Babil 400/132KV GIS Substa | 220421001 |  | New Babil 400/132KV GIS Substa | 2589125.81 | 2589125.81 | 0 | 2589125.81
EDNC Hardscape Package | EDNC HARDESCAPE IPC3 | 3 | EDNC Hardscape Package3 | 5414598.24 | 5240048.512 | 0 | 5240048.512
Al-Ula Towers | inv ( 3 ) 15-6-2022 | 3 | Al-Ula Towers3 | 704867.2 | 470009.89 | 0 | 470009.89
Ghana Street lighting | MIDA Ins. Inv. 14 | 14 | Ghana Street lighting14 | 30507.77 | 27456.99 | 0 | 27456.99
Mahmoudia Additional Scope | 2005210008 |  | Mahmoudia Additional Scope | 625000 | 225000 | 400000 | 625000
Kayan 3 New Cairo Capital City | كيان صحى م 4 | 4 | Kayan 3 New Cairo Capital City4 | 2205970 | 1578873.1 | 0 | 1578873.1
Assuit PP (CP-118) | Invoice # 27 Assuit |  | Assuit PP (CP-118) | 2850495.23 | 2993019.99 | 0 | 2993019.99
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .22 | 22 | Benban 3/ Toshka 2 LOT 422 | 3132051.3 | 2793396.41 | 0 | 2793396.41
Benban 500 K.V / 100 K.M | Ref-Ret-Benban lot1 |  | Benban 500 K.V / 100 K.M | 6000000 | 6000000 | 0 | 6000000
158E/2019 33kv Project | 11543 |  | 158E/2019 33kv Project | 2198273.88 | 2587844.86 | 0 | 1293922.43
MDF Factory | MDF - IPC18 | 18 | MDF Factory18 | 3979485.33 | 3423126.0965 | 1306895.58 | 4730021.6765
PLAYA ROOF & Wet Areas | IPC-2-PLAYA ROOF | 2 | PLAYA ROOF & Wet Areas2 | 60260.25 | 51709.33 | 0 | 51709.33
Baron Palace | 10024 |  | Baron Palace | 8025.6 | 7142.784 | 0 | 7142.784
Al-Shabab PP Phase II (CP-117) | 2001220002 |  | Al-Shabab PP Phase II (CP-117) | 0 | -0.03 | 0 | -0.03
MDF Factory | MDF factory(2) IPC7 | 7 | MDF Factory7 | 787160.02 | 795031.6228 | 0 | 795031.6228
Racecores 3092-16 132KV C | 11767 |  | Racecores 3092-16 132KV C | 10800 | 11340 | 0 | 11340
SSC Suez Steel Company Project | In&ReSupply(ABB)ipc3 | 3 | SSC Suez Steel Company Project3 | 1037578.56 | 814872.9584 | 357590.81 | 1172463.7684
LP-16-21 VC Elsewedy P. | 80 |  | LP-16-21 VC Elsewedy P. | 1635028.68 | 931966.35 | 0 | 931966.35
RING ROAD MARYOTIA EXPANSION | mariotya ipc18 | 18 | RING ROAD MARYOTIA EXPANSION18 | 27321187.62 | 27047975.741 | 0 | 27047975.741
Cairo-Alex Railway | cairo-alex ipc 28 | 28 | Cairo-Alex Railway28 | 2127149 | 1545725.91 | 223350.65 | 1769076.56
Ain Sokhna Port Development | IPC#19 Sokhna Port | 19 | Ain Sokhna Port Development19 | 740772 | 555082.66 | 0 | 693853.32
EDNC Hardscape Package | Sorealhardscape IPC9 | 9 | EDNC Hardscape Package9 | 5047602.19 | 1004245.4695 | 0 | 1004245.4695
Ministries Buildings | MINISTIRYFITOUT IPC4 | 4 | Ministries Buildings4 | 37243120.9 | 31376920 | 0 | 31376920
Abou Ghaleb Bridge | Abo ghaleb ipc 05 | 5 | Abou Ghaleb Bridge5 | 13460041.27 | 11836953.4135 | 0 | 11836953.4135
October Under-Railway Tunnel | october tunnel ipc1 | 1 | October Under-Railway Tunnel1 | 802790.71 | 1520548 | 0 | 1520548
El Khatatba Bridge | el khatatba ipc 06 | 6 | El Khatatba Bridge6 | 11047474.29 | 9612859.45 | 0 | 9612859.45
seashell Playa | IPC000024' | 24 | seashell Playa24 | 34.51 | 34.51 | 0 | 34.51
Creeks URBN-K | urbn-k ipc 11 | 11 | Creeks URBN-K11 | 13885723.37 | 11569432 | 1914479.74 | 13483911.74
Creeks URBN-K | URBN-K IPC 12 | 12 | Creeks URBN-K12 | 10141133.17 | 8618325 | 1285635.17 | 9903960.17
Seashell Playa 5 Villas | seashell playa- IPC2 | 2 | Seashell Playa 5 Villas2 | 297533.35 | 249026.8 | 0 | 249026.8
Sokhna Port Expansion | sokhna port ex ipc04 | 4 | Sokhna Port Expansion4 | 24751031.1 | 16604871.935 | 5197716.53 | 21802588.465
SSC Suez Steel Company Project | R.O(5:8) APP ipc 4 | 4 | SSC Suez Steel Company Project4 | 1554992.04 | 1195633.3756 | 530407.79 | 1726041.1656
SSC Suez Steel Company Project | R.O. Supply - IPC5 | 5 | SSC Suez Steel Company Project5 | 4510403.17 | 0 | 1353120.95 | 5096755.5838
ORA-ZED Towers P01B | IPC000003 | 3 | ORA-ZED Towers P01B3 | 128121.83 | 113451.88 | 0 | 113451.88
Playa Epoxy | 4 |  | Playa Epoxy | 84594.2 | 72590.28 | 0 | 72590.28
HSR-6th of October | final HSR |  | HSR-6th of October | 1275240 | 1001891.28 | 0 | 1001891.28
EPICO 3 Facility | EIPICO3- IPC 2 | 2 | EPICO 3 Facility2 | 13487203.1 | 13338534.97 | 0 | 13338534.97
Katameya Creeks - RME | IPC000002 | 2 | Katameya Creeks - RME2 | 13243.47 | 11227.1 | 0 | 11227.1
MDF Factory | MDF 2 - IPC 10 | 10 | MDF Factory10 | 606265.2 | 612327.848 | 0 | 612327.848
U3 & U5 | IPC1-TR055 | 1 | U3 & U51 | 741275.46 | 640165 | 0 | 640165
El-Warraq | IPC#1 Warraq | 1 | El-Warraq1 | 860000 | 763766 | 0 | 763766
MAF HQ Renovation | Carrefour RBS IPC1 | 1 | MAF HQ Renovation1 | 1198156.2 | 805760.048 | 314516 | 1120276.048
MDF Factory | MDF Factory2 ipc 16 | 16 | MDF Factory16 | 953893.47 | 963432.4058 | 0 | 963432.4058
Hyper One Badr | INV ( 11 ) Hyper | 11 | Hyper One Badr11 | 553473.99 | 476513.88 | 0 | 476513.88
Asmarat Roads L&L | asmarat IPC Final |  | Asmarat Roads L&L | 2917810 | 2256420 | 0 | 2256420
PLAYA ROOF & Wet Areas | IPC0020 | 20 | PLAYA ROOF & Wet Areas20 | 118402.29 | 101601.02 | 0 | 101601.02
EPICO 3 Facility | Eipico ipc 3 | 3 | EPICO 3 Facility3 | 8222480.29 | 13033885 | 0 | 13033885
MDF Factory | Mdf Factory 3 ipc 13 | 13 | MDF Factory13 | 3743051.03 | 0 | 3780481.5442 | 3780481.5442
Abo Shanab El Agamien | Abo shanab ipc 4 | 4 | Abo Shanab El Agamien4 | 14117757.67 | 0 | 4383784.66 | 4383784.66
Air Defence College | IPC0014 TR46 | 14 | Air Defence College14 | 277883.72 | 235923.26 | 0 | 235923.26
Playa Resort | 230000010 |  | Playa Resort | 35000 | 35000 | 0 | 35000
MDF Factory | MDF factory ipc 34 | 34 | MDF Factory34 | 27337098.5 | 12636241.38 | 11483337.33 | 24119578.71
EIPICO Factory | IPC001 TR54 | 1 | EIPICO Factory1 | 176320 | 151300.19 | 0 | 151300.19
Closed | (29)pkg#32 | 29 | Closed29 | 539887 | 1228520.89 | 0 | 1228520.89
SEASHELL TECHNICAL ROOM | IPC002TR65 | 2 | SEASHELL TECHNICAL ROOM2 | 373089.4 | 322200.01 | 0 | 322200.01
EGAT Mechanical Installations | Egat Piping ipc 1 | 1 | EGAT Mechanical Installations1 | 42583.33 | 32359.0662 | 10645.83 | 43004.8962
EGAT Pelletizing Plant | ipc2 supply of RO | 2 | EGAT Pelletizing Plant2 | 2837834.44 | 1818704.1772 | 1388048.74 | 3206752.9172
EGAT Pelletizing Plant | EGAT MEP- IPC2 | 2 | EGAT Pelletizing Plant2 | 112937.5 | 117455 | 0 | 117455
MDF Factory | MDF2 IPC ( 18) | 18 | MDF Factory18 | 355884.12 | 359356.67 | 0 | 359356.67
Sultana Malak Restoration | Sultana 034 IPC Fin |  | Sultana Malak Restoration | 3151023.81 | 2967850 | 0 | 2967850
EMAAR-Pkg#162/163- Marassi | pkg#177- IPC 40 | 40 | EMAAR-Pkg#162/163- Marassi40 | 2265659.38 | 118928.159 | 0 | 118928.159
HST - 6 October - Arab Cont. | IPC 4 D0076 | 4 | HST - 6 October - Arab Cont.4 | 5781955 | 4959479.76 | 0 | 4959479.76
Wadi El Natroun | IPC#4 | 4 | Wadi El Natroun4 | 750915 | 698815.1 | 0 | 698815.1
El Salam Bridge | IPC#2 | 2 | El Salam Bridge2 | 348690 | -128634.3 | 0 | -128634.3
Sultana Malak Restoration | sultana malak2 final |  | Sultana Malak Restoration | 212099.05 | 199390 | 0 | 199390
U3 & U5 | IPC11 TR55 | 11 | U3 & U511 | 234462.55 | 202481.85 | 0 | 202481.85
VILLA CLUSTRER B | IPC07TR0077 | 7 | VILLA CLUSTRER B7 | 204666.5 | 176749.97 | 0 | 176749.97
ZED Phase 2 | IPC001 TR62 | 1 | ZED Phase 21 | 75881.78 | 64461.55 | 0 | 64461.55
MDF Factory | mdf equip ipc 19 | 19 | MDF Factory19 | 1179001.02 | 1190791 | 0 | 1190791
Mivida BP#189 | pkg#189-IPC4 | 4 | Mivida BP#1894 | 24279069.68 | 21067752.4505 | 2534689.17 | 23602441.6205
HST Bridges-Sokhna & Mahager | sokhna bridge ipc16 | 16 | HST Bridges-Sokhna & Mahager16 | 16000000 | 4888975.7 | 0 | 14888975.7
EIPICO C002-23 | IPC03TR0068 | 3 | EIPICO C002-233 | 167886.92 | 144063.76 | 0 | 144063.76
Wady El Natroon Bridge | wady elnatroon ipc5 | 5 | Wady El Natroon Bridge5 | 8632100 | 7689057.6 | 0 | 7689057.6
Tarek Abdel-Hakim Center | TAH ipc 7 | 7 | Tarek Abdel-Hakim Center7 | 2195644.04 | 1689548.1 | 197607.96 | 1887156.06
U7-SEASHELL | IPC09TR0064 | 9 | U7-SEASHELL9 | 502420.5 | 433890.33 | 0 | 433890.33
Seashell Playa 5 Villas | PLAYA - C072 IPC 4 | 4 | Seashell Playa 5 Villas4 | 16406.84 | 14168.95 | 0 | 14168.95
Abo Shanab El Agamien | Abo Shanab ipc01 | 1 | Abo Shanab El Agamien1 | 8743501.28 | 19325460.17 | 0 | 19325460.17
EIPICO Factory | IPC05TR0054 | 5 | EIPICO Factory5 | 24286.4 | 20840.16 | 0 | 20840.16
Mivida BP#189 | Emaar pkg#189 ipc 19 | 19 | Mivida BP#18919 | 21710553.31 | 23323710.1055 | 2962118.09 | 26285828.1955
Kattmeya Creeks Urban | IPC04TR0071 | 4 | Kattmeya Creeks Urban4 | 81683.7 | 72330.9 | 0 | 72330.9
AIRDEFNSE -EPOXY | IPC01 TR66 | 1 | AIRDEFNSE -EPOXY1 | 25160 | 21360.84 | 0 | 21360.84
Kattmeya Creeks Urban | IPC001 TR71 | 1 | Kattmeya Creeks Urban1 | 863894.37 | 764978.47 | 0 | 764978.47
Ora Zed -Landscape | IPC001 TR70 | 1 | Ora Zed -Landscape1 | 43231.19 | 37096.69 | 0 | 37096.69
R05 (New) | IPC05TR0559 | 5 | R05 (New)5 | 88844 | 75348.59 | 0 | 75348.59
U3 & U5 | IPC17TR0055 | 17 | U3 & U517 | 254302.57 | 219615.69 | 0 | 219615.69
Kattmeya Creeks Urban | IPC05TR0071 | 5 | Kattmeya Creeks Urban5 | 64024.38 | 56693.59 | 0 | 56693.59
Roof-Playa Cluster A,B,C | IPC07TR0088 | 7 | Roof-Playa Cluster A,B,C7 | 628606.13 | 542864.25 | 0 | 542864.25
Seashell Playa 5 Villas | Playa C038- IPC11 | 11 | Seashell Playa 5 Villas11 | 60385.23 | 11638.46 | 0 | 11638.46
WADY EL-NATROUN BRIDGE(HST) | IPC17 wadyelnatroun | 17 | WADY EL-NATROUN BRIDGE(HST)17 | 1667492.5 | 777131.41 | 0 | 777131.41
EIPICO C002-23 | IPC05TR0068 | 5 | EIPICO C002-235 | 30916.9 | 26529.78 | 0 | 26529.78
Port Said Grain Storage | ipc 11 | 11 | Port Said Grain Storage11 | 1200866 | 76901.19 | 0 | 76901.19
ZED Phase 2 | IPC08TR0062 | 8 | ZED Phase 28 | 88072.621 | 74817.41 | 0 | 74817.41
U7-SEASHELL | IPC15TR0064 | 15 | U7-SEASHELL15 | 38381 | 33145.84 | 0 | 33145.84
GOV2 - Infra | Gov2 ipc 26 | 26 | GOV2 - Infra26 | 12717028 | 4895688.12 | 825933.51 | 5721621.63
Tarek Abdel-Hakim Center | TAH ipc 11 | 11 | Tarek Abdel-Hakim Center11 | 6272151.58 | 4826420.64 | 564493.64 | 5390914.28
WADY EL-NATROUN BRIDGE(HST) | IPC#18#WADI ELNATROU | 18 | WADY EL-NATROUN BRIDGE(HST)18 | 859617.5 | 767908.49 | 0 | 767908.49
U7-SEASHELL | IPC16TR0064 | 16 | U7-SEASHELL16 | 26208 | 22633.22 | 0 | 22633.22
U7-SEASHELL | IPC18TR0064 | 18 | U7-SEASHELL18 | 83992.9 | 72536.26 | 0 | 72536.26
VILLA CLUSTRER B | IPC08TR0077 | 8 | VILLA CLUSTRER B8 | 371481.88 | 291405.93 | 0 | 291405.93
Samaya Factory - 2 | Samaya factory ( 1 ) | 1 | Samaya Factory - 21 | 386925 | 360000 | 0 | 360000
Seashell Playa 5 Villas | Playa - c469 ipc 3 | 3 | Seashell Playa 5 Villas3 | 119758.36 | 109411.24 | 0 | 109411.24
MDF Factory | Mdf Factory ipc 39 | 39 | MDF Factory39 | 17738610.9 | 6984174.92 | 7449976.85 | 14434151.77
Waldorf Astoria Cairo | Waldorf Spare ipc 1 | 1 | Waldorf Astoria Cairo1 | 1707917.54 | 1929946 | 0 | 1929946
DP World Basin 2 Ph2 | Dp World PH2 ipc 15 | 15 | DP World Basin 2 Ph215 | 98969.1 | 35568315.9 | 0 | 35568315.9
MDF Factory | MDF Equip ipc 23 | 23 | MDF Factory23 | 539932.48 | 545331.8072 | 0 | 545331.8072
Kafr Shokr Bridge | kafr shokr ipc08 | 8 | Kafr Shokr Bridge8 | 1839476.19 | 1610960.6295 | 0 | 1610960.6295
Sokhna Port Expansion | SPX.1(22+23) part 2 |  | Sokhna Port Expansion | 992022 | 992022 | 0 | 992022
ElSewedy HQ Internal Finishing | ELSEWEDY HQ- IPC 22 | 22 | ElSewedy HQ Internal Finishing22 | 9615384.76 | 10000000.148 | 0 | 10000000.148
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC15 | 15 | ElSewedy HQ Internal Finishing15 | 16126527.14 | 10437709.627 | 3444305.6 | 13882015.227
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 41 | 41 | ORA ZED - Ph 01B - Pkgs A&D41 | 8233965.99 | 6728778.2096 | 0 | 6728778.2096
Abo Ghaleb | IPC#2 Abo Galab | 2 | Abo Ghaleb2 | 156000 | 142483.6 | 0 | 142483.6
Cairo-Alex Railway | Escalation ipc 1:28 | 1 | Cairo-Alex Railway1 | 79609401.55 | 42043714.07 | 0 | 42043714.07
Creeks URBN-K | Katamya Urbnk ipc 13 | 13 | Creeks URBN-K13 | 23806990.16 | 23221916 | 1024902.32 | 24246818.32
RADAMIS CITY | IPC07TR0084 | 7 | RADAMIS CITY7 | 105622.27 | 93528.53 | 0 | 93528.53
RADAMIS CITY | IPC08TR0084 | 8 | RADAMIS CITY8 | 354795.02 | 314170.99 | 0 | 314170.99
Wady El Natroon Bridge | Wady elnatron esc1:8 |  | Wady El Natroon Bridge | 18408122.38 | 15951714.1562 | 0 | 15951714.1562
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 42 | 42 | ORA ZED - Ph 01B - Pkgs A&D42 | 9191767.67 | 7070851.77 | 0 | 7070851.77
Open Channel 2 | IPC03TR0099 | 3 | Open Channel 23 | 1105489.57 | 953595.3 | 0 | 953595.3
Katameya Creeks - RME | IPC20TR0053 | 20 | Katameya Creeks - RME20 | 270410.98 | 239448.92 | 0 | 239448.92
Katameya Creeks - RME | IPC21TR0053 | 21 | Katameya Creeks - RME21 | 63517.06 | 56244.36 | 0 | 56244.36
R05 (New) | IPC11TR0059 | 11 | R05 (New)11 | 135138 | 114610.54 | 0 | 114610.54
AL-JAWHARA PALACE | IPC01TR0095 | 1 | AL-JAWHARA PALACE1 | 29531.25 | 26282.82 | 0 | 26282.82
New Giza Hos | IPC02TR0073 | 2 | New Giza Hos2 | 84721.52 | 76295.93 | 0 | 76295.93
Koumassi Flyover | INV no.13 | 13 | Koumassi Flyover13 | 928223426.66 | 841697209.67 | 0 | 841697209.67
Seashell Playa 5 Villas | PLAYA C470 IPC3 | 3 | Seashell Playa 5 Villas3 | 28196.79 | 24350.74 | 0 | 24350.74
MDF Factory | Mdf Equip ipc 26 | 26 | MDF Factory26 | 1237478.6 | 1249700.047 | 0 | 1249700.047
Wadi El Natroun Bridge | inv ( 1 ) W. Natron | 1 | Wadi El Natroun Bridge1 | 2861070 | 240852.3 | 0 | 240852.3
Cairo-Alex Railway | CR cairo alex ipc 40 | 40 | Cairo-Alex Railway40 | 0 | 0 | 0 | #DIV/0!
Air Defence College | CAN.. |  | Air Defence College | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 62 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
SHATRA 400/132kV SS | 206 |  | SHATRA 400/132kV SS | -4640388.65 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 78 |  | FX-02-22 Decent Life-UE | 2084153.94 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CRIPC_1_SARAYA_GAMA2 |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | Ref.Ret PIPWst inv.4 | 4 | Pyramids Industrial Park4 | 30000 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref.Akhme Asuit T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-Tah ipc07 | 7 | Tarek Abdel-Hakim Center7 | 0 | 0 | 0 | #DIV/0!
ORA-ZED Towers01B | cr.IPC_4_Rowad_Ora |  | ORA-ZED Towers01B | 0 | 0 | 0 | #DIV/0!
DP World Basin 2 Ph2 | Cr DPworldph.2-IPC2 | 2 | DP World Basin 2 Ph22 | 0 | 0 | 0 | #DIV/0!
33KV Canal Farm Grid | Inv. 19 Farm | 19 | 33KV Canal Farm Grid19 | 1466133.62 | 0 | 0 | #DIV/0!
El Mostakbal City Project | CR.2 مد وثيقة تامين |  | El Mostakbal City Project | 0 | 0 | 0 | #DIV/0!
Ministries Buildings | landscape ipc06 | 6 | Ministries Buildings6 | 2042482 | 0 | 0 | #DIV/0!
Al Alamein Marina Towers | FPC- Marina Towers |  | Al Alamein Marina Towers | 308073.15 | 0 | 0 | #DIV/0!
Cairo Capital S1 | Cr, Inv. 1 S1 | 1 | Cairo Capital S11 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11769 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 83 |  | FX-01-22 Decent Life-WD | 1481446.62 | 0 | 0 | #DIV/0!
Residence 8 ( S05 ) | Cr.Inv ( 1 ) S05 | 1 | Residence 8 ( S05 )1 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | DEC ADJ 67 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
184E Substation | 11766 |  | 184E Substation | 0 | 0 | 0 | #DIV/0!
IRAQ - Al-Diwaniya Power Plant | Inv.68 Bank charges | 68 | IRAQ - Al-Diwaniya Power Plant68 | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | ipc1 aswan | 1 | Aswan axis - Daraw1 | 1015991.43 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 14 USD- Suez Gulf |  | Suez Gulf Substation | 296941 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 1 EGP -El Tebein 113 |  | Miscellaneous Projects | 1190173.27 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 48 |  | Al-Shabab PP Phase II (CP-117) | 2223457.74 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 58 |  | Suez Gulf Substation | 1485632.74 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Inv.3&4 deductions | 3 | Assuit PP (CP-118)3 | 0 | 0 | 0 | #DIV/0!
K047 FDH JV | ADJ-Inv.15 | 15 | K047 FDH JV15 | 0 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | Cr.P-13-2016 | 13 | Angola Emergency fast-track13 | 0 | 0 | 0 | #DIV/0!
Port Said Port Silos | Cr-port said EURipc1 | 1 | Port Said Port Silos1 | 0 | 0 | 0 | #DIV/0!
Elniger | CR Close El Niger |  | Elniger | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 51 |  | Al-Shabab PP Phase II (CP-117) | 2223457.74 | 0 | 0 | #DIV/0!
33KV Canal Farm Grid | Soc.2020 تشيد وبناء |  | 33KV Canal Farm Grid | 5000 | 0 | 0 | #DIV/0!
Air Defense College | Air def harek IPC1 | 1 | Air Defense College1 | 65275424.71 | 0 | 0 | #DIV/0!
KATAMYA GREEKS LAND SCAPE STAR | C.IPC03TR0081 | 3 | KATAMYA GREEKS LAND SCAPE STAR3 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR- 18 EGP Domiat | 18 | W Dam PP Phase II (CP-117)18 | 0 | 0 | 0 | #DIV/0!
SSC Suez Steel Company Project | CR R.O Sup. adj ipc4 | 4 | SSC Suez Steel Company Project4 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | adj. 180010 &180013 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
FX-03-22 Urban Communities-WD | 96 |  | FX-03-22 Urban Communities-WD | 696935.72 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 7 EGP - South Helwan |  | South Helwan PP (CP-117) | 59582.1048 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 474 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Air Defence College | 2Cancel IPC11 TR46 | 11 | Air Defence College11 | 190510.2 | 0 | 0 | #DIV/0!
Military 110 Kayan Project | CR.refund ret.kay |  | Military 110 Kayan Project | 0 | 0 | 0 | #DIV/0!
TNYA-WSHP | 11663 |  | TNYA-WSHP | -74312 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,7 usd Borg Ar | 7 | Marsa Matrouh 500KV7 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11523 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 109 |  | Suez Gulf Substation | 75670023.9137 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 536 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
U3 & U5 | TR55-CR2 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
JICA lot 02 | اتحاد تشيدP-29-EGY | 29 | JICA lot 0229 | 5000 | 0 | 0 | #DIV/0!
Mangrouve Hotel - Gouna | CR.TR0021CLOSING.DEC |  | Mangrouve Hotel - Gouna | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 8 |  | Zafranaa - Beni Suef | 103212.25 | 0 | 0 | #DIV/0!
Hosh Eisa Hospit. | can IPC02TR0089 | 2 | Hosh Eisa Hospit.2 | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr Inv 10 Usd Borg | 10 | Marsa Matrouh 500KV10 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | رد تامين الزعفرانه غ |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
U3 & U5 | 55-CR3F |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
Egat Rolling Mill no.4 | CR-rolling millIPC10 | 10 | Egat Rolling Mill no.410 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MCBs inv.No.1.Cncl | 1 | Ghana Street lighting1 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Inv deductions |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10429 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
GPC-Gupco (Automation) | GPC inv. deductions |  | GPC-Gupco (Automation) | 0 | 0 | 0 | #DIV/0!
El Katameya Mall | CR(14)281020 | 14 | El Katameya Mall14 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 304 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 27 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 16 EGP-progress adj. |  | Suez Gulf Substation | 157103.8629 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR-invs 2018 | 2018 | Al-Shabab PP Phase II (CP-117)2018 | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Refund .Reten.banha |  | Siemens 6x500/220 KV GIS-MOU | 377907.88 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | CR. 12 Oewon Mousa |  | Beni Seuf - 358 | 0 | 0 | 0 | #DIV/0!
EMAAR-PKG#62-UPTOWN | CR Amend vat |  | EMAAR-PKG#62-UPTOWN | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | ipc no3 aswan |  | Aswan axis - Daraw | 257712 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR IPC_1_SARAYA_GAMA |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | refund 1 |  | Barwa 2x60/22 KV S/S | 0 | 0 | 0 | #DIV/0!
ACWA POWER & NOMAC HQ | CR ACWA IPC1 | 1 | ACWA POWER & NOMAC HQ1 | 0 | 0 | 0 | #DIV/0!
Military 110 Kayan Project | Ref.Ret. 8 EGP |  | Military 110 Kayan Project | 8 | 0 | 0 | #DIV/0!
R05 (New) | IPC12TR0059 | 12 | R05 (New)12 | 182340 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr-17 EGP - Shabab | 17 | Al-Shabab PP Phase II (CP-117)17 | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-TAH ipc06 | 6 | Tarek Abdel-Hakim Center6 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 260 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 257 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 60 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR.TR0025CLOSING.DEC |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Al Alamein Marina Towers | final inv elalamien |  | Al Alamein Marina Towers | 442239 | 0 | 0 | #DIV/0!
Residence 8 ( k12 ) | Cr.INV ( 1 ) R08-K12 | 1 | Residence 8 ( k12 )1 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180084 |  | Suez Gulf Substation | 3785.08 | 0 | 0 | #DIV/0!
RING ROAD MARYOTIA EXPANSION | crفروق اسعار مريوطية |  | RING ROAD MARYOTIA EXPANSION | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj .1904210014 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 76 |  | Governmental Campus-N2 | 335629 | 0 | 0 | #DIV/0!
IRAQ - Al-Diwaniya Power Plant | rev. ( 65 USD -Diwan |  | IRAQ - Al-Diwaniya Power Plant | 0 | 0 | 0 | #DIV/0!
Beni Suef ISKRA | 258 |  | Beni Suef ISKRA | 0 | 0 | 0 | #DIV/0!
HST Bridges-Sokhna & Mahager | SOKHNA BRI. ESC1:21F |  | HST Bridges-Sokhna & Mahager | 7685556 | 0 | 0 | #DIV/0!
HST Bridge - Arab Contractors | ipc#2#harm city d083 | 2 | HST Bridge - Arab Contractors2 | 1253062.5 | 0 | 0 | #DIV/0!
Kuraimate - Samalot 500KV | Ret.OB Korimat500 |  | Kuraimate - Samalot 500KV | 14168726.79 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 270 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | CR_in 37 |  | Siemens 6x500/220 KV GIS-MOU | 0 | 0 | 0 | #DIV/0!
Bahr ElBakar – Power Station | IPC#02 Madkour CR | 2 | Bahr ElBakar – Power Station2 | 0 | 0 | 0 | #DIV/0!
Multi Sport Hall | CR.TR0013CLOSING.DEC |  | Multi Sport Hall | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR - 7 USD - West D. | 7 | W Dam PP Phase II (CP-117)7 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180075 |  | Suez Gulf Substation | 5242.42 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | IPC#3 - NRCC | 3 | Expansion of Ring Road NRCC3 | 215300 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | inv 1.2 d0080 CR | 1 | Expansion of Ring Road NRCC1 | -344835 | 0 | 0 | #DIV/0!
MAF HQ Renovation | CR po 0020024000370 |  | MAF HQ Renovation | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | CR. 11 Oewon Mousa |  | Beni Seuf - 358 | 0 | 0 | 0 | #DIV/0!
CS-20 Mall | Inv ( 17 ) CS-20 | 17 | CS-20 Mall17 | 173039.56 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Cr.Memo Reten.usd |  | Abo Quir - Badr 500KV | 0 | 0 | 0 | #DIV/0!
PLAYA ROOF & Wet Areas | IPC0022_CR | 22 | PLAYA ROOF & Wet Areas22 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 84 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | Credit-inv4-final | 4 | Al-Ula Towers4 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Inv 29 Shaba EGP | 29 | Al-Shabab PP Phase II (CP-117)29 | 730337.3898 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/002Cnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
El Mostakbal City Project | CR.مد وثيقة التامين |  | El Mostakbal City Project | 0 | 0 | 0 | #DIV/0!
LP-08-22 CFC Digital-Signage | 93 |  | LP-08-22 CFC Digital-Signage | 377358.8 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Cr-memo W.hold 9-EGP |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Mivida BP#189 | cr-emarpkg#189 ipc18 | 18 | Mivida BP#18918 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR_IPC_!_Saraya_Gama |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 06 | 6 | Suez Gulf/S4 - 500KV OHTL6 | 25379.35 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.inv.11 Assuit Akh | 11 | Akhmem Assiut11 | 0 | 0 | 0 | #DIV/0!
Suez Bridge | D0017-OB-Dec-2020/Cr | 2020 | Suez Bridge2020 | 0 | 0 | 0 | #DIV/0!
EPICO 3 Facility | crEipi material ipc3 | 3 | EPICO 3 Facility3 | 0 | 0 | 0 | #DIV/0!
Al-Kayan | CR.TR0012CLOSING.DEC |  | Al-Kayan | 0 | 0 | 0 | #DIV/0!
VILLA CLUSTRER B | IPC09TR0077 | 9 | VILLA CLUSTRER B9 | 3205 | 0 | 0 | #DIV/0!
10Th of Ramadan LRT | CR.10Ramadan Inv.03 | 3 | 10Th of Ramadan LRT3 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR IPC-12-Saray-2 | 12 | Taval Sarai 5212 | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | inv (5) final CA | 5 | Al-Ula Towers5 | 0 | 0 | 0 | #DIV/0!
HSR | HSR-OCT 5 |  | HSR | 44291359.78 | 0 | 0 | 44291359.78
MOC HQ at Diriyah | MOC Inv-01 | 1 | MOC HQ at Diriyah1 | 11546313 | 0 | 0 | 16597824.65
Mivida BP#189 | Emar PKG#189 IPC18 | 18 | Mivida BP#18918 | 18563752.6 | 0 | 0 | 21162677.964
SSC Suez Steel Company Project | R.O(50:80)S adj ipc4 | 4 | SSC Suez Steel Company Project4 | 6762600 | 0 | 0 | 7709364
Capital One | inv ( 10 ) Captal 1 | 10 | Capital One10 | 314044.9 | 0 | 0 | 314044.9
ElSewedy HQ Internal Finishing | elsewedy HQ- IPC24 | 24 | ElSewedy HQ Internal Finishing24 | 25519032.04 | 0 | 0 | 26794983.642
Kafr Shokr Bridge | kafr shokr ipc 9+ | 9 | Kafr Shokr Bridge9 | 1131554.29 | 0 | 0 | 1188132.0045
Kafr Shokr Bridge | kafr shokr ipc09 | 9 | Kafr Shokr Bridge9 | 4378148.57 | 0 | 0 | 4597055.9985
Ghana Street lighting | Pole. Cvr. Inv.2 | 2 | Ghana Street lighting2 | 13755 | 0 | 0 | 13755
FURJAN Cable Works | 11559 |  | FURJAN Cable Works | 4868005.51 | 0 | 0 | 5111405.7855
LAYAN Substation | 11496 |  | LAYAN Substation | 204999.08 | 0 | 0 | 215249.034
Governmental Campus-N2 | 27 |  | Governmental Campus-N2 | 19087.57 | 19075.1844 | 0 | 19084.1844
Bahr ElBakar – Power Station | IPC#02 - Madkour | 2 | Bahr ElBakar – Power Station2 | 1357812 | 0 | 0 | 1357812
Assuit PP (CP-118) | 2108210012 |  | Assuit PP (CP-118) | 188091.51 | 188091.51 | 0 | 188091.51
Elsewedy Univ - Enabling Works | sewedy uni-mep-07 | 7 | Elsewedy Univ - Enabling Works7 | 4929812 | 0 | 0 | 4929812
Elhegaz | D0028-OB-Dec-2020 | 2020 | Elhegaz2020 | 19094677.06 | 0 | 0 | 19094677.06
Ghana Street lighting | MIDA Ins. Inv. 5 | 5 | Ghana Street lighting5 | 51879.18 | 0 | 0 | 51879.18
Ameria | D0030-OB-Dec-2020 | 2020 | Ameria2020 | 976800 | 0 | 0 | 976800
Koning Food V3 LP-09-20 | 14 |  | Koning Food V3 LP-09-20 | 3907.02 | 0 | 0 | 3907.02
Elhegaz | D0028-OB-Dec-20202 | 20202 | Elhegaz20202 | 3047032.8 | 0 | 0 | 3047032.8
ORA-ZED Towers01B | IPC_4_ORA |  | ORA-ZED Towers01B | 265558.44 | 0 | 0 | 265558.44
Safir bridge | D0021-OB-Dec-2020 | 2020 | Safir bridge2020 | 2137025 | 0 | 0 | 2137025
Multi Sport Hall | TR0013DEC.Closing |  | Multi Sport Hall | 1884465 | 0 | 0 | 1884465
Ministries Building ROOF | TR0010DEC.Closing |  | Ministries Building ROOF | 419621.64 | 0 | 0 | 419621.64
Mivida | TR0009DEC.Closing |  | Mivida | 1128062.5 | 0 | 0 | 1128062.5
Dubai Port | TR0005DEC.Closing |  | Dubai Port | 92190.9 | 0 | 0 | 92190.9
Sodic East | TR0004DEC.Closing |  | Sodic East | 6723457.11 | 0 | 0 | 6723457.11
Sewage Treatment Plant | D0024-OB-Dec-2020 | 2020 | Sewage Treatment Plant2020 | 3309831 | 0 | 0 | 3309831
Museum of Egyp. Civilization | D0027-OB-Dec-2020 | 2020 | Museum of Egyp. Civilization2020 | 7444035.25 | 0 | 0 | 7444035.25
AWEER POWER STATION 'H' Phase | IMP/061 |  | AWEER POWER STATION 'H' Phase | 1334822.56 | 0 | 0 | 1401563.688
LRT Project | IPC_1_GRowad_LRT |  | LRT Project | 103200 | 0 | 0 | 103200
Assuit PP (CP-118) | 2011210010 |  | Assuit PP (CP-118) | 3790219.4004 | 0 | 0 | 3790219.4004
Assuit PP (CP-118) | 2009210001 |  | Assuit PP (CP-118) | 2796554.1345 | 0 | 0 | 2796554.1345
Club House-Sodic Wesset | 10037 |  | Club House-Sodic Wesset | 117700 | 0 | 0 | 117700
Manshiet Nasser Substation | 2001210020 |  | Manshiet Nasser Substation | 112340.62 | 102500.56 | 0 | 102500.56
West Damietta PP Phase I | 7 USD - West D. Khor |  | West Damietta PP Phase I | 206295.53 | 206295.53 | 0 | 206295.53
Suez Gulf Substation | 23 EGP VO TOAC |  | Suez Gulf Substation | 285942.83 | 270724.25 | 30080.47 | 300804.72
Elmaragha Bridge - Sohag | IPC#1. | 1 | Elmaragha Bridge - Sohag1 | 1108500 | 0 | 0 | 1108500
Ghana | 30/P/10/ER/2017/USD |  | Ghana | 281189.93 | 0 | 0 | 281189.93
Port Said | Adj Inv 8 Final | 8 | Port Said8 | 2319219.99 | 0 | 0 | 2319219.99
Beni-Suef Power Plant EPC | 180179 |  | Beni-Suef Power Plant EPC | 23871736.05 | 23871736.05 | 0 | 23871736.05
Beni-Suef Power Plant EPC | 6 beni Suef - 1020 | 1020 | Beni-Suef Power Plant EPC1020 | 578156812.05 | 578156812.05 | 0 | 578156812.05
Guinea 2 | P-2S-10 ADJ | 2 | Guinea 22 | 11554466.6 | 0 | 0 | 11554466.6
Al-Shabab PP Phase II (CP-117) | 11 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 170503.2 | 0 | 0 | 170503.2
Marsa Matrouh 500KV | Inv,11 usd Borg Arab | 11 | Marsa Matrouh 500KV11 | 570257.56 | 0 | 0 | 570257.56
Beni-Suef Power Plant EPC | 180121 |  | Beni-Suef Power Plant EPC | 72447911.34 | 0 | 0 | 72447911.34
Akhmem - Qena | Adj Inv 10 | 10 | Akhmem - Qena10 | 129881573.54 | 0 | 0 | 129881573.54
New Heliopolis | Adj Inv 8 | 8 | New Heliopolis8 | 20034607.72 | 0 | 0 | 20034607.72
Siemens 6x500/220 KV GIS-MOU | Adj. Inv. 14 | 14 | Siemens 6x500/220 KV GIS-MOU14 | 146872878.87 | 0 | 0 | 146872878.87
New Capital | Adj Inv. 21 | 21 | New Capital21 | -2859976.89 | 0 | 0 | -2859976.89
Metro 2L Rehabitation Cable | 11 |  | Metro 2L Rehabitation Cable | 23433781 | 0 | 0 | 23433781
Mahmoudia Power Plant | 16 |  | Mahmoudia Power Plant | 1796305467 | 0 | 0 | 1796305467
Cairo South PP Rehabilitation | 90 |  | Cairo South PP Rehabilitation | -1879699.6962 | 0 | 0 | -1879699.6962
Abu Qir PP (CP-118) | 95 |  | Abu Qir PP (CP-118) | 162534882.5048 | 0 | 0 | 162534882.5048
Lina Farm Substation | 6 |  | Lina Farm Substation | 47077633 | 0 | 0 | 47077633
Ain-Sokhna PP (CP-117) | 70 |  | Ain-Sokhna PP (CP-117) | -60401841.9989 | 0 | 0 | -60401841.9989
Banha PP (CP-117) | 73 |  | Banha PP (CP-117) | -28330353.9995 | 0 | 0 | -28330353.9995
Giza North PP Phase3(CP-117) | 83 |  | Giza North PP Phase3(CP-117) | 45181023.2033 | 0 | 0 | 45181023.2033
W Dam PP Phase II (CP-117) | 75 |  | W Dam PP Phase II (CP-117) | 162173895.3701 | 0 | 0 | 162173895.3701
Lina Farm Substation | 2 EGP - Lina |  | Lina Farm Substation | 1056047.85 | 1056047.85 | 0 | 1056047.85
Cairo South PP Rehabilitation | 4 USD - Cairo South |  | Cairo South PP Rehabilitation | 124324.15 | 124324.15 | 0 | 124324.15
Banha PP (CP-118) | 2 USD - Banha 118 |  | Banha PP (CP-118) | 3971.55 | 0 | 0 | 3971.55
Cameron EDC | 030/2021 |  | Cameron EDC | 91259811.22 | 91259810.69 | 0 | 91259810.69
Lina Farm Substation | 6 EGP - Lina |  | Lina Farm Substation | 1281616.08 | 1281616.08 | 0 | 1281616.08
W Dam PP Phase II (CP-117) | 180034 |  | W Dam PP Phase II (CP-117) | 84300.8476 | 0 | 0 | 88515.89
W Dam PP Phase II (CP-117) | 16 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 126741.8571 | 0 | 19961 | 19961
Ismailiya East Substation | ISE-SW-EGP-02 | 2 | Ismailiya East Substation2 | 910000 | 673400 | 136500 | 809900
Beni Suef Substation R61 | BSF-SW-EGP-11 | 11 | Beni Suef Substation R6111 | 342125 | 253172.5 | 51318.75 | 304491.25
W Dam PP Phase II (CP-117) | 27 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 149316.5714 | 133265.04 | 23517.36 | 156782.4
IRAQ - Al-Diwaniya Power Plant | 65 USD -Diwaniya |  | IRAQ - Al-Diwaniya Power Plant | 1178165.5524 | 0 | 0 | 0
Giza North PP Phase3(CP-117) | 24 Euro - Giza N.III |  | Giza North PP Phase3(CP-117) | 338411.5429 | 302032.3 | 0 | 302032.3
Beni Seuf - 358 | Banha-Zagazg Inv.02 | 2 | Beni Seuf - 3582 | 14936190.2 | 0 | 2568703.2 | 2568703.2
Kayan 3 New Cairo Capital City | OB-SI-EL Kayaan2 |  | Kayan 3 New Cairo Capital City | 6017614.8 | 6017614.8 | 0 | 6017614.8
Closed | (3) p.o52/156 | 3 | Closed3 | 827640 | 0 | 0 | 943509.6
Giza North PP Phase3(CP-117) | Inv 43 EGP Giza III | 43 | Giza North PP Phase3(CP-117)43 | 883836.4667 | 928028.29 | 0 | 928028.29
South Helwan PP (CP-117) | 6 EGP - South Helwan |  | South Helwan PP (CP-117) | 761181.781 | 771723.2 | 0 | 799240.87
Barwa and Damac 220 OHTL | Inv No7 Wattanya220 | 7 | Barwa and Damac 220 OHTL7 | 1088147.3 | 807539.65 | 163222.1 | 970761.75
EMAAR-PKG#107-MARASSI | (4) pkg#107 | 4 | EMAAR-PKG#107-MARASSI4 | 5849287 | 4822188.97 | 910581.7 | 5732770.67
Royal City | ROYALCITY-IPC-12 | 12 | Royal City12 | 12232818.51 | 9802860.3155 | 1521591.13 | 11324451.4455
Abo Quir - Badr 500KV | Ref.Ret Bridge2 |  | Abo Quir - Badr 500KV | 167850 | 4699.8 | 0 | 4699.8
South Helwan PP (CP-117) | 180013 |  | South Helwan PP (CP-117) | -3593016.45 | 0 | -1540734.18 | -513578.06
Suez Gulf Substation | 11 USD Suez Gulf |  | Suez Gulf Substation | 66027.72 | 66027.72 | 0 | 66027.72
Suez Gulf Substation | 10 USD Suez Gulf |  | Suez Gulf Substation | 1856743 | 1856743 | 0 | 1856743
Apache Electrical Works | Apachi Inv No PC.#26 |  | Apache Electrical Works | 67749.77 | 67749.77 | 0 | 67749.77
Apache Electrical Works | Abachi Inv No P.C#18 |  | Apache Electrical Works | 44649.31 | 44649.31 | 0 | 44649.31
Al-Wukair 11 Substation | Inv June Qatar |  | Al-Wukair 11 Substation | 10595856.35 | 10595856.35 | 0 | 10595856.35
South Helwan PP (CP-117) | 6 EuroSouth Helwan |  | South Helwan PP (CP-117) | 820360.14 | 820360.14 | 0 | 820360.14
South Helwan PP (CP-117) | 5 EuroSouth Helwan |  | South Helwan PP (CP-117) | 2248485.57 | 2248485.57 | 0 | 2248485.57
EMAAR-PKG#107-MARASSI | (6) pkg#107 | 6 | EMAAR-PKG#107-MARASSI6 | 4593486 | 3381863.35 | 640822.23 | 4022685.58
Tebbin PP Rehabitation(CP-124) | 2 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 9992.26 | 9992.26 | 0 | 9992.26
Strining Lot A- Elegect | Inv No 3 Elegect | 3 | Strining Lot A- Elegect3 | 1018903.51 | 934690.99 | 0 | 934690.99
EMAAR-PKG#85-UPTOWN | (2) pkg#85 | 2 | EMAAR-PKG#85-UPTOWN2 | 632221.85 | 293424.1225 | 270591.53 | 564015.6525
Cairo South PP Rehabilitation | Inv 11 Cairo south | 11 | Cairo South PP Rehabilitation11 | 128240.16 | 128240.16 | 0 | 128240.16
Siemens 6x500/220 KV GIS-MOU | Assuit 82 Inv.12 | 12 | Siemens 6x500/220 KV GIS-MOU12 | 2916027.27 | 2090013.95 | 437404.09 | 2527418.04
El Mostakbal City Project | Inv. 16 Mostakbal | 16 | El Mostakbal City Project16 | 89999706 | 0 | 0 | 0
Badr | Inv. 3-4 Badr | 3 | Badr3 | 6253355 | 4642692.35 | 938003.25 | 5580695.6
Siemens 6x500/220 KV GIS-MOU | Ref. Reten 66 wadi19 |  | Siemens 6x500/220 KV GIS-MOU | 248104.43 | 248104.43 | 0 | 248104.43
Abou El Matameer and Sammanoud | Sammound Inv No 1 | 1 | Abou El Matameer and Sammanoud1 | 23528662.92 | 17015634.76 | 3529299.44 | 20544934.2
South Helwan PP (CP-117) | 180058 |  | South Helwan PP (CP-117) | 26982.57 | 24127.24 | 4257.75 | 28384.99
EMAAR-PKG#107-MARASSI | (11) pkg#107 | 11 | EMAAR-PKG#107-MARASSI11 | 4966368.53 | 4454492.696 | 0 | 4454492.696
Akhmem Assiut | Soci 1&2 Asuit Akhme |  | Akhmem Assiut | 4121022.42 | 4121022.42 | 0 | 4121022.42
Assuit PP (CP-118) | 2108210007 |  | Assuit PP (CP-118) | 410432.59 | 358519.77 | 64643.13 | 423162.9
Assuit PP (CP-118) | 220721003 |  | Assuit PP (CP-118) | 655334.79 | 585170.6 | 102881.34 | 688051.94
Assuit PP (CP-118) | 2105210006 |  | Assuit PP (CP-118) | 296502.505 | 312107.9 | 0 | 312107.9
Assuit PP (CP-118) | 1903210002 |  | Assuit PP (CP-118) | 373943.67 | 333744.72 | 58896.13 | 392640.85
Al-Shabab PP Phase II (CP-117) | 180031 |  | Al-Shabab PP Phase II (CP-117) | 724244.2476 | 0 | 0 | 760456.46
Abou El Matameer and Sammanoud | Soc 5 abou almatamer |  | Abou El Matameer and Sammanoud | 146474.9 | 146474.88 | 0 | 146474.88
Ismailiya East Substation | (5)cw elasmaaliya | 5 | Ismailiya East Substation5 | 4978600.47 | 3709057.35 | 746790.07 | 4455847.42
Ministries Buildings | Mini Landscape IPC04 | 4 | Ministries Buildings4 | 6846859.74 | 1465114.99 | 4395390 | 5860504.99
Apache Electrical Works | Closing Morganti USD |  | Apache Electrical Works | 192916.42 | 145020.88 | 0 | 145020.88
Apache Electrical Works | Closing Morganti bal |  | Apache Electrical Works | 232520.8 | 162104.78 | 0 | 162104.78
Lina Farm Substation | Green power EUR |  | Lina Farm Substation | 14868 | 14868 | 0 | 14868
EMAAR-PKG#53-UPTOWN | PKG#53-IPC 33 | 33 | EMAAR-PKG#53-UPTOWN33 | 3219269.97 | 2214577.5 | 0 | 2214577.5
Kuwait | 36-132KVA(9J) | 132 | Kuwait132 | 57009.91 | 42757.43 | 0 | 42757.43
Akhmem Assiut | Inv.12Assuit Akhmem$ | 12 | Akhmem Assiut12 | 2343024.65 | 1978207.74 | 0 | 1978207.74
Ministries Buildings | MIN-CORE-IPC06 | 6 | Ministries Buildings6 | 13037164.63 | 8237545 | 2745852 | 10983397
Ministries Buildings | MIN-FIT OUT-IPC03 | 3 | Ministries Buildings3 | 1567410.24 | 0 | 1279230.67 | 1279230.67
Marsa Matrouh 500KV | Inv.4 Borg Alarab | 4 | Marsa Matrouh 500KV4 | 10378117.8 | 10378117.8 | 0 | 10378117.8
Abou El Matameer and Sammanoud | Soc.Inv.12 Matamet | 12 | Abou El Matameer and Sammanoud12 | 80779.65 | 80779.65 | 0 | 80779.65
Akhmem Assiut | Inv.15Assuit Akhmem$ | 15 | Akhmem Assiut15 | 502505.24 | 424567.38 | 0 | 424567.38
Akhmem - Qena | Soci.41EGP Qena Akh |  | Akhmem - Qena | 75446.45 | 75446.45 | 0 | 75446.45
Phosfat | Inv.2 Phosfat | 2 | Phosfat2 | 655555.42 | 584675.65 | 0 | 584675.65
South Helwan PP (CP-117) | SH inv.33&34 ded | 33 | South Helwan PP (CP-117)33 | 0 | -7244.06 | 0 | -7244.06
Akhmem - Qena | Ref Instil 4 Qena |  | Akhmem - Qena | 32572164.39 | 32572164.39 | 0 | 32572164.39
AWEER POWER STATION 'H' Phase | CON/026 |  | AWEER POWER STATION 'H' Phase | 266187.22 | 233653.222 | 29576.358 | 263229.58
AWEER POWER STATION 'H' Phase | CON/025 |  | AWEER POWER STATION 'H' Phase | 638849.32 | 560767.7317 | 70983.2583 | 631750.99
AWEER POWER STATION 'H' Phase | LOC/015 |  | AWEER POWER STATION 'H' Phase | 140566.43 | 123386.0815 | 15618.49 | 139004.5715
AWEER POWER STATION 'H' Phase | LOC/010 |  | AWEER POWER STATION 'H' Phase | 2676366.4 | 2646629 | 0 | 2646629
Mall Of Egypt | mall masr-IPC FINAL |  | Mall Of Egypt | 43407790.67 | 237867.55 | 0 | 19146767.55
DPW Onshore Port & Terminal | DP WORLD- IPC 01 | 1 | DPW Onshore Port & Terminal1 | 21619523.77 | 15998139 | 3242928.57 | 19241067.57
DPW Onshore Port & Terminal | dpw ipc33 | 33 | DPW Onshore Port & Terminal33 | 20335452.72 | 15048235.01 | 3050317.91 | 18098552.92
Akhmem - Qena | Social Inv.45-46 Qen | 45 | Akhmem - Qena45 | 348892.8 | 348892.8 | 0 | 348892.8
Strining Lot A- Elegect | Ref.ret.198200 krimt |  | Strining Lot A- Elegect | 198200 | 198200 | 0 | 198200
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC13 | 13 | EMAAR- Pkg 140-ITP-Mivida13 | 1425866.3 | 1169767.915 | 149687.31 | 1319455.225
Beni Suef Substation R61 | BSF-CW-EURO-04 | 4 | Beni Suef Substation R614 | 196177.99 | 146152.6 | 29426.7 | 175579.3
Akhmem Assiut | Ref.Ret 3 assuit akh |  | Akhmem Assiut | 605789.54 | 601778 | 0 | 601778
Akhmem - Qena | Ref.Ret 2-3 Qena akh | 3 | Akhmem - Qena3 | 812733.22 | 807520 | 0 | 807520
Kuraiamte Lot1&2 | Ref.reten korimat |  | Kuraiamte Lot1&2 | 15000 | 15000 | 0 | 15000
Al-Wukair 11 Substation | 1905210010 |  | Al-Wukair 11 Substation | 366979.21 | 366979.21 | 0 | 366979.21
MAYSAN 400/132kV SS | 222 |  | MAYSAN 400/132kV SS | 154958.54 | 154958.54 | 0 | 154958.54
AWEER POWER STATION 'H' Phase | 10049 |  | AWEER POWER STATION 'H' Phase | 724555.2 | 1521472.3 | 0 | 760736.15
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 30 | 30 | Benban 500 K.V/95 K.M30 | 52220398.44 | 37261933.77 | 5483141.84 | 42745075.61
Elco Steel 220/33 KV SS | 1903210012 |  | Elco Steel 220/33 KV SS | 61593.9 | 64673.6 | 0 | 64673.6
Benban 500 K.V/95 K.M | Benban Lot2 Inv 16F$ | 16 | Benban 500 K.V/95 K.M16 | 4519011.34 | 3795620.54 | 409820.99 | 4205441.53
MAYSAN 400/132kV SS | 235 |  | MAYSAN 400/132kV SS | 2203500.54 | 2203500.54 | 0 | 2203500.54
Royal City | 20100006 |  | Royal City | 7597991.64 | 7075066.885 | 1423243.71 | 8498310.595
Canal Sugar S/s | Inv 4 $ Sugar S/s | 4 | Canal Sugar S/s4 | 1127442.46 | 860238.6 | 169116.37 | 1029354.97
Akhmem - Qena | Soc Inv 26 $ Quna T | 26 | Akhmem - Qena26 | 159039 | 157735.2 | 0 | 157735.2
Akhmem - Qena | Soc Inv .... Quana |  | Akhmem - Qena | 247339 | 247339 | 0 | 247339
Akhmem - Qena | Soc Inv ...Quana |  | Akhmem - Qena | 1249900 | 1249900 | 0 | 1249900
Suez IPB | 3*14 EGP- Suez Steel |  | Suez IPB | 14182.89 | 14182.89 | 0 | 14182.89
LAYYAH CCPP | 492 |  | LAYYAH CCPP | 2467647 | 2097499.95 | 370147.05 | 2467647
4 SS - Technical Service | 263 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
MAYSAN 400/132kV SS | 276 |  | MAYSAN 400/132kV SS | 419182.98 | 419182.98 | 0 | 419182.98
MOTHANA 400/132kV SS | 271 |  | MOTHANA 400/132kV SS | 656229.68 | 656229.68 | 0 | 656229.68
Akhmem - Qena | soc inv 48 labor Qua | 48 | Akhmem - Qena48 | 64345 | 64345 | 0 | 64345
Akhmem Assiut | Soc Inv 50 labor Asu | 50 | Akhmem Assiut50 | 63670.5 | 63670.5 | 0 | 63670.5
33KV Canal Farm Grid | Inv. 18 Farm | 18 | 33KV Canal Farm Grid18 | 1193427.22 | 0 | 179014.08 | 179014.08
Manshiet Nasser Substation | 1907210017 |  | Manshiet Nasser Substation | 2825453.4 | 3004138.18 | 0 | 3004138.18
Akhmem - Qena | Instill.Pay 5 Akhme2 |  | Akhmem - Qena | 310306.56 | 308124 | 0 | 308124
Siemens 6x500/220 KV GIS-MOU | Refund.Ret.Assuit |  | Siemens 6x500/220 KV GIS-MOU | 4388302.89 | 4383302.89 | 0 | 4383302.89
Latin Compound - New Alamin | inv ( 29 ) 30-9-21 | 29 | Latin Compound - New Alamin29 | 838474 | 14586.29 | 0 | 14586.29
MOTHANA 400/132kV SS | 274 |  | MOTHANA 400/132kV SS | 88777.26 | 88777.26 | 0 | 88777.26
Tamey El-amdeed Substation | TAM-CW-EGP-19 | 19 | Tamey El-amdeed Substation19 | 1066428.5 | 789157.08 | 159964.28 | 949121.36
AWEER POWER STATION 'H' Phase | 10267 |  | AWEER POWER STATION 'H' Phase | 301898 | 316992.9 | 0 | 316992.9
Cairo Capital Cables Tunnel | Tunnel Inv. 8 | 8 | Cairo Capital Cables Tunnel8 | 9223841.7 | 6115406.9 | 2305960.43 | 8421367.33
Beni Suef Add-on Sales | 518 |  | Beni Suef Add-on Sales | 7336866 | 8290658.58 | 0 | 8290658.58
Abu Ghazala Lock & Load | ABO GHZALA L&L-IPC01 | 1 | Abu Ghazala Lock & Load1 | 2200000 | 1459070 | 454462 | 1913532
Beni-Suef Power Plant EPC | Adj.1904210014 |  | Beni-Suef Power Plant EPC | 16897401.78 | 16897401.78 | 0 | 16897401.78
Manshiet Nasser Substation | 180166 |  | Manshiet Nasser Substation | 1438442.16 | 1351776.02 | 158588.25 | 1510364.27
Elco Steel 220/33 KV SS | 1903210005 |  | Elco Steel 220/33 KV SS | 190732.29 | 200268.9 | 0 | 200268.9
Elco Steel 220/33 KV SS | 1904210011 |  | Elco Steel 220/33 KV SS | 17518.63 | 18394.56 | 0 | 18394.56
Elco Steel 220/33 KV SS | 1901210002 |  | Elco Steel 220/33 KV SS | 723284.22 | 759448.43 | 0 | 759448.43
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 26 | 26 | Benban 500 K.V/95 K.M26 | 838750.91 | 646086.4 | 88068.85 | 734155.25
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .17 | 17 | Benban 3/ Toshka 2 LOT 417 | 2028697.87 | 1383175.4 | 213013.28 | 1596188.68
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $2 | 2 | Benban 3/ Toshka 2 LOT 42 | 1237182.5 | 1039025.81 | 129904.16 | 1168929.97
Royal City | ROYAL CITY- IPC0018 | 18 | Royal City18 | 9398674.2 | 4501953.51 | 2391545.92 | 6893499.43
New Giza 2 | NEW GIZA2-IPC FINAL |  | New Giza 2 | 3590050.37 | 2104161 | 0 | 2104161
SHAT Al ARAB 400/132kV SS | 298 |  | SHAT Al ARAB 400/132kV SS | 1441961.89 | 1441961.89 | 0 | 1441961.89
MOTHANA 400/132kV SS | 297 |  | MOTHANA 400/132kV SS | 721322.01 | 721322.01 | 0 | 721322.01
Zafranaa - Ras Ghareb | Inv. Ins10-1/15-12-3 | 1 | Zafranaa - Ras Ghareb1 | 558641.95 | 55475.98 | 0 | 56564.03
Manshiet Nasser Substation | 507 |  | Manshiet Nasser Substation | 648100.62 | 307367.77 | 0 | 307367.77
Tamey El-amdeed Substation | TAM-CALIM-01 | 1 | Tamey El-amdeed Substation1 | 5000000 | 4999415.55 | 0 | 4999415.55
marassi inland marina | IPC#2 | 2 | marassi inland marina2 | 1069424.13 | 267356.03 | 0 | 929929.96
Akhmem Assiut | So.22:25$assuit lot1 |  | Akhmem Assiut | 870270 | 870270 | 0 | 870270
Beni Seuf - 358 | Social Ins.Itay6/358 |  | Beni Seuf - 358 | 179941 | 179941 | 0 | 179941
Akhmem Assiut | Inv.22Assuit Akhmem$ | 22 | Akhmem Assiut22 | 818106.75 | 528417.337 | 0 | 528417.337
ESU Ph2-Enabling & Struc | ESU2-IPC7-ENABLE | 7 | ESU Ph2-Enabling & Struc7 | 9076073.5 | 3548357.425 | 2858963.1 | 6407320.525
Ismailiya East Substation | ISE-CW-EGP-22 | 22 | Ismailiya East Substation22 | 1460588 | 1153864.52 | 0 | 1153864.52
Beni Suef Add-on Sales | 2003210007 |  | Beni Suef Add-on Sales | 250125 | 277638.75 | 0 | 277638.75
Manshiet Nasser Substation | 501 |  | Manshiet Nasser Substation | 20726.78 | 7566.93 | 0 | 7566.93
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $1 | 1 | Benban 3/ Toshka 2 LOT 41 | 414484.03 | 348166.59 | 43520.82 | 391687.41
SHAT Al ARAB 400/132kV SS | 321 |  | SHAT Al ARAB 400/132kV SS | 225008.85 | 225008.85 | 0 | 225008.85
MAYSAN 400/132kV SS | 307 |  | MAYSAN 400/132kV SS | 138212.12 | 138212.12 | 0 | 138212.12
SHAT Al ARAB 400/132kV SS | 342 |  | SHAT Al ARAB 400/132kV SS | 118204.19 | 118204.19 | 0 | 118204.19
Abu Qir PP (CP-117) | 2003210011 |  | Abu Qir PP (CP-117) | 4875 | 4875 | 0 | 4875
Marsa Matrouh 500KV | Inv.68 Borg Alarab | 68 | Marsa Matrouh 500KV68 | 9614502.86 | 9407789.55 | 0 | 9407789.55
Katamia Dunes Villa | 10029 |  | Katamia Dunes Villa | 47667.26 | 2000 | 30000 | 32000
Marsa Matrouh 500KV | Inv.72 Borg Alarab | 72 | Marsa Matrouh 500KV72 | 2000875.6 | 1642720.75 | 0 | 1642720.75
LAYAN Substation | 10363 |  | LAYAN Substation | 200736 | 339243.84 | 0 | 169621.92
Miscellaneous Projects | 2005210011 |  | Miscellaneous Projects | 2779934.65 | 3141326.15 | 0 | 3141326.15
Baron Palace | 10197 |  | Baron Palace | 2548.48 | 2268.16 | 0 | 2268.16
Miscellaneous Projects | 2004210002 |  | Miscellaneous Projects | 6479.38 | 7321.7 | 0 | 7321.7
Multi Sport Hall | 10096 |  | Multi Sport Hall | 100370.35 | 89329.61 | 0 | 89329.61
R5 | inv(10)50720 | 10 | R510 | 934500 | 140175 | 0 | 871364.75
El Banna project | 442 |  | El Banna project | 1384734.8553 | 0 | 1384734.8553 | 1384734.8553
ESU Ph2-Enabling & Struc | EL.S.U.2-ENABLE-09* | 9 | ESU Ph2-Enabling & Struc9 | 222154.38 | 212579.529 | 0 | 212579.529
LRT - El Shorouk Bridge | IPC#2 | 2 | LRT - El Shorouk Bridge2 | 1168200 | 1047291.3 | 0 | 1047291.3
LRT - El Shorouk Bridge | IPC#1 | 1 | LRT - El Shorouk Bridge1 | 1118700 | 1002914.55 | 0 | 1002914.55
4 SS - Technical Service | 376 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
R5 | inv ( 11 ) | 11 | R511 | 1563000 | 78150 | 0 | 1419380.31
IKEA Extension MoA | IEKA2-MARAKZ-IPC01 | 1 | IKEA Extension MoA1 | 1325211.28 | 1264914.16 | 0 | 1264914.16
MAYSAN 400/132kV SS | 372 |  | MAYSAN 400/132kV SS | 483418.29 | 483418.29 | 0 | 483418.29
LRT - El Shorouk Bridge | IPC#4 | 4 | LRT - El Shorouk Bridge4 | 437580 | 386290.47 | 0 | 386290.47
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .12 | 12 | Benban 3/ Toshka 2 LOT 412 | 14409711.26 | 11686276.22 | 1513019.68 | 13199295.9
Governmental Campus-N2 | 26 |  | Governmental Campus-N2 | 2543859.68 | 0 | 2543859.68 | 2543859.68
El Zagazig Railway P2 | IPC#1 | 1 | El Zagazig Railway P21 | 489480 | 89750.4 | 0 | 89750.4
AWEER POWER STATION 'H' Phase | ENG/034 |  | AWEER POWER STATION 'H' Phase | 172442.17 | 181064.2785 | 0 | 181064.2785
MOTHANA 400/132kV SS | 390 |  | MOTHANA 400/132kV SS | 284952.79 | 284952.79 | 0 | 284952.79
Miscellaneous Projects | 2006210009 |  | Miscellaneous Projects | 8384.62 | 9306.9268 | 0 | 9306.9268
AWEER POWER STATION 'H' Phase | ENG/035 Rev0 |  | AWEER POWER STATION 'H' Phase | 105856.05 | 111148.8525 | 0 | 111148.8525
LRT Project | IPC_2_LRT | 2 | LRT Project2 | 136000 | 115124 | 0 | 115124
DoubleTree Mangroovy ElGouna | MANGROVERENT-IPC3 | 3 | DoubleTree Mangroovy ElGouna3 | 71250 | 74100 | 0 | 74100
Toshka-04 GIS Substation | Cre.adv. $ Toshka 4. |  | Toshka-04 GIS Substation | 0 | 0 | -11677.59 | -11677.59
Assuit PP (CP-118) | 2101210003 |  | Assuit PP (CP-118) | 165327.09 | 147554.42 | 26039.02 | 173593.44
MAYSAN 400/132kV SS | 393 |  | MAYSAN 400/132kV SS | 22225.68 | 22225.68 | 0 | 22225.68
West Port Said 220 kV GIS | P-45-Portsaid Inv.04 | 4 | West Port Said 220 kV GIS4 | 12362859.05 | 0 | 1298100.2 | 1298100.2
Sodic East | IPC_21_Rowad_Seast |  | Sodic East | 78423.4 | 69443.916 | 0 | 69443.916
ORA-ZED Towers01B | IPC_Ora_4 |  | ORA-ZED Towers01B | 132779.22 | 113990.96 | 0 | 113990.96
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 02 | 2 | Suez Gulf/S4 - 500KV OHTL2 | 1293439.8 | 1083630.81 | 135811.18 | 1219441.99
RING ROAD MARYOTIA EXPANSION | RING MARYOTUA-IPC04 | 4 | RING ROAD MARYOTIA EXPANSION4 | 4364397.86 | 3940994.49 | 0 | 3940994.49
Selwa 220 KV - 27 KM OHTL | Selwa OHTL Inv . 01 | 1 | Selwa 220 KV - 27 KM OHTL1 | 3353492.41 | 3423925.56 | 0 | 3423925.56
Zone(J) South Valley Toshka | South Valley Inv. 11 | 11 | Zone(J) South Valley Toshka11 | 70904705.85 | 52919426.25 | 9075802.35 | 61995228.6
Marazik Railway Bridge | IPC#1 Marazik | 1 | Marazik Railway Bridge1 | 208500 | 184558.32 | 0 | 184558.32
DoubleTree Mangroovy ElGouna | MANGROVE-IPC5B RENT | 5 | DoubleTree Mangroovy ElGouna5 | 3125 | 3187.5 | 0 | 3187.5
AWEER POWER STATION 'H' Phase | Eng/038 |  | AWEER POWER STATION 'H' Phase | 389425.46 | 408896.73 | 0 | 408896.73
MAYSAN 400/132kV SS | 402 |  | MAYSAN 400/132kV SS | 148556.58 | 148556.58 | 0 | 148556.58
Air Force Project | Air Force Inv . 08 | 8 | Air Force Project8 | 11311470.02 | 8098605.6 | 2827867.51 | 10926473.11
Asher Mn Ramadan Bridge No2 | alasher bridge-f+ |  | Asher Mn Ramadan Bridge No2 | 33000 | 33000 | 0 | 33000
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 12 | 12 | Hosh Essa 220 KV OHTL12 | 104897.12 | 0 | 11014.2 | 11014.2
SHAT Al ARAB 400/132kV SS | 408 |  | SHAT Al ARAB 400/132kV SS | 1526892.63 | 1526892.63 | 0 | 1526892.63
MOTHANA 400/132kV SS | 407 |  | MOTHANA 400/132kV SS | 129783.64 | 129783.64 | 0 | 129783.64
33KV Canal Farm Grid | Refund retention 01 |  | 33KV Canal Farm Grid | 4768632.85 | 4768632.85 | 0 | 4768632.85
TZ – Offshore E&M Procurement | 421 |  | TZ – Offshore E&M Procurement | 70670.23 | 70670.23 | 0 | 70670.23
ElMarg | IPC#2 - Marg | 2 | ElMarg2 | 49450 | 39555.5 | 0 | 39555.5
10Th of Ramadan LRT | LRT 10Ramadan Inv.05 | 5 | 10Th of Ramadan LRT5 | 1063082.52 | 0 | 106308.25 | 106308.25
Governmental Campus-N2 | 24 |  | Governmental Campus-N2 | 485707.7 | 485707.7 | 0 | 485707.7
4 SS - Technical Service | 419 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
AWEER POWER STATION 'H' Phase | LOC/016 |  | AWEER POWER STATION 'H' Phase | 1811602.76 | 1590184.64 | 201289.2 | 1791473.84
Air Force Project | Air Force Inv . 11 | 11 | Air Force Project11 | 6851572.16 | 4905315 | 1712893.05 | 6618208.05
El Ameed 220 KV | Ref.Ret ELAmeed |  | El Ameed 220 KV | 39500 | 39500 | 0 | 39500
CFC Podium 2 | CFC IPC025 | 25 | CFC Podium 225 | 13190112.67 | 9682524.4635 | 0 | 9682524.4635
RING ROAD MARYOTIA EXPANSION | El-Marg IPC07 | 7 | RING ROAD MARYOTIA EXPANSION7 | 6420256.71 | 1787764.23 | 0 | 5787764.23
Benban 500 K.V/95 K.M | Ret Benban Lot 2 T |  | Benban 500 K.V/95 K.M | 11755279.89 | 11755279.89 | 0 | 11755279.89
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.08 | 8 | Toshka 2/Owinat East LOT2 OHTL8 | 2074893.94 | 1533989.24 | 217863.86 | 1751853.1
DRCC | Credit Memo DRCC |  | DRCC | 0 | 0 | -113.49 | -113.49
33KV Canal Farm Grid | Ref.2 sugar Farm T |  | 33KV Canal Farm Grid | 6831156.24 | 6831156.24 | 0 | 6831156.24
Benban 500 K.V/95 K.M | Ref.3 benban Lot 2 T |  | Benban 500 K.V/95 K.M | 10000000 | 10000000 | 0 | 10000000
Akhmem - Qena | Ref.8 Akhme Quana T |  | Akhmem - Qena | 10000000 | 10000000 | 0 | 10000000
NUCA R05 - Z02 | R05 IPC029 | 29 | NUCA R05 - Z0229 | 1322169.7 | 898252.5 | 115012 | 1013264.5
Sokhna Port Expansion | sokhna port ex ipc10 | 10 | Sokhna Port Expansion10 | 39642891.35 | 27461819.55 | 7928578.26 | 35390397.81
158E/2019 33kv Project | 11062 |  | 158E/2019 33kv Project | 104000 | 109200 | 0 | 109200
Air Force Project | Air Force Inv . 21 | 21 | Air Force Project21 | 4593369.44 | 4436962 | 0 | 4436962
Ring Road Bridges Project | INV ( 7 ) Ring R | 7 | Ring Road Bridges Project7 | 4235172 | 3553200.32 | 0 | 3553200.32
TZ – Offshore E&M Procurement | 472 |  | TZ – Offshore E&M Procurement | 78872.94 | 0 | 15774.59 | 15774.59
TZ – Offshore E&M Procurement | 463 |  | TZ – Offshore E&M Procurement | 86394.34 | 8056.76 | 0 | 8056.76
Benban 500 K.V / 100 K.M | رد تامين بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 10000000 | 10000000 | 0 | 10000000
PLAYA ROOF & Wet Areas | IPC-1-PLAYA ROOF | 1 | PLAYA ROOF & Wet Areas1 | 465527.7 | 399466.31 | 0 | 399466.31
Taval Sarai 52 | IPC-16-SARAY | 16 | Taval Sarai 5216 | 31911.3 | 27447.1702 | 0 | 27447.1702
Egyptian Exchange building | IPC-2-BORSA | 2 | Egyptian Exchange building2 | 157350.13 | 139333.53 | 0 | 139333.53
seashell Playa | IPC-11-PLAYA | 11 | seashell Playa11 | 151371.6 | 105672.51 | 24219.46 | 129891.97
Ain Sokhna Port Development | IPC#7 Sokhna Port | 7 | Ain Sokhna Port Development7 | 1426672 | 1101390.78 | 0 | 1341071.68
New Babil 400/132KV GIS Substa | 2201210002 |  | New Babil 400/132KV GIS Substa | 461933.6 | 461933.6 | 0 | 461933.6
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.01 | 1 | 10th Ramadan Indu Park Plot111 | 6065851.81 | 4179371.89 | 955371.66 | 5134743.55
Cairo-Alex Railway | cairo-alex ipc16 | 16 | Cairo-Alex Railway16 | 26294302.62 | 18095195.25 | 2760901.78 | 20856097.03
Racecores 3092-17 132KV E | 11368 |  | Racecores 3092-17 132KV E | 701153.6942 | 3554849.22 | 0 | 592474.87
Ghana Street lighting | MIDA Ins. Inv.10 | 10 | Ghana Street lighting10 | 12865.6 | 11579.04 | 0 | 11579.04
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 17 | 17 | Suez Gulf/S4 - 500KV OHTL17 | 814311.61 | 245883.04 | 0 | 245883.04
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 12 | 12 | Suez Gulf/S4 - 500KV OHTL12 | 1597816.61 | 463592.36 | 0 | 463592.36
Mivida BP#189 | PKG#189 IPC 30 | 30 | Mivida BP#18930 | 22415427.41 | 14412191.1105 | 2417376.75 | 16829567.8605
National Batteries LP-05-20 | 38 |  | National Batteries LP-05-20 | 2412280.71 | 2750000.01 | 0 | 2750000.01
El Mostakbal City Project | Inv. 15 Mostakbal | 15 | El Mostakbal City Project15 | 117317404.76 | 37374677.67 | 21472965.19 | 58847642.86
El Khatatba Bridge | EL KHATATBA IPC02 | 2 | El Khatatba Bridge2 | 2437694.05 | 1381244.0525 | 0 | 1381244.0525
Aljazi Project | Al - Jazi Inv. 3 | 3 | Aljazi Project3 | 121070 | 58174.3 | 0 | 58174.3
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv13 | 13 | Marsa Alam/ Bernes LOT2 OHTL13 | 228072.6 | 205215.78 | 0 | 205215.78
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 9 | 9 | Marsa Alam/ Bernes LOT2 OHTL9 | 62479.21 | 55854.37 | 0 | 55854.37
Selwa / New Isna 220KV OHTL | Selwa - Isna Inv. 01 | 1 | Selwa / New Isna 220KV OHTL1 | 2177093.48 | 2015950.57 | 0 | 2015950.57
HST Bridges-Sokhna & Mahager | SOKHNA BRIDGE IPC03 | 3 | HST Bridges-Sokhna & Mahager3 | 4418251.43 | 4374068.9215 | 0 | 4374068.9215
Ain Sokhna Port Development | IPC#16 - Sokhna Port | 16 | Ain Sokhna Port Development16 | 246924 | 185420.68 | 0 | 231775.85
Assuit PP (CP-118) | 220721006 |  | Assuit PP (CP-118) | 1365739.79 | 1400586.7175 | 33401.06 | 1433987.7775
SSC Suez Steel Company Project | in&reSupply-SSC IPC2 | 2 | SSC Suez Steel Company Project2 | 3765789.87 | 3190884.0818 | 1064458.47 | 4255342.5518
SSC Suez Steel Company Project | In&ReApply(SSC)-IPC1 | 1 | SSC Suez Steel Company Project1 | 1124419.48 | 1102291.6272 | 145814 | 1248105.6272
Marassi Epoxy | TR0047-IPC00001 | 1 | Marassi Epoxy1 | 83820 | 71925.94 | 0 | 71925.94
CS-20 Mall | inv ( 14 ) CS-20 | 14 | CS-20 Mall14 | 67848.81 | 63777.88 | 0 | 63777.88
CS-20 Mall | inv ( 12 ) CS-20 | 12 | CS-20 Mall12 | 376497.27 | 150598.91 | 0 | 150598.91
Kattameya Creeks | Kattameya IPC20 | 20 | Kattameya Creeks20 | 25275496.94 | 24429045.007 | 1857471.81 | 26286516.817
EGAT Pelletizing Plant | Plant supply Ro ipc3 | 3 | EGAT Pelletizing Plant3 | 11779040 | 1531275.2 | 11779040 | 13310315.2
RING ROAD MARYOTIA EXPANSION | ipc23 el maryotia | 23 | RING ROAD MARYOTIA EXPANSION23 | 1935881.9 | 1673762.43 | 0 | 1673762.43
Ministries Buildings | Mini Core IPC10 | 10 | Ministries Buildings10 | 6320819 | 5324885 | 0 | 5324885
EGAT Pelletizing Plant | EGAT watertank IPC13 | 13 | EGAT Pelletizing Plant13 | 376223.99 | 391272.9495 | 0 | 391272.9495
New Giza Hospital | IPC005RMENEWGIZAHOSP | 5 | New Giza Hospital5 | 36839.36 | 30804.8 | 0 | 30804.8
Mivida BP#189 | PKG#189- IPC (15) | 15 | Mivida BP#18915 | 18379426.48 | 20013901.014 | 4268668.94 | 24282569.954
Abou Ghaleb Bridge | abo ghaleb ipc04 | 4 | Abou Ghaleb Bridge4 | 2545336.5 | 2519883.145 | 0 | 2519883.145
Get Business Complex | INV ( 18 ) GET | 18 | Get Business Complex18 | 298864.75 | 59772.95 | 0 | 59772.95
Creeks URBN-K | Katamya Urbnk ipc14 | 14 | Creeks URBN-K14 | 7646354.5 | 6223872.155 | 1152224.35 | 7376096.505
RING ROAD MARYOTIA EXPANSION | Mariotya ipc 19 | 19 | RING ROAD MARYOTIA EXPANSION19 | 2168187.95 | 1876305.07 | 0 | 1876305.07
MDF Factory | MDF3 - IPC9 | 9 | MDF Factory9 | 2622768.25 | 1901506.985 | 747488.95 | 2648995.935
EGAT Injection | IPC00003 | 3 | EGAT Injection3 | 43330.5 | 37181.9 | 0 | 37181.9
Air Defence College | IPC#005 air defense | 5 | Air Defence College5 | 211750.14 | 179775.86 | 0 | 179775.86
Egyptian Exchange building | IPC09-Exchange RME | 9 | Egyptian Exchange building9 | 96748.76 | 85671.02 | 0 | 85671.02
Business District Hyde Park | INV ( 3 ) HY Bark | 3 | Business District Hyde Park3 | 347415 | 296692.41 | 0 | 296692.41
Business District Hyde Park | INV ( 2 ) HY Bark | 2 | Business District Hyde Park2 | 1127787 | 963130.1 | 0 | 963130.1
PLAYA ROOF & Wet Areas | IPC0000016 | 16 | PLAYA ROOF & Wet Areas16 | 40852.24 | 35055.31 | 0 | 35055.31
PLAYA ROOF & Wet Areas | IPC0019 | 19 | PLAYA ROOF & Wet Areas19 | 264385.95 | 226869.57 | 0 | 226869.57
Expansion of Ring Road-CFA | IPC 3 CFA | 3 | Expansion of Ring Road-CFA3 | 169935 | 150000 | 0 | 150000
DP World Basin 2 Ph2 | DP World ph.2-IPC 1 | 1 | DP World Basin 2 Ph21 | 24448993.55 | 21759604.25 | 0 | 21759604.25
MDF Factory | MDF 2 - IPC 13 | 13 | MDF Factory13 | 478450.77 | 483235.2778 | 0 | 483235.2778
Ministries Buildings | Minis MEP IPC7 | 7 | Ministries Buildings7 | 177952479 | 118055250 | 0 | 118055250
MDF Factory | MDF 3 IPC( 11) | 11 | MDF Factory11 | 1606948.05 | 1123017.527 | 500000 | 1623017.527
Air Defense College | Air sihi IPC1 | 1 | Air Defense College1 | 4288332 | 1280760 | 2300000 | 3580760
PLAYA ROOF & Wet Areas | IPC0021 TR41 | 21 | PLAYA ROOF & Wet Areas21 | 132780.21 | 113938.19 | 0 | 113938.19
EMAAR-Pkg#162/163- Marassi | EMaarPKG#177 IPC 43 | 43 | EMAAR-Pkg#162/163- Marassi43 | 15896560.84 | 15323561.672 | 0 | 15323561.672
SEASHELL TECHNICAL ROOM | IPC04 TR65 | 4 | SEASHELL TECHNICAL ROOM4 | 3974.32 | 3432.22 | 0 | 3432.22
U3 & U5 | IPC10 TR55 | 10 | U3 & U510 | 21350.8 | 18438.55 | 0 | 18438.55
HST El Mahager Bridge | ipc 3 elmahager | 3 | HST El Mahager Bridge3 | 7054473.33 | 6250171.5 | 0 | 6250171.5
Seashell Playa 5 Villas | playa c104- ipc 7 | 7 | Seashell Playa 5 Villas7 | 279706.62 | 232507.66 | 0 | 232507.66
Marassi - Water proofing | IPC 3 TR0044 | 3 | Marassi - Water proofing3 | 45658.84 | 35430.91 | 0 | 35430.91
Marassi - Anti carbonation | IPC003 TR43 | 3 | Marassi - Anti carbonation3 | 59705.1 | 17868.86 | 0 | 17868.86
Olympic City Lock&Load | Olympic L&L IPC1 | 1 | Olympic City Lock&Load1 | 3638578 | 3022610 | 0 | 3022610
EGAT Pelletizing Plant | egat P supply ipc 1 | 1 | EGAT Pelletizing Plant1 | 1390180.04 | 1570903.4452 | 0 | 1570903.4452
DP World Basin 2 Ph2 | Dp World ph2 ipc(6) | 6 | DP World Basin 2 Ph26 | 32175841.3 | 23809772.84 | 4826376.19 | 28636149.03
MDF Factory | mdf 2 ipc (17) | 17 | MDF Factory17 | 614911.7 | 536737.62 | 0 | 536737.62
British International School | BIS IPC (3) | 3 | British International School3 | 11138109 | 10414131.92 | 0 | 10414131.92
DP World Basin 2 Ph2 | DP world ipc (5) | 5 | DP World Basin 2 Ph25 | 40682207.5 | 30104833.54 | 6102331.12 | 36207164.66
British International School | Bis ipc ( 2) | 2 | British International School2 | 8895320.4 | 4500000 | 0 | 4500000
Tarek Abdel-Hakim Center | TAH ipc08 | 8 | Tarek Abdel-Hakim Center8 | 3071127.97 | 2363232.97 | 276401.52 | 2639634.49
26th of July Corridor New | IPC 1 26th july | 1 | 26th of July Corridor New1 | 612000 | 525157.2 | 0 | 525157.2
Borg El Arab Bridge - Km 21 | IPC#03 Kilo 21 | 3 | Borg El Arab Bridge - Km 213 | 153140 | 143951.6 | 0 | 143951.6
El-Herafeen brigde | IPC#1 Credit | 1 | El-Herafeen brigde1 | -18585 | -18585 | 0 | -18585
Ameria | 310321 |  | Ameria | -120000 | -120000 | 0 | -120000
Seashell Playa 5 Villas | Playa c104 ipc 8 | 8 | Seashell Playa 5 Villas8 | 731710.17 | 522023.35 | 0 | 522023.35
Seashell Playa 5 Villas | PLAYA - C072 IPC 3 | 3 | Seashell Playa 5 Villas3 | 93725.55 | 65948.14 | 0 | 65948.14
U4,U8 Seashell Playa | IPC10TR0060 | 10 | U4,U8 Seashell Playa10 | 31445.08 | 27155.97 | 0 | 27155.97
Mohamed Ali Palace Restoration | MOHAMED ALY2 FINAL |  | Mohamed Ali Palace Restoration | 271501.23 | 255350 | 0 | 255350
KATAMYA GREEKS LAND SCAPE STAR | IPC02TR0081 | 2 | KATAMYA GREEKS LAND SCAPE STAR2 | 1470429.19 | 1453666.51 | 0 | 1453666.51
Sultana Malak Restoration | sultana malak ipc03 | 3 | Sultana Malak Restoration3 | 1079127.29 | 282361.25 | 677115 | 959476.25
Air Defense College | Air dev shabkat IPC2 | 2 | Air Defense College2 | 5675439 | 4781150 | 0 | 4781150
Venice Mall | inv ( 2 ) vensia | 2 | Venice Mall2 | 58480 | 52047.2 | 0 | 52047.2
EIPICO C002-23 | IPC0001 TR68 | 1 | EIPICO C002-231 | 106044.19 | 90996.52 | 0 | 90996.52
Quarry Bridge | inv ( 1 ) MAHGER Br | 1 | Quarry Bridge1 | 4110000 | 810561 | 0 | 810561
SSC Suez Steel Company Project | Baraka Fence ipc 5 | 5 | SSC Suez Steel Company Project5 | 7617134 | 0 | 2285140.2 | 2285140.2
Seashell Playa 5 Villas | playa-c045 ipc 5 | 5 | Seashell Playa 5 Villas5 | 20694.48 | 17871.75 | 0 | 17871.75
Olympic MultiSport Hall | IPC01TR0079 | 1 | Olympic MultiSport Hall1 | 49280 | 41469.12 | 0 | 41469.12
Ora Zed -Landscape | IPC002 TR70 | 2 | Ora Zed -Landscape2 | 43452.13 | 32464.11 | 0 | 32464.11
Seashell Playa 5 Villas | Playa-c038 ipc 9 | 9 | Seashell Playa 5 Villas9 | 33072.33 | 28561.17 | 0 | 28561.17
Katameya Creeks - RME | IPC14TR0053 | 14 | Katameya Creeks - RME14 | 10371.46 | 9183.94 | 0 | 9183.94
Katameya Creeks - RME | IPC10 TR53 | 10 | Katameya Creeks - RME10 | 12213.55 | 10815.1 | 0 | 10815.1
EIPICO Factory | IPC003 TR54 | 3 | EIPICO Factory3 | 34283.4 | 29418.58 | 0 | 29418.58
SOL Town PKG.220 | pkg#220- ipc 4 | 4 | SOL Town PKG.2204 | 1274131.45 | 1849642.29 | 0 | 1849642.29
SSC Suez Steel Company Project | Revamp ipc 8 | 8 | SSC Suez Steel Company Project8 | 2887080.34 | 1992085.4336 | 866124.1 | 2858209.5336
Irrigation Tank | IPC06TR0061 | 6 | Irrigation Tank6 | 289444.8 | 249964.53 | 0 | 249964.53
U7-SEASHELL | IPC14TR0064 | 14 | U7-SEASHELL14 | 62375.6 | 53867.56 | 0 | 53867.56
AIRDEFNSE -EPOXY | IPC08TR0066 | 8 | AIRDEFNSE -EPOXY8 | 104010.4 | 88304.83 | 0 | 88304.83
MDF Factory | mdf local ipc 17 | 17 | MDF Factory17 | 791.23 | 799.1422 | 0 | 799.1422
U4,U8 Seashell Playa | IPC12TR0060 | 12 | U4,U8 Seashell Playa12 | 724900 | 574873.65 | 0 | 574873.65
Abou Ghaleb Bridge | ABO GHALEB ESC 1:11 |  | Abou Ghaleb Bridge | 3359523.81 | 3244903.17 | 0 | 3244903.17
Seashell Playa 5 Villas | Playa-c470 ipc 1 | 1 | Seashell Playa 5 Villas1 | 215083.62 | 185746.2 | 0 | 185746.2
Wady El Natroon Bridge | wady elnatron ipc9 | 9 | Wady El Natroon Bridge9 | 9721357.14 | 8667165 | 0 | 8667165
Sokhna Port Expansion | SPX INT.ROADS2 FINAL |  | Sokhna Port Expansion | 56070.14 | 3219.75 | 0 | 3219.75
MDF Factory | MDf Local ipc 19 | 19 | MDF Factory19 | 4087720.52 | 3358613 | 0 | 3358613
RING ROAD MARYOTIA EXPANSION | mariotya esc 1:22 es |  | RING ROAD MARYOTIA EXPANSION | 1247325.71 | 1204519.8 | 0 | 1204519.8
Seashell Playa 5 Villas | Playa c469 - ipc 2 | 2 | Seashell Playa 5 Villas2 | 297812.93 | 272081.89 | 0 | 272081.89
U7-SEASHELL | IPC21TR0064 | 21 | U7-SEASHELL21 | 633528.25 | 500000 | 0 | 500000
Open Channal | IPC06TR0074 | 6 | Open Channal6 | 332096.32 | 286466.28 | 0 | 286466.28
Olympic MultiSport Hall | IPC03TR0079 | 3 | Olympic MultiSport Hall3 | 40252.8 | 33872.73 | 0 | 33872.73
Ora Zed Landscape Ph1 | Ora landscape-IPC18 | 18 | Ora Zed Landscape Ph118 | 1175128.22 | 975356.43 | 123388.46 | 1098744.89
SSC Suez Steel Company Project | V.O Smp2 ipc 1 | 1 | SSC Suez Steel Company Project1 | 1132829 | 1121500.71 | 0 | 1121500.71
Senator | Inv ( 3 ) Sentor | 3 | Senator3 | 153232 | 83000 | 0 | 83000
Rabigh PP - Piling Works | Inv-04 | 4 | Rabigh PP - Piling Works4 | 1553962.12 | 5361169.32 | 0 | 1787056.44
Roof-Playa Cluster A,B,C | IPC09TR0088 | 9 | Roof-Playa Cluster A,B,C9 | 371928.37 | 321197.34 | 0 | 321197.34
Al-Parco | INV ( 10 ) ALparco | 10 | Al-Parco10 | 2205121.51 | 241095.43 | 0 | 241095.43
ORA-ZED Towers P01B | IPC15TR0051 | 15 | ORA-ZED Towers P01B15 | 143352.86 | 126936.46 | 0 | 126936.46
Open Channal | IPC07TR0074 | 7 | Open Channal7 | 125000 | 107825 | 0 | 107825
Roof-Playa Cluster A,B,C | IPC10TR0088 | 10 | Roof-Playa Cluster A,B,C10 | 534780.49 | 393479.26 | 0 | 393479.26
U4,U8 Seashell Playa | IPC18TR0060 | 18 | U4,U8 Seashell Playa18 | 284793.15 | 216564.36 | 0 | 216564.36
Katameya Creeks - RME | IPC24TR0053 | 24 | Katameya Creeks - RME24 | 800341.7 | 708702.08 | 0 | 708702.08
Open Channal | IPC03TR0074 | 3 | Open Channal3 | 110592 | 95396.66 | 0 | 95396.66
U4,U8 Seashell Playa | IPC19TR0060 | 19 | U4,U8 Seashell Playa19 | 697767.53 | 568772.71 | 0 | 568772.71
Roof-Playa Cluster A,B,C | IPC11TR0088 | 11 | Roof-Playa Cluster A,B,C11 | 1087452.41 | 925073.9 | 0 | 925073.9
Seashell Playa 5 Villas | Playa c470 ipc 6 | 6 | Seashell Playa 5 Villas6 | 54184.3 | 46793.55 | 0 | 46793.55
Kemet Tower | INV(10 final ) Kemet | 10 | Kemet Tower10 | 112800 | 96793.68 | 0 | 96793.68
JICA lot 02 | JICA lot 02 Inv. 01 | 1 | JICA lot 021 | 29289728.56 | 0 | 0 | #DIV/0!
RING ROAD MARYOTIA EXPANSION | crMaryotya IPC06 | 6 | RING ROAD MARYOTIA EXPANSION6 | -2460952.38 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | IPC# FINAL SUHAG |  | Elmaragha Bridge - Sohag | 346077.5 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | 10001 |  | Abo Quir - Badr 500KV | 34370.43 | 0 | 0 | #DIV/0!
Celia | IPC#006CR | 6 | Celia6 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 33 |  | Suez Gulf Substation | 2735633.8944 | 0 | 0 | #DIV/0!
MDF Factory | CR-MDF IPC13 | 13 | MDF Factory13 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | CR.Al Lahoon Inv 01 | 1 | Lahoon 220/22/221 | 0 | 0 | 0 | #DIV/0!
ORA ZED-Ph 2-Pkgs A&D | cr-ora zed2 ipc16 | 16 | ORA ZED-Ph 2-Pkgs A&D16 | 0 | 0 | 0 | #DIV/0!
LP-07-21 Petrojet | 82 |  | LP-07-21 Petrojet | 28249911.55 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10171 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
Palm Hill-Infra Str(Elec.Work) | DEC ADJ 107 |  | Palm Hill-Infra Str(Elec.Work) | 0 | 0 | 0 | #DIV/0!
Sewage Treatment Plant | IPC#4&5 | 4 | Sewage Treatment Plant4 | 1257865 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | Adjust 180177 |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
Royal City | Cr Royal fin ipc43 | 43 | Royal City43 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11453 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
LP-18-21 ODP Passive & DC | 97 |  | LP-18-21 ODP Passive & DC | 2790163.2473 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Assuit Inv.2 ded | 2 | Assuit PP (CP-118)2 | 1172138.01 | 2344276.02 | 0 | 2344276.02
W Dam PP Phase II (CP-117) | 262 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Infra Project 4428 | 220621007 |  | Infra Project 4428 | 285714285.72 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cr.90 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Inv.27&28 ded. | 27 | South Helwan PP (CP-117)27 | 0 | 0 | 0 | #DIV/0!
Benban 500 K.V/95 K.M | CR.Ref-Ret-Benban2 |  | Benban 500 K.V/95 K.M | 0 | 0 | 0 | #DIV/0!
C5 Bridge 2 New Alamein | D0011-OB-Dec-2020/Cr | 2020 | C5 Bridge 2 New Alamein2020 | 0 | 0 | 0 | #DIV/0!
EGAT Pelletizing Plant | CR ELCO EGAT IPC17 | 17 | EGAT Pelletizing Plant17 | 0 | 0 | 0 | #DIV/0!
El-Warraq | IPC#FINAL#El-Warraq |  | El-Warraq | 984000 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 264 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 94 |  | FX-01-22 Decent Life-WD | 76178.17 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj 180119-180120 | 180120 | Beni-Suef Power Plant EPC180120 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 18 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 293419.819 | 0 | 0 | #DIV/0!
TOSHKA MADKOUR | C.1 |  | TOSHKA MADKOUR | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref Akhmm Asuit4T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Beni Suef ISKRA | 1907220005 |  | Beni Suef ISKRA | 0 | 0 | 0 | #DIV/0!
ORA ZED - Ph 01B - Pkgs A&D | Ora Zed ipc 38 M | 38 | ORA ZED - Ph 01B - Pkgs A&D38 | 3482324.82 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 4 EUR - South Helwan |  | South Helwan PP (CP-117) | 504604.0762 | 0 | 0 | #DIV/0!
Haramein Columns Transfer | cr-haramin ipc01 | 1 | Haramein Columns Transfer1 | 0 | 0 | 0 | #DIV/0!
Port Said | Cr Adj Inv 8 Final | 8 | Port Said8 | 0 | 0 | 0 | #DIV/0!
Cameron EDC | 5007 Credit |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Residence 8 ( S09 ) | Cr.Inv ( 1 ) S09 | 1 | Residence 8 ( S09 )1 | 0 | 0 | 0 | #DIV/0!
LRT - El Shorouk Bridge | D0034-OB-Dec-2020/Cr | 2020 | LRT - El Shorouk Bridge2020 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref Akhmm Asuit5T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Residence 8 ( K10 ) | Cr.Inv ( 2 ) K 10 | 2 | Residence 8 ( K10 )2 | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-KAFR SHOKR2 |  | Kafr Shokr Bridge | 0 | 0 | 0 | #DIV/0!
Celia | CR-IPC#2 | 2 | Celia2 | 0 | 0 | 0 | #DIV/0!
Port Said | Cr. Inv. 8 Bortsaid | 8 | Port Said8 | 0 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Inv.18 - Lot 1 | 18 | Mauritania Lot 118 | 117062 | 0 | 0 | #DIV/0!
SSC Suez Steel Company Project | L967/2024 |  | SSC Suez Steel Company Project | 7476526 | 0 | 0 | #DIV/0!
U3 & U5 | IPC007TR55 | 7 | U3 & U57 | 44347.28 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | DEC ADJ 23 |  | Giza North PP Phase3(CP-117) | 342523.91 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR- 16 EGP - West D. | 16 | W Dam PP Phase II (CP-117)16 | 0 | 0 | 0 | #DIV/0!
Seashell Playa 5 Villas | CRseashell playaIPC1 | 1 | Seashell Playa 5 Villas1 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10428 |  | AWEER POWER STATION 'H' Phase | 1065842.99 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 220722001 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Hosh Eisa Hospit. | can. IPC01TR0089 | 1 | Hosh Eisa Hospit.1 | 0 | 0 | 0 | #DIV/0!
Berket Ghelion | RE 18 |  | Berket Ghelion | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR- 8 USD- Shabab | 8 | Al-Shabab PP Phase II (CP-117)8 | 0 | 0 | 0 | #DIV/0!
Ain-Sokhna PP (CP-111) | close client |  | Ain-Sokhna PP (CP-111) | 0 | 0 | 0 | #DIV/0!
RING ROAD MARYOTIA EXPANSION | cr mariotya esc.19es |  | RING ROAD MARYOTIA EXPANSION | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 11 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 434762.5333 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 23 ) GET | 23 | Get Business Complex23 | 208126.81 | 0 | 0 | #DIV/0!
ZED Phase 2 | IPC12TR0062 | 12 | ZED Phase 212 | 19091.11 | 0 | 0 | #DIV/0!
Attaqa Power Plant | Discount interest |  | Attaqa Power Plant | 0 | 0 | 0 | #DIV/0!
EL -mahager Bridge Ain sokhna | 2 |  | EL -mahager Bridge Ain sokhna | 0 | 0 | 0 | #DIV/0!
HAC CCC JV | D0008-OB-Dec-2020/Cr | 2020 | HAC CCC JV2020 | 0 | 0 | 0 | #DIV/0!
Port Said Port Silos | cr-port said1-supply |  | Port Said Port Silos | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180081 |  | Suez Gulf Substation | 17815.17 | 0 | 0 | #DIV/0!
Open Channal | C.ipc01 | 1 | Open Channal1 | 0 | 0 | 0 | #DIV/0!
R05 | CR-IPC_1_R5 |  | R05 | 0 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | Inv. No. 3 - intrest | 3 | Angola Emergency fast-track3 | 23797596.41 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 303 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
JICA lot 02 | JICA lot 02 Inv.$ 01 |  | JICA lot 02 | 2067501.12 | 0 | 0 | #DIV/0!
Banha PP (CP-118) | DEC ADJ 11 |  | Banha PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | Cr-م 10 كفر شكر | 10 | Kafr Shokr Bridge10 | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | CR Samanoud 5 inv.81 | 81 | Abou El Matameer and Sammanoud81 | 0 | 0 | 0 | #DIV/0!
Wadi El Natroun | D0014-OB-Dec-2020/Cr | 2020 | Wadi El Natroun2020 | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial P - East | Inv. 17 Fin PIP EAST | 17 | Pyramids Industrial P - East17 | 5689276.96 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2007220003 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2011220006 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Museum of Egyp. Civilization | CR-IPC#4 | 4 | Museum of Egyp. Civilization4 | 0 | 0 | 0 | #DIV/0!
East Owainat | 15 |  | East Owainat | -11517.22 | 0 | 0 | #DIV/0!
PIP West 2 | Cr Adj inv 2 | 2 | PIP West 22 | 0 | 0 | 0 | #DIV/0!
DRCC | P-44-EGY اتحاد تشيد | 44 | DRCC44 | 5000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 92 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2009220001 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR1IPC_5_Gama_Saray |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Soc.2020 تشيد مرسى |  | Marsa Alam/ Bernes LOT2 OHTL | 5000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 85 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 65 |  | Al-Shabab PP Phase II (CP-117) | 19158118.26 | 0 | 0 | #DIV/0!
Kayan 3 New Cairo Capital City | OB-RE-EL Kayaan |  | Kayan 3 New Cairo Capital City | 6017614.8 | 0 | 0 | #DIV/0!
Benban 500 K.V/95 K.M | CR.2 benban Lot 2 |  | Benban 500 K.V/95 K.M | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 63 |  | Al-Shabab PP Phase II (CP-117) | -7373940.95 | 0 | 0 | #DIV/0!
Zambia | CR.P-2-10 AccRev | 2 | Zambia2 | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2008220004 |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
EL Sewedy University Tec. | CR-INV ( 2 ) S.UNIV | 2 | EL Sewedy University Tec.2 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | Cr.IPC_5_Gama_salary |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR-19 EGP- Shabab | 19 | Al-Shabab PP Phase II (CP-117)19 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | cr Soc inv 48 As | 48 | Akhmem Assiut48 | 0 | 0 | 0 | #DIV/0!
Expansion of Ring Road-CFA | IPC#4 CFA | 4 | Expansion of Ring Road-CFA4 | 377421.5 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | ANG-Cam-Inv 4 - part | 4 | Angola Emergency fast-track4 | 16100 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply.Inv.2Ret. | 2 | Ghana Street lighting2 | 71126.5 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 48 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 29 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Open Channel 2 | C.INV.2 | 2 | Open Channel 22 | 0 | 0 | 0 | #DIV/0!
FX-05-22 Close compound | 95 |  | FX-05-22 Close compound | 199533.21 | 0 | 0 | #DIV/0!
LAYAN Substation | 11520 |  | LAYAN Substation | 0 | 0 | 0 | #DIV/0!
Museum of Egyp. Civilization | D0027-OB-Dec-2020/Cr | 2020 | Museum of Egyp. Civilization2020 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 82 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | IPC#22 CR | 22 | El Boghaz Brigde22 | 0 | 0 | 0 | #DIV/0!
Sokhna Port Expansion | cr-SPX ROADS 2 FINAL |  | Sokhna Port Expansion | 0 | 0 | 0 | #DIV/0!
Mauritania-Lot 2 | Inv.6 – Lot 2 RDC | 6 | Mauritania-Lot 26 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr. Amend - Ras Gha |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 250 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Residence 8 ( S05 ) | Cr . Inv ( 1 ) S 05 | 1 | Residence 8 ( S05 )1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 11 USD- Shabab | 11 | Al-Shabab PP Phase II (CP-117)11 | 0 | 0 | 0 | #DIV/0!
Ain-Sokhna PP(CP-102) | 2104220006 |  | Ain-Sokhna PP(CP-102) | 0 | 0 | 0 | #DIV/0!
Sultana Malak Restoration | Sultana mlk22 2final |  | Sultana Malak Restoration | 5285834.29 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR Akhmem Asuit3T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | DEC ADJ 66 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2009220004 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
PIP Zona 2 | Cr Adj inv 1 | 1 | PIP Zona 21 | 0 | 0 | 0 | #DIV/0!
LP-22-21 ECMEI–6000–RFID | 55 |  | LP-22-21 ECMEI–6000–RFID | 33180 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,4 usd Borg Ar | 4 | Marsa Matrouh 500KV4 | 0 | 0 | 0 | #DIV/0!
U7-SEASHELL | CANCEL IPC12 | 12 | U7-SEASHELL12 | 0 | 0 | 0 | #DIV/0!
PLAYA ROOF & Wet Areas | Credut Memo IPC00015 | 15 | PLAYA ROOF & Wet Areas15 | 0 | 0 | 0 | #DIV/0!
EPICO 3 Facility | CR Material ipc3 | 3 | EPICO 3 Facility3 | 0 | 0 | 0 | #DIV/0!
Al-Wukair 11 Substation | Cr.Memo-Expenses. |  | Al-Wukair 11 Substation | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 9 |  | Zafranaa - Beni Suef | 79487.99 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Inv.6&7 Deductions | 6 | Assuit PP (CP-118)6 | 0 | 0 | 0 | #DIV/0!
Ain Sokhna Port Development | IPC no25 |  | Ain Sokhna Port Development | 214074 | 0 | 0 | #DIV/0!
Luxor North Axis Bridge-Off | cr ipc 5 luxoroff | 5 | Luxor North Axis Bridge-Off5 | -672192 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 255 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj.180178 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | ENG/040 C |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 67 |  | FX-01-22 Decent Life-WD | 1794527.17 | 0 | 0 | #DIV/0!
Ain Sokhna Bridge | Cr. Inv ( 5 ) A.S | 5 | Ain Sokhna Bridge5 | 0 | 0 | 0 | #DIV/0!
Celia | D0020-OB-Dec-2020/Cr | 2020 | Celia2020 | 0 | 0 | 0 | #DIV/0!
New Heliopolis | cancel inv 8 | 8 | New Heliopolis8 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Cr adj inv12 | 12 | Abo Quir - Badr 500KV12 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH inv.39 deductions | 39 | South Helwan PP (CP-117)39 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr.Cr. Soc Inv. 48 | 48 | Akhmem Assiut48 | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2008220002 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Giza North PP Ph I,II (CP-117) | Cr-36 EGP-Giza I&II | 36 | Giza North PP Ph I,II (CP-117)36 | 0 | 0 | 0 | #DIV/0!
Museum of Egyp. Civilization | CR-IPC#3 | 3 | Museum of Egyp. Civilization3 | 0 | 0 | 0 | #DIV/0!
El Katameya Mall | CR inv ( 13 ) | 13 | El Katameya Mall13 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | de. transfer to EGP. |  | Abo Quir - Badr 500KV | 0 | 0 | 0 | #DIV/0!
Elhegaz | D0028-OB-Dec-202/Cr | 202 | Elhegaz202 | 0 | 0 | 0 | #DIV/0!
Ahl Misr P3 – Zamalek Sector | CR-IPC#5&6 | 5 | Ahl Misr P3 – Zamalek Sector5 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | adjust |  | South Helwan PP (CP-117) | -108901.12 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | rev.( 8 EGP-West D.) |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 180063 rev. |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | Inv-01 MOC | 1 | MOC HQ at Diriyah1 | 9771187.56 | 0 | 0 | 13219842
Haramein Columns Transfer | Haramin ipc01 | 1 | Haramein Columns Transfer1 | 5354496 | 0 | 0 | 5354496
Hosh Eisa Hospit. | IPC01TR0089 | 1 | Hosh Eisa Hospit.1 | 364500 | 0 | 0 | 364500
ORA ZED-Ph 2-Pkgs A&D | Ora Ph1 ipc (22) | 22 | ORA ZED-Ph 2-Pkgs A&D22 | 10796355.55 | 0 | 0 | 11336173.3275
SOL Town PKG.220 | PKG#220- IPC2 | 2 | SOL Town PKG.2202 | 23621739.09 | 0 | 0 | 26928782.5626
Get Business Complex | INV ( 6 ) GET | 6 | Get Business Complex6 | 1164549.6 | 0 | 0 | 1164549.6
El Katameya Mall | INV ( 14 ) 28-10-20 | 14 | El Katameya Mall14 | 169232 | 0 | 0 | 169232
Sixty Iconic Tower | inv ( 1) sixty | 1 | Sixty Iconic Tower1 | 1454355 | 0 | 0 | 1454355
Playa Resort | 41- مردودات بنكية |  | Playa Resort | 218.5 | 0 | 0 | 218.5
October Under-Railway Tunnel | october tunnel ipc01 | 1 | October Under-Railway Tunnel1 | 802790.71 | 0 | 0 | 842930.2455
MDF Factory | MDF_ IPC 13 | 13 | MDF Factory13 | 15274426.88 | 0 | 0 | 15274426.88
LAYAN Substation | 11745 |  | LAYAN Substation | 3545.48 | 0 | 0 | 3545.48
Nuweibaa (Swro) | 220621003 |  | Nuweibaa (Swro) | 46666.67 | 0 | 0 | 46666.67
Luxor North Axis Bridge-Off | IPC#2-Luxoroffshor | 2 | Luxor North Axis Bridge-Off2 | 2759054.4 | 0 | 0 | 2759054.4
Racecores 3092-15 132KV A | 11449 |  | Racecores 3092-15 132KV A | 3551.62 | 0 | 0 | 3551.62
EGYTEC A1,A3 ( LP-05-21) | 50 |  | EGYTEC A1,A3 ( LP-05-21) | 572325 | 0 | 0 | 572325
EGYTEC A1,A3 ( LP-05-21) | 56 |  | EGYTEC A1,A3 ( LP-05-21) | 1716975 | 0 | 0 | 1716975
Kafr Shokr Bridge | Kafr Shokr - IPC01 | 1 | Kafr Shokr Bridge1 | 32770679.81 | 0 | 0 | 34409213.8005
Banha PP (CP-117) | 2012210037 |  | Banha PP (CP-117) | -129460.88 | 0 | 0 | -129460.88
Daraw Bridge | D0033-OB-Dec-2020 | 2020 | Daraw Bridge2020 | 3578560 | 0 | 0 | 3578560
Elmaragha Bridge - Sohag | D0015-OB-Dec-2020 | 2020 | Elmaragha Bridge - Sohag2020 | 1475650 | 0 | 0 | 1475650
Road El Farag Axis | D0006-OB-Dec-2020 | 2020 | Road El Farag Axis2020 | 344798 | 0 | 0 | 344798
10th of Ramadan Railway | D0046 OB-Dec-2020 | 2020 | 10th of Ramadan Railway2020 | 5014107 | 0 | 0 | 5014107
Roots -Kafr ElSheikh Bridge | D0009-OB-Dec-2020 | 2020 | Roots -Kafr ElSheikh Bridge2020 | 421141.5 | 0 | 0 | 421141.5
LRT | D0045-OB-Dec-2020 | 2020 | LRT2020 | 778080 | 0 | 0 | 778080
Lahoon 220/22/22 | Al Lahoon Sub Inv 01 | 1 | Lahoon 220/22/221 | 13414631.32 | 0 | 0 | 13414631.32
Taval Sarai 52 | IPC_3_Saray_Gama |  | Taval Sarai 52 | 158874.5 | 0 | 0 | 158874.5
Sodic East | IPC12_sodic_east | 12 | Sodic East12 | 2661271.6 | 0 | 0 | 2661271.6
Manshiet Nasser Substation | 497 |  | Manshiet Nasser Substation | 969125.29 | 83472.1 | 0 | 83472.1
Cameron EDC | 024/2020 |  | Cameron EDC | 69576437.45 | 0 | 0 | 69576437.45
Cameron EDC | 023/2020 |  | Cameron EDC | 66315041.94 | 0 | 0 | 66315041.94
Suez Gulf Substation | 1909210007 |  | Suez Gulf Substation | 10987.09 | 10987.09 | 0 | 10987.09
Suez Gulf Substation | 1909210005 |  | Suez Gulf Substation | 3333550 | 3333550 | 0 | 3333550
Suez Gulf Substation | 1909210003 |  | Suez Gulf Substation | 116186 | 116186 | 0 | 116186
AWEER POWER STATION 'H' Phase | 5001 |  | AWEER POWER STATION 'H' Phase | 117898343.39 | 353695030.17 | 0 | 117898343.39
Beni-Suef Power Plant EPC | 67 |  | Beni-Suef Power Plant EPC | 0.01 | 0.01 | 0 | 0.01
Beni Suef COMCAVI | 1907210007 |  | Beni Suef COMCAVI | 611368269.3372 | 611368269.3372 | 0 | 611368269.3372
Beni-Suef Power Plant EPC | 1904210014 |  | Beni-Suef Power Plant EPC | 16897401.78 | 16897401.78 | 0 | 16897401.78
Beni-Suef Power Plant EPC | 180178 |  | Beni-Suef Power Plant EPC | 427482390.92 | 427482390.92 | 0 | 427482390.92
Cameroon EAR | P-09-13 AccRev | 9 | Cameroon EAR9 | 287923.24 | 0 | 0 | 287923.24
K047 FDH JV | p-10-16 ADJ | 10 | K047 FDH JV10 | 5651248 | 0 | 0 | 5651248
W Dam PP Phase II (CP-117) | DM for wrong credit |  | W Dam PP Phase II (CP-117) | 113117.95 | 0 | 0 | 113117.95
W Dam PP Phase II (CP-117) | 17 EGP-West Domiat |  | W Dam PP Phase II (CP-117) | 6435.43 | 6435.43 | 0 | 6435.43
Port Said | Adj.Inv. 17 | 17 | Port Said17 | 23601397.56 | 0 | 0 | 23601397.56
PIP- Zonafranca | Adj Inv 5 | 5 | PIP- Zonafranca5 | 56503324.28 | 0 | 0 | 56503324.28
Beni-Suef Power Plant EPC | 180070 |  | Beni-Suef Power Plant EPC | 96760325.43 | 0 | 0 | 96760325.43
Beni-Suef Power Plant EPC | 180118 |  | Beni-Suef Power Plant EPC | 487337915.43 | 487337915.43 | 0 | 487337915.43
Apache Electrical Works | 113 |  | Apache Electrical Works | -62239131.5949 | 0 | 0 | -62239131.5949
Abu Qir PP (CP-118) | 96 |  | Abu Qir PP (CP-118) | -282927272.3471 | 0 | 0 | -282927272.3471
Abu Qir PP (CP-118) | 28 |  | Abu Qir PP (CP-118) | 3115665.5712 | 0 | 0 | 3115665.5712
Abu Qir PP (CP-118) | 27 |  | Abu Qir PP (CP-118) | 55291.82 | 0 | 0 | 55291.82
IRAQ - Substations Soil Invest | 117 |  | IRAQ - Substations Soil Invest | -4177500 | 0 | 0 | -4177500
Lina Farm Substation | 100 |  | Lina Farm Substation | -4252794.1107 | 0 | 0 | -4252794.1107
Beni-Suef PP Site Preparation | 2 |  | Beni-Suef PP Site Preparation | 237544015.6515 | 0 | 0 | 237544015.6515
IRAQ - Al-Diwaniya Power Plant | 79 |  | IRAQ - Al-Diwaniya Power Plant | 583608125.3815 | 0 | 0 | 583608125.3815
IRAQ - Al-Diwaniya Power Plant | 78 |  | IRAQ - Al-Diwaniya Power Plant | -507140001 | 0 | 0 | -507140001
Ain-Sokhna PP (CP-117) | 69 |  | Ain-Sokhna PP (CP-117) | 18001724 | 0 | 0 | 18001724
Cairo South PP Rehabilitation | 10 USD - Cairo South |  | Cairo South PP Rehabilitation | 27162.77 | 27162.77 | 0 | 27162.77
Akhmem - Qena | Inv. 6 Akhmem Qena | 6 | Akhmem - Qena6 | 18108403.21 | 0 | 0 | 18108403.21
Siemens 6x500/220 KV GIS-MOU | ٍSoc 72 Asuit 10 |  | Siemens 6x500/220 KV GIS-MOU | 115457.3 | 0 | 0 | 115457.3
South Helwan PP (CP-117) | adj. 180010 & 180013 |  | South Helwan PP (CP-117) | 338325.46 | 338325.46 | 0 | 338325.46
Pyramids Industrial Park | Inv.5 PIP West | 5 | Pyramids Industrial Park5 | 3985862.7 | 0 | 0 | 3746710.95
New Capital | Inv 1 El Tbeen | 1 | New Capital1 | 17707402.209 | 0 | 0 | 17707402.209
New Capital | Inv 2 Abo Zaabl | 2 | New Capital2 | 21843369.1 | 0 | 0 | 21843369.1
Banha PP (CP-118) | 1 USD - Banha 118 |  | Banha PP (CP-118) | 159437.19 | 0 | 0 | 159437.19
Kuwait | 30-132KVA-J | 132 | Kuwait132 | 559622.7 | 363754.75 | 0 | 363754.75
IRAQ - Substations Soil Invest | 7 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
IRAQ - Substations Soil Invest | 8 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
New Capital | new acpita tbeen 1 |  | New Capital | 17707402.5 | 12208229.095 | 1859277.26 | 14067506.355
Siemens 6x500/220 KV GIS-MOU | Social 37 Bnha 6 |  | Siemens 6x500/220 KV GIS-MOU | 47216.96 | 47216.96 | 0 | 47216.96
Ismailiya East Substation | ISE-CW-EURO-01 | 1 | Ismailiya East Substation1 | 1513092.67 | 1044033.94 | 226963.9 | 1270997.84
Tamey El-amdeed Substation | TAM-CW-EGP-10 | 10 | Tamey El-amdeed Substation10 | 4385067.75 | 3244950.23 | 657760.16 | 3902710.39
Al Mostathmreen GIS Substation | (13)cw mostsmrin | 13 | Al Mostathmreen GIS Substation13 | 2554107.7 | 1902810.23 | 383116.16 | 2285926.39
Beni Suef ISKRA | 180115 |  | Beni Suef ISKRA | 59610.29 | 50668.75 | 8941.54 | 59610.29
Beni Suef COMCAVI | 180003 |  | Beni Suef COMCAVI | 396995.6 | 0 | 397030.9 | 198515.45
Beni Suef ISKRA | inv no(2 Euro-Iskrae | 2 | Beni Suef ISKRA2 | 13771766.91 | 13771766.91 | 0 | 13771766.91
Beni Seuf - 358 | Banha-Zagazg Inv.01 | 1 | Beni Seuf - 3581 | 24118240.19 | 0 | 4163750.7 | 4163750.7
Abu Qir PP (CP-117) | 49 Euro Abo Qir 117 |  | Abu Qir PP (CP-117) | 223059.5333 | 185384.04 | 0 | 185384.04
Banha PP (CP-118) | Collection |  | Banha PP (CP-118) | 162591.7 | 162591.7 | 0 | 162591.7
Apache Electrical Works | Apachi Inv No PC.#24 |  | Apache Electrical Works | 30425.9 | 30425.9 | 0 | 30425.9
Apache Electrical Works | Apachi Inv No PC.#22 |  | Apache Electrical Works | 50046.57 | 50046.57 | 0 | 50046.57
kayan wall lock & Load | مستخلص 2 كيان ردم 2 | 2 | kayan wall lock & Load2 | 2493680 | 1050255 | 1050264.4 | 2100519.4
South Helwan PP (CP-117) | 4 EUR South Helwan |  | South Helwan PP (CP-117) | 450359.14 | 450359.14 | 0 | 450359.14
Ghana | 33/P/10/ER/2017/USD |  | Ghana | 740200.21 | 740185.71 | 0 | 740185.71
Siemens 6x500/220 KV GIS-MOU | Ret.Itay sub |  | Siemens 6x500/220 KV GIS-MOU | 3682736.56 | 3682736.56 | 0 | 3682736.56
KSA - Rabegh PMS | INV PMS S.A |  | KSA - Rabegh PMS | 22502.2 | 22502.2 | 0 | 22502.2
Military 110 Kayan Project | Inv No3 ElKean 220 | 3 | Military 110 Kayan Project3 | 10659874.49 | 9673442.05 | 0 | 9673442.05
Cairo North PP Rehabilitation | 7 EGP - Cairo North |  | Cairo North PP Rehabilitation | 41928.07 | 41928.07 | 0 | 41928.07
Cairo South PP Rehabilitation | 8 USD - Cairo South |  | Cairo South PP Rehabilitation | 21238.01 | 21238.01 | 0 | 21238.01
Siemens 6x500/220 KV GIS-MOU | Ret. Kafr Elzayat |  | Siemens 6x500/220 KV GIS-MOU | 352432.62 | 352432.62 | 0 | 352432.62
El Mostakbal City Project | Inv. 12 Mostakbal | 12 | El Mostakbal City Project12 | 10382302.18 | 7745197.51 | 2180283.46 | 9925480.97
Military 110 Kayan Project | Inv.4 Elkayan | 4 | Military 110 Kayan Project4 | 7708606.29 | 6995162.45 | 0 | 6995162.45
Military 110 Kayan Project | Inv No 6 ElKean 220 | 6 | Military 110 Kayan Project6 | 12792300.22 | 11994040.85 | 0 | 11994040.85
South Helwan PP (CP-117) | Commercial fees SH- |  | South Helwan PP (CP-117) | 152890.19 | 152890.19 | 0 | 152890.19
Ain-Sokhna PP (CP-111) | Ret... Balance... |  | Ain-Sokhna PP (CP-111) | 1446650.57 | 1446650.57 | 0 | 1446650.57
Akhmem Assiut | Soc 3 Asuit |  | Akhmem Assiut | 240662.91 | 240662.91 | 0 | 240662.91
Siemens 6x500/220 KV GIS-MOU | Soc 11 east asuit |  | Siemens 6x500/220 KV GIS-MOU | 47673.85 | 47673.82 | 0 | 47673.82
SHAT Al ARAB 400/132kV SS | 202 |  | SHAT Al ARAB 400/132kV SS | 4240533.36 | 0 | 0 | 0
EMAAR-PKG#62-UPTOWN | PKG#62- IPC 14 | 14 | EMAAR-PKG#62-UPTOWN14 | 3683223.04 | 815558.87 | 0 | 815558.87
Abou El Matameer and Sammanoud | Social 10 matamer 89 |  | Abou El Matameer and Sammanoud | 58636.3 | 58636.29 | 0 | 58636.29
Marsa Matrouh 500KV | Inv.6 Borg Alarab | 6 | Marsa Matrouh 500KV6 | 87830687.53 | 87830687.53 | 0 | 87830687.53
Akhmem - Qena | Soci.$11-16:23Qena | 16 | Akhmem - Qena16 | 3541868.1 | 3541868.1 | 0 | 3541868.1
Kayan 3 New Cairo Capital City | Kayan MEP- ipc 4 | 4 | Kayan 3 New Cairo Capital City4 | 58955037 | 53206512.5 | 0 | 53206512.5
DPW Onshore Port & Terminal | DP WORLD-IPC09 | 9 | DPW Onshore Port & Terminal9 | 54097551.55 | 40031882.73 | 8114632.73 | 48146515.46
DPW Onshore Port & Terminal | DP World IPC032 | 32 | DPW Onshore Port & Terminal32 | 16694467.33 | 12304801.83 | 2504170.1 | 14808971.93
Closed | (3)Sobra-banha | 3 | Closed3 | 159125 | 220385.54 | 0 | 220385.54
Manshiet Nasser Substation | 503 |  | Manshiet Nasser Substation | 4028410.81 | 2391144.23 | 604261.62 | 2995405.85
Manshiet Nasser Substation | 502 |  | Manshiet Nasser Substation | 119663 | 0 | 17949.45 | 17949.45
Manshiet Nasser Substation | 490 |  | Manshiet Nasser Substation | 39228.15 | 0 | 5884.22 | 5884.22
EMAAR-PKG# 144, Marassi | PKG#144-IPC09 | 9 | EMAAR-PKG# 144, Marassi9 | 10299181.31 | 9830068.4255 | 458688.86 | 10288757.2855
4 SS - Technical Service | 220 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
El Boghaz Brigde | IPC#17 | 17 | El Boghaz Brigde17 | 436620.18 | 410422.97 | 0 | 410422.97
4 SS - Technical Service | 232 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 33 | 33 | Benban 500 K.V/95 K.M33 | 4275995.22 | 3254035.3 | 448979.5 | 3703014.8
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 10 | 10 | Benban 500 K.V/95 K.M10 | 296011.5 | 228227.96 | 31081.21 | 259309.17
Elco Steel 220/33 KV SS | 1904210002 |  | Elco Steel 220/33 KV SS | 426459.2 | 447782.16 | 0 | 447782.16
Elco Steel 220/33 KV SS | 1903210009 |  | Elco Steel 220/33 KV SS | 2989549.75 | 6278054.46 | 0 | 3139027.23
Akhmem Assiut | Social 48 Assuit |  | Akhmem Assiut | 2182603.5 | 2182603.5 | 0 | 2182603.5
Akhmem Assiut | Soc inv 1to49 Asuit | 1 | Akhmem Assiut1 | 1915923.61 | 1915923.61 | 0 | 1915923.61
Suez IPB | 1 USD - Suez Steel |  | Suez IPB | 1980 | 1980 | 0 | 1980
SHAT Al ARAB 400/132kV SS | 260 |  | SHAT Al ARAB 400/132kV SS | 372746.38 | 372746.38 | 0 | 372746.38
AWEER POWER STATION 'H' Phase | 10136 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
MOTHANA 400/132kV SS | 272 |  | MOTHANA 400/132kV SS | 68410.54 | 68410.54 | 0 | 68410.54
33KV Canal Farm Grid | Inv. 04 Farm | 4 | 33KV Canal Farm Grid4 | 22354576.27 | 17660115.25 | 3353186.44 | 21013301.69
Alamein | ALALAMEN SUPPLY-01 | 1 | Alamein1 | 5635700 | 4067203 | 0 | 4067203
Beni Suef Add-on Sales | 1908210014 |  | Beni Suef Add-on Sales | 117000 | 132210 | 0 | 132210
Beni Suef Substation R61 | BSF- CLIAM-EGP-01 | 1 | Beni Suef Substation R611 | 10000000 | 9999405.8 | 0 | 9999405.8
Elco Steel 220/33 KV SS | 517 |  | Elco Steel 220/33 KV SS | 61491.53 | 64566.11 | 0 | 64566.11
Cairo Capital Cables Tunnel | Tunnel Inv. 4 | 4 | Cairo Capital Cables Tunnel4 | 14140637.9 | 9516649.2 | 3535159.48 | 13051808.68
EMAAR-PKG#107-MARASSI | PKG#107-IPC18 | 18 | EMAAR-PKG#107-MARASSI18 | 1069591.54 | 1054265.617 | 0 | 1054265.617
Elco Steel 220/33 KV SS | 1907210009 |  | Elco Steel 220/33 KV SS | 15950.22 | 16747.73 | 0 | 16747.73
Elco Steel 220/33 KV SS | 1901210004 |  | Elco Steel 220/33 KV SS | 241517.84 | 253593.73 | 0 | 253593.73
SHATRA 400/132kV SS | 293 |  | SHATRA 400/132kV SS | 522747.52 | 522747.52 | 0 | 522747.52
MOTHANA 400/132kV SS | 289 |  | MOTHANA 400/132kV SS | 715698.36 | 715698.36 | 0 | 715698.36
Safir bridge | IPC#2 | 2 | Safir bridge2 | 106500 | 0 | 0 | 67533.6
Beni Seuf - 358 | Soci. 4-5Banysof 358 | 5 | Beni Seuf - 3585 | 868383 | 868383 | 0 | 868383
SHAT Al ARAB 400/132kV SS | 327 |  | SHAT Al ARAB 400/132kV SS | 429 | 429 | 0 | 429
MOTHANA 400/132kV SS | 292 |  | MOTHANA 400/132kV SS | 766712.41 | 766712.41 | 0 | 766712.41
LAYYAH CCPP | MP -09 | 9 | LAYYAH CCPP9 | 8569800 | 7284322.89 | 1285477.11 | 8569800
Zafranaa - Ras Ghareb | Abolila Zafra Instal |  | Zafranaa - Ras Ghareb | 799.68 | 799.68 | 0 | 799.68
Zafranaa - Ras Ghareb | Ref. Ghareeb |  | Zafranaa - Ras Ghareb | 0 | -173025.16 | 0 | -173025.16
Akhmem - Qena | Soc 49 Quana labour |  | Akhmem - Qena | 306247 | 305657.78 | 0 | 305657.78
CFC Podium 2 | CFC-IPC11 | 11 | CFC Podium 211 | 16864873.52 | 18030566.05 | 3463044.876 | 21493610.926
Toshka GIS 500 kV | Toshka Sub Inv. 17 $ | 17 | Toshka GIS 500 kV17 | 38060 | 21544.65 | 9990.75 | 31535.4
Phosfat | Inv.7 Phosfat | 7 | Phosfat7 | 375611.1 | 315903.65 | 0 | 315903.65
CFC Podium 2 | CFC IPC020 | 20 | CFC Podium 220 | 23105145.86 | 23721354.77 | 4488317.19 | 28209671.96
Multi Sport Hall | 10019 |  | Multi Sport Hall | 71955 | 64039.95 | 0 | 64039.95
AWEER POWER STATION 'H' Phase | ENG-023/Rev0 | 23 | AWEER POWER STATION 'H' Phase23 | 211328.6 | 221895.03 | 0 | 221895.03
Manshiet Nasser Substation | 2002210023 |  | Manshiet Nasser Substation | 4588.2 | 1675.05 | 0 | 1675.05
Sodic Wesset | 10022 |  | Sodic Wesset | 52649.24 | 48068.76 | 0 | 48068.76
4 SS - Technical Service | 343 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHAT Al ARAB 400/132kV SS | 322 |  | SHAT Al ARAB 400/132kV SS | 291176.33 | 291176.33 | 0 | 291176.33
MAYSAN 400/132kV SS | 308 |  | MAYSAN 400/132kV SS | 103659.09 | 103659.09 | 0 | 103659.09
SHAT Al ARAB 400/132kV SS | 326 |  | SHAT Al ARAB 400/132kV SS | 516459.01 | 516459.01 | 0 | 516459.01
Miscellaneous Projects | 2003210012 |  | Miscellaneous Projects | 140 | 155.4 | 0 | 155.4
4 SS - Technical Service | 349 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Miscellaneous Projects | 2004210001 |  | Miscellaneous Projects | 194088 | 219319.44 | 0 | 219319.44
4 SS - Technical Service | 354 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Abas El Akkad Bridge | IPC#1 | 1 | Abas El Akkad Bridge1 | 1023425 | 0 | 0 | 1013190.75
Al-Wukair 11 Substation | 2006210005 |  | Al-Wukair 11 Substation | 2521965.63 | 2521965.63 | 0 | 2521965.63
Miscellaneous Projects | 2007210006 |  | Miscellaneous Projects | 19570.71 | 21723.494 | 0 | 21723.494
AWEER POWER STATION 'H' Phase | Eng-029 Rev0 | 29 | AWEER POWER STATION 'H' Phase29 | 288828.17 | 303247.5785 | 0 | 303247.5785
AWEER POWER STATION 'H' Phase | Eng/030 |  | AWEER POWER STATION 'H' Phase | 135084.69 | 141767.11 | 0 | 141767.11
Beni Suef Add-on Sales | 1908210012 |  | Beni Suef Add-on Sales | 158042.56 | 175427.24 | 0 | 175427.24
NUCA R05 - Z02 | R05(2) IPC 47 | 47 | NUCA R05 - Z0247 | 22597861.91 | 20170545 | 2643691.59 | 22814236.59
Mahmoudia Additional Scope | 2003210005 |  | Mahmoudia Additional Scope | 625000 | 625000 | 0 | 625000
Zambia Project | SCD1/007 |  | Zambia Project | 82886.4 | 74597.76 | 0 | 74597.76
South Helwan PP (CP-117) | 2009210009 |  | South Helwan PP (CP-117) | 348942.6 | 363451.65 | 0 | 363451.65
AWEER POWER STATION 'H' Phase | ENG-031 | 31 | AWEER POWER STATION 'H' Phase31 | 539333.84 | 566300.532 | 0 | 566300.532
Racecores 3092-17 132KV E | 11290 |  | Racecores 3092-17 132KV E | 148481.03 | 123239.24 | 0 | 123239.24
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 35 | 35 | ORA ZED - Ph 01B - Pkgs A&D35 | 9206608.75 | 7391485.26 | 966693.92 | 8358179.18
EMAAR-PKG#62-UPTOWN | Pkg 162- IPC 19 | 19 | EMAAR-PKG#62-UPTOWN19 | 1831902.3 | 1275390.455 | 0 | 1275390.455
MOTHANA 400/132kV SS | 378 |  | MOTHANA 400/132kV SS | 40000 | 40000 | 0 | 40000
4 SS - Technical Service | 387 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Latin Compound - New Alamin | inv ( 26 )23-12-2020 | 26 | Latin Compound - New Alamin26 | 357456.4 | 303745.85 | 0 | 303745.85
Abu Quir Timmay Alamdid 500KV | Abo-Qair-Temay Inv.1 | 1 | Abu Quir Timmay Alamdid 500KV1 | 2740005.3 | 2110682.6 | 0 | 2110682.6
Canal Sugar 33KV OHTL | Inv. 5 Sugar 33 OHTL | 5 | Canal Sugar 33KV OHTL5 | 1053666.22 | 961997.25 | 0 | 961997.25
Lahoon 220/22/22 | Al-Lahoon Sub Inv 05 | 5 | Lahoon 220/22/225 | 106376100.95 | 0 | 26594025.24 | 26594025.24
Fish Market | FISH MARKER-MEP+1FIN |  | Fish Market | 201317.62 | 201317.62 | 0 | 201317.62
Mahmoudia Additional Scope | 2005210007 |  | Mahmoudia Additional Scope | 8250000 | 8250000 | 0 | 8250000
Mansoura University | IPC#01 - Mansoura | 1 | Mansoura University1 | 1548130.5 | 1000000 | 0 | 1503741.64
Toshka-04 GIS Substation | Toshka Sub 4 Inv.2 $ | 2 | Toshka-04 GIS Substation2 | 794984.46 | 0 | 39749.22 | 39749.22
4 SS - Technical Service | 398 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
West Port Said 220 kV GIS | P-45-Portsaid Inv.02 | 2 | West Port Said 220 kV GIS2 | 15693269.47 | 12570305.27 | 1647793.29 | 14218098.56
Shorouk Bridge-LRT | SHROUK BDRIDG-IPC03 | 3 | Shorouk Bridge-LRT3 | 7701312.1 | 6500000 | 0 | 6500000
Group # 1 - 25 LX | Reailway PSP Inv. 03 | 3 | Group # 1 - 25 LX3 | 840000 | 831600 | 0 | 831600
R5 | inv ( 14 ) | 14 | R514 | 1467000 | 1320105.5 | 0 | 1320105.5
Ghana Street lighting | MIDA Ins. Inv.6 | 6 | Ghana Street lighting6 | 110082.95 | 99074.65 | 0 | 99074.65
Akhmem - Qena | Ref.Ret Quana akh |  | Akhmem - Qena | 9060111.33 | 0 | 0 | 0
Mauritania Lot 1 | Inv.17 - Lot 1 | 17 | Mauritania Lot 117 | 265232.96 | 251956.56 | 0 | 251956.56
4 SS - Technical Service | 411 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Akhmem Assiut | Ref.Ret Asuit akh 1 |  | Akhmem Assiut | 10000000 | 10000000 | 0 | 10000000
SHAT Al ARAB 400/132kV SS | 416 |  | SHAT Al ARAB 400/132kV SS | 891552.99 | 891552.99 | 0 | 891552.99
ElMoneeb 2 | IPC#04 Moneeb Bridge | 4 | ElMoneeb 24 | 312855 | 309726.45 | 0 | 309726.45
Waldorf Astoria Cairo | WALDORF ASTORIA IPC2 | 2 | Waldorf Astoria Cairo2 | 3507480.42 | 2448867.881 | 955903.96 | 3404771.841
Zafranaa - Beni Suef | Ret Zafra-B-Suef T |  | Zafranaa - Beni Suef | 1114579.04 | 1114579.04 | 0 | 1114579.04
Racecores 3092-17 132KV E | 10965 |  | Racecores 3092-17 132KV E | 45479.7 | 45479.7 | 0 | 45479.7
Racecores 3092-16 132KV C | 10963 |  | Racecores 3092-16 132KV C | 47958.05 | 47958.05 | 0 | 47958.05
Benban 500 K.V/95 K.M | Ref.2 benban Lot 2 T |  | Benban 500 K.V/95 K.M | 10000000 | 10000000 | 0 | 10000000
BKG#178-Lagoon Discharge | pkg#178 ipc07 | 7 | BKG#178-Lagoon Discharge7 | 686559 | 1680446.34 | 0 | 1680446.34
Akhmem - Qena | Ret Qen-akh 9 T |  | Akhmem - Qena | 3599122.18 | 3450778.99 | 0 | 3450778.99
Akhmem - Qena | ref,ret,Qena - Akhme |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
RING ROAD MARYOTIA EXPANSION | elmarg ipc09 | 9 | RING ROAD MARYOTIA EXPANSION9 | 4536217.14 | 4020500.727 | 0 | 4020500.727
TZ – Offshore E&M Procurement | 454 |  | TZ – Offshore E&M Procurement | 455556.64 | 0 | 68333.5 | 68333.5
Ring Road Bridges Project | inv ( 5 ) 12-12-2021 | 5 | Ring Road Bridges Project5 | 2202635.7 | 1846142.42 | 0 | 1846142.42
Kemet Tower | inv ( 1 ) 9-12-2021 | 1 | Kemet Tower1 | 132480 | 113681.09 | 0 | 113681.09
AWEER POWER STATION 'H' Phase | ENG/050 |  | AWEER POWER STATION 'H' Phase | 52620.22 | 55251.231 | 0 | 55251.231
Taval Sarai 52 | IPC-17-SARAY | 17 | Taval Sarai 5217 | 53244 | 45230.78 | 0 | 45230.78
TZ – Offshore E&M Procurement | 445 |  | TZ – Offshore E&M Procurement | 193636.12 | 193636.12 | 0 | 193636.12
Racecores 3092-16 132KV C | 11285 |  | Racecores 3092-16 132KV C | 7273.18 | 7273.18 | 0 | 7273.18
MAYSAN 400/132kV SS | 432 |  | MAYSAN 400/132kV SS | 2968 | 2968 | 0 | 2968
MOTHANA 400/132kV SS | 438 |  | MOTHANA 400/132kV SS | 4928 | 4928 | 0 | 4928
MRINACMN KSWG & FRDH Circuit | 11322 |  | MRINACMN KSWG & FRDH Circuit | 19207.5 | 19207.5 | 0 | 19207.5
AWEER POWER STATION 'H' Phase | Eng/052 |  | AWEER POWER STATION 'H' Phase | 421109.11 | 442164.5655 | 0 | 442164.5655
LAYAN Substation | 11445 |  | LAYAN Substation | 276190.4762 | 290000 | 0 | 290000
New Giza Hospital | IPC-1-New Giza | 1 | New Giza Hospital1 | 412689.21 | 354128.62 | 0 | 354128.62
LAYAN Substation | 11461 |  | LAYAN Substation | 10249.95 | 10249.95 | 0 | 10249.95
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 18 | 18 | Suez Gulf/S4 - 500KV OHTL18 | 12894915.94 | 11811722 | 0 | 11811722
Racecores 3092-17 132KV E | 11500 |  | Racecores 3092-17 132KV E | 3816.96 | 3816.96 | 0 | 3816.96
Solar ITS | ITS Solar Inv. 01 | 1 | Solar ITS1 | 14119547.5 | 11039280 | 0 | 11039280
TEst | 001 |  | TEst | 44143.76 | 149647.3392 | 0 | 49882.4464
National Batteries LP-05-20 | 81 |  | National Batteries LP-05-20 | 578947.37 | 213315.34 | 0 | 213315.34
TZ – Offshore E&M Procurement | 465 |  | TZ – Offshore E&M Procurement | 167285.32 | 167285.32 | 0 | 167285.32
Kafr Shokr Bridge | kafr shokr IPC07 | 7 | Kafr Shokr Bridge7 | 30363309.48 | 27070646.13 | 0 | 27070646.13
FURJAN Cable Works | 11587 |  | FURJAN Cable Works | 4868005.51 | 132896550.4233 | 0 | 5111405.7855
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 6 | 6 | Marsa Alam/ Bernes LOT2 OHTL6 | 2436089.29 | 2196846.98 | 0 | 2196846.98
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv11 | 11 | Marsa Alam/ Bernes LOT2 OHTL11 | 414591.11 | 373460.2 | 0 | 373460.2
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 8 | 8 | Marsa Alam/ Bernes LOT2 OHTL8 | 209328.02 | 188310.4 | 0 | 188310.4
TNYA-WSHP | 11662 |  | TNYA-WSHP | 0 | -78027.6 | 0 | -78027.6
PO3092200025 | 11702 |  | PO3092200025 | 123220.12 | 123220.12 | 0 | 123220.12
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC 33+34 | 33 | EMAAR-Pkg#162/163- Marassi33 | 4083110.28 | 3354959.084 | 0 | 3354959.084
Assuit PP (CP-118) | Invoice # 39 Assuit |  | Assuit PP (CP-118) | 820286.39 | 861300.7095 | 0 | 861300.7095
Benban 500 K.V/95 K.M | Ref-Ret-Benban-lot2 |  | Benban 500 K.V/95 K.M | 4000000 | 4000000 | 0 | 4000000
New Giza Hospital | IPC-3-NEW GIZA | 3 | New Giza Hospital3 | 64993.96 | 37962.83 | 0 | 37962.83
New Babil 400/132KV GIS Substa | 220721002 |  | New Babil 400/132KV GIS Substa | 888398.4 | 888398.4 | 0 | 888398.4
New Giza Hospital | IPC-4-NEW GIZA | 4 | New Giza Hospital4 | 46975 | 37529.21 | 0 | 37529.21
W Dam PP Phase II (CP-117) | 2 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 35142.34 | 35142.34 | 0 | 35142.34
Playa Epoxy | 03 |  | Playa Epoxy | 53171.2 | 45626.21 | 0 | 45626.21
Playa Resort | 37 |  | Playa Resort | 6763.71 | 6763.71 | 0 | 6763.71
EGAT Pelletizing Plant | Water tank IPC 11+ | 11 | EGAT Pelletizing Plant11 | 1966603.81 | 1946937.7705 | 0 | 1946937.7705
Playa Resort | kantine.4 -40 | 40 | Playa Resort40 | 35000 | 35000 | 0 | 35000
Get Business Complex | INV ( 19 ) GET | 19 | Get Business Complex19 | 105763.25 | 99417.46 | 0 | 99417.46
Air Defence College | IPC003 | 3 | Air Defence College3 | 412839.98 | 350501.14 | 0 | 350501.14
Creeks URBN-K | katameya urbnk ipc15 | 15 | Creeks URBN-K15 | 10771231.15 | 10206848 | 267101.62 | 10473949.62
Air Defence College | IPC00006 | 6 | Air Defence College6 | 69600 | 59090.4 | 0 | 59090.4
Olympic Multi – Sports Hall | Olympic IPC1 | 1 | Olympic Multi – Sports Hall1 | 2197625 | 1812330 | 0 | 1812330
Olympic Multi – Sports Hall | Oly fin IPC4 | 4 | Olympic Multi – Sports Hall4 | 4391058 | 3699060 | 0 | 3699060
EGAT Mechanical Installations | Egat piping ipc 3 | 3 | EGAT Mechanical Installations3 | 1042361.93 | 849902.8302 | 260590.48 | 1110493.3102
SSC Suez Steel Company Project | R.O sup pri adj.ipc2 | 2 | SSC Suez Steel Company Project2 | 1686530.02 | 918958.5973 | 0 | 918958.5973
U3 & U5 | IPC3-TR55 | 3 | U3 & U53 | 34000.72 | 28363.02 | 0 | 28363.02
Olympic Multi – Sports Hall | SPORT HALL IPC 07 | 7 | Olympic Multi – Sports Hall7 | 16168000 | 14222372.5 | 0 | 14222372.5
U3 & U5 | IPC004 TR55 | 4 | U3 & U54 | 186640.4 | 161182.65 | 0 | 161182.65
MDF Factory | Mdf Factory 3 ipc 12 | 12 | MDF Factory12 | 1715548.54 | 0 | 1732936.45 | 1732936.45
SEASHELL TECHNICAL ROOM | IPC05TR0065 | 5 | SEASHELL TECHNICAL ROOM5 | 381327.19 | 329314.16 | 0 | 329314.16
Air Defense College | Air Tahsen IPC Fin |  | Air Defense College | 4238538 | 3570560 | 0 | 3570560
PLAYA ROOF & Wet Areas | IPC0022 TR41 | 22 | PLAYA ROOF & Wet Areas22 | 127113.34 | 109075.77 | 0 | 109075.77
U3 & U5 | IPC06 TR0055 | 6 | U3 & U56 | 73568.7 | 63533.92 | 0 | 63533.92
EPICO 3 Facility | Eipico ipc (9) | 9 | EPICO 3 Facility9 | 35000000 | 34650000 | 0 | 34650000
Seashell Playa 5 Villas | playa-c045 ipc 4 | 4 | Seashell Playa 5 Villas4 | 59845.85 | 46508.62 | 0 | 46508.62
Seashell Playa 5 Villas | playa-c072 ipc (1) | 1 | Seashell Playa 5 Villas1 | 115275.25 | 83551.7 | 0 | 83551.7
Seashell Playa 5 Villas | Playa-c038 ipc(4) | 4 | Seashell Playa 5 Villas4 | 78107.46 | 67453.6 | 0 | 67453.6
Air Defense College | Air Dev Allom IPC2 | 2 | Air Defense College2 | 3044221 | 2564350 | 0 | 2564350
HST El Mahager Bridge | ipc 5 elmahager | 5 | HST El Mahager Bridge5 | 7551825 | 6691275.33 | 0 | 6691275.33
VILLA CLUSTRER B | IPC03TR0077 | 3 | VILLA CLUSTRER B3 | 74105 | 63997.08 | 0 | 63997.08
U7-SEASHELL | IPC08TR0064 | 8 | U7-SEASHELL8 | 546742.03 | 459198.66 | 0 | 459198.66
MDF Factory | Mdf Equip ipc 20 | 20 | MDF Factory20 | 640115.15 | 606416.12 | 0 | 606416.12
Air Defense College | Air Dev sihi IPC2 | 2 | Air Defense College2 | 1074100 | 904520 | 0 | 904520
Ain Sokhna Bridge | Inv ( 4 ) A.S | 4 | Ain Sokhna Bridge4 | 333124.3 | 273490.77 | 0 | 273490.77
ZED Phase 2 | IPC03TR0062 | 3 | ZED Phase 23 | 15613.821 | 13263.94 | 0 | 13263.94
EGAT Injection | IPC006 TR48 | 6 | EGAT Injection6 | 52237.38 | 44824.9 | 0 | 44824.9
seashell Playa | IPC28TR0038 | 28 | seashell Playa28 | 267610.19 | 229636.3 | 0 | 229636.3
Creeks URBN-K | ipc16 katamya urbnk | 16 | Creeks URBN-K16 | 6516046.61 | 6345313.6705 | 0 | 6345313.6705
October Dry Port Railway | ODP Dry port ipc 4 | 4 | October Dry Port Railway4 | 650753.99 | 4734676.94 | 0 | 4734676.94
South Dabaa Axis | ipc final..2 elwaraq |  | South Dabaa Axis | 891923.1 | 789798.79 | 0 | 789798.79
Seashell Playa 5 Villas | Playa-c045 ipc 7 | 7 | Seashell Playa 5 Villas7 | 119128.39 | 72006.28 | 0 | 72006.28
Air Defence College | IPC21TR0046 | 21 | Air Defence College21 | 515431.5 | 437601.33 | 0 | 437601.33
EGAT Injection | IPC07 | 7 | EGAT Injection7 | 28544.81 | 24494.3 | 0 | 24494.3
Creeks URBN-K | Urbn-k ipc 17 | 17 | Creeks URBN-K17 | 8554341.9 | 8554807.445 | 0 | 8554807.445
Katameya Creeks - RME | IPC16TR0053 | 16 | Katameya Creeks - RME16 | 156756.24 | 138807.66 | 0 | 138807.66
Kattmeya Creeks Urban | IPC06TR0071 | 6 | Kattmeya Creeks Urban6 | 153630.36 | 136039.68 | 0 | 136039.68
MDF Factory | mdf local ipc 16 | 16 | MDF Factory16 | 1249666.24 | 1262162.9036 | 0 | 1262162.9036
seashell Playa | IPC30TR0038 | 30 | seashell Playa30 | 6489.78 | 5568.88 | 0 | 5568.88
HST Bridges-Sokhna & Mahager | sokhna bri ipc 20 | 20 | HST Bridges-Sokhna & Mahager20 | 5229351.9 | 4655093.281 | 0 | 4655093.281
Ministries Buildings | Mini Long lead IPC5 | 5 | Ministries Buildings5 | 3048577 | 2568010 | 0 | 2568010
HST Bridges-Sokhna & Mahager | sokhna esc.16 |  | HST Bridges-Sokhna & Mahager | 29623249.9 | 26411692.75 | 0 | 26411692.75
Creeks URBN-K | Urbnk ipc 18 | 18 | Creeks URBN-K18 | 9384875.1 | 9363449.555 | 0 | 9363449.555
Rabigh PP - Piling Works | Inv-1 | 1 | Rabigh PP - Piling Works1 | 824244.82 | 2843644.65 | 0 | 947881.55
U7-SEASHELL | IPC19TR0064 | 19 | U7-SEASHELL19 | 109721.9 | 94755.82 | 0 | 94755.82
Rabigh PP - Piling Works | Remaning Inv-2 | 2 | Rabigh PP - Piling Works2 | 187165.29 | 215240.08 | 0 | 215240.08
Port Said Grain Storage | RENT-007 | 7 | Port Said Grain Storage7 | 131650 | 150081 | 0 | 150081
El Khatatba Bridge | KHATATBA IPC10+11+12 | 10 | El Khatatba Bridge10 | 9666748.9 | 7237461.1 | 0 | 7237461.1
ORA ZED - Ph 01B - Pkgs A&D | ORA PH1 IPC 40 | 40 | ORA ZED - Ph 01B - Pkgs A&D40 | 4495110.55 | 3717952.37 | 0 | 3717952.37
Sultana Malak Restoration | sultana malak Damage |  | Sultana Malak Restoration | 178949.52 | 176047.4 | 0 | 176047.4
U7-SEASHELL | IPC20TR0064 | 20 | U7-SEASHELL20 | 26097.3 | 22537.64 | 0 | 22537.64
Seashell Playa 5 Villas | playa - c469 ipc4 | 4 | Seashell Playa 5 Villas4 | 67230.66 | 61421.93 | 0 | 61421.93
EMAAR-PKG# 101-UPTOWN | Emaar pkg#101 ipc 24 | 24 | EMAAR-PKG# 101-UPTOWN24 | 270197.08 | 546994.614 | 0 | 546994.614
EGAT ADMIN (Pelletizing) | IPC01TR0094 | 1 | EGAT ADMIN (Pelletizing)1 | 310640 | 266560.18 | 0 | 266560.18
Rabigh CCPP-Civil | Inv-01 | 1 | Rabigh CCPP-Civil1 | 2313265.08 | 7980764.49 | 0 | 2660254.83
U3 & U5 | IPC22TR0055 | 22 | U3 & U522 | 242534.58 | 158302.85 | 0 | 158302.85
Abou Ghaleb Bridge | abo ghaleb esc.1:11 |  | Abou Ghaleb Bridge | 26616364.1 | 25711010.9 | 0 | 25711010.9
EDNC Mobilization Works | EDNC PO NO. (3349T) |  | EDNC Mobilization Works | 609204.24 | 633572.41 | 0 | 633572.41
RADAMIS CITY | IPC04TR0084 | 4 | RADAMIS CITY4 | 24234.05 | 21459.26 | 0 | 21459.26
RADAMIS CITY | IPC10TR0084 | 10 | RADAMIS CITY10 | 383921.2 | 272636.36 | 0 | 272636.36
Irrigation Tank | IPC12TR0061 | 12 | Irrigation Tank12 | 689048.85 | 499792.67 | 0 | 499792.67
Egyptian Exchange building | IPC16TR0039 | 16 | Egyptian Exchange building16 | 624770.85 | 553234.59 | 0 | 553234.59
Katameya Creeks - RME | IPC21(1)TR0053 | 21 | Katameya Creeks - RME21 | 529445.82 | 462161.77 | 0 | 462161.77
U7-SEASHELL | IPC24TR0064 | 24 | U7-SEASHELL24 | 83712.08 | 43465.65 | 0 | 43465.65
WADY EL-NATROUN BRIDGE(HST) | IPC#19 wady elnatron | 19 | WADY EL-NATROUN BRIDGE(HST)19 | 109940 | 34465.36 | 0 | 34465.36
U7-SEASHELL | IPC25TR0064 | 25 | U7-SEASHELL25 | 231425 | 0 | 0 | 0
Wady El Natroon Bridge | WADY ELNATROON IPC12 | 12 | Wady El Natroon Bridge12 | 13068802.86 | 11651747.9 | 0 | 11651747.9
Rabigh PP - Piling Works | K0004 Inv-07 | 7 | Rabigh PP - Piling Works7 | 2703528.67 | 9327173.91 | 0 | 3109057.97
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 1199.73 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DECADJ 81 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | CR-IPC 4 | 4 | WADY EL-NATROUN BRIDGE(HST)4 | -937184.64 | 0 | 0 | #DIV/0!
Koning Food V3 LP-09-20 | 16 |  | Koning Food V3 LP-09-20 | 0 | 0 | 0 | #DIV/0!
LINX Tower | CR-INV(1)LINX | 1 | LINX Tower1 | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | 30 Euro - Banha 117 |  | Banha PP (CP-117) | 41716.7333 | 0 | 0 | #DIV/0!
Al-Parco | INV ( 9 ) ALparco | 9 | Al-Parco9 | 4925521.5 | 0 | 0 | #DIV/0!
SOL Town PKG.220 | CR PKG#220- IPC 2 | 2 | SOL Town PKG.2202 | 0 | 0 | 0 | #DIV/0!
ElSewedy HQ Internal Finishing | CR-Elsewedy HQ-IPC24 | 24 | ElSewedy HQ Internal Finishing24 | 0 | 0 | 0 | #DIV/0!
East Port Said Industrial Area | FPC - Orascom HA |  | East Port Said Industrial Area | 50000 | 0 | 0 | #DIV/0!
Cameron EDC | 022/2020cncl |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Ahl Misr P3 – Zamalek Sector | CR-IPC#5 | 5 | Ahl Misr P3 – Zamalek Sector5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 247 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Kemet Tower | CR INV ( 9 ) KEMET | 9 | Kemet Tower9 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr-Sales tax USD inv |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2103220004 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 5 Euro-South Helwan |  | South Helwan PP (CP-117) | 2519311.5619 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2103210013 |  | Miscellaneous Projects | 10500 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 88 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Wadi El Natroun Bridge | inv ( 3 ) W. Natron | 3 | Wadi El Natroun Bridge3 | 9507300 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | 28 |  | Barwa 2x60/22 KV S/S | 430464.18 | 0 | 0 | #DIV/0!
SHAT Al ARAB 400/132kV SS | 246 |  | SHAT Al ARAB 400/132kV SS | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 9 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 78700.1238 | 0 | 0 | #DIV/0!
Akhmem - Qena | close Adj Inv 10 | 10 | Akhmem - Qena10 | 0 | 0 | 0 | #DIV/0!
Amal Bridge Lock & Load | cr(1) ALAMAL BRIDGE | 1 | Amal Bridge Lock & Load1 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | CR MOC Inv-01 | 1 | MOC HQ at Diriyah1 | 0 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | IPC#4 - Maragha Brid | 4 | Elmaragha Bridge - Sohag4 | 219822.5 | 0 | 0 | #DIV/0!
Almaza Bridge - Safir 2 | D0023-OB-Dec-2020/Cr | 2020 | Almaza Bridge - Safir 22020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 10 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1159738.7714 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | LOC/014CR |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
ORA ZED-Ph 2-Pkgs A&D | Cr-ORA PH.2-ipc13 | 13 | ORA ZED-Ph 2-Pkgs A&D13 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_INV.13 | 13 | Akhmem - Qena13 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 18 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 412796.7524 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 20 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 43165.1619 | 0 | 0 | #DIV/0!
Ministries Buildings | Ministiry MEP ipc09 | 9 | Ministries Buildings9 | 68533369.3 | 0 | 0 | #DIV/0!
ElMoneeb 2 | D0041-OB-Dec-2020/Cr | 2020 | ElMoneeb 22020 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | Inv-001 MOC | 1 | MOC HQ at Diriyah1 | 11546312.44 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2012220003 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Adj on inv.1 lot 1 | 1 | Mauritania Lot 11 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_INV.7 | 7 | Akhmem Assiut7 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 241 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Water pumping New Obour City | DR.Pump Obour Inv.6 | 6 | Water pumping New Obour City6 | 159283.13 | 0 | 0 | #DIV/0!
Sixty Iconic Tower | Cr inv ( 1 ) sixty | 1 | Sixty Iconic Tower1 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ret Asuit akh 5 |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Abo Ghaleb | IPC#2#Abo Ghaleb cr | 2 | Abo Ghaleb2 | 0 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | D0015-OB-Dec-20/Cr | 20 | Elmaragha Bridge - Sohag20 | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 66 |  | FX-01-22 Decent Life-WD | 1083168.5 | 0 | 0 | #DIV/0!
Infra Project 4428 | 220322002 |  | Infra Project 4428 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | IMP-61 | 61 | AWEER POWER STATION 'H' Phase61 | 0 | 0 | 0 | #DIV/0!
Containment Data Center- | 35 |  | Containment Data Center- | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 64 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
LRT Project | Cancel IPC_1_GRowad |  | LRT Project | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2105210018 |  | Miscellaneous Projects | -10500 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 476 |  | TZ – Offshore E&M Procurement | 3240000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 87 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_inv. 8 | 8 | Akhmem Assiut8 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 2004220006 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10367 |  | AWEER POWER STATION 'H' Phase | 2129497.75 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Cr. Inv. 1 Temmay | 1 | Beni Seuf - 3581 | 0 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | Inv. No. 3 -Int.part | 3 | Angola Emergency fast-track3 | 946963.18 | 0 | 0 | #DIV/0!
Benban 3/ Toshka 2 LOT 4 | Cr.Tos Lot6 Inv.4 | 4 | Benban 3/ Toshka 2 LOT 44 | 0 | 0 | 0 | #DIV/0!
Development of Mahmudiyah axis | D0012-OB-Dec-2020/Cr | 2020 | Development of Mahmudiyah axis2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 243 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Latin Quarter- New Alamein | Cr 4-2021 | 2021 | Latin Quarter- New Alamein2021 | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,6 usd Borg Ar | 6 | Marsa Matrouh 500KV6 | 0 | 0 | 0 | #DIV/0!
ORA-ZED Towers01B | CR.TR0029DEC.Closing |  | ORA-ZED Towers01B | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 265 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | inv no 15.2 d0073 | 15 | WADY EL-NATROUN BRIDGE(HST)15 | 57555 | 0 | 0 | #DIV/0!
Ministries Building ROOF | CR.TR0010CLOSING.DEC |  | Ministries Building ROOF | 0 | 0 | 0 | #DIV/0!
Al-Parco | cr inv ( 3 ) | 3 | Al-Parco3 | 0 | 0 | 0 | #DIV/0!
Port Saad Industiral zone | D0022-OB-Dec-2020/Cr | 2020 | Port Saad Industiral zone2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 42 |  | Al-Shabab PP Phase II (CP-117) | 6496326.93 | 0 | 0 | #DIV/0!
Sodic East Town(EDNC) | IPC01TR0090 | 1 | Sodic East Town(EDNC)1 | 328820.4 | 0 | 0 | #DIV/0!
Damac 2x60/22 KV S/S | CR.ADJ.inv.20 | 20 | Damac 2x60/22 KV S/S20 | 0 | 0 | 0 | #DIV/0!
New Heliopolis | cancel inv. 9 | 9 | New Heliopolis9 | 0 | 0 | 0 | #DIV/0!
Cameron EDC | 023/2020cncl |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Open Channal | CANCELLED |  | Open Channal | 0 | 0 | 0 | #DIV/0!
WPS Substations 1&2 | P-10-EGY اتحاد تشيد | 10 | WPS Substations 1&210 | 5000 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11522 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11584 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 10 EGP- Suez Gulf |  | Suez Gulf Substation | 431640.3238 | 0 | 0 | #DIV/0!
Beni Suef Add-on Sales | 2005220004 |  | Beni Suef Add-on Sales | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | 31 EUR - Banha 117 ) |  | Banha PP (CP-117) | 10450.4762 | 0 | 0 | #DIV/0!
Phosfat | Cr Inv.6 Phosfat | 6 | Phosfat6 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 10 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 2928987.5048 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Retention OB |  | Zafranaa - Ras Ghareb | 10024979.95 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 56 |  | Suez Gulf Substation | 4828633.4664 | 0 | 0 | #DIV/0!
New Capital | CrAdj Inv. 21 | 21 | New Capital21 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr- 5 + 7 USD-Shabab | 5 | Al-Shabab PP Phase II (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Cairo-Alex Railway | CR cairo alex ipc41 | 41 | Cairo-Alex Railway41 | 0 | 0 | 0 | #DIV/0!
ZED Phase 2 | IPC10TR0062 | 10 | ZED Phase 210 | 60814.55 | 0 | 0 | #DIV/0!
Street Lighting Fayoum | CR.Fayoum Inv.01 | 1 | Street Lighting Fayoum1 | 0 | 0 | 0 | #DIV/0!
Residence 8 ( k12 ) | CrINV( 1 ) R08 - K12 | 1 | Residence 8 ( k12 )1 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 3 |  | Zafranaa - Ras Ghareb | 118994.99 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR-16 EGP- West D. | 16 | W Dam PP Phase II (CP-117)16 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen-akh |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Inv13 SH EUR | 13 | South Helwan PP (CP-117)13 | 167451.4286 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | CR-40 EGP-Giza N.III | 40 | Giza North PP Phase3(CP-117)40 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 7 |  | Zafranaa - Beni Suef | 26717.69 | 0 | 0 | #DIV/0!
HST - 6 October - Arab Cont. | CR IPC#1 HSR | 1 | HST - 6 October - Arab Cont.1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR- 5 USD - Shabab | 5 | Al-Shabab PP Phase II (CP-117)5 | 0 | 0 | 0 | #DIV/0!
10Th of Ramadan LRT | P-37-EGY اتحاد تشيد | 37 | 10Th of Ramadan LRT37 | 5000 | 0 | 0 | #DIV/0!
Hyper One Badr | INV ( 13 fin ) Hyper | 13 | Hyper One Badr13 | 187199.31 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180018 |  | Suez Gulf Substation | -354232.13 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180016 |  | Suez Gulf Substation | 354232.13 | 0 | 0 | #DIV/0!
LAYAN Substation | 11748 |  | LAYAN Substation | 0 | 0 | 0 | #DIV/0!
Minis Building(Polyurethane) | CR.TR0020CLOSING.DEC |  | Minis Building(Polyurethane) | 0 | 0 | 0 | #DIV/0!
New Heliopolis | Cr Adj Inv 8 | 8 | New Heliopolis8 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 20 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 466026.0571 | 0 | 0 | #DIV/0!
MDF Factory | CR-MDF FACTORY-IPC07 | 7 | MDF Factory7 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 9 EGP- Suez Gulf |  | Suez Gulf Substation | 1870441.4095 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 50 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,5 usd Borg Ar | 5 | Marsa Matrouh 500KV5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 180021 |  | Al-Shabab PP Phase II (CP-117) | -2176819.63 | 0 | 0 | #DIV/0!
DPW Onshore Port & Terminal | CR-DP WORLD-IPC06 | 6 | DPW Onshore Port & Terminal6 | 0 | 0 | 0 | #DIV/0!
Ameria | Credit FPC04 |  | Ameria | 0 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 100 |  | FX-02-22 Decent Life-UE | 1200671.97 | 0 | 0 | #DIV/0!
Capital One | inv ( 10 ) Captal Cr | 10 | Capital One10 | 0 | 0 | 0 | #DIV/0!
Cairo Monorail - 6th October | CR IPC#7 | 7 | Cairo Monorail - 6th October7 | 0 | 0 | 0 | #DIV/0!
Elniger | 5004 Credit |  | Elniger | 0 | 0 | 0 | #DIV/0!
Residence 8 ( k12 ) | INV ( 1 ) R08 - K12 | 1 | Residence 8 ( k12 )1 | 19407.18 | 0 | 0 | 19407.18
ACWA POWER & NOMAC HQ | Acwa Power ipc 1 | 1 | ACWA POWER & NOMAC HQ1 | 85714.29 | 0 | 0 | 90000.0045
Abo Shanab El Agamien | ABO SHANAB IPC 2 | 2 | Abo Shanab El Agamien2 | 1014478 | 0 | 0 | 1014478
Katameya Creeks - RME | IPC13TR53 | 13 | Katameya Creeks - RME13 | 36591.65 | 0 | 0 | 0
Koumassi Flyover | INV 1 | 1 | Koumassi Flyover1 | 464398 | 0 | 0 | 464398
Al-Parco | INV (3 ) | 3 | Al-Parco3 | 2422608 | 0 | 0 | 2422608
ORA ZED-Ph 2-Pkgs A&D | ora zed (2) ipc 16 | 16 | ORA ZED-Ph 2-Pkgs A&D16 | 12061901.86 | 0 | 0 | 12664996.953
Expansion of Ring Road NRCC | IPC 3 NRCC | 3 | Expansion of Ring Road NRCC3 | 169935 | 0 | 0 | 169935
FURJAN Cable Works | 11561 |  | FURJAN Cable Works | 60494.4 | 0 | 0 | 63519.12
Beni-Suef Power Plant EPC | Inv. 26 | 26 | Beni-Suef Power Plant EPC26 | 779.29 | 0 | 0 | 779.29
Wadi El Natroun | D0014-OB-Dec-2020 | 2020 | Wadi El Natroun2020 | 6130260 | 0 | 0 | 6130260
ElMoneeb 2 | D0041-OB-Dec-2020 | 2020 | ElMoneeb 22020 | 677700 | 0 | 0 | 677700
ITS | Adv. ITS Inv. 01 | 1 | ITS1 | 8999900 | 0 | 0 | 8999900
Koning Food V3 LP-09-20 | 13 |  | Koning Food V3 LP-09-20 | 99912.28 | 0 | 0 | 99912.28
Hadaek ElAharam | D0037-OB-Dec-2020 | 2020 | Hadaek ElAharam2020 | 1214680 | 0 | 0 | 1214680
Assuit PP (CP-118) | 2001210018 |  | Assuit PP (CP-118) | 419062.41 | 0 | 0 | 440015.53
Al-Shabab PP Phase II (CP-117) | 2001210010 |  | Al-Shabab PP Phase II (CP-117) | 696.0051 | 0 | 0 | 797.51
LAYYAH CCPP | 470 |  | LAYYAH CCPP | 12854700 | 0 | 0 | 12854700
AWEER POWER STATION 'H' Phase | 10170 |  | AWEER POWER STATION 'H' Phase | 34632651.97 | 0 | 0 | 36364284.5685
Beni-Suef Power Plant EPC | 1907210004 |  | Beni-Suef Power Plant EPC | 31670696.4 | 31670696.4 | 0 | 31670696.4
Beni-Suef Power Plant EPC | 180120 |  | Beni-Suef Power Plant EPC | 16392318.57 | 16392318.57 | 0 | 16392318.57
Abu Qir PP (CP-117) | 1902210011 |  | Abu Qir PP (CP-117) | 196748.76 | 196748.76 | 0 | 196748.76
Beni-Suef Power Plant EPC | In 9+10 Beni Suef |  | Beni-Suef Power Plant EPC | 234962660.6 | 234962660.6 | 0 | 234962660.6
Akhmem Assiut | Soc Inv 49 Asuit | 49 | Akhmem Assiut49 | 48705.75 | 0 | 0 | 48705.75
Akhmem Assiut | Soc Inv 44 To 47 Qun | 44 | Akhmem Assiut44 | 2259485.5 | 0 | 0 | 2259485.5
Abou El Matameer and Sammanoud | Adj. Inv. 15 | 15 | Abou El Matameer and Sammanoud15 | 2916027.28 | 0 | 0 | 5832054.56
Siemens 6x500/220 KV GIS-MOU | Adj. Inv. 22 | 22 | Siemens 6x500/220 KV GIS-MOU22 | 2916027.23 | 0 | 0 | 2916027.23
K047 FDH JV | p-10-16 ADJ 2 | 10 | K047 FDH JV10 | 182114.96 | 0 | 0 | 182114.96
Al-Shabab PP Phase II (CP-117) | DR-Sales tax USD inv |  | Al-Shabab PP Phase II (CP-117) | 71027.48 | 71027.48 | 0 | 71027.48
Al-Shabab PP Phase II (CP-117) | DM-CR-19 EGP- Shabab | 19 | Al-Shabab PP Phase II (CP-117)19 | 2580132 | 0 | 0 | 2709138.6
Al-Shabab PP Phase II (CP-117) | 15 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 130940.02 | 0 | 0 | 130940.02
Marsa Matrouh 500KV | Inv, 7 usd Borg Arab | 7 | Marsa Matrouh 500KV7 | 1105819.91 | 0 | 0 | 1105819.91
South Helwan PP (CP-117) | 180145 |  | South Helwan PP (CP-117) | 245790.16 | 0 | 0 | 245790.16
South Helwan PP (CP-117) | 180144 |  | South Helwan PP (CP-117) | 245790.16 | 0 | 0 | 245790.16
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 04 |  | Giza North PP Ph I,II (CP-117) | 695709.53 | 695709.53 | 0 | 695709.53
South Helwan PP (CP-117) | Commercial fees |  | South Helwan PP (CP-117) | 11551.94 | 11551.94 | 0 | 11551.94
Pyramids Industrial P - East | Adj Inv 4 | 4 | Pyramids Industrial P - East4 | 85372216.25 | 0 | 0 | 85372216.25
Akhmem Assiut | Soc.$4-8:19Assuit | 8 | Akhmem Assiut8 | 10725414 | 0 | 0 | 10725414
Abu Qir PP (CP-118) | 441 EGP-Abo qeir 118 |  | Abu Qir PP (CP-118) | 3204257 | 3204257 | 0 | 3204257
Apache Electrical Works | 112 |  | Apache Electrical Works | 65105214.1353 | 0 | 0 | 65105214.1353
Mahmoudia Power Plant | 120 |  | Mahmoudia Power Plant | 2268359476.0321 | 0 | 0 | 2268359476.0321
Abu Qir PP (CP-118) | 19 |  | Abu Qir PP (CP-118) | 317532447 | 0 | 0 | 317532447
IRAQ - Substations Soil Invest | 22 |  | IRAQ - Substations Soil Invest | 1957500 | 0 | 0 | 1957500
IRAQ - Substations Soil Invest | 38 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
Ain-Sokhna PP(CP-102) | 26 |  | Ain-Sokhna PP(CP-102) | 16867317 | 0 | 0 | 16867317
Lina Farm Substation | 99 |  | Lina Farm Substation | 3820219.5717 | 0 | 0 | 3820219.5717
Beni-Suef Power Plant EPC | 3 |  | Beni-Suef Power Plant EPC | 45492840.03 | 0 | 0 | 45492840.03
Abu Qir PP (CP-117) | 20 |  | Abu Qir PP (CP-117) | 50353425 | 0 | 0 | 50353425
Abu Qir PP (CP-117) | 93 |  | Abu Qir PP (CP-117) | -38338457.9583 | 0 | 0 | -38338457.9583
Abu Qir PP (CP-117) | 32 |  | Abu Qir PP (CP-117) | 1383755.4984 | 0 | 0 | 1383755.4984
Ain-Sokhna PP (CP-111) | 98 |  | Ain-Sokhna PP (CP-111) | 937757.98 | 0 | 0 | 937757.98
KSA - Rabegh PMS | 124 |  | KSA - Rabegh PMS | 1462768.8503 | 0 | 0 | 1462768.8503
Palm Hill-Infra Str(Elec.Work) | 10 |  | Palm Hill-Infra Str(Elec.Work) | 5669708 | 0 | 0 | 5669708
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 02 |  | Giza North PP Ph I,II (CP-117) | 182670.58 | 182670.58 | 0 | 182670.58
Cairo South PP Rehabilitation | 5 USD - Cairo South |  | Cairo South PP Rehabilitation | 5565.27 | 5565.27 | 0 | 5565.27
Akhmem - Qena | Inv.13 Akhmem Qena | 13 | Akhmem - Qena13 | 23766468.95 | 0 | 0 | 23766468.95
Abu Qir PP (CP-118) | 452 Euro - Avice |  | Abu Qir PP (CP-118) | 42422.31 | 0 | 0 | 42422.31
Abu Qir PP (CP-118) | 451 USD - Avice |  | Abu Qir PP (CP-118) | 56897.28 | 0 | 0 | 56897.28
Abu Qir PP (CP-118) | 450 USD - Avice |  | Abu Qir PP (CP-118) | 350863.24 | 0 | 0 | 350863.24

## operation
project name | operation
6TH October tunnel | 2
Abo Ghaleb Bridge | 2
AEON
Al Jazi | 1
Al Jazi - Center Zone | 1
Al Jazi - Center Zone-DP | 1
Al Jazi - Social Insurance | 1
Al Jazi-DP | 1
Alfa Lab | 1
Allegria-New Modifications | 1
Astoria - Sharm | 1
Astoria - Sharm-DP | 1
Astoria Hotel | 1
Astoria Hotel - DP | 1
Astoria Hotel - Final Retention | 1
Astoria Hotel - On Account | 1
Astoria Hotel - Social Insurrance | 1
Astoria Hotel - Spare Parts V.O 137 | 1
Astoria Hotel IPCs 15-20 | 1
Baraka Land Fence | 1
Benban - Aswan | 1
Benban - Aswan - DP | 1
Cement Plant | 1
Cement Plant -Last Claim | 1
CFC | 1
CFC - Final Retention | 1
CFC-DP | 1
Comoros - DP | 1
Comoros - Off Shore | 1
Comoros - On Shore | 1
Comoros - On Shore - On Account | 1
Creeks - URBN K | 1
Creeks - URBN K - DP | 1
Creeks - URBN K - On Account | 1
Damietta Port - Civil | 1
Damietta Port - Civil - DP | 1
Damietta Port - Infra - DP | 1
1
DP World Sokhna | 1
DP World Sokhna-AP | 1
DPW - Ph.02 | 1
DPW - Ph.02 - DP | 1
EGAT Pelletizing Plant | 1
EGAT Pelletizing Plant - Admin Building | 1
EGAT Pelletizing Plant - Supply | 1
EGAT Pelletizing Plant-Concrete Infra | 1
EGAT Pelletizing Plant-DP | 1
EGAT Pelletizing Plant-Escalation | 1
EGAT Pelletizing Plant-Mechanical Installation | 1
EGAT Pelletizing Plant-MEP | 1
EGAT Pelletizing Plant-MEP Coordination | 1
EGAT Pelletizing Plant-On account | 1
EGAT Pelletizing Plant-Water Tank | 1
EGAT-Asphalt | 1
EGAT-Asphalt - Retenion Release | 1
EGAT-EGAT ON Account | 1
EGAT-Fence | 1
EGAT-Fence - Retenion Release | 1
EGAT-HeliPad | 1
EGAT-Lock & Load | 1
EGAT-Lock & Load-AP | 1
EGAT-SZ | 1
EGAT-Warehouse | 1
EIPICO | 1
EIPICO-DP | 1
EIPICO-On Account | 1
El Sewedy Uni.-PKG.1 | 1
El Sewedy Uni.-PKG.1-DP1 | 1
El Sewedy Uni.-PKG.2 | 1
El Sewedy Uni.-PKG.2-DP2 | 1
El Sewedy Uni.-PKG.2-Social Insurrance | 1
El Sewedy Uni.-PKG.3 | 1
El Sewedy Uni.-PKG.3 - On Account | 1
El Sewedy Uni.-PKG.3-DP | 1
El Sewedy Uni.-PKG.3-Social Insurrance | 1
Elco Steel | 1
Elco Steel - ADMIN. | 1
Elco Steel - MEP | 1
Elco Steel - MEP - Social Insurance | 1
Elco Steel - Social Insurance | 1
Elco Steel EGAT-DP | 1
Elco Steel V.O | 1
Elco Steel V.O-DP | 1
Elco Steel V.O-Infra. Network | 1
El-Gouna | 1
El-Gouna - DP | 1
El-Gouna - Equip. Rental | 1
El-Gouna - Temp. Fence | 1
EUA-DP
Existing Intake Apply -SSC-Mech | 1
Existing Intake Supply -SSC-Mech | 1
FIEM | 1
FIEM - Retention | 1
FIEM-Site Offices Rental Payment Request | 1
H1 Solaymaneya-MEP | 1
H1 Solaymaneya-MEP-DP | 1
HQ - CFC | 1
HQ - CFC - DP | 1
HQ - CFC - Retention release | 1
HQ - CFC - Social Insurrance | 1
HyperOne | 1
HyperOne-DP | 1
HyperOne-Steel Supply | 1
HyperOne-VAT 1,2,3 | 1
IKEA | 1
IKEA-DP | 1
IKEA-Retention Release | 1
JICA | 1
JICA-Site Offices Rental Payment Request | 1
Kafr Shokr | 2
Kafr Shokr - Retention Release | 2
Katameya - Creeks | 1
Katameya - Creeks - DP | 1
Katameya - Creeks - DP - Alu Glass | 1
Katameya - Creeks - On Account | 1
KFW | 1
KFW-Road Signals | 1
Khatatba Bridge | 2
KSA-Tarek AbdelHakim Center | 1
KSA-Tarek AbdelHakim Center - DP | 1
LEKELA | 1
LEKELA - Supply Bill | 1
LEKELA- On Account | 1
LEKELA Remedial | 1
LEKELA Remedial-DP | 1
LEKELA-DP | 1
MDF Factory | 1
MDF Factory - Equip. | 1
MDF Factory - Local Fabrication | 1
MDF Factory-DP | 1
MDF Factory-F.F V.O-on account | 1
MDF Factory-Hold Amount release | 1
MDF Factory-Local Fab.-on account | 1
MDF Factory-on account | 1
MDF Factory-on account solera | 1
MDF Factory-P.O-on account | 1
Mechanical Installation | 1
Mechanical Installation-DP | 1
Mintra | 1
Mintra-DP | 1
Mintra-Hanger 1200m2 | 1
Mivida-PK#140 | 1
Mivida-PK#140- Social Insurance | 1
Mivida-PK#140-DP | 1
Mivida-PK#189 | 1
Mivida-PK#189 - on account | 1
Mivida-PK#189 - Social insurance | 1
Mivida-PK#189-DP | 1
Mobilization
MOC | 1
MOC - DP | 1
New Gas Station | 1
New Giza Hospital | 1
New Giza Hospital-DP | 1
New Giza Hospital-On Account | 1
New Giza Hospital-Social Insurance | 1
NGU 2 | 1
NGU 2 - Retension release | 1
Old H1 remaining IPC
ORA - ZED | 1
ORA - ZED - Compansation | 1
ORA - ZED - Deficit | 1
ORA - ZED - DP | 1
ORA - ZED - On account | 1
ORA - ZED - Social Insurrance | 1
ORA - ZED - Landscape | 1
ORA - ZED - Landscape - Deficit | 1
ORA - ZED - Landscape - DP | 1
ORA - ZED - ph.02 | 1
ORA - ZED - ph.02 - Claims | 1
ORA - ZED - ph.02 - Deficit | 1
ORA - ZED - ph.02 - On Account | 1
PH.2-El Sewedy Uni. - Enabling | 1
PH.2-El Sewedy Uni. - Enabling - Retention release | 1
PH.2-El Sewedy Uni. - Finishes | 1
PH.2-El Sewedy Uni. - Finishes - on account | 1
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 1
PH.2-El Sewedy Uni.-DP | 1
PI Parks - ELSEWEDY | 1
PI Parks - MEP | 1
PI Parks - MEP-DP1 | 1
PI Parks - MEP-DP2 | 1
PK #107 | 1
PK #117 | 1
PK #117 - Social Insurance | 1
PK #22 - Social Insurance | 1
PK#22 | 1
PK#32 | 1
PKG#101 | 1
PKG#101- Social Insurance | 1
PKG#101-DP | 1
PKG#101-VO1&VO2 AP | 1
PKG#144 | 1
PKG#144 - Social Insurance | 1
PKG#144-DP | 1
PKG#162 | 1
PKG#162- Social Insurance | 1
PKG#162-DP | 1
PKG#163 | 1
PKG#163- Social Insurance | 1
PKG#163-DP | 1
PKG#177 | 1
PKG#177 - DP | 1
PKG#177 - on account | 1
PKG#177 - SWI 07 | 1
PKG#177- Social Insurance | 1
PKG#178 | 1
PKG#178 - DP | 1
PKG#178- Social Insurance | 1
PKG#205 | 1
PKG#205 - DP | 1
PKG#205-Social Insurance | 1
PKG#220B | 1
PKG#220B - DP | 1
PKG#45 | 1
PKG#58 | 1
PKG#85 | 1
PO#11687 | 1
Port Said Silos | 1
Port Said Silos - Foreigner Supply | 1
Port Said Silos - Local Supply | 1
Port Said Silos-DP | 1
Port Said Silos-On account | 1
Port Said Silos-Social Insurrance | 1
PSP Substation | 1
PSP Substation - Beni Suef | 1
PSP Substation - DP | 1
PSP Substation-Retention | 1
Rabigh Ext. - Piles | 1
Rabigh Ext. - Piles- DP | 1
Rabigh Ext. -Building | 1
Rabigh Ext. -Building- DP | 1
Radamis-Concrete | 1
Radamis-Concrete-DP | 1
Radamis-H1 Main Builidng | 1
Radamis-H1-On Account | 1
Radamis-Rooms Fitout | 1
Radamis-Rooms Fitout-DP | 1
Radamis-Villas Finishes | 1
Red Sea Museum | 1
Red Sea Museum - DP | 1
Ring Road - El Marg | 2
Ring Road - El Marg - Retention Release | 2
Ring Road - Mounib | 2
Ring Road - Mounib - refund | 2
Ring Road - Mounib - Social Insurance | 2
RO Apply -Mech- SSC | 1
RO Eriction | 1
RO Pump Room | 1
RO - Supply - Electric | 1
RO Supply -Mech- SSC | 1
RO 2 | 1
RO Pump room - SSC - price diff. | 1
RO.2 | 1
Rolling Mill #4-TRAESUEZ | 1
Rolling Mill #4-TRAESUEZ -AP | 1
Royal City | 1
Royal City - Landscape | 1
Royal City-DP 3 | 1
Royal City-DP 4 | 1
Royal City-DP1 | 1
Royal City-DP2 | 1
Saint Gobain Factory - DP | 1
SIEMENS - Sokhna | 1
SIEMENS - Sokhna - Bill | 1
SMP1 - Revamp | 1
SMP1 - Revamp - DP | 1
SMP1 - Shut Down | 1
SMP1 - Shut Down- Final Retention | 1
SMP2 - Shut Down | 1
SMP2 - Shut Down- Retention release | 1
SMP2 - Shut Down- V.O | 1
Sodic Club House | 1
Sodic Club House - Social Insurance | 1
Sodic Eastown | 1
Sodic Eastown - Landscape | 1
Sodic Eastown - On Account | 1
Sodic Eastown - Social Insurance | 1
Sodic Eastown-DP | 1
Sokhna Port Expansion | 1
Sokhna Port Expansion- 100m | 1
Sokhna Port Expansion 100m- Escalation | 1
Sokhna Port Expansion- EDECS | 1
Sokhna Port Expansion- Escalation | 1
Sokhna Port Expansion-AP | 1
Sokhna Port Expansion-internal roads | 1
Sports Hall - Civil Works | 2
Sports Hall - Finishes | 2
Sports Hall - Finishes - ADD.01 | 2
Sports Hall - Finishes - ADD.01 - Final Retention | 2
Sports Hall - Finishes - Landscape | 2
Sports Hall - Finishes - Landscape - Final Retention | 2
Sports Hall - Finishes - Social Insurance | 2
Sports Hall - MEP | 2
Sports Hall - MEP - DP | 2
Sports Hall - MEP - Final Retention | 2
Suez Intake & P Stations-ABB apply | 1
Suez Intake & P Stations-ABB supply | 1
Suez Intake & P Stations-ABB-Escalation | 1
Suez Intake & P Stations-SSC apply | 1
Suez Intake & P Stations-SSC supply | 1
Suez Steel Intake & P Stations-DP | 1
Suez Steel-Al Baraka-DP | 1
Suez Steel-Gas Station-DP | 1
SVC | 1
SVC-DP | 1
Uptown PK #53 | 1
Uptown PK #62 | 1
Uptown PK #62 - Retention | 1
Wady Halfa | 1
Wady Halfa - DP | 1
Wady Halfa - Escalation Claim | 1
Wady Halfa - Stoppage Period | 1
Western Fence | 1
Western Fence-PO | 1
Zayed Park

## per.project.from.invoicing
PROJECT_NAME | gross | collection from applied | on account from applied | collection
Cameron EDC | 1409056440.57 | 773758405.11 | 0 | 1096281358.71
Kuwait | 13536323.858 | 1767461.38 | 0 | 12713559.1
Al-Shabab PP Phase II (CP-117) | 380603266.9871 | 58079512.991 | 13422070.57 | 109626800.082
W Dam PP Phase II (CP-117) | 245502771.8865 | 30261523.9495 | 6230276.88 | 287163708.9192
Suez Gulf Substation | 208261732.1148 | 79853942.86 | 4204951.12 | 96371307.2074
Pyramids Industrial P - East | 109369646.39 | 7212729.5094 | 1317140.66 | 93902086.4194
Abou El Matameer and Sammanoud | 242506693.0599 | 148697097.4178 | 30540900.01 | 219776038.8278
Siemens 6x500/220 KV GIS-MOU | 236833915.9333 | 61408667.174 | 8233426.25 | 231704905.338
Barwa 2x60/22 KV S/S | 77119804.31 | 19127378.5 | 4058976.63 | 70408376.86
Damac 2x60/22 KV S/S | 79709614.77 | 20662527.71 | 4383510.76 | 74251539.01
IRAQ - Substations Soil Invest | 4427500 | 250000 | 0 | 4427500
Abo Quir - Badr 500KV | 984494567.01 | 1610918.88 | 522292.98 | 939049619.33
South Helwan PP (CP-117) | 241601719.2829 | 38825308.9239 | 1322935.32 | 238153777.8593
Abu Qir PP (CP-118) | 209115982.6846 | 4866874.3685 | 0 | 209121009.2136
New Capital | 187298763.911 | 86089668.29 | 11986710.66 | 171199012.547
Gabal Elgalalaa | 4861616.29 | 3761903.02 | 0 | 2625166.14
Berket Ghelion | 114687085.72 | 42408494.33 | 17750000 | 103845580.05
Beni-Suef Power Plant EPC | 17018424992.55 | 8580179538.32 | 0 | 15574453060.4533
Ismailiya East Substation | 111577500.48 | 104081380.13 | 12010128.82 | 116091508.95
Tamey El-amdeed Substation | 113026639.64 | 97733471.3 | 15811920.92 | 113545392.22
Beni Suef Substation R61 | 206446213.62 | 167261089.41 | 32143671.49 | 199404760.9
Al Mostathmreen GIS Substation | 62448724 | 53238536.94 | 9067391.25 | 62305928.19
Sodic Club House | 117882779.21 | 79939871.3505 | 18969504.0575 | 98909375.408
New Giza 2 | 56956316.78 | 49196980.979 | 7857711 | 57054691.979
EMAAR-PKG#53-UPTOWN | 208921390.67 | 161563851.3545 | 46884907.21 | 210390736.5445
EMAAR-PKG#62-UPTOWN | 45491143.52 | 31149418.2925 | 14325770.18 | 45530950.2625
EMAAR-PKG#107-MARASSI | 54747174.24 | 53560171.427 | 7782348.29 | 56258247.2
Beni Seuf - 358 | 1600886223.04 | 1013494114.04 | 256596415.41 | 1289319958.67
Kayan 3 New Cairo Capital City | 1499235324.85 | 633698716 | 288401173.6 | 1385572741.03
Giza North PP Ph I,II (CP-117) | 90175908.7526 | 7739955.7 | 0 | 90396053.784
K047 FDH JV | 6447528.49 | 526761.34 | 0 | 6386111.92
Royal City | 567527944.71 | 425704643.6985 | 114263247.3955 | 557611698.604
New Heliopolis | 192716394.74 | 116534682.7 | 14474147.83 | 176328647.75
Barwa and Damac 220 OHTL | 50019378.61 | 29258725.93 | 6152780.36 | 44412352.72
Flour project | 430726.191 | 430990.846 | 0 | 430990.846
Beni Suef ISKRA | 383886219.7424 | 14496330.07 | 127864.08 | 383886219.7424
Apache Electrical Works | 80661450.8904 | 1610713.79 | 0 | 80543139.3304
Tunnel of Sokhna Road | 46639506.13 | 23801416.2 | 2567657.25 | 44145480.45
Ghana | 93038488.89 | 6432541.61 | 0 | 93038410.07
Military 110 Kayan Project | 409459172.32 | 332032518.49 | 0 | 351532418.49
Kuraimate - Samalot 500KV | 14190780.39 | 22053.6 | 0 | 22053.6
Amal Bridge Lock & Load | 27171634.86 | 14139802.35 | 6948500 | 25617054.15
Akhmem Assiut | 1443367941.9306 | 910146753.1252 | 138950529.51 | 1212671440.2904
Akhmem - Qena | 1818551946.78 | 945304444.3787 | 150171876.23 | 1565006976.9587
Bani Suef Old Substation | 40914797.66 | 46210913.05 | 8526864.73 | 54812271.28
El Mostakbal City Project | 642419542.35 | 396040189.56 | 112727272.73 | 509325572.29
Badr | 459347760.81 | 312401622.94 | 68902164.14 | 381303787.08
Mohamed Ali Palace Restoration | 143922090.22 | 98880476.9965 | 25092298.36 | 123972775.3565
Assuit PP (CP-118) | 147041487.7897 | 128971189.7478 | 11143451.46 | 153821251.3969
Marsa Matrouh 500KV | 2004925351.68 | 1683106444.2112 | 151773074.2 | 1869885772.2612
MAYSAN 400/132kV SS | 53868592.59 | 66513253.13 | 0 | 53867781.5
MOTHANA 400/132kV SS | 45522223.55 | 45423445.43 | 0 | 45522223.55
SHAT Al ARAB 400/132kV SS | 47550798.05 | 47511347.34 | 0 | 47517812.62
Cairo Capital S1 | 1360482061.56 | 991727933.15 | 173429262 | 1232092543.72
Ministries Buildings | 2735149638.69 | 912122894.49 | 682978287.085 | 2271208309.165
EMAAR-PKG117- MARASSI | 46843952.64 | 44469964.9617 | 4130124.14 | 48600089.1017
Attaqa Power Plant | 4896336601.31 | 359300934.96 | 0 | 4896020976.96
Substation Elco Steel | 32341773.85 | 25359653.55 | 6647052.2 | 32006705.75
EL-Hegaz Square Bridge | 131409370.11 | 0 | 83260470.12 | 122359240.12
New bridge Ismailiya Nefisha | 70928098 | 24075766.2 | 12103989.25 | 63297485.45
P-28-16 Balat Owinat Lot 3 | 196046030.58 | 142278641.36 | 20471770.7 | 162750412.06
Elsewedy Univ - Enabling Works | 267595441.71 | 299348859.386 | 91170255.86 | 276806743.972
NUCA R05 - Z02 | 2046636158.36 | 1644416035.3565 | 291537847.34 | 1922990748.9965
R5 Mix-Use Complex Project | 82769789.46 | 79983946.1025 | 9832887.76 | 89816833.8625
Beni Suef COMCAVI | 615794724.6172 | 615436297.4772 | 556960.24 | 615794742.2672
Canal Regional Control Center | 114658054.95 | 72033902.88 | 24078191.54 | 96112094.42
P-28-16 Balat Owinat Lot 2 | 192274213.75 | 137161629.51 | 22895067.14 | 160056696.65
El Boghaz Brigde | 41054346.25 | 17754485.05 | 0 | 37959127.64
PIP- Zonafranca | 104243617.76 | 13174716.3368 | 15256668.32 | 84934708.9368
AWEER POWER STATION 'H' Phase | 461506367.295 | 585117795.2507 | 46826855.1866 | 431942608.3638
EDNC Retail & Offices Civil | 1145187121.17 | 867196309.172 | 162497088.7825 | 1040114019.5145
New Capital Tunnels | 344545653.1 | 93964074.95 | 80295874 | 324117340.95
EMAAR-PKG# 101-UPTOWN | 50727362.381 | 32861329.1491 | 19136167.75 | 51997496.8991
Mall Of Egypt | 70084387.43 | 33466116.9 | 0 | 55715016.9
Asec Spare-Parts | 8521869.55 | 6676728.4 | 2852953.42 | 9529681.82
DPW Onshore Port & Terminal | 1677911074.56 | 1272524392.42 | 241563831.8 | 1580870935.41
C5 Bridge 2 New Alamein | 26669335 | 12900552.47 | 0 | 26235219.97
Manshiet Nasser Substation | 81596495.4624 | 55610102.84 | 5210172.47 | 68211543.37
Zafranaa - Ras Ghareb | 64420361.28 | 9785281.7 | 0 | 52339877.58
kayan wall lock & Load | 95593680 | 70218652.85 | 18956654.4 | 89175307.25
Abu Sultan Road Extension | 18772993.25 | 2280393.35 | 2216936.85 | 15777805.2
RME-Abu Sultan Bridge | 1905550 | 1874644.5 | 0 | 1874644.5
Development of Mahmudiyah axis | 15101550 | 7338000 | 0 | 14875500
EMAAR- Pkg 140-ITP-Mivida | 174061648.74 | 156885863.687 | 22881566.9 | 179767430.587
HAC CCC JV | 20678226.27 | 8880000.41 | 0 | 19594897.114
EMAAR-PKG# 144, Marassi | 176420375.18 | 147279720.6915 | 31806339.73 | 179086060.4215
Mauritania-Lot 2 | 11235938.14 | 10272940.42 | 0 | 10274728.22
Mauritania Lot 1 | 8359738.108 | 7529984.5 | 0 | 7627332.39
Air Defense College | 1364003685.13 | 344617664.95 | 701443160 | 1036631293.75
Alamein Coastal Road Bridge | 258031564.78 | 58773095 | 46800000 | 238719874.9995
Benban 500 K.V/95 K.M | 442287950.21 | 302499140.5 | 58233985.08 | 387824237.51
Benban 500 K.V / 100 K.M | 625325224.14 | 495419831.07 | 62442279.38 | 557862110.45
Canal Sugar OHTL | 108416926.98 | 81235370.52 | 15454924.2 | 96690294.72
Canal Sugar S/s | 174722130.42 | 137970556.9 | 25474645.72 | 163445202.62
Tunnel of Sokhna Road (2) | 22334150 | 8913422.15 | 7352144.9 | 20062843.05
4 SS - Technical Service | 4445015.37 | 4445015.37 | 0 | 4445015.37
AbuSultan Rd Bridge2 Extension | 78713413.82 | 26645454.35 | 14045300 | 72065904.35
Road El Farag Axis | 633576 | 264330 | 0 | 609128
Port Said Subs 220/66 | 498984444.18 | 315829840 | 119246116.21 | 435075956.21
Zambia Project | 4490504.84 | 3618005.2 | 0 | 4123974.04
Elco Steel 220/33 KV SS | 64545092.89 | 88945451.247 | 0 | 67639660.887
Latin Quarter- New Alamein | 38015254.5 | 18123757.69 | 0 | 18123757.69
Latin Compound - New Alamin | 14168000 | 9191995.53 | 1433452.53 | 10625448.06
Safeer Square Bridge | 95036406.14 | 12232717 | 29045117 | 87430959
LAYYAH CCPP | 333837189 | 212425820.27 | 75730261.29 | 330854925.56
DoubleTree Mangroovy ElGouna | 61162018.58 | 53680877.982 | 13625000 | 67305877.982
Nagaa Hamady/Assuit OHTL | 69385450.54 | 48931743.23 | 7289855.41 | 56226598.64
Fish Market | 66386978.19 | 14175764 | 25141375.6 | 45418239.6
Marsa Alam/ Bernes LOT2 OHTL | 285180307.315 | 199276635.5805 | 27851834.28 | 226076607.1855
Port Saad Industiral zone | 64487325.68 | 31035530.77 | 0 | 63312643.61
Canal Sugar 33KV OHTL | 66627697.44 | 54182156.34 | 7921350.47 | 62670026.83
33KV Canal Farm Grid | 269814188.28 | 207161160.71 | 37906847.03 | 245068007.74
Celia | 4900668.75 | 2024802.25 | 0 | 4724112.0147
HyperOne Zayed Extension | 131528902.2 | 90790688.775 | 33750000 | 131985104.1815
Safir bridge | 4274050 | 837650 | 75000 | 4190025.6
Asher Mn Ramadan Bridge No2 | 93780498.34 | 17596560 | 19922914.7 | 84876302.7
OHTL Mostakable East Boundary | 35112112.9 | 28497039.41 | 8019551 | 36516590.41
El Katameya Mall | 6577144 | 4686935.27 | 266914.67 | 5167153.94
ESU Ph2-Enabling & Struc | 608748208.71 | 372525071.886 | 122745710.8 | 556024093.9065
Cairo Capital Cables Tunnel | 305724503.3 | 204170257.55 | 76431125.96 | 280601383.51
Mahmoudia Additional Scope | 76864687.5 | 56408999.87 | 400000 | 56808999.87
IKEA Extension MoA | 200594718.8 | 156723470.129 | 40155862.02 | 196879332.149
Benban 3/ Toshka 2 LOT 4 | 787582711.18 | 623336380.92 | 72024522.16 | 695364313.89
CFC Podium 2 | 637419839.06 | 562651733.4145 | 93202416.55 | 655854149.9645
Badr 500 S/S / Zizenia 220 Kv | 39937398.45 | 24913584.3 | 9984349.61 | 34897933.91
Nuweibaa (Swro) | 7460261.55 | 5006560.794 | 1251640.206 | 7460261.55
Wadi El Natroun | 13006329 | 5048026.25 | 0 | 11178286.25
Museum of Egyp. Civilization | 15647404.4643 | 7320866.25 | 0 | 14782180.2336
ORA Zed Park LOCK&LOAD | 1017939.05 | 898331.2025 | 0 | 898331.2025
marassi inland marina | 25043946.96 | 8526037.16 | 0 | 23261778.27
Toshka GIS 500 kV | 330263259.63 | 196531345.42 | 86687433.41 | 283244196.93
EMAAR-Pkg#162/163- Marassi | 860066867.1254 | 628554886.1548 | 234104329.154 | 862659215.3088
Juba PV | 20000000 | 20000000 | 0 | 20000000
Elmaragha Bridge - Sohag | 4371196.1538 | 1277703.5 | 0 | 3635345.0769
Multi Sport Hall | 3867096 | 1859765.75 | 0 | 3744230.75
Villa Fabio | 115868.95 | 62300 | 50000 | 112300
Ministries Building ROOF | 839243.28 | 394444.34 | 0 | 814065.98
Rail Way Tunnel Zagazig | 4045600 | 1885249.6 | 0 | 3908049.6
Maspiro Towers | 7515950 | 3534709.31 | 0 | 6463514.71
Vila Palm Hills | 65347.64 | 3900 | 50000 | 53900
Sodic East | 16611875.46 | 5356573.0073 | 333555.67 | 15255043.3573
SHATRA 400/132kV SS | 50992622.01 | 50992621.84 | 0 | 50992621.84
Miscellaneous Projects | 48845789.86 | 10147486.7102 | 0 | 48077394.5507
Air Defence College | 10029138.96 | 8117171.574 | 0 | 8438744.574
Angola Emergency fast-track | 489409941.28 | 175185552.07 | 0 | 388432997.23
LAYAN Substation | 42441086.0252 | 62716436.2608 | 0 | 35533737.6007
R5 | 23937000 | 6497632.7033 | 0 | 16839160.72
Olympic Multi – Sports Hall | 1041770776.43 | 213689000.03 | 574296835.65 | 898871140.68
Banha PP (CP-117) | 43119813.9795 | 12252.61 | 0 | 35620295.73
Minis Building(Polyurethane) | 6171801.96 | 2711384.87 | 0 | 5829709.1
Ministries A13-A14 | 1169751 | 795393.12 | 0 | 1048794.12
Suez Gulf/S4 - 500KV OHTL | 123458202.54 | 88963728.29 | 8718565.8 | 97682294.09
Oasis Buildings- New Capital | 14774450 | 13497722 | 0 | 13497722
Elhegaz | 44283419.72 | 19094677.06 | 0 | 43741495.82
Ministries A17-A18 | 2516664 | 2126834.216 | 0 | 2126834.216
Ain-Sokhna PP (CP-117) | 73234691.82 | 2120232.25 | 0 | 73245792.96
Mohamed Ali Palace | 788110.6 | 361743.078 | 0 | 686355.478
Ameria | 2073600 | 798670 | 0 | 1895470
Racecores 3092-16 132KV C | 27529985.1013 | 64122333.4613 | 0 | 22974416.0749
Mostakbal 2 Package No. (8) | 153391444.51 | 125446865.61 | 32211153.34 | 157658018.95
Mivida | 2542945 | 1120000 | 100000 | 2348062.5
Almaza Bridge - Safir 2 | 945772.5 | 50000 | 0 | 902088.5
Group # 1 - 25 LX | 5497900 | 5442921 | 0 | 5442921
Daraw Bridge | 7157120 | 2950000 | 0 | 6528560
El-Moneeb Bridge | 5269500 | 2622349.31 | 0 | 5257099.31
Cairo-Alex Railway | 1111529051.63 | 738094434.81 | 144582383 | 911878107.725
Racecores 3092-17 132KV E | 21579766.1551 | 73998844.8722 | 0 | 18031597.6139
Lekela 250MW Wind Farm | 233203769 | 186351528.7395 | 49581010.08 | 235932538.8195
EMAAR-PKG#22-MARASSI | 1232045.42 | 1228735.201 | 15499.05 | 1244234.251
ORA ZED - Ph 01B - Pkgs A&D | 956060987.36 | 701913808.7171 | 189380773.32 | 919974319.8581
Vila Fabio (North Coast) | 42750 | 42750 | 0 | 42750
10th of Ramadan Railway | 14592782 | 8170896.66 | 0 | 13185003.66
RING ROAD MARYOTIA EXPANSION | 704980256.49 | 497936633.536 | 34159591.2 | 628048404.942
ElSewedy HQ Internal Finishing | 379959726.32 | 164055422.0915 | 113231198.179 | 385239348.583
El-Nyaba El-Ama | 5861594.2 | 4785622.75 | 439619.6 | 5225242.35
Toshka-04 GIS Substation | 173971316.91 | 132744402.14 | 18210360.39 | 150954762.53
ORA-ZED Towers01B | 1504439.21 | 583617.61 | 0 | 1384621.82
Kattameya Creeks | 2027599304.12 | 1821158928.6402 | 282184075.91 | 2104143819.5502
Taval Sarai 52 | 10857726.95 | 6463165.784 | 0 | 8141065.519
Azab Tex Factory | 1271350 | 1247925 | 0 | 1247925
Lahoon 220/22/22 | 211870699.07 | 45153747.85 | 49482104.95 | 108573132.1
MR3 Bridge L&L | 1778990.75 | 714789.99 | 714792.5 | 1429582.49
2B3 | 75000 | 75000 | 0 | 75000
Mangrouve Hotel - Gouna | 81168.18 | 32994.97 | 0 | 76961.97
ITS | 17999800 | 8999900 | 0 | 17999800
Suez Bridge | 387860 | 188112.1 | 0 | 382042.1
Coastal road Bridge Extension | 12526155 | 11919727.29 | 0 | 11919727.29
Koning Food V2 - LP-08-20 | 140461.37 | 175535.99 | 0 | 160125.99
BKG#178-Lagoon Discharge | 48731447.35 | 45164066.1075 | 3747170.2 | 48911236.3075
Babil WBS | 24800 | 24552 | 0 | 24552
Hassan El Mamoun Bridge | 100523370.39 | 19100390.003 | 28019639.88 | 83818869.883
LRT Project | 766498.65 | 461000 | 0 | 667400
EGAT Pelletizing Plant | 798933395.04 | 686543794.1165 | 125689684.11 | 833859409.2245
LRT | 3621240 | 2416901.12 | 0 | 3194981.12
West Port Said 220 kV GIS | 130733416.78 | 66994724.0034 | 13726483.76 | 80721207.7634
New Babil 400/132KV Substation | 7110251.33 | 1910251.33 | 5200000 | 7110251.33
National Batteries LP-05-20 | 5307018.08 | 4330393.6 | 660000.49 | 4990394.09
Zone(J) South Valley Toshka | 709779608.38 | 525668042.5 | 90000000 | 615668042.5
Ahl Misr Walkway | 3474606.5 | 3223103 | 0 | 3223103
Koning Food V3 LP-09-20 | 207638.6 | 59177.02 | 59177 | 222173.32
GOV2 - Infra | 420059706.25 | 392228451.1525 | 52130848.54 | 444359299.6925
Corporate Project LP-02-21 | 224640.7 | 175270.05 | 80820.35 | 256090.4
Industria Sadat | 157021007.56 | 123696070.9 | 28065293.42 | 175138117.52
Al Montaza Hotels - Alexandria | 16152978 | 15407575 | 0 | 15407575
Bridge Axis Firdaws | 10764000 | 9723948.6618 | 0 | 9723948.6618
UIC Project (LP-04-21) | 955987.5 | 0 | 0 | 955987.5
Cairo Monorail - 6th October | 15498700 | 13584877 | 0 | 14855877
ORA ZED-Ph 2-Pkgs A&D | 452012507.88 | 350432311.4306 | 53631256.38 | 449576270.4026
Bahr ElBakar – Power Station | 17976376.95 | 12600458.94 | 0 | 17131160.94
Shenzo Aby Bridge - Haggana | 1553600 | 1387328.5 | 0 | 1387328.5
Toshka 2/Owinat East LOT2 OHTL | 139638562.84 | 107744456.82 | 14662049.12 | 122406505.94
Diplomatic District - Infra | 432031986.9348 | 353352194.5057 | 32500000 | 385852194.5057
Air Force Project | 176814289.25 | 126590178.6 | 44202305 | 170792483.6
Faculty of Medicine | 584199684.06 | 437364874.5428 | 60402014.01 | 497766888.5528
October Dry Port | 110921341.4 | 76062663.16 | 29115540.18 | 105178203.34
Hosh Essa 220 KV OHTL | 77430416.17 | 45332245.23 | 8122374.6 | 53454619.83
seashell Playa | 11233389.54 | 8952111.3651 | 488000 | 9440111.3651
Capital One | 12347930.4738 | 9725437 | 400000 | 10439481.9
10Th of Ramadan LRT | 35830626.02 | 14710721.62 | 3268051.72 | 21123882.14
New Babil 400/132KV GIS Substa | 36031203.56 | 35326677.27 | 0 | 36031203.56
Mansoura University | 2648278.5 | 2061156.66 | 0 | 2564898.3
TZ – Offshore E&M Procurement | 15762675.1 | 7741736.06 | 1185303.64 | 9155070.86
P.I.Parks - Plot 10 | 10077092.59 | 26190404.4 | 3331715.08 | 29522119.48
Playa Resort | 616560887.3767 | 30146763.71 | 1023769353.412 | 623044009.512
East Owainat 5 LOTS | 613805231.54 | 249214473.88 | 322247746.52 | 571462220.4
El Salam Bridge | 5425110 | 2102646.77 | 0 | 4640856.77
Transportation Hub | 2541840 | 2453890 | 0 | 2453890
Railway Bridge - Assuit | 14685590 | 11958930.23 | 0 | 11560842.23
ElMoneeb 2 | 3674678 | 1965776.24 | 0 | 3418645.97
MDF Factory | 728463652.27 | 484849824.3287 | 241614980.71 | 760890341.3267
Ain Sokhna Port Development | 25980370 | 20931308.95 | 0 | 22274682.33
Ras El Teen Hangar | 11187821.08 | 9143692.13 | 2149294.27 | 11292986.4
AMRIYA WWTP (3RD STAGE) | 11865039.21 | 10138331.2 | 1186504 | 11559935.81
Mar Girgis Church- R3 | 185600 | 185600 | 0 | 185600
ENR-Signaling Inst. | 14647397.56 | 12299614.32 | 1464239.76 | 13763854.08
Al-Ula Towers | 3377825.41 | 2049098.6 | 0 | 3219963.4205
Toshka Farm | 105914109.11 | 53987241.7 | 46123502 | 100644077.03
158E/2019 33kv Project | 7423987.9508 | 10468096.1838 | 0 | 5867110.0738
Ahl Misr P3 – Zamalek Sector | 4831400 | 3068149.99 | 0 | 3919549.99
Ain Sokhna Bridge – RME | 12102126.3 | 8942818.56 | 0 | 11760782
R06 Loack & Load | 1050000 | 997500 | 0 | 997500
Governmental Campus-N2 | 9287134.95 | 5027920.7191 | 2543859.68 | 7571789.3991
Waldorf Astoria Cairo | 248450534.47 | 130550580.4505 | 82871540.1 | 258241670.672
Ext.110 S. Military 220 Kv S/S | 66247238.25 | 42328625 | 15711854.52 | 58040479.52
El Taameer Axis Expansion | 8238010 | 7923222.67 | 0 | 7923222.67
Pridge 5 | 4600300 | 1964967 | 0 | 4065267
Get Business Complex | 21979055.4 | 6659800.06 | 0 | 12062255.5
10th Ramadan Indu Park Plot11 | 26194543.65 | 58196900.83 | 4124852.96 | 62321753.79
Ring Road Bridges Project | 15757374 | 7172042.83 | 0 | 7462989.36
Sokhna Port Expansion | 1235871108.69 | 821763237.5403 | 204058952.7 | 1099774686.3873
Port Said Grain Storage | 13547450 | 6458744.9 | 0 | 11173109.93
New Giza Teaching Hospital | 598028482.65 | 331478318.6905 | 107508305 | 490622640.5855
Egat Rolling Mill no.4 | 655745909.65 | 553389160.6256 | 108750000 | 682166482.4471
EGAT Lock & Load | 55000000 | 51799999.9913 | 5400000 | 57199999.9913
Egyptian Exchange building | 688299294.645 | 71603906.0342 | 82622000 | 647930503.0482
Port Said Port Silos | 253501552.4501 | 302243665.0889 | 41815819.3684 | 232074651.392
PLAYA ROOF & Wet Areas | 4598904.163 | 3478088.653 | 0 | 3908623.083
Port Saeed East - OHTL | 17170883.4 | 13969435 | 0 | 13969435
Houd Negaih | 1961673.81 | 1360213 | 205450.75 | 1565663.75
Luxor North Axis Bridge | 6556269 | 5913025.38 | 0 | 5913025.38
Mivida BP#189 | 764903424.19 | 688857877.1595 | 137838332.85 | 847858887.9735
Abou Ghaleb Bridge | 187067556.6 | 114672212.5416 | 0 | 152746828.9416
The Open Channel Project | 652923847.43 | 144720910 | 319441531.19 | 464162441.19
Ora Zed Landscape Ph1 | 62492502.6725 | 50281542.3847 | 6814705.14 | 59425125.9354
Beymen Fit Out | 18645405.16 | 10080095.7995 | 7461363.96 | 17541459.7595
West Domiatte 500KV TowersZT60 | 2452240.2 | 1873789.17 | 0 | 1873789.17
Ghana Street lighting | 4029825.99 | 3355950.93 | 0 | 3656869.62
Luxor North Axis Bridge-Off | 10963774 | 7883016.08 | 0 | 10642070.48
Infra Project 2524 | 426101328.57 | 166837109.05 | 0 | 348617539.5445
EGAT New Rolling Mill 4 | 1143460 | 823066.73 | 0 | 1028833.41
EDNC Hardscape Package | 70642868.33 | 42631677.4485 | 0 | 49904730.9985
WADY EL-NATROUN BRIDGE(HST) | 15922122.49 | 13463075.05 | 0 | 13737156.44
LINX Tower | 3647739 | 3260882.96 | 0 | 3277229.2517
SSC Suez Steel Company Project | 509732084.17 | 317990889.9809 | 125641703.26 | 478096692.3709
Astoria Sharm elSheikh | 6619935.92 | 5518079.8735 | 1365525 | 6883604.8735
EPICO 3 Facility | 655977489.41 | 399756244.2355 | 168482074.8 | 638495152.4515
BridgeNasr Rd w Abbas El-Akkad | 124958229.6 | 14634905.01 | 29800000 | 105900595.01
CS-20 Mall | 7204770.25 | 3132692.28 | 0 | 3132692.28
Railway Bridge - El Hammam | 7042688.9 | 6180321.11 | 0 | 6180321.11
HST Bridges-Sokhna & Mahager | 548209975.42 | 290053523.1082 | 0 | 469352413.2082
EL -mahager Bridge Ain sokhna | 9641500 | 5803629.68 | 0 | 8369674.48
Expansion of Ring Road NRCC | 1933635 | 1179725.3 | 0 | 1349660.3
Creeks URBN-K | 335774638.69 | 210382164.7719 | 124558950 | 334941114.7719
ORA-ZED Towers P01B | 3826567.58 | 3213424.27 | 0 | 3213424.27
Kemet Tower | 1906240 | 986237.16 | 0 | 1356477.16
Ring Road El Mansoria | 945180 | 648244.56 | 0 | 648244.56
MAF HQ Renovation | 32667996.6 | 21908247.2798 | 8561052.22 | 30564853.2168
U4,U8 Seashell Playa | 7371939.63 | 5917260.14 | 0 | 5917260.14
Katameya Creeks - RME | 3928711.98 | 3320058.3735 | 0 | 3452956.4135
El-Herafeen brigde | 2507885 | 1014190.58 | 0 | 2277425.58
Hyper One Badr | 6369675.61 | 5382750 | 0 | 5382750
HST - 6 October - Arab Cont. | 15411550 | 8269909.39 | 0 | 11198409.39
U3 & U5 | 7912642.42 | 3456514.86 | 0 | 7068296.15
Irrigation Tank | 7123091.19 | 5755812.52 | 0 | 5755812.52
HSR-6th of October | 8912474 | 7327647.07 | 0 | 7327647.07
EGAT Mechanical Installations | 97797506.35 | 74374136.8627 | 24449376.7436 | 98823513.6063
Business District Hyde Park | 7544473.94 | 3222962.25 | 0 | 6961234.19
DP World Basin 2 Ph2 | 503944643.92 | 390826588.3987 | 65057898.42 | 487211772.2687
Wady El Natroon Bridge | 323975961 | 140089801.2879 | 0 | 272524703.4879
Abo Shanab El Agamien | 50867570.62 | 55268292.61 | 8589895.1 | 64872665.71
Seashell Playa 5 Villas | 8244809.69 | 6110474.19 | 0 | 6317328.0762
East Port Said Industrial Area | 386092 | 199065.45 | 0 | 199065.45
El Khatatba Bridge | 171300222.12 | 113981141.2446 | 0 | 141877537.2446
SOL Town PKG.220 | 50481629.15 | 17460291.28 | 7500000 | 51889073.8426
British International School | 53630305.09 | 34572809.42 | 9399724.44 | 56669978.12
SEASHELL TECHNICAL ROOM | 1070368.24 | 888419.97 | 0 | 888419.97
Wadi Halfa Port | 129542558.46 | 72591764.2764 | 12277523.52 | 123224509.2954
Sixty Iconic Tower | 12318245 | 11170383.65 | 0 | 9890551.25
Al-Parco | 33504153.01 | 12255000 | 0 | 19522824
Venice Mall | 134640 | 127445.6 | 0 | 127445.6
Tarek Abdel-Hakim Center | 40629339.49 | 26686063.22 | 3141590.17 | 35550435.32
Monoril | 3529420 | 1206530 | 0 | 1206530
ora zed orascom | 4705093.46 | 3800610.59 | 0 | 3800610.59
KATAMYA GREEKS LAND SCAPE STAR | 16876031.87 | 15489461.642 | 0 | 16697415.732
VILLA CLUSTER C | 574034.84 | 419436.5 | 0 | 419436.5
VILLA CLUSTRER B | 1527299.77 | 1286802.32 | 0 | 1286802.32
Jawhara Palace Restoratio | 16481760.03 | 10900899.91 | 4120440.02 | 15021339.93
Blue Planet Sharm. | 3067328.84 | 2772865.27 | 0 | 2772865.27
U6T11 PART1 Palay | 40617.5 | 37108.14 | 0 | 37108.14
New Giza Hos | 121747.6 | 108068.03 | 0 | 108068.03
EGAT Injection | 4642165.11 | 3932050.34 | 0 | 3932050.34
Ain Sokhna Bridge | 33645564.96 | 3919579.69 | 0 | 4252704.19
EIPICO Factory | 399973.68 | 338107.63 | 0 | 331909.36
U7-SEASHELL | 5638283.45 | 4384037.65 | 0 | 4408673.11
Qasr Rashwan - Lot B | 62447646.18 | 93737187.04 | 11146475.84 | 104883662.88
EIPICO C002-23 | 1467308.05 | 1245231.96 | 0 | 1245231.96
Central Capital | 689580 | 517500 | 0 | 551484
ZED Phase 2 | 585501.253 | 333679.62 | 0 | 333679.62
ACWA POWER & NOMAC HQ | 387708.71 | 284459.5267 | 0 | 374594.6506
R05 (New) | 1183367.7467 | 900217.64 | 0 | 854972.7067
EL Baragil Bridge | 10457265 | 6750000 | 0 | 6750000
RADAMIS CITY | 2131333.81 | 1819972.1 | 0 | 1819972.1
Haramein Columns Transfer | 6314496 | 624000 | 576000 | 6266496
Tarek AbdelHakim Center - KSA | 25996512.73 | 0 | 0 | 28708009.9
PLAYA Main Gate | 155883 | 134620.56 | 0 | 134620.56
Open Channal | 2085284.06 | 1272216.25 | 0 | 1566584.51
Koumassi Flyover | 5701286923.44 | 5636632897.23 | 0 | 5242626827.49
Main Spine | 1150178.1 | 972394.1 | 0 | 972394.1
Senator | 1227760 | 376000 | 0 | 376000
Al Alamein Marina Towers | 2925310 | 1868125.47 | 0 | 1868125.47
HSR | 396401563.89 | 5947537.45 | 292260480.051 | 342499377.281
Olympic MultiSport Hall | 265070.4 | 223056.74 | 0 | 223056.74
Ring Road - Service Road | 51494873.04 | 25068039.5 | 0 | 45068039.5
Roubiky Hassan Allam | 1888837.5 | 1500000 | 0 | 1500000
BISC New Society Bldg | 2946690.48 | 1732655 | 928207 | 2660862
Rabigh CCPP-Civil | 10359504.61 | 40265868.86 | 0 | 11913430.29
Open Channel 2 | 9060009.57 | 4347012.79 | 0 | 8324272.79
Sultana Malak Restoration | 157963085.25 | 42701032.4 | 83888859.26 | 126589891.66
Red Sea Museum-Bab El-Bunt | 5442183.62 | 18775533.51 | 0 | 6258511.17
Open Chanel Epoxy | 2681280 | 2037397 | 0 | 2037397
EGAT ADMIN (Pelletizing) | 472545.4 | 354700.61 | 0 | 354700.61
MDF Factory - Sadat | 670048.6 | 554719.63 | 0 | 554719.63
October Under-Railway Tunnel | 50346091.04 | 40122061.9 | 0 | 45564348.295
Pushing Tunnel | 16050250 | 12870207.02 | 0 | 12870207.02
Kafr Shokr Bridge | 206789507.09 | 103747101.77 | 0 | 206476062.3111
Roots -Kafr ElSheikh Bridge | 461941.5 | 0 | 0 | 461125.5
El Zagazig Railway P2 | 978960 | 89750.4 | 0 | 579230.4
FX-04-22 U.Communities-UE | 388352.49 | 0 | 0 | 0
Giza North PP Phase3(CP-117) | 54593098.5868 | 2530937.82 | 16996.17 | 53520647.16
AIRDEFNSE -EPOXY | 1881324.8 | 1262643.22 | 0 | 1262643.22
Cairo North PP Rehabilitation | 24736.902 | 259586.28 | 23278.95 | 1717574.2241
FX-02-22 Decent Life-UE | 4463829.83 | 0 | 0 | 0
Palm Hill-Infra Str(Elec.Work) | 8413366.36 | 0 | 0 | 8488703.556
Baron Palace | 64064 | 22681.484 | 0 | 61260.684
Sewage Treatment Plant | 7138247 | 1260000 | 0 | 5088416
ARAB ALMADABEG WWTP 105000 CMD | 49386084.14 | 15510764 | 4595743.2 | 21153072.35
LP-09-22 Koning Buzz | 635778 | 0 | 0 | 0
Hadaek ElAharam | 2429360 | 866790.56 | 0 | 2081470.56
Guinea 2 | 11554466.6 | 0 | 0 | 11554466.6
6th Oct. Ph2 PP-Elect Work | 13474738.07 | 157479.07 | 0 | 13474738.07
SHUQAIQ High Voltage Works | 6493362.2 | 0 | 0 | 0
MOC HQ at Diriyah | 72346246.462 | 0 | 0 | 53171489.69
FURJAN Cable Works | 12311404.8 | 132896550.4233 | 0 | 11574893.3055
FX-05-22 Close compound | 388933.64 | 0 | 0 | 0
Berty Badr Bridge | 785593.67 | 400000 | 0 | 400000
Cameroon EAR | 287923.24 | 0 | 0 | 287923.24
Infra Project 4514 | 133333333.33 | 0 | 0 | 0
Almaza | 60117290.42 | 2862672 | 0 | 59974103.15
LP-07-22 Koning GPS | 13650 | 0 | 0 | 0
Residence 8 ( S05 ) | 1470711.35 | 0 | 0 | 1470711.35
Residence 8 ( k12 ) | 1043507.18 | 0 | 0 | 1043507.18
Containment Data Center- | 75680574 | 14645486 | 4875129 | 51203149.78
Railway Bridge - Alex | 1515464.85 | 0 | 0 | 1515464.85
Masr ELgedeeda | 3441875 | 1649518.18 | 0 | 3370455.68
Abu Qir PP (CP-117) | 57099292.6033 | 7822632.81 | 0 | 56958659.48
Cairo South PP Rehabilitation | 6744662.0539 | 360496.41 | 0 | 6744662.0539
Al-Wukair 11 Substation | 361970981.4165 | 79151252.52 | 0 | 355285762.0065
Strining Lot A- Elegect | 3115848.96 | 1237316.99 | 0 | 3010237.805
Ismalia Bridge | 56527473.95 | 26717991.85 | 15714159.36 | 53117044.21
PIP Zona 2 | 71197648.68 | 33462894.917 | 0 | 69061719.257
Pyramids Industrial Park | 50488441.48 | 3315354.2615 | 0 | 45596592.5615
West Damietta PP Phase I | 10017263.9 | 944377.9 | 0 | 19090149.9
Tebbin PP Rehabitation(CP-124) | 29797247.42 | 5010092.81 | 0 | 25146780.45
Lina Farm Substation | 55797864.701 | 9152806.24 | 0 | 55797864.701
Baron Fence | 13543383.34 | 8026455 | 4588337.35 | 12614792.35
RME- Marassi Sidi Abdel Rahman | 150000 | 150000 | 0 | 150000
Suez IPB | 7080380.3098 | 121373.17 | 0 | 7080380.3098
Neighborhood New Capital R5 | 8117160 | 6520951.56 | 0 | 6520951.56
Alamein | 54325746.8 | 49607551.5 | 0 | 50569646.74
Mohamed Aly Fahmy Lock&Load | 6646200 | 2119060 | 3805194 | 5924254
Beni Suef Add-on Sales | 8337288.52 | 10811470.658 | 0 | 9544049.338
Lock&Load-30June w Sokhna Rd | 1030928 | 454415 | 454429.05 | 908844.05
Dubai Port | 184381.8 | 81373.3075 | 0 | 173564.2075
Mountain View | 101817.9 | 20709 | 75000 | 95709
Albatross | 132750 | 0 | 100000 | 100000
Marsa Allam | 79719.95 | 49636.0088 | 40000 | 89636.0088
Ministry Building EPOXY | 259497.74 | 121963.94 | 0 | 251712.81
Club House-Sodic Wesset | 353100 | 116523 | 0 | 351923
Abbas El Akkad Bridge | 800030 | 40001.5 | 0 | 748428.06
Banha PP (CP-118) | 11223545.5143 | 786021.26 | 0 | 11230161.7243
Tanzania hydropower Project | 1354999.67 | 1098911.62 | 0 | 1098911.62
LRT - El Shorouk Bridge | 8237000 | 3517446 | 0 | 7635946
ElMarg | 2235650 | 1039555.5 | 0 | 2214824.5
Shorouk Bridge-LRT | 23284983.4 | 11500000 | 8000000 | 19500000
El Ameed 220 KV | 791880.95 | 730158.35 | 0 | 730158.35
Marassi Inner Marina - PKG178 | 3106644 | 2266211.1 | 0 | 2731675.66
El Sewedy University | 2436188.36 | 121809.42 | 0 | 2149382.1333
EGYTEC A1,A3 ( LP-05-21) | 4983890 | 1662137.6 | 1363545 | 5314982.6
October Dry Port Railway | 67799746.72 | 44952841.1145 | 11340435.75 | 70480832.2395
French District | 118269 | 110271 | 0 | 110271
Central Bus Station | 2605240 | 2605240 | 0 | 2605240
Le Galawa Hotel Resort | 510933569 | 510933569 | 0 | 510933569
Cement Factory-Beni Suef | 188320 | 177020.8 | 0 | 177020.8
Water pumping New Obour City | 135542179.77 | 104285240.95 | 14277356.47 | 118562597.42
Zafranaa - Beni Suef | 14329463.3 | 1124226.45 | 0 | 12907545.91
Mehwar elsalam Lock & Load | 21834190.48 | 5656410 | 13530390 | 19186800
EGY TECH V2 LP-12-21 | 4560 | 5198.4 | 0 | 5198.4
R05 | 157444.76 | 54150.66 | 0 | 131949.04
159E | 281422.51 | 281422.51 | 0 | 281422.51
Koning Food LP-04-20 | 126180 | 138809.374 | 5000 | 143809.374
LP-01-22 Citrix Workspace | 48245.58 | 26773.9404 | 0 | 26773.9404
LP-23-21 UMC – 5000 RFID | 27650 | 31244.5 | 0 | 31244.5
Infra Project 4428 | 663374410.48 | 282000000.009 | 0 | 397706797.005
Racecores 3092-15 132KV A | 187347.93 | 297448.128 | 0 | 157159.159
Phosfat | 9158687 | 6774656.3 | 0 | 8201541.3
2 track mach | 10526315.79 | 3000000 | 1200000 | 4200000
Benban 3/ Toshka 2 Lot 6 | 39953263.27 | 39515486.43 | 437776.84 | 39953263.27
Infra Project 2531 | 704811822.39 | 454500910 | 14357670 | 631600725.0025
GSM-02-22 IHS | 2215649.1 | 2525839.99 | 0 | 2525839.99
Marassi - Anti carbonation | 311878.8 | 225664.66 | 0 | 225664.66
Playa Epoxy | 768594.2 | 603427.7689 | 0 | 603427.7689
SODIC Allegria Villa f100 | 5146090.48 | 1600000 | 3776500 | 5376500
PVD - El Hammam | 760862.6 | 650000 | 0 | 650000
Al-Ula Towers - ( 2 ) | 3385443.4 | 2800000 | 0 | 2800000
Mohamed Nader Villa's | 4289255.33 | 2070213.9265 | 2165425.71 | 4235639.6365
HST El Mahager Bridge | 152168942.62 | 88363916.1538 | 0 | 127934291.1538
Quarry Bridge | 4658000 | 1216207 | 0 | 1216207
EL Sewedy University Tec. | 762715.2 | 517646 | 0 | 658324.4
ORA ZED TOWER #2 | 33000 | 29221.5 | 0 | 29221.5
El-Warraq | 5397294 | 3219520.92 | 0 | 3219520.92
El Zomor Axis (2) - Leaaba | 401500 | 317661 | 0 | 317661
Kattmeya Creeks Urban | 1862808.84 | 1649517.22 | 0 | 1649517.22
Roof-Playa Cluster A,B,C | 8477238.85 | 6742957.53 | 0 | 6742957.53
3A-L2M Building | 22281960.78 | 18337374.889 | 1000000 | 19337374.889
Hosh Eisa Hospital | 587000.25 | 503704.92 | 0 | 503704.92
Qani bay Al rammah Mosque | 8571603.81 | 6624100 | 0 | 6624100
Rabigh PP - Piling Works | 9677157.65 | 32955685.24 | 0 | 11128721.8
Damietta Container Termin | 3210071.37 | 3017467.0861 | 0 | 3017467.0861
Hosh Eisa | 61151.5 | 52474.09 | 0 | 52474.09
South Dabaa Axis | 3593633.5 | 2456281.01 | 0 | 2456281.01
Aswan axis - Daraw | 1948171.43 | 0 | 0 | 0
Aljazi Project | 722114 | 440767.07 | 0 | 470608.07
Solar ITS | 14124547.5 | 11039280 | 0 | 11039280
LP-03-22 IIoT - UIC | 6750 | 0 | 0 | 0
HST Bridge - Arab Contractors | 1937612.5 | 0 | 0 | 0
Zayed Monorail 66/22 KV GIS | 7128937.84 | 0 | 0 | 0
Closed | 9257009.95 | 6971999.75 | 0 | 7915509.35
TOSHKA MADKOUR | 2853296.64 | 1515632.349 | 0 | 2643393.549
IRAQ - Al-Diwaniya Power Plant | 587270361.0563 | 1113368.92 | 0 | 586151103.7815
Elniger | 33393415.326 | 0 | 0 | 33393415.326
Ethiopia S/S | 103540391.93 | 0 | 0 | 103540391.93
Suez PP (CP-106) | 10419150.52 | 928251.58 | 0 | 10400206.6
Ain-Sokhna PP(CP-102) | 17272493.9634 | 0 | 0 | 17272493.9634
Beni-Suef PP Site Preparation | 463664313.658 | 0 | 0 | 463664313.658
Wall - New Giza | 612721 | 664733.66 | 0 | 664733.66
Shubra-Banha lock&load | 2839375.76 | 1590000 | 0 | 1590000
GPC-Gupco (Automation) | 2031182.96 | 74362.96 | 0 | 2031182.96
Ain-Sokhna PP (CP-111) | 18214562.2262 | 2881923.58 | 0 | 18282908.56
Middle Tunnel Lock Load | 1024820 | 677590 | 225865.1 | 903455.1
Metro 2L Rehabitation Cable | 24236907.24 | 1591777.48 | 0 | 24229669.74
Hyper El-Temsah | 156262515.12 | 32665911.0505 | 81376020.75 | 130688641.8005
Kayan Landscape | 99199992.95 | 38339195 | 47870959.65 | 86210154.65
Al-Kayan | 61723.04 | 26053.04 | 0 | 56914.56
Samaya Electronics factory | 880000 | 880000 | 0 | 880000
Bahr El Baqar Treatment Plant | 2560377.3 | 1149670 | 0 | 2362480.3
El Banna project | 4210719.9943 | 2825393.32 | 1385326.6743 | 4210719.9943
Abas El Akkad Bridge | 2786850 | 109010 | 0 | 2515625.75
El Mostaqbal lock & load | 4100076 | 1713657 | 1621424.45 | 3335081.45
Huawei Technologies LP-11-20 | 220000 | 248600 | 0 | 248600
Koning Food V4 LP-01-21 | 62280.7 | 71000 | 0 | 71000
Borg El Arab Bridge - Km 21 | 2453372 | 1654885.16 | 0 | 1654885.16
Cables Egypt (LP-03-21) | 579060 | 355594.4 | 304530 | 660124.4
LP-24-21 Autostrada | 1742695.64 | 1990457.1666 | 0 | 1990457.1666
Ring Road -General Nile Co | 656138 | 649576.62 | 0 | 649576.62
Alfa New Central Labs | 1403211.67 | 1459340 | 0 | 1459340
LP-26-21 Koning Food V5 | 25264 | 28764.48 | 0 | 28764.48
LP-13-21 -UIC | 44500 | 50285 | 0 | 50285
Monorail | 1816490 | 2052633.7 | 0 | 2052633.7
El Sadat City | 94558050.17 | 52376438.56 | 0 | 52376438.56
Expansion of Ring Road | 355200 | 350000 | 0 | 350000
Marassi - Water proofing | 224375.87 | 193684.85 | 0 | 193684.85
PO3092200025 | 123220.12 | 123095.12 | 0 | 123095.12
The American School ASE | 509326 | 504232.73 | 0 | 504232.73
Jawhar El-Lala Mosque | 16500 | 14008.5 | 0 | 14008.5
El- Hussein Mosque | 5007440 | 3865320 | 0 | 3865320
Residence 8 ( S07 ) | 1134750 | 1025814 | 0 | 1025814
Jawhar Al-Lala Mosque | 8815759 | 1979890 | 4951647 | 6931537
UGC Factory | 2989546 | 2810173.24 | 0 | 2810173.24
EDNC Retail - SEOUDI MODI | 3317744.06 | 1574320.56 | 1592217.31 | 3166537.87
Qasr Rashwan Lot A | 32298855.95 | 50401968.48 | 5979189.16 | 56381157.64
Sohag HSR Station | 14703480.67 | 7843918.88 | 0 | 13008126.88
Benban 4 As El-Nakra 220 K.V | 13910905.32 | 6456442.88 | 0 | 13410070.04
Mozambique TL | 4823630 | 0 | 0 | 4823630
Residence 8 ( S09 ) | 1443296.63 | 0 | 0 | 1443296.63
Mahmoudia Power Plant | 2268360021 | 0 | 0 | 2268360021
KSA - PP-12 | 31773079.5235 | 0 | 0 | 31773079.5235
Algeria S/Ss | 8205579.67 | 2541738.82 | 0 | 7923164.25
Shanghai CO. | 14140 | 14140 | 0 | 14140
ASEC-El Menya | 825530.61 | 532467.24 | 247659.18 | 780126.42
EMAAR-PKG#85-UPTOWN | 2668533.04 | 1107056.632 | 1121091.53 | 2228148.162
El Amal Bridge | 12935441.7 | 7963694.65 | 1178000 | 11895796.65
Kuraiamte Lot1&2 | 278157.89 | 257528.11 | 0 | 257528.11
Port Said | 30871817.21 | 4722185.55 | 0 | 30642803.1
VM Horizon Cloud LP-07-20 | 109647.83 | 124998.53 | 0 | 124998.53
Mid Town - Condo | 40000 | 40000 | 0 | 40000
MIDELEC 66 KV OHTL | 1787986.2 | 1501908.41 | 268197.93 | 1770106.34
BRSH-JHRC | 506746.2476 | 50674.62 | 0 | 50674.62
LP-15-21 UIC | 30000 | 33900 | 0 | 33900
LP-20-21 ACUD Fiber optics | 1166400 | 1318032 | 0 | 1318032
Dwelling Villas Seashell Playa | 75551.56 | 65246.33 | 0 | 65246.33
26th of July Corridor New | 1549500 | 1329625.95 | 0 | 1329625.95
6 Octobar Stores | 285824 | 60000 | 0 | 60000
Abo Ghaleb | 2544000 | 1150073.2 | 0 | 2422073.2
AL-JAWHARA PALACE | 70875 | 61635.67 | 0 | 61635.67
Residence 8 ( K10 ) | 1053074.22 | 725753 | 0 | 850877.61
Aswan- Belana 60K m³/day WWTP | 0 | 0 | 0 | 0
Bashteel - Tahya Masr Bridge | 1528500 | 0 | 0 | 0
Hosh Eisa Hospit. | 587000.25 | 0 | 0 | 587000.25
Street Lighting Fayoum | 32271820 | 24688585 | 0 | 26225338.33
Suez Road Tunnel RES | 6984390.19 | 4148825 | 1382947.14 | 5531772.14
Iskraemeco show room | 741585.97 | 845408 | 0 | 845408
Sherouk Bridge- LOCK&LOAD | 728000 | 550000 | 0 | 550000
Solera LP-08-21 | 723400.12 | 704264 | 0 | 704264
LP-07-21 Petrojet | 34646843.55 | 3081350.89 | 1599233 | 4680583.89
Supply E.S. Kit - MAUR. | 29938 | 29935.38 | 0 | 29935.38
TNYA-WSHP | 666297.528 | 1799417.5332 | 0 | 547787.4444
New Giza Hospital | 611073.57 | 502966.67 | 0 | 502966.67
Abou Matamer & Samanoud | 4561945.18 | 4561945.18 | 0 | 4561945.18
HST Culverts | 40303792.95 | 22689004.0376 | 0 | 36689004.0376
Expansion of Ring Road-CFA | 2345220 | 260000 | 0 | 260000
Villa Clustera Playa | 874855 | 653224.78 | 0 | 653224.78
Wadi El Natroun Bridge | 14299770 | 296232.18 | 0 | 296232.18
WPS Substation 3 | 5000 | 0 | 0 | 0
LP-17-21 ODP-Computing | 211225.15 | 0 | 0 | 0
JICA lot 02 | 37271883.06 | 0 | 0 | 0
LP-19-21 N2 Extension | 3282236 | 0 | 0 | 0
Ring Road El Monib | 1781000 | 0 | 0 | 0
FX-03-22 Urban Communities-WD | 928819.52 | 0 | 0 | 0
184E Substation | 155857.75 | 0 | 0 | 160157.75
Zambia | 146431587 | 0 | 0 | 146431587
PIP West 2 | 21544102.56 | 0 | 0 | 21544102.56
Tebbin PP Rehabitation (CP106) | 125133.41 | 0 | 0 | 125133.41
Borolos Over Head | 2100000 | 1870602.15 | 0 | 1970602.15
Gesr El suez | 75000 | 75000 | 0 | 75000
Sodic Wesset | 134479.24 | 122779.5558 | 0 | 122779.5558
South Mohamed Ben Zayed S.L | 21877894.1 | 17754986.46 | 0 | 17754986.46
LP-25-21 UIC4 Printers | 12719.25 | 14372.75 | 0 | 14372.75
DEWA 36 (OPGW) | 50442 | 50442 | 0 | 50442
LP-27-21-Elsewedy1000RFID | 5530 | 6304.2 | 0 | 6304.2
LP-16-21 VC Elsewedy P. | 1635028.68 | 931966.35 | 0 | 931966.35
Asmarat Roads L&L | 2917810 | 2256420 | 0 | 2256420
Ora Zed -Landscape | 86683.32 | 69560.8 | 0 | 69560.8
Samaya Factory - 2 | 386925 | 360000 | 0 | 360000
FX-01-22 Decent Life-WD | 4435320.46 | 0 | 0 | 0
LP-08-22 CFC Digital-Signage | 377358.8 | 0 | 0 | 0
Abu Ghazala Lock & Load | 2200000 | 1459070 | 454462 | 1913532
Katamia Dunes Villa | 47667.26 | 2000 | 30000 | 32000
Selwa 220 KV - 27 KM OHTL | 3353492.41 | 3423925.56 | 0 | 3423925.56
Marazik Railway Bridge | 208500 | 184558.32 | 0 | 184558.32
DRCC | 5000 | 0 | -113.49 | -113.49
Selwa / New Isna 220KV OHTL | 2177093.48 | 2015950.57 | 0 | 2015950.57
Marassi Epoxy | 83820 | 71925.94 | 0 | 71925.94
Olympic City Lock&Load | 3638578 | 3022610 | 0 | 3022610
LP-18-21 ODP Passive & DC | 2790163.2473 | 0 | 0 | 0
East Owainat | -11517.22 | 0 | 0 | 0
LP-22-21 ECMEI–6000–RFID | 33180 | 0 | 0 | 0
KSA - Rabegh PMS | 1485271.0503 | 22502.2 | 0 | 1485271.0503
Abu Quir Timmay Alamdid 500KV | 2740005.3 | 2110682.6 | 0 | 2110682.6
MRINACMN KSWG & FRDH Circuit | 19207.5 | 19207.5 | 0 | 19207.5
TEst | 44143.76 | 149647.3392 | 0 | 49882.4464
EDNC Mobilization Works | 609204.24 | 633572.41 | 0 | 633572.41
Sodic East Town(EDNC) | 328820.4 | 0 | 0 | 0
WPS Substations 1&2 | 5000 | 0 | 0 | 0

## per.project
project eslam | project erp | gross eslam | gross erp | var | collection eslam | collection applied erp | var
6TH October tunnel | October Under-Railway Tunnel | 17396267 | 50346091.04 | -32949824.04 | 14377439.501 | 40122061.9 | -25744622.399
Abo Ghaleb Bridge | Abo Ghaleb | 26708197.2 | 2544000 | 24164197.2 | 19072529.3001 | 1150073.2 | 17922456.1001
AEON | 0 | 3737551.6717 | 0 | 3737551.6717 | 4042720.14 | 0 | 4042720.14
Al Jazi | Aljazi Project | 210649381.49 | 722114 | 209927267.49 | 115504490.2401 | 440767.07 | 115063723.1701
Al Jazi - Center Zone | Aljazi Project | 39621391.5949 | 722114 | 38899277.5949 | 18183801.98 | 440767.07 | 17743034.91
Alfa Lab | Alfa New Central Labs | 0 | 1403211.67 | -1403211.67 | 1459340 | 1459340 | 0
Allegria-New Modifications | 0 | 0 | 0 | 0 | 659568.2 | 0 | 659568.2
Astoria - Sharm | Astoria Sharm elSheikh | 5455402.14 | 6619935.92 | -1164533.78 | 5518080.8 | 5518079.8735 | 0.9265
Astoria Hotel | Waldorf Astoria Cairo | 219912624 | 248450534.47 | -28537910.47 | 137591009.8602 | 130550580.4505 | 7040429.4097
Baraka Land Fence | 0 | 46556214 | 0 | 46556214 | 32455285.85 | 0 | 32455285.85
Benban - Aswan | 0 | 223546645.0145 | 0 | 223546645.0145 | 227493021.4292 | 0 | 227493021.4292
Cement Plant | Cement Factory-Beni Suef | 50948609.6551 | 188320 | 50760289.6551 | 58290731.3871 | 177020.8 | 58113710.5871
CFC | CFC Podium 2 | 637419839.06 | 637419839.06 | 0 | 550014659.8648 | 562651733.4145 | -12637073.5497
Comoros - Off Shore | Le Galawa Hotel Resort | 1137692.89 | 510933569 | -509795876.11 | 3465542 | 510933569 | -507468027
Comoros - On Shore | Le Galawa Hotel Resort | 1545364.67 | 510933569 | -509388204.33 | 1500000 | 510933569 | -509433569
Creeks - URBN K | Creeks URBN-K | 339995246.28 | 335774638.69 | 4220607.59 | 232191136.19 | 210382164.7719 | 21808971.4181
Damietta Port - Civil | Damietta Container Termin | 0 | 3210071.37 | -3210071.37 | 7076157.99 | 3017467.0861 | 4058690.9039
Damietta Port - Infra | #N/A | 0 | 0 | 0 | 6541975.22 | 0 | 6541975.22
DP World Sokhna | DPW Onshore Port & Terminal | 1611128362.46 | 1677911074.56 | -66782712.1 | 1515088223.55 | 1272524392.42 | 242563831.13
DPW - Ph.02 | DP World Basin 2 Ph2 | 466005047.8999 | 503944643.92 | -37939596.0201 | 446884519.7379 | 390826588.3987 | 56057931.3392
EGAT Pelletizing Plant | EGAT Pelletizing Plant | 469996440.45 | 798933395.04 | -328936954.59 | 1415634547.37 | 686543794.1165 | 729090753.2535
EGAT Pelletizing Plant - Admin Building | EGAT Pelletizing Plant | 115239950.18 | 798933395.04 | -683693444.86 | 0 | 686543794.1165 | -686543794.1165
EGAT Pelletizing Plant - Supply | EGAT Pelletizing Plant | 1390180.36 | 798933395.04 | -797543214.68 | 1570903.44 | 686543794.1165 | -684972890.6765
EGAT Pelletizing Plant-Concrete Infra | EGAT Pelletizing Plant | 0 | 798933395.04 | -798933395.04 | 1e-05 | 686543794.1165 | -686543794.1165
EGAT Pelletizing Plant-Mechanical Installation | EGAT Pelletizing Plant | 0 | 798933395.04 | -798933395.04 | 1e-05 | 686543794.1165 | -686543794.1165
EGAT Pelletizing Plant-MEP | EGAT Pelletizing Plant | 3847983.19 | 798933395.04 | -795085411.85 | 3e-05 | 686543794.1165 | -686543794.1165
EGAT Pelletizing Plant-MEP Coordination | EGAT Pelletizing Plant | 0 | 798933395.04 | -798933395.04 | 1e-05 | 686543794.1165 | -686543794.1165
EGAT Pelletizing Plant-Water Tank | EGAT Pelletizing Plant | 18248170.91 | 798933395.04 | -780685224.13 | 18558268.73 | 686543794.1165 | -667985525.3865
EGAT-Asphalt | 0 | 0 | 0 | 0 | 598688 | 0 | 598688
EGAT-Fence | 0 | -616810.92 | 0 | -616810.92 | 3781834.346 | 0 | 3781834.346
EGAT-HeliPad | 0 | 0 | 0 | 0 | 1255798.13 | 0 | 1255798.13
EGAT-Lock & Load | EGAT Lock & Load | 34708617.75 | 55000000 | -20291382.25 | 33241080.59 | 51799999.9913 | -18558919.4013
EGAT-SZ | 0 | 6085108 | 0 | 6085108 | 20694859.36 | 0 | 20694859.36
EGAT-Warehouse | 0 | 0 | 0 | 0 | 923651.335 | 0 | 923651.335
EIPICO | EPICO 3 Facility | 517317277 | 655977489.41 | -138660212.41 | 526013000.52 | 399756244.2355 | 126256756.2845
El Sewedy Uni.-PKG.1 | Elsewedy Univ - Enabling Works | 8945871.5 | 267595441.71 | -258649570.21 | 6131821.2653 | 299348859.386 | -293217038.1207
El Sewedy Uni.-PKG.2 | Elsewedy Univ - Enabling Works | 42530405.3 | 267595441.71 | -225065036.41 | 34291191.53 | 299348859.386 | -265057667.856
El Sewedy Uni.-PKG.3 | Elsewedy Univ - Enabling Works | 211191712.9 | 267595441.71 | -56403728.81 | 213911305.17 | 299348859.386 | -85437554.216
Elco Steel | Substation Elco Steel | 256512475.28 | 32341773.85 | 224170701.43 | 216244876.98 | 25359653.55 | 190885223.43
Elco Steel - ADMIN. | Substation Elco Steel | 29666524.51 | 32341773.85 | -2675249.34 | 35208233.9323 | 25359653.55 | 9848580.3823
Elco Steel - MEP | Substation Elco Steel | 18876028.8389 | 32341773.85 | -13465745.0111 | 24314580.2491 | 25359653.55 | -1045073.3009
Elco Steel V.O-Infra. Network | Substation Elco Steel | 0 | 32341773.85 | -32341773.85 | 1060000 | 25359653.55 | -24299653.55
El-Gouna | DoubleTree Mangroovy ElGouna | 56611222.83 | 61162018.58 | -4550795.75 | 46416955.52 | 53680877.982 | -7263922.462
El-Gouna - Equip. Rental | DoubleTree Mangroovy ElGouna | 95875 | 61162018.58 | -61066143.58 | 183701.37 | 53680877.982 | -53497176.612
El-Gouna - Temp. Fence | DoubleTree Mangroovy ElGouna | 409200 | 61162018.58 | -60752818.58 | 1040844 | 53680877.982 | -52640033.982
Existing Intake Apply -SSC-Mech | 0 | 573500 | 0 | 573500 | 1e-05 | 0 | 1e-05
Existing Intake Supply -SSC-Mech | 0 | 2140488 | 0 | 2140488 | 2311727.07 | 0 | 2311727.07
FIEM | 0 | 4870155.99 | 0 | 4870155.99 | 3282949.756 | 0 | 3282949.756
HQ - CFC | ElSewedy HQ Internal Finishing | 339256604.7048 | 379959726.32 | -40703121.6152 | 235094683.46 | 164055422.0915 | 71039261.3685
HyperOne | HyperOne Zayed Extension | 125813738 | 131528902.2 | -5715164.2 | 109988127 | 90790688.775 | 19197438.225
IKEA | IKEA Extension MoA | 196469398.74 | 200594718.8 | -4125320.06 | 187283627.918 | 156723470.129 | 30560157.789
JICA | 0 | 1493988.77 | 0 | 1493988.77 | 1554690.71 | 0 | 1554690.71
Kafr Shokr | Kafr Shokr Bridge | 43013139.95 | 206789507.09 | -163776367.14 | 93351030.25 | 103747101.77 | -10396071.52
Katameya - Creeks | Kattameya Creeks | 1969330870.97 | 2027599304.12 | -58268433.15 | 1940540543.3709 | 1821158928.6402 | 119381614.7307
KFW | 0 | 513498.85 | 0 | 513498.85 | 505795.52 | 0 | 505795.52
Khatatba Bridge | El Khatatba Bridge | 103541825 | 171300222.12 | -67758397.12 | 44616552.35 | 113981141.2446 | -69364588.8946
KSA-Tarek AbdelHakim Center | 0 | 12373409.49 | 0 | 12373409.49 | 6760079.54 | 0 | 6760079.54
LEKELA | Lekela 250MW Wind Farm | 197715926.3399 | 233203769 | -35487842.6601 | 215826961.0619 | 186351528.7395 | 29475432.3224
LEKELA Remedial | Lekela 250MW Wind Farm | 9038826.59 | 233203769 | -224164942.41 | 16400380.18 | 186351528.7395 | -169951148.5595
MDF Factory | MDF Factory | 646587687.4 | 728463652.27 | -81875964.87 | 652429505.73 | 484849824.3287 | 167579681.4013
MDF Factory - Equip. | MDF Factory | 9909890.82 | 728463652.27 | -718553761.45 | 24295511.57 | 484849824.3287 | -460554312.7587
MDF Factory - Local Fabrication | MDF Factory | 37198576.6334 | 728463652.27 | -691265075.6366 | 36836586.38 | 484849824.3287 | -448013237.9487
Mechanical Installation | EGAT Mechanical Installations | 96641266.36 | 97797506.35 | -1156239.99 | 15000000 | 74374136.8627 | -59374136.8627
Mintra | 0 | 71975982.5504 | 0 | 71975982.5504 | 40226731.05 | 0 | 40226731.05
Mintra-Hanger 1200m2 | 0 | 1411985.3421 | 0 | 1411985.3421 | 525781.49 | 0 | 525781.49
Mivida-PK#140 | EMAAR- Pkg 140-ITP-Mivida | 174986240.77 | 174061648.74 | 924592.03 | 170629197.1757 | 156885863.687 | 13743333.4887
Mivida-PK#189 | Mivida BP#189 | 722063050.6096 | 764903424.19 | -42840373.5804 | 967154954.8563 | 688857877.1595 | 278297077.6968
Mobilization | 0 | 3847983.19 | 0 | 3847983.19 | 0 | 0 | 0
MOC | MOC HQ at Diriyah | 0 | 72346246.462 | -72346246.462 | 33350000 | 0 | 33350000
MOC - DP | MOC HQ at Diriyah | 0 | 72346246.462 | -72346246.462 | 0 | 0 | 0
New Gas Station | New Giza Teaching Hospital | 12691483.19 | 598028482.65 | -585336999.46 | 3620565.65 | 331478318.6905 | -327857753.0405
New Giza Hospital | New Giza Teaching Hospital | 601647088.7799 | 598028482.65 | 3618606.1299 | 419361224.2248 | 331478318.6905 | 87882905.5343
NGU 2 | New Giza 2 | 16857005.6181 | 56956316.78 | -40099311.1619 | 9562840.7 | 49196980.979 | -39634140.279
ORA - ZED | ORA ZED - Ph 01B - Pkgs A&D | 937969554.6476 | 956060987.36 | -18091432.7124 | 930474767.37 | 701913808.7171 | 228560958.6529
ORA - ZED - Landscape | Ora Zed Landscape Ph1 | 73384959.6762 | 62492502.6725 | 10892457.0037 | 62860365.69 | 50281542.3847 | 12578823.3053
ORA - ZED - ph.02 | ORA ZED-Ph 2-Pkgs A&D | 422723572.7017 | 452012507.88 | -29288935.1783 | 362749602.28 | 350432311.4306 | 12317290.8494
PH.2-El Sewedy Uni. - Enabling | ESU Ph2-Enabling & Struc | 113226141.7 | 608748208.71 | -495522067.01 | 79793038.32 | 372525071.886 | -292732033.566
PH.2-El Sewedy Uni. - Finishes | ESU Ph2-Enabling & Struc | 494664244.29 | 608748208.71 | -114083964.42 | 325272803.2 | 372525071.886 | -47252268.686
PI Parks - ELSEWEDY | 0 | 48749863.7034 | 0 | 48749863.7034 | 45635248.43 | 0 | 45635248.43
PI Parks - MEP | 0 | 46221454.64 | 0 | 46221454.64 | 35236361.52 | 0 | 35236361.52
PK #107 | EMAAR-PKG#107-MARASSI | 18514020.23 | 54747174.24 | -36233154.01 | 19516387.07 | 53560171.427 | -34043784.357
PK #117 | EMAAR-PKG117- MARASSI | 51045129.21 | 46843952.64 | 4201176.57 | 46229297.51 | 44469964.9617 | 1759332.5483
PK#22 | EMAAR-PKG#22-MARASSI | 0 | 1232045.42 | -1232045.42 | 780036 | 1228735.201 | -448699.201
PK#32 | 0 | 0 | 0 | 0 | 900093.35 | 0 | 900093.35
PKG#101 | EMAAR-PKG# 101-UPTOWN | 50455724.1353 | 50727362.381 | -271638.2457 | 42449902.61 | 32861329.1491 | 9588573.4609
PKG#144 | EMAAR-PKG# 144, Marassi | 176412609.32 | 176420375.18 | -7765.86 | 143694275.79 | 147279720.6915 | -3585444.9015
PKG#162 | EMAAR-Pkg#162/163- Marassi | 100261401 | 860066867.1254 | -759805466.1254 | 90399845.0589 | 628554886.1548 | -538155041.0959
PKG#163 | EMAAR-Pkg#162/163- Marassi | 198641259.21 | 860066867.1254 | -661425607.9154 | 166205264.9103 | 628554886.1548 | -462349621.2445
PKG#177 | EMAAR-Pkg#162/163- Marassi | 609745628.719 | 860066867.1254 | -250321238.4064 | 546376728.6001 | 628554886.1548 | -82178157.5547
PKG#177 - DP | EMAAR-Pkg#162/163- Marassi | 0 | 860066867.1254 | -860066867.1254 | 0 | 628554886.1548 | -628554886.1548
PKG#177 - SWI 07 | EMAAR-Pkg#162/163- Marassi | 13989412.2626 | 860066867.1254 | -846077454.8628 | 1e-05 | 628554886.1548 | -628554886.1548
PKG#178 | BKG#178-Lagoon Discharge | 48731447.3599 | 48731447.35 | 0.0099 | 46354505.36 | 45164066.1075 | 1190439.2525
PKG#205 | 0 | 3983412 | 0 | 3983412 | 2432072.07 | 0 | 2432072.07
PKG#220B | SOL Town PKG.220 | 23621739.09 | 50481629.15 | -26859890.06 | 16542097.8 | 17460291.28 | -918193.48
PKG#220B - DP | SOL Town PKG.220 | 0 | 50481629.15 | -50481629.15 | 0 | 17460291.28 | -17460291.28
PKG#45 | 0 | 0 | 0 | 0 | 1844931.02 | 0 | 1844931.02
PKG#58 | 0 | 0 | 0 | 0 | 327696.29 | 0 | 327696.29
PKG#85 | EMAAR-PKG#85-UPTOWN | 2033193.5852 | 2668533.04 | -635339.4548 | 3919781 | 1107056.632 | 2812724.368
PO#11687 | 0 | 0 | 0 | 0 | 2179100 | 0 | 2179100
Port Said Silos | Port Said Port Silos | 194694011.2613 | 253501552.4501 | -58807541.1888 | 248477311.94 | 302243665.0889 | -53766353.1489
Port Said Silos - Foreigner Supply | Port Said Port Silos | 5539353.23 | 253501552.4501 | -247962199.2201 | 5982501.45 | 302243665.0889 | -296261163.6389
Port Said Silos - Local Supply | Port Said Port Silos | 25664811.6942 | 253501552.4501 | -227836740.7559 | 20939480.09 | 302243665.0889 | -281304184.9989
PSP Substation | 0 | 28049799.0115 | 0 | 28049799.0115 | 22125476.64 | 0 | 22125476.64
Rabigh Ext. - Piles | Rabigh PP - Piling Works | 4532144.9 | 9677157.65 | -5145012.75 | 8019672.14 | 32955685.24 | -24936013.1
Rabigh Ext. -Building | Rabigh CCPP-Civil | 19657624.24 | 10359504.61 | 9298119.63 | 7368302.61 | 40265868.86 | -32897566.25
Radamis-Concrete | 0 | 0 | 0 | 0 | 20000000 | 0 | 20000000
Radamis-H1 Main Builidng | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radamis-Rooms Fitout | 0 | 0 | 0 | 0 | 19750000 | 0 | 19750000
Radamis-Villas Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0
Red Sea Museum | Red Sea Museum-Bab El-Bunt | 6802729 | 5442183.62 | 1360545.38 | 14076875.93 | 18775533.51 | -4698657.58
Ring Road - El Marg | RING ROAD MARYOTIA EXPANSION | 12521916.095 | 704980256.49 | -692458340.395 | 89560604.8003 | 497936633.536 | -408376028.7357
Ring Road - Mounib | RING ROAD MARYOTIA EXPANSION | 380682347.7902 | 704980256.49 | -324297908.6998 | 295101657.0891 | 497936633.536 | -202834976.4469
RO Apply -Mech- SSC | 0 | 6699867.78 | 0 | 6699867.78 | 1730229.071 | 0 | 1730229.071
RO Eriction | 0 | 6000000 | 0 | 6000000 | 0 | 0 | 0
RO Pump Room | 0 | 22392582.54 | 0 | 22392582.54 | 0 | 0 | 0
RO - Supply - Electric | 0 | 20142134.74 | 0 | 20142134.74 | 2225665.9095 | 0 | 2225665.9095
RO Supply -Mech- SSC | 0 | 72918679.38 | 0 | 72918679.38 | 31850492.4035 | 0 | 31850492.4035
RO 2 | 0 | 37356959.8 | 0 | 37356959.8 | 0 | 0 | 0
RO Pump room - SSC - price diff. | 0 | 31828983.21 | 0 | 31828983.21 | 33463444.62 | 0 | 33463444.62
RO.2 | 0 | 0 | 0 | 0 | 1e-05 | 0 | 1e-05
Rolling Mill #4-TRAESUEZ | EGAT New Rolling Mill 4 | 823298504.69 | 1143460 | 822155044.69 | 247223556.35 | 823066.73 | 246400489.62
Royal City | Royal City | 432695392.6 | 567527944.71 | -134832552.11 | 397670173.0109 | 425704643.6985 | -28034470.6876
Royal City - Landscape | Royal City | 110218542.31 | 567527944.71 | -457309402.4 | 97543968.2041 | 425704643.6985 | -328160675.4944
Saint Gobain Factory - DP | 0 | 0 | 0 | 0 | 0 | 0 | 0
SIEMENS - Sokhna | 0 | 323400070.32 | 0 | 323400070.32 | 341815198.568 | 0 | 341815198.568
SMP1 - Revamp | 0 | 38750521.78 | 0 | 38750521.78 | 73165890.8292 | 0 | 73165890.8292
SMP1 - Shut Down | 0 | 32843145.26 | 0 | 32843145.26 | 29178174.7798 | 0 | 29178174.7798
SMP2 - Shut Down | 0 | 18543709.74 | 0 | 18543709.74 | 6007380.2913 | 0 | 6007380.2913
Sodic Club House | Sodic Club House | 107614518.3 | 117882779.21 | -10268260.91 | 53591447.14 | 79939871.3505 | -26348424.2105
Sodic Eastown | EDNC Retail & Offices Civil | 1145187121.1617 | 1145187121.17 | -0.0083148 | 991816334.7529 | 867196309.172 | 124620025.5809
Sodic Eastown - Landscape | EDNC Hardscape Package | 51825860.8952 | 70642868.33 | -18817007.4348 | 40777673.38 | 42631677.4485 | -1854004.0685
Sokhna Port Expansion | Sokhna Port Expansion | 722376298.67 | 1235871108.69 | -513494810.02 | 760346305.5055 | 821763237.5403 | -61416932.0348
Sokhna Port Expansion- 100m | Sokhna Port Expansion | 103062673.94 | 1235871108.69 | -1132808434.75 | 96746521.75 | 821763237.5403 | -725016715.7903
Sokhna Port Expansion-internal roads | Sokhna Port Expansion | 0 | 1235871108.69 | -1235871108.69 | 1803690.2 | 821763237.5403 | -819959547.3403
Sports Hall - Civil Works | Olympic Multi – Sports Hall | 98877565 | 1041770776.43 | -942893211.43 | 30592330 | 213689000.03 | -183096670.03
Sports Hall - Finishes | Olympic Multi – Sports Hall | 91998353.75 | 1041770776.43 | -949772422.68 | 25289285 | 213689000.03 | -188399715.03
Sports Hall - Finishes - ADD.01 | Olympic Multi – Sports Hall | 9145259 | 1041770776.43 | -1032625517.43 | 8573040 | 213689000.03 | -205115960.03
Sports Hall - Finishes - Landscape | Olympic Multi – Sports Hall | 0 | 1041770776.43 | -1041770776.43 | 0.0003 | 213689000.03 | -213689000.0297
Sports Hall - MEP | Olympic Multi – Sports Hall | 0 | 1041770776.43 | -1041770776.43 | 68520890 | 213689000.03 | -145168110.03
Suez Intake & P Stations-ABB apply | 0 | 9998619 | 0 | 9998619 | 2545932.1364 | 0 | 2545932.1364
Suez Intake & P Stations-ABB supply | 0 | 39796178.06 | 0 | 39796178.06 | 17055077.32 | 0 | 17055077.32
Suez Intake & P Stations-SSC apply | 0 | 19268018.4 | 0 | 19268018.4 | 6782714.6624 | 0 | 6782714.6624
Suez Intake & P Stations-SSC supply | 0 | 23684958.55 | 0 | 23684958.55 | 12200771.57 | 0 | 12200771.57
SVC | 0 | 3212437.04 | 0 | 3212437.04 | 3375312.6616 | 0 | 3375312.6616
Uptown PK #53 | EMAAR-PKG#53-UPTOWN | 110923486.8564 | 208921390.67 | -97997903.8136 | 105256075.6652 | 161563851.3545 | -56307775.6893
Uptown PK #62 | EMAAR-PKG#62-UPTOWN | 28675727.83 | 45491143.52 | -16815415.69 | 21083386.4 | 31149418.2925 | -10066031.8925
Wady Halfa | Wadi Halfa Port | 53392295.4 | 129542558.46 | -76150263.06 | 39736481.05 | 72591764.2764 | -32855283.2264
Western Fence | 0 | 762742.21 | 0 | 762742.21 | 418218.39 | 0 | 418218.39
Zayed Park | 0 | 1033297.776 | 0 | 1033297.776 | 770220.21 | 0 | 770220.21