## Cash In-Month (3) (hidden)
Project Name | Month/Year | Cash In | Cash Out | Cum IN | Cum Out | Net Cash flow | Revised Contract Amount | % From Contract | Min Percent | Value of Work | Date | Source |  |  | Year
Marassi Civic Center Pkg 45 | 2013-12-31 | 19559799 | 0 | 19559799 | 0 | 19559799 | 56931016 | 34.36% | 18.9% | 1275096 | 2013-12-31 | original |  |  | 2013
Marassi Civic Center Pkg 45 | 2014-01-31 | 1419824.74 | 1540259.6 | 20979623.74 | 1540259.6 | 19439364.14 | 56931016 | 34.15% |  | 3927841 | 2014-01-31 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-02-28 | 4012695.33 | 3090424.21 | 24992319.07 | 4630683.81 | 20361635.26 | 56931016 | 35.77% |  | 2146092 | 2014-02-28 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-03-31 | 2489526.62 | 3032287.47 | 27481845.69 | 7662971.28 | 19818874.41 | 56931016 | 34.81% |  | 4028277 | 2014-03-31 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-04-30 | 3000000 | 3378653.79 | 30481845.69 | 11041625.07 | 19440220.62 | 56931016 | 34.15% |  | 3352119 | 2014-04-30 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-05-31 | 2473267.87 | 3909050 | 32955113.56 | 14950675.07 | 18004438.49 | 56931016 | 31.63% |  | 4213793 | 2014-05-31 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-06-30 | 1746555.29 | 4994649.24 | 34701668.85 | 19945324.31 | 14756344.54 | 56931016 | 25.92% |  | 2407980 | 2014-06-30 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-07-31 | 2743644.04 | 2030895.4 | 37445312.89 | 21976219.71 | 15469093.18 | 56931016 | 27.17% |  | 484963 | 2014-07-31 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-08-31 | 945541.57 | 1820193.93 | 38390854.46 | 23796413.64 | 14594440.82 | 56931016 | 25.64% |  | 806066 | 2014-08-31 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-09-30 | 688683.32 | 1059803.11 | 39079537.78 | 24856216.75 | 14223321.03 | 56931016 | 24.98% |  | 320413 | 2014-09-30 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-10-31 | 0 | 958518.9284 | 39079537.78 | 25814735.6784 | 13264802.1016 | 56931016 | 23.3% |  | 811736 | 2014-10-31 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-11-30 | 795805.82 | 784665.56 | 39875343.6 | 26599401.2384 | 13275942.3616 | 56931016 | 23.32% |  | 1003619 | 2014-11-30 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2014-12-31 | 0 | 959821.19 | 39875343.6 | 27559222.4284 | 12316121.1716 | 56931016 | 21.63% |  | 702424 | 2014-12-31 | original |  |  | 2014
Marassi Civic Center Pkg 45 | 2015-01-31 | 0 | 739606 | 39875343.6 | 28298828.4284 | 11576515.1716 | 56931016 | 20.33% |  | 818192 | 2015-01-31 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-02-28 | 798019 | 731493 | 40673362.6 | 29030321.4284 | 11643041.1716 | 56931016 | 20.45% |  | 1627690 | 2015-02-28 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-03-31 | 157942 | 1040284 | 40831304.6 | 30070605.4284 | 10760699.1716 | 56931016 | 18.9% |  | 751751 | 2015-03-31 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-04-30 | 1156272 | 803490 | 41987576.6 | 30874095.4284 | 11113481.1716 | 56931016 | 19.52% |  | 1218297 | 2015-04-30 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-05-31 | 1963896 | 956005 | 43951472.6 | 31830100.4284 | 12121372.1716 | 56931016 | 21.29% |  | 0 | 2015-05-31 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-06-30 | 592451 | 841121 | 44543923.6 | 32671221.4284 | 11872702.1716 | 56931016 | 20.85% |  | 2032372 | 2015-06-30 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-07-31 | 946975 | 566181 | 45490898.6 | 33237402.4284 | 12253496.1716 | 56931016 | 21.52% |  | 973468 | 2015-07-31 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-08-31 | 0 | 912402 | 45490898.6 | 34149804.4284 | 11341094.1716 | 56931016 | 19.92% |  | 1088031 | 2015-08-31 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-09-30 | 1709112 | 601472 | 47200010.6 | 34751276.4284 | 12448734.1716 | 56931016 | 21.87% |  | 181597 | 2015-09-30 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-10-31 | 0 | 382349 | 47200010.6 | 35133625.4284 | 12066385.1716 | 56931016 | 21.19% |  | 790090 | 2015-10-31 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-11-30 | 1693638 | 888784 | 48893648.6 | 36022409.4284 | 12871239.1716 | 56931016 | 22.61% |  | 1294652 | 2015-11-30 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2015-12-31 | 801254 | 732208 | 49694902.6 | 36754617.4284 | 12940285.1716 | 56931016 | 22.73% |  | 0 | 2015-12-31 | original |  |  | 2015
Marassi Civic Center Pkg 45 | 2016-01-31 | 0 | 731407 | 49694902.6 | 37486024.4284 | 12208878.1716 | 56931016 | 21.45% |  | 416763 | 2016-01-31 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-02-29 | 798018.64 | 1011941 | 50492921.24 | 38497965.4284 | 11994955.8116 | 56931016 | 21.07% |  | 791891 | 2016-02-29 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-03-31 | 157942.32 | 551174 | 50650863.56 | 39049139.4284 | 11601724.1316 | 56931016 | 20.38% |  | 173722 | 2016-03-31 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-04-30 | 1156271.93 | 507787 | 51807135.49 | 39556926.4284 | 12250209.0616 | 56931016 | 21.52% |  | 2164773 | 2016-04-30 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-05-31 | 1910376.71 | 488764 | 53717512.2 | 40045690.4284 | 13671821.7716 | 56931016 | 24.01% |  | 0 | 2016-05-31 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-06-30 | 1539426.61 | 541908 | 55256938.81 | 40587598.4284 | 14669340.3816 | 56931016 | 25.77% |  | 0 | 2016-06-30 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-07-31 | 0 | 334273 | 55256938.81 | 40921871.4284 | 14335067.3816 | 56931016 | 25.18% |  | 3840878 | 2016-07-31 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-08-31 | 0 | 468748 | 55256938.81 | 41390619.4284 | 13866319.3816 | 56931016 | 24.36% |  | 0 | 2016-08-31 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-09-30 | 1709112.45 | 192197 | 56966051.26 | 41582816.4284 | 15383234.8316 | 56931016 | 27.02% |  | 869139 | 2016-09-30 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-10-31 | 0 | 166255 | 56966051.26 | 41749071.4284 | 15216979.8316 | 56931016 | 26.73% |  | 0 | 2016-10-31 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-11-30 | 0 | 117052 | 56966051.26 | 41866123.4284 | 15099927.8316 | 56931016 | 26.52% |  | 811904 | 2016-11-30 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2016-12-31 | 912839 | 120969 | 57878890.26 | 41987092.4284 | 15891797.8316 | 56931016 | 27.91% |  | 0 | 2016-12-31 | original |  |  | 2016
Marassi Civic Center Pkg 45 | 2017-01-31 | 2242394 | 557957 | 60121284.26 | 42545049.4284 | 17576234.8316 | 56931016 | 30.87% |  | 0 | 2017-01-31 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-02-28 | 0 | 833 | 60121284.26 | 42545882.4284 | 17575401.8316 | 56931016 | 30.87% |  | 0 | 2017-02-28 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-03-31 | 0 | 24387 | 60121284.26 | 42570269.4284 | 17551014.8316 | 56931016 | 30.83% |  | 0 | 2017-03-31 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-04-30 | 0 | 10662 | 60121284.26 | 42580931.4284 | 17540352.8316 | 56931016 | 30.81% |  | 0 | 2017-04-30 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-05-31 | 0 | 3500 | 60121284.26 | 42584431.4284 | 17536852.8316 | 56931016 | 30.8% |  | 0 | 2017-05-31 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-06-30 | 0 | 3000 | 60121284.26 | 42587431.4284 | 17533852.8316 | 56931016 | 30.8% |  | 0 | 2017-06-30 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-07-31 | 0 | 3809 | 60121284.26 | 42591240.4284 | 17530043.8316 | 56931016 | 30.79% |  | 0 | 2017-07-31 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-08-31 | 0 | 167610 | 60121284.26 | 42758850.4284 | 17362433.8316 | 56931016 | 30.5% |  | 0 | 2017-08-31 | original |  |  | 2017
Marassi Civic Center Pkg 45 | 2017-12-31 | 0 | 30720 | 60121284.26 | 42789570.4284 | 17331713.8316 | 56931016 | 30.44% |  | 0 | 2017-12-31 | original |  |  | 2017
1900
Al Oula Infra | 2012-11-30 | 1282219.8 |  | 1282219.8 | 0 | 1282219.8 | 72946445.96 | 1.758% |  | 1102537.12 | 2012-11-30 | original |  | 1143780.12 | 2012
Al Oula Infra | 2012-12-31 | 1642241.84 |  | 2924461.64 | 0 | 2924461.64 | 72946445.96 | 4.009% |  | 1555153.26 | 2012-12-31 | original |  |  | 2012
Al Oula Infra | 2013-01-31 | 1372357.53 |  | 4296819.17 | 0 | 4296819.17 | 72946445.96 | 5.89% |  | 1984932.77 | 2013-01-31 | original |  |  | 2013
Al Oula Infra | 2013-02-28 |  |  | 4296819.17 | 0 | 4296819.17 | 72946445.96 | 5.89% |  |  | 2013-02-28 | original |  |  | 2013
Al Oula Infra | 2013-03-31 |  |  | 4296819.17 | 0 | 4296819.17 | 72946445.96 | 5.89% |  |  | 2013-03-31 | original |  |  | 2013
Al Oula Infra | 2013-04-30 | 1038522.64 |  | 5335341.81 | 0 | 5335341.81 | 72946445.96 | 7.314% |  | 455037.87 | 2013-04-30 | original |  |  | 2013
Al Oula Infra | 2013-05-31 | 152371.09 |  | 5487712.9 | 0 | 5487712.9 | 72946445.96 | 7.523% |  | 132334.03 | 2013-05-31 | original |  |  | 2013
Al Oula Infra | 2013-06-30 | 0 |  | 5487712.9 | 0 | 5487712.9 | 72946445.96 | 7.523% |  | 13152.45 | 2013-06-30 | original |  |  | 2013
Al Oula Infra | 2013-07-31 | 960436.47 |  | 6448149.37 | 0 | 6448149.37 | 72946445.96 | 8.84% |  | 922362.13 | 2013-07-31 | original |  |  | 2013
Al Oula Infra | 2013-08-31 | 970743.47 |  | 7418892.84 | 0 | 7418892.84 | 72946445.96 | 10.17% |  | 919264.65 | 2013-08-31 | original |  |  | 2013
Al Oula Infra | 2013-09-30 | 917923.51 |  | 8336816.35 | 0 | 8336816.35 | 72946445.96 | 11.43% |  | 905504.09 | 2013-09-30 | original |  |  | 2013
Al Oula Infra | 2013-10-31 | 894841.59 |  | 9231657.94 | 0 | 9231657.94 | 72946445.96 | 12.66% |  | 805285.14 | 2013-10-31 | original |  |  | 2013
Al Oula Infra | 2013-11-30 |  |  | 9231657.94 | 0 | 9231657.94 | 72946445.96 | 12.66% |  |  | 2013-11-30 | original |  |  | 2013
Al Oula Infra | 2013-12-31 |  |  | 9231657.94 | 0 | 9231657.94 | 72946445.96 | 12.66% |  |  | 2013-12-31 | original |  |  | 2013
Al Oula Infra | 2014-01-31 | 953478.06 | 155553 | 10185136 | 155553 | 10029583 | 72946445.96 | 13.75% |  | 3573112.59 | 2014-01-31 | original |  |  | 2014
Al Oula Infra | 2014-02-28 | 1984294.87 | 1259419.84 | 12169430.87 | 1414972.84 | 10754458.03 | 72946445.96 | 14.74% |  | 2330524.48 | 2014-02-28 | original |  |  | 2014
Al Oula Infra | 2014-03-31 | 0 | 446040.16 | 12169430.87 | 1861013 | 10308417.87 | 72946445.96 | 14.13% |  |  | 2014-03-31 | original |  |  | 2014
Al Oula Infra | 2014-04-30 | 2835609.68 | 1383606.64 | 15005040.55 | 3244619.64 | 11760420.91 | 72946445.96 | 16.12% |  | 920317.32 | 2014-04-30 | original |  |  | 2014
Al Oula Infra | 2014-05-31 | 1000000 | 911465.1 | 16005040.55 | 4156084.74 | 11848955.81 | 72946445.96 | 16.24% |  | 2261731.74 | 2014-05-31 | original |  |  | 2014
Al Oula Infra | 2014-06-30 | 2482317.59 | 1993077.2 | 18487358.14 | 6149161.94 | 12338196.2 | 72946445.96 | 16.91% |  | 2160160.31 | 2014-06-30 | original |  |  | 2014
Al Oula Infra | 2014-07-31 | 1374359.02 | 1907782.83 | 19861717.16 | 8056944.77 | 11804772.39 | 72946445.96 | 16.18% |  | 3157921 | 2014-07-31 | original |  |  | 2014
Al Oula Infra | 2014-08-31 | 155610.6 | 1027649.39 | 20017327.76 | 9084594.16 | 10932733.6 | 72946445.96 | 14.99% |  | 1931615.02 | 2014-08-31 | original |  |  | 2014
Al Oula Infra | 2014-09-30 | 3194521.8 | 1252838.1 | 23211849.56 | 10337432.26 | 12874417.3 | 72946445.96 | 17.65% |  | 2303487.2 | 2014-09-30 | original |  |  | 2014
Al Oula Infra | 2014-10-31 | 263359.07 | 1671940.6496 | 23475208.63 | 12009372.9096 | 11465835.7204 | 72946445.96 | 15.72% |  | 560098.94 | 2014-10-31 | original |  |  | 2014
Al Oula Infra | 2014-11-30 | 1237279.6 | 769672.42 | 24712488.23 | 12779045.3296 | 11933442.9004 | 72946445.96 | 16.36% |  | 2652754.46 | 2014-11-30 | original |  |  | 2014
Al Oula Infra | 2014-12-31 | 1569343.89 | 1890682.92 | 26281832.12 | 14669728.2496 | 11612103.8704 | 72946445.96 | 15.92% |  | 2735912.02 | 2014-12-31 | original |  |  | 2014
Al Oula Infra | 2015-01-31 | 0 |  | 26281832.12 | 14669728.2496 | 11612103.8704 | 72946445.96 | 15.92% |  | 0 | 2015-01-31 | original |  |  | 2015
Al Oula Infra | 2015-02-28 | 1561421.03 |  | 27843253.15 | 14669728.2496 | 13173524.9004 | 72946445.96 | 18.06% |  | 1606475.57 | 2015-02-28 | original |  |  | 2015
Al Oula Infra | 2015-03-31 | 332453.76 |  | 28175706.91 | 14669728.2496 | 13505978.6604 | 72946445.96 | 18.51% |  | 362162.45 | 2015-03-31 | original |  |  | 2015
Al Oula Infra | 2015-04-30 | 1320407.19 |  | 29496114.1 | 14669728.2496 | 14826385.8504 | 72946445.96 | 20.33% |  | 1897290.31 | 2015-04-30 | original |  |  | 2015
Al Oula Infra | 2015-05-31 | 430210.52 |  | 29926324.62 | 14669728.2496 | 15256596.3704 | 72946445.96 | 20.91% |  | 428247.26 | 2015-05-31 | original |  |  | 2015
1900
New Giza Phase 01 | 2014-09-30 |  | 420681.66 | 0 | 420681.66 | -420681.66 | 172216796.0405 | -0.2443% |  |  |  | original |  |  | 2014
New Giza Phase 01 | 2014-10-31 | 33126223 | 22345868.7 | 33126223 | 22766550.36 | 10359672.64 | 172216796.0405 | 6.015% |  | 4070308 | 2014-10-31 | original |  |  | 2014
New Giza Phase 01 | 2014-11-30 | 2835173 | 4534947.27 | 35961396 | 27301497.63 | 8659898.37 | 172216796.0405 | 5.028% |  | 5457746 | 2014-11-30 | original |  |  | 2014
New Giza Phase 01 | 2014-12-31 | 3801593 | 10060401.03 | 39762989 | 37361898.66 | 2401090.34 | 172216796.0405 | 1.394% |  | 7076513 | 2014-12-31 | original |  |  | 2014
New Giza Phase 01 | 2015-01-31 | 4928609 | 6194030 | 44691598 | 43555928.66 | 1135669.34 | 172216796.0405 | 0.6594% |  | 7510605 | 2015-01-31 | original |  |  | 2015
New Giza Phase 01 | 2015-02-28 | 5377358 | 9392461 | 50068956 | 52948389.66 | -2879433.66 | 172216796.0405 | -1.672% |  | 15322889 | 2015-02-28 | original |  |  | 2015
New Giza Phase 01 | 2015-03-31 | 12437428 | 10726300 | 62506384 | 63674689.66 | -1168305.66 | 172216796.0405 | -0.6784% |  | 21416423 | 2015-03-31 | original |  |  | 2015
New Giza Phase 01 | 2015-04-30 | 14852301 | 26465474 | 77358685 | 90140163.66 | -12781478.66 | 172216796.0405 | -7.422% |  | 26061408 | 2015-04-30 | original |  |  | 2015
New Giza Phase 01 | 2015-05-31 | 19864489 | 6089978 | 97223174 | 96230141.66 | 993032.34 | 172216796.0405 | 0.5766% |  | 26433358 | 2015-05-31 | original |  |  | 2015
New Giza Phase 01 | 2015-06-30 | 0 | 18417415 | 97223174 | 114647556.66 | -17424382.66 | 172216796.0405 | -10.12% |  | 12518448 | 2015-06-30 | original |  |  | 2015
New Giza Phase 01 | 2015-07-31 | 18290570 | 14025027 | 115513744 | 128672583.66 | -13158839.66 | 172216796.0405 | -7.641% |  | 6572985 | 2015-07-31 | original |  |  | 2015
New Giza Phase 01 | 2015-08-31 | 8712875 | 9340026 | 124226619 | 138012609.66 | -13785990.66 | 172216796.0405 | -8.005% |  | 4027853 | 2015-08-31 | original |  |  | 2015
New Giza Phase 01 | 2015-09-30 | 3740191 | 6902824 | 127966810 | 144915433.66 | -16948623.66 | 172216796.0405 | -9.841% |  | 11787603 | 2015-09-30 | original |  |  | 2015
New Giza Phase 01 | 2015-10-31 | 3810161 | 1736860 | 131776971 | 146652293.66 | -14875322.66 | 172216796.0405 | -8.638% |  | 3038222 | 2015-10-31 | original |  |  | 2015
New Giza Phase 01 | 2015-11-30 | 0 | 1272238 | 131776971 | 147924531.66 | -16147560.66 | 172216796.0405 | -9.376% |  | 2377345 | 2015-11-30 | original |  |  | 2015
New Giza Phase 01 | 2015-12-31 | 6962059 | 9169059 | 138739030 | 157093590.66 | -18354560.66 | 172216796.0405 | -10.66% |  | 4185609 | 2015-12-31 | original |  |  | 2015
New Giza Phase 01 | 2016-01-31 | 0 | 580372 | 138739030 | 157673962.66 | -18934932.66 | 172216796.0405 | -10.99% |  | 2127586 | 2016-01-31 | original |  |  | 2016
New Giza Phase 01 | 2016-02-29 | 0 | 484922 | 138739030 | 158158884.66 | -19419854.66 | 172216796.0405 | -11.28% |  | 3677610 | 2016-02-29 | original |  |  | 2016
New Giza Phase 01 | 2016-03-31 | 3770042 | 2480314 | 142509072 | 160639198.66 | -18130126.66 | 172216796.0405 | -10.53% |  | 494877 | 2016-03-31 | original |  |  | 2016
New Giza Phase 01 | 2016-04-30 | 6658941 | 5657717 | 149168013 | 166296915.66 | -17128902.66 | 172216796.0405 | -9.946% |  | 2071377 | 2016-04-30 | original |  |  | 2016
New Giza Phase 01 | 2016-05-31 | 1785421 | 401446 | 150953434 | 166698361.66 | -15744927.66 | 172216796.0405 | -9.143% |  | 239952 | 2016-05-31 | original |  |  | 2016
New Giza Phase 01 | 2016-06-30 | 1284266 | 1837421 | 152237700 | 168535782.66 | -16298082.66 | 172216796.0405 | -9.464% |  | 0 | 2016-06-30 | original |  |  | 2016
New Giza Phase 01 | 2016-07-31 | 0 | 637615 | 152237700 | 169173397.66 | -16935697.66 | 172216796.0405 | -9.834% |  | 2008293 | 2016-07-31 | original |  |  | 2016
New Giza Phase 01 | 2016-08-31 | 1538142 | 383186 | 153775842 | 169556583.66 | -15780741.66 | 172216796.0405 | -9.163% |  | 0 | 2016-08-31 | original |  |  | 2016
New Giza Phase 01 | 2016-09-30 | 7242730 | 3487128 | 161018572 | 173043711.66 | -12025139.66 | 172216796.0405 | -6.983% |  | 573623 | 2016-09-30 | original |  |  | 2016
New Giza Phase 01 | 2016-10-31 | 0 | 76623 | 161018572 | 173120334.66 | -12101762.66 | 172216796.0405 | -7.027% |  | 0 | 2016-10-31 | original |  |  | 2016
New Giza Phase 01 | 2016-11-30 | 1832963 | 36836 | 162851535 | 173157170.66 | -10305635.66 | 172216796.0405 | -5.984% |  | 0 | 2016-11-30 | original |  |  | 2016
New Giza Phase 01 | 2016-12-31 | 0 | 444420 | 162851535 | 173601590.66 | -10750055.66 | 172216796.0405 | -6.242% |  | 0 | 2016-12-31 | original |  |  | 2016
New Giza Phase 01 | 2017-01-31 | 0 | 272750 | 162851535 | 173874340.66 | -11022805.66 | 172216796.0405 | -6.401% |  | 0 | 2017-01-31 | original |  |  | 2017
New Giza Phase 01 | 2017-02-28 | 0 | 7016 | 162851535 | 173881356.66 | -11029821.66 | 172216796.0405 | -6.405% |  | 0 | 2017-02-28 | original |  |  | 2017
New Giza Phase 01 | 2017-03-31 | 0 | 6845 | 162851535 | 173888201.66 | -11036666.66 | 172216796.0405 | -6.409% |  | 0 | 2017-03-31 | original |  |  | 2017
New Giza Phase 01 | 2017-04-30 | 0 | 753828 | 162851535 | 174642029.66 | -11790494.66 | 172216796.0405 | -6.846% |  | 0 | 2017-04-30 | original |  |  | 2017
New Giza Phase 01 | 2017-05-31 | 0 | 297990 | 162851535 | 174940019.66 | -12088484.66 | 172216796.0405 | -7.019% |  | 0 | 2017-05-31 | original |  |  | 2017
New Giza Phase 01 | 2017-06-30 | 0 | 7961 | 162851535 | 174947980.66 | -12096445.66 | 172216796.0405 | -7.024% |  | 0 | 2017-06-30 | original |  |  | 2017
New Giza Phase 01 | 2017-07-31 | 0 | 4977 | 162851535 | 174952957.66 | -12101422.66 | 172216796.0405 | -7.027% |  | 0 | 2017-07-31 | original |  |  | 2017
New Giza Phase 01 | 2017-08-31 | 4029400 | 2000000 | 166880935 | 176952957.66 | -10072022.66 | 172216796.0405 | -5.848% |  | 0 | 2017-08-31 | original |  |  | 2017
New Giza Phase 01 | 2017-10-31 | 0 | 0 | 166880935 | 176952957.66 | -10072022.66 | 172216796.0405 | -5.848% |  | 6377727.87 | 2017-10-31 | original |  |  | 2017
New Giza Phase 01 | 2017-11-30 | 4561573 | 0 | 171442508 | 176952957.66 | -5510449.66 | 172216796.0405 | -3.2% |  | 0 | 2017-11-30 | original |  |  | 2017
New Giza Phase 01 | 2017-12-31 | 0 | 2975394 | 171442508 | 179928351.66 | -8485843.66 | 172216796.0405 | -4.927% |  | 0 | 2017-12-31 | original |  |  | 2017
1900
Hyper Solimanya | 2014-06-30 | 16750000 | 52005.48 | 16750000 | 52005.48 | 16697994.52 | 110450184.62 | 15.12% |  |  |  | original |  |  | 2014
Hyper Solimanya | 2014-07-31 | 0 | 388799.06 | 16750000 | 440804.54 | 16309195.46 | 110450184.62 | 14.77% |  |  |  | original |  |  | 2014
Hyper Solimanya | 2014-08-31 | 1708588 | 2597195.25 | 18458588 | 3037999.79 | 15420588.21 | 110450184.62 | 13.96% |  |  |  | original |  |  | 2014
Hyper Solimanya | 2014-09-30 | 1348749 | 1716979.29 | 19807337 | 4754979.08 | 15052357.92 | 110450184.62 | 13.63% |  |  |  | original |  |  | 2014
Hyper Solimanya | 2014-10-31 | 5087011 | 4728640.44 | 24894348 | 9483619.52 | 15410728.48 | 110450184.62 | 13.95% |  |  |  | original |  |  | 2014
Hyper Solimanya | 2014-11-30 | 6510468 | 8169739.38 | 31404816 | 17653358.9 | 13751457.1 | 110450184.62 | 12.45% |  | 28151956 | 2014-11-30 | original |  |  | 2014
Hyper Solimanya | 2014-12-31 | 12930069.4 | 11832712.72 | 44334885.4 | 29486071.62 | 14848813.78 | 110450184.62 | 13.44% |  | 5160865 | 2014-12-31 | original |  |  | 2014
Hyper Solimanya | 2015-01-31 | 3259514 | 5062604 | 47594399.4 | 34548675.62 | 13045723.78 | 110450184.62 | 11.81% |  | 6233182 | 2015-01-31 | original |  |  | 2015
Hyper Solimanya | 2015-02-28 | 4204986 | 6758235 | 51799385.4 | 41306910.62 | 10492474.78 | 110450184.62 | 9.5% |  | 4894046 | 2015-02-28 | original |  |  | 2015
Hyper Solimanya | 2015-03-31 | 3342260 | 5459976 | 55141645.4 | 46766886.62 | 8374758.78 | 110450184.62 | 7.582% |  | 3151181 | 2015-03-31 | original |  |  | 2015
Hyper Solimanya | 2015-04-30 | 448748 | 5255727 | 55590393.4 | 52022613.62 | 3567779.78 | 110450184.62 | 3.23% |  | 7766186 | 2015-04-30 | original |  |  | 2015
Hyper Solimanya | 2015-05-31 | 9019935 | 4712105 | 64610328.4 | 56734718.62 | 7875609.78 | 110450184.62 | 7.13% |  | 5157059 | 2015-05-31 | original |  |  | 2015
Hyper Solimanya | 2015-06-30 | 4536200 | 4383659 | 69146528.4 | 61118377.62 | 8028150.78 | 110450184.62 | 7.269% |  | 5968470 | 2015-06-30 | original |  |  | 2015
Hyper Solimanya | 2015-07-31 | 0 | 6130413 | 69146528.4 | 67248790.62 | 1897737.78 | 110450184.62 | 1.718% |  | 5601446 | 2015-07-31 | original |  |  | 2015
Hyper Solimanya | 2015-08-31 | 5435883 | 5856543 | 74582411.4 | 73105333.62 | 1477077.78 | 110450184.62 | 1.337% |  | 4308584 | 2015-08-31 | original |  |  | 2015
Hyper Solimanya | 2015-09-30 | 5908096 | 4259405 | 80490507.4 | 77364738.62 | 3125768.78 | 110450184.62 | 2.83% |  | 5308802 | 2015-09-30 | original |  |  | 2015
Hyper Solimanya | 2015-10-31 | 5178516 | 2710525 | 85669023.4 | 80075263.62 | 5593759.78 | 110450184.62 | 5.065% |  | 3400766 | 2015-10-31 | original |  |  | 2015
Hyper Solimanya | 2015-11-30 | 6198762 | 3408392 | 91867785.4 | 83483655.62 | 8384129.78 | 110450184.62 | 7.591% |  | 0 | 2015-11-30 | original |  |  | 2015
Hyper Solimanya | 2015-12-31 | 2307372 | 1727318 | 94175157.4 | 85210973.62 | 8964183.78 | 110450184.62 | 8.116% |  | 0 | 2015-12-31 | original |  |  | 2015
Hyper Solimanya | 2016-01-31 | 0 | 1983705 | 94175157.4 | 87194678.62 | 6980478.78 | 110450184.62 | 6.32% |  | 0 | 2016-01-31 | original |  |  | 2016
Hyper Solimanya | 2016-02-29 | 0 | 1157008 | 94175157.4 | 88351686.62 | 5823470.78 | 110450184.62 | 5.272% |  | 0 | 2016-02-29 | original |  |  | 2016
Hyper Solimanya | 2016-03-31 | 0 | 340596 | 94175157.4 | 88692282.62 | 5482874.78 | 110450184.62 | 4.964% |  | 0 | 2016-03-31 | original |  |  | 2016
Hyper Solimanya | 2016-04-30 | 0 | 218086 | 94175157.4 | 88910368.62 | 5264788.78 | 110450184.62 | 4.767% |  | 6387675 | 2016-04-30 | original |  |  | 2016
Hyper Solimanya | 2016-05-31 | 0 | 960676 | 94175157.4 | 89871044.62 | 4304112.78 | 110450184.62 | 3.897% |  | 3041879 | 2016-05-31 | original |  |  | 2016
Hyper Solimanya | 2016-06-30 | 0 | 752280 | 94175157.4 | 90623324.62 | 3551832.78 | 110450184.62 | 3.216% |  | 0 | 2016-06-30 | original |  |  | 2016
Hyper Solimanya | 2016-07-31 | 1000000 | 763392 | 95175157.4 | 91386716.62 | 3788440.78 | 110450184.62 | 3.43% |  | 5736350 | 2016-07-31 | original |  |  | 2016
Hyper Solimanya | 2016-08-31 | 1000000 | 2546647 | 96175157.4 | 93933363.62 | 2241793.78 | 110450184.62 | 2.03% |  | 0 | 2016-08-31 | original |  |  | 2016
Hyper Solimanya | 2016-09-30 | 803468 | 858598 | 96978625.4 | 94791961.62 | 2186663.78 | 110450184.62 | 1.98% |  | 2477444 | 2016-09-30 | original |  |  | 2016
Hyper Solimanya | 2016-10-31 | 0 | 1705520 | 96978625.4 | 96497481.62 | 481143.78 | 110450184.62 | 0.4356% |  | 2737674 | 2016-10-31 | original |  |  | 2016
Hyper Solimanya | 2016-11-30 | 5417312 | 1260821 | 102395937.4 | 97758302.62 | 4637634.78 | 110450184.62 | 4.199% |  | 0 | 2016-11-30 | original |  |  | 2016
Hyper Solimanya | 2016-12-31 | 0 | 1023770 | 102395937.4 | 98782072.62 | 3613864.78 | 110450184.62 | 3.272% |  | 5227900 | 2016-12-31 | original |  |  | 2016
Hyper Solimanya | 2017-01-31 | 0 | 896570 | 102395937.4 | 99678642.62 | 2717294.78 | 110450184.62 | 2.46% |  | 0 | 2017-01-31 | original |  |  | 2017
Hyper Solimanya | 2017-02-28 | 4889400 | 291102 | 107285337.4 | 99969744.62 | 7315592.78 | 110450184.62 | 6.623% |  | 0 | 2017-02-28 | original |  |  | 2017
Hyper Solimanya | 2017-03-31 | 0 | 763038 | 107285337.4 | 100732782.62 | 6552554.78 | 110450184.62 | 5.933% |  | 0 | 2017-03-31 | original |  |  | 2017
Hyper Solimanya | 2017-04-30 | 0 | 1632574 | 107285337.4 | 102365356.62 | 4919980.78 | 110450184.62 | 4.454% |  | 0 | 2017-04-30 | original |  |  | 2017
Hyper Solimanya | 2017-05-31 | 0 | 770281 | 107285337.4 | 103135637.62 | 4149699.78 | 110450184.62 | 3.757% |  | 0 | 2017-05-31 | original |  |  | 2017
Hyper Solimanya | 2017-06-30 | 0 | 87975 | 107285337.4 | 103223612.62 | 4061724.78 | 110450184.62 | 3.677% |  | 0 | 2017-06-30 | original |  |  | 2017
Hyper Solimanya | 2017-07-31 | 0 | 918963 | 107285337.4 | 104142575.62 | 3142761.78 | 110450184.62 | 2.845% |  | 0 | 2017-07-31 | original |  |  | 2017
Hyper Solimanya | 2017-09-30 | 1321895 | 0 | 108607232.4 | 104142575.62 | 4464656.78 | 110450184.62 | 4.042% |  | 0 | 2017-09-30 | original |  |  | 2017
Hyper Solimanya | 2017-10-31 | 0 | 186197 | 108607232.4 | 104328772.62 | 4278459.78 | 110450184.62 | 3.874% |  | 0 | 2017-10-31 | original |  |  | 2017
Hyper Solimanya | 2017-11-30 | 0 | 161237 | 108607232.4 | 104490009.62 | 4117222.78 | 110450184.62 | 3.728% |  | 0 | 2017-11-30 | original |  |  | 2017
Hyper Solimanya | 2020-08-17 | 4000000 |  | 112607232.4 | 104490009.62 | 8117222.78 | 110450184.62 | 7.349% |  |  | 2020-08-17 | added 1 |  |  | 2020
1900
Ismailia Bridges | 2017-01-31 | 0 | 392672 | 0 | 392672 | -392672 | 56527617 | -0.6947% |  | 0 | 2017-01-31 | original |  |  | 2017
Ismailia Bridges | 2017-02-28 | 0 | 433326 | 0 | 825998 | -825998 | 56527617 | -1.461% |  | 4887326 | 2017-02-28 | original |  |  | 2017
Ismailia Bridges | 2017-03-31 | 0 | 1104825 | 0 | 1930823 | -1930823 | 56527617 | -3.416% |  | 4766326 | 2017-03-31 | original |  |  | 2017
Ismailia Bridges | 2017-04-30 | 0 | 1644983 | 0 | 3575806 | -3575806 | 56527617 | -6.326% |  | 0 | 2017-04-30 | original |  |  | 2017
Ismailia Bridges | 2017-05-31 | 0 | 1585186 | 0 | 5160992 | -5160992 | 56527617 | -9.13% |  | 0 | 2017-05-31 | original |  |  | 2017
Ismailia Bridges | 2017-06-01 | 0 | 127942.5 | 0 | 5288934.5 | -5288934.5 | 56527617 | -9.356% |  |  |  | cash out both |  |  | 2017
Ismailia Bridges | 2017-06-30 | 0 | 883605 | 0 | 6172539.5 | -6172539.5 | 56527617 | -10.92% |  | 5538681 | 2017-06-30 | original |  |  | 2017
Ismailia Bridges | 2017-07-01 | 0 | 9464 | 0 | 6182003.5 | -6182003.5 | 56527617 | -10.94% |  |  |  | cash out both |  |  | 2017
Ismailia Bridges | 2017-07-31 | 0 | 878607 | 0 | 7060610.5 | -7060610.5 | 56527617 | -12.49% |  | 2576439 | 2017-07-31 | original |  |  | 2017
Ismailia Bridges | 2017-08-01 | 0 | 21980.5 | 0 | 7082591 | -7082591 | 56527617 | -12.53% |  |  |  | cash out both |  |  | 2017
Ismailia Bridges | 2017-08-31 | 0 | 4168453 | 0 | 11251044 | -11251044 | 56527617 | -19.9% |  | 6966921 | 2017-08-31 | original |  |  | 2017
Ismailia Bridges | 2017-09-01 | 0 | 6751.23 | 0 | 11257795.23 | -11257795.23 | 56527617 | -19.92% |  |  |  | cash out both |  |  | 2017
Ismailia Bridges | 2017-09-30 | 0 | 1893017 | 0 | 13150812.23 | -13150812.23 | 56527617 | -23.26% |  | 2591250 | 2017-09-30 | original |  |  | 2017
Ismailia Bridges | 2017-10-01 | 0 | 7310 | 0 | 13158122.23 | -13158122.23 | 56527617 | -23.28% |  |  |  | cash out both |  |  | 2017
Ismailia Bridges | 2017-10-31 | 0 | 2443448 | 0 | 15601570.23 | -15601570.23 | 56527617 | -27.6% |  | 9251895 | 2017-10-31 | original |  |  | 2017
Ismailia Bridges | 2017-11-01 | 0 | 2067 | 0 | 15603637.23 | -15603637.23 | 56527617 | -27.6% |  |  |  | cash out both |  |  | 2017
Ismailia Bridges | 2017-11-30 | 3328227 | 1359661 | 3328227 | 16963298.23 | -13635071.23 | 56527617 | -24.12% |  | 3709327 | 2017-11-30 | original |  |  | 2017
Ismailia Bridges | 2017-12-01 |  | 108320.6 | 3328227 | 17071618.83 | -13743391.83 | 56527617 | -24.31% |  |  |  | cash out both |  |  | 2017
Ismailia Bridges | 2017-12-31 | 5277681 | 1626182 | 8605908 | 18697800.83 | -10091892.83 | 56527617 | -17.85% |  | 11126864 | 2017-12-31 | original |  |  | 2017
Ismailia Bridges | 2018-01-01 |  | 56013 | 8605908 | 18753813.83 | -10147905.83 | 56527617 | -17.95% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-01-18 | 2307926.3 |  | 10913834.3 | 18753813.83 | -7839979.53 | 56527617 | -13.87% |  |  | 2018-01-18 | added cash in 3 |  |  | 2018
Ismailia Bridges | 2018-02-01 |  | 132600.4 | 10913834.3 | 18886414.23 | -7972579.93 | 56527617 | -14.1% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-03-01 |  | 225944.45 | 10913834.3 | 19112358.68 | -8198524.38 | 56527617 | -14.5% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-04-01 |  | 75637.61 | 10913834.3 | 19187996.29 | -8274161.99 | 56527617 | -14.64% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-05-01 |  | 52941.98 | 10913834.3 | 19240938.27 | -8327103.97 | 56527617 | -14.73% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-06-01 |  | 112501.59 | 10913834.3 | 19353439.86 | -8439605.56 | 56527617 | -14.93% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-07-01 |  | 87884.46 | 10913834.3 | 19441324.32 | -8527490.02 | 56527617 | -15.09% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-08-01 |  | 89562.44 | 10913834.3 | 19530886.76 | -8617052.46 | 56527617 | -15.24% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-09-01 |  | 22079.96 | 10913834.3 | 19552966.72 | -8639132.42 | 56527617 | -15.28% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-10-01 |  | 611278 | 10913834.3 | 20164244.72 | -9250410.42 | 56527617 | -16.36% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-10-29 | 5747504 |  | 16661338.3 | 20164244.72 | -3502906.42 | 56527617 | -6.197% |  |  | 2018-10-29 | added cash in 3 |  |  | 2018
Ismailia Bridges | 2018-11-01 |  | 121006.54 | 16661338.3 | 20285251.26 | -3623912.96 | 56527617 | -6.411% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-12-01 |  | 428359.65 | 16661338.3 | 20713610.91 | -4052272.61 | 56527617 | -7.169% |  |  |  | cash out both |  |  | 2018
Ismailia Bridges | 2018-12-10 | 5204466.15 |  | 21865804.45 | 20713610.91 | 1152193.54 | 56527617 | 2.038% |  |  | 2018-12-10 | added cash in 3 |  |  | 2018
Ismailia Bridges | 2018-12-18 | 851862 |  | 22717666.45 | 20713610.91 | 2004055.54 | 56527617 | 3.545% |  |  | 2018-12-18 | added cash in 3 |  |  | 2018
Ismailia Bridges | 2019-01-01 |  | 19831.05 | 22717666.45 | 20733441.96 | 1984224.49 | 56527617 | 3.51% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-02-01 |  | 333539.48 | 22717666.45 | 21066981.44 | 1650685.01 | 56527617 | 2.92% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-03-01 |  | 159734.85 | 22717666.45 | 21226716.29 | 1490950.16 | 56527617 | 2.638% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-03-04 | 5111907.85 |  | 27829574.3 | 21226716.29 | 6602858.01 | 56527617 | 11.68% |  |  | 2019-03-04 | added cash in 3 |  |  | 2019
Ismailia Bridges | 2019-03-04 | 4256312.3 |  | 32085886.6 | 21226716.29 | 10859170.31 | 56527617 | 19.21% |  |  | 2019-03-04 | added cash in 3 |  |  | 2019
Ismailia Bridges | 2019-03-17 | 350551.65 |  | 32436438.25 | 21226716.29 | 11209721.96 | 56527617 | 19.83% |  |  | 2019-03-17 | added cash in 3 |  |  | 2019
Ismailia Bridges | 2019-04-01 |  | 123883.85 | 32436438.25 | 21350600.14 | 11085838.11 | 56527617 | 19.61% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-05-01 |  | 117174.95 | 32436438.25 | 21467775.09 | 10968663.16 | 56527617 | 19.4% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-06-01 |  | 178591.18 | 32436438.25 | 21646366.27 | 10790071.98 | 56527617 | 19.09% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-07-01 |  | 80834 | 32436438.25 | 21727200.27 | 10709237.98 | 56527617 | 18.95% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-08-01 |  | 118814.43 | 32436438.25 | 21846014.7 | 10590423.55 | 56527617 | 18.73% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-09-01 |  | 11397.33 | 32436438.25 | 21857412.03 | 10579026.22 | 56527617 | 18.71% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-10-01 |  | 10753.86 | 32436438.25 | 21868165.89 | 10568272.36 | 56527617 | 18.7% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-11-01 |  | 8524.83 | 32436438.25 | 21876690.72 | 10559747.53 | 56527617 | 18.68% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2019-11-30 | 29057 |  | 32465495.25 | 21876690.72 | 10588804.53 | 56527617 | 18.73% |  |  | 2019-11-30 | added cash in 3 |  |  | 2019
Ismailia Bridges | 2019-12-01 |  | 7500 | 32465495.25 | 21884190.72 | 10581304.53 | 56527617 | 18.72% |  |  |  | cash out both |  |  | 2019
Ismailia Bridges | 2020-01-01 |  | 218281 | 32465495.25 | 22102471.72 | 10363023.53 | 56527617 | 18.33% |  |  |  | cash out both |  |  | 2020
Ismailia Bridges | 2020-02-01 |  | 600 | 32465495.25 | 22103071.72 | 10362423.53 | 56527617 | 18.33% |  |  |  | cash out both |  |  | 2020
Ismailia Bridges | 2020-09-01 |  | 423111.4 | 32465495.25 | 22526183.12 | 9939312.13 | 56527617 | 17.58% |  |  |  | cash out both |  |  | 2020
1900
Maxium Mall | 2015-03-31 | 15224252 | 4822917 | 15224252 | 4822917 | 10401335 | 98576600 | 10.55% |  | 1439514 | 2015-03-31 | original |  |  | 2015
Maxium Mall | 2015-04-30 | 0 | 3255994 | 15224252 | 8078911 | 7145341 | 98576600 | 7.249% |  | 1771139 | 2015-04-30 | original |  |  | 2015
Maxium Mall | 2015-05-31 | 0 | 3190107 | 15224252 | 11269018 | 3955234 | 98576600 | 4.012% |  | 2707257 | 2015-05-31 | original |  |  | 2015
Maxium Mall | 2015-06-30 | 244015 | 2140642 | 15468267 | 13409660 | 2058607 | 98576600 | 2.088% |  | 0 | 2015-06-30 | original |  |  | 2015
Maxium Mall | 2015-07-31 | 400000 | 3534973 | 15868267 | 16944633 | -1076366 | 98576600 | -1.092% |  | 0 | 2015-07-31 | original |  |  | 2015
Maxium Mall | 2015-08-31 | 0 | 2972390 | 15868267 | 19917023 | -4048756 | 98576600 | -4.107% |  | 8255695 | 2015-08-31 | original |  |  | 2015
Maxium Mall | 2015-09-30 | 2360774 | 2474254 | 18229041 | 22391277 | -4162236 | 98576600 | -4.222% |  | 2375384 | 2015-09-30 | original |  |  | 2015
Maxium Mall | 2015-10-31 | 0 | 3987025 | 18229041 | 26378302 | -8149261 | 98576600 | -8.267% |  | 2636612 | 2015-10-31 | original |  |  | 2015
Maxium Mall | 2015-11-30 | 0 | 2603449 | 18229041 | 28981751 | -10752710 | 98576600 | -10.91% |  | 4413767 | 2015-11-30 | original |  |  | 2015
Maxium Mall | 2015-12-31 | 5000000 | 3764312 | 23229041 | 32746063 | -9517022 | 98576600 | -9.654% |  | 6388454 | 2015-12-31 | original |  |  | 2015
Maxium Mall | 2016-01-31 | 0 | 1595837 | 23229041 | 34341900 | -11112859 | 98576600 | -11.27% |  | 3641125 | 2016-01-31 | original |  |  | 2016
Maxium Mall | 2016-02-29 | 5451339 | 2109944 | 28680380 | 36451844 | -7771464 | 98576600 | -7.884% |  | 6086206 | 2016-02-29 | original |  |  | 2016
Maxium Mall | 2016-03-31 | 7015308 | 3990806 | 35695688 | 40442650 | -4746962 | 98576600 | -4.816% |  | 5036933 | 2016-03-31 | original |  |  | 2016
Maxium Mall | 2016-04-30 | 3110526 | 4060261 | 38806214 | 44502911 | -5696697 | 98576600 | -5.779% |  | 4775714 | 2016-04-30 | original |  |  | 2016
Maxium Mall | 2016-05-31 | 7420666 | 5104900 | 46226880 | 49607811 | -3380931 | 98576600 | -3.43% |  | 6573287 | 2016-05-31 | original |  |  | 2016
Maxium Mall | 2016-06-30 | 3865200 | 8773380 | 50092080 | 58381191 | -8289111 | 98576600 | -8.409% |  | 6082936 | 2016-06-30 | original |  |  | 2016
Maxium Mall | 2016-07-31 | 1519015 | 4405159 | 51611095 | 62786350 | -11175255 | 98576600 | -11.34% |  | 5840450 | 2016-07-31 | original |  |  | 2016
Maxium Mall | 2016-08-31 | 4813144 | 3187880 | 56424239 | 65974230 | -9549991 | 98576600 | -9.688% |  | 3848433 | 2016-08-31 | original |  |  | 2016
Maxium Mall | 2016-09-30 | 5771123 | 2199541 | 62195362 | 68173771 | -5978409 | 98576600 | -6.065% |  | 7341288 | 2016-09-30 | original |  |  | 2016
Maxium Mall | 2016-10-31 | 0 | 2712710 | 62195362 | 70886481 | -8691119 | 98576600 | -8.817% |  | 2797229 | 2016-10-31 | original |  |  | 2016
Maxium Mall | 2016-11-30 | 2273138 | 2562221 | 64468500 | 73448702 | -8980202 | 98576600 | -9.11% |  | 3527531 | 2016-11-30 | original |  |  | 2016
Maxium Mall | 2016-12-31 | 2018939 | 2047212 | 66487439 | 75495914 | -9008475 | 98576600 | -9.139% |  | 2687601 | 2016-12-31 | original |  |  | 2016
Maxium Mall | 2017-01-31 | 0 | 2352202 | 66487439 | 77848116 | -11360677 | 98576600 | -11.52% |  | 0 | 2017-01-31 | original |  |  | 2017
Maxium Mall | 2017-02-28 | 2408492 | 1408853 | 68895931 | 79256969 | -10361038 | 98576600 | -10.51% |  | 0 | 2017-02-28 | original |  |  | 2017
Maxium Mall | 2017-03-30 | 3311465.16 |  | 72207396.16 | 79256969 | -7049572.84 | 98576600 | -7.151% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
Maxium Mall | 2017-03-31 | 1100000 | 1221082 | 73307396.16 | 80478051 | -7170654.84 | 98576600 | -7.274% |  | 2104189 | 2017-03-31 | original |  |  | 2017
Maxium Mall | 2017-04-01 |  | 51746.05 | 73307396.16 | 80529797.05 | -7222400.89 | 98576600 | -7.327% |  |  |  | cash out both |  |  | 2017
Maxium Mall | 2017-04-30 | 0 | 1548129 | 73307396.16 | 82077926.05 | -8770529.89 | 98576600 | -8.897% |  | 0 | 2017-04-30 | original |  |  | 2017
Maxium Mall | 2017-05-31 | 0 | 586227 | 73307396.16 | 82664153.05 | -9356756.89 | 98576600 | -9.492% |  | 3722169 | 2017-05-31 | original |  |  | 2017
Maxium Mall | 2017-06-30 | 2000000 | 1157847 | 75307396.16 | 83822000.05 | -8514603.89 | 98576600 | -8.638% |  | 0 | 2017-06-30 | original |  |  | 2017
Maxium Mall | 2017-07-01 |  | 4055.04 | 75307396.16 | 83826055.09 | -8518658.93 | 98576600 | -8.642% |  |  |  | cash out both |  |  | 2017
Maxium Mall | 2017-07-31 | 1000000 | 400939 | 76307396.16 | 84226994.09 | -7919597.93 | 98576600 | -8.034% |  | 0 | 2017-07-31 | original |  |  | 2017
Maxium Mall | 2017-08-01 |  | 28386.74 | 76307396.16 | 84255380.83 | -7947984.67 | 98576600 | -8.063% |  |  |  | cash out both |  |  | 2017
Maxium Mall | 2017-08-31 | 2000000 | 591194 | 78307396.16 | 84846574.83 | -6539178.67 | 98576600 | -6.634% |  | 0 | 2017-08-31 | original |  |  | 2017
Maxium Mall | 2017-09-01 |  | 17567 | 78307396.16 | 84864141.83 | -6556745.67 | 98576600 | -6.651% |  |  |  | cash out both |  |  | 2017
Maxium Mall | 2017-09-30 | 0 | 200508 | 78307396.16 | 85064649.83 | -6757253.67 | 98576600 | -6.855% |  | 0 | 2017-09-30 | original |  |  | 2017
Maxium Mall | 2017-10-01 |  | 43619 | 78307396.16 | 85108268.83 | -6800872.67 | 98576600 | -6.899% |  |  |  | cash out both |  |  | 2017
Maxium Mall | 2017-10-31 | 0 | 260665 | 78307396.16 | 85368933.83 | -7061537.67 | 98576600 | -7.164% |  | 0 | 2017-10-31 | original |  |  | 2017
Maxium Mall | 2017-11-01 |  | 4858 | 78307396.16 | 85373791.83 | -7066395.67 | 98576600 | -7.168% |  |  |  | cash out both |  |  | 2017
Maxium Mall | 2017-11-30 | 0 | 318876 | 78307396.16 | 85692667.83 | -7385271.67 | 98576600 | -7.492% |  | 0 | 2017-11-30 | original |  |  | 2017
Maxium Mall | 2017-12-01 |  | 23918.38 | 78307396.16 | 85716586.21 | -7409190.05 | 98576600 | -7.516% |  |  |  | cash out both |  |  | 2017
Maxium Mall | 2017-12-31 | 0 | 620213 | 78307396.16 | 86336799.21 | -8029403.05 | 98576600 | -8.145% |  | 0 | 2017-12-31 | original |  |  | 2017
Maxium Mall | 2018-01-01 |  | 50706.56 | 78307396.16 | 86387505.77 | -8080109.61 | 98576600 | -8.197% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-01-21 | 1000000 |  | 79307396.16 | 86387505.77 | -7080109.61 | 98576600 | -7.182% |  |  | 2018-01-21 | added cash in 3 |  |  | 2018
Maxium Mall | 2018-02-01 |  | 784 | 79307396.16 | 86388289.77 | -7080893.61 | 98576600 | -7.183% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-03-01 |  | 171689.7 | 79307396.16 | 86559979.47 | -7252583.31 | 98576600 | -7.357% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-05-01 |  | 64250.32 | 79307396.16 | 86624229.79 | -7316833.63 | 98576600 | -7.422% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-05-27 | 2900000 |  | 82207396.16 | 86624229.79 | -4416833.63 | 98576600 | -4.481% |  |  | 2018-05-27 | added cash in 3 |  |  | 2018
Maxium Mall | 2018-06-01 |  | 98524.93 | 82207396.16 | 86722754.72 | -4515358.56 | 98576600 | -4.581% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-07-01 |  | 800 | 82207396.16 | 86723554.72 | -4516158.56 | 98576600 | -4.581% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-07-09 | 2900000 |  | 85107396.16 | 86723554.72 | -1616158.56 | 98576600 | -1.639% |  |  | 2018-07-09 | added cash in 3 |  |  | 2018
Maxium Mall | 2018-08-01 |  | 350928.63 | 85107396.16 | 87074483.35 | -1967087.19 | 98576600 | -1.995% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-10-01 |  | 400000 | 85107396.16 | 87474483.35 | -2367087.19 | 98576600 | -2.401% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-10-25 | 1000000 |  | 86107396.16 | 87474483.35 | -1367087.19 | 98576600 | -1.387% |  |  | 2018-10-25 | added cash in 3 |  |  | 2018
Maxium Mall | 2018-11-01 |  | 27666.56 | 86107396.16 | 87502149.91 | -1394753.75 | 98576600 | -1.415% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2018-12-01 |  | 14.06 | 86107396.16 | 87502163.97 | -1394767.81 | 98576600 | -1.415% |  |  |  | cash out both |  |  | 2018
Maxium Mall | 2019-01-01 |  | 2340522.73 | 86107396.16 | 89842686.7 | -3735290.54 | 98576600 | -3.789% |  |  |  | cash out both |  |  | 2019
Maxium Mall | 2019-03-01 |  | 116366.16 | 86107396.16 | 89959052.86 | -3851656.7 | 98576600 | -3.907% |  |  |  | cash out both |  |  | 2019
Maxium Mall | 2019-07-17 | 4000000 |  | 90107396.16 | 89959052.86 | 148343.3 | 98576600 | 0.1505% |  |  | 2019-07-17 | added cash in 3 |  |  | 2019
Maxium Mall | 2019-12-09 | 3250000 |  | 93357396.16 | 89959052.86 | 3398343.3 | 98576600 | 3.447% |  |  | 2019-12-09 | added cash in 3 |  |  | 2019
Maxium Mall | 2019-12-09 | 2985954 |  | 96343350.16 | 89959052.86 | 6384297.3 | 98576600 | 6.476% |  |  | 2019-12-09 | added cash in 3 |  |  | 2019
Maxium Mall | 2020-06-01 |  | 42300 | 96343350.16 | 90001352.86 | 6341997.3 | 98576600 | 6.434% |  |  |  | cash out both |  |  | 2020
Maxium Mall | 2020-10-12 | 3250000 |  | 99593350.16 | 90001352.86 | 9591997.3 | 98576600 | 9.731% |  |  | 2020-10-12 | added cash in 3 |  |  | 2020
1900
Ataqqa Power Plant | 2014-12-31 | 37499946 | 2929502.47 | 37499946 | 2929502.47 | 34570443.53 | 184387980.81 | 18.75% |  | 0 | 2014-12-31 | original |  |  | 2014
Ataqqa Power Plant | 2015-01-31 | 0 | 2648622 | 37499946 | 5578124.47 | 31921821.53 | 184387980.81 | 17.31% |  | 15677598 | 2015-01-31 | original |  |  | 2015
Ataqqa Power Plant | 2015-02-28 | 10000000 | 5378106 | 47499946 | 10956230.47 | 36543715.53 | 184387980.81 | 19.82% |  | 9136479.17 | 2015-02-28 | original |  |  | 2015
Ataqqa Power Plant | 2015-03-31 | 20289932 | 7624306 | 67789878 | 18580536.47 | 49209341.53 | 184387980.81 | 26.69% |  | 35246312 | 2015-03-31 | original |  |  | 2015
Ataqqa Power Plant | 2015-04-30 | 21735246 | 12042770 | 89525124 | 30623306.47 | 58901817.53 | 184387980.81 | 31.94% |  | 21847708 | 2015-04-30 | original |  |  | 2015
Ataqqa Power Plant | 2015-05-31 | 4639446 | 13147883 | 94164570 | 43771189.47 | 50393380.53 | 184387980.81 | 27.33% |  | 12001478 | 2015-05-31 | original |  |  | 2015
Ataqqa Power Plant | 2015-06-30 | 4379194 | 8664394 | 98543764 | 52435583.47 | 46108180.53 | 184387980.81 | 25.01% |  | 12051428 | 2015-06-30 | original |  |  | 2015
Ataqqa Power Plant | 2015-07-31 | 11763312 | 3142626 | 110307076 | 55578209.47 | 54728866.53 | 184387980.81 | 29.68% |  | 4881112 | 2015-07-31 | original |  |  | 2015
Ataqqa Power Plant | 2015-08-31 | 3392373 | 5973388 | 113699449 | 61551597.47 | 52147851.53 | 184387980.81 | 28.28% |  | 4564838.26 | 2015-08-31 | original |  |  | 2015
Ataqqa Power Plant | 2015-09-30 | 3304852 | 4958701 | 117004301 | 66510298.47 | 50494002.53 | 184387980.81 | 27.38% |  | 11572731.29 | 2015-09-30 | original |  |  | 2015
Ataqqa Power Plant | 2015-10-31 | 5133030 | 4105409 | 122137331 | 70615707.47 | 51521623.53 | 184387980.81 | 27.94% |  | 9573967.28 | 2015-10-31 | original |  |  | 2015
Ataqqa Power Plant | 2015-11-30 | 8929234 | 3145301 | 131066565 | 73761008.47 | 57305556.53 | 184387980.81 | 31.08% |  | 13069952 | 2015-11-30 | original |  |  | 2015
Ataqqa Power Plant | 2015-12-31 | 4794332 | 3979589 | 135860897 | 77740597.47 | 58120299.53 | 184387980.81 | 31.52% |  | 16665118 | 2015-12-31 | original |  |  | 2015
Ataqqa Power Plant | 2016-01-31 | 8242355 | 3395313 | 144103252 | 81135910.47 | 62967341.53 | 184387980.81 | 34.15% |  | 3185147.22 | 2016-01-31 | original |  |  | 2016
Ataqqa Power Plant | 2016-02-29 | 10640355 | 3334406 | 154743607 | 84470316.47 | 70273290.53 | 184387980.81 | 38.11% |  | 0 | 2016-02-29 | original |  |  | 2016
Ataqqa Power Plant | 2016-03-31 | 10455766 | 3139710 | 165199373 | 87610026.47 | 77589346.53 | 184387980.81 | 42.08% |  | 0 | 2016-03-31 | original |  |  | 2016
Ataqqa Power Plant | 2016-04-30 | 0 | 895818 | 165199373 | 88505844.47 | 76693528.53 | 184387980.81 | 41.59% |  | 0 | 2016-04-30 | original |  |  | 2016
Ataqqa Power Plant | 2016-05-31 | 0 | 534039 | 165199373 | 89039883.47 | 76159489.53 | 184387980.81 | 41.3% |  | 14914113.78 | 2016-05-31 | original |  |  | 2016
Ataqqa Power Plant | 2016-06-30 | 0 | 770631 | 165199373 | 89810514.47 | 75388858.53 | 184387980.81 | 40.89% |  | 0 | 2016-06-30 | original |  |  | 2016
Ataqqa Power Plant | 2016-07-31 | 13000000 | 370048 | 178199373 | 90180562.47 | 88018810.53 | 184387980.81 | 47.74% |  | 0 | 2016-07-31 | original |  |  | 2016
Ataqqa Power Plant | 2016-08-31 | 0 | 176959 | 178199373 | 90357521.47 | 87841851.53 | 184387980.81 | 47.64% |  | 0 | 2016-08-31 | original |  |  | 2016
Ataqqa Power Plant | 2016-09-30 | 0 | 430418 | 178199373 | 90787939.47 | 87411433.53 | 184387980.81 | 47.41% |  | 0 | 2016-09-30 | original |  |  | 2016
Ataqqa Power Plant | 2016-10-31 | 0 | 106569 | 178199373 | 90894508.47 | 87304864.53 | 184387980.81 | 47.35% |  | 0 | 2016-10-31 | original |  |  | 2016
Ataqqa Power Plant | 2016-11-30 | 1357575 | 9308 | 179556948 | 90903816.47 | 88653131.53 | 184387980.81 | 48.08% |  | 0 | 2016-11-30 | original |  |  | 2016
Ataqqa Power Plant | 2016-12-31 | 0 | 150084 | 179556948 | 91053900.47 | 88503047.53 | 184387980.81 | 48% |  | 0 | 2016-12-31 | original |  |  | 2016
Ataqqa Power Plant | 2017-01-31 | 0 | 100000 | 179556948 | 91153900.47 | 88403047.53 | 184387980.81 | 47.94% |  | 0 | 2017-01-31 | original |  |  | 2017
Ataqqa Power Plant | 2017-05-31 | 2092941 | 0 | 181649889 | 91153900.47 | 90495988.53 | 184387980.81 | 49.08% |  | 0 | 2017-05-31 | original |  |  | 2017
Ataqqa Power Plant | 2017-06-30 | 0 | 200000 | 181649889 | 91353900.47 | 90295988.53 | 184387980.81 | 48.97% |  | 0 | 2017-06-30 | original |  |  | 2017
1900
Mall of Egypt Bridge | 2015-04-30 | 0 | 539585 | 0 | 539585 | -539585 | 183459815.63 | -0.2941% |  | 0 | 2015-04-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-05-30 | 0 | 903185 | 0 | 1442770 | -1442770 | 183459815.63 | -0.7864% |  | 10447311 | 2015-05-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-06-30 | 0 | 820538 | 0 | 2263308 | -2263308 | 183459815.63 | -1.234% |  | 5619740 | 2015-06-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-07-30 | 0 | 789689 | 0 | 3052997 | -3052997 | 183459815.63 | -1.664% |  | 5418949 | 2015-07-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-08-30 | 15900000 | 2067448 | 15900000 | 5120445 | 10779555 | 183459815.63 | 5.876% |  | 9016812 | 2015-08-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-09-30 | 0 | 2118947 | 15900000 | 7239392 | 8660608 | 183459815.63 | 4.721% |  | 8800233 | 2015-09-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-10-30 | 0 | 2183916 | 15900000 | 9423308 | 6476692 | 183459815.63 | 3.53% |  | 11846048 | 2015-10-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-11-30 | 0 | 4214337 | 15900000 | 13637645 | 2262355 | 183459815.63 | 1.233% |  | 10532483 | 2015-11-30 | original |  |  | 2015
Mall of Egypt Bridge | 2015-12-30 | 21614153 | 3522202 | 37514153 | 17159847 | 20354306 | 183459815.63 | 11.09% |  | 14019176 | 2015-12-30 | original |  |  | 2015
Mall of Egypt Bridge | 2016-01-30 | 0 | 2457304 | 37514153 | 19617151 | 17897002 | 183459815.63 | 9.755% |  | 4736062 | 2016-01-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-02-29 | 0 | 3486306 | 37514153 | 23103457 | 14410696 | 183459815.63 | 7.855% |  | 11251725 | 2016-02-29 | original |  |  | 2016
Mall of Egypt Bridge | 2016-03-30 | 0 | 2668271 | 37514153 | 25771728 | 11742425 | 183459815.63 | 6.401% |  | 6269405 | 2016-03-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-04-30 | 0 | 3056404 | 37514153 | 28828132 | 8686021 | 183459815.63 | 4.735% |  | 14870800 | 2016-04-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-05-30 | 0 | 8465236 | 37514153 | 37293368 | 220785 | 183459815.63 | 0.1203% |  | 11768625 | 2016-05-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-06-30 | 33853790 | 1971575 | 71367943 | 39264943 | 32103000 | 183459815.63 | 17.5% |  | 4052223 | 2016-06-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-07-30 | 0 | 3308176 | 71367943 | 42573119 | 28794824 | 183459815.63 | 15.7% |  | 19398300 | 2016-07-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-08-30 | 7881790 | 2632295 | 79249733 | 45205414 | 34044319 | 183459815.63 | 18.56% |  | 5308629 | 2016-08-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-09-30 | 0 | 2831552 | 79249733 | 48036966 | 31212767 | 183459815.63 | 17.01% |  | 5605452 | 2016-09-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-10-30 | 0 | 2000950 | 79249733 | 50037916 | 29211817 | 183459815.63 | 15.92% |  | 0 | 2016-10-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-11-30 | 0 | 2189772 | 79249733 | 52227688 | 27022045 | 183459815.63 | 14.73% |  | 1793763 | 2016-11-30 | original |  |  | 2016
Mall of Egypt Bridge | 2016-12-30 | 17612634 | 1129170 | 96862367 | 53356858 | 43505509 | 183459815.63 | 23.71% |  | 0 | 2016-12-30 | original |  |  | 2016
Mall of Egypt Bridge | 2017-01-30 | 0 | 4947601 | 96862367 | 58304459 | 38557908 | 183459815.63 | 21.02% |  | 0 | 2017-01-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-02-28 | 0 | 1274688 | 96862367 | 59579147 | 37283220 | 183459815.63 | 20.32% |  | 0 | 2017-02-28 | original |  |  | 2017
Mall of Egypt Bridge | 2017-03-30 | 0 | 761356 | 96862367 | 60340503 | 36521864 | 183459815.63 | 19.91% |  | 73561 | 2017-03-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-04-30 | 0 | 1284597 | 96862367 | 61625100 | 35237267 | 183459815.63 | 19.21% |  | 0 | 2017-04-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-05-01 |  | 0.55 | 96862367 | 61625100.55 | 35237266.45 | 183459815.63 | 19.21% |  |  |  | cash out both |  |  | 2017
Mall of Egypt Bridge | 2017-05-30 | 0 | 1660338 | 96862367 | 63285438.55 | 33576928.45 | 183459815.63 | 18.3% |  | 0 | 2017-05-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-06-30 | 0 | 19915 | 96862367 | 63305353.55 | 33557013.45 | 183459815.63 | 18.29% |  | 8051960 | 2017-06-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-07-30 | 0 | 1062685 | 96862367 | 64368038.55 | 32494328.45 | 183459815.63 | 17.71% |  | 0 | 2017-07-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-08-01 |  | 1000000 | 96862367 | 65368038.55 | 31494328.45 | 183459815.63 | 17.17% |  |  |  | cash out both |  |  | 2017
Mall of Egypt Bridge | 2017-08-30 | 0 | 1645450 | 96862367 | 67013488.55 | 29848878.45 | 183459815.63 | 16.27% |  | 0 | 2017-08-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-09-30 | 0 | 516401 | 96862367 | 67529889.55 | 29332477.45 | 183459815.63 | 15.99% |  | 0 | 2017-09-30 | original |  |  | 2017
Mall of Egypt Bridge | 2017-12-30 | 0 | 14131 | 96862367 | 67544020.55 | 29318346.45 | 183459815.63 | 15.98% |  | 0 | 2017-12-30 | original |  |  | 2017
Mall of Egypt Bridge | 2018-01-01 |  | 254499.61 | 96862367 | 67798520.16 | 29063846.84 | 183459815.63 | 15.84% |  |  |  | cash out both |  |  | 2018
Mall of Egypt Bridge | 2018-03-01 |  | 219000 | 96862367 | 68017520.16 | 28844846.84 | 183459815.63 | 15.72% |  |  |  | cash out both |  |  | 2018
Mall of Egypt Bridge | 2018-08-01 |  | 215259.09 | 96862367 | 68232779.25 | 28629587.75 | 183459815.63 | 15.61% |  |  |  | cash out both |  |  | 2018
Mall of Egypt Bridge | 2018-09-01 |  | 250000 | 96862367 | 68482779.25 | 28379587.75 | 183459815.63 | 15.47% |  |  |  | cash out both |  |  | 2018
Mall of Egypt Bridge | 2018-10-01 |  | 1230615 | 96862367 | 69713394.25 | 27148972.75 | 183459815.63 | 14.8% |  |  |  | cash out both |  |  | 2018
Mall of Egypt Bridge | 2018-11-01 |  | 58780.04 | 96862367 | 69772174.29 | 27090192.71 | 183459815.63 | 14.77% |  |  |  | cash out both |  |  | 2018
Mall of Egypt Bridge | 2018-12-01 |  | 350000 | 96862367 | 70122174.29 | 26740192.71 | 183459815.63 | 14.58% |  |  |  | cash out both |  |  | 2018
Mall of Egypt Bridge | 2018-12-24 | 237867.55 |  | 97100234.55 | 70122174.29 | 26978060.26 | 183459815.63 | 14.71% |  |  | 2018-12-24 | added cash in 3 |  |  | 2018
Mall of Egypt Bridge | 2018-12-24 | 18908900 |  | 116009134.55 | 70122174.29 | 45886960.26 | 183459815.63 | 25.01% |  |  | 2018-12-24 | added cash in 3 |  |  | 2018
Mall of Egypt Bridge | 2019-01-01 |  | 44500 | 116009134.55 | 70166674.29 | 45842460.26 | 183459815.63 | 24.99% |  |  |  | cash out both |  |  | 2019
Mall of Egypt Bridge | 2019-01-03 | 6039510.3 |  | 122048644.85 | 70166674.29 | 51881970.56 | 183459815.63 | 28.28% |  |  | 2019-01-03 | added cash in 3 |  |  | 2019
Mall of Egypt Bridge | 2019-03-01 |  | 356389 | 122048644.85 | 70523063.29 | 51525581.56 | 183459815.63 | 28.09% |  |  |  | cash out both |  |  | 2019
Mall of Egypt Bridge | 2019-08-01 |  | 27370.3 | 122048644.85 | 70550433.59 | 51498211.26 | 183459815.63 | 28.07% |  |  |  | cash out both |  |  | 2019
Mall of Egypt Bridge | 2019-08-25 | 5574585.6 |  | 127623230.45 | 70550433.59 | 57072796.86 | 183459815.63 | 31.11% |  |  | 2019-08-25 | added cash in 3 |  |  | 2019
Mall of Egypt Bridge | 2019-09-01 |  | 47130 | 127623230.45 | 70597563.59 | 57025666.86 | 183459815.63 | 31.08% |  |  |  | cash out both |  |  | 2019
1900
Marassi Tanks PKG 22 | 2015-04-30 | 0 | 545325 | 0 | 545325 | -545325 | 18438370 | -2.958% |  | 361243 | 2015-04-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-05-30 | 0 | 338808 | 0 | 884133 | -884133 | 18438370 | -4.795% |  | 1255716 | 2015-05-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-06-30 | 0 | 787544 | 0 | 1671677 | -1671677 | 18438370 | -9.066% |  | 1197476 | 2015-06-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-07-30 | 313398 | 970980 | 313398 | 2642657 | -2329259 | 18438370 | -12.63% |  | 733802 | 2015-07-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-08-30 | 1124042 | 2050996 | 1437440 | 4693653 | -3256213 | 18438370 | -17.66% |  | 2176660 | 2015-08-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-09-30 | 1721144 | 1237752 | 3158584 | 5931405 | -2772821 | 18438370 | -15.04% |  | 165696 | 2015-09-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-10-30 | 3075432 | 621081 | 6234016 | 6552486 | -318470 | 18438370 | -1.727% |  | 2449389 | 2015-10-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-11-30 | 51999 | 971120 | 6286015 | 7523606 | -1237591 | 18438370 | -6.712% |  | 0 | 2015-11-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2015-12-30 | 1983258 | 1166958 | 8269273 | 8690564 | -421291 | 18438370 | -2.285% |  | 882673 | 2015-12-30 | original |  |  | 2015
Marassi Tanks PKG 22 | 2016-01-30 | 0 | 722559 | 8269273 | 9413123 | -1143850 | 18438370 | -6.204% |  | 116975 | 2016-01-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-02-29 | 728974 | 824337 | 8998247 | 10237460 | -1239213 | 18438370 | -6.721% |  | 805479 | 2016-02-29 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-03-30 | 306588 | 1059766 | 9304835 | 11297226 | -1992391 | 18438370 | -10.81% |  | 0 | 2016-03-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-04-30 | 1205323 | 465410 | 10510158 | 11762636 | -1252478 | 18438370 | -6.793% |  | 1383216 | 2016-04-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-05-30 | 136297 | 743758 | 10646455 | 12506394 | -1859939 | 18438370 | -10.09% |  | 951643 | 2016-05-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-06-30 | 1080850 | 1726525 | 11727305 | 14232919 | -2505614 | 18438370 | -13.59% |  | 0 | 2016-06-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-07-30 | 763400 | 309096 | 12490705 | 14542015 | -2051310 | 18438370 | -11.13% |  | 1762191 | 2016-07-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-08-30 | 0 | 635340 | 12490705 | 15177355 | -2686650 | 18438370 | -14.57% |  | 0 | 2016-08-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-09-30 | 1345167 | 431331 | 13835872 | 15608686 | -1772814 | 18438370 | -9.615% |  | 540236 | 2016-09-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-10-30 | 337754 | 181696 | 14173626 | 15790382 | -1616756 | 18438370 | -8.768% |  | 0 | 2016-10-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-11-30 | 639374 | 303192 | 14813000 | 16093574 | -1280574 | 18438370 | -6.945% |  | 0 | 2016-11-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2016-12-30 | 0 | 260192 | 14813000 | 16353766 | -1540766 | 18438370 | -8.356% |  | 0 | 2016-12-30 | original |  |  | 2016
Marassi Tanks PKG 22 | 2017-01-30 | 0 | 212226 | 14813000 | 16565992 | -1752992 | 18438370 | -9.507% |  | 2574334 | 2017-01-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-02-28 | 0 | 52219 | 14813000 | 16618211 | -1805211 | 18438370 | -9.791% |  | 0 | 2017-02-28 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-03-30 | 2381296 | 154004 | 17194296 | 16772215 | 422081 | 18438370 | 2.289% |  | 154991 | 2017-03-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-04-30 | 0 | 34882 | 17194296 | 16807097 | 387199 | 18438370 | 2.1% |  | 0 | 2017-04-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-05-30 | 185149 | 0 | 17379445 | 16807097 | 572348 | 18438370 | 3.104% |  | 0 | 2017-05-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-05-31 | 185149.13 |  | 17564594.13 | 16807097 | 757497.13 | 18438370 | 4.108% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
Marassi Tanks PKG 22 | 2017-06-30 | 0 | 29782 | 17564594.13 | 16836879 | 727715.13 | 18438370 | 3.947% |  | 0 | 2017-06-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-07-30 | 0 | 159247 | 17564594.13 | 16996126 | 568468.13 | 18438370 | 3.083% |  | 0 | 2017-07-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-09-30 | 0 | 24109 | 17564594.13 | 17020235 | 544359.13 | 18438370 | 2.952% |  | 0 | 2017-09-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2017-11-30 | 0 | 6049 | 17564594.13 | 17026284 | 538310.13 | 18438370 | 2.92% |  | 0 | 2017-11-30 | original |  |  | 2017
Marassi Tanks PKG 22 | 2018-02-01 |  | 28162.19 | 17564594.13 | 17054446.19 | 510147.94 | 18438370 | 2.767% |  |  |  | cash out both |  |  | 2018
Marassi Tanks PKG 22 | 2018-03-01 |  | 28162.19 | 17564594.13 | 17082608.38 | 481985.75 | 18438370 | 2.614% |  |  |  | cash out both |  |  | 2018
Marassi Tanks PKG 22 | 2018-04-01 |  | 11951.55 | 17564594.13 | 17094559.93 | 470034.2 | 18438370 | 2.549% |  |  |  | cash out both |  |  | 2018
Marassi Tanks PKG 22 | 2018-09-01 |  | 2819.12 | 17564594.13 | 17097379.05 | 467215.08 | 18438370 | 2.534% |  |  |  | cash out both |  |  | 2018
Marassi Tanks PKG 22 | 2018-11-01 |  | 4373.46 | 17564594.13 | 17101752.51 | 462841.62 | 18438370 | 2.51% |  |  |  | cash out both |  |  | 2018
Marassi Tanks PKG 22 | 2018-12-01 |  | 47605.57 | 17564594.13 | 17149358.08 | 415236.05 | 18438370 | 2.252% |  |  |  | cash out both |  |  | 2018
Marassi Tanks PKG 22 | 2019-02-01 |  | 191530 | 17564594.13 | 17340888.08 | 223706.05 | 18438370 | 1.213% |  |  |  | cash out both |  |  | 2019
Marassi Tanks PKG 22 | 2019-03-01 |  | 174727.57 | 17564594.13 | 17515615.65 | 48978.48 | 18438370 | 0.2656% |  |  |  | cash out both |  |  | 2019
Marassi Tanks PKG 22 | 2019-04-09 | 263550.07 |  | 17828144.2 | 17515615.65 | 312528.55 | 18438370 | 1.695% |  |  | 2019-04-09 | added cash in 3 |  |  | 2019
Marassi Tanks PKG 22 | 2019-05-01 |  | 16815 | 17828144.2 | 17532430.65 | 295713.55 | 18438370 | 1.604% |  |  |  | cash out both |  |  | 2019
Marassi Tanks PKG 22 | 2019-08-01 |  | 5244.55 | 17828144.2 | 17537675.2 | 290469 | 18438370 | 1.575% |  |  |  | cash out both |  |  | 2019
Marassi Tanks PKG 22 | 2019-10-01 |  | 17930 | 17828144.2 | 17555605.2 | 272539 | 18438370 | 1.478% |  |  |  | cash out both |  |  | 2019
Marassi Tanks PKG 22 | 2019-11-01 |  | 9642.98 | 17828144.2 | 17565248.18 | 262896.02 | 18438370 | 1.426% |  |  |  | cash out both |  |  | 2019
Marassi Tanks PKG 22 | 2019-12-01 |  | 3649.67 | 17828144.2 | 17568897.85 | 259246.35 | 18438370 | 1.406% |  |  |  | cash out both |  |  | 2019
Marassi Tanks PKG 22 | 2020-01-01 |  | 2374.06 | 17828144.2 | 17571271.91 | 256872.29 | 18438370 | 1.393% |  |  |  | cash out both |  |  | 2020
Marassi Tanks PKG 22 | 2020-02-01 |  | 27938.68 | 17828144.2 | 17599210.59 | 228933.61 | 18438370 | 1.242% |  |  |  | cash out both |  |  | 2020
Marassi Tanks PKG 22 | 2020-06-01 |  | 52377.98 | 17828144.2 | 17651588.57 | 176555.63 | 18438370 | 0.9575% |  |  |  | cash out both |  |  | 2020
Marassi Tanks PKG 22 | 2020-08-01 |  | 5374.25 | 17828144.2 | 17656962.82 | 171181.38 | 18438370 | 0.9284% |  |  |  | cash out both |  |  | 2020
Marassi Tanks PKG 22 | 2020-09-01 |  | 50115 | 17828144.2 | 17707077.82 | 121066.38 | 18438370 | 0.6566% |  |  |  | cash out both |  |  | 2020
Marassi Tanks PKG 22 | 2020-10-15 | 780036 |  | 18608180.2 | 17707077.82 | 901102.38 | 18438370 | 4.887% |  |  | 2020-10-15 | added cash in 3 |  |  | 2020
1900
Sodic Club House | 2015-03-31 | 7040000 | 118690 | 7040000 | 118690 | 6921310 | 161208266 | 4.293% |  | 0 | 2015-03-31 | original |  |  | 2015
Sodic Club House | 2015-04-30 | 0 | 128500 | 7040000 | 247190 | 6792810 | 161208266 | 4.214% |  | 0 | 2015-04-30 | original |  |  | 2015
Sodic Club House | 2015-05-31 | 0 | 661534 | 7040000 | 908724 | 6131276 | 161208266 | 3.803% |  | 0 | 2015-05-31 | original |  |  | 2015
Sodic Club House | 2015-06-30 | 0 | 1086471 | 7040000 | 1995195 | 5044805 | 161208266 | 3.129% |  | 0 | 2015-06-30 | original |  |  | 2015
Sodic Club House | 2015-07-31 | 430664 | 1083495 | 7470664 | 3078690 | 4391974 | 161208266 | 2.724% |  | 0 | 2015-07-31 | original |  | 42216 | 2015
Sodic Club House | 2015-08-31 | 885707 | 558470 | 8356371 | 3637160 | 4719211 | 161208266 | 2.927% |  | 0 | 2015-08-31 | original |  | 42247 | 2015
Sodic Club House | 2015-09-30 | 0 | 969675 | 8356371 | 4606835 | 3749536 | 161208266 | 2.326% |  | 0 | 2015-09-30 | original |  | 42277 | 2015
Sodic Club House | 2015-10-31 | 744842 | 1235888 | 9101213 | 5842723 | 3258490 | 161208266 | 2.021% |  | 124721 | 2015-10-31 | original |  | 167029 | 2015
Sodic Club House | 2015-11-30 | 0 | 982250 | 9101213 | 6824973 | 2276240 | 161208266 | 1.412% |  | 32630 | 2015-11-30 | original |  | 74968 | 2015
Sodic Club House | 2015-12-31 | 994182 | 1839023 | 10095395 | 8663996 | 1431399 | 161208266 | 0.8879% |  | 217578 | 2015-12-31 | original |  | 259947 | 2015
Sodic Club House | 2016-01-31 | 899985 | 2311600 | 10995380 | 10975596 | 19784 | 161208266 | 0.01227% |  | 81525 | 2016-01-31 | original |  | 123925 | 2016
Sodic Club House | 2016-02-29 | 1857883 | 1907743 | 12853263 | 12883339 | -30076 | 161208266 | -0.01866% |  | 144258 | 2016-02-29 | original |  | 186687 | 2016
Sodic Club House | 2016-03-31 | 1279246 | 2454209 | 14132509 | 15337548 | -1205039 | 161208266 | -0.7475% |  | 173765 | 2016-03-31 | original |  | 216225 | 2016
Sodic Club House | 2016-04-30 | 1306190 | 3031677 | 15438699 | 18369225 | -2930526 | 161208266 | -1.818% |  | 166648 | 2016-04-30 | original |  | 209138 | 2016
Sodic Club House | 2016-05-31 | 1486761 | 1609642 | 16925460 | 19978867 | -3053407 | 161208266 | -1.894% |  | 623524 | 2016-05-31 | original |  | 666045 | 2016
Sodic Club House | 2016-06-30 | 2355243 | 1191143 | 19280703 | 21170010 | -1889307 | 161208266 | -1.172% |  | -8211 | 2016-06-30 | original |  | 34340 | 2016
Sodic Club House | 2016-07-31 | 1154879 | 446976 | 20435582 | 21616986 | -1181404 | 161208266 | -0.7328% |  | 0 | 2016-07-31 | original |  | 42582 | 2016
Sodic Club House | 2016-08-31 | 0 | 1129430 | 20435582 | 22746416 | -2310834 | 161208266 | -1.433% |  | 0 | 2016-08-31 | original |  | 42613 | 2016
Sodic Club House | 2016-09-30 | 1974894 | 1100158 | 22410476 | 23846574 | -1436098 | 161208266 | -0.8908% |  | 270130 | 2016-09-30 | original |  | 312773 | 2016
Sodic Club House | 2016-10-31 | 2811471 | 2236647 | 25221947 | 26083221 | -861274 | 161208266 | -0.5343% |  | 2680029 | 2016-10-31 | original |  | 2722703 | 2016
Sodic Club House | 2016-11-30 | 10093966 | 2751284 | 35315913 | 28834505 | 6481408 | 161208266 | 4.021% |  | 1271140 | 2016-11-30 | original |  | 1313844 | 2016
Sodic Club House | 2016-12-31 | 1831900 | 838576 | 37147813 | 29673081 | 7474732 | 161208266 | 4.637% |  | 221840 | 2016-12-31 | original |  | 264575 | 2016
Sodic Club House | 2017-01-31 | 0 | 2393940 | 37147813 | 32067021 | 5080792 | 161208266 | 3.152% |  | 2824041.38 | 2017-01-31 | original |  | 2866807.38 | 2017
Sodic Club House | 2017-02-28 | 3047963 | 2559491 | 40195776 | 34626512 | 5569264 | 161208266 | 3.455% |  | 3485234.55 | 2017-02-28 | original |  | 3528028.55 | 2017
Sodic Club House | 2017-03-31 | 1525588 | 4738924 | 41721364 | 39365436 | 2355928 | 161208266 | 1.461% |  | 3307426.13 | 2017-03-31 | original |  | 3350251.13 | 2017
Sodic Club House | 2017-04-01 |  | 290359.99 | 41721364 | 39655795.99 | 2065568.01 | 161208266 | 1.281% |  |  |  | cash out both |  | 0 | 2017
Sodic Club House | 2017-04-30 | 2166353 | 2495212 | 43887717 | 42151007.99 | 1736709.01 | 161208266 | 1.077% |  | 3742413.63 | 2017-04-30 | original |  | 3785268.63 | 2017
Sodic Club House | 2017-05-01 |  | 773437.26 | 43887717 | 42924445.25 | 963271.75 | 161208266 | 0.5975% |  |  |  | cash out both |  | 0 | 2017
Sodic Club House | 2017-05-31 | 0 | 2251328 | 43887717 | 45175773.25 | -1288056.25 | 161208266 | -0.799% |  | 0 | 2017-05-31 | original |  | 42886 | 2017
Sodic Club House | 2017-06-01 |  | 1400643.19 | 43887717 | 46576416.44 | -2688699.44 | 161208266 | -1.668% |  |  |  | cash out both |  | 0 | 2017
Sodic Club House | 2017-06-30 | 2058984 | 2604749 | 45946701 | 49181165.44 | -3234464.44 | 161208266 | -2.006% |  | 4524968.41 | 2017-06-30 | original |  | 4567884.41 | 2017
Sodic Club House | 2017-07-01 |  | 2118948.21 | 45946701 | 51300113.65 | -5353412.65 | 161208266 | -3.321% |  |  |  | cash out both |  | 0 | 2017
Sodic Club House | 2017-07-31 | 4816361 | 3214661 | 50763062 | 54514774.65 | -3751712.65 | 161208266 | -2.327% |  | 2035095.79 | 2017-07-31 | original |  | 2078042.79 | 2017
Sodic Club House | 2017-08-01 |  | 5280401.56 | 50763062 | 59795176.21 | -9032114.21 | 161208266 | -5.603% |  |  |  | cash out both |  | 0 | 2017
Sodic Club House | 2017-08-31 | 6522784 | 4824691 | 57285846 | 64619867.21 | -7334021.21 | 161208266 | -4.549% |  | 0 | 2017-08-31 | original |  | 42978 | 2017
Sodic Club House | 2017-09-01 |  | 544491.92 | 57285846 | 65164359.13 | -7878513.13 | 161208266 | -4.887% |  |  |  | cash out both |  |  | 2017
Sodic Club House | 2017-09-30 | 0 | 1459744 | 57285846 | 66624103.13 | -9338257.13 | 161208266 | -5.793% |  | 695689.48 | 2017-09-30 | original |  |  | 2017
Sodic Club House | 2017-10-01 |  | 4244741.83 | 57285846 | 70868844.96 | -13582998.96 | 161208266 | -8.426% |  |  |  | cash out both |  |  | 2017
Sodic Club House | 2017-10-31 | 1701896 | 2412658 | 58987742 | 73281502.96 | -14293760.96 | 161208266 | -8.867% |  | 5326663.54 | 2017-10-31 | original |  |  | 2017
Sodic Club House | 2017-11-01 |  | 1435317.95 | 58987742 | 74716820.91 | -15729078.91 | 161208266 | -9.757% |  |  |  | cash out both |  |  | 2017
Sodic Club House | 2017-11-30 | 2727407 | 3568103 | 61715149 | 78284923.91 | -16569774.91 | 161208266 | -10.28% |  | 6710848.7 | 2017-11-30 | original |  |  | 2017
Sodic Club House | 2017-12-01 |  | 754030.96 | 61715149 | 79038954.87 | -17323805.87 | 161208266 | -10.75% |  |  |  | cash out both |  |  | 2017
Sodic Club House | 2017-12-31 | 0 | 1902118 | 61715149 | 80941072.87 | -19225923.87 | 161208266 | -11.93% |  | 6289400.69 | 2017-12-31 | original |  |  | 2017
Sodic Club House | 2018-01-01 |  | 5253101.51 | 61715149 | 86194174.38 | -24479025.38 | 161208266 | -15.18% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-01-02 | 4528572.66 |  | 66243721.66 | 86194174.38 | -19950452.72 | 161208266 | -12.38% |  |  | 2018-01-02 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-01-21 | 75783.54 |  | 66319505.2 | 86194174.38 | -19874669.18 | 161208266 | -12.33% |  |  | 2018-01-21 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-01-21 | 713547.9 |  | 67033053.1 | 86194174.38 | -19161121.28 | 161208266 | -11.89% |  |  | 2018-01-21 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-01-21 | 14753.19 |  | 67047806.29 | 86194174.38 | -19146368.09 | 161208266 | -11.88% |  |  | 2018-01-21 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-01-30 | 894280.83 |  | 67942087.12 | 86194174.38 | -18252087.26 | 161208266 | -11.32% |  |  | 2018-01-30 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-02-01 |  | 2109288.34 | 67942087.12 | 88303462.72 | -20361375.6 | 161208266 | -12.63% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-02-27 | 2563543.65 |  | 70505630.77 | 88303462.72 | -17797831.95 | 161208266 | -11.04% |  |  | 2018-02-27 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-02-27 | 157325.68 |  | 70662956.45 | 88303462.72 | -17640506.27 | 161208266 | -10.94% |  |  | 2018-02-27 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-03-01 |  | 4757625.49 | 70662956.45 | 93061088.21 | -22398131.76 | 161208266 | -13.89% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-03-29 | 7171420.81 |  | 77834377.26 | 93061088.21 | -15226710.95 | 161208266 | -9.445% |  |  | 2018-03-29 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-04-01 |  | 3698643.72 | 77834377.26 | 96759731.93 | -18925354.67 | 161208266 | -11.74% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-04-12 | 174364.8 |  | 78008742.06 | 96759731.93 | -18750989.87 | 161208266 | -11.63% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-04-12 | 3171197.25 |  | 81179939.31 | 96759731.93 | -15579792.62 | 161208266 | -9.664% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-05-01 |  | 5567895.44 | 81179939.31 | 102327627.37 | -21147688.06 | 161208266 | -13.12% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-05-08 | 3643251.2 |  | 84823190.51 | 102327627.37 | -17504436.86 | 161208266 | -10.86% |  |  | 2018-05-08 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-05-21 | 2500000 |  | 87323190.51 | 102327627.37 | -15004436.86 | 161208266 | -9.307% |  |  | 2018-05-21 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-05-31 | 115101.74 |  | 87438292.25 | 102327627.37 | -14889335.12 | 161208266 | -9.236% |  |  | 2018-05-31 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-05-31 | 98174.35 |  | 87536466.6 | 102327627.37 | -14791160.77 | 161208266 | -9.175% |  |  | 2018-05-31 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-05-31 | 2927170.54 |  | 90463637.14 | 102327627.37 | -11863990.23 | 161208266 | -7.359% |  |  | 2018-05-31 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-06-01 |  | 3238710.01 | 90463637.14 | 105566337.38 | -15102700.24 | 161208266 | -9.368% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-06-13 | 2500000 |  | 92963637.14 | 105566337.38 | -12602700.24 | 161208266 | -7.818% |  |  | 2018-06-13 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-07-01 |  | 5182157.23 | 92963637.14 | 110748494.61 | -17784857.47 | 161208266 | -11.03% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-07-09 | 1523667.33 |  | 94487304.47 | 110748494.61 | -16261190.14 | 161208266 | -10.09% |  |  | 2018-07-09 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-07-09 | 175190.11 |  | 94662494.58 | 110748494.61 | -16086000.03 | 161208266 | -9.978% |  |  | 2018-07-09 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-08-01 |  | 6955137.08 | 94662494.58 | 117703631.69 | -23041137.11 | 161208266 | -14.29% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-08-14 | 1052933.22 |  | 95715427.8 | 117703631.69 | -21988203.89 | 161208266 | -13.64% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-08-14 | 87359.86 |  | 95802787.66 | 117703631.69 | -21900844.03 | 161208266 | -13.59% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-08-14 | 700000 |  | 96502787.66 | 117703631.69 | -21200844.03 | 161208266 | -13.15% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-08-14 | 2000000 |  | 98502787.66 | 117703631.69 | -19200844.03 | 161208266 | -11.91% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-08-19 | 3000000 |  | 101502787.66 | 117703631.69 | -16200844.03 | 161208266 | -10.05% |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-09-01 |  | 4409524.21 | 101502787.66 | 122113155.9 | -20610368.24 | 161208266 | -12.78% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-09-12 | 1851323.25 |  | 103354110.91 | 122113155.9 | -18759044.99 | 161208266 | -11.64% |  |  | 2018-09-12 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-09-23 | 4000000 |  | 107354110.91 | 122113155.9 | -14759044.99 | 161208266 | -9.155% |  |  | 2018-09-23 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-10-01 |  | 4745348.72 | 107354110.91 | 126858504.62 | -19504393.71 | 161208266 | -12.1% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-10-18 | 1028067.13 |  | 108382178.04 | 126858504.62 | -18476326.58 | 161208266 | -11.46% |  |  | 2018-10-18 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-10-30 | 4000000 |  | 112382178.04 | 126858504.62 | -14476326.58 | 161208266 | -8.98% |  |  | 2018-10-30 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-11-01 |  | 3994534.59 | 112382178.04 | 130853039.21 | -18470861.17 | 161208266 | -11.46% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-12-01 |  | 2770057.02 | 112382178.04 | 133623096.23 | -21240918.19 | 161208266 | -13.18% |  |  |  | cash out both |  |  | 2018
Sodic Club House | 2018-12-13 | 642206.29 |  | 113024384.33 | 133623096.23 | -20598711.9 | 161208266 | -12.78% |  |  | 2018-12-13 | added cash in 3 |  |  | 2018
Sodic Club House | 2018-12-13 | 1372787.16 |  | 114397171.49 | 133623096.23 | -19225924.74 | 161208266 | -11.93% |  |  | 2018-12-13 | added cash in 3 |  |  | 2018
Sodic Club House | 2019-01-01 |  | 1463200.06 | 114397171.49 | 135086296.29 | -20689124.8 | 161208266 | -12.83% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-01-15 | 2061960.6 |  | 116459132.09 | 135086296.29 | -18627164.2 | 161208266 | -11.55% |  |  | 2019-01-15 | added cash in 3 |  |  | 2019
Sodic Club House | 2019-02-01 |  | 1257798.19 | 116459132.09 | 136344094.48 | -19884962.39 | 161208266 | -12.33% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-03-01 |  | 815360.64 | 116459132.09 | 137159455.12 | -20700323.03 | 161208266 | -12.84% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-04-01 |  | 308528.78 | 116459132.09 | 137467983.9 | -21008851.81 | 161208266 | -13.03% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-04-11 | 184729.32 |  | 116643861.41 | 137467983.9 | -20824122.49 | 161208266 | -12.92% |  |  | 2019-04-11 | added cash in 3 |  |  | 2019
Sodic Club House | 2019-05-01 |  | 1033679.11 | 116643861.41 | 138501663.01 | -21857801.6 | 161208266 | -13.56% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-06-01 |  | 1013827.03 | 116643861.41 | 139515490.04 | -22871628.63 | 161208266 | -14.19% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-07-01 |  | 37446.68 | 116643861.41 | 139552936.72 | -22909075.31 | 161208266 | -14.21% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-07-09 | 503082.9 |  | 117146944.31 | 139552936.72 | -22405992.41 | 161208266 | -13.9% |  |  | 2019-07-09 | added cash in 3 |  |  | 2019
Sodic Club House | 2019-08-01 |  | 113794.73 | 117146944.31 | 139666731.45 | -22519787.14 | 161208266 | -13.97% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-08-25 | 3000000 |  | 120146944.31 | 139666731.45 | -19519787.14 | 161208266 | -12.11% |  |  | 2019-08-25 | added cash in 3 |  |  | 2019
Sodic Club House | 2019-09-01 |  | 92884.94 | 120146944.31 | 139759616.39 | -19612672.08 | 161208266 | -12.17% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-10-01 |  | 72952.1 | 120146944.31 | 139832568.49 | -19685624.18 | 161208266 | -12.21% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-11-01 |  | 540672.67 | 120146944.31 | 140373241.16 | -20226296.85 | 161208266 | -12.55% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2019-11-27 | 13881.35 |  | 120160825.66 | 140373241.16 | -20212415.5 | 161208266 | -12.54% |  |  | 2019-11-27 | added cash in 3 |  |  | 2019
Sodic Club House | 2019-12-01 |  | 129924.07 | 120160825.66 | 140503165.23 | -20342339.57 | 161208266 | -12.62% |  |  |  | cash out both |  |  | 2019
Sodic Club House | 2020-01-01 |  | 129100 | 120160825.66 | 140632265.23 | -20471439.57 | 161208266 | -12.7% |  |  |  | cash out both |  |  | 2020
Sodic Club House | 2020-01-16 | 6516540.66 |  | 126677366.32 | 140632265.23 | -13954898.91 | 161208266 | -8.656% |  |  | 2020-01-16 | added 1 |  |  | 2020
Sodic Club House | 2020-02-01 |  | 297059.98 | 126677366.32 | 140929325.21 | -14251958.89 | 161208266 | -8.841% |  |  |  | cash out both |  |  | 2020
Sodic Club House | 2020-03-01 |  | 446120.81 | 126677366.32 | 141375446.02 | -14698079.7 | 161208266 | -9.117% |  |  |  | cash out both |  |  | 2020
Sodic Club House | 2020-05-01 |  | 93809.92 | 126677366.32 | 141469255.94 | -14791889.62 | 161208266 | -9.176% |  |  |  | cash out both |  |  | 2020
Sodic Club House | 2020-06-01 |  | 128602.89 | 126677366.32 | 141597858.83 | -14920492.51 | 161208266 | -9.255% |  |  |  | cash out both |  |  | 2020
Sodic Club House | 2020-08-01 |  | 31157.79 | 126677366.32 | 141629016.62 | -14951650.3 | 161208266 | -9.275% |  |  |  | cash out both |  |  | 2020
Sodic Club House | 2020-09-01 |  | 15085.89 | 126677366.32 | 141644102.51 | -14966736.19 | 161208266 | -9.284% |  |  |  | cash out both |  |  | 2020
Sodic Club House | 2020-10-01 |  | 228666.92 | 126677366.32 | 141872769.43 | -15195403.11 | 161208266 | -9.426% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Sodic Club House | 2020-12-01 |  | 38783 | 126677366.32 | 141911552.43 | -15234186.11 | 161208266 | -9.45% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Sodic Club House | 2021-02-01 |  | 58033.38 | 126677366.32 | 141969585.81 | -15292219.49 | 161208266 | -9.486% |  |  |  | cash out both |  |  | 2021
Sodic Club House | 2021-03-01 |  | 759855 | 126677366.32 | 142729440.81 | -16052074.49 | 161208266 | -9.957% |  |  |  | cash out both |  |  | 2021
Sodic Club House | 2021-03-22 | 4028521 |  | 130705887.32 | 142729440.81 | -12023553.49 | 161208266 | -7.458% |  |  | 2021-03-22 | added 1 |  |  | 2021
1900
Uptown Cairo Pkg 53 | 2015-05-30 | 22197572 | 276275 | 22197572 | 276275 | 21921297 | 314789511 | 6.964% |  | 0 | 2015-05-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2015-06-30 | 0 | 2218396 | 22197572 | 2494671 | 19702901 | 314789511 | 6.259% |  | 3375819 | 2015-06-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2015-07-30 | 0 | 2378353 | 22197572 | 4873024 | 17324548 | 314789511 | 5.504% |  | 4871804 | 2015-07-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2015-08-30 | 25331090 | 4001637 | 47528662 | 8874661 | 38654001 | 314789511 | 12.28% |  | 6620592 | 2015-08-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2015-09-30 | 0 | 6707634 | 47528662 | 15582295 | 31946367 | 314789511 | 10.15% |  | 4530736 | 2015-09-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2015-10-30 | 8388503 | 4386195 | 55917165 | 19968490 | 35948675 | 314789511 | 11.42% |  | 5368329 | 2015-10-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2015-11-30 | 3640804 | 8552396 | 59557969 | 28520886 | 31037083 | 314789511 | 9.86% |  | 10007597 | 2015-11-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2015-12-30 | 5140038 | 8467010 | 64698007 | 36987896 | 27710111 | 314789511 | 8.803% |  | 10287159 | 2015-12-30 | original |  |  | 2015
Uptown Cairo Pkg 53 | 2016-01-30 | 7685729 | 6938553 | 72383736 | 43926449 | 28457287 | 314789511 | 9.04% |  | 6087611 | 2016-01-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-02-29 | 6538575 | 7370547 | 78922311 | 51296996 | 27625315 | 314789511 | 8.776% |  | 10052757 | 2016-02-29 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-03-30 | 4182770 | 7281299 | 83105081 | 58578295 | 24526786 | 314789511 | 7.791% |  | 9825883 | 2016-03-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-04-30 | 7197655 | 8362049 | 90302736 | 66940344 | 23362392 | 314789511 | 7.422% |  | 6233880 | 2016-04-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-05-30 | 6336694 | 10614378 | 96639430 | 77554722 | 19084708 | 314789511 | 6.063% |  | 4861241 | 2016-05-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-06-30 | 4180361 | 6877557 | 100819791 | 84432279 | 16387512 | 314789511 | 5.206% |  | 3544720 | 2016-06-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-07-30 | 3615040 | 6844122 | 104434831 | 91276401 | 13158430 | 314789511 | 4.18% |  | 7057268 | 2016-07-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-08-30 | 2686256 | 5078227 | 107121087 | 96354628 | 10766459 | 314789511 | 3.42% |  | 6452626 | 2016-08-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-09-30 | 5342829 | 7908797 | 112463916 | 104263425 | 8200491 | 314789511 | 2.605% |  | 6612101 | 2016-09-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-10-30 | 4862346 | 8301340 | 117326262 | 112564765 | 4761497 | 314789511 | 1.513% |  | 0 | 2016-10-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-11-30 | 6054470 | 10177650 | 123380732 | 122742415 | 638317 | 314789511 | 0.2028% |  | 9641488 | 2016-11-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2016-12-30 | 5000000 | 13116531 | 128380732 | 135858946 | -7478214 | 314789511 | -2.376% |  | 8205250 | 2016-12-30 | original |  |  | 2016
Uptown Cairo Pkg 53 | 2017-01-30 | 8210499 | 14864652 | 136591231 | 150723598 | -14132367 | 314789511 | -4.489% |  | 0 | 2017-01-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-02-28 | 0 | 9233896 | 136591231 | 159957494 | -23366263 | 314789511 | -7.423% |  | 5860433 | 2017-02-28 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-03-30 | 8397446 | 8153089 | 144988677 | 168110583 | -23121906 | 314789511 | -7.345% |  | 13097397 | 2017-03-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-03-30 | 29729371.66 |  | 174718048.66 | 168110583 | 6607465.66 | 314789511 | 2.099% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-04-01 |  | 3465234.44 | 174718048.66 | 171575817.44 | 3142231.22 | 314789511 | 0.9982% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-04-01 | 8268748.21 |  | 182986796.87 | 171575817.44 | 11410979.43 | 314789511 | 3.625% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-04-30 | 8268748 | 13296054 | 191255544.87 | 184871871.44 | 6383673.43 | 314789511 | 2.028% |  | 0 | 2017-04-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-05-01 |  | 2118291.03 | 191255544.87 | 186990162.47 | 4265382.4 | 314789511 | 1.355% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-05-30 | 0 | 8468085 | 191255544.87 | 195458247.47 | -4202702.6 | 314789511 | -1.335% |  | 15107064 | 2017-05-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-06-01 |  | 3488731.35 | 191255544.87 | 198946978.82 | -7691433.95 | 314789511 | -2.443% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-06-30 | 10580125 | 11774180 | 201835669.87 | 210721158.82 | -8885488.95 | 314789511 | -2.823% |  | 7401541 | 2017-06-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-06-30 | 8693366.11 |  | 210529035.98 | 210721158.82 | -192122.84 | 314789511 | -0.06103% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-06-30 | 1886758.4 |  | 212415794.38 | 210721158.82 | 1694635.56 | 314789511 | 0.5383% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-07-01 |  | 1598385.6 | 212415794.38 | 212319544.42 | 96249.96 | 314789511 | 0.03058% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-07-30 | 5375403 | 8656661 | 217791197.38 | 220976205.42 | -3185008.04 | 314789511 | -1.012% |  | 16155110 | 2017-07-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-07-31 | 5375402.82 |  | 223166600.2 | 220976205.42 | 2190394.78 | 314789511 | 0.6958% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-08-01 |  | 4936393.68 | 223166600.2 | 225912599.1 | -2745998.9 | 314789511 | -0.8723% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-08-30 | 9068282 | 12944671 | 232234882.2 | 238857270.1 | -6622387.9 | 314789511 | -2.104% |  | 10877624 | 2017-08-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-08-31 | 5530292.87 |  | 237765175.07 | 238857270.1 | -1092095.03 | 314789511 | -0.3469% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-08-31 | 1706138.77 |  | 239471313.84 | 238857270.1 | 614043.74 | 314789511 | 0.1951% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-08-31 | 1831850.29 |  | 241303164.13 | 238857270.1 | 2445894.03 | 314789511 | 0.777% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Uptown Cairo Pkg 53 | 2017-09-01 |  | 1648195.05 | 241303164.13 | 240505465.15 | 797698.98 | 314789511 | 0.2534% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-09-30 | 0 | 4594734 | 241303164.13 | 245100199.15 | -3797035.02 | 314789511 | -1.206% |  | 18032647 | 2017-09-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-10-01 |  | 6593283.85 | 241303164.13 | 251693483 | -10390318.87 | 314789511 | -3.301% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-10-30 | 15631210 | 12543584 | 256934374.13 | 264237067 | -7302692.87 | 314789511 | -2.32% |  | 18646794 | 2017-10-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-11-01 |  | 4946297.34 | 256934374.13 | 269183364.34 | -12248990.21 | 314789511 | -3.891% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-11-30 | 20089288 | 8835476 | 277023662.13 | 278018840.34 | -995178.21 | 314789511 | -0.3161% |  | 11525428 | 2017-11-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2017-12-01 |  | 4994530.67 | 277023662.13 | 283013371.01 | -5989708.88 | 314789511 | -1.903% |  |  |  | cash out both |  |  | 2017
Uptown Cairo Pkg 53 | 2017-12-30 | 0 | 10179893 | 277023662.13 | 293193264.01 | -16169601.88 | 314789511 | -5.137% |  | 13381664 | 2017-12-30 | original |  |  | 2017
Uptown Cairo Pkg 53 | 2018-01-01 |  | 10353800.46 | 277023662.13 | 303547064.47 | -26523402.34 | 314789511 | -8.426% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-01-09 | 13124888.11 |  | 290148550.24 | 303547064.47 | -13398514.23 | 314789511 | -4.256% |  |  | 2018-01-09 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-01-11 | 1984358.38 |  | 292132908.62 | 303547064.47 | -11414155.85 | 314789511 | -3.626% |  |  | 2018-01-11 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-01-30 | 9514913.54 |  | 301647822.16 | 303547064.47 | -1899242.31 | 314789511 | -0.6033% |  |  | 2018-01-30 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-02-01 |  | 4412276.3 | 301647822.16 | 307959340.77 | -6311518.61 | 314789511 | -2.005% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-02-19 | 13320601.43 |  | 314968423.59 | 307959340.77 | 7009082.82 | 314789511 | 2.227% |  |  | 2018-02-19 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-02-19 | 1360370.04 |  | 316328793.63 | 307959340.77 | 8369452.86 | 314789511 | 2.659% |  |  | 2018-02-19 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-03-01 |  | 4019413.99 | 316328793.63 | 311978754.76 | 4350038.87 | 314789511 | 1.382% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-03-13 | 10942287.56 |  | 327271081.19 | 311978754.76 | 15292326.43 | 314789511 | 4.858% |  |  | 2018-03-13 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-04-01 |  | 4634224.86 | 327271081.19 | 316612979.62 | 10658101.57 | 314789511 | 3.386% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-04-19 | 6775827.66 |  | 334046908.85 | 316612979.62 | 17433929.23 | 314789511 | 5.538% |  |  | 2018-04-19 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-05-01 |  | 5096713.67 | 334046908.85 | 321709693.29 | 12337215.56 | 314789511 | 3.919% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-05-13 | 4572974.6 |  | 338619883.45 | 321709693.29 | 16910190.16 | 314789511 | 5.372% |  |  | 2018-05-13 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-05-27 | 2877801.39 |  | 341497684.84 | 321709693.29 | 19787991.55 | 314789511 | 6.286% |  |  | 2018-05-27 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-06-01 |  | 2859439.8 | 341497684.84 | 324569133.09 | 16928551.75 | 314789511 | 5.378% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-06-10 | 7033824.83 |  | 348531509.67 | 324569133.09 | 23962376.58 | 314789511 | 7.612% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-07-01 |  | 2048823.25 | 348531509.67 | 326617956.34 | 21913553.33 | 314789511 | 6.961% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-07-09 | 2358051.13 |  | 350889560.8 | 326617956.34 | 24271604.46 | 314789511 | 7.71% |  |  | 2018-07-09 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-07-19 | 2690853.59 |  | 353580414.39 | 326617956.34 | 26962458.05 | 314789511 | 8.565% |  |  | 2018-07-19 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-08-01 |  | 2616371.06 | 353580414.39 | 329234327.4 | 24346086.99 | 314789511 | 7.734% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-08-14 | 738114.93 |  | 354318529.32 | 329234327.4 | 25084201.92 | 314789511 | 7.969% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-08-14 | 1431626.08 |  | 355750155.4 | 329234327.4 | 26515828 | 314789511 | 8.423% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-09-01 |  | 1299669.71 | 355750155.4 | 330533997.11 | 25216158.29 | 314789511 | 8.01% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-09-27 | 2466454.76 |  | 358216610.16 | 330533997.11 | 27682613.05 | 314789511 | 8.794% |  |  | 2018-09-27 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-10-01 |  | 1150556.4 | 358216610.16 | 331684553.51 | 26532056.65 | 314789511 | 8.429% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-11-01 |  | 4067971.59 | 358216610.16 | 335752525.1 | 22464085.06 | 314789511 | 7.136% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2018-11-08 | 2490213.39 |  | 360706823.55 | 335752525.1 | 24954298.45 | 314789511 | 7.927% |  |  | 2018-11-08 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-11-29 | 1150865.97 |  | 361857689.52 | 335752525.1 | 26105164.42 | 314789511 | 8.293% |  |  | 2018-11-29 | added cash in 3 |  |  | 2018
Uptown Cairo Pkg 53 | 2018-12-01 |  | 1113764.04 | 361857689.52 | 336866289.14 | 24991400.38 | 314789511 | 7.939% |  |  |  | cash out both |  |  | 2018
Uptown Cairo Pkg 53 | 2019-01-01 |  | 441258.47 | 361857689.52 | 337307547.61 | 24550141.91 | 314789511 | 7.799% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-01-09 | 1746850.68 |  | 363604540.2 | 337307547.61 | 26296992.59 | 314789511 | 8.354% |  |  | 2019-01-09 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-01-30 | 1090584 |  | 364695124.2 | 337307547.61 | 27387576.59 | 314789511 | 8.7% |  |  | 2019-01-30 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-02-01 |  | 1977550.6 | 364695124.2 | 339285098.21 | 25410025.99 | 314789511 | 8.072% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-03-01 |  | 716244.11 | 364695124.2 | 340001342.32 | 24693781.88 | 314789511 | 7.845% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-03-12 | 1902092.11 |  | 366597216.31 | 340001342.32 | 26595873.99 | 314789511 | 8.449% |  |  | 2019-03-12 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-04-01 |  | 442940.14 | 366597216.31 | 340444282.46 | 26152933.85 | 314789511 | 8.308% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-04-09 | 451528 |  | 367048744.31 | 340444282.46 | 26604461.85 | 314789511 | 8.452% |  |  | 2019-04-09 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-05-01 |  | 453790.4 | 367048744.31 | 340898072.86 | 26150671.45 | 314789511 | 8.307% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-06-01 |  | 269135.29 | 367048744.31 | 341167208.15 | 25881536.16 | 314789511 | 8.222% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-06-10 | 943725.79 |  | 367992470.1 | 341167208.15 | 26825261.95 | 314789511 | 8.522% |  |  | 2019-06-10 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-07-01 |  | 245868.3 | 367992470.1 | 341413076.45 | 26579393.65 | 314789511 | 8.444% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-08-01 |  | 393472.74 | 367992470.1 | 341806549.19 | 26185920.91 | 314789511 | 8.319% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-08-07 | 1435222.17 |  | 369427692.27 | 341806549.19 | 27621143.08 | 314789511 | 8.774% |  |  | 2019-08-07 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-09-01 |  | 375978.67 | 369427692.27 | 342182527.86 | 27245164.41 | 314789511 | 8.655% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-09-12 | 293788 |  | 369721480.27 | 342182527.86 | 27538952.41 | 314789511 | 8.748% |  |  | 2019-09-12 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-09-23 | 4202366.45 |  | 373923846.72 | 342182527.86 | 31741318.86 | 314789511 | 10.08% |  |  | 2019-09-23 | added cash in 3 |  |  | 2019
Uptown Cairo Pkg 53 | 2019-10-01 |  | 505480.85 | 373923846.72 | 342688008.71 | 31235838.01 | 314789511 | 9.923% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-11-01 |  | 218136.99 | 373923846.72 | 342906145.7 | 31017701.02 | 314789511 | 9.853% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2019-12-01 |  | 257588.12 | 373923846.72 | 343163733.82 | 30760112.9 | 314789511 | 9.772% |  |  |  | cash out both |  |  | 2019
Uptown Cairo Pkg 53 | 2020-01-01 |  | 511542.8 | 373923846.72 | 343675276.62 | 30248570.1 | 314789511 | 9.609% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-01-20 | 29830.3 |  | 373953677.02 | 343675276.62 | 30278400.4 | 314789511 | 9.619% |  |  | 2020-01-20 | added cash in 3 |  |  | 2020
Uptown Cairo Pkg 53 | 2020-02-01 |  | 252076.81 | 373953677.02 | 343927353.43 | 30026323.59 | 314789511 | 9.539% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-02-17 | 1380970.95 |  | 375334647.97 | 343927353.43 | 31407294.54 | 314789511 | 9.977% |  |  | 2020-02-17 | added cash in 3 |  |  | 2020
Uptown Cairo Pkg 53 | 2020-03-01 |  | 648900.38 | 375334647.97 | 344576253.81 | 30758394.16 | 314789511 | 9.771% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-04-01 |  | 120394.34 | 375334647.97 | 344696648.15 | 30637999.82 | 314789511 | 9.733% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-04-29 | 1391898.96 |  | 376726546.93 | 344696648.15 | 32029898.78 | 314789511 | 10.18% |  |  | 2020-04-29 | added cash in 3 |  |  | 2020
Uptown Cairo Pkg 53 | 2020-05-01 |  | 89389.86 | 376726546.93 | 344786038.01 | 31940508.92 | 314789511 | 10.15% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-06-01 |  | 1282175.11 | 376726546.93 | 346068213.12 | 30658333.81 | 314789511 | 9.739% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-07-01 |  | 85228.53 | 376726546.93 | 346153441.65 | 30573105.28 | 314789511 | 9.712% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-08-01 |  | 155882.57 | 376726546.93 | 346309324.22 | 30417222.71 | 314789511 | 9.663% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-09-01 |  | 408741.45 | 376726546.93 | 346718065.67 | 30008481.26 | 314789511 | 9.533% |  |  |  | cash out both |  |  | 2020
Uptown Cairo Pkg 53 | 2020-10-01 |  | 47530 | 376726546.93 | 346765595.67 | 29960951.26 | 314789511 | 9.518% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Uptown Cairo Pkg 53 | 2020-11-01 |  | 85691 | 376726546.93 | 346851286.67 | 29875260.26 | 314789511 | 9.491% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Uptown Cairo Pkg 53 | 2020-11-11 | 4834138.97 |  | 381560685.9 | 346851286.67 | 34709399.23 | 314789511 | 11.03% |  |  | 2020-11-11 | added cash in 3 |  |  | 2020
Uptown Cairo Pkg 53 | 2020-12-01 |  | 58479.53 | 381560685.9 | 346909766.2 | 34650919.7 | 314789511 | 11.01% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Uptown Cairo Pkg 53 | 2021-01-01 |  | 55175.2 | 381560685.9 | 346964941.4 | 34595744.5 | 314789511 | 10.99% |  |  |  | cash out both |  |  | 2021
Uptown Cairo Pkg 53 | 2021-02-01 |  | 60443 | 381560685.9 | 347025384.4 | 34535301.5 | 314789511 | 10.97% |  |  |  | cash out both |  |  | 2021
Uptown Cairo Pkg 53 | 2021-03-01 |  | 404760.88 | 381560685.9 | 347430145.28 | 34130540.62 | 314789511 | 10.84% |  |  |  | cash out both |  |  | 2021
1900
Bani Suif Power Plant 1021 | 2015-07-31 | 0 | 147700 | 0 | 147700 | -147700 | 427594086.74 | -0.03454% |  | 0 | 2015-07-31 | original |  |  | 2015
Bani Suif Power Plant 1021 | 2015-08-30 | 0 | 334580 | 0 | 482280 | -482280 | 427594086.74 | -0.1128% |  | 0 | 2015-08-30 | original |  |  | 2015
Bani Suif Power Plant 1021 | 2015-09-29 | 3540240 | 247460 | 3540240 | 729740 | 2810500 | 427594086.74 | 0.6573% |  | 4049316 | 2015-09-29 | original |  |  | 2015
Bani Suif Power Plant 1021 | 2015-10-29 | 13624138 | 989897 | 17164378 | 1719637 | 15444741 | 427594086.74 | 3.612% |  | 7136419 | 2015-10-29 | original |  |  | 2015
Bani Suif Power Plant 1021 | 2015-11-28 | 6387095 | 5947736 | 23551473 | 7667373 | 15884100 | 427594086.74 | 3.715% |  | 3051785 | 2015-11-28 | original |  |  | 2015
Bani Suif Power Plant 1021 | 2015-12-28 | 43430464 | 16315539 | 66981937 | 23982912 | 42999025 | 427594086.74 | 10.06% |  | 0 | 2015-12-28 | original |  |  | 2015
Bani Suif Power Plant 1021 | 2016-01-27 | 63199591 | 12117980 | 130181528 | 36100892 | 94080636 | 427594086.74 | 22% |  | 2077186 | 2016-01-27 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-02-26 | 16149696 | 18985169 | 146331224 | 55086061 | 91245163 | 427594086.74 | 21.34% |  | 0 | 2016-02-26 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-03-27 | 18497443 | 24380775 | 164828667 | 79466836 | 85361831 | 427594086.74 | 19.96% |  | 0 | 2016-03-27 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-04-26 | 25207548 | 23115342 | 190036215 | 102582178 | 87454037 | 427594086.74 | 20.45% |  | 0 | 2016-04-26 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-05-26 | 16979590 | 13864400 | 207015805 | 116446578 | 90569227 | 427594086.74 | 21.18% |  | 9692661 | 2016-05-26 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-06-25 | 23636716 | 13116897 | 230652521 | 129563475 | 101089046 | 427594086.74 | 23.64% |  | 0 | 2016-06-25 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-07-25 | 0 | 7784151 | 230652521 | 137347626 | 93304895 | 427594086.74 | 21.82% |  | 2891177 | 2016-07-25 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-08-24 | 28428128 | 14054325 | 259080649 | 151401951 | 107678698 | 427594086.74 | 25.18% |  | 1602218 | 2016-08-24 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-09-23 | 0 | 10804163 | 259080649 | 162206114 | 96874535 | 427594086.74 | 22.66% |  | 0 | 2016-09-23 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-10-23 | 14538316 | 10947421 | 273618965 | 173153535 | 100465430 | 427594086.74 | 23.5% |  | 0 | 2016-10-23 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-11-22 | 18459309 | 10580410 | 292078274 | 183733945 | 108344329 | 427594086.74 | 25.34% |  | 0 | 2016-11-22 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2016-12-22 | 20000000 | 8207528 | 312078274 | 191941473 | 120136801 | 427594086.74 | 28.1% |  | 0 | 2016-12-22 | original |  |  | 2016
Bani Suif Power Plant 1021 | 2017-01-21 | 3120341 | 11875941 | 315198615 | 203817414 | 111381201 | 427594086.74 | 26.05% |  | 0 | 2017-01-21 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-02-20 | 15647341 | 11376813 | 330845956 | 215194227 | 115651729 | 427594086.74 | 27.05% |  | 0 | 2017-02-20 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-03-22 | 16367760 | 7121129 | 347213716 | 222315356 | 124898360 | 427594086.74 | 29.21% |  | 0 | 2017-03-22 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-03-30 | 16602510.88 |  | 363816226.88 | 222315356 | 141500870.88 | 427594086.74 | 33.09% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-04-01 |  | 218671.05 | 363816226.88 | 222534027.05 | 141282199.83 | 427594086.74 | 33.04% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-04-01 | 16079328.53 |  | 379895555.41 | 222534027.05 | 157361528.36 | 427594086.74 | 36.8% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-04-01 | 9303628.72 |  | 37203068.72 | 347220.87 | 36855847.85 | 427594086.74 | 8.619% |  |  | 2017-04-01 | added cash in 3 | old substation |  | 2017
Bani Suif Power Plant 1021 | 2017-07-31 | 993957.22 |  | 40017459.19 | 7453984.21 | 32563474.98 | 427594086.74 | 7.616% |  |  | 2017-07-31 | added cash in 3 | old substation |  | 2017
Bani Suif Power Plant 1021 | 2018-01-09 | 1624203.41 |  | 69938398.77 | 60364907.44 | 9573491.33 | 427594086.74 | 2.239% |  |  | 2018-01-09 | added cash in 3 | old substation |  | 2018
Bani Suif Power Plant 1021 | 2018-02-28 | 395600 |  | 77836552.95 | 63024606.34 | 14811946.61 | 427594086.74 | 3.464% |  |  | 2018-02-28 | added cash in 3 | old substation |  | 2018
Bani Suif Power Plant 1021 | 2018-02-28 | 5249425.15 |  | 83085978.1 | 63024606.34 | 20061371.76 | 427594086.74 | 4.692% |  |  | 2018-02-28 | added cash in 3 | old substation |  | 2018
Bani Suif Power Plant 1021 | 2018-06-10 | 2738736.27 |  | 105889189.93 | 87253962.2 | 18635227.73 | 427594086.74 | 4.358% |  |  | 2018-06-10 | added cash in 3 | old substation |  | 2018
Bani Suif Power Plant 1021 | 2018-06-10 | 674994.52 |  | 107239178.97 | 87253962.2 | 19985216.77 | 427594086.74 | 4.674% |  |  | 2018-06-10 | added cash in 3 | old substation |  | 2018
Bani Suif Power Plant 1021 | 2018-09-18 | 1693887.15 |  | 117037045.84 | 99707013.16 | 17330032.68 | 427594086.74 | 4.053% |  |  | 2018-09-18 | added cash in 3 | old substation |  | 2018
Bani Suif Power Plant 1021 | 2021-01-05 | 4329311.62 |  | 166120058 | 135514497.68 | 30605560.32 | 427594086.74 | 7.158% |  |  | 2021-01-05 | added cash in 3 | old substation |  | 2021
Bani Suif Power Plant 1021 | 2017-04-21 | 0 | 14680650 | 379895555.41 | 237214677.05 | 142680878.36 | 427594086.74 | 33.37% |  | 0 | 2017-04-21 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-05-01 |  | 506665.31 | 379895555.41 | 237721342.36 | 142174213.05 | 427594086.74 | 33.25% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-05-21 | 9303629 | 6125453 | 389199184.41 | 243846795.36 | 145352389.05 | 427594086.74 | 33.99% |  | 1145904 | 2017-05-21 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-05-31 | 13710534.18 |  | 402909718.59 | 243846795.36 | 159062923.23 | 427594086.74 | 37.2% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-05-31 | 23265624.91 |  | 426175343.5 | 243846795.36 | 182328548.14 | 427594086.74 | 42.64% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-06-01 |  | 572825.11 | 426175343.5 | 244419620.47 | 181755723.03 | 427594086.74 | 42.51% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-06-20 | 0 | 6563881 | 426175343.5 | 250983501.47 | 175191842.03 | 427594086.74 | 40.97% |  | 0 | 2017-06-20 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-06-30 | 12546063.86 |  | 438721407.36 | 250983501.47 | 187737905.89 | 427594086.74 | 43.91% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-07-01 |  | 626070.69 | 438721407.36 | 251609572.16 | 187111835.2 | 427594086.74 | 43.76% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-07-20 | 9571756 | 6041588 | 448293163.36 | 257651160.16 | 190642003.2 | 427594086.74 | 44.58% |  | 0 | 2017-07-20 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-07-31 | 5224000 |  | 453517163.36 | 257651160.16 | 195866003.2 | 427594086.74 | 45.81% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-08-01 |  | 846992.45 | 453517163.36 | 258498152.61 | 195019010.75 | 427594086.74 | 45.61% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-08-19 | 10250422 | 6297057 | 463767585.36 | 264795209.61 | 198972375.75 | 427594086.74 | 46.53% |  | 0 | 2017-08-19 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-08-31 | 8112852.08 |  | 471880437.44 | 264795209.61 | 207085227.83 | 427594086.74 | 48.43% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-09-01 |  | 298421.5 | 471880437.44 | 265093631.11 | 206786806.33 | 427594086.74 | 48.36% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-09-18 | 0 | 2069165 | 471880437.44 | 267162796.11 | 204717641.33 | 427594086.74 | 47.88% |  | 0 | 2017-09-18 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-09-30 | 17115970.9 |  | 488996408.34 | 267162796.11 | 221833612.23 | 427594086.74 | 51.88% |  |  | 2017-09-30 | added cash in 3 |  |  | 2017
Bani Suif Power Plant 1021 | 2017-10-01 |  | 3079125.26 | 488996408.34 | 270241921.37 | 218754486.97 | 427594086.74 | 51.16% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-10-18 | 27371052 | 3000178 | 516367460.34 | 273242099.37 | 243125360.97 | 427594086.74 | 56.86% |  | 0 | 2017-10-18 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-11-01 |  | 427092 | 516367460.34 | 273669191.37 | 242698268.97 | 427594086.74 | 56.76% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-11-17 | 0 | 1999696 | 516367460.34 | 275668887.37 | 240698572.97 | 427594086.74 | 56.29% |  | 0 | 2017-11-17 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2017-12-01 |  | 3969878.27 | 516367460.34 | 279638765.64 | 236728694.7 | 427594086.74 | 55.36% |  |  |  | cash out both |  |  | 2017
Bani Suif Power Plant 1021 | 2017-12-17 | 0 | 1968591 | 516367460.34 | 281607356.64 | 234760103.7 | 427594086.74 | 54.9% |  | 0 | 2017-12-17 | original |  |  | 2017
Bani Suif Power Plant 1021 | 2018-01-01 |  | 7289651.01 | 516367460.34 | 288897007.65 | 227470452.69 | 427594086.74 | 53.2% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-01-10 | 6990595.36 |  | 523358055.7 | 288897007.65 | 234461048.05 | 427594086.74 | 54.83% |  |  | 2018-01-10 | added cash in 3 |  |  | 2018
Bani Suif Power Plant 1021 | 2018-02-01 |  | 856732.47 | 523358055.7 | 289753740.12 | 233604315.58 | 427594086.74 | 54.63% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-02-18 | 7424114.83 |  | 530782170.53 | 289753740.12 | 241028430.41 | 427594086.74 | 56.37% |  |  | 2018-02-18 | added cash in 3 |  |  | 2018
Bani Suif Power Plant 1021 | 2018-03-01 |  | 3626135.94 | 530782170.53 | 293379876.06 | 237402294.47 | 427594086.74 | 55.52% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-03-07 | 6925479.91 |  | 537707650.44 | 293379876.06 | 244327774.38 | 427594086.74 | 57.14% |  |  | 2018-03-07 | added cash in 3 |  |  | 2018
Bani Suif Power Plant 1021 | 2018-04-01 |  | 5248992.36 | 537707650.44 | 298628868.42 | 239078782.02 | 427594086.74 | 55.91% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-05-01 |  | 3391151.83 | 537707650.44 | 302020020.25 | 235687630.19 | 427594086.74 | 55.12% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-05-08 | 12791498.8 |  | 550499149.24 | 302020020.25 | 248479128.99 | 427594086.74 | 58.11% |  |  | 2018-05-08 | added cash in 3 |  |  | 2018
Bani Suif Power Plant 1021 | 2018-06-01 |  | 1681341.06 | 550499149.24 | 303701361.31 | 246797787.93 | 427594086.74 | 57.72% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-07-01 |  | 982254.01 | 550499149.24 | 304683615.32 | 245815533.92 | 427594086.74 | 57.49% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-08-01 |  | 1608874.04 | 550499149.24 | 306292489.36 | 244206659.88 | 427594086.74 | 57.11% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-09-01 |  | 893435.51 | 550499149.24 | 307185924.87 | 243313224.37 | 427594086.74 | 56.9% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-10-01 |  | 473618.3 | 550499149.24 | 307659543.17 | 242839606.07 | 427594086.74 | 56.79% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-11-01 |  | 493053.43 | 550499149.24 | 308152596.6 | 242346552.64 | 427594086.74 | 56.68% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-12-01 |  | 216491.27 | 550499149.24 | 308369087.87 | 242130061.37 | 427594086.74 | 56.63% |  |  |  | cash out both |  |  | 2018
Bani Suif Power Plant 1021 | 2018-12-17 | 5224000 |  | 555723149.24 | 308369087.87 | 247354061.37 | 427594086.74 | 57.85% |  |  | 2018-12-17 | added cash in 3 |  |  | 2018
Bani Suif Power Plant 1021 | 2019-01-01 |  | 345622.64 | 555723149.24 | 308714710.51 | 247008438.73 | 427594086.74 | 57.77% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-02-01 |  | 1694295.5 | 555723149.24 | 310409006.01 | 245314143.23 | 427594086.74 | 57.37% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-03-01 |  | 63012.4 | 555723149.24 | 310472018.41 | 245251130.83 | 427594086.74 | 57.36% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-03-17 | 10152661.36 |  | 565875810.6 | 310472018.41 | 255403792.19 | 427594086.74 | 59.73% |  |  | 2019-03-17 | added cash in 3 |  |  | 2019
Bani Suif Power Plant 1021 | 2019-04-01 |  | 212898.37 | 565875810.6 | 310684916.78 | 255190893.82 | 427594086.74 | 59.68% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-05-01 |  | 108105.2 | 565875810.6 | 310793021.98 | 255082788.62 | 427594086.74 | 59.66% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-07-01 |  | 7135.32 | 565875810.6 | 310800157.3 | 255075653.3 | 427594086.74 | 59.65% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-09-01 |  | 3939 | 565875810.6 | 310804096.3 | 255071714.3 | 427594086.74 | 59.65% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-10-01 |  | 29789.37 | 565875810.6 | 310833885.67 | 255041924.93 | 427594086.74 | 59.65% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-11-01 |  | 1528 | 565875810.6 | 310835413.67 | 255040396.93 | 427594086.74 | 59.65% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2019-12-01 |  | 88677.31 | 565875810.6 | 310924090.98 | 254951719.62 | 427594086.74 | 59.62% |  |  |  | cash out both |  |  | 2019
Bani Suif Power Plant 1021 | 2020-01-01 |  | 100000 | 565875810.6 | 311024090.98 | 254851719.62 | 427594086.74 | 59.6% |  |  |  | cash out both |  |  | 2020
Bani Suif Power Plant 1021 | 2020-02-01 |  | 5075.05 | 565875810.6 | 311029166.03 | 254846644.57 | 427594086.74 | 59.6% |  |  |  | cash out both |  |  | 2020
Bani Suif Power Plant 1021 | 2020-03-01 |  | 14320 | 565875810.6 | 311043486.03 | 254832324.57 | 427594086.74 | 59.6% |  |  |  | cash out both |  |  | 2020
Bani Suif Power Plant 1021 | 2020-04-01 |  | 22196.31 | 565875810.6 | 311065682.34 | 254810128.26 | 427594086.74 | 59.59% |  |  |  | cash out both |  |  | 2020
Bani Suif Power Plant 1021 | 2020-08-01 |  | 114225 | 565875810.6 | 311179907.34 | 254695903.26 | 427594086.74 | 59.56% |  |  |  | cash out both |  |  | 2020
Bani Suif Power Plant 1021 | 2020-10-01 |  | 149657.94 | 565875810.6 | 311329565.28 | 254546245.32 | 427594086.74 | 59.53% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Bani Suif Power Plant 1021 | 2020-12-01 |  | 92545.2 | 565875810.6 | 311422110.48 | 254453700.12 | 427594086.74 | 59.51% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Bani Suif Power Plant 1021 | 2021-01-05 | 4326586.5 |  | 570202397.1 | 311422110.48 | 258780286.62 | 427594086.74 | 60.52% |  |  | 2021-01-05 | added 1 |  |  | 2021
1900
New Giza Phase 02 | 2015-08-30 | 0 | 1235235 | 0 | 1235235 | -1235235 | 155643269.76 | -0.7936% |  | 3666159 | 2015-08-30 | original |  |  | 2015
New Giza Phase 02 | 2015-09-30 | 29637377 | 13446591 | 29637377 | 14681826 | 14955551 | 155643269.76 | 9.609% |  | 2947529 | 2015-09-30 | original |  |  | 2015
New Giza Phase 02 | 2015-10-30 | 4586765 | 2616279 | 34224142 | 17298105 | 16926037 | 155643269.76 | 10.87% |  | 5298608 | 2015-10-30 | original |  |  | 2015
New Giza Phase 02 | 2015-11-30 | 0 | 5501224 | 34224142 | 22799329 | 11424813 | 155643269.76 | 7.34% |  | 8220856 | 2015-11-30 | original |  |  | 2015
New Giza Phase 02 | 2015-12-30 | 0 | 8141258 | 34224142 | 30940587 | 3283555 | 155643269.76 | 2.11% |  | 5801943 | 2015-12-30 | original |  |  | 2015
New Giza Phase 02 | 2016-01-30 | 0 | 5451532 | 34224142 | 36392119 | -2167977 | 155643269.76 | -1.393% |  | 5352562 | 2016-01-30 | original |  |  | 2016
New Giza Phase 02 | 2016-02-29 | 0 | 3603669 | 34224142 | 39995788 | -5771646 | 155643269.76 | -3.708% |  | 4388436 | 2016-02-29 | original |  |  | 2016
New Giza Phase 02 | 2016-03-30 | 17563755 | 12545548 | 51787897 | 52541336 | -753439 | 155643269.76 | -0.4841% |  | 3420205 | 2016-03-30 | original |  |  | 2016
New Giza Phase 02 | 2016-04-30 | 3905995 | 3148793 | 55693892 | 55690129 | 3763 | 155643269.76 | 0.002418% |  | 8821905 | 2016-04-30 | original |  |  | 2016
New Giza Phase 02 | 2016-05-30 | 8423296 | 3830635 | 64117188 | 59520764 | 4596424 | 155643269.76 | 2.953% |  | 2771682 | 2016-05-30 | original |  |  | 2016
New Giza Phase 02 | 2016-06-30 | 3298717 | 6751529 | 67415905 | 66272293 | 1143612 | 155643269.76 | 0.7348% |  | 2098881 | 2016-06-30 | original |  |  | 2016
New Giza Phase 02 | 2016-07-30 | 0 | 2378336 | 67415905 | 68650629 | -1234724 | 155643269.76 | -0.7933% |  | 6034533 | 2016-07-30 | original |  |  | 2016
New Giza Phase 02 | 2016-08-30 | 3461858 | 3473570 | 70877763 | 72124199 | -1246436 | 155643269.76 | -0.8008% |  | 9407244 | 2016-08-30 | original |  |  | 2016
New Giza Phase 02 | 2016-09-30 | 5275168 | 5300631 | 76152931 | 77424830 | -1271899 | 155643269.76 | -0.8172% |  | 7438667 | 2016-09-30 | original |  |  | 2016
New Giza Phase 02 | 2016-10-30 | 5636322 | 4222393 | 81789253 | 81647223 | 142030 | 155643269.76 | 0.09125% |  | 7251283 | 2016-10-30 | original |  |  | 2016
New Giza Phase 02 | 2016-11-30 | 10000016 | 9401120 | 91789269 | 91048343 | 740926 | 155643269.76 | 0.476% |  | 4715979 | 2016-11-30 | original |  |  | 2016
New Giza Phase 02 | 2016-12-30 | 4814232 | 2934762 | 96603501 | 93983105 | 2620396 | 155643269.76 | 1.684% |  | 9189505 | 2016-12-30 | original |  |  | 2016
New Giza Phase 02 | 2017-01-30 | 3576546 | 3139736 | 100180047 | 97122841 | 3057206 | 155643269.76 | 1.964% |  | 6589859 | 2017-01-30 | original |  |  | 2017
New Giza Phase 02 | 2017-02-28 | 5550000 | 7547923 | 105730047 | 104670764 | 1059283 | 155643269.76 | 0.6806% |  | 6232054 | 2017-02-28 | original |  |  | 2017
New Giza Phase 02 | 2017-03-30 | 8460776 | 5417841 | 114190823 | 110088605 | 4102218 | 155643269.76 | 2.636% |  | 7360122 | 2017-03-30 | original |  |  | 2017
New Giza Phase 02 | 2017-03-30 | 13857711 |  | 128048534 | 110088605 | 17959929 | 155643269.76 | 11.54% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
New Giza Phase 02 | 2017-04-01 | 4160257 |  | 132208791 | 110088605 | 22120186 | 155643269.76 | 14.21% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
New Giza Phase 02 | 2017-04-30 | 4160257 | 2321143 | 136369048 | 112409748 | 23959300 | 155643269.76 | 15.39% |  | 7780352 | 2017-04-30 | original |  |  | 2017
New Giza Phase 02 | 2017-05-01 |  | 2845820.75 | 136369048 | 115255568.75 | 21113479.25 | 155643269.76 | 13.57% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-05-30 | 5937405 | 5767975 | 142306453 | 121023543.75 | 21282909.25 | 155643269.76 | 13.67% |  | 6227576 | 2017-05-30 | original |  |  | 2017
New Giza Phase 02 | 2017-05-31 | 5937405 |  | 148243858 | 121023543.75 | 27220314.25 | 155643269.76 | 17.49% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
New Giza Phase 02 | 2017-06-01 |  | 200216.03 | 148243858 | 121223759.78 | 27020098.22 | 155643269.76 | 17.36% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-06-30 | 4635242 | 2658024 | 152879100 | 123881783.78 | 28997316.22 | 155643269.76 | 18.63% |  | 3408230 | 2017-06-30 | original |  |  | 2017
New Giza Phase 02 | 2017-06-30 | 4635241.71 |  | 157514341.71 | 123881783.78 | 33632557.93 | 155643269.76 | 21.61% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
New Giza Phase 02 | 2017-07-01 |  | 1797671.43 | 157514341.71 | 125679455.21 | 31834886.5 | 155643269.76 | 20.45% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-07-30 | 0 | 2833463 | 157514341.71 | 128512918.21 | 29001423.5 | 155643269.76 | 18.63% |  | 3675454 | 2017-07-30 | original |  |  | 2017
New Giza Phase 02 | 2017-08-01 |  | 1200698.53 | 157514341.71 | 129713616.74 | 27800724.97 | 155643269.76 | 17.86% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-08-30 | 6236991 | 5711834 | 163751332.71 | 135425450.74 | 28325881.97 | 155643269.76 | 18.2% |  | 3533111 | 2017-08-30 | original |  |  | 2017
New Giza Phase 02 | 2017-08-31 | 2470878 |  | 166222210.71 | 135425450.74 | 30796759.97 | 155643269.76 | 19.79% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
New Giza Phase 02 | 2017-08-31 | 7795512.89 |  | 174017723.6 | 135425450.74 | 38592272.86 | 155643269.76 | 24.8% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
New Giza Phase 02 | 2017-09-01 |  | 4658 | 174017723.6 | 135430108.74 | 38587614.86 | 155643269.76 | 24.79% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-09-30 | 0 | 207737 | 174017723.6 | 135637845.74 | 38379877.86 | 155643269.76 | 24.66% |  | 0 | 2017-09-30 | original |  |  | 2017
New Giza Phase 02 | 2017-10-01 |  | 1236963.09 | 174017723.6 | 136874808.83 | 37142914.77 | 155643269.76 | 23.86% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-10-30 | 1524217 | 2293921 | 175541940.6 | 139168729.83 | 36373210.77 | 155643269.76 | 23.37% |  | 0 | 2017-10-30 | original |  |  | 2017
New Giza Phase 02 | 2017-11-01 |  | 1875767.51 | 175541940.6 | 141044497.34 | 34497443.26 | 155643269.76 | 22.16% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-11-30 | 2468494 | 2682433 | 178010434.6 | 143726930.34 | 34283504.26 | 155643269.76 | 22.03% |  | 0 | 2017-11-30 | original |  |  | 2017
New Giza Phase 02 | 2017-12-01 |  | 82446.79 | 178010434.6 | 143809377.13 | 34201057.47 | 155643269.76 | 21.97% |  |  |  | cash out both |  |  | 2017
New Giza Phase 02 | 2017-12-30 | 0 | 723271 | 178010434.6 | 144532648.13 | 33477786.47 | 155643269.76 | 21.51% |  | 0 | 2017-12-30 | original |  |  | 2017
New Giza Phase 02 | 2018-01-01 |  | 144319.6 | 178010434.6 | 144676967.73 | 33333466.87 | 155643269.76 | 21.42% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-02-01 |  | 22446.66 | 178010434.6 | 144699414.39 | 33311020.21 | 155643269.76 | 21.4% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-03-01 |  | 9866.55 | 178010434.6 | 144709280.94 | 33301153.66 | 155643269.76 | 21.4% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-04-01 |  | 329690.05 | 178010434.6 | 145038970.99 | 32971463.61 | 155643269.76 | 21.18% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-05-01 |  | 6689.07 | 178010434.6 | 145045660.06 | 32964774.54 | 155643269.76 | 21.18% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-06-01 |  | 92833.35 | 178010434.6 | 145138493.41 | 32871941.19 | 155643269.76 | 21.12% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-06-19 | 3603174 |  | 181613608.6 | 145138493.41 | 36475115.19 | 155643269.76 | 23.44% |  |  | 2018-06-19 | added cash in 3 |  |  | 2018
New Giza Phase 02 | 2018-07-01 |  | 450517.66 | 181613608.6 | 145589011.07 | 36024597.53 | 155643269.76 | 23.15% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-07-15 | 4990186 |  | 186603794.6 | 145589011.07 | 41014783.53 | 155643269.76 | 26.35% |  |  | 2018-07-15 | added cash in 3 |  |  | 2018
New Giza Phase 02 | 2018-08-01 |  | 3041255.48 | 186603794.6 | 148630266.55 | 37973528.05 | 155643269.76 | 24.4% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-08-14 | 7673599 |  | 194277393.6 | 148630266.55 | 45647127.05 | 155643269.76 | 29.33% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
New Giza Phase 02 | 2018-09-01 |  | 2372999.77 | 194277393.6 | 151003266.32 | 43274127.28 | 155643269.76 | 27.8% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-10-01 |  | 647350.04 | 194277393.6 | 151650616.36 | 42626777.24 | 155643269.76 | 27.39% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-11-01 |  | 1252075 | 194277393.6 | 152902691.36 | 41374702.24 | 155643269.76 | 26.58% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2018-12-01 |  | 252299.43 | 194277393.6 | 153154990.79 | 41122402.81 | 155643269.76 | 26.42% |  |  |  | cash out both |  |  | 2018
New Giza Phase 02 | 2019-01-01 |  | 100591.46 | 194277393.6 | 153255582.25 | 41021811.35 | 155643269.76 | 26.36% |  |  |  | cash out both |  |  | 2019
New Giza Phase 02 | 2019-02-01 |  | 10289.42 | 194277393.6 | 153265871.67 | 41011521.93 | 155643269.76 | 26.35% |  |  |  | cash out both |  |  | 2019
New Giza Phase 02 | 2019-03-01 |  | 139871.89 | 194277393.6 | 153405743.56 | 40871650.04 | 155643269.76 | 26.26% |  |  |  | cash out both |  |  | 2019
New Giza Phase 02 | 2019-04-01 |  | 174699.23 | 194277393.6 | 153580442.79 | 40696950.81 | 155643269.76 | 26.15% |  |  |  | cash out both |  |  | 2019
New Giza Phase 02 | 2019-12-01 |  | 132497.49 | 194277393.6 | 153712940.28 | 40564453.32 | 155643269.76 | 26.06% |  |  |  | cash out both |  |  | 2019
New Giza Phase 02 | 2020-01-28 | 2104161 |  | 196381554.6 | 153712940.28 | 42668614.32 | 155643269.76 | 27.41% |  |  | 2020-01-28 | added 1 |  |  | 2020
New Giza Phase 02 | 2020-04-01 |  | 35314.26 | 196381554.6 | 153748254.54 | 42633300.06 | 155643269.76 | 27.39% |  |  |  | cash out both |  |  | 2020
New Giza Phase 02 | 2020-05-01 |  | 40517 | 196381554.6 | 153788771.54 | 42592783.06 | 155643269.76 | 27.37% |  |  |  | cash out both |  |  | 2020
New Giza Phase 02 | 2020-06-01 |  | 34470.28 | 196381554.6 | 153823241.82 | 42558312.78 | 155643269.76 | 27.34% |  |  |  | cash out both |  |  | 2020
New Giza Phase 02 | 2020-10-01 |  | 21982.92 | 196381554.6 | 153845224.74 | 42536329.86 | 155643269.76 | 27.33% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
New Giza Phase 02 | 2020-10-25 | 313708 |  | 196695262.6 | 153845224.74 | 42850037.86 | 155643269.76 | 27.53% |  |  | 2020-10-25 | added 1 |  |  | 2020
New Giza Phase 02 | 2020-11-01 |  | 121183.78 | 196695262.6 | 153966408.52 | 42728854.08 | 155643269.76 | 27.45% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
New Giza Phase 02 | 2020-12-01 |  | 358005 | 196695262.6 | 154324413.52 | 42370849.08 | 155643269.76 | 27.22% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
New Giza Phase 02 | 2021-02-01 |  | 104901.44 | 196695262.6 | 154429314.96 | 42265947.64 | 155643269.76 | 27.16% |  |  |  | cash out both |  |  | 2021
1900
JICA Wind Farm Gabal El Zeet | 2015-11-30 | 0 | 70000 | 0 | 70000 | -70000 | 120483319.9 | -0.0581% |  | 0 | 2015-11-30 | original |  |  | 2015
JICA Wind Farm Gabal El Zeet | 2015-12-31 | 40803000 | 422060 | 40803000 | 492060 | 40310940 | 120483319.9 | 33.46% |  | 0 | 2015-12-31 | original |  |  | 2015
JICA Wind Farm Gabal El Zeet | 2016-01-31 | 0 | 1312651 | 40803000 | 1804711 | 38998289 | 120483319.9 | 32.37% |  | 6596770 | 2016-01-31 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-02-29 | 0 | 3108546 | 40803000 | 4913257 | 35889743 | 120483319.9 | 29.79% |  | 10725650 | 2016-02-29 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-03-31 | 0 | 5078863 | 40803000 | 9992120 | 30810880 | 120483319.9 | 25.57% |  | 5923635 | 2016-03-31 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-04-30 | 0 | 3078859 | 40803000 | 13070979 | 27732021 | 120483319.9 | 23.02% |  | 5319791 | 2016-04-30 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-05-31 | 9237636 | 3423933 | 50040636 | 16494912 | 33545724 | 120483319.9 | 27.84% |  | 11503990 | 2016-05-31 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-06-30 | 0 | 3375856 | 50040636 | 19870768 | 30169868 | 120483319.9 | 25.04% |  | 8848356 | 2016-06-30 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-07-31 | 6127667 | 5596265 | 56168303 | 25467033 | 30701270 | 120483319.9 | 25.48% |  | 10889299 | 2016-07-31 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-08-31 | 6269675 | 7018075 | 62437978 | 32485108 | 29952870 | 120483319.9 | 24.86% |  | 11732540 | 2016-08-31 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-09-30 | 0 | 3378966 | 62437978 | 35864074 | 26573904 | 120483319.9 | 22.06% |  | 12559619 | 2016-09-30 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-10-31 | 14744602 | 11229556 | 77182580 | 47093630 | 30088950 | 120483319.9 | 24.97% |  | 9456723 | 2016-10-31 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-11-30 | 9251647 | 4726905 | 86434227 | 51820535 | 34613692 | 120483319.9 | 28.73% |  | 8920594 | 2016-11-30 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2016-12-31 | 0 | 17575959 | 86434227 | 69396494 | 17037733 | 120483319.9 | 14.14% |  | 2983177 | 2016-12-31 | original |  |  | 2016
JICA Wind Farm Gabal El Zeet | 2017-01-31 | 11998906 | 3032449 | 98433133 | 72428943 | 26004190 | 120483319.9 | 21.58% |  | 1879134 | 2017-01-31 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-02-28 | 4563406 | 4528710 | 102996539 | 76957653 | 26038886 | 120483319.9 | 21.61% |  | 7874877 | 2017-02-28 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-03-30 | 2404766.19 |  | 105401305.19 | 76957653 | 28443652.19 | 120483319.9 | 23.61% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-03-31 | 0 | 3267691 | 105401305.19 | 80225344 | 25175961.19 | 120483319.9 | 20.9% |  | 3592384 | 2017-03-31 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-04-30 | 5202314 | 2502244 | 110603619.19 | 82727588 | 27876031.19 | 120483319.9 | 23.14% |  | 323060 | 2017-04-30 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-05-31 | 3704353 | 2859736 | 114307972.19 | 85587324 | 28720648.19 | 120483319.9 | 23.84% |  | 0 | 2017-05-31 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-05-31 | 2586268.54 |  | 116894240.73 | 85587324 | 31306916.73 | 120483319.9 | 25.98% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-05-31 | 1118084.46 |  | 118012325.19 | 85587324 | 32425001.19 | 120483319.9 | 26.91% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-06-01 |  | 20837.77 | 118012325.19 | 85608161.77 | 32404163.42 | 120483319.9 | 26.9% |  |  |  | cash out both |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-06-30 | 0 | 5638250 | 118012325.19 | 91246411.77 | 26765913.42 | 120483319.9 | 22.22% |  | 0 | 2017-06-30 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-07-01 |  | 401234.21 | 118012325.19 | 91647645.98 | 26364679.21 | 120483319.9 | 21.88% |  |  |  | cash out both |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-07-31 | 4018478 | 4099625 | 122030803.19 | 95747270.98 | 26283532.21 | 120483319.9 | 21.82% |  | 0 | 2017-07-31 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-07-31 | 2137468.33 |  | 124168271.52 | 95747270.98 | 28421000.54 | 120483319.9 | 23.59% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-07-31 | 1696005.64 |  | 125864277.16 | 95747270.98 | 30117006.18 | 120483319.9 | 25% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-07-31 | 186004 |  | 126050281.16 | 95747270.98 | 30303010.18 | 120483319.9 | 25.15% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-08-01 |  | 213098.55 | 126050281.16 | 95960369.53 | 30089911.63 | 120483319.9 | 24.97% |  |  |  | cash out both |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-08-31 | 6005029 | 1235495 | 132055310.16 | 97195864.53 | 34859445.63 | 120483319.9 | 28.93% |  | 0 | 2017-08-31 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-09-30 | 0 | 219490 | 132055310.16 | 97415354.53 | 34639955.63 | 120483319.9 | 28.75% |  | 0 | 2017-09-30 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-10-01 |  | 172517.7 | 132055310.16 | 97587872.23 | 34467437.93 | 120483319.9 | 28.61% |  |  |  | cash out both |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-10-31 | 53837 | 928432 | 132109147.16 | 98516304.23 | 33592842.93 | 120483319.9 | 27.88% |  | 1210864 | 2017-10-31 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-11-01 |  | 30074.73 | 132109147.16 | 98546378.96 | 33562768.2 | 120483319.9 | 27.86% |  |  |  | cash out both |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-11-30 | 4132072 | 53368 | 136241219.16 | 98599746.96 | 37641472.2 | 120483319.9 | 31.24% |  | 0 | 2017-11-30 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-12-01 |  | 52214.88 | 136241219.16 | 98651961.84 | 37589257.32 | 120483319.9 | 31.2% |  |  |  | cash out both |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2017-12-31 | 0 | 248838 | 136241219.16 | 98900799.84 | 37340419.32 | 120483319.9 | 30.99% |  | 0 | 2017-12-31 | original |  |  | 2017
JICA Wind Farm Gabal El Zeet | 2018-01-01 |  | 179964.77 | 136241219.16 | 99080764.61 | 37160454.55 | 120483319.9 | 30.84% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-02-01 |  | 204171.36 | 136241219.16 | 99284935.97 | 36956283.19 | 120483319.9 | 30.67% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-03-01 |  | 271214.9 | 136241219.16 | 99556150.87 | 36685068.29 | 120483319.9 | 30.45% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-04-01 |  | 295681.56 | 136241219.16 | 99851832.43 | 36389386.73 | 120483319.9 | 30.2% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-04-24 | 75000 |  | 136316219.16 | 99851832.43 | 36464386.73 | 120483319.9 | 30.27% |  |  | 2018-04-24 | added cash in 3 |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-05-01 |  | 207873.45 | 136316219.16 | 100059705.88 | 36256513.28 | 120483319.9 | 30.09% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-05-08 | 221249.2 |  | 136537468.36 | 100059705.88 | 36477762.48 | 120483319.9 | 30.28% |  |  | 2018-05-08 | added cash in 3 |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-06-01 |  | 184000 | 136537468.36 | 100243705.88 | 36293762.48 | 120483319.9 | 30.12% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-06-10 | 1141675.9 |  | 137679144.26 | 100243705.88 | 37435438.38 | 120483319.9 | 31.07% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-07-01 |  | 198620.53 | 137679144.26 | 100442326.41 | 37236817.85 | 120483319.9 | 30.91% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-07-09 | 182280 |  | 137861424.26 | 100442326.41 | 37419097.85 | 120483319.9 | 31.06% |  |  | 2018-07-09 | added cash in 3 |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-07-25 | 91140 |  | 137952564.26 | 100442326.41 | 37510237.85 | 120483319.9 | 31.13% |  |  | 2018-07-25 | added cash in 3 |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-08-01 |  | 587193.9 | 137952564.26 | 101029520.31 | 36923043.95 | 120483319.9 | 30.65% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-09-01 |  | 404069.3 | 137952564.26 | 101433589.61 | 36518974.65 | 120483319.9 | 30.31% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-10-01 |  | 180496.45 | 137952564.26 | 101614086.06 | 36338478.2 | 120483319.9 | 30.16% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-11-01 |  | 92905 | 137952564.26 | 101706991.06 | 36245573.2 | 120483319.9 | 30.08% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-11-22 | 2648763.21 |  | 140601327.47 | 101706991.06 | 38894336.41 | 120483319.9 | 32.28% |  |  | 2018-11-22 | added cash in 3 |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2018-12-01 |  | 158878.66 | 140601327.47 | 101865869.72 | 38735457.75 | 120483319.9 | 32.15% |  |  |  | cash out both |  |  | 2018
JICA Wind Farm Gabal El Zeet | 2019-01-01 |  | 150000 | 140601327.47 | 102015869.72 | 38585457.75 | 120483319.9 | 32.03% |  |  |  | cash out both |  |  | 2019
JICA Wind Farm Gabal El Zeet | 2019-02-01 |  | 200000 | 140601327.47 | 102215869.72 | 38385457.75 | 120483319.9 | 31.86% |  |  |  | cash out both |  |  | 2019
JICA Wind Farm Gabal El Zeet | 2019-03-01 |  | 138643.58 | 140601327.47 | 102354513.3 | 38246814.17 | 120483319.9 | 31.74% |  |  |  | cash out both |  |  | 2019
JICA Wind Farm Gabal El Zeet | 2019-05-01 |  | 200000 | 140601327.47 | 102554513.3 | 38046814.17 | 120483319.9 | 31.58% |  |  |  | cash out both |  |  | 2019
JICA Wind Farm Gabal El Zeet | 2019-08-01 |  | 50000 | 140601327.47 | 102604513.3 | 37996814.17 | 120483319.9 | 31.54% |  |  |  | cash out both |  |  | 2019
JICA Wind Farm Gabal El Zeet | 2019-10-01 |  | 242455.96 | 140601327.47 | 102846969.26 | 37754358.21 | 120483319.9 | 31.34% |  |  |  | cash out both |  |  | 2019
JICA Wind Farm Gabal El Zeet | 2020-08-01 |  | 108222 | 140601327.47 | 102955191.26 | 37646136.21 | 120483319.9 | 31.25% |  |  |  | cash out both |  |  | 2020
1900
El Mostathmereen Mokatam Substation | 2017-04-01 |  | 651002.5 | 0 | 651002.5 | -651002.5 | 135792183 | -0.4794% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-04-01 | 2491720.43 |  | 2491720.43 | 651002.5 | 1840717.93 | 135792183 | 1.356% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-05-01 |  | 9380.96 | 2491720.43 | 660383.46 | 1831336.97 | 135792183 | 1.349% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-05-31 | 5999615 |  | 8491335.43 | 660383.46 | 7830951.97 | 135792183 | 5.767% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-06-01 |  | 145014.46 | 8491335.43 | 805397.92 | 7685937.51 | 135792183 | 5.66% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-07-01 |  | 345164.46 | 8491335.43 | 1150562.38 | 7340773.05 | 135792183 | 5.406% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-08-01 |  | 752110.92 | 8491335.43 | 1902673.3 | 6588662.13 | 135792183 | 4.852% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-08-31 | 6998696.74 |  | 15490032.17 | 1902673.3 | 13587358.87 | 135792183 | 10.01% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-08-31 | 5662699.51 |  | 21152731.68 | 1902673.3 | 19250058.38 | 135792183 | 14.18% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-08-31 | 858548.57 |  | 22011280.25 | 1902673.3 | 20108606.95 | 135792183 | 14.81% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-08-31 | 2264574.66 |  | 24275854.91 | 1902673.3 | 22373181.61 | 135792183 | 16.48% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-08-31 | 2003444.81 |  | 26279299.72 | 1902673.3 | 24376626.42 | 135792183 | 17.95% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-09-01 |  | 107891.55 | 26279299.72 | 2010564.85 | 24268734.87 | 135792183 | 17.87% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-09-30 | 876287.52 |  | 27155587.24 | 2010564.85 | 25145022.39 | 135792183 | 18.52% |  |  | 2017-09-30 | added cash in 3 |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-10-01 |  | 220222.77 | 27155587.24 | 2230787.62 | 24924799.62 | 135792183 | 18.36% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-11-01 |  | 23360.56 | 27155587.24 | 2254148.18 | 24901439.06 | 135792183 | 18.34% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2017-12-01 |  | 17393.36 | 27155587.24 | 2271541.54 | 24884045.7 | 135792183 | 18.33% |  |  |  | cash out both |  |  | 2017
El Mostathmereen Mokatam Substation | 2018-01-01 |  | 319918.08 | 27155587.24 | 2591459.62 | 24564127.62 | 135792183 | 18.09% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-02-01 |  | 6306.93 | 27155587.24 | 2597766.55 | 24557820.69 | 135792183 | 18.08% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-02-14 | 251219.38 |  | 27406806.62 | 2597766.55 | 24809040.07 | 135792183 | 18.27% |  |  | 2018-02-14 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-02-14 | 1006227.65 |  | 28413034.27 | 2597766.55 | 25815267.72 | 135792183 | 19.01% |  |  | 2018-02-14 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-03-01 |  | 109475.02 | 28413034.27 | 2707241.57 | 25705792.7 | 135792183 | 18.93% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-03-01 | 3022108.87 |  | 31435143.14 | 2707241.57 | 28727901.57 | 135792183 | 21.16% |  |  | 2018-03-01 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-03-01 | 1917903.73 |  | 33353046.87 | 2707241.57 | 30645805.3 | 135792183 | 22.57% |  |  | 2018-03-01 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-04-01 |  | 525375.37 | 33353046.87 | 3232616.94 | 30120429.93 | 135792183 | 22.18% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-04-12 | 9932.85 |  | 33362979.72 | 3232616.94 | 30130362.78 | 135792183 | 22.19% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-04-19 | 103400.93 |  | 33466380.65 | 3232616.94 | 30233763.71 | 135792183 | 22.26% |  |  | 2018-04-19 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-04-19 | 4746 |  | 33471126.65 | 3232616.94 | 30238509.71 | 135792183 | 22.27% |  |  | 2018-04-19 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-05-01 |  | 196312.29 | 33471126.65 | 3428929.23 | 30042197.42 | 135792183 | 22.12% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-06-01 |  | 190504.63 | 33471126.65 | 3619433.86 | 29851692.79 | 135792183 | 21.98% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-06-24 | 662862.19 |  | 34133988.84 | 3619433.86 | 30514554.98 | 135792183 | 22.47% |  |  | 2018-06-24 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-06-24 | 201588.47 |  | 34335577.31 | 3619433.86 | 30716143.45 | 135792183 | 22.62% |  |  | 2018-06-24 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-06-24 | 125202.1 |  | 34460779.41 | 3619433.86 | 30841345.55 | 135792183 | 22.71% |  |  | 2018-06-24 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-07-01 |  | 665347.46 | 34460779.41 | 4284781.32 | 30175998.09 | 135792183 | 22.22% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-08-01 |  | 367807.95 | 34460779.41 | 4652589.27 | 29808190.14 | 135792183 | 21.95% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-09-01 |  | 89153.83 | 34460779.41 | 4741743.1 | 29719036.31 | 135792183 | 21.89% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-10-01 |  | 268351.58 | 34460779.41 | 5010094.68 | 29450684.73 | 135792183 | 21.69% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-10-08 | 1250414.58 |  | 35711193.99 | 5010094.68 | 30701099.31 | 135792183 | 22.61% |  |  | 2018-10-08 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-10-16 | 357966.9 |  | 36069160.89 | 5010094.68 | 31059066.21 | 135792183 | 22.87% |  |  | 2018-10-16 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-10-16 | 19882.99 |  | 36089043.88 | 5010094.68 | 31078949.2 | 135792183 | 22.89% |  |  | 2018-10-16 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-10-25 | 2246164.14 |  | 38335208.02 | 5010094.68 | 33325113.34 | 135792183 | 24.54% |  |  | 2018-10-25 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-11-01 |  | 146686.95 | 38335208.02 | 5156781.63 | 33178426.39 | 135792183 | 24.43% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-12-01 |  | 232123.79 | 38335208.02 | 5388905.42 | 32946302.6 | 135792183 | 24.26% |  |  |  | cash out both |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-12-19 | 3748571.22 |  | 42083779.24 | 5388905.42 | 36694873.82 | 135792183 | 27.02% |  |  | 2018-12-19 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2018-12-19 | 6818.1 |  | 42090597.34 | 5388905.42 | 36701691.92 | 135792183 | 27.03% |  |  | 2018-12-19 | added cash in 3 |  |  | 2018
El Mostathmereen Mokatam Substation | 2019-01-01 |  | 888 | 42090597.34 | 5389793.42 | 36700803.92 | 135792183 | 27.03% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-01-09 | 3583860.22 |  | 45674457.56 | 5389793.42 | 40284664.14 | 135792183 | 29.67% |  |  | 2019-01-09 | added cash in 3 |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-01-17 | 1518598.55 |  | 47193056.11 | 5389793.42 | 41803262.69 | 135792183 | 30.78% |  |  | 2019-01-17 | added cash in 3 |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-03-01 |  | 21494.82 | 47193056.11 | 5411288.24 | 41781767.87 | 135792183 | 30.77% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-04-01 |  | 140145 | 47193056.11 | 5551433.24 | 41641622.87 | 135792183 | 30.67% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-04-15 | 9815.15 |  | 47202871.26 | 5551433.24 | 41651438.02 | 135792183 | 30.67% |  |  | 2019-04-15 | added cash in 3 |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-04-18 | 206942.77 |  | 47409814.03 | 5551433.24 | 41858380.79 | 135792183 | 30.83% |  |  | 2019-04-18 | added cash in 3 |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-08-01 |  | 736856.6 | 47409814.03 | 6288289.84 | 41121524.19 | 135792183 | 30.28% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-09-01 |  | 143348 | 47409814.03 | 6431637.84 | 40978176.19 | 135792183 | 30.18% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-10-01 |  | 15000 | 47409814.03 | 6446637.84 | 40963176.19 | 135792183 | 30.17% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-10-09 | 1757020.47 |  | 49166834.5 | 6446637.84 | 42720196.66 | 135792183 | 31.46% |  |  | 2019-10-09 | added cash in 3 |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-10-13 | 266971.95 |  | 49433806.45 | 6446637.84 | 42987168.61 | 135792183 | 31.66% |  |  | 2019-10-13 | added cash in 3 |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-11-01 |  | 54191.89 | 49433806.45 | 6500829.73 | 42932976.72 | 135792183 | 31.62% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-12-01 |  | 5447349.2 | 49433806.45 | 11948178.93 | 37485627.52 | 135792183 | 27.61% |  |  |  | cash out both |  |  | 2019
El Mostathmereen Mokatam Substation | 2019-12-31 | 2000000 |  | 51433806.45 | 11948178.93 | 39485627.52 | 135792183 | 29.08% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
El Mostathmereen Mokatam Substation | 2020-01-01 |  | 888 | 51433806.45 | 11949066.93 | 39484739.52 | 135792183 | 29.08% |  |  |  | cash out both |  |  | 2020
El Mostathmereen Mokatam Substation | 2020-02-01 |  | 49862.7 | 51433806.45 | 11998929.63 | 39434876.82 | 135792183 | 29.04% |  |  |  | cash out both |  |  | 2020
El Mostathmereen Mokatam Substation | 2020-05-01 |  | 49862.7 | 51433806.45 | 12048792.33 | 39385014.12 | 135792183 | 29% |  |  |  | cash out both |  |  | 2020
El Mostathmereen Mokatam Substation | 2020-06-01 |  | 260 | 51433806.45 | 12049052.33 | 39384754.12 | 135792183 | 29% |  |  |  | cash out both |  |  | 2020
El Mostathmereen Mokatam Substation | 2020-08-01 |  | 44123.41 | 51433806.45 | 12093175.74 | 39340630.71 | 135792183 | 28.97% |  |  |  | cash out both |  |  | 2020
El Mostathmereen Mokatam Substation | 2020-11-01 |  | 44123.35 | 51433806.45 | 12137299.09 | 39296507.36 | 135792183 | 28.94% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
El Mostathmereen Mokatam Substation | 2021-03-01 |  | 44123.41 | 51433806.45 | 12181422.5 | 39252383.95 | 135792183 | 28.91% |  |  |  | cash out both |  |  | 2021
1900
Levana UpTown Pkg 62 | 2016-03-31 | 0 | 37382 | 0 | 37382 | -37382 | 47319156 | -0.079% |  | 0 | 2016-03-31 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-04-30 | 15011610 | 675195 | 15011610 | 712577 | 14299033 | 47319156 | 30.22% |  | 0 | 2016-04-30 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-05-31 | 0 | 532745 | 15011610 | 1245322 | 13766288 | 47319156 | 29.09% |  | 0 | 2016-05-31 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-06-30 | 0 | 229819 | 15011610 | 1475141 | 13536469 | 47319156 | 28.61% |  | 0 | 2016-06-30 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-07-31 | 0 | 1135579 | 15011610 | 2610720 | 12400890 | 47319156 | 26.21% |  | 0 | 2016-07-31 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-08-31 | 0 | 446458 | 15011610 | 3057178 | 11954432 | 47319156 | 25.26% |  | 0 | 2016-08-31 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-09-30 | 0 | 415909 | 15011610 | 3473087 | 11538523 | 47319156 | 24.38% |  | 0 | 2016-09-30 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-10-31 | 0 | 404830 | 15011610 | 3877917 | 11133693 | 47319156 | 23.53% |  | 0 | 2016-10-31 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-11-30 | 0 | 966035 | 15011610 | 4843952 | 10167658 | 47319156 | 21.49% |  | 2732328 | 2016-11-30 | original |  |  | 2016
Levana UpTown Pkg 62 | 2016-12-31 | 0 | 297394 | 15011610 | 5141346 | 9870264 | 47319156 | 20.86% |  | 0 | 2016-12-31 | original |  |  | 2016
Levana UpTown Pkg 62 | 2017-01-31 | 0 | 456488 | 15011610 | 5597834 | 9413776 | 47319156 | 19.89% |  | 0 | 2017-01-31 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-02-28 | 0 | 458750 | 15011610 | 6056584 | 8955026 | 47319156 | 18.92% |  | 0 | 2017-02-28 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-03-30 | 12606185.12 |  | 27617795.12 | 6056584 | 21561211.12 | 47319156 | 45.57% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
Levana UpTown Pkg 62 | 2017-03-31 | 0 | 306806 | 27617795.12 | 6363390 | 21254405.12 | 47319156 | 44.92% |  | 1481722 | 2017-03-31 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-04-01 |  | 37976.41 | 27617795.12 | 6401366.41 | 21216428.71 | 47319156 | 44.84% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-04-01 | 875748.73 |  | 28493543.85 | 6401366.41 | 22092177.44 | 47319156 | 46.69% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
Levana UpTown Pkg 62 | 2017-04-30 | 875749 | 928941 | 29369292.85 | 7330307.41 | 22038985.44 | 47319156 | 46.58% |  | 2210783 | 2017-04-30 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-05-01 |  | 177091.05 | 29369292.85 | 7507398.46 | 21861894.39 | 47319156 | 46.2% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-05-31 | 0 | 1131718 | 29369292.85 | 8639116.46 | 20730176.39 | 47319156 | 43.81% |  | 0 | 2017-05-31 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-06-01 |  | 11808.15 | 29369292.85 | 8650924.61 | 20718368.24 | 47319156 | 43.78% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-06-30 | 1232263 | 456253 | 30601555.85 | 9107177.61 | 21494378.24 | 47319156 | 45.42% |  | 1036832 | 2017-06-30 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-06-30 | 1232262.6 |  | 31833818.45 | 9107177.61 | 22726640.84 | 47319156 | 48.03% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
Levana UpTown Pkg 62 | 2017-07-01 |  | 44881.68 | 31833818.45 | 9152059.29 | 22681759.16 | 47319156 | 47.93% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-07-31 | 0 | 1281697 | 31833818.45 | 10433756.29 | 21400062.16 | 47319156 | 45.22% |  | 5457135 | 2017-07-31 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-08-01 |  | 310508.62 | 31833818.45 | 10744264.91 | 21089553.54 | 47319156 | 44.57% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-08-31 | 3833708 | 2543944 | 35667526.45 | 13288208.91 | 22379317.54 | 47319156 | 47.29% |  | 2439085 | 2017-08-31 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-08-31 | 3833708.33 |  | 39501234.78 | 13288208.91 | 26213025.87 | 47319156 | 55.4% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Levana UpTown Pkg 62 | 2017-09-01 |  | 61383.15 | 39501234.78 | 13349592.06 | 26151642.72 | 47319156 | 55.27% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-09-30 | 3442195 | 901089 | 42943429.78 | 14250681.06 | 28692748.72 | 47319156 | 60.64% |  | 3062111 | 2017-09-30 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-09-30 | 1484274.29 |  | 44427704.07 | 14250681.06 | 30177023.01 | 47319156 | 63.77% |  |  | 2017-09-30 | added cash in 3 |  |  | 2017
Levana UpTown Pkg 62 | 2017-09-30 | 1957920.34 |  | 46385624.41 | 14250681.06 | 32134943.35 | 47319156 | 67.91% |  |  | 2017-09-30 | added cash in 3 |  |  | 2017
Levana UpTown Pkg 62 | 2017-10-01 |  | 597864.3 | 46385624.41 | 14848545.36 | 31537079.05 | 47319156 | 66.65% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-10-31 | 0 | 2927378 | 46385624.41 | 17775923.36 | 28609701.05 | 47319156 | 60.46% |  | 4024170 | 2017-10-31 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-11-01 |  | 1154898.5 | 46385624.41 | 18930821.86 | 27454802.55 | 47319156 | 58.02% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-11-30 | 1684908 | 2553220 | 48070532.41 | 21484041.86 | 26586490.55 | 47319156 | 56.19% |  | 3353637 | 2017-11-30 | original |  |  | 2017
Levana UpTown Pkg 62 | 2017-12-01 |  | 1278380.5 | 48070532.41 | 22762422.36 | 25308110.05 | 47319156 | 53.48% |  |  |  | cash out both |  |  | 2017
Levana UpTown Pkg 62 | 2017-12-31 | 2970871 | 3859473 | 51041403.41 | 26621895.36 | 24419508.05 | 47319156 | 51.61% |  | 3315630 | 2017-12-31 | original |  |  | 2017
Levana UpTown Pkg 62 | 2018-01-01 |  | 3268363.8 | 51041403.41 | 29890259.16 | 21151144.25 | 47319156 | 44.7% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-01-02 | 2124952.16 |  | 53166355.57 | 29890259.16 | 23276096.41 | 47319156 | 49.19% |  |  | 2018-01-02 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-01-29 | 1215279.38 |  | 54381634.95 | 29890259.16 | 24491375.79 | 47319156 | 51.76% |  |  | 2018-01-29 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-02-01 |  | 3350598.15 | 54381634.95 | 33240857.31 | 21140777.64 | 47319156 | 44.68% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-02-07 | 2207449.91 |  | 56589084.86 | 33240857.31 | 23348227.55 | 47319156 | 49.34% |  |  | 2018-02-07 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-03-01 |  | 3454652.16 | 56589084.86 | 36695509.47 | 19893575.39 | 47319156 | 42.04% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-03-08 | 1524280.95 |  | 58113365.81 | 36695509.47 | 21417856.34 | 47319156 | 45.26% |  |  | 2018-03-08 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-04-01 |  | 1685712.48 | 58113365.81 | 38381221.95 | 19732143.86 | 47319156 | 41.7% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-04-12 | 1565019.14 |  | 59678384.95 | 38381221.95 | 21297163 | 47319156 | 45.01% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-05-01 |  | 2696978.7 | 59678384.95 | 41078200.65 | 18600184.3 | 47319156 | 39.31% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-05-16 | 2219134.03 |  | 61897518.98 | 41078200.65 | 20819318.33 | 47319156 | 44% |  |  | 2018-05-16 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-05-27 | 532677.78 |  | 62430196.76 | 41078200.65 | 21351996.11 | 47319156 | 45.12% |  |  | 2018-05-27 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-06-01 |  | 543492.04 | 62430196.76 | 41621692.69 | 20808504.07 | 47319156 | 43.97% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-07-01 |  | 140888.76 | 62430196.76 | 41762581.45 | 20667615.31 | 47319156 | 43.68% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-08-01 |  | 291983.76 | 62430196.76 | 42054565.21 | 20375631.55 | 47319156 | 43.06% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-08-14 | 854854.29 |  | 63285051.05 | 42054565.21 | 21230485.84 | 47319156 | 44.87% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-09-01 |  | 80626.53 | 63285051.05 | 42135191.74 | 21149859.31 | 47319156 | 44.7% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-10-01 |  | 204712.1 | 63285051.05 | 42339903.84 | 20945147.21 | 47319156 | 44.26% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-10-24 | 2299870.99 |  | 65584922.04 | 42339903.84 | 23245018.2 | 47319156 | 49.12% |  |  | 2018-10-24 | added cash in 3 |  |  | 2018
Levana UpTown Pkg 62 | 2018-11-01 |  | 863989.14 | 65584922.04 | 43203892.98 | 22381029.06 | 47319156 | 47.3% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2018-12-01 |  | 287870.08 | 65584922.04 | 43491763.06 | 22093158.98 | 47319156 | 46.69% |  |  |  | cash out both |  |  | 2018
Levana UpTown Pkg 62 | 2019-01-01 |  | 20590.24 | 65584922.04 | 43512353.3 | 22072568.74 | 47319156 | 46.65% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-01-09 | 931895.88 |  | 66516817.92 | 43512353.3 | 23004464.62 | 47319156 | 48.62% |  |  | 2019-01-09 | added cash in 3 |  |  | 2019
Levana UpTown Pkg 62 | 2019-01-20 | 148822.86 |  | 66665640.78 | 43512353.3 | 23153287.48 | 47319156 | 48.93% |  |  | 2019-01-20 | added cash in 3 |  |  | 2019
Levana UpTown Pkg 62 | 2019-02-01 |  | 353680.59 | 66665640.78 | 43866033.89 | 22799606.89 | 47319156 | 48.18% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-02-21 | 504922.64 |  | 67170563.42 | 43866033.89 | 23304529.53 | 47319156 | 49.25% |  |  | 2019-02-21 | added cash in 3 |  |  | 2019
Levana UpTown Pkg 62 | 2019-03-01 |  | 339484.21 | 67170563.42 | 44205518.1 | 22965045.32 | 47319156 | 48.53% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-04-01 |  | 85703.63 | 67170563.42 | 44291221.73 | 22879341.69 | 47319156 | 48.35% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-06-01 |  | 9327.89 | 67170563.42 | 44300549.62 | 22870013.8 | 47319156 | 48.33% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-06-10 | 419078.79 |  | 67589642.21 | 44300549.62 | 23289092.59 | 47319156 | 49.22% |  |  | 2019-06-10 | added cash in 3 |  |  | 2019
Levana UpTown Pkg 62 | 2019-07-01 |  | 18248.53 | 67589642.21 | 44318798.15 | 23270844.06 | 47319156 | 49.18% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-08-01 |  | 6039 | 67589642.21 | 44324837.15 | 23264805.06 | 47319156 | 49.17% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-09-01 |  | 9226.5 | 67589642.21 | 44334063.65 | 23255578.56 | 47319156 | 49.15% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-10-01 |  | 18248.53 | 67589642.21 | 44352312.18 | 23237330.03 | 47319156 | 49.11% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2019-11-25 | 864260.36 |  | 68453902.57 | 44352312.18 | 24101590.39 | 47319156 | 50.93% |  |  | 2019-11-25 | added cash in 3 |  |  | 2019
Levana UpTown Pkg 62 | 2019-12-01 |  | 9226.5 | 68453902.57 | 44361538.68 | 24092363.89 | 47319156 | 50.91% |  |  |  | cash out both |  |  | 2019
Levana UpTown Pkg 62 | 2020-01-01 |  | 18248.53 | 68453902.57 | 44379787.21 | 24074115.36 | 47319156 | 50.88% |  |  |  | cash out both |  |  | 2020
Levana UpTown Pkg 62 | 2020-06-01 |  | 124706.12 | 68453902.57 | 44504493.33 | 23949409.24 | 47319156 | 50.61% |  |  |  | cash out both |  |  | 2020
Levana UpTown Pkg 62 | 2020-09-01 |  | 273240.66 | 68453902.57 | 44777733.99 | 23676168.58 | 47319156 | 50.04% |  |  |  | cash out both |  |  | 2020
Levana UpTown Pkg 62 | 2020-10-01 |  | 104893.12 | 68453902.57 | 44882627.11 | 23571275.46 | 47319156 | 49.81% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Levana UpTown Pkg 62 | 2020-11-01 | 1416810.93 |  | 69870713.5 | 44882627.11 | 24988086.39 | 47319156 | 52.81% |  |  | 2020-11-01 | added 1 |  |  | 2020
Levana UpTown Pkg 62 | 2021-03-01 |  | 72815.8 | 69870713.5 | 44955442.91 | 24915270.59 | 47319156 | 52.65% |  |  |  | cash out both |  |  | 2021
1900
Kayan 110 | 2016-05-31 | 0 | 860500 | 0 | 860500 | -860500 | 1335232523 | -0.06445% |  | 4000000 | 2016-05-31 | original |  |  | 2016
Kayan 110 | 2016-06-30 | 55000000 | 210051 | 55000000 | 1070551 | 53929449 | 1335232523 | 4.039% |  | 16860000 | 2016-06-30 | original |  |  | 2016
Kayan 110 | 2016-07-31 | 0 | 5797210 | 55000000 | 6867761 | 48132239 | 1335232523 | 3.605% |  | 5014273 | 2016-07-31 | original |  |  | 2016
Kayan 110 | 2016-08-31 | 0 | 4223578 | 55000000 | 11091339 | 43908661 | 1335232523 | 3.288% |  | 14172854 | 2016-08-31 | original |  |  | 2016
Kayan 110 | 2016-09-30 | 25000000 | 6918725 | 80000000 | 18010064 | 61989936 | 1335232523 | 4.643% |  | 8448406 | 2016-09-30 | original |  |  | 2016
Kayan 110 | 2016-10-31 | 0 | 5761473 | 80000000 | 23771537 | 56228463 | 1335232523 | 4.211% |  | 12758335 | 2016-10-31 | original |  |  | 2016
Kayan 110 | 2016-11-30 | 0 | 11455502 | 80000000 | 35227039 | 44772961 | 1335232523 | 3.353% |  | 43227106 | 2016-11-30 | original |  |  | 2016
Kayan 110 | 2016-12-31 | 0 | 9154402 | 80000000 | 44381441 | 35618559 | 1335232523 | 2.668% |  | 12128868 | 2016-12-31 | original |  |  | 2016
Kayan 110 | 2017-01-31 | 0 | 11470298 | 80000000 | 55851739 | 24148261 | 1335232523 | 1.809% |  | 3742582 | 2017-01-31 | original |  |  | 2017
Kayan 110 | 2017-02-28 | 0 | 11527723 | 80000000 | 67379462 | 12620538 | 1335232523 | 0.9452% |  | 58697488 | 2017-02-28 | original |  |  | 2017
Kayan 110 | 2017-03-30 | 4140013 |  | 84140013 | 67379462 | 16760551 | 1335232523 | 1.255% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
Kayan 110 | 2017-03-31 | 23196662 | 13151769 | 107336675 | 80531231 | 26805444 | 1335232523 | 2.008% |  | 10879402 | 2017-03-31 | original |  |  | 2017
Kayan 110 | 2017-04-01 |  | 2760123.94 | 107336675 | 83291354.94 | 24045320.06 | 1335232523 | 1.801% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-04-01 | 50223564.95 |  | 157560239.95 | 83291354.94 | 74268885.01 | 1335232523 | 5.562% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
Kayan 110 | 2017-04-30 | 50223565 | 21904196 | 207783804.95 | 105195550.94 | 102588254.01 | 1335232523 | 7.683% |  | 26153462 | 2017-04-30 | original |  |  | 2017
Kayan 110 | 2017-05-01 |  | 2767223.3 | 207783804.95 | 107962774.24 | 99821030.71 | 1335232523 | 7.476% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-05-31 | 66017615 | 19731529 | 273801419.95 | 127694303.24 | 146107116.71 | 1335232523 | 10.94% |  | 24482093 | 2017-05-31 | original |  |  | 2017
Kayan 110 | 2017-05-31 | 6017614.8 |  | 279819034.75 | 127694303.24 | 152124731.51 | 1335232523 | 11.39% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
Kayan 110 | 2017-05-31 | 60000000 |  | 339819034.75 | 127694303.24 | 212124731.51 | 1335232523 | 15.89% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
Kayan 110 | 2017-06-01 |  | 5400829.3 | 339819034.75 | 133095132.54 | 206723902.21 | 1335232523 | 15.48% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-06-30 | 0 | 20675574 | 339819034.75 | 153770706.54 | 186048328.21 | 1335232523 | 13.93% |  | 15797320 | 2017-06-30 | original |  |  | 2017
Kayan 110 | 2017-07-01 |  | 6031755.6 | 339819034.75 | 159802462.14 | 180016572.61 | 1335232523 | 13.48% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-07-31 | 35643752 | 20810172 | 375462786.75 | 180612634.14 | 194850152.61 | 1335232523 | 14.59% |  | 47310652 | 2017-07-31 | original |  |  | 2017
Kayan 110 | 2017-07-31 | 35643751.5 |  | 411106538.25 | 180612634.14 | 230493904.11 | 1335232523 | 17.26% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
Kayan 110 | 2017-08-01 |  | 9695619.09 | 411106538.25 | 190308253.23 | 220798285.02 | 1335232523 | 16.54% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-08-31 | 60000000 | 28447976 | 471106538.25 | 218756229.23 | 252350309.02 | 1335232523 | 18.9% |  | 20808430 | 2017-08-31 | original |  |  | 2017
Kayan 110 | 2017-08-31 | 60000000 |  | 531106538.25 | 218756229.23 | 312350309.02 | 1335232523 | 23.39% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Kayan 110 | 2017-09-01 |  | 3770157.11 | 531106538.25 | 222526386.34 | 308580151.91 | 1335232523 | 23.11% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-09-30 | 0 | 15296273 | 531106538.25 | 237822659.34 | 293283878.91 | 1335232523 | 21.97% |  | 39607725 | 2017-09-30 | original |  |  | 2017
Kayan 110 | 2017-10-01 |  | 6868629.41 | 531106538.25 | 244691288.75 | 286415249.5 | 1335232523 | 21.45% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-10-31 | 0 | 25571562 | 531106538.25 | 270262850.75 | 260843687.5 | 1335232523 | 19.54% |  | 45731593 | 2017-10-31 | original |  |  | 2017
Kayan 110 | 2017-11-01 |  | 4876932.91 | 531106538.25 | 275139783.66 | 255966754.59 | 1335232523 | 19.17% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-11-30 | 10553942 | 18087855 | 541660480.25 | 293227638.66 | 248432841.59 | 1335232523 | 18.61% |  | 37795060 | 2017-11-30 | original |  |  | 2017
Kayan 110 | 2017-12-01 |  | 10751671.25 | 541660480.25 | 303979309.91 | 237681170.34 | 1335232523 | 17.8% |  |  |  | cash out both |  |  | 2017
Kayan 110 | 2017-12-31 | 0 | 34407143 | 541660480.25 | 338386452.91 | 203274027.34 | 1335232523 | 15.22% |  | 28053894 | 2017-12-31 | original |  |  | 2017
Kayan 110 | 2018-01-01 |  | 25008317.08 | 541660480.25 | 363394769.99 | 178265710.26 | 1335232523 | 13.35% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-02-01 |  | 21652799.5 | 541660480.25 | 385047569.49 | 156612910.76 | 1335232523 | 11.73% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-02-26 | 4294503.3 |  | 545954983.55 | 385047569.49 | 160907414.06 | 1335232523 | 12.05% |  |  | 2018-02-26 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-03-01 |  | 34450882.6 | 545954983.55 | 419498452.09 | 126456531.46 | 1335232523 | 9.471% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-03-11 | 37500000 |  | 583454983.55 | 419498452.09 | 163956531.46 | 1335232523 | 12.28% |  |  | 2018-03-11 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-03-12 | 15853592.25 |  | 599308575.8 | 419498452.09 | 179810123.71 | 1335232523 | 13.47% |  |  | 2018-03-12 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-04-01 |  | 23360245.25 | 599308575.8 | 442858697.34 | 156449878.46 | 1335232523 | 11.72% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-04-16 | 4403115 |  | 603711690.8 | 442858697.34 | 160852993.46 | 1335232523 | 12.05% |  |  | 2018-04-16 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-04-24 | 19389978.25 |  | 623101669.05 | 442858697.34 | 180242971.71 | 1335232523 | 13.5% |  |  | 2018-04-24 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-05-01 |  | 31285850.73 | 623101669.05 | 474144548.07 | 148957120.98 | 1335232523 | 11.16% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-05-08 | 11242619.75 |  | 634344288.8 | 474144548.07 | 160199740.73 | 1335232523 | 12% |  |  | 2018-05-08 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-06-01 |  | 22431807.59 | 634344288.8 | 496576355.66 | 137767933.14 | 1335232523 | 10.32% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-06-18 | 17600000 |  | 651944288.8 | 496576355.66 | 155367933.14 | 1335232523 | 11.64% |  |  | 2018-06-18 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-06-20 | 39352862.65 |  | 691297151.45 | 496576355.66 | 194720795.79 | 1335232523 | 14.58% |  |  | 2018-06-20 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-07-01 |  | 24210505.31 | 691297151.45 | 520786860.97 | 170510290.48 | 1335232523 | 12.77% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-07-19 | 11062482.8 |  | 702359634.25 | 520786860.97 | 181572773.28 | 1335232523 | 13.6% |  |  | 2018-07-19 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-08-01 |  | 18976705.83 | 702359634.25 | 539763566.8 | 162596067.45 | 1335232523 | 12.18% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-08-19 | 16500000 |  | 718859634.25 | 539763566.8 | 179096067.45 | 1335232523 | 13.41% |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-08-28 | 30076698.55 |  | 748936332.8 | 539763566.8 | 209172766 | 1335232523 | 15.67% |  |  | 2018-08-28 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-09-01 |  | 27537447.81 | 748936332.8 | 567301014.61 | 181635318.19 | 1335232523 | 13.6% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-09-27 | 66272397.35 |  | 815208730.15 | 567301014.61 | 247907715.54 | 1335232523 | 18.57% |  |  | 2018-09-27 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-10-01 |  | 38403899.85 | 815208730.15 | 605704914.46 | 209503815.69 | 1335232523 | 15.69% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-11-01 |  | 21658837.52 | 815208730.15 | 627363751.98 | 187844978.17 | 1335232523 | 14.07% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-12-01 |  | 23038899.73 | 815208730.15 | 650402651.71 | 164806078.44 | 1335232523 | 12.34% |  |  |  | cash out both |  |  | 2018
Kayan 110 | 2018-12-09 | 459255.1 |  | 815667985.25 | 650402651.71 | 165265333.54 | 1335232523 | 12.38% |  |  | 2018-12-09 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-12-17 | 39276155.35 |  | 854944140.6 | 650402651.71 | 204541488.89 | 1335232523 | 15.32% |  |  | 2018-12-17 | added cash in 3 |  |  | 2018
Kayan 110 | 2018-12-25 | 1539733.25 |  | 856483873.85 | 650402651.71 | 206081222.14 | 1335232523 | 15.43% |  |  | 2018-12-25 | added cash in 3 |  |  | 2018
Kayan 110 | 2019-01-01 |  | 19059546.97 | 856483873.85 | 669462198.68 | 187021675.17 | 1335232523 | 14.01% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-01-06 | 53206512.5 |  | 909690386.35 | 669462198.68 | 240228187.67 | 1335232523 | 17.99% |  |  | 2019-01-06 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-02-01 |  | 21848202.06 | 909690386.35 | 691310400.74 | 218379985.61 | 1335232523 | 16.36% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-02-28 | 87421678.5 |  | 997112064.85 | 691310400.74 | 305801664.11 | 1335232523 | 22.9% |  |  | 2019-02-28 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-03-01 |  | 29786647.74 | 997112064.85 | 721097048.48 | 276015016.37 | 1335232523 | 20.67% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-03-19 | 58725306.85 |  | 1055837371.7 | 721097048.48 | 334740323.22 | 1335232523 | 25.07% |  |  | 2019-03-19 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-03-28 | 15654597.1 |  | 1071491968.8 | 721097048.48 | 350394920.32 | 1335232523 | 26.24% |  |  | 2019-03-28 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-04-01 |  | 52408796.77 | 1071491968.8 | 773505845.25 | 297986123.55 | 1335232523 | 22.32% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-04-10 | 190000000 |  | 1261491968.8 | 773505845.25 | 487986123.55 | 1335232523 | 36.55% |  |  | 2019-04-10 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-04-23 | 20011341.75 |  | 1281503310.55 | 773505845.25 | 507997465.3 | 1335232523 | 38.05% |  |  | 2019-04-23 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-05-01 |  | 27228247.69 | 1281503310.55 | 800734092.94 | 480769217.61 | 1335232523 | 36.01% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-05-05 | 8928462.45 |  | 1290431773 | 800734092.94 | 489697680.06 | 1335232523 | 36.68% |  |  | 2019-05-05 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-06-01 |  | 18107906.56 | 1290431773 | 818841999.5 | 471589773.5 | 1335232523 | 35.32% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-07-01 |  | 57032978.96 | 1290431773 | 875874978.46 | 414556794.54 | 1335232523 | 31.05% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-08-01 |  | 24527556.08 | 1290431773 | 900402534.54 | 390029238.46 | 1335232523 | 29.21% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-09-01 |  | 16373062.61 | 1290431773 | 916775597.15 | 373656175.85 | 1335232523 | 27.98% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-10-01 |  | 17863882.64 | 1290431773 | 934639479.79 | 355792293.21 | 1335232523 | 26.65% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-10-03 | 11725207 |  | 1302156980 | 934639479.79 | 367517500.21 | 1335232523 | 27.52% |  |  | 2019-10-03 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-10-03 | 7715157 |  | 1309872137 | 934639479.79 | 375232657.21 | 1335232523 | 28.1% |  |  | 2019-10-03 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-10-03 | 1573927 |  | 1311446064 | 934639479.79 | 376806584.21 | 1335232523 | 28.22% |  |  | 2019-10-03 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-10-16 | 6945437 |  | 1318391501 | 934639479.79 | 383752021.21 | 1335232523 | 28.74% |  |  | 2019-10-16 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-10-20 | 1508357 |  | 1319899858 | 934639479.79 | 385260378.21 | 1335232523 | 28.85% |  |  | 2019-10-20 | added cash in 3 |  |  | 2019
Kayan 110 | 2019-11-01 |  | 37739785.37 | 1319899858 | 972379265.16 | 347520592.84 | 1335232523 | 26.03% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-12-01 |  | 20045230.27 | 1319899858 | 992424495.43 | 327475362.57 | 1335232523 | 24.53% |  |  |  | cash out both |  |  | 2019
Kayan 110 | 2019-12-23 | 2086567 |  | 1321986425 | 992424495.43 | 329561929.57 | 1335232523 | 24.68% |  |  | 2019-12-23 | added cash in 3 |  |  | 2019
Kayan 110 | 2020-01-01 |  | 36980646.2 | 1321986425 | 1029405141.63 | 292581283.37 | 1335232523 | 21.91% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-02-01 |  | 15033181.94 | 1321986425 | 1044438323.57 | 277548101.43 | 1335232523 | 20.79% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-03-01 |  | 10926610.62 | 1321986425 | 1055364934.19 | 266621490.81 | 1335232523 | 19.97% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-03-02 | 31120880 |  | 1353107305 | 1055364934.19 | 297742370.81 | 1335232523 | 22.3% |  |  | 2020-03-02 | added 1 |  |  | 2020
Kayan 110 | 2020-03-10 | 1825290 |  | 1354932595 | 1055364934.19 | 299567660.81 | 1335232523 | 22.44% |  |  | 2020-03-10 | added 1 |  |  | 2020
Kayan 110 | 2020-04-01 |  | 6381053.32 | 1354932595 | 1061745987.51 | 293186607.49 | 1335232523 | 21.96% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-05-01 |  | 8951560.13 | 1354932595 | 1070697547.64 | 284235047.36 | 1335232523 | 21.29% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-06-01 |  | 7469937.83 | 1354932595 | 1078167485.47 | 276765109.53 | 1335232523 | 20.73% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-06-23 | 95 |  | 1354932690 | 1078167485.47 | 276765204.53 | 1335232523 | 20.73% |  |  | 2020-06-23 | added 1 |  |  | 2020
Kayan 110 | 2020-06-25 | 95 |  | 1354932785 | 1078167485.47 | 276765299.53 | 1335232523 | 20.73% |  |  | 2020-06-25 | added 1 |  |  | 2020
Kayan 110 | 2020-06-29 | 477762.85 |  | 1355410547.85 | 1078167485.47 | 277243062.38 | 1335232523 | 20.76% |  |  | 2020-06-29 | added cash in 3 |  |  | 2020
Kayan 110 | 2020-07-01 |  | 6612714.38 | 1355410547.85 | 1084780199.85 | 270630348 | 1335232523 | 20.27% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-07-16 | 1325075 |  | 1356735622.85 | 1084780199.85 | 271955423 | 1335232523 | 20.37% |  |  | 2020-07-16 | added 1 |  |  | 2020
Kayan 110 | 2020-07-19 | 1325075 |  | 1358060697.85 | 1084780199.85 | 273280498 | 1335232523 | 20.47% |  |  | 2020-07-19 | added cash in 3 |  |  | 2020
Kayan 110 | 2020-08-01 |  | 4678863.35 | 1358060697.85 | 1089459063.2 | 268601634.65 | 1335232523 | 20.12% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-09-01 |  | 6073048.32 | 1358060697.85 | 1095532111.52 | 262528586.33 | 1335232523 | 19.66% |  |  |  | cash out both |  |  | 2020
Kayan 110 | 2020-09-09 | 12515545 |  | 1370576242.85 | 1095532111.52 | 275044131.33 | 1335232523 | 20.6% |  |  | 2020-09-09 | added 1 |  |  | 2020
Kayan 110 | 2020-09-09 | 9452905 |  | 1380029147.85 | 1095532111.52 | 284497036.33 | 1335232523 | 21.31% |  |  | 2020-09-09 | added 1 |  |  | 2020
Kayan 110 | 2020-09-09 | 572225 |  | 1380601372.85 | 1095532111.52 | 285069261.33 | 1335232523 | 21.35% |  |  | 2020-09-09 | added 1 |  |  | 2020
Kayan 110 | 2020-10-01 |  | 6514406.21 | 1380601372.85 | 1102046517.73 | 278554855.12 | 1335232523 | 20.86% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Kayan 110 | 2020-11-01 |  | 4208756.9 | 1380601372.85 | 1106255274.63 | 274346098.22 | 1335232523 | 20.55% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Kayan 110 | 2020-12-01 |  | 3300995.03 | 1380601372.85 | 1109556269.66 | 271045103.19 | 1335232523 | 20.3% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Kayan 110 | 2021-01-01 |  | 3966606.84 | 1380601372.85 | 1113522876.5 | 267078496.35 | 1335232523 | 20% |  |  |  | cash out both |  |  | 2021
Kayan 110 | 2021-01-06 | 1712930 |  | 1382314302.85 | 1113522876.5 | 268791426.35 | 1335232523 | 20.13% |  |  | 2021-01-06 | added 1 |  |  | 2021
Kayan 110 | 2021-01-24 | 20582125 |  | 1402896427.85 | 1113522876.5 | 289373551.35 | 1335232523 | 21.67% |  |  | 2021-01-24 | added 1 |  |  | 2021
Kayan 110 | 2021-02-01 |  | 2340657.04 | 1402896427.85 | 1115863533.54 | 287032894.31 | 1335232523 | 21.5% |  |  |  | cash out both |  |  | 2021
Kayan 110 | 2021-03-01 |  | 2825278.74 | 1402896427.85 | 1118688812.28 | 284207615.57 | 1335232523 | 21.29% |  |  |  | cash out both |  |  | 2021
1900
El Amal Bridge | 2017-08-01 |  | 1943 | 0 | 1943 | -1943 | 28943151 | -0.006713% |  |  |  | cash out both |  |  | 2017
El Amal Bridge | 2017-09-01 |  | 1934 | 0 | 3877 | -3877 | 28943151 | -0.0134% |  |  |  | cash out both |  |  | 2017
El Amal Bridge | 2017-10-01 |  | 4495.5 | 0 | 8372.5 | -8372.5 | 28943151 | -0.02893% |  |  |  | cash out both |  |  | 2017
El Amal Bridge | 2018-01-01 |  | 300940 | 0 | 309312.5 | -309312.5 | 28943151 | -1.069% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-02-01 |  | 121647.61 | 0 | 430960.11 | -430960.11 | 28943151 | -1.489% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-03-01 |  | 245185.34 | 0 | 676145.45 | -676145.45 | 28943151 | -2.336% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-05-01 |  | 40404.25 | 0 | 716549.7 | -716549.7 | 28943151 | -2.476% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-05-22 | 942917.55 |  | 942917.55 | 716549.7 | 226367.85 | 28943151 | 0.7821% |  |  | 2018-05-22 | added cash in 3 |  |  | 2018
El Amal Bridge | 2018-05-27 | 6785022.95 |  | 7727940.5 | 716549.7 | 7011390.8 | 28943151 | 24.22% |  |  | 2018-05-27 | added cash in 3 |  |  | 2018
El Amal Bridge | 2018-06-01 |  | 57046.39 | 7727940.5 | 773596.09 | 6954344.41 | 28943151 | 24.03% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-08-01 |  | 21947.08 | 7727940.5 | 795543.17 | 6932397.33 | 28943151 | 23.95% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-09-01 |  | 6831.85 | 7727940.5 | 802375.02 | 6925565.48 | 28943151 | 23.93% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-10-01 |  | 128395.11 | 7727940.5 | 930770.13 | 6797170.37 | 28943151 | 23.48% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-11-01 |  | 16707.52 | 7727940.5 | 947477.65 | 6780462.85 | 28943151 | 23.43% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2018-12-01 |  | 10822.45 | 7727940.5 | 958300.1 | 6769640.4 | 28943151 | 23.39% |  |  |  | cash out both |  |  | 2018
El Amal Bridge | 2019-01-01 |  | 15189.34 | 7727940.5 | 973489.44 | 6754451.06 | 28943151 | 23.34% |  |  |  | cash out both |  |  | 2019
El Amal Bridge | 2019-01-27 | 1178671.7 |  | 8906612.2 | 973489.44 | 7933122.76 | 28943151 | 27.41% |  |  | 2019-01-27 | added cash in 3 |  |  | 2019
El Amal Bridge | 2019-02-01 |  | 10224.64 | 8906612.2 | 983714.08 | 7922898.12 | 28943151 | 27.37% |  |  |  | cash out both |  |  | 2019
El Amal Bridge | 2019-09-01 |  | 1923.82 | 8906612.2 | 985637.9 | 7920974.3 | 28943151 | 27.37% |  |  |  | cash out both |  |  | 2019
El Amal Bridge | 2019-12-01 |  | 2622372.03 | 8906612.2 | 3608009.93 | 5298602.27 | 28943151 | 18.31% |  |  |  | cash out both |  |  | 2019
1900
Bani Suif Cement | 2016-07-31 | 0 | 164006 | 0 | 164006 | -164006 | 274663700 | -0.05971% |  | 0 | 2016-07-31 | original |  |  | 2016
Bani Suif Cement | 2016-08-31 | 31008558 | 678639 | 31008558 | 842645 | 30165913 | 274663700 | 10.98% |  | 0 | 2016-08-31 | original |  |  | 2016
Bani Suif Cement | 2016-09-30 | 0 | 7751031 | 31008558 | 8593676 | 22414882 | 274663700 | 8.161% |  | 3315887 | 2016-09-30 | original |  |  | 2016
Bani Suif Cement | 2016-10-31 | 0 | 13725760 | 31008558 | 22319436 | 8689122 | 274663700 | 3.164% |  | 15479865 | 2016-10-31 | original |  |  | 2016
Bani Suif Cement | 2016-11-30 | 2431481 | 19985096 | 33440039 | 42304532 | -8864493 | 274663700 | -3.227% |  | 19641409 | 2016-11-30 | original |  |  | 2016
Bani Suif Cement | 2016-12-31 | 11664033 | 12775230 | 45104072 | 55079762 | -9975690 | 274663700 | -3.632% |  | 19382634 | 2016-12-31 | original |  |  | 2016
Bani Suif Cement | 2017-01-31 | 30215733 | 9325965 | 75319805 | 64405727 | 10914078 | 274663700 | 3.974% |  | 29411034 | 2017-01-31 | original |  |  | 2017
Bani Suif Cement | 2017-02-28 | 0 | 22437549 | 75319805 | 86843276 | -11523471 | 274663700 | -4.195% |  | 20410494 | 2017-02-28 | original |  |  | 2017
Bani Suif Cement | 2017-03-31 | 23184069 | 23359182 | 98503874 | 110202458 | -11698584 | 274663700 | -4.259% |  | 30054634 | 2017-03-31 | original |  |  | 2017
Bani Suif Cement | 2017-04-30 | 16078329 | 15214946 | 114582203 | 125417404 | -10835201 | 274663700 | -3.945% |  | 17833591 | 2017-04-30 | original |  |  | 2017
Bani Suif Cement | 2017-05-31 | 36976159 | 23863782 | 151558362 | 149281186 | 2277176 | 274663700 | 0.8291% |  | 15920715 | 2017-05-31 | original |  |  | 2017
Bani Suif Cement | 2017-06-30 | 12546064 | 26492361 | 164104426 | 175773547 | -11669121 | 274663700 | -4.249% |  | 15670937 | 2017-06-30 | original |  |  | 2017
Bani Suif Cement | 2017-07-31 | 5224000 | 18368515 | 169328426 | 194142062 | -24813636 | 274663700 | -9.034% |  | 15715649 | 2017-07-31 | original |  |  | 2017
Bani Suif Cement | 2017-08-31 | 8112852 | 14863076 | 177441278 | 209005138 | -31563860 | 274663700 | -11.49% |  | 20878242 | 2017-08-31 | original |  |  | 2017
Bani Suif Cement | 2017-09-30 | 17115970 | 8220088 | 194557248 | 217225226 | -22667978 | 274663700 | -8.253% |  | 6421252 | 2017-09-30 | original |  |  | 2017
Bani Suif Cement | 2017-10-31 | 15460620 | 11297355 | 210017868 | 228522581 | -18504713 | 274663700 | -6.737% |  | 8583366 | 2017-10-31 | original |  |  | 2017
Bani Suif Cement | 2017-11-30 | 7309725 | 11909214 | 217327593 | 240431795 | -23104202 | 274663700 | -8.412% |  | 6621785 | 2017-11-30 | original |  |  | 2017
Bani Suif Cement | 2017-12-31 | 6696657 | 7785865 | 224024250 | 248217660 | -24193410 | 274663700 | -8.808% |  | 6642565 | 2017-12-31 | original |  |  | 2017
1900
New Giza Wall | 2017-06-30 | 527488.29 |  | 527488.29 | 0 | 527488.29 | 2648340.9749 | 19.92% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
1900
Tamey El Amdid Mansora Power Station | 2016-06-30 | 14475149 | 0 | 14475149 | 0 | 14475149 | 114399640 | 12.65% |  | 0 | 2016-06-30 | original |  |  | 2016
Tamey El Amdid Mansora Power Station | 2017-01-31 | 0 | 33682 | 14475149 | 33682 | 14441467 | 114399640 | 12.62% |  | 0 | 2017-01-31 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-02-28 | 0 | 120088 | 14475149 | 153770 | 14321379 | 114399640 | 12.52% |  | 0 | 2017-02-28 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-03-31 | 0 | 161095 | 14475149 | 314865 | 14160284 | 114399640 | 12.38% |  | 0 | 2017-03-31 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-04-30 | 0 | 34773 | 14475149 | 349638 | 14125511 | 114399640 | 12.35% |  | 0 | 2017-04-30 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-05-31 | 0 | 81695 | 14475149 | 431333 | 14043816 | 114399640 | 12.28% |  | 0 | 2017-05-31 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-06-30 | 0 | 100779 | 14475149 | 532112 | 13943037 | 114399640 | 12.19% |  | 0 | 2017-06-30 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-07-01 |  | 35696.61 | 14475149 | 567808.61 | 13907340.39 | 114399640 | 12.16% |  |  |  | cash out both |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-07-31 | 0 | 57578 | 14475149 | 625386.61 | 13849762.39 | 114399640 | 12.11% |  | 0 | 2017-07-31 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-08-31 | 0 | 274220 | 14475149 | 899606.61 | 13575542.39 | 114399640 | 11.87% |  | 0 | 2017-08-31 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-09-01 |  | 96.42 | 14475149 | 899703.03 | 13575445.97 | 114399640 | 11.87% |  |  |  | cash out both |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-09-30 | 0 | 98236 | 14475149 | 997939.03 | 13477209.97 | 114399640 | 11.78% |  | 0 | 2017-09-30 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-10-01 |  | 65376.58 | 14475149 | 1063315.61 | 13411833.39 | 114399640 | 11.72% |  |  |  | cash out both |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-10-31 | 0 | 551574 | 14475149 | 1614889.61 | 12860259.39 | 114399640 | 11.24% |  | 0 | 2017-10-31 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-11-01 |  | 204621.09 | 14475149 | 1819510.7 | 12655638.3 | 114399640 | 11.06% |  |  |  | cash out both |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-11-30 | 0 | 2333593 | 14475149 | 4153103.7 | 10322045.3 | 114399640 | 9.023% |  | 0 | 2017-11-30 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-12-01 |  | 190629.73 | 14475149 | 4343733.43 | 10131415.57 | 114399640 | 8.856% |  |  |  | cash out both |  |  | 2017
Tamey El Amdid Mansora Power Station | 2017-12-31 | 0 | 5192267 | 14475149 | 9536000.43 | 4939148.57 | 114399640 | 4.317% |  | 7657332 | 2017-12-31 | original |  |  | 2017
Tamey El Amdid Mansora Power Station | 2018-01-01 |  | 2162233.84 | 14475149 | 11698234.27 | 2776914.73 | 114399640 | 2.427% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-02-01 |  | 3362348.64 | 14475149 | 15060582.91 | -585433.91 | 114399640 | -0.5117% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-03-01 |  | 2473988.66 | 14475149 | 17534571.57 | -3059422.57 | 114399640 | -2.674% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-03-28 | 5704185.9 |  | 20179334.9 | 17534571.57 | 2644763.33 | 114399640 | 2.312% |  |  | 2018-03-28 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-04-01 |  | 9368200.33 | 20179334.9 | 26902771.9 | -6723437 | 114399640 | -5.877% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-04-16 | 4460637.4 |  | 24639972.3 | 26902771.9 | -2262799.6 | 114399640 | -1.978% |  |  | 2018-04-16 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-05-01 |  | 5326188.32 | 24639972.3 | 32228960.22 | -7588987.92 | 114399640 | -6.634% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-05-20 | 2844752.9 |  | 27484725.2 | 32228960.22 | -4744235.02 | 114399640 | -4.147% |  |  | 2018-05-20 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-06-01 |  | 5838925.13 | 27484725.2 | 38067885.35 | -10583160.15 | 114399640 | -9.251% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-06-10 | 2454573.85 |  | 29939299.05 | 38067885.35 | -8128586.3 | 114399640 | -7.105% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-07-01 |  | 5542866.76 | 29939299.05 | 43610752.11 | -13671453.06 | 114399640 | -11.95% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-07-31 | 3862350.4 |  | 33801649.45 | 43610752.11 | -9809102.66 | 114399640 | -8.574% |  |  | 2018-07-31 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-08-01 |  | 2639855.04 | 33801649.45 | 46250607.15 | -12448957.7 | 114399640 | -10.88% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-09-01 |  | 3145703.33 | 33801649.45 | 49396310.48 | -15594661.03 | 114399640 | -13.63% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-09-17 | 157932.21 |  | 33959581.66 | 49396310.48 | -15436728.82 | 114399640 | -13.49% |  |  | 2018-09-17 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-10-01 |  | 5410418.1 | 33959581.66 | 54806728.58 | -20847146.92 | 114399640 | -18.22% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-10-08 | 3204837.55 |  | 37164419.21 | 54806728.58 | -17642309.37 | 114399640 | -15.42% |  |  | 2018-10-08 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-11-01 |  | 6197456.11 | 37164419.21 | 61004184.69 | -23839765.48 | 114399640 | -20.84% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-11-18 | 6303674.55 |  | 43468093.76 | 61004184.69 | -17536090.93 | 114399640 | -15.33% |  |  | 2018-11-18 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-12-01 |  | 3733641.57 | 43468093.76 | 64737826.26 | -21269732.5 | 114399640 | -18.59% |  |  |  | cash out both |  |  | 2018
Tamey El Amdid Mansora Power Station | 2018-12-19 | 2397298.02 |  | 45865391.78 | 64737826.26 | -18872434.48 | 114399640 | -16.5% |  |  | 2018-12-19 | added cash in 3 |  |  | 2018
Tamey El Amdid Mansora Power Station | 2019-01-01 |  | 3936073.56 | 45865391.78 | 68673899.82 | -22808508.04 | 114399640 | -19.94% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-01-09 | 7786242.65 |  | 53651634.43 | 68673899.82 | -15022265.39 | 114399640 | -13.13% |  |  | 2019-01-09 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-01-17 | 8290245.2 |  | 61941879.63 | 68673899.82 | -6732020.19 | 114399640 | -5.885% |  |  | 2019-01-17 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-02-01 |  | 2587393.25 | 61941879.63 | 71261293.07 | -9319413.44 | 114399640 | -8.146% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-02-07 | 646885.25 |  | 62588764.88 | 71261293.07 | -8672528.19 | 114399640 | -7.581% |  |  | 2019-02-07 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-02-14 | 4723641.55 |  | 67312406.43 | 71261293.07 | -3948886.64 | 114399640 | -3.452% |  |  | 2019-02-14 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-02-27 | 1406345.3 |  | 68718751.73 | 71261293.07 | -2542541.34 | 114399640 | -2.223% |  |  | 2019-02-27 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-03-01 |  | 3256717.88 | 68718751.73 | 74518010.95 | -5799259.22 | 114399640 | -5.069% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-03-26 | 572427.4 |  | 69291179.13 | 74518010.95 | -5226831.82 | 114399640 | -4.569% |  |  | 2019-03-26 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-04-01 |  | 2818936.01 | 69291179.13 | 77336946.96 | -8045767.83 | 114399640 | -7.033% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-04-15 | 4378250.65 |  | 73669429.78 | 77336946.96 | -3667517.18 | 114399640 | -3.206% |  |  | 2019-04-15 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-04-15 | 2605118.8 |  | 76274548.58 | 77336946.96 | -1062398.38 | 114399640 | -0.9287% |  |  | 2019-04-15 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-04-18 | 1688733.85 |  | 77963282.43 | 77336946.96 | 626335.47 | 114399640 | 0.5475% |  |  | 2019-04-18 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-05-01 |  | 2782141.63 | 77963282.43 | 80119088.59 | -2155806.16 | 114399640 | -1.884% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-05-30 | 3212556.35 |  | 81175838.78 | 80119088.59 | 1056750.19 | 114399640 | 0.9237% |  |  | 2019-05-30 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-06-01 |  | 1362961.26 | 81175838.78 | 81482049.85 | -306211.07 | 114399640 | -0.2677% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-06-26 | 673869.4 |  | 81849708.18 | 81482049.85 | 367658.33 | 114399640 | 0.3214% |  |  | 2019-06-26 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-07-01 |  | 992471.64 | 81849708.18 | 82474521.49 | -624813.31 | 114399640 | -0.5462% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-08-01 |  | 2504381.49 | 81849708.18 | 84978902.98 | -3129194.8 | 114399640 | -2.735% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-08-05 | 2002680.05 |  | 83852388.23 | 84978902.98 | -1126514.75 | 114399640 | -0.9847% |  |  | 2019-08-05 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-09-01 |  | 712492.1 | 83852388.23 | 85691395.08 | -1839006.85 | 114399640 | -1.608% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-09-11 | 1624563.45 |  | 85476951.68 | 85691395.08 | -214443.4 | 114399640 | -0.1875% |  |  | 2019-09-11 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-09-17 | 2141987.65 |  | 87618939.33 | 85691395.08 | 1927544.25 | 114399640 | 1.685% |  |  | 2019-09-17 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-10-01 |  | 384474.63 | 87618939.33 | 86075869.71 | 1543069.62 | 114399640 | 1.349% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-10-09 | 453949.5 |  | 88072888.83 | 86075869.71 | 1997019.12 | 114399640 | 1.746% |  |  | 2019-10-09 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-10-20 | 1850140.05 |  | 89923028.88 | 86075869.71 | 3847159.17 | 114399640 | 3.363% |  |  | 2019-10-20 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-11-01 |  | 400815.96 | 89923028.88 | 86476685.67 | 3446343.21 | 114399640 | 3.013% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-12-01 |  | 8203862.87 | 89923028.88 | 94680548.54 | -4757519.66 | 114399640 | -4.159% |  |  |  | cash out both |  |  | 2019
Tamey El Amdid Mansora Power Station | 2019-12-30 | 88401.76 |  | 90011430.64 | 94680548.54 | -4669117.9 | 114399640 | -4.081% |  |  | 2019-12-30 | added cash in 3 |  |  | 2019
Tamey El Amdid Mansora Power Station | 2020-01-01 |  | 340616.99 | 90011430.64 | 95021165.53 | -5009734.89 | 114399640 | -4.379% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-01-14 | 80060.48 |  | 90091491.12 | 95021165.53 | -4929674.41 | 114399640 | -4.309% |  |  | 2020-01-14 | added 1 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-01-22 | 234715.6 |  | 90326206.72 | 95021165.53 | -4694958.81 | 114399640 | -4.104% |  |  | 2020-01-22 | added 1 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-02-01 |  | 724431.47 | 90326206.72 | 95745597 | -5419390.28 | 114399640 | -4.737% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-02-20 | 4999415.55 |  | 95325622.27 | 95745597 | -419974.73 | 114399640 | -0.3671% |  |  | 2020-02-20 | added 1 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-02-23 | 4999415.55 |  | 100325037.82 | 95745597 | 4579440.82 | 114399640 | 4.003% |  |  | 2020-02-23 | added cash in 3 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-03-01 |  | 131775.99 | 100325037.82 | 95877372.99 | 4447664.83 | 114399640 | 3.888% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-04-01 |  | 60503.26 | 100325037.82 | 95937876.25 | 4387161.57 | 114399640 | 3.835% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-05-01 |  | 72160.25 | 100325037.82 | 96010036.5 | 4315001.32 | 114399640 | 3.772% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-06-01 |  | 107753.46 | 100325037.82 | 96117789.96 | 4207247.86 | 114399640 | 3.678% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-07-01 |  | 201917.9 | 100325037.82 | 96319707.86 | 4005329.96 | 114399640 | 3.501% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-07-27 | 35903.65 |  | 100360941.47 | 96319707.86 | 4041233.61 | 114399640 | 3.533% |  |  | 2020-07-27 | added cash in 3 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-07-28 | 35903.65 |  | 100396845.12 | 96319707.86 | 4077137.26 | 114399640 | 3.564% |  |  | 2020-07-28 | added 1 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-08-01 |  | 45588.61 | 100396845.12 | 96365296.47 | 4031548.65 | 114399640 | 3.524% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-09-01 |  | 78180.83 | 100396845.12 | 96443477.3 | 3953367.82 | 114399640 | 3.456% |  |  |  | cash out both |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-09-27 | 71764 |  | 100468609.12 | 96443477.3 | 4025131.82 | 114399640 | 3.518% |  |  | 2020-09-27 | added 1 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-09-28 | 71764 |  | 100540373.12 | 96443477.3 | 4096895.82 | 114399640 | 3.581% |  |  | 2020-09-28 | added cash in 3 |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-10-01 |  | 19606.21 | 100540373.12 | 96463083.51 | 4077289.61 | 114399640 | 3.564% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-11-01 |  | 13480.37 | 100540373.12 | 96476563.88 | 4063809.24 | 114399640 | 3.552% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Tamey El Amdid Mansora Power Station | 2020-12-01 |  | 23808.25 | 100540373.12 | 96500372.13 | 4040000.99 | 114399640 | 3.531% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Tamey El Amdid Mansora Power Station | 2021-01-01 |  | 58081.02 | 100540373.12 | 96558453.15 | 3981919.97 | 114399640 | 3.481% |  |  |  | cash out both |  |  | 2021
Tamey El Amdid Mansora Power Station | 2021-02-01 |  | 62535 | 100540373.12 | 96620988.15 | 3919384.97 | 114399640 | 3.426% |  |  |  | cash out both |  |  | 2021
Tamey El Amdid Mansora Power Station | 2021-03-01 |  | 432315.18 | 100540373.12 | 97053303.33 | 3487069.79 | 114399640 | 3.048% |  |  |  | cash out both |  |  | 2021
1900
Ismailia Substation 500-220 | 2017-06-01 |  | 26772.48 | 0 | 26772.48 | -26772.48 | 109399640 | -0.02447% |  |  |  | cash out both |  |  | 2017
Ismailia Substation 500-220 | 2017-06-30 | 0 | 13841 | 0 | 40613.48 | -40613.48 | 109399640 | -0.03712% |  | 0 | 2017-06-30 | original |  |  | 2017
Ismailia Substation 500-220 | 2017-07-31 | 0 | 142795 | 0 | 183408.48 | -183408.48 | 109399640 | -0.1676% |  | 0 | 2017-07-31 | original |  |  | 2017
Ismailia Substation 500-220 | 2017-08-01 |  | 177059.13 | 0 | 360467.61 | -360467.61 | 109399640 | -0.3295% |  |  |  | cash out both |  |  | 2017
Ismailia Substation 500-220 | 2017-08-31 | 0 | 302595 | 0 | 663062.61 | -663062.61 | 109399640 | -0.6061% |  | 0 | 2017-08-31 | original |  |  | 2017
Ismailia Substation 500-220 | 2017-09-01 |  | 146162.02 | 0 | 809224.63 | -809224.63 | 109399640 | -0.7397% |  |  |  | cash out both |  |  | 2017
Ismailia Substation 500-220 | 2017-09-30 | 0 | 602697 | 0 | 1411921.63 | -1411921.63 | 109399640 | -1.291% |  | 5586802 | 2017-09-30 | original |  |  | 2017
Ismailia Substation 500-220 | 2017-10-01 |  | 167815.09 | 0 | 1579736.72 | -1579736.72 | 109399640 | -1.444% |  |  |  | cash out both |  |  | 2017
Ismailia Substation 500-220 | 2017-10-31 | 0 | 6243354 | 0 | 7823090.72 | -7823090.72 | 109399640 | -7.151% |  | 4449390 | 2017-10-31 | original |  |  | 2017
Ismailia Substation 500-220 | 2017-11-01 |  | 1574081.47 | 0 | 9397172.19 | -9397172.19 | 109399640 | -8.59% |  |  |  | cash out both |  |  | 2017
Ismailia Substation 500-220 | 2017-11-30 | 4159164 | 5101692 | 4159164 | 14498864.19 | -10339700.19 | 109399640 | -9.451% |  | 5141666 | 2017-11-30 | original |  |  | 2017
Ismailia Substation 500-220 | 2017-12-01 |  | 818944.55 | 4159164 | 15317808.74 | -11158644.74 | 109399640 | -10.2% |  |  |  | cash out both |  |  | 2017
Ismailia Substation 500-220 | 2017-12-31 | 0 | 10094912 | 4159164 | 25412720.74 | -21253556.74 | 109399640 | -19.43% |  | 5057617 | 2017-12-31 | original |  |  | 2017
Ismailia Substation 500-220 | 2018-01-01 |  | 3740908.13 | 4159164 | 29153628.87 | -24994464.87 | 109399640 | -22.85% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-01-30 | 3314345.55 |  | 7473509.55 | 29153628.87 | -21680119.32 | 109399640 | -19.82% |  |  | 2018-01-30 | added cash in 3 |  |  | 2018
Ismailia Substation 500-220 | 2018-02-01 |  | 1664984.35 | 7473509.55 | 30818613.22 | -23345103.67 | 109399640 | -21.34% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-03-01 |  | 880801.75 | 7473509.55 | 31699414.97 | -24225905.42 | 109399640 | -22.14% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-03-01 | 30335 |  | 7503844.55 | 31699414.97 | -24195570.42 | 109399640 | -22.12% |  |  | 2018-03-01 | added cash in 3 |  |  | 2018
Ismailia Substation 500-220 | 2018-03-08 | 7597909.44 |  | 15101753.99 | 31699414.97 | -16597660.98 | 109399640 | -15.17% |  |  | 2018-03-08 | added cash in 3 |  |  | 2018
Ismailia Substation 500-220 | 2018-04-01 |  | 786248.12 | 15101753.99 | 32485663.09 | -17383909.1 | 109399640 | -15.89% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-05-01 |  | 803021.13 | 15101753.99 | 33288684.22 | -18186930.23 | 109399640 | -16.62% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-06-01 |  | 1424251.5 | 15101753.99 | 34712935.72 | -19611181.73 | 109399640 | -17.93% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-06-10 | 4195153.81 |  | 19296907.8 | 34712935.72 | -15416027.92 | 109399640 | -14.09% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Ismailia Substation 500-220 | 2018-07-01 |  | 1819574.82 | 19296907.8 | 36532510.54 | -17235602.74 | 109399640 | -15.75% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-08-01 |  | 2211651.52 | 19296907.8 | 38744162.06 | -19447254.26 | 109399640 | -17.78% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-09-01 |  | 2432926.04 | 19296907.8 | 41177088.1 | -21880180.3 | 109399640 | -20% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-10-01 |  | 3566344.41 | 19296907.8 | 44743432.51 | -25446524.71 | 109399640 | -23.26% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-11-01 |  | 3065805.18 | 19296907.8 | 47809237.69 | -28512329.89 | 109399640 | -26.06% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2018-11-25 | 7250071.15 |  | 26546978.95 | 47809237.69 | -21262258.74 | 109399640 | -19.44% |  |  | 2018-11-25 | added cash in 3 |  |  | 2018
Ismailia Substation 500-220 | 2018-12-01 |  | 3579926.76 | 26546978.95 | 51389164.45 | -24842185.5 | 109399640 | -22.71% |  |  |  | cash out both |  |  | 2018
Ismailia Substation 500-220 | 2019-01-01 |  | 4796272.16 | 26546978.95 | 56185436.61 | -29638457.66 | 109399640 | -27.09% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-01-30 | 5137574.8 |  | 31684553.75 | 56185436.61 | -24500882.86 | 109399640 | -22.4% |  |  | 2019-01-30 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-02-01 |  | 2376618.42 | 31684553.75 | 58562055.03 | -26877501.28 | 109399640 | -24.57% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-02-28 | 12961 |  | 31697514.75 | 58562055.03 | -26864540.28 | 109399640 | -24.56% |  |  | 2019-02-28 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-03-01 |  | 3278687.38 | 31697514.75 | 61840742.41 | -30143227.66 | 109399640 | -27.55% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-04-01 |  | 2492659.28 | 31697514.75 | 64333401.69 | -32635886.94 | 109399640 | -29.83% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-04-18 | 1044033.95 |  | 32741548.7 | 64333401.69 | -31591852.99 | 109399640 | -28.88% |  |  | 2019-04-18 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-05-01 |  | 2545880.7 | 32741548.7 | 66879282.39 | -34137733.69 | 109399640 | -31.2% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-05-16 | 5974553.29 |  | 38716101.99 | 66879282.39 | -28163180.4 | 109399640 | -25.74% |  |  | 2019-05-16 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-06-01 |  | 1481896.28 | 38716101.99 | 68361178.67 | -29645076.68 | 109399640 | -27.1% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-06-26 | 1671263.87 |  | 40387365.86 | 68361178.67 | -27973812.81 | 109399640 | -25.57% |  |  | 2019-06-26 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-06-26 | 16949.28 |  | 40404315.14 | 68361178.67 | -27956863.53 | 109399640 | -25.55% |  |  | 2019-06-26 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-07-01 |  | 2079569.59 | 40404315.14 | 70440748.26 | -30036433.12 | 109399640 | -27.46% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-07-10 | 4174473.87 |  | 44578789.01 | 70440748.26 | -25861959.25 | 109399640 | -23.64% |  |  | 2019-07-10 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-08-01 |  | 3237678.45 | 44578789.01 | 73678426.71 | -29099637.7 | 109399640 | -26.6% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-08-05 | 1266190.73 |  | 45844979.74 | 73678426.71 | -27833446.97 | 109399640 | -25.44% |  |  | 2019-08-05 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-09-01 |  | 5319231.27 | 45844979.74 | 78997657.98 | -33152678.24 | 109399640 | -30.3% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-09-17 | 2390185.26 |  | 48235165 | 78997657.98 | -30762492.98 | 109399640 | -28.12% |  |  | 2019-09-17 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-09-25 | 2850932.8 |  | 51086097.8 | 78997657.98 | -27911560.18 | 109399640 | -25.51% |  |  | 2019-09-25 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-10-01 |  | 867863.24 | 51086097.8 | 79865521.22 | -28779423.42 | 109399640 | -26.31% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-10-13 | 2715718.48 |  | 53801816.28 | 79865521.22 | -26063704.94 | 109399640 | -23.82% |  |  | 2019-10-13 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-10-20 | 141100.77 |  | 53942917.05 | 79865521.22 | -25922604.17 | 109399640 | -23.7% |  |  | 2019-10-20 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-11-01 |  | 1831906.83 | 53942917.05 | 81697428.05 | -27754511 | 109399640 | -25.37% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-12-01 |  | 3641609.19 | 53942917.05 | 85339037.24 | -31396120.19 | 109399640 | -28.7% |  |  |  | cash out both |  |  | 2019
Ismailia Substation 500-220 | 2019-12-09 | 981.6 |  | 53943898.65 | 85339037.24 | -31395138.59 | 109399640 | -28.7% |  |  | 2019-12-09 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2019-12-09 | 534207.6 |  | 54478106.25 | 85339037.24 | -30860930.99 | 109399640 | -28.21% |  |  | 2019-12-09 | added cash in 3 |  |  | 2019
Ismailia Substation 500-220 | 2020-01-01 |  | 288845.05 | 54478106.25 | 85627882.29 | -31149776.04 | 109399640 | -28.47% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-01-14 | 4224095.51 |  | 58702201.76 | 85627882.29 | -26925680.53 | 109399640 | -24.61% |  |  | 2020-01-14 | added 1 |  |  | 2020
Ismailia Substation 500-220 | 2020-01-22 | 6680787.75 |  | 65382989.51 | 85627882.29 | -20244892.78 | 109399640 | -18.51% |  |  | 2020-01-22 | added 1 |  |  | 2020
Ismailia Substation 500-220 | 2020-02-01 |  | 1177692.67 | 65382989.51 | 86805574.96 | -21422585.45 | 109399640 | -19.58% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-03-01 |  | 470499.49 | 65382989.51 | 87276074.45 | -21893084.94 | 109399640 | -20.01% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-03-10 | 1170773.36 |  | 66553762.87 | 87276074.45 | -20722311.58 | 109399640 | -18.94% |  |  | 2020-03-10 | added 1 |  |  | 2020
Ismailia Substation 500-220 | 2020-04-01 |  | 614268.8 | 66553762.87 | 87890343.25 | -21336580.38 | 109399640 | -19.5% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-05-01 |  | 366775.42 | 66553762.87 | 88257118.67 | -21703355.8 | 109399640 | -19.84% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-06-01 |  | 745395.3 | 66553762.87 | 89002513.97 | -22448751.1 | 109399640 | -20.52% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-07-01 |  | 341157.31 | 66553762.87 | 89343671.28 | -22789908.41 | 109399640 | -20.83% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-07-27 | 1446764.54 |  | 68000527.41 | 89343671.28 | -21343143.87 | 109399640 | -19.51% |  |  | 2020-07-27 | added cash in 3 |  |  | 2020
Ismailia Substation 500-220 | 2020-07-28 | 1446764.54 |  | 69447291.95 | 89343671.28 | -19896379.33 | 109399640 | -18.19% |  |  | 2020-07-28 | added 1 |  |  | 2020
Ismailia Substation 500-220 | 2020-08-01 |  | 250748.68 | 69447291.95 | 89594419.96 | -20147128.01 | 109399640 | -18.42% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-08-06 | 2899097.58 |  | 72346389.53 | 89594419.96 | -17248030.43 | 109399640 | -15.77% |  |  | 2020-08-06 | added 1 |  |  | 2020
Ismailia Substation 500-220 | 2020-09-01 |  | 332330.69 | 72346389.53 | 89926750.65 | -17580361.12 | 109399640 | -16.07% |  |  |  | cash out both |  |  | 2020
Ismailia Substation 500-220 | 2020-09-16 | 667221.67 |  | 73013611.2 | 89926750.65 | -16913139.45 | 109399640 | -15.46% |  |  | 2020-09-16 | added 1 |  |  | 2020
Ismailia Substation 500-220 | 2020-09-17 | 70946.57 |  | 73084557.77 | 89926750.65 | -16842192.88 | 109399640 | -15.4% |  |  | 2020-09-17 | added 1 |  |  | 2020
Ismailia Substation 500-220 | 2020-09-28 | 9900 |  | 73094457.77 | 89926750.65 | -16832292.88 | 109399640 | -15.39% |  |  | 2020-09-28 | added cash in 3 |  |  | 2020
Ismailia Substation 500-220 | 2020-09-28 | 389570.04 |  | 73484027.81 | 89926750.65 | -16442722.84 | 109399640 | -15.03% |  |  | 2020-09-28 | added cash in 3 |  |  | 2020
Ismailia Substation 500-220 | 2020-10-01 |  | 132372.71 | 73484027.81 | 90059123.36 | -16575095.55 | 109399640 | -15.15% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Ismailia Substation 500-220 | 2020-11-01 |  | 230397.45 | 73484027.81 | 90289520.81 | -16805493 | 109399640 | -15.36% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Ismailia Substation 500-220 | 2020-12-01 |  | 10911.29 | 73484027.81 | 90300432.1 | -16816404.29 | 109399640 | -15.37% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Ismailia Substation 500-220 | 2020-12-07 | 214819.72 |  | 73698847.53 | 90300432.1 | -16601584.57 | 109399640 | -15.18% |  |  | 2020-12-07 | added cash in 3 |  |  | 2020
Ismailia Substation 500-220 | 2020-12-07 | 593 |  | 73699440.53 | 90300432.1 | -16600991.57 | 109399640 | -15.17% |  |  | 2020-12-07 | added cash in 3 |  |  | 2020
Ismailia Substation 500-220 | 2021-01-01 |  | 25415.8 | 73699440.53 | 90325847.9 | -16626407.37 | 109399640 | -15.2% |  |  |  | cash out both |  |  | 2021
Ismailia Substation 500-220 | 2021-01-20 | 288528.58 |  | 73987969.11 | 90325847.9 | -16337878.79 | 109399640 | -14.93% |  |  | 2021-01-20 | added cash in 3 |  |  | 2021
Ismailia Substation 500-220 | 2021-02-01 |  | 180197.06 | 73987969.11 | 90506044.96 | -16518075.85 | 109399640 | -15.1% |  |  |  | cash out both |  |  | 2021
Ismailia Substation 500-220 | 2021-02-24 | 5362261.37 |  | 79350230.48 | 90506044.96 | -11155814.48 | 109399640 | -10.2% |  |  | 2021-02-24 | added cash in 3 |  |  | 2021
Ismailia Substation 500-220 | 2021-03-01 |  | 121287.64 | 79350230.48 | 90627332.6 | -11277102.12 | 109399640 | -10.31% |  |  |  | cash out both |  |  | 2021
Ismailia Substation 500-220 | 2021-03-28 | 535 |  | 79350765.48 | 90627332.6 | -11276567.12 | 109399640 | -10.31% |  |  | 2021-03-28 | added 1 |  |  | 2021
Ismailia Substation 500-220 | 2021-03-28 | 250406.62 |  | 79601172.1 | 90627332.6 | -11026160.5 | 109399640 | -10.08% |  |  | 2021-03-28 | added 1 |  |  | 2021
1900
El Amal Bridge L&L | 2017-05-01 |  | 18772.05 | 0 | 18772.05 | -18772.05 | 9050320 | -0.2074% |  |  |  | cash out both |  |  | 2017
El Amal Bridge L&L | 2017-05-31 | 1115000 |  | 1115000 | 18772.05 | 1096227.95 | 9050320 | 12.11% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
El Amal Bridge L&L | 2017-08-01 |  | 21342 | 1115000 | 40114.05 | 1074885.95 | 9050320 | 11.88% |  |  |  | cash out both |  |  | 2017
El Amal Bridge L&L | 2017-09-01 |  | 202989.69 | 1115000 | 243103.74 | 871896.26 | 9050320 | 9.634% |  |  |  | cash out both |  |  | 2017
El Amal Bridge L&L | 2017-10-01 |  | 3064.03 | 1115000 | 246167.77 | 868832.23 | 9050320 | 9.6% |  |  |  | cash out both |  |  | 2017
El Amal Bridge L&L | 2017-11-01 |  | 7821.35 | 1115000 | 253989.12 | 861010.88 | 9050320 | 9.514% |  |  |  | cash out both |  |  | 2017
El Amal Bridge L&L | 2017-12-01 |  | 483426.17 | 1115000 | 737415.29 | 377584.71 | 9050320 | 4.172% |  |  |  | cash out both |  |  | 2017
El Amal Bridge L&L | 2018-01-01 |  | 984041.29 | 1115000 | 1721456.58 | -606456.58 | 9050320 | -6.701% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-02-01 |  | 1208788.34 | 1115000 | 2930244.92 | -1815244.92 | 9050320 | -20.06% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-03-01 |  | 942303.73 | 1115000 | 3872548.65 | -2757548.65 | 9050320 | -30.47% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-04-01 |  | 883025.97 | 1115000 | 4755574.62 | -3640574.62 | 9050320 | -40.23% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-05-01 |  | 1170386.81 | 1115000 | 5925961.43 | -4810961.43 | 9050320 | -53.16% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-06-01 |  | 407379.19 | 1115000 | 6333340.62 | -5218340.62 | 9050320 | -57.66% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-06-11 | 4930770.85 |  | 6045770.85 | 6333340.62 | -287569.77 | 9050320 | -3.177% |  |  | 2018-06-11 | added cash in 3 |  |  | 2018
El Amal Bridge L&L | 2018-06-20 | 570100 |  | 6615870.85 | 6333340.62 | 282530.23 | 9050320 | 3.122% |  |  | 2018-06-20 | added cash in 3 |  |  | 2018
El Amal Bridge L&L | 2018-07-01 |  | 1755667.11 | 6615870.85 | 8089007.73 | -1473136.88 | 9050320 | -16.28% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-08-01 |  | 1166414.18 | 6615870.85 | 9255421.91 | -2639551.06 | 9050320 | -29.17% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-09-01 |  | 574475.43 | 6615870.85 | 9829897.34 | -3214026.49 | 9050320 | -35.51% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-10-01 |  | 2459804.84 | 6615870.85 | 12289702.18 | -5673831.33 | 9050320 | -62.69% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-11-01 |  | 1743963.1 | 6615870.85 | 14033665.28 | -7417794.43 | 9050320 | -81.96% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2018-12-01 |  | 1026384.16 | 6615870.85 | 15060049.44 | -8444178.59 | 9050320 | -93.3% |  |  |  | cash out both |  |  | 2018
El Amal Bridge L&L | 2019-01-01 |  | 1591582.89 | 6615870.85 | 16651632.33 | -10035761.48 | 9050320 | -110.9% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-02-01 |  | 1074306.55 | 6615870.85 | 17725938.88 | -11110068.03 | 9050320 | -122.8% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-03-01 |  | 974305.4 | 6615870.85 | 18700244.28 | -12084373.43 | 9050320 | -133.5% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-04-01 |  | 243500.39 | 6615870.85 | 18943744.67 | -12327873.82 | 9050320 | -136.2% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-05-01 |  | 411430.91 | 6615870.85 | 19355175.58 | -12739304.73 | 9050320 | -140.8% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-06-01 |  | 22932.84 | 6615870.85 | 19378108.42 | -12762237.57 | 9050320 | -141% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-07-01 |  | 22747.17 | 6615870.85 | 19400855.59 | -12784984.74 | 9050320 | -141.3% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-07-22 | 947802.1 |  | 7563672.95 | 19400855.59 | -11837182.64 | 9050320 | -130.8% |  |  | 2019-07-22 | added cash in 3 |  |  | 2019
El Amal Bridge L&L | 2019-08-01 |  | 3600 | 7563672.95 | 19404455.59 | -11840782.64 | 9050320 | -130.8% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-08-18 | 309647 |  | 7873319.95 | 19404455.59 | -11531135.64 | 9050320 | -127.4% |  |  | 2019-08-18 | added cash in 3 |  |  | 2019
El Amal Bridge L&L | 2019-10-01 |  | 4170.1 | 7873319.95 | 19408625.69 | -11535305.74 | 9050320 | -127.5% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2019-12-01 |  | 70945.9 | 7873319.95 | 19479571.59 | -11606251.64 | 9050320 | -128.2% |  |  |  | cash out both |  |  | 2019
El Amal Bridge L&L | 2020-01-01 |  | 570.1 | 7873319.95 | 19480141.69 | -11606821.74 | 9050320 | -128.2% |  |  |  | cash out both |  |  | 2020
El Amal Bridge L&L | 2020-02-01 |  | 40660.8 | 7873319.95 | 19520802.49 | -11647482.54 | 9050320 | -128.7% |  |  |  | cash out both |  |  | 2020
El Amal Bridge L&L | 2020-09-01 |  | 1710.3 | 7873319.95 | 19522512.79 | -11649192.84 | 9050320 | -128.7% |  |  |  | cash out both |  |  | 2020
El Amal Bridge L&L | 2020-12-01 |  | 79460.31 | 7873319.95 | 19601973.1 | -11728653.15 | 9050320 | -129.6% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
El Amal Bridge L&L | 2021-03-01 |  | 1710.31 | 7873319.95 | 19603683.41 | -11730363.46 | 9050320 | -129.6% |  |  |  | cash out both |  |  | 2021
1900
FIEM Wind Farm Gabal El Zeet | 2016-11-30 | 0 | 0 | 0 | 0 | 0 | 72547889 | 0% |  | 13973051 | 2016-11-30 | original |  |  | 2016
FIEM Wind Farm Gabal El Zeet | 2016-12-31 | 0 | 0 | 0 | 0 | 0 | 72547889 | 0% |  | 1956164 | 2016-12-31 | original |  |  | 2016
FIEM Wind Farm Gabal El Zeet | 2017-01-31 | 22186715 | 117409 | 22186715 | 117409 | 22069306 | 72547889 | 30.42% |  | 2299242 | 2017-01-31 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-02-28 | 0 | 6035079 | 22186715 | 6152488 | 16034227 | 72547889 | 22.1% |  | 14635357 | 2017-02-28 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-03-30 | 15487757.03 |  | 37674472.03 | 6152488 | 31521984.03 | 72547889 | 43.45% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-03-31 | 0 | 834404 | 37674472.03 | 6986892 | 30687580.03 | 72547889 | 42.3% |  | 21475622 | 2017-03-31 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-04-01 |  | 5000000 | 37674472.03 | 11986892 | 25687580.03 | 72547889 | 35.41% |  |  |  | cash out both |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-04-01 | 1261725.72 |  | 38936197.75 | 11986892 | 26949305.75 | 72547889 | 37.15% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-04-01 | 3409626 |  | 42345823.75 | 11986892 | 30358931.75 | 72547889 | 41.85% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-04-30 | 12985517 | 11480030 | 55331340.75 | 23466922 | 31864418.75 | 72547889 | 43.92% |  | 13232145 | 2017-04-30 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-05-01 |  | 1900822.05 | 55331340.75 | 25367744.05 | 29963596.7 | 72547889 | 41.3% |  |  |  | cash out both |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-05-31 | 9014308 | 11115131 | 64345648.75 | 36482875.05 | 27862773.7 | 72547889 | 38.41% |  | 0 | 2017-05-31 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-05-31 | 7531296.79 |  | 71876945.54 | 36482875.05 | 35394070.49 | 72547889 | 48.79% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-05-31 | 1483010.76 |  | 73359956.3 | 36482875.05 | 36877081.25 | 72547889 | 50.83% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-06-01 |  | 412255.42 | 73359956.3 | 36895130.47 | 36464825.83 | 72547889 | 50.26% |  |  |  | cash out both |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-06-30 | 0 | 6457537 | 73359956.3 | 43352667.47 | 30007288.83 | 72547889 | 41.36% |  | 0 | 2017-06-30 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-07-31 | 15627594 | 1022983 | 88987550.3 | 44375650.47 | 44611899.83 | 72547889 | 61.49% |  | 0 | 2017-07-31 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-07-31 | 796460.77 |  | 89784011.07 | 44375650.47 | 45408360.6 | 72547889 | 62.59% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-07-31 | 14831133.17 |  | 104615144.24 | 44375650.47 | 60239493.77 | 72547889 | 83.03% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-08-01 |  | 188407.67 | 104615144.24 | 44564058.14 | 60051086.1 | 72547889 | 82.77% |  |  |  | cash out both |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-08-31 | 9138162 | 1484349 | 113753306.24 | 46048407.14 | 67704899.1 | 72547889 | 93.32% |  | 0 | 2017-08-31 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-09-30 | 0 | 80911 | 113753306.24 | 46129318.14 | 67623988.1 | 72547889 | 93.21% |  | 0 | 2017-09-30 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-10-31 | 0 | 610714 | 113753306.24 | 46740032.14 | 67013274.1 | 72547889 | 92.37% |  | 2236447 | 2017-10-31 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-11-30 | 0 | 239263 | 113753306.24 | 46979295.14 | 66774011.1 | 72547889 | 92.04% |  | 341821 | 2017-11-30 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2017-12-31 | 2309407 | 239095 | 116062713.24 | 47218390.14 | 68844323.1 | 72547889 | 94.9% |  | 0 | 2017-12-31 | original |  |  | 2017
FIEM Wind Farm Gabal El Zeet | 2018-01-01 |  | 171545.41 | 116062713.24 | 47389935.55 | 68672777.69 | 72547889 | 94.66% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-01-03 | 1523916.51 |  | 117586629.75 | 47389935.55 | 70196694.2 | 72547889 | 96.76% |  |  | 2018-01-03 | added cash in 3 |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-03-01 |  | 117816.12 | 117586629.75 | 47507751.67 | 70078878.08 | 72547889 | 96.6% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-04-01 |  | 326063.6 | 117586629.75 | 47833815.27 | 69752814.48 | 72547889 | 96.15% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-04-24 | 218510 |  | 117805139.75 | 47833815.27 | 69971324.48 | 72547889 | 96.45% |  |  | 2018-04-24 | added cash in 3 |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-05-01 |  | 171248.52 | 117805139.75 | 48005063.79 | 69800075.96 | 72547889 | 96.21% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-06-01 |  | 178854.3 | 117805139.75 | 48183918.09 | 69621221.66 | 72547889 | 95.97% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-07-01 |  | 266452 | 117805139.75 | 48450370.09 | 69354769.66 | 72547889 | 95.6% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-08-01 |  | 314398.6 | 117805139.75 | 48764768.69 | 69040371.06 | 72547889 | 95.17% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-09-01 |  | 164390 | 117805139.75 | 48929158.69 | 68875981.06 | 72547889 | 94.94% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-10-01 |  | 37921 | 117805139.75 | 48967079.69 | 68838060.06 | 72547889 | 94.89% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2018-11-01 |  | 60300.49 | 117805139.75 | 49027380.18 | 68777759.57 | 72547889 | 94.8% |  |  |  | cash out both |  |  | 2018
FIEM Wind Farm Gabal El Zeet | 2019-01-01 |  | 7570.77 | 117805139.75 | 49034950.95 | 68770188.8 | 72547889 | 94.79% |  |  |  | cash out both |  |  | 2019
FIEM Wind Farm Gabal El Zeet | 2019-10-01 |  | 6339.06 | 117805139.75 | 49041290.01 | 68763849.74 | 72547889 | 94.78% |  |  |  | cash out both |  |  | 2019
FIEM Wind Farm Gabal El Zeet | 2019-10-13 | 286904.18 |  | 118092043.93 | 49041290.01 | 69050753.92 | 72547889 | 95.18% |  |  | 2019-10-13 | added cash in 3 |  |  | 2019
FIEM Wind Farm Gabal El Zeet | 2020-08-01 |  | 62501.49 | 118092043.93 | 49103791.5 | 68988252.43 | 72547889 | 95.09% |  |  |  | cash out both |  |  | 2020
1900
KFW Wind Farm Gabal El Zeet | 2016-10-31 | 7080183 | 0 | 7080183 | 0 | 7080183 | 23038288.54 | 30.73% |  | 5689328 | 2016-10-31 | original |  |  | 2016
KFW Wind Farm Gabal El Zeet | 2016-11-30 | 0 | 0 | 7080183 | 0 | 7080183 | 23038288.54 | 30.73% |  | 3637915 | 2016-11-30 | original |  |  | 2016
KFW Wind Farm Gabal El Zeet | 2016-12-31 | 0 | 0 | 7080183 | 0 | 7080183 | 23038288.54 | 30.73% |  | 1910183 | 2016-12-31 | original |  |  | 2016
KFW Wind Farm Gabal El Zeet | 2017-01-31 | 0 | 184065 | 7080183 | 184065 | 6896118 | 23038288.54 | 29.93% |  | 2616085 | 2017-01-31 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-02-28 | 3385150 | 435344 | 10465333 | 619409 | 9845924 | 23038288.54 | 42.74% |  | 7271634 | 2017-02-28 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-03-30 | 1989017.66 |  | 12454350.66 | 619409 | 11834941.66 | 23038288.54 | 51.37% |  |  | 2017-03-30 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-03-31 | 0 | 120209 | 12454350.66 | 739618 | 11714732.66 | 23038288.54 | 50.85% |  | 799962 | 2017-03-31 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-04-01 | 1136559.01 |  | 13590909.67 | 739618 | 12851291.67 | 23038288.54 | 55.78% |  |  | 2017-04-01 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-04-30 | 4997781 | 636709 | 18588690.67 | 1376327 | 17212363.67 | 23038288.54 | 74.71% |  | 486002 | 2017-04-30 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-05-01 |  | 12024.57 | 18588690.67 | 1388351.57 | 17200339.1 | 23038288.54 | 74.66% |  |  |  | cash out both |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-05-31 | 5037092 | 93863 | 23625782.67 | 1482214.57 | 22143568.1 | 23038288.54 | 96.12% |  | 0 | 2017-05-31 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-05-31 | 1687374.91 |  | 25313157.58 | 1482214.57 | 23830943.01 | 23038288.54 | 103.4% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-05-31 | 3349717.03 |  | 28662874.61 | 1482214.57 | 27180660.04 | 23038288.54 | 118% |  |  | 2017-05-31 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-06-30 | 0 | 84940 | 28662874.61 | 1567154.57 | 27095720.04 | 23038288.54 | 117.6% |  | 436653 | 2017-06-30 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-07-31 | 1986753 | 120057 | 30649627.61 | 1687211.57 | 28962416.04 | 23038288.54 | 125.7% |  | 0 | 2017-07-31 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-07-31 | 848331 |  | 31497958.61 | 1687211.57 | 29810747.04 | 23038288.54 | 129.4% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-07-31 | 561871.31 |  | 32059829.92 | 1687211.57 | 30372618.35 | 23038288.54 | 131.8% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-07-31 | 418293.1 |  | 32478123.02 | 1687211.57 | 30790911.45 | 23038288.54 | 133.7% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-07-31 | 158251.28 |  | 32636374.3 | 1687211.57 | 30949162.73 | 23038288.54 | 134.3% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-08-31 | 584820 | 184602 | 33221194.3 | 1871813.57 | 31349380.73 | 23038288.54 | 136.1% |  | 0 | 2017-08-31 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-09-30 | 654214 | 3000 | 33875408.3 | 1874813.57 | 32000594.73 | 23038288.54 | 138.9% |  | 156311 | 2017-09-30 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-09-30 | 654213.56 |  | 34529621.86 | 1874813.57 | 32654808.29 | 23038288.54 | 141.7% |  |  | 2017-09-30 | added cash in 3 |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-10-01 |  | 4165.64 | 34529621.86 | 1878979.21 | 32650642.65 | 23038288.54 | 141.7% |  |  |  | cash out both |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-11-30 | 137345 | 0 | 34666966.86 | 1878979.21 | 32787987.65 | 23038288.54 | 142.3% |  | 0 | 2017-11-30 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2017-12-31 | 0 | 2079 | 34666966.86 | 1881058.21 | 32785908.65 | 23038288.54 | 142.3% |  | 0 | 2017-12-31 | original |  |  | 2017
KFW Wind Farm Gabal El Zeet | 2018-01-01 |  | 58180.73 | 34666966.86 | 1939238.94 | 32727727.92 | 23038288.54 | 142.1% |  |  |  | cash out both |  |  | 2018
KFW Wind Farm Gabal El Zeet | 2018-01-23 | 128570.36 |  | 34795537.22 | 1939238.94 | 32856298.28 | 23038288.54 | 142.6% |  |  | 2018-01-23 | added cash in 3 |  |  | 2018
KFW Wind Farm Gabal El Zeet | 2018-03-01 |  | 29275.96 | 34795537.22 | 1968514.9 | 32827022.32 | 23038288.54 | 142.5% |  |  |  | cash out both |  |  | 2018
KFW Wind Farm Gabal El Zeet | 2018-05-01 |  | 10910.29 | 34795537.22 | 1979425.19 | 32816112.03 | 23038288.54 | 142.4% |  |  |  | cash out both |  |  | 2018
KFW Wind Farm Gabal El Zeet | 2018-06-01 |  | 2000 | 34795537.22 | 1981425.19 | 32814112.03 | 23038288.54 | 142.4% |  |  |  | cash out both |  |  | 2018
KFW Wind Farm Gabal El Zeet | 2018-09-01 |  | 27909.31 | 34795537.22 | 2009334.5 | 32786202.72 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  | 2018
KFW Wind Farm Gabal El Zeet | 2018-12-01 |  | 2022.91 | 34795537.22 | 2011357.41 | 32784179.81 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  | 2018
KFW Wind Farm Gabal El Zeet | 2019-09-01 |  | 2022.91 | 34795537.22 | 2013380.32 | 32782156.9 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  | 2019
KFW Wind Farm Gabal El Zeet | 2019-12-01 |  | 2022.91 | 34795537.22 | 2015403.23 | 32780133.99 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  | 2019
KFW Wind Farm Gabal El Zeet | 2020-08-01 |  | 21004.91 | 34795537.22 | 2036408.14 | 32759129.08 | 23038288.54 | 142.2% |  |  |  | cash out both |  |  | 2020
1900
Marassi Tank PKG 107 | 2017-02-28 | 0 | 635038 | 0 | 635038 | -635038 | 54777143 | -1.159% |  | 0 | 2017-02-28 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-03-31 | 6948801 | 924047 | 6948801 | 1559085 | 5389716 | 54777143 | 9.839% |  | 5089749 | 2017-03-31 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-04-01 |  | 74246.43 | 6948801 | 1633331.43 | 5315469.57 | 54777143 | 9.704% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-04-30 | 0 | 4244377 | 6948801 | 5877708.43 | 1071092.57 | 54777143 | 1.955% |  | 7583998 | 2017-04-30 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-05-01 |  | 71910.33 | 6948801 | 5949618.76 | 999182.24 | 54777143 | 1.824% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-05-31 | 10601254 | 3668078 | 17550055 | 9617696.76 | 7932358.24 | 54777143 | 14.48% |  | 5849284 | 2017-05-31 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-06-01 |  | 106020.29 | 17550055 | 9723717.05 | 7826337.95 | 54777143 | 14.29% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-06-30 | 4521275 | 3598135 | 22071330 | 13321852.05 | 8749477.95 | 54777143 | 15.97% |  | 5459726 | 2017-06-30 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-07-01 |  | 222735.52 | 22071330 | 13544587.57 | 8526742.43 | 54777143 | 15.57% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-07-31 | 4038006 | 3476517 | 26109336 | 17021104.57 | 9088231.43 | 54777143 | 16.59% |  | 3207733 | 2017-07-31 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-08-01 |  | 1165231.06 | 26109336 | 18186335.63 | 7923000.37 | 54777143 | 14.46% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-08-31 | 4655009 | 3536425 | 30764345 | 21722760.63 | 9041584.37 | 54777143 | 16.51% |  | 4593486 | 2017-08-31 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-09-01 |  | 58332.35 | 30764345 | 21781092.98 | 8983252.02 | 54777143 | 16.4% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-09-30 | 574298 | 1560412 | 31338643 | 23341504.98 | 7997138.02 | 54777143 | 14.6% |  | 4398604 | 2017-09-30 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-10-01 |  | 395517.07 | 31338643 | 23737022.05 | 7601620.95 | 54777143 | 13.88% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-10-31 | 6664691 | 2956736 | 38003334 | 26693758.05 | 11309575.95 | 54777143 | 20.65% |  | 1856322 | 2017-10-31 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-11-01 |  | 46929.67 | 38003334 | 26740687.72 | 11262646.28 | 54777143 | 20.56% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-11-30 | 0 | 981843 | 38003334 | 27722530.72 | 10280803.28 | 54777143 | 18.77% |  | 2025124 | 2017-11-30 | original |  |  | 2017
Marassi Tank PKG 107 | 2017-12-01 |  | 316753.22 | 38003334 | 28039283.94 | 9964050.06 | 54777143 | 18.19% |  |  |  | cash out both |  |  | 2017
Marassi Tank PKG 107 | 2017-12-31 | 1418091 | 3444139 | 39421425 | 31483422.94 | 7938002.06 | 54777143 | 14.49% |  | 3591068 | 2017-12-31 | original |  |  | 2017
Marassi Tank PKG 107 | 2018-01-01 |  | 1386471.9 | 39421425 | 32869894.84 | 6551530.16 | 54777143 | 11.96% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-01-02 | 203292.99 |  | 39624717.99 | 32869894.84 | 6754823.15 | 54777143 | 12.33% |  |  | 2018-01-02 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-01-11 | 1453205.38 |  | 41077923.37 | 32869894.84 | 8208028.53 | 54777143 | 14.98% |  |  | 2018-01-11 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-02-01 |  | 713801.85 | 41077923.37 | 33583696.69 | 7494226.68 | 54777143 | 13.68% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-02-10 | 194407.29 |  | 41272330.66 | 33583696.69 | 7688633.97 | 54777143 | 14.04% |  |  | 2018-02-10 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-02-25 | 2354508.52 |  | 43626839.18 | 33583696.69 | 10043142.49 | 54777143 | 18.33% |  |  | 2018-02-25 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-03-01 |  | 3278167.58 | 43626839.18 | 36861864.27 | 6764974.91 | 54777143 | 12.35% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-03-13 | 4193998 |  | 47820837.18 | 36861864.27 | 10958972.91 | 54777143 | 20.01% |  |  | 2018-03-13 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-04-01 |  | 277697.88 | 47820837.18 | 37139562.15 | 10681275.03 | 54777143 | 19.5% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-04-19 | 3281572.56 |  | 51102409.74 | 37139562.15 | 13962847.59 | 54777143 | 25.49% |  |  | 2018-04-19 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-05-01 |  | 556513.87 | 51102409.74 | 37696076.02 | 13406333.72 | 54777143 | 24.47% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-05-09 | 166316.41 |  | 51268726.15 | 37696076.02 | 13572650.13 | 54777143 | 24.78% |  |  | 2018-05-09 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-05-16 | 391905.3 |  | 51660631.45 | 37696076.02 | 13964555.43 | 54777143 | 25.49% |  |  | 2018-05-16 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-06-01 |  | 505439.58 | 51660631.45 | 38201515.6 | 13459115.85 | 54777143 | 24.57% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-06-11 | 186644 |  | 51847275.45 | 38201515.6 | 13645759.85 | 54777143 | 24.91% |  |  | 2018-06-11 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-06-13 | 1406606.27 |  | 53253881.72 | 38201515.6 | 15052366.12 | 54777143 | 27.48% |  |  | 2018-06-13 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-06-28 | 59875.63 |  | 53313757.35 | 38201515.6 | 15112241.75 | 54777143 | 27.59% |  |  | 2018-06-28 | added cash in 3 |  |  | 2018
Marassi Tank PKG 107 | 2018-07-01 |  | 605871.85 | 53313757.35 | 38807387.45 | 14506369.9 | 54777143 | 26.48% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-08-01 |  | 578798.26 | 53313757.35 | 39386185.71 | 13927571.64 | 54777143 | 25.43% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-09-01 |  | 412108.33 | 53313757.35 | 39798294.04 | 13515463.31 | 54777143 | 24.67% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-10-01 |  | 161750.86 | 53313757.35 | 39960044.9 | 13353712.45 | 54777143 | 24.38% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-11-01 |  | 804028.65 | 53313757.35 | 40764073.55 | 12549683.8 | 54777143 | 22.91% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2018-12-01 |  | 167704.23 | 53313757.35 | 40931777.78 | 12381979.57 | 54777143 | 22.6% |  |  |  | cash out both |  |  | 2018
Marassi Tank PKG 107 | 2019-01-01 |  | 24348.06 | 53313757.35 | 40956125.84 | 12357631.51 | 54777143 | 22.56% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2019-02-01 |  | 23676.72 | 53313757.35 | 40979802.56 | 12333954.79 | 54777143 | 22.52% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2019-03-01 |  | 23052.2 | 53313757.35 | 41002854.76 | 12310902.59 | 54777143 | 22.47% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2019-03-13 | 894884.44 |  | 54208641.79 | 41002854.76 | 13205787.03 | 54777143 | 24.11% |  |  | 2019-03-13 | added cash in 3 |  |  | 2019
Marassi Tank PKG 107 | 2019-05-01 |  | 69667.89 | 54208641.79 | 41072522.65 | 13136119.14 | 54777143 | 23.98% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2019-06-01 |  | 16188.48 | 54208641.79 | 41088711.13 | 13119930.66 | 54777143 | 23.95% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2019-08-01 |  | 269048.8 | 54208641.79 | 41357759.93 | 12850881.86 | 54777143 | 23.46% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2019-09-01 |  | 16188.48 | 54208641.79 | 41373948.41 | 12834693.38 | 54777143 | 23.43% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2019-11-25 | 1341459.14 |  | 55550100.93 | 41373948.41 | 14176152.52 | 54777143 | 25.88% |  |  | 2019-11-25 | added cash in 3 |  |  | 2019
Marassi Tank PKG 107 | 2019-12-01 |  | 92637.22 | 55550100.93 | 41466585.63 | 14083515.3 | 54777143 | 25.71% |  |  |  | cash out both |  |  | 2019
Marassi Tank PKG 107 | 2020-01-01 |  | 99256 | 55550100.93 | 41565841.63 | 13984259.3 | 54777143 | 25.53% |  |  |  | cash out both |  |  | 2020
Marassi Tank PKG 107 | 2020-02-01 |  | 198512 | 55550100.93 | 41764353.63 | 13785747.3 | 54777143 | 25.17% |  |  |  | cash out both |  |  | 2020
Marassi Tank PKG 107 | 2020-03-01 |  | 16188.48 | 55550100.93 | 41780542.11 | 13769558.82 | 54777143 | 25.14% |  |  |  | cash out both |  |  | 2020
Marassi Tank PKG 107 | 2020-04-01 |  | 0.57 | 55550100.93 | 41780542.68 | 13769558.25 | 54777143 | 25.14% |  |  |  | cash out both |  |  | 2020
Marassi Tank PKG 107 | 2020-06-01 |  | 16188.48 | 55550100.93 | 41796731.16 | 13753369.77 | 54777143 | 25.11% |  |  |  | cash out both |  |  | 2020
Marassi Tank PKG 107 | 2020-09-01 |  | 16188.48 | 55550100.93 | 41812919.64 | 13737181.29 | 54777143 | 25.08% |  |  |  | cash out both |  |  | 2020
Marassi Tank PKG 107 | 2020-10-01 |  | 16175.03 | 55550100.93 | 41829094.67 | 13721006.26 | 54777143 | 25.05% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Marassi Tank PKG 107 | 2020-12-01 |  | 16794.4 | 55550100.93 | 41845889.07 | 13704211.86 | 54777143 | 25.02% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
1900
Ben Zayed New Capital Tunnel | 2017-04-01 |  | 500000 | 0 | 500000 | -500000 | 343357654.106 | -0.1456% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-05-01 |  | 1865980.42 | 0 | 2365980.42 | -2365980.42 | 343357654.106 | -0.6891% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-06-01 |  | 1814913.59 | 0 | 4180894.01 | -4180894.01 | 343357654.106 | -1.218% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-07-01 |  | 858442.83 | 0 | 5039336.84 | -5039336.84 | 343357654.106 | -1.468% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-08-01 |  | 1610520 | 0 | 6649856.84 | -6649856.84 | 343357654.106 | -1.937% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-09-01 |  | 1077570.84 | 0 | 7727427.68 | -7727427.68 | 343357654.106 | -2.251% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-10-01 |  | 1403301.44 | 0 | 9130729.12 | -9130729.12 | 343357654.106 | -2.659% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-11-01 |  | 1805648.69 | 0 | 10936377.81 | -10936377.81 | 343357654.106 | -3.185% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2017-12-01 |  | 1795222.75 | 0 | 12731600.56 | -12731600.56 | 343357654.106 | -3.708% |  |  |  | cash out both |  |  | 2017
Ben Zayed New Capital Tunnel | 2018-01-01 |  | 6134697.58 | 0 | 18866298.14 | -18866298.14 | 343357654.106 | -5.495% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-02-01 |  | 7622729.39 | 0 | 26489027.53 | -26489027.53 | 343357654.106 | -7.715% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-02-01 | 34397309.55 |  | 34397309.55 | 26489027.53 | 7908282.02 | 343357654.106 | 2.303% |  |  | 2018-02-01 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-02-27 | 15800505.2 |  | 50197814.75 | 26489027.53 | 23708787.22 | 343357654.106 | 6.905% |  |  | 2018-02-27 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-03-01 |  | 6855235.08 | 50197814.75 | 33344262.61 | 16853552.14 | 343357654.106 | 4.908% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-04-01 |  | 2692337.96 | 50197814.75 | 36036600.57 | 14161214.18 | 343357654.106 | 4.124% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-05-01 |  | 5182825.62 | 50197814.75 | 41219426.19 | 8978388.56 | 343357654.106 | 2.615% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-06-01 |  | 5308830.37 | 50197814.75 | 46528256.56 | 3669558.19 | 343357654.106 | 1.069% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-06-11 | 2372381.85 |  | 52570196.6 | 46528256.56 | 6041940.04 | 343357654.106 | 1.76% |  |  | 2018-06-11 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-07-01 |  | 4338476.67 | 52570196.6 | 50866733.23 | 1703463.37 | 343357654.106 | 0.4961% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-08-01 |  | 2815491.27 | 52570196.6 | 53682224.5 | -1112027.9 | 343357654.106 | -0.3239% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-08-31 | 35350000 |  | 87920196.6 | 53682224.5 | 34237972.1 | 343357654.106 | 9.972% |  |  | 2018-08-31 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-08-31 | 18748.3 |  | 87938944.9 | 53682224.5 | 34256720.4 | 343357654.106 | 9.977% |  |  | 2018-08-31 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-09-01 |  | 2438882.65 | 87938944.9 | 56121107.15 | 31817837.75 | 343357654.106 | 9.267% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-10-01 |  | 1492701.73 | 87938944.9 | 57613808.88 | 30325136.02 | 343357654.106 | 8.832% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-10-18 | 3408205.8 |  | 91347150.7 | 57613808.88 | 33733341.82 | 343357654.106 | 9.825% |  |  | 2018-10-18 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-10-28 | 1059272.8 |  | 92406423.5 | 57613808.88 | 34792614.62 | 343357654.106 | 10.13% |  |  | 2018-10-28 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-10-29 | 5414775 |  | 97821198.5 | 57613808.88 | 40207389.62 | 343357654.106 | 11.71% |  |  | 2018-10-29 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-11-01 |  | 1829195.68 | 97821198.5 | 59443004.56 | 38378193.94 | 343357654.106 | 11.18% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-11-18 | 59397 |  | 97880595.5 | 59443004.56 | 38437590.94 | 343357654.106 | 11.19% |  |  | 2018-11-18 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-12-01 |  | 1251141.58 | 97880595.5 | 60694146.14 | 37186449.36 | 343357654.106 | 10.83% |  |  |  | cash out both |  |  | 2018
Ben Zayed New Capital Tunnel | 2018-12-19 | 792617 |  | 98673212.5 | 60694146.14 | 37979066.36 | 343357654.106 | 11.06% |  |  | 2018-12-19 | added cash in 3 |  |  | 2018
Ben Zayed New Capital Tunnel | 2019-01-01 |  | 975257.31 | 98673212.5 | 61669403.45 | 37003809.05 | 343357654.106 | 10.78% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-01-20 | 6080870.45 |  | 104754082.95 | 61669403.45 | 43084679.5 | 343357654.106 | 12.55% |  |  | 2019-01-20 | added cash in 3 |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-02-01 |  | 719983.47 | 104754082.95 | 62389386.92 | 42364696.03 | 343357654.106 | 12.34% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-03-01 |  | 2102120.71 | 104754082.95 | 64491507.63 | 40262575.32 | 343357654.106 | 11.73% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-04-01 |  | 357064.6 | 104754082.95 | 64848572.23 | 39905510.72 | 343357654.106 | 11.62% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-05-01 |  | 2084145.44 | 104754082.95 | 66932717.67 | 37821365.28 | 343357654.106 | 11.02% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-06-01 |  | 1013297.48 | 104754082.95 | 67946015.15 | 36808067.8 | 343357654.106 | 10.72% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-07-01 |  | 591707.4 | 104754082.95 | 68537722.55 | 36216360.4 | 343357654.106 | 10.55% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-07-30 | 7946257 |  | 112700339.95 | 68537722.55 | 44162617.4 | 343357654.106 | 12.86% |  |  | 2019-07-30 | added cash in 3 |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-08-01 |  | 893913.7 | 112700339.95 | 69431636.25 | 43268703.7 | 343357654.106 | 12.6% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-08-14 | 16321127 |  | 129021466.95 | 69431636.25 | 59589830.7 | 343357654.106 | 17.36% |  |  | 2019-08-14 | added cash in 3 |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-09-01 |  | 502268.86 | 129021466.95 | 69933905.11 | 59087561.84 | 343357654.106 | 17.21% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-10-01 |  | 126805.94 | 129021466.95 | 70060711.05 | 58960755.9 | 343357654.106 | 17.17% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-11-01 |  | 398134.41 | 129021466.95 | 70458845.46 | 58562621.49 | 343357654.106 | 17.06% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2019-12-01 |  | 453907.04 | 129021466.95 | 70912752.5 | 58108714.45 | 343357654.106 | 16.92% |  |  |  | cash out both |  |  | 2019
Ben Zayed New Capital Tunnel | 2020-01-01 |  | 426566.73 | 129021466.95 | 71339319.23 | 57682147.72 | 343357654.106 | 16.8% |  |  |  | cash out both |  |  | 2020
Ben Zayed New Capital Tunnel | 2020-02-01 |  | 523798.86 | 129021466.95 | 71863118.09 | 57158348.86 | 343357654.106 | 16.65% |  |  |  | cash out both |  |  | 2020
Ben Zayed New Capital Tunnel | 2020-06-01 |  | 200 | 129021466.95 | 71863318.09 | 57158148.86 | 343357654.106 | 16.65% |  |  |  | cash out both |  |  | 2020
Ben Zayed New Capital Tunnel | 2020-08-01 |  | 123355.06 | 129021466.95 | 71986673.15 | 57034793.8 | 343357654.106 | 16.61% |  |  |  | cash out both |  |  | 2020
Ben Zayed New Capital Tunnel | 2020-10-01 |  | 13763.75 | 129021466.95 | 72000436.9 | 57021030.05 | 343357654.106 | 16.61% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Ben Zayed New Capital Tunnel | 2021-01-01 |  | 38898 | 129021466.95 | 72039334.9 | 56982132.05 | 343357654.106 | 16.6% |  |  |  | cash out both |  |  | 2021
1900
Ministries Buildings | 2017-03-31 | 0 | 188964 | 0 | 188964 | -188964 | 2740570200 | -0.006895% |  | 0 | 2017-03-31 | original |  |  | 2017
Ministries Buildings | 2017-04-30 | 0 | 153905 | 0 | 342869 | -342869 | 2740570200 | -0.01251% |  | 0 | 2017-04-30 | original |  |  | 2017
Ministries Buildings | 2017-05-01 |  | 570107.8 | 0 | 912976.8 | -912976.8 | 2740570200 | -0.03331% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-05-31 | 0 | 1820187 | 0 | 2733163.8 | -2733163.8 | 2740570200 | -0.09973% |  | 4208625 | 2017-05-31 | original |  |  | 2017
Ministries Buildings | 2017-06-01 |  | 1013592.05 | 0 | 3746755.85 | -3746755.85 | 2740570200 | -0.1367% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-06-30 | 50000000 | 2038708 | 50000000 | 5785463.85 | 44214536.15 | 2740570200 | 1.613% |  | 2309681 | 2017-06-30 | original |  |  | 2017
Ministries Buildings | 2017-06-30 | 50000000 |  | 100000000 | 5785463.85 | 94214536.15 | 2740570200 | 3.438% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
Ministries Buildings | 2017-07-01 |  | 3177925.87 | 100000000 | 8963389.72 | 91036610.28 | 2740570200 | 3.322% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-07-31 | 30000000 | 8009229 | 130000000 | 16972618.72 | 113027381.28 | 2740570200 | 4.124% |  | 19580519 | 2017-07-31 | original |  |  | 2017
Ministries Buildings | 2017-07-31 | 30000000 |  | 160000000 | 16972618.72 | 143027381.28 | 2740570200 | 5.219% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
Ministries Buildings | 2017-08-01 |  | 3659555.63 | 160000000 | 20632174.35 | 139367825.65 | 2740570200 | 5.085% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-08-31 | 60000000 | 10775691 | 220000000 | 31407865.35 | 188592134.65 | 2740570200 | 6.881% |  | 18663617 | 2017-08-31 | original |  |  | 2017
Ministries Buildings | 2017-08-31 | 70000000 |  | 290000000 | 31407865.35 | 258592134.65 | 2740570200 | 9.436% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Ministries Buildings | 2017-09-01 |  | 2023480.05 | 290000000 | 33431345.4 | 256568654.6 | 2740570200 | 9.362% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-09-30 | 0 | 10695649 | 290000000 | 44126994.4 | 245873005.6 | 2740570200 | 8.972% |  | 45266644 | 2017-09-30 | original |  |  | 2017
Ministries Buildings | 2017-10-01 |  | 2200546.42 | 290000000 | 46327540.82 | 243672459.18 | 2740570200 | 8.891% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-10-31 | 0 | 17811658 | 290000000 | 64139198.82 | 225860801.18 | 2740570200 | 8.241% |  | 50037584 | 2017-10-31 | original |  |  | 2017
Ministries Buildings | 2017-11-01 |  | 3226674.86 | 290000000 | 67365873.68 | 222634126.32 | 2740570200 | 8.124% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-11-30 | 0 | 18197510 | 290000000 | 85563383.68 | 204436616.32 | 2740570200 | 7.46% |  | 38477605 | 2017-11-30 | original |  |  | 2017
Ministries Buildings | 2017-12-01 |  | 3274354.65 | 290000000 | 88837738.33 | 201162261.67 | 2740570200 | 7.34% |  |  |  | cash out both |  |  | 2017
Ministries Buildings | 2017-12-01 | 35000000 |  | 325000000 | 88837738.33 | 236162261.67 | 2740570200 | 8.617% |  |  | 2017-12-01 | added cash in 3 |  |  | 2017
Ministries Buildings | 2017-12-31 | 35000000 | 27322000 | 360000000 | 116159738.33 | 243840261.67 | 2740570200 | 8.897% |  | 42599880 | 2017-12-31 | original |  |  | 2017
Ministries Buildings | 2018-01-01 |  | 50818659.44 | 360000000 | 166978397.77 | 193021602.23 | 2740570200 | 7.043% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-01-29 | 80000000 |  | 440000000 | 166978397.77 | 273021602.23 | 2740570200 | 9.962% |  |  | 2018-01-29 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-02-01 |  | 12977050.18 | 440000000 | 179955447.95 | 260044552.05 | 2740570200 | 9.489% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-03-01 |  | 23890488.06 | 440000000 | 203845936.01 | 236154063.99 | 2740570200 | 8.617% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-03-20 | 80000000 |  | 520000000 | 203845936.01 | 316154063.99 | 2740570200 | 11.54% |  |  | 2018-03-20 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-04-01 |  | 14804232.03 | 520000000 | 218650168.04 | 301349831.96 | 2740570200 | 11% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-05-01 |  | 17011513.76 | 520000000 | 235661681.8 | 284338318.2 | 2740570200 | 10.38% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-06-01 |  | 34973159.2 | 520000000 | 270634841 | 249365159 | 2740570200 | 9.099% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-06-10 | 80000000 |  | 600000000 | 270634841 | 329365159 | 2740570200 | 12.02% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-07-01 |  | 13252281.83 | 600000000 | 283887122.83 | 316112877.17 | 2740570200 | 11.53% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-08-01 |  | 15500737.93 | 600000000 | 299387860.76 | 300612139.24 | 2740570200 | 10.97% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-09-01 |  | 23488060.07 | 600000000 | 322875920.83 | 277124079.17 | 2740570200 | 10.11% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-09-23 | 165848000 |  | 765848000 | 322875920.83 | 442972079.17 | 2740570200 | 16.16% |  |  | 2018-09-23 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-09-30 | 65410520 |  | 831258520 | 322875920.83 | 508382599.17 | 2740570200 | 18.55% |  |  | 2018-09-30 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-10-01 |  | 31749536.71 | 831258520 | 354625457.54 | 476633062.46 | 2740570200 | 17.39% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-10-09 | 473784.15 |  | 831732304.15 | 354625457.54 | 477106846.61 | 2740570200 | 17.41% |  |  | 2018-10-09 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-10-11 | 79999997 |  | 911732301.15 | 354625457.54 | 557106843.61 | 2740570200 | 20.33% |  |  | 2018-10-11 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-10-11 | 80000000 |  | 991732301.15 | 354625457.54 | 637106843.61 | 2740570200 | 23.25% |  |  | 2018-10-11 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-10-16 | 28111276.05 |  | 1019843577.2 | 354625457.54 | 665218119.66 | 2740570200 | 24.27% |  |  | 2018-10-16 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-11-01 |  | 18529572.93 | 1019843577.2 | 373155030.47 | 646688546.73 | 2740570200 | 23.6% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2018-11-19 | 25450216.8 |  | 1045293794 | 373155030.47 | 672138763.53 | 2740570200 | 24.53% |  |  | 2018-11-19 | added cash in 3 |  |  | 2018
Ministries Buildings | 2018-12-01 |  | 27526803.53 | 1045293794 | 400681834 | 644611960 | 2740570200 | 23.52% |  |  |  | cash out both |  |  | 2018
Ministries Buildings | 2019-01-01 |  | 16965897.31 | 1045293794 | 417647731.31 | 627646062.69 | 2740570200 | 22.9% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-02-01 |  | 23082154.62 | 1045293794 | 440729885.93 | 604563908.07 | 2740570200 | 22.06% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-03-01 |  | 24007674.25 | 1045293794 | 464737560.18 | 580556233.82 | 2740570200 | 21.18% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-03-21 | 70000000 |  | 1115293794 | 464737560.18 | 650556233.82 | 2740570200 | 23.74% |  |  | 2019-03-21 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-04-01 |  | 55118842.58 | 1115293794 | 519856402.76 | 595437391.24 | 2740570200 | 21.73% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-04-22 | 100000000 |  | 1215293794 | 519856402.76 | 695437391.24 | 2740570200 | 25.38% |  |  | 2019-04-22 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-05-01 |  | 28005761.59 | 1215293794 | 547862164.35 | 667431629.65 | 2740570200 | 24.35% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-06-01 |  | 31424550.83 | 1215293794 | 579286715.18 | 636007078.82 | 2740570200 | 23.21% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-06-23 | 100000000 |  | 1315293794 | 579286715.18 | 736007078.82 | 2740570200 | 26.86% |  |  | 2019-06-23 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-07-01 |  | 40314984.33 | 1315293794 | 619601699.51 | 695692094.49 | 2740570200 | 25.38% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-08-01 |  | 42436749 | 1315293794 | 662038448.51 | 653255345.49 | 2740570200 | 23.84% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-08-08 | 8435650 |  | 1323729444 | 662038448.51 | 661690995.49 | 2740570200 | 24.14% |  |  | 2019-08-08 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-08-08 | 22764070 |  | 1346493514 | 662038448.51 | 684455065.49 | 2740570200 | 24.97% |  |  | 2019-08-08 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-08-08 | 82000000 |  | 1428493514 | 662038448.51 | 766455065.49 | 2740570200 | 27.97% |  |  | 2019-08-08 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-08-08 | 152106.5 |  | 1428645620.5 | 662038448.51 | 766607171.99 | 2740570200 | 27.97% |  |  | 2019-08-08 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-09-01 |  | 59274274.09 | 1428645620.5 | 721312722.6 | 707332897.9 | 2740570200 | 25.81% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-09-03 | 10335977 |  | 1438981597.5 | 721312722.6 | 717668874.9 | 2740570200 | 26.19% |  |  | 2019-09-03 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-09-04 | 15845427 |  | 1454827024.5 | 721312722.6 | 733514301.9 | 2740570200 | 26.77% |  |  | 2019-09-04 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-09-08 | 8947617 |  | 1463774641.5 | 721312722.6 | 742461918.9 | 2740570200 | 27.09% |  |  | 2019-09-08 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-09-23 | 5695997 |  | 1469470638.5 | 721312722.6 | 748157915.9 | 2740570200 | 27.3% |  |  | 2019-09-23 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-09-30 | 4942072 |  | 1474412710.5 | 721312722.6 | 753099987.9 | 2740570200 | 27.48% |  |  | 2019-09-30 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-10-01 |  | 89908498.7 | 1474412710.5 | 811221221.3 | 663191489.2 | 2740570200 | 24.2% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-10-15 | 63279757.2 |  | 1537692467.7 | 811221221.3 | 726471246.4 | 2740570200 | 26.51% |  |  | 2019-10-15 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-10-30 | 699177 |  | 1538391644.7 | 811221221.3 | 727170423.4 | 2740570200 | 26.53% |  |  | 2019-10-30 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-10-30 | 1356777 |  | 1539748421.7 | 811221221.3 | 728527200.4 | 2740570200 | 26.58% |  |  | 2019-10-30 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-10-30 | 4174487 |  | 1543922908.7 | 811221221.3 | 732701687.4 | 2740570200 | 26.74% |  |  | 2019-10-30 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-11-01 |  | 57941965.08 | 1543922908.7 | 869163186.38 | 674759722.32 | 2740570200 | 24.62% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-11-20 | 7040557 |  | 1550963465.7 | 869163186.38 | 681800279.32 | 2740570200 | 24.88% |  |  | 2019-11-20 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-11-20 | 2943337 |  | 1553906802.7 | 869163186.38 | 684743616.32 | 2740570200 | 24.99% |  |  | 2019-11-20 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-12-01 |  | 34708025.77 | 1553906802.7 | 903871212.15 | 650035590.55 | 2740570200 | 23.72% |  |  |  | cash out both |  |  | 2019
Ministries Buildings | 2019-12-02 | 3869107 |  | 1557775909.7 | 903871212.15 | 653904697.55 | 2740570200 | 23.86% |  |  | 2019-12-02 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-12-30 | 1182927 |  | 1558958836.7 | 903871212.15 | 655087624.55 | 2740570200 | 23.9% |  |  | 2019-12-30 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-12-31 | 3500000 |  | 1562458836.7 | 903871212.15 | 658587624.55 | 2740570200 | 24.03% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-12-31 | 80000000 |  | 1642458836.7 | 903871212.15 | 738587624.55 | 2740570200 | 26.95% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-12-31 | 59000000 |  | 1701458836.7 | 903871212.15 | 797587624.55 | 2740570200 | 29.1% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Ministries Buildings | 2019-12-31 | 883900 |  | 1702342736.7 | 903871212.15 | 798471524.55 | 2740570200 | 29.14% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Ministries Buildings | 2020-01-01 |  | 138788979.29 | 1702342736.7 | 1042660191.44 | 659682545.26 | 2740570200 | 24.07% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-01-19 | 2851037 |  | 1705193773.7 | 1042660191.44 | 662533582.26 | 2740570200 | 24.18% |  |  | 2020-01-19 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-02-01 |  | 75615089.69 | 1705193773.7 | 1118275281.13 | 586918492.57 | 2740570200 | 21.42% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-02-11 | 6579617 |  | 1711773390.7 | 1118275281.13 | 593498109.57 | 2740570200 | 21.66% |  |  | 2020-02-11 | added 1 |  |  | 2020
Ministries Buildings | 2020-02-17 | 47786690 |  | 1759560080.7 | 1118275281.13 | 641284799.57 | 2740570200 | 23.4% |  |  | 2020-02-17 | added 1 |  |  | 2020
Ministries Buildings | 2020-02-17 | 6411270 |  | 1765971350.7 | 1118275281.13 | 647696069.57 | 2740570200 | 23.63% |  |  | 2020-02-17 | added 1 |  |  | 2020
Ministries Buildings | 2020-02-18 | 6411270 |  | 1772382620.7 | 1118275281.13 | 654107339.57 | 2740570200 | 23.87% |  |  | 2020-02-18 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-02-18 | 47786690 |  | 1820169310.7 | 1118275281.13 | 701894029.57 | 2740570200 | 25.61% |  |  | 2020-02-18 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-02-23 | 10906440 |  | 1831075750.7 | 1118275281.13 | 712800469.57 | 2740570200 | 26.01% |  |  | 2020-02-23 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-02-26 | 9359710 |  | 1840435460.7 | 1118275281.13 | 722160179.57 | 2740570200 | 26.35% |  |  | 2020-02-26 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-03-01 | 557310 |  | 1840992770.7 | 1118275281.13 | 722717489.57 | 2740570200 | 26.37% |  |  | 2020-03-01 | added 1 |  |  | 2020
Ministries Buildings | 2020-03-01 | 318910 |  | 1841311680.7 | 1118275281.13 | 723036399.57 | 2740570200 | 26.38% |  |  | 2020-03-01 | added 1 |  |  | 2020
Ministries Buildings | 2020-03-01 |  | 32230884.5 | 1841311680.7 | 1150506165.63 | 690805515.07 | 2740570200 | 25.21% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-03-03 | 557310 |  | 1841868990.7 | 1150506165.63 | 691362825.07 | 2740570200 | 25.23% |  |  | 2020-03-03 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-03-03 | 318910 |  | 1842187900.7 | 1150506165.63 | 691681735.07 | 2740570200 | 25.24% |  |  | 2020-03-03 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-03-05 | 200590 |  | 1842388490.7 | 1150506165.63 | 691882325.07 | 2740570200 | 25.25% |  |  | 2020-03-05 | added 1 |  |  | 2020
Ministries Buildings | 2020-03-22 | 21929380 |  | 1864317870.7 | 1150506165.63 | 713811705.07 | 2740570200 | 26.05% |  |  | 2020-03-22 | added 1 |  |  | 2020
Ministries Buildings | 2020-03-26 | 5400020 |  | 1869717890.7 | 1150506165.63 | 719211725.07 | 2740570200 | 26.24% |  |  | 2020-03-26 | added 1 |  |  | 2020
Ministries Buildings | 2020-03-26 | 10490 |  | 1869728380.7 | 1150506165.63 | 719222215.07 | 2740570200 | 26.24% |  |  | 2020-03-26 | added 1 |  |  | 2020
Ministries Buildings | 2020-03-31 | 715217 |  | 1870443597.7 | 1150506165.63 | 719937432.07 | 2740570200 | 26.27% |  |  | 2020-03-31 | added 1 |  |  | 2020
Ministries Buildings | 2020-04-01 |  | 13628063.76 | 1870443597.7 | 1164134229.39 | 706309368.31 | 2740570200 | 25.77% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-04-23 | 506375 |  | 1870949972.7 | 1164134229.39 | 706815743.31 | 2740570200 | 25.79% |  |  | 2020-04-23 | added 1 |  |  | 2020
Ministries Buildings | 2020-04-26 | 1771845 |  | 1872721817.7 | 1164134229.39 | 708587588.31 | 2740570200 | 25.86% |  |  | 2020-04-26 | added 1 |  |  | 2020
Ministries Buildings | 2020-04-26 | 1741265 |  | 1874463082.7 | 1164134229.39 | 710328853.31 | 2740570200 | 25.92% |  |  | 2020-04-26 | added 1 |  |  | 2020
Ministries Buildings | 2020-05-01 |  | 25563496.08 | 1874463082.7 | 1189697725.47 | 684765357.23 | 2740570200 | 24.99% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-06-01 |  | 36844843.56 | 1874463082.7 | 1226542569.03 | 647920513.67 | 2740570200 | 23.64% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-06-21 | 501405 |  | 1874964487.7 | 1226542569.03 | 648421918.67 | 2740570200 | 23.66% |  |  | 2020-06-21 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-06-30 | 15000008.85 |  | 1889964496.55 | 1226542569.03 | 663421927.52 | 2740570200 | 24.21% |  |  | 2020-06-30 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-07-01 |  | 49618323.32 | 1889964496.55 | 1276160892.35 | 613803604.2 | 2740570200 | 22.4% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-07-28 | 101591695 |  | 1991556191.55 | 1276160892.35 | 715395299.2 | 2740570200 | 26.1% |  |  | 2020-07-28 | added 1 |  |  | 2020
Ministries Buildings | 2020-07-28 | 7703215 |  | 1999259406.55 | 1276160892.35 | 723098514.2 | 2740570200 | 26.38% |  |  | 2020-07-28 | added 1 |  |  | 2020
Ministries Buildings | 2020-07-28 | 19470665 |  | 2018730071.55 | 1276160892.35 | 742569179.2 | 2740570200 | 27.1% |  |  | 2020-07-28 | added 1 |  |  | 2020
Ministries Buildings | 2020-08-01 |  | 23577214.7 | 2018730071.55 | 1299738107.05 | 718991964.5 | 2740570200 | 26.24% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-08-23 | 49745 |  | 2018779816.55 | 1299738107.05 | 719041709.5 | 2740570200 | 26.24% |  |  | 2020-08-23 | added 1 |  |  | 2020
Ministries Buildings | 2020-08-25 | 14328230 |  | 2033108046.55 | 1299738107.05 | 733369939.5 | 2740570200 | 26.76% |  |  | 2020-08-25 | added 1 |  |  | 2020
Ministries Buildings | 2020-08-25 | 14328225 |  | 2047436271.55 | 1299738107.05 | 747698164.5 | 2740570200 | 27.28% |  |  | 2020-08-25 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-09-01 |  | 30170906.38 | 2047436271.55 | 1329909013.43 | 717527258.12 | 2740570200 | 26.18% |  |  |  | cash out both |  |  | 2020
Ministries Buildings | 2020-09-10 | 23375895 |  | 2070812166.55 | 1329909013.43 | 740903153.12 | 2740570200 | 27.03% |  |  | 2020-09-10 | added 1 |  |  | 2020
Ministries Buildings | 2020-10-01 | 2928255 |  | 2073740421.55 | 1329909013.43 | 743831408.12 | 2740570200 | 27.14% |  |  | 2020-10-01 | added 1 |  |  | 2020
Ministries Buildings | 2020-10-01 |  | 28627865.5 | 2073740421.55 | 1358536878.93 | 715203542.62 | 2740570200 | 26.1% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Ministries Buildings | 2020-10-04 | 2928255 |  | 2076668676.55 | 1358536878.93 | 718131797.62 | 2740570200 | 26.2% |  |  | 2020-10-04 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-10-18 | 2837565 |  | 2079506241.55 | 1358536878.93 | 720969362.62 | 2740570200 | 26.31% |  |  | 2020-10-18 | added 1 |  |  | 2020
Ministries Buildings | 2020-10-25 | 1032345 |  | 2080538586.55 | 1358536878.93 | 722001707.62 | 2740570200 | 26.34% |  |  | 2020-10-25 | added 1 |  |  | 2020
Ministries Buildings | 2020-10-28 | 3723275 |  | 2084261861.55 | 1358536878.93 | 725724982.62 | 2740570200 | 26.48% |  |  | 2020-10-28 | added 1 |  |  | 2020
Ministries Buildings | 2020-10-28 | 2590775 |  | 2086852636.55 | 1358536878.93 | 728315757.62 | 2740570200 | 26.58% |  |  | 2020-10-28 | added 1 |  |  | 2020
Ministries Buildings | 2020-10-28 | 13360535 |  | 2100213171.55 | 1358536878.93 | 741676292.62 | 2740570200 | 27.06% |  |  | 2020-10-28 | added 1 |  |  | 2020
Ministries Buildings | 2020-11-01 |  | 40400805.22 | 2100213171.55 | 1398937684.15 | 701275487.4 | 2740570200 | 25.59% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Ministries Buildings | 2020-11-11 | 424210 |  | 2100637381.55 | 1398937684.15 | 701699697.4 | 2740570200 | 25.6% |  |  | 2020-11-11 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-11-11 | 142550 |  | 2100779931.55 | 1398937684.15 | 701842247.4 | 2740570200 | 25.61% |  |  | 2020-11-11 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-11-22 | 4122020 |  | 2104901951.55 | 1398937684.15 | 705964267.4 | 2740570200 | 25.76% |  |  | 2020-11-22 | added 1 |  |  | 2020
Ministries Buildings | 2020-11-29 | 956020 |  | 2105857971.55 | 1398937684.15 | 706920287.4 | 2740570200 | 25.79% |  |  | 2020-11-29 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-11-29 | 77920 |  | 2105935891.55 | 1398937684.15 | 706998207.4 | 2740570200 | 25.8% |  |  | 2020-11-29 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-11-29 | 5853780 |  | 2111789671.55 | 1398937684.15 | 712851987.4 | 2740570200 | 26.01% |  |  | 2020-11-29 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-11-30 | 2018500 |  | 2113808171.55 | 1398937684.15 | 714870487.4 | 2740570200 | 26.08% |  |  | 2020-11-30 | added 1 |  |  | 2020
Ministries Buildings | 2020-12-01 |  | 29467721.14 | 2113808171.55 | 1428405405.29 | 685402766.26 | 2740570200 | 25.01% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Ministries Buildings | 2020-12-31 | 44100768 |  | 2157908939.55 | 1428405405.29 | 729503534.26 | 2740570200 | 26.62% |  |  | 2020-12-31 | added cash in 3 |  |  | 2020
Ministries Buildings | 2020-12-31 | 196010 |  | 2158104949.55 | 1428405405.29 | 729699544.26 | 2740570200 | 26.63% |  |  | 2020-12-31 | added cash in 3 |  |  | 2020
Ministries Buildings | 2021-01-01 |  | 28291031.43 | 2158104949.55 | 1456696436.72 | 701408512.83 | 2740570200 | 25.59% |  |  |  | cash out both |  |  | 2021
Ministries Buildings | 2021-01-06 | 2174820 |  | 2160279769.55 | 1456696436.72 | 703583332.83 | 2740570200 | 25.67% |  |  | 2021-01-06 | added 1 |  |  | 2021
Ministries Buildings | 2021-02-01 |  | 29928786.91 | 2160279769.55 | 1486625223.63 | 673654545.92 | 2740570200 | 24.58% |  |  |  | cash out both |  |  | 2021
Ministries Buildings | 2021-02-24 | 877175 |  | 2161156944.55 | 1486625223.63 | 674531720.92 | 2740570200 | 24.61% |  |  | 2021-02-24 | added cash in 3 |  |  | 2021
Ministries Buildings | 2021-02-24 | 231155 |  | 2161388099.55 | 1486625223.63 | 674762875.92 | 2740570200 | 24.62% |  |  | 2021-02-24 | added cash in 3 |  |  | 2021
Ministries Buildings | 2021-02-25 | 16645526 |  | 2178033625.55 | 1486625223.63 | 691408401.92 | 2740570200 | 25.23% |  |  | 2021-02-25 | added cash in 3 |  |  | 2021
Ministries Buildings | 2021-02-26 | 231155 |  | 2178264780.55 | 1486625223.63 | 691639556.92 | 2740570200 | 25.24% |  |  | 2021-02-26 | added 1 |  |  | 2021
Ministries Buildings | 2021-02-26 | 877175 |  | 2179141955.55 | 1486625223.63 | 692516731.92 | 2740570200 | 25.27% |  |  | 2021-02-26 | added 1 |  |  | 2021
Ministries Buildings | 2021-03-01 |  | 36200188.82 | 2179141955.55 | 1522825412.45 | 656316543.1 | 2740570200 | 23.95% |  |  |  | cash out both |  |  | 2021
Ministries Buildings | 2021-04-06 | 30488418 |  | 2209630373.55 | 1522825412.45 | 686804961.1 | 2740570200 | 25.06% |  |  | 2021-04-06 | added cash in 3 |  |  | 2021
1900
Bani Suif Substation | 2016-06-30 | 14475149 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  | 0 | 2016-06-30 | original |  |  | 2016
Bani Suif Substation | 2016-09-30 | 0 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  | 15153556 | 2016-09-30 | original |  |  | 2016
Bani Suif Substation | 2016-10-30 | 0 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  | 10121476 | 2016-10-30 | original |  |  | 2016
Bani Suif Substation | 2016-11-30 | 0 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  | 4821423 | 2016-11-30 | original |  |  | 2016
Bani Suif Substation | 2016-12-30 | 8239 | 0 | 14483388 | 0 | 14483388 | 120712211 | 12% |  | 0 | 2016-12-30 | original |  |  | 2016
Bani Suif Substation | 2017-01-31 | 0 | 0 | 14483388 | 0 | 14483388 | 120712211 | 12% |  | 12888090 | 2017-01-31 | original |  |  | 2017
Bani Suif Substation | 2017-02-28 | 0 | 0 | 14483388 | 0 | 14483388 | 120712211 | 12% |  | 6146055 | 2017-02-28 | original |  |  | 2017
Bani Suif Substation | 2017-03-31 | 13416052 | 181527 | 27899440 | 181527 | 27717913 | 120712211 | 22.96% |  | 9275154 | 2017-03-31 | original |  |  | 2017
Bani Suif Substation | 2017-04-01 |  | 3979.15 | 27899440 | 185506.15 | 27713933.85 | 120712211 | 22.96% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-04-01 |  | 161714.72 | 27899440 | 347220.87 | 27552219.13 | 120712211 | 22.82% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-04-30 | 0 | 610368 | 37203068.72 | 957588.87 | 36245479.85 | 120712211 | 30.03% |  | 5494300 | 2017-04-30 | original |  |  | 2017
Bani Suif Substation | 2017-05-01 |  | 146451.01 | 37203068.72 | 1104039.88 | 36099028.84 | 120712211 | 29.91% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-05-01 |  | 333805.27 | 37203068.72 | 1437845.15 | 35765223.57 | 120712211 | 29.63% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-05-31 | 0 | 413881 | 37203068.72 | 1851726.15 | 35351342.57 | 120712211 | 29.29% |  | 3473623 | 2017-05-31 | original |  |  | 2017
Bani Suif Substation | 2017-06-01 |  | 112913.09 | 37203068.72 | 1964639.24 | 35238429.48 | 120712211 | 29.19% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-06-01 |  | 97665.45 | 37203068.72 | 2062304.69 | 35140764.03 | 120712211 | 29.11% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-06-30 | 0 | 232463 | 37203068.72 | 2294767.69 | 34908301.03 | 120712211 | 28.92% |  | 14504056 | 2017-06-30 | original |  |  | 2017
Bani Suif Substation | 2017-06-30 | 1820433.25 |  | 39023501.97 | 2294767.69 | 36728734.28 | 120712211 | 30.43% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
Bani Suif Substation | 2017-07-01 |  | 137635.9 | 39023501.97 | 2432403.59 | 36591098.38 | 120712211 | 30.31% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-07-01 |  | 493222.62 | 39023501.97 | 2925626.21 | 36097875.76 | 120712211 | 29.9% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-07-31 | 0 | 4528358 | 39023501.97 | 7453984.21 | 31569517.76 | 120712211 | 26.15% |  | 2268981 | 2017-07-31 | original |  |  | 2017
Bani Suif Substation | 2017-07-31 | 3827674.82 |  | 43845134.01 | 7453984.21 | 36391149.8 | 120712211 | 30.15% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
Bani Suif Substation | 2017-07-31 | 2929690.54 |  | 46774824.55 | 7453984.21 | 39320840.34 | 120712211 | 32.57% |  |  | 2017-07-31 | added cash in 3 |  |  | 2017
Bani Suif Substation | 2017-08-01 |  | 2222769.56 | 46774824.55 | 9676753.77 | 37098070.78 | 120712211 | 30.73% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-08-01 |  | 693768.3 | 46774824.55 | 10370522.07 | 36404302.48 | 120712211 | 30.16% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-08-31 | 0 | 2949432 | 46774824.55 | 13319954.07 | 33454870.48 | 120712211 | 27.71% |  | 1621441 | 2017-08-31 | original |  |  | 2017
Bani Suif Substation | 2017-08-31 | 3000000 |  | 49774824.55 | 13319954.07 | 36454870.48 | 120712211 | 30.2% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Bani Suif Substation | 2017-08-31 | 7250421.81 |  | 57025246.36 | 13319954.07 | 43705292.29 | 120712211 | 36.21% |  |  | 2017-08-31 | added cash in 3 |  |  | 2017
Bani Suif Substation | 2017-09-01 |  | 114386.79 | 57025246.36 | 13434340.86 | 43590905.5 | 120712211 | 36.11% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-09-01 |  | 310815.75 | 57025246.36 | 13745156.61 | 43280089.75 | 120712211 | 35.85% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-09-30 | 0 | 8575834 | 57025246.36 | 22320990.61 | 34704255.75 | 120712211 | 28.75% |  | 2833459 | 2017-09-30 | original |  |  | 2017
Bani Suif Substation | 2017-10-01 |  | 262682.67 | 57025246.36 | 22583673.28 | 34441573.08 | 120712211 | 28.53% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-10-01 |  | 1371732.24 | 57025246.36 | 23955405.52 | 33069840.84 | 120712211 | 27.4% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-10-31 | 0 | 7781298 | 57025246.36 | 31736703.52 | 25288542.84 | 120712211 | 20.95% |  | 6985512 | 2017-10-31 | original |  |  | 2017
Bani Suif Substation | 2017-11-01 |  | 500225.04 | 57025246.36 | 32236928.56 | 24788317.8 | 120712211 | 20.54% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-11-01 |  | 1099505.39 | 57025246.36 | 33336433.95 | 23688812.41 | 120712211 | 19.62% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-11-30 | 11288949 | 7505262 | 68314195.36 | 40841695.95 | 27472499.41 | 120712211 | 22.76% |  | 3003863 | 2017-11-30 | original |  |  | 2017
Bani Suif Substation | 2017-12-01 |  | 661989.05 | 68314195.36 | 41503685 | 26810510.36 | 120712211 | 22.21% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-12-01 |  | 816561.4 | 68314195.36 | 42320246.4 | 25993948.96 | 120712211 | 21.53% |  |  |  | cash out both |  |  | 2017
Bani Suif Substation | 2017-12-31 | 0 | 10160970 | 68314195.36 | 52481216.4 | 15832978.96 | 120712211 | 13.12% |  | 2335376 | 2017-12-31 | original |  |  | 2017
Bani Suif Substation | 2018-01-01 |  | 2202032.37 | 68314195.36 | 54683248.77 | 13630946.59 | 120712211 | 11.29% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-01-01 |  | 5681658.67 | 68314195.36 | 60364907.44 | 7949287.92 | 120712211 | 6.585% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-01-30 | 7502554.18 |  | 77440952.95 | 60364907.44 | 17076045.51 | 120712211 | 14.15% |  |  | 2018-01-30 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-02-01 |  | 170029.07 | 77440952.95 | 60534936.51 | 16906016.44 | 120712211 | 14.01% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-02-01 |  | 2489669.83 | 77440952.95 | 63024606.34 | 14416346.61 | 120712211 | 11.94% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-03-01 |  | 2288273.44 | 83085978.1 | 65312879.78 | 17773098.32 | 120712211 | 14.72% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-03-01 |  | 5892599.56 | 83085978.1 | 71205479.34 | 11880498.76 | 120712211 | 9.842% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-03-11 | 37661.77 |  | 83123639.87 | 71205479.34 | 11918160.53 | 120712211 | 9.873% |  |  | 2018-03-11 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-03-28 | 3591432.79 |  | 86715072.66 | 71205479.34 | 15509593.32 | 120712211 | 12.85% |  |  | 2018-03-28 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-04-01 |  | 364070.63 | 86715072.66 | 71569549.97 | 15145522.69 | 120712211 | 12.55% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-04-01 |  | 2615839.46 | 86715072.66 | 74185389.43 | 12529683.23 | 120712211 | 10.38% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-04-19 | 9601100.35 |  | 96316173.01 | 74185389.43 | 22130783.58 | 120712211 | 18.33% |  |  | 2018-04-19 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-05-01 |  | 824585.87 | 96316173.01 | 75009975.3 | 21306197.71 | 120712211 | 17.65% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-05-01 |  | 5360468.71 | 96316173.01 | 80370444.01 | 15945729 | 120712211 | 13.21% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-05-27 | 6834280.65 |  | 103150453.66 | 80370444.01 | 22780009.65 | 120712211 | 18.87% |  |  | 2018-05-27 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-06-01 |  | 1823759.17 | 103150453.66 | 82194203.18 | 20956250.48 | 120712211 | 17.36% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-06-01 |  | 5059759.02 | 103150453.66 | 87253962.2 | 15896491.46 | 120712211 | 13.17% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-06-10 | 674994.52 |  | 106564184.45 | 87253962.2 | 19310222.25 | 120712211 | 16% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-06-10 | 13499 |  | 106577683.45 | 87253962.2 | 19323721.25 | 120712211 | 16.01% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-07-01 |  | 185555.09 | 106577683.45 | 87439517.29 | 19138166.16 | 120712211 | 15.85% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-07-01 |  | 7021699.84 | 106577683.45 | 94461217.13 | 12116466.32 | 120712211 | 10.04% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-07-11 | 3596 |  | 106581279.45 | 94461217.13 | 12120062.32 | 120712211 | 10.04% |  |  | 2018-07-11 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-07-11 | 1889200.95 |  | 108470480.4 | 94461217.13 | 14009263.27 | 120712211 | 11.61% |  |  | 2018-07-11 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-07-17 | 8239.2 |  | 108478719.6 | 94461217.13 | 14017502.47 | 120712211 | 11.61% |  |  | 2018-07-17 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-07-31 | 18180.41 |  | 108496900.01 | 94461217.13 | 14035682.88 | 120712211 | 11.63% |  |  | 2018-07-31 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-07-31 | 4788095.03 |  | 113284995.04 | 94461217.13 | 18823777.91 | 120712211 | 15.59% |  |  | 2018-07-31 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-08-01 |  | 380475.97 | 113284995.04 | 94841693.1 | 18443301.94 | 120712211 | 15.28% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-08-01 |  | 2057357.75 | 113284995.04 | 96899050.85 | 16385944.19 | 120712211 | 13.57% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-09-01 |  | 334380.75 | 113284995.04 | 97233431.6 | 16051563.44 | 120712211 | 13.3% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-09-01 |  | 2473581.56 | 113284995.04 | 99707013.16 | 13577981.88 | 120712211 | 11.25% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-09-17 | 2058163.65 |  | 115343158.69 | 99707013.16 | 15636145.53 | 120712211 | 12.95% |  |  | 2018-09-17 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-10-01 |  | 773966.76 | 117037045.84 | 100480979.92 | 16556065.92 | 120712211 | 13.72% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-10-01 |  | 4826165.01 | 117037045.84 | 105307144.93 | 11729900.91 | 120712211 | 9.717% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-10-25 | 11354292.42 |  | 128391338.26 | 105307144.93 | 23084193.33 | 120712211 | 19.12% |  |  | 2018-10-25 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-10-29 | 482231.1 |  | 128873569.36 | 105307144.93 | 23566424.43 | 120712211 | 19.52% |  |  | 2018-10-29 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-10-29 | 2171210.17 |  | 131044779.53 | 105307144.93 | 25737634.6 | 120712211 | 21.32% |  |  | 2018-10-29 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-11-01 |  | 282393.75 | 131044779.53 | 105589538.68 | 25455240.85 | 120712211 | 21.09% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-11-01 |  | 4043499.36 | 131044779.53 | 109633038.04 | 21411741.49 | 120712211 | 17.74% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-11-12 | 517711.72 |  | 131562491.25 | 109633038.04 | 21929453.21 | 120712211 | 18.17% |  |  | 2018-11-12 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-11-15 | 539875.47 |  | 132102366.72 | 109633038.04 | 22469328.68 | 120712211 | 18.61% |  |  | 2018-11-15 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-11-15 | 5138.1 |  | 132107504.82 | 109633038.04 | 22474466.78 | 120712211 | 18.62% |  |  | 2018-11-15 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2018-12-01 |  | 65751.05 | 132107504.82 | 109698789.09 | 22408715.73 | 120712211 | 18.56% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-12-01 |  | 3142408.48 | 132107504.82 | 112841197.57 | 19266307.25 | 120712211 | 15.96% |  |  |  | cash out both |  |  | 2018
Bani Suif Substation | 2018-12-12 | 3472508.49 |  | 135580013.31 | 112841197.57 | 22738815.74 | 120712211 | 18.84% |  |  | 2018-12-12 | added cash in 3 |  |  | 2018
Bani Suif Substation | 2019-01-01 |  | 68641.49 | 135580013.31 | 112909839.06 | 22670174.25 | 120712211 | 18.78% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-01-01 |  | 3296550.54 | 135580013.31 | 116206389.6 | 19373623.71 | 120712211 | 16.05% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-01-09 | 1692379.55 |  | 137272392.86 | 116206389.6 | 21066003.26 | 120712211 | 17.45% |  |  | 2019-01-09 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-01-30 | 2150410.67 |  | 139422803.53 | 116206389.6 | 23216413.93 | 120712211 | 19.23% |  |  | 2019-01-30 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-02-01 |  | 175738.13 | 139422803.53 | 116382127.73 | 23040675.8 | 120712211 | 19.09% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-02-01 |  | 1302737.87 | 139422803.53 | 117684865.6 | 21737937.93 | 120712211 | 18.01% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-02-24 | 149332.9 |  | 139572136.43 | 117684865.6 | 21887270.83 | 120712211 | 18.13% |  |  | 2019-02-24 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-02-27 | 4261673.16 |  | 143833809.59 | 117684865.6 | 26148943.99 | 120712211 | 21.66% |  |  | 2019-02-27 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-02-28 | 1000000 |  | 144833809.59 | 117684865.6 | 27148943.99 | 120712211 | 22.49% |  |  | 2019-02-28 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-02-28 | 1075465.03 |  | 145909274.62 | 117684865.6 | 28224409.02 | 120712211 | 23.38% |  |  | 2019-02-28 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-03-01 |  | 81868.17 | 145909274.62 | 117766733.77 | 28142540.85 | 120712211 | 23.31% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-03-01 |  | 2320397.74 | 145909274.62 | 120087131.51 | 25822143.11 | 120712211 | 21.39% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-04-01 |  | 40000 | 145909274.62 | 120127131.51 | 25782143.11 | 120712211 | 21.36% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-04-01 |  | 622565.72 | 145909274.62 | 120749697.23 | 25159577.39 | 120712211 | 20.84% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-04-15 | 34200.69 |  | 145943475.31 | 120749697.23 | 25193778.08 | 120712211 | 20.87% |  |  | 2019-04-15 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-04-18 | 1949637.35 |  | 147893112.66 | 120749697.23 | 27143415.43 | 120712211 | 22.49% |  |  | 2019-04-18 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-05-01 |  | 126306.12 | 147893112.66 | 120876003.35 | 27017109.31 | 120712211 | 22.38% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-05-01 |  | 732351.24 | 147893112.66 | 121608354.59 | 26284758.07 | 120712211 | 21.77% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-06-01 |  | 5372.02 | 147893112.66 | 121613726.61 | 26279386.05 | 120712211 | 21.77% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-06-01 |  | 882940.06 | 147893112.66 | 122496666.67 | 25396445.99 | 120712211 | 21.04% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-07-01 |  | 240126.7 | 147893112.66 | 122736793.37 | 25156319.29 | 120712211 | 20.84% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-07-17 | 2049127.88 |  | 149942240.54 | 122736793.37 | 27205447.17 | 120712211 | 22.54% |  |  | 2019-07-17 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-08-01 |  | 707538.9 | 149942240.54 | 123444332.27 | 26497908.27 | 120712211 | 21.95% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-08-05 | 168482.17 |  | 150110722.71 | 123444332.27 | 26666390.44 | 120712211 | 22.09% |  |  | 2019-08-05 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-09-01 |  | 561878.05 | 150110722.71 | 124006210.32 | 26104512.39 | 120712211 | 21.63% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-10-01 |  | 238344.2 | 150110722.71 | 124244554.52 | 25866168.19 | 120712211 | 21.43% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-10-20 | 9999405.8 |  | 160110128.51 | 124244554.52 | 35865573.99 | 120712211 | 29.71% |  |  | 2019-10-20 | added cash in 3 |  |  | 2019
Bani Suif Substation | 2019-11-01 |  | 290101.52 | 160110128.51 | 124534656.04 | 35575472.47 | 120712211 | 29.47% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-11-01 |  | 163167.26 | 160110128.51 | 124697823.3 | 35412305.21 | 120712211 | 29.34% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2019-12-01 |  | 9710316.83 | 160110128.51 | 134408140.13 | 25701988.38 | 120712211 | 21.29% |  |  |  | cash out both |  |  | 2019
Bani Suif Substation | 2020-01-01 |  | 36240.98 | 160110128.51 | 134444381.11 | 25665747.4 | 120712211 | 21.26% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-02-01 |  | 326290.52 | 160110128.51 | 134770671.63 | 25339456.88 | 120712211 | 20.99% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-03-01 |  | 102293.51 | 160110128.51 | 134872965.14 | 25237163.37 | 120712211 | 20.91% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-04-01 |  | 41927.7 | 160110128.51 | 134914892.84 | 25195235.67 | 120712211 | 20.87% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-05-01 |  | 211021.03 | 160110128.51 | 135125913.87 | 24984214.64 | 120712211 | 20.7% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-05-01 |  | 172687.14 | 160110128.51 | 135298601.01 | 24811527.5 | 120712211 | 20.55% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-06-01 |  | 7000 | 160110128.51 | 135305601.01 | 24804527.5 | 120712211 | 20.55% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-07-01 |  | 52642.88 | 160110128.51 | 135358243.89 | 24751884.62 | 120712211 | 20.5% |  |  |  | cash out both |  |  | 2020
Bani Suif Substation | 2020-09-28 | 18610.78 |  | 160128739.29 | 135358243.89 | 24770495.4 | 120712211 | 20.52% |  |  | 2020-09-28 | added cash in 3 |  |  | 2020
Bani Suif Substation | 2020-09-28 | 758220.28 |  | 160886959.57 | 135358243.89 | 25528715.68 | 120712211 | 21.15% |  |  | 2020-09-28 | added cash in 3 |  |  | 2020
Bani Suif Substation | 2020-10-01 |  | 96928.79 | 160886959.57 | 135455172.68 | 25431786.89 | 120712211 | 21.07% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Bani Suif Substation | 2020-11-01 |  | 59325 | 160886959.57 | 135514497.68 | 25372461.89 | 120712211 | 21.02% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Bani Suif Substation | 2020-11-22 | 903786.81 |  | 161790746.38 | 135514497.68 | 26276248.7 | 120712211 | 21.77% |  |  | 2020-11-22 | added cash in 3 |  |  | 2020
Bani Suif Substation | 2021-01-11 | 3316128.41 |  | 169436186.41 | 135514497.68 | 33921688.73 | 120712211 | 28.1% |  |  | 2021-01-11 | added cash in 3 |  |  | 2021
Bani Suif Substation | 2021-01-20 | 2415310.91 |  | 171851497.32 | 135514497.68 | 36336999.64 | 120712211 | 30.1% |  |  | 2021-01-20 | added cash in 3 |  |  | 2021
Bani Suif Substation | 2021-01-31 | 34200 |  | 171885697.32 | 135514497.68 | 36371199.64 | 120712211 | 30.13% |  |  | 2021-01-31 | added cash in 3 |  |  | 2021
Bani Suif Substation | 2021-02-01 | 663480 |  | 172549177.32 | 135514497.68 | 37034679.64 | 120712211 | 30.68% |  |  | 2021-02-01 | added 1 |  |  | 2021
Bani Suif Substation | 2021-02-08 | 5000000 |  | 177549177.32 | 135514497.68 | 42034679.64 | 120712211 | 34.82% |  |  | 2021-02-08 | added cash in 3 |  |  | 2021
Bani Suif Substation | 2021-02-24 | 25000 |  | 177574177.32 | 135514497.68 | 42059679.64 | 120712211 | 34.84% |  |  | 2021-02-24 | added cash in 3 |  |  | 2021
1900
Royal City Mall | 2017-05-01 |  | 2186 | 0 | 2186 | -2186 | 527037820 | -0.0004148% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-06-01 |  | 40000 | 0 | 42186 | -42186 | 527037820 | -0.008004% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-06-30 | 58500000 | 1061909 | 58500000 | 1104095 | 57395905 | 527037820 | 10.89% |  | 0 | 2017-06-30 | original |  |  | 2017
Royal City Mall | 2017-06-30 | 58500000 |  | 117000000 | 1104095 | 115895905 | 527037820 | 21.99% |  |  | 2017-06-30 | added cash in 3 |  |  | 2017
Royal City Mall | 2017-07-01 |  | 3664451.56 | 117000000 | 4768546.56 | 112231453.44 | 527037820 | 21.29% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-07-31 | 0 | 1431114 | 117000000 | 6199660.56 | 110800339.44 | 527037820 | 21.02% |  | 0 | 2017-07-31 | original |  |  | 2017
Royal City Mall | 2017-08-01 |  | 958479.48 | 117000000 | 7158140.04 | 109841859.96 | 527037820 | 20.84% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-08-31 | 0 | 5812269 | 117000000 | 12970409.04 | 104029590.96 | 527037820 | 19.74% |  | 3918482 | 2017-08-31 | original |  |  | 2017
Royal City Mall | 2017-09-01 |  | 1090092.6 | 117000000 | 14060501.64 | 102939498.36 | 527037820 | 19.53% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-09-30 | 0 | 3552315 | 117000000 | 17612816.64 | 99387183.36 | 527037820 | 18.86% |  | 4957067 | 2017-09-30 | original |  |  | 2017
Royal City Mall | 2017-10-01 |  | 8237982.32 | 117000000 | 25850798.96 | 91149201.04 | 527037820 | 17.29% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-10-31 | 5235332 | 12048418 | 122235332 | 37899216.96 | 84336115.04 | 527037820 | 16% |  | 8111601 | 2017-10-31 | original |  |  | 2017
Royal City Mall | 2017-10-31 | 5235331.6 |  | 127470663.6 | 37899216.96 | 89571446.64 | 527037820 | 17% |  |  | 2017-10-31 | added cash in 3 |  |  | 2017
Royal City Mall | 2017-11-01 |  | 3499538.01 | 127470663.6 | 41398754.97 | 86071908.63 | 527037820 | 16.33% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-11-30 | 22592835 | 7727414 | 150063498.6 | 49126168.97 | 100937329.63 | 527037820 | 19.15% |  | 10259672 | 2017-11-30 | original |  |  | 2017
Royal City Mall | 2017-11-30 | 4892835.45 |  | 154956334.05 | 49126168.97 | 105830165.08 | 527037820 | 20.08% |  |  | 2017-11-30 | added cash in 3 |  |  | 2017
Royal City Mall | 2017-11-30 | 1000000 |  | 155956334.05 | 49126168.97 | 106830165.08 | 527037820 | 20.27% |  |  | 2017-11-30 | added cash in 3 |  |  | 2017
Royal City Mall | 2017-12-01 |  | 3197976.11 | 155956334.05 | 52324145.08 | 103632188.97 | 527037820 | 19.66% |  |  |  | cash out both |  |  | 2017
Royal City Mall | 2017-12-01 | 7926742.1 |  | 163883076.15 | 52324145.08 | 111558931.07 | 527037820 | 21.17% |  |  | 2017-12-01 | added cash in 3 |  |  | 2017
Royal City Mall | 2017-12-31 | 7926742 | 21213020 | 171809818.15 | 73537165.08 | 98272653.07 | 527037820 | 18.65% |  | 10108224 | 2017-12-31 | original |  |  | 2017
Royal City Mall | 2018-01-01 |  | 9437622.55 | 171809818.15 | 82974787.63 | 88835030.52 | 527037820 | 16.86% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-01-22 | 10437271.65 |  | 182247089.8 | 82974787.63 | 99272302.17 | 527037820 | 18.84% |  |  | 2018-01-22 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-02-01 |  | 9038900.33 | 182247089.8 | 92013687.96 | 90233401.84 | 527037820 | 17.12% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-02-28 | 5169557.65 |  | 187416647.45 | 92013687.96 | 95402959.49 | 527037820 | 18.1% |  |  | 2018-02-28 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-03-01 |  | 12250207.57 | 187416647.45 | 104263895.53 | 83152751.92 | 527037820 | 15.78% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-04-01 |  | 18440458.23 | 187416647.45 | 122704353.76 | 64712293.69 | 527037820 | 12.28% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-04-12 | 2000000 |  | 189416647.45 | 122704353.76 | 66712293.69 | 527037820 | 12.66% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-05-01 |  | 14258130.74 | 189416647.45 | 136962484.5 | 52454162.95 | 527037820 | 9.953% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-05-21 | 12495801.4 |  | 201912448.85 | 136962484.5 | 64949964.35 | 527037820 | 12.32% |  |  | 2018-05-21 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-06-01 |  | 11467950.99 | 201912448.85 | 148430435.49 | 53482013.36 | 527037820 | 10.15% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-06-19 | 2000000 |  | 203912448.85 | 148430435.49 | 55482013.36 | 527037820 | 10.53% |  |  | 2018-06-19 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-06-24 | 8703262.4 |  | 212615711.25 | 148430435.49 | 64185275.76 | 527037820 | 12.18% |  |  | 2018-06-24 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-07-01 |  | 9559328.95 | 212615711.25 | 157989764.44 | 54625946.81 | 527037820 | 10.36% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-08-01 |  | 7832899.99 | 212615711.25 | 165822664.43 | 46793046.82 | 527037820 | 8.878% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-08-14 | 6085844.5 |  | 218701555.75 | 165822664.43 | 52878891.32 | 527037820 | 10.03% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-08-28 | 6397146.2 |  | 225098701.95 | 165822664.43 | 59276037.52 | 527037820 | 11.25% |  |  | 2018-08-28 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-09-01 |  | 8011052.92 | 225098701.95 | 173833717.35 | 51264984.6 | 527037820 | 9.727% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-09-23 | 5786688.5 |  | 230885390.45 | 173833717.35 | 57051673.1 | 527037820 | 10.82% |  |  | 2018-09-23 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-10-01 |  | 10688187.36 | 230885390.45 | 184521904.71 | 46363485.74 | 527037820 | 8.797% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-10-31 | 1000000 |  | 231885390.45 | 184521904.71 | 47363485.74 | 527037820 | 8.987% |  |  | 2018-10-31 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-11-01 |  | 13048898.77 | 231885390.45 | 197570803.48 | 34314586.97 | 527037820 | 6.511% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-11-12 | 3482306.95 |  | 235367697.4 | 197570803.48 | 37796893.92 | 527037820 | 7.172% |  |  | 2018-11-12 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-11-22 | 9822648.05 |  | 245190345.45 | 197570803.48 | 47619541.97 | 527037820 | 9.035% |  |  | 2018-11-22 | added cash in 3 |  |  | 2018
Royal City Mall | 2018-12-01 |  | 9472756.08 | 245190345.45 | 207043559.56 | 38146785.89 | 527037820 | 7.238% |  |  |  | cash out both |  |  | 2018
Royal City Mall | 2018-12-17 | 6339338.45 |  | 251529683.9 | 207043559.56 | 44486124.34 | 527037820 | 8.441% |  |  | 2018-12-17 | added cash in 3 |  |  | 2018
Royal City Mall | 2019-01-01 |  | 11027066.71 | 251529683.9 | 218070626.27 | 33459057.63 | 527037820 | 6.349% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-01-21 | 5980045.3 |  | 257509729.2 | 218070626.27 | 39439102.93 | 527037820 | 7.483% |  |  | 2019-01-21 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-02-01 |  | 11015291.19 | 257509729.2 | 229085917.46 | 28423811.74 | 527037820 | 5.393% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-02-12 | 6570751.8 |  | 264080481 | 229085917.46 | 34994563.54 | 527037820 | 6.64% |  |  | 2019-02-12 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-03-01 |  | 12464172.49 | 264080481 | 241550089.95 | 22530391.05 | 527037820 | 4.275% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-03-14 | 7847127.4 |  | 271927608.4 | 241550089.95 | 30377518.45 | 527037820 | 5.764% |  |  | 2019-03-14 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-04-01 |  | 7322125.13 | 271927608.4 | 248872215.08 | 23055393.32 | 527037820 | 4.375% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-04-10 | 5868379.55 |  | 277795987.95 | 248872215.08 | 28923772.87 | 527037820 | 5.488% |  |  | 2019-04-10 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-05-01 |  | 15513586.9 | 277795987.95 | 264385801.98 | 13410185.97 | 527037820 | 2.544% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-05-21 | 4501953.5 |  | 282297941.45 | 264385801.98 | 17912139.47 | 527037820 | 3.399% |  |  | 2019-05-21 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-06-01 |  | 8246919.25 | 282297941.45 | 272632721.23 | 9665220.22 | 527037820 | 1.834% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-06-03 | 5000000 |  | 287297941.45 | 272632721.23 | 14665220.22 | 527037820 | 2.783% |  |  | 2019-06-03 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-06-13 | 9999974.75 |  | 297297916.2 | 272632721.23 | 24665194.97 | 527037820 | 4.68% |  |  | 2019-06-13 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-07-01 |  | 11142490.15 | 297297916.2 | 283775211.38 | 13522704.82 | 527037820 | 2.566% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-07-22 | 5072118.4 |  | 302370034.6 | 283775211.38 | 18594823.22 | 527037820 | 3.528% |  |  | 2019-07-22 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-07-29 | 93247.4 |  | 302463282 | 283775211.38 | 18688070.62 | 527037820 | 3.546% |  |  | 2019-07-29 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-07-29 | 10000000 |  | 312463282 | 283775211.38 | 28688070.62 | 527037820 | 5.443% |  |  | 2019-07-29 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-08-01 |  | 8488199.86 | 312463282 | 292263411.24 | 20199870.76 | 527037820 | 3.833% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-09-01 |  | 6511826.72 | 312463282 | 298775237.96 | 13688044.04 | 527037820 | 2.597% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-09-19 | 6824453.7 |  | 319287735.7 | 298775237.96 | 20512497.74 | 527037820 | 3.892% |  |  | 2019-09-19 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-09-19 | 10000000 |  | 329287735.7 | 298775237.96 | 30512497.74 | 527037820 | 5.789% |  |  | 2019-09-19 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-10-01 |  | 28549777.89 | 329287735.7 | 327325015.85 | 1962719.85 | 527037820 | 0.3724% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-10-09 | 1782000 |  | 331069735.7 | 327325015.85 | 3744719.85 | 527037820 | 0.7105% |  |  | 2019-10-09 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-10-15 | 4014037.5 |  | 335083773.2 | 327325015.85 | 7758757.35 | 527037820 | 1.472% |  |  | 2019-10-15 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-10-24 | 6453450.6 |  | 341537223.8 | 327325015.85 | 14212207.95 | 527037820 | 2.697% |  |  | 2019-10-24 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-11-01 |  | 7306520.58 | 341537223.8 | 334631536.43 | 6905687.37 | 527037820 | 1.31% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-11-19 | 9088642.9 |  | 350625866.7 | 334631536.43 | 15994330.27 | 527037820 | 3.035% |  |  | 2019-11-19 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-11-19 | 2421804.9 |  | 353047671.6 | 334631536.43 | 18416135.17 | 527037820 | 3.494% |  |  | 2019-11-19 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-12-01 |  | 19807621.99 | 353047671.6 | 354439158.42 | -1391486.82 | 527037820 | -0.264% |  |  |  | cash out both |  |  | 2019
Royal City Mall | 2019-12-25 | 4390934.75 |  | 357438606.35 | 354439158.42 | 2999447.93 | 527037820 | 0.5691% |  |  | 2019-12-25 | added cash in 3 |  |  | 2019
Royal City Mall | 2019-12-25 | 9972683.95 |  | 367411290.3 | 354439158.42 | 12972131.88 | 527037820 | 2.461% |  |  | 2019-12-25 | added cash in 3 |  |  | 2019
Royal City Mall | 2020-01-01 |  | 20361632.01 | 367411290.3 | 374800790.43 | -7389500.13 | 527037820 | -1.402% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-01-16 | 8025338.3 |  | 375436628.6 | 374800790.43 | 635838.17 | 527037820 | 0.1206% |  |  | 2020-01-16 | added 1 |  |  | 2020
Royal City Mall | 2020-01-16 | 7060326.8 |  | 382496955.4 | 374800790.43 | 7696164.97 | 527037820 | 1.46% |  |  | 2020-01-16 | added 1 |  |  | 2020
Royal City Mall | 2020-01-27 | 8025338.3 |  | 390522293.7 | 374800790.43 | 15721503.27 | 527037820 | 2.983% |  |  | 2020-01-27 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-01-27 | 7060326.8 |  | 397582620.5 | 374800790.43 | 22781830.07 | 527037820 | 4.323% |  |  | 2020-01-27 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-02-01 |  | 14527230.19 | 397582620.5 | 389328020.62 | 8254599.88 | 527037820 | 1.566% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-03-01 |  | 12911045.97 | 397582620.5 | 402239066.59 | -4656446.09 | 527037820 | -0.8835% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-03-03 | 9240902.25 |  | 406823522.75 | 402239066.59 | 4584456.16 | 527037820 | 0.8699% |  |  | 2020-03-03 | added 1 |  |  | 2020
Royal City Mall | 2020-03-17 | 5000000 |  | 411823522.75 | 402239066.59 | 9584456.16 | 527037820 | 1.819% |  |  | 2020-03-17 | added 1 |  |  | 2020
Royal City Mall | 2020-03-17 | 1000000 |  | 412823522.75 | 402239066.59 | 10584456.16 | 527037820 | 2.008% |  |  | 2020-03-17 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-03-17 | 2000000 |  | 414823522.75 | 402239066.59 | 12584456.16 | 527037820 | 2.388% |  |  | 2020-03-17 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-03-23 | 5150000 |  | 419973522.75 | 402239066.59 | 17734456.16 | 527037820 | 3.365% |  |  | 2020-03-23 | added 1 |  |  | 2020
Royal City Mall | 2020-03-23 | 2000000 |  | 421973522.75 | 402239066.59 | 19734456.16 | 527037820 | 3.744% |  |  | 2020-03-23 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-03-23 | 1150000 |  | 423123522.75 | 402239066.59 | 20884456.16 | 527037820 | 3.963% |  |  | 2020-03-23 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-03-31 | 1745943.7 |  | 424869466.45 | 402239066.59 | 22630399.86 | 527037820 | 4.294% |  |  | 2020-03-31 | added 1 |  |  | 2020
Royal City Mall | 2020-04-01 |  | 5751087.14 | 424869466.45 | 407990153.73 | 16879312.72 | 527037820 | 3.203% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-04-09 | 2000000 |  | 426869466.45 | 407990153.73 | 18879312.72 | 527037820 | 3.582% |  |  | 2020-04-09 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-04-09 | 1000000 |  | 427869466.45 | 407990153.73 | 19879312.72 | 527037820 | 3.772% |  |  | 2020-04-09 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-04-26 | 500000 |  | 428369466.45 | 407990153.73 | 20379312.72 | 527037820 | 3.867% |  |  | 2020-04-26 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-04-26 | 2000000 |  | 430369466.45 | 407990153.73 | 22379312.72 | 527037820 | 4.246% |  |  | 2020-04-26 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-04-29 | 500000 |  | 430869466.45 | 407990153.73 | 22879312.72 | 527037820 | 4.341% |  |  | 2020-04-29 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-05-01 |  | 8838218.19 | 430869466.45 | 416828371.92 | 14041094.53 | 527037820 | 2.664% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-05-20 | 2161790.65 |  | 433031257.1 | 416828371.92 | 16202885.18 | 527037820 | 3.074% |  |  | 2020-05-20 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-05-20 | 2838209.35 |  | 435869466.45 | 416828371.92 | 19041094.53 | 527037820 | 3.613% |  |  | 2020-05-20 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-05-20 | 10000000 |  | 445869466.45 | 416828371.92 | 29041094.53 | 527037820 | 5.51% |  |  | 2020-05-20 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-06-01 |  | 8736347.34 | 445869466.45 | 425564719.26 | 20304747.19 | 527037820 | 3.853% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-06-10 | 10000000 |  | 455869466.45 | 425564719.26 | 30304747.19 | 527037820 | 5.75% |  |  | 2020-06-10 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-06-10 | 194453.1 |  | 456063919.55 | 425564719.26 | 30499200.29 | 527037820 | 5.787% |  |  | 2020-06-10 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-06-23 | 7400000 |  | 463463919.55 | 425564719.26 | 37899200.29 | 527037820 | 7.191% |  |  | 2020-06-23 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-07-01 |  | 7457993.59 | 463463919.55 | 433022712.85 | 30441206.7 | 527037820 | 5.776% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-07-09 | 7318070.05 |  | 470781989.6 | 433022712.85 | 37759276.75 | 527037820 | 7.164% |  |  | 2020-07-09 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-07-29 | 2500000 |  | 473281989.6 | 433022712.85 | 40259276.75 | 527037820 | 7.639% |  |  | 2020-07-29 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-08-01 |  | 6124140.97 | 473281989.6 | 439146853.82 | 34135135.78 | 527037820 | 6.477% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-08-19 | 2500000 |  | 475781989.6 | 439146853.82 | 36635135.78 | 527037820 | 6.951% |  |  | 2020-08-19 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-08-19 | 2036519.55 |  | 477818509.15 | 439146853.82 | 38671655.33 | 527037820 | 7.338% |  |  | 2020-08-19 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-09-01 |  | 6261350.01 | 477818509.15 | 445408203.83 | 32410305.32 | 527037820 | 6.15% |  |  |  | cash out both |  |  | 2020
Royal City Mall | 2020-09-20 | 2000000 |  | 479818509.15 | 445408203.83 | 34410305.32 | 527037820 | 6.529% |  |  | 2020-09-20 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-09-20 | 5099443.8 |  | 484917952.95 | 445408203.83 | 39509749.12 | 527037820 | 7.497% |  |  | 2020-09-20 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-10-01 |  | 6208903.56 | 484917952.95 | 451617107.39 | 33300845.56 | 527037820 | 6.318% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Royal City Mall | 2020-10-22 | 2000000 |  | 486917952.95 | 451617107.39 | 35300845.56 | 527037820 | 6.698% |  |  | 2020-10-22 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-10-22 | 1000000 |  | 487917952.95 | 451617107.39 | 36300845.56 | 527037820 | 6.888% |  |  | 2020-10-22 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-11-01 |  | 2816247.7 | 487917952.95 | 454433355.09 | 33484597.86 | 527037820 | 6.353% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Royal City Mall | 2020-11-24 | 1556155.7 |  | 489474108.65 | 454433355.09 | 35040753.56 | 527037820 | 6.649% |  |  | 2020-11-24 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-11-24 | 2000000 |  | 491474108.65 | 454433355.09 | 37040753.56 | 527037820 | 7.028% |  |  | 2020-11-24 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-11-24 | 1443844.3 |  | 492917952.95 | 454433355.09 | 38484597.86 | 527037820 | 7.302% |  |  | 2020-11-24 | added cash in 3 |  |  | 2020
Royal City Mall | 2020-12-01 |  | 3241562.12 | 492917952.95 | 457674917.21 | 35243035.74 | 527037820 | 6.687% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Royal City Mall | 2021-01-01 |  | 5074964.39 | 492917952.95 | 462749881.6 | 30168071.35 | 527037820 | 5.724% |  |  |  | cash out both |  |  | 2021
Royal City Mall | 2021-01-06 | 5395558.1 |  | 498313511.05 | 462749881.6 | 35563629.45 | 527037820 | 6.748% |  |  | 2021-01-06 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-01-06 | 8433867.1 |  | 506747378.15 | 462749881.6 | 43997496.55 | 527037820 | 8.348% |  |  | 2021-01-06 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-01-21 | 8894768.85 |  | 515642147 | 462749881.6 | 52892265.4 | 527037820 | 10.04% |  |  | 2021-01-21 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-02-01 |  | 4112738.99 | 515642147 | 466862620.59 | 48779526.41 | 527037820 | 9.255% |  |  |  | cash out both |  |  | 2021
Royal City Mall | 2021-02-09 | 2000000 |  | 517642147 | 466862620.59 | 50779526.41 | 527037820 | 9.635% |  |  | 2021-02-09 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-02-09 | 1184508.35 |  | 518826655.35 | 466862620.59 | 51964034.76 | 527037820 | 9.86% |  |  | 2021-02-09 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-03-01 |  | 4153763.79 | 518826655.35 | 471016384.38 | 47810270.97 | 527037820 | 9.072% |  |  |  | cash out both |  |  | 2021
Royal City Mall | 2021-03-18 | 1107014.9 |  | 519933670.25 | 471016384.38 | 48917285.87 | 527037820 | 9.282% |  |  | 2021-03-18 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-03-18 | 872368.15 |  | 520806038.4 | 471016384.38 | 49789654.02 | 527037820 | 9.447% |  |  | 2021-03-18 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-03-18 | 2000000 |  | 522806038.4 | 471016384.38 | 51789654.02 | 527037820 | 9.827% |  |  | 2021-03-18 | added cash in 3 |  |  | 2021
Royal City Mall | 2021-03-18 | 1951088.5 |  | 524757126.9 | 471016384.38 | 53740742.52 | 527037820 | 10.2% |  |  | 2021-03-18 | added cash in 3 |  |  | 2021
1900
Shoubra Banha Bridge L&L | 2017-05-01 |  | 11960 | 0 | 11960 | -11960 | 3865380 | -0.3094% |  |  |  | cash out both |  |  | 2017
Shoubra Banha Bridge L&L | 2017-08-01 |  | 15800 | 0 | 27760 | -27760 | 3865380 | -0.7182% |  |  |  | cash out both |  |  | 2017
Shoubra Banha Bridge L&L | 2017-10-01 |  | 34500.83 | 0 | 62260.83 | -62260.83 | 3865380 | -1.611% |  |  |  | cash out both |  |  | 2017
Shoubra Banha Bridge L&L | 2018-01-04 | 500000 |  | 500000 | 62260.83 | 437739.17 | 3865380 | 11.32% |  |  | 2018-01-04 | added cash in 3 |  |  | 2018
Shoubra Banha Bridge L&L | 2018-03-01 |  | 13289.17 | 500000 | 75550 | 424450 | 3865380 | 10.98% |  |  |  | cash out both |  |  | 2018
Shoubra Banha Bridge L&L | 2018-04-01 |  | 39641.08 | 500000 | 115191.08 | 384808.92 | 3865380 | 9.955% |  |  |  | cash out both |  |  | 2018
Shoubra Banha Bridge L&L | 2018-08-01 |  | 4421 | 500000 | 119612.08 | 380387.92 | 3865380 | 9.841% |  |  |  | cash out both |  |  | 2018
Shoubra Banha Bridge L&L | 2018-10-01 |  | 53825 | 500000 | 173437.08 | 326562.92 | 3865380 | 8.448% |  |  |  | cash out both |  |  | 2018
Shoubra Banha Bridge L&L | 2018-11-01 |  | 14843.29 | 500000 | 188280.37 | 311719.63 | 3865380 | 8.064% |  |  |  | cash out both |  |  | 2018
Shoubra Banha Bridge L&L | 2019-01-01 |  | 1231.71 | 500000 | 189512.08 | 310487.92 | 3865380 | 8.033% |  |  |  | cash out both |  |  | 2019
Shoubra Banha Bridge L&L | 2019-11-01 |  | 786.42 | 500000 | 190298.5 | 309701.5 | 3865380 | 8.012% |  |  |  | cash out both |  |  | 2019
Shoubra Banha Bridge L&L | 2019-12-01 |  | 627886.26 | 500000 | 818184.76 | -318184.76 | 3865380 | -8.232% |  |  |  | cash out both |  |  | 2019
Shoubra Banha Bridge L&L | 2020-08-01 |  | 769.32 | 500000 | 818954.08 | -318954.08 | 3865380 | -8.252% |  |  |  | cash out both |  |  | 2020
1900
SLP Logistic Center PI Park Sewedy Stores | 2017-07-31 | 6400000 | 11130 | 6400000 | 11130 | 6388870 | 98230405 | 6.504% |  | 0 | 2017-07-31 | original |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-08-01 |  | 87056.8 | 6400000 | 98186.8 | 6301813.2 | 98230405 | 6.415% |  |  |  | cash out both |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-08-31 | 0 | 365984 | 6400000 | 464170.8 | 5935829.2 | 98230405 | 6.043% |  | 0 | 2017-08-31 | original |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-09-01 |  | 183373.52 | 6400000 | 647544.32 | 5752455.68 | 98230405 | 5.856% |  |  |  | cash out both |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-09-30 | 0 | 436860 | 6400000 | 1084404.32 | 5315595.68 | 98230405 | 5.411% |  | 3990887 | 2017-09-30 | original |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-10-01 |  | 532251.23 | 6400000 | 1616655.55 | 4783344.45 | 98230405 | 4.87% |  |  |  | cash out both |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-10-31 | 0 | 2914171 | 6400000 | 4530826.55 | 1869173.45 | 98230405 | 1.903% |  | 3599516 | 2017-10-31 | original |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-11-01 |  | 273406.03 | 6400000 | 4804232.58 | 1595767.42 | 98230405 | 1.625% |  |  |  | cash out both |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-11-30 | 3779007 | 6068657 | 10179007 | 10872889.58 | -693882.58 | 98230405 | -0.7064% |  | 1558907 | 2017-11-30 | original |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-12-01 |  | 528233.59 | 10179007 | 11401123.17 | -1222116.17 | 98230405 | -1.244% |  |  |  | cash out both |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2017-12-31 | 3366014 | 887464 | 13545021 | 12288587.17 | 1256433.83 | 98230405 | 1.279% |  | 3130756 | 2017-12-31 | original |  |  | 2017
SLP Logistic Center PI Park Sewedy Stores | 2018-01-01 |  | 1301092.92 | 13545021 | 13589680.09 | -44659.09 | 98230405 | -0.04546% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-02-01 |  | 856943.88 | 13545021 | 14446623.97 | -901602.97 | 98230405 | -0.9178% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-02-21 | 2572231.81 |  | 16117252.81 | 14446623.97 | 1670628.84 | 98230405 | 1.701% |  |  | 2018-02-21 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-03-01 |  | 893390.97 | 16117252.81 | 15340014.94 | 777237.87 | 98230405 | 0.7912% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-04-01 |  | 2101196.64 | 16117252.81 | 17441211.58 | -1323958.77 | 98230405 | -1.348% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-04-12 | 1175600.49 |  | 17292853.3 | 17441211.58 | -148358.28 | 98230405 | -0.151% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-04-12 | 5000000 |  | 22292853.3 | 17441211.58 | 4851641.72 | 98230405 | 4.939% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-04-17 | 7600000 |  | 29892853.3 | 17441211.58 | 12451641.72 | 98230405 | 12.68% |  |  | 2018-04-17 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-05-01 |  | 1412628.15 | 29892853.3 | 18853839.73 | 11039013.57 | 98230405 | 11.24% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-05-13 | 689110.93 |  | 30581964.23 | 18853839.73 | 11728124.5 | 98230405 | 11.94% |  |  | 2018-05-13 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-05-13 | 1209313.47 |  | 31791277.7 | 18853839.73 | 12937437.97 | 98230405 | 13.17% |  |  | 2018-05-13 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-06-01 |  | 1977571.86 | 31791277.7 | 20831411.59 | 10959866.11 | 98230405 | 11.16% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-06-13 | 1492654.2 |  | 33283931.9 | 20831411.59 | 12452520.31 | 98230405 | 12.68% |  |  | 2018-06-13 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-06-30 | 1471457.2 |  | 34755389.1 | 20831411.59 | 13923977.51 | 98230405 | 14.17% |  |  | 2018-06-30 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-07-01 |  | 1683748.12 | 34755389.1 | 22515159.71 | 12240229.39 | 98230405 | 12.46% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-08-01 |  | 8370557.78 | 34755389.1 | 30885717.49 | 3869671.61 | 98230405 | 3.939% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-08-14 | 2470019.34 |  | 37225408.44 | 30885717.49 | 6339690.95 | 98230405 | 6.454% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-09-01 |  | 961785.85 | 37225408.44 | 31847503.34 | 5377905.1 | 98230405 | 5.475% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-09-17 | 945860.23 |  | 38171268.67 | 31847503.34 | 6323765.33 | 98230405 | 6.438% |  |  | 2018-09-17 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-10-01 |  | 2844514.14 | 38171268.67 | 34692017.48 | 3479251.19 | 98230405 | 3.542% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-10-18 | 1347803.37 |  | 39519072.04 | 34692017.48 | 4827054.56 | 98230405 | 4.914% |  |  | 2018-10-18 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-11-01 |  | 6003365.14 | 39519072.04 | 40695382.62 | -1176310.58 | 98230405 | -1.198% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-11-06 | 7818631.64 |  | 47337703.68 | 40695382.62 | 6642321.06 | 98230405 | 6.762% |  |  | 2018-11-06 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-11-06 | 719804.13 |  | 48057507.81 | 40695382.62 | 7362125.19 | 98230405 | 7.495% |  |  | 2018-11-06 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-11-27 | 1704160 |  | 49761667.81 | 40695382.62 | 9066285.19 | 98230405 | 9.23% |  |  | 2018-11-27 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-12-01 |  | 11138708.44 | 49761667.81 | 51834091.06 | -2072423.25 | 98230405 | -2.11% |  |  |  | cash out both |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-12-04 | 775351.46 |  | 50537019.27 | 51834091.06 | -1297071.79 | 98230405 | -1.32% |  |  | 2018-12-04 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2018-12-04 | 3907009.94 |  | 54444029.21 | 51834091.06 | 2609938.15 | 98230405 | 2.657% |  |  | 2018-12-04 | added cash in 3 |  |  | 2018
SLP Logistic Center PI Park Sewedy Stores | 2019-01-01 |  | 2373644.85 | 54444029.21 | 54207735.91 | 236293.3 | 98230405 | 0.2406% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-01-03 | 3921714.73 |  | 58365743.94 | 54207735.91 | 4158008.03 | 98230405 | 4.233% |  |  | 2019-01-03 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-01-03 | 4484634.17 |  | 62850378.11 | 54207735.91 | 8642642.2 | 98230405 | 8.798% |  |  | 2019-01-03 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-02-01 |  | 3175849.25 | 62850378.11 | 57383585.16 | 5466792.95 | 98230405 | 5.565% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-02-11 | 4125986.43 |  | 66976364.54 | 57383585.16 | 9592779.38 | 98230405 | 9.766% |  |  | 2019-02-11 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-02-12 | 3366511.48 |  | 70342876.02 | 57383585.16 | 12959290.86 | 98230405 | 13.19% |  |  | 2019-02-12 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-03-01 |  | 8813928.26 | 70342876.02 | 66197513.42 | 4145362.6 | 98230405 | 4.22% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-03-17 | 1375431.38 |  | 71718307.4 | 66197513.42 | 5520793.98 | 98230405 | 5.62% |  |  | 2019-03-17 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-03-17 | 6350059.5 |  | 78068366.9 | 66197513.42 | 11870853.48 | 98230405 | 12.08% |  |  | 2019-03-17 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-04-01 |  | 3888202.36 | 78068366.9 | 70085715.78 | 7982651.12 | 98230405 | 8.126% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-04-07 | 3699864.67 |  | 81768231.57 | 70085715.78 | 11682515.79 | 98230405 | 11.89% |  |  | 2019-04-07 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-04-07 | 919139.23 |  | 82687370.8 | 70085715.78 | 12601655.02 | 98230405 | 12.83% |  |  | 2019-04-07 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-05-01 |  | 4182766.77 | 82687370.8 | 74268482.55 | 8418888.25 | 98230405 | 8.571% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-05-26 | 2661364.08 |  | 85348734.88 | 74268482.55 | 11080252.33 | 98230405 | 11.28% |  |  | 2019-05-26 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-05-26 | 2311261.81 |  | 87659996.69 | 74268482.55 | 13391514.14 | 98230405 | 13.63% |  |  | 2019-05-26 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-06-01 |  | 2059167.4 | 87659996.69 | 76327649.95 | 11332346.74 | 98230405 | 11.54% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-07-01 |  | 302701.88 | 87659996.69 | 76630351.83 | 11029644.86 | 98230405 | 11.23% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-08-01 |  | 2420645.94 | 87659996.69 | 79050997.77 | 8608998.92 | 98230405 | 8.764% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-09-01 |  | 864171.97 | 87659996.69 | 79915169.74 | 7744826.95 | 98230405 | 7.884% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-09-05 | 1478131.5 |  | 89138128.19 | 79915169.74 | 9222958.45 | 98230405 | 9.389% |  |  | 2019-09-05 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-09-05 | 1466574.4 |  | 90604702.59 | 79915169.74 | 10689532.85 | 98230405 | 10.88% |  |  | 2019-09-05 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-10-01 |  | 186123.84 | 90604702.59 | 80101293.58 | 10503409.01 | 98230405 | 10.69% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-11-01 |  | 218624.98 | 90604702.59 | 80319918.56 | 10284784.03 | 98230405 | 10.47% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-12-01 |  | 8109117.13 | 90604702.59 | 88429035.69 | 2175666.9 | 98230405 | 2.215% |  |  |  | cash out both |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-12-25 | 4361327.46 |  | 94966030.05 | 88429035.69 | 6536994.36 | 98230405 | 6.655% |  |  | 2019-12-25 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2019-12-25 | 4813799.42 |  | 99779829.47 | 88429035.69 | 11350793.78 | 98230405 | 11.56% |  |  | 2019-12-25 | added cash in 3 |  |  | 2019
SLP Logistic Center PI Park Sewedy Stores | 2020-01-01 |  | 1093583.04 | 99779829.47 | 89522618.73 | 10257210.74 | 98230405 | 10.44% |  |  |  | cash out both |  |  | 2020
1900
El Mostakbal Bridge L&L | 2019-05-01 |  | 132843 | 0 | 132843 | -132843 | 4424558 | -3.002% |  |  |  | cash out both |  |  | 2019
El Mostakbal Bridge L&L | 2019-10-01 |  | 41230 | 0 | 174073 | -174073 | 4424558 | -3.934% |  |  |  | cash out both |  |  | 2019
El Mostakbal Bridge L&L | 2019-11-01 |  | 68724.6 | 0 | 242797.6 | -242797.6 | 4424558 | -5.487% |  |  |  | cash out both |  |  | 2019
El Mostakbal Bridge L&L | 2019-11-20 | 1392527 |  | 1392527 | 242797.6 | 1149729.4 | 4424558 | 25.99% |  |  | 2019-11-20 | added cash in 3 |  |  | 2019
El Mostakbal Bridge L&L | 2019-12-01 |  | 44585.08 | 1392527 | 287382.68 | 1105144.32 | 4424558 | 24.98% |  |  |  | cash out both |  |  | 2019
El Mostakbal Bridge L&L | 2020-01-01 |  | 101868.41 | 1392527 | 389251.09 | 1003275.91 | 4424558 | 22.68% |  |  |  | cash out both |  |  | 2020
El Mostakbal Bridge L&L | 2020-12-31 | 182760 |  | 1575287 | 389251.09 | 1186035.91 | 4424558 | 26.81% |  |  | 2020-12-31 | added cash in 3 |  |  | 2020
El Mostakbal Bridge L&L | 2021-01-24 | 138370 |  | 1713657 | 389251.09 | 1324405.91 | 4424558 | 29.93% |  |  | 2021-01-24 | added cash in 3 |  |  | 2021
1900
Kayan Wall L&L | 2017-11-01 |  | 37173.99 | 0 | 37173.99 | -37173.99 | 107782440 | -0.03449% |  |  |  | cash out both |  |  | 2017
Kayan Wall L&L | 2017-12-01 |  | 514939.75 | 0 | 552113.74 | -552113.74 | 107782440 | -0.5122% |  |  |  | cash out both |  |  | 2017
Kayan Wall L&L | 2018-01-01 |  | 2461382.69 | 0 | 3013496.43 | -3013496.43 | 107782440 | -2.796% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-02-01 |  | 1574495.22 | 0 | 4587991.65 | -4587991.65 | 107782440 | -4.257% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-03-01 |  | 2531407.41 | 0 | 7119399.06 | -7119399.06 | 107782440 | -6.605% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-04-01 |  | 2024242.44 | 0 | 9143641.5 | -9143641.5 | 107782440 | -8.483% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-04-29 | 14751577.1 |  | 14751577.1 | 9143641.5 | 5607935.6 | 107782440 | 5.203% |  |  | 2018-04-29 | added cash in 3 |  |  | 2018
Kayan Wall L&L | 2018-05-01 |  | 1866377.4 | 14751577.1 | 11010018.9 | 3741558.2 | 107782440 | 3.471% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-05-15 | 3914997 |  | 18666574.1 | 11010018.9 | 7656555.2 | 107782440 | 7.104% |  |  | 2018-05-15 | added cash in 3 |  |  | 2018
Kayan Wall L&L | 2018-06-01 |  | 1515135.58 | 18666574.1 | 12525154.48 | 6141419.62 | 107782440 | 5.698% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-06-20 | 8894827.6 |  | 27561401.7 | 12525154.48 | 15036247.22 | 107782440 | 13.95% |  |  | 2018-06-20 | added cash in 3 |  |  | 2018
Kayan Wall L&L | 2018-07-01 |  | 2321027.15 | 27561401.7 | 14846181.63 | 12715220.07 | 107782440 | 11.8% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-08-01 |  | 1067955.79 | 27561401.7 | 15914137.42 | 11647264.28 | 107782440 | 10.81% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-08-28 | 3329140.4 |  | 30890542.1 | 15914137.42 | 14976404.68 | 107782440 | 13.9% |  |  | 2018-08-28 | added cash in 3 |  |  | 2018
Kayan Wall L&L | 2018-09-01 |  | 2076373.76 | 30890542.1 | 17990511.18 | 12900030.92 | 107782440 | 11.97% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-10-01 |  | 2483382.09 | 30890542.1 | 20473893.27 | 10416648.83 | 107782440 | 9.665% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-11-01 |  | 2236063.96 | 30890542.1 | 22709957.23 | 8180584.87 | 107782440 | 7.59% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2018-11-12 | 5426691.7 |  | 36317233.8 | 22709957.23 | 13607276.57 | 107782440 | 12.62% |  |  | 2018-11-12 | added cash in 3 |  |  | 2018
Kayan Wall L&L | 2018-12-01 |  | 2537753.59 | 36317233.8 | 25247710.82 | 11069522.98 | 107782440 | 10.27% |  |  |  | cash out both |  |  | 2018
Kayan Wall L&L | 2019-01-01 |  | 3430911.48 | 36317233.8 | 28678622.3 | 7638611.5 | 107782440 | 7.087% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-02-01 |  | 825270.66 | 36317233.8 | 29503892.96 | 6813340.84 | 107782440 | 6.321% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-02-07 | 10570220.8 |  | 46887454.6 | 29503892.96 | 17383561.64 | 107782440 | 16.13% |  |  | 2019-02-07 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2019-03-01 |  | 1087938.8 | 46887454.6 | 30591831.76 | 16295622.84 | 107782440 | 15.12% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-03-04 | 7568893 |  | 54456347.6 | 30591831.76 | 23864515.84 | 107782440 | 22.14% |  |  | 2019-03-04 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2019-04-01 |  | 1098570.43 | 54456347.6 | 31690402.19 | 22765945.41 | 107782440 | 21.12% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-04-10 | 10000000 |  | 64456347.6 | 31690402.19 | 32765945.41 | 107782440 | 30.4% |  |  | 2019-04-10 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2019-05-01 |  | 1034034.08 | 64456347.6 | 32724436.27 | 31731911.33 | 107782440 | 29.44% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-06-01 |  | 199688.07 | 64456347.6 | 32924124.34 | 31532223.26 | 107782440 | 29.26% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-06-12 | 1519519.25 |  | 65975866.85 | 32924124.34 | 33051742.51 | 107782440 | 30.67% |  |  | 2019-06-12 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2019-07-01 |  | 518893.13 | 65975866.85 | 33443017.47 | 32532849.38 | 107782440 | 30.18% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-08-01 |  | 479889.61 | 65975866.85 | 33922907.08 | 32052959.77 | 107782440 | 29.74% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-08-08 | 2370680 |  | 68346546.85 | 33922907.08 | 34423639.77 | 107782440 | 31.94% |  |  | 2019-08-08 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2019-09-01 |  | 150297.07 | 68346546.85 | 34073204.15 | 34273342.7 | 107782440 | 31.8% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-10-01 |  | 327660.04 | 68346546.85 | 34400864.19 | 33945682.66 | 107782440 | 31.49% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-10-27 | 347617 |  | 68694163.85 | 34400864.19 | 34293299.66 | 107782440 | 31.82% |  |  | 2019-10-27 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2019-10-30 | 230837 |  | 68925000.85 | 34400864.19 | 34524136.66 | 107782440 | 32.03% |  |  | 2019-10-30 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2019-11-01 |  | 163593.15 | 68925000.85 | 34564457.34 | 34360543.51 | 107782440 | 31.88% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-12-01 |  | 5379412.16 | 68925000.85 | 39943869.5 | 28981131.35 | 107782440 | 26.89% |  |  |  | cash out both |  |  | 2019
Kayan Wall L&L | 2019-12-31 | 984167 |  | 69909167.85 | 39943869.5 | 29965298.35 | 107782440 | 27.8% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Kayan Wall L&L | 2020-01-01 |  | 44469.69 | 69909167.85 | 39988339.19 | 29920828.66 | 107782440 | 27.76% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-02-01 |  | 323028.68 | 69909167.85 | 40311367.87 | 29597799.98 | 107782440 | 27.46% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-02-17 | 428300 |  | 70337467.85 | 40311367.87 | 30026099.98 | 107782440 | 27.86% |  |  | 2020-02-17 | added 1 |  |  | 2020
Kayan Wall L&L | 2020-02-17 | 2253440 |  | 72590907.85 | 40311367.87 | 32279539.98 | 107782440 | 29.95% |  |  | 2020-02-17 | added 1 |  |  | 2020
Kayan Wall L&L | 2020-02-18 | 2253440 |  | 74844347.85 | 40311367.87 | 34532979.98 | 107782440 | 32.04% |  |  | 2020-02-18 | added cash in 3 |  |  | 2020
Kayan Wall L&L | 2020-02-18 | 428300 |  | 75272647.85 | 40311367.87 | 34961279.98 | 107782440 | 32.44% |  |  | 2020-02-18 | added cash in 3 |  |  | 2020
Kayan Wall L&L | 2020-03-01 |  | 49328.47 | 75272647.85 | 40360696.34 | 34911951.51 | 107782440 | 32.39% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-03-10 | 364497 |  | 75637144.85 | 40360696.34 | 35276448.51 | 107782440 | 32.73% |  |  | 2020-03-10 | added 1 |  |  | 2020
Kayan Wall L&L | 2020-04-01 |  | 57581.21 | 75637144.85 | 40418277.55 | 35218867.3 | 107782440 | 32.68% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-05-01 |  | 104272.98 | 75637144.85 | 40522550.53 | 35114594.32 | 107782440 | 32.58% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-06-01 |  | 61758.48 | 75637144.85 | 40584309.01 | 35052835.84 | 107782440 | 32.52% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-07-01 |  | 149830.76 | 75637144.85 | 40734139.77 | 34903005.08 | 107782440 | 32.38% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-07-09 | 249955 |  | 75887099.85 | 40734139.77 | 35152960.08 | 107782440 | 32.61% |  |  | 2020-07-09 | added 1 |  |  | 2020
Kayan Wall L&L | 2020-07-12 | 249995 |  | 76137094.85 | 40734139.77 | 35402955.08 | 107782440 | 32.85% |  |  | 2020-07-12 | added cash in 3 |  |  | 2020
Kayan Wall L&L | 2020-08-01 |  | 71457.3 | 76137094.85 | 40805597.07 | 35331497.78 | 107782440 | 32.78% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-09-01 |  | 55634.66 | 76137094.85 | 40861231.73 | 35275863.12 | 107782440 | 32.73% |  |  |  | cash out both |  |  | 2020
Kayan Wall L&L | 2020-09-09 | 2801245 |  | 78938339.85 | 40861231.73 | 38077108.12 | 107782440 | 35.33% |  |  | 2020-09-09 | added 1 |  |  | 2020
Kayan Wall L&L | 2020-10-01 |  | 71328.78 | 78938339.85 | 40932560.51 | 38005779.34 | 107782440 | 35.26% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Kayan Wall L&L | 2020-11-01 |  | 65033.78 | 78938339.85 | 40997594.29 | 37940745.56 | 107782440 | 35.2% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Kayan Wall L&L | 2020-12-01 |  | 79253.78 | 78938339.85 | 41076848.07 | 37861491.78 | 107782440 | 35.13% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Kayan Wall L&L | 2021-01-01 |  | 740 | 78938339.85 | 41077588.07 | 37860751.78 | 107782440 | 35.13% |  |  |  | cash out both |  |  | 2021
Kayan Wall L&L | 2021-02-01 |  | 41244.98 | 78938339.85 | 41118833.05 | 37819506.8 | 107782440 | 35.09% |  |  |  | cash out both |  |  | 2021
Kayan Wall L&L | 2021-03-01 |  | 18566.64 | 78938339.85 | 41137399.69 | 37800940.16 | 107782440 | 35.07% |  |  |  | cash out both |  |  | 2021
1900
Elco Suez Steel Rolling Mill Plant 3 | 2017-06-01 |  | 7364.72 | 0 | 7364.72 | -7364.72 | 417390514 | -0.001764% |  |  |  | cash out both |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-08-01 |  | 1237.5 | 0 | 8602.22 | -8602.22 | 417390514 | -0.002061% |  |  |  | cash out both |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-08-01 | 53000000 |  | 53000000 | 8602.22 | 52991397.78 | 417390514 | 12.7% |  |  | 2017-08-01 | added cash in 3 |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-08-31 | 53000000 | 0 | 106000000 | 8602.22 | 105991397.78 | 417390514 | 25.39% |  | 0 | 2017-08-31 | original |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-09-30 | 0 | 4888256 | 106000000 | 4896858.22 | 101103141.78 | 417390514 | 24.22% |  | 17022109 | 2017-09-30 | original |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-10-01 |  | 3701258.44 | 106000000 | 8598116.66 | 97401883.34 | 417390514 | 23.34% |  |  |  | cash out both |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-10-31 | 56413682 | 9362396 | 162413682 | 17960512.66 | 144453169.34 | 417390514 | 34.61% |  | 54045554 | 2017-10-31 | original |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-11-01 |  | 797491.36 | 162413682 | 18758004.02 | 143655677.98 | 417390514 | 34.42% |  |  |  | cash out both |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-11-30 | 20000000 | 15018753 | 182413682 | 33776757.02 | 148636924.98 | 417390514 | 35.61% |  | 68968025 | 2017-11-30 | original |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-12-01 |  | 1068028.69 | 182413682 | 34844785.71 | 147568896.29 | 417390514 | 35.36% |  |  |  | cash out both |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-12-31 | 34829580 | 20512562 | 217243262 | 55357347.71 | 161885914.29 | 417390514 | 38.79% |  | 45198075 | 2017-12-31 | original |  |  | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2018-01-01 |  | 17464371.62 | 217243262 | 72821719.33 | 144421542.67 | 417390514 | 34.6% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-01-09 | 6800000 |  | 224043262 | 72821719.33 | 151221542.67 | 417390514 | 36.23% |  |  | 2018-01-09 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-01-09 | 10000000 |  | 234043262 | 72821719.33 | 161221542.67 | 417390514 | 38.63% |  |  | 2018-01-09 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-01-15 | 25932469.35 |  | 259975731.35 | 72821719.33 | 187154012.02 | 417390514 | 44.84% |  |  | 2018-01-15 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-01-18 | 9000000 |  | 268975731.35 | 72821719.33 | 196154012.02 | 417390514 | 47% |  |  | 2018-01-18 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-02-01 |  | 7669860.67 | 268975731.35 | 80491580 | 188484151.35 | 417390514 | 45.16% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-02-11 | 2900000 |  | 271875731.35 | 80491580 | 191384151.35 | 417390514 | 45.85% |  |  | 2018-02-11 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-02-15 | 1253543.18 |  | 273129274.53 | 80491580 | 192637694.53 | 417390514 | 46.15% |  |  | 2018-02-15 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-02-15 | 331328.32 |  | 273460602.85 | 80491580 | 192969022.85 | 417390514 | 46.23% |  |  | 2018-02-15 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-02-19 | 9138252.26 |  | 282598855.11 | 80491580 | 202107275.11 | 417390514 | 48.42% |  |  | 2018-02-19 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-03-01 |  | 21645612.2 | 282598855.11 | 102137192.2 | 180461662.91 | 417390514 | 43.24% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-03-13 | 20010303.66 |  | 302609158.77 | 102137192.2 | 200471966.57 | 417390514 | 48.03% |  |  | 2018-03-13 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-03-14 | 2059899.63 |  | 304669058.4 | 102137192.2 | 202531866.2 | 417390514 | 48.52% |  |  | 2018-03-14 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-03-14 | 2897721.63 |  | 307566780.03 | 102137192.2 | 205429587.83 | 417390514 | 49.22% |  |  | 2018-03-14 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-04-01 |  | 11746504.19 | 307566780.03 | 113883696.39 | 193683083.64 | 417390514 | 46.4% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-04-16 | 1986502.95 |  | 309553282.98 | 113883696.39 | 195669586.59 | 417390514 | 46.88% |  |  | 2018-04-16 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-04-16 | 3188918.44 |  | 312742201.42 | 113883696.39 | 198858505.03 | 417390514 | 47.64% |  |  | 2018-04-16 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-04-16 | 7919870.17 |  | 320662071.59 | 113883696.39 | 206778375.2 | 417390514 | 49.54% |  |  | 2018-04-16 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-05-01 |  | 18325318.11 | 320662071.59 | 132209014.5 | 188453057.09 | 417390514 | 45.15% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-05-15 | 2505278.84 |  | 323167350.43 | 132209014.5 | 190958335.93 | 417390514 | 45.75% |  |  | 2018-05-15 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-05-15 | 3617002.3 |  | 326784352.73 | 132209014.5 | 194575338.23 | 417390514 | 46.62% |  |  | 2018-05-15 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-05-15 | 6348055.64 |  | 333132408.37 | 132209014.5 | 200923393.87 | 417390514 | 48.14% |  |  | 2018-05-15 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-06-01 |  | 15144191.1 | 333132408.37 | 147353205.6 | 185779202.77 | 417390514 | 44.51% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-06-13 | 740665.09 |  | 333873073.46 | 147353205.6 | 186519867.86 | 417390514 | 44.69% |  |  | 2018-06-13 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-06-13 | 1819035.22 |  | 335692108.68 | 147353205.6 | 188338903.08 | 417390514 | 45.12% |  |  | 2018-06-13 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-06-13 | 2440101.67 |  | 338132210.35 | 147353205.6 | 190779004.75 | 417390514 | 45.71% |  |  | 2018-06-13 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-07-01 |  | 17869636.94 | 338132210.35 | 165222842.54 | 172909367.81 | 417390514 | 41.43% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-07-12 | 4000000 |  | 342132210.35 | 165222842.54 | 176909367.81 | 417390514 | 42.38% |  |  | 2018-07-12 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-07-12 | 5058047.58 |  | 347190257.93 | 165222842.54 | 181967415.39 | 417390514 | 43.6% |  |  | 2018-07-12 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-07-12 | 2133379.76 |  | 349323637.69 | 165222842.54 | 184100795.15 | 417390514 | 44.11% |  |  | 2018-07-12 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-08-01 |  | 7999191.34 | 349323637.69 | 173222033.88 | 176101603.81 | 417390514 | 42.19% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-08-14 | 5750618.58 |  | 355074256.27 | 173222033.88 | 181852222.39 | 417390514 | 43.57% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-08-14 | 7075101.66 |  | 362149357.93 | 173222033.88 | 188927324.05 | 417390514 | 45.26% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-08-14 | 2606150.31 |  | 364755508.24 | 173222033.88 | 191533474.36 | 417390514 | 45.89% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-09-01 |  | 12596146.71 | 364755508.24 | 185818180.59 | 178937327.65 | 417390514 | 42.87% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-09-18 | 1980608.55 |  | 366736116.79 | 185818180.59 | 180917936.2 | 417390514 | 43.35% |  |  | 2018-09-18 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-09-18 | 2485656 |  | 369221772.79 | 185818180.59 | 183403592.2 | 417390514 | 43.94% |  |  | 2018-09-18 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-09-18 | 3289926.92 |  | 372511699.71 | 185818180.59 | 186693519.12 | 417390514 | 44.73% |  |  | 2018-09-18 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-10-01 |  | 13999793.19 | 372511699.71 | 199817973.78 | 172693725.93 | 417390514 | 41.37% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-10-18 | 2518616.18 |  | 375030315.89 | 199817973.78 | 175212342.11 | 417390514 | 41.98% |  |  | 2018-10-18 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-10-18 | 1940428.07 |  | 376970743.96 | 199817973.78 | 177152770.18 | 417390514 | 42.44% |  |  | 2018-10-18 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-10-28 | 2178754.66 |  | 379149498.62 | 199817973.78 | 179331524.84 | 417390514 | 42.96% |  |  | 2018-10-28 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-10-29 | 13218500 |  | 392367998.62 | 199817973.78 | 192550024.84 | 417390514 | 46.13% |  |  | 2018-10-29 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-11-01 |  | 16399752.94 | 392367998.62 | 216217726.72 | 176150271.9 | 417390514 | 42.2% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-11-22 | 2629432.67 |  | 394997431.29 | 216217726.72 | 178779704.57 | 417390514 | 42.83% |  |  | 2018-11-22 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-11-22 | 2857649.27 |  | 397855080.56 | 216217726.72 | 181637353.84 | 417390514 | 43.52% |  |  | 2018-11-22 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-11-22 | 2335545.55 |  | 400190626.11 | 216217726.72 | 183972899.39 | 417390514 | 44.08% |  |  | 2018-11-22 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-12-01 |  | 10298474.42 | 400190626.11 | 226516201.14 | 173674424.97 | 417390514 | 41.61% |  |  |  | cash out both |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-12-23 | 2179703.08 |  | 402370329.19 | 226516201.14 | 175854128.05 | 417390514 | 42.13% |  |  | 2018-12-23 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-12-23 | 1720441.01 |  | 404090770.2 | 226516201.14 | 177574569.06 | 417390514 | 42.54% |  |  | 2018-12-23 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2018-12-23 | 1595365.5 |  | 405686135.7 | 226516201.14 | 179169934.56 | 417390514 | 42.93% |  |  | 2018-12-23 | added cash in 3 |  |  | 2018
Elco Suez Steel Rolling Mill Plant 3 | 2019-01-01 |  | 11225359.33 | 405686135.7 | 237741560.47 | 167944575.23 | 417390514 | 40.24% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-01-15 | 1394236.79 |  | 407080372.49 | 237741560.47 | 169338812.02 | 417390514 | 40.57% |  |  | 2019-01-15 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-01-15 | 1037321.77 |  | 408117694.26 | 237741560.47 | 170376133.79 | 417390514 | 40.82% |  |  | 2019-01-15 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-01-15 | 310509.31 |  | 408428203.57 | 237741560.47 | 170686643.1 | 417390514 | 40.89% |  |  | 2019-01-15 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-01-30 | 500000 |  | 408928203.57 | 237741560.47 | 171186643.1 | 417390514 | 41.01% |  |  | 2019-01-30 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-02-01 |  | 8832697.11 | 408928203.57 | 246574257.58 | 162353945.99 | 417390514 | 38.9% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-01 |  | 2589663.2 | 408928203.57 | 249163920.78 | 159764282.79 | 417390514 | 38.28% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-01 |  | 9173827.94 | 408928203.57 | 258337748.72 | 150590454.85 | 417390514 | 36.08% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-07 | 117652.86 |  | 409045856.43 | 258337748.72 | 150708107.71 | 417390514 | 36.11% |  |  | 2019-03-07 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-07 | 388339.4 |  | 409434195.83 | 258337748.72 | 151096447.11 | 417390514 | 36.2% |  |  | 2019-03-07 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-07 | 1079101.72 |  | 410513297.55 | 258337748.72 | 152175548.83 | 417390514 | 36.46% |  |  | 2019-03-07 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-11 | 5000000 |  | 415513297.55 | 258337748.72 | 157175548.83 | 417390514 | 37.66% |  |  | 2019-03-11 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-20 | 2250000 |  | 417763297.55 | 258337748.72 | 159425548.83 | 417390514 | 38.2% |  |  | 2019-03-20 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-20 | 1700000 |  | 419463297.55 | 258337748.72 | 161125548.83 | 417390514 | 38.6% |  |  | 2019-03-20 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-27 | 105992.48 |  | 419569290.03 | 258337748.72 | 161231541.31 | 417390514 | 38.63% |  |  | 2019-03-27 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-27 | 317040.71 |  | 419886330.74 | 258337748.72 | 161548582.02 | 417390514 | 38.7% |  |  | 2019-03-27 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-28 | 12000000 |  | 431886330.74 | 258337748.72 | 173548582.02 | 417390514 | 41.58% |  |  | 2019-03-28 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-04-01 |  | 8844386.66 | 431886330.74 | 267182135.38 | 164704195.36 | 417390514 | 39.46% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-04-01 |  | 4699209.08 | 431886330.74 | 271881344.46 | 160004986.28 | 417390514 | 38.33% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-04-02 | 4624356.65 |  | 436510687.39 | 271881344.46 | 164629342.93 | 417390514 | 39.44% |  |  | 2019-04-02 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-04-02 | 10000000 |  | 446510687.39 | 271881344.46 | 174629342.93 | 417390514 | 41.84% |  |  | 2019-04-02 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-04-11 | 1573000 |  | 448083687.39 | 271881344.46 | 176202342.93 | 417390514 | 42.22% |  |  | 2019-04-11 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-04-21 | 6000000 |  | 454083687.39 | 271881344.46 | 182202342.93 | 417390514 | 43.65% |  |  | 2019-04-21 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-05-01 |  | 5920747.57 | 454083687.39 | 277802092.03 | 176281595.36 | 417390514 | 42.23% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-05-01 |  | 5777234.32 | 454083687.39 | 283579326.35 | 170504361.04 | 417390514 | 40.85% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-05-16 | 6000000 |  | 460083687.39 | 283579326.35 | 176504361.04 | 417390514 | 42.29% |  |  | 2019-05-16 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-05-16 | 259861.3 |  | 460343548.69 | 283579326.35 | 176764222.34 | 417390514 | 42.35% |  |  | 2019-05-16 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-05-31 | 676486.65 |  | 461020035.34 | 283579326.35 | 177440708.99 | 417390514 | 42.51% |  |  | 2019-05-31 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-06-01 |  | 7802278.49 | 461020035.34 | 291381604.84 | 169638430.5 | 417390514 | 40.64% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-06-01 |  | 2388783.78 | 461020035.34 | 293770388.62 | 167249646.72 | 417390514 | 40.07% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-06-25 | 1500000 |  | 462520035.34 | 293770388.62 | 168749646.72 | 417390514 | 40.43% |  |  | 2019-06-25 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-07-01 |  | 1432379.51 | 462520035.34 | 295202768.13 | 167317267.21 | 417390514 | 40.09% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-07-01 |  | 3241423.15 | 462520035.34 | 298444191.28 | 164075844.06 | 417390514 | 39.31% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-07-03 | 4160000 |  | 466680035.34 | 298444191.28 | 168235844.06 | 417390514 | 40.31% |  |  | 2019-07-03 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-08-01 |  | 2368065.27 | 466680035.34 | 300812256.55 | 165867778.79 | 417390514 | 39.74% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-08-01 |  | 5178284.42 | 466680035.34 | 305990540.97 | 160689494.37 | 417390514 | 38.5% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-08-05 | 1550238.73 |  | 468230274.07 | 305990540.97 | 162239733.1 | 417390514 | 38.87% |  |  | 2019-08-05 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-08-26 | 111854.13 |  | 468342128.2 | 305990540.97 | 162351587.23 | 417390514 | 38.9% |  |  | 2019-08-26 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-08-26 | 588984.52 |  | 468931112.72 | 305990540.97 | 162940571.75 | 417390514 | 39.04% |  |  | 2019-08-26 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-08-26 | 5369664.06 |  | 474300776.78 | 305990540.97 | 168310235.81 | 417390514 | 40.32% |  |  | 2019-08-26 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-09-01 |  | 542207.3 | 474300776.78 | 306532748.27 | 167768028.51 | 417390514 | 40.19% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-09-01 |  | 2718399.21 | 474300776.78 | 309251147.48 | 165049629.3 | 417390514 | 39.54% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-09-05 | 767138.81 |  | 475067915.59 | 309251147.48 | 165816768.11 | 417390514 | 39.73% |  |  | 2019-09-05 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-10-01 |  | 2342653.9 | 475067915.59 | 311593801.38 | 163474114.21 | 417390514 | 39.17% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-10-01 |  | 574945.35 | 475067915.59 | 312168746.73 | 162899168.86 | 417390514 | 39.03% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-10-09 | 134252.42 |  | 475202168.01 | 312168746.73 | 163033421.28 | 417390514 | 39.06% |  |  | 2019-10-09 | added cash in 3 |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-11-01 |  | 728069.5 | 475202168.01 | 312896816.23 | 162305351.78 | 417390514 | 38.89% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-11-01 |  | 260466.52 | 475202168.01 | 313157282.75 | 162044885.26 | 417390514 | 38.82% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-12-01 |  | 937044.65 | 475202168.01 | 314094327.4 | 161107840.61 | 417390514 | 38.6% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2019-12-01 |  | 1602856.59 | 475202168.01 | 315697183.99 | 159504984.02 | 417390514 | 38.21% |  |  |  | cash out both |  |  | 2019
Elco Suez Steel Rolling Mill Plant 3 | 2020-01-01 |  | 690604.81 | 475202168.01 | 316387788.8 | 158814379.21 | 417390514 | 38.05% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-01-01 |  | 769511.91 | 475202168.01 | 317157300.71 | 158044867.3 | 417390514 | 37.86% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-01-16 | 750000 |  | 475952168.01 | 317157300.71 | 158794867.3 | 417390514 | 38.04% |  |  | 2020-01-16 | added cash in 3 |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-02-01 |  | 1826911 | 475952168.01 | 318984211.71 | 156967956.3 | 417390514 | 37.61% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-02-01 |  | 284022.21 | 475952168.01 | 319268233.92 | 156683934.09 | 417390514 | 37.54% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-03-01 |  | 599524.7 | 475952168.01 | 319867758.62 | 156084409.39 | 417390514 | 37.4% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-03-01 |  | 3576438.08 | 475952168.01 | 323444196.7 | 152507971.31 | 417390514 | 36.54% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-03-23 | 500000 |  | 476452168.01 | 323444196.7 | 153007971.31 | 417390514 | 36.66% |  |  | 2020-03-23 | added cash in 3 |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-04-01 |  | 395814.05 | 476452168.01 | 323840010.75 | 152612157.26 | 417390514 | 36.56% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-04-01 |  | 178439.29 | 476452168.01 | 324018450.04 | 152433717.97 | 417390514 | 36.52% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-04-09 | 2000000 |  | 478452168.01 | 324018450.04 | 154433717.97 | 417390514 | 37% |  |  | 2020-04-09 | added cash in 3 |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-04-13 | 1000000 |  | 479452168.01 | 324018450.04 | 155433717.97 | 417390514 | 37.24% |  |  | 2020-04-13 | added cash in 3 |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-05-01 |  | 296961.05 | 479452168.01 | 324315411.09 | 155136756.92 | 417390514 | 37.17% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-05-01 |  | 724169.15 | 479452168.01 | 325039580.24 | 154412587.77 | 417390514 | 36.99% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-06-01 |  | 576179.75 | 479452168.01 | 325615759.99 | 153836408.02 | 417390514 | 36.86% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-06-01 |  | 111533.9 | 479452168.01 | 325727293.89 | 153724874.12 | 417390514 | 36.83% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-06-21 | 750000 |  | 480202168.01 | 325727293.89 | 154474874.12 | 417390514 | 37.01% |  |  | 2020-06-21 | added cash in 3 |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-07-01 |  | 181178.05 | 480202168.01 | 325908471.94 | 154293696.07 | 417390514 | 36.97% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-07-01 |  | 685365.63 | 480202168.01 | 326593837.57 | 153608330.44 | 417390514 | 36.8% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-08-01 |  | 79758.96 | 480202168.01 | 326673596.53 | 153528571.48 | 417390514 | 36.78% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-08-01 |  | 14572.85 | 480202168.01 | 326688169.38 | 153513998.63 | 417390514 | 36.78% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-09-01 |  | 99109.03 | 480202168.01 | 326787278.41 | 153414889.6 | 417390514 | 36.76% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-09-01 |  | 19358.53 | 480202168.01 | 326806636.94 | 153395531.07 | 417390514 | 36.75% |  |  |  | cash out both |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2020-12-17 | 291975.34 |  | 480494143.35 | 326806636.94 | 153687506.41 | 417390514 | 36.82% |  |  | 2020-12-17 | added cash in 3 |  |  | 2020
Elco Suez Steel Rolling Mill Plant 3 | 2021-03-31 | 302594.27 |  | 480796737.62 | 326806636.94 | 153990100.68 | 417390514 | 36.89% |  |  | 2021-03-31 | added cash in 3 |  |  | 2021
1900
Hyper El Temsah | 2017-09-01 |  | 245160 | 0 | 245160 | -245160 | 168976040.9524 | -0.1451% |  |  |  | cash out both |  |  | 2017
Hyper El Temsah | 2017-09-30 | 0 | 707379 | 0 | 952539 | -952539 | 168976040.9524 | -0.5637% |  | 5921350 | 2017-09-30 | original |  |  | 2017
Hyper El Temsah | 2017-10-01 |  | 544862.2 | 0 | 1497401.2 | -1497401.2 | 168976040.9524 | -0.8862% |  |  |  | cash out both |  |  | 2017
Hyper El Temsah | 2017-10-31 | 0 | 895176 | 0 | 2392577.2 | -2392577.2 | 168976040.9524 | -1.416% |  | 0 | 2017-10-31 | original |  |  | 2017
Hyper El Temsah | 2017-11-01 |  | 535752.5 | 0 | 2928329.7 | -2928329.7 | 168976040.9524 | -1.733% |  |  |  | cash out both |  |  | 2017
Hyper El Temsah | 2017-11-30 | 0 | 1814907 | 0 | 4743236.7 | -4743236.7 | 168976040.9524 | -2.807% |  | 1369484 | 2017-11-30 | original |  |  | 2017
Hyper El Temsah | 2017-12-01 |  | 340352 | 0 | 5083588.7 | -5083588.7 | 168976040.9524 | -3.008% |  |  |  | cash out both |  |  | 2017
Hyper El Temsah | 2017-12-31 | 0 | 1082249 | 0 | 6165837.7 | -6165837.7 | 168976040.9524 | -3.649% |  | 0 | 2017-12-31 | original |  |  | 2017
Hyper El Temsah | 2018-01-01 |  | 446933.78 | 0 | 6612771.48 | -6612771.48 | 168976040.9524 | -3.913% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-02-01 |  | 6840 | 0 | 6619611.48 | -6619611.48 | 168976040.9524 | -3.917% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-03-01 |  | 78294.75 | 0 | 6697906.23 | -6697906.23 | 168976040.9524 | -3.964% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-05-01 |  | 119267.32 | 0 | 6817173.55 | -6817173.55 | 168976040.9524 | -4.034% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-06-01 |  | 389952.29 | 0 | 7207125.84 | -7207125.84 | 168976040.9524 | -4.265% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-07-01 |  | 789303.07 | 0 | 7996428.91 | -7996428.91 | 168976040.9524 | -4.732% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-08-01 |  | 1888802.65 | 0 | 9885231.56 | -9885231.56 | 168976040.9524 | -5.85% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-09-01 |  | 6463900.25 | 0 | 16349131.81 | -16349131.81 | 168976040.9524 | -9.675% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-10-01 |  | 9836882.75 | 0 | 26186014.56 | -26186014.56 | 168976040.9524 | -15.5% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-11-01 |  | 4228628.93 | 0 | 30414643.49 | -30414643.49 | 168976040.9524 | -18% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2018-12-01 |  | 10511632.71 | 0 | 40926276.2 | -40926276.2 | 168976040.9524 | -24.22% |  |  |  | cash out both |  |  | 2018
Hyper El Temsah | 2019-01-01 |  | 19083105.7 | 0 | 60009381.9 | -60009381.9 | 168976040.9524 | -35.51% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-02-01 |  | 8119859.98 | 0 | 68129241.88 | -68129241.88 | 168976040.9524 | -40.32% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-02-11 | 50000000 |  | 50000000 | 68129241.88 | -18129241.88 | 168976040.9524 | -10.73% |  |  | 2019-02-11 | added cash in 3 |  |  | 2019
Hyper El Temsah | 2019-03-01 |  | 9265654.75 | 50000000 | 77394896.63 | -27394896.63 | 168976040.9524 | -16.21% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-04-01 |  | 10884794.94 | 50000000 | 88279691.57 | -38279691.57 | 168976040.9524 | -22.65% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-05-01 |  | 4016076.61 | 50000000 | 92295768.18 | -42295768.18 | 168976040.9524 | -25.03% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-06-01 |  | 9122729.91 | 50000000 | 101418498.09 | -51418498.09 | 168976040.9524 | -30.43% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-07-01 |  | 4525912.01 | 50000000 | 105944410.1 | -55944410.1 | 168976040.9524 | -33.11% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-07-31 | 16646710 |  | 66646710 | 105944410.1 | -39297700.1 | 168976040.9524 | -23.26% |  |  | 2019-07-31 | added cash in 3 |  |  | 2019
Hyper El Temsah | 2019-08-01 |  | 1230114.32 | 66646710 | 107174524.42 | -40527814.42 | 168976040.9524 | -23.98% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-09-01 |  | 3027722.54 | 66646710 | 110202246.96 | -43555536.96 | 168976040.9524 | -25.78% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-10-01 |  | 516624.62 | 66646710 | 110718871.58 | -44072161.58 | 168976040.9524 | -26.08% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-11-01 |  | 2480726.03 | 66646710 | 113199597.61 | -46552887.61 | 168976040.9524 | -27.55% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2019-12-01 |  | 25517062.53 | 66646710 | 138716660.14 | -72069950.14 | 168976040.9524 | -42.65% |  |  |  | cash out both |  |  | 2019
Hyper El Temsah | 2020-01-01 |  | 208257.96 | 66646710 | 138924918.1 | -72278208.1 | 168976040.9524 | -42.77% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-02-01 |  | 1446030.75 | 66646710 | 140370948.85 | -73724238.85 | 168976040.9524 | -43.63% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-03-01 |  | 709465.39 | 66646710 | 141080414.24 | -74433704.24 | 168976040.9524 | -44.05% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-04-01 |  | 54533.8 | 66646710 | 141134948.04 | -74488238.04 | 168976040.9524 | -44.08% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-05-01 |  | 385336.8 | 66646710 | 141520284.84 | -74873574.84 | 168976040.9524 | -44.31% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-06-01 |  | 24449.64 | 66646710 | 141544734.48 | -74898024.48 | 168976040.9524 | -44.32% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-07-01 |  | 82387.5 | 66646710 | 141627121.98 | -74980411.98 | 168976040.9524 | -44.37% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-08-01 |  | 216850.76 | 66646710 | 141843972.74 | -75197262.74 | 168976040.9524 | -44.5% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-09-01 |  | 4630.96 | 66646710 | 141848603.7 | -75201893.7 | 168976040.9524 | -44.5% |  |  |  | cash out both |  |  | 2020
Hyper El Temsah | 2020-10-01 |  | 3150 | 66646710 | 141851753.7 | -75205043.7 | 168976040.9524 | -44.51% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Hyper El Temsah | 2021-01-01 |  | 163444.25 | 66646710 | 142015197.95 | -75368487.95 | 168976040.9524 | -44.6% |  |  |  | cash out both |  |  | 2021
Hyper El Temsah | 2021-03-01 |  | 114625.7 | 66646710 | 142129823.65 | -75483113.65 | 168976040.9524 | -44.67% |  |  |  | cash out both |  |  | 2021
1900
Marassi Bridge Pkg 117 | 2017-10-31 | 0 | 30000 | 0 | 30000 | -30000 | 45205818 | -0.06636% |  | 0 | 2017-10-31 | original |  |  | 2017
Marassi Bridge Pkg 117 | 2017-11-01 |  | 71200 | 0 | 101200 | -101200 | 45205818 | -0.2239% |  |  |  | cash out both |  |  | 2017
Marassi Bridge Pkg 117 | 2017-11-30 | 0 | 141327 | 0 | 242527 | -242527 | 45205818 | -0.5365% |  | 0 | 2017-11-30 | original |  |  | 2017
Marassi Bridge Pkg 117 | 2017-12-01 |  | 320950.5 | 0 | 563477.5 | -563477.5 | 45205818 | -1.246% |  |  |  | cash out both |  |  | 2017
Marassi Bridge Pkg 117 | 2017-12-31 | 0 | 2369103 | 0 | 2932580.5 | -2932580.5 | 45205818 | -6.487% |  | 0 | 2017-12-31 | original |  |  | 2017
Marassi Bridge Pkg 117 | 2018-01-01 |  | 980425.42 | 0 | 3913005.92 | -3913005.92 | 45205818 | -8.656% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-02-01 |  | 2031924.09 | 0 | 5944930.01 | -5944930.01 | 45205818 | -13.15% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-02-22 | 4130124.14 |  | 4130124.14 | 5944930.01 | -1814805.87 | 45205818 | -4.015% |  |  | 2018-02-22 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-03-01 |  | 2698556.32 | 4130124.14 | 8643486.33 | -4513362.19 | 45205818 | -9.984% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-03-13 | 6455421.01 |  | 10585545.15 | 8643486.33 | 1942058.82 | 45205818 | 4.296% |  |  | 2018-03-13 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-04-01 |  | 545075.16 | 10585545.15 | 9188561.49 | 1396983.66 | 45205818 | 3.09% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-04-12 | 4502026.51 |  | 15087571.66 | 9188561.49 | 5899010.17 | 45205818 | 13.05% |  |  | 2018-04-12 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-05-01 |  | 2647409.29 | 15087571.66 | 11835970.78 | 3251600.88 | 45205818 | 7.193% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-05-09 | 3740180.08 |  | 18827751.74 | 11835970.78 | 6991780.96 | 45205818 | 15.47% |  |  | 2018-05-09 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-05-31 | 409662.25 |  | 19237413.99 | 11835970.78 | 7401443.21 | 45205818 | 16.37% |  |  | 2018-05-31 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-06-01 |  | 2018725.56 | 19237413.99 | 13854696.34 | 5382717.65 | 45205818 | 11.91% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-06-10 | 4762507.56 |  | 23999921.55 | 13854696.34 | 10145225.21 | 45205818 | 22.44% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-06-28 | 522919.51 |  | 24522841.06 | 13854696.34 | 10668144.72 | 45205818 | 23.6% |  |  | 2018-06-28 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-07-01 |  | 1073426.77 | 24522841.06 | 14928123.11 | 9594717.95 | 45205818 | 21.22% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-07-31 | 5347404.78 |  | 29870245.84 | 14928123.11 | 14942122.73 | 45205818 | 33.05% |  |  | 2018-07-31 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-08-01 |  | 1261773.88 | 29870245.84 | 16189896.99 | 13680348.85 | 45205818 | 30.26% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-08-14 | 301773.91 |  | 30172019.75 | 16189896.99 | 13982122.76 | 45205818 | 30.93% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-09-01 |  | 972230.29 | 30172019.75 | 17162127.28 | 13009892.47 | 45205818 | 28.78% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-09-27 | 344451.17 |  | 30516470.92 | 17162127.28 | 13354343.64 | 45205818 | 29.54% |  |  | 2018-09-27 | added cash in 3 |  |  | 2018
Marassi Bridge Pkg 117 | 2018-10-01 |  | 1409245.11 | 30516470.92 | 18571372.39 | 11945098.53 | 45205818 | 26.42% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-11-01 |  | 2246958.27 | 30516470.92 | 20818330.66 | 9698140.26 | 45205818 | 21.45% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2018-12-01 |  | 930830.54 | 30516470.92 | 21749161.2 | 8767309.72 | 45205818 | 19.39% |  |  |  | cash out both |  |  | 2018
Marassi Bridge Pkg 117 | 2019-01-01 |  | 523327.33 | 30516470.92 | 22272488.53 | 8243982.39 | 45205818 | 18.24% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-01-20 | 4015282.83 |  | 34531753.75 | 22272488.53 | 12259265.22 | 45205818 | 27.12% |  |  | 2019-01-20 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-02-01 |  | 1203843.06 | 34531753.75 | 23476331.59 | 11055422.16 | 45205818 | 24.46% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-02-21 | 2578109.73 |  | 37109863.48 | 23476331.59 | 13633531.89 | 45205818 | 30.16% |  |  | 2019-02-21 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-02-21 | 229049.99 |  | 37338913.47 | 23476331.59 | 13862581.88 | 45205818 | 30.67% |  |  | 2019-02-21 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-03-01 |  | 2182046.24 | 37338913.47 | 25658377.83 | 11680535.64 | 45205818 | 25.84% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-03-14 | 882296.11 |  | 38221209.58 | 25658377.83 | 12562831.75 | 45205818 | 27.79% |  |  | 2019-03-14 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-04-01 |  | 517499.8 | 38221209.58 | 26175877.63 | 12045331.95 | 45205818 | 26.65% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-04-09 | 163866.22 |  | 38385075.8 | 26175877.63 | 12209198.17 | 45205818 | 27.01% |  |  | 2019-04-09 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-05-01 |  | 1186483.73 | 38385075.8 | 27362361.36 | 11022714.44 | 45205818 | 24.38% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-05-21 | 56058.22 |  | 38441134.02 | 27362361.36 | 11078772.66 | 45205818 | 24.51% |  |  | 2019-05-21 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-06-01 |  | 316875.55 | 38441134.02 | 27679236.91 | 10761897.11 | 45205818 | 23.81% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-06-10 | 809762.24 |  | 39250896.26 | 27679236.91 | 11571659.35 | 45205818 | 25.6% |  |  | 2019-06-10 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-07-01 |  | 203824.2 | 39250896.26 | 27883061.11 | 11367835.15 | 45205818 | 25.15% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-07-24 | 57062.55 |  | 39307958.81 | 27883061.11 | 11424897.7 | 45205818 | 25.27% |  |  | 2019-07-24 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-08-01 |  | 247991.13 | 39307958.81 | 28131052.24 | 11176906.57 | 45205818 | 24.72% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-09-01 |  | 147625.68 | 39307958.81 | 28278677.92 | 11029280.89 | 45205818 | 24.4% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-10-01 |  | 375458.68 | 39307958.81 | 28654136.6 | 10653822.21 | 45205818 | 23.57% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-11-01 |  | 355231.29 | 39307958.81 | 29009367.89 | 10298590.92 | 45205818 | 22.78% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-11-13 | 3376927.91 |  | 42684886.72 | 29009367.89 | 13675518.83 | 45205818 | 30.25% |  |  | 2019-11-13 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2019-12-01 |  | 4538747.53 | 42684886.72 | 33548115.42 | 9136771.3 | 45205818 | 20.21% |  |  |  | cash out both |  |  | 2019
Marassi Bridge Pkg 117 | 2019-12-18 | 3145907.11 |  | 45830793.83 | 33548115.42 | 12282678.41 | 45205818 | 27.17% |  |  | 2019-12-18 | added cash in 3 |  |  | 2019
Marassi Bridge Pkg 117 | 2020-01-01 |  | 1096980.84 | 45830793.83 | 34645096.26 | 11185697.57 | 45205818 | 24.74% |  |  |  | cash out both |  |  | 2020
Marassi Bridge Pkg 117 | 2020-02-01 |  | 397669.97 | 45830793.83 | 35042766.23 | 10788027.6 | 45205818 | 23.86% |  |  |  | cash out both |  |  | 2020
Marassi Bridge Pkg 117 | 2020-04-01 |  | 12390.38 | 45830793.83 | 35055156.61 | 10775637.22 | 45205818 | 23.84% |  |  |  | cash out both |  |  | 2020
Marassi Bridge Pkg 117 | 2020-04-09 | 285951.45 |  | 46116745.28 | 35055156.61 | 11061588.67 | 45205818 | 24.47% |  |  | 2020-04-09 | added 1 |  |  | 2020
Marassi Bridge Pkg 117 | 2020-07-01 |  | 15373.58 | 46116745.28 | 35070530.19 | 11046215.09 | 45205818 | 24.44% |  |  |  | cash out both |  |  | 2020
Marassi Bridge Pkg 117 | 2020-10-01 |  | 252803.38 | 46116745.28 | 35323333.57 | 10793411.71 | 45205818 | 23.88% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Marassi Bridge Pkg 117 | 2020-11-01 |  | 195238 | 46116745.28 | 35518571.57 | 10598173.71 | 45205818 | 23.44% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Marassi Bridge Pkg 117 | 2020-12-01 |  | 105849.34 | 46116745.28 | 35624420.91 | 10492324.37 | 45205818 | 23.21% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Marassi Bridge Pkg 117 | 2020-12-21 | 2483342.5 |  | 48600087.78 | 35624420.91 | 12975666.87 | 45205818 | 28.7% |  |  | 2020-12-21 | added cash in 3 |  |  | 2020
Marassi Bridge Pkg 117 | 2021-01-01 |  | 12390.38 | 48600087.78 | 35636811.29 | 12963276.49 | 45205818 | 28.68% |  |  |  | cash out both |  |  | 2021
Marassi Bridge Pkg 117 | 2021-02-01 |  | 81906.72 | 48600087.78 | 35718718.01 | 12881369.77 | 45205818 | 28.49% |  |  |  | cash out both |  |  | 2021
Marassi Bridge Pkg 117 | 2021-03-01 |  | 9700 | 48600087.78 | 35728418.01 | 12871669.77 | 45205818 | 28.47% |  |  |  | cash out both |  |  | 2021
1900
Siemens Power Station | 2017-11-01 |  | 325000 | 0 | 325000 | -325000 | 332856409 | -0.09764% |  |  |  | cash out both |  |  | 2017
Siemens Power Station | 2017-11-30 | 0 | 1386347 | 0 | 1711347 | -1711347 | 332856409 | -0.5141% |  | 0 | 2017-11-30 | original |  |  | 2017
Siemens Power Station | 2017-12-01 |  | 36105.04 | 0 | 1747452.04 | -1747452.04 | 332856409 | -0.525% |  |  |  | cash out both |  |  | 2017
Siemens Power Station | 2017-12-31 | 93300000 | 17946376 | 93300000 | 19693828.04 | 73606171.96 | 332856409 | 22.11% |  | 4401847 | 2017-12-31 | original |  |  | 2017
Siemens Power Station | 2018-01-01 |  | 2692849.35 | 93300000 | 22386677.39 | 70913322.61 | 332856409 | 21.3% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-02-01 |  | 13868263.53 | 93300000 | 36254940.92 | 57045059.08 | 332856409 | 17.14% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-03-01 |  | 15856372.59 | 93300000 | 52111313.51 | 41188686.49 | 332856409 | 12.37% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-03-05 | 3059283.73 |  | 96359283.73 | 52111313.51 | 44247970.22 | 332856409 | 13.29% |  |  | 2018-03-05 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-03-15 | 7201577.05 |  | 103560860.78 | 52111313.51 | 51449547.27 | 332856409 | 15.46% |  |  | 2018-03-15 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-04-01 |  | 20054182.34 | 103560860.78 | 72165495.85 | 31395364.93 | 332856409 | 9.432% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-04-29 | 11065687.7 |  | 114626548.48 | 72165495.85 | 42461052.63 | 332856409 | 12.76% |  |  | 2018-04-29 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-05-01 |  | 13243374.04 | 114626548.48 | 85408869.89 | 29217678.59 | 332856409 | 8.778% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-06-01 |  | 9644209.72 | 114626548.48 | 95053079.61 | 19573468.87 | 332856409 | 5.88% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-06-13 | 13218163.56 |  | 127844712.04 | 95053079.61 | 32791632.43 | 332856409 | 9.852% |  |  | 2018-06-13 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-07-01 |  | 17289950.78 | 127844712.04 | 112343030.39 | 15501681.65 | 332856409 | 4.657% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-07-17 | 7060448.9 |  | 134905160.94 | 112343030.39 | 22562130.55 | 332856409 | 6.778% |  |  | 2018-07-17 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-07-30 | 8833159.82 |  | 143738320.76 | 112343030.39 | 31395290.37 | 332856409 | 9.432% |  |  | 2018-07-30 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-08-01 |  | 7125695.83 | 143738320.76 | 119468726.22 | 24269594.54 | 332856409 | 7.291% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-08-14 | 12641621.4 |  | 156379942.16 | 119468726.22 | 36911215.94 | 332856409 | 11.09% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-09-01 |  | 20998983.27 | 156379942.16 | 140467709.49 | 15912232.67 | 332856409 | 4.781% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-09-17 | 13673026.82 |  | 170052968.98 | 140467709.49 | 29585259.49 | 332856409 | 8.888% |  |  | 2018-09-17 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-10-01 |  | 27846645.1 | 170052968.98 | 168314354.59 | 1738614.39 | 332856409 | 0.5223% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-10-15 | 6271528.33 |  | 176324497.31 | 168314354.59 | 8010142.72 | 332856409 | 2.406% |  |  | 2018-10-15 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-11-01 |  | 26331552.1 | 176324497.31 | 194645906.69 | -18321409.38 | 332856409 | -5.504% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-11-08 | 5230123.67 |  | 181554620.98 | 194645906.69 | -13091285.71 | 332856409 | -3.933% |  |  | 2018-11-08 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-11-21 | 20041232.56 |  | 201595853.54 | 194645906.69 | 6949946.85 | 332856409 | 2.088% |  |  | 2018-11-21 | added cash in 3 |  |  | 2018
Siemens Power Station | 2018-12-01 |  | 21352523.97 | 201595853.54 | 215998430.66 | -14402577.12 | 332856409 | -4.327% |  |  |  | cash out both |  |  | 2018
Siemens Power Station | 2018-12-11 | 17822796.64 |  | 219418650.18 | 215998430.66 | 3420219.52 | 332856409 | 1.028% |  |  | 2018-12-11 | added cash in 3 |  |  | 2018
Siemens Power Station | 2019-01-01 |  | 20382650.41 | 219418650.18 | 236381081.07 | -16962430.89 | 332856409 | -5.096% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-01-06 | 20002003.08 |  | 239420653.26 | 236381081.07 | 3039572.19 | 332856409 | 0.9132% |  |  | 2019-01-06 | added cash in 3 |  |  | 2019
Siemens Power Station | 2019-02-01 |  | 14215044.71 | 239420653.26 | 250596125.78 | -11175472.52 | 332856409 | -3.357% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-02-07 | 27970974.36 |  | 267391627.62 | 250596125.78 | 16795501.84 | 332856409 | 5.046% |  |  | 2019-02-07 | added cash in 3 |  |  | 2019
Siemens Power Station | 2019-03-01 |  | 19918306.52 | 267391627.62 | 270514432.3 | -3122804.68 | 332856409 | -0.9382% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-04-01 |  | 15576469.86 | 267391627.62 | 286090902.16 | -18699274.54 | 332856409 | -5.618% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-05-01 |  | 10157200.82 | 267391627.62 | 296248102.98 | -28856475.36 | 332856409 | -8.669% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-05-13 | 20418831.59 |  | 287810459.21 | 296248102.98 | -8437643.77 | 332856409 | -2.535% |  |  | 2019-05-13 | added cash in 3 |  |  | 2019
Siemens Power Station | 2019-06-01 |  | 6560392.16 | 287810459.21 | 302808495.14 | -14998035.93 | 332856409 | -4.506% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-07-01 |  | 2536532.82 | 287810459.21 | 305345027.96 | -17534568.75 | 332856409 | -5.268% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-08-01 |  | 4693731.53 | 287810459.21 | 310038759.49 | -22228300.28 | 332856409 | -6.678% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-09-01 |  | 4150447.48 | 287810459.21 | 314189206.97 | -26378747.76 | 332856409 | -7.925% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-09-29 | 12124718 |  | 299935177.21 | 314189206.97 | -14254029.76 | 332856409 | -4.282% |  |  | 2019-09-29 | added cash in 3 |  |  | 2019
Siemens Power Station | 2019-10-01 |  | 1291060.92 | 299935177.21 | 315480267.89 | -15545090.68 | 332856409 | -4.67% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-11-01 |  | 525714.18 | 299935177.21 | 316005982.07 | -16070804.86 | 332856409 | -4.828% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2019-12-01 |  | 2185295.58 | 299935177.21 | 318191277.65 | -18256100.44 | 332856409 | -5.485% |  |  |  | cash out both |  |  | 2019
Siemens Power Station | 2020-01-01 |  | 1392288.2 | 299935177.21 | 319583565.85 | -19648388.64 | 332856409 | -5.903% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-02-01 |  | 1036801.86 | 299935177.21 | 320620367.71 | -20685190.5 | 332856409 | -6.214% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-02-23 | 25672200.91 |  | 325607378.12 | 320620367.71 | 4987010.41 | 332856409 | 1.498% |  |  | 2020-02-23 | added 1 |  |  | 2020
Siemens Power Station | 2020-03-01 |  | 5406000.02 | 325607378.12 | 326026367.73 | -418989.61 | 332856409 | -0.1259% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-03-19 | 15319191 |  | 340926569.12 | 326026367.73 | 14900201.39 | 332856409 | 4.476% |  |  | 2020-03-19 | added 1 |  |  | 2020
Siemens Power Station | 2020-04-01 |  | 816601.57 | 340926569.12 | 326842969.3 | 14083599.82 | 332856409 | 4.231% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-05-01 |  | 2090061.1 | 340926569.12 | 328933030.4 | 11993538.72 | 332856409 | 3.603% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-06-01 |  | 195960.88 | 340926569.12 | 329128991.28 | 11797577.84 | 332856409 | 3.544% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-07-01 |  | 1332197.1 | 340926569.12 | 330461188.38 | 10465380.74 | 332856409 | 3.144% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-08-01 |  | 150348.5 | 340926569.12 | 330611536.88 | 10315032.24 | 332856409 | 3.099% |  |  |  | cash out both |  |  | 2020
Siemens Power Station | 2020-09-30 | 144907 |  | 341071476.12 | 330611536.88 | 10459939.24 | 332856409 | 3.142% |  |  | 2020-09-30 | added 1 |  |  | 2020
Siemens Power Station | 2020-10-01 |  | 829761.26 | 341071476.12 | 331441298.14 | 9630177.98 | 332856409 | 2.893% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Siemens Power Station | 2020-11-01 |  | 108900 | 341071476.12 | 331550198.14 | 9521277.98 | 332856409 | 2.86% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Siemens Power Station | 2020-11-18 | 888628.7 |  | 341960104.82 | 331550198.14 | 10409906.68 | 332856409 | 3.127% |  |  | 2020-11-18 | added cash in 3 |  |  | 2020
Siemens Power Station | 2020-12-01 |  | 479946.07 | 341960104.82 | 332030144.21 | 9929960.61 | 332856409 | 2.983% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Siemens Power Station | 2021-02-01 |  | 1677560.13 | 341960104.82 | 333707704.34 | 8252400.48 | 332856409 | 2.479% |  |  |  | cash out both |  |  | 2021
Siemens Power Station | 2021-03-01 |  | 138860.39 | 341960104.82 | 333846564.73 | 8113540.09 | 332856409 | 2.438% |  |  |  | cash out both |  |  | 2021
1900
Uptown FM85 Pkg 85 | 2017-11-30 | 1692495 |  | 1692495 | 0 | 1692495 | 0 | #DIV/0! |  |  | 2017-11-30 | added cash in 3 |  |  | 2017
Uptown FM85 Pkg 85 | 2018-01-01 |  | 296517.99 | 1692495 | 296517.99 | 1395977.01 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-01-18 | 813632.52 |  | 2506127.52 | 296517.99 | 2209609.53 | 0 | #DIV/0! |  |  | 2018-01-18 | added cash in 3 |  |  | 2018
Uptown FM85 Pkg 85 | 2018-02-01 |  | 53199.39 | 2506127.52 | 349717.38 | 2156410.14 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-03-01 |  | 177163.25 | 2506127.52 | 526880.63 | 1979246.89 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-03-22 | 293424.13 |  | 2799551.65 | 526880.63 | 2272671.02 | 0 | #DIV/0! |  |  | 2018-03-22 | added cash in 3 |  |  | 2018
Uptown FM85 Pkg 85 | 2018-04-01 |  | 213603.84 | 2799551.65 | 740484.47 | 2059067.18 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-05-01 |  | 80420 | 2799551.65 | 820904.47 | 1978647.18 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-06-01 |  | 165464.4 | 2799551.65 | 986368.87 | 1813182.78 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-07-01 |  | 227927.8 | 2799551.65 | 1214296.67 | 1585254.98 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-08-01 |  | 26592.19 | 2799551.65 | 1240888.86 | 1558662.79 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-08-19 | 247265.58 |  | 3046817.23 | 1240888.86 | 1805928.37 | 0 | #DIV/0! |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Uptown FM85 Pkg 85 | 2018-08-19 | 1837500 |  | 4884317.23 | 1240888.86 | 3643428.37 | 0 | #DIV/0! |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Uptown FM85 Pkg 85 | 2018-08-19 | 409998.48 |  | 5294315.71 | 1240888.86 | 4053426.85 | 0 | #DIV/0! |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Uptown FM85 Pkg 85 | 2018-09-01 |  | 52100 | 5294315.71 | 1292988.86 | 4001326.85 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-10-01 |  | 296570 | 5294315.71 | 1589558.86 | 3704756.85 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-11-01 |  | 645015.14 | 5294315.71 | 2234574 | 3059741.71 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2018-12-01 |  | 314147.25 | 5294315.71 | 2548721.25 | 2745594.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
Uptown FM85 Pkg 85 | 2019-01-01 |  | 190646.71 | 5294315.71 | 2739367.96 | 2554947.75 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Uptown FM85 Pkg 85 | 2019-02-01 |  | 246164.2 | 5294315.71 | 2985532.16 | 2308783.55 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Uptown FM85 Pkg 85 | 2019-02-10 | 1729285.15 |  | 7023600.86 | 2985532.16 | 4038068.7 | 0 | #DIV/0! |  |  | 2019-02-10 | added cash in 3 |  |  | 2019
Uptown FM85 Pkg 85 | 2019-03-01 |  | 16025 | 7023600.86 | 3001557.16 | 4022043.7 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Uptown FM85 Pkg 85 | 2019-05-01 |  | 62219.61 | 7023600.86 | 3063776.77 | 3959824.09 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Uptown FM85 Pkg 85 | 2019-05-21 | 768766.59 |  | 7792367.45 | 3063776.77 | 4728590.68 | 0 | #DIV/0! |  |  | 2019-05-21 | added cash in 3 |  |  | 2019
Uptown FM85 Pkg 85 | 2019-08-01 |  | 21500 | 7792367.45 | 3085276.77 | 4707090.68 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Uptown FM85 Pkg 85 | 2020-01-15 | 29830.3 |  | 7822197.75 | 3085276.77 | 4736920.98 | 0 | #DIV/0! |  |  | 2020-01-15 | added 1 |  |  | 2020
Uptown FM85 Pkg 85 | 2020-03-01 |  | 247925 | 7822197.75 | 3333201.77 | 4488995.98 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
Uptown FM85 Pkg 85 | 2020-04-29 | 1391898.96 |  | 9214096.71 | 3333201.77 | 5880894.94 | 0 | #DIV/0! |  |  | 2020-04-29 | added 1 |  |  | 2020
Uptown FM85 Pkg 85 | 2021-02-01 |  | 98875 | 9214096.71 | 3432076.77 | 5782019.94 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2021
1900
El Sokhna Tunnel 01 | 2018-01-01 |  | 332132.97 | 0 | 332132.97 | -332132.97 | 46639513 | -0.7121% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-02-01 |  | 260504.32 | 0 | 592637.29 | -592637.29 | 46639513 | -1.271% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-03-01 |  | 1433831.6 | 0 | 2026468.89 | -2026468.89 | 46639513 | -4.345% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-04-01 |  | 491806.59 | 0 | 2518275.48 | -2518275.48 | 46639513 | -5.399% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-05-01 |  | 2892827.27 | 0 | 5411102.75 | -5411102.75 | 46639513 | -11.6% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-06-01 |  | 3549019.15 | 0 | 8960121.9 | -8960121.9 | 46639513 | -19.21% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-07-01 |  | 1683429.59 | 0 | 10643551.49 | -10643551.49 | 46639513 | -22.82% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-08-01 |  | 1045341.82 | 0 | 11688893.31 | -11688893.31 | 46639513 | -25.06% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-09-01 |  | 1425805.89 | 0 | 13114699.2 | -13114699.2 | 46639513 | -28.12% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-09-24 | 16465907 |  | 16465907 | 13114699.2 | 3351207.8 | 46639513 | 7.185% |  |  | 2018-09-24 | added cash in 3 |  |  | 2018
El Sokhna Tunnel 01 | 2018-09-25 | 13239993 |  | 29705900 | 13114699.2 | 16591200.8 | 46639513 | 35.57% |  |  | 2018-09-25 | added cash in 3 |  |  | 2018
El Sokhna Tunnel 01 | 2018-10-01 |  | 1459978.03 | 29705900 | 14574677.23 | 15131222.77 | 46639513 | 32.44% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-10-28 | 2369466.65 |  | 32075366.65 | 14574677.23 | 17500689.42 | 46639513 | 37.52% |  |  | 2018-10-28 | added cash in 3 |  |  | 2018
El Sokhna Tunnel 01 | 2018-11-01 |  | 666332.68 | 32075366.65 | 15241009.91 | 16834356.74 | 46639513 | 36.09% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-11-06 | 2014847.9 |  | 34090214.55 | 15241009.91 | 18849204.64 | 46639513 | 40.41% |  |  | 2018-11-06 | added cash in 3 |  |  | 2018
El Sokhna Tunnel 01 | 2018-12-01 |  | 145169.08 | 34090214.55 | 15386178.99 | 18704035.56 | 46639513 | 40.1% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 01 | 2018-12-25 | 3305891.9 |  | 37396106.45 | 15386178.99 | 22009927.46 | 46639513 | 47.19% |  |  | 2018-12-25 | added cash in 3 |  |  | 2018
El Sokhna Tunnel 01 | 2018-12-26 | 1310500 |  | 38706606.45 | 15386178.99 | 23320427.46 | 46639513 | 50% |  |  | 2018-12-26 | added cash in 3 |  |  | 2018
El Sokhna Tunnel 01 | 2019-01-01 |  | 684833.66 | 38706606.45 | 16071012.65 | 22635593.8 | 46639513 | 48.53% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 01 | 2019-02-01 |  | 55943.56 | 38706606.45 | 16126956.21 | 22579650.24 | 46639513 | 48.41% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 01 | 2019-03-01 |  | 41837.18 | 38706606.45 | 16168793.39 | 22537813.06 | 46639513 | 48.32% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 01 | 2019-05-01 |  | 10312.02 | 38706606.45 | 16179105.41 | 22527501.04 | 46639513 | 48.3% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 01 | 2019-07-03 | 1116704.5 |  | 39823310.95 | 16179105.41 | 23644205.54 | 46639513 | 50.7% |  |  | 2019-07-03 | added cash in 3 |  |  | 2019
El Sokhna Tunnel 01 | 2019-12-01 |  | 674528 | 39823310.95 | 16853633.41 | 22969677.54 | 46639513 | 49.25% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 01 | 2020-09-09 | 1702965 |  | 41526275.95 | 16853633.41 | 24672642.54 | 46639513 | 52.9% |  |  | 2020-09-09 | added cash in 3 |  |  | 2020
El Sokhna Tunnel 01 | 2021-02-01 |  | 1116.71 | 41526275.95 | 16854750.12 | 24671525.83 | 46639513 | 52.9% |  |  |  | cash out both |  |  | 2021
El Sokhna Tunnel 01 | 2021-03-01 |  | 81 | 41526275.95 | 16854831.12 | 24671444.83 | 46639513 | 52.9% |  |  |  | cash out both |  |  | 2021
1900
Abu Sultan Bridge 01 | 2018-01-01 |  | 99700 | 0 | 99700 | -99700 | 18752986 | -0.5316% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-02-01 |  | 339116.34 | 0 | 438816.34 | -438816.34 | 18752986 | -2.34% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-03-01 |  | 288546.9 | 0 | 727363.24 | -727363.24 | 18752986 | -3.879% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-04-01 |  | 194305.82 | 0 | 921669.06 | -921669.06 | 18752986 | -4.915% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-05-01 |  | 957258.78 | 0 | 1878927.84 | -1878927.84 | 18752986 | -10.02% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-06-01 |  | 1343658.02 | 0 | 3222585.86 | -3222585.86 | 18752986 | -17.18% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-07-01 |  | 1524434.49 | 0 | 4747020.35 | -4747020.35 | 18752986 | -25.31% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-08-01 |  | 1225823.63 | 0 | 5972843.98 | -5972843.98 | 18752986 | -31.85% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-09-01 |  | 1370928.36 | 0 | 7343772.34 | -7343772.34 | 18752986 | -39.16% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-10-01 |  | 896181.84 | 0 | 8239954.18 | -8239954.18 | 18752986 | -43.94% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-11-01 |  | 1352163.46 | 0 | 9592117.64 | -9592117.64 | 18752986 | -51.15% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2018-12-01 |  | 1399972.07 | 0 | 10992089.71 | -10992089.71 | 18752986 | -58.62% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 01 | 2019-01-01 |  | 14286.61 | 0 | 11006376.32 | -11006376.32 | 18752986 | -58.69% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 01 | 2019-01-31 | 11280475 |  | 11280475 | 11006376.32 | 274098.68 | 18752986 | 1.462% |  |  | 2019-01-31 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 01 | 2019-02-01 |  | 68140.8 | 11280475 | 11074517.12 | 205957.88 | 18752986 | 1.098% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 01 | 2019-03-01 |  | 71808.22 | 11280475 | 11146325.34 | 134149.66 | 18752986 | 0.7154% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 01 | 2019-04-01 |  | 1500 | 11280475 | 11147825.34 | 132649.66 | 18752986 | 0.7074% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 01 | 2019-06-01 |  | 1221 | 11280475 | 11149046.34 | 131428.66 | 18752986 | 0.7008% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 01 | 2019-12-01 |  | 20107 | 11280475 | 11169153.34 | 111321.66 | 18752986 | 0.5936% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 01 | 2019-12-31 | 495270 |  | 11775745 | 11169153.34 | 606591.66 | 18752986 | 3.235% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 01 | 2020-01-26 | 664967 |  | 12440712 | 11169153.34 | 1271558.66 | 18752986 | 6.781% |  |  | 2020-01-26 | added 1 |  |  | 2020
Abu Sultan Bridge 01 | 2020-02-01 |  | 3525.75 | 12440712 | 11172679.09 | 1268032.91 | 18752986 | 6.762% |  |  |  | cash out both |  |  | 2020
1900
Mintra Factory | 2018-01-17 | 10000000 |  | 10000000 | 0 | 10000000 | 112045826 | 8.925% |  |  | 2018-01-17 | added cash in 3 |  |  | 2018
Mintra Factory | 2018-02-01 |  | 138415 | 10000000 | 138415 | 9861585 | 112045826 | 8.801% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-03-01 |  | 1857867.59 | 10000000 | 1996282.59 | 8003717.41 | 112045826 | 7.143% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-04-01 |  | 1042147.17 | 10000000 | 3038429.76 | 6961570.24 | 112045826 | 6.213% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-04-24 | 1500000 |  | 11500000 | 3038429.76 | 8461570.24 | 112045826 | 7.552% |  |  | 2018-04-24 | added cash in 3 |  |  | 2018
Mintra Factory | 2018-05-01 |  | 1699029.18 | 11500000 | 4737458.94 | 6762541.06 | 112045826 | 6.036% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-06-01 |  | 5830118.14 | 11500000 | 10567577.08 | 932422.92 | 112045826 | 0.8322% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-06-10 | 4000000 |  | 15500000 | 10567577.08 | 4932422.92 | 112045826 | 4.402% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Mintra Factory | 2018-07-01 |  | 2214918.06 | 15500000 | 12782495.14 | 2717504.86 | 112045826 | 2.425% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-08-01 |  | 2908079.66 | 15500000 | 15690574.8 | -190574.8 | 112045826 | -0.1701% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-08-15 | 3000000 |  | 18500000 | 15690574.8 | 2809425.2 | 112045826 | 2.507% |  |  | 2018-08-15 | added cash in 3 |  |  | 2018
Mintra Factory | 2018-09-01 |  | 6129955.33 | 18500000 | 21820530.13 | -3320530.13 | 112045826 | -2.964% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-10-01 |  | 2840033.34 | 18500000 | 24660563.47 | -6160563.47 | 112045826 | -5.498% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-10-16 | 2220782.14 |  | 20720782.14 | 24660563.47 | -3939781.33 | 112045826 | -3.516% |  |  | 2018-10-16 | added cash in 3 |  |  | 2018
Mintra Factory | 2018-11-01 |  | 4006449.74 | 20720782.14 | 28667013.21 | -7946231.07 | 112045826 | -7.092% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-11-06 | 531998.67 |  | 21252780.81 | 28667013.21 | -7414232.4 | 112045826 | -6.617% |  |  | 2018-11-06 | added cash in 3 |  |  | 2018
Mintra Factory | 2018-11-22 | 3500000 |  | 24752780.81 | 28667013.21 | -3914232.4 | 112045826 | -3.493% |  |  | 2018-11-22 | added cash in 3 |  |  | 2018
Mintra Factory | 2018-12-01 |  | 2692007.54 | 24752780.81 | 31359020.75 | -6606239.94 | 112045826 | -5.896% |  |  |  | cash out both |  |  | 2018
Mintra Factory | 2018-12-30 | 8000000 |  | 32752780.81 | 31359020.75 | 1393760.06 | 112045826 | 1.244% |  |  | 2018-12-30 | added cash in 3 |  |  | 2018
Mintra Factory | 2019-01-01 |  | 2508200.16 | 32752780.81 | 33867220.91 | -1114440.1 | 112045826 | -0.9946% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-02-01 |  | 2185912.68 | 32752780.81 | 36053133.59 | -3300352.78 | 112045826 | -2.946% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-03-01 |  | 1164893.68 | 32752780.81 | 37218027.27 | -4465246.46 | 112045826 | -3.985% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-04-01 |  | 984398.2 | 32752780.81 | 38202425.47 | -5449644.66 | 112045826 | -4.864% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-04-02 | 3000000 |  | 35752780.81 | 38202425.47 | -2449644.66 | 112045826 | -2.186% |  |  | 2019-04-02 | added cash in 3 |  |  | 2019
Mintra Factory | 2019-05-01 |  | 1046236.19 | 35752780.81 | 39248661.66 | -3495880.85 | 112045826 | -3.12% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-05-28 | 3000000 |  | 38752780.81 | 39248661.66 | -495880.85 | 112045826 | -0.4426% |  |  | 2019-05-28 | added cash in 3 |  |  | 2019
Mintra Factory | 2019-06-01 |  | 346450.46 | 38752780.81 | 39595112.12 | -842331.31 | 112045826 | -0.7518% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-07-01 |  | 295577.76 | 38752780.81 | 39890689.88 | -1137909.07 | 112045826 | -1.016% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-08-01 |  | 990628.41 | 38752780.81 | 40881318.29 | -2128537.48 | 112045826 | -1.9% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-09-01 |  | 917579.61 | 38752780.81 | 41798897.9 | -3046117.09 | 112045826 | -2.719% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-10-01 |  | 248013.15 | 38752780.81 | 42046911.05 | -3294130.24 | 112045826 | -2.94% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-11-01 |  | 16213.92 | 38752780.81 | 42063124.97 | -3310344.16 | 112045826 | -2.954% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-12-01 |  | 319930.18 | 38752780.81 | 42383055.15 | -3630274.34 | 112045826 | -3.24% |  |  |  | cash out both |  |  | 2019
Mintra Factory | 2019-12-31 | 47941930.12 |  | 86694710.93 | 42383055.15 | 44311655.78 | 112045826 | 39.55% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Mintra Factory | 2020-01-01 |  | 20124.99 | 86694710.93 | 42403180.14 | 44291530.79 | 112045826 | 39.53% |  |  |  | cash out both |  |  | 2020
Mintra Factory | 2020-02-01 |  | 70032.41 | 86694710.93 | 42473212.55 | 44221498.38 | 112045826 | 39.47% |  |  |  | cash out both |  |  | 2020
Mintra Factory | 2020-03-01 |  | 120619.12 | 86694710.93 | 42593831.67 | 44100879.26 | 112045826 | 39.36% |  |  |  | cash out both |  |  | 2020
Mintra Factory | 2020-04-01 |  | 90025.05 | 86694710.93 | 42683856.72 | 44010854.21 | 112045826 | 39.28% |  |  |  | cash out both |  |  | 2020
Mintra Factory | 2020-05-01 |  | 86818.53 | 86694710.93 | 42770675.25 | 43924035.68 | 112045826 | 39.2% |  |  |  | cash out both |  |  | 2020
Mintra Factory | 2020-06-01 |  | 469061.83 | 86694710.93 | 43239737.08 | 43454973.85 | 112045826 | 38.78% |  |  |  | cash out both |  |  | 2020
Mintra Factory | 2020-09-01 |  | 66123.38 | 86694710.93 | 43305860.46 | 43388850.47 | 112045826 | 38.72% |  |  |  | cash out both |  |  | 2020
Mintra Factory | 2020-10-01 |  | 71495 | 86694710.93 | 43377355.46 | 43317355.47 | 112045826 | 38.66% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Mintra Factory | 2020-11-01 |  | 3513.52 | 86694710.93 | 43380868.98 | 43313841.95 | 112045826 | 38.66% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Mintra Factory | 2020-12-01 |  | 117222.45 | 86694710.93 | 43498091.43 | 43196619.5 | 112045826 | 38.55% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Mintra Factory | 2021-02-08 | 500000 |  | 87194710.93 | 43498091.43 | 43696619.5 | 112045826 | 39% |  |  | 2021-02-08 | added cash in 3 |  |  | 2021
Mintra Factory | 2021-02-08 | 499731.72 |  | 87694442.65 | 43498091.43 | 44196351.22 | 112045826 | 39.44% |  |  | 2021-02-08 | added cash in 3 |  |  | 2021
Mintra Factory | 2021-02-09 | 1999731.73 |  | 89694174.38 | 43498091.43 | 46196082.95 | 112045826 | 41.23% |  |  | 2021-02-09 | added 1 |  |  | 2021
Mintra Factory | 2021-03-01 |  | 7949.5 | 89694174.38 | 43506040.93 | 46188133.45 | 112045826 | 41.22% |  |  |  | cash out both |  |  | 2021
1900
King Farouk Restoration | 2018-04-01 |  | 20258.6 | 0 | 20258.6 | -20258.6 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
King Farouk Restoration | 2018-05-01 |  | 39355 | 0 | 59613.6 | -59613.6 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
King Farouk Restoration | 2018-06-01 |  | 25234.25 | 0 | 84847.85 | -84847.85 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
King Farouk Restoration | 2018-07-01 |  | 18497.2 | 0 | 103345.05 | -103345.05 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
King Farouk Restoration | 2018-08-01 |  | 6160 | 0 | 109505.05 | -109505.05 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
1900
Mohamed Ali Palace | 2018-03-01 |  | 16115 | 0 | 16115 | -16115 | 150000000 | -0.01074% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-03-13 | 5800000 |  | 5800000 | 16115 | 5783885 | 150000000 | 3.856% |  |  | 2018-03-13 | added cash in 3 |  |  | 2018
Mohamed Ali Palace | 2018-04-01 |  | 122274 | 5800000 | 138389 | 5661611 | 150000000 | 3.774% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-05-01 |  | 411107.95 | 5800000 | 549496.95 | 5250503.05 | 150000000 | 3.5% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-06-01 |  | 333148.55 | 5800000 | 882645.5 | 4917354.5 | 150000000 | 3.278% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-07-01 |  | 155537.98 | 5800000 | 1038183.48 | 4761816.52 | 150000000 | 3.175% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-08-01 |  | 627647.03 | 5800000 | 1665830.51 | 4134169.49 | 150000000 | 2.756% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-08-19 | 2700000 |  | 8500000 | 1665830.51 | 6834169.49 | 150000000 | 4.556% |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Mohamed Ali Palace | 2018-09-01 |  | 639235.38 | 8500000 | 2305065.89 | 6194934.11 | 150000000 | 4.13% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-10-01 |  | 673355.81 | 8500000 | 2978421.7 | 5521578.3 | 150000000 | 3.681% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-11-01 |  | 1172087.2 | 8500000 | 4150508.9 | 4349491.1 | 150000000 | 2.9% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2018-12-01 |  | 1168321.79 | 8500000 | 5318830.69 | 3181169.31 | 150000000 | 2.121% |  |  |  | cash out both |  |  | 2018
Mohamed Ali Palace | 2019-01-01 |  | 822985.11 | 8500000 | 6141815.8 | 2358184.2 | 150000000 | 1.572% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-02-01 |  | 996248.18 | 8500000 | 7138063.98 | 1361936.02 | 150000000 | 0.908% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-03-01 |  | 1170433.23 | 8500000 | 8308497.21 | 191502.79 | 150000000 | 0.1277% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-04-01 |  | 1577851.14 | 8500000 | 9886348.35 | -1386348.35 | 150000000 | -0.9242% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-05-01 |  | 1314462.57 | 8500000 | 11200810.92 | -2700810.92 | 150000000 | -1.801% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-06-01 |  | 1435290.59 | 8500000 | 12636101.51 | -4136101.51 | 150000000 | -2.757% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-07-01 |  | 2879743.91 | 8500000 | 15515845.42 | -7015845.42 | 150000000 | -4.677% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-08-01 |  | 1446316.66 | 8500000 | 16962162.08 | -8462162.08 | 150000000 | -5.641% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-09-01 |  | 1739488.36 | 8500000 | 18701650.44 | -10201650.44 | 150000000 | -6.801% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-10-01 |  | 916732.18 | 8500000 | 19618382.62 | -11118382.62 | 150000000 | -7.412% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-11-01 |  | 2250260.91 | 8500000 | 21868643.53 | -13368643.53 | 150000000 | -8.912% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2019-12-01 |  | 2913698.17 | 8500000 | 24782341.7 | -16282341.7 | 150000000 | -10.85% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Palace | 2020-01-01 |  | 1961976.68 | 8500000 | 26744318.38 | -18244318.38 | 150000000 | -12.16% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-02-01 |  | 1086385.92 | 8500000 | 27830704.3 | -19330704.3 | 150000000 | -12.89% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-03-01 |  | 628881.02 | 8500000 | 28459585.32 | -19959585.32 | 150000000 | -13.31% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-03-15 | 18753780 |  | 27253780 | 28459585.32 | -1205805.32 | 150000000 | -0.8039% |  |  | 2020-03-15 | added 1 |  |  | 2020
Mohamed Ali Palace | 2020-03-25 | 4205847 |  | 31459627 | 28459585.32 | 3000041.68 | 150000000 | 2% |  |  | 2020-03-25 | added 1 |  |  | 2020
Mohamed Ali Palace | 2020-04-01 |  | 855430.16 | 31459627 | 29315015.48 | 2144611.52 | 150000000 | 1.43% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-05-01 |  | 1032518.29 | 31459627 | 30347533.77 | 1112093.23 | 150000000 | 0.7414% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-06-01 |  | 990392.09 | 31459627 | 31337925.86 | 121701.14 | 150000000 | 0.08113% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-07-01 |  | 3352570.33 | 31459627 | 34690496.19 | -3230869.19 | 150000000 | -2.154% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-08-01 |  | 2064789.27 | 31459627 | 36755285.46 | -5295658.46 | 150000000 | -3.53% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-09-01 |  | 2220668.47 | 31459627 | 38975953.93 | -7516326.93 | 150000000 | -5.011% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Palace | 2020-10-01 |  | 3545688.26 | 31459627 | 42521642.19 | -11062015.19 | 150000000 | -7.375% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Mohamed Ali Palace | 2020-10-04 | 572405 |  | 32032032 | 42521642.19 | -10489610.19 | 150000000 | -6.993% |  |  | 2020-10-04 | added cash in 3 |  |  | 2020
Mohamed Ali Palace | 2020-11-01 |  | 5461955.2 | 32032032 | 47983597.39 | -15951565.39 | 150000000 | -10.63% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Mohamed Ali Palace | 2020-12-01 |  | 4701467.52 | 32032032 | 52685064.91 | -20653032.91 | 150000000 | -13.77% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Mohamed Ali Palace | 2021-01-01 |  | 4699528.24 | 32032032 | 57384593.15 | -25352561.15 | 150000000 | -16.9% |  |  |  | cash out both |  |  | 2021
Mohamed Ali Palace | 2021-01-31 | 1597635 |  | 33629667 | 57384593.15 | -23754926.15 | 150000000 | -15.84% |  |  | 2021-01-31 | added cash in 3 |  |  | 2021
Mohamed Ali Palace | 2021-02-01 |  | 3110502.73 | 33629667 | 60495095.88 | -26865428.88 | 150000000 | -17.91% |  |  |  | cash out both |  |  | 2021
Mohamed Ali Palace | 2021-03-01 |  | 5253442.88 | 33629667 | 65748538.76 | -32118871.76 | 150000000 | -21.41% |  |  |  | cash out both |  |  | 2021
1900
Nefisha Bridge | 2018-03-01 |  | 165869.05 | 0 | 165869.05 | -165869.05 | 70928098 | -0.2339% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-04-01 |  | 73090 | 0 | 238959.05 | -238959.05 | 70928098 | -0.3369% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-05-01 |  | 235755.71 | 0 | 474714.76 | -474714.76 | 70928098 | -0.6693% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-06-01 |  | 198714.37 | 0 | 673429.13 | -673429.13 | 70928098 | -0.9495% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-07-01 |  | 1424063 | 0 | 2097492.13 | -2097492.13 | 70928098 | -2.957% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-08-01 |  | 1865942.45 | 0 | 3963434.58 | -3963434.58 | 70928098 | -5.588% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-08-19 | 22000000 |  | 22000000 | 3963434.58 | 18036565.42 | 70928098 | 25.43% |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Nefisha Bridge | 2018-09-01 |  | 4441560.05 | 22000000 | 8404994.63 | 13595005.37 | 70928098 | 19.17% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-10-01 |  | 4354340.91 | 22000000 | 12759335.54 | 9240664.46 | 70928098 | 13.03% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-11-01 |  | 3160685.81 | 22000000 | 15920021.35 | 6079978.65 | 70928098 | 8.572% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-12-01 |  | 2047482.98 | 22000000 | 17967504.33 | 4032495.67 | 70928098 | 5.685% |  |  |  | cash out both |  |  | 2018
Nefisha Bridge | 2018-12-27 | 27117730 |  | 49117730 | 17967504.33 | 31150225.67 | 70928098 | 43.92% |  |  | 2018-12-27 | added cash in 3 |  |  | 2018
Nefisha Bridge | 2019-01-01 |  | 1952928.38 | 49117730 | 19920432.71 | 29197297.29 | 70928098 | 41.16% |  |  |  | cash out both |  |  | 2019
Nefisha Bridge | 2019-02-01 |  | 973730.81 | 49117730 | 20894163.52 | 28223566.48 | 70928098 | 39.79% |  |  |  | cash out both |  |  | 2019
Nefisha Bridge | 2019-02-07 | 12381198.65 |  | 61498928.65 | 20894163.52 | 40604765.13 | 70928098 | 57.25% |  |  | 2019-02-07 | added cash in 3 |  |  | 2019
Nefisha Bridge | 2019-03-01 |  | 766775.78 | 61498928.65 | 21660939.3 | 39837989.35 | 70928098 | 56.17% |  |  |  | cash out both |  |  | 2019
Nefisha Bridge | 2019-04-01 |  | 42076.9 | 61498928.65 | 21703016.2 | 39795912.45 | 70928098 | 56.11% |  |  |  | cash out both |  |  | 2019
Nefisha Bridge | 2019-06-01 |  | 319177 | 61498928.65 | 22022193.2 | 39476735.45 | 70928098 | 55.66% |  |  |  | cash out both |  |  | 2019
Nefisha Bridge | 2019-07-16 | 9103986.25 |  | 70602914.9 | 22022193.2 | 48580721.7 | 70928098 | 68.49% |  |  | 2019-07-16 | added cash in 3 |  |  | 2019
Nefisha Bridge | 2019-07-22 | 2590581.3 |  | 73193496.2 | 22022193.2 | 51171303 | 70928098 | 72.15% |  |  | 2019-07-22 | added cash in 3 |  |  | 2019
Nefisha Bridge | 2019-08-01 |  | 16740 | 73193496.2 | 22038933.2 | 51154563 | 70928098 | 72.12% |  |  |  | cash out both |  |  | 2019
Nefisha Bridge | 2019-12-01 |  | 13262259.73 | 73193496.2 | 35301192.93 | 37892303.27 | 70928098 | 53.42% |  |  |  | cash out both |  |  | 2019
1900
Fish Market | 2018-03-01 |  | 30000 | 0 | 30000 | -30000 | 66185668.5714 | -0.04533% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-04-01 |  | 43015 | 0 | 73015 | -73015 | 66185668.5714 | -0.1103% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-05-01 |  | 39990.5 | 0 | 113005.5 | -113005.5 | 66185668.5714 | -0.1707% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-06-01 |  | 471730.33 | 0 | 584735.83 | -584735.83 | 66185668.5714 | -0.8835% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-07-01 |  | 144257.88 | 0 | 728993.71 | -728993.71 | 66185668.5714 | -1.101% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-08-01 |  | 1573817.14 | 0 | 2302810.85 | -2302810.85 | 66185668.5714 | -3.479% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-09-01 |  | 34590.72 | 0 | 2337401.57 | -2337401.57 | 66185668.5714 | -3.532% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-10-01 |  | 877441.09 | 0 | 3214842.66 | -3214842.66 | 66185668.5714 | -4.857% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-11-01 |  | 450155.73 | 0 | 3664998.39 | -3664998.39 | 66185668.5714 | -5.537% |  |  |  | cash out both |  |  | 2018
Fish Market | 2018-12-01 |  | 1451075.87 | 0 | 5116074.26 | -5116074.26 | 66185668.5714 | -7.73% |  |  |  | cash out both |  |  | 2018
Fish Market | 2019-01-01 |  | 7267365.78 | 0 | 12383440.04 | -12383440.04 | 66185668.5714 | -18.71% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-02-01 |  | 4122879.37 | 0 | 16506319.41 | -16506319.41 | 66185668.5714 | -24.94% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-02-11 | 50000000 |  | 50000000 | 16506319.41 | 33493680.59 | 66185668.5714 | 50.61% |  |  | 2019-02-11 | added cash in 3 |  |  | 2019
Fish Market | 2019-03-01 |  | 10376459.73 | 50000000 | 26882779.14 | 23117220.86 | 66185668.5714 | 34.93% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-04-01 |  | 5111401.43 | 50000000 | 31994180.57 | 18005819.43 | 66185668.5714 | 27.21% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-05-01 |  | 2586847.01 | 50000000 | 34581027.58 | 15418972.42 | 66185668.5714 | 23.3% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-06-01 |  | 793853.41 | 50000000 | 35374880.99 | 14625119.01 | 66185668.5714 | 22.1% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-07-01 |  | 513720.15 | 50000000 | 35888601.14 | 14111398.86 | 66185668.5714 | 21.32% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-08-01 |  | 268198.35 | 50000000 | 36156799.49 | 13843200.51 | 66185668.5714 | 20.92% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-09-01 |  | 1222005.98 | 50000000 | 37378805.47 | 12621194.53 | 66185668.5714 | 19.07% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-09-30 | 6101100 |  | 56101100 | 37378805.47 | 18722294.53 | 66185668.5714 | 28.29% |  |  | 2019-09-30 | added cash in 3 |  |  | 2019
Fish Market | 2019-10-01 |  | 986480 | 56101100 | 38365285.47 | 17735814.53 | 66185668.5714 | 26.8% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-11-01 |  | 1078944.54 | 56101100 | 39444230.01 | 16656869.99 | 66185668.5714 | 25.17% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-11-06 | 49997 |  | 56151097 | 39444230.01 | 16706866.99 | 66185668.5714 | 25.24% |  |  | 2019-11-06 | added cash in 3 |  |  | 2019
Fish Market | 2019-11-20 | 1461737 |  | 57612834 | 39444230.01 | 18168603.99 | 66185668.5714 | 27.45% |  |  | 2019-11-20 | added cash in 3 |  |  | 2019
Fish Market | 2019-12-01 |  | 2607532.15 | 57612834 | 42051762.16 | 15561071.84 | 66185668.5714 | 23.51% |  |  |  | cash out both |  |  | 2019
Fish Market | 2019-12-31 | 9151350 |  | 66764184 | 42051762.16 | 24712421.84 | 66185668.5714 | 37.34% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Fish Market | 2020-01-01 |  | 24268.18 | 66764184 | 42076030.34 | 24688153.66 | 66185668.5714 | 37.3% |  |  |  | cash out both |  |  | 2020
Fish Market | 2020-02-01 |  | 772613.7 | 66764184 | 42848644.04 | 23915539.96 | 66185668.5714 | 36.13% |  |  |  | cash out both |  |  | 2020
Fish Market | 2020-03-01 |  | 123315 | 66764184 | 42971959.04 | 23792224.96 | 66185668.5714 | 35.95% |  |  |  | cash out both |  |  | 2020
Fish Market | 2020-06-01 |  | 1949 | 66764184 | 42973908.04 | 23790275.96 | 66185668.5714 | 35.94% |  |  |  | cash out both |  |  | 2020
Fish Market | 2020-07-01 |  | 10000 | 66764184 | 42983908.04 | 23780275.96 | 66185668.5714 | 35.93% |  |  |  | cash out both |  |  | 2020
Fish Market | 2020-08-01 |  | 124246.9 | 66764184 | 43108154.94 | 23656029.06 | 66185668.5714 | 35.74% |  |  |  | cash out both |  |  | 2020
Fish Market | 2020-09-01 |  | 42500 | 66764184 | 43150654.94 | 23613529.06 | 66185668.5714 | 35.68% |  |  |  | cash out both |  |  | 2020
Fish Market | 2020-12-01 |  | 2379.68 | 66764184 | 43153034.62 | 23611149.38 | 66185668.5714 | 35.67% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Fish Market | 2021-01-01 |  | 77359.28 | 66764184 | 43230393.9 | 23533790.1 | 66185668.5714 | 35.56% |  |  |  | cash out both |  |  | 2021
Fish Market | 2021-01-31 | 1715135 |  | 68479319 | 43230393.9 | 25248925.1 | 66185668.5714 | 38.15% |  |  | 2021-01-31 | added cash in 3 |  |  | 2021
Fish Market | 2021-02-01 |  | 309.82 | 68479319 | 43230703.72 | 25248615.28 | 66185668.5714 | 38.15% |  |  |  | cash out both |  |  | 2021
Fish Market | 2021-03-01 |  | 24040.51 | 68479319 | 43254744.23 | 25224574.77 | 66185668.5714 | 38.11% |  |  |  | cash out both |  |  | 2021
1900
Al Jazi Mall | 2018-02-01 |  | 33580 | 0 | 33580 | -33580 | 245977347.1316 | -0.01365% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-04-01 |  | 879590.49 | 0 | 913170.49 | -913170.49 | 245977347.1316 | -0.3712% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-05-01 |  | 6418153.54 | 0 | 7331324.03 | -7331324.03 | 245977347.1316 | -2.98% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-05-08 | 53125000 |  | 53125000 | 7331324.03 | 45793675.97 | 245977347.1316 | 18.62% |  |  | 2018-05-08 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-06-01 |  | 6945643.61 | 53125000 | 14276967.64 | 38848032.36 | 245977347.1316 | 15.79% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-06-10 | 2199495 |  | 55324495 | 14276967.64 | 41047527.36 | 245977347.1316 | 16.69% |  |  | 2018-06-10 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-06-28 | 2330066 |  | 57654561 | 14276967.64 | 43377593.36 | 245977347.1316 | 17.63% |  |  | 2018-06-28 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-06-30 | 2992814 |  | 60647375 | 14276967.64 | 46370407.36 | 245977347.1316 | 18.85% |  |  | 2018-06-30 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-06-30 | 4840000 |  | 65487375 | 14276967.64 | 51210407.36 | 245977347.1316 | 20.82% |  |  | 2018-06-30 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-07-01 |  | 8005177.89 | 65487375 | 22282145.53 | 43205229.47 | 245977347.1316 | 17.56% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-07-24 | 3357056.9 |  | 68844431.9 | 22282145.53 | 46562286.37 | 245977347.1316 | 18.93% |  |  | 2018-07-24 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-07-31 | 2174491 |  | 71018922.9 | 22282145.53 | 48736777.37 | 245977347.1316 | 19.81% |  |  | 2018-07-31 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-08-01 |  | 9410409.92 | 71018922.9 | 31692555.45 | 39326367.45 | 245977347.1316 | 15.99% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-08-14 | 3867947.36 |  | 74886870.26 | 31692555.45 | 43194314.81 | 245977347.1316 | 17.56% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-08-19 | 1750000 |  | 76636870.26 | 31692555.45 | 44944314.81 | 245977347.1316 | 18.27% |  |  | 2018-08-19 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-08-31 | 1410678.5 |  | 78047548.76 | 31692555.45 | 46354993.31 | 245977347.1316 | 18.85% |  |  | 2018-08-31 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-08-31 | 2289155 |  | 80336703.76 | 31692555.45 | 48644148.31 | 245977347.1316 | 19.78% |  |  | 2018-08-31 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-09-01 |  | 9725084.65 | 80336703.76 | 41417640.1 | 38919063.66 | 245977347.1316 | 15.82% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-09-30 | 1282600 |  | 81619303.76 | 41417640.1 | 40201663.66 | 245977347.1316 | 16.34% |  |  | 2018-09-30 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-09-30 | 1383592 |  | 83002895.76 | 41417640.1 | 41585255.66 | 245977347.1316 | 16.91% |  |  | 2018-09-30 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-09-30 | 3149388 |  | 86152283.76 | 41417640.1 | 44734643.66 | 245977347.1316 | 18.19% |  |  | 2018-09-30 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-09-30 | 1000000 |  | 87152283.76 | 41417640.1 | 45734643.66 | 245977347.1316 | 18.59% |  |  | 2018-09-30 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-10-01 |  | 4957645.68 | 87152283.76 | 46375285.78 | 40776997.98 | 245977347.1316 | 16.58% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-10-18 | 4138160 |  | 91290443.76 | 46375285.78 | 44915157.98 | 245977347.1316 | 18.26% |  |  | 2018-10-18 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-10-29 | 2563385 |  | 93853828.76 | 46375285.78 | 47478542.98 | 245977347.1316 | 19.3% |  |  | 2018-10-29 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-11-01 |  | 7625002.14 | 93853828.76 | 54000287.92 | 39853540.84 | 245977347.1316 | 16.2% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-11-13 | 6905844.19 |  | 100759672.95 | 54000287.92 | 46759385.03 | 245977347.1316 | 19.01% |  |  | 2018-11-13 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-11-26 | 3367551 |  | 104127223.95 | 54000287.92 | 50126936.03 | 245977347.1316 | 20.38% |  |  | 2018-11-26 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-12-01 |  | 5781447.47 | 104127223.95 | 59781735.39 | 44345488.56 | 245977347.1316 | 18.03% |  |  |  | cash out both |  |  | 2018
Al Jazi Mall | 2018-12-10 | 1762571.78 |  | 105889795.73 | 59781735.39 | 46108060.34 | 245977347.1316 | 18.74% |  |  | 2018-12-10 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-12-19 | 4078063 |  | 109967858.73 | 59781735.39 | 50186123.34 | 245977347.1316 | 20.4% |  |  | 2018-12-19 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2018-12-31 | 2048530 |  | 112016388.73 | 59781735.39 | 52234653.34 | 245977347.1316 | 21.24% |  |  | 2018-12-31 | added cash in 3 |  |  | 2018
Al Jazi Mall | 2019-01-01 |  | 2532186.59 | 112016388.73 | 62313921.98 | 49702466.75 | 245977347.1316 | 20.21% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-01-03 | 2302251 |  | 114318639.73 | 62313921.98 | 52004717.75 | 245977347.1316 | 21.14% |  |  | 2019-01-03 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-01-17 | 3838772.36 |  | 118157412.09 | 62313921.98 | 55843490.11 | 245977347.1316 | 22.7% |  |  | 2019-01-17 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-01-31 | 2812282 |  | 120969694.09 | 62313921.98 | 58655772.11 | 245977347.1316 | 23.85% |  |  | 2019-01-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-02-01 |  | 4908781.94 | 120969694.09 | 67222703.92 | 53746990.17 | 245977347.1316 | 21.85% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-02-14 | 922154 |  | 121891848.09 | 67222703.92 | 54669144.17 | 245977347.1316 | 22.23% |  |  | 2019-02-14 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-02-27 | 2736294 |  | 124628142.09 | 67222703.92 | 57405438.17 | 245977347.1316 | 23.34% |  |  | 2019-02-27 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-03-01 |  | 3938080.58 | 124628142.09 | 71160784.5 | 53467357.59 | 245977347.1316 | 21.74% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-03-18 | 2994292.79 |  | 127622434.88 | 71160784.5 | 56461650.38 | 245977347.1316 | 22.95% |  |  | 2019-03-18 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-03-31 | 3479839 |  | 131102273.88 | 71160784.5 | 59941489.38 | 245977347.1316 | 24.37% |  |  | 2019-03-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-04-01 |  | 4935089.14 | 131102273.88 | 76095873.64 | 55006400.24 | 245977347.1316 | 22.36% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-04-08 | 14666580.12 |  | 145768854 | 76095873.64 | 69672980.36 | 245977347.1316 | 28.32% |  |  | 2019-04-08 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-05-01 |  | 3541837.77 | 145768854 | 79637711.41 | 66131142.59 | 245977347.1316 | 26.89% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-05-06 | 1629015.64 |  | 147397869.64 | 79637711.41 | 67760158.23 | 245977347.1316 | 27.55% |  |  | 2019-05-06 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-05-06 | 90608.89 |  | 147488478.53 | 79637711.41 | 67850767.12 | 245977347.1316 | 27.58% |  |  | 2019-05-06 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-05-30 | 3484206.5 |  | 150972685.03 | 79637711.41 | 71334973.62 | 245977347.1316 | 29% |  |  | 2019-05-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-05-30 | 1122638 |  | 152095323.03 | 79637711.41 | 72457611.62 | 245977347.1316 | 29.46% |  |  | 2019-05-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-05-31 | 11566832.04 |  | 163662155.07 | 79637711.41 | 84024443.66 | 245977347.1316 | 34.16% |  |  | 2019-05-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-01 |  | 2122276.3 | 163662155.07 | 81759987.71 | 81902167.36 | 245977347.1316 | 33.3% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-06-03 | 2107757 |  | 165769912.07 | 81759987.71 | 84009924.36 | 245977347.1316 | 34.15% |  |  | 2019-06-03 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-18 | 1686320.29 |  | 167456232.36 | 81759987.71 | 85696244.65 | 245977347.1316 | 34.84% |  |  | 2019-06-18 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-25 | 1270745.7 |  | 168726978.06 | 81759987.71 | 86966990.35 | 245977347.1316 | 35.36% |  |  | 2019-06-25 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-25 | 2113359.39 |  | 170840337.45 | 81759987.71 | 89080349.74 | 245977347.1316 | 36.21% |  |  | 2019-06-25 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-25 | 1442864.5 |  | 172283201.95 | 81759987.71 | 90523214.24 | 245977347.1316 | 36.8% |  |  | 2019-06-25 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-25 | 2590006.56 |  | 174873208.51 | 81759987.71 | 93113220.8 | 245977347.1316 | 37.85% |  |  | 2019-06-25 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-27 | 120989.08 |  | 174994197.59 | 81759987.71 | 93234209.88 | 245977347.1316 | 37.9% |  |  | 2019-06-27 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-30 | 4173169 |  | 179167366.59 | 81759987.71 | 97407378.88 | 245977347.1316 | 39.6% |  |  | 2019-06-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-06-30 | 2729837 |  | 181897203.59 | 81759987.71 | 100137215.88 | 245977347.1316 | 40.71% |  |  | 2019-06-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-07-01 |  | 2257979.27 | 181897203.59 | 84017966.98 | 97879236.61 | 245977347.1316 | 39.79% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-07-31 | 1168479.31 |  | 183065682.9 | 84017966.98 | 99047715.92 | 245977347.1316 | 40.27% |  |  | 2019-07-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-07-31 | 1971074.61 |  | 185036757.51 | 84017966.98 | 101018790.53 | 245977347.1316 | 41.07% |  |  | 2019-07-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-07-31 | 2935343.72 |  | 187972101.23 | 84017966.98 | 103954134.25 | 245977347.1316 | 42.26% |  |  | 2019-07-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-08-01 |  | 3202833.79 | 187972101.23 | 87220800.77 | 100751300.46 | 245977347.1316 | 40.96% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-08-07 | 2748544.1 |  | 190720645.33 | 87220800.77 | 103499844.56 | 245977347.1316 | 42.08% |  |  | 2019-08-07 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-08-31 | 711986.51 |  | 191432631.84 | 87220800.77 | 104211831.07 | 245977347.1316 | 42.37% |  |  | 2019-08-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-08-31 | 2165251.23 |  | 193597883.07 | 87220800.77 | 106377082.3 | 245977347.1316 | 43.25% |  |  | 2019-08-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-09-01 |  | 2109688.72 | 193597883.07 | 89330489.49 | 104267393.58 | 245977347.1316 | 42.39% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-09-03 | 360179.68 |  | 193958062.75 | 89330489.49 | 104627573.26 | 245977347.1316 | 42.54% |  |  | 2019-09-03 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-09-18 | 2000000 |  | 195958062.75 | 89330489.49 | 106627573.26 | 245977347.1316 | 43.35% |  |  | 2019-09-18 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-09-30 | 1435202.12 |  | 197393264.87 | 89330489.49 | 108062775.38 | 245977347.1316 | 43.93% |  |  | 2019-09-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-09-30 | 6670246 |  | 204063510.87 | 89330489.49 | 114733021.38 | 245977347.1316 | 46.64% |  |  | 2019-09-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-10-01 |  | 4595501.66 | 204063510.87 | 93925991.15 | 110137519.72 | 245977347.1316 | 44.78% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-10-03 | 370581.69 |  | 204434092.56 | 93925991.15 | 110508101.41 | 245977347.1316 | 44.93% |  |  | 2019-10-03 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-10-07 | 1100493.11 |  | 205534585.67 | 93925991.15 | 111608594.52 | 245977347.1316 | 45.37% |  |  | 2019-10-07 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-10-31 | 1785234 |  | 207319819.67 | 93925991.15 | 113393828.52 | 245977347.1316 | 46.1% |  |  | 2019-10-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-10-31 | 1498257.44 |  | 208818077.11 | 93925991.15 | 114892085.96 | 245977347.1316 | 46.71% |  |  | 2019-10-31 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-11-01 |  | 2660378.13 | 208818077.11 | 96586369.28 | 112231707.83 | 245977347.1316 | 45.63% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2019-11-24 | 371543.5 |  | 209189620.61 | 96586369.28 | 112603251.33 | 245977347.1316 | 45.78% |  |  | 2019-11-24 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-11-24 | 858100 |  | 210047720.61 | 96586369.28 | 113461351.33 | 245977347.1316 | 46.13% |  |  | 2019-11-24 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-11-30 | 5639672.46 |  | 215687393.07 | 96586369.28 | 119101023.79 | 245977347.1316 | 48.42% |  |  | 2019-11-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-11-30 | 5259870 |  | 220947263.07 | 96586369.28 | 124360893.79 | 245977347.1316 | 50.56% |  |  | 2019-11-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-11-30 | 700859.03 |  | 221648122.1 | 96586369.28 | 125061752.82 | 245977347.1316 | 50.84% |  |  | 2019-11-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-11-30 | 3925240 |  | 225573362.1 | 96586369.28 | 128986992.82 | 245977347.1316 | 52.44% |  |  | 2019-11-30 | added cash in 3 |  |  | 2019
Al Jazi Mall | 2019-12-01 |  | 9420238.52 | 225573362.1 | 106006607.8 | 119566754.3 | 245977347.1316 | 48.61% |  |  |  | cash out both |  |  | 2019
Al Jazi Mall | 2020-01-01 |  | 3242358.09 | 225573362.1 | 109248965.89 | 116324396.21 | 245977347.1316 | 47.29% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-02-01 |  | 3812548.83 | 225573362.1 | 113061514.72 | 112511847.38 | 245977347.1316 | 45.74% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-03-01 |  | 1515151.74 | 225573362.1 | 114576666.46 | 110996695.64 | 245977347.1316 | 45.12% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-04-01 |  | 518325.25 | 225573362.1 | 115094991.71 | 110478370.39 | 245977347.1316 | 44.91% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-05-01 |  | 347802.87 | 225573362.1 | 115442794.58 | 110130567.52 | 245977347.1316 | 44.77% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-06-01 |  | 475479.26 | 225573362.1 | 115918273.84 | 109655088.26 | 245977347.1316 | 44.58% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-06-10 | 4562568.48 |  | 230135930.58 | 115918273.84 | 114217656.74 | 245977347.1316 | 46.43% |  |  | 2020-06-10 | added cash in 3 |  |  | 2020
Al Jazi Mall | 2020-06-30 | 6686539.11 |  | 236822469.69 | 115918273.84 | 120904195.85 | 245977347.1316 | 49.15% |  |  | 2020-06-30 | added cash in 3 |  |  | 2020
Al Jazi Mall | 2020-07-01 |  | 256063.08 | 236822469.69 | 116174336.92 | 120648132.77 | 245977347.1316 | 49.05% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-08-01 |  | 674445.56 | 236822469.69 | 116848782.48 | 119973687.21 | 245977347.1316 | 48.77% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-09-01 |  | 1989199.62 | 236822469.69 | 118837982.1 | 117984487.59 | 245977347.1316 | 47.97% |  |  |  | cash out both |  |  | 2020
Al Jazi Mall | 2020-10-01 |  | 123662.95 | 236822469.69 | 118961645.05 | 117860824.64 | 245977347.1316 | 47.92% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Al Jazi Mall | 2020-11-01 |  | 86833.84 | 236822469.69 | 119048478.89 | 117773990.8 | 245977347.1316 | 47.88% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Al Jazi Mall | 2020-12-01 |  | 32396.36 | 236822469.69 | 119080875.25 | 117741594.44 | 245977347.1316 | 47.87% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Al Jazi Mall | 2021-01-01 |  | 40105.3 | 236822469.69 | 119120980.55 | 117701489.14 | 245977347.1316 | 47.85% |  |  |  | cash out both |  |  | 2021
Al Jazi Mall | 2021-03-01 |  | 7548.34 | 236822469.69 | 119128528.89 | 117693940.8 | 245977347.1316 | 47.85% |  |  |  | cash out both |  |  | 2021
1900
Benban Aswan Alcazars Solar Park | 2018-05-01 |  | 117482.44 | 0 | 117482.44 | -117482.44 | 212005784 | -0.05541% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-06-01 |  | 1459920.17 | 0 | 1577402.61 | -1577402.61 | 212005784 | -0.744% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-07-01 |  | 3284170.65 | 0 | 4861573.26 | -4861573.26 | 212005784 | -2.293% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-08-01 |  | 6748136.25 | 0 | 11609709.51 | -11609709.51 | 212005784 | -5.476% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-08-14 | 18261008.6 |  | 18261008.6 | 11609709.51 | 6651299.09 | 212005784 | 3.137% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-08-14 | 6416029.96 |  | 24677038.56 | 11609709.51 | 13067329.05 | 212005784 | 6.164% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-09-01 |  | 6263015.82 | 24677038.56 | 17872725.33 | 6804313.23 | 212005784 | 3.209% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-09-17 | 12749008.91 |  | 37426047.47 | 17872725.33 | 19553322.14 | 212005784 | 9.223% |  |  | 2018-09-17 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-09-17 | 9093164.7 |  | 46519212.17 | 17872725.33 | 28646486.84 | 212005784 | 13.51% |  |  | 2018-09-17 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-10-01 |  | 19897186.42 | 46519212.17 | 37769911.75 | 8749300.42 | 212005784 | 4.127% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-10-08 | 9732619.19 |  | 56251831.36 | 37769911.75 | 18481919.61 | 212005784 | 8.718% |  |  | 2018-10-08 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-10-08 | 2640269.25 |  | 58892100.61 | 37769911.75 | 21122188.86 | 212005784 | 9.963% |  |  | 2018-10-08 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-10-09 | 7937543.77 |  | 66829644.38 | 37769911.75 | 29059732.63 | 212005784 | 13.71% |  |  | 2018-10-09 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-10-09 | 5273732.55 |  | 72103376.93 | 37769911.75 | 34333465.18 | 212005784 | 16.19% |  |  | 2018-10-09 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-11-01 |  | 11869356.24 | 72103376.93 | 49639267.99 | 22464108.94 | 212005784 | 10.6% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-12-01 |  | 15040207.78 | 72103376.93 | 64679475.77 | 7423901.16 | 212005784 | 3.502% |  |  |  | cash out both |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-12-02 | 6171851.63 |  | 78275228.56 | 64679475.77 | 13595752.79 | 212005784 | 6.413% |  |  | 2018-12-02 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-12-02 | 5516009.9 |  | 83791238.46 | 64679475.77 | 19111762.69 | 212005784 | 9.015% |  |  | 2018-12-02 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-12-02 | 16984620.78 |  | 100775859.24 | 64679475.77 | 36096383.47 | 212005784 | 17.03% |  |  | 2018-12-02 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-12-02 | 8438577.84 |  | 109214437.08 | 64679475.77 | 44534961.31 | 212005784 | 21.01% |  |  | 2018-12-02 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-12-04 | 329437 |  | 109543874.08 | 64679475.77 | 44864398.31 | 212005784 | 21.16% |  |  | 2018-12-04 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2018-12-18 | 6884560 |  | 116428434.08 | 64679475.77 | 51748958.31 | 212005784 | 24.41% |  |  | 2018-12-18 | added cash in 3 |  |  | 2018
Benban Aswan Alcazars Solar Park | 2019-01-01 |  | 18705269.64 | 116428434.08 | 83384745.41 | 33043688.67 | 212005784 | 15.59% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-01-27 | 15158175.01 |  | 131586609.09 | 83384745.41 | 48201863.68 | 212005784 | 22.74% |  |  | 2019-01-27 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-01-27 | 3936233.47 |  | 135522842.56 | 83384745.41 | 52138097.15 | 212005784 | 24.59% |  |  | 2019-01-27 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-02-01 |  | 6266630.35 | 135522842.56 | 89651375.76 | 45871466.8 | 212005784 | 21.64% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-02-07 | 25761157.35 |  | 161283999.91 | 89651375.76 | 71632624.15 | 212005784 | 33.79% |  |  | 2019-02-07 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-02-27 | 1352108.84 |  | 162636108.75 | 89651375.76 | 72984732.99 | 212005784 | 34.43% |  |  | 2019-02-27 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-03-01 |  | 13906045.82 | 162636108.75 | 103557421.58 | 59078687.17 | 212005784 | 27.87% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-04-01 |  | 5890904.4 | 162636108.75 | 109448325.98 | 53187782.77 | 212005784 | 25.09% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-04-04 | 400103.44 |  | 163036212.19 | 109448325.98 | 53587886.21 | 212005784 | 25.28% |  |  | 2019-04-04 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-04-16 | 752335.75 |  | 163788547.94 | 109448325.98 | 54340221.96 | 212005784 | 25.63% |  |  | 2019-04-16 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-04-22 | 715835.27 |  | 164504383.21 | 109448325.98 | 55056057.23 | 212005784 | 25.97% |  |  | 2019-04-22 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-05-01 |  | 7794652.5 | 164504383.21 | 117242978.48 | 47261404.73 | 212005784 | 22.29% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-05-05 | 8628 |  | 164513011.21 | 117242978.48 | 47270032.73 | 212005784 | 22.3% |  |  | 2019-05-05 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-05-09 | 693046.48 |  | 165206057.69 | 117242978.48 | 47963079.21 | 212005784 | 22.62% |  |  | 2019-05-09 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-05-14 | 20418.44 |  | 165226476.13 | 117242978.48 | 47983497.65 | 212005784 | 22.63% |  |  | 2019-05-14 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-06-01 |  | 5805417.25 | 165226476.13 | 123048395.73 | 42178080.4 | 212005784 | 19.89% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-06-03 | 39562.1 |  | 165266038.23 | 123048395.73 | 42217642.5 | 212005784 | 19.91% |  |  | 2019-06-03 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-06-03 | 97818.28 |  | 165363856.51 | 123048395.73 | 42315460.78 | 212005784 | 19.96% |  |  | 2019-06-03 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-06-26 | 73946.25 |  | 165437802.76 | 123048395.73 | 42389407.03 | 212005784 | 19.99% |  |  | 2019-06-26 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-06-26 | 69205.41 |  | 165507008.17 | 123048395.73 | 42458612.44 | 212005784 | 20.03% |  |  | 2019-06-26 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-07-01 |  | 1924376.55 | 165507008.17 | 124972772.28 | 40534235.89 | 212005784 | 19.12% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-07-17 | 2188.44 |  | 165509196.61 | 124972772.28 | 40536424.33 | 212005784 | 19.12% |  |  | 2019-07-17 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-07-25 | 14673700.68 |  | 180182897.29 | 124972772.28 | 55210125.01 | 212005784 | 26.04% |  |  | 2019-07-25 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-07-31 | 70052.36 |  | 180252949.65 | 124972772.28 | 55280177.37 | 212005784 | 26.07% |  |  | 2019-07-31 | added cash in 3 |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-08-01 |  | 6633584.34 | 180252949.65 | 131606356.62 | 48646593.03 | 212005784 | 22.95% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-09-01 |  | 314728.04 | 180252949.65 | 131921084.66 | 48331864.99 | 212005784 | 22.8% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-10-01 |  | 4656703.09 | 180252949.65 | 136577787.75 | 43675161.9 | 212005784 | 20.6% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-11-01 |  | 872160.22 | 180252949.65 | 137449947.97 | 42803001.68 | 212005784 | 20.19% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2019-12-01 |  | 58599013.17 | 180252949.65 | 196048961.14 | -15796011.49 | 212005784 | -7.451% |  |  |  | cash out both |  |  | 2019
Benban Aswan Alcazars Solar Park | 2020-01-01 |  | 1450432.48 | 180252949.65 | 197499393.62 | -17246443.97 | 212005784 | -8.135% |  |  |  | cash out both |  |  | 2020
Benban Aswan Alcazars Solar Park | 2020-02-01 |  | 154280.24 | 180252949.65 | 197653673.86 | -17400724.21 | 212005784 | -8.208% |  |  |  | cash out both |  |  | 2020
Benban Aswan Alcazars Solar Park | 2020-03-01 |  | 87268.19 | 180252949.65 | 197740942.05 | -17487992.4 | 212005784 | -8.249% |  |  |  | cash out both |  |  | 2020
Benban Aswan Alcazars Solar Park | 2020-04-01 |  | 11512.8 | 180252949.65 | 197752454.85 | -17499505.2 | 212005784 | -8.254% |  |  |  | cash out both |  |  | 2020
Benban Aswan Alcazars Solar Park | 2020-06-01 |  | 45780.04 | 180252949.65 | 197798234.89 | -17545285.24 | 212005784 | -8.276% |  |  |  | cash out both |  |  | 2020
Benban Aswan Alcazars Solar Park | 2020-07-01 |  | 99415 | 180252949.65 | 197897649.89 | -17644700.24 | 212005784 | -8.323% |  |  |  | cash out both |  |  | 2020
Benban Aswan Alcazars Solar Park | 2020-09-01 |  | 44141.23 | 180252949.65 | 197941791.12 | -17688841.47 | 212005784 | -8.344% |  |  |  | cash out both |  |  | 2020
Benban Aswan Alcazars Solar Park | 2020-12-01 |  | 462361.7 | 180252949.65 | 198404152.82 | -18151203.17 | 212005784 | -8.562% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Benban Aswan Alcazars Solar Park | 2021-01-01 |  | 166000 | 180252949.65 | 198570152.82 | -18317203.17 | 212005784 | -8.64% |  |  |  | cash out both |  |  | 2021
Benban Aswan Alcazars Solar Park | 2021-02-01 |  | 547231.36 | 180252949.65 | 199117384.18 | -18864434.53 | 212005784 | -8.898% |  |  |  | cash out both |  |  | 2021
Benban Aswan Alcazars Solar Park | 2021-03-01 |  | 120492.22 | 180252949.65 | 199237876.4 | -18984926.75 | 212005784 | -8.955% |  |  |  | cash out both |  |  | 2021
1900
El Alameen Roads Earth Works | 2018-07-01 |  | 94383 | 0 | 94383 | -94383 | 54192857 | -0.1742% |  |  |  | cash out both |  |  | 2018
El Alameen Roads Earth Works | 2018-08-01 |  | 1240057.1 | 0 | 1334440.1 | -1334440.1 | 54192857 | -2.462% |  |  |  | cash out both |  |  | 2018
El Alameen Roads Earth Works | 2018-09-01 |  | 1450613.86 | 0 | 2785053.96 | -2785053.96 | 54192857 | -5.139% |  |  |  | cash out both |  |  | 2018
El Alameen Roads Earth Works | 2018-10-01 |  | 2241343.16 | 0 | 5026397.12 | -5026397.12 | 54192857 | -9.275% |  |  |  | cash out both |  |  | 2018
El Alameen Roads Earth Works | 2018-11-01 |  | 1768688.5 | 0 | 6795085.62 | -6795085.62 | 54192857 | -12.54% |  |  |  | cash out both |  |  | 2018
El Alameen Roads Earth Works | 2018-12-01 |  | 1432890.8 | 0 | 8227976.42 | -8227976.42 | 54192857 | -15.18% |  |  |  | cash out both |  |  | 2018
El Alameen Roads Earth Works | 2019-01-01 |  | 3278942.4 | 0 | 11506918.82 | -11506918.82 | 54192857 | -21.23% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-02-01 |  | 860413.09 | 0 | 12367331.91 | -12367331.91 | 54192857 | -22.82% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-03-01 |  | 2039662.53 | 0 | 14406994.44 | -14406994.44 | 54192857 | -26.58% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-04-01 |  | 2261071.33 | 0 | 16668065.77 | -16668065.77 | 54192857 | -30.76% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-05-01 |  | 1831122.24 | 0 | 18499188.01 | -18499188.01 | 54192857 | -34.14% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-06-01 |  | 1600554.87 | 0 | 20099742.88 | -20099742.88 | 54192857 | -37.09% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-07-01 |  | 2412249.46 | 0 | 22511992.34 | -22511992.34 | 54192857 | -41.54% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-07-15 | 7626342.25 |  | 7626342.25 | 22511992.34 | -14885650.09 | 54192857 | -27.47% |  |  | 2019-07-15 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-07-25 | 7626341.25 |  | 15252683.5 | 22511992.34 | -7259308.84 | 54192857 | -13.4% |  |  | 2019-07-25 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-08-01 |  | 1521819.27 | 15252683.5 | 24033811.61 | -8781128.11 | 54192857 | -16.2% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-09-01 |  | 2275723.1 | 15252683.5 | 26309534.71 | -11056851.21 | 54192857 | -20.4% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-09-22 | 1761540 |  | 17014223.5 | 26309534.71 | -9295311.21 | 54192857 | -17.15% |  |  | 2019-09-22 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-10-01 |  | 2081868.68 | 17014223.5 | 28391403.39 | -11377179.89 | 54192857 | -20.99% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-10-03 | 2033601.5 |  | 19047825 | 28391403.39 | -9343578.39 | 54192857 | -17.24% |  |  | 2019-10-03 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-10-07 | 2033601.5 |  | 21081426.5 | 28391403.39 | -7309976.89 | 54192857 | -13.49% |  |  | 2019-10-07 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-10-14 | 3562679.5 |  | 22610504.5 | 28391403.39 | -5780898.89 | 54192857 | -10.67% |  |  | 2019-10-14 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-10-14 | 3562679.5 |  | 24644106 | 28391403.39 | -3747297.39 | 54192857 | -6.915% |  |  | 2019-10-14 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-11-01 |  | 2184029.04 | 24644106 | 30575432.43 | -5931326.43 | 54192857 | -10.94% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2019-11-18 | 8403859 |  | 33047965 | 30575432.43 | 2472532.57 | 54192857 | 4.562% |  |  | 2019-11-18 | added cash in 3 |  |  | 2019
El Alameen Roads Earth Works | 2019-12-01 |  | 5009859.74 | 33047965 | 35585292.17 | -2537327.17 | 54192857 | -4.682% |  |  |  | cash out both |  |  | 2019
El Alameen Roads Earth Works | 2020-01-01 |  | 1760866.49 | 33047965 | 37346158.66 | -4298193.66 | 54192857 | -7.931% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-02-01 |  | 1394896.15 | 33047965 | 38741054.81 | -5693089.81 | 54192857 | -10.51% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-03-01 |  | 1058790.85 | 33047965 | 39799845.66 | -6751880.66 | 54192857 | -12.46% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-04-01 |  | 59128.35 | 33047965 | 39858974.01 | -6811009.01 | 54192857 | -12.57% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-04-30 | 2098992 |  | 35146957 | 39858974.01 | -4712017.01 | 54192857 | -8.695% |  |  | 2020-04-30 | added cash in 3 |  |  | 2020
El Alameen Roads Earth Works | 2020-04-30 | 2098992 |  | 37245949 | 39858974.01 | -2613025.01 | 54192857 | -4.822% |  |  | 2020-04-30 | added cash in 3 |  |  | 2020
El Alameen Roads Earth Works | 2020-04-30 | 2098992 |  | 39344941 | 39858974.01 | -514033.01 | 54192857 | -0.9485% |  |  | 2020-04-30 | added cash in 3 |  |  | 2020
El Alameen Roads Earth Works | 2020-05-01 |  | 703925.82 | 39344941 | 40562899.83 | -1217958.83 | 54192857 | -2.247% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-06-01 | 1419727 | 479450.07 | 40764668 | 41042349.9 | -277681.9 | 54192857 | -0.5124% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-07-01 |  | 390250.99 | 40764668 | 41432600.89 | -667932.89 | 54192857 | -1.233% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-08-01 |  | 650531.98 | 40764668 | 42083132.87 | -1318464.87 | 54192857 | -2.433% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-08-26 | 5280204 |  | 46044872 | 42083132.87 | 3961739.13 | 54192857 | 7.31% |  |  | 2020-08-26 | added cash in 3 |  |  | 2020
El Alameen Roads Earth Works | 2020-09-01 |  | 25140.9 | 46044872 | 42108273.77 | 3936598.23 | 54192857 | 7.264% |  |  |  | cash out both |  |  | 2020
El Alameen Roads Earth Works | 2020-10-01 |  | 1761.98 | 46044872 | 42110035.75 | 3934836.25 | 54192857 | 7.261% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
El Alameen Roads Earth Works | 2020-11-01 |  | 19340 | 46044872 | 42129375.75 | 3915496.25 | 54192857 | 7.225% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
El Alameen Roads Earth Works | 2021-01-01 |  | 1761.98 | 46044872 | 42131137.73 | 3913734.27 | 54192857 | 7.222% |  |  |  | cash out both |  |  | 2021
El Alameen Roads Earth Works | 2021-03-01 |  | 81 | 46044872 | 42131218.73 | 3913653.27 | 54192857 | 7.222% |  |  |  | cash out both |  |  | 2021
1900
El Sewedy Univeristy | 2020-10-01 |  | 536658.84 | 0 | 536658.84 | -536658.84 | #N/A | #N/A |  |  | 2020-10-01 | cashout both updated |  |  | 2020
El Sewedy Univeristy | 2020-11-01 |  | 381529 | 0 | 918187.84 | -918187.84 | #N/A | #N/A |  |  | 2020-11-01 | cashout both updated |  |  | 2020
El Sewedy Univeristy | 2020-12-01 |  | 1152793.29 | 0 | 2070981.13 | -2070981.13 | #N/A | #N/A |  |  | 2020-12-01 | cashout both updated |  |  | 2020
El Sewedy Univeristy | 2021-01-01 |  | 825348.65 | 0 | 2896329.78 | -2896329.78 | #N/A | #N/A |  |  |  | cash out both |  |  | 2021
El Sewedy Univeristy | 2021-02-01 |  | 1786324.61 | 0 | 4682654.39 | -4682654.39 | #N/A | #N/A |  |  |  | cash out both |  |  | 2021
El Sewedy Univeristy | 2021-03-01 |  | 953751.25 | 0 | 5636405.64 | -5636405.64 | #N/A | #N/A |  |  |  | cash out both |  |  | 2021
1900
El Sokhna Tunnel L&L | 2018-07-01 |  | 67012.74 | 0 | 67012.74 | -67012.74 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel L&L | 2018-08-01 |  | 53660.37 | 0 | 120673.11 | -120673.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel L&L | 2018-09-01 |  | 2597 | 0 | 123270.11 | -123270.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel L&L | 2018-10-01 |  | 750 | 0 | 124020.11 | -124020.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel L&L | 2019-01-01 |  | 1231.71 | 0 | 125251.82 | -125251.82 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel L&L | 2019-02-01 |  | 12475.93 | 0 | 137727.75 | -137727.75 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel L&L | 2019-03-01 |  | 59250 | 0 | 196977.75 | -196977.75 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel L&L | 2019-04-01 |  | 79215 | 0 | 276192.75 | -276192.75 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel L&L | 2019-05-01 |  | 3955 | 0 | 280147.75 | -280147.75 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel L&L | 2019-09-01 |  | 1116.71 | 0 | 281264.46 | -281264.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel L&L | 2019-11-01 |  | 1116.71 | 0 | 282381.17 | -282381.17 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel L&L | 2020-02-01 |  | 4504.49 | 0 | 286885.66 | -286885.66 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
El Sokhna Tunnel L&L | 2020-05-01 |  | 4504.49 | 0 | 291390.15 | -291390.15 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
El Sokhna Tunnel L&L | 2020-06-01 |  | 54918.9 | 0 | 346309.05 | -346309.05 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
El Sokhna Tunnel L&L | 2020-07-01 |  | 1116 | 0 | 347425.05 | -347425.05 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
El Sokhna Tunnel L&L | 2020-08-01 |  | 4504.49 | 0 | 351929.54 | -351929.54 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
El Sokhna Tunnel L&L | 2021-01-31 | 454415 |  | 454415 | 351929.54 | 102485.46 | 0 | #DIV/0! |  |  | 2021-01-31 | added cash in 3 |  |  | 2021
1900
R05 Residential District Z1 & Z2 | 2018-04-01 |  | 39000 | 0 | 39000 | -39000 | 3200000000 | -0.001219% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-05-01 |  | 57973.5 | 0 | 96973.5 | -96973.5 | 3200000000 | -0.00303% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-06-01 |  | 329979.13 | 0 | 426952.63 | -426952.63 | 3200000000 | -0.01334% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-07-01 |  | 4166373.78 | 0 | 4593326.41 | -4593326.41 | 3200000000 | -0.1435% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-08-01 |  | 12019093.58 | 0 | 16612419.99 | -16612419.99 | 3200000000 | -0.5191% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-09-01 |  | 1245853.3 | 0 | 17858273.29 | -17858273.29 | 3200000000 | -0.5581% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-09-01 |  | 12128445.32 | 0 | 29986718.61 | -29986718.61 | 3200000000 | -0.9371% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-09-17 | 100000000 |  | 100000000 | 29986718.61 | 70013281.39 | 3200000000 | 2.188% |  |  | 2018-09-17 | added cash in 3 |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-10-01 |  | 19848381.98 | 100000000 | 49835100.59 | 50164899.41 | 3200000000 | 1.568% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-10-01 |  | 21276033.88 | 100000000 | 71111134.47 | 28888865.53 | 3200000000 | 0.9028% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-10-01 |  | 56177712.56 | 100000000 | 127288847.03 | -27288847.03 | 3200000000 | -0.8528% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-11-01 |  | 385483.16 | 100000000 | 127674330.19 | -27674330.19 | 3200000000 | -0.8648% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-11-01 |  | 3504206.46 | 100000000 | 131178536.65 | -31178536.65 | 3200000000 | -0.9743% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-11-01 |  | 1144968.94 | 100000000 | 132323505.59 | -32323505.59 | 3200000000 | -1.01% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-11-01 |  | 11230610.53 | 100000000 | 143554116.12 | -43554116.12 | 3200000000 | -1.361% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-11-25 | 13792500 |  | 113792500 | 143554116.12 | -29761616.12 | 3200000000 | -0.9301% |  |  | 2018-11-25 | added cash in 3 |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-12-01 |  | 2940906.33 | 113792500 | 146495022.45 | -32702522.45 | 3200000000 | -1.022% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-12-01 |  | 13916772.42 | 113792500 | 160411794.87 | -46619294.87 | 3200000000 | -1.457% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-12-01 |  | 728617.34 | 113792500 | 161140412.21 | -47347912.21 | 3200000000 | -1.48% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-12-01 |  | 10436027.42 | 113792500 | 171576439.63 | -57783939.63 | 3200000000 | -1.806% |  |  |  | cash out both |  |  | 2018
R05 Residential District Z1 & Z2 | 2018-12-31 | 30000000 |  | 143792500 | 171576439.63 | -27783939.63 | 3200000000 | -0.8682% |  |  | 2018-12-31 | added cash in 3 |  |  | 2018
R05 Residential District Z1 & Z2 | 2019-01-01 |  | 6965696.96 | 143792500 | 178542136.59 | -34749636.59 | 3200000000 | -1.086% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-01-01 |  | 30914031.95 | 143792500 | 209456168.54 | -65663668.54 | 3200000000 | -2.052% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-01-01 |  | 619710.45 | 143792500 | 210075878.99 | -66283378.99 | 3200000000 | -2.071% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-01-01 |  | 16635686.38 | 143792500 | 226711565.37 | -82919065.37 | 3200000000 | -2.591% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-01-09 | 50000000 |  | 193792500 | 226711565.37 | -32919065.37 | 3200000000 | -1.029% |  |  | 2019-01-09 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-02-01 |  | 4491397.74 | 193792500 | 231202963.11 | -37410463.11 | 3200000000 | -1.169% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-02-01 |  | 8369176.75 | 193792500 | 239572139.86 | -45779639.86 | 3200000000 | -1.431% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-02-01 |  | 318240.9 | 193792500 | 239890380.76 | -46097880.76 | 3200000000 | -1.441% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-02-01 |  | 39195732.22 | 193792500 | 279086112.98 | -85293612.98 | 3200000000 | -2.665% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-03-01 |  | 3228026.41 | 193792500 | 282314139.39 | -88521639.39 | 3200000000 | -2.766% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-03-01 |  | 12692212.55 | 193792500 | 295006351.94 | -101213851.94 | 3200000000 | -3.163% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-03-01 |  | 26725824.2 | 193792500 | 321732176.14 | -127939676.14 | 3200000000 | -3.998% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-03-07 | 44232256.1 |  | 238024756.1 | 321732176.14 | -83707420.04 | 3200000000 | -2.616% |  |  | 2019-03-07 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-03-14 | 84232258.79 |  | 322257014.89 | 321732176.14 | 524838.75 | 3200000000 | 0.0164% |  |  | 2019-03-14 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-03-17 | 22660316.98 |  | 344917331.87 | 321732176.14 | 23185155.73 | 3200000000 | 0.7245% |  |  | 2019-03-17 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-03-17 | 17339683.02 |  | 362257014.89 | 321732176.14 | 40524838.75 | 3200000000 | 1.266% |  |  | 2019-03-17 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-04-01 |  | 6184611.95 | 362257014.89 | 327916788.09 | 34340226.8 | 3200000000 | 1.073% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-04-01 |  | 7664656.53 | 362257014.89 | 335581444.62 | 26675570.27 | 3200000000 | 0.8336% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-04-01 |  | 47606 | 362257014.89 | 335629050.62 | 26627964.27 | 3200000000 | 0.8321% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-04-01 |  | 20073988.53 | 362257014.89 | 355703039.15 | 6553975.74 | 3200000000 | 0.2048% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-04-30 | 33239727.62 |  | 395496742.51 | 355703039.15 | 39793703.36 | 3200000000 | 1.244% |  |  | 2019-04-30 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-05-01 |  | 6657786.69 | 395496742.51 | 362360825.84 | 33135916.67 | 3200000000 | 1.035% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-05-01 |  | 11106831.15 | 395496742.51 | 373467656.99 | 22029085.52 | 3200000000 | 0.6884% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-05-01 |  | 26503581.86 | 395496742.51 | 399971238.85 | -4474496.34 | 3200000000 | -0.1398% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-05-05 | 4871486.85 |  | 400368229.36 | 399971238.85 | 396990.51 | 3200000000 | 0.01241% |  |  | 2019-05-05 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-05-05 | 28368240.75 |  | 428736470.11 | 399971238.85 | 28765231.26 | 3200000000 | 0.8989% |  |  | 2019-05-05 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-05-19 | 12983100.64 |  | 441719570.75 | 399971238.85 | 41748331.9 | 3200000000 | 1.305% |  |  | 2019-05-19 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-01 |  | 5948480.11 | 441719570.75 | 405919718.96 | 35799851.79 | 3200000000 | 1.119% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-01 |  | 4930084.92 | 441719570.75 | 410849803.88 | 30869766.87 | 3200000000 | 0.9647% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-01 |  | 75000 | 441719570.75 | 410924803.88 | 30794766.87 | 3200000000 | 0.9623% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-01 |  | 25186799.44 | 441719570.75 | 436111603.32 | 5607967.43 | 3200000000 | 0.1752% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-02 | 32983100.66 |  | 474702671.41 | 436111603.32 | 38591068.09 | 3200000000 | 1.206% |  |  | 2019-06-02 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-16 | 20000000 |  | 494702671.41 | 436111603.32 | 58591068.09 | 3200000000 | 1.831% |  |  | 2019-06-16 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-25 | 34182205.73 |  | 528884877.14 | 436111603.32 | 92773273.82 | 3200000000 | 2.899% |  |  | 2019-06-25 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-06-26 | 34182205.7 |  | 563067082.84 | 436111603.32 | 126955479.52 | 3200000000 | 3.967% |  |  | 2019-06-26 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-07-01 |  | 8117246.21 | 563067082.84 | 444228849.53 | 118838233.31 | 3200000000 | 3.714% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-07-01 |  | 20189200.56 | 563067082.84 | 464418050.09 | 98649032.75 | 3200000000 | 3.083% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-07-01 |  | 756.36 | 563067082.84 | 464418806.45 | 98648276.39 | 3200000000 | 3.083% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-07-01 |  | 23065905.38 | 563067082.84 | 487484711.83 | 75582371.01 | 3200000000 | 2.362% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-07-02 | 39074639.76 |  | 602141722.6 | 487484711.83 | 114657010.77 | 3200000000 | 3.583% |  |  | 2019-07-02 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-07-09 | 39074639.7 |  | 641216362.3 | 487484711.83 | 153731650.47 | 3200000000 | 4.804% |  |  | 2019-07-09 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-08-01 |  | 7176747.63 | 641216362.3 | 494661459.46 | 146554902.84 | 3200000000 | 4.58% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-08-01 |  | 8560770.57 | 641216362.3 | 503222230.03 | 137994132.27 | 3200000000 | 4.312% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-08-01 |  | 23330840.84 | 641216362.3 | 526553070.87 | 114663291.43 | 3200000000 | 3.583% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-08-08 | 17368496 |  | 658584858.3 | 526553070.87 | 132031787.43 | 3200000000 | 4.126% |  |  | 2019-08-08 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-08-25 | 714927.1 |  | 659299785.4 | 526553070.87 | 132746714.53 | 3200000000 | 4.148% |  |  | 2019-08-25 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-09-01 |  | 3812455.62 | 659299785.4 | 530365526.49 | 128934258.91 | 3200000000 | 4.029% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-09-01 |  | 6975277.24 | 659299785.4 | 537340803.73 | 121958981.67 | 3200000000 | 3.811% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-09-01 |  | 18919848.99 | 659299785.4 | 556260652.72 | 103039132.68 | 3200000000 | 3.22% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-09-17 | 27368495.94 |  | 686668281.34 | 556260652.72 | 130407628.62 | 3200000000 | 4.075% |  |  | 2019-09-17 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-09-17 | 10000000 |  | 696668281.34 | 556260652.72 | 140407628.62 | 3200000000 | 4.388% |  |  | 2019-09-17 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-09-19 | 18813823.95 |  | 715482105.29 | 556260652.72 | 159221452.57 | 3200000000 | 4.976% |  |  | 2019-09-19 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-10-01 |  | 6953248.92 | 715482105.29 | 563213901.64 | 152268203.65 | 3200000000 | 4.758% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-10-01 |  | 8884054.32 | 715482105.29 | 572097955.96 | 143384149.33 | 3200000000 | 4.481% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-10-01 |  | 14857757.62 | 715482105.29 | 586955713.58 | 128526391.71 | 3200000000 | 4.016% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-10-15 | 28813824.71 |  | 744295930 | 586955713.58 | 157340216.42 | 3200000000 | 4.917% |  |  | 2019-10-15 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-10-20 | 10000000 |  | 754295930 | 586955713.58 | 167340216.42 | 3200000000 | 5.229% |  |  | 2019-10-20 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-10-20 | 7768504.1 |  | 762064434.1 | 586955713.58 | 175108720.52 | 3200000000 | 5.472% |  |  | 2019-10-20 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-01 |  | 5927977.71 | 762064434.1 | 592883691.29 | 169180742.81 | 3200000000 | 5.287% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-01 |  | 15405719.14 | 762064434.1 | 608289410.43 | 153775023.67 | 3200000000 | 4.805% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-01 |  | 139149.69 | 762064434.1 | 608428560.12 | 153635873.98 | 3200000000 | 4.801% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-01 |  | 7787357.22 | 762064434.1 | 616215917.34 | 145848516.76 | 3200000000 | 4.558% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-17 | 27768504.1 |  | 789832938.2 | 616215917.34 | 173617020.86 | 3200000000 | 5.426% |  |  | 2019-11-17 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-17 | 22348276.35 |  | 812181214.55 | 616215917.34 | 195965297.21 | 3200000000 | 6.124% |  |  | 2019-11-17 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-17 | 20000000 |  | 832181214.55 | 616215917.34 | 215965297.21 | 3200000000 | 6.749% |  |  | 2019-11-17 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-20 | 26359242 |  | 858540456.55 | 616215917.34 | 242324539.21 | 3200000000 | 7.573% |  |  | 2019-11-20 | added cash in 3 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-11-21 | 26359242 |  | 884899698.55 | 616215917.34 | 268683781.21 | 3200000000 | 8.396% |  |  | 2019-11-21 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-12-01 |  | 8522080.35 | 884899698.55 | 624737997.69 | 260161700.86 | 3200000000 | 8.13% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-12-01 |  | 33350839.96 | 884899698.55 | 658088837.65 | 226810860.9 | 3200000000 | 7.088% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-12-01 |  | 4875935.61 | 884899698.55 | 662964773.26 | 221934925.29 | 3200000000 | 6.935% |  |  |  | cash out both |  |  | 2019
R05 Residential District Z1 & Z2 | 2019-12-22 | 23826290.1 |  | 908725988.65 | 662964773.26 | 245761215.39 | 3200000000 | 7.68% |  |  | 2019-12-22 | added 1 |  |  | 2019
R05 Residential District Z1 & Z2 | 2020-01-01 |  | 6039332.59 | 908725988.65 | 669004105.85 | 239721882.8 | 3200000000 | 7.491% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-01-01 |  | 21309533.92 | 908725988.65 | 690313639.77 | 218412348.88 | 3200000000 | 6.825% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-01-01 |  | 4632982.68 | 908725988.65 | 694946622.45 | 213779366.2 | 3200000000 | 6.681% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-02-01 |  | 7152900.05 | 908725988.65 | 702099522.5 | 206626466.15 | 3200000000 | 6.457% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-02-01 |  | 39627705.68 | 908725988.65 | 741727228.18 | 166998760.47 | 3200000000 | 5.219% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-02-01 |  | 3424586.89 | 908725988.65 | 745151815.07 | 163574173.58 | 3200000000 | 5.112% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-02-09 | 29830600.5 |  | 938556589.15 | 745151815.07 | 193404774.08 | 3200000000 | 6.044% |  |  | 2020-02-09 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-03-01 |  | 5598607.46 | 938556589.15 | 750750422.53 | 187806166.62 | 3200000000 | 5.869% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-03-01 |  | 14430127.07 | 938556589.15 | 765180549.6 | 173376039.55 | 3200000000 | 5.418% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-03-01 |  | 1615808.26 | 938556589.15 | 766796357.86 | 171760231.29 | 3200000000 | 5.368% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-03-19 | 22909628.3 |  | 961466217.45 | 766796357.86 | 194669859.59 | 3200000000 | 6.083% |  |  | 2020-03-19 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-04-01 |  | 9674509.52 | 961466217.45 | 776470867.38 | 184995350.07 | 3200000000 | 5.781% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-04-01 |  | 11216608.3 | 961466217.45 | 787687475.68 | 173778741.77 | 3200000000 | 5.431% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-04-01 |  | 1713169.18 | 961466217.45 | 789400644.86 | 172065572.59 | 3200000000 | 5.377% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-04-09 | 21628889.1 |  | 983095106.55 | 789400644.86 | 193694461.69 | 3200000000 | 6.053% |  |  | 2020-04-09 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-05-01 |  | 1950320.47 | 983095106.55 | 791350965.33 | 191744141.22 | 3200000000 | 5.992% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-05-01 |  | 13876921.58 | 983095106.55 | 805227886.91 | 177867219.64 | 3200000000 | 5.558% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-05-01 |  | 2111232.36 | 983095106.55 | 807339119.27 | 175755987.28 | 3200000000 | 5.492% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-05-04 | 35488384.45 |  | 1018583491 | 807339119.27 | 211244371.73 | 3200000000 | 6.601% |  |  | 2020-05-04 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-05-20 | 12244457.65 |  | 1030827948.65 | 807339119.27 | 223488829.38 | 3200000000 | 6.984% |  |  | 2020-05-20 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-05-26 | 35000000 |  | 1065827948.65 | 807339119.27 | 258488829.38 | 3200000000 | 8.078% |  |  | 2020-05-26 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-05-31 | 35000000 |  | 1100827948.65 | 807339119.27 | 293488829.38 | 3200000000 | 9.172% |  |  | 2020-05-31 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-06-01 |  | 11664743.66 | 1100827948.65 | 819003862.93 | 281824085.72 | 3200000000 | 8.807% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-06-01 |  | 24514808.8 | 1100827948.65 | 843518671.73 | 257309276.92 | 3200000000 | 8.041% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-06-01 |  | 1686225 | 1100827948.65 | 845204896.73 | 255623051.92 | 3200000000 | 7.988% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-06-07 | 11413010.6 |  | 1112240959.25 | 845204896.73 | 267036062.52 | 3200000000 | 8.345% |  |  | 2020-06-07 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-06-08 | 2000000 |  | 1114240959.25 | 845204896.73 | 269036062.52 | 3200000000 | 8.407% |  |  | 2020-06-08 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-06-08 | 11413010.6 |  | 1125653969.85 | 845204896.73 | 280449073.12 | 3200000000 | 8.764% |  |  | 2020-06-08 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-01 |  | 6783764.36 | 1125653969.85 | 851988661.09 | 273665308.76 | 3200000000 | 8.552% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-01 |  | 24620530.92 | 1125653969.85 | 876609192.01 | 249044777.84 | 3200000000 | 7.783% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-01 |  | 1350504 | 1125653969.85 | 877959696.01 | 247694273.84 | 3200000000 | 7.74% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-13 | 15000000 |  | 1140653969.85 | 877959696.01 | 262694273.84 | 3200000000 | 8.209% |  |  | 2020-07-13 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-13 | 28461647.31 |  | 1169115617.16 | 877959696.01 | 291155921.15 | 3200000000 | 9.099% |  |  | 2020-07-13 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-14 | 28461647.31 |  | 1197577264.47 | 877959696.01 | 319617568.46 | 3200000000 | 9.988% |  |  | 2020-07-14 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-22 | 22790518.4 |  | 1220367782.87 | 877959696.01 | 342408086.86 | 3200000000 | 10.7% |  |  | 2020-07-22 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-31 | 3425282.3 |  | 1223793065.17 | 877959696.01 | 345833369.16 | 3200000000 | 10.81% |  |  | 2020-07-31 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-07-31 | 22790518.4 |  | 1246583583.57 | 877959696.01 | 368623887.56 | 3200000000 | 11.52% |  |  | 2020-07-31 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-08-01 |  | 1478718.19 | 1246583583.57 | 879438414.2 | 367145169.37 | 3200000000 | 11.47% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-08-01 |  | 18431470.09 | 1246583583.57 | 897869884.29 | 348713699.28 | 3200000000 | 10.9% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-08-06 | 3425282.3 |  | 1250008865.87 | 897869884.29 | 352138981.58 | 3200000000 | 11% |  |  | 2020-08-06 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-08-31 | 46190767.35 |  | 1296199633.22 | 897869884.29 | 398329748.93 | 3200000000 | 12.45% |  |  | 2020-08-31 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-01 |  | 10456811.21 | 1296199633.22 | 908326695.5 | 387872937.72 | 3200000000 | 12.12% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-01 |  | 30239520.27 | 1296199633.22 | 938566215.77 | 357633417.45 | 3200000000 | 11.18% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-01 |  | 2045601.7 | 1296199633.22 | 940611817.47 | 355587815.75 | 3200000000 | 11.11% |  |  |  | cash out both |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-02 | 46190767.35 |  | 1342390400.57 | 940611817.47 | 401778583.1 | 3200000000 | 12.56% |  |  | 2020-09-02 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-02 | 3482659.8 |  | 1345873060.37 | 940611817.47 | 405261242.9 | 3200000000 | 12.66% |  |  | 2020-09-02 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-02 | 1602620.05 |  | 1347475680.42 | 940611817.47 | 406863862.95 | 3200000000 | 12.71% |  |  | 2020-09-02 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-08 | 3482659.8 |  | 1350958340.22 | 940611817.47 | 410346522.75 | 3200000000 | 12.82% |  |  | 2020-09-08 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-08 | 1602620.05 |  | 1352560960.27 | 940611817.47 | 411949142.8 | 3200000000 | 12.87% |  |  | 2020-09-08 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-09-20 | 122781824.85 |  | 1475342785.12 | 940611817.47 | 534730967.65 | 3200000000 | 16.71% |  |  | 2020-09-20 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-10-01 | 1000000 |  | 1476342785.12 | 940611817.47 | 535730967.65 | 3200000000 | 16.74% |  |  | 2020-10-01 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-10-01 |  | 33257145.05 | 1476342785.12 | 973868962.52 | 502473822.6 | 3200000000 | 15.7% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-10-04 | 20000000 |  | 1496342785.12 | 973868962.52 | 522473822.6 | 3200000000 | 16.33% |  |  | 2020-10-04 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-10-04 | 34332927.05 |  | 1530675712.17 | 973868962.52 | 556806749.65 | 3200000000 | 17.4% |  |  | 2020-10-04 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-10-05 | 34332927.05 |  | 1565008639.22 | 973868962.52 | 591139676.7 | 3200000000 | 18.47% |  |  | 2020-10-05 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-10-05 | 11158750.85 |  | 1576167390.07 | 973868962.52 | 602298427.55 | 3200000000 | 18.82% |  |  | 2020-10-05 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-10-07 | 11158750.85 |  | 1587326140.92 | 973868962.52 | 613457178.4 | 3200000000 | 19.17% |  |  | 2020-10-07 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-11-01 |  | 27732596.03 | 1587326140.92 | 1001601558.55 | 585724582.37 | 3200000000 | 18.3% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-11-09 | 22661440.9 |  | 1609987581.82 | 1001601558.55 | 608386023.27 | 3200000000 | 19.01% |  |  | 2020-11-09 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-11-12 | 70000000 |  | 1679987581.82 | 1001601558.55 | 678386023.27 | 3200000000 | 21.2% |  |  | 2020-11-12 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-11-15 | 70000000 |  | 1749987581.82 | 1001601558.55 | 748386023.27 | 3200000000 | 23.39% |  |  | 2020-11-15 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-11-18 | 10611814.75 |  | 1760599396.57 | 1001601558.55 | 758997838.02 | 3200000000 | 23.72% |  |  | 2020-11-18 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-11-19 | 10611814.75 |  | 1771211211.32 | 1001601558.55 | 769609652.77 | 3200000000 | 24.05% |  |  | 2020-11-19 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-11-23 | 23127827.2 |  | 1794339038.52 | 1001601558.55 | 792737479.97 | 3200000000 | 24.77% |  |  | 2020-11-23 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-12-01 |  | 24176534.45 | 1794339038.52 | 1025778093 | 768560945.52 | 3200000000 | 24.02% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-12-15 | 61866445.3 |  | 1856205483.82 | 1025778093 | 830427390.82 | 3200000000 | 25.95% |  |  | 2020-12-15 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-12-16 | 11075840.05 |  | 1867281323.87 | 1025778093 | 841503230.87 | 3200000000 | 26.3% |  |  | 2020-12-16 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-12-16 | 61866445.3 |  | 1929147769.17 | 1025778093 | 903369676.17 | 3200000000 | 28.23% |  |  | 2020-12-16 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-12-23 | 11075840.05 |  | 1940223609.22 | 1025778093 | 914445516.22 | 3200000000 | 28.58% |  |  | 2020-12-23 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-12-31 | 8196791 |  | 1948420400.22 | 1025778093 | 922642307.22 | 3200000000 | 28.83% |  |  | 2020-12-31 | added 1 |  |  | 2020
R05 Residential District Z1 & Z2 | 2020-12-31 | 8196778.85 |  | 1956617179.07 | 1025778093 | 930839086.07 | 3200000000 | 29.09% |  |  | 2020-12-31 | added cash in 3 |  |  | 2020
R05 Residential District Z1 & Z2 | 2021-01-01 |  | 34820698.08 | 1956617179.07 | 1060598791.08 | 896018387.99 | 3200000000 | 28% |  |  |  | cash out both |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-01-11 | 19661149.99 |  | 1976278329.06 | 1060598791.08 | 915679537.98 | 3200000000 | 28.61% |  |  | 2021-01-11 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-01 |  | 28846175.38 | 1976278329.06 | 1089444966.46 | 886833362.6 | 3200000000 | 27.71% |  |  |  | cash out both |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-18 | 11910531.03 |  | 1988188860.09 | 1089444966.46 | 898743893.63 | 3200000000 | 28.09% |  |  | 2021-02-18 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-18 | 11910519.03 |  | 2000099379.12 | 1089444966.46 | 910654412.66 | 3200000000 | 28.46% |  |  | 2021-02-18 | added cash in 3 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-22 | 4000000 |  | 2004099379.12 | 1089444966.46 | 914654412.66 | 3200000000 | 28.58% |  |  | 2021-02-22 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-22 | 1500000 |  | 2005599379.12 | 1089444966.46 | 916154412.66 | 3200000000 | 28.63% |  |  | 2021-02-22 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-22 | 1251300.48 |  | 2006850679.6 | 1089444966.46 | 917405713.14 | 3200000000 | 28.67% |  |  | 2021-02-22 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-23 | 1500000 |  | 2008350679.6 | 1089444966.46 | 918905713.14 | 3200000000 | 28.72% |  |  | 2021-02-23 | added cash in 3 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-23 | 4000000 |  | 2012350679.6 | 1089444966.46 | 922905713.14 | 3200000000 | 28.84% |  |  | 2021-02-23 | added cash in 3 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-23 | 1251300.48 |  | 2013601980.08 | 1089444966.46 | 924157013.62 | 3200000000 | 28.88% |  |  | 2021-02-23 | added cash in 3 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-02-28 | 16426047.71 |  | 2030028027.79 | 1089444966.46 | 940583061.33 | 3200000000 | 29.39% |  |  | 2021-02-28 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-01 |  | 12180272.53 | 2030028027.79 | 1101625238.99 | 928402788.8 | 3200000000 | 29.01% |  |  |  | cash out both |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-07 | 713899.2 |  | 2030741926.99 | 1101625238.99 | 929116688 | 3200000000 | 29.03% |  |  | 2021-03-07 | added cash in 3 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-08 | 713899.2 |  | 2031455826.19 | 1101625238.99 | 929830587.2 | 3200000000 | 29.06% |  |  | 2021-03-08 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-28 | 10000000.03 |  | 2041455826.22 | 1101625238.99 | 939830587.23 | 3200000000 | 29.37% |  |  | 2021-03-28 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-28 | 1000000 |  | 2042455826.22 | 1101625238.99 | 940830587.23 | 3200000000 | 29.4% |  |  | 2021-03-28 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-28 | 13096920.15 |  | 2055552746.37 | 1101625238.99 | 953927507.38 | 3200000000 | 29.81% |  |  | 2021-03-28 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-28 | 14603884 |  | 2070156630.37 | 1101625238.99 | 968531391.38 | 3200000000 | 30.27% |  |  | 2021-03-28 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-28 | 8206207.05 |  | 2078362837.42 | 1101625238.99 | 976737598.43 | 3200000000 | 30.52% |  |  | 2021-03-28 | added 1 |  |  | 2021
R05 Residential District Z1 & Z2 | 2021-03-28 | 11000000 |  | 2089362837.42 | 1101625238.99 | 987737598.43 | 3200000000 | 30.87% |  |  | 2021-03-28 | added cash in 3 |  |  | 2021
1900
Abu Sultan Bridge 02 Greenhouse | 2018-07-01 |  | 180000 | 0 | 180000 | -180000 | 67755600 | -0.2657% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 02 Greenhouse | 2018-08-01 |  | 120625 | 0 | 300625 | -300625 | 67755600 | -0.4437% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 02 Greenhouse | 2018-09-01 |  | 221545 | 0 | 522170 | -522170 | 67755600 | -0.7707% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 02 Greenhouse | 2018-10-01 |  | 604540.2 | 0 | 1126710.2 | -1126710.2 | 67755600 | -1.663% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 02 Greenhouse | 2018-11-01 |  | 2176076.76 | 0 | 3302786.96 | -3302786.96 | 67755600 | -4.875% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 02 Greenhouse | 2018-12-01 |  | 2412694.59 | 0 | 5715481.55 | -5715481.55 | 67755600 | -8.435% |  |  |  | cash out both |  |  | 2018
Abu Sultan Bridge 02 Greenhouse | 2019-01-01 |  | 2444710.54 | 0 | 8160192.09 | -8160192.09 | 67755600 | -12.04% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-01-16 | 1120156.35 |  | 1120156.35 | 8160192.09 | -7040035.74 | 67755600 | -10.39% |  |  | 2019-01-16 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-02-01 |  | 2540959.22 | 1120156.35 | 10701151.31 | -9580994.96 | 67755600 | -14.14% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-03-01 |  | 3521770.18 | 1120156.35 | 14222921.49 | -13102765.14 | 67755600 | -19.34% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-04-01 |  | 1356068.35 | 1120156.35 | 15578989.84 | -14458833.49 | 67755600 | -21.34% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-05-01 |  | 980908.48 | 1120156.35 | 16559898.32 | -15439741.97 | 67755600 | -22.79% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-06-01 |  | 214990.45 | 1120156.35 | 16774888.77 | -15654732.42 | 67755600 | -23.1% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-06-09 | 10268543.35 |  | 11388699.7 | 16774888.77 | -5386189.07 | 67755600 | -7.949% |  |  | 2019-06-09 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-06-25 | 24850000 |  | 36238699.7 | 16774888.77 | 19463810.93 | 67755600 | 28.73% |  |  | 2019-06-25 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-07-01 |  | 944483.45 | 36238699.7 | 17719372.22 | 18519327.48 | 67755600 | 27.33% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-07-04 | 3387777 |  | 39626476.7 | 17719372.22 | 21907104.48 | 67755600 | 32.33% |  |  | 2019-07-04 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-07-31 | 6525150 |  | 46151626.7 | 17719372.22 | 28432254.48 | 67755600 | 41.96% |  |  | 2019-07-31 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-08-01 |  | 576975.95 | 46151626.7 | 18296348.17 | 27855278.53 | 67755600 | 41.11% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-09-01 |  | 230366.77 | 46151626.7 | 18526714.94 | 27624911.76 | 67755600 | 40.77% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-09-19 | 6214797 |  | 52366423.7 | 18526714.94 | 33839708.76 | 67755600 | 49.94% |  |  | 2019-09-19 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-09-29 | 2392747 |  | 54759170.7 | 18526714.94 | 36232455.76 | 67755600 | 53.48% |  |  | 2019-09-29 | added cash in 3 |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-10-01 |  | 163352.25 | 54759170.7 | 18690067.19 | 36069103.51 | 67755600 | 53.23% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-11-01 |  | 3387.78 | 54759170.7 | 18693454.97 | 36065715.73 | 67755600 | 53.23% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2019-12-01 |  | 3263663.74 | 54759170.7 | 21957118.71 | 32802051.99 | 67755600 | 48.41% |  |  |  | cash out both |  |  | 2019
Abu Sultan Bridge 02 Greenhouse | 2020-02-01 |  | 2019.51 | 54759170.7 | 21959138.22 | 32800032.48 | 67755600 | 48.41% |  |  |  | cash out both |  |  | 2020
Abu Sultan Bridge 02 Greenhouse | 2021-02-16 | 3830495 |  | 58589665.7 | 21959138.22 | 36630527.48 | 67755600 | 54.06% |  |  | 2021-02-16 | added cash in 3 |  |  | 2021
1900
El Sokhna Tunnel 02 | 2018-08-01 |  | 215295 | 0 | 215295 | -215295 | 22334150 | -0.964% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 02 | 2018-09-01 |  | 74228.99 | 0 | 289523.99 | -289523.99 | 22334150 | -1.296% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 02 | 2018-10-01 |  | 1079959.14 | 0 | 1369483.13 | -1369483.13 | 22334150 | -6.132% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 02 | 2018-11-01 |  | 1654571.72 | 0 | 3024054.85 | -3024054.85 | 22334150 | -13.54% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 02 | 2018-12-01 |  | 789569.3 | 0 | 3813624.15 | -3813624.15 | 22334150 | -17.08% |  |  |  | cash out both |  |  | 2018
El Sokhna Tunnel 02 | 2019-01-01 |  | 964202.24 | 0 | 4777826.39 | -4777826.39 | 22334150 | -21.39% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-02-01 |  | 595096.08 | 0 | 5372922.47 | -5372922.47 | 22334150 | -24.06% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-03-01 |  | 556442.53 | 0 | 5929365 | -5929365 | 22334150 | -26.55% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-04-01 |  | 104032.14 | 0 | 6033397.14 | -6033397.14 | 22334150 | -27.01% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-05-01 |  | 693999.44 | 0 | 6727396.58 | -6727396.58 | 22334150 | -30.12% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-06-01 |  | 3378.96 | 0 | 6730775.54 | -6730775.54 | 22334150 | -30.14% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-06-17 | 4962905.4 |  | 4962905.4 | 6730775.54 | -1767870.14 | 22334150 | -7.916% |  |  | 2019-06-17 | added cash in 3 |  |  | 2019
El Sokhna Tunnel 02 | 2019-06-30 | 3797276 |  | 8760181.4 | 6730775.54 | 2029405.86 | 22334150 | 9.087% |  |  | 2019-06-30 | added cash in 3 |  |  | 2019
El Sokhna Tunnel 02 | 2019-07-01 |  | 367040.25 | 8760181.4 | 7097815.79 | 1662365.61 | 22334150 | 7.443% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-09-01 |  | 52513.44 | 8760181.4 | 7150329.23 | 1609852.17 | 22334150 | 7.208% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-09-25 | 2166937 |  | 10927118.4 | 7150329.23 | 3776789.17 | 22334150 | 16.91% |  |  | 2019-09-25 | added cash in 3 |  |  | 2019
El Sokhna Tunnel 02 | 2019-10-01 |  | 16772.72 | 10927118.4 | 7167101.95 | 3760016.45 | 22334150 | 16.84% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2019-11-13 | 666877 |  | 11593995.4 | 7167101.95 | 4426893.45 | 22334150 | 19.82% |  |  | 2019-11-13 | added cash in 3 |  |  | 2019
El Sokhna Tunnel 02 | 2019-12-01 |  | 1197331.1 | 11593995.4 | 8364433.05 | 3229562.35 | 22334150 | 14.46% |  |  |  | cash out both |  |  | 2019
El Sokhna Tunnel 02 | 2020-08-01 |  | 7108.4 | 11593995.4 | 8371541.45 | 3222453.95 | 22334150 | 14.43% |  |  |  | cash out both |  |  | 2020
El Sokhna Tunnel 02 | 2020-09-09 | 1702965 |  | 13296960.4 | 8371541.45 | 4925418.95 | 22334150 | 22.05% |  |  | 2020-09-09 | added 1 |  |  | 2020
1900
El Awsty Middle Tunnel L&L | 2018-10-01 |  | 17805 | 0 | 17805 | -17805 | 1024820 | -1.737% |  |  |  | cash out both |  |  | 2018
El Awsty Middle Tunnel L&L | 2018-11-01 |  | 68698.63 | 0 | 86503.63 | -86503.63 | 1024820 | -8.441% |  |  |  | cash out both |  |  | 2018
El Awsty Middle Tunnel L&L | 2018-12-01 |  | 10425 | 0 | 96928.63 | -96928.63 | 1024820 | -9.458% |  |  |  | cash out both |  |  | 2018
El Awsty Middle Tunnel L&L | 2019-01-01 |  | 25262 | 0 | 122190.63 | -122190.63 | 1024820 | -11.92% |  |  |  | cash out both |  |  | 2019
El Awsty Middle Tunnel L&L | 2019-04-01 |  | 20855 | 0 | 143045.63 | -143045.63 | 1024820 | -13.96% |  |  |  | cash out both |  |  | 2019
El Awsty Middle Tunnel L&L | 2019-05-01 |  | 30737 | 0 | 173782.63 | -173782.63 | 1024820 | -16.96% |  |  |  | cash out both |  |  | 2019
El Awsty Middle Tunnel L&L | 2019-12-01 |  | 17506.21 | 0 | 191288.84 | -191288.84 | 1024820 | -18.67% |  |  |  | cash out both |  |  | 2019
El Awsty Middle Tunnel L&L | 2020-12-20 | 677590 |  | 677590 | 191288.84 | 486301.16 | 1024820 | 47.45% |  |  | 2020-12-20 | added cash in 3 |  |  | 2020
1900
Sodic Eastown EDNC | 2018-11-01 |  | 496500 | 0 | 496500 | -496500 | 1074545067 | -0.04621% |  |  |  | cash out both |  |  | 2018
Sodic Eastown EDNC | 2018-12-01 |  | 37731.56 | 0 | 534231.56 | -534231.56 | 1074545067 | -0.04972% |  |  |  | cash out both |  |  | 2018
Sodic Eastown EDNC | 2018-12-09 | 122000000 |  | 122000000 | 534231.56 | 121465768.44 | 1074545067 | 11.3% |  |  | 2018-12-09 | added cash in 3 |  |  | 2018
Sodic Eastown EDNC | 2019-01-01 |  | 200957.34 | 122000000 | 735188.9 | 121264811.1 | 1074545067 | 11.29% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-02-01 |  | 5716029.96 | 122000000 | 6451218.86 | 115548781.14 | 1074545067 | 10.75% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-03-01 |  | 14981771.08 | 122000000 | 21432989.94 | 100567010.06 | 1074545067 | 9.359% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-04-01 |  | 14415072.39 | 122000000 | 35848062.33 | 86151937.67 | 1074545067 | 8.018% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-04-11 | 6789620.12 |  | 128789620.12 | 35848062.33 | 92941557.79 | 1074545067 | 8.649% |  |  | 2019-04-11 | added 1 |  |  | 2019
Sodic Eastown EDNC | 2019-05-01 |  | 17545595.44 | 128789620.12 | 53393657.77 | 75395962.35 | 1074545067 | 7.017% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-05-09 | 15638373.66 |  | 144427993.78 | 53393657.77 | 91034336.01 | 1074545067 | 8.472% |  |  | 2019-05-09 | added 1 |  |  | 2019
Sodic Eastown EDNC | 2019-06-01 |  | 14513172.01 | 144427993.78 | 67906829.78 | 76521164 | 1074545067 | 7.121% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-07-01 |  | 42043691.46 | 144427993.78 | 109950521.24 | 34477472.54 | 1074545067 | 3.209% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-07-09 | 10000000 |  | 154427993.78 | 109950521.24 | 44477472.54 | 1074545067 | 4.139% |  |  | 2019-07-09 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-07-17 | 1574016.18 |  | 156002009.96 | 109950521.24 | 46051488.72 | 1074545067 | 4.286% |  |  | 2019-07-17 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-07-24 | 15688338.61 |  | 171690348.57 | 109950521.24 | 61739827.33 | 1074545067 | 5.746% |  |  | 2019-07-24 | added 1 |  |  | 2019
Sodic Eastown EDNC | 2019-07-24 | 849097.69 |  | 172539446.26 | 109950521.24 | 62588925.02 | 1074545067 | 5.825% |  |  | 2019-07-24 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-08-01 |  | 36555367.52 | 172539446.26 | 146505888.76 | 26033557.5 | 1074545067 | 2.423% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-08-05 | 15000000 |  | 187539446.26 | 146505888.76 | 41033557.5 | 1074545067 | 3.819% |  |  | 2019-08-05 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-08-25 | 22056568.4 |  | 209596014.66 | 146505888.76 | 63090125.9 | 1074545067 | 5.871% |  |  | 2019-08-25 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-09-01 |  | 22974102.1 | 209596014.66 | 169479990.86 | 40116023.8 | 1074545067 | 3.733% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-09-05 | 18000000 |  | 227596014.66 | 169479990.86 | 58116023.8 | 1074545067 | 5.408% |  |  | 2019-09-05 | added 1 |  |  | 2019
Sodic Eastown EDNC | 2019-10-01 |  | 52148786.35 | 227596014.66 | 221628777.21 | 5967237.45 | 1074545067 | 0.5553% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-10-03 | 10554847.67 |  | 238150862.33 | 221628777.21 | 16522085.12 | 1074545067 | 1.538% |  |  | 2019-10-03 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-10-03 | 59565.32 |  | 238210427.65 | 221628777.21 | 16581650.44 | 1074545067 | 1.543% |  |  | 2019-10-03 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-11-01 |  | 41059341.61 | 238210427.65 | 262688118.82 | -24477691.17 | 1074545067 | -2.278% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-11-04 | 35000000 |  | 273210427.65 | 262688118.82 | 10522308.83 | 1074545067 | 0.9792% |  |  | 2019-11-04 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-11-27 | 3197130.95 |  | 276407558.6 | 262688118.82 | 13719439.78 | 1074545067 | 1.277% |  |  | 2019-11-27 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-12-01 |  | 35916639.7 | 276407558.6 | 298604758.52 | -22197199.92 | 1074545067 | -2.066% |  |  |  | cash out both |  |  | 2019
Sodic Eastown EDNC | 2019-12-02 | 46000000 |  | 322407558.6 | 298604758.52 | 23802800.08 | 1074545067 | 2.215% |  |  | 2019-12-02 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-12-17 | 3554660.12 |  | 325962218.72 | 298604758.52 | 27357460.2 | 1074545067 | 2.546% |  |  | 2019-12-17 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-12-17 | 9532397.61 |  | 335494616.33 | 298604758.52 | 36889857.81 | 1074545067 | 3.433% |  |  | 2019-12-17 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2019-12-30 | 40504812.26 |  | 375999428.59 | 298604758.52 | 77394670.07 | 1074545067 | 7.203% |  |  | 2019-12-30 | added cash in 3 |  |  | 2019
Sodic Eastown EDNC | 2020-01-01 |  | 35985916.6 | 375999428.59 | 334590675.12 | 41408753.47 | 1074545067 | 3.854% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-01-09 | 1311245.56 |  | 377310674.15 | 334590675.12 | 42719999.03 | 1074545067 | 3.976% |  |  | 2020-01-09 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-01-22 | 32553581.24 |  | 409864255.39 | 334590675.12 | 75273580.27 | 1074545067 | 7.005% |  |  | 2020-01-22 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-02-01 |  | 24089446.28 | 409864255.39 | 358680121.4 | 51184133.99 | 1074545067 | 4.763% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-02-09 | 32553581.23 |  | 442417836.62 | 358680121.4 | 83737715.22 | 1074545067 | 7.793% |  |  | 2020-02-09 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-02-09 | 1311245.56 |  | 443729082.18 | 358680121.4 | 85048960.78 | 1074545067 | 7.915% |  |  | 2020-02-09 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-03-01 |  | 15079838.43 | 443729082.18 | 373759959.83 | 69969122.35 | 1074545067 | 6.512% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-03-05 | 27179529.39 |  | 470908611.57 | 373759959.83 | 97148651.74 | 1074545067 | 9.041% |  |  | 2020-03-05 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-03-05 | 2324832.91 |  | 473233444.48 | 373759959.83 | 99473484.65 | 1074545067 | 9.257% |  |  | 2020-03-05 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-03-26 | 19553108.79 |  | 492786553.27 | 373759959.83 | 119026593.44 | 1074545067 | 11.08% |  |  | 2020-03-26 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-03-26 | 2884335.94 |  | 495670889.21 | 373759959.83 | 121910929.38 | 1074545067 | 11.35% |  |  | 2020-03-26 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-04-01 |  | 5709072.59 | 495670889.21 | 379469032.42 | 116201856.79 | 1074545067 | 10.81% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-05-01 |  | 17860266.56 | 495670889.21 | 397329298.98 | 98341590.23 | 1074545067 | 9.152% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-05-04 | 5928168 |  | 501599057.21 | 397329298.98 | 104269758.23 | 1074545067 | 9.704% |  |  | 2020-05-04 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-05-05 | 10000000 |  | 511599057.21 | 397329298.98 | 114269758.23 | 1074545067 | 10.63% |  |  | 2020-05-05 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-05-14 | 6201534.04 |  | 517800591.25 | 397329298.98 | 120471292.27 | 1074545067 | 11.21% |  |  | 2020-05-14 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-05-14 | 5928168 |  | 523728759.25 | 397329298.98 | 126399460.27 | 1074545067 | 11.76% |  |  | 2020-05-14 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-06-01 |  | 22096035.81 | 523728759.25 | 419425334.79 | 104303424.46 | 1074545067 | 9.707% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-06-11 | 15000000 |  | 538728759.25 | 419425334.79 | 119303424.46 | 1074545067 | 11.1% |  |  | 2020-06-11 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-07-01 |  | 23893101.81 | 538728759.25 | 443318436.6 | 95410322.65 | 1074545067 | 8.879% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-07-13 | 12895954 |  | 551624713.25 | 443318436.6 | 108306276.65 | 1074545067 | 10.08% |  |  | 2020-07-13 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-08-01 |  | 20400288.06 | 551624713.25 | 463718724.66 | 87905988.59 | 1074545067 | 8.181% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-08-18 | 1801458.51 |  | 553426171.76 | 463718724.66 | 89707447.1 | 1074545067 | 8.348% |  |  | 2020-08-18 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-08-18 | 1537461.58 |  | 554963633.34 | 463718724.66 | 91244908.68 | 1074545067 | 8.491% |  |  | 2020-08-18 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-09-01 | 1322438.36 |  | 556286071.7 | 463718724.66 | 92567347.04 | 1074545067 | 8.615% |  |  | 2020-09-01 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-09-01 |  | 29856014.31 | 556286071.7 | 493574738.97 | 62711332.73 | 1074545067 | 5.836% |  |  |  | cash out both |  |  | 2020
Sodic Eastown EDNC | 2020-09-13 | 899381.34 |  | 557185453.04 | 493574738.97 | 63610714.07 | 1074545067 | 5.92% |  |  | 2020-09-13 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-09-15 | 1322438.36 |  | 558507891.4 | 493574738.97 | 64933152.43 | 1074545067 | 6.043% |  |  | 2020-09-15 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-09-15 | 899381.34 |  | 559407272.74 | 493574738.97 | 65832533.77 | 1074545067 | 6.127% |  |  | 2020-09-15 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-09-24 | 1754521.36 |  | 561161794.1 | 493574738.97 | 67587055.13 | 1074545067 | 6.29% |  |  | 2020-09-24 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-09-29 | 15000000 |  | 576161794.1 | 493574738.97 | 82587055.13 | 1074545067 | 7.686% |  |  | 2020-09-29 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-10-01 |  | 23473520.22 | 576161794.1 | 517048259.19 | 59113534.91 | 1074545067 | 5.501% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Sodic Eastown EDNC | 2020-10-20 | 7406610.78 |  | 583568404.88 | 517048259.19 | 66520145.69 | 1074545067 | 6.191% |  |  | 2020-10-20 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-11-01 |  | 31194663.36 | 583568404.88 | 548242922.55 | 35325482.33 | 1074545067 | 3.287% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Sodic Eastown EDNC | 2020-11-03 | 25500000 |  | 609068404.88 | 548242922.55 | 60825482.33 | 1074545067 | 5.661% |  |  | 2020-11-03 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-11-22 | 862557.37 |  | 609930962.25 | 548242922.55 | 61688039.7 | 1074545067 | 5.741% |  |  | 2020-11-22 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-11-24 | 8917592.72 |  | 618848554.97 | 548242922.55 | 70605632.42 | 1074545067 | 6.571% |  |  | 2020-11-24 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-11-24 | 862557.37 |  | 619711112.34 | 548242922.55 | 71468189.79 | 1074545067 | 6.651% |  |  | 2020-11-24 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-11-24 | 8917592.73 |  | 628628705.07 | 548242922.55 | 80385782.52 | 1074545067 | 7.481% |  |  | 2020-11-24 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-12-01 |  | 32209765.4 | 628628705.07 | 580452687.95 | 48176017.12 | 1074545067 | 4.483% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Sodic Eastown EDNC | 2020-12-17 | 4197031.83 |  | 632825736.9 | 580452687.95 | 52373048.95 | 1074545067 | 4.874% |  |  | 2020-12-17 | added 1 |  |  | 2020
Sodic Eastown EDNC | 2020-12-22 | 25000000 |  | 657825736.9 | 580452687.95 | 77373048.95 | 1074545067 | 7.201% |  |  | 2020-12-22 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2020-12-22 | 4197031.83 |  | 662022768.73 | 580452687.95 | 81570080.78 | 1074545067 | 7.591% |  |  | 2020-12-22 | added cash in 3 |  |  | 2020
Sodic Eastown EDNC | 2021-01-01 |  | 36263541.01 | 662022768.73 | 616716228.96 | 45306539.77 | 1074545067 | 4.216% |  |  |  | cash out both |  |  | 2021
Sodic Eastown EDNC | 2021-02-01 | 4743783.32 |  | 666766552.05 | 616716228.96 | 50050323.09 | 1074545067 | 4.658% |  |  | 2021-02-01 | added 1 |  |  | 2021
Sodic Eastown EDNC | 2021-02-01 | 15000000 |  | 681766552.05 | 616716228.96 | 65050323.09 | 1074545067 | 6.054% |  |  | 2021-02-01 | added 1 |  |  | 2021
Sodic Eastown EDNC | 2021-02-01 |  | 26912717.7 | 681766552.05 | 643628946.66 | 38137605.39 | 1074545067 | 3.549% |  |  |  | cash out both |  |  | 2021
Sodic Eastown EDNC | 2021-02-03 | 4743783.32 |  | 686510335.37 | 643628946.66 | 42881388.71 | 1074545067 | 3.991% |  |  | 2021-02-03 | added cash in 3 |  |  | 2021
Sodic Eastown EDNC | 2021-02-03 | 15000000 |  | 701510335.37 | 643628946.66 | 57881388.71 | 1074545067 | 5.387% |  |  | 2021-02-03 | added cash in 3 |  |  | 2021
Sodic Eastown EDNC | 2021-03-01 |  | 28256186.4 | 701510335.37 | 671885133.06 | 29625202.31 | 1074545067 | 2.757% |  |  |  | cash out both |  |  | 2021
Sodic Eastown EDNC | 2021-03-04 | 4964135.7 |  | 706474471.07 | 671885133.06 | 34589338.01 | 1074545067 | 3.219% |  |  | 2021-03-04 | added cash in 3 |  |  | 2021
Sodic Eastown EDNC | 2021-03-04 | 2423402.76 |  | 708897873.83 | 671885133.06 | 37012740.77 | 1074545067 | 3.445% |  |  | 2021-03-04 | added cash in 3 |  |  | 2021
Sodic Eastown EDNC | 2021-03-11 | 12000000 |  | 720897873.83 | 671885133.06 | 49012740.77 | 1074545067 | 4.561% |  |  | 2021-03-11 | added cash in 3 |  |  | 2021
Sodic Eastown EDNC | 2021-03-23 | 7672746.63 |  | 728570620.46 | 671885133.06 | 56685487.4 | 1074545067 | 5.275% |  |  | 2021-03-23 | added cash in 3 |  |  | 2021
Sodic Eastown EDNC | 2021-04-04 | 12000000 |  | 740570620.46 | 671885133.06 | 68685487.4 | 1074545067 | 6.392% |  |  | 2021-04-04 | added cash in 3 |  |  | 2021
1900
Marassi Civic Center Pkg 144 | 2018-12-01 |  | 768848.02 | 0 | 768848.02 | -768848.02 | 176420375 | -0.4358% |  |  |  | cash out both |  |  | 2018
Marassi Civic Center Pkg 144 | 2018-12-25 | 24600000 |  | 24600000 | 768848.02 | 23831151.98 | 176420375 | 13.51% |  |  | 2018-12-25 | added cash in 3 |  |  | 2018
Marassi Civic Center Pkg 144 | 2019-01-01 |  | 14944297.11 | 24600000 | 15713145.13 | 8886854.87 | 176420375 | 5.037% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-02-01 |  | 10205548.06 | 24600000 | 25918693.19 | -1318693.19 | 176420375 | -0.7475% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-02-13 | 2532120.6 |  | 27132120.6 | 25918693.19 | 1213427.41 | 176420375 | 0.6878% |  |  | 2019-02-13 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-01 |  | 15866046.55 | 27132120.6 | 41784739.74 | -14652619.14 | 176420375 | -8.306% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-04 | 6189125.05 |  | 33321245.65 | 41784739.74 | -8463494.09 | 176420375 | -4.797% |  |  | 2019-03-04 | added 1 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-14 | 6887377.01 |  | 40208622.66 | 41784739.74 | -1576117.08 | 176420375 | -0.8934% |  |  | 2019-03-14 | added 1 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-14 | 7206339.7 |  | 47414962.36 | 41784739.74 | 5630222.62 | 176420375 | 3.191% |  |  | 2019-03-14 | added 1 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-14 | 6487337.01 |  | 53902299.37 | 41784739.74 | 12117559.63 | 176420375 | 6.869% |  |  | 2019-03-14 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-17 | 7206339.73 |  | 61108639.1 | 41784739.74 | 19323899.36 | 176420375 | 10.95% |  |  | 2019-03-17 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-26 | 216614.52 |  | 61325253.62 | 41784739.74 | 19540513.88 | 176420375 | 11.08% |  |  | 2019-03-26 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-03-26 | 14929468.44 |  | 76254722.06 | 41784739.74 | 34469982.32 | 176420375 | 19.54% |  |  | 2019-03-26 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-04-01 |  | 13359565.12 | 76254722.06 | 55144304.86 | 21110417.2 | 176420375 | 11.97% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-05-01 |  | 18380053.23 | 76254722.06 | 73524358.09 | 2730363.97 | 176420375 | 1.548% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-05-07 | 12477244.23 |  | 88731966.29 | 73524358.09 | 15207608.2 | 176420375 | 8.62% |  |  | 2019-05-07 | added 1 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-05-16 | 8906660.63 |  | 97638626.92 | 73524358.09 | 24114268.83 | 176420375 | 13.67% |  |  | 2019-05-16 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-05-26 | 9782161.34 |  | 107420788.26 | 73524358.09 | 33896430.17 | 176420375 | 19.21% |  |  | 2019-05-26 | added 1 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-06-01 |  | 9275864.62 | 107420788.26 | 82800222.71 | 24620565.55 | 176420375 | 13.96% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-06-03 | 10000000 |  | 117420788.26 | 82800222.71 | 34620565.55 | 176420375 | 19.62% |  |  | 2019-06-03 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-06-17 | 1074114.43 |  | 118494902.69 | 82800222.71 | 35694679.98 | 176420375 | 20.23% |  |  | 2019-06-17 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-07-01 |  | 7248897.82 | 118494902.69 | 90049120.53 | 28445782.16 | 176420375 | 16.12% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-07-25 | 7386054.95 |  | 125880957.64 | 90049120.53 | 35831837.11 | 176420375 | 20.31% |  |  | 2019-07-25 | added 1 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-08-01 |  | 10432654.92 | 125880957.64 | 100481775.45 | 25399182.19 | 176420375 | 14.4% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-09-01 |  | 1936980.78 | 125880957.64 | 102418756.23 | 23462201.41 | 176420375 | 13.3% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-10-01 |  | 3568247.4 | 125880957.64 | 105987003.63 | 19893954.01 | 176420375 | 11.28% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-10-07 | 4748411.06 |  | 130629368.7 | 105987003.63 | 24642365.07 | 176420375 | 13.97% |  |  | 2019-10-07 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-10-07 | 506192.12 |  | 131135560.82 | 105987003.63 | 25148557.19 | 176420375 | 14.25% |  |  | 2019-10-07 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-10-16 | 687983.17 |  | 131823543.99 | 105987003.63 | 25836540.36 | 176420375 | 14.64% |  |  | 2019-10-16 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-10-28 | 15000000 |  | 146823543.99 | 105987003.63 | 40836540.36 | 176420375 | 23.15% |  |  | 2019-10-28 | added cash in 3 |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-11-01 |  | 1814760.87 | 146823543.99 | 107801764.5 | 39021779.49 | 176420375 | 22.12% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2019-12-01 |  | 56564764.01 | 146823543.99 | 164366528.51 | -17542984.52 | 176420375 | -9.944% |  |  |  | cash out both |  |  | 2019
Marassi Civic Center Pkg 144 | 2020-01-01 |  | 1230549.33 | 146823543.99 | 165597077.84 | -18773533.85 | 176420375 | -10.64% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-01-06 | 6073691.31 |  | 152897235.3 | 165597077.84 | -12699842.54 | 176420375 | -7.199% |  |  | 2020-01-06 | added 1 |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-01-20 | 2262789.43 |  | 155160024.73 | 165597077.84 | -10437053.11 | 176420375 | -5.916% |  |  | 2020-01-20 | added cash in 3 |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-02-01 |  | 2172252.68 | 155160024.73 | 167769330.52 | -12609305.79 | 176420375 | -7.147% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-03-01 |  | 1461175.27 | 155160024.73 | 169230505.79 | -14070481.06 | 176420375 | -7.976% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-03-09 | 1430834.93 |  | 156590859.66 | 169230505.79 | -12639646.13 | 176420375 | -7.165% |  |  | 2020-03-09 | added 1 |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-03-16 | 10173240.83 |  | 166764100.49 | 169230505.79 | -2466405.3 | 176420375 | -1.398% |  |  | 2020-03-16 | added 1 |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-04-01 |  | 306967.18 | 166764100.49 | 169537472.97 | -2773372.48 | 176420375 | -1.572% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-04-29 | 596740.76 |  | 167360841.25 | 169537472.97 | -2176631.72 | 176420375 | -1.234% |  |  | 2020-04-29 | added 1 |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-05-01 |  | 1259466.53 | 167360841.25 | 170796939.5 | -3436098.25 | 176420375 | -1.948% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-06-01 |  | 1078335.43 | 167360841.25 | 171875274.93 | -4514433.68 | 176420375 | -2.559% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-07-01 |  | 1137069.85 | 167360841.25 | 173012344.78 | -5651503.53 | 176420375 | -3.203% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-08-01 |  | 959078.26 | 167360841.25 | 173971423.04 | -6610581.79 | 176420375 | -3.747% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-09-01 |  | 87312.56 | 167360841.25 | 174058735.6 | -6697894.35 | 176420375 | -3.797% |  |  |  | cash out both |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-09-07 | 342218.65 |  | 167703059.9 | 174058735.6 | -6355675.7 | 176420375 | -3.603% |  |  | 2020-09-07 | added cash in 3 |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-10-01 |  | 675261.54 | 167703059.9 | 174733997.14 | -7030937.24 | 176420375 | -3.985% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-11-01 |  | 318165.1 | 167703059.9 | 175052162.24 | -7349102.34 | 176420375 | -4.166% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Marassi Civic Center Pkg 144 | 2020-12-01 |  | 108188.81 | 167703059.9 | 175160351.05 | -7457291.15 | 176420375 | -4.227% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Marassi Civic Center Pkg 144 | 2021-01-01 |  | 343308.89 | 167703059.9 | 175503659.94 | -7800600.04 | 176420375 | -4.422% |  |  |  | cash out both |  |  | 2021
Marassi Civic Center Pkg 144 | 2021-02-01 |  | 67550 | 167703059.9 | 175571209.94 | -7868150.04 | 176420375 | -4.46% |  |  |  | cash out both |  |  | 2021
Marassi Civic Center Pkg 144 | 2021-02-03 | 9960243.27 |  | 177663303.17 | 175571209.94 | 2092093.23 | 176420375 | 1.186% |  |  | 2021-02-03 | added cash in 3 |  |  | 2021
Marassi Civic Center Pkg 144 | 2021-03-01 |  | 818169.05 | 177663303.17 | 176389378.99 | 1273924.18 | 176420375 | 0.7221% |  |  |  | cash out both |  |  | 2021
1900
DPW Sokhna Dubai Port | 2018-11-01 |  | 6250 | 0 | 6250 | -6250 | 1633315425 | -0.0003827% |  |  |  | cash out both |  |  | 2018
DPW Sokhna Dubai Port | 2018-12-01 |  | 1558519.47 | 0 | 1564769.47 | -1564769.47 | 1633315425 | -0.0958% |  |  |  | cash out both |  |  | 2018
DPW Sokhna Dubai Port | 2019-01-01 |  | 2323205.22 | 0 | 3887974.69 | -3887974.69 | 1633315425 | -0.238% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-01-29 | 81563831.8 |  | 81563831.8 | 3887974.69 | 77675857.11 | 1633315425 | 4.756% |  |  | 2019-01-29 | added cash in 3 |  |  | 2019
DPW Sokhna Dubai Port | 2019-01-29 | 80000000 |  | 161563831.8 | 3887974.69 | 157675857.11 | 1633315425 | 9.654% |  |  | 2019-01-29 | added cash in 3 |  |  | 2019
DPW Sokhna Dubai Port | 2019-02-01 |  | 5181623.85 | 161563831.8 | 9069598.54 | 152494233.26 | 1633315425 | 9.336% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-03-01 |  | 22124584.32 | 161563831.8 | 31194182.86 | 130369648.94 | 1633315425 | 7.982% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-03-13 | 15998139 |  | 177561970.8 | 31194182.86 | 146367787.94 | 1633315425 | 8.961% |  |  | 2019-03-13 | added cash in 3 |  |  | 2019
DPW Sokhna Dubai Port | 2019-04-01 |  | 13354736.56 | 177561970.8 | 44548919.42 | 133013051.38 | 1633315425 | 8.144% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-04-15 | 18062199.23 |  | 195624170.03 | 44548919.42 | 151075250.61 | 1633315425 | 9.25% |  |  | 2019-04-15 | added 1 |  |  | 2019
DPW Sokhna Dubai Port | 2019-05-01 |  | 7139997.48 | 195624170.03 | 51688916.9 | 143935253.13 | 1633315425 | 8.812% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-05-29 | 15357944.03 |  | 210982114.06 | 51688916.9 | 159293197.16 | 1633315425 | 9.753% |  |  | 2019-05-29 | added cash in 3 |  |  | 2019
DPW Sokhna Dubai Port | 2019-06-01 |  | 17260686.74 | 210982114.06 | 68949603.64 | 142032510.42 | 1633315425 | 8.696% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-07-01 |  | 29860309.8 | 210982114.06 | 98809913.44 | 112172200.62 | 1633315425 | 6.868% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-07-17 | 27940477.28 |  | 238922591.34 | 98809913.44 | 140112677.9 | 1633315425 | 8.578% |  |  | 2019-07-17 | added 1 |  |  | 2019
DPW Sokhna Dubai Port | 2019-08-01 |  | 21052019.15 | 238922591.34 | 119861932.59 | 119060658.75 | 1633315425 | 7.29% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-08-05 | 13161622.85 |  | 252084214.19 | 119861932.59 | 132222281.6 | 1633315425 | 8.095% |  |  | 2019-08-05 | added 1 |  |  | 2019
DPW Sokhna Dubai Port | 2019-09-01 |  | 32814557.43 | 252084214.19 | 152676490.02 | 99407724.17 | 1633315425 | 6.086% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-09-09 | 24492163.72 |  | 276576377.91 | 152676490.02 | 123899887.89 | 1633315425 | 7.586% |  |  | 2019-09-09 | added 1 |  |  | 2019
DPW Sokhna Dubai Port | 2019-10-01 |  | 59773701.22 | 276576377.91 | 212450191.24 | 64126186.67 | 1633315425 | 3.926% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-10-07 | 29974844.16 |  | 306551222.07 | 212450191.24 | 94101030.83 | 1633315425 | 5.761% |  |  | 2019-10-07 | added 1 |  |  | 2019
DPW Sokhna Dubai Port | 2019-10-31 | 29128813.98 |  | 335680036.05 | 212450191.24 | 123229844.81 | 1633315425 | 7.545% |  |  | 2019-10-31 | added cash in 3 |  |  | 2019
DPW Sokhna Dubai Port | 2019-11-01 |  | 61414500.84 | 335680036.05 | 273864692.08 | 61815343.97 | 1633315425 | 3.785% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-12-01 |  | 84767956.57 | 335680036.05 | 358632648.65 | -22952612.6 | 1633315425 | -1.405% |  |  |  | cash out both |  |  | 2019
DPW Sokhna Dubai Port | 2019-12-08 | 40031882.73 |  | 375711918.78 | 358632648.65 | 17079270.13 | 1633315425 | 1.046% |  |  | 2019-12-08 | added 1 |  |  | 2019
DPW Sokhna Dubai Port | 2020-01-01 |  | 64410602 | 375711918.78 | 423043250.65 | -47331331.87 | 1633315425 | -2.898% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-01-13 | 66994289.3 |  | 442706208.08 | 423043250.65 | 19662957.43 | 1633315425 | 1.204% |  |  | 2020-01-13 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-01-29 | 75494532.33 |  | 518200740.41 | 423043250.65 | 95157489.76 | 1633315425 | 5.826% |  |  | 2020-01-29 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-02-01 |  | 67384522.12 | 518200740.41 | 490427772.77 | 27772967.64 | 1633315425 | 1.7% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-03-01 |  | 59590833.37 | 518200740.41 | 550018606.14 | -31817865.73 | 1633315425 | -1.948% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-03-04 | 59999695.78 |  | 578200436.19 | 550018606.14 | 28181830.05 | 1633315425 | 1.725% |  |  | 2020-03-04 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-03-17 | 49675726.5 |  | 627876162.69 | 550018606.14 | 77857556.55 | 1633315425 | 4.767% |  |  | 2020-03-17 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-04-01 |  | 31023546 | 627876162.69 | 581042152.14 | 46834010.55 | 1633315425 | 2.867% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-04-16 | 46089743 |  | 673965905.69 | 581042152.14 | 92923753.55 | 1633315425 | 5.689% |  |  | 2020-04-16 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-05-01 |  | 56700638.34 | 673965905.69 | 637742790.48 | 36223115.21 | 1633315425 | 2.218% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-05-07 | 46089743 |  | 720055648.69 | 637742790.48 | 82312858.21 | 1633315425 | 5.04% |  |  | 2020-05-07 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-05-17 | 52189292.94 |  | 772244941.63 | 637742790.48 | 134502151.15 | 1633315425 | 8.235% |  |  | 2020-05-17 | added cash in 3 |  |  | 2020
DPW Sokhna Dubai Port | 2020-06-01 |  | 90026395.45 | 772244941.63 | 727769185.93 | 44475755.7 | 1633315425 | 2.723% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-06-07 | 52189292.94 |  | 824434234.57 | 727769185.93 | 96665048.64 | 1633315425 | 5.918% |  |  | 2020-06-07 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-06-23 | 81940298.01 |  | 906374532.58 | 727769185.93 | 178605346.65 | 1633315425 | 10.94% |  |  | 2020-06-23 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-07-01 |  | 43160587.28 | 906374532.58 | 770929773.21 | 135444759.37 | 1633315425 | 8.293% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-07-15 | 63998840.71 |  | 970373373.29 | 770929773.21 | 199443600.08 | 1633315425 | 12.21% |  |  | 2020-07-15 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-08-01 |  | 18603231.7 | 970373373.29 | 789533004.91 | 180840368.38 | 1633315425 | 11.07% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-08-16 | 41776446.85 |  | 1012149820.14 | 789533004.91 | 222616815.23 | 1633315425 | 13.63% |  |  | 2020-08-16 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-09-01 |  | 51842829.28 | 1012149820.14 | 841375834.19 | 170773985.95 | 1633315425 | 10.46% |  |  |  | cash out both |  |  | 2020
DPW Sokhna Dubai Port | 2020-09-17 | 44310014.32 |  | 1056459834.46 | 841375834.19 | 215084000.27 | 1633315425 | 13.17% |  |  | 2020-09-17 | added cash in 3 |  |  | 2020
DPW Sokhna Dubai Port | 2020-10-01 |  | 21431140.62 | 1056459834.46 | 862806974.81 | 193652859.65 | 1633315425 | 11.86% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
DPW Sokhna Dubai Port | 2020-10-15 | 25431108.58 |  | 1081890943.04 | 862806974.81 | 219083968.23 | 1633315425 | 13.41% |  |  | 2020-10-15 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2020-11-01 |  | 33745292.9 | 1081890943.04 | 896552267.71 | 185338675.33 | 1633315425 | 11.35% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
DPW Sokhna Dubai Port | 2020-11-15 | 31817254.2 |  | 1113708197.24 | 896552267.71 | 217155929.53 | 1633315425 | 13.3% |  |  | 2020-11-15 | added cash in 3 |  |  | 2020
DPW Sokhna Dubai Port | 2020-12-01 |  | 34025388.2 | 1113708197.24 | 930577655.91 | 183130541.33 | 1633315425 | 11.21% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
DPW Sokhna Dubai Port | 2020-12-13 | 25746407.39 |  | 1139454604.63 | 930577655.91 | 208876948.72 | 1633315425 | 12.79% |  |  | 2020-12-13 | added 1 |  |  | 2020
DPW Sokhna Dubai Port | 2021-01-01 |  | 25918366.95 | 1139454604.63 | 956496022.86 | 182958581.77 | 1633315425 | 11.2% |  |  |  | cash out both |  |  | 2021
DPW Sokhna Dubai Port | 2021-01-21 | 17720371.71 |  | 1157174976.34 | 956496022.86 | 200678953.48 | 1633315425 | 12.29% |  |  | 2021-01-21 | added 1 |  |  | 2021
DPW Sokhna Dubai Port | 2021-02-01 |  | 20301696.69 | 1157174976.34 | 976797719.55 | 180377256.79 | 1633315425 | 11.04% |  |  |  | cash out both |  |  | 2021
DPW Sokhna Dubai Port | 2021-02-15 | 26545255.12 |  | 1183720231.46 | 976797719.55 | 206922511.91 | 1633315425 | 12.67% |  |  | 2021-02-15 | added 1 |  |  | 2021
DPW Sokhna Dubai Port | 2021-03-01 |  | 14383975.04 | 1183720231.46 | 991181694.59 | 192538536.87 | 1633315425 | 11.79% |  |  |  | cash out both |  |  | 2021
DPW Sokhna Dubai Port | 2021-03-18 | 20867275.72 |  | 1204587507.18 | 991181694.59 | 213405812.59 | 1633315425 | 13.07% |  |  | 2021-03-18 | added cash in 3 |  |  | 2021
DPW Sokhna Dubai Port | 2021-04-19 | 10313601.64 |  | 1214901108.82 | 991181694.59 | 223719414.23 | 1633315425 | 13.7% |  |  | 2021-04-19 | added cash in 3 |  |  | 2021
1900
Slope Stablization PKG 101 | 2018-12-01 |  | 48446.71 | 0 | 48446.71 | -48446.71 | 52028085.7143 | -0.09312% |  |  |  | cash out both |  |  | 2018
Slope Stablization PKG 101 | 2019-01-01 |  | 1037572.3 | 0 | 1086019.01 | -1086019.01 | 52028085.7143 | -2.087% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-01-06 | 8723141 |  | 8723141 | 1086019.01 | 7637121.99 | 52028085.7143 | 14.68% |  |  | 2019-01-06 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-02-01 |  | 696376.21 | 8723141 | 1782395.22 | 6940745.78 | 52028085.7143 | 13.34% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-03-01 |  | 1325727.57 | 8723141 | 3108122.79 | 5615018.21 | 52028085.7143 | 10.79% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-03-12 | 1029594.82 |  | 9752735.82 | 3108122.79 | 6644613.03 | 52028085.7143 | 12.77% |  |  | 2019-03-12 | added 1 |  |  | 2019
Slope Stablization PKG 101 | 2019-04-01 |  | 1705310.36 | 9752735.82 | 4813433.15 | 4939302.67 | 52028085.7143 | 9.494% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-04-18 | 2222206.65 |  | 11974942.47 | 4813433.15 | 7161509.32 | 52028085.7143 | 13.76% |  |  | 2019-04-18 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-05-01 |  | 2051607.17 | 11974942.47 | 6865040.32 | 5109902.15 | 52028085.7143 | 9.821% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-05-30 | 2246109.51 |  | 14221051.98 | 6865040.32 | 7356011.66 | 52028085.7143 | 14.14% |  |  | 2019-05-30 | added 1 |  |  | 2019
Slope Stablization PKG 101 | 2019-06-01 |  | 1413088.72 | 14221051.98 | 8278129.04 | 5942922.94 | 52028085.7143 | 11.42% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-06-24 | 2512749.68 |  | 16733801.66 | 8278129.04 | 8455672.62 | 52028085.7143 | 16.25% |  |  | 2019-06-24 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-07-01 |  | 1252532.38 | 16733801.66 | 9530661.42 | 7203140.24 | 52028085.7143 | 13.84% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-08-01 |  | 1801484.02 | 16733801.66 | 11332145.44 | 5401656.22 | 52028085.7143 | 10.38% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-08-07 | 2051541.97 |  | 18785343.63 | 11332145.44 | 7453198.19 | 52028085.7143 | 14.33% |  |  | 2019-08-07 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-09-01 |  | 1310343.71 | 18785343.63 | 12642489.15 | 6142854.48 | 52028085.7143 | 11.81% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-09-19 | 1828569.06 |  | 20613912.69 | 12642489.15 | 7971423.54 | 52028085.7143 | 15.32% |  |  | 2019-09-19 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-09-19 | 5263141.46 |  | 25877054.15 | 12642489.15 | 13234565 | 52028085.7143 | 25.44% |  |  | 2019-09-19 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-09-23 | 1988552.05 |  | 27865606.2 | 12642489.15 | 15223117.05 | 52028085.7143 | 29.26% |  |  | 2019-09-23 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-10-01 |  | 2243161.77 | 27865606.2 | 14885650.92 | 12979955.28 | 52028085.7143 | 24.95% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-10-28 | 1824097.56 |  | 29689703.76 | 14885650.92 | 14804052.84 | 52028085.7143 | 28.45% |  |  | 2019-10-28 | added 1 |  |  | 2019
Slope Stablization PKG 101 | 2019-11-01 |  | 1399641.5 | 29689703.76 | 16285292.42 | 13404411.34 | 52028085.7143 | 25.76% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2019-11-25 | 2104893.84 |  | 31794597.6 | 16285292.42 | 15509305.18 | 52028085.7143 | 29.81% |  |  | 2019-11-25 | added cash in 3 |  |  | 2019
Slope Stablization PKG 101 | 2019-12-01 |  | 3511320.37 | 31794597.6 | 19796612.79 | 11997984.81 | 52028085.7143 | 23.06% |  |  |  | cash out both |  |  | 2019
Slope Stablization PKG 101 | 2020-01-01 |  | 876489.71 | 31794597.6 | 20673102.5 | 11121495.1 | 52028085.7143 | 21.38% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-01-06 | 1424816.56 |  | 33219414.16 | 20673102.5 | 12546311.66 | 52028085.7143 | 24.11% |  |  | 2020-01-06 | added 1 |  |  | 2020
Slope Stablization PKG 101 | 2020-02-01 |  | 1300356.68 | 33219414.16 | 21973459.18 | 11245954.98 | 52028085.7143 | 21.62% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-02-17 | 1976416.89 |  | 35195831.05 | 21973459.18 | 13222371.87 | 52028085.7143 | 25.41% |  |  | 2020-02-17 | added 1 |  |  | 2020
Slope Stablization PKG 101 | 2020-03-01 |  | 677357.53 | 35195831.05 | 22650816.71 | 12545014.34 | 52028085.7143 | 24.11% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-03-23 | 1709961.04 |  | 36905792.09 | 22650816.71 | 14254975.38 | 52028085.7143 | 27.4% |  |  | 2020-03-23 | added 1 |  |  | 2020
Slope Stablization PKG 101 | 2020-04-01 |  | 797488.27 | 36905792.09 | 23448304.98 | 13457487.11 | 52028085.7143 | 25.87% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-05-01 |  | 1451291.03 | 36905792.09 | 24899596.01 | 12006196.08 | 52028085.7143 | 23.08% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-05-04 | 1146998.21 |  | 38052790.3 | 24899596.01 | 13153194.29 | 52028085.7143 | 25.28% |  |  | 2020-05-04 | added 1 |  |  | 2020
Slope Stablization PKG 101 | 2020-06-01 |  | 268243.77 | 38052790.3 | 25167839.78 | 12884950.52 | 52028085.7143 | 24.77% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-06-10 | 1343055.66 |  | 39395845.96 | 25167839.78 | 14228006.18 | 52028085.7143 | 27.35% |  |  | 2020-06-10 | added cash in 3 |  |  | 2020
Slope Stablization PKG 101 | 2020-07-01 |  | 575024.75 | 39395845.96 | 25742864.53 | 13652981.43 | 52028085.7143 | 26.24% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-08-01 |  | 565202.11 | 39395845.96 | 26308066.64 | 13087779.32 | 52028085.7143 | 25.16% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-09-01 |  | 268521.56 | 39395845.96 | 26576588.2 | 12819257.76 | 52028085.7143 | 24.64% |  |  |  | cash out both |  |  | 2020
Slope Stablization PKG 101 | 2020-10-01 |  | 2103262.78 | 39395845.96 | 28679850.98 | 10715994.98 | 52028085.7143 | 20.6% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Slope Stablization PKG 101 | 2020-10-07 | 191421.72 |  | 39587267.68 | 28679850.98 | 10907416.7 | 52028085.7143 | 20.96% |  |  | 2020-10-07 | added cash in 3 |  |  | 2020
Slope Stablization PKG 101 | 2020-11-01 |  | 711830.03 | 39587267.68 | 29391681.01 | 10195586.67 | 52028085.7143 | 19.6% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Slope Stablization PKG 101 | 2020-11-16 | 877190.31 |  | 40464457.99 | 29391681.01 | 11072776.98 | 52028085.7143 | 21.28% |  |  | 2020-11-16 | added cash in 3 |  |  | 2020
Slope Stablization PKG 101 | 2020-12-01 |  | 599150.03 | 40464457.99 | 29990831.04 | 10473626.95 | 52028085.7143 | 20.13% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Slope Stablization PKG 101 | 2021-01-01 |  | 860087.45 | 40464457.99 | 30850918.49 | 9613539.5 | 52028085.7143 | 18.48% |  |  |  | cash out both |  |  | 2021
Slope Stablization PKG 101 | 2021-01-20 | 303853.8 |  | 40768311.79 | 30850918.49 | 9917393.3 | 52028085.7143 | 19.06% |  |  | 2021-01-20 | added cash in 3 |  |  | 2021
Slope Stablization PKG 101 | 2021-02-01 |  | 107706.62 | 40768311.79 | 30958625.11 | 9809686.68 | 52028085.7143 | 18.85% |  |  |  | cash out both |  |  | 2021
Slope Stablization PKG 101 | 2021-02-22 | 693232.98 |  | 41461544.77 | 30958625.11 | 10502919.66 | 52028085.7143 | 20.19% |  |  | 2021-02-22 | added cash in 3 |  |  | 2021
Slope Stablization PKG 101 | 2021-03-01 |  | 418036.32 | 41461544.77 | 31376661.43 | 10084883.34 | 52028085.7143 | 19.38% |  |  |  | cash out both |  |  | 2021
Slope Stablization PKG 101 | 2021-03-08 | 866491 |  | 42328035.77 | 31376661.43 | 10951374.34 | 52028085.7143 | 21.05% |  |  | 2021-03-08 | added 1 |  |  | 2021
1900
Elco Steel Substation | 2018-07-11 | 6647052.2 |  | 6647052.2 | 0 | 6647052.2 | 32341773 | 20.55% |  |  | 2018-07-11 | added cash in 3 |  |  | 2018
Elco Steel Substation | 2018-09-18 | 1160599.12 |  | 7807651.32 | 0 | 7807651.32 | 32341773 | 24.14% |  |  | 2018-09-18 | added 1 |  |  | 2018
Elco Steel Substation | 2018-10-18 | 1834172.07 |  | 9641823.39 | 0 | 9641823.39 | 32341773 | 29.81% |  |  | 2018-10-18 | added 1 |  |  | 2018
Elco Steel Substation | 2018-11-21 | 1268627.7 |  | 10910451.09 | 0 | 10910451.09 | 32341773 | 33.73% |  |  | 2018-11-21 | added cash in 3 |  |  | 2018
Elco Steel Substation | 2018-11-21 | 3991290.99 |  | 14901742.08 | 0 | 14901742.08 | 32341773 | 46.08% |  |  | 2018-11-21 | added cash in 3 |  |  | 2018
Elco Steel Substation | 2019-01-01 |  | 3179.66 | 14901742.08 | 3179.66 | 14898562.42 | 32341773 | 46.07% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-02-01 |  | 328500 | 14901742.08 | 331679.66 | 14570062.42 | 32341773 | 45.05% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-02-17 | 4827680.45 |  | 19729422.53 | 331679.66 | 19397742.87 | 32341773 | 59.98% |  |  | 2019-02-17 | added cash in 3 |  |  | 2019
Elco Steel Substation | 2019-03-01 |  | 594594.84 | 19729422.53 | 926274.5 | 18803148.03 | 32341773 | 58.14% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-04-01 |  | 231187.27 | 19729422.53 | 1157461.77 | 18571960.76 | 32341773 | 57.42% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-04-02 | 1829713.21 |  | 21559135.74 | 1157461.77 | 20401673.97 | 32341773 | 63.08% |  |  | 2019-04-02 | added 1 |  |  | 2019
Elco Steel Substation | 2019-04-02 | 597560.88 |  | 22156696.62 | 1157461.77 | 20999234.85 | 32341773 | 64.93% |  |  | 2019-04-02 | added cash in 3 |  |  | 2019
Elco Steel Substation | 2019-04-18 | 1314287.28 |  | 23470983.9 | 1157461.77 | 22313522.13 | 32341773 | 68.99% |  |  | 2019-04-18 | added cash in 3 |  |  | 2019
Elco Steel Substation | 2019-05-01 |  | 481662.53 | 23470983.9 | 1639124.3 | 21831859.6 | 32341773 | 67.5% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-06-01 |  | 26135.55 | 23470983.9 | 1665259.85 | 21805724.05 | 32341773 | 67.42% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-06-13 | 480264.83 |  | 23951248.73 | 1665259.85 | 22285988.88 | 32341773 | 68.91% |  |  | 2019-06-13 | added cash in 3 |  |  | 2019
Elco Steel Substation | 2019-06-19 | 3264225.8 |  | 27215474.53 | 1665259.85 | 25550214.68 | 32341773 | 79% |  |  | 2019-06-19 | added 1 |  |  | 2019
Elco Steel Substation | 2019-07-01 |  | 316636.41 | 27215474.53 | 1981896.26 | 25233578.27 | 32341773 | 78.02% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-08-01 |  | 269362.72 | 27215474.53 | 2251258.98 | 24964215.55 | 32341773 | 77.19% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-09-01 |  | 95862.86 | 27215474.53 | 2347121.84 | 24868352.69 | 32341773 | 76.89% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-10-01 |  | 45830.78 | 27215474.53 | 2392952.62 | 24822521.91 | 32341773 | 76.75% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-11-01 |  | 107215.22 | 27215474.53 | 2500167.84 | 24715306.69 | 32341773 | 76.42% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-12-01 |  | 280394.73 | 27215474.53 | 2780562.57 | 24434911.96 | 32341773 | 75.55% |  |  |  | cash out both |  |  | 2019
Elco Steel Substation | 2019-12-26 | 2606365.14 |  | 29821839.67 | 2780562.57 | 27041277.1 | 32341773 | 83.61% |  |  | 2019-12-26 | added cash in 3 |  |  | 2019
Elco Steel Substation | 2020-02-01 |  | 3430.5 | 29821839.67 | 2783993.07 | 27037846.6 | 32341773 | 83.6% |  |  |  | cash out both |  |  | 2020
Elco Steel Substation | 2020-03-01 |  | 11272.85 | 29821839.67 | 2795265.92 | 27026573.75 | 32341773 | 83.57% |  |  |  | cash out both |  |  | 2020
Elco Steel Substation | 2020-04-01 |  | 61562.5 | 29821839.67 | 2856828.42 | 26965011.25 | 32341773 | 83.38% |  |  |  | cash out both |  |  | 2020
Elco Steel Substation | 2020-06-01 |  | 2311.58 | 29821839.67 | 2859140 | 26962699.67 | 32341773 | 83.37% |  |  |  | cash out both |  |  | 2020
Elco Steel Substation | 2020-09-01 |  | 12804.39 | 29821839.67 | 2871944.39 | 26949895.28 | 32341773 | 83.33% |  |  |  | cash out both |  |  | 2020
Elco Steel Substation | 2020-10-25 | 536537.44 |  | 30358377.11 | 2871944.39 | 27486432.72 | 32341773 | 84.99% |  |  | 2020-10-25 | added cash in 3 |  |  | 2020
Elco Steel Substation | 2021-01-05 | 31239.74 |  | 30389616.85 | 2871944.39 | 27517672.46 | 32341773 | 85.08% |  |  | 2021-01-05 | added 1 |  |  | 2021
Elco Steel Substation | 2021-01-05 | 1645603.62 |  | 32035220.47 | 2871944.39 | 29163276.08 | 32341773 | 90.17% |  |  | 2021-01-05 | added cash in 3 |  |  | 2021
1900
Sewab Greenhouse Tunnel | 2019-07-01 |  | 583.1 | 0 | 583.1 | -583.1 | 10957813.825 | -0.005321% |  |  |  | cash out both |  |  | 2019
Sewab Greenhouse Tunnel | 2019-09-01 |  | 2700 | 0 | 3283.1 | -3283.1 | 10957813.825 | -0.02996% |  |  |  | cash out both |  |  | 2019
Sewab Greenhouse Tunnel | 2021-02-15 | 3830500 |  | 3830500 | 3283.1 | 3827216.9 | 10957813.825 | 34.93% |  |  | 2021-02-15 | added 1 |  |  | 2021
1900
Mivida Irrigation Treatment Plant Pkg 140 | 2019-01-01 |  | 56000 | 0 | 56000 | -56000 | 170057475.6641 | -0.03293% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-02-01 |  | 211876.6 | 0 | 267876.6 | -267876.6 | 170057475.6641 | -0.1575% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-02-12 | 15567604.3 |  | 15567604.3 | 267876.6 | 15299727.7 | 170057475.6641 | 8.997% |  |  | 2019-02-12 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-03-01 |  | 334489.19 | 15567604.3 | 602365.79 | 14965238.51 | 170057475.6641 | 8.8% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-04-01 |  | 313433.85 | 15567604.3 | 915799.64 | 14651804.66 | 170057475.6641 | 8.616% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-05-01 |  | 6557727.1 | 15567604.3 | 7473526.74 | 8094077.56 | 170057475.6641 | 4.76% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-06-01 |  | 509544.35 | 15567604.3 | 7983071.09 | 7584533.21 | 170057475.6641 | 4.46% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-06-25 | 7313962.6 |  | 22881566.9 | 7983071.09 | 14898495.81 | 170057475.6641 | 8.761% |  |  | 2019-06-25 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-07-01 |  | 2706618.74 | 22881566.9 | 10689689.83 | 12191877.07 | 170057475.6641 | 7.169% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-07-17 | 2533668.03 |  | 25415234.93 | 10689689.83 | 14725545.1 | 170057475.6641 | 8.659% |  |  | 2019-07-17 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-08-01 |  | 8288612.73 | 25415234.93 | 18978302.56 | 6436932.37 | 170057475.6641 | 3.785% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-08-07 | 2620895.13 |  | 28036130.06 | 18978302.56 | 9057827.5 | 170057475.6641 | 5.326% |  |  | 2019-08-07 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-09-01 |  | 2281984.71 | 28036130.06 | 21260287.27 | 6775842.79 | 170057475.6641 | 3.984% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-10-01 |  | 5749035.93 | 28036130.06 | 27009323.2 | 1026806.86 | 170057475.6641 | 0.6038% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-10-07 | 4070832.4 |  | 32106962.46 | 27009323.2 | 5097639.26 | 170057475.6641 | 2.998% |  |  | 2019-10-07 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-10-16 | 999645.44 |  | 33106607.9 | 27009323.2 | 6097284.7 | 170057475.6641 | 3.585% |  |  | 2019-10-16 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-11-01 |  | 4593575.33 | 33106607.9 | 31602898.53 | 1503709.37 | 170057475.6641 | 0.8842% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-11-06 | 1337507.07 |  | 34444114.97 | 31602898.53 | 2841216.44 | 170057475.6641 | 1.671% |  |  | 2019-11-06 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-12-01 |  | 6273855.73 | 34444114.97 | 37876754.26 | -3432639.29 | 170057475.6641 | -2.019% |  |  |  | cash out both |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2019-12-18 | 10719905.22 |  | 45164020.19 | 37876754.26 | 7287265.93 | 170057475.6641 | 4.285% |  |  | 2019-12-18 | added cash in 3 |  |  | 2019
Mivida Irrigation Treatment Plant Pkg 140 | 2020-01-01 |  | 4920579.14 | 45164020.19 | 42797333.4 | 2366686.79 | 170057475.6641 | 1.392% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-01-20 | 6547225.82 |  | 51711246.01 | 42797333.4 | 8913912.61 | 170057475.6641 | 5.242% |  |  | 2020-01-20 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-02-01 |  | 6394039.9 | 51711246.01 | 49191373.3 | 2519872.71 | 170057475.6641 | 1.482% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-02-17 | 509706.15 |  | 52220952.16 | 49191373.3 | 3029578.86 | 170057475.6641 | 1.782% |  |  | 2020-02-17 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-02-17 | 4740517.55 |  | 56961469.71 | 49191373.3 | 7770096.41 | 170057475.6641 | 4.569% |  |  | 2020-02-17 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-03-01 | 1677431.09 | 2469893.53 | 58638900.8 | 51661266.83 | 6977633.97 | 170057475.6641 | 4.103% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-04-01 | 4559999.09 | 2062038.86 | 63198899.89 | 53723305.69 | 9475594.2 | 170057475.6641 | 5.572% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-05-01 |  | 2856879.89 | 63198899.89 | 56580185.58 | 6618714.31 | 170057475.6641 | 3.892% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-05-20 | 2647674.17 |  | 65846574.06 | 56580185.58 | 9266388.48 | 170057475.6641 | 5.449% |  |  | 2020-05-20 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-06-01 |  | 8260687.53 | 65846574.06 | 64840873.11 | 1005700.95 | 170057475.6641 | 0.5914% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-06-10 | 4687303.44 |  | 70533877.5 | 64840873.11 | 5693004.39 | 170057475.6641 | 3.348% |  |  | 2020-06-10 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-07-01 |  | 4140620.96 | 70533877.5 | 68981494.07 | 1552383.43 | 170057475.6641 | 0.9129% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-07-08 | 1169770.65 |  | 71703648.15 | 68981494.07 | 2722154.08 | 170057475.6641 | 1.601% |  |  | 2020-07-08 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-08-01 |  | 2282257.84 | 71703648.15 | 71263751.91 | 439896.24 | 170057475.6641 | 0.2587% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-08-10 | 7336701.1 |  | 79040349.25 | 71263751.91 | 7776597.34 | 170057475.6641 | 4.573% |  |  | 2020-08-10 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-09-01 | 5668741 | 4720808.76 | 84709090.25 | 75984560.67 | 8724529.58 | 170057475.6641 | 5.13% |  |  |  | cash out both |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-09-21 | 596538.75 |  | 85305629 | 75984560.67 | 9321068.33 | 170057475.6641 | 5.481% |  |  | 2020-09-21 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-09-21 | 10305723.52 |  | 95611352.52 | 75984560.67 | 19626791.85 | 170057475.6641 | 11.54% |  |  | 2020-09-21 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-10-01 |  | 8447138.36 | 95611352.52 | 84431699.03 | 11179653.49 | 170057475.6641 | 6.574% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-10-07 | 10553431.24 |  | 106164783.76 | 84431699.03 | 21733084.73 | 170057475.6641 | 12.78% |  |  | 2020-10-07 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-11-01 |  | 2986773.84 | 106164783.76 | 87418472.87 | 18746310.89 | 170057475.6641 | 11.02% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-11-11 | 908034.47 |  | 107072818.23 | 87418472.87 | 19654345.36 | 170057475.6641 | 11.56% |  |  | 2020-11-11 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-11-23 | 11726998.43 |  | 118799816.66 | 87418472.87 | 31381343.79 | 170057475.6641 | 18.45% |  |  | 2020-11-23 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-12-01 |  | 4583956.46 | 118799816.66 | 92002429.33 | 26797387.33 | 170057475.6641 | 15.76% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2020-12-21 | 3831058.93 |  | 122630875.59 | 92002429.33 | 30628446.26 | 170057475.6641 | 18.01% |  |  | 2020-12-21 | added cash in 3 |  |  | 2020
Mivida Irrigation Treatment Plant Pkg 140 | 2021-01-01 |  | 7433145.89 | 122630875.59 | 99435575.22 | 23195300.37 | 170057475.6641 | 13.64% |  |  |  | cash out both |  |  | 2021
Mivida Irrigation Treatment Plant Pkg 140 | 2021-01-13 | 8885358.62 |  | 131516234.21 | 99435575.22 | 32080658.99 | 170057475.6641 | 18.86% |  |  | 2021-01-13 | added cash in 3 |  |  | 2021
Mivida Irrigation Treatment Plant Pkg 140 | 2021-02-01 | 8185193.83 | 4155145.48 | 139701428.04 | 103590720.7 | 36110707.34 | 170057475.6641 | 21.23% |  |  |  | cash out both |  |  | 2021
Mivida Irrigation Treatment Plant Pkg 140 | 2021-02-03 | 1805452.05 |  | 141506880.09 | 103590720.7 | 37916159.39 | 170057475.6641 | 22.3% |  |  | 2021-02-03 | added cash in 3 |  |  | 2021
Mivida Irrigation Treatment Plant Pkg 140 | 2021-02-22 | 5084359.83 |  | 146591239.92 | 103590720.7 | 43000519.22 | 170057475.6641 | 25.29% |  |  | 2021-02-22 | added cash in 3 |  |  | 2021
Mivida Irrigation Treatment Plant Pkg 140 | 2021-03-01 | 976304.25 | 3547784.23 | 147567544.17 | 107138504.93 | 40429039.24 | 170057475.6641 | 23.77% |  |  |  | cash out both |  |  | 2021
1900
Multi Sports Hall | 2019-01-01 |  | 1495325 | 0 | 1495325 | -1495325 | 1200000000 | -0.1246% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-02-01 |  | 4000 | 0 | 1499325 | -1499325 | 1200000000 | -0.1249% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-03-01 |  | 211739.99 | 0 | 1711064.99 | -1711064.99 | 1200000000 | -0.1426% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-04-01 |  | 129406.81 | 0 | 1840471.8 | -1840471.8 | 1200000000 | -0.1534% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-05-01 |  | 3775416.83 | 0 | 5615888.63 | -5615888.63 | 1200000000 | -0.468% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-06-01 |  | 289602.76 | 0 | 5905491.39 | -5905491.39 | 1200000000 | -0.4921% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-07-01 |  | 3084912.18 | 0 | 8990403.57 | -8990403.57 | 1200000000 | -0.7492% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-08-01 |  | 2841261.96 | 0 | 11831665.53 | -11831665.53 | 1200000000 | -0.986% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-09-01 |  | 2875277.15 | 0 | 14706942.68 | -14706942.68 | 1200000000 | -1.226% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-10-01 |  | 4791235.19 | 0 | 19498177.87 | -19498177.87 | 1200000000 | -1.625% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-11-01 |  | 3705232.81 | 0 | 23203410.68 | -23203410.68 | 1200000000 | -1.934% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-11-24 | 100000000 |  | 100000000 | 23203410.68 | 76796589.32 | 1200000000 | 6.4% |  |  | 2019-11-24 | added cash in 3 |  |  | 2019
Multi Sports Hall | 2019-12-01 |  | 4739401.69 | 100000000 | 27942812.37 | 72057187.63 | 1200000000 | 6.005% |  |  |  | cash out both |  |  | 2019
Multi Sports Hall | 2019-12-31 | 9000000 |  | 109000000 | 27942812.37 | 81057187.63 | 1200000000 | 6.755% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Multi Sports Hall | 2020-01-01 |  | 37418376.17 | 109000000 | 65361188.54 | 43638811.46 | 1200000000 | 3.637% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-02-01 |  | 10471428.61 | 109000000 | 75832617.15 | 33167382.85 | 1200000000 | 2.764% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-03-01 |  | 10933828.52 | 109000000 | 86766445.67 | 22233554.33 | 1200000000 | 1.853% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-04-01 |  | 2101.8 | 109000000 | 86768547.47 | 22231452.53 | 1200000000 | 1.853% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-04-01 |  | 5337499.65 | 109000000 | 92106047.12 | 16893952.88 | 1200000000 | 1.408% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-05-01 |  | 7603723.75 | 109000000 | 99709770.87 | 9290229.13 | 1200000000 | 0.7742% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-05-18 | 99806255 |  | 208806255 | 99709770.87 | 109096484.13 | 1200000000 | 9.091% |  |  | 2020-05-18 | added 1 |  |  | 2020
Multi Sports Hall | 2020-05-21 | 26264795 |  | 235071050 | 99709770.87 | 135361279.13 | 1200000000 | 11.28% |  |  | 2020-05-21 | added 1 |  |  | 2020
Multi Sports Hall | 2020-06-01 |  | 8873309.23 | 235071050 | 108583080.1 | 126487969.9 | 1200000000 | 10.54% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-06-25 | 65551020.25 |  | 300622070.25 | 108583080.1 | 192038990.15 | 1200000000 | 16% |  |  | 2020-06-25 | added cash in 3 |  |  | 2020
Multi Sports Hall | 2020-07-01 |  | 26177319.93 | 300622070.25 | 134760400.03 | 165861670.22 | 1200000000 | 13.82% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-07-27 | 105 |  | 300622175.25 | 134760400.03 | 165861775.22 | 1200000000 | 13.82% |  |  | 2020-07-27 | added cash in 3 |  |  | 2020
Multi Sports Hall | 2020-07-28 | 105 |  | 300622280.25 | 134760400.03 | 165861880.22 | 1200000000 | 13.82% |  |  | 2020-07-28 | added 1 |  |  | 2020
Multi Sports Hall | 2020-08-01 |  | 9802453.68 | 300622280.25 | 144562853.71 | 156059426.54 | 1200000000 | 13% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-09-01 |  | 22460409.51 | 300622280.25 | 167023263.22 | 133599017.03 | 1200000000 | 11.13% |  |  |  | cash out both |  |  | 2020
Multi Sports Hall | 2020-09-27 | 13887855 |  | 314510135.25 | 167023263.22 | 147486872.03 | 1200000000 | 12.29% |  |  | 2020-09-27 | added 1 |  |  | 2020
Multi Sports Hall | 2020-09-30 | 15050340 |  | 329560475.25 | 167023263.22 | 162537212.03 | 1200000000 | 13.54% |  |  | 2020-09-30 | added cash in 3 |  |  | 2020
Multi Sports Hall | 2020-10-01 |  | 32447008.16 | 329560475.25 | 199470271.38 | 130090203.87 | 1200000000 | 10.84% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Multi Sports Hall | 2020-10-04 | 124999995 |  | 454560470.25 | 199470271.38 | 255090198.87 | 1200000000 | 21.26% |  |  | 2020-10-04 | added cash in 3 |  |  | 2020
Multi Sports Hall | 2020-11-01 |  | 19519706.45 | 454560470.25 | 218989977.83 | 235570492.42 | 1200000000 | 19.63% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Multi Sports Hall | 2020-12-01 |  | 25779271.03 | 454560470.25 | 244769248.86 | 209791221.39 | 1200000000 | 17.48% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Multi Sports Hall | 2021-01-01 |  | 32039547.67 | 454560470.25 | 276808796.53 | 177751673.72 | 1200000000 | 14.81% |  |  |  | cash out both |  |  | 2021
Multi Sports Hall | 2021-01-31 | 9493334.75 |  | 464053805 | 276808796.53 | 187245008.47 | 1200000000 | 15.6% |  |  | 2021-01-31 | added cash in 3 |  |  | 2021
Multi Sports Hall | 2021-02-01 |  | 20926874.29 | 464053805 | 297735670.82 | 166318134.18 | 1200000000 | 13.86% |  |  |  | cash out both |  |  | 2021
Multi Sports Hall | 2021-02-28 | 2493330 |  | 466547135 | 297735670.82 | 168811464.18 | 1200000000 | 14.07% |  |  | 2021-02-28 | added 1 |  |  | 2021
Multi Sports Hall | 2021-03-01 |  | 12228252.34 | 466547135 | 309963923.16 | 156583211.84 | 1200000000 | 13.05% |  |  |  | cash out both |  |  | 2021
1900
Emergency Bridge | 2019-03-01 |  | 146287.5 | 0 | 146287.5 | -146287.5 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-04-01 |  | 63150 | 0 | 209437.5 | -209437.5 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-05-01 |  | 33981.68 | 0 | 243419.18 | -243419.18 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-06-01 |  | 24815 | 0 | 268234.18 | -268234.18 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-07-01 |  | 49728.25 | 0 | 317962.43 | -317962.43 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-08-01 |  | 425475.3 | 0 | 743437.73 | -743437.73 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-09-01 |  | 84583.07 | 0 | 828020.8 | -828020.8 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-10-01 |  | 151950.83 | 0 | 979971.63 | -979971.63 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-11-01 |  | 185224.15 | 0 | 1165195.78 | -1165195.78 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2019-12-01 |  | 98229.5 | 0 | 1263425.28 | -1263425.28 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Emergency Bridge | 2020-01-01 |  | 442135.62 | 0 | 1705560.9 | -1705560.9 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Emergency Bridge | 2020-02-01 |  | 132311.45 | 0 | 1837872.35 | -1837872.35 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Emergency Bridge | 2020-03-01 |  | 4835 | 0 | 1842707.35 | -1842707.35 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Emergency Bridge | 2020-04-01 |  | 21410.04 | 0 | 1864117.39 | -1864117.39 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Emergency Bridge | 2020-06-01 |  | 43208.09 | 0 | 1907325.48 | -1907325.48 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Emergency Bridge | 2020-10-01 |  | 1280.2 | 0 | 1908605.68 | -1908605.68 | #N/A | #N/A |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Emergency Bridge | 2021-01-01 |  | 1538.32 | 0 | 1910144 | -1910144 | #N/A | #N/A |  |  |  | cash out both |  |  | 2021
1900
Pyramid El Remayah Tunnel | 2019-03-01 |  | 42000 | 0 | 42000 | -42000 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-04-01 |  | 37900 | 0 | 79900 | -79900 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-05-01 |  | 17300 | 0 | 97200 | -97200 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-06-01 |  | 34500 | 0 | 131700 | -131700 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-07-01 |  | 114209 | 0 | 245909 | -245909 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-08-01 |  | 106690 | 0 | 352599 | -352599 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-09-01 |  | 140914.62 | 0 | 493513.62 | -493513.62 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-10-01 |  | 74705.35 | 0 | 568218.97 | -568218.97 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-11-01 |  | 33095 | 0 | 601313.97 | -601313.97 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2019-12-01 |  | 123609.76 | 0 | 724923.73 | -724923.73 | #N/A | #N/A |  |  |  | cash out both |  |  | 2019
Pyramid El Remayah Tunnel | 2020-01-01 |  | 76710.62 | 0 | 801634.35 | -801634.35 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Pyramid El Remayah Tunnel | 2020-02-01 |  | 2619 | 0 | 804253.35 | -804253.35 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Pyramid El Remayah Tunnel | 2020-03-01 |  | 10000 | 0 | 814253.35 | -814253.35 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Pyramid El Remayah Tunnel | 2020-04-01 |  | 6666 | 0 | 820919.35 | -820919.35 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Pyramid El Remayah Tunnel | 2020-07-01 |  | 8270 | 0 | 829189.35 | -829189.35 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
1900
EGAT | 2019-03-11 | 22000000 |  | 22000000 | 0 | 22000000 | 65831906 | 33.42% |  |  | 2019-09-06 | added 1 |  |  | 2019
EGAT | 2019-04-21 | 20624356.65 |  | 42624356.65 | 0 | 42624356.65 | 65831906 | 64.75% |  |  | 2019-09-06 | added 1 |  |  | 2019
EGAT | 2019-09-06 | 9050238.73 |  | 51674595.38 | 0 | 51674595.38 | 65831906 | 78.49% |  |  | 2019-09-06 | added 1 |  |  | 2019
EGAT | 2020-01-16 | 292862 |  | 51967457.38 | 0 | 51967457.38 | 65831906 | 78.94% |  |  | 2020-01-16 | added 1 |  |  | 2020
EGAT | 2020-01-16 | 457138.81 |  | 52424596.19 | 0 | 52424596.19 | 65831906 | 79.63% |  |  | 2020-01-16 | added 1 |  |  | 2020
EGAT | 2020-03-23 | 500000 |  | 52924596.19 | 0 | 52924596.19 | 65831906 | 80.39% |  |  | 2020-03-23 | added 1 |  |  | 2020
EGAT | 2020-04-09 | 237906.87 |  | 53162503.06 | 0 | 53162503.06 | 65831906 | 80.75% |  |  | 2020-04-09 | added 1 |  |  | 2020
EGAT | 2020-04-09 | 838441.79 |  | 54000944.85 | 0 | 54000944.85 | 65831906 | 82.03% |  |  | 2020-04-09 | added 1 |  |  | 2020
EGAT | 2020-04-09 | 923651.34 |  | 54924596.19 | 0 | 54924596.19 | 65831906 | 83.43% |  |  | 2020-04-09 | added 1 |  |  | 2020
EGAT | 2020-04-13 | 1000000 |  | 55924596.19 | 0 | 55924596.19 | 65831906 | 84.95% |  |  | 2020-04-13 | added 1 |  |  | 2020
EGAT | 2020-06-18 | 750000 |  | 56674596.19 | 0 | 56674596.19 | 65831906 | 86.09% |  |  | 2020-06-18 | added 1 |  |  | 2020
EGAT | 2020-10-01 |  | 230351.35 | 56674596.19 | 230351.35 | 56444244.84 | 65831906 | 85.74% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
EGAT | 2020-11-01 |  | 91485 | 56674596.19 | 321836.35 | 56352759.84 | 65831906 | 85.6% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
EGAT | 2020-12-01 |  | 636142.19 | 56674596.19 | 957978.54 | 55716617.65 | 65831906 | 84.63% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
EGAT | 2020-12-16 | 291975.34 |  | 56966571.53 | 957978.54 | 56008592.99 | 65831906 | 85.08% |  |  | 2020-12-16 | added 1 |  |  | 2020
EGAT | 2021-01-01 |  | 76538.05 | 56966571.53 | 1034516.59 | 55932054.94 | 65831906 | 84.96% |  |  |  | cash out both |  |  | 2021
EGAT | 2021-02-01 |  | 30000 | 56966571.53 | 1064516.59 | 55902054.94 | 65831906 | 84.92% |  |  |  | cash out both |  |  | 2021
EGAT | 2021-02-01 |  | 2588287.96 | 56966571.53 | 3652804.55 | 53313766.98 | 65831906 | 80.98% |  |  |  | cash out both |  |  | 2021
EGAT | 2021-03-01 |  | 20870.22 | 56966571.53 | 3673674.77 | 53292896.76 | 65831906 | 80.95% |  |  |  | cash out both |  |  | 2021
1900
Abou Ghazala Bridge Ramp L&L | 2019-03-01 |  | 60310.53 | 0 | 60310.53 | -60310.53 | 1688453 | -3.572% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-04-01 |  | 1320 | 0 | 61630.53 | -61630.53 | 1688453 | -3.65% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-06-01 |  | 16395 | 0 | 78025.53 | -78025.53 | 1688453 | -4.621% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-07-01 |  | 7535 | 0 | 85560.53 | -85560.53 | 1688453 | -5.067% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-08-01 |  | 14750 | 0 | 100310.53 | -100310.53 | 1688453 | -5.941% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-09-01 |  | 79561 | 0 | 179871.53 | -179871.53 | 1688453 | -10.65% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-10-01 |  | 41010.72 | 0 | 220882.25 | -220882.25 | 1688453 | -13.08% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-11-01 |  | 999 | 0 | 221881.25 | -221881.25 | 1688453 | -13.14% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2019-12-01 |  | 64163.26 | 0 | 286044.51 | -286044.51 | 1688453 | -16.94% |  |  |  | cash out both |  |  | 2019
Abou Ghazala Bridge Ramp L&L | 2020-01-01 |  | 1805 | 0 | 287849.51 | -287849.51 | 1688453 | -17.05% |  |  |  | cash out both |  |  | 2020
Abou Ghazala Bridge Ramp L&L | 2020-02-01 |  | 2310 | 0 | 290159.51 | -290159.51 | 1688453 | -17.18% |  |  |  | cash out both |  |  | 2020
Abou Ghazala Bridge Ramp L&L | 2020-05-01 |  | 18615.2 | 0 | 308774.71 | -308774.71 | 1688453 | -18.29% |  |  |  | cash out both |  |  | 2020
Abou Ghazala Bridge Ramp L&L | 2020-10-28 | 1343575 |  | 1343575 | 308774.71 | 1034800.29 | 1688453 | 61.29% |  |  | 2020-10-28 | added 1 |  |  | 2020
Abou Ghazala Bridge Ramp L&L | 2021-02-01 |  | 5318.63 | 1343575 | 314093.34 | 1029481.66 | 1688453 | 60.97% |  |  |  | cash out both |  |  | 2021
Abou Ghazala Bridge Ramp L&L | 2021-03-01 |  | 1189.01 | 1343575 | 315282.35 | 1028292.65 | 1688453 | 60.9% |  |  |  | cash out both |  |  | 2021
1900
Mohamed Ali Fahmy Ramps L&L | 2019-04-01 |  | 50965 | 0 | 50965 | -50965 | 7149700 | -0.7128% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-05-01 |  | 588829.18 | 0 | 639794.18 | -639794.18 | 7149700 | -8.949% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-06-01 |  | 172070.9 | 0 | 811865.08 | -811865.08 | 7149700 | -11.36% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-07-01 |  | 351317.8 | 0 | 1163182.88 | -1163182.88 | 7149700 | -16.27% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-08-01 |  | 90723.27 | 0 | 1253906.15 | -1253906.15 | 7149700 | -17.54% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-09-01 |  | 239353.3 | 0 | 1493259.45 | -1493259.45 | 7149700 | -20.89% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-10-01 |  | 227119.69 | 0 | 1720379.14 | -1720379.14 | 7149700 | -24.06% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-11-01 |  | 47223.93 | 0 | 1767603.07 | -1767603.07 | 7149700 | -24.72% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-12-01 |  | 167212.97 | 0 | 1934816.04 | -1934816.04 | 7149700 | -27.06% |  |  |  | cash out both |  |  | 2019
Mohamed Ali Fahmy Ramps L&L | 2020-01-01 |  | 79839.48 | 0 | 2014655.52 | -2014655.52 | 7149700 | -28.18% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-02-01 |  | 109705.5 | 0 | 2124361.02 | -2124361.02 | 7149700 | -29.71% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-03-01 |  | 332.31 | 0 | 2124693.33 | -2124693.33 | 7149700 | -29.72% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-05-01 |  | 69610.59 | 0 | 2194303.92 | -2194303.92 | 7149700 | -30.69% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-06-01 |  | 332.31 | 0 | 2194636.23 | -2194636.23 | 7149700 | -30.7% |  |  |  | cash out both |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-06-18 | 1494015 |  | 1494015 | 2194636.23 | -700621.23 | 7149700 | -9.799% |  |  | 2020-06-18 | added 1 |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-07-12 | 166155 |  | 1660170 | 2194636.23 | -534466.23 | 7149700 | -7.475% |  |  | 2020-07-12 | added cash in 3 |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-12-14 | 222130 |  | 1882300 | 2194636.23 | -312336.23 | 7149700 | -4.369% |  |  | 2020-12-14 | added 1 |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2020-12-14 | 236760 |  | 2119060 | 2194636.23 | -75576.23 | 7149700 | -1.057% |  |  | 2020-12-14 | added cash in 3 |  |  | 2020
Mohamed Ali Fahmy Ramps L&L | 2021-02-01 |  | 19888.76 | 2119060 | 2214524.99 | -95464.99 | 7149700 | -1.335% |  |  |  | cash out both |  |  | 2021
Mohamed Ali Fahmy Ramps L&L | 2021-03-01 |  | 1580.08 | 2119060 | 2216105.07 | -97045.07 | 7149700 | -1.357% |  |  |  | cash out both |  |  | 2021
1900
El Mosheer Bridge Abu Zaied Khdr L&L | 2019-11-01 |  | 46683 | 0 | 46683 | -46683 | 4203687 | -1.111% |  |  |  | cash out both |  |  | 2019
El Mosheer Bridge Abu Zaied Khdr L&L | 2019-12-01 |  | 2118461.31 | 0 | 2165144.31 | -2165144.31 | 4203687 | -51.51% |  |  |  | cash out both |  |  | 2019
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-01-01 |  | 8547 | 0 | 2173691.31 | -2173691.31 | 4203687 | -51.71% |  |  |  | cash out both |  |  | 2020
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-02-01 |  | 12795 | 0 | 2186486.31 | -2186486.31 | 4203687 | -52.01% |  |  |  | cash out both |  |  | 2020
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-06-01 |  | 196068.6 | 0 | 2382554.91 | -2382554.91 | 4203687 | -56.68% |  |  |  | cash out both |  |  | 2020
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-08-01 |  | 33234 | 0 | 2415788.91 | -2415788.91 | 4203687 | -57.47% |  |  |  | cash out both |  |  | 2020
1900
Ora Zed Park L&L | 2019-07-01 |  | 4000 | 0 | 4000 | -4000 | 1042542 | -0.3837% |  |  |  | cash out both |  |  | 2019
Ora Zed Park L&L | 2019-08-01 |  | 29590 | 0 | 33590 | -33590 | 1042542 | -3.222% |  |  |  | cash out both |  |  | 2019
Ora Zed Park L&L | 2019-09-01 |  | 190975 | 0 | 224565 | -224565 | 1042542 | -21.54% |  |  |  | cash out both |  |  | 2019
Ora Zed Park L&L | 2019-10-01 |  | 83030.02 | 0 | 307595.02 | -307595.02 | 1042542 | -29.5% |  |  |  | cash out both |  |  | 2019
Ora Zed Park L&L | 2019-11-01 |  | 28265.17 | 0 | 335860.19 | -335860.19 | 1042542 | -32.22% |  |  |  | cash out both |  |  | 2019
Ora Zed Park L&L | 2019-11-07 | 505797.14 |  | 505797.14 | 335860.19 | 169936.95 | 1042542 | 16.3% |  |  | 2019-11-07 | added cash in 3 |  |  | 2019
Ora Zed Park L&L | 2019-12-01 |  | 237800.21 | 505797.14 | 573660.4 | -67863.26 | 1042542 | -6.509% |  |  |  | cash out both |  |  | 2019
Ora Zed Park L&L | 2020-01-01 |  | 20686 | 505797.14 | 594346.4 | -88549.26 | 1042542 | -8.494% |  |  |  | cash out both |  |  | 2020
Ora Zed Park L&L | 2020-02-01 |  | 33959.75 | 505797.14 | 628306.15 | -122509.01 | 1042542 | -11.75% |  |  |  | cash out both |  |  | 2020
Ora Zed Park L&L | 2020-02-09 | 264423.21 |  | 770220.35 | 628306.15 | 141914.2 | 1042542 | 13.61% |  |  | 2020-02-09 | added 1 |  |  | 2020
Ora Zed Park L&L | 2020-03-01 |  | 18120 | 770220.35 | 646426.15 | 123794.2 | 1042542 | 11.87% |  |  |  | cash out both |  |  | 2020
Ora Zed Park L&L | 2020-04-01 |  | 15456 | 770220.35 | 661882.15 | 108338.2 | 1042542 | 10.39% |  |  |  | cash out both |  |  | 2020
Ora Zed Park L&L | 2020-05-01 |  | 118727.74 | 770220.35 | 780609.89 | -10389.54 | 1042542 | -0.9966% |  |  |  | cash out both |  |  | 2020
Ora Zed Park L&L | 2020-06-01 |  | 1765 | 770220.35 | 782374.89 | -12154.54 | 1042542 | -1.166% |  |  |  | cash out both |  |  | 2020
Ora Zed Park L&L | 2020-10-01 |  | 63220.59 | 770220.35 | 845595.48 | -75375.13 | 1042542 | -7.23% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Ora Zed Park L&L | 2020-11-01 |  | 179176.92 | 770220.35 | 1024772.4 | -254552.05 | 1042542 | -24.42% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Ora Zed Park L&L | 2021-02-11 | 128110.86 |  | 898331.21 | 1024772.4 | -126441.19 | 1042542 | -12.13% |  |  | 2021-02-11 | added cash in 3 |  |  | 2021
1900
DoubleTree Mangroovy El Gouna Hotel | 2019-08-01 |  | 123695 | 0 | 123695 | -123695 | 57898699.39 | -0.2136% |  |  |  | cash out both |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-08-25 | 13625000 |  | 13625000 | 123695 | 13501305 | 57898699.39 | 23.32% |  |  | 2019-08-25 | added cash in 3 |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-09-01 |  | 916740.44 | 13625000 | 1040435.44 | 12584564.56 | 57898699.39 | 21.74% |  |  |  | cash out both |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-10-01 |  | 2815823.91 | 13625000 | 3856259.35 | 9768740.65 | 57898699.39 | 16.87% |  |  |  | cash out both |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-11-01 |  | 2474341.27 | 13625000 | 6330600.62 | 7294399.38 | 57898699.39 | 12.6% |  |  |  | cash out both |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-11-27 | 2327690.6 |  | 15952690.6 | 6330600.62 | 9622089.98 | 57898699.39 | 16.62% |  |  | 2019-11-27 | added cash in 3 |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-12-01 |  | 2430905.56 | 15952690.6 | 8761506.18 | 7191184.42 | 57898699.39 | 12.42% |  |  |  | cash out both |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-12-18 | 3867767.27 |  | 19820457.87 | 8761506.18 | 11058951.69 | 57898699.39 | 19.1% |  |  | 2019-12-18 | added cash in 3 |  |  | 2019
DoubleTree Mangroovy El Gouna Hotel | 2020-01-01 |  | 6227180.54 | 19820457.87 | 14988686.72 | 4831771.15 | 57898699.39 | 8.345% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-01-12 | 2286139.86 |  | 22106597.73 | 14988686.72 | 7117911.01 | 57898699.39 | 12.29% |  |  | 2020-01-12 | added 1 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-01-26 | 73813.12 |  | 22180410.85 | 14988686.72 | 7191724.13 | 57898699.39 | 12.42% |  |  | 2020-01-26 | added 1 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-02-01 |  | 2096022.36 | 22180410.85 | 17084709.08 | 5095701.77 | 57898699.39 | 8.801% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-02-09 | 425568 |  | 22605978.85 | 17084709.08 | 5521269.77 | 57898699.39 | 9.536% |  |  | 2020-02-09 | added 1 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-02-09 | 73813.12 |  | 22679791.97 | 17084709.08 | 5595082.89 | 57898699.39 | 9.664% |  |  | 2020-02-09 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-02-27 | 2572404.48 |  | 25252196.45 | 17084709.08 | 8167487.37 | 57898699.39 | 14.11% |  |  | 2020-02-27 | added 1 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-02-27 | 425568 |  | 25677764.45 | 17084709.08 | 8593055.37 | 57898699.39 | 14.84% |  |  | 2020-02-27 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-03-01 |  | 1978445.9 | 25677764.45 | 19063154.98 | 6614609.47 | 57898699.39 | 11.42% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-03-22 | 1808595.27 |  | 27486359.72 | 19063154.98 | 8423204.74 | 57898699.39 | 14.55% |  |  | 2020-03-22 | added 1 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-03-22 | 441526.8 |  | 27927886.52 | 19063154.98 | 8864731.54 | 57898699.39 | 15.31% |  |  | 2020-03-22 | added 1 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-04-01 |  | 702657.88 | 27927886.52 | 19765812.86 | 8162073.66 | 57898699.39 | 14.1% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-05-01 |  | 2009562.65 | 27927886.52 | 21775375.51 | 6152511.01 | 57898699.39 | 10.63% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-06-01 |  | 603884.31 | 27927886.52 | 22379259.82 | 5548626.7 | 57898699.39 | 9.583% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-06-17 | 16757 |  | 27944643.52 | 22379259.82 | 5565383.7 | 57898699.39 | 9.612% |  |  | 2020-06-17 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-06-17 | 2000000 |  | 29944643.52 | 22379259.82 | 7565383.7 | 57898699.39 | 13.07% |  |  | 2020-06-17 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-06-29 | 1617 |  | 29946260.52 | 22379259.82 | 7567000.7 | 57898699.39 | 13.07% |  |  | 2020-06-29 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-07-01 |  | 878558.31 | 29946260.52 | 23257818.13 | 6688442.39 | 57898699.39 | 11.55% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-08-01 |  | 4457113.88 | 29946260.52 | 27714932.01 | 2231328.51 | 57898699.39 | 3.854% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-08-26 | 2145687.36 |  | 32091947.88 | 27714932.01 | 4377015.87 | 57898699.39 | 7.56% |  |  | 2020-08-26 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-08-26 | 4246133.4 |  | 36338081.28 | 27714932.01 | 8623149.27 | 57898699.39 | 14.89% |  |  | 2020-08-26 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-08-26 | 1922134.77 |  | 38260216.05 | 27714932.01 | 10545284.04 | 57898699.39 | 18.21% |  |  | 2020-08-26 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-09-01 |  | 4761736.81 | 38260216.05 | 32476668.82 | 5783547.23 | 57898699.39 | 9.989% |  |  |  | cash out both |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-10-01 |  | 3643919.27 | 38260216.05 | 36120588.09 | 2139627.96 | 57898699.39 | 3.695% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-10-05 | 1030964.27 |  | 39291180.32 | 36120588.09 | 3170592.23 | 57898699.39 | 5.476% |  |  | 2020-10-05 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-10-26 | 1173489.52 |  | 40464669.84 | 36120588.09 | 4344081.75 | 57898699.39 | 7.503% |  |  | 2020-10-26 | added cash in 3 |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-11-01 |  | 398244.78 | 40464669.84 | 36518832.87 | 3945836.97 | 57898699.39 | 6.815% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2020-12-01 |  | 1297987.62 | 40464669.84 | 37816820.49 | 2647849.35 | 57898699.39 | 4.573% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
DoubleTree Mangroovy El Gouna Hotel | 2021-01-01 |  | 5176581.33 | 40464669.84 | 42993401.82 | -2528731.98 | 57898699.39 | -4.368% |  |  |  | cash out both |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-01-14 | 1942857.14 |  | 42407526.98 | 42993401.82 | -585874.84 | 57898699.39 | -1.012% |  |  | 2021-01-14 | added cash in 3 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-01 | 1750027.3 |  | 44157554.28 | 42993401.82 | 1164152.46 | 57898699.39 | 2.011% |  |  | 2021-02-01 | added 1 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-01 |  | 2428701.65 | 44157554.28 | 45422103.47 | -1264549.19 | 57898699.39 | -2.184% |  |  |  | cash out both |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-03 | 1750027.3 |  | 45907581.58 | 45422103.47 | 485478.11 | 57898699.39 | 0.8385% |  |  | 2021-02-03 | added cash in 3 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-21 | 1951940.18 |  | 47859521.76 | 45422103.47 | 2437418.29 | 57898699.39 | 4.21% |  |  | 2021-02-21 | added 1 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-21 | 173749.2 |  | 48033270.96 | 45422103.47 | 2611167.49 | 57898699.39 | 4.51% |  |  | 2021-02-21 | added 1 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-21 | 74100 |  | 48107370.96 | 45422103.47 | 2685267.49 | 57898699.39 | 4.638% |  |  | 2021-02-21 | added 1 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-21 | 8424 |  | 48115794.96 | 45422103.47 | 2693691.49 | 57898699.39 | 4.652% |  |  | 2021-02-21 | added cash in 3 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-02-21 | 165325.2 |  | 48281120.16 | 45422103.47 | 2859016.69 | 57898699.39 | 4.938% |  |  | 2021-02-21 | added cash in 3 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-03-01 |  | 3119396.69 | 48281120.16 | 48541500.16 | -260380 | 57898699.39 | -0.4497% |  |  |  | cash out both |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-04-20 | 3187.5 |  | 48284307.66 | 48541500.16 | -257192.5 | 57898699.39 | -0.4442% |  |  | 2021-04-20 | added cash in 3 |  |  | 2021
DoubleTree Mangroovy El Gouna Hotel | 2021-04-20 | 3058799.81 |  | 51343107.47 | 48541500.16 | 2801607.31 | 57898699.39 | 4.839% |  |  | 2021-04-20 | added cash in 3 |  |  | 2021
1900
Baron Palace Fence | 2019-08-01 |  | 14090 | 0 | 14090 | -14090 | 16220552 | -0.08687% |  |  |  | cash out both |  |  | 2019
Baron Palace Fence | 2019-09-01 |  | 308480 | 0 | 322570 | -322570 | 16220552 | -1.989% |  |  |  | cash out both |  |  | 2019
Baron Palace Fence | 2019-10-01 |  | 477249.15 | 0 | 799819.15 | -799819.15 | 16220552 | -4.931% |  |  |  | cash out both |  |  | 2019
Baron Palace Fence | 2019-11-01 |  | 1306567.91 | 0 | 2106387.06 | -2106387.06 | 16220552 | -12.99% |  |  |  | cash out both |  |  | 2019
Baron Palace Fence | 2019-12-01 |  | 1047888.89 | 0 | 3154275.95 | -3154275.95 | 16220552 | -19.45% |  |  |  | cash out both |  |  | 2019
Baron Palace Fence | 2020-01-01 |  | 1770657.46 | 0 | 4924933.41 | -4924933.41 | 16220552 | -30.36% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-02-01 |  | 2675048.79 | 0 | 7599982.2 | -7599982.2 | 16220552 | -46.85% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-03-01 |  | 2357973.45 | 0 | 9957955.65 | -9957955.65 | 16220552 | -61.39% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-04-01 |  | 412976.27 | 0 | 10370931.92 | -10370931.92 | 16220552 | -63.94% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-05-01 |  | 1195.04 | 0 | 10372126.96 | -10372126.96 | 16220552 | -63.94% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-06-01 |  | 55159 | 0 | 10427285.96 | -10427285.96 | 16220552 | -64.28% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-07-01 |  | 8670.85 | 0 | 10435956.81 | -10435956.81 | 16220552 | -64.34% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-09-01 |  | 501066.13 | 0 | 10937022.94 | -10937022.94 | 16220552 | -67.43% |  |  |  | cash out both |  |  | 2020
Baron Palace Fence | 2020-10-04 | 5600125 |  | 5600125 | 10937022.94 | -5336897.94 | 16220552 | -32.9% |  |  | 2020-10-04 | added cash in 3 |  |  | 2020
Baron Palace Fence | 2020-11-01 |  | 448670 | 5600125 | 11385692.94 | -5785567.94 | 16220552 | -35.67% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Baron Palace Fence | 2020-12-01 |  | 2500 | 5600125 | 11388192.94 | -5788067.94 | 16220552 | -35.68% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Baron Palace Fence | 2020-12-14 | 392980 |  | 5993105 | 11388192.94 | -5395087.94 | 16220552 | -33.26% |  |  | 2020-12-14 | added cash in 3 |  |  | 2020
Baron Palace Fence | 2021-01-01 |  | 91695 | 5993105 | 11479887.94 | -5486782.94 | 16220552 | -33.83% |  |  |  | cash out both |  |  | 2021
Baron Palace Fence | 2021-02-01 |  | 792.03 | 5993105 | 11480679.97 | -5487574.97 | 16220552 | -33.83% |  |  |  | cash out both |  |  | 2021
Baron Palace Fence | 2021-02-24 | 355500 |  | 6348605 | 11480679.97 | -5132074.97 | 16220552 | -31.64% |  |  | 2021-02-24 | added cash in 3 |  |  | 2021
Baron Palace Fence | 2021-03-01 |  | 3040.33 | 6348605 | 11483720.3 | -5135115.3 | 16220552 | -31.66% |  |  |  | cash out both |  |  | 2021
1900
Safeer Square Bridge | 2019-08-01 |  | 230000 | 0 | 230000 | -230000 | 95436549 | -0.241% |  |  |  | cash out both |  |  | 2019
Safeer Square Bridge | 2019-09-01 |  | 1011621.78 | 0 | 1241621.78 | -1241621.78 | 95436549 | -1.301% |  |  |  | cash out both |  |  | 2019
Safeer Square Bridge | 2019-10-01 |  | 5568944.65 | 0 | 6810566.43 | -6810566.43 | 95436549 | -7.136% |  |  |  | cash out both |  |  | 2019
Safeer Square Bridge | 2019-11-01 |  | 7992126.69 | 0 | 14802693.12 | -14802693.12 | 95436549 | -15.51% |  |  |  | cash out both |  |  | 2019
Safeer Square Bridge | 2019-12-01 |  | 14530425.24 | 0 | 29333118.36 | -29333118.36 | 95436549 | -30.74% |  |  |  | cash out both |  |  | 2019
Safeer Square Bridge | 2020-01-01 |  | 6675475.41 | 0 | 36008593.77 | -36008593.77 | 95436549 | -37.73% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-01-31 | 40035000 |  | 40035000 | 36008593.77 | 4026406.23 | 95436549 | 4.219% |  |  | 2020-01-31 | added cash in 3 |  |  | 2020
Safeer Square Bridge | 2020-02-01 |  | 1836134.8 | 40035000 | 37844728.57 | 2190271.43 | 95436549 | 2.295% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-02-09 | 997 |  | 40035997 | 37844728.57 | 2191268.43 | 95436549 | 2.296% |  |  | 2020-02-09 | added cash in 3 |  |  | 2020
Safeer Square Bridge | 2020-02-16 | 5454520 |  | 45490517 | 37844728.57 | 7645788.43 | 95436549 | 8.011% |  |  | 2020-02-16 | added cash in 3 |  |  | 2020
Safeer Square Bridge | 2020-03-01 |  | 757140.3 | 45490517 | 38601868.87 | 6888648.13 | 95436549 | 7.218% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-04-01 |  | 134873.65 | 45490517 | 38736742.52 | 6753774.48 | 95436549 | 7.077% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-05-01 |  | 114604.29 | 45490517 | 38851346.81 | 6639170.19 | 95436549 | 6.957% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-06-01 |  | 263853.74 | 45490517 | 39115200.55 | 6375316.45 | 95436549 | 6.68% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-07-01 |  | 673273.7 | 45490517 | 39788474.25 | 5702042.75 | 95436549 | 5.975% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-07-29 | 6118125 |  | 51608642 | 39788474.25 | 11820167.75 | 95436549 | 12.39% |  |  | 2020-07-29 | added cash in 3 |  |  | 2020
Safeer Square Bridge | 2020-07-31 | 179725 |  | 51788367 | 39788474.25 | 11999892.75 | 95436549 | 12.57% |  |  | 2020-07-31 | added cash in 3 |  |  | 2020
Safeer Square Bridge | 2020-08-13 | 3298745 |  | 55087112 | 39788474.25 | 15298637.75 | 95436549 | 16.03% |  |  | 2020-08-13 | added 1 |  |  | 2020
Safeer Square Bridge | 2020-09-01 |  | 182243.92 | 55087112 | 39970718.17 | 15116393.83 | 95436549 | 15.84% |  |  |  | cash out both |  |  | 2020
Safeer Square Bridge | 2020-11-01 | 3298730 | 2410290 | 58385842 | 42381008.17 | 16004833.83 | 95436549 | 16.77% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Safeer Square Bridge | 2020-12-01 |  | 5454.52 | 58385842 | 42386462.69 | 15999379.31 | 95436549 | 16.76% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Safeer Square Bridge | 2021-03-01 |  | 5454.52 | 58385842 | 42391917.21 | 15993924.79 | 95436549 | 16.76% |  |  |  | cash out both |  |  | 2021
1900
Suez Road Tunnel Res L&L | 2019-09-01 |  | 41835 | 0 | 41835 | -41835 | 4423592 | -0.9457% |  |  |  | cash out both |  |  | 2019
Suez Road Tunnel Res L&L | 2019-10-01 |  | 186408.87 | 0 | 228243.87 | -228243.87 | 4423592 | -5.16% |  |  |  | cash out both |  |  | 2019
Suez Road Tunnel Res L&L | 2019-11-01 |  | 370529.97 | 0 | 598773.84 | -598773.84 | 4423592 | -13.54% |  |  |  | cash out both |  |  | 2019
Suez Road Tunnel Res L&L | 2019-12-01 |  | 22267.29 | 0 | 621041.13 | -621041.13 | 4423592 | -14.04% |  |  |  | cash out both |  |  | 2019
Suez Road Tunnel Res L&L | 2020-01-01 |  | 44884.55 | 0 | 665925.68 | -665925.68 | 4423592 | -15.05% |  |  |  | cash out both |  |  | 2020
Suez Road Tunnel Res L&L | 2020-02-01 |  | 14965.5 | 0 | 680891.18 | -680891.18 | 4423592 | -15.39% |  |  |  | cash out both |  |  | 2020
Suez Road Tunnel Res L&L | 2020-05-01 |  | 55138.6 | 0 | 736029.78 | -736029.78 | 4423592 | -16.64% |  |  |  | cash out both |  |  | 2020
Suez Road Tunnel Res L&L | 2020-06-01 |  | 23748 | 0 | 759777.78 | -759777.78 | 4423592 | -17.18% |  |  |  | cash out both |  |  | 2020
Suez Road Tunnel Res L&L | 2020-07-01 |  | 8044 | 0 | 767821.78 | -767821.78 | 4423592 | -17.36% |  |  |  | cash out both |  |  | 2020
Suez Road Tunnel Res L&L | 2020-10-01 |  | 37742 | 0 | 805563.78 | -805563.78 | 4423592 | -18.21% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Suez Road Tunnel Res L&L | 2020-10-18 | 2837565 |  | 2837565 | 805563.78 | 2032001.22 | 4423592 | 45.94% |  |  | 2020-10-18 | added cash in 3 |  |  | 2020
Suez Road Tunnel Res L&L | 2020-11-22 | 1311260 |  | 4148825 | 805563.78 | 3343261.22 | 4423592 | 75.58% |  |  | 2020-11-22 | added 1 |  |  | 2020
Suez Road Tunnel Res L&L | 2021-02-01 |  | 454187.42 | 4148825 | 1259751.2 | 2889073.8 | 4423592 | 65.31% |  |  |  | cash out both |  |  | 2021
Suez Road Tunnel Res L&L | 2021-03-01 |  | 3673.94 | 4148825 | 1263425.14 | 2885399.86 | 4423592 | 65.23% |  |  |  | cash out both |  |  | 2021
1900
HyperOne Zayed Extention | 2019-09-01 |  | 141750 | 0 | 141750 | -141750 | 133583770 | -0.1061% |  |  |  | cash out both |  |  | 2019
HyperOne Zayed Extention | 2019-10-01 |  | 953319.33 | 0 | 1095069.33 | -1095069.33 | 133583770 | -0.8198% |  |  |  | cash out both |  |  | 2019
HyperOne Zayed Extention | 2019-10-13 | 33750000 |  | 33750000 | 1095069.33 | 32654930.67 | 133583770 | 24.45% |  |  | 2019-10-13 | added cash in 3 |  |  | 2019
HyperOne Zayed Extention | 2019-11-01 |  | 4599187.47 | 33750000 | 5694256.8 | 28055743.2 | 133583770 | 21% |  |  |  | cash out both |  |  | 2019
HyperOne Zayed Extention | 2019-12-01 |  | 3785151.58 | 33750000 | 9479408.38 | 24270591.62 | 133583770 | 18.17% |  |  |  | cash out both |  |  | 2019
HyperOne Zayed Extention | 2019-12-02 | 2499090 |  | 36249090 | 9479408.38 | 26769681.62 | 133583770 | 20.04% |  |  | 2019-12-02 | added 1 |  |  | 2019
HyperOne Zayed Extention | 2019-12-25 | 8063620 |  | 44312710 | 9479408.38 | 34833301.62 | 133583770 | 26.08% |  |  | 2019-12-25 | added cash in 3 |  |  | 2019
HyperOne Zayed Extention | 2020-01-01 |  | 5033335.71 | 44312710 | 14512744.09 | 29799965.91 | 133583770 | 22.31% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-01-20 | 6681009 |  | 50993719 | 14512744.09 | 36480974.91 | 133583770 | 27.31% |  |  | 2020-01-20 | added cash in 3 |  |  | 2020
HyperOne Zayed Extention | 2020-02-01 |  | 5225134.66 | 50993719 | 19737878.75 | 31255840.25 | 133583770 | 23.4% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-02-23 | 6318712 |  | 57312431 | 19737878.75 | 37574552.25 | 133583770 | 28.13% |  |  | 2020-02-23 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-02-23 | 1171706 |  | 58484137 | 19737878.75 | 38746258.25 | 133583770 | 29.01% |  |  | 2020-02-23 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-02-27 | 3307335 |  | 61791472 | 19737878.75 | 42053593.25 | 133583770 | 31.48% |  |  | 2020-02-27 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-02-29 | 4993651.07 |  | 66785123.07 | 19737878.75 | 47047244.32 | 133583770 | 35.22% |  |  | 2020-02-29 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-03-01 |  | 10387082.84 | 66785123.07 | 30124961.59 | 36660161.48 | 133583770 | 27.44% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-03-02 | 4724997 |  | 71510120.07 | 30124961.59 | 41385158.48 | 133583770 | 30.98% |  |  | 2020-03-02 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-03-15 | 8598544 |  | 80108664.07 | 30124961.59 | 49983702.48 | 133583770 | 37.42% |  |  | 2020-03-15 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-03-23 | 980000 |  | 81088664.07 | 30124961.59 | 50963702.48 | 133583770 | 38.15% |  |  | 2020-03-23 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-03-26 | 8960935 |  | 90049599.07 | 30124961.59 | 59924637.48 | 133583770 | 44.86% |  |  | 2020-03-26 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-03-29 | 1165162 |  | 91214761.07 | 30124961.59 | 61089799.48 | 133583770 | 45.73% |  |  | 2020-03-29 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-04-01 |  | 1626963.97 | 91214761.07 | 31751925.56 | 59462835.51 | 133583770 | 44.51% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-04-21 | 3276433 |  | 94491194.07 | 31751925.56 | 62739268.51 | 133583770 | 46.97% |  |  | 2020-04-21 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-04-26 | 1165148 |  | 95656342.07 | 31751925.56 | 63904416.51 | 133583770 | 47.84% |  |  | 2020-04-26 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-04-30 | 305602.34 |  | 95961944.41 | 31751925.56 | 64210018.85 | 133583770 | 48.07% |  |  | 2020-04-30 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-05-01 |  | 9104866.65 | 95961944.41 | 40856792.21 | 55105152.2 | 133583770 | 41.25% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-05-05 | 1277872 |  | 97239816.41 | 40856792.21 | 56383024.2 | 133583770 | 42.21% |  |  | 2020-05-05 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-06-01 |  | 7321582.33 | 97239816.41 | 48178374.54 | 49061441.87 | 133583770 | 36.73% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-06-03 | 3490984 |  | 100730800.41 | 48178374.54 | 52552425.87 | 133583770 | 39.34% |  |  | 2020-06-03 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-06-09 | 4688664 |  | 105419464.41 | 48178374.54 | 57241089.87 | 133583770 | 42.85% |  |  | 2020-06-09 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-07-01 |  | 9049949.79 | 105419464.41 | 57228324.33 | 48191140.08 | 133583770 | 36.08% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-07-05 | 6700148 |  | 112119612.41 | 57228324.33 | 54891288.08 | 133583770 | 41.09% |  |  | 2020-07-05 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-07-26 | 1896315 |  | 114015927.41 | 57228324.33 | 56787603.08 | 133583770 | 42.51% |  |  | 2020-07-26 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-08-01 |  | 2196771.75 | 114015927.41 | 59425096.08 | 54590831.33 | 133583770 | 40.87% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-08-17 | 4000000 |  | 118015927.41 | 59425096.08 | 58590831.33 | 133583770 | 43.86% |  |  | 2020-08-17 | added cash in 3 |  |  | 2020
HyperOne Zayed Extention | 2020-09-01 | 6738702 |  | 124754629.41 | 59425096.08 | 65329533.33 | 133583770 | 48.91% |  |  | 2020-09-01 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-09-01 |  | 4555524.57 | 124754629.41 | 63980620.65 | 60774008.76 | 133583770 | 45.5% |  |  |  | cash out both |  |  | 2020
HyperOne Zayed Extention | 2020-09-24 | 4476191 |  | 129230820.41 | 63980620.65 | 65250199.76 | 133583770 | 48.85% |  |  | 2020-09-24 | added 1 |  |  | 2020
HyperOne Zayed Extention | 2020-10-01 |  | 6889598.01 | 129230820.41 | 70870218.66 | 58360601.75 | 133583770 | 43.69% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
HyperOne Zayed Extention | 2020-11-01 |  | 4807891.28 | 129230820.41 | 75678109.94 | 53552710.47 | 133583770 | 40.09% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
HyperOne Zayed Extention | 2020-12-01 |  | 2392170.96 | 129230820.41 | 78070280.9 | 51160539.51 | 133583770 | 38.3% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
HyperOne Zayed Extention | 2021-01-01 |  | 2158911.93 | 129230820.41 | 80229192.83 | 49001627.58 | 133583770 | 36.68% |  |  |  | cash out both |  |  | 2021
HyperOne Zayed Extention | 2021-02-01 |  | 657871.69 | 129230820.41 | 80887064.52 | 48343755.89 | 133583770 | 36.19% |  |  |  | cash out both |  |  | 2021
HyperOne Zayed Extention | 2021-03-01 |  | 934686.41 | 129230820.41 | 81821750.93 | 47409069.48 | 133583770 | 35.49% |  |  |  | cash out both |  |  | 2021
1900
IKEA Extention MoA | 2019-10-01 |  | 3011216.94 | 0 | 3011216.94 | -3011216.94 | 196190620 | -1.535% |  |  |  | cash out both |  |  | 2019
IKEA Extention MoA | 2019-10-16 | 428986.9 |  | 428986.9 | 3011216.94 | -2582230.04 | 196190620 | -1.316% |  |  | 2019-10-16 | added cash in 3 |  |  | 2019
IKEA Extention MoA | 2019-10-16 | 5000000 |  | 5428986.9 | 3011216.94 | 2417769.96 | 196190620 | 1.232% |  |  | 2019-10-16 | added cash in 3 |  |  | 2019
IKEA Extention MoA | 2019-11-01 |  | 7126856.85 | 5428986.9 | 10138073.79 | -4709086.89 | 196190620 | -2.4% |  |  |  | cash out both |  |  | 2019
IKEA Extention MoA | 2019-11-17 | 4032556.9 |  | 9461543.8 | 10138073.79 | -676529.99 | 196190620 | -0.3448% |  |  | 2019-11-17 | added cash in 3 |  |  | 2019
IKEA Extention MoA | 2019-11-26 | 10633715.55 |  | 20095259.35 | 10138073.79 | 9957185.56 | 196190620 | 5.075% |  |  | 2019-11-26 | added 1 |  |  | 2019
IKEA Extention MoA | 2019-12-01 |  | 7373329.8 | 20095259.35 | 17511403.59 | 2583855.76 | 196190620 | 1.317% |  |  |  | cash out both |  |  | 2019
IKEA Extention MoA | 2019-12-09 | 4951900.8 |  | 25047160.15 | 17511403.59 | 7535756.56 | 196190620 | 3.841% |  |  | 2019-12-09 | added cash in 3 |  |  | 2019
IKEA Extention MoA | 2019-12-31 | 5000000 |  | 30047160.15 | 17511403.59 | 12535756.56 | 196190620 | 6.39% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
IKEA Extention MoA | 2019-12-31 | 633715.55 |  | 30680875.7 | 17511403.59 | 13169472.11 | 196190620 | 6.713% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
IKEA Extention MoA | 2020-01-01 |  | 11867880.08 | 30680875.7 | 29379283.67 | 1301592.03 | 196190620 | 0.6634% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-01-21 | 1122526.46 |  | 31803402.16 | 29379283.67 | 2424118.49 | 196190620 | 1.236% |  |  | 2020-01-21 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-01-21 | 993522.91 |  | 32796925.07 | 29379283.67 | 3417641.4 | 196190620 | 1.742% |  |  | 2020-01-21 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-01-29 | 7184168.18 |  | 39981093.25 | 29379283.67 | 10601809.58 | 196190620 | 5.404% |  |  | 2020-01-29 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-01-29 | 5000000 |  | 44981093.25 | 29379283.67 | 15601809.58 | 196190620 | 7.952% |  |  | 2020-01-29 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-01-29 | 2184168.18 |  | 47165261.43 | 29379283.67 | 17785977.76 | 196190620 | 9.066% |  |  | 2020-01-29 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-02-01 |  | 28621085.84 | 47165261.43 | 58000369.51 | -10835108.08 | 196190620 | -5.523% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-02-16 | 5000000 |  | 52165261.43 | 58000369.51 | -5835108.08 | 196190620 | -2.974% |  |  | 2020-02-16 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-02-16 | 1562500 |  | 53727761.43 | 58000369.51 | -4272608.08 | 196190620 | -2.178% |  |  | 2020-02-16 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-03-01 |  | 6172946.29 | 53727761.43 | 64173315.8 | -10445554.37 | 196190620 | -5.324% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-03-05 | 8278802.07 |  | 62006563.5 | 64173315.8 | -2166752.3 | 196190620 | -1.104% |  |  | 2020-03-05 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-03-05 | 3278802.07 |  | 65285365.57 | 64173315.8 | 1112049.77 | 196190620 | 0.5668% |  |  | 2020-03-05 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-03-05 | 5000000 |  | 70285365.57 | 64173315.8 | 6112049.77 | 196190620 | 3.115% |  |  | 2020-03-05 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-04-01 |  | 4596619.73 | 70285365.57 | 68769935.53 | 1515430.04 | 196190620 | 0.7724% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-04-14 | 5000000 |  | 75285365.57 | 68769935.53 | 6515430.04 | 196190620 | 3.321% |  |  | 2020-04-14 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-04-14 | 2929959.81 |  | 78215325.38 | 68769935.53 | 9445389.85 | 196190620 | 4.814% |  |  | 2020-04-14 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-05-01 |  | 9542179.94 | 78215325.38 | 78312115.47 | -96790.09 | 196190620 | -0.04933% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-05-10 | 1818917.5 |  | 80034242.88 | 78312115.47 | 1722127.41 | 196190620 | 0.8778% |  |  | 2020-05-10 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-05-10 | 3751873.62 |  | 83786116.5 | 78312115.47 | 5474001.03 | 196190620 | 2.79% |  |  | 2020-05-10 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-05-12 | 3899213.68 |  | 87685330.18 | 78312115.47 | 9373214.71 | 196190620 | 4.778% |  |  | 2020-05-12 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-05-19 | 525633.83 |  | 88210964.01 | 78312115.47 | 9898848.54 | 196190620 | 5.046% |  |  | 2020-05-19 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-05-21 | 3899213.68 |  | 92110177.69 | 78312115.47 | 13798062.22 | 196190620 | 7.033% |  |  | 2020-05-21 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-05-21 | 525633.83 |  | 92635811.52 | 78312115.47 | 14323696.05 | 196190620 | 7.301% |  |  | 2020-05-21 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-06-01 |  | 14513935.55 | 92635811.52 | 92826051.02 | -190239.5 | 196190620 | -0.09697% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-07-01 |  | 9843472.56 | 92635811.52 | 102669523.58 | -10033712.06 | 196190620 | -5.114% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-07-05 | 1161858.91 |  | 93797670.43 | 102669523.58 | -8871853.15 | 196190620 | -4.522% |  |  | 2020-07-05 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-07-05 | 5000000 |  | 98797670.43 | 102669523.58 | -3871853.15 | 196190620 | -1.974% |  |  | 2020-07-05 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-08-01 |  | 14055586.3 | 98797670.43 | 116725109.88 | -17927439.45 | 196190620 | -9.138% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-08-10 | 3080191.13 |  | 101877861.56 | 116725109.88 | -14847248.32 | 196190620 | -7.568% |  |  | 2020-08-10 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-08-10 | 5000000 |  | 106877861.56 | 116725109.88 | -9847248.32 | 196190620 | -5.019% |  |  | 2020-08-10 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-08-11 | 13080191.13 |  | 119958052.69 | 116725109.88 | 3232942.81 | 196190620 | 1.648% |  |  | 2020-08-11 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-09-01 | 21936362.84 |  | 141894415.53 | 116725109.88 | 25169305.65 | 196190620 | 12.83% |  |  | 2020-09-01 | added 1 |  |  | 2020
IKEA Extention MoA | 2020-09-01 |  | 24766400.5 | 141894415.53 | 141491510.38 | 402905.15 | 196190620 | 0.2054% |  |  |  | cash out both |  |  | 2020
IKEA Extention MoA | 2020-09-01 | 5000000 |  | 146894415.53 | 141491510.38 | 5402905.15 | 196190620 | 2.754% |  |  | 2020-09-01 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-09-01 | 1936362.84 |  | 148830778.37 | 141491510.38 | 7339267.99 | 196190620 | 3.741% |  |  | 2020-09-01 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-10-01 |  | 10255443.06 | 148830778.37 | 151746953.44 | -2916175.07 | 196190620 | -1.486% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
IKEA Extention MoA | 2020-10-14 | 5000000 |  | 153830778.37 | 151746953.44 | 2083824.93 | 196190620 | 1.062% |  |  | 2020-10-14 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-10-14 | 981834.92 |  | 154812613.29 | 151746953.44 | 3065659.85 | 196190620 | 1.563% |  |  | 2020-10-14 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-10-22 | 1264914.16 |  | 156077527.45 | 151746953.44 | 4330574.01 | 196190620 | 2.207% |  |  | 2020-10-22 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-11-01 |  | 16609524.11 | 156077527.45 | 168356477.55 | -12278950.1 | 196190620 | -6.259% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
IKEA Extention MoA | 2020-11-19 | 1592416.38 |  | 157669943.83 | 168356477.55 | -10686533.72 | 196190620 | -5.447% |  |  | 2020-11-19 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-11-19 | 5000000 |  | 162669943.83 | 168356477.55 | -5686533.72 | 196190620 | -2.898% |  |  | 2020-11-19 | added cash in 3 |  |  | 2020
IKEA Extention MoA | 2020-12-01 |  | 5286036.68 | 162669943.83 | 173642514.23 | -10972570.4 | 196190620 | -5.593% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
IKEA Extention MoA | 2021-01-01 |  | 3462029.26 | 162669943.83 | 177104543.49 | -14434599.66 | 196190620 | -7.357% |  |  |  | cash out both |  |  | 2021
IKEA Extention MoA | 2021-01-19 | 1513146.56 |  | 164183090.39 | 177104543.49 | -12921453.1 | 196190620 | -6.586% |  |  | 2021-01-19 | added cash in 3 |  |  | 2021
IKEA Extention MoA | 2021-01-24 | 5000000 |  | 169183090.39 | 177104543.49 | -7921453.1 | 196190620 | -4.038% |  |  | 2021-01-24 | added cash in 3 |  |  | 2021
IKEA Extention MoA | 2021-01-24 | 898929.26 |  | 170082019.65 | 177104543.49 | -7022523.84 | 196190620 | -3.579% |  |  | 2021-01-24 | added cash in 3 |  |  | 2021
IKEA Extention MoA | 2021-02-01 |  | 13442010.46 | 170082019.65 | 190546553.95 | -20464534.3 | 196190620 | -10.43% |  |  |  | cash out both |  |  | 2021
IKEA Extention MoA | 2021-03-01 |  | 3809231.23 | 170082019.65 | 194355785.18 | -24273765.53 | 196190620 | -12.37% |  |  |  | cash out both |  |  | 2021
IKEA Extention MoA | 2021-03-03 | 780253.07 |  | 170862272.72 | 194355785.18 | -23493512.46 | 196190620 | -11.97% |  |  | 2021-03-03 | added cash in 3 |  |  | 2021
IKEA Extention MoA | 2021-03-15 | 5000000 |  | 175862272.72 | 194355785.18 | -18493512.46 | 196190620 | -9.426% |  |  | 2021-03-15 | added cash in 3 |  |  | 2021
IKEA Extention MoA | 2021-03-15 | 400893.31 |  | 176263166.03 | 194355785.18 | -18092619.15 | 196190620 | -9.222% |  |  | 2021-03-15 | added cash in 3 |  |  | 2021
1900
CFC Podium II | 2019-10-01 |  | 153062.78 | 0 | 153062.78 | -153062.78 | 635000000 | -0.0241% |  |  |  | cash out both |  |  | 2019
CFC Podium II | 2019-11-01 |  | 3188079.48 | 0 | 3341142.26 | -3341142.26 | 635000000 | -0.5262% |  |  |  | cash out both |  |  | 2019
CFC Podium II | 2019-12-01 |  | 10012953.38 | 0 | 13354095.64 | -13354095.64 | 635000000 | -2.103% |  |  |  | cash out both |  |  | 2019
CFC Podium II | 2020-01-01 |  | 9572180.59 | 0 | 22926276.23 | -22926276.23 | 635000000 | -3.61% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-01-21 | 25000000 |  | 25000000 | 22926276.23 | 2073723.77 | 635000000 | 0.3266% |  |  | 2020-01-21 | added 1 |  |  | 2020
CFC Podium II | 2020-01-21 | 12134944.55 |  | 37134944.55 | 22926276.23 | 14208668.32 | 635000000 | 2.238% |  |  | 2020-01-21 | added 1 |  |  | 2020
CFC Podium II | 2020-01-21 | 25000000 |  | 62134944.55 | 22926276.23 | 39208668.32 | 635000000 | 6.175% |  |  | 2020-01-21 | added 1 |  |  | 2020
CFC Podium II | 2020-02-01 |  | 31588029.16 | 62134944.55 | 54514305.39 | 7620639.16 | 635000000 | 1.2% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-02-27 | 17105598.33 |  | 79240542.88 | 54514305.39 | 24726237.49 | 635000000 | 3.894% |  |  | 2020-02-27 | added 1 |  |  | 2020
CFC Podium II | 2020-02-27 | 6067472 |  | 85308014.88 | 54514305.39 | 30793709.49 | 635000000 | 4.849% |  |  | 2020-02-27 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-02-27 | 6200445.26 |  | 91508460.14 | 54514305.39 | 36994154.75 | 635000000 | 5.826% |  |  | 2020-02-27 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-02-27 | 25000000 |  | 116508460.14 | 54514305.39 | 61994154.75 | 635000000 | 9.763% |  |  | 2020-02-27 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-03-01 |  | 21545591.32 | 116508460.14 | 76059896.71 | 40448563.43 | 635000000 | 6.37% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-03-31 | 12263695.64 |  | 128772155.78 | 76059896.71 | 52712259.07 | 635000000 | 8.301% |  |  | 2020-03-31 | added 1 |  |  | 2020
CFC Podium II | 2020-04-01 |  | 12872110.15 | 128772155.78 | 88932006.86 | 39840148.92 | 635000000 | 6.274% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-05-01 |  | 8997379.04 | 128772155.78 | 97929385.9 | 30842769.88 | 635000000 | 4.857% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-06-01 |  | 42998694.33 | 128772155.78 | 140928080.23 | -12155924.45 | 635000000 | -1.914% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-06-02 | 88910222.55 |  | 217682378.33 | 140928080.23 | 76754298.1 | 635000000 | 12.09% |  |  | 2020-06-02 | added 1 |  |  | 2020
CFC Podium II | 2020-07-01 |  | 24580639.89 | 217682378.33 | 165508720.12 | 52173658.21 | 635000000 | 8.216% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-07-09 | 19510038.16 |  | 237192416.49 | 165508720.12 | 71683696.37 | 635000000 | 11.29% |  |  | 2020-07-09 | added 1 |  |  | 2020
CFC Podium II | 2020-08-01 |  | 14981487.26 | 237192416.49 | 180490207.38 | 56702209.11 | 635000000 | 8.929% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-08-06 | 21459125.32 |  | 258651541.81 | 180490207.38 | 78161334.43 | 635000000 | 12.31% |  |  | 2020-08-06 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-09-01 |  | 43690870.72 | 258651541.81 | 224181078.1 | 34470463.71 | 635000000 | 5.428% |  |  |  | cash out both |  |  | 2020
CFC Podium II | 2020-09-03 | 24499895.82 |  | 283151437.63 | 224181078.1 | 58970359.53 | 635000000 | 9.287% |  |  | 2020-09-03 | added 1 |  |  | 2020
CFC Podium II | 2020-09-30 | 21426363.61 |  | 304577801.24 | 224181078.1 | 80396723.14 | 635000000 | 12.66% |  |  | 2020-09-30 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-09-30 | 18022232.23 |  | 322600033.47 | 224181078.1 | 98418955.37 | 635000000 | 15.5% |  |  | 2020-09-30 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-10-01 |  | 24294894.3 | 322600033.47 | 248475972.4 | 74124061.07 | 635000000 | 11.67% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
CFC Podium II | 2020-10-28 | 18030566.05 |  | 340630599.52 | 248475972.4 | 92154627.12 | 635000000 | 14.51% |  |  | 2020-10-28 | added 1 |  |  | 2020
CFC Podium II | 2020-11-01 |  | 17926727 | 340630599.52 | 266402699.4 | 74227900.12 | 635000000 | 11.69% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
CFC Podium II | 2020-12-01 |  | 20992902.49 | 340630599.52 | 287395601.89 | 53234997.63 | 635000000 | 8.383% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
CFC Podium II | 2020-12-06 | 11033207.32 |  | 351663806.84 | 287395601.89 | 64268204.95 | 635000000 | 10.12% |  |  | 2020-12-06 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-12-06 | 18657986.99 |  | 370321793.83 | 287395601.89 | 82926191.94 | 635000000 | 13.06% |  |  | 2020-12-06 | added cash in 3 |  |  | 2020
CFC Podium II | 2020-12-27 | 23213756.67 |  | 393535550.5 | 287395601.89 | 106139948.61 | 635000000 | 16.71% |  |  | 2020-12-27 | added 1 |  |  | 2020
CFC Podium II | 2021-01-01 |  | 22504065.09 | 393535550.5 | 309899666.98 | 83635883.52 | 635000000 | 13.17% |  |  |  | cash out both |  |  | 2021
CFC Podium II | 2021-02-01 |  | 17327439.37 | 393535550.5 | 327227106.35 | 66308444.15 | 635000000 | 10.44% |  |  |  | cash out both |  |  | 2021
CFC Podium II | 2021-02-10 | 19708943.72 |  | 413244494.22 | 327227106.35 | 86017387.87 | 635000000 | 13.55% |  |  | 2021-02-10 | added cash in 3 |  |  | 2021
CFC Podium II | 2021-03-01 |  | 30165688.98 | 413244494.22 | 357392795.33 | 55851698.89 | 635000000 | 8.796% |  |  |  | cash out both |  |  | 2021
CFC Podium II | 2021-03-08 | 27514205.72 |  | 440758699.94 | 357392795.33 | 83365904.61 | 635000000 | 13.13% |  |  | 2021-03-08 | added cash in 3 |  |  | 2021
CFC Podium II | 2021-03-08 | 12865453.91 |  | 453624153.85 | 357392795.33 | 96231358.52 | 635000000 | 15.15% |  |  | 2021-03-08 | added cash in 3 |  |  | 2021
CFC Podium II | 2021-04-04 | 22871121.16 |  | 476495275.01 | 357392795.33 | 119102479.68 | 635000000 | 18.76% |  |  | 2021-04-04 | added cash in 3 |  |  | 2021
CFC Podium II | 2021-04-20 | 15047803.35 |  | 491543078.36 | 357392795.33 | 134150283.03 | 635000000 | 21.13% |  |  | 2021-04-20 | added cash in 3 |  |  | 2021
1900
Josef Tito Bridge L&L | 2019-11-01 |  | 20000 | 0 | 20000 | -20000 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Josef Tito Bridge L&L | 2020-01-01 |  | 6705 | 0 | 26705 | -26705 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
1900
Espiko Bridge L&L | 2019-11-01 |  | 77065.6 | 0 | 77065.6 | -77065.6 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Espiko Bridge L&L | 2019-12-01 |  | 15209.6 | 0 | 92275.2 | -92275.2 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Espiko Bridge L&L | 2020-01-01 |  | 12000 | 0 | 104275.2 | -104275.2 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
Espiko Bridge L&L | 2020-03-01 |  | 6000 | 0 | 110275.2 | -110275.2 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
Espiko Bridge L&L | 2020-04-01 |  | 3000 | 0 | 113275.2 | -113275.2 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
1900
MR3 Bridge L&L | 2019-10-01 |  | 26700 | 0 | 26700 | -26700 | 1520085 | -1.756% |  |  |  | cash out both |  |  | 2019
MR3 Bridge L&L | 2019-11-01 |  | 73154.6 | 0 | 99854.6 | -99854.6 | 1520085 | -6.569% |  |  |  | cash out both |  |  | 2019
MR3 Bridge L&L | 2019-12-01 |  | 170728.56 | 0 | 270583.16 | -270583.16 | 1520085 | -17.8% |  |  |  | cash out both |  |  | 2019
MR3 Bridge L&L | 2020-01-01 |  | 67553.93 | 0 | 338137.09 | -338137.09 | 1520085 | -22.24% |  |  |  | cash out both |  |  | 2020
MR3 Bridge L&L | 2020-02-01 |  | 87924.37 | 0 | 426061.46 | -426061.46 | 1520085 | -28.03% |  |  |  | cash out both |  |  | 2020
MR3 Bridge L&L | 2020-03-01 |  | 3044 | 0 | 429105.46 | -429105.46 | 1520085 | -28.23% |  |  |  | cash out both |  |  | 2020
MR3 Bridge L&L | 2020-05-01 |  | 16758.44 | 0 | 445863.9 | -445863.9 | 1520085 | -29.33% |  |  |  | cash out both |  |  | 2020
MR3 Bridge L&L | 2020-07-01 |  | 21050 | 0 | 466913.9 | -466913.9 | 1520085 | -30.72% |  |  |  | cash out both |  |  | 2020
MR3 Bridge L&L | 2021-01-06 | 714790 |  | 714790 | 466913.9 | 247876.1 | 1520085 | 16.31% |  |  | 2021-01-06 | added cash in 3 |  |  | 2021
MR3 Bridge L&L | 2021-02-01 |  | 4788.11 | 714790 | 471702.01 | 243087.99 | 1520085 | 15.99% |  |  |  | cash out both |  |  | 2021
1900
El Sewedy Univeristy 2 Phase 2 | 2018-08-01 |  | 603460 | 0 | 603460 | -603460 | 262378822 | -0.23% |  |  |  | cash out both |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-08-14 | 2898141.12 |  | 2898141.12 | 603460 | 2294681.12 | 262378822 | 0.8746% |  |  | 2018-08-14 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-09-01 |  | 5393496.53 | 2898141.12 | 5996956.53 | -3098815.41 | 262378822 | -1.181% |  |  |  | cash out both |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-09-12 | 8589000 |  | 11487141.12 | 5996956.53 | 5490184.59 | 262378822 | 2.092% |  |  | 2018-09-12 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-10-01 |  | 3914541.12 | 11487141.12 | 9911497.65 | 1575643.47 | 262378822 | 0.6005% |  |  |  | cash out both |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-10-11 | 1917993.24 |  | 13405134.36 | 9911497.65 | 3493636.71 | 262378822 | 1.332% |  |  | 2018-10-11 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-10-23 | 3110956.56 |  | 16516090.92 | 9911497.65 | 6604593.27 | 262378822 | 2.517% |  |  | 2018-10-23 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-11-01 |  | 4135515.18 | 16516090.92 | 14047012.83 | 2469078.09 | 262378822 | 0.941% |  |  |  | cash out both |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-11-06 | 881744.36 |  | 17397835.28 | 14047012.83 | 3350822.45 | 262378822 | 1.277% |  |  | 2018-11-06 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-11-15 | 6754267.57 |  | 24152102.85 | 14047012.83 | 10105090.02 | 262378822 | 3.851% |  |  | 2018-11-15 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-12-01 |  | 5706049.89 | 24152102.85 | 19753062.72 | 4399040.13 | 262378822 | 1.677% |  |  |  | cash out both |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-12-12 | 1214989 |  | 25367091.85 | 19753062.72 | 5614029.13 | 262378822 | 2.14% |  |  | 2018-12-12 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2018-12-20 | 3212953.45 |  | 28580045.3 | 19753062.72 | 8826982.58 | 262378822 | 3.364% |  |  | 2018-12-20 | added cash in 3 |  |  | 2018
El Sewedy Univeristy 2 Phase 2 | 2019-01-01 |  | 17642188.83 | 28580045.3 | 37395251.55 | -8815206.25 | 262378822 | -3.36% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-01-10 | 1204112.86 |  | 29784158.16 | 37395251.55 | -7611093.39 | 262378822 | -2.901% |  |  | 2019-01-10 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-01-17 | 24971065.75 |  | 54755223.91 | 37395251.55 | 17359972.36 | 262378822 | 6.616% |  |  | 2019-01-17 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-01-31 | 142702.12 |  | 54897926.03 | 37395251.55 | 17502674.48 | 262378822 | 6.671% |  |  | 2019-01-31 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-01-31 | 3208255.76 |  | 58106181.79 | 37395251.55 | 20710930.24 | 262378822 | 7.894% |  |  | 2019-01-31 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-01-31 | 185635.06 |  | 58291816.85 | 37395251.55 | 20896565.3 | 262378822 | 7.964% |  |  | 2019-01-31 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-02-01 |  | 14854000.37 | 58291816.85 | 52249251.92 | 6042564.93 | 262378822 | 2.303% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-02-07 | 8000000 |  | 66291816.85 | 52249251.92 | 14042564.93 | 262378822 | 5.352% |  |  | 2019-02-07 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-02-19 | 4527299.68 |  | 70819116.53 | 52249251.92 | 18569864.61 | 262378822 | 7.078% |  |  | 2019-02-19 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-02-19 | 284879.77 |  | 71103996.3 | 52249251.92 | 18854744.38 | 262378822 | 7.186% |  |  | 2019-02-19 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-02-19 | 235901.48 |  | 71339897.78 | 52249251.92 | 19090645.86 | 262378822 | 7.276% |  |  | 2019-02-19 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-03-01 |  | 14374015.11 | 71339897.78 | 66623267.03 | 4716630.75 | 262378822 | 1.798% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-03-10 | 12000000 |  | 83339897.78 | 66623267.03 | 16716630.75 | 262378822 | 6.371% |  |  | 2019-03-10 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-03-10 | 1727255.6 |  | 85067153.38 | 66623267.03 | 18443886.35 | 262378822 | 7.029% |  |  | 2019-03-10 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-03-10 | 3185421.17 |  | 88252574.55 | 66623267.03 | 21629307.52 | 262378822 | 8.244% |  |  | 2019-03-10 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-03-21 | 7457797.24 |  | 95710371.79 | 66623267.03 | 29087104.76 | 262378822 | 11.09% |  |  | 2019-03-21 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-03-28 | 5785718.63 |  | 101496090.42 | 66623267.03 | 34872823.39 | 262378822 | 13.29% |  |  | 2019-03-28 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-04-01 |  | 17369715.11 | 101496090.42 | 83992982.14 | 17503108.28 | 262378822 | 6.671% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-04-04 | 4931187 |  | 106427277.42 | 83992982.14 | 22434295.28 | 262378822 | 8.55% |  |  | 2019-04-04 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-04-22 | 1785482.76 |  | 108212760.18 | 83992982.14 | 24219778.04 | 262378822 | 9.231% |  |  | 2019-04-22 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-04-23 | 72777.03 |  | 108285537.21 | 83992982.14 | 24292555.07 | 262378822 | 9.259% |  |  | 2019-04-23 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-04-30 | 2278076.64 |  | 110563613.85 | 83992982.14 | 26570631.71 | 262378822 | 10.13% |  |  | 2019-04-30 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-05-01 |  | 27974414.64 | 110563613.85 | 111967396.78 | -1403782.93 | 262378822 | -0.535% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-05-13 | 24218860.89 |  | 134782474.74 | 111967396.78 | 22815077.96 | 262378822 | 8.695% |  |  | 2019-05-13 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-06-01 |  | 17825387.85 | 134782474.74 | 129792784.63 | 4989690.11 | 262378822 | 1.902% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-06-19 | 18660913.61 |  | 153443388.35 | 129792784.63 | 23650603.72 | 262378822 | 9.014% |  |  | 2019-06-19 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-06-19 | 8055178 |  | 161498566.35 | 129792784.63 | 31705781.72 | 262378822 | 12.08% |  |  | 2019-06-19 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-07-01 |  | 13814354.38 | 161498566.35 | 143607139.01 | 17891427.34 | 262378822 | 6.819% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-07-11 | 15000000 |  | 176498566.35 | 143607139.01 | 32891427.34 | 262378822 | 12.54% |  |  | 2019-07-11 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-07-30 | 17000000 |  | 193498566.35 | 143607139.01 | 49891427.34 | 262378822 | 19.02% |  |  | 2019-07-30 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-08-01 |  | 20494514.51 | 193498566.35 | 164101653.52 | 29396912.83 | 262378822 | 11.2% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-09-01 |  | 22187588.75 | 193498566.35 | 186289242.27 | 7209324.08 | 262378822 | 2.748% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-09-04 | 5410862.51 |  | 198909428.86 | 186289242.27 | 12620186.59 | 262378822 | 4.81% |  |  | 2019-09-04 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-09-04 | 2625161.63 |  | 201534590.49 | 186289242.27 | 15245348.22 | 262378822 | 5.81% |  |  | 2019-09-04 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-09-16 | 12292368.36 |  | 213826958.85 | 186289242.27 | 27537716.58 | 262378822 | 10.5% |  |  | 2019-09-16 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-09-16 | 19287810.69 |  | 233114769.54 | 186289242.27 | 46825527.27 | 262378822 | 17.85% |  |  | 2019-09-16 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-10-01 |  | 11934828.43 | 233114769.54 | 198224070.7 | 34890698.84 | 262378822 | 13.3% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-10-08 | 20919758.57 |  | 254034528.11 | 198224070.7 | 55810457.41 | 262378822 | 21.27% |  |  | 2019-10-08 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-11-01 |  | 6819992.36 | 254034528.11 | 205044063.06 | 48990465.05 | 262378822 | 18.67% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-11-01 |  | 5286433.51 | 254034528.11 | 210330496.57 | 43704031.54 | 262378822 | 16.66% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-11-28 | 31397824.8 |  | 285432352.91 | 210330496.57 | 75101856.34 | 262378822 | 28.62% |  |  | 2019-11-28 | added cash in 3 |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-12-01 |  | 6378760.03 | 285432352.91 | 216709256.6 | 68723096.31 | 262378822 | 26.19% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2019-12-01 |  | 36382947.09 | 285432352.91 | 253092203.69 | 32340149.22 | 262378822 | 12.33% |  |  |  | cash out both |  |  | 2019
El Sewedy Univeristy 2 Phase 2 | 2020-01-01 |  | 11350643.25 | 285432352.91 | 264442846.94 | 20989505.97 | 262378822 | 8% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-01-01 |  | 1662180.52 | 285432352.91 | 266105027.46 | 19327325.45 | 262378822 | 7.366% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-02-01 |  | 8343038.66 | 285432352.91 | 274448066.12 | 10984286.79 | 262378822 | 4.186% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-02-01 |  | 5506362.99 | 285432352.91 | 279954429.11 | 5477923.8 | 262378822 | 2.088% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-02-11 | 267208.33 |  | 285699561.24 | 279954429.11 | 5745132.13 | 262378822 | 2.19% |  |  | 2020-02-11 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-02-11 | 1120262.65 |  | 286819823.89 | 279954429.11 | 6865394.78 | 262378822 | 2.617% |  |  | 2020-02-11 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-02-11 | 253659.18 |  | 287073483.07 | 279954429.11 | 7119053.96 | 262378822 | 2.713% |  |  | 2020-02-11 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-03-01 |  | 11778131.55 | 287073483.07 | 291732560.66 | -4659077.59 | 262378822 | -1.776% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-03-01 |  | 2412972.58 | 287073483.07 | 294145533.24 | -7072050.17 | 262378822 | -2.695% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-04-01 |  | 19767993.36 | 287073483.07 | 313913526.6 | -26840043.53 | 262378822 | -10.23% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-04-01 |  | 626612.03 | 287073483.07 | 314540138.63 | -27466655.56 | 262378822 | -10.47% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-05-01 |  | 21346890.25 | 287073483.07 | 335887028.88 | -48813545.81 | 262378822 | -18.6% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-05-01 |  | 2607589.67 | 287073483.07 | 338494618.55 | -51421135.48 | 262378822 | -19.6% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-05-12 | 21059913.35 |  | 308133396.42 | 338494618.55 | -30361222.13 | 262378822 | -11.57% |  |  | 2020-05-12 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-05-31 | 7788095.22 |  | 315921491.64 | 338494618.55 | -22573126.91 | 262378822 | -8.603% |  |  | 2020-05-31 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-06-01 |  | 29004240.72 | 315921491.64 | 367498859.27 | -51577367.63 | 262378822 | -19.66% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-06-01 |  | 667921 | 315921491.64 | 368166780.27 | -52245288.63 | 262378822 | -19.91% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-06-07 | 23262698.71 |  | 339184190.35 | 368166780.27 | -28982589.92 | 262378822 | -11.05% |  |  | 2020-06-07 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-06-29 | 18322600.95 |  | 357506791.3 | 368166780.27 | -10659988.97 | 262378822 | -4.063% |  |  | 2020-06-29 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-07-01 |  | 63284411.02 | 357506791.3 | 431451191.29 | -73944399.99 | 262378822 | -28.18% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-07-01 |  | 576178.49 | 357506791.3 | 432027369.78 | -74520578.48 | 262378822 | -28.4% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-07-19 | 10000000 |  | 367506791.3 | 432027369.78 | -64520578.48 | 262378822 | -24.59% |  |  | 2020-07-19 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-08-01 |  | 5334273.03 | 367506791.3 | 437361642.81 | -69854851.51 | 262378822 | -26.62% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-08-01 |  | 876386.26 | 367506791.3 | 438238029.07 | -70731237.77 | 262378822 | -26.96% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-08-16 | 1607563.05 |  | 369114354.35 | 438238029.07 | -69123674.72 | 262378822 | -26.34% |  |  | 2020-08-16 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-09-01 |  | 42253061.29 | 369114354.35 | 480491090.36 | -111376736.01 | 262378822 | -42.45% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-09-01 |  | 323916.91 | 369114354.35 | 480815007.27 | -111700652.92 | 262378822 | -42.57% |  |  |  | cash out both |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-09-01 | 25755604.75 |  | 394869959.1 | 480815007.27 | -85945048.17 | 262378822 | -32.76% |  |  | 2020-09-01 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-09-01 | 20000000 |  | 414869959.1 | 480815007.27 | -65945048.17 | 262378822 | -25.13% |  |  | 2020-09-01 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-09-14 | 8739144.88 |  | 423609103.98 | 480815007.27 | -57205903.29 | 262378822 | -21.8% |  |  | 2020-09-14 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-10-01 |  | 26752963.95 | 423609103.98 | 507567971.22 | -83958867.24 | 262378822 | -32% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-11-01 |  | 22562634.05 | 423609103.98 | 530130605.27 | -106521501.29 | 262378822 | -40.6% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-11-29 | 9765894.56 |  | 433374998.54 | 530130605.27 | -96755606.73 | 262378822 | -36.88% |  |  | 2020-11-29 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-11-30 | 6845790.37 |  | 440220788.91 | 530130605.27 | -89909816.36 | 262378822 | -34.27% |  |  | 2020-11-30 | added cash in 3 |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2020-12-01 |  | 27257085.67 | 440220788.91 | 557387690.94 | -117166902.03 | 262378822 | -44.66% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
El Sewedy Univeristy 2 Phase 2 | 2021-01-01 |  | 16359908.1 | 440220788.91 | 573747599.04 | -133526810.13 | 262378822 | -50.89% |  |  |  | cash out both |  |  | 2021
El Sewedy Univeristy 2 Phase 2 | 2021-01-10 | 13851401.63 |  | 454072190.54 | 573747599.04 | -119675408.5 | 262378822 | -45.61% |  |  | 2021-01-10 | added cash in 3 |  |  | 2021
El Sewedy Univeristy 2 Phase 2 | 2021-02-01 |  | 3398566.17 | 454072190.54 | 577146165.21 | -123073974.67 | 262378822 | -46.91% |  |  |  | cash out both |  |  | 2021
El Sewedy Univeristy 2 Phase 2 | 2021-03-01 |  | 12657223.86 | 454072190.54 | 589803389.07 | -135731198.53 | 262378822 | -51.73% |  |  |  | cash out both |  |  | 2021
El Sewedy Univeristy 2 Phase 2 | 2021-03-18 | 1023770.56 |  | 455095961.1 | 589803389.07 | -134707427.97 | 262378822 | -51.34% |  |  | 2021-03-18 | added cash in 3 |  |  | 2021
El Sewedy Univeristy 2 Phase 2 | 2021-03-31 | 53713.92 |  | 455149675.02 | 589803389.07 | -134653714.05 | 262378822 | -51.32% |  |  | 2021-03-31 | added cash in 3 |  |  | 2021
El Sewedy Univeristy 2 Phase 2 | 2021-04-05 | 23340124.9 |  | 478489799.92 | 589803389.07 | -111313589.15 | 262378822 | -42.42% |  |  | 2021-04-05 | added cash in 3 |  |  | 2021
1900
Mehwar El Salam Axis L&L | 2019-12-01 |  | 235890.58 | 0 | 235890.58 | -235890.58 | 16843027 | -1.401% |  |  |  | cash out both |  |  | 2019
Mehwar El Salam Axis L&L | 2020-01-01 |  | 316868.75 | 0 | 552759.33 | -552759.33 | 16843027 | -3.282% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-02-01 |  | 692970.01 | 0 | 1245729.34 | -1245729.34 | 16843027 | -7.396% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-03-01 |  | 78544 | 0 | 1324273.34 | -1324273.34 | 16843027 | -7.862% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-04-01 |  | 221945.5 | 0 | 1546218.84 | -1546218.84 | 16843027 | -9.18% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-05-01 |  | 189351.98 | 0 | 1735570.82 | -1735570.82 | 16843027 | -10.3% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-06-01 |  | 19303 | 0 | 1754873.82 | -1754873.82 | 16843027 | -10.42% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-08-01 |  | 181000 | 0 | 1935873.82 | -1935873.82 | 16843027 | -11.49% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-09-01 |  | 290812.5 | 0 | 2226686.32 | -2226686.32 | 16843027 | -13.22% |  |  |  | cash out both |  |  | 2020
Mehwar El Salam Axis L&L | 2020-10-01 |  | 1400 | 0 | 2228086.32 | -2228086.32 | 16843027 | -13.23% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Mehwar El Salam Axis L&L | 2020-11-01 |  | 7612.81 | 0 | 2235699.13 | -2235699.13 | 16843027 | -13.27% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Mehwar El Salam Axis L&L | 2021-01-01 |  | 18803.2 | 0 | 2254502.33 | -2254502.33 | 16843027 | -13.39% |  |  |  | cash out both |  |  | 2021
Mehwar El Salam Axis L&L | 2021-01-06 | 714790 |  | 714790 | 2254502.33 | -1539712.33 | 16843027 | -9.142% |  |  | 2021-01-06 | added 1 |  |  | 2021
Mehwar El Salam Axis L&L | 2021-03-01 |  | 14043.58 | 714790 | 2268545.91 | -1553755.91 | 16843027 | -9.225% |  |  |  | cash out both |  |  | 2021
1900
El Hegaz Square Bridge | 2019-12-01 |  | 270914.04 | 0 | 270914.04 | -270914.04 | 138370050 | -0.1958% |  |  |  | cash out both |  |  | 2019
El Hegaz Square Bridge | 2020-01-01 |  | 1764668.39 | 0 | 2035582.43 | -2035582.43 | 138370050 | -1.471% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-02-01 |  | 13273301.11 | 0 | 15308883.54 | -15308883.54 | 138370050 | -11.06% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-03-01 |  | 9584322.98 | 0 | 24893206.52 | -24893206.52 | 138370050 | -17.99% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-03-26 | 40000000 |  | 40000000 | 24893206.52 | 15106793.48 | 138370050 | 10.92% |  |  | 2020-03-26 | added 1 |  |  | 2020
El Hegaz Square Bridge | 2020-04-01 |  | 2279323.76 | 40000000 | 27172530.28 | 12827469.72 | 138370050 | 9.27% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-05-01 |  | 1894887.1 | 40000000 | 29067417.38 | 10932582.62 | 138370050 | 7.901% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-05-30 | 18649995 |  | 58649995 | 29067417.38 | 29582577.62 | 138370050 | 21.38% |  |  | 2020-05-30 | added cash in 3 |  |  | 2020
El Hegaz Square Bridge | 2020-06-01 |  | 4010557.8 | 58649995 | 33077975.18 | 25572019.82 | 138370050 | 18.48% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-06-25 | 54393250 |  | 113043245 | 33077975.18 | 79965269.82 | 138370050 | 57.79% |  |  | 2020-06-25 | added cash in 3 |  |  | 2020
El Hegaz Square Bridge | 2020-07-01 |  | 2386717.32 | 113043245 | 35464692.5 | 77578552.5 | 138370050 | 56.07% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-08-01 |  | 24538.52 | 113043245 | 35489231.02 | 77554013.98 | 138370050 | 56.05% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-09-01 |  | 487977.17 | 113043245 | 35977208.19 | 77066036.81 | 138370050 | 55.7% |  |  |  | cash out both |  |  | 2020
El Hegaz Square Bridge | 2020-10-01 |  | 14092.29 | 113043245 | 35991300.48 | 77051944.52 | 138370050 | 55.69% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
El Hegaz Square Bridge | 2020-11-01 |  | 117488.53 | 113043245 | 36108789.01 | 76934455.99 | 138370050 | 55.6% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
El Hegaz Square Bridge | 2020-12-01 |  | 517164.89 | 113043245 | 36625953.9 | 76417291.1 | 138370050 | 55.23% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
El Hegaz Square Bridge | 2020-12-22 | 955520 |  | 113998765 | 36625953.9 | 77372811.1 | 138370050 | 55.92% |  |  | 2020-12-22 | added cash in 3 |  |  | 2020
El Hegaz Square Bridge | 2021-01-01 |  | 107350 | 113998765 | 36733303.9 | 77265461.1 | 138370050 | 55.84% |  |  |  | cash out both |  |  | 2021
El Hegaz Square Bridge | 2021-02-01 |  | 5947.45 | 113998765 | 36739251.35 | 77259513.65 | 138370050 | 55.84% |  |  |  | cash out both |  |  | 2021
El Hegaz Square Bridge | 2021-03-01 |  | 247498.4 | 113998765 | 36986749.75 | 77012015.25 | 138370050 | 55.66% |  |  |  | cash out both |  |  | 2021
1900
Ring Road 1 Maryotyah | 2020-01-01 |  | 98517 | 0 | 98517 | -98517 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-02-01 |  | 3036236.37 | 0 | 3134753.37 | -3134753.37 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-03-01 |  | 3845631.15 | 0 | 6980384.52 | -6980384.52 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-04-01 |  | 1363317.62 | 0 | 8343702.14 | -8343702.14 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-05-01 |  | 1763082.3 | 0 | 10106784.44 | -10106784.44 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-06-01 |  | 5716969.29 | 0 | 15823753.73 | -15823753.73 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-07-01 |  | 7560973.77 | 0 | 23384727.5 | -23384727.5 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-08-01 |  | 4645579.42 | 0 | 28030306.92 | -28030306.92 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-09-01 |  | 6414119.45 | 0 | 34444426.37 | -34444426.37 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road 1 Maryotyah | 2020-10-01 |  | 11835676.54 | 0 | 46280102.91 | -46280102.91 | #N/A | #N/A |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Ring Road 1 Maryotyah | 2020-10-11 | 34159591.2 |  | 34159591.2 | 46280102.91 | -12120511.71 | #N/A | #N/A |  |  | 2020-10-11 | added cash in 3 |  |  | 2020
Ring Road 1 Maryotyah | 2020-12-13 | 15945365.65 |  | 50104956.85 | 46280102.91 | 3824853.94 | #N/A | #N/A |  |  | 2020-12-13 | added cash in 3 |  |  | 2020
Ring Road 1 Maryotyah | 2021-01-01 |  | 13636545.56 | 50104956.85 | 59916648.47 | -9811691.62 | #N/A | #N/A |  |  |  | cash out both |  |  | 2021
Ring Road 1 Maryotyah | 2021-02-01 |  | 21809303.01 | 50104956.85 | 81725951.48 | -31620994.63 | #N/A | #N/A |  |  |  | cash out both |  |  | 2021
Ring Road 1 Maryotyah | 2021-02-10 | 7157243.6 |  | 57262200.45 | 81725951.48 | -24463751.03 | #N/A | #N/A |  |  | 2021-02-10 | added cash in 3 |  |  | 2021
Ring Road 1 Maryotyah | 2021-03-01 |  | 24829331.43 | 57262200.45 | 106555282.91 | -49293082.46 | #N/A | #N/A |  |  |  | cash out both |  |  | 2021
Ring Road 1 Maryotyah | 2021-03-07 | 10759736.15 |  | 68021936.6 | 106555282.91 | -38533346.31 | #N/A | #N/A |  |  | 2021-03-07 | added cash in 3 |  |  | 2021
Ring Road 1 Maryotyah | 2021-03-09 | 45719198.4 |  | 113741135 | 106555282.91 | 7185852.09 | #N/A | #N/A |  |  | 2021-03-09 | added cash in 3 |  |  | 2021
Ring Road 1 Maryotyah | 2021-03-31 | 4521989.75 |  | 118263124.75 | 106555282.91 | 11707841.84 | #N/A | #N/A |  |  | 2021-03-31 | added cash in 3 |  |  | 2021
Ring Road 1 Maryotyah | 2021-04-20 | 6026340.35 |  | 124289465.1 | 106555282.91 | 17734182.19 | #N/A | #N/A |  |  | 2021-04-20 | added cash in 3 |  |  | 2021
1900
Marina Inland Marassi Pkg 162 | 2020-01-01 |  | 1128089.7 | 0 | 1128089.7 | -1128089.7 | 434504076.4286 | -0.2596% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-02-01 | 7681619.5 | 4666410 | 7681619.5 | 5794499.7 | 1887119.8 | 434504076.4286 | 0.4343% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-03-01 |  | 2473992.92 | 7681619.5 | 8268492.62 | -586873.12 | 434504076.4286 | -0.1351% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-03-29 | 24950583 |  | 32632202.5 | 8268492.62 | 24363709.88 | 434504076.4286 | 5.607% |  |  | 2020-03-29 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-04-01 | 7794726.52 | 1512801.08 | 40426929.02 | 9781293.7 | 30645635.32 | 434504076.4286 | 7.053% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-05-01 |  | 1666357.85 | 40426929.02 | 11447651.55 | 28979277.47 | 434504076.4286 | 6.67% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-06-01 |  | 5500379.1 | 40426929.02 | 16948030.65 | 23478898.37 | 434504076.4286 | 5.404% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-06-10 | 6124877.69 |  | 46551806.71 | 16948030.65 | 29603776.06 | 434504076.4286 | 6.813% |  |  | 2020-06-10 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-07-01 |  | 5818137.37 | 46551806.71 | 22766168.02 | 23785638.69 | 434504076.4286 | 5.474% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-07-08 | 4824045.39 |  | 51375852.1 | 22766168.02 | 28609684.08 | 434504076.4286 | 6.584% |  |  | 2020-07-08 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-08-01 |  | 5975447.82 | 51375852.1 | 28741615.84 | 22634236.26 | 434504076.4286 | 5.209% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-08-06 | 7215874.21 |  | 58591726.31 | 28741615.84 | 29850110.47 | 434504076.4286 | 6.87% |  |  | 2020-08-06 | added 1 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-08-10 | 1068966.43 |  | 59660692.74 | 28741615.84 | 30919076.9 | 434504076.4286 | 7.116% |  |  | 2020-08-10 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-08-19 | 7215874.21 |  | 66876566.95 | 28741615.84 | 38134951.11 | 434504076.4286 | 8.777% |  |  | 2020-08-19 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-09-01 |  | 7587470.83 | 66876566.95 | 36329086.67 | 30547480.28 | 434504076.4286 | 7.03% |  |  |  | cash out both |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-09-03 | 829293.83 |  | 67705860.78 | 36329086.67 | 31376774.11 | 434504076.4286 | 7.221% |  |  | 2020-09-03 | added 1 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-09-07 | 2977091.11 |  | 70682951.89 | 36329086.67 | 34353865.22 | 434504076.4286 | 7.906% |  |  | 2020-09-07 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-09-07 | 826293.83 |  | 71509245.72 | 36329086.67 | 35180159.05 | 434504076.4286 | 8.097% |  |  | 2020-09-07 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-09-21 | 9432027.72 |  | 80941273.44 | 36329086.67 | 44612186.77 | 434504076.4286 | 10.27% |  |  | 2020-09-21 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-10-01 |  | 9409439.63 | 80941273.44 | 45738526.3 | 35202747.14 | 434504076.4286 | 8.102% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-10-07 | 6845695.77 |  | 87786969.21 | 45738526.3 | 42048442.91 | 434504076.4286 | 9.677% |  |  | 2020-10-07 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-10-15 | 1584302.83 |  | 89371272.04 | 45738526.3 | 43632745.74 | 434504076.4286 | 10.04% |  |  | 2020-10-15 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-10-15 | 78430.21 |  | 89449702.25 | 45738526.3 | 43711175.95 | 434504076.4286 | 10.06% |  |  | 2020-10-15 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-10-15 | 9889305.11 |  | 99339007.36 | 45738526.3 | 53600481.06 | 434504076.4286 | 12.34% |  |  | 2020-10-15 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-10-18 | 1584302 |  | 100923309.36 | 45738526.3 | 55184783.06 | 434504076.4286 | 12.7% |  |  | 2020-10-18 | added 1 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-11-01 |  | 9587251.93 | 100923309.36 | 55325778.23 | 45597531.13 | 434504076.4286 | 10.49% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-11-16 | 3782501.29 |  | 104705810.65 | 55325778.23 | 49380032.42 | 434504076.4286 | 11.36% |  |  | 2020-11-16 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-11-30 | 1223560.05 |  | 105929370.7 | 55325778.23 | 50603592.47 | 434504076.4286 | 11.65% |  |  | 2020-11-30 | added 1 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-11-30 | 720699.2 |  | 106650069.9 | 55325778.23 | 51324291.67 | 434504076.4286 | 11.81% |  |  | 2020-11-30 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-12-01 |  | 8842500.9 | 106650069.9 | 64168279.13 | 42481790.77 | 434504076.4286 | 9.777% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-12-03 | 13282474.22 |  | 119932544.12 | 64168279.13 | 55764264.99 | 434504076.4286 | 12.83% |  |  | 2020-12-03 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-12-21 | 159865.31 |  | 120092409.43 | 64168279.13 | 55924130.3 | 434504076.4286 | 12.87% |  |  | 2020-12-21 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2020-12-28 | 6255172.17 |  | 126347581.6 | 64168279.13 | 62179302.47 | 434504076.4286 | 14.31% |  |  | 2020-12-28 | added cash in 3 |  |  | 2020
Marina Inland Marassi Pkg 162 | 2021-01-01 |  | 7596676.65 | 126347581.6 | 71764955.78 | 54582625.82 | 434504076.4286 | 12.56% |  |  |  | cash out both |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-01-11 | 4922193.5 |  | 131269775.1 | 71764955.78 | 59504819.32 | 434504076.4286 | 13.69% |  |  | 2021-01-11 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-01-20 | 7840185.48 |  | 139109960.58 | 71764955.78 | 67345004.8 | 434504076.4286 | 15.5% |  |  | 2021-01-20 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-02-01 | 760409.01 |  | 139870369.59 | 71764955.78 | 68105413.81 | 434504076.4286 | 15.67% |  |  | 2021-02-01 | added 1 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-02-01 |  | 6046528.83 | 139870369.59 | 77811484.61 | 62058884.98 | 434504076.4286 | 14.28% |  |  |  | cash out both |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-02-03 | 277522.63 |  | 140147892.22 | 77811484.61 | 62336407.61 | 434504076.4286 | 14.35% |  |  | 2021-02-03 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-02-03 | 760409.01 |  | 140908301.23 | 77811484.61 | 63096816.62 | 434504076.4286 | 14.52% |  |  | 2021-02-03 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-02-22 | 6050639.77 |  | 146958941 | 77811484.61 | 69147456.39 | 434504076.4286 | 15.91% |  |  | 2021-02-22 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-02-24 | 4608392 |  | 151567333 | 77811484.61 | 73755848.39 | 434504076.4286 | 16.97% |  |  | 2021-02-24 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-03-01 |  | 6140780.47 | 151567333 | 83952265.08 | 67615067.92 | 434504076.4286 | 15.56% |  |  |  | cash out both |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-03-08 | 451906.96 |  | 152019239.96 | 83952265.08 | 68066974.88 | 434504076.4286 | 15.67% |  |  | 2021-03-08 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-03-10 | 502581.43 |  | 152521821.39 | 83952265.08 | 68569556.31 | 434504076.4286 | 15.78% |  |  | 2021-03-10 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-03-10 | 3429815.26 |  | 155951636.65 | 83952265.08 | 71999371.57 | 434504076.4286 | 16.57% |  |  | 2021-03-10 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-03-22 | 4602212.16 |  | 160553848.81 | 83952265.08 | 76601583.73 | 434504076.4286 | 17.63% |  |  | 2021-03-22 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-04-07 | 22337274.9 |  | 182891123.71 | 83952265.08 | 98938858.63 | 434504076.4286 | 22.77% |  |  | 2021-04-07 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-04-08 | 361142 |  | 183252265.71 | 83952265.08 | 99300000.63 | 434504076.4286 | 22.85% |  |  | 2021-04-08 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-04-08 | 2532838.58 |  | 185785104.29 | 83952265.08 | 101832839.21 | 434504076.4286 | 23.44% |  |  | 2021-04-08 | added cash in 3 |  |  | 2021
Marina Inland Marassi Pkg 162 | 2021-04-08 | 393728.94 |  | 186178833.23 | 83952265.08 | 102226568.15 | 434504076.4286 | 23.53% |  |  | 2021-04-08 | added cash in 3 |  |  | 2021
1900
Sultana Malek Restoration | 2020-01-01 |  | 16540 | 0 | 16540 | -16540 | 85000000 | -0.01946% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-02-01 |  | 14220 | 0 | 30760 | -30760 | 85000000 | -0.03619% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-03-01 |  | 30600 | 0 | 61360 | -61360 | 85000000 | -0.07219% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-04-01 |  | 30380 | 0 | 91740 | -91740 | 85000000 | -0.1079% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-05-01 |  | 23335.4 | 0 | 115075.4 | -115075.4 | 85000000 | -0.1354% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-06-01 |  | 108108.14 | 0 | 223183.54 | -223183.54 | 85000000 | -0.2626% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-07-01 |  | 311190.27 | 0 | 534373.81 | -534373.81 | 85000000 | -0.6287% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-08-01 |  | 85920 | 0 | 620293.81 | -620293.81 | 85000000 | -0.7298% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-09-01 |  | 593138.44 | 0 | 1213432.25 | -1213432.25 | 85000000 | -1.428% |  |  |  | cash out both |  |  | 2020
Sultana Malek Restoration | 2020-10-01 |  | 508574.4 | 0 | 1722006.65 | -1722006.65 | 85000000 | -2.026% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Sultana Malek Restoration | 2020-11-01 |  | 905343.87 | 0 | 2627350.52 | -2627350.52 | 85000000 | -3.091% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Sultana Malek Restoration | 2020-12-01 |  | 976595.58 | 0 | 3603946.1 | -3603946.1 | 85000000 | -4.24% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Sultana Malek Restoration | 2021-01-01 |  | 1282427.41 | 0 | 4886373.51 | -4886373.51 | 85000000 | -5.749% |  |  |  | cash out both |  |  | 2021
Sultana Malek Restoration | 2021-02-01 |  | 1426985.94 | 0 | 6313359.45 | -6313359.45 | 85000000 | -7.427% |  |  |  | cash out both |  |  | 2021
Sultana Malek Restoration | 2021-03-01 |  | 2012452.83 | 0 | 8325812.28 | -8325812.28 | 85000000 | -9.795% |  |  |  | cash out both |  |  | 2021
1900
Lekela 250MW Wind Farm | 2020-01-01 |  | 8241322.4 | 0 | 8241322.4 | -8241322.4 | 182442342 | -4.517% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-02-01 |  | 2074558.62 | 0 | 10315881.02 | -10315881.02 | 182442342 | -5.654% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-02-23 | 36300000 |  | 36300000 | 10315881.02 | 25984118.98 | 182442342 | 14.24% |  |  | 2020-02-23 | added 1 |  |  | 2020
Lekela 250MW Wind Farm | 2020-03-01 |  | 1445743.92 | 36300000 | 11761624.94 | 24538375.06 | 182442342 | 13.45% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-04-01 |  | 3702586.57 | 36300000 | 15464211.51 | 20835788.49 | 182442342 | 11.42% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-05-01 |  | 1619505.72 | 36300000 | 17083717.23 | 19216282.77 | 182442342 | 10.53% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-06-01 |  | 3604695.98 | 36300000 | 20688413.21 | 15611586.79 | 182442342 | 8.557% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-07-01 |  | 7498509.9 | 36300000 | 28186923.11 | 8113076.89 | 182442342 | 4.447% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-08-01 |  | 2993438.1 | 36300000 | 31180361.21 | 5119638.79 | 182442342 | 2.806% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-09-01 |  | 6162204.69 | 36300000 | 37342565.9 | -1042565.9 | 182442342 | -0.5714% |  |  |  | cash out both |  |  | 2020
Lekela 250MW Wind Farm | 2020-10-01 |  | 11207255.13 | 36300000 | 48549821.03 | -12249821.03 | 182442342 | -6.714% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Lekela 250MW Wind Farm | 2020-10-11 | 4497719.46 |  | 40797719.46 | 48549821.03 | -7752101.57 | 182442342 | -4.249% |  |  | 2020-10-11 | added cash in 3 |  |  | 2020
Lekela 250MW Wind Farm | 2020-10-25 | 652923.5 |  | 41450642.96 | 48549821.03 | -7099178.07 | 182442342 | -3.891% |  |  | 2020-10-25 | added cash in 3 |  |  | 2020
Lekela 250MW Wind Farm | 2020-11-01 |  | 15709758.46 | 41450642.96 | 64259579.49 | -22808936.53 | 182442342 | -12.5% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Lekela 250MW Wind Farm | 2020-11-24 | 124228 |  | 41574870.96 | 64259579.49 | -22684708.53 | 182442342 | -12.43% |  |  | 2020-11-24 | added 1 |  |  | 2020
Lekela 250MW Wind Farm | 2020-11-30 | 7094957.77 |  | 48669828.73 | 64259579.49 | -15589750.76 | 182442342 | -8.545% |  |  | 2020-11-30 | added cash in 3 |  |  | 2020
Lekela 250MW Wind Farm | 2020-11-30 | 124228 |  | 48794056.73 | 64259579.49 | -15465522.76 | 182442342 | -8.477% |  |  | 2020-11-30 | added cash in 3 |  |  | 2020
Lekela 250MW Wind Farm | 2020-12-01 |  | 12772294.33 | 48794056.73 | 77031873.82 | -28237817.09 | 182442342 | -15.48% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Lekela 250MW Wind Farm | 2021-01-01 |  | 16571648.95 | 48794056.73 | 93603522.77 | -44809466.04 | 182442342 | -24.56% |  |  |  | cash out both |  |  | 2021
Lekela 250MW Wind Farm | 2021-02-01 |  | 15413120.18 | 48794056.73 | 109016642.95 | -60222586.22 | 182442342 | -33.01% |  |  |  | cash out both |  |  | 2021
Lekela 250MW Wind Farm | 2021-02-10 | 15073158.35 |  | 63867215.08 | 109016642.95 | -45149427.87 | 182442342 | -24.75% |  |  | 2021-02-10 | added 1 |  |  | 2021
Lekela 250MW Wind Farm | 2021-02-28 | 14840272.42 |  | 78707487.5 | 109016642.95 | -30309155.45 | 182442342 | -16.61% |  |  | 2021-02-28 | added 1 |  |  | 2021
Lekela 250MW Wind Farm | 2021-02-28 | 32746957.22 |  | 111454444.72 | 109016642.95 | 2437801.77 | 182442342 | 1.336% |  |  | 2021-02-28 | added 1 |  |  | 2021
Lekela 250MW Wind Farm | 2021-03-01 |  | 10876714.04 | 111454444.72 | 119893356.99 | -8438912.27 | 182442342 | -4.626% |  |  |  | cash out both |  |  | 2021
Lekela 250MW Wind Farm | 2021-04-25 | 40304357.7 |  | 151758802.42 | 119893356.99 | 31865445.43 | 182442342 | 17.47% |  |  | 2021-04-25 | added cash in 3 |  |  | 2021
1900
New Giza Hospital | 2020-06-01 |  | 832.5 | 0 | 832.5 | -832.5 | 542690000 | -0.0001534% |  |  |  | cash out both |  |  | 2020
1900
Kayan Landscape | 2019-12-31 | 15494720 |  | 15494720 | 0 | 15494720 | 100042648 | 15.49% |  |  | 2019-12-31 | added cash in 3 |  |  | 2019
Kayan Landscape | 2020-03-01 |  | 2500000 | 15494720 | 2500000 | 12994720 | 100042648 | 12.99% |  |  |  | cash out both |  |  | 2020
Kayan Landscape | 2020-04-01 |  | 8000000 | 15494720 | 10500000 | 4994720 | 100042648 | 4.993% |  |  |  | cash out both |  |  | 2020
Kayan Landscape | 2020-06-01 |  | 3000000 | 15494720 | 13500000 | 1994720 | 100042648 | 1.994% |  |  |  | cash out both |  |  | 2020
Kayan Landscape | 2020-06-29 | 95 |  | 15494815 | 13500000 | 1994815 | 100042648 | 1.994% |  |  | 2020-06-29 | added cash in 3 |  |  | 2020
Kayan Landscape | 2020-07-01 |  | 2114917.27 | 15494815 | 15614917.27 | -120102.27 | 100042648 | -0.1201% |  |  |  | cash out both |  |  | 2020
Kayan Landscape | 2020-08-01 |  | 5000000 | 15494815 | 20614917.27 | -5120102.27 | 100042648 | -5.118% |  |  |  | cash out both |  |  | 2020
1900
Abbas Akkad Bridge | 2020-03-01 |  | 815080 | 0 | 815080 | -815080 | 124132580.9524 | -0.6566% |  |  |  | cash out both |  |  | 2020
Abbas Akkad Bridge | 2020-04-01 |  | 6767355.35 | 0 | 7582435.35 | -7582435.35 | 124132580.9524 | -6.108% |  |  |  | cash out both |  |  | 2020
Abbas Akkad Bridge | 2020-05-01 |  | 10136135.98 | 0 | 17718571.33 | -17718571.33 | 124132580.9524 | -14.27% |  |  |  | cash out both |  |  | 2020
Abbas Akkad Bridge | 2020-05-13 | 20000000 |  | 20000000 | 17718571.33 | 2281428.67 | 124132580.9524 | 1.838% |  |  | 2020-05-13 | added 1 |  |  | 2020
Abbas Akkad Bridge | 2020-06-01 |  | 7529622.6 | 20000000 | 25248193.93 | -5248193.93 | 124132580.9524 | -4.228% |  |  |  | cash out both |  |  | 2020
Abbas Akkad Bridge | 2020-07-01 |  | 2787393.4 | 20000000 | 28035587.33 | -8035587.33 | 124132580.9524 | -6.473% |  |  |  | cash out both |  |  | 2020
Abbas Akkad Bridge | 2020-08-01 |  | 1496601.58 | 20000000 | 29532188.91 | -9532188.91 | 124132580.9524 | -7.679% |  |  |  | cash out both |  |  | 2020
Abbas Akkad Bridge | 2020-09-01 |  | 4050574.04 | 20000000 | 33582762.95 | -13582762.95 | 124132580.9524 | -10.94% |  |  |  | cash out both |  |  | 2020
Abbas Akkad Bridge | 2020-10-01 |  | 417215.48 | 20000000 | 33999978.43 | -13999978.43 | 124132580.9524 | -11.28% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Abbas Akkad Bridge | 2020-11-01 |  | 2205024.46 | 20000000 | 36205002.89 | -16205002.89 | 124132580.9524 | -13.05% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Abbas Akkad Bridge | 2020-12-01 |  | 467048.55 | 20000000 | 36672051.44 | -16672051.44 | 124132580.9524 | -13.43% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Abbas Akkad Bridge | 2020-12-29 | 61465690 |  | 81465690 | 36672051.44 | 44793638.56 | 124132580.9524 | 36.09% |  |  | 2020-12-29 | added cash in 3 |  |  | 2020
Abbas Akkad Bridge | 2021-01-01 |  | 796272.06 | 81465690 | 37468323.5 | 43997366.5 | 124132580.9524 | 35.44% |  |  |  | cash out both |  |  | 2021
Abbas Akkad Bridge | 2021-02-01 |  | 5577.45 | 81465690 | 37473900.95 | 43991789.05 | 124132580.9524 | 35.44% |  |  |  | cash out both |  |  | 2021
Abbas Akkad Bridge | 2021-03-01 |  | 396178.24 | 81465690 | 37870079.19 | 43595610.81 | 124132580.9524 | 35.12% |  |  |  | cash out both |  |  | 2021
Abbas Akkad Bridge | 2021-03-31 | 6904265 |  | 88369955 | 37870079.19 | 50499875.81 | 124132580.9524 | 40.68% |  |  | 2021-03-31 | added cash in 3 |  |  | 2021
1900
El Asher Men Ramadan Bridge | 2020-04-01 |  | 20000 | 0 | 20000 | -20000 | 93910355 | -0.0213% |  |  |  | cash out both |  |  | 2020
El Asher Men Ramadan Bridge | 2020-05-01 |  | 165208.13 | 0 | 185208.13 | -185208.13 | 93910355 | -0.1972% |  |  |  | cash out both |  |  | 2020
El Asher Men Ramadan Bridge | 2020-06-01 |  | 3536962.07 | 0 | 3722170.2 | -3722170.2 | 93910355 | -3.964% |  |  |  | cash out both |  |  | 2020
El Asher Men Ramadan Bridge | 2020-07-01 |  | 6452555.07 | 0 | 10174725.27 | -10174725.27 | 93910355 | -10.83% |  |  |  | cash out both |  |  | 2020
El Asher Men Ramadan Bridge | 2020-08-01 |  | 5777684.12 | 0 | 15952409.39 | -15952409.39 | 93910355 | -16.99% |  |  |  | cash out both |  |  | 2020
El Asher Men Ramadan Bridge | 2020-08-17 | 5299995 |  | 5299995 | 15952409.39 | -10652414.39 | 93910355 | -11.34% |  |  | 2020-08-17 | added 1 |  |  | 2020
El Asher Men Ramadan Bridge | 2020-09-01 |  | 4954513.52 | 5299995 | 20906922.91 | -15606927.91 | 93910355 | -16.62% |  |  |  | cash out both |  |  | 2020
El Asher Men Ramadan Bridge | 2020-10-01 |  | 2081097.21 | 5299995 | 22988020.12 | -17688025.12 | 93910355 | -18.84% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
El Asher Men Ramadan Bridge | 2020-11-01 |  | 2122081.29 | 5299995 | 25110101.41 | -19810106.41 | 93910355 | -21.09% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
El Asher Men Ramadan Bridge | 2020-11-22 | 2644030 |  | 7944025 | 25110101.41 | -17166076.41 | 93910355 | -18.28% |  |  | 2020-11-22 | added cash in 3 |  |  | 2020
El Asher Men Ramadan Bridge | 2020-11-24 | 47356828 |  | 55300853 | 25110101.41 | 30190751.59 | 93910355 | 32.15% |  |  | 2020-11-24 | added cash in 3 |  |  | 2020
El Asher Men Ramadan Bridge | 2020-12-01 |  | 2787020.21 | 55300853 | 27897121.62 | 27403731.38 | 93910355 | 29.18% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
El Asher Men Ramadan Bridge | 2020-12-14 | 3163290 |  | 58464143 | 27897121.62 | 30567021.38 | 93910355 | 32.55% |  |  | 2020-12-14 | added cash in 3 |  |  | 2020
El Asher Men Ramadan Bridge | 2021-01-01 |  | 1185328.32 | 58464143 | 29082449.94 | 29381693.06 | 93910355 | 31.29% |  |  |  | cash out both |  |  | 2021
El Asher Men Ramadan Bridge | 2021-02-01 |  | 47700.77 | 58464143 | 29130150.71 | 29333992.29 | 93910355 | 31.24% |  |  |  | cash out both |  |  | 2021
El Asher Men Ramadan Bridge | 2021-03-01 |  | 1274208.85 | 58464143 | 30404359.56 | 28059783.44 | 93910355 | 29.88% |  |  |  | cash out both |  |  | 2021
1900
Kafr Shokr Bridge | 2020-06-01 |  | 144438.27 | 0 | 144438.27 | -144438.27 | 147845325 | -0.0977% |  |  |  | cash out both |  |  | 2020
Kafr Shokr Bridge | 2020-07-01 |  | 137412.73 | 0 | 281851 | -281851 | 147845325 | -0.1906% |  |  |  | cash out both |  |  | 2020
Kafr Shokr Bridge | 2020-08-01 |  | 95962.62 | 0 | 377813.62 | -377813.62 | 147845325 | -0.2555% |  |  |  | cash out both |  |  | 2020
Kafr Shokr Bridge | 2020-09-01 |  | 453037.71 | 0 | 830851.33 | -830851.33 | 147845325 | -0.562% |  |  |  | cash out both |  |  | 2020
Kafr Shokr Bridge | 2020-10-01 |  | 4690086.46 | 0 | 5520937.79 | -5520937.79 | 147845325 | -3.734% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Kafr Shokr Bridge | 2020-11-01 |  | 2569581.78 | 0 | 8090519.57 | -8090519.57 | 147845325 | -5.472% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Kafr Shokr Bridge | 2020-11-22 | 2644030 |  | 2644030 | 8090519.57 | -5446489.57 | 147845325 | -3.684% |  |  | 2020-11-22 | added 1 |  |  | 2020
Kafr Shokr Bridge | 2020-12-01 |  | 2717734.8 | 2644030 | 10808254.37 | -8164224.37 | 147845325 | -5.522% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Kafr Shokr Bridge | 2021-01-01 |  | 6770763.48 | 2644030 | 17579017.85 | -14934987.85 | 147845325 | -10.1% |  |  |  | cash out both |  |  | 2021
Kafr Shokr Bridge | 2021-02-01 |  | 7434187.14 | 2644030 | 25013204.99 | -22369174.99 | 147845325 | -15.13% |  |  |  | cash out both |  |  | 2021
Kafr Shokr Bridge | 2021-03-01 |  | 8398385.47 | 2644030 | 33411590.46 | -30767560.46 | 147845325 | -20.81% |  |  |  | cash out both |  |  | 2021
1900
Al Shorouk Bridge (LRT) | 2020-06-01 |  | 13993.86 | 0 | 13993.86 | -13993.86 | 26145782 | -0.05352% |  |  |  | cash out both |  |  | 2020
Al Shorouk Bridge (LRT) | 2020-07-01 |  | 886685.74 | 0 | 900679.6 | -900679.6 | 26145782 | -3.445% |  |  |  | cash out both |  |  | 2020
Al Shorouk Bridge (LRT) | 2020-08-01 |  | 1430356.75 | 0 | 2331036.35 | -2331036.35 | 26145782 | -8.916% |  |  |  | cash out both |  |  | 2020
Al Shorouk Bridge (LRT) | 2020-09-01 |  | 2087514.06 | 0 | 4418550.41 | -4418550.41 | 26145782 | -16.9% |  |  |  | cash out both |  |  | 2020
Al Shorouk Bridge (LRT) | 2020-10-01 |  | 2772979.71 | 0 | 7191530.12 | -7191530.12 | 26145782 | -27.51% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Al Shorouk Bridge (LRT) | 2020-11-01 |  | 4074320.41 | 0 | 11265850.53 | -11265850.53 | 26145782 | -43.09% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Al Shorouk Bridge (LRT) | 2020-11-03 | 8000000 |  | 8000000 | 11265850.53 | -3265850.53 | 26145782 | -12.49% |  |  | 2020-11-03 | added cash in 3 |  |  | 2020
Al Shorouk Bridge (LRT) | 2020-12-01 |  | 2676440.32 | 8000000 | 13942290.85 | -5942290.85 | 26145782 | -22.73% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Al Shorouk Bridge (LRT) | 2021-01-01 |  | 3976901.78 | 8000000 | 17919192.63 | -9919192.63 | 26145782 | -37.94% |  |  |  | cash out both |  |  | 2021
Al Shorouk Bridge (LRT) | 2021-01-14 | 3550000 |  | 11550000 | 17919192.63 | -6369192.63 | 26145782 | -24.36% |  |  | 2021-01-14 | added cash in 3 |  |  | 2021
Al Shorouk Bridge (LRT) | 2021-02-01 |  | 813613.25 | 11550000 | 18732805.88 | -7182805.88 | 26145782 | -27.47% |  |  |  | cash out both |  |  | 2021
Al Shorouk Bridge (LRT) | 2021-02-08 | 2000000 |  | 13550000 | 18732805.88 | -5182805.88 | 26145782 | -19.82% |  |  | 2021-02-08 | added cash in 3 |  |  | 2021
Al Shorouk Bridge (LRT) | 2021-03-01 |  | 1316091.64 | 13550000 | 20048897.52 | -6498897.52 | 26145782 | -24.86% |  |  |  | cash out both |  |  | 2021
Al Shorouk Bridge (LRT) | 2021-03-16 | 6500000 |  | 20050000 | 20048897.52 | 1102.48 | 26145782 | 0.004217% |  |  | 2021-03-16 | added 1 |  |  | 2021
1900
Ring Road El Marg | 2020-06-01 |  | 100806.58 | 0 | 100806.58 | -100806.58 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road El Marg | 2020-07-01 |  | 54000 | 0 | 154806.58 | -154806.58 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road El Marg | 2020-08-01 |  | 40000 | 0 | 194806.58 | -194806.58 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road El Marg | 2020-09-01 |  | 58744.83 | 0 | 253551.41 | -253551.41 | #N/A | #N/A |  |  |  | cash out both |  |  | 2020
Ring Road El Marg | 2020-10-01 |  | 134191.03 | 0 | 387742.44 | -387742.44 | #N/A | #N/A |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Ring Road El Marg | 2020-11-01 |  | 11486588.24 | 0 | 11874330.68 | -11874330.68 | #N/A | #N/A |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Ring Road El Marg | 2020-12-01 |  | 20933294.21 | 0 | 32807624.89 | -32807624.89 | #N/A | #N/A |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Ring Road El Marg | 2021-03-08 | 45719198.4 |  | 45719198.4 | 32807624.89 | 12911573.51 | #N/A | #N/A |  |  | 2021-03-08 | added 1 |  |  | 2021
1900
GOV2 Infra | 2020-07-01 |  | 132750 | 0 | 132750 | -132750 | 650000000 | -0.02042% |  |  |  | cash out both |  |  | 2020
GOV2 Infra | 2020-09-01 |  | 45330.09 | 0 | 178080.09 | -178080.09 | 650000000 | -0.0274% |  |  |  | cash out both |  |  | 2020
GOV2 Infra | 2020-10-01 |  | 4544678.51 | 0 | 4722758.6 | -4722758.6 | 650000000 | -0.7266% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
GOV2 Infra | 2020-11-01 |  | 264757.88 | 0 | 4987516.48 | -4987516.48 | 650000000 | -0.7673% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
GOV2 Infra | 2020-12-01 |  | 3606552.14 | 0 | 8594068.62 | -8594068.62 | 650000000 | -1.322% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
GOV2 Infra | 2021-01-01 |  | 2631270.59 | 0 | 11225339.21 | -11225339.21 | 650000000 | -1.727% |  |  |  | cash out both |  |  | 2021
GOV2 Infra | 2021-02-01 |  | 5624766.49 | 0 | 16850105.7 | -16850105.7 | 650000000 | -2.592% |  |  |  | cash out both |  |  | 2021
GOV2 Infra | 2021-03-01 |  | 10032429.02 | 0 | 26882534.72 | -26882534.72 | 650000000 | -4.136% |  |  |  | cash out both |  |  | 2021
GOV2 Infra | 2021-03-18 | 2964607.7 |  | 2964607.7 | 26882534.72 | -23917927.02 | 650000000 | -3.68% |  |  | 2021-03-18 | added cash in 3 |  |  | 2021
GOV2 Infra | 2021-03-31 | 5828902.51 |  | 8793510.21 | 26882534.72 | -18089024.51 | 650000000 | -2.783% |  |  | 2021-03-31 | added cash in 3 |  |  | 2021
1900
Cairo Alex Railroad | 2020-06-01 |  | 72323.19 | 0 | 72323.19 | -72323.19 | 967000000 | -0.007479% |  |  |  | cash out both |  |  | 2020
Cairo Alex Railroad | 2020-08-01 |  | 209295.88 | 0 | 281619.07 | -281619.07 | 967000000 | -0.02912% |  |  |  | cash out both |  |  | 2020
Cairo Alex Railroad | 2020-09-01 |  | 339516.03 | 0 | 621135.1 | -621135.1 | 967000000 | -0.06423% |  |  |  | cash out both |  |  | 2020
Cairo Alex Railroad | 2020-10-01 |  | 936117.48 | 0 | 1557252.58 | -1557252.58 | 967000000 | -0.161% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Cairo Alex Railroad | 2020-10-18 | 144582383 |  | 144582383 | 1557252.58 | 143025130.42 | 967000000 | 14.79% |  |  | 2020-10-18 | added 1 |  |  | 2020
Cairo Alex Railroad | 2020-11-01 |  | 8426902.48 | 144582383 | 9984155.06 | 134598227.94 | 967000000 | 13.92% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Cairo Alex Railroad | 2020-12-01 |  | 22966624.36 | 144582383 | 32950779.42 | 111631603.58 | 967000000 | 11.54% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Cairo Alex Railroad | 2021-01-01 |  | 4524339.42 | 144582383 | 37475118.84 | 107107264.16 | 967000000 | 11.08% |  |  |  | cash out both |  |  | 2021
Cairo Alex Railroad | 2021-02-01 |  | 7873554.79 | 144582383 | 45348673.63 | 99233709.37 | 967000000 | 10.26% |  |  |  | cash out both |  |  | 2021
Cairo Alex Railroad | 2021-03-01 |  | 7186757.34 | 144582383 | 52535430.97 | 92046952.03 | 967000000 | 9.519% |  |  |  | cash out both |  |  | 2021
Cairo Alex Railroad | 2021-03-09 | 5025720.35 |  | 149608103.35 | 52535430.97 | 97072672.38 | 967000000 | 10.04% |  |  | 2021-03-09 | added cash in 3 |  |  | 2021
Cairo Alex Railroad | 2021-04-14 | 3883856.25 |  | 153491959.6 | 52535430.97 | 100956528.63 | 967000000 | 10.44% |  |  | 2021-04-14 | added cash in 3 |  |  | 2021
1900
Hassan El Mamoun Bridge | 2020-07-01 |  | 9252.13 | 0 | 9252.13 | -9252.13 | 93800000 | -0.009864% |  |  |  | cash out both |  |  | 2020
Hassan El Mamoun Bridge | 2020-08-01 |  | 7680664.25 | 0 | 7689916.38 | -7689916.38 | 93800000 | -8.198% |  |  |  | cash out both |  |  | 2020
Hassan El Mamoun Bridge | 2020-09-01 |  | 6632324.54 | 0 | 14322240.92 | -14322240.92 | 93800000 | -15.27% |  |  |  | cash out both |  |  | 2020
Hassan El Mamoun Bridge | 2020-10-01 |  | 7512810.36 | 0 | 21835051.28 | -21835051.28 | 93800000 | -23.28% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Hassan El Mamoun Bridge | 2020-11-01 |  | 5039532.75 | 0 | 26874584.03 | -26874584.03 | 93800000 | -28.65% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Hassan El Mamoun Bridge | 2020-12-01 |  | 3884242.38 | 0 | 30758826.41 | -30758826.41 | 93800000 | -32.79% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Hassan El Mamoun Bridge | 2020-12-31 | 36412560 |  | 36412560 | 30758826.41 | 5653733.59 | 93800000 | 6.027% |  |  | 2020-12-31 | added cash in 3 |  |  | 2020
Hassan El Mamoun Bridge | 2021-01-01 |  | 1568029.03 | 36412560 | 32326855.44 | 4085704.56 | 93800000 | 4.356% |  |  |  | cash out both |  |  | 2021
Hassan El Mamoun Bridge | 2021-01-31 | 286280 |  | 36698840 | 32326855.44 | 4371984.56 | 93800000 | 4.661% |  |  | 2021-01-31 | added cash in 3 |  |  | 2021
Hassan El Mamoun Bridge | 2021-02-01 |  | 684739.23 | 36698840 | 33011594.67 | 3687245.33 | 93800000 | 3.931% |  |  |  | cash out both |  |  | 2021
Hassan El Mamoun Bridge | 2021-02-28 | 4682080 |  | 41380920 | 33011594.67 | 8369325.33 | 93800000 | 8.923% |  |  | 2021-02-28 | added 1 |  |  | 2021
Hassan El Mamoun Bridge | 2021-03-01 |  | 1589632.58 | 41380920 | 34601227.25 | 6779692.75 | 93800000 | 7.228% |  |  |  | cash out both |  |  | 2021
Hassan El Mamoun Bridge | 2021-03-31 | 1893795 |  | 43274715 | 34601227.25 | 8673487.75 | 93800000 | 9.247% |  |  | 2021-03-31 | added cash in 3 |  |  | 2021
1900
Sherouk Bridge L&L | 2020-09-01 |  | 354746.03 | 0 | 354746.03 | -354746.03 | 1000000 | -35.47% |  |  |  | cash out both |  |  | 2020
Sherouk Bridge L&L | 2021-02-01 |  | 149697.02 | 0 | 504443.05 | -504443.05 | 1000000 | -50.44% |  |  |  | cash out both |  |  | 2021
Sherouk Bridge L&L | 2021-03-01 |  | 102459.16 | 0 | 606902.21 | -606902.21 | 1000000 | -60.69% |  |  |  | cash out both |  |  | 2021
1900
Ora Zed Park 1B Pkgs A&D | 2020-09-01 |  | 50000 | 0 | 50000 | -50000 | 870293108 | -0.005745% |  |  |  | cash out both |  |  | 2020
Ora Zed Park 1B Pkgs A&D | 2020-10-01 |  | 11436650.94 | 0 | 11486650.94 | -11486650.94 | 870293108 | -1.32% |  |  | 2020-10-01 | cashout both updated |  |  | 2020
Ora Zed Park 1B Pkgs A&D | 2020-11-01 |  | 15350524.19 | 0 | 26837175.13 | -26837175.13 | 870293108 | -3.084% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Ora Zed Park 1B Pkgs A&D | 2020-11-09 | 91380773 |  | 91380773 | 26837175.13 | 64543597.87 | 870293108 | 7.416% |  |  | 2020-11-09 | added 1 |  |  | 2020
Ora Zed Park 1B Pkgs A&D | 2020-12-01 |  | 13620467.66 | 91380773 | 40457642.79 | 50923130.21 | 870293108 | 5.851% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Ora Zed Park 1B Pkgs A&D | 2021-01-01 |  | 27377068.56 | 91380773 | 67834711.35 | 23546061.65 | 870293108 | 2.706% |  |  |  | cash out both |  |  | 2021
Ora Zed Park 1B Pkgs A&D | 2021-01-01 |  | 614228.65 | 91380773 | 68448940 | 22931833 | 870293108 | 2.635% |  |  |  | cash out both |  |  | 2021
Ora Zed Park 1B Pkgs A&D | 2021-02-01 |  | 30569405.47 | 91380773 | 99018345.47 | -7637572.47 | 870293108 | -0.8776% |  |  |  | cash out both |  |  | 2021
Ora Zed Park 1B Pkgs A&D | 2021-02-21 | 9787286.79 |  | 101168059.79 | 99018345.47 | 2149714.32 | 870293108 | 0.247% |  |  | 2021-02-21 | added 1 |  |  | 2021
Ora Zed Park 1B Pkgs A&D | 2021-03-01 |  | 20416380.18 | 101168059.79 | 119434725.65 | -18266665.86 | 870293108 | -2.099% |  |  |  | cash out both |  |  | 2021
Ora Zed Park 1B Pkgs A&D | 2021-03-01 |  | 7258.41 | 101168059.79 | 119441984.06 | -18273924.27 | 870293108 | -2.1% |  |  |  | cash out both |  |  | 2021
1900
Kattameya Creeks | 2020-11-01 |  | 1557075.8 | 0 | 1557075.8 | -1557075.8 | 1462000000 | -0.1065% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Kattameya Creeks | 2020-12-01 |  | 328448.53 | 0 | 1885524.33 | -1885524.33 | 1462000000 | -0.129% |  |  | 2020-12-01 | cashout both updated |  |  | 2020
Kattameya Creeks | 2021-01-01 |  | 6724969.81 | 0 | 8610494.14 | -8610494.14 | 1462000000 | -0.589% |  |  |  | cash out both |  |  | 2021
Kattameya Creeks | 2021-01-13 | 200000000 |  | 200000000 | 8610494.14 | 191389505.86 | 1462000000 | 13.09% |  |  | 2021-01-13 | added cash in 3 |  |  | 2021
Kattameya Creeks | 2021-02-01 |  | 22904906.74 | 200000000 | 31515400.88 | 168484599.12 | 1462000000 | 11.52% |  |  |  | cash out both |  |  | 2021
Kattameya Creeks | 2021-03-01 |  | 13042601.93 | 200000000 | 44558002.81 | 155441997.19 | 1462000000 | 10.63% |  |  |  | cash out both |  |  | 2021
Kattameya Creeks | 2021-03-15 | 2741191.29 |  | 202741191.29 | 44558002.81 | 158183188.48 | 1462000000 | 10.82% |  |  | 2021-03-15 | added 1 |  |  | 2021
Kattameya Creeks | 2021-03-29 | 11302769.94 |  | 214043961.23 | 44558002.81 | 169485958.42 | 1462000000 | 11.59% |  |  | 2021-03-29 | added cash in 3 |  |  | 2021
1900
Mansoura University Faculty of Medicine | 2021-02-01 |  | 1066750 | 0 | 1066750 | -1066750 | 219047619.0476 | -0.487% |  |  |  | cash out both |  |  | 2021
Mansoura University Faculty of Medicine | 2021-03-01 |  | 156695.75 | 0 | 1223445.75 | -1223445.75 | 219047619.0476 | -0.5585% |  |  |  | cash out both |  |  | 2021
1900
Diplomatic District - Infra | 2020-11-01 |  | 3644 | 0 | 3644 | -3644 | 390000000 | -0.0009344% |  |  | 2020-11-01 | cashout both updated |  |  | 2020
Diplomatic District - Infra | 2021-01-01 |  | 132894.98 | 0 | 136538.98 | -136538.98 | 390000000 | -0.03501% |  |  |  | cash out both |  |  | 2021
Diplomatic District - Infra | 2021-02-01 |  | 122701 | 0 | 259239.98 | -259239.98 | 390000000 | -0.06647% |  |  |  | cash out both |  |  | 2021
Diplomatic District - Infra | 2021-03-01 |  | 2077151.82 | 0 | 2336391.8 | -2336391.8 | 390000000 | -0.5991% |  |  |  | cash out both |  |  | 2021
Diplomatic District - Infra | 2021-04-27 | 20000000 |  | 20000000 | 2336391.8 | 17663608.2 | 390000000 | 4.529% |  |  | 2021-04-27 | added cash in 3 |  |  | 2021
1900
El Sewedy CFC HQ Internal Finishing | 2020-12-08 | 103231218.3 |  | 103231218.3 | 0 | 103231218.3 | 327718153.3333 | 31.5% |  |  | 2020-12-08 | added cash in 3 |  |  | 2020
El Sewedy CFC HQ Internal Finishing | 2021-01-01 |  | 445163.16 | 103231218.3 | 445163.16 | 102786055.14 | 327718153.3333 | 31.36% |  |  |  | cash out both |  |  | 2021
El Sewedy CFC HQ Internal Finishing | 2021-02-01 |  | 43409152.65 | 103231218.3 | 43854315.81 | 59376902.49 | 327718153.3333 | 18.12% |  |  |  | cash out both |  |  | 2021
El Sewedy CFC HQ Internal Finishing | 2021-03-01 |  | 3622260.91 | 103231218.3 | 47476576.72 | 55754641.58 | 327718153.3333 | 17.01% |  |  |  | cash out both |  |  | 2021
El Sewedy CFC HQ Internal Finishing | 2021-03-22 | 6847513.64 |  | 110078731.94 | 47476576.72 | 62602155.22 | 327718153.3333 | 19.1% |  |  | 2021-03-22 | added 1 |  |  | 2021
El Sewedy CFC HQ Internal Finishing | 2021-04-11 | 8021127.82 |  | 118099859.76 | 47476576.72 | 70623283.04 | 327718153.3333 | 21.55% |  |  | 2021-04-11 | added cash in 3 |  |  | 2021
1900
Lagoon Discharge Pkg 178 | 2021-01-01 |  | 976942.63 | 0 | 976942.63 | -976942.63 | 40449240 | -2.415% |  |  |  | cash out both |  |  | 2021
Lagoon Discharge Pkg 178 | 2021-02-01 |  | 2082179.42 | 0 | 3059122.05 | -3059122.05 | 40449240 | -7.563% |  |  |  | cash out both |  |  | 2021
Lagoon Discharge Pkg 178 | 2021-02-16 | 3747170.2 |  | 3747170.2 | 3059122.05 | 688048.15 | 40449240 | 1.701% |  |  | 2021-02-16 | added cash in 3 |  |  | 2021
Lagoon Discharge Pkg 178 | 2021-03-01 |  | 1804254.82 | 3747170.2 | 4863376.87 | -1116206.67 | 40449240 | -2.76% |  |  |  | cash out both |  |  | 2021
1900
El Khatatba Bridge | 2021-02-01 |  | 256400 | 0 | 256400 | -256400 | 142857142.8571 | -0.1795% |  |  |  | cash out both |  |  | 2021
El Khatatba Bridge | 2021-03-01 |  | 233175 | 0 | 489575 | -489575 | 142857142.8571 | -0.3427% |  |  |  | cash out both |  |  | 2021
1900
EGAT Pelletizing Plant | 2021-02-25 | 10000000 |  | 10000000 | 0 | 10000000 | 375000000 | 2.667% |  |  | 2021-02-25 | added cash in 3 |  |  | 2021
EGAT Pelletizing Plant | 2021-04-14 | 2000000 |  | 12000000 | 0 | 12000000 | 375000000 | 3.2% |  |  | 2021-04-14 | added cash in 3 |  |  | 2021
1900
MDF Factory | 2021-03-01 |  | 60000 | 0 | 60000 | -60000 | 175000000 | -0.03429% |  |  |  | cash out both |  |  | 2021
MDF Factory | 2021-04-15 | 41622365.4 |  | 41622365.4 | 60000 | 41562365.4 | 175000000 | 23.75% |  |  | 2021-04-15 | added cash in 3 |  |  | 2021
1900
Aeon Towers Chiller Building | 2020-10-18 | 1264914.16 |  | 1264914.16 | 0 | 1264914.16 | 0 | #DIV/0! |  |  | 2020-10-18 | added 1 |  |  | 2020
Aeon Towers Chiller Building | 2021-01-21 | 1513146.56 |  | 2778060.72 | 0 | 2778060.72 | 0 | #DIV/0! |  |  | 2021-01-21 | added 1 |  |  | 2021
Aeon Towers Chiller Building | 2021-02-28 | 780253.07 |  | 3558313.79 | 0 | 3558313.79 | 0 | #DIV/0! |  |  | 2021-02-28 | added 1 |  |  | 2021
1900
Alegria DP Port | 2015-01-31 | 6624155 | 1653901 | 6624155 | 1653901 | 4970254 | 605714038 | 0.8206% |  | 5798117.99 | 2015-01-31 | original |  |  | 2015
Alegria DP Port | 2015-02-28 | 0 | 3194973 | 6624155 | 4848874 | 1775281 | 605714038 | 0.2931% |  | 2401628.5 | 2015-02-28 | original |  |  | 2015
Alegria DP Port | 2015-03-31 | 5764258 | 4333570 | 12388413 | 9182444 | 3205969 | 605714038 | 0.5293% |  | 3251532.35 | 2015-03-31 | original |  |  | 2015
Alegria DP Port | 2015-04-30 | 0 | 1907111 | 12388413 | 11089555 | 1298858 | 605714038 | 0.2144% |  | 1751613.06 | 2015-04-30 | original |  |  | 2015
Alegria DP Port | 2015-05-31 | 2259233 | 1875177 | 14647646 | 12964732 | 1682914 | 605714038 | 0.2778% |  | 2896334.5 | 2015-05-31 | original |  |  | 2015
Alegria DP Port | 2015-06-30 | 1216788 | 1691561 | 15864434 | 14656293 | 1208141 | 605714038 | 0.1995% |  | 1327252.64 | 2015-06-30 | original |  |  | 2015
Alegria DP Port | 2015-07-31 | 2012370 | 2677365 | 17876804 | 17333658 | 543146 | 605714038 | 0.08967% |  | 3189427.65 | 2015-07-31 | original |  |  | 2015
Alegria DP Port | 2015-08-31 | 0 | 2088743 | 17876804 | 19422401 | -1545597 | 605714038 | -0.2552% |  | 6474594.96 | 2015-08-31 | original |  |  | 2015
Alegria DP Port | 2015-09-30 | 2832049 | 1169364 | 20708853 | 20591765 | 117088 | 605714038 | 0.01933% |  | 0 | 2015-09-30 | original |  |  | 2015
Alegria DP Port | 2015-10-31 | 4806304 | 1471310 | 25515157 | 22063075 | 3452082 | 605714038 | 0.5699% |  | 3097164.11 | 2015-10-31 | original |  |  | 2015
Alegria DP Port | 2015-11-30 | 0 | 841116 | 25515157 | 22904191 | 2610966 | 605714038 | 0.4311% |  | 0 | 2015-11-30 | original |  |  | 2015
Alegria DP Port | 2015-12-31 | 2152237 | 1936416 | 27667394 | 24840607 | 2826787 | 605714038 | 0.4667% |  | 0 | 2015-12-31 | original |  |  | 2015
Alegria DP Port | 2016-01-31 | 0 | 409440 | 27667394 | 25250047 | 2417347 | 605714038 | 0.3991% |  | 0 | 2016-01-31 | original |  |  | 2016
Alegria DP Port | 2016-02-29 | 0 | 468487 | 27667394 | 25718534 | 1948860 | 605714038 | 0.3217% |  | 0 | 2016-02-29 | original |  |  | 2016
Alegria DP Port | 2016-03-31 | 815274 | 255404 | 28482668 | 25973938 | 2508730 | 605714038 | 0.4142% |  | 0 | 2016-03-31 | original |  |  | 2016
Alegria DP Port | 2016-04-30 | 0 | 298449 | 28482668 | 26272387 | 2210281 | 605714038 | 0.3649% |  | 0 | 2016-04-30 | original |  |  | 2016
Alegria DP Port | 2016-05-31 | 2680004 | 459076 | 31162672 | 26731463 | 4431209 | 605714038 | 0.7316% |  | 0 | 2016-05-31 | original |  |  | 2016
Alegria DP Port | 2016-06-30 | 0 | 530927 | 31162672 | 27262390 | 3900282 | 605714038 | 0.6439% |  | 0 | 2016-06-30 | original |  |  | 2016
Alegria DP Port | 2016-07-31 | 0 | 1086772 | 31162672 | 28349162 | 2813510 | 605714038 | 0.4645% |  | 0 | 2016-07-31 | original |  |  | 2016
Alegria DP Port | 2016-09-30 | 0 | 74351 | 31162672 | 28423513 | 2739159 | 605714038 | 0.4522% |  | 0 | 2016-09-30 | original |  |  | 2016
Alegria DP Port | 2016-10-31 | 0 | 56431 | 31162672 | 28479944 | 2682728 | 605714038 | 0.4429% |  | 0 | 2016-10-31 | original |  |  | 2016
Alegria DP Port | 2016-11-30 | 1723207 | 0 | 32885879 | 28479944 | 4405935 | 605714038 | 0.7274% |  | 0 | 2016-11-30 | original |  |  | 2016
Alegria DP Port | 2019-10-01 |  | 8277.12 | 32885879 | 28488221.12 | 4397657.88 | 605714038 | 0.726% |  |  |  | cash out both |  |  | 2019
Alegria DP Port | 2019-11-01 |  | 283548.59 | 32885879 | 28771769.71 | 4114109.29 | 605714038 | 0.6792% |  |  |  | cash out both |  |  | 2019
Alegria DP Port | 2019-12-01 |  | 232093.13 | 32885879 | 29003862.84 | 3882016.16 | 605714038 | 0.6409% |  |  |  | cash out both |  |  | 2019
Alegria DP Port | 2020-02-01 |  | 252905.76 | 32885879 | 29256768.6 | 3629110.4 | 605714038 | 0.5991% |  |  |  | cash out both |  |  | 2020
Alegria DP Port | 2020-03-01 |  | 1510.08 | 32885879 | 29258278.68 | 3627600.32 | 605714038 | 0.5989% |  |  |  | cash out both |  |  | 2020
Alegria DP Port | 2020-04-01 |  | 17245.91 | 32885879 | 29275524.59 | 3610354.41 | 605714038 | 0.596% |  |  |  | cash out both |  |  | 2020
Alegria DP Port | 2020-05-01 |  | 244429.03 | 32885879 | 29519953.62 | 3365925.38 | 605714038 | 0.5557% |  |  |  | cash out both |  |  | 2020
Alegria DP Port | 2020-06-01 |  | 17755.91 | 32885879 | 29537709.53 | 3348169.47 | 605714038 | 0.5528% |  |  |  | cash out both |  |  | 2020
Alegria DP Port | 2020-07-01 |  | 237541.6 | 32885879 | 29775251.13 | 3110627.87 | 605714038 | 0.5135% |  |  |  | cash out both |  |  | 2020
Alegria DP Port | 2020-08-01 |  | 253826.25 | 32885879 | 30029077.38 | 2856801.62 | 605714038 | 0.4716% |  |  |  | cash out both |  |  | 2020
Alegria DP Port | 2020-09-01 |  | 76774.85 | 32885879 | 30105852.23 | 2780026.77 | 605714038 | 0.459% |  |  |  | cash out both |  |  | 2020
1900
Alexandria Bridges | 2010-09-30 | 0 |  | 0 | 0 | 0 | 35589876.5 | 0% |  | 1425467.48 | 2010-09-30 | original |  |  | 2010
Alexandria Bridges | 2010-10-30 | 3096000 |  | 3096000 | 0 | 3096000 | 35589876.5 | 8.699% |  | 2191262.34 | 2010-10-30 | original |  |  | 2010
Alexandria Bridges | 2010-11-30 | 2000000 |  | 5096000 | 0 | 5096000 | 35589876.5 | 14.32% |  | 2222531.45 | 2010-11-30 | original |  |  | 2010
Alexandria Bridges | 2010-12-30 | 0 |  | 5096000 | 0 | 5096000 | 35589876.5 | 14.32% |  |  | 2010-12-30 | original |  |  | 2010
Alexandria Bridges | 2011-01-30 | 1500000 |  | 6596000 | 0 | 6596000 | 35589876.5 | 18.53% |  | 5121176.6 | 2011-01-30 | original |  |  | 2011
Alexandria Bridges | 2011-02-28 | 200000 |  | 6796000 | 0 | 6796000 | 35589876.5 | 19.1% |  | 1621880.16 | 2011-02-28 | original |  |  | 2011
Alexandria Bridges | 2011-03-30 | 500000 |  | 7296000 | 0 | 7296000 | 35589876.5 | 20.5% |  | 526037.81 | 2011-03-30 | original |  |  | 2011
Alexandria Bridges | 2011-04-30 | 1490000 |  | 8786000 | 0 | 8786000 | 35589876.5 | 24.69% |  | 174970.84 | 2011-04-30 | original |  |  | 2011
Alexandria Bridges | 2011-05-30 | 1150000 |  | 9936000 | 0 | 9936000 | 35589876.5 | 27.92% |  | 1802651.39 | 2011-05-30 | original |  |  | 2011
Alexandria Bridges | 2011-06-30 | 200000 |  | 10136000 | 0 | 10136000 | 35589876.5 | 28.48% |  | 1569277.4 | 2011-06-30 | original |  |  | 2011
Alexandria Bridges | 2011-07-30 | 0 |  | 10136000 | 0 | 10136000 | 35589876.5 | 28.48% |  |  | 2011-07-30 | original |  |  | 2011
Alexandria Bridges | 2011-08-30 | 1500000 |  | 11636000 | 0 | 11636000 | 35589876.5 | 32.69% |  | 0 | 2011-08-30 | original |  |  | 2011
Alexandria Bridges | 2011-09-30 | 915000 |  | 12551000 | 0 | 12551000 | 35589876.5 | 35.27% |  | 777655.22 | 2011-09-30 | original |  |  | 2011
Alexandria Bridges | 2011-10-30 | 880000 |  | 13431000 | 0 | 13431000 | 35589876.5 | 37.74% |  | 678828.4 | 2011-10-30 | original |  |  | 2011
Alexandria Bridges | 2011-11-30 | 950000 |  | 14381000 | 0 | 14381000 | 35589876.5 | 40.41% |  | 908518.86 | 2011-11-30 | original |  |  | 2011
Alexandria Bridges | 2011-12-30 | 350000 |  | 14731000 | 0 | 14731000 | 35589876.5 | 41.39% |  | 695736.66 | 2011-12-30 | original |  |  | 2011
Alexandria Bridges | 2012-01-30 | 250000 |  | 14981000 | 0 | 14981000 | 35589876.5 | 42.09% |  | 1309247.75 | 2012-01-30 | original |  |  | 2012
Alexandria Bridges | 2012-02-29 | 450000 |  | 15431000 | 0 | 15431000 | 35589876.5 | 43.36% |  | 0 | 2012-02-29 | original |  |  | 2012
Alexandria Bridges | 2012-03-30 | 370000 |  | 15801000 | 0 | 15801000 | 35589876.5 | 44.4% |  | 306264.03 | 2012-03-30 | original |  |  | 2012
Alexandria Bridges | 2012-04-30 | 250000 |  | 16051000 | 0 | 16051000 | 35589876.5 | 45.1% |  | 1751360.69 | 2012-04-30 | original |  |  | 2012
Alexandria Bridges | 2012-05-30 | 0 |  | 16051000 | 0 | 16051000 | 35589876.5 | 45.1% |  |  | 2012-05-30 | original |  |  | 2012
Alexandria Bridges | 2012-06-30 | 650000 |  | 16701000 | 0 | 16701000 | 35589876.5 | 46.93% |  | 1197055.49 | 2012-06-30 | original |  |  | 2012
Alexandria Bridges | 2012-07-30 | 0 |  | 16701000 | 0 | 16701000 | 35589876.5 | 46.93% |  |  | 2012-07-30 | original |  |  | 2012
Alexandria Bridges | 2012-08-30 | 0 |  | 16701000 | 0 | 16701000 | 35589876.5 | 46.93% |  |  | 2012-08-30 | original |  |  | 2012
Alexandria Bridges | 2012-09-30 | 1120000 |  | 17821000 | 0 | 17821000 | 35589876.5 | 50.07% |  | 2483007.3 | 2012-09-30 | original |  |  | 2012
Alexandria Bridges | 2012-10-30 | 550000 |  | 18371000 | 0 | 18371000 | 35589876.5 | 51.62% |  | 376520.46 | 2012-10-30 | original |  |  | 2012
Alexandria Bridges | 2012-11-30 | 0 |  | 18371000 | 0 | 18371000 | 35589876.5 | 51.62% |  |  | 2012-11-30 | original |  |  | 2012
Alexandria Bridges | 2012-12-30 | 2000000 |  | 20371000 | 0 | 20371000 | 35589876.5 | 57.24% |  | 1418457.17 | 2012-12-30 | original |  |  | 2012
1900
Alstom-French Station | 2016-01-31 | 0 | 41550 | 0 | 41550 | -41550 | #N/A | #N/A |  | 0 | 2016-01-31 | original |  |  | 2016
Alstom-French Station | 2016-03-31 | 0 | 102318 | 0 | 143868 | -143868 | #N/A | #N/A |  | 0 | 2016-03-31 | original |  |  | 2016
Alstom-French Station | 2016-04-30 | 0 | 442386 | 0 | 586254 | -586254 | #N/A | #N/A |  | 0 | 2016-04-30 | original |  |  | 2016
Alstom-French Station | 2016-05-31 | 0 | 2317224 | 0 | 2903478 | -2903478 | #N/A | #N/A |  | 0 | 2016-05-31 | original |  |  | 2016
Alstom-French Station | 2016-06-30 | 62880564 | 3783562 | 62880564 | 6687040 | 56193524 | #N/A | #N/A |  | 0 | 2016-06-30 | original |  |  | 2016
Alstom-French Station | 2016-07-31 | 0 | 2520105 | 62880564 | 9207145 | 53673419 | #N/A | #N/A |  | 10287160 | 2016-07-31 | original |  |  | 2016
Alstom-French Station | 2016-08-31 | 0 | 2682038 | 62880564 | 11889183 | 50991381 | #N/A | #N/A |  | 0 | 2016-08-31 | original |  |  | 2016
Alstom-French Station | 2016-09-30 | 0 | 2165753 | 62880564 | 14054936 | 48825628 | #N/A | #N/A |  | 9549945 | 2016-09-30 | original |  |  | 2016
Alstom-French Station | 2016-10-31 | 0 | 2202561 | 62880564 | 16257497 | 46623067 | #N/A | #N/A |  | 4868636 | 2016-10-31 | original |  |  | 2016
Alstom-French Station | 2016-11-30 | 0 | 14771658 | 62880564 | 31029155 | 31851409 | #N/A | #N/A |  | 24139859 | 2016-11-30 | original |  |  | 2016
Alstom-French Station | 2016-12-31 | 0 | 12434843 | 62880564 | 43463998 | 19416566 | #N/A | #N/A |  | 13767355 | 2016-12-31 | original |  |  | 2016
Alstom-French Station | 2017-01-31 | 7678950 | 4851985 | 70559514 | 48315983 | 22243531 | #N/A | #N/A |  | 3327277 | 2017-01-31 | original |  |  | 2017
Alstom-French Station | 2017-02-28 | 22832552 | 2739979 | 93392066 | 51055962 | 42336104 | #N/A | #N/A |  | 8173447 | 2017-02-28 | original |  |  | 2017
Alstom-French Station | 2017-03-31 | 3812636 | 2389640 | 97204702 | 53445602 | 43759100 | #N/A | #N/A |  | 5291063 | 2017-03-31 | original |  |  | 2017
Alstom-French Station | 2017-04-30 | 3442547 | 9468759 | 100647249 | 62914361 | 37732888 | #N/A | #N/A |  | 1461718 | 2017-04-30 | original |  |  | 2017
Alstom-French Station | 2017-05-31 | 5999615 | 2501903 | 106646864 | 65416264 | 41230600 | #N/A | #N/A |  | 670147 | 2017-05-31 | original |  |  | 2017
Alstom-French Station | 2017-06-30 | 0 | 2598562 | 106646864 | 68014826 | 38632038 | #N/A | #N/A |  | 5776026 | 2017-06-30 | original |  |  | 2017
Alstom-French Station | 2017-07-31 | 0 | 1778655 | 106646864 | 69793481 | 36853383 | #N/A | #N/A |  | 0 | 2017-07-31 | original |  |  | 2017
Alstom-French Station | 2017-08-31 | 17787964 | 2440770 | 124434828 | 72234251 | 52200577 | #N/A | #N/A |  | 5091161 | 2017-08-31 | original |  |  | 2017
Alstom-French Station | 2017-09-30 | 876288 | 668075 | 125311116 | 72902326 | 52408790 | #N/A | #N/A |  | 3371467 | 2017-09-30 | original |  |  | 2017
Alstom-French Station | 2017-10-31 | 4288254 | 2007184 | 129599370 | 74909510 | 54689860 | #N/A | #N/A |  | 15080386 | 2017-10-31 | original |  |  | 2017
Alstom-French Station | 2017-11-30 | 10186244 | 807921 | 139785614 | 75717431 | 64068183 | #N/A | #N/A |  | 17313 | 2017-11-30 | original |  |  | 2017
Alstom-French Station | 2017-12-31 | 2192203 | 268305 | 141977817 | 75985736 | 65992081 | #N/A | #N/A |  | 0 | 2017-12-31 | original |  |  | 2017
1900
Autoville Strip Mall | 2010-08-30 | 527345.15 |  | 527345.15 | 0 | 527345.15 | 51072634 | 1.033% |  | 578964.52 | 2010-08-30 | original |  |  | 2010
Autoville Strip Mall | 2010-09-30 | 812764.54 |  | 1340109.69 | 0 | 1340109.69 | 51072634 | 2.624% |  | 1047851.19 | 2010-09-30 | original |  |  | 2010
Autoville Strip Mall | 2010-10-30 | 1228985.92 |  | 2569095.61 | 0 | 2569095.61 | 51072634 | 5.03% |  | 1807137.46 | 2010-10-30 | original |  |  | 2010
Autoville Strip Mall | 2010-11-30 | 637825 |  | 3206920.61 | 0 | 3206920.61 | 51072634 | 6.279% |  | 1163582.93 | 2010-11-30 | original |  |  | 2010
Autoville Strip Mall | 2010-12-30 | 1168758.7 |  | 4375679.31 | 0 | 4375679.31 | 51072634 | 8.568% |  | 1603576.1 | 2010-12-30 | original |  |  | 2010
Autoville Strip Mall | 2011-01-30 |  |  | 4375679.31 | 0 | 4375679.31 | 51072634 | 8.568% |  |  | 2011-01-30 | original |  |  | 2011
Autoville Strip Mall | 2011-02-28 | 1839270.15 |  | 6214949.46 | 0 | 6214949.46 | 51072634 | 12.17% |  | 2857058.37 | 2011-02-28 | original |  |  | 2011
Autoville Strip Mall | 2011-03-30 |  |  | 6214949.46 | 0 | 6214949.46 | 51072634 | 12.17% |  |  | 2011-03-30 | original |  |  | 2011
Autoville Strip Mall | 2011-04-30 | 1103798.1 |  | 7318747.56 | 0 | 7318747.56 | 51072634 | 14.33% |  | 1640084.44 | 2011-04-30 | original |  |  | 2011
Autoville Strip Mall | 2011-05-30 | 1667864.79 |  | 8986612.35 | 0 | 8986612.35 | 51072634 | 17.6% |  | 2630742.58 | 2011-05-30 | original |  |  | 2011
Autoville Strip Mall | 2011-06-30 | 1044888.93 |  | 10031501.28 | 0 | 10031501.28 | 51072634 | 19.64% |  | 1599236.57 | 2011-06-30 | original |  |  | 2011
Autoville Strip Mall | 2011-07-30 | 4040565.4 |  | 14072066.68 | 0 | 14072066.68 | 51072634 | 27.55% |  | 2531332.15 | 2011-07-30 | original |  |  | 2011
Autoville Strip Mall | 2011-08-30 | 1274229 |  | 15346295.68 | 0 | 15346295.68 | 51072634 | 30.05% |  | 1914179.35 | 2011-08-30 | original |  |  | 2011
Autoville Strip Mall | 2011-09-30 | 1655521.61 |  | 17001817.29 | 0 | 17001817.29 | 51072634 | 33.29% |  | 2826232.64 | 2011-09-30 | original |  |  | 2011
Autoville Strip Mall | 2011-10-30 | 1112667.42 |  | 18114484.71 | 0 | 18114484.71 | 51072634 | 35.47% |  | 1502687.29 | 2011-10-30 | original |  |  | 2011
Autoville Strip Mall | 2011-11-30 | 898433.3 |  | 19012918.01 | 0 | 19012918.01 | 51072634 | 37.23% |  | 1234163.11 | 2011-11-30 | original |  |  | 2011
Autoville Strip Mall | 2011-12-30 | 1194116.1 |  | 20207034.11 | 0 | 20207034.11 | 51072634 | 39.57% |  | 1761743.932 | 2011-12-30 | original |  |  | 2011
Autoville Strip Mall | 2012-01-30 | 1450011.88 |  | 21657045.99 | 0 | 21657045.99 | 51072634 | 42.4% |  | 1841736.449 | 2012-01-30 | original |  |  | 2012
Autoville Strip Mall | 2012-02-29 | 1698106 |  | 23355151.99 | 0 | 23355151.99 | 51072634 | 45.73% |  | 2945473.265 | 2012-02-29 | original |  |  | 2012
Autoville Strip Mall | 2012-03-30 | 1726582.17 |  | 25081734.16 | 0 | 25081734.16 | 51072634 | 49.11% |  | 2583612.284 | 2012-03-30 | original |  |  | 2012
Autoville Strip Mall | 2012-04-30 | 453007.6 |  | 25534741.76 | 0 | 25534741.76 | 51072634 | 50% |  | 3757768.07 | 2012-04-30 | original |  |  | 2012
Autoville Strip Mall | 2012-05-30 |  |  | 25534741.76 | 0 | 25534741.76 | 51072634 | 50% |  |  | 2012-05-30 | original |  |  | 2012
Autoville Strip Mall | 2012-06-30 | 1054923.69 |  | 26589665.45 | 0 | 26589665.45 | 51072634 | 52.06% |  | 1469112.716 | 2012-06-30 | original |  |  | 2012
Autoville Strip Mall | 2012-07-30 | 419730.92 |  | 27009396.37 | 0 | 27009396.37 | 51072634 | 52.88% |  | 470039.964 | 2012-07-30 | original |  |  | 2012
Autoville Strip Mall | 2012-08-30 | 17883.33 |  | 27027279.7 | 0 | 27027279.7 | 51072634 | 52.92% |  | 274501.41 | 2012-08-30 | original |  |  | 2012
Autoville Strip Mall | 2012-09-30 | 610137 |  | 27637416.7 | 0 | 27637416.7 | 51072634 | 54.11% |  | 554573.35 | 2012-09-30 | original |  |  | 2012
Autoville Strip Mall | 2012-10-30 |  |  | 27637416.7 | 0 | 27637416.7 | 51072634 | 54.11% |  |  | 2012-10-30 | original |  |  | 2012
Autoville Strip Mall | 2012-11-30 | 364111.32 |  | 28001528.02 | 0 | 28001528.02 | 51072634 | 54.83% |  | 418483 | 2012-11-30 | original |  |  | 2012
Autoville Strip Mall | 2012-12-30 | 415290.57 |  | 28416818.59 | 0 | 28416818.59 | 51072634 | 55.64% |  | 406487.07 | 2012-12-30 | original |  |  | 2012
Autoville Strip Mall | 2013-01-30 |  |  | 28416818.59 | 0 | 28416818.59 | 51072634 | 55.64% |  | 1358638.66 | 2013-01-30 | original |  |  | 2013
Autoville Strip Mall | 2013-02-28 |  |  | 28416818.59 | 0 | 28416818.59 | 51072634 | 55.64% |  |  | 2013-02-28 | original |  |  | 2013
Autoville Strip Mall | 2013-03-30 |  |  | 28416818.59 | 0 | 28416818.59 | 51072634 | 55.64% |  |  | 2013-03-30 | original |  |  | 2013
Autoville Strip Mall | 2013-04-30 | 1048008.48 |  | 29464827.07 | 0 | 29464827.07 | 51072634 | 57.69% |  | 502054.965 | 2013-04-30 | original |  |  | 2013
Autoville Strip Mall | 2013-05-30 | 691323.34 |  | 30156150.41 | 0 | 30156150.41 | 51072634 | 59.05% |  | 1393383.145 | 2013-05-30 | original |  |  | 2013
Autoville Strip Mall | 2013-06-30 | 561893.75 |  | 30718044.16 | 0 | 30718044.16 | 51072634 | 60.15% |  | 766026.75 | 2013-06-30 | original |  |  | 2013
Autoville Strip Mall | 2013-07-30 | 579836.99 |  | 31297881.15 | 0 | 31297881.15 | 51072634 | 61.28% |  | 649050.24 | 2013-07-30 | original |  |  | 2013
Autoville Strip Mall | 2013-08-30 | 441588.76 |  | 31739469.91 | 0 | 31739469.91 | 51072634 | 62.15% |  | 317586.06 | 2013-08-30 | original |  |  | 2013
Autoville Strip Mall | 2013-09-30 | 1667148 |  | 33406617.91 | 0 | 33406617.91 | 51072634 | 65.41% |  | 1035096.92 | 2013-09-30 | original |  |  | 2013
Autoville Strip Mall | 2013-10-30 |  |  | 33406617.91 | 0 | 33406617.91 | 51072634 | 65.41% |  |  | 2013-10-30 | original |  |  | 2013
Autoville Strip Mall | 2013-11-30 | 1056818.84 |  | 34463436.75 | 0 | 34463436.75 | 51072634 | 67.48% |  | 1093224.05 | 2013-11-30 | original |  |  | 2013
Autoville Strip Mall | 2013-12-30 |  |  | 34463436.75 | 0 | 34463436.75 | 51072634 | 67.48% |  | 487957.7 | 2013-12-30 | original |  |  | 2013
Autoville Strip Mall | 2014-01-30 | 611443.97 | 85921.22 | 35074880.72 | 85921.22 | 34988959.5 | 51072634 | 68.51% |  |  | 2014-01-30 | original |  |  | 2014
Autoville Strip Mall | 2014-02-28 | 0 | 218054.59 | 35074880.72 | 303975.81 | 34770904.91 | 51072634 | 68.08% |  | 893468 | 2014-02-28 | original |  |  | 2014
Autoville Strip Mall | 2014-03-29 | 42691.91 | 140856.67 | 35117572.63 | 444832.48 | 34672740.15 | 51072634 | 67.89% |  |  | 2014-03-29 | original |  |  | 2014
Autoville Strip Mall | 2014-04-27 | 2809347.96 | 124046.79 | 37926920.59 | 568879.27 | 37358041.32 | 51072634 | 73.15% |  |  | 2014-04-27 | original |  |  | 2014
Autoville Strip Mall | 2014-05-26 |  | 52430.99 | 37926920.59 | 621310.26 | 37305610.33 | 51072634 | 73.04% |  |  | 2014-05-26 | original |  |  | 2014
Autoville Strip Mall | 2014-06-24 |  | 45526.92 | 37926920.59 | 666837.18 | 37260083.41 | 51072634 | 72.96% |  |  | 2014-06-24 | original |  |  | 2014
Autoville Strip Mall | 2014-07-23 |  | 57525.72 | 37926920.59 | 724362.9 | 37202557.69 | 51072634 | 72.84% |  |  | 2014-07-23 | original |  |  | 2014
Autoville Strip Mall | 2014-08-21 |  | 8333.49 | 37926920.59 | 732696.39 | 37194224.2 | 51072634 | 72.83% |  |  | 2014-08-21 | original |  |  | 2014
Autoville Strip Mall | 2014-09-19 |  | 0 | 37926920.59 | 732696.39 | 37194224.2 | 51072634 | 72.83% |  |  | 2014-09-19 | original |  |  | 2014
Autoville Strip Mall | 2014-10-18 |  | 0 | 37926920.59 | 732696.39 | 37194224.2 | 51072634 | 72.83% |  |  | 2014-10-18 | original |  |  | 2014
Autoville Strip Mall | 2014-11-16 |  | 197496.71 | 37926920.59 | 930193.1 | 36996727.49 | 51072634 | 72.44% |  |  | 2014-11-16 | original |  |  | 2014
Autoville Strip Mall | 2014-12-15 |  | 49733.79 | 37926920.59 | 979926.89 | 36946993.7 | 51072634 | 72.34% |  |  | 2014-12-15 | original |  |  | 2014
1900
El Mahala Bridge | 2014-01-31 |  | 167056.05 | 0 | 167056.05 | -167056.05 | 67245402 | -0.2484% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-02-28 |  | 337593.25 | 0 | 504649.3 | -504649.3 | 67245402 | -0.7505% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-03-31 |  | 236892.16 | 0 | 741541.46 | -741541.46 | 67245402 | -1.103% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-04-30 |  | 406729.32 | 0 | 1148270.78 | -1148270.78 | 67245402 | -1.708% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-05-31 |  | 623744.84 | 0 | 1772015.62 | -1772015.62 | 67245402 | -2.635% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-06-30 |  | 694547.28 | 0 | 2466562.9 | -2466562.9 | 67245402 | -3.668% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-07-31 |  | 1166548.74 | 0 | 3633111.64 | -3633111.64 | 67245402 | -5.403% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-08-31 |  | 999419.35 | 0 | 4632530.99 | -4632530.99 | 67245402 | -6.889% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-09-30 |  | 1205874.08 | 0 | 5838405.07 | -5838405.07 | 67245402 | -8.682% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-10-31 |  | 952769.73 | 0 | 6791174.8 | -6791174.8 | 67245402 | -10.1% |  |  |  | original |  |  | 2014
El Mahala Bridge | 2014-11-30 | 0 | 2196536.4 | 0 | 8987711.2 | -8987711.2 | 67245402 | -13.37% |  | 42859946 | 2014-11-30 | original |  |  | 2014
El Mahala Bridge | 2014-12-31 | 13887457 | 3846353.54 | 13887457 | 12834064.74 | 1053392.26 | 67245402 | 1.566% |  | 0 | 2014-12-31 | original |  |  | 2014
El Mahala Bridge | 2015-01-31 | 3792225 | 2469766 | 17679682 | 15303830.74 | 2375851.26 | 67245402 | 3.533% |  | 4424505 | 2015-01-31 | original |  |  | 2015
El Mahala Bridge | 2015-02-28 | 10225673 | 999379 | 27905355 | 16303209.74 | 11602145.26 | 67245402 | 17.25% |  | 0 | 2015-02-28 | original |  |  | 2015
El Mahala Bridge | 2015-03-31 | 828261 | 2021463 | 28733616 | 18324672.74 | 10408943.26 | 67245402 | 15.48% |  | 6770565 | 2015-03-31 | original |  |  | 2015
El Mahala Bridge | 2015-04-30 | 0 | 1796856 | 28733616 | 20121528.74 | 8612087.26 | 67245402 | 12.81% |  | 8178995 | 2015-04-30 | original |  |  | 2015
El Mahala Bridge | 2015-05-31 | 0 | 1314563 | 28733616 | 21436091.74 | 7297524.26 | 67245402 | 10.85% |  | 0 | 2015-05-31 | original |  |  | 2015
El Mahala Bridge | 2015-06-30 | 4569470 | 1127121 | 33303086 | 22563212.74 | 10739873.26 | 67245402 | 15.97% |  | 5196348 | 2015-06-30 | original |  |  | 2015
El Mahala Bridge | 2015-07-31 | 0 | 862981 | 33303086 | 23426193.74 | 9876892.26 | 67245402 | 14.69% |  | 0 | 2015-07-31 | original |  |  | 2015
El Mahala Bridge | 2015-08-31 | 0 | 1148916 | 33303086 | 24575109.74 | 8727976.26 | 67245402 | 12.98% |  | 0 | 2015-08-31 | original |  |  | 2015
El Mahala Bridge | 2015-09-30 | 0 | 86025 | 33303086 | 24661134.74 | 8641951.26 | 67245402 | 12.85% |  | 0 | 2015-09-30 | original |  |  | 2015
El Mahala Bridge | 2015-10-31 | 0 | 88349 | 33303086 | 24749483.74 | 8553602.26 | 67245402 | 12.72% |  | 0 | 2015-10-31 | original |  |  | 2015
El Mahala Bridge | 2015-11-30 | 0 | 27280 | 33303086 | 24776763.74 | 8526322.26 | 67245402 | 12.68% |  | 0 | 2015-11-30 | original |  |  | 2015
El Mahala Bridge | 2015-12-31 | 0 | 32091 | 33303086 | 24808854.74 | 8494231.26 | 67245402 | 12.63% |  | 0 | 2015-12-31 | original |  |  | 2015
El Mahala Bridge | 2016-05-31 | 0 | 690072 | 33303086 | 25498926.74 | 7804159.26 | 67245402 | 11.61% |  | 0 | 2016-05-31 | original |  |  | 2016
El Mahala Bridge | 2016-06-30 | 14775102 | 0 | 48078188 | 25498926.74 | 22579261.26 | 67245402 | 33.58% |  | 0 | 2016-06-30 | original |  |  | 2016
El Mahala Bridge | 2016-08-31 | 0 | 433350 | 48078188 | 25932276.74 | 22145911.26 | 67245402 | 32.93% |  | 0 | 2016-08-31 | original |  |  | 2016
El Mahala Bridge | 2016-09-30 | 0 | 25721 | 48078188 | 25957997.74 | 22120190.26 | 67245402 | 32.89% |  | 0 | 2016-09-30 | original |  |  | 2016
El Mahala Bridge | 2016-10-31 | 0 | 106875 | 48078188 | 26064872.74 | 22013315.26 | 67245402 | 32.74% |  | 0 | 2016-10-31 | original |  |  | 2016
1900
EMEC | 2011-03-31 | 812266.13 |  | 812266.13 | 0 | 812266.13 | 10688481.1 | 7.599% |  | 992881.9242 | 2011-03-31 | original |  |  | 2011
EMEC | 2011-04-30 | 674406.29 |  | 1486672.42 | 0 | 1486672.42 | 10688481.1 | 13.91% |  | 824443.8678 | 2011-04-30 | original |  |  | 2011
EMEC | 2011-05-31 | 508827.95 |  | 1995500.37 | 0 | 1995500.37 | 10688481.1 | 18.67% |  | 999206.9582 | 2011-05-31 | original |  |  | 2011
EMEC | 2011-06-30 | 891799.85 |  | 2887300.22 | 0 | 2887300.22 | 10688481.1 | 27.01% |  | 1298338.2507 | 2011-06-30 | original |  |  | 2011
EMEC | 2011-07-31 | 864555.37 |  | 3751855.59 | 0 | 3751855.59 | 10688481.1 | 35.1% |  | 1638114.3926 | 2011-07-31 | original |  |  | 2011
EMEC | 2011-08-31 | 1289991 |  | 5041846.59 | 0 | 5041846.59 | 10688481.1 | 47.17% |  | 1706277.2109 | 2011-08-31 | original |  |  | 2011
EMEC | 2011-09-30 | 169807.73 |  | 5211654.32 | 0 | 5211654.32 | 10688481.1 | 48.76% |  | 602710.068 | 2011-09-30 | original |  |  | 2011
EMEC | 2011-10-31 | 615234.08 |  | 5826888.4 | 0 | 5826888.4 | 10688481.1 | 54.52% |  | 964040.2041 | 2011-10-31 | original |  |  | 2011
EMEC | 2011-11-30 | 391126 |  | 6218014.4 | 0 | 6218014.4 | 10688481.1 | 58.17% |  | 847281.2828 | 2011-11-30 | original |  |  | 2011
EMEC | 2011-12-31 | 0 |  | 6218014.4 | 0 | 6218014.4 | 10688481.1 | 58.17% |  | 235607.3664 | 2011-12-31 | original |  |  | 2011
EMEC | 2012-01-31 | 231974.16 |  | 6449988.56 | 0 | 6449988.56 | 10688481.1 | 60.35% |  | 39547.2983 | 2012-01-31 | original |  |  | 2012
EMEC | 2012-02-29 | 61854.48 |  | 6511843.04 | 0 | 6511843.04 | 10688481.1 | 60.92% |  | 0 | 2012-02-29 | original |  |  | 2012
EMEC | 2012-03-31 |  |  | 6511843.04 | 0 | 6511843.04 | 10688481.1 | 60.92% |  | 238802.0019 | 2012-03-31 | original |  |  | 2012
1900
Logestica 02 | 2011-09-30 | 534360.87 |  | 534360.87 | 0 | 534360.87 | #N/A | #N/A |  | 375293.05 | 2011-09-30 | original |  |  | 2011
Logestica 02 | 2011-10-30 | 334260.48 |  | 868621.35 | 0 | 868621.35 | #N/A | #N/A |  | 403480.81 | 2011-10-30 | original |  |  | 2011
Logestica 02 | 2011-11-30 | 1006563.08 |  | 1875184.43 | 0 | 1875184.43 | #N/A | #N/A |  | 1179260.82 | 2011-11-30 | original |  |  | 2011
Logestica 02 | 2011-12-30 | 1679999.78 |  | 3555184.21 | 0 | 3555184.21 | #N/A | #N/A |  | 1871385.39 | 2011-12-30 | original |  |  | 2011
Logestica 02 | 2012-01-30 | 2279316.26 |  | 5834500.47 | 0 | 5834500.47 | #N/A | #N/A |  | 1570447.18 | 2012-01-30 | original |  |  | 2012
Logestica 02 | 2012-02-29 | 1901607.28 |  | 7736107.75 | 0 | 7736107.75 | #N/A | #N/A |  | 2724779.37 | 2012-02-29 | original |  |  | 2012
Logestica 02 | 2012-03-30 | 2758362.75 |  | 10494470.5 | 0 | 10494470.5 | #N/A | #N/A |  | 2095362.63 | 2012-03-30 | original |  |  | 2012
Logestica 02 | 2012-04-30 | 4207798.04 |  | 14702268.54 | 0 | 14702268.54 | #N/A | #N/A |  | 4819059.94 | 2012-04-30 | original |  |  | 2012
Logestica 02 | 2012-05-30 | 4500000 |  | 19202268.54 | 0 | 19202268.54 | #N/A | #N/A |  | 6902632.47 | 2012-05-30 | original |  |  | 2012
Logestica 02 | 2012-06-30 | 5018951.63 |  | 24221220.17 | 0 | 24221220.17 | #N/A | #N/A |  | 6531346.74 | 2012-06-30 | original |  |  | 2012
Logestica 02 | 2012-07-30 | 0 |  | 24221220.17 | 0 | 24221220.17 | #N/A | #N/A |  | 0 | 2012-07-30 | original |  |  | 2012
Logestica 02 | 2012-08-30 | 2500000 |  | 26721220.17 | 0 | 26721220.17 | #N/A | #N/A |  | 3410178.97 | 2012-08-30 | original |  |  | 2012
Logestica 02 | 2012-09-30 | 0 |  | 26721220.17 | 0 | 26721220.17 | #N/A | #N/A |  | 0 | 2012-09-30 | original |  |  | 2012
Logestica 02 | 2012-10-30 | 800000 |  | 27521220.17 | 0 | 27521220.17 | #N/A | #N/A |  | 1364060.05 | 2012-10-30 | original |  |  | 2012
Logestica 02 | 2012-11-30 | 2518175.49 |  | 30039395.66 | 0 | 30039395.66 | #N/A | #N/A |  | 1953643.09 | 2012-11-30 | original |  |  | 2012
Logestica 02 | 2012-12-30 | 2967694.05 |  | 33007089.71 | 0 | 33007089.71 | #N/A | #N/A |  | 1336128.87 | 2012-12-30 | original |  |  | 2012
Logestica 02 | 2013-01-30 | 1089297.15 |  | 34096386.86 | 0 | 34096386.86 | #N/A | #N/A |  | 1954100.51 | 2013-01-30 | original |  |  | 2013
Logestica 02 | 2013-02-28 | 1250000 |  | 35346386.86 | 0 | 35346386.86 | #N/A | #N/A |  | 2058351.48 | 2013-02-28 | original |  |  | 2013
Logestica 02 | 2013-03-30 | 3053495.58 |  | 38399882.44 | 0 | 38399882.44 | #N/A | #N/A |  | 3470871.08 | 2013-03-30 | original |  |  | 2013
Logestica 02 | 2013-04-30 | 2800000 |  | 41199882.44 | 0 | 41199882.44 | #N/A | #N/A |  | 4814116.3 | 2013-04-30 | original |  |  | 2013
Logestica 02 | 2013-05-30 | 0 |  | 41199882.44 | 0 | 41199882.44 | #N/A | #N/A |  | 0 | 2013-05-30 | original |  |  | 2013
Logestica 02 | 2013-06-30 | 1645440.77 |  | 42845323.21 | 0 | 42845323.21 | #N/A | #N/A |  | 1583441.85 | 2013-06-30 | original |  |  | 2013
Logestica 02 | 2013-07-30 | 1648683.42 |  | 44494006.63 | 0 | 44494006.63 | #N/A | #N/A |  | 1024930.11 | 2013-07-30 | original |  |  | 2013
Logestica 02 | 2013-08-30 | 594687.94 |  | 45088694.57 | 0 | 45088694.57 | #N/A | #N/A |  | -131791.54 | 2013-08-30 | original |  |  | 2013
Logestica 02 | 2013-09-30 | 0 |  | 45088694.57 | 0 | 45088694.57 | #N/A | #N/A |  | 0 | 2013-09-30 | original |  |  | 2013
Logestica 02 | 2013-10-30 | 101291.61 |  | 45189986.18 | 0 | 45189986.18 | #N/A | #N/A |  | 485933.48 | 2013-10-30 | original |  |  | 2013
Logestica 02 | 2013-11-30 | 0 |  | 45189986.18 | 0 | 45189986.18 | #N/A | #N/A |  | 0 | 2013-11-30 | original |  |  | 2013
Logestica 02 | 2013-12-30 | 0 |  | 45189986.18 | 0 | 45189986.18 | #N/A | #N/A |  | 616183.61 | 2013-12-30 | original |  |  | 2013
Logestica 02 | 2014-01-30 | 592312 | 219556.83 | 45782298.18 | 219556.83 | 45562741.35 | #N/A | #N/A |  | 194134.03 | 2014-01-30 | original |  |  | 2014
Logestica 02 | 2014-02-28 | 0 | 548413.6 | 45782298.18 | 767970.43 | 45014327.75 | #N/A | #N/A |  | 0 | 2014-02-28 | original |  |  | 2014
Logestica 02 | 2014-03-30 | 300000 | 244155.28 | 46082298.18 | 1012125.71 | 45070172.47 | #N/A | #N/A |  | 1010207.12 | 2014-03-30 | original |  |  | 2014
Logestica 02 | 2014-04-30 | 1000000 | 1037944.46 | 47082298.18 | 2050070.17 | 45032228.01 | #N/A | #N/A |  | 0 | 2014-04-30 | original |  |  | 2014
Logestica 02 | 2014-05-30 | 1700000 | 626142.17 | 48782298.18 | 2676212.34 | 46106085.84 | #N/A | #N/A |  | 2683058.29 | 2014-05-30 | original |  |  | 2014
Logestica 02 | 2014-06-30 | 0 | 576920.45 | 48782298.18 | 3253132.79 | 45529165.39 | #N/A | #N/A |  | 0 | 2014-06-30 | original |  |  | 2014
Logestica 02 | 2014-07-30 | 0 | 162116.34 | 48782298.18 | 3415249.13 | 45367049.05 | #N/A | #N/A |  | 594603.41 | 2014-07-30 | original |  |  | 2014
Logestica 02 | 2014-08-30 | 122257 | 222464.85 | 48904555.18 | 3637713.98 | 45266841.2 | #N/A | #N/A |  | 0 | 2014-08-30 | original |  |  | 2014
Logestica 02 | 2014-09-30 | 750000 | 0 | 49654555.18 | 3637713.98 | 46016841.2 | #N/A | #N/A |  | 0 | 2014-09-30 | original |  |  | 2014
Logestica 02 | 2014-10-30 | 0 | 29950.72 | 49654555.18 | 3667664.7 | 45986890.48 | #N/A | #N/A |  | 314772.28 | 2014-10-30 | original |  |  | 2014
Logestica 02 | 2014-11-30 | 0 | 66593.71 | 49654555.18 | 3734258.41 | 45920296.77 | #N/A | #N/A |  | 0 | 2014-11-30 | original |  |  | 2014
Logestica 02 | 2014-12-31 | 480000 | 15443 | 50134555.18 | 3749701.41 | 46384853.77 | #N/A | #N/A |  | 0 | 2014-12-31 | original |  |  | 2014
1900
Marassi Bridges Pkg 37 | 2014-12-31 | 22164568 | 22879392 | 22164568 | 22879392 | -714824 | 26193836.68 | -2.729% |  | 0 | 2014-12-31 | original |  |  | 2014
Marassi Bridges Pkg 37 | 2015-01-31 | 455102 | 258131 | 22619670 | 23137523 | -517853 | 26193836.68 | -1.977% |  | 0 | 2015-01-31 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-02-28 | 0 | 223477 | 22619670 | 23361000 | -741330 | 26193836.68 | -2.83% |  | 668823 | 2015-02-28 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-03-31 | 0 | 274333 | 22619670 | 23635333 | -1015663 | 26193836.68 | -3.877% |  | 0 | 2015-03-31 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-04-30 | 0 | 176327 | 22619670 | 23811660 | -1191990 | 26193836.68 | -4.551% |  | 136217 | 2015-04-30 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-05-31 | 598246 | 256471 | 23217916 | 24068131 | -850215 | 26193836.68 | -3.246% |  | 0 | 2015-05-31 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-06-30 | 460061 | 240419 | 23677977 | 24308550 | -630573 | 26193836.68 | -2.407% |  | 0 | 2015-06-30 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-07-31 | 0 | 32883 | 23677977 | 24341433 | -663456 | 26193836.68 | -2.533% |  | 0 | 2015-07-31 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-08-31 | 0 | 0 | 23677977 | 24341433 | -663456 | 26193836.68 | -2.533% |  | 42523 | 2015-08-31 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-09-30 | 57351 | 0 | 23735328 | 24341433 | -606105 | 26193836.68 | -2.314% |  | 0 | 2015-09-30 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-11-30 | 256625 | 13606 | 23991953 | 24355039 | -363086 | 26193836.68 | -1.386% |  | 0 | 2015-11-30 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2015-12-31 | 0 | 2516 | 23991953 | 24357555 | -365602 | 26193836.68 | -1.396% |  | 104583 | 2015-12-31 | original |  |  | 2015
Marassi Bridges Pkg 37 | 2016-01-31 | 48358 | 0 | 24040311 | 24357555 | -317244 | 26193836.68 | -1.211% |  | 0 | 2016-01-31 | original |  |  | 2016
Marassi Bridges Pkg 37 | 2016-03-31 | 335562 | 0 | 24375873 | 24357555 | 18318 | 26193836.68 | 0.06993% |  | 0 | 2016-03-31 | original |  |  | 2016
Marassi Bridges Pkg 37 | 2016-04-30 | 0 | 19673 | 24375873 | 24377228 | -1355 | 26193836.68 | -0.005173% |  | 0 | 2016-04-30 | original |  |  | 2016
Marassi Bridges Pkg 37 | 2016-06-30 | 0 | 96561 | 24375873 | 24473789 | -97916 | 26193836.68 | -0.3738% |  | 0 | 2016-06-30 | original |  |  | 2016
Marassi Bridges Pkg 37 | 2016-08-31 | 398372 | 0 | 24774245 | 24473789 | 300456 | 26193836.68 | 1.147% |  | 0 | 2016-08-31 | original |  |  | 2016
1900
Marassi Golf Maintance Building Pkg 58 | 2013-08-31 | 0 | 71947 | 0 | 71947 | -71947 | 4720405.25 | -1.524% |  | 0 | 2013-08-31 | original |  |  | 2013
Marassi Golf Maintance Building Pkg 58 | 2013-10-31 | 0 | 412339 | 0 | 484286 | -484286 | 4720405.25 | -10.26% |  | 0 | 2013-10-31 | original |  |  | 2013
Marassi Golf Maintance Building Pkg 58 | 2013-11-30 | 0 | 482288 | 0 | 966574 | -966574 | 4720405.25 | -20.48% |  | 0 | 2013-11-30 | original |  |  | 2013
Marassi Golf Maintance Building Pkg 58 | 2013-12-31 | 0 | 226750 | 0 | 1193324 | -1193324 | 4720405.25 | -25.28% |  | 0 | 2013-12-31 | original |  |  | 2013
Marassi Golf Maintance Building Pkg 58 | 2014-01-31 | 376486.77 | 272717.48 | 376486.77 | 1466041.48 | -1089554.71 | 4720405.25 | -23.08% |  | 0 | 2014-01-31 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-02-28 | 173298.19 | 253081.73 | 549784.96 | 1719123.21 | -1169338.25 | 4720405.25 | -24.77% |  | 0 | 2014-02-28 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-03-31 | 222016.09 | 269914.66 | 771801.05 | 1989037.87 | -1217236.82 | 4720405.25 | -25.79% |  | 0 | 2014-03-31 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-04-30 | 0 | 415105.46 | 771801.05 | 2404143.33 | -1632342.28 | 4720405.25 | -34.58% |  | 0 | 2014-04-30 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-05-31 | 370600.71 | 129085.96 | 1142401.76 | 2533229.29 | -1390827.53 | 4720405.25 | -29.46% |  | 0 | 2014-05-31 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-06-30 | 0 | 302227.7 | 1142401.76 | 2835456.99 | -1693055.23 | 4720405.25 | -35.87% |  | 0 | 2014-06-30 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-07-31 | 0 | 254281.63 | 1142401.76 | 3089738.62 | -1947336.86 | 4720405.25 | -41.25% |  | 0 | 2014-07-31 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-08-31 | 339924.47 | 92749.94 | 1482326.23 | 3182488.56 | -1700162.33 | 4720405.25 | -36.02% |  | 0 | 2014-08-31 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-09-30 | 95706.34 | 179422.25 | 1578032.57 | 3361910.81 | -1783878.24 | 4720405.25 | -37.79% |  | 0 | 2014-09-30 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-10-31 | 296267.7 | 197897.23 | 1874300.27 | 3559808.04 | -1685507.77 | 4720405.25 | -35.71% |  | 0 | 2014-10-31 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-11-30 | 149820.58 | 156171.85 | 2024120.85 | 3715979.89 | -1691859.04 | 4720405.25 | -35.84% |  | 0 | 2014-11-30 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2014-12-31 | 55333.35 | 334619 | 2079454.2 | 4050598.89 | -1971144.69 | 4720405.25 | -41.76% |  | 3658393 | 2014-12-31 | original |  |  | 2014
Marassi Golf Maintance Building Pkg 58 | 2015-01-31 | 107852 | 187198 | 2187306.2 | 4237796.89 | -2050490.69 | 4720405.25 | -43.44% |  | 187198 | 2015-01-31 | original |  |  | 2015
Marassi Golf Maintance Building Pkg 58 | 2015-03-31 | 148615 | 76348 | 2335921.2 | 4314144.89 | -1978223.69 | 4720405.25 | -41.91% |  | 76348 | 2015-03-31 | original |  |  | 2015
Marassi Golf Maintance Building Pkg 58 | 2015-06-30 | 60612 | 0 | 2396533.2 | 4314144.89 | -1917611.69 | 4720405.25 | -40.62% |  | 0 | 2015-06-30 | original |  |  | 2015
Marassi Golf Maintance Building Pkg 58 | 2015-07-31 | 0 | 591754 | 2396533.2 | 4905898.89 | -2509365.69 | 4720405.25 | -53.16% |  | 591754 | 2015-07-31 | original |  |  | 2015
Marassi Golf Maintance Building Pkg 58 | 2015-09-30 | 347788 | 115507 | 2744321.2 | 5021405.89 | -2277084.69 | 4720405.25 | -48.24% |  | 0 | 2015-09-30 | original |  |  | 2015
Marassi Golf Maintance Building Pkg 58 | 2015-10-31 | 58700 | 0 | 2803021.2 | 5021405.89 | -2218384.69 | 4720405.25 | -47% |  | 0 | 2015-10-31 | original |  |  | 2015
Marassi Golf Maintance Building Pkg 58 | 2015-12-31 | 0 | 228097 | 2803021.2 | 5249502.89 | -2446481.69 | 4720405.25 | -51.83% |  | 0 | 2015-12-31 | original |  |  | 2015
Marassi Golf Maintance Building Pkg 58 | 2016-01-31 | 48540 | 0 | 2851561.2 | 5249502.89 | -2397941.69 | 4720405.25 | -50.8% |  | 0 | 2016-01-31 | original |  |  | 2016
1900
Uptown Service Buildings Pkg 17A | 2014-02-28 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 932431 | 2014-02-28 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-03-31 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 2923296 | 2014-03-31 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-04-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 873212 | 2014-04-30 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-05-31 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 1533995 | 2014-05-31 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-06-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 721222 | 2014-06-30 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-07-31 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 945578 | 2014-07-31 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-08-31 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 248465 | 2014-08-31 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-09-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 565896 | 2014-09-30 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-10-31 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 655576 | 2014-10-31 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-11-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  | 622078 | 2014-11-30 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2014-12-31 | 9650499 | 9673297 | 9650499 | 9673297 | -22798 | 55905931 | -0.04078% |  | 858276 | 2014-12-31 | original |  |  | 2014
Uptown Service Buildings Pkg 17A | 2015-01-31 | 983001 | 275398 | 10633500 | 9948695 | 684805 | 55905931 | 1.225% |  | 168006 | 2015-01-31 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-02-28 | 581832 | 464417 | 11215332 | 10413112 | 802220 | 55905931 | 1.435% |  | 402361 | 2015-02-28 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-03-31 | 639609 | 447496 | 11854941 | 10860608 | 994333 | 55905931 | 1.779% |  | 0 | 2015-03-31 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-04-30 | 324662 | 472109 | 12179603 | 11332717 | 846886 | 55905931 | 1.515% |  | 0 | 2015-04-30 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-05-31 | 0 | 479590 | 12179603 | 11812307 | 367296 | 55905931 | 0.657% |  | 1293019 | 2015-05-31 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-06-30 | 0 | 486461 | 12179603 | 12298768 | -119165 | 55905931 | -0.2132% |  | 0 | 2015-06-30 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-07-31 | 530306 | 564423 | 12709909 | 12863191 | -153282 | 55905931 | -0.2742% |  | 0 | 2015-07-31 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-08-31 | 0 | 910803 | 12709909 | 13773994 | -1064085 | 55905931 | -1.903% |  | 930855 | 2015-08-31 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-09-30 | 0 | 776990 | 12709909 | 14550984 | -1841075 | 55905931 | -3.293% |  | 0 | 2015-09-30 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-10-31 | 0 | 1111148 | 12709909 | 15662132 | -2952223 | 55905931 | -5.281% |  | 408632 | 2015-10-31 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-11-30 | 0 | 162511 | 12709909 | 15824643 | -3114734 | 55905931 | -5.571% |  | 0 | 2015-11-30 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2015-12-31 | 0 | 77434 | 12709909 | 15902077 | -3192168 | 55905931 | -5.71% |  | 53264 | 2015-12-31 | original |  |  | 2015
Uptown Service Buildings Pkg 17A | 2016-01-31 | 1145796 | 27324 | 13855705 | 15929401 | -2073696 | 55905931 | -3.709% |  | 0 | 2016-01-31 | original |  |  | 2016
Uptown Service Buildings Pkg 17A | 2016-02-29 | 591788 | 7800 | 14447493 | 15937201 | -1489708 | 55905931 | -2.665% |  | 0 | 2016-02-29 | original |  |  | 2016
Uptown Service Buildings Pkg 17A | 2016-03-31 | 0 | 35523 | 14447493 | 15972724 | -1525231 | 55905931 | -2.728% |  | 0 | 2016-03-31 | original |  |  | 2016
Uptown Service Buildings Pkg 17A | 2016-05-31 | 0 | 22686 | 14447493 | 15995410 | -1547917 | 55905931 | -2.769% |  | 0 | 2016-05-31 | original |  |  | 2016
Uptown Service Buildings Pkg 17A | 2016-10-31 | 0 | 83797 | 14447493 | 16079207 | -1631714 | 55905931 | -2.919% |  | 0 | 2016-10-31 | original |  |  | 2016
Uptown Service Buildings Pkg 17A | 2016-11-30 | 0 | 8092 | 14447493 | 16087299 | -1639806 | 55905931 | -2.933% |  | 0 | 2016-11-30 | original |  |  | 2016
Uptown Service Buildings Pkg 17A | 2017-03-31 | 0 | 261460 | 14447493 | 16348759 | -1901266 | 55905931 | -3.401% |  | 0 | 2017-03-31 | original |  |  | 2017
Uptown Service Buildings Pkg 17A | 2017-04-30 | 1978172 | 83797 | 16425665 | 16432556 | -6891 | 55905931 | -0.01233% |  | 0 | 2017-04-30 | original |  |  | 2017
1900
Point 90 New Cairo Mall | 2014-01-31 | 0 | 556808.3 | 0 | 556808.3 | -556808.3 | 145010925.68 | -0.384% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-02-28 | 0 | 1242119.83 | 0 | 1798928.13 | -1798928.13 | 145010925.68 | -1.241% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-03-31 | 337595.15 | 977662.47 | 337595.15 | 2776590.6 | -2438995.45 | 145010925.68 | -1.682% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-04-30 | 7575591.25 | 1272996.69 | 7913186.4 | 4049587.29 | 3863599.11 | 145010925.68 | 2.664% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-05-31 | 8757008 | 10215274.38 | 16670194.4 | 14264861.67 | 2405332.73 | 145010925.68 | 1.659% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-06-30 | 984119.05 | 2620346.63 | 17654313.45 | 16885208.3 | 769105.15 | 145010925.68 | 0.5304% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-07-31 | 0 | 1844072.2 | 17654313.45 | 18729280.5 | -1074967.05 | 145010925.68 | -0.7413% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-08-31 | 2126778.6 | 2656903.22 | 19781092.05 | 21386183.72 | -1605091.67 | 145010925.68 | -1.107% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-09-30 | 6643055.47 | 5390039.21 | 26424147.52 | 26776222.93 | -352075.41 | 145010925.68 | -0.2428% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-10-31 | 4902226.76 | 4858479.24 | 31326374.28 | 31634702.17 | -308327.89 | 145010925.68 | -0.2126% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-11-30 | 7278364.77 | 6854191.42 | 38604739.05 | 38488893.59 | 115845.46 | 145010925.68 | 0.07989% |  |  |  | original |  |  | 2014
Point 90 New Cairo Mall | 2014-12-31 | 15334084.92 | 16008211.2368 | 53938823.97 | 54497104.8268 | -558280.8568 | 145010925.68 | -0.385% |  | 49721431 | 2014-12-31 | original |  |  | 2014
Point 90 New Cairo Mall | 2015-01-31 | 416611 | 2043654 | 54355434.97 | 56540758.8268 | -2185323.8568 | 145010925.68 | -1.507% |  | 14571348 | 2015-01-31 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-02-28 | 2150000 | 6495524 | 56505434.97 | 63036282.8268 | -6530847.8568 | 145010925.68 | -4.504% |  | 13969943 | 2015-02-28 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-03-31 | 16677165 | 10539604 | 73182599.97 | 73575886.8268 | -393286.8568 | 145010925.68 | -0.2712% |  | 22855987 | 2015-03-31 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-04-30 | 15690320 | 10869155 | 88872919.97 | 84445041.8268 | 4427878.1432 | 145010925.68 | 3.053% |  | 0 | 2015-04-30 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-05-31 | 0 | 3421832 | 88872919.97 | 87866873.8268 | 1006046.1432 | 145010925.68 | 0.6938% |  | 0 | 2015-05-31 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-06-30 | 0 | 2177645 | 88872919.97 | 90044518.8268 | -1171598.8568 | 145010925.68 | -0.8079% |  | 14122394 | 2015-06-30 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-07-31 | 2456456 | 1681434 | 91329375.97 | 91725952.8268 | -396576.8568 | 145010925.68 | -0.2735% |  | 0 | 2015-07-31 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-08-31 | 495396 | 1621720 | 91824771.97 | 93347672.8268 | -1522900.8568 | 145010925.68 | -1.05% |  | 5634518 | 2015-08-31 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-09-30 | 2888335 | 1712941 | 94713106.97 | 95060613.8268 | -347506.8568 | 145010925.68 | -0.2396% |  | 0 | 2015-09-30 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-10-31 | 0 | 3075717 | 94713106.97 | 98136330.8268 | -3423223.8568 | 145010925.68 | -2.361% |  | 0 | 2015-10-31 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-11-30 | 5068703 | 5527644 | 99781809.97 | 103663974.8268 | -3882164.8568 | 145010925.68 | -2.677% |  | 0 | 2015-11-30 | original |  |  | 2015
Point 90 New Cairo Mall | 2015-12-31 | 3649856 | 769111 | 103431665.97 | 104433085.8268 | -1001419.8568 | 145010925.68 | -0.6906% |  | 0 | 2015-12-31 | original |  |  | 2015
Point 90 New Cairo Mall | 2016-01-31 | 2869899 | 640175 | 106301564.97 | 105073260.8268 | 1228304.1432 | 145010925.68 | 0.847% |  | 0 | 2016-01-31 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-02-29 | 190857 | 333983 | 106492421.97 | 105407243.8268 | 1085178.1432 | 145010925.68 | 0.7483% |  | 0 | 2016-02-29 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-03-31 | 0 | 283204 | 106492421.97 | 105690447.8268 | 801974.1432 | 145010925.68 | 0.553% |  | 0 | 2016-03-31 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-04-30 | 0 | 118066 | 106492421.97 | 105808513.8268 | 683908.1432 | 145010925.68 | 0.4716% |  | 0 | 2016-04-30 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-05-31 | 0 | 23805 | 106492421.97 | 105832318.8268 | 660103.1432 | 145010925.68 | 0.4552% |  | 0 | 2016-05-31 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-06-30 | 6858538 | 389365 | 113350959.97 | 106221683.8268 | 7129276.1432 | 145010925.68 | 4.916% |  | 0 | 2016-06-30 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-07-31 | 0 | 3646910 | 113350959.97 | 109868593.8268 | 3482366.1432 | 145010925.68 | 2.401% |  | 0 | 2016-07-31 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-08-31 | 0 | 21539 | 113350959.97 | 109890132.8268 | 3460827.1432 | 145010925.68 | 2.387% |  | 0 | 2016-08-31 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-09-30 | 0 | 2300 | 113350959.97 | 109892432.8268 | 3458527.1432 | 145010925.68 | 2.385% |  | 0 | 2016-09-30 | original |  |  | 2016
Point 90 New Cairo Mall | 2016-11-30 | 9745815 | 142189 | 123096774.97 | 110034621.8268 | 13062153.1432 | 145010925.68 | 9.008% |  | 0 | 2016-11-30 | original |  |  | 2016
Point 90 New Cairo Mall | 2017-01-31 | 0 | 90327 | 123096774.97 | 110124948.8268 | 12971826.1432 | 145010925.68 | 8.945% |  | 0 | 2017-01-31 | original |  |  | 2017
Point 90 New Cairo Mall | 2017-03-31 | 939483 | 2188641 | 124036257.97 | 112313589.8268 | 11722668.1432 | 145010925.68 | 8.084% |  | 0 | 2017-03-31 | original |  |  | 2017
Point 90 New Cairo Mall | 2017-04-30 | 2000000 | 805141 | 126036257.97 | 113118730.8268 | 12917527.1432 | 145010925.68 | 8.908% |  | 0 | 2017-04-30 | original |  |  | 2017
Point 90 New Cairo Mall | 2017-05-31 | 3053641 | 1040079 | 129089898.97 | 114158809.8268 | 14931089.1432 | 145010925.68 | 10.3% |  | 0 | 2017-05-31 | original |  |  | 2017
Point 90 New Cairo Mall | 2017-06-30 | 0 | 54612 | 129089898.97 | 114213421.8268 | 14876477.1432 | 145010925.68 | 10.26% |  | 0 | 2017-06-30 | original |  |  | 2017
Point 90 New Cairo Mall | 2017-08-31 | 0 | 75378 | 129089898.97 | 114288799.8268 | 14801099.1432 | 145010925.68 | 10.21% |  | 0 | 2017-08-31 | original |  |  | 2017
Point 90 New Cairo Mall | 2017-09-30 | 0 | 194363 | 129089898.97 | 114483162.8268 | 14606736.1432 | 145010925.68 | 10.07% |  | 0 | 2017-09-30 | original |  |  | 2017
1900
Sodic MV Cables | 2013-01-31 | 524591.63 |  | 524591.63 | 0 | 524591.63 | 19589518 | 2.678% |  | 271800 | 2013-01-31 | original |  |  | 2013
Sodic MV Cables | 2013-02-28 | 556442.63 |  | 1081034.26 | 0 | 1081034.26 | 19589518 | 5.518% |  | 820972.8 | 2013-02-28 | original |  |  | 2013
Sodic MV Cables | 2013-03-31 | -203590.49 |  | 877443.77 | 0 | 877443.77 | 19589518 | 4.479% |  | -188160.6 | 2013-03-31 | original |  |  | 2013
Sodic MV Cables | 2013-04-30 | 783737.74 |  | 1661181.51 | 0 | 1661181.51 | 19589518 | 8.48% |  | 1279513.2 | 2013-04-30 | original |  |  | 2013
Sodic MV Cables | 2013-05-31 |  |  | 1661181.51 | 0 | 1661181.51 | 19589518 | 8.48% |  |  | 2013-05-31 | original |  |  | 2013
Sodic MV Cables | 2013-06-30 | 1144175.2 |  | 2805356.71 | 0 | 2805356.71 | 19589518 | 14.32% |  | 916729.7 | 2013-06-30 | original |  |  | 2013
Sodic MV Cables | 2013-07-31 |  |  | 2805356.71 | 0 | 2805356.71 | 19589518 | 14.32% |  |  | 2013-07-31 | original |  |  | 2013
Sodic MV Cables | 2013-08-31 | 2297660.32 |  | 5103017.03 | 0 | 5103017.03 | 19589518 | 26.05% |  | 73787.7 | 2013-08-31 | original |  |  | 2013
Sodic MV Cables | 2013-09-30 |  |  | 5103017.03 | 0 | 5103017.03 | 19589518 | 26.05% |  |  | 2013-09-30 | original |  |  | 2013
Sodic MV Cables | 2013-10-31 | 1974465.6 |  | 7077482.63 | 0 | 7077482.63 | 19589518 | 36.13% |  | 312485.4 | 2013-10-31 | original |  |  | 2013
Sodic MV Cables | 2013-11-30 | 1916406 |  | 8993888.63 | 0 | 8993888.63 | 19589518 | 45.91% |  | 6433474.9 | 2013-11-30 | original |  |  | 2013
Sodic MV Cables | 2013-12-31 | 704764.6 |  | 9698653.23 | 0 | 9698653.23 | 19589518 | 49.51% |  | 1859255.5 | 2013-12-31 | original |  |  | 2013
Sodic MV Cables | 2014-01-31 | 677974.81 | 254792.08 | 10376628.04 | 254792.08 | 10121835.96 | 19589518 | 51.67% |  | 513148.38 | 2014-01-31 | original |  |  | 2014
Sodic MV Cables | 2014-02-28 | 1217342.68 | 921610.95 | 11593970.72 | 1176403.03 | 10417567.69 | 19589518 | 53.18% |  | 1866216.72 | 2014-02-28 | original |  |  | 2014
Sodic MV Cables | 2014-03-31 | 0 | 1744837.91 | 11593970.72 | 2921240.94 | 8672729.78 | 19589518 | 44.27% |  |  | 2014-03-31 | original |  |  | 2014
Sodic MV Cables | 2014-04-30 | 1229370.9 | 85404.71 | 12823341.62 | 3006645.65 | 9816695.97 | 19589518 | 50.11% |  | 2161353.34 | 2014-04-30 | original |  |  | 2014
Sodic MV Cables | 2014-05-31 | 821536.2 | 132912.95 | 13644877.82 | 3139558.6 | 10505319.22 | 19589518 | 53.63% |  |  | 2014-05-31 | original |  |  | 2014
Sodic MV Cables | 2014-06-30 | 0 | 112885.61 | 13644877.82 | 3252444.21 | 10392433.61 | 19589518 | 53.05% |  | 1277568.94 | 2014-06-30 | original |  |  | 2014
Sodic MV Cables | 2014-07-31 | 0 | 90177.86 | 13644877.82 | 3342622.07 | 10302255.75 | 19589518 | 52.59% |  |  | 2014-07-31 | original |  |  | 2014
Sodic MV Cables | 2014-08-31 | 0 | 19647.49 | 13644877.82 | 3362269.56 | 10282608.26 | 19589518 | 52.49% |  |  | 2014-08-31 | original |  |  | 2014
Sodic MV Cables | 2014-09-30 | 0 | 45012.42 | 13644877.82 | 3407281.98 | 10237595.84 | 19589518 | 52.26% |  |  | 2014-09-30 | original |  |  | 2014
Sodic MV Cables | 2014-10-31 | 661055.73 | 619979.78 | 14305933.55 | 4027261.76 | 10278671.79 | 19589518 | 52.47% |  |  | 2014-10-31 | original |  |  | 2014
Sodic MV Cables | 2014-11-30 | 0 | 45544 | 14305933.55 | 4072805.76 | 10233127.79 | 19589518 | 52.24% |  | 297920.4 | 2014-11-30 | original |  |  | 2014
Sodic MV Cables | 2014-12-31 |  | 127827.79 | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  | 2014-12-31 | original |  |  | 2014
Sodic MV Cables | 2015-01-31 |  |  | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  | 2015-01-31 | original |  |  | 2015
Sodic MV Cables | 2015-02-28 |  |  | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  | 911195.14 | 2015-02-28 | original |  |  | 2015
Sodic MV Cables | 2015-03-31 |  |  | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  | 2015-03-31 | original |  |  | 2015
Sodic MV Cables | 2015-04-30 |  |  | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  | 2015-04-30 | original |  |  | 2015
Sodic MV Cables | 2015-05-31 |  |  | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  | 1020185.7 | 2015-05-31 | original |  |  | 2015
1900
Sodic West Town Hub | 2012-11-30 | 1015025.63 |  | 1015025.63 | 0 | 1015025.63 | 54160920.41 | 1.874% |  | 1240648.91 | 2012-11-30 | original |  |  | 2012
Sodic West Town Hub | 2012-12-30 | 2605028.33 |  | 3620053.96 | 0 | 3620053.96 | 54160920.41 | 6.684% |  | 1962475.27 | 2012-12-30 | original |  |  | 2012
Sodic West Town Hub | 2013-01-30 | 3380021.91 |  | 7000075.87 | 0 | 7000075.87 | 54160920.41 | 12.92% |  | 5031467.5 | 2013-01-30 | original |  |  | 2013
Sodic West Town Hub | 2013-02-28 |  |  | 7000075.87 | 0 | 7000075.87 | 54160920.41 | 12.92% |  | 2575471.19 | 2013-02-28 | original |  |  | 2013
Sodic West Town Hub | 2013-03-30 | 2655964.84 |  | 9656040.71 | 0 | 9656040.71 | 54160920.41 | 17.83% |  | 0 | 2013-03-30 | original |  |  | 2013
Sodic West Town Hub | 2013-04-30 | 1932233.42 |  | 11588274.13 | 0 | 11588274.13 | 54160920.41 | 21.4% |  | 2766264.9 | 2013-04-30 | original |  |  | 2013
Sodic West Town Hub | 2013-05-30 |  |  | 11588274.13 | 0 | 11588274.13 | 54160920.41 | 21.4% |  |  | 2013-05-30 | original |  |  | 2013
Sodic West Town Hub | 2013-06-30 | 2153527.94 |  | 13741802.07 | 0 | 13741802.07 | 54160920.41 | 25.37% |  | 7127244.46 | 2013-06-30 | original |  |  | 2013
Sodic West Town Hub | 2013-07-30 | 6382668.26 |  | 20124470.33 | 0 | 20124470.33 | 54160920.41 | 37.16% |  | 3666461.88 | 2013-07-30 | original |  |  | 2013
Sodic West Town Hub | 2013-08-30 | 4256983.04 |  | 24381453.37 | 0 | 24381453.37 | 54160920.41 | 45.02% |  | 5511181.28 | 2013-08-30 | original |  |  | 2013
Sodic West Town Hub | 2013-09-30 |  |  | 24381453.37 | 0 | 24381453.37 | 54160920.41 | 45.02% |  |  | 2013-09-30 | original |  |  | 2013
Sodic West Town Hub | 2013-10-30 |  |  | 24381453.37 | 0 | 24381453.37 | 54160920.41 | 45.02% |  |  | 2013-10-30 | original |  |  | 2013
Sodic West Town Hub | 2013-11-30 | 4737107.07 |  | 29118560.44 | 0 | 29118560.44 | 54160920.41 | 53.76% |  | 7898858.92 | 2013-11-30 | original |  |  | 2013
Sodic West Town Hub | 2013-12-30 |  |  | 29118560.44 | 0 | 29118560.44 | 54160920.41 | 53.76% |  | 4312330.02 | 2013-12-30 | original |  |  | 2013
Sodic West Town Hub | 2014-01-30 | 3961192.53 | 3471449.93 | 33079752.97 | 3471449.93 | 29608303.04 | 54160920.41 | 54.67% |  | 2723844.33 | 2014-01-30 | original |  |  | 2014
Sodic West Town Hub | 2014-02-28 | 2217702.79 | 1613380.26 | 35297455.76 | 5084830.19 | 30212625.57 | 54160920.41 | 55.78% |  |  | 2014-02-28 | original |  |  | 2014
Sodic West Town Hub | 2014-03-30 | 2351237.09 | 1530817.31 | 37648692.85 | 6615647.5 | 31033045.35 | 54160920.41 | 57.3% |  | 2599945.18 | 2014-03-30 | original |  |  | 2014
Sodic West Town Hub | 2014-04-30 | 0 | 1180951.95 | 37648692.85 | 7796599.45 | 29852093.4 | 54160920.41 | 55.12% |  |  | 2014-04-30 | original |  |  | 2014
Sodic West Town Hub | 2014-05-30 | 1579148.73 | 1905780.03 | 39227841.58 | 9702379.48 | 29525462.1 | 54160920.41 | 54.51% |  | 1791133.74 | 2014-05-30 | original |  |  | 2014
Sodic West Town Hub | 2014-06-30 | 1198642.12 | 749789.15 | 40426483.7 | 10452168.63 | 29974315.07 | 54160920.41 | 55.34% |  |  | 2014-06-30 | original |  |  | 2014
Sodic West Town Hub | 2014-07-30 | 0 | 450847.33 | 40426483.7 | 10903015.96 | 29523467.74 | 54160920.41 | 54.51% |  |  | 2014-07-30 | original |  |  | 2014
Sodic West Town Hub | 2014-08-30 | 2424916.36 | 205701.78 | 42851400.06 | 11108717.74 | 31742682.32 | 54160920.41 | 58.61% |  | 3233648.08 | 2014-08-30 | original |  |  | 2014
Sodic West Town Hub | 2014-09-30 | 1213164 | 536987.5 | 44064564.06 | 11645705.24 | 32418858.82 | 54160920.41 | 59.86% |  |  | 2014-09-30 | original |  |  | 2014
Sodic West Town Hub | 2014-10-30 | 132371.95 | 157832.99 | 44196936.01 | 11803538.23 | 32393397.78 | 54160920.41 | 59.81% |  |  | 2014-10-30 | original |  |  | 2014
Sodic West Town Hub | 2014-11-30 | 0 | 127813.68 | 44196936.01 | 11931351.91 | 32265584.1 | 54160920.41 | 59.57% |  |  | 2014-11-30 | original |  |  | 2014
Sodic West Town Hub | 2014-12-30 | 1992120.77 | 370082.84 | 46189056.78 | 12301434.75 | 33887622.03 | 54160920.41 | 62.57% |  | 1719945.09 | 2014-12-30 | original |  |  | 2014
Sodic West Town Hub | 2015-01-30 | 17070496.34 | 12363810.07 | 63259553.12 | 24665244.82 | 38594308.3 | 54160920.41 | 71.26% |  |  | 2015-01-30 | original |  |  | 2015
Sodic West Town Hub | 2015-02-28 | 0 | 475151.71 | 63259553.12 | 25140396.53 | 38119156.59 | 54160920.41 | 70.38% |  |  | 2015-02-28 | original |  |  | 2015
Sodic West Town Hub | 2015-03-30 | 593631 | 256000 | 63853184.12 | 25396396.53 | 38456787.59 | 54160920.41 | 71% |  |  | 2015-03-30 | original |  |  | 2015
Sodic West Town Hub | 2015-04-30 | 0 | 143214.74 | 63853184.12 | 25539611.27 | 38313572.85 | 54160920.41 | 70.74% |  |  | 2015-04-30 | original |  |  | 2015
Sodic West Town Hub | 2015-05-30 | 1534360.84 | 82410.61 | 65387544.96 | 25622021.88 | 39765523.08 | 54160920.41 | 73.42% |  |  | 2015-05-30 | original |  |  | 2015
Sodic West Town Hub | 2015-06-30 |  | 302232.44 | 65387544.96 | 25924254.32 | 39463290.64 | 54160920.41 | 72.86% |  |  | 2015-06-30 | original |  |  | 2015
Sodic West Town Hub | 2015-07-30 |  |  | 65387544.96 | 25924254.32 | 39463290.64 | 54160920.41 | 72.86% |  |  | 2015-07-30 | original |  |  | 2015
Sodic West Town Hub | 2015-08-30 |  | 150000 | 65387544.96 | 26074254.32 | 39313290.64 | 54160920.41 | 72.59% |  |  | 2015-08-30 | original |  |  | 2015
Sodic West Town Hub | 2015-09-30 |  | 254711.37 | 65387544.96 | 26328965.69 | 39058579.27 | 54160920.41 | 72.12% |  |  | 2015-09-30 | original |  |  | 2015
Sodic West Town Hub | 2015-10-30 |  | 150000 | 65387544.96 | 26478965.69 | 38908579.27 | 54160920.41 | 71.84% |  |  | 2015-10-30 | original |  |  | 2015
1900
Limak TB2 Cairo Airport Terminal | 2013-04-30 | 68910040.25 |  | 68910040.25 | 0 | 68910040.25 | 119626844 | 57.6% |  | 2033442.93 | 2013-04-30 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-05-31 | 67546820.11 |  | 136456860.36 | 0 | 136456860.36 | 119626844 | 114.1% |  | 2751449.6 | 2013-05-31 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-06-30 | 66546820.11 |  | 203003680.47 | 0 | 203003680.47 | 119626844 | 169.7% |  | 1480306.8 | 2013-06-30 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-07-31 | 64426820.11 |  | 267430500.58 | 0 | 267430500.58 | 119626844 | 223.6% |  | 2901568.43 | 2013-07-31 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-08-31 | 62411075.23 |  | 329841575.81 | 0 | 329841575.81 | 119626844 | 275.7% |  | 220369.64 | 2013-08-31 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-09-30 | 62236366.79 |  | 392077942.6 | 0 | 392077942.6 | 119626844 | 327.8% |  | 1946705.41 | 2013-09-30 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-10-31 | 60903595.22 |  | 452981537.82 | 0 | 452981537.82 | 119626844 | 378.7% |  | 4456997.32 | 2013-10-31 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-11-30 | 58232221.87 |  | 511213759.69 | 0 | 511213759.69 | 119626844 | 427.3% |  | 394928.75 | 2013-11-30 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2013-12-31 | 57543239.2 |  | 568756998.89 | 0 | 568756998.89 | 119626844 | 475.4% |  | 0 | 2013-12-31 | original |  |  | 2013
Limak TB2 Cairo Airport Terminal | 2014-01-31 | 2556309.78 | 2917911.59 | 571313308.67 | 2917911.59 | 568395397.08 | 119626844 | 475.1% |  | 8525595.66 | 2014-01-31 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-02-28 | 4500000 | 4018119.69 | 575813308.67 | 6936031.28 | 568877277.39 | 119626844 | 475.5% |  | 4226487.56 | 2014-02-28 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-03-31 | 2000000 | 5146141.37 | 577813308.67 | 12082172.65 | 565731136.02 | 119626844 | 472.9% |  | 5331045.01 | 2014-03-31 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-04-30 | 6470455.36 | 4675969.06 | 584283764.03 | 16758141.71 | 567525622.32 | 119626844 | 474.4% |  | 3236718.47 | 2014-04-30 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-05-31 | 4000000 | 5980577.46 | 588283764.03 | 22738719.17 | 565545044.86 | 119626844 | 472.8% |  | 7212360.38 | 2014-05-31 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-06-30 | 1976271.33 | 5146368.54 | 590260035.36 | 27885087.71 | 562374947.65 | 119626844 | 470.1% |  | 4271721.07 | 2014-06-30 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-07-31 | 3500000 | 1962774.07 | 593760035.36 | 29847861.78 | 563912173.58 | 119626844 | 471.4% |  | 4787479.51 | 2014-07-31 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-08-31 | 5167892.93 | 2695896.58 | 598927928.29 | 32543758.36 | 566384169.93 | 119626844 | 473.5% |  | 2884992.09 | 2014-08-31 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-09-30 | 4500000 | 4810854.92 | 603427928.29 | 37354613.28 | 566073315.01 | 119626844 | 473.2% |  | 5043420.04 | 2014-09-30 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-10-31 | 3074518 | 4103108.44 | 606502446.29 | 41457721.72 | 565044724.57 | 119626844 | 472.3% |  | 4594880.59 | 2014-10-31 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-11-30 | 2824636.13 | 2313160.12 | 609327082.42 | 43770881.84 | 565556200.58 | 119626844 | 472.8% |  | 2033454.15 | 2014-11-30 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2014-12-31 | 2380352.34 | 4679596.48 | 611707434.76 | 48450478.32 | 563256956.44 | 119626844 | 470.8% |  | 5133336.96 | 2014-12-31 | original |  |  | 2014
Limak TB2 Cairo Airport Terminal | 2015-01-31 | 13225504.79 |  | 624932939.55 | 48450478.32 | 576482461.23 | 119626844 | 481.9% |  | 6437499.14 | 2015-01-31 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-02-28 | 7853167.56 |  | 632786107.11 | 48450478.32 | 584335628.79 | 119626844 | 488.5% |  | 3320336.19 | 2015-02-28 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-03-31 | 5724776.4 |  | 638510883.51 | 48450478.32 | 590060405.19 | 119626844 | 493.3% |  | 0 | 2015-03-31 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-04-30 | 5724776.4 |  | 644235659.91 | 48450478.32 | 595785181.59 | 119626844 | 498% |  | 5101527.28 | 2015-04-30 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-05-31 | 1791760.92 |  | 646027420.83 | 48450478.32 | 597576942.51 | 119626844 | 499.5% |  | 2196526.14 | 2015-05-31 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-06-30 | 149600.52 |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2015-06-30 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-07-31 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2015-07-31 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-08-31 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2015-08-31 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-09-30 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2015-09-30 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-10-31 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2015-10-31 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-11-30 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2015-11-30 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2015-12-31 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2015-12-31 | original |  |  | 2015
Limak TB2 Cairo Airport Terminal | 2016-01-31 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2016-01-31 | original |  |  | 2016
Limak TB2 Cairo Airport Terminal | 2016-02-29 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2016-02-29 | original |  |  | 2016
Limak TB2 Cairo Airport Terminal | 2016-03-31 |  |  | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  | 0 | 2016-03-31 | original |  |  | 2016
1900
Twin Towers | 2010-12-30 | 1782375.88 |  | 1782375.88 | 0 | 1782375.88 | 64000000.23 | 2.785% |  | 2181410.5 | 2010-12-30 | original |  |  | 2010
Twin Towers | 2011-01-31 |  |  | 1782375.88 | 0 | 1782375.88 | 64000000.23 | 2.785% |  |  | 2011-01-31 | original |  |  | 2011
Twin Towers | 2011-02-28 | 1042075.56 |  | 2824451.44 | 0 | 2824451.44 | 64000000.23 | 4.413% |  | 997763.58 | 2011-02-28 | original |  |  | 2011
Twin Towers | 2011-03-31 | 1260843.13 |  | 4085294.57 | 0 | 4085294.57 | 64000000.23 | 6.383% |  | 1609045.61 | 2011-03-31 | original |  |  | 2011
Twin Towers | 2011-04-30 | 1414868.61 |  | 5500163.18 | 0 | 5500163.18 | 64000000.23 | 8.594% |  | 1574402.88 | 2011-04-30 | original |  |  | 2011
Twin Towers | 2011-05-31 | 1292579.86 |  | 6792743.04 | 0 | 6792743.04 | 64000000.23 | 10.61% |  | 1087938.99 | 2011-05-31 | original |  |  | 2011
Twin Towers | 2011-06-30 | 1177608.41 |  | 7970351.45 | 0 | 7970351.45 | 64000000.23 | 12.45% |  | 1221001.33 | 2011-06-30 | original |  |  | 2011
Twin Towers | 2011-07-31 |  |  | 7970351.45 | 0 | 7970351.45 | 64000000.23 | 12.45% |  |  | 2011-07-31 | original |  |  | 2011
Twin Towers | 2011-08-31 | 1491226.87 |  | 9461578.32 | 0 | 9461578.32 | 64000000.23 | 14.78% |  | 1394092.61 | 2011-08-31 | original |  |  | 2011
Twin Towers | 2011-09-30 | 2018417.57 |  | 11479995.89 | 0 | 11479995.89 | 64000000.23 | 17.94% |  | 2216138.55 | 2011-09-30 | original |  |  | 2011
Twin Towers | 2011-10-31 | 1048114.83 |  | 12528110.72 | 0 | 12528110.72 | 64000000.23 | 19.58% |  | 1189062.01 | 2011-10-31 | original |  |  | 2011
Twin Towers | 2011-11-30 | 1135288.54 |  | 13663399.26 | 0 | 13663399.26 | 64000000.23 | 21.35% |  | 1332534.56 | 2011-11-30 | original |  |  | 2011
Twin Towers | 2011-12-31 | 1144950.05 |  | 14808349.31 | 0 | 14808349.31 | 64000000.23 | 23.14% |  | 1054803.11 | 2011-12-31 | original |  |  | 2011
Twin Towers | 2012-01-31 | 1635725.59 |  | 16444074.9 | 0 | 16444074.9 | 64000000.23 | 25.69% |  | 1709860.82 | 2012-01-31 | original |  |  | 2012
Twin Towers | 2012-02-29 | 1405373.93 |  | 17849448.83 | 0 | 17849448.83 | 64000000.23 | 27.89% |  | 1541224.4 | 2012-02-29 | original |  |  | 2012
Twin Towers | 2012-03-31 | 1346977.29 |  | 19196426.12 | 0 | 19196426.12 | 64000000.23 | 29.99% |  | 1406283.31 | 2012-03-31 | original |  |  | 2012
Twin Towers | 2012-04-30 | 1533462.2 |  | 20729888.32 | 0 | 20729888.32 | 64000000.23 | 32.39% |  | 1773702.84 | 2012-04-30 | original |  |  | 2012
Twin Towers | 2012-05-31 | 1690948.85 |  | 22420837.17 | 0 | 22420837.17 | 64000000.23 | 35.03% |  | 1754138.98 | 2012-05-31 | original |  |  | 2012
Twin Towers | 2012-06-30 | 1524559.45 |  | 23945396.62 | 0 | 23945396.62 | 64000000.23 | 37.41% |  | 1430024.98 | 2012-06-30 | original |  |  | 2012
Twin Towers | 2012-07-31 | 1066394.39 |  | 25011791.01 | 0 | 25011791.01 | 64000000.23 | 39.08% |  | 1451663.67 | 2012-07-31 | original |  |  | 2012
Twin Towers | 2012-08-31 | 985272.88 |  | 25997063.89 | 0 | 25997063.89 | 64000000.23 | 40.62% |  | 911090.51 | 2012-08-31 | original |  |  | 2012
Twin Towers | 2012-09-30 | 1395488.71 |  | 27392552.6 | 0 | 27392552.6 | 64000000.23 | 42.8% |  | 1472885.04 | 2012-09-30 | original |  |  | 2012
Twin Towers | 2012-10-31 | 940238.32 |  | 28332790.92 | 0 | 28332790.92 | 64000000.23 | 44.27% |  | 1270647.38 | 2012-10-31 | original |  |  | 2012
Twin Towers | 2012-11-30 | 336933.59 |  | 28669724.51 | 0 | 28669724.51 | 64000000.23 | 44.8% |  | 74472.44 | 2012-11-30 | original |  |  | 2012
Twin Towers | 2012-12-31 |  |  | 28669724.51 | 0 | 28669724.51 | 64000000.23 | 44.8% |  |  | 2012-12-31 | original |  |  | 2012
Twin Towers | 2013-01-31 |  |  | 28669724.51 | 0 | 28669724.51 | 64000000.23 | 44.8% |  | 358871.52 | 2013-01-31 | original |  |  | 2013
Twin Towers | 2013-02-28 | 331467.02 |  | 29001191.53 | 0 | 29001191.53 | 64000000.23 | 45.31% |  | -124885.99 | 2013-02-28 | original |  |  | 2013
Twin Towers | 2013-03-31 | 399287.55 |  | 29400479.08 | 0 | 29400479.08 | 64000000.23 | 45.94% |  | 830206.93 | 2013-03-31 | original |  |  | 2013
Twin Towers | 2013-04-30 | 1206261.26 |  | 30606740.34 | 0 | 30606740.34 | 64000000.23 | 47.82% |  | 1647281.36 | 2013-04-30 | original |  |  | 2013
Twin Towers | 2013-05-31 | 1678026.98 |  | 32284767.32 | 0 | 32284767.32 | 64000000.23 | 50.44% |  | 1581412.29 | 2013-05-31 | original |  |  | 2013
Twin Towers | 2013-06-30 | 1264998.07 |  | 33549765.39 | 0 | 33549765.39 | 64000000.23 | 52.42% |  | 1376367.18 | 2013-06-30 | original |  |  | 2013
Twin Towers | 2013-07-31 | 110796.29 |  | 33660561.68 | 0 | 33660561.68 | 64000000.23 | 52.59% |  | 297205.23 | 2013-07-31 | original |  |  | 2013
Twin Towers | 2013-08-31 | 1015605.01 |  | 34676166.69 | 0 | 34676166.69 | 64000000.23 | 54.18% |  | 1465782.56 | 2013-08-31 | original |  |  | 2013
Twin Towers | 2013-09-30 | 2227132.83 |  | 36903299.52 | 0 | 36903299.52 | 64000000.23 | 57.66% |  | 1725899.76 | 2013-09-30 | original |  |  | 2013
Twin Towers | 2013-10-31 | 0 |  | 36903299.52 | 0 | 36903299.52 | 64000000.23 | 57.66% |  | 0 | 2013-10-31 | original |  |  | 2013
Twin Towers | 2013-11-30 | 0 |  | 36903299.52 | 0 | 36903299.52 | 64000000.23 | 57.66% |  | 0 | 2013-11-30 | original |  |  | 2013
Twin Towers | 2013-12-31 | 892543.25 |  | 37795842.77 | 0 | 37795842.77 | 64000000.23 | 59.06% |  | 1505875.3 | 2013-12-31 | original |  |  | 2013
Twin Towers | 2014-01-31 | 588784.71 | 847987.23 | 38384627.48 | 847987.23 | 37536640.25 | 64000000.23 | 58.65% |  | 3577066.93 | 2014-01-31 | original |  |  | 2014
Twin Towers | 2014-02-28 | 1708357.87 | 861719.8 | 40092985.35 | 1709707.03 | 38383278.32 | 64000000.23 | 59.97% |  | 0 | 2014-02-28 | original |  |  | 2014
Twin Towers | 2014-03-31 | 1823483.39 | 1173422.38 | 41916468.74 | 2883129.41 | 39033339.33 | 64000000.23 | 60.99% |  | 540084.63 | 2014-03-31 | original |  |  | 2014
Twin Towers | 2014-04-30 | 750000 | 2031280.22 | 42666468.74 | 4914409.63 | 37752059.11 | 64000000.23 | 58.99% |  | 1499549.36 | 2014-04-30 | original |  |  | 2014
Twin Towers | 2014-05-31 | 1187298.19 | 1619384.9 | 43853766.93 | 6533794.53 | 37319972.4 | 64000000.23 | 58.31% |  | 619710.55 | 2014-05-31 | original |  |  | 2014
Twin Towers | 2014-06-30 | 1571450.51 | 1349007.48 | 45425217.44 | 7882802.01 | 37542415.43 | 64000000.23 | 58.66% |  | 1702812.65 | 2014-06-30 | original |  |  | 2014
Twin Towers | 2014-07-31 | 421925.37 | 1027930.74 | 45847142.81 | 8910732.75 | 36936410.06 | 64000000.23 | 57.71% |  | 845936.37 | 2014-07-31 | original |  |  | 2014
Twin Towers | 2014-08-31 | 469981.59 | 569155.04 | 46317124.4 | 9479887.79 | 36837236.61 | 64000000.23 | 57.56% |  | 67780.37 | 2014-08-31 | original |  |  | 2014
Twin Towers | 2014-09-30 | 668376.51 | 1299581.65 | 46985500.91 | 10779469.44 | 36206031.47 | 64000000.23 | 56.57% |  | 430929.23 | 2014-09-30 | original |  |  | 2014
Twin Towers | 2014-10-31 | 1890854.63 | 1287934.12 | 48876355.54 | 12067403.56 | 36808951.98 | 64000000.23 | 57.51% |  | 3560753.25 | 2014-10-31 | original |  |  | 2014
Twin Towers | 2014-11-30 | 1142714.04 | 837986.7 | 50019069.58 | 12905390.26 | 37113679.32 | 64000000.23 | 57.99% |  | 1424768.8 | 2014-11-30 | original |  |  | 2014
Twin Towers | 2014-12-31 | 809103.45 | 1342122.18 | 50828173.03 | 14247512.44 | 36580660.59 | 64000000.23 | 57.16% |  | 2292391.65 | 2014-12-31 | original |  |  | 2014
Twin Towers | 2015-01-31 | 1669641.52 |  | 52497814.55 | 14247512.44 | 38250302.11 | 64000000.23 | 59.77% |  | 0 | 2015-01-31 | original |  |  | 2015
Twin Towers | 2015-02-28 | 0 |  | 52497814.55 | 14247512.44 | 38250302.11 | 64000000.23 | 59.77% |  | 1072718.84 | 2015-02-28 | original |  |  | 2015
Twin Towers | 2015-03-31 | 588090.74 |  | 53085905.29 | 14247512.44 | 38838392.85 | 64000000.23 | 60.68% |  | 594998.64 | 2015-03-31 | original |  |  | 2015
Twin Towers | 2015-04-30 | 297794.48 |  | 53383699.77 | 14247512.44 | 39136187.33 | 64000000.23 | 61.15% |  | 0 | 2015-04-30 | original |  |  | 2015
Twin Towers | 2015-05-31 | 0 |  | 53383699.77 | 14247512.44 | 39136187.33 | 64000000.23 | 61.15% |  | 0 | 2015-05-31 | original |  |  | 2015
1900
Uptown Soil Stabilization Pkg 32 | 2012-11-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 192752 | 2012-11-30 | original |  |  | 2012
Uptown Soil Stabilization Pkg 32 | 2012-12-31 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 643839 | 2012-12-31 | original |  |  | 2012
Uptown Soil Stabilization Pkg 32 | 2013-01-31 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 542866 | 2013-01-31 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2013-02-28 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 350895 | 2013-02-28 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2013-03-31 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 561524 | 2013-03-31 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2013-04-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 823276 | 2013-04-30 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2013-06-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 582356 | 2013-06-30 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2013-07-31 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 212322 | 2013-07-31 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2013-09-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 238906 | 2013-09-30 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2013-11-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  | 439596 | 2013-11-30 | original |  |  | 2013
Uptown Soil Stabilization Pkg 32 | 2014-01-31 | 0 | 167558.7 | 0 | 167558.7 | -167558.7 | 17421145.8 | -0.9618% |  | 0 | 2014-01-31 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-02-28 | 0 | 243644.89 | 0 | 411203.59 | -411203.59 | 17421145.8 | -2.36% |  | 0 | 2014-02-28 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-03-31 | 327560.64 | 77210.41 | 327560.64 | 488414 | -160853.36 | 17421145.8 | -0.9233% |  | 0 | 2014-03-31 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-04-30 | 0 | 92784.43 | 327560.64 | 581198.43 | -253637.79 | 17421145.8 | -1.456% |  | 0 | 2014-04-30 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-05-31 | 0 | 87186.71 | 327560.64 | 668385.14 | -340824.5 | 17421145.8 | -1.956% |  | 0 | 2014-05-31 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-06-30 | 0 | 79780.06 | 327560.64 | 748165.2 | -420604.56 | 17421145.8 | -2.414% |  | 0 | 2014-06-30 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-07-31 | 0 | 189033.61 | 327560.64 | 937198.81 | -609638.17 | 17421145.8 | -3.499% |  | 1010899 | 2014-07-31 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-08-31 | 0 | 288827.77 | 327560.64 | 1226026.58 | -898465.94 | 17421145.8 | -5.157% |  | 0 | 2014-08-31 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-09-30 | 4486779.13 | 258753.98 | 4814339.77 | 1484780.56 | 3329559.21 | 17421145.8 | 19.11% |  | 614584 | 2014-09-30 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-10-31 | 0 | 487318.28 | 4814339.77 | 1972098.84 | 2842240.93 | 17421145.8 | 16.31% |  | 636775 | 2014-10-31 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-11-30 | 0 | 278633.56 | 4814339.77 | 2250732.4 | 2563607.37 | 17421145.8 | 14.72% |  | 583973 | 2014-11-30 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2014-12-31 | 482367.61 | 1106281.04 | 5296707.38 | 3357013.44 | 1939693.94 | 17421145.8 | 11.13% |  | 369952 | 2014-12-31 | original |  |  | 2014
Uptown Soil Stabilization Pkg 32 | 2015-01-31 | 230752 | 552612 | 5527459.38 | 3909625.44 | 1617833.94 | 17421145.8 | 9.287% |  | 715588 | 2015-01-31 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-02-28 | 146183 | 432488 | 5673642.38 | 4342113.44 | 1331528.94 | 17421145.8 | 7.643% |  | 976455 | 2015-02-28 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-03-31 | 562527 | 324983 | 6236169.38 | 4667096.44 | 1569072.94 | 17421145.8 | 9.007% |  | 0 | 2015-03-31 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-04-30 | 385837 | 649494 | 6622006.38 | 5316590.44 | 1305415.94 | 17421145.8 | 7.493% |  | 1184256 | 2015-04-30 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-05-31 | 0 | 1066058 | 6622006.38 | 6382648.44 | 239357.94 | 17421145.8 | 1.374% |  | 542399 | 2015-05-31 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-06-30 | 682272 | 598183 | 7304278.38 | 6980831.44 | 323446.94 | 17421145.8 | 1.857% |  | 1266465 | 2015-06-30 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-07-31 | 580510 | 790977 | 7884788.38 | 7771808.44 | 112979.94 | 17421145.8 | 0.6485% |  | 1174518 | 2015-07-31 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-08-31 | 0 | 605922 | 7884788.38 | 8377730.44 | -492942.06 | 17421145.8 | -2.83% |  | 0 | 2015-08-31 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-09-30 | 726448 | 955858 | 8611236.38 | 9333588.44 | -722352.06 | 17421145.8 | -4.146% |  | 526005 | 2015-09-30 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-10-31 | 0 | 321024 | 8611236.38 | 9654612.44 | -1043376.06 | 17421145.8 | -5.989% |  | 589862 | 2015-10-31 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-11-30 | 0 | 240630 | 8611236.38 | 9895242.44 | -1284006.06 | 17421145.8 | -7.37% |  | 197670 | 2015-11-30 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2015-12-31 | 899642 | 254894 | 9510878.38 | 10150136.44 | -639258.06 | 17421145.8 | -3.669% |  | 261673 | 2015-12-31 | original |  |  | 2015
Uptown Soil Stabilization Pkg 32 | 2016-01-31 | 0 | 181452 | 9510878.38 | 10331588.44 | -820710.06 | 17421145.8 | -4.711% |  | 0 | 2016-01-31 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-02-29 | 300770 | 190093 | 9811648.38 | 10521681.44 | -710033.06 | 17421145.8 | -4.076% |  | 0 | 2016-02-29 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-03-31 | 0 | 554825 | 9811648.38 | 11076506.44 | -1264858.06 | 17421145.8 | -7.26% |  | 568528 | 2016-03-31 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-04-30 | 0 | 145417 | 9811648.38 | 11221923.44 | -1410275.06 | 17421145.8 | -8.095% |  | 0 | 2016-04-30 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-05-31 | 0 | 188996 | 9811648.38 | 11410919.44 | -1599271.06 | 17421145.8 | -9.18% |  | 294683 | 2016-05-31 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-06-30 | 316081 | 153380 | 10127729.38 | 11564299.44 | -1436570.06 | 17421145.8 | -8.246% |  | 0 | 2016-06-30 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-07-31 | 263606 | 40002 | 10391335.38 | 11604301.44 | -1212966.06 | 17421145.8 | -6.963% |  | 0 | 2016-07-31 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-08-31 | 0 | 75247 | 10391335.38 | 11679548.44 | -1288213.06 | 17421145.8 | -7.395% |  | 0 | 2016-08-31 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-09-30 | 0 | 42460 | 10391335.38 | 11722008.44 | -1330673.06 | 17421145.8 | -7.638% |  | 0 | 2016-09-30 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-10-31 | 0 | 40916 | 10391335.38 | 11762924.44 | -1371589.06 | 17421145.8 | -7.873% |  | 0 | 2016-10-31 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2016-11-30 | 0 | 43820 | 10391335.38 | 11806744.44 | -1415409.06 | 17421145.8 | -8.125% |  | 440712 | 2016-11-30 | original |  |  | 2016
Uptown Soil Stabilization Pkg 32 | 2017-01-31 | 0 | 52746 | 10391335.38 | 11859490.44 | -1468155.06 | 17421145.8 | -8.427% |  | 0 | 2017-01-31 | original |  |  | 2017
Uptown Soil Stabilization Pkg 32 | 2017-02-28 | 0 | 64065 | 10391335.38 | 11923555.44 | -1532220.06 | 17421145.8 | -8.795% |  | 0 | 2017-02-28 | original |  |  | 2017
Uptown Soil Stabilization Pkg 32 | 2017-03-31 | 583453 | 118483 | 10974788.38 | 12042038.44 | -1067250.06 | 17421145.8 | -6.126% |  | 0 | 2017-03-31 | original |  |  | 2017
Uptown Soil Stabilization Pkg 32 | 2017-04-30 | 0 | 11000 | 10974788.38 | 12053038.44 | -1078250.06 | 17421145.8 | -6.189% |  | 0 | 2017-04-30 | original |  |  | 2017
Uptown Soil Stabilization Pkg 32 | 2017-07-31 | 0 | 3582 | 10974788.38 | 12056620.44 | -1081832.06 | 17421145.8 | -6.21% |  | 0 | 2017-07-31 | original |  |  | 2017
Uptown Soil Stabilization Pkg 32 | 2017-09-30 | 766581 | 0 | 11741369.38 | 12056620.44 | -315251.06 | 17421145.8 | -1.81% |  | 0 | 2017-09-30 | original |  |  | 2017
1900
Electric Train LRT | 2019-05-01 |  | 4000 | 0 | 4000 | -4000 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2019-06-01 |  | 5219505.11 | 0 | 5223505.11 | -5223505.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2019-07-01 |  | 1150 | 0 | 5224655.11 | -5224655.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2019-08-01 |  | 38526.78 | 0 | 5263181.89 | -5263181.89 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2019-09-01 |  | 261305.95 | 0 | 5524487.84 | -5524487.84 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2019-10-01 |  | 2533278.58 | 0 | 8057766.42 | -8057766.42 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2019-11-01 |  | 3178.64 | 0 | 8060945.06 | -8060945.06 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2019-12-01 |  | 148904.4 | 0 | 8209849.46 | -8209849.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2019
Electric Train LRT | 2020-01-01 |  | 1000000 | 0 | 9209849.46 | -9209849.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
Electric Train LRT | 2020-03-01 |  | 146900 | 0 | 9356749.46 | -9356749.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
Electric Train LRT | 2020-06-01 |  | 146900 | 0 | 9503649.46 | -9503649.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
Electric Train LRT | 2020-09-01 |  | 146900 | 0 | 9650549.46 | -9650549.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  | 2020
Formulas:
Date = [Month/Year]
Month/Year = [Date]

## Market Share (hidden)
Main Category | Sub Category | Amount | Date |  | RME Amount
Residential | Residential | 15330672000 | 2010-01-01 | LE | 0
Commercial | Commercial | 7068768000 | 2010-01-01 | LE | 115072634.23
Restoration | Palace | 112560000 | 2010-01-01 | LE | 0
Infrastructure | Railway | 0 | 2010-01-01 | LE | 0
Infrastructure | Roads | 804000000 | 2010-01-01 | LE | 0
Infrastructure | Port | 0 | 2010-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 0 | 2010-01-01 | LE | 35589876.5
Infrastructure | Networks | 0 | 2010-01-01 | LE | 0
Industrial | Factory | 5092000000 | 2010-01-01 | LE | 0
Industrial | Power Plant | 9112000000 | 2010-01-01 | LE | 0
Infrastructure | Tank | 0 | 2010-01-01 | LE | 0
Residential | Residential | 20430000000 | 2011-01-01 | LE | 0
Commercial | Commercial | 9420000000 | 2011-01-01 | LE | 10688481.1
Restoration | Palace | 150000000 | 2011-01-01 | LE | 0
Infrastructure | Railway | 300000000 | 2011-01-01 | LE | 0
Infrastructure | Roads | 0 | 2011-01-01 | LE | 0
Infrastructure | Port | 0 | 2011-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 0 | 2011-01-01 | LE | 0
Infrastructure | Networks | 2700000000 | 2011-01-01 | LE | 0
Industrial | Factory | 1800000000 | 2011-01-01 | LE | 31905026.19
Industrial | Power Plant | 19200000000 | 2011-01-01 | LE | 0
Infrastructure | Tank | 0 | 2011-01-01 | LE | 55905931
Residential | Residential | 18662805000 | 2012-01-01 | LE | 0
Commercial | Commercial | 8605170000 | 2012-01-01 | LE | 56931016
Restoration | Palace | 137025000 | 2012-01-01 | LE | 0
Infrastructure | Railway | 213150000 | 2012-01-01 | LE | 0
Infrastructure | Roads | 0 | 2012-01-01 | LE | 0
Infrastructure | Port | 0 | 2012-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 0 | 2012-01-01 | LE | 26193836.68
Infrastructure | Networks | 1918350000 | 2012-01-01 | LE | 72946445.96
Industrial | Factory | 5481000000 | 2012-01-01 | LE | 0
Industrial | Power Plant | 2892750000 | 2012-01-01 | LE | 0
Infrastructure | Tank | 152250000 | 2012-01-01 | LE | 18438370
Residential | Residential | 8176086000 | 2013-01-01 | LE | 0
Commercial | Commercial | 3769884000 | 2013-01-01 | LE | 323519095.34
Restoration | Palace | 60030000 | 2013-01-01 | LE | 0
Infrastructure | Railway | 1167250000 | 2013-01-01 | LE | 0
Infrastructure | Roads | 1167250000 | 2013-01-01 | LE | 0
Infrastructure | Port | 0 | 2013-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 0 | 2013-01-01 | LE | 0
Infrastructure | Networks | 1000500000 | 2013-01-01 | LE | 34548331.29
Industrial | Factory | 667000000 | 2013-01-01 | LE | 25501883
Industrial | Power Plant | 3401700000 | 2013-01-01 | LE | 0
Infrastructure | Tank | 600300000 | 2013-01-01 | LE | 0
Residential | Residential | 18989685000 | 2014-01-01 | LE | 0
Commercial | Commercial | 8755890000 | 2014-01-01 | LE | 421664927.1872
Restoration | Palace | 139425000 | 2014-01-01 | LE | 0
Infrastructure | Railway | 5005000000 | 2014-01-01 | LE | 0
Infrastructure | Roads | 11261250000 | 2014-01-01 | LE | 0
Infrastructure | Port | 0 | 2014-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 17517500000 | 2014-01-01 | LE | 76245402
Infrastructure | Networks | 0 | 2014-01-01 | LE | 19589518
Industrial | Factory | 4290000000 | 2014-01-01 | LE | 0
Industrial | Power Plant | 18232500000 | 2014-01-01 | LE | 184387980.81
Infrastructure | Tank | 3217500000 | 2014-01-01 | LE | 0
Residential | Residential | 21862143000 | 2015-01-01 | LE | 314789511
Commercial | Commercial | 10080342000 | 2015-01-01 | LE | 319499876.7349
Restoration | Palace | 160515000 | 2015-01-01 | LE | 0
Infrastructure | Railway | 10570500000 | 2015-01-01 | LE | 0
Infrastructure | Roads | 10570500000 | 2015-01-01 | LE | 0
Infrastructure | Port | 2349000000 | 2015-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 1174500000 | 2015-01-01 | LE | 253761914.9983
Infrastructure | Networks | 0 | 2015-01-01 | LE | 0
Industrial | Factory | 6264000000 | 2015-01-01 | LE | 0
Industrial | Power Plant | 66946500000 | 2015-01-01 | LE | 548077406.64
Infrastructure | Tank | 3523500000 | 2015-01-01 | LE | 0
Residential | Residential | 24161880000 | 2016-01-01 | LE | 0
Commercial | Commercial | 11140720000 | 2016-01-01 | LE | 1335232523
Restoration | Palace | 177400000 | 2016-01-01 | LE | 0
Infrastructure | Railway | 16719950000 | 2016-01-01 | LE | 0
Infrastructure | Roads | 2572300000 | 2016-01-01 | LE | 0
Infrastructure | Port | 1286150000 | 2016-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 1286150000 | 2016-01-01 | LE | 399885271.106
Infrastructure | Networks | 3858450000 | 2016-01-01 | LE | 0
Industrial | Factory | 10644000000 | 2016-01-01 | LE | 274663700
Industrial | Power Plant | 21288000000 | 2016-01-01 | LE | 231378360.54
Infrastructure | Tank | 5322000000 | 2016-01-01 | LE | 0
Residential | Residential | 96838200000 | 2017-01-01 | LE | 0
Commercial | Commercial | 44650800000 | 2017-01-01 | LE | 3267608020
Restoration | Palace | 711000000 | 2017-01-01 | LE | 0
Infrastructure | Railway | 23400000000 | 2017-01-01 | LE | 0
Infrastructure | Roads | 4680000000 | 2017-01-01 | LE | 0
Infrastructure | Port | 0 | 2017-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 9360000000 | 2017-01-01 | LE | 45205818
Infrastructure | Networks | 9360000000 | 2017-01-01 | LE | 605714038
Industrial | Factory | 9000000000 | 2017-01-01 | LE | 848477328
Industrial | Power Plant | 72000000000 | 2017-01-01 | LE | 344511491
Infrastructure | Tank | 18000000000 | 2017-01-01 | LE | 54777143
Residential | Residential | 104193000000 | 2018-01-01 | LE | 3200000000
Commercial | Commercial | 48042000000 | 2018-01-01 | LE | 919938253.6554
Restoration | Palace | 765000000 | 2018-01-01 | LE | 150000000
Infrastructure | Railway | 5400000000 | 2018-01-01 | LE | 0
Infrastructure | Roads | 10800000000 | 2018-01-01 | LE | 54192857
Infrastructure | Port | 18000000000 | 2018-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 1800000000 | 2018-01-01 | LE | 286853371.025
Infrastructure | Networks | 0 | 2018-01-01 | LE | 1633315425
Industrial | Factory | 12600000000 | 2018-01-01 | LE | 112045826
Industrial | Power Plant | 81000000000 | 2018-01-01 | LE | 244347557
Infrastructure | Tank | 9000000000 | 2018-01-01 | LE | 0
Residential | Residential | 57544500000 | 2019-01-01 | LE | 0
Commercial | Commercial | 26533000000 | 2019-01-01 | LE | 3297218156.39
Restoration | Palace | 422500000 | 2019-01-01 | LE | 0
Infrastructure | Railway | 44954000000 | 2019-01-01 | LE | 0
Infrastructure | Roads | 3211000000 | 2019-01-01 | LE | 0
Infrastructure | Port | 12844000000 | 2019-01-01 | LE | 0
Infrastructure | Bridges & Tunnels | 3211000000 | 2019-01-01 | LE | 233806599
Infrastructure | Networks | 0 | 2019-01-01 | LE | 0
Industrial | Factory | 15210000000 | 2019-01-01 | LE | 65831906
Industrial | Power Plant | 43264000000 | 2019-01-01 | LE | 0
Infrastructure | Tank | 10816000000 | 2019-01-01 | LE | 170057475.6641
Residential | Residential | 44353530000 | 2020-01-01 | LE | 870293108
Commercial | Commercial | 20450820000 | 2020-01-01 | LE | 992769728.9033
Restoration | Palace | 325650000 | 2020-01-01 | LE | 101220552
Infrastructure | Railway | 46760000000 | 2020-01-01 | LE | 967000000
Infrastructure | Roads | 3340000000 | 2020-01-01 | LE | 0
Infrastructure | Port | 13360000000 | 2020-01-01 | LE | 434504076.4286
Infrastructure | Bridges & Tunnels | 3340000000 | 2020-01-01 | LE | 1068468556.9524
Infrastructure | Networks | 0 | 2020-01-01 | LE | 650000000
Industrial | Factory | 12525000000 | 2020-01-01 | LE | 0
Industrial | Power Plant | 60120000000 | 2020-01-01 | LE | 182442342
Infrastructure | Tank | 6680000000 | 2020-01-01 | LE | 0
Residential | Residential | 44353530000 | 2021-01-01 | LE | 1462000000
Commercial | Commercial | 20450820000 | 2021-01-01 | LE | 761737619.0476
Restoration | Palace | 325650000 | 2021-01-01 | LE | 0
Infrastructure | Railway | 46760000000 | 2021-01-01 | LE | 0
Infrastructure | Roads | 3340000000 | 2021-01-01 | LE | 0
Infrastructure | Port | 13360000000 | 2021-01-01 | LE | 1100000000
Infrastructure | Bridges & Tunnels | 3340000000 | 2021-01-01 | LE | 142857142.8571
Infrastructure | Networks | 0 | 2021-01-01 | LE | 390000000
Industrial | Factory | 12525000000 | 2021-01-01 | LE | 550000000
Industrial | Power Plant | 60120000000 | 2021-01-01 | LE | 0
Infrastructure | Tank | 6680000000 | 2021-01-01 | LE | 0
Infrastructure | L&L | 0 | 2010-01-01 | LE | 1000000
Infrastructure | L&L | 0 | 2011-01-01 | LE | 0
Infrastructure | L&L | 0 | 2012-01-01 | LE | 17421145.8
Infrastructure | L&L | 0 | 2013-01-01 | LE | 0
Infrastructure | L&L | 0 | 2014-01-01 | LE | 0
Infrastructure | L&L | 0 | 2015-01-01 | LE | 0
Infrastructure | L&L | 0 | 2016-01-01 | LE | 47319156
Infrastructure | L&L | 0 | 2017-01-01 | LE | 107782440
Infrastructure | L&L | 0 | 2018-01-01 | LE | 74596850.7143
Infrastructure | L&L | 0 | 2019-01-01 | LE | 32667399
Infrastructure | L&L | 0 | 2020-01-01 | LE | 0
Infrastructure | L&L | 0 | 2021-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2010-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2011-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2012-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2013-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2014-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2015-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2016-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2017-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2018-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2019-01-01 | LE | 100042648
Infrastructure | Landscape | 0 | 2020-01-01 | LE | 0
Infrastructure | Landscape | 0 | 2021-01-01 | LE | 0

## POC Sheet (hidden)
Year | POC Amount
2010 | 50000000
2011 | 100000000
2012 | 153000000
2013 | 269000000
2014 | 392000000
2015 | 866000000
2016 | 1133000000
2017 | 1889000000
2018 | 2861000000
2019 | 4021000000
2020 | 5800000000
2021 | 1873000000

## 00-Datum
Project Name | Main Category | Sub Category | Scope | Client | Project Manager | Area Manager | Location | S/D Client | Client Type
Marassi Civic Center Pkg 45 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | North Coast | D | Private
Al Oula Infra | Infrastructure | Networks | Civil Works | Sewedy | Eng Hany Fareed | Eng. yasser el saadny | 6th of October | D | Affiliates
New Giza Phase 01 | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private
Hyper Solimanya | Commercial | Market | Civil Works | Hyper | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private
Ismailia Bridges | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY
Maxium Mall | Commercial | Offices & Mall | Turn Key | Maxim | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private
Ataqqa Power Plant | Industrial | Power Plant | Turn Key | Sewedy | Eng Mohamed Abd El Fatah | Eng. Mohamed Salah Helmy | Suez | D | Affiliates
Mall of Egypt Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed Mostafa | Eng. Omar Sobhy | 6th of October | D | ARMY
Marassi Tanks Pkg 22 | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | North Coast | D | Private
Sodic Club House | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private
Montazah Hotel Sharm | Commercial | Hotel | Civil Works | El Montazah | Eng Wael Ragabi | Eng. Omar Sobhy | sharm | S | Private
Uptown Cairo Pkg 53 | Residential | Residential | Turn Key | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | Private
Bani Suif Power Plant 1021 | Industrial | Power Plant | Turn Key | Sewedy | Eng Ashraf Abd El Satar | Eng. Mohamed Ragab | Benisuef | D | Affiliates
New Giza Phase 02 | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private
JICA Wind Farm Gabal El Zeet | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private
El Mostathmereen Mokatam Substation | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Cairo | S | Public
Levana UpTown Pkg 62 | Infrastructure | L&L | Civil Works | EMAAR | Eng Alaa Mahran | Eng Mahmoud Mahlab | Cairo | D | Private
Kayan 110 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Adel Rahmo | Eng. Mohamed Ashry | New Capital | D | ARMY
El Amal Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | New Capital | D | ARMY
Bani Suif Cement | Industrial | Factory | Civil Works | CDI | Eng Mohamed Zaki | Eng Mahmoud Mahlab | Benisuef | S | Private
New Giza Wall | Commercial | Fence | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private
Tamey El Amdid Mansora Power Station | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Mansoura | S | Public
Ismailia Substation 500-220 | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Ismailia | S | Public
El Amal Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
FIEM Wind Farm Gabal El Zeet | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private
KFW Wind Farm Gabal El Zeet | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private
Marassi Tank Pkg 107 | Infrastructure | Tank | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private
Ben Zayed New Capital Tunnel | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | New Capital | D | ARMY
Ministries Buildings | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Wael Ragabi | Eng. Mohamed Ashry | New Capital | D | ARMY
Bani Suif Substation | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Benisuef | S | Public
Royal City Mall | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private
Shoubra Banha Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
SLP Logistic Center PI Park Sewedy Stores | Industrial | Factory | Turn Key | Sewedy | Eng Amir | Eng. Mohamed Fawzy | Cairo | D | Affiliates
El Mostakbal Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Kayan Wall L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Elco Suez Steel Rolling Mill Plant 3 | Industrial | Factory | Turn Key | Elco Suez | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Private
Hyper El Temsah | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY
Marassi Bridge Pkg 117 | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private
Siemens Power Station | Industrial | Factory | Turn Key | SIEMENS | Eng Hassan Youssef | Eng Mahmoud Mahlab | Sokhna | S | Private
Uptown FM85 Pkg 85 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Mohamed Bassuony | Eng Mahmoud Mahlab | Cairo | D | Private
El Sokhna Tunnel 01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Sokhna | D | ARMY
Abu Sultan Bridge 01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY
Mintra Factory | Industrial | Factory | Civil Works | Mintra | Eng Salah Rashad | Eng. Mohamed Abdel Raouf | Cairo | S | Private
King Farouk Restoration | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY
Mohamed Ali Palace | Restoration | Palace | Restoration | Army Forces | Eng Mohamed Saber | Eng Mariam Youssef | Cairo | D | ARMY
Nefisha Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY
Fish Market | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY
Al Jazi Mall | Commercial | Offices & Mall | Civil Works | YAMM | Eng Mohamed Zaki | Eng. Waleed Barakat | 5th settelment | S | Private
Benban Aswan Alcazars Solar Park | Industrial | Power Plant | Civil Works | TSK | Eng Amir | Eng Mahmoud Mahlab | Aswan | S | Private
El Alameen Roads Earth Works | Infrastructure | Roads | Civil Works | Army Forces | Eng Mohamed Abd El Nabi | General Mohamed Salah | North Coast | D | ARMY
El Sewedy Univeristy 2 phase 2 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates
El Sokhna Tunnel L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Sokhna | D | ARMY
R05 Z03 | Residential | Residential | Turn Key | Utilities And Urban Communities | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | New Capital | D | Public
R05 Residential District Z1 & Z2 | Residential | Residential | Turn Key | Utilities And Urban Communities | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | New Capital | D | Public
Abu Sultan Bridge 02 Greenhouse | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY
El Sokhna Tunnel 02 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Sokhna | D | ARMY
El Awsty Middle Tunnel L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Sodic Eastown EDNC | Commercial | Offices & Mall | Turn Key | SODIC | Eng Sayed Osman | Eng. Waleed Barakat | 5th settelment | D | Private
Marassi Civic Center Pkg 144 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private
DPW Sokhna Dubai Port | Infrastructure | Networks | EPC | DPW | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Sokhna | D | Private
Slope Stablization PKG 101 | Infrastructure | L&L | Civil Works | EMAAR | Eng Mohamed Bassuony | Eng Mahmoud Mahlab | Cairo | D | Private
Elco Steel Substation | Industrial | Power Plant | Turn Key | Elco Suez | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Private
Sewab Greenhouse Tunnel | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY
Mivida Irrigation Treatment Plant Pkg 140 | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng. Waleed Barakat | 5th settelment | D | Private
Multi Sports Hall | Commercial | Stadium | EPC | Army Forces | Eng Adel Rahmo | Eng Mahmoud Mahlab | New Capital | D | ARMY
Emergency Bridge
Pyramid El Remayah Tunnel
EGAT | Industrial | Factory | Turn Key | Sewedy | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Affiliates
Abou Ghazala Bridge Ramp L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Mohamed Ali Fahmy Ramps L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
El Mosheer Bridge Abu Zaied Khdr L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Ora Zed Park L&L | Infrastructure | L&L | Civil Works | Ora | Eng Adham Edward | Eng.adham edward | 6th of October | D | Private
DoubleTree Mangroovy El Gouna Hotel | Commercial | Hotel | Civil Works | Sewedy | Eng Sherif El Sisi | Eng. Mohamed Fawzy | Gouna | D | Affiliates
Baron Palace Fence | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY
Safeer Square Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY
Suez Road Tunnel Res L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
HyperOne Zayed Extention | Commercial | Parking | Civil Works | Hyper | Eng Tarek Ramadan | Eng. Mohamed Fawzy | 6th of October | D | Private
IKEA Extention MoA | Commercial | Offices & Mall | Turn Key | Marakez | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private
CFC Podium II | Commercial | Offices & Mall | Core And Shell | Al-Futtaim | Eng Amir | Eng. Waleed Barakat | 5th settelment | S | Private
Mostafa Kamel Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Josef Tito Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Espiko Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
El Gabal El Asfr Tunnel L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
MR3 Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
El Sewedy University 1 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates
Mehwar El Salam Axis L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
El Hegaz Square Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY
Ring Road | Infrastructure | Bridges & Tunnels | Civil Works | Roads and Bridges Authority | Eng Abd El Naby Shaban | Eng Hussien Bahgat | Cairo | D | Public
Marina Inland Marassi Pkg 162 | Infrastructure | Port | Civil Works | EMAAR | Eng Reda | Eng. Mohamed Fawzy | North Coast | D | Private
Sultana Malek Restoration | Restoration | Palace | Restoration | Army Forces | Eng Karem Ehab | Eng Mariam Youssef | Cairo | D | ARMY
Lekela 250MW Wind Farm | Industrial | Power Plant | Civil Works | GAMESA | Eng Marwan Shibl | Eng. Waleed Barakat | Gabal El Zeit | D | Private
New Giza Hospital | Commercial | Hospital | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private
Kayan Landscape | Infrastructure | Landscape | Civil Works | Army Forces | Eng Adel Rahmo | Eng. Omar Sobhy | New Capital | D | ARMY
Abbas Akkad Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY
El Asher Men Ramadan Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mostafa Diab | Eng Hussien Bahgat | Cairo | D | ARMY
Kafr Shokr Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Ahmed El Adawy | Eng Hussien Bahgat | qlyboya | D | ARMY
Al Shorouk Bridge (LRT) | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY
GOV2 Infra | Infrastructure | Networks | Civil Works | Utilities And Urban Communities | Eng Mohamed Abd El Moktader | Eng Mohamed Abd El Fatah | New Capital | D | Public
Cairo Alex Railroad | Infrastructure | Railway | Civil Works | ENR | Eng Ali Tawfeek | Eng.callum | alex | S | Public
Hassan El Mamoun Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mostafa Diab | Eng Hussien Bahgat | Cairo | D | ARMY
Sherouk Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Ora Zed Park 1B Pkgs A&D | Residential | Residential | Turn Key | Ora | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private
Kattameya Creeks | Residential | Residential | Turn Key | Starlight | Eng Mohamed Kamal | Eng. Waleed Barakat | 5th settelment | S | Private
Mansoura University Faculty of Medicine | Commercial | University | Civil Works | Utilities And Urban Communities | Eng Emad Habi | Eng Mohamed Abd El Fatah | mansoura | D | Public
Diplomatic District - Infra | Infrastructure | Networks | Civil Works | Utilities And Urban Communities | Eng Mohamed Abd El Moktader | Eng Mohamed Abd El Fatah | New Capital | D | Public
El Sewedy CFC HQ Internal Finishing | Commercial | Offices & Mall | Turn Key | Sewedy | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 5th settelment | D | Affiliates
Lagoon Discharge Pkg 178 | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Reda | Eng. Mohamed Fawzy | North Coast | D | Private
El Khatatba Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Roads and Bridges Authority | Eng Khaled Tawfek | Eng Hussien Bahgat | qlyboya | D | Public
EGAT Pelletizing Plant | Industrial | Factory | Turn Key | Elco Suez | Eng Mohamed Fadel | Eng. mohamed el seman | Suez | D | Private
Sokhna Port Expansion | Infrastructure | Port | Civil Works | Transportation Ministry | Eng Tarek Ramadan | Eng. mohamed el seman | Sokhna | S | Public
Waldorf Astoria Mock Up Room | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY
MDF Factory | Industrial | Factory | Turn Key | Naile Wood | Eng Bader Osman | Eng. mohamed el seman | sadat | S | Private
Olympic City L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
Kemet Building | Commercial | Offices & Mall | Civil Works | Kemet | Eng Hany Yassin | Eng. Mohamed Ashry | New Capital | S | Private
Alegria DP Port | Infrastructure | Networks | Civil Works | DPW | Eng Mohamed Mostafa | Eng. Omar Sobhy | Alegria | D | Private
Alexandria Bridges | Infrastructure | Bridges & Tunnels | Civil Works | Mohamed Abd El Wahab | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Alex | S | Private
Allegria Club House | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private
Alstom-French Station | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Cairo | S | Public
Autoville Strip Mall | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private
Dubai Port Sokhna Basin 1 | Infrastructure | Networks | Civil Works | DPW | Eng Karim El Far | Eng. Omar Sobhy | Sokhna | D | Private
El Alameen Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
El Asher Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mostafa Diab | Eng Hussien Bahgat | Cairo | D | ARMY
El Asher of Ramadan Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
El Mahala Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed Mostafa | Eng. Omar Sobhy | Mahalla | D | ARMY
El Mostakbal Bridge L&L | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY
El Obour Bridge B2 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Cairo | D | ARMY
El Shone Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Sokhna | D | ARMY
El Wahat Bridge | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | 6th of October | D | ARMY
El Wahat Tunnel | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | 6th of October | D | ARMY
EMEC | Commercial | Offices & Mall | Civil Works | EMEC | Eng Mohamed Abd El Fatah | Eng Mahmoud Mahlab | 5th settelment | S | Private
Hyper Matrouh | Commercial | Market | Turn Key | Army Forces | Eng Omar Sobhy | Eng Omar Sobhy | Alex | D | ARMY
Ismailia Bridge L&L | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY
Logestica Phase 01 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private
Logestica Phase 02 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private
Logestica Phase 03 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private
Marassi Bridges Pkg 37 | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Waleed Tag | Eng Mahmoud Mahlab | North Coast | D | Private
Marassi Golf Maintance Building Pkg 58 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Waleed Tag | Eng Mahmoud Mahlab | North Coast | D | Private
Point 90 New Cairo Mall | Commercial | Offices & Mall | Turn Key | Cairo Company for Housing & Development (CCHD) | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private
Sodic MV Cables | Infrastructure | Networks | Civil Works | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private
Sodic West Town Hub | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private
Limak TB2 Cairo Airport Terminal | Commercial | Terminal | Civil Works | Limak | Eng Mohamed El Saman | Eng. Omar Sobhy | Cairo | S | Private
Twin Towers | Commercial | Offices & Mall | Turn Key | Arabian Group | Eng Karim El Far | Eng Mahmoud Mahlab | 6th of October | D | Private
Uptown Soil Stabilization Pkg 32 | Infrastructure | L&L | Civil Works | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | Cairo | D | Private
Uptown Service Buildings Pkg 17A | Infrastructure | Tank | Civil Works | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | Private
Electric Train LRT | Industrial | Factory | Turn Key | NAT | Eng Hassan | Eng Mahmoud Mahlab | Cairo | S | Public
Sea Shell Playa | Residential | Residential | Turn Key | New Giza | Eng Wael Ragabi | Eng. Omar Sobhy | North Coast | D | Private
El Asmarat | Commercial | Offices & Mall | Civil Works | Arabian Group | Eng Karim El Far | Eng Mahmoud Mahlab | Cairo | D | Private
Aeon Towers Chiller Building

## 01-Cash (hidden)
Project Name | Cash In | Cash Out | Revised Contract Value | Diff Bet Invoice & Cash In | Value of Work
Marassi Civic Center Pkg 45 | 60121284.26 | 42786070.4284 | 56931016 | 3190268.26 | #REF!
Al Oula Infra | 29926324.62 | 14669728.2496 | 72946445.96 | -43020121.34 | #REF!
New Giza Phase 01 | 171442508 | 179630361.66 | 172216796.0405 | -774288.0405 | #REF!
Hyper Solimanya | 112607232.4 | 103719728.62 | 110450184.62 | 2157047.78 | #REF!
Ismailia Bridges | 0 | 0 | 56527617 | -56527617 | #REF!
Maxium Mall | 99593350.16 | 103001352.86 | 98576600 | 1016750.16 | #REF!
Ataqqa Power Plant | 181649889 | 91353900.47 | 184387980.81 | -2738091.81 | #REF!
Mall of Egypt Bridge | 0 | 0 | 183459815.63 | -183459815.63 | #REF!
Marassi Tanks PKG 22 | 18608180.2 | 17707077.82 | 18438370 | 169810.2 | #REF!
Sodic Club House | 130705887.32 | 142729440.81 | 161208266 | -30502378.68 | #REF!
Montazah Hotel Sharm | 0 | 0 | 33784495.5267 | -33784495.5267
Uptown Cairo Pkg 53 | 381560685.9 | 347430145.28 | 314789511 | 66771174.9 | #REF!
Bani Suif Power Plant 1021 | 597206141.16 | 311422110.48 | 427594086.74 | 169612054.42 | #REF!
New Giza Phase 02 | 154546599.71 | 158529314.96 | 155643269.76 | -1096670.05 | #REF!
JICA Wind Farm Gabal El Zeet | 140601327.47 | 102955191.26 | 120483319.9 | 20118007.57 | #REF!
El Mostathmereen Mokatam Substation | 51433806.45 | 12181422.5 | 135792183 | -84358376.55
Levana UpTown Pkg 62 | 69870713.5 | 44955442.91 | 47319156 | 22551557.5 | #REF!
Kayan 110 | 1402896427.85 | 1258688812.28 | 1335232523 | 67663904.85 | #REF!
El Amal Bridge | 0 | 0 | 28943151 | -28943151
Bani Suif Cement | 224024250 | 248217660 | 274663700 | -50639450 | #REF!
Tamey El Amdid Mansora Power Station | 100540373.12 | 97053303.33 | 114399640 | -13859266.88 | #REF!
Ismailia Substation 500-220 | 79601172.1 | 90627332.6 | 109399640 | -29798467.9 | #REF!
El Amal Bridge L&L | 7873319.95 | 18341345.53 | 9050320 | -1177000.05
FIEM Wind Farm Gabal El Zeet | 118092043.93 | 49103791.5 | 72547889 | 45544154.93 | #REF!
KFW Wind Farm Gabal El Zeet | 34795537.22 | 2036408.14 | 23038288.54 | 11757248.68 | #REF!
Marassi Tank PKG 107 | 55550100.93 | 41845889.07 | 54777143 | 772957.93 | #REF!
Ben Zayed New Capital Tunnel | 129021466.95 | 72039334.9 | 343357654.106 | -214336187.156 | #REF!
Ministries Buildings | 2128058098.7 | 1522825412.45 | 2740570200 | -612512101.3 | #REF!
Bani Suif Substation | 151245427.78 | 135514497.68 | 120712211 | 30533216.78 | #REF!
Royal City Mall | 524757126.9 | 471016384.38 | 527037820 | -2280693.1 | #REF!
Shoubra Banha Bridge L&L | 500000 | 820505.14 | 3865380 | -3365380
SLP Logistic Center PI Park Sewedy Stores | 99779829.47 | 89522618.73 | 98230405 | 1549424.47 | #REF!
El Mostakbal Bridge L&L | 1713657 | 132843 | 4424558 | -2710901
Kayan Wall L&L | 78938339.85 | 41137399.69 | 107782440 | -28844100.15
Elco Suez Steel Rolling Mill Plant 3 | 480796737.62 | 326806636.94 | 417390514 | 63406223.62 | #REF!
Hyper El Temsah | 50000000 | 137630112.65 | 168976040.9524 | -118976040.9524 | #REF!
Marassi Bridge Pkg 117 | 48600087.78 | 35728418.01 | 45205818 | 3394269.78 | #REF!
Siemens Power Station | 341960104.82 | 333846564.73 | 332856409 | 9103695.82 | #REF!
Uptown FM85 Pkg 85 | 9214096.71 | 3432076.77 | 0
El Sokhna Tunnel 01 | 41526275.95 | 16853644.76 | 46639513 | -5113237.05
Abu Sultan Bridge 01 | 12440712 | 11172679.09 | 18752986 | -6312274 | #REF!
Mintra Factory | 41752244.26 | 43506040.93 | 112045826 | -70293581.74 | #REF!
King Farouk Restoration | 0 | 109505.05 | 0 | 0
Mohamed Ali Palace | 33629667 | 71307257.86 | 150000000 | -116370333 | #REF!
Nefisha Bridge | 46075766.2 | 35263913.85 | 70928098 | -24852331.8 | #REF!
Fish Market | 62378219 | 43255489.04 | 66185668.5714 | -3807449.5714 | #REF!
Al Jazi Mall | 133503335.2 | 119130046.89 | 245977347.1316 | -112474011.9316 | #REF!
Benban Aswan Alcazars Solar Park | 250818966.47 | 199505682.62 | 212005784 | 38813182.47 | #REF!
El Alameen Roads Earth Works | 49607551.5 | 42131218.73 | 54192857 | -4585305.5 | #REF!
El Sewedy Univeristy 2 phase 2 | 456682638.09 | 334885912.63 | 262378822 | 194303816.09 | #REF!
El Sokhna Tunnel L&L | 454415 | 351929.54 | 0 | 454415
R05 Residential District Z1 & Z2 | 1099567845.15 | 606687510.9 | 3200000000 | -2100432154.85 | #REF!
Abu Sultan Bridge 02 Greenhouse | 58589665.7 | 21959138.22 | 67755600 | -9165934.3 | #REF!
El Sokhna Tunnel 02 | 11593995.4 | 9252376.55 | 22334150 | -10740154.6 | #REF!
El Awsty Middle Tunnel L&L | 677590 | 191288.84 | 1024820 | -347230
Sodic Eastown EDNC | 741980612.15 | 698564330.06 | 1074545067 | -332564454.85 | #REF!
Marassi Civic Center Pkg 144 | 177969586.46 | 176730410.79 | 176420375 | 1549211.46 | #REF!
DPW Sokhna Dubai Port | 1294901108.82 | 976336418.44 | 1633315425 | -338414316.18 | #REF!
Slope Stablization PKG 101 | 156897142.95 | 31602600.69 | 52028085.7143 | 104869057.2357 | #REF!
Elco Steel Substation | 116935651.99 | 2871944.39 | 32341773 | 84593878.99 | #REF!
Sewab Greenhouse Tunnel | 3830500 | 3283.1 | 10957813.825 | -7127313.825 | #REF!
Mivida Irrigation Treatment Plant Pkg 140 | 147578226.23 | 108021882.15 | 170057475.6641 | -22479249.4341 | #REF!
Multi Sports Hall | 376452335 | 329774945.01 | 1200000000 | -823547665
EGAT | 56966571.53 | 3673674.77 | 65831906 | -8865334.47
Abou Ghazala Bridge Ramp L&L | 1343575 | 315282.35 | 1688453 | -344878
Mohamed Ali Fahmy Ramps L&L | 40208582.66 | 2216105.07 | 7149700 | 33058882.66
El Mosheer Bridge Abu Zaied Khdr L&L | 0 | 2447030.43 | 4203687 | -4203687
Ora Zed Park L&L | 898331.21 | 2307400.69 | 1042542 | -144210.79
DoubleTree Mangroovy El Gouna Hotel | 50919949.85 | 50641659.97 | 57898699.39 | -6978749.54 | #REF!
Baron Palace Fence | 6348605 | 11483720.3 | 16220552 | -9871947
Safeer Square Bridge | 12309120.6 | 42391917.21 | 95436549 | -83127428.4
Suez Road Tunnel Res L&L | 4148825 | 823007.59 | 4423592 | -274767
HyperOne Zayed Extention | 121786405 | 82970455.7 | 133583770 | -11797365 | #REF!
IKEA Extention MoA | 175725075.28 | 194355785.18 | 196190620 | -20465544.72 | #REF!
CFC Podium II | 491543078.36 | 376746629.72 | 635000000 | -143456921.64 | #REF!
Josef Tito Bridge L&L | 0 | 26705 | 0 | 0
Espiko Bridge L&L | 0 | 113275.2 | 0 | 0
MR3 Bridge L&L | 714790 | 471702.01 | 1520085 | -805295
El Sewedy University 1 | 268548987.51 | 261294944.82 | 593999147 | -325450159.49 | #REF!
Mehwar El Salam Axis L&L | 0 | 2268545.91 | 16843027 | -16843027
El Hegaz Square Bridge | 58649995 | 92040766.86 | 138370050 | -79720055
Ring Road | 124289465.1 | 151157457.61 | 524000000 | -399710534.9
Marina Inland Marassi Pkg 162 | 187683270.38 | 90374145.69 | 434504076.4286 | -246820806.0486 | #REF!
Sultana Malek Restoration | 0 | 8325812.28 | 85000000 | -85000000
Lekela 250MW Wind Farm | 151634574.42 | 121669992.58 | 182442342 | -30807767.58 | #REF!
New Giza Hospital | 0 | 0 | 542690000 | -542690000
Kayan Landscape | 15494815 | 20614917.27 | 100042648 | -84547833
Abbas Akkad Bridge | 26904265 | 37932184.28 | 124132580.9524 | -97228315.9524
El Asher Men Ramadan Bridge | 11107315 | 79981200.02 | 93910355 | -82803040
Kafr Shokr Bridge | 2644030 | 46765918.07 | 147845325 | -145201295
Al Shorouk Bridge (LRT) | 20050000 | 20136787.36 | 26145782 | -6095782
GOV2 Infra | 8793510.21 | 34351419.65 | 650000000 | -641206489.79
Cairo Alex Railroad | 153491959.6 | 64634871.1 | 967000000 | -813508040.4
Hassan El Mamoun Bridge | 6575875 | 71839254.73 | 93800000 | -87224125
Sherouk Bridge L&L | 0 | 606902.21 | 1000000 | -1000000
Ora Zed Park 1B Pkgs A&D | 101168059.79 | 141761437.38 | 870293108 | -769125048.21
Kattameya Creeks | 214043961.23 | 89054175.5 | 1462000000 | -1247956038.77
Mansoura University Faculty of Medicine | 0 | 4827409 | 219047619.0476 | -219047619.0476
Diplomatic District - Infra | 20000000 | 3656490.64 | 390000000 | -370000000
El Sewedy CFC HQ Internal Finishing | 118099859.76 | 49805372.19 | 327718153.3333 | -209618293.5733
Lagoon Discharge Pkg 178 | 3747170.2 | 7763963.85 | 40449240 | -36702069.8
El Khatatba Bridge | 0 | 771525.12 | 142857142.8571 | -142857142.8571
EGAT Pelletizing Plant | 12000000 | 200923.62 | 375000000 | -363000000
Sokhna Port Expansion | 0 | 1618143.15 | 1100000000 | -1100000000
MDF Factory | 41622365.4 | 8488877.87 | 175000000 | -133377634.6
Kemet Building | 0 | 0 | 71052428.57 | -71052428.57
Alegria DP Port | 32885879 | 30105852.23 | 605714038 | -572828159 | #REF!
Alexandria Bridges | 0 | 0 | 35589876.5 | -35589876.5 | #REF!
Autoville Strip Mall | 0 | 0 | 51072634 | -51072634 | #REF!
Batch Plant | 0 | 0 | #N/A | #N/A
Dubai Port Sokhna Basin 1 | 0 | 0 | 34548331.29 | -34548331.29
El Alameen Bridge L&L | 0 | 0 | 0 | 0
El Asher of Ramadan Bridge L&L | 0 | 0 | 0 | 0
El Mahala Bridge | 48078188 | 26064872.74 | 67245402 | -19167214 | #REF!
Logestica 02 | 50134555.18 | 3749701.41 | #N/A | #N/A | #REF!
Marassi Bridges Pkg 37 | 24774245 | 24473789 | 26193836.68 | -1419591.68 | #REF!
Marassi Golf Maintance Building Pkg 58 | 2851561.2 | 5249502.89 | 4720405.25 | -1868844.05 | #REF!
Point 90 New Cairo Mall | 129089898.97 | 114483162.8268 | 145010925.68 | -15921026.71 | #REF!
Sodic MV Cables | 14305933.55 | 4200633.55 | 19589518 | -5283584.45 | #REF!
Sodic West Town Hub | 3620053.96 | 0 | 54160920.41 | -50540866.45 | #REF!
Limak TB2 Cairo Airport Terminal | 646177021.35 | 48450478.32 | 119626844 | 526550177.35 | #REF!
Twin Towers | 53383699.77 | 14247512.44 | 64000000.23 | -10616300.46 | #REF!
Uptown Soil Stabilization Pkg 32 | 11741369.38 | 12056620.44 | 17421145.8 | -5679776.42 | #REF!
Uptown Service Buildings Pkg 17A | 16425665 | 16432556 | 55905931 | -39480266
Electric Train LRT | 0 | 8650549.46 | 0 | 0
Sea Shell Playa | 0 | 0 | 0 | 0

## Sheet1 (hidden)
1900-01-05 | Marassi Civic Center Pkg 45 |  | 6 | Marassi Civic Center Pkg 45 | 6 | Marassi Civic Center Pkg 45 |  |  |  | 1900-01-05 | Marassi Civic Center Pkg 45 | 6 | Marassi Civic Center Pkg 45 |  | 1900-01-05 | Marassi Civic Center Pkg 45
8 | Al Oula Infra |  | 8 | Al Oula Infra | 8 | Al Oula Infra |  |  |  | 1900-01-07 | Al Oula Infra | 6 | Marassi Civic Center Pkg 45 |  | 8 | Al Oula Infra
1900-01-11 | New Giza Phase 01 |  | 12 | New Giza Phase 01 | 12 | New Giza Phase 01 |  |  |  | 12 | New Giza Phase 01 | 6 | Marassi Civic Center Pkg 45 |  | 1900-01-11 | New Giza Phase 01
13 | Hyper Solimanya A |  | 13 | Hyper Solimanya | 13 | Hyper Solimanya |  |  |  | 13 | Hyper Solimanya | 6 | Marassi Civic Center Pkg 45 |  | 13 | Hyper Solimanya
13 | Hyper Solimanya B |  | 19 | Ismailia Bridges | 19 | Ismailia Bridges |  |  |  | 19 | Ismailia Bridges | 6 | Marassi Civic Center Pkg 45 |  | 19 | Ismailia Bridges
13 | Hyper Solimanya C |  | 23 | Maxium Mall | 23 | Maxium Mall |  |  |  | 23 | Maxium Mall | 6 | Marassi Civic Center Pkg 45 |  | 23 | Maxium Mall
13 | Hyper Solimanya |  | 28 | Ataqqa Power Plant | 28 | Ataqqa Power Plant |  |  |  | 28 | Ataqqa Power Plant | 6 | Marassi Civic Center Pkg 45 |  | 28 | Ataqqa Power Plant
19 | Ismailia Bridges |  | 30 | Mall of Egypt Bridge | 30 | Mall of Egypt Bridge |  |  |  | 30 | Mall of Egypt Bridge | 6 | Marassi Civic Center Pkg 45 |  | 30 | Mall of Egypt Bridge
23 | Maxium Mall A |  | 31 | Marassi Tanks Pkg 22 | 31 | Marassi Tanks PKG 22 |  |  |  | 31 | Marassi Tanks PKG 22 | 6 | Marassi Civic Center Pkg 45 |  | 1900-01-30 | Marassi Tanks PKG 22
23 | Maxium Mall B |  | 32 | Sodic Club House | 32 | Sodic Club House |  |  |  | 32 | Sodic Club House | 6 | Marassi Civic Center Pkg 45 |  | 32 | Sodic Club House
23 | Maxium Mall |  | 33 | Montazah Hotel Sharm | 33 | Montazah Hotel Sharm |  |  |  | 1900-02-01 | Montazah Hotel Sharm | 6 | Marassi Civic Center Pkg 45 |  | 1900-02-01 | Montazah Hotel Sharm
28 | Ataqqa Power Plant |  | 34 | Uptown Cairo Pkg 53 | 34 | Uptown Cairo Pkg 53 |  |  |  | 34 | Uptown Cairo Pkg 53 | 6 | Marassi Civic Center Pkg 45 |  | 34 | Uptown Cairo Pkg 53
30 | Mall of Egypt Bridge |  | 35 | Bani Suif Power Plant 1021 | 35 | Bani Suif Power Plant 1021 |  |  |  | 35 | Bani Suif Power Plant 1021 | 6 | Marassi Civic Center Pkg 45 |  | 1900-02-03 | Bani Suif Power Plant 1021
1900-01-30 | Marassi Tanks PKG 22 |  | 37 | New Giza Phase 02 | 37 | New Giza Phase 02 |  |  |  | 37 | New Giza Phase 02 | 6 | Marassi Civic Center Pkg 45 |  | 1900-02-05 | New Giza Phase 02
32 | Sodic Club House A |  | 39 | JICA Wind Farm Gabal El Zeet | 39 | JICA Wind Farm Gabal El Zeet |  |  |  | 39 | JICA Wind Farm Gabal El Zeet | 6 | Marassi Civic Center Pkg 45 |  | 1900-02-07 | JICA Wind Farm Gabal El Zeet
32 | Sodic Club House B |  | 40 | El Mostathmereen Mokatam Substation | 40 | El Mostathmereen Mokatam Substation |  |  |  | 1900-02-08 | El Mostathmereen Mokatam Substation | 6 | Marassi Civic Center Pkg 45 |  | 40 | El Mostathmereen Mokatam Substation
32 | Sodic Club House C |  | 41 | Levana UpTown Pkg 62 | 41 | Levana UpTown Pkg 62 |  |  |  | 41 | Levana UpTown PKG 62 | 6 | Marassi Civic Center Pkg 45 |  | 41 | Levana UpTown PKG 62
32 | Sodic Club House D |  | 45 | Kayan 110 | 45 | Kayan 110 |  |  |  | 45 | Kayan 110 | 6 | Marassi Civic Center Pkg 45 |  | 45 | Kayan 110
32 | Sodic Club House E |  | 46 | El Amal Bridge | 46 | El Amal Bridge |  |  |  | 1900-02-14 | El Amal Bridge | 6 | Marassi Civic Center Pkg 45 |  | 46 | El Amal Bridge
32 | Sodic Club House F |  | 47 | Bani Suif Cement | 47 | Bani Suif Cement |  |  |  | 47 | Bani Suif Cement | 6 | Marassi Civic Center Pkg 45 |  | 47 | Bani Suif Cement
32 | Sodic Club House |  | 48 | New Giza Wall | 48 | New Giza Wall |  |  |  | 1900-02-16 | New Giza Wall | 6 | Marassi Civic Center Pkg 45 |  | 48 | New Giza Wall
1900-02-01 | Montazah Hotel Sharm |  | 51 | Tamey El Amdid Mansora Power Station | 51 | Tamey El Amdid Mansora Power Station |  |  |  | 51 | Tamey El Amdid Mansora Power Station | 6 | Marassi Civic Center Pkg 45 |  | 51 | Tamey El Amdid Mansora Power Station
34 | Uptown Cairo Pkg 53 |  | 52 | Ismailia Substation 500-220 | 52 | Ismailia Substation 500-220 |  |  |  | 52 | Ismailia Substation 500-220 | 6 | Marassi Civic Center Pkg 45 |  | 52 | Ismailia Substation 500-220
1900-02-03 | Bani Suif Power Plant 1021 |  | 53 | El Amal Bridge L&L | 53 | El Amal Bridge L&L |  |  |  | 53 | El Amal Bridge L&L | 6 | Marassi Civic Center Pkg 45 |  | 53 | El Amal Bridge L&L
1900-02-05 | New Giza Phase 02 |  | 54 | FIEM Wind Farm Gabal El Zeet | 54 | FIEM Wind Farm Gabal El Zeet |  |  |  | 54 | FIEM Wind Farm Gabal El Zeet | 6 | Marassi Civic Center Pkg 45 |  | 1900-02-22 | FIEM Wind Farm Gabal El Zeet
1900-02-07 | JICA Wind Farm Gabal El Zeet |  | 55 | KFW Wind Farm Gabal El Zeet | 55 | KFW Wind Farm Gabal El Zeet |  |  |  | 55 | KFW Wind Farm Gabal El Zeet | 6 | Marassi Civic Center Pkg 45 |  | 1900-02-23 | KFW Wind Farm Gabal El Zeet
40 | El Mostathmereen Mokatam Sub | station | 58 | Marassi Tank Pkg 107 | 58 | Marassi Tank PKG 107 |  |  |  | 58 | Marassi Tank PKG 107 | 6 | Marassi Civic Center Pkg 45 |  | 58 | Marassi Tank PKG 107
41 | Levana UpTown PKG 62 |  | 59 | Ben Zayed New Capital Tunnel | 59 | Ben Zayed New Capital Tunnel |  |  |  | 59 | Ben Zayed New Capital Tunnel | 6 | Marassi Civic Center Pkg 45 |  | 59 | Ben Zayed New Capital Tunnel
45 | Kayan 110 A |  | 60 | Ministries Buildings | 60 | Ministries Buildings |  |  |  | 60 | Ministries Buildings | 6 | Marassi Civic Center Pkg 45 |  | 60 | Ministries Buildings
45 | Kayan 110 B |  | 61 | Bani Suif Substation | 61 | Bani Suif Substation |  |  |  | 61 | Bani Suif Substation | 6 | Marassi Civic Center Pkg 45 |  | 61 | Bani Suif Substation
45 | Kayan 110 C |  | 63 | Royal City Mall | 63 | Royal City Mall |  |  |  | 63 | Royal City Mall | 6 | Marassi Civic Center Pkg 45 |  | 63 | Royal City Mall
45 | Kayan 110 |  | 64 | Shoubra Banha Bridge L&L | 64 | Shoubra Banha Bridge L&L |  |  |  | 1900-03-04 | Shoubra Banha Bridge L&L | 6 | Marassi Civic Center Pkg 45 |  | 64 | Shoubra Banha Bridge L&L
46 | El Amal Bridge |  | 65 | SLP Logistic Center PI Park Sewedy Stores | 65 | SLP Logistic Center PI Park Sewedy Stores |  |  |  | 65 | SLP Logistic Center PI Park Sewedy Stores | 6 | Marassi Civic Center Pkg 45 |  | 65 | SLP Logistic Center PI Park Sewedy Stores
47 | Bani Suif Cement |  | 66 | El Mostakbal Bridge L&L | 66 | El Mostakbal Bridge L&L |  |  |  | 66 | El Mostakbal Bridge L&L | 6 | Marassi Civic Center Pkg 45 |  | 66 | El Mostakbal Bridge L&L
48 | New Giza Wall |  | 68 | Kayan Wall L&L | 68 | Kayan Wall L&L |  |  |  | 1900-03-08 | Kayan Wall L&L | 6 | Marassi Civic Center Pkg 45 |  | 68 | Kayan Wall L&L
51 | Tamey El Amdid Mansora Power | Station | 69 | Elco Suez Steel Rolling Mill Plant 3 | 69 | Elco Suez Steel Rolling Mill Plant 3 |  |  |  | 69 | Elco Suez Steel Rolling Mill Plant 3 | 6 | Marassi Civic Center Pkg 45 |  | 69 | Elco Suez Steel Rolling Mill Plant 3
52 | Ismailia Substation 500-220 |  | 70 | Hyper El Temsah | 70 | Hyper El Temsah |  |  |  | 70 | Hyper El Temsah | 6 | Marassi Civic Center Pkg 45 |  | 70 | Hyper El Temsah
53 | El Amal Bridge L&L |  | 71 | Marassi Bridge Pkg 117 | 71 | Marassi Bridge Pkg 117 |  |  |  | 71 | Marassi Bridge Pkg 117 | 6 | Marassi Civic Center Pkg 45 |  | 71 | Marassi Bridge Pkg 117
1900-02-22 | FIEM Wind Farm Gabal El Zeet |  | 72 | Siemens Power Station | 72 | Siemens Power Station |  |  |  | 72 | Siemens Power Station | 6 | Marassi Civic Center Pkg 45 |  | 72 | Siemens Power Station
1900-02-23 | KFW Wind Farm Gabal El Zeet |  | 73 | Uptown FM85 Pkg 85 | 73 | Uptown FM85 Pkg 85 |  |  |  | 73 | Uptown FM85 Pkg 85 | 6 | Marassi Civic Center Pkg 45 |  | 73 | Uptown FM85 Pkg 85
58 | Marassi Tank PKG 107 A |  | 74 | El Sokhna Tunnel 01 | 74 | El Sokhna Tunnel 01 |  |  |  | 1900-03-14 | El Sokhna Tunnel 01 | 6 | Marassi Civic Center Pkg 45 |  | 74 | El Sokhna Tunnel 01
58 | Marassi Tank PKG 107 B |  | 75 | Abu Sultan Bridge 01 | 75 | Abu Sultan Bridge 01 |  |  |  | 75 | Abu Sultan Bridge 01 | 6 | Marassi Civic Center Pkg 45 |  | 75 | Abu Sultan Bridge 01
58 | Marassi Tank PKG 107 C |  | 76 | Mintra Factory | 76 | Mintra Factory |  |  |  | 76 | Mintra Factory | 6 | Marassi Civic Center Pkg 45 |  | 76 | Mintra Factory
58 | Marassi Tank PKG 107 |  | 77 | King Farouk Restoration | 77 | King Farouk Restoration |  |  |  | 1900-03-17 | King Farouk Restoration | 6 | Marassi Civic Center Pkg 45 |  | 77 | King Farouk Restoration
59 | Ben Zayed New Capital Tunnel |  | 78 | Mohamed Ali Palace | 78 | Mohamed Ali Palace |  |  |  | 78 | Mohamed Ali Palace | 6 | Marassi Civic Center Pkg 45 |  | 78 | Mohamed Ali Palace
60 | Ministries Buildings A |  | 79 | Nefisha Bridge | 79 | Nefisha Bridge |  |  |  | 79 | Nefisha Bridge | 6 | Marassi Civic Center Pkg 45 |  | 79 | Nefisha Bridge
60 | Ministries Buildings B |  | 80 | Fish Market | 80 | Fish Market |  |  |  | 80 | Fish Market |  |  |  | 80 | Fish Market
60 | Ministries Buildings C |  | 81 | Al Jazi Mall | 81 | Al Jazi Mall |  |  |  | 81 | Al Jazi Mall | 8 | Al Oula Infra |  | 81 | Al Jazi Mall
60 | Ministries Buildings D |  | 83 | Benban Aswan Alcazars Solar Park | 83 | Benban Aswan Alcazars Solar Park |  |  |  | 83 | Benban Aswan Alcazars Solar Park | 8 | Al Oula Infra |  | 83 | Benban Aswan Alcazars Solar Park
60 | Ministries Buildings |  | 84 | El Alameen Roads Earth Works | 84 | El Alameen Roads Earth Works |  |  |  | 84 | El Alameen Roads Earth Works | 8 | Al Oula Infra |  | 84 | El Alameen Roads Earth Works
61 | Bani Suif Substation |  | 85 | El Sewedy Univeristy | 85 | El Sewedy Univeristy |  |  |  | 85 | El Sewedy Univeristy | 8 | Al Oula Infra |  | 85 | El Sewedy Univeristy
63 | Royal City Mall A |  | 86 | El Sokhna Tunnel L&L | 86 | El Sokhna Tunnel L&L |  |  |  | 86 | El Sokhna Tunnel L&L | 8 | Al Oula Infra |  | 86 | El Sokhna Tunnel L&L
63 | Royal City Mall B |  | 87 | R05 Z03 | 88 | R05 Residential District Z1 & Z2 |  |  |  | 87 | R05 Z03 | 8 | Al Oula Infra |  | 88 | R05 Residential District Z1 & Z2
63 | Royal City Mall C |  | 88 | R05 Residential District Z1 & Z2 | 89 | Abu Sultan Bridge 02 Greenhouse |  |  |  | 88 | R05 Residential District Z1 & Z2 | 8 | Al Oula Infra |  | 89 | Abu Sultan Bridge 02 Greenhouse
63 | Royal City Mall D |  | 89 | Abu Sultan Bridge 02 Greenhouse | 90 | El Sokhna Tunnel 02 |  |  |  | 89 | Abu Sultan Bridge 02 Greenhouse | 8 | Al Oula Infra |  | 90 | El Sokhna Tunnel 02
63 | Royal City Mall |  | 90 | El Sokhna Tunnel 02 | 91 | El Awsty Middle Tunnel L&L |  |  |  | 90 | El Sokhna Tunnel 02 | 8 | Al Oula Infra |  | 91 | El Awsty Middle Tunnel L&L
63 | Royal City Mall E |  | 91 | El Awsty Middle Tunnel L&L | 92 | Sodic Eastown EDNC |  |  |  | 1900-03-31 | El Awsty Middle Tunnel L&L | 8 | Al Oula Infra |  | 92 | Sodic Eastown EDNC
64 | Shoubra Banha Bridge L&L |  | 92 | Sodic Eastown EDNC | 93 | Marassi Civic Center Pkg 144 |  |  |  | 92 | Sodic Eastown EDNC | 8 | Al Oula Infra |  | 93 | Marassi Civic Center Pkg 144
65 | SLP Logistic Center PI Park | Sewedy Stores A | 93 | Marassi Civic Center Pkg 144 | 94 | DPW Sokhna Dubai Port |  |  |  | 93 | Marassi Civic Center Pkg 144 | 8 | Al Oula Infra |  | 94 | DPW Sokhna Dubai Port
65 | SLP Logistic Center PI Park | Sewedy Stores B | 94 | DPW Sokhna Dubai Port | 95 | Slope Stablization PKG 101 |  |  |  | 94 | DPW Sokhna Dubai Port | 8 | Al Oula Infra |  | 95 | Slope Stablization PKG 101
65 | SLP Logistic Center PI Park | Sewedy Stores C | 95 | Slope Stablization PKG 101 | 96 | Elco Steel Substation |  |  |  | 95 | Slope Stablization PKG 101 | 8 | Al Oula Infra |  | 96 | Elco Steel Substation
65 | SLP Logistic Center PI Park | Sewedy Stores | 96 | Elco Steel Substation | 97 | Sewab Greenhouse Tunnel |  |  |  | 1900-04-05 | Elco Steel Substation | 8 | Al Oula Infra |  | 97 | Sewab Greenhouse Tunnel
66 | El Mostakbal Bridge L&L |  | 97 | Sewab Greenhouse Tunnel | 98 | Mivida Irrigation Treatment Plant Pkg 140 |  |  |  | 97 | Sewab Greenhouse Tunnel | 8 | Al Oula Infra |  | 98 | Mivida Irrigation Treatment Plant Pkg 140
68 | Kayan Wall L&L |  | 98 | Mivida Irrigation Treatment Plant Pkg 140 | 99 | Multi Sports Hall |  |  |  | 98 | Mivida Irrigation Treatment Plant Pkg 140 | 8 | Al Oula Infra |  | 98 | Mivida Irrigation Treatment Plant Pkg 140
69 | Elco Suez Steel Rolling Mill | Plant 3 | 99 | Multi Sports Hall | 100 | Emergency Bridge |  |  |  | 1900-04-08 | Multi Sports Hall | 8 | Al Oula Infra |  | 99 | Multi Sports Hall
70 | Hyper El Temsah A |  | 100 | Emergency Bridge | 101 | Pyramid El Remayah Tunnel |  |  |  | 1900-04-11 | EGAT | 8 | Al Oula Infra |  | 100 | Emergency Bridge
70 | Hyper El Temsah B |  | 101 | Pyramid El Remayah Tunnel | 102 | EGAT |  |  |  | 1900-04-12 | Abou Ghazala Bridge Ramp L&L | 8 | Al Oula Infra |  | 101 | Pyramid El Remayah Tunnel
70 | Hyper El Temsah C |  | 102 | EGAT | 103 | Abou Ghazala Bridge Ramp L&L |  |  |  | 1900-04-13 | Mohamed Ali Fahmy Ramps L&L | 8 | Al Oula Infra |  | 102 | EGAT
70 | Hyper El Temsah |  | 103 | Abou Ghazala Bridge Ramp L&L | 104 | Mohamed Ali Fahmy Ramps L&L |  |  |  | 1900-04-14 | El Mosheer Bridge Abu Zaied Khdr L&L | 8 | Al Oula Infra |  | 103 | Abou Ghazala Bridge Ramp L&L
71 | Marassi Bridge Pkg 117 |  | 104 | Mohamed Ali Fahmy Ramps L&L | 105 | El Mosheer Bridge Abu Zaied Khdr L&L |  |  |  | 1900-04-15 | Ora Zed Park L&L | 8 | Al Oula Infra |  | 104 | Mohamed Ali Fahmy Ramps L&L
72 | Siemens Power Station |  | 105 | El Mosheer Bridge Abu Zaied Khdr L&L | 106 | Ora Zed Park L&L |  |  |  | 107 | DoubleTree Mangroovy El Gouna Hotel | 8 | Al Oula Infra |  | 105 | El Mosheer Bridge Abu Zaied Khdr L&L
73 | Uptown FM85 Pkg 85 |  | 106 | Ora Zed Park L&L | 107 | DoubleTree Mangroovy El Gouna Hotel |  |  |  | 1900-04-17 | Baron Palace Fence | 8 | Al Oula Infra |  | 106 | Ora Zed Park L&L
74 | El Sokhna Tunnel 01 |  | 107 | DoubleTree Mangroovy El Gouna Hotel | 108 | Baron Palace Fence |  |  |  | 109 | Safeer Square Bridge | 8 | Al Oula Infra |  | 107 | DoubleTree Mangroovy El Gouna Hotel
75 | Abu Sultan Bridge 01 |  | 108 | Baron Palace Fence | 109 | Safeer Square Bridge |  |  |  | 111 | HyperOne Zayed Extention | 8 | Al Oula Infra |  | 108 | Baron Palace Fence
76 | Mintra Factory |  | 109 | Safeer Square Bridge | 110 | Suez Road Tunnel Res L&L |  |  |  | 1900-04-19 | Suez Road Tunnel Res L&L | 8 | Al Oula Infra |  | 109 | Safeer Square Bridge
77 | King Farouk Restoration |  | 110 | Suez Road Tunnel Res L&L | 111 | HyperOne Zayed Extention |  |  |  | 112 | IKEA Extention MoA | 8 | Al Oula Infra |  | 110 | Suez Road Tunnel Res L&L
78 | Mohamed Ali Palace |  | 111 | HyperOne Zayed Extention | 112 | IKEA Extention MoA |  |  |  | 113 | CFC Podium II | 8 | Al Oula Infra |  | 111 | HyperOne Zayed Extention
79 | Nefisha Bridge |  | 112 | IKEA Extention MoA | 113 | CFC Podium II |  |  |  | 114 | Mostafa Kamel Bridge L&L | 8 | Al Oula Infra |  | 112 | IKEA Extention MoA
80 | Fish Market A |  | 113 | CFC Podium II | 114 | Mostafa Kamel Bridge L&L |  |  |  | 115 | Josef Tito Bridge L&L |  |  |  | 113 | CFC Podium II
80 | Fish Market B |  | 114 | Mostafa Kamel Bridge L&L | 115 | Josef Tito Bridge L&L |  |  |  | 116 | Espiko Bridge L&L | 12 | New Giza Phase 01 |  | 114 | Mostafa Kamel Bridge L&L
80 | Fish Market C |  | 115 | Josef Tito Bridge L&L | 116 | Espiko Bridge L&L |  |  |  | 117 | El Gabal El Asfr Tunnel L&L | 12 | New Giza Phase 01 |  | 115 | Josef Tito Bridge L&L
80 | Fish Market D |  | 116 | Espiko Bridge L&L | 117 | El Gabal El Asfr Tunnel L&L |  |  |  | 1900-04-27 | MR3 Bridge L&L | 12 | New Giza Phase 01 |  | 116 | Espiko Bridge L&L
80 | Fish Market |  | 117 | El Gabal El Asfr Tunnel L&L | 118 | MR3 Bridge L&L |  |  |  | 1900-04-28 | El Sewedy Univeristy 2 | 12 | New Giza Phase 01 |  | 117 | El Gabal El Asfr Tunnel L&L
81 | Al Jazi Mall |  | 118 | MR3 Bridge L&L | 119 | El Sewedy Univeristy 2 |  |  |  | 119 | El Sewedy Univeristy 2 Phase 2 | 12 | New Giza Phase 01 |  | 118 | MR3 Bridge L&L
83 | Benban Aswan Alcazars Solar | Park | 119 | El Sewedy Univeristy 2 Phase 2 | 119 | El Sewedy Univeristy 2 Phase 2 |  |  |  | 1900-04-29 | Mehwar El Salam Axis L&L | 12 | New Giza Phase 01 |  | 119 | El Sewedy Univeristy 2 Phase 2
84 | El Alameen Roads Earth Works |  | 120 | Mehwar El Salam Axis L&L | 120 | Mehwar El Salam Axis L&L |  |  |  | 1900-04-30 | El Hegaz Square Bridge | 12 | New Giza Phase 01 |  | 120 | Mehwar El Salam Axis L&L
85 | El Sewedy Univeristy A |  | 121 | El Hegaz Square Bridge | 121 | El Hegaz Square Bridge |  |  |  | 1900-05-01 | Ring Road Extension | 12 | New Giza Phase 01 |  | 121 | El Hegaz Square Bridge
85 | El Sewedy Univeristy B |  | 122 | Ring Road Extension | 122 | Ring Road Extension |  |  |  | 123 | Marina Inland Marassi Pkg 162 | 12 | New Giza Phase 01 |  | 122 | Ring Road Extension
85 | El Sewedy Univeristy C |  | 123 | Marassi Marina Infrastructure Pkg 163 | 123 | Marina Inland Marassi Pkg 162 |  |  |  | 123 | Marassi Marina Infrastructure Pkg 163 | 12 | New Giza Phase 01 |  | 123 | Marina Inland Marassi Pkg 162
85 | El Sewedy Univeristy |  | 123 | Marina Inland Marassi Pkg 162 | 123 | Marassi Marina Infrastructure Pkg 163 |  |  |  | 1900-05-03 | Sultana Malek Restoration | 12 | New Giza Phase 01 |  | 123 | Marassi Marina Infrastructure Pkg 163
86 | El Sokhna Tunnel L&L |  | 124 | Sultana Malek Restoration | 124 | Sultana Malek Restoration |  |  |  | 125 | Lekela 250MW Wind Farm | 12 | New Giza Phase 01 |  | 124 | Sultana Malek Restoration
88 | R05 Residential District Z1 | & Z2 | 125 | Lekela 250MW Wind Farm | 125 | Lekela 250MW Wind Farm |  |  |  | 126 | New Giza Hospital | 12 | New Giza Phase 01 |  | 125 | Lekela 250MW Wind Farm
89 | Abu Sultan Bridge 02 Greenho | use | 126 | New Giza Hospital | 126 | New Giza Hospital |  |  |  | 127 | Kayan Landscape | 12 | New Giza Phase 01 |  | 126 | New Giza Hospital
90 | El Sokhna Tunnel 02 |  | 127 | Kayan Landscape | 127 | Kayan Landscape |  |  |  | 128 | Abbas Akkad Bridge | 12 | New Giza Phase 01 |  | 127 | Kayan Landscape
91 | El Awsty Middle Tunnel L&L |  | 128 | Abbas Akkad Bridge | 128 | Abbas Akkad Bridge |  |  |  | 129 | El Asher Men Ramadan Bridge | 12 | New Giza Phase 01 |  | 128 | Abbas Akkad Bridge
92 | Sodic Eastown EDNC A |  | 129 | El Asher Men Ramadan Bridge | 129 | El Asher Men Ramadan Bridge |  |  |  | 130 | Kafr Shokr Bridge | 12 | New Giza Phase 01 |  | 129 | El Asher Men Ramadan Bridge
92 | Sodic Eastown EDNC B |  | 130 | Kafr Shokr Bridge | 130 | Kafr Shokr Bridge |  |  |  | 131 | Al Shorouk Bridge (LRT) | 12 | New Giza Phase 01 |  | 130 | Kafr Shokr Bridge
92 | Sodic Eastown EDNC C |  | 131 | Al Shorouk Bridge (LRT) | 131 | Al Shorouk Bridge (LRT) |  |  |  | 132 | Ring Road El Marg | 12 | New Giza Phase 01 |  | 131 | Al Shorouk Bridge (LRT)
92 | Sodic Eastown EDNC |  | 132 | Ring Road El Marg | 132 | Ring Road El Marg |  |  |  | 133 | GOV2 Infra | 12 | New Giza Phase 01 |  | 132 | Ring Road El Marg
93 | Marassi Civic Center Pkg 144 | A | 133 | GOV2 Infra | 133 | GOV2 Infra |  |  |  | 134 | Cairo Alex Railroad | 12 | New Giza Phase 01 |  | 133 | GOV2 Infra
93 | Marassi Civic Center Pkg 144 | B | 134 | Cairo Alex Railroad | 134 | Cairo Alex Railroad |  |  |  | 135 | Hassan El Mamoun Bridge | 12 | New Giza Phase 01 |  | 134 | Cairo Alex Railroad
93 | Marassi Civic Center Pkg 144 | C | 135 | Hassan El Mamoun Bridge | 135 | Hassan El Mamoun Bridge |  |  |  | 136 | Sherouk Bridge L&L | 12 | New Giza Phase 01 |  | 135 | Hassan El Mamoun Bridge
93 | Marassi Civic Center Pkg 144 |  | 136 | Sherouk Bridge L&L | 136 | Sherouk Bridge L&L |  |  |  | 137 | Ora Zed Park 1B Pkgs A&D | 12 | New Giza Phase 01 |  | 136 | Sherouk Bridge L&L
93 | Marassi Civic Center Pkg 144 | D | 137 | Ora Zed Park 1B Pkgs A&D | 137 | Ora Zed Park 1B Pkgs A&D |  |  |  | 138 | Kattameya Creeks | 12 | New Giza Phase 01 |  | 137 | Ora Zed Park 1B Pkgs A&D
94 | DPW Sokhna Dubai Port |  | 138 | Kattameya Creeks | 138 | Kattameya Creeks |  |  |  | 139 | Mansoura University Faculty of Medicine | 12 | New Giza Phase 01 |  | 138 | Kattameya Creeks
95 | Slope Stablization PKG 101 |  | 139 | Mansoura University Faculty of Medicine | 139 | Mansoura University Faculty of Medicine |  |  |  | 140 | Diplomatic District - Infra | 12 | New Giza Phase 01 |  | 139 | Mansoura University Faculty of Medicine
96 | Elco Steel Substation |  | 140 | Diplomatic District - Infra | 140 | Diplomatic District - Infra |  |  |  | 141 | El Sewedy CFC HQ Internal Finishing | 12 | New Giza Phase 01 |  | 140 | Diplomatic District - Infra
97 | Sewab Greenhouse Tunnel |  | 141 | El Sewedy CFC HQ Internal Finishing | 141 | El Sewedy CFC HQ Internal Finishing |  |  |  | 142 | Lagoon Discharge Pkg 178 | 12 | New Giza Phase 01 |  | 141 | El Sewedy CFC HQ Internal Finishing
98 | Mivida Irrigation Treatment | Plant Pkg 140 | 142 | Lagoon Discharge Pkg 178 | 142 | Lagoon Discharge Pkg 178 |  |  |  | 143 | El Khatatba Bridge | 12 | New Giza Phase 01 |  | 142 | Lagoon Discharge Pkg 178
98 | Mivida Irrigation Treatment | Plant Pkg 140 | 143 | El Khatatba Bridge | 143 | El Khatatba Bridge |  |  |  | 144 | EGAT Pelletizing Plant | 12 | New Giza Phase 01 |  | 143 | El Khatatba Bridge
99 | Multi Sports Hall A |  | 144 | EGAT Pelletizing Plant | 144 | EGAT Pelletizing Plant |  |  |  | 145 | Sokhna Port Expansion | 12 | New Giza Phase 01 |  | 144 | EGAT Pelletizing Plant
99 | Multi Sports Hall B |  | 145 | Sokhna Port Expansion | 145 | Sokhna Port Expansion |  |  |  | 146 | Waldorf Astoria Mock Up Room | 12 | New Giza Phase 01 |  | 145 | Sokhna Port Expansion
99 | Multi Sports Hall C |  | 146 | Waldorf Astoria Mock Up Room | 146 | Waldorf Astoria Mock Up Room |  |  |  | 147 | MDF Factory | 12 | New Giza Phase 01 |  | 147 | MDF Factory
99 | Multi Sports Hall |  | 147 | MDF Factory | 147 | MDF Factory |  |  |  | 148 | Olympic City L&L | 12 | New Giza Phase 01 |  | 148 | Olympic City L&L
100 | Emergency Bridge |  | 148 | Olympic City L&L | 148 | Olympic City L&L |  |  |  | 149 | Kemet Building | 12 | New Giza Phase 01 |  | 149 | Kemet Building
101 | Pyramid El Remayah Tunnel |  | 149 | Kemet Building | 149 | Kemet Building |  |  |  | 000x | Uptown Soil Stabilization Pkg 32 | 12 | New Giza Phase 01 |  | 000x | Point 90 New Cairo Mall
102 | EGAT |  | 000x | Alegria DP Port | 000x | Alegria DP Port |  |  |  | 000x | Marassi Bridges Pkg 37 | 12 | New Giza Phase 01 |  | 000x | Marassi Bridges Pkg 37
103 | Abou Ghazala Bridge Ramp L&L |  | 000x | Alexandria Bridges | 000x | Alexandria Bridges |  |  |  | 000x | Marassi Golf Maintance Building Pkg 58 | 12 | New Giza Phase 01 |  | 000x | Marassi Golf Maintance Building Pkg 58
104 | Mohamed Ali Fahmy Ramps L&L |  | 000x | Allegria Club House | 000x | Allegria Club House |  |  |  | 000x | Limak TB2 Cairo Airport Terminal |  |  |  | 000x | Uptown Soil Stabilization Pkg 32
105 | El Mosheer Bridge Abu Zaied | Khdr L&L | 000x | Alstom-French Station | 000x | Alstom-French Station |  |  |  | 000x | Point 90 New Cairo Mall | 13 | Hyper Solimanya |  | 000x | Ismailia Bridge L&L
106 | Ora Zed Park L&L |  | 000x | Autoville Strip Mall | 000x | Autoville Strip Mall |  |  |  | 000x | Hyper Matrouh | 13 | Hyper Solimanya |  | 000x | El Obour Bridge B2
107 | DoubleTree Mangroovy El Goun | a Hotel | 000x | Dubai Port Sokhna Basin 1 | 000x | Batch Plant |  |  |  | 000x | Ismailia Bridge L&L | 13 | Hyper Solimanya |  | 000x | Autoville Strip Mall
108 | Baron Palace Fence |  | 000x | El Alameen Bridge L&L | 000x | Dubai Port Sokhna Basin 1 |  |  |  | 000x | Autoville Strip Mall | 13 | Hyper Solimanya |  | 000x | Uptown Service Buildings Pkg 17A
109 | Safeer Square Bridge |  | 000x | El Asher Bridge | 000x | El Alameen Bridge L&L |  |  |  | 000x | El Obour Bridge B2 | 13 | Hyper Solimanya |  | 000x | Sodic West Town Hub
110 | Suez Road Tunnel Res L&L |  | 000x | El Asher of Ramadan Bridge L&L | 000x | El Asher Bridge |  |  |  | Rolli | ng Mill Plant 3 | 13 | Hyper Solimanya |  | 000x | Dubai Port Sokhna Basin 1
111 | HyperOne Zayed Extention |  | 000x | El Mahala Bridge | 000x | El Asher of Ramadan Bridge L&L |  |  |  | DP Wo | rld Sokhna - Concrete | 13 | Hyper Solimanya |  | 000x | Alexandria Bridges
112 | IKEA Extention MoA |  | 000x | El Mostakbal Bridge L&L | 000x | El Mahala Bridge |  |  |  | DP Wo | rld Sokhna - Infra | 13 | Hyper Solimanya |  | 000x | El Mahala Bridge
113 | CFC Podium II A |  | 000x | El Obour Bridge B2 | 000x | El Mostakbal Bridge L&L |  |  |  | DP Wo | rld Sokhna - Interlock | 13 | Hyper Solimanya |  | 000x | El Wahat Bridge
113 | CFC Podium II B |  | 000x | El Shone Bridge | 000x | El Obour Bridge B2 |  |  |  | 000x | Alexandria Bridges | 13 | Hyper Solimanya |  | 000x | El Wahat Tunnel
113 | CFC Podium II C |  | 000x | El Wahat Bridge | 000x | El Shone Bridge |  |  |  | 000x | Uptown Service Buildings Pkg 17A | 13 | Hyper Solimanya |  | 0xxx | AL-Asmarat
113 | CFC Podium II |  | 000x | El Wahat Tunnel | 000x | El Wahat Bridge |  |  |  | 000x | El Mahala Bridge | 13 | Hyper Solimanya |  | 000x | Alegria DP Port
114 | Mostafa Kamel Bridge L&L |  | 000x | EMEC | 000x | El Wahat Tunnel |  |  |  | 000x | El Wahat Tunnel | 13 | Hyper Solimanya |  | 000x | El Alameen Bridge L&L
115 | Josef Tito Bridge L&L |  | 000x | Hyper Matrouh | 000x | EMEC |  |  |  | SODIC | West town Hub | 13 | Hyper Solimanya |  | 000x | El Asher of Ramadan Bridge L&L
116 | Espiko Bridge L&L |  | 000x | Ismailia Bridge L&L | 000x | FM85 | 1900-01-05 | Marassi Civic Center Pkg 45 |  | 000x | EMEC | 13 | Hyper Solimanya |  | 000x | EMEC
117 | El Gabal El Asfr Tunnel L&L |  | 000x | Logestica Phase 01 | 000x | Hyper Matrouh | 8 | Al Oula Infra |  | 000x | Twin Towers | 13 | Hyper Solimanya |  | 000x | Ismailia Bridge L&L
118 | MR3 Bridge L&L |  | 000x | Logestica Phase 02 | 000x | Ismailia Bridge L&L | 1900-01-11 | New Giza Phase 01 |  | SODIC | MV Cables | 13 | Hyper Solimanya |  | 000x | Logestica Phase 01
119 | El Sewedy Univeristy 2 Phase | 2:00 | 000x | Logestica Phase 03 | 000x | Logestica 01 | 13 | Hyper Solimanya A |  | 000x | Alstom-French Station | 13 | Hyper Solimanya |  | 000x | Logestica Phase 02
119 | El Sewedy Univeristy 2 Phase | 2 B | 000x | Marassi Bridges Pkg 37 | 000x | Logestica 02 | 13 | Hyper Solimanya B |  | 000x | Alegria DP Port | 13 | Hyper Solimanya |  | 000x | Logestica Phase 03
119 | El Sewedy Univeristy 2 Phase | 2 C | 000x | Marassi Golf Maintance Building Pkg 58 | 000x | Marassi Bridges Pkg 37 | 13 | Hyper Solimanya C |  | 000x | Allegria Club House | 13 | Hyper Solimanya |  | 000x | Sodic MV Cables
119 | El Sewedy Univeristy 2 Phase | 2 | 000x | Point 90 New Cairo Mall | 000x | Marassi Golf Maintance Building Pkg 58 | 13 | Hyper Solimanya |  | 000x | Autoville Strip Mall | 13 | Hyper Solimanya |  | 000x | Limak TB2 Cairo Airport Terminal
120 | Mehwar El Salam Axis L&L |  | 000x | Sodic MV Cables | 000x | Point 90 New Cairo Mall | 19 | Ismailia Bridges |  | 000x | Batch Plant | 13 | Hyper Solimanya |  | 000x | Twin Towers
121 | El Hegaz Square Bridge |  | 000x | Sodic West Town Hub | 000x | Sodic MV Cables | 23 | Maxium Mall A |  | 000x | Dubai Port Sokhna Basin 1 | 13 | Hyper Solimanya |  | 000x | Aeon Towers Chiller Building
122 | Ring Road Extension |  | 000x | Limak TB2 Cairo Airport Terminal | 000x | Sodic West Town Hub | 23 | Maxium Mall B |  | 000x | El Alameen Bridge L&L | 13 | Hyper Solimanya |  | 0xxx | Electric Train LRT
123 | Marina Inland Marassi Pkg 16 | 2 | 000x | Twin Towers | 000x | Limak TB2 Cairo Airport Terminal | 23 | Maxium Mall |  | 000x | El Asher Bridge | 13 | Hyper Solimanya |  | 0xxx | Sea Shell Playa
123 | Marassi Marina Infrastructur | e Pkg 163 | 000x | Uptown Soil Stabilization Pkg 32 | 000x | Twin Towers | 28 | Ataqqa Power Plant |  | 000x | El Asher of Ramadan Bridge L&L | 13 | Hyper Solimanya
124 | Sultana Malek Restoration |  | 000x | Uptown Service Buildings Pkg 17A | 000x | Uptown Soil Stabilization Pkg 32 | 30 | Mall of Egypt Bridge |  | 000x | El Mahala Bridge | 13 | Hyper Solimanya
125 | Lekela 250MW Wind Farm |  | 0xxx | Electric Train LRT | 000x | Uptown Service Buildings Pkg 17A | 1900-01-30 | Marassi Tanks PKG 22 |  | 000x | El Mostakbal Bridge L&L | 13 | Hyper Solimanya
126 | New Giza Hospital |  | 0xxx | Sea Shell Playa | 0xxx | Electric Train LRT | 32 | Sodic Club House A |  | 000x | El Obour Bridge B2 | 13 | Hyper Solimanya
127 | Kayan Landscape |  | 0xxx | El Asmarat | 0xxx | Sea Shell Playa | 32 | Sodic Club House B |  | 000x | El Shone Bridge | 13 | Hyper Solimanya
128 | Abbas Akkad Bridge |  | 000x | Aeon Towers Chiller Building |  |  | 32 | Sodic Club House C |  | 000x | El Wahat Bridge | 13 | Hyper Solimanya
129 | El Asher Men Ramadan Bridge | [5 empty] | 32 | Sodic Club House D |  | 000x | EMEC | 13 | Hyper Solimanya
130 | Kafr Shokr Bridge | [5 empty] | 32 | Sodic Club House E |  | 000x | Hyper Matrouh | 13 | Hyper Solimanya
131 | Al Shorouk Bridge (LRT) | [5 empty] | 32 | Sodic Club House F |  | 000x | Ismailia Bridge L&L | 13 | Hyper Solimanya
132 | Ring Road El Marg | [5 empty] | 32 | Sodic Club House |  | 000x | Logestica Phase 01 | 13 | Hyper Solimanya
133 | GOV2 Infra | [5 empty] | 1900-02-01 | Montazah Hotel Sharm |  | 000x | Logestica Phase 02 | 13 | Hyper Solimanya
134 | Cairo Alex Railroad | [5 empty] | 34 | Uptown Cairo Pkg 53 |  | 000x | Logestica Phase 03 | 13 | Hyper Solimanya
135 | Hassan El Mamoun Bridge | [5 empty] | 1900-02-03 | Bani Suif Power Plant 1021 |  | 000x | Marassi Bridges Pkg 37 | 13 | Hyper Solimanya
136 | Sherouk Bridge L&L | [5 empty] | 1900-02-05 | New Giza Phase 02 |  | 000x | Marassi Golf Maintance Building Pkg 58 | 13 | Hyper Solimanya
137 | Ora Zed Park 1B Pkgs A&D | [5 empty] | 1900-02-07 | JICA Wind Farm Gabal El Zeet |  | 000x | Point 90 New Cairo Mall | 13 | Hyper Solimanya
138 | Kattameya Creeks | [5 empty] | 40 | El Mostathmereen Mokatam Sub | station | 000x | Sodic MV Cables | 13 | Hyper Solimanya
139 | Mansoura University Faculty | of Medicine |  |  |  |  | 41 | Levana UpTown PKG 62 |  | 000x | Sodic West Town Hub | 13 | Hyper Solimanya
140 | Diplomatic District - Infra | [5 empty] | 45 | Kayan 110 A |  | 000x | Uptown Soil Stabilization Pkg 32
141 | El Sewedy CFC HQ Internal Fi | nishing |  |  |  |  | 45 | Kayan 110 B |  | 0xxx | Electric Train LRT | 19 | Ismailia Bridges
142 | Lagoon Discharge Pkg 178 | [5 empty] | 45 | Kayan 110 C |  | 0xxx | Sea Shell Playa | 19 | Ismailia Bridges
143 | El Khatatba Bridge | [5 empty] | 45 | Kayan 110 |  | 0xxx | AL-Asmarat | 19 | Ismailia Bridges
144 | EGAT Pelletizing Plant | [5 empty] | 46 | El Amal Bridge |  |  |  | 19 | Ismailia Bridges
145 | Sokhna Port Expansion | [5 empty] | 47 | Bani Suif Cement |  |  |  | 19 | Ismailia Bridges
147 | MDF Factory | [5 empty] | 48 | New Giza Wall |  |  |  | 19 | Ismailia Bridges
148 | Olympic City L&L | [5 empty] | 51 | Tamey El Amdid Mansora Power | Station |  |  | 19 | Ismailia Bridges
149 | Kemet Building | [5 empty] | 52 | Ismailia Substation 500-220 |  |  |  | 19 | Ismailia Bridges
000x | Point 90 New Cairo Mall A | [5 empty] | 53 | El Amal Bridge L&L |  |  |  | 19 | Ismailia Bridges
000x | Point 90 New Cairo Mall B | [5 empty] | 1900-02-22 | FIEM Wind Farm Gabal El Zeet |  |  |  | 19 | Ismailia Bridges
000x | Point 90 New Cairo Mall | [5 empty] | 1900-02-23 | KFW Wind Farm Gabal El Zeet |  |  |  | 19 | Ismailia Bridges
000x | Marassi Bridges Pkg 37 | [5 empty] | 58 | Marassi Tank PKG 107 A |  |  |  | 19 | Ismailia Bridges
000x | Marassi Golf Maintance Build | ing Pkg 58 |  |  |  |  | 58 | Marassi Tank PKG 107 B |  |  |  | 19 | Ismailia Bridges
000x | Uptown Soil Stabilization Pk | g 32 |  |  |  |  | 58 | Marassi Tank PKG 107 C |  |  |  | 19 | Ismailia Bridges
000x | Ismailia Bridge L&L | [5 empty] | 58 | Marassi Tank PKG 107 |  |  |  | 19 | Ismailia Bridges
000x | El Obour Bridge B2 | [5 empty] | 59 | Ben Zayed New Capital Tunnel |  |  |  | 19 | Ismailia Bridges
000x | Autoville Strip Mall | [5 empty] | 60 | Ministries Buildings A |  |  |  | 19 | Ismailia Bridges
000x | Uptown Service Buildings Pkg | 17A |  |  |  |  | 60 | Ministries Buildings B |  |  |  | 19 | Ismailia Bridges
000x | Sodic West Town Hub | [5 empty] | 60 | Ministries Buildings C |  |  |  | 19 | Ismailia Bridges
000x | Dubai Port Sokhna Basin 1 | [5 empty] | 60 | Ministries Buildings D |  |  |  | 19 | Ismailia Bridges
000x | Alexandria Bridges | [5 empty] | 60 | Ministries Buildings |  |  |  | 19 | Ismailia Bridges
000x | El Mahala Bridge | [5 empty] | 61 | Bani Suif Substation |  |  |  | 19 | Ismailia Bridges
000x | El Wahat Bridge | [5 empty] | 63 | Royal City Mall A |  |  |  | 19 | Ismailia Bridges
000x | El Wahat Tunnel | [5 empty] | 63 | Royal City Mall B |  |  |  | 19 | Ismailia Bridges
0xxx | AL-Asmarat | [5 empty] | 63 | Royal City Mall C |  |  |  | 19 | Ismailia Bridges
000x | Alegria DP Port | [5 empty] | 63 | Royal City Mall D |  |  |  | 19 | Ismailia Bridges
000x | El Alameen Bridge L&L | [5 empty] | 63 | Royal City Mall |  |  |  | 19 | Ismailia Bridges
000x | El Asher of Ramadan Bridge L | &L |  |  |  |  | 63 | Royal City Mall E |  |  |  | 19 | Ismailia Bridges
000x | EMEC | [5 empty] | 64 | Shoubra Banha Bridge L&L |  |  |  | 19 | Ismailia Bridges
000x | Ismailia Bridge L&L | [5 empty] | 65 | SLP Logistic Center PI Park | Sewedy Stores A |  |  | 19 | Ismailia Bridges
000x | Logestica Phase 01 | [5 empty] | 65 | SLP Logistic Center PI Park | Sewedy Stores B |  |  | 19 | Ismailia Bridges
000x | Logestica Phase 02 | [5 empty] | 65 | SLP Logistic Center PI Park | Sewedy Stores C |  |  | 19 | Ismailia Bridges
000x | Logestica Phase 03 | [5 empty] | 65 | SLP Logistic Center PI Park | Sewedy Stores |  |  | 19 | Ismailia Bridges
000x | Sodic MV Cables | [5 empty] | 66 | El Mostakbal Bridge L&L |  |  |  | 19 | Ismailia Bridges
000x | Limak TB2 Cairo Airport Term | inal |  |  |  |  | 68 | Kayan Wall L&L |  |  |  | 19 | Ismailia Bridges
000x | Twin Towers | [5 empty] | 69 | Elco Suez Steel Rolling Mill | Plant 3 |  |  | 19 | Ismailia Bridges
000x | Aeon Towers Chiller Building | [5 empty] | 70 | Hyper El Temsah A |  |  |  | 19 | Ismailia Bridges
0xxx | Electric Train LRT | [5 empty] | 70 | Hyper El Temsah B |  |  |  | 19 | Ismailia Bridges
0xxx | Sea Shell Playa | [5 empty] | 70 | Hyper El Temsah C |  |  |  | 19 | Ismailia Bridges
[7 empty] | 70 | Hyper El Temsah |  |  |  | 19 | Ismailia Bridges
Subto | tal | [5 empty] | 71 | Marassi Bridge Pkg 117 |  |  |  | 19 | Ismailia Bridges
[7 empty] | 72 | Siemens Power Station |  |  |  | 19 | Ismailia Bridges
[7 empty] | 73 | Uptown FM85 Pkg 85 |  |  |  | 19 | Ismailia Bridges
[7 empty] | 74 | El Sokhna Tunnel 01 |  |  |  | 19 | Ismailia Bridges
[7 empty] | 75 | Abu Sultan Bridge 01 |  |  |  | 19 | Ismailia Bridges
[7 empty] | 76 | Mintra Factory |  |  |  | 19 | Ismailia Bridges
[7 empty] | 77 | King Farouk Restoration |  |  |  | 19 | Ismailia Bridges
[7 empty] | 78 | Mohamed Ali Palace |  |  |  | 19 | Ismailia Bridges
[7 empty] | 79 | Nefisha Bridge |  |  |  | 19 | Ismailia Bridges
[7 empty] | 80 | Fish Market A |  |  |  | 19 | Ismailia Bridges
[7 empty] | 80 | Fish Market B |  |  |  | 19 | Ismailia Bridges
[7 empty] | 80 | Fish Market C |  |  |  | 19 | Ismailia Bridges
[7 empty] | 80 | Fish Market D |  |  |  | 19 | Ismailia Bridges
[7 empty] | 80 | Fish Market |  |  |  | 19 | Ismailia Bridges
[7 empty] | 81 | Al Jazi Mall
[7 empty] | 83 | Benban Aswan Alcazars Solar | Park |  |  | 23 | Maxium Mall
[7 empty] | 84 | El Alameen Roads Earth Works |  |  |  | 23 | Maxium Mall
[7 empty] | 85 | El Sewedy Univeristy A |  |  |  | 23 | Maxium Mall
[7 empty] | 85 | El Sewedy Univeristy B |  |  |  | 23 | Maxium Mall
[7 empty] | 85 | El Sewedy Univeristy C |  |  |  | 23 | Maxium Mall
[7 empty] | 85 | El Sewedy Univeristy |  |  |  | 23 | Maxium Mall
[7 empty] | 86 | El Sokhna Tunnel L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 88 | R05 Residential District Z1 | & Z2 |  |  | 23 | Maxium Mall
[7 empty] | 89 | Abu Sultan Bridge 02 Greenho | use |  |  | 23 | Maxium Mall
[7 empty] | 90 | El Sokhna Tunnel 02 |  |  |  | 23 | Maxium Mall
[7 empty] | 91 | El Awsty Middle Tunnel L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 92 | Sodic Eastown EDNC A |  |  |  | 23 | Maxium Mall
[7 empty] | 92 | Sodic Eastown EDNC B |  |  |  | 23 | Maxium Mall
[7 empty] | 92 | Sodic Eastown EDNC C |  |  |  | 23 | Maxium Mall
[7 empty] | 92 | Sodic Eastown EDNC |  |  |  | 23 | Maxium Mall
[7 empty] | 93 | Marassi Civic Center Pkg 144 | A |  |  | 23 | Maxium Mall
[7 empty] | 93 | Marassi Civic Center Pkg 144 | B |  |  | 23 | Maxium Mall
[7 empty] | 93 | Marassi Civic Center Pkg 144 | C |  |  | 23 | Maxium Mall
[7 empty] | 93 | Marassi Civic Center Pkg 144 |  |  |  | 23 | Maxium Mall
[7 empty] | 93 | Marassi Civic Center Pkg 144 | D |  |  | 23 | Maxium Mall
[7 empty] | 94 | DPW Sokhna Dubai Port |  |  |  | 23 | Maxium Mall
[7 empty] | 95 | Slope Stablization PKG 101 |  |  |  | 23 | Maxium Mall
[7 empty] | 96 | Elco Steel Substation |  |  |  | 23 | Maxium Mall
[7 empty] | 97 | Sewab Greenhouse Tunnel |  |  |  | 23 | Maxium Mall
[7 empty] | 98 | Mivida Irrigation Treatment | Plant Pkg 140 |  |  | 23 | Maxium Mall
[7 empty] | 98 | Mivida Irrigation Treatment | Plant Pkg 140 |  |  | 23 | Maxium Mall
[7 empty] | 99 | Multi Sports Hall A |  |  |  | 23 | Maxium Mall
[7 empty] | 99 | Multi Sports Hall B |  |  |  | 23 | Maxium Mall
[7 empty] | 99 | Multi Sports Hall C |  |  |  | 23 | Maxium Mall
[7 empty] | 99 | Multi Sports Hall |  |  |  | 23 | Maxium Mall
[7 empty] | 100 | Emergency Bridge |  |  |  | 23 | Maxium Mall
[7 empty] | 101 | Pyramid El Remayah Tunnel |  |  |  | 23 | Maxium Mall
[7 empty] | 102 | EGAT |  |  |  | 23 | Maxium Mall
[7 empty] | 103 | Abou Ghazala Bridge Ramp L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 104 | Mohamed Ali Fahmy Ramps L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 105 | El Mosheer Bridge Abu Zaied | Khdr L&L |  |  | 23 | Maxium Mall
[7 empty] | 106 | Ora Zed Park L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 107 | DoubleTree Mangroovy El Goun | a Hotel |  |  | 23 | Maxium Mall
[7 empty] | 108 | Baron Palace Fence |  |  |  | 23 | Maxium Mall
[7 empty] | 109 | Safeer Square Bridge |  |  |  | 23 | Maxium Mall
[7 empty] | 110 | Suez Road Tunnel Res L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 111 | HyperOne Zayed Extention |  |  |  | 23 | Maxium Mall
[7 empty] | 112 | IKEA Extention MoA |  |  |  | 23 | Maxium Mall
[7 empty] | 113 | CFC Podium II A |  |  |  | 23 | Maxium Mall
[7 empty] | 113 | CFC Podium II B |  |  |  | 23 | Maxium Mall
[7 empty] | 113 | CFC Podium II C |  |  |  | 23 | Maxium Mall
[7 empty] | 113 | CFC Podium II |  |  |  | 23 | Maxium Mall
[7 empty] | 114 | Mostafa Kamel Bridge L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 115 | Josef Tito Bridge L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 116 | Espiko Bridge L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 117 | El Gabal El Asfr Tunnel L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 118 | MR3 Bridge L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 119 | El Sewedy Univeristy 2 Phase | 2:00 |  |  | 23 | Maxium Mall
[7 empty] | 119 | El Sewedy Univeristy 2 Phase | 2 B |  |  | 23 | Maxium Mall
[7 empty] | 119 | El Sewedy Univeristy 2 Phase | 2 C |  |  | 23 | Maxium Mall
[7 empty] | 119 | El Sewedy Univeristy 2 Phase | 2 |  |  | 23 | Maxium Mall
[7 empty] | 120 | Mehwar El Salam Axis L&L |  |  |  | 23 | Maxium Mall
[7 empty] | 121 | El Hegaz Square Bridge |  |  |  | 23 | Maxium Mall
[7 empty] | 122 | Ring Road Extension |  |  |  | 23 | Maxium Mall
[7 empty] | 123 | Marina Inland Marassi Pkg 16 | 2 |  |  | 23 | Maxium Mall
[7 empty] | 123 | Marassi Marina Infrastructur | e Pkg 163 |  |  | 23 | Maxium Mall
[7 empty] | 124 | Sultana Malek Restoration |  |  |  | 23 | Maxium Mall
[7 empty] | 125 | Lekela 250MW Wind Farm |  |  |  | 23 | Maxium Mall
[7 empty] | 126 | New Giza Hospital
[7 empty] | 127 | Kayan Landscape |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 128 | Abbas Akkad Bridge |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 129 | El Asher Men Ramadan Bridge |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 130 | Kafr Shokr Bridge |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 131 | Al Shorouk Bridge (LRT) |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 132 | Ring Road El Marg |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 133 | GOV2 Infra |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 134 | Cairo Alex Railroad |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 135 | Hassan El Mamoun Bridge |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 136 | Sherouk Bridge L&L |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 137 | Ora Zed Park 1B Pkgs A&D |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 138 | Kattameya Creeks |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 139 | Mansoura University Faculty | of Medicine |  |  | 28 | Ataqqa Power Plant
[7 empty] | 140 | Diplomatic District - Infra |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 141 | El Sewedy CFC HQ Internal Fi | nishing |  |  | 28 | Ataqqa Power Plant
[7 empty] | 142 | Lagoon Discharge Pkg 178 |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 143 | El Khatatba Bridge |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 144 | EGAT Pelletizing Plant |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 145 | Sokhna Port Expansion |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 147 | MDF Factory |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 148 | Olympic City L&L |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 149 | Kemet Building |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 000x | Point 90 New Cairo Mall A |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 000x | Point 90 New Cairo Mall B |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 000x | Point 90 New Cairo Mall |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 000x | Marassi Bridges Pkg 37 |  |  |  | 28 | Ataqqa Power Plant
[7 empty] | 000x | Marassi Golf Maintance Build | ing Pkg 58 |  |  | 28 | Ataqqa Power Plant
[7 empty] | 000x | Uptown Soil Stabilization Pk | g 32 |  |  | 28 | Ataqqa Power Plant
[7 empty] | 000x | Ismailia Bridge L&L
[7 empty] | 000x | El Obour Bridge B2 |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Autoville Strip Mall |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Uptown Service Buildings Pkg | 17A |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Sodic West Town Hub |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Dubai Port Sokhna Basin 1 |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Alexandria Bridges |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | El Mahala Bridge |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | El Wahat Bridge |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | El Wahat Tunnel |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 0xxx | AL-Asmarat |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Alegria DP Port |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | El Alameen Bridge L&L |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | El Asher of Ramadan Bridge L | &L |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | EMEC |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Ismailia Bridge L&L |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Logestica Phase 01 |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Logestica Phase 02 |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Logestica Phase 03 |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Sodic MV Cables |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Limak TB2 Cairo Airport Term | inal |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Twin Towers |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 000x | Aeon Towers Chiller Building |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 0xxx | Electric Train LRT |  |  |  | 30 | Mall of Egypt Bridge
[7 empty] | 0xxx | Sea Shell Playa |  |  |  | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 30 | Mall of Egypt Bridge
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 31 | Marassi Tanks PKG 22
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 32 | Sodic Club House
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 34 | Uptown Cairo Pkg 53
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 35 | Bani Suif Power Plant 1021
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 37 | New Giza Phase 02
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 39 | JICA Wind Farm Gabal El Zeet | t
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 40 | El Mostathmereen Mokatam Substation | bstation
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 41 | Levana UpTown Pkg 62
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 45 | Kayan 110
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 46 | El Amal Bridge
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 47 | Bani Suif Cement
[12 empty] | 48 | New Giza Wall
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 51 | Tamey El Amdid Mansora Power Station | r Station
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 52 | Ismailia Substation 500-220
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 53 | El Amal Bridge L&L
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 54 | FIEM Wind Farm Gabal El Zeet | t
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 55 | KFW Wind Farm Gabal El Zeet
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 58 | Marassi Tank PKG 107
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 59 | Ben Zayed New Capital Tunnel | l
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 60 | Ministries Buildings
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 61 | Bani Suif Substation
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 63 | Royal City Mall
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 64 | Shoubra Banha Bridge L&L
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 65 | SLP Logistic Center PI Park Sewedy Stores | Sewedy Stores
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 66 | El Mostakbal Bridge L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 68 | Kayan Wall L&L
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 69 | Elco Suez Steel Rolling Mill Plant 3 | l Plant 3
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 70 | Hyper El Temsah
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 71 | Marassi Bridge Pkg 117
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 72 | Siemens Power Station
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 73 | Uptown FM85 Pkg 85
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 74 | El Sokhna Tunnel 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 75 | Abu Sultan Bridge 01
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 76 | Mintra Factory
[12 empty] | 77 | King Farouk Restoration
[12 empty] | 77 | King Farouk Restoration
[12 empty] | 77 | King Farouk Restoration
[12 empty] | 77 | King Farouk Restoration
[12 empty] | 77 | King Farouk Restoration
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 78 | Mohamed Ali Palace
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 79 | Nefisha Bridge
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 80 | Fish Market
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 81 | Al Jazi Mall
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 83 | Benban Aswan Alcazars Solar Park | Park
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 84 | El Alameen Roads Earth Works | s
[12 empty] | 85 | El Sewedy Univeristy
[12 empty] | 85 | El Sewedy Univeristy
[12 empty] | 85 | El Sewedy Univeristy
[12 empty] | 85 | El Sewedy Univeristy
[12 empty] | 85 | El Sewedy Univeristy
[12 empty] | 85 | El Sewedy Univeristy
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 86 | El Sokhna Tunnel L&L
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 88 | R05 Residential District Z1 & Z2 | & Z2
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 89 | Abu Sultan Bridge 02 Greenhouse | ouse
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 90 | El Sokhna Tunnel 02
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 91 | El Awsty Middle Tunnel L&L
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 92 | Sodic Eastown EDNC
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 93 | Marassi Civic Center Pkg 144 | 4
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 94 | DPW Sokhna Dubai Port
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 95 | Slope Stablization PKG 101
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 96 | Elco Steel Substation
[12 empty] | 97 | Sewab Greenhouse Tunnel
[12 empty] | 97 | Sewab Greenhouse Tunnel
[12 empty] | 97 | Sewab Greenhouse Tunnel
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 98 | Mivida Irrigation Treatment Plant Pkg 140 | Plant Pkg 140
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 99 | Multi Sports Hall
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 100 | Emergency Bridge
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 101 | Pyramid El Remayah Tunnel
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 102 | EGAT
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 103 | Abou Ghazala Bridge Ramp L&L | L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 104 | Mohamed Ali Fahmy Ramps L&L
[12 empty] | 105 | El Mosheer Bridge Abu Zaied Khdr L&L | Khdr L&L
[12 empty] | 105 | El Mosheer Bridge Abu Zaied Khdr L&L | Khdr L&L
[12 empty] | 105 | El Mosheer Bridge Abu Zaied Khdr L&L | Khdr L&L
[12 empty] | 105 | El Mosheer Bridge Abu Zaied Khdr L&L | Khdr L&L
[12 empty] | 105 | El Mosheer Bridge Abu Zaied Khdr L&L | Khdr L&L
[12 empty] | 105 | El Mosheer Bridge Abu Zaied Khdr L&L | Khdr L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 106 | Ora Zed Park L&L
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 107 | DoubleTree Mangroovy El Gouna Hotel | na Hotel
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 108 | Baron Palace Fence
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 109 | Safeer Square Bridge
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 110 | Suez Road Tunnel Res L&L
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 111 | HyperOne Zayed Extention
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 112 | IKEA Extention MoA
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 113 | CFC Podium II
[12 empty] | 115 | Josef Tito Bridge L&L
[12 empty] | 115 | Josef Tito Bridge L&L
[12 empty] | 116 | Espiko Bridge L&L
[12 empty] | 116 | Espiko Bridge L&L
[12 empty] | 116 | Espiko Bridge L&L
[12 empty] | 116 | Espiko Bridge L&L
[12 empty] | 116 | Espiko Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 118 | MR3 Bridge L&L
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 119 | El Sewedy Univeristy 2 Phase 2 | e 2
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 120 | Mehwar El Salam Axis L&L
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 121 | El Hegaz Square Bridge
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 122 | Ring Road 1 Maryotyah
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 123 | Marina Inland Marassi Pkg 162 | 62
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 124 | Sultana Malek Restoration
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 125 | Lekela 250MW Wind Farm
[12 empty] | 126 | New Giza Hospital
[12 empty] | 127 | Kayan Landscape
[12 empty] | 127 | Kayan Landscape
[12 empty] | 127 | Kayan Landscape
[12 empty] | 127 | Kayan Landscape
[12 empty] | 127 | Kayan Landscape
[12 empty] | 127 | Kayan Landscape
[12 empty] | 127 | Kayan Landscape
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 128 | Abbas Akkad Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 129 | El Asher Men Ramadan Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 130 | Kafr Shokr Bridge
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 131 | Al Shorouk Bridge (LRT)
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 132 | Ring Road El Marg
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 133 | GOV2 Infra
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 134 | Cairo Alex Railroad
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 135 | Hassan El Mamoun Bridge
[12 empty] | 136 | Sherouk Bridge L&L
[12 empty] | 136 | Sherouk Bridge L&L
[12 empty] | 136 | Sherouk Bridge L&L
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 137 | Ora Zed Park 1B Pkgs A&D
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 138 | Kattameya Creeks
[12 empty] | 139 | Mansoura University Faculty of Medicine | of Medicine
[12 empty] | 139 | Mansoura University Faculty of Medicine | of Medicine
[12 empty] | 140 | Diplomatic District - Infra
[12 empty] | 140 | Diplomatic District - Infra
[12 empty] | 140 | Diplomatic District - Infra
[12 empty] | 140 | Diplomatic District - Infra
[12 empty] | 140 | Diplomatic District - Infra
[12 empty] | 141 | El Sewedy CFC HQ Internal Finishing | inishing
[12 empty] | 141 | El Sewedy CFC HQ Internal Finishing | inishing
[12 empty] | 141 | El Sewedy CFC HQ Internal Finishing | inishing
[12 empty] | 141 | El Sewedy CFC HQ Internal Finishing | inishing
[12 empty] | 141 | El Sewedy CFC HQ Internal Finishing | inishing
[12 empty] | 141 | El Sewedy CFC HQ Internal Finishing | inishing
[12 empty] | 142 | Lagoon Discharge Pkg 178
[12 empty] | 142 | Lagoon Discharge Pkg 178
[12 empty] | 142 | Lagoon Discharge Pkg 178
[12 empty] | 142 | Lagoon Discharge Pkg 178
[12 empty] | 143 | El Khatatba Bridge
[12 empty] | 143 | El Khatatba Bridge
[12 empty] | 144 | EGAT Pelletizing Plant
[12 empty] | 144 | EGAT Pelletizing Plant
[12 empty] | 147 | MDF Factory
[12 empty] | 147 | MDF Factory
[12 empty] | 000x | Aeon Towers Chiller Building | g
[12 empty] | 000x | Aeon Towers Chiller Building | g
[12 empty] | 000x | Aeon Towers Chiller Building | g
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alegria DP Port
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alexandria Bridges
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Alstom-French Station
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | Autoville Strip Mall
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | El Mahala Bridge
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | EMEC
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Logestica 02
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Bridges Pkg 37
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Marassi Golf Maintance Building Pkg 58 | ding Pkg 58
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Uptown Service Buildings Pkg 17A | g 17A
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Point 90 New Cairo Mall
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic MV Cables
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Sodic West Town Hub
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Limak TB2 Cairo Airport Terminal | minal
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Twin Towers
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 000x | Uptown Soil Stabilization Pkg 32 | kg 32
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT
[12 empty] | 0xxx | Electric Train LRT

## 03-Time (hidden)
Project Name | Project Start | Concrete Finish | Project Finish | Concrete Duration | Total Duration | Project Manager | Client
Marassi Civic Center Pkg 45 | 2012-11-13 | 2013-10-13 | 2015-11-13 | 10.9808 | 36 | Eng Hassan Youssef | EMAAR
Al Oula Infra | 2012-02-06 | 2015-06-06 | 2015-06-06 | 39.9781 | 39.9781 | Eng Hany Fareed | Sewedy
New Giza Phase 01 | 2014-09-20 | 2015-07-20 | 2016-02-20 | 9.9616 | 17.0301 | Eng Ashraf Abd El Satar | New Giza
Hyper Solimanya | 2015-06-15 | 2016-04-15 | 2017-04-15 | 10.0274 | 22.0274 | Eng Amir | Hyper
Ismailia Bridges | 2016-01-01 | 2017-01-30 | 2017-01-30 | 12.9863 | 12.9863 | Eng Mohamed El Tahlawi | Army Forces
Maxium Mall | 2014-10-19 | 2016-05-20 | 2017-05-20 | 19.0356 | 31.0356 | Eng Raed | Maxim
Ataqqa Power Plant | 2014-12-20 | 2016-03-20 | 2016-03-20 | 14.9918 | 14.9918 | Eng Mohamed Abd El Fatah | Sewedy
Mall of Egypt Bridge | 2015-02-10 | 2016-12-10 | 2016-12-10 | 21.9945 | 21.9945 | Eng Mohamed Mostafa | Army Forces
Marassi Tanks PKG 22 | 2012-10-30 | 2014-09-30 | 2014-09-30 | 23.0137 | 23.0137 | Eng Hassan Youssef | EMAAR
Sodic Club House | 2015-03-01 | 2017-05-30 | 2019-09-30 | 26.9918 | 55.0356 | Eng Hesham Ibrahim | SODIC
Montazah Hotel Sharm | 2014-12-31 | 2016-12-30 | 2016-12-30 | 24 | 24 | Eng Wael Ragabi | El Montazah
Uptown Cairo Pkg 53 | 2015-04-01 | 2017-04-30 | 2018-12-30 | 24.9863 | 45.0082 | Eng Mohamed Abd El Raouf | EMAAR
Bani Suif Power Plant 1021 | 2015-07-01 | 2017-07-01 | 2017-11-30 | 24.0329 | 29.0301 | Eng Ashraf Abd El Satar | Sewedy
New Giza Phase 02 | 2015-07-25 | 2016-09-24 | 2017-08-24 | 14.0384 | 25.0192 | Eng Ashraf Abd El Satar | New Giza
JICA Wind Farm Gabal El Zeet | 2015-12-01 | 2017-04-01 | 2017-04-01 | 16.011 | 16.011 | Eng Karim El Far | GAMESA
El Mostathmereen Mokatam Substation | 2016-01-01 | 2016-10-30 | 2017-11-30 | 9.9616 | 22.9808 | Eng Mohamed Abd El Fatah | EETC
Levana UpTown PKG 62 | 2016-04-27 | 2018-12-27 | 2018-12-27 | 32.0219 | 32.0219 | Eng Alaa Mahran | EMAAR
Kayan 110 | 2016-05-16 | 2018-01-15 | 2020-06-15 | 20.0219 | 49.0192 | Eng Adel Rahmo | Army Forces
El Amal Bridge | 2015-02-01 | 2016-02-01 | 2016-02-01 | 12 | 12 | Eng Mohamed El Tahlawi | Army Forces
Bani Suif Cement | 2016-08-09 | 2018-07-09 | 2018-07-09 | 22.9808 | 22.9808 | Eng Mohamed Zaki | CDI
New Giza Wall | 2015-12-01 | 2016-11-13 | 2016-11-13 | 11.4411 | 11.4411 | Eng Ashraf Abd El Satar | New Giza
Tamey El Amdid Mansora Power Station | 2017-07-01 | 2018-05-01 | 2019-11-01 | 9.9945 | 28.0438 | Eng Mohamed Abd El Fatah | EETC
Ismailia Substation 500-220 | 2017-07-10 | 2018-04-10 | 2020-01-10 | 9.0082 | 30.0493 | Eng Mohamed Abd El Fatah | EETC
El Amal Bridge L&L | 2018-02-01 | 2018-06-03 | 2018-06-03 | 4.011 | 4.011 | Eng Adham Edward | Army Forces
FIEM Wind Farm Gabal El Zeet | 2016-10-01 | 2017-05-01 | 2017-05-01 | 6.9699 | 6.9699 | Eng Karim El Far | GAMESA
KFW Wind Farm Gabal El Zeet | 2016-11-01 | 2017-04-01 | 2017-04-01 | 4.9644 | 4.9644 | Eng Karim El Far | GAMESA
Marassi Tank PKG 107 | 2017-02-15 | 2017-12-15 | 2019-03-16 | 9.9616 | 24.9534 | Eng Marwan Shibl | EMAAR
Ben Zayed New Capital Tunnel | 2016-03-18 | 2017-12-18 | 2017-12-18 | 21.0411 | 21.0411 | Eng Mohamed El Tahlawi | Army Forces
Ministries Buildings | 2017-04-01 | 2018-08-01 | 2021-12-30 | 16.011 | 57.0082 | Eng Wael Ragabi | Army Forces
Bani Suif Substation | 2017-07-01 | 2017-11-01 | 2019-03-01 | 4.0438 | 19.989 | Eng Mohamed Abd El Fatah | EETC
Royal City Mall | 2017-06-01 | 2020-03-30 | 2020-12-30 | 33.9616 | 43.0027 | Eng Ashraf Abd El Satar | Al Babtain Group
Shoubra Banha Bridge L&L | 2018-04-30 | 2018-07-30 | 2018-07-30 | 2.9918 | 2.9918 | Eng Adham Edward | Army Forces
SLP Logistic Center PI Park Sewedy Stores | 2017-07-19 | 2018-05-19 | 2019-06-20 | 9.9945 | 23.0466 | Eng Amir | Sewedy
El Mostakbal Bridge L&L | 2018-07-01 | 2018-10-30 | 2018-10-30 | 3.9781 | 3.9781 | Eng Adham Edward | Army Forces
Kayan Wall L&L | 2017-11-01 | 2019-10-01 | 2019-10-01 | 22.9808 | 22.9808 | Eng Adham Edward | Army Forces
Elco Suez Steel Rolling Mill Plant 3 | 2017-09-07 | 2018-12-07 | 2018-12-07 | 14.9918 | 14.9918 | Eng Mohamed El Saman | Elco Suez
Hyper El Temsah | 2018-06-07 | 2018-09-07 | 2019-07-07 | 3.0247 | 12.9863 | Eng Sayed Osman | Army Forces
Marassi Bridge Pkg 117 | 2017-11-13 | 2019-08-13 | 2019-08-13 | 20.9753 | 20.9753 | Eng Marwan Shibl | EMAAR
Siemens Power Station | 2017-11-05 | 2018-12-05 | 2019-12-05 | 12.9863 | 24.9863 | Eng Hassan Youssef | SIEMENS
Uptown FM85 Pkg 85 |  |  |  | 0 | 0 | Eng Mohamed Bassuony | EMAAR
El Sokhna Tunnel 01 | 2018-02-01 | 2018-12-01 | 2018-12-01 | 9.9616 | 9.9616 | Eng Mohamed El Tahlawi | Army Forces
Abu Sultan Bridge 01 | 2018-03-01 | 2018-09-30 | 2018-09-30 | 7.0027 | 7.0027 | Eng Mohamed El Tahlawi | Army Forces
Mintra Factory | 2018-02-01 | 2019-01-01 | 2019-01-01 | 10.9808 | 10.9808 | Eng Salah Rashad | Mintra
King Farouk Restoration | 2018-02-01 | 2018-02-10 | 2018-02-11 | 0.29589 | 0.32877 | Eng Mariam Youssef | Army Forces
Mohamed Ali Palace | 2018-04-01 | 2022-06-30 | 2022-06-30 | 50.9918 | 50.9918 | Eng Mohamed Saber | Army Forces
Nefisha Bridge | 2018-05-02 | 2019-01-01 | 2019-01-01 | 8.0219 | 8.0219 | Eng Mohamed El Tahlawi | Army Forces
Fish Market | 2018-06-01 | 2019-03-01 | 2019-06-30 | 8.9753 | 12.9534 | Eng Sayed Osman | Army Forces
Al Jazi Mall | 2018-05-01 | 2020-02-15 | 2020-02-28 | 21.5342 | 21.9616 | Eng Mohamed Zaki | YAMM
Benban Aswan Alcazars Solar Park | 2018-06-02 | 2019-07-02 | 2019-07-02 | 12.9863 | 12.9863 | Eng Amir | TSK
El Alameen Roads Earth Works | 2018-09-15 | 2019-06-15 | 2019-06-15 | 8.9753 | 8.9753 | Eng Mohamed Abd El Nabi | Army Forces
El Sewedy Univeristy 2 phase 2 | 2019-10-10 | 2020-05-10 | 2020-12-10 | 7.0027 | 14.0384 | Eng Hesham Ibrahim | Sewedy
El Sokhna Tunnel L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
R05 Z03 | 2018-07-16 | 2021-01-14 | 2022-05-16 | 30.0164 | 46.0274 | #N/A | #N/A
R05 Residential District Z1 & Z2 | 2018-07-16 | 2021-01-14 | 2022-05-16 | 30.0164 | 46.0274 | Eng Mohamed Abd El Fatah | Utilities And Urban Communities
Abu Sultan Bridge 02 Greenhouse | 2018-09-01 | 2019-06-01 | 2019-06-01 | 8.9753 | 8.9753 | Eng Mohamed El Tahlawi | Army Forces
El Sokhna Tunnel 02 | 2018-09-01 | 2019-04-01 | 2019-04-01 | 6.9699 | 6.9699 | Eng Mohamed El Tahlawi | Army Forces
El Awsty Middle Tunnel L&L | 2018-12-01 | 2019-04-01 | 2019-04-01 | 3.9781 | 3.9781 | Eng Adham Edward | Army Forces
Sodic Eastown EDNC | 2019-03-25 | 2021-12-24 | 2021-12-24 |  | 33.0411 | Eng Sayed Osman | SODIC
Marassi Civic Center Pkg 144 | 2018-11-01 | 2019-08-01 | 2019-08-01 | 8.9753 | 8.9753 | Eng Marwan Shibl | EMAAR
DPW Sokhna Dubai Port | 2018-11-16 | 2020-04-16 | 2021-07-16 | 16.9973 | 31.989 | Eng Mohamed El Saman | DPW
Slope Stablization PKG 101 | 2018-10-11 | 2020-11-10 | 2020-11-10 | 25.0192 | 25.0192 | Eng Mohamed Bassuony | EMAAR
Elco Steel Substation | 2018-05-01 | 2019-04-01 | 2019-04-01 | 11.0137 | 11.0137 | Eng Mohamed El Saman | Elco Suez
Sewab Greenhouse Tunnel | 2018-09-01 | 2019-06-01 | 2019-06-01 | 8.9753 | 8.9753 | Eng Mohamed El Tahlawi | Army Forces
Mivida Irrigation Treatment Plant Pkg 140 | 2019-01-14 | 2020-03-14 | 2021-07-14 | 13.9726 | 29.9836 | Eng Hassan Youssef | EMAAR
Multi Sports Hall | 2019-08-30 | 2021-03-30 | 2022-05-31 | 19.0027 | 33.0411 | Eng Adel Rahmo | Army Forces
EGAT | 2019-04-30 | 2019-12-30 | 2019-12-30 | 8.0219 | 8.0219 | Eng Mohamed El Saman | Elco Suez
Abou Ghazala Bridge Ramp L&L | 2019-03-15 | 2019-07-15 | 2019-07-15 | 4.011 | 4.011 | Eng Adham Edward | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-03-15 | 2019-12-15 | 2019-12-15 | 9.0411 | 9.0411 | Eng Adham Edward | Army Forces
El Mosheer Bridge Abu Zaied Khdr L&L | 2018-10-01 | 2019-03-01 | 2019-03-01 | 4.9644 | 4.9644 | Eng Adham Edward | Army Forces | 1
Ora Zed Park L&L | 2019-07-01 | 2019-11-01 | 2019-11-01 | 4.0438 | 4.0438 | Eng Adham Edward | Ora | 1
DoubleTree Mangroovy El Gouna Hotel | 2019-08-22 | 2021-08-22 | 2021-08-22 | 24.0329 | 24.0329 | Eng Sherif El Sisi | Sewedy
Baron Palace Fence | 2020-02-01 | 2020-07-01 | 2020-07-01 | 4.9644 | 4.9644 | Eng Mariam Youssef | Army Forces
Safeer Square Bridge | 2019-08-01 | 2019-12-01 | 2019-12-01 | 4.011 | 4.011 | Eng Hany Yassin | Army Forces
HyperOne Zayed Extention | 2019-10-13 | 2020-12-13 | 2020-12-13 | 14.0384 | 14.0384 | Eng Tarek Ramadan | Hyper | 1
Suez Road Tunnel Res L&L | 2019-08-20 | 2019-10-20 | 2019-10-20 | 2.0055 | 2.0055 | Eng Adham Edward | Army Forces
IKEA Extention MoA | 2019-10-01 | 2020-02-13 | 2020-11-30 | 4.4384 | 14.0055 | Eng Ashraf Abd El Satar | Marakez
CFC Podium II | 2019-10-01 | 2020-12-01 | 2021-07-30 | 14.0384 | 21.9616 | Eng Amir | Al-Futtaim
Mostafa Kamel Bridge L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
Josef Tito Bridge L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
Espiko Bridge L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
El Gabal El Asfr Tunnel L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
MR3 Bridge L&L | 2019-10-19 | 2019-12-19 | 2019-12-19 | 2.0055 | 2.0055 | Eng Adham Edward | Army Forces
El Sewedy University 1 | 2018-09-09 | 2019-03-09 | 2019-09-09 | 5.9507 | 12 | Eng Hesham Ibrahim | Sewedy | 1
Mehwar El Salam Axis L&L | 2019-10-01 | 2020-02-01 | 2020-02-01 | 4.0438 | 4.0438 | Eng Adham Edward | Army Forces | 1
El Hegaz Square Bridge | 2019-12-05 | 2020-04-05 | 2020-04-05 | 4.011 | 4.011 | Eng Hany Yassin | Army Forces
Ring Road | 2020-02-01 | 2022-03-30 | 2022-03-30 | 25.9068 | 25.9068 | Eng Abd El Naby Shaban | Roads and Bridges Authority | 1
Marina Inland Marassi Pkg 162 | 2020-02-02 | 2021-04-02 | 2022-03-02 | 13.9726 | 24.9534 | Eng Reda | EMAAR
Sultana Malek Restoration | 2020-08-01 | 2022-06-01 | 2022-06-01 | 21.9945 | 21.9945 | Eng Karem Ehab | Army Forces
Lekela 250MW Wind Farm | 2020-06-03 | 2021-06-04 | 2021-06-04 | 12.0329 | 12.0329 | Eng Marwan Shibl | GAMESA
New Giza Hospital | 2021-09-30 | 2022-09-30 | 2023-09-30 | 12 | 24 | Eng Ashraf Abd El Satar | New Giza
Kayan Landscape | 2019-06-01 | 2020-03-01 | 2020-03-01 | 9.0082 | 9.0082 | Eng Adel Rahmo | Army Forces | 1
Abbas Akkad Bridge | 2020-02-01 | 2020-06-01 | 2020-06-01 | 3.9781 | 3.9781 | Eng Hany Yassin | Army Forces
El Asher Men Ramadan Bridge | 2020-02-28 | 2020-06-30 | 2020-06-30 | 4.0438 | 4.0438 | Eng Mostafa Diab | Army Forces | 1
Kafr Shokr Bridge | 2020-08-15 | 2021-08-15 | 2021-08-15 | 12 | 12 | Eng Ahmed El Adawy | Army Forces | 1
Al Shorouk Bridge (LRT) | 2020-05-09 | 2021-02-08 | 2021-02-08 | 9.0411 | 9.0411 | Eng Hany Yassin | Army Forces
GOV2 Infra | 2020-06-01 | 2021-12-01 | 2021-12-01 | 18.0164 | 18.0164 | Eng Mohamed Abd El Moktader | Utilities And Urban Communities | 1
Cairo Alex Railroad | 2020-10-15 | 2022-10-15 | 2022-10-15 | 24 | 24 | Eng Ali Tawfeek | ENR
Hassan El Mamoun Bridge | 2020-06-01 | 2020-09-01 | 2020-09-01 | 3.0247 | 3.0247 | Eng Mostafa Diab | Army Forces
Sherouk Bridge L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
Ora Zed Park 1B Pkgs A&D | 2020-09-28 | 2022-02-28 | 2023-06-28 | 17.0301 | 32.9753 | Eng Hesham Ibrahim | Ora | 1
Kattameya Creeks | 2021-01-15 | 2022-10-15 | 2024-01-15 | 20.9753 | 36 | Eng Mohamed Kamal | Starlight | 1
Mansoura University Faculty of Medicine | 2021-01-01 | 2021-12-31 | 2021-12-31 | 11.9671 | 11.9671 | Eng Emad Habi | Utilities And Urban Communities | 1
Diplomatic District - Infra | 2021-01-01 | 2022-01-01 | 2022-01-01 | 12 | 12 | Eng Mohamed Abd El Moktader | Utilities And Urban Communities
El Sewedy CFC HQ Internal Finishing | 2020-12-08 |  | 2022-06-08 |  | 17.9836 | Eng Ashraf Abd El Satar | Sewedy | 1
Lagoon Discharge Pkg 178 | 2020-12-28 | 2021-03-30 | 2021-07-30 | 3.0247 | 7.0356 | Eng Reda | EMAAR
El Khatatba Bridge | 2021-06-01 | 2022-06-01 | 2022-06-01 | 12 | 12 | Eng Khaled Tawfek | Roads and Bridges Authority
EGAT Pelletizing Plant | 2021-06-01 | 2022-06-01 | 2022-06-01 | 12 | 12 | Eng Mohamed Fadel | Elco Suez
Sokhna Port Expansion | 2021-06-01 | 2022-06-01 | 2022-06-01 | 12 | 12 | Eng Tarek Ramadan | Transportation Ministry
Waldorf Astoria Mock Up Room |  |  |  | 0 | 0 | #N/A | #N/A
MDF Factory | 2021-03-06 | 2022-05-05 | 2022-05-05 | 13.9726 | 13.9726 | Eng Bader Osman | Naile Wood
Olympic City L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
Kemet Building | 2021-03-30 | 2021-10-30 | 2021-10-30 | 7.0356 | 7.0356 | Eng Hany Yassin | Kemet
Uptown Soil Stabilization Pkg 32 | 2012-08-05 | 2015-05-05 | 2015-05-05 | 32.9753 | 32.9753 | Eng Hassan Youssef | EMAAR
Marassi Bridges Pkg 37 | 2012-08-01 | 2013-08-01 | 2014-06-01 | 12 | 21.9945 | Eng Waleed Tag | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2013-03-19 | 2015-01-18 | 2015-01-18 | 22.0274 | 22.0274 | Eng Waleed Tag | EMAAR
Limak TB2 Cairo Airport Terminal | 2013-02-13 | 2015-11-13 | 2015-11-13 | 32.9753 | 32.9753 | Eng Mohamed El Saman | Limak
Point 90 New Cairo Mall | 2013-09-19 | 2015-09-18 | 2015-09-18 | 23.9671 | 23.9671 | Eng Raed | Cairo Company for Housing & Development (CCHD)
Hyper Matrouh | 2019-12-29 |  |  |  |  | #N/A | #N/A | 1
Ismailia Bridge L&L | 2018-12-29 | 2019-03-29 | 2019-03-29 | 2.9589 | 2.9589 | Eng Mohamed El Tahlawi | Army Forces | 1
Autoville Strip Mall | 2010-04-28 | 2014-04-28 | 2014-04-28 | 48.0329 | 48.0329 | Eng Ashraf Abd El Satar | SODIC
El Obour Bridge B2 | 2014-07-30 | 2014-12-30 | 2014-12-30 | 5.0301 | 5.0301 | Eng Mohamed El Tahlawi | Army Forces
ng Mill Plant 3 | 2017-09-07 | 2018-10-15 | 2019-03-26 | 13.2493 | 18.5753 | #N/A | #N/A
rld Sokhna - Concrete | 2019-04-03 | 2020-08-25 | 2021-02-28 | 16.7671 | 22.9151 | #N/A | #N/A
rld Sokhna - Infra | 2019-03-13 | 2020-08-25 | 2020-08-25 | 17.4575 | 17.4575 | #N/A | #N/A
rld Sokhna - Interlock | 2019-10-05 | 2020-11-30 | 2020-11-30 | 13.874 | 13.874 | #N/A | #N/A
Alexandria Bridges | 2010-10-01 | 2012-12-31 | 2012-12-31 | 27.0247 | 27.0247 | Eng Mohamed El Saman | Mohamed Abd El Wahab
Uptown Service Buildings Pkg 17A | 2011-07-27 | 2013-12-26 | 2013-12-26 | 29.0301 | 29.0301 | Eng Mohamed Abd El Raouf | EMAAR
El Mahala Bridge | 2014-11-30 | 2015-11-30 | 2015-11-30 | 12 | 12 | Eng Mohamed Mostafa | Army Forces
El Wahat Tunnel | 2015-02-16 | 2015-12-16 | 2015-12-16 | 9.9616 | 9.9616 | Eng Mohamed El Tahlawi | Army Forces
West town Hub | 2012-09-30 | 2013-12-30 | 2015-01-30 | 14.9918 | 28.011 | #N/A | #N/A
EMEC | 2011-03-20 | 2012-03-20 | 2012-03-20 | 12.0329 | 12.0329 | Eng Mohamed Abd El Fatah | EMEC
Twin Towers | 2011-06-30 | 2013-06-30 | 2015-06-30 | 24.0329 | 48.0329 | Eng Karim El Far | Arabian Group
MV Cables | 2012-11-25 |  |  |  |  | #N/A | #N/A
Alstom-French Station |  |  | 2017-11-01 | 0 |  | #N/A | #N/A
Alegria DP Port | 2017-11-24 | 2021-12-24 | 2021-12-24 | 49.0192 | 49.0192 | Eng Mohamed Mostafa | DPW
Allegria Club House |  |  |  | 0 | 0 | #N/A | #N/A
Autoville Strip Mall |  |  |  | 0 | 0 | Eng Ashraf Abd El Satar | SODIC
Batch Plant |  |  |  | 0 | 0 | #N/A | #N/A
Dubai Port Sokhna Basin 1 | 2013-06-01 | 2015-09-01 | 2015-09-01 | 27.0247 | 27.0247 | Eng Karim El Far | DPW
El Alameen Bridge L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
El Asher Bridge |  |  |  | 0 | 0 | #N/A | #N/A
El Asher of Ramadan Bridge L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
El Mahala Bridge |  |  |  | 0 | 0 | Eng Mohamed Mostafa | Army Forces
El Mostakbal Bridge L&L |  |  |  | 0 | 0 | Eng Adham Edward | Army Forces
El Obour Bridge B2 |  |  |  | 0 | 0 | Eng Mohamed El Tahlawi | Army Forces
El Shone Bridge |  |  |  | 0 | 0 | #N/A | #N/A
El Wahat Bridge | 2015-02-16 | 2015-12-16 | 2015-12-16 | 9.9616 | 9.9616 | Eng Mohamed El Tahlawi | Army Forces
EMEC |  |  |  | 0 | 0 | Eng Mohamed Abd El Fatah | EMEC
Hyper Matrouh |  |  |  | 0 | 0 | #N/A | #N/A
Ismailia Bridge L&L |  |  |  | 0 | 0 | Eng Mohamed El Tahlawi | Army Forces
Logestica Phase 01 | 2011-12-18 | 2013-08-18 | 2013-08-18 | 20.0219 | 20.0219 | Eng Amir | Logestica
Logestica Phase 02 | 2013-12-18 | 2015-02-18 | 2015-02-18 | 14.0384 | 14.0384 | Eng Amir | Logestica
Logestica Phase 03 | 2013-12-18 | 2015-02-18 | 2015-02-18 | 14.0384 | 14.0384 | Eng Amir | Logestica
Marassi Bridges Pkg 37 |  |  |  | 0 | 0 | Eng Waleed Tag | EMAAR
Marassi Golf Maintance Building Pkg 58 |  |  |  | 0 | 0 | Eng Waleed Tag | EMAAR
Point 90 New Cairo Mall |  |  |  | 0 | 0 | Eng Raed | Cairo Company for Housing & Development (CCHD)
Sodic MV Cables | 2014-12-30 | 2015-12-30 | 2015-12-30 | 12 | 12 | Eng Ashraf Abd El Satar | SODIC
Sodic West Town Hub | 2013-01-01 | 2014-01-02 | 2015-12-31 | 12.0329 | 35.9671 | Eng Ashraf Abd El Satar | SODIC
Uptown Soil Stabilization Pkg 32 |  |  |  | 0 | 0 | Eng Hassan Youssef | EMAAR
Electric Train LRT | 2019-01-01 | 2022-11-01 | 2022-11-01 | 46.0274 | 46.0274 | Eng Hassan | NAT
Sea Shell Playa |  |  |  | 0 | 0 | Eng Wael Ragabi | New Giza
El Asmarat | 2014-06-14 | 2015-09-14 | 2015-09-14 | 15.0247 | 15.0247 | Eng Karim El Far | Arabian Group
Formulas:
Project Start = [Project Start, row below]
Concrete Finish = [Concrete Finish, row below]
Project Finish = [Project Finish, row below]

## 02-Metrics
Project | Project Start | Project Finish | Main Category | Sub Category | Scope | Client | Project Manager | Area Manager | Location | S/D Client | Client Type | Unit | Outcome | Area | Type | Original Contract Value | Revised Contract Value | EAC / Cost From POC | Gross % | write name here % | Price/m2 | Price/Unit | Cost/m2 | Cost/Unit | Price $/m2 | Price $/Unit | Cost $/m2 | Cost $/Unit | $ Value | Bridges Length | Bridges Width | Landscape Area | Main Category | Sub Category
Marassi Civic Center Pkg 45 | 2012-11-13 | 2015-11-13 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | North Coast | D | Private |  |  | 6743 | All | 51530647 | 56931016 | 64758247.2535 | -13.75% | 18.9% | 8442.9803 | 0 | 9603.7739 | 0 | 1386.3679 | 0 | 1576.9744 | 0 | 6.09 |  |  |  |  | Mall
Al Oula Infra | 2012-02-06 | 2015-06-06 | Infrastructure | Networks | Civil Works | Sewedy | Eng Hany Fareed | Eng. yasser el saadny | 6th of October | D | Affiliates |  |  |  | All | 33000000 | 72946445.96 | 66087308.6012 | 9.403% | 1.758% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.09
New Giza Phase 01 | 2014-09-20 | 2016-02-20 | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 16200 | All | 188451123.6823 | 172216796.0405 | 173716038.3248 | -0.8706% | -11.28% | 10630.6664 | 0 | 10723.2122 | 0 | 1486.8065 | 0 | 1499.75 | 0 | 7.15
Hyper Solimanya A | 2015-06-15 | 2017-04-15 | Commercial | Market | Civil Works | Hyper | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private | Customer/Day | 5539.1926 | 10871 | Civil | 63179500 | 84316881.2881 | 82964778.4635 | 1.604% | 0% | 7756.1293 | 15221.8721 | 7631.7522 | 14977.7746 | 1084.7733 | 2128.9332 | 1067.3779 | 2094.7937 | 7.15 |  |  |  | Mall | Building
Hyper Solimanya B | 2015-06-15 | 2017-04-15 | Commercial | Market | Civil Works | Hyper | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private | Customer/Day | 5539.1926 | 10871 | Arch | 3820500 | 5098689.3686 | 5016926.9481 | 1.604% | 0% | 469.0175 | 920.4752 | 461.4964 | 905.7145 | 65.5969 | 128.7378 | 64.5449 | 126.6734 | 7.15 |  |  |  | Mall | Building
Hyper Solimanya C | 2015-06-15 | 2017-04-15 | Commercial | Market | Civil Works | Hyper | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private | Customer/Day | 5539.1926 | 10871 | MEP | 15761451 | 21034613.9633 | 20697303.5633 | 1.604% | 0% | 1934.9291 | 3797.4152 | 1903.9006 | 3736.5199 | 270.6195 | 531.107 | 266.2798 | 522.5902 | 7.15 |  |  |  | Mall | Building
Hyper Solimanya | 2015-06-15 | 2017-04-15 | Commercial | Market | Civil Works | Hyper | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  | 5539.1926 | 10871 | Total | 82761451 | 110450184.62 | 108679008.9749 | 1.604% | 0.4356% | 10160.0759 | 19939.7624 | 9997.1492 | 19620.009 | 1420.9896 | 2788.778 | 1398.2027 | 2744.0572 | 7.15 |  |  |  | Mall | Building
Ismailia Bridges | 2016-01-01 | 2017-01-30 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY | m | 174 | 6309 | All | 56652000 | 56527617 | 33948207.928 | 39.94% | 0% | 8959.8379 | 324871.3621 | 5380.9174 | 195104.6433 | 1008.9907 | 36584.6128 | 605.9592 | 21971.2436 | 8.88 | 174 | 102 |  | Bridges | Precast/Box
Maxium Mall A | 2014-10-19 | 2017-05-20 | Commercial | Offices & Mall | Turn Key | Maxim | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | Customer/Day | 26750.7692 | 70000 | MEP | 58000000 | 56332254.0422 | 59939513.622 | -6.404% | 0% | 804.7465 | 2105.8181 | 856.2788 | 2240.665 | 112.552 | 294.52 | 119.7593 | 313.3797 | 7.15 |  |  |  | Mall | Building
Maxium Mall B | 2014-10-19 | 2017-05-20 | Commercial | Offices & Mall | Turn Key | Maxim | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | Customer/Day | 26750.7692 | 70000 | Arch | 43495012 | 42244345.9578 | 44949480.4183 | -6.404% | 0% | 603.4907 | 1579.1825 | 642.1354 | 1680.3061 | 84.4043 | 220.8647 | 89.8092 | 235.0078 | 7.15 |  |  |  | Mall | Building
Maxium Mall | 2014-10-19 | 2017-05-20 | Commercial | Offices & Mall | Turn Key | Maxim | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | Customer/Day |  | 70000 | Total | 101495012 | 98576600 | 104888994.0403 | -6.404% | -24.71% | 1408.2371 | 0 | 1498.4142 | 0 | 196.9562 | 0 | 209.5684 | 0 | 7.15 |  |  |  | Mall | Building
Ataqqa Power Plant | 2014-12-20 | 2016-03-20 | Industrial | Power Plant | Turn Key | Sewedy | Eng Mohamed Abd El Fatah | Eng. Mohamed Salah Helmy | Suez | D | Affiliates |  |  |  | All | 149999782.52 | 184387980.81 | 97786625.9352 | 46.97% | 17.31% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.15
Mall of Egypt Bridge | 2015-02-10 | 2016-12-10 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed Mostafa | Eng. Omar Sobhy | 6th of October | D | ARMY |  |  | 1553 | All | 157635800 | 183459815.63 | 165227581.2857 | 9.938% | 0% | 118132.5278 | 0 | 106392.5185 | 0 | 15087.1683 | 0 | 13587.8057 | 0 | 7.83 | 84 | 18 |  | Bridges | Pre cast
Marassi Tanks PKG 22 | 2012-10-30 | 2014-09-30 | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | North Coast | D | Private | tank storage m3 | 5000 |  | All | 16562387.829 | 18438370 | 16655530.55 | 9.669% | -17.66% | 0 | 3687.674 | 0 | 3331.1061 | 0 | 605.5294 | 0 | 546.9797 | 6.09
Sodic Club House A | 2015-03-01 | 2019-09-30 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 20000 | Civil | 30327415.5623 | 29248357.7418 | 29665059.0304 | -1.425% | 0% | 1462.4179 | 0 | 1483.253 | 0 | 186.7711 | 0 | 189.4321 | 0 | 7.83 |  |  | 28652 | Commercial | Building
Sodic Club House B | 2015-03-01 | 2019-09-30 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 20000 | Arch | 56234959.2434 | 54234103.8646 | 55006777.0233 | -1.425% | 0% | 2711.7052 | 0 | 2750.3389 | 0 | 346.3225 | 0 | 351.2566 | 0 | 7.83 |  |  | 28652 | Commercial | Building
Sodic Club House C | 2015-03-01 | 2019-09-30 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 20000 | MEP | 28333644.681 | 27325525.7791 | 27714832.4849 | -1.425% | 0% | 1366.2763 | 0 | 1385.7416 | 0 | 174.4925 | 0 | 176.9785 | 0 | 7.83 |  |  | 28652 | Commercial | Building
Sodic Club House D | 2015-03-01 | 2019-09-30 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 28650 | Civil | 7219874.0615 | 6962988.9487 | 7062190.637 | -1.425% | 0% | 243.0363 | 0 | 246.4988 | 0 | 31.0391 | 0 | 31.4813 | 0 | 7.83 |  |  |  | Commercial | Exeternal Work
Sodic Club House E | 2015-03-01 | 2019-09-30 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 28650 | Arch | 10918397.1361 | 10529917.5509 | 10679937.2632 | -1.425% | 0% | 367.5364 | 0 | 372.7727 | 0 | 46.9395 | 0 | 47.6083 | 0 | 7.83 |  |  |  | Commercial | Exeternal Work
Sodic Club House F | 2015-03-01 | 2019-09-30 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 28650 | MEP | 34121421.7223 | 32907372.1149 | 33376203.3733 | -1.425% | 0% | 1148.5994 | 0 | 1164.9635 | 0 | 146.6921 | 0 | 148.7821 | 0 | 7.83 |  |  |  | Commercial | Exeternal Work
Sodic Club House | 2015-03-01 | 2019-09-30 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 20000 | Total | 167155712.4065 | 161208266 | 169537179.4745 | -5.167% | -14.19% | 8060.4133 | 0 | 8476.859 | 0 | 1029.427 | 0 | 1082.6129 | 0 | 7.83 |  |  |  | Commercial
Montazah Hotel Sharm | 2014-12-31 | 2016-12-30 | Commercial | Hotel | Civil Works | El Montazah | Eng Wael Ragabi | Eng. Omar Sobhy | sharm | S | Private |  |  | 16580 | All | 15941883 | 33784495.5267 | 30373982.7996 | 10.09% |  | 2037.6656 | 0 | 1831.9652 | 0 | 284.9882 | 0 | 256.2189 | 0 | 7.15
Uptown Cairo Pkg 53 | 2015-04-01 | 2018-12-30 | Residential | Residential | Turn Key | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | Private |  |  | 63752 | Civil | 83305896.191 | 314789511 | 344222187 | -9.35% | -7.423% | 4937.7198 | 0 | 5399.3943 | 0 | 630.6156 | 0 | 689.5778 | 0 | 7.83 |  |  |  | Residual | Building
Bani Suif Power Plant 1021 | 2015-07-01 | 2017-11-30 | Industrial | Power Plant | Turn Key | Sewedy | Eng Ashraf Abd El Satar | Eng. Mohamed Ragab | Benisuef | D | Affiliates | MW | 4800 |  | All | 442721012 | 427594086.74 | 319973217.7839 | 25.17% | -0.1128% | 0 | 89082.1014 | 0 | 66661.087 | 0 | 11377.0244 | 0 | 8513.5488 | 7.83 |  |  |  | Power Plant
New Giza Phase 02 | 2015-07-25 | 2017-08-24 | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 16200 | All | 148186885 | 155643269.76 | 161564179.8036 | -3.804% | -3.708% | 9607.6092 | 0 | 9973.0975 | 0 | 1227.0254 | 0 | 1273.7034 | 0 | 7.83
JICA Wind Farm Gabal El Zeet | 2015-12-01 | 2017-04-01 | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private | MW | 220 |  | All | 116000000.0279 | 120483319.9 | 82164809.214 | 31.8% | -0.0581% | 0 | 547651.4541 | 0 | 373476.4055 | 0 | 69942.7144 | 0 | 47698.1361 | 7.83
El Mostathmereen Mokatam Substation | 2016-01-01 | 2017-11-30 | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Cairo | S | Public | KV | 220 |  | All | 135792183 | 135792183 | 85209855.07 | 37.25% | 1.356% | 0 | 617237.1955 | 0 | 387317.523 | 0 | 69587.057 | 0 | 43666.0116 | 8.87 |  |  |  | Substation | Building
Levana UpTown PKG 62 | 2016-04-27 | 2018-12-27 | Infrastructure | L&L | Civil Works | EMAAR | Eng Alaa Mahran | Eng Mahmoud Mahlab | Cairo | D | Private |  |  | 22213.8 | All | 47942099.8594 | 47319156 | 52574895.421 | -11.11% | -0.079% | 2130.1694 | 0 | 2366.7673 | 0 | 239.8839 | 0 | 266.5278 | 0 | 8.88 |  |  |  | L&L | wall
Kayan 110 A | 2016-05-16 | 2020-06-15 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Adel Rahmo | Eng. Mohamed Ashry | New Capital | D | ARMY | person | 3600 | 152000 | Civil | 571311487.7878 | 609590858.0364 | 596388512.5258 | 2.166% | 0% | 4010.4662 | 169330.7939 | 3923.6086 | 165663.4757 | 452.1382 | 19090.2812 | 442.346 | 18676.8293 | 8.87 |  |  | 42000 | Residual | Building
Kayan 110 B | 2016-05-16 | 2020-06-15 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Adel Rahmo | Eng. Mohamed Ashry | New Capital | D | ARMY | person | 3600 | 152000 | Arch | 524428139.881 | 559566202.6794 | 547447276.9336 | 2.166% | 0% | 3681.3566 | 155435.0563 | 3601.6268 | 152068.688 | 415.0346 | 17523.6817 | 406.0459 | 17144.1587 | 8.87 |  |  | 42000 | Residual | Building
Kayan 110 C | 2016-05-16 | 2020-06-15 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Adel Rahmo | Eng. Mohamed Ashry | New Capital | D | ARMY | person | 3600 | 152000 | MEP | 155646723.0304 | 166075462.2842 | 162478647.1336 | 2.166% | 0% | 1092.6017 | 46132.0729 | 1068.9385 | 45132.9575 | 123.1795 | 5200.9101 | 120.5117 | 5088.2703 | 8.87 |  |  | 42000 | Residual | Building
Kayan 110 | 2016-05-16 | 2020-06-15 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Adel Rahmo | Eng. Mohamed Ashry | New Capital | D | ARMY |  |  | 152000 | Total | 1251386350.6992 | 1335232523 | 1306314436.593 | 2.166% | -0.06445% | 8784.4245 | 0 | 8594.1739 | 0 | 1228.5908 | 0 | 1201.9824 | 0 | 7.15 |  |  |  | Mall | Building
El Amal Bridge | 2015-02-01 | 2016-02-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | New Capital | D | ARMY | m | 90 | 2520 | All | 31793876 | 28943151 | 21210869.997 | 26.72% | 0% | 11485.3774 | 321590.5667 | 8417.0119 | 235676.3333 | 1466.8426 | 41071.5922 |  |  | 7.83 | 90 | 28 |  | Bridges | Pre cast
Bani Suif Cement | 2016-08-09 | 2018-07-09 | Industrial | Factory | Civil Works | CDI | Eng Mohamed Zaki | Eng Mahmoud Mahlab | Benisuef | S | Private | Ton / Day | 1000 |  | All | 274663700 | 274663700 | 265512440.135 | 3.332% | -11.49% | 0 | 274663.7 | 0 | 265512.4401 | 0 | 30965.4679 | 0 | 29933.7588 | 8.87 |  |  |  | Cement Plant | Building
New Giza Wall | 2015-12-01 | 2016-11-13 | Commercial | Fence | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  |  | All | 2750000 | 2648340.9749 | 1057277.26 | 60.08% | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 7.83
Tamey El Amdid Mansora Power Station | 2017-07-01 | 2019-11-01 | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Mansoura | S | Public | KV | 220 |  | All | 102015745.0742 | 114399640 | 92853851.3 | 18.83% | -16.5% | 0 | 519998.3636 | 0 | 422062.9605 | 0 | 28808.7736 | 0 | 23382.9895 | 18.05 |  |  | 16250 | Substation | Building
Ismailia Substation 500-220 | 2017-07-10 | 2020-01-10 | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Ismailia | S | Public | KV | 220 | 15000 | All | 109399640 | 109399640 | 94574974.6595 | 13.55% | -28.88% | 7293.3093 | 497271.0909 | 6304.9983 | 429886.2485 | 404.0615 | 27549.6449 | 349.3074 | 23816.4127 | 18.05 |  |  |  | Substation | Building
El Amal Bridge L&L | 2018-02-01 | 2018-06-03 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 8184472.88 | 9050320 | 6335224 | 30% | -127.1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.74 |  |  |  | L&L
FIEM Wind Farm Gabal El Zeet | 2016-10-01 | 2017-05-01 | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private | MW | 120 |  | All | 63636697.06 | 72547889 | 43182355.317 | 40.48% | 0% | 0 | 604565.7417 | 0 | 359852.961 | 0 | 68158.4827 | 0 | 40569.6687 | 8.87
KFW Wind Farm Gabal El Zeet | 2016-11-01 | 2017-04-01 | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private | MW | 40 |  | All | 20229094 | 23038288.54 | 13129303.501 | 43.01% | 29.93% | 0 | 575957.2135 | 0 | 328232.5875 | 0 | 64933.1695 | 0 | 37004.8013 | 8.87
Marassi Tank PKG 107 A | 2017-02-15 | 2019-03-16 | Infrastructure | Tank | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | tank storage m3 | 24500 |  | Civil | 43357003.3105 | 43357003.3105 | 33885169.5548 | 21.85% | 0% | 0 | 1769.6736 | 0 | 1383.0681 | 0 | 226.012 | 0 | 176.6371 | 7.83 |  |  |  | Tanks | Building
Marassi Tank PKG 107 B | 2017-02-15 | 2019-03-16 | Infrastructure | Tank | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | tank storage m3 | 24500 |  | Arch | 6640026.7565 | 6640026.7565 | 5189436.8917 | 21.85% | 0% | 0 | 271.0215 | 0 | 211.8138 | 0 | 34.6132 | 0 | 27.0516 | 7.83 |  |  |  | Tanks | Building
Marassi Tank PKG 107 C | 2017-02-15 | 2019-03-16 | Infrastructure | Tank | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | tank storage m3 | 24500 |  | MEP | 4780112.933 | 4780112.933 | 3735842.5365 | 21.85% | 0% | 0 | 195.1067 | 0 | 152.4834 | 0 | 24.9178 | 0 | 19.4742 | 7.83 |  |  |  | Tanks | Building
Marassi Tank PKG 107 | 2017-02-15 | 2019-03-16 | Infrastructure | Tank | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | tank storage m3 | 24500 | 0 | Total | 54777143 | 54777143 | 42810448.983 | 21.85% | -1.159% | 0 | 2235.8018 | 0 | 1747.3653 | 0 | 312.6995 | 0 | 244.3868 | 7.15 |  |  |  | Mall | Building
Ben Zayed New Capital Tunnel | 2016-03-18 | 2017-12-18 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | New Capital | D | ARMY | m | 330 | 18596 | All | 446010164 | 343357654.106 | 271212136.105 | 21.01% | -5.495% | 18464.0597 | 1040477.7397 | 14584.4341 | 821854.9579 | 1025.7811 | 57804.3189 | 810.2463 | 45658.6088 | 18 | 330 | 56 |  | Tunnels
Ministries Buildings A | 2017-04-01 | 2021-12-30 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Wael Ragabi | Eng. Mohamed Ashry | New Capital | D | ARMY | People Served | 4200 | 169000 | Civil | 412947199.05 | 538863802.0289 | 523638595.4064 | 2.825% | 0% | 3188.5432 | 128300.9052 | 3098.4532 | 124675.856 | 177.1413 | 7127.8281 | 172.1363 | 6926.4364 | 18 |  |  |  |  | Building
Ministries Buildings B | 2017-04-01 | 2021-12-30 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Wael Ragabi | Eng. Mohamed Ashry | New Capital | D | ARMY | People Served | 4200 | 169000 | Arch | 480124332.43 | 639866032.0624 | 621787080.5496 | 2.825% | 0% | 3786.1895 | 152349.0553 | 3679.2135 | 148044.543 | 210.3439 | 8463.8364 | 204.4007 | 8224.6968 | 18 |  |  |  |  | Building
Ministries Buildings C | 2017-04-01 | 2021-12-30 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Wael Ragabi | Eng. Mohamed Ashry | New Capital | D | ARMY | People Served | 4200 | 169000 | MEP | 1141981770.03 | 1498260528.2613 | 1455928261.6826 | 2.825% | 0% | 8865.4469 | 356728.6972 | 8614.9601 | 346649.5861 | 492.5248 | 19818.261 | 478.6089 | 19258.3103 | 18 |  |  |  |  | Building
Ministries Buildings D | 2017-04-01 | 2021-12-30 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Wael Ragabi | Eng. Mohamed Ashry | New Capital | D | ARMY | People Served | 4200 | 169000 | Roads & Landscape | 48611344.37 | 63579837.6474 | 61783435.3625 | 2.825% | 0% | 376.2121 | 15138.0566 | 365.5825 | 14710.3418 | 20.9007 | 841.0031 | 20.3101 | 817.2412 | 18 |  |  |  |  | Building
Ministries Buildings | 2017-04-01 | 2021-12-30 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Wael Ragabi | Eng. Mohamed Ashry | New Capital | D | ARMY | People Served | 4200 | 169000 | Total | 2083664645.88 | 2740570200 | 2663137373.0012 | 2.825% | -0.09973% | 16216.3917 | 652516.7143 | 15758.2093 | 634080.3269 | 900.9107 | 36250.9286 | 875.4561 | 35226.6848 | 18 |  |  |  |  | Building
Bani Suif Substation | 2017-07-01 | 2019-03-01 | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Benisuef | S | Public | KV | 220 | 29643 | All | 120712211 | 120712211 | 101105076 | 16.24% | -3.868% | 4072.1995 | 548691.8682 | 3410.7572 | 459568.5273 | 225.6066 | 30398.4415 | 188.9616 | 25460.8602 | 18.05 |  |  |  | Substation | Building
Royal City Mall A | 2017-06-01 | 2020-12-30 | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private | No of Shops | 95 | 25379 | Civil | 124972783 | 191239789.8548 | 182423510.9848 | 4.61% | 0% | 7535.3556 | 2013050.4195 | 7187.9708 | 1920247.4841 | 416.318 | 111218.2552 | 397.1255 | 106091.0212 | 18.1 |  |  |  | Commercial | Building
Royal City Mall B | 2017-06-01 | 2020-12-30 | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private | No of Shops | 95 | 25379 | Arch | 65302785 | 99929685.3327 | 95322861.7529 | 4.61% | 0% | 3937.495 | 1051891.4246 | 3755.9739 | 1003398.5448 | 217.5412 | 58115.5483 | 207.5124 | 55436.3837 | 18.1 |  |  |  | Commercial | Building
Royal City Mall C | 2017-06-01 | 2020-12-30 | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private | No of Shops | 95 | 25379 | MEP | 138661374 | 212186776.898 | 202404828.2821 | 4.61% | 0% | 8360.7225 | 2233545.02 | 7975.2878 | 2130577.1398 | 461.9184 | 123400.2773 | 440.6236 | 117711.4442 | 18.1 |  |  |  | Commercial | Building
Royal City Mall D | 2017-06-01 | 2020-12-30 | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private | No of Shops | 95 | 125000 | Roads & Landscape | 15475605 | 23681567.9145 | 22589832.2094 | 4.61% | 0% | 189.4525 | 249279.6623 | 180.7187 | 237787.7075 | 10.467 | 13772.357 | 9.9845 | 13137.4424 | 18.1 |  |  |  | Commercial | Building
Royal City Mall | 2017-06-01 | 2020-12-30 | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private | No of Shops | 95 | 25379 | Total | 344412547 | 527037820 | 502741033.2292 | 4.61% | -0.0004148% | 20766.6898 | 5547766.5263 | 19809.3319 | 5292010.8761 | 1147.3309 | 306506.4379 | 1094.4382 | 292376.2915 | 18.1 |  |  |  | Commercial | Building
Royal City Mall E | 2017-06-01 | 2020-12-30 | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private | Storage Capacity | 45000 | 13000 | Total | 97038375.909 | 98230405 | 85595093 | 12.86% | 0% | 7556.185 | 2182.8979 | 6584.2379 | 1902.1132 | 418.6252 | 120.9362 | 364.7777 | 105.3802 | 18.05 |  |  | 8000 | Commercial | Building
Shoubra Banha Bridge L&L | 2018-04-30 | 2018-07-30 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY | m | 5000 | 4000 | All | 3865380 | 3865380 | 1461115 | 62.2% | -8.292% | 966.345 | 773.076 | 365.2788 | 292.223 | 54.7815 | 43.8252 | 20.7074 | 16.5659 | 17.64 |  |  |  | Bridges
SLP Logistic Center PI Park Sewedy Stores A | 2017-07-19 | 2019-06-20 | Industrial | Factory | Turn Key | Sewedy | Eng Amir | Eng. Mohamed Fawzy | Cairo | D | Affiliates | Storage Capacity | 45000 | 13000 | Civil | 32488963.8724 | 32888061.546 | 28657691.95 | 12.86% | 0% | 2529.8509 | 730.8458 | 2204.4378 | 636.8376 | 140.1579 | 40.4901 | 122.1295 | 35.2819 | 18.05 |  |  | 8000 | Commercial | Building
SLP Logistic Center PI Park Sewedy Stores B | 2017-07-19 | 2019-06-20 | Industrial | Factory | Turn Key | Sewedy | Eng Amir | Eng. Mohamed Fawzy | Cairo | D | Affiliates | Storage Capacity | 45000 | 13000 | Arch | 15148223.7584 | 15334306.0504 | 13361864.4092 | 12.86% | 0% | 1179.562 | 340.7624 | 1027.8357 | 296.9303 | 65.3497 | 18.8788 | 56.9438 | 16.4504 | 18.05 |  |  | 8000 | Commercial | Building
SLP Logistic Center PI Park Sewedy Stores C | 2017-07-19 | 2019-06-20 | Industrial | Factory | Turn Key | Sewedy | Eng Amir | Eng. Mohamed Fawzy | Cairo | D | Affiliates | Storage Capacity | 45000 | 13000 | MEP | 49401188.2782 | 50008037.4037 | 43575536.6408 | 12.86% | 0% | 3846.7721 | 1111.2897 | 3351.9644 | 968.3453 | 213.1176 | 61.5673 | 185.7044 | 53.6479 | 18.05 |  |  | 8000 | Commercial | Building
SLP Logistic Center PI Park Sewedy Stores | 2017-07-19 | 2019-06-20 | Industrial | Factory | Turn Key | Sewedy | Eng Amir | Eng. Mohamed Fawzy | Cairo | D | Affiliates | Storage Capacity | 45000 | 13000 | Total | 97038375.909 | 98230405 | 86259669.128 | 12.19% | -0.7064% | 7556.185 | 2182.8979 | 6635.3592 | 1916.8815 | 418.6252 | 120.9362 | 367.6099 | 106.1984 | 18.05 |  |  |  | Commercial | Building
El Mostakbal Bridge L&L | 2018-07-01 | 2018-10-30 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  | 4286.7 | All | 4574604.922 | 4424558 | 2062745 | 53.38% | -3.002% | 1032.1595 | 0 | 481.1965 | 0 | 57.8241 | 0 | 26.9578 | 0 | 17.85 |  |  |  | L&L
Kayan Wall L&L | 2017-11-01 | 2019-10-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 87197267.1201 | 107782440 | 82991132 | 23% | -6.605% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.73 |  |  |  | L&L
Elco Suez Steel Rolling Mill Plant 3 | 2017-09-07 | 2018-12-07 | Industrial | Factory | Turn Key | Elco Suez | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Private | Million ton / year | 1.4 |  | All | 412223139.5933 | 417390514 | 292181074.4464 | 30% | -0.001764% | 0 | 298136081.4286 | 0 | 208700767.4617 | 0 | 16749218.0578 | 0 | 11724762.217 | 17.8 |  |  |  | Industrials | Steel Factory
Hyper El Temsah A | 2018-06-07 | 2019-07-07 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY | Customer/Day | 3312 | 7800 | Civil | 61662015 | 62145442.3104 | 52103846.6377 | 16.16% | 0% | 7967.3644 | 18763.7205 | 6679.9803 | 15731.8378 | 444.3594 | 1046.4986 | 372.5589 | 877.4031 | 17.93 |  |  |  | Commercial | Building
Hyper El Temsah B | 2018-06-07 | 2019-07-07 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY | Customer/Day | 3312 | 7800 | Arch | 32249653 | 32502488.7695 | 27250665.9737 | 16.16% | 0% | 4166.9857 | 9813.5534 | 3493.6751 | 8227.8581 | 232.403 | 547.3259 | 194.8508 | 458.8878 | 17.93 |  |  |  | Commercial | Building
Hyper El Temsah C | 2018-06-07 | 2019-07-07 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY | Customer/Day | 3312 | 7800 | MEP | 73749914 | 74328109.8725 | 62318012.2901 | 16.16% | 0% | 9529.2449 | 22442.0622 | 7989.4888 | 18815.825 | 531.4693 | 1251.6488 | 445.5933 | 1049.4046 | 17.93 |  |  |  | Commercial | Building
Hyper El Temsah | 2018-06-07 | 2019-07-07 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY | Customer/Day | 3312 | 7800 | Total | 167661582 | 168976040.9524 | 141672524.9015 | 16.16% | -51.86% | 21663.595 | 51019.336 | 18163.1442 | 42775.5208 | 1208.2317 | 2845.4733 | 1013.003 | 2385.6955 | 17.93 |  |  |  | Commercial | Building
Marassi Bridge Pkg 117 | 2017-11-13 | 2019-08-13 | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | Length m | 60 | 1080 | All | 44915215.9833 | 45205818 | 31111755 | 31.18% | -8.656% | 41857.2389 | 753430.3 | 28807.1806 | 518529.25 | 2360.8144 | 42494.6588 | 1624.7705 | 29245.8686 | 17.73 |  |  |  | Bridges | Exeternal Work
Siemens Power Station | 2017-11-05 | 2019-12-05 | Industrial | Factory | Turn Key | SIEMENS | Eng Hassan Youssef | Eng Mahmoud Mahlab | Sokhna | S | Private |  |  | 16200 | All | 317512165.921 | 332856409 | 319846012.345 | 3.909% | -6.678% | 20546.6919 | 0 | 19743.581 | 0 | 1158.8659 | 0 | 1113.5691 | 0 | 17.73 |  |  |  | Power Plant | Building
Uptown FM85 Pkg 85 | 2019-01-01 | 2020-01-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Mohamed Bassuony | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All |  |  |  | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.91 |  |  |  | Power Plant | Building
El Sokhna Tunnel 01 | 2018-02-01 | 2018-12-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Sokhna | D | ARMY |  |  | 3604 | All | 46639513 | 46639513 | 37675288 | 19.22% | -25.06% | 12941.0413 | 0 | 10453.7425 | 0 | 729.4837 | 0 | 589.2752 | 0 | 17.74 | 68 | 53 |  | Tunnels | Exeternal Work
Abu Sultan Bridge 01 | 2018-03-01 | 2018-09-30 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 1738 | All | 18754740.365 | 18752986 | 13705181 | 26.92% | -58.62% | 10789.9804 | 0 | 7885.6047 | 0 | 610.9842 | 0 | 446.5235 | 0 | 17.66 | 37 | 47 |  | Bridges | Box Section
Mintra Factory | 2018-02-01 | 2019-01-01 | Industrial | Factory | Civil Works | Mintra | Eng Salah Rashad | Eng. Mohamed Abdel Raouf | Cairo | S | Private |  |  | 52500 | All | 109817542.56 | 112045826 | 113125840.857 | -0.9639% | -4.235% | 2134.2062 | 0 | 2154.7779 | 0 | 120.3047 | 0 | 121.4644 | 0 | 17.74 |  |  |  | Industrials | Building
King Farouk Restoration | 2018-02-01 | 2018-02-11 | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.66 |  |  |  | Renovation | Building
Mohamed Ali Palace | 2018-04-01 | 2022-06-30 | Restoration | Palace | Restoration | Army Forces | Eng Mohamed Saber | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All | 94773524.91 | 150000000 | 125642410.0235 | 16.24% | -25.12% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.66 |  |  |  | Renovation | Building
Nefisha Bridge | 2018-05-02 | 2019-01-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 6900 | All | 70928098.3435 | 70928098 | 51420131 | 27.5% | -2.957% | 10279.4345 | 0 | 7452.1929 | 0 | 575.2342 | 0 | 417.0225 | 0 | 17.87 | 600 | 12 |  | Bridges | Pre cast
Fish Market A | 2018-06-01 | 2019-06-30 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY |  |  | 6400 | Civil | 18799989 | 21507218.7894 | 18864167.0557 | 12.29% | 0% | 3360.5029 | 0 | 2947.5261 | 0 | 187.4235 | 0 | 164.3907 | 0 | 17.93 |  |  |  | Commercial | Building
Fish Market B | 2018-06-01 | 2019-06-30 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY |  |  | 6400 | Arch | 12288687 | 14058278.4353 | 12330637.2394 | 12.29% | 0% | 2196.606 | 0 | 1926.6621 | 0 | 122.5101 | 0 | 107.4547 | 0 | 17.93 |  |  |  | Commercial | Building
Fish Market C | 2018-06-01 | 2019-06-30 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY |  |  | 6400 | MEP | 13497795 | 15441500.0051 | 13543872.8056 | 12.29% | 0% | 2412.7344 | 0 | 2116.2301 | 0 | 134.5641 | 0 | 118.0273 | 0 | 17.93 |  |  |  | Commercial | Building
Fish Market D | 2018-06-01 | 2019-06-30 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY |  |  | 6400 | Machines | 13268050 | 15178671.3417 | 13313343.5186 | 12.29% | 0% | 2371.6674 | 0 | 2080.2099 | 0 | 132.2737 | 0 | 116.0184 | 0 | 17.93 |  |  |  | Commercial | Building
Fish Market | 2018-06-01 | 2019-06-30 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY | Shops | 32 | 6400 | Total | 57854521 | 66185668.5714 | 58052020.6193 | 12.29% | -18.71% | 10341.5107 | 2068302.1429 | 9070.6282 | 1814125.6444 | 576.7714 | 115354.2746 | 505.8911 | 101178.2289 | 17.93 |  |  |  | Commercial | Building
Al Jazi Mall | 2018-05-01 | 2020-02-28 | Commercial | Offices & Mall | Civil Works | YAMM | Eng Mohamed Zaki | Eng. Waleed Barakat | 5th settelment | S | Private |  |  | 48853.59 | Civil | 241102529.6406 | 245977347.1316 | 228488395.4632 | 7.11% | -0.3712% | 5034.9902 | 0 | 4677.0032 | 0 | 281.7566 | 0 | 261.7237 | 0 | 17.87 |  |  |  | Commercial
Benban Aswan Alcazars Solar Park | 2018-06-02 | 2019-07-02 | Industrial | Power Plant | Civil Works | TSK | Eng Amir | Eng Mahmoud Mahlab | Aswan | S | Private | MW | 200 |  | All | 212005783.75 | 212005784 | 118641100 | 44.04% | -2.293% | 0 | 1060028.92 | 0 | 593205.5 | 0 | 59120.4083 | 0 | 33084.5231 | 17.93 |  |  |  | Industrials | Solar Plants
El Alameen Roads Earth Works | 2018-09-15 | 2019-06-15 | Infrastructure | Roads | Civil Works | Army Forces | Eng Mohamed Abd El Nabi | General Mohamed Salah | North Coast | D | ARMY |  |  |  | All | 45583868.7231 | 54192857 | 46001919 | 15.11% | -37.09% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.88 |  |  |  | Bridges
El Sewedy Univeristy A | 2019-10-10 | 2020-12-10 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | Student | 300 | 4975 | Civil | 51296891.54 | 53088714.8227 | 47141962.0372 | 11.2% | 0% | 10671.0985 | 176962.3827 | 9475.7713 | 157139.8735 | 593.8285 | 9847.6562 | 527.3106 | 8744.5672 | 17.97 |  |  |  | Commercial | Building
El Sewedy Univeristy B | 2019-10-10 | 2020-12-10 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | Student | 300 | 4975 | Arch | 107726254 | 111489180.062 | 99000676.7276 | 11.2% | 0% | 22409.8854 | 371630.6002 | 19899.6335 | 330002.2558 | 1247.0721 | 20680.6121 | 1107.3808 | 18364.0654 | 17.97 |  |  |  | Commercial | Building
El Sewedy Univeristy C | 2019-10-10 | 2020-12-10 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | Student | 300 | 4975 | MEP | 94500000 | 97800927.1153 | 86845718.6932 | 11.2% | 0% | 19658.4778 | 326003.0904 | 17456.4259 | 289485.729 | 1093.9609 | 18141.5187 | 971.4205 | 16109.3895 | 17.97 |  |  |  | Commercial | Building
El Sewedy Univeristy 2 phase 2 | 2019-10-10 | 2020-12-10 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | Student | 300 | 14500 | Total | 253523145.54 | 262378822 | 232988357.458 | 11.2% | 6.936% | 18095.0912 | 874596.0733 | 16068.1626 | 776627.8582 | 1006.9611 | 48669.7871 | 894.166 | 43218.0222 | 17.97 |  |  | 3500 | Commercial | Building
El Sokhna Tunnel L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Sokhna | D | ARMY |  |  |  | All |  |  |  | 0% | #DIV/0! | 0 | 0 |  |  | 0 | 0 |  |  | 5.36
R05 Residential District Z1 & Z2 | 2018-07-16 | 2022-05-16 | Residential | Residential | Turn Key | Utilities And Urban Communities | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | New Capital | D | Public |  |  | 418237 | Civil | 2949277335 | 3200000000 | 2976000000 | 7% | 0% | 7651.1643 | 0 | 7115.5828 | 0 | 426.7242 | 0 | 396.8535 | 0 | 17.93
Abu Sultan Bridge 02 Greenhouse | 2018-09-01 | 2019-06-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 476 | All | 67755600 | 67755600 | 59506484.6859 | 12.17% | -22.79% | 142343.6975 | 0 |  |  | 8005.8323 | 0 |  |  | 17.78
El Sokhna Tunnel 02 | 2018-09-01 | 2019-04-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Sokhna | D | ARMY |  |  | 1813 | All | 22334150 | 22334150 | 17647987 | 20.98% | -30.12% | 12318.8913 | 0 | 9734.1351 | 0 | 686.6718 | 0 | 542.5939 | 0 | 17.94 | 90 | 20 |  | Tunnels | Exeternal Work
El Awsty Middle Tunnel L&L | 2018-12-01 | 2019-04-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 1024820 | 1024820 | 819856 | 20% | -18.67% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.14 |  |  |  | L&L
Sodic Eastown EDNC A | 2019-03-25 | 2021-12-24 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Sayed Osman | Eng. Waleed Barakat | 5th settelment | D | Private |  |  | 156000 | Civil | 471569378 | 498109248.2406 | 468222693.3461 | 6% | 0% | 3193.008 | 0 | 3001.4275 | 0 | 181.524 | 0 | 170.6326 | 0 | 17.59 |  |  |  | Commercial | Building
Sodic Eastown EDNC B | 2019-03-25 | 2021-12-24 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Sayed Osman | Eng. Waleed Barakat | 5th settelment | D | Private |  |  | 156000 | Arch | 126180994 | 133282445.7986 | 125285499.0507 | 6% | 0% | 854.3747 | 0 | 803.1122 | 0 | 48.5716 | 0 | 45.6573 | 0 | 17.59 |  |  |  | Commercial | Building
Sodic Eastown EDNC C | 2019-03-25 | 2021-12-24 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Sayed Osman | Eng. Waleed Barakat | 5th settelment | D | Private |  |  | 156000 | MEP | 419541619 | 443153372.9608 | 416564170.5831 | 6% | 0% | 2840.7267 | 0 | 2670.2831 | 0 | 161.4967 | 0 | 151.8069 | 0 | 17.59 |  |  |  | Commercial | Building
Sodic Eastown EDNC | 2019-03-25 | 2021-12-24 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Sayed Osman | Eng. Waleed Barakat | 5th settelment | D | Private | 0 | 0 | 156000 | Total | 1017291991 | 1074545067 | 1010072362.98 | 6% | -0.04621% | 6888.1094 | 0 | 6474.8228 | 0 | 391.5923 | 0 | 368.0968 | 0 | 17.59 |  |  |  | Commercial | Building
Marassi Civic Center Pkg 144 A | 2018-11-01 | 2019-08-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private |  |  | 12500 | Civil | 28591006.1697 | 31382045.1953 | 21744199.5882 | 30.71% | 0% | 2510.5636 | 0 | 1739.536 | 0 | 141.5998 | 0 | 98.1126 | 0 | 17.73 |  |  |  | Residual | Mporium
Marassi Civic Center Pkg 144 B | 2018-11-01 | 2019-08-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private |  |  | 12500 | Arch | 57415590.1512 | 63020469.9457 | 43666041.1428 | 30.71% | 0% | 5041.6376 | 0 | 3493.2833 | 0 | 284.3563 | 0 | 197.0267 | 0 | 17.73 |  |  |  | Residual | Mporium
Marassi Civic Center Pkg 144 C | 2018-11-01 | 2019-08-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private |  |  | 12500 | MEP | 74723400.6791 | 82017859.859 | 56829078.649 | 30.71% | 0% | 6561.4288 | 0 | 4546.3263 | 0 | 370.0749 | 0 | 256.42 | 0 | 17.73 |  |  |  | Residual | Mporium
Marassi Civic Center Pkg 144 | 2018-11-01 | 2019-08-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private |  |  | 12500 | Total | 160729997 | 176420375 | 122239319.38 | 30.71% | -17.71% | 14113.63 | 0 | 9779.1456 | 0 | 796.031 | 0 | 551.5593 | 0 | 17.73 |  |  |  | Residual | #REF!
Marassi Civic Center Pkg 144 D | 2018-11-01 | 2019-08-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | Car Capacity | 450 | 6600 | All | 160729997 | 176420375 | 122239319.38 | 30.71% | 0% | 26730.3598 | 392045.2778 | 18521.109 | 271642.932 | 1507.6345 | 22111.9728 | 1044.6198 | 15321.0904 | 17.73 |  |  |  |  | Park
DPW Sokhna Dubai Port | 2018-11-16 | 2021-07-16 | Infrastructure | Networks | EPC | DPW | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Sokhna | D | Private | Container Slots | 9190 | 600000 | All | 1557966434.4861 | 1633315425 | 1246507144.6956 | 23.68% | -0.0958% | 2722.1924 | 177727.4674 | 2077.5119 | 135637.3389 | 152.2479 | 9940.015 | 116.1919 | 7585.9809 | 17.88 |  |  |  | Port | Building
Slope Stablization PKG 101 | 2018-10-11 | 2020-11-10 | Infrastructure | L&L | Civil Works | EMAAR | Eng Mohamed Bassuony | Eng Mahmoud Mahlab | Cairo | D | Private |  |  | 11305 | All | 40371611 | 52028085.7143 | 47340355.1914 | 9.01% | 45.19% | 4602.219 | 0 | 4187.5591 | 0 | 256.2483 | 0 | 233.1603 | 0 | 17.96 |  |  |  | L&L
Elco Steel Substation | 2018-05-01 | 2019-04-01 | Industrial | Power Plant | Turn Key | Elco Suez | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Private | KW | 220 |  | All | 31790191.494 | 32341773 | 34798196.7776 | -7.595% | 0% | 0 | 147008.0591 | 0 | 158173.6217 | 0 | 8180.749 | 0 | 8802.0936 | 17.97
Sewab Greenhouse Tunnel | 2018-09-01 | 2019-06-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 476 | All | 11220000 | 10957813.825 | 9623720.8521 | 12.17% | -0.02996% | 23020.6173 | 0 | 20217.9009 | 0 | 1294.7479 | 0 | 1137.1148 | 0 | 17.78 | 28 | 17 |  | Tunnels
Mivida Irrigation Treatment Plant Pkg 140 | 2019-01-14 | 2021-07-14 | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng. Waleed Barakat | 5th settelment | D | Private | Water be treated m3/ hour For 16 hours / day | 680 | 12350 | All | 168347427 | 170057475.6641 | 136045980.5313 | 20% | -0.03293% | 13769.8361 | 250084.523 | 11015.8689 | 200067.6184 | 770.1251 | 13986.8301 | 616.1 | 11189.4641 | 17.88 |  |  |  |  | Irrigation Treatment Plant
Mivida Irrigation Treatment Plant Pkg 140 | 2019-01-14 | 2021-07-14 | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng. Waleed Barakat | 5th settelment | D | Private | Tank Volume m3 | 10600 | 12350 | All | 168347427 | 170057475.6641 | 136045980.5313 | 20% | -0.03293% | 13769.8361 | 16043.1581 | 11015.8689 | 12834.5265 | 770.1251 | 897.2683 | 616.1 | 717.8147 | 17.88 |  |  |  |  | Treatment Tank
Multi Sports Hall A | 2019-08-30 | 2022-05-31 | Commercial | Stadium | EPC | Army Forces | Eng Adel Rahmo | Eng Mahmoud Mahlab | New Capital | D | ARMY | Chair | 15000 | 18000 | Civil | 522000000 | 522000000 | 495900000 | 5% | 0% | 29000 | 34800 | 27550 | 33060 | 1782.4216 | 2138.906 | 1693.3006 | 2031.9607 | 16.27
Multi Sports Hall B | 2019-08-30 | 2022-05-31 | Commercial | Stadium | EPC | Army Forces | Eng Adel Rahmo | Eng Mahmoud Mahlab | New Capital | D | ARMY | Chair | 15000 | 18000 | Arch | 271200000 | 271200000 | 257640000 | 5% | 0% | 15066.6667 | 18080 | 14313.3333 | 17176 | 926.0397 | 1111.2477 | 879.7378 | 1055.6853 | 16.27
Multi Sports Hall C | 2019-08-30 | 2022-05-31 | Commercial | Stadium | EPC | Army Forces | Eng Adel Rahmo | Eng Mahmoud Mahlab | New Capital | D | ARMY | Chair | 15000 | 18000 | MEP | 406800000 | 406800000 | 386460000 | 5% | 0% | 22600 | 27120 | 21470 | 25764 | 1389.0596 | 1666.8715 | 1319.6066 | 1583.528 | 16.27
Multi Sports Hall | 2019-08-30 | 2022-05-31 | Commercial | Stadium | EPC | Army Forces | Eng Adel Rahmo | Eng Mahmoud Mahlab | New Capital | D | ARMY | Chair | 15000 | 18000 | Total | 1200000000 | 1200000000 | 1140000000 | 5% | -0.6711% | 66666.6667 | 80000 | 63333.3333 | 76000 | 4097.521 | 4917.0252 | 3892.6449 | 4671.1739 | 16.27 |  |  |  | 0 | 0
EGAT | 2019-04-30 | 2019-12-30 | Industrial | Factory | Turn Key | Sewedy | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Affiliates |  |  |  | All | 65831906 | 65831906 | 56811131 | 13.7% | 33.42% | 0 | 0 |  |  | 0 | 0 |  |  | 17.14
Abou Ghazala Bridge Ramp L&L | 2019-03-15 | 2019-07-15 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 980186.2937 | 1688453 | 1511719 | 10.47% | -18.29% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.59 |  |  |  | L&L
Mohamed Ali Fahmy Ramps L&L | 2019-03-15 | 2019-12-15 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 3670033.532 | 7149700 | 6713205 | 6.105% | -0.7128% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.59 |  |  |  | L&L
El Mosheer Bridge Abu Zaied Khdr L&L | 2018-10-01 | 2019-03-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 4203687 | 4203687 | 2001684 | 52.38% | -58.21% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.97 |  |  |  | L&L
Ora Zed Park L&L | 2019-07-01 | 2019-11-01 | Infrastructure | L&L | Civil Works | Ora | Eng Adham Edward | Eng.adham edward | 6th of October | D | Private |  |  |  | All | 1100000 | 1042542 | 758212.27 | 27.27% | -135.2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.27 |  |  |  | L&L
DoubleTree Mangroovy El Gouna Hotel | 2019-08-22 | 2021-08-22 | Commercial | Hotel | Civil Works | Sewedy | Eng Sherif El Sisi | Eng. Mohamed Fawzy | Gouna | D | Affiliates |  |  | 18352 | All | 44797273 | 57898699.39 | 54424777.4266 | 6% | -1.679% | 3154.8986 | 0 | 2965.6047 | 0 | 192.9602 | 0 | 181.3826 | 0 | 16.35 |  |  |  |  | Building
Baron Palace Fence | 2020-02-01 | 2020-07-01 | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All | 6306643.0958 | 16220552 | 14434567.4488 | 11.01% | -67.43% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 |  |  |  | L&L
Safeer Square Bridge | 2019-08-01 | 2019-12-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 6750 | All | 95436549 | 95436549 | 82927091 | 13.11% | -37.73% | 14138.748 | 0 | 12285.495 | 0 | 864.7552 | 0 | 751.4064 | 0 | 16.35 | 250 | 27 |  | Bridges | Exeternal Work
Suez Road Tunnel Res L&L | 2019-08-20 | 2019-10-20 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 3270317.6497 | 4423592 | 4769909 | -7.829% | -17.36% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 |  |  |  | L&L
HyperOne Zayed Extention | 2019-10-13 | 2020-12-13 | Commercial | Parking | Civil Works | Hyper | Eng Tarek Ramadan | Eng. Mohamed Fawzy | 6th of October | D | Private | Parking Capacity | 510 | 30000 | All | 135000000 | 133583770 | 99106552.4453 | 25.81% | -0.1061% | 4452.7923 | 261928.9608 | 3303.5517 | 194326.5734 | 273.6812 | 16098.8913 | 203.0456 | 11943.8582 | 16.27
IKEA Extention MoA | 2019-10-01 | 2020-11-30 | Commercial | Offices & Mall | Turn Key | Marakez | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private |  |  | 19836 | All | 52793757.1332 | 196190620 | 212380869 | -8.252% | -10.96% | 9890.6342 | 0 | 10706.8395 | 0 | 607.9062 | 0 | 658.0725 | 0 | 16.27 |  |  |  | Commercial | Building
CFC Podium II A | 2019-10-01 | 2021-07-30 | Commercial | Offices & Mall | Core And Shell | Al-Futtaim | Eng Amir | Eng. Waleed Barakat | 5th settelment | S | Private | Offices | 300 | 98633 | Civil | 389765966 | 635000000 | 524290213.0394 | 17.43% | 0% | 6438.0076 | 2116666.6667 | 5315.5659 | 1747634.0435 | 395.6981 | 130096.2917 | 326.7096 | 107414.5079 | 16.27 |  |  |  | Residual | Building
CFC Podium II B | 2019-10-01 | 2021-07-30 | Commercial | Offices & Mall | Core And Shell | Al-Futtaim | Eng Amir | Eng. Waleed Barakat | 5th settelment | S | Private | Offices | 300 | 98633 | Arch | 146804895 | 635000000 | 524290213.0394 | 17.43% | 0% | 6438.0076 | 2116666.6667 | 5315.5659 | 1747634.0435 | 395.6981 | 130096.2917 | 326.7096 | 107414.5079 | 16.27 |  |  |  | Residual | Building
CFC Podium II C | 2019-10-01 | 2021-07-30 | Commercial | Offices & Mall | Core And Shell | Al-Futtaim | Eng Amir | Eng. Waleed Barakat | 5th settelment | S | Private | Offices | 300 | 98633 | MEP | 17553800 | 635000000 | 524290213.0394 | 17.43% | 0% | 6438.0076 | 2116666.6667 | 5315.5659 | 1747634.0435 | 395.6981 | 130096.2917 | 326.7096 | 107414.5079 | 16.27 |  |  |  | Residual | Building
CFC Podium II | 2019-10-01 | 2021-07-30 | Commercial | Offices & Mall | Core And Shell | Al-Futtaim | Eng Amir | Eng. Waleed Barakat | 5th settelment | S | Private | Offices | 300 | 98633 | Total | 559510195 | 635000000 | 524290213.0394 | 17.43% | -2.103% | 6438.0076 | 2116666.6667 | 5315.5659 | 1747634.0435 | 363.1138 | 119383.3427 | 299.8063 | 98569.32 | 17.73 |  |  |  | Residual | #REF!
Mostafa Kamel Bridge L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 5.36
Josef Tito Bridge L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | #DIV/0! | 0 | 0 |  |  | 0 | 0 |  |  | 5.36
Espiko Bridge L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | #DIV/0! | 0 | 0 |  |  | 0 | 0 |  |  | 5.36
El Gabal El Asfr Tunnel L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 5.36
MR3 Bridge L&L | 2019-10-19 | 2019-12-19 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 1520085 | 1520085 | 1367204 | 10.06% | -30.72% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.27 |  |  |  | L&L
El Sewedy Univeristy 2 Phase 2 A | 2018-09-09 | 2019-09-09 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | People Served | 900 | 56000 | Civil | 92770189.4948 | 98488667.2653 | 84700253.7786 | 14% | 0% | 1758.7262 | 109431.8525 | 1512.5045 | 94111.3931 | 97.8701 | 6089.6969 | 84.1683 | 5237.1393 | 17.97 |  |  |  | Commercial | Building | 70446064
El Sewedy Univeristy 2 Phase 2 B | 2018-09-09 | 2019-09-09 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | People Served | 900 | 56000 | Arch | 155706225.0673 | 165304163.7115 | 142161580.675 | 14% | 0% | 2951.8601 | 183671.293 | 2538.5997 | 157957.3119 | 164.266 | 10220.9957 | 141.2688 | 8790.0563 | 17.97 |  |  |  | Commercial | Building | 118237235
El Sewedy Univeristy 2 Phase 2 C | 2018-09-09 | 2019-09-09 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | People Served | 900 | 56000 | MEP | 311033780.438 | 330206316.0231 | 283977431.5464 | 14% | 0% | 5896.5414 | 366895.9067 | 5071.0256 | 315530.4795 | 328.1325 | 20417.1345 | 282.194 | 17558.7356 | 17.97 |  |  |  | Commercial | Building | 236186923
El Sewedy University 1 | 2018-09-09 | 2019-09-09 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affiliates | People Served | 900 | 38447 | Total | 559510195 | 593999147 | 510839266 | 14% | 0.3863% | 15449.8179 | 659999.0522 | 13286.8433 | 567599.1844 | 871.3941 | 37224.9888 | 749.3989 | 32013.4904 | 17.73 |  |  |  | Commercial | #REF! | 424870222
Mehwar El Salam Axis L&L | 2019-10-01 | 2020-02-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 16843027 | 16843027 | 15775883 | 6.336% | -13.47% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.27 |  |  |  | L&L
El Hegaz Square Bridge | 2019-12-05 | 2020-04-05 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 9450 | All | 138370050 | 138370050 | 121772563 | 11.99% | -24.13% | 14642.3333 | 0 | 12885.9855 | 0 | 899.959 | 0 | 792.0089 | 0 | 16.27 | 350 | 27 |  | Bridges | Pre cast + box section
Ring Road | 2020-02-01 | 2022-03-30 | Infrastructure | Bridges & Tunnels | Civil Works | Roads and Bridges Authority | Eng Abd El Naby Shaban | Eng Hussien Bahgat | Cairo | D | Public |  |  | 63600 | All | 771935871 | 524000000 | 492560000 | 6% | -8.855% | 8238.9937 | 0 |  | 0 | 503.914 | 0 |  |  | 16.35
Marina Inland Marassi Pkg 162 | 2020-02-02 | 2022-03-02 | Infrastructure | Port | Civil Works | EMAAR | Eng Reda | Eng. Mohamed Fawzy | North Coast | D | Private |  |  |  | All | 434504076.4286 | 434504076.4286 | 354989830.4421 | 18.3% | -0.2596% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.35
Sultana Malek Restoration | 2020-08-01 | 2022-06-01 | Restoration | Palace | Restoration | Army Forces | Eng Karem Ehab | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All | 85000000 | 85000000 | 72250000 | 15% | -9.795% | 0 | 0 |  |  | 0 | 0 |  |  | 15.93
Lekela 250MW Wind Farm | 2020-06-03 | 2021-06-04 | Industrial | Power Plant | Civil Works | GAMESA | Eng Marwan Shibl | Eng. Waleed Barakat | Gabal El Zeit | D | Private | MW | 250 |  | All | 119626844 | 182442342 | 178793495.16 | 2% | -22.81% | 0 | 729769.368 | 0 | 715173.9806 | 0 | 42927.6099 | 0 | 42069.0577 | 17
New Giza Hospital | 2021-09-30 | 2023-09-30 | Commercial | Hospital | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private | bed | 164 | 23000 | All | 542690000 | 542690000 | 507186915.8879 | 6.542% | 0% | 23595.2174 | 3309085.3659 | 22051.605 | 3092603.1457 | 0 | 0 | 0 | 0
Kayan Landscape | 2019-06-01 | 2020-03-01 | Infrastructure | Landscape | Civil Works | Army Forces | Eng Adel Rahmo | Eng. Omar Sobhy | New Capital | D | ARMY |  |  |  | All | 100042648 | 100042648 | 93060671.3161 | 6.979% | -5.118% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.74
Abbas Akkad Bridge | 2020-02-01 | 2020-06-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 15600 | All | 135000000 | 124132580.9524 | 122869821.99 | 1.017% | -14.12% | 7957.2167 | 0 | 7876.2706 | 0 | 486.6799 | 0 | 481.7291 | 0 | 16.35 | 600 | 26 |  | Bridges
El Asher Men Ramadan Bridge | 2020-02-28 | 2020-06-30 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mostafa Diab | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 4200 | All | 84354414 | 93910355 | 85732351.721 | 8.708% | -73.34% | 22359.6083 | 0 | 20412.4647 | 0 | 1367.5601 | 0 | 1248.4688 | 0 | 16.35
Kafr Shokr Bridge | 2020-08-15 | 2021-08-15 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Ahmed El Adawy | Eng Hussien Bahgat | qlyboya | D | ARMY |  |  | 16900 | All | 191000000 | 147845325 | 133974586 | 9.382% | -29.84% | 8748.2441 | 0 | 7927.4903 | 0 | 549.1679 | 0 | 497.6453 | 0 | 15.93
Al Shorouk Bridge (LRT) | 2020-05-09 | 2021-02-08 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 7070 | All | 40774553.92 | 26145782 | 24180000 | 7.519% | -27.51% | 3698.1304 | 0 | 3420.0849 | 0 | 237.669 | 0 | 219.7998 | 0 | 15.56
GOV2 Infra | 2020-06-01 | 2021-12-01 | Infrastructure | Networks | Civil Works | Utilities And Urban Communities | Eng Mohamed Abd El Moktader | Eng Mohamed Abd El Fatah | New Capital | D | Public | ACRE | 1500 |  | All | 650000000 | 650000000 | 607750000 | 6.5% | -3.932% | 0 | 433333.3333 | 0 | 405166.6667 | 0 | 25490.1961 | 0 | 23833.3333 | 17
Cairo Alex Railroad | 2020-10-15 | 2022-10-15 | Infrastructure | Railway | Civil Works | ENR | Eng Ali Tawfeek | Eng.callum | alex | S | Public | KM RAIL | 35 |  | All | 1350000000 | 967000000 | 879970000 | 9% | -0.06423% | 0 | 27628571.4286 | 0 | 25142000 | 0 | 1758661.4531 | 0 | 1600381.9223 | 15.71
Hassan El Mamoun Bridge | 2020-06-01 | 2020-09-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mostafa Diab | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 13440 | All | 124285762 | 93800000 | 88756688.976 | 5.377% | -73.64% | 6979.1667 | 0 | 6603.9203 | 0 | 410.5392 | 0 | 388.4659 | 0 | 17
Sherouk Bridge L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 1000000 | 1000000 | 1648128.4931 | -64.81% | -60.69% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36
Ora Zed Park 1B Pkgs A&D | 2020-09-28 | 2023-06-28 | Residential | Residential | Turn Key | Ora | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private | no of apr | 320 | 75500 | All | 870293108.0057 | 870293108 | 808937442.9565 | 7.05% | -4.664% | 11527.061 | 2719665.9625 | 10714.4032 | 2527929.5092 | 732.3419 | 172786.9099 | 680.7118 | 160605.4326 | 15.74
Kattameya Creeks | 2021-01-15 | 2024-01-15 | Residential | Residential | Turn Key | Starlight | Eng Mohamed Kamal | Eng. Waleed Barakat | 5th settelment | S | Private |  |  | 140150 | All | 1462000000 | 1462000000 | 1352350000 | 7.5% | -0.129% | 10431.6803 | 0 | 9649.3043 | 0 | 658.5657 | 0 | 609.1733 | 0 | 15.84
Mansoura University Faculty of Medicine | 2021-01-01 | 2021-12-31 | Commercial | University | Civil Works | Utilities And Urban Communities | Eng Emad Habi | Eng Mohamed Abd El Fatah | mansoura | D | Public |  |  | 40000 | All | 219047619.0476 | 219047619.0476 | 203714285.7143 | 7% | -2.204% | 5476.1905 | 0 | 5092.8571 | 0 | 345.7191 | 0 | 321.5188 | 0 | 15.84
Diplomatic District - Infra | 2021-01-01 | 2022-01-01 | Infrastructure | Networks | Civil Works | Utilities And Urban Communities | Eng Mohamed Abd El Moktader | Eng Mohamed Abd El Fatah | New Capital | D | Public | ACRE | 1600 |  | All | 390000000 | 390000000 | 364650000 | 6.5% | -0.6544% | 0 | 243750 | 0 | 227906.25 | 0 | 15388.2576 | 0 | 14388.0208 | 15.84
El Sewedy CFC HQ Internal Finishing | 2020-12-08 | 2022-06-08 | Commercial | Offices & Mall | Turn Key | Sewedy | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 5th settelment | D | Affiliates |  |  | 23500 | All | 327718153.3333 | 327718153.3333 | 302367726 | 7.735% | 18.06% | 13945.4533 | 0 | 12866.7117 | 0 | 889.946 | 0 | 821.1048 | 0 | 15.67
Lagoon Discharge Pkg 178 | 2020-12-28 | 2021-07-30 | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Reda | Eng. Mohamed Fawzy | North Coast | D | Private |  |  |  | All | 40449240 | 40449240 | 35085670.776 | 13.26% | -4.132% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.67
El Khatatba Bridge | 2021-06-01 | 2022-06-01 | Infrastructure | Bridges & Tunnels | Civil Works | Roads and Bridges Authority | Eng Khaled Tawfek | Eng Hussien Bahgat | qlyboya | D | Public |  |  | 9940 | All | 165000000 | 142857142.8571 | 130845321 | 8.408% | -0.3637% | 14371.946 | 0 | 13163.5132 | 0 | 0 | 0 | 0 | 0
EGAT Pelletizing Plant | 2021-06-01 | 2022-06-01 | Industrial | Factory | Turn Key | Elco Suez | Eng Mohamed Fadel | Eng. mohamed el seman | Suez | D | Private |  |  |  | All | 375000000 | 375000000 | 341250000 | 9% | 2.659% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sokhna Port Expansion | 2021-06-01 | 2022-06-01 | Infrastructure | Port | Civil Works | Transportation Ministry | Eng Tarek Ramadan | Eng. mohamed el seman | Sokhna | S | Public | KM | 12 |  | All | 1100000000 | 1100000000 | 1023000000 | 7% | -0.1471% | 0 | 91666666.6667 | 0 | 85250000 | 0 | 0 | 0 | 0
MDF Factory | 2021-03-06 | 2022-05-05 | Industrial | Factory | Turn Key | Naile Wood | Eng Bader Osman | Eng. mohamed el seman | sadat | S | Private |  |  | 23710 | All | 175000000 | 175000000 | 162750000 | 7% | -0.09627% | 7380.852 | 0 | 6864.1923 | 0 | 469.2214 | 0 | 436.3759 | 0 | 15.73
Olympic City L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36
Kemet Building | 2021-03-30 | 2021-10-30 | Commercial | Offices & Mall | Civil Works | Kemet | Eng Hany Yassin | Eng. Mohamed Ashry | New Capital | S | Private |  |  | 21460 | All | 71052428.57 | 71052428.57 | 66078758.5701 | 7% | 0% | 3310.924 | 0 | 3079.1593 | 0 | 211.5606 | 0 | 196.7514 | 0 | 15.65
Point 90 New Cairo Mall A | 2013-09-19 | 2015-09-18 | Commercial | Offices & Mall | Turn Key | Cairo Company for Housing & Development (CCHD) | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | No of Shops | 75 | 69132.17 | Arch | 82055230.75 | 81349214.5901 | 72488400.8195 | 10.89% | 0% | 1176.7201 | 1084656.1945 | 1048.548 | 966512.0109 | 173.8139 | 160215.0952 | 154.8815 | 142763.9603 | 6.77 |  |  | 17442.21
Point 90 New Cairo Mall B | 2013-09-19 | 2015-09-18 | Commercial | Offices & Mall | Turn Key | Cairo Company for Housing & Development (CCHD) | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | No of Shops | 75 | 69132.17 | MEP | 64214220.38 | 63661711.0899 | 56727476.1483 | 10.89% | 0% | 920.8696 | 848822.8145 | 820.5655 | 756366.3486 | 136.0221 | 125380.0317 | 121.2061 | 111723.242 | 6.77 |  |  | 17442.21
Point 90 New Cairo Mall | 2013-09-19 | 2015-09-18 | Commercial | Offices & Mall | Turn Key | Cairo Company for Housing & Development (CCHD) | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | No of Shops | 75 | 69132.17 | Total | 146269451.13 | 145010925.68 | 129215876.9678 | 10.89% | -4.504% | 2097.5897 | 1933479.0091 | 1869.1136 | 1722878.3596 | 309.836 | 285595.1269 | 276.0877 | 254487.2023 | 6.77 |  |  |  | 0 | #REF!
Marassi Bridges Pkg 37 | 2012-08-01 | 2014-06-01 | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Waleed Tag | Eng Mahmoud Mahlab | North Coast | D | Private |  |  |  | All | 27187290 | 26193836.68 | 27330602.3975 | -4.34% | -4.551% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.09
Marassi Golf Maintance Building Pkg 58 | 2013-03-19 | 2015-01-18 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Waleed Tag | Eng Mahmoud Mahlab | North Coast | D | Private |  |  |  | All | 5325286 | 4720405.25 | 5275181.8987 | -11.75% | -53.16% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77
Uptown Soil Stabilization Pkg 32 | 2012-08-05 | 2015-05-05 | Infrastructure | L&L | Civil Works | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All | 5983238.64 | 17421145.8 | 21051883.5147 | -20.84% | -9.18% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.09
Ismailia Bridge L&L | 2018-12-29 | 2019-03-29 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  |  | All | 49485210.2 | 49485210.2 | 39588168 | 20% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.04 |  |  |  | L&L
El Obour Bridge B2 | 2014-07-30 | 2014-12-30 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Cairo | D | ARMY |  |  | 735 | All | 9000000 | 9000000 | 7200000 | 20% | 0% | 12244.898 | 0 | 9795.9184 | 0 | 1712.5731 | 0 | 1370.0585 | 0 | 7.15 | 35 | 21 |  | Bridges | Pre cast
Autoville Strip Mall | 2010-04-28 | 2014-04-28 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 39524132 | 51072634 | 55255998 | -8.191% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36
Uptown Service Buildings Pkg 17A | 2011-07-27 | 2013-12-26 | Infrastructure | Tank | Civil Works | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All | 56114398 | 55905931 | 53843629.5863 | 3.689% | -5.71% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.66
Sodic West Town Hub | 2013-01-01 | 2015-12-31 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 28850000 | 54160920.41 | 56137642.32 | -3.65% | 1.874% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 |  |  |  | Commercial
Dubai Port Sokhna Basin 1 | 2013-06-01 | 2015-09-01 | Infrastructure | Networks | Civil Works | DPW | Eng Karim El Far | Eng. Omar Sobhy | Sokhna | D | Private |  |  |  | All | 34548331.29 | 34548331.29 | 27990071.4837 | 18.98% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 |  |  |  | Port
Alexandria Bridges | 2010-10-01 | 2012-12-31 | Infrastructure | Bridges & Tunnels | Civil Works | Mohamed Abd El Wahab | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Alex | S | Private | m | 630 | 9135 | All | 32000000 | 35589876.5 | 28766462 | 19.17% | 0% | 3895.9909 | 56491.8675 | 3149.038 | 45661.0508 | 726.864 | 10539.5275 | 587.5071 | 8518.8528 | 5.36 | 630 | 15 |  | Bridges | Box Section
El Mahala Bridge | 2014-11-30 | 2015-11-30 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed Mostafa | Eng. Omar Sobhy | Mahalla | D | ARMY |  |  | 7830 | All | 68000000 | 67245402 | 48126832 | 28.43% | -13.37% | 8588.1739 | 0 | 6146.4664 | 0 | 1201.1432 | 0 | 859.6457 | 0 | 7.15 | 540 | 15 |  | Bridges | Cast in situe + Cantilever Carriage
El Wahat Bridge | 2015-02-16 | 2015-12-16 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | 6th of October | D | ARMY | m | 35 | 735 | All | 28176166.3603 | 22540933.0883 | 18032746.4706 | 20% | 0% | 30667.9362 | 644026.6597 | 24534.3489 | 515221.3277 | 3916.7224 | 82251.1698 | 3133.3779 | 65800.9359 | 7.83 | 35 | 21 |  | Bridges | Cast in situ + Piles
El Wahat Tunnel | 2015-02-16 | 2015-12-16 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | 6th of October | D | ARMY | m | 60 | 3000 | All | 18275304 | 18818015.28 | 13923981.6424 | 26.01% | 0% | 6272.6718 | 313633.588 | 4641.3272 | 232066.3607 | 801.1075 | 40055.3752 | 592.7621 | 29638.1048 | 7.83 | 60 | 50 |  | Tunnels
El Asmarat | 2014-06-14 | 2015-09-14 | Commercial | Offices & Mall | Civil Works | Arabian Group | Eng Karim El Far | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All | 6636851 | 6636851 | 8517150.2182 | -28.33% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.15
Alegria DP Port | 2017-11-24 | 2021-12-24 | Infrastructure | Networks | Civil Works | DPW | Eng Mohamed Mostafa | Eng. Omar Sobhy | Alegria | D | Private |  |  |  | All | 605714038 | 605714038 | 498059352 | 17.77% | -0.2552% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.73
El Alameen Bridge L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36
El Asher of Ramadan Bridge L&L | 2010-01-01 | 2010-01-01 | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36
EMEC | 2011-03-20 | 2012-03-20 | Commercial | Offices & Mall | Civil Works | EMEC | Eng Mohamed Abd El Fatah | Eng Mahmoud Mahlab | 5th settelment | S | Private |  |  |  | All | 10688481.1 | 10688481.1 | 8907067.5833 | 16.67% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.86
Logestica Phase 01 | 2011-12-18 | 2013-08-18 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 31805400 | 31905026.19 | 27743501.0348 | 13.04% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.05
Logestica Phase 02 | 2013-12-18 | 2015-02-18 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 20681422 | 20681422 | 16069494.51 | 22.3% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77
Logestica Phase 03 | 2013-12-18 | 2015-02-18 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 4820461 | 4820461 | 3681383 | 23.63% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77
Sodic MV Cables | 2014-12-30 | 2015-12-30 | Infrastructure | Networks | Civil Works | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 19589518 | 19589518 | 16384636.8472 | 16.36% | 2.678% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.15
Limak TB2 Cairo Airport Terminal | 2013-02-13 | 2015-11-13 | Commercial | Terminal | Civil Works | Limak | Eng Mohamed El Saman | Eng. Omar Sobhy | Cairo | S | Private |  |  |  | All | 49359671.05 | 119626844 | 96755558 | 19.12% | 57.6% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77
Twin Towers | 2011-06-30 | 2015-06-30 | Commercial | Offices & Mall | Turn Key | Arabian Group | Eng Karim El Far | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 64000000.23 | 64000000.23 | 63714421.967 | 0.4462% | 2.785% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36
Aeon Towers Chiller Building | 2019-10-01 | 2020-11-30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | All |  |  |  | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.31
Electric Train LRT | 2018-11-01 | 2022-12-30 | Industrial | Factory | Turn Key | NAT | Eng Hassan | Eng Mahmoud Mahlab | Cairo | S | Public |  |  |  | All |  |  |  | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.89
Sea Shell Playa | 2021-01-01 | 2024-12-30 | Residential | Residential | Turn Key | New Giza | Eng Wael Ragabi | Eng. Omar Sobhy | North Coast | D | Private |  |  |  | All |  |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.84
Subtotal | [5 empty] | + | [9 empty] | 38025576572.8541 | 41919563519.2322 | 37942183059.9224 | 9.488% | 100%
[16 empty] | 30023489280.809 | 31379002901.837
133.6%

## Metrics Total
Project | Project Start | Project Finish | Category Code | Main Category | Sub Category | Scope | Client | Project Manager | Area Manager | Location | S/D Client | Client Type | Unit | Outcome | Area | Type | Original Contract Value | Revised Contract Value | EAC / Cost From POC | Gross % | Price/m2 | Price/Unit | Cost/m2 | Cost/Unit | Price $/m2 | Price $/Unit | Cost $/m2 | Cost $/Unit | $ Value | Revised Contract/$ | EAC/$ | year
Marassi Civic Center Pkg 45 | 2012-11-13 | 2015-11-13 | Construction | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | North Coast | D | Private |  |  | 6743 | All | 51530647 | 56931016 | 64758247.2535 | -13.75% | 8442.9803 | 0 | 9603.7739 | 0 | 1386.3679 | 0 | 1576.9744 | 0 | 6.09 | 9348278.4893 | 10633538.1369 | 2012
Al Oula Infra | 2012-02-06 | 2015-06-06 | Transportation | Infrastructure | Networks | Civil Works | Sewedy | Eng Hany Fareed | Eng. yasser el saadny | 6th of October | D | Affilates |  |  |  | All | 33000000 | 72946445.96 | 66087308.6012 | 9.403% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.09 | 11978069.9442 | 10851774.8114 | 2012
New Giza Phase 01 | 2014-09-20 | 2016-02-20 | Construction | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 16200 | All | 188451123.6823 | 172216796.0405 | 173716038.3248 | -0.8706% | 10630.6664 | 0 | 10723.2122 | 0 | 1486.8065 | 0 | 1499.75 | 0 | 7.15 | 24086265.1805 | 24295949.4161 | 2014
Hyper Solimanya | 2015-06-15 | 2017-04-15 | Construction | Commercial | Market | Civil Works | Hyper | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  | 5539.1926 | 10871 | Total | 82761451 | 110450184.62 | 108679008.9749 | 1.604% | 10160.0759 | 0 | 9997.1492 | 0 | 1420.9896 | 0 | 1398.2027 | 0 | 7.15 | 15447578.2685 | 15199861.3951 | 2015
Ismailia Bridges | 2016-01-01 | 2017-01-30 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY | m | 174 | 6309 | All | 56652000 | 56527617 | 33948207.928 | 39.94% | 8959.8379 | 324871.3621 | 5380.9174 | 195104.6433 | 1008.9907 | 36584.6128 | 605.9592 | 21971.2436 | 8.88 | 6365722.6351 | 3822996.3883 | 2016
Maxium Mall | 2014-10-19 | 2017-05-20 | Construction | Commercial | Offices & Mall | Turn Key | Maxim | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | Customer/Day |  | 70000 | Total | 101495012 | 98576600 | 104888994.0403 | -6.404% | 1408.2371 | 3685.0006 | 1498.4142 | 3920.9711 | 196.9562 | 515.3847 | 209.5684 | 548.3876 | 7.15 | 13786937.0629 | 14669789.3763 | 2014
Ataqqa Power Plant | 2014-12-20 | 2016-03-20 | Industrial | Industrial | Power Plant | Turn Key | Sewedy | Eng Mohamed Abd El Fatah | Eng. Mohamed Salah Helmy | Suez | D | Affilates |  |  |  | All | 149999782.52 | 184387980.81 | 97786625.9352 | 46.97% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.15 | 25788528.7846 | 13676451.1797 | 2014
Mall of Egypt Bridge | 2015-02-10 | 2016-12-10 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed Mostafa | Eng. Omar Sobhy | 6th of October | D | ARMY |  |  | 1553 | All | 157635800 | 183459815.63 | 165227581.2857 | 9.938% | 118132.5278 | 0 | 106392.5185 | 0 | 0 | 0 | 0 | 0 | 7.83 | 23430372.3665 | 21101862.2332 | 2015
Marassi Tanks PKG 22 | 2012-10-30 | 2014-09-30 | Transportation | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | North Coast | D | Private | tank storage m3 | 5000 |  | All | 16562387.829 | 18438370 | 16655530.55 | 9.669% | 0 | 3687.674 | 0 | 3331.1061 | 0 | 0 | 0 | 0 | 6.09 | 3027646.9622 | 2734898.2841 | 2012
Sodic Club House | 2015-03-01 | 2019-09-30 | Construction | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 20000 | Total | 167155712.4065 | 161208266 | 169537179.4745 | -5.167% | 8060.4133 | 0 | 8476.859 | 0 | 1029.427 | 0 | 1082.6129 | 0 | 7.83 | 20588539.719 | 21652257.915 | 2015
Montazah Hotel Sharm | 2014-12-31 | 2016-12-30 | Construction | Commercial | Hotel | Civil Works | El Montazah | Eng Wael Ragabi | Eng. Omar Sobhy | sharm | S | Private |  |  | 16580 | All | 15941883 | 33784495.5267 | 30373982.7996 | 10.09% | 2037.6656 | 0 | 1831.9652 | 0 | 284.9882 | 0 | 256.2189 | 0 | 7.15 | 4725104.2695 | 4248109.4825 | 2014
Uptown Cairo Pkg 53 | 2015-04-01 | 2018-12-30 | Construction | Residential | Residential | Turn Key | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | Private |  |  | 63752 | Civil | 83305896.191 | 314789511 | 344222187 | -9.35% | 4937.7198 | 0 | 5399.3943 | 0 | 630.6156 | 0 | 689.5778 | 0 | 7.83 | 40203002.682 | 43961965.1341 | 2015
Bani Suif Power Plant 1021 | 2015-07-01 | 2017-11-30 | Industrial | Industrial | Power Plant | Turn Key | Sewedy | Eng Ashraf Abd El Satar | Eng. Mohamed Ragab | Benisuef | D | Affilates | MW | 4800 |  | All | 442721012 | 427594086.74 | 319973217.7839 | 25.17% | 0 | 89082.1014 | 0 | 66661.087 | 0 | 11377.0244 | 0 | 8513.5488 | 7.83 | 54609717.3359 | 40865034.1997 | 2015
New Giza Phase 02 | 2015-07-25 | 2017-08-24 | Construction | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  | 16200 | All | 148186885 | 155643269.76 | 161564179.8036 | -3.804% | 9607.6092 | 0 | 9973.0975 | 0 | 1227.0254 | 0 | 1273.7034 | 0 | 7.83 | 19877812.2299 | 20633994.8664 | 2015
JICA Wind Farm Gabal El Zeet | 2015-12-01 | 2017-04-01 | Industrial | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private | MW | 220 |  | All | 116000000.0279 | 120483319.9 | 82164809.214 | 31.8% | 0 | 547651.4541 | 0 | 373476.4055 | 0 | 69942.7144 | 0 | 47698.1361 | 7.83 | 15387397.1775 | 10493589.9379 | 2015
El Mostathmereen Mokatam Substation | 2016-01-01 | 2017-11-30 | Industrial | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Cairo | S | Public | KV | 220 |  | All | 135792183 | 135792183 | 85209855.07 | 37.25% | 0 | 617237.1955 | 0 | 387317.523 | 0 | 69587.057 | 0 | 43666.0116 | 8.87 | 15309152.5366 | 9606522.5558 | 2016
Levana UpTown PKG 62 | 2016-04-27 | 2018-12-27 | Transportation | Infrastructure | L&L | Civil Works | EMAAR | Eng Alaa Mahran | Eng Mahmoud Mahlab | Cairo | D | Private |  |  | 22213.8 | All | 47942099.8594 | 47319156 | 52574895.421 | -11.11% | 2130.1694 | 0 | 2366.7673 | 0 | 239.8839 | 0 | 266.5278 | 0 | 8.88 | 5328733.7838 | 5920596.3312 | 2016
Kayan 110 | 2016-05-16 | 2020-06-15 | Construction | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Adel Rahmo | Eng. Mohamed Ashry | New Capital | D | ARMY |  |  | 152000 | Total | 1251386350.6992 | 1335232523 | 1306314436.593 | 2.166% | 8784.4245 | 0 | 8594.1739 | 0 | 1228.5908 | 0 | 1201.9824 | 0 | 7.15 | 186745807.4126 | 182701319.8032 | 2016
El Amal Bridge | 2015-02-01 | 2016-02-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | New Capital | D | ARMY | m | 90 | 2520 | All | 31793876 | 28943151 | 21210869.997 | 26.72% | 11485.3774 | 321590.5667 | 8417.0119 | 235676.3333 | 1466.8426 | 41071.5922 |  |  | 7.83 | 3696443.295 | 2708923.3713 | 2015
Bani Suif Cement | 2016-08-09 | 2018-07-09 | Industrial | Industrial | Factory | Civil Works | CDI | Eng Mohamed Zaki | Eng Mahmoud Mahlab | Benisuef | S | Private | Ton / Day | 1000 |  | All | 274663700 | 274663700 | 265512440.135 | 3.332% | 0 | 274663.7 | 0 | 265512.4401 | 0 | 30965.4679 | 0 | 29933.7588 | 8.87 | 30965467.8692 | 29933758.7525 | 2016
New Giza Wall | 2015-12-01 | 2016-11-13 | Construction | Commercial | Fence | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private |  |  |  | All | 2750000 | 2648340.9749 | 1057277.26 | 60.08% | 0 | 0 |  |  | 0 | 0 |  |  | 7.83 | 338230.0096 | 135029.0243 | 2015
Tamey El Amdid Mansora Power Station | 2017-07-01 | 2019-11-01 | Industrial | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Mansoura | S | Public | KV | 220 |  | All | 102015745.0742 | 114399640 | 92853851.3 | 18.83% | 0 | 519998.3636 | 0 | 422062.9605 | 0 | 28808.7736 | 0 | 23382.9895 | 18.05 | 6337930.1939 | 5144257.6898 | 2017
Ismailia Substation 500-220 | 2017-07-10 | 2020-01-10 | Industrial | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Ismailia | S | Public | KV | 220 | 15000 | All | 109399640 | 109399640 | 94574974.6595 | 13.55% | 7293.3093 | 497271.0909 | 6304.9983 | 429886.2485 | 404.0615 | 27549.6449 | 349.3074 | 23816.4127 | 18.05 | 6060921.8837 | 5239610.7845 | 2017
El Amal Bridge L&L | 2018-02-01 | 2018-06-03 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 8184472.88 | 9050320 | 6335224 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.74 | 510164.5998 | 357115.2198 | 2018
FIEM Wind Farm Gabal El Zeet | 2016-10-01 | 2017-05-01 | Industrial | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private | MW | 120 |  | All | 63636697.06 | 72547889 | 43182355.317 | 40.48% | 0 | 604565.7417 | 0 | 359852.961 | 0 | 68158.4827 | 0 | 40569.6687 | 8.87 | 8179017.9256 | 4868360.2387 | 2016
KFW Wind Farm Gabal El Zeet | 2016-11-01 | 2017-04-01 | Industrial | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | Private | MW | 40 |  | All | 20229094 | 23038288.54 | 13129303.501 | 43.01% | 0 | 575957.2135 | 0 | 328232.5875 | 0 | 64933.1695 | 0 | 37004.8013 | 8.87 | 2597326.7802 | 1480192.052 | 2016
Marassi Tank PKG 107 | 2017-02-15 | 2019-03-16 | Transportation | Infrastructure | Tank | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | tank storage m3 | 24500 | 0 | Total | 54777143 | 54777143 | 42810448.983 | 21.85% | 0 | 2235.8018 | 0 | 1747.3653 | 0 | 312.6995 | 0 | 244.3868 | 7.15 | 7661138.8811 | 5987475.3822 | 2017
Ben Zayed New Capital Tunnel | 2016-03-18 | 2017-12-18 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | New Capital | D | ARMY | m | 330 | 18596 | All | 446010164 | 343357654.106 | 271212136.105 | 21.01% | 18464.0597 | 1040477.7397 | 14584.4341 | 821854.9579 | 1025.7811 | 57804.3189 | 810.2463 | 45658.6088 | 18 | 19075425.2281 | 15067340.8947 | 2016
Ministries Buildings | 2017-04-01 | 2021-12-30 | Construction | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Wael Ragabi | Eng. Mohamed Ashry | New Capital | D | ARMY | People Served | 4200 | 169000 | Total | 2083664645.88 | 2740570200 | 2663137373.0012 | 2.825% | 16216.3917 | 652516.7143 | 15758.2093 | 634080.3269 | 900.9107 | 36250.9286 | 875.4561 | 35226.6848 | 18 | 152253900 | 147952076.2778 | 2017
Bani Suif Substation | 2017-07-01 | 2019-03-01 | Industrial | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Benisuef | S | Public | KV | 220 | 29643 | All | 120712211 | 120712211 | 101105076 | 16.24% | 4072.1995 | 548691.8682 | 3410.7572 | 459568.5273 | 225.6066 | 30398.4415 | 188.9616 | 25460.8602 | 18.05 | 6687657.1191 | 5601389.2521 | 2017
Royal City Mall | 2017-06-01 | 2020-12-30 | Construction | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private | No of Shops | 95 | 25379 | Total | 344412547 | 527037820 | 502741033.2292 | 4.61% | 20766.6898 | 5547766.5263 | 19809.3319 | 5292010.8761 | 1147.3309 | 306506.4379 | 1094.4382 | 292376.2915 | 18.1 | 29118111.6022 | 27775747.6922 | 2017
Shoubra Banha Bridge L&L | 2018-04-30 | 2018-07-30 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY | m | 5000 | 4000 | All | 3865380 | 3865380 | 1461115 | 62.2% | 966.345 | 773.076 | 365.2788 | 292.223 | 0 | 0 | 0 | 0 | 17.64 | 219125.8503 | 82829.6485 | 2018
SLP Logistic Center PI Park Sewedy Stores | 2017-07-19 | 2019-06-20 | Industrial | Industrial | Factory | Turn Key | Sewedy | Eng Amir | Eng. Mohamed Fawzy | Cairo | D | Affilates | Storage Capacity | 45000 | 13000 | Total | 97038375.909 | 98230405 | 86259669.128 | 12.19% | 7556.185 | 2182.8979 | 6635.3592 | 1916.8815 | 418.6252 | 120.9362 | 367.6099 | 106.1984 | 18.05 | 5442127.7008 | 4778929.0376 | 2017
El Mostakbal Bridge L&L | 2018-07-01 | 2018-10-30 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  | 4286.7 | All | 4574604.922 | 4424558 | 2062745 | 53.38% | 1032.1595 | 0 | 481.1965 | 0 | 0 | 0 | 0 | 0 | 17.85 | 247874.3978 | 115559.944 | 2018
Kayan Wall L&L | 2017-11-01 | 2019-10-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 87197267.1201 | 107782440 | 82991132 | 23% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.73 | 6079099.8308 | 4680830.9081 | 2017
Elco Suez Steel Rolling Mill Plant 3 | 2017-09-07 | 2018-12-07 | Industrial | Industrial | Factory | Turn Key | Elco Suez | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Private | Million ton / year | 1.4 |  | All | 412223139.5933 | 417390514 | 292181074.4464 | 30% | 0 | 298136081.4286 | 0 | 208700767.4617 | 0 | 16749218.0578 | 0 | 11724762.217 | 17.8 | 23448905.2809 | 16414667.1037 | 2017
Hyper El Temsah | 2018-06-07 | 2019-07-07 | Construction | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY | Customer/Day | 3312 | 7800 | Total | 167661582 | 168976040.9524 | 141672524.9015 | 16.16% | 21663.595 | 112500.693 | 18163.1442 | 94322.5865 | 1208.2317 | 6274.4391 | 1013.003 | 5260.6016 | 17.93 | 9424207.5266 | 7901423.5863 | 2018
Marassi Bridge Pkg 117 | 2017-11-13 | 2019-08-13 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private | Length m | 60 | 1080 | All | 44915215.9833 | 45205818 | 31111755 | 31.18% | 41857.2389 | 753430.3 | 28807.1806 | 518529.25 | 2360.8144 | 42494.6588 | 1624.7705 | 29245.8686 | 17.73 | 2549679.5262 | 1754752.1151 | 2017
Siemens Power Station | 2017-11-05 | 2019-12-05 | Industrial | Industrial | Factory | Turn Key | SIEMENS | Eng Hassan Youssef | Eng Mahmoud Mahlab | Sokhna | S | Private |  |  | 16200 | All | 317512165.921 | 332856409 | 319846012.345 | 3.909% | 20546.6919 | 0 | 19743.581 | 0 | 1158.8659 | 0 | 1113.5691 | 0 | 17.73 | 18773627.1292 | 18039820.2112 | 2017
Uptown FM85 Pkg 85 | 2019-01-01 | 2020-01-01 | Construction | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Mohamed Bassuony | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.91 | 0 | 0 | 2019
El Sokhna Tunnel 01 | 2018-02-01 | 2018-12-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Sokhna | D | ARMY |  |  | 3604 | All | 46639513 | 46639513 | 37675288 | 19.22% | 12941.0413 | 0 | 10453.7425 | 0 | 729.4837 | 0 | 589.2752 | 0 | 17.74 | 2629059.3574 | 2123747.9143 | 2018
Abu Sultan Bridge 01 | 2018-03-01 | 2018-09-30 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 1738 | All | 18754740.365 | 18752986 | 13705181 | 26.92% | 10789.9804 | 0 | 7885.6047 | 0 | 610.9842 | 0 | 446.5235 | 0 | 17.66 | 1061890.487 | 776057.8143 | 2018
Mintra Factory | 2018-02-01 | 2019-01-01 | Industrial | Industrial | Factory | Civil Works | Mintra | Eng Salah Rashad | Eng. Mohamed Abdel Raouf | Cairo | S | Private |  |  | 52500 | All | 109817542.56 | 112045826 | 113125840.857 | -0.9639% | 2134.2062 | 0 | 2154.7779 | 0 | 120.3047 | 0 | 121.4644 | 0 | 17.74 | 6315999.2108 | 6376879.417 | 2018
King Farouk Restoration | 2018-02-01 | 2018-02-11 | Construction | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.66 | 0 | 0 | 2018
Mohamed Ali Palace | 2018-04-01 | 2022-06-30 | Construction | Restoration | Palace | Restoration | Army Forces | Eng Mohamed Saber | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All | 94773524.91 | 150000000 | 125642410.0235 | 16.24% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.66 | 8493771.2344 | 7114519.2539 | 2018
Nefisha Bridge | 2018-05-02 | 2019-01-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 6900 | All | 70928098.3435 | 70928098 | 51420131 | 27.5% | 10279.4345 | 0 | 7452.1929 | 0 | 575.2342 | 0 | 417.0225 | 0 | 17.87 | 3969115.7247 | 2877455.568 | 2018
Fish Market | 2018-06-01 | 2019-06-30 | Construction | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY | Shops | 32 | 6400 | Total | 57854521 | 66185668.5714 | 58052020.6193 | 12.29% | 10341.5107 | 2068302.1429 | 9070.6282 | 1814125.6444 | 576.7714 | 115354.2746 | 505.8911 | 101178.2289 | 17.93 | 3691336.7859 | 3237703.3251 | 2018
Al Jazi Mall | 2018-05-01 | 2020-02-28 | Construction | Commercial | Offices & Mall | Civil Works | YAMM | Eng Mohamed Zaki | Eng. Waleed Barakat | 5th settelment | S | Private |  |  | 48853.59 | Civil | 241102529.6406 | 245977347.1316 | 228488395.4632 | 7.11% | 5034.9902 | 0 | 4677.0032 | 0 | 281.7566 | 0 | 261.7237 | 0 | 17.87 | 13764820.7684 | 12786144.1222 | 2018
Benban Aswan Alcazars Solar Park | 2018-06-02 | 2019-07-02 | Industrial | Industrial | Power Plant | Civil Works | TSK | Eng Amir | Eng Mahmoud Mahlab | Aswan | S | Private | KW | 200 |  | All | 212005783.75 | 212005784 | 118641100 | 44.04% | 0 | 1060028.92 | 0 | 593205.5 | 0 | 59120.4083 | 0 | 33084.5231 | 17.93 | 11824081.6509 | 6616904.6291 | 2018
El Alameen Roads Earth Works | 2018-09-15 | 2019-06-15 | Transportation | Infrastructure | Roads | Civil Works | Army Forces | Eng Mohamed Abd El Nabi | General Mohamed Salah | North Coast | D | ARMY |  |  |  | All | 45583868.7231 | 54192857 | 46001919 | 15.11% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.88 | 3030920.4139 | 2572814.2617 | 2018
El Sewedy Univeristy 2 phase 2 | 2019-10-10 | 2020-12-10 | Construction | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affilates | Student | 300 | 14500 | Total | 253523145.54 | 262378822 | 232988357.458 | 11.2% | 18095.0912 | 874596.0733 | 16068.1626 | 776627.8582 | 1006.9611 | 48669.7871 | 894.166 | 43218.0222 | 17.97 | 14600936.1157 | 12965406.6476 | 2019
El Sokhna Tunnel L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Sokhna | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 5.36 | 0 | 0 | 2010
R05 Residential District Z1 & Z2 | 2018-07-16 | 2022-05-16 | Construction | Residential | Residential | Turn Key | Utilities And Urban Communities | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | New Capital | D | Public |  |  | 418000 | Civil | 2949277335 | 3200000000 | 2976000000 | 7% | 5176.0086 | 0 | 4813.688 | 0 | 288.6787 | 0 | 268.4712 | 0 | 17.93 | 178471834.9136 | 165978806.4696 | 2018
Abu Sultan Bridge 02 Greenhouse | 2018-09-01 | 2019-06-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 476 | All | 67755600 | 67755600 | 59506484.6859 | 12.17% | 142343.6975 | 0 |  |  | 0 | 0 |  |  | 17.78 | 3810776.153 | 3346821.4109 | 2018
El Sokhna Tunnel 02 | 2018-09-01 | 2019-04-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Sokhna | D | ARMY |  |  | 1813 | All | 22334150 | 22334150 | 17647987 | 20.98% | 12318.8913 | 0 | 9734.1351 | 0 | 686.6718 | 0 | 542.5939 | 0 | 17.94 | 1244935.8974 | 983722.7982 | 2018
El Awsty Middle Tunnel L&L | 2018-12-01 | 2019-04-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 1024820 | 1024820 | 819856 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.14 | 63495.6629 | 50796.5304 | 2018
Sodic Eastown EDNC | 2019-03-25 | 2021-12-24 | Construction | Commercial | Offices & Mall | Turn Key | SODIC | Eng Sayed Osman | Eng. Waleed Barakat | 5th settelment | D | Private | 0 | 0 | 156000 | Total | 1017291991 | 1074545067 | 1010072362.98 | 6% | 6888.1094 | 0 | 6474.8228 | 0 | 391.5923 | 0 | 368.0968 | 0 | 17.59 | 61088406.3104 | 57423101.9318 | 2019
Marassi Civic Center Pkg 144 | 2018-11-01 | 2019-08-01 | Construction | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | Private |  |  | 12500 | Total | 160729997 | 176420375 | 122239319.38 | 30.71% | 14113.63 | 0 | 9779.1456 | 0 | 796.031 | 0 | 551.5593 | 0 | 17.73 | 9950387.7609 | 6894490.6588 | 2018
DPW Sokhna Dubai Port | 2018-11-16 | 2021-07-16 | Transportation | Infrastructure | Networks | EPC | DPW | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Sokhna | D | Private | Container Slots | 9190 | 600000 | All | 1557966434.4861 | 1633315425 | 1246507144.6956 | 23.68% | 2722.1924 | 177727.4674 | 2077.5119 | 135637.3389 | 152.2479 | 9940.015 | 116.1919 | 7585.9809 | 17.88 | 91348737.4161 | 69715164.6921 | 2018
Slope Stablization PKG 101 | 2018-10-11 | 2020-11-10 | Transportation | Infrastructure | L&L | Civil Works | EMAAR | Eng Mohamed Bassuony | Eng Mahmoud Mahlab | Cairo | D | Private |  |  | 11305 | All | 40371611 | 52028085.7143 | 47340355.1914 | 9.01% | 4602.219 | 0 | 4187.5591 | 0 | 256.2483 | 0 | 233.1603 | 0 | 17.96 | 2896886.7324 | 2635877.2378 | 2018
Elco Steel Substation | 2018-05-01 | 2019-04-01 | Industrial | Industrial | Power Plant | Turn Key | Elco Suez | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Private | KW | 220 |  | All | 31790191.494 | 32341773 | 34798196.7776 | -7.595% | 0 | 147008.0591 | 0 | 158173.6217 | 0 | 8180.749 | 0 | 8802.0936 | 17.97 | 1799764.7746 | 1936460.5886 | 2018
Sewab Greenhouse Tunnel | 2018-09-01 | 2019-06-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY |  |  | 476 | All | 11220000 | 10957813.825 | 9623720.8521 | 12.17% | 23020.6173 | 0 | 20217.9009 | 0 | 0 | 0 | 0 | 0 | 17.78 | 616299.9902 | 541266.6396 | 2018
Mivida Irrigation Treatment Plant Pkg 140 | 2019-01-14 | 2021-07-14 | Transportation | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng. Waleed Barakat | 5th settelment | D | Private | Water be treated m3/ hour For 16 hours / day | 680 | 12350 | All | 168347427 | 170057475.6641 | 136045980.5313 | 20% | 13769.8361 | 250084.523 | 11015.8689 | 200067.6184 | 770.1251 | 13986.8301 | 616.1 | 11189.4641 | 17.88 | 9511044.5002 | 7608835.6002 | 2019
Multi Sports Hall | 2019-08-30 | 2022-05-31 | Construction | Commercial | Stadium | EPC | Army Forces | Eng Adel Rahmo | Eng Mahmoud Mahlab | New Capital | D | ARMY | Chair | 15000 | 18000 | Total | 1200000000 | 1200000000 | 1140000000 | 5% | 66666.6667 | 80000 | 63333.3333 | 76000 | 4097.521 | 4917.0252 | 3892.6449 | 4671.1739 | 16.27 | 73755377.9963 | 70067609.0965 | 2019
EGAT | 2019-04-30 | 2019-12-30 | Industrial | Industrial | Factory | Turn Key | Sewedy | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | Affilates |  |  |  | All | 65831906 | 65831906 | 56811131 | 13.7% | 0 | 0 |  |  | 0 | 0 |  |  | 17.14 | 3840834.6558 | 3314535.0642 | 2019
Abou Ghazala Bridge Ramp L&L | 2019-03-15 | 2019-07-15 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 980186.2937 | 1688453 | 1511719 | 10.47% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.59 | 95989.369 | 85941.9557 | 2019
Mohamed Ali Fahmy Ramps L&L | 2019-03-15 | 2019-12-15 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 3670033.532 | 7149700 | 6713205 | 6.105% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.59 | 406463.8999 | 381648.9483 | 2019
El Mosheer Bridge Abu Zaied Khdr L&L | 2018-10-01 | 2019-03-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 4203687 | 4203687 | 2001684 | 52.38% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.97 | 233928.0467 | 111390.3172 | 2018
Ora Zed Park L&L | 2019-07-01 | 2019-11-01 | Transportation | Infrastructure | L&L | Civil Works | Ora | Eng Adham Edward | Eng.adham edward | 6th of October | D | Private |  |  |  | All | 1100000 | 1042542 | 758212.27 | 27.27% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.27 | 64077.5661 | 46601.8605 | 2019
DoubleTree Mangroovy El Gouna Hotel | 2019-08-22 | 2021-08-22 | Construction | Commercial | Hotel | Civil Works | Sewedy | Eng Sherif El Sisi | Eng. Mohamed Fawzy | Gouna | D | Affilates |  |  | 18352 | All | 44797273 | 57898699.39 | 54424777.4266 | 6% | 3154.8986 | 0 | 2965.6047 | 0 | 192.9602 | 0 | 181.3826 | 0 | 16.35 | 3541204.8557 | 3328732.5643 | 2019
Baron Palace Fence | 2020-02-01 | 2020-07-01 | Construction | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All | 6306643.0958 | 16220552 | 14434567.4488 | 11.01% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 | 992082.6911 | 882848.162 | 2020
Safeer Square Bridge | 2019-08-01 | 2019-12-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 6750 | All | 95436549 | 95436549 | 82927091 | 13.11% | 14138.748 | 0 | 12285.495 | 0 | 864.7552 | 0 | 751.4064 | 0 | 16.35 | 5837097.7982 | 5071993.3333 | 2019
Suez Road Tunnel Res L&L | 2019-08-20 | 2019-10-20 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 3270317.6497 | 4423592 | 4769909 | -7.829% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 | 270556.0856 | 291737.5535 | 2019
HyperOne Zayed Extention | 2019-10-13 | 2020-12-13 | Construction | Commercial | Parking | Civil Works | Hyper | Eng Tarek Ramadan | Eng. Mohamed Fawzy | 6th of October | D | Private | Parking Capacity | 510 | 30000 | All | 135000000 | 133583770 | 99106552.4453 | 25.81% | 4452.7923 | 261928.9608 | 3303.5517 | 194326.5734 | 273.6812 | 16098.8913 | 203.0456 | 11943.8582 | 16.27 | 8210434.5421 | 6091367.6979 | 2019
IKEA Extention MoA | 2019-10-01 | 2020-11-30 | Construction | Commercial | Offices & Mall | Turn Key | Marakez | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private |  |  | 19836 | All | 52793757.1332 | 196190620 | 212380869 | -8.252% | 9890.6342 | 0 | 10706.8395 | 0 | 607.9062 | 0 | 658.0725 | 0 | 16.27 | 12058427.7812 | 13053526.0602 | 2019
CFC Podium II | 2019-10-01 | 2021-07-30 | Construction | Commercial | Offices & Mall | Core And Shell | Al-Futtaim | Eng Amir | Eng. Waleed Barakat | 5th settelment | S | Private | Offices | 300 | 98633 | Total | 559510195 | 635000000 | 524290213.0394 | 17.43% | 6438.0076 | 2116666.6667 | 5315.5659 | 1747634.0435 | 363.1138 | 119383.3427 | 299.8063 | 98569.32 | 17.73 | 35815002.8201 | 29570795.9977 | 2019
Mostafa Kamel Bridge L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 5.36 | 0 | 0 | 2010
Josef Tito Bridge L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 5.36 | 0 | 0 | 2010
Espiko Bridge L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 5.36 | 0 | 0 | 2010
El Gabal El Asfr Tunnel L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 5.36 | 0 | 0 | 2010
MR3 Bridge L&L | 2019-10-19 | 2019-12-19 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 1520085 | 1520085 | 1367204 | 10.06% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.27 | 93428.7031 | 84032.2065 | 2019
El Sewedy University 1 | 2018-09-09 | 2019-09-09 | Construction | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | Affilates | People Served | 900 | 38447 | Total | 559510195 | 593999147 | 510839266 | 14% | 15449.8179 | 659999.0522 | 13286.8433 | 567599.1844 | 871.3941 | 37224.9888 | 749.3989 | 32013.4904 | 17.73 | 33502489.9605 | 28812141.3424 | 2018
Mehwar El Salam Axis L&L | 2019-10-01 | 2020-02-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 16843027 | 16843027 | 15775883 | 6.336% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.27 | 1035219.8525 | 969630.1782 | 2019
El Hegaz Square Bridge | 2019-12-05 | 2020-04-05 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 9450 | All | 138370050 | 138370050 | 121772563 | 11.99% | 14642.3333 | 0 | 12885.9855 | 0 | 899.959 | 0 | 792.0089 | 0 | 16.27 | 8504612.7843 | 7484484.5114 | 2019
Ring Road | 2020-02-01 | 2022-03-30 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Roads and Bridges Authority | Eng Abd El Naby Shaban | Eng Hussien Bahgat | Cairo | D | Public |  |  | 63600 | All | 771935871 | 524000000 | 492560000 | 6% | 6046.0243 | 0 |  | 0 | 0 | 0 |  |  | 16.35 | 32048929.6636 | 30125993.8838 | 2020
Marina Inland Marassi Pkg 162 | 2020-02-02 | 2022-03-02 | Transportation | Infrastructure | Port | Civil Works | EMAAR | Eng Reda | Eng. Mohamed Fawzy | North Coast | D | Private |  |  |  | All | 434504076.4286 | 434504076.4286 | 354989830.4421 | 18.3% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 | 26575172.8702 | 21711916.235 | 2020
Sultana Malek Restoration | 2020-08-01 | 2022-06-01 | Construction | Restoration | Palace | Restoration | Army Forces | Eng Karem Ehab | Eng Mariam Youssef | Cairo | D | ARMY |  |  |  | All | 85000000 | 85000000 | 72250000 | 15% | 0 | 0 |  |  | 0 | 0 |  |  | 15.93 | 5335844.3189 | 4535467.6711 | 2020
Lekela 250MW Wind Farm | 2020-06-03 | 2021-06-04 | Industrial | Industrial | Power Plant | Civil Works | GAMESA | Eng Marwan Shibl | Eng. Waleed Barakat | Gabal El Zeit | D | Private | MW | 250 |  | All | 119626844 | 182442342 | 178793495.16 | 2% | 0 | 729769.368 | 0 | 715173.9806 | 0 | 42927.6099 | 0 | 42069.0577 | 17 | 10731902.4706 | 10517264.4212 | 2020
New Giza Hospital | 2021-09-30 | 2023-09-30 | Construction | Commercial | Hospital | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | Private | bed | 164 | 23000 | All | 542690000 | 542690000 | 507186915.8879 | 6.542% | 23595.2174 | 3309085.3659 | 22051.605 | 3092603.1457 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 2021
Kayan Landscape | 2019-06-01 | 2020-03-01 | Transportation | Infrastructure | Landscape | Civil Works | Army Forces | Eng Adel Rahmo | Eng. Omar Sobhy | New Capital | D | ARMY |  |  |  | All | 100042648 | 100042648 | 93060671.3161 | 6.979% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.74 | 5976263.3214 | 5559179.8875 | 2019
Abbas Akkad Bridge | 2020-02-01 | 2020-06-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 15600 | All | 135000000 | 124132580.9524 | 122869821.99 | 1.017% | 7957.2167 | 0 | 7876.2706 | 0 | 0 | 0 | 0 | 0 | 16.35 | 7592206.7861 | 7514973.822 | 2020
El Asher Men Ramadan Bridge | 2020-02-28 | 2020-06-30 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mostafa Diab | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 4200 | All | 84354414 | 93910355 | 85732351.721 | 8.708% | 22359.6083 | 0 | 20412.4647 | 0 | 0 | 0 | 0 | 0 | 16.35 | 5743752.5994 | 5243568.9126 | 2020
Kafr Shokr Bridge | 2020-08-15 | 2021-08-15 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Ahmed El Adawy | Eng Hussien Bahgat | qlyboya | D | ARMY |  |  | 16900 | All | 191000000 | 147845325 | 133974586 | 9.382% | 8748.2441 | 0 | 7927.4903 | 0 | 0 | 0 | 0 | 0 | 15.93 | 9280936.9115 | 8410206.2775 | 2020
Al Shorouk Bridge (LRT) | 2020-05-09 | 2021-02-08 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Hany Yassin | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 7070 | All | 40774553.92 | 26145782 | 24180000 | 7.519% | 3698.1304 | 0 | 3420.0849 | 0 | 0 | 0 | 0 | 0 | 15.56 | 1680320.1799 | 1553984.5758 | 2020
GOV2 Infra | 2020-06-01 | 2021-12-01 | Transportation | Infrastructure | Networks | Civil Works | Utilities And Urban Communities | Eng Mohamed Abd El Moktader | Eng Mohamed Abd El Fatah | New Capital | D | Public | ACRE | 1500 |  | All | 650000000 | 650000000 | 607750000 | 6.5% | 0 | 433333.3333 | 0 | 405166.6667 | 0 | 0 | 0 | 0 | 17 | 38235294.1176 | 35750000 | 2020
Cairo Alex Railroad | 2020-10-15 | 2022-10-15 | Transportation | Infrastructure | Railway | Civil Works | ENR | Eng Ali Tawfeek | Eng.callum | alex | S | Public | KM RAIL | 35 |  | All | 1350000000 | 967000000 | 879970000 | 9% | 0 | 27628571.4286 | 0 | 25142000 | 0 | 0 | 0 | 0 | 15.71 | 61553150.8593 | 56013367.282 | 2020
Hassan El Mamoun Bridge | 2020-06-01 | 2020-09-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mostafa Diab | Eng Hussien Bahgat | Cairo | D | ARMY |  |  | 13440 | All | 124285762 | 93800000 | 88756688.976 | 5.377% | 6979.1667 | 0 | 6603.9203 | 0 | 0 | 0 | 0 | 0 | 17 | 5517647.0588 | 5220981.7045 | 2020
Sherouk Bridge L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All | 1000000 | 1000000 | 1648128.4931 | -64.81% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36 | 186567.1642 | 307486.6592 | 2010
Ora Zed Park 1B Pkgs A&D | 2020-09-28 | 2023-06-28 | Construction | Residential | Residential | Turn Key | Ora | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | Private | no of apr | 320 | 75500 | All | 870293108.0057 | 870293108 | 808937442.9565 | 7.05% | 11527.061 | 2719665.9625 | 10714.4032 | 2527929.5092 | 732.3419 | 172786.9099 | 680.7118 | 160605.4326 | 15.74 | 55291811.1817 | 51393738.4343 | 2020
Kattameya Creeks | 2021-01-15 | 2024-01-15 | Construction | Residential | Residential | Turn Key | Starlight | Eng Mohamed Kamal | Eng. Waleed Barakat | 5th settelment | S | Private |  |  | 140150 | All | 1462000000 | 1462000000 | 1352350000 | 7.5% | 10431.6803 | 0 | 9649.3043 | 0 | 0 | 0 | 0 | 0 | 15.84 | 92297979.798 | 85375631.3131 | 2021
Mansoura University Faculty of Medicine | 2021-01-01 | 2021-12-31 | Construction | Commercial | University | Civil Works | Utilities And Urban Communities | Eng Emad Habi | Eng Mohamed Abd El Fatah | mansoura | D | Public |  |  | 40000 | All | 219047619.0476 | 219047619.0476 | 203714285.7143 | 7% | 5476.1905 | 0 | 5092.8571 | 0 | 0 | 0 | 0 | 0 | 15.84 | 13828763.8288 | 12860750.3608 | 2021
Diplomatic District - Infra | 2021-01-01 | 2022-01-01 | Transportation | Infrastructure | Networks | Civil Works | Utilities And Urban Communities | Eng Mohamed Abd El Moktader | Eng Mohamed Abd El Fatah | New Capital | D | Public | ACRE | 1600 |  | All | 390000000 | 390000000 | 364650000 | 6.5% | 0 | 243750 | 0 | 227906.25 | 0 | 0 | 0 | 0 | 15.84 | 24621212.1212 | 23020833.3333 | 2021
El Sewedy CFC HQ Internal Finishing | 2020-12-08 | 2022-06-08 | Construction | Commercial | Offices & Mall | Turn Key | Sewedy | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 5th settelment | D | Affilates |  |  | 23500 | All | 327718153.3333 | 327718153.3333 | 302367726 | 7.735% | 13945.4533 | 0 | 12866.7117 | 0 | 0 | 0 | 0 | 0 | 15.67 | 20913730.2702 | 19295962.0932 | 2020
Lagoon Discharge Pkg 178 | 2020-12-28 | 2021-07-30 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Reda | Eng. Mohamed Fawzy | North Coast | D | Private |  |  |  | All | 40449240 | 40449240 | 35085670.776 | 13.26% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.67 | 2581317.1666 | 2239034.5103 | 2020
El Khatatba Bridge | 2021-06-01 | 2022-06-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Roads and Bridges Authority | Eng Khaled Tawfek | Eng Hussien Bahgat | qlyboya | D | Public |  |  | 9940 | All | 165000000 | 142857142.8571 | 130845321 | 8.408% | 14371.946 | 0 | 13163.5132 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 2021
EGAT Pelletizing Plant | 2021-06-01 | 2022-06-01 | Industrial | Industrial | Factory | Turn Key | Elco Suez | Eng Mohamed Fadel | Eng. mohamed el seman | Suez | D | Private |  |  |  | All | 375000000 | 375000000 | 341250000 | 9% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 2021
Sokhna Port Expansion | 2021-06-01 | 2022-06-01 | Transportation | Infrastructure | Port | Civil Works | Transportation Ministry | Eng Tarek Ramadan | Eng. mohamed el seman | Sokhna | S | Public | KM | 12 |  | All | 1100000000 | 1100000000 | 1023000000 | 7% | 0 | 91666666.6667 | 0 | 85250000 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | 2021
MDF Factory | 2021-03-06 | 2022-05-05 | Industrial | Industrial | Factory | Turn Key | Naile Wood | Eng Bader Osman | Eng. mohamed el seman | sadat | S | Private |  |  | 23710 | All | 175000000 | 175000000 | 162750000 | 7% | 7380.852 | 0 | 6864.1923 | 0 | 0 | 0 | 0 | 0 | 15.73 | 11125238.398 | 10346471.7101 | 2021
Olympic City L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36 | 0 | 0 | 2010
Kemet Building | 2021-03-30 | 2021-10-30 | Construction | Commercial | Offices & Mall | Civil Works | Kemet | Eng Hany Yassin | Eng. Mohamed Ashry | New Capital | S | Private |  |  | 21460 | All | 71052428.57 | 71052428.57 | 66078758.5701 | 7% | 3310.924 | 0 | 3079.1593 | 0 | 0 | 0 | 0 | 0 | 15.65 | 4540091.2824 | 4222284.8927 | 2021
Point 90 New Cairo Mall | 2013-09-19 | 2015-09-18 | Construction | Commercial | Offices & Mall | Turn Key | Cairo Company for Housing & Development (CCHD) | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | Private | No of Shops | 75 | 69132.17 | Total | 146269451.13 | 145010925.68 | 129215876.9678 | 10.89% | 2097.5897 | 1933479.0091 | 1869.1136 | 1722878.3596 | 118.3074 | 109051.2695 | 105.421 | 97173.0603 | 6.77 | 21419634.517 | 19086540.1725 | 2013
Marassi Bridges Pkg 37 | 2012-08-01 | 2014-06-01 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Waleed Tag | Eng Mahmoud Mahlab | North Coast | D | Private |  |  |  | All | 27187290 | 26193836.68 | 27330602.3975 | -4.34% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.09 | 4301122.6076 | 4487783.6449 | 2012
Marassi Golf Maintance Building Pkg 58 | 2013-03-19 | 2015-01-18 | Construction | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Waleed Tag | Eng Mahmoud Mahlab | North Coast | D | Private |  |  |  | All | 5325286 | 4720405.25 | 5275181.8987 | -11.75% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 | 697253.3604 | 779199.6896 | 2013
Uptown Soil Stabilization Pkg 32 | 2012-08-05 | 2015-05-05 | Transportation | Infrastructure | L&L | Civil Works | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All | 5983238.64 | 17421145.8 | 21051883.5147 | -20.84% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.09 | 2860615.0739 | 3456795.3226 | 2012
Ismailia Bridge L&L | 2018-12-29 | 2019-03-29 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Ismailia | D | ARMY |  |  |  | All | 49485210.2 | 49485210.2 | 39588168 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.04 | 3085112.8554 | 2468090.2743 | 2018
El Obour Bridge B2 | 2014-07-30 | 2014-12-30 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Cairo | D | ARMY |  |  | 735 | All | 9000000 | 9000000 | 7200000 | 20% | 12244.898 | 0 | 9795.9184 | 0 | 1712.5731 | 0 | 1370.0585 | 0 | 7.15 | 1258741.2587 | 1006993.007 | 2014
Autoville Strip Mall | 2010-04-28 | 2014-04-28 | Construction | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 39524132 | 51072634 | 55255998 | -8.191% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36 | 9528476.4925 | 10308954.8507 | 2010
Uptown Service Buildings Pkg 17A | 2011-07-27 | 2013-12-26 | Transportation | Infrastructure | Tank | Civil Works | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All | 56114398 | 55905931 | 53843629.5863 | 3.689% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.66 | 9877372.9682 | 9513008.7608 | 2011
Sodic West Town Hub | 2013-01-01 | 2015-12-31 | Construction | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 28850000 | 54160920.41 | 56137642.32 | -3.65% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 | 8000135.9542 | 8292118.5111 | 2013
Dubai Port Sokhna Basin 1 | 2013-06-01 | 2015-09-01 | Transportation | Infrastructure | Networks | Civil Works | DPW | Eng Karim El Far | Eng. Omar Sobhy | Sokhna | D | Private |  |  |  | All | 34548331.29 | 34548331.29 | 27990071.4837 | 18.98% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 | 5103150.8552 | 4134427.1025 | 2013
Alexandria Bridges | 2010-10-01 | 2012-12-31 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Mohamed Abd El Wahab | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Alex | S | Private | m | 630 | 9135 | All | 32000000 | 35589876.5 | 28766462 | 19.17% | 3895.9909 | 56491.8675 | 3149.038 | 45661.0508 | 726.864 | 10539.5275 | 587.5071 | 8518.8528 | 5.36 | 6639902.3321 | 5366877.2388 | 2010
El Mahala Bridge | 2014-11-30 | 2015-11-30 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed Mostafa | Eng. Omar Sobhy | Mahalla | D | ARMY |  |  | 7830 | All | 68000000 | 67245402 | 48126832 | 28.43% | 8588.1739 | 0 | 6146.4664 | 0 | 1201.1432 | 0 | 859.6457 | 0 | 7.15 | 9404951.3287 | 6731025.4545 | 2014
El Wahat Bridge | 2015-02-16 | 2015-12-16 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | 6th of October | D | ARMY | m | 35 | 735 | All | 28176166.3603 | 22540933.0883 | 18032746.4706 | 20% | 30667.9362 | 644026.6597 | 24534.3489 | 515221.3277 | 0 | 0 | 0 | 0 | 7.83 | 2878790.9436 | 2303032.7549 | 2015
El Wahat Tunnel | 2015-02-16 | 2015-12-16 | Transportation | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | 6th of October | D | ARMY | m | 60 | 3000 | All | 18275304 | 18818015.28 | 13923981.6424 | 26.01% | 6272.6718 | 313633.588 | 4641.3272 | 232066.3607 | 801.1075 | 40055.3752 | 592.7621 | 29638.1048 | 7.83 | 2403322.5134 | 1778286.2889 | 2015
El Asmarat | 2014-06-14 | 2015-09-14 |  | Commercial | Offices & Mall | Civil Works | Arabian Group | Eng Karim El Far | Eng Mahmoud Mahlab | Cairo | D | Private |  |  |  | All | 6636851 | 6636851 | 8517150.2182 | -28.33% | [8 empty] | 7.15 | 928230.9091 | 1191209.8207 | 2014
Alegria DP Port | 2017-11-24 | 2021-12-24 | Transportation | Infrastructure | Networks | Civil Works | DPW | Eng Mohamed Mostafa | Eng. Omar Sobhy | Alegria | D | Private |  |  |  | All | 605714038 | 605714038 | 498059352 | 17.77% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.73 | 34163228.3136 | 28091334.0102 | 2017
El Alameen Bridge L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36 | 0 | 0 | 2010
El Asher of Ramadan Bridge L&L | 2010-01-01 | 2010-01-01 | Transportation | Infrastructure | L&L | Civil Works | Army Forces | Eng Adham Edward | Eng.adham edward | Cairo | D | ARMY |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36 | 0 | 0 | 2010
EMEC | 2011-03-20 | 2012-03-20 | Construction | Commercial | Offices & Mall | Civil Works | EMEC | Eng Mohamed Abd El Fatah | Eng Mahmoud Mahlab | 5th settelment | S | Private |  |  |  | All | 10688481.1 | 10688481.1 | 8907067.5833 | 16.67% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.86 | 1823972.884 | 1519977.4033 | 2011
Logestica Phase 01 | 2011-12-18 | 2013-08-18 | Industrial | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 31805400 | 31905026.19 | 27743501.0348 | 13.04% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.05 | 5273558.0479 | 4585702.6504 | 2011
Logestica Phase 02 | 2013-12-18 | 2015-02-18 | Industrial | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 20681422 | 20681422 | 16069494.51 | 22.3% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 | 3054862.9247 | 2373632.8671 | 2013
Logestica Phase 03 | 2013-12-18 | 2015-02-18 | Industrial | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 4820461 | 4820461 | 3681383 | 23.63% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 | 712032.644 | 543778.8774 | 2013
Sodic MV Cables | 2014-12-30 | 2015-12-30 | Transportation | Infrastructure | Networks | Civil Works | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 19589518 | 19589518 | 16384636.8472 | 16.36% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.15 | 2739792.7273 | 2291557.601 | 2014
Limak TB2 Cairo Airport Terminal | 2013-02-13 | 2015-11-13 | Construction | Commercial | Terminal | Civil Works | Limak | Eng Mohamed El Saman | Eng. Omar Sobhy | Cairo | S | Private |  |  |  | All | 49359671.05 | 119626844 | 96755558 | 19.12% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.77 | 17670139.4387 | 14291810.6352 | 2013
Twin Towers | 2011-06-30 | 2015-06-30 | Construction | Commercial | Offices & Mall | Turn Key | Arabian Group | Eng Karim El Far | Eng Mahmoud Mahlab | 6th of October | D | Private |  |  |  | All | 64000000.23 | 64000000.23 | 63714421.967 | 0.4462% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.36 | 11940298.5504 | 11887019.0237 | 2011
Aeon Towers Chiller Building | 2019-10-01 | 2020-11-30 | Construction | Commercial | Offices & Mall | Turn Key | Marakez | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | Private |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.31 | 0 | 0 | 2019
Electric Train LRT | 2018-11-01 | 2022-12-30 | Industrial | Industrial | Factory | Turn Key | NAT | Eng Hassan | Eng Mahmoud Mahlab | Cairo | S | Public |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.89 | 0 | 0 | 2018
Sea Shell Playa | 2021-01-01 | 2024-12-30 | Construction | Residential | Residential | Turn Key | New Giza | Eng Wael Ragabi | Eng. Omar Sobhy | North Coast | D | Private |  |  |  | All |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 | 0 | 0 | 2021

## Cash In-Month
Project Name | Month/Year | Cash In | Cash Out | Cum IN | Cum Out | Net Cash flow | Revised Contract Amount | % From Contract | Min Percent | Value of Work | Date | Source |  |  |  | Year | Main Category | Sub Category | Client
Marassi Civic Center Pkg 45 | 2013-12-30 | 19559799 | 0 | 19559799 | 0 | 19559799 | 56931016 | 34.36% | 18.9% | 1275096 | 2013-12-31 | original |  |  |  | 2013 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-01-30 | 1419824.74 | 1540259.6 | 20979623.74 | 1540259.6 | 19439364.14 | 56931016 | 34.15% |  | 3927841 | 2014-01-31 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-02-28 | 4012695.33 | 3090424.21 | 24992319.07 | 4630683.81 | 20361635.26 | 56931016 | 35.77% |  | 2146092 | 2014-02-28 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-03-30 | 2489526.62 | 3032287.47 | 27481845.69 | 7662971.28 | 19818874.41 | 56931016 | 34.81% |  | 4028277 | 2014-03-31 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-04-30 | 3000000 | 3378653.79 | 30481845.69 | 11041625.07 | 19440220.62 | 56931016 | 34.15% |  | 3352119 | 2014-04-30 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-05-30 | 2473267.87 | 3909050 | 32955113.56 | 14950675.07 | 18004438.49 | 56931016 | 31.63% |  | 4213793 | 2014-05-31 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-06-30 | 1746555.29 | 4994649.24 | 34701668.85 | 19945324.31 | 14756344.54 | 56931016 | 25.92% |  | 2407980 | 2014-06-30 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-07-30 | 2743644.04 | 2030895.4 | 37445312.89 | 21976219.71 | 15469093.18 | 56931016 | 27.17% |  | 484963 | 2014-07-31 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-08-30 | 945541.57 | 1820193.93 | 38390854.46 | 23796413.64 | 14594440.82 | 56931016 | 25.64% |  | 806066 | 2014-08-31 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-09-30 | 688683.32 | 1059803.11 | 39079537.78 | 24856216.75 | 14223321.03 | 56931016 | 24.98% |  | 320413 | 2014-09-30 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-10-30 | 0 | 958518.9284 | 39079537.78 | 25814735.6784 | 13264802.1016 | 56931016 | 23.3% |  | 811736 | 2014-10-31 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-11-30 | 795805.82 | 784665.56 | 39875343.6 | 26599401.2384 | 13275942.3616 | 56931016 | 23.32% |  | 1003619 | 2014-11-30 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2014-12-30 | 0 | 959821.19 | 39875343.6 | 27559222.4284 | 12316121.1716 | 56931016 | 21.63% |  | 702424 | 2014-12-31 | original |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-01-30 | 0 | 739606 | 39875343.6 | 28298828.4284 | 11576515.1716 | 56931016 | 20.33% |  | 818192 | 2015-01-31 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-02-28 | 798019 | 731493 | 40673362.6 | 29030321.4284 | 11643041.1716 | 56931016 | 20.45% |  | 1627690 | 2015-02-28 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-03-30 | 157942 | 1040284 | 40831304.6 | 30070605.4284 | 10760699.1716 | 56931016 | 18.9% |  | 751751 | 2015-03-31 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-04-30 | 1156272 | 803490 | 41987576.6 | 30874095.4284 | 11113481.1716 | 56931016 | 19.52% |  | 1218297 | 2015-04-30 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-05-30 | 1963896 | 956005 | 43951472.6 | 31830100.4284 | 12121372.1716 | 56931016 | 21.29% |  | 0 | 2015-05-31 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-06-30 | 592451 | 841121 | 44543923.6 | 32671221.4284 | 11872702.1716 | 56931016 | 20.85% |  | 2032372 | 2015-06-30 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-07-30 | 946975 | 566181 | 45490898.6 | 33237402.4284 | 12253496.1716 | 56931016 | 21.52% |  | 973468 | 2015-07-31 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-08-30 | 0 | 912402 | 45490898.6 | 34149804.4284 | 11341094.1716 | 56931016 | 19.92% |  | 1088031 | 2015-08-31 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-09-30 | 1709112 | 601472 | 47200010.6 | 34751276.4284 | 12448734.1716 | 56931016 | 21.87% |  | 181597 | 2015-09-30 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-10-30 | 0 | 382349 | 47200010.6 | 35133625.4284 | 12066385.1716 | 56931016 | 21.19% |  | 790090 | 2015-10-31 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-11-30 | 1693638 | 888784 | 48893648.6 | 36022409.4284 | 12871239.1716 | 56931016 | 22.61% |  | 1294652 | 2015-11-30 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2015-12-30 | 801254 | 732208 | 49694902.6 | 36754617.4284 | 12940285.1716 | 56931016 | 22.73% |  | 0 | 2015-12-31 | original |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-01-30 | 0 | 731407 | 49694902.6 | 37486024.4284 | 12208878.1716 | 56931016 | 21.45% |  | 416763 | 2016-01-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-02-28 | 798018.64 | 1011941 | 50492921.24 | 38497965.4284 | 11994955.8116 | 56931016 | 21.07% |  | 791891 | 2016-02-29 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-03-30 | 157942.32 | 551174 | 50650863.56 | 39049139.4284 | 11601724.1316 | 56931016 | 20.38% |  | 173722 | 2016-03-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-04-30 | 1156271.93 | 507787 | 51807135.49 | 39556926.4284 | 12250209.0616 | 56931016 | 21.52% |  | 2164773 | 2016-04-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-05-30 | 1910376.71 | 488764 | 53717512.2 | 40045690.4284 | 13671821.7716 | 56931016 | 24.01% |  | 0 | 2016-05-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-06-30 | 1539426.61 | 541908 | 55256938.81 | 40587598.4284 | 14669340.3816 | 56931016 | 25.77% |  | 0 | 2016-06-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-07-30 | 0 | 334273 | 55256938.81 | 40921871.4284 | 14335067.3816 | 56931016 | 25.18% |  | 3840878 | 2016-07-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-08-30 | 0 | 468748 | 55256938.81 | 41390619.4284 | 13866319.3816 | 56931016 | 24.36% |  | 0 | 2016-08-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-09-30 | 1709112.45 | 192197 | 56966051.26 | 41582816.4284 | 15383234.8316 | 56931016 | 27.02% |  | 869139 | 2016-09-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-10-30 | 0 | 166255 | 56966051.26 | 41749071.4284 | 15216979.8316 | 56931016 | 26.73% |  | 0 | 2016-10-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-11-30 | 0 | 117052 | 56966051.26 | 41866123.4284 | 15099927.8316 | 56931016 | 26.52% |  | 811904 | 2016-11-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2016-12-30 | 912839 | 120969 | 57878890.26 | 41987092.4284 | 15891797.8316 | 56931016 | 27.91% |  | 0 | 2016-12-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-01-30 | 2242394 | 557957 | 60121284.26 | 42545049.4284 | 17576234.8316 | 56931016 | 30.87% |  | 0 | 2017-01-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-02-28 | 0 | 833 | 60121284.26 | 42545882.4284 | 17575401.8316 | 56931016 | 30.87% |  | 0 | 2017-02-28 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-03-30 | 0 | 24387 | 60121284.26 | 42570269.4284 | 17551014.8316 | 56931016 | 30.83% |  | 0 | 2017-03-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-04-30 | 0 | 10662 | 60121284.26 | 42580931.4284 | 17540352.8316 | 56931016 | 30.81% |  | 0 | 2017-04-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-05-31 | 0 | 0 | 60121284.26 | 42580931.4284 | 17540352.8316 | 56931016 | 30.81% |  | 0 | 2017-05-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-06-30 | 0 | 3000 | 60121284.26 | 42583931.4284 | 17537352.8316 | 56931016 | 30.8% |  | 0 | 2017-06-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-07-30 | 0 | 3809 | 60121284.26 | 42587740.4284 | 17533543.8316 | 56931016 | 30.8% |  | 0 | 2017-07-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-08-30 | 0 | 167610 | 60121284.26 | 42755350.4284 | 17365933.8316 | 56931016 | 30.5% |  | 0 | 2017-08-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 45 | 2017-12-30 | 0 | 30720 | 60121284.26 | 42786070.4284 | 17335213.8316 | 56931016 | 30.45% |  | 0 | 2017-12-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
1 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Al Oula Infra | 2012-11-30 | 1282219.8 | 0 | 1282219.8 | 0 | 1282219.8 | 72946445.96 | 1.758% |  | 1102537.12 | 2012-11-30 | original |  | 1143780.12 |  | 2012 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2012-12-30 | 1642241.84 | 0 | 2924461.64 | 0 | 2924461.64 | 72946445.96 | 4.009% |  | 1555153.26 | 2012-12-30 | original |  |  |  | 2012 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-01-30 | 1372357.53 | 0 | 4296819.17 | 0 | 4296819.17 | 72946445.96 | 5.89% |  | 1984932.77 | 2013-01-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-02-28 | 0 | 0 | 4296819.17 | 0 | 4296819.17 | 72946445.96 | 5.89% |  |  | 2013-02-28 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-03-30 | 0 | 0 | 4296819.17 | 0 | 4296819.17 | 72946445.96 | 5.89% |  |  | 2013-03-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-04-30 | 1038522.64 | 0 | 5335341.81 | 0 | 5335341.81 | 72946445.96 | 7.314% |  | 455037.87 | 2013-04-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-05-30 | 152371.09 | 0 | 5487712.9 | 0 | 5487712.9 | 72946445.96 | 7.523% |  | 132334.03 | 2013-05-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-06-30 | 0 | 0 | 5487712.9 | 0 | 5487712.9 | 72946445.96 | 7.523% |  | 13152.45 | 2013-06-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-07-30 | 960436.47 | 0 | 6448149.37 | 0 | 6448149.37 | 72946445.96 | 8.84% |  | 922362.13 | 2013-07-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-08-30 | 970743.47 | 0 | 7418892.84 | 0 | 7418892.84 | 72946445.96 | 10.17% |  | 919264.65 | 2013-08-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-09-30 | 917923.51 | 0 | 8336816.35 | 0 | 8336816.35 | 72946445.96 | 11.43% |  | 905504.09 | 2013-09-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-10-30 | 894841.59 | 0 | 9231657.94 | 0 | 9231657.94 | 72946445.96 | 12.66% |  | 805285.14 | 2013-10-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-11-30 | 0 | 0 | 9231657.94 | 0 | 9231657.94 | 72946445.96 | 12.66% |  |  | 2013-11-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2013-12-30 | 0 | 0 | 9231657.94 | 0 | 9231657.94 | 72946445.96 | 12.66% |  |  | 2013-12-30 | original |  |  |  | 2013 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-01-30 | 953478.06 | 155553 | 10185136 | 155553 | 10029583 | 72946445.96 | 13.75% |  | 3573112.59 | 2014-01-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-02-28 | 1984294.87 | 1259419.84 | 12169430.87 | 1414972.84 | 10754458.03 | 72946445.96 | 14.74% |  | 2330524.48 | 2014-02-28 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-03-30 | 0 | 446040.16 | 12169430.87 | 1861013 | 10308417.87 | 72946445.96 | 14.13% |  |  | 2014-03-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-04-30 | 2835609.68 | 1383606.64 | 15005040.55 | 3244619.64 | 11760420.91 | 72946445.96 | 16.12% |  | 920317.32 | 2014-04-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-05-30 | 1000000 | 911465.1 | 16005040.55 | 4156084.74 | 11848955.81 | 72946445.96 | 16.24% |  | 2261731.74 | 2014-05-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-06-30 | 2482317.59 | 1993077.2 | 18487358.14 | 6149161.94 | 12338196.2 | 72946445.96 | 16.91% |  | 2160160.31 | 2014-06-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-07-30 | 1374359.02 | 1907782.83 | 19861717.16 | 8056944.77 | 11804772.39 | 72946445.96 | 16.18% |  | 3157921 | 2014-07-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-08-30 | 155610.6 | 1027649.39 | 20017327.76 | 9084594.16 | 10932733.6 | 72946445.96 | 14.99% |  | 1931615.02 | 2014-08-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-09-30 | 3194521.8 | 1252838.1 | 23211849.56 | 10337432.26 | 12874417.3 | 72946445.96 | 17.65% |  | 2303487.2 | 2014-09-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-10-30 | 263359.07 | 1671940.6496 | 23475208.63 | 12009372.9096 | 11465835.7204 | 72946445.96 | 15.72% |  | 560098.94 | 2014-10-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-11-30 | 1237279.6 | 769672.42 | 24712488.23 | 12779045.3296 | 11933442.9004 | 72946445.96 | 16.36% |  | 2652754.46 | 2014-11-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2014-12-30 | 1569343.89 | 1890682.92 | 26281832.12 | 14669728.2496 | 11612103.8704 | 72946445.96 | 15.92% |  | 2735912.02 | 2014-12-30 | original |  |  |  | 2014 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2015-01-30 | 0 | 0 | 26281832.12 | 14669728.2496 | 11612103.8704 | 72946445.96 | 15.92% |  | 0 | 2015-01-30 | original |  |  |  | 2015 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2015-02-28 | 1561421.03 | 0 | 27843253.15 | 14669728.2496 | 13173524.9004 | 72946445.96 | 18.06% |  | 1606475.57 | 2015-02-28 | original |  |  |  | 2015 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2015-03-30 | 332453.76 | 0 | 28175706.91 | 14669728.2496 | 13505978.6604 | 72946445.96 | 18.51% |  | 362162.45 | 2015-03-30 | original |  |  |  | 2015 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2015-04-30 | 1320407.19 | 0 | 29496114.1 | 14669728.2496 | 14826385.8504 | 72946445.96 | 20.33% |  | 1897290.31 | 2015-04-30 | original |  |  |  | 2015 | Infrastructure | Networks | Sewedy
Al Oula Infra | 2015-05-30 | 430210.52 | 0 | 29926324.62 | 14669728.2496 | 15256596.3704 | 72946445.96 | 20.91% |  | 428247.26 | 2015-05-30 | original |  |  |  | 2015 | Infrastructure | Networks | Sewedy
2 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
New Giza Phase 01 | 2014-09-30 | 0 | 420681.66 | 0 | 420681.66 | -420681.66 | 172216796.0405 | -0.2443% |  |  |  | original |  |  |  | 2014 | Commercial | University | New Giza
New Giza Phase 01 | 2014-10-30 | 33126223 | 22345868.7 | 33126223 | 22766550.36 | 10359672.64 | 172216796.0405 | 6.015% |  | 4070308 | 2014-10-31 | original |  |  |  | 2014 | Commercial | University | New Giza
New Giza Phase 01 | 2014-11-30 | 2835173 | 4534947.27 | 35961396 | 27301497.63 | 8659898.37 | 172216796.0405 | 5.028% |  | 5457746 | 2014-11-30 | original |  |  |  | 2014 | Commercial | University | New Giza
New Giza Phase 01 | 2014-12-30 | 3801593 | 10060401.03 | 39762989 | 37361898.66 | 2401090.34 | 172216796.0405 | 1.394% |  | 7076513 | 2014-12-31 | original |  |  |  | 2014 | Commercial | University | New Giza
New Giza Phase 01 | 2015-01-30 | 4928609 | 6194030 | 44691598 | 43555928.66 | 1135669.34 | 172216796.0405 | 0.6594% |  | 7510605 | 2015-01-31 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-02-28 | 5377358 | 9392461 | 50068956 | 52948389.66 | -2879433.66 | 172216796.0405 | -1.672% |  | 15322889 | 2015-02-28 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-03-30 | 12437428 | 10726300 | 62506384 | 63674689.66 | -1168305.66 | 172216796.0405 | -0.6784% |  | 21416423 | 2015-03-31 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-04-30 | 14852301 | 26465474 | 77358685 | 90140163.66 | -12781478.66 | 172216796.0405 | -7.422% |  | 26061408 | 2015-04-30 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-05-30 | 19864489 | 6089978 | 97223174 | 96230141.66 | 993032.34 | 172216796.0405 | 0.5766% |  | 26433358 | 2015-05-31 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-06-30 | 0 | 18417415 | 97223174 | 114647556.66 | -17424382.66 | 172216796.0405 | -10.12% |  | 12518448 | 2015-06-30 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-07-30 | 18290570 | 14025027 | 115513744 | 128672583.66 | -13158839.66 | 172216796.0405 | -7.641% |  | 6572985 | 2015-07-31 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-08-30 | 8712875 | 9340026 | 124226619 | 138012609.66 | -13785990.66 | 172216796.0405 | -8.005% |  | 4027853 | 2015-08-31 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-09-30 | 3740191 | 6902824 | 127966810 | 144915433.66 | -16948623.66 | 172216796.0405 | -9.841% |  | 11787603 | 2015-09-30 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-10-30 | 3810161 | 1736860 | 131776971 | 146652293.66 | -14875322.66 | 172216796.0405 | -8.638% |  | 3038222 | 2015-10-31 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-11-30 | 0 | 1272238 | 131776971 | 147924531.66 | -16147560.66 | 172216796.0405 | -9.376% |  | 2377345 | 2015-11-30 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2015-12-30 | 6962059 | 9169059 | 138739030 | 157093590.66 | -18354560.66 | 172216796.0405 | -10.66% |  | 4185609 | 2015-12-31 | original |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 01 | 2016-01-30 | 0 | 580372 | 138739030 | 157673962.66 | -18934932.66 | 172216796.0405 | -10.99% |  | 2127586 | 2016-01-31 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-02-28 | 0 | 484922 | 138739030 | 158158884.66 | -19419854.66 | 172216796.0405 | -11.28% |  | 3677610 | 2016-02-29 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-03-30 | 3770042 | 2480314 | 142509072 | 160639198.66 | -18130126.66 | 172216796.0405 | -10.53% |  | 494877 | 2016-03-31 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-04-30 | 6658941 | 5657717 | 149168013 | 166296915.66 | -17128902.66 | 172216796.0405 | -9.946% |  | 2071377 | 2016-04-30 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-05-30 | 1785421 | 401446 | 150953434 | 166698361.66 | -15744927.66 | 172216796.0405 | -9.143% |  | 239952 | 2016-05-31 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-06-30 | 1284266 | 1837421 | 152237700 | 168535782.66 | -16298082.66 | 172216796.0405 | -9.464% |  | 0 | 2016-06-30 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-07-30 | 0 | 637615 | 152237700 | 169173397.66 | -16935697.66 | 172216796.0405 | -9.834% |  | 2008293 | 2016-07-31 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-08-30 | 1538142 | 383186 | 153775842 | 169556583.66 | -15780741.66 | 172216796.0405 | -9.163% |  | 0 | 2016-08-31 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-09-30 | 7242730 | 3487128 | 161018572 | 173043711.66 | -12025139.66 | 172216796.0405 | -6.983% |  | 573623 | 2016-09-30 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-10-30 | 0 | 76623 | 161018572 | 173120334.66 | -12101762.66 | 172216796.0405 | -7.027% |  | 0 | 2016-10-31 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-11-30 | 1832963 | 36836 | 162851535 | 173157170.66 | -10305635.66 | 172216796.0405 | -5.984% |  | 0 | 2016-11-30 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2016-12-30 | 0 | 444420 | 162851535 | 173601590.66 | -10750055.66 | 172216796.0405 | -6.242% |  | 0 | 2016-12-31 | original |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 01 | 2017-01-30 | 0 | 272750 | 162851535 | 173874340.66 | -11022805.66 | 172216796.0405 | -6.401% |  | 0 | 2017-01-31 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-02-28 | 0 | 7016 | 162851535 | 173881356.66 | -11029821.66 | 172216796.0405 | -6.405% |  | 0 | 2017-02-28 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-03-30 | 0 | 6845 | 162851535 | 173888201.66 | -11036666.66 | 172216796.0405 | -6.409% |  | 0 | 2017-03-31 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-04-30 | 0 | 753828 | 162851535 | 174642029.66 | -11790494.66 | 172216796.0405 | -6.846% |  | 0 | 2017-04-30 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-05-31 | 0 | 0 | 162851535 | 174642029.66 | -11790494.66 | 172216796.0405 | -6.846% |  | 0 | 2017-05-31 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-06-30 | 0 | 7961 | 162851535 | 174649990.66 | -11798455.66 | 172216796.0405 | -6.851% |  | 0 | 2017-06-30 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-07-30 | 0 | 4977 | 162851535 | 174654967.66 | -11803432.66 | 172216796.0405 | -6.854% |  | 0 | 2017-07-31 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-08-30 | 4029400 | 2000000 | 166880935 | 176654967.66 | -9774032.66 | 172216796.0405 | -5.675% |  | 0 | 2017-08-31 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-10-30 | 0 | 0 | 166880935 | 176654967.66 | -9774032.66 | 172216796.0405 | -5.675% |  | 6377727.87 | 2017-10-31 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-11-30 | 4561573 | 0 | 171442508 | 176654967.66 | -5212459.66 | 172216796.0405 | -3.027% |  | 0 | 2017-11-30 | original |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 01 | 2017-12-30 | 0 | 2975394 | 171442508 | 179630361.66 | -8187853.66 | 172216796.0405 | -4.754% |  | 0 | 2017-12-31 | original |  |  |  | 2017 | Commercial | University | New Giza
3 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Hyper Solimanya | 2014-06-30 | 16750000 | 52005.48 | 16750000 | 52005.48 | 16697994.52 | 110450184.62 | 15.12% |  |  |  | original |  |  |  | 2014 | Commercial | Market | Hyper
Hyper Solimanya | 2014-07-30 | 0 | 388799.06 | 16750000 | 440804.54 | 16309195.46 | 110450184.62 | 14.77% |  |  |  | original |  |  |  | 2014 | Commercial | Market | Hyper
Hyper Solimanya | 2014-08-30 | 1708588 | 2597195.25 | 18458588 | 3037999.79 | 15420588.21 | 110450184.62 | 13.96% |  |  |  | original |  |  |  | 2014 | Commercial | Market | Hyper
Hyper Solimanya | 2014-09-30 | 1348749 | 1716979.29 | 19807337 | 4754979.08 | 15052357.92 | 110450184.62 | 13.63% |  |  |  | original |  |  |  | 2014 | Commercial | Market | Hyper
Hyper Solimanya | 2014-10-30 | 5087011 | 4728640.44 | 24894348 | 9483619.52 | 15410728.48 | 110450184.62 | 13.95% |  |  |  | original |  |  |  | 2014 | Commercial | Market | Hyper
Hyper Solimanya | 2014-11-30 | 6510468 | 8169739.38 | 31404816 | 17653358.9 | 13751457.1 | 110450184.62 | 12.45% |  | 28151956 | 2014-11-30 | original |  |  |  | 2014 | Commercial | Market | Hyper
Hyper Solimanya | 2014-12-30 | 12930069.4 | 11832712.72 | 44334885.4 | 29486071.62 | 14848813.78 | 110450184.62 | 13.44% |  | 5160865 | 2014-12-31 | original |  |  |  | 2014 | Commercial | Market | Hyper
Hyper Solimanya | 2015-01-30 | 3259514 | 5062604 | 47594399.4 | 34548675.62 | 13045723.78 | 110450184.62 | 11.81% |  | 6233182 | 2015-01-31 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-02-28 | 4204986 | 6758235 | 51799385.4 | 41306910.62 | 10492474.78 | 110450184.62 | 9.5% |  | 4894046 | 2015-02-28 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-03-30 | 3342260 | 5459976 | 55141645.4 | 46766886.62 | 8374758.78 | 110450184.62 | 7.582% |  | 3151181 | 2015-03-31 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-04-30 | 448748 | 5255727 | 55590393.4 | 52022613.62 | 3567779.78 | 110450184.62 | 3.23% |  | 7766186 | 2015-04-30 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-05-30 | 9019935 | 4712105 | 64610328.4 | 56734718.62 | 7875609.78 | 110450184.62 | 7.13% |  | 5157059 | 2015-05-31 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-06-30 | 4536200 | 4383659 | 69146528.4 | 61118377.62 | 8028150.78 | 110450184.62 | 7.269% |  | 5968470 | 2015-06-30 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-07-30 | 0 | 6130413 | 69146528.4 | 67248790.62 | 1897737.78 | 110450184.62 | 1.718% |  | 5601446 | 2015-07-31 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-08-30 | 5435883 | 5856543 | 74582411.4 | 73105333.62 | 1477077.78 | 110450184.62 | 1.337% |  | 4308584 | 2015-08-31 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-09-30 | 5908096 | 4259405 | 80490507.4 | 77364738.62 | 3125768.78 | 110450184.62 | 2.83% |  | 5308802 | 2015-09-30 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-10-30 | 5178516 | 2710525 | 85669023.4 | 80075263.62 | 5593759.78 | 110450184.62 | 5.065% |  | 3400766 | 2015-10-31 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-11-30 | 6198762 | 3408392 | 91867785.4 | 83483655.62 | 8384129.78 | 110450184.62 | 7.591% |  | 0 | 2015-11-30 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2015-12-30 | 2307372 | 1727318 | 94175157.4 | 85210973.62 | 8964183.78 | 110450184.62 | 8.116% |  | 0 | 2015-12-31 | original |  |  |  | 2015 | Commercial | Market | Hyper
Hyper Solimanya | 2016-01-30 | 0 | 1983705 | 94175157.4 | 87194678.62 | 6980478.78 | 110450184.62 | 6.32% |  | 0 | 2016-01-31 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-02-28 | 0 | 1157008 | 94175157.4 | 88351686.62 | 5823470.78 | 110450184.62 | 5.272% |  | 0 | 2016-02-29 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-03-30 | 0 | 340596 | 94175157.4 | 88692282.62 | 5482874.78 | 110450184.62 | 4.964% |  | 0 | 2016-03-31 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-04-30 | 0 | 218086 | 94175157.4 | 88910368.62 | 5264788.78 | 110450184.62 | 4.767% |  | 6387675 | 2016-04-30 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-05-30 | 0 | 960676 | 94175157.4 | 89871044.62 | 4304112.78 | 110450184.62 | 3.897% |  | 3041879 | 2016-05-31 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-06-30 | 0 | 752280 | 94175157.4 | 90623324.62 | 3551832.78 | 110450184.62 | 3.216% |  | 0 | 2016-06-30 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-07-30 | 1000000 | 763392 | 95175157.4 | 91386716.62 | 3788440.78 | 110450184.62 | 3.43% |  | 5736350 | 2016-07-31 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-08-30 | 1000000 | 2546647 | 96175157.4 | 93933363.62 | 2241793.78 | 110450184.62 | 2.03% |  | 0 | 2016-08-31 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-09-30 | 803468 | 858598 | 96978625.4 | 94791961.62 | 2186663.78 | 110450184.62 | 1.98% |  | 2477444 | 2016-09-30 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-10-30 | 0 | 1705520 | 96978625.4 | 96497481.62 | 481143.78 | 110450184.62 | 0.4356% |  | 2737674 | 2016-10-31 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-11-30 | 5417312 | 1260821 | 102395937.4 | 97758302.62 | 4637634.78 | 110450184.62 | 4.199% |  | 0 | 2016-11-30 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2016-12-30 | 0 | 1023770 | 102395937.4 | 98782072.62 | 3613864.78 | 110450184.62 | 3.272% |  | 5227900 | 2016-12-31 | original |  |  |  | 2016 | Commercial | Market | Hyper
Hyper Solimanya | 2017-01-30 | 0 | 896570 | 102395937.4 | 99678642.62 | 2717294.78 | 110450184.62 | 2.46% |  | 0 | 2017-01-31 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-02-28 | 4889400 | 291102 | 107285337.4 | 99969744.62 | 7315592.78 | 110450184.62 | 6.623% |  | 0 | 2017-02-28 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-03-30 | 0 | 763038 | 107285337.4 | 100732782.62 | 6552554.78 | 110450184.62 | 5.933% |  | 0 | 2017-03-31 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-04-30 | 0 | 1632574 | 107285337.4 | 102365356.62 | 4919980.78 | 110450184.62 | 4.454% |  | 0 | 2017-04-30 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-05-31 | 0 | 0 | 107285337.4 | 102365356.62 | 4919980.78 | 110450184.62 | 4.454% |  | 0 | 2017-05-31 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-06-30 | 0 | 87975 | 107285337.4 | 102453331.62 | 4832005.78 | 110450184.62 | 4.375% |  | 0 | 2017-06-30 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-07-30 | 0 | 918963 | 107285337.4 | 103372294.62 | 3913042.78 | 110450184.62 | 3.543% |  | 0 | 2017-07-31 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-09-30 | 1321895 | 0 | 108607232.4 | 103372294.62 | 5234937.78 | 110450184.62 | 4.74% |  | 0 | 2017-09-30 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-10-30 | 0 | 186197 | 108607232.4 | 103558491.62 | 5048740.78 | 110450184.62 | 4.571% |  | 0 | 2017-10-31 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2017-11-30 | 0 | 161237 | 108607232.4 | 103719728.62 | 4887503.78 | 110450184.62 | 4.425% |  | 0 | 2017-11-30 | original |  |  |  | 2017 | Commercial | Market | Hyper
Hyper Solimanya | 2020-08-30 | 4000000 | 0 | 112607232.4 | 103719728.62 | 8887503.78 | 110450184.62 | 8.047% |  |  | 2020-08-17 | added 1 |  |  |  | 2020 | Commercial | Market | Hyper
4 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
5 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Maxium Mall | 2015-03-30 | 15224252 | 4822917 | 15224252 | 4822917 | 10401335 | 98576600 | 10.55% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-04-30 | 0 | 4255994 | 15224252 | 9078911 | 6145341 | 98576600 | 6.234% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-05-30 | 0 | 4190107 | 15224252 | 13269018 | 1955234 | 98576600 | 1.983% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-06-30 | 244015 | 3140642 | 15468267 | 16409660 | -941393 | 98576600 | -0.955% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-07-30 | 400000 | 4534973 | 15868267 | 20944633 | -5076366 | 98576600 | -5.15% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-08-30 | 0 | 3972390 | 15868267 | 24917023 | -9048756 | 98576600 | -9.179% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-09-30 | 2360774 | 3474254 | 18229041 | 28391277 | -10162236 | 98576600 | -10.31% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-10-30 | 0 | 4987025 | 18229041 | 33378302 | -15149261 | 98576600 | -15.37% |  |  | 2019-11-30 | added cash in 3 |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-11-30 | 0 | 3603449 | 18229041 | 36981751 | -18752710 | 98576600 | -19.02% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2015-12-30 | 5000000 | 3764312 | 23229041 | 40746063 | -17517022 | 98576600 | -17.77% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-01-30 | 0 | 2595837 | 23229041 | 43341900 | -20112859 | 98576600 | -20.4% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-02-28 | 5451339 | 3109944 | 28680380 | 46451844 | -17771464 | 98576600 | -18.03% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-03-30 | 7015308 | 4990806 | 35695688 | 51442650 | -15746962 | 98576600 | -15.97% | [7 empty] | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-04-30 | 3110526 | 5060261 | 38806214 | 56502911 | -17696697 | 98576600 | -17.95% |  | 1439514 | 2015-03-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-05-30 | 7420666 | 6104900 | 46226880 | 62607811 | -16380931 | 98576600 | -16.62% |  | 1771139 | 2015-04-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-06-30 | 3865200 | 8773380 | 50092080 | 71381191 | -21289111 | 98576600 | -21.6% |  | 2707257 | 2015-05-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-07-30 | 1519015 | 4405159 | 51611095 | 75786350 | -24175255 | 98576600 | -24.52% |  | 0 | 2015-06-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-08-30 | 4813144 | 3187880 | 56424239 | 78974230 | -22549991 | 98576600 | -22.88% |  | 0 | 2015-07-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-09-30 | 5771123 | 2199541 | 62195362 | 81173771 | -18978409 | 98576600 | -19.25% |  | 8255695 | 2015-08-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-10-30 | 0 | 2712710 | 62195362 | 83886481 | -21691119 | 98576600 | -22% |  | 2375384 | 2015-09-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-11-30 | 2273138 | 2562221 | 64468500 | 86448702 | -21980202 | 98576600 | -22.3% |  | 2636612 | 2015-10-31 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2016-12-30 | 2018939 | 2047212 | 66487439 | 88495914 | -22008475 | 98576600 | -22.33% |  | 4413767 | 2015-11-30 | original |  |  |  | 2016 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-01-30 | 0 | 2352202 | 66487439 | 90848116 | -24360677 | 98576600 | -24.71% |  | 6388454 | 2015-12-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-02-28 | 2408492 | 1408853 | 68895931 | 92256969 | -23361038 | 98576600 | -23.7% |  | 3641125 | 2016-01-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-03-30 | 4411465.16 | 1221082 | 73307396.16 | 93478051 | -20170654.84 | 98576600 | -20.46% |  | 6086206 | 2016-02-29 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-04-30 | 0 | 1599875.05 | 73307396.16 | 95077926.05 | -21770529.89 | 98576600 | -22.08% |  | 5036933 | 2016-03-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-05-30 | 0 | 586227 | 73307396.16 | 95664153.05 | -22356756.89 | 98576600 | -22.68% |  | 4775714 | 2016-04-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-06-30 | 2000000 | 1157847 | 75307396.16 | 96822000.05 | -21514603.89 | 98576600 | -21.83% |  | 6573287 | 2016-05-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-07-30 | 1000000 | 404994.04 | 76307396.16 | 97226994.09 | -20919597.93 | 98576600 | -21.22% |  | 6082936 | 2016-06-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-08-30 | 2000000 | 619580.74 | 78307396.16 | 97846574.83 | -19539178.67 | 98576600 | -19.82% |  | 5840450 | 2016-07-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-09-30 | 0 | 218075 | 78307396.16 | 98064649.83 | -19757253.67 | 98576600 | -20.04% |  | 3848433 | 2016-08-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-10-30 | 0 | 304284 | 78307396.16 | 98368933.83 | -20061537.67 | 98576600 | -20.35% |  | 7341288 | 2016-09-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-11-30 | 0 | 323734 | 78307396.16 | 98692667.83 | -20385271.67 | 98576600 | -20.68% |  | 2797229 | 2016-10-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2017-12-30 | 0 | 644131.38 | 78307396.16 | 99336799.21 | -21029403.05 | 98576600 | -21.33% |  | 3527531 | 2016-11-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-01-30 | 1000000 | 50706.56 | 79307396.16 | 99387505.77 | -20080109.61 | 98576600 | -20.37% |  | 2687601 | 2016-12-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-02-28 | 0 | 784 | 79307396.16 | 99388289.77 | -20080893.61 | 98576600 | -20.37% |  | 0 | 2017-01-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-03-30 | 0 | 171689.7 | 79307396.16 | 99559979.47 | -20252583.31 | 98576600 | -20.55% |  | 0 | 2017-02-28 | original |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-05-30 | 2900000 | 64250.32 | 82207396.16 | 99624229.79 | -17416833.63 | 98576600 | -17.67% |  |  | 2017-03-30 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-06-30 | 0 | 98524.93 | 82207396.16 | 99722754.72 | -17515358.56 | 98576600 | -17.77% |  | 2104189 | 2017-03-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-07-30 | 2900000 | 800 | 85107396.16 | 99723554.72 | -14616158.56 | 98576600 | -14.83% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-08-30 | 0 | 350928.63 | 85107396.16 | 100074483.35 | -14967087.19 | 98576600 | -15.18% |  | 0 | 2017-04-30 | original |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-10-30 | 1000000 | 400000 | 86107396.16 | 100474483.35 | -14367087.19 | 98576600 | -14.57% |  | 3722169 | 2017-05-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-11-30 | 0 | 27666.56 | 86107396.16 | 100502149.91 | -14394753.75 | 98576600 | -14.6% |  | 0 | 2017-06-30 | original |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2018-12-30 | 0 | 14.06 | 86107396.16 | 100502163.97 | -14394767.81 | 98576600 | -14.6% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2019-01-30 | 0 | 2340522.73 | 86107396.16 | 102842686.7 | -16735290.54 | 98576600 | -16.98% |  | 0 | 2017-07-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2019-03-30 | 0 | 116366.16 | 86107396.16 | 102959052.86 | -16851656.7 | 98576600 | -17.09% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2019-07-30 | 4000000 | 0 | 90107396.16 | 102959052.86 | -12851656.7 | 98576600 | -13.04% |  | 0 | 2017-08-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2019-12-30 | 6235954 | 0 | 96343350.16 | 102959052.86 | -6615702.7 | 98576600 | -6.711% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2020-06-30 | 0 | 42300 | 96343350.16 | 103001352.86 | -6658002.7 | 98576600 | -6.754% |  | 0 | 2017-09-30 | original |  |  |  | 2020 | Commercial | Offices & Mall | Maxim
Maxium Mall | 2020-10-30 | 3250000 | 0 | 99593350.16 | 103001352.86 | -3408002.7 | 98576600 | -3.457% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Maxim
6 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Ataqqa Power Plant | 2014-12-30 | 37499946 | 2929502.47 | 37499946 | 2929502.47 | 34570443.53 | 184387980.81 | 18.75% |  |  |  | cash out both |  |  |  | 2014 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-01-30 | 0 | 2648622 | 37499946 | 5578124.47 | 31921821.53 | 184387980.81 | 17.31% |  | 0 | 2017-11-30 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-02-28 | 10000000 | 5378106 | 47499946 | 10956230.47 | 36543715.53 | 184387980.81 | 19.82% |  |  |  | cash out both |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-03-30 | 20289932 | 7624306 | 67789878 | 18580536.47 | 49209341.53 | 184387980.81 | 26.69% |  | 0 | 2017-12-31 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-04-30 | 21735246 | 12042770 | 89525124 | 30623306.47 | 58901817.53 | 184387980.81 | 31.94% |  |  |  | cash out both |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-05-30 | 4639446 | 13147883 | 94164570 | 43771189.47 | 50393380.53 | 184387980.81 | 27.33% |  |  | 2018-01-21 | added cash in 3 |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-06-30 | 4379194 | 8664394 | 98543764 | 52435583.47 | 46108180.53 | 184387980.81 | 25.01% |  |  |  | cash out both |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-07-30 | 11763312 | 3142626 | 110307076 | 55578209.47 | 54728866.53 | 184387980.81 | 29.68% |  |  |  | cash out both |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-08-30 | 3392373 | 5973388 | 113699449 | 61551597.47 | 52147851.53 | 184387980.81 | 28.28% |  |  |  | cash out both |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-09-30 | 3304852 | 4958701 | 117004301 | 66510298.47 | 50494002.53 | 184387980.81 | 27.38% |  |  | 2018-05-27 | added cash in 3 |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-10-30 | 5133030 | 4105409 | 122137331 | 70615707.47 | 51521623.53 | 184387980.81 | 27.94% |  |  |  | cash out both |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-11-30 | 8929234 | 3145301 | 131066565 | 73761008.47 | 57305556.53 | 184387980.81 | 31.08% |  |  |  | cash out both |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2015-12-30 | 4794332 | 3979589 | 135860897 | 77740597.47 | 58120299.53 | 184387980.81 | 31.52% |  |  | 2018-07-09 | added cash in 3 |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-01-30 | 8242355 | 3395313 | 144103252 | 81135910.47 | 62967341.53 | 184387980.81 | 34.15% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-02-28 | 10640355 | 3334406 | 154743607 | 84470316.47 | 70273290.53 | 184387980.81 | 38.11% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-03-30 | 10455766 | 3139710 | 165199373 | 87610026.47 | 77589346.53 | 184387980.81 | 42.08% |  |  | 2018-10-25 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-04-30 | 0 | 895818 | 165199373 | 88505844.47 | 76693528.53 | 184387980.81 | 41.59% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-05-30 | 0 | 534039 | 165199373 | 89039883.47 | 76159489.53 | 184387980.81 | 41.3% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-06-30 | 0 | 770631 | 165199373 | 89810514.47 | 75388858.53 | 184387980.81 | 40.89% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-07-30 | 13000000 | 370048 | 178199373 | 90180562.47 | 88018810.53 | 184387980.81 | 47.74% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-08-30 | 0 | 176959 | 178199373 | 90357521.47 | 87841851.53 | 184387980.81 | 47.64% |  |  | 2019-07-17 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-09-30 | 0 | 430418 | 178199373 | 90787939.47 | 87411433.53 | 184387980.81 | 47.41% |  |  | 2019-12-09 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-10-30 | 0 | 106569 | 178199373 | 90894508.47 | 87304864.53 | 184387980.81 | 47.35% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-11-30 | 1357575 | 9308 | 179556948 | 90903816.47 | 88653131.53 | 184387980.81 | 48.08% |  |  | 2020-10-12 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2016-12-30 | 0 | 150084 | 179556948 | 91053900.47 | 88503047.53 | [9 empty] | 2016 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2017-01-30 | 0 | 100000 | 179556948 | 91153900.47 | 88403047.53 | 184387980.81 | 47.94% |  | 0 | 2014-12-31 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2017-05-30 | 2092941 | 0 | 181649889 | 91153900.47 | 90495988.53 | 184387980.81 | 49.08% |  | 15677598 | 2015-01-31 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Ataqqa Power Plant | 2017-06-30 | 0 | 200000 | 181649889 | 91353900.47 | 90295988.53 | 184387980.81 | 48.97% |  | 9136479.17 | 2015-02-28 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
7 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
8 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Marassi Tanks PKG 22 | 2015-04-30 | 0 | 545325 | 0 | 545325 | -545325 | 18438370 | -2.958% |  | 0 | 2016-10-30 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-05-30 | 0 | 338808 | 0 | 884133 | -884133 | 18438370 | -4.795% |  | 1793763 | 2016-11-30 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-06-30 | 0 | 787544 | 0 | 1671677 | -1671677 | 18438370 | -9.066% |  | 0 | 2016-12-30 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-07-30 | 313398 | 970980 | 313398 | 2642657 | -2329259 | 18438370 | -12.63% |  | 0 | 2017-01-30 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-08-30 | 1124042 | 2050996 | 1437440 | 4693653 | -3256213 | 18438370 | -17.66% |  | 0 | 2017-02-28 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-09-30 | 1721144 | 1237752 | 3158584 | 5931405 | -2772821 | 18438370 | -15.04% |  | 73561 | 2017-03-30 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-10-30 | 3075432 | 621081 | 6234016 | 6552486 | -318470 | 18438370 | -1.727% |  | 0 | 2017-04-30 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-11-30 | 51999 | 971120 | 6286015 | 7523606 | -1237591 | 18438370 | -6.712% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2015-12-30 | 1983258 | 1166958 | 8269273 | 8690564 | -421291 | 18438370 | -2.285% |  | 0 | 2017-05-30 | original |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-01-30 | 0 | 722559 | 8269273 | 9413123 | -1143850 | 18438370 | -6.204% |  | 8051960 | 2017-06-30 | original |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-02-28 | 728974 | 824337 | 8998247 | 10237460 | -1239213 | 18438370 | -6.721% |  | 0 | 2017-07-30 | original |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-03-30 | 306588 | 1059766 | 9304835 | 11297226 | -1992391 | 18438370 | -10.81% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-04-30 | 1205323 | 465410 | 10510158 | 11762636 | -1252478 | 18438370 | -6.793% |  | 0 | 2017-08-30 | original |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-05-30 | 136297 | 743758 | 10646455 | 12506394 | -1859939 | 18438370 | -10.09% |  | 0 | 2017-09-30 | original |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-06-30 | 1080850 | 1726525 | 11727305 | 14232919 | -2505614 | 18438370 | -13.59% |  | 0 | 2017-12-30 | original |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-07-30 | 763400 | 309096 | 12490705 | 14542015 | -2051310 | 18438370 | -11.13% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-08-30 | 0 | 635340 | 12490705 | 15177355 | -2686650 | 18438370 | -14.57% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-09-30 | 1345167 | 431331 | 13835872 | 15608686 | -1772814 | 18438370 | -9.615% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-10-30 | 337754 | 181696 | 14173626 | 15790382 | -1616756 | 18438370 | -8.768% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-11-30 | 639374 | 303192 | 14813000 | 16093574 | -1280574 | 18438370 | -6.945% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2016-12-30 | 0 | 260192 | 14813000 | 16353766 | -1540766 | 18438370 | -8.356% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-01-30 | 0 | 212226 | 14813000 | 16565992 | -1752992 | 18438370 | -9.507% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-02-28 | 0 | 52219 | 14813000 | 16618211 | -1805211 | 18438370 | -9.791% |  |  | 2018-12-24 | added cash in 3 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-03-30 | 2381296 | 154004 | 17194296 | 16772215 | 422081 | 18438370 | 2.289% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-04-30 | 0 | 34882 | 17194296 | 16807097 | 387199 | 18438370 | 2.1% |  |  | 2019-01-03 | added cash in 3 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-05-30 | 370298.13 | 0 | 17564594.13 | 16807097 | 757497.13 | 18438370 | 4.108% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-06-30 | 0 | 29782 | 17564594.13 | 16836879 | 727715.13 | 18438370 | 3.947% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-07-30 | 0 | 159247 | 17564594.13 | 16996126 | 568468.13 | 18438370 | 3.083% |  |  | 2019-08-25 | added cash in 3 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-09-30 | 0 | 24109 | 17564594.13 | 17020235 | 544359.13 | 18438370 | 2.952% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2017-11-30 | 0 | 6049 | 17564594.13 | 17026284 | 538310.13 | [9 empty] | 2017 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2018-02-28 | 0 | 28162.19 | 17564594.13 | 17054446.19 | 510147.94 | 18438370 | 2.767% |  | 361243 | 2015-04-30 | original |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2018-03-30 | 0 | 28162.19 | 17564594.13 | 17082608.38 | 481985.75 | 18438370 | 2.614% |  | 1255716 | 2015-05-30 | original |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2018-04-30 | 0 | 11951.55 | 17564594.13 | 17094559.93 | 470034.2 | 18438370 | 2.549% |  | 1197476 | 2015-06-30 | original |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2018-09-30 | 0 | 2819.12 | 17564594.13 | 17097379.05 | 467215.08 | 18438370 | 2.534% |  | 733802 | 2015-07-30 | original |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2018-11-30 | 0 | 4373.46 | 17564594.13 | 17101752.51 | 462841.62 | 18438370 | 2.51% |  | 2176660 | 2015-08-30 | original |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2018-12-30 | 0 | 47605.57 | 17564594.13 | 17149358.08 | 415236.05 | 18438370 | 2.252% |  | 165696 | 2015-09-30 | original |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-02-28 | 0 | 191530 | 17564594.13 | 17340888.08 | 223706.05 | 18438370 | 1.213% |  | 2449389 | 2015-10-30 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-03-30 | 0 | 174727.57 | 17564594.13 | 17515615.65 | 48978.48 | 18438370 | 0.2656% |  | 0 | 2015-11-30 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-04-30 | 263550.07 | 0 | 17828144.2 | 17515615.65 | 312528.55 | 18438370 | 1.695% |  | 882673 | 2015-12-30 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-05-30 | 0 | 16815 | 17828144.2 | 17532430.65 | 295713.55 | 18438370 | 1.604% |  | 116975 | 2016-01-30 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-08-30 | 0 | 5244.55 | 17828144.2 | 17537675.2 | 290469 | 18438370 | 1.575% |  | 805479 | 2016-02-29 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-10-30 | 0 | 17930 | 17828144.2 | 17555605.2 | 272539 | 18438370 | 1.478% |  | 0 | 2016-03-30 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-11-30 | 0 | 9642.98 | 17828144.2 | 17565248.18 | 262896.02 | 18438370 | 1.426% |  | 1383216 | 2016-04-30 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2019-12-30 | 0 | 3649.67 | 17828144.2 | 17568897.85 | 259246.35 | 18438370 | 1.406% |  | 951643 | 2016-05-30 | original |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2020-01-30 | 0 | 2374.06 | 17828144.2 | 17571271.91 | 256872.29 | 18438370 | 1.393% |  | 0 | 2016-06-30 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2020-02-28 | 0 | 27938.68 | 17828144.2 | 17599210.59 | 228933.61 | 18438370 | 1.242% |  | 1762191 | 2016-07-30 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2020-06-30 | 0 | 52377.98 | 17828144.2 | 17651588.57 | 176555.63 | 18438370 | 0.9575% |  | 0 | 2016-08-30 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2020-08-30 | 0 | 5374.25 | 17828144.2 | 17656962.82 | 171181.38 | 18438370 | 0.9284% |  | 540236 | 2016-09-30 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2020-09-30 | 0 | 50115 | 17828144.2 | 17707077.82 | 121066.38 | 18438370 | 0.6566% |  | 0 | 2016-10-30 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tanks PKG 22 | 2020-10-30 | 780036 | 0 | 18608180.2 | 17707077.82 | 901102.38 | 18438370 | 4.887% |  | 0 | 2016-11-30 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
9 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sodic Club House | 2015-03-30 | 7040000 | 118690 | 7040000 | 118690 | 6921310 | 161208266 | 4.293% |  | 2574334 | 2017-01-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-04-30 | 0 | 128500 | 7040000 | 247190 | 6792810 | 161208266 | 4.214% |  | 0 | 2017-02-28 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-05-30 | 0 | 661534 | 7040000 | 908724 | 6131276 | 161208266 | 3.803% |  | 154991 | 2017-03-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-06-30 | 0 | 1086471 | 7040000 | 1995195 | 5044805 | 161208266 | 3.129% |  | 0 | 2017-04-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-07-30 | 430664 | 1083495 | 7470664 | 3078690 | 4391974 | 161208266 | 2.724% |  | 0 | 2017-05-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-08-30 | 885707 | 558470 | 8356371 | 3637160 | 4719211 | 161208266 | 2.927% |  |  | 2017-05-31 | added cash in 3 |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-09-30 | 0 | 969675 | 8356371 | 4606835 | 3749536 | 161208266 | 2.326% |  | 0 | 2017-06-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-10-30 | 744842 | 1235888 | 9101213 | 5842723 | 3258490 | 161208266 | 2.021% |  | 0 | 2017-07-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-11-30 | 0 | 982250 | 9101213 | 6824973 | 2276240 | 161208266 | 1.412% |  | 0 | 2017-09-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2015-12-30 | 994182 | 1839023 | 10095395 | 8663996 | 1431399 | 161208266 | 0.8879% |  | 0 | 2017-11-30 | original |  |  |  | 2015 | Commercial | Club | SODIC
Sodic Club House | 2016-01-30 | 899985 | 2311600 | 10995380 | 10975596 | 19784 | 161208266 | 0.01227% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-02-28 | 1857883 | 1907743 | 12853263 | 12883339 | -30076 | 161208266 | -0.01866% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-03-30 | 1279246 | 2454209 | 14132509 | 15337548 | -1205039 | 161208266 | -0.7475% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-04-30 | 1306190 | 3031677 | 15438699 | 18369225 | -2930526 | 161208266 | -1.818% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-05-30 | 1486761 | 1609642 | 16925460 | 19978867 | -3053407 | 161208266 | -1.894% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-06-30 | 2355243 | 1191143 | 19280703 | 21170010 | -1889307 | 161208266 | -1.172% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-07-30 | 1154879 | 446976 | 20435582 | 21616986 | -1181404 | 161208266 | -0.7328% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-08-30 | 0 | 1129430 | 20435582 | 22746416 | -2310834 | 161208266 | -1.433% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-09-30 | 1974894 | 1100158 | 22410476 | 23846574 | -1436098 | 161208266 | -0.8908% |  |  | 2019-04-09 | added cash in 3 |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-10-30 | 2811471 | 2236647 | 25221947 | 26083221 | -861274 | 161208266 | -0.5343% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-11-30 | 10093966 | 2751284 | 35315913 | 28834505 | 6481408 | 161208266 | 4.021% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2016-12-30 | 1831900 | 838576 | 37147813 | 29673081 | 7474732 | 161208266 | 4.637% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Club | SODIC
Sodic Club House | 2017-01-30 | 0 | 2393940 | 37147813 | 32067021 | 5080792 | 161208266 | 3.152% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-02-28 | 3047963 | 2559491 | 40195776 | 34626512 | 5569264 | 161208266 | 3.455% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-03-30 | 1525588 | 4738924 | 41721364 | 39365436 | 2355928 | 161208266 | 1.461% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-04-30 | 2166353 | 2785571.99 | 43887717 | 42151007.99 | 1736709.01 | 161208266 | 1.077% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-05-30 | 0 | 3024765.26 | 43887717 | 45175773.25 | -1288056.25 | 161208266 | -0.799% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-06-30 | 2058984 | 4005392.19 | 45946701 | 49181165.44 | -3234464.44 | 161208266 | -2.006% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-07-30 | 4816361 | 5333609.21 | 50763062 | 54514774.65 | -3751712.65 | 161208266 | -2.327% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-08-30 | 6522784 | 10105092.56 | 57285846 | 64619867.21 | -7334021.21 | 161208266 | -4.549% |  |  | 2020-10-15 | added cash in 3 |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-09-30 | 0 | 2004235.92 | 57285846 | 66624103.13 | -9338257.13 | [9 empty] | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-10-30 | 1701896 | 6657399.83 | 58987742 | 73281502.96 | -14293760.96 | 161208266 | -8.867% |  | 0 | 2015-03-31 | original |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-11-30 | 2727407 | 5003420.95 | 61715149 | 78284923.91 | -16569774.91 | 161208266 | -10.28% |  | 0 | 2015-04-30 | original |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2017-12-30 | 0 | 2656148.96 | 61715149 | 80941072.87 | -19225923.87 | 161208266 | -11.93% |  | 0 | 2015-05-31 | original |  |  |  | 2017 | Commercial | Club | SODIC
Sodic Club House | 2018-01-30 | 6226938.12 | 5253101.51 | 67942087.12 | 86194174.38 | -18252087.26 | 161208266 | -11.32% |  | 0 | 2015-06-30 | original |  |  |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-02-28 | 2720869.33 | 2109288.34 | 70662956.45 | 88303462.72 | -17640506.27 | 161208266 | -10.94% |  | 0 | 2015-07-31 | original |  | 42216 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-03-30 | 7171420.81 | 4757625.49 | 77834377.26 | 93061088.21 | -15226710.95 | 161208266 | -9.445% |  | 0 | 2015-08-31 | original |  | 42247 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-04-30 | 3345562.05 | 3698643.72 | 81179939.31 | 96759731.93 | -15579792.62 | 161208266 | -9.664% |  | 0 | 2015-09-30 | original |  | 42277 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-05-30 | 9283697.83 | 5567895.44 | 90463637.14 | 102327627.37 | -11863990.23 | 161208266 | -7.359% |  | 124721 | 2015-10-31 | original |  | 167029 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-06-30 | 2500000 | 3238710.01 | 92963637.14 | 105566337.38 | -12602700.24 | 161208266 | -7.818% |  | 32630 | 2015-11-30 | original |  | 74968 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-07-30 | 1698857.44 | 5182157.23 | 94662494.58 | 110748494.61 | -16086000.03 | 161208266 | -9.978% |  | 217578 | 2015-12-31 | original |  | 259947 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-08-30 | 6840293.08 | 6955137.08 | 101502787.66 | 117703631.69 | -16200844.03 | 161208266 | -10.05% |  | 81525 | 2016-01-31 | original |  | 123925 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-09-30 | 5851323.25 | 4409524.21 | 107354110.91 | 122113155.9 | -14759044.99 | 161208266 | -9.155% |  | 144258 | 2016-02-29 | original |  | 186687 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-10-30 | 5028067.13 | 4745348.72 | 112382178.04 | 126858504.62 | -14476326.58 | 161208266 | -8.98% |  | 173765 | 2016-03-31 | original |  | 216225 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-11-30 | 0 | 3994534.59 | 112382178.04 | 130853039.21 | -18470861.17 | 161208266 | -11.46% |  | 166648 | 2016-04-30 | original |  | 209138 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2018-12-30 | 2014993.45 | 2770057.02 | 114397171.49 | 133623096.23 | -19225924.74 | 161208266 | -11.93% |  | 623524 | 2016-05-31 | original |  | 666045 |  | 2018 | Commercial | Club | SODIC
Sodic Club House | 2019-01-30 | 2061960.6 | 1463200.06 | 116459132.09 | 135086296.29 | -18627164.2 | 161208266 | -11.55% |  | -8211 | 2016-06-30 | original |  | 34340 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-02-28 | 0 | 1257798.19 | 116459132.09 | 136344094.48 | -19884962.39 | 161208266 | -12.33% |  | 0 | 2016-07-31 | original |  | 42582 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-03-30 | 0 | 815360.64 | 116459132.09 | 137159455.12 | -20700323.03 | 161208266 | -12.84% |  | 0 | 2016-08-31 | original |  | 42613 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-04-30 | 184729.32 | 308528.78 | 116643861.41 | 137467983.9 | -20824122.49 | 161208266 | -12.92% |  | 270130 | 2016-09-30 | original |  | 312773 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-05-30 | 0 | 1033679.11 | 116643861.41 | 138501663.01 | -21857801.6 | 161208266 | -13.56% |  | 2680029 | 2016-10-31 | original |  | 2722703 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-06-30 | 0 | 1013827.03 | 116643861.41 | 139515490.04 | -22871628.63 | 161208266 | -14.19% |  | 1271140 | 2016-11-30 | original |  | 1313844 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-07-30 | 503082.9 | 37446.68 | 117146944.31 | 139552936.72 | -22405992.41 | 161208266 | -13.9% |  | 221840 | 2016-12-31 | original |  | 264575 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-08-30 | 3000000 | 113794.73 | 120146944.31 | 139666731.45 | -19519787.14 | 161208266 | -12.11% |  | 2824041.38 | 2017-01-31 | original |  | 2866807.38 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-09-30 | 0 | 92884.94 | 120146944.31 | 139759616.39 | -19612672.08 | 161208266 | -12.17% |  | 3485234.55 | 2017-02-28 | original |  | 3528028.55 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-10-30 | 0 | 72952.1 | 120146944.31 | 139832568.49 | -19685624.18 | 161208266 | -12.21% |  | 3307426.13 | 2017-03-31 | original |  | 3350251.13 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-11-30 | 13881.35 | 540672.67 | 120160825.66 | 140373241.16 | -20212415.5 | 161208266 | -12.54% |  |  |  | cash out both |  | 0 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2019-12-30 | 0 | 129924.07 | 120160825.66 | 140503165.23 | -20342339.57 | 161208266 | -12.62% |  | 3742413.63 | 2017-04-30 | original |  | 3785268.63 |  | 2019 | Commercial | Club | SODIC
Sodic Club House | 2020-01-30 | 6516540.66 | 129100 | 126677366.32 | 140632265.23 | -13954898.91 | 161208266 | -8.656% |  |  |  | cash out both |  | 0 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-02-28 | 0 | 297059.98 | 126677366.32 | 140929325.21 | -14251958.89 | 161208266 | -8.841% |  | 0 | 2017-05-31 | original |  | 42886 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-03-30 | 0 | 446120.81 | 126677366.32 | 141375446.02 | -14698079.7 | 161208266 | -9.117% |  |  |  | cash out both |  | 0 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-05-30 | 0 | 93809.92 | 126677366.32 | 141469255.94 | -14791889.62 | 161208266 | -9.176% |  | 4524968.41 | 2017-06-30 | original |  | 4567884.41 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-06-30 | 0 | 128602.89 | 126677366.32 | 141597858.83 | -14920492.51 | 161208266 | -9.255% |  |  |  | cash out both |  | 0 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-08-30 | 0 | 31157.79 | 126677366.32 | 141629016.62 | -14951650.3 | 161208266 | -9.275% |  | 2035095.79 | 2017-07-31 | original |  | 2078042.79 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-09-30 | 0 | 15085.89 | 126677366.32 | 141644102.51 | -14966736.19 | 161208266 | -9.284% |  |  |  | cash out both |  | 0 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-10-30 | 0 | 228666.92 | 126677366.32 | 141872769.43 | -15195403.11 | 161208266 | -9.426% |  | 0 | 2017-08-31 | original |  | 42978 |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2020-12-30 | 0 | 38783 | 126677366.32 | 141911552.43 | -15234186.11 | 161208266 | -9.45% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Club | SODIC
Sodic Club House | 2021-02-28 | 0 | 58033.38 | 126677366.32 | 141969585.81 | -15292219.49 | 161208266 | -9.486% |  | 695689.48 | 2017-09-30 | original |  |  |  | 2021 | Commercial | Club | SODIC
Sodic Club House | 2021-03-30 | 4028521 | 759855 | 130705887.32 | 142729440.81 | -12023553.49 | 161208266 | -7.458% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Club | SODIC
10 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Uptown Cairo Pkg 53 | 2015-05-30 | 22197572 | 276275 | 22197572 | 276275 | 21921297 | 314789511 | 6.964% |  |  |  | cash out both |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2015-06-30 | 0 | 2218396 | 22197572 | 2494671 | 19702901 | 314789511 | 6.259% |  | 6710848.7 | 2017-11-30 | original |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2015-07-30 | 0 | 2378353 | 22197572 | 4873024 | 17324548 | 314789511 | 5.504% |  |  |  | cash out both |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2015-08-30 | 25331090 | 4001637 | 47528662 | 8874661 | 38654001 | 314789511 | 12.28% |  | 6289400.69 | 2017-12-31 | original |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2015-09-30 | 0 | 6707634 | 47528662 | 15582295 | 31946367 | 314789511 | 10.15% |  |  |  | cash out both |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2015-10-30 | 8388503 | 4386195 | 55917165 | 19968490 | 35948675 | 314789511 | 11.42% |  |  | 2018-01-02 | added cash in 3 |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2015-11-30 | 3640804 | 8552396 | 59557969 | 28520886 | 31037083 | 314789511 | 9.86% |  |  | 2018-01-21 | added cash in 3 |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2015-12-30 | 5140038 | 8467010 | 64698007 | 36987896 | 27710111 | 314789511 | 8.803% |  |  | 2018-01-30 | added cash in 3 |  |  |  | 2015 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-01-30 | 7685729 | 6938553 | 72383736 | 43926449 | 28457287 | 314789511 | 9.04% |  |  |  | cash out both |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-02-28 | 6538575 | 7370547 | 78922311 | 51296996 | 27625315 | 314789511 | 8.776% |  |  | 2018-02-27 | added cash in 3 |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-03-30 | 4182770 | 7281299 | 83105081 | 58578295 | 24526786 | 314789511 | 7.791% |  |  |  | cash out both |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-04-30 | 7197655 | 8362049 | 90302736 | 66940344 | 23362392 | 314789511 | 7.422% |  |  | 2018-03-29 | added cash in 3 |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-05-30 | 6336694 | 10614378 | 96639430 | 77554722 | 19084708 | 314789511 | 6.063% |  |  |  | cash out both |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-06-30 | 4180361 | 6877557 | 100819791 | 84432279 | 16387512 | 314789511 | 5.206% |  |  | 2018-04-12 | added cash in 3 |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-07-30 | 3615040 | 6844122 | 104434831 | 91276401 | 13158430 | 314789511 | 4.18% |  |  |  | cash out both |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-08-30 | 2686256 | 5078227 | 107121087 | 96354628 | 10766459 | 314789511 | 3.42% |  |  | 2018-05-08 | added cash in 3 |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-09-30 | 5342829 | 7908797 | 112463916 | 104263425 | 8200491 | 314789511 | 2.605% |  |  | 2018-05-21 | added cash in 3 |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-10-30 | 4862346 | 8301340 | 117326262 | 112564765 | 4761497 | 314789511 | 1.513% |  |  | 2018-05-31 | added cash in 3 |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-11-30 | 6054470 | 10177650 | 123380732 | 122742415 | 638317 | 314789511 | 0.2028% |  |  |  | cash out both |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2016-12-30 | 5000000 | 13116531 | 128380732 | 135858946 | -7478214 | 314789511 | -2.376% |  |  | 2018-06-13 | added cash in 3 |  |  |  | 2016 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-01-30 | 8210499 | 14864652 | 136591231 | 150723598 | -14132367 | 314789511 | -4.489% |  |  |  | cash out both |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-02-28 | 0 | 9233896 | 136591231 | 159957494 | -23366263 | 314789511 | -7.423% |  |  | 2018-07-09 | added cash in 3 |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-03-30 | 38126817.66 | 8153089 | 174718048.66 | 168110583 | 6607465.66 | 314789511 | 2.099% |  |  |  | cash out both |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-04-30 | 16537496.21 | 16761288.44 | 191255544.87 | 184871871.44 | 6383673.43 | 314789511 | 2.028% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-05-30 | 0 | 10586376.03 | 191255544.87 | 195458247.47 | -4202702.6 | 314789511 | -1.335% |  |  | 2018-08-19 | added cash in 3 |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-06-30 | 21160249.51 | 15262911.35 | 212415794.38 | 210721158.82 | 1694635.56 | 314789511 | 0.5383% |  |  |  | cash out both |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-07-30 | 10750805.82 | 10255046.6 | 223166600.2 | 220976205.42 | 2190394.78 | 314789511 | 0.6958% |  |  | 2018-09-12 | added cash in 3 |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-08-30 | 18136563.93 | 17881064.68 | 241303164.13 | 238857270.1 | 2445894.03 | 314789511 | 0.777% |  |  | 2018-09-23 | added cash in 3 |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-09-30 | 0 | 6242929.05 | 241303164.13 | 245100199.15 | -3797035.02 | 314789511 | -1.206% |  |  |  | cash out both |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-10-30 | 15631210 | 19136867.85 | 256934374.13 | 264237067 | -7302692.87 | 314789511 | -2.32% |  |  | 2018-10-18 | added cash in 3 |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-11-30 | 20089288 | 13781773.34 | 277023662.13 | 278018840.34 | -995178.21 | 314789511 | -0.3161% |  |  | 2018-10-30 | added cash in 3 |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2017-12-30 | 0 | 15174423.67 | 277023662.13 | 293193264.01 | -16169601.88 | 314789511 | -5.137% |  |  |  | cash out both |  |  |  | 2017 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-01-30 | 24624160.03 | 10353800.46 | 301647822.16 | 303547064.47 | -1899242.31 | 314789511 | -0.6033% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-02-28 | 14680971.47 | 4412276.3 | 316328793.63 | 307959340.77 | 8369452.86 | 314789511 | 2.659% |  |  | 2018-12-13 | added cash in 3 |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-03-30 | 10942287.56 | 4019413.99 | 327271081.19 | 311978754.76 | 15292326.43 | 314789511 | 4.858% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-04-30 | 6775827.66 | 4634224.86 | 334046908.85 | 316612979.62 | 17433929.23 | 314789511 | 5.538% |  |  | 2019-01-15 | added cash in 3 |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-05-30 | 7450775.99 | 5096713.67 | 341497684.84 | 321709693.29 | 19787991.55 | 314789511 | 6.286% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-06-30 | 7033824.83 | 2859439.8 | 348531509.67 | 324569133.09 | 23962376.58 | 314789511 | 7.612% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-07-30 | 5048904.72 | 2048823.25 | 353580414.39 | 326617956.34 | 26962458.05 | 314789511 | 8.565% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-08-30 | 2169741.01 | 2616371.06 | 355750155.4 | 329234327.4 | 26515828 | 314789511 | 8.423% |  |  | 2019-04-11 | added cash in 3 |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-09-30 | 2466454.76 | 1299669.71 | 358216610.16 | 330533997.11 | 27682613.05 | 314789511 | 8.794% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-10-30 | 0 | 1150556.4 | 358216610.16 | 331684553.51 | 26532056.65 | 314789511 | 8.429% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-11-30 | 3641079.36 | 4067971.59 | 361857689.52 | 335752525.1 | 26105164.42 | 314789511 | 8.293% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2018-12-30 | 0 | 1113764.04 | 361857689.52 | 336866289.14 | 24991400.38 | 314789511 | 7.939% |  |  | 2019-07-09 | added cash in 3 |  |  |  | 2018 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-01-30 | 2837434.68 | 441258.47 | 364695124.2 | 337307547.61 | 27387576.59 | 314789511 | 8.7% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-02-28 | 0 | 1977550.6 | 364695124.2 | 339285098.21 | 25410025.99 | 314789511 | 8.072% |  |  | 2019-08-25 | added cash in 3 |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-03-30 | 1902092.11 | 716244.11 | 366597216.31 | 340001342.32 | 26595873.99 | 314789511 | 8.449% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-04-30 | 451528 | 442940.14 | 367048744.31 | 340444282.46 | 26604461.85 | 314789511 | 8.452% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-05-30 | 0 | 453790.4 | 367048744.31 | 340898072.86 | 26150671.45 | 314789511 | 8.307% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-06-30 | 943725.79 | 269135.29 | 367992470.1 | 341167208.15 | 26825261.95 | 314789511 | 8.522% |  |  | 2019-11-27 | added cash in 3 |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-07-30 | 0 | 245868.3 | 367992470.1 | 341413076.45 | 26579393.65 | 314789511 | 8.444% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-08-30 | 1435222.17 | 393472.74 | 369427692.27 | 341806549.19 | 27621143.08 | 314789511 | 8.774% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-09-30 | 4496154.45 | 375978.67 | 373923846.72 | 342182527.86 | 31741318.86 | 314789511 | 10.08% |  |  | 2020-01-16 | added 1 |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-10-30 | 0 | 505480.85 | 373923846.72 | 342688008.71 | 31235838.01 | 314789511 | 9.923% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-11-30 | 0 | 218136.99 | 373923846.72 | 342906145.7 | 31017701.02 | 314789511 | 9.853% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2019-12-30 | 0 | 257588.12 | 373923846.72 | 343163733.82 | 30760112.9 | 314789511 | 9.772% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-01-30 | 29830.3 | 511542.8 | 373953677.02 | 343675276.62 | 30278400.4 | 314789511 | 9.619% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-02-28 | 1380970.95 | 252076.81 | 375334647.97 | 343927353.43 | 31407294.54 | 314789511 | 9.977% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-03-30 | 0 | 648900.38 | 375334647.97 | 344576253.81 | 30758394.16 | 314789511 | 9.771% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-04-30 | 1391898.96 | 120394.34 | 376726546.93 | 344696648.15 | 32029898.78 | 314789511 | 10.18% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-05-30 | 0 | 89389.86 | 376726546.93 | 344786038.01 | 31940508.92 | 314789511 | 10.15% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-06-30 | 0 | 1282175.11 | 376726546.93 | 346068213.12 | 30658333.81 | 314789511 | 9.739% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-07-30 | 0 | 85228.53 | 376726546.93 | 346153441.65 | 30573105.28 | 314789511 | 9.712% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-08-30 | 0 | 155882.57 | 376726546.93 | 346309324.22 | 30417222.71 | 314789511 | 9.663% |  |  | 2021-03-22 | added 1 |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-09-30 | 0 | 408741.45 | 376726546.93 | 346718065.67 | 30008481.26 | [9 empty] | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-10-30 | 0 | 47530 | 376726546.93 | 346765595.67 | 29960951.26 | 314789511 | 9.518% |  | 0 | 2015-05-30 | original |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-11-30 | 4834138.97 | 85691 | 381560685.9 | 346851286.67 | 34709399.23 | 314789511 | 11.03% |  | 3375819 | 2015-06-30 | original |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2020-12-30 | 0 | 58479.53 | 381560685.9 | 346909766.2 | 34650919.7 | 314789511 | 11.01% |  | 4871804 | 2015-07-30 | original |  |  |  | 2020 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2021-01-30 | 0 | 55175.2 | 381560685.9 | 346964941.4 | 34595744.5 | 314789511 | 10.99% |  | 6620592 | 2015-08-30 | original |  |  |  | 2021 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2021-02-28 | 0 | 60443 | 381560685.9 | 347025384.4 | 34535301.5 | 314789511 | 10.97% |  | 4530736 | 2015-09-30 | original |  |  |  | 2021 | Residential | Residential | EMAAR
Uptown Cairo Pkg 53 | 2021-03-30 | 0 | 404760.88 | 381560685.9 | 347430145.28 | 34130540.62 | 314789511 | 10.84% |  | 5368329 | 2015-10-30 | original |  |  |  | 2021 | Residential | Residential | EMAAR
11 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Bani Suif Power Plant 1021 | 2015-07-30 | 0 | 147700 | 0 | 147700 | -147700 | 427594086.74 | -0.03454% |  | 10287159 | 2015-12-30 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2015-08-30 | 0 | 334580 | 0 | 482280 | -482280 | 427594086.74 | -0.1128% |  | 6087611 | 2016-01-30 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2015-09-30 | 3540240 | 247460 | 3540240 | 729740 | 2810500 | 427594086.74 | 0.6573% |  | 10052757 | 2016-02-29 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2015-10-30 | 13624138 | 989897 | 17164378 | 1719637 | 15444741 | 427594086.74 | 3.612% |  | 9825883 | 2016-03-30 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2015-11-30 | 6387095 | 5947736 | 23551473 | 7667373 | 15884100 | 427594086.74 | 3.715% |  | 6233880 | 2016-04-30 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2015-12-30 | 43430464 | 16315539 | 66981937 | 23982912 | 42999025 | 427594086.74 | 10.06% |  | 4861241 | 2016-05-30 | original |  |  |  | 2015 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-01-30 | 63199591 | 12117980 | 130181528 | 36100892 | 94080636 | 427594086.74 | 22% |  | 3544720 | 2016-06-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-02-28 | 16149696 | 18985169 | 146331224 | 55086061 | 91245163 | 427594086.74 | 21.34% |  | 7057268 | 2016-07-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-03-30 | 18497443 | 24380775 | 164828667 | 79466836 | 85361831 | 427594086.74 | 19.96% |  | 6452626 | 2016-08-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-04-30 | 25207548 | 23115342 | 190036215 | 102582178 | 87454037 | 427594086.74 | 20.45% |  | 6612101 | 2016-09-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-05-30 | 16979590 | 13864400 | 207015805 | 116446578 | 90569227 | 427594086.74 | 21.18% |  | 0 | 2016-10-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-06-30 | 23636716 | 13116897 | 230652521 | 129563475 | 101089046 | 427594086.74 | 23.64% |  | 9641488 | 2016-11-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-07-30 | 0 | 7784151 | 230652521 | 137347626 | 93304895 | 427594086.74 | 21.82% |  | 8205250 | 2016-12-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-08-30 | 28428128 | 14054325 | 259080649 | 151401951 | 107678698 | 427594086.74 | 25.18% |  | 0 | 2017-01-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-09-30 | 0 | 10804163 | 259080649 | 162206114 | 96874535 | 427594086.74 | 22.66% |  | 5860433 | 2017-02-28 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-10-30 | 14538316 | 10947421 | 273618965 | 173153535 | 100465430 | 427594086.74 | 23.5% |  | 13097397 | 2017-03-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-11-30 | 18459309 | 10580410 | 292078274 | 183733945 | 108344329 | 427594086.74 | 25.34% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2016-12-30 | 20000000 | 8207528 | 312078274 | 191941473 | 120136801 | 427594086.74 | 28.1% |  | 0 | 2017-04-30 | original |  |  |  | 2016 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-01-30 | 3120341 | 11875941 | 315198615 | 203817414 | 111381201 | 427594086.74 | 26.05% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-02-28 | 15647341 | 11376813 | 330845956 | 215194227 | 115651729 | 427594086.74 | 27.05% |  | 15107064 | 2017-05-30 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-03-30 | 32970270.88 | 7121129 | 363816226.88 | 222315356 | 141500870.88 | 427594086.74 | 33.09% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-04-30 | 25382957.25 | 14899321.05 | 389199184.13 | 237214677.05 | 151984507.08 | 427594086.74 | 35.54% |  | 7401541 | 2017-06-30 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-07-30 | 15789713.22 | 6667658.69 | 404988897.35 | 243882335.74 | 161106561.61 | 427594086.74 | 37.68% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-01-30 | 8614798.77 | 7289651.01 | 413603696.12 | 251171986.75 | 162431709.37 | 427594086.74 | 37.99% |  | 16155110 | 2017-07-30 | original |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-02-28 | 13069139.98 | 856732.47 | 426672836.1 | 252028719.22 | 174644116.88 | 427594086.74 | 40.84% |  |  | 2017-07-31 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-06-30 | 3413730.79 | 1681341.06 | 430086566.89 | 253710060.28 | 176376506.61 | 427594086.74 | 41.25% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-09-30 | 1693887.15 | 893435.51 | 431780454.04 | 254603495.79 | 177176958.25 | 427594086.74 | 41.44% |  | 10877624 | 2017-08-30 | original |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2021-01-30 | 8655898.12 | 0 | 440436352.16 | 254603495.79 | 185832856.37 | 427594086.74 | 43.46% |  |  | 2017-08-31 | added cash in 3 |  |  |  | 2021 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-05-30 | 46279788.09 | 6632118.31 | 486716140.25 | 261235614.1 | 225480526.15 | 427594086.74 | 52.73% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-06-30 | 12546063.86 | 7136706.11 | 499262204.11 | 268372320.21 | 230889883.9 | 427594086.74 | 54% |  | 18032647 | 2017-09-30 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-08-30 | 18363274.08 | 7144049.45 | 517625478.19 | 275516369.66 | 242109108.53 | 427594086.74 | 56.62% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-09-30 | 17115970.9 | 2367586.5 | 534741449.09 | 277883956.16 | 256857492.93 | 427594086.74 | 60.07% |  | 18646794 | 2017-10-30 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-10-30 | 27371052 | 6079303.26 | 562112501.09 | 283963259.42 | 278149241.67 | 427594086.74 | 65.05% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-11-30 | 0 | 2426788 | 562112501.09 | 286390047.42 | 275722453.67 | 427594086.74 | 64.48% |  | 11525428 | 2017-11-30 | original |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2017-12-30 | 0 | 5938469.27 | 562112501.09 | 292328516.69 | 269783984.4 | 427594086.74 | 63.09% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-03-30 | 6925479.91 | 3626135.94 | 569037981 | 295954652.63 | 273083328.37 | 427594086.74 | 63.87% |  | 13381664 | 2017-12-30 | original |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-04-30 | 0 | 5248992.36 | 569037981 | 301203644.99 | 267834336.01 | 427594086.74 | 62.64% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-05-30 | 12791498.8 | 3391151.83 | 581829479.8 | 304594796.82 | 277234682.98 | 427594086.74 | 64.84% |  |  | 2018-01-09 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-07-30 | 0 | 982254.01 | 581829479.8 | 305577050.83 | 276252428.97 | 427594086.74 | 64.61% |  |  | 2018-01-11 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-08-30 | 0 | 1608874.04 | 581829479.8 | 307185924.87 | 274643554.93 | 427594086.74 | 64.23% |  |  | 2018-01-30 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-10-30 | 0 | 473618.3 | 581829479.8 | 307659543.17 | 274169936.63 | 427594086.74 | 64.12% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-11-30 | 0 | 493053.43 | 581829479.8 | 308152596.6 | 273676883.2 | 427594086.74 | 64% |  |  | 2018-02-19 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2018-12-30 | 5224000 | 216491.27 | 587053479.8 | 308369087.87 | 278684391.93 | 427594086.74 | 65.17% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-01-30 | 0 | 345622.64 | 587053479.8 | 308714710.51 | 278338769.29 | 427594086.74 | 65.09% |  |  | 2018-03-13 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-02-28 | 0 | 1694295.5 | 587053479.8 | 310409006.01 | 276644473.79 | 427594086.74 | 64.7% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-03-30 | 10152661.36 | 63012.4 | 597206141.16 | 310472018.41 | 286734122.75 | 427594086.74 | 67.06% |  |  | 2018-04-19 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-04-30 | 0 | 212898.37 | 597206141.16 | 310684916.78 | 286521224.38 | 427594086.74 | 67.01% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-05-30 | 0 | 108105.2 | 597206141.16 | 310793021.98 | 286413119.18 | 427594086.74 | 66.98% |  |  | 2018-05-13 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-07-30 | 0 | 7135.32 | 597206141.16 | 310800157.3 | 286405983.86 | 427594086.74 | 66.98% |  |  | 2018-05-27 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-09-30 | 0 | 3939 | 597206141.16 | 310804096.3 | 286402044.86 | 427594086.74 | 66.98% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-10-30 | 0 | 29789.37 | 597206141.16 | 310833885.67 | 286372255.49 | 427594086.74 | 66.97% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-11-30 | 0 | 1528 | 597206141.16 | 310835413.67 | 286370727.49 | 427594086.74 | 66.97% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2019-12-30 | 0 | 88677.31 | 597206141.16 | 310924090.98 | 286282050.18 | 427594086.74 | 66.95% |  |  | 2018-07-09 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2020-01-30 | 0 | 100000 | 597206141.16 | 311024090.98 | 286182050.18 | 427594086.74 | 66.93% |  |  | 2018-07-19 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2020-02-28 | 0 | 5075.05 | 597206141.16 | 311029166.03 | 286176975.13 | 427594086.74 | 66.93% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2020-03-30 | 0 | 14320 | 597206141.16 | 311043486.03 | 286162655.13 | 427594086.74 | 66.92% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2020-04-30 | 0 | 22196.31 | 597206141.16 | 311065682.34 | 286140458.82 | 427594086.74 | 66.92% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2020-08-30 | 0 | 114225 | 597206141.16 | 311179907.34 | 286026233.82 | 427594086.74 | 66.89% |  |  | 2018-09-27 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2020-10-30 | 0 | 149657.94 | 597206141.16 | 311329565.28 | 285876575.88 | 427594086.74 | 66.86% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | Sewedy
Bani Suif Power Plant 1021 | 2020-12-30 | 0 | 92545.2 | 597206141.16 | 311422110.48 | 285784030.68 | 427594086.74 | 66.84% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | Sewedy
12 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
New Giza Phase 02 | 2015-08-30 | 0 | 1235235 | 0 | 1235235 | -1235235 | 155643269.76 | -0.7936% |  |  | 2018-11-29 | added cash in 3 |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 02 | 2015-09-30 | 29637377 | 13446591 | 29637377 | 14681826 | 14955551 | 155643269.76 | 9.609% |  |  |  | cash out both |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 02 | 2015-10-30 | 4586765 | 2616279 | 34224142 | 17298105 | 16926037 | 155643269.76 | 10.87% |  |  |  | cash out both |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 02 | 2015-11-30 | 0 | 5501224 | 34224142 | 22799329 | 11424813 | 155643269.76 | 7.34% |  |  | 2019-01-09 | added cash in 3 |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 02 | 2015-12-30 | 0 | 8141258 | 34224142 | 30940587 | 3283555 | 155643269.76 | 2.11% |  |  | 2019-01-30 | added cash in 3 |  |  |  | 2015 | Commercial | University | New Giza
New Giza Phase 02 | 2016-01-30 | 0 | 5451532 | 34224142 | 36392119 | -2167977 | 155643269.76 | -1.393% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-02-28 | 0 | 3603669 | 34224142 | 39995788 | -5771646 | 155643269.76 | -3.708% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-03-30 | 17563755 | 12545548 | 51787897 | 52541336 | -753439 | 155643269.76 | -0.4841% |  |  | 2019-03-12 | added cash in 3 |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-04-30 | 3905995 | 3148793 | 55693892 | 55690129 | 3763 | 155643269.76 | 0.002418% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-05-30 | 8423296 | 3830635 | 64117188 | 59520764 | 4596424 | 155643269.76 | 2.953% |  |  | 2019-04-09 | added cash in 3 |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-06-30 | 3298717 | 6751529 | 67415905 | 66272293 | 1143612 | 155643269.76 | 0.7348% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-07-30 | 0 | 2378336 | 67415905 | 68650629 | -1234724 | 155643269.76 | -0.7933% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-08-30 | 3461858 | 3473570 | 70877763 | 72124199 | -1246436 | 155643269.76 | -0.8008% |  |  | 2019-06-10 | added cash in 3 |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-09-30 | 5275168 | 5300631 | 76152931 | 77424830 | -1271899 | 155643269.76 | -0.8172% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-10-30 | 5636322 | 4222393 | 81789253 | 81647223 | 142030 | 155643269.76 | 0.09125% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-11-30 | 10000016 | 9401120 | 91789269 | 91048343 | 740926 | 155643269.76 | 0.476% |  |  | 2019-08-07 | added cash in 3 |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2016-12-30 | 4814232 | 2934762 | 96603501 | 93983105 | 2620396 | 155643269.76 | 1.684% |  |  |  | cash out both |  |  |  | 2016 | Commercial | University | New Giza
New Giza Phase 02 | 2017-01-30 | 3576546 | 3139736 | 100180047 | 97122841 | 3057206 | 155643269.76 | 1.964% |  |  | 2019-09-12 | added cash in 3 |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-02-28 | 5550000 | 7547923 | 105730047 | 104670764 | 1059283 | 155643269.76 | 0.6806% |  |  | 2019-09-23 | added cash in 3 |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-03-30 | 22318487 | 5417841 | 128048534 | 110088605 | 17959929 | 155643269.76 | 11.54% |  |  |  | cash out both |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-04-30 | 8320514 | 2321143 | 136369048 | 112409748 | 23959300 | 155643269.76 | 15.39% |  |  |  | cash out both |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-05-30 |  | 8613795.75 | 136369048 | 121023543.75 | 15345504.25 | 155643269.76 | 9.859% |  |  |  | cash out both |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-06-30 | 9270483.71 | 2858240.03 | 145639531.71 | 123881783.78 | 21757747.93 | 155643269.76 | 13.98% |  |  |  | cash out both |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-07-30 | 0 | 4631134.43 | 145639531.71 | 128512918.21 | 17126613.5 | 155643269.76 | 11% |  |  | 2020-01-20 | added cash in 3 |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-08-30 |  | 6912532.53 | 145639531.71 | 135425450.74 | 10214080.97 | 155643269.76 | 6.562% |  |  |  | cash out both |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-09-30 | 0 | 212395 | 145639531.71 | 135637845.74 | 10001685.97 | 155643269.76 | 6.426% |  |  | 2020-02-17 | added cash in 3 |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-10-30 |  | 3530884.09 | 145639531.71 | 139168729.83 | 6470801.88 | 155643269.76 | 4.157% |  |  |  | cash out both |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-11-30 |  | 5558200.51 | 145639531.71 | 144726930.34 | 912601.37 | 155643269.76 | 0.5863% |  |  |  | cash out both |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2017-12-30 | 0 | 805717.79 | 145639531.71 | 145532648.13 | 106883.58 | 155643269.76 | 0.06867% |  |  | 2020-04-29 | added cash in 3 |  |  |  | 2017 | Commercial | University | New Giza
New Giza Phase 02 | 2018-01-30 | 0 | 144319.6 | 145639531.71 | 145676967.73 | -37436.02 | 155643269.76 | -0.02405% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-02-28 | 0 | 22446.66 | 145639531.71 | 145699414.39 | -59882.68 | 155643269.76 | -0.03847% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-03-30 | 0 | 9866.55 | 145639531.71 | 145709280.94 | -69749.23 | 155643269.76 | -0.04481% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-04-30 | 0 | 1329690.05 | 145639531.71 | 147038970.99 | -1399439.28 | 155643269.76 | -0.8991% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-05-30 | 0 | 6689.07 | 145639531.71 | 147045660.06 | -1406128.35 | 155643269.76 | -0.9034% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-06-30 | 3603174 | 192833.35 | 149242705.71 | 147238493.41 | 2004212.3 | 155643269.76 | 1.288% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-07-30 | 4990186 | 450517.66 | 154232891.71 | 147689011.07 | 6543880.64 | 155643269.76 | 4.204% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-08-30 |  | 4041255.48 | 154232891.71 | 151730266.55 | 2502625.16 | 155643269.76 | 1.608% |  |  | 2020-11-11 | added cash in 3 |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-09-30 | 0 | 3372999.77 | 154232891.71 | 155103266.32 | -870374.61 | 155643269.76 | -0.5592% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-10-30 | 0 | 647350.04 | 154232891.71 | 155750616.36 | -1517724.65 | 155643269.76 | -0.9751% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-11-30 | 0 | 1252075 | 154232891.71 | 157002691.36 | -2769799.65 | 155643269.76 | -1.78% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2018-12-30 | 0 | 252299.43 | 154232891.71 | 157254990.79 | -3022099.08 | 155643269.76 | -1.942% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | New Giza
New Giza Phase 02 | 2019-01-30 | 0 | 100591.46 | 154232891.71 | 157355582.25 | -3122690.54 | 155643269.76 | -2.006% | [7 empty] | 2019 | Commercial | University | New Giza
New Giza Phase 02 | 2019-02-28 | 0 | 10289.42 | 154232891.71 | 157365871.67 | -3132979.96 | 155643269.76 | -2.013% |  | 0 | 2015-07-31 | original |  |  |  | 2019 | Commercial | University | New Giza
New Giza Phase 02 | 2019-03-30 | 0 | 139871.89 | 154232891.71 | 157505743.56 | -3272851.85 | 155643269.76 | -2.103% |  | 0 | 2015-08-30 | original |  |  |  | 2019 | Commercial | University | New Giza
New Giza Phase 02 | 2019-04-30 | 0 | 174699.23 | 154232891.71 | 157680442.79 | -3447551.08 | 155643269.76 | -2.215% |  | 4049316 | 2015-09-29 | original |  |  |  | 2019 | Commercial | University | New Giza
New Giza Phase 02 | 2019-12-30 | 0 | 132497.49 | 154232891.71 | 157812940.28 | -3580048.57 | 155643269.76 | -2.3% |  | 7136419 | 2015-10-29 | original |  |  |  | 2019 | Commercial | University | New Giza
New Giza Phase 02 | 2020-01-30 |  | 0 | 154232891.71 | 157812940.28 | -3580048.57 | 155643269.76 | -2.3% |  | 3051785 | 2015-11-28 | original |  |  |  | 2020 | Commercial | University | New Giza
New Giza Phase 02 | 2020-04-30 | 0 | 35314.26 | 154232891.71 | 157848254.54 | -3615362.83 | 155643269.76 | -2.323% |  | 0 | 2015-12-28 | original |  |  |  | 2020 | Commercial | University | New Giza
New Giza Phase 02 | 2020-05-30 | 0 | 40517 | 154232891.71 | 157888771.54 | -3655879.83 | 155643269.76 | -2.349% |  | 2077186 | 2016-01-27 | original |  |  |  | 2020 | Commercial | University | New Giza
New Giza Phase 02 | 2020-06-30 | 0 | 34470.28 | 154232891.71 | 157923241.82 | -3690350.11 | 155643269.76 | -2.371% |  | 0 | 2016-02-26 | original |  |  |  | 2020 | Commercial | University | New Giza
New Giza Phase 02 | 2020-10-30 | 313708 | 21982.92 | 154546599.71 | 157945224.74 | -3398625.03 | 155643269.76 | -2.184% |  | 0 | 2016-03-27 | original |  |  |  | 2020 | Commercial | University | New Giza
New Giza Phase 02 | 2020-11-30 | 0 | 121183.78 | 154546599.71 | 158066408.52 | -3519808.81 | 155643269.76 | -2.261% |  | 0 | 2016-04-26 | original |  |  |  | 2020 | Commercial | University | New Giza
New Giza Phase 02 | 2020-12-30 | 0 | 358005 | 154546599.71 | 158424413.52 | -3877813.81 | 155643269.76 | -2.491% |  | 9692661 | 2016-05-26 | original |  |  |  | 2020 | Commercial | University | New Giza
New Giza Phase 02 | 2021-02-28 | 0 | 104901.44 | 154546599.71 | 158529314.96 | -3982715.25 | 155643269.76 | -2.559% |  | 0 | 2016-06-25 | original |  |  |  | 2021 | Commercial | University | New Giza
13 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
JICA Wind Farm Gabal El Zeet | 2015-11-30 | 0 | 70000 | 0 | 70000 | -70000 | 120483319.9 | -0.0581% |  | 1602218 | 2016-08-24 | original |  |  |  | 2015 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2015-12-30 | 40803000 | 422060 | 40803000 | 492060 | 40310940 | 120483319.9 | 33.46% |  | 0 | 2016-09-23 | original |  |  |  | 2015 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-01-30 | 0 | 1312651 | 40803000 | 1804711 | 38998289 | 120483319.9 | 32.37% |  | 0 | 2016-10-23 | original |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-02-28 | 0 | 3108546 | 40803000 | 4913257 | 35889743 | 120483319.9 | 29.79% |  | 0 | 2016-11-22 | original |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-03-30 | 0 | 5078863 | 40803000 | 9992120 | 30810880 | 120483319.9 | 25.57% |  | 0 | 2016-12-22 | original |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-04-30 | 0 | 3078859 | 40803000 | 13070979 | 27732021 | 120483319.9 | 23.02% |  | 0 | 2017-01-21 | original |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-05-30 | 9237636 | 3423933 | 50040636 | 16494912 | 33545724 | 120483319.9 | 27.84% |  | 0 | 2017-02-20 | original |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-06-30 | 0 | 3375856 | 50040636 | 19870768 | 30169868 | 120483319.9 | 25.04% |  | 0 | 2017-03-22 | original |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-07-30 | 6127667 | 5596265 | 56168303 | 25467033 | 30701270 | 120483319.9 | 25.48% |  |  | 2017-03-30 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-08-30 | 6269675 | 7018075 | 62437978 | 32485108 | 29952870 | 120483319.9 | 24.86% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-09-30 | 0 | 3378966 | 62437978 | 35864074 | 26573904 | 120483319.9 | 22.06% |  |  | 2017-07-31 | added cash in 3 | old substation |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-10-30 | 14744602 | 11229556 | 77182580 | 47093630 | 30088950 | 120483319.9 | 24.97% |  |  | 2018-01-09 | added cash in 3 | old substation |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-11-30 | 9251647 | 4726905 | 86434227 | 51820535 | 34613692 | 120483319.9 | 28.73% |  |  | 2018-02-28 | added cash in 3 | old substation |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2016-12-30 | 0 | 17575959 | 86434227 | 69396494 | 17037733 | 120483319.9 | 14.14% |  |  | 2018-06-10 | added cash in 3 | old substation |  |  | 2016 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-01-30 | 11998906 | 3032449 | 98433133 | 72428943 | 26004190 | 120483319.9 | 21.58% |  |  | 2018-09-18 | added cash in 3 | old substation |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-02-28 | 4563406 | 4528710 | 102996539 | 76957653 | 26038886 | 120483319.9 | 21.61% |  |  | 2021-01-05 | added cash in 3 | old substation |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-03-30 | 2404766.19 | 3267691 | 105401305.19 | 80225344 | 25175961.19 | 120483319.9 | 20.9% |  | 0 | 2017-04-21 | original |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-04-30 | 5202314 | 2502244 | 110603619.19 | 82727588 | 27876031.19 | 120483319.9 | 23.14% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-05-30 | 7408706 | 2859736 | 118012325.19 | 85587324 | 32425001.19 | 120483319.9 | 26.91% |  | 1145904 | 2017-05-21 | original |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-06-30 | 0 | 5659087.77 | 118012325.19 | 91246411.77 | 26765913.42 | 120483319.9 | 22.22% |  |  | 2017-05-31 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-07-30 | 8037955.97 | 4500859.21 | 126050281.16 | 95747270.98 | 30303010.18 | 120483319.9 | 25.15% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-08-30 | 6005029 | 1448593.55 | 132055310.16 | 97195864.53 | 34859445.63 | 120483319.9 | 28.93% |  | 0 | 2017-06-20 | original |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-09-30 | 0 | 219490 | 132055310.16 | 97415354.53 | 34639955.63 | 120483319.9 | 28.75% |  |  | 2017-06-30 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-10-30 | 53837 | 1100949.7 | 132109147.16 | 98516304.23 | 33592842.93 | 120483319.9 | 27.88% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-11-30 | 4132072 | 83442.73 | 136241219.16 | 98599746.96 | 37641472.2 | 120483319.9 | 31.24% |  | 0 | 2017-07-20 | original |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2017-12-30 | 0 | 301052.88 | 136241219.16 | 98900799.84 | 37340419.32 | 120483319.9 | 30.99% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-01-30 | 0 | 179964.77 | 136241219.16 | 99080764.61 | 37160454.55 | 120483319.9 | 30.84% |  | 0 | 2017-08-19 | original |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-02-28 | 0 | 204171.36 | 136241219.16 | 99284935.97 | 36956283.19 | 120483319.9 | 30.67% |  |  | 2017-08-31 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-03-30 | 0 | 271214.9 | 136241219.16 | 99556150.87 | 36685068.29 | 120483319.9 | 30.45% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-04-30 | 75000 | 295681.56 | 136316219.16 | 99851832.43 | 36464386.73 | 120483319.9 | 30.27% |  | 0 | 2017-09-18 | original |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-05-30 | 221249.2 | 207873.45 | 136537468.36 | 100059705.88 | 36477762.48 | 120483319.9 | 30.28% |  |  | 2017-09-30 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-06-30 | 1141675.9 | 184000 | 137679144.26 | 100243705.88 | 37435438.38 | 120483319.9 | 31.07% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-07-30 | 273420 | 198620.53 | 137952564.26 | 100442326.41 | 37510237.85 | 120483319.9 | 31.13% |  | 0 | 2017-10-18 | original |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-08-30 | 0 | 587193.9 | 137952564.26 | 101029520.31 | 36923043.95 | 120483319.9 | 30.65% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-09-30 | 0 | 404069.3 | 137952564.26 | 101433589.61 | 36518974.65 | 120483319.9 | 30.31% |  | 0 | 2017-11-17 | original |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-10-30 | 0 | 180496.45 | 137952564.26 | 101614086.06 | 36338478.2 | 120483319.9 | 30.16% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-11-30 | 2648763.21 | 92905 | 140601327.47 | 101706991.06 | 38894336.41 | 120483319.9 | 32.28% |  | 0 | 2017-12-17 | original |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2018-12-30 | 0 | 158878.66 | 140601327.47 | 101865869.72 | 38735457.75 | 120483319.9 | 32.15% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2019-01-30 | 0 | 150000 | 140601327.47 | 102015869.72 | 38585457.75 | 120483319.9 | 32.03% |  |  | 2018-01-10 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2019-02-28 | 0 | 200000 | 140601327.47 | 102215869.72 | 38385457.75 | 120483319.9 | 31.86% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2019-03-30 | 0 | 138643.58 | 140601327.47 | 102354513.3 | 38246814.17 | 120483319.9 | 31.74% |  |  | 2018-02-18 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2019-05-30 | 0 | 200000 | 140601327.47 | 102554513.3 | 38046814.17 | 120483319.9 | 31.58% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2019-08-30 | 0 | 50000 | 140601327.47 | 102604513.3 | 37996814.17 | 120483319.9 | 31.54% |  |  | 2018-03-07 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2019-10-30 | 0 | 242455.96 | 140601327.47 | 102846969.26 | 37754358.21 | 120483319.9 | 31.34% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | GAMESA
JICA Wind Farm Gabal El Zeet | 2020-08-30 | 0 | 108222 | 140601327.47 | 102955191.26 | 37646136.21 | 120483319.9 | 31.25% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
14 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Mostathmereen Mokatam Substation | 2017-04-30 | 2491720.43 | 651002.5 | 2491720.43 | 651002.5 | 1840717.93 | 135792183 | 1.356% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-05-30 | 5999615 | 9380.96 | 8491335.43 | 660383.46 | 7830951.97 | 135792183 | 5.767% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-06-30 | 0 | 145014.46 | 8491335.43 | 805397.92 | 7685937.51 | 135792183 | 5.66% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-07-30 | 0 | 345164.46 | 8491335.43 | 1150562.38 | 7340773.05 | 135792183 | 5.406% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-08-30 | 17787964.29 | 752110.92 | 26279299.72 | 1902673.3 | 24376626.42 | 135792183 | 17.95% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-09-30 | 876287.52 | 107891.55 | 27155587.24 | 2010564.85 | 25145022.39 | 135792183 | 18.52% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-10-30 | 0 | 220222.77 | 27155587.24 | 2230787.62 | 24924799.62 | 135792183 | 18.36% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-11-30 | 0 | 23360.56 | 27155587.24 | 2254148.18 | 24901439.06 | 135792183 | 18.34% |  |  | 2018-12-17 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2017-12-30 | 0 | 17393.36 | 27155587.24 | 2271541.54 | 24884045.7 | 135792183 | 18.33% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-01-30 | 0 | 319918.08 | 27155587.24 | 2591459.62 | 24564127.62 | 135792183 | 18.09% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-02-28 | 1257447.03 | 6306.93 | 28413034.27 | 2597766.55 | 25815267.72 | 135792183 | 19.01% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-03-30 | 4940012.6 | 109475.02 | 33353046.87 | 2707241.57 | 30645805.3 | 135792183 | 22.57% |  |  | 2019-03-17 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-04-30 | 118079.78 | 525375.37 | 33471126.65 | 3232616.94 | 30238509.71 | 135792183 | 22.27% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-05-30 | 0 | 196312.29 | 33471126.65 | 3428929.23 | 30042197.42 | 135792183 | 22.12% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-06-30 | 989652.76 | 190504.63 | 34460779.41 | 3619433.86 | 30841345.55 | 135792183 | 22.71% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-07-30 | 0 | 665347.46 | 34460779.41 | 4284781.32 | 30175998.09 | 135792183 | 22.22% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-08-30 | 0 | 367807.95 | 34460779.41 | 4652589.27 | 29808190.14 | 135792183 | 21.95% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-09-30 | 0 | 89153.83 | 34460779.41 | 4741743.1 | 29719036.31 | 135792183 | 21.89% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-10-30 | 3874428.61 | 268351.58 | 38335208.02 | 5010094.68 | 33325113.34 | 135792183 | 24.54% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-11-30 | 0 | 146686.95 | 38335208.02 | 5156781.63 | 33178426.39 | 135792183 | 24.43% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2018-12-30 | 3755389.32 | 232123.79 | 42090597.34 | 5388905.42 | 36701691.92 | 135792183 | 27.03% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-01-30 | 5102458.77 | 888 | 47193056.11 | 5389793.42 | 41803262.69 | 135792183 | 30.78% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-03-30 | 0 | 21494.82 | 47193056.11 | 5411288.24 | 41781767.87 | 135792183 | 30.77% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-04-30 | 216757.92 | 140145 | 47409814.03 | 5551433.24 | 41858380.79 | 135792183 | 30.83% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-08-30 | 0 | 736856.6 | 47409814.03 | 6288289.84 | 41121524.19 | 135792183 | 30.28% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-09-30 | 0 | 143348 | 47409814.03 | 6431637.84 | 40978176.19 | 135792183 | 30.18% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-10-30 | 2023992.42 | 15000 | 49433806.45 | 6446637.84 | 42987168.61 | [9 empty] | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-11-30 | 0 | 54191.89 | 49433806.45 | 6500829.73 | 42932976.72 | 135792183 | 31.62% |  | 3666159 | 2015-08-30 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2019-12-30 | 2000000 | 5447349.2 | 51433806.45 | 11948178.93 | 39485627.52 | 135792183 | 29.08% |  | 2947529 | 2015-09-30 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2020-01-30 | 0 | 888 | 51433806.45 | 11949066.93 | 39484739.52 | 135792183 | 29.08% |  | 5298608 | 2015-10-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2020-02-28 | 0 | 49862.7 | 51433806.45 | 11998929.63 | 39434876.82 | 135792183 | 29.04% |  | 8220856 | 2015-11-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2020-05-30 | 0 | 49862.7 | 51433806.45 | 12048792.33 | 39385014.12 | 135792183 | 29% |  | 5801943 | 2015-12-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2020-06-30 | 0 | 260 | 51433806.45 | 12049052.33 | 39384754.12 | 135792183 | 29% |  | 5352562 | 2016-01-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2020-08-30 | 0 | 44123.41 | 51433806.45 | 12093175.74 | 39340630.71 | 135792183 | 28.97% |  | 4388436 | 2016-02-29 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2020-11-30 | 0 | 44123.35 | 51433806.45 | 12137299.09 | 39296507.36 | 135792183 | 28.94% |  | 3420205 | 2016-03-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
El Mostathmereen Mokatam Substation | 2021-03-30 | 0 | 44123.41 | 51433806.45 | 12181422.5 | 39252383.95 | 135792183 | 28.91% |  | 8821905 | 2016-04-30 | original |  |  |  | 2021 | Industrial | Power Plant | EETC
15 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Levana UpTown Pkg 62 | 2016-03-30 | 0 | 37382 | 0 | 37382 | -37382 | 47319156 | -0.079% |  | 2098881 | 2016-06-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-04-30 | 15011610 | 675195 | 15011610 | 712577 | 14299033 | 47319156 | 30.22% |  | 6034533 | 2016-07-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-05-30 | 0 | 532745 | 15011610 | 1245322 | 13766288 | 47319156 | 29.09% |  | 9407244 | 2016-08-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-06-30 | 0 | 229819 | 15011610 | 1475141 | 13536469 | 47319156 | 28.61% |  | 7438667 | 2016-09-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-07-30 | 0 | 1135579 | 15011610 | 2610720 | 12400890 | 47319156 | 26.21% |  | 7251283 | 2016-10-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-08-30 | 0 | 446458 | 15011610 | 3057178 | 11954432 | 47319156 | 25.26% |  | 4715979 | 2016-11-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-09-30 | 0 | 415909 | 15011610 | 3473087 | 11538523 | 47319156 | 24.38% |  | 9189505 | 2016-12-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-10-30 | 0 | 404830 | 15011610 | 3877917 | 11133693 | 47319156 | 23.53% |  | 6589859 | 2017-01-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-11-30 | 0 | 966035 | 15011610 | 4843952 | 10167658 | 47319156 | 21.49% |  | 6232054 | 2017-02-28 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2016-12-30 | 0 | 297394 | 15011610 | 5141346 | 9870264 | 47319156 | 20.86% |  | 7360122 | 2017-03-30 | original |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-01-30 | 0 | 456488 | 15011610 | 5597834 | 9413776 | 47319156 | 19.89% |  |  | 2017-04-01 | added cash in 3 |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-02-28 | 0 | 458750 | 15011610 | 6056584 | 8955026 | 47319156 | 18.92% |  | 7780352 | 2017-04-30 | original |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-03-30 | 12606185.12 | 306806 | 27617795.12 | 6363390 | 21254405.12 | 47319156 | 44.92% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-04-30 | 1751497.73 | 966917.41 | 29369292.85 | 7330307.41 | 22038985.44 | 47319156 | 46.58% |  | 6227576 | 2017-05-30 | original |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-05-30 | 0 | 1308809.05 | 29369292.85 | 8639116.46 | 20730176.39 | 47319156 | 43.81% |  |  | 2017-05-31 | added cash in 3 |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-06-30 | 2464525.6 | 468061.15 | 31833818.45 | 9107177.61 | 22726640.84 | 47319156 | 48.03% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-07-30 | 0 | 1326578.68 | 31833818.45 | 10433756.29 | 21400062.16 | 47319156 | 45.22% |  | 3408230 | 2017-06-30 | original |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-08-30 | 7667416.33 | 2854452.62 | 39501234.78 | 13288208.91 | 26213025.87 | 47319156 | 55.4% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-09-30 | 6884389.63 | 962472.15 | 46385624.41 | 14250681.06 | 32134943.35 | 47319156 | 67.91% |  | 3675454 | 2017-07-30 | original |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-10-30 | 0 | 3525242.3 | 46385624.41 | 17775923.36 | 28609701.05 | 47319156 | 60.46% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-11-30 | 1684908 | 3708118.5 | 48070532.41 | 21484041.86 | 26586490.55 | 47319156 | 56.19% |  | 3533111 | 2017-08-30 | original |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2017-12-30 | 2970871 | 5137853.5 | 51041403.41 | 26621895.36 | 24419508.05 | 47319156 | 51.61% |  |  | 2017-08-31 | added cash in 3 |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-01-30 | 3340231.54 | 3268363.8 | 54381634.95 | 29890259.16 | 24491375.79 | 47319156 | 51.76% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-02-28 | 2207449.91 | 3350598.15 | 56589084.86 | 33240857.31 | 23348227.55 | 47319156 | 49.34% |  | 0 | 2017-09-30 | original |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-03-30 | 1524280.95 | 3454652.16 | 58113365.81 | 36695509.47 | 21417856.34 | 47319156 | 45.26% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-04-30 | 1565019.14 | 1685712.48 | 59678384.95 | 38381221.95 | 21297163 | 47319156 | 45.01% |  | 0 | 2017-10-30 | original |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-05-30 | 2751811.81 | 2696978.7 | 62430196.76 | 41078200.65 | 21351996.11 | 47319156 | 45.12% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-06-30 | 0 | 543492.04 | 62430196.76 | 41621692.69 | 20808504.07 | 47319156 | 43.97% |  | 0 | 2017-11-30 | original |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-07-30 | 0 | 140888.76 | 62430196.76 | 41762581.45 | 20667615.31 | 47319156 | 43.68% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-08-30 | 854854.29 | 291983.76 | 63285051.05 | 42054565.21 | 21230485.84 | 47319156 | 44.87% |  | 0 | 2017-12-30 | original |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-09-30 | 0 | 80626.53 | 63285051.05 | 42135191.74 | 21149859.31 | 47319156 | 44.7% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-10-30 | 2299870.99 | 204712.1 | 65584922.04 | 42339903.84 | 23245018.2 | 47319156 | 49.12% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-11-30 | 0 | 863989.14 | 65584922.04 | 43203892.98 | 22381029.06 | 47319156 | 47.3% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2018-12-30 | 0 | 287870.08 | 65584922.04 | 43491763.06 | 22093158.98 | 47319156 | 46.69% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-01-30 | 1080718.74 | 20590.24 | 66665640.78 | 43512353.3 | 23153287.48 | 47319156 | 48.93% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-02-28 | 504922.64 | 353680.59 | 67170563.42 | 43866033.89 | 23304529.53 | 47319156 | 49.25% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-03-30 | 0 | 339484.21 | 67170563.42 | 44205518.1 | 22965045.32 | 47319156 | 48.53% |  |  | 2018-06-19 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-04-30 | 0 | 85703.63 | 67170563.42 | 44291221.73 | 22879341.69 | 47319156 | 48.35% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-06-30 | 419078.79 | 9327.89 | 67589642.21 | 44300549.62 | 23289092.59 | 47319156 | 49.22% |  |  | 2018-07-15 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-07-30 | 0 | 18248.53 | 67589642.21 | 44318798.15 | 23270844.06 | 47319156 | 49.18% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-08-30 | 0 | 6039 | 67589642.21 | 44324837.15 | 23264805.06 | 47319156 | 49.17% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-09-30 | 0 | 9226.5 | 67589642.21 | 44334063.65 | 23255578.56 | 47319156 | 49.15% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-10-30 | 0 | 18248.53 | 67589642.21 | 44352312.18 | 23237330.03 | 47319156 | 49.11% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-11-30 | 864260.36 | 0 | 68453902.57 | 44352312.18 | 24101590.39 | 47319156 | 50.93% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2019-12-30 | 0 | 9226.5 | 68453902.57 | 44361538.68 | 24092363.89 | 47319156 | 50.91% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2020-01-30 | 0 | 18248.53 | 68453902.57 | 44379787.21 | 24074115.36 | 47319156 | 50.88% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2020-06-30 | 0 | 124706.12 | 68453902.57 | 44504493.33 | 23949409.24 | 47319156 | 50.61% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2020-09-30 | 0 | 273240.66 | 68453902.57 | 44777733.99 | 23676168.58 | 47319156 | 50.04% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2020-10-30 | 0 | 104893.12 | 68453902.57 | 44882627.11 | 23571275.46 | 47319156 | 49.81% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2020-11-30 | 1416810.93 | 0 | 69870713.5 | 44882627.11 | 24988086.39 | 47319156 | 52.81% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Levana UpTown Pkg 62 | 2021-03-30 | 0 | 72815.8 | 69870713.5 | 44955442.91 | 24915270.59 | 47319156 | 52.65% |  |  | 2020-01-28 | added 1 |  |  |  | 2021 | Infrastructure | L&L | EMAAR
16 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Kayan 110 | 2016-05-30 | 0 | 860500 | 0 | 860500 | -860500 | 1335232523 | -0.06445% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2016-06-30 | 55000000 | 210051 | 55000000 | 1070551 | 53929449 | 1335232523 | 4.039% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2016-07-30 | 0 | 5797210 | 55000000 | 6867761 | 48132239 | 1335232523 | 3.605% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2016-08-30 | 0 | 4223578 | 55000000 | 11091339 | 43908661 | 1335232523 | 3.288% |  |  | 2020-10-25 | added 1 |  |  |  | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2016-09-30 | 25000000 | 6918725 | 80000000 | 18010064 | 61989936 | 1335232523 | 4.643% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2016-10-30 | 0 | 5761473 | 80000000 | 23771537 | 56228463 | 1335232523 | 4.211% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2016-11-30 | 0 | 11455502 | 80000000 | 35227039 | 44772961 | 1335232523 | 3.353% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2016-12-30 | 0 | 9154402 | 80000000 | 44381441 | 35618559 | 1335232523 | 2.668% | [7 empty] | 2016 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-01-30 | 0 | 13543795.0973 | 80000000 | 57925236.0973 | 22074763.9027 | 1335232523 | 1.653% |  | 0 | 2015-11-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-02-28 | 0 | 13611600.8712 | 80000000 | 71536836.9685 | 8463163.0315 | 1335232523 | 0.6338% |  | 0 | 2015-12-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-03-30 | 27336675 | 15529227.2705 | 107336675 | 87066064.239 | 20270610.761 | 1335232523 | 1.518% |  | 6596770 | 2016-01-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-04-30 | 100447129.95 | 29122913.4135 | 207783804.95 | 116188977.6525 | 91594827.2975 | 1335232523 | 6.86% |  | 10725650 | 2016-02-29 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-05-30 | 132035229.8 | 26565873.9725 | 339819034.75 | 142754851.625 | 197064183.125 | 1335232523 | 14.76% |  | 5923635 | 2016-03-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-06-30 | 0 | 30790260.477 | 339819034.75 | 173545112.1021 | 166273922.6479 | 1335232523 | 12.45% |  | 5319791 | 2016-04-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-07-30 | 71287503.5 | 31694169.3607 | 411106538.25 | 205239281.4628 | 205867256.7872 | 1335232523 | 15.42% |  | 11503990 | 2016-05-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-08-30 | 120000000 | 45038850.4442 | 531106538.25 | 250278131.907 | 280828406.343 | 1335232523 | 21.03% |  | 8848356 | 2016-06-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-09-30 | 0 | 22513087.5106 | 531106538.25 | 272791219.4175 | 258315318.8325 | 1335232523 | 19.35% |  | 10889299 | 2016-07-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-10-30 | 0 | 38304436.8484 | 531106538.25 | 311095656.2659 | 220010881.9841 | 1335232523 | 16.48% |  | 11732540 | 2016-08-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-11-30 | 10553942 | 27116155.3 | 541660480.25 | 338211811.5659 | 203448668.6841 | 1335232523 | 15.24% |  | 12559619 | 2016-09-30 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2017-12-30 | 0 | 53322217.6998 | 541660480.25 | 391534029.2658 | 150126450.9842 | 1335232523 | 11.24% |  | 9456723 | 2016-10-31 | original |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-01-30 | 0 | 29529095.2562 | 541660480.25 | 421063124.522 | 120597355.728 | 1335232523 | 9.032% |  | 8920594 | 2016-11-30 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-02-28 | 4294503.3 | 25566997.4494 | 545954983.55 | 446630121.9714 | 99324861.5786 | 1335232523 | 7.439% |  | 2983177 | 2016-12-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-03-30 | 53353592.25 | 40678602.6705 | 599308575.8 | 487308724.6419 | 111999851.1581 | 1335232523 | 8.388% |  | 1879134 | 2017-01-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-04-30 | 23793093.25 | 27583099.8539 | 623101669.05 | 514891824.4958 | 108209844.5542 | 1335232523 | 8.104% |  | 7874877 | 2017-02-28 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-05-30 | 11242619.75 | 36941424.8637 | 634344288.8 | 551833249.3595 | 82511039.4405 | 1335232523 | 6.18% |  |  | 2017-03-30 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-06-30 | 56952862.65 | 26486827.6012 | 691297151.45 | 578320076.9607 | 112977074.4893 | 1335232523 | 8.461% |  | 3592384 | 2017-03-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-07-30 | 11062482.8 | 28587062.2646 | 702359634.25 | 606907139.2253 | 95452495.0247 | 1335232523 | 7.149% |  | 323060 | 2017-04-30 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-08-30 | 46576698.55 | 22407143.6839 | 748936332.8 | 629314282.9092 | 119622049.8908 | 1335232523 | 8.959% |  | 0 | 2017-05-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-09-30 | 66272397.35 | 32515419.446 | 815208730.15 | 661829702.3552 | 153379027.7948 | 1335232523 | 11.49% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-10-30 | 0 | 45346210.7527 | 815208730.15 | 707175913.1079 | 108032817.0421 | 1335232523 | 8.091% |  | 0 | 2017-06-30 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-11-30 | 0 | 25574126.9683 | 815208730.15 | 732750040.0762 | 82458690.0738 | 1335232523 | 6.176% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2018-12-30 | 41275143.7 | 27203664.3869 | 856483873.85 | 759953704.4631 | 96530169.3869 | 1335232523 | 7.229% |  | 0 | 2017-07-31 | original |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-01-30 | 53206512.5 | 22504960.0985 | 909690386.35 | 782458664.5616 | 127231721.7884 | 1335232523 | 9.529% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-02-28 | 87421678.5 | 25797723.1232 | 997112064.85 | 808256387.6848 | 188855677.1652 | 1335232523 | 14.14% |  | 0 | 2017-08-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-03-30 | 74379903.95 | 35171209.4686 | 1071491968.8 | 843427597.1534 | 228064371.6466 | 1335232523 | 17.08% |  | 0 | 2017-09-30 | original |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-04-30 | 210011341.75 | 61882786.7199 | 1281503310.55 | 905310383.8733 | 376192926.6767 | 1335232523 | 28.17% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-05-30 | 8928462.45 | 32150324.9149 | 1290431773 | 937460708.7882 | 352971064.2118 | 1335232523 | 26.44% |  | 1210864 | 2017-10-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-06-30 | 0 | 21381290.7118 | 1290431773 | 958841999.5 | 331589773.5 | 1335232523 | 24.83% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-07-30 | 0 | 57032978.96 | 1290431773 | 1015874978.46 | 274556794.54 | 1335232523 | 20.56% |  | 0 | 2017-11-30 | original |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-08-30 | 0 | 24527556.08 | 1290431773 | 1040402534.54 | 250029238.46 | 1335232523 | 18.73% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-09-30 | 0 | 16373062.61 | 1290431773 | 1056775597.15 | 233656175.85 | 1335232523 | 17.5% |  | 0 | 2017-12-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-10-30 | 29468085 | 17863882.64 | 1319899858 | 1074639479.79 | 245260378.21 | 1335232523 | 18.37% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-11-30 | 0 | 37739785.37 | 1319899858 | 1112379265.16 | 207520592.84 | 1335232523 | 15.54% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2019-12-30 | 2086567 | 20045230.27 | 1321986425 | 1132424495.43 | 189561929.57 | 1335232523 | 14.2% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-01-30 | 0 | 36980646.2 | 1321986425 | 1169405141.63 | 152581283.37 | 1335232523 | 11.43% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-02-28 | 0 | 15033181.94 | 1321986425 | 1184438323.57 | 137548101.43 | 1335232523 | 10.3% |  |  | 2018-04-24 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-03-30 | 32946170 | 10926610.62 | 1354932595 | 1195364934.19 | 159567660.81 | 1335232523 | 11.95% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-04-30 | 0 | 6381053.32 | 1354932595 | 1201745987.51 | 153186607.49 | 1335232523 | 11.47% |  |  | 2018-05-08 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-05-30 | 0 | 8951560.13 | 1354932595 | 1210697547.64 | 144235047.36 | 1335232523 | 10.8% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-06-30 | 477952.85 | 7469937.83 | 1355410547.85 | 1218167485.47 | 137243062.38 | 1335232523 | 10.28% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-07-30 | 2650150 | 6612714.38 | 1358060697.85 | 1224780199.85 | 133280498 | 1335232523 | 9.982% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-08-30 | 0 | 4678863.35 | 1358060697.85 | 1229459063.2 | 128601634.65 | 1335232523 | 9.631% |  |  | 2018-07-09 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-09-30 | 22540675 | 6073048.32 | 1380601372.85 | 1235532111.52 | 145069261.33 | 1335232523 | 10.86% |  |  | 2018-07-25 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-10-30 | 0 | 6514406.21 | 1380601372.85 | 1242046517.73 | 138554855.12 | 1335232523 | 10.38% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-11-30 | 0 | 4208756.9 | 1380601372.85 | 1246255274.63 | 134346098.22 | 1335232523 | 10.06% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2020-12-30 | 0 | 3300995.03 | 1380601372.85 | 1249556269.66 | 131045103.19 | 1335232523 | 9.814% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2021-01-30 | 22295055 | 3966606.84 | 1402896427.85 | 1253522876.5 | 149373551.35 | 1335232523 | 11.19% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2021-02-28 | 0 | 2340657.04 | 1402896427.85 | 1255863533.54 | 147032894.31 | 1335232523 | 11.01% |  |  | 2018-11-22 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | Army Forces
Kayan 110 | 2021-03-30 | 0 | 2825278.74 | 1402896427.85 | 1258688812.28 | 144207615.57 | 1335232523 | 10.8% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Army Forces
17 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
18 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Bani Suif Cement | 2016-07-30 | 0 | 164006 | 0 | 164006 | -164006 | 274663700 | -0.05971% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Factory | CDI
Bani Suif Cement | 2016-08-30 | 31008558 | 678639 | 31008558 | 842645 | 30165913 | 274663700 | 10.98% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Factory | CDI
Bani Suif Cement | 2016-09-30 | 0 | 7751031 | 31008558 | 8593676 | 22414882 | 274663700 | 8.161% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Factory | CDI
Bani Suif Cement | 2016-10-30 | 0 | 13725760 | 31008558 | 22319436 | 8689122 | 274663700 | 3.164% |  |  | 2018-02-14 | added cash in 3 |  |  |  | 2016 | Industrial | Factory | CDI
Bani Suif Cement | 2016-11-30 | 2431481 | 19985096 | 33440039 | 42304532 | -8864493 | 274663700 | -3.227% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Factory | CDI
Bani Suif Cement | 2016-12-30 | 11664033 | 12775230 | 45104072 | 55079762 | -9975690 | 274663700 | -3.632% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Factory | CDI
Bani Suif Cement | 2017-01-30 | 30215733 | 9325965 | 75319805 | 64405727 | 10914078 | 274663700 | 3.974% |  |  | 2018-04-12 | added cash in 3 |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-02-28 | 0 | 22437549 | 75319805 | 86843276 | -11523471 | 274663700 | -4.195% |  |  | 2018-04-19 | added cash in 3 |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-03-30 | 23184069 | 23359182 | 98503874 | 110202458 | -11698584 | 274663700 | -4.259% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-04-30 | 16078329 | 15214946 | 114582203 | 125417404 | -10835201 | 274663700 | -3.945% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-05-30 | 36976159 | 23863782 | 151558362 | 149281186 | 2277176 | 274663700 | 0.8291% |  |  | 2018-06-24 | added cash in 3 |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-06-30 | 12546064 | 26492361 | 164104426 | 175773547 | -11669121 | 274663700 | -4.249% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-07-30 | 5224000 | 18368515 | 169328426 | 194142062 | -24813636 | 274663700 | -9.034% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-08-30 | 8112852 | 14863076 | 177441278 | 209005138 | -31563860 | 274663700 | -11.49% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-09-30 | 17115970 | 8220088 | 194557248 | 217225226 | -22667978 | 274663700 | -8.253% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-10-30 | 15460620 | 11297355 | 210017868 | 228522581 | -18504713 | 274663700 | -6.737% |  |  | 2018-10-08 | added cash in 3 |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-11-30 | 7309725 | 11909214 | 217327593 | 240431795 | -23104202 | 274663700 | -8.412% |  |  | 2018-10-16 | added cash in 3 |  |  |  | 2017 | Industrial | Factory | CDI
Bani Suif Cement | 2017-12-30 | 6696657 | 7785865 | 224024250 | 248217660 | -24193410 | 274663700 | -8.808% |  |  | 2018-10-25 | added cash in 3 |  |  |  | 2017 | Industrial | Factory | CDI
19 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
20 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Tamey El Amdid Mansora Power Station | 2016-06-30 | 14475149 | 0 | 14475149 | 0 | 14475149 | 114399640 | 12.65% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-01-30 | 0 | 33682 | 14475149 | 33682 | 14441467 | 114399640 | 12.62% |  |  | 2019-01-09 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-02-28 | 0 | 120088 | 14475149 | 153770 | 14321379 | 114399640 | 12.52% |  |  | 2019-01-17 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-03-30 | 0 | 161095 | 14475149 | 314865 | 14160284 | 114399640 | 12.38% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-04-30 | 0 | 34773 | 14475149 | 349638 | 14125511 | 114399640 | 12.35% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-05-30 | 0 | 81695 | 14475149 | 431333 | 14043816 | 114399640 | 12.28% |  |  | 2019-04-15 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-06-30 | 0 | 100779 | 14475149 | 532112 | 13943037 | 114399640 | 12.19% |  |  | 2019-04-18 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-07-30 | 0 | 93274.61 | 14475149 | 625386.61 | 13849762.39 | 114399640 | 12.11% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-08-30 | 0 | 274220 | 14475149 | 899606.61 | 13575542.39 | 114399640 | 11.87% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-09-30 | 0 | 98332.42 | 14475149 | 997939.03 | 13477209.97 | 114399640 | 11.78% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-10-30 | 0 | 616950.58 | 14475149 | 1614889.61 | 12860259.39 | 114399640 | 11.24% |  |  | 2019-10-09 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-11-30 | 0 | 2538214.09 | 14475149 | 4153103.7 | 10322045.3 | 114399640 | 9.023% |  |  | 2019-10-13 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2017-12-30 | 0 | 5382896.73 | 14475149 | 9536000.43 | 4939148.57 | 114399640 | 4.317% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-01-30 | 0 | 2162233.84 | 14475149 | 11698234.27 | 2776914.73 | 114399640 | 2.427% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-02-28 | 0 | 3362348.64 | 14475149 | 15060582.91 | -585433.91 | 114399640 | -0.5117% |  |  | 2019-12-31 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-03-30 | 5704185.9 | 2473988.66 | 20179334.9 | 17534571.57 | 2644763.33 | 114399640 | 2.312% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-04-30 | 4460637.4 | 9368200.33 | 24639972.3 | 26902771.9 | -2262799.6 | 114399640 | -1.978% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-05-30 | 2844752.9 | 5326188.32 | 27484725.2 | 32228960.22 | -4744235.02 | 114399640 | -4.147% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-06-30 | 2454573.85 | 5838925.13 | 29939299.05 | 38067885.35 | -8128586.3 | 114399640 | -7.105% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-07-30 | 3862350.4 | 5542866.76 | 33801649.45 | 43610752.11 | -9809102.66 | 114399640 | -8.574% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-08-30 | 0 | 2639855.04 | 33801649.45 | 46250607.15 | -12448957.7 | 114399640 | -10.88% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-09-30 | 157932.21 | 3145703.33 | 33959581.66 | 49396310.48 | -15436728.82 | 114399640 | -13.49% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-10-30 | 3204837.55 | 5410418.1 | 37164419.21 | 54806728.58 | -17642309.37 | [9 empty] | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-11-30 | 6303674.55 | 6197456.11 | 43468093.76 | 61004184.69 | -17536090.93 | 114399640 | -15.33% |  | 0 | 2016-03-31 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2018-12-30 | 2397298.02 | 3733641.57 | 45865391.78 | 64737826.26 | -18872434.48 | 114399640 | -16.5% |  | 0 | 2016-04-30 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-01-30 | 16076487.85 | 3936073.56 | 61941879.63 | 68673899.82 | -6732020.19 | 114399640 | -5.885% |  | 0 | 2016-05-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-02-28 | 6776872.1 | 2587393.25 | 68718751.73 | 71261293.07 | -2542541.34 | 114399640 | -2.223% |  | 0 | 2016-06-30 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-03-30 | 572427.4 | 3256717.88 | 69291179.13 | 74518010.95 | -5226831.82 | 114399640 | -4.569% |  | 0 | 2016-07-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-04-30 | 8672103.3 | 2818936.01 | 77963282.43 | 77336946.96 | 626335.47 | 114399640 | 0.5475% |  | 0 | 2016-08-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-05-30 | 3212556.35 | 2782141.63 | 81175838.78 | 80119088.59 | 1056750.19 | 114399640 | 0.9237% |  | 0 | 2016-09-30 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-06-30 | 673869.4 | 1362961.26 | 81849708.18 | 81482049.85 | 367658.33 | 114399640 | 0.3214% |  | 0 | 2016-10-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-07-30 | 0 | 992471.64 | 81849708.18 | 82474521.49 | -624813.31 | 114399640 | -0.5462% |  | 2732328 | 2016-11-30 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-08-30 | 2002680.05 | 2504381.49 | 83852388.23 | 84978902.98 | -1126514.75 | 114399640 | -0.9847% |  | 0 | 2016-12-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-09-30 | 3766551.1 | 712492.1 | 87618939.33 | 85691395.08 | 1927544.25 | 114399640 | 1.685% |  | 0 | 2017-01-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-10-30 | 2304089.55 | 384474.63 | 89923028.88 | 86075869.71 | 3847159.17 | 114399640 | 3.363% |  | 0 | 2017-02-28 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-11-30 | 0 | 400815.96 | 89923028.88 | 86476685.67 | 3446343.21 | 114399640 | 3.013% |  |  | 2017-03-30 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2019-12-30 | 88401.76 | 8203862.87 | 90011430.64 | 94680548.54 | -4669117.9 | 114399640 | -4.081% |  | 1481722 | 2017-03-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-01-30 | 314776.08 | 340616.99 | 90326206.72 | 95021165.53 | -4694958.81 | 114399640 | -4.104% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-02-28 | 9998831.1 | 724431.47 | 100325037.82 | 95745597 | 4579440.82 | 114399640 | 4.003% |  | 2210783 | 2017-04-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-03-30 | 0 | 131775.99 | 100325037.82 | 95877372.99 | 4447664.83 | 114399640 | 3.888% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-04-30 | 0 | 60503.26 | 100325037.82 | 95937876.25 | 4387161.57 | 114399640 | 3.835% |  | 0 | 2017-05-31 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-05-30 | 0 | 72160.25 | 100325037.82 | 96010036.5 | 4315001.32 | 114399640 | 3.772% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-06-30 | 0 | 107753.46 | 100325037.82 | 96117789.96 | 4207247.86 | 114399640 | 3.678% |  | 1036832 | 2017-06-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-07-30 | 71807.3 | 201917.9 | 100396845.12 | 96319707.86 | 4077137.26 | 114399640 | 3.564% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-08-30 | 0 | 45588.61 | 100396845.12 | 96365296.47 | 4031548.65 | 114399640 | 3.524% |  | 5457135 | 2017-07-31 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-09-30 | 143528 | 78180.83 | 100540373.12 | 96443477.3 | 4096895.82 | 114399640 | 3.581% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-10-30 | 0 | 19606.21 | 100540373.12 | 96463083.51 | 4077289.61 | 114399640 | 3.564% |  | 2439085 | 2017-08-31 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-11-30 | 0 | 13480.37 | 100540373.12 | 96476563.88 | 4063809.24 | 114399640 | 3.552% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2020-12-30 | 0 | 23808.25 | 100540373.12 | 96500372.13 | 4040000.99 | 114399640 | 3.531% |  | 3062111 | 2017-09-30 | original |  |  |  | 2020 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2021-01-30 | 0 | 58081.02 | 100540373.12 | 96558453.15 | 3981919.97 | 114399640 | 3.481% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2021-02-28 | 0 | 62535 | 100540373.12 | 96620988.15 | 3919384.97 | 114399640 | 3.426% |  | 4024170 | 2017-10-31 | original |  |  |  | 2021 | Industrial | Power Plant | EETC
Tamey El Amdid Mansora Power Station | 2021-03-30 | 0 | 432315.18 | 100540373.12 | 97053303.33 | 3487069.79 | 114399640 | 3.048% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | EETC
21 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Ismailia Substation 500-220 | 2017-06-30 | 0 | 40613.48 | 0 | 40613.48 | -40613.48 | 109399640 | -0.03712% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2017-07-30 | 0 | 142795 | 0 | 183408.48 | -183408.48 | 109399640 | -0.1676% |  | 3315630 | 2017-12-31 | original |  |  |  | 2017 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2017-08-30 | 0 | 479654.13 | 0 | 663062.61 | -663062.61 | 109399640 | -0.6061% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2017-09-30 | 0 | 748859.02 | 0 | 1411921.63 | -1411921.63 | 109399640 | -1.291% |  |  | 2018-01-02 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2017-10-30 | 0 | 6411169.09 | 0 | 7823090.72 | -7823090.72 | 109399640 | -7.151% |  |  | 2018-01-29 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2017-11-30 | 4159164 | 6675773.47 | 4159164 | 14498864.19 | -10339700.19 | 109399640 | -9.451% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2017-12-30 | 0 | 10913856.55 | 4159164 | 25412720.74 | -21253556.74 | 109399640 | -19.43% |  |  | 2018-02-07 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-01-30 | 3314345.55 | 3740908.13 | 7473509.55 | 29153628.87 | -21680119.32 | 109399640 | -19.82% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-02-28 | 0 | 1664984.35 | 7473509.55 | 30818613.22 | -23345103.67 | 109399640 | -21.34% |  |  | 2018-03-08 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-03-30 | 7628244.44 | 880801.75 | 15101753.99 | 31699414.97 | -16597660.98 | 109399640 | -15.17% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-04-30 | 0 | 786248.12 | 15101753.99 | 32485663.09 | -17383909.1 | 109399640 | -15.89% |  |  | 2018-04-12 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-05-30 | 0 | 803021.13 | 15101753.99 | 33288684.22 | -18186930.23 | 109399640 | -16.62% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-06-30 | 4195153.81 | 1424251.5 | 19296907.8 | 34712935.72 | -15416027.92 | 109399640 | -14.09% |  |  | 2018-05-16 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-07-30 | 0 | 1819574.82 | 19296907.8 | 36532510.54 | -17235602.74 | 109399640 | -15.75% |  |  | 2018-05-27 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-08-30 | 0 | 2211651.52 | 19296907.8 | 38744162.06 | -19447254.26 | 109399640 | -17.78% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-09-30 | 0 | 2432926.04 | 19296907.8 | 41177088.1 | -21880180.3 | 109399640 | -20% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-10-30 | 0 | 3566344.41 | 19296907.8 | 44743432.51 | -25446524.71 | 109399640 | -23.26% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-11-30 | 7250071.15 | 3065805.18 | 26546978.95 | 47809237.69 | -21262258.74 | 109399640 | -19.44% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2018-12-30 | 0 | 3579926.76 | 26546978.95 | 51389164.45 | -24842185.5 | 109399640 | -22.71% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-01-30 | 5137574.8 | 4796272.16 | 31684553.75 | 56185436.61 | -24500882.86 | 109399640 | -22.4% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-02-28 | 12961 | 2376618.42 | 31697514.75 | 58562055.03 | -26864540.28 | 109399640 | -24.56% |  |  | 2018-10-24 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-03-30 | 0 | 3278687.38 | 31697514.75 | 61840742.41 | -30143227.66 | 109399640 | -27.55% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-04-30 | 1044033.95 | 2492659.28 | 32741548.7 | 64333401.69 | -31591852.99 | 109399640 | -28.88% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-05-30 | 5974553.29 | 2545880.7 | 38716101.99 | 66879282.39 | -28163180.4 | 109399640 | -25.74% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-06-30 | 1688213.15 | 1481896.28 | 40404315.14 | 68361178.67 | -27956863.53 | 109399640 | -25.55% |  |  | 2019-01-09 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-07-30 | 4174473.87 | 2079569.59 | 44578789.01 | 70440748.26 | -25861959.25 | 109399640 | -23.64% |  |  | 2019-01-20 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-08-30 | 1266190.73 | 3237678.45 | 45844979.74 | 73678426.71 | -27833446.97 | 109399640 | -25.44% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-09-30 | 5241118.06 | 5319231.27 | 51086097.8 | 78997657.98 | -27911560.18 | 109399640 | -25.51% |  |  | 2019-02-21 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-10-30 | 2856819.25 | 867863.24 | 53942917.05 | 79865521.22 | -25922604.17 | 109399640 | -23.7% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-11-30 | 0 | 1831906.83 | 53942917.05 | 81697428.05 | -27754511 | 109399640 | -25.37% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2019-12-30 | 535189.2 | 3641609.19 | 54478106.25 | 85339037.24 | -30860930.99 | 109399640 | -28.21% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-01-30 | 10904883.26 | 288845.05 | 65382989.51 | 85627882.29 | -20244892.78 | 109399640 | -18.51% |  |  | 2019-06-10 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-02-28 | 0 | 1177692.67 | 65382989.51 | 86805574.96 | -21422585.45 | 109399640 | -19.58% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-03-30 | 1170773.36 | 470499.49 | 66553762.87 | 87276074.45 | -20722311.58 | 109399640 | -18.94% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-04-30 | 0 | 614268.8 | 66553762.87 | 87890343.25 | -21336580.38 | 109399640 | -19.5% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-05-30 | 0 | 366775.42 | 66553762.87 | 88257118.67 | -21703355.8 | 109399640 | -19.84% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-06-30 | 0 | 745395.3 | 66553762.87 | 89002513.97 | -22448751.1 | 109399640 | -20.52% |  |  | 2019-11-25 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-07-30 | 2893529.08 | 341157.31 | 69447291.95 | 89343671.28 | -19896379.33 | 109399640 | -18.19% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-08-30 | 2899097.58 | 250748.68 | 72346389.53 | 89594419.96 | -17248030.43 | 109399640 | -15.77% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-09-30 | 1137638.28 | 332330.69 | 73484027.81 | 89926750.65 | -16442722.84 | 109399640 | -15.03% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-10-30 | 0 | 132372.71 | 73484027.81 | 90059123.36 | -16575095.55 | 109399640 | -15.15% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-11-30 | 0 | 230397.45 | 73484027.81 | 90289520.81 | -16805493 | 109399640 | -15.36% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2020-12-30 | 215412.72 | 10911.29 | 73699440.53 | 90300432.1 | -16600991.57 | 109399640 | -15.17% |  |  | 2020-11-01 | added 1 |  |  |  | 2020 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2021-01-30 | 288528.58 | 25415.8 | 73987969.11 | 90325847.9 | -16337878.79 | 109399640 | -14.93% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2021-02-28 | 5362261.37 | 180197.06 | 79350230.48 | 90506044.96 | -11155814.48 | [9 empty] | 2021 | Industrial | Power Plant | EETC
Ismailia Substation 500-220 | 2021-03-30 | 250941.62 | 121287.64 | 79601172.1 | 90627332.6 | -11026160.5 | 109399640 | -10.08% |  | 4000000 | 2016-05-31 | original |  |  |  | 2021 | Industrial | Power Plant | EETC
22 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Amal Bridge L&L | 2017-05-30 | 1115000 | 18772.05 | 1115000 | 18772.05 | 1096227.95 | 9050320 | 12.11% |  | 5014273 | 2016-07-31 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2017-08-30 | 0 | 21342 | 1115000 | 40114.05 | 1074885.95 | 9050320 | 11.88% |  | 14172854 | 2016-08-31 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2017-09-30 | 0 | 202989.69 | 1115000 | 243103.74 | 871896.26 | 9050320 | 9.634% |  | 8448406 | 2016-09-30 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2017-10-30 | 0 | 3064.03 | 1115000 | 246167.77 | 868832.23 | 9050320 | 9.6% |  | 12758335 | 2016-10-31 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2017-11-30 | 0 | 7821.35 | 1115000 | 253989.12 | 861010.88 | 9050320 | 9.514% |  | 43227106 | 2016-11-30 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2017-12-30 | 0 | 483426.17 | 1115000 | 737415.29 | 377584.71 | 9050320 | 4.172% |  | 12128868 | 2016-12-31 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-01-30 | 0 | 984041.29 | 1115000 | 1721456.58 | -606456.58 | 9050320 | -6.701% |  | 3742582 | 2017-01-31 | original |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-02-28 | 0 | 1208788.34 | 1115000 | 2930244.92 | -1815244.92 | 9050320 | -20.06% |  | 58697488 | 2017-02-28 | original |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-03-30 | 0 | 942303.73 | 1115000 | 3872548.65 | -2757548.65 | 9050320 | -30.47% |  |  | 2017-03-30 | added cash in 3 |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-04-30 | 0 | 883025.97 | 1115000 | 4755574.62 | -3640574.62 | 9050320 | -40.23% |  | 10879402 | 2017-03-31 | original |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-05-30 | 0 | 587759.24 | 1115000 | 5343333.86 | -4228333.86 | 9050320 | -46.72% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-06-30 | 5500870.85 | 407379.19 | 6615870.85 | 5750713.05 | 865157.8 | 9050320 | 9.559% |  | 26153462 | 2017-04-30 | original |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-07-30 | 0 | 1077667.11 | 6615870.85 | 6828380.16 | -212509.31 | 9050320 | -2.348% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-08-30 | 0 | 1166414.18 | 6615870.85 | 7994794.34 | -1378923.49 | 9050320 | -15.24% |  | 24482093 | 2017-05-31 | original |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-09-30 | 0 | 574475.43 | 6615870.85 | 8569269.77 | -1953398.92 | 9050320 | -21.58% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-10-30 | 0 | 2459804.84 | 6615870.85 | 11029074.61 | -4413203.76 | 9050320 | -48.76% |  | 15797320 | 2017-06-30 | original |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-11-30 | 0 | 1743963.1 | 6615870.85 | 12773037.71 | -6157166.86 | 9050320 | -68.03% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2018-12-30 | 0 | 1026384.16 | 6615870.85 | 13799421.87 | -7183551.02 | 9050320 | -79.37% |  | 47310652 | 2017-07-31 | original |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-01-30 | 0 | 1591582.89 | 6615870.85 | 15391004.76 | -8775133.91 | 9050320 | -96.96% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-02-28 | 0 | 1074306.55 | 6615870.85 | 16465311.31 | -9849440.46 | 9050320 | -108.8% |  | 20808430 | 2017-08-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-03-30 | 0 | 974305.4 | 6615870.85 | 17439616.71 | -10823745.86 | 9050320 | -119.6% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-04-30 | 0 | 243500.39 | 6615870.85 | 17683117.1 | -11067246.25 | 9050320 | -122.3% |  | 39607725 | 2017-09-30 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-05-30 | 0 | 411430.91 | 6615870.85 | 18094548.01 | -11478677.16 | 9050320 | -126.8% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-06-30 | 0 | 22932.84 | 6615870.85 | 18117480.85 | -11501610 | 9050320 | -127.1% |  | 45731593 | 2017-10-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-07-30 | 947802.1 | 22747.17 | 7563672.95 | 18140228.02 | -10576555.07 | 9050320 | -116.9% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-08-30 | 309647 | 3600 | 7873319.95 | 18143828.02 | -10270508.07 | 9050320 | -113.5% |  | 37795060 | 2017-11-30 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-10-30 | 0 | 4170.1 | 7873319.95 | 18147998.12 | -10274678.17 | 9050320 | -113.5% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2019-12-30 | 0 | 70945.9 | 7873319.95 | 18218944.02 | -10345624.07 | 9050320 | -114.3% |  | 28053894 | 2017-12-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2020-01-30 | 0 | 570.1 | 7873319.95 | 18219514.12 | -10346194.17 | 9050320 | -114.3% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2020-02-28 | 0 | 40660.8 | 7873319.95 | 18260174.92 | -10386854.97 | 9050320 | -114.8% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2020-09-30 | 0 | 1710.3 | 7873319.95 | 18261885.22 | -10388565.27 | 9050320 | -114.8% |  |  | 2018-02-26 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Amal Bridge L&L | 2020-12-30 | 0 | 79460.31 | 7873319.95 | 18341345.53 | -10468025.58 | 9050320 | -115.7% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
23 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
FIEM Wind Farm Gabal El Zeet | 2016-11-30 | 0 | 0 | 0 | 0 | 0 | 72547889 | 0% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2016-12-30 | 0 | 0 | 0 | 0 | 0 | 72547889 | 0% |  |  | 2018-04-16 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-01-30 | 22186715 | 117409 | 22186715 | 117409 | 22069306 | 72547889 | 30.42% |  |  | 2018-04-24 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-02-28 | 0 | 6035079 | 22186715 | 6152488 | 16034227 | 72547889 | 22.1% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-03-30 | 15487757.03 | 834404 | 37674472.03 | 6986892 | 30687580.03 | 72547889 | 42.3% |  |  | 2018-05-08 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-04-30 | 17656868.72 | 16480030 | 55331340.75 | 23466922 | 31864418.75 | 72547889 | 43.92% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-05-30 | 18028615.55 | 13015953.05 | 73359956.3 | 36482875.05 | 36877081.25 | 72547889 | 50.83% |  |  | 2018-06-18 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-06-30 | 0 | 6869792.42 | 73359956.3 | 43352667.47 | 30007288.83 | 72547889 | 41.36% |  |  | 2018-06-20 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-07-30 | 31255187.94 | 1022983 | 104615144.24 | 44375650.47 | 60239493.77 | 72547889 | 83.03% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-08-30 | 9138162 | 1672756.67 | 113753306.24 | 46048407.14 | 67704899.1 | 72547889 | 93.32% |  |  | 2018-07-19 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-09-30 | 0 | 80911 | 113753306.24 | 46129318.14 | 67623988.1 | 72547889 | 93.21% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-10-30 | 0 | 610714 | 113753306.24 | 46740032.14 | 67013274.1 | 72547889 | 92.37% |  |  | 2018-08-19 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-11-30 | 0 | 239263 | 113753306.24 | 46979295.14 | 66774011.1 | 72547889 | 92.04% |  |  | 2018-08-28 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2017-12-30 | 2309407 | 239095 | 116062713.24 | 47218390.14 | 68844323.1 | 72547889 | 94.9% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-01-30 | 1523916.51 | 171545.41 | 117586629.75 | 47389935.55 | 70196694.2 | 72547889 | 96.76% |  |  | 2018-09-27 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-03-30 | 0 | 117816.12 | 117586629.75 | 47507751.67 | 70078878.08 | 72547889 | 96.6% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-04-30 | 218510 | 326063.6 | 117805139.75 | 47833815.27 | 69971324.48 | 72547889 | 96.45% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-05-30 | 0 | 171248.52 | 117805139.75 | 48005063.79 | 69800075.96 | 72547889 | 96.21% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-06-30 | 0 | 178854.3 | 117805139.75 | 48183918.09 | 69621221.66 | 72547889 | 95.97% |  |  | 2018-12-09 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-07-30 | 0 | 266452 | 117805139.75 | 48450370.09 | 69354769.66 | 72547889 | 95.6% |  |  | 2018-12-17 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-08-30 | 0 | 314398.6 | 117805139.75 | 48764768.69 | 69040371.06 | 72547889 | 95.17% |  |  | 2018-12-25 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-09-30 | 0 | 164390 | 117805139.75 | 48929158.69 | 68875981.06 | 72547889 | 94.94% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-10-30 | 0 | 37921 | 117805139.75 | 48967079.69 | 68838060.06 | 72547889 | 94.89% |  |  | 2019-01-06 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2018-11-30 | 0 | 60300.49 | 117805139.75 | 49027380.18 | 68777759.57 | 72547889 | 94.8% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2019-01-30 | 0 | 7570.77 | 117805139.75 | 49034950.95 | 68770188.8 | 72547889 | 94.79% |  |  | 2019-02-28 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2019-10-30 | 286904.18 | 6339.06 | 118092043.93 | 49041290.01 | 69050753.92 | 72547889 | 95.18% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | GAMESA
FIEM Wind Farm Gabal El Zeet | 2020-08-30 | 0 | 62501.49 | 118092043.93 | 49103791.5 | 68988252.43 | 72547889 | 95.09% |  |  | 2019-03-19 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | GAMESA
24 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
KFW Wind Farm Gabal El Zeet | 2016-10-30 | 7080183 | 0 | 7080183 | 0 | 7080183 | 23038288.54 | 30.73% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2016-11-30 | 0 | 0 | 7080183 | 0 | 7080183 | 23038288.54 | 30.73% |  |  | 2019-04-10 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2016-12-30 | 0 | 0 | 7080183 | 0 | 7080183 | 23038288.54 | 30.73% |  |  | 2019-04-23 | added cash in 3 |  |  |  | 2016 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-01-30 | 0 | 184065 | 7080183 | 184065 | 6896118 | 23038288.54 | 29.93% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-02-28 | 3385150 | 435344 | 10465333 | 619409 | 9845924 | 23038288.54 | 42.74% |  |  | 2019-05-05 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-03-30 | 1989017.66 | 120209 | 12454350.66 | 739618 | 11714732.66 | 23038288.54 | 50.85% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-04-30 | 6134340.01 | 636709 | 18588690.67 | 1376327 | 17212363.67 | 23038288.54 | 74.71% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-05-30 | 10074183.94 | 105887.57 | 28662874.61 | 1482214.57 | 27180660.04 | 23038288.54 | 118% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-06-30 | 0 | 84940 | 28662874.61 | 1567154.57 | 27095720.04 | 23038288.54 | 117.6% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-07-30 | 3973499.69 | 120057 | 32636374.3 | 1687211.57 | 30949162.73 | 23038288.54 | 134.3% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-08-30 | 584820 | 184602 | 33221194.3 | 1871813.57 | 31349380.73 | 23038288.54 | 136.1% |  |  | 2019-10-03 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-09-30 | 1308427.56 | 3000 | 34529621.86 | 1874813.57 | 32654808.29 | 23038288.54 | 141.7% |  |  | 2019-10-16 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-10-30 | 0 | 4165.64 | 34529621.86 | 1878979.21 | 32650642.65 | 23038288.54 | 141.7% |  |  | 2019-10-20 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-11-30 | 137345 | 0 | 34666966.86 | 1878979.21 | 32787987.65 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2017-12-30 | 0 | 2079 | 34666966.86 | 1881058.21 | 32785908.65 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2018-01-30 | 128570.36 | 58180.73 | 34795537.22 | 1939238.94 | 32856298.28 | 23038288.54 | 142.6% |  |  | 2019-12-23 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2018-03-30 | 0 | 29275.96 | 34795537.22 | 1968514.9 | 32827022.32 | 23038288.54 | 142.5% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2018-05-30 | 0 | 10910.29 | 34795537.22 | 1979425.19 | 32816112.03 | 23038288.54 | 142.4% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2018-06-30 | 0 | 2000 | 34795537.22 | 1981425.19 | 32814112.03 | 23038288.54 | 142.4% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2018-09-30 | 0 | 27909.31 | 34795537.22 | 2009334.5 | 32786202.72 | 23038288.54 | 142.3% |  |  | 2020-03-02 | added 1 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2018-12-30 | 0 | 2022.91 | 34795537.22 | 2011357.41 | 32784179.81 | 23038288.54 | 142.3% |  |  | 2020-03-10 | added 1 |  |  |  | 2018 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2019-09-30 | 0 | 2022.91 | 34795537.22 | 2013380.32 | 32782156.9 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2019-12-30 | 0 | 2022.91 | 34795537.22 | 2015403.23 | 32780133.99 | 23038288.54 | 142.3% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | GAMESA
KFW Wind Farm Gabal El Zeet | 2020-08-30 | 0 | 21004.91 | 34795537.22 | 2036408.14 | 32759129.08 | 23038288.54 | 142.2% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
25 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Marassi Tank PKG 107 | 2017-02-28 | 0 | 635038 | 0 | 635038 | -635038 | 54777143 | -1.159% |  |  | 2020-06-25 | added 1 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-03-30 | 6948801 | 924047 | 6948801 | 1559085 | 5389716 | 54777143 | 9.839% |  |  | 2020-06-29 | added cash in 3 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-04-30 | 0 | 4318623.43 | 6948801 | 5877708.43 | 1071092.57 | 54777143 | 1.955% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-05-30 | 10601254 | 3739988.33 | 17550055 | 9617696.76 | 7932358.24 | 54777143 | 14.48% |  |  | 2020-07-16 | added 1 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-06-30 | 4521275 | 3704155.29 | 22071330 | 13321852.05 | 8749477.95 | 54777143 | 15.97% |  |  | 2020-07-19 | added cash in 3 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-07-30 | 4038006 | 3699252.52 | 26109336 | 17021104.57 | 9088231.43 | 54777143 | 16.59% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-08-30 | 4655009 | 4701656.06 | 30764345 | 21722760.63 | 9041584.37 | 54777143 | 16.51% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-09-30 | 574298 | 1618744.35 | 31338643 | 23341504.98 | 7997138.02 | 54777143 | 14.6% |  |  | 2020-09-09 | added 1 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-10-30 | 6664691 | 3352253.07 | 38003334 | 26693758.05 | 11309575.95 | 54777143 | 20.65% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-11-30 | 0 | 1028772.67 | 38003334 | 27722530.72 | 10280803.28 | 54777143 | 18.77% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2017-12-30 | 1418091 | 3760892.22 | 39421425 | 31483422.94 | 7938002.06 | 54777143 | 14.49% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-01-30 | 1656498.37 | 1386471.9 | 41077923.37 | 32869894.84 | 8208028.53 | 54777143 | 14.98% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-02-28 | 2548915.81 | 713801.85 | 43626839.18 | 33583696.69 | 10043142.49 | 54777143 | 18.33% |  |  | 2021-01-06 | added 1 |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-03-30 | 4193998 | 3278167.58 | 47820837.18 | 36861864.27 | 10958972.91 | 54777143 | 20.01% |  |  | 2021-01-24 | added 1 |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-04-30 | 3281572.56 | 277697.88 | 51102409.74 | 37139562.15 | 13962847.59 | 54777143 | 25.49% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-05-30 | 558221.71 | 556513.87 | 51660631.45 | 37696076.02 | 13964555.43 | 54777143 | 25.49% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-06-30 | 1653125.9 | 505439.58 | 53313757.35 | 38201515.6 | 15112241.75 | [9 empty] | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-07-30 | 0 | 605871.85 | 53313757.35 | 38807387.45 | 14506369.9 | 54777143 | 26.48% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-08-30 | 0 | 578798.26 | 53313757.35 | 39386185.71 | 13927571.64 | 54777143 | 25.43% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-09-30 | 0 | 412108.33 | 53313757.35 | 39798294.04 | 13515463.31 | 54777143 | 24.67% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-10-30 | 0 | 161750.86 | 53313757.35 | 39960044.9 | 13353712.45 | 54777143 | 24.38% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-11-30 | 0 | 804028.65 | 53313757.35 | 40764073.55 | 12549683.8 | 54777143 | 22.91% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2018-12-30 | 0 | 167704.23 | 53313757.35 | 40931777.78 | 12381979.57 | 54777143 | 22.6% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-01-30 | 0 | 24348.06 | 53313757.35 | 40956125.84 | 12357631.51 | 54777143 | 22.56% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-02-28 | 0 | 23676.72 | 53313757.35 | 40979802.56 | 12333954.79 | 54777143 | 22.52% |  |  | 2018-05-22 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-03-30 | 894884.44 | 23052.2 | 54208641.79 | 41002854.76 | 13205787.03 | 54777143 | 24.11% |  |  | 2018-05-27 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-05-30 | 0 | 69667.89 | 54208641.79 | 41072522.65 | 13136119.14 | 54777143 | 23.98% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-06-30 | 0 | 16188.48 | 54208641.79 | 41088711.13 | 13119930.66 | 54777143 | 23.95% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-08-30 | 0 | 269048.8 | 54208641.79 | 41357759.93 | 12850881.86 | 54777143 | 23.46% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-09-30 | 0 | 16188.48 | 54208641.79 | 41373948.41 | 12834693.38 | 54777143 | 23.43% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-11-30 | 1341459.14 | 0 | 55550100.93 | 41373948.41 | 14176152.52 | 54777143 | 25.88% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2019-12-30 | 0 | 92637.22 | 55550100.93 | 41466585.63 | 14083515.3 | 54777143 | 25.71% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-01-30 | 0 | 99256 | 55550100.93 | 41565841.63 | 13984259.3 | 54777143 | 25.53% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-02-28 | 0 | 198512 | 55550100.93 | 41764353.63 | 13785747.3 | 54777143 | 25.17% |  |  | 2019-01-27 | added cash in 3 |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-03-30 | 0 | 16188.48 | 55550100.93 | 41780542.11 | 13769558.82 | 54777143 | 25.14% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-04-30 | 0 | 0.57 | 55550100.93 | 41780542.68 | 13769558.25 | 54777143 | 25.14% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-06-30 | 0 | 16188.48 | 55550100.93 | 41796731.16 | 13753369.77 | 54777143 | 25.11% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-09-30 | 0 | 16188.48 | 55550100.93 | 41812919.64 | 13737181.29 | [9 empty] | 2020 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-10-30 | 0 | 16175.03 | 55550100.93 | 41829094.67 | 13721006.26 | 54777143 | 25.05% |  | 0 | 2016-07-31 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Marassi Tank PKG 107 | 2020-12-30 | 0 | 16794.4 | 55550100.93 | 41845889.07 | 13704211.86 | 54777143 | 25.02% |  | 0 | 2016-08-31 | original |  |  |  | 2020 | Infrastructure | Tank | EMAAR
26 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Ben Zayed New Capital Tunnel | 2017-04-30 | 0 | 500000 | 0 | 500000 | -500000 | 343357654.106 | -0.1456% |  | 15479865 | 2016-10-31 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-05-30 | 0 | 1865980.42 | 0 | 2365980.42 | -2365980.42 | 343357654.106 | -0.6891% |  | 19641409 | 2016-11-30 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-06-30 | 0 | 1814913.59 | 0 | 4180894.01 | -4180894.01 | 343357654.106 | -1.218% |  | 19382634 | 2016-12-31 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-07-30 | 0 | 858442.83 | 0 | 5039336.84 | -5039336.84 | 343357654.106 | -1.468% |  | 29411034 | 2017-01-31 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-08-30 | 0 | 1610520 | 0 | 6649856.84 | -6649856.84 | 343357654.106 | -1.937% |  | 20410494 | 2017-02-28 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-09-30 | 0 | 1077570.84 | 0 | 7727427.68 | -7727427.68 | 343357654.106 | -2.251% |  | 30054634 | 2017-03-31 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-10-30 | 0 | 1403301.44 | 0 | 9130729.12 | -9130729.12 | 343357654.106 | -2.659% |  | 17833591 | 2017-04-30 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-11-30 | 0 | 1805648.69 | 0 | 10936377.81 | -10936377.81 | 343357654.106 | -3.185% |  | 15920715 | 2017-05-31 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2017-12-30 | 0 | 1795222.75 | 0 | 12731600.56 | -12731600.56 | 343357654.106 | -3.708% |  | 15670937 | 2017-06-30 | original |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-01-30 | 0 | 6134697.58 | 0 | 18866298.14 | -18866298.14 | 343357654.106 | -5.495% |  | 15715649 | 2017-07-31 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-02-28 | 50197814.75 | 7622729.39 | 50197814.75 | 26489027.53 | 23708787.22 | 343357654.106 | 6.905% |  | 20878242 | 2017-08-31 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-03-30 | 0 | 6855235.08 | 50197814.75 | 33344262.61 | 16853552.14 | 343357654.106 | 4.908% |  | 6421252 | 2017-09-30 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-04-30 | 0 | 2692337.96 | 50197814.75 | 36036600.57 | 14161214.18 | 343357654.106 | 4.124% |  | 8583366 | 2017-10-31 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-05-30 | 0 | 5182825.62 | 50197814.75 | 41219426.19 | 8978388.56 | 343357654.106 | 2.615% |  | 6621785 | 2017-11-30 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-06-30 | 2372381.85 | 5308830.37 | 52570196.6 | 46528256.56 | 6041940.04 | 343357654.106 | 1.76% |  | 6642565 | 2017-12-31 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-07-30 | 0 | 4338476.67 | 52570196.6 | 50866733.23 | 1703463.37 | [9 empty] | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-08-30 | 35368748.3 | 2815491.27 | 87938944.9 | 53682224.5 | 34256720.4 | 343357654.106 | 9.977% |  |  | 2017-06-30 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-09-30 | 0 | 2438882.65 | 87938944.9 | 56121107.15 | 31817837.75 | [9 empty] | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-10-30 | 9882253.6 | 1492701.73 | 97821198.5 | 57613808.88 | 40207389.62 | 343357654.106 | 11.71% |  | 0 | 2016-06-30 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-11-30 | 59397 | 1829195.68 | 97880595.5 | 59443004.56 | 38437590.94 | 343357654.106 | 11.19% |  | 0 | 2017-01-31 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2018-12-30 | 792617 | 1251141.58 | 98673212.5 | 60694146.14 | 37979066.36 | 343357654.106 | 11.06% |  | 0 | 2017-02-28 | original |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-01-30 | 6080870.45 | 975257.31 | 104754082.95 | 61669403.45 | 43084679.5 | 343357654.106 | 12.55% |  | 0 | 2017-03-31 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-02-28 | 0 | 719983.47 | 104754082.95 | 62389386.92 | 42364696.03 | 343357654.106 | 12.34% |  | 0 | 2017-04-30 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-03-30 | 0 | 2102120.71 | 104754082.95 | 64491507.63 | 40262575.32 | 343357654.106 | 11.73% |  | 0 | 2017-05-31 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-04-30 | 0 | 357064.6 | 104754082.95 | 64848572.23 | 39905510.72 | 343357654.106 | 11.62% |  | 0 | 2017-06-30 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-05-30 | 0 | 2084145.44 | 104754082.95 | 66932717.67 | 37821365.28 | 343357654.106 | 11.02% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-06-30 | 0 | 1013297.48 | 104754082.95 | 67946015.15 | 36808067.8 | 343357654.106 | 10.72% |  | 0 | 2017-07-31 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-07-30 | 7946257 | 591707.4 | 112700339.95 | 68537722.55 | 44162617.4 | 343357654.106 | 12.86% |  | 0 | 2017-08-31 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-08-30 | 16321127 | 893913.7 | 129021466.95 | 69431636.25 | 59589830.7 | 343357654.106 | 17.36% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-09-30 | 0 | 502268.86 | 129021466.95 | 69933905.11 | 59087561.84 | 343357654.106 | 17.21% |  | 0 | 2017-09-30 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-10-30 | 0 | 126805.94 | 129021466.95 | 70060711.05 | 58960755.9 | 343357654.106 | 17.17% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-11-30 | 0 | 398134.41 | 129021466.95 | 70458845.46 | 58562621.49 | 343357654.106 | 17.06% |  | 0 | 2017-10-31 | original |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2019-12-30 | 0 | 453907.04 | 129021466.95 | 70912752.5 | 58108714.45 | 343357654.106 | 16.92% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2020-01-30 | 0 | 426566.73 | 129021466.95 | 71339319.23 | 57682147.72 | 343357654.106 | 16.8% |  | 0 | 2017-11-30 | original |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2020-02-28 | 0 | 523798.86 | 129021466.95 | 71863118.09 | 57158348.86 | 343357654.106 | 16.65% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2020-06-30 | 0 | 200 | 129021466.95 | 71863318.09 | 57158148.86 | 343357654.106 | 16.65% |  | 7657332 | 2017-12-31 | original |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2020-08-30 | 0 | 123355.06 | 129021466.95 | 71986673.15 | 57034793.8 | 343357654.106 | 16.61% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2020-10-30 | 0 | 13763.75 | 129021466.95 | 72000436.9 | 57021030.05 | 343357654.106 | 16.61% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Ben Zayed New Capital Tunnel | 2021-01-30 | 0 | 38898 | 129021466.95 | 72039334.9 | 56982132.05 | 343357654.106 | 16.6% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
27 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Ministries Buildings | 2017-03-30 | 0 | 188964 | 0 | 188964 | -188964 | 2740570200 | -0.006895% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-04-30 | 0 | 153905 | 0 | 342869 | -342869 | 2740570200 | -0.01251% |  |  | 2018-04-16 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-05-30 | 0 | 2390294.8 | 0 | 2733163.8 | -2733163.8 | 2740570200 | -0.09973% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-06-30 | 100000000 | 3052300.05 | 100000000 | 5785463.85 | 94214536.15 | 2740570200 | 3.438% |  |  | 2018-05-20 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-07-30 | 60000000 | 11187154.87 | 160000000 | 16972618.72 | 143027381.28 | 2740570200 | 5.219% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-08-30 | 130000000 | 14435246.63 | 290000000 | 31407865.35 | 258592134.65 | 2740570200 | 9.436% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-09-30 | 0 | 12719129.05 | 290000000 | 44126994.4 | 245873005.6 | 2740570200 | 8.972% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-10-30 | 0 | 20012204.42 | 290000000 | 64139198.82 | 225860801.18 | 2740570200 | 8.241% |  |  | 2018-07-31 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-11-30 | 0 | 21424184.86 | 290000000 | 85563383.68 | 204436616.32 | 2740570200 | 7.46% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2017-12-30 | 70000000 | 30596354.65 | 360000000 | 116159738.33 | 243840261.67 | 2740570200 | 8.897% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-01-30 | 80000000 | 50818659.44 | 440000000 | 166978397.77 | 273021602.23 | 2740570200 | 9.962% |  |  | 2018-09-17 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-02-28 | 0 | 12977050.18 | 440000000 | 179955447.95 | 260044552.05 | 2740570200 | 9.489% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-03-30 | 80000000 | 23890488.06 | 520000000 | 203845936.01 | 316154063.99 | 2740570200 | 11.54% |  |  | 2018-10-08 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-04-30 | 0 | 14804232.03 | 520000000 | 218650168.04 | 301349831.96 | 2740570200 | 11% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-05-30 | 0 | 17011513.76 | 520000000 | 235661681.8 | 284338318.2 | 2740570200 | 10.38% |  |  | 2018-11-18 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-06-30 | 80000000 | 34973159.2 | 600000000 | 270634841 | 329365159 | 2740570200 | 12.02% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-07-30 | 0 | 13252281.83 | 600000000 | 283887122.83 | 316112877.17 | 2740570200 | 11.53% |  |  | 2018-12-19 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-08-30 | 0 | 15500737.93 | 600000000 | 299387860.76 | 300612139.24 | 2740570200 | 10.97% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-09-30 | 231258520 | 23488060.07 | 831258520 | 322875920.83 | 508382599.17 | 2740570200 | 18.55% |  |  | 2019-01-09 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-10-30 | 188585057.2 | 31749536.71 | 1019843577.2 | 354625457.54 | 665218119.66 | 2740570200 | 24.27% |  |  | 2019-01-17 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-11-30 | 25450216.8 | 18529572.93 | 1045293794 | 373155030.47 | 672138763.53 | 2740570200 | 24.53% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2018-12-30 | 0 | 27526803.53 | 1045293794 | 400681834 | 644611960 | 2740570200 | 23.52% |  |  | 2019-02-07 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-01-30 | 0 | 16965897.31 | 1045293794 | 417647731.31 | 627646062.69 | 2740570200 | 22.9% |  |  | 2019-02-14 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-02-28 | 0 | 23082154.62 | 1045293794 | 440729885.93 | 604563908.07 | 2740570200 | 22.06% |  |  | 2019-02-27 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-03-30 | 70000000 | 24007674.25 | 1115293794 | 464737560.18 | 650556233.82 | 2740570200 | 23.74% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-04-30 | 100000000 | 55118842.58 | 1215293794 | 519856402.76 | 695437391.24 | 2740570200 | 25.38% |  |  | 2019-03-26 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-05-30 | 0 | 28005761.59 | 1215293794 | 547862164.35 | 667431629.65 | 2740570200 | 24.35% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-06-30 | 100000000 | 31424550.83 | 1315293794 | 579286715.18 | 736007078.82 | 2740570200 | 26.86% |  |  | 2019-04-15 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-07-30 | 0 | 40314984.33 | 1315293794 | 619601699.51 | 695692094.49 | 2740570200 | 25.38% |  |  | 2019-04-18 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-08-30 | 113351826.5 | 42436749 | 1428645620.5 | 662038448.51 | 766607171.99 | 2740570200 | 27.97% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-09-30 | 40825018 | 59274274.09 | 1469470638.5 | 721312722.6 | 748157915.9 | 2740570200 | 27.3% |  |  | 2019-05-30 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-10-30 | 69510198.2 | 89908498.7 | 1538980836.7 | 811221221.3 | 727759615.4 | 2740570200 | 26.56% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-11-30 | 9983894 | 57941965.08 | 1548964730.7 | 869163186.38 | 679801544.32 | 2740570200 | 24.81% |  |  | 2019-06-26 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2019-12-30 | 147552034 | 34708025.77 | 1696516764.7 | 903871212.15 | 792645552.55 | 2740570200 | 28.92% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-01-30 | 2851037 | 138788979.29 | 1699367801.7 | 1042660191.44 | 656707610.26 | 2740570200 | 23.96% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-02-28 | 135241687 | 75615089.69 | 1834609488.7 | 1118275281.13 | 716334207.57 | 2740570200 | 26.14% |  |  | 2019-08-05 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-03-30 | 30008137 | 32230884.5 | 1864617625.7 | 1150506165.63 | 714111460.07 | 2740570200 | 26.06% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-04-30 | 4019485 | 13628063.76 | 1868637110.7 | 1164134229.39 | 704502881.31 | 2740570200 | 25.71% |  |  | 2019-09-11 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-05-30 | 0 | 25563496.08 | 1868637110.7 | 1189697725.47 | 678939385.23 | 2740570200 | 24.77% |  |  | 2019-09-17 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-06-30 | 501405 | 36844843.56 | 1869138515.7 | 1226542569.03 | 642595946.67 | 2740570200 | 23.45% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-07-30 | 128765575 | 49618323.32 | 1997904090.7 | 1276160892.35 | 721743198.35 | 2740570200 | 26.34% |  |  | 2019-10-09 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-08-30 | 28706200 | 23577214.7 | 2026610290.7 | 1299738107.05 | 726872183.65 | 2740570200 | 26.52% |  |  | 2019-10-20 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-09-30 | 23375895 | 30170906.38 | 2049986185.7 | 1329909013.43 | 720077172.27 | 2740570200 | 26.27% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-10-30 | 29401005 | 28627865.5 | 2079387190.7 | 1358536878.93 | 720850311.77 | 2740570200 | 26.3% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-11-30 | 13595000 | 40400805.22 | 2092982190.7 | 1398937684.15 | 694044506.55 | 2740570200 | 25.32% |  |  | 2019-12-30 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2020-12-30 | 196010 | 29467721.14 | 2093178200.7 | 1428405405.29 | 664772795.41 | 2740570200 | 24.26% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2021-01-30 | 2174820 | 28291031.43 | 2095353020.7 | 1456696436.72 | 638656583.98 | 2740570200 | 23.3% |  |  | 2020-01-14 | added 1 |  |  |  | 2021 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2021-02-28 | 2216660 | 29928786.91 | 2097569680.7 | 1486625223.63 | 610944457.07 | 2740570200 | 22.29% |  |  | 2020-01-22 | added 1 |  |  |  | 2021 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2021-03-30 | 0 | 36200188.82 | 2097569680.7 | 1522825412.45 | 574744268.25 | 2740570200 | 20.97% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Army Forces
Ministries Buildings | 2021-04-30 | 30488418 | 0 | 2128058098.7 | 1522825412.45 | 605232686.25 | 2740570200 | 22.08% |  |  | 2020-02-20 | added 1 |  |  |  | 2021 | Commercial | Offices & Mall | Army Forces
28 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Bani Suif Substation | 2016-06-30 | 14475149 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | EETC
Bani Suif Substation | 2016-09-30 | 0 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | EETC
Bani Suif Substation | 2016-10-30 | 0 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | EETC
Bani Suif Substation | 2016-11-30 | 0 | 0 | 14475149 | 0 | 14475149 | 120712211 | 11.99% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | EETC
Bani Suif Substation | 2016-12-30 | 8239 | 0 | 14483388 | 0 | 14483388 | 120712211 | 12% |  |  |  | cash out both |  |  |  | 2016 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-01-30 | 0 | 0 | 14483388 | 0 | 14483388 | 120712211 | 12% |  |  | 2020-07-27 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-02-28 | 0 | 0 | 14483388 | 0 | 14483388 | 120712211 | 12% |  |  | 2020-07-28 | added 1 |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-03-30 | 13416052 | 181527 | 27899440 | 181527 | 27717913 | 120712211 | 22.96% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-04-30 | 0 | 776061.87 | 27899440 | 957588.87 | 26941851.13 | 120712211 | 22.32% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-05-30 | 0 | 894137.28 | 27899440 | 1851726.15 | 26047713.85 | 120712211 | 21.58% |  |  | 2020-09-27 | added 1 |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-06-30 | 1820433.25 | 443041.54 | 29719873.25 | 2294767.69 | 27425105.56 | 120712211 | 22.72% |  |  | 2020-09-28 | added cash in 3 |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-07-30 | 6757365.36 | 5159216.52 | 36477238.61 | 7453984.21 | 29023254.4 | 120712211 | 24.04% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-08-30 | 10250421.81 | 5865969.86 | 46727660.42 | 13319954.07 | 33407706.35 | 120712211 | 27.68% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-09-30 | 0 | 9001036.54 | 46727660.42 | 22320990.61 | 24406669.81 | 120712211 | 20.22% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-10-30 | 0 | 9415712.91 | 46727660.42 | 31736703.52 | 14990956.9 | 120712211 | 12.42% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-11-30 | 11288949 | 9104992.43 | 58016609.42 | 40841695.95 | 17174913.47 | 120712211 | 14.23% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2017-12-30 | 0 | 11639520.45 | 58016609.42 | 52481216.4 | 5535393.02 | 120712211 | 4.586% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-01-30 | 7502554.18 | 7883691.04 | 65519163.6 | 60364907.44 | 5154256.16 | [9 empty] | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-02-28 | 0 | 2659698.9 | 65519163.6 | 63024606.34 | 2494557.26 | 120712211 | 2.067% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-03-30 | 3629094.56 | 8180873 | 69148258.16 | 71205479.34 | -2057221.18 | 120712211 | -1.704% |  | 0 | 2017-06-30 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-04-30 | 9601100.35 | 2979910.09 | 78749358.51 | 74185389.43 | 4563969.08 | 120712211 | 3.781% |  | 0 | 2017-07-31 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-05-30 | 6834280.65 | 6185054.58 | 85583639.16 | 80370444.01 | 5213195.15 | 120712211 | 4.319% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-06-30 | 688493.52 | 6883518.19 | 86272132.68 | 87253962.2 | -981829.52 | 120712211 | -0.8134% |  | 0 | 2017-08-31 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-07-30 | 6707311.59 | 7207254.93 | 92979444.27 | 94461217.13 | -1481772.86 | 120712211 | -1.228% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-08-30 | 0 | 2437833.72 | 92979444.27 | 96899050.85 | -3919606.58 | 120712211 | -3.247% |  | 5586802 | 2017-09-30 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-09-30 | 2058163.65 | 2807962.31 | 95037607.92 | 99707013.16 | -4669405.24 | 120712211 | -3.868% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-10-30 | 14007733.69 | 5600131.77 | 109045341.61 | 105307144.93 | 3738196.68 | 120712211 | 3.097% |  | 4449390 | 2017-10-31 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-11-30 | 1062725.29 | 4325893.11 | 110108066.9 | 109633038.04 | 475028.86 | 120712211 | 0.3935% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2018-12-30 | 3472508.49 | 3208159.53 | 113580575.39 | 112841197.57 | 739377.82 | 120712211 | 0.6125% |  | 5141666 | 2017-11-30 | original |  |  |  | 2018 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-01-30 | 3842790.22 | 3365192.03 | 117423365.61 | 116206389.6 | 1216976.01 | 120712211 | 1.008% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-02-28 | 6486471.09 | 1478476 | 123909836.7 | 117684865.6 | 6224971.1 | 120712211 | 5.157% |  | 5057617 | 2017-12-31 | original |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-03-30 | 0 | 2402265.91 | 123909836.7 | 120087131.51 | 3822705.19 | 120712211 | 3.167% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-04-30 | 1983838.04 | 662565.72 | 125893674.74 | 120749697.23 | 5143977.51 | 120712211 | 4.261% |  |  | 2018-01-30 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-05-30 | 0 | 858657.36 | 125893674.74 | 121608354.59 | 4285320.15 | 120712211 | 3.55% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-06-30 | 0 | 888312.08 | 125893674.74 | 122496666.67 | 3397008.07 | 120712211 | 2.814% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-07-30 | 2049127.88 | 240126.7 | 127942802.62 | 122736793.37 | 5206009.25 | 120712211 | 4.313% |  |  | 2018-03-08 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-08-30 | 168482.17 | 707538.9 | 128111284.79 | 123444332.27 | 4666952.52 | 120712211 | 3.866% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-09-30 | 0 | 561878.05 | 128111284.79 | 124006210.32 | 4105074.47 | 120712211 | 3.401% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-10-30 | 9999405.8 | 238344.2 | 138110690.59 | 124244554.52 | 13866136.07 | 120712211 | 11.49% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-11-30 | 0 | 453268.78 | 138110690.59 | 124697823.3 | 13412867.29 | 120712211 | 11.11% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2019-12-30 | 0 | 9710316.83 | 138110690.59 | 134408140.13 | 3702550.46 | 120712211 | 3.067% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-01-30 | 0 | 36240.98 | 138110690.59 | 134444381.11 | 3666309.48 | 120712211 | 3.037% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-02-28 | 0 | 326290.52 | 138110690.59 | 134770671.63 | 3340018.96 | 120712211 | 2.767% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-03-30 | 0 | 102293.51 | 138110690.59 | 134872965.14 | 3237725.45 | 120712211 | 2.682% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-04-30 | 0 | 41927.7 | 138110690.59 | 134914892.84 | 3195797.75 | 120712211 | 2.647% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-05-30 | 0 | 383708.17 | 138110690.59 | 135298601.01 | 2812089.58 | 120712211 | 2.33% |  |  | 2018-11-25 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-06-30 | 0 | 7000 | 138110690.59 | 135305601.01 | 2805089.58 | 120712211 | 2.324% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-07-30 | 0 | 52642.88 | 138110690.59 | 135358243.89 | 2752446.7 | 120712211 | 2.28% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-09-30 | 776831.06 | 0 | 138887521.65 | 135358243.89 | 3529277.76 | 120712211 | 2.924% |  |  | 2019-01-30 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-10-30 | 0 | 96928.79 | 138887521.65 | 135455172.68 | 3432348.97 | 120712211 | 2.843% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2020-11-30 | 903786.81 | 59325 | 139791308.46 | 135514497.68 | 4276810.78 | 120712211 | 3.543% |  |  | 2019-02-28 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | EETC
Bani Suif Substation | 2021-01-30 | 5765639.32 | 0 | 145556947.78 | 135514497.68 | 10042450.1 | 120712211 | 8.319% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | EETC
Bani Suif Substation | 2021-02-28 | 5688480 | 0 | 151245427.78 | 135514497.68 | 15730930.1 | 120712211 | 13.03% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | EETC
29 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Royal City Mall | 2017-05-30 | 0 | 2186 | 0 | 2186 | -2186 | 527037820 | -0.0004148% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2017-06-30 | 117000000 | 1101909 | 117000000 | 1104095 | 115895905 | 527037820 | 21.99% |  |  | 2019-05-16 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2017-07-30 | 0 | 5095565.56 | 117000000 | 6199660.56 | 110800339.44 | 527037820 | 21.02% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2017-08-30 | 0 | 6770748.48 | 117000000 | 12970409.04 | 104029590.96 | 527037820 | 19.74% |  |  | 2019-06-26 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2017-09-30 | 0 | 4642407.6 | 117000000 | 17612816.64 | 99387183.36 | 527037820 | 18.86% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2017-10-30 | 10470663.6 | 20286400.32 | 127470663.6 | 37899216.96 | 89571446.64 | 527037820 | 17% |  |  | 2019-07-10 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2017-11-30 | 28485670.45 | 11226952.01 | 155956334.05 | 49126168.97 | 106830165.08 | 527037820 | 20.27% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2017-12-30 | 15853484.1 | 24410996.11 | 171809818.15 | 73537165.08 | 98272653.07 | 527037820 | 18.65% |  |  | 2019-08-05 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-01-30 | 10437271.65 | 9437622.55 | 182247089.8 | 82974787.63 | 99272302.17 | 527037820 | 18.84% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-02-28 | 5169557.65 | 9038900.33 | 187416647.45 | 92013687.96 | 95402959.49 | 527037820 | 18.1% |  |  | 2019-09-17 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-03-30 | 0 | 12250207.57 | 187416647.45 | 104263895.53 | 83152751.92 | 527037820 | 15.78% |  |  | 2019-09-25 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-04-30 | 2000000 | 18440458.23 | 189416647.45 | 122704353.76 | 66712293.69 | 527037820 | 12.66% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-05-30 | 12495801.4 | 14258130.74 | 201912448.85 | 136962484.5 | 64949964.35 | 527037820 | 12.32% |  |  | 2019-10-13 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-06-30 | 10703262.4 | 11467950.99 | 212615711.25 | 148430435.49 | 64185275.76 | 527037820 | 12.18% |  |  | 2019-10-20 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-07-30 | 0 | 9559328.95 | 212615711.25 | 157989764.44 | 54625946.81 | 527037820 | 10.36% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-08-30 | 12482990.7 | 7832899.99 | 225098701.95 | 165822664.43 | 59276037.52 | 527037820 | 11.25% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-09-30 | 5786688.5 | 8011052.92 | 230885390.45 | 173833717.35 | 57051673.1 | 527037820 | 10.82% |  |  | 2019-12-09 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-10-30 | 1000000 | 10688187.36 | 231885390.45 | 184521904.71 | 47363485.74 | 527037820 | 8.987% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-11-30 | 13304955 | 13048898.77 | 245190345.45 | 197570803.48 | 47619541.97 | 527037820 | 9.035% |  |  | 2020-01-14 | added 1 |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2018-12-30 | 6339338.45 | 9472756.08 | 251529683.9 | 207043559.56 | 44486124.34 | 527037820 | 8.441% |  |  | 2020-01-22 | added 1 |  |  |  | 2018 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-01-30 | 5980045.3 | 11027066.71 | 257509729.2 | 218070626.27 | 39439102.93 | 527037820 | 7.483% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-02-28 | 6570751.8 | 11015291.19 | 264080481 | 229085917.46 | 34994563.54 | 527037820 | 6.64% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-03-30 | 7847127.4 | 12464172.49 | 271927608.4 | 241550089.95 | 30377518.45 | 527037820 | 5.764% |  |  | 2020-03-10 | added 1 |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-04-30 | 5868379.55 | 7322125.13 | 277795987.95 | 248872215.08 | 28923772.87 | 527037820 | 5.488% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-05-30 | 4501953.5 | 15513586.9 | 282297941.45 | 264385801.98 | 17912139.47 | 527037820 | 3.399% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-06-30 | 14999974.75 | 8246919.25 | 297297916.2 | 272632721.23 | 24665194.97 | 527037820 | 4.68% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-07-30 | 15165365.8 | 11142490.15 | 312463282 | 283775211.38 | 28688070.62 | 527037820 | 5.443% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-08-30 | 0 | 8488199.86 | 312463282 | 292263411.24 | 20199870.76 | 527037820 | 3.833% |  |  | 2020-07-27 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-09-30 | 16824453.7 | 6511826.72 | 329287735.7 | 298775237.96 | 30512497.74 | 527037820 | 5.789% |  |  | 2020-07-28 | added 1 |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-10-30 | 12249488.1 | 28549777.89 | 341537223.8 | 327325015.85 | 14212207.95 | 527037820 | 2.697% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-11-30 | 11510447.8 | 7306520.58 | 353047671.6 | 334631536.43 | 18416135.17 | 527037820 | 3.494% |  |  | 2020-08-06 | added 1 |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2019-12-30 | 14363618.7 | 19807621.99 | 367411290.3 | 354439158.42 | 12972131.88 | 527037820 | 2.461% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-01-30 | 30171330.2 | 20361632.01 | 397582620.5 | 374800790.43 | 22781830.07 | 527037820 | 4.323% |  |  | 2020-09-16 | added 1 |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-02-28 | 0 | 14527230.19 | 397582620.5 | 389328020.62 | 8254599.88 | 527037820 | 1.566% |  |  | 2020-09-17 | added 1 |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-03-30 | 27286845.95 | 12911045.97 | 424869466.45 | 402239066.59 | 22630399.86 | 527037820 | 4.294% |  |  | 2020-09-28 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-04-30 | 6000000 | 5751087.14 | 430869466.45 | 407990153.73 | 22879312.72 | 527037820 | 4.341% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-05-30 | 15000000 | 8838218.19 | 445869466.45 | 416828371.92 | 29041094.53 | 527037820 | 5.51% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-06-30 | 17594453.1 | 8736347.34 | 463463919.55 | 425564719.26 | 37899200.29 | 527037820 | 7.191% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-07-30 | 9818070.05 | 7457993.59 | 473281989.6 | 433022712.85 | 40259276.75 | 527037820 | 7.639% |  |  | 2020-12-07 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-08-30 | 4536519.55 | 6124140.97 | 477818509.15 | 439146853.82 | 38671655.33 | 527037820 | 7.338% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-09-30 | 7099443.8 | 6261350.01 | 484917952.95 | 445408203.83 | 39509749.12 | 527037820 | 7.497% |  |  | 2021-01-20 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-10-30 | 3000000 | 6208903.56 | 487917952.95 | 451617107.39 | 36300845.56 | 527037820 | 6.888% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-11-30 | 5000000 | 2816247.7 | 492917952.95 | 454433355.09 | 38484597.86 | 527037820 | 7.302% |  |  | 2021-02-24 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2020-12-30 | 0 | 3241562.12 | 492917952.95 | 457674917.21 | 35243035.74 | 527037820 | 6.687% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2021-01-30 | 22724194.05 | 5074964.39 | 515642147 | 462749881.6 | 52892265.4 | 527037820 | 10.04% |  |  | 2021-03-28 | added 1 |  |  |  | 2021 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2021-02-28 | 3184508.35 | 4112738.99 | 518826655.35 | 466862620.59 | 51964034.76 | [9 empty] | 2021 | Commercial | Offices & Mall | Al Babtain Group
Royal City Mall | 2021-03-30 | 5930471.55 | 4153763.79 | 524757126.9 | 471016384.38 | 53740742.52 | 527037820 | 10.2% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Al Babtain Group
30 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Shoubra Banha Bridge L&L | 2017-05-30 | 0 | 11960 | 0 | 11960 | -11960 | 3865380 | -0.3094% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2017-08-30 | 0 | 15800 | 0 | 27760 | -27760 | 3865380 | -0.7182% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2017-10-30 | 0 | 34500.83 | 0 | 62260.83 | -62260.83 | 3865380 | -1.611% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2018-01-30 | 500000 | 0 | 500000 | 62260.83 | 437739.17 | 3865380 | 11.32% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2018-03-30 | 0 | 13289.17 | 500000 | 75550 | 424450 | 3865380 | 10.98% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2018-04-30 | 0 | 39641.08 | 500000 | 115191.08 | 384808.92 | 3865380 | 9.955% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2018-08-30 | 0 | 4421 | 500000 | 119612.08 | 380387.92 | 3865380 | 9.841% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2018-10-30 | 0 | 53825 | 500000 | 173437.08 | 326562.92 | 3865380 | 8.448% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2018-11-30 | 0 | 14843.29 | 500000 | 188280.37 | 311719.63 | 3865380 | 8.064% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2019-01-30 | 0 | 1231.71 | 500000 | 189512.08 | 310487.92 | 3865380 | 8.033% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2019-11-30 | 0 | 786.42 | 500000 | 190298.5 | 309701.5 | 3865380 | 8.012% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2019-12-30 | 0 | 627886.26 | 500000 | 818184.76 | -318184.76 | 3865380 | -8.232% |  |  | 2018-06-11 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2020-08-30 | 0 | 769.32 | 500000 | 818954.08 | -318954.08 | 3865380 | -8.252% |  |  | 2018-06-20 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Shoubra Banha Bridge L&L | 2021-02-28 | 0 | 1551.06 | 500000 | 820505.14 | -320505.14 | 3865380 | -8.292% | [8 empty] | Infrastructure | L&L | Army Forces
31 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
SLP Logistic Center PI Park Sewedy Stores | 2017-07-30 | 6400000 | 11130 | 6400000 | 11130 | 6388870 | 98230405 | 6.504% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2017-08-30 | 0 | 453040.8 | 6400000 | 464170.8 | 5935829.2 | 98230405 | 6.043% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2017-09-30 | 0 | 620233.52 | 6400000 | 1084404.32 | 5315595.68 | 98230405 | 5.411% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2017-10-30 | 0 | 3446422.23 | 6400000 | 4530826.55 | 1869173.45 | 98230405 | 1.903% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2017-11-30 | 3779007 | 6342063.03 | 10179007 | 10872889.58 | -693882.58 | 98230405 | -0.7064% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2017-12-30 | 3366014 | 1415697.59 | 13545021 | 12288587.17 | 1256433.83 | 98230405 | 1.279% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-01-30 | 0 | 1301092.92 | 13545021 | 13589680.09 | -44659.09 | 98230405 | -0.04546% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-02-28 | 2572231.81 | 856943.88 | 16117252.81 | 14446623.97 | 1670628.84 | 98230405 | 1.701% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-03-30 | 0 | 893390.97 | 16117252.81 | 15340014.94 | 777237.87 | 98230405 | 0.7912% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-04-30 | 13775600.49 | 2101196.64 | 29892853.3 | 17441211.58 | 12451641.72 | 98230405 | 12.68% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-05-30 | 1898424.4 | 1412628.15 | 31791277.7 | 18853839.73 | 12937437.97 | 98230405 | 13.17% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-06-30 | 2964111.4 | 1977571.86 | 34755389.1 | 20831411.59 | 13923977.51 | 98230405 | 14.17% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-07-30 | 0 | 1683748.12 | 34755389.1 | 22515159.71 | 12240229.39 | 98230405 | 12.46% |  |  | 2019-07-22 | added cash in 3 |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-08-30 | 2470019.34 | 8370557.78 | 37225408.44 | 30885717.49 | 6339690.95 | 98230405 | 6.454% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-09-30 | 945860.23 | 961785.85 | 38171268.67 | 31847503.34 | 6323765.33 | 98230405 | 6.438% |  |  | 2019-08-18 | added cash in 3 |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-10-30 | 1347803.37 | 2844514.14 | 39519072.04 | 34692017.48 | 4827054.56 | 98230405 | 4.914% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-11-30 | 10242595.77 | 6003365.14 | 49761667.81 | 40695382.62 | 9066285.19 | 98230405 | 9.23% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2018-12-30 | 4682361.4 | 11138708.44 | 54444029.21 | 51834091.06 | 2609938.15 | 98230405 | 2.657% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-01-30 | 8406348.9 | 2373644.85 | 62850378.11 | 54207735.91 | 8642642.2 | 98230405 | 8.798% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-02-28 | 7492497.91 | 3175849.25 | 70342876.02 | 57383585.16 | 12959290.86 | 98230405 | 13.19% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-03-30 | 7725490.88 | 8813928.26 | 78068366.9 | 66197513.42 | 11870853.48 | 98230405 | 12.08% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-04-30 | 4619003.9 | 3888202.36 | 82687370.8 | 70085715.78 | 12601655.02 | 98230405 | 12.83% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-05-30 | 4972625.89 | 4182766.77 | 87659996.69 | 74268482.55 | 13391514.14 | [9 empty] | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-06-30 | 0 | 2059167.4 | 87659996.69 | 76327649.95 | 11332346.74 | 98230405 | 11.54% |  | 13973051 | 2016-11-30 | original |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-07-30 | 0 | 302701.88 | 87659996.69 | 76630351.83 | 11029644.86 | 98230405 | 11.23% |  | 1956164 | 2016-12-31 | original |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-08-30 | 0 | 2420645.94 | 87659996.69 | 79050997.77 | 8608998.92 | 98230405 | 8.764% |  | 2299242 | 2017-01-31 | original |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-09-30 | 2944705.9 | 864171.97 | 90604702.59 | 79915169.74 | 10689532.85 | 98230405 | 10.88% |  | 14635357 | 2017-02-28 | original |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-10-30 | 0 | 186123.84 | 90604702.59 | 80101293.58 | 10503409.01 | 98230405 | 10.69% |  |  | 2017-03-30 | added cash in 3 |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-11-30 | 0 | 218624.98 | 90604702.59 | 80319918.56 | 10284784.03 | 98230405 | 10.47% |  | 21475622 | 2017-03-31 | original |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2019-12-30 | 9175126.88 | 8109117.13 | 99779829.47 | 88429035.69 | 11350793.78 | 98230405 | 11.56% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Sewedy
SLP Logistic Center PI Park Sewedy Stores | 2020-01-30 | 0 | 1093583.04 | 99779829.47 | 89522618.73 | 10257210.74 | 98230405 | 10.44% |  | 13232145 | 2017-04-30 | original |  |  |  | 2020 | Industrial | Factory | Sewedy
32 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Mostakbal Bridge L&L | 2019-05-30 | 0 | 132843 | 0 | 132843 | -132843 | 4424558 | -3.002% |  | 0 | 2017-05-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Mostakbal Bridge L&L | 2019-10-30 | 0 | 0 | 0 | 132843 | -132843 | 4424558 | -3.002% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Mostakbal Bridge L&L | 2019-11-30 | 1392527 | 0 | 1392527 | 132843 | 1259684 | 4424558 | 28.47% |  | 0 | 2017-06-30 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Mostakbal Bridge L&L | 2019-12-30 | 0 | 0 | 1392527 | 132843 | 1259684 | 4424558 | 28.47% |  | 0 | 2017-07-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Mostakbal Bridge L&L | 2020-01-30 | 0 | 0 | 1392527 | 132843 | 1259684 | 4424558 | 28.47% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Mostakbal Bridge L&L | 2020-12-30 | 182760 | 0 | 1575287 | 132843 | 1442444 | 4424558 | 32.6% |  | 0 | 2017-08-31 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Mostakbal Bridge L&L | 2021-01-30 | 138370 | 0 | 1713657 | 132843 | 1580814 | 4424558 | 35.73% |  | 0 | 2017-09-30 | original |  |  |  | 2021 | Infrastructure | L&L | Army Forces
33 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Kayan Wall L&L | 2017-11-30 | 0 | 37173.99 | 0 | 37173.99 | -37173.99 | 107782440 | -0.03449% |  | 341821 | 2017-11-30 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2017-12-30 | 0 | 514939.75 | 0 | 552113.74 | -552113.74 | 107782440 | -0.5122% |  | 0 | 2017-12-31 | original |  |  |  | 2017 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-01-30 | 0 | 2461382.69 | 0 | 3013496.43 | -3013496.43 | 107782440 | -2.796% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-02-28 | 0 | 1574495.22 | 0 | 4587991.65 | -4587991.65 | 107782440 | -4.257% |  |  | 2018-01-03 | added cash in 3 |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-03-30 | 0 | 2531407.41 | 0 | 7119399.06 | -7119399.06 | 107782440 | -6.605% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-04-30 | 14751577.1 | 2024242.44 | 14751577.1 | 9143641.5 | 5607935.6 | 107782440 | 5.203% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-05-30 | 3914997 | 1866377.4 | 18666574.1 | 11010018.9 | 7656555.2 | 107782440 | 7.104% |  |  | 2018-04-24 | added cash in 3 |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-06-30 | 8894827.6 | 1515135.58 | 27561401.7 | 12525154.48 | 15036247.22 | 107782440 | 13.95% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-07-30 | 0 | 2321027.15 | 27561401.7 | 14846181.63 | 12715220.07 | 107782440 | 11.8% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-08-30 | 3329140.4 | 1067955.79 | 30890542.1 | 15914137.42 | 14976404.68 | 107782440 | 13.9% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-09-30 | 0 | 2076373.76 | 30890542.1 | 17990511.18 | 12900030.92 | 107782440 | 11.97% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-10-30 | 0 | 2483382.09 | 30890542.1 | 20473893.27 | 10416648.83 | 107782440 | 9.665% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-11-30 | 5426691.7 | 2236063.96 | 36317233.8 | 22709957.23 | 13607276.57 | 107782440 | 12.62% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2018-12-30 | 0 | 2537753.59 | 36317233.8 | 25247710.82 | 11069522.98 | 107782440 | 10.27% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-01-30 | 0 | 3430911.48 | 36317233.8 | 28678622.3 | 7638611.5 | 107782440 | 7.087% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-02-28 | 10570220.8 | 825270.66 | 46887454.6 | 29503892.96 | 17383561.64 | 107782440 | 16.13% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-03-30 | 7568893 | 1087938.8 | 54456347.6 | 30591831.76 | 23864515.84 | 107782440 | 22.14% |  |  | 2019-10-13 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-04-30 | 10000000 | 1098570.43 | 64456347.6 | 31690402.19 | 32765945.41 | 107782440 | 30.4% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-05-30 | 0 | 1034034.08 | 64456347.6 | 32724436.27 | 31731911.33 | [9 empty] | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-06-30 | 1519519.25 | 199688.07 | 65975866.85 | 32924124.34 | 33051742.51 | 107782440 | 30.67% |  | 5689328 | 2016-10-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-07-30 | 0 | 518893.13 | 65975866.85 | 33443017.47 | 32532849.38 | 107782440 | 30.18% |  | 3637915 | 2016-11-30 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-08-30 | 2370680 | 479889.61 | 68346546.85 | 33922907.08 | 34423639.77 | 107782440 | 31.94% |  | 1910183 | 2016-12-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-09-30 | 0 | 150297.07 | 68346546.85 | 34073204.15 | 34273342.7 | 107782440 | 31.8% |  | 2616085 | 2017-01-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-10-30 | 578454 | 327660.04 | 68925000.85 | 34400864.19 | 34524136.66 | 107782440 | 32.03% |  | 7271634 | 2017-02-28 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-11-30 | 0 | 163593.15 | 68925000.85 | 34564457.34 | 34360543.51 | 107782440 | 31.88% |  |  | 2017-03-30 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2019-12-30 | 984167 | 5379412.16 | 69909167.85 | 39943869.5 | 29965298.35 | 107782440 | 27.8% |  | 799962 | 2017-03-31 | original |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-01-30 | 0 | 44469.69 | 69909167.85 | 39988339.19 | 29920828.66 | 107782440 | 27.76% |  |  | 2017-04-01 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-02-28 | 5363480 | 323028.68 | 75272647.85 | 40311367.87 | 34961279.98 | 107782440 | 32.44% |  | 486002 | 2017-04-30 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-03-30 | 364497 | 49328.47 | 75637144.85 | 40360696.34 | 35276448.51 | 107782440 | 32.73% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-04-30 | 0 | 57581.21 | 75637144.85 | 40418277.55 | 35218867.3 | 107782440 | 32.68% |  | 0 | 2017-05-31 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-05-30 | 0 | 104272.98 | 75637144.85 | 40522550.53 | 35114594.32 | 107782440 | 32.58% |  | 436653 | 2017-06-30 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-06-30 | 0 | 61758.48 | 75637144.85 | 40584309.01 | 35052835.84 | 107782440 | 32.52% |  | 0 | 2017-07-31 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-07-30 | 499950 | 149830.76 | 76137094.85 | 40734139.77 | 35402955.08 | 107782440 | 32.85% |  | 0 | 2017-08-31 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-08-30 | 0 | 71457.3 | 76137094.85 | 40805597.07 | 35331497.78 | 107782440 | 32.78% |  | 156311 | 2017-09-30 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-09-30 | 2801245 | 55634.66 | 78938339.85 | 40861231.73 | 38077108.12 | 107782440 | 35.33% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-10-30 | 0 | 71328.78 | 78938339.85 | 40932560.51 | 38005779.34 | 107782440 | 35.26% |  | 0 | 2017-11-30 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-11-30 | 0 | 65033.78 | 78938339.85 | 40997594.29 | 37940745.56 | 107782440 | 35.2% |  | 0 | 2017-12-31 | original |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2020-12-30 | 0 | 79253.78 | 78938339.85 | 41076848.07 | 37861491.78 | 107782440 | 35.13% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2021-01-30 | 0 | 740 | 78938339.85 | 41077588.07 | 37860751.78 | 107782440 | 35.13% |  |  | 2018-01-23 | added cash in 3 |  |  |  | 2021 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2021-02-28 | 0 | 41244.98 | 78938339.85 | 41118833.05 | 37819506.8 | 107782440 | 35.09% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
Kayan Wall L&L | 2021-03-30 | 0 | 18566.64 | 78938339.85 | 41137399.69 | 37800940.16 | 107782440 | 35.07% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
34 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Elco Suez Steel Rolling Mill Plant 3 | 2017-06-30 | 0 | 7364.72 | 0 | 7364.72 | -7364.72 | 417390514 | -0.001764% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2017-08-30 | 106000000 | 1237.5 | 106000000 | 8602.22 | 105991397.78 | 417390514 | 25.39% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2017-09-30 | 0 | 4888256 | 106000000 | 4896858.22 | 101103141.78 | 417390514 | 24.22% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2017-10-30 | 56413682 | 13063654.44 | 162413682 | 17960512.66 | 144453169.34 | 417390514 | 34.61% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2017-11-30 | 20000000 | 15816244.36 | 182413682 | 33776757.02 | 148636924.98 | 417390514 | 35.61% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2017-12-30 | 34829580 | 21580590.69 | 217243262 | 55357347.71 | 161885914.29 | [9 empty] | 2017 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-01-30 | 51732469.35 | 17464371.62 | 268975731.35 | 72821719.33 | 196154012.02 | 417390514 | 47% |  | 0 | 2017-02-28 | original |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-02-28 | 13623123.76 | 7669860.67 | 282598855.11 | 80491580 | 202107275.11 | 417390514 | 48.42% |  | 5089749 | 2017-03-31 | original |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-03-30 | 24967924.92 | 21645612.2 | 307566780.03 | 102137192.2 | 205429587.83 | 417390514 | 49.22% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-04-30 | 13095291.56 | 11746504.19 | 320662071.59 | 113883696.39 | 206778375.2 | 417390514 | 49.54% |  | 7583998 | 2017-04-30 | original |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-05-30 | 12470336.78 | 18325318.11 | 333132408.37 | 132209014.5 | 200923393.87 | 417390514 | 48.14% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-06-30 | 4999801.98 | 15144191.1 | 338132210.35 | 147353205.6 | 190779004.75 | 417390514 | 45.71% |  | 5849284 | 2017-05-31 | original |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-07-30 | 11191427.34 | 17869636.94 | 349323637.69 | 165222842.54 | 184100795.15 | 417390514 | 44.11% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-08-30 | 15431870.55 | 7999191.34 | 364755508.24 | 173222033.88 | 191533474.36 | 417390514 | 45.89% |  | 5459726 | 2017-06-30 | original |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-09-30 | 7756191.47 | 12596146.71 | 372511699.71 | 185818180.59 | 186693519.12 | 417390514 | 44.73% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-10-30 | 19856298.91 | 13999793.19 | 392367998.62 | 199817973.78 | 192550024.84 | 417390514 | 46.13% |  | 3207733 | 2017-07-31 | original |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-11-30 | 7822627.49 | 16399752.94 | 400190626.11 | 216217726.72 | 183972899.39 | 417390514 | 44.08% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2018-12-30 | 5495509.59 | 10298474.42 | 405686135.7 | 226516201.14 | 179169934.56 | 417390514 | 42.93% |  | 4593486 | 2017-08-31 | original |  |  |  | 2018 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-01-30 | 3242067.87 | 11225359.33 | 408928203.57 | 237741560.47 | 171186643.1 | 417390514 | 41.01% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-02-28 | 0 | 8832697.11 | 408928203.57 | 246574257.58 | 162353945.99 | 417390514 | 38.9% |  | 4398604 | 2017-09-30 | original |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-03-30 | 22958127.17 | 11763491.14 | 431886330.74 | 258337748.72 | 173548582.02 | 417390514 | 41.58% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-04-30 | 22197356.65 | 13543595.74 | 454083687.39 | 271881344.46 | 182202342.93 | 417390514 | 43.65% |  | 1856322 | 2017-10-31 | original |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-05-30 | 6936347.95 | 11697981.89 | 461020035.34 | 283579326.35 | 177440708.99 | 417390514 | 42.51% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-06-30 | 1500000 | 10191062.27 | 462520035.34 | 293770388.62 | 168749646.72 | 417390514 | 40.43% |  | 2025124 | 2017-11-30 | original |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-07-30 | 4160000 | 4673802.66 | 466680035.34 | 298444191.28 | 168235844.06 | 417390514 | 40.31% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-08-30 | 7620741.44 | 7546349.69 | 474300776.78 | 305990540.97 | 168310235.81 | 417390514 | 40.32% |  | 3591068 | 2017-12-31 | original |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-09-30 | 767138.81 | 3260606.51 | 475067915.59 | 309251147.48 | 165816768.11 | 417390514 | 39.73% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-10-30 | 134252.42 | 2917599.25 | 475202168.01 | 312168746.73 | 163033421.28 | 417390514 | 39.06% |  |  | 2018-01-02 | added cash in 3 |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-11-30 | 0 | 988536.02 | 475202168.01 | 313157282.75 | 162044885.26 | 417390514 | 38.82% |  |  | 2018-01-11 | added cash in 3 |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2019-12-30 | 0 | 2539901.24 | 475202168.01 | 315697183.99 | 159504984.02 | 417390514 | 38.21% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-01-30 | 750000 | 1460116.72 | 475952168.01 | 317157300.71 | 158794867.3 | 417390514 | 38.04% |  |  | 2018-02-10 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-02-28 | 0 | 2110933.21 | 475952168.01 | 319268233.92 | 156683934.09 | 417390514 | 37.54% |  |  | 2018-02-25 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-03-30 | 500000 | 4175962.78 | 476452168.01 | 323444196.7 | 153007971.31 | 417390514 | 36.66% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-04-30 | 3000000 | 574253.34 | 479452168.01 | 324018450.04 | 155433717.97 | 417390514 | 37.24% |  |  | 2018-03-13 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-05-30 | 0 | 1021130.2 | 479452168.01 | 325039580.24 | 154412587.77 | 417390514 | 36.99% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-06-30 | 750000 | 687713.65 | 480202168.01 | 325727293.89 | 154474874.12 | 417390514 | 37.01% |  |  | 2018-04-19 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-07-30 | 0 | 866543.68 | 480202168.01 | 326593837.57 | 153608330.44 | 417390514 | 36.8% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-08-30 | 0 | 94331.81 | 480202168.01 | 326688169.38 | 153513998.63 | 417390514 | 36.78% |  |  | 2018-05-09 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-09-30 | 0 | 118467.56 | 480202168.01 | 326806636.94 | 153395531.07 | 417390514 | 36.75% |  |  | 2018-05-16 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2020-12-30 | 291975.34 | 0 | 480494143.35 | 326806636.94 | 153687506.41 | 417390514 | 36.82% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Elco Suez
Elco Suez Steel Rolling Mill Plant 3 | 2021-03-30 | 302594.27 | 0 | 480796737.62 | 326806636.94 | 153990100.68 | 417390514 | 36.89% |  |  | 2018-06-11 | added cash in 3 |  |  |  | 2021 | Industrial | Factory | Elco Suez
35 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Hyper El Temsah | 2017-09-30 | 0 | 245160 | 0 | 245160 | -245160 | 168976040.9524 | -0.1451% |  |  | 2018-06-28 | added cash in 3 |  |  |  | 2017 | Commercial | Market | Army Forces
Hyper El Temsah | 2017-10-30 | 0 | 544862.2 | 0 | 790022.2 | -790022.2 | 168976040.9524 | -0.4675% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Market | Army Forces
Hyper El Temsah | 2017-11-30 | 0 | 535752.5 | 0 | 1325774.7 | -1325774.7 | 168976040.9524 | -0.7846% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Market | Army Forces
Hyper El Temsah | 2017-12-30 | 0 | 340352 | 0 | 1666126.7 | -1666126.7 | 168976040.9524 | -0.986% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-01-30 | 0 | 446933.78 | 0 | 2113060.48 | -2113060.48 | 168976040.9524 | -1.251% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-02-28 | 0 | 6840 | 0 | 2119900.48 | -2119900.48 | 168976040.9524 | -1.255% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-03-30 | 0 | 78294.75 | 0 | 2198195.23 | -2198195.23 | 168976040.9524 | -1.301% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-05-30 | 0 | 119267.32 | 0 | 2317462.55 | -2317462.55 | 168976040.9524 | -1.371% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-06-30 | 0 | 389952.29 | 0 | 2707414.84 | -2707414.84 | 168976040.9524 | -1.602% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-07-30 | 0 | 789303.07 | 0 | 3496717.91 | -3496717.91 | 168976040.9524 | -2.069% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-08-30 | 0 | 1888802.65 | 0 | 5385520.56 | -5385520.56 | 168976040.9524 | -3.187% |  |  | 2019-03-13 | added cash in 3 |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-09-30 | 0 | 6463900.25 | 0 | 11849420.81 | -11849420.81 | 168976040.9524 | -7.012% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-10-30 | 0 | 9836882.75 | 0 | 21686303.56 | -21686303.56 | 168976040.9524 | -12.83% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-11-30 | 0 | 4228628.93 | 0 | 25914932.49 | -25914932.49 | 168976040.9524 | -15.34% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2018-12-30 | 0 | 10511632.71 | 0 | 36426565.2 | -36426565.2 | 168976040.9524 | -21.56% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-01-30 | 0 | 19083105.7 | 0 | 55509670.9 | -55509670.9 | 168976040.9524 | -32.85% |  |  | 2019-11-25 | added cash in 3 |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-02-28 | 50000000 | 8119859.98 | 50000000 | 63629530.88 | -13629530.88 | 168976040.9524 | -8.066% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-03-30 | 0 | 9265654.75 | 50000000 | 72895185.63 | -22895185.63 | 168976040.9524 | -13.55% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-04-30 | 0 | 10884794.94 | 50000000 | 83779980.57 | -33779980.57 | 168976040.9524 | -19.99% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-05-30 | 0 | 4016076.61 | 50000000 | 87796057.18 | -37796057.18 | 168976040.9524 | -22.37% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-06-30 | 0 | 9122729.91 | 50000000 | 96918787.09 | -46918787.09 | 168976040.9524 | -27.77% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-07-30 | 0 | 4525912.01 | 50000000 | 101444699.1 | -51444699.1 | 168976040.9524 | -30.44% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-08-30 | 0 | 1230114.32 | 50000000 | 102674813.42 | -52674813.42 | 168976040.9524 | -31.17% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-09-30 | 0 | 3027722.54 | 50000000 | 105702535.96 | -55702535.96 | 168976040.9524 | -32.96% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-10-30 | 0 | 516624.62 | 50000000 | 106219160.58 | -56219160.58 | 168976040.9524 | -33.27% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-11-30 | 0 | 2480726.03 | 50000000 | 108699886.61 | -58699886.61 | [9 empty] | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2019-12-30 | 0 | 25517062.53 | 50000000 | 134216949.14 | -84216949.14 | 168976040.9524 | -49.84% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-01-30 | 0 | 208257.96 | 50000000 | 134425207.1 | -84425207.1 | 168976040.9524 | -49.96% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-02-28 | 0 | 1446030.75 | 50000000 | 135871237.85 | -85871237.85 | 168976040.9524 | -50.82% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-03-30 | 0 | 709465.39 | 50000000 | 136580703.24 | -86580703.24 | 168976040.9524 | -51.24% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-04-30 | 0 | 54533.8 | 50000000 | 136635237.04 | -86635237.04 | 168976040.9524 | -51.27% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-05-30 | 0 | 385336.8 | 50000000 | 137020573.84 | -87020573.84 | 168976040.9524 | -51.5% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-06-30 | 0 | 24449.64 | 50000000 | 137045023.48 | -87045023.48 | 168976040.9524 | -51.51% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-07-30 | 0 | 82387.5 | 50000000 | 137127410.98 | -87127410.98 | 168976040.9524 | -51.56% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-08-30 | 0 | 216850.76 | 50000000 | 137344261.74 | -87344261.74 | 168976040.9524 | -51.69% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-09-30 | 0 | 4630.96 | 50000000 | 137348892.7 | -87348892.7 | 168976040.9524 | -51.69% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2020-10-30 | 0 | 3150 | 50000000 | 137352042.7 | -87352042.7 | 168976040.9524 | -51.69% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Hyper El Temsah | 2021-01-30 | 0 | 163444.25 | 50000000 | 137515486.95 | -87515486.95 | 168976040.9524 | -51.79% |  |  | 2018-02-27 | added cash in 3 |  |  |  | 2021 | Commercial | Market | Army Forces
Hyper El Temsah | 2021-03-30 | 0 | 114625.7 | 50000000 | 137630112.65 | -87630112.65 | 168976040.9524 | -51.86% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Market | Army Forces
36 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Marassi Bridge Pkg 117 | 2017-10-30 | 0 | 30000 | 0 | 30000 | -30000 | 45205818 | -0.06636% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2017-11-30 | 0 | 212527 | 0 | 242527 | -242527 | 45205818 | -0.5365% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2017-12-30 | 0 | 2690053.5 | 0 | 2932580.5 | -2932580.5 | 45205818 | -6.487% |  |  | 2018-06-11 | added cash in 3 |  |  |  | 2017 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-01-30 | 0 | 980425.42 | 0 | 3913005.92 | -3913005.92 | 45205818 | -8.656% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-02-28 | 4130124.14 | 2031924.09 | 4130124.14 | 5944930.01 | -1814805.87 | 45205818 | -4.015% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-03-30 | 6455421.01 | 2698556.32 | 10585545.15 | 8643486.33 | 1942058.82 | 45205818 | 4.296% |  |  | 2018-08-31 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-04-30 | 4502026.51 | 545075.16 | 15087571.66 | 9188561.49 | 5899010.17 | 45205818 | 13.05% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-05-30 | 4149842.33 | 2647409.29 | 19237413.99 | 11835970.78 | 7401443.21 | 45205818 | 16.37% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-06-30 | 5285427.07 | 2018725.56 | 24522841.06 | 13854696.34 | 10668144.72 | 45205818 | 23.6% |  |  | 2018-10-18 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-07-30 | 5347404.78 | 1073426.77 | 29870245.84 | 14928123.11 | 14942122.73 | 45205818 | 33.05% |  |  | 2018-10-28 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-08-30 | 301773.91 | 1261773.88 | 30172019.75 | 16189896.99 | 13982122.76 | 45205818 | 30.93% |  |  | 2018-10-29 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-09-30 | 344451.17 | 972230.29 | 30516470.92 | 17162127.28 | 13354343.64 | 45205818 | 29.54% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-10-30 | 0 | 1409245.11 | 30516470.92 | 18571372.39 | 11945098.53 | 45205818 | 26.42% |  |  | 2018-11-18 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-11-30 | 0 | 2246958.27 | 30516470.92 | 20818330.66 | 9698140.26 | 45205818 | 21.45% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2018-12-30 | 0 | 930830.54 | 30516470.92 | 21749161.2 | 8767309.72 | 45205818 | 19.39% |  |  | 2018-12-19 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-01-30 | 4015282.83 | 523327.33 | 34531753.75 | 22272488.53 | 12259265.22 | 45205818 | 27.12% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-02-28 | 2807159.72 | 1203843.06 | 37338913.47 | 23476331.59 | 13862581.88 | 45205818 | 30.67% |  |  | 2019-01-20 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-03-30 | 882296.11 | 2182046.24 | 38221209.58 | 25658377.83 | 12562831.75 | 45205818 | 27.79% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-04-30 | 163866.22 | 517499.8 | 38385075.8 | 26175877.63 | 12209198.17 | 45205818 | 27.01% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-05-30 | 56058.22 | 1186483.73 | 38441134.02 | 27362361.36 | 11078772.66 | 45205818 | 24.51% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-06-30 | 809762.24 | 316875.55 | 39250896.26 | 27679236.91 | 11571659.35 | 45205818 | 25.6% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-07-30 | 57062.55 | 203824.2 | 39307958.81 | 27883061.11 | 11424897.7 | 45205818 | 25.27% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-08-30 | 0 | 247991.13 | 39307958.81 | 28131052.24 | 11176906.57 | 45205818 | 24.72% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-09-30 | 0 | 147625.68 | 39307958.81 | 28278677.92 | 11029280.89 | 45205818 | 24.4% |  |  | 2019-07-30 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-10-30 | 0 | 375458.68 | 39307958.81 | 28654136.6 | 10653822.21 | 45205818 | 23.57% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-11-30 | 3376927.91 | 355231.29 | 42684886.72 | 29009367.89 | 13675518.83 | 45205818 | 30.25% |  |  | 2019-08-14 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2019-12-30 | 3145907.11 | 4538747.53 | 45830793.83 | 33548115.42 | 12282678.41 | 45205818 | 27.17% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2020-01-30 | 0 | 1096980.84 | 45830793.83 | 34645096.26 | 11185697.57 | 45205818 | 24.74% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2020-02-28 | 0 | 397669.97 | 45830793.83 | 35042766.23 | 10788027.6 | 45205818 | 23.86% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2020-04-30 | 285951.45 | 12390.38 | 46116745.28 | 35055156.61 | 11061588.67 | 45205818 | 24.47% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2020-07-30 | 0 | 15373.58 | 46116745.28 | 35070530.19 | 11046215.09 | 45205818 | 24.44% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2020-10-30 | 0 | 252803.38 | 46116745.28 | 35323333.57 | 10793411.71 | 45205818 | 23.88% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2020-11-30 | 0 | 195238 | 46116745.28 | 35518571.57 | 10598173.71 | 45205818 | 23.44% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2020-12-30 | 2483342.5 | 105849.34 | 48600087.78 | 35624420.91 | 12975666.87 | 45205818 | 28.7% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2021-01-30 | 0 | 12390.38 | 48600087.78 | 35636811.29 | 12963276.49 | 45205818 | 28.68% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2021-02-28 | 0 | 81906.72 | 48600087.78 | 35718718.01 | 12881369.77 | 45205818 | 28.49% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridge Pkg 117 | 2021-03-30 | 0 | 9700 | 48600087.78 | 35728418.01 | 12871669.77 | [9 empty] | 2021 | Infrastructure | Bridges & Tunnels | EMAAR
37 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Siemens Power Station | 2017-11-30 | 0 | 1711347 | 0 | 1711347 | -1711347 | 332856409 | -0.5141% |  | 0 | 2017-04-30 | original |  |  |  | 2017 | Industrial | Factory | SIEMENS
Siemens Power Station | 2017-12-30 | 93300000 | 17982481.04 | 93300000 | 19693828.04 | 73606171.96 | 332856409 | 22.11% |  |  |  | cash out both |  |  |  | 2017 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-01-30 | 0 | 2692849.35 | 93300000 | 22386677.39 | 70913322.61 | 332856409 | 21.3% |  | 4208625 | 2017-05-31 | original |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-02-28 | 0 | 13868263.53 | 93300000 | 36254940.92 | 57045059.08 | 332856409 | 17.14% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-03-30 | 10260860.78 | 15856372.59 | 103560860.78 | 52111313.51 | 51449547.27 | 332856409 | 15.46% |  | 2309681 | 2017-06-30 | original |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-04-30 | 11065687.7 | 20054182.34 | 114626548.48 | 72165495.85 | 42461052.63 | 332856409 | 12.76% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-05-30 | 0 | 13243374.04 | 114626548.48 | 85408869.89 | 29217678.59 | 332856409 | 8.778% |  | 19580519 | 2017-07-31 | original |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-06-30 | 13218163.56 | 9644209.72 | 127844712.04 | 95053079.61 | 32791632.43 | 332856409 | 9.852% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-07-30 | 15893608.72 | 17289950.78 | 143738320.76 | 112343030.39 | 31395290.37 | 332856409 | 9.432% |  | 18663617 | 2017-08-31 | original |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-08-30 | 12641621.4 | 7125695.83 | 156379942.16 | 119468726.22 | 36911215.94 | 332856409 | 11.09% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-09-30 | 13673026.82 | 20998983.27 | 170052968.98 | 140467709.49 | 29585259.49 | 332856409 | 8.888% |  | 45266644 | 2017-09-30 | original |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-10-30 | 6271528.33 | 27846645.1 | 176324497.31 | 168314354.59 | 8010142.72 | 332856409 | 2.406% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-11-30 | 25271356.23 | 26331552.1 | 201595853.54 | 194645906.69 | 6949946.85 | 332856409 | 2.088% |  | 50037584 | 2017-10-31 | original |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2018-12-30 | 17822796.64 | 21352523.97 | 219418650.18 | 215998430.66 | 3420219.52 | 332856409 | 1.028% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-01-30 | 20002003.08 | 20382650.41 | 239420653.26 | 236381081.07 | 3039572.19 | 332856409 | 0.9132% |  | 38477605 | 2017-11-30 | original |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-02-28 | 27970974.36 | 14215044.71 | 267391627.62 | 250596125.78 | 16795501.84 | 332856409 | 5.046% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-03-30 | 0 | 19918306.52 | 267391627.62 | 270514432.3 | -3122804.68 | 332856409 | -0.9382% |  | 42599880 | 2017-12-31 | original |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-04-30 | 0 | 15576469.86 | 267391627.62 | 286090902.16 | -18699274.54 | 332856409 | -5.618% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-05-30 | 20418831.59 | 10157200.82 | 287810459.21 | 296248102.98 | -8437643.77 | 332856409 | -2.535% |  |  | 2018-01-29 | added cash in 3 |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-06-30 | 0 | 6560392.16 | 287810459.21 | 302808495.14 | -14998035.93 | 332856409 | -4.506% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-07-30 | 0 | 2536532.82 | 287810459.21 | 305345027.96 | -17534568.75 | 332856409 | -5.268% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-08-30 | 0 | 4693731.53 | 287810459.21 | 310038759.49 | -22228300.28 | 332856409 | -6.678% |  |  | 2018-03-20 | added cash in 3 |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-09-30 | 12124718 | 4150447.48 | 299935177.21 | 314189206.97 | -14254029.76 | 332856409 | -4.282% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-10-30 | 0 | 1291060.92 | 299935177.21 | 315480267.89 | -15545090.68 | 332856409 | -4.67% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-11-30 | 0 | 525714.18 | 299935177.21 | 316005982.07 | -16070804.86 | 332856409 | -4.828% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2019-12-30 | 0 | 2185295.58 | 299935177.21 | 318191277.65 | -18256100.44 | 332856409 | -5.485% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2019 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-01-30 | 0 | 1392288.2 | 299935177.21 | 319583565.85 | -19648388.64 | 332856409 | -5.903% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-02-28 | 25672200.91 | 1036801.86 | 325607378.12 | 320620367.71 | 4987010.41 | 332856409 | 1.498% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-03-30 | 15319191 | 5406000.02 | 340926569.12 | 326026367.73 | 14900201.39 | 332856409 | 4.476% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-04-30 | 0 | 816601.57 | 340926569.12 | 326842969.3 | 14083599.82 | 332856409 | 4.231% |  |  | 2018-09-23 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-05-30 | 0 | 2090061.1 | 340926569.12 | 328933030.4 | 11993538.72 | 332856409 | 3.603% |  |  | 2018-09-30 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-06-30 | 0 | 195960.88 | 340926569.12 | 329128991.28 | 11797577.84 | 332856409 | 3.544% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-07-30 | 0 | 1332197.1 | 340926569.12 | 330461188.38 | 10465380.74 | 332856409 | 3.144% |  |  | 2018-10-09 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-08-30 | 0 | 150348.5 | 340926569.12 | 330611536.88 | 10315032.24 | 332856409 | 3.099% |  |  | 2018-10-11 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-09-30 | 144907 | 0 | 341071476.12 | 330611536.88 | 10459939.24 | 332856409 | 3.142% |  |  | 2018-10-16 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-10-30 | 0 | 829761.26 | 341071476.12 | 331441298.14 | 9630177.98 | 332856409 | 2.893% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-11-30 | 888628.7 | 108900 | 341960104.82 | 331550198.14 | 10409906.68 | 332856409 | 3.127% |  |  | 2018-11-19 | added cash in 3 |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2020-12-30 | 0 | 479946.07 | 341960104.82 | 332030144.21 | 9929960.61 | 332856409 | 2.983% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | SIEMENS
Siemens Power Station | 2021-02-28 | 0 | 1677560.13 | 341960104.82 | 333707704.34 | 8252400.48 | 332856409 | 2.479% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Factory | SIEMENS
Siemens Power Station | 2021-03-30 | 0 | 138860.39 | 341960104.82 | 333846564.73 | 8113540.09 | 332856409 | 2.438% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Factory | SIEMENS
38 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Uptown FM85 Pkg 85 | 2017-11-30 | 1692495 | 0 | 1692495 | 0 | 1692495 | 0 | #DIV/0! |  |  | 2019-03-21 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-01-30 | 813632.52 | 296517.99 | 2506127.52 | 296517.99 | 2209609.53 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-02-28 | 0 | 53199.39 | 2506127.52 | 349717.38 | 2156410.14 | 0 | #DIV/0! |  |  | 2019-04-22 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-03-30 | 293424.13 | 177163.25 | 2799551.65 | 526880.63 | 2272671.02 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-04-30 | 0 | 213603.84 | 2799551.65 | 740484.47 | 2059067.18 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-05-30 | 0 | 80420 | 2799551.65 | 820904.47 | 1978647.18 | 0 | #DIV/0! |  |  | 2019-06-23 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-06-30 | 0 | 165464.4 | 2799551.65 | 986368.87 | 1813182.78 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-07-30 | 0 | 227927.8 | 2799551.65 | 1214296.67 | 1585254.98 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-08-30 | 2494764.06 | 26592.19 | 5294315.71 | 1240888.86 | 4053426.85 | 0 | #DIV/0! |  |  | 2019-08-08 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-09-30 | 0 | 52100 | 5294315.71 | 1292988.86 | 4001326.85 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-10-30 | 0 | 296570 | 5294315.71 | 1589558.86 | 3704756.85 | 0 | #DIV/0! |  |  | 2019-09-03 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-11-30 | 0 | 645015.14 | 5294315.71 | 2234574 | 3059741.71 | 0 | #DIV/0! |  |  | 2019-09-04 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2018-12-30 | 0 | 314147.25 | 5294315.71 | 2548721.25 | 2745594.46 | 0 | #DIV/0! |  |  | 2019-09-08 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2019-01-30 | 0 | 190646.71 | 5294315.71 | 2739367.96 | 2554947.75 | 0 | #DIV/0! |  |  | 2019-09-23 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2019-02-28 | 1729285.15 | 246164.2 | 7023600.86 | 2985532.16 | 4038068.7 | 0 | #DIV/0! |  |  | 2019-09-30 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2019-03-30 | 0 | 16025 | 7023600.86 | 3001557.16 | 4022043.7 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2019-05-30 | 768766.59 | 62219.61 | 7792367.45 | 3063776.77 | 4728590.68 | 0 | #DIV/0! |  |  | 2019-10-15 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2019-08-30 | 0 | 21500 | 7792367.45 | 3085276.77 | 4707090.68 | 0 | #DIV/0! |  |  | 2019-10-30 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2020-01-30 | 29830.3 | 0 | 7822197.75 | 3085276.77 | 4736920.98 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2020-03-30 | 0 | 247925 | 7822197.75 | 3333201.77 | 4488995.98 | 0 | #DIV/0! |  |  | 2019-11-20 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2020-04-30 | 1391898.96 | 0 | 9214096.71 | 3333201.77 | 5880894.94 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Uptown FM85 Pkg 85 | 2021-02-28 | 0 | 98875 | 9214096.71 | 3432076.77 | 5782019.94 | 0 | #DIV/0! |  |  | 2019-12-02 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | EMAAR
39 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Sokhna Tunnel 01 | 2018-01-30 | 0 | 332132.97 | 0 | 332132.97 | -332132.97 | 46639513 | -0.7121% |  |  | 2019-12-31 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-02-28 | 0 | 260504.32 | 0 | 592637.29 | -592637.29 | 46639513 | -1.271% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-03-30 | 0 | 1433831.6 | 0 | 2026468.89 | -2026468.89 | 46639513 | -4.345% |  |  | 2020-01-19 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-04-30 | 0 | 491806.59 | 0 | 2518275.48 | -2518275.48 | 46639513 | -5.399% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-05-30 | 0 | 2892827.27 | 0 | 5411102.75 | -5411102.75 | 46639513 | -11.6% |  |  | 2020-02-11 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-06-30 | 0 | 3549019.15 | 0 | 8960121.9 | -8960121.9 | 46639513 | -19.21% |  |  | 2020-02-17 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-07-30 | 0 | 1683429.59 | 0 | 10643551.49 | -10643551.49 | 46639513 | -22.82% |  |  | 2020-02-18 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-08-30 | 0 | 1045341.82 | 0 | 11688893.31 | -11688893.31 | 46639513 | -25.06% |  |  | 2020-02-23 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-09-30 | 29705900 | 1425805.89 | 29705900 | 13114699.2 | 16591200.8 | 46639513 | 35.57% |  |  | 2020-02-26 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-10-30 | 2369466.65 | 1459978.03 | 32075366.65 | 14574677.23 | 17500689.42 | 46639513 | 37.52% |  |  | 2020-03-01 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-11-30 | 2014847.9 | 666332.68 | 34090214.55 | 15241009.91 | 18849204.64 | 46639513 | 40.41% |  |  | 2020-03-03 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2018-12-30 | 4616391.9 | 145169.08 | 38706606.45 | 15386178.99 | 23320427.46 | 46639513 | 50% |  |  | 2020-03-05 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2019-01-30 | 0 | 684833.66 | 38706606.45 | 16071012.65 | 22635593.8 | 46639513 | 48.53% |  |  | 2020-03-22 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2019-02-28 | 0 | 55943.56 | 38706606.45 | 16126956.21 | 22579650.24 | 46639513 | 48.41% |  |  | 2020-03-26 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2019-03-30 | 0 | 41837.18 | 38706606.45 | 16168793.39 | 22537813.06 | 46639513 | 48.32% |  |  | 2020-03-31 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2019-05-30 | 0 | 10312.02 | 38706606.45 | 16179105.41 | 22527501.04 | 46639513 | 48.3% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2019-07-30 | 1116704.5 | 0 | 39823310.95 | 16179105.41 | 23644205.54 | 46639513 | 50.7% |  |  | 2020-04-23 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2019-12-30 | 0 | 674528 | 39823310.95 | 16853633.41 | 22969677.54 | 46639513 | 49.25% |  |  | 2020-04-26 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2020-09-30 | 1702965 | 0 | 41526275.95 | 16853633.41 | 24672642.54 | 46639513 | 52.9% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 01 | 2020-12-30 | 0 | 11.35 | 41526275.95 | 16853644.76 | 24672631.19 | 46639513 | 52.9% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
40 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Abu Sultan Bridge 01 | 2018-01-30 | 0 | 99700 | 0 | 99700 | -99700 | 18752986 | -0.5316% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-02-28 | 0 | 339116.34 | 0 | 438816.34 | -438816.34 | 18752986 | -2.34% |  |  | 2020-07-28 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-03-30 | 0 | 288546.9 | 0 | 727363.24 | -727363.24 | 18752986 | -3.879% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-04-30 | 0 | 194305.82 | 0 | 921669.06 | -921669.06 | 18752986 | -4.915% |  |  | 2020-08-23 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-05-30 | 0 | 957258.78 | 0 | 1878927.84 | -1878927.84 | 18752986 | -10.02% |  |  | 2020-08-25 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-06-30 | 0 | 1343658.02 | 0 | 3222585.86 | -3222585.86 | 18752986 | -17.18% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-07-30 | 0 | 1524434.49 | 0 | 4747020.35 | -4747020.35 | 18752986 | -25.31% |  |  | 2020-09-10 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-08-30 | 0 | 1225823.63 | 0 | 5972843.98 | -5972843.98 | 18752986 | -31.85% |  |  | 2020-10-01 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-09-30 | 0 | 1370928.36 | 0 | 7343772.34 | -7343772.34 | 18752986 | -39.16% |  |  | 2020-10-04 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-10-30 | 0 | 896181.84 | 0 | 8239954.18 | -8239954.18 | 18752986 | -43.94% |  |  | 2020-10-18 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-11-30 | 0 | 1352163.46 | 0 | 9592117.64 | -9592117.64 | 18752986 | -51.15% |  |  | 2020-10-25 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2018-12-30 | 0 | 1399972.07 | 0 | 10992089.71 | -10992089.71 | 18752986 | -58.62% |  |  | 2020-10-28 | added 1 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2019-01-30 | 11280475 | 14286.61 | 11280475 | 11006376.32 | 274098.68 | 18752986 | 1.462% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2019-02-28 | 0 | 68140.8 | 11280475 | 11074517.12 | 205957.88 | 18752986 | 1.098% |  |  | 2020-11-11 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2019-03-30 | 0 | 71808.22 | 11280475 | 11146325.34 | 134149.66 | 18752986 | 0.7154% |  |  | 2020-11-22 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2019-04-30 | 0 | 1500 | 11280475 | 11147825.34 | 132649.66 | 18752986 | 0.7074% |  |  | 2020-11-29 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2019-06-30 | 0 | 1221 | 11280475 | 11149046.34 | 131428.66 | 18752986 | 0.7008% |  |  | 2020-11-30 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2019-12-30 | 495270 | 20107 | 11775745 | 11169153.34 | 606591.66 | 18752986 | 3.235% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2020-01-30 | 664967 | 0 | 12440712 | 11169153.34 | 1271558.66 | 18752986 | 6.781% |  |  | 2020-12-31 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 01 | 2020-02-28 | 0 | 3525.75 | 12440712 | 11172679.09 | 1268032.91 | 18752986 | 6.762% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
41 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Mintra Factory | 2018-01-30 | 10000000 | 0 | 10000000 | 0 | 10000000 | 112045826 | 8.925% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-02-28 | 0 | 138415 | 10000000 | 138415 | 9861585 | 112045826 | 8.801% |  |  | 2021-02-24 | added cash in 3 |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-03-30 | 0 | 1857867.59 | 10000000 | 1996282.59 | 8003717.41 | 112045826 | 7.143% |  |  | 2021-02-25 | added cash in 3 |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-04-30 | 1500000 | 1042147.17 | 11500000 | 3038429.76 | 8461570.24 | 112045826 | 7.552% |  |  | 2021-02-26 | added 1 |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-05-30 | 0 | 1699029.18 | 11500000 | 4737458.94 | 6762541.06 | 112045826 | 6.036% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-06-30 | 4000000 | 5830118.14 | 15500000 | 10567577.08 | 4932422.92 | 112045826 | 4.402% |  |  | 2021-04-06 | added cash in 3 |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-07-30 | 0 | 2214918.06 | 15500000 | 12782495.14 | 2717504.86 | [9 empty] | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-08-30 | 3000000 | 2908079.66 | 18500000 | 15690574.8 | 2809425.2 | 112045826 | 2.507% |  | 0 | 2016-06-30 | original |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-09-30 | 0 | 6129955.33 | 18500000 | 21820530.13 | -3320530.13 | 112045826 | -2.964% |  | 15153556 | 2016-09-30 | original |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-10-30 | 2220782.14 | 2840033.34 | 20720782.14 | 24660563.47 | -3939781.33 | 112045826 | -3.516% |  | 10121476 | 2016-10-30 | original |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-11-30 | 4031998.67 | 4006449.74 | 24752780.81 | 28667013.21 | -3914232.4 | 112045826 | -3.493% |  | 4821423 | 2016-11-30 | original |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2018-12-30 | 8000000 | 2692007.54 | 32752780.81 | 31359020.75 | 1393760.06 | 112045826 | 1.244% |  | 0 | 2016-12-30 | original |  |  |  | 2018 | Industrial | Factory | Mintra
Mintra Factory | 2019-01-30 | 0 | 2508200.16 | 32752780.81 | 33867220.91 | -1114440.1 | 112045826 | -0.9946% |  | 12888090 | 2017-01-31 | original |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-02-28 | 0 | 2185912.68 | 32752780.81 | 36053133.59 | -3300352.78 | 112045826 | -2.946% |  | 6146055 | 2017-02-28 | original |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-03-30 | 0 | 1164893.68 | 32752780.81 | 37218027.27 | -4465246.46 | 112045826 | -3.985% |  | 9275154 | 2017-03-31 | original |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-04-30 | 3000000 | 984398.2 | 35752780.81 | 38202425.47 | -2449644.66 | 112045826 | -2.186% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-05-30 | 3000000 | 1046236.19 | 38752780.81 | 39248661.66 | -495880.85 | 112045826 | -0.4426% |  | 5494300 | 2017-04-30 | original |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-06-30 | 0 | 346450.46 | 38752780.81 | 39595112.12 | -842331.31 | 112045826 | -0.7518% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-07-30 | 0 | 295577.76 | 38752780.81 | 39890689.88 | -1137909.07 | 112045826 | -1.016% |  | 3473623 | 2017-05-31 | original |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-08-30 | 0 | 990628.41 | 38752780.81 | 40881318.29 | -2128537.48 | 112045826 | -1.9% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-09-30 | 0 | 917579.61 | 38752780.81 | 41798897.9 | -3046117.09 | 112045826 | -2.719% |  | 14504056 | 2017-06-30 | original |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-10-30 | 0 | 248013.15 | 38752780.81 | 42046911.05 | -3294130.24 | 112045826 | -2.94% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-11-30 | 0 | 16213.92 | 38752780.81 | 42063124.97 | -3310344.16 | 112045826 | -2.954% |  | 2268981 | 2017-07-31 | original |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2019-12-30 | 0 | 319930.18 | 38752780.81 | 42383055.15 | -3630274.34 | 112045826 | -3.24% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Mintra
Mintra Factory | 2020-01-30 | 0 | 20124.99 | 38752780.81 | 42403180.14 | -3650399.33 | 112045826 | -3.258% |  | 1621441 | 2017-08-31 | original |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-02-28 | 0 | 70032.41 | 38752780.81 | 42473212.55 | -3720431.74 | 112045826 | -3.32% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-03-30 | 0 | 120619.12 | 38752780.81 | 42593831.67 | -3841050.86 | 112045826 | -3.428% |  | 2833459 | 2017-09-30 | original |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-04-30 | 0 | 90025.05 | 38752780.81 | 42683856.72 | -3931075.91 | 112045826 | -3.508% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-05-30 | 0 | 86818.53 | 38752780.81 | 42770675.25 | -4017894.44 | 112045826 | -3.586% |  | 6985512 | 2017-10-31 | original |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-06-30 | 0 | 469061.83 | 38752780.81 | 43239737.08 | -4486956.27 | 112045826 | -4.005% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-09-30 | 0 | 66123.38 | 38752780.81 | 43305860.46 | -4553079.65 | 112045826 | -4.064% |  | 3003863 | 2017-11-30 | original |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-10-30 | 0 | 71495 | 38752780.81 | 43377355.46 | -4624574.65 | 112045826 | -4.127% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-11-30 | 0 | 3513.52 | 38752780.81 | 43380868.98 | -4628088.17 | 112045826 | -4.131% |  | 2335376 | 2017-12-31 | original |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2020-12-30 | 0 | 117222.45 | 38752780.81 | 43498091.43 | -4745310.62 | 112045826 | -4.235% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Mintra
Mintra Factory | 2021-02-28 | 2999463.45 | 0 | 41752244.26 | 43498091.43 | -1745847.17 | 112045826 | -1.558% |  |  | 2018-01-30 | added cash in 3 |  |  |  | 2021 | Industrial | Factory | Mintra
Mintra Factory | 2021-03-30 | 0 | 7949.5 | 41752244.26 | 43506040.93 | -1753796.67 | 112045826 | -1.565% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Factory | Mintra
42 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
King Farouk Restoration | 2018-04-30 | 0 | 20258.6 | 0 | 20258.6 | -20258.6 | 0 | #DIV/0! |  |  | 2018-03-11 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
King Farouk Restoration | 2018-05-30 | 0 | 39355 | 0 | 59613.6 | -59613.6 | 0 | #DIV/0! |  |  | 2018-03-28 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
King Farouk Restoration | 2018-06-30 | 0 | 25234.25 | 0 | 84847.85 | -84847.85 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Restoration | Palace | Army Forces
King Farouk Restoration | 2018-07-30 | 0 | 18497.2 | 0 | 103345.05 | -103345.05 | 0 | #DIV/0! |  |  | 2018-04-19 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
King Farouk Restoration | 2018-08-30 | 0 | 6160 | 0 | 109505.05 | -109505.05 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Restoration | Palace | Army Forces
43 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Mohamed Ali Palace | 2018-03-30 | 5800000 | 16115 | 5800000 | 16115 | 5783885 | 150000000 | 3.856% |  |  |  | cash out both |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-04-30 | 0 | 122274 | 5800000 | 138389 | 5661611 | 150000000 | 3.774% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-05-30 | 0 | 411107.95 | 5800000 | 549496.95 | 5250503.05 | 150000000 | 3.5% |  |  |  | cash out both |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-06-30 | 0 | 333148.55 | 5800000 | 882645.5 | 4917354.5 | 150000000 | 3.278% |  |  | 2018-07-11 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-07-30 | 0 | 155537.98 | 5800000 | 1038183.48 | 4761816.52 | 150000000 | 3.175% |  |  | 2018-07-17 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-08-30 | 2700000 | 627647.03 | 8500000 | 1665830.51 | 6834169.49 | 150000000 | 4.556% |  |  | 2018-07-31 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-09-30 | 0 | 639235.38 | 8500000 | 2305065.89 | 6194934.11 | 150000000 | 4.13% |  |  |  | cash out both |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-10-30 | 0 | 673355.81 | 8500000 | 2978421.7 | 5521578.3 | 150000000 | 3.681% |  |  |  | cash out both |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-11-30 | 0 | 1172087.2 | 8500000 | 4150508.9 | 4349491.1 | 150000000 | 2.9% |  |  | 2018-09-17 | added cash in 3 |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2018-12-30 | 0 | 1168321.79 | 8500000 | 5318830.69 | 3181169.31 | 150000000 | 2.121% |  |  |  | cash out both |  |  |  | 2018 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-01-30 | 0 | 822985.11 | 8500000 | 6141815.8 | 2358184.2 | 150000000 | 1.572% |  |  | 2018-10-25 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-02-28 | 0 | 996248.18 | 8500000 | 7138063.98 | 1361936.02 | 150000000 | 0.908% |  |  | 2018-10-29 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-03-30 | 0 | 1170433.23 | 8500000 | 8308497.21 | 191502.79 | 150000000 | 0.1277% |  |  |  | cash out both |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-04-30 | 0 | 1577851.14 | 8500000 | 9886348.35 | -1386348.35 | 150000000 | -0.9242% |  |  | 2018-11-12 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-05-30 | 0 | 1314462.57 | 8500000 | 11200810.92 | -2700810.92 | 150000000 | -1.801% |  |  | 2018-11-15 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-06-30 | 0 | 1435290.59 | 8500000 | 12636101.51 | -4136101.51 | 150000000 | -2.757% |  |  |  | cash out both |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-07-30 | 0 | 2879743.91 | 8500000 | 15515845.42 | -7015845.42 | 150000000 | -4.677% |  |  | 2018-12-12 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-08-30 | 0 | 1446316.66 | 8500000 | 16962162.08 | -8462162.08 | 150000000 | -5.641% |  |  |  | cash out both |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-09-30 | 0 | 1739488.36 | 8500000 | 18701650.44 | -10201650.44 | 150000000 | -6.801% |  |  | 2019-01-09 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-10-30 | 0 | 916732.18 | 8500000 | 19618382.62 | -11118382.62 | 150000000 | -7.412% |  |  | 2019-01-30 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-11-30 | 0 | 2250260.91 | 8500000 | 21868643.53 | -13368643.53 | 150000000 | -8.912% |  |  |  | cash out both |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2019-12-30 | 0 | 2913698.17 | 8500000 | 24782341.7 | -16282341.7 | 150000000 | -10.85% |  |  | 2019-02-24 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-01-30 | 0 | 1961976.68 | 8500000 | 26744318.38 | -18244318.38 | 150000000 | -12.16% |  |  | 2019-02-27 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-02-28 | 0 | 1086385.92 | 8500000 | 27830704.3 | -19330704.3 | 150000000 | -12.89% |  |  | 2019-02-28 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-03-30 | 22959627 | 628881.02 | 31459627 | 28459585.32 | 3000041.68 | 150000000 | 2% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-04-30 | 0 | 855430.16 | 31459627 | 29315015.48 | 2144611.52 | 150000000 | 1.43% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-05-30 | 0 | 1032518.29 | 31459627 | 30347533.77 | 1112093.23 | 150000000 | 0.7414% |  |  | 2019-04-15 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-06-30 | 0 | 990392.09 | 31459627 | 31337925.86 | 121701.14 | 150000000 | 0.08113% |  |  | 2019-04-18 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-07-30 | 0 | 3352570.33 | 31459627 | 34690496.19 | -3230869.19 | 150000000 | -2.154% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-08-30 | 0 | 2064789.27 | 31459627 | 36755285.46 | -5295658.46 | 150000000 | -3.53% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-09-30 | 0 | 2220668.47 | 31459627 | 38975953.93 | -7516326.93 | 150000000 | -5.011% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-10-30 | 572405 | 3545688.26 | 32032032 | 42521642.19 | -10489610.19 | 150000000 | -6.993% |  |  | 2019-07-17 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-11-30 | 0 | 5461955.2 | 32032032 | 47983597.39 | -15951565.39 | 150000000 | -10.63% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2020-12-30 | 0 | 4701467.52 | 32032032 | 52685064.91 | -20653032.91 | 150000000 | -13.77% |  |  | 2019-08-05 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2021-01-30 | 1597635 | 4699528.24 | 33629667 | 57384593.15 | -23754926.15 | 150000000 | -15.84% |  |  |  | cash out both |  |  |  | 2021 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2021-02-28 | 0 | 3110502.73 | 33629667 | 60495095.88 | -26865428.88 | 150000000 | -17.91% |  |  |  | cash out both |  |  |  | 2021 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2021-03-30 | 0 | 5379249.69 | 33629667 | 65874345.57 | -32244678.57 | 150000000 | -21.5% |  |  | 2019-10-20 | added cash in 3 |  |  |  | 2021 | Restoration | Palace | Army Forces
Mohamed Ali Palace | 2021-04-30 | 0 | 5432912.29 | 33629667 | 71307257.86 | -37677590.86 | 150000000 | -25.12% | [8 empty] | Restoration | Palace | Army Forces
44 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Nefisha Bridge | 2018-03-30 | 0 | 165869.05 | 0 | 165869.05 | -165869.05 | 70928098 | -0.2339% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-04-30 | 0 | 73090 | 0 | 238959.05 | -238959.05 | 70928098 | -0.3369% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-05-30 | 0 | 235755.71 | 0 | 474714.76 | -474714.76 | 70928098 | -0.6693% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-06-30 | 0 | 198714.37 | 0 | 673429.13 | -673429.13 | 70928098 | -0.9495% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-07-30 | 0 | 1424063 | 0 | 2097492.13 | -2097492.13 | 70928098 | -2.957% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-08-30 | 22000000 | 1865942.45 | 22000000 | 3963434.58 | 18036565.42 | 70928098 | 25.43% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-09-30 | 0 | 4441560.05 | 22000000 | 8404994.63 | 13595005.37 | 70928098 | 19.17% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-10-30 | 0 | 4354340.91 | 22000000 | 12759335.54 | 9240664.46 | 70928098 | 13.03% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-11-30 | 0 | 3160685.81 | 22000000 | 15920021.35 | 6079978.65 | 70928098 | 8.572% |  |  | 2020-09-28 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2018-12-30 |  | 2000000 | 22000000 | 17920021.35 | 4079978.65 | 70928098 | 5.752% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-01-30 | 0 | 1952928.38 | 22000000 | 19872949.73 | 2127050.27 | 70928098 | 2.999% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-02-28 | 12381198.65 | 973730.81 | 34381198.65 | 20846680.54 | 13534518.11 | 70928098 | 19.08% |  |  | 2020-11-22 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-03-30 | 0 | 766775.78 | 34381198.65 | 21613456.32 | 12767742.33 | 70928098 | 18% |  |  | 2021-01-11 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-04-30 | 0 | 42076.9 | 34381198.65 | 21655533.22 | 12725665.43 | 70928098 | 17.94% |  |  | 2021-01-20 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-06-30 | 0 | 319177 | 34381198.65 | 21974710.22 | 12406488.43 | 70928098 | 17.49% |  |  | 2021-01-31 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-07-30 | 11694567.55 | 0 | 46075766.2 | 21974710.22 | 24101055.98 | 70928098 | 33.98% |  |  | 2021-02-01 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-08-30 | 0 | 16740 | 46075766.2 | 21991450.22 | 24084315.98 | 70928098 | 33.96% |  |  | 2021-02-08 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2019-12-30 | 0 | 13262259.73 | 46075766.2 | 35253709.95 | 10822056.25 | 70928098 | 15.26% |  |  | 2021-02-24 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Nefisha Bridge | 2020-12-30 | 0 | 10203.9 | 46075766.2 | 35263913.85 | 10811852.35 | 70928098 | 15.24% | [8 empty] | Infrastructure | Bridges & Tunnels | Army Forces
45 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Fish Market | 2018-03-30 | 0 | 30000 | 0 | 30000 | -30000 | 66185668.5714 | -0.04533% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-04-30 | 0 | 43015 | 0 | 73015 | -73015 | 66185668.5714 | -0.1103% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-05-30 | 0 | 39990.5 | 0 | 113005.5 | -113005.5 | 66185668.5714 | -0.1707% |  | 0 | 2017-06-30 | original |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-06-30 | 0 | 471730.33 | 0 | 584735.83 | -584735.83 | 66185668.5714 | -0.8835% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-07-30 | 0 | 144257.88 | 0 | 728993.71 | -728993.71 | 66185668.5714 | -1.101% |  | 0 | 2017-07-31 | original |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-08-30 | 0 | 1573817.14 | 0 | 2302810.85 | -2302810.85 | 66185668.5714 | -3.479% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-09-30 | 0 | 34590.72 | 0 | 2337401.57 | -2337401.57 | 66185668.5714 | -3.532% |  | 3918482 | 2017-08-31 | original |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-10-30 | 0 | 877441.09 | 0 | 3214842.66 | -3214842.66 | 66185668.5714 | -4.857% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-11-30 | 0 | 450155.73 | 0 | 3664998.39 | -3664998.39 | 66185668.5714 | -5.537% |  | 4957067 | 2017-09-30 | original |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2018-12-30 | 0 | 1451075.87 | 0 | 5116074.26 | -5116074.26 | 66185668.5714 | -7.73% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Market | Army Forces
Fish Market | 2019-01-30 | 0 | 7267365.78 | 0 | 12383440.04 | -12383440.04 | 66185668.5714 | -18.71% |  | 8111601 | 2017-10-31 | original |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-02-28 | 50000000 | 4122879.37 | 50000000 | 16506319.41 | 33493680.59 | 66185668.5714 | 50.61% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-03-30 | 0 | 10376459.73 | 50000000 | 26882779.14 | 23117220.86 | 66185668.5714 | 34.93% |  | 10259672 | 2017-11-30 | original |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-04-30 | 0 | 5111401.43 | 50000000 | 31994180.57 | 18005819.43 | 66185668.5714 | 27.21% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-05-30 | 0 | 2586847.01 | 50000000 | 34581027.58 | 15418972.42 | 66185668.5714 | 23.3% |  | 10108224 | 2017-12-31 | original |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-06-30 | 0 | 793853.41 | 50000000 | 35374880.99 | 14625119.01 | 66185668.5714 | 22.1% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-07-30 | 0 | 513720.15 | 50000000 | 35888601.14 | 14111398.86 | 66185668.5714 | 21.32% |  |  | 2018-01-22 | added cash in 3 |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-08-30 | 0 | 268198.35 | 50000000 | 36156799.49 | 13843200.51 | 66185668.5714 | 20.92% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-09-30 | 0 | 1222005.98 | 50000000 | 37378805.47 | 12621194.53 | 66185668.5714 | 19.07% |  |  | 2018-02-28 | added cash in 3 |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-10-30 | 0 | 986480 | 50000000 | 38365285.47 | 11634714.53 | 66185668.5714 | 17.58% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-11-30 | 1511734 | 1078944.54 | 51511734 | 39444230.01 | 12067503.99 | 66185668.5714 | 18.23% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2019-12-30 | 9151350 | 2607532.15 | 60663084 | 42051762.16 | 18611321.84 | 66185668.5714 | 28.12% |  |  | 2018-04-12 | added cash in 3 |  |  |  | 2019 | Commercial | Market | Army Forces
Fish Market | 2020-01-30 | 0 | 24268.18 | 60663084 | 42076030.34 | 18587053.66 | 66185668.5714 | 28.08% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2020-02-28 | 0 | 772613.7 | 60663084 | 42848644.04 | 17814439.96 | 66185668.5714 | 26.92% |  |  | 2018-05-21 | added cash in 3 |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2020-03-30 | 0 | 123315 | 60663084 | 42971959.04 | 17691124.96 | 66185668.5714 | 26.73% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2020-06-30 | 0 | 1949 | 60663084 | 42973908.04 | 17689175.96 | 66185668.5714 | 26.73% |  |  | 2018-06-19 | added cash in 3 |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2020-07-30 | 0 | 10000 | 60663084 | 42983908.04 | 17679175.96 | 66185668.5714 | 26.71% |  |  | 2018-06-24 | added cash in 3 |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2020-08-30 | 0 | 124246.9 | 60663084 | 43108154.94 | 17554929.06 | 66185668.5714 | 26.52% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2020-09-30 | 0 | 42500 | 60663084 | 43150654.94 | 17512429.06 | 66185668.5714 | 26.46% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2020-12-30 | 0 | 2379.68 | 60663084 | 43153034.62 | 17510049.38 | 66185668.5714 | 26.46% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2020 | Commercial | Market | Army Forces
Fish Market | 2021-01-30 | 1715135 | 77359.28 | 62378219 | 43230393.9 | 19147825.1 | 66185668.5714 | 28.93% |  |  | 2018-08-28 | added cash in 3 |  |  |  | 2021 | Commercial | Market | Army Forces
Fish Market | 2021-02-28 | 0 | 309.82 | 62378219 | 43230703.72 | 19147515.28 | 66185668.5714 | 28.93% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Market | Army Forces
Fish Market | 2021-03-30 | 0 | 24040.51 | 62378219 | 43254744.23 | 19123474.77 | 66185668.5714 | 28.89% |  |  | 2018-09-23 | added cash in 3 |  |  |  | 2021 | Commercial | Market | Army Forces
Fish Market | 2021-04-30 | 0 | 744.81 | 62378219 | 43255489.04 | 19122729.96 | 66185668.5714 | 28.89% | [8 empty] | Commercial | Market | Army Forces
46 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Al Jazi Mall | 2018-02-28 | 0 | 33580 | 0 | 33580 | -33580 | 245977347.1316 | -0.01365% |  |  | 2018-10-31 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-04-30 | 0 | 879590.49 | 0 | 913170.49 | -913170.49 | 245977347.1316 | -0.3712% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-05-30 | 53125000 | 6418153.54 | 53125000 | 7331324.03 | 45793675.97 | 245977347.1316 | 18.62% |  |  | 2018-11-12 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-06-30 | 4529561 | 6945643.61 | 57654561 | 14276967.64 | 43377593.36 | 245977347.1316 | 17.63% |  |  | 2018-11-22 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-07-30 | 3357056.9 | 8005177.89 | 61011617.9 | 22282145.53 | 38729472.37 | 245977347.1316 | 15.75% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-08-30 | 7907102.36 | 9410409.92 | 68918720.26 | 31692555.45 | 37226164.81 | 245977347.1316 | 15.13% |  |  | 2018-12-17 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-09-30 | 6815580 | 9725084.65 | 75734300.26 | 41417640.1 | 34316660.16 | 245977347.1316 | 13.95% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-10-30 | 4138160 | 4957645.68 | 79872460.26 | 46375285.78 | 33497174.48 | 245977347.1316 | 13.62% |  |  | 2019-01-21 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-11-30 | 6905844.19 | 7625002.14 | 86778304.45 | 54000287.92 | 32778016.53 | 245977347.1316 | 13.33% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2018-12-30 | 1762571.78 | 5781447.47 | 88540876.23 | 59781735.39 | 28759140.84 | 245977347.1316 | 11.69% |  |  | 2019-02-12 | added cash in 3 |  |  |  | 2018 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-01-30 | 6141023.36 | 2532186.59 | 94681899.59 | 62313921.98 | 32367977.61 | 245977347.1316 | 13.16% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-02-28 | 3658448 | 4908781.94 | 98340347.59 | 67222703.92 | 31117643.67 | 245977347.1316 | 12.65% |  |  | 2019-03-14 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-03-30 | 2994292.79 | 3938080.58 | 101334640.38 | 71160784.5 | 30173855.88 | 245977347.1316 | 12.27% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-04-30 | 14666580.12 | 4935089.14 | 116001220.5 | 76095873.64 | 39905346.86 | 245977347.1316 | 16.22% |  |  | 2019-04-10 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-05-30 | 2842262.53 | 3541837.77 | 118843483.03 | 79637711.41 | 39205771.62 | 245977347.1316 | 15.94% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-06-30 | 3915066.37 | 2122276.3 | 122758549.4 | 81759987.71 | 40998561.69 | 245977347.1316 | 16.67% |  |  | 2019-05-21 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-07-30 | 2935343.72 | 2257979.27 | 125693893.12 | 84017966.98 | 41675926.14 | 245977347.1316 | 16.94% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-08-30 | 2748544.1 | 3202833.79 | 128442437.22 | 87220800.77 | 41221636.45 | 245977347.1316 | 16.76% |  |  | 2019-06-03 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-09-30 | 2360179.68 | 2109688.72 | 130802616.9 | 89330489.49 | 41472127.41 | 245977347.1316 | 16.86% |  |  | 2019-06-13 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-10-30 | 1471074.8 | 4595501.66 | 132273691.7 | 93925991.15 | 38347700.55 | 245977347.1316 | 15.59% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-11-30 | 1229643.5 | 2660378.13 | 133503335.2 | 96586369.28 | 36916965.92 | 245977347.1316 | 15.01% |  |  | 2019-07-22 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2019-12-30 | 0 | 9420238.52 | 133503335.2 | 106006607.8 | 27496727.4 | 245977347.1316 | 11.18% |  |  | 2019-07-29 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-01-30 | 0 | 3242358.09 | 133503335.2 | 109248965.89 | 24254369.31 | 245977347.1316 | 9.86% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-02-28 | 0 | 3812548.83 | 133503335.2 | 113061514.72 | 20441820.48 | 245977347.1316 | 8.31% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-03-30 | 0 | 1515151.74 | 133503335.2 | 114576666.46 | 18926668.74 | 245977347.1316 | 7.694% |  |  | 2019-09-19 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-04-30 | 0 | 518325.25 | 133503335.2 | 115094991.71 | 18408343.49 | 245977347.1316 | 7.484% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-05-30 | 0 | 347802.87 | 133503335.2 | 115442794.58 | 18060540.62 | 245977347.1316 | 7.342% |  |  | 2019-10-09 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-06-30 | 0 | 475479.26 | 133503335.2 | 115918273.84 | 17585061.36 | 245977347.1316 | 7.149% |  |  | 2019-10-15 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-07-30 | 0 | 256063.08 | 133503335.2 | 116174336.92 | 17328998.28 | 245977347.1316 | 7.045% |  |  | 2019-10-24 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-08-30 | 0 | 674445.56 | 133503335.2 | 116848782.48 | 16654552.72 | 245977347.1316 | 6.771% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-09-30 | 0 | 1989199.62 | 133503335.2 | 118837982.1 | 14665353.1 | 245977347.1316 | 5.962% |  |  | 2019-11-19 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-10-30 | 0 | 123662.95 | 133503335.2 | 118961645.05 | 14541690.15 | 245977347.1316 | 5.912% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-11-30 | 0 | 86833.84 | 133503335.2 | 119048478.89 | 14454856.31 | 245977347.1316 | 5.876% |  |  | 2019-12-25 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2020-12-30 | 0 | 32396.36 | 133503335.2 | 119080875.25 | 14422459.95 | 245977347.1316 | 5.863% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2021-01-30 | 0 | 40105.3 | 133503335.2 | 119120980.55 | 14382354.65 | 245977347.1316 | 5.847% |  |  | 2020-01-16 | added 1 |  |  |  | 2021 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2021-03-30 | 0 | 7548.34 | 133503335.2 | 119128528.89 | 14374806.31 | 245977347.1316 | 5.844% |  |  | 2020-01-27 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | YAMM
Al Jazi Mall | 2021-04-30 | 0 | 1518 | 133503335.2 | 119130046.89 | 14373288.31 | 245977347.1316 | 5.843% | [8 empty] | Commercial | Offices & Mall | YAMM
47 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Benban Aswan Alcazars Solar Park | 2018-05-30 | 0 | 117482.44 | 0 | 117482.44 | -117482.44 | 212005784 | -0.05541% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2018-06-30 | 0 | 1459920.17 | 0 | 1577402.61 | -1577402.61 | 212005784 | -0.744% |  |  | 2020-03-03 | added 1 |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2018-07-30 | 0 | 3284170.65 | 0 | 4861573.26 | -4861573.26 | 212005784 | -2.293% |  |  | 2020-03-17 | added 1 |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2018-08-30 | 24677038.56 | 6748136.25 | 24677038.56 | 11609709.51 | 13067329.05 | 212005784 | 6.164% |  |  | 2020-03-23 | added 1 |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2018-09-30 | 21842173.61 | 6263015.82 | 46519212.17 | 17872725.33 | 28646486.84 | 212005784 | 13.51% |  |  | 2020-03-31 | added 1 |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2018-10-30 | 25584164.76 | 19897186.42 | 72103376.93 | 37769911.75 | 34333465.18 | 212005784 | 16.19% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2018-11-30 | 0 | 11869356.24 | 72103376.93 | 49639267.99 | 22464108.94 | 212005784 | 10.6% |  |  | 2020-04-09 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2018-12-30 | 44325057.15 | 15040207.78 | 116428434.08 | 64679475.77 | 51748958.31 | 212005784 | 24.41% |  |  | 2020-04-26 | added cash in 3 |  |  |  | 2018 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-01-30 | 19094408.48 | 18705269.64 | 135522842.56 | 83384745.41 | 52138097.15 | 212005784 | 24.59% |  |  | 2020-04-29 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-02-28 | 49743000 | 6266630.35 | 185265842.56 | 89651375.76 | 95614466.8 | 212005784 | 45.1% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-03-30 | 0 | 13906045.82 | 185265842.56 | 103557421.58 | 81708420.98 | 212005784 | 38.54% |  |  | 2020-05-20 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-04-30 | 32489292.86 | 5890904.4 | 217755135.42 | 109448325.98 | 108306809.44 | 212005784 | 51.09% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-05-30 | 12448881.95 | 7794652.5 | 230204017.37 | 117242978.48 | 112961038.89 | 212005784 | 53.28% |  |  | 2020-06-10 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-06-30 | 4729770.2 | 5805417.25 | 234933787.57 | 123048395.73 | 111885391.84 | 212005784 | 52.77% |  |  | 2020-06-23 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-07-30 | 15885178.9 | 1924376.55 | 250818966.47 | 124972772.28 | 125846194.19 | 212005784 | 59.36% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-08-30 | 0 | 6633584.34 | 250818966.47 | 131606356.62 | 119212609.85 | 212005784 | 56.23% |  |  | 2020-07-09 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-09-30 | 0 | 314728.04 | 250818966.47 | 131921084.66 | 118897881.81 | 212005784 | 56.08% |  |  | 2020-07-29 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-10-30 | 0 | 4656703.09 | 250818966.47 | 136577787.75 | 114241178.72 | 212005784 | 53.89% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-11-30 | 0 | 872160.22 | 250818966.47 | 137449947.97 | 113369018.5 | 212005784 | 53.47% |  |  | 2020-08-19 | added cash in 3 |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2019-12-30 | 0 | 58599013.17 | 250818966.47 | 196048961.14 | 54770005.33 | 212005784 | 25.83% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-01-30 | 0 | 1450432.48 | 250818966.47 | 197499393.62 | 53319572.85 | 212005784 | 25.15% |  |  | 2020-09-20 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-02-28 | 0 | 154280.24 | 250818966.47 | 197653673.86 | 53165292.61 | 212005784 | 25.08% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-03-30 | 0 | 87268.19 | 250818966.47 | 197740942.05 | 53078024.42 | 212005784 | 25.04% |  |  | 2020-10-22 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-04-30 | 0 | 11512.8 | 250818966.47 | 197752454.85 | 53066511.62 | 212005784 | 25.03% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-06-30 | 0 | 45780.04 | 250818966.47 | 197798234.89 | 53020731.58 | 212005784 | 25.01% |  |  | 2020-11-24 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-07-30 | 0 | 99415 | 250818966.47 | 197897649.89 | 52921316.58 | 212005784 | 24.96% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-09-30 | 0 | 44141.23 | 250818966.47 | 197941791.12 | 52877175.35 | 212005784 | 24.94% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2020-12-30 | 0 | 462361.7 | 250818966.47 | 198404152.82 | 52414813.65 | 212005784 | 24.72% |  |  | 2021-01-06 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2021-01-30 | 0 | 166000 | 250818966.47 | 198570152.82 | 52248813.65 | 212005784 | 24.64% |  |  | 2021-01-21 | added cash in 3 |  |  |  | 2021 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2021-02-28 | 0 | 547231.36 | 250818966.47 | 199117384.18 | 51701582.29 | 212005784 | 24.39% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2021-03-30 | 0 | 90000.44 | 250818966.47 | 199207384.62 | 51611581.85 | 212005784 | 24.34% |  |  | 2021-02-09 | added cash in 3 |  |  |  | 2021 | Industrial | Power Plant | TSK
Benban Aswan Alcazars Solar Park | 2021-04-30 | 0 | 298298 | 250818966.47 | 199505682.62 | 51313283.85 | 212005784 | 24.2% | [8 empty] | Industrial | Power Plant | TSK
48 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Alameen Roads Earth Works | 2018-07-30 | 0 | 94383 | 0 | 94383 | -94383 | 54192857 | -0.1742% |  |  | 2021-03-18 | added cash in 3 |  |  |  | 2018 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2018-08-30 | 0 | 1240057.1 | 0 | 1334440.1 | -1334440.1 | [9 empty] | 2018 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2018-09-30 | 0 | 1450613.86 | 0 | 2785053.96 | -2785053.96 | 54192857 | -5.139% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2018-10-30 | 0 | 2241343.16 | 0 | 5026397.12 | -5026397.12 | 54192857 | -9.275% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2018-11-30 | 0 | 1768688.5 | 0 | 6795085.62 | -6795085.62 | 54192857 | -12.54% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2018-12-30 | 0 | 1432890.8 | 0 | 8227976.42 | -8227976.42 | 54192857 | -15.18% |  |  | 2018-01-04 | added cash in 3 |  |  |  | 2018 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-01-30 | 0 | 3278942.4 | 0 | 11506918.82 | -11506918.82 | 54192857 | -21.23% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-02-28 | 0 | 860413.09 | 0 | 12367331.91 | -12367331.91 | 54192857 | -22.82% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-03-30 | 0 | 2039662.53 | 0 | 14406994.44 | -14406994.44 | 54192857 | -26.58% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-04-30 | 0 | 2261071.33 | 0 | 16668065.77 | -16668065.77 | 54192857 | -30.76% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-05-30 | 0 | 1831122.24 | 0 | 18499188.01 | -18499188.01 | 54192857 | -34.14% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-06-30 | 0 | 1600554.87 | 0 | 20099742.88 | -20099742.88 | 54192857 | -37.09% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-07-30 | 15252683.5 | 2412249.46 | 15252683.5 | 22511992.34 | -7259308.84 | 54192857 | -13.4% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-08-30 | 0 | 1521819.27 | 15252683.5 | 24033811.61 | -8781128.11 | 54192857 | -16.2% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-09-30 | 1761540 | 2275723.1 | 17014223.5 | 26309534.71 | -9295311.21 | 54192857 | -17.15% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-10-30 | 11192562 | 2081868.68 | 28206785.5 | 28391403.39 | -184617.89 | [9 empty] | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-11-30 | 8403859 | 2184029.04 | 36610644.5 | 30575432.43 | 6035212.07 | 54192857 | 11.14% |  | 0 | 2017-07-31 | original |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2019-12-30 | 0 | 5009859.74 | 36610644.5 | 35585292.17 | 1025352.33 | 54192857 | 1.892% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-01-30 | 0 | 1760866.49 | 36610644.5 | 37346158.66 | -735514.16 | 54192857 | -1.357% |  | 0 | 2017-08-31 | original |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-02-28 | 0 | 1394896.15 | 36610644.5 | 38741054.81 | -2130410.31 | 54192857 | -3.931% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-03-30 | 0 | 1058790.85 | 36610644.5 | 39799845.66 | -3189201.16 | 54192857 | -5.885% |  | 3990887 | 2017-09-30 | original |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-04-30 | 6296976 | 59128.35 | 42907620.5 | 39858974.01 | 3048646.49 | 54192857 | 5.626% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-05-30 | 0 | 703925.82 | 42907620.5 | 40562899.83 | 2344720.67 | 54192857 | 4.327% |  | 3599516 | 2017-10-31 | original |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-06-30 | 1419727 | 479450.07 | 44327347.5 | 41042349.9 | 3284997.6 | 54192857 | 6.062% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-07-30 | 0 | 390250.99 | 44327347.5 | 41432600.89 | 2894746.61 | 54192857 | 5.342% |  | 1558907 | 2017-11-30 | original |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-08-30 | 5280204 | 650531.98 | 49607551.5 | 42083132.87 | 7524418.63 | 54192857 | 13.88% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-09-30 | 0 | 25140.9 | 49607551.5 | 42108273.77 | 7499277.73 | 54192857 | 13.84% |  | 3130756 | 2017-12-31 | original |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-10-30 | 0 | 1761.98 | 49607551.5 | 42110035.75 | 7497515.75 | 54192857 | 13.83% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2020-11-30 | 0 | 19340 | 49607551.5 | 42129375.75 | 7478175.75 | 54192857 | 13.8% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2021-01-30 | 0 | 1761.98 | 49607551.5 | 42131137.73 | 7476413.77 | 54192857 | 13.8% |  |  | 2018-02-21 | added cash in 3 |  |  |  | 2021 | Infrastructure | Roads | Army Forces
El Alameen Roads Earth Works | 2021-03-30 | 0 | 81 | 49607551.5 | 42131218.73 | 7476332.77 | 54192857 | 13.8% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Roads | Army Forces
49 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Sewedy Univeristy 2 phase 2 | 2019-11-30 | 31397824.8 | 6819992.36 | 31397824.8 | 6819992.36 | 24577832.44 | 262378822 | 9.367% |  |  | 2018-04-12 | added cash in 3 |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2019-12-30 | 0 | 6378760.03 | 31397824.8 | 13198752.39 | 18199072.41 | 262378822 | 6.936% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-01-30 | 16150645.07 | 11350643.25 | 47548469.87 | 24549395.64 | 22999074.23 | 262378822 | 8.766% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-02-29 | 17089175.4 | 8343038.66 | 64637645.27 | 32892434.3 | 31745210.97 | 262378822 | 12.1% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-03-30 | 101758035.71 | 11778131.55 | 166395680.98 | 44670565.85 | 121725115.13 | 262378822 | 46.39% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-04-30 | 2392694.8 | 19767993.36 | 168788375.78 | 64438559.21 | 104349816.57 | 262378822 | 39.77% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-05-30 | 13486571.37 | 21346890.25 | 182274947.15 | 85785449.46 | 96489497.69 | 262378822 | 36.77% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-06-30 | 45133657.09 | 29004240.72 | 227408604.24 | 114789690.18 | 112618914.06 | 262378822 | 42.92% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-07-30 | 64006362.98 | 63284411.02 | 291414967.22 | 178074101.2 | 113340866.02 | 262378822 | 43.2% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-08-30 | 10490817.12 | 5334273.03 | 301905784.34 | 183408374.23 | 118497410.11 | 262378822 | 45.16% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-09-30 | 79622075.16 | 42253061.29 | 381527859.5 | 225661435.52 | 155866423.98 | 262378822 | 59.41% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-10-30 | 0 | 26752963.95 | 381527859.5 | 252414399.47 | 129113460.03 | 262378822 | 49.21% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-11-30 | 30259740.65 | 22502774.82 | 411787600.15 | 274917174.29 | 136870425.86 | 262378822 | 52.17% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2020-12-30 | 7703511.41 | 26681402.47 | 419491111.56 | 301598576.76 | 117892534.8 | 262378822 | 44.93% | [8 empty] | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2021-01-30 | 13851401.63 | 16399722.59 | 433342513.19 | 317998299.35 | 115344213.84 | 262378822 | 43.96% |  |  | 2018-04-17 | added cash in 3 |  |  |  | 2021 | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2021-02-28 | 0 | 3456637.89 | 433342513.19 | 321454937.24 | 111887575.95 | 262378822 | 42.64% |  |  |  | cash out both |  |  |  | 2021 | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2021-03-30 | 0 | 12690200.68 | 433342513.19 | 334145137.92 | 99197375.27 | 262378822 | 37.81% |  |  | 2018-05-13 | added cash in 3 |  |  |  | 2021 | Commercial | University | Sewedy
El Sewedy Univeristy 2 phase 2 | 2021-04-30 | 23340124.9 | 740774.71 | 456682638.09 | 334885912.63 | 121796725.46 | 262378822 | 46.42% |  |  |  | cash out both |  |  |  | 2021 | Commercial | University | Sewedy
50 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Sokhna Tunnel L&L | 2018-07-30 | 0 | 67012.74 | 0 | 67012.74 | -67012.74 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2018-08-30 | 0 | 53660.37 | 0 | 120673.11 | -120673.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2018-09-30 | 0 | 2597 | 0 | 123270.11 | -123270.11 | 0 | #DIV/0! |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2018-10-30 | 0 | 750 | 0 | 124020.11 | -124020.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2019-01-30 | 0 | 1231.71 | 0 | 125251.82 | -125251.82 | 0 | #DIV/0! |  |  | 2018-09-17 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2019-02-28 | 0 | 12475.93 | 0 | 137727.75 | -137727.75 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2019-03-30 | 0 | 59250 | 0 | 196977.75 | -196977.75 | 0 | #DIV/0! |  |  | 2018-10-18 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2019-04-30 | 0 | 79215 | 0 | 276192.75 | -276192.75 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2019-05-30 | 0 | 3955 | 0 | 280147.75 | -280147.75 | 0 | #DIV/0! |  |  | 2018-11-06 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2019-09-30 | 0 | 1116.71 | 0 | 281264.46 | -281264.46 | 0 | #DIV/0! |  |  | 2018-11-27 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2019-11-30 | 0 | 1116.71 | 0 | 282381.17 | -282381.17 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2020-02-28 | 0 | 4504.49 | 0 | 286885.66 | -286885.66 | 0 | #DIV/0! |  |  | 2018-12-04 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2020-05-30 | 0 | 4504.49 | 0 | 291390.15 | -291390.15 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2020-06-30 | 0 | 54918.9 | 0 | 346309.05 | -346309.05 | 0 | #DIV/0! |  |  | 2019-01-03 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2020-07-30 | 0 | 1116 | 0 | 347425.05 | -347425.05 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2020-08-30 | 0 | 4504.49 | 0 | 351929.54 | -351929.54 | 0 | #DIV/0! |  |  | 2019-02-11 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Sokhna Tunnel L&L | 2021-01-30 | 454415 | 0 | 454415 | 351929.54 | 102485.46 | 0 | #DIV/0! |  |  | 2019-02-12 | added cash in 3 |  |  |  | 2021 | Infrastructure | L&L | Army Forces
51 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
R05 Residential District Z1 & Z2 | 2018-04-30 | 0 |  | 0 | 0 | 0 | 3200000000 | 0% |  |  | 2019-03-17 | added cash in 3 |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-05-30 | 0 |  | 0 | 0 | 0 | 3200000000 | 0% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-06-30 | 0 |  | 0 | 0 | 0 | 3200000000 | 0% |  |  | 2019-04-07 | added cash in 3 |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-07-30 | 0 |  | 0 | 0 | 0 | 3200000000 | 0% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-08-30 | 0 |  | 0 | 0 | 0 | 3200000000 | 0% |  |  | 2019-05-26 | added cash in 3 |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-09-30 | 100000000 | 1245853.3 | 100000000 | 1245853.3 | 98754146.7 | 3200000000 | 3.086% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-10-30 | 0 | 41124415.86 | 100000000 | 42370269.16 | 57629730.84 | 3200000000 | 1.801% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-11-30 | 13792500 | 4649175.4 | 113792500 | 47019444.56 | 66773055.44 | 3200000000 | 2.087% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2018-12-30 | 30000000 | 14645389.76 | 143792500 | 61664834.32 | 82127665.68 | 3200000000 | 2.566% |  |  |  | cash out both |  |  |  | 2018 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-01-30 | 50000000 | 31533742.4 | 193792500 | 93198576.72 | 100593923.28 | 3200000000 | 3.144% |  |  | 2019-09-05 | added cash in 3 |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-02-28 | 0 | 8687417.65 | 193792500 | 101885994.37 | 91906505.63 | 3200000000 | 2.872% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-03-30 | 66892573.08 | 12692212.55 | 260685073.08 | 114578206.92 | 146106866.16 | 3200000000 | 4.566% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-04-30 | 0 | 7712262.53 | 260685073.08 | 122290469.45 | 138394603.63 | 3200000000 | 4.325% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-05-30 | 4871486.85 | 11106831.15 | 265556559.93 | 133397300.6 | 132159259.33 | 3200000000 | 4.13% |  |  | 2019-12-25 | added cash in 3 |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-06-30 | 0 | 2192578.15 | 265556559.93 | 135589878.75 | 129966681.18 | 3200000000 | 4.061% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-07-30 | 0 | 20189956.92 | 265556559.93 | 155779835.67 | 109776724.26 | 3200000000 | 3.431% | [7 empty] | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-08-30 | 0 | 8560770.57 | 265556559.93 | 164340606.24 | 101215953.69 | 3200000000 | 3.163% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-09-30 | 0 | 6975277.24 | 265556559.93 | 171315883.48 | 94240676.45 | 3200000000 | 2.945% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-10-30 | 0 | 8884054.32 | 265556559.93 | 180199937.8 | 85356622.13 | 3200000000 | 2.667% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-11-30 | 46359242 | 15544868.83 | 311915801.93 | 195744806.63 | 116170995.3 | 3200000000 | 3.63% |  |  | 2019-11-20 | added cash in 3 |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2019-12-30 | 0 | 33350839.96 | 311915801.93 | 229095646.59 | 82820155.34 | 3200000000 | 2.588% |  |  |  | cash out both |  |  |  | 2019 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-01-30 | 0 | 21309533.92 | 311915801.93 | 250405180.51 | 61510621.42 | 3200000000 | 1.922% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-02-28 | 29830600.5 | 39627705.68 | 341746402.43 | 290032886.19 | 51713516.24 | 3200000000 | 1.616% |  |  | 2020-12-31 | added cash in 3 |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-03-30 | 22909628.3 | 14430127.07 | 364656030.73 | 304463013.26 | 60193017.47 | 3200000000 | 1.881% |  |  | 2021-01-24 | added cash in 3 |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-04-30 | 21628889.1 | 11216608.3 | 386284919.83 | 315679621.56 | 70605298.27 | 3200000000 | 2.206% | [7 empty] | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-05-30 | 82732842.1 | 13876921.58 | 469017761.93 | 329556543.14 | 139461218.79 | 3200000000 | 4.358% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-06-30 | 11413010.6 | 24514808.8 | 480430772.53 | 354071351.94 | 126359420.59 | 3200000000 | 3.949% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-07-30 | 69677448.01 | 24620530.92 | 550108220.54 | 378691882.86 | 171416337.68 | 3200000000 | 5.357% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-08-30 | 0 | 18431470.09 | 550108220.54 | 397123352.95 | 152984867.59 | 3200000000 | 4.781% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-09-30 | 174057872.05 | 30239520.27 | 724166092.59 | 427362873.22 | 296803219.37 | 3200000000 | 9.275% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-10-30 | 65491677.9 | 33257145.06 | 789657770.49 | 460620018.28 | 329037752.21 | 3200000000 | 10.28% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-11-30 | 126401082.85 | 27709040.96 | 916058853.34 | 488329059.24 | 427729794.1 | 3200000000 | 13.37% |  |  | 2018-04-29 | added cash in 3 |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2020-12-30 | 81139064.2 | 22678763.28 | 997197917.54 | 511007822.52 | 486190095.02 | 3200000000 | 15.19% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2021-01-30 | 19661149.99 | 39104527.14 | 1016859067.53 | 550112349.66 | 466746717.87 | 3200000000 | 14.59% |  |  | 2018-05-15 | added cash in 3 |  |  |  | 2021 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2021-02-28 | 35087867.22 | 29088725.58 | 1051946934.75 | 579201075.24 | 472745859.51 | 3200000000 | 14.77% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2021-03-30 | 47620910.4 | 14268085.78 | 1099567845.15 | 593469161.02 | 506098684.13 | 3200000000 | 15.82% |  |  | 2018-06-20 | added cash in 3 |  |  |  | 2021 | Residential | Residential | Utilities And Urban Communities
R05 Residential District Z1 & Z2 | 2021-04-30 | 0 | 13218349.88 | 1099567845.15 | 606687510.9 | 492880334.25 | 3200000000 | 15.4% | [8 empty] | Residential | Residential | Utilities And Urban Communities
52 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Abu Sultan Bridge 02 Greenhouse | 2018-07-30 | 0 | 180000 | 0 | 180000 | -180000 | 67755600 | -0.2657% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2018-08-30 | 0 | 120625 | 0 | 300625 | -300625 | 67755600 | -0.4437% |  |  | 2018-08-28 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2018-09-30 | 0 | 221545 | 0 | 522170 | -522170 | 67755600 | -0.7707% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2018-10-30 | 0 | 604540.2 | 0 | 1126710.2 | -1126710.2 | 67755600 | -1.663% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2018-11-30 | 0 | 2176076.76 | 0 | 3302786.96 | -3302786.96 | 67755600 | -4.875% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2018-12-30 | 0 | 2412694.59 | 0 | 5715481.55 | -5715481.55 | 67755600 | -8.435% |  |  | 2018-11-12 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-01-30 | 1120156.35 | 2444710.54 | 1120156.35 | 8160192.09 | -7040035.74 | 67755600 | -10.39% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-02-28 | 0 | 2540959.22 | 1120156.35 | 10701151.31 | -9580994.96 | 67755600 | -14.14% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-03-30 | 0 | 3521770.18 | 1120156.35 | 14222921.49 | -13102765.14 | 67755600 | -19.34% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-04-30 | 0 | 1356068.35 | 1120156.35 | 15578989.84 | -14458833.49 | 67755600 | -21.34% |  |  | 2019-02-07 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-05-30 | 0 | 980908.48 | 1120156.35 | 16559898.32 | -15439741.97 | 67755600 | -22.79% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-06-30 | 35118543.35 | 214990.45 | 36238699.7 | 16774888.77 | 19463810.93 | 67755600 | 28.73% |  |  | 2019-03-04 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-07-30 | 9912927 | 944483.45 | 46151626.7 | 17719372.22 | 28432254.48 | 67755600 | 41.96% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-08-30 | 0 | 576975.95 | 46151626.7 | 18296348.17 | 27855278.53 | 67755600 | 41.11% |  |  | 2019-04-10 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-09-30 | 8607544 | 230366.77 | 54759170.7 | 18526714.94 | 36232455.76 | 67755600 | 53.48% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-10-30 | 0 | 163352.25 | 54759170.7 | 18690067.19 | 36069103.51 | 67755600 | 53.23% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-11-30 | 0 | 3387.78 | 54759170.7 | 18693454.97 | 36065715.73 | 67755600 | 53.23% |  |  | 2019-06-12 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2019-12-30 | 0 | 3263663.74 | 54759170.7 | 21957118.71 | 32802051.99 | 67755600 | 48.41% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2020-02-28 | 0 | 2019.51 | 54759170.7 | 21959138.22 | 32800032.48 | 67755600 | 48.41% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abu Sultan Bridge 02 Greenhouse | 2021-02-28 | 3830495 | 0 | 58589665.7 | 21959138.22 | 36630527.48 | 67755600 | 54.06% |  |  | 2019-08-08 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
53 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Sokhna Tunnel 02 | 2018-08-30 | 0 | 215295 | 0 | 215295 | -215295 | 22334150 | -0.964% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2018-09-30 | 0 | 74228.99 | 0 | 289523.99 | -289523.99 | 22334150 | -1.296% |  |  | 2019-10-27 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2018-10-30 | 0 | 1079959.14 | 0 | 1369483.13 | -1369483.13 | 22334150 | -6.132% |  |  | 2019-10-30 | added cash in 3 |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2018-11-30 | 0 | 1654571.72 | 0 | 3024054.85 | -3024054.85 | 22334150 | -13.54% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2018-12-30 | 0 | 789569.3 | 0 | 3813624.15 | -3813624.15 | 22334150 | -17.08% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-01-30 | 0 | 964202.24 | 0 | 4777826.39 | -4777826.39 | 22334150 | -21.39% |  |  | 2019-12-31 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-02-28 | 0 | 595096.08 | 0 | 5372922.47 | -5372922.47 | 22334150 | -24.06% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-03-30 | 0 | 556442.53 | 0 | 5929365 | -5929365 | 22334150 | -26.55% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-04-30 | 0 | 104032.14 | 0 | 6033397.14 | -6033397.14 | 22334150 | -27.01% |  |  | 2020-02-17 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-05-30 | 0 | 693999.44 | 0 | 6727396.58 | -6727396.58 | 22334150 | -30.12% |  |  | 2020-02-18 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-06-30 | 8760181.4 | 3378.96 | 8760181.4 | 6730775.54 | 2029405.86 | 22334150 | 9.087% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-07-30 | 0 | 367040.25 | 8760181.4 | 7097815.79 | 1662365.61 | 22334150 | 7.443% |  |  | 2020-03-10 | added 1 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-09-30 | 2166937 | 52513.44 | 10927118.4 | 7150329.23 | 3776789.17 | 22334150 | 16.91% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-10-30 | 0 | 16772.72 | 10927118.4 | 7167101.95 | 3760016.45 | 22334150 | 16.84% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-11-30 | 666877 | 0 | 11593995.4 | 7167101.95 | 4426893.45 | 22334150 | 19.82% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2019-12-30 | 0 | 1197331.1 | 11593995.4 | 8364433.05 | 3229562.35 | 22334150 | 14.46% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2020-08-30 | 0 | 7108.4 | 11593995.4 | 8371541.45 | 3222453.95 | 22334150 | 14.43% |  |  | 2020-07-09 | added 1 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2020-11-30 | 0 | 7108.4 | 11593995.4 | 8378649.85 | 3215345.55 | 22334150 | 14.4% |  |  | 2020-07-12 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Sokhna Tunnel 02 | 2021-02-28 | 0 | 873726.7 | 11593995.4 | 9252376.55 | 2341618.85 | 22334150 | 10.48% | [8 empty] | Infrastructure | Bridges & Tunnels | Army Forces
54 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Awsty Middle Tunnel L&L | 2018-10-30 | 0 | 17805 | 0 | 17805 | -17805 | 1024820 | -1.737% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Awsty Middle Tunnel L&L | 2018-11-30 | 0 | 68698.63 | 0 | 86503.63 | -86503.63 | 1024820 | -8.441% |  |  | 2020-09-09 | added 1 |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Awsty Middle Tunnel L&L | 2018-12-30 | 0 | 10425 | 0 | 96928.63 | -96928.63 | 1024820 | -9.458% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2018 | Infrastructure | L&L | Army Forces
El Awsty Middle Tunnel L&L | 2019-01-30 | 0 | 25262 | 0 | 122190.63 | -122190.63 | 1024820 | -11.92% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Awsty Middle Tunnel L&L | 2019-04-30 | 0 | 20855 | 0 | 143045.63 | -143045.63 | 1024820 | -13.96% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Awsty Middle Tunnel L&L | 2019-05-30 | 0 | 30737 | 0 | 173782.63 | -173782.63 | 1024820 | -16.96% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Awsty Middle Tunnel L&L | 2019-12-30 | 0 | 17506.21 | 0 | 191288.84 | -191288.84 | 1024820 | -18.67% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Awsty Middle Tunnel L&L | 2020-12-30 | 677590 | 0 | 677590 | 191288.84 | 486301.16 | 1024820 | 47.45% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
55 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sodic Eastown EDNC | 2018-11-30 | 0 | 496500 | 0 | 496500 | -496500 | 1074545067 | -0.04621% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2018-12-30 | 122000000 | 37731.56 | 122000000 | 534231.56 | 121465768.44 | 1074545067 | 11.3% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-01-30 | 0 | 200957.34 | 122000000 | 735188.9 | 121264811.1 | 1074545067 | 11.29% |  | 0 | 2017-08-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-02-28 | 0 | 5716029.96 | 122000000 | 6451218.86 | 115548781.14 | 1074545067 | 10.75% |  | 17022109 | 2017-09-30 | original |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-03-30 | 0 | 14981771.08 | 122000000 | 21432989.94 | 100567010.06 | 1074545067 | 9.359% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-04-30 | 6789620.12 | 14415072.39 | 128789620.12 | 35848062.33 | 92941557.79 | 1074545067 | 8.649% |  | 54045554 | 2017-10-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-05-30 | 15638373.66 | 17545595.44 | 144427993.78 | 53393657.77 | 91034336.01 | 1074545067 | 8.472% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-06-30 | 0 | 14513172.01 | 144427993.78 | 67906829.78 | 76521164 | 1074545067 | 7.121% |  | 68968025 | 2017-11-30 | original |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-07-30 | 28111452.48 | 42043691.46 | 172539446.26 | 109950521.24 | 62588925.02 | 1074545067 | 5.825% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-08-30 | 37056568.4 | 36555367.52 | 209596014.66 | 146505888.76 | 63090125.9 | 1074545067 | 5.871% |  | 45198075 | 2017-12-31 | original |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-09-30 | 18000000 | 22974102.1 | 227596014.66 | 169479990.86 | 58116023.8 | 1074545067 | 5.408% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-10-30 | 10614412.99 | 52148786.35 | 238210427.65 | 221628777.21 | 16581650.44 | 1074545067 | 1.543% |  |  | 2018-01-09 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-11-30 | 38197130.95 | 41059341.61 | 276407558.6 | 262688118.82 | 13719439.78 | 1074545067 | 1.277% |  |  | 2018-01-15 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2019-12-30 | 99591869.99 | 35916639.7 | 375999428.59 | 298604758.52 | 77394670.07 | 1074545067 | 7.203% |  |  | 2018-01-18 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-01-30 | 0 | 35985916.6 | 375999428.59 | 334590675.12 | 41408753.47 | 1074545067 | 3.854% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-02-28 | 33864826.79 | 24089446.28 | 409864255.38 | 358680121.4 | 51184133.98 | 1074545067 | 4.763% |  |  | 2018-02-11 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-03-30 | 51941807.03 | 15079838.43 | 461806062.41 | 373759959.83 | 88046102.58 | 1074545067 | 8.194% |  |  | 2018-02-15 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-04-30 | 0 | 5709072.59 | 461806062.41 | 379469032.42 | 82337029.99 | 1074545067 | 7.663% |  |  | 2018-02-19 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-05-30 | 22129702 | 17860266.56 | 483935764.41 | 397329298.98 | 86606465.43 | 1074545067 | 8.06% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-06-30 | 15000000 | 22096035.81 | 498935764.41 | 419425334.79 | 79510429.62 | 1074545067 | 7.399% |  |  | 2018-03-13 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-07-30 | 12895954 | 23893101.81 | 511831718.41 | 443318436.6 | 68513281.81 | 1074545067 | 6.376% |  |  | 2018-03-14 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-08-30 | 33484691.66 | 20400288.06 | 545316410.07 | 463718724.66 | 81597685.41 | 1074545067 | 7.594% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-09-30 | 38976341.06 | 29856014.31 | 584292751.13 | 493574738.97 | 90718012.16 | 1074545067 | 8.442% |  |  | 2018-04-16 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-10-30 | 7406610.78 | 23473520.22 | 591699361.91 | 517048259.19 | 74651102.72 | 1074545067 | 6.947% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-11-30 | 62280150 | 31194663.36 | 653979511.91 | 548242922.55 | 105736589.36 | 1074545067 | 9.84% |  |  | 2018-05-15 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2020-12-30 | 29197031.83 | 32209765.4 | 683176543.74 | 580452687.95 | 102723855.79 | 1074545067 | 9.56% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2021-01-30 | 0 | 36263541.01 | 683176543.74 | 616716228.96 | 66460314.78 | 1074545067 | 6.185% |  |  | 2018-06-13 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2021-02-28 | 19743783.32 | 26912717.7 | 702920327.06 | 643628946.66 | 59291380.4 | 1074545067 | 5.518% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2021-03-30 | 27060285.09 | 28256186.4 | 729980612.15 | 671885133.06 | 58095479.09 | 1074545067 | 5.407% |  |  | 2018-07-12 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | SODIC
Sodic Eastown EDNC | 2021-04-30 | 12000000 | 26679197 | 741980612.15 | 698564330.06 | 43416282.09 | 1074545067 | 4.04% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | SODIC
56 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Marassi Civic Center Pkg 144 | 2018-12-30 | 24600000 | 768848.02 | 24600000 | 768848.02 | 23831151.98 | 176420375 | 13.51% |  |  |  | cash out both |  |  |  | 2018 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-01-30 | 0 | 14944297.11 | 24600000 | 15713145.13 | 8886854.87 | 176420375 | 5.037% |  |  | 2018-09-18 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-02-28 | 2532120.6 | 10205548.06 | 27132120.6 | 25918693.19 | 1213427.41 | 176420375 | 0.6878% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-03-30 | 35428884.75 | 15866046.55 | 62561005.35 | 41784739.74 | 20776265.61 | 176420375 | 11.78% |  |  | 2018-10-18 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-04-30 | 0 | 13359565.12 | 62561005.35 | 55144304.86 | 7416700.49 | 176420375 | 4.204% |  |  | 2018-10-28 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-05-30 | 31166066.2 | 18380053.23 | 93727071.55 | 73524358.09 | 20202713.46 | 176420375 | 11.45% |  |  | 2018-10-29 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-06-30 | 11074114.43 | 9275864.62 | 104801185.98 | 82800222.71 | 22000963.27 | 176420375 | 12.47% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-07-30 | 7386054.95 | 7248897.82 | 112187240.93 | 90049120.53 | 22138120.4 | 176420375 | 12.55% |  |  | 2018-11-22 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-08-30 | 0 | 10432654.92 | 112187240.93 | 100481775.45 | 11705465.48 | 176420375 | 6.635% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-09-30 | 0 | 1936980.78 | 112187240.93 | 102418756.23 | 9768484.7 | 176420375 | 5.537% |  |  | 2018-12-23 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-10-30 | 20942586.35 | 3568247.4 | 133129827.28 | 105987003.63 | 27142823.65 | 176420375 | 15.39% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-11-30 | 0 | 1814760.87 | 133129827.28 | 107801764.5 | 25328062.78 | 176420375 | 14.36% |  |  | 2019-01-15 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2019-12-30 | 0 | 56564764.01 | 133129827.28 | 164366528.51 | -31236701.23 | 176420375 | -17.71% |  |  | 2019-01-30 | added cash in 3 |  |  |  | 2019 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-01-30 | 22336480.74 | 1230549.33 | 155466308.02 | 165597077.84 | -10130769.82 | 176420375 | -5.742% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-02-28 | 0 | 2172252.68 | 155466308.02 | 167769330.52 | -12303022.5 | 176420375 | -6.974% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-03-30 | 11604075.76 | 1461175.27 | 167070383.78 | 169230505.79 | -2160122.01 | 176420375 | -1.224% |  |  | 2019-03-07 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-04-30 | 596740.76 | 306967.18 | 167667124.54 | 169537472.97 | -1870348.43 | 176420375 | -1.06% |  |  | 2019-03-11 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-05-30 | 0 | 1259466.53 | 167667124.54 | 170796939.5 | -3129814.96 | 176420375 | -1.774% |  |  | 2019-03-20 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-06-30 | 0 | 1078335.43 | 167667124.54 | 171875274.93 | -4208150.39 | 176420375 | -2.385% |  |  | 2019-03-27 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-07-30 | 0 | 1137069.85 | 167667124.54 | 173012344.78 | -5345220.24 | 176420375 | -3.03% |  |  | 2019-03-28 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-08-30 | 0 | 959078.26 | 167667124.54 | 173971423.04 | -6304298.5 | 176420375 | -3.573% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-09-30 | 342218.65 | 87312.56 | 168009343.19 | 174058735.6 | -6049392.41 | 176420375 | -3.429% |  |  | 2019-04-02 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-10-30 | 0 | 675261.54 | 168009343.19 | 174733997.14 | -6724653.95 | 176420375 | -3.812% |  |  | 2019-04-11 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-11-30 | 0 | 318165.1 | 168009343.19 | 175052162.24 | -7042819.05 | 176420375 | -3.992% |  |  | 2019-04-21 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2020-12-30 | 0 | 108188.81 | 168009343.19 | 175160351.05 | -7151007.86 | 176420375 | -4.053% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2021-01-30 | 0 | 343308.89 | 168009343.19 | 175503659.94 | -7494316.75 | 176420375 | -4.248% |  |  | 2019-05-16 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2021-02-28 | 9960243.27 | 67550 | 177969586.46 | 175571209.94 | 2398376.52 | 176420375 | 1.359% |  |  | 2019-05-31 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2021-03-30 | 0 | 1154597.55 | 177969586.46 | 176725807.49 | 1243778.97 | 176420375 | 0.705% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | EMAAR
Marassi Civic Center Pkg 144 | 2021-04-30 | 0 | 4603.3 | 177969586.46 | 176730410.79 | 1239175.67 | 176420375 | 0.7024% | [8 empty] | Commercial | Offices & Mall | EMAAR
57 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
DPW Sokhna Dubai Port | 2018-11-30 | 0 | 6250 | 0 | 6250 | -6250 | 1633315425 | -0.0003827% |  |  |  | cash out both |  |  |  | 2018 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2018-12-30 | 0 | 1558519.47 | 0 | 1564769.47 | -1564769.47 | 1633315425 | -0.0958% |  |  | 2019-07-03 | added cash in 3 |  |  |  | 2018 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-01-30 | 241563831.8 | 2323205.22 | 241563831.8 | 3887974.69 | 237675857.11 | 1633315425 | 14.55% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-02-28 | 0 | 1852353.85 | 241563831.8 | 5740328.54 | 235823503.26 | 1633315425 | 14.44% |  |  | 2019-08-05 | added cash in 3 |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-03-30 | 15998139 | 16988320.32 | 257561970.8 | 22728648.86 | 234833321.94 | 1633315425 | 14.38% |  |  | 2019-08-26 | added cash in 3 |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-04-30 | 18062199.23 | 13328512.56 | 275624170.03 | 36057161.42 | 239567008.61 | 1633315425 | 14.67% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-05-30 | 15357944.03 | 7139997.48 | 290982114.06 | 43197158.9 | 247784955.16 | 1633315425 | 15.17% |  |  | 2019-09-05 | added cash in 3 |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-06-30 | 0 | 12788642.54 | 290982114.06 | 55985801.44 | 234996312.62 | 1633315425 | 14.39% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-07-30 | 27940477.28 | 29860309.8 | 318922591.34 | 85846111.24 | 233076480.1 | 1633315425 | 14.27% |  |  | 2019-10-09 | added cash in 3 |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-08-30 | 13161622.85 | 20283046.55 | 332084214.19 | 106129157.79 | 225955056.4 | 1633315425 | 13.83% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-09-30 | 24492163.72 | 32756019.93 | 356576377.91 | 138885177.72 | 217691200.19 | 1633315425 | 13.33% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-10-30 | 59103658.14 | 56277541.42 | 415680036.05 | 195162719.14 | 220517316.91 | 1633315425 | 13.5% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-11-30 | 0 | 61285300.84 | 415680036.05 | 256448019.98 | 159232016.07 | 1633315425 | 9.749% |  |  | 2020-01-16 | added cash in 3 |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2019-12-30 | 40031882.73 | 84722506.57 | 455711918.78 | 341170526.55 | 114541392.23 | 1633315425 | 7.013% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-01-30 | 142488821.63 | 64410602 | 598200740.41 | 405581128.55 | 192619611.86 | 1633315425 | 11.79% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-02-28 | 0 | 61463827.12 | 598200740.41 | 467044955.67 | 131155784.74 | 1633315425 | 8.03% |  |  | 2020-03-23 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-03-30 | 109675422.28 | 59590833.37 | 707876162.69 | 526635789.04 | 181240373.65 | 1633315425 | 11.1% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-04-30 | 46089743 | 30284914.25 | 753965905.69 | 556920703.29 | 197045202.4 | 1633315425 | 12.06% |  |  | 2020-04-09 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-05-30 | 98279035.94 | 56700638.34 | 852244941.63 | 613621341.63 | 238623600 | 1633315425 | 14.61% |  |  | 2020-04-13 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-06-30 | 134129590.95 | 86326921.01 | 986374532.58 | 699948262.64 | 286426269.94 | 1633315425 | 17.54% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-07-30 | 63998840.71 | 43160587.28 | 1050373373.29 | 743108849.92 | 307264523.37 | 1633315425 | 18.81% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-08-30 | 41776446.85 | 18603231.7 | 1092149820.14 | 761712081.62 | 330437738.52 | 1633315425 | 20.23% |  |  | 2020-06-21 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-09-30 | 44310014.32 | 51830400.92 | 1136459834.46 | 813542482.54 | 322917351.92 | 1633315425 | 19.77% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-10-30 | 25431108.58 | 20585636.71 | 1161890943.04 | 834128119.25 | 327762823.79 | 1633315425 | 20.07% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-11-30 | 31817254.2 | 28770207.61 | 1193708197.24 | 862898326.86 | 330809870.38 | 1633315425 | 20.25% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2020-12-30 | 25746407.39 | 32212781.2 | 1219454604.63 | 895111108.06 | 324343496.57 | 1633315425 | 19.86% |  |  | 2020-12-17 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2021-01-30 | 17720371.71 | 26148810.21 | 1237174976.34 | 921259918.27 | 315915058.07 | 1633315425 | 19.34% |  |  | 2021-03-31 | added cash in 3 |  |  |  | 2021 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2021-02-28 | 26545255.12 | 20790764.3 | 1263720231.46 | 942050682.57 | 321669548.89 | [9 empty] | 2021 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2021-03-30 | 20867275.72 | 14947124.83 | 1284587507.18 | 956997807.4 | 327589699.78 | 1633315425 | 20.06% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Networks | DPW
DPW Sokhna Dubai Port | 2021-04-30 | 10313601.64 | 19338611.04 | 1294901108.82 | 976336418.44 | 318564690.38 | 1633315425 | 19.5% |  | 5921350 | 2017-09-30 | original |  |  |  | 2021 | Infrastructure | Networks | DPW
58 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Slope Stablization PKG 101 | 2018-12-30 | 24600000 | 48446.71 | 24600000 | 48446.71 | 24551553.29 | 52028085.7143 | 47.19% |  | 0 | 2017-10-31 | original |  |  |  | 2018 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-01-30 | 0 | 1037572.3 | 24600000 | 1086019.01 | 23513980.99 | 52028085.7143 | 45.19% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-02-28 | 2532120.6 | 696376.21 | 27132120.6 | 1782395.22 | 25349725.38 | 52028085.7143 | 48.72% |  | 1369484 | 2017-11-30 | original |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-03-30 | 35428884.75 | 1325727.57 | 62561005.35 | 3108122.79 | 59452882.56 | 52028085.7143 | 114.3% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-04-30 | 0 | 1705310.36 | 62561005.35 | 4813433.15 | 57747572.2 | 52028085.7143 | 111% |  | 0 | 2017-12-31 | original |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-05-30 | 31166066.2 | 2051607.17 | 93727071.55 | 6865040.32 | 86862031.23 | 52028085.7143 | 167% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-06-30 | 11074114.43 | 1413088.72 | 104801185.98 | 8278129.04 | 96523056.94 | 52028085.7143 | 185.5% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-07-30 | 7386054.95 | 1252532.38 | 112187240.93 | 9530661.42 | 102656579.51 | 52028085.7143 | 197.3% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-08-30 | 0 | 1801484.02 | 112187240.93 | 11332145.44 | 100855095.49 | 52028085.7143 | 193.8% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-09-30 | 0 | 1240508.94 | 112187240.93 | 12572654.38 | 99614586.55 | 52028085.7143 | 191.5% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-10-30 | 20942586.35 | 2243161.77 | 133129827.28 | 14815816.15 | 118314011.13 | 52028085.7143 | 227.4% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-11-30 | 0 | 1399641.5 | 133129827.28 | 16215457.65 | 116914369.63 | 52028085.7143 | 224.7% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2019-12-30 | 0 | 3511320.37 | 133129827.28 | 19726778.02 | 113403049.26 | 52028085.7143 | 218% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-01-30 | 22336480.74 | 876489.71 | 155466308.02 | 20603267.73 | 134863040.29 | 52028085.7143 | 259.2% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-02-28 | 0 | 1300356.68 | 155466308.02 | 21903624.41 | 133562683.61 | 52028085.7143 | 256.7% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-03-30 | 1430834.93 | 677357.53 | 156897142.95 | 22580981.94 | 134316161.01 | 52028085.7143 | 258.2% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-04-30 | 0 | 797488.27 | 156897142.95 | 23378470.21 | 133518672.74 | 52028085.7143 | 256.6% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-05-30 | 0 | 1451291.03 | 156897142.95 | 24829761.24 | 132067381.71 | 52028085.7143 | 253.8% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-06-30 | 0 | 268243.77 | 156897142.95 | 25098005.01 | 131799137.94 | 52028085.7143 | 253.3% |  |  | 2019-02-11 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-07-30 | 0 | 575024.75 | 156897142.95 | 25673029.76 | 131224113.19 | 52028085.7143 | 252.2% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-08-30 | 0 | 565202.11 | 156897142.95 | 26238231.87 | 130658911.08 | 52028085.7143 | 251.1% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-09-30 | 0 | 268521.56 | 156897142.95 | 26506753.43 | 130390389.52 | 52028085.7143 | 250.6% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-10-30 | 0 | 2087960.39 | 156897142.95 | 28594713.82 | 128302429.13 | 52028085.7143 | 246.6% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-11-30 | 0 | 692636.56 | 156897142.95 | 29287350.38 | 127609792.57 | 52028085.7143 | 245.3% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2020-12-30 | 0 | 599150.03 | 156897142.95 | 29886500.41 | 127010642.54 | 52028085.7143 | 244.1% |  |  | 2019-07-31 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2021-01-30 | 0 | 877628.44 | 156897142.95 | 30764128.85 | 126133014.1 | 52028085.7143 | 242.4% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2021-02-28 | 0 | 107706.62 | 156897142.95 | 30871835.47 | 126025307.48 | 52028085.7143 | 242.2% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2021-03-30 | 0 | 418586.83 | 156897142.95 | 31290422.3 | 125606720.65 | 52028085.7143 | 241.4% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | EMAAR
Slope Stablization PKG 101 | 2021-04-30 | 0 | 312178.39 | 156897142.95 | 31602600.69 | 125294542.26 | 52028085.7143 | 240.8% | [8 empty] | Infrastructure | L&L | EMAAR
59 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Elco Steel Substation | 2018-07-30 |  | 0 | 0 | 0 | 0 | 32341773 | 0% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2018-09-30 |  | 0 | 0 | 0 | 0 | 32341773 | 0% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2018-10-30 |  | 0 | 0 | 0 | 0 | 32341773 | 0% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2018-12-30 | 24600000 | 0 | 24600000 | 0 | 24600000 | 32341773 | 76.06% |  |  |  | cash out both |  |  |  | 2018 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-01-30 |  | 3179.66 | 24600000 | 3179.66 | 24596820.34 | 32341773 | 76.05% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-02-28 | 2532120.6 | 328500 | 27132120.6 | 331679.66 | 26800440.94 | 32341773 | 82.87% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-03-30 | 35428884.75 | 594594.84 | 62561005.35 | 926274.5 | 61634730.85 | 32341773 | 190.6% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-04-30 |  | 231187.27 | 62561005.35 | 1157461.77 | 61403543.58 | 32341773 | 189.9% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-05-30 | 31166066.2 | 481662.53 | 93727071.55 | 1639124.3 | 92087947.25 | 32341773 | 284.7% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-06-30 | 11074114.43 | 26135.55 | 104801185.98 | 1665259.85 | 103135926.13 | 32341773 | 318.9% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-07-30 | 7386054.95 | 316636.41 | 112187240.93 | 1981896.26 | 110205344.67 | 32341773 | 340.8% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-08-30 |  | 269362.72 | 112187240.93 | 2251258.98 | 109935981.95 | 32341773 | 339.9% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-09-30 |  | 95862.86 | 112187240.93 | 2347121.84 | 109840119.09 | 32341773 | 339.6% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-10-30 | 4748411.06 | 45830.78 | 116935651.99 | 2392952.62 | 114542699.37 | [9 empty] | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-11-30 |  | 107215.22 | 116935651.99 | 2500167.84 | 114435484.15 | 32341773 | 353.8% |  | 0 | 2017-10-31 | original |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2019-12-30 |  | 280394.73 | 116935651.99 | 2780562.57 | 114155089.42 | 32341773 | 353% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2020-02-28 |  | 3430.5 | 116935651.99 | 2783993.07 | 114151658.92 | 32341773 | 353% |  | 0 | 2017-11-30 | original |  |  |  | 2020 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2020-03-30 |  | 11272.85 | 116935651.99 | 2795265.92 | 114140386.07 | 32341773 | 352.9% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2020-04-30 |  | 61562.5 | 116935651.99 | 2856828.42 | 114078823.57 | 32341773 | 352.7% |  | 0 | 2017-12-31 | original |  |  |  | 2020 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2020-06-30 |  | 2311.58 | 116935651.99 | 2859140 | 114076511.99 | 32341773 | 352.7% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | Elco Suez
Elco Steel Substation | 2020-09-30 |  | 12804.39 | 116935651.99 | 2871944.39 | 114063707.6 | 32341773 | 352.7% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | Elco Suez
60 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sewab Greenhouse Tunnel | 2019-07-30 | 0 | 583.1 | 0 | 583.1 | -583.1 | 10957813.825 | -0.005321% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Sewab Greenhouse Tunnel | 2019-09-30 | 0 | 2700 | 0 | 3283.1 | -3283.1 | 10957813.825 | -0.02996% |  |  | 2018-04-12 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Sewab Greenhouse Tunnel | 2021-02-28 | 3830500 | 0 | 3830500 | 3283.1 | 3827216.9 | 10957813.825 | 34.93% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
61 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Mivida Irrigation Treatment Plant Pkg 140 | 2019-01-30 | 0 | 56000 | 0 | 56000 | -56000 | 170057475.6641 | -0.03293% |  |  | 2018-05-31 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-02-28 | 15567604.3 | 211876.6 | 15567604.3 | 267876.6 | 15299727.7 | 170057475.6641 | 8.997% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-03-30 | 0 | 334489.19 | 15567604.3 | 602365.79 | 14965238.51 | 170057475.6641 | 8.8% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-04-30 | 0 | 313433.85 | 15567604.3 | 915799.64 | 14651804.66 | 170057475.6641 | 8.616% |  |  | 2018-06-28 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-05-30 | 0 | 6557727.1 | 15567604.3 | 7473526.74 | 8094077.56 | 170057475.6641 | 4.76% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-06-30 | 7313962.6 | 509544.35 | 22881566.9 | 7983071.09 | 14898495.81 | 170057475.6641 | 8.761% |  |  | 2018-07-31 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-07-30 | 2533668.03 | 2706618.74 | 25415234.93 | 10689689.83 | 14725545.1 | 170057475.6641 | 8.659% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-08-30 | 2620895.13 | 8288612.73 | 28036130.06 | 18978302.56 | 9057827.5 | 170057475.6641 | 5.326% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-09-30 | 0 | 2281984.71 | 28036130.06 | 21260287.27 | 6775842.79 | 170057475.6641 | 3.984% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-10-30 | 5070477.84 | 5749035.93 | 33106607.9 | 27009323.2 | 6097284.7 | 170057475.6641 | 3.585% |  |  | 2018-09-27 | added cash in 3 |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-11-30 | 1337507.07 | 4593575.33 | 34444114.97 | 31602898.53 | 2841216.44 | 170057475.6641 | 1.671% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2019-12-30 | 10719905.22 | 6273855.73 | 45164020.19 | 37876754.26 | 7287265.93 | 170057475.6641 | 4.285% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-01-30 | 6547225.82 | 4920579.14 | 51711246.01 | 42797333.4 | 8913912.61 | 170057475.6641 | 5.242% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-02-28 | 5250223.7 | 6394039.9 | 56961469.71 | 49191373.3 | 7770096.41 | 170057475.6641 | 4.569% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-03-30 | 6237430.18 | 2240079.65 | 63198899.89 | 51431452.95 | 11767446.94 | 170057475.6641 | 6.92% |  |  | 2019-01-20 | added cash in 3 |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-04-30 | 5679423.06 | 2062038.86 | 68878322.95 | 53493491.81 | 15384831.14 | 170057475.6641 | 9.047% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-05-30 | 2647674.17 | 2856879.89 | 71525997.12 | 56350371.7 | 15175625.42 | 170057475.6641 | 8.924% |  |  | 2019-02-21 | added cash in 3 |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-06-30 | 4687303.44 | 8260687.53 | 76213300.56 | 64611059.23 | 11602241.33 | 170057475.6641 | 6.823% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-07-30 | 1169770.65 | 4140620.96 | 77383071.21 | 68751680.19 | 8631391.02 | 170057475.6641 | 5.076% |  |  | 2019-03-14 | added cash in 3 |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-08-30 | 7336701.1 | 2282257.84 | 84719772.31 | 71033938.03 | 13685834.28 | 170057475.6641 | 8.048% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-09-30 | 10902262.27 | 4720808.76 | 95622034.58 | 75754746.79 | 19867287.79 | 170057475.6641 | 11.68% |  |  | 2019-04-09 | added cash in 3 |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-10-30 | 10553431.24 | 8374047.96 | 106175465.82 | 84128794.75 | 22046671.07 | 170057475.6641 | 12.96% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-11-30 | 12635032.9 | 2931638.95 | 118810498.72 | 87060433.7 | 31750065.02 | 170057475.6641 | 18.67% |  |  | 2019-05-21 | added cash in 3 |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2020-12-30 | 3831058.93 | 4350956.46 | 122641557.65 | 91411390.16 | 31230167.49 | 170057475.6641 | 18.36% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2021-01-30 | 8885358.62 | 7492446 | 131526916.27 | 98903836.16 | 32623080.11 | 170057475.6641 | 19.18% |  |  | 2019-06-10 | added cash in 3 |  |  |  | 2021 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2021-02-28 | 6889811.88 | 4168009.61 | 138416728.15 | 103071845.77 | 35344882.38 | 170057475.6641 | 20.78% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2021-03-30 | 9161498.08 | 3728908.84 | 147578226.23 | 106800754.61 | 40777471.62 | 170057475.6641 | 23.98% |  |  | 2019-07-24 | added cash in 3 |  |  |  | 2021 | Infrastructure | Tank | EMAAR
Mivida Irrigation Treatment Plant Pkg 140 | 2021-04-30 | 0 | 1221127.54 | 147578226.23 | 108021882.15 | 39556344.08 | 170057475.6641 | 23.26% | [8 empty] | Infrastructure | Tank | EMAAR
62 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Multi Sports Hall | 2019-01-30 | 0 | 76500 | 0 | 76500 | -76500 | 1200000000 | -0.006375% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-02-28 | 0 | 4000 | 0 | 80500 | -80500 | 1200000000 | -0.006708% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-03-30 | 0 | 18569.08 | 0 | 99069.08 | -99069.08 | 1200000000 | -0.008256% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-04-30 | 0 | 129406.81 | 0 | 228475.89 | -228475.89 | 1200000000 | -0.01904% |  |  | 2019-11-13 | added cash in 3 |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-05-30 | 0 | 302666.83 | 0 | 531142.72 | -531142.72 | 1200000000 | -0.04426% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-06-30 | 0 | 289602.76 | 0 | 820745.48 | -820745.48 | 1200000000 | -0.0684% |  |  | 2019-12-18 | added cash in 3 |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-07-30 | 0 | 780987.18 | 0 | 1601732.66 | -1601732.66 | 1200000000 | -0.1335% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-08-30 | 0 | 2002148.96 | 0 | 3603881.62 | -3603881.62 | 1200000000 | -0.3003% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-09-30 | 0 | 1764752.15 | 0 | 5368633.77 | -5368633.77 | 1200000000 | -0.4474% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-10-30 | 0 | 2684185.19 | 0 | 8052818.96 | -8052818.96 | 1200000000 | -0.6711% |  |  | 2020-04-09 | added 1 |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-11-30 | 100000000 | 3705232.81 | 100000000 | 11758051.77 | 88241948.23 | 1200000000 | 7.353% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2019-12-30 | 9000000 | 4739401.69 | 109000000 | 16497453.46 | 92502546.54 | 1200000000 | 7.709% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2019 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-01-30 | 0 | 34625538.17 | 109000000 | 51122991.63 | 57877008.37 | 1200000000 | 4.823% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-02-28 | 0 | 9310128.61 | 109000000 | 60433120.24 | 48566879.76 | 1200000000 | 4.047% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-03-30 | 0 | 10109203.52 | 109000000 | 70542323.76 | 38457676.24 | 1200000000 | 3.205% |  |  | 2020-12-21 | added cash in 3 |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-04-30 | 0 | 4849101.45 | 109000000 | 75391425.21 | 33608574.79 | 1200000000 | 2.801% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-05-30 | 126071050 | 7603723.75 | 235071050 | 82995148.96 | 152075901.04 | 1200000000 | 12.67% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-06-30 | 0 | 8528630.83 | 235071050 | 91523779.79 | 143547270.21 | 1200000000 | 11.96% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-07-30 | 105 | 26177319.93 | 235071155 | 117701099.72 | 117370055.28 | 1200000000 | 9.781% | [7 empty] | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-08-30 | 0 | 9484597.68 | 235071155 | 127185697.4 | 107885457.6 | 1200000000 | 8.99% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-09-30 | 13887855 | 21920409.51 | 248959010 | 149106106.91 | 99852903.09 | 1200000000 | 8.321% |  | 0 | 2017-11-30 | original |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-10-30 | 124999995 | 30914723.37 | 373959005 | 180020830.28 | 193938174.72 | 1200000000 | 16.16% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-11-30 | 0 | 19394351.07 | 373959005 | 199415181.35 | 174543823.65 | 1200000000 | 14.55% |  | 4401847 | 2017-12-31 | original |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2020-12-30 | 0 | 23015410.91 | 373959005 | 222430592.26 | 151528412.74 | 1200000000 | 12.63% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2021-01-30 | 0 | 30983542.93 | 373959005 | 253414135.19 | 120544869.81 | 1200000000 | 10.05% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2021-02-28 | 2493330 | 20926874.29 | 376452335 | 274341009.48 | 102111325.52 | 1200000000 | 8.509% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2021-03-30 | 0 | 16941894.83 | 376452335 | 291282904.31 | 85169430.69 | 1200000000 | 7.097% |  |  | 2018-03-05 | added cash in 3 |  |  |  | 2021 | Commercial | Stadium | Army Forces
Multi Sports Hall | 2021-04-30 | 0 | 38492040.7 | 376452335 | 329774945.01 | 46677389.99 | 1200000000 | 3.89% | [8 empty] | Commercial | Stadium | Army Forces
63 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-03-30 | 0 | 146287.5 | 0 | 146287.5 | -146287.5 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-04-30 | 0 | 63150 | 0 | 209437.5 | -209437.5 | #N/A | #N/A |  |  | 2018-04-29 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-05-30 | 0 | 33981.68 | 0 | 243419.18 | -243419.18 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-06-30 | 0 | 24815 | 0 | 268234.18 | -268234.18 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-07-30 | 0 | 49728.25 | 0 | 317962.43 | -317962.43 | #N/A | #N/A |  |  | 2018-06-13 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-08-30 | 0 | 425475.3 | 0 | 743437.73 | -743437.73 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-09-30 | 0 | 84583.07 | 0 | 828020.8 | -828020.8 | #N/A | #N/A |  |  | 2018-07-17 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-10-30 | 0 | 151950.83 | 0 | 979971.63 | -979971.63 | #N/A | #N/A |  |  | 2018-07-30 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-11-30 | 0 | 185224.15 | 0 | 1165195.78 | -1165195.78 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2019-12-30 | 0 | 98229.5 | 0 | 1263425.28 | -1263425.28 | #N/A | #N/A |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Emergency Bridge | 2020-01-30 | 0 | 442135.62 | 0 | 1705560.9 | -1705560.9 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Emergency Bridge | 2020-02-28 | 0 | 132311.45 | 0 | 1837872.35 | -1837872.35 | #N/A | #N/A |  |  | 2018-09-17 | added cash in 3 |  |  |  | 2020 | #N/A | #N/A | #N/A
Emergency Bridge | 2020-03-30 | 0 | 4835 | 0 | 1842707.35 | -1842707.35 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Emergency Bridge | 2020-04-30 | 0 | 21410.04 | 0 | 1864117.39 | -1864117.39 | #N/A | #N/A |  |  | 2018-10-15 | added cash in 3 |  |  |  | 2020 | #N/A | #N/A | #N/A
Emergency Bridge | 2020-06-30 | 0 | 43208.09 | 0 | 1907325.48 | -1907325.48 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Emergency Bridge | 2020-10-30 | 0 | 1280.2 | 0 | 1908605.68 | -1908605.68 | #N/A | #N/A |  |  | 2018-11-08 | added cash in 3 |  |  |  | 2020 | #N/A | #N/A | #N/A
Emergency Bridge | 2021-01-30 | 0 | 1538.32 | 0 | 1910144 | -1910144 | #N/A | #N/A |  |  | 2018-11-21 | added cash in 3 |  |  |  | 2021 | #N/A | #N/A | #N/A
64 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-03-30 | 0 | 42000 | 0 | 42000 | -42000 | #N/A | #N/A |  |  | 2018-12-11 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-04-30 | 0 | 37900 | 0 | 79900 | -79900 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-05-30 | 0 | 17300 | 0 | 97200 | -97200 | #N/A | #N/A |  |  | 2019-01-06 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-06-30 | 0 | 34500 | 0 | 131700 | -131700 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-07-30 | 0 | 114209 | 0 | 245909 | -245909 | #N/A | #N/A |  |  | 2019-02-07 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-08-30 | 0 | 106690 | 0 | 352599 | -352599 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-09-30 | 0 | 140914.62 | 0 | 493513.62 | -493513.62 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-10-30 | 0 | 74705.35 | 0 | 568218.97 | -568218.97 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-11-30 | 0 | 33095 | 0 | 601313.97 | -601313.97 | #N/A | #N/A |  |  | 2019-05-13 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2019-12-30 | 0 | 123609.76 | 0 | 724923.73 | -724923.73 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2020-01-30 | 0 | 76710.62 | 0 | 801634.35 | -801634.35 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2020-02-28 | 0 | 2619 | 0 | 804253.35 | -804253.35 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2020-03-30 | 0 | 10000 | 0 | 814253.35 | -814253.35 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2020-04-30 | 0 | 6666 | 0 | 820919.35 | -820919.35 | #N/A | #N/A |  |  | 2019-09-29 | added cash in 3 |  |  |  | 2020 | #N/A | #N/A | #N/A
Pyramid El Remayah Tunnel | 2020-07-30 | 0 | 8270 | 0 | 829189.35 | -829189.35 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
65 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
EGAT | 2019-03-30 | 22000000 | 0 | 22000000 | 0 | 22000000 | 65831906 | 33.42% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Sewedy
EGAT | 2019-04-30 | 20624356.65 | 0 | 42624356.65 | 0 | 42624356.65 | 65831906 | 64.75% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Sewedy
EGAT | 2019-09-30 | 9050238.73 | 0 | 51674595.38 | 0 | 51674595.38 | 65831906 | 78.49% |  |  |  | cash out both |  |  |  | 2019 | Industrial | Factory | Sewedy
EGAT | 2020-01-30 | 750000.81 | 0 | 52424596.19 | 0 | 52424596.19 | 65831906 | 79.63% |  |  | 2020-02-23 | added 1 |  |  |  | 2020 | Industrial | Factory | Sewedy
EGAT | 2020-03-30 | 500000 | 0 | 52924596.19 | 0 | 52924596.19 | 65831906 | 80.39% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Sewedy
EGAT | 2020-04-30 | 3000000 | 0 | 55924596.19 | 0 | 55924596.19 | 65831906 | 84.95% |  |  | 2020-03-19 | added 1 |  |  |  | 2020 | Industrial | Factory | Sewedy
EGAT | 2020-06-30 | 750000 | 0 | 56674596.19 | 0 | 56674596.19 | 65831906 | 86.09% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Sewedy
EGAT | 2020-10-30 | 0 | 230351.35 | 56674596.19 | 230351.35 | 56444244.84 | 65831906 | 85.74% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Sewedy
EGAT | 2020-11-30 | 0 | 91485 | 56674596.19 | 321836.35 | 56352759.84 | 65831906 | 85.6% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Sewedy
EGAT | 2020-12-30 | 291975.34 | 636142.19 | 56966571.53 | 957978.54 | 56008592.99 | 65831906 | 85.08% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Factory | Sewedy
EGAT | 2021-01-30 | 0 | 76538.05 | 56966571.53 | 1034516.59 | 55932054.94 | 65831906 | 84.96% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Factory | Sewedy
EGAT | 2021-02-28 | 0 | 2618287.96 | 56966571.53 | 3652804.55 | 53313766.98 | 65831906 | 80.98% |  |  | 2020-09-30 | added 1 |  |  |  | 2021 | Industrial | Factory | Sewedy
EGAT | 2021-03-30 | 0 | 20870.22 | 56966571.53 | 3673674.77 | 53292896.76 | 65831906 | 80.95% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2021 | Industrial | Factory | Sewedy
66 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Abou Ghazala Bridge Ramp L&L | 2019-03-30 | 0 | 60310.53 | 0 | 60310.53 | -60310.53 | 1688453 | -3.572% |  |  | 2020-11-18 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-04-30 | 0 | 1320 | 0 | 61630.53 | -61630.53 | 1688453 | -3.65% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-06-30 | 0 | 16395 | 0 | 78025.53 | -78025.53 | 1688453 | -4.621% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-07-30 | 0 | 7535 | 0 | 85560.53 | -85560.53 | 1688453 | -5.067% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-08-30 | 0 | 14750 | 0 | 100310.53 | -100310.53 | [9 empty] | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-09-30 | 0 | 79561 | 0 | 179871.53 | -179871.53 | 1688453 | -10.65% |  |  | 2017-11-30 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-10-30 | 0 | 41010.72 | 0 | 220882.25 | -220882.25 | 1688453 | -13.08% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-11-30 | 0 | 999 | 0 | 221881.25 | -221881.25 | 1688453 | -13.14% |  |  | 2018-01-18 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2019-12-30 | 0 | 64163.26 | 0 | 286044.51 | -286044.51 | 1688453 | -16.94% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2020-01-30 | 0 | 1805 | 0 | 287849.51 | -287849.51 | 1688453 | -17.05% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2020-02-28 | 0 | 2310 | 0 | 290159.51 | -290159.51 | 1688453 | -17.18% |  |  | 2018-03-22 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2020-05-30 | 0 | 18615.2 | 0 | 308774.71 | -308774.71 | 1688453 | -18.29% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2020-10-30 | 1343575 | 0 | 1343575 | 308774.71 | 1034800.29 | 1688453 | 61.29% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2021-02-28 | 0 | 5318.63 | 1343575 | 314093.34 | 1029481.66 | 1688453 | 60.97% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
Abou Ghazala Bridge Ramp L&L | 2021-03-30 | 0 | 1189.01 | 1343575 | 315282.35 | 1028292.65 | 1688453 | 60.9% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
67 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Mohamed Ali Fahmy Ramps L&L | 2019-04-30 | 0 | 50965 | 0 | 50965 | -50965 | 7149700 | -0.7128% |  |  | 2018-08-19 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2018-12-30 | 24600000 | 0 | 24600000 | 50965 | 24549035 | [10 empty] | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-02-28 | 2532120.6 | 0 | 27132120.6 | 50965 | 27081155.6 | [10 empty] | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-03-30 | 13076462.06 | 0 | 40208582.66 | 50965 | 40157617.66 | [10 empty] | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-05-30 | 0 | 588829.18 | 40208582.66 | 639794.18 | 39568788.48 | 7149700 | 553.4% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-06-30 | 0 | 172070.9 | 40208582.66 | 811865.08 | 39396717.58 | 7149700 | 551% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-07-30 | 0 | 351317.8 | 40208582.66 | 1163182.88 | 39045399.78 | 7149700 | 546.1% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-08-30 | 0 | 90723.27 | 40208582.66 | 1253906.15 | 38954676.51 | 7149700 | 544.8% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-09-30 | 0 | 239353.3 | 40208582.66 | 1493259.45 | 38715323.21 | 7149700 | 541.5% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-10-30 | 0 | 227119.69 | 40208582.66 | 1720379.14 | 38488203.52 | 7149700 | 538.3% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-11-30 | 0 | 47223.93 | 40208582.66 | 1767603.07 | 38440979.59 | 7149700 | 537.7% |  |  | 2019-02-10 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2019-12-30 | 0 | 167212.97 | 40208582.66 | 1934816.04 | 38273766.62 | 7149700 | 535.3% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2020-01-30 | 0 | 79839.48 | 40208582.66 | 2014655.52 | 38193927.14 | 7149700 | 534.2% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2020-02-28 | 0 | 109705.5 | 40208582.66 | 2124361.02 | 38084221.64 | 7149700 | 532.7% |  |  | 2019-05-21 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2020-03-30 | 0 | 332.31 | 40208582.66 | 2124693.33 | 38083889.33 | 7149700 | 532.7% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2020-05-30 | 0 | 69610.59 | 40208582.66 | 2194303.92 | 38014278.74 | 7149700 | 531.7% |  |  | 2020-01-15 | added 1 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2020-06-30 | 0 | 332.31 | 40208582.66 | 2194636.23 | 38013946.43 | 7149700 | 531.7% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2020-07-30 | 0 | 0 | 40208582.66 | 2194636.23 | 38013946.43 | 7149700 | 531.7% |  |  | 2020-04-29 | added 1 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2020-12-30 | 0 | 0 | 40208582.66 | 2194636.23 | 38013946.43 | 7149700 | 531.7% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2021-02-28 | 0 | 19888.76 | 40208582.66 | 2214524.99 | 37994057.67 | [9 empty] | 2021 | Infrastructure | L&L | Army Forces
Mohamed Ali Fahmy Ramps L&L | 2021-03-30 | 0 | 1580.08 | 40208582.66 | 2216105.07 | 37992477.59 | 7149700 | 531.4% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
68 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Mosheer Bridge Abu Zaied Khdr L&L | 2019-11-30 | 0 | 46683 | 0 | 46683 | -46683 | 4203687 | -1.111% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Mosheer Bridge Abu Zaied Khdr L&L | 2019-12-30 | 0 | 2118461.31 | 0 | 2165144.31 | -2165144.31 | 4203687 | -51.51% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-01-30 | 0 | 8547 | 0 | 2173691.31 | -2173691.31 | 4203687 | -51.71% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-02-28 | 0 | 12795 | 0 | 2186486.31 | -2186486.31 | 4203687 | -52.01% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-06-30 | 0 | 196068.6 | 0 | 2382554.91 | -2382554.91 | 4203687 | -56.68% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Mosheer Bridge Abu Zaied Khdr L&L | 2020-08-30 | 0 | 33234 | 0 | 2415788.91 | -2415788.91 | 4203687 | -57.47% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
El Mosheer Bridge Abu Zaied Khdr L&L | 2021-02-28 | 0 | 31241.52 | 0 | 2447030.43 | -2447030.43 | 4203687 | -58.21% |  |  |  | cash out both |  |  |  |  | Infrastructure | L&L | Army Forces
69 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Ora Zed Park L&L | 2019-07-30 | 0 | 4000 | 0 | 4000 | -4000 | 1042542 | -0.3837% |  |  | 2018-09-24 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2019-08-30 | 0 | 29590 | 0 | 33590 | -33590 | 1042542 | -3.222% |  |  | 2018-09-25 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2019-09-30 | 0 | 190975 | 0 | 224565 | -224565 | 1042542 | -21.54% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2019-10-30 | 0 | 83030.02 | 0 | 307595.02 | -307595.02 | 1042542 | -29.5% |  |  | 2018-10-28 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2019-11-30 | 505797.14 | 28265.17 | 505797.14 | 335860.19 | 169936.95 | 1042542 | 16.3% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2019-12-30 | 0 | 237800.21 | 505797.14 | 573660.4 | -67863.26 | 1042542 | -6.509% |  |  | 2018-11-06 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-01-30 | 0 | 20686 | 505797.14 | 594346.4 | -88549.26 | 1042542 | -8.494% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-02-28 | 264423.21 | 33959.75 | 770220.35 | 628306.15 | 141914.2 | 1042542 | 13.61% |  |  | 2018-12-25 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-03-30 | 0 | 18120 | 770220.35 | 646426.15 | 123794.2 | 1042542 | 11.87% |  |  | 2018-12-26 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-04-30 | 0 | 15456 | 770220.35 | 661882.15 | 108338.2 | 1042542 | 10.39% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-05-30 | 0 | 118727.74 | 770220.35 | 780609.89 | -10389.54 | 1042542 | -0.9966% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-06-30 | 0 | 1765 | 770220.35 | 782374.89 | -12154.54 | 1042542 | -1.166% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-10-30 | 0 | 63220.59 | 770220.35 | 845595.48 | -75375.13 | 1042542 | -7.23% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2020-11-30 | 0 | 179176.92 | 770220.35 | 1024772.4 | -254552.05 | 1042542 | -24.42% |  |  | 2019-07-03 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2021-01-30 | 0 | 614228.65 | 770220.35 | 1639001.05 | -868780.7 | 1042542 | -83.33% | [8 empty] | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2021-02-28 | 128110.86 | 0 | 898331.21 | 1639001.05 | -740669.84 | 1042542 | -71.04% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2021-03-30 | 0 | 7258.41 | 898331.21 | 1646259.46 | -747928.25 | 1042542 | -71.74% | [8 empty] | Infrastructure | L&L | Ora
Ora Zed Park L&L | 2021-04-30 | 0 | 661141.23 | 898331.21 | 2307400.69 | -1409069.48 | 1042542 | -135.2% | [8 empty] | Infrastructure | L&L | Ora
70 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
DoubleTree Mangroovy El Gouna Hotel | 2019-08-30 | 13625000 | 123695 | 13625000 | 123695 | 13501305 | 57898699.39 | 23.32% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2019-09-30 | 0 | 916740.44 | 13625000 | 1040435.44 | 12584564.56 | 57898699.39 | 21.74% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2019-10-30 | 0 | 2815823.91 | 13625000 | 3856259.35 | 9768740.65 | 57898699.39 | [8 empty] | 2019 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2019-11-30 | 2327690.6 | 2474341.27 | 15952690.6 | 6330600.62 | 9622089.98 | 57898699.39 | 16.62% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2019-12-30 | 3867767.27 | 2430905.56 | 19820457.87 | 8761506.18 | 11058951.69 | 57898699.39 | 19.1% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-01-30 | 2286139.86 | 6227180.54 | 22106597.73 | 14988686.72 | 7117911.01 | 57898699.39 | 12.29% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-02-28 | 3071785.6 | 2096022.36 | 25178383.33 | 17084709.08 | 8093674.25 | 57898699.39 | 13.98% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-03-30 | 2250122.07 | 1978445.9 | 27428505.4 | 19063154.98 | 8365350.42 | 57898699.39 | 14.45% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-04-30 | 0 | 702657.88 | 27428505.4 | 19765812.86 | 7662692.54 | 57898699.39 | 13.23% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-05-30 | 0 | 2009562.65 | 27428505.4 | 21775375.51 | 5653129.89 | 57898699.39 | 9.764% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-06-30 | 4018374 | 603884.31 | 31446879.4 | 22379259.82 | 9067619.58 | 57898699.39 | 15.66% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-07-30 | 0 | 878558.31 | 31446879.4 | 23257818.13 | 8189061.27 | 57898699.39 | 14.14% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-08-30 | 8313955.53 | 4457113.88 | 39760834.93 | 27714932.01 | 12045902.92 | 57898699.39 | 20.81% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-09-30 | 0 | 4761736.81 | 39760834.93 | 32476668.82 | 7284166.11 | 57898699.39 | 12.58% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-10-30 | 2204453.79 | 3643919.27 | 41965288.72 | 36120588.09 | 5844700.63 | 57898699.39 | 10.09% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-11-30 | 0 | 398244.78 | 41965288.72 | 36518832.87 | 5446455.85 | 57898699.39 | 9.407% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2020-12-30 | 0 | 482487.62 | 41965288.72 | 37001320.49 | 4963968.23 | 57898699.39 | 8.574% |  |  | 2019-01-31 | added cash in 3 |  |  |  | 2020 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2021-01-30 | 1942857.14 | 5176581.33 | 43908145.86 | 42177901.82 | 1730244.04 | 57898699.39 | 2.988% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2021-02-28 | 3949816.68 | 2428701.65 | 47857962.54 | 44606603.47 | 3251359.07 | 57898699.39 | 5.616% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2021-03-30 | 0 | 4223342.22 | 47857962.54 | 48829945.69 | -971983.15 | 57898699.39 | -1.679% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Hotel | Sewedy
DoubleTree Mangroovy El Gouna Hotel | 2021-04-30 | 3061987.31 | 1811714.28 | 50919949.85 | 50641659.97 | 278289.88 | 57898699.39 | 0.4806% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Hotel | Sewedy
71 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Baron Palace Fence | 2019-08-30 | 0 | 14090 | 0 | 14090 | -14090 | 16220552 | -0.08687% |  |  | 2019-12-31 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Baron Palace Fence | 2019-09-30 | 0 | 308480 | 0 | 322570 | -322570 | 16220552 | -1.989% |  |  | 2020-01-26 | added 1 |  |  |  | 2019 | Restoration | Palace | Army Forces
Baron Palace Fence | 2019-10-30 | 0 | 477249.15 | 0 | 799819.15 | -799819.15 | 16220552 | -4.931% |  |  |  | cash out both |  |  |  | 2019 | Restoration | Palace | Army Forces
Baron Palace Fence | 2019-11-30 | 0 | 1306567.91 | 0 | 2106387.06 | -2106387.06 | [9 empty] | 2019 | Restoration | Palace | Army Forces
Baron Palace Fence | 2019-12-30 | 0 | 1047888.89 | 0 | 3154275.95 | -3154275.95 | 16220552 | -19.45% |  |  | 2018-01-17 | added cash in 3 |  |  |  | 2019 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-01-30 | 0 | 1770657.46 | 0 | 4924933.41 | -4924933.41 | 16220552 | -30.36% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-02-28 | 0 | 2675048.79 | 0 | 7599982.2 | -7599982.2 | 16220552 | -46.85% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-03-30 | 0 | 2357973.45 | 0 | 9957955.65 | -9957955.65 | 16220552 | -61.39% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-04-30 | 0 | 412976.27 | 0 | 10370931.92 | -10370931.92 | 16220552 | -63.94% |  |  | 2018-04-24 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-05-30 | 0 | 1195.04 | 0 | 10372126.96 | -10372126.96 | 16220552 | -63.94% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-06-30 | 0 | 55159 | 0 | 10427285.96 | -10427285.96 | 16220552 | -64.28% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-07-30 | 0 | 8670.85 | 0 | 10435956.81 | -10435956.81 | 16220552 | -64.34% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-09-30 | 0 | 501066.13 | 0 | 10937022.94 | -10937022.94 | 16220552 | -67.43% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-10-30 | 5600125 | 0 | 5600125 | 10937022.94 | -5336897.94 | 16220552 | -32.9% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-11-30 | 0 | 448670 | 5600125 | 11385692.94 | -5785567.94 | 16220552 | -35.67% |  |  | 2018-08-15 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2020-12-30 | 392980 | 2500 | 5993105 | 11388192.94 | -5395087.94 | 16220552 | -33.26% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Baron Palace Fence | 2021-01-30 | 0 | 91695 | 5993105 | 11479887.94 | -5486782.94 | 16220552 | -33.83% |  |  |  | cash out both |  |  |  | 2021 | Restoration | Palace | Army Forces
Baron Palace Fence | 2021-02-28 | 355500 | 792.03 | 6348605 | 11480679.97 | -5132074.97 | 16220552 | -31.64% |  |  | 2018-10-16 | added cash in 3 |  |  |  | 2021 | Restoration | Palace | Army Forces
Baron Palace Fence | 2021-03-30 | 0 | 3040.33 | 6348605 | 11483720.3 | -5135115.3 | 16220552 | -31.66% |  |  |  | cash out both |  |  |  | 2021 | Restoration | Palace | Army Forces
72 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Safeer Square Bridge | 2019-08-30 | 0 | 230000 | 0 | 230000 | -230000 | 95436549 | -0.241% |  |  | 2018-11-22 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2018-12-30 |  | 0 | 0 | 230000 | -230000 | [10 empty] | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2019-02-28 |  | 0 | 0 | 230000 | -230000 | [10 empty] | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2019-03-28 |  | 0 | 0 | 230000 | -230000 | [10 empty] | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2019-09-30 | 0 | 1011621.78 | 0 | 1241621.78 | -1241621.78 | 95436549 | -1.301% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2019-10-30 | 0 | 5568944.65 | 0 | 6810566.43 | -6810566.43 | 95436549 | -7.136% |  |  | 2018-12-30 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2019-11-30 | 0 | 7992126.69 | 0 | 14802693.12 | -14802693.12 | 95436549 | -15.51% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2019-12-30 | 0 | 14530425.24 | 0 | 29333118.36 | -29333118.36 | 95436549 | -30.74% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-01-30 | 0 | 6675475.41 | 0 | 36008593.77 | -36008593.77 | 95436549 | -37.73% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-02-28 | 5532120.6 | 1836134.8 | 5532120.6 | 37844728.57 | -32312607.97 | 95436549 | -33.86% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-03-30 | 0 | 757140.3 | 5532120.6 | 38601868.87 | -33069748.27 | 95436549 | -34.65% |  |  | 2019-04-02 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-04-30 | 0 | 134873.65 | 5532120.6 | 38736742.52 | -33204621.92 | 95436549 | -34.79% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-05-30 | 0 | 114604.29 | 5532120.6 | 38851346.81 | -33319226.21 | 95436549 | -34.91% |  |  | 2019-05-28 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-06-30 | 0 | 263853.74 | 5532120.6 | 39115200.55 | -33583079.95 | 95436549 | -35.19% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-07-30 | 0 | 673273.7 | 5532120.6 | 39788474.25 | -34256353.65 | 95436549 | -35.89% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-08-30 | 0 | 0 | 5532120.6 | 39788474.25 | -34256353.65 | 95436549 | -35.89% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-09-30 | 0 | 182243.92 | 5532120.6 | 39970718.17 | -34438597.57 | 95436549 | -36.09% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-11-30 | 6777000 | 2410290 | 12309120.6 | 42381008.17 | -30071887.57 | 95436549 | -31.51% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2020-12-30 | 0 | 5454.52 | 12309120.6 | 42386462.69 | -30077342.09 | 95436549 | -31.52% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Safeer Square Bridge | 2021-03-30 | 0 | 5454.52 | 12309120.6 | 42391917.21 | -30082796.61 | 95436549 | -31.52% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
73 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Suez Road Tunnel Res L&L | 2019-09-30 | 0 | 41835 | 0 | 41835 | -41835 | 4423592 | -0.9457% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2019-10-30 | 0 | 186408.87 | 0 | 228243.87 | -228243.87 | 4423592 | -5.16% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2019-11-30 | 0 | 370529.97 | 0 | 598773.84 | -598773.84 | 4423592 | -13.54% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2019-12-30 | 0 | 22267.29 | 0 | 621041.13 | -621041.13 | 4423592 | -14.04% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2020-01-30 | 0 | 44884.55 | 0 | 665925.68 | -665925.68 | 4423592 | -15.05% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2020-02-28 | 0 | 14965.5 | 0 | 680891.18 | -680891.18 | 4423592 | -15.39% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2020-05-30 | 0 | 55138.6 | 0 | 736029.78 | -736029.78 | 4423592 | -16.64% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2020-06-30 | 0 | 23748 | 0 | 759777.78 | -759777.78 | 4423592 | -17.18% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2020-07-30 | 0 | 8044 | 0 | 767821.78 | -767821.78 | 4423592 | -17.36% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2020-10-30 | 2837565 | 37742 | 2837565 | 805563.78 | 2032001.22 | 4423592 | 45.94% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2020-11-30 | 1311260 | 0 | 4148825 | 805563.78 | 3343261.22 | 4423592 | 75.58% |  |  | 2021-02-08 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2021-02-28 | 0 | 13769.87 | 4148825 | 819333.65 | 3329491.35 | 4423592 | 75.27% |  |  | 2021-02-09 | added 1 |  |  |  | 2021 | Infrastructure | L&L | Army Forces
Suez Road Tunnel Res L&L | 2021-03-30 | 0 | 3673.94 | 4148825 | 823007.59 | 3325817.41 | 4423592 | 75.18% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
74 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
HyperOne Zayed Extention | 2019-09-30 | 0 | 141750 | 0 | 141750 | -141750 | 133583770 | -0.1061% |  |  |  | cash out both |  |  | 9 | 2019 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2019-10-30 | 33750000 | 953319.33 | 33750000 | 1095069.33 | 32654930.67 | 133583770 | 24.45% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2019-11-30 | 0 | 4599187.47 | 33750000 | 5694256.8 | 28055743.2 | 133583770 | 21% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2019-12-30 | 10562710 | 3785151.58 | 44312710 | 9479408.38 | 34833301.62 | 133583770 | 26.08% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-01-30 | 6681009 | 5033335.71 | 50993719 | 14512744.09 | 36480974.91 | 133583770 | 27.31% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-02-28 | 10797753 | 5225134.66 | 61791472 | 19737878.75 | 42053593.25 | [9 empty] | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-03-30 | 22284476 | 10387082.84 | 84075948 | 30124961.59 | 53950986.41 | 133583770 | 40.39% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-04-30 | 4441581 | 1626963.97 | 88517529 | 31751925.56 | 56765603.44 | 133583770 | 42.49% |  |  | 2018-03-13 | added cash in 3 |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-05-30 | 1277872 | 9104866.65 | 89795401 | 40856792.21 | 48938608.79 | 133583770 | 36.64% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-06-30 | 8179648 | 7321582.33 | 97975049 | 48178374.54 | 49796674.46 | 133583770 | 37.28% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-07-30 | 8596463 | 9049949.79 | 106571512 | 57228324.33 | 49343187.67 | 133583770 | 36.94% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-08-30 | 4000000 | 2196771.75 | 110571512 | 59425096.08 | 51146415.92 | 133583770 | 38.29% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-09-30 | 11214893 | 4555524.57 | 121786405 | 63980620.65 | 57805784.35 | 133583770 | 43.27% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-10-30 | 0 | 6889598.01 | 121786405 | 70870218.66 | 50916186.34 | 133583770 | 38.12% |  |  | 2018-08-19 | added cash in 3 |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-11-30 | 0 | 4807891.28 | 121786405 | 75678109.94 | 46108295.06 | 133583770 | 34.52% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2020-12-30 | 0 | 2392170.96 | 121786405 | 78070280.9 | 43716124.1 | 133583770 | 32.73% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2021-01-30 | 0 | 3177919.96 | 121786405 | 81248200.86 | 40538204.14 | 133583770 | 30.35% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2021-02-28 | 0 | 657871.69 | 121786405 | 81906072.55 | 39880332.45 | 133583770 | 29.85% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2021-03-30 | 0 | 959133.29 | 121786405 | 82865205.84 | 38921199.16 | 133583770 | 29.14% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Parking | Hyper
HyperOne Zayed Extention | 2021-04-30 | 0 | 105249.86 | 121786405 | 82970455.7 | 38815949.3 | 133583770 | 29.06% | [7 empty] | 2021 | Commercial | Parking | Hyper
75 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
IKEA Extention MoA | 2019-10-30 | 5428986.9 | 3011216.94 | 5428986.9 | 3011216.94 | 2417769.96 | 196190620 | 1.232% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2019-11-30 | 4032556.9 | 7126856.85 | 9461543.8 | 10138073.79 | -676529.99 | 196190620 | -0.3448% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2019-12-30 | 15585616 | 7373329.8 | 25047159.8 | 17511403.59 | 7535756.21 | 196190620 | 3.841% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-01-30 | 9300217 | 11867880.08 | 34347376.8 | 29379283.67 | 4968093.13 | 196190620 | 2.532% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-02-28 | 21562500 | 28621085.84 | 55909876.8 | 58000369.51 | -2090492.71 | 196190620 | -1.066% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-03-30 | 8278802 | 6172946.29 | 64188678.8 | 64173315.8 | 15363 | 196190620 | 0.007831% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-04-30 | 7929959.81 | 4596619.73 | 72118638.61 | 68769935.53 | 3348703.08 | 196190620 | 1.707% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-05-30 | 9995638 | 9542179.94 | 82114276.61 | 78312115.47 | 3802161.14 | 196190620 | 1.938% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-06-30 | 0 | 14513935.55 | 82114276.61 | 92826051.02 | -10711774.41 | 196190620 | -5.46% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-07-30 | 6161858.91 | 9843472.56 | 88276135.52 | 102669523.58 | -14393388.06 | 196190620 | -7.336% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-08-30 | 13080191 | 14055586.3 | 101356326.52 | 116725109.88 | -15368783.36 | 196190620 | -7.834% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-09-30 | 21936362 | 24766400.5 | 123292688.52 | 141491510.38 | -18198821.86 | 196190620 | -9.276% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-10-30 | 12246749 | 10255443.06 | 135539437.52 | 151746953.44 | -16207515.92 | 196190620 | -8.261% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-11-30 | 16592416.38 | 16609524.11 | 152131853.9 | 168356477.55 | -16224623.65 | 196190620 | -8.27% |  |  | 2020-03-15 | added 1 |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2020-12-30 | 0 | 5286036.68 | 152131853.9 | 173642514.23 | -21510660.33 | 196190620 | -10.96% |  |  | 2020-03-25 | added 1 |  |  |  | 2020 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2021-01-30 | 17412075 | 3462029.26 | 169543928.9 | 177104543.49 | -7560614.59 | 196190620 | -3.854% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2021-02-28 | 0 | 13442010.46 | 169543928.9 | 190546553.95 | -21002625.05 | 196190620 | -10.71% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Marakez
IKEA Extention MoA | 2021-03-30 | 6181146.38 | 3809231.23 | 175725075.28 | 194355785.18 | -18630709.9 | 196190620 | -9.496% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Marakez
76 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
CFC Podium II | 2019-10-30 | 0 | 153062.78 | 0 | 153062.78 | -153062.78 | 635000000 | -0.0241% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2019-11-30 | 0 | 3188079.48 | 0 | 3341142.26 | -3341142.26 | 635000000 | -0.5262% |  |  |  | cash out both |  |  |  | 2019 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2019-12-30 | 0 | 10012953.38 | 0 | 13354095.64 | -13354095.64 | 635000000 | -2.103% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2019 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-01-30 | 62134944.55 | 9572180.59 | 62134944.55 | 22926276.23 | 39208668.32 | 635000000 | 6.175% |  |  | 2020-10-04 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-02-28 | 54373515.59 | 31588029.16 | 116508460.14 | 54514305.39 | 61994154.75 | 635000000 | 9.763% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-03-30 | 12263695.64 | 21545591.32 | 128772155.78 | 76059896.71 | 52712259.07 | 635000000 | 8.301% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-04-30 | 0 | 12872110.15 | 128772155.78 | 88932006.86 | 39840148.92 | 635000000 | 6.274% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-05-30 | 0 | 8997379.04 | 128772155.78 | 97929385.9 | 30842769.88 | 635000000 | 4.857% |  |  | 2021-01-31 | added cash in 3 |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-06-30 | 88910222.55 | 42998694.33 | 217682378.33 | 140928080.23 | 76754298.1 | 635000000 | 12.09% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-07-30 | 19510038.16 | 24580639.89 | 237192416.49 | 165508720.12 | 71683696.37 | 635000000 | 11.29% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-08-30 | 21459125.32 | 14981487.26 | 258651541.81 | 180490207.38 | 78161334.43 | [9 empty] | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-09-30 | 63948491.66 | 43690870.72 | 322600033.47 | 224181078.1 | 98418955.37 | 635000000 | 15.5% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-10-30 | 18030566.05 | 24294894.3 | 340630599.52 | 248475972.4 | 92154627.12 | 635000000 | 14.51% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-11-30 | 0 | 17809882.32 | 340630599.52 | 266285854.72 | 74344744.8 | 635000000 | 11.71% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2020-12-30 | 52904950.98 | 13927953 | 393535550.5 | 280213807.72 | 113321742.78 | 635000000 | 17.85% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2021-01-30 | 0 | 22558677 | 393535550.5 | 302772484.72 | 90763065.78 | 635000000 | 14.29% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2021-02-28 | 19708943.72 | 20874557 | 413244494.22 | 323647041.72 | 89597452.5 | 635000000 | 14.11% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2021-03-30 | 40379659.63 | 35847301 | 453624153.85 | 359494342.72 | 94129811.13 | 635000000 | 14.82% |  |  | 2018-08-19 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | Al-Futtaim
CFC Podium II | 2021-04-30 | 37918924.51 | 17252287 | 491543078.36 | 376746629.72 | 114796448.64 | 635000000 | 18.08% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Al-Futtaim
77 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Josef Tito Bridge L&L | 2019-11-30 | 0 | 20000 | 0 | 20000 | -20000 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Josef Tito Bridge L&L | 2020-01-30 | 0 | 6705 | 0 | 26705 | -26705 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
78 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Espiko Bridge L&L | 2019-11-30 | 0 | 77065.6 | 0 | 77065.6 | -77065.6 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Espiko Bridge L&L | 2019-12-30 | 0 | 15209.6 | 0 | 92275.2 | -92275.2 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Espiko Bridge L&L | 2020-01-30 | 0 | 12000 | 0 | 104275.2 | -104275.2 | 0 | #DIV/0! |  |  | 2019-02-07 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Espiko Bridge L&L | 2020-03-30 | 0 | 6000 | 0 | 110275.2 | -110275.2 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Espiko Bridge L&L | 2020-04-30 | 0 | 3000 | 0 | 113275.2 | -113275.2 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
79 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
MR3 Bridge L&L | 2019-10-30 | 0 | 26700 | 0 | 26700 | -26700 | 1520085 | -1.756% |  |  | 2019-07-16 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2019-11-30 | 0 | 73154.6 | 0 | 99854.6 | -99854.6 | 1520085 | -6.569% |  |  | 2019-07-22 | added cash in 3 |  |  |  | 2019 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2019-12-30 | 0 | 170728.56 | 0 | 270583.16 | -270583.16 | 1520085 | -17.8% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2020-01-30 | 0 | 67553.93 | 0 | 338137.09 | -338137.09 | 1520085 | -22.24% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2020-02-28 | 0 | 87924.37 | 0 | 426061.46 | -426061.46 | [9 empty] | 2020 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2020-03-30 | 0 | 3044 | 0 | 429105.46 | -429105.46 | 1520085 | -28.23% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2020-05-30 | 0 | 16758.44 | 0 | 445863.9 | -445863.9 | 1520085 | -29.33% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2020-07-30 | 0 | 21050 | 0 | 466913.9 | -466913.9 | 1520085 | -30.72% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2021-01-30 | 714790 | 0 | 714790 | 466913.9 | 247876.1 | 1520085 | 16.31% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
MR3 Bridge L&L | 2021-02-28 | 0 | 4788.11 | 714790 | 471702.01 | 243087.99 | 1520085 | 15.99% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
80 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Sewedy University 1 | 2018-08-30 | 2898141.12 | 603460 | 2898141.12 | 603460 | 2294681.12 | 593999147 | 0.3863% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | Sewedy
El Sewedy University 1 | 2018-09-30 | 8589000 | 5393496.53 | 11487141.12 | 5996956.53 | 5490184.59 | 593999147 | 0.9243% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | Sewedy
El Sewedy University 1 | 2018-10-30 | 5028949.8 | 3914541.12 | 16516090.92 | 9911497.65 | 6604593.27 | 593999147 | 1.112% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | Sewedy
El Sewedy University 1 | 2018-11-30 | 7636011.93 | 4135515.18 | 24152102.85 | 14047012.83 | 10105090.02 | 593999147 | 1.701% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | Sewedy
El Sewedy University 1 | 2018-12-30 | 4427942.45 | 5706049.89 | 28580045.3 | 19753062.72 | 8826982.58 | 593999147 | 1.486% |  |  |  | cash out both |  |  |  | 2018 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-01-30 | 29711771.55 | 17642188.83 | 58291816.85 | 37395251.55 | 20896565.3 | 593999147 | 3.518% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-02-28 | 13048080.93 | 14854000.37 | 71339897.78 | 52249251.92 | 19090645.86 | 593999147 | 3.214% |  |  | 2019-02-11 | added cash in 3 |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-03-30 | 30156192.64 | 14374015.11 | 101496090.42 | 66623267.03 | 34872823.39 | 593999147 | 5.871% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-04-30 | 9067523.43 | 17369715.11 | 110563613.85 | 83992982.14 | 26570631.71 | 593999147 | 4.473% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-05-30 | 24218860.89 | 27974414.64 | 134782474.74 | 111967396.78 | 22815077.96 | 593999147 | 3.841% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-06-30 | 26716091.61 | 17825387.85 | 161498566.35 | 129792784.63 | 31705781.72 | 593999147 | 5.338% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-07-30 | 32000000 | 13814354.38 | 193498566.35 | 143607139.01 | 49891427.34 | 593999147 | 8.399% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-08-30 | 0 | 19088651.09 | 193498566.35 | 162695790.1 | 30802776.25 | 593999147 | 5.186% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-09-30 | 39616203.19 | 22187588.75 | 233114769.54 | 184883378.85 | 48231390.69 | 593999147 | 8.12% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-10-30 | 20919758.57 | 11934828.43 | 254034528.11 | 196818207.28 | 57216320.83 | 593999147 | 9.632% |  |  | 2019-09-30 | added cash in 3 |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-11-30 | 0 | 5286433.51 | 254034528.11 | 202104640.79 | 51929887.32 | 593999147 | 8.742% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2019-12-30 | 0 | 36382947.09 | 254034528.11 | 238487587.88 | 15546940.23 | 593999147 | 2.617% |  |  |  | cash out both |  |  |  | 2019 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-01-30 | 2318161.39 | 1662180.52 | 256352689.5 | 240149768.4 | 16202921.1 | 593999147 | 2.728% |  |  | 2019-11-06 | added cash in 3 |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-02-28 | 1641130.16 | 5506362.99 | 257993819.66 | 245656131.39 | 12337688.27 | 593999147 | 2.077% |  |  | 2019-11-20 | added cash in 3 |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-03-30 | 0 | 2412972.58 | 257993819.66 | 248069103.97 | 9924715.69 | 593999147 | 1.671% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-04-30 | 1116423 | 626612.03 | 259110242.66 | 248695716 | 10414526.66 | 593999147 | 1.753% |  |  | 2019-12-31 | added cash in 3 |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-05-30 | 0 | 2607589.67 | 259110242.66 | 251303305.67 | 7806936.99 | 593999147 | 1.314% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-06-30 | 0 | 667921 | 259110242.66 | 251971226.67 | 7139015.99 | 593999147 | 1.202% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-07-30 | 0 | 576178.49 | 259110242.66 | 252547405.16 | 6562837.5 | 593999147 | 1.105% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-08-30 | 1515470 | 876386.26 | 260625712.66 | 253423791.42 | 7201921.24 | 593999147 | 1.212% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-09-30 | 0 | 323916.91 | 260625712.66 | 253747708.33 | 6878004.33 | 593999147 | 1.158% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-10-30 | 0 | 536658.84 | 260625712.66 | 254284367.17 | 6341345.49 | 593999147 | 1.068% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-11-30 | 6845790.37 | 381529 | 267471503.03 | 254665896.17 | 12805606.86 | 593999147 | 2.156% |  |  |  | cash out both |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2020-12-30 | 0 | 1152793.29 | 267471503.03 | 255818689.46 | 11652813.57 | 593999147 | 1.962% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2020 | Commercial | University | Sewedy
El Sewedy University 1 | 2021-01-30 | 0 | 920651.81 | 267471503.03 | 256739341.27 | 10732161.76 | 593999147 | 1.807% |  |  |  | cash out both |  |  |  | 2021 | Commercial | University | Sewedy
El Sewedy University 1 | 2021-02-28 | 0 | 3484781.76 | 267471503.03 | 260224123.03 | 7247380 | 593999147 | 1.22% |  |  | 2021-01-31 | added cash in 3 |  |  |  | 2021 | Commercial | University | Sewedy
El Sewedy University 1 | 2021-03-30 | 1077484.48 | 953751.25 | 268548987.51 | 261177874.28 | 7371113.23 | 593999147 | 1.241% |  |  |  | cash out both |  |  |  | 2021 | Commercial | University | Sewedy
El Sewedy University 1 | 2021-04-30 | 0 | 117070.54 | 268548987.51 | 261294944.82 | 7254042.69 | 593999147 | 1.221% |  |  |  | cash out both |  |  |  | 2021 | Commercial | University | Sewedy
81 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Mehwar El Salam Axis L&L | 2019-12-30 | 0 | 235890.58 | 0 | 235890.58 | -235890.58 | 16843027 | -1.401% |  |  |  | cash out both |  |  |  | 2019 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-01-30 | 0 | 316868.75 | 0 | 552759.33 | -552759.33 | 16843027 | -3.282% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-02-28 | 0 | 692970.01 | 0 | 1245729.34 | -1245729.34 | 16843027 | -7.396% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-03-30 | 0 | 78544 | 0 | 1324273.34 | -1324273.34 | 16843027 | -7.862% |  |  | 2018-05-08 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-04-30 | 0 | 221945.5 | 0 | 1546218.84 | -1546218.84 | 16843027 | -9.18% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-05-30 | 0 | 189351.98 | 0 | 1735570.82 | -1735570.82 | 16843027 | -10.3% |  |  | 2018-06-10 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-06-30 | 0 | 19303 | 0 | 1754873.82 | -1754873.82 | 16843027 | -10.42% |  |  | 2018-06-28 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-08-30 | 0 | 181000 | 0 | 1935873.82 | -1935873.82 | 16843027 | -11.49% |  |  | 2018-06-30 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-09-30 | 0 | 290812.5 | 0 | 2226686.32 | -2226686.32 | 16843027 | -13.22% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-10-30 | 0 | 1400 | 0 | 2228086.32 | -2228086.32 | 16843027 | -13.23% |  |  | 2018-07-24 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2020-11-30 | 0 | 7612.81 | 0 | 2235699.13 | -2235699.13 | 16843027 | -13.27% |  |  | 2018-07-31 | added cash in 3 |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2021-01-30 | 0 | 18803.2 | 0 | 2254502.33 | -2254502.33 | 16843027 | -13.39% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
Mehwar El Salam Axis L&L | 2021-03-30 | 0 | 14043.58 | 0 | 2268545.91 | -2268545.91 | 16843027 | -13.47% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2021 | Infrastructure | L&L | Army Forces
82 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Hegaz Square Bridge | 2019-12-30 | 0 | 270914.04 | 0 | 270914.04 | -270914.04 | 138370050 | -0.1958% |  |  | 2018-08-31 | added cash in 3 |  |  |  | 2019 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-01-30 | 0 | 1764668.39 | 0 | 2035582.43 | -2035582.43 | 138370050 | -1.471% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-02-28 | 0 | 13273301.11 | 0 | 15308883.54 | -15308883.54 | 138370050 | -11.06% |  |  | 2018-09-30 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-03-30 | 40000000 | 9584322.98 | 40000000 | 24893206.52 | 15106793.48 | 138370050 | 10.92% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-04-30 | 0 | 2279323.76 | 40000000 | 27172530.28 | 12827469.72 | 138370050 | 9.27% |  |  | 2018-10-18 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-05-30 | 18649995 | 1894887.1 | 58649995 | 29067417.38 | 29582577.62 | 138370050 | 21.38% |  |  | 2018-10-29 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-06-30 |  | 58403807.8 | 58649995 | 87471225.18 | -28821230.18 | 138370050 | -20.83% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-07-30 | 0 | 2386717.32 | 58649995 | 89857942.5 | -31207947.5 | 138370050 | -22.55% |  |  | 2018-11-13 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-08-30 | 0 | 24538.52 | 58649995 | 89882481.02 | -31232486.02 | 138370050 | -22.57% |  |  | 2018-11-26 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-09-30 | 0 | 487977.17 | 58649995 | 90370458.19 | -31720463.19 | 138370050 | -22.92% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-10-30 | 0 | 14092.29 | 58649995 | 90384550.48 | -31734555.48 | 138370050 | -22.93% |  |  | 2018-12-10 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-11-30 | 0 | 117488.53 | 58649995 | 90502039.01 | -31852044.01 | 138370050 | -23.02% |  |  | 2018-12-19 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2020-12-30 |  | 961582 | 58649995 | 91463621.01 | -32813626.01 | 138370050 | -23.71% |  |  | 2018-12-31 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2021-01-30 | 0 | 214700 | 58649995 | 91678321.01 | -33028326.01 | 138370050 | -23.87% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2021-02-28 | 0 | 5947.45 | 58649995 | 91684268.46 | -33034273.46 | 138370050 | -23.87% |  |  | 2019-01-03 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
El Hegaz Square Bridge | 2021-03-30 | 0 | 356498.4 | 58649995 | 92040766.86 | -33390771.86 | 138370050 | -24.13% |  |  | 2019-01-17 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
83 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Ring Road | 2020-01-30 | 0 | 98517 | 0 | 98517 | -98517 | 524000000 | -0.0188% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-02-28 | 0 | 3036236.37 | 0 | 3134753.37 | -3134753.37 | 524000000 | -0.5982% |  |  | 2019-02-14 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-03-30 | 0 | 3845631.15 | 0 | 6980384.52 | -6980384.52 | 524000000 | -1.332% |  |  | 2019-02-27 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-04-30 | 0 | 1363317.62 | 0 | 8343702.14 | -8343702.14 | 524000000 | -1.592% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-05-30 | 0 | 1763082.3 | 0 | 10106784.44 | -10106784.44 | 524000000 | -1.929% |  |  | 2019-03-18 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-06-30 | 0 | 5817775.87 | 0 | 15924560.31 | -15924560.31 | 524000000 | -3.039% |  |  | 2019-03-31 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-07-30 | 0 | 5770969.29 | 0 | 21695529.6 | -21695529.6 | 524000000 | -4.14% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-08-30 | 0 | 5756969.29 | 0 | 27452498.89 | -27452498.89 | 524000000 | -5.239% |  |  | 2019-04-08 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-09-30 | 0 | 5775714.12 | 0 | 33228213.01 | -33228213.01 | 524000000 | -6.341% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-10-30 | 34159591.2 | 5851160.32 | 34159591.2 | 39079373.33 | -4919782.13 | 524000000 | -0.9389% |  |  | 2019-05-06 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-11-30 | 0 | 11476177.89 | 34159591.2 | 50555551.22 | -16395960.02 | 524000000 | -3.129% | [8 empty] | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2020-12-30 | 15945365.65 | 9010795.73 | 50104956.85 | 59566346.95 | -9461390.1 | 524000000 | -1.806% |  |  | 2019-05-30 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2021-01-30 | 0 | 13650887.5 | 50104956.85 | 73217234.45 | -23112277.6 | 524000000 | -4.411% |  |  | 2019-05-31 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2021-02-28 | 7157243.6 | 30443071.44 | 57262200.45 | 103660305.89 | -46398105.44 | 524000000 | -8.855% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2021-03-30 | 61000924.3 | 32321661.3 | 118263124.75 | 135981967.19 | -17718842.44 | 524000000 | -3.381% |  |  | 2019-06-03 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
Ring Road | 2021-04-30 | 6026340.35 | 15175490.42 | 124289465.1 | 151157457.61 | -26867992.51 | 524000000 | -5.127% |  |  | 2019-06-18 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
84 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Marina Inland Marassi Pkg 162 | 2020-01-30 | 0 | 1128089.7 | 0 | 1128089.7 | -1128089.7 | 434504076.4286 | -0.2596% |  |  | 2019-06-27 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-02-28 | 7681619.5 | 4666410 | 7681619.5 | 5794499.7 | 1887119.8 | 434504076.4286 | 0.4343% |  |  | 2019-06-30 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-03-30 | 24950583 | 2473992.92 | 32632202.5 | 8268492.62 | 24363709.88 | 434504076.4286 | 5.607% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-04-30 | 12914325.86 | 1512801.08 | 45546528.36 | 9781293.7 | 35765234.66 | 434504076.4286 | 8.231% |  |  | 2019-07-31 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-05-30 | 6336538.23 | 1666357.85 | 51883066.59 | 11447651.55 | 40435415.04 | 434504076.4286 | 9.306% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-06-30 | 6124877.69 | 5500379.1 | 58007944.28 | 16948030.65 | 41059913.63 | 434504076.4286 | 9.45% |  |  | 2019-08-07 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-07-30 | 4824045.39 | 5818137.37 | 62831989.67 | 22766168.02 | 40065821.65 | 434504076.4286 | 9.221% |  |  | 2019-08-31 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-08-30 | 8284840.64 | 5975447.82 | 71116830.31 | 28741615.84 | 42375214.47 | 434504076.4286 | 9.753% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-09-30 | 13235412.66 | 7587470.83 | 84352242.97 | 36329086.67 | 48023156.3 | 434504076.4286 | 11.05% |  |  | 2019-09-03 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-10-30 | 18397733.92 | 9409439.63 | 102749976.89 | 45738526.3 | 57011450.59 | 434504076.4286 | 13.12% |  |  | 2019-09-18 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-11-30 | 5726760.54 | 9587251.93 | 108476737.43 | 55325778.23 | 53150959.2 | 434504076.4286 | 12.23% |  |  | 2019-09-30 | added cash in 3 |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2020-12-30 | 19697511.7 | 8842500.9 | 128174249.13 | 64168279.13 | 64005970 | 434504076.4286 | 14.73% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2021-01-30 | 12762378.98 | 7627418.88 | 140936628.11 | 71795698.01 | 69140930.1 | 434504076.4286 | 15.91% |  |  | 2019-10-03 | added cash in 3 |  |  |  | 2021 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2021-02-28 | 11696963.41 | 6120541.8 | 152633591.52 | 77916239.81 | 74717351.71 | 434504076.4286 | 17.2% |  |  | 2019-10-07 | added cash in 3 |  |  |  | 2021 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2021-03-30 | 9424694.44 | 8046612.33 | 162058285.96 | 85962852.14 | 76095433.82 | 434504076.4286 | 17.51% |  |  | 2019-10-31 | added cash in 3 |  |  |  | 2021 | Infrastructure | Port | EMAAR
Marina Inland Marassi Pkg 162 | 2021-04-30 | 25624984.42 | 4411293.55 | 187683270.38 | 90374145.69 | 97309124.69 | 434504076.4286 | 22.4% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Port | EMAAR
85 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sultana Malek Restoration | 2020-01-30 | 0 | 16540 | 0 | 16540 | -16540 | 85000000 | -0.01946% |  |  | 2019-11-30 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-02-28 | 0 | 14220 | 0 | 30760 | -30760 | 85000000 | -0.03619% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-03-30 | 0 | 30600 | 0 | 61360 | -61360 | 85000000 | -0.07219% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-04-30 | 0 | 30380 | 0 | 91740 | -91740 | 85000000 | -0.1079% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-05-30 | 0 | 23335.4 | 0 | 115075.4 | -115075.4 | 85000000 | -0.1354% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-06-30 | 0 | 108108.14 | 0 | 223183.54 | -223183.54 | 85000000 | -0.2626% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-07-30 | 0 | 311190.27 | 0 | 534373.81 | -534373.81 | 85000000 | -0.6287% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-08-30 | 0 | 85920 | 0 | 620293.81 | -620293.81 | 85000000 | -0.7298% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-09-30 | 0 | 593138.44 | 0 | 1213432.25 | -1213432.25 | 85000000 | -1.428% |  |  | 2020-06-10 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-10-30 | 0 | 508574.4 | 0 | 1722006.65 | -1722006.65 | 85000000 | -2.026% |  |  | 2020-06-30 | added cash in 3 |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-11-30 | 0 | 905343.87 | 0 | 2627350.52 | -2627350.52 | 85000000 | -3.091% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2020-12-30 | 0 | 976595.58 | 0 | 3603946.1 | -3603946.1 | 85000000 | -4.24% |  |  |  | cash out both |  |  |  | 2020 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2021-01-30 | 0 | 1282427.41 | 0 | 4886373.51 | -4886373.51 | 85000000 | -5.749% |  |  |  | cash out both |  |  |  | 2021 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2021-02-28 | 0 | 1426985.94 | 0 | 6313359.45 | -6313359.45 | 85000000 | -7.427% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2021 | Restoration | Palace | Army Forces
Sultana Malek Restoration | 2021-03-30 | 0 | 2012452.83 | 0 | 8325812.28 | -8325812.28 | 85000000 | -9.795% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2021 | Restoration | Palace | Army Forces
86 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Lekela 250MW Wind Farm | 2020-01-30 | 0 | 8241322.4 | 0 | 8241322.4 | -8241322.4 | 182442342 | -4.517% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-02-28 | 36300000 | 2074558.62 | 36300000 | 10315881.02 | 25984118.98 | 182442342 | 14.24% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-03-30 | 0 | 1445743.92 | 36300000 | 11761624.94 | 24538375.06 | 182442342 | [8 empty] | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-04-30 | 0 | 3702586.57 | 36300000 | 15464211.51 | 20835788.49 | 182442342 | 11.42% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-05-30 | 0 | 1619505.72 | 36300000 | 17083717.23 | 19216282.77 | 182442342 | 10.53% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-06-30 | 0 | 3604695.98 | 36300000 | 20688413.21 | 15611586.79 | 182442342 | 8.557% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-07-30 | 0 | 7498509.9 | 36300000 | 28186923.11 | 8113076.89 | 182442342 | 4.447% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-08-30 | 0 | 2993438.1 | 36300000 | 31180361.21 | 5119638.79 | 182442342 | 2.806% |  |  | 2018-08-14 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-09-30 | 0 | 6162204.69 | 36300000 | 37342565.9 | -1042565.9 | 182442342 | -0.5714% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-10-30 | 5150642.96 | 11207255.13 | 41450642.96 | 48549821.03 | -7099178.07 | 182442342 | -3.891% |  |  | 2018-09-17 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-11-30 | 7219185.77 | 15709758.46 | 48669828.73 | 64259579.49 | -15589750.76 | 182442342 | -8.545% |  |  |  | cash out both |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2020-12-30 | 0 | 9220501.36 | 48669828.73 | 73480080.85 | -24810252.12 | 182442342 | -13.6% |  |  | 2018-10-08 | added cash in 3 |  |  |  | 2020 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2021-01-30 | 0 | 16806547.7 | 48669828.73 | 90286628.55 | -41616799.82 | 182442342 | -22.81% |  |  | 2018-10-09 | added cash in 3 |  |  |  | 2021 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2021-02-28 | 62660387.99 | 15557794.37 | 111330216.72 | 105844422.92 | 5485793.8 | 182442342 | 3.007% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2021-03-30 | 0 | 11323248.16 | 111330216.72 | 117167671.08 | -5837454.36 | 182442342 | -3.2% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Power Plant | GAMESA
Lekela 250MW Wind Farm | 2021-04-30 | 40304357.7 | 4502321.5 | 151634574.42 | 121669992.58 | 29964581.84 | 182442342 | 16.42% |  |  | 2018-12-02 | added cash in 3 |  |  |  | 2021 | Industrial | Power Plant | GAMESA
87 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
88 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Kayan Landscape | 2019-12-30 | 15494720 | 0 | 15494720 | 0 | 15494720 | 100042648 | 15.49% |  |  | 2019-01-27 | added cash in 3 |  |  |  | 2019 | Infrastructure | Landscape | Army Forces
Kayan Landscape | 2020-03-30 | 0 | 2500000 | 15494720 | 2500000 | 12994720 | 100042648 | 12.99% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Landscape | Army Forces
Kayan Landscape | 2020-04-30 | 0 | 8000000 | 15494720 | 10500000 | 4994720 | 100042648 | 4.993% |  |  | 2019-02-07 | added cash in 3 |  |  |  | 2020 | Infrastructure | Landscape | Army Forces
Kayan Landscape | 2020-06-30 | 95 | 3000000 | 15494815 | 13500000 | 1994815 | 100042648 | 1.994% |  |  | 2019-02-27 | added cash in 3 |  |  |  | 2020 | Infrastructure | Landscape | Army Forces
Kayan Landscape | 2020-07-30 | 0 | 2114917.27 | 15494815 | 15614917.27 | -120102.27 | 100042648 | -0.1201% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Landscape | Army Forces
Kayan Landscape | 2020-08-30 | 0 | 5000000 | 15494815 | 20614917.27 | -5120102.27 | 100042648 | -5.118% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Landscape | Army Forces
89 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Abbas Akkad Bridge | 2020-03-30 | 0 | 815080 | 0 | 815080 | -815080 | 124132580.9524 | -0.6566% |  |  | 2019-04-16 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-04-30 | 0 | 6767355.35 | 0 | 7582435.35 | -7582435.35 | 124132580.9524 | -6.108% |  |  | 2019-04-22 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-05-30 | 20000000 | 10136135.98 | 20000000 | 17718571.33 | 2281428.67 | 124132580.9524 | 1.838% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-06-30 | 0 | 7529622.6 | 20000000 | 25248193.93 | -5248193.93 | 124132580.9524 | -4.228% |  |  | 2019-05-05 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-07-30 | 0 | 2787393.4 | 20000000 | 28035587.33 | -8035587.33 | 124132580.9524 | -6.473% |  |  | 2019-05-09 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-08-30 | 0 | 1496601.58 | 20000000 | 29532188.91 | -9532188.91 | 124132580.9524 | -7.679% |  |  | 2019-05-14 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-09-30 | 0 | 4050574.04 | 20000000 | 33582762.95 | -13582762.95 | 124132580.9524 | -10.94% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-10-30 | 0 | 417215.48 | 20000000 | 33999978.43 | -13999978.43 | 124132580.9524 | -11.28% |  |  | 2019-06-03 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-11-30 | 0 | 2205024.46 | 20000000 | 36205002.89 | -16205002.89 | 124132580.9524 | -13.05% |  |  | 2019-06-26 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2020-12-30 | 0 | 467048.55 | 20000000 | 36672051.44 | -16672051.44 | 124132580.9524 | -13.43% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2021-01-30 | 0 | 846475.2 | 20000000 | 37518526.64 | -17518526.64 | 124132580.9524 | -14.11% |  |  | 2019-07-17 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2021-02-28 | 0 | 5577.45 | 20000000 | 37524104.09 | -17524104.09 | 124132580.9524 | -14.12% |  |  | 2019-07-25 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2021-03-30 | 6904265 | 396178.24 | 26904265 | 37920282.33 | -11016017.33 | 124132580.9524 | -8.874% |  |  | 2019-07-31 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Abbas Akkad Bridge | 2021-04-30 | 0 | 11901.95 | 26904265 | 37932184.28 | -11027919.28 | 124132580.9524 | -8.884% | [8 empty] | Infrastructure | Bridges & Tunnels | Army Forces
90 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Asher Men Ramadan Bridge | 2020-04-30 | 0 | 20000 | 0 | 20000 | -20000 | 93910355 | -0.0213% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-05-30 | 0 | 165208.13 | 0 | 185208.13 | -185208.13 | 93910355 | -0.1972% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-06-30 | 0 | 3536962.07 | 0 | 3722170.2 | -3722170.2 | 93910355 | -3.964% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-07-30 | 0 | 6452555.07 | 0 | 10174725.27 | -10174725.27 | 93910355 | -10.83% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-08-30 | 5299995 | 5777684.12 | 5299995 | 15952409.39 | -10652414.39 | 93910355 | -11.34% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-09-30 | 0 | 4954513.52 | 5299995 | 20906922.91 | -15606927.91 | 93910355 | -16.62% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-10-30 | 0 | 2081097.23 | 5299995 | 22988020.14 | -17688025.14 | 93910355 | -18.84% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-11-30 | 2644030 | 52054475.67 | 7944025 | 75042495.81 | -67098470.81 | 93910355 | -71.45% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2020-12-30 | 3163290 | 2417036.27 | 11107315 | 77459532.08 | -66352217.08 | 93910355 | -70.65% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2021-01-30 | 0 | 1185328.32 | 11107315 | 78644860.4 | -67537545.4 | 93910355 | -71.92% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2021-02-28 | 0 | 47700.77 | 11107315 | 78692561.17 | -67585246.17 | 93910355 | -71.97% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2021-03-30 | 0 | 1274208.85 | 11107315 | 79966770.02 | -68859455.02 | 93910355 | -73.32% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
El Asher Men Ramadan Bridge | 2021-04-30 | 0 | 14430 | 11107315 | 79981200.02 | -68873885.02 | 93910355 | -73.34% | [8 empty] | Infrastructure | Bridges & Tunnels | Army Forces
91 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Kafr Shokr Bridge | 2020-06-30 | 0 | 144438.27 | 0 | 144438.27 | -144438.27 | 147845325 | -0.0977% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2020-07-30 | 0 | 137412.73 | 0 | 281851 | -281851 | 147845325 | -0.1906% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2020-08-30 | 0 | 95962.62 | 0 | 377813.62 | -377813.62 | [9 empty] | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2020-09-30 | 0 | 453037.71 | 0 | 830851.33 | -830851.33 | 147845325 | -0.562% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2020-10-30 | 0 | 4690086.46 | 0 | 5520937.79 | -5520937.79 | 147845325 | -3.734% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2020-11-30 | 2644030 | 2558955.68 | 2644030 | 8079893.47 | -5435863.47 | 147845325 | -3.677% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2020-12-30 | 0 | 2717734.8 | 2644030 | 10797628.27 | -8153598.27 | 147845325 | -5.515% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2021-01-30 | 0 | 6770763.48 | 2644030 | 17568391.75 | -14924361.75 | 147845325 | -10.09% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2021-02-28 | 0 | 11544187.14 | 2644030 | 29112578.89 | -26468548.89 | 147845325 | -17.9% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2021-03-30 | 0 | 10769755.12 | 2644030 | 39882334.01 | -37238304.01 | 147845325 | -25.19% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Kafr Shokr Bridge | 2021-04-30 | 0 | 6883584.06 | 2644030 | 46765918.07 | -44121888.07 | 147845325 | -29.84% | [8 empty] | Infrastructure | Bridges & Tunnels | Army Forces
92 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Al Shorouk Bridge (LRT) | 2020-06-30 | 0 | 13993.86 | 0 | 13993.86 | -13993.86 | 26145782 | -0.05352% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2020-07-30 | 0 | 886685.74 | 0 | 900679.6 | -900679.6 | 26145782 | -3.445% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2020-08-30 | 0 | 1430356.75 | 0 | 2331036.35 | -2331036.35 | 26145782 | -8.916% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2020-09-30 | 0 | 2087514.06 | 0 | 4418550.41 | -4418550.41 | 26145782 | -16.9% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2020-10-30 | 0 | 2772979.71 | 0 | 7191530.12 | -7191530.12 | 26145782 | -27.51% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2020-11-30 | 8000000 | 3467861.27 | 8000000 | 10659391.39 | -2659391.39 | 26145782 | -10.17% |  |  | 2019-07-15 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2020-12-30 | 0 | 2615098.09 | 8000000 | 13274489.48 | -5274489.48 | 26145782 | -20.17% |  |  | 2019-07-25 | added cash in 3 |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2021-01-30 | 3550000 | 3772513 | 11550000 | 17047002.48 | -5497002.48 | 26145782 | -21.02% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2021-02-28 | 2000000 | 813613.25 | 13550000 | 17860615.73 | -4310615.73 | 26145782 | -16.49% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2021-03-30 | 6500000 | 1822182 | 20050000 | 19682797.73 | 367202.27 | 26145782 | 1.404% |  |  | 2019-09-22 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Al Shorouk Bridge (LRT) | 2021-04-30 | 0 | 453989.63 | 20050000 | 20136787.36 | -86787.36 | 26145782 | -0.3319% | [8 empty] | Infrastructure | Bridges & Tunnels | Army Forces
93 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
94 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
GOV2 Infra | 2020-07-30 | 0 | 132750 | 0 | 132750 | -132750 | 650000000 | -0.02042% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2020-09-30 | 0 | 45330.09 | 0 | 178080.09 | -178080.09 | 650000000 | -0.0274% |  |  | 2020-04-30 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2020-10-30 | 0 | 4544678.51 | 0 | 4722758.6 | -4722758.6 | 650000000 | -0.7266% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2020-11-30 | 0 | 264757.88 | 0 | 4987516.48 | -4987516.48 | 650000000 | -0.7673% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2020-12-30 | 0 | 3606552.14 | 0 | 8594068.62 | -8594068.62 | 650000000 | -1.322% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2021-01-30 | 0 | 2631270.59 | 0 | 11225339.21 | -11225339.21 | 650000000 | -1.727% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2021-02-28 | 0 | 5980965.49 | 0 | 17206304.7 | -17206304.7 | 650000000 | -2.647% |  |  | 2020-08-26 | added cash in 3 |  |  |  | 2021 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2021-03-30 | 8793510.21 | 12903968.04 | 8793510.21 | 30110272.74 | -21316762.53 | 650000000 | -3.28% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Networks | Utilities And Urban Communities
GOV2 Infra | 2021-04-30 | 0 | 4241146.91 | 8793510.21 | 34351419.65 | -25557909.44 | 650000000 | -3.932% | [8 empty] | Infrastructure | Networks | Utilities And Urban Communities
95 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Cairo Alex Railroad | 2020-06-30 | 0 | 72323.19 | 0 | 72323.19 | -72323.19 | 967000000 | -0.007479% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2020 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2020-08-30 | 0 | 209295.88 | 0 | 281619.07 | -281619.07 | 967000000 | -0.02912% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2020-09-30 | 0 | 339516.03 | 0 | 621135.1 | -621135.1 | 967000000 | -0.06423% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2020-10-30 | 144582383 | 668422 | 144582383 | 1289557.1 | 143292825.9 | [9 empty] | 2020 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2020-11-30 | 0 | 8315728 | 144582383 | 9605285.1 | 134977097.9 | 967000000 | 13.96% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2020 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2020-12-30 | 0 | 22916576 | 144582383 | 32521861.1 | 112060521.9 | 967000000 | 11.59% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2020 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2021-01-30 | 0 | 4759014 | 144582383 | 37280875.1 | 107301507.9 | 967000000 | 11.1% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2021 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2021-02-28 | 0 | 7869857 | 144582383 | 45150732.1 | 99431650.9 | 967000000 | 10.28% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2021-03-30 | 5025720.35 | 7601011 | 149608103.35 | 52751743.1 | 96856360.25 | 967000000 | 10.02% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Railway | ENR
Cairo Alex Railroad | 2021-04-30 | 3883856.25 | 11883128 | 153491959.6 | 64634871.1 | 88857088.5 | 967000000 | 9.189% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Railway | ENR
96 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Hassan El Mamoun Bridge | 2020-07-30 | 0 | 9252.13 | 0 | 9252.13 | -9252.13 | 93800000 | -0.009864% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2020-08-30 | 0 | 7680664.25 | 0 | 7689916.38 | -7689916.38 | 93800000 | -8.198% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2020-09-30 | 0 | 6632324.54 | 0 | 14322240.92 | -14322240.92 | 93800000 | -15.27% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2020-10-30 | 0 | 7512810.37 | 0 | 21835051.29 | -21835051.29 | 93800000 | -23.28% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2020-11-30 | 0 | 5039532.75 | 0 | 26874584.04 | -26874584.04 | 93800000 | -28.65% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2020-12-30 |  | 40296802.38 | 0 | 67171386.42 | -67171386.42 | 93800000 | -71.61% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2021-01-30 |  | 1900639.03 | 0 | 69072025.45 | -69072025.45 | 93800000 | -73.64% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2021-02-28 | 4682080 | 684739.23 | 4682080 | 69756764.68 | -65074684.68 | 93800000 | -69.38% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2021-03-30 | 1893795 | 1589632.58 | 6575875 | 71346397.26 | -64770522.26 | 93800000 | -69.05% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Army Forces
Hassan El Mamoun Bridge | 2021-04-30 | 0 | 492857.47 | 6575875 | 71839254.73 | -65263379.73 | 93800000 | -69.58% | [8 empty] | Infrastructure | Bridges & Tunnels | Army Forces
97 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sherouk Bridge L&L | 2020-09-30 | 0 | 354746.03 | 0 | 354746.03 | -354746.03 | 1000000 | -35.47% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | L&L | Army Forces
Sherouk Bridge L&L | 2021-02-28 | 0 | 149697.02 | 0 | 504443.05 | -504443.05 | 1000000 | -50.44% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
Sherouk Bridge L&L | 2021-03-30 | 0 | 102459.16 | 0 | 606902.21 | -606902.21 | 1000000 | -60.69% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | L&L | Army Forces
98 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Ora Zed Park 1B Pkgs A&D | 2020-09-30 | 0 | 50000 | 0 | 50000 | -50000 | 870293108 | -0.005745% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Ora
Ora Zed Park 1B Pkgs A&D | 2020-10-30 | 0 | 10893838.44 | 0 | 10943838.44 | -10943838.44 | 870293108 | -1.257% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Ora
Ora Zed Park 1B Pkgs A&D | 2020-11-30 | 91380773 | 15350524.19 | 91380773 | 26294362.63 | 65086410.37 | 870293108 | 7.479% |  |  | 2021-01-31 | added cash in 3 |  |  |  | 2020 | Residential | Residential | Ora
Ora Zed Park 1B Pkgs A&D | 2020-12-30 | 0 | 2449570.66 | 91380773 | 28743933.29 | 62636839.71 | [9 empty] | 2020 | Residential | Residential | Ora
Ora Zed Park 1B Pkgs A&D | 2021-01-30 | 0 | 35398773.5 | 91380773 | 64142706.79 | 27238066.21 | 870293108 | 3.13% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Ora
Ora Zed Park 1B Pkgs A&D | 2021-02-28 | 9787286.79 | 41396673.79 | 101168059.79 | 105539380.58 | -4371320.79 | 870293108 | -0.5023% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Ora
Ora Zed Park 1B Pkgs A&D | 2021-03-30 | 0 | 24538405.3 | 101168059.79 | 130077785.88 | -28909726.09 | 870293108 | -3.322% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Ora
Ora Zed Park 1B Pkgs A&D | 2021-04-30 | 0 | 11683651.5 | 101168059.79 | 141761437.38 | -40593377.59 | 870293108 | -4.664% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Ora
99 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Kattameya Creeks | 2020-11-30 | 0 | 1557075.8 | 0 | 1557075.8 | -1557075.8 | 1462000000 | -0.1065% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Starlight
Kattameya Creeks | 2020-12-30 | 0 | 328448.53 | 0 | 1885524.33 | -1885524.33 | 1462000000 | -0.129% |  |  |  | cash out both |  |  |  | 2020 | Residential | Residential | Starlight
Kattameya Creeks | 2021-01-30 | 200000000 | 6724969.81 | 200000000 | 8610494.14 | 191389505.86 | 1462000000 | 13.09% |  |  | 2018-09-17 | added cash in 3 |  |  |  | 2021 | Residential | Residential | Starlight
Kattameya Creeks | 2021-02-28 | 0 | 44281805.86 | 200000000 | 52892300 | 147107700 | 1462000000 | 10.06% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Starlight
Kattameya Creeks | 2021-03-30 | 14043961.23 | 14656144.88 | 214043961.23 | 67548444.88 | 146495516.35 | 1462000000 | 10.02% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Starlight
Kattameya Creeks | 2021-04-30 | 0 | 21505730.62 | 214043961.23 | 89054175.5 | 124989785.73 | 1462000000 | 8.549% |  |  |  | cash out both |  |  |  | 2021 | Residential | Residential | Starlight
100 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Mansoura University Faculty of Medicine | 2021-01-30 | 0 | 50000 | 0 | 50000 | -50000 | 219047619.0476 | -0.02283% |  |  |  | cash out both |  |  |  | 2021 | Commercial | University | Utilities And Urban Communities
Mansoura University Faculty of Medicine | 2021-02-28 | 0 | 1066750 | 0 | 1116750 | -1116750 | 219047619.0476 | -0.5098% | [8 empty] | Commercial | University | Utilities And Urban Communities
Mansoura University Faculty of Medicine | 2021-03-30 | 0 | 225964 | 0 | 1342714 | -1342714 | 219047619.0476 | -0.613% |  |  | 2018-12-31 | added cash in 3 |  |  |  | 2021 | Commercial | University | Utilities And Urban Communities
Mansoura University Faculty of Medicine | 2021-04-30 | 0 | 3484695 | 0 | 4827409 | -4827409 | 219047619.0476 | -2.204% |  |  | 2018-12-31 | added cash in 3 |  |  |  | 2021 | Commercial | University | Utilities And Urban Communities
101 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Diplomatic District - Infra | 2020-11-30 | 0 | 3644 | 0 | 3644 | -3644 | 390000000 | -0.0009344% |  |  | 2019-01-09 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | Utilities And Urban Communities
Diplomatic District - Infra | 2020-12-30 | 0 | 91660 | 0 | 95304 | -95304 | 390000000 | -0.02444% | [8 empty] | Infrastructure | Networks | Utilities And Urban Communities
Diplomatic District - Infra | 2021-01-30 | 0 | 132894.98 | 0 | 228198.98 | -228198.98 | 390000000 | -0.05851% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Networks | Utilities And Urban Communities
Diplomatic District - Infra | 2021-02-28 | 0 | 130938.74 | 0 | 359137.72 | -359137.72 | 390000000 | -0.09209% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Networks | Utilities And Urban Communities
Diplomatic District - Infra | 2021-03-30 | 0 | 2192834.59 | 0 | 2551972.31 | -2551972.31 | 390000000 | -0.6544% |  |  | 2019-03-07 | added cash in 3 |  |  |  | 2021 | Infrastructure | Networks | Utilities And Urban Communities
Diplomatic District - Infra | 2021-04-30 | 20000000 | 1104518.33 | 20000000 | 3656490.64 | 16343509.36 | 390000000 | 4.191% |  |  | 2019-03-14 | added 1 |  |  |  | 2021 | Infrastructure | Networks | Utilities And Urban Communities
102 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Sewedy CFC HQ Internal Finishing | 2020-12-30 | 103231218.3 | 197751.09 | 103231218.3 | 197751.09 | 103033467.21 | 327718153.3333 | 31.44% |  |  |  | cash out both |  |  |  | 2020 | Commercial | Offices & Mall | Sewedy
El Sewedy CFC HQ Internal Finishing | 2021-01-30 | 0 | 445163.16 | 103231218.3 | 642914.25 | 102588304.05 | 327718153.3333 | 31.3% |  |  | 2019-04-30 | added 1 |  |  |  | 2021 | Commercial | Offices & Mall | Sewedy
El Sewedy CFC HQ Internal Finishing | 2021-02-28 | 0 | 43409152.65 | 103231218.3 | 44052066.9 | 59179151.4 | 327718153.3333 | 18.06% |  |  |  | cash out both |  |  |  | 2021 | Commercial | Offices & Mall | Sewedy
El Sewedy CFC HQ Internal Finishing | 2021-03-30 | 6847513.64 | 4048790.46 | 110078731.94 | 48100857.36 | 61977874.58 | 327718153.3333 | 18.91% |  |  | 2019-05-05 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | Sewedy
El Sewedy CFC HQ Internal Finishing | 2021-04-30 | 8021127.82 | 1704514.83 | 118099859.76 | 49805372.19 | 68294487.57 | 327718153.3333 | 20.84% |  |  | 2019-05-19 | added cash in 3 |  |  |  | 2021 | Commercial | Offices & Mall | Sewedy
103 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Lagoon Discharge Pkg 178 | 2021-01-30 | 0 | 976942.63 | 0 | 976942.63 | -976942.63 | 40449240 | -2.415% |  |  | 2019-06-02 | added 1 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | EMAAR
Lagoon Discharge Pkg 178 | 2021-02-28 | 3747170.2 | 2082179.42 | 3747170.2 | 3059122.05 | 688048.15 | 40449240 | 1.701% |  |  | 2019-06-16 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | EMAAR
Lagoon Discharge Pkg 178 | 2021-03-30 | 0 | 2359368.15 | 3747170.2 | 5418490.2 | -1671320 | 40449240 | -4.132% |  |  | 2019-06-16 | added cash in 3 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | EMAAR
Lagoon Discharge Pkg 178 | 2021-04-30 | 0 | 2345473.65 | 3747170.2 | 5404595.7 | -1657425.5 | 40449240 | -4.098% |  |  | 2019-06-25 | added 1 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | EMAAR
104 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Khatatba Bridge | 2021-02-28 | 0 | 256400 | 0 | 256400 | -256400 | 142857142.8571 | -0.1795% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
El Khatatba Bridge | 2021-03-30 | 0 | 263175 | 0 | 519575 | -519575 | 142857142.8571 | -0.3637% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
El Khatatba Bridge | 2021-04-30 | 0 | 251950.12 | 0 | 508350.12 | -508350.12 | 142857142.8571 | -0.3558% |  |  | 2019-07-02 | added 1 |  |  |  | 2021 | Infrastructure | Bridges & Tunnels | Roads and Bridges Authority
105 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
EGAT Pelletizing Plant | 2021-02-28 | 10000000 | 30000 | 10000000 | 30000 | 9970000 | 375000000 | 2.659% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Factory | Elco Suez
EGAT Pelletizing Plant | 2021-04-30 | 2000000 | 170923.62 | 12000000 | 200923.62 | 11799076.38 | 375000000 | 3.146% |  |  | 2019-08-08 | added cash in 3 |  |  |  | 2021 | Industrial | Factory | Elco Suez
106 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
MDF Factory | 2021-03-30 | 0 | 168477 | 0 | 168477 | -168477 | 175000000 | -0.09627% |  |  |  | cash out both |  |  |  | 2021 | Industrial | Factory | Naile Wood
MDF Factory | 2021-04-30 | 41622365.4 | 8320400.87 | 41622365.4 | 8488877.87 | 33133487.53 | 175000000 | 18.93% |  |  | 2019-09-17 | added 1 |  |  |  | 2021 | Industrial | Factory | Naile Wood
107 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Aeon Towers Chiller Building | 2020-10-30 | 1264914.16 | 0 | 1264914.16 | 0 | 1264914.16 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Aeon Towers Chiller Building | 2021-01-30 | 1513146.56 | 0 | 2778060.72 | 0 | 2778060.72 | 0 | #DIV/0! |  |  | 2019-10-15 | added 1 |  |  |  | 2021 | #N/A | #N/A | #N/A
Aeon Towers Chiller Building | 2021-02-28 | 780253.07 | 0 | 3558313.79 | 0 | 3558313.79 | 0 | #DIV/0! |  |  | 2019-10-20 | added cash in 3 |  |  |  | 2021 | #N/A | #N/A | #N/A
108 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Alegria DP Port | 2015-01-30 | 6624155 | 1653901 | 6624155 | 1653901 | 4970254 | 605714038 | 0.8206% |  |  | 2019-11-17 | added 1 |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-02-28 | 0 | 3194973 | 6624155 | 4848874 | 1775281 | 605714038 | 0.2931% |  |  | 2019-11-20 | added cash in 3 |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-03-30 | 5764258 | 4333570 | 12388413 | 9182444 | 3205969 | 605714038 | 0.5293% |  |  | 2019-11-21 | added 1 |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-04-30 | 0 | 1907111 | 12388413 | 11089555 | 1298858 | 605714038 | 0.2144% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-05-30 | 2259233 | 1875177 | 14647646 | 12964732 | 1682914 | 605714038 | 0.2778% |  |  | 2019-12-22 | added 1 |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-06-30 | 1216788 | 1691561 | 15864434 | 14656293 | 1208141 | 605714038 | 0.1995% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-07-30 | 2012370 | 2677365 | 17876804 | 17333658 | 543146 | 605714038 | 0.08967% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-08-30 | 0 | 2088743 | 17876804 | 19422401 | -1545597 | 605714038 | -0.2552% |  |  | 2020-02-09 | added 1 |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-09-30 | 2832049 | 1169364 | 20708853 | 20591765 | 117088 | 605714038 | 0.01933% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-10-30 | 4806304 | 1471310 | 25515157 | 22063075 | 3452082 | 605714038 | 0.5699% |  |  | 2020-03-19 | added 1 |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-11-30 | 0 | 841116 | 25515157 | 22904191 | 2610966 | 605714038 | 0.4311% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2015-12-30 | 2152237 | 1936416 | 27667394 | 24840607 | 2826787 | 605714038 | 0.4667% |  |  | 2020-04-09 | added 1 |  |  |  | 2015 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-01-30 | 0 | 409440 | 27667394 | 25250047 | 2417347 | 605714038 | 0.3991% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-02-28 | 0 | 468487 | 27667394 | 25718534 | 1948860 | 605714038 | 0.3217% |  |  | 2020-05-04 | added 1 |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-03-30 | 815274 | 255404 | 28482668 | 25973938 | 2508730 | 605714038 | 0.4142% |  |  | 2020-05-20 | added 1 |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-04-30 | 0 | 298449 | 28482668 | 26272387 | 2210281 | 605714038 | 0.3649% |  |  | 2020-05-26 | added 1 |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-05-30 | 2680004 | 459076 | 31162672 | 26731463 | 4431209 | 605714038 | 0.7316% |  |  | 2020-05-31 | added cash in 3 |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-06-30 | 0 | 530927 | 31162672 | 27262390 | 3900282 | 605714038 | 0.6439% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-07-30 | 0 | 1086772 | 31162672 | 28349162 | 2813510 | 605714038 | 0.4645% |  |  | 2020-06-07 | added 1 |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-09-30 | 0 | 74351 | 31162672 | 28423513 | 2739159 | 605714038 | 0.4522% |  |  | 2020-06-08 | added 1 |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-10-30 | 0 | 56431 | 31162672 | 28479944 | 2682728 | 605714038 | 0.4429% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2016-11-30 | 1723207 | 0 | 32885879 | 28479944 | 4405935 | 605714038 | 0.7274% |  |  | 2020-07-13 | added 1 |  |  |  | 2016 | Infrastructure | Networks | DPW
Alegria DP Port | 2019-10-30 | 0 | 8277.12 | 32885879 | 28488221.12 | 4397657.88 | 605714038 | 0.726% |  |  | 2020-07-14 | added 1 |  |  |  | 2019 | Infrastructure | Networks | DPW
Alegria DP Port | 2019-11-30 | 0 | 283548.59 | 32885879 | 28771769.71 | 4114109.29 | 605714038 | 0.6792% |  |  | 2020-07-22 | added 1 |  |  |  | 2019 | Infrastructure | Networks | DPW
Alegria DP Port | 2019-12-30 | 0 | 232093.13 | 32885879 | 29003862.84 | 3882016.16 | 605714038 | 0.6409% |  |  | 2020-07-31 | added cash in 3 |  |  |  | 2019 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-02-28 | 0 | 252905.76 | 32885879 | 29256768.6 | 3629110.4 | 605714038 | 0.5991% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-03-30 | 0 | 1510.08 | 32885879 | 29258278.68 | 3627600.32 | 605714038 | 0.5989% |  |  | 2020-08-06 | added 1 |  |  |  | 2020 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-04-30 | 0 | 17245.91 | 32885879 | 29275524.59 | 3610354.41 | 605714038 | 0.596% |  |  | 2020-08-31 | added 1 |  |  |  | 2020 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-05-30 | 0 | 244429.03 | 32885879 | 29519953.62 | 3365925.38 | 605714038 | 0.5557% |  |  |  | cash out both |  |  |  | 2020 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-06-30 | 0 | 17755.91 | 32885879 | 29537709.53 | 3348169.47 | 605714038 | 0.5528% |  |  | 2020-09-02 | added cash in 3 |  |  |  | 2020 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-07-30 | 0 | 237541.6 | 32885879 | 29775251.13 | 3110627.87 | 605714038 | 0.5135% |  |  | 2020-09-08 | added 1 |  |  |  | 2020 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-08-30 | 0 | 253826.25 | 32885879 | 30029077.38 | 2856801.62 | 605714038 | 0.4716% |  |  | 2020-09-20 | added 1 |  |  |  | 2020 | Infrastructure | Networks | DPW
Alegria DP Port | 2020-09-30 | 0 | 76774.85 | 32885879 | 30105852.23 | 2780026.77 | 605714038 | 0.459% |  |  | 2020-10-01 | added 1 |  |  |  | 2020 | Infrastructure | Networks | DPW
109 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
110 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-01-30 | 0 | 41550 | 0 | 41550 | -41550 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-03-30 | 0 | 102318 | 0 | 143868 | -143868 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-04-30 | 0 | 442386 | 0 | 586254 | -586254 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-05-30 | 0 | 2317224 | 0 | 2903478 | -2903478 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-06-30 | 62880564 | 3783562 | 62880564 | 6687040 | 56193524 | #N/A | #N/A |  |  | 2019-01-16 | added cash in 3 |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-07-30 | 0 | 2520105 | 62880564 | 9207145 | 53673419 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-08-30 | 0 | 2682038 | 62880564 | 11889183 | 50991381 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-09-30 | 0 | 2165753 | 62880564 | 14054936 | 48825628 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-10-30 | 0 | 2202561 | 62880564 | 16257497 | 46623067 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-11-30 | 0 | 14771658 | 62880564 | 31029155 | 31851409 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2016-12-30 | 0 | 12434843 | 62880564 | 43463998 | 19416566 | #N/A | #N/A |  |  | 2019-06-09 | added cash in 3 |  |  |  | 2016 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-01-30 | 7678950 | 4851985 | 70559514 | 48315983 | 22243531 | #N/A | #N/A |  |  | 2019-06-25 | added cash in 3 |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-02-28 | 22832552 | 2739979 | 93392066 | 51055962 | 42336104 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-03-30 | 3812636 | 2389640 | 97204702 | 53445602 | 43759100 | #N/A | #N/A |  |  | 2019-07-04 | added cash in 3 |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-04-30 | 3442547 | 9468759 | 100647249 | 62914361 | 37732888 | #N/A | #N/A |  |  | 2019-07-31 | added cash in 3 |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-05-30 | 5999615 | 2501903 | 106646864 | 65416264 | 41230600 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-06-30 | 0 | 2598562 | 106646864 | 68014826 | 38632038 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-07-30 | 0 | 1778655 | 106646864 | 69793481 | 36853383 | #N/A | #N/A |  |  | 2019-09-19 | added cash in 3 |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-08-30 | 17787964 | 2440770 | 124434828 | 72234251 | 52200577 | #N/A | #N/A |  |  | 2019-09-29 | added cash in 3 |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-09-30 | 876288 | 668075 | 125311116 | 72902326 | 52408790 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-10-30 | 4288254 | 2007184 | 129599370 | 74909510 | 54689860 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-11-30 | 10186244 | 807921 | 139785614 | 75717431 | 64068183 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2017 | #N/A | #N/A | #N/A
Alstom-French Station | 2017-12-30 | 2192203 | 268305 | 141977817 | 75985736 | 65992081 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2017 | #N/A | #N/A | #N/A
111 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
112 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
El Mahala Bridge | 2014-01-30 | 0 | 167056.05 | 0 | 167056.05 | -167056.05 | 67245402 | -0.2484% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-02-28 | 0 | 337593.25 | 0 | 504649.3 | -504649.3 | 67245402 | -0.7505% |  |  | 2019-11-04 | added cash in 3 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-03-30 | 0 | 236892.16 | 0 | 741541.46 | -741541.46 | 67245402 | -1.103% |  |  | 2019-11-27 | added cash in 3 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-04-30 | 0 | 406729.32 | 0 | 1148270.78 | -1148270.78 | 67245402 | -1.708% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-05-30 | 0 | 623744.84 | 0 | 1772015.62 | -1772015.62 | 67245402 | -2.635% |  |  | 2019-12-02 | added cash in 3 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-06-30 | 0 | 694547.28 | 0 | 2466562.9 | -2466562.9 | 67245402 | -3.668% |  |  | 2019-12-17 | added cash in 3 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-07-30 | 0 | 1166548.74 | 0 | 3633111.64 | -3633111.64 | 67245402 | -5.403% |  |  | 2019-12-30 | added cash in 3 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-08-30 | 0 | 999419.35 | 0 | 4632530.99 | -4632530.99 | 67245402 | -6.889% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-09-30 | 0 | 1205874.08 | 0 | 5838405.07 | -5838405.07 | 67245402 | -8.682% |  |  | 2020-01-09 | added 1 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-10-30 | 0 | 952769.73 | 0 | 6791174.8 | -6791174.8 | 67245402 | -10.1% |  |  | 2020-01-22 | added 1 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-11-30 | 0 | 2196536.4 | 0 | 8987711.2 | -8987711.2 | 67245402 | -13.37% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2014-12-30 | 13887457 | 3846353.54 | 13887457 | 12834064.74 | 1053392.26 | 67245402 | 1.566% |  |  | 2020-02-09 | added cash in 3 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-01-30 | 3792225 | 2469766 | 17679682 | 15303830.74 | 2375851.26 | 67245402 | 3.533% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-02-28 | 10225673 | 999379 | 27905355 | 16303209.74 | 11602145.26 | 67245402 | 17.25% |  |  | 2020-03-05 | added 1 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-03-30 | 828261 | 2021463 | 28733616 | 18324672.74 | 10408943.26 | 67245402 | 15.48% |  |  | 2020-03-26 | added 1 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-04-30 | 0 | 1796856 | 28733616 | 20121528.74 | 8612087.26 | 67245402 | 12.81% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-05-30 | 0 | 1314563 | 28733616 | 21436091.74 | 7297524.26 | 67245402 | 10.85% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-06-30 | 4569470 | 1127121 | 33303086 | 22563212.74 | 10739873.26 | 67245402 | 15.97% |  |  | 2020-05-04 | added 1 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-07-30 | 0 | 862981 | 33303086 | 23426193.74 | 9876892.26 | 67245402 | 14.69% |  |  | 2020-05-05 | added 1 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-08-30 | 0 | 1148916 | 33303086 | 24575109.74 | 8727976.26 | 67245402 | 12.98% |  |  | 2020-05-14 | added cash in 3 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-09-30 | 0 | 86025 | 33303086 | 24661134.74 | 8641951.26 | 67245402 | 12.85% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-10-30 | 0 | 88349 | 33303086 | 24749483.74 | 8553602.26 | 67245402 | 12.72% |  |  | 2020-06-11 | added 1 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-11-30 | 0 | 27280 | 33303086 | 24776763.74 | 8526322.26 | 67245402 | 12.68% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2015-12-30 | 0 | 32091 | 33303086 | 24808854.74 | 8494231.26 | 67245402 | 12.63% |  |  | 2020-07-13 | added cash in 3 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2016-05-30 | 0 | 690072 | 33303086 | 25498926.74 | 7804159.26 | 67245402 | 11.61% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2016-06-30 | 14775102 | 0 | 48078188 | 25498926.74 | 22579261.26 | 67245402 | 33.58% |  |  | 2020-08-18 | added cash in 3 |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2016-08-30 | 0 | 433350 | 48078188 | 25932276.74 | 22145911.26 | 67245402 | 32.93% |  |  | 2020-09-01 | added 1 |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2016-09-30 | 0 | 25721 | 48078188 | 25957997.74 | 22120190.26 | 67245402 | 32.89% |  |  | 2020-09-13 | added 1 |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | Army Forces
El Mahala Bridge | 2016-10-30 | 0 | 106875 | 48078188 | 26064872.74 | 22013315.26 | 67245402 | 32.74% |  |  | 2020-09-15 | added cash in 3 |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | Army Forces
113 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
114 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Logestica 02 | 2011-09-30 | 534360.87 | 0 | 534360.87 | 0 | 534360.87 | #N/A | #N/A |  |  | 2021-03-04 | added cash in 3 |  |  |  | 2011 | #N/A | #N/A | #N/A
Logestica 02 | 2011-10-30 | 334260.48 | 0 | 868621.35 | 0 | 868621.35 | #N/A | #N/A |  |  | 2021-03-11 | added cash in 3 |  |  |  | 2011 | #N/A | #N/A | #N/A
Logestica 02 | 2011-11-30 | 1006563.08 | 0 | 1875184.43 | 0 | 1875184.43 | #N/A | #N/A |  |  | 2021-03-23 | added cash in 3 |  |  |  | 2011 | #N/A | #N/A | #N/A
Logestica 02 | 2011-12-30 | 1679999.78 | 0 | 3555184.21 | 0 | 3555184.21 | #N/A | #N/A |  |  | 2021-04-04 | added cash in 3 |  |  |  | 2011 | #N/A | #N/A | #N/A
Logestica 02 | 2012-01-30 | 2279316.26 | 0 | 5834500.47 | 0 | 5834500.47 | [9 empty] | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-02-28 | 1901607.28 | 0 | 7736107.75 | 0 | 7736107.75 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-03-30 | 2758362.75 | 0 | 10494470.5 | 0 | 10494470.5 | #N/A | #N/A |  |  | 2018-12-25 | added cash in 3 |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-04-30 | 4207798.04 | 0 | 14702268.54 | 0 | 14702268.54 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-05-30 | 4500000 | 0 | 19202268.54 | 0 | 19202268.54 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-06-30 | 5018951.63 | 0 | 24221220.17 | 0 | 24221220.17 | #N/A | #N/A |  |  | 2019-02-13 | added cash in 3 |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-07-30 | 0 | 0 | 24221220.17 | 0 | 24221220.17 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-08-30 | 2500000 | 0 | 26721220.17 | 0 | 26721220.17 | #N/A | #N/A |  |  | 2019-03-04 | added 1 |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-09-30 | 0 | 0 | 26721220.17 | 0 | 26721220.17 | #N/A | #N/A |  |  | 2019-03-14 | added 1 |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-10-30 | 800000 | 0 | 27521220.17 | 0 | 27521220.17 | #N/A | #N/A |  |  | 2019-03-17 | added cash in 3 |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-11-30 | 2518175.49 | 0 | 30039395.66 | 0 | 30039395.66 | #N/A | #N/A |  |  | 2019-03-26 | added cash in 3 |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2012-12-30 | 2967694.05 | 0 | 33007089.71 | 0 | 33007089.71 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Logestica 02 | 2013-01-30 | 1089297.15 | 0 | 34096386.86 | 0 | 34096386.86 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-02-28 | 1250000 | 0 | 35346386.86 | 0 | 35346386.86 | #N/A | #N/A |  |  | 2019-05-07 | added 1 |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-03-30 | 3053495.58 | 0 | 38399882.44 | 0 | 38399882.44 | #N/A | #N/A |  |  | 2019-05-16 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-04-30 | 2800000 | 0 | 41199882.44 | 0 | 41199882.44 | #N/A | #N/A |  |  | 2019-05-26 | added 1 |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-05-30 | 0 | 0 | 41199882.44 | 0 | 41199882.44 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-06-30 | 1645440.77 | 0 | 42845323.21 | 0 | 42845323.21 | #N/A | #N/A |  |  | 2019-06-03 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-07-30 | 1648683.42 | 0 | 44494006.63 | 0 | 44494006.63 | #N/A | #N/A |  |  | 2019-06-17 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-08-30 | 594687.94 | 0 | 45088694.57 | 0 | 45088694.57 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-09-30 | 0 | 0 | 45088694.57 | 0 | 45088694.57 | #N/A | #N/A |  |  | 2019-07-25 | added 1 |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-10-30 | 101291.61 | 0 | 45189986.18 | 0 | 45189986.18 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-11-30 | 0 | 0 | 45189986.18 | 0 | 45189986.18 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2013-12-30 | 0 | 0 | 45189986.18 | 0 | 45189986.18 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Logestica 02 | 2014-01-30 | 592312 | 219556.83 | 45782298.18 | 219556.83 | 45562741.35 | #N/A | #N/A |  |  | 2019-10-07 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-02-28 | 0 | 548413.6 | 45782298.18 | 767970.43 | 45014327.75 | #N/A | #N/A |  |  | 2019-10-16 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-03-30 | 300000 | 244155.28 | 46082298.18 | 1012125.71 | 45070172.47 | #N/A | #N/A |  |  | 2019-10-28 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-04-30 | 1000000 | 1037944.46 | 47082298.18 | 2050070.17 | 45032228.01 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-05-30 | 1700000 | 626142.17 | 48782298.18 | 2676212.34 | 46106085.84 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-06-30 | 0 | 576920.45 | 48782298.18 | 3253132.79 | 45529165.39 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-07-30 | 0 | 162116.34 | 48782298.18 | 3415249.13 | 45367049.05 | #N/A | #N/A |  |  | 2020-01-06 | added 1 |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-08-30 | 122257 | 222464.85 | 48904555.18 | 3637713.98 | 45266841.2 | #N/A | #N/A |  |  | 2020-01-20 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-09-30 | 750000 | 0 | 49654555.18 | 3637713.98 | 46016841.2 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-10-30 | 0 | 29950.72 | 49654555.18 | 3667664.7 | 45986890.48 | #N/A | #N/A |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-11-30 | 0 | 66593.71 | 49654555.18 | 3734258.41 | 45920296.77 | #N/A | #N/A |  |  | 2020-03-09 | added 1 |  |  |  | 2014 | #N/A | #N/A | #N/A
Logestica 02 | 2014-12-30 | 480000 | 15443 | 50134555.18 | 3749701.41 | 46384853.77 | #N/A | #N/A |  |  | 2020-03-16 | added 1 |  |  |  | 2014 | #N/A | #N/A | #N/A
115 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Marassi Bridges Pkg 37 | 2014-12-30 | 22164568 | 22879392 | 22164568 | 22879392 | -714824 | 26193836.68 | -2.729% |  |  | 2020-04-29 | added 1 |  |  |  | 2014 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-01-30 | 455102 | 258131 | 22619670 | 23137523 | -517853 | 26193836.68 | -1.977% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-02-28 | 0 | 223477 | 22619670 | 23361000 | -741330 | 26193836.68 | -2.83% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-03-30 | 0 | 274333 | 22619670 | 23635333 | -1015663 | 26193836.68 | -3.877% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-04-30 | 0 | 176327 | 22619670 | 23811660 | -1191990 | 26193836.68 | -4.551% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-05-30 | 598246 | 256471 | 23217916 | 24068131 | -850215 | 26193836.68 | -3.246% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-06-30 | 460061 | 240419 | 23677977 | 24308550 | -630573 | 26193836.68 | -2.407% |  |  | 2020-09-07 | added cash in 3 |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-07-30 | 0 | 32883 | 23677977 | 24341433 | -663456 | 26193836.68 | -2.533% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-08-30 | 0 | 0 | 23677977 | 24341433 | -663456 | 26193836.68 | -2.533% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-09-30 | 57351 | 0 | 23735328 | 24341433 | -606105 | 26193836.68 | -2.314% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-11-30 | 256625 | 13606 | 23991953 | 24355039 | -363086 | 26193836.68 | -1.386% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2015-12-30 | 0 | 2516 | 23991953 | 24357555 | -365602 | 26193836.68 | -1.396% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2016-01-30 | 48358 | 0 | 24040311 | 24357555 | -317244 | 26193836.68 | -1.211% |  |  | 2021-02-03 | added cash in 3 |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2016-03-30 | 335562 | 0 | 24375873 | 24357555 | 18318 | 26193836.68 | 0.06993% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2016-04-30 | 0 | 19673 | 24375873 | 24377228 | -1355 | [9 empty] | 2016 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2016-06-30 | 0 | 96561 | 24375873 | 24473789 | -97916 | 26193836.68 | -0.3738% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | EMAAR
Marassi Bridges Pkg 37 | 2016-08-30 | 398372 | 0 | 24774245 | 24473789 | 300456 | 26193836.68 | 1.147% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Bridges & Tunnels | EMAAR
116 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Marassi Golf Maintance Building Pkg 58 | 2013-08-30 | 0 | 71947 | 0 | 71947 | -71947 | 4720405.25 | -1.524% |  |  | 2019-01-29 | added cash in 3 |  |  |  | 2013 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2013-10-30 | 0 | 412339 | 0 | 484286 | -484286 | 4720405.25 | -10.26% |  |  |  | cash out both |  |  |  | 2013 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2013-11-30 | 0 | 482288 | 0 | 966574 | -966574 | 4720405.25 | -20.48% |  |  |  | cash out both |  |  |  | 2013 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2013-12-30 | 0 | 226750 | 0 | 1193324 | -1193324 | 4720405.25 | -25.28% |  |  | 2019-03-13 | added cash in 3 |  |  |  | 2013 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-01-30 | 376486.77 | 272717.48 | 376486.77 | 1466041.48 | -1089554.71 | 4720405.25 | -23.08% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-02-28 | 173298.19 | 253081.73 | 549784.96 | 1719123.21 | -1169338.25 | 4720405.25 | -24.77% |  |  | 2019-04-15 | added 1 |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-03-30 | 222016.09 | 269914.66 | 771801.05 | 1989037.87 | -1217236.82 | 4720405.25 | -25.79% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-04-30 | 0 | 415105.46 | 771801.05 | 2404143.33 | -1632342.28 | 4720405.25 | -34.58% |  |  | 2019-05-29 | added cash in 3 |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-05-30 | 370600.71 | 129085.96 | 1142401.76 | 2533229.29 | -1390827.53 | 4720405.25 | -29.46% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-06-30 | 0 | 302227.7 | 1142401.76 | 2835456.99 | -1693055.23 | 4720405.25 | -35.87% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-07-30 | 0 | 254281.63 | 1142401.76 | 3089738.62 | -1947336.86 | 4720405.25 | -41.25% |  |  | 2019-07-17 | added 1 |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-08-30 | 339924.47 | 92749.94 | 1482326.23 | 3182488.56 | -1700162.33 | 4720405.25 | -36.02% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-09-30 | 95706.34 | 179422.25 | 1578032.57 | 3361910.81 | -1783878.24 | 4720405.25 | -37.79% |  |  | 2019-08-05 | added 1 |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-10-30 | 296267.7 | 197897.23 | 1874300.27 | 3559808.04 | -1685507.77 | 4720405.25 | -35.71% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-11-30 | 149820.58 | 156171.85 | 2024120.85 | 3715979.89 | -1691859.04 | 4720405.25 | -35.84% |  |  | 2019-09-09 | added 1 |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2014-12-30 | 55333.35 | 334619 | 2079454.2 | 4050598.89 | -1971144.69 | 4720405.25 | -41.76% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2015-01-30 | 107852 | 187198 | 2187306.2 | 4237796.89 | -2050490.69 | 4720405.25 | -43.44% |  |  | 2019-10-07 | added 1 |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2015-03-30 | 148615 | 76348 | 2335921.2 | 4314144.89 | -1978223.69 | 4720405.25 | -41.91% |  |  | 2019-10-31 | added cash in 3 |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2015-06-30 | 60612 | 0 | 2396533.2 | 4314144.89 | -1917611.69 | 4720405.25 | -40.62% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2015-07-30 | 0 | 591754 | 2396533.2 | 4905898.89 | -2509365.69 | 4720405.25 | -53.16% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2015-09-30 | 347788 | 115507 | 2744321.2 | 5021405.89 | -2277084.69 | 4720405.25 | -48.24% |  |  | 2019-12-08 | added 1 |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2015-10-30 | 58700 | 0 | 2803021.2 | 5021405.89 | -2218384.69 | 4720405.25 | -47% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2015-12-30 | 0 | 228097 | 2803021.2 | 5249502.89 | -2446481.69 | 4720405.25 | -51.83% |  |  | 2020-01-13 | added 1 |  |  |  | 2015 | Commercial | Offices & Mall | EMAAR
Marassi Golf Maintance Building Pkg 58 | 2016-01-30 | 48540 | 0 | 2851561.2 | 5249502.89 | -2397941.69 | 4720405.25 | -50.8% |  |  | 2020-01-29 | added 1 |  |  |  | 2016 | Commercial | Offices & Mall | EMAAR
117 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Uptown Service Buildings Pkg 17A | 2014-02-28 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-03-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  | 2020-03-04 | added 1 |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-04-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  | 2020-03-17 | added 1 |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-05-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-06-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  | 2020-04-16 | added 1 |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-07-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-08-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  | 2020-05-07 | added 1 |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-09-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  | 2020-05-17 | added cash in 3 |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-10-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-11-30 | 0 | 0 | 0 | 0 | 0 | 55905931 | 0% |  |  | 2020-06-07 | added 1 |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2014-12-30 | 9650499 | 9673297 | 9650499 | 9673297 | -22798 | 55905931 | -0.04078% |  |  | 2020-06-23 | added 1 |  |  |  | 2014 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-01-30 | 983001 | 275398 | 10633500 | 9948695 | 684805 | 55905931 | 1.225% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-02-28 | 581832 | 464417 | 11215332 | 10413112 | 802220 | 55905931 | 1.435% |  |  | 2020-07-15 | added 1 |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-03-30 | 639609 | 447496 | 11854941 | 10860608 | 994333 | 55905931 | 1.779% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-04-30 | 324662 | 472109 | 12179603 | 11332717 | 846886 | 55905931 | 1.515% |  |  | 2020-08-16 | added 1 |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-05-30 | 0 | 479590 | 12179603 | 11812307 | 367296 | 55905931 | 0.657% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-06-30 | 0 | 486461 | 12179603 | 12298768 | -119165 | 55905931 | -0.2132% |  |  | 2020-09-17 | added cash in 3 |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-07-30 | 530306 | 564423 | 12709909 | 12863191 | -153282 | 55905931 | -0.2742% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-08-30 | 0 | 910803 | 12709909 | 13773994 | -1064085 | 55905931 | -1.903% |  |  | 2020-10-15 | added 1 |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-09-30 | 0 | 776990 | 12709909 | 14550984 | -1841075 | 55905931 | -3.293% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-10-30 | 0 | 1111148 | 12709909 | 15662132 | -2952223 | 55905931 | -5.281% |  |  | 2020-11-15 | added cash in 3 |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-11-30 | 0 | 162511 | 12709909 | 15824643 | -3114734 | 55905931 | -5.571% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2015-12-30 | 0 | 77434 | 12709909 | 15902077 | -3192168 | 55905931 | -5.71% |  |  | 2020-12-13 | added 1 |  |  |  | 2015 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2016-01-30 | 1145796 | 27324 | 13855705 | 15929401 | -2073696 | 55905931 | -3.709% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2016-02-28 | 591788 | 7800 | 14447493 | 15937201 | -1489708 | 55905931 | -2.665% |  |  | 2021-01-21 | added 1 |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2016-03-30 | 0 | 35523 | 14447493 | 15972724 | -1525231 | 55905931 | -2.728% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2016-05-30 | 0 | 22686 | 14447493 | 15995410 | -1547917 | 55905931 | -2.769% |  |  | 2021-02-15 | added 1 |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2016-10-30 | 0 | 83797 | 14447493 | 16079207 | -1631714 | 55905931 | -2.919% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2016-11-30 | 0 | 8092 | 14447493 | 16087299 | -1639806 | 55905931 | -2.933% |  |  | 2021-03-18 | added cash in 3 |  |  |  | 2016 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2017-03-30 | 0 | 261460 | 14447493 | 16348759 | -1901266 | 55905931 | -3.401% |  |  | 2021-04-19 | added cash in 3 |  |  |  | 2017 | Infrastructure | Tank | EMAAR
Uptown Service Buildings Pkg 17A | 2017-04-30 | 1978172 | 83797 | 16425665 | 16432556 | -6891 | [9 empty] | 2017 | Infrastructure | Tank | EMAAR
118 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Point 90 New Cairo Mall | 2014-01-30 | 0 | 556808.3 | 0 | 556808.3 | -556808.3 | 145010925.68 | -0.384% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-02-28 | 0 | 1242119.83 | 0 | 1798928.13 | -1798928.13 | 145010925.68 | -1.241% |  |  | 2019-01-06 | added cash in 3 |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-03-30 | 337595.15 | 977662.47 | 337595.15 | 2776590.6 | -2438995.45 | 145010925.68 | -1.682% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-04-30 | 7575591.25 | 1272996.69 | 7913186.4 | 4049587.29 | 3863599.11 | 145010925.68 | 2.664% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-05-30 | 8757008 | 10215274.38 | 16670194.4 | 14264861.67 | 2405332.73 | 145010925.68 | 1.659% |  |  | 2019-03-12 | added 1 |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-06-30 | 984119.05 | 2620346.63 | 17654313.45 | 16885208.3 | 769105.15 | 145010925.68 | 0.5304% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-07-30 | 0 | 1844072.2 | 17654313.45 | 18729280.5 | -1074967.05 | 145010925.68 | -0.7413% |  |  | 2019-04-18 | added cash in 3 |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-08-30 | 2126778.6 | 2656903.22 | 19781092.05 | 21386183.72 | -1605091.67 | 145010925.68 | -1.107% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-09-30 | 6643055.47 | 5390039.21 | 26424147.52 | 26776222.93 | -352075.41 | 145010925.68 | -0.2428% |  |  | 2019-05-30 | added 1 |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-10-30 | 4902226.76 | 4858479.24 | 31326374.28 | 31634702.17 | -308327.89 | 145010925.68 | -0.2126% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-11-30 | 7278364.77 | 6854191.42 | 38604739.05 | 38488893.59 | 115845.46 | 145010925.68 | 0.07989% |  |  | 2019-06-24 | added cash in 3 |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2014-12-30 | 15334084.92 | 16008211.2368 | 53938823.97 | 54497104.8268 | -558280.8568 | 145010925.68 | -0.385% |  |  |  | cash out both |  |  |  | 2014 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-01-30 | 416611 | 2043654 | 54355434.97 | 56540758.8268 | -2185323.8568 | 145010925.68 | -1.507% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-02-28 | 2150000 | 6495524 | 56505434.97 | 63036282.8268 | -6530847.8568 | 145010925.68 | -4.504% |  |  | 2019-08-07 | added cash in 3 |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-03-30 | 16677165 | 10539604 | 73182599.97 | 73575886.8268 | -393286.8568 | 145010925.68 | -0.2712% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-04-30 | 15690320 | 10869155 | 88872919.97 | 84445041.8268 | 4427878.1432 | 145010925.68 | 3.053% |  |  | 2019-09-19 | added cash in 3 |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-05-30 | 0 | 3421832 | 88872919.97 | 87866873.8268 | 1006046.1432 | 145010925.68 | 0.6938% |  |  | 2019-09-23 | added cash in 3 |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-06-30 | 0 | 2177645 | 88872919.97 | 90044518.8268 | -1171598.8568 | 145010925.68 | -0.8079% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-07-30 | 2456456 | 1681434 | 91329375.97 | 91725952.8268 | -396576.8568 | 145010925.68 | -0.2735% |  |  | 2019-10-28 | added 1 |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-08-30 | 495396 | 1621720 | 91824771.97 | 93347672.8268 | -1522900.8568 | 145010925.68 | -1.05% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-09-30 | 2888335 | 1712941 | 94713106.97 | 95060613.8268 | -347506.8568 | 145010925.68 | -0.2396% |  |  | 2019-11-25 | added cash in 3 |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-10-30 | 0 | 3075717 | 94713106.97 | 98136330.8268 | -3423223.8568 | 145010925.68 | -2.361% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-11-30 | 5068703 | 5527644 | 99781809.97 | 103663974.8268 | -3882164.8568 | 145010925.68 | -2.677% |  |  |  | cash out both |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2015-12-30 | 3649856 | 769111 | 103431665.97 | 104433085.8268 | -1001419.8568 | 145010925.68 | -0.6906% |  |  | 2020-01-06 | added 1 |  |  |  | 2015 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-01-30 | 2869899 | 640175 | 106301564.97 | 105073260.8268 | 1228304.1432 | 145010925.68 | 0.847% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-02-28 | 190857 | 333983 | 106492421.97 | 105407243.8268 | 1085178.1432 | 145010925.68 | 0.7483% |  |  | 2020-02-17 | added 1 |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-03-30 | 0 | 283204 | 106492421.97 | 105690447.8268 | 801974.1432 | 145010925.68 | 0.553% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-04-30 | 0 | 118066 | 106492421.97 | 105808513.8268 | 683908.1432 | 145010925.68 | 0.4716% |  |  | 2020-03-23 | added 1 |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-05-30 | 0 | 23805 | 106492421.97 | 105832318.8268 | 660103.1432 | 145010925.68 | 0.4552% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-06-30 | 6858538 | 389365 | 113350959.97 | 106221683.8268 | 7129276.1432 | 145010925.68 | 4.916% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-07-30 | 0 | 3646910 | 113350959.97 | 109868593.8268 | 3482366.1432 | 145010925.68 | 2.401% |  |  | 2020-05-04 | added 1 |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-08-30 | 0 | 21539 | 113350959.97 | 109890132.8268 | 3460827.1432 | 145010925.68 | 2.387% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-09-30 | 0 | 2300 | 113350959.97 | 109892432.8268 | 3458527.1432 | 145010925.68 | 2.385% |  |  | 2020-06-10 | added cash in 3 |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2016-11-30 | 9745815 | 142189 | 123096774.97 | 110034621.8268 | 13062153.1432 | 145010925.68 | 9.008% |  |  |  | cash out both |  |  |  | 2016 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2017-01-30 | 0 | 90327 | 123096774.97 | 110124948.8268 | 12971826.1432 | 145010925.68 | 8.945% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2017-03-30 | 939483 | 2188641 | 124036257.97 | 112313589.8268 | 11722668.1432 | 145010925.68 | 8.084% |  |  |  | cash out both |  |  |  | 2017 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2017-04-30 | 2000000 | 805141 | 126036257.97 | 113118730.8268 | 12917527.1432 | 145010925.68 | 8.908% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2017 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2017-05-30 | 3053641 | 1040079 | 129089898.97 | 114158809.8268 | 14931089.1432 | 145010925.68 | 10.3% |  |  | 2020-10-07 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2017-06-30 | 0 | 54612 | 129089898.97 | 114213421.8268 | 14876477.1432 | 145010925.68 | 10.26% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2017 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2017-08-30 | 0 | 75378 | 129089898.97 | 114288799.8268 | 14801099.1432 | 145010925.68 | 10.21% |  |  | 2020-11-16 | added cash in 3 |  |  |  | 2017 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
Point 90 New Cairo Mall | 2017-09-30 | 0 | 194363 | 129089898.97 | 114483162.8268 | 14606736.1432 | 145010925.68 | 10.07% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2017 | Commercial | Offices & Mall | Cairo Company for Housing & Development (CCHD)
119 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-01-30 | 524591.63 | 0 | 524591.63 | 0 | 524591.63 | 19589518 | 2.678% |  |  | 2021-01-20 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-02-28 | 556442.63 | 0 | 1081034.26 | 0 | 1081034.26 | 19589518 | 5.518% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-03-30 | -203590.49 | 0 | 877443.77 | 0 | 877443.77 | 19589518 | 4.479% |  |  | 2021-02-22 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-04-30 | 783737.74 | 0 | 1661181.51 | 0 | 1661181.51 | 19589518 | 8.48% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-05-30 | 0 | 0 | 1661181.51 | 0 | 1661181.51 | 19589518 | 8.48% |  |  | 2021-03-08 | added 1 |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-06-30 | 1144175.2 | 0 | 2805356.71 | 0 | 2805356.71 | [9 empty] | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-07-30 | 0 | 0 | 2805356.71 | 0 | 2805356.71 | 19589518 | 14.32% |  |  | 2018-07-11 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-08-30 | 2297660.32 | 0 | 5103017.03 | 0 | 5103017.03 | 19589518 | 26.05% |  |  | 2018-09-18 | added 1 |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-09-30 | 0 | 0 | 5103017.03 | 0 | 5103017.03 | 19589518 | 26.05% |  |  | 2018-10-18 | added 1 |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-10-30 | 1974465.6 | 0 | 7077482.63 | 0 | 7077482.63 | 19589518 | 36.13% |  |  | 2018-11-21 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-11-30 | 1916406 | 0 | 8993888.63 | 0 | 8993888.63 | 19589518 | 45.91% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2013-12-30 | 704764.6 | 0 | 9698653.23 | 0 | 9698653.23 | 19589518 | 49.51% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-01-30 | 677974.81 | 254792.08 | 10376628.04 | 254792.08 | 10121835.96 | 19589518 | 51.67% |  |  | 2019-02-17 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-02-28 | 1217342.68 | 921610.95 | 11593970.72 | 1176403.03 | 10417567.69 | 19589518 | 53.18% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-03-30 | 0 | 1744837.91 | 11593970.72 | 2921240.94 | 8672729.78 | 19589518 | 44.27% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-04-30 | 1229370.9 | 85404.71 | 12823341.62 | 3006645.65 | 9816695.97 | 19589518 | 50.11% |  |  | 2019-04-02 | added 1 |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-05-30 | 821536.2 | 132912.95 | 13644877.82 | 3139558.6 | 10505319.22 | 19589518 | 53.63% |  |  | 2019-04-18 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-06-30 | 0 | 112885.61 | 13644877.82 | 3252444.21 | 10392433.61 | 19589518 | 53.05% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-07-30 | 0 | 90177.86 | 13644877.82 | 3342622.07 | 10302255.75 | 19589518 | 52.59% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-08-30 | 0 | 19647.49 | 13644877.82 | 3362269.56 | 10282608.26 | 19589518 | 52.49% |  |  | 2019-06-13 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-09-30 | 0 | 45012.42 | 13644877.82 | 3407281.98 | 10237595.84 | 19589518 | 52.26% |  |  | 2019-06-19 | added 1 |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-10-30 | 661055.73 | 619979.78 | 14305933.55 | 4027261.76 | 10278671.79 | 19589518 | 52.47% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-11-30 | 0 | 45544 | 14305933.55 | 4072805.76 | 10233127.79 | 19589518 | 52.24% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2014-12-30 | 0 | 127827.79 | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Sodic MV Cables | 2015-01-30 | 0 | 0 | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Sodic MV Cables | 2015-02-28 | 0 | 0 | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Sodic MV Cables | 2015-03-30 | 0 | 0 | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Sodic MV Cables | 2015-04-30 | 0 | 0 | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  | 2019-12-26 | added cash in 3 |  |  |  | 2015 | #N/A | #N/A | #N/A
Sodic MV Cables | 2015-05-30 | 0 | 0 | 14305933.55 | 4200633.55 | 10105300 | 19589518 | 51.59% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
120 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sodic West Town Hub | 2012-11-30 | 1015025.63 | 0 | 1015025.63 | 0 | 1015025.63 | 54160920.41 | 1.874% |  |  |  | cash out both |  |  |  | 2012 | Commercial | Offices & Mall | SODIC
Sodic West Town Hub | 2012-12-30 | 2605028.33 | 0 | 3620053.96 | 0 | 3620053.96 | 54160920.41 | 6.684% |  |  |  | cash out both |  |  |  | 2012 | Commercial | Offices & Mall | SODIC
121 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-04-30 | 68910040.25 | 0 | 68910040.25 | 0 | 68910040.25 | 119626844 | 57.6% |  |  | 2020-05-20 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-05-30 | 67546820.11 | 0 | 136456860.36 | 0 | 136456860.36 | 119626844 | 114.1% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-06-30 | 66546820.11 | 0 | 203003680.47 | 0 | 203003680.47 | 119626844 | 169.7% |  |  | 2020-06-10 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-07-30 | 64426820.11 | 0 | 267430500.58 | 0 | 267430500.58 | 119626844 | 223.6% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-08-30 | 62411075.23 | 0 | 329841575.81 | 0 | 329841575.81 | 119626844 | 275.7% |  |  | 2020-07-08 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-09-30 | 62236366.79 | 0 | 392077942.6 | 0 | 392077942.6 | 119626844 | 327.8% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-10-30 | 60903595.22 | 0 | 452981537.82 | 0 | 452981537.82 | 119626844 | 378.7% |  |  | 2020-08-10 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-11-30 | 58232221.87 | 0 | 511213759.69 | 0 | 511213759.69 | 119626844 | 427.3% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2013-12-30 | 57543239.2 | 0 | 568756998.89 | 0 | 568756998.89 | 119626844 | 475.4% |  |  | 2020-09-21 | added cash in 3 |  |  |  | 2013 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-01-30 | 2556309.78 | 2917911.59 | 571313308.67 | 2917911.59 | 568395397.08 | 119626844 | 475.1% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-02-28 | 4500000 | 4018119.69 | 575813308.67 | 6936031.28 | 568877277.39 | 119626844 | 475.5% |  |  | 2020-10-07 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-03-30 | 2000000 | 5146141.37 | 577813308.67 | 12082172.65 | 565731136.02 | 119626844 | 472.9% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-04-30 | 6470455.36 | 4675969.06 | 584283764.03 | 16758141.71 | 567525622.32 | 119626844 | 474.4% |  |  | 2020-11-11 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-05-30 | 4000000 | 5980577.46 | 588283764.03 | 22738719.17 | 565545044.86 | 119626844 | 472.8% |  |  | 2020-11-23 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-06-30 | 1976271.33 | 5146368.54 | 590260035.36 | 27885087.71 | 562374947.65 | 119626844 | 470.1% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-07-30 | 3500000 | 1962774.07 | 593760035.36 | 29847861.78 | 563912173.58 | 119626844 | 471.4% |  |  | 2020-12-21 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-08-30 | 5167892.93 | 2695896.58 | 598927928.29 | 32543758.36 | 566384169.93 | 119626844 | 473.5% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-09-30 | 4500000 | 4810854.92 | 603427928.29 | 37354613.28 | 566073315.01 | 119626844 | 473.2% |  |  | 2021-01-13 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-10-30 | 3074518 | 4103108.44 | 606502446.29 | 41457721.72 | 565044724.57 | 119626844 | 472.3% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-11-30 | 2824636.13 | 2313160.12 | 609327082.42 | 43770881.84 | 565556200.58 | 119626844 | 472.8% |  |  | 2021-02-03 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2014-12-30 | 2380352.34 | 4679596.48 | 611707434.76 | 48450478.32 | 563256956.44 | 119626844 | 470.8% |  |  | 2021-02-22 | added cash in 3 |  |  |  | 2014 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-01-30 | 13225504.79 | 0 | 624932939.55 | 48450478.32 | 576482461.23 | 119626844 | 481.9% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-02-28 | 7853167.56 | 0 | 632786107.11 | 48450478.32 | 584335628.79 | [9 empty] | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-03-30 | 5724776.4 | 0 | 638510883.51 | 48450478.32 | 590060405.19 | 119626844 | 493.3% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-04-30 | 5724776.4 | 0 | 644235659.91 | 48450478.32 | 595785181.59 | 119626844 | 498% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-05-30 | 1791760.92 | 0 | 646027420.83 | 48450478.32 | 597576942.51 | 119626844 | 499.5% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-06-30 | 149600.52 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-07-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-08-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-09-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-10-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-11-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2015-12-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2016-01-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2016-02-28 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  | 2019-11-24 | added cash in 3 |  |  |  | 2016 | #N/A | #N/A | #N/A
Limak TB2 Cairo Airport Terminal | 2016-03-30 | 0 | 0 | 646177021.35 | 48450478.32 | 597726543.03 | 119626844 | 499.7% |  |  |  | cash out both |  |  |  | 2016 | #N/A | #N/A | #N/A
122 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Twin Towers | 2010-12-30 | 1782375.88 | 0 | 1782375.88 | 0 | 1782375.88 | 64000000.23 | 2.785% |  |  |  | cash out both |  |  |  | 2010 | #N/A | #N/A | #N/A
Twin Towers | 2011-01-30 | 0 | 0 | 1782375.88 | 0 | 1782375.88 | 64000000.23 | 2.785% |  |  |  | cash out both |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-02-28 | 1042075.56 | 0 | 2824451.44 | 0 | 2824451.44 | 64000000.23 | 4.413% |  |  |  | cash out both |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-03-30 | 1260843.13 | 0 | 4085294.57 | 0 | 4085294.57 | 64000000.23 | 6.383% |  |  |  | cash out both |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-04-30 | 1414868.61 | 0 | 5500163.18 | 0 | 5500163.18 | 64000000.23 | 8.594% |  |  |  | cash out both |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-05-30 | 1292579.86 | 0 | 6792743.04 | 0 | 6792743.04 | 64000000.23 | 10.61% |  |  | 2020-05-18 | added 1 |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-06-30 | 1177608.41 | 0 | 7970351.45 | 0 | 7970351.45 | 64000000.23 | 12.45% |  |  | 2020-05-21 | added 1 |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-07-30 | 0 | 0 | 7970351.45 | 0 | 7970351.45 | 64000000.23 | 12.45% |  |  |  | cash out both |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-08-30 | 1491226.87 | 0 | 9461578.32 | 0 | 9461578.32 | 64000000.23 | 14.78% |  |  | 2020-06-25 | added cash in 3 |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-09-30 | 2018417.57 | 0 | 11479995.89 | 0 | 11479995.89 | 64000000.23 | 17.94% |  |  |  | cash out both |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-10-30 | 1048114.83 | 0 | 12528110.72 | 0 | 12528110.72 | 64000000.23 | 19.58% |  |  | 2020-07-27 | added cash in 3 |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-11-30 | 1135288.54 | 0 | 13663399.26 | 0 | 13663399.26 | 64000000.23 | 21.35% |  |  | 2020-07-28 | added 1 |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2011-12-30 | 1144950.05 | 0 | 14808349.31 | 0 | 14808349.31 | 64000000.23 | 23.14% |  |  |  | cash out both |  |  |  | 2011 | #N/A | #N/A | #N/A
Twin Towers | 2012-01-30 | 1635725.59 | 0 | 16444074.9 | 0 | 16444074.9 | 64000000.23 | 25.69% |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-02-28 | 1405373.93 | 0 | 17849448.83 | 0 | 17849448.83 | 64000000.23 | 27.89% |  |  | 2020-09-27 | added 1 |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-03-30 | 1346977.29 | 0 | 19196426.12 | 0 | 19196426.12 | 64000000.23 | 29.99% |  |  | 2020-09-30 | added cash in 3 |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-04-30 | 1533462.2 | 0 | 20729888.32 | 0 | 20729888.32 | 64000000.23 | 32.39% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-05-30 | 1690948.85 | 0 | 22420837.17 | 0 | 22420837.17 | 64000000.23 | 35.03% |  |  | 2020-10-04 | added cash in 3 |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-06-30 | 1524559.45 | 0 | 23945396.62 | 0 | 23945396.62 | 64000000.23 | 37.41% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-07-30 | 1066394.39 | 0 | 25011791.01 | 0 | 25011791.01 | 64000000.23 | 39.08% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-08-30 | 985272.88 | 0 | 25997063.89 | 0 | 25997063.89 | 64000000.23 | 40.62% |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-09-30 | 1395488.71 | 0 | 27392552.6 | 0 | 27392552.6 | 64000000.23 | 42.8% |  |  | 2021-01-31 | added cash in 3 |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-10-30 | 940238.32 | 0 | 28332790.92 | 0 | 28332790.92 | 64000000.23 | 44.27% |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-11-30 | 336933.59 | 0 | 28669724.51 | 0 | 28669724.51 | 64000000.23 | 44.8% |  |  | 2021-02-28 | added 1 |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2012-12-30 | 0 | 0 | 28669724.51 | 0 | 28669724.51 | 64000000.23 | 44.8% |  |  |  | cash out both |  |  |  | 2012 | #N/A | #N/A | #N/A
Twin Towers | 2013-01-30 | 0 | 0 | 28669724.51 | 0 | 28669724.51 | [9 empty] | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-02-28 | 331467.02 | 0 | 29001191.53 | 0 | 29001191.53 | 64000000.23 | 45.31% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-03-30 | 399287.55 | 0 | 29400479.08 | 0 | 29400479.08 | 64000000.23 | 45.94% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-04-30 | 1206261.26 | 0 | 30606740.34 | 0 | 30606740.34 | 64000000.23 | 47.82% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-05-30 | 1678026.98 | 0 | 32284767.32 | 0 | 32284767.32 | 64000000.23 | 50.44% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-06-30 | 1264998.07 | 0 | 33549765.39 | 0 | 33549765.39 | 64000000.23 | 52.42% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-07-30 | 110796.29 | 0 | 33660561.68 | 0 | 33660561.68 | 64000000.23 | 52.59% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-08-30 | 1015605.01 | 0 | 34676166.69 | 0 | 34676166.69 | 64000000.23 | 54.18% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-09-30 | 2227132.83 | 0 | 36903299.52 | 0 | 36903299.52 | 64000000.23 | 57.66% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-10-30 | 0 | 0 | 36903299.52 | 0 | 36903299.52 | 64000000.23 | 57.66% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-11-30 | 0 | 0 | 36903299.52 | 0 | 36903299.52 | 64000000.23 | 57.66% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2013-12-30 | 892543.25 | 0 | 37795842.77 | 0 | 37795842.77 | 64000000.23 | 59.06% |  |  |  | cash out both |  |  |  | 2013 | #N/A | #N/A | #N/A
Twin Towers | 2014-01-30 | 588784.71 | 847987.23 | 38384627.48 | 847987.23 | 37536640.25 | 64000000.23 | 58.65% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-02-28 | 1708357.87 | 861719.8 | 40092985.35 | 1709707.03 | 38383278.32 | 64000000.23 | 59.97% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-03-30 | 1823483.39 | 1173422.38 | 41916468.74 | 2883129.41 | 39033339.33 | 64000000.23 | 60.99% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-04-30 | 750000 | 2031280.22 | 42666468.74 | 4914409.63 | 37752059.11 | 64000000.23 | 58.99% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-05-30 | 1187298.19 | 1619384.9 | 43853766.93 | 6533794.53 | 37319972.4 | 64000000.23 | 58.31% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-06-30 | 1571450.51 | 1349007.48 | 45425217.44 | 7882802.01 | 37542415.43 | 64000000.23 | 58.66% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-07-30 | 421925.37 | 1027930.74 | 45847142.81 | 8910732.75 | 36936410.06 | [9 empty] | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-08-30 | 469981.59 | 569155.04 | 46317124.4 | 9479887.79 | 36837236.61 | 64000000.23 | 57.56% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-09-30 | 668376.51 | 1299581.65 | 46985500.91 | 10779469.44 | 36206031.47 | 64000000.23 | 56.57% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-10-30 | 1890854.63 | 1287934.12 | 48876355.54 | 12067403.56 | 36808951.98 | 64000000.23 | 57.51% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-11-30 | 1142714.04 | 837986.7 | 50019069.58 | 12905390.26 | 37113679.32 | 64000000.23 | 57.99% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2014-12-30 | 809103.45 | 1342122.18 | 50828173.03 | 14247512.44 | 36580660.59 | 64000000.23 | 57.16% |  |  |  | cash out both |  |  |  | 2014 | #N/A | #N/A | #N/A
Twin Towers | 2015-01-30 | 1669641.52 | 0 | 52497814.55 | 14247512.44 | 38250302.11 | 64000000.23 | 59.77% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Twin Towers | 2015-02-28 | 0 | 0 | 52497814.55 | 14247512.44 | 38250302.11 | 64000000.23 | 59.77% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Twin Towers | 2015-03-30 | 588090.74 | 0 | 53085905.29 | 14247512.44 | 38838392.85 | 64000000.23 | 60.68% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Twin Towers | 2015-04-30 | 297794.48 | 0 | 53383699.77 | 14247512.44 | 39136187.33 | 64000000.23 | 61.15% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
Twin Towers | 2015-05-30 | 0 | 0 | 53383699.77 | 14247512.44 | 39136187.33 | 64000000.23 | 61.15% |  |  |  | cash out both |  |  |  | 2015 | #N/A | #N/A | #N/A
123 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Uptown Soil Stabilization Pkg 32 | 2012-11-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  |  | cash out both |  |  |  | 2012 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2012-12-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  |  | cash out both |  |  |  | 2012 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-01-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  |  | cash out both |  |  |  | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-02-28 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  |  | cash out both |  |  |  | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-03-30 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-04-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  | 2019-09-06 | added 1 |  |  |  | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-06-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  | 2019-09-06 | added 1 |  |  |  | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-07-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  | 2019-09-06 | added 1 |  |  |  | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-09-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  | 2020-01-16 | added 1 |  |  |  | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2013-11-30 | 0 | 0 | 0 | 0 | 0 | 17421145.8 | 0% |  |  | 2020-03-23 | added 1 |  |  |  | 2013 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-01-30 | 0 | 167558.7 | 0 | 167558.7 | -167558.7 | 17421145.8 | -0.9618% |  |  | 2020-04-09 | added 1 |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-02-28 | 0 | 243644.89 | 0 | 411203.59 | -411203.59 | 17421145.8 | -2.36% |  |  | 2020-04-13 | added 1 |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-03-30 | 327560.64 | 77210.41 | 327560.64 | 488414 | -160853.36 | 17421145.8 | -0.9233% |  |  | 2020-06-18 | added 1 |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-04-30 | 0 | 92784.43 | 327560.64 | 581198.43 | -253637.79 | 17421145.8 | -1.456% |  |  | 2020-10-01 | cashout both updated |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-05-30 | 0 | 87186.71 | 327560.64 | 668385.14 | -340824.5 | 17421145.8 | -1.956% |  |  | 2020-11-01 | cashout both updated |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-06-30 | 0 | 79780.06 | 327560.64 | 748165.2 | -420604.56 | 17421145.8 | -2.414% |  |  | 2020-12-01 | cashout both updated |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-07-30 | 0 | 189033.61 | 327560.64 | 937198.81 | -609638.17 | 17421145.8 | -3.499% |  |  | 2020-12-16 | added 1 |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-08-30 | 0 | 288827.77 | 327560.64 | 1226026.58 | -898465.94 | 17421145.8 | -5.157% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-09-30 | 4486779.13 | 258753.98 | 4814339.77 | 1484780.56 | 3329559.21 | 17421145.8 | 19.11% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-10-30 | 0 | 487318.28 | 4814339.77 | 1972098.84 | 2842240.93 | 17421145.8 | 16.31% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-11-30 | 0 | 278633.56 | 4814339.77 | 2250732.4 | 2563607.37 | [9 empty] | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2014-12-30 | 482367.61 | 1106281.04 | 5296707.38 | 3357013.44 | 1939693.94 | 17421145.8 | 11.13% |  |  |  | cash out both |  |  |  | 2014 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-01-30 | 230752 | 552612 | 5527459.38 | 3909625.44 | 1617833.94 | 17421145.8 | 9.287% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-02-28 | 146183 | 432488 | 5673642.38 | 4342113.44 | 1331528.94 | 17421145.8 | 7.643% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-03-30 | 562527 | 324983 | 6236169.38 | 4667096.44 | 1569072.94 | 17421145.8 | 9.007% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-04-30 | 385837 | 649494 | 6622006.38 | 5316590.44 | 1305415.94 | 17421145.8 | 7.493% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-05-30 | 0 | 1066058 | 6622006.38 | 6382648.44 | 239357.94 | 17421145.8 | 1.374% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-06-30 | 682272 | 598183 | 7304278.38 | 6980831.44 | 323446.94 | 17421145.8 | 1.857% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-07-30 | 580510 | 790977 | 7884788.38 | 7771808.44 | 112979.94 | 17421145.8 | 0.6485% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-08-30 | 0 | 605922 | 7884788.38 | 8377730.44 | -492942.06 | 17421145.8 | -2.83% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-09-30 | 726448 | 955858 | 8611236.38 | 9333588.44 | -722352.06 | 17421145.8 | -4.146% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-10-30 | 0 | 321024 | 8611236.38 | 9654612.44 | -1043376.06 | 17421145.8 | -5.989% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-11-30 | 0 | 240630 | 8611236.38 | 9895242.44 | -1284006.06 | 17421145.8 | -7.37% |  |  |  | cash out both |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2015-12-30 | 899642 | 254894 | 9510878.38 | 10150136.44 | -639258.06 | 17421145.8 | -3.669% |  |  | 2020-10-28 | added 1 |  |  |  | 2015 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-01-30 | 0 | 181452 | 9510878.38 | 10331588.44 | -820710.06 | 17421145.8 | -4.711% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-02-28 | 300770 | 190093 | 9811648.38 | 10521681.44 | -710033.06 | 17421145.8 | -4.076% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-03-30 | 0 | 554825 | 9811648.38 | 11076506.44 | -1264858.06 | [9 empty] | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-04-30 | 0 | 145417 | 9811648.38 | 11221923.44 | -1410275.06 | 17421145.8 | -8.095% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-05-30 | 0 | 188996 | 9811648.38 | 11410919.44 | -1599271.06 | 17421145.8 | -9.18% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-06-30 | 316081 | 153380 | 10127729.38 | 11564299.44 | -1436570.06 | 17421145.8 | -8.246% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-07-30 | 263606 | 40002 | 10391335.38 | 11604301.44 | -1212966.06 | 17421145.8 | -6.963% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-08-30 | 0 | 75247 | 10391335.38 | 11679548.44 | -1288213.06 | 17421145.8 | -7.395% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-09-30 | 0 | 42460 | 10391335.38 | 11722008.44 | -1330673.06 | 17421145.8 | -7.638% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-10-30 | 0 | 40916 | 10391335.38 | 11762924.44 | -1371589.06 | 17421145.8 | -7.873% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2016-11-30 | 0 | 43820 | 10391335.38 | 11806744.44 | -1415409.06 | 17421145.8 | -8.125% |  |  |  | cash out both |  |  |  | 2016 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2017-01-30 | 0 | 52746 | 10391335.38 | 11859490.44 | -1468155.06 | 17421145.8 | -8.427% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2017-02-28 | 0 | 64065 | 10391335.38 | 11923555.44 | -1532220.06 | 17421145.8 | -8.795% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2017-03-30 | 583453 | 118483 | 10974788.38 | 12042038.44 | -1067250.06 | 17421145.8 | -6.126% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2017-04-30 | 0 | 11000 | 10974788.38 | 12053038.44 | -1078250.06 | 17421145.8 | -6.189% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2017-07-30 | 0 | 3582 | 10974788.38 | 12056620.44 | -1081832.06 | 17421145.8 | -6.21% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
Uptown Soil Stabilization Pkg 32 | 2017-09-30 | 766581 | 0 | 11741369.38 | 12056620.44 | -315251.06 | 17421145.8 | -1.81% |  |  |  | cash out both |  |  |  | 2017 | Infrastructure | L&L | EMAAR
124 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-05-30 | 0 | 4000 | 0 | 4000 | -4000 | 0 | #DIV/0! |  |  | 2020-07-12 | added cash in 3 |  |  |  | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-06-30 | 0 | 5219505.11 | 0 | 5223505.11 | -5223505.11 | 0 | #DIV/0! |  |  | 2020-12-14 | added 1 |  |  |  | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-07-30 | 0 | 1150 | 0 | 5224655.11 | -5224655.11 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-08-30 | 0 | 38526.78 | 0 | 5263181.89 | -5263181.89 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-09-30 | 0 | 261305.95 | 0 | 5524487.84 | -5524487.84 | [9 empty] | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-10-30 | 0 | 2533278.58 | 0 | 8057766.42 | -8057766.42 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-11-30 | 0 | 3178.64 | 0 | 8060945.06 | -8060945.06 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2019-12-30 | 0 | 148904.4 | 0 | 8209849.46 | -8209849.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2019 | #N/A | #N/A | #N/A
Electric Train LRT | 2020-01-01 | 0 | 0 | 0 | 8209849.46 | -8209849.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Electric Train LRT | 2020-03-30 | 0 | 146900 | 0 | 8356749.46 | -8356749.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Electric Train LRT | 2020-06-30 | 0 | 146900 | 0 | 8503649.46 | -8503649.46 | 0 | #DIV/0! |  |  |  | cash out both |  |  |  | 2020 | #N/A | #N/A | #N/A
Electric Train LRT | 2020-09-30 | 0 | 146900 | 0 | 8650549.46 | -8650549.46 | [9 empty] | 2020 | #N/A | #N/A | #N/A
125 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
126 | 1900-01-01 | [14 empty] | 1900 | #N/A | #N/A | #N/A
Sokhna Port Expansion | 2021-02-28 | 0 | 52000 | 0 | 52000 | -52000 | 1100000000 | -0.004727% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Port | Transportation Ministry
Sokhna Port Expansion | 2021-03-30 | 0 | 1313277 | 0 | 1365277 | -1365277 | 1100000000 | -0.1241% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Port | Transportation Ministry
Sokhna Port Expansion | 2021-04-30 | 0 | 252866.15 | 0 | 1618143.15 | -1618143.15 | 1100000000 | -0.1471% |  |  |  | cash out both |  |  |  | 2021 | Infrastructure | Port | Transportation Ministry
Formulas:
Date = [Month/Year]

## Invoicing (hidden)
Ope. | Cost Center | Project | Invice No. | Invoice month | Cut Of Date | Invoice Status | Date of Submission | Date of Approval | Monthly Sub. Gross Value of work | Monthly Appr Gross Value of work | Monthly Sub./Appr. Net amount | Duration of Pay | Due Date | Actual Paid Amount | Actual Date of Pay | Delay duration of pay
2 | 0023 | Maxim Mall |  |  | 2020-10-07 | Approved | 2020-10-07 | 2020-10-07 | 0 | 0 |  |  | 2020-10-07 | 3250000 | 2020-10-07 | 0
1 | 0032 | Sodic Club House | 36 |  | 2020-01-16 | Approved | 2020-01-16 | 2020-01-16 | 0 | 0 |  |  | 2020-01-16 | 6516540.66 | 2020-01-16 | 0
1 |  | Hyper El Solymanya | MEP-DP |  | 2020-08-17 | Approved | 2020-08-17 |  | 0 | 0 |  |  | 2020-08-17 | 4000000 | 2020-08-17 | 0
1 | 0032 | Sodic Club House | 37 (Final) |  |  | Submitted | 2020-08-11 |  | 0 |  | 4028521 | 56 | 2020-10-06 | 4028521 | 2021-03-22 | -167
1 | 0034 | PKG # 53 | 42 | 2019-12-19 | 2019-12-19 | Approved | 2019-12-20 | 2020-01-26 | 0 | 0 | 1380970.95 | 40 | 2020-01-29 | 1380970.95 | 2020-02-05 | -7
1 | 0034 | PKG # 53 | 43 | 2020-02-01 | 2020-03-10 | Approved | 2020-03-10 | 2020-04-15 | 5884788.181 | 3569085 | 3747539.31 | 40 | 2020-04-19 | 4834138.97 | 2020-11-05 | -200
1 | 0035 | Benisueif Pwr | 29 Final |  | 2018-11-10 | Approved | 2020-12-03 |  | 2627278.35 | 2627278.35 | 4326586.5 | 30 | 2021-01-05 | 4326586.5 | 2021-01-05 | 0
|  | ابناء مصر للتعمير | Payment |  | 2020-02-18 | Approved | 2020-02-18 | 2020-02-18 | 0 | 0 |  |  | 2020-02-18 | 2152765.7 | 2020-02-18 | 0
|  | ابناء مصر للتعمير | Payment |  | 2020-05-05 | Approved | 2020-05-05 | 2020-05-05 | 0 | 0 |  |  | 2020-05-05 | 1457700 | 2020-05-05 | 0
|  | سيف للهندسة | 4 |  | 2020-06-26 | Approved | 2020-06-26 |  | 0 | 0 |  |  | 2020-06-26 | 50000 | 2020-06-26 | 0
|  | سيف للهندسة | 4 |  | 2020-07-28 | Approved | 2020-07-28 |  | 0 | 0 |  |  | 2020-07-28 | 94922.5 | 2020-06-28 | 30
| 0131 | Shorouk Bridge-LRT |  |  | 2021-01-13 | Approved | 2021-01-13 |  | 0 | 0 |  |  | 2021-01-13 | 3550000 | 2021-01-13 | 0
| 0131 | Shorouk Bridge-LRT | 2 |  | 2021-02-04 | Approved | 2021-02-04 |  | 0 | 0 |  |  | 2021-02-09 | 2000000 | 2021-02-09 | 0
| 0131 | Shorouk Bridge-LRT | 3 |  | 2021-03-16 | Approved | 2021-03-16 |  | 0 | 0 |  |  | 2021-03-16 | 6500000 | 2021-03-16 | 0
|  | Tetra | Payment |  | 2020-03-18 | Approved | 2020-03-18 | 2020-03-18 | 0 | 0 |  |  | 2020-03-18 | 1150000 | 2020-03-18 | 0
2 |  | Middle Tunnel Lock Load | Final |  | 2020-12-16 | Approved | 2020-12-16 |  | 0 | 0 |  |  | 2020-12-16 | 677590 | 2020-12-16 | 0
2 | 0051 | Amadid Substataion | TAM - CW - EUR - 10 |  | 2020-01-22 | Approved | 2020-01-22 | 2020-01-22 | 0 | 0 |  |  | 2020-01-22 | 234715.6 | 2020-01-22 | 0
2 | 0051 | Amadid Substataion | CW-EGP-22 |  | 2020-01-14 | Approved | 2020-01-14 | 2020-01-14 | 0 | 0 |  |  | 2020-01-14 | 80060.48 | 2020-01-14 | 0
2 | 0051 | Amadid Substataion | تعويضات محطة محولات المنصورة |  | 2020-02-20 | Approved | 2020-02-20 | 2020-02-20 | 0 | 0 |  |  | 2020-02-20 | 4999415.55 | 2020-02-20 | 0
2 | 0051 | Amadid Substataion | TAM-CW-EGP-24 |  | 2020-09-27 | Approved | 2020-09-27 | 2020-09-27 | 0 | 0 |  |  | 2020-09-27 | 71764 | 2020-09-27 | 0
2 | 0051 | Amadid Substataion | TAM-CW-EGP-23 |  | 2020-07-28 | Approved | 2020-07-28 | 2020-07-28 | 0 | 0 |  |  | 2020-07-28 | 35903.65 | 2020-07-28 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | SW-EGP-6,7 - CW-EGP-19,20,21 |  | 2020-01-14 | Approved | 2020-01-14 | 2020-01-14 | 0 | 0 |  |  | 2020-01-14 | 4224095.51 | 2020-01-14 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE - SD - EUR - 3 - 4 - 5 |  | 2020-01-22 | Approved | 2020-01-22 | 2020-01-22 | 0 | 0 |  |  | 2020-01-22 | 6680787.75 | 2020-01-22 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-CW-EGP-22 ISE-SD-EGP-03 |  | 2020-03-10 | Approved | 2020-03-10 | 2020-03-10 | 0 | 0 |  |  | 2020-03-10 | 1170773.36 | 2020-03-10 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-CW-EGP-23 / ISE-SW-EGP-08 |  | 2020-07-28 | Approved | 2020-07-28 | 2020-07-28 | 0 | 0 |  |  | 2020-07-28 | 1446764.54 | 2020-07-28 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-CW-EURO-03 |  | 2020-08-06 | Approved | 2020-08-06 | 2020-08-06 | 0 | 0 |  |  | 2020-08-06 | 2899097.58 | 2020-08-06 | 0
2 | 0052 | French Fund Substations ( Ismailia ) |  |  | 2020-09-17 | Approved | 2020-09-17 | 2020-09-17 | 0 | 0 |  |  | 2020-09-17 | 70946.57 | 2020-09-17 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-SD-EURO-06 |  | 2020-09-16 | Approved | 2020-09-16 | 2020-09-16 | 0 | 0 |  |  | 2020-09-16 | 667221.67 | 2020-09-16 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-CW-EGP-24 / ISE-CW-EGP-26 |  | 2020-09-27 | Approved | 2020-09-27 | 2020-09-27 | 0 | 0 |  |  | 2020-09-27 | 389570.04 | 2020-09-27 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | رد عمالة غير منتظمة |  | 2020-09-20 | Approved | 2020-09-20 | 2020-09-20 | 0 | 0 |  |  | 2020-09-20 | 9900 | 2020-09-20 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | رد عمالة غير منتظمة |  | 2020-12-05 | Approved | 2020-12-05 |  | 0 | 0 |  |  | 2020-12-05 | 593 | 2020-12-05 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-CW-EGP-25 |  | 2020-12-05 | Approved | 2020-12-05 |  | 0 | 0 |  |  | 2020-12-05 | 214819.722 | 2020-12-05 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-CW-EGP-27 |  | 2021-01-12 | Approved | 2021-01-12 |  | 0 | 0 |  |  | 2021-01-12 | 288528.58 | 2021-01-12 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | رد غرامات محولات الاسماعيلية |  | 2021-02-28 | Approved | 2021-02-28 |  | 0 | 0 |  |  | 2021-02-28 | 5362261.37 | 2021-02-28 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | عمالة غيرمنتظمة الاسماعلية |  | 2021-03-28 | Approved | 2021-03-28 |  | 0 | 0 |  |  | 2021-03-28 | 535 | 2021-03-28 | 0
2 | 0052 | French Fund Substations ( Ismailia ) | ISE-SW-09-EGP |  | 2021-03-28 | Approved | 2021-03-28 |  | 0 | 0 |  |  | 2021-03-28 | 250406.62 | 2021-03-28 | 0
2 | 0061 | French Fund Substations (Bani-Swif) | BSF-CW-EGP-17 FINAL |  | 2020-09-27 | Approved | 2020-09-27 | 2020-09-27 | 0 | 0 |  |  | 2020-09-27 | 758220.28 | 2020-09-27 | 0
2 | 0061 | French Fund Substations (Bani-Swif) | BSF-CW-EURO-09 FINAL / BSF-SW-12 FINAL |  | 2020-09-20 | Approved | 2020-09-20 | 2020-09-20 | 0 | 0 |  |  | 2020-09-20 | 18610.78 | 2020-09-20 | 0
2 | 0061 | French Fund Substations (Bani-Swif) | BSF-CW-EGP-16 |  | 2020-11-04 | Approved | 2020-11-04 |  | 0 | 0 |  |  | 2020-11-04 | 903786.81 | 2020-11-04 | 0
2 | 0061 | French Fund Substations (Bani-Swif) | رد تأمين محجوز يورو |  | 2021-01-12 | Approved | 2021-01-12 |  | 0 | 0 |  |  | 2021-01-12 | 2415310.91 | 2021-01-12 | 0
2 | 0061 | French Fund Substations (Bani-Swif) | رد جزء تأمين محجوز محولات بنى سويف |  | 2021-01-12 | Approved | 2021-01-12 |  | 0 | 0 |  |  | 2021-01-12 | 3316128.41 | 2021-01-12 | 0
2 | 0061 | French Fund Substations (Bani-Swif) | رد تأمين محجوز يورو034200D,V, |  | 2021-01-27 | Approved | 2021-01-27 |  | 0 | 0 |  |  | 2021-02-01 | 663480 | 2021-02-01 | 0
2 | 0061 | French Fund Substations (Bani-Swif) | رد جزء تأمين محجوز محولات بنى سويف |  | 2021-02-04 | Approved | 2021-02-04 |  | 0 | 0 |  |  | 2021-02-04 | 5000000 | 2021-02-09 | -5
2 | 0061 | French Fund Substations (Bani-Swif) | رد غرامات محولات بنى سويف |  | 2021-02-28 | Approved | 2021-02-28 |  | 0 | 0 |  |  | 2021-02-28 | 25000 | 2021-02-28 | 0
1 |  | NGU2 | 27 | 2019-06-30 | 2017-11-30 | Approved | 2019-07-04 | 2019-07-04 | 0 | 0 |  |  | 2020-01-28 | 2104161 | 2020-01-28 | 0
1 |  | NGU2 | رد تأمينات اجتماعية مستخلص ختامى |  | 2020-10-25 | Approved | 2020-10-25 | 2020-10-25 | 0 | 0 |  |  | 2020-10-25 | 313708 | 2020-10-25 | 0
1 | 0073 | PKG #85 | 7 |  |  | Approved | 2020-01-15 | 2020-01-15 | 0 | 0 |  | 30 | 2020-01-15 | 29830.3 | 2020-01-15 | 0
1 | 0073 | PKG #85 | Final Inv. |  | 2019-10-11 | Approved | 2020-02-27 |  | 0 | 0 | 1869841.86 | 30 | 2019-12-18 | 1391898.96 | 2020-04-29 | -133
1 |  | PKG#22 | 37 | 2019-02-01 |  | Approved | 2019-07-31 |  | 0 | 0 | 471641.26 | 40 | 2019-09-09 | 780036 | 2020-10-18 | -405
2 | 0060 | Ministries Complex | 1 - FIT OUT (Retention Release) |  | 2020-01-16 | Approved | 2020-01-16 | 2020-01-16 | 0 | 0 |  |  | 2020-01-16 | 2851037 | 2020-01-16 | 0
2 | 0060 | Ministries Complex | م (2) حى الوزارات fit out |  | 2020-10-28 | Approved | 2020-10-28 | 2020-10-28 | 0 | 0 |  |  | 2020-10-28 | 3723275 | 2020-10-28 | 0
2 | 0060 | Ministries Complex | 1 - Long Lead |  | 2020-02-11 | Approved | 2020-02-11 | 2020-02-11 | 0 | 0 |  |  | 2020-02-11 | 6579617 | 2020-02-11 | 0
2 | 0060 | Ministries Complex | 1 - MEP |  | 2020-02-17 | Approved | 2020-02-17 | 2020-02-17 | 0 | 0 |  |  | 2020-02-17 | 47786690 | 2020-02-17 | 0
2 | 0060 | Ministries Complex | 1 - Shell |  | 2020-02-17 | Approved | 2020-02-17 | 2020-02-17 | 0 | 0 |  |  | 2020-02-17 | 6411270 | 2020-02-17 | 0
2 | 0060 | Ministries Complex | م (4) الوزارات SHELL |  | 2020-03-22 | Approved | 2020-03-22 | 2020-03-22 | 0 | 0 |  |  | 2020-03-22 | 21929380 | 2020-03-22 | 0
2 | 0060 | Ministries Complex | م (5) الوزارات SHELL |  | 2020-08-25 | Approved | 2020-08-25 | 2020-08-25 | 0 | 0 |  |  | 2020-08-25 | 14328230 | 2020-08-25 | 0
2 | 0060 | Ministries Complex | م (6) الوزارات SHELL |  | 2020-11-22 | Approved | 2020-11-22 | 2020-11-22 | 0 | 0 |  |  | 2020-11-22 | 4122020 | 2020-11-22 | 0
2 | 0060 | Ministries Complex | م (7) الوزارات SHELL |  | 2021-01-06 | Approved | 2021-01-06 | 2021-01-06 | 0 | 0 |  |  | 2021-01-06 | 2174820 | 2021-01-06 | 0
2 | 0060 | Ministries Complex | Inv.03 (concrete) |  | 2020-02-20 | Approved | 2020-02-20 | 2020-02-20 | 0 | 0 |  |  | 2020-02-20 | 10906440 | 2020-02-20 | 0
2 | 0060 | Ministries Complex | Long Lead (Retention Release) |  | 2020-02-24 | Approved | 2020-02-24 | 2020-02-24 | 0 | 0 |  |  | 2020-02-24 | 9359710 | 2020-02-24 | 0
2 | 0060 | Ministries Complex | م (2،3) الوزارات long lead |  | 2021-02-26 | Approved | 2021-02-26 | 2021-02-26 | 0 | 0 |  |  | 2021-02-26 | 231155 | 2021-02-26 | 0
2 | 0060 | Ministries Complex | م (3 ،4) الوزارات fit out |  | 2021-02-26 | Approved | 2021-02-26 | 2021-02-26 | 0 | 0 |  |  | 2021-02-26 | 877175 | 2021-02-26 | 0
2 | 0060 | Ministries Complex | Social Insurance Inv.02 (Core) |  | 2020-03-01 | Approved | 2020-03-01 | 2020-03-01 | 0 | 0 |  |  | 2020-03-01 | 557310 | 2020-03-01 | 0
2 | 0060 | Ministries Complex | Social Insurance Inv.01 (Fit Out) |  | 2020-03-01 | Approved | 2020-03-01 | 2020-03-01 | 0 | 0 |  |  | 2020-03-01 | 318910 | 2020-03-01 | 0
2 | 0060 | Ministries Complex | رد خصم بوليصة الحريق م 2 الوزارات fit out |  | 2020-11-09 | Approved | 2020-11-09 | 2020-11-09 | 0 | 0 |  |  | 2020-11-09 | 142550 | 2020-11-09 | 0
2 | 0060 | Ministries Complex | Social Insurance Inv.02 (allocation) |  | 2020-11-08 | Approved | 2020-11-08 | 2020-11-08 | 0 | 0 |  |  | 2020-11-08 | 424210 | 2020-11-08 | 0
2 | 0060 | Ministries Complex | م 1 العناصر المائية |  | 2020-03-05 | Approved | 2020-03-05 | 2020-03-05 | 0 | 0 |  |  | 2020-03-05 | 200590 | 2020-03-05 | 0
2 | 0060 | Ministries Complex | م 2 العناصر المائية |  | 2020-06-21 | Approved | 2020-06-21 | 2020-06-21 | 0 | 0 |  |  | 2020-06-21 | 501410 | 2020-06-21 | 0
2 | 0060 | Ministries Complex | رد تأمينات اجتماعية م (1) العناصر المائية ميكانيكة |  | 2020-08-23 | Approved | 2020-08-23 | 2020-08-23 | 0 | 0 |  |  | 2020-08-23 | 49745 | 2020-08-23 | 0
2 | 0060 | Ministries Complex | IPC - 03 - Core |  | 2020-03-26 | Approved | 2020-03-26 | 2020-03-26 | 0 | 0 |  |  | 2020-03-26 | 5400020 | 2020-03-26 | 0
2 | 0060 | Ministries Complex | IPC - 01 - Landscape |  | 2020-03-26 | Approved | 2020-03-26 | 2020-03-26 | 0 | 0 |  |  | 2020-03-26 | 10490 | 2020-03-26 | 0
2 | 0060 | Ministries Complex | رد تأمين نهائى حى الوزارات لاند سكيب |  | 2020-03-31 | Approved | 2020-03-31 | 2020-03-31 | 0 | 0 |  |  | 2020-03-31 | 715217 | 2020-03-31 | 0
2 | 0060 | Ministries Complex | رد تأمينات اجتماعية حى الوزارات خرسانة م 3 |  | 2020-04-23 | Approved | 2020-04-23 | 2020-04-23 | 0 | 0 |  |  | 2020-04-23 | 506375 | 2020-04-23 | 0
2 | 0060 | Ministries Complex | رد تأمين نهائى الوزارات LAND SCAPE |  | 2020-04-26 | Approved | 2020-04-26 | 2020-04-26 | 0 | 0 |  |  | 2020-04-26 | 1771845 | 2020-04-26 | 0
2 | 0060 | Ministries Complex |  |  | 2020-10-28 | Approved | 2020-10-28 | 2020-10-28 | 0 | 0 |  |  | 2020-10-28 | 2590775 | 2020-10-28 | 0
2 | 0060 | Ministries Complex | م (3) الوزارات ALLOCATION |  | 2020-04-26 | Approved | 2020-04-26 | 2020-04-26 | 0 | 0 |  |  | 2020-04-26 | 1741265 | 2020-04-26 | 0
2 | 0060 | Ministries Complex | م (2) الكتروميكانيك حى الوزارات |  | 2020-07-28 | Approved | 2020-07-28 | 2020-07-28 | 0 | 0 |  |  | 2020-07-28 | 101591695 | 2020-07-28 | 0
2 | 0060 | Ministries Complex | م (4) حى الوزارات allocation |  | 2020-07-28 | Approved | 2020-07-28 | 2020-07-28 | 0 | 0 |  |  | 2020-07-28 | 7703215 | 2020-07-28 | 0
2 | 0060 | Ministries Complex | م (4) حى الوزارات core |  | 2020-07-28 | Approved | 2020-07-28 | 2020-07-28 | 0 | 0 |  |  | 2020-07-28 | 19470665 | 2020-07-28 | 0
2 | 0060 | Ministries Complex | م (5) حى الوزارات core |  | 2020-10-28 | Approved | 2020-10-28 | 2020-10-28 | 0 | 0 |  |  | 2020-10-28 | 13360535 | 2020-10-28 | 0
2 | 0060 | Ministries Complex | رد ت محجوز الوزارات خرسانة |  | 2020-09-10 | Approved | 2020-09-10 | 2020-09-10 | 0 | 0 |  |  | 2020-09-10 | 23375895 | 2020-09-10 | 0
2 | 0060 | Ministries Complex | رد تأمينات اجتماعية م 1 الوزارات LONG LEAD |  | 2020-10-01 | Approved | 2020-10-01 | 2020-10-01 | 0 | 0 |  |  | 2020-10-01 | 2928255 | 2020-10-01 | 0
2 | 0060 | Ministries Complex | م 3 الوزارات العناصر المائية |  | 2020-11-24 | Approved | 2020-11-24 |  | 0 | 0 |  |  | 2020-11-24 | 956020 | 2020-11-24 | 0
2 | 0060 | Ministries Complex | م1 الوزارات اعمال الصحى والنوافير العناصر المائية |  | 2020-11-24 | Approved | 2020-11-24 |  | 0 | 0 |  |  | 2020-11-24 | 77920 | 2020-11-24 | 0
2 | 0060 | Ministries Complex | م (5) الوزارات ALLOCATION |  | 2020-11-24 | Approved | 2020-11-24 |  | 0 | 0 |  |  | 2020-11-24 | 5853780 | 2020-11-24 | 0
2 | 0060 | Ministries Complex | م (3) حى الوزارات land scape |  | 2020-11-30 | Approved | 2020-11-30 |  | 0 | 0 |  |  | 2020-11-30 | 2018500 | 2020-11-30 | 0
2 | 0060 | Ministries Complex |  |  | 2020-10-18 | Approved | 2020-10-18 | 2020-10-18 | 0 | 0 |  |  | 2020-10-18 | 2837565 | 2020-10-18 | 0
2 | 0060 | Ministries Complex |  |  | 2020-10-25 | Approved | 2020-10-25 | 2020-10-25 | 0 | 0 |  |  | 2020-10-25 | 1032345 | 2020-10-25 | 0
2 | 0075 | Abu Sultan Road Extension | (Retention Release) |  | 2020-01-26 | Approved | 2020-01-26 | 2020-01-26 | 0 | 0 |  |  | 2020-01-26 | 664967 | 2020-01-26 | 0
1 | 0063 | Royal City Mall | 26 | 2019-11-01 | 2019-11-30 | Approved | 2019-11-30 | 2020-01-16 | 0 | 0 |  |  | 2020-01-16 | 8025338.3 | 2020-01-16 | 0
1 | 0063 | Royal City Mall | 27 | 2019-12-19 | 2019-12-31 | Approved | 2020-01-07 | 2020-01-12 | 26855720.17 | 23741158.02 | 14587648.31 | 34 | 2020-02-16 | 5000000 | 2020-03-17 | -30
1 | 0063 | Royal City Mall | 27.1 |  |  | Approved |  |  | 0 | 0 | 9587648.31 | 34 | 2020-02-16 | 5150000 | 2020-03-23 | -36
1 | 0063 | Royal City Mall | 27.2 |  |  | Approved |  |  | 0 | 0 | 4437648.31 | 34 | 2020-02-16 | 1745943.7 | 2020-03-31 | -44
1 | 0063 | Royal City Mall | 28 | 2020-01-01 | 2020-01-31 | Approved | 2020-02-19 |  | 12200842.987 | 8853848.2642 | 10986396.56 | 34 | 2020-03-24 | 7000000 | 2020-04-09 | -16
1 | 0063 | Royal City Mall | 28.1 | 2020-01-01 | 2020-01-31 | Approved | 2020-02-19 |  | 0 | 0 | 3986396.56 | 34 | 2020-03-24 | 2943030.1 | 2020-05-04 | -41
1 | 0063 | Royal City Mall | 29 | 2020-02-01 | 2020-02-29 | Approved | 2020-03-17 |  | 25394142.02 | 21313616 | 13166441.53 | 34 | 2020-04-20 | 12838209.35 | 2020-05-21 | -31
1 | 0063 | Royal City Mall | 30 | 2020-03-01 | 2020-03-31 | Approved | 2020-04-09 |  | 20115796.24 | 13862319 | 9831952.14 | 34 | 2020-05-13 | 7400000 | 2020-06-20 | -38
1 | 0063 | Royal City Mall | 30.1 |  |  | Approved | 2020-04-09 |  | 0 | 0 | 2431952.14 | 34 | 2020-05-13 | 2431952.14 | 2020-07-09 | -57
1 | 0063 | Royal City Mall | 31 | 2020-04-01 | 2020-04-30 | Approved | 2020-05-15 |  | 15616818.33 | 10234077.88 | 7550426.17 | 34 | 2020-06-18 | 2500000 | 2020-08-06 | -49
1 | 0063 | Royal City Mall | 31.1 | 2020-04-01 |  | Approved | 2020-05-15 |  | 0 | 0 | 5050426.17 | 34 | 2020-06-18 | 3975508.58 | 2020-08-19 | -62
1 | 0063 | Royal City Mall | 32 | 2020-05-01 | 2020-05-31 | Approved | 2020-06-15 |  | 7652207.11 | 3761397.6023 | 2648440.23 | 34 | 2020-07-19 | 2151533.38 | 2020-09-20 | -63
1 | 0063 | Royal City Mall | 33 | 2020-06-01 | 2020-06-30 | Approved | 2020-07-20 |  | 17857415 | 13830917.44 | 9101413.8171 | 34 | 2020-08-23 | 5000000 | 2020-11-24 | -93
1 | 0063 | Royal City Mall | 33.1 | 2020-06-01 | 2020-06-30 | Approved | 2020-07-20 |  | 0 | 0 | 4101413.8171 | 34 | 2020-08-23 | 4101413.8171 | 2021-01-04 | -134
1 | 0063 | Royal City Mall | 34 | 2020-07-01 | 2020-07-31 | Approved | 2020-08-16 | 2020-09-13 | 13875203.32 | 7811640 | 5373442.93 | 34 | 2020-09-19 | 1294144.2829 | 2021-01-04 | -107
1 | 0063 | Royal City Mall | 34.1 | 2020-07-01 | 2020-07-31 | Approved | 2020-08-16 | 2020-09-13 | 0 | 0 | 4079298.6471 | 34 | 2020-09-19 | 4079298.6432 | 2021-01-21 | -124
1 | 0063 | Royal City Mall | 35 | 2020-08-01 | 2020-08-31 | Approved | 2020-09-16 | 2020-10-08 | 10414718 | 3980750.52 | 3237336.59 | 34 | 2020-10-20 | 3237336.5863 | 2021-01-21 | -93
1 | 0063 | Royal City Mall | 36 | 2020-09-01 | 2020-09-30 | Approved | 2020-10-11 | 2020-10-27 | 12674208.7843 | 7514139.0336 | 5231425.19 | 34 | 2020-11-14 | 1578133.6205 | 2021-01-21 | -68
1 | 0063 | Royal City Mall | 36.1 | 2020-09-01 | 2020-09-30 | Approved | 2020-10-11 |  | 0 | 0 | 3653291.5695 | 34 | 2020-11-14 | 3653291.5695 | 2021-02-09 | -87
1 | 0063 | Royal City Mall | 37 | 2020-10-01 | 2020-10-31 | Approved | 2020-11-07 | 2020-11-26 | 11643426.86 | 5412454.87 | 3663343.67 | 34 | 2020-12-11 | 3663343.67 | 2021-03-22 | -101
1 | 0063 | Royal City Mall | 38 | 2020-11-01 | 2020-11-30 | Approved | 2020-12-14 | 2020-12-28 | 7384425.52 | 3712322.32 | 3951088.51 | 34 | 2021-01-17 | 2267127.55 | 2021-03-22 | -64
1 | 0063 | Royal City Mall | 38.1 | 2020-11-01 | 2020-11-30 | Approved | 2020-12-14 | 2020-12-28 | 0 | 0 | 1683960.96 | 34 | 2021-01-17 |  |  | -78
1 | 0063 | Royal City Mall | 39 | 2020-12-01 | 2020-12-31 | Approved | 2021-01-13 |  | 4058370.53 | 1174176.51 | 1002773.1926 | 34 | 2021-02-16 |  |  | -48
1 | 0063 | Royal City Mall | 40 | 2021-02-01 | 2021-02-28 | Approved | 2021-03-09 | 2021-03-29 | 10547505.15 | 4021129.38 | 4259837.7284 | 34 | 2021-04-12 |  |  | 7
1 | 0063 | Royal City Mall | 5 (Landscape) | 2019-10-01 | 2019-11-13 | Approved | 2019-10-12 | 2020-01-16 | 0 | 0 |  | 34 | 2020-01-16 | 7060326.8 | 2020-01-16 | 0
1 | 0063 | Royal City Mall | 6 (Landscape) | 2019-12-19 | 2019-12-31 | Approved | 2020-01-12 | 2020-01-12 | 13449553.29 | 12932194.62 | 9619287.67 | 34 | 2020-02-16 | 9240902.25 | 2020-03-03 | -16
1 | 0063 | Royal City Mall | 7 (Landscape) | 2020-01-01 | 2020-01-31 | Approved | 2020-02-11 |  | 6630665.013 | 6479189.85 | 6246175.8 | 34 | 2020-03-16 | 5000000 | 2020-04-26 | -41
1 | 0063 | Royal City Mall | 7.1 (Landscape) |  |  | Approved | 2020-02-11 |  | 0 | 0 | 1246175.8 | 34 | 2020-03-16 | 2000000 | 2020-05-04 | -49
1 | 0063 | Royal City Mall | 8 (Landscape) | 2020-02-01 | 2020-02-29 | Approved | 2020-03-17 |  | 19535529.98 | 14628722.94 | 12899186.07 | 34 | 2020-04-20 | 2161790.65 | 2020-05-21 | -31
1 | 0063 | Royal City Mall | 8.1 (Landscape) |  |  | Approved | 2020-03-17 |  | 0 | 0 | 10737395.42 | 34 | 2020-04-20 | 10194453.1 | 2020-06-10 | -51
1 | 0063 | Royal City Mall | 9 (Landscape) | 2020-03-01 | 2020-03-31 | Approved | 2020-04-09 |  | 10039862.12 | 6296235 | 4988413.7416 | 34 | 2020-05-13 | 4886117.91 | 2020-07-09 | -57
1 | 0063 | Royal City Mall | 10 (Landscape) | 2020-04-01 | 2020-04-30 | Approved | 2020-05-14 |  | 5338760.5 | 3937484.9 | 3101056.01 | 34 | 2020-06-17 | 2500000 | 2020-08-06 | -50
1 | 0063 | Royal City Mall | 10.1 (Landscape) | 2020-04-01 |  | Approved | 2020-05-14 |  | 0 | 0 | 601056.01 | 34 | 2020-06-17 | 561010.97 | 2020-08-19 | -63
1 | 0063 | Royal City Mall | 11 (Landscape) | 2020-05-01 | 2020-05-31 | Approved | 2020-06-15 |  | 8142520.41 | 5192701.49 | 3973857.74 | 34 | 2020-07-19 | 4947910.42 | 2020-09-27 | -70
1 | 0063 | Royal City Mall | 12 (Landscape) | 2020-06-01 | 2020-06-30 | Approved | 2020-07-19 |  | 8468925.79 | 8940402.3 | 7029456.42 | 34 | 2020-08-22 | 5000000 | 2020-10-25 | -64
1 | 0063 | Royal City Mall | 12.1 (Landscape) | 2020-06-01 |  | Approved | 2020-07-19 |  | 0 | 0 | 2029456.42 | 34 | 2020-08-22 | 2029456.42 | 2021-01-04 | -135
1 | 0063 | Royal City Mall | 13 (Landscape) | 2020-07-07 | 2020-07-31 | Approved | 2020-08-16 | 2020-09-07 | 6024550.12 | 3598777.12 | 2173267.62 | 34 | 2020-09-19 | 2173267.62 | 2021-01-04 | -107
1 | 0063 | Royal City Mall | 14 (Landscape) | 2020-08-01 | 2020-08-31 | Approved | 2020-09-16 |  | 2749874 | 2137131.09 | 1308214.76 | 34 | 2020-10-20 | 1308214.76 | 2021-01-04 | -76
1 | 0063 | Royal City Mall | 15 (Landscape) | 2020-09-01 | 2020-09-30 | Approved | 2020-10-11 | 2020-10-28 | 5474450.84 | 3135305.5946 | 2303900.24 | 34 | 2020-11-14 | 2303900.24 | 2021-01-04 | -51
1 | 0063 | Royal City Mall | 16 (Landscape) | 2020-10-01 | 2020-10-31 | Approved | 2020-11-09 | 2020-11-26 | 3338578.0854 | 1582061.2654 | 869369.65 | 34 | 2020-12-13 | 619028.06 | 2021-01-04 | -22
1 | 0063 | Royal City Mall | 17 (Landscape) | 2020-11-01 | 2020-11-30 | Approved | 2020-12-14 | 2020-12-28 | 5855383.68 | 3716309.82 | 2058324.55 | 34 | 2021-01-17 | 1288827.45 | 2021-01-21 | -4
1 | 0063 | Royal City Mall | 17.1 (Landscape) | 2020-11-01 | 2020-11-30 | Approved | 2020-12-14 |  | 0 | 0 | 769497.1 | 34 | 2021-01-17 | 1531216.7805 | 2021-02-09 | -23
1 | 0063 | Royal City Mall | 18 (Landscape) | 2020-12-01 | 2020-12-31 | Approved | 2021-01-13 | 2021-02-03 | 3341877.52 | 1163660.88 | 819297.0816 | 34 | 2021-02-16 |  |  | -48
1 | 0063 | Royal City Mall | 19 (Landscape) | 2021-01-01 | 2021-01-31 | Approved | 2021-02-09 |  | 3000900.31 | 2029657.83 | 1116339.89 | 34 | 2021-03-15 |  |  | -21
1 | 0063 | Royal City Mall | 20 (Landscape) | 2021-02-01 | 2021-02-28 | Approved | 2021-03-09 | 2021-03-29 | 1717930.8 | 1251134.26 | 1058241.32 | 34 | 2021-04-12 |  |  | 7
1 | 0065 | Sewedy Stores | Final |  | 2020-01-30 | Approved | 2020-01-30 |  | 0 | 0 |  |  | 2020-01-30 | 972238.28 | 2020-01-30 | 0
2 | 0066 | Mostaqbal L&L |  |  | 2021-01-14 | Approved | 2021-01-14 | 2021-01-14 | 0 | 0 |  |  | 2021-01-14 | 138370 | 2021-01-14 | 0
2 | 0068 | Kayan Wall L&L | Final (Contract 1) |  | 2020-02-17 | Approved | 2020-02-17 | 2020-02-17 | 0 | 0 |  |  | 2020-02-17 | 428300 | 2020-02-17 | 0
2 | 0068 | Kayan Wall L&L | Final (Contract 2) |  | 2020-02-17 | Approved | 2020-02-17 | 2020-02-17 | 0 | 0 |  |  | 2020-02-17 | 2253440 | 2020-02-17 | 0
2 | 0068 | Kayan Wall L&L | رد ت نهائى الكيان رد بوك اند لود رقم 2 |  | 2020-07-09 | Approved | 2020-07-09 | 2020-07-09 | 0 | 0 |  |  | 2020-07-09 | 249955 | 2020-07-09 | 0
2 | 0068 | Kayan Wall L&L | رد تأمين (contract1 Backfilling) |  | 2020-03-10 | Approved | 2020-03-10 | 2020-03-10 | 0 | 0 |  |  | 2020-03-10 | 364497 | 2020-03-10 | 0
2 | 0068 | Kayan Wall L&L | رد تأمين محجوز الكيان لوك اند لود |  | 2020-09-09 | Approved | 2020-09-09 | 2020-09-09 | 0 | 0 |  |  | 2020-09-09 | 2801245 | 2020-09-09 | 0
2 | 0045 | Kayan | 2 (MEP) |  | 2020-03-02 | Approved | 2020-03-02 | 2020-03-02 | 0 | 0 |  |  | 2020-03-02 | 31120880 | 2020-03-02 | 0
2 | 0045 | Kayan | 3 (MEP) |  | 2020-06-23 | Approved | 2020-06-23 | 2020-06-23 | 0 | 0 |  |  | 2020-06-23 | 95 | 2020-06-23 | 0
2 | 0045 | Kayan | 6 (MEP) |  | 2021-01-24 | Approved | 2021-01-24 | 2021-01-24 | 0 | 0 |  |  | 2021-01-24 | 20582125 | 2021-01-24 | 0
2 | 0045 | Kayan | م (1) الكيان منع انتشار حريق |  | 2021-01-06 | Approved | 2021-01-06 | 2021-01-06 | 0 | 0 |  |  | 2021-01-06 | 1712930 | 2021-01-06 | 0
2 | 0045 | Kayan | رد تأمينات اجتماعية م 2 MEP |  | 2020-03-10 | Approved | 2020-03-10 | 2020-03-10 | 0 | 0 |  |  | 2020-03-10 | 1825290 | 2020-03-10 | 0
2 | 0045 | Kayan | Inv.08 Finishing |  | 2020-06-23 | Approved | 2020-06-23 | 2020-06-23 | 0 | 0 |  |  | 2020-06-23 | 95 | 2020-06-23 | 0
2 | 0045 | Kayan | رد تأمينات اجتماعية م 8 الكيان تشطيبات |  | 2020-07-16 | Approved | 2020-07-16 | 2020-07-16 | 0 | 0 |  |  | 2020-07-16 | 1325075 | 2020-07-16 | 0
2 | 0045 | Kayan | م (2) الكيان الروضة |  |  | Approved |  |  | 0 | 0 |  |  | 2020-06-25 | 95 | 2020-06-25 | 0
2 | 0045 | Kayan | رد تأمين محجوز الكيان تشطيبات |  | 2020-09-09 | Approved | 2020-09-09 | 2020-09-09 | 0 | 0 |  |  | 2020-09-09 | 12515545 | 2020-09-09 | 0
2 | 0045 | Kayan | رد تأمين محجوز الكيان ميكانيكة 1 |  | 2020-09-09 | Approved | 2020-09-09 | 2020-09-09 | 0 | 0 |  |  | 2020-09-09 | 9452905 | 2020-09-09 | 0
2 | 0045 | Kayan | رد تأمين محجوز الكيان صحى |  | 2020-09-09 | Approved | 2020-09-09 | 2020-09-09 | 0 | 0 |  |  | 2020-09-09 | 572225 | 2020-09-09 | 0
2 | 0084 | Alamein | Final |  | 2020-04-30 | Approved | 2020-04-30 | 2020-04-30 | 0 | 0 |  |  | 2020-04-30 | 6296976 | 2020-04-30 | 0
2 | 0084 | Alamein | رد ت اعمال ردم طريق العلمين |  | 2020-06-02 | Approved | 2020-06-02 | 2020-06-02 | 0 | 0 |  |  | 2020-06-02 | 1419727 | 2020-06-02 | 0
2 | 0084 | Alamein | دفعة ( 3 / 4 ) |  | 2020-09-01 | Approved | 2020-09-01 | 2020-09-01 | 0 | 0 |  |  | 2020-09-01 | 5280204 | 2020-09-01 | 0
1 | 0071 | PKG 117 | relase socail insurance invoice (12,13) |  | 2020-04-09 | Approved | 2020-04-09 | 2020-04-09 | 0 | 0 |  |  | 2020-04-09 | 285951.45 | 2020-04-09 | 0
1 | 0071 | PKG 117 | 14 Final | 2020-03-01 | 2020-04-14 | Approved | 2020-06-24 |  | 0 | 0 | 2238761.46 | 30 | 2020-07-24 | 2483342.5 | 2020-12-17 | -146
1 | 0072 | Siemens Power Station | 19 | 2019-10-01 | 2019-10-30 | Approved | 2019-10-30 |  | 0 | 0 | 25672201.42 | 45 | 2020-03-01 | 25672200.91 | 2020-02-23 | 7
1 | 0072 | Siemens Power Station | 20 | 2019-10-01 | 2019-10-30 | Approved | 2019-11-15 |  | 0 | 0 | 15319191.73 | 45 | 2020-03-01 | 15319191 | 2020-03-19 | -18
1 | 0072 | Siemens Power Station | 21 |  | 2020-11-17 | Approved | 2020-11-17 |  | 0 | 0 |  | 45 | 2020-11-17 | 888628.7 | 2020-11-17 | 0
1 | 0072 | Siemens Power Station | Bill 1 |  | 2020-09-30 | Approved | 2020-09-30 |  | 0 | 0 |  |  | 2020-09-30 | 144907 | 2020-09-30 | 0
2 | 0074 | Tunnel of Sokhna Road | رد ت محجوز نفق السخنة 1 |  | 2020-09-09 | Approved | 2020-09-09 |  | 0 | 0 |  |  | 2020-09-09 | 1702965 | 2020-09-09 | 0
1 | 0034 | PO#11687 | 5 |  |  | Submitted |  |  | 0 |  | 343200 |  | 2020-01-03 |  |  | -458
1 | 0076 | Mintra New Factory | 2 (Hanger 1200m2) |  |  | Submitted | 2020-11-22 |  | 0 |  | -6217.18 |  | 2020-12-07 | 0 | 2021-02-09 | -64
1 | 0076 | Mintra New Factory | 7 (final) | 2020-10-01 | 2020-11-11 | Submitted | 2020-11-22 | 2021-02-03 | 0 |  | 2005948.91 |  | 2020-12-07 | 1999731.73 | 2021-02-09 | -64
2 | 0078 | Mohamed Ali Palace | 1 |  | 2020-03-15 | Approved | 2020-03-15 | 2020-03-15 | 0 | 0 |  |  | 2020-03-15 | 18753780 | 2020-03-15 | 0
2 | 0078 | Mohamed Ali Palace | 2 |  | 2020-10-01 | Approved | 2020-10-01 | 2020-10-01 | 0 | 0 |  |  | 2020-10-01 | 572405 | 2020-10-01 | 0
2 | 0078 | Mohamed Ali Palace | رد تأمين نهائى |  | 2020-03-25 | Approved | 2020-03-25 | 2020-03-25 | 0 | 0 |  |  | 2020-03-25 | 4205847 | 2020-03-25 | 0
2 | 0078 | Mohamed Ali Palace | رد ت اجتماعية م 1 |  | 2021-01-24 | Approved | 2021-01-24 |  | 0 | 0 |  |  | 2021-02-01 | 1597635 | 2021-02-01 | 0
2 | 0080 | Fish Market | 1 MEP |  | 2021-01-27 | Approved | 2021-01-27 |  | 0 | 0 |  |  | 2021-02-01 | 1715135 | 2021-02-01 | 0
1 | 0081 | AL-JAZI EGYPT | 21 | 2020-01-01 | 2020-02-12 | Approved | 2020-03-23 |  | 25280351.63 | 20606238.59 | 5243962.19 | 15 | 2020-02-27 |  |  | -403
1 | 0081 | AL-JAZI EGYPT | 6 (Center zone) | 2020-01-01 | 2020-02-12 | Approved | 2020-03-23 |  | 1531778.37 | 1231699.41 | 0 | 15 | 2020-02-27 | 0.0001 |  | -403
1 | 0081 | AL-JAZI EGYPT | 7 (Center zone) |  | 2020-04-21 | Approved | 2020-04-23 |  | 840390.11 | 840390.11 | -2325487.18 | 15 | 2020-05-08 |  |  | -332
1 | 0041 | PKG # 62 | 19 | 2019-12-19 | 2019-12-18 | Approved | 2019-12-18 |  | 0 | 901366.73 | 1195853.88 | 40 | 2020-01-27 | 1416810.93 | 2020-11-05 | -283
1 | 0085 | Elsewedy Univ - Enabling Works | 11-Finishing | 2020-01-01 | 2020-01-27 | Approved | 2020-01-27 |  | 0 | 0 | 43857 | 17 | 2020-01-27 | 2318161.39 | 2020-01-27 | 0
1 | 0085 | Elsewedy Univ - Enabling Works | 12-Finishing | 2020-05-01 |  | Approved | 2020-06-21 |  | 0 | 0 | 1515470 | 17 | 2020-06-22 | 1515470 | 2020-08-16 | -55
1 | 0085 | Elsewedy Univ - Enabling Works | 13-Finishing | 2020-09-01 | 2020-09-24 | Submitted | 2020-10-26 |  | 0 |  | 6845790.3 | 17 | 2020-11-12 | 6845790.37 | 2020-11-29 | -17
1 | 0085 | Elsewedy Univ - Enabling Works | 9-STR | 2020-03-01 | 2020-03-21 | Approved | 2020-03-22 |  | 369916.9 | 369916.9 | 1116423 | 14 | 2020-03-15 | 1116423 | 2020-04-30 | -46
1 | 0085 | Elsewedy Univ - Enabling Works | رد ت اجتماعية م 2 :7 |  | 2020-02-09 | Approved | 2020-02-09 |  | 0 | 0 |  |  | 2020-02-09 | 1120262.65 | 2020-02-09 | 0
1 | 0085 | Elsewedy Univ - Enabling Works | رد ت اجتماعية م 2 :4 |  | 2020-02-09 | Approved | 2020-02-09 |  | 0 | 0 |  |  | 2020-02-09 | 253659.18 | 2020-02-09 | 0
1 | 0085 | Elsewedy Univ - Enabling Works | رد ت اجتماعية م 1 |  | 2020-02-09 | Approved | 2020-02-09 |  | 0 | 0 |  |  | 2020-02-09 | 267208.33 | 2020-02-09 | 0
2 | 0086 | Lock&Load-30June w Sokhna Rd | 1 |  | 2021-01-27 | Approved | 2021-01-27 |  | 0 | 0 |  |  | 2021-02-01 | 454415 | 2021-02-01 | 0
2 | 0110 | Suez Tunnel L&L | Final |  | 2020-11-22 | Approved | 2020-11-22 |  | 0 | 0 |  |  | 2020-11-22 | 1311260 | 2020-11-22 | 0
2 | 0088 | R05 | 1 | 2018-12-01 |  | Approved | 2019-01-12 |  | 87931599.6 | 87931599.6 | 84232258.79 | 60 | 2019-03-13 | 84232258.79 | 2019-03-14 | -1
2 | 0088 | R05 | 2 | 2019-01-01 |  | Approved | 2019-02-04 |  | 30312099.7 | 30312099.7 | 33239727.62 | 60 | 2019-04-05 | 33239727.62 | 2019-04-30 | -25
2 | 0088 | R05 | 3 | 2019-02-01 |  | Approved | 2019-03-19 |  | 31573869.75 | 31573869.75 | 32983100.66 | 60 | 2019-05-18 | 32983100.66 | 2019-06-02 | -15
2 | 0088 | R05 | 4 | 2019-03-01 |  | Approved | 2019-04-10 |  | 44525663.3 | 44525663.3 | 34182205.73 | 60 | 2019-06-09 | 34182205.73 | 2019-06-25 | -16
2 | 0088 | R05 | 5 | 2019-04-01 |  | Approved | 2019-05-02 |  | 45848307.35 | 45848307.35 | 39074639.76 | 60 | 2019-07-01 | 39074639.76 | 2019-07-02 | -1
2 | 0088 | R05 | 6 | 2019-05-01 |  | Approved | 2019-06-10 |  | 33530322.1 | 33530322.1 | 27368495.94 | 60 | 2019-08-09 | 27368495.94 | 2019-09-17 | -39
2 | 0088 | R05 | 7 | 2019-06-01 |  | Approved | 2019-07-16 |  | 36808732.3 | 36808732.3 | 28813824.71 | 60 | 2019-09-14 | 28813824.71 | 2019-10-15 | -31
2 | 0088 | R05 | 8 | 2019-07-01 |  | Approved | 2019-08-03 |  | 33154478.5 | 33154478.5 | 27768504.1 | 60 | 2019-10-02 | 27768504.1 | 2019-11-17 | -46
2 | 0088 | R05 | 9 | 2019-08-01 |  | Approved | 2019-09-02 |  | 24093801.65 | 24093801.65 | 22348276.35 | 60 | 2019-11-01 | 22348276.35 | 2019-11-17 | -16
2 | 0088 | R05 | 10 | 2019-09-01 |  | Approved | 2019-10-07 |  | 26640996.55 | 26640996.55 | 23826290.1 | 60 | 2019-12-06 | 23826290.1 | 2019-12-22 | -16
2 | 0088 | R05 | 11 | 2019-10-01 |  | Approved | 2019-11-04 |  | 35072197.95 | 35072197.95 | 29830600.5 | 60 | 2020-01-03 | 29830600.5 | 2020-02-09 | -37
2 | 0088 | R05 | 12 | 2019-11-01 |  | Approved | 2019-12-07 |  | 26622562.5 | 26622562.5 | 22976221.5 | 60 | 2020-02-05 | 22909628.3 | 2020-03-19 | -43
2 | 0088 | R05 | 13 | 2019-12-01 | 2019-12-31 | Approved | 2020-01-01 |  | 35089603.4 | 35089603.4 | 21364882.72 | 60 | 2020-03-01 | 21628889.1 | 2020-04-09 | -39
2 | 0088 | R05 | 14 | 2020-01-01 | 2020-01-31 | Approved | 2020-02-04 |  | 48665536.25 | 48665536.25 | 37488389.75 | 60 | 2020-04-04 | 35488384.45 | 2020-05-04 | -30
2 | 0088 | R05 | 14.1 |  |  | Approved | 2020-02-04 |  | 0 | 0 | 2000005.3 | 60 | 2020-04-04 | 2000000 | 2020-06-08 | -65
2 | 0088 | R05 | 15 | 2020-02-01 | 2020-02-29 | Approved | 2020-03-05 |  | 48673667.5 | 48673667.5 | 47244452.4 | 60 | 2020-05-04 | 12244457.65 | 2020-05-20 | -16
2 | 0088 | R05 | 15.1 |  |  | Approved | 2020-03-05 |  | 0 | 0 | 34999994.75 | 60 | 2020-05-04 | 35000000 | 2020-05-26 | -22
2 | 0088 | R05 | 16 | 2020-03-01 | 2020-03-31 | Approved | 2020-04-02 |  | 41433707.7 | 41433707.7 | 26136902.16 | 60 | 2020-06-01 | 11413010.6 | 2020-06-07 | -6
2 | 0088 | R05 | 16.1 |  |  | Approved | 2020-04-02 |  | 0 | 0 | 14723891.56 | 60 | 2020-06-01 | 15000000 | 2020-07-13 | -42
2 | 0088 | R05 | 17 | 2020-04-01 | 2020-04-30 | Approved | 2020-05-05 |  | 40451064.68 | 40451064.68 | 28650722.75 | 60 | 2020-07-04 | 28461647.31 | 2020-07-14 | -10
2 | 0088 | R05 | 18 | 2020-05-01 | 2020-05-31 | Approved | 2020-06-04 |  | 28976061.4 | 28976061.4 | 23790518.4 | 60 | 2020-08-03 | 22790518.4 | 2020-07-22 | 12
2 | 0088 | R05 | 18.1 |  |  | Approved | 2020-06-04 |  | 0 | 0 | 1000000 | 60 | 2020-08-03 | 1000000 | 2020-10-01 | -59
2 | 0088 | R05 | 19 | 2020-06-01 | 2020-06-30 | Approved | 2020-06-30 |  | 86436847.69 | 86436847.69 | 66204670.03 | 60 | 2020-08-29 | 46190767.35 | 2020-08-31 | -2
2 | 0088 | R05 | 19.1 | 2020-06-01 |  | Approved | 2020-06-30 |  | 0 | 0 | 20013902.68 | 60 | 2020-08-29 | 20000000 | 2020-10-04 | -36
2 | 0088 | R05 | 20 | 2020-07-01 | 2020-07-31 | Approved | 2020-07-31 |  | 40939275.19 | 40939275.19 | 36332927.05 | 60 | 2020-09-29 | 34332927.05 | 2020-10-05 | -6
2 | 0088 | R05 | 20.1 | 2020-07-01 |  | Approved | 2020-07-31 |  | 0 | 0 | 2000000 | 60 | 2020-09-29 |  |  | -188
2 | 0088 | R05 | 21 | 2020-08-01 | 2020-08-31 | Approved | 2020-08-31 |  | 37143144.01 | 37143144.01 | 23661440.91 | 60 | 2020-10-30 | 22661440.9 | 2020-11-09 | -10
2 | 0088 | R05 | 21.1 | 2020-08-01 |  | Approved | 2020-08-31 |  | 0 | 0 | 1000000.01 | 60 | 2020-10-30 |  |  | -157
2 | 0088 | R05 | 22 | 2020-09-01 | 2020-09-30 | Approved | 2020-09-30 |  | 29282126.25 | 29282126.25 | 24627827.2 | 60 | 2020-11-29 | 23127827.2 | 2020-11-23 | 6
2 | 0088 | R05 | 22.1 | 2020-09-01 |  | Approved | 2020-09-30 |  | 0 | 0 | 1500000 | 60 | 2020-11-29 |  |  | -127
2 | 0088 | R05 | 23 | 2020-10-01 | 2020-10-28 | Approved | 2020-10-30 |  | 88626920.8 | 88626920.8 | 71866445.33 | 60 | 2020-12-29 | 61866445.3 | 2020-12-15 | 14
2 | 0088 | R05 | 23.1 | 2020-10-01 | 2020-10-28 | Approved | 2020-10-30 |  | 0 | 0 | 10000000.03 | 60 | 2020-12-29 | 10000000.03 | 2021-03-28 | -89
2 | 0088 | R05 | 24 | 2020-11-01 | 2020-11-30 | Approved | 2020-11-30 |  | 25606376.04 | 25606376.04 | 20574974.57 | 60 | 2021-01-29 | 19661149.99 | 2021-01-11 | 18
2 | 0088 | R05 | 24 | 2020-11-01 | 2020-11-30 | Approved | 2020-11-30 |  | 0 | 0 | 913824.58 | 60 | 2021-01-29 | 1000000 | 2021-03-28 | -58
2 | 0088 | R05 | 25 | 2020-12-01 | 2020-12-31 | Approved | 2020-12-31 |  | 20378846.3 | 20505707.57 | 17581166.48 | 60 | 2021-03-01 | 16426047.71 | 2021-02-28 | 1
2 | 0088 | R05 | 25.1 | 2020-12-01 | 2020-12-31 | Approved | 2020-12-31 |  | 0 | 0 | 1155118.77 | 60 | 2021-03-01 |  |  | -35
2 | 0088 | R05 | 26 | 2021-01-01 | 2021-01-31 | Approved | 2021-01-31 |  | 16935236.87 | 16935236.87 | 14568659.63 | 60 | 2021-04-01 | 13096920.15 | 2021-03-28 | 4
2 | 0088 | R05 | 26.1 | 2021-01-01 | 2021-01-31 | Approved | 2021-01-31 |  | 0 | 0 | 1471739.48 | 60 | 2021-04-01 |  |  | -4
2 | 0088 | R05 | 27 | 2021-02-01 | 2021-02-28 | Submitted | 2021-02-28 |  | 12195893.26 |  | 7984380.68 | 60 | 2021-04-29 |  |  | 24
2 | 0088 | R05 | رد تعليا تأمينات اجتماعية المرحلة الاولى 20 ،21 ،22 |  |  | Approved | 2021-02-22 |  | 0 | 0 |  | 60 | 2021-02-22 | 4000000 | 2021-02-22 | 0
2 | 0088 | R05 | 1 (Finsh) | 2020-05-01 | 2020-05-21 | Approved | 2020-05-21 |  | 7954118.74 | 7954118.74 | 3423588.95 | 60 | 2020-07-20 | 3425282.3 | 2020-08-06 | -17
2 | 0088 | R05 | 2 (Finsh) | 2020-05-01 | 2020-05-31 | Approved | 2020-06-04 |  | 5273374.21 | 5273374.21 | 3884365.15 | 60 | 2020-08-03 | 3482659.8 | 2020-09-08 | -36
2 | 0088 | R05 | 2.1 (Finsh) | 2020-05-01 | 2020-05-31 | Approved | 2020-06-04 |  | 0 | 0 | 401705.35 | 60 | 2020-08-03 |  |  | -245
2 | 0088 | R05 | 3 (Finsh) | 2020-06-01 | 2020-06-30 | Approved | 2020-06-30 |  | 4461112.9 | 4461112.9 | 1602620.06 | 60 | 2020-08-29 | 1602620.05 | 2020-09-08 | -10
2 | 0088 | R05 | 4 (Finsh) | 2020-07-01 | 2020-07-31 | Approved | 2020-07-31 |  | 7950408.39 | 7950408.39 | 11658750 | 60 | 2020-09-29 | 11158750.85 | 2020-10-05 | -6
2 | 0088 | R05 | 4.1 (Finsh) | 2020-07-01 | 2020-07-31 | Approved | 2020-07-31 |  | 0 | 0 | 499999.15 | 60 | 2020-09-29 |  |  | -188
2 | 0088 | R05 | 5 (Finsh) | 2020-08-01 | 2020-08-31 | Approved | 2020-08-31 |  | 14579854.08 | 14579854.08 | 11111826.75 | 60 | 2020-10-30 | 10611814.75 | 2020-11-18 | -19
2 | 0088 | R05 | 5.1 (Finsh) | 2020-08-01 | 2020-08-31 | Approved | 2020-08-31 |  | 0 | 0 | 500012 | 60 | 2020-10-30 |  |  | -157
2 | 0088 | R05 | 6 (Finsh) | 2020-09-01 | 2020-09-30 | Approved | 2020-09-30 |  | 15528392.68 | 15528392.68 | 13043448.31 | 60 | 2020-11-29 | 11075840.05 | 2020-12-16 | -17
2 | 0088 | R05 | 6.1 (Finsh) | 2020-09-01 | 2020-09-30 | Approved | 2020-09-30 |  | 0 | 0 | 1967608.26 | 60 | 2020-11-29 |  |  | -127
2 | 0088 | R05 | 7 (Finsh) | 2020-10-01 | 2020-10-29 | Approved | 2020-10-29 |  | 10813860.39 | 10813860.39 | 8527191.14 | 60 | 2020-12-28 | 8196791 | 2020-12-31 | -3
2 | 0088 | R05 | 8 (Finsh) | 2020-11-01 | 2020-11-30 | Approved | 2020-11-30 |  | 17212975.68 | 16508334.62 | 13041584.35 | 60 | 2021-01-29 | 11910531.03 | 2021-02-18 | -20
2 | 0088 | R05 | 9 (Finsh) | 2020-12-01 | 2020-12-31 | Approved | 2020-12-31 |  | 19792351.54 | 19769181.79 | 15617653.62 | 60 | 2021-03-01 | 14603884 | 2021-03-28 | -27
2 | 0088 | R05 | 9.1 (Finsh) | 2020-12-01 | 2020-12-31 | Approved | 2020-12-31 |  | 0 | 0 | 1013769.62 | 60 | 2021-03-01 |  |  | -35
2 | 0088 | R05 | 10 (Finsh) | 2021-01-01 | 2021-01-31 | Approved | 2021-01-31 |  | 10920865.72 | 10920865.72 | 8627483.92 | 60 | 2021-04-01 | 8206207.05 | 2021-03-28 | 4
2 | 0088 | R05 | 10.1 (Finsh) | 2021-01-01 | 2021-01-31 | Approved | 2021-01-31 |  | 0 | 0 | 421276.87 | 60 | 2021-04-01 |  |  | -4
2 | 0088 | R05 | 11 (Finsh) | 2021-02-01 | 2021-02-28 | Submitted | 2021-02-28 |  | 19671461.28 |  | 15540454.41 | 60 | 2021-04-29 |  |  | 24
2 | 0088 | R05 | رد تعيات تأمينات اجتماعية المرحلة الثانية6،7 |  |  | Approved | 2021-02-22 |  | 0 | 0 |  | 60 | 2021-02-22 | 1500000 | 2021-02-22 | 0
2 | 0088 | R05 | رد تعيات تأمينات اجتماعية المرحلة الثانية1 ،2 ،4 ،5 بعد خصم 148699.53مياه |  |  | Approved | 2021-02-22 |  | 0 | 0 |  | 60 | 2021-02-22 | 1251300.48 | 2021-02-22 | 0
2 | 0088 | R05 | رد عمالة غير منتظمة م 16 الى 20 المرحلة الاولى |  |  | Approved | 2021-03-08 |  | 0 | 0 |  |  | 2021-03-08 | 713899.2 | 2021-03-08 | 0
2 | 0088 | R05 | (A-P) (Finsh) | 2019-11-01 |  | Approved | 2019-11-21 |  | 26359242 | 26359242 | 26359242 | 60 | 2019-11-21 | 26359242 | 2019-11-21 | 0
2 | 0088 | R05 | (A-P) (Finsh) |  | 2020-09-20 | Approved | 2020-09-20 |  | 0 | 0 |  | 60 | 2019-11-21 | 122781824.85 | 2020-09-20 | -304
2 | 0088 | R05 | (A-P) (Finsh) |  | 2020-11-12 | Approved | 2020-11-12 |  | 0 | 0 |  | 60 | 2020-11-12 | 70000000 | 2020-11-12 | 0
1 | 0092 | EDNC Retail & Offices Civil | 1 | 2019-03-01 |  | Approved | 2019-03-17 | 2019-03-21 | 11772365.68 | 9,063,098 | 6785088.57 | 42 | 2019-04-28 | 6789620.12 | 2019-04-11 | 17
1 | 0092 | EDNC Retail & Offices Civil | 2 | 2019-04-01 |  | Approved | 2019-04-16 | 2019-04-18 | 29706899.18 | 20,887,437 | 15652355.21 | 42 | 2019-05-28 | 15638373.66 | 2019-05-09 | 19
1 | 0092 | EDNC Retail & Offices Civil | 3 | 2019-05-01 |  | Approved | 2019-05-23 | 2019-05-23 | 33654185.34 | 2101069 | 1574016.17 | 42 | 2019-07-04 | 1574016.17 | 2019-07-18 | -14
1 | 0092 | EDNC Retail & Offices Civil | 4 | 2019-06-01 |  | Approved | 2019-06-23 | 2019-07-14 | 66609891.3333 | 20869008 | 26267292.44 | 42 | 2019-08-04 | 10000000 | 2019-07-07 | 28
1 | 0092 | EDNC Retail & Offices Civil | 4.1 | 2019-06-01 |  | Approved | 2019-06-23 | 2019-07-14 | 0 | 0 | 16267292.44 | 42 | 2019-08-04 | 15688338.61 | 2019-07-24 | 11
1 | 0092 | EDNC Retail & Offices Civil | 5 | 2019-07-01 |  | Approved | 2019-07-15 |  | 25629789 | 44468645 | 44242009.55 | 42 | 2019-08-26 | 15000000 | 2019-08-04 | 22
1 | 0092 | EDNC Retail & Offices Civil | 5.1 | 2019-07-01 |  | Approved | 2019-07-15 |  | 0 | 0 | 29242009.55 | 42 | 2019-08-26 | 22056568 | 2019-08-04 | 22
1 | 0092 | EDNC Retail & Offices Civil | 6 | 2019-08-01 |  | Approved | 2019-08-18 |  | 36441934 | 38734277 | 22056568.4 | 42 | 2019-09-29 | 18000000 | 2019-09-05 | 24
1 | 0092 | EDNC Retail & Offices Civil | 6.1 | 2019-08-01 |  | Approved | 2019-08-18 |  | 0 | 0 | 4056568.4 | 42 | 2019-09-29 | 10554847.68 | 2019-10-03 | -4
1 | 0092 | EDNC Retail & Offices Civil | 7 | 2019-09-01 |  | Approved | 2019-09-22 | 2019-11-04 | 86225177.27 | 44530987 | 38890621.05 | 42 | 2019-11-03 | 35000000 | 2019-10-27 | 7
1 | 0092 | EDNC Retail & Offices Civil | 7.1 | 2019-09-01 |  | Approved | 2019-09-22 |  | 0 | 0 | 3890621.05 | 42 | 2019-11-03 | 3197130.95 | 2019-11-07 | -4
1 | 0092 | EDNC Retail & Offices Civil | 8 | 2019-10-04 |  | Approved | 2019-11-01 | 2019-11-14 | 58746555 | 72358378 | 58794871.95 | 42 | 2019-12-13 | 46000000 | 2019-11-30 | 13
1 | 0092 | EDNC Retail & Offices Civil | 8.1 | 2019-10-04 |  | Approved | 2019-11-01 |  | 0 | 0 | 12794871.95 | 42 | 2019-12-13 | 9532397.61 | 2019-12-08 | 5
1 | 0092 | EDNC Retail & Offices Civil | 9 | 2019-11-05 |  | Approved | 2019-12-02 | 2019-12-18 | 60909784.17 | 67022041.58 | 40504812.26 | 42 | 2020-01-13 | 40504812.26 | 2019-12-25 | 19
1 | 0092 | EDNC Retail & Offices Civil | 10 | 2019-12-07 | 2019-12-31 | Approved | 2020-01-03 | 2020-01-19 | 46079197.4404 | 60039664.8448 | 32553581.24 | 42 | 2020-02-14 | 32553581.24 | 2020-01-22 | 23
1 | 0092 | EDNC Retail & Offices Civil | 11 | 2020-01-01 | 2020-01-31 | Approved | 2020-02-03 | 2020-02-19 | 62418153.0152 | 74019440.7272 | 27179529.39 | 42 | 2020-03-16 | 27179529.39 | 2020-03-05 | 11
1 | 0092 | EDNC Retail & Offices Civil | 12 | 2020-02-01 | 2020-02-29 | Approved | 2020-03-03 |  | 35042601.0956 | 26833421.4194 | 19553108.79 | 42 | 2020-04-14 | 19553108.79 | 2020-03-26 | 19
1 | 0092 | EDNC Retail & Offices Civil | 13 | 2020-03-01 | 2020-03-24 | Approved | 2020-03-25 | 2020-04-02 | 26633364 | 22228765.619 | 19217788.54 | 42 | 2020-05-06 | 10000000 | 2020-05-05 | 1
1 | 0092 | EDNC Retail & Offices Civil | 13.1 |  |  | Approved | 2020-03-25 | 2020-04-02 | 0 | 0 | 6201534.04 | 42 | 2020-05-06 | 6201534.04 | 2020-05-11 | -5
1 | 0092 | EDNC Retail & Offices Civil | 14 | 2020-04-01 | 2020-05-07 | Approved | 2020-05-10 | 2020-06-03 | 31439009 | 24418089.9619 | 16537461.58 | 42 | 2020-06-21 | 15000000 | 2020-06-11 | 10
1 | 0092 | EDNC Retail & Offices Civil | 14.1 |  |  | Approved | 2020-05-10 |  | 0 | 0 | 1537461.58 | 42 | 2020-06-21 | 1537461.58 | 2020-08-15 | -55
1 | 0092 | EDNC Retail & Offices Civil | 15 | 2020-05-01 | 2020-05-31 | Approved | 2020-06-02 | 2020-06-17 | 17152607.4286 | 19101976.1238 | 12895953.97 | 42 | 2020-07-14 | 12895954 | 2020-07-12 | 2
1 | 0092 | EDNC Retail & Offices Civil | 16 | 2020-06-01 | 2020-06-30 | Approved | 2020-07-01 | 2020-07-19 | 51131860 | 42785902.6952 | 30145771.53 | 42 | 2020-08-12 | 30145771.57 | 2020-08-19 | -7
1 | 0092 | EDNC Retail & Offices Civil | 17 | 2020-07-01 | 2020-08-08 | Approved | 2020-08-10 |  | 41323295.1048 | 33693489.0135 | 22896073.3381 | 42 | 2020-09-21 | 20000000 | 2020-09-01 | 20
1 | 0092 | EDNC Retail & Offices Civil | 17.1 | 2020-07-01 |  | Approved | 2020-08-10 |  | 0 | 0 | 2896073.3381 | 42 | 2020-09-21 | 899381.34 | 2020-09-13 | 8
1 | 0092 | EDNC Retail & Offices Civil | 18 | 2020-08-01 | 2020-08-31 | Approved | 2020-09-03 | 2020-10-11 | 39052650 | 36663335.5429 | 22406610.78 | 42 | 2020-10-15 | 15000000 | 2020-09-23 | 22
1 | 0092 | EDNC Retail & Offices Civil | 18.1 | 2020-08-01 |  | Approved | 2020-09-03 |  | 0 | 0 | 7406610.78 | 42 | 2020-10-15 | 7406610.78 | 2020-10-18 | -3
1 | 0092 | EDNC Retail & Offices Civil | 19 | 2020-09-01 | 2020-10-01 | Approved | 2020-11-08 |  | 58025608.3714 | 48818243.381 | 37913427.51 | 42 | 2020-12-20 | 25500000 | 2020-11-05 | 45
1 | 0092 | EDNC Retail & Offices Civil | 19.1 | 2020-09-01 |  | Approved | 2020-11-08 |  | 0 | 0 | 8917592.72 | 42 | 2020-12-20 | 8917592.72 | 2020-11-24 | 26
1 | 0092 | EDNC Retail & Offices Civil | 20 | 2020-10-01 | 2020-10-31 | Approved | 2020-11-03 |  | 60682214.9143 | 11264193.3714 | 35073043.88 | 42 | 2020-12-15 | 27000000 | 2020-11-24 | 21
1 | 0092 | EDNC Retail & Offices Civil | 20.1 | 2020-10-01 | 2020-10-31 | Approved | 2020-11-08 |  | 0 | 0 | 4197031.83 | 42 | 2020-12-20 | 4197031.83 | 2020-12-17 | 3
1 | 0092 | EDNC Retail & Offices Civil | 21 | 2020-11-01 | 2020-11-30 | Approved | 2020-12-03 |  | 81665882.7143 | 79356615.1714 | 32143414.32 | 42 | 2021-01-14 | 25000000 | 2020-12-17 | 28
1 | 0092 | EDNC Retail & Offices Civil | 21.1 | 2020-11-01 | 2020-11-30 | Approved | 2020-12-03 |  | 0 | 0 | 4743783.32 | 42 | 2021-01-14 | 4743783.32 | 2021-02-01 | -18
1 | 0092 | EDNC Retail & Offices Civil | 22 | 2020-12-01 | 2020-12-31 | Approved | 2021-01-03 | 2021-02-09 | 32428728.0857 | 29539477.0476 | 19360701.21 | 42 | 2021-02-14 | 15000000 | 2021-02-01 | 13
1 | 0092 | EDNC Retail & Offices Civil | 22.1 | 2020-12-01 | 2020-12-31 | Approved | 2021-01-03 |  | 0 | 0 | 4964135.7 | 42 | 2021-02-14 | 4964135.7 | 2021-03-09 | -23
1 | 0092 | EDNC Retail & Offices Civil | 23 | 2021-01-01 | 2021-01-31 | Approved | 2021-02-03 | 2021-03-04 | 28389603.9714 | 23832998.7238 | 7672746.6443 | 42 | 2021-03-17 | 7672746.6443 | 2021-03-22 | -5
1 | 0092 | EDNC Retail & Offices Civil | 24 | 2021-02-01 | 2021-02-28 | Submitted | 2021-03-07 |  | 25445155.619 |  | 17436083.38 | 42 | 2021-04-18 | 12000000 | 2021-03-15 | 34
1 | 0092 | EDNC Retail & Offices Civil | 24.1 | 2021-02-01 | 2021-02-28 | Submitted | 2021-03-07 |  | 0 |  | 5436083.38 | 42 | 2021-04-18 |  |  | 13
1 | 0092 | EDNC Retail & Offices Civil | م (7) رد تأمينات أجتماعية |  | 2020-01-09 | Approved | 2020-01-09 | 2020-01-09 | 0 | 0 |  |  | 2020-01-09 | 1311245.56 | 2020-01-09 | 0
1 | 0092 | EDNC Retail & Offices Civil | م (9-10) رد تأمينات أجتماعية |  | 2020-03-26 | Approved | 2020-03-26 | 2020-03-26 | 0 | 0 |  |  | 2020-03-26 | 2884335.94 | 2020-03-26 | 0
1 | 0092 | EDNC Retail & Offices Civil | رد ت اجتماعية م (13 ،14 ) سوريل |  | 2020-09-01 | Approved | 2020-09-01 | 2020-09-01 | 0 | 0 |  |  | 2020-09-01 | 1322438.36 | 2020-09-01 | 0
1 | 0092 | EDNC Retail & Offices Civil | رد تأمينات اجتماعية م (18 ،19) سوريل |  |  | Approved | 2021-03-08 | 2021-03-08 | 0 | 0 |  |  | 2021-03-08 | 2423402.76 | 2021-03-08 | 0
1 | 0092 | EDNC Retail & Offices Civil |  |  | 2020-03-05 | Approved | 2020-03-05 | 2020-03-05 | 0 | 0 |  |  | 2020-03-05 | 2324832.91 | 2020-03-05 | 0
1 | 0092 | EDNC Retail & Offices Civil | (A-P) | (A-P) | 2020-03-22 | Submitted | 2020-03-22 |  | 0 |  | 5928168 |  | 2020-03-31 | 5928168 | 2020-05-04 | -34
1 | 0092 | EDNC Retail & Offices Civil | Social Insurance |  | 2020-08-15 | Approved | 2020-08-15 |  | 0 | 0 |  |  | 2020-08-15 | 1801458.51 | 2020-08-15 | 0
1 | 0092 | EDNC Retail & Offices Civil | Social Insurance |  | 2020-09-24 | Approved | 2020-09-24 |  | 0 | 0 |  |  | 2020-09-24 | 1754521.36 | 2020-09-24 | 0
1 | 0092 | EDNC Retail & Offices Civil | Social Insurance |  | 2020-11-22 | Submitted | 2020-11-22 |  | 0 |  |  |  | 2020-11-22 | 862557.37 | 2020-11-22 | 0
1 | 0093 | PKG# 144, Marassi | 2 | 2018-12-01 |  | Approved | 2018-12-27 | 2019-01-17 | 4939983.61 | 4125990.87 | 2532120.6 | 30 | 2019-01-26 | 2532120.6 | 2019-02-12 | -17
1 | 0093 | PKG# 144, Marassi | 3 | 2019-01-01 |  | Approved | 2019-01-31 | 2019-02-18 | 14734355.62 | 6872046.63 | 6190737 | 30 | 2019-03-02 | 6189125.05 | 2019-03-04 | -2
1 | 0093 | PKG# 144, Marassi | 4 | 2019-02-02 |  | Approved | 2019-02-27 | 2019-03-11 | 22452721.13 | 11224614.17 | 6888545 | 30 | 2019-03-29 | 6887377.01 | 2019-03-14 | 15
1 | 0093 | PKG# 144, Marassi | 5 | 2019-02-02 |  | Approved | 2019-03-11 | 2019-03-11 | 0 | 0 | 7206339.7 | 30 | 2019-04-10 | 7206339.7 | 2019-03-14 | 27
1 | 0093 | PKG# 144, Marassi | 6 | 2019-03-01 |  | Approved | 2019-03-14 | 2019-03-21 | 38466266.02 | 24444079.39 | 14801922 | 30 | 2019-04-13 | 14929468.44 | 2019-03-27 | 17
1 | 0093 | PKG# 144, Marassi | 7 | 2019-03-01 |  | Approved | 2019-03-30 | 2019-04-11 | 34978364.98 | 20465525.62 | 12603636.33 | 30 | 2019-04-29 | 12477244.23 | 2019-05-07 | -8
1 | 0093 | PKG# 144, Marassi | 8 | 2019-04-01 |  | Approved | 2019-04-15 | 2019-05-04 | 30203655.8 | 16379645.04 | 8909777 | 30 | 2019-05-15 | 8906660.63 | 2019-05-07 | 8
1 | 0093 | PKG# 144, Marassi | 9 | 2019-04-02 |  | Approved | 2019-05-05 | 2019-05-15 | 29741976.58 | 10296123.49 | 9777923.95 | 30 | 2019-06-04 | 9782161.34 | 2019-05-26 | 9
1 | 0093 | PKG# 144, Marassi | 10 | 2019-05-03 |  | Approved | 2019-05-21 | 2019-05-30 | 49431098.39 | 13866715.29 | 11184527.72 | 30 | 2019-06-20 | 10000000 | 2019-06-02 | 18
1 | 0093 | PKG# 144, Marassi | 11 | 2019-06-03 |  | Approved | 2019-06-18 | 2019-07-11 | 50294810.8 | 9087190.4 | 7466833.97 | 30 | 2019-07-18 | 7386054.95 | 2019-07-25 | -7
1 | 0093 | PKG# 144, Marassi | 12 | 2019-08-04 |  | Approved | 2019-09-05 | 2019-10-03 | 94327677.9 | 34717376.4 | 22411649.36 | 30 | 2019-10-05 | 15000000 | 2019-11-28 | -54
1 | 0093 | PKG# 144, Marassi | 12.1 | 2019-08-04 |  | Approved | 2019-09-05 |  | 0 | 0 | 7411649.36 | 30 | 2019-10-05 | 6073691.31 | 2020-01-06 | -93
1 | 0093 | PKG# 144, Marassi | 13 | 2019-12-25 | 2019-12-25 | Approved | 2020-01-05 | 2020-01-22 | 27052955.66 | 11410387.3 | 14635108.89 | 30 | 2020-02-04 | 14000000 | 2020-01-27 | 8
1 | 0093 | PKG# 144, Marassi | 14 | 2020-01-01 | 2020-02-03 | Approved | 2020-02-03 | 2020-02-19 | 14663207.2 | 10741455.4 | 10377806.92 | 30 | 2020-03-04 | 10173240.83 | 2020-03-16 | -12
1 | 0093 | PKG# 144, Marassi | 15 | 2020-08-01 | 2020-08-20 | Approved | 2020-08-13 | 2020-12-10 | 2871075.33 | 2638691 | 10405304.53 | 30 | 2021-01-12 | 9960243.27 | 2021-02-01 | -20
1 | 0093 | PKG# 144, Marassi | 16 | 2021-01-01 | 2021-01-20 | Approved | 2021-01-21 |  | 240149.4 | 150533.34 | 1132971.99 | 30 | 2021-02-20 |  |  | -44
1 | 0093 | PKG# 144, Marassi | رد تأمينات أجتماعية |  | 2020-01-15 | Approved | 2020-01-15 | 2020-01-15 | 0 | 0 |  |  | 2020-01-15 | 2262789.43 | 2020-01-15 | 0
1 | 0093 | PKG# 144, Marassi | رد تأمينات اجتماعية م 12 |  | 2020-09-03 | Approved | 2020-09-03 | 2020-09-03 | 0 | 0 |  |  | 2020-09-03 | 342218.65 | 2020-09-03 | 0
1 | 0093 | PKG# 144, Marassi |  |  | 2020-03-09 | Approved | 2020-03-09 | 2020-03-09 | 0 | 0 |  |  | 2020-03-09 | 1430834.93 | 2020-03-09 | 0
1 | 0093 | PKG# 144, Marassi | RELASE SOCAIL INSURANCE INVOICE(11) |  | 2020-04-29 | Approved | 2020-04-29 | 2020-04-29 | 0 | 0 |  |  | 2020-04-29 | 596740.76 | 2020-04-29 | 0
1 | 0094 | DPW Onshore Port & Terminal | 1 | 2019-01-01 |  | Approved | 2019-02-04 | 2019-02-11 | 23004881.34 | 21036301.63 | 16214642 | 56 | 2019-04-01 | 15998139 | 2019-03-12 | 20
1 | 0094 | DPW Onshore Port & Terminal | 2 | 2019-02-02 |  | Approved | 2019-03-04 | 2019-03-05 | 24408794 | 24408794 | 18306595.43 | 56 | 2019-04-29 | 18062199.23 | 2019-04-15 | 14
1 | 0094 | DPW Onshore Port & Terminal | 3 | 2019-03-01 |  | Approved | 2019-04-11 | 2019-04-11 | 20754393.51 | 20754393.52 | 15565795.14 | 56 | 2019-06-06 | 15357944.03 | 2019-05-28 | 9
1 | 0094 | DPW Onshore Port & Terminal | 4 | 2019-04-28 |  | Approved | 2019-05-02 | 2019-05-16 | 37757872.1 | 37757872 | 28318404.08 | 56 | 2019-06-27 | 27940477.28 | 2019-07-17 | -20
1 | 0094 | DPW Onshore Port & Terminal | 5 | 2019-05-25 |  | Approved | 2019-06-01 | 2019-06-16 | 19480793.18 | 17786447 | 13339835 | 56 | 2019-07-27 | 13161622.85 | 2019-08-05 | -9
1 | 0094 | DPW Onshore Port & Terminal | 6 | 2019-06-26 |  | Approved | 2019-07-13 | 2019-08-06 | 33097932.28 | 33097932 | 24823449.22 | 56 | 2019-09-07 | 24492163.72 | 2019-09-09 | -2
1 | 0094 | DPW Onshore Port & Terminal | 7 | 2019-07-27 |  | Approved | 2019-08-22 | 2019-08-22 | 40506959.46 | 40506958.69 | 30380219.6 | 56 | 2019-10-17 | 29974844.16 | 2019-10-07 | 10
1 | 0094 | DPW Onshore Port & Terminal | 8 | 2019-08-28 |  | Approved | 2019-09-05 | 2019-09-17 | 53367957.97 | 39363675 | 29522756.11 | 56 | 2019-10-31 | 29128813.98 | 2019-10-30 | 1
1 | 0094 | DPW Onshore Port & Terminal | 9 | 2019-09-28 |  | Approved | 2019-10-08 | 2019-10-23 | 54097551.55 | 54097552 | 40573163.66 | 56 | 2019-12-03 | 40031882.73 | 2019-12-08 | -5
1 | 0094 | DPW Onshore Port & Terminal | 10 | 2019-10-29 |  | Approved | 2019-11-12 | 2019-11-24 | 109488509.31 | 90533235.51 | 67899926.6 | 56 | 2020-01-07 | 66994289.3 | 2020-01-13 | -6
1 | 0094 | DPW Onshore Port & Terminal | 11 | 2019-11-19 |  | Approved | 2019-12-12 | 2019-12-22 | 136155500.73 | 102603272.32 | 76515037.44 | 56 | 2020-02-06 | 75494532.33 | 2020-01-29 | 8
1 | 0094 | DPW Onshore Port & Terminal | 12 | 2019-12-01 | 2020-01-15 | Approved | 2020-01-15 | 2020-02-16 | 175539457.8 | 148210852.7 | 111158139.52 | 56 | 2020-03-11 | 59999695.78 | 2020-03-04 | 7
1 | 0094 | DPW Onshore Port & Terminal | 12.1 | 2019-12-01 | 2020-01-15 | Approved | 2020-01-15 | 2020-02-16 | 0 | 0 | 51158443.74 | 56 | 2020-03-11 | 49675726.5 | 2020-03-17 | -6
1 | 0094 | DPW Onshore Port & Terminal | 13 | 2020-01-01 | 2020-02-15 | Approved | 2020-02-18 | 2020-03-16 | 172715454.8 | 124566872.96 | 93425154.72 | 56 | 2020-04-14 | 46089743 | 2020-04-16 | -2
1 | 0094 | DPW Onshore Port & Terminal | 13.1 | 2020-01-01 | 2020-02-15 | Approved | 2020-02-18 | 2020-03-16 | 0 | 0 | 47335411.72 | 56 | 2020-04-14 | 46089743 | 2020-05-07 | -23
1 | 0094 | DPW Onshore Port & Terminal | 14 | 2020-02-01 | 2020-03-17 | Approved | 2020-03-17 | 2020-04-14 | 200759089.1 | 141052143 | 105789107.31 | 56 | 2020-05-12 | 52189292.94 | 2020-05-14 | -2
1 | 0094 | DPW Onshore Port & Terminal | 14.1 |  |  | Approved | 2020-03-17 |  | 0 | 0 | 53599814.37 | 56 | 2020-05-12 | 52189292.94 | 2020-06-07 | -26
1 | 0094 | DPW Onshore Port & Terminal | 15 | 2020-03-01 | 2020-04-18 | Approved | 2020-04-19 | 2020-05-17 | 172209220.96 | 110730132 | 83047599.34 | 56 | 2020-06-14 | 81940298.01 | 2020-06-23 | -9
1 | 0094 | DPW Onshore Port & Terminal | 16 | 2020-04-01 | 2020-05-19 | Approved | 2020-05-19 | 2020-06-21 | 140993514 | 86484920.33 | 64863689.91 | 56 | 2020-07-14 | 63998840.71 | 2020-07-15 | -1
1 | 0094 | DPW Onshore Port & Terminal | 17 | 2020-05-01 | 2020-06-18 | Approved | 2020-06-18 | 2020-07-22 | 108277596.69 | 56454658 | 42340993.43 | 56 | 2020-08-13 | 41776446.85 | 2020-08-16 | -3
1 | 0094 | DPW Onshore Port & Terminal | 18 | 2020-06-01 | 2020-07-23 | Approved | 2020-07-23 | 2020-08-19 | 109240989.24 | 59878397.73 | 44908798.3 | 56 | 2020-09-17 | 44310014 | 2020-09-17 | 0
1 | 0094 | DPW Onshore Port & Terminal | 19 | 2020-07-01 | 2020-08-19 | Approved | 2020-08-19 | 2020-09-16 | 81567142.44 | 34366362.95 | 25774772.21 | 56 | 2020-10-14 | 25431108.58 | 2020-10-15 | -1
1 | 0094 | DPW Onshore Port & Terminal | 20 | 2020-08-01 | 2020-09-17 | Approved | 2020-09-17 | 2020-10-13 | 68801954.05 | 42996289.46 | 32247217.1 | 56 | 2020-11-12 | 31817254.2 | 2020-11-12 | 0
1 | 0094 | DPW Onshore Port & Terminal | 21 | 2020-09-01 | 2020-10-15 | Approved | 2020-10-15 | 2020-10-28 | 74890032.77 | 34792442.43 | 26094331.82 | 56 | 2020-12-10 | 25746407.39 | 2020-12-13 | -3
1 | 0094 | DPW Onshore Port & Terminal | 22 | 2020-10-01 | 2020-11-13 | Approved | 2020-11-13 | 2020-12-20 | 68577404.41 | 23946448.24 | 17959836.19 | 56 | 2021-01-08 | 17720371.71 | 2021-01-21 | -13
1 | 0094 | DPW Onshore Port & Terminal | 23 | 2020-11-01 | 2020-12-10 | Approved | 2020-12-10 | 2021-01-19 | 93583815.28 | 35871966.38 | 26903974.78 | 56 | 2021-02-04 | 26545255.12 | 2021-02-15 | -11
1 | 0094 | DPW Onshore Port & Terminal | 24 | 2020-12-01 | 2021-01-10 | Approved | 2021-01-10 | 2021-02-15 | 140509297.42 | 28199021.24 | 21149265.93 | 56 | 2021-03-07 | 20867275.72 | 2021-03-22 | -15
1 | 0094 | DPW Onshore Port & Terminal | 25 | 2021-01-01 | 2021-02-16 | Submitted | 2021-02-17 |  | 87508998.68 |  | 65631749.01 | 56 | 2021-04-14 |  |  | 9
1 | 0095 | PKG# 101 Slope Stabilization | 1 | 2019-01-01 |  | Approved | 2019-02-02 | 2019-02-17 | 1764438.09 | 1738465.7143 | 1029594.82 | 40 | 2019-03-14 | 1029594.82 | 2019-03-12 | 2
1 | 0095 | PKG# 101 Slope Stabilization | 2 | 2019-02-01 |  | Approved | 2019-03-20 | 2019-03-20 | 3516843.24 | 1610904.3905 | 2222206.65 | 40 | 2019-04-29 | 2222206.65 | 2019-04-21 | 8
1 | 0095 | PKG# 101 Slope Stabilization | 3 | 2019-03-19 |  | Approved | 2019-04-11 | 2019-05-05 | 2467477.23 | 4030399.0476 | 2246109.51 | 40 | 2019-05-21 | 2246109.51 | 2019-05-30 | -9
1 | 0095 | PKG# 101 Slope Stabilization | 4 | 2019-04-20 |  | Approved | 2019-05-22 | 2019-05-22 | 4542532.47 | 4428902.8571 | 2512749.68 | 40 | 2019-07-01 | 2512749.68 | 2019-06-11 | 20
1 | 0095 | PKG# 101 Slope Stabilization | 5 | 2019-06-21 |  | Approved | 2019-07-01 | 2019-07-28 | 2224632 | 2224632 | 2051541.96 | 40 | 2019-08-10 | 2051541.97 | 2019-08-01 | 9
1 | 0095 | PKG# 101 Slope Stabilization | 6 | 2019-07-22 |  | Approved | 2019-08-05 | 2019-08-29 | 3821872 | 3489093.2 | 1988552.05 | 40 | 2019-09-14 | 1988552.05 | 2019-09-08 | 6
1 | 0095 | PKG# 101 Slope Stabilization | 7 | 2019-08-19 |  | Approved | 2019-09-10 | 2019-09-16 | 3602541 | 3126425 | 1824097.57 | 40 | 2019-10-20 | 1824097.56 | 2019-10-28 | -8
1 | 0095 | PKG# 101 Slope Stabilization | 8 | 2019-09-01 |  | Approved | 2019-10-15 | 2019-11-05 | 5811949.86 | 4704891 | 2104893.83 | 40 | 2019-11-24 | 2104893 | 2019-11-14 | 10
1 | 0095 | PKG# 101 Slope Stabilization | 9 | 2019-10-01 |  | Approved | 2019-11-15 | 2019-12-01 | 5174768 | 3175801.54 | 1424816.56 | 40 | 2019-12-25 | 1424816.56 | 2020-01-06 | -12
1 | 0095 | PKG# 101 Slope Stabilization | 10 | 2019-11-01 |  | Approved | 2019-12-17 | 2019-12-31 | 4887507.7605 | 3115828.86 | 1976417 | 40 | 2020-01-26 | 1976416.89 | 2020-02-17 | -22
1 | 0095 | PKG# 101 Slope Stabilization | 11 | 2020-01-01 | 2020-01-30 | Approved | 2020-02-08 | 2020-02-24 | 1959809.4505 | 350346.9805 | 1709961 | 40 | 2020-03-19 | 1709961.04 | 2020-03-23 | -4
1 | 0095 | PKG# 101 Slope Stabilization | 12 | 2020-03-01 | 2020-03-23 | Approved | 2020-03-23 | 2020-04-08 | 3583465 | 2584478 | 1146998.22 | 40 | 2020-05-02 | 1146998.21 | 2020-05-04 | -2
1 | 0095 | PKG# 101 Slope Stabilization | 13 | 2020-04-01 | 2020-04-22 | Approved | 2020-04-23 | 2020-05-04 | 2272890 | 2595712 | 1407211.96 | 40 | 2020-06-02 | 1343055.66 | 2020-06-11 | -9
1 | 0095 | PKG# 101 Slope Stabilization | 14 | 2020-05-01 | 2020-05-31 | Approved | 2020-07-12 | 2020-09-09 | 5042501.1105 | 4659442 | 191421.72 | 40 | 2020-08-21 | 191421.72 | 2020-10-08 | -48
1 | 0095 | PKG# 101 Slope Stabilization | 15 | 2020-09-30 | 2020-12-08 | Approved | 2020-12-09 |  | 181866.4762 | 181866.4762 | 303853.8 | 40 | 2021-01-18 | 303853.8 | 2021-01-21 | -3
1 | 0095 | PKG# 101 Slope Stabilization | 16 | 2020-09-30 | 2021-09-30 | Approved | 2021-02-07 | 2021-02-15 | 0 | 0 | 866491.01 | 40 | 2021-03-19 | 866491 | 2021-03-08 | 11
1 | 0095 | PKG# 101 Slope Stabilization | رد تأمينات اجتماعية م (1 :5) |  | 2020-11-10 | Approved | 2020-11-10 | 2020-11-10 | 0 | 0 |  | 40 | 2020-11-10 | 877190.31 | 2020-11-10 | 0
1 | 0095 | PKG# 101 Slope Stabilization | رد تامينات اجتماعية م (6 ،7 ،8 ،9 ،10 ) |  |  | Approved |  |  | 0 | 0 |  |  | 2021-02-26 | 693232.98 | 2021-02-26 | 0
1 | 0096 | Substation Elco Steel | 2 | 2018-06-01 |  | Approved | 2018-06-03 | 2018-07-22 | 1944504 | 1669926.804 | 1244095.47 | 30 | 2018-07-03 | 1160599.12 | 2018-09-18 | -77
1 | 0096 | Substation Elco Steel | 3 | 2018-07-01 |  | Approved | 2018-07-05 |  | 2696322.196 | 2658220.387 | 2008760.63 | 30 | 2018-08-04 | 1834172.07 | 2018-10-18 | -75
1 | 0096 | Substation Elco Steel | 4 | 2018-08-01 |  | Approved | 2018-08-11 |  | 1926482.604 | 1838590.863 | 1435229.54 | 30 | 2018-09-10 | 1268627.7 | 2018-11-22 | -73
1 | 0096 | Substation Elco Steel | 5 | 2018-09-01 |  | Approved | 2018-09-08 |  | 6955790.536 | 6527819.686 | 5046458.33 | 30 | 2018-10-08 | 3991290.99 | 2018-11-22 | -45
1 | 0096 | Substation Elco Steel | 6 | 2018-10-01 |  | Approved | 2018-11-11 |  | 3411282.26 | 3067261.24 | 3047586.1 | 30 | 2018-12-11 | 3047586.1 | 2019-02-17 | -68
1 | 0096 | Substation Elco Steel | 7 | 2018-11-01 |  | Approved | 2018-12-13 |  | 3725312.62 | 3165661.59 | 2548357.58 | 30 | 2019-01-12 | 1780094.35 | 2019-02-17 | -36
1 | 0096 | Substation Elco Steel | 8 | 2018-12-01 |  | Approved | 2019-01-16 |  | 3172544.999 | 2786776.24 | 2116372.52 | 30 | 2019-02-15 | 1829713.21 | 2019-04-02 | -46
1 | 0096 | Substation Elco Steel | 9 | 2019-01-01 |  | Approved | 2019-02-23 |  | 3842828 | 2055055 | 1560678 | 30 | 2019-03-25 | 1314287.28 | 2019-04-21 | -27
1 | 0096 | Substation Elco Steel | 10 | 2019-03-01 |  | Approved | 2019-04-03 |  | 5990523.58 | 4978708 | 3808343.08 | 30 | 2019-05-03 | 3264225.8 | 2019-06-19 | -47
1 | 0096 | Substation Elco Steel | 11 | 2019-06-02 |  | Approved | 2019-07-03 |  | 4372520.425 | 2458104.95 | 2852078.43 | 30 | 2019-08-02 | 2606365.4 | 2019-12-23 | -143
1 | 0096 | Substation Elco Steel | 12 | 2019-06-02 |  | Approved | 2020-12-06 |  | 4372520.425 | 4372520.425 | 31240.04 | 30 | 2021-01-06 | 31239.74 | 2021-01-05 | 1
1 | 0096 | Substation Elco Steel | Retention Release | 2020-12-06 |  | Approved | 2020-12-06 |  | 0 | 0 | 1617088.7 | 30 | 2021-01-06 | 1617088.7 | 2021-01-05 | 1
1 | 0096 | Substation Elco Steel | Retention Release |  |  | Approved | 2020-10-04 |  | 0 | 0 | 536537.44 | 30 | 2020-10-04 | 536537.44 | 2020-10-04 | 0
2 | 0097 | Agric Greenhouses Tunnel | 1 |  | 2021-02-15 | Approved | 2021-02-15 |  | 0 | 0 | 3830500 |  | 2021-02-15 | 3830500 | 2021-02-15 | 0
1 | 0098 | Mivida Pkg 140-ITP | 1 | 2019-05-01 |  | Approved | 2019-06-03 | 2019-06-10 | 4797449.52 | 4797450 | 2533668.03 | 40 | 2019-07-13 | 2533668.03 | 2019-07-18 | -5
1 | 0098 | Mivida Pkg 140-ITP | 2 | 2019-06-02 |  | Approved | 2019-07-04 | 2019-07-21 | 5522046.79 | 4911239 | 2620895.13 | 40 | 2019-08-13 | 2620895.13 | 2019-08-01 | 12
1 | 0098 | Mivida Pkg 140-ITP | 3 | 2019-07-03 |  | Approved | 2019-07-31 | 2019-08-20 | 6014973.22 | 6244070 | 4070832.39 | 40 | 2019-09-09 | 4070832 | 2019-07-10 | 61
1 | 0098 | Mivida Pkg 140-ITP | 4 | 2019-08-04 |  | Approved | 2019-09-01 | 2019-09-23 | 2565314.47 | 2976636 | 999645.44 | 40 | 2019-10-11 | 999645.44 | 2019-10-14 | -3
1 | 0098 | Mivida Pkg 140-ITP | 5 | 2019-09-04 |  | Approved | 2019-10-02 | 2019-01-15 | 1887669.92 | 1460309 | 1337507.07 | 40 | 2019-11-11 | 1337607.07 | 2019-10-29 | 13
1 | 0098 | Mivida Pkg 140-ITP | 6 | 2019-10-04 |  | Approved | 2019-11-06 | 2019-12-12 | 2000000 | 12232781 | 10719905.24 | 40 | 2019-12-16 | 10719905.2 | 2019-12-12 | 4
1 | 0098 | Mivida Pkg 140-ITP | 7 | 2019-11-04 |  | Approved | 2019-12-05 | 2019-12-19 | 7611814 | 7170532.12 | 6547225.82 | 40 | 2020-01-14 | 6547225.82 | 2020-01-08 | 6
1 | 0098 | Mivida Pkg 140-ITP | 8 | 2019-12-04 | 2020-01-06 | Approved | 2020-01-06 | 2020-01-23 | 6009355.1508 | 6113446.3571 | 4740517.55 | 40 | 2020-02-15 | 4740517.55 | 2020-02-05 | 10
1 | 0098 | Mivida Pkg 140-ITP | 9 | 2020-01-01 | 2020-02-05 | Approved | 2020-02-06 |  | 5394519.4492 | 4233335.7597 | 4559999.07 | 40 | 2020-03-17 | 4559999.09 | 2020-03-23 | -6
1 | 0098 | Mivida Pkg 140-ITP | 10 | 2020-02-01 | 2020-03-05 | Approved | 2020-03-05 |  | 6633028.1932 | 6612228 | 5679423.06 | 40 | 2020-04-14 | 5679423.06 | 2020-04-05 | 9
1 | 0098 | Mivida Pkg 140-ITP | 11 | 2020-03-01 | 2020-04-02 | Approved | 2020-04-02 |  | 3747217 | 3124627.593 | 2647674.18 | 40 | 2020-05-12 | 2647674.17 | 2020-05-14 | -2
1 | 0098 | Mivida Pkg 140-ITP | 12 | 2020-04-01 | 2020-05-02 | Approved | 2020-05-03 | 2020-05-19 | 2213915.57 | 1875813 | 4687303.43 | 40 | 2020-06-12 | 4687303.44 | 2020-06-07 | 5
1 | 0098 | Mivida Pkg 140-ITP | 13 | 2020-05-01 | 2020-06-01 | Approved | 2020-06-01 |  | 1682509.64 | 1425866 | 1169770.65 | 40 | 2020-07-11 | 1169770.65 | 2020-07-05 | 6
1 | 0098 | Mivida Pkg 140-ITP | 14 | 2020-06-01 | 2020-07-01 | Approved | 2020-07-06 | 2020-07-20 | 2791173 | 2429362 | 7336701.0997 | 40 | 2020-08-15 | 7336701.1 | 2020-08-09 | 6
1 | 0098 | Mivida Pkg 140-ITP | 15 | 2020-07-01 | 2020-07-28 | Approved | 2020-08-06 |  | 16540622.5664 | 16266668 | 10305723.5244 | 40 | 2020-09-15 | 10305723.52 | 2020-09-10 | 5
1 | 0098 | Mivida Pkg 140-ITP | 16 | 2020-08-01 | 2020-09-01 | Approved | 2020-09-01 |  | 20902282.8251 | 19380294.5984 | 10553431.24 | 40 | 2020-10-11 | 10553431.24 | 2020-10-08 | 3
1 | 0098 | Mivida Pkg 140-ITP | 17 | 2020-09-01 | 2020-10-01 | Approved | 2020-10-04 |  | 19616183.2567 | 16610857.3267 | 11726998.43 | 40 | 2020-11-13 | 11726998.43 | 2020-11-01 | 12
1 | 0098 | Mivida Pkg 140-ITP | 18 | 2020-10-01 | 2020-11-04 | Approved | 2020-11-09 | 2020-11-29 | 7256151.06 | 4603926.06 | 3831058.93 | 40 | 2020-12-19 | 3831058.93 | 2020-12-07 | 12
1 | 0098 | Mivida Pkg 140-ITP | 19 | 2020-11-01 | 2020-12-03 | Approved | 2020-12-06 |  | 10834949.28 | 11459315.57 | 8885358.6191 | 40 | 2021-01-15 | 8885358.62 | 2021-01-12 | 3
1 | 0098 | Mivida Pkg 140-ITP | 20 | 2020-12-01 | 2020-12-31 | Approved | 2021-01-05 | 2021-02-01 | 6052186.63 | 5957491.07 | 5084359.82 | 40 | 2021-02-14 | 5084359.83 | 2021-02-21 | -7
1 | 0098 | Mivida Pkg 140-ITP | 21 | 2021-01-01 | 2021-01-31 | Approved | 2021-02-07 |  | 12208690.95 | 9991628.98 | 8185193.83 | 40 | 2021-03-19 | 8185193.83 | 2021-03-08 | 11
1 | 0098 | Mivida Pkg 140-ITP | 22 | 2021-02-01 | 2021-03-04 | Submitted | 2021-03-15 |  | 5859232.63 |  | 4807793.33 | 40 | 2021-04-24 |  |  | 19
1 | 0098 | Mivida Pkg 140-ITP | release social insurance invoice 12 |  | 2020-02-05 | Approved | 2020-02-05 | 2020-02-05 | 0 | 0 |  |  | 2020-02-05 | 509706.15 | 2020-02-05 | 0
1 | 0098 | Mivida Pkg 140-ITP | release social insurance invoice 3:7 |  | 2020-03-16 | Approved | 2020-03-16 | 2020-03-16 | 0 | 0 |  |  | 2020-03-16 | 1677431.09 | 2020-03-16 | 0
1 | 0098 | Mivida Pkg 140-ITP | release social insurance invoice 3:7 |  | 2020-09-06 | Approved | 2020-09-06 | 2020-09-06 | 0 | 0 |  |  | 2020-09-06 | 596538.75 | 2020-09-06 | 0
1 | 0098 | Mivida Pkg 140-ITP | رد تأمينات اجتماعية م (10 ،11 ،12 ،13 ) |  | 2020-11-05 | Approved | 2020-11-05 | 2020-11-05 | 0 | 0 |  |  | 2020-11-05 | 908034.47 | 2020-11-05 | 0
1 | 0098 | Mivida Pkg 140-ITP | رد تأمينات اجتماعية م (14 ،15 ،16 ) PKG#140 |  | 2021-01-27 | Approved | 2021-02-01 |  | 0 | 0 |  |  | 2021-02-01 | 1805452.05 | 2021-02-01 | 0
1 | 0098 | Mivida Pkg 140-ITP | رد تأمينات اجتماعية م (17 ،18 ) PKG#140 |  |  | Approved | 2021-03-08 |  | 0 | 0 |  |  | 2021-03-08 | 976304.25 | 2021-03-08 | 0
2 | 0099 | Olympic Multi – Sports Hall | (A-P) |  | 2020-05-18 | Approved | 2020-05-18 | 2020-05-18 | 0 | 0 |  |  | 2020-05-18 | 99806255 | 2020-05-18 | 0
2 | 0099 | Olympic Multi – Sports Hall | (A-P) |  | 2020-05-21 | Approved | 2020-05-21 | 2020-05-21 | 0 | 0 |  |  | 2020-05-21 | 26264795 | 2020-05-21 | 0
2 | 0099 | Olympic Multi – Sports Hall | on account Payment |  | 2020-10-01 | Approved | 2020-10-01 | 2020-10-01 | 0 | 0 |  |  | 2020-10-01 | 124999995 | 2020-10-01 | 0
2 | 0099 | Olympic Multi – Sports Hall | 1 |  | 2020-07-28 | Approved | 2020-07-28 | 2020-07-28 | 0 | 0 |  |  | 2020-07-28 | 105 | 2020-07-28 | 0
2 | 0099 | Olympic Multi – Sports Hall | 2 |  | 2020-09-27 | Approved | 2020-09-27 | 2020-09-27 | 0 | 0 |  |  | 2020-09-27 | 13887855 | 2020-09-27 | 0
2 | 0099 | Olympic Multi – Sports Hall | 3 |  | 2021-02-28 | Approved | 2021-02-28 |  | 0 | 0 |  |  | 2021-02-28 | 2493330 | 2021-02-28 | 0
1 | 0102 | EGAT | Infra Structure (V.O) Part 01 |  |  | Approved |  |  | 0 | 0 |  | 15 | 2019-10-29 | 767138.81 | 2019-09-06 | 53
1 | 0102 | EGAT | Infra Structure (V.O) Part 02 |  |  | Approved |  |  | 0 | 0 |  | 15 | 2019-10-29 | 292862 | 2020-01-16 | -79
1 | 0102 | EGAT | 2 (Fence) | 2019-08-08 | 2019-08-31 | Approved | 2019-09-10 | 2019-10-08 | -616810 | -616810 | -575046.57 | 15 | 2019-10-29 | 0 | 2020-01-16 | -79
1 | 0102 | EGAT | 3 (Fence) | 2019-09-01 | 2019-09-30 | Submitted | 2019-10-14 |  | 1978945 |  | 1270092 | 15 | 2019-10-29 | 457138.81 | 2020-01-16 | -79
1 | 0102 | EGAT | 3.1 (Fence) |  |  | Submitted |  |  | 0 |  | 237906.87 | 15 | 2019-10-29 | 237906.87 | 2020-04-09 | -163
1 | 0102 | EGAT | 4 Final (Fence) | 2019-12-19 | 2019-12-19 | Submitted | 2020-02-05 |  | 4988252.95 |  | 3964366.76 | 15 | 2020-02-24 | 838441.79 | 2020-04-09 | -45
1 | 0102 | EGAT | 4.1 Final (Fence) |  |  | Submitted | 2020-02-05 |  | 0 |  | 3125924.97 | 15 | 2020-02-24 | 1000000 | 2020-04-13 | -49
1 | 0102 | EGAT | 4.2 Final (Fence) |  |  | Submitted | 2020-02-05 |  | 0 |  | 2125924.97 | 15 | 2020-02-24 | 750000 | 2020-06-18 | -115
1 | 0102 | EGAT | 4.3 Final (Fence) |  |  | Submitted | 2020-02-05 |  | 0 |  | 1603000 | 15 | 2020-02-24 |  |  | -406
1 | 0102 | EGAT | EGAT-Asphalt - Retenion Release |  | 2020-12-16 | Submitted | 2020-12-16 |  | 0 |  | 44181 | 15 | 2020-02-24 | 291975.34 | 2020-12-16 | -296
1 | 0102 | EGAT | 1 (Warehouse) | 2019-08-01 | 2019-09-12 | Submitted | 2020-02-05 |  | 5923651.34 |  | 923651.34 | 15 | 2020-03-06 | 923651.34 | 2020-04-09 | -34
1 | 0102 | EGAT | 2 (HELIPAD) | 2019-08-01 | 2019-09-12 | Submitted | 2020-02-05 |  | 10897278.84 |  | 537697 | 15 | 2020-03-06 | 500000 | 2020-03-23 | -17
2 | 0103 | Abou Ghazala Lock & Load | 1 |  | 2020-10-28 | Approved | 2020-10-28 | 2020-10-28 | 0 | 0 |  |  | 2020-10-28 | 1343575 | 2020-10-28 | 0
2 | 0104 | Mohamed Ali Fahmy Lock & Load | 1 |  | 2020-06-18 | Approved | 2020-06-18 |  | 0 | 0 |  |  | 2020-06-18 | 1494015 | 2020-06-18 | 0
2 | 0104 | Mohamed Ali Fahmy Lock & Load | رد تأمين نهائى المشير محمد على لوك لند لود |  | 2020-07-09 | Approved | 2020-07-09 |  | 0 | 0 |  |  | 2020-07-09 | 166155 | 2020-07-09 | 0
2 | 0104 | Mohamed Ali Fahmy Lock & Load | Final |  | 2020-12-14 | Approved | 2020-12-14 |  | 0 | 0 |  |  | 2020-12-14 | 222130 | 2020-12-14 | 0
2 | 0104 | Mohamed Ali Fahmy Lock & Load | رد تأمين نهائى المشير محمد على لوك لند لود |  | 2020-12-12 | Approved | 2020-12-12 |  | 0 | 0 |  |  | 2020-12-12 | 236760 | 2020-12-12 | 0
1 | 0106 | ORA Zed | 1 | 2019-10-19 | 2019-10-28 | Approved | 2019-10-28 | 2019-11-04 | 601798.3 | 601798.3 | 505797.14 | 30 | 2019-11-27 | 505797.14 | 2019-11-27 | 0
1 | 0106 | ORA Zed | 2 | 2019-12-01 | 2019-12-31 | Approved | 2019-12-31 | 31-09-2020 | 431499.48 | 431499.48 | 352690.39 | 30 | 2020-01-30 | 264423.21 | 2020-02-09 | -10
1 | 0106 | ORA Zed | 3 |  | 2021-02-15 | Submitted | 2021-02-15 |  |  |  |  | 30 | 2021-02-15 | 128110.86 | 2021-02-15 | 0
1 | 0107 | DoubleTree Mangroovy ElGouna | 1 | 2019-09-01 |  | Approved | 2019-10-17 | 2019-11-25 | 4079822.24 | 3393576.42 | 2338174.15 | 21 | 2019-11-07 | 2327690.6 | 2019-11-28 | -21
1 | 0107 | DoubleTree Mangroovy ElGouna | 2 | 2019-10-02 |  | Approved | 2019-11-17 | 2019-11-25 | 3535981.982 | 3546875.032 | 3879736.97 | 21 | 2019-12-08 | 3867767.27 | 2019-12-16 | -8
1 | 0107 | DoubleTree Mangroovy ElGouna | 3 | 2019-11-19 |  | Approved | 2019-12-16 | 2019-12-18 | 4055557 | 4290021.355 | 2286139.86 | 21 | 2020-01-06 | 2286139.86 | 2020-01-12 | -6
1 | 0107 | DoubleTree Mangroovy ElGouna | 4 | 2019-12-01 | 2019-01-15 | Approved | 2020-01-21 | 2020-01-21 | 2686069.271 | 2682428.729 | 2579351.66 | 21 | 2020-02-11 | 2572404.48 | 2020-02-27 | -16
1 | 0107 | DoubleTree Mangroovy ElGouna | 5 | 2020-01-01 | 2020-02-15 | Approved | 2020-02-18 | 2020-02-23 | 3430037.649 | 3349162.22 | 1815739.6 | 21 | 2020-03-10 | 1808595.27 | 2020-03-22 | -12
1 | 0107 | DoubleTree Mangroovy ElGouna | 6 | 2020-02-01 | 2020-03-15 | Approved | 2020-03-18 |  | 5706931.19 | 5706931.19 | 4271724.93 | 21 | 2020-04-08 | 4246133.4 | 2020-08-23 | -137
1 | 0107 | DoubleTree Mangroovy ElGouna | 7 | 2020-03-01 | 2020-04-15 | Approved | 2020-04-21 | 2020-04-21 | 3114205.16 | 3114205.16 | 2145687.36 | 21 | 2020-05-12 | 2145687.36 | 2020-08-23 | -103
1 | 0107 | DoubleTree Mangroovy ElGouna | 8 | 2020-06-01 | 2020-07-01 | Approved | 2020-07-04 |  | 3250030 | 3250030 | 1922134.77 | 21 | 2020-07-25 | 1922134.77 | 2020-08-23 | -29
1 | 0107 | DoubleTree Mangroovy ElGouna | 9 | 2020-07-01 | 2020-07-24 | Approved | 2020-07-26 | 2020-07-27 | 1824300 | 1824300 | 996914.3 | 21 | 2020-08-16 | 1030964.27 | 2020-10-01 | -46
1 | 0107 | DoubleTree Mangroovy ElGouna | 10 | 2020-08-01 | 2020-09-01 | Approved | 2020-09-05 | 2020-09-06 | 1947431.76 | 1889241.54 | 1180949.34 | 21 | 2020-09-26 | 1173489.52 | 2020-10-13 | -17
1 | 0107 | DoubleTree Mangroovy ElGouna | 11 | 2020-11-01 | 2020-11-30 | Approved | 2020-12-09 | 2020-12-13 | 881976.77 | 881976.77 | 1788649.6992 | 21 | 2020-12-30 | 1750027.3 | 2021-02-01 | -33
1 | 0107 | DoubleTree Mangroovy ElGouna | 12 | 2020-12-20 | 2020-11-22 | Approved | 2020-12-23 |  | 0 | 0 | 2000000 | 21 | 2021-01-13 | 1942857.14 | 2021-01-21 | -8
1 | 0107 | DoubleTree Mangroovy ElGouna | 13 | 2020-12-01 | 2020-12-31 | Approved | 2021-01-10 |  | 2225492.71 | 2225492.71 | 1964526.99 | 21 | 2021-01-31 | 1951940.18 | 2021-02-21 | -21
1 | 0107 | DoubleTree Mangroovy ElGouna | 14 | 2021-01-01 | 2021-01-31 | Approved | 2021-02-14 |  | 3901532.2 | 3901532.2 | 3061707.07 | 21 | 2021-03-07 |  |  | -29
1 | 0107 | DoubleTree Mangroovy ElGouna | 15 | 2021-02-01 | 2021-03-11 | Approved | 2021-03-13 | 2021-03-30 | 4447615.06 | 4447615.06 | 3016703.15 | 21 | 2021-04-03 |  |  | -2
1 | 0107 | DoubleTree Mangroovy ElGouna | 1 (Fence) | 2019-12-01 | 2019-01-15 | Approved | 2020-01-18 |  | 409200 | 409200 | 429660 | 21 | 2020-02-08 | 425568 | 2020-02-09 | -1
1 | 0107 | DoubleTree Mangroovy ElGouna | 2 (Fence) | 2020-01-01 | 2019-02-15 | Approved | 2020-02-15 | 2020-02-23 | 424545 | 424545 | 445772.25 | 21 | 2020-03-07 | 441526.8 | 2020-03-22 | -15
1 | 0107 | DoubleTree Mangroovy ElGouna | 3 (Fence) | 2020-05-01 | 2020-06-05 | Submitted | 2020-06-06 |  | 189255 |  | 167217.75 | 21 | 2020-06-27 | 173749.2 | 2021-02-21 | -239
1 | 0107 | DoubleTree Mangroovy ElGouna | 1 (Equipment) | 2019-11-01 |  | Approved | 2019-12-12 |  | 80875 | 80875 | 84918.75 | 21 | 2020-01-02 | 73813.12 | 2020-01-26 | -24
1 | 0107 | DoubleTree Mangroovy ElGouna | 2 (Equipment) | 2020-03-01 | 2020-03-17 | Approved | 2020-03-18 |  | 16112.5 | 16112.5 | 16918.13 | 21 | 2020-04-08 | 16757 | 2020-06-11 | -64
1 | 0107 | DoubleTree Mangroovy ElGouna | 3 (Equipment) | 2020-06-01 | 2020-07-09 | Submitted | 2020-07-09 |  | 74812.5 |  | 74812.5 | 21 | 2020-07-30 | 74100 | 2021-02-21 | -206
2 | 0108 | Baron | 1 |  | 2020-10-01 | Approved | 2020-10-01 |  | 0 | 0 |  |  | 2020-10-01 | 5600125 | 2020-10-01 | 0
2 | 0108 | Baron | رد تأمينات اجتماعية قصر البارون |  | 2020-12-07 | Approved | 2020-12-07 |  | 0 | 0 |  |  | 2020-12-07 | 392980 | 2020-12-07 | 0
2 | 0108 | Baron | رد تأمين نهائى سور البارون |  | 2021-02-28 | Approved | 2021-02-28 |  | 0 | 0 |  |  | 2021-02-28 | 355500 | 2021-02-28 | 0
2 | 0109 | Safeer | 1 |  | 2020-02-03 | Submitted | 2020-02-03 | 2020-02-03 |  |  |  |  | 2020-02-03 | 997 | 2020-02-03 | 0
2 | 0109 | Safeer | رد تأمين نهائى |  | 2020-02-13 | Approved | 2020-02-13 | 2020-02-13 | 0 | 0 |  |  | 2020-02-13 | 5454520 | 2020-02-13 | 0
2 | 0109 | Safeer | رد تأمين محجوز |  | 2020-08-13 | Approved | 2020-08-13 | 2020-08-13 | 0 | 0 |  |  | 2020-08-13 | 3298745 | 2020-08-13 | 0
2 | 0109 | Safeer | رد تأمينات اجتماعية م 1 |  | 2020-11-22 | Approved | 2020-11-22 | 2020-11-22 | 0 | 0 |  |  | 2020-11-22 | 3298730 | 2020-11-22 | 0
1 | 0111 | HyperOne Zayed Extension | 1 | 2019-10-19 | 2019-11-10 | Approved | 2019-11-12 | 2019-11-25 | 1684523.66 | 1394602.91 | 2583317 | 14 | 2019-11-26 | 2499090 | 2019-12-02 | -6
1 | 0111 | HyperOne Zayed Extension | 2 | 2019-11-19 | 2019-12-07 | Approved | 2019-12-08 | 2019-12-12 | 11763292.92 | 11763292.92 | 8637289.16 | 14 | 2019-12-22 | 8063620 | 2019-12-23 | -1
1 | 0111 | HyperOne Zayed Extension | 3 | 2019-12-20 | 2019-12-31 | Approved | 2020-01-02 | 2020-01-13 | 10276217.17 | 10276217.59 | 7194819.71 | 14 | 2020-01-16 | 6681008.8353 | 2020-01-19 | -3
1 | 0111 | HyperOne Zayed Extension | 4 | 2020-01-01 | 2020-01-31 | Approved | 2020-02-06 | 2020-02-13 | 15608956.95 | 12451224.37 | 7075844.13 | 14 | 2020-02-20 | 6318712 | 2020-02-23 | -3
1 | 0111 | HyperOne Zayed Extension | 5 | 2020-01-01 | 2020-02-14 | Approved | 2020-02-18 | 2020-02-23 | 5616638.21 | 5616638.21 | 3307335 | 14 | 2020-03-03 | 3307335 | 2020-02-27 | 5
1 | 0111 | HyperOne Zayed Extension | 6 | 2020-02-01 | 2020-02-29 | Approved | 2020-03-02 | 2020-03-07 | 11058708 | 10663484.86 | 8049737 | 14 | 2020-03-16 | 8598544 | 2020-03-15 | 1
1 | 0111 | HyperOne Zayed Extension | 7 | 2020-03-01 | 2020-03-16 | Approved | 2020-03-17 |  | 12302665.46 | 12302665.46 | 8896507.6777 | 14 | 2020-03-31 | 8960935 | 2020-03-26 | 5
1 | 0111 | HyperOne Zayed Extension | 8 | 2020-03-01 | 2020-03-31 | Approved | 2020-04-04 |  | 21120127.14 | 7593014.68 | 3400669 | 14 | 2020-04-18 | 3276433 | 2020-04-21 | -3
1 | 0111 | HyperOne Zayed Extension | 9 | 2020-04-01 | 2020-04-19 | Approved | 2020-04-19 | 2020-04-26 | 2029339 | 2029339 | 1277872 | 14 | 2020-05-03 | 1277872 | 2020-05-05 | -2
1 | 0111 | HyperOne Zayed Extension | 10 | 2020-04-01 | 2020-05-15 | Approved | 2020-05-17 |  | 10283575 | 7741768 | 4810581.9155 | 14 | 2020-05-31 | 4688664 | 2020-06-09 | -9
1 | 0111 | HyperOne Zayed Extension | 11 | 2020-05-01 | 2020-06-16 | Approved | 2020-06-18 | 2020-06-21 | 10630940 | 9960646 | 6700151 | 14 | 2020-07-02 | 6700148 | 2020-07-05 | -3
1 | 0111 | HyperOne Zayed Extension | 12 | 2020-06-01 | 2020-06-30 | Approved | 2020-07-04 | 2020-07-11 | 3093529 | 3093529 | 1896314 | 14 | 2020-07-18 | 1896315 | 2020-07-26 | -8
1 | 0111 | HyperOne Zayed Extension | 13 | 2020-07-01 | 2020-07-31 | Approved | 2020-08-09 | 2020-08-19 | 9225878 | 9161230 | 6738701.3468 | 14 | 2020-08-23 | 6738702 | 2020-09-01 | -9
1 | 0111 | HyperOne Zayed Extension | 14 | 2020-08-01 | 2020-08-31 | Approved | 2020-09-02 | 2020-09-13 | 5875412 | 5698539 | 4476191 | 14 | 2020-09-16 | 4476191 | 2020-09-24 | -8
1 | 0111 | HyperOne Zayed Extension | 15 | 2021-01-01 | 2021-01-31 | Submitted | 2021-03-15 |  | 16363023 |  | 7874134 | 14 | 2021-03-29 |  |  | -7
1 | 0111 | HyperOne Zayed Extension | VAT 1 ,2 ,3 |  | 2020-02-23 | Approved | 2020-02-23 | 2020-02-23 | 0 | 0 |  |  | 2020-02-23 | 1171706 | 2020-02-23 | 0
1 | 0111 | HyperOne Zayed Extension | Steel Supply |  | 2020-02-29 | Approved | 2020-02-29 | 2020-02-29 | 0 | 0 |  |  | 2020-02-29 | 4993651.07 | 2020-02-29 | 0
1 | 0111 | HyperOne Zayed Extension |  |  | 2020-03-02 | Approved | 2020-03-02 | 2020-03-02 | 0 | 0 |  |  | 2020-03-02 | 4724997 | 2020-03-02 | 0
1 | 0111 | HyperOne Zayed Extension | 6 steel deduction |  | 2020-03-23 | Approved | 2020-03-23 | 2020-03-23 | 0 | 0 |  |  | 2020-03-23 | 980000 | 2020-03-23 | 0
1 | 0111 | HyperOne Zayed Extension | 7 steel deduction |  | 2020-03-29 | Approved | 2020-03-29 | 2020-03-29 | 0 | 0 |  |  | 2020-03-29 | 1165162 | 2020-03-29 | 0
1 | 0111 | HyperOne Zayed Extension | Inv.01 MEP |  | 2020-04-26 | Approved | 2020-04-26 | 2020-04-26 | 0 | 0 |  |  | 2020-04-26 | 1165148 | 2020-04-26 | 0
1 | 0111 | HyperOne Zayed Extension | خصم حديد م 8 |  | 2020-04-30 | Approved | 2020-04-30 | 2020-04-30 | 0 | 0 |  |  | 2020-04-30 | 305602.34 | 2020-04-30 | 0
1 | 0111 | HyperOne Zayed Extension | Steel Supply |  | 2020-06-03 | Approved | 2020-06-03 | 2020-06-03 | 0 | 0 |  |  | 2020-06-03 | 3490984 | 2020-06-03 | 0
1 | 0112 | IKEA Extension MoA | 1 | 2019-10-19 | 2019-10-24 | Approved | 2019-10-24 | 2019-11-04 | 5115639.31 | 2651353.89 | 4032556.9 | 22 | 2019-11-15 | 4032556.9 | 2019-11-06 | 9
1 | 0112 | IKEA Extension MoA | 2 | 2019-11-19 | 2019-12-01 | Approved | 2019-12-01 | 2019-12-16 | 14721642.41 | 11255708.29 | 10633715.55 | 22 | 2019-12-23 | 10633715.55 | 2019-11-26 | 27
1 | 0112 | IKEA Extension MoA | 3 | 2019-12-19 | 2019-12-31 | Approved | 2019-12-29 | 2020-01-27 | 10066585.31 | 10066585.32 | 7184168.18 | 22 | 2020-01-20 | 7184168.18 | 2020-01-29 | -9
1 | 0112 | IKEA Extension MoA | 4 | 2020-01-01 | 2020-01-31 | Approved | 2020-02-03 | 2020-02-06 | 17547524.55 | 12574284 | 8278802.07 | 22 | 2020-02-25 | 8278802.07 | 2020-03-05 | -9
1 | 0112 | IKEA Extension MoA | 5 | 2020-02-01 | 2020-02-29 | Approved | 2020-03-02 |  | 10445417.59 | 9421690.8414 | 7929959.81 | 22 | 2020-03-24 | 7929959.81 | 2020-04-14 | -21
1 | 0112 | IKEA Extension MoA | 6 | 2020-03-20 | 2020-03-31 | Approved | 2020-03-31 |  | 11363084 | 5112809.0509 | 3899213.6765 | 22 | 2020-04-22 | 3899213.68 | 2020-05-12 | -20
1 | 0112 | IKEA Extension MoA | 7 | 2020-04-01 | 2020-04-30 | Approved | 2020-05-04 |  | 15356807.93 | 9400137.0042 | 6161858.91 | 22 | 2020-05-26 | 6161858.91 | 2020-07-05 | -40
1 | 0112 | IKEA Extension MoA | 8 | 2020-06-01 | 2020-06-23 | Approved | 2020-06-23 |  | 20473406.5922 | 17657619 | 13080191.1331 | 22 | 2020-08-18 | 13080191.13 | 2020-08-11 | 7
1 | 0112 | IKEA Extension MoA | 9 | 2020-07-01 | 2020-07-22 | Approved | 2020-07-23 |  | 19853625 | 19939474 | 21936362.84 | 22 | 2020-09-17 | 21936362.84 | 2020-09-01 | 16
1 | 0112 | IKEA Extension MoA | 10 | 2020-08-01 | 2020-08-16 | Approved | 2020-08-18 | 2020-09-27 | 13975365 | 16241524.1447 | 10981834.92 | 22 | 2020-10-13 | 10981834.92 | 2020-10-15 | -2
1 | 0112 | IKEA Extension MoA | 11 | 2020-09-01 | 2020-10-12 | Approved | 2020-10-14 | 2020-11-12 | 46229658.48 | 40022086.82 | 16592416.938 | 22 | 2020-12-09 | 16592416.938 | 2020-11-16 | 23
1 | 0112 | IKEA Extension MoA | 12 | 2020-11-01 | 2020-11-25 | Approved | 2020-11-29 | 2021-12-30 | 30949840.16 | 29619584.42 | 15898929.26 | 22 | 2021-01-24 | 15898929.26 | 2021-01-21 | 3
1 | 0112 | IKEA Extension MoA | 13 | 2020-12-01 | 2020-12-31 | Approved | 2021-01-13 | 2021-02-18 | 6803157.62 | A | 5400893.31 | 22 | 2021-03-10 | 5400893.31 | 2021-03-16 | -6
1 | 0112 | IKEA Extension MoA | (A-P) |  | 2020-01-19 | Approved | 2020-01-19 | 2020-01-19 | 0 | 0 |  |  | 2020-01-19 | 5000000 | 2020-01-19 | 0
1 | 0112 | IKEA Extension MoA | (A-P) |  | 2020-01-21 | Approved | 2020-01-21 | 2020-01-21 | 0 | 0 |  |  | 2020-01-21 | 1122526.46 | 2020-01-21 | 0
1 | 0112 | IKEA Extension MoA | (A-P) |  | 2020-01-21 | Approved | 2020-01-21 | 2020-01-21 | 0 | 0 |  |  | 2020-01-21 | 993522.91 | 2020-01-21 | 0
1 | 0112 | IKEA Extension MoA | (A-P) |  | 2020-01-29 | Approved | 2020-01-29 | 2020-01-29 | 0 | 0 |  |  | 2020-01-29 | 5000000 | 2020-01-29 | 0
1 | 0112 | IKEA Extension MoA | (A-P) |  | 2020-01-29 | Approved | 2020-01-29 | 2020-01-29 | 0 | 0 |  |  | 2020-01-29 | 5000000 | 2020-01-29 | 0
1 | 0112 | IKEA Extension MoA | (A-P) |  | 2020-01-29 | Approved | 2020-01-29 | 2020-01-29 | 0 | 0 |  |  | 2020-01-29 | 5000000 | 2020-01-29 | 0
1 | 0112 | IKEA Extension MoA | (A-P) |  | 2020-01-29 | Approved | 2020-01-29 | 2020-01-29 | 0 | 0 |  |  | 2020-01-29 | 1562500 | 2020-01-29 | 0
1 | 0112 | IKEA Extension MoA | (A-P) | (A-P) |  | Submitted | 2020-03-22 |  | 0 |  | 1818917 |  | 2020-03-31 | 1818917.5 | 2020-05-07 | -37
1 | 0112 | IKEA Extension MoA | (A-P) | (A-P) |  | Submitted | 2020-04-13 |  | 0 |  | 3751873.62 |  | 2020-04-20 | 3751873.62 | 2020-05-07 | -17
1 | 0112 | IKEA Extension MoA | (A-P) | (A-P) | 2020-05-19 | Approved | 2020-05-19 | 2020-05-19 | 0 | 0 |  |  | 2020-05-19 | 525633.83 | 2020-05-19 | 0
1 | 0112 | AEON Towers Chiller Building | 1 | 2020-09-01 | 2020-09-16 | Approved | 2020-09-20 |  | 138295.7048 | 1325211.2762 | 1307983.5264 | 56 | 2020-11-15 | 1264914.16 | 2020-10-18 | 28
1 | 0112 | AEON Towers Chiller Building | 2 | 2020-10-01 | 2020-11-03 | Approved | 2020-11-03 | 2020-12-15 | 1388075.5619 | 1300835.2 | 1513146.56 | 56 | 2020-12-29 | 1513146.56 | 2021-01-21 | -23
1 | 0112 | AEON Towers Chiller Building | 3 | 2020-12-01 | 2020-12-20 | Approved | 2020-12-21 |  | 1130137.6381 | 1111505.2 | 780253.07 | 56 | 2021-02-15 | 780253.07 | 2021-02-28 | -13
1 | 0113 | CFC Podium 2 | 1 | 2019-11-19 | 2019-11-25 | Approved | 2019-12-09 | 2020-01-12 | 6808093.37 | 6586123.18 | 6200445 | 60 | 2020-02-07 | 6200445.37 | 2020-02-27 | -20
1 | 0113 | CFC Podium 2 | 2 | 2019-12-19 | 2019-12-25 | Approved | 2020-01-05 | 2020-02-11 | 15810150.71 | 15810150.71 | 17323666.18 | 60 | 2020-03-05 | 17105598.33 | 2020-02-27 | 7
1 | 0113 | CFC Podium 2 | 3 | 2020-01-01 | 2020-01-25 | Approved | 2020-02-05 | 2020-03-03 | 19132016.17 | 16936816.5 | 12263695.27 | 60 | 2020-04-05 | 12263695.64 | 2020-03-31 | 5
1 | 0113 | CFC Podium 2 | 4 | 2020-02-01 | 2020-02-29 | Approved | 2020-03-11 | 2020-04-02 | 39783980.32 | 35226223.2 | 32660833.58 | 60 | 2020-05-10 | 32660833.58 | 2020-06-02 | -23
1 | 0113 | CFC Podium 2 | 5 | 2020-03-20 | 2020-03-17 | Approved | 2020-03-21 | 2020-04-22 | 35816816.67 | 30502560.31 | 25145645.23 | 60 | 2020-05-20 | 24749111.52 | 2020-06-02 | -13
1 | 0113 | CFC Podium 2 | 6 | 2020-03-20 | 2020-03-25 | Approved | 2020-04-07 | 2020-04-30 | 42150322.37 | 42011127.69 | 31500278.62 | 60 | 2020-06-06 | 31500278.62 | 2020-06-02 | 4
1 | 0113 | CFC Podium 2 | 7 | 2020-04-01 | 2020-04-30 | Approved | 2020-05-07 |  | 22998412.5849 | 17879880 | 19510038 | 60 | 2020-07-06 | 19510038.16 | 2020-07-09 | -3
1 | 0113 | CFC Podium 2 | 8 | 2020-05-01 | 2020-05-31 | Approved | 2020-06-08 | 2020-07-07 | 35783152.9971 | 31008098.6054 | 21459124.497 | 60 | 2020-08-07 | 21459125.327 | 2020-08-06 | 1
1 | 0113 | CFC Podium 2 | 9 | 2020-06-01 | 2020-06-25 | Approved | 2020-07-01 | 2020-07-27 | 53195483 | 29660399.8246 | 24499895.52 | 60 | 2020-08-30 | 24499895.82 | 2020-09-03 | -4
1 | 0113 | CFC Podium 2 | 10 | 2020-07-01 | 2020-07-25 | Approved | 2020-07-28 | 2020-08-26 | 52992236.98 | 46257284 | 39448595.57 | 60 | 2020-09-26 | 39448595.84 | 2020-09-30 | -4
1 | 0113 | CFC Podium 2 | 11 | 2020-08-01 | 2020-08-25 | Approved | 2020-08-31 | 2020-09-29 | 29649854 | 22706553.5186 | 18030565.73 | 60 | 2020-10-30 | 18030566.05 | 2020-10-28 | 2
1 | 0113 | CFC Podium 2 | 12 | 2020-09-01 | 2020-09-25 | Approved | 2020-10-07 |  | 48492606.0714 | 35304714.2414 | 29691194.98 | 60 | 2020-12-06 | 29691194.98 | 2020-12-06 | 0
1 | 0113 | CFC Podium 2 | 13 | 2020-10-01 | 2020-10-25 | Approved | 2020-11-05 | 2020-12-09 | 27022429.26 | 13502068.45 | 23213755.7909 | 60 | 2021-01-04 | 23213756.67 | 2020-12-27 | 8
1 | 0113 | CFC Podium 2 | 14 | 2020-11-01 | 2020-11-25 | Approved | 2020-12-05 | 2021-01-11 | 43955748.14 | 29172801.67 | 19708944.2711 | 60 | 2021-02-03 | 19708944.2711 | 2021-02-10 | -7
1 | 0113 | CFC Podium 2 | 15 | 2020-12-01 | 2020-12-25 | Approved | 2021-01-06 | 2021-02-22 | 63421446.6 | 63421446.6 | 40379659.9 | 60 | 2021-03-07 | 40379659.9 | 2021-03-08 | -1
1 | 0113 | CFC Podium 2 | 16 | 2021-01-25 | 2021-01-25 | Approved | 2021-02-03 | 2021-03-21 | 40861483.58 | 25170121.1 | 23198332.7266 | 60 | 2021-04-04 |  |  | -1
1 | 0113 | CFC Podium 2 | 17 | 2021-01-25 | 2021-02-10 | Approved | 2021-03-29 | 2021-03-25 | 39333975.14 | 23196101.96 | 15349352.6823 | 60 | 2021-05-28 |  |  | 53
1 | 0113 | CFC Podium 2 | 18 | 2021-02-01 | 2021-02-25 | Submitted | 2021-03-02 |  | 33708224.18 |  | 12624381.71 | 60 | 2021-05-01 |  |  | 26
1 | 0113 | CFC Podium 2 | 19 | 2021-03-01 | 2021-03-10 | Submitted | 2021-03-17 |  | 22745774.86 |  | 14719075.51 | 60 | 2021-05-16 |  |  | 41
1 | 0113 | CFC Podium 2 | 20 | 2021-03-01 | 2021-03-25 | Submitted | 2021-03-29 |  | 23117724.96 |  | 24402600.35 | 60 | 2021-05-28 |  |  | 53
1 | 0113 | CFC Podium 2 | (A-P) |  | 2020-01-21 | Approved | 2020-01-21 | 2020-01-21 | 0 | 0 |  |  | 2020-01-21 | 25000000 | 2020-01-21 | 0
1 | 0113 | CFC Podium 2 | (A-P) |  | 2020-01-21 | Approved | 2020-01-21 | 2020-01-21 | 0 | 0 |  |  | 2020-01-21 | 25000000 | 2020-01-21 | 0
1 | 0113 | CFC Podium 2 | (A-P) |  | 2020-01-21 | Approved | 2020-01-21 | 2020-01-21 | 0 | 0 |  |  | 2020-01-21 | 12134944.55 | 2020-01-21 | 0
1 | 0113 | CFC Podium 2 | (A-P) |  | 2020-02-27 | Approved | 2020-02-27 | 2020-02-27 | 0 | 0 |  |  | 2020-02-27 | 31067472.28 | 2020-02-27 | 0
1 | 0119 | ESU Ph2-Enabling & Struc | 1 (STR) | 2019-11-19 | 2019-11-25 | Approved | 2019-12-07 |  | 1222080 | 1222080 | 2841415.8 | 7 | 2019-12-14 | 2832501.18 | 2020-01-13 | -30
1 | 0119 | ESU Ph2-Enabling & Struc | 2 (STR) | 2019-12-20 | 2020-01-02 | Approved | 2020-01-02 | 2020-01-11 | 19989409 | 19989409 | 13446882.5 | 7 | 2020-01-09 | 13318143.89 | 2020-01-27 | -18
1 | 0119 | ESU Ph2-Enabling & Struc | 3 (STR) | 2020-01-01 | 2020-01-30 | Approved | 2020-01-30 | 2020-02-04 | 22171564.6 | 22171564.6 | 17089175.5 | 7 | 2020-02-06 | 17089175.4 | 2020-02-17 | -11
1 | 0119 | ESU Ph2-Enabling & Struc | 4 (STR) | 2020-02-01 | 2020-02-29 | Approved | 2020-03-07 | 2020-03-16 | 17983035.5 | 17471459 | 14773850.7 | 7 | 2020-03-14 | 14773850.81 | 2020-03-22 | -8
1 | 0119 | ESU Ph2-Enabling & Struc | 5 (STR) | 2020-03-01 | 2020-03-15 | Approved | 2020-03-26 | 2020-04-09 | 7891720 | 7891720 | 2392694.9 | 7 | 2020-04-02 | 2392694.8 | 2020-04-30 | -28
1 | 0119 | ESU Ph2-Enabling & Struc | 6 (STR) | 2020-04-01 | 2020-04-15 | Approved | 2020-04-26 | 2020-05-06 | 18635558.5 | 18379179 | 7788095.2 | 7 | 2020-05-03 | 7788095.22 | 2020-05-21 | -18
1 | 0119 | ESU Ph2-Enabling & Struc | 7 (STR) | 2020-05-01 | 2020-05-31 | Approved | 2020-06-07 | 2020-06-11 | 9076073.5 | 9076073.5 | 3548357.4 | 7 | 2020-06-14 | 3548357.43 | 2020-06-24 | -10
1 | 0119 | ESU Ph2-Enabling & Struc | 8 (STR) | 2020-06-01 | 2020-06-30 | Approved | 2020-07-07 | 2020-07-09 | 2504382 | 2504382 | 1607563.1 | 7 | 2020-07-14 | 1607563.1 | 2020-08-16 | -33
1 | 0119 | ESU Ph2-Enabling & Struc | 9 (STR) | 2020-07-01 | 2020-07-15 | Approved | 2020-08-17 | 2020-08-27 | 10591344.6 | 9452003 | 8526565.2 | 7 | 2020-08-24 | 8739144.88 | 2020-09-09 | -16
1 | 0119 | ESU Ph2-Enabling & Struc | 10 (STR) | 2020-11-01 | 2020-11-15 | Approved | 2020-11-22 | 2020-11-22 | 5068272 | 5068271.5 | 7703511.3 | 7 | 2020-11-29 | 7703511.41 | 2020-12-09 | -10
1 | 0119 | ESU Ph2-Enabling & Struc | 1 (ARCH-MEP) | 2020-02-01 | 2020-02-29 | Approved | 2020-03-07 | 2020-03-22 | 12614125.71 | 39552087.9 | 35066141.6 | 7 | 2020-03-14 | 15636298.9 | 2020-03-25 | -11
1 | 0119 | ESU Ph2-Enabling & Struc | 1.1 (ARCH-MEP) |  |  | Approved | 2020-03-07 |  | 0 | 0 | 19429842.7 | 7 | 2020-03-14 | 20000000 | 2020-04-14 | -31
1 | 0119 | ESU Ph2-Enabling & Struc | 2 (ARCH-MEP) | 2020-03-01 | 2020-03-31 | Approved | 2020-04-05 | 2020-04-19 | 22283239.73 | 33281363.92 | 5698476.15 | 7 | 2020-04-12 | 5698476.15 | 2020-05-10 | -28
1 | 0119 | ESU Ph2-Enabling & Struc | 3 (ARCH-MEP) | 2020-04-01 | 2020-04-30 | Approved | 2020-05-06 | 2020-05-18 | 22660159.75 | 24169965.91 | 23262698.8 | 7 | 2020-05-13 | 23262698.71 | 2020-06-04 | -22
1 | 0119 | ESU Ph2-Enabling & Struc | 4 (ARCH-MEP) | 2020-05-01 | 2020-05-31 | Approved | 2020-06-14 |  | 27904460.97 | 24591514.84 | 18322601 | 7 | 2020-06-28 | 18322600.95 | 2020-06-28 | 0
1 | 0119 | ESU Ph2-Enabling & Struc | 5 (ARCH-MEP) | 2020-06-01 | 2020-06-30 | Approved | 2020-07-08 | 2020-07-13 | 56253941 | 77007398.3 | 64006362.8 | 7 | 2020-07-15 | 10000000 | 2020-07-16 | -1
1 | 0119 | ESU Ph2-Enabling & Struc | 5.1 (ARCH-MEP) | 2020-06-01 |  | Approved | 2020-07-08 |  | 0 | 0 | 54006362.8 | 7 | 2020-07-15 | 54006362.98 | 2020-07-22 | -7
1 | 0119 | ESU Ph2-Enabling & Struc | 6 (ARCH-MEP) | 2020-07-01 | 2020-07-15 | Approved | 2020-07-27 | 2020-07-29 | 28648433 | 22875033.55 | 8883254.2 | 7 | 2020-08-03 | 8883254.07 | 2020-08-24 | -21
1 | 0119 | ESU Ph2-Enabling & Struc | 7 (ARCH-MEP) | 2020-08-01 | 2020-08-15 | Approved | 2020-08-17 | 2020-08-26 | 72920432.99 | 54216090.64 | 30755604.9 | 7 | 2020-08-24 | 30755604.75 | 2020-09-01 | -8
1 | 0119 | ESU Ph2-Enabling & Struc | 8 (ARCH-MEP) | 2020-08-01 | 2020-08-31 | Approved | 2020-09-10 |  | 69405800 | 61814968.03 | 30127325.7 | 7 | 2020-09-24 | 25127325.53 | 2020-09-29 | -5
1 | 0119 | ESU Ph2-Enabling & Struc | 9 (ARCH-MEP) | 2020-09-01 | 2020-09-15 | Approved | 2020-10-18 | 2020-10-20 | 56169721.63 | 56169721.63 | 20493846 | 7 | 2020-11-01 | 20493846.09 | 2020-11-09 | -8
1 | 0119 | ESU Ph2-Enabling & Struc | 10 (ARCH-MEP) | 2020-10-01 | 2020-10-25 | Approved | 2020-11-10 | 2020-11-10 | 33972687.3 | 24987828 | 10281953.1 | 7 | 2020-11-17 | 9765894.8 | 2020-11-29 | -12
1 | 0119 | ESU Ph2-Enabling & Struc | 11 (ARCH-MEP) | 2020-11-01 | 2020-12-01 | Approved | 2020-12-15 | 2020-12-21 | 18821904 | 15060756.27 | 13851401.2 | 7 | 2020-12-22 | 13851401.2 | 2021-01-06 | -15
1 | 0119 | ESU Ph2-Enabling & Struc | 12 (ARCH-MEP) | 2021-01-01 | 2021-02-10 | Approved | 2021-02-10 | 2021-03-22 | 51471453.87 | 33191485.02 | 23340124.9 | 7 | 2021-02-17 |  |  | -47
1 | 0119 | ESU Ph2-Enabling & Struc | (A-P) |  | 2020-03-08 | Approved | 2020-03-08 | 2020-03-08 | 0 | 0 |  | 7 | 2020-03-08 | 71347886 | 2020-03-08 | 0
1 | 0119 | ESU Ph2-Enabling & Struc | on account Payment |  | 2020-09-01 | Approved | 2020-09-01 | 2020-09-01 | 0 | 0 |  |  | 2020-09-01 | 15000000 | 2020-09-01 | 0
1 | 0119 | ESU Ph2-Enabling & Struc | رد ت اجتماعية م6جامعة السويدى عقد 190 |  | 2021-03-22 | Approved | 2021-03-22 |  | 0 | 0 |  |  | 2021-03-22 | 1023770.56 | 2021-03-22 | 0
2 | 0120 | Mehwar elsalam Lock & Load | Final |  | 2021-01-06 | Approved | 2021-01-06 | 2021-01-06 | 0 | 0 |  |  | 2021-01-06 | 714790 | 2021-01-06 | 0
2 | 0121 | El hegaz bridge | (A-P) |  | 2020-03-26 | Approved | 2020-03-26 | 2020-03-26 | 0 | 0 |  |  | 2020-03-26 | 40000000 | 2020-03-26 | 0
2 | 0121 | El hegaz bridge | (A-P) |  | 2020-05-21 | Approved | 2020-05-21 | 2020-05-21 | 0 | 0 |  |  | 2020-05-21 | 18649995 | 2020-05-21 | 0
2 | 0122 | RING ROAD MARYOTIA EXPANSION | (A-P) |  | 2020-10-07 | Approved | 2020-10-07 | 2020-10-07 | 0 | 0 |  |  | 2020-10-07 | 34159591.2 | 2020-10-07 | 0
2 | 0122 | RING ROAD MARYOTIA EXPANSION | 1 |  |  | Approved | 2020-12-14 |  | 0 | 0 |  |  | 2020-12-14 | 15945365.65 | 2020-12-14 | 0
2 | 0122 | RING ROAD MARYOTIA EXPANSION | 2 | 2020-10-01 | 2020-10-31 | Approved | 2020-10-31 |  | 0 | 0 | 7000000 |  | 2020-12-30 | 7157243.6 | 2021-02-15 | -47
2 | 0122 | RING ROAD MARYOTIA EXPANSION | 3 | 2020-12-01 | 2020-12-31 | Submitted | 2020-12-31 |  |  |  | 8000000 |  | 2021-03-01 | 10759736.15 | 2021-03-08 | -7
2 | 0122 | RING ROAD MARYOTIA EXPANSION | 4 | 2021-01-01 | 2021-02-08 | Submitted | 2021-02-08 |  |  |  | 5192662.75 |  | 2021-04-09 |  |  | 4
2 | 0122 | RING ROAD El Marg | 1 |  |  | Submitted |  |  |  |  | 49942366.856 |  | 2021-04-21 | 45719198.4 | 2021-03-08 | 44
1 | 0123 | Pkg162 Marina Inland Marassi | (A-P) |  | 2020-02-03 | Approved | 2020-02-03 | 2020-02-06 | 0 | 0 | 7681619.5 | 40 | 2020-03-04 | 7681619.5 | 2020-02-18 | 15
1 | 0123 | Pkg162 Marina Inland Marassi | 2 | 2020-02-01 | 2020-02-29 | Approved | 2020-03-05 | 2020-03-22 | 16411967.814 | 8785942 | 7794726.52 | 40 | 2020-04-14 | 7794726.52 | 2020-04-09 | 5
1 | 0123 | Pkg162 Marina Inland Marassi | 3 | 2020-03-01 | 2020-03-18 | Approved | 2020-03-21 | 2020-03-30 | 12632249.88 | 6446667.35 | 5119599.35 | 40 | 2020-04-30 | 5119599.34 | 2020-04-29 | 1
1 | 0123 | Pkg162 Marina Inland Marassi | 4 | 2020-03-01 | 2020-04-06 | Approved | 2020-04-06 | 2020-04-22 | 8748017.73 | 7314177.99 | 6336538.23 | 40 | 2020-05-16 | 6336538.23 | 2020-05-04 | 12
1 | 0123 | Pkg162 Marina Inland Marassi | 5 | 2020-04-01 | 2020-05-05 | Approved | 2020-05-04 | 2020-05-13 | 8846002.32 | 8006098.61 | 6124877.69 | 40 | 2020-06-13 | 6124877.69 | 2020-06-11 | 2
1 | 0123 | Pkg162 Marina Inland Marassi | 6 | 2020-05-01 | 2020-06-06 | Approved | 2020-06-10 | 2020-06-26 | 6745300.27 | 6540614.36 | 4824045.38 | 40 | 2020-07-20 | 4824045.38 | 2020-07-05 | 15
1 | 0123 | Pkg162 Marina Inland Marassi | 7 | 2020-06-01 | 2020-07-06 | Approved | 2020-07-06 | 2020-07-29 | 11477410 | 8862411 | 7215874.21 | 40 | 2020-08-15 | 7215874.21 | 2020-08-06 | 9
1 | 0123 | Pkg162 Marina Inland Marassi | 8 | 2020-07-01 | 2020-08-10 | Approved | 2020-08-16 | 2020-09-03 | 12062100 | 11326452 | 9432027.72 | 40 | 2020-09-25 | 9432027.72 | 2020-09-10 | 15
1 | 0123 | Pkg162 Marina Inland Marassi | 9 | 2020-08-01 | 2020-09-05 | Approved | 2020-09-09 | 2020-09-28 | 16572482.71 | 12073571.58 | 9889305.13 | 40 | 2020-10-19 | 9889305 | 2020-10-18 | 1
1 | 0123 | Pkg162 Marina Inland Marassi | 10 | 2020-09-01 | 2020-10-05 | Approved | 2020-10-07 | 2020-11-03 | 19093483.05 | 13392831.96 | 13282474.21 | 40 | 2020-11-16 | 13282474.22 | 2020-12-02 | -16
1 | 0123 | Pkg162 Marina Inland Marassi | 11 | 2020-10-01 | 2020-11-05 | Approved | 2020-11-05 | 2020-12-02 | 14188599.6 | 9303551.62 | 7840185.49 | 40 | 2020-12-15 | 7840185.48 | 2021-01-21 | -37
1 | 0123 | Pkg162 Marina Inland Marassi | 12 | 2020-11-01 | 2020-12-01 | Approved | 2020-12-13 | 2021-02-02 | 7674593.05 | 7488918.75 | 4608392 | 40 | 2021-01-22 | 4608392 | 2021-02-26 | -35
1 | 0123 | Pkg162 Marina Inland Marassi | 13 | 2020-12-01 | 2021-01-05 | Approved | 2021-01-05 | 2021-02-07 | 720208.824 | 933808.87 | 3429815.25 | 40 | 2021-02-14 | 3429815.26 | 2021-03-15 | -29
1 | 0123 | Pkg162 Marina Inland Marassi | 14 | 2021-01-01 | 2021-01-25 | Approved | 2021-02-03 | 2021-02-24 | 0 | 0 | 502581.44 | 40 | 2021-03-15 | 502581.43 | 2021-03-15 | 0
1 | 0123 | Pkg162 Marina Inland Marassi | رد تأمينات اجتماعية م 2 ،3 |  | 2020-09-03 | Approved | 2020-09-03 | 2020-09-03 | 0 | - | 44077 | 40 | 2020-09-03 | 829293.83 | 2020-09-03 | 0
1 | 0123 | Pkg162 Marina Inland Marassi | Social Insurance |  | 2020-10-18 | Approved | 2020-10-18 | 2020-10-18 | 0 | - |  | 40 | 2020-10-18 | 1584302 | 2020-10-18 | 0
1 | 0123 | Pkg162 Marina Inland Marassi | Social Insurance |  | 2020-11-30 | Approved | 2020-11-30 |  | 0 | 0 | 1223560.05 | 40 | 2020-11-30 | 1223560.05 | 2020-11-30 | 0
1 | 0123 | Pkg162 Marina Inland Marassi | رد تأمينات اجتماعية م 10 |  | 2021-01-27 | Approved | 2021-02-01 |  | 0 | 0 |  |  | 2021-02-01 | 760409.01 | 2021-02-01 | 0
1 | 0123 | Pkg162 Marina Inland Marassi | رد تأمينات اجتماعية م 11 pkg#162 |  |  | Approved | 2021-03-08 |  | 0 | 0 |  |  | 2021-03-08 | 438178.63 | 2021-03-08 | 0
1 | 0123 | Pkg163 Marina Inland Marassi | (A-P) |  | 2020-03-24 | Approved | 2020-03-02 |  | 0 | - | 24950583 |  | 2020-03-31 | 24950583 | 2020-03-29 | 2
1 | 0123 | Pkg163 Marina Inland Marassi | 2 | 2020-06-01 | 2020-07-07 | Approved | 2020-07-07 |  | 301525.5 | 175889.88 | 1068966.43 | 40 | 2020-08-16 | 1068966.43 | 2020-08-04 | 12
1 | 0123 | Pkg163 Marina Inland Marassi | 3 | 2020-07-01 | 2020-08-10 | Approved | 2020-08-18 | 2020-08-26 | 2093986.51 | 1865149 | 2977091.11 | 40 | 2020-09-27 | 2977091.11 | 2020-09-01 | 26
1 | 0123 | Pkg163 Marina Inland Marassi | 4 | 2020-08-01 | 2020-09-03 | Approved | 2020-09-03 | 2020-09-23 | 4573143 | 3480646.12 | 6845695.77 | 40 | 2020-10-13 | 6845695.77 | 2020-10-08 | 5
1 | 0123 | Pkg163 Marina Inland Marassi | 5 | 2020-09-01 | 2020-09-30 | Approved | 2020-09-30 | 2020-10-22 | 5457618.16 | 3896848.67 | 3782501.28 | 40 | 2020-11-09 | 3782501.29 | 2020-11-05 | 4
1 | 0123 | Pkg163 Marina Inland Marassi | 6 | 2020-10-01 | 2020-10-31 | Approved | 2020-11-03 | 2020-11-29 | 8666141.61 | 8666141.61 | 6255172.17 | 40 | 2020-12-13 | 6255172.17 | 2020-12-10 | 3
1 | 0123 | Pkg163 Marina Inland Marassi | 7 | 2020-11-01 | 2020-12-07 | Approved | 2020-12-08 | 2020-12-21 | 4501584.69 | 4389607.26 | 4922193.5 | 40 | 2021-01-17 | 4922193.5 | 2021-01-11 | 6
1 | 0123 | Pkg163 Marina Inland Marassi | 8 | 2020-12-01 | 2021-01-05 | Approved | 2021-01-05 | 2021-02-02 | 7544156.07 | 7415396.3148 | 6050639.77 | 40 | 2021-02-14 | 6050639.77 | 2021-02-21 | -7
1 | 0123 | Pkg163 Marina Inland Marassi | 9 | 2021-01-01 | 2021-01-25 | Approved | 2021-02-25 | 2021-03-08 | 6160521.3452 | 5020188.6252 | 4602212.16 | 40 | 2021-04-06 | 4602212.16 | 2021-03-22 | 15
1 | 0123 | Pkg163 Marina Inland Marassi | 10 | 2021-02-01 | 2021-02-25 | Submitted | 2021-03-03 |  | 5656289.08 |  | 3881758.73 | 40 | 2021-04-12 |  |  | 7
1 | 0123 | Pkg163 Marina Inland Marassi | Social Insurance |  | 2020-10-18 | Approved | 2020-10-18 | 2020-10-18 | 0 | 0 |  | 40 | 2020-10-18 | 78430 | 2020-10-18 | 0
1 | 0123 | Pkg163 Marina Inland Marassi | Social Insurance |  | 2020-11-30 | Approved | 2020-11-30 |  | 0 | 0 |  | 40 | 2020-11-30 | 720699.2 | 2020-11-30 | 0
1 | 0123 | Pkg163 Marina Inland Marassi | رد تأمينات اجتماعية م 5 |  | 2021-01-27 | Approved | 2021-02-01 |  | 0 | 0 |  |  | 2021-02-01 | 277522.63 | 2021-02-01 | 0
1 | 0123 | Pkg163 Marina Inland Marassi | رد تأمينات اجتماعية م 6 pkg#163 |  |  | Approved | 2021-03-08 |  | 0 | 0 |  |  | 2021-03-08 | 451906.96 | 2021-03-08 | 0
1 | 0123 | Pkg177 | (A-P) |  |  | Submitted | 2021-03-24 |  | 0 |  | 22337274.9 | 40 | 2021-03-08 |  |  | -28
1 | 0125 | Lekela 250MW Wind Farm | (A-P) |  | 2020-02-23 | Approved | 2020-02-23 | 2020-02-23 | 0 | 0 | 36300000 | 60 | 2020-02-29 | 36300000 | 2020-02-23 | 6
1 | 0125 | Lekela 250MW Wind Farm | 1 | 2020-03-01 | 2020-03-25 | Approved | 2020-03-29 |  | 2486462 | 1989169.6 | 1670902.46 | 60 | 2020-09-17 | 1670902.46 | 2020-10-11 | -24
1 | 0125 | Lekela 250MW Wind Farm | 2 | 2020-06-01 | 2020-06-30 | Approved | 2020-07-01 |  | 1271272 | 1271271.81 | 1067868.0976 | 60 | 2020-09-17 | 1067868.0976 | 2020-10-11 | -24
1 | 0125 | Lekela 250MW Wind Farm | 3 | 2020-07-01 | 2020-07-26 | Approved | 2020-07-27 |  | 2093987 | 2093986.51 | 1758948.9 | 60 | 2020-09-25 | 1758948.8952 | 2020-10-11 | -16
1 | 0125 | Lekela 250MW Wind Farm | 4 | 2020-08-01 | 2020-08-30 | Approved | 2020-09-12 |  | 777289.9 | 777289.9 | 652923.51 | 60 | 2020-11-11 | 652923.5 | 2020-10-21 | 21
1 | 0125 | Lekela 250MW Wind Farm | 5 | 2020-09-01 | 2020-09-30 | Approved | 2020-09-30 |  | 8446374.73 | 8446374.73 | 7094954.77 | 60 | 2020-11-29 | 7094954.7715 | 2020-11-29 | 0
1 | 0125 | Lekela 250MW Wind Farm | 6 | 2020-10-01 | 2020-10-28 | Approved | 2020-10-28 |  | 23567112.326 | 17262367.14 | 14840272.42 | 60 | 2020-12-27 | 14840272.42 | 2021-02-28 | -63
1 | 0125 | Lekela 250MW Wind Farm | 7 | 2020-11-01 | 2020-11-22 | Approved | 2020-11-23 |  | 18017284.05 | 17619865.65 | 15073158.35 | 60 | 2021-01-22 | 15073158.35 | 2021-02-10 | -19
1 | 0125 | Lekela 250MW Wind Farm | 8 | 2020-12-01 | 2020-12-28 | Approved | 2020-12-28 |  | 38206684.38 | 38206684.38 | 33513527.47 | 60 | 2021-02-26 | 32746957.22 | 2021-02-28 | -2
1 | 0125 | Lekela 250MW Wind Farm | 9 | 2021-01-01 | 2021-01-15 | Submitted | 2021-01-31 |  | 21219483.49 |  | 18594958.19 | 60 | 2021-04-01 |  |  | -4
1 | 0125 | Lekela 250MW Wind Farm | 10 | 2021-02-01 | 2021-02-15 | Submitted | 2021-02-17 |  | 24782925.37 |  | 21709399.51 | 60 | 2021-04-18 |  |  | 13
1 | 0125 | Lekela 250MW Wind Farm | 11 | 2021-03-01 | 2021-03-15 | Submitted | 2021-03-16 |  | 16648813.83 |  | 14823033.6 | 60 | 2021-05-15 |  |  | 40
1 | 0125 | Lekela 250MW Wind Farm | م (1) توريدات |  | 2020-11-24 | Approved | 2020-11-24 |  | 0 | 0 | 124228 |  | 2020-11-24 | 124228 | 2020-11-24 | 0
2 | 0128 | BridgeNasr Rd w Abbas El-Akkad | (A-P) |  | 2020-05-13 | Approved | 2020-05-13 |  | 0 | 0 | 20000000 |  | 2020-05-13 | 20000000 | 2020-05-13 | 0
2 | 0129 | Asher Mn Ramadan Bridge No2 | (A-P) |  | 2020-08-17 | Approved | 2020-08-17 |  | 0 | 0 |  |  | 2020-08-17 | 5299995 | 2020-08-17 | 0
2 | 0129 | Asher Mn Ramadan Bridge No2 | رد تأمين نهائى كوبرى العاشر |  | 2020-12-08 | Approved | 2020-12-08 |  | 0 | 0 |  |  | 2020-12-08 | 3163290 | 2020-12-08 | 0
2 | 0130 | Kafr Shokr Bridge | 1 |  | 2020-11-22 | Approved | 2020-11-22 |  | 0 | 0 |  |  | 2020-11-22 | 2644030 | 2020-11-22 | 0
2 | 0133 | GOV2 - Infra | 1 | 2021-01-01 | 2021-01-31 | Submitted | 2021-01-31 |  | 118000 |  | 3223167.81 | 60 | 2021-04-01 | 2964607 | 2021-03-15 | 17
2 | 0133 | GOV2 - Infra | 2 | 2021-02-01 | 2021-02-28 | Submitted | 2021-03-04 |  | 6769868.75 |  | 5840472.48 | 60 | 2021-05-03 |  |  | 28
2 | 0134 | Cairo-Alex Railway | (A-P) |  | 2020-10-18 | Approved | 2020-10-18 |  | 0 | 0 | 144582383 |  | 2020-10-18 | 144582383 | 2020-10-18 | 0
2 | 0134 | Cairo-Alex Railway | 1 | 2020-12-01 | 2020-12-20 | Approved | 2020-12-20 |  | 7627641 | 7627641 | 6006767 | 60 | 2021-02-18 | 5025720.35 | 2021-03-08 | -18
2 | 0134 | Cairo-Alex Railway | 2 | 2021-01-01 | 2021-01-31 | Approved | 2021-01-31 |  | 5895813 | 5895813 | 4642953 | 60 | 2021-04-01 |  |  | -4
2 | 0134 | Cairo-Alex Railway | 3 | 2021-02-01 | 2021-03-07 | Approved | 2021-02-28 |  | 8330916 | 5582108 | 4395910 | 60 | 2021-04-29 |  |  | 24
2 | 0135 | Hassan El Mamoun Bridge | 1 |  | 2021-02-28 | Approved | 2021-02-28 |  | 0 | 0 |  |  | 2021-02-28 | 4682080 | 2021-02-28 | 0
1 | 0137 | ORA ZED - Ph 01B - Pkgs A&D | (A-P) |  |  | Approved | 2020-09-30 |  | 0 | 0 | 91380773.3 | 56 | 2020-11-25 | 91380773 | 2020-11-09 | 16
1 | 0137 | ORA ZED - Ph 01B - Pkgs A&D | 1 | 2020-11-01 | 2020-11-25 | Approved | 2020-11-23 |  | 4393014.1 | 2407390.5714 | 10345156.8 | 56 | 2021-01-18 | 9787286.79 | 2021-02-21 | -34
1 | 0137 | ORA ZED - Ph 01B - Pkgs A&D | 2 | 2020-12-01 | 2020-12-31 | Approved | 2020-12-22 |  | 47114233.048 | 43865060.0957 | 37827388.66 | 56 | 2021-02-16 |  |  | -48
1 | 0137 | ORA ZED - Ph 01B - Pkgs A&D | 3 | 2021-01-01 | 2021-01-25 | Submitted | 2021-01-31 |  | 24413679.5048 |  | 28404325.826 | 56 | 2021-03-28 |  |  | -8
1 | 0137 | ORA ZED - Ph 01B - Pkgs A&D | 4 | 2021-02-01 | 2021-02-28 | Submitted | 2021-03-15 |  | 20767703.1429 |  | 21185755.528 | 56 | 2021-05-10 |  |  | 35
1 | 0141 | ElSewedy HQ Internal Finishing | (A-P) |  |  | Approved | 2020-11-11 |  | 0 | 0 | 103231218.3 | 21 | 2020-12-02 | 103231218.3 | 2020-12-07 | -5
1 | 0141 | ElSewedy HQ Internal Finishing | 1 | 2021-01-01 | 2021-01-31 | Approved | 2021-02-03 | 2021-02-22 | 1205204.8 | 1435679.4286 | 6847513.73 | 21 | 2021-02-24 | 6847513.64 | 2021-03-22 | -26
1 | 0141 | ElSewedy HQ Internal Finishing | 2 | 2021-02-01 | 2021-02-28 | Approved | 2021-03-08 |  | 8490954.6667 | 7766126.6667 | 8152527.57 | 21 | 2021-03-29 |  |  | -7
1 | 0138 | Kattameya Creeks | (A-P) |  |  | Approved | 2020-11-12 |  | 0 | 0 | 200529173.7 | 40 | 2020-12-22 | 200000000 | 2021-01-12 | -21
1 | 0138 | Kattameya Creeks | 1 | 2020-12-01 | 2020-12-31 | Approved | 2021-01-14 |  | 2919397.4 | 2268973.71 | 2741191.2884 | 40 | 2021-02-23 | 2741191.29 | 2021-03-15 | -20
1 | 0138 | Kattameya Creeks | 2 | 2021-01-01 | 2021-01-31 | Approved | 2021-02-04 | 2021-02-18 | 12571948.23 | 11780609.67 | 11302769.94 | 40 | 2021-03-16 | 11302769.94 | 2021-03-28 | -12
1 | 0138 | Kattameya Creeks | 3 | 2021-02-01 | 2021-02-28 | Submitted | 2021-03-06 |  | 42884514.58 |  | 40115416.96 | 40 | 2021-04-15 |  |  | 10
1 | 0142 | BP178-Lagoon Discharge | (A-P) |  |  | Approved | 2021-01-25 | 2021-02-02 | 0 | 0 | 3747170.2 | 30 | 2021-02-24 | 3747170 | 2021-02-15 | 9
1 | 0142 | BP178-Lagoon Discharge | 1 | 2021-02-01 | 2021-02-28 | Submitted | 2021-03-04 |  | 16438756.67 |  | 13488821.78 | 30 | 2021-04-03 |  |  | -2
1 | 0144 | EGAT Pelletizing Plant | (A-P) |  |  | Approved |  |  | 0 | 0 |  |  | 2021-02-28 | 10000000 | 2021-02-28 | 0
A2 |  | Ministry Building (MEP) | جارى ( 3 ) | [7 empty] | 88009455.156
A2 |  | حى الوزرات - شبكات المياه والصرف الصحي | جارى (2 ) | [7 empty] | 141304.8
A2 |  | BridgeNasr Rd w Abbas El-Akkad | ختامى ( 1 ) | [7 empty] | 15373622.36
A2 |  | Tunnel Of Sokhna Road | ختامى | [7 empty] | 1042894.6219
A2 |  | Fish Market (F.F & Plumping) | جارى ( 1 ) | [7 empty] | 2642227.56
A2 |  | Hassan El Mamoun Bridge | تامين نهائي | [7 empty] | 3787617
A2 |  | Hyper El-Temsah | Inv.01 | [7 empty] | 59480456.8201
A2 |  | Hyper El-Temsah (MEP) | جارى (1 ) | [7 empty] | 51682050.43
A2 |  | Hyper El-Temsah (Plumping) | جارى (1 ) | [7 empty] | 2294345.334
A2 |  | Ministry Building (Concrete) | جارى (4) | [7 empty] | 43649644.805
A2 |  | Ministry Building (Core) | جارى (6) | [7 empty] | 10951218.2909
A2 |  | Ministry Building (Allocation) | جارى (6) | [7 empty] | 14200673.9952
A2 |  | Sports Hall | جارى (1 ) | [7 empty] | 4627310.4359
A2 |  | Baron | ختامى | [7 empty] | 3142350.876
A2 |  | Mohamed Ali Palace | جارى 3 | [7 empty] | 660456.5184
A2 |  | Mohamed Ali Palace | جارى (4) | [7 empty] | 6352691.688
A2 |  | Hassan El Mamoun Bridge | تامين اعمال | [7 empty] | 3566242.7755
A2 |  | Hassan El Mamoun Bridge | ختامى 2 | [7 empty] | 3453404
A2 |  | El Alamain PO | تأمين نهائى | [7 empty] | 1083150
A2 |  | El hegaz bridge | جارى ( 1 ) | [7 empty] | 39817004.08
A2 |  | El hegaz bridge | ختامى | [7 empty] | 4829358.4554
A2 |  | El hegaz bridge | تامين اعمال | [7 empty] | 5946608.5438
A2 |  | Fish Market (Civil) | ختامى ( 2 ) | [7 empty] | 8511749.3832
A2 |  | Fish Market (Civil) | تأمين أعمال | [7 empty] | 2358253.65
A2 |  | Fish Market (F.F & Plumping) | ختامى ( 2 ) | [7 empty] | 846258
A2 |  | Fish Market (F.F & Plumping) | تأمين أعمال | [7 empty] | 207647.95
A2 |  | Suez Tunnel L&L | تامين اعمال | [7 empty] | 251250.0375
A2 |  | محور الطواريء - لوك اند لود | ختامى (1) | [7 empty] | 15662050.4
A2 |  | Hyper El-Temsah (Civil) | ختامى ( 2 ) | [7 empty] | 12308705.2452
A2 |  | Hyper El-Temsah (Civil) | تأمين أعمال | [7 empty] | 5121327.1
A2 |  | Hyper El-Temsah (Plumping) | ختامى ( 2 ) | [7 empty] | 1663081.896
A2 |  | Hyper El-Temsah (Plumping) | تأمين أعمال | [7 empty] | 244204.7
A2 |  | Hyper El-Temsah (MEP) | ختامى ( 2 ) | [7 empty] | 2892867.6
A2 |  | Hyper El-Temsah (MEP) | تأمين أعمال | [7 empty] | 3443210.35
A2 |  | Elmostaqbal Lock & Load | تامين اعمال | [7 empty] | 184503.44
A2 |  | Central Road Lock & Load | تامين نهائى | [7 empty] | 51241
A2 |  | Ministry Building (Long lead) | جارى (4) | [7 empty] | 5445651.7875
A2 |  | Ministry Building (Long lead) | جارى (2) تأمين أعمال | [7 empty] | 1695145.9075
A2 |  | Ministry Building (Long lead) | جارى (3) تأمين أعمال | [7 empty] | 324755.0625
A2 |  | Asher Mn Ramadan Bridge No2 | جارى (1 ) شهادة تأمينات اجتماعية | [7 empty] | 3634950.6
A2 |  | Asher Mn Ramadan Bridge No2 | ختامى (1) | [7 empty] | 10256643.8366
A2 |  | Agric Greenhouses Tunnel | تامين نهائى | [7 empty] | 551100
A2 |  | حى الوزرات - شبكات المياه والصرف الصحي | جارى (1 ) | [7 empty] | 92731.6
A2 |  | Asher Mn Ramadan Bridge No2 | جارى (1 ) شهادة تأمينات اجتماعية | [7 empty] | 3634950.6
A2 |  | Kayan MEP | جارى 3 شهادة تأمينات اجتماعية | [7 empty] | 302146.9
A2 |  | Kayan MEP | جارى 6 شهادة تأمينات اجتماعية | [7 empty] | 2306143.75
A2 |  | كيان منع انتشار حريق | جارى 1 - شهادة تأمينات | [7 empty] | 519000
A2 |  | Mohamed Ali Fahmy Lock & Load | جارى 1 - شهادة تأمينات | [7 empty] | 315694.5
A2 |  | Mohamed Ali Fahmy Lock & Load | جارى 2 - شهادة تأمينات | [7 empty] | 16615.5
A2 |  | حى الوزرات - العناصر المائيه | جارى (2 ) شهادة تأمينات اجتماعية | [7 empty] | 105678.15
A2 |  | حى الوزرات - العناصر المائيه | جارى (3 ) شهادة تأمينات اجتماعية | [7 empty] | 75673.8
A2 |  | Safeer | ختامى شهادة تأمينات اجتماعية | [7 empty] | 353484.55
A2 |  | Fish Market (Elec) | ختامى ( 1 ) | [7 empty] | 211383.5
A2 |  | Mohamed Ali Palace | جارى (2 ) شهادة تأمينات اجتماعية | [7 empty] | 30749.4
A2 |  | Suez Tunnel L&L | جارى 1 - شهادة تأمينات | [7 empty] | 251250.0375
A2 |  | Suez Tunnel L&L | ختامى 2 - شهادة تأمينات | [7 empty] | 97969.47
A2 |  | MR3 - لوك اند لود | ختامى 1 - شهادة تأمينات | [7 empty] | 88949.55
A2 |  | Elmostaqbal Lock & Load | تأمين أعمال- شهادة تأمينات | [7 empty] | 205003.8
A2 |  | Ministry Building (Shell) | جارى 3 - شهادة تأمينات | [7 empty] | 1381159.7575
A2 |  | Ministry Building (Shell) | جارى 4 - شهادة تأمينات | [7 empty] | 1714930.985
A2 |  | Ministry Building (Shell) | جارى 5 - شهادة تأمينات | [7 empty] | 1142854.3275
A2 |  | Ministry Building (Shell) | جارى 6 - شهادة تأمينات | [7 empty] | 326197.6325
A2 |  | Ministry Building (Shell) | جارى 7 - شهادة تأمينات | [7 empty] | 430255.5
A2 |  | Ministry Building (Allocation) | جارى 3 - شهادة تأمينات | [7 empty] | 464585.6
A2 |  | Ministry Building (Allocation) | جارى (4 ) شهادة تأمينات اجتماعية | [7 empty] | 1125065.8
A2 |  | Ministry Building (Allocation) | جارى (5 ) شهادة تأمينات اجتماعية | [7 empty] | 874070.49
A2 |  | Ministry Building (Land scape) | جارى (1 ) شهادة تأمينات اجتماعية | [7 empty] | 149150.6825
A2 |  | Ministry Building (Land scape) | جارى (2 ) شهادة تأمينات اجتماعية | [7 empty] | 206625.26
A2 |  | Ministry Building (Land scape) | جارى (3 ) شهادة تأمينات اجتماعية | [7 empty] | 157228.79
A2 |  | Ministry Building MEP | جارى (1 ) شهادة تأمينات اجتماعية | [7 empty] | 2701100.85
A2 |  | Ministry Building MEP | جارى (2 ) شهادة تأمينات اجتماعية | [7 empty] | 9207405.15
A2 |  | Ministry Building (Core) | جارى( 3) شهادة تأمينات اجتماعية | [7 empty] | 422312.9025
A2 |  | Ministry Building (Core) | جارى (4 ) شهادة تأمينات اجتماعية | [7 empty] | 1522657.45
A2 |  | Ministry Building (Core) | جارى (5 ) شهادة تأمينات اجتماعية | [7 empty] | 1057237.595
A2 |  | Ministry Building (Fitout) | جارى (2 ) شهادة تأمينات | [7 empty] | 307140.28
A2 |  | Ministry Building (Fitout) | جارى (3 ) شهادة تأمينات | [7 empty] | 78370.512
A2 |  | Ministry Building (Fitout) | جارى (4 ) شهادة تأمينات | [7 empty] | 163622.478
A2 |  | Ministry Building (Concrete) | تأمين نهائي | [7 empty] | 846462
A2 |  | Ministry Building (Long lead) | جارى (2) تأمينات اجتماعية | [7 empty] | 1695145.9075
A2 |  | Ministry Building (Long lead) | جارى (3) تأمينات اجتماعية | [7 empty] | 324755.0625
A2 |  | Sports Hall | جارى (1 ) شهادة تأمينات اجتماعية | [7 empty] | 3412750
A2 |  | Sports Hall | جارى (2 ) شهادة تأمينات اجتماعية | [7 empty] | 4250175.845
A2 |  | Sports Hall | جارى (3 ) شهادة تأمينات اجتماعية | [7 empty] | 1846773.35
A2 |  | Hassan El Mamoun Bridge | جارى (1 ) شهادة تأمينات اجتماعية | [7 empty] | 3566242.8
A2 |  | Abou Ghazala Lock & Load | ختامي 1 - شهادة تأمينات | [7 empty] | 115500
A2 |  | Abou Ghazala Lock & Load | تامين نهائي | [7 empty] | 115500
A2 |  | EL MOSSTASMREEN substation | [8 empty] | 8000000

## Project List (hidden)
Project Name
0006 Marassi Civic Center Pkg 45
0008 Al Oula Infra
0012 New Giza Phase 01
0013 Hyper Solimanya
0019 Ismailia Bridges
0023 Maxium Mall
0028 Ataqqa Power Plant
0030 Mall of Egypt Bridge
0031 Marassi Tanks Pkg 22
0032 Sodic Club House
0033 Montazah Hotel Sharm
0034 Uptown Cairo Pkg 53
0035 Bani Suif Power Plant 1021
0037 New Giza Phase 02
0039 JICA Wind Farm Gabal El Zeet
0040 El Mostathmereen Mokatam Substation
0041 Levana UpTown Pkg 62
0045 Kayan 110
0046 El Amal Bridge
0047 Bani Suif Cement
0048 New Giza Wall
0051 Tamey El Amdid Mansora Power Station 500-220
0052 Ismailia Substation 500-220
0053 El Amal Bridge L&L
0054 FIEM Wind Farm Gabal El Zeet
0055 KFW Wind Farm Gabal El Zeet
0058 Marassi Tank Pkg 107
0059 Ben Zayed Tunnel
0060 Ministries Buildings
0061 Bani Suif Substation
0063 Royal City Mall
0064 Shoubra Banha Bridge L&L
0065 SLP Logistic Center PI Park Sewedy Stores
0066 Mostakbal L&L
0068 Kayan L&L
0069 Elco Suez Steel Rolling Mill Plant 3
0070 Hyper El Temsah
0071 Marassi Bridge Pkg 117
0072 Siemens Power Station
0074 El Sokhna Tunnel 01
0075 Abu Sultan Bridge 01
0076 Mintra Factory
0077 King Farouk Restoration
0078 Mohamed Ali Palace
0079 Nefisha Bridge
0080 Fish Market
0081 Al Jazi Mall
0083 Benban Aswan Alcazars Solar Park
0084 El Alameen Roads Earth Works
0085 El Sewedy Univeristy
0086 El Sokhna Tunnel L&L
0087 R05 Z03
0088 R05 Residential District Z1 & Z2
0089 Abu Sultan Bridge 02 Greenhouse
0090 El Sokhna Tunnel 02
0091 El Awsty Middle Tunnel L&L
0092 Sodic Eastown EDNC
0093 Marassi Civic Center Pkg 144
0094 DPW Sokhna Dubai Port
0095 Slope Stablization PKG 101
0096 Elco Steel Substation
0097 Sewab Greenhouse Tunnel
0098 Mivida Irrigation Treatment Plant Pkg 140
0099 Multi Sports Hall
0100 Emergency Bridge
0101 Pyramid El Remayah Tunnel
0102 EGAT
0103 Abou Ghazala Bridge Ramp L&L
0104 Mohamed Aly Fahmy Ramps L&L
0105 El Mosheer Bridge Abu Zaied Khdr L&L
0106 Ora Zed Park L&L
0107 DoubleTree Mangroovy El Gouna Hotel
0108 Baron Palace Fence
0109 Safeer Square Bridge
0110 Suez Road Tunnel Res L&L
0111 HyperOne Zayed Extention
0112 IKEA Extention MoA
0113 CFC Podium II
0114 Mostafa Kamel Bridge L&L
0115 Josef Tito Bridge L&L
0116 Espiko Bridge L&L
0117 El Gabal El Asfr Tunnel L&L
0118 MR3 Bridge L&L
0119 El Sewedy Univeristy 2
0119 El Sewedy Univeristy 2 Phase 2
0120 Mehwar El Salam Axis L&L
0121 El Hegaz Square Bridge
0122 Ring Road Extension
0123 Marina Inland Marassi Pkg 162
0123 Pkg 163 Marassi Marina Infrastructure
0124 Sultana Malek Restoration
0125 Lekela 250MW Wind Farm
0126 New Giza Hospital
0127 Kayan Landscape
0128 Abbas Akkad Bridge
0129 El Asher Men Ramadan Bridge
0130 Kafr Skokr Bridge
0131 Al Shorouk Bridge (LRT)
0132 Ring Road El Marg
0133 GOV2 Infra
0134 Cairo Alex Railroad
0135 Hassan El Mamoun Bridge
0136 Sherouk Bridge L&L
0137 Ora Zed Park
0138 Kattameya Creeks
0139 Faculty of Medicine
0140 Diplomatic District - Infra
0141 El Sewedy CFC HQ Internal Finishing
0142 Pkg 178 Lagoon Discharge
0143 El Khatatba Bridge
0144 EGAT Pelletizing Plant
0145 Sokhna Port Expansion
0146 Waldorf Astoria Mock Up Room
0147 MDF Factory
0148 Olympic City L&L
0149 Kemet Building
000x Alegria DP Port
000x Alexandria Bridges
000x Allegria Club House
000x Alstom-French Station
000x Autoville Strip Mall
000x Batch Plant
000x Dubai Port Sokhna Basin 1
000x El Alameen Bridge L&L
000x El Asher Bridge
000x El Asher of Ramadan Bridge L&L
000x El Mahala Bridge
000x El Mostakbal Bridge L&L
000x El Obour Bridge B2
000x El Shone Bridge
000x El Wahat Bridge
000x El Wahat Tunnel
000x EMEC
000x FM85
000x Hyper Matrouh
000x Ismailia Bridge L&L
000x Logestica 01
000x Logestica 02
000x Marassi Bridges Pkg 37
000x Marassi Golf Maintance Building Pkg 58
000x Point 90 New Cairo Mall
000x Sodic MV Cables
000x Sodic West Town Hub
000x TB2 Cairo Airport Terminal
000x Twin Towers
000x Uptown Soil Stabilization Pkg 32
000x Uptown Tank Pkg 17A
0xxx Electric Train LRT
0xxx Sea Shell Playa

## POC (hidden)
DATE | Description | CODT CENTER | Total Contracts | Total Cost
2013-06-01 | Alex - Bridge |  | 35589876.5 | 28766462
2013-06-01 | D.Mall |  | 48637725 | 47805000
2013-06-01 | Zaid II |  | 48655938.52 | 42460203
2013-06-01 | Uptown Cairo PKG 17 |  | 40367752 | 33672697
2013-06-01 | M.Bridges BP 37 |  | 27486610 | 22308006
2013-06-01 | P.School |  | 24785270 | 22050000
2013-06-01 | Al Oula |  | 33000000 | 30000000
2013-06-01 | SODIC HUB |  | 64334151 | 54653461
2013-06-01 | Uptown Cairo PK#32 |  | 5814614.8 | 6238750
2013-06-01 | Logistica Phase II |  | 19619723 | 13972642
2013-06-01 | Marassi Tank PKG22 |  | 17409328 | 14236821
2013-06-01 | Marassi Civic center |  | 54039717 | 52324136
2013-06-01 | TCHAD |  | 23332988 | 13133940
2013-06-01 | Misr Express |  | 16183910 | 12168169
2013-06-01 | Limak TB2 |  | 49359671.05 | 46916158
2013-06-01 | Carfour |  | 53449951 | 51000000
2013-06-01 | Sodic West Town |  | 2317895 | 1890000
2015-12-12 | D.Mall |  | 51072634 | 55255998
2015-12-12 | Zaid II |  | 64000000.23 | 63714421.967
2015-12-12 | Uptown Cairo PKG 17 |  | 55905931 | 53403393.3863
2015-12-12 | M.Bridges BP 37 |  | 26193836.68 | 27228966.3975
2015-12-12 | P.School |  | 24658801 | 22318865.7202
2015-12-12 | Al Oula |  | 60627323 | 50000000
2015-12-12 | SODIC HUB |  | 54160920.41 | 56137642.32
2015-12-12 | Uptown Cairo PK#32 |  | 17421145.8 | 19958702.4389
2015-12-12 | Logistica Phase II |  | 20681422 | 16069494.51
2015-12-12 | Marassi Tank PKG22 |  | 18438370 | 16655530.55
2015-12-12 | Marassi Civic center |  | 55905931 | 55489926.2535
2015-12-12 | TCHAD OFF-SHORE |  | 26188774.7 | 10748930.96
2015-12-12 | Misr Express |  | 7271134.78 | 6562385.54
2015-12-12 | Limak TB2 |  | 119626844 | 96755558
2015-12-12 | Carfour |  | 57725947 | 43502005.21
2015-12-12 | Sodic West Town |  | 6395865 | 5349893.5806
2015-12-12 | MARASSI PKG#58 |  | 4720405.25 | 5275181.8987
2015-12-12 | SODIC Villas |  | 4628204.31 | 3871486.73
2015-12-12 | EZZ STEEL |  | 41346417.38 | 37079290.2792
2015-12-12 | SODIC MV Cables |  | 19589518 | 16384636.8472
2015-12-12 | NEW Cairo Mall |  | 145010925.68 | 129215876.9678
2015-12-12 | Mahala Bridge |  | 62700000 | 48550966.2717
2015-12-12 | AL-Asmarat |  | 6636851 | 8517150.2182
2015-12-12 | Logistica Phase III |  | 4820461 | 3681383
2015-12-12 | El Wahat Bridges |  | 33068735.17 | 19855963.2606
2015-12-12 | Hyper Al Sulaimaniya |  | 97181729.03 | 91999999.6317
2015-12-12 | EL ISMAILIA Bridges |  | 8508050 | 5640588.7887
2015-12-12 | New Giza |  | 175794302.41 | 179017245.5327
2015-12-12 | ميناء السخنة |  | 34548331.29 | 21343147.8837
2015-12-12 | Maxim mall |  | 99573205 | 95089662.5306
2015-12-12 | Attaka |  | 155493789 | 99578013.6852
2015-12-12 | الفرنسية |  | 1641039.86 | 713685.6775
2015-12-12 | مول مصر |  | 158000000 | 146877848.8152
2015-12-12 | مراسى تانك الخزان الجديد PKG22 New |  | 16510059.28 | 15612624.567
2015-12-12 | نادي سوديك |  | 66635490 | 62669092
2015-12-12 | شرم الشيخ |  | 15492289.89 | 13982628
2015-12-12 | عمائر اب تاون 53 |  | 288918027 | 266252587.5225
2015-12-12 | New Giza phase 2 |  | 144891598 | 137108129
2015-12-12 | Beni suef |  | 422730662 | 378548686.1336
2015-12-12 | كوبرى الشيخ بن زايد - كوبرى العاصمة |  | 103000000 | 95465467
2015-12-12 | جبل الزيت - GAMISA |  | 116000000 | 105254776
2016-12-12 | Al Oula |  | 72000000 | 62666841.66
2016-12-12 | Hyper Al Sulaimaniya |  | 108788118.03 | 105490266.9349
2016-12-12 | New Giza I |  | 172181998.814 | 178018117.1846
2016-12-12 | Maxim mall |  | 95704579 | 92245938.56
2016-12-12 | Attaka |  | 184374873 | 97229131.4552
2016-12-12 | مول مصر |  | 171490065 | 142973982.8425
2016-12-12 | مراسى تانك الخزان الجديد PKG22 New |  | 16510059.28 | 16262187.567
2016-12-12 | نادي سوديك |  | 99588109 | 92629182.7436
2016-12-12 | شرم الشيخ |  | 33784495.5267 | 30160353.0632
2016-12-12 | عمائر اب تاون 53 |  | 270610661 | 264427222.0689
2016-12-12 | New Giza phase 2 |  | 144891598 | 140108129
2016-12-12 | Beni suef |  | 324195538 | 251025418.2023
2016-12-12 | كوبرى الشيخ بن زايد - كوبرى العاصمة |  | 98662660 | 72511483
2016-12-12 | جبل الزيت - GAMISA |  | 116000000 | 86100602.93
2016-12-12 | PKG62 |  | 40934935 | 41675578.9164
2016-12-12 | محطه كهرباء المستثمرين بالقطامي |  | 130103216 | 109630210.621
2016-12-12 | لوك اند لوت كوبرى الغرابلى - الاس |  | 3896945 | 3159874
2016-12-12 | سور لوك اند لود ( اوراسكوم) |  | 4817500 | 3295000
2016-12-12 | مشروع الكيان |  | 415155664.53 | 385768894.0459
2016-12-12 | مشروع الامل |  | 30857015 | 26620877.6125
2016-12-12 | مشروع مصنع الاسمنت |  | 206723720 | 187827866.3247
2016-12-12 | سور نيو جيزة |  | 2517009 | 2320307
2016-12-12 | Tamay Elamdeed substation (Alestom ) |  | 95970234.5006 | 90342516.8054
2016-12-12 | Wind Farm KFW |  | 20229094.48 | 16723936.9007
2016-12-12 | Wind Farm FIEM |  | 63390614 | 51386363.568
2017-12-12 | Al Oula |  | 72946445.96 | 66087308.6012
2017-12-12 | Hyper Al Sulaimaniya |  | 110450184.62 | 108679008.9749
2017-12-12 | New Giza I |  | 172216796.0405 | 173672666.3248
2017-12-12 | Maxim mall |  | 95704579 | 97884701.4913
2017-12-12 | Attaka |  | 184387980.81 | 97786625.9352
2017-12-12 | مول مصر |  | 166000000 | 139531961.2457
2017-12-12 | مراسى تانك الخزان الجديد PKG22 New |  | 17510059.28 | 17215605.8728
2017-12-12 | نادي سوديك |  | 148488134 | 149161589
2017-12-12 | شرم الشيخ |  | 33784495.5267 | 30373982.7996
2017-12-12 | عمائر اب تاون 53 |  | 308751426 | 316334066
2017-12-12 | New Giza phase 2 |  | 153841650 | 151759218
2017-12-12 | Beni suef |  | 432591184 | 319810885
2017-12-12 | كوبرى الشيخ بن زايد - كوبرى العاصمة |  | 93729526.98 | 71382872.0783
2017-12-12 | جبل الزيت - GAMISA |  | 120340462.76 | 79827798.99
2017-12-12 | PKG62 |  | 44392025 | 41977835
2017-12-12 | محطه كهرباء المستثمرين بالقطامي |  | 129792183 | 86447848
2017-12-12 | لوك اند لوت كوبرى الغرابلى - الاس |  | 2983560 | 3161393.34
2017-12-12 | سور لوك اند لود ( اوراسكوم) |  | 4776406 | 2477865.32
2017-12-12 | مشروع الكيان |  | 1124609030 | 1051496911
2017-12-12 | مشروع الامل |  | 28943151 | 19602893.42
2017-12-12 | مشروع مصنع الاسمنت |  | 269134670 | 247103063
2017-12-12 | سور نيو جيزة |  | 2648340.9749 | 1057277.26
2017-12-12 | Tamay Elamdeed substation (Alestom ) |  | 108790091 | 95540051
2017-12-12 | Wind Farm KFW |  | 23001621.88 | 13075726.34
2017-12-12 | Wind Farm FIEM |  | 71547614 | 42395913
2017-12-12 | PkG 107 |  | 54101395 | 43802147
2017-12-12 | كباري الأسماعيلية |  | 55077947 | 43375407.3857
2017-12-12 | نفق العاصمة |  | 412854534 | 318244664
2017-12-12 | Bani Sweif substation (Alestom ) |  | 108790091 | 96896266
2017-12-12 | Ismalia substation (Alestom ) |  | 108790091 | 94914373
2017-12-12 | مبنى وزارات الجيش |  | 428626339 | 394130704
2017-12-12 | رويال سيتى |  | 409523809.836 | 381327168.1479
2017-12-12 | كوبرى شبرا بنها |  | 2800000 | 2520000
2017-12-12 | كوبري الأمل لوك لود |  | 9050320 | 6335224
2017-12-12 | Hyper ismalia |  | 51838240 | 47721580.5944
2017-12-12 | P.I.PARKS - SLP |  | 32000000 | 31612131.219
2017-12-12 | Rolling Mills |  | 264370000 | 150482575
2017-12-12 | Siemens |  | 311000000 | 295519635
2017-12-12 | PKG 117 |  | 39336927 | 36189973
2017-12-12 | Kayan Lock Load |  | 107782440 | 82991132
2018-12-12 | Al Oula |  | 72946445.96 | 66087308.6012
2018-12-12 | Hyper Al Sulaimaniya |  | 110450184.62 | 108679008.9749
2018-12-12 | New Giza I |  | 172216796.0405 | 173716038.3248
2018-12-12 | Maxim mall |  | 98576600 | 104888994.0403
2018-12-12 | Attaka |  | 184387980.81 | 97786625.9352
2018-12-12 | مول مصر |  | 183459815.63 | 165227581.2857
2018-12-12 | مراسى تانك الخزان الجديد PKG22 New |  | 17510059.28 | 17383240.3578
2018-12-12 | نادي سوديك |  | 156847858 | 152585452
2018-12-12 | شرم الشيخ |  | 33784495.5267 | 30373982.7996
2018-12-12 | عمائر اب تاون 53 |  | 314968838 | 340241169
2018-12-12 | New Giza phase 2 |  | 154600508 | 160062056.3836
2018-12-12 | Beni suef |  | 427594086.74 | 319973217.7839
2018-12-12 | كوبرى الشيخ بن زايد - كوبرى العاصمة |  | 93729526.98 | 71382872.0783
2018-12-12 | جبل الزيت - GAMISA |  | 120483319.9 | 82164809.214
2018-12-12 | PKG62 |  | 47319156 | 52574895.421
2018-12-12 | محطه كهرباء المستثمرين بالقطامي |  | 129792183 | 85209855.07
2018-12-12 | لوك اند لوت كوبرى الغرابلى - الاس |  | 2983560 | 3161393.34
2018-12-12 | سور لوك اند لود ( اوراسكوم) |  | 4776406 | 2477865.32
2018-12-12 | مشروع الكيان |  | 1174132718 | 1112586148
2018-12-12 | مشروع الامل |  | 28943151 | 21210869.997
2018-12-12 | مشروع مصنع الاسمنت |  | 275632132 | 259287399.009
2018-12-12 | سور نيو جيزة |  | 2648340.9749 | 1057277.26
2018-12-12 | Tamay Elamdeed substation (Alestom ) |  | 108790091 | 99024505
2018-12-12 | Wind Farm KFW |  | 23038288.54 | 13129303.501
2018-12-12 | Wind Farm FIEM |  | 72547889 | 43182355.317
2018-12-12 | PkG 107 |  | 53707553 | 41367355.483
2018-12-12 | كباري الأسماعيلية |  | 56527617 | 33948207.928
2018-12-12 | نفق العاصمة |  | 344545654 | 263867080
2018-12-12 | Bani Sweif substation (Alestom ) |  | 111800446 | 101027337
2018-12-12 | Ismalia substation (Alestom ) |  | 108790091 | 99231624
2018-12-12 | مبنى وزارات الجيش |  | 735147064 | 649537426
2018-12-12 | رويال سيتى |  | 409523809.836 | 381327168.1479
2018-12-12 | كوبرى شبرا بنها |  | 2943356 | 1175416.75
2018-12-12 | كوبري الأمل لوك لود |  | 9050320 | 5980925
2018-12-12 | Hyper ismalia |  | 185531873 | 170819279.5
2018-12-12 | P.I.PARKS - SLP |  | 97023156 | 85200084
2018-12-12 | Rolling Mills |  | 351370000 | 213567813
2018-12-12 | Siemens |  | 331000000 | 304104567
2018-12-12 | PKG 117 |  | 41985689 | 30101708
2018-12-12 | Kayan Lock Load |  | 107782440 | 82991132
2018-12-12 | Sokhna Tunnel |  | 46639513 | 38194835.6
2018-12-12 | Abu Sultan Bridge |  | 18752986 | 13705180.686
2018-12-12 | Mientra |  | 110237621 | 100904012
2018-12-12 | Al Jazi Mall |  | 212502100 | 194848891.049
2018-12-12 | Nefisha Bridge |  | 57413676 | 50899028
2018-12-12 | Mohammed Ali Palace |  | 51936384.3429 | 36097261
2018-12-12 | Fish Market |  | 76548751 | 72943610.9
2018-12-12 | Benban Solar Power |  | 201152000 | 142943053
2018-12-12 | Alamein |  | 28594000 | 22585376
2018-12-12 | R05 - Zone 1 |  | 943050990 | 868890600
2018-12-12 | R05 - Zone 2 |  | 400057672 | 353629976
2018-12-12 | R05 - Zone 3 |  | 594816338 | 515475161
2018-12-12 | Sokhna Tunnel 2 |  | 20219635 | 16046395.8
2018-12-12 | Abu Sultan Bridge 2 |  | 64301760 | 55874977
2018-12-12 | El Sewedy University |  | 245658572 | 232124083
2018-12-12 | Substation Elco Steel |  | 33235261 | 30756410
2018-12-12 | PKG 101 |  | 27692512 | 24530229
2018-12-12 | PKG 144 |  | 78095238 | 69377455
2018-12-12 | Port of Sokhna |  | 1610425545 | 1472155701
2018-12-12 | EDNC Offices & Retail Project |  | 1000494581 | 946905944
2018-12-12 | Mostakbal Lock Load |  | 4424558 | 2062745
2018-12-12 | 30 June Tunnel Lock load |  | 1683412 | 541888
2018-12-12 | Middle Tunnel Lock Load |  | 1534748 | 602067
2019-12-12 | نادي سوديك | 0032 | 161208266 | 161637668
2019-12-12 | عمائر اب تاون 53 | EMAR/SIER/1354 | 314789511 | 344222187.4669
2019-12-12 | مشروع الكيان | ARMY/KYAN/1446 | 1335232523 | 1277814437
2019-12-12 | Tamay Elamdeed substation (Alestom ) | 0051 | 114399640 | 97853851
2019-12-12 | نفق العاصمة | 0059 | 344545654 | 271212136.105
2019-12-12 | Bani Sweif substation (Alestom ) | 0061 | 120712211 | 101105076
2019-12-12 | Ismalia substation (Alestom ) | 0052 | 109399640 | 100062903
2019-12-12 | مبنى وزارات الجيش | 0060 | 2740570200 | 2575535488
2019-12-12 | رويال سيتى | 0063 | 504962612 | 477120515
2019-12-12 | كوبري الأمل لوك لود | 0053 | 8184472.88 | 5824614.895
2019-12-12 | Hyper ismalia | 0070 | 171725231 | 138351333.4
2019-12-12 | P.I.PARKS - SLP | 0065 | 98230405.15 | 85595093
2019-12-12 | Rolling Mills | 0069 | 426637165 | 293568988
2019-12-12 | Siemens | 0072 | 332856409 | 335260498
2019-12-12 | PKG 117 | 0071 | 45205818.26 | 31111755
2019-12-12 | Kayan Lock Load | 0082 | 89838640 | 68024197
2019-12-12 | Sokhna Tunnel | 0074 | 46639513 | 37675287.964
2019-12-12 | Mientra | 0076 | 111043092.79 | 113258437
2019-12-12 | Al Jazi Mall | 0081 | 241102529 | 221422916
2019-12-12 | Nefisha Bridge | 0079 | 70928098 | 51420131
2019-12-12 | Mohammed Ali Palace | 0078 | 90260500 | 74301387
2019-12-12 | Fish Market | 0080 | 67664157 | 60753080.3
2019-12-12 | Benban Solar Power | 0083 | 212005783.75 | 118641100.203
2019-12-12 | Alamein | 0084 | 54192857 | 46001919
2019-12-12 | R05 - Zone 1 | 0082 | 1428771204 | 1313077291
2019-12-12 | R05 - Zone 2 | 0088 | 1947384057 | 1788866995
2019-12-12 | R05 - Zone 3 |  | 594816338 | 515475161
2019-12-12 | Sokhna Tunnel 2 | 0090 | 22334150 | 17647987.418
2019-12-12 | Abu Sultan Bridge 2 | 0089 | 78713414 | 69130205.538
2019-12-12 | El Sewedy University | 0085 | 262378822 | 223557346
2019-12-12 | Substation Elco Steel | 0096 | 32287263 | 34798197
2019-12-12 | PKG 101 | 0095 | 40371611 | 35563291
2019-12-12 | PKG 144 | 0093 | 173031232 | 114847455
2019-12-12 | Port of Sokhna | 0094 | 1557966434 | 1345287964
2019-12-12 | EDNC Offices & Retail Project | 0092 | 1039200141 | 983489361
2019-12-12 | مشروع الامل | 0046 | 31793876 | 21432678.776
2019-12-12 | مشروع مصنع الاسمنت | CDRI/BSCC/1445 | 274663700 | 265512440.135
2019-12-12 | Olympic Multi Sports Hall | 0099 | 1000000000 | 933950000
2019-12-12 | PKG 140 Mivida | 0098 | 168347427 | 154145627
2019-12-12 | EGAT Elco Steel | 0102 | 65831906 | 56811131
2019-12-12 | Pyramid Tunnel | 0101 | 317540750 | 280541761
2019-12-12 | Abo Ghazala Lock & Load | 0103 | 1688453 | 1511718.5
2019-12-12 | Mohamed Aly Fahmy Lock & Load |  | 7149700 | 6713205
2019-12-12 | محطه كهرباء المستثمرين بالقطامي | 0040 | 135792183 | 85741917.656
2019-12-12 | كوبرى شبرا بنها | 0064 | 3865380 | 1461114.75
2019-12-12 | El Mosheir Lock Load | 0105 | 4203687 | 2001684
2019-12-12 | PKG 107 | EMAR/IPWT/1459 | 54777143 | 42810448.983
2019-12-12 | Emergency Bridge | 0100 | 80000000 | 72001553
2019-12-12 | Bouble Tree Mangrouvy | 0107 | 51904762 | 48264559
2019-12-12 | Safeer Square Bridge | 0109 | 95436549 | 82927091
2019-12-12 | Suez Road Tunnel |  | 4423592 | 4769908.5
2019-12-12 | Mostafa Kamel Lock Load |  | 3000000 | 2725000
2019-12-12 | Baron Palace |  | 13000000 | 11674000
2019-12-12 | Ikea Retail | 0112 | 54289869 | 50715599
2019-12-12 | HyperOne Zayed | 0111 | 135000000 | 113943108
2019-12-12 | CFC Podium 2 | 0113 | 586475831 | 514705851
2019-12-12 | MR3 | 0118 | 1520085 | 1367204.3
2019-12-12 | El Sewedy University phase II | 0119 | 99675634 | 91382011
2019-12-12 | ORA Zed |  | 1100000 | 800000
2019-12-12 | Mehwar El Salam |  | 16843027 | 15775882.8
2019-12-12 | El Hegaz Square | 0121 | 138370050 | 121772563
2020-10-13 | نادي سوديك | 0032 | 161315477 | 169537179.4745
2020-10-13 | مشروع الكيان | ARMY/KYAN/1446 | 1335232523 | 1306314436.593
2020-10-13 | Tamay Elamdeed substation (Alestom ) | 0051 | 114399640 | 92853851.3
2020-10-13 | Bani Sweif substation (Alestom ) | 0061 | 120712211 | 100615455.89
2020-10-13 | Ismalia substation (Alestom ) | 0052 | 109399640 | 94574974.6595
2020-10-13 | مبنى وزارات الجيش | 0060 | 2740570200 | 2663137373.0012
2020-10-13 | رويال سيتى | 0063 | 527037820 | 502741033.2292
2020-10-13 | Hyper ismalia | 0070 | 168976040.9524 | 141672524.9015
2020-10-13 | P.I.PARKS - SLP | 0065 | 98230405 | 86259669.128
2020-10-13 | Rolling Mills | 0069 | 417390514 | 292181074.4464
2020-10-13 | Siemens | 0072 | 332856409 | 319846012.345
2020-10-13 | PKG 117 | 0071 | 46843954 | 31356816.307
2020-10-13 | Kayan Lock Load | 0068 | 89838640 | 68267669.843
2020-10-13 | Mientra | 0076 | 112045826 | 113125840.857
2020-10-13 | Al Jazi Mall | 0081 | 245977347.1316 | 228488395.4632
2020-10-13 | Mohammed Ali Palace | 0078 | 150000000 | 125642410.0235
2020-10-13 | Fish Market | 0080 | 66185668.5714 | 58052020.6193
2020-10-13 | Alamein | 0084 | 55041740 | 42062144.867
2020-10-13 | R05 - Zone 2 | 0088 | 3200000000 | 2976000000
2020-10-13 | El Sewedy University | 0085 | 262665630 | 232988357.458
2020-10-13 | Substation Elco Steel | 0096 | 32341773 | 34798196.7776
2020-10-13 | PKG 101 | 0095 | 52028085.7143 | 47340355.1914
2020-10-13 | PKG 144 | 0093 | 176262075.98 | 121991101.7935
2020-10-13 | Port of Sokhna | 0094 | 1633315425 | 1246507144.6956
2020-10-13 | EDNC Offices & Retail Project | 0092 | 1074545067 | 1010072362.98
2020-10-13 | Olympic Multi Sports Hall | 0099 | 1200000000 | 1140000000
2020-10-13 | PKG 140 Mivida | 0098 | 147581294.7 | 120912795.7184
2020-10-13 | Pyramid Tunnel | 0101 | 0 | 0
2020-10-13 | Abo Ghazala Lock & Load | 0103 | 2200000 | 1126200.65
2020-10-13 | Mohamed Aly Fahmy Lock & Load | 0104 | 6646200 | 4190366.63
2020-10-13 | Bouble Tree Mangrouvy | 0107 | 47364429.7979 | 44522564.01
2020-10-13 | Safeer Square Bridge | 0109 | 95036407 | 86001212.7976
2020-10-13 | Suez Road Tunnel | 0110 | 6984390 | 4248211.07
2020-10-13 | Baron Palace | 0108 | 16220552 | 14434567.4488
2020-10-13 | Ikea Retail | 0112 | 191876596 | 208979654.779
2020-10-13 | HyperOne Zayed | 0111 | 133583770 | 99106552.4453
2020-10-13 | CFC Podium 2 | 0113 | 591898555 | 488703337.7932
2020-10-13 | MR3 | 0118 | 1778991 | 1450752.91
2020-10-13 | El Sewedy University phase II | 0119 | 627196198 | 539388730.28
2020-10-13 | ORA Zed | 0106 | 1042542 | 758212.27
2020-10-13 | Mehwar El Salam | 0120 | 19057080.9524 | 13403611.1284
2020-10-13 | El Hegaz Square | 0121 | 132083146 | 121523786.2432
2020-10-13 | New Giza phase 2 | NGZA/UNVI/1369 | 155643269.76 | 161564179.8036
2020-10-13 | Kayan Landscape | 0127 | 100042648 | 93060671.3161
2020-10-13 | Lekela | 0125 | 177657966 | 171792189
2020-10-13 | Ring Road | 0122 | 892629096 | 825661983
2020-10-13 | Marassi PKG# 162 | 0123 | 221768125 | 181354013
2020-10-13 | Abbas Akkad Bridge | 0128 | 121132580.9524 | 122869821.99
2020-10-13 | PKG 53 | EMAR/SIER/1354 | 316571124 | 345127714.8769
2020-10-13 | Sultana Malak | 0124 | 85000000 | 72250000
2020-10-13 | 10th of Ramadan Bridge | 0129 | 93910355 | 85732351.721
2020-10-13 | Kafr Shoukr Bridge | 0130 | 155000000 | 141050000
2020-10-13 | El Shourouk Bridge | 0131 | 26145782 | 24180000
2020-10-13 | PKG62 | Village E PKG#62 | 47817473 | 52574895.421
2020-10-13 | Cairo-Alex Railway | 0134 | 1376190476.1905 | 1195902854.4986
2020-10-13 | Hassan El Mamoun Bridge | 0135 | 91300000 | 83996000
2020-10-13 | ORA ZED - Ph 01B - Pkgs A&D | 0137 | 870293108 | 808937442.9565
2020-10-13 | GOV2 - Infra | 0133 | 650000000 | 607750000
2021-03-13 | Kattameya Creeks |  | 1462000000 | 1352350000
2021-03-13 | Diplomatic District - Infra |  | 390000000 | 364650000
2021-03-13 | ElSewedy HQ Internal Finishing |  | 327718153.3333 | 304777882.29
2021-03-13 | Sherouk Bridge- LOCK&LOAD |  | 1000000 | 850000
2021-03-13 | Bani Suef Old Substation |  | 430034944.12 | 321198676.8954
2021-03-13 | رويال سيتى | 0063 | 527037820 | 502741033.2292
2021-03-13 | Hyper ismalia | 0070 | 168976040.9524 | 141672524.9015
2021-03-13 | Al Jazi Mall | 0081 | 245977347.1316 | 228488395.4632
2021-03-13 | Mohammed Ali Palace | 0078 | 150000000 | 125642410.0235
2021-03-13 | Fish Market | 0080 | 66185668.5714 | 58052020.6193
2021-03-13 | R05 - Zone 2 | 0088 | 3200000000 | 2976000000
2021-03-13 | Substation Elco Steel | 0096 | 32341773 | 34798196.7776
2021-03-13 | PKG 101 | 0095 | 52028085.7143 | 47340355.1914
2021-03-13 | PKG 144 | 0093 | 176420357 | 122395420.14
2021-03-13 | Port of Sokhna | 0094 | 1633315425 | 1228038344.6956
2021-03-13 | EDNC Offices & Retail Project | 0092 | 1056951198 | 993534126.12
2021-03-13 | Olympic Multi Sports Hall | 0099 | 1200000000 | 1140000000
2021-03-13 | PKG 140 Mivida | 0098 | 170057475.6641 | 136045980.5313
2021-03-13 | Bouble Tree Mangrouvy | 0107 | 57898699.39 | 54424777.4266
2021-03-13 | Baron Palace | 0108 | 16220552 | 14434567.4488
2021-03-13 | Ikea Retail | 0112 | 196190620 | 212380869
2021-03-13 | HyperOne Zayed | 0111 | 133583770 | 99106552.4453
2021-03-13 | CFC Podium 2 | 0113 | 635000000 | 524290213.0394
2021-03-13 | El Sewedy University phase II | 0119 | 593999147 | 510839266
2021-03-13 | El Hegaz Square | 0121 | 132083146 | 121523786.2432
2021-03-13 | Kayan Landscape | 0127 | 100042648 | 93060671.3161
2021-03-13 | Lekela | 0125 | 182442342 | 178793495.16
2021-03-13 | Ring Road | 0122 | 703937495 | 651126465
2021-03-13 | Marassi PKG# 162 | 0123 | 434504076.4286 | 354989830.4421
2021-03-13 | Abbas Akkad Bridge | 0128 | 124132580.9524 | 122869821.99
2021-03-13 | Sultana Malak | 0124 | 85000000 | 72250000
2021-03-13 | 10th of Ramadan Bridge | 0129 | 93910355 | 85732351.721
2021-03-13 | Kafr Shoukr Bridge | 0130 | 155000000 | 141050000
2021-03-13 | El Shourouk Bridge | 0131 | 29476843 | 26823927.13
2021-03-13 | Cairo-Alex Railway | 0134 | 967000000 | 879970000
2021-03-13 | Hassan El Mamoun Bridge | 0135 | 93800000 | 88756688.976
2021-03-13 | ORA ZED - Ph 01B - Pkgs A&D | 0137 | 870293108 | 808937442.9565
2021-03-13 | GOV2 - Infra | 0133 | 650000000 | 607750000
2021-03-13 | Kattameya Creeks | 0138 | 1462000000 | 1352350000
2021-03-13 | Diplomatic District - Infra | 0140 | 390000000 | 364650000
2021-03-13 | ElSewedy HQ Internal Finishing | 0141 | 327718153.3333 | 302367726
2021-03-13 | Sherouk Bridge- LOCK&LOAD | 0136 | 1000000 | 1648128.4931
2021-03-13 | BKG#178-Lagoon Discharge | 0142 | 40449240 | 35085670.776
2021-03-13 | Faculty of Medicine | 0139 | 219047619.0476 | 203714285.7143
2021-03-13 | El Khatatba Bridge | 0143 | 142857142.8571 | 130000000
2021-03-13 | EGAT Pelletizing Plant | 0144 | 375000000 | 341250000
2021-03-13 | Sokhna Port Expansion | 0145 | 1100000000 | 1023000000
2021-03-13 | Waldorf Astoria Mock-up Room | 0146 | 0 | 0
2021-03-13 | MDF Factory | 0147 | 175000000 | 162750000

## filter location GM, RC (hidden)
Project | Revised | Estimate | Revised/Gross Value | N
Marassi Civic Center Pkg 45 | 56931016 | 64758247.2535 | Gross Margin | -7827231.2535
Al Oula Infra | 72946445.96 | 66087308.6012 | Gross Margin | 6859137.3588
New Giza Phase 01 | 172216796.0405 | 173716038.3248 | Gross Margin | -1499242.2843
Hyper Solimanya | 110450184.62 | 108679008.9749 | Gross Margin | 1771175.6451
Ismailia Bridges | 56527617 | 33948207.928 | Gross Margin | 22579409.072
Maxium Mall | 98576600 | 104888994.0403 | Gross Margin | -6312394.0403
Ataqqa Power Plant | 184387980.81 | 97786625.9352 | Gross Margin | 86601354.8748
Mall of Egypt Bridge | 183459815.63 | 165227581.2857 | Gross Margin | 18232234.3443
Marassi Tanks PKG 22 | 18438370 | 16655530.55 | Gross Margin | 1782839.45
Sodic Club House | 161208266 | 169537179.4745 | Gross Margin | -8328913.4745
Montazah Hotel Sharm | 33784495.5267 | 30373982.7996 | Gross Margin | 3410512.7271
Uptown Cairo Pkg 53 | 314789511 | 344222187 | Gross Margin | -29432676
Bani Suif Power Plant 1021 | 427594086.74 | 319973217.7839 | Gross Margin | 107620868.9561
New Giza Phase 02 | 155643269.76 | 161564179.8036 | Gross Margin | -5920910.0436
JICA Wind Farm Gabal El Zeet | 120483319.9 | 82164809.214 | Gross Margin | 38318510.686
El Mostathmereen Mokatam Substation | 135792183 | 85209855.07 | Gross Margin | 50582327.93
Levana UpTown PKG 62 | 47319156 | 52574895.421 | Gross Margin | -5255739.421
Kayan 110 | 1335232523 | 1306314436.593 | Gross Margin | 28918086.407
El Amal Bridge | 28943151 | 21210869.997 | Gross Margin | 7732281.003
Bani Suif Cement | 274663700 | 265512440.135 | Gross Margin | 9151259.865
New Giza Wall | 2648340.9749 | 1057277.26 | Gross Margin | 1591063.7149
Tamey El Amdid Mansora Power Station | 114399640 | 92853851.3 | Gross Margin | 21545788.7
Ismailia Substation 500-220 | 109399640 | 94574974.6595 | Gross Margin | 14824665.3405
El Amal Bridge L&L | 9050320 | 6335224 | Gross Margin | 2715096
FIEM Wind Farm Gabal El Zeet | 72547889 | 43182355.317 | Gross Margin | 29365533.683
KFW Wind Farm Gabal El Zeet | 23038288.54 | 13129303.501 | Gross Margin | 9908985.039
Marassi Tank PKG 107 | 54777143 | 42810448.983 | Gross Margin | 11966694.017
Ben Zayed New Capital Tunnel | 343357654.106 | 271212136.105 | Gross Margin | 72145518.001
Ministries Buildings | 2740570200 | 2663137373.0012 | Gross Margin | 77432826.9988
Bani Suif Substation | 120712211 | 101105076 | Gross Margin | 19607135
Royal City Mall | 527037820 | 502741033.2292 | Gross Margin | 24296786.7708
Shoubra Banha Bridge L&L | 3865380 | 1461115 | Gross Margin | 2404265
SLP Logistic Center PI Park Sewedy Stores | 98230405 | 86259669.128 | Gross Margin | 11970735.872
El Mostakbal Bridge L&L | 4424558 | 2062745 | Gross Margin | 2361813
Kayan Wall L&L | 107782440 | 82991132 | Gross Margin | 24791308
Elco Suez Steel Rolling Mill Plant 3 | 417390514 | 292181074.4464 | Gross Margin | 125209439.5536
Hyper El Temsah | 168976040.9524 | 141672524.9015 | Gross Margin | 27303516.0509
Marassi Bridge Pkg 117 | 45205818 | 31111755 | Gross Margin | 14094063
Siemens Power Station | 332856409 | 319846012.345 | Gross Margin | 13010396.655
Uptown FM85 Pkg 85 |  |  | Gross Margin | 0
El Sokhna Tunnel 01 | 46639513 | 37675288 | Gross Margin | 8964225
Abu Sultan Bridge 01 | 18752986 | 13705181 | Gross Margin | 5047805
Mintra Factory | 112045826 | 113125840.857 | Gross Margin | -1080014.857
King Farouk Restoration |  |  | Gross Margin | 0
Mohamed Ali Palace | 150000000 | 125642410.0235 | Gross Margin | 24357589.9765
Nefisha Bridge | 70928098 | 51420131 | Gross Margin | 19507967
Fish Market | 66185668.5714 | 58052020.6193 | Gross Margin | 8133647.9521
Al Jazi Mall | 245977347.1316 | 228488395.4632 | Gross Margin | 17488951.6684
Benban Aswan Alcazars Solar Park | 212005784 | 118641100 | Gross Margin | 93364684
El Alameen Roads Earth Works | 54192857 | 46001919 | Gross Margin | 8190938
El Sewedy Univeristy | 262378822 | 232988357.458 | Gross Margin | 29390464.542
El Sokhna Tunnel L&L |  |  | Gross Margin | 0
R05 Residential District Z1 & Z2 | 3200000000 | 2976000000 | Gross Margin | 224000000
Abu Sultan Bridge 02 Greenhouse | 67755600 | 59506484.6859 | Gross Margin | 8249115.3141
El Sokhna Tunnel 02 | 22334150 | 17647987 | Gross Margin | 4686163
El Awsty Middle Tunnel L&L | 1024820 |  | Gross Margin | 1024820
Sodic Eastown EDNC | 1074545067 | 1010072362.98 | Gross Margin | 64472704.02
Marassi Civic Center Pkg 144 | 176420375 | 122239319.38 | Gross Margin | 54181055.62
DPW Sokhna Dubai Port | 1633315425 | 1246507144.6956 | Gross Margin | 386808280.3044
Slope Stablization PKG 101 | 52028085.7143 | 47340355.1914 | Gross Margin | 4687730.5229
Elco Steel Substation | 32341773 | 34798196.7776 | Gross Margin | -2456423.7776
Sewab Greenhouse Tunnel | 10957813.825 | 9623720.8521 | Gross Margin | 1334092.9729
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 | 136045980.5313 | Gross Margin | 34011495.1328
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 | 136045980.5313 | Gross Margin | 34011495.1328
Multi Sports Hall | 1200000000 | 1140000000 | Gross Margin | 60000000
EGAT | 65831906 | 56811131 | Gross Margin | 9020775
Abou Ghazala Bridge Ramp L&L | 1688453 | 1511719 | Gross Margin | 176734
Mohamed Ali Fahmy Ramps L&L | 7149700 | 6713205 | Gross Margin | 436495
El Mosheer Bridge Abu Zaied Khdr L&L | 4203687 | 2001684 | Gross Margin | 2202003
Ora Zed Park L&L | 1042542 | 758212.27 | Gross Margin | 284329.73
DoubleTree Mangroovy El Gouna Hotel | 57898699.39 | 54424777.4266 | Gross Margin | 3473921.9634
Baron Palace Fence | 16220552 | 14434567.4488 | Gross Margin | 1785984.5512
Safeer Square Bridge | 95436549 | 82927091 | Gross Margin | 12509458
Suez Road Tunnel Res L&L | 4423592 | 4769909 | Gross Margin | -346317
HyperOne Zayed Extention | 133583770 | 99106552.4453 | Gross Margin | 34477217.5547
IKEA Extention MoA | 196190620 | 212380869 | Gross Margin | -16190249
CFC Podium II | 635000000 | 524290213.0394 | Gross Margin | 110709786.9606
Mostafa Kamel Bridge L&L |  |  | Gross Margin | 0
Josef Tito Bridge L&L |  |  | Gross Margin | 0
Espiko Bridge L&L |  |  | Gross Margin | 0
El Gabal El Asfr Tunnel L&L |  |  | Gross Margin | 0
MR3 Bridge L&L | 1520085 | 1367204 | Gross Margin | 152881
El Sewedy Univeristy 2 Phase 2 | 593999147 | 510839266 | Gross Margin | 83159881
Mehwar El Salam Axis L&L | 16843027 | 15775883 | Gross Margin | 1067144
El Hegaz Square Bridge | 138370050 | 121772563 | Gross Margin | 16597487
Ring Road Extension | 384527145 | 371951236 | Gross Margin | 12575909
Marina Inland Marassi Pkg 162 | 434504076.4286 | 354989830.4421 | Gross Margin | 79514245.9864
Sultana Malek Restoration | 85000000 | 72250000 | Gross Margin | 12750000
Lekela 250MW Wind Farm | 182442342 | 178793495.16 | Gross Margin | 3648846.84
New Giza Hospital | 542690000 | 507186915.8879 | Gross Margin | 35503084.1121
Kayan Landscape | 100042648 | 93060671.3161 | Gross Margin | 6981976.6839
Abbas Akkad Bridge | 124132580.9524 | 122869821.99 | Gross Margin | 1262758.9624
El Asher Men Ramadan Bridge | 93910355 | 85732351.721 | Gross Margin | 8178003.279
Kafr Shokr Bridge | 147845325 | 133974586 | Gross Margin | 13870739
Al Shorouk Bridge (LRT) | 26145782 | 24180000 | Gross Margin | 1965782
Ring Road El Marg | 157658129 | 152523872 | Gross Margin | 5134257
GOV2 Infra | 650000000 | 607750000 | Gross Margin | 42250000
Cairo Alex Railroad | 967000000 | 879970000 | Gross Margin | 87030000
Hassan El Mamoun Bridge | 93800000 | 88756688.976 | Gross Margin | 5043311.024
Sherouk Bridge L&L | 1000000 | 1648128.4931 | Gross Margin | -648128.4931
Ora Zed Park 1B Pkgs A&D | 870293108 | 808937442.9565 | Gross Margin | 61355665.0435
Kattameya Creeks | 1462000000 | 1352350000 | Gross Margin | 109650000
Mansoura University Faculty of Medicine | 219047619.0476 | 203714285.7143 | Gross Margin | 15333333.3333
Diplomatic District - Infra | 390000000 | 364650000 | Gross Margin | 25350000
El Sewedy CFC HQ Internal Finishing | 327718153.3333 | 302367726 | Gross Margin | 25350427.3333
Lagoon Discharge Pkg 178 | 40449240 | 35085670.776 | Gross Margin | 5363569.224
El Khatatba Bridge | 142857142.8571 | 130845321 | Gross Margin | 12011821.8571
EGAT Pelletizing Plant | 375000000 | 341250000 | Gross Margin | 33750000
Sokhna Port Expansion | 1100000000 | 1023000000 | Gross Margin | 77000000
MDF Factory | 175000000 | 162750000 | Gross Margin | 12250000
Olympic City L&L |  |  | Gross Margin | 0
Kemet Building | 71052428.57 | 66078758.5701 | Gross Margin | 4973669.9999
Point 90 New Cairo Mall | 145010925.68 | 129215876.9678 | Gross Margin | 15795048.7122
Marassi Bridges Pkg 37 | 26193836.68 | 27330602.3975 | Gross Margin | -1136765.7175
Marassi Golf Maintance Building Pkg 58 | 4720405.25 | 5275181.8987 | Gross Margin | -554776.6487
Uptown Soil Stabilization Pkg 32 | 17421145.8 | 21051883.5147 | Gross Margin | -3630737.7147
Ismailia Bridge L&L | 49485210.2 |  | Gross Margin | 49485210.2
El Obour Bridge B2 | 9000000 | 7200000 | Gross Margin | 1800000
Autoville Strip Mall | 51072634 | 55255998 | Gross Margin | -4183364
Uptown Service Buildings Pkg 17A | 55905931 | 53843629.5863 | Gross Margin | 2062301.4137
Sodic West Town Hub | 54160920.41 | 56137642.32 | Gross Margin | -1976721.91
Dubai Port Sokhna Basin 1 | 34548331.29 | 27990071.4837 | Gross Margin | 6558259.8063
Alexandria Bridges | 35589876.5 | 28766462 | Gross Margin | 6823414.5
El Mahala Bridge | 67245402 | 48126832 | Gross Margin | 19118570
El Wahat Bridge | 22540933.0883 | 18032746.4706 | Gross Margin | 4508186.6177
El Wahat Tunnel | 18818015.28 | 13923981.6424 | Gross Margin | 4894033.6376
AL-Asmarat | 6636851 | 8517150.2182 | Gross Margin | -1880299.2182
Alegria DP Port | 605714038 | 498059352 | Gross Margin | 107654686
El Alameen Bridge L&L |  |  | Gross Margin | 0
El Asher of Ramadan Bridge L&L |  |  | Gross Margin | 0
EMEC | 10688481.1 | 8907067.5833 | Gross Margin | 1781413.5167
Ismailia Bridge L&L |  |  | Gross Margin | 0
Logestica Phase 01 | 31905026.19 | 27743501.0348 | Gross Margin | 4161525.1552
Logestica Phase 02 | 20681422 | 16069494.51 | Gross Margin | 4611927.49
Logestica Phase 03 | 4820461 | 3681383 | Gross Margin | 1139078
Sodic MV Cables | 19589518 | 16384636.8472 | Gross Margin | 3204881.1528
Limak TB2 Cairo Airport Terminal | 119626844 | 96755558 | Gross Margin | 22871286
Twin Towers | 64000000.23 | 63714421.967 | Gross Margin | 285578.263
Aeon Towers Chiller Building |  |  | Gross Margin | 0
Electric Train LRT |  |  | Gross Margin | 0
Sea Shell Playa |  |  | Gross Margin | 0
Marassi Civic Center Pkg 45 | 56931016 |  | Revised Contract | 0
Al Oula Infra | 72946445.96 |  | Revised Contract | 0
New Giza Phase 01 | 172216796.0405 |  | Revised Contract | 0
Hyper Solimanya | 110450184.62 |  | Revised Contract | 0
Ismailia Bridges | 56527617 |  | Revised Contract | 0
Maxium Mall | 98576600 |  | Revised Contract | 0
Ataqqa Power Plant | 184387980.81 |  | Revised Contract | 0
Mall of Egypt Bridge | 183459815.63 |  | Revised Contract | 0
Marassi Tanks PKG 22 | 18438370 |  | Revised Contract | 0
Sodic Club House | 161208266 |  | Revised Contract | 0
Montazah Hotel Sharm | 33784495.5267 |  | Revised Contract | 0
Uptown Cairo Pkg 53 | 314789511 |  | Revised Contract | 0
Bani Suif Power Plant 1021 | 427594086.74 |  | Revised Contract | 0
New Giza Phase 02 | 155643269.76 |  | Revised Contract | 0
JICA Wind Farm Gabal El Zeet | 120483319.9 |  | Revised Contract | 0
El Mostathmereen Mokatam Substation | 135792183 |  | Revised Contract | 0
Levana UpTown PKG 62 | 47319156 |  | Revised Contract | 0
Kayan 110 | 1335232523 |  | Revised Contract | 0
El Amal Bridge | 28943151 |  | Revised Contract | 0
Bani Suif Cement | 274663700 |  | Revised Contract | 0
New Giza Wall | 2648340.9749 |  | Revised Contract | 0
Tamey El Amdid Mansora Power Station | 114399640 |  | Revised Contract | 0
Ismailia Substation 500-220 | 109399640 |  | Revised Contract | 0
El Amal Bridge L&L | 9050320 |  | Revised Contract | 0
FIEM Wind Farm Gabal El Zeet | 72547889 |  | Revised Contract | 0
KFW Wind Farm Gabal El Zeet | 23038288.54 |  | Revised Contract | 0
Marassi Tank PKG 107 | 54777143 |  | Revised Contract | 0
Ben Zayed New Capital Tunnel | 343357654.106 |  | Revised Contract | 0
Ministries Buildings | 2740570200 |  | Revised Contract | 0
Bani Suif Substation | 120712211 |  | Revised Contract | 0
Royal City Mall | 527037820 |  | Revised Contract | 0
Shoubra Banha Bridge L&L | 3865380 |  | Revised Contract | 0
SLP Logistic Center PI Park Sewedy Stores | 98230405 |  | Revised Contract | 0
El Mostakbal Bridge L&L | 4424558 |  | Revised Contract | 0
Kayan Wall L&L | 107782440 |  | Revised Contract | 0
Elco Suez Steel Rolling Mill Plant 3 | 417390514 |  | Revised Contract | 0
Hyper El Temsah | 168976040.9524 |  | Revised Contract | 0
Marassi Bridge Pkg 117 | 45205818 |  | Revised Contract | 0
Siemens Power Station | 332856409 |  | Revised Contract | 0
Uptown FM85 Pkg 85 |  |  | Revised Contract | 0
El Sokhna Tunnel 01 | 46639513 |  | Revised Contract | 0
Abu Sultan Bridge 01 | 18752986 |  | Revised Contract | 0
Mintra Factory | 112045826 |  | Revised Contract | 0
King Farouk Restoration |  |  | Revised Contract | 0
Mohamed Ali Palace | 150000000 |  | Revised Contract | 0
Nefisha Bridge | 70928098 |  | Revised Contract | 0
Fish Market | 66185668.5714 |  | Revised Contract | 0
Al Jazi Mall | 245977347.1316 |  | Revised Contract | 0
Benban Aswan Alcazars Solar Park | 212005784 |  | Revised Contract | 0
El Alameen Roads Earth Works | 54192857 |  | Revised Contract | 0
El Sewedy Univeristy | 262378822 |  | Revised Contract | 0
El Sokhna Tunnel L&L |  |  | Revised Contract | 0
R05 Residential District Z1 & Z2 | 3200000000 |  | Revised Contract | 0
Abu Sultan Bridge 02 Greenhouse | 67755600 |  | Revised Contract | 0
El Sokhna Tunnel 02 | 22334150 |  | Revised Contract | 0
El Awsty Middle Tunnel L&L | 1024820 |  | Revised Contract | 0
Sodic Eastown EDNC | 1074545067 |  | Revised Contract | 0
Marassi Civic Center Pkg 144 | 176420375 |  | Revised Contract | 0
DPW Sokhna Dubai Port | 1633315425 |  | Revised Contract | 0
Slope Stablization PKG 101 | 52028085.7143 |  | Revised Contract | 0
Elco Steel Substation | 32341773 |  | Revised Contract | 0
Sewab Greenhouse Tunnel | 10957813.825 |  | Revised Contract | 0
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 |  | Revised Contract | 0
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 |  | Revised Contract | 0
Multi Sports Hall | 1200000000 |  | Revised Contract | 0
EGAT | 65831906 |  | Revised Contract | 0
Abou Ghazala Bridge Ramp L&L | 1688453 |  | Revised Contract | 0
Mohamed Ali Fahmy Ramps L&L | 7149700 |  | Revised Contract | 0
El Mosheer Bridge Abu Zaied Khdr L&L | 4203687 |  | Revised Contract | 0
Ora Zed Park L&L | 1042542 |  | Revised Contract | 0
DoubleTree Mangroovy El Gouna Hotel | 57898699.39 |  | Revised Contract | 0
Baron Palace Fence | 16220552 |  | Revised Contract | 0
Safeer Square Bridge | 95436549 |  | Revised Contract | 0
Suez Road Tunnel Res L&L | 4423592 |  | Revised Contract | 0
HyperOne Zayed Extention | 133583770 |  | Revised Contract | 0
IKEA Extention MoA | 196190620 |  | Revised Contract | 0
CFC Podium II | 635000000 |  | Revised Contract | 0
Mostafa Kamel Bridge L&L |  |  | Revised Contract | 0
Josef Tito Bridge L&L |  |  | Revised Contract | 0
Espiko Bridge L&L |  |  | Revised Contract | 0
El Gabal El Asfr Tunnel L&L |  |  | Revised Contract | 0
MR3 Bridge L&L | 1520085 |  | Revised Contract | 0
El Sewedy Univeristy 2 Phase 2 | 593999147 |  | Revised Contract | 0
Mehwar El Salam Axis L&L | 16843027 |  | Revised Contract | 0
El Hegaz Square Bridge | 138370050 |  | Revised Contract | 0
Ring Road Extension | 384527145 |  | Revised Contract | 0
Marina Inland Marassi Pkg 162 | 434504076.4286 |  | Revised Contract | 0
Sultana Malek Restoration | 85000000 |  | Revised Contract | 0
Lekela 250MW Wind Farm | 182442342 |  | Revised Contract | 0
New Giza Hospital | 542690000 |  | Revised Contract | 0
Kayan Landscape | 100042648 |  | Revised Contract | 0
Abbas Akkad Bridge | 124132580.9524 |  | Revised Contract | 0
El Asher Men Ramadan Bridge | 93910355 |  | Revised Contract | 0
Kafr Shokr Bridge | 147845325 |  | Revised Contract | 0
Al Shorouk Bridge (LRT) | 26145782 |  | Revised Contract | 0
Ring Road El Marg | 157658129 |  | Revised Contract | 0
GOV2 Infra | 650000000 |  | Revised Contract | 0
Cairo Alex Railroad | 967000000 |  | Revised Contract | 0
Hassan El Mamoun Bridge | 93800000 |  | Revised Contract | 0
Sherouk Bridge L&L | 1000000 |  | Revised Contract | 0
Ora Zed Park 1B Pkgs A&D | 870293108 |  | Revised Contract | 0
Kattameya Creeks | 1462000000 |  | Revised Contract | 0
Mansoura University Faculty of Medicine | 219047619.0476 |  | Revised Contract | 0
Diplomatic District - Infra | 390000000 |  | Revised Contract | 0
El Sewedy CFC HQ Internal Finishing | 327718153.3333 |  | Revised Contract | 0
Lagoon Discharge Pkg 178 | 40449240 |  | Revised Contract | 0
El Khatatba Bridge | 142857142.8571 |  | Revised Contract | 0
EGAT Pelletizing Plant | 375000000 |  | Revised Contract | 0
Sokhna Port Expansion | 1100000000 |  | Revised Contract | 0
MDF Factory | 175000000 |  | Revised Contract | 0
Olympic City L&L |  |  | Revised Contract | 0
Kemet Building | 71052428.57 |  | Revised Contract | 0
Point 90 New Cairo Mall | 145010925.68 |  | Revised Contract | 0
Marassi Bridges Pkg 37 | 26193836.68 |  | Revised Contract | 0
Marassi Golf Maintance Building Pkg 58 | 4720405.25 |  | Revised Contract | 0
Uptown Soil Stabilization Pkg 32 | 17421145.8 |  | Revised Contract | 0
Ismailia Bridge L&L | 49485210.2 |  | Revised Contract | 0
El Obour Bridge B2 | 9000000 |  | Revised Contract | 0
Autoville Strip Mall | 51072634 |  | Revised Contract | 0
Uptown Service Buildings Pkg 17A | 55905931 |  | Revised Contract | 0
Sodic West Town Hub | 54160920.41 |  | Revised Contract | 0
Dubai Port Sokhna Basin 1 | 34548331.29 |  | Revised Contract | 0
Alexandria Bridges | 35589876.5 |  | Revised Contract | 0
El Mahala Bridge | 67245402 |  | Revised Contract | 0
El Wahat Bridge | 22540933.0883 |  | Revised Contract | 0
El Wahat Tunnel | 18818015.28 |  | Revised Contract | 0
AL-Asmarat | 6636851 |  | Revised Contract | 0
Alegria DP Port | 605714038 |  | Revised Contract | 0
El Alameen Bridge L&L |  |  | Revised Contract | 0
El Asher of Ramadan Bridge L&L |  |  | Revised Contract | 0
EMEC | 10688481.1 |  | Revised Contract | 0
Ismailia Bridge L&L |  |  | Revised Contract | 0
Logestica Phase 01 | 31905026.19 |  | Revised Contract | 0
Logestica Phase 02 | 20681422 |  | Revised Contract | 0
Logestica Phase 03 | 4820461 |  | Revised Contract | 0
Sodic MV Cables | 19589518 |  | Revised Contract | 0
Limak TB2 Cairo Airport Terminal | 119626844 |  | Revised Contract | 0
Twin Towers | 64000000.23 |  | Revised Contract | 0
Aeon Towers Chiller Building |  |  | Revised Contract | 0
Electric Train LRT |  |  | Revised Contract | 0
Sea Shell Playa |  |  | Revised Contract | 0

## -ve cashflow
Project Name | Negative Cash Flow
Marassi Civic Center Pkg 45 | #REF!
Al Oula Infra | #REF!
New Giza Phase 01 | #REF!
Hyper Solimanya | #REF!
Ismailia Bridges | #REF!
Maxium Mall | #REF!
Ataqqa Power Plant | #REF!
Mall of Egypt Bridge | #REF!
Marassi Tanks PKG 22 | #REF!
Sodic Club House | #REF!
Uptown Cairo Pkg 53 | #REF!
Bani Suif Power Plant 1021 | #REF!
New Giza Phase 02 | #REF!
JICA Wind Farm Gabal El Zeet | #REF!
El Mostathmereen Mokatam Substation | #REF!
Levana UpTown Pkg 62 | #REF!
Kayan 110 | #REF!
El Amal Bridge | #REF!
Bani Suif Cement | #REF!
New Giza Wall | #REF!
Tamey El Amdid Mansora Power Station | #REF!
Ismailia Substation 500-220 | #REF!
El Amal Bridge L&L | #REF!
FIEM Wind Farm Gabal El Zeet | #REF!
KFW Wind Farm Gabal El Zeet | #REF!
Marassi Tank PKG 107 | #REF!
Ben Zayed New Capital Tunnel | #REF!
Ministries Buildings | #REF!
Bani Suif Substation | #REF!
Royal City Mall | #REF!
Shoubra Banha Bridge L&L | #REF!
SLP Logistic Center PI Park Sewedy Stores | #REF!
El Mostakbal Bridge L&L | #REF!
Kayan Wall L&L | #REF!
Elco Suez Steel Rolling Mill Plant 3 | #REF!
Hyper El Temsah | #REF!
Marassi Bridge Pkg 117 | #REF!
Siemens Power Station | #REF!
Uptown FM85 Pkg 85 | #REF!
El Sokhna Tunnel 01 | #REF!
Abu Sultan Bridge 01 | #REF!
Mintra Factory | #REF!
King Farouk Restoration | #REF!
Mohamed Ali Palace | #REF!
Nefisha Bridge | #REF!
Fish Market | #REF!
Al Jazi Mall | #REF!
Benban Aswan Alcazars Solar Park | #REF!
El Alameen Roads Earth Works | #REF!
El Sewedy Univeristy | #REF!
El Sokhna Tunnel L&L | #REF!
R05 Residential District Z1 & Z2 | #REF!
Abu Sultan Bridge 02 Greenhouse | #REF!
El Sokhna Tunnel 02 | #REF!
El Awsty Middle Tunnel L&L | #REF!
Sodic Eastown EDNC | #REF!
Marassi Civic Center Pkg 144 | #REF!
DPW Sokhna Dubai Port | #REF!
Slope Stablization PKG 101 | #REF!
Elco Steel Substation | #REF!
Sewab Greenhouse Tunnel | #REF!
Mivida Irrigation Treatment Plant Pkg 140 | #REF!
Multi Sports Hall | #REF!
Emergency Bridge | #REF!
Pyramid El Remayah Tunnel | #REF!
EGAT | #REF!
Abou Ghazala Bridge Ramp L&L | #REF!
Mohamed Ali Fahmy Ramps L&L | #REF!
El Mosheer Bridge Abu Zaied Khdr L&L | #REF!
Ora Zed Park L&L | #REF!
DoubleTree Mangroovy El Gouna Hotel | #REF!
Baron Palace Fence | #REF!
Safeer Square Bridge | #REF!
Suez Road Tunnel Res L&L | #REF!
HyperOne Zayed Extention | #REF!
IKEA Extention MoA | #REF!
CFC Podium II | #REF!
Josef Tito Bridge L&L | #REF!
Espiko Bridge L&L | #REF!
MR3 Bridge L&L | #REF!
El Sewedy Univeristy 2 Phase 2 | #REF!
Mehwar El Salam Axis L&L | #REF!
El Hegaz Square Bridge | #REF!
Ring Road 1 Maryotyah | #REF!
Marina Inland Marassi Pkg 162 | #REF!
Sultana Malek Restoration | #REF!
Lekela 250MW Wind Farm | #REF!
New Giza Hospital | #REF!
Kayan Landscape | #REF!
Abbas Akkad Bridge | #REF!
El Asher Men Ramadan Bridge | #REF!
Kafr Shokr Bridge | #REF!
Al Shorouk Bridge (LRT) | #REF!
Ring Road El Marg | #REF!
GOV2 Infra | #REF!
Cairo Alex Railroad | #REF!
Hassan El Mamoun Bridge | #REF!
Sherouk Bridge L&L | #REF!
Ora Zed Park 1B Pkgs A&D | #REF!
Kattameya Creeks | #REF!
Mansoura University Faculty of Medicine | #REF!
Diplomatic District - Infra | #REF!
El Sewedy CFC HQ Internal Finishing | #REF!
Lagoon Discharge Pkg 178 | #REF!
El Khatatba Bridge | #REF!
EGAT Pelletizing Plant | #REF!
MDF Factory | #REF!
Aeon Towers Chiller Building | #REF!
Alegria DP Port | #REF!
Alexandria Bridges | #REF!
Alstom-French Station | #REF!
Autoville Strip Mall | #REF!
El Mahala Bridge | #REF!
EMEC | #REF!
Logestica 02 | #REF!
Marassi Bridges Pkg 37 | #REF!
Marassi Golf Maintance Building Pkg 58 | #REF!
Uptown Service Buildings Pkg 17A | #REF!
Point 90 New Cairo Mall | #REF!
Sodic MV Cables | #REF!
Sodic West Town Hub | #REF!
Limak TB2 Cairo Airport Terminal | #REF!
Twin Towers | #REF!
Uptown Soil Stabilization Pkg 32 | #REF!
Electric Train LRT | #REF!

## Single & Multi Clients (hidden)
Year | Main Category | Sub Category | Scope | Client | Project Manager | Area Manager | Location | S/D Client | Client Type
2010-05-01 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | PR
2010-05-01 | Infrastructure | Bridges & Tunnels | Civil Works | Mohamed Abd El Wahab | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Alex | S | PR
2010-05-01 | Commercial | Offices & Mall | Turn Key | Arabian Group | Eng Karim El Far | Eng Mahmoud Mahlab | 6th of October | D | PR
2011-05-01 | Infrastructure | Tank | Civil Works | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | PR
2011-05-01 | Commercial | Offices & Mall | Civil Works | EMEC | Eng Mohamed Abd El Fatah | Eng Mahmoud Mahlab | 5th settelment | S | PR
2011-05-01 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | PR
2012-05-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Hassan Youssef | Eng Mahmoud Mahlab | North Coast | D | PR
2012-05-01 | Infrastructure | Networks | Civil Works | Sewedy | Eng Hany Fareed | Eng. yasser el saadny | 6th of October | D | AF
2013-05-01 | Commercial | Offices & Mall | Turn Key | Cairo Company for Housing & Development (CCHD) | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | PR
2013-05-01 | Commercial | Offices & Mall | Turn Key | EMAAR | Eng Waleed Tag | Eng Mahmoud Mahlab | North Coast | D | PR
2013-05-01 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | PR
2013-05-01 | Infrastructure | Networks | Civil Works | DPW | Eng Karim El Far | Eng. Omar Sobhy | Sokhna | D | PR
2013-05-01 | Industrial | Factory | Turn Key | Logestica | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | PR
2013-05-01 | Commercial | Terminal | Civil Works | Limak | Eng Mohamed El Saman | Eng. Omar Sobhy | Cairo | S | PR
2014-05-01 | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | PR
2014-05-01 | Commercial | Market | Civil Works | Hyper | Eng Amir | Eng Mahmoud Mahlab | 6th of October | D | PR
2014-05-01 | Commercial | Offices & Mall | Turn Key | Maxim | Eng Raed | Eng. Omar Sobhy | 5th settelment | S | PR
2014-05-01 | Industrial | Power Plant | Turn Key | Sewedy | Eng Mohamed Abd El Fatah | Eng. Mohamed Salah Helmy | Suez | D | AF
2014-05-01 | Commercial | Hotel | Civil Works | El Montazah | Eng Wael Ragabi | Eng. Omar Sobhy | sharm | S | PR
2014-05-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Cairo | D | ARMY
2014-05-01 | Infrastructure | Networks | Civil Works | SODIC | Eng Ashraf Abd El Satar | Eng Mahmoud Mahlab | 6th of October | D | PR
2014-05-01 | Infrastructure | L&L | Civil Works | Al-Futtaim | Eng Mohamed Mostafa | Eng. Omar Sobhy | 6th of October | S | PR
2015-05-01 | Commercial | Club | Turn Key | SODIC | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | PR
2015-05-01 | Residential | Residential | Turn Key | EMAAR | Eng Mohamed Abd El Raouf | Eng Mahmoud Mahlab | Cairo | D | PR
2015-05-01 | Industrial | Power Plant | Turn Key | Sewedy | Eng Ashraf Abd El Satar | Eng. Mohamed Ragab | Benisuef | D | AF
2015-05-01 | Commercial | University | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | PR
2015-05-01 | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | PR
2015-05-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | New Capital | D | ARMY
2016-05-01 | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Cairo | S | PU
2016-05-01 | Infrastructure | L&L | Civil Works | EMAAR | Eng Alaa Mahran | Eng Mahmoud Mahlab | Cairo | D | PR
2016-05-01 | Commercial | Offices & Mall | Turn Key | Army Forces | Eng Adel Rahmo | Eng. Mohamed Ashry | New Capital | D | ARMY
2016-05-01 | Industrial | Factory | Civil Works | CDI | Eng Mohamed Zaki | Eng Mahmoud Mahlab | Benisuef | S | PR
2016-05-01 | Industrial | Power Plant | Civil Works | GAMESA | Eng Karim El Far | Eng Mahmoud Mahlab | Gabal El Zeit | D | PR
2017-05-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Mohamed El Tahlawi | Eng. Tahlawi | Ismailia | D | ARMY
2017-05-01 | Industrial | Power Plant | Turn Key | EETC | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | Mansoura | S | PU
2017-05-01 | Infrastructure | Tank | Civil Works | EMAAR | Eng Marwan Shibl | Eng. Mohamed Fawzy | North Coast | D | PR
2017-05-01 | Commercial | Offices & Mall | Turn Key | Al Babtain Group | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | PR
2017-05-01 | Industrial | Factory | Turn Key | Sewedy | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | AF
2017-05-01 | Industrial | Factory | Turn Key | SIEMENS | Eng Hassan Youssef | Eng Mahmoud Mahlab | Sokhna | S | PR
2017-05-01 | Infrastructure | Networks | Civil Works | DPW | Eng Mohamed Mostafa | Eng. Omar Sobhy | Alegria | D | PR
2018-05-01 | Industrial | Factory | Civil Works | Mintra | Eng Salah Rashad | Eng. Mohamed Abdel Raouf | Cairo | S | PR
2018-05-01 | Commercial | Market | Turn Key | Army Forces | Eng Sayed Osman | Eng. Omar Sobhy | Ismailia | D | ARMY
2018-05-01 | Commercial | Offices & Mall | Civil Works | YAMM | Eng Mohamed Zaki | Eng. Waleed Barakat | 5th settelment | S | PR
2018-05-01 | Industrial | Power Plant | Civil Works | TSK | Eng Amir | Eng Mahmoud Mahlab | Aswan | S | PR
2018-05-01 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | AF
2018-05-01 | Residential | Residential | Turn Key | Utilities And Urban Communities | Eng Mohamed Abd El Fatah | Eng. Omar Sobhy | New Capital | D | PU
2018-05-01 | Infrastructure | Networks | EPC | DPW | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Sokhna | D | PR
2018-05-01 | Infrastructure | L&L | Civil Works | EMAAR | Eng Mohamed Bassuony | Eng Mahmoud Mahlab | Cairo | D | PR
2019-05-01 | Commercial | Offices & Mall | Turn Key | SODIC | Eng Sayed Osman | Eng. Waleed Barakat | 5th settelment | D | PR
2019-05-01 | Infrastructure | Tank | Civil Works | EMAAR | Eng Hassan Youssef | Eng. Waleed Barakat | 5th settelment | D | PR
2019-05-01 | Industrial | Factory | Turn Key | Sewedy | Eng Mohamed El Saman | Eng Mahmoud Mahlab | Suez | D | AF
2019-05-01 | Infrastructure | L&L | Civil Works | Ora | Eng Adham Edward | Eng.adham edward | 6th of October | D | PR
2019-05-01 | Commercial | Parking | Civil Works | Hyper | Eng Tarek Ramadan | Eng. Mohamed Fawzy | 6th of October | D | PR
2019-05-01 | Commercial | Offices & Mall | Turn Key | Marakez | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | S | PR
2019-05-01 | Commercial | Offices & Mall | Core And Shell | Al-Futtaim | Eng Amir | Eng. Waleed Barakat | 5th settelment | S | PR
2019-05-01 | Infrastructure | Landscape | Civil Works | Army Forces | Eng Adel Rahmo | Eng. Omar Sobhy | New Capital | D | ARMY
2020-05-01 | Restoration | Palace | Restoration | Army Forces | Eng Mariam Youssef | Eng Mariam Youssef | Cairo | D | ARMY
2020-05-01 | Commercial | University | Turn Key | Sewedy | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | New Capital | D | AF
2020-05-01 | Industrial | Power Plant | Civil Works | GAMESA | Eng Marwan Shibl | Eng. Waleed Barakat | Gabal El Zeit | D | PR
2020-05-01 | Infrastructure | Networks | Civil Works | Utilities And Urban Communities | Eng Mohamed Abd El Moktader | Eng Mohamed Abd El Fatah | New Capital | D | PU
2020-05-01 | Infrastructure | Railway | Civil Works | ENR | Eng Ali Tawfeek | Eng.callum | alex | S | PU
2020-05-01 | Residential | Residential | Turn Key | Ora | Eng Hesham Ibrahim | Eng. Mohamed Fawzy | 6th of October | D | PR
2020-05-01 | Infrastructure | Bridges & Tunnels | Civil Works | EMAAR | Eng Reda | Eng. Mohamed Fawzy | North Coast | D | PR
2020-05-01 | Commercial | Offices & Mall | Civil Works | Kemet | Eng Hany Yassin | Eng. Mohamed Ashry | New Capital | S | PR
2021-05-01 | Commercial | Hospital | Turn Key | New Giza | Eng Ashraf Abd El Satar | Eng. Mohamed Fawzy | 6th of October | D | PR
2021-05-01 | Residential | Residential | Turn Key | Starlight | Eng Mohamed Kamal | Eng. Waleed Barakat | 5th settelment | S | PR
2021-05-01 | Commercial | University | Civil Works | Utilities And Urban Communities | Eng Emad Habi | Eng Mohamed Abd El Fatah | mansoura | D | PU
2021-05-01 | Infrastructure | Bridges & Tunnels | Civil Works | Army Forces | Eng Khaled Tawfek | Eng Hussien Bahgat | qlyboya | D | ARMY
2021-05-01 | Industrial | Factory | Turn Key | Sewedy | Eng Mohamed Fadel | Eng. mohamed el seman | Suez | D | AF
2021-05-01 | Infrastructure | Port | Civil Works | Transportation Ministry | Eng Tarek Ramadan | Eng. mohamed el seman | Sokhna | S | PU
2021-05-01 | Industrial | Factory | Turn Key | Naile Wood | Eng Bader Osman | Eng. mohamed el seman | sadat | S | PR

## Cost & Price Filter
Project | Revised Contract Value | EAC | dividend | Type of Unit | factor | Filter | LE-$
Marassi Civic Center Pkg 45 | 56931016 | 64758247.2535 |  |  | 1 | Unit | LE
Al Oula Infra | 72946445.96 | 66087308.6012 |  |  | 1 | Unit | LE
New Giza Phase 01 | 172216796.0405 | 173716038.3248 |  |  | 1 | Unit | LE
Hyper Solimanya | 110450184.62 | 108679008.9749 | 5539.1926 |  | 1 | Unit | LE
Ismailia Bridges | 56527617 | 33948207.928 | 174 | m | 1 | Unit | LE
Maxium Mall | 98576600 | 104888994.0403 |  | Customer/Day | 1 | Unit | LE
Ataqqa Power Plant | 184387980.81 | 97786625.9352 |  |  | 1 | Unit | LE
Mall of Egypt Bridge | 183459815.63 | 165227581.2857 |  |  | 1 | Unit | LE
Marassi Tanks PKG 22 | 18438370 | 16655530.55 | 5000 | tank storage m3 | 1 | Unit | LE
Sodic Club House | 161208266 | 169537179.4745 |  |  | 1 | Unit | LE
Montazah Hotel Sharm | 33784495.5267 | 30373982.7996 |  |  | 1 | Unit | LE
Uptown Cairo Pkg 53 | 314789511 | 344222187 |  |  | 1 | Unit | LE
Bani Suif Power Plant 1021 | 427594086.74 | 319973217.7839 | 4800 | MW | 1 | Unit | LE
New Giza Phase 02 | 155643269.76 | 161564179.8036 |  |  | 1 | Unit | LE
JICA Wind Farm Gabal El Zeet | 120483319.9 | 82164809.214 | 220 | MW | 1 | Unit | LE
El Mostathmereen Mokatam Substation | 135792183 | 85209855.07 | 220 | KV | 1 | Unit | LE
Levana UpTown PKG 62 | 47319156 | 52574895.421 |  |  | 1 | Unit | LE
Kayan 110 | 1335232523 | 1306314436.593 |  |  | 1 | Unit | LE
El Amal Bridge | 28943151 | 21210869.997 | 90 | m | 1 | Unit | LE
Bani Suif Cement | 274663700 | 265512440.135 | 1000 | 1000 Ton / Day | 1 | Unit | LE
New Giza Wall | 2648340.9749 | 1057277.26 |  |  | 1 | Unit | LE
Tamey El Amdid Mansora Power Station | 114399640 | 92853851.3 | 220 | KV | 1 | Unit | LE
Ismailia Substation 500-220 | 109399640 | 94574974.6595 | 220 | KV | 1 | Unit | LE
El Amal Bridge L&L | 9050320 | 6335224 |  |  | 1 | Unit | LE
FIEM Wind Farm Gabal El Zeet | 72547889 | 43182355.317 | 120 | MW | 1 | Unit | LE
KFW Wind Farm Gabal El Zeet | 23038288.54 | 13129303.501 | 40 | MW | 1 | Unit | LE
Marassi Tank PKG 107 | 54777143 | 42810448.983 | 24500 | tank storage m3 | 1 | Unit | LE
Ben Zayed New Capital Tunnel | 343357654.106 | 271212136.105 | 330 | m | 1 | Unit | LE
Ministries Buildings | 2740570200 | 2663137373.0012 | 4200 | People Served | 1 | Unit | LE
Bani Suif Substation | 120712211 | 101105076 | 220 | KV | 1 | Unit | LE
Royal City Mall | 527037820 | 502741033.2292 | 95 | No of Shops | 1 | Unit | LE
Shoubra Banha Bridge L&L | 3865380 | 1461115 | 5000 | m | 1 | Unit | LE
SLP Logistic Center PI Park Sewedy Stores | 98230405 | 86259669.128 | 45000 | Storage Capacity | 1 | Unit | LE
El Mostakbal Bridge L&L | 4424558 | 2062745 |  |  | 1 | Unit | LE
Kayan Wall L&L | 107782440 | 82991132 |  |  | 1 | Unit | LE
Elco Suez Steel Rolling Mill Plant 3 | 417390514 | 292181074.4464 | 1.4 | Million ton / year | 1 | Unit | LE
Hyper El Temsah | 168976040.9524 | 141672524.9015 | 3312 | Customer/Day | 1 | Unit | LE
Marassi Bridge Pkg 117 | 45205818 | 31111755 | 60 | Length m | 1 | Unit | LE
Siemens Power Station | 332856409 | 319846012.345 |  |  | 1 | Unit | LE
Uptown FM85 Pkg 85 |  |  |  |  | 1 | Unit | LE
El Sokhna Tunnel 01 | 46639513 | 37675288 |  |  | 1 | Unit | LE
Abu Sultan Bridge 01 | 18752986 | 13705181 |  |  | 1 | Unit | LE
Mintra Factory | 112045826 | 113125840.857 |  |  | 1 | Unit | LE
King Farouk Restoration |  |  |  |  | 1 | Unit | LE
Mohamed Ali Palace | 150000000 | 125642410.0235 |  |  | 1 | Unit | LE
Nefisha Bridge | 70928098 | 51420131 |  |  | 1 | Unit | LE
Fish Market | 66185668.5714 | 58052020.6193 | 32 | Shops | 1 | Unit | LE
Al Jazi Mall | 245977347.1316 | 228488395.4632 |  |  | 1 | Unit | LE
Benban Aswan Alcazars Solar Park | 212005784 | 118641100 | 200 | KW | 1 | Unit | LE
El Alameen Roads Earth Works | 54192857 | 46001919 |  |  | 1 | Unit | LE
El Sewedy Univeristy | 262378822 | 232988357.458 | 300 | Student | 1 | Unit | LE
El Sokhna Tunnel L&L |  |  |  |  | 1 | Unit | LE
R05 Residential District Z1 & Z2 | 3200000000 | 2976000000 |  |  | 1 | Unit | LE
Abu Sultan Bridge 02 Greenhouse | 67755600 | 59506484.6859 |  |  | 1 | Unit | LE
El Sokhna Tunnel 02 | 22334150 | 17647987 |  |  | 1 | Unit | LE
El Awsty Middle Tunnel L&L | 1024820 |  |  |  | 1 | Unit | LE
Sodic Eastown EDNC | 1074545067 | 1010072362.98 | 0 | 0 | 1 | Unit | LE
Marassi Civic Center Pkg 144 | 176420375 | 122239319.38 |  |  | 1 | Unit | LE
DPW Sokhna Dubai Port | 1633315425 | 1246507144.6956 | 9190 | Container Slots | 1 | Unit | LE
Slope Stablization PKG 101 | 52028085.7143 | 47340355.1914 |  |  | 1 | Unit | LE
Elco Steel Substation | 32341773 | 34798196.7776 | 220 | KW | 1 | Unit | LE
Sewab Greenhouse Tunnel | 10957813.825 | 9623720.8521 |  |  | 1 | Unit | LE
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 | 136045980.5313 | 680 | Water be treated m3/ hour For 16 hours / day | 1 | Unit | LE
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 | 136045980.5313 | 10600 | Tank Volume m3 | 1 | Unit | LE
Multi Sports Hall | 1200000000 | 1140000000 | 15000 | Chair | 1 | Unit | LE
EGAT | 65831906 | 56811131 |  |  | 1 | Unit | LE
Abou Ghazala Bridge Ramp L&L | 1688453 | 1511719 |  |  | 1 | Unit | LE
Mohamed Ali Fahmy Ramps L&L | 7149700 | 6713205 |  |  | 1 | Unit | LE
El Mosheer Bridge Abu Zaied Khdr L&L | 4203687 | 2001684 |  |  | 1 | Unit | LE
Ora Zed Park L&L | 1042542 | 758212.27 |  |  | 1 | Unit | LE
DoubleTree Mangroovy El Gouna Hotel | 57898699.39 | 54424777.4266 |  |  | 1 | Unit | LE
Baron Palace Fence | 16220552 | 14434567.4488 |  |  | 1 | Unit | LE
Safeer Square Bridge | 95436549 | 82927091 |  |  | 1 | Unit | LE
Suez Road Tunnel Res L&L | 4423592 | 4769909 |  |  | 1 | Unit | LE
HyperOne Zayed Extention | 133583770 | 99106552.4453 | 510 | Parking Capacity | 1 | Unit | LE
IKEA Extention MoA | 196190620 | 212380869 |  |  | 1 | Unit | LE
CFC Podium II | 635000000 | 524290213.0394 | 300 | Offices | 1 | Unit | LE
Mostafa Kamel Bridge L&L |  |  |  |  | 1 | Unit | LE
Josef Tito Bridge L&L |  |  |  |  | 1 | Unit | LE
Espiko Bridge L&L |  |  |  |  | 1 | Unit | LE
El Gabal El Asfr Tunnel L&L |  |  |  |  | 1 | Unit | LE
MR3 Bridge L&L | 1520085 | 1367204 |  |  | 1 | Unit | LE
El Sewedy Univeristy 2 Phase 2 | 593999147 | 510839266 | 900 | People Served | 1 | Unit | LE
Mehwar El Salam Axis L&L | 16843027 | 15775883 |  |  | 1 | Unit | LE
El Hegaz Square Bridge | 138370050 | 121772563 |  |  | 1 | Unit | LE
Marina Inland Marassi Pkg 162 | 434504076.4286 | 354989830.4421 |  |  | 1 | Unit | LE
Sultana Malek Restoration | 85000000 | 72250000 |  |  | 1 | Unit | LE
Lekela 250MW Wind Farm | 182442342 | 178793495.16 | 250 | MW | 1 | Unit | LE
New Giza Hospital | 542690000 | 507186915.8879 | 164 | bed | 1 | Unit | LE
Kayan Landscape | 100042648 | 93060671.3161 |  |  | 1 | Unit | LE
Abbas Akkad Bridge | 124132580.9524 | 122869821.99 |  |  | 1 | Unit | LE
El Asher Men Ramadan Bridge | 93910355 | 85732351.721 |  |  | 1 | Unit | LE
Kafr Shokr Bridge | 147845325 | 133974586 |  |  | 1 | Unit | LE
Al Shorouk Bridge (LRT) | 26145782 | 24180000 |  |  | 1 | Unit | LE
GOV2 Infra | 650000000 | 607750000 | 1500 | ACRE | 1 | Unit | LE
Cairo Alex Railroad | 967000000 | 879970000 | 35 | KM RAIL | 1 | Unit | LE
Hassan El Mamoun Bridge | 93800000 | 88756688.976 |  |  | 1 | Unit | LE
Sherouk Bridge L&L | 1000000 | 1648128.4931 |  |  | 1 | Unit | LE
Ora Zed Park 1B Pkgs A&D | 870293108 | 808937442.9565 | 320 | no of apr | 1 | Unit | LE
Kattameya Creeks | 1462000000 | 1352350000 |  |  | 1 | Unit | LE
Mansoura University Faculty of Medicine | 219047619.0476 | 203714285.7143 |  |  | 1 | Unit | LE
Diplomatic District - Infra | 390000000 | 364650000 | 1600 | ACRE | 1 | Unit | LE
El Sewedy CFC HQ Internal Finishing | 327718153.3333 | 302367726 |  |  | 1 | Unit | LE
Lagoon Discharge Pkg 178 | 40449240 | 35085670.776 |  |  | 1 | Unit | LE
El Khatatba Bridge | 142857142.8571 | 130845321 |  |  | 1 | Unit | LE
EGAT Pelletizing Plant | 375000000 | 341250000 |  |  | 1 | Unit | LE
Sokhna Port Expansion | 1100000000 | 1023000000 | 12 | KM | 1 | Unit | LE
MDF Factory | 175000000 | 162750000 |  |  | 1 | Unit | LE
Olympic City L&L |  |  |  |  | 1 | Unit | LE
Kemet Building | 71052428.57 | 66078758.5701 |  |  | 1 | Unit | LE
Point 90 New Cairo Mall | 145010925.68 | 129215876.9678 | 75 | No of Shops | 1 | Unit | LE
Marassi Bridges Pkg 37 | 26193836.68 | 27330602.3975 |  |  | 1 | Unit | LE
Marassi Golf Maintance Building Pkg 58 | 4720405.25 | 5275181.8987 |  |  | 1 | Unit | LE
Uptown Soil Stabilization Pkg 32 | 17421145.8 | 21051883.5147 |  |  | 1 | Unit | LE
Ismailia Bridge L&L | 49485210.2 |  |  |  | 1 | Unit | LE
El Obour Bridge B2 | 9000000 | 7200000 |  |  | 1 | Unit | LE
Autoville Strip Mall | 51072634 | 55255998 |  |  | 1 | Unit | LE
Uptown Service Buildings Pkg 17A | 55905931 | 53843629.5863 |  |  | 1 | Unit | LE
Sodic West Town Hub | 54160920.41 | 56137642.32 |  |  | 1 | Unit | LE
Dubai Port Sokhna Basin 1 | 34548331.29 | 27990071.4837 |  |  | 1 | Unit | LE
Alexandria Bridges | 35589876.5 | 28766462 | 630 | m | 1 | Unit | LE
El Mahala Bridge | 67245402 | 48126832 |  |  | 1 | Unit | LE
El Wahat Bridge | 22540933.0883 | 18032746.4706 | 35 | m | 1 | Unit | LE
El Wahat Tunnel | 18818015.28 | 13923981.6424 | 60 | m | 1 | Unit | LE
AL-Asmarat | 6636851 | 8517150.2182 |  |  | 1 | Unit | LE
Alegria DP Port | 605714038 | 498059352 |  |  | 1 | Unit | LE
El Alameen Bridge L&L |  |  |  |  | 1 | Unit | LE
El Asher of Ramadan Bridge L&L |  |  |  |  | 1 | Unit | LE
EMEC | 10688481.1 | 8907067.5833 |  |  | 1 | Unit | LE
Ismailia Bridge L&L |  |  |  |  | 1 | Unit | LE
Logestica Phase 01 | 31905026.19 | 27743501.0348 |  |  | 1 | Unit | LE
Logestica Phase 02 | 20681422 | 16069494.51 |  |  | 1 | Unit | LE
Logestica Phase 03 | 4820461 | 3681383 |  |  | 1 | Unit | LE
Sodic MV Cables | 19589518 | 16384636.8472 |  |  | 1 | Unit | LE
Limak TB2 Cairo Airport Terminal | 119626844 | 96755558 |  |  | 1 | Unit | LE
Twin Towers | 64000000.23 | 63714421.967 |  |  | 1 | Unit | LE
Aeon Towers Chiller Building |  |  |  |  | 1 | Unit | LE
Electric Train LRT |  |  |  |  | 1 | Unit | LE
Sea Shell Playa |  |  |  |  | 1 | Unit | LE
Marassi Civic Center Pkg 45 | 56931016 | 64758247.2535 | 6743 | m2 | 1 | area | LE
Al Oula Infra | 72946445.96 | 66087308.6012 |  | m2 | 1 | area | LE
New Giza Phase 01 | 172216796.0405 | 173716038.3248 | 16200 | m2 | 1 | area | LE
Hyper Solimanya | 110450184.62 | 108679008.9749 | 10871 | m2 | 1 | area | LE
Ismailia Bridges | 56527617 | 33948207.928 | 6309 | m2 | 1 | area | LE
Maxium Mall | 98576600 | 104888994.0403 | 70000 | m2 | 1 | area | LE
Ataqqa Power Plant | 184387980.81 | 97786625.9352 |  | m2 | 1 | area | LE
Mall of Egypt Bridge | 183459815.63 | 165227581.2857 | 1553 | m2 | 1 | area | LE
Marassi Tanks PKG 22 | 18438370 | 16655530.55 |  | m2 | 1 | area | LE
Sodic Club House | 161208266 | 169537179.4745 | 20000 | m2 | 1 | area | LE
Montazah Hotel Sharm | 33784495.5267 | 30373982.7996 | 16580 | m2 | 1 | area | LE
Uptown Cairo Pkg 53 | 314789511 | 344222187 | 63752 | m2 | 1 | area | LE
Bani Suif Power Plant 1021 | 427594086.74 | 319973217.7839 |  | m2 | 1 | area | LE
New Giza Phase 02 | 155643269.76 | 161564179.8036 | 16200 | m2 | 1 | area | LE
JICA Wind Farm Gabal El Zeet | 120483319.9 | 82164809.214 |  | m2 | 1 | area | LE
El Mostathmereen Mokatam Substation | 135792183 | 85209855.07 |  | m2 | 1 | area | LE
Levana UpTown PKG 62 | 47319156 | 52574895.421 | 22213.8 | m2 | 1 | area | LE
Kayan 110 | 1335232523 | 1306314436.593 | 152000 | m2 | 1 | area | LE
El Amal Bridge | 28943151 | 21210869.997 | 2520 | m2 | 1 | area | LE
Bani Suif Cement | 274663700 | 265512440.135 |  | m2 | 1 | area | LE
New Giza Wall | 2648340.9749 | 1057277.26 |  | m2 | 1 | area | LE
Tamey El Amdid Mansora Power Station | 114399640 | 92853851.3 |  | m2 | 1 | area | LE
Ismailia Substation 500-220 | 109399640 | 94574974.6595 | 15000 | m2 | 1 | area | LE
El Amal Bridge L&L | 9050320 | 6335224 |  | m2 | 1 | area | LE
FIEM Wind Farm Gabal El Zeet | 72547889 | 43182355.317 |  | m2 | 1 | area | LE
KFW Wind Farm Gabal El Zeet | 23038288.54 | 13129303.501 |  | m2 | 1 | area | LE
Marassi Tank PKG 107 | 54777143 | 42810448.983 | 0 | m2 | 1 | area | LE
Ben Zayed New Capital Tunnel | 343357654.106 | 271212136.105 | 18596 | m2 | 1 | area | LE
Ministries Buildings | 2740570200 | 2663137373.0012 | 169000 | m2 | 1 | area | LE
Bani Suif Substation | 120712211 | 101105076 | 29643 | m2 | 1 | area | LE
Royal City Mall | 527037820 | 502741033.2292 | 25379 | m2 | 1 | area | LE
Shoubra Banha Bridge L&L | 3865380 | 1461115 | 4000 | m2 | 1 | area | LE
SLP Logistic Center PI Park Sewedy Stores | 98230405 | 86259669.128 | 13000 | m2 | 1 | area | LE
El Mostakbal Bridge L&L | 4424558 | 2062745 | 4286.7 | m2 | 1 | area | LE
Kayan Wall L&L | 107782440 | 82991132 |  | m2 | 1 | area | LE
Elco Suez Steel Rolling Mill Plant 3 | 417390514 | 292181074.4464 |  | m2 | 1 | area | LE
Hyper El Temsah | 168976040.9524 | 141672524.9015 | 7800 | m2 | 1 | area | LE
Marassi Bridge Pkg 117 | 45205818 | 31111755 | 1080 | m2 | 1 | area | LE
Siemens Power Station | 332856409 | 319846012.345 | 16200 | m2 | 1 | area | LE
Uptown FM85 Pkg 85 |  |  |  | m2 | 1 | area | LE
El Sokhna Tunnel 01 | 46639513 | 37675288 | 3604 | m2 | 1 | area | LE
Abu Sultan Bridge 01 | 18752986 | 13705181 | 1738 | m2 | 1 | area | LE
Mintra Factory | 112045826 | 113125840.857 | 52500 | m2 | 1 | area | LE
King Farouk Restoration |  |  |  | m2 | 1 | area | LE
Mohamed Ali Palace | 150000000 | 125642410.0235 |  | m2 | 1 | area | LE
Nefisha Bridge | 70928098 | 51420131 | 6900 | m2 | 1 | area | LE
Fish Market | 66185668.5714 | 58052020.6193 | 6400 | m2 | 1 | area | LE
Al Jazi Mall | 245977347.1316 | 228488395.4632 | 48853.59 | m2 | 1 | area | LE
Benban Aswan Alcazars Solar Park | 212005784 | 118641100 |  | m2 | 1 | area | LE
El Alameen Roads Earth Works | 54192857 | 46001919 |  | m2 | 1 | area | LE
El Sewedy Univeristy | 262378822 | 232988357.458 | 14500 | m2 | 1 | area | LE
El Sokhna Tunnel L&L |  |  |  | m2 | 1 | area | LE
R05 Residential District Z1 & Z2 | 3200000000 | 2976000000 | 618237 | m2 | 1 | area | LE
Abu Sultan Bridge 02 Greenhouse | 67755600 | 59506484.6859 | 476 | m2 | 1 | area | LE
El Sokhna Tunnel 02 | 22334150 | 17647987 | 1813 | m2 | 1 | area | LE
El Awsty Middle Tunnel L&L | 1024820 |  |  | m2 | 1 | area | LE
Sodic Eastown EDNC | 1074545067 | 1010072362.98 | 156000 | m2 | 1 | area | LE
Marassi Civic Center Pkg 144 | 176420375 | 122239319.38 | 12500 | m2 | 1 | area | LE
DPW Sokhna Dubai Port | 1633315425 | 1246507144.6956 | 600000 | m2 | 1 | area | LE
Slope Stablization PKG 101 | 52028085.7143 | 47340355.1914 | 11305 | m2 | 1 | area | LE
Elco Steel Substation | 32341773 | 34798196.7776 |  | m2 | 1 | area | LE
Sewab Greenhouse Tunnel | 10957813.825 | 9623720.8521 | 476 | m2 | 1 | area | LE
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 | 136045980.5313 | 12350 | m2 | 1 | area | LE
Mivida Irrigation Treatment Plant Pkg 140 | 170057475.6641 | 136045980.5313 | 12350 | m2 | 1 | area | LE
Multi Sports Hall | 1200000000 | 1140000000 | 18000 | m2 | 1 | area | LE
EGAT | 65831906 | 56811131 |  | m2 | 1 | area | LE
Abou Ghazala Bridge Ramp L&L | 1688453 | 1511719 |  | m2 | 1 | area | LE
Mohamed Ali Fahmy Ramps L&L | 7149700 | 6713205 |  | m2 | 1 | area | LE
El Mosheer Bridge Abu Zaied Khdr L&L | 4203687 | 2001684 |  | m2 | 1 | area | LE
Ora Zed Park L&L | 1042542 | 758212.27 |  | m2 | 1 | area | LE
DoubleTree Mangroovy El Gouna Hotel | 57898699.39 | 54424777.4266 | 18352 | m2 | 1 | area | LE
Baron Palace Fence | 16220552 | 14434567.4488 |  | m2 | 1 | area | LE
Safeer Square Bridge | 95436549 | 82927091 | 6750 | m2 | 1 | area | LE
Suez Road Tunnel Res L&L | 4423592 | 4769909 |  | m2 | 1 | area | LE
HyperOne Zayed Extention | 133583770 | 99106552.4453 | 30000 | m2 | 1 | area | LE
IKEA Extention MoA | 196190620 | 212380869 | 19836 | m2 | 1 | area | LE
CFC Podium II | 635000000 | 524290213.0394 | 98633 | m2 | 1 | area | LE
Mostafa Kamel Bridge L&L |  |  |  | m2 | 1 | area | LE
Josef Tito Bridge L&L |  |  |  | m2 | 1 | area | LE
Espiko Bridge L&L |  |  |  | m2 | 1 | area | LE
El Gabal El Asfr Tunnel L&L |  |  |  | m2 | 1 | area | LE
MR3 Bridge L&L | 1520085 | 1367204 |  | m2 | 1 | area | LE
El Sewedy Univeristy 2 Phase 2 | 593999147 | 510839266 | 38447 | m2 | 1 | area | LE
Mehwar El Salam Axis L&L | 16843027 | 15775883 |  | m2 | 1 | area | LE
El Hegaz Square Bridge | 138370050 | 121772563 | 9450 | m2 | 1 | area | LE
Ring Road | 524000000 | 492560000 | 63600 | m2 | 1 | area | LE
Marina Inland Marassi Pkg 162 | 434504076.4286 | 354989830.4421 |  | m2 | 1 | area | LE
Sultana Malek Restoration | 85000000 | 72250000 |  | m2 | 1 | area | LE
Lekela 250MW Wind Farm | 182442342 | 178793495.16 |  | m2 | 1 | area | LE
New Giza Hospital | 542690000 | 507186915.8879 | 23000 | m2 | 1 | area | LE
Kayan Landscape | 100042648 | 93060671.3161 |  | m2 | 1 | area | LE
Abbas Akkad Bridge | 124132580.9524 | 122869821.99 | 15600 | m2 | 1 | area | LE
El Asher Men Ramadan Bridge | 93910355 | 85732351.721 | 4200 | m2 | 1 | area | LE
Kafr Shokr Bridge | 147845325 | 133974586 | 16900 | m2 | 1 | area | LE
Al Shorouk Bridge (LRT) | 26145782 | 24180000 | 7070 | m2 | 1 | area | LE
GOV2 Infra | 650000000 | 607750000 |  | m2 | 1 | area | LE
Cairo Alex Railroad | 967000000 | 879970000 |  | m2 | 1 | area | LE
Hassan El Mamoun Bridge | 93800000 | 88756688.976 | 13440 | m2 | 1 | area | LE
Sherouk Bridge L&L | 1000000 | 1648128.4931 |  | m2 | 1 | area | LE
Ora Zed Park 1B Pkgs A&D | 870293108 | 808937442.9565 | 75500 | m2 | 1 | area | LE
Kattameya Creeks | 1462000000 | 1352350000 | 140150 | m2 | 1 | area | LE
Mansoura University Faculty of Medicine | 219047619.0476 | 203714285.7143 | 40000 | m2 | 1 | area | LE
Diplomatic District - Infra | 390000000 | 364650000 |  | m2 | 1 | area | LE
El Sewedy CFC HQ Internal Finishing | 327718153.3333 | 302367726 | 23500 | m2 | 1 | area | LE
Lagoon Discharge Pkg 178 | 40449240 | 35085670.776 |  | m2 | 1 | area | LE
El Khatatba Bridge | 142857142.8571 | 130845321 | 9940 | m2 | 1 | area | LE
EGAT Pelletizing Plant | 375000000 | 341250000 |  | m2 | 1 | area | LE
Sokhna Port Expansion | 1100000000 | 1023000000 |  | m2 | 1 | area | LE
MDF Factory | 175000000 | 162750000 | 23710 | m2 | 1 | area | LE
Olympic City L&L |  |  |  | m2 | 1 | area | LE
Kemet Building | 71052428.57 | 66078758.5701 | 21460 | m2 | 1 | area | LE
Point 90 New Cairo Mall | 145010925.68 | 129215876.9678 | 69132.17 | m2 | 1 | area | LE
Marassi Bridges Pkg 37 | 26193836.68 | 27330602.3975 |  | m2 | 1 | area | LE
Marassi Golf Maintance Building Pkg 58 | 4720405.25 | 5275181.8987 |  | m2 | 1 | area | LE
Uptown Soil Stabilization Pkg 32 | 17421145.8 | 21051883.5147 |  | m2 | 1 | area | LE
Ismailia Bridge L&L | 49485210.2 |  |  | m2 | 1 | area | LE
El Obour Bridge B2 | 9000000 | 7200000 | 735 | m2 | 1 | area | LE
Autoville Strip Mall | 51072634 | 55255998 |  | m2 | 1 | area | LE
Uptown Service Buildings Pkg 17A | 55905931 | 53843629.5863 |  | m2 | 1 | area | LE
Sodic West Town Hub | 54160920.41 | 56137642.32 |  | m2 | 1 | area | LE
Dubai Port Sokhna Basin 1 | 34548331.29 | 27990071.4837 |  | m2 | 1 | area | LE
Alexandria Bridges | 35589876.5 | 28766462 | 9135 | m2 | 1 | area | LE
El Mahala Bridge | 67245402 | 48126832 | 7830 | m2 | 1 | area | LE
El Wahat Bridge | 22540933.0883 | 18032746.4706 | 735 | m2 | 1 | area | LE
El Wahat Tunnel | 18818015.28 | 13923981.6424 | 3000 | m2 | 1 | area | LE
AL-Asmarat | 6636851 | 8517150.2182 |  | m2 | 1 | area | LE
Alegria DP Port | 605714038 | 498059352 |  | m2 | 1 | area | LE
El Alameen Bridge L&L |  |  |  | m2 | 1 | area | LE
El Asher of Ramadan Bridge L&L |  |  |  | m2 | 1 | area | LE
EMEC | 10688481.1 | 8907067.5833 |  | m2 | 1 | area | LE
Ismailia Bridge L&L |  |  |  | m2 | 1 | area | LE
Logestica Phase 01 | 31905026.19 | 27743501.0348 |  | m2 | 1 | area | LE
Logestica Phase 02 | 20681422 | 16069494.51 |  | m2 | 1 | area | LE
Logestica Phase 03 | 4820461 | 3681383 |  | m2 | 1 | area | LE
Sodic MV Cables | 19589518 | 16384636.8472 |  | m2 | 1 | area | LE
Limak TB2 Cairo Airport Terminal | 119626844 | 96755558 |  | m2 | 1 | area | LE
Twin Towers | 64000000.23 | 63714421.967 |  | m2 | 1 | area | LE
Aeon Towers Chiller Building |  |  |  | m2 | 1 | area | LE
Electric Train LRT |  |  |  | m2 | 1 | area | LE
Sea Shell Playa |  |  |  | m2 | 1 | area | LE
Marassi Civic Center Pkg 45 | 9348278.4893 | 10633538.1369 |  |  | 6.09 | Unit | $
Al Oula Infra | 11978069.9442 | 10851774.8114 |  |  | 6.09 | Unit | $
New Giza Phase 01 | 24086265.1805 | 24295949.4161 |  |  | 7.15 | Unit | $
Hyper Solimanya | 15447578.2685 | 15199861.3951 | 5539.1926 |  | 7.15 | Unit | $
Ismailia Bridges | 6365722.6351 | 3822996.3883 | 174 | m | 8.88 | Unit | $
Maxium Mall | 13786937.0629 | 14669789.3763 |  | Customer/Day | 7.15 | Unit | $
Ataqqa Power Plant | 25788528.7846 | 13676451.1797 |  |  | 7.15 | Unit | $
Mall of Egypt Bridge | 23430372.3665 | 21101862.2332 |  |  | 7.83 | Unit | $
Marassi Tanks PKG 22 | 3027646.9622 | 2734898.2841 | 5000 | tank storage m3 | 6.09 | Unit | $
Sodic Club House | 20588539.719 | 21652257.915 |  |  | 7.83 | Unit | $
Montazah Hotel Sharm | 4725104.2695 | 4248109.4825 |  |  | 7.15 | Unit | $
Uptown Cairo Pkg 53 | 40203002.682 | 43961965.1341 |  |  | 7.83 | Unit | $
Bani Suif Power Plant 1021 | 54609717.3359 | 40865034.1997 | 4800 | MW | 7.83 | Unit | $
New Giza Phase 02 | 19877812.2299 | 20633994.8664 |  |  | 7.83 | Unit | $
JICA Wind Farm Gabal El Zeet | 15387397.1775 | 10493589.9379 | 220 | MW | 7.83 | Unit | $
El Mostathmereen Mokatam Substation | 15309152.5366 | 9606522.5558 | 220 | KV | 8.87 | Unit | $
Levana UpTown PKG 62 | 5328733.7838 | 5920596.3312 |  |  | 8.88 | Unit | $
Kayan 110 | 186745807.4126 | 182701319.8032 |  |  | 7.15 | Unit | $
El Amal Bridge | 3696443.295 | 2708923.3713 | 90 | m | 7.83 | Unit | $
Bani Suif Cement | 30965467.8692 | 29933758.7525 | 1000 | 1000 Ton / Day | 8.87 | Unit | $
New Giza Wall | 338230.0096 | 135029.0243 |  |  | 7.83 | Unit | $
Tamey El Amdid Mansora Power Station | 6337930.1939 | 5144257.6898 | 220 | KV | 18.05 | Unit | $
Ismailia Substation 500-220 | 6060921.8837 | 5239610.7845 | 220 | KV | 18.05 | Unit | $
El Amal Bridge L&L | 510164.5998 | 357115.2198 |  |  | 17.74 | Unit | $
FIEM Wind Farm Gabal El Zeet | 8179017.9256 | 4868360.2387 | 120 | MW | 8.87 | Unit | $
KFW Wind Farm Gabal El Zeet | 2597326.7802 | 1480192.052 | 40 | MW | 8.87 | Unit | $
Marassi Tank PKG 107 | 7661138.8811 | 5987475.3822 | 24500 | tank storage m3 | 7.15 | Unit | $
Ben Zayed New Capital Tunnel | 19075425.2281 | 15067340.8947 | 330 | m | 18 | Unit | $
Ministries Buildings | 152253900 | 147952076.2778 | 4200 | People Served | 18 | Unit | $
Bani Suif Substation | 6687657.1191 | 5601389.2521 | 220 | KV | 18.05 | Unit | $
Royal City Mall | 29118111.6022 | 27775747.6922 | 95 | No of Shops | 18.1 | Unit | $
Shoubra Banha Bridge L&L | 219125.8503 | 82829.6485 | 5000 | m | 17.64 | Unit | $
SLP Logistic Center PI Park Sewedy Stores | 5442127.7008 | 4778929.0376 | 45000 | Storage Capacity | 18.05 | Unit | $
El Mostakbal Bridge L&L | 247874.3978 | 115559.944 |  |  | 17.85 | Unit | $
Kayan Wall L&L | 6079099.8308 | 4680830.9081 |  |  | 17.73 | Unit | $
Elco Suez Steel Rolling Mill Plant 3 | 23448905.2809 | 16414667.1037 | 1.4 | Million ton / year | 17.8 | Unit | $
Hyper El Temsah | 9424207.5266 | 7901423.5863 | 3312 | Customer/Day | 17.93 | Unit | $
Marassi Bridge Pkg 117 | 2549679.5262 | 1754752.1151 | 60 | Length m | 17.73 | Unit | $
Siemens Power Station | 18773627.1292 | 18039820.2112 |  |  | 17.73 | Unit | $
Uptown FM85 Pkg 85 | 0 | 0 |  |  | 17.91 | Unit | $
El Sokhna Tunnel 01 | 2629059.3574 | 2123747.9143 |  |  | 17.74 | Unit | $
Abu Sultan Bridge 01 | 1061890.487 | 776057.8143 |  |  | 17.66 | Unit | $
Mintra Factory | 6315999.2108 | 6376879.417 |  |  | 17.74 | Unit | $
King Farouk Restoration | 0 | 0 |  |  | 17.66 | Unit | $
Mohamed Ali Palace | 8493771.2344 | 7114519.2539 |  |  | 17.66 | Unit | $
Nefisha Bridge | 3969115.7247 | 2877455.568 |  |  | 17.87 | Unit | $
Fish Market | 3691336.7859 | 3237703.3251 | 32 | Shops | 17.93 | Unit | $
Al Jazi Mall | 13764820.7684 | 12786144.1222 |  |  | 17.87 | Unit | $
Benban Aswan Alcazars Solar Park | 11824081.6509 | 6616904.6291 | 200 | KW | 17.93 | Unit | $
El Alameen Roads Earth Works | 3030920.4139 | 2572814.2617 |  |  | 17.88 | Unit | $
El Sewedy Univeristy | 14600936.1157 | 12965406.6476 | 300 | Student | #N/A | Unit | $
El Sokhna Tunnel L&L | 0 | 0 |  |  | 5.36 | Unit | $
R05 Residential District Z1 & Z2 | 178471834.9136 | 165978806.4696 |  |  | 17.93 | Unit | $
Abu Sultan Bridge 02 Greenhouse | 3810776.153 | 3346821.4109 |  |  | 17.78 | Unit | $
El Sokhna Tunnel 02 | 1244935.8974 | 983722.7982 |  |  | 17.94 | Unit | $
El Awsty Middle Tunnel L&L | 63495.6629 | 0 |  |  | 16.14 | Unit | $
Sodic Eastown EDNC | 61088406.3104 | 57423101.9318 | 0 | 0 | 17.59 | Unit | $
Marassi Civic Center Pkg 144 | 9950387.7609 | 6894490.6588 |  |  | 17.73 | Unit | $
DPW Sokhna Dubai Port | 91348737.4161 | 69715164.6921 | 9190 | Container Slots | 17.88 | Unit | $
Slope Stablization PKG 101 | 2896886.7324 | 2635877.2378 |  |  | 17.96 | Unit | $
Elco Steel Substation | 1799764.7746 | 1936460.5886 | 220 | KW | 17.97 | Unit | $
Sewab Greenhouse Tunnel | 616299.9902 | 541266.6396 |  |  | 17.78 | Unit | $
Mivida Irrigation Treatment Plant Pkg 140 | 9511044.5002 | 7608835.6002 | 680 | Water be treated m3/ hour For 16 hours / day | 17.88 | Unit | $
Mivida Irrigation Treatment Plant Pkg 140 | 9511044.5002 | 7608835.6002 | 10600 | Tank Volume m3 | 17.88 | Unit | $
Multi Sports Hall | 73755377.9963 | 70067609.0965 | 15000 | Chair | 16.27 | Unit | $
EGAT | 3840834.6558 | 3314535.0642 |  |  | 17.14 | Unit | $
Abou Ghazala Bridge Ramp L&L | 95989.369 | 85941.9557 |  |  | 17.59 | Unit | $
Mohamed Ali Fahmy Ramps L&L | 406463.8999 | 381648.9483 |  |  | 17.59 | Unit | $
El Mosheer Bridge Abu Zaied Khdr L&L | 233928.0467 | 111390.3172 |  |  | 17.97 | Unit | $
Ora Zed Park L&L | 64077.5661 | 46601.8605 |  |  | 16.27 | Unit | $
DoubleTree Mangroovy El Gouna Hotel | 3541204.8557 | 3328732.5643 |  |  | 16.35 | Unit | $
Baron Palace Fence | 992082.6911 | 882848.162 |  |  | 16.35 | Unit | $
Safeer Square Bridge | 5837097.7982 | 5071993.3333 |  |  | 16.35 | Unit | $
Suez Road Tunnel Res L&L | 270556.0856 | 291737.5535 |  |  | 16.35 | Unit | $
HyperOne Zayed Extention | 8210434.5421 | 6091367.6979 | 510 | Parking Capacity | 16.27 | Unit | $
IKEA Extention MoA | 12058427.7812 | 13053526.0602 |  |  | 16.27 | Unit | $
CFC Podium II | 35815002.8201 | 29570795.9977 | 300 | Offices | 17.73 | Unit | $
Mostafa Kamel Bridge L&L | 0 | 0 |  |  | 5.36 | Unit | $
Josef Tito Bridge L&L | 0 | 0 |  |  | 5.36 | Unit | $
Espiko Bridge L&L | 0 | 0 |  |  | 5.36 | Unit | $
El Gabal El Asfr Tunnel L&L | 0 | 0 |  |  | 5.36 | Unit | $
MR3 Bridge L&L | 93428.7031 | 84032.2065 |  |  | 16.27 | Unit | $
El Sewedy Univeristy 2 Phase 2 | 33502489.9605 | 28812141.3424 | 900 | People Served | 17.97 | Unit | $
Mehwar El Salam Axis L&L | 1035219.8525 | 969630.1782 |  |  | 16.27 | Unit | $
El Hegaz Square Bridge | 8504612.7843 | 7484484.5114 |  |  | 16.27 | Unit | $
Marina Inland Marassi Pkg 162 | 26575172.8702 | 21711916.235 |  |  | 16.35 | Unit | $
Sultana Malek Restoration | 5335844.3189 | 4535467.6711 |  |  | 15.93 | Unit | $
Lekela 250MW Wind Farm | 10731902.4706 | 10517264.4212 | 250 | MW | 17 | Unit | $
New Giza Hospital | #DIV/0! | #DIV/0! | 164 | bed | 0 | Unit | $
Kayan Landscape | 5976263.3214 | 5559179.8875 |  |  | 16.74 | Unit | $
Abbas Akkad Bridge | 7592206.7861 | 7514973.822 |  |  | 16.35 | Unit | $
El Asher Men Ramadan Bridge | 5743752.5994 | 5243568.9126 |  |  | 16.35 | Unit | $
Kafr Shokr Bridge | 9280936.9115 | 8410206.2775 |  |  | 15.93 | Unit | $
Al Shorouk Bridge (LRT) | 1680320.1799 | 1553984.5758 |  |  | 15.56 | Unit | $
GOV2 Infra | 38235294.1176 | 35750000 | 1500 | ACRE | 17 | Unit | $
Cairo Alex Railroad | 61553150.8593 | 56013367.282 | 35 | KM RAIL | 15.71 | Unit | $
Hassan El Mamoun Bridge | 5517647.0588 | 5220981.7045 |  |  | 17 | Unit | $
Sherouk Bridge L&L | 186567.1642 | 307486.6592 |  |  | 5.36 | Unit | $
Ora Zed Park 1B Pkgs A&D | 55291811.1817 | 51393738.4343 | 320 | no of apr | 15.74 | Unit | $
Kattameya Creeks | 92297979.798 | 85375631.3131 |  |  | 15.84 | Unit | $
Mansoura University Faculty of Medicine | 13828763.8288 | 12860750.3608 |  |  | 15.84 | Unit | $
Diplomatic District - Infra | 24621212.1212 | 23020833.3333 | 1600 | ACRE | 15.84 | Unit | $
El Sewedy CFC HQ Internal Finishing | 20913730.2702 | 19295962.0932 |  |  | 15.67 | Unit | $
Lagoon Discharge Pkg 178 | 2581317.1666 | 2239034.5103 |  |  | 15.67 | Unit | $
El Khatatba Bridge | #DIV/0! | #DIV/0! |  |  | 0 | Unit | $
EGAT Pelletizing Plant | #DIV/0! | #DIV/0! |  |  | 0 | Unit | $
Sokhna Port Expansion | #DIV/0! | #DIV/0! | 12 | KM | 0 | Unit | $
MDF Factory | 11125238.398 | 10346471.7101 |  |  | 15.73 | Unit | $
Olympic City L&L | 0 | 0 |  |  | 5.36 | Unit | $
Kemet Building | 4540091.2824 | 4222284.8927 |  |  | 15.65 | Unit | $
Point 90 New Cairo Mall | 21419634.517 | 19086540.1725 | 75 | No of Shops | 6.77 | Unit | $
Marassi Bridges Pkg 37 | 4301122.6076 | 4487783.6449 |  |  | 6.09 | Unit | $
Marassi Golf Maintance Building Pkg 58 | 697253.3604 | 779199.6896 |  |  | 6.77 | Unit | $
Uptown Soil Stabilization Pkg 32 | 2860615.0739 | 3456795.3226 |  |  | 6.09 | Unit | $
Ismailia Bridge L&L | 3085112.8554 | 0 |  |  | 16.04 | Unit | $
El Obour Bridge B2 | 1258741.2587 | 1006993.007 |  |  | 7.15 | Unit | $
Autoville Strip Mall | 9528476.4925 | 10308954.8507 |  |  | 5.36 | Unit | $
Uptown Service Buildings Pkg 17A | 9877372.9682 | 9513008.7608 |  |  | 5.66 | Unit | $
Sodic West Town Hub | 8000135.9542 | 8292118.5111 |  |  | 6.77 | Unit | $
Dubai Port Sokhna Basin 1 | 5103150.8552 | 4134427.1025 |  |  | 6.77 | Unit | $
Alexandria Bridges | 6639902.3321 | 5366877.2388 | 630 | m | 5.36 | Unit | $
El Mahala Bridge | 9404951.3287 | 6731025.4545 |  |  | 7.15 | Unit | $
El Wahat Bridge | 2878790.9436 | 2303032.7549 | 35 | m | 7.83 | Unit | $
El Wahat Tunnel | 2403322.5134 | 1778286.2889 | 60 | m | 7.83 | Unit | $
AL-Asmarat | 928230.9091 | 1191209.8207 |  |  | #N/A | Unit | $
Alegria DP Port | 34163228.3136 | 28091334.0102 |  |  | 17.73 | Unit | $
El Alameen Bridge L&L | 0 | 0 |  |  | 5.36 | Unit | $
El Asher of Ramadan Bridge L&L | 0 | 0 |  |  | 5.36 | Unit | $
EMEC | 1823972.884 | 1519977.4033 |  |  | 5.86 | Unit | $
Ismailia Bridge L&L | 0 | 0 |  |  | 16.04 | Unit | $
Logestica Phase 01 | 5273558.0479 | 4585702.6504 |  |  | 6.05 | Unit | $
Logestica Phase 02 | 3054862.9247 | 2373632.8671 |  |  | 6.77 | Unit | $
Logestica Phase 03 | 712032.644 | 543778.8774 |  |  | 6.77 | Unit | $
Sodic MV Cables | 2739792.7273 | 2291557.601 |  |  | 7.15 | Unit | $
Limak TB2 Cairo Airport Terminal | 17670139.4387 | 14291810.6352 |  |  | 6.77 | Unit | $
Twin Towers | 11940298.5504 | 11887019.0237 |  |  | 5.36 | Unit | $
Aeon Towers Chiller Building | 0 | 0 |  |  | 16.31 | Unit | $
Electric Train LRT | 0 | 0 |  |  | 17.89 | Unit | $
Sea Shell Playa | 0 | 0 |  |  | 15.84 | Unit | $
Marassi Civic Center Pkg 45 | 9348278.4893 | 10633538.1369 | 6743 | m2 | 6.09 | area | $
Al Oula Infra | 11978069.9442 | 10851774.8114 |  | m2 | 6.09 | area | $
New Giza Phase 01 | 24086265.1805 | 24295949.4161 | 16200 | m2 | 7.15 | area | $
Hyper Solimanya | 15447578.2685 | 15199861.3951 | 10871 | m2 | 7.15 | area | $
Ismailia Bridges | 6365722.6351 | 3822996.3883 | 6309 | m2 | 8.88 | area | $
Maxium Mall | 13786937.0629 | 14669789.3763 | 70000 | m2 | 7.15 | area | $
Ataqqa Power Plant | 25788528.7846 | 13676451.1797 |  | m2 | 7.15 | area | $
Mall of Egypt Bridge | 23430372.3665 | 21101862.2332 | 1553 | m2 | 7.83 | area | $
Marassi Tanks PKG 22 | 3027646.9622 | 2734898.2841 |  | m2 | 6.09 | area | $
Sodic Club House | 20588539.719 | 21652257.915 | 20000 | m2 | 7.83 | area | $
Montazah Hotel Sharm | 4725104.2695 | 4248109.4825 | 16580 | m2 | 7.15 | area | $
Uptown Cairo Pkg 53 | 40203002.682 | 43961965.1341 | 63752 | m2 | 7.83 | area | $
Bani Suif Power Plant 1021 | 54609717.3359 | 40865034.1997 |  | m2 | 7.83 | area | $
New Giza Phase 02 | 19877812.2299 | 20633994.8664 | 16200 | m2 | 7.83 | area | $
JICA Wind Farm Gabal El Zeet | 15387397.1775 | 10493589.9379 |  | m2 | 7.83 | area | $
El Mostathmereen Mokatam Substation | 15309152.5366 | 9606522.5558 |  | m2 | 8.87 | area | $
Levana UpTown PKG 62 | 5328733.7838 | 5920596.3312 | 22213.8 | m2 | 8.88 | area | $
Kayan 110 | 186745807.4126 | 182701319.8032 | 152000 | m2 | 7.15 | area | $
El Amal Bridge | 3696443.295 | 2708923.3713 | 2520 | m2 | 7.83 | area | $
Bani Suif Cement | 30965467.8692 | 29933758.7525 |  | m2 | 8.87 | area | $
New Giza Wall | 338230.0096 | 135029.0243 |  | m2 | 7.83 | area | $
Tamey El Amdid Mansora Power Station | 6337930.1939 | 5144257.6898 |  | m2 | 18.05 | area | $
Ismailia Substation 500-220 | 6060921.8837 | 5239610.7845 | 15000 | m2 | 18.05 | area | $
El Amal Bridge L&L | 510164.5998 | 357115.2198 |  | m2 | 17.74 | area | $
FIEM Wind Farm Gabal El Zeet | 8179017.9256 | 4868360.2387 |  | m2 | 8.87 | area | $
KFW Wind Farm Gabal El Zeet | 2597326.7802 | 1480192.052 |  | m2 | 8.87 | area | $
Marassi Tank PKG 107 | 7661138.8811 | 5987475.3822 | 0 | m2 | 7.15 | area | $
Ben Zayed New Capital Tunnel | 19075425.2281 | 15067340.8947 | 18596 | m2 | 18 | area | $
Ministries Buildings | 152253900 | 147952076.2778 | 169000 | m2 | 18 | area | $
Bani Suif Substation | 6687657.1191 | 5601389.2521 | 29643 | m2 | 18.05 | area | $
Royal City Mall | 29118111.6022 | 27775747.6922 | 25379 | m2 | 18.1 | area | $
Shoubra Banha Bridge L&L | 219125.8503 | 82829.6485 | 4000 | m2 | 17.64 | area | $
SLP Logistic Center PI Park Sewedy Stores | 5442127.7008 | 4778929.0376 | 13000 | m2 | 18.05 | area | $
El Mostakbal Bridge L&L | 247874.3978 | 115559.944 | 4286.7 | m2 | 17.85 | area | $
Kayan Wall L&L | 6079099.8308 | 4680830.9081 |  | m2 | 17.73 | area | $
Elco Suez Steel Rolling Mill Plant 3 | 23448905.2809 | 16414667.1037 |  | m2 | 17.8 | area | $
Hyper El Temsah | 9424207.5266 | 7901423.5863 | 7800 | m2 | 17.93 | area | $
Marassi Bridge Pkg 117 | 2549679.5262 | 1754752.1151 | 1080 | m2 | 17.73 | area | $
Siemens Power Station | 18773627.1292 | 18039820.2112 | 16200 | m2 | 17.73 | area | $
Uptown FM85 Pkg 85 | 0 | 0 |  | m2 | 17.91 | area | $
El Sokhna Tunnel 01 | 2629059.3574 | 2123747.9143 | 3604 | m2 | 17.74 | area | $
Abu Sultan Bridge 01 | 1061890.487 | 776057.8143 | 1738 | m2 | 17.66 | area | $
Mintra Factory | 6315999.2108 | 6376879.417 | 52500 | m2 | 17.74 | area | $
King Farouk Restoration | 0 | 0 |  | m2 | 17.66 | area | $
Mohamed Ali Palace | 8493771.2344 | 7114519.2539 |  | m2 | 17.66 | area | $
Nefisha Bridge | 3969115.7247 | 2877455.568 | 6900 | m2 | 17.87 | area | $
Fish Market | 3691336.7859 | 3237703.3251 | 6400 | m2 | 17.93 | area | $
Al Jazi Mall | 13764820.7684 | 12786144.1222 | 48853.59 | m2 | 17.87 | area | $
Benban Aswan Alcazars Solar Park | 11824081.6509 | 6616904.6291 |  | m2 | 17.93 | area | $
El Alameen Roads Earth Works | 3030920.4139 | 2572814.2617 |  | m2 | 17.88 | area | $
El Sewedy Univeristy | 14600936.1157 | 12965406.6476 | 14500 | m2 | #N/A | area | $
El Sokhna Tunnel L&L | 0 | 0 |  | m2 | 5.36 | area | $
R05 Residential District Z1 & Z2 | 178471834.9136 | 165978806.4696 | 618237 | m2 | 17.93 | area | $
Abu Sultan Bridge 02 Greenhouse | 3810776.153 | 3346821.4109 | 476 | m2 | 17.78 | area | $
El Sokhna Tunnel 02 | 1244935.8974 | 983722.7982 | 1813 | m2 | 17.94 | area | $
El Awsty Middle Tunnel L&L | 63495.6629 | 0 |  | m2 | 16.14 | area | $
Sodic Eastown EDNC | 61088406.3104 | 57423101.9318 | 156000 | m2 | 17.59 | area | $
Marassi Civic Center Pkg 144 | 9950387.7609 | 6894490.6588 | 12500 | m2 | 17.73 | area | $
DPW Sokhna Dubai Port | 91348737.4161 | 69715164.6921 | 600000 | m2 | 17.88 | area | $
Slope Stablization PKG 101 | 2896886.7324 | 2635877.2378 | 11305 | m2 | 17.96 | area | $
Elco Steel Substation | 1799764.7746 | 1936460.5886 |  | m2 | 17.97 | area | $
Sewab Greenhouse Tunnel | 616299.9902 | 541266.6396 | 476 | m2 | 17.78 | area | $
Mivida Irrigation Treatment Plant Pkg 140 | 9511044.5002 | 7608835.6002 | 12350 | m2 | 17.88 | area | $
Mivida Irrigation Treatment Plant Pkg 140 | 9511044.5002 | 7608835.6002 | 12350 | m2 | 17.88 | area | $
Multi Sports Hall | 73755377.9963 | 70067609.0965 | 18000 | m2 | 16.27 | area | $
EGAT | 3840834.6558 | 3314535.0642 |  | m2 | 17.14 | area | $
Abou Ghazala Bridge Ramp L&L | 95989.369 | 85941.9557 |  | m2 | 17.59 | area | $
Mohamed Ali Fahmy Ramps L&L | 406463.8999 | 381648.9483 |  | m2 | 17.59 | area | $
El Mosheer Bridge Abu Zaied Khdr L&L | 233928.0467 | 111390.3172 |  | m2 | 17.97 | area | $
Ora Zed Park L&L | 64077.5661 | 46601.8605 |  | m2 | 16.27 | area | $
DoubleTree Mangroovy El Gouna Hotel | 3541204.8557 | 3328732.5643 | 18352 | m2 | 16.35 | area | $
Baron Palace Fence | 992082.6911 | 882848.162 |  | m2 | 16.35 | area | $
Safeer Square Bridge | 5837097.7982 | 5071993.3333 | 6750 | m2 | 16.35 | area | $
Suez Road Tunnel Res L&L | 270556.0856 | 291737.5535 |  | m2 | 16.35 | area | $
HyperOne Zayed Extention | 8210434.5421 | 6091367.6979 | 30000 | m2 | 16.27 | area | $
IKEA Extention MoA | 12058427.7812 | 13053526.0602 | 19836 | m2 | 16.27 | area | $
CFC Podium II | 35815002.8201 | 29570795.9977 | 98633 | m2 | 17.73 | area | $
Mostafa Kamel Bridge L&L | 0 | 0 |  | m2 | 5.36 | area | $
Josef Tito Bridge L&L | 0 | 0 |  | m2 | 5.36 | area | $
Espiko Bridge L&L | 0 | 0 |  | m2 | 5.36 | area | $
El Gabal El Asfr Tunnel L&L | 0 | 0 |  | m2 | 5.36 | area | $
MR3 Bridge L&L | 93428.7031 | 84032.2065 |  | m2 | 16.27 | area | $
El Sewedy Univeristy 2 Phase 2 | 33502489.9605 | 28812141.3424 | 38447 | m2 | 17.97 | area | $
Mehwar El Salam Axis L&L | 1035219.8525 | 969630.1782 |  | m2 | 16.27 | area | $
El Hegaz Square Bridge | 8504612.7843 | 7484484.5114 | 9450 | m2 | 16.27 | area | $
Ring Road | 32048929.6636 | 30125993.8838 | 63600 | m2 | 16.35 | area | $
Marina Inland Marassi Pkg 162 | 26575172.8702 | 21711916.235 |  | m2 | 16.35 | area | $
Sultana Malek Restoration | 5335844.3189 | 4535467.6711 |  | m2 | 15.93 | area | $
Lekela 250MW Wind Farm | 10731902.4706 | 10517264.4212 |  | m2 | 17 | area | $
New Giza Hospital | #DIV/0! | #DIV/0! | 23000 | m2 | 0 | area | $
Kayan Landscape | 5976263.3214 | 5559179.8875 |  | m2 | 16.74 | area | $
Abbas Akkad Bridge | 7592206.7861 | 7514973.822 | 15600 | m2 | 16.35 | area | $
El Asher Men Ramadan Bridge | 5743752.5994 | 5243568.9126 | 4200 | m2 | 16.35 | area | $
Kafr Shokr Bridge | 9280936.9115 | 8410206.2775 | 16900 | m2 | 15.93 | area | $
Al Shorouk Bridge (LRT) | 1680320.1799 | 1553984.5758 | 7070 | m2 | 15.56 | area | $
GOV2 Infra | 38235294.1176 | 35750000 |  | m2 | 17 | area | $
Cairo Alex Railroad | 61553150.8593 | 56013367.282 |  | m2 | 15.71 | area | $
Hassan El Mamoun Bridge | 5517647.0588 | 5220981.7045 | 13440 | m2 | 17 | area | $
Sherouk Bridge L&L | 186567.1642 | 307486.6592 |  | m2 | 5.36 | area | $
Ora Zed Park 1B Pkgs A&D | 55291811.1817 | 51393738.4343 | 75500 | m2 | 15.74 | area | $
Kattameya Creeks | 92297979.798 | 85375631.3131 | 140150 | m2 | 15.84 | area | $
Mansoura University Faculty of Medicine | 13828763.8288 | 12860750.3608 | 40000 | m2 | 15.84 | area | $
Diplomatic District - Infra | 24621212.1212 | 23020833.3333 |  | m2 | 15.84 | area | $
El Sewedy CFC HQ Internal Finishing | 20913730.2702 | 19295962.0932 | 23500 | m2 | 15.67 | area | $
Lagoon Discharge Pkg 178 | 2581317.1666 | 2239034.5103 |  | m2 | 15.67 | area | $
El Khatatba Bridge | #DIV/0! | #DIV/0! | 9940 | m2 | 0 | area | $
EGAT Pelletizing Plant | #DIV/0! | #DIV/0! |  | m2 | 0 | area | $
Sokhna Port Expansion | #DIV/0! | #DIV/0! |  | m2 | 0 | area | $
MDF Factory | 11125238.398 | 10346471.7101 | 23710 | m2 | 15.73 | area | $
Olympic City L&L | 0 | 0 |  | m2 | 5.36 | area | $
Kemet Building | 4540091.2824 | 4222284.8927 | 21460 | m2 | 15.65 | area | $
Point 90 New Cairo Mall | 21419634.517 | 19086540.1725 | 69132.17 | m2 | 6.77 | area | $
Marassi Bridges Pkg 37 | 4301122.6076 | 4487783.6449 |  | m2 | 6.09 | area | $
Marassi Golf Maintance Building Pkg 58 | 697253.3604 | 779199.6896 |  | m2 | 6.77 | area | $
Uptown Soil Stabilization Pkg 32 | 2860615.0739 | 3456795.3226 |  | m2 | 6.09 | area | $
Ismailia Bridge L&L | 3085112.8554 | 0 |  | m2 | 16.04 | area | $
El Obour Bridge B2 | 1258741.2587 | 1006993.007 | 735 | m2 | 7.15 | area | $
Autoville Strip Mall | 9528476.4925 | 10308954.8507 |  | m2 | 5.36 | area | $
Uptown Service Buildings Pkg 17A | 9877372.9682 | 9513008.7608 |  | m2 | 5.66 | area | $
Sodic West Town Hub | 8000135.9542 | 8292118.5111 |  | m2 | 6.77 | area | $
Dubai Port Sokhna Basin 1 | 5103150.8552 | 4134427.1025 |  | m2 | 6.77 | area | $
Alexandria Bridges | 6639902.3321 | 5366877.2388 | 9135 | m2 | 5.36 | area | $
El Mahala Bridge | 9404951.3287 | 6731025.4545 | 7830 | m2 | 7.15 | area | $
El Wahat Bridge | 2878790.9436 | 2303032.7549 | 735 | m2 | 7.83 | area | $
El Wahat Tunnel | 2403322.5134 | 1778286.2889 | 3000 | m2 | 7.83 | area | $
AL-Asmarat | 928230.9091 | 1191209.8207 |  | m2 | #N/A | area | $
Alegria DP Port | 34163228.3136 | 28091334.0102 |  | m2 | 17.73 | area | $
El Alameen Bridge L&L | 0 | 0 |  | m2 | 5.36 | area | $
El Asher of Ramadan Bridge L&L | 0 | 0 |  | m2 | 5.36 | area | $
EMEC | 1823972.884 | 1519977.4033 |  | m2 | 5.86 | area | $
Ismailia Bridge L&L | 0 | 0 |  | m2 | 16.04 | area | $
Logestica Phase 01 | 5273558.0479 | 4585702.6504 |  | m2 | 6.05 | area | $
Logestica Phase 02 | 3054862.9247 | 2373632.8671 |  | m2 | 6.77 | area | $
Logestica Phase 03 | 712032.644 | 543778.8774 |  | m2 | 6.77 | area | $
Sodic MV Cables | 2739792.7273 | 2291557.601 |  | m2 | 7.15 | area | $
Limak TB2 Cairo Airport Terminal | 17670139.4387 | 14291810.6352 |  | m2 | 6.77 | area | $
Twin Towers | 11940298.5504 | 11887019.0237 |  | m2 | 5.36 | area | $
Aeon Towers Chiller Building | 0 | 0 |  | m2 | 16.31 | area | $
Electric Train LRT | 0 | 0 |  | m2 | 17.89 | area | $
Sea Shell Playa | 0 | 0 |  | m2 | 15.84 | area | $
| 31379002902 |  | 3132984
10015.692