## needed
item | value | note
revised boq
latest invoice
% of marksup without risk
project start month
cost dist month
project finish month
matksup to date cost | 0 | = % marksup x latest invoice
marksup at completion | 0 | = % marksup x revised boq
marksup cost dist |  | less than marksup to date cost
marksup cash | 0 | = same as marksup cost dist

## budget_cost
work_package | actual_cost | eac | start month | finish month | remaining_cost | remaining_duration_months
Excavation | 1481132 | 3369576 |  |  | 1888444 | 0
Backfill | 2067745 | 2645733 |  |  | 577988 | 0
Demolish | 7271 | 259456 |  |  | 252185 | 0
Piles | 45840449 | 50668906 |  |  | 4828457 | 0
Formwork | 15631794 | 48244250 |  |  | 32612456 | 0
Steel Rft. | 96911824 | 296215615 |  |  | 199303791 | 0
Concrete | 30047668 | 97722844 |  |  | 67675176 | 0
Post Tension | 1157750 | 51007583 |  |  | 49849833 | 0
Joints | 0 | 29027778 |  |  | 29027778 | 0
Insulation | 54533 | 2564072 |  |  | 2509539 | 0
Paint | 161397 | 5001397 |  |  | 4840000 | 0
Bearings | 0 | 76105856 |  |  | 76105856 | 0
Plumbing Works | 0 | 1488010 |  |  | 1488010 | 0
Electrical Works | 262464 | 2820009 |  |  | 2557545 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
2 - Indirect Cost |  |  | 0 | 0 | 0 | 0
3- Taxes And Insurance |  |  | 1900-03-02 | 1900-03-02 | 0 | 2.0667
Formulas:
start month = [start month, row above]+62
finish month = [finish month, row above]+62