# CONTRACTOR DAILY REPORT (CDR)

| Project Name : EIPICO 3, Biologicals and Biosimilars Manufacturing Facility. Project No. : 1250 Employer : EIPICO |  |  |  | Package : EIPICO 3 Phase : EIPICO 3 Contractor: ROWAD MODERN Engineering |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Site Supervision Consultant: EHAF Consulting Engineers |  |  |  |  |  |  |  |
| From : ROWAD MODERN Engineering To : EGYCAN Attn. : Eng. Ibrahim Tawfik |  |  |  | Date : 19/11/2023 Ref. : 1250/CDR/RME/EGYCAN/2023/310 Report No. : 310 |  |  |  |
| Weather Condition: |  |  |  |  |  |  |  |
| Clear | Windy | Cool |  |  | Overcast | Foggy |  |
| Worm | Rainy | Cold |  |  | Hot |  |  |
| Temprature Rang : ------------------------------------------------------------------------------------------------------- |  |  |  |  |  |  |  |
| Site Condition : -------------------------------------------------------------------------------------------------------- |  |  |  |  |  |  |  |
|  | Clear |  | Dusty |  | Muddy |  | Other |

| Activities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ID | location | On Site Activities Description | Planned Completion Date | Actual Completion Date | Commentary |
|  | B02 Ground Floor | Cont. installation of electrical conduits at level-1 |  |  |  |
|  | B02 Gr floor | Installation of galvanized ducts- GR floor |  |  |  |
|  | B2-level 01 | Installation of Fire Fighting Pipes at B02- level 01 |  |  |  |
|  | B01 Risers | Cont. installation of drainage pipes at B01-risers |  |  |  |
|  | B02 1st floor | Installation of galvanized ducts- 1st floor |  |  |  |
|  | B4 | Installation of chilled works at B04 |  |  |  |
|  | B01 GR floor | Cont. installation of electrical conduits at B01-Ground Floor |  |  |  |
|  | B02 1st floor | Cont. installation of Hangers & Support for cable trays |  |  |  |
|  | Utility | Plaster works - chiller |  |  |  |
|  | Utility | Boiler installation |  |  |  |
|  | Utility | Plaster - Facade |  |  |  |
|  | Transformer | Plaster – internal and facade |  |  |  |
|  | Warehouse | Blockwork GF |  |  |  |
|  | Warehouse | Plaster work GF |  |  |  |
|  | EIPICO 3 Overall | Documentation Works – (Preparing Transmittals, Reports…., etc.) |  |  |  |

| Equipment |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Name | Type | Model | Age | No | In use Hrs | Standby Hrs | Commentary |
| 1 | Total Station |  |  |  | 1 | Hrs |  |  |
| 2 | Level |  |  |  | 1 | Hrs |  |  |
| 3 | Generator 500 KVA |  |  |  | 2 | Hrs |  |  |
| 4 | Forklift |  |  |  | 2 | Hrs |  |  |
| 5 | Loader 36 (Teeth & Bucket) |  |  |  | 1 | Hrs |  |  |
| 6 | JCP |  |  |  | 1 | Hrs |  |  |
| 7 | Trailer (9m3) and tractor |  |  |  | 1 | Hrs |  |  |
| 8 | Mobile crane |  |  |  | 1 | Hrs |  |  |
| 9 | Pump |  |  |  | 1 | Hrs |  |  |
| 10 | Loader 66 |  |  |  | 2 | Hrs |  |  |

| Manpower |  |  |  |  |
| --- | --- | --- | --- | --- |
| ID | Trade / Position | No | Hours | Commentary |
| 1 | Project manager | 1 | 9 Hrs |  |
| 2 | Construction manager | 1 | 9 Hrs |  |
| 3 | Technical Office Team Leader | 1 | 9 Hrs |  |
| 4 | Civil engineer | 3 | 9 Hrs |  |
| 5 | Q.C. Engineer | 5 | 9 Hrs |  |
| 6 | Planning Engineer | 2 | 9 Hrs |  |
| 7 | Mechanical TO Manager | 1 | 9 Hrs |  |
| 8 | Mechanical Tech. Office Engineer | 1 | 9 Hrs |  |
| 9 | Electrical Tech. Office Engineer | 1 | 9 Hrs |  |
| 10 | Civil Tech. Office Engineer | 3 | 9 Hrs |  |
| 11 | Arch Tech. Office Engineer | 1 | 9 Hrs |  |
| 12 | BIM Coordinator | 1 | 9 Hrs |  |
| 13 | Supervisor | 5 | 9 Hrs |  |
| 14 | Document Controller | 3 | 9 Hrs |  |
| 15 | Safety Manager | 1 | 9 Hrs |  |
| 16 | Safety Officer | 4 | 9 Hrs |  |
| 17 | Accountant | 1 | 9 Hrs |  |
| 18 | Administrator | 1 | 9 Hrs |  |
| 19 | Survey Engineer | 1 | 9 Hrs |  |
| 20 | Surveyor | 6 | 9 Hrs |  |
| 21 | Security | 2 | 9 Hrs |  |
| 22 | Timekeeper | 1 | 9 Hrs |  |
| 23 | Electrician Assistant | 4 | 9 Hrs |  |
| 24 | Bobcat Driver | 1 | 9 Hrs |  |
| 25 | Storekeeper | 1 | 9 Hrs |  |
| 26 | Material Supervisor | 1 | 9 Hrs |  |
| 27 | Purchasing Officer | 1 | 9 Hrs |  |
| 28 | Lab Technician | 1 | 9 Hrs |  |
| 29 | Office Boy | 2 | 9 Hrs |  |
| 30 | Plumber | 2 | 9 Hrs |  |
| 31 | Drivers | 5 | 9 Hrs |  |
| 32 | Storekeeper Helper | 1 | 9 Hrs |  |
| 33 | Nurse | 1 | 9 Hrs |  |
|  | Total Indirect Manpower | 58 |  |  |
| 34 | Carpenters | 14 | 9 Hrs |  |
| 35 | Steel Fixer | 2 | 9 Hrs |  |
| 36 | Scaffolding Technician | 29 | 9 Hrs |  |
| 37 | Farmaga | 16 | 9 Hrs |  |
| 38 | Labors | 50 | 9 Hrs |  |
| 39 | Plaster | 55 | 9 Hrs |  |
| 40 | Sculptor | 7 | 9 Hrs |  |
| 41 | Masonry | 30 | 9 Hrs |  |
| 42 | Painter | 5 | 9 Hrs |  |
| 43 | Insulation Technician | 0 | 9 Hrs |  |
| 45 | Welders | 4 | 9 Hrs |  |
| 46 | Electricians | 30 | 9 Hrs |  |
| 47 | Plumber | 15 | 9 Hrs |  |
| 48 | Mechanicians | 51 | 9 Hrs |  |
| 49 | Tilling workers | 10 | 9 Hrs |  |
| 50 | Aluminum tech | 20 | 9 Hrs |  |
| 51 | Steel structure tech | 0 | 9 Hrs |  |
|  | Total direct Manpower | 388 |  |  |

| Total Direct Manpower |  | Planned As Per Approved Programme |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 338 |  |  |
| Materials |  |  |  |  |  |  |
| ID | Material description |  | Quantity on site | Quantity installed |  | Commentary |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |

| Tests/ Inspections |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ID | Material Description | Specs. Ref. | Drawings Ref. | Name Of Tester | Results | Commentary |
| 1 |  |  |  |  |  |  |

| Safety measures |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ID | Instructor Name | Title | Represents | Instruction Description | Commentary |
| 1 |  |  |  |  |  |

| Official Visitors Today |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Visitor Name | Title | Represents | Visit |  |  | Commentary |
|  |  |  |  | From |  | To |  |
| Area of Concern: |  |  |  |  |  |  |  |
| Nature of Exceptions / Defects (Include Specifications and / or Drawings Numbers, Location, Description): |  |  |  |  |  |  |  |
| Attachments : ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------ |  |  |  |  | ------------------------------------------- Contractor Authorized Representative Date ---------/-----------/------------- |  |  |

Progress Photos

Transformer

Utility

Warehouse