## eslam.data
project | Opr | invoice no. | Gross | Gross From ERP | Gross Cases | Collection | Collection from ERP | Collection Cases | dp amount | on account amount | other amount (comment) | Net | invoice month | cut off date | submittal date | duration of pay | pay due date | approval_date | cummulative amount approved | material on site cummulative amount approved | v.o. cummulative amount approved | ncr cummulative amount approved | escalation cummulative amount approved | 1st retention cummulative amount approved | 2nd retention cummulative amount approved | total deductions | consultant gross | consultant gross cumulative | consultant net | project name in invoicing | Notes | Gross - Material on Site (both eslam) | Gross Cases (MOS Deducted) | concact eslam name with invoice no | concat invoicing name with invoice no
6TH October tunnel | 2 | 1 | 842930 | 1605581.42 | 762651.42 | 1520548 | 1520548 | 0 |  |  |  | 1520548 | 2022-05-31 | 2022-06-08 | 2022-06-15 | 60 | 2022-08-14 | 2022-09-11 | 842930 | 1367190 | [5 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel1 | October Under-Railway Tunnel1
6TH October tunnel | 2 | 2 | 3756426.15 | 8760678.38 | 5004252.23 | 3508372.9 | 3508352.9 | -20 |  |  |  | 3208372.9 | 2022-07-31 | 2022-08-10 | 2022-08-21 | 60 | 2022-10-20 | 2022-09-25 | 4599356.15 | 921846.75 | [5 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel2 | October Under-Railway Tunnel2
6TH October tunnel | 2 | 3 |  | 5911928.1 | 5911928.1 | 0.001 | 5155347.1955 | 5155347.1945 |  |  |  |  | 2022-08-31 | 2022-09-06 | 2022-09-07 | 60 | 2022-11-06 | [8 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel3 | October Under-Railway Tunnel3
6TH October tunnel | 2 | 4 | 7050454.75 | 0 | -7050454.75 | 5155347 | 0 | -5155347 |  |  |  | 5155347.5 | 2022-09-30 | 2022-10-01 | 2022-11-13 | 60 | 2023-01-12 | 2022-11-14 | 11649810.9 | 750750 | [5 empty] | 0 | 7663602.64 | 12262958.79 | 3604450.6683 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel4 | October Under-Railway Tunnel4
6TH October tunnel | 2 | 5 | 3846689.4 | 3663513.71 | -183175.69 | 2856009 | 2856009 | 0 |  |  |  | 3524900.34 | 2022-10-31 | 2022-11-15 | 2022-11-17 | 60 | 2023-01-16 | 2022-11-25 | 15496500.3 | 298295 | [5 empty] | 0 | 6157467.55 | 17807278.45 | 3524900.34 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel5 | October Under-Railway Tunnel5
6TH October tunnel | 2 | 6 | 1899766.7 | 1809302.29 | -90464.41 | 1337162.6 | 1337162.5545 | -0.0455 |  |  |  | 1337162.6 | 2022-12-31 | 2022-12-15 | 2023-01-09 | 60 | 2023-03-10 | 2023-02-12 | 17396267 | [6 empty] | 0 | 0 | 0 | 0 | October Under-Railway Tunnel |  |  |  | 6TH October tunnel6 | October Under-Railway Tunnel6
Abo Ghaleb Bridge | 2 | 1 |  | 1116000 | 1116000 | 175270.85 | 1007589.6 | 832318.75 |  |  |  |  | 2022-01-31 | 2022-01-31 | 2022-02-03 | 60 | 2022-04-04 | [8 empty] | 0 | 0 | 0 | 0 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge1 | Abo Ghaleb1
Abo Ghaleb Bridge | 2 | 2 | 3079766.7 | 1428000 | -1651766.7 | 2494611.027 | 142483.6 | -2352127.427 |  |  |  | 2494611.027 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 15845653.7 | [6 empty] | 0 | 3079766.7 | 15845653.7 | 2494611.027 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge2 | Abo Ghaleb2
Abo Ghaleb Bridge | 2 | 3 | 3857104.5 | 0 | -3857104.5 | 2045810.923 | 0 | -2045810.923 |  |  |  | 3124254.645 | 2022-03-31 | 2022-03-31 | 2022-04-04 | 60 | 2022-06-03 | 2022-04-04 | 19702758.2 | [6 empty] | 0 | 3857104.5 | 19702758.2 | 3124254.645 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge3 | Abo Ghaleb3
Abo Ghaleb Bridge | 2 | 4 | 17739438 | 0 | -17739438 | 12711007.22 | 0 | -12711007.22 |  |  |  | 6555212.9406 | 2022-04-30 | 2022-04-30 | 2022-04-15 | 60 | 2022-06-14 | 2022-08-09 | 37442196.2 | [6 empty] | 0 | 17739438 | 37442196.2 | 6555212.9406 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge4 | Abo Ghaleb4
Abo Ghaleb Bridge | 2 | 5 | 2031888 | 0 | -2031888 | 1645829.28 | 0 | -1645829.28 |  |  |  | 1645829.28 | 2022-07-31 | 2022-07-31 | 2022-08-21 | 60 | 2022-10-20 | 2022-08-21 | 39474084.2 | [6 empty] | 0 | 2031888 | 39474084.2 | 1645829.28 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge5 | Abo Ghaleb5
Abo Ghaleb Bridge | 2 | 6 |  | 0 | 0 | 0.0001 | 0 | -0.0001 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 | [8 empty] | 0 | 0 | 0 | 0 | Abo Ghaleb |  |  |  | Abo Ghaleb Bridge6 | Abo Ghaleb6
AEON | 0 | 1 | 1325211.2762 | 0 | -1325211.2762 | 1264914.16 | 0 | -1264914.16 |  |  |  | 1264914.16 | 2020-09-30 | 2020-09-16 | 2020-09-20 | 56 | 2020-11-15 | 2020-09-22 | 1325211.2762 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | AEON1 | 01
AEON | 0 | 2 | 1613181.4 | 0 | -1613181.4 | 1513146.56 | 0 | -1513146.56 |  |  |  | 1513146.56 | 2020-10-31 | 2020-11-03 | 2020-11-03 | 56 | 2020-12-29 | 2020-12-15 | 2938392.6762 | [6 empty] | 0 | 1300835.2032 | 2626046.4794 | 1610113.5212 | 0 |  |  |  | AEON2 | 02
AEON | 0 | 3 | 799158.9955 | 0 | -799158.9955 | 780253.07 | 0 | -780253.07 |  |  |  | 780253.0677 | 2020-12-31 | 2020-12-20 | 2020-12-21 | 56 | 2021-02-15 | 2021-01-04 | 3737551.6717 | 20153.7514 | [5 empty] | 27500 | 799158.9955 | 3737551.6717 | 780253.0677 | 0 |  |  |  | AEON3 | 03
AEON | 0 | 4 |  | 0 | 0 | 484406.35 | 0 | -484406.35 |  |  |  |  | 2021-02-28 | 2021-02-28 | 2021-06-24 | 56 | 2021-08-19 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | AEON4 | 04
Al Jazi | 1 | 1 | 9888666.63 | 278661 | -9610005.63 | 55324495 | 230795 | -55093700 | 53125000 |  |  | 2199496 | 2018-04-30 | 2018-05-21 | 2018-05-21 | 15 | 2018-06-05 | 2018-06-03 | 9888666.63 | 0 | [5 empty] | 5395000 | 9888666.63 | 9888666.63 | 2462056.64 | Aljazi Project |  |  |  | Al Jazi1 | Aljazi Project1
Al Jazi | 1 | 2 | 6959342.1 | 322383 | -6636959.1 | 2330066 | 151797.77 | -2178268.23 |  |  |  | 2330066 | 2018-05-31 | 2018-06-05 | 2018-06-07 | 15 | 2018-06-22 | 2018-06-26 | 16848008.73 | 0 | [5 empty] | 8409664 | 6959342.1 | 16848008.73 | 3686157.94 | Aljazi Project |  |  |  | Al Jazi2 | Aljazi Project2
Al Jazi | 1 | 3 | 6863084.68 | 121070 | -6742014.68 | 3090062.9 | 58174.3 | -3031888.6 |  |  |  | 3357056.9 | 2018-06-30 | 2018-07-04 | 2018-07-07 | 15 | 2018-07-22 | 2018-07-25 | 23711093.41 | 0 | [5 empty] | 10989780.0001 | 6863158.19 | 23711166.92 | 3748572.21 | Aljazi Project |  |  |  | Al Jazi3 | Aljazi Project3
Al Jazi | 1 | 4 | 6873217.27 | 0 | -6873217.27 | 3867947.36 | 0 | -3867947.36 |  |  |  | 3867947.36 | 2018-07-31 | 2018-07-24 | 2018-07-24 | 15 | 2018-08-08 | 2018-07-29 | 30584310.68 | 0 | [5 empty] | 12001158.5 | 6873307.38 | 30584400.79 | 4444997.23 | Aljazi Project |  |  |  | Al Jazi4 | Aljazi Project4
Al Jazi | 1 | 5 | 7893070.92 | 0 | -7893070.92 | 4039155 | 0 | -4039155 |  |  |  | 4039155 | 2018-07-31 | 2018-08-08 | 2018-08-11 | 15 | 2018-08-26 | 2018-08-30 | 38477381.6 | 1152162.9504 | [5 empty] | 15549196.5 | 7893373.579 | 38477684.259 | 4854984.5363 | Aljazi Project |  |  |  | Al Jazi5 | Aljazi Project5
Al Jazi | 1 | 6 | 4850391.56 | 0 | -4850391.56 | 2383592 | 0 | -2383592 |  |  |  | 2965400.21 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 15 | 2018-09-21 | 2018-09-10 | 43327773.16 | 1152162.95 | [5 empty] | 16838621.5 | 4850391.56 | 43327773.16 | 2965400.21 | Aljazi Project |  |  |  | Al Jazi6 | Aljazi Project6
Al Jazi | 1 | 7 | 9360993.26 | 0 | -9360993.26 | 4138160 | 0 | -4138160 |  |  |  | 4138160 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 15 | 2018-10-17 | 2018-10-16 | 52688766.42 | 782387 | [5 empty] | 19429378.5 | 9361764.45 | 52689537.61 | 5019788.5 | Aljazi Project |  |  |  | Al Jazi7 | Aljazi Project7
Al Jazi | 1 | 8 | 13305889.63 | 0 | -13305889.63 | 6905844.19 | 0 | -6905844.19 |  |  |  | 7730375.21 | 2018-10-31 | 2018-10-28 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-06 | 65994656.05 | 684096.75 | [5 empty] | 22966415.34 | 13305889.63 | 65994656.05 | 7730375.21 | Aljazi Project |  |  |  | Al Jazi8 | Aljazi Project8
Al Jazi | 1 | 9 | 11249079.12 | 0 | -11249079.12 | 1762571 | 0 | -1762571 |  |  |  | 3297350.06 | 2018-11-30 | 2018-11-19 | 2018-11-19 | 15 | 2018-12-04 | 2018-11-28 | 77243735.17 | 504071.29 | [5 empty] | 28710343.34 | 11249079.12 | 77243735.17 | 3297350.06 | Aljazi Project |  |  |  | Al Jazi9 | Aljazi Project9
Al Jazi | 1 | 10 | 7201307.23 | 0 | -7201307.23 | 2302251 | 0 | -2302251 |  |  |  | 3398127.58 | 2018-12-31 | 2018-12-04 | 2018-12-04 | 15 | 2018-12-19 | 2018-12-19 | 84445042.4 | 324045.83 | [5 empty] | 32846001.3 | 7201307.23 | 84445042.4 | 3398127.58 | Aljazi Project |  |  |  | Al Jazi10 | Aljazi Project10
Al Jazi | 1 | 11 | 10407080.28 | 0 | -10407080.28 | 3838772.36 | 0 | -3838772.36 |  |  |  | 4227710.49 | 2018-12-31 | 2018-12-24 | 2018-12-24 | 15 | 2019-01-08 | 2019-01-08 | 94852122.68 | 0.001 | [5 empty] | 37611714.98 | 10407080.28 | 94852122.68 | 4227710.49 | Aljazi Project |  |  |  | Al Jazi11 | Aljazi Project11
Al Jazi | 1 | 12 | 8329656 | 0 | -8329656 | 922154 | 0 | -922154 |  |  |  | 2264521.51 | 2019-01-31 | 2019-01-21 | 2019-01-22 | 15 | 2019-02-06 | 2019-02-04 | 103181778.68 | 0.001 | [5 empty] | 42316559.84 | 8329656 | 103181778.68 | 2264521.51 | Aljazi Project |  |  |  | Al Jazi12 | Aljazi Project12
Al Jazi | 1 | 13 | 8749208.76 | 0 | -8749208.76 | 2994292.79 | 0 | -2994292.79 |  |  |  | 3848045.61 | 2019-02-28 | 2019-02-17 | 2019-02-19 | 15 | 2019-03-06 | 2019-03-04 | 111930987.44 | 347539.5 | [5 empty] | 47070296.16 | 8749208.76 | 111930987.44 | 3848045.61 | Aljazi Project |  |  |  | Al Jazi13 | Aljazi Project13
Al Jazi | 1 | 14 | 9382086.37 | 0 | -9382086.37 | 1629015.64 | 0 | -1629015.64 |  |  |  | 1995238.89 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-08 | 121313073.81 | 104261.85 | [5 empty] | 52347380.67 | 9382086.37 | 121313073.81 | 1995238.89 | Aljazi Project |  |  |  | Al Jazi14 | Aljazi Project14
Al Jazi | 1 | 15 | 9011217.19 | 0 | -9011217.19 | 2107757 | 0 | -2107757 |  |  |  | 2738501.15 | 2019-04-30 | 2019-04-21 | 2019-04-24 | 15 | 2019-05-09 | 2019-05-09 | 130324291 | 208523.7 | [5 empty] | 56948226.2 | 9011217.19 | 130324291 | 2738501.15 | Aljazi Project |  |  |  | Al Jazi15 | Aljazi Project15
Al Jazi | 1 | 16 | 9502208.88 | 0 | -9502208.88 | 120989.08 | 0 | -120989.08 |  |  |  | 1009779.23 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-06-01 | 139826499.88 | 0.0001 | [5 empty] | 63851171.86 | 9502208.88 | 139826499.88 | 1009779.23 | Aljazi Project |  |  |  | Al Jazi16 | Aljazi Project16
Al Jazi | 1 | 17 | 7664029.32 | 0 | -7664029.32 | 2935343.72 | 0 | -2935343.72 |  |  |  | 3577364.85 | 2019-06-30 | 2019-06-16 | 2019-06-18 | 15 | 2019-07-03 | 2019-07-06 | 147490529.2 | 0 | [5 empty] | 67191637.78 | 7664029.32 | 147490529.2 | 3577364.85 | Aljazi Project |  |  |  | Al Jazi17 | Aljazi Project17
Al Jazi | 1 | 18 | 7401622.43 | 0 | -7401622.43 | 2748544.1 | 0 | -2748544.1 |  |  |  | 3297235.7 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-07-27 | 154892151.63 | [6 empty] | 70366044.94 | 7401622.43 | 154892151.63 | 3297235.7 | Aljazi Project |  |  |  | Al Jazi18 | Aljazi Project18
Al Jazi | 1 | 19 | 9504587.63 | 0 | -9504587.63 | 3100493.11 | 0 | -3100493.11 |  |  |  | 4336532.29 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 164396739.26 | [6 empty] | 74067058.47 | 9504587.63 | 164396739.26 | 4336532.29 | Aljazi Project |  |  |  | Al Jazi19 | Aljazi Project19
Al Jazi | 1 | 20 | 8799095.49 | 0 | -8799095.49 | 371543.5 | 0 | -371543.5 |  |  |  | 2000000 | 2019-09-30 | 2019-09-30 | 2019-10-07 | 15 | 2019-10-22 | 2019-11-03 | 173195834.75 | [6 empty] | 80216713.09 | 8799095.49 | 173195834.75 | 2000000 | Aljazi Project |  |  |  | Al Jazi20 | Aljazi Project20
Al Jazi | 1 | 21 | 33097306.6205 | 0 | -33097306.6205 | 0.0001 | 0 | -0.0001 |  |  |  | 5243962.1948 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 206293141.3705 | [6 empty] | 93639432.282 | 33097306.6205 | 206293141.3705 | 5243962.1948 | Aljazi Project |  |  |  | Al Jazi21 | Aljazi Project21
Al Jazi | 1 | 22 | 4356240.1195 | 0 | -4356240.1195 | 8591440.49 | 0 | -8591440.49 |  |  |  | 8742870.72 | 2020-04-30 | 2020-04-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 210649381.49 | [7 empty] | 0 | 0 | 0 | Aljazi Project |  |  |  | Al Jazi22 | Aljazi Project22
Al Jazi - Center Zone | 1 | 1 | 2348807.6 | 278661 | -2070146.6 | 14757189.01 | 230795 | -14526394.01 | 14666580.12 |  |  | 90608.89 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-24 | 2348807.6 | [6 empty] | 1554730.83 | 2377467.23 | 2377467.23 | 909309.25 | Aljazi Project |  |  |  | Al Jazi - Center Zone1 | Aljazi Project1
Al Jazi - Center Zone | 1 | 2 | 6291718.01 | 322383 | -5969335.01 | 1686320.29 | 151797.77 | -1534522.52 |  |  |  | 2035039.03 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-05-29 | 8640525.61 | [6 empty] | 4268341.03 | 6291718.01 | 8640525.61 | 2035039.03 | Aljazi Project |  |  |  | Al Jazi - Center Zone2 | Aljazi Project2
Al Jazi - Center Zone | 1 | 3 | 12038668.84 | 121070 | -11917598.84 | 360179.68 | 58174.3 | -302005.38 |  |  |  | 360179.68 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-09-01 | 20679194.45 | [6 empty] | 12373789.15 | 12038969.26 | 20679494.87 | 1152186.95 | Aljazi Project |  |  |  | Al Jazi - Center Zone3 | Aljazi Project3
Al Jazi - Center Zone | 1 | 4 | 4840645.74 | 0 | -4840645.74 | 370581.69 | 0 | -370581.69 |  |  |  | 1090291.72 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 25519840.19 | [6 empty] | 15657190.5 | 4840645.74 | 25519840.19 | 1090291.72 | Aljazi Project |  |  |  | Al Jazi - Center Zone4 | Aljazi Project4
Al Jazi - Center Zone | 1 | 5 | 7051826.31 | 0 | -7051826.31 | 858100 | 0 | -858100 |  |  |  | 1000000 | 2019-09-30 | 2019-09-30 | 2019-10-08 | 15 | 2019-10-23 | 2019-11-03 | 32571666.5 | [6 empty] | 20595342.09 | 7051826.31 | 32571666.5 | 1000000 | Aljazi Project |  |  |  | Al Jazi - Center Zone5 | Aljazi Project5
Al Jazi - Center Zone | 1 | 6 | 6082957.03 | 0 | -6082957.03 | -0.01 | 0 | 0.01 |  |  |  | -2446690.14 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 38654623.53 | [6 empty] | 22479352.29 | 6082957.03 | 38654623.53 | -2446690.14 | Aljazi Project |  |  |  | Al Jazi - Center Zone6 | Aljazi Project6
Al Jazi - Center Zone | 1 | 7 | 966768.0649 | 0 | -966768.0649 | 151431.32 | 0 | -151431.32 |  |  |  | 151431.3187 | 2020-03-31 | 2020-03-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 39621391.5949 | [7 empty] | 0 | 0 | 0 | Aljazi Project |  |  |  | Al Jazi - Center Zone7 | Aljazi Project7
Alfa Lab | 1 | 1 |  | 1403211.67 | 1403211.67 | 1459340 | 1459340 | 0 |  |  |  |  | 2021-10-31 | 2021-10-31 | 2021-12-05 | 30 | 2022-01-04 | [8 empty] | 0 | 0 | 0 | 0 | Alfa New Central Labs |  |  |  | Alfa Lab1 | Alfa New Central Labs1
Allegria-New Modifications | 1 | 1 |  | 0 | 0 | 659568.2 | 0 | -659568.2 |  |  |  |  | 2019-06-30 | 2019-07-02 | 2019-08-22 | 31 | 2019-09-22 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Allegria-New Modifications1 | 01
Astoria - Sharm | 1 | 2 | 1243970 | 401082.65 | -842887.35 | 837813.8 | 269728 | -568085.8 |  |  |  | 836570 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 42 | 2022-08-16 | 2022-07-06 | 1243970 |  |  |  |  | 65308.425 | 65308.425 | 0 | 1243970 | 1243970 | 836570 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm2 | Astoria Sharm elSheikh2
Astoria - Sharm | 1 | 3 | 401082.65 | 2440310 | 2039227.35 | 269728 | 1641108 | 1371380 |  |  |  | 269728 | 2022-07-31 | 2022-07-31 | 2022-08-03 | 42 | 2022-09-14 | 2022-08-09 | 1645052.65 |  | 98567.65 |  |  | 21056.84 | 21056.84 | 0 | 401082.65 | 1645052.65 | 269728 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm3 | Astoria Sharm elSheikh3
Astoria - Sharm | 1 | 4 | 2440310 | 1055208 | -1385102 | 1641108 | 709627 | -931481 |  |  |  | 1641108 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 42 | 2022-10-12 | 2022-09-05 | 4085362.65 |  | 98567.65 |  |  | 128116.275 | 128116.275 | 0 | 2440310 | 4085362.65 | 1641108 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm4 | Astoria Sharm elSheikh4
Astoria - Sharm | 1 | 5 | 1055208 | 314831.49 | -740376.51 | 709627 | 278242.2245 | -431384.7755 |  |  |  | 709627 | 2022-09-30 | 2022-09-30 | 2022-10-04 | 42 | 2022-11-15 | 2022-10-06 | 5140570.65 |  | 98567.65 |  | 33170 | 55398 | 55398 | 0 | 1055208 | 5140570.65 | 709627 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm5 | Astoria Sharm elSheikh5
Astoria - Sharm | 1 | 6 | 314831.49 | 172304.78 | -142526.71 | 244817 | 621397.339 | 376580.339 |  |  |  | 244817 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 42 | 2022-12-09 | 2022-10-30 | 5455402.14 |  | 98567.65 |  |  | 221100 | 221100 | 0 | 314831.49 | 5455402.14 | 244817 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm6 | Astoria Sharm elSheikh6
Astoria - Sharm | 1 | 7 |  | 1116626 | 1116626 | 654151 | 1160163.51 | 506012.51 |  |  |  |  | 2022-11-30 | 2022-11-28 | 2022-11-28 | 42 | 2023-01-09 | [8 empty] | 0 | 0 | 0 | 0 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm7 | Astoria Sharm elSheikh7
Astoria - Sharm | 1 | 8 |  | 0 | 0 | 1160836 | 0 | -1160836 |  |  |  |  | 2023-01-31 | 2023-02-01 | 2023-02-01 | 42 | 2023-03-15 | [8 empty] | 0 | 0 | 0 | 0 | Astoria Sharm elSheikh |  |  |  | Astoria - Sharm8 | Astoria Sharm elSheikh8
Astoria Hotel | 1 | 1 | 6707988.52 | 8415906.06 | 1707917.54 | 6511122 | 6441068.119 | -70053.881 | 46039744.5 | 2000000 |  | 4511122 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 42 | 2022-03-29 | 2022-02-28 | 6707988.52 | [6 empty] | 0 | 6707988.52 | 6707988.52 | 4511122 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel1 | Waldorf Astoria Cairo1
Astoria Hotel | 1 | 2 | 3507480.42 | 3507480.42 | 0 | 2448868 | 2448867.881 | -0.119 | 18415897.8 |  |  | 2448868 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 42 | 2022-04-20 | 2022-03-23 | 10215468.94 | 140761.4 |  |  |  | 191180.79 | 191180.79 | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel2 | Waldorf Astoria Cairo2
Astoria Hotel | 1 | 3 | 6522225.37 | 6522225.37 | 0 | 5421697 | 5421697.4285 | 0.4285 | 9207948.9 |  |  | 5421697 | 2022-03-31 | 2022-03-31 | 2022-04-07 | 42 | 2022-05-19 | 2022-04-21 | 16737694.31 | 3185804.68 |  |  |  | 501707.065 | 501707.065 | 0 | 6522225.37 | 16737694.31 | 5421697 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel3 | Waldorf Astoria Cairo3
Astoria Hotel | 1 | 4 | 5466647.24 | 5452379.98 | -14267.26 | 13842213.9 | 4634265 | -9207948.9 |  |  |  | 4634265 | 2022-04-30 | 2022-05-10 | 2022-05-17 | 42 | 2022-06-28 | 2022-05-31 | 22204341.55 | 4790259 | 987281.94 |  |  | 1171022.63 | 1171022.63 | 0 | 5466647.24 | 22204341.55 | 4634265 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel4 | Waldorf Astoria Cairo4
Astoria Hotel | 1 | 5 | 3030560.1014 | 3030560.1 | -0.0014405 | 5818860 | 5818860.175 | 0.175 |  |  |  | 5818860 | 2022-05-31 | 2022-06-01 | 2022-06-05 | 42 | 2022-07-17 | 2022-06-28 | 25234901.6514 | 9900984.5198 | 1091283.222 |  |  | 538643.0456 | 538643.0456 | 0 | 3030560.1014 | 25234901.6514 | 5818860 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel5 | Waldorf Astoria Cairo5
Astoria Hotel | 1 | 6 | 14829494.3486 | 14843761.8 | 14267.4514 | 8446328.13 | 8446327.45 | -0.68 |  |  |  | 8446328.13 | 2022-06-30 | 2022-06-28 | 2022-06-29 | 42 | 2022-08-10 | 2022-07-06 | 40064396 | 11427302 | 2183203.94 |  |  | 2103380.5 | 2103380.5 | 0 | 14829494.3486 | 40064396 | 8446328.13 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel6 | Waldorf Astoria Cairo6
Astoria Hotel | 1 | 7 | 11030217.63 | 14720271.03 | 3690053.4 | 8710615 | 8710614.8515 | -0.1485 |  |  |  | 8710615 | 2022-07-31 | 2022-08-03 | 2022-08-04 | 42 | 2022-09-15 | 2022-08-08 | 51094613.63 | 12186248.36 | 2194500 |  |  | 849101.84 | 849101.84 | 0 | 11030217.63 | 51094613.63 | 8710615 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel7 | Waldorf Astoria Cairo7
Astoria Hotel | 1 | 8 | 14516248.37 | 9001222.98 | -5515025.39 | 2805916 | 2805915.699 | -0.301 |  |  |  | 2805916 | 2022-08-31 | 2022-08-20 | 2022-08-25 | 42 | 2022-10-06 | 2022-09-08 | 65610862 | 13343046 | 6856879.13 |  |  | 3444570.26 | 3444570.26 | 0 | 14516248.37 | 65610862 | 2805916 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel8 | Waldorf Astoria Cairo8
Astoria Hotel | 1 | 9 | 10555127.63 | 16070153.02 | 5515025.39 | 6286403 | 6286403 | 0 |  |  |  | 6286403 | 2022-09-30 | 2022-09-15 | 2022-09-21 | 42 | 2022-11-02 | 2022-09-26 | 76165989.63 | 6497174.95 | 1117474.28 |  |  | 713450.5 | 713450.5 | 0 | 10555127.63 | 76165989.63 | 6286403 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel9 | Waldorf Astoria Cairo9
Astoria Hotel | 1 | 10 | 9739259.16 | 9739259.16 | 0 | 4982321 | 4982321 | 0 |  |  |  | 4982321 | 2022-09-30 | 2022-09-27 | 2022-10-03 | 42 | 2022-11-14 | 2022-10-06 | 85905248.79 | 7583343.27 | 4748282.13 |  |  | 565619.52 | 565619.52 | 0 | 9739259.16 | 85905248.79 | 4982321 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel10 | Waldorf Astoria Cairo10
Astoria Hotel | 1 | 11 | 22454296.86 | 22454296.86 | 0 | 10757000 | 10757000 | 0 |  |  |  | 10757000 | 2022-10-31 | 2022-10-17 | 2022-10-23 | 42 | 2022-12-04 | 2022-10-31 | 108359545.65 | 9996725.48 | 8116978.46 |  |  | 6188712.42 | 6188712.42 | 0 | 22454296.86 | 108359545.65 | 10757000 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel11 | Waldorf Astoria Cairo11
Astoria Hotel | 1 | 12 | 7707398.94 | 7707398.93 | -0.01 | 2603000 | 2602999.7165 | -0.2835 |  |  |  | 2603000 | 2022-10-31 | 2022-10-31 | 2022-11-03 | 42 | 2022-12-15 | 2022-11-10 | 116066944.59 | 7811106.63 | 9547937.37 |  |  | 6484069.92 | 6484069.92 | 0 | 7707398.94 | 116066944.59 | 2603000 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel12 | Waldorf Astoria Cairo12
Astoria Hotel | 1 | 13 | 11273556.71 | 11273556.71 | 0 | 5389256 | 5389256 | 0 |  |  |  | 5389256 | 2022-11-30 | 2022-11-19 | 2022-11-22 | 42 | 2023-01-03 | 2022-11-28 | 127340501.3 | 8209371.3 | 13101564.96 |  |  | 7095844.885 | 7095844.885 | 0 | 11273556.71 | 127340501.3 | 5389256 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel13 | Waldorf Astoria Cairo13
Astoria Hotel | 1 | 14 | 13597376.25 | 13597376.25 | 0 | 6216098 | 6216098 | 0 |  |  |  | 6216098 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2022-12-20 | 140937877.55 | 8044171.13 | 13024305.91 |  |  | 7801447.13 | 7801447.13 | 0 | 13597376.25 | 140937877.55 | 6216098 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel14 | Waldorf Astoria Cairo14
Astoria Hotel | 1 | 15 | 9032753.11 | 9032753.1 | -0.01 | 4185662 | 0 | -4185662 |  |  |  | 4185662 | 2022-12-31 | 2022-12-31 | 2022-12-26 | 42 | 2023-02-06 | 2023-01-25 | 149970630.66 | 8062383.03 | 14785109.7 |  |  | 8276577.26 | 8276577.26 | 0 | 9032753.11 | 149970630.66 | 4185662 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel15 | Waldorf Astoria Cairo15
Astoria Hotel | 1 | 16 | 9372213.83 | 9372213.84 | 0.01 | 3225683 | 0 | -3225683 |  |  |  | 3225683 | 2023-01-31 | 2023-02-08 | 2023-02-09 | 42 | 2023-03-23 | 2023-02-25 | 159342844.49 | 5542006.23 | 15892420.28 |  |  | 8642599.645 | 8642599.645 | 0 | 9372213.83 | 159342844.49 | 3225683 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel16 | Waldorf Astoria Cairo16
Astoria Hotel | 1 | 17 | 7818140.35 | 7818140.35 | 0 | 2804159 | 0 | -2804159 |  |  |  | 2804159 | 2023-02-28 | 2023-03-09 | 2023-03-13 | 42 | 2023-04-24 | 2023-04-02 | 167160984.84 | 3697164.11 | 15797479.81 |  |  | 8960809.91 | 8960809.91 | 0 | 7818140.35 | 167160984.84 | 2804159 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel17 | Waldorf Astoria Cairo17
Astoria Hotel | 1 | 18 | 10420915.55 | 10421093.88 | 178.33 | 4819756 | 3217413.914 | -1602342.086 |  |  |  | 4819756 | 2023-04-30 | 2023-04-19 | 2023-04-19 | 42 | 2023-05-31 | 2023-05-10 | 177581900.39 | 3697164.11 | 22952907.31 |  |  | 9507907.975 | 9507907.975 | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel18 | Waldorf Astoria Cairo18
Astoria Hotel | 1 | 19 | 12873774.1358 | 22057316.41 | 9183542.2742 | 1511334.24 | 1409611.34 | -101722.9 |  |  |  | 1511334.2104 | 2023-05-31 | 2023-06-07 | 2023-06-08 | 42 | 2023-07-20 | 2023-06-19 | 190455674.5258 |  | 28856915.5258 |  |  | 10019924.47 | 10019924.47 | 0 | 12873774.1358 | 190455674.5258 | 1511334.2104 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel19 | Waldorf Astoria Cairo19
Astoria Hotel | 1 | 20 | 3956219.0142 | 7912437.94 | 3956218.9258 | 0.0001 | 0 | -0.0001 |  |  |  | 3400772 | 2023-06-30 | 2023-07-13 | 2023-07-13 | 42 | 2023-08-24 | 2023-08-02 | 194411893.54 | 84871.19 | 34031882.79 |  |  | 10210867.97 | 10210867.97 | 0 | 3956219.0142 | 194411893.54 | 3400772 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel20 | Waldorf Astoria Cairo20
Astoria Hotel | 1 | 21 | 1422437.2 | 1422437.2 | -1.8161e-08 | 0.0001 | 0 | -0.0001 |  |  |  | 854979 | 2023-07-31 | 2023-08-15 | 2023-08-15 | 42 | 2023-09-26 | 2023-09-14 | 195834330.74 | 84871.19 | 37786420.4 |  |  | 10285545.925 | 10285545.925 | 0 | 1422437.2 | 195834330.74 | 854979 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel21 | Waldorf Astoria Cairo21
Astoria Hotel | 1 | 22 | 10800888.71 | 10800888.32 | -0.39 | 1e-05 | 1999998.286 | 1999998.286 |  |  |  | 9327545.58 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 42 | 2023-11-13 | 2023-10-14 | 206635219.45 |  | 43324930.66 |  |  | 10848349.02 | 10848349.02 | 1170750 | 13661357.26 | 209495688 | 44838437.05 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel22 | Waldorf Astoria Cairo22
Astoria Hotel | 1 | 23 | 13277404.55 | 13277404.76 | 0.21 | 17286732.59 | 20506021.05 | 3219288.46 |  |  |  | 17286732.59 | 2023-10-31 | 2023-11-12 | 2023-11-12 | 42 | 2023-12-24 | 2023-11-23 | 219912624 |  | 44280344.8 |  | 10667080 | 10985391.04 | 10985391.04 | 8403824.77 | 13277404.55 | 219912624 | 17286732.59 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel23 | Waldorf Astoria Cairo23
Astoria Hotel | 1 | 24 |  | 10000000 | 10000000 | 10400000 | 22455841.54 | 12055841.54 |  |  |  |  | 2023-11-30 | 2023-11-28 | 2023-11-28 | 42 | 2024-01-09 | [8 empty] | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel24 | Waldorf Astoria Cairo24
Astoria Hotel | 1 | 25 |  | 0 | 0 | 3117985 | 0 | -3117985 |  |  |  |  | 2023-11-30 | 2023-11-30 | 2024-02-07 | 42 | 2024-03-20 | [8 empty] | 0 | 0 | 0 | 0 | Waldorf Astoria Cairo |  |  |  | Astoria Hotel25 | Waldorf Astoria Cairo25
#N/A
Baraka Land Fence | 1 | 1 | 3575400 | 0 | -3575400 | 2467026 | 0 | -2467026 |  |  |  | 2645796 | 2023-10-31 | 2023-10-30 | 2023-11-06 | 42 | 2023-12-18 | 2023-11-06 | 3575400 | [6 empty] | 0 | 3575400 | 3575400 | 2645796 | 0 |  |  |  | Baraka Land Fence1 | 01
Baraka Land Fence | 1 | 2 |  | 0 | 0 | 8497787.46 | 0 | -8497787.46 |  |  |  |  | 2023-11-30 | 2023-11-30 | 2023-12-04 | 42 | 2024-01-15 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Baraka Land Fence2 | 02
Baraka Land Fence | 1 | 3 | 23602796 | 0 | -23602796 | 15418299.78 | 0 | -15418299.78 |  |  |  | 16535567.88 | 2024-02-29 | 2024-03-11 | 2024-03-11 | 42 | 2024-04-22 | 2024-03-20 | 38236396 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Baraka Land Fence3 | 03
Baraka Land Fence | 1 | 4 | 11760884 | 0 | -11760884 | 6072172.61 | 0 | -6072172.61 |  |  |  | 8703054.16 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-05-21 | 49997280 | [6 empty] | 0 | 11760884 | 49997280 | 8703054.16 | 0 |  |  |  | Baraka Land Fence4 | 04
Baraka Land Fence | 1 | 5 | 7617134 | 0 | -7617134 | 0 | 0 | 0 |  |  |  | 5636679.16 | 2024-08-31 | 2024-08-20 | 2024-08-20 | 42 | 2024-10-01 | 2024-08-20 | 57614414 | [6 empty] | 0 | 7617134 | 57614414 | 5636679.16 | 0 |  |  |  | Baraka Land Fence5 | 05
#N/A
Benban - Aswan | 1 | 2 | 22287932.1928 | 0 | -22287932.1928 | 21842173.61 | 0 | -21842173.61 |  |  |  | 21953613.1594 | 2018-06-30 | 2018-07-11 | 2018-07-11 | 60 | 2018-09-09 | 2018-07-26 | 22287932.1928 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan2 | 02
Benban - Aswan | 1 | 3 | 10786951.8956 | 0 | -10786951.8956 | 10577813.02 | 0 | -10577813.02 |  |  |  | 10577813.1577 | 2018-07-31 | 2018-07-31 | 2018-08-05 | 60 | 2018-10-04 | 2018-09-11 | 33074884.0884 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan3 | 03
Benban - Aswan | 1 | 4 | 15307380.738 | 0 | -15307380.738 | 15006351.74 | 0 | -15006351.74 |  |  |  | 15006351.7412 | 2018-08-31 | 2018-08-31 | 2018-09-05 | 60 | 2018-11-04 | 2018-09-20 | 48382264.8264 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan4 | 04
Benban - Aswan | 1 | 5 | 36144803.3444 | 0 | -36144803.3444 | 37440497.15 | 0 | -37440497.15 |  |  |  | 37440886.7444 | 2018-09-30 | 2018-09-30 | 2018-10-08 | 60 | 2018-12-07 | 2018-10-30 | 84527068.1708 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan5 | 05
Benban - Aswan | 1 | 6 | 23770609.3964 | 0 | -23770609.3964 | 23886898.7775 | 0 | -23886898.7775 |  |  |  | 23958997.0448 | 2018-10-31 | 2018-10-31 | 2018-11-11 | 60 | 2019-01-10 | 2018-11-28 | 108297677.5672 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan6 | 06
Benban - Aswan | 1 | 7 | 25005235.2928 | 0 | -25005235.2928 | 25237199.4694 | 0 | -25237199.4694 |  |  |  | 25352621.3844 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 60 | 2019-02-03 | 2018-12-08 | 133302912.86 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan7 | 07
Benban - Aswan | 1 | 8 | 27760540.7682 | 0 | -27760540.7682 | 28236383.5819 | 0 | -28236383.5819 |  |  |  | 28073115.5265 | 2018-12-31 | 2019-01-03 | 2019-01-03 | 60 | 2019-03-04 | 2019-01-06 | 161063453.6282 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan8 | 08
Benban - Aswan | 1 | 9 | 31169325.9933 | 0 | -31169325.9933 | 33103432.2978 | 0 | -33103432.2978 |  |  |  | 33103432.2978 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 60 | 2019-04-01 | 2019-02-03 | 192232779.6215 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan9 | 09
Benban - Aswan | 1 | 10 | 12107665.0539 | 0 | -12107665.0539 | 12102732.036 | 0 | -12102732.036 |  |  |  | 12014082.9225 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 60 | 2019-05-05 | 2019-03-10 | 204340444.6754 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan10 | 010
Benban - Aswan | 1 | 11 | 2235914.343 | 0 | -2235914.343 | 2222964.1737 | 0 | -2222964.1737 |  |  |  | 2314903.9752 | 2019-03-31 | 2019-03-31 | 2019-04-01 | 60 | 2019-05-31 | 2019-04-07 | 206576359.0184 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan11 | 011
Benban - Aswan | 1 | 12 | 15216014.8348 | 0 | -15216014.8348 | 16625097.353 | 0 | -16625097.353 |  |  |  | 16690051.1455 | 2019-04-30 | 2019-05-01 | 2019-05-01 | 60 | 2019-06-30 | 2019-05-09 | 221792373.8532 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan12 | 012
Benban - Aswan | 1 | 13 | 1724157.1613 | 0 | -1724157.1613 | 36700.14 | 0 | -36700.14 |  |  |  | 36947.2012 | 2019-05-31 | 2019-05-31 | 2019-05-30 | 60 | 2019-07-29 | 2019-07-11 | 223516531.0145 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan13 | 013
Benban - Aswan | 1 | 14 | 30114 | 0 | -30114 | 1174778.08 | 0 | -1174778.08 |  |  |  | 1206378.8856 | 2019-06-30 | 2019-07-02 | 2019-07-02 | 60 | 2019-08-31 | 2019-07-11 | 223546645.0145 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Benban - Aswan14 | 014
#N/A
Cement Plant | 1 | 14 | 6421251.87 | 0 | -6421251.87 | 7309725 | 0 | -7309725 |  |  |  | 7309725 | 2017-09-30 | 2017-09-25 | 2017-10-03 | 45 | 2017-11-17 | 2017-10-19 | 219688342.71 | [6 empty] | 0 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant14 | Cement Factory-Beni Suef14
Cement Plant | 1 | 15 | 8583366.193 | 0 | -8583366.193 | 6696657.1239 | 0 | -6696657.1239 |  |  |  | 6696657.1239 | 2017-10-31 | 2017-10-25 | 2017-11-02 | 45 | 2017-12-17 | 2017-11-15 | 228271708.9079 | [6 empty] | 139900 | 8583366.193 | 228271708.9079 | 6696657.1239 | Cement Factory-Beni Suef |  |  |  | Cement Plant15 | Cement Factory-Beni Suef15
Cement Plant | 1 | 16 | 6621784.9509 | 0 | -6621784.9509 | 6990595.3607 | 0 | -6990595.3607 |  |  |  | 6990595.3607 | 2017-11-30 | 2017-11-25 | 2017-12-05 | 45 | 2018-01-19 | 2017-12-14 | 234893493.8588 | [6 empty] | 149900 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant16 | Cement Factory-Beni Suef16
Cement Plant | 1 | 17 | 6642565.2352 | 0 | -6642565.2352 | 7424114.8339 | 0 | -7424114.8339 |  |  |  | 7424114.8339 | 2017-12-31 | 2017-12-25 | 2018-01-04 | 45 | 2018-02-18 | 2018-01-15 | 241536059.094 | [6 empty] | 159900 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant17 | Cement Factory-Beni Suef17
Cement Plant | 1 | 18 | 5438078.8724 | 0 | -5438078.8724 | 6925479.9129 | 0 | -6925479.9129 |  |  |  | 6925479.9129 | 2018-01-31 | 2018-01-25 | 2018-01-23 | 45 | 2018-03-09 | 2018-01-29 | 246974137.9664 | 0 | [5 empty] | 185884 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant18 | Cement Factory-Beni Suef18
Cement Plant | 1 | 19 | 12265173.6434 | 0 | -12265173.6434 | 12791497.7957 | 0 | -12791497.7957 |  |  |  | 12791498.7957 | 2018-02-28 | 2018-02-25 | 2018-02-28 | 45 | 2018-04-14 | 2018-03-17 | 269687311.6098 | 0 | [5 empty] | 195884 | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant19 | Cement Factory-Beni Suef19
Cement Plant | 1 | 20 | 4976388.8902 | 0 | -4976388.8902 | 10152661.36 | 0 | -10152661.36 |  |  |  | 10152661.36 | 2018-06-30 | 2018-06-25 | 2018-12-04 |  | 2019-01-30 | 2019-01-20 | 274663700.5 | [7 empty] | 0 | 0 | 0 | Cement Factory-Beni Suef |  |  |  | Cement Plant20 | Cement Factory-Beni Suef20
#N/A
CFC | 1 | 1 | 6586123.18 | 6586123.18 | 0 | 6200445.37 | 6200445.359 | -0.011 | 62134944.55 |  |  | 6200445.37 | 2019-11-30 | 2019-11-25 | 2019-12-10 | 60 | 2020-02-08 | 2020-01-12 | 6586123.18 | 553645.74 | [5 empty] | 0 | 6586123.18 | 6586123.18 | 6200445.37 | CFC Podium 2 |  | 6032477.44 | 553645.74 | CFC1 | CFC Podium 21
CFC | 1 | 2 | 16003200.38 | 15707266.4 | -295933.98 | 17105598.33 | 17105451.15 | -147.18 | 31067472 |  |  | 17323666.18 | 2019-12-31 | 2019-12-25 | 2020-01-09 | 60 | 2020-03-09 | 2020-02-11 | 22589323.56 | 4441799.42 | [5 empty] | 143549.58 | 16003200.38 | 22589323.56 | 17323666.18 | CFC Podium 2 |  | 11561400.96 | 4145865.44 | CFC2 | CFC Podium 22
CFC | 1 | 3 | 16743766.83 | 17039700.42 | 295933.59 | 12263695.26 | 12263842.721 | 147.461 |  |  |  | 12263695.26 | 2020-01-31 | 2020-01-25 | 2020-02-05 | 60 | 2020-04-05 | 2020-03-11 | 39333090.39 | 3876592.5 | [5 empty] | 60000 | 16743766.83 | 39333090.39 | 12263695.26 | CFC Podium 2 |  | 12867174.33 | 4172526.09 | CFC3 | CFC Podium 23
CFC | 1 | 4 | 35226223.2 | 35226223.59 | 0.39 | 32660833.58 | 32660832.57 | -1.01 |  |  |  | 32660833.58 | 2020-02-29 | 2020-02-25 | 2020-03-11 | 60 | 2020-05-10 | 2020-04-02 | 74559313.59 | 8287526.25 | [5 empty] | 60000 | 35226223.2 | 74559313.59 | 32660833.58 | CFC Podium 2 |  | 26938696.95 | 8287526.64 | CFC4 | CFC Podium 24
CFC | 1 | 5 | 30502560.31 | 30502560 | -0.31 | 24749111.95 | 24749111.52 | -0.43 |  |  |  | 24749111.95 | 2020-03-31 | 2020-03-17 | 2020-03-21 | 60 | 2020-05-20 | 2020-04-22 | 105061873.9 | 7691894.47 | [5 empty] | 0 | 30502560.31 | 105061873.9 | 24749111.95 | CFC Podium 2 |  | 22810665.84 | 7691894.16 | CFC5 | CFC Podium 25
CFC | 1 | 6 | 42011127.9851 | 42011128.3 | 0.31492 | 31500278.62 | 31500278.46 | -0.16 |  |  |  | 31500278.62 | 2020-03-31 | 2020-03-25 | 2020-04-07 | 60 | 2020-06-06 | 2020-05-04 | 147073001.8851 | 3638239.2055 | [5 empty] | 60000 | 42011127.9851 | 147073001.8851 | 31500278.62 | CFC Podium 2 |  | 38372888.7796 | 3638239.5204 | CFC6 | CFC Podium 26
CFC | 1 | 7 | 17879880.0649 | 17879880.11 | 0.045077 | 19510038 | 19510039.82 | 1.82 |  |  |  | 19510038 | 2020-04-30 | 2020-04-25 | 2020-05-07 | 60 | 2020-07-06 | 2020-06-04 | 164952881.95 | 9650322 | [5 empty] | 0 | 17879880.0649 | 164952881.95 | 19510038 | CFC Podium 2 |  | 8229558.0649 | 9650322.0451 | CFC7 | CFC Podium 27
CFC | 1 | 8 | 31008098.6054 | 31008097.6 | -1.0054 | 21459124.497 | 21459123.66 | -0.83704 |  |  |  | 21459124.497 | 2020-05-31 | 2020-05-25 | 2020-06-08 | 60 | 2020-08-07 | 2020-07-07 | 195960980.5554 | 4559164.5 | [5 empty] | 0 | 31008098.6054 | 195960980.5554 | 21459124.497 | CFC Podium 2 |  | 26448934.1054 | 4559163.4946 | CFC8 | CFC Podium 28
CFC | 1 | 9 | 29660399.8248 | 29660400.78 | 0.95519 | 24499895.82 | 24499896.0885 | 0.2685 |  |  |  | 24499895.52 | 2020-06-30 | 2020-06-25 | 2020-07-01 | 60 | 2020-08-30 | 2020-07-27 | 225621380.3802 | 4522595.5868 | [5 empty] | 0 | 29660399.8248 | 225621380.3802 | 24499895.52 | CFC Podium 2 |  | 25137804.2381 | 4522596.5419 | CFC9 | CFC Podium 29
CFC | 1 | 10 | 46257284.4262 | 52098964.43 | 5841680.0038 | 39448595.84 | 39448595.5715 | -0.2685 |  |  |  | 39448595.5711 | 2020-07-31 | 2020-07-25 | 2020-07-28 | 60 | 2020-09-26 | 2020-08-26 | 271878664.8064 | [6 empty] | 353049.48 | 46257284.4262 | 271878664.8064 | 39448595.5711 | CFC Podium 2 |  | 46257284.4262 | 5841680.0038 | CFC10 | CFC Podium 210
CFC | 1 | 11 | 22706553.5236 | 16864873.52 | -5841680.0036 | 18030565.73 | 18030566.05 | 0.32 |  |  |  | 18030565.73 | 2020-08-31 | 2020-08-25 | 2020-08-31 | 60 | 2020-10-30 | 2020-09-29 | 294585218.33 | 5378850.75 | [5 empty] | 0 | 22706553.5236 | 294585218.33 | 18030565.73 | CFC Podium 2 |  | 17327702.7736 | -462829.2536 | CFC11 | CFC Podium 211
CFC | 1 | 12 | 35304714.2417 | 34817130.72 | -487583.5217 | 29691194.9757 | 29691195.016 | 0.040322 |  |  |  | 29691194.9757 | 2020-09-30 | 2020-09-25 | 2020-10-07 | 60 | 2020-12-06 | 2020-11-04 | 329889932.5717 | 5192537.25 | [5 empty] | 0 | 35304714.2417 | 329889932.5717 | 29691194.9757 | CFC Podium 2 |  | 30112176.9917 | 4704953.7283 | CFC12 | CFC Podium 212
CFC | 1 | 13 | 13502068.4452 | 13989651.96 | 487583.5148 | 23213756.67 | 23213755.8 | -0.87 |  |  |  | 23213755.7909 | 2020-10-31 | 2020-10-25 | 2020-11-05 | 60 | 2021-01-04 | 2020-12-09 | 343392001.0169 | 19923580.7274 | [5 empty] | 0 | 13502068.4452 | 343392001.0169 | 23213755.7909 | CFC Podium 2 |  | -6421512.2822 | 20411164.2422 | CFC13 | CFC Podium 213
CFC | 1 | 14 | 29172801.673 | 29172801.68 | 0.0070295 | 19708943.72 | 19708944.274 | 0.554 |  |  |  | 19708944.2711 | 2020-11-30 | 2020-11-25 | 2020-12-05 | 60 | 2021-02-03 | 2021-01-11 | 372564802.6899 | 14613590.8525 | [5 empty] | 0 | 29172801.673 | 372564802.6899 | 19708944.2711 | CFC Podium 2 |  | 14559210.8205 | 14613590.8595 | CFC14 | CFC Podium 214
CFC | 1 | 15 | 46288367.9197 | 42273319.3 | -4015048.6197 | 40379659.8985 | 40379659.08 | -0.81848 |  |  |  | 40379659.8985 | 2020-12-31 | 2020-12-25 | 2021-01-06 | 60 | 2021-03-07 | 2021-02-22 | 418853170.6096 | 17260909.7245 | [5 empty] | 1045046 | 46288367.9197 | 418853170.6096 | 40379659.8985 | CFC Podium 2 |  | 29027458.1953 | 13245861.1047 | CFC15 | CFC Podium 215
CFC | 1 | 16 | 25170121.1048 | 29185169.72 | 4015048.6152 | 22871121.16 | 22871121.156 | -0.004 |  |  |  | 22871121.15 | 2021-01-31 | 2021-01-25 | 2021-02-03 | 60 | 2021-04-04 | 2021-03-21 | 444023291.7144 | 19535751.2059 | [5 empty] | 0 | 25170121.1048 | 444023291.7144 | 22871121.15 | CFC Podium 2 |  | 5634369.899 | 23550799.821 | CFC16 | CFC Podium 216
CFC | 1 | 17 | 23196101.9456 | 23196101.95 | 0.0044488 | 15047803.35 | 15047803.35 | 0 |  |  |  | 15047803.36 | 2021-01-31 | 2021-02-10 | 2021-02-15 | 60 | 2021-04-16 | 2021-03-25 | 467219393.66 | 14368442.92 | [5 empty] | 0 | 23196101.9456 | 467219393.66 | 15047803.36 | CFC Podium 2 |  | 8827659.0256 | 14368442.9244 | CFC17 | CFC Podium 217
CFC | 1 | 18 | 16880809.49 | 16880809.49 | 4.8429e-08 | 12196441.12 | 12196441.12 | 0 |  |  |  | 12196441.11 | 2021-02-28 | 2021-02-25 | 2021-03-02 | 60 | 2021-05-01 | 2021-04-06 | 484100203.15 | 14078602.67 | [5 empty] | 0 | 16880809.49 | 484100203.15 | 12196441.11 | CFC Podium 2 |  | 2802206.82 | 14078602.67 | CFC18 | CFC Podium 218
CFC | 1 | 19 | 20398722.16 | 20398722.15 | -0.01 | 14008565.7 | 14008565.7 | 0 |  |  |  | 14008565.71 | 2021-03-31 | 2021-03-10 | 2021-03-17 | 60 | 2021-05-16 | 2021-04-20 | 504498925.31 | 10502130.78 | [5 empty] | 0 | 20398722.16 | 504498925.31 | 14008565.71 | CFC Podium 2 |  | 9896591.38 | 10502130.77 | CFC19 | CFC Podium 219
CFC | 1 | 20 | 23102145.85 | 23105145.86 | 3000.01 | 23721354.77 | 23721354.77 | 0 |  |  |  | 23721354.77 | 2021-03-31 | 2021-03-25 | 2021-03-29 | 60 | 2021-05-28 | 2021-05-24 | 527601071.16 | 16161812.22 | [5 empty] | 992616.34 | 23102145.85 | 527601071.16 | 23721354.77 | CFC Podium 2 |  | 6940333.63 | 16164812.23 | CFC20 | CFC Podium 220
CFC | 1 | 21 | 23568050.8 | 23565050.79 | -3000.01 | 17156725.12 | 19156725.1095 | 1999999.9895 |  |  |  | 17156225.13 | 2021-04-30 | 2021-04-10 | 2021-04-15 | 60 | 2021-06-14 | 2021-06-17 | 551169121.96 | 15788492.2694 | [5 empty] | 3023908.26 | 23568050.8 | 551169121.96 | 17156225.13 | CFC Podium 2 |  | 7779558.5306 | 15785492.2594 | CFC21 | CFC Podium 221
CFC | 1 | 22 | 19833699.32 | 19833699.33 | 0.01 | 13410069.82 | 13410069.82 | 0 |  |  |  | 13410069.82 | 2021-04-30 | 2021-04-25 | 2021-05-06 | 60 | 2021-07-05 | 2021-06-29 | 571002821.28 | 12047992.86 | [5 empty] | 0 | 19833699.32 | 571002821.28 | 13410069.82 | CFC Podium 2 |  | 7785706.46 | 12047992.87 | CFC22 | CFC Podium 222
CFC | 1 | 23 | 19569971.41 | 19569971.41 | -8.9407e-08 | 15440459.23 | 15440458.9205 | -0.3095 |  |  |  | 15440458.92 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 60 | 2021-08-29 | 2021-08-18 | 590572792.69 | 9696296.63 | [5 empty] | 0 | 19569971.41 | 590572792.69 | 15440458.92 | CFC Podium 2 |  | 9873674.78 | 9696296.63 | CFC23 | CFC Podium 223
CFC | 1 | 24 | 14455028.52 | 14455028.51 | -0.01 | 7464480.35 | 9889480.3655 | 2425000.0155 |  |  |  | 7464840.35 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 60 | 2021-09-13 | 2021-09-23 | 605027821.21 | 5161877.98 | [5 empty] | 5612498.72 | 14455028.52 | 605027821.21 | 7464840.35 | CFC Podium 2 |  | 9293150.54 | 5161877.97 | CFC24 | CFC Podium 224
CFC | 1 | 25 | 13190112.67 | 13190112.67 | 3.9116e-08 | 9682524.46 | 9682524.4635 | 0.0035 |  |  |  | 9682524.47 | 2021-07-31 | 2021-08-10 | 2021-08-16 | 60 | 2021-10-15 | 2021-10-25 | 618217933.88 | 1715079.08 | [5 empty] | 0 | 13190112.67 | 618217933.88 | 9682524.47 | CFC Podium 2 |  | 11475033.59 | 1715079.08 | CFC25 | CFC Podium 225
CFC | 1 | 26 | 6460765.9427 | 6460765.95 | 0.0073488 | 2397254.3033 | 4897254.2975 | 2499999.9942 |  |  |  | 2397254.3033 | 2021-08-31 | 2021-08-25 | 2021-09-02 | 60 | 2021-11-01 | 2021-11-18 | 624678699.8227 | 200294.3722 | [5 empty] | 0 | 6460765.9427 | 624678699.8227 | 2397254.3033 | CFC Podium 2 |  | 6260471.5705 | 200294.3795 | CFC26 | CFC Podium 226
CFC | 1 | 27 | 7714993.7673 | 7714993.76 | -0.0073489 | 10793868.64 | 7405131.708 | -3388736.932 |  |  |  | 10793868.55 | 2021-09-30 | 2021-09-10 | 2021-09-19 | 60 | 2021-11-18 | 2021-11-22 | 632393693.59 | [6 empty] | 4776768.68 | 7714993.7673 | 632393693.59 | 10793868.55 | CFC Podium 2 |  | 7714993.7673 | -0.0073489 | CFC27 | CFC Podium 227
CFC | 1 | 28 | 5026145.47 | 5026145.48 | 0.01 | 10367935.31 | 34503065.494 | 24135130.184 |  |  |  | 10367935.42 | 2021-09-30 | 2021-09-14 | 2022-03-07 | 60 | 2022-05-06 | 2022-05-09 | 637419839.06 |  |  |  |  | 16732270.78 | 16732270.78 | 0 | 5026145.47 | 637419839.06 | 10367935.42 | CFC Podium 2 |  | 5026145.47 | 0.01 | CFC28 | CFC Podium 228
CFC | 1 | 29 |  | 0 | 0 | 15034318.2703 | 0 | -15034318.2703 |  |  |  |  | 2021-09-30 | 2021-09-14 | 2022-10-03 | 60 | 2022-12-02 | [8 empty] | 0 | 0 | 0 | 0 | CFC Podium 2 |  |  |  | CFC29 | CFC Podium 229
#N/A
Comoros - Off Shore | 1 | 1 |  | 0 | 0 | 2555388 | 0 | -2555388 |  |  |  |  | 2022-06-30 | 2022-06-23 | 2022-06-23 | 45 | 2022-08-07 | [8 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - Off Shore1 | Le Galawa Hotel Resort1
Comoros - Off Shore | 1 | 2 | 1137692.89 | 0 | -1137692.89 | 910154 | 0 | -910154 |  |  |  | 910154.31 | 2023-01-31 | 2023-01-28 | 2023-03-21 | 45 | 2023-05-05 | 2023-03-21 | 4331928.01 | [6 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - Off Shore2 | Le Galawa Hotel Resort2
Comoros - Off Shore | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 | [8 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - Off Shore3 | Le Galawa Hotel Resort3
Comoros - On Shore | 1 | 1 | 1038550.94 | 0 | -1038550.94 | 1094549.01 | 0 | -1094549.01 |  | 263708.26 |  | 830840.75 | 2023-01-31 | 2023-01-28 | 2023-03-23 | 45 | 2023-05-07 | 2023-03-23 | 1038550.94 | [6 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - On Shore1 | Le Galawa Hotel Resort1
Comoros - On Shore | 1 | 2 | 506813.73 | 0 | -506813.73 | 405450.99 | 0 | -405450.99 |  |  |  | 405450.99 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 | 2023-10-12 | 1545364.67 | [6 empty] | 0 | 0 | 0 | 0 | Le Galawa Hotel Resort |  |  |  | Comoros - On Shore2 | Le Galawa Hotel Resort2
#N/A
Creeks - URBN K | 1 | 1 | 6070824.52 | 10988694.51 | 4917869.99 | 10729515 | 10729515 | 0 | 25000000 | 57750000 |  | 10729515.71 | 2023-03-31 | 2023-04-10 | 2023-04-13 | 54 | 2023-06-06 | 2023-05-17 | 6070824.52 | 4917870 |  |  | 1412647.23 | 116454.43 | 116454.43 | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 1152954.52 | 9835739.99 | Creeks - URBN K1 | Creeks URBN-K1
Creeks - URBN K | 1 | 2 | 24895588.2 | 19977718.2 | -4917870 | 3863139 | 3863139 | 0 |  |  |  | 3863139.56 | 2023-04-30 | 2023-05-10 | 2023-05-17 | 54 | 2023-07-10 | 2023-06-01 | 30966412.72 |  |  |  | 9774769.5 | 529152.325 | 529152.325 | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 24895588.2 | -4917870 | Creeks - URBN K2 | Creeks URBN-K2
Creeks - URBN K | 1 | 3 | 40661954.88 | 40661954.89 | 0.01 | 21808950 | 0 | -21808950 |  |  |  | 21808950.42 | 2023-05-31 | 2023-06-10 | 2023-06-13 | 54 | 2023-08-06 | 2023-06-18 | 71628367.6 |  |  |  | 10182390.98 | 1536149.435 | 1536149.435 | 0 | 40661954.88 | 71628367.6 | 21808950.42 | Creeks URBN-K |  | 40661954.88 | 0.01 | Creeks - URBN K3 | Creeks URBN-K3
Creeks - URBN K | 1 | 4 | 25969563.12 | 25969563.12 | 0 | 8830426 | 8830426 | 0 |  |  |  | 8830426.33 | 2023-06-30 | 2023-07-10 | 2023-07-11 | 54 | 2023-09-03 | 2023-07-19 | 97597930.72 |  |  |  | 11215823.74 | 2159552.5 | 2159552.5 | 0 | 0 | 0 | 8830426.33 | Creeks URBN-K |  | 25969563.12 | 0 | Creeks - URBN K4 | Creeks URBN-K4
Creeks - URBN K | 1 | 5 | 21068069.1 | 29818122.52 | 8750053.42 | 13533059 | 13533059 | 0 |  |  |  | 13533059.96 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 54 | 2023-10-07 | 2023-08-23 | 118665999.82 | 8750053.42 |  |  | 12015310.55 | 2666267.23 | 2666267.23 | 0 | 21068069.1 | 118665999.82 | 13533059.96 | Creeks URBN-K |  | 12318015.68 | 17500106.84 | Creeks - URBN K5 | Creeks URBN-K5
Creeks - URBN K | 1 | 6 | 18829649.55 | 21266246.93 | 2436597.38 | 19608847 | 19608846.9472 | -0.0528 |  |  |  | 19608846.96 | 2023-08-31 | 2023-09-13 | 2023-09-14 | 54 | 2023-11-07 | 2023-09-27 | 137495649.37 | 11186650.81 |  |  | 14124627.7 | 3084275.5 | 3084275.5 | 0 | 18829649.55 | 137495649.37 | 19608846.96 | Creeks URBN-K |  | 7642998.74 | 13623248.19 | Creeks - URBN K6 | Creeks URBN-K6
Creeks - URBN K | 1 | 7 | 18845217.25 | 18657407.33 | -187809.92 | 16761479 | 16761479 | 0 |  |  |  | 16761479.32 | 2023-09-30 | 2023-10-13 | 2023-10-15 | 54 | 2023-12-08 | 2023-11-02 | 156340866.62 | 10998840.9 |  |  | 15355016.01 | 3524646.26 | 3524646.26 | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 7846376.35 | 10811030.98 | Creeks - URBN K7 | Creeks URBN-K7
Creeks - URBN K | 1 | 8 | 21024971.71 | 18875663.98 | -2149307.73 | 16707965 | 16707944.9992 | -20.0008 |  |  |  | 16707965 | 2023-10-31 | 2023-10-13 | 2023-11-15 | 54 | 2024-01-08 | 2023-12-02 | 177365838.33 | 8849533.16 | 524238 |  | 16370912 | 8023534 |  | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 12175438.55 | 6700225.43 | Creeks - URBN K8 | Creeks URBN-K8
Creeks - URBN K | 1 | 9 | 18661864.22 | 18620717.8 | -41146.42 | 16997068 | 16997068 | 0 |  |  |  | 16997068.33 | 2023-11-30 | 2023-12-13 | 2023-12-17 | 54 | 2024-02-09 | 2023-12-28 | 196027702.55 | 8808386.74 | 549978 |  | 19145680.99 | 8813027.1 |  | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 9853477.48 | 8767240.32 | Creeks - URBN K9 | Creeks URBN-K9
Creeks - URBN K | 1 | 10 | 32359750.94 | 40231853.45 | 7872102.51 | 19246723 | 19246723 | 0 |  |  |  | 19246723.67 | 2023-12-31 | 2024-01-13 | 2024-01-15 | 54 | 2024-03-09 | 2024-03-15 | 228387453.49 | 16680489.26 | 713540 |  | 34117344 | 9677828.4 |  | 0 | 21707049.44 | 217734751.99 | 18357105.31 | Creeks URBN-K | 2 lines in invoicing | 15679261.68 | 24552591.77 | Creeks - URBN K10 | Creeks URBN-K10
Creeks - URBN K | 1 | 11 | 19399852.91 | 13885723.37 | -5514129.54 | 11569432 | 11569432 | 0 |  |  |  | 11569432.7 | 2024-01-31 | 2024-02-13 | 2024-02-15 | 54 | 2024-04-09 | 2024-03-10 | 247787306.4 | 11166359.72 | 713540 |  | 34372400 | 10635068.27 |  | 0 | 19399852.91 | 247787306.4 | 11569432.7 | Creeks URBN-K |  | 8233493.19 | 5652230.18 | Creeks - URBN K11 | Creeks URBN-K11
Creeks - URBN K | 1 | 12 | 13939506.69 | 10141133.17 | -3798373.52 | 8618325 | 8618325 | 0 |  |  |  | 8618325.74 | 2024-02-29 | 2024-03-13 | 2024-03-16 | 54 | 2024-05-09 | 2024-04-03 | 261726813.09 | 7367986.2 | 777032.73 |  | 35392063.88 | 11277885.86 |  | 0 | 13939506.69 | 261726813.09 | 8618325.74 | Creeks URBN-K |  | 6571520.49 | 3569612.68 | Creeks - URBN K12 | Creeks URBN-K12
Creeks - URBN K | 1 | 13 | 17837569.29 | 23806990.16 | 5969420.87 | 23221916 | 23221916 | 0 |  |  |  | 23221916.29 | 2024-03-31 | 2024-03-13 | 2024-04-17 | 54 | 2024-06-10 | 2024-04-24 | 279564382.38 | 13337407.07 | 777032 |  | 42980609.88 | 11790337 |  | 0 | 0 | 0 | 0 | Creeks URBN-K |  | 4500162.22 | 19306827.94 | Creeks - URBN K13 | Creeks URBN-K13
Creeks - URBN K | 1 | 14 | 11923940.57 | 7646354.5 | -4277586.07 | 6223873.19 | 6223872.155 | -1.035 |  |  |  | 6223873.19 | 2024-04-30 | 2024-05-13 | 2024-05-16 | 54 | 2024-07-09 | 2024-05-22 | 291488322.95 | 9059823 | 777032.73 |  | 43382302 | 12366449.19 |  | 0 | 0 | 0 | 0 | Creeks URBN-K | collection with creeks | 2864117.57 | 4782236.93 | Creeks - URBN K14 | Creeks URBN-K14
Creeks - URBN K | 1 | 15 | 15151516.49 | 10771231.15 | -4380285.34 | 10206848 | 10206848 | 0 |  |  |  | 10206848.68 | 2024-05-31 | 2024-06-13 | 2024-06-11 | 54 | 2024-08-04 | 2024-06-12 | 306639839.44 | 4679535.56 | 777032 |  | 43540689 | 13094578 |  | 0 | 15151516.49 | 306639839.44 | 10206848.68 | Creeks URBN-K |  | 10471980.93 | 299250.22 | Creeks - URBN K15 | Creeks URBN-K15
Creeks - URBN K | 1 | 16 | 8934038.52 | 6516046.61 | -2417991.91 | 6345314 | 6345313.6705 | -0.3295 |  |  |  | 6345313.67 | 2024-06-30 | 2024-07-13 | 2024-07-15 | 54 | 2024-09-07 | 2024-07-29 | 315573877.96 | 2261543.76 | 777032.73 |  | 44277783.1705 | 13525953 |  | 0 | 8934038.52 | 315573877.96 | 6345313.67 | Creeks URBN-K |  | 6672494.76 | -156448.15 | Creeks - URBN K16 | Creeks URBN-K16
Creeks - URBN K | 1 | 17 | 8615746.66 | 8554341.9 | -61404.76 | 8554807 | 8554807.445 | 0.445 |  |  |  | 8554807.45 | 2024-07-31 | 2024-08-13 | 2024-08-15 | 54 | 2024-10-08 | 2024-09-05 | 324189624.62 | 2200139 | 777032 |  | 46059367 | 13867661 |  | 0 | 8615746.66 | 324189624.62 | 8554807.45 | Creeks URBN-K | 17,18 togeather | 6415607.66 | 2138734.24 | Creeks - URBN K17 | Creeks URBN-K17
Creeks - URBN K | 1 | 18 | 9557078 | 9384875.1 | -172202.9 | 9363450 | 9363449.555 | -0.445 |  |  |  | 9363449.62 | 2024-08-31 | 2024-09-13 | 2024-09-15 | 54 | 2024-11-08 | 2024-09-25 | 333746702.62 | 2027936.1 | 777032 |  | 47680035 | 7132240.5 | 7132240.5 | 0 | 9557078 | 333746702.62 | 9363449.62 | Creeks URBN-K |  | 7529141.9 | 1855733.2 | Creeks - URBN K18 | Creeks URBN-K18
Creeks - URBN K | 1 | 19 | 6248543.66 | 0 | -6248543.66 | 0 | 0 | 0 |  |  |  | 6696306.5 | 2024-10-31 | 2024-10-13 | 2024-10-15 | 54 | 2024-12-08 | 2024-11-02 | 339995246.28 | 2452144.43 | 777032 |  | 49061466 | 7253918.5 | 7253918.5 | 0 | 6248543.66 | 339995246.28 | 6696306.5 | Creeks URBN-K |  |  |  | Creeks - URBN K19 | Creeks URBN-K19
Creeks - URBN K | 1 | 20 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-11-30 | 2024-11-13 | 2024-11-14 | 54 | 2025-01-07 | [8 empty] | 0 | 0 | 0 | 0 | Creeks URBN-K |  |  |  | Creeks - URBN K20 | Creeks URBN-K20
#N/A
Damietta Port - Civil | 1 | 2 |  | 1592229.98 | 1592229.98 | 1520770.91 | 1496696.18 | -24074.73 |  |  |  |  | 2024-10-31 | 2024-10-17 | 2024-10-17 | 42 | 2024-11-28 | [8 empty] | 0 | 0 | 0 | 0 | Damietta Container Termin |  |  |  | Damietta Port - Civil2 | Damietta Container Termin2
Damietta Port - Civil | 1 | 3 |  | 0 | 0 | 1496696.18 | 0 | -1496696.18 |  |  |  |  | 2024-10-31 | 2024-10-30 | 2024-10-30 | 42 | 2024-12-11 | [8 empty] | 0 | 0 | 0 | 0 | Damietta Container Termin |  |  |  | Damietta Port - Civil3 | Damietta Container Termin3
Damietta Port - Civil | 1 | 1 |  | 1617841.39 | 1617841.39 | 4058690.9 | 1520770.9061 | -2537919.9939 | 4058690.9 |  |  |  | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 | [8 empty] | 0 | 0 | 0 | 0 | Damietta Container Termin |  |  |  | Damietta Port - Civil1 | Damietta Container Termin1
Damietta Port - Infra | #N/A | 1 |  | 0 | 0 | 6541975.22 | 0 | -6541975.22 | 6541975.22 |  |  |  | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 | [8 empty] | 0 | 0 | 0 | 0 | #N/A |  |  |  | Damietta Port - Infra1 | #N/A
#N/A
DP World Sokhna | 1 | 1 | 21619523.77 | 21619523.77 | 0 | 257561970.68 | 15998139 | -241563831.68 |  |  |  | 16214642.83 | 2019-01-31 | 2019-02-04 | 2019-02-04 | 56 | 2019-04-01 | 2019-02-11 | 21619523.77 | 0 | [5 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna1 | DPW Onshore Port & Terminal1
DP World Sokhna | 1 | 2 | 24408793.91 | 24408793.92 | 0.01 | 18062199.23 | 18062199.23 | 0 |  |  |  | 18306595.43 | 2019-02-28 | 2019-02-28 | 2019-03-04 | 56 | 2019-04-29 | 2019-03-05 | 46028317.68 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna2 | DPW Onshore Port & Terminal2
DP World Sokhna | 1 | 3 | 20754393.51 | 0 | -20754393.51 | 15357944.03 | 0 | -15357944.03 |  |  |  | 15565795.14 | 2019-03-31 | 2019-03-31 | 2019-04-02 | 56 | 2019-05-28 | 2019-04-11 | 66782711.19 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna3 | DPW Onshore Port & Terminal3
DP World Sokhna | 1 | 4 | 37757872.09 | 20754393.51 | -17003478.58 | 27940477.28 | 15357944.03 | -12582533.25 |  |  |  | 28318404.08 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 56 | 2019-06-30 | 2019-05-16 | 104540583.28 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna4 | DPW Onshore Port & Terminal4
DP World Sokhna | 1 | 5 | 17786446.66 | 37757872.1 | 19971425.44 | 13161622.85 | 27940477.28 | 14778854.43 |  |  |  | 13339835 | 2019-05-31 | 2019-05-31 | 2019-06-02 | 56 | 2019-07-28 | 2019-06-16 | 122327029.94 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna5 | DPW Onshore Port & Terminal5
DP World Sokhna | 1 | 6 | 33097932.28 | 84569157.85 | 51471225.57 | 24492163.72 | 13161622.85 | -11330540.87 |  |  |  | 24823449.22 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 56 | 2019-09-07 | 2019-08-06 | 155424962.22 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna6 | DPW Onshore Port & Terminal6
DP World Sokhna | 1 | 7 | 40506959.47 | 33097932.28 | -7409027.19 | 29974844.16 | 24492163.72 | -5482680.44 |  |  |  | 30380219.6 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 56 | 2019-10-01 | 2019-08-22 | 195931921.69 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna7 | DPW Onshore Port & Terminal7
DP World Sokhna | 1 | 8 | 39363674.8 | 79870634.27 | 40506959.47 | 29128813.98 | 59103658.14 | 29974844.16 |  |  |  | 29522756.11 | 2019-08-31 | 2019-09-05 | 2019-09-05 | 56 | 2019-10-31 | 2019-09-17 | 235295596.49 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna8 | DPW Onshore Port & Terminal8
DP World Sokhna | 1 | 9 | 54097551.55 | 54097551.55 | 0 | 40031882.73 | 40031882.73 | 0 |  |  |  | 40573163.66 | 2019-09-30 | 2019-10-06 | 2019-10-08 | 56 | 2019-12-03 | 2019-10-23 | 289393148.04 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna9 | DPW Onshore Port & Terminal9
DP World Sokhna | 1 | 10 | 90533235.47 | 90533235.47 | 0 | 66994289.3 | 66994289.3 | 0 |  |  |  | 67899926.6 | 2019-10-31 | 2019-11-17 | 2019-11-11 | 56 | 2020-01-06 | 2019-11-24 | 379926383.51 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna10 | DPW Onshore Port & Terminal10
DP World Sokhna | 1 | 11 | 102020049.91 | 102020049.91 | 0 | 76494532.33 | 75494532.33 | -1000000 |  |  |  | 76515037.44 | 2019-11-30 | 2019-12-12 | 2019-12-12 | 56 | 2020-02-06 | 2019-12-22 | 481946433.42 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna11 | DPW Onshore Port & Terminal11
DP World Sokhna | 1 | 12 | 148210852.7 | 148210852.69 | -0.01 | 109675422.28 | 109675422.28 | 0 |  |  |  | 111158139.52 | 2019-12-31 | 2020-01-15 | 2020-01-15 | 56 | 2020-03-11 | 2020-02-16 | 630157286.12 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna12 | DPW Onshore Port & Terminal12
DP World Sokhna | 1 | 13 | 124566872.96 | 124566873.87 | 0.91 | 92179486 | 92179486 | 0 |  |  |  | 93425154.72 | 2020-01-31 | 2020-02-15 | 2020-02-18 | 56 | 2020-04-14 | 2020-03-16 | 754724159.08 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna13 | DPW Onshore Port & Terminal13
DP World Sokhna | 1 | 14 | 141052143.0757 | 141052143.07 | -0.0056975 | 104378585.88 | 104378585.87 | -0.01 |  |  |  | 105789107.3061 | 2020-02-29 | 2020-03-17 | 2020-03-17 | 56 | 2020-05-12 | 2020-04-14 | 895776302.1557 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna14 | DPW Onshore Port & Terminal14
DP World Sokhna | 1 | 15 | 110730132.4543 | 110730132.45 | -0.0043024 | 81940298.01 | 81940298.01 | 0 |  |  |  | 83047599.34 | 2020-03-31 | 2020-04-15 | 2020-04-19 | 56 | 2020-06-14 | 2020-05-17 | 1006506434.61 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna15 | DPW Onshore Port & Terminal15
DP World Sokhna | 1 | 16 | 86484919.88 | 86484919.88 | 0 | 63998840.71 | 63998840.71 | 0 |  |  |  | 64863689.91 | 2020-04-30 | 2020-05-19 | 2020-05-19 | 56 | 2020-07-14 | 2020-06-21 | 1092991354.49 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna16 | DPW Onshore Port & Terminal16
DP World Sokhna | 1 | 17 | 56454657.9 | 56454657.9 | -1.0431e-07 | 41776446.85 | 41776446.84 | -0.01 |  |  |  | 42340993.43 | 2020-05-31 | 2020-06-18 | 2020-06-18 | 56 | 2020-08-13 | 2020-07-22 | 1149446012.39 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna17 | DPW Onshore Port & Terminal17
DP World Sokhna | 1 | 18 | 59878397.73 | 59878397.73 | 2.1607e-07 | 44310014.32 | 44310014.32 | 0 |  |  |  | 44908798.3 | 2020-06-30 | 2020-07-23 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-19 | 1209324410.12 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna18 | DPW Onshore Port & Terminal18
DP World Sokhna | 1 | 19 | 34366362.95 | 34366362.95 | 0 | 25431108.58 | 25431108.58 | 0 |  |  |  | 25774772.21 | 2020-07-31 | 2020-08-19 | 2020-08-19 | 56 | 2020-10-14 | 2020-09-16 | 1243690773.07 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna19 | DPW Onshore Port & Terminal19
DP World Sokhna | 1 | 20 | 42996289.46 | 42996289.46 | 0 | 31817254.2 | 31817254.2 | 0 |  |  |  | 32247217.1 | 2020-08-31 | 2020-09-17 | 2020-09-17 | 56 | 2020-11-12 | 2020-10-13 | 1286687062.53 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna20 | DPW Onshore Port & Terminal20
DP World Sokhna | 1 | 21 | 34792442.43 | 34792442.42 | -0.01 | 25746407.39 | 25746407.4 | 0.01 |  |  |  | 26094331.82 | 2020-09-30 | 2020-10-15 | 2020-10-15 | 56 | 2020-12-10 | 2020-10-28 | 1321479504.96 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna21 | DPW Onshore Port & Terminal21
DP World Sokhna | 1 | 22 | 23946448.24 | 23946448.25 | 0.01 | 17720371 | 17720371.7 | 0.7 |  |  |  | 17959836.19 | 2020-10-31 | 2020-11-13 | 2020-11-13 | 56 | 2021-01-08 | 2020-12-20 | 1345425953.2 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna22 | DPW Onshore Port & Terminal22
DP World Sokhna | 1 | 23 | 35871966.38 | 35871966.38 | 1.1921e-07 | 26545255.12 | 26545255.12 | 0 |  |  |  | 26903974.78 | 2020-11-30 | 2020-12-10 | 2020-12-15 | 56 | 2021-02-09 | 2021-01-19 | 1381297919.58 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna23 | DPW Onshore Port & Terminal23
DP World Sokhna | 1 | 24 | 28199021.24 | 28199021.24 | 0 | 20867275.72 | 20867275.72 | 0 |  |  |  | 21149265.93 | 2020-12-31 | 2021-01-10 | 2021-01-10 | 56 | 2021-03-07 | 2021-02-15 | 1409496940.82 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna24 | DPW Onshore Port & Terminal24
DP World Sokhna | 1 | 25 | 13937299.51 | 13937299.51 | 0 | 10313601.64 | 10313601.63 | -0.01 |  |  |  | 10452974.64 | 2021-01-31 | 2021-02-16 | 2021-02-17 | 56 | 2021-04-14 | 2021-03-21 | 1423434240.33 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna25 | DPW Onshore Port & Terminal25
DP World Sokhna | 1 | 26 | 30564756.18 | 30564756.18 | -7.0781e-08 | 22617919.57 | 22617919.57 | 0 |  |  |  | 22923567.13 | 2021-02-28 | 2021-03-17 | 2021-03-25 | 56 | 2021-05-20 | 2021-04-14 | 1453998996.51 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna26 | DPW Onshore Port & Terminal26
DP World Sokhna | 1 | 27 | 21307969.76 | 21307969.76 | 0 | 15718793.62 | 15718793.62 | 0 |  |  |  | 15980977.32 | 2021-03-31 | 2021-04-15 | 2021-04-15 | 56 | 2021-06-10 | 2021-05-19 | 1475306966.27 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna27 | DPW Onshore Port & Terminal27
DP World Sokhna | 1 | 28 | 27099548.45 | 27099548.46 | 0.0099999 | 19977105.85 | 19977105.85 | 0 |  |  |  | 20324661.34 | 2021-05-31 | 2021-05-23 | 2021-05-23 | 56 | 2021-07-18 | 2021-06-24 | 1502406514.72 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna28 | DPW Onshore Port & Terminal28
DP World Sokhna | 1 | 29 | 27690935.6 | 27690935.6 | 1.0058e-07 | 20394668.34 | 20394668.34 | 0 |  |  |  | 20768201.7 | 2021-06-30 | 2021-06-24 | 2021-06-24 | 56 | 2021-08-19 | 2021-07-30 | 1530097450.32 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna29 | DPW Onshore Port & Terminal29
DP World Sokhna | 1 | 30 | 14579181.6 | 14579181.6 | -1.397e-07 | 10739490.38 | 10739490.38 | 0 |  |  |  | 10934386.2 | 2021-07-31 | 2021-07-29 | 2021-07-29 | 56 | 2021-09-23 | 2021-09-07 | 1544676631.92 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna30 | DPW Onshore Port & Terminal30
DP World Sokhna | 1 | 31 | 13597917.64 | 13597917.63 | -0.0099999 | 10014939.05 | 10014939.05 | 0 |  |  |  | 10198438.22 | 2021-08-31 | 2021-09-02 | 2021-09-02 | 56 | 2021-10-28 | 2021-10-11 | 1558274549.56 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna31 | DPW Onshore Port & Terminal31
DP World Sokhna | 1 | 32 | 16694467.33 | 16694467.33 | -1.6019e-07 | 12304801.83 | 12304801.83 | 0 |  |  |  | 12520850.5 | 2021-09-30 | 2021-10-05 | 2021-10-13 | 56 | 2021-12-08 | 2021-12-19 | 1574969016.89 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna32 | DPW Onshore Port & Terminal32
DP World Sokhna | 1 | 33 | 20335452.71 | 20335452.72 | 0.01 | 15048235.01 | 15048235.01 | 0 |  |  |  | 15251589.54 | 2021-12-31 | 2021-12-22 | 2021-12-22 | 56 | 2022-02-16 | 2022-01-11 | 1595304469.6 | [6 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna33 | DPW Onshore Port & Terminal33
DP World Sokhna | 1 | 34 | 12548237.84 | 12548237.84 | -1.4901e-07 | 8899770.44 | 8899770.35 | -0.09 |  |  |  | 9025252.81 | 2022-03-31 | 2022-04-06 | 2022-04-06 | 56 | 2022-06-01 | 2022-04-12 | 1607852707.44 |  |  |  |  | 80392635.37 | 80392635.37 | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna34 | DPW Onshore Port & Terminal34
DP World Sokhna | 1 | 35 | 3275655.02 | 3275655.01 | -0.01 | 2915333 | 83471391.43 | 80556058.43 |  |  |  | 2948089.53 | 2022-04-30 | 2022-05-15 | 2022-05-15 | 56 | 2022-07-10 | 2022-06-08 | 1611128362.46 |  | 37040890.72 |  |  | 80556418.125 | 80556418.125 | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna35 | DPW Onshore Port & Terminal35
DP World Sokhna | 1 | 36 |  | 0 | 0 | 80556058.47 | 0 | -80556058.47 |  |  |  |  | 2022-05-31 | 2022-06-08 | 2022-06-08 | 56 | 2022-08-03 | [8 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna36 | DPW Onshore Port & Terminal36
DP World Sokhna | 1 | 37 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-02-28 | 2023-02-19 | 2023-02-19 | 56 | 2023-04-16 | [8 empty] | 0 | 0 | 0 | 0 | DPW Onshore Port & Terminal |  |  |  | DP World Sokhna37 | DPW Onshore Port & Terminal37
#N/A
DPW - Ph.02 | 1 | 1 | 23907099.3 | 24448993.55 | 541894.25 | 21783711.58 | 21759604.25 | -24107.33 |  |  |  | 21516389.4 | 2023-01-31 | 2023-01-25 | 2023-01-31 | 56 | 2023-03-28 | 2023-02-16 | 23907099.3 |  |  |  |  | 1195354.95 | 1195354.95 | 0 | 23907099.3 | 23907099.3 | 21516389.4 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.021 | DP World Basin 2 Ph21
DPW - Ph.02 | 1 | 2 | 30365704.8 | 62640096.58 | 32274391.78 | 84506660.86 | 19472869.78 | -65033791.08 |  |  |  | 19188213.6 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 56 | 2023-04-27 | 2023-03-22 | 54272804.1 |  |  |  |  | 2713640.25 | 2713640.25 | 0 | 30365704.8 | 54272804.1 | 19188213.6 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.022 | DP World Basin 2 Ph22
DPW - Ph.02 | 1 | 3 | 1809093.47 | 38504541.13 | 36695447.66 | 28493360.54 | 28493360.4387 | -0.1013 |  |  |  | 19827820.72 | 2023-03-31 | 2023-03-25 | 2023-04-03 | 56 | 2023-05-29 | 2023-03-27 | 56081897.57 |  |  |  |  | 2804094.925 | 2804094.925 | 0 | 1809093.47 | 56081897.57 | 19827820.72 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.023 | DP World Basin 2 Ph23
DPW - Ph.02 | 1 | 4 | 38567084.81 | 37025201.2 | -1541883.61 | 27398639.54 | 27398648.888 | 9.348 |  |  |  | 28925313.53 | 2023-04-30 | 2023-04-25 | 2023-05-08 | 56 | 2023-07-03 | 2023-06-08 | 94648982.38 |  |  |  |  | 9464898.3 | 9464898.3 | 0 | 38567084.81 | 94648982.38 | 28925313.53 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.024 | DP World Basin 2 Ph24
DPW - Ph.02 | 1 | 5 | 77833745.07 | 40682207.5 | -37151537.57 | 30104833.54 | 30104833.54 | 0 |  |  |  | 30561302.57 | 2023-05-31 | 2023-05-25 | 2023-06-03 | 56 | 2023-07-29 | 2023-06-25 | 172482727.45 |  |  |  |  | 8624122.5 | 8624122.5 | 0 | 77833745.07 | 172482727.45 | 30561302.57 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.025 | DP World Basin 2 Ph25
DPW - Ph.02 | 1 | 6 | 32227821.34 | 32175841.3 | -51980.04 | 23809772.84 | 23809772.84 | 0 |  |  |  | 24170866.16 | 2023-06-30 | 2023-06-25 | 2023-06-26 | 56 | 2023-08-21 | 2023-07-31 | 204710548.79 |  |  |  |  | 10235527.455 | 10235527.455 | 0 | 32227821.34 | 204710548.79 | 24170866.16 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.026 | DP World Basin 2 Ph26
DPW - Ph.02 | 1 | 7 | 21546507.22 | 21511754.48 | -34752.74 | 15918348.27 | 15918423.282 | 75.012 |  |  |  | 16159880.26 | 2023-07-31 | 2023-07-25 | 2023-08-01 | 56 | 2023-09-26 | 2023-08-28 | 226257056.01 |  |  |  |  | 11312852.785 | 11312852.785 | 0 | 21546507.22 | 226257056.01 | 16159880.26 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.027 | DP World Basin 2 Ph27
DPW - Ph.02 | 1 | 8 | 27781672.69 | 0 | -27781672.69 | 20524928.94 | 0 | -20524928.94 |  |  |  | 20836254.44 | 2023-08-31 | 2023-08-25 | 2023-09-04 | 56 | 2023-10-30 | 2023-09-04 | 254038728.7 |  |  |  |  | 12701936.435 | 12701936.435 | 0 | 27781672.69 | 254038728.7 | 20836254.44 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.028 | DP World Basin 2 Ph28
DPW - Ph.02 | 1 | 9 | 66926760.56 | 27736619.9 | -39190140.66 | 49445572.72 | 20524928.94 | -28920643.78 |  |  |  | 50195070.42 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 56 | 2023-11-28 | 2023-10-31 | 320965489.26 |  |  |  |  | 16048266 | 16048266 | 0 | 66926760.56 | 320965489.26 | 50195070.42 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.029 | DP World Basin 2 Ph29
DPW - Ph.02 | 1 | 10 | 59028304.35 | 66818227.5 | 7789923.15 | 34610141.8 | 49445488.36 | 14835346.56 |  |  |  | 44271228.34 | 2023-10-31 | 2023-10-25 | 2023-11-01 | 56 | 2023-12-27 | 2023-11-29 | 379993793.61 |  |  |  |  | 18999683 | 18999683 | 0 | 59028304.35 | 379993793.61 | 44271228.34 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0210 | DP World Basin 2 Ph210
DPW - Ph.02 | 1 | 11 | 54711779.1 | 58932579.7 | 4220800.6 | 40236573.85 | 43610108.98 | 3373535.13 |  |  |  | 40849045.03 | 2023-11-30 | 2023-11-25 | 2023-11-30 | 56 | 2024-01-25 | 2023-12-31 | 434705572.71 |  |  |  |  | 21735278.62 | 21735278.62 | 0 | 54711779.1 | 434705572.71 | 40849045.03 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0211 | DP World Basin 2 Ph211
DPW - Ph.02 | 1 | 12 | 17644384.08 | 54623534 | 36979149.92 | 15678173.8779 | 40236573.85 | 24558399.9721 |  |  |  | 15879945.92 | 2023-12-31 | 2023-12-25 | 2024-01-01 | 56 | 2024-02-26 | 2024-02-04 | 452349956.79 |  | 25824647.96 |  |  | 22617497.855 | 22617497.855 | 0 | 17644384.08 | 452349956.79 | 15879945.92 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0212 | DP World Basin 2 Ph212
DPW - Ph.02 | 1 | 13 | 13655091.11 | 17615925.7 | 3960834.59 | 18805485.48 | 15678173.87 | -3127311.61 |  |  |  | 18632592.11 | 2024-02-29 | 2024-03-09 | 2024-03-09 | 56 | 2024-05-04 | 2024-04-01 | 466005047.9 |  | 44215690.5 |  |  | 33822947.025 | 33822947.025 | 0 | 13655091.11 | 466005047.9 | 18632592.11 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0213 | DP World Basin 2 Ph213
DPW - Ph.02 | 1 | 14 | -0.0001 | 21130152.28 | 21130152.2801 | 35568315.9 | 18805485.48 | -16762830.42 |  |  |  | 35418927.4 | 2024-02-29 | 2024-03-10 | 2024-03-13 | 56 | 2024-05-08 | 2024-05-14 | 466005047.9 |  | 30459697.9 |  |  | 23300252.395 | 23300252.395 | 0 | -0.0001 | 466005047.9 | 35418927.4 | DP World Basin 2 Ph2 |  |  |  | DPW - Ph.0214 | DP World Basin 2 Ph214
#N/A
EGAT Pelletizing Plant | 1 | 1 | 5145072.89 | 120259964.16 | 115114891.27 | 16605643.54 | 83153826.7838 | 66548183.2438 | 10000000 |  |  | 4887819.25 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-15 | 5145072.89 | [6 empty] | 0 | 5145072.89 | 5145072.89 | 4887819.25 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant | 1 | 2 | 10496612.58 | 70957037.06 | 60460424.48 | 27019256.26 | 39460085.8972 | 12440829.6372 | 2000000 |  |  | 10124222.67 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 15641685.47 | [6 empty] | 0 | 10496612.58 | 15641685.47 | 10124222.67 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant | 1 | 3 | 4383722.29 | 18154275.33 | 13770553.04 | 59114716.8 | 7687509.5247 | -51427207.2753 | 5000000 |  |  | 4165165.88 | 2021-07-31 | 2021-07-31 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 20025407.76 | [6 empty] | 0 | 4383722.29 | 20025407.76 | 4165165.88 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant | 1 | 4 | 6320391.6 | 11231401.59 | 4911009.99 | 50190590.75 | 10595646.6638 | -39594944.0862 | 20500000 |  |  | 6104444.17 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-27 | 26345799.36 | [6 empty] | 0 | 6320391.6 | 26345799.36 | 6104444.17 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant4 | EGAT Pelletizing Plant4
EGAT Pelletizing Plant | 1 | 5 | 14624189 | 15488991.77 | 864802.77 | 142794796.93 | 14877796.7585 | -127917000.1715 | 28804143.3 |  |  | 14109093.06 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-20 | 40969988.36 | [6 empty] | 0 | 14624189 | 40969988.36 | 14109093.06 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant5 | EGAT Pelletizing Plant5
EGAT Pelletizing Plant | 1 | 6 | 11102739.54 | 12567056.14 | 1464316.6 | 160253665.39 | 11723923.507 | -148529741.883 | 100000000 |  |  | 10385277.48 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-14 | 52072727.9 | [6 empty] | 0 | 11102739.54 | 52072727.9 | 10385277.48 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant6 | EGAT Pelletizing Plant6
EGAT Pelletizing Plant | 1 | 7 | 14005522.66 | 14405251.96 | 399729.3 | 163147791.3 | 13543523.308 | -149604267.992 | 100000000 |  |  | 13304274.45 | 2021-11-30 | 2021-12-05 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-20 | 66078250.56 | [6 empty] | 0 | 14005522.66 | 66078250.56 | 13304274.45 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant7 | EGAT Pelletizing Plant7
EGAT Pelletizing Plant | 1 | 8 | 12121253.25 | 12428479.44 | 307226.19 | 241455129.95 | 11759283.892 | -229695846.058 | 200000000 |  |  | 11576342.49 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-18 | 78199503.81 | [6 empty] | 0 | 12121253.25 | 78199503.81 | 11576342.49 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant8 | EGAT Pelletizing Plant8
EGAT Pelletizing Plant | 1 | 9 | 15797419.96 | 16727419.96 | 930000 | 71197856.25 | 15809146.998 | -55388709.252 | 26309409.25 |  |  | 15046421.2 | 2022-01-31 | 2022-02-05 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 93996923.77 | [6 empty] | 0 | 15797419.96 | 93996923.77 | 15046421.2 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant9 | EGAT Pelletizing Plant9
EGAT Pelletizing Plant | 1 | 10 | 13671163.11 | 20568627.09 | 6897463.98 | 41034098.6 | 19539421.1 | -21494677.5 |  |  |  | 13017478.47 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-04-12 | 107668086.88 | [6 empty] | 0 | 13671163.11 | 107668086.88 | 13017478.47 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant10 | EGAT Pelletizing Plant10
EGAT Pelletizing Plant | 1 | 11 | 14893958.07 | 18647708.09 | 3753750.02 | 34151886.79 | 17868099.3045 | -16283787.4855 |  |  |  | 14300826.37 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-21 | 122562044.95 | [6 empty] | 0 | 14893958.07 | 122562044.95 | 14300826.37 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant11 | EGAT Pelletizing Plant11
EGAT Pelletizing Plant | 1 | 12 | 8116943.05 | 8815883.11 | 698940.06 | 23500000 | 8787503.2355 | -14712496.7645 |  |  |  | 7722438.9 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-23 | 130678988 |  | 5987660 |  |  |  |  | 0 | 8116943.05 | 130678988 | 7722438.9 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant12 | EGAT Pelletizing Plant12
EGAT Pelletizing Plant | 1 | 13 | 13958441.79 | 22599332.95 | 8640891.16 | 53397068.58 | 21971546.5175 | -31425522.0625 |  |  |  | 13285393.01 | 2022-05-31 | 2022-06-05 | 2022-06-12 | 42 | 2022-07-24 | 2022-07-05 | 144637429.79 |  | 6236391 |  |  |  |  | 0 | 13958441.79 | 144637429.79 | 13285393.01 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant13 | EGAT Pelletizing Plant13
EGAT Pelletizing Plant | 1 | 14 | 8283062.84 | 10176085.16 | 1893022.32 | 17794639.63 | 10704026.928 | -7090612.702 |  |  |  | 7877469.99 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-23 | 152920492.63 |  | 6321993.82 |  |  |  |  | 0 | 8283062.84 | 152920492.63 | 7877469.99 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant14 | EGAT Pelletizing Plant14
EGAT Pelletizing Plant | 1 | 15 | 20298475.01 | 20298475.24 | 0.23 | 29186530.1 | 19186530.252 | -9999999.848 |  |  |  | 19389514.84 | 2022-07-31 | 2022-08-10 | 2022-08-15 | 42 | 2022-09-26 | 2022-08-24 | 173218967.64 |  | 7381629.61 |  |  |  |  | 0 | 20298475.01 | 173218967.64 | 19389514.84 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant15 | EGAT Pelletizing Plant15
EGAT Pelletizing Plant | 1 | 16 | 14282809.35 | 14282809.35 | 0 | 23336148.65 | 14096166.6275 | -9239982.0225 |  |  |  | 14238994.72 | 2022-08-31 | 2022-09-10 | 2022-09-20 | 42 | 2022-11-01 | 2022-10-10 | 187501776.99 |  | 14084887.93 |  |  |  |  | 0 | 14282809.35 | 187501776.99 | 14238994.72 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant16 | EGAT Pelletizing Plant16
EGAT Pelletizing Plant | 1 | 17 | 16943574.98 | 37539699.74 | 20596124.76 | 39257376.65 | 15969082.719 | -23288293.931 |  |  |  | 16138518.46 | 2022-10-31 | 2022-10-25 | 2022-10-27 | 42 | 2022-12-08 | 2022-11-23 | 204445351.97 |  | 14506110.34 |  |  |  |  | 0 | 16943574.98 | 204445351.97 | 16138518.46 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant17 | EGAT Pelletizing Plant17
EGAT Pelletizing Plant | 1 | 18 | 13727755.25 | 930523.4 | -12797231.85 | 35000000 | 0 | -35000000 |  |  |  | 12845007.22 | 2022-11-30 | 2022-11-20 | 2022-11-24 | 42 | 2023-01-05 | 2022-12-19 | 218173107.22 |  | 14925857.7 |  |  |  |  | 0 | 13727755.25 | 218173107.22 | 12845007.22 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant18 | EGAT Pelletizing Plant18
EGAT Pelletizing Plant | 1 | 19 | 20329650.19 | 20329650.19 | 0 | 42197351.2 | 19169766.1895 | -23027585.0105 |  |  |  | 19373062.69 | 2022-12-31 | 2022-12-27 | 2022-12-27 | 42 | 2023-02-07 | 2023-02-14 | 238502757.41 |  | 15524807.77 |  |  |  |  | 0 | 20329650.19 | 238502757.41 | 19373062.69 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant19 | EGAT Pelletizing Plant19
EGAT Pelletizing Plant | 1 | 20 |  | 0 | 0 | 40000000 | 0 | -40000000 |  |  |  |  | 2023-03-31 | 2023-03-30 | 2023-03-30 | 42 | 2023-05-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant20 | EGAT Pelletizing Plant20
EGAT Pelletizing Plant | 1 | 21 |  | 37437141.5 | 37437141.5 | 20000000 | 38934627.165 | 18934627.165 |  |  |  |  | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant21 | EGAT Pelletizing Plant21
EGAT Pelletizing Plant | 1 | 22 |  | 0 | 0 | 50000000 | 0 | -50000000 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant22 | EGAT Pelletizing Plant22
EGAT Pelletizing Plant | 1 | 23 | 165505167.47 | 0 | -165505167.47 | 15000000 | 0 | -15000000 |  |  |  | 284426280.45 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 533590339.98 |  | 85167648 |  | 7000000 |  |  | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant23 | EGAT Pelletizing Plant23
EGAT Pelletizing Plant | 1 | 24 | 65988515.57 | 0 | -65988515.57 | 10000000 | 0 | -10000000 |  |  |  | 38934626.46 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 599578855.55 |  | 96518287.15 |  | 7000000 |  |  | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant24 | EGAT Pelletizing Plant24
EGAT Pelletizing Plant | 1 | 25 |  | 0 | 0 | 10000000 | 0 | -10000000 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant25 | EGAT Pelletizing Plant25
EGAT Pelletizing Plant - Admin Building | 1 | 1 | 61566718.68 | 120259964.16 | 58693245.48 | 0 | 83153826.7838 | 83153826.7838 |  |  |  | 27089356.22 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 61566718.68 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Admin Building1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant - Admin Building | 1 | 2 | 53673231.5 | 70957037.06 | 17283805.56 | 0 | 39460085.8972 | 39460085.8972 |  |  |  | 23616221.86 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 115239950.18 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Admin Building2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant - Admin Building | 1 | 3 |  | 18154275.33 | 18154275.33 | 0 | 7687509.5247 | 7687509.5247 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Admin Building3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant - Supply | 1 | 1 | 1390180.36 | 120259964.16 | 118869783.8 | 1570903.44 | 83153826.7838 | 81582923.3438 |  |  |  | 1584805.61 | 2023-07-31 | 2023-07-26 | 2023-07-26 | 42 | 2023-09-06 | 2023-07-26 | 1390180.36 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant - Supply1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Concrete Infra | 1 | 1 |  | 120259964.16 | 120259964.16 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Concrete Infra1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Mechanical Installation | 1 | 1 |  | 120259964.16 | 120259964.16 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installation1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-Mechanical Installation | 1 | wrong |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 |  |  | 42 | 1900-02-10 | [9 empty] | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Mechanical Installationwrong | EGAT Pelletizing Plantwrong
EGAT Pelletizing Plant-MEP | 1 | 1 | 2011978.5 | 120259964.16 | 118247985.66 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  | 2112577.42 | 2021-04-30 | 2021-04-30 | 2021-05-11 | 42 | 2021-06-22 | 2021-08-25 | 2011978.5 | [6 empty] | 0 | 2011978.5 | 2011978.5 | 2112577.42 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-MEP | 1 | 2 | 112937.5 | 70957037.06 | 70844099.56 | 1e-05 | 39460085.8972 | 39460085.8972 |  |  |  | 118584.38 | 2022-02-28 | 2022-02-22 | 2022-02-24 | 42 | 2022-04-07 | 2022-02-22 | 2124916 | [6 empty] | 0 | 112937.5 | 2124916 | 118584.38 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant-MEP | 1 | 3 | 1723067.19 | 18154275.33 | 16431208.14 | 1e-05 | 7687509.5247 | 7687509.5247 |  |  |  | 1329462.73 | 2022-05-31 | 2022-06-05 | 2022-06-06 | 42 | 2022-07-18 | 2023-02-12 | 3847983.19 | [6 empty] | 0 | 1723067.19 | 3847983.19 | 1329462.73 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant-MEP Coordination | 1 | 1 |  | 120259964.16 | 120259964.16 | 1e-05 | 83153826.7838 | 83153826.7838 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-MEP Coordination1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Water Tank | 1 | 1 | 3274479.04 | 120259964.16 | 116985485.12 | 3241734.16 | 83153826.7838 | 79912092.6238 |  |  |  | 3438202.99 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-22 | 3274479.04 | [6 empty] | 0 | 3274479.04 | 3274479.04 | 3438202.99 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank1 | EGAT Pelletizing Plant1
EGAT Pelletizing Plant-Water Tank | 1 | 2 | 2028589.79 | 70957037.06 | 68928447.27 | 2008304.1 | 39460085.8972 | 37451781.7972 |  |  |  | 2130019.28 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 5303068.83 | [6 empty] | 0 | 2028589.79 | 5303068.83 | 2130019.28 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank2 | EGAT Pelletizing Plant2
EGAT Pelletizing Plant-Water Tank | 1 | 3 | 725357.85 | 18154275.33 | 17428917.48 | 718104.27 | 7687509.5247 | 6969405.2547 |  |  |  | 761625.75 | 2021-07-31 | 2021-08-04 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 6028426.68 | [6 empty] | 0 | 725357.85 | 6028426.68 | 761625.75 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank3 | EGAT Pelletizing Plant3
EGAT Pelletizing Plant-Water Tank | 1 | 4 | 766173.48 | 11231401.59 | 10465228.11 | 758512.36 | 10595646.6638 | 9837134.3038 |  |  |  | 804482.15 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-05 | 6794600.16 | [6 empty] | 0 | 766173.48 | 6794600.16 | 804482.15 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank4 | EGAT Pelletizing Plant4
EGAT Pelletizing Plant-Water Tank | 1 | 5 | 923594.34 | 15488991.77 | 14565397.43 | 914358.66 | 14877796.7585 | 13963438.0985 |  |  |  | 969774.05 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-12 | 7718194.5 | [6 empty] | 0 | 923594.34 | 7718194.5 | 969774.05 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank5 | EGAT Pelletizing Plant5
EGAT Pelletizing Plant-Water Tank | 1 | 6 | 1464316.6 | 12567056.14 | 11102739.54 | 1449673.43 | 11723923.507 | 10274250.077 |  |  |  | 1537532.43 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-09 | 9182511.1 | [6 empty] | 0 | 1464316.6 | 9182511.1 | 1537532.43 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank6 | EGAT Pelletizing Plant6
EGAT Pelletizing Plant-Water Tank | 1 | 7 | 399729.3 | 14405251.96 | 14005522.66 | 395732.02 | 13543523.308 | 13147791.288 |  |  |  | 419715.76 | 2021-11-30 | 2021-12-06 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-09 | 9582240.4 | [6 empty] | 0 | 399729.3 | 9582240.4 | 419715.76 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank7 | EGAT Pelletizing Plant7
EGAT Pelletizing Plant-Water Tank | 1 | 8 | 307226.2 | 12428479.44 | 12121253.24 | 304153.94 | 11759283.892 | 11455129.952 |  |  |  | 322587.51 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-06 | 9889466.6 | [6 empty] | 0 | 307226.2 | 9889466.6 | 322587.51 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank8 | EGAT Pelletizing Plant8
EGAT Pelletizing Plant-Water Tank | 1 | 9 | 1064224 | 16727419.96 | 15663195.96 | 967200 | 15809146.998 | 14841946.998 |  |  |  | 1117435.2 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-03-02 | 10953690.6 | [6 empty] | 0 | 1064224 | 10953690.6 | 1117435.2 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank9 | EGAT Pelletizing Plant9
EGAT Pelletizing Plant-Water Tank | 1 | 10 | 3540729.8 | 20568627.09 | 17027897.29 | 3505322.5 | 19539421.1 | 16034098.6 |  |  |  | 3717766.29 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-14 | 14494420.4 | [6 empty] | 0 | 3540729.8 | 14494420.4 | 3717766.29 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank10 | EGAT Pelletizing Plant10
EGAT Pelletizing Plant-Water Tank | 1 | 11 | 3753750.32 | 18647708.09 | 14893957.77 | 3903900.34 | 17868099.3045 | 13964198.9645 |  |  |  | 3941437.84 | 2022-03-31 | 2022-03-05 | 2022-06-06 | 42 | 2022-07-18 | 2022-08-23 | 18248170.72 | [6 empty] | 0 | 3753750.32 | 18248170.72 | 3941437.84 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank11 | EGAT Pelletizing Plant11
EGAT Pelletizing Plant-Water Tank | 1 | 12 |  | 8815883.11 | 8815883.11 | 1e-05 | 8787503.2355 | 8787503.2355 |  |  |  |  | 2022-09-30 | 2022-09-15 | 2022-09-19 | 42 | 2022-10-31 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank12 | EGAT Pelletizing Plant12
EGAT Pelletizing Plant-Water Tank | 1 | 13 |  | 22599332.95 | 22599332.95 | 391272.95 | 21971546.5175 | 21580273.5675 |  |  |  |  | 2022-10-31 | 2022-10-10 | 2022-11-01 | 42 | 2022-12-13 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank13 | EGAT Pelletizing Plant13
EGAT Pelletizing Plant-Water Tank | 1 | 14 |  | 10176085.16 | 10176085.16 | 1e-05 | 10704026.928 | 10704026.928 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank14 | EGAT Pelletizing Plant14
EGAT Pelletizing Plant-Water Tank | 1 | 15 | 0.19 | 20298475.24 | 20298475.05 | 0 | 19186530.252 | 19186530.252 |  |  |  | 2909387.53 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 21082133.03 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Pelletizing Plant |  |  |  | EGAT Pelletizing Plant-Water Tank15 | EGAT Pelletizing Plant15
EGAT-Asphalt | 1 | 1 |  | 0 | 0 | 598688 | 0 | -598688 |  |  |  |  | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Asphalt1 | 01
EGAT-Fence | 1 | 1 |  | 0 | 0 | 195752.6 | 0 | -195752.6 |  |  |  |  | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence1 | 01
EGAT-Fence | 1 | 2 | -616810.92 | 0 | 616810.92 | 0.001 | 0 | -0.001 |  |  |  | -575046.5692 | 2019-08-31 | 2019-08-31 | 2019-09-10 | 15 | 2019-09-25 | 2019-10-08 | 18362278.12 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence2 | 02
EGAT-Fence | 1 | 3 |  | 0 | 0 | 695045.6828 | 0 | -695045.6828 |  |  |  |  | 2019-09-30 | 2019-09-30 | 2019-10-14 | 15 | 2019-10-29 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence3 | 03
EGAT-Fence | 1 | 4 |  | 0 | 0 | 2891036.0622 | 0 | -2891036.0622 |  |  |  |  | 2019-10-31 | 2019-12-19 | 2020-02-09 | 15 | 2020-02-24 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Fence4 | 04
EGAT-HeliPad | 1 | 1 |  | 0 | 0 | 755798.13 | 0 | -755798.13 |  |  |  |  | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-HeliPad1 | 01
EGAT-HeliPad | 1 | 2 |  | 0 | 0 | 500000 | 0 | -500000 |  |  |  |  | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-HeliPad2 | 02
EGAT-Lock & Load | 1 | 1 | 5018202.5 | 5018202.5 | 0 | 10117110.35 | 4717110.345 | -5400000.005 |  |  |  | 4767292.38 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 5018202.5 | [6 empty] | 0 | 5018202.5 | 5018202.5 | 4767292.38 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load1 | EGAT Lock & Load1
EGAT-Lock & Load | 1 | 2 | 2362059.16 | 2362059.16 | 0 | 2773213.88 | 2220335.608 | -552878.272 |  |  |  | 2243956.2 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-06 | 7380261.66 | [6 empty] | 0 | 2362059.16 | 7380261.66 | 2243956.2 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load2 | EGAT Lock & Load2
EGAT-Lock & Load | 1 | 3 | 1772326.51 | 1772326.5 | -0.01 | 1665986.92 | 1665986.905 | -0.015 |  |  |  | 1683710.18 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-12 | 9152588.17 | [6 empty] | 0 | 1772326.51 | 9152588.17 | 1683710.18 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load3 | EGAT Lock & Load3
EGAT-Lock & Load | 1 | 4 |  | 879124 | 879124 | 747255.39 | 826376.56 | 79121.17 |  |  |  |  | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load4 | EGAT Lock & Load4
EGAT-Lock & Load | 1 | 5 | 3180176.34 | 3180176.34 | 0 | 2436487.51 | 2989365.767 | 552878.257 |  |  |  | 3021167.52 | 2022-05-31 | 2022-05-28 | 2022-06-06 | 42 | 2022-07-18 | 2022-06-07 | 13211888.51 | [6 empty] | 0 | 3180176.34 | 13211888.51 | 3021167.52 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load5 | EGAT Lock & Load5
EGAT-Lock & Load | 1 | 6 | 3378839.59 | 3378839.59 | 0 | 3176089.21 | 3176109.2095 | 19.9995 |  |  |  | 3209897.61 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-07-06 | 16590728.1 | [6 empty] | 0 | 3378839.59 | 16590728.1 | 3209897.61 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load6 | EGAT Lock & Load6
EGAT-Lock & Load | 1 | 7 | 1415984.07 | 1415984.07 | -1.8626e-09 | 1319107.49 | 1331025.0235 | 11917.5335 |  |  |  | 1345184.87 | 2022-07-31 | 2022-08-10 | 2022-08-16 | 42 | 2022-09-27 | 2022-08-16 | 18006712.17 | [6 empty] | 0 | 1415984.07 | 18006712.17 | 1345184.87 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load7 | EGAT Lock & Load7
EGAT-Lock & Load | 1 | 8 | 2786604.1 | 2786604.1 | 0 | 2619387.85 | 2619407.855 | 20.005 |  |  |  | 2647273.89 | 2022-08-31 | 2022-09-10 | 2022-09-11 | 42 | 2022-10-23 | 2022-09-11 | 20793316.27 | [6 empty] | 0 | 2786604.1 | 20793316.27 | 2647273.89 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load8 | EGAT Lock & Load8
EGAT-Lock & Load | 1 | 9 | 3980460.75 | 3980460.75 | 0 | 3741613.11 | 3741633.0975 | 19.9875 |  |  |  | 3781437.71 | 2022-09-30 | 2022-09-10 | 2022-10-17 | 42 | 2022-11-28 | 2022-10-18 | 24773777.02 | [6 empty] | 0 | 3980460.75 | 24773777.02 | 3781437.71 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load9 | EGAT Lock & Load9
EGAT-Lock & Load | 1 | 10 | 1157252.56 | 1157252.56 | 0 | 1099389.93 | 1087817.398 | -11572.532 |  |  |  | 1099389.93 | 2022-10-31 | 2022-10-31 | 2022-11-01 | 42 | 2022-12-13 | 2022-11-03 | 25931029.58 | [6 empty] | 0 | 1157252.56 | 25931029.58 | 1099389.93 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load10 | EGAT Lock & Load10
EGAT-Lock & Load | 1 | 11 | 1992889.65 | 1992889.65 | -2.3283e-09 | 1873296.27 | 1873316.2725 | 20.0025 |  |  |  | 1893245.16 | 2022-11-30 | 2022-11-30 | 2022-11-30 | 42 | 2023-01-11 | 2022-12-07 | 27923919.23 | [6 empty] | 0 | 1992889.65 | 27923919.23 | 1893245.16 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load11 | EGAT Lock & Load11
EGAT-Lock & Load | 1 | 12 | 1778896.47 | 1778896.47 | 0 | 1672142.68 | 1672162.6835 | 20.0035 |  |  |  | 1689951.65 | 2022-12-31 | 2022-12-25 | 2022-12-28 | 42 | 2023-02-08 | 2022-12-28 | 29702815.7 | [6 empty] | 0 | 1778896.47 | 29702815.7 | 1689951.65 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load12 | EGAT Lock & Load12
EGAT-Lock & Load | 1 | 13 | 2116780.43 | 2116780.44 | 0.01 | 1e-05 | 1989773.622 | 1989773.622 |  |  |  | 2010941.41 | 2023-01-31 | 2023-01-31 | 2023-02-01 | 42 | 2023-03-15 | 2023-02-07 | 31819596.13 | [6 empty] | 0 | 2116780.43 | 31819596.13 | 2010941.41 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load13 | EGAT Lock & Load13
EGAT-Lock & Load | 1 | 14 | 2768145.62 | 2768145.62 | 0 | 1e-05 | 2602056.8848 | 2602056.8848 |  |  |  | 2629738.34 | 2023-02-28 | 2023-02-28 | 2023-03-02 | 42 | 2023-04-13 | 2023-03-08 | 34587741.75 | [6 empty] | 0 | 2768145.62 | 34587741.75 | 2629738.34 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load14 | EGAT Lock & Load14
EGAT-Lock & Load | 1 | 15 |  | 19312258.25 | 19312258.25 | 1e-05 | 18153522.75 | 18153522.75 |  |  |  |  | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load15 | EGAT Lock & Load15
EGAT-Lock & Load | 1 | 16 |  | 1100000 | 1100000 | 1e-05 | 1134000.01 | 1134000.01 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load16 | EGAT Lock & Load16
EGAT-Lock & Load | 1 | 17 | -100000 | 0 | 100000 | 0 | 0 | 0 |  |  |  | 18153522.75 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-02-28 | 53900000 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load17 | EGAT Lock & Load17
EGAT-Lock & Load | 1 | 18 | 1100000 | 0 | -1100000 | 0 | 0 | 0 |  |  |  | 1134000 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 55000000 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Lock & Load |  |  |  | EGAT-Lock & Load18 | EGAT Lock & Load18
EGAT-SZ | 1 | 1 | 6085108 | 0 | -6085108 | 4624356.65 | 0 | -4624356.65 |  |  |  | 4624356.65 | 2019-03-31 | 2019-03-27 | 2019-03-27 | 15 | 2019-04-11 | 2019-04-01 | 6085108 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-SZ1 | 01
EGAT-SZ | 1 | 2 |  | 0 | 0 | 10000000 | 0 | -10000000 |  |  |  |  | 2019-03-31 | 2019-04-10 | 2019-04-03 | 15 | 2019-04-18 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-SZ2 | 02
EGAT-SZ | 1 | 3 |  | 0 | 0 | 6070502.71 | 0 | -6070502.71 |  |  |  |  | 2019-06-30 | 2019-06-26 | 2019-08-01 | 15 | 2019-08-16 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-SZ3 | 03
EGAT-Warehouse | 1 | 1 |  | 0 | 0 | 923651.335 | 0 | -923651.335 |  |  |  |  | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | EGAT-Warehouse1 | 01
#N/A
EIPICO | 1 | 1 | 9332911.16 | 12192163.2 | 2859252.04 | 180532933.37 | 12050858.57 | -168482074.8 | 83482074.8 |  |  | 12050858.57 | 2022-11-30 | 2022-11-25 | 2022-12-19 | 35 | 2023-01-23 | 2022-12-25 | 9332911.16 | 2859252.04 | 393834.3 |  |  | 304804.08 | 304804.08 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO1 | EPICO 3 Facility1
EIPICO | 1 | 2 | 13142288.21 | 13487203.1 | 344914.89 | 23338534.97 | 13338534.97 | -10000000 |  |  |  | 13338534.97 | 2022-12-31 | 2022-12-25 | 2022-12-27 | 35 | 2023-01-31 | 2023-02-20 | 22475199.37 | 3204166.92 | 795852.42 |  |  | 641984.155 | 641984.155 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO2 | EPICO 3 Facility2
EIPICO | 1 | 3 | 11426647.21 | 17810265.88 | 6383618.67 | 13033885 | 13033885 | 0 |  |  |  | 13033884.61 | 2023-01-31 | 2023-01-25 | 2023-02-12 | 35 | 2023-03-19 | 2023-03-14 | 33901846.58 | 4910817.01 | 1876208.86 |  | 611410.75 | 847546.165 | 847546.165 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO3 | EPICO 3 Facility3
EIPICO | 1 | 4 | 8374674.1725 | 8374674.18 | 0.0075 | 7344659 | 7344658.43 | -0.57 |  |  |  | 7345011.2 | 2023-02-28 | 2023-02-28 | 2023-02-27 | 35 | 2023-04-03 | 2023-03-15 | 42276520.7525 | 6456809.6644 | 3032593.7925 |  | 611410.7518 | 1056913.015 | 1056913.015 | 0 | 8374674.1725 | 42276520.7525 | 7345011.2 | EPICO 3 Facility |  |  |  | EIPICO4 | EPICO 3 Facility4
EIPICO | 1 | 5 | 13210447.2775 | 13210447.27 | -0.0075 | 10064340.12 | 10064340.12 | 0 |  |  |  | 10066271.07 | 2023-03-31 | 2023-03-31 | 2023-03-28 | 35 | 2023-05-02 | 2023-04-10 | 55486968.03 | 6862783.17 | 3640633.73 |  | 4882891.89 | 1387174.2 | 1387174.2 | 0 | 13210447.2775 | 55486968.03 | 10066271.07 | EPICO 3 Facility |  |  |  | EIPICO5 | EPICO 3 Facility5
EIPICO | 1 | 6 | 6910722.77 | 6910722.77 | 0 | 5949568.74 | 5949568.74 | 0 |  |  |  | 5949977.84 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 35 | 2023-06-05 | 2023-05-17 | 62397690.8 | 8009743.26 | 3788186.81 |  | 4882891.89 | 1559942.27 | 1559942.27 | 0 | 6910722.77 | 62397690.8 | 5949977.84 | EPICO 3 Facility |  |  |  | EIPICO6 | EPICO 3 Facility6
EIPICO | 1 | 7 | 1928406.33 | 7955142.87 | 6026736.54 | 6395645.73 | 6395645.73 | 0 |  |  |  | 6395645.73 | 2023-05-31 | 2023-05-30 | 2023-06-13 | 35 | 2023-07-18 | 2023-07-16 | 64326097.13 | 8718966.12 | 6026736.54 |  | 4882891.89 | 1758820.84 | 1758820.84 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO7 | EPICO 3 Facility7
EIPICO | 1 | 8 | 24151774.29 | 18125037.75 | -6026736.54 | 20317361.34 | 20317361.34 | 0 |  |  |  | 20317361.34 | 2023-06-30 | 2023-06-30 | 2023-07-06 | 35 | 2023-08-10 | 2023-08-31 | 88477871.42 | 17971072.1 | 8593156.6 |  | 15010831.83 | 2211946.785 | 2211946.785 | 0 | 24151774.29 | 88477871.42 | 20317779.3 | EPICO 3 Facility |  |  |  | EIPICO8 | EPICO 3 Facility8
EIPICO | 1 | 9 | 35000000 | 35000000 | 0 | 34650000 | 34650000 | 0 |  |  |  | 34650000 | 2023-07-31 | 2023-07-31 | 2023-08-02 | 35 | 2023-09-06 | 2023-08-22 | 123477871.42 | 17971072.1 | 43593156.6 |  | 15010831.83 | 3086946.785 | 3086946.785 | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO9 | EPICO 3 Facility9
EIPICO | 1 | 10 | 9818518.79 | 9818518.79 | 0 | 1e-05 | 0 | -1e-05 |  |  |  | 6328465.78 | 2023-07-31 | 2023-07-31 | 2023-08-28 | 35 | 2023-10-02 | 2023-10-29 | 133296390.21 | 16843609 | 47694027.06 |  | 15663610.71 | 3332409.755 | 3332409.755 | 0 | 9818518.79 | 133296390.21 | 6328837.05 | EPICO 3 Facility |  |  |  | EIPICO10 | EPICO 3 Facility10
EIPICO | 1 | 11 | 27259074.64 | 27259074.64 | 0 | 23263190.12 | 23263190.12 | 0 |  |  |  | 30654533.46 | 2023-09-30 | 2023-09-30 | 2023-10-10 | 35 | 2023-11-14 | 2023-11-28 | 160555464.85 | 30897743.79 | 49443090.43 |  | 24919582.39 | 4013886.62 | 4013886.62 | 0 | 27259074.64 | 160555464.85 | 30655535.07 | EPICO 3 Facility |  |  |  | EIPICO11 | EPICO 3 Facility11
EIPICO | 1 | 12 | 13086699.85 | 13086699.86 | 0.01 | 25548194.95 | 25548194.95 | 0 |  |  |  | 25548194.95 | 2023-10-31 | 2023-10-31 | 2023-10-29 | 35 | 2023-12-03 | 2024-01-02 | 173642164.7 | 56153346.77 | 51092750.03 |  | 24919582.39 | 4341054.12 | 4341054.12 | 0 | 13086699.85 | 173642164.7 | 28595406.99 | EPICO 3 Facility |  |  |  | EIPICO12 | EPICO 3 Facility12
EIPICO | 1 | 13 | 50645327.08 | 50645327.08 | 0 | 2882568.41 | 2882568.41 | 0 |  |  |  | 3870916.75 | 2023-11-30 | 2023-11-30 | 2023-12-03 | 35 | 2024-01-07 | 2024-01-01 | 224287491.78 | 34066592.92 | 51710056.53 |  | 25596151.45 | 5607188.795 | 5607188.795 | 1e-05 | 50645387.03 | 224287551.73 | 3870961.12 | EPICO 3 Facility |  |  |  | EIPICO13 | EPICO 3 Facility13
EIPICO | 1 | 14 | 69127504.85 | 69127444.9 | -59.95 | 26305980.07 | 36305980.07 | 10000000 |  |  |  | 26305980.07 | 2023-12-31 | 2023-12-31 | 2024-01-06 | 35 | 2024-02-10 | 2024-03-07 | 293414996.63 | 36975442.25 | 57799027.37 |  | 60908341.96 | 7335374.915 | 7335374.915 | 0 | 69127444.9 | 293414996.63 | 26305980.07 | EPICO 3 Facility |  |  |  | EIPICO14 | EPICO 3 Facility14
EIPICO | 1 | 15 | 41894786.25 | 41894786.25 | 0 | 29236256.89 | 29236255.9825 | -0.9075 |  |  |  | 29236256.02 | 2024-01-31 | 2024-01-31 | 2024-02-04 | 35 | 2024-03-10 | 2024-03-20 | 335309782.88 | 34393385.98 | 69350170.39 |  | 63104446.32 | 8382744.57 | 8382744.57 | 0 | 41894786.25 | 335309782.88 | 58472512.04 | EPICO 3 Facility |  |  |  | EIPICO15 | EPICO 3 Facility15
EIPICO | 1 | 16 | 54812520.11 | 54812520.18 | 0.07 | 26363887.4 | 26363887.4 | 0 |  |  |  | 26365248.98 | 2024-03-31 | 2024-03-31 | 2024-04-03 | 35 | 2024-05-08 | 2024-04-24 | 390122302.99 | 33031508.83 | 74589819.54 |  | 94064398.16 | 9753057.575 | 9753057.575 | 0 | 54812520.11 | 390122302.99 | 26365248.98 | EPICO 3 Facility |  |  |  | EIPICO16 | EPICO 3 Facility16
EIPICO | 1 | 17 | 30260072.01 | 30615959.94 | 355887.93 | 13161378.75 | 13161378.737 | -0.013 |  |  |  | 13161378 | 2024-04-30 | 2024-04-30 | 2024-05-28 | 35 | 2024-07-02 | 2024-06-13 | 420382375 | 32932557 | 81926235 |  | 110270621 | 10518279.5 | 10518279.5 | 0 | 30260072.01 | 420382375 | 13161378 | EPICO 3 Facility |  |  |  | EIPICO17 | EPICO 3 Facility17
EIPICO | 1 | 18 | 61471115.83 | 61115227.87 | -355887.96 | 35188037.3 | 35188037.3 | 0 |  |  |  | 38010351.15 | 2024-06-30 | 2024-06-30 | 2024-07-15 | 35 | 2024-08-19 | 2024-07-30 | 481853490.83 | 27876972.92 | 86364959.21 |  | 143970319.09 | 12046337.27 | 12046337.27 | 0 | 61471115.83 | 481853490.83 | 38010351.15 | EPICO 3 Facility |  |  |  | EIPICO18 | EPICO 3 Facility18
EIPICO | 1 | 19 | 35463786.17 | 35463786.32 | 0.15 | 22436578.36 | 22436578.356 | -0.004 |  |  |  | 22436578.36 | 2024-08-31 | 2024-08-31 | 2024-09-03 | 35 | 2024-10-08 | 2024-10-26 | 517317277 | 23341078 | 95950976 |  | 145234855 | 12932931.5 | 12932931.5 | 17754935 | 35463786.17 | 517317277 | 29978125.14 | EPICO 3 Facility |  |  |  | EIPICO19 | EPICO 3 Facility19
EIPICO | 1 | 20 |  | 71749002.23 | 71749002.23 | 20000000 | 62225320.01 | 42225320.01 |  |  |  |  | 2024-09-30 | 2024-09-30 | 2024-10-29 | 35 | 2024-12-03 | [8 empty] | 0 | 0 | 0 | 0 | EPICO 3 Facility |  |  |  | EIPICO20 | EPICO 3 Facility20
#N/A
El Sewedy Uni.-PKG.1 | 1 | 1 | 2762087.0381 | 1805053.36 | -957033.6781 | 1917993.24 | 1727255.568 | -190737.672 |  |  |  | 2002513.1 | 2018-07-31 | 2018-08-31 | 2018-09-03 | 4 | 2018-10-19 | 2018-10-15 | 2762087.0381 | 0 | [5 empty] | 0 | 2762087.0381 | 2762087.0381 | 2002513.1 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.11 | Elsewedy Univ - Enabling Works1
El Sewedy Uni.-PKG.1 | 1 | 2 | 1370079.6319 | 9832451.04 | 8462371.4081 | 881744.36 | 9096115.222 | 8214370.862 |  |  |  | 951383.3 | 2018-09-30 | 2018-10-15 | 2018-10-18 | 4 | 2018-10-29 | 2018-10-25 | 4132166.67 | [6 empty] | 0 | 1370079.6319 | 4132166.67 | 951383.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.12 | Elsewedy Univ - Enabling Works2
El Sewedy Uni.-PKG.1 | 1 | 3 | 1749696.33 | 10413552.39 | 8663856.06 | 1214989 | 10213661.2305 | 8998672.2305 |  |  |  | 1214989.1272 | 2018-10-31 | 2018-11-15 | 2018-11-14 | 4 | 2018-12-01 | 2018-11-27 | 5881863 | [6 empty] | 0 | 1749696.33 | 5881863 | 1214989.1272 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.13 | Elsewedy Univ - Enabling Works3
El Sewedy Uni.-PKG.1 | 1 | 4 | 1734033.5 | 2548899.1 | 814865.6 | 1204112.8596 | 1785482.76 | 581369.9004 |  |  |  | 1204112.8596 | 2018-11-30 | 2018-11-30 | 2018-12-02 | 4 | 2018-12-14 | 2018-12-10 | 7615896.5 | [6 empty] | 0 | 807197.6524 | 7615896.5 | 1204112.8596 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.14 | Elsewedy Univ - Enabling Works4
El Sewedy Uni.-PKG.1 | 1 | 5 | 267331.59 | 26249903.38 | 25982571.79 | 185635.0557 | 125621602.973 | 125435967.9173 |  |  |  | 185635.0557 | 2018-12-31 | 2018-12-15 | 2018-12-17 | 4 | 2018-12-22 | 2018-12-18 | 7883228.09 | [6 empty] | 0 | 267331.59 | 7883228.09 | 185635.0557 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.15 | Elsewedy Univ - Enabling Works5
El Sewedy Uni.-PKG.1 | 1 | 6 | 205504.28 | 41901505.6 | 41696001.32 | 142702.12 | 27378382.8135 | 27235680.6935 |  |  |  | 142702.1677 | 2018-12-31 | 2018-12-25 | 2018-12-29 | 4 | 2019-01-12 | 2019-01-08 | 8088732.37 | [6 empty] | 0 | 205504.28 | 8088732.37 | 142702.1677 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.16 | Elsewedy Univ - Enabling Works6
El Sewedy Uni.-PKG.1 | 1 | 7 | 410253.12 | 46029832.92 | 45619579.8 | 284879.77 | 39973819.3095 | 39688939.5395 |  |  |  | 284879.76 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 4 | 2019-01-26 | 2019-01-22 | 8498985.49 | [6 empty] | 0 | 410253.12 | 8498985.49 | 284879.76 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.17 | Elsewedy Univ - Enabling Works7
El Sewedy Uni.-PKG.1 | 1 | 8 | 339720.12 | 23803040.59 | 23463320.47 | 235901.48 | 14971243.825 | 14735342.345 |  |  |  | 235901.6556 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 4 | 2019-02-10 | 2019-02-06 | 8838705.61 | [6 empty] | 0 | 339720.12 | 8838705.61 | 235901.6556 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.18 | Elsewedy Univ - Enabling Works8
El Sewedy Uni.-PKG.1 | 1 | 9 | 104805.89 | 43474156.5 | 43369350.61 | 72777.3 | 19546532.045 | 19473754.745 |  |  |  | 72777.3 | 2019-03-31 | 2019-03-25 | 2019-03-26 | 4 | 2019-04-14 | 2019-04-10 | 8943511.5 | [6 empty] | 0 | 104805.89 | 8943511.5 | 72777.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.19 | Elsewedy Univ - Enabling Works9
El Sewedy Uni.-PKG.1 | 1 | 10 | 2360 | 30617684.7 | 30615324.7 | -8913.92 | 20919758.826 | 20928672.746 |  |  |  | -8913.92 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 4 | 2019-08-11 | 2019-08-07 | 8945871.5 | [6 empty] | 0 | 2360 | 8945871.5 | -8913.92 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.110 | Elsewedy Univ - Enabling Works10
El Sewedy Uni.-PKG.2 | 1 | 1 | 4165158.06 | 1805053.36 | -2360104.7 | 3110956.56 | 1727255.568 | -1383700.992 |  |  |  | 3110956.56 | 2018-09-30 | 2018-09-25 | 2018-09-27 | 17 | 2018-10-14 | 2018-10-18 | 4165158.06 | [6 empty] | 0 | 4165158.06 | 4165158.06 | 3110956.56 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.21 | Elsewedy Univ - Enabling Works1
El Sewedy Uni.-PKG.2 | 1 | 2 | 5976536.23 | 9832451.04 | 3855914.81 | 6754267.57 | 9096115.222 | 2341847.652 |  |  |  | 6088678.96 | 2018-10-31 | 2018-10-31 | 2018-10-31 | 17 | 2018-11-17 | 2018-11-08 | 10141694.29 | [6 empty] | 0 | 5976536.23 | 10141694.29 | 6088678.96 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.22 | Elsewedy Univ - Enabling Works2
El Sewedy Uni.-PKG.2 | 1 | 3 | 4458367.3606 | 10413552.39 | 5955185.0294 | 3212953.45 | 10213661.2305 | 7000707.7805 |  |  |  | 3212953.6168 | 2018-11-30 | 2018-11-25 | 2018-11-27 | 17 | 2018-12-14 | 2018-12-10 | 14600061.6506 | 2173392 | [5 empty] | 0 | 0 | 0 | 0 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.23 | Elsewedy Univ - Enabling Works3
El Sewedy Uni.-PKG.2 | 1 | 4 | 5121900.2295 | 2548899.1 | -2573001.1295 | 3208255.76 | 1785482.76 | -1422773 |  |  |  | 3208255.2815 | 2018-12-31 | 2018-12-25 | 2018-12-31 | 17 | 2019-01-17 | 2019-01-10 | 19721961.8801 | 1556100 | [5 empty] | 0 | 5121900.2295 | 19721961.8801 | 3208255.2815 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.24 | Elsewedy Univ - Enabling Works4
El Sewedy Uni.-PKG.2 | 1 | 5 | 8018043.8084 | 26249903.38 | 18231859.5716 | 4527299.68 | 125621602.973 | 121094303.293 |  |  |  | 4527299.6695 | 2019-01-31 | 2019-01-25 | 2019-01-31 | 17 | 2019-02-17 | 2019-02-10 | 27740005.6885 | [6 empty] | 0 | 8018043.8084 | 27740005.6885 | 4527299.6695 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.25 | Elsewedy Univ - Enabling Works5
El Sewedy Uni.-PKG.2 | 1 | 6 | 8105230.8115 | 41901505.6 | 33796274.7885 | 7457797.24 | 27378382.8135 | 19920585.5735 |  |  |  | 7457797.2 | 2019-02-28 | 2019-02-25 | 2019-03-02 | 17 | 2019-03-19 | 2019-03-11 | 35845236.5 | 1404000 | [5 empty] | 0 | 8105230.8115 | 35845236.5 | 7457797.2 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.26 | Elsewedy Univ - Enabling Works6
El Sewedy Uni.-PKG.2 | 1 | 7 | 4929812 | 46029832.92 | 41100020.92 | 2278076.64 | 39973819.3095 | 37695742.6695 |  |  |  | 2278076.6 | 2019-03-31 | 2019-03-25 | 2019-04-08 | 17 | 2019-04-25 | 2019-04-10 | 40775048.5 | 0 | [5 empty] | 0 | 4929812 | 40775048.5 | 2278076.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.27 | Elsewedy Univ - Enabling Works7
El Sewedy Uni.-PKG.2 | 1 | 8 | 1755356.8 | 23803040.59 | 22047683.79 | 2625161.63 | 14971243.825 | 12346082.195 |  |  |  | 2625161.5 | 2019-05-31 | 2019-05-23 | 2019-05-23 | 17 | 2019-06-09 | 2019-08-07 | 42530405.3 | [6 empty] | 50000 | 1755356.8 | 42530405.3 | 2625161.5 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.28 | Elsewedy Univ - Enabling Works8
El Sewedy Uni.-PKG.2 | 1 | 9 | 0 | 43474156.5 | 43474156.5 | 1116423 | 19546532.045 | 18430109.045 |  |  |  | 1116423.1 | 2020-03-31 | 2020-07-31 | 2020-03-22 |  | 2020-03-31 | 2020-03-23 | 42530405.3 | [6 empty] | 0 | 0 | 0 | 1116423.1 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.29 | Elsewedy Univ - Enabling Works9
El Sewedy Uni.-PKG.3 | 1 | 1 | 1805053.3662 | 1805053.36 | -0.00625 | 41698321.35 | 1727255.568 | -39971065.782 | 24971065.75 | 15000000 |  | 1727255.5662 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 14 | 2019-02-14 | 2019-02-18 | 1805053.3662 | [6 empty] | 0 | 1805053.3662 | 1805053.3662 | 1727255.5662 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.31 | Elsewedy Univ - Enabling Works1
El Sewedy Uni.-PKG.3 | 1 | 2 | 3340179.702 | 9832451.04 | 6492271.338 | 11185421.17 | 9096115.222 | -2089305.948 | 8000000 |  |  | 3185421.0011 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 14 | 2019-02-16 | 2019-02-19 | 3340179.702 | [6 empty] | 0 | 3340179.702 | 3340179.702 | 3185421.0011 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.32 | Elsewedy Univ - Enabling Works2
El Sewedy Uni.-PKG.3 | 1 | 3 | 2400436.8318 | 10413552.39 | 8013115.5582 | 17785718.63 | 10213661.2305 | -7572057.3995 | 12000000 |  |  | 5785718.6 | 2019-02-28 | 2019-02-21 | 2019-02-27 | 14 | 2019-03-13 | 2019-03-12 | 7545669.9 | 3477943.8 | [5 empty] | 0 | 2400436.8318 | 7545669.9 | 5785718.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.33 | Elsewedy Univ - Enabling Works3
El Sewedy Uni.-PKG.3 | 1 | 4 | 6026842.9 | 2548899.1 | -3477943.8 | 6716669.76 | 1785482.76 | -4931187 | 4931187 |  |  | 1785483.1 | 2019-03-31 | 2019-03-21 | 2019-03-24 | 14 | 2019-04-07 | 2019-04-10 | 13572512.8 | 4077447.9 | [5 empty] | 0 | 6026842.9 | 13572512.8 | 1785483.1 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.34 | Elsewedy Univ - Enabling Works4
El Sewedy Uni.-PKG.3 | 1 | 5 | 27458064.6 | 26249903.38 | -1208161.22 | 24218860.6 | 125621602.973 | 101402742.373 |  |  |  | 24218860.6 | 2019-04-30 | 2019-04-21 | 2019-04-23 | 14 | 2019-05-07 | 2019-05-05 | 41030577.4 | 16291927.3 | [5 empty] | 0 | 27458064.6 | 41030577.4 | 24218860.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.35 | Elsewedy Univ - Enabling Works5
El Sewedy Uni.-PKG.3 | 1 | 6 | 30765208.3 | 41901505.6 | 11136297.3 | 26716091.61 | 27378382.8135 | 662291.2035 |  |  |  | 26656864.3 | 2019-05-31 | 2019-05-25 | 2019-06-01 | 14 | 2019-06-15 | 2019-06-16 | 71795785.7 | 10815243.6 | [5 empty] | 0 | 30765208.3 | 71795785.7 | 26656864.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.36 | Elsewedy Univ - Enabling Works6
El Sewedy Uni.-PKG.3 | 1 | 7 | 41332921.1 | 46029832.92 | 4696911.82 | 22410862.51 | 39973819.3095 | 17562956.7995 |  |  |  | 22410862.51 | 2019-06-30 | 2019-07-04 | 2019-07-08 | 14 | 2019-07-22 | 2019-07-25 | 113128706.8 | 20405227.9 | [5 empty] | 0 | 41332921.1 | 113128706.8 | 22410862.51 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.37 | Elsewedy Univ - Enabling Works7
El Sewedy Uni.-PKG.3 | 1 | 8 | 23588218.3 | 23803040.59 | 214822.29 | 12292368.36 | 14971243.825 | 2678875.465 |  |  |  | 13598061.6 | 2019-07-31 | 2019-07-31 | 2019-08-08 | 14 | 2019-08-22 | 2019-08-24 | 136716925.1 | 16590818.6 | [5 empty] | 0 | 23588218.3 | 136716925.1 | 13598061.6 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.38 | Elsewedy Univ - Enabling Works8
El Sewedy Uni.-PKG.3 | 1 | 9 | 30130968 | 43474156.5 | 13343188.5 | 19287810.69 | 19546532.045 | 258721.355 |  |  |  | 19410255.3 | 2019-08-31 | 2019-08-21 | 2019-08-24 | 14 | 2019-09-07 | 2019-08-28 | 166847893.1 | 4696608.5 | [5 empty] | 0 | 30130968 | 166847893.1 | 19410255.3 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.39 | Elsewedy Univ - Enabling Works9
El Sewedy Uni.-PKG.3 | 1 | 10 | 28039187.7 | 30617684.7 | 2578497 | 20919758.8 | 20919758.826 | 0.026 |  |  |  | 20919758.8 | 2019-08-31 | 2019-09-10 | 2019-09-16 | 14 | 2019-09-30 | 2019-09-29 | 194887080.8 | 1904733.1 | [5 empty] | 0 | 28039187.7 | 194887080.8 | 20919758.8 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.310 | Elsewedy Univ - Enabling Works10
El Sewedy Uni.-PKG.3 | 1 | 11 | 16304632.1 | 17614054.86 | 1309422.76 | 2318161.39 | 16620031.47 | 14301870.08 |  |  |  | 2318168.2 | 2019-10-31 | 2019-10-31 | 2019-12-22 | 14 | 2020-01-05 | 2020-01-01 | 211191712.9 | [6 empty] | 3221774.75 | 0 | 0 | 0 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.311 | Elsewedy Univ - Enabling Works11
El Sewedy Uni.-PKG.3 | 1 | 12 | 0 | 0 | 0 | 1515470 | 0 | -1515470 |  |  |  | 1515470 | 2019-10-31 | 2019-10-31 | 2020-06-08 | 14 | 2020-06-22 | 2020-06-21 | 211191712.9 | [6 empty] | 1706304.8 | 0 | 0 | 1515470 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.312 | Elsewedy Univ - Enabling Works12
El Sewedy Uni.-PKG.3 | 1 | 13 |  | 0 | 0 | 6845790.3 | 0 | -6845790.3 |  |  |  |  | 2020-09-30 | 2020-09-17 | 2020-11-15 | 14 | 2020-11-29 | [8 empty] | 0 | 0 | 0 | 0 | Elsewedy Univ - Enabling Works |  |  |  | El Sewedy Uni.-PKG.313 | Elsewedy Univ - Enabling Works13
#N/A
Elco Steel | 1 | 1 | 17022109.47 | 0 | -17022109.47 | 13532577.04 | 0 | -13532577.04 |  |  |  | 13617687.58 | 2017-09-30 | 2017-10-01 | 2017-10-01 | 15 | 2017-10-16 | 2017-10-08 | 17022109.47 | [6 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel1 | Substation Elco Steel1
Elco Steel | 1 | 2 | 54045554.24 | 1669926.8 | -52375627.44 | 42881105.07 | 1160599.13 | -41720505.94 |  |  |  | 42881105.07 | 2017-10-31 | 2017-10-25 | 2017-10-25 | 15 | 2017-11-09 | 2017-10-29 | 71067663.71 | [6 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel2 | Substation Elco Steel2
Elco Steel | 1 | 3 | 68968024.81 | 2658220.39 | -66309804.42 | 54829579.72 | 1834172.07 | -52995407.65 |  |  |  | 54829579.72 | 2017-11-30 | 2017-11-30 | 2017-11-27 | 15 | 2017-12-12 | 2017-11-28 | 140035688.52 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel3 | Substation Elco Steel3
Elco Steel | 1 | 4 | 45198074.67 | 1838590.86 | -43359483.81 | 35932469.35 | 1268627.7 | -34663841.65 |  |  |  | 35932469.36 | 2017-12-31 | 2017-12-31 | 2017-12-27 | 15 | 2018-01-11 | 2018-01-02 | 185233763.18 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel4 | Substation Elco Steel4
Elco Steel | 1 | 5 | 15262763.5 | 5784479.69 | -9478283.81 | 12038252.26 | 4588851.87 | -7449400.39 |  |  |  | 12133896.98 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 200496526.68 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel5 | Substation Elco Steel5
Elco Steel | 1 | 6 | 23107300.22 | 3766431.24 | -19340868.98 | 20100303 | 2598837.56 | -17501465.44 |  |  |  | 19914658.95 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 223603826.9 | 0 | [5 empty] | 95644.72 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel6 | Substation Elco Steel6
Elco Steel | 1 | 7 | 9962100.82 | 3187107.5 | -6774993.32 | 7919870.17 | 2228843.15 | -5691027.02 |  |  |  | 7919870.15 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 233565927.72 | 0 | [5 empty] | 95644.72 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel7 | Substation Elco Steel7
Elco Steel | 1 | 8 | 7984975.64 | 2651758.28 | -5333217.36 | 6348055.64 | 1829713.22 | -4518342.42 |  |  |  | 6348055.64 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 241550903.36 | 0 | [5 empty] | 95644.72 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel8 | Substation Elco Steel8
Elco Steel | 1 | 9 | 1027177.94 | 1904763.72 | 877585.78 | 740665.09 | 1314286.96 | 573621.87 |  |  |  | 740665.1 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 242578081.3 | 0 | [5 empty] | 171586.08 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel9 | Substation Elco Steel9
Elco Steel | 1 | 10 | 5032217.21 | 4730762.03 | -301455.18 | 4000000 | 3744490.63 | -255509.37 |  |  |  | 4000612.68 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 247610298.51 | 0 | [5 empty] | 171586.08 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel10 | Substation Elco Steel10
Elco Steel | 1 | 11 | 8902176.76 | 4095222.62 | -4806954.14 | 7075101.66 | 3142902.52 | -3932199.14 |  |  |  | 7077230.5163 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 256512475.27 | 0 | [5 empty] | 171586.08 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel11 | Substation Elco Steel11
Elco Steel | 1 | 12 |  | 0 | 0 | 2485656 | 0 | -2485656 |  |  |  |  | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel12 | Substation Elco Steel12
Elco Steel | 1 | 13 |  | 0 | 0 | 2518616.18 | 0 | -2518616.18 |  |  |  |  | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel13 | Substation Elco Steel13
Elco Steel | 1 | 14 |  | 0 | 0 | 2857649.27 | 0 | -2857649.27 |  |  |  |  | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel14 | Substation Elco Steel14
Elco Steel | 1 | 15 |  | 0 | 0 | 1595365.5 | 0 | -1595365.5 |  |  |  |  | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel15 | Substation Elco Steel15
Elco Steel | 1 | 16 |  | 0 | 0 | 310509.31 | 0 | -310509.31 |  |  |  |  | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel16 | Substation Elco Steel16
Elco Steel | 1 | 17 |  | 0 | 0 | 1079101.72 | 0 | -1079101.72 |  |  |  |  | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel17 | Substation Elco Steel17
Elco Steel - ADMIN. | 1 | 1 | 1576783.88 | 0 | -1576783.88 | 1253543.1806 | 0 | -1253543.1806 |  |  |  | 1253543.1806 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 1576783.88 | [6 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.1 | Substation Elco Steel1
Elco Steel - ADMIN. | 1 | 2 | 3644932.88 | 1669926.8 | -1975006.08 | 2897721.63 | 1160599.13 | -1737122.5 |  |  |  | 2897721.64 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 5221716.76 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.2 | Substation Elco Steel2
Elco Steel - ADMIN. | 1 | 3 | 4011218.17 | 2658220.39 | -1352997.78 | 3188918.44 | 1834172.07 | -1354746.37 |  |  |  | 3188918.45 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 9232934.93 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.3 | Substation Elco Steel3
Elco Steel - ADMIN. | 1 | 4 | 4549688.44 | 1838590.86 | -2711097.58 | 3617002.31 | 1268627.7 | -2348374.61 |  |  |  | 3617002.31 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 13782623.37 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.4 | Substation Elco Steel4
Elco Steel - ADMIN. | 1 | 5 | 2288094.62 | 5784479.69 | 3496385.07 | 1819035.22 | 4588851.87 | 2769816.65 |  |  |  | 1819035.23 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 16070717.99 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.5 | Substation Elco Steel5
Elco Steel - ADMIN. | 1 | 6 | 6362324.03 | 3766431.24 | -2595892.79 | 5058047.58 | 2598837.56 | -2459210.02 |  |  |  | 5094386.24 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 22433042.02 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.6 | Substation Elco Steel6
Elco Steel - ADMIN. | 1 | 7 | 7233482.49 | 3187107.5 | -4046374.99 | 5750618.5816 | 2228843.15 | -3521775.4316 |  |  |  | 5750618.5816 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 29666524.51 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.7 | Substation Elco Steel7
Elco Steel - ADMIN. | 1 | 8 |  | 2651758.28 | 2651758.28 | 3289926.92 | 1829713.22 | -1460213.7 |  |  |  |  | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.8 | Substation Elco Steel8
Elco Steel - ADMIN. | 1 | 9 |  | 1904763.72 | 1904763.72 | 1940428 | 1314286.96 | -626141.04 |  |  |  |  | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.9 | Substation Elco Steel9
Elco Steel - ADMIN. | 1 | 10 |  | 4730762.03 | 4730762.03 | 2335545.55 | 3744490.63 | 1408945.08 |  |  |  |  | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.10 | Substation Elco Steel10
Elco Steel - ADMIN. | 1 | 11 |  | 4095222.62 | 4095222.62 | 2179703.08 | 3142902.52 | 963199.44 |  |  |  |  | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.11 | Substation Elco Steel11
Elco Steel - ADMIN. | 1 | 12 |  | 0 | 0 | 1394236.8 | 0 | -1394236.8 |  |  |  |  | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.12 | Substation Elco Steel12
Elco Steel - ADMIN. | 1 | 13 |  | 0 | 0 | 117652.86 | 0 | -117652.86 |  |  |  |  | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.13 | Substation Elco Steel13
Elco Steel - ADMIN. | 1 | 14 |  | 0 | 0 | 105992.48 | 0 | -105992.48 |  |  |  |  | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.14 | Substation Elco Steel14
Elco Steel - ADMIN. | 1 | 15 |  | 0 | 0 | 259861.3 | 0 | -259861.3 |  |  |  |  | 2019-03-31 | 2019-04-10 | 2019-04-16 | 15 | 2019-05-01 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - ADMIN.15 | Substation Elco Steel15
Elco Steel - MEP | 1 | 1 | 444736.0027 | 0 | -444736.0027 | 331328.322 | 0 | -331328.322 |  |  |  | 331328.322 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 444736.0027 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP1 | Substation Elco Steel1
Elco Steel - MEP | 1 | 2 | 2764965.97 | 1669926.8 | -1095039.17 | 2059899.63 | 1160599.13 | -899300.5 |  |  |  | 2059899.65 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 3209701.97 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP2 | Substation Elco Steel2
Elco Steel - MEP | 1 | 3 | 2666446.92 | 2658220.39 | -8226.53 | 1986502.95 | 1834172.07 | -152330.88 |  |  |  | 1986502.96 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 5876148.87 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP3 | Substation Elco Steel3
Elco Steel - MEP | 1 | 4 | 3362790.38 | 1838590.86 | -1524199.52 | 2505278.83 | 1268627.7 | -1236651.13 |  |  |  | 2505278.83 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 9238939.25 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP4 | Substation Elco Steel4
Elco Steel - MEP | 1 | 5 | 3275304.26 | 5784479.69 | 2509175.43 | 2440101.67 | 4588851.87 | 2148750.2 |  |  |  | 2440101.69 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 12514243.51 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP5 | Substation Elco Steel5
Elco Steel - MEP | 1 | 6 | 2863596.99 | 3766431.24 | 902834.25 | 2133379.76 | 2598837.56 | 465457.8 |  |  |  | 2133379.78 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 15377840.5 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP6 | Substation Elco Steel6
Elco Steel - MEP | 1 | 7 | 3498188.3161 | 3187107.5 | -311080.8161 | 2606150.307 | 2228843.15 | -377307.157 |  |  |  | 2606150.307 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 18876028.8161 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP7 | Substation Elco Steel7
Elco Steel - MEP | 1 | 8 |  | 2651758.28 | 2651758.28 | 1980608.55 | 1829713.22 | -150895.33 |  |  |  |  | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP8 | Substation Elco Steel8
Elco Steel - MEP | 1 | 9 |  | 1904763.72 | 1904763.72 | 2178754.66 | 1314286.96 | -864467.7 |  |  |  |  | 2018-09-30 | 2018-10-09 | 2018-10-10 | 15 | 2018-10-25 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP9 | Substation Elco Steel9
Elco Steel - MEP | 1 | 10 |  | 4730762.03 | 4730762.03 | 2629432.67 | 3744490.63 | 1115057.96 |  |  |  |  | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP10 | Substation Elco Steel10
Elco Steel - MEP | 1 | 11 |  | 4095222.62 | 4095222.62 | 1720441.01 | 3142902.52 | 1422461.51 |  |  |  |  | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP11 | Substation Elco Steel11
Elco Steel - MEP | 1 | 12 |  | 0 | 0 | 1037321.78 | 0 | -1037321.78 |  |  |  |  | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP12 | Substation Elco Steel12
Elco Steel - MEP | 1 | 13 |  | 0 | 0 | 388339.4 | 0 | -388339.4 |  |  |  |  | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP13 | Substation Elco Steel13
Elco Steel - MEP | 1 | 14 |  | 0 | 0 | 317040.71 | 0 | -317040.71 |  |  |  |  | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 | [8 empty] | 0 | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel - MEP14 | Substation Elco Steel14
Elco Steel V.O-Infra. Network | 1 | 1 |  | 0 | 0 | 1060000 | 0 | -1060000 |  |  |  |  | 2019-06-30 | 2019-07-03 | 2019-07-03 | 15 | 2019-07-18 | [9 empty] | 0 | 0 | 0 | Substation Elco Steel |  |  |  | Elco Steel V.O-Infra. Network1 | Substation Elco Steel1
#N/A
El-Gouna | 1 | 1 | 3393576.42 | 3474451.4 | 80874.98 | 2327690.6 | 2401503.7825 | 73813.1825 | 13625000 |  |  | 2338174.15 | 2019-09-30 | 2019-10-15 | 2019-11-04 | 21 | 2019-11-25 | 2019-11-24 | 3393576.42 | [6 empty] | 0 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna1 | DoubleTree Mangroovy ElGouna1
El-Gouna | 1 | 2 | 3546875.03 | 6040168.01 | 2493292.98 | 3867767.27 | 4293335.2605 | 425567.9905 |  |  |  | 3879736.97 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 21 | 2019-12-08 | 2019-11-24 | 6940451.45 | 2084092.99 | [5 empty] | 0 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna2 | DoubleTree Mangroovy ElGouna2
El-Gouna | 1 | 3 | 4290021.36 | 685050 | -3604971.36 | 2286139.86 | 680952 | -1605187.86 |  |  |  | 2286139.86 | 2019-11-30 | 2019-12-15 | 2019-12-16 | 21 | 2020-01-06 | 2019-12-19 | 11230472.81 | 1112126.59 | [5 empty] | 10483.55 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna3 | DoubleTree Mangroovy ElGouna3
El-Gouna | 1 | 4 | 2686069.3 | 3767828.94 | 1081759.64 | 2572404.48 | 2597585.492 | 25181.012 |  |  |  | 2572404.48 | 2019-12-31 | 2020-01-15 | 2020-01-21 | 21 | 2020-02-11 | 2020-01-21 | 13916542.11 | 2169673.66 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna4 | DoubleTree Mangroovy ElGouna4
El-Gouna | 1 | 5 | 3430037.61 | 2653452.18 | -776585.43 | 1808595.27 | 1828998.833 | 20403.563 |  |  |  | 1815739.6 | 2020-01-31 | 2020-02-15 | 2020-02-19 | 21 | 2020-03-11 | 2020-02-23 | 17346579.72 | 1374961.99 | [5 empty] | 10483.55 | 3430037.61 | 17346579.72 | 1815739.6 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna5 | DoubleTree Mangroovy ElGouna5
El-Gouna | 1 | 6 | 6540676.19 | 6170230.65 | -370445.54 | 4246133.4 | 8251289.2525 | 4005155.8525 |  |  |  | 4271724.93 | 2020-02-29 | 2020-03-15 | 2020-03-18 | 21 | 2020-04-08 | 2020-03-18 | 23887255.91 | 1023807.82 | [5 empty] | 29400.49 | 6540676.19 | 23887255.91 | 6823693.4 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna6 | DoubleTree Mangroovy ElGouna6
El-Gouna | 1 | 7 | 3114205.16 | 3133496.53 | 19291.37 | 2145687.36 | 2166123.4165 | 20436.0565 |  |  |  | 2145687.36 | 2020-03-31 | 2020-04-15 | 2020-04-18 | 21 | 2020-05-09 | 2020-04-21 | 27001461.07 | 1023807.82 | [5 empty] | 29400.49 | 3114205.16 | 27001461.07 | 2158979.11 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna7 | DoubleTree Mangroovy ElGouna7
El-Gouna | 1 | 8 | 3250029.8 | 2806757.16 | -443272.64 | 1922134.77 | 1896543.798 | -25590.972 |  |  |  | 1922134.77 | 2020-06-30 | 2020-07-01 | 2020-07-05 | 21 | 2020-07-26 | 2020-07-06 | 30251490.87 | 580535.19 | [5 empty] | 29400.49 | 3250029.8 | 30251490.87 | 1933855.68 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna8 | DoubleTree Mangroovy ElGouna8
El-Gouna | 1 | 9 | 1882490 | 1505090.04 | -377399.96 | 1030964.27 | 1030964.272 | 0.002 |  |  |  | 1037007.36 | 2020-07-31 | 2020-08-01 | 2020-07-26 | 21 | 2020-08-16 | 2020-07-27 | 32133980.87 | 203135.69 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna9 | DoubleTree Mangroovy ElGouna9
El-Gouna | 1 | 10 | 1889241.5387 | 1714004.8 | -175236.7387 | 1173489.52 | 1173489.49 | -0.03 |  |  |  | 1180949.3351 | 2020-08-31 | 2020-09-01 | 2020-09-05 | 21 | 2020-09-26 | 2020-09-05 | 34023222.4087 | 27898.992 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna10 | DoubleTree Mangroovy ElGouna10
El-Gouna | 1 | 11 | 881976.7757 | 2596008.28 | 1714031.5043 | 1750027.3 | 1750027.305 | 0.005 |  |  |  | 1788649.6992 | 2020-11-30 | 2020-11-30 | 2020-12-09 | 21 | 2020-12-30 | 2020-12-19 | 34905199.1844 | 1741930.488 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna11 | DoubleTree Mangroovy ElGouna11
El-Gouna | 1 | 12 | -0.0044313 | 1904761.9 | 1904761.9044 | 1942857.14 | 1942857.135 | -0.005 |  |  |  | 2000000 | 2020-11-30 | 2020-11-30 | 2020-12-23 | 21 | 2021-01-13 | 2020-12-23 | 34905199.18 | 1741930.49 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna12 | DoubleTree Mangroovy ElGouna12
El-Gouna | 1 | 13 | 2225492.71 | 2664148.65 | 438655.94 | 1951940.18 | 1951940.1825 | 0.0025 |  |  |  | 1964526.99 | 2020-12-31 | 2020-12-31 | 2021-01-10 | 21 | 2021-01-31 | 2021-01-12 | 37130691.89 | 1823017.32 | [5 empty] | 29400.49 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna13 | DoubleTree Mangroovy ElGouna13
El-Gouna | 1 | 14 | 3901532.2 | 4271693.53 | 370161.33 | 3058799.81 | 3058799.81 | 0 |  |  |  | 3061707.07 | 2021-01-31 | 2021-01-31 | 2021-02-14 | 21 | 2021-03-07 | 2021-03-03 | 41032224.09 | 1836465.31 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna14 | DoubleTree Mangroovy ElGouna14
El-Gouna | 1 | 15 | 4440680.41 | 4199870.68 | -240809.73 | 3002136.21 | 3002136.214 | 0.004 |  |  |  | 3011925.18 | 2021-02-28 | 2021-03-11 | 2021-03-13 | 21 | 2021-04-03 | 2021-04-17 | 45472904.5 | 1238512.71 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna15 | DoubleTree Mangroovy ElGouna15
El-Gouna | 1 | 16 | 4113209.61 | 4424891.64 | 311682.03 | 3166964.63 | 3166964.612 | -0.018 |  |  |  | 3166964.63 | 2021-03-31 | 2021-04-12 | 2021-04-15 | 21 | 2021-05-06 | 2021-04-27 | 49586114.11 | 1193051.88 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna16 | DoubleTree Mangroovy ElGouna16
El-Gouna | 1 | 17 | 3640319.41 | 2987451.96 | -652867.45 | 2526942.2 | 4581335.978 | 2054393.778 |  |  |  | 2547089.28 | 2021-05-31 | 2021-05-31 | 2021-06-03 | 21 | 2021-06-24 | 2021-06-14 | 53226433.52 | 540181.99 | [5 empty] | 120415.29 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna17 | DoubleTree Mangroovy ElGouna17
El-Gouna | 1 | 18 | 3384789.31 | 2844607.33 | -540181.98 | 5636281.25 | 5619891.3535 | -16389.8965 |  |  |  | 5636285.41 | 2021-08-31 | 2021-08-26 | 2021-08-26 | 21 | 2021-09-16 | 2021-08-26 | 56611222.83 | [6 empty] | 195708.06 | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna18 | DoubleTree Mangroovy ElGouna18
El-Gouna - Equip. Rental | 1 | 1 | 80875 | 3474451.4 | 3393576.4 | 73813.12 | 2401503.7825 | 2327690.6625 |  |  |  | 73813.12 | 2019-12-31 | 2019-12-31 | 2019-12-12 | 21 | 2020-01-02 | 2020-02-02 | 80875 | [7 empty] | 80875 | 80875 | 73813.12 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental1 | DoubleTree Mangroovy ElGouna1
El-Gouna - Equip. Rental | 1 | 2 |  | 6040168.01 | 6040168.01 | 16757 | 4293335.2605 | 4276578.2605 |  |  |  |  | 2020-03-31 | 2020-03-31 | 2020-03-18 | 21 | 2020-04-08 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental2 | DoubleTree Mangroovy ElGouna2
El-Gouna - Equip. Rental | 1 | 3 |  | 685050 | 685050 | 74100 | 680952 | 606852 |  |  |  |  | 2020-06-30 | 2020-07-09 | 2020-07-09 | 21 | 2020-07-30 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental3 | DoubleTree Mangroovy ElGouna3
El-Gouna - Equip. Rental | 1 | 4 |  | 3767828.94 | 3767828.94 | 3281.25 | 2597585.492 | 2594304.242 |  |  |  |  | 2021-03-31 | 2021-03-31 | 2021-03-31 | 21 | 2021-04-21 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental4 | DoubleTree Mangroovy ElGouna4
El-Gouna - Equip. Rental | 1 | 5 | 15000 | 2653452.18 | 2638452.18 | 15750 | 1828998.833 | 1813248.833 |  |  |  | 15750 | 2021-05-31 | 2021-05-24 | 2021-05-24 | 21 | 2021-06-14 | 2021-06-24 | 186362.5 | [7 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Equip. Rental5 | DoubleTree Mangroovy ElGouna5
El-Gouna - Temp. Fence | 1 | 1 | 409200 | 3474451.4 | 3065251.4 | 425568 | 2401503.7825 | 1975935.7825 |  |  |  | 429660 | 2019-12-31 | 2020-01-15 | 2020-01-18 | 21 | 2020-02-08 | 2020-03-01 | 409200 | [7 empty] | 409200 | 409200 | 429660 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Temp. Fence1 | DoubleTree Mangroovy ElGouna1
El-Gouna - Temp. Fence | 1 | 2 |  | 6040168.01 | 6040168.01 | 441526.8 | 4293335.2605 | 3851808.4605 |  |  |  |  | 2020-01-31 | 2020-02-15 | 2020-02-23 | 21 | 2020-03-15 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Temp. Fence2 | DoubleTree Mangroovy ElGouna2
El-Gouna - Temp. Fence | 1 | 3 |  | 685050 | 685050 | 173749.2 | 680952 | 507202.8 |  |  |  |  | 2020-05-31 | 2020-06-06 | 2020-06-06 | 21 | 2020-06-27 | [9 empty] | 0 | 0 | 0 | DoubleTree Mangroovy ElGouna |  |  |  | El-Gouna - Temp. Fence3 | DoubleTree Mangroovy ElGouna3
Existing Intake Apply -SSC-Mech | 1 | 1 | 573500 | 0 | -573500 | 1e-05 | 0 | -1e-05 |  |  |  | 636585 | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-30 | 573500 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Existing Intake Apply -SSC-Mech1 | 01
Existing Intake Supply -SSC-Mech | 1 | 1 | 2140488 | 0 | -2140488 | 2311727.07 | 0 | -2311727.07 |  |  |  | 2418751.44 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 2140488 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Existing Intake Supply -SSC-Mech1 | 01
#N/A
FIEM | 1 | 210 | 2236443.87 | 0 | -2236443.87 | 1523916.51 | 0 | -1523916.51 |  |  |  | 1524934.13 | 2017-10-31 | 2017-10-20 | 2017-10-20 | 60 | 2017-12-19 | 2017-10-23 | 69807649.46 | [6 empty] | 0 | 2236443.87 | 69808024.8 | 1524934.13 | 0 |  |  |  | FIEM210 | 0210
FIEM | 1 | 211 | 342199.52 | 0 | -342199.52 | 218510 | 0 | -218510 |  |  |  | 221255.83 | 2017-11-30 | 2017-12-04 | 2018-01-02 | 60 | 2018-03-03 | 2018-01-19 | 70149848.98 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | FIEM211 | 0211
FIEM | 1 | 212 | 1955183.63 | 0 | -1955183.63 | 1205285.3 | 0 | -1205285.3 |  |  |  | 1546005.35 | 2018-05-31 | 2018-06-12 | 2018-07-12 | 60 | 2018-09-10 | 2018-10-24 | 72105032.61 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | FIEM212 | 0212
FIEM | 1 | 213 | 336328.97 | 0 | -336328.97 | 335237.946 | 0 | -335237.946 |  |  |  | 335237.946 | 2018-08-31 | 2018-08-15 | 2018-10-21 | 60 | 2018-12-20 | 2018-10-24 | 72441361.58 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | FIEM213 | 0213
#N/A
HQ - CFC | 1 | 1 | 1435679.4 | 1435679.43 | 0.03 | 6847513.64 | 6886276.98 | 38763.34 | 103231218.3 |  |  | 6847513.7311 | 2021-01-31 | 2021-01-31 | 2021-02-03 | 21 | 2021-02-24 | 2021-02-22 | 1435679.4 | 5469259.14 | [5 empty] | 0 | 1435679.4 | 1435679.4 | 6847513.7311 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC1 | ElSewedy HQ Internal Finishing1
HQ - CFC | 1 | 2 | 7766126.7 | 7766126.67 | -0.03 | 8021127.82 | 8230813.242 | 209685.422 |  |  |  | 8021127.94 | 2021-02-28 | 2021-02-28 | 2021-03-08 | 21 | 2021-03-29 | 2021-03-22 | 9201806.1 | 7106192.52 | [5 empty] | 0 | 7766126.7 | 9201806.1 | 8021127.94 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC2 | ElSewedy HQ Internal Finishing2
HQ - CFC | 1 | 3 | 12533035.1 | 12533035.14 | 0.04 | 8213720.11 | 8552112.06 | 338391.95 |  |  |  | 8213719.76 | 2021-03-31 | 2021-03-31 | 2021-04-10 | 21 | 2021-05-01 | 2021-04-15 | 21734841.2 | 6815308.56 | [5 empty] | 50000 | 12533035.1 | 21734841.2 | 8213719.76 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC3 | ElSewedy HQ Internal Finishing3
HQ - CFC | 1 | 4 | 11480730.2 | 11480730.19 | -0.01 | 7815807.73 | 7530697.05 | -285110.68 |  |  |  | 7815807.64 | 2021-04-30 | 2021-04-30 | 2021-05-06 | 21 | 2021-05-27 | 2021-05-26 | 33215571.4 | 6784708.63 | [5 empty] | 50000 | 11480730.2 | 33215571.4 | 7815807.64 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC4 | ElSewedy HQ Internal Finishing4
HQ - CFC | 1 | 5 | 6032812.4 | 6032812.38 | -0.02 | 3447418.19 | 3447418.189 | -0.001 |  |  |  | 3447418.19 | 2021-06-30 | 2021-06-30 | 2021-07-06 | 21 | 2021-07-27 | 2021-07-14 | 39248383.8 | 6043914.88 | [5 empty] | 298842.16 | 0 | 0 | 0 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC5 | ElSewedy HQ Internal Finishing5
HQ - CFC | 1 | 6 | 5418722.3 | 5418722.29 | -0.01 | 13157200.99 | 8157201.3445 | -4999999.6455 |  |  |  | 13157201.34 | 2021-07-31 | 2021-07-31 | 2021-08-04 | 21 | 2021-08-25 | 2021-08-17 | 44667106.1 | 15536980.84 | [5 empty] | 258842.16 | 0 | 0 | 0 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC6 | ElSewedy HQ Internal Finishing6
HQ - CFC | 1 | 7 | 14463563.8 | 14463563.81 | 0.01 | 14942810.84 | 9724934.81 | -5217876.03 |  |  |  | 14942810.8492 | 2021-08-31 | 2021-09-06 | 2021-09-07 | 21 | 2021-09-28 | 2021-09-09 | 59130669.9 | 20740314.76 | [5 empty] | 258842.16 | 14463563.8 | 59130669.9 | 14942810.8492 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC7 | ElSewedy HQ Internal Finishing7
HQ - CFC | 1 | 8 | 12855494 | 12855494 | 0 | 10012745.7 | 10012746.11 | 0.41 |  |  |  | 10012746.11 | 2021-09-30 | 2021-10-06 | 2021-10-09 | 21 | 2021-10-30 | 2021-10-17 | 71986163.9 | 21760696.01 | [5 empty] | 253842.16 | 12903651.6 | 72034321.5 | 10059001.5 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC8 | ElSewedy HQ Internal Finishing8
HQ - CFC | 1 | 9 | 11039038.4 | 11039038.38 | -0.02 | 17174919.84 | 10415313.809 | -6759606.031 |  |  |  | 17174919.86 | 2021-10-31 | 2021-11-03 | 2021-11-04 | 21 | 2021-11-25 | 2021-11-11 | 83025202.3 | 31225957.6 | [5 empty] | 253842.16 | 11039038.4 | 83025202.3 | 17174919.86 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC9 | ElSewedy HQ Internal Finishing9
HQ - CFC | 1 | 10 | 10645458.9 | 10645458.95 | 0.05 | 7981881.94 | 0 | -7981881.94 |  |  |  | 7981881.9284 | 2021-11-30 | 2021-12-04 | 2021-12-07 | 21 | 2021-12-28 | 2021-12-16 | 93670661.2 | 32240807.02 | [5 empty] | 673673.38 | 10645458.9 | 93670661.2 | 7981881.9284 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC10 | ElSewedy HQ Internal Finishing10
HQ - CFC | 1 | 11 | 21606398.42 | 21606397.82 | -0.6 | 27417402.1 | 17417402.071 | -10000000.029 |  |  |  | 17417402.06 | 2021-12-31 | 2022-01-09 | 2022-01-10 | 21 | 2022-01-31 | 2022-10-20 | 115277059.62 | 33736026.89 | [5 empty] | 673673.38 | 21606397.9 | 115277059.1 | 17417402.1321 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC11 | ElSewedy HQ Internal Finishing11
HQ - CFC | 1 | 12 | 11990804.88 | 11990805.42 | 0.54 | 11342066.99 | 8175767.971 | -3166299.019 |  |  |  | 11342067.06 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 21 | 2022-03-08 | 2022-02-24 | 127267864.5 | 36548454.91 | [5 empty] | 0 | 11990804.88 | 127267864.5 | 11342067.06 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC12 | ElSewedy HQ Internal Finishing12
HQ - CFC | 1 | 13 | 23373232.3 | 23373232.29 | -0.01 | 10869511.32 | 869511.3245 | -9999999.9955 |  |  |  | 869511.3183 | 2022-02-28 | 2022-03-10 | 2022-03-15 | 21 | 2022-04-05 | 2022-03-28 | 150641096.8 | 40068734.4 |  |  |  | 3954328.79 | 3954328.79 | 0 | 23373232.3 | 150641096.8 | 869511.3183 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC13 | ElSewedy HQ Internal Finishing13
HQ - CFC | 1 | 14 |  | 15411463.14 | 15411463.14 | 6179916.44 | 1748564.937 | -4431351.503 |  |  |  | 1748564.91 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 21 | 2022-05-04 | [8 empty] | 0 | 0 | 0 | 1748564.91 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC14 | ElSewedy HQ Internal Finishing14
HQ - CFC | 1 | 15 | 16353901 | 16126527.14 | -227373.86 | 10437699.8 | 10437709.627 | 9.827 |  |  |  | 10437709.6267 | 2022-04-30 | 2022-04-30 | 2022-05-10 | 21 | 2022-05-31 | 2022-05-17 | 182179087 | 36127505.39 | 42019925.8 |  | 380603 | 4782201.035 | 4782201.035 | 28096 | 16353901 | 182179087 | 10437709.6267 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC15 | ElSewedy HQ Internal Finishing15
HQ - CFC | 1 | 16 | 8911604.3 | 8911604.29 | -0.01 | 1064612.28 | 0.0045 | -1064612.2755 |  |  |  | 1064612.35 | 2022-05-31 | 2022-05-31 | 2022-06-12 | 21 | 2022-07-03 | 2022-06-15 | 191090691.3 | 35019448 | 44132357 |  | 534156.21 | 5016130.5 | 5016130.5 | 1429217 | 8911604.3 | 191090691.3 | 1064612.35 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC16 | ElSewedy HQ Internal Finishing16
HQ - CFC | 1 | 17 | 17076484.2 | 17076484.19 | -0.01 | 8013147.43 | 2847047.2295 | -5166100.2005 |  |  |  | 8013147.4 | 2022-06-30 | 2022-06-30 | 2022-07-04 | 21 | 2022-07-25 | 2022-07-18 | 208167175.5 | 34368331.94 | 46825994 |  | 855446.95 | 5464388 | 5464388 | 28096.4 | 17076484.2 | 208167175.5 | 8013147.4 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC17 | ElSewedy HQ Internal Finishing17
HQ - CFC | 1 | 18 | 15625697.2 | 15535743.72 | -89953.48 | 12964666.86 | 11331892.376 | -1632774.484 |  |  |  | 13019444.4 | 2022-07-31 | 2022-07-31 | 2022-08-06 | 21 | 2022-08-27 | 2022-08-17 | 223792872.7 | 42794128.97 | 51289544.4 |  | 1216434.1435 | 5874504.1475 | 5874504.1475 | 28096.4 | 15625697.2 | 223792872.7 | 13019444.4 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC18 | ElSewedy HQ Internal Finishing18
HQ - CFC | 1 | 19 | 11070593.3 | 11160546.75 | 89953.45 | 2123375.29 | 0 | -2123375.29 |  |  |  | 2123376.4 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 21 | 2022-09-28 | 2022-10-16 | 234863466 | 43167126 | 53959703 |  | 1482872 | 6165165.5 | 6165165.5 | 23096 | 11070593.3 | 234863466 | 2123376.4 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC19 | ElSewedy HQ Internal Finishing19
HQ - CFC | 1 | 20 | 43687204.7 | 43687204.67 | -0.03 | 9324446.8 | 10136401.93 | 811955.13 |  |  |  | 9324446.7637 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 21 | 2022-11-01 | 2022-10-17 | 278550670.7 | 25330248.86 | 72413577.8 |  | 2630548.1069 | 7311955.105 | 7311955.105 | 23096.4 | 43687204.7 | 278550670.7 | 9324446.7637 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC20 | ElSewedy HQ Internal Finishing20
HQ - CFC | 1 | 21 | 6969185.9 | 6969185.9 | 2.4214e-08 | 1704646.05 | 0 | -1704646.05 |  |  |  | 1704646.05 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 21 | 2022-11-29 | 2022-11-20 | 285519856.6 | 22835242 | 75563462.2 |  | 2846115 | 7494896 | 7494896 | 0 | 6969185.9 | 285519856.6 | 1704646.05 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC21 | ElSewedy HQ Internal Finishing21
HQ - CFC | 1 | 23 | 9615384.7 | 25519032.04 | 15903647.34 | 10000000 | 1915761.653 | -8084238.347 |  |  |  | 10000000.1524 | 2022-11-30 | 2022-11-30 | 2022-12-07 | 21 | 2022-12-28 | 2022-12-14 | 295135241.3 | 22835242.98 | 85178846.6 |  | 2846115.9564 | 7494896.235 | 7494896.235 | 2085744.58 | 0 | 0 | 0 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC23 | ElSewedy HQ Internal Finishing23
HQ - CFC | 1 | 24 | 25568878.3 | 25519032.04 | -49846.26 | 5681250.46 | 0 | -5681250.46 |  |  |  | 5979128.01 | 2022-11-30 | 2022-11-30 | 2022-12-13 | 21 | 2023-01-03 | 2022-12-27 | 320704119.6 | 12624923 | 98574568 |  | 4317722 | 7311955.09 | 9525011.19 | 325973.55 | 25568878.3 | 320704119.6 | 5979128.01 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC24 | ElSewedy HQ Internal Finishing24
HQ - CFC | 1 | 25 | 17887580.019 | 17937426.6 | 49846.581 | 9125697.43 | 4987239.22 | -4138458.21 |  |  |  | 10125697.7641 | 2022-12-31 | 2022-12-31 | 2023-01-11 | 21 | 2023-02-01 | 2023-01-30 | 338591699.619 | 5521723.78 | 103716174.2 |  | 5354076.6018 | 7311955.09 | 10464109.14 | 297877.55 | 17887580.019 | 338591699.619 | 10125697.7641 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC25 | ElSewedy HQ Internal Finishing25
HQ - CFC | 1 | 26 | 15848994.2857 | 15848994.31 | 0.024286 | 11231097.41 | 11230610.0055 | -487.4045 |  |  |  | 24450753.15 | 2023-01-31 | 2023-01-31 | 2023-11-22 | 21 | 2023-12-13 | 2024-02-15 | 354440693.9048 | 2203336.47 | 119098372.4 |  | 6380098.57 | 9304068.215 | 9304068.215 | 0 | 15848994.2857 | 354440693.9048 | 24450753.15 | ElSewedy HQ Internal Finishing |  |  |  | HQ - CFC26 | ElSewedy HQ Internal Finishing26
#N/A
HyperOne | 1 | 1 | 1684523.66 | 1684524 | 0.34 | 36249090 | 2583316 | -33665774 | 33750000 |  |  | 2673900.95 | 2019-10-31 | 2019-11-10 | 2019-11-11 | 14 | 2019-11-25 | 2019-11-24 | 1684523.66 | 1191900 | [5 empty] | 0 | 1684523.66 | 1684523.66 | 2673900.95 | HyperOne Zayed Extension |  |  |  | HyperOne1 | HyperOne Zayed Extension1
HyperOne | 1 | 2 | 11473372.17 | 11473371.43 | -0.74 | 8063620 | 8637288.8615 | 573668.8615 |  |  |  | 8554552.61 | 2019-11-30 | 2019-12-07 | 2019-12-08 | 14 | 2019-12-22 | 2019-12-12 | 13157895.83 | 478500 | [5 empty] | 0 | 11473372.17 | 13157895.83 | 8554552.61 | HyperOne Zayed Extension |  |  |  | HyperOne2 | HyperOne Zayed Extension2
HyperOne | 1 | 3 | 10276217.5887 | 10276217.14 | -0.4487 | 6681009 | 7194819.68 | 513810.68 |  |  |  | 7194819.7145 | 2019-12-31 | 2019-12-31 | 2020-01-02 | 14 | 2020-01-16 | 2020-01-13 | 23434113.4187 | 478500 | [5 empty] | 1194684.3216 | 10276217.5887 | 23434113.4187 | 7194819.7145 | HyperOne Zayed Extension |  |  |  | HyperOne3 | HyperOne Zayed Extension3
HyperOne | 1 | 4 | 12451224.3668 | 12451225.71 | 1.3432 | 6318712 | 6318712 | 0 |  |  |  | 6318712 | 2020-01-31 | 2020-01-31 | 2020-02-06 | 14 | 2020-02-20 | 2020-02-23 | 35885337.7855 | [6 empty] | 4562652.7636 | 12451224.3668 | 35885337.7855 | 7092200.1311 | HyperOne Zayed Extension |  |  |  | HyperOne4 | HyperOne Zayed Extension4
HyperOne | 1 | 5 | 5616638.2145 | 5616447.62 | -190.5945 | 3307335 | 3307335 | 0 |  |  |  | 3307335 | 2020-02-29 | 2020-02-14 | 2020-02-18 | 14 | 2020-03-03 | 2020-02-23 | 41501976 | [6 empty] | 5067252 | 5616638.2145 | 41501976 | 3307335 | HyperOne Zayed Extension |  |  |  | HyperOne5 | HyperOne Zayed Extension5
HyperOne | 1 | 6 | 10976157.5052 | 10976158 | 0.4948 | 8598544 | 8598918.82 | 374.82 |  |  |  | 8598545.1487 | 2020-02-29 | 2020-02-29 | 2020-03-03 | 14 | 2020-03-17 | 2020-03-07 | 52478133.5052 | [6 empty] | 6203130.8054 | 10976157.5052 | 52478133.5052 | 8598545.1487 | HyperOne Zayed Extension |  |  |  | HyperOne6 | HyperOne Zayed Extension6
HyperOne | 1 | 7 | 12354446.4948 | 12419046 | 64599.5052 | 8960935 | 8960289.48 | -645.52 |  |  |  | 8896507 | 2020-03-31 | 2020-03-16 | 2020-03-19 | 14 | 2020-04-02 | 2020-03-23 | 64832580 | [6 empty] | 7392793.3392 | 12354446.4948 | 64832580 | 8896507 | HyperOne Zayed Extension |  |  |  | HyperOne7 | HyperOne Zayed Extension7
HyperOne | 1 | 8 | 7228560.7301 | 7092750.29 | -135810.4401 | 3276433 | 3276433 | 0 |  |  |  | 3400669 | 2020-03-31 | 2020-03-31 | 2020-04-04 | 14 | 2020-04-18 | 2020-04-12 | 72061140.7301 | [6 empty] | 9893521.3392 | 7228560.7301 | 72061140.7301 | 3400669 | HyperOne Zayed Extension |  |  |  | HyperOne8 | HyperOne Zayed Extension8
HyperOne | 1 | 9 | 2029339.2699 | 2100740 | 71400.7301 | 1277872 | 9493853 | 8215981 |  |  |  | 1277872 | 2020-04-30 | 2020-04-16 | 2020-04-19 | 14 | 2020-05-03 | 2020-04-26 | 74090480 | [6 empty] | 10272402 | 2029339.2699 | 74090480 | 1277872 | HyperOne Zayed Extension |  |  |  | HyperOne9 | HyperOne Zayed Extension9
HyperOne | 1 | 10 | 7741768.3647 | 7629179.05 | -112589.3147 | 4688664 | 4688663.2125 | -0.7875 |  |  |  | 4810581.9155 | 2020-05-31 | 2020-05-15 | 2020-05-17 | 14 | 2020-05-31 | 2020-06-01 | 81832248.3647 | [6 empty] | 11782199.7246 | 7741768.3647 | 81832248.3647 | 4810581.9155 | HyperOne Zayed Extension |  |  |  | HyperOne10 | HyperOne Zayed Extension10
HyperOne | 1 | 11 | 9960645.6353 | 10073235.24 | 112589.6047 | 6700148 | 6700148 | 0 |  |  |  | 6700151 | 2020-06-30 | 2020-06-15 | 2020-06-18 | 14 | 2020-07-02 | 2020-06-23 | 91792894 | [6 empty] | 13305539 | 9960645.6353 | 91792894 | 6700151 | HyperOne Zayed Extension |  |  |  | HyperOne11 | HyperOne Zayed Extension11
HyperOne | 1 | 12 | 3093528.5715 | 3093527.62 | -0.95152 | 1896315 | 1896313.721 | -1.279 |  |  |  | 1896314.4172 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 14 | 2020-07-18 | 2020-07-11 | 94886422.5715 | [6 empty] | 13935080.9072 | 3093528.5715 | 94886422.5715 | 1896314.4172 | HyperOne Zayed Extension |  |  |  | HyperOne12 | HyperOne Zayed Extension12
HyperOne | 1 | 13 | 9161230.539 | 9161231 | 0.46098 | 6738702 | 6738702 | 0 |  |  |  | 6738701.3468 | 2020-07-31 | 2020-07-31 | 2020-08-09 | 14 | 2020-08-23 | 2020-08-19 | 104047653.1105 | [6 empty] | 14675608.1725 | 9161230.539 | 104047653.1105 | 6738701.3468 | HyperOne Zayed Extension |  |  |  | HyperOne13 | HyperOne Zayed Extension13
HyperOne | 1 | 14 | 5698538.8895 | 5698546.6 | 7.7105 | 4476191 | 4476191 | 0 |  |  |  | 4476191 | 2020-08-31 | 2020-08-31 | 2020-09-02 | 14 | 2020-09-16 | 2020-09-13 | 109746192 | [6 empty] | 14851704 | 5698538.8895 | 109746192 | 4476191 | HyperOne Zayed Extension |  |  |  | HyperOne14 | HyperOne Zayed Extension14
HyperOne | 1 | 15 | 16067546 | 0 | -16067546 | 2754557 | 0 | -2754557 |  |  |  | 2800899.62 | 2020-12-31 | 2020-12-31 | 2021-07-10 | 14 | 2021-07-24 | 2021-09-08 | 125813738 | [6 empty] | 18113646 | 16067546 | 125813738 | 2800899.62 | HyperOne Zayed Extension |  |  |  | HyperOne15 | HyperOne Zayed Extension15
#N/A
IKEA | 1 | 1 | 2651353.89 | 3976564.28 | 1325210.39 | 9032556.9 | 5297470.32 | -3735086.58 | 5000000 |  |  | 4032556.9 | 2019-10-31 | 2019-10-24 | 2019-10-29 | 56 | 2019-12-24 | 2019-11-13 | 2651353.89 | 2149309.09 | [5 empty] | 0 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA1 | IKEA Extension MoA1
IKEA | 1 | 2 | 11255708.29 | 12868979.7 | 1613271.41 | 11062702.45 | 12738076.37 | 1675373.92 | 428986.9 |  |  | 10633715.55 | 2019-11-30 | 2019-11-30 | 2019-12-01 | 56 | 2020-01-26 | 2019-12-23 | 13907062.18 | 4289692.08 | [5 empty] | 619021.13 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA2 | IKEA Extension MoA2
IKEA | 1 | 3 | 10066585.32 | 10925856.01 | 859270.69 | 12136068.98 | 8007384.775 | -4128684.205 | 4951900.8 |  |  | 7184168.18 | 2019-12-31 | 2019-12-31 | 2019-12-29 | 56 | 2020-02-23 | 2020-01-27 | 23973647.5 | 2903747.63 | [5 empty] | 726571.28 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA3 | IKEA Extension MoA3
IKEA | 1 | 4 | 12574283.5677 | 12901940.25 | 327656.6823 | 10394851.44 | 8955635.564 | -1439215.876 | 2116049.37 |  |  | 8278802.0663 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 56 | 2020-03-30 | 2020-02-26 | 36547931.0677 | 465407.831 | [5 empty] | 919175.0927 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA4 | IKEA Extension MoA4
IKEA | 1 | 5 | 9421690.8414 | 9421690.84 | -0.001378 | 29492459.808 | 7739970.29 | -21752489.518 | 21562500 |  |  | 7929959.808 | 2020-02-29 | 2020-02-29 | 2020-03-02 | 56 | 2020-04-27 | 2020-03-29 | 45969621.9091 | 371420 | [5 empty] | 847495.2609 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA5 | IKEA Extension MoA5
IKEA | 1 | 6 | 5112809.0459 | 5112809.05 | 0.0041118 | 5718130.68 | 4141935.79 | -1576194.89 | 1818917 |  |  | 3899213.6765 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 56 | 2020-05-26 | 2020-04-23 | 51082430.955 | 371420 | [5 empty] | 1125963.2758 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA6 | IKEA Extension MoA6
IKEA | 1 | 7 | 9400137.0091 | 9400137.01 | 0.00085056 | 9913732.53 | 6567550.07 | -3346182.46 | 3751873.62 |  |  | 6161858.9082 | 2020-04-30 | 2020-05-03 | 2020-05-05 | 56 | 2020-06-30 | 2020-06-07 | 60482567.9642 | [6 empty] | 1472106.3608 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA7 | IKEA Extension MoA7
IKEA | 1 | 8 | 17657618.9509 | 18401730.5 | 744111.5491 | 13605824.96 | 13497644.42 | -108180.54 | 525633.83 |  |  | 13080191.1331 | 2020-06-30 | 2020-06-23 | 2020-06-23 | 56 | 2020-08-18 | 2020-07-15 | 78140186.9151 | 5848353.145 | [5 empty] | 2079486.5167 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA8 | IKEA Extension MoA8
IKEA | 1 | 9 | 19939473.9502 | 19195362.4 | -744111.5502 | 21936362.84 | 21335051.85 | -601310.99 |  |  |  | 21936362.8422 | 2020-07-31 | 2020-07-22 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-13 | 98079660.8653 | 17006675.991 | [5 empty] | 1611811.9037 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA9 | IKEA Extension MoA9
IKEA | 1 | 10 | 16241524.1447 | 16241435.02 | -89.1247 | 10981834.92 | 10892925.95 | -88908.97 |  |  |  | 10981834.92 | 2020-08-31 | 2020-08-15 | 2020-08-18 | 56 | 2020-10-13 | 2020-09-27 | 114321185.01 | 16856139.28 | [5 empty] | 2394063.2 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA10 | IKEA Extension MoA10
IKEA | 1 | 11 | 40022086.8222 | 40022086.82 | -0.00225 | 16592416.38 | 16989482.64 | 397066.26 |  |  |  | 16592416.38 | 2020-09-30 | 2020-10-12 | 2020-10-14 | 56 | 2020-12-09 | 2020-11-15 | 154343271.8322 | 2685460.4477 | [5 empty] | 3391607 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA11 | IKEA Extension MoA11
IKEA | 1 | 12 | 27619584.4178 | 27691689.43 | 72105.0123 | 15898929.26 | 15913350.29 | 14421.03 |  |  |  | 15898929.26 | 2020-11-30 | 2020-11-25 | 2020-11-29 | 56 | 2021-01-24 | 2021-12-30 | 181962856.25 | -4332571 | [5 empty] | 0 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA12 | IKEA Extension MoA12
IKEA | 1 | 13 | 3981119.65 | 3981119.65 | -6.0536e-09 | 5400893.31 | 4064871.9 | -1336021.41 |  |  |  | 5400893.31 | 2020-12-31 | 2021-01-10 | 2021-01-13 | 56 | 2021-03-10 | 2021-02-18 | 185943975.9 | [6 empty] | 4547790.9 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA13 | IKEA Extension MoA13
IKEA | 1 | 14 | 10525422.84 | 10453317.84 | -72105 | 15116863.46 | 20582119.9 | 5465256.44 |  |  |  | 15116863.46 | 2021-04-30 | 2021-04-19 | 2021-06-24 | 56 | 2021-08-19 | 2021-08-09 | 196469398.74 | [6 empty] | 0 | 0 | 0 | 0 | IKEA Extension MoA |  |  |  | IKEA14 | IKEA Extension MoA14
JICA | 1 | 19 | 1210863.76 | 0 | -1210863.76 | 1141675.91 | 0 | -1141675.91 |  |  |  | 1141675.91 | 2017-10-31 | 2017-10-28 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-30 | 117203462.77 | 0 | [5 empty] | 0 | 1210863.76 | 117203462.77 | 1141675.91 | 0 |  |  |  | JICA19 | 019
JICA | 1 | 20 | 283125.01 | 0 | -283125.01 | 413014.8 | 0 | -413014.8 |  |  |  | 413014.8 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 117486587.78 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | JICA20 | 020
#N/A
Kafr Shokr | 2 | 1 |  | 98312039.43 | 98312039.43 | 28845197.4 | 29730005.7605 | 884808.3605 |  |  |  |  | 2021-03-31 | 2021-03-14 | 2021-03-17 | 60 | 2021-05-16 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 1 | Kafr Shokr Bridge1
Kafr Shokr | 2 | 2 |  | 21005491.44 | 21005491.44 | 6242742.2 | 6242742.164 | -0.036 |  |  |  |  | 2021-03-31 | 2021-03-31 | 2021-04-07 | 60 | 2021-06-06 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 2 | Kafr Shokr Bridge2
Kafr Shokr | 2 | 3 |  | 9630317.86 | 9630317.86 | 8372664.9 | 8372664.936 | 0.036 |  |  |  |  | 2021-04-30 | 2021-04-30 | 2021-05-23 | 60 | 2021-07-22 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 3 | Kafr Shokr Bridge3
Kafr Shokr | 2 | 4 |  | 14900014.29 | 14900014.29 | 8190447.9 | 8190447.9 | 0 |  |  |  |  | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 4 | Kafr Shokr Bridge4
Kafr Shokr | 2 | 5 |  | 6107250 | 6107250 | 5371513.65 | 5371513.65 | 0 |  |  |  |  | 2021-07-31 | 2021-07-31 | 2021-08-12 | 60 | 2021-10-11 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 5 | Kafr Shokr Bridge5
Kafr Shokr | 2 | 6 |  | 2805242.86 | 2805242.86 | 444257.7 | 444257.73 | 0.03 |  |  |  |  | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | [8 empty] | 0 | 0 | 0 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 6 | Kafr Shokr Bridge6
Kafr Shokr | 2 | 7 | 31881474.95 | 30363309.48 | -1518165.47 | 26652960.08 | 27070646.13 | 417686.05 |  |  |  | 25823994.7095 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 60 | 2021-12-09 |  | 108184525 | [6 empty] | 0 | 31881474.95 | 108184525 | 25823994.7095 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 7 | Kafr Shokr Bridge7
Kafr Shokr | 2 | 8 | 2504502 | 1839476.19 | -665025.81 | 2028646.62 | 1610960.6295 | -417685.9905 |  |  |  | 2028646.62 | 2021-11-30 | 2021-11-30 | 2021-11-30 | 60 | 2022-01-29 | 2021-12-25 | 110689027 | [6 empty] | 0 | 2504502 | 110689027 | 2028646.62 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 8 | Kafr Shokr Bridge8
Kafr Shokr | 2 | 9 | 5785188 | 11019405.72 | 5234217.72 | 4811891.1 | 4811892.2 | 1.1 |  |  |  | 0 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-08-07 | 116474215 | [6 empty] | 0 | 5785188 | 116474215 | 0 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 9 | Kafr Shokr Bridge9
Kafr Shokr | 2 | 10 | 2841975 | 5413285.72 | 2571310.72 | 2390708.7 | 2390708.77 | 0.07 |  |  |  | 2301999.75 | 2021-12-31 | 2021-12-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-09-26 | 119316190 | [6 empty] | 0 | 2841975 | 119316190 | 2301999.75 | Kafr Shokr Bridge |  |  |  | Kafr Shokr 10 | Kafr Shokr Bridge10
#N/A
Katameya - Creeks | 1 | 1 | 2910883.3063 | 2919397.4 | 8514.0937 | 2741191.29 | 2748675.4515 | 7484.1615 | 200000000 |  |  | 2741191.2884 | 2020-12-31 | 2020-12-31 | 2021-01-14 | 40 | 2021-02-23 | 2021-01-31 | 2910883.3063 | [6 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks1 | Kattameya Creeks1
Katameya - Creeks | 1 | 2 | 11780609.6823 | 12368012.17 | 587402.4877 | 56302769.9409 | 11295285.7785 | -45007484.1624 |  | 45000000 |  | 11302769.9409 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 40 | 2021-03-16 | 2021-02-18 | 14691492.9885 | 595916.5854 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks2 | Kattameya Creeks2
Katameya - Creeks | 1 | 3 | 36329559.9323 | 41751425.71 | 5421865.7777 | 84570120.9 | 39570120.8955 | -45000000.0045 |  | 45000000 |  | 39570120.8973 | 2021-02-28 | 2021-02-28 | 2021-03-06 | 40 | 2021-04-15 | 2021-03-21 | 51021052.9208 | 6017782.3615 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks3 | Kattameya Creeks3
Katameya - Creeks | 1 | 4 | 30128591.4792 | 31881858.16 | 1753266.6808 | 49688637.31 | 29687637.308 | -20001000.002 |  | 20000000 |  | 29688637.31 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 40 | 2021-05-16 | 2021-04-22 | 81149644.4 | 7771049.05 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks4 | Kattameya Creeks4
Katameya - Creeks | 1 | 5 | 41641437.57 | 43155172.94 | 1513735.37 | 40006572.36 | 40007572.367 | 1000.007 |  |  |  | 40006572.36 | 2021-04-30 | 2021-05-06 | 2021-05-06 | 40 | 2021-06-15 | 2021-05-23 | 122791081.97 | 9284784.42 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks5 | Kattameya Creeks5
Katameya - Creeks | 1 | 6 | 35290109.98 | 32255415.11 | -3034694.87 | 29363826.77 | 29363826.7655 | -0.0045 |  |  |  | 29363826.77 | 2021-05-31 | 2021-06-06 | 2021-06-06 | 40 | 2021-07-16 | 2021-06-29 | 158081191.95 | 6250089.55 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks6 | Kattameya Creeks6
Katameya - Creeks | 1 | 7 | 46826693.78 | 48280873.42 | 1454179.64 | 44380443 | 44380444.2275 | 1.2275 |  |  |  | 44596069.78 | 2021-06-30 | 2021-07-06 | 2021-07-06 | 40 | 2021-08-15 | 2021-07-27 | 204907885.73 | 7704269.19 | [5 empty] | 523000 | 46826693.78 | 204907885.73 | 44596069.78 | Kattameya Creeks |  |  |  | Katameya - Creeks7 | Kattameya Creeks7
Katameya - Creeks | 1 | 8 | 41480221.37 | 43370006.73 | 1889785.36 | 40343227.98 | 40343227.9665 | -0.0135 |  |  |  | 40343227.98 | 2021-07-31 | 2021-08-07 | 2021-08-07 | 40 | 2021-09-16 | 2021-08-07 | 246388107.1 | 9594054.56 | [5 empty] | 777600 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks8 | Kattameya Creeks8
Katameya - Creeks | 1 | 9 | 44965022.45 | 45658900.57 | 693878.12 | 43056438.19 | 43056438.1785 | -0.0115 |  |  |  | 43056438.19 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 40 | 2021-10-15 | 2021-09-23 | 291353129.55 | 10287932.68 | [5 empty] | 800600 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks9 | Kattameya Creeks9
Katameya - Creeks | 1 | 10 | 37520387.97 | 38757548.53 | 1237160.56 | 61159972.97 | 36159161.9365 | -25000811.0335 |  |  |  | 36159161.93 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 40 | 2021-11-15 | 2021-10-28 | 328873517.52 | 11525093.24 | [5 empty] | 813250 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks10 | Kattameya Creeks10
Katameya - Creeks | 1 | 11 |  | 46662391.16 | 46662391.16 | 43214038.28 | 43214038.288 | 0.008 |  |  |  | 43214038.28 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 40 | 2021-12-16 | 2021-11-22 | 379505848.55 | 7555153.37 | [5 empty] | 823370 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks11 | Kattameya Creeks11
Katameya - Creeks | 1 | 12 | 40810274.28 | 39536093.61 | -1274180.67 | 36461301.55 | 36461301.5305 | -0.0195 |  |  |  | 36461301.55 | 2021-11-30 | 2021-11-30 | 2021-12-06 | 40 | 2022-01-15 | 2021-12-27 | 420316122.83 | 6280972.71 | [5 empty] | 841080 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks12 | Kattameya Creeks12
Katameya - Creeks | 1 | 13 | 39636501.96 | 41829784.58 | 2193282.62 | 39353596.01 | 39353596.009 | -0.00099999 |  |  |  | 39353596.01 | 2021-12-31 | 2021-12-31 | 2022-01-08 | 40 | 2022-02-17 | 2022-01-27 | 459952624.79 | 8474255.32 | [5 empty] | 863850 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks13 | Kattameya Creeks13
Katameya - Creeks | 1 | 14 | 45239351.95 | 48574512.67 | 3335160.72 | 45904629.98 | 45904629.9935 | 0.0135 |  |  |  | 45904629.98 | 2022-01-31 | 2022-01-31 | 2022-02-07 | 40 | 2022-03-19 | 2022-02-24 | 505191976.74 | 11809416.04 | [5 empty] | 0 | 45239351.95 | 505191976.74 | 45904629.98 | Kattameya Creeks |  |  |  | Katameya - Creeks14 | Kattameya Creeks14
Katameya - Creeks | 1 | 15 | 47493723.66 | 51903318.98 | 4409595.32 | 49567395 | 49567394.569 | -0.431 |  |  |  | 49567394.59 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 40 | 2022-04-14 | 2022-03-14 | 552685700.4 | 16219011.36 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks15 | Kattameya Creeks15
Katameya - Creeks | 1 | 16 | 48315079.39 | 47021445.38 | -1293634.01 | 44583744 | 44583744.0045 | 0.0045 |  |  |  | 44583744.4 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 40 | 2022-05-16 | 2022-04-17 | 601000779.79 | 14925377.35 | [5 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks16 | Kattameya Creeks16
Katameya - Creeks | 1 | 17 | 37444918.46 | 37521775.17 | 76856.71 | 36501027.74 | 36571027.7485 | 70000.0085 |  |  |  | 36501027.74 | 2022-04-30 | 2022-04-30 | 2022-05-07 | 40 | 2022-06-16 | 2022-05-29 | 638445698.25 | 15002234.06 | 50675010 |  | 97675643 |  |  | 1009270 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks17 | Kattameya Creeks17
Katameya - Creeks | 1 | 18 | 37748158.21 | 42935687.01 | 5187528.8 | 41565441.8 | 41641258.1345 | 75816.3345 |  |  |  | 41565441.8 | 2022-05-31 | 2022-05-31 | 2022-06-05 | 40 | 2022-07-15 | 2022-06-05 | 676193856.46 | 20189762.86 | 59495615 |  | 103801771 |  |  | 1085086 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks18 | Kattameya Creeks18
Katameya - Creeks | 1 | 19 | 37876838.61 | 37484144.91 | -392693.7 | 36081249.47 | 36075433.1155 | -5816.3545 |  |  |  | 36081249.47 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-03 | 714070695.07 | 19797069.17 | 71508662.79 |  | 108653109.7 |  |  | 1084330 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks19 | Kattameya Creeks19
Katameya - Creeks | 1 | 20 | 23863809.78 | 25275496.94 | 1411687.16 | 24569045 | 24429045.007 | -139999.993 |  |  |  | 24569045.01 | 2022-07-31 | 2022-07-31 | 2022-08-07 | 40 | 2022-09-16 | 2022-08-21 | 737934504.85 | 21208756.33 | 79759027 |  | 110507501 |  |  | 944330 | 23863809.78 | 737934504.85 | 24569045.01 | Kattameya Creeks |  |  |  | Katameya - Creeks20 | Kattameya Creeks20
Katameya - Creeks | 1 | 21 | 37145495.17 | 36255948.47 | -889546.7 | 35259435.93 | 35259435.93 | 0 |  |  |  | 35259435.93 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 40 | 2022-10-15 | 2022-09-20 | 775080000.02 | 20319209.63 | 93957089.31 |  | 115330857 |  |  | 944330 | 37145495.17 | 775080000.02 | 35259435.93 | Kattameya Creeks |  |  |  | Katameya - Creeks21 | Kattameya Creeks21
Katameya - Creeks | 1 | 22 | 28622135.19 | 32375932.35 | 3753797.16 | 31299260.01 | 31299260.0175 | 0.0075 |  |  |  | 31299260.01 | 2022-09-30 | 2022-09-30 | 2022-10-06 | 40 | 2022-11-15 | 2022-10-22 | 803702135.21 | 24073006.79 | 104402623 |  | 118783626 |  |  | 944330 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks22 | Kattameya Creeks22
Katameya - Creeks | 1 | 23 | 24245600.88 | 30664402.09 | 6418801.21 | 29834733.07 | 29834733.0645 | -0.0055 |  |  |  | 29834733.07 | 2022-10-31 | 2022-10-25 | 2022-11-06 | 40 | 2022-12-16 | 2022-11-28 | 827947736.09 | 30491808 | 110827191.37 |  | 121373214 |  |  | 944330 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks23 | Kattameya Creeks23
Katameya - Creeks | 1 | 24 | 30975620.82 | 38710056.01 | 7734435.19 | 37876579.92 | 37876579.918 | -0.002 |  |  |  | 37876581.29 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 40 | 2023-01-14 | 2022-12-26 | 858923356.91 | 38226243.19 | 123338828 |  | 123817551 |  |  | 944330 | 30975620.82 | 858923356.91 | 37876581.29 | Kattameya Creeks |  |  |  | Katameya - Creeks24 | Kattameya Creeks24
Katameya - Creeks | 1 | 25 | 21870157.41 | 45327391.41 | 23457234 | 45191848.31 | 45191848.31 | 0 |  |  |  | 45191848.32 | 2022-12-31 | 2022-12-31 | 2023-01-03 | 40 | 2023-02-12 | 2023-01-25 | 880793514.32 | 61683477.19 | 133104770 |  | 126424933 |  |  | 944330 | 21870157.41 | 880793514.32 | 45191848.32 | Kattameya Creeks |  |  |  | Katameya - Creeks25 | Kattameya Creeks25
Katameya - Creeks | 1 | 26 | 41254688.36 | 73494584.17 | 32239895.81 | 74263221 | 74263221 | 0 |  |  |  | 74263221.64 | 2023-01-31 | 2023-01-31 | 2023-02-05 | 40 | 2023-03-17 | 2023-02-28 | 922048202.68 | 93923373 | 158579085 |  | 130310913 |  |  | 975300.2 | 41254688.36 | 922048202.68 | 74263221.64 | Kattameya Creeks |  |  |  | Katameya - Creeks26 | Kattameya Creeks26
Katameya - Creeks | 1 | 27 | 23948941.02 | 35445373.6 | 11496432.58 | 35452924 | 35452924 | 0 |  |  |  | 35452924.06 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 40 | 2023-04-14 | 2023-03-30 | 945997143.7 | 105419805.57 | 170052796 |  | 133396502 |  |  | 975300 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks27 | Kattameya Creeks27
Katameya - Creeks | 1 | 28 | 26373696.19 | 28889381.89 | 2515685.7 | 28650459 | 28650459 | 0 |  |  |  | 28650459.02 | 2023-03-31 | 2023-03-30 | 2023-04-06 | 40 | 2023-05-16 | 2023-05-04 | 972370839.89 | 107935491.27 | 183454579.15 |  | 136180192 |  |  | 975300 | 26373696.19 | 972370839.89 | 28650459.02 | Kattameya Creeks |  |  |  | Katameya - Creeks28 | Kattameya Creeks28
Katameya - Creeks | 1 | 29 | 23994845.49 | 40212630.08 | 16217784.59 | 40904481 | 40904481 | 0 |  |  |  | 40904481.77 | 2023-04-30 | 2023-04-30 | 2023-05-10 | 40 | 2023-06-19 | 2023-06-03 | 996365685.38 | 124153275.86 | 196775586 |  | 138759517 |  |  | 1187195.2 | 23994845.49 | 996365685.38 | 40904481.77 | Kattameya Creeks |  |  |  | Katameya - Creeks29 | Kattameya Creeks29
Katameya - Creeks | 1 | 30 | 81851684.98 | 55298315.11 | -26553369.87 | 43084120 | 43084120 | 0 |  |  |  | 43084120.03 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 40 | 2023-07-17 | 2023-06-22 | 1078217370.36 | 97599905.99 | 269087133.95 |  | 142922586 |  |  | 1474123.2 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks30 | Kattameya Creeks30
Katameya - Creeks | 1 | 31 | 34090513.58 | 49290024.52 | 15199510.94 | 37106226 | 37106226 | 0 |  |  |  | 37106226.16 | 2023-06-30 | 2023-06-30 | 2023-07-09 | 40 | 2023-08-18 | 2023-07-31 | 1112307883.94 | 112799416.94 | 291661196 |  | 146035580.84 |  |  | 1474123.2 | 34090513.58 | 1112307883.94 | 37106226.16 | Kattameya Creeks |  |  |  | Katameya - Creeks31 | Kattameya Creeks31
Katameya - Creeks | 1 | 32 | 36694395.36 | 52360770.17 | 15666374.81 | 41216438 | 41216438 | 0 |  |  |  | 53216438.64 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 40 | 2023-09-17 | 2023-09-04 | 1149002279.3 | 128465791.75 | 319241513 |  | 149874135 |  |  | 1474123.2 | 0 | 0 | 53390542.82 | Kattameya Creeks |  |  |  | Katameya - Creeks32 | Kattameya Creeks32
Katameya - Creeks | 1 | 33 | 61801377.92 | 61236907.71 | -564470.21 | 47329833 | 47329832.9684 | -0.0316 |  |  |  | 47329832.99 | 2023-08-31 | 2023-08-31 | 2023-09-07 | 40 | 2023-10-17 | 2023-10-01 | 1210803657.22 | 127901321.55 | 370075065.87 |  | 154477701.6 |  |  | 1474123.2 | 61801377.92 | 1210803657.22 | 47329832.99 | Kattameya Creeks |  |  |  | Katameya - Creeks33 | Kattameya Creeks33
Katameya - Creeks | 1 | 34 | 67431952.34 | 82997244.56 | 15565292.22 | 70308953 | 70308953 | 0 |  |  |  | 70308953.76 | 2023-09-30 | 2023-09-30 | 2023-10-08 | 40 | 2023-11-17 | 2023-11-02 | 1278235609.56 | 143466613.76 | 421285092.94 |  | 161880059 |  |  | 2286300.2 | 67431952.34 | 1278235609.56 | 70308953.76 | Kattameya Creeks |  |  |  | Katameya - Creeks34 | Kattameya Creeks34
Katameya - Creeks | 1 | 35 | 61247331.12 | 59094596.48 | -2152734.64 | 46816344 | 46816344 | 0 |  |  |  | 46816344.41 | 2023-10-31 | 2023-10-31 | 2023-11-08 | 40 | 2023-12-18 | 2023-12-06 | 1339482940.68 | 141313879.12 | 467826001.19 |  | 169260713.53 |  |  | 2593710.2 | 61247331.12 | 1339482940.68 | 46816344.41 | Kattameya Creeks |  |  |  | Katameya - Creeks35 | Kattameya Creeks35
Katameya - Creeks | 1 | 36 | 74463161.12 | 64452457.92 | -10010703.2 | 50530224.78 | 50530224.78 | 0 |  |  |  | 50530225.45 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 40 | 2024-01-16 | 2023-12-30 | 1413946101.8 | 131303175.93 | 514457815.28 |  | 175537623 |  |  | 2835674.2 | 74463161.12 | 1413946101.8 | 50530225.45 | Kattameya Creeks |  |  |  | Katameya - Creeks36 | Kattameya Creeks36
Katameya - Creeks | 1 | 37 | 53331460.14 | 60819348.36 | 7487888.22 | 62109565 | 62109565 | 0 |  |  |  | 62109565.07 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-01-22 | 1467277561.94 | 138791064.14 | 557616767.77 |  | 179660456 |  |  | 3087279.2 | 53331460.14 | 1467277561.94 | 62109565.07 | Kattameya Creeks |  |  |  | Katameya - Creeks37 | Kattameya Creeks37
Katameya - Creeks | 1 | 38 | 83842743.6 | 78865309.72 | -4977433.88 | 79235150 | 79235149.8888 | -0.1112 |  |  |  | 79235149.9 | 2024-01-31 | 2024-01-31 | 2024-02-08 | 40 | 2024-03-19 | 2024-03-06 | 1551120305.54 | 133813630.27 | 619119624.83 |  | 194495708 |  |  | 3385105 | 83842743.6 | 1551120305.54 | 79235149.9 | Kattameya Creeks |  |  |  | Katameya - Creeks38 | Kattameya Creeks38
Katameya - Creeks | 1 | 39 | 81688930.92 | 66379928.69 | -15309002.23 | 66261026 | 66261026 | 0 |  |  |  | 66261026.21 | 2024-02-29 | 2024-02-29 | 2024-03-10 | 40 | 2024-04-19 | 2024-04-02 | 1632809236.46 | 118504628.04 | 681574347 |  | 206803236 |  |  | 3583708 | 81688930.92 | 1632809236.46 | 66261026.21 | Kattameya Creeks |  |  |  | Katameya - Creeks39 | Kattameya Creeks39
Katameya - Creeks | 1 | 40 | 66582662.04 | 52383248.29 | -14199413.75 | 52039038 | 52039038 | 0 |  |  |  | 52039038.12 | 2024-03-31 | 2024-03-31 | 2024-04-06 | 40 | 2024-05-16 | 2024-05-02 | 1699391898.5 | 104305214.28 | 732184516 |  | 217702929 |  |  | 3885490.2 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks40 | Kattameya Creeks40
Katameya - Creeks | 1 | 41 | 47455342.03 | 44558913.7 | -2896428.33 | 45340678.81 | 45340679.808 | 0.998 |  |  |  | 45340679.8 | 2024-04-30 | 2024-04-30 | 2024-05-08 | 40 | 2024-06-17 | 2024-05-25 | 1746847240.53 | 101408785.94 | 771118051 |  | 224726984.46 |  |  | 4067349.2 | 47455342.03 | 1746847240.53 | 45340679.8 | Kattameya Creeks |  |  |  | Katameya - Creeks41 | Kattameya Creeks41
Katameya - Creeks | 1 | 42 | 56995945.47 | 52161798.49 | -4834146.98 | 52791233 | 52791233 | 0 |  |  |  | 52791233.92 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 40 | 2024-07-19 | 2024-07-07 | 1803843186 | 96574638 | 816861989 |  | 232964321 |  |  | 4370002 | 56995945.47 | 1803843186 | 52791233.92 | Kattameya Creeks |  |  |  | Katameya - Creeks42 | Kattameya Creeks42
Katameya - Creeks | 1 | 43 | 56437240.4362 | 42016089.18 | -14421151.2562 | 21224102 | 21224102 | 0 |  |  |  | 30082113.9462 | 2024-06-30 | 2024-06-30 | 2024-07-10 | 40 | 2024-08-19 | 2024-07-27 | 1860280426.4362 | 90480931.8131 | 861619431.0834 |  | 241015625.4571 |  |  | 4370002.2 | 56437240.4362 | 1860280426.4362 | 30082113.9462 | Kattameya Creeks |  |  |  | Katameya - Creeks43 | Kattameya Creeks43
Katameya - Creeks | 1 | 44 | 49427006.6938 | 34374886.21 | -15052120.4838 | 8345106.3 | 8345106.3084 | 0.0084 |  |  |  | 8345106.3 | 2024-07-31 | 2024-07-31 | 2024-08-10 | 40 | 2024-09-19 | 2024-08-31 | 1909707433.13 | 67101367.22 | 899419335 |  | 247392879 |  |  | 4855643.2 | 49427006.6938 | 1909707433.13 | 8345106.3 | Kattameya Creeks |  |  |  | Katameya - Creeks44 | Kattameya Creeks44
Katameya - Creeks | 1 | 45 | 67801530.87 | 50790503.79 | -17011027.08 | 8654893.7 | 24274088.3716 | 15619194.6716 |  |  |  | 24274088.38 | 2024-08-31 | 2024-08-31 | 2024-09-09 | 40 | 2024-10-19 | 2024-10-03 | 1977508964 | 50090340 | 947220416 |  | 256761214 |  |  | 5144638 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks45 | Kattameya Creeks45
Katameya - Creeks | 1 | 46 | 42454238 | 0 | -42454238 | 0 | 0 | 0 |  |  |  | 22007540.78 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 40 | 2024-11-19 | 2024-11-04 | 2019963202 | 39951618 | 976799080 |  | 264112905 |  |  | 5327913 | 42454238 | 2019963202 | 22007540.78 | Kattameya Creeks |  |  |  | Katameya - Creeks46 | Kattameya Creeks46
Katameya - Creeks | 1 | 47 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-11-09 | 40 | 2024-12-19 | [8 empty] | 0 | 0 | 0 | 0 | Kattameya Creeks |  |  |  | Katameya - Creeks47 | Kattameya Creeks47
KFW | 1 | 109 | 156311.35 | 0 | -156311.35 | 128570.36 | 0 | -128570.36 |  |  |  | 128570.36 | 2017-09-30 | 2017-10-09 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-23 | 20308378.88 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KFW109 | 0109
KFW | 1 | 110 | 357187.5 | 0 | -357187.5 | 377225.16 | 0 | -377225.16 |  |  |  | 377225.16 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 20665566.38 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KFW110 | 0110
Khatatba Bridge | 2 | 1 | 42898060 | 40855295.24 | -2042764.76 | 803531.75 | 6931826.092 | 6128294.342 |  |  |  | 8313070.05 | 2022-01-31 | 2022-01-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-02-08 | 42898060 | [6 empty] | 0 | 0 | 0 | 0 | El Khatatba Bridge |  |  |  | Khatatba Bridge1 | El Khatatba Bridge1
Khatatba Bridge | 2 | 2 | 10581515 | 2437694.05 | -8143820.95 | 7509538.3 | 1381244.0525 | -6128294.2475 |  |  |  | 10363626.0758 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 53479575 | [6 empty] | 0 | 0 | 0 | 0 | El Khatatba Bridge |  |  |  | Khatatba Bridge2 | El Khatatba Bridge2
Khatatba Bridge | 2 | 4 | 50062250 | 0 | -50062250 | 36303482.3 | 0 | -36303482.3 |  |  |  | 49031394.797 | 2022-07-31 | 2022-08-01 | 2022-08-15 | 60 | 2022-10-14 | 2022-08-15 | 103541825 | [6 empty] | 0 | 0 | 0 | 0 | El Khatatba Bridge |  |  |  | Khatatba Bridge4 | El Khatatba Bridge4
KSA-Tarek AbdelHakim Center | 1 | 1 | 1174788.1 | 0 | -1174788.1 | 1183249.5731 | 0 | -1183249.5731 |  |  |  | 951578.36 | 2023-02-28 | 2023-02-28 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 1174788.1 |  |  |  |  | 117478.81 |  | 0 | 1174788.1 | 1174788.1 | 951578.36 | 0 |  |  |  | KSA-Tarek AbdelHakim Center1 | 01
KSA-Tarek AbdelHakim Center | 1 | 2 | 2619891.03 | 0 | -2619891.03 | 562894.3581 | 0 | -562894.3581 |  |  |  | 2122111.73 | 2023-03-31 | 2023-03-31 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 3794679.13 |  |  |  |  | 379467.91 |  | 0 | 2619891.03 | 3794679.13 | 2122111.73 | 0 |  |  |  | KSA-Tarek AbdelHakim Center2 | 02
KSA-Tarek AbdelHakim Center | 1 | 3 | 1124829.43 | 0 | -1124829.43 | 194180.7389 | 0 | -194180.7389 |  |  |  | 911111.84 | 2023-04-30 | 2023-04-30 | 2023-06-22 | 75 | 2023-09-05 | 2023-07-25 | 4919508.56 |  |  |  |  | 491950.85 |  | 0 | 1124829.43 | 4919508.56 | 911111.84 | 0 |  |  |  | KSA-Tarek AbdelHakim Center3 | 03
KSA-Tarek AbdelHakim Center | 1 | 4 | 1181749.35 | 0 | -1181749.35 | 242494.97 | 0 | -242494.97 |  |  |  | 957216.97 | 2023-05-31 | 2023-05-31 | 2023-07-24 | 75 | 2023-10-07 | 2023-07-25 | 6101257.91 |  |  |  |  | 610125.78 |  | 0 | 1181749.35 | 6101257.91 | 957216.97 | 0 |  |  |  | KSA-Tarek AbdelHakim Center4 | 04
KSA-Tarek AbdelHakim Center | 1 | 5 |  | 0 | 0 | 260811.86 | 0 | -260811.86 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-09-14 | 75 | 2023-11-28 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center5 | 05
KSA-Tarek AbdelHakim Center | 1 | 6 |  | 0 | 0 | 253333.77 | 0 | -253333.77 |  |  |  |  | 2023-07-31 | 2023-07-31 | 2023-09-14 | 75 | 2023-11-28 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center6 | 06
KSA-Tarek AbdelHakim Center | 1 | 7 |  | 0 | 0 | 450546.16 | 0 | -450546.16 |  |  |  |  | 2023-08-31 | 2023-08-31 | 2023-09-14 | 75 | 2023-11-28 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center7 | 07
KSA-Tarek AbdelHakim Center | 1 | 8 |  | 0 | 0 | 630195.46 | 0 | -630195.46 |  |  |  |  | 2023-09-30 | 2023-09-30 | 2023-10-17 | 75 | 2023-12-31 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center8 | 08
KSA-Tarek AbdelHakim Center | 1 | 9 |  | 0 | 0 | 1513478.59 | 0 | -1513478.59 |  |  |  |  | 2023-10-31 | 2023-11-06 | 2023-11-06 | 75 | 2024-01-20 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center9 | 09
KSA-Tarek AbdelHakim Center | 1 | 10 |  | 0 | 0 | 1468894.06 | 0 | -1468894.06 |  |  |  |  | 2023-11-30 | 2023-11-21 | 2023-11-21 | 75 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center10 | 010
KSA-Tarek AbdelHakim Center | 1 | 11 | 6272151.58 | 0 | -6272151.58 | 0 | 0 | 0 |  |  |  | 5080442.78 | 2023-12-31 | 2023-12-24 | 2023-12-24 | 75 | 2024-03-08 | 2024-01-04 | 34906557.56 |  |  |  |  | 3367198.74 |  | 0 | 6272151.58 | 34906557.56 | 5080442.78 | 0 |  |  |  | KSA-Tarek AbdelHakim Center11 | 011
KSA-Tarek AbdelHakim Center | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-05-09 | 2024-09-24 | 75 | 2024-12-08 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | KSA-Tarek AbdelHakim Center12 | 012
#N/A
LEKELA | 1 | 1 |  | 17769330.58 | 17769330.58 | 37970902.46 | 4795487.799 | -33175414.661 | 36300000 |  |  |  | 2020-03-31 | 2020-03-15 | 2020-07-19 | 60 | 2020-09-17 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA1 | Lekela 250MW Wind Farm1
LEKELA | 1 | 2 |  | 7425139.15 | 7425139.15 | 1067868.0976 | 7467890.397 | 6400022.2994 |  |  |  |  | 2020-06-30 | 2020-06-30 | 2020-07-19 | 60 | 2020-09-17 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA2 | Lekela 250MW Wind Farm2
LEKELA | 1 | 3 |  | 2093986.78 | 2093986.78 | 1758948.8952 | 1758948.889 | -0.0062 |  |  |  |  | 2020-07-31 | 2020-07-27 | 2020-07-27 | 60 | 2020-09-25 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA3 | Lekela 250MW Wind Farm3
LEKELA | 1 | 4 |  | 777289.9 | 777289.9 | 652923.5 | 652923.515 | 0.015 |  |  |  |  | 2020-08-31 | 2020-08-31 | 2020-09-12 | 60 | 2020-11-11 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA4 | Lekela 250MW Wind Farm4
LEKELA | 1 | 5 | 8446374.726 | 8446374.72 | -0.006 | 7094954.7715 | 7094954.766 | -0.00552 |  |  |  | 7094954.7715 | 2020-09-30 | 2020-09-29 | 2020-09-30 | 60 | 2020-11-29 | 2020-10-08 | 14578092.546 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA5 | Lekela 250MW Wind Farm5
LEKELA | 1 | 6 | 20620363.18 | 17262367.14 | -3357996.04 | 14840272.4231 | 14840272.417 | -0.006116 |  |  |  | 14840272.4231 | 2020-10-31 | 2020-10-28 | 2020-10-28 | 60 | 2020-12-27 | 2020-11-12 | 35198455.726 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA6 | Lekela 250MW Wind Farm6
LEKELA | 1 | 7 | 19433463.8412 | 17619865.65 | -1813598.1912 | 15073158.35 | 15073158.3375 | -0.0125 |  |  |  | 15073158.3499 | 2020-11-30 | 2020-11-22 | 2020-11-23 | 60 | 2021-01-22 | 2020-12-02 | 54631919.5672 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA7 | Lekela 250MW Wind Farm7
LEKELA | 1 | 8 | 41700595.0348 | 38206684.39 | -3493910.6448 | 33357157.2169 | 33513527.4795 | 156370.2626 |  |  |  | 33513527.4715 | 2020-12-31 | 2020-12-28 | 2020-12-28 | 60 | 2021-02-26 | 2021-01-19 | 96332514.602 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA8 | Lekela 250MW Wind Farm8
LEKELA | 1 | 9 | 23169483.21 | 21219483.49 | -1949999.72 | 18594958.1925 | 18594958.1945 | 0.001976 |  |  |  | 18594958.1925 | 2021-01-31 | 2021-01-15 | 2021-01-31 | 60 | 2021-04-01 | 2021-02-05 | 119501997.812 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA9 | Lekela 250MW Wind Farm9
LEKELA | 1 | 10 | 27064762.4727 | 24782925.38 | -2281837.0927 | 21709399.51 | 21709399.519 | 0.009 |  |  |  | 21709399.51 | 2021-02-28 | 2021-02-15 | 2021-02-17 | 60 | 2021-04-18 | 2021-03-11 | 146566760.2847 | 0 | [5 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA10 | Lekela 250MW Wind Farm10
LEKELA | 1 | 11 | 18055279.9362 | 16648813.83 | -1406466.1062 | 14896483.6 | 14823033.5915 | -73450.0085 |  |  |  | 14823033.596 | 2021-03-31 | 2021-03-15 | 2021-03-16 | 60 | 2021-05-15 | 2021-05-20 | 164622040.2209 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA11 | Lekela 250MW Wind Farm11
LEKELA | 1 | 12 | 26449156.1285 | 24308181.24 | -2140974.8885 | 21477147.745 | 21477147.752 | 0.0069623 |  |  |  | 21477147.745 | 2021-04-30 | 2021-04-15 | 2021-04-20 | 60 | 2021-06-19 | 2021-05-24 | 191071196.3494 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA12 | Lekela 250MW Wind Farm12
LEKELA | 1 | 13 | 6179424.4906 | 2899145.1 | -3280279.3906 | 2329136.4958 | 2329136.495 | -0.00080502 |  |  |  | 2329136.4958 | 2021-05-31 | 2021-05-15 | 2021-05-24 | 60 | 2021-07-23 | 2021-08-01 | 197250620.84 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA13 | Lekela 250MW Wind Farm13
LEKELA | 1 | 14 |  | 18187988.27 | 18187988.27 | 12951636.6142 | 12931636.6285 | -19999.9857 |  |  |  |  | 2021-06-30 | 2021-06-15 | 2021-07-26 | 60 | 2021-09-24 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA14 | Lekela 250MW Wind Farm14
LEKELA | 1 | 15 | 6597023.32 | 15041907.67 | 8444884.35 | 3839081.19 | 8754195.8235 | 4915114.6335 |  |  |  | 3229199.86 | 2021-10-31 | 2021-10-15 | 2022-11-15 | 60 | 2023-01-14 | 2022-12-14 | 207000000 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA15 | Lekela 250MW Wind Farm15
LEKELA | 1 | 16 | -0.0001 | 0 | 0.0001 | 8212932 | 0 | -8212932 |  |  |  | 8212932.01 | 2022-11-30 | 2022-11-20 | 2023-02-22 | 60 | 2023-04-23 | 2023-03-31 | 207000000 | [6 empty] | 0 | -0.0001 | 207000000 | 8212932.01 | Lekela 250MW Wind Farm |  |  |  | LEKELA16 | Lekela 250MW Wind Farm16
LEKELA Remedial | 1 | 2 |  | 7425139.15 | 7425139.15 | 7000000.52 | 7467890.397 | 467889.877 |  |  |  |  | 2024-01-31 | 2024-01-30 | 2024-02-26 | 60 | 2024-04-26 | [8 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA Remedial2 | Lekela 250MW Wind Farm2
LEKELA Remedial | 1 | 3 | 2884958.98 | 2093986.78 | -790972.2 | 3000357.34 | 1758948.889 | -1241408.451 |  |  |  | 3000357.86 | 2024-05-31 | 2024-05-19 | 2024-08-19 | 60 | 2024-10-18 | 2024-08-21 | 15655160.98 | [6 empty] | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA Remedial3 | Lekela 250MW Wind Farm3
LEKELA Remedial | 1 | 4 | 6153867.61 | 777289.9 | -5376577.71 | 6400022.32 | 652923.515 | -5747098.805 |  |  |  | 6400022.32 | 2024-08-31 | 2024-08-20 | 2024-08-21 | 60 | 2024-10-20 | 2024-10-20 | 21809028.59 |  |  |  | 2290980.91 |  |  | 0 | 0 | 0 | 0 | Lekela 250MW Wind Farm |  |  |  | LEKELA Remedial4 | Lekela 250MW Wind Farm4
#N/A
MDF Factory | 1 | 1 | 3709029.4 | 4162769.76 | 453740.36 | 47854244.4 | 7639890.6466 | -40214353.7534 | 41622365.4 |  |  | 6231879.24 | 2021-06-30 | 2021-06-30 | 2021-07-05 | 28 | 2021-08-02 | 2021-08-17 | 3709029.4 | 4472196.39 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory1 | MDF Factory1
MDF Factory | 1 | 2 | 5178414.72 | 14246453.58 | 9068038.86 | 13393735 | 10804321.9583 | -2589413.0417 | 6300000 |  |  | 7093735 | 2021-07-31 | 2021-08-08 | 2021-08-08 | 28 | 2021-09-05 | 2021-08-31 | 8887444.12 | 7086056.01 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory2 | MDF Factory2
MDF Factory | 1 | 3 | 9214079.17 | 12892747.34 | 3678668.17 | 18410664.56 | 11956077.4667 | -6454587.0933 | 2000000 |  |  | 8598866.23 | 2021-08-31 | 2021-08-31 | 2021-09-06 | 28 | 2021-10-04 | 2021-09-22 | 18101523.29 | 8983935.87 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory3 | MDF Factory3
MDF Factory | 1 | 4 | 9266652.88 | 12068060.73 | 2801407.85 | 19359615 | 11048205.3073 | -8311409.6927 | 2000000 |  |  | 8359615.97 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 28 | 2021-11-03 | 2021-10-27 | 27368176.17 | 10661948.66 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory4 | MDF Factory4
MDF Factory | 1 | 5 | 23662523.0739 | 28836911.51 | 5174388.4361 | 38802133.78 | 26370472.8636 | -12431660.9164 | 10016624.86 |  |  | 21785509.71 | 2021-10-31 | 2021-10-31 | 2021-11-07 | 28 | 2021-12-05 | 2021-12-05 | 51030699.2439 | 10195623.7568 | [5 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory5 | MDF Factory5
MDF Factory | 1 | 6 | 17937654.1261 | 21669465.7 | 3731811.5739 | 28503193.33 | 20230205.9677 | -8272987.3623 | 7332000 |  |  | 17171193.3155 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 28 | 2022-01-06 | 2022-01-20 | 68968353.37 | 11973915.52 | [5 empty] | 0 | 17937654.1261 | 68968353.37 | 17171193.3155 | MDF Factory |  |  |  | MDF Factory6 | MDF Factory6
MDF Factory | 1 | 7 | 16080953.7816 | 31404222.49 | 15323268.7084 | 59606480 | 15247412.6383 | -44359067.3617 | 6000000 |  |  | 14452550.5619 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 28 | 2022-02-08 | 2022-02-14 | 85049307.1516 | 12658184.96 | [5 empty] | 0 | 16588591.02 | 85556944.39 | 14851309.99 | MDF Factory |  |  |  | MDF Factory7 | MDF Factory7
MDF Factory | 1 | 8 | 12291002.2884 | 7933985.43 | -4357016.8584 | 29352571.68 | 13514522.7416 | -15838048.9384 | 11000000 |  |  | 12391060.05 | 2022-01-31 | 2022-01-31 | 2022-02-09 | 28 | 2022-03-09 | 2022-03-01 | 97340309.44 | 14426942.06 | [5 empty] | 0 | 12291002.2884 | 97340309.44 | 12391060.05 | MDF Factory |  |  |  | MDF Factory8 | MDF Factory8
MDF Factory | 1 | 9 | 8038787.77 | 10331670.72 | 2292882.95 | 18942922.65 | 8739856.8749 | -10203065.7751 | 13754630 |  |  | 7655361.33 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 28 | 2022-04-06 | 2022-04-07 | 105379097.21 | 14289033.25 |  |  |  | 2526800.69 | 2526800.69 | 0 | 8038787.77 | 105379097.21 | 7655361.33 | MDF Factory |  |  |  | MDF Factory9 | MDF Factory9
MDF Factory | 1 | 10 | 6155129.99 | 12252037.93 | 6096907.94 | 11719330.26 | 14703215.5981 | 2983885.3381 | 1488562.75 |  |  | 11119452.63 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 28 | 2022-05-11 | 2022-04-27 | 111534227.2 | 19004034.21 | [5 empty] | 0 | 6155129.99 | 111534227.2 | 11119452.63 | MDF Factory |  |  |  | MDF Factory10 | MDF Factory10
MDF Factory | 1 | 11 | 9364100.8 | 11285215.73 | 1921114.93 | 11835349.23 | 10374106.9038 | -1461242.3262 | 3000000 |  |  | 9991684.94 | 2022-04-30 | 2022-04-30 | 2022-04-28 | 28 | 2022-05-26 | 2022-06-07 | 120898328 | 19378872 | 6694496.17 |  | 8943366.16 | 2938817.5 | 2938817.5 | 985000 | 9364100.8 | 120898328 | 9991684.94 | MDF Factory |  |  |  | MDF Factory11 | MDF Factory11
MDF Factory | 1 | 12 | 27509389.27 | 37291327.43 | 9781938.16 | 25380982.3 | 25882723.2211 | 501740.9211 |  |  |  | 29337407.23 | 2022-05-31 | 2022-05-31 | 2022-06-11 | 28 | 2022-07-09 | 2022-06-29 | 148407717.27 | 21048487.96 | 9413326 |  | 14867864 | 3374171 | 3374171 | 0 | 27509389.27 | 148407717.27 | 29337407.23 | MDF Factory |  |  |  | MDF Factory12 | MDF Factory12
MDF Factory | 1 | 13 | 15343913.47 | 35534076.91 | 20190163.44 | 2351273.22 | 2860119.7471 | 508846.5271 |  |  |  | 19866888.03 | 2022-06-30 | 2022-06-30 | 2022-07-06 | 28 | 2022-08-03 | 2022-08-07 | 163751630.74 | 25112316.18 | 10650525.16 |  | 15407262.1 | 3894039.675 | 3894039.675 | 1300000 | 15343913.47 | 163751630.74 | 19866888.03 | MDF Factory |  |  |  | MDF Factory13 | MDF Factory13
MDF Factory | 1 | 14 | 11905906.3968 | 25805203.92 | 13899297.5232 | 11219362.36 | 23227533.8875 | 12008171.5275 |  |  |  | 11219361.6633 | 2022-07-31 | 2022-07-25 | 2022-08-14 | 28 | 2022-09-11 | 2022-09-25 | 175657537.1368 | 28064532.2963 | 10473927.4807 |  | 17096495.4946 | 4266369.805 | 4266369.805 | 3250000 | 12301138.79 | 176052769.53 | 15316196.46 | MDF Factory |  |  |  | MDF Factory14 | MDF Factory14
MDF Factory | 1 | 15 | 8651043.7332 | 15085332.3 | 6434288.5668 | 10812468.25 | 15790368.0492 | 4977899.7992 |  |  |  | 15409194.69 | 2022-08-31 | 2022-08-31 | 2022-09-08 | 28 | 2022-10-06 | 2022-10-09 | 184308580.87 | 33441117.05 | 10616746 |  | 16229441.88 | 4412077.4 | 4412077.4 | 1350000 | 8651043.7332 | 184308580.87 | 15409194.69 | MDF Factory |  |  |  | MDF Factory15 | MDF Factory15
MDF Factory | 1 | 16 | 21753082.06 | 13891677.72 | -7861404.34 | 10601848.06 | 12827443.3694 | 2225595.3094 |  |  |  | 22014291.85 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 28 | 2022-11-08 | 2022-11-06 | 206061662.93 | 35882692.55 | 10827826.68 |  | 16039161.03 | 4776541.575 | 4776541.575 | 3300000 | 21753082.06 | 206061662.93 | 22014291.85 | MDF Factory |  |  |  | MDF Factory16 | MDF Factory16
MDF Factory | 1 | 17 | 3503748.7 | 13012853.94 | 9509105.24 | 13701835.53 | 13738045.4627 | 36209.9327 |  |  |  | 15156893.21 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 28 | 2022-12-06 | 2022-11-23 | 209565411.63 | 38117303.52 | 12364842.71 |  | 20883147.71 | 5114135 | 5114135 | 2890000 | 3503748.7 | 209565411.63 | 15156893.21 | MDF Factory |  |  |  | MDF Factory17 | MDF Factory17
MDF Factory | 1 | 18 | 4093790.13 | 8557464.69 | 4463674.56 | 3474417.48 | 8046794.6243 | 4572377.1443 |  |  |  | 5028798.98 | 2022-11-30 | 2022-11-15 | 2022-11-27 | 28 | 2022-12-25 | 2022-12-11 | 213659201.76 | 38907634.85 | 12512881.83 |  | 19805682.68 | 5216480 | 5216480 | 2840000 | 4093790.13 | 213659201.76 | 5028798.98 | MDF Factory |  |  |  | MDF Factory18 | MDF Factory18
MDF Factory | 1 | 19 | 12077854.33 | 18177972.44 | 6100118.11 | 8855940.16 | 13406399.725 | 4550459.565 |  |  |  | 9756751.36 | 2022-11-30 | 2022-11-30 | 2022-12-12 | 28 | 2023-01-09 | 2022-12-28 | 225737056.09 | 37074813.73 | 17269270.26 |  | 19805682.68 | 5518426.4 | 5518426.4 | 1240000 | 12077854.33 | 225737056.09 | 9756751.36 | MDF Factory |  |  |  | MDF Factory19 | MDF Factory19
MDF Factory | 1 | 20 | 10662163.65 | 12424707.76 | 1762544.11 | 1506264.66 | 3607979.0847 | 2101714.4247 |  |  |  | 14838164.52 | 2022-12-31 | 2022-12-25 | 2022-12-22 | 28 | 2023-01-19 | 2023-01-12 | 236399219.74 | 44141114.86 | 18934354.95 |  | 21551157.34 | 5784980.495 | 5784980.495 | 1240000 | 10662163.65 | 236399219.74 | 14838164.52 | MDF Factory |  |  |  | MDF Factory20 | MDF Factory20
MDF Factory | 1 | 21 | 18933899.86 | 14221356.8 | -4712543.06 | 16783340.22 | 7032766.641 | -9750573.579 |  |  |  | 18749752.53 | 2023-01-31 | 2023-01-12 | 2023-01-19 | 28 | 2023-02-16 | 2023-02-06 | 255333119.6 | 44152242.9 | 21222761.6 |  | 32601298.43 | 6258327.99 | 6258327.99 | 890000 | 18933899.86 | 255333119.6 | 18749752.53 | MDF Factory |  |  |  | MDF Factory21 | MDF Factory21
MDF Factory | 1 | 22 | 3256087.31 | 9643470.77 | 6387383.46 | 9454487.21 | 9336218.2731 | -118268.9369 |  |  |  | 3016784.72 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 28 | 2023-03-08 | 2023-02-25 | 258589206.91 | 44812446.87 | 22595375.04 | 400000 | 31182122.08 | 6339730 | 6339730 | 490000 | 3256087.31 | 258589206.91 | 3016784.72 | MDF Factory |  |  |  | MDF Factory22 | MDF Factory22
MDF Factory | 1 | 23 | 38888289.8 | 37819950.25 | -1068339.55 | 10035885.59 | 14557763.9768 | 4521878.3868 |  |  |  | 26140854.32 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 28 | 2023-04-02 | 2023-03-22 | 297477496.71 | 41744854.59 | 37403483.04 | 400000 | 31433209.86 | 7311937.42 | 7311937.42 | 470000 | 38888289.8 | 297477496.71 | 26140854.32 | MDF Factory |  |  |  | MDF Factory23 | MDF Factory23
MDF Factory | 1 | 24 | 18681389.16 | 20607720.2 | 1926331.04 | 5923051.17 | 2441794.1756 | -3481256.9944 |  |  |  | 13504786.11 | 2023-03-31 | 2023-03-31 | 2023-04-04 | 28 | 2023-05-02 | 2023-04-30 | 316158885.87 | 36725913.89 | 48869956.89 | 400000 | 31459228.76 | 7778972.145 | 7778972.145 | 470000 | 18681389.16 | 316158885.87 | 13504786.11 | MDF Factory |  |  |  | MDF Factory24 | MDF Factory24
MDF Factory | 1 | 25 | 10484631.76 | 11020344.59 | 535712.83 | 4519315.77 | 5060375.9885 | 541060.2185 |  |  |  | 14874774.09 | 2023-04-30 | 2023-04-30 | 2023-05-08 | 28 | 2023-06-05 | 2023-06-05 | 326643517.63 | 41744047.17 | 58047371.04 | 650000 | 31459228.76 | 8041087.94 | 8041087.94 | 400000 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory25 | MDF Factory25
MDF Factory | 1 | 26 | 21011393.06 | 21659546.55 | 648153.49 | 12901160.06 | 13730860.297 | 829700.237 |  |  |  | 18123054.07 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 28 | 2023-07-06 | 2023-06-21 | 347654910.69 | 39628505.18 | 73625314.2 | 200000 | 33225314.57 | 8566372.765 | 8566372.765 | 450000 | 21011393.06 | 347654910.69 | 18123054.07 | MDF Factory |  |  |  | MDF Factory26 | MDF Factory26
MDF Factory | 1 | 27 | 10160280.74 | 7649824.31 | -2510456.43 | 19177600.34 | 19177600.34 | 0 |  |  |  | 21231778.46 | 2023-06-30 | 2023-06-30 | 2023-06-26 | 28 | 2023-07-24 | 2023-07-12 | 357815191.43 | 54504636.34 | 81071518.94 | 250000 | 33210812.42 | 8820379.785 | 8820379.785 | 450000 | 10160280.74 | 357815191.43 | 21231778.46 | MDF Factory |  |  |  | MDF Factory27 | MDF Factory27
MDF Factory | 1 | 28 | 4632219.77 | 4537395.02 | -94824.75 | 5380287.99 | 5380287.99 | 0 |  |  |  | 5471658.1245 | 2023-07-31 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 | 2023-07-31 | 362447411.2 | 57298682.38 | 84101651.16 | 200000 | 33299495.32 | 8936185.28 | 8936185.28 | 500000 | 4632219.77 | 362447411.2 | 5471658.1245 | MDF Factory |  |  |  | MDF Factory28 | MDF Factory28
MDF Factory | 1 | 29 | 7201895.8 | 6882776.19 | -319119.61 | 10038430.32 | 10041845.6384 | 3415.3184 |  |  |  | 13138195.96 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 28 | 2023-09-05 | 2023-09-10 | 369649307 | 63433973.15 | 88923223.93 | 200000 | 35138135.49 | 9116232.675 | 9116232.675 | 520000 | 7201895.8 | 369649307 | 13138195.96 | MDF Factory |  |  |  | MDF Factory29 | MDF Factory29
MDF Factory | 1 | 30 | 42878737.92 | 46563799.32 | 3685061.4 | 11530799.53 | 11554812.9428 | 24013.4128 |  |  |  | 12581507.75 | 2023-08-31 | 2023-08-30 | 2023-09-10 | 28 | 2023-10-08 | 2023-09-19 | 412528044.92 | 48447410.77 | 120743192.13 | 200000 | 35183358.23 | 10188201.125 | 10188201.125 | 550000 | 42878737.92 | 412528044.92 | 12581507.75 | MDF Factory |  |  |  | MDF Factory30 | MDF Factory30
MDF Factory | 1 | 31 | 26984773 | 25781281.67 | -1203491.33 | 18846610.6 | 18542599.6668 | -304010.9332 |  |  |  | 20429584.53 | 2023-09-30 | 2023-09-30 | 2023-10-05 | 28 | 2023-11-02 | 2023-10-07 | 439512817.92 | 52299084.09 | 141277943.84 | 200000 | 34937145.36 | 10862820.45 | 10862820.45 | 250000 | 26984773 | 439512817.92 | 20429584.53 | MDF Factory |  |  |  | MDF Factory31 | MDF Factory31
MDF Factory | 1 | 32 | 2754000 | 2754000 | 0 | 2726460 | 2726460 | 0 |  |  |  | 2726460 | 2023-10-31 | 2023-10-25 | 2023-10-26 | 28 | 2023-11-23 | 2023-10-26 | 442266817.92 | 52299084.09 | 144031943.84 | 200000 | 34937145.36 | 10931670.45 | 10931670.45 | 250000 | 2754000 | 442266817.92 | 2726460 | MDF Factory |  |  |  | MDF Factory32 | MDF Factory32
MDF Factory | 1 | 33 | 20665276.54 | 18965945.93 | -1699330.61 | 8808260.33 | 10638561.7072 | 1830301.3772 |  |  |  | 12154985.64 | 2023-10-31 | 2023-10-31 | 2023-11-07 | 28 | 2023-12-05 | 2023-11-25 | 462932094.46 | 52125340.59 | 161100913.16 | 250000 | 35201311.24 | 11448302 | 11448302 | 200000 | 20665276.54 | 462932094.46 | 12154985.64 | MDF Factory |  |  |  | MDF Factory33 | MDF Factory33
MDF Factory | 1 | 34 | 25469525.62 | 27337098.5 | 1867572.88 | 12466636.78 | 12636241.38 | 169604.6 |  |  |  | 13093494.9 | 2023-11-30 | 2023-11-30 | 2023-12-09 | 28 | 2024-01-06 | 2023-12-20 | 488401620.08 | 49181191.79 | 181875990.6 | 250000 | 35200228.82 | 12085040.5 | 12085040.5 | 200000 | 25469525.62 | 488401620.08 | 13093494.9 | MDF Factory |  |  |  | MDF Factory34 | MDF Factory34
MDF Factory | 1 | 35 | 7460561 | 8184195.01 | 723634.01 | 11964736.84 | 11964736.84 | 0 |  |  |  | 14005346.87 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 28 | 2024-01-28 | 2024-01-21 | 495862181.08 | 56480937.48 | 187067355.65 | 100000 | 35200149.54 | 12271554.525 | 12271554.525 | 350000 | 7460561 | 495862181.08 | 14005346.87 | MDF Factory |  |  |  | MDF Factory35 | MDF Factory35
MDF Factory | 1 | 36 | 24220349.75 | 24401575.22 | 181225.47 | 10194821.77 | 10167393.0388 | -27428.7312 |  |  |  | 12150509.06 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-28 | 520082530.83 | 52738337.77 | 208687659.78 | 200000 | 35240386.14 | 12877063.27 | 12877063.27 | 220000 | 24220349.75 | 520082530.83 | 12150509.06 | MDF Factory |  |  |  | MDF Factory36 | MDF Factory36
MDF Factory | 1 | 37 | 18799337.86 | 18482561.46 | -316776.4 | 4465149.39 | 4465149.39 | 0 |  |  |  | 7449862.86 | 2024-02-29 | 2024-02-29 | 2024-03-11 | 28 | 2024-04-08 | 2024-04-02 | 538881868.69 | 47546890.76 | 225598759.07 | 1500000 | 35240386.14 | 13347046.715 | 13347046.715 | 700000 | 18799337.86 | 538881868.69 | 7449862.86 | MDF Factory |  |  |  | MDF Factory37 | MDF Factory37
MDF Factory | 1 | 38 | 25264630.57 | 25020067.65 | -244562.92 | 9539881.65 | 9539881.65 | 0 |  |  |  | 10129299.6901 | 2024-03-31 | 2024-03-31 | 2024-04-08 | 28 | 2024-05-06 | 2024-04-24 | 564146499.26 | 42828938.17 | 247874489.5 | 200000 | 35240386.14 | 13978662.48 | 13978662.48 | 253450 | 25264630.57 | 564146499.26 | 10129299.6901 | MDF Factory |  |  |  | MDF Factory38 | MDF Factory38
MDF Factory | 1 | 39 | 17461783.47 | 17738610.9 | 276827.43 | 6984174.92 | 6984174.92 | 0 |  |  |  | 7951387.28 | 2024-04-30 | 2024-04-30 | 2024-05-07 | 28 | 2024-06-04 | 2024-05-22 | 581608282.73 | 39702840.21 | 261893208.84 | 200000 | 35240386.14 | 14415207 | 14415207 | 253450 | 17461783.47 | 581608282.73 | 7951387.28 | MDF Factory |  |  |  | MDF Factory39 | MDF Factory39
MDF Factory | 1 | 40 | -0.73 | 759488.56 | 759489.29 | 13054639.6 | 14022964.76 | 968325.16 |  |  |  | 13055049.84 | 2024-04-30 | 2024-04-30 | 2024-05-26 | 28 | 2024-06-23 | 2024-06-12 | 581608282 | 39702840 | 261893208 |  | 35240386 | 6101647 |  | 453450 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory40 | MDF Factory40
MDF Factory | 1 | 41 | 26553112.48 | 12031521.12 | -14521591.36 | 8347962.7 | 7229637.5348 | -1118325.1652 |  |  |  | 25000718.68 | 2024-05-31 | 2024-05-31 | 2024-06-06 | 28 | 2024-07-04 | 2024-06-13 | 608161394.48 | 40071589.73 | 273875725.24 |  | 35240386.14 | 7033092.855 | 7033092.855 | 303450 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory41 | MDF Factory41
MDF Factory | 1 | 42 | 750284.2 | 19536964.22 | 18786680.02 | 7602001.04 | 7602001.04 | 0 |  |  |  | 7547918.7 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 28 | 2024-08-04 | 2024-07-24 | 608911678.68 | 33497125 | 289636214 |  | 35240386 | 7100876.5 | 7100876.5 | 453450 | 750284.2 | 608911678.68 | 7547918.7 | MDF Factory |  |  |  | MDF Factory42 | MDF Factory42
MDF Factory | 1 | 43 | 11210135.32 | 0 | -11210135.32 | 45999180 | 0 | -45999180 |  |  |  | 57977475.46 | 2024-07-31 | 2024-07-31 | 2024-08-06 | 28 | 2024-09-03 | 2024-08-21 | 620121814 | 31321429 | 299419159 |  | 35243045 | 7887682 | 7887682 | 553450 | 11210135.32 | 620121814 | 57977475.46 | MDF Factory |  |  |  | MDF Factory43 | MDF Factory43
MDF Factory | 1 | 44 | 10205950.6 | 0 | -10205950.6 | 0 | 0 | 0 |  |  |  | 13417821.66 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 28 | 2024-10-03 | 2024-09-26 | 630327764.6 | 30187176.6062 | 308819628.409 |  | 35266531.1337 | 15775364.249 |  | 4593450 | 10205950.6 | 630327764.6 | 13417821.66 | MDF Factory |  |  |  | MDF Factory44 | MDF Factory44
MDF Factory | 1 | 45 | 16259922.8 | 0 | -16259922.8 | 0 | 0 | 0 |  |  |  | 21518034.22 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 28 | 2024-11-07 | 2024-11-04 | 646587687.4 | 21616659 | 325129806 |  | 34015260 | 15775364 |  | 3833450 | 16259922.8 | 646587687.4 | 21518034.22 | MDF Factory |  |  |  | MDF Factory45 | MDF Factory45
MDF Factory - Equip. | 1 | 1 | 474511.19 | 4162769.76 | 3688258.57 | 479255 | 7639890.6466 | 7160635.6466 |  |  |  | 487660.4 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-16 | 474511.19 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.1 | MDF Factory1
MDF Factory - Equip. | 1 | 2 | 2969783.71 | 14246453.58 | 11276669.87 | 2957905.39 | 10804321.9583 | 7846416.5683 |  |  |  | 2999481.54 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-18 | 3444294.9 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.2 | MDF Factory2
MDF Factory - Equip. | 1 | 3 | 2443276.13 | 12892747.34 | 10449471.21 | 2467707.5 | 11956077.4667 | 9488369.9667 |  |  |  | 2478572.15 | 2022-01-31 | 2022-02-15 | 2022-02-22 | 28 | 2022-03-22 | 2022-03-01 | 5887571.03 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.3 | MDF Factory3
MDF Factory - Equip. | 1 | 4 |  | 12068060.73 | 12068060.73 | 2118826 | 11048205.3073 | 8929379.3073 |  |  |  |  | 2022-03-31 | 2022-03-15 | 2022-03-29 | 28 | 2022-04-26 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.4 | MDF Factory4
MDF Factory - Equip. | 1 | 5 |  | 28836911.51 | 28836911.51 | 2067056 | 26370472.8636 | 24303416.8636 |  |  |  |  | 2022-04-30 | 2022-04-15 | 2022-04-24 | 28 | 2022-05-22 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.5 | MDF Factory5
MDF Factory - Equip. | 1 | 6 |  | 21669465.7 | 21669465.7 | 569764 | 20230205.9677 | 19660441.9677 |  |  |  |  | 2022-05-31 | 2022-05-15 | 2022-05-24 | 28 | 2022-06-21 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.6 | MDF Factory6
MDF Factory - Equip. | 1 | 7 |  | 31404222.49 | 31404222.49 | 795032 | 15247412.6383 | 14452380.6383 |  |  |  |  | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.7 | MDF Factory7
MDF Factory - Equip. | 1 | 8 | 340101.34 | 7933985.43 | 7593884.09 | 322760 | 13514522.7416 | 13191762.7416 |  |  |  | 324002.35 | 2022-07-31 | 2022-07-15 | 2022-07-25 | 28 | 2022-08-22 | 2022-08-02 | 11819751.78 | [6 empty] | 0 | 340101.34 | 11819751.78 | 324002.35 | MDF Factory |  |  |  | MDF Factory - Equip.8 | MDF Factory8
MDF Factory - Equip. | 1 | 9 |  | 10331670.72 | 10331670.72 | 1546900 | 8739856.8749 | 7192956.8749 |  |  |  |  | 2022-08-31 | 2022-08-15 | 2022-08-29 | 28 | 2022-09-26 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.9 | MDF Factory9
MDF Factory - Equip. | 1 | 10 |  | 12252037.93 | 12252037.93 | 362327.85 | 14703215.5981 | 14340887.7481 |  |  |  |  | 2022-09-30 | 2022-09-15 | 2022-09-20 | 28 | 2022-10-18 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.10 | MDF Factory10
MDF Factory - Equip. | 1 | 11 |  | 11285215.73 | 11285215.73 | 115740.16 | 10374106.9038 | 10258366.7438 |  |  |  |  | 2022-10-31 | 2022-10-15 | 2022-11-01 | 28 | 2022-11-29 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.11 | MDF Factory11
MDF Factory - Equip. | 1 | 12 |  | 37291327.43 | 37291327.43 | 617997.99 | 25882723.2211 | 25264725.2311 |  |  |  |  | 2022-11-30 | 2022-11-15 | 2022-11-30 | 28 | 2022-12-28 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.12 | MDF Factory12
MDF Factory - Equip. | 1 | 13 |  | 35534076.91 | 35534076.91 | 1033353.65 | 2860119.7471 | 1826766.0971 |  |  |  |  | 2022-12-31 | 2022-12-15 | 2023-01-04 | 28 | 2023-02-01 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.13 | MDF Factory13
MDF Factory - Equip. | 1 | 14 |  | 25805203.92 | 25805203.92 | 1342515 | 23227533.8875 | 21885018.8875 |  |  |  |  | 2023-01-31 | 2023-01-15 | 2023-02-05 | 28 | 2023-03-05 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.14 | MDF Factory14
MDF Factory - Equip. | 1 | 15 |  | 15085332.3 | 15085332.3 | 1508230 | 15790368.0492 | 14282138.0492 |  |  |  |  | 2023-02-28 | 2023-02-15 | 2023-03-05 | 28 | 2023-04-02 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.15 | MDF Factory15
MDF Factory - Equip. | 1 | 16 |  | 13891677.72 | 13891677.72 | 963455.46 | 12827443.3694 | 11863987.9094 |  |  |  |  | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.16 | MDF Factory16
MDF Factory - Equip. | 1 | 17 |  | 13012853.94 | 13012853.94 | 359356.67 | 13738045.4627 | 13378688.7927 |  |  |  |  | 2023-05-31 | 2023-06-15 | 2023-06-18 | 28 | 2023-07-16 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.17 | MDF Factory17
MDF Factory - Equip. | 1 | 18 |  | 8557464.69 | 8557464.69 | 536737.62 | 8046794.6243 | 7510057.0043 |  |  |  |  | 2023-06-30 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.18 | MDF Factory18
MDF Factory - Equip. | 1 | 19 | 461776.49 | 18177972.44 | 17716195.95 | 1190791 | 13406399.725 | 12215608.725 |  |  |  | 1199203.75 | 2023-08-31 | 2023-08-30 | 2023-09-09 | 28 | 2023-10-07 | 2023-10-02 | 21352041.9 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.19 | MDF Factory19
MDF Factory - Equip. | 1 | 20 |  | 12424707.76 | 12424707.76 | 606416.12 | 3607979.0847 | 3001562.9647 |  |  |  |  | 2023-09-30 | 2023-09-30 | 2023-10-16 | 28 | 2023-11-13 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.20 | MDF Factory20
MDF Factory - Equip. | 1 | 21 | 540952.41 | 14221356.8 | 13680404.39 | 600370.17 | 7032766.641 | 6432396.471 |  |  |  | 592013.93 | 2023-12-31 | 2023-12-20 | 2023-12-25 | 28 | 2024-01-22 | 2024-02-06 | 22578347.52 | [6 empty] | 0 | 540952.41 | 22578347.52 | 592013.93 | MDF Factory |  |  |  | MDF Factory - Equip.21 | MDF Factory21
MDF Factory - Equip. | 1 | 22 |  | 9643470.77 | 9643470.77 | 205199.38 | 9336218.2731 | 9131018.8931 |  |  |  |  | 2024-03-31 | 2024-03-31 | 2024-03-31 | 28 | 2024-04-28 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.22 | MDF Factory22
MDF Factory - Equip. | 1 | 23 | 539934.96 | 37819950.25 | 37280015.29 | 545334.31 | 14557763.9768 | 14012429.6668 |  |  |  | 638068.17 | 2024-04-30 | 2024-04-15 | 2024-05-02 | 28 | 2024-05-30 | 2024-05-08 | 23413265.89 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.23 | MDF Factory23
MDF Factory - Equip. | 1 | 24 | 250311 | 20607720.2 | 20357409.2 | 345289.58 | 2441794.1756 | 2096504.5956 |  |  |  | 252814.11 | 2024-04-30 | 2024-04-15 | 2024-05-08 | 28 | 2024-06-05 | 2024-05-21 | 23663576.89 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.24 | MDF Factory24
MDF Factory - Equip. | 1 | 25 | 631287.83 | 11020344.59 | 10389056.76 | 637190.72 | 5060375.9885 | 4423185.2685 |  |  |  | 637600.71 | 2024-06-30 | 2024-06-30 | 2024-06-26 | 28 | 2024-07-24 | 2024-07-01 | 24294864.72 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.25 | MDF Factory25
MDF Factory - Equip. | 1 | 26 | 1237289.1 | 21659546.55 | 20422257.45 | 0 | 13730860.297 | 13730860.297 |  |  |  | 1250071.98 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 28 | 2024-09-29 | 2024-10-02 | 25532153.82 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.26 | MDF Factory26
MDF Factory - Equip. | 1 | 27 | 20666.66 | 7649824.31 | 7629157.65 | 0 | 19177600.34 | 19177600.34 |  |  |  | 2574782 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 28 | 2024-10-28 | 2024-10-17 | 25552820.48 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Equip.27 | MDF Factory27
MDF Factory - Local Fabrication | 1 | 1 |  | 4162769.76 | 4162769.76 | 920351.25 | 7639890.6466 | 6719539.3966 |  |  |  |  | 2022-02-28 | 2022-02-15 | 2022-03-03 | 28 | 2022-03-31 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication1 | MDF Factory1
MDF Factory - Local Fabrication | 1 | 2 |  | 14246453.58 | 14246453.58 | 711105.4 | 10804321.9583 | 10093216.5583 |  |  |  |  | 2022-03-31 | 2022-03-15 | 2022-03-21 | 28 | 2022-04-18 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication2 | MDF Factory2
MDF Factory - Local Fabrication | 1 | 3 | 1275030.41 | 12892747.34 | 11617716.93 | 897908 | 11956077.4667 | 11058169.4667 |  |  |  | 926763.57 | 2022-03-31 | 2022-04-10 | 2022-04-13 | 28 | 2022-05-11 | 2022-05-10 | 7663208.07 |  |  |  |  | 330996.915 | 330996.915 | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication3 | MDF Factory3
MDF Factory - Local Fabrication | 1 | 4 |  | 12068060.73 | 12068060.73 | 667444 | 11048205.3073 | 10380761.3073 |  |  |  |  | 2022-05-31 | 2022-05-15 | 2022-05-26 | 28 | 2022-06-23 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication4 | MDF Factory4
MDF Factory - Local Fabrication | 1 | 5 | 3437985.57 | 28836911.51 | 25398925.94 | 2517907.41 | 26370472.8636 | 23852565.4536 |  |  |  | 2517906.93 | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 | 2022-06-20 | 11948651.83 |  |  |  |  | 597432.59 | 597432.59 | 45737 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication5 | MDF Factory5
MDF Factory - Local Fabrication | 1 | 6 | 1016613.3233 | 21669465.7 | 20652852.3767 | 737043.71 | 20230205.9677 | 19493162.2577 |  |  |  | 737044.172 | 2022-07-31 | 2022-07-15 | 2022-08-11 | 28 | 2022-09-08 | 2022-09-22 | 12965265.1533 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication6 | MDF Factory6
MDF Factory - Local Fabrication | 1 | 7 | 2281868.7949 | 31404222.49 | 29122353.6951 | 785269 | 15247412.6383 | 14462143.6383 |  |  |  | 785269.1906 | 2022-08-31 | 2022-08-15 | 2022-08-30 | 28 | 2022-09-27 | 2022-09-22 | 15247133.9482 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication7 | MDF Factory7
MDF Factory - Local Fabrication | 1 | 8 | 619278.6162 | 7933985.43 | 7314706.8138 | 381060.37 | 13514522.7416 | 13133462.3716 |  |  |  | 1318063.6318 | 2022-09-30 | 2022-09-15 | 2022-09-22 | 28 | 2022-10-20 | 2022-09-22 | 15866412.5644 | [6 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication8 | MDF Factory8
MDF Factory - Local Fabrication | 1 | 9 |  | 10331670.72 | 10331670.72 | 1752018.76 | 8739856.8749 | 6987838.1149 |  |  |  |  | 2022-10-31 | 2022-11-15 | 2022-11-16 | 28 | 2022-12-14 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication9 | MDF Factory9
MDF Factory - Local Fabrication | 1 | 10 |  | 12252037.93 | 12252037.93 | 2881529.05 | 14703215.5981 | 11821686.5481 |  |  |  |  | 2022-11-30 | 2022-12-15 | 2022-12-26 | 28 | 2023-01-23 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication10 | MDF Factory10
MDF Factory - Local Fabrication | 1 | 11 |  | 11285215.73 | 11285215.73 | 2412700.43 | 10374106.9038 | 7961406.4738 |  |  |  |  | 2023-01-31 | 2023-01-15 | 2023-02-18 | 28 | 2023-03-18 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication11 | MDF Factory11
MDF Factory - Local Fabrication | 1 | 12 |  | 37291327.43 | 37291327.43 | 0 | 25882723.2211 | 25882723.2211 |  |  |  |  | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication12 | MDF Factory12
MDF Factory - Local Fabrication | 1 | 13 |  | 35534076.91 | 35534076.91 | 0 | 2860119.7471 | 2860119.7471 |  |  |  |  | 2023-06-30 | 2023-06-15 | 2023-06-21 | 28 | 2023-07-19 | [8 empty] | 0 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication13 | MDF Factory13
MDF Factory - Local Fabrication | 1 | 14 | 12083527.18 | 25805203.92 | 13721676.74 | 10315795 | 23227533.8875 | 12911738.8875 |  |  |  | 11829412.85 | 2023-07-31 | 2023-08-15 | 2023-08-29 | 28 | 2023-09-26 | 2023-10-02 | 41889851.51 |  | 24971308.61 |  |  | 2094492.575 | 2094492.575 | 112541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication14 | MDF Factory14
MDF Factory - Local Fabrication | 1 | 15 | 5403242.47 | 15085332.3 | 9682089.83 | 2970230 | 15790368.0492 | 12820138.0492 |  |  |  | 5457274.9 | 2023-08-31 | 2023-10-15 | 2023-11-08 | 28 | 2023-12-06 | 2023-12-18 | 47293093.98 |  |  |  |  | 2364654.7 | 2364654.7 | 112541 | 5403242.47 | 47293093.98 | 5457274.9 | MDF Factory |  |  |  | MDF Factory - Local Fabrication15 | MDF Factory15
MDF Factory - Local Fabrication | 1 | 16 | 1250000 | 13891677.72 | 12641677.72 | 1262500 | 12827443.3694 | 11564943.3694 |  |  |  | 1262500 | 2023-11-30 | 2023-11-15 | 2023-12-03 | 28 | 2023-12-31 | 2024-02-11 | 48543093.98 |  |  |  |  | 2427154.7 | 2427154.7 | 66804 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication16 | MDF Factory16
MDF Factory - Local Fabrication | 1 | 17 | -0.001 | 13012853.94 | 13012853.941 | 0 | 13738045.4627 | 13738045.4627 |  |  |  | 0.0001 | 2023-12-31 | 2023-12-25 | 2023-12-25 | 28 | 2024-01-22 | 2024-04-22 | 48543093.98 |  |  |  |  | 2427154.7 | 2427154.7 | 112541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication17 | MDF Factory17
MDF Factory - Local Fabrication | 1 | 18 | 4414101.95 | 8557464.69 | 4143362.74 | 4265111 | 8046794.6243 | 3781683.6243 |  |  |  | 4458904.86 | 2024-01-31 | 2024-01-15 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-22 | 52957195.93 |  |  |  |  | 2647859.795 | 2647859.795 | 112541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication18 | MDF Factory18
MDF Factory - Local Fabrication | 1 | 19 | 4220898.94 | 18177972.44 | 13957073.5 | 3358613 | 13406399.725 | 10047786.725 |  |  |  | 4456901.8 | 2024-02-29 | 2024-03-15 | 2024-03-20 | 28 | 2024-04-17 | 2024-04-04 | 57178094.87 |  |  |  |  | 2858904.5 | 2858904.5 | 882541 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication19 | MDF Factory19
MDF Factory - Local Fabrication | 1 | 20 | 1196029.38 | 12424707.76 | 11228678.38 | 0 | 3607979.0847 | 3607979.0847 |  |  |  | 2286278.72 | 2024-05-31 | 2024-05-15 | 2024-07-03 | 28 | 2024-07-31 | 2024-07-29 | 58374124.25 |  |  |  |  | 2918706 | 2918706 | 66804 | 0 | 0 | 0 | MDF Factory |  |  |  | MDF Factory - Local Fabrication20 | MDF Factory20
#N/A
Mechanical Installation | 1 | 1 | 96641266.36 | 4758315.53 | -91882950.83 | 15000000 | 3615843.9682 | -11384156.0318 | 15000000 |  |  | 2845427.8 | 2024-01-31 | 2024-01-31 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 96641266.36 | [6 empty] | 0 | 0 | 0 | 0 | EGAT Mechanical Installations |  |  |  | Mechanical Installation1 | EGAT Mechanical Installations1
Mechanical Installation | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-31 | 2024-06-01 | 42 | 2024-07-13 | [8 empty] | 0 | 0 | 0 | 0 | EGAT Mechanical Installations |  |  |  | Mechanical Installation9 | EGAT Mechanical Installations9
Mintra | 1 | 1 | 26487256.44 | 0 | -26487256.44 | 15500000 | 0 | -15500000 | 10000000 |  |  | 2860852.09 | 2018-05-31 | 2018-05-29 | 2018-07-09 | 15 | 2018-07-24 | 2018-09-18 | 26487256.44 | 0 | [5 empty] | 17226261.898 | 26487256.44 | 26487256.44 | 2860852.09 | 0 |  |  |  | Mintra1 | 01
Mintra | 1 | 2 | 16295714.9 | 0 | -16295714.9 | 3000000 | 0 | -3000000 |  |  |  | 1791407.73 | 2018-07-31 | 2018-07-21 | 2018-07-25 | 15 | 2018-08-09 | 2018-09-23 | 42782971.34 | 3426213 | [5 empty] | 31002926.91 | 16295714.9 | 42782971.34 | 1791407.73 | 0 |  |  |  | Mintra2 | 02
Mintra | 1 | 3 | 19469085.79 | 0 | -19469085.79 | 2220782.14 | 0 | -2220782.14 |  |  |  | 2220782.14 | 2018-08-31 | 2018-09-15 | 2018-09-23 | 15 | 2018-10-08 | 2018-10-15 | 62252057.13 | 0 | [5 empty] | 41220014.7 | 19469085.79 | 62252057.13 | 2220782.14 | 0 |  |  |  | Mintra3 | 03
Mintra | 1 | 4 | 9723925.4204 | 0 | -9723925.4204 | 3500000 | 0 | -3500000 |  |  |  | 2907075.5801 | 2018-09-30 | 2018-10-10 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-18 | 71975982.5504 | [6 empty] | 47988244.922 | 9723925.4204 | 71975982.5504 | 2907075.5801 | 0 |  |  |  | Mintra4 | 04
Mintra | 1 | 5 |  | 0 | 0 | 8000000 | 0 | -8000000 |  |  |  |  | 2018-11-30 | 2018-12-10 | 2018-12-18 | 15 | 2019-01-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mintra5 | 05
Mintra | 1 | 6 |  | 0 | 0 | 6000000 | 0 | -6000000 |  |  |  |  | 2019-03-31 | 2019-03-28 | 2019-04-15 | 15 | 2019-04-30 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mintra6 | 06
Mintra | 1 | 7 |  | 0 | 0 | 2005948.91 | 0 | -2005948.91 |  |  |  |  | 2019-09-30 | 2019-11-17 | 2021-02-03 | 15 | 2021-02-18 | [9 empty] | 0 | 0 | 0 | 0 |  |  |  | Mintra7 | 07
Mintra-Hanger 1200m2 | 1 | 1 | 1411985.3421 | 0 | -1411985.3421 | 531998.67 | 0 | -531998.67 |  |  |  | 531998.6721 | 2018-10-31 | 2018-10-18 | 2018-10-21 | 15 | 2018-11-05 | 2018-10-29 | 1411985.3421 | [6 empty] | 879986.67 | 1411985.3421 | 1411985.3421 | 531998.6721 | 0 |  |  |  | Mintra-Hanger 1200m21 | 01
Mintra-Hanger 1200m2 | 1 | 2 |  | 0 | 0 | -6217.18 | 0 | 6217.18 |  |  |  |  | 2019-09-30 | 2019-09-30 | 2021-02-03 | 15 | 2021-02-18 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mintra-Hanger 1200m22 | 02
#N/A
Mivida-PK#140 | 1 | 1 | 4797449.5194 | 4797449.52 | 0.0006 | 18101272.3255 | 2533668.016 | -15567604.3095 | 15567604.3 |  |  | 2533668.0255 | 2019-05-31 | 2019-05-31 | 2019-06-10 | 40 | 2019-07-20 | 2019-06-27 | 4797449.5194 | 0 | [5 empty] | 45335.898 | 4797449.5194 | 4797449.5194 | 2533668.0255 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1401 | EMAAR- Pkg 140-ITP-Mivida1
Mivida-PK#140 | 1 | 2 | 4911239.0806 | 4911239.08 | -0.0006 | 9934857.73 | 2620895.13 | -7313962.6 | 7313962.6 |  |  | 2620895.13 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 40 | 2019-08-13 | 2019-07-21 | 9708688.6 | [6 empty] | 91747.11 | 4911239.0806 | 9708688.6 | 2620895.13 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1402 | EMAAR- Pkg 140-ITP-Mivida2
Mivida-PK#140 | 1 | 3 | 6244069.8629 | 6247225.23 | 3155.3671 | 4070832.3885 | 4070832.4 | 0.011547 |  |  |  | 4070832.3885 | 2019-07-31 | 2019-07-31 | 2019-08-04 | 40 | 2019-09-13 | 2019-08-20 | 15952758.4629 | 207615.6315 | [5 empty] | 152651.9264 | 6244069.8629 | 15952758.4629 | 4070832.3885 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1403 | EMAAR- Pkg 140-ITP-Mivida3
Mivida-PK#140 | 1 | 4 | 2442385.7689 | 2442385.78 | 0.011145 | 999645.4398 | 999645.44 | 0.00017344 |  |  |  | 999645.4398 | 2019-08-31 | 2019-08-31 | 2019-09-01 | 40 | 2019-10-11 | 2019-09-17 | 18395144.2317 | 207615.6315 | [5 empty] | 175732.4719 | 2442385.7689 | 18395144.2317 | 999645.4398 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1404 | EMAAR- Pkg 140-ITP-Mivida4
Mivida-PK#140 | 1 | 5 | 1994559.8383 | 1994559.84 | 0.0017124 | 1337507.07 | 1337507.07 | 0 |  |  |  | 1337507.07 | 2019-09-30 | 2019-09-30 | 2019-10-02 | 40 | 2019-11-11 | 2019-10-23 | 20389704.07 | 207615.63 | [5 empty] | 194581.06 | 1994559.8383 | 20389704.07 | 1337507.07 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1405 | EMAAR- Pkg 140-ITP-Mivida5
Mivida-PK#140 | 1 | 6 | 12232780.54 | 0 | -12232780.54 | 10719905.22 | 0 | -10719905.22 |  |  |  | 10719905.2391 | 2019-10-31 | 2019-11-06 | 2019-11-06 | 40 | 2019-12-16 | 2019-12-10 | 32622484.61 | 1084016.3529 | [5 empty] | 318038.6268 | 12232780.5437 | 32622484.6137 | 10719905.2391 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1406 | EMAAR- Pkg 140-ITP-Mivida6
Mivida-PK#140 | 1 | 7 | 7170532.1164 | 12232780.52 | 5062248.4036 | 6547225.82 | 10719905.22 | 4172679.4 |  |  |  | 6547225.8223 | 2019-11-30 | 2019-12-05 | 2019-12-05 | 40 | 2020-01-14 | 2019-12-19 | 39793016.7264 | 1960077.2048 | [5 empty] | 414859.7029 | 7170532.1164 | 39793016.7264 | 6547225.8223 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1407 | EMAAR- Pkg 140-ITP-Mivida7
Mivida-PK#140 | 1 | 8 | 6113446.7536 | 6113446.74 | -0.013553 | 4740517.5525 | 5253107.1475 | 512589.595 |  |  |  | 4740517.5525 | 2019-12-31 | 2020-01-06 | 2020-01-06 | 40 | 2020-02-15 | 2020-02-13 | 45906463.48 | 1612694.6715 | [5 empty] | 473905.3319 | 6113446.7507 | 45906463.4771 | 4740517.5525 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1408 | EMAAR- Pkg 140-ITP-Mivida8
Mivida-PK#140 | 1 | 9 | 4233335.7568 | 4233335.77 | 0.013195 | 4559999.09 | 6237430.1585 | 1677431.0685 |  |  |  | 4559999.0726 | 2020-01-31 | 2020-02-05 | 2020-02-06 | 40 | 2020-03-17 | 2020-03-18 | 50139799.2368 | 3026730.6056 | [5 empty] | 545336.6782 | 4233335.7568 | 50139799.2368 | 4559999.0726 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#1409 | EMAAR- Pkg 140-ITP-Mivida9
Mivida-PK#140 | 1 | 10 | 6612227.7834 | 6612227.79 | 0.0065658 | 5679423.0614 | 5679423.0695 | 0.0081432 |  |  |  | 5679423.0614 | 2020-02-29 | 2020-03-05 | 2020-03-05 | 40 | 2020-04-14 | 2020-04-29 | 56752027.0202 | 3351448.8206 | [5 empty] | 610744.6947 | 6612227.7834 | 56752027.0202 | 5679423.0614 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14010 | EMAAR- Pkg 140-ITP-Mivida10
Mivida-PK#140 | 1 | 11 | 3124627.5928 | 3121472.23 | -3155.3628 | 2647674.17 | 2644790.7215 | -2883.4485 |  |  |  | 2647674.1799 | 2020-03-31 | 2020-04-02 | 2020-04-02 | 40 | 2020-05-12 | 2020-04-29 | 59876654.613 | 3468836.925 | [5 empty] | 649303.9184 | 3124627.5928 | 59876654.613 | 2647674.1799 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14011 | EMAAR- Pkg 140-ITP-Mivida11
Mivida-PK#140 | 1 | 12 | 1875813.048 | 1875812.84 | -0.20801 | 4687303.44 | 4687303.232 | -0.208 |  |  |  | 4687303.4253 | 2020-04-30 | 2020-05-02 | 2020-05-03 | 40 | 2020-06-12 | 2020-05-21 | 61752467.661 | 7497245.0417 | [5 empty] | 703286.0248 | 1875813.048 | 61752467.661 | 4687303.4253 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14012 | EMAAR- Pkg 140-ITP-Mivida12
Mivida-PK#140 | 1 | 13 | 1425866.309 | 1425866.3 | -0.008997 | 1169770.65 | 1169767.915 | -2.735 |  |  |  | 1169770.65 | 2020-05-31 | 2020-06-01 | 2020-06-01 | 40 | 2020-07-11 | 2020-06-21 | 63178333.97 | 7496958.47 | [5 empty] | 52250 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14013 | EMAAR- Pkg 140-ITP-Mivida13
Mivida-PK#140 | 1 | 14 | 2429362.3736 | 2429362.37 | -0.0035546 | 7336701.1 | 7336701.0985 | -0.0015 |  |  |  | 7336701.0997 | 2020-06-30 | 2020-07-01 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-21 | 65607696.3436 | 14334387.2636 | [5 empty] | 52250 | 2429362.3736 | 65607696.3436 | 7336701.0997 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14014 | EMAAR- Pkg 140-ITP-Mivida14
Mivida-PK#140 | 1 | 15 | 16266667.6714 | 16266667.66 | -0.011359 | 10305723.52 | 10902262.273 | 596538.753 |  |  |  | 10305723.5244 | 2020-07-31 | 2020-07-28 | 2020-08-06 | 40 | 2020-09-15 | 2020-08-24 | 81874364.0149 | 10470685.8866 | [5 empty] | 74750 | 16266667.6714 | 81874364.0149 | 10305723.5244 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14015 | EMAAR- Pkg 140-ITP-Mivida15
Mivida-PK#140 | 1 | 16 | 19380294.5984 | 19380294.6 | 0.0016493 | 10553431.24 | 13266917.76 | 2713486.52 |  |  |  | 10553431.2394 | 2020-08-31 | 2020-09-01 | 2020-09-01 | 40 | 2020-10-11 | 2020-09-15 | 101254658.6133 | 3625858.6756 | [5 empty] | 74750 | 19380294.5984 | 101254658.6133 | 10553431.2394 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14016 | EMAAR- Pkg 140-ITP-Mivida16
Mivida-PK#140 | 1 | 17 | 16610857.3328 | 16610857.34 | 0.0072358 | 11726998.43 | 11726998.4315 | 0.0015 |  |  |  | 11726998.4266 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 40 | 2020-11-13 | 2020-10-19 | 117865515.946 | 808207.3196 | [5 empty] | 74750 | 16610857.3328 | 117865515.946 | 11726998.4266 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14017 | EMAAR- Pkg 140-ITP-Mivida17
Mivida-PK#140 | 1 | 18 | 4603925.7609 | 4603925.77 | 0.0090585 | 3831058.93 | 3831058.9285 | -0.0015 |  |  |  | 3831058.93 | 2020-10-31 | 2020-11-04 | 2020-11-09 | 40 | 2020-12-19 | 2020-11-29 | 122469441.707 | 876421.358 | [5 empty] | 74750 | 4603925.7609 | 122469441.707 | 3831058.93 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14018 | EMAAR- Pkg 140-ITP-Mivida18
Mivida-PK#140 | 1 | 19 | 11459315.8636 | 11459315.86 | -0.0036022 | 8885358.62 | 8885358.623 | 0.003 |  |  |  | 8885358.6191 | 2020-11-30 | 2020-12-03 | 2020-12-06 | 40 | 2021-01-15 | 2020-12-21 | 133928757.5706 | 214106.8575 | [5 empty] | 74750 | 11459315.8636 | 133928757.5706 | 8885358.6191 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14019 | EMAAR- Pkg 140-ITP-Mivida19
Mivida-PK#140 | 1 | 20 | 5957491.0722 | 5957491.28 | 0.20777 | 5084359.83 | 6060664.08 | 976304.25 |  |  |  | 5084359.8248 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-04 | 139886248.6428 | 17194.8 | [5 empty] | 85700 | 5957491.0722 | 139886248.6428 | 5084359.8248 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14020 | EMAAR- Pkg 140-ITP-Mivida20
Mivida-PK#140 | 1 | 21 | 9991628.9772 | 9991628.97 | -0.0071991 | 8185193.83 | 8185193.8285 | -0.0015 |  |  |  | 8185193.8344 | 2021-01-31 | 2021-02-04 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-18 | 149877877.62 | [6 empty] | 85700 | 9991628.9775 | 149877877.6203 | 8185193.8344 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14021 | EMAAR- Pkg 140-ITP-Mivida21
Mivida-PK#140 | 1 | 22 | 5467007.07 | 5467007.05 | -0.02 | 4603109.14 | 4603109.1525 | 0.0125 |  |  |  | 4603109.16 | 2021-02-28 | 2021-03-04 | 2021-03-15 | 40 | 2021-04-24 | 2021-04-01 | 155344884.69 | [6 empty] | 85700 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14022 | EMAAR- Pkg 140-ITP-Mivida22
Mivida-PK#140 | 1 | 23 | 4716911.44 | 4716911.47 | 0.03 | 3870461.7 | 3870461.7235 | 0.0235 |  |  |  | 3870461.69 | 2021-03-31 | 2021-04-04 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-26 | 160061796.13 | [6 empty] | 85700 | 1777689.2863 | 157122573.9763 | 1458682.9494 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14023 | EMAAR- Pkg 140-ITP-Mivida23
Mivida-PK#140 | 1 | 24 | 4573435.8657 | 4573435.86 | -0.0057481 | 3732732.7981 | 4604153.83 | 871421.0319 |  |  |  | 3732732.7981 | 2021-05-31 | 2021-06-04 | 2021-06-30 | 40 | 2021-08-09 | 2021-07-15 | 164635231.9957 | [6 empty] | 105700 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14024 | EMAAR- Pkg 140-ITP-Mivida24
Mivida-PK#140 | 1 | 25 | 5220299.9543 | 5220299.96 | 0.0057481 | 9016182.24 | 9290247.798 | 274065.558 |  |  |  | 9016182.24 | 2021-06-30 | 2021-06-29 | 2021-08-18 | 40 | 2021-09-27 | 2021-08-31 | 169855531.95 | [6 empty] | 623487.51 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14025 | EMAAR- Pkg 140-ITP-Mivida25
Mivida-PK#140 | 1 | 26 | 3380977.62 | 3380977.62 | -4.6566e-09 | 3143991.8 | 3321493.111 | 177501.311 |  |  |  | 3143991.79 | 2021-10-31 | 2021-10-31 | 2021-11-02 | 40 | 2021-12-12 | 2021-11-21 | 173236509.57 | [6 empty] | 623487.51 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14026 | EMAAR- Pkg 140-ITP-Mivida26
Mivida-PK#140 | 1 | 27 | 825139.1896 | 825139.18 | -0.0095798 | 5157960.04 | 6499741.709 | 1341781.669 |  |  |  | 5157960.0562 | 2022-01-31 | 2022-01-15 | 2022-01-25 | 40 | 2022-03-06 | 2022-03-01 | 174061648.7596 |  |  |  |  | 4569118.28 | 4569118.28 | 0 | 0 | 0 | 0 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14027 | EMAAR- Pkg 140-ITP-Mivida27
Mivida-PK#140 | 1 | 28 | 924592.0104 | 0 | -924592.0104 | 0 | 0 | 0 |  |  |  | 1576397.44 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 40 | 2023-07-18 | 2024-07-09 | 174986240.77 |  |  |  |  | 4593388.82 | 4593388.82 | 909436.51 | 924591.9704 | 174986240.73 | 1577397.44 | EMAAR- Pkg 140-ITP-Mivida |  |  |  | Mivida-PK#14028 | EMAAR- Pkg 140-ITP-Mivida28
Mivida-PK#189 | 1 | 1 | 15323108.5333 | 0 | -15323108.5333 | 117695262.89 | 0 | -117695262.89 | 99600000 |  |  | 18095262.89 | 2022-05-31 | 2022-05-25 | 2022-05-26 | 40 | 2022-07-05 | 2022-06-16 | 15323108.5333 | 5493727.64 |  |  |  | 559686.37 | 559686.37 | 100000 | 15323108.5333 | 15323108.5333 | 18095262.89 | Mivida BP#189 |  |  |  | Mivida-PK#1891 | Mivida BP#1891
Mivida-PK#189 | 1 | 2 | 28497042.4952 | 16089263.96 | -12407778.5352 | 22529255.88 | 19214635.628 | -3314620.252 |  |  |  | 22529255.8764 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-06 | 43820151.0286 | 5215901.19 |  |  | 1210923 | 1280676.495 | 1280676.495 | 108208.75 | 28497042.4952 | 43820151.0286 | 22529255.8764 | Mivida BP#189 |  |  |  | Mivida-PK#1892 | Mivida BP#1892
Mivida-PK#189 | 1 | 3 | 24279069.6762 | 27730887.07 | 3451817.3938 | 19800407.88 | 23971236.1335 | 4170828.2535 |  |  |  | 19800407.88 | 2022-07-31 | 2022-08-06 | 2022-08-06 | 40 | 2022-09-15 | 2022-09-04 | 68099220.7048 | 5069769.75 |  |  | 4205865.52 | 1914348.785 | 1914348.785 | 115793.25 | 24279069.6762 | 68099220.7048 | 19800407.88 | Mivida BP#189 |  |  |  | Mivida-PK#1893 | Mivida BP#1893
Mivida-PK#189 | 1 | 4 | 28546026.8476 | 24279069.68 | -4266957.1676 | 27644756.83 | 21067752.4505 | -6577004.3795 |  |  |  | 27644756.83 | 2022-08-31 | 2022-09-05 | 2022-09-06 | 40 | 2022-10-16 | 2022-10-09 | 96645247.5524 | 10542311 |  |  | 4205865.52 | 2800495.535 | 2800495.535 | 171139 | 28546026.8476 | 96645247.5524 | 27644756.83 | Mivida BP#189 |  |  |  | Mivida-PK#1894 | Mivida BP#1894
Mivida-PK#189 | 1 | 5 | 57245166.7876 | 28546026.85 | -28699139.9376 | 46638711.45 | 29417050.3325 | -17221661.1175 |  |  |  | 46638711.45 | 2022-09-30 | 2022-10-12 | 2022-10-12 | 40 | 2022-11-21 | 2022-11-05 | 153890414.34 | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759 | 57245166.7876 | 153890414.34 | 46638711.45 | Mivida BP#189 |  |  |  | Mivida-PK#1895 | Mivida BP#1895
Mivida-PK#189 | 1 | 6 | -0.0001 | 57254690.6 | 57254690.6001 | 70000000 | 49630186.51 | -20369813.49 |  |  |  | 70000000 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | 153890414.34 | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759 | -0.0001 | 153890414.34 | 70000000 | Mivida BP#189 |  |  |  | Mivida-PK#1896 | Mivida BP#1896
Mivida-PK#189 | 1 | 7 | 39773865.3076 | 49447555.48 | 9673690.1724 | 38664242.89 | 41131640.064 | 2467397.174 |  |  |  | 38664242.9 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | 193664279.6476 | 7682397 |  |  | 14543436.55 | 5529931.65 | 5529931.65 | 187759 | 39773865.3076 | 193664279.6476 | 38664242.9 | Mivida BP#189 |  |  |  | Mivida-PK#1897 | Mivida BP#1897
Mivida-PK#189 | 1 | 8 | 90047890.8024 | 80364676.81 | -9683213.9924 | 62566272.8 | 66596247.2075 | 4029974.4075 |  |  |  | 62566272.81 | 2022-11-30 | 2022-12-12 | 2022-12-14 | 40 | 2023-01-23 | 2023-01-01 | 283712170.45 | 3898975.5 |  |  | 19923003.68 | 7544918.86 | 7544918.86 | 608067.35 | 90047890.8024 | 283712170.45 | 62566272.81 | Mivida BP#189 |  |  |  | Mivida-PK#1898 | Mivida BP#1898
Mivida-PK#189 | 1 | 9 | 42271935.09 | 42271935.1 | 0.01 | 37089198 | 39465389.045 | 2376191.045 |  |  |  | 37089197.56 | 2022-12-31 | 2023-01-05 | 2023-01-09 | 40 | 2023-02-18 | 2023-01-24 | 325984105.54 | 7037273.25 |  |  | 24970230.92 | 8733014.6 | 8733014.6 | 657611 | 42271935.09 | 325984105.54 | 37089197.56 | Mivida BP#189 |  |  |  | Mivida-PK#1899 | Mivida BP#1899
Mivida-PK#189 | 1 | 10 | 29038558.46 | 29038558.46 | 0 | 22123110.41 | 23647399.753 | 1524289.343 |  |  |  | 22123110.41 | 2023-01-31 | 2023-02-01 | 2023-02-01 | 40 | 2023-03-13 | 2023-02-26 | 355022664 | 7032573.83 |  | 285000 | 27238935.45 | 9495159.275 | 9495159.275 | 573417.35 | 29038558.46 | 355022664 | 22123110.41 | Mivida BP#189 |  |  |  | Mivida-PK#18910 | Mivida BP#18910
Mivida-PK#189 | 1 | 11 | 23000800.56 | 23000800.56 | 0 | 18794302.39 | 19983996.088 | 1189693.698 |  |  |  | 18794302.38 | 2023-02-28 | 2023-03-01 | 2023-03-08 | 40 | 2023-04-17 | 2023-04-10 | 378023464.56 | 6675607.4 |  | 55000 | 34635720.71 | 10090006.13 | 10090006.13 | 603461 | 23000800.56 | 378023464.56 | 18794302.38 | Mivida BP#189 |  |  |  | Mivida-PK#18911 | Mivida BP#18911
Mivida-PK#189 | 1 | 12 | 15682494.86 | 15682494.86 | 5.0291e-08 | 16890748.06 | 17976827.49 | 1086079.43 |  |  |  | 16890748.07 | 2023-03-31 | 2023-04-01 | 2023-04-09 | 40 | 2023-05-19 | 2023-05-08 | 393705959.42 | 11930576.4 |  | 90000 | 36499853.4 | 10633045.845 | 10633045.845 | 652617.35 | 15682494.86 | 393705959.42 | 16890748.07 | Mivida BP#189 |  |  |  | Mivida-PK#18912 | Mivida BP#18912
Mivida-PK#189 | 1 | 13 | 16636045.76 | 16636045.76 | -5.0291e-08 | 50032149.11 | 53623446.998 | 3591297.888 |  |  |  | 50032149.1 | 2023-04-30 | 2023-05-05 | 2023-05-09 | 40 | 2023-06-18 | 2023-06-06 | 410342005.18 | 58593047.95 | 1714555.5 | 140000 | 38456764.67 | 12236303.835 | 12236303.835 | 686786.1 | 16636045.76 | 410342005.18 | 50032149.1 | Mivida BP#189 |  |  |  | Mivida-PK#18913 | Mivida BP#18913
Mivida-PK#189 | 1 | 14 | 22729528.92 | 22729528.92 | 0 | 22045664.4 | 23637153.386 | 1591488.986 |  |  |  | 22045664.4 | 2023-05-31 | 2023-06-05 | 2023-06-05 | 40 | 2023-07-15 | 2023-07-15 | 433071534.1 | 63146488.9 | 3995594.72 | 240000 | 42393533.94 | 12946789.995 | 12946789.995 | 750242.35 | 22729528.92 | 433071534.1 | 22045664.4 | Mivida BP#189 |  |  |  | Mivida-PK#18914 | Mivida BP#18914
Mivida-PK#189 | 1 | 15 | 18379426.49 | 18379426.48 | -0.0099999 | 20013901.02 | 20013901.014 | -0.006 |  |  |  | 20013901.03 | 2023-06-30 | 2023-07-13 | 2023-07-18 | 40 | 2023-08-27 | 2023-08-07 | 451450960.59 | 71534780.44 | 7645358.03 | 330000 | 45605336.83 | 13638957.225 | 13638957.225 | 782829.85 | 18379426.49 | 451450960.59 | 20013901.03 | Mivida BP#189 |  |  |  | Mivida-PK#18915 | Mivida BP#18915
Mivida-PK#189 | 1 | 16 | 24459783.7762 | 24459783.78 | 0.003758 | 22512171.88 | 22512171.879 | -0.001 |  |  |  | 22512171.8728 | 2023-07-31 | 2023-08-15 | 2023-08-17 | 40 | 2023-09-26 | 2023-09-20 | 475910744.3662 | 78434225.1876 | 8773118.9707 | 230000 | 50069955.0917 | 14453512.665 | 14453512.665 | 832885.35 | 24459783.7762 | 475910744.3662 | 22512171.8728 | Mivida BP#189 |  |  |  | Mivida-PK#18916 | Mivida BP#18916
Mivida-PK#189 | 1 | 17 | 30434807.7338 | 30434807.73 | -0.003758 | 47104890.0563 | 47104890.0565 | 0.00022 |  |  |  | 47104890.06 | 2023-09-30 | 2023-09-25 | 2023-09-27 | 40 | 2023-11-06 | 2023-10-17 | 506345552.1 | 73723080.15 | 9982715.55 | 390000 | 53354142.27 | 15134647.745 | 15134647.745 | 859629.1 | 30434807.7338 | 506345552.1 | 47104890.06 | Mivida BP#189 |  |  |  | Mivida-PK#18917 | Mivida BP#18917
Mivida-PK#189 | 1 | 18 | 18563752.6 | 37127505.2 | 18563752.6 | 20024965.62 | 20024965.62 | 0 |  |  |  | 20024965.62 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 40 | 2023-12-10 | 2023-12-02 | 524909304.7 | 79805243.6 | 11738051.38 | 340000 | 54783582.6 | 15774000.34 | 15774000.34 | 870216.6 | 18563752.6 | 524909304.7 | 20024965.62 | Mivida BP#189 |  |  |  | Mivida-PK#18918 | Mivida BP#18918
Mivida-PK#189 | 1 | 19 | 21710553.3095 | 21710553.31 | 0.0004763 | 23323710.11 | 23323710.1055 | -0.0045 |  |  |  | 23323710.1 | 2023-11-30 | 2023-11-25 | 2023-12-02 | 40 | 2024-01-11 | 2024-01-02 | 546619858.0095 | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1 | 21710553.3095 | 546619858.0095 | 23323710.1 | Mivida BP#189 |  |  |  | Mivida-PK#18919 | Mivida BP#18919
Mivida-PK#189 | 1 | 20 | -0.0003 | 0 | 0.0003 | 135145955 | 0 | -135145955 |  | 135145955 |  |  | 2023-11-30 | 2023-11-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-11 | 546619858.0095 | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1 | -0.0003 | 546619858.0095 | 0 | Mivida BP#189 |  |  |  | Mivida-PK#18920 | Mivida BP#18920
Mivida-PK#189 | 1 | 21 | 22586754.7048 | 22586754.17 | -0.53476 | 14476604.63 | 14476604.0585 | -0.5715 |  |  |  | 14476604.63 | 2023-12-31 | 2023-12-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-24 | 569206612.7143 | 81314246.26 | 16546391.27 | 130000 | 59318989.42 | 16974529.74 | 16974529.74 | 807307.6 | 22586754.7048 | 569206612.7143 | 14476604.63 | Mivida BP#189 |  |  |  | Mivida-PK#18921 | Mivida BP#18921
Mivida-PK#189 | 1 | 22 | 23140993.5357 | 23140993.33 | -0.20571 | 17552608.99 | 17552608.8365 | -0.1535 |  |  |  | 17552609 | 2024-01-31 | 2024-01-30 | 2024-02-04 | 40 | 2024-03-15 | 2024-02-27 | 592347606.25 | 88194427.7 | 17630743.31 | 130000 | 61582414.39 | 17753985.355 | 17753985.355 | 900122.85 | 23140993.5357 | 592347606.25 | 17552609 | Mivida BP#189 |  |  |  | Mivida-PK#18922 | Mivida BP#18922
Mivida-PK#189 | 1 | 23 | 30858954.27 | 30858954.29 | 0.02 | 14242173.09 | 14242173.0845 | -0.0055 |  |  |  | 14242173.08 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 40 | 2024-04-15 | 2024-04-21 | 623206560.52 | 84128553.28 | 31879195.04 | 260000 | 64992287.15 | 18462386.045 | 18462386.045 | 912222.85 | 30858954.27 | 623206560.52 | 14242173.08 | Mivida BP#189 |  |  |  | Mivida-PK#18923 | Mivida BP#18923
Mivida-PK#189 | 1 | 24 | 16112816.1181 | 16112816.1 | -0.018095 | 13803484.92 | 13803484.915 | -0.005 |  |  |  | 13803484.93 | 2024-03-31 | 2024-03-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-05-22 | 639319376.6381 | 96423729.78 | 32655160.1 | 130000 | 66746916.67 | 19192726.88 | 19192726.88 | 1304406.85 | 16112816.1181 | 639319376.6381 | 13803484.93 | Mivida BP#189 |  |  |  | Mivida-PK#18924 | Mivida BP#18924
Mivida-PK#189 | 1 | 25 | 29437278.3119 | 29437278.32 | 0.0080952 | 28360739.45 | 28360739.446 | -0.004 |  |  |  | 28360739.45 | 2024-04-30 | 2024-04-30 | 2024-05-09 | 40 | 2024-06-18 | 2024-06-06 | 668756654.95 | 101680151.25 | 44526060.5 | 30000 | 69988148.31 | 20096865.975 | 20096865.975 | 1306194.35 | 29437278.3119 | 668756654.95 | 28360739.45 | Mivida BP#189 |  |  |  | Mivida-PK#18925 | Mivida BP#18925
Mivida-PK#189 | 1 | 26 | 16876594.42 | 16876594.44 | 0.02 | 14177811.26 | 14177811.26 | 0 |  |  |  | 14177811.24 | 2024-05-31 | 2024-05-30 | 2024-06-01 | 40 | 2024-07-11 | 2024-07-03 | 685633249.37 | 113839940.35 | 49627280.83 | 230000 | 71860776.18 | 20843871.305 | 20843871.305 | 1314994.35 | 16876594.42 | 685633249.37 | 14177811.24 | Mivida BP#189 |  |  |  | Mivida-PK#18926 | Mivida BP#18926
Mivida-PK#189 | 1 | 27 | 14919836.13 | 14919836.12 | -0.01 | 4389859.04 | 4389859.036 | -0.004 |  |  |  | 4389859.04 | 2024-06-30 | 2024-06-30 | 2024-07-01 | 40 | 2024-08-10 | 2024-08-01 | 700553085.5 | 115715406.16 | 55352768.73 | 130000 | 73509397.76 | 21282403.65 | 21282403.65 | 5470850.6 | 14919836.13 | 700553085.5 | 4389859.04 | Mivida BP#189 |  |  |  | Mivida-PK#18927 | Mivida BP#18927
Mivida-PK#189 | 1 | 28 | 3487392.66 | 3487392.64 | -0.02 | 2409288.21 | 2409288.192 | -0.018 |  |  |  | 2409288.21 | 2024-07-31 | 2024-07-30 | 2024-08-01 | 40 | 2024-09-10 | 2024-08-31 | 704040478.16 | 115148780.66 | 49698695.44 | 130000 | 73901796.57 | 21359782.07 | 21359782.07 | 5480338.1 | 3487392.66 | 704040478.16 | 2409288.21 | Mivida BP#189 |  |  |  | Mivida-PK#18928 | Mivida BP#18928
Mivida-PK#189 | 1 | 29 | 369049.79 | 369049.79 | 3.8068e-08 | 2690517.47 | 2690517.4595 | -0.0105 |  |  |  | 2690517.47 | 2024-08-31 | 2024-08-31 | 2024-09-18 | 40 | 2024-10-28 | 2024-09-26 | 704409527.95 | 118334746.14 | 36219473.08 | 230000 | 73927905.13 | 21449118.76 | 21449118.76 | 5482400 | 369049.79 | 704409527.95 | 2690517.47 | Mivida BP#189 |  |  |  | Mivida-PK#18929 | Mivida BP#18929
Mivida-PK#189 | 1 | 30 | 17653522.66 | 22415427.41 | 4761904.75 | 14412191.12 | 14412191.1105 | -0.0095 |  |  |  | 14412191.13 | 2024-09-30 | 2024-09-30 | 2024-10-09 | 40 | 2024-11-18 | 2024-11-12 | 722063050.61 | 118972314.89 | 37380637.32 | 230000 | 80926432.97 | 22053462.95 | 22053462.95 | 9961433.24 | 17653522.66 | 722063050.61 | 14412191.13 | Mivida BP#189 |  |  |  | Mivida-PK#18930 | Mivida BP#18930
Mivida-PK#189 | 1 | 31 |  | 19514716.97 | 19514716.97 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-11-01 | 40 | 2024-12-11 | [8 empty] | 0 | 0 | 0 | 0 | Mivida BP#189 |  |  |  | Mivida-PK#18931 | Mivida BP#18931
Mobilization | 0 | 1 | 3847983.19 | 0 | -3847983.19 | 0 | 0 | 0 |  |  |  | 475188.5 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-02-28 | 3847983.19 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Mobilization1 | 01
MOC | 1 | 1 |  | 32863813 | 32863813 | 33350000 | 0 | -33350000 |  |  |  |  | 2024-05-31 | 2024-06-08 | 2024-05-05 | 40 | 2024-06-14 | [8 empty] | 0 | 0 | 0 | 0 | MOC HQ at Diriyah |  |  |  | MOC1 | MOC HQ at Diriyah1
MOC | 1 | 2 |  | 2521761.64 | 2521761.64 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-07-15 | 2024-07-15 | 40 | 2024-08-24 | [8 empty] | 0 | 0 | 0 | 0 | MOC HQ at Diriyah |  |  |  | MOC2 | MOC HQ at Diriyah2
MOC - DP | 1 | 1 |  | 32863813 | 32863813 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-01 | 2024-04-01 | 40 | 2024-05-11 | [8 empty] | 0 | 0 | 0 | 0 | MOC HQ at Diriyah |  |  |  | MOC - DP1 | MOC HQ at Diriyah1
New Gas Station | 1 | 1 | 3190160 | 34312846.59 | 31122686.59 | 2201210.4 | 24876813.7695 | 22675603.3695 |  |  |  | 2360718.4 | 2023-10-31 | 2023-10-31 | 2023-11-02 | 42 | 2023-12-14 | 2023-11-02 | 3190160 | [6 empty] | 0 | 3190160 | 3190160 | 2360718.4 | New Giza Teaching Hospital |  |  |  | New Gas Station1 | New Giza Teaching Hospital1
New Gas Station | 1 | 2 |  | 20687718.13 | 20687718.13 | 1419355.25 | 14998595.6465 | 13579240.3965 |  |  |  |  | 2023-12-31 | 2023-12-31 | 2024-01-01 | 42 | 2024-02-12 | [8 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Gas Station2 | New Giza Teaching Hospital2
New Gas Station | 1 | 3 | 2793703.2 | 7560552.29 | 4766849.09 | 0 | 7466045.3845 | 7466045.3845 |  |  |  | 1433129.44 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 42 | 2024-03-14 | 2024-02-07 | 7183858 | [6 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Gas Station3 | New Giza Teaching Hospital3
New Gas Station | 1 | 4 | 6707619.99 | 36077726.42 | 29370106.43 | 0 | 27335611.781 | 27335611.781 |  |  |  | 4963638.79 | 2024-04-30 | 2024-04-21 | 2024-04-21 | 42 | 2024-06-02 | 2024-04-28 | 13891477.99 | [6 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Gas Station4 | New Giza Teaching Hospital4
#N/A
New Giza Hospital | 1 | 1 | 34312846.6 | 34312846.59 | -0.01 | 111673736 | 24876813.7695 | -86796922.2305 | 73512565 |  |  | 23504299.92 | 2022-01-31 | 2022-01-30 | 2022-02-01 | 51 | 2022-03-24 | 2022-02-14 | 34312846.6 | [6 empty] | 0 | 34312846.6 | 34312846.6 | 23504299.92 | New Giza Teaching Hospital |  |  |  | New Giza Hospital1 | New Giza Teaching Hospital1
New Giza Hospital | 1 | 2 | 20701192.62 | 20687718.13 | -13474.49 | 16948027.1724 | 14998595.6465 | -1949431.5259 |  |  |  | 13966904.63 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 51 | 2022-04-25 | 2022-03-21 | 55014039.22 | [6 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital2 | New Giza Teaching Hospital2
New Giza Hospital | 1 | 3 | -0.0001 | 7560552.29 | 7560552.2901 | 7088017 | 7466045.3845 | 378028.3845 |  |  |  | 7088017.77 | 2022-03-31 | 2022-03-15 | 2022-03-20 | 51 | 2022-05-10 | 2022-03-28 | 55014039.22 |  |  |  |  | 1642229.32 | 1642229.32 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital3 | New Giza Teaching Hospital3
New Giza Hospital | 1 | 4 | 43472048.71 | 36077726.42 | -7394322.29 | 25531752 | 27335611.781 | 1803859.781 |  |  |  | 25608972.36 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 51 | 2022-05-27 | 2022-04-24 | 98486087.93 |  |  |  |  | 2584225.375 | 2584225.375 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital4 | New Giza Teaching Hospital4
New Giza Hospital | 1 | 5 | 15040366.17 | 14819091.38 | -221274.79 | 9692684 | 10433639.459 | 740955.459 |  |  |  | 10219240.4 | 2022-04-30 | 2022-05-10 | 2022-05-10 | 51 | 2022-06-30 | 2022-05-25 | 113526454.1 |  |  |  | 12821619 | 2978829.635 | 2978829.635 | 447088.63 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital5 | New Giza Teaching Hospital5
New Giza Hospital | 1 | 6 | 21219859 | 21174583.68 | -45275.32 | 12645886 | 13704613.324 | 1058727.324 |  |  |  | 14292844 | 2022-05-31 | 2022-05-31 | 2022-06-15 | 51 | 2022-08-05 | 2022-06-21 | 134746313.1 |  |  |  | 12821619 | 3534103.595 | 3534103.595 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital6 | New Giza Teaching Hospital6
New Giza Hospital | 1 | 7 | 20073764.28 | 20034184.42 | -39579.86 | 12694720 | 13696429.151 | 1001709.151 |  |  |  | 13315074.93 | 2022-06-30 | 2022-06-30 | 2022-06-23 | 51 | 2022-08-13 | 2022-07-04 | 154820077.38 |  |  |  | 12821619.84 | 4060000.94 | 4060000.94 | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital7 | New Giza Teaching Hospital7
New Giza Hospital | 1 | 8 | 18180164.07 | 18146654.72 | -33509.35 | 11865059 | 12772392.376 | 907333.376 |  |  |  | 12573205.03 | 2022-07-31 | 2022-08-07 | 2022-08-23 | 51 | 2022-10-13 | 2022-08-28 | 173000241.45 |  |  |  | 12821619 | 4536350.625 | 4536350.625 | 2987283.85 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital8 | New Giza Teaching Hospital8
New Giza Hospital | 1 | 9 | 23318711.12 | 23282485.08 | -36226.04 | 15594713 | 16758838.084 | 1164125.084 |  |  |  | 15620677.42 | 2022-08-31 | 2022-09-11 | 2022-09-14 | 51 | 2022-11-04 | 2022-09-22 | 196318952.57 |  |  |  | 12821619.84 | 5147515.86 | 5147515.86 | 3790429.25 | 23318711.12 | 196318952.57 | 15620677.42 | New Giza Teaching Hospital |  |  |  | New Giza Hospital9 | New Giza Teaching Hospital9
New Giza Hospital | 1 | 10 | 22254898.64 | 22234302.84 | -20595.8 | 14931468 | 16043183.482 | 1111715.482 |  |  |  | 14944068.34 | 2022-09-30 | 2022-10-15 | 2022-10-18 | 51 | 2022-12-08 | 2022-11-03 | 218573851.21 |  |  |  | 12821619.84 | 5731166.305 | 5731166.305 | 3910342.85 | 22254898.64 | 218573851.21 | 14944068.34 | New Giza Teaching Hospital |  |  |  | New Giza Hospital10 | New Giza Teaching Hospital10
New Giza Hospital | 1 | 11 | 29701638.2 | 29644027.2 | -57611 | 19979218 | 21461419.72 | 1482201.72 |  |  |  | 19999087.83 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 51 | 2022-12-31 | 2022-12-07 | 248275489.41 |  | 47447.2 |  | 12821619.84 | 6509322.02 | 6509322.02 | 3819797.85 | 29701638.2 | 248275489.41 | 19999087.83 | New Giza Teaching Hospital |  |  |  | New Giza Hospital11 | New Giza Teaching Hospital11
New Giza Hospital | 1 | 12 | 25988546.64 | 30417445.78 | 4428899.14 | 21023839 | 22544712.249 | 1520873.249 |  |  |  | 21046664.64 | 2022-11-30 | 2022-12-06 | 2022-12-08 | 51 | 2023-01-28 | 2022-12-29 | 274264036.05 | 4878335.3 | 1113844.57 |  | 12821619.84 | 7307779.5 | 7307779.5 | 3966447.85 | 25988546.64 | 274264036.05 | 21046664.64 | New Giza Teaching Hospital |  |  |  | New Giza Hospital12 | New Giza Teaching Hospital12
New Giza Hospital | 1 | 13 | 24670486.27 | 26683802.78 | 2013316.51 | 17903308 | 19237495.901 | 1334187.901 |  |  |  | 18169651.25 | 2022-12-31 | 2023-01-05 | 2023-01-08 | 51 | 2023-02-28 | 2023-02-06 | 298934522.32 | 7074573 | 1237105.25 |  | 12821619.84 | 8008229.795 | 8008229.795 | 3886497.85 | 24670486.27 | 298934522.32 | 18169651.25 | New Giza Teaching Hospital |  |  |  | New Giza Hospital13 | New Giza Teaching Hospital13
New Giza Hospital | 1 | 14 | 21692266.85 | 21572565.8 | -119701.05 | 15197022 | 16275653.05 | 1078631.05 |  |  |  | 14731551.62 | 2023-01-31 | 2023-02-11 | 2023-02-09 | 51 | 2023-04-01 | 2023-03-14 | 320626789.17 | 6879606.09 | 1773014.33 |  | 12821619.84 | 8574509.66 | 8574509.66 | 4107797.85 | 21692266.85 | 320626789.17 | 14731551.62 | New Giza Teaching Hospital |  |  |  | New Giza Hospital14 | New Giza Teaching Hospital14
New Giza Hospital | 1 | 15 | 23725978.81 | 22076508.27 | -1649470.54 | 7535461 | 8639287.3435 | 1103826.3435 |  |  |  | 14839693.08 | 2023-02-28 | 2023-03-14 | 2023-03-16 | 51 | 2023-05-06 | 2023-04-18 | 344352767.98 | 5193267.92 | 2584321.32 |  | 12821619.84 | 9154018.005 | 9154018.005 | 4143497.85 | 23725978.81 | 344352767.98 | 14839693.08 | New Giza Teaching Hospital |  |  |  | New Giza Hospital15 | New Giza Teaching Hospital15
New Giza Hospital | 1 | 16 | 22492246.1 | 22109235.45 | -383010.65 | 7643976 | 8749433.6065 | 1105457.6065 |  |  |  | 15222233.72 | 2023-04-30 | 2023-04-19 | 2023-04-30 | 51 | 2023-06-20 | 2023-05-14 | 366845014.08 | 4834698.32 | 3206608.76 |  | 12821619.84 | 9734385.435 | 9734385.435 | 3938997.85 | 22492246.1 | 366845014.08 | 15222233.72 | New Giza Teaching Hospital |  |  |  | New Giza Hospital16 | New Giza Teaching Hospital16
New Giza Hospital | 1 | 17 | 21612019.52 | 21552600.91 | -59418.61 | 0 | 1077630.05 | 1077630.05 |  |  |  | 12680990.84 | 2023-05-31 | 2023-05-31 | 2023-06-03 | 51 | 2023-07-24 | 2023-07-04 | 388457033.6 | 4817538.46 | 3364840.52 |  | 12821619.84 | 10300141.21 | 10300141.21 | 6117327.71 | 21612019.52 | 388457033.6 | 12680990.84 | New Giza Teaching Hospital |  |  |  | New Giza Hospital17 | New Giza Teaching Hospital17
New Giza Hospital | 1 | 18 | 9332664.78 | 24967998.04 | 15635333.26 | 14511461 | 15759862.1875 | 1248401.1875 |  |  |  | 14934202.65 | 2023-06-30 | 2023-07-09 | 2023-07-12 | 51 | 2023-09-01 | 2023-08-06 | 397789698.38 | 21298296.55 | 3366900.3 |  | 12821619.84 | 10955551.155 | 10955551.155 | 6117327.71 | 9332664.78 | 397789698.38 | 14934202.65 | New Giza Teaching Hospital |  |  |  | New Giza Hospital18 | New Giza Teaching Hospital18
New Giza Hospital | 1 | 19 | 18985757.51 | 8254281.5 | -10731476.01 | 3705542 | 4118256.08 | 412714.08 |  |  |  | 5705542.36 | 2023-08-31 | 2023-08-12 | 2023-08-13 | 51 | 2023-10-03 | 2023-09-14 | 416775455.89 | 10041623.17 | 3890054.47 |  | 12821619.84 | 11172226.045 | 11172226.045 | 6117327.71 | 18985757.51 | 416775455.89 | 5705542.36 | New Giza Teaching Hospital |  |  |  | New Giza Hospital19 | New Giza Teaching Hospital19
New Giza Hospital | 1 | 20 | -1e-07 | 0 | 1e-07 | 18995740 | 0 | -18995740 |  |  |  | 18995740.42 | 2023-09-30 | 2023-09-30 | 2023-09-27 | 51 | 2023-11-17 | 2023-10-03 | 416775455.89 | 10041623.17 | 3890054.47 |  | 12821619.84 | 22344452.09 |  | 6117327.71 | -1e-07 | 416775455.89 | 18995740.42 | New Giza Teaching Hospital |  |  |  | New Giza Hospital20 | New Giza Teaching Hospital20
New Giza Hospital | 1 | 21 | 12758386.3 | 12130160.82 | -628225.48 | 4008305 | 4614812.92 | 606507.92 |  |  |  | 8010369.24 | 2023-09-30 | 2023-09-30 | 2023-10-16 | 51 | 2023-12-06 | 2023-10-16 | 429533842.19 | 9402295.53 | 3259999.96 |  | 12821619 | 22981285.53 |  | 6117327.71 | 12758386.3 | 429533842.19 | 8010369.24 | New Giza Teaching Hospital |  |  |  | New Giza Hospital21 | New Giza Teaching Hospital21
New Giza Hospital | 1 | 22 | 18598623.84 | 12179338.16 | -6419285.68 | 6681249 | 7290216.108 | 608967.108 |  |  |  | 8695249.6 | 2023-10-31 | 2023-11-05 | 2023-11-08 | 51 | 2023-12-29 | 2023-11-30 | 448132466.03 | 2678290.23 | 4983458.07 |  | 12821619.84 | 23620700.79 |  | 6119391.71 | 18598623.84 | 448132466.03 | 8695249.6 | New Giza Teaching Hospital |  |  |  | New Giza Hospital22 | New Giza Teaching Hospital22
New Giza Hospital | 1 | 23 | 9056705.71 | 8466924.1 | -589781.61 | 3104562 | 3527907.892 | 423345.892 |  |  |  | 4604562.68 | 2023-11-30 | 2023-12-10 | 2023-12-12 | 51 | 2024-02-01 | 2024-01-27 | 457189171.74 | 2083276.16 | 4983458.07 |  | 12821619.84 | 24065214.3 |  | 6133391.71 | 9056705.71 | 457189171.74 | 4604562.68 | New Giza Teaching Hospital |  |  |  | New Giza Hospital23 | New Giza Teaching Hospital23
New Giza Hospital | 1 | 24 | 30645299.93 | 29604524.13 | -1040775.8 | 4494905.88 | 4494905.8665 | -0.0135 |  |  |  | 5494905.78 | 2024-01-31 | 2024-02-12 | 2024-02-13 | 51 | 2024-04-04 | 2024-04-01 | 487834471.67 | 1034048.23 | 5018947.83 |  | 12821619.84 | 25619451 |  | 8956130 | 30645299.93 | 487834471.67 | 5494905.78 | New Giza Teaching Hospital |  |  |  | New Giza Hospital24 | New Giza Teaching Hospital24
New Giza Hospital | 1 | 25 | 12955562.12 | 12359506.46 | -596055.66 | 10195246 | 10195246.193 | 0.193 |  |  |  | 10195246.28 | 2024-03-31 | 2024-04-06 | 2024-04-07 | 51 | 2024-05-28 | 2024-01-05 | 500790033.79 | 421352.25 | 12168583.45 |  | 12821619.84 | 26268325.91 |  | 8956130.8 | 12955562.12 | 500790033.79 | 10195246.28 | New Giza Teaching Hospital |  |  |  | New Giza Hospital25 | New Giza Teaching Hospital25
New Giza Hospital | 1 | 26 | 15191903.43 | 68532450.22 | 53340546.79 | 18129119.1724 | 16494091.451 | -1635027.7214 |  |  |  | 17232986.3 | 2024-04-30 | 2024-05-12 | 2024-05-29 | 51 | 2024-07-19 | 2024-06-13 | 515981937.22 | 268661.25 | 14260202.71 |  |  | 27057529.55 |  | 23641604 | 15191903.43 | 515981937.22 | 17232986.3 | New Giza Teaching Hospital |  |  |  | New Giza Hospital26 | New Giza Teaching Hospital26
New Giza Hospital | 1 | 27 | 16227230.2 | 16173467.3 | -53762.9 | 2051894 | 3376911.615 | 1325017.615 |  |  |  | 13715277.6 | 2024-06-30 | 2024-07-14 | 2024-07-16 | 51 | 2024-09-05 | 2024-08-18 | 532209167.42 | 268661.25 | 14260202 |  | 56175000 | 30715749 |  | 20879747 | 16227230.2 | 532209167.42 | 13715277.6 | New Giza Teaching Hospital |  |  |  | New Giza Hospital27 | New Giza Teaching Hospital27
New Giza Hospital | 1 | 28 | 69437921.36 | 12973500.18 | -56464421.18 | 5534314 | 5534314 | 0 |  |  |  | 6800969.24 | 2024-08-31 | 2024-09-11 | 2024-09-12 | 51 | 2024-11-02 | 2024-10-03 | 601647088.78 | 268661 | 18531949 |  | 56175000 | 15698247.5 | 15698247.5 | 9038450 | 69437921.36 | 601647088.78 | 6800969.24 | New Giza Teaching Hospital |  |  |  | New Giza Hospital28 | New Giza Teaching Hospital28
New Giza Hospital | 1 | 29 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-17 | 2024-10-19 | 51 | 2024-12-09 | [8 empty] | 0 | 0 | 0 | 0 | New Giza Teaching Hospital |  |  |  | New Giza Hospital29 | New Giza Teaching Hospital29
NGU 2 | 1 | 25 | 3430150 | 0 | -3430150 | 2468493.7 | 0 | -2468493.7 |  |  |  |  | 2017-09-30 | 2017-10-01 | 2017-09-16 | 28 | 2017-10-14 | 2017-10-11 | 140490291 | 1675290.17 | [5 empty] | 807366.8348 | 0 | 0 | 0 | New Giza 2 |  |  |  | NGU 225 | New Giza 225
NGU 2 | 1 | 26 | 10391625.25 | 6396673.25 | -3994952 | 4990186 | 4990687.1405 | 501.1405 |  |  |  | 6719251.6 | 2017-11-30 | 2017-11-30 | 2018-01-23 | 28 | 2018-02-20 | 2018-05-23 | 150881916.25 | 0 | [5 empty] | 699355.4648 | 6579666.5395 | 147069957.5395 | 3027155.9789 | New Giza 2 |  |  |  | NGU 226 | New Giza 226
NGU 2 | 1 | 27 | 3035230.3681 | 6000000 | 2964769.6319 | 2104161 | 6000000 | 3895839 |  |  |  | 1589855.1267 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 28 | 2019-08-01 | 2019-11-02 | 153917146.6181 | 734008.68 | [5 empty] | 0 | 0 | 0 | 2440072.7285 | New Giza 2 |  |  |  | NGU 227 | New Giza 227
#N/A
ORA - ZED | 1 | 1 | 2407390.5714 | 2407390.57 | -0.0014286 | 101168059.79 | 10377230.16 | -90790829.63 |  |  |  | 10345156.8 | 2020-11-30 | 2020-11-25 | 2020-11-22 | 56 | 2021-01-17 | 2021-01-17 | 2407390.5714 | 9271107.2 | [5 empty] | 0 | 2407390.5714 | 2407390.5714 | 10345156.8 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED1 | ORA ZED - Ph 01B - Pkgs A&D1
ORA - ZED | 1 | 2 | 45205427.0762 | 45205416.45 | -10.6262 | 293983829 | 39936351.7025 | -254047477.2975 |  | 256451321 |  | 37532508 | 2020-12-31 | 2020-12-31 | 2020-12-22 | 56 | 2021-02-16 | 2021-01-06 | 47612817.6476 | 9882492.63 | [5 empty] | 10718.8648 | 43865060.0886 | 46272450.66 | 37827388.6601 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED2 | ORA ZED - Ph 01B - Pkgs A&D2
ORA - ZED | 1 | 3 | 26768107.4476 | 26768118.08 | 10.6324 | 78068925.863 | 29651159.334 | -48417766.529 |  | 50172571.863 |  | 27896354 | 2021-01-31 | 2021-02-03 | 2021-01-31 | 56 | 2021-03-28 | 2021-02-17 | 74380925.0952 | 17071953.36 | [5 empty] | 24994.28 | 23073312.5238 | 70686130.1714 | 28404325.826 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED3 | ORA ZED - Ph 01B - Pkgs A&D3
ORA - ZED | 1 | 4 | 26593168.5429 | 26593168.54 | -0.0028571 | 45888247.393 | 26411905.937 | -19476341.456 |  | 25000000 |  | 20888247.393 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 56 | 2021-05-02 | 2021-03-24 | 100974093.6381 | 20604136.5 | [5 empty] | 50275.41 | 21833038.3714 | 96213963.4667 | 21185755.528 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED4 | ORA ZED - Ph 01B - Pkgs A&D4
ORA - ZED | 1 | 5 | 39594206.7048 | 41442903.7 | 1848696.9952 | 83744386.154 | 33310478.505 | -50433907.649 |  | 50000000 |  | 33744386.154 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 56 | 2021-06-01 | 2021-05-11 | 140568300.3429 | 16740725.26 | [5 empty] | 66054.2648 | 41442903.7055 | 142416997.3436 | 35278804.6637 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED5 | ORA ZED - Ph 01B - Pkgs A&D5
ORA - ZED | 1 | 6 | 13625124.4935 | 13829636.33 | 204511.8365 | 14374377.19 | 4832623.5365 | -9541753.6535 |  | 10000000 |  | 4374377.19 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 56 | 2021-07-05 | 2021-06-08 | 154193424.8364 | 7989637.5618 | [5 empty] | 83003.9348 | 15678333.3286 | 156246633.6714 | 4544122.0162 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED6 | ORA ZED - Ph 01B - Pkgs A&D6
ORA - ZED | 1 | 7 | 11321353.516 | 9268144.68 | -2053208.836 | 10782895.78 | 4340903.024 | -6441992.756 |  | 5000000 |  | 5782895.78 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 56 | 2021-08-04 | 2021-07-15 | 165514778.3524 | 3501497.22 | [5 empty] | 99063.49 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED7 | ORA ZED - Ph 01B - Pkgs A&D7
ORA - ZED | 1 | 8 | 26950096.619 | 26950096.62 | 0.00095236 | 24387331.1 | 25931572.791 | 1544241.691 |  |  |  | 24387331.1 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 56 | 2021-08-25 | 2021-08-12 | 192464874.9714 | 6088729.64 | [5 empty] | 175458.21 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED8 | ORA ZED - Ph 01B - Pkgs A&D8
ORA - ZED | 1 | 9 | 27403398.0286 | 27403398.03 | 0.0014286 | 22624923.97 | 24054179.0515 | 1429255.0815 |  |  |  | 22624923.97 | 2021-07-31 | 2021-07-25 | 2021-08-10 | 56 | 2021-10-05 | 2021-09-20 | 219868273 | 5900263.67 | [5 empty] | 146376.75 | 29833656.4571 | 222298531.4286 | 26728065.13 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED9 | ORA ZED - Ph 01B - Pkgs A&D9
ORA - ZED | 1 | 10 | 32858070.0667 | 32858070.07 | 0.0033334 | 29047725.55 | 30886238.8435 | 1838513.2935 |  |  |  | 29047725.55 | 2021-08-31 | 2021-08-25 | 2021-09-09 | 56 | 2021-11-04 | 2021-09-26 | 252726343.0667 | 8169556.06 | [5 empty] | 164670.96 | 32858070.0667 | 252726343.0667 | 29047725.55 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED10 | ORA ZED - Ph 01B - Pkgs A&D10
ORA - ZED | 1 | 11 | 34769848.6 | 34769848.6 | 0 | 0 | 33022101.84 | 33022101.84 |  |  |  | 31056565.55 | 2021-09-30 | 2021-09-25 | 2021-10-14 | 56 | 2021-12-09 | 2021-11-18 | 287496191.6667 | 10971940.82 | [5 empty] | 182298.18 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED11 | ORA ZED - Ph 01B - Pkgs A&D11
ORA - ZED | 1 | 12 | 33050531.6762 | 33050531.68 | 0.0038095 | 0 | 26088449.724 | 26088449.724 |  |  |  | 24536445.63 | 2021-10-31 | 2021-10-25 | 2021-11-24 | 56 | 2022-01-19 | 2021-12-07 | 320546723.3429 | 7308964.38 | [5 empty] | 182298.18 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED12 | ORA ZED - Ph 01B - Pkgs A&D12
ORA - ZED | 1 | 13 | 30511414.9714 | 30511414.97 | -0.0014286 | 0 | 25426794.8085 | 25426794.8085 |  |  |  | 23914152.624 | 2021-11-30 | 2021-11-25 | 2021-12-14 | 56 | 2022-02-08 | 2021-12-21 | 351058138.3143 | 5524822.34 | [5 empty] | 182298.18 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED13 | ORA ZED - Ph 01B - Pkgs A&D13
ORA - ZED | 1 | 14 | 45635766.9524 | 45635766.95 | -0.002381 | 0 | 38191818.9175 | 38191818.9175 |  |  |  | 35917954.71 | 2021-12-31 | 2021-12-25 | 2021-12-23 | 56 | 2022-02-17 | 2022-01-18 | 396693905.2667 | 3084551.02 | [5 empty] | 213053.66 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED14 | ORA ZED - Ph 01B - Pkgs A&D14
ORA - ZED | 1 | 15 | 27710999.5429 | 27710999.54 | -0.0028571 | 0 | 27179982.227 | 27179982.227 |  |  |  | 25550073.0625 | 2022-01-31 | 2022-01-25 | 2022-02-17 | 56 | 2022-04-14 | 2022-03-31 | 424404904.8095 | 6586185.1 | [5 empty] | 0 | 27710999.5475 | 424404904.8142 | 25550073.0625 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED15 | ORA ZED - Ph 01B - Pkgs A&D15
ORA - ZED | 1 | 16 | 28676537.6667 | 28676537.67 | 0.0033333 | 0 | 23357925.2135 | 23357925.2135 |  |  |  | 21942762.07 | 2022-02-28 | 2022-02-25 | 2022-03-16 | 56 | 2022-05-11 | 2022-04-12 | 453081442.4762 | 4779083.27 |  |  |  | 12012864.945 | 12012864.945 | 0 | 28676537.6669 | 453081442.4811 | 21942762.0737 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED16 | ORA ZED - Ph 01B - Pkgs A&D16
ORA - ZED | 1 | 17 | 30883724.2667 | 31100661.13 | 216936.8633 | 0 | 27837999.2465 | 27837999.2465 |  |  |  | 26002482 | 2022-03-31 | 2022-03-25 | 2022-04-06 | 56 | 2022-06-01 | 2022-05-11 | 483965166.7429 | 5232577.92 | [5 empty] | 0 | 31100661.1293 | 484182103.6103 | 26182539.8028 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED17 | ORA ZED - Ph 01B - Pkgs A&D17
ORA - ZED | 1 | 18 | 9956410.019 | 9690075.24 | -266334.779 | 0 | 7029281.442 | 7029281.442 |  |  |  | 6791166 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-05-26 | 493921576.7619 | 3421449.48 | [5 empty] | 0 | 11112905.9801 | 495295009.5905 | 9292712.69 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED18 | ORA ZED - Ph 01B - Pkgs A&D18
ORA - ZED | 1 | 19 | 21443765.7238 | 21493163.81 | 49398.0862 | 0 | 17518053.2705 | 17518053.2705 |  |  |  | 16483568.4889 | 2022-05-31 | 2022-05-25 | 2022-06-06 | 56 | 2022-08-01 | 2022-06-28 | 515365342.4857 | 1543331.93 | [5 empty] | 0 | 20070332.8941 | 515365342.4846 | 16483568.4889 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED19 | ORA ZED - Ph 01B - Pkgs A&D19
ORA - ZED | 1 | 20 | 25297815.7745 | 25297815.24 | -0.53451 | 16483569.19 | 21744431.032 | 5260861.842 |  |  |  | 8954952.87 | 2022-06-30 | 2022-06-25 | 2022-07-06 | 56 | 2022-08-31 | 2022-08-28 | 540663158.2602 | 852186.4268 | [5 empty] | 0 | 25297815.7756 | 540663158.2602 | 20010194.1812 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED20 | ORA ZED - Ph 01B - Pkgs A&D20
ORA - ZED | 1 | 21 | 9295356.7831 | 9295357.14 | 0.35693 | 7443623.53 | 8181176.157 | 737552.627 |  |  |  | 7443624.2902 | 2022-07-31 | 2022-07-25 | 2022-08-09 | 56 | 2022-10-04 | 2022-09-11 | 549958515.0433 | 836488.6182 | 81555880.4439 |  | 36726721.206 | 14457323.235 | 14457323.235 | 1401842.4693 | 9295356.7831 | 549958515.0433 | 7443624.2902 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED21 | ORA ZED - Ph 01B - Pkgs A&D21
ORA - ZED | 1 | 22 | 9997079.1377 | 9997079.14 | 0.0023408 | 8098825.75 | 8609716.257 | 510890.507 |  |  |  | 8098824.8775 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 56 | 2022-11-02 | 2022-09-28 | 559955594.181 | 557383.0572 | 85664325.1821 |  | 36749996.0022 | 14712768.92 | 14712768.92 | 1379966.9772 | 9997079.1377 | 559955594.181 | 8098824.8775 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED22 | ORA ZED - Ph 01B - Pkgs A&D22
ORA - ZED | 1 | 23 | 27314036.0095 | 51455589.8 | 24141553.7905 | 20215840.09 | 21483271.639 | 1267431.549 |  |  |  | 22964574.875 | 2022-09-30 | 2022-09-25 | 2022-10-09 | 56 | 2022-12-04 | 2022-10-27 | 587269630.1905 | 479281.1936 | 93161830.5539 |  | 36812284.0164 | 15427809.82 | 15427809.82 | 1232906.9943 | 27314036.0095 | 587269630.1905 | 22964574.875 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED23 | ORA ZED - Ph 01B - Pkgs A&D23
ORA - ZED | 1 | 24 | 11751887.1042 | 10139035.7 | -1612851.4042 | 6648903.39 | 8591385.3318 | 1942481.9418 |  |  |  | 7490234.3814 | 2022-12-31 | 2022-12-25 | 2023-01-18 | 56 | 2023-03-15 | 2023-03-22 | 599021517.2946 | 269002.8006 | 98882541.0407 |  | 36839181.7521 | 15725824.83 | 15725824.83 | 3165623.4593 | 11751887.1042 | 599021517.2946 | 7490234.3814 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED24 | ORA ZED - Ph 01B - Pkgs A&D24
ORA - ZED | 1 | 25 | 50310527.2958 | 0 | -50310527.2958 | 2e-05 | 0 | -2e-05 |  |  |  | -9163815.8569 | 2023-02-28 | 2023-02-25 | 2023-03-12 | 56 | 2023-05-07 | 2023-04-10 | 649332044.5905 | 241736.3176 | 113559937.642 | 3600000 | 36956312.6915 | 17045794.51 | 17045794.51 | 465623.4593 | 50310527.2958 | 649332044.5905 | -9163815.8569 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED25 | ORA ZED - Ph 01B - Pkgs A&D25
ORA - ZED | 1 | 26 | 19434003.5361 | 68520137.14 | 49086133.6039 | 9808194.12 | 6863669.1846 | -2944524.9354 |  |  |  | 16993731.7513 | 2023-03-31 | 2023-03-25 | 2023-04-16 | 56 | 2023-06-11 | 2023-05-01 | 668766048.1265 | 239033.6571 | 121577515.47 | 2750000 | 37000350.0494 | 17553262 | 17553262 | 465623.4593 | 19434003.5361 | 668766048.1265 | 16993731.7513 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED26 | ORA ZED - Ph 01B - Pkgs A&D26
ORA - ZED | 1 | 27 | 10662740.4195 | 10547653.65 | -115086.7695 | 8872947.14 | 8722947.15 | -149999.99 |  |  |  | 9042387.5614 | 2023-04-30 | 2023-04-25 | 2023-05-15 | 56 | 2023-07-10 | 2023-06-15 | 679428788.546 | 229309.1567 | 124928010.98 | 2550000 | 37025174.6113 | 17832915.825 | 17832915.825 | 465623.4593 | 10662740.4195 | 679428788.546 | 9042387.5614 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED27 | ORA ZED - Ph 01B - Pkgs A&D27
ORA - ZED | 1 | 28 | 24304667.5968 | 22847215.74 | -1457451.8568 | 9105384.7 | 8905384.6977 | -200000.0023 |  |  |  | 10264179.63 | 2023-05-31 | 2023-05-25 | 2023-06-15 | 56 | 2023-08-10 | 2023-07-09 | 703733456.1429 | 156183.3 | 132876310.5982 | 2350000 | 37192477.1578 | 18469085.205 | 18469085.205 | 489541.1493 | 24304667.5968 | 703733456.1429 | 10264179.63 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED28 | ORA ZED - Ph 01B - Pkgs A&D28
ORA - ZED | 1 | 29 | 27532348.019 | 23928989.08 | -3603358.939 | 10687601.99 | 10687601.99 | 0 |  |  |  | 13678389.68 | 2023-06-30 | 2023-06-25 | 2023-07-17 | 56 | 2023-09-11 | 2023-08-24 | 731265804.1619 |  | 143774737.6483 | 2400000 | 37381001.7016 | 19187904.7592 | 19187904.7592 | 489541.1493 | 27532348.019 | 731265804.1619 | 13678389.68 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED29 | ORA ZED - Ph 01B - Pkgs A&D29
ORA - ZED | 1 | 30 | 26015241.1905 | 24199949.01 | -1815292.1805 | 11585957.67 | 11085957.6804 | -499999.9896 |  |  |  | 13092650.18 | 2023-07-31 | 2023-07-25 | 2023-08-15 | 56 | 2023-10-10 | 2023-09-17 | 757281045.3524 |  | 149337289.3675 | 1900000 | 37609920.1669 | 19870804.84 | 19870804.84 | 489541.1493 | 26015241.1905 | 757281045.3524 | 13092650.18 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED30 | ORA ZED - Ph 01B - Pkgs A&D30
ORA - ZED | 1 | 31 | 26102241.2286 | 21322773.91 | -4779467.3186 | 10253641.2 | 10153641.2135 | -99999.9865 |  |  |  | 12746258.22 | 2023-08-31 | 2023-08-25 | 2023-09-17 | 56 | 2023-11-12 | 2023-09-27 | 783383286.581 |  | 156088918.0852 | 1800000 | 37790500.7321 | 20555988.67 | 20555988.67 | 508143.1541 | 26102241.2286 | 783383286.581 | 12746258.22 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED31 | ORA ZED - Ph 01B - Pkgs A&D31
ORA - ZED | 1 | 32 | 24532813.9714 | 17918865.67 | -6613948.3014 | 8010573.17 | 8010573.17 | 0 |  |  |  | 17052495.52 | 2023-09-30 | 2023-09-25 | 2023-10-12 | 56 | 2023-12-07 | 2023-11-11 | 807916100.5524 |  | 169479041.6436 | 1800000 | 37962018.2328 | 21199975.0395 | 21199975.0395 | 566244.2563 | 24532813.9714 | 807916100.5524 | 17052495.52 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED32 | ORA ZED - Ph 01B - Pkgs A&D32
ORA - ZED | 1 | 33 | 20642302.219 | 18602239.47 | -2040062.749 | 12164893.39 | 12164893.39 | 0 |  |  |  | 13971110.85 | 2023-10-31 | 2023-10-25 | 2023-11-11 | 56 | 2024-01-06 | 2023-12-17 | 828558402.7714 |  | 183850209.8662 | 1800000 | 38104925.5449 | 21741835.4727 | 21741835.4727 | 728244.2563 | 20642302.219 | 828558402.7714 | 13971110.85 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED33 | ORA ZED - Ph 01B - Pkgs A&D33
ORA - ZED | 1 | 34 | 14702199.581 | 12357935.4 | -2344264.181 | 9568963.5 | 10018963.4932 | 449999.9932 |  |  |  | 11514703.33 | 2023-11-30 | 2023-11-25 | 2023-12-17 | 56 | 2024-02-11 | 2024-01-28 | 843260602.3524 |  | 188799507.8 | 2350000 | 38207159.3831 | 22127768.21 | 22127768.21 | 866366.5763 | 14702199.581 | 843260602.3524 | 11514703.33 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED34 | ORA ZED - Ph 01B - Pkgs A&D34
ORA - ZED | 1 | 35 | 13918410.7524 | 9206608.75 | -4711802.0024 | 7391485.26 | 7391485.26 | 0 |  |  |  | 11302280.92 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-02-11 | 857179013.1048 |  | 199336628.67 | 2600000 | 40055372.1837 | 22493126.49 | 22493126.49 | 866366.5763 | 13918410.7524 | 857179013.1048 | 11302280.92 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED35 | ORA ZED - Ph 01B - Pkgs A&D35
ORA - ZED | 1 | 36 | 9427629.6762 | 9427628.57 | -1.1062 | 7054023.71 | 7054023.71 | 0 |  |  |  | 30791363.32 | 2024-01-31 | 2024-01-25 | 2024-02-11 | 56 | 2024-04-07 | 2024-03-12 | 866606642.781 |  | 202490336.7307 | 2950000 | 40124683.5553 | 22740601.77 | 22740601.77 | 1287275.408 | 9427629.6762 | 866606642.781 | 30791363.32 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED36 | ORA ZED - Ph 01B - Pkgs A&D36
ORA - ZED | 1 | 37 | 11141064.9524 | 29089779.62 | 17948714.6676 | 23554316.1 | 23554316.1 | 0 |  |  |  | 9469567.93 | 2024-02-29 | 2024-02-25 | 2024-03-12 | 56 | 2024-05-07 | 2024-04-24 | 877747707.7333 |  | 205574473.0325 | 3350000 | 40202154.5368 | 23033054.728 | 23033054.728 | 1416236.983 | 11141064.9524 | 877747707.7333 | 9469567.93 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED37 | ORA ZED - Ph 01B - Pkgs A&D37
ORA - ZED | 1 | 38 | 15909843.4381 | 23109783.65 | 7199940.2119 | 17627053.17 | 17627053.17 | 0 |  |  |  | 12665876.69 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-09 | 893657551.1714 |  | 212207212.1568 | 3550000 | 40322143.2235 | 23450688.1182 | 23450688.1182 | 1426063.9 | 15909843.4381 | 893657551.1714 | 12665876.69 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED38 | ORA ZED - Ph 01B - Pkgs A&D38
ORA - ZED | 1 | 39 | 9971577.2286 | 9971577.14 | -0.088571 | 7606231.63 | 7606231.63 | 0 |  |  |  | 7606231.5 | 2024-04-30 | 2024-04-25 | 2024-05-09 | 56 | 2024-07-04 | 2024-06-06 | 903629128.4 |  | 212836770.28 | 5150000 | 40471225.4023 | 23712442.02 | 23712442.02 | 1543257.113 | 9971577.2286 | 903629128.4 | 7606231.5 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED39 | ORA ZED - Ph 01B - Pkgs A&D39
ORA - ZED | 1 | 40 | 7576454.8952 | 4495110.55 | -3081344.3452 | 3717952.37 | 3717952.37 | 0 |  |  |  | 6599009.58 | 2024-05-31 | 2024-05-25 | 2024-06-06 | 56 | 2024-08-01 | 2024-07-01 | 911205583.2952 |  | 217295013.586 | 5311993 | 40584498.7969 | 23911323.96 | 23911323.96 | 1866239.86 | 7576454.8952 | 911205583.2952 | 6599009.58 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED40 | ORA ZED - Ph 01B - Pkgs A&D40
ORA - ZED | 1 | 41 | 4542501.819 | 8233965.99 | 3691464.171 | 4428778.21 | 6728778.2096 | 2299999.9996 |  |  |  | 3961614.17 | 2024-06-30 | 2024-06-25 | 2024-07-16 | 56 | 2024-09-10 | 2024-08-31 | 915748085.1143 |  | 218624574.9261 | 4611993 | 40652412.433 | 24038387.2343 | 24038387.2343 | 2836219.6905 | 4542501.819 | 915748085.1143 | 3961614.17 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED41 | ORA ZED - Ph 01B - Pkgs A&D41
ORA - ZED | 1 | 42 | 5377971.181 | 9191767.67 | 3813796.489 | 70851.77 | 7070851.77 | 7000000 |  |  |  | 3504951.97 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-01 | 921126056.2952 |  | 221585074.8608 | 5650000 | 40732816.931 | 24179558.9777 | 24179558.9777 | 3321663.778 | 5377971.181 | 921126056.2952 | 3504951.97 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED42 | ORA ZED - Ph 01B - Pkgs A&D42
ORA - ZED | 1 | 43 | 11538786.4 | 11538786.67 | 0.27 | 6004454.53 | 10554454.5368 | 4550000.0068 |  |  |  | 11004454.56 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-22 | 932664842.6952 |  | 225919078.57 | 5200000 | 40983305.2755 | 24482452.12 | 24482452.12 | 3555974.5005 | 11538786.4 | 932664842.6952 | 11004454.56 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED43 | ORA ZED - Ph 01B - Pkgs A&D43
ORA - ZED | 1 | 44 | 5304711.9524 | 0 | -5304711.9524 | 0 | 0 | 0 |  |  |  | 4559905.68 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 937969554.6476 |  | 231364687.5663 | 5600000 | 41098461.9713 | 24621700.8095 | 24621700.8095 | 3555974.5005 | 5304711.9524 | 937969554.6476 | 4559905.68 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED44 | ORA ZED - Ph 01B - Pkgs A&D44
ORA - ZED | 1 | 45 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 | [8 empty] | 0 | 0 | 0 | 0 | ORA ZED - Ph 01B - Pkgs A&D |  |  |  | ORA - ZED45 | ORA ZED - Ph 01B - Pkgs A&D45
ORA - ZED - Landscape | 1 | 1 | 2611606.8286 | 2611606.83 | 0.0014286 | 11802742.07 | 2304743.0232 | -9497999.0468 |  |  |  | 2167633.6703 | 2022-11-30 | 2022-11-25 | 2022-12-11 | 56 | 2023-02-05 | 2022-12-20 | 2611606.8286 |  | 503419.5862 |  |  | 68554.675 | 68554.675 | 0 | 2611606.8286 | 2611606.8286 | 2167633.6703 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape1 | Ora Zed Landscape Ph11
ORA - ZED - Landscape | 1 | 2 | 2071867.5333 | 4143733 | 2071865.4667 | 1719649.2 | 1828422.185 | 108772.985 |  |  |  | 1719650.0563 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-01 | 4683474.3619 |  | 1329550.324 |  | 30299.3908 | 122941.2 | 122941.2 | 0 | 2071867.5333 | 4683474.3619 | 1719650.0563 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape2 | Ora Zed Landscape Ph12
ORA - ZED - Landscape | 1 | 3 | 2138801.7905 | 2138801.9 | 0.10952 | 1775205.58 | 1887492.675 | 112287.095 |  |  |  | 1775205.4809 | 2023-01-31 | 2023-01-25 | 2023-01-25 | 56 | 2023-03-22 | 2023-02-26 | 6822276.1524 |  | 2116384.0303 |  | 118260.296 | 179084.745 | 179084.745 | 0 | 2138801.7905 | 6822276.1524 | 1775205.4809 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape3 | Ora Zed Landscape Ph13
ORA - ZED - Landscape | 1 | 4 | 4909563.9143 | 4909564.83 | 0.91571 | 4074938.81 | 4332690.6 | 257751.79 |  |  |  | 4074938.0511 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-10 | 11731840.0667 |  | 4050371.3819 |  | 639071.4395 | 307960.8 | 307960.8 | 0 | 4909563.9143 | 11731840.0667 | 4074938.0511 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape4 | Ora Zed Landscape Ph14
ORA - ZED - Landscape | 1 | 5 | 3861209.6 | 3284925.66 | -576283.94 | 2726488.3 | 2898946.893 | 172458.593 |  |  |  | 3204803.968 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 15593049.6667 |  | 5404662.8768 |  | 772348.3981 | 409317.55 | 409317.55 | 0 | 3861209.6 | 15593049.6667 | 3204803.968 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape5 | Ora Zed Landscape Ph15
ORA - ZED - Landscape | 1 | 6 | 3232045.3524 | 3759868.55 | 527823.1976 | 3120690.89 | 3318083.9875 | 197393.0975 |  |  |  | 3160913.3163 | 2023-04-30 | 2023-04-25 | 2023-05-11 | 56 | 2023-07-06 | 2023-06-07 | 18825095.019 |  | 6624089.2242 |  | 816946.8694 | 494158.74 | 494158.74 | 0 | 3232045.3524 | 18825095.019 | 3160913.3163 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape6 | Ora Zed Landscape Ph16
ORA - ZED - Landscape | 1 | 7 | 1440674.7619 | 1343089.52 | -97585.2419 | 964764.3 | 1035276.496 | 70512.196 |  |  |  | 1045760.0532 | 2023-05-31 | 2023-05-25 | 2023-06-07 | 56 | 2023-08-02 | 2023-07-17 | 20265769.781 |  | 7155995.1362 |  | 835084.5832 | 531976.455 | 531976.455 | 0 | 1440674.7619 | 20265769.781 | 1045760.0532 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape7 | Ora Zed Landscape Ph17
ORA - ZED - Landscape | 1 | 8 | 11600772.2694 | 6274745.71 | -5326026.5594 | 5158038.94 | 5158038.9355 | -0.0045 |  |  |  | 9578640.9799 | 2023-06-30 | 2023-06-25 | 2023-07-09 | 56 | 2023-09-03 | 2023-08-09 | 31866542.0504 |  | 10056562.0507 | 200000 | 5892201.0451 | 836496.7288 | 836496.7288 | 0 | 11600772.2694 | 31866542.0504 | 9578640.9799 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape8 | Ora Zed Landscape Ph18
ORA - ZED - Landscape | 1 | 9 | 3994751.4353 | 4486249.0225 | 491497.5872 | 3863087.97 | 3863087.97 | 0 |  |  |  | 3636861.9198 | 2023-07-31 | 2023-07-25 | 2023-08-07 | 56 | 2023-10-02 | 2023-09-17 | 35861293.4857 |  | 10889989.7064 |  | 5974589.29 | 941358.95 | 941358.95 | 0 | 3994751.4353 | 35861293.4857 | 3636861.9198 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape9 | Ora Zed Landscape Ph19
ORA - ZED - Landscape | 1 | 10 | 3258480.2857 | 3148169.54 | -110310.7457 | 6562980.72 | 2562980.717 | -4000000.003 |  |  |  | 2654538.63 | 2023-08-31 | 2023-08-25 | 2023-09-10 | 56 | 2023-11-05 | 2023-10-10 | 39119773.7714 |  | 12128157.28 | 50000 | 6008554.2 | 1026894.06 | 1026894.06 | 0 | 3258480.2857 | 39119773.7714 | 2654538.63 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape10 | Ora Zed Landscape Ph110
ORA - ZED - Landscape | 1 | 11 | 6742108.1048 | 6460754.42 | -281353.6848 | 5312426.17 | 5312426.17 | 0 |  |  |  | 6014170.71 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-04 | 45861881.8762 |  | 14252099.55 | 100000 | 6064800 | 1203874 | 1203874 | 0 | 6742108.1048 | 45861881.8762 | 6014170.71 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape11 | Ora Zed Landscape Ph111
ORA - ZED - Landscape | 1 | 12 | 9303031.3714 | 7506327.07 | -1796704.3014 | 6030251.47 | 6030251.47 | 0 |  |  |  | 7521516.04 | 2023-10-31 | 2023-10-25 | 2023-11-06 | 56 | 2024-01-01 | 2023-11-20 | 55164913.2476 |  | 16356170.6 | 300000 | 6136800.24 | 1448078.975 | 1448078.975 | 0 | 9303031.3714 | 55164913.2476 | 7521516.04 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape12 | Ora Zed Landscape Ph112
ORA - ZED - Landscape | 1 | 13 | -692002.6286 | 1148717.83 | 1840720.4586 | 0 | 868255.79 | 868255.79 |  |  |  | -674362.19 | 2023-11-30 | 2023-11-25 | 2023-12-11 | 56 | 2024-02-05 | 2024-02-20 | 54472910.619 |  | 13854310.92 | 400000 | 6133954.27 | 1429913.905 | 1429913.905 | 0 | -692002.6286 | 54472910.619 | -674362.19 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape13 | Ora Zed Landscape Ph113
ORA - ZED - Landscape | 1 | 14 | 1197004.6952 | 0 | -1197004.6952 | 868255.79 | 0 | -868255.79 |  |  |  | 1008333.54 | 2023-12-31 | 2023-12-25 | 2024-01-16 | 56 | 2024-03-12 | 2024-03-20 | 55669915.3143 |  | 14304471.38 | 385180.36 | 6143327.5 | 1461335.275 | 1461335.275 | 0 | 1197004.6952 | 55669915.3143 | 1008333.54 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape14 | Ora Zed Landscape Ph114
ORA - ZED - Landscape | 1 | 15 | 3753240.219 | 3753240.01 | -0.20905 | 3165189.2 | 3165189.2 | 0 |  |  |  | 5175911.36 | 2024-01-31 | 2024-01-25 | 2024-02-06 | 56 | 2024-04-02 | 2024-04-20 | 59423155.5333 |  | 16680600.84 | 335180.36 | 5731208.99 | 1559857.835 | 1559857.835 | 0 | 3753240.219 | 59423155.5333 | 5175911.36 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape15 | Ora Zed Landscape Ph115
ORA - ZED - Landscape | 1 | 16 | 1773392.8381 | 1773393.33 | 0.4919 | 1521916.47 | 1521916.4665 | -0.0035 |  |  |  | 1521916.05 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-03-30 | 61196548.3714 |  | 14544514.79 | 285180.36 | 5755565.16 | 1606409.395 | 1606409.395 | 0 | 1773392.8381 | 61196548.3714 | 1521916.05 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape16 | Ora Zed Landscape Ph116
ORA - ZED - Landscape | 1 | 17 | 1582674.7048 | 1582674.29 | -0.41476 | 1313619.66 | 1313619.66 | 0 |  |  |  | 1313620 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-04-28 | 62779223.0762 |  | 15060209.78 | 285180.36 | 5766649.95 | 1647954.605 | 1647954.605 | 0 | 1582674.7048 | 62779223.0762 | 775773.82 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape17 | Ora Zed Landscape Ph117
ORA - ZED - Landscape | 1 | 18 | 1979868.8571 | 1175128.22 | -804740.6371 | 975356.43 | 975356.43 | 0 |  |  |  | 1643291.15 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-05-14 | 64759091.9333 |  | 16924136.12 | 285180.36 | 5796250.4 | 1699926.165 | 1699926.165 | 0 | 1979868.8571 | 64759091.9333 | 1643291.15 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape18 | Ora Zed Landscape Ph118
ORA - ZED - Landscape | 1 | 19 | 1453055.0476 | 1347822.27 | -105232.7776 | 618692.48 | 618692.48 | 0 |  |  |  | 168189.5 | 2024-05-31 | 2024-05-25 | 2024-06-04 | 56 | 2024-07-30 | 2024-07-07 | 66212146.981 |  | 17189828.91 | 785180.36 | 5817974.6 | 1738068.86 | 1738068.86 | 0 | 1453055.0476 | 66212146.981 | 168189.5 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape19 | Ora Zed Landscape Ph119
ORA - ZED - Landscape | 1 | 20 | 1399335.6857 | 1318831.15 | -80504.5357 | 1177303.85 | 1177303.85 | 0 |  |  |  | 1244123 | 2024-06-30 | 2024-06-25 | 2024-07-07 | 56 | 2024-09-01 | 2024-07-23 | 67611482.6667 |  | 17563515.19 | 335180.36 | 5838895.67 | 1774801.42 | 1774801.42 | 0 | 1399335.6857 | 67611482.6667 | 1244123 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape20 | Ora Zed Landscape Ph120
ORA - ZED - Landscape | 1 | 21 | 422349.9905 | 324859.52 | -97490.4705 | 108767.39 | 108767.386 | -0.004 |  |  |  | 189683.6223 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-05 | 68033832.6571 |  | 17849734.0836 | 385180.36 | 5845210.1017 | 1785888.105 | 1785888.105 | 0 | 422349.9905 | 68033832.6571 | 189683.6223 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape21 | Ora Zed Landscape Ph121
ORA - ZED - Landscape | 1 | 22 | 4226377.8476 | 0 | -4226377.8476 | 0 | 0 | 0 |  |  |  | 1388299.8 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-16 | 72260210.5048 |  | 19837405.71 | 935180.36 | 5908397.46 | 1896830.525 | 1896830.525 | 0 | 4226377.8476 | 72260210.5048 | 1388299.8 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape22 | Ora Zed Landscape Ph122
ORA - ZED - Landscape | 1 | 23 | 1124749.1714 | 0 | -1124749.1714 | 0 | 0 | 0 |  |  |  | 1551640.48 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 73384959.6762 |  | 20272182.95 | 435180.36 | 5961374.39 | 1926355.19 | 1926355.19 | 0 | 1124749.1714 | 73384959.6762 | 1551640.48 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape23 | Ora Zed Landscape Ph123
ORA - ZED - Landscape | 1 | 24 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-10 | 56 | 2025-01-05 | [8 empty] | 0 | 0 | 0 | 0 | Ora Zed Landscape Ph1 |  |  |  | ORA - ZED - Landscape24 | Ora Zed Landscape Ph124
ORA - ZED - ph.02 | 1 | 1 | 13196047.2 | 13196047.2 | 0 | 14536704.19 | 15456194.14 | 919489.95 |  | 25000000 | 25000000 | 14536703 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 56 | 2021-12-01 | 2021-10-13 | 13196047.2 | 4533956.5 | [5 empty] | 0 | 13196047.2 | 13196047.2 | 14536703.8371 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.021 | ORA ZED-Ph 2-Pkgs A&D1
ORA - ZED - ph.02 | 1 | 2 | 21711682.2 | 21711682.2 | 0 | 20471935.63 | 21766847.47 | 1294911.84 |  | 15000000 | 12500000 | 20471935.87 | 2021-10-31 | 2021-10-25 | 2021-11-15 | 56 | 2022-01-10 | 2021-11-14 | 34907729.4 | 7634922.31 | [5 empty] | 0 | 21711682.2014 | 34907729.4014 | 20471935.8674 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.022 | ORA ZED-Ph 2-Pkgs A&D2
ORA - ZED - ph.02 | 1 | 3 | 15579509.1905 | 15579509.09 | -0.10048 | 12325142.71 | 9914986.5145 | -2410156.1955 |  | 3000000 |  | 9325143.2186 | 2021-11-30 | 2021-11-25 | 2021-12-05 | 56 | 2022-01-30 | 2022-01-18 | 50487238.5905 | 3073305.59 | [5 empty] | 0 | 15579509.1856 | 50487238.587 | 9325143.2186 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.023 | ORA ZED-Ph 2-Pkgs A&D3
ORA - ZED - ph.02 | 1 | 4 | 34347323.4857 | 34347323.22 | -0.26571 | 54728856.89 | 30546043.101 | -24182813.789 |  | 26000000 |  | 28728856.62 | 2021-12-31 | 2021-12-26 | 2021-12-26 | 56 | 2022-02-20 | 2022-02-15 | 84834562.0762 | 3352350.21 | [5 empty] | 0 | 34505631.6966 | 84992870.2836 | 28860252.4316 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.024 | ORA ZED-Ph 2-Pkgs A&D4
ORA - ZED - ph.02 | 1 | 5 | 10060643.6952 | 10060644.07 | 0.37476 | 12407121.98 | 13201853.2135 | 794731.2335 |  |  |  | 12407122.37 | 2022-01-31 | 2022-01-25 | 2022-02-10 | 56 | 2022-04-07 | 2022-03-23 | 94895205.7714 | 8683284.6 | [5 empty] | 0 | 9902335.4874 | 94895205.771 | 12407122.3694 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.025 | ORA ZED-Ph 2-Pkgs A&D5
ORA - ZED - ph.02 | 1 | 6 | 23225104.4643 | 23225104.47 | 0.0056804 | 16610991.38 | 17674903.7 | 1063912.32 |  |  |  | 16610990.7481 | 2022-02-28 | 2022-02-25 | 2022-03-21 | 56 | 2022-05-16 | 2022-05-10 | 118120310.2353 | 5575171.2714 |  |  |  | 3240037.4255 | 3240037.4255 | 0 | 23225104.4643 | 118120310.2353 | 16610990.7481 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.026 | ORA ZED-Ph 2-Pkgs A&D6
ORA - ZED - ph.02 | 1 | 7 | 42383851.5888 | 42383851.59 | 0.0011564 | 32100387.28 | 34124964.2595 | 2024576.9795 |  |  |  | 32100388.5958 | 2022-03-31 | 2022-03-25 | 2022-04-04 | 56 | 2022-05-30 | 2022-08-07 | 160504161.8242 | 1563640.4346 |  |  |  | 4252325.255 | 4252325.255 | 273333.59 | 42383851.5888 | 160504161.8242 | 32100388.5958 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.027 | ORA ZED-Ph 2-Pkgs A&D7
ORA - ZED - ph.02 | 1 | 8 | 8766077.2795 | 8766077.29 | 0.010467 | 8595540.37 | 9151883.2345 | 556342.8645 |  |  |  | 8595538.9026 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-06-09 | 169270239.1037 | 3486145.8511 |  |  | 32252330.5602 | 4530497.42 | 4530497.42 | 473333.59 | 8766077.2795 | 169270239.1037 | 8595538.9026 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.028 | ORA ZED-Ph 2-Pkgs A&D8
ORA - ZED - ph.02 | 1 | 9 | 8712415.4916 | 8712415.5 | 0.0083646 | 7163536.59 | 7614021.055 | 450484.465 |  |  |  | 7163536.3546 | 2022-05-31 | 2022-05-25 | 2022-06-05 | 56 | 2022-07-31 | 2022-08-08 | 177982654.5953 | 3347808.9149 | 15346414.5805 |  | 32754709.2407 | 4755739.905 | 4755739.905 | 431750.04 | 8712415.4916 | 177982654.5953 | 7163536.3546 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.029 | ORA ZED-Ph 2-Pkgs A&D9
ORA - ZED - ph.02 | 1 | 10 | 25761823.8629 | 25761823.86 | -0.0029215 | 20828447.26 | 22199070.249 | 1370622.989 |  |  |  | 20828447.3064 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 56 | 2022-08-30 | 2022-08-22 | 203744478.4582 | 2710387.4388 | 19184341.5109 |  | 44374111.2806 | 5416052.245 | 5416052.245 | 481750.04 | 25761823.8629 | 203744478.4582 | 20828447.3064 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0210 | ORA ZED-Ph 2-Pkgs A&D10
ORA - ZED - ph.02 | 1 | 11 | 10555360.8465 | 10555360.84 | -0.0065181 | 12170282.5 | 12170282.5 | 0 |  |  |  | 12170283.1854 | 2022-07-31 | 2022-07-25 | 2022-08-10 | 56 | 2022-10-05 | 2022-09-14 | 214299839.3048 | 6960146.9261 | 21459521.0485 |  | 44831361.1808 | 5799374.45 | 5799374.45 | 431750.04 | 10555360.8465 | 214299839.3048 | 12170283.1854 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0211 | ORA ZED-Ph 2-Pkgs A&D11
ORA - ZED - ph.02 | 1 | 12 | 16689354.4631 | 16689354.47 | 0.0068557 | 14759397.95 | 15225579.9035 | 466181.9535 |  |  |  | 14759398 | 2022-08-31 | 2022-08-25 | 2022-09-08 | 56 | 2022-11-03 | 2022-10-12 | 230989193.7679 | 8729597.3 | 23666966.21 |  | 45632622.2463 | 6281714.5 | 6281714.5 | 923489 | 16545380.5429 | 230845219.8476 | 14639634.3822 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0212 | ORA ZED-Ph 2-Pkgs A&D12
ORA - ZED - ph.02 | 1 | 13 | 20581919.2571 | 36051317.97 | 15469398.7129 | 13268244.56 | 13357287.557 | 89042.997 |  |  |  | 17432997.712 | 2022-09-30 | 2022-09-25 | 2022-10-02 | 56 | 2022-11-27 | 2022-10-22 | 251427139.1048 | 9285019.1626 | 25526704.6029 |  | 54138067.1729 | 6832087.88 | 6832087.88 | 1012532.93 | 20581919.2571 | 251427139.1048 | 17432997.712 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0213 | ORA ZED-Ph 2-Pkgs A&D13
ORA - ZED - ph.02 | 1 | 14 | 19311587.7934 | 12548033.06 | -6763554.7334 | 15256729.38 | 15106729.373 | -150000.007 |  |  |  | 15411600.8685 | 2022-10-31 | 2022-10-25 | 2022-11-09 | 56 | 2023-01-04 | 2022-12-15 | 270738726.8982 | 8366501.3369 | 26771100.6571 |  | 60073669.5278 | 7316054.1145 | 7316054.1145 | 862532.9342 | 19311587.7934 | 270738726.8982 | 15411600.8685 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0214 | ORA ZED-Ph 2-Pkgs A&D14
ORA - ZED - ph.02 | 1 | 15 | 14179983.4542 | 20441047.55 | 6261064.0958 | 11384143.67 | 11268654.1775 | -115489.4925 |  |  |  | 11605388.8976 | 2022-11-30 | 2022-11-25 | 2022-12-05 | 56 | 2023-01-30 | 2022-12-20 | 284918710.3524 | 8026884.6944 | 27159626.8647 |  | 63560657.3095 | 7679788.26 | 7679788.26 | 758071.44 | 14179983.4542 | 284918710.3524 | 11605388.8976 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0215 | ORA ZED-Ph 2-Pkgs A&D15
ORA - ZED - ph.02 | 1 | 16 | 11487525.8247 | 23549427.44 | 12061901.6153 | 9858410.94 | 9768410.9408 | -89999.9992 |  |  |  | 9858411.1445 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-05 | 296406236.1771 | 8322611.144 | 27430483.1297 |  | 65684472.9994 | 7988728.975 | 7988728.975 | 668071.44 | 11487525.8247 | 296406236.1771 | 9858411.1445 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0216 | ORA ZED-Ph 2-Pkgs A&D16
ORA - ZED - ph.02 | 1 | 17 | 9516947.0875 | 9516947.6 | 0.51246 | 8988166.12 | 8988166.1131 | -0.0069 |  |  |  | 8988165.9521 | 2023-01-31 | 2023-01-25 | 2023-01-28 | 56 | 2023-03-25 | 2023-03-19 | 305923183.2647 | 9631056.1321 | 28105199.965 |  | 66254957.5517 | 8271259.96 | 8271259.96 | 613266.18 | 9516947.0875 | 305923183.2647 | 8988165.9521 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0217 | ORA ZED-Ph 2-Pkgs A&D17
ORA - ZED - ph.02 | 1 | 18 | 15495416.059 | 15364644.61 | -130771.449 | 13223027.75 | 13333027.7475 | 109999.9975 |  |  |  | 13331568.0485 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-18 | 321418599.3237 | 10365262.5801 | 28915218.0403 | 400000 | 72791890.9694 | 8696369.795 | 8696369.795 | 323266.18 | 15495416.059 | 321418599.3237 | 13331568.0485 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0218 | ORA ZED-Ph 2-Pkgs A&D18
ORA - ZED - ph.02 | 1 | 19 | 8053943.7501 | 8053943.79 | 0.039909 | 6921352.11 | 7571824.5446 | 650472.4346 |  |  |  | 6921352.2914 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 329472543.0738 | 10413345.9625 | 29296490.0269 | 200000 | 76001927.9044 | 8908987.9 | 8908987.9 | 324695.97 | 8053943.7501 | 329472543.0738 | 6921352.2914 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0219 | ORA ZED-Ph 2-Pkgs A&D19
ORA - ZED - ph.02 | 1 | 20 | 4423045.841 | 4105367.03 | -317678.811 | 3038540.29 | 3188540.2834 | 149999.9934 |  |  |  | 3302213.7069 | 2023-04-30 | 2023-04-25 | 2023-05-10 | 56 | 2023-07-05 | 2023-06-01 | 333895588.9148 | 10136406.1294 | 30236499.4184 | 350000 | 76323656.7997 | 9018169.36 | 9018169.36 | 324695.97 | 4423045.841 | 333895588.9148 | 3302213.7069 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0220 | ORA ZED-Ph 2-Pkgs A&D20
ORA - ZED - ph.02 | 1 | 21 | 4766150.0757 | 4766150.56 | 0.48435 | 4532160.06 | 4432160.4921 | -99999.5679 |  |  |  | 4532159.65 | 2023-05-31 | 2023-05-25 | 2023-06-04 | 56 | 2023-07-30 | 2023-08-14 | 338661738.9905 | 10738897.52 | 27714328.99 | 250000 | 79032701.56 | 9158343.085 | 9158343.085 | 324695.97 | 4766150.0798 | 338661738.9946 | 4532159.6508 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0221 | ORA ZED-Ph 2-Pkgs A&D21
ORA - ZED - ph.02 | 1 | 22 | 11000140.3008 | 21592711.1 | 10592570.7992 | 8297638.82 | 8347638.3819 | 49999.5619 |  |  |  | 8466780.16 | 2023-06-30 | 2023-06-25 | 2023-07-12 | 56 | 2023-09-06 | 2023-08-09 | 349661879.2913 | 9962990.1626 | 30646302.9038 | 300000 | 84045575.3164 | 9427699.0855 | 9427699.0855 | 324695.97 | 11000140.3008 | 349661879.2913 | 8466780.16 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0222 | ORA ZED-Ph 2-Pkgs A&D22
ORA - ZED - ph.02 | 1 | 23 | 1051681.4414 | 1051680.08 | -1.3614 | 564270 | 534269.994 | -30000.006 |  |  |  | 564270.13 | 2023-07-31 | 2023-07-25 | 2023-08-09 | 56 | 2023-10-04 | 2023-09-17 | 350713560.7327 | 9534609.8107 | 30624495.36 | 270001 | 84127290.1745 | 9444596.21 | 9444596.21 | 324695.97 | 1051681.4414 | 350713560.7327 | 564270.13 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0223 | ORA ZED-Ph 2-Pkgs A&D23
ORA - ZED - ph.02 | 1 | 24 | 1619984.7524 | 1619984.79 | 0.037619 | 1374587.38 | 1344587.3795 | -30000.0005 |  |  |  | 1374588.34 | 2023-08-31 | 2023-08-25 | 2023-09-09 | 56 | 2023-11-04 | 2023-09-17 | 352333545.4851 | 9534609.8107 | 30639873.392 | 240000 | 84127290.1745 | 9487120.81 | 9487120.81 | 324695.97 | 1619984.7524 | 352333545.4851 | 1374588.34 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0224 | ORA ZED-Ph 2-Pkgs A&D24
ORA - ZED - ph.02 | 1 | 25 | 1429470.734 | 1429471.43 | 0.69601 | 996461.29 | 1086725.0887 | 90263.7987 |  |  |  | 996460.71 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-07 | 353763016.219 | 9534609.81 | 30639873.4 | 430000 | 84470961.01 | 9524644.42 | 9524644.42 | 324695.97 | 1429470.734 | 353763016.219 | 996460.71 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0225 | ORA ZED-Ph 2-Pkgs A&D25
ORA - ZED - ph.02 | 1 | 26 | 3475331.4095 | 3475331.25 | -0.15952 | 2944524.93 | 2884524.9425 | -59999.9875 |  |  |  | 2944525.07 | 2023-10-31 | 2023-10-25 | 2023-11-07 | 56 | 2024-01-02 | 2023-12-14 | 357238347.6286 | 9534609.81 | 30760806.2 | 370000 | 84664884.26 | 9615871.87 | 9615871.87 | 324695.97 | 3475331.4095 | 357238347.6286 | 2944525.07 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0226 | ORA ZED-Ph 2-Pkgs A&D26
ORA - ZED - ph.02 | 1 | 27 | 3041219.2755 | 6420474.62 | 3379255.3445 | 5268993.93 | 5328993.921 | 59999.991 |  |  |  | 6012429.48 | 2023-11-30 | 2023-11-25 | 2023-12-14 | 56 | 2024-02-08 | 2024-01-14 | 360279566.9041 | 9534609.8107 | 31106243.5594 | 430000 | 84803721.0331 | 9695703.875 | 9695703.875 | 324695.97 | 3041219.2755 | 360279566.9041 | 6012429.48 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0227 | ORA ZED-Ph 2-Pkgs A&D27
ORA - ZED - ph.02 | 1 | 28 | 5861894.8952 | 2340664.72 | -3521230.1752 | 1922751.71 | 1922751.71 | 0 |  |  |  | 1674078.17 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-03-03 | 366141461.7993 | 9534609.8107 | 32767206.4615 | 450000 | 88600538.3056 | 9849578.6176 | 9849578.6176 | 324695.97 | 5861894.8952 | 366141461.7993 | 1674078.17 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0228 | ORA ZED-Ph 2-Pkgs A&D28
ORA - ZED - ph.02 | 1 | 29 | 2577878.9747 | 7868267.11 | 5290388.1353 | 5009481.72 | 5059481.7155 | 49999.9955 |  |  |  | 622103 | 2024-01-31 | 2024-01-25 | 2024-02-13 | 56 | 2024-04-09 | 2024-04-15 | 368719340.774 | 7793026.7073 | 32686135.972 | 500000 | 89023126.49 | 9873708.36 | 9873708.36 | 419195.97 | 2577878.9747 | 368719340.774 | 651831.843 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0229 | ORA ZED-Ph 2-Pkgs A&D29
ORA - ZED - ph.02 | 1 | 30 | 2066668.4069 | 10058718.7 | 7992050.2931 | 73017 | 3791012.07 | 3717995.07 |  |  |  | 73017 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-04-29 | 370786009.181 | 6499733.7 | 32340261.62 | 1120000 | 89409590.24 | 9895626.085 | 9895626.085 | 419195.97 | 2066668.4036 | 370786009.1777 | -2279827.56 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0230 | ORA ZED-Ph 2-Pkgs A&D30
ORA - ZED - ph.02 | 1 | 31 | 7992050.6095 | 0 | -7992050.6095 | 3717995 | 0 | -3717995 |  |  |  | 3717995 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-15 | 378778059.7905 | 3482050.01 | 39683396.61 | 1650000 | 88674483.32 | 10029975.32 | 10029975.32 | 419195.97 | 7992050.6 | 378778059.7777 | 3758520.95 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0231 | ORA ZED-Ph 2-Pkgs A&D31
ORA - ZED - ph.02 | 1 | 32 | 2766734.981 | 2766735.75 | 0.76905 | 2836390.67 | 2836390.6675 | -0.0025 |  |  |  | 2943652.2 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-06-05 | 381544794.7714 | 3482050.01 | 39914992.15 | 1110000 | 89539810.97 | 10102602.115 | 10102602.115 | 419195.97 | 2766734.981 | 381544794.7714 | 2943652.2 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0232 | ORA ZED-Ph 2-Pkgs A&D32
ORA - ZED - ph.02 | 1 | 33 | 6575447.0667 | 7988113.29 | 1412666.2233 | 1e-05 | 5000134.02 | 5000134.02 |  |  |  | 1631186.62 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 56 | 2024-07-31 | 2024-07-01 | 388120241.8381 | 3482050.01 | 40131194.96 | 2270000 | 90446780.46 | 10188156.35 | 10188156.35 | 419195.97 | 6575447.0667 | 388120241.8381 | 1631186.62 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0233 | ORA ZED-Ph 2-Pkgs A&D33
ORA - ZED - ph.02 | 1 | 34 | 1412666.8095 | 0 | -1412666.8095 | 1e-05 | 0 | -1e-05 |  |  |  | 3368948.46 | 2024-06-30 | 2024-06-25 | 2024-07-06 | 56 | 2024-08-31 | 2024-08-06 | 389532908.6476 | 3482050.01 | 40483731.09 | 2740000 | 92888843.55 | 10312290.1 | 10312290.1 | 419195.97 | 1412666.8095 | 389532908.6476 | 3368948.46 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0234 | ORA ZED-Ph 2-Pkgs A&D34
ORA - ZED - ph.02 | 1 | 35 | 7262978.339 | 7262978.01 | -0.32896 | 1e-05 | 3820917.5505 | 3820917.5505 |  |  |  | 6454315.65 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-08-31 | 396795886.9866 | 3482050.0134 | 42071751.0265 | 2400000 | 94659153.4844 | 10502943.2837 | 10502943.2837 | 419195.97 | 7262978.339 | 396795886.9866 | 6454315.65 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0235 | ORA ZED-Ph 2-Pkgs A&D35
ORA - ZED - ph.02 | 1 | 36 | 0.003893 | 0 | -0.003893 | 4160916.8 | 0 | -4160916.8 |  |  |  | 6578211.32 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 56 | 2024-10-27 | 2024-09-05 | 396795886.9905 | 11803883.61 | 42071751.03 | 2400000 | 94659153.49 | 10710989.125 | 10710989.125 | 419195.97 | 0.003893 | 396795886.9905 | 6578211.32 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0236 | ORA ZED-Ph 2-Pkgs A&D36
ORA - ZED - ph.02 | 1 | 37 | 12000518.9238 | 12751303.62 | 750784.6962 | 8601492.56 | 12413453.42 | 3811960.86 |  |  |  | 9153293.69 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-10-07 | 408796405.9143 | 10593047.63 | 43987735.96 | 2250000 | 101066779.38 | 10995731.845 | 10995731.845 | 419195.97 | 12000518.9238 | 408796405.9143 | 9153293.69 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0237 | ORA ZED-Ph 2-Pkgs A&D37
ORA - ZED - ph.02 | 1 | 38 | -0.0095238 | 0 | 0.0095238 | 3811960.86 | 0 | -3811960.86 |  |  |  | 3851310.01 | 2024-09-30 | 2024-09-16 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-07 | 408796405.9048 | 15718197.44 | 43987735.96 | 2450000 | 101066779.38 | 11123860.59 | 11123860.59 | 419195.97 | -0.0095238 | 408796405.9048 | 3851310.01 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0238 | ORA ZED-Ph 2-Pkgs A&D38
ORA - ZED - ph.02 | 1 | 39 | 13783192.8762 | 0 | -13783192.8762 | 0 | 0 | 0 |  |  |  | 14526906.83 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-11-09 | 422579598.781 | 19699160.8 | 49807541.52 | 2510000 | 103795295.53 | 11585193.49 | 11585193.49 | 419195.97 | 13783192.8762 | 422579598.781 | 14526906.83 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0239 | ORA ZED-Ph 2-Pkgs A&D39
ORA - ZED - ph.02 | 1 | 40 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-30 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 | [8 empty] | 0 | 0 | 0 | 0 | ORA ZED-Ph 2-Pkgs A&D |  |  |  | ORA - ZED - ph.0240 | ORA ZED-Ph 2-Pkgs A&D40
#N/A
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | 1222080 | 12938311.9 | 11716231.9 | 2832501.18 | 18468978.3325 | 15636477.1525 |  |  |  | 2841415.8 | 2019-11-30 | 2019-12-05 | 2019-12-07 | 7 | 2019-12-14 | 2019-12-11 | 1222080 | 2056962.6 | [5 empty] | 0 | 1222080 | 1222080 | 2841415.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling1 | ESU Ph2-Enabling & Struc1
PH.2-El Sewedy Uni. - Enabling | 1 | 2 | 19989408.99 | 50450016.01 | 30460607.02 | 13318143.89 | 27543185.353 | 14225041.463 |  |  |  | 13446882.5 | 2019-12-31 | 2020-01-02 | 2020-01-02 | 7 | 2020-01-09 | 2020-01-11 | 21211488.99 | 2672643.6 | [5 empty] | 0 | 19989408.99 | 21211488.99 | 13446882.5 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling2 | ESU Ph2-Enabling & Struc2
PH.2-El Sewedy Uni. - Enabling | 1 | 3 | 22171564.66 | 42202241.42 | 20030676.76 | 17089175.5 | 40351874.115 | 23262698.615 |  |  |  | 17089175.5 | 2020-01-31 | 2020-01-30 | 2020-01-30 | 7 | 2020-02-06 | 2020-02-05 | 43383053.65 | 5401152.9 | [5 empty] | 0 | 22171564.66 | 43383053.65 | 17089175.5 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling3 | ESU Ph2-Enabling & Struc3
PH.2-El Sewedy Uni. - Enabling | 1 | 4 | 17471458.95 | 45147950.09 | 27676491.14 | 14773850.81 | 33096273.5075 | 18322422.6975 |  |  |  | 14773850.7 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 7 | 2020-03-14 | 2020-03-16 | 60854512.6 | 8960074.2 | [5 empty] | 0 | 17471458.95 | 60854512.6 | 14773850.7 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling4 | ESU Ph2-Enabling & Struc4
PH.2-El Sewedy Uni. - Enabling | 1 | 5 | 7891719.6 | 61459711.62 | 53567992.02 | 2392694.9 | 66399057.54 | 64006362.64 |  |  |  | 2392694.9 | 2020-03-31 | 2020-03-15 | 2020-03-26 | 7 | 2020-04-02 | 2020-04-09 | 68746232.2 | 6287074.2 | [5 empty] | 0 | 7891719.6 | 68746232.2 | 2392694.9 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling5 | ESU Ph2-Enabling & Struc5
PH.2-El Sewedy Uni. - Enabling | 1 | 6 | 18379179.4 | 47027611.72 | 28648432.32 | 7788095.22 | 16671348.956 | 8883253.736 |  |  |  | 7788095.2 | 2020-04-30 | 2020-04-15 | 2020-04-26 | 7 | 2020-05-03 | 2020-05-06 | 87125411.6 | 2277574.2 | [5 empty] | 0 | 18379179.4 | 87125411.6 | 7788095.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling6 | ESU Ph2-Enabling & Struc6
PH.2-El Sewedy Uni. - Enabling | 1 | 7 | 9076073.5 | 65881799.31 | 56805725.81 | 3548357.43 | 29303962.2315 | 25755604.8015 |  |  |  | 3548357.4 | 2020-05-31 | 2020-05-31 | 2020-06-08 | 7 | 2020-06-15 | 2020-07-11 | 96201485.1 | 0 | [5 empty] | 0 | 9076073.5 | 96201485.1 | 3548357.4 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling7 | ESU Ph2-Enabling & Struc7
PH.2-El Sewedy Uni. - Enabling | 1 | 8 | 2504382.4 | 72131815.88 | 69627433.48 | 1607563.1 | 26734888.538 | 25127325.438 |  |  |  | 1607563.1 | 2020-06-30 | 2020-06-30 | 2020-07-07 | 7 | 2020-07-14 | 2020-07-09 | 98705867.5 | [6 empty] | 0 | 2504382.4 | 98705867.5 | 1607563.1 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling8 | ESU Ph2-Enabling & Struc8
PH.2-El Sewedy Uni. - Enabling | 1 | 9 | 9452002.7 | 85510909.33 | 76058906.63 | 8739144.88 | 20706425.9765 | 11967281.0965 |  |  |  | 8526565.2 | 2020-07-31 | 2020-08-15 | 2020-08-17 | 7 | 2020-08-24 | 2020-08-27 | 108157870.2 | [6 empty] | 0 | 9452002.7 | 108157870.2 | 8526565.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling9 | ESU Ph2-Enabling & Struc9
PH.2-El Sewedy Uni. - Enabling | 1 | 10 | 5068271.5 | 49141746.76 | 44073475.26 | 7703511.41 | 20441591.628 | 12738080.218 |  |  |  | 7703511.3 | 2020-11-30 | 2020-11-15 | 2020-11-22 | 7 | 2020-11-29 | 2020-11-22 | 113226141.7 | [6 empty] | 118504 | 0 | 0 | 0 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Enabling10 | ESU Ph2-Enabling & Struc10
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | 39552087.9 | 12938311.9 | -26613776 | 50636298.9 | 18468978.3325 | -32167320.5675 |  | 15000000 |  | 35636298.9 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 14 | 2020-03-21 | 2020-03-22 | 39552087.9 | 27835856 | [5 empty] | 0 | 39552087.9 | 39552087.9 | 35636298.9 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes1 | ESU Ph2-Enabling & Struc1
PH.2-El Sewedy Uni. - Finishes | 1 | 2 | 33281363.92 | 50450016.01 | 17168652.09 | 26758389.8 | 27543185.353 | 784795.553 |  |  |  | 26758389.8 | 2020-03-31 | 2020-03-31 | 2020-04-05 | 14 | 2020-04-19 | 2020-04-22 | 72833451.82 | 40761852.6 | [5 empty] | 0 | 33281363.92 | 72833451.82 | 26758389.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes2 | ESU Ph2-Enabling & Struc2
PH.2-El Sewedy Uni. - Finishes | 1 | 3 | 24169965.9076 | 42202241.42 | 18032275.5124 | 23262698.8 | 40351874.115 | 17089175.315 |  |  |  | 23262698.8 | 2020-04-30 | 2020-04-30 | 2020-05-06 | 14 | 2020-05-20 | 2020-05-19 | 97003417.7276 | 51226946.1 | [5 empty] | 0 | 24169965.9076 | 97003417.7276 | 23262698.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes3 | ESU Ph2-Enabling & Struc3
PH.2-El Sewedy Uni. - Finishes | 1 | 4 | 24591514.8424 | 45147950.09 | 20556435.2476 | 18322600.95 | 33096273.5075 | 14773672.5575 |  |  |  | 18322601 | 2020-05-31 | 2020-05-31 | 2020-06-14 | 14 | 2020-06-28 | 2020-06-18 | 121594932.57 | 51695436 | [5 empty] | 0 | 24591514.8424 | 121594932.57 | 18322601 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes4 | ESU Ph2-Enabling & Struc4
PH.2-El Sewedy Uni. - Finishes | 1 | 5 | 77007398.3 | 61459711.62 | -15547686.68 | 64006362.98 | 66399057.54 | 2392694.56 |  |  |  | 64006362.8 | 2020-06-30 | 2020-06-30 | 2020-07-08 | 14 | 2020-07-22 | 2020-07-13 | 198602330.87 | 81242431.4 | [5 empty] | 0 | 77007398.3 | 198602330.87 | 64006362.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes5 | ESU Ph2-Enabling & Struc5
PH.2-El Sewedy Uni. - Finishes | 1 | 6 | 22875033.55 | 47027611.72 | 24152578.17 | 8883254.07 | 16671348.956 | 7788094.886 |  |  |  | 8883254.2 | 2020-07-31 | 2020-07-15 | 2020-07-27 | 14 | 2020-08-10 | 2020-07-29 | 221477364.42 | 71736256.5 | [5 empty] | 0 | 22875033.55 | 221477364.42 | 8883254.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes6 | ESU Ph2-Enabling & Struc6
PH.2-El Sewedy Uni. - Finishes | 1 | 7 | 54216090.64 | 65881799.31 | 11665708.67 | 25755604.75 | 29303962.2315 | 3548357.4815 |  |  |  | 30755604.9 | 2020-08-31 | 2020-08-15 | 2020-08-17 | 14 | 2020-08-31 | 2020-08-26 | 275693455.06 | 65901640.4 | [5 empty] | 0 | 54216090.64 | 275693455.06 | 30755604.9 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes7 | ESU Ph2-Enabling & Struc7
PH.2-El Sewedy Uni. - Finishes | 1 | 8 | 61814968.03 | 72131815.88 | 10316847.85 | 25127325.53 | 26734888.538 | 1607563.008 |  |  |  | 30127325.7 | 2020-08-31 | 2020-08-31 | 2020-09-10 | 14 | 2020-09-24 | 2020-09-17 | 337508423.09 | 51289431.9 | [5 empty] | 0 | 61814968.03 | 337508423.09 | 30127325.7 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes8 | ESU Ph2-Enabling & Struc8
PH.2-El Sewedy Uni. - Finishes | 1 | 9 | 56169721.37 | 85510909.33 | 29341187.96 | 20493846.09 | 20706425.9765 | 212579.8865 |  |  |  | 20493846 | 2020-09-30 | 2020-09-15 | 2020-10-18 | 14 | 2020-11-01 | 2020-10-20 | 393678144.46 | 22011525 | [5 empty] | 0 | 56169721.37 | 393678144.46 | 20493846 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes9 | ESU Ph2-Enabling & Struc9
PH.2-El Sewedy Uni. - Finishes | 1 | 10 | 33204826.41 | 49141746.76 | 15936920.35 | 9765894.8 | 20441591.628 | 10675696.828 |  |  |  | 9765894.8 | 2020-10-31 | 2020-10-25 | 2020-11-10 | 14 | 2020-11-24 | 2020-11-19 | 426882970.87 | 8412160.7 | [5 empty] | 0 | 33204826.41 | 426882970.87 | 9765894.8 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes10 | ESU Ph2-Enabling & Struc10
PH.2-El Sewedy Uni. - Finishes | 1 | 11 | 20698550.4 | 24045616.1 | 3347065.7 | 13851401.63 | 13851401.63 | 0 |  |  |  | 13851401.2 | 2020-11-30 | 2020-12-01 | 2020-12-15 | 14 | 2020-12-29 | 2020-12-21 | 447581521.27 | 6756406.26 | [5 empty] | 0 | 20698550.4 | 447581521.27 | 13851401.2 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes11 | ESU Ph2-Enabling & Struc11
PH.2-El Sewedy Uni. - Finishes | 1 | 12 | 33191485.02 | 38061417.81 | 4869932.79 | 23340124.9 | 23340124.2605 | -0.6395 |  |  |  | 23340124.9 | 2021-01-31 | 2021-02-10 | 2021-02-14 | 14 | 2021-02-28 | 2021-03-22 | 480773006.29 | [6 empty] | 0 | 36099063.7776 | 483680585.0476 | 26122387 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes12 | ESU Ph2-Enabling & Struc12
PH.2-El Sewedy Uni. - Finishes | 1 | 13 | 13891238 | 0 | -13891238 | 15069000 | 0 | -15069000 |  |  |  | 19693398.5 | 2021-05-31 | 2021-06-09 | 2022-03-28 | 14 | 2022-04-11 | 2022-04-27 | 494664244.29 |  |  |  |  | 12984936.4125 | 12984936.4125 | 0 | 13891238 | 494664244.29 | 19693398.5 | ESU Ph2-Enabling & Struc |  |  |  | PH.2-El Sewedy Uni. - Finishes13 | ESU Ph2-Enabling & Struc13
PI Parks - ELSEWEDY | 1 | 1 | 2947938.09 | 0 | -2947938.09 | 3779007.23 | 0 | -3779007.23 |  |  |  | 3779007.23 | 2017-09-30 | 2017-10-03 | 2017-10-18 | 15 | 2017-11-16 | 2017-11-04 | 2947938.09 | 2165254 | [5 empty] | 350000 | 3990886.7187 | 3990886.7187 | 5549711.3149 | 0 |  |  |  | PI Parks - ELSEWEDY1 | 01
PI Parks - ELSEWEDY | 1 | 2 | 4598153.29 | 0 | -4598153.29 | 3366014.15 | 0 | -3366014.15 |  |  |  | 3366014.15 | 2017-10-31 | 2017-11-04 | 2017-11-06 | 15 | 2017-12-09 | 2017-11-28 | 7546090.84 | 1128937.5 | [5 empty] | 360362.87 | 4642464.2724 | 7590402.3632 | 4153538.7944 | 0 |  |  |  | PI Parks - ELSEWEDY2 | 02
PI Parks - ELSEWEDY | 1 | 3 | 1603218.21 | 0 | -1603218.21 | 823701.85 | 0 | -823701.85 |  |  |  | 823701.84 | 2017-11-30 | 2017-12-04 | 2017-12-04 | 15 | 2018-01-09 | 2017-12-25 | 9149309.06 | 1055385.4 | [5 empty] | 360362.87 | 1837652.48 | 9383809.13 | 1754857.27 | 0 |  |  |  | PI Parks - ELSEWEDY3 | 03
PI Parks - ELSEWEDY | 1 | 4 |  | 0 | 0 | 2572231.81 | 0 | -2572231.81 |  |  |  | 2572231.81 | 2017-12-31 | 2017-12-31 | 2018-01-04 | 15 | 2018-02-17 | 2018-02-15 | 12280064.67 | 862309.875 | [5 empty] | 711378.1905 | 3758163.8696 | 12907472.9296 | 3155027.6241 | 0 |  |  |  | PI Parks - ELSEWEDY4 | 04
PI Parks - ELSEWEDY | 1 | 5 | 2043145.23 | 0 | -2043145.23 | 1175600.49 | 0 | -1175600.49 |  |  |  | 1175600.49 | 2018-01-31 | 2018-02-07 | 2018-02-07 | 15 | 2018-03-28 | 2018-04-05 | 14323209.9 | 439890.2 | [5 empty] | 110286.54 | 1927670.8 | 14835143.73 | 1692874.42 | 0 |  |  |  | PI Parks - ELSEWEDY5 | 05
PI Parks - ELSEWEDY | 1 | 6 | 662608.11 | 0 | -662608.11 | 689110.93 | 0 | -689110.93 |  |  |  | 689113.69 | 2018-02-28 | 2018-03-10 | 2018-03-11 | 15 | 2018-04-28 | 2018-04-15 | 14985818.01 | 602282.21 | [5 empty] | 0 | 694638.63 | 15017848.53 | 306624.33 | 0 |  |  |  | PI Parks - ELSEWEDY6 | 06
PI Parks - ELSEWEDY | 1 | 7 | 667972.21 | 0 | -667972.21 | 1209313.47 | 0 | -1209313.47 |  |  |  | 1938615.93 | 2018-03-31 | 2018-04-10 | 2018-04-16 | 15 | 2018-05-08 | 2018-04-21 | 15685820.74 | 1491568.3 | [5 empty] | 0 | 667972.21 | 15685820.74 | 1938615.93 | 0 |  |  |  | PI Parks - ELSEWEDY7 | 07
PI Parks - ELSEWEDY | 1 | 8 | 1859636.86 | 0 | -1859636.86 | 1492654.2 | 0 | -1492654.2 |  |  |  | 1633991.6379 | 2018-04-30 | 2018-05-09 | 2018-05-09 | 15 | 2018-06-03 | 2018-06-02 | 17545457.6 | 1274527.689 | [5 empty] | 0 | 1892096.0888 | 17577916.8288 | 1633991.6379 | 0 |  |  |  | PI Parks - ELSEWEDY8 | 08
PI Parks - ELSEWEDY | 1 | 9 | 1491159.5592 | 0 | -1491159.5592 | 1471457.2 | 0 | -1471457.2 |  |  |  | 1607545.8276 | 2018-05-31 | 2018-06-09 | 2018-06-09 | 15 | 2018-06-29 | 2018-06-12 | 19036617.1592 | 1586317.356 | [5 empty] | 0 | 1491159.5592 | 19036617.1592 | 1607545.8276 | 0 |  |  |  | PI Parks - ELSEWEDY9 | 09
PI Parks - ELSEWEDY | 1 | 10 | 3200065.7108 | 0 | -3200065.7108 | 2470019.34 | 0 | -2470019.34 |  |  |  | 2470019.34 | 2018-06-30 | 2018-07-08 | 2018-07-10 | 15 | 2018-08-08 | 2018-08-01 | 22236682.87 | 1486479.93 | [5 empty] | 115532.14 | 4758616.5674 | 23795233.7266 | 3824599.4146 | 0 |  |  |  | PI Parks - ELSEWEDY10 | 010
PI Parks - ELSEWEDY | 1 | 11 | 890276.26 | 0 | -890276.26 | 945860.23 | 0 | -945860.23 |  |  |  | 945860.23 | 2018-07-31 | 2018-08-02 | 2018-08-07 | 15 | 2018-08-25 | 2018-09-13 | 23126959.13 | 1734570.528 | [5 empty] | 125532.14 | 891495.1766 | 23128178.0466 | 442152.4951 | 0 |  |  |  | PI Parks - ELSEWEDY11 | 011
PI Parks - ELSEWEDY | 1 | 12 | 1804540.7798 | 0 | -1804540.7798 | 1347803.37 | 0 | -1347803.37 |  |  |  | 1530660.1341 | 2018-08-31 | 2018-09-06 | 2018-09-08 | 15 | 2018-10-13 | 2018-09-26 | 24932718.8264 | 1713142.271 | [5 empty] | 0 | 1804540.7798 | 24932718.8264 | 1530660.1341 | 0 |  |  |  | PI Parks - ELSEWEDY12 | 012
PI Parks - ELSEWEDY | 1 | 13 | 1076504.1197 | 0 | -1076504.1197 | 719804.13 | 0 | -719804.13 |  |  |  | 716605.5327 | 2018-09-30 | 2018-10-04 | 2018-10-04 | 15 | 2018-10-27 | 2018-10-10 | 26009222.9461 | 1579309.545 | [5 empty] | 0 | 1076504.1197 | 26009222.9461 | 716605.5327 | 0 |  |  |  | PI Parks - ELSEWEDY13 | 013
PI Parks - ELSEWEDY | 1 | 14 | 1188716.2339 | 0 | -1188716.2339 | 775351.46 | 0 | -775351.46 |  |  |  | 775351.46 | 2018-10-31 | 2018-11-05 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 27197939.18 | 1430574.85 | [5 empty] | 194651.72 | 2476006.3139 | 28485229.26 | 1986968.45 | 0 |  |  |  | PI Parks - ELSEWEDY14 | 014
PI Parks - ELSEWEDY | 1 | 15 | 6486957.62 | 0 | -6486957.62 | 4484634.14 | 0 | -4484634.14 |  |  |  | 4484634.17 | 2018-11-30 | 2018-12-06 | 2018-12-06 | 15 | 2019-01-01 | 2018-12-26 | 33684896.8 | 1125214.43 | [5 empty] | 209651.72 | 7576900.68 | 34774839.86 | 5773335.65 | 0 |  |  |  | PI Parks - ELSEWEDY15 | 015
PI Parks - ELSEWEDY | 1 | 16 | 4932880.46 | 0 | -4932880.46 | 4125986.43 | 0 | -4125986.43 |  |  |  | 4125986.43 | 2018-12-31 | 2019-01-06 | 2019-01-06 | 15 | 2019-01-31 | 2019-01-27 | 38617777.26 | 889716.88 | [5 empty] | 245586.01 | 6344223.5299 | 40029120.3299 | 5768808.1936 | 0 |  |  |  | PI Parks - ELSEWEDY16 | 016
PI Parks - ELSEWEDY | 1 | 17 | 1718123.55 | 0 | -1718123.55 | 1375431.38 | 0 | -1375431.38 |  |  |  | 1375431.38 | 2019-01-31 | 2019-02-05 | 2019-02-07 | 15 | 2019-03-05 | 2019-03-13 | 40335900.81 | 584649.66 | [5 empty] | 261703.2 | 3393993.12 | 42011770.38 | 3296251.57 | 0 |  |  |  | PI Parks - ELSEWEDY17 | 017
PI Parks - ELSEWEDY | 1 | 18 | 4308748.67 | 0 | -4308748.67 | 3699864.67 | 0 | -3699864.67 |  |  |  | 3699864.67 | 2019-02-28 | 2019-03-05 | 2019-03-06 | 15 | 2019-04-03 | 2019-03-27 | 44644649.48 | 439815.151 | [5 empty] | 261703.2 | 4573274.545 | 46585044.925 | 5638741.9194 | 0 |  |  |  | PI Parks - ELSEWEDY18 | 018
PI Parks - ELSEWEDY | 1 | 19 | 2652468.02 | 0 | -2652468.02 | 2311261.81 | 0 | -2311261.81 |  |  |  | 2311261.81 | 2019-03-31 | 2019-04-06 | 2019-04-06 | 15 | 2019-05-04 | 2019-05-14 | 47297117.5 | 171933.6095 | [5 empty] | 276703.2 | 4823264.9186 | 49467914.3986 | 4754946.3629 | 0 |  |  |  | PI Parks - ELSEWEDY19 | 019
PI Parks - ELSEWEDY | 1 | 20 | 4018450.9279 | 0 | -4018450.9279 | 1466574.4 | 0 | -1466574.4 |  |  |  | 1816746.614 | 2019-04-30 | 2019-05-05 | 2019-05-07 | 15 | 2019-06-05 | 2019-05-19 | 51315568.4279 | 161583.8345 | [5 empty] | 0 | 4018450.9279 | 51315568.4279 | 1816746.614 | 0 |  |  |  | PI Parks - ELSEWEDY20 | 020
PI Parks - ELSEWEDY | 1 | 21 | 598299.7921 | 0 | -598299.7921 | 5333565.74 | 0 | -5333565.74 |  |  |  | 5879272.6391 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 51913868.22 | 179052.64 | [5 empty] | 0 | 598299.7921 | 51913868.22 | 5879272.6391 | 0 |  |  |  | PI Parks - ELSEWEDY21 | 021
PI Parks - MEP | 1 | 1 | 4100153.37 | 0 | -4100153.37 | 7818631.64 | 0 | -7818631.64 |  |  |  | 7818631.64 | 2018-09-30 | 2018-10-04 | 2018-09-27 | 15 | 2018-10-27 | 2018-10-10 | 4100153.37 | 4989525.8132 | [5 empty] | 0 | 4100153.37 | 4100153.37 | 7818631.64 | 0 |  |  |  | PI Parks - MEP1 | 01
PI Parks - MEP | 1 | 2 | 3824663.6 | 0 | -3824663.6 | 3907009.94 | 0 | -3907009.94 |  |  |  | 3907009.94 | 2018-10-31 | 2018-11-02 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 7924816.97 | 5871509.91 | [5 empty] | 0 | 3824663.6 | 7924816.97 | 3978690.02 | 0 |  |  |  | PI Parks - MEP2 | 02
PI Parks - MEP | 1 | 3 | 2526634.86 | 0 | -2526634.86 | 3921714.73 | 0 | -3921714.73 |  |  |  | 3921714.73 | 2018-11-30 | 2018-12-10 | 2018-12-03 | 15 | 2019-01-01 | 2018-12-26 | 10451451.83 | 8435854.55 | [5 empty] | 0 | 4229682.9 | 12154499.87 | 4042223.64 | 0 |  |  |  | PI Parks - MEP3 | 03
PI Parks - MEP | 1 | 4 | 13292686.78 | 0 | -13292686.78 | 3366511.48 | 0 | -3366511.48 |  |  |  | 3514249.7617 | 2018-12-31 | 2019-01-05 | 2019-01-05 | 15 | 2019-01-31 | 2019-01-14 | 23744138.61 | 6341086.69 | [5 empty] | 0 | 13292686.78 | 23744138.61 | 3514249.7617 | 0 |  |  |  | PI Parks - MEP4 | 04
PI Parks - MEP | 1 | 5 | 8084326 | 0 | -8084326 | 6350059.5 | 0 | -6350059.5 |  |  |  | 6350059.5 | 2019-01-31 | 2019-02-05 | 2019-02-05 | 15 | 2019-03-05 | 2019-03-13 | 31828464.61 | 8184608.01 | [5 empty] | 0 | 7765619.63 | 31509758.24 | 6241537.12 | 0 |  |  |  | PI Parks - MEP5 | 05
PI Parks - MEP | 1 | 6 | 3232894.78 | 0 | -3232894.78 | 919139.23 | 0 | -919139.23 |  |  |  | 919139.23 | 2019-02-28 | 2019-03-05 | 2019-03-05 | 15 | 2019-04-03 | 2019-03-26 | 35061359.39 | 6744285.61 | [5 empty] | 0 | 3555303.77 | 35065062.01 | 2455515.29 | 0 |  |  |  | PI Parks - MEP6 | 06
PI Parks - MEP | 1 | 7 | 4908164.7341 | 0 | -4908164.7341 | 2661364.08 | 0 | -2661364.08 |  |  |  | 2661364.08 | 2019-03-31 | 2019-04-01 | 2019-04-04 | 15 | 2019-05-04 | 2019-05-14 | 39969524.1241 | 4404706.2941 | [5 empty] | 0 | 4908164.7774 | 39969524.1674 | 4844170.7079 | 0 |  |  |  | PI Parks - MEP7 | 07
PI Parks - MEP | 1 | 8 | 2655162.8183 | 0 | -2655162.8183 | 1478131.5 | 0 | -1478131.5 |  |  |  | 1686090.7908 | 2019-04-30 | 2019-05-05 | 2019-05-06 | 15 | 2019-06-05 | 2019-05-19 | 42624686.9424 | 3262993.985 | [5 empty] | 0 | 2655162.8183 | 42624686.9424 | 1686090.7908 | 0 |  |  |  | PI Parks - MEP8 | 08
PI Parks - MEP | 1 | 9 | 3596767.6976 | 0 | -3596767.6976 | 4813799.42 | 0 | -4813799.42 |  |  |  | 5081340.66 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 46221454.64 | 42070.75 | [5 empty] | 0 | 3596767.6976 | 46221454.64 | 5081340.66 | 0 |  |  |  | PI Parks - MEP9 | 09
#N/A
PK #107 | 1 | 8 |  | 0 | 0 | 3005745.85 | 0 | -3005745.85 |  |  |  | 3005745.85 | 2017-09-30 | 2017-09-28 | 2017-09-28 | 30 | 2017-10-28 | 2017-10-15 | 36182581.41 | 1713544.64 | [5 empty] | 238645.64 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #1078 | EMAAR-PKG#107-MARASSI8
PK #107 | 1 | 9 | 1856322.11 | 0 | -1856322.11 | 1418090.5 | 0 | -1418090.5 |  |  |  | 1418090.5 | 2017-10-31 | 2017-10-31 | 2017-11-01 | 30 | 2017-12-01 | 2017-11-28 | 38038903.52 | 1713544.64 | [5 empty] | 253179.82 | 1856322.11 | 38038903.52 | 1418090.5 | EMAAR-PKG#107-MARASSI |  |  |  | PK #1079 | EMAAR-PKG#107-MARASSI9
PK #107 | 1 | 10 | 2025124.41 | 0 | -2025124.41 | 1453205.38 | 0 | -1453205.38 |  |  |  | 1453205.39 | 2017-11-30 | 2017-11-28 | 2017-11-28 | 30 | 2017-12-28 | 2017-12-27 | 40064027.93 | 1875947.9 | [5 empty] | 264974.51 | 2025124.41 | 40064027.93 | 1453205.39 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10710 | EMAAR-PKG#107-MARASSI10
PK #107 | 1 | 11 | 3591068.23 | 0 | -3591068.23 | 2354508.52 | 0 | -2354508.52 |  |  |  | 2604921.36 | 2017-12-31 | 2017-12-25 | 2017-12-27 | 30 | 2018-01-26 | 2018-01-15 | 43655096.16 | 1188936.54 | [5 empty] | 282897.2 | 3591068.23 | 43655096.16 | 2604921.36 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10711 | EMAAR-PKG#107-MARASSI11
PK #107 | 1 | 12 | 5883258.75 | 0 | -5883258.75 | 4193998 | 0 | -4193998 |  |  |  | 5012769.61 | 2018-01-31 | 2018-01-25 | 2018-01-25 | 30 | 2018-02-24 | 2018-02-26 | 49538354.91 | 366842.14 | [5 empty] | 315029.17 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10712 | EMAAR-PKG#107-MARASSI12
PK #107 | 1 | 13 | 2719252.37 | 0 | -2719252.37 | 3281572.56 | 0 | -3281572.56 |  |  |  | 2462800.95 | 2018-02-28 | 2018-03-10 | 2018-03-12 | 30 | 2018-04-11 | 2018-04-04 | 52257607.28 | 323504.14 | [5 empty] | 369537.93 | 2719252.37 | 52257607.28 | 2462800.95 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10713 | EMAAR-PKG#107-MARASSI13
PK #107 | 1 | 14 | 1449945.81 | 1449945.92 | 0.11 | 166316.41 | 2534475.77 | 2368159.36 |  |  |  | 166316.41 | 2018-03-31 | 2018-04-10 | 2018-04-11 | 30 | 2018-05-11 | 2018-04-29 | 53707553.09 | 0 | [5 empty] | 1275350.71 | 1449945.81 | 53707553.09 | 166316.41 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10714 | EMAAR-PKG#107-MARASSI14
PK #107 | 1 | 15 | 0 | 0 | 0 | 1406606.27 | 0 | -1406606.27 |  |  |  | 1406606.27 | 2018-04-30 | 2018-05-05 | 2018-05-06 | 30 | 2018-06-05 | 2018-05-23 | 53707553.09 | 0 | [5 empty] | 1275350.71 | 0 | 0 | 1406606.27 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10715 | EMAAR-PKG#107-MARASSI15
PK #107 | 1 | 16 | 0.01 | 0 | -0.01 | 131256.74 | 0 | -131256.74 |  |  |  | 131256.74 | 2018-05-31 | 2018-06-01 | 2018-05-30 | 30 | 2018-06-29 | 2018-06-28 | 53707553.1 | 0 | [5 empty] | 1292122.78 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10716 | EMAAR-PKG#107-MARASSI16
PK #107 | 1 | 17 | 0 | 0 | 0 | 763627.7 | 0 | -763627.7 |  |  |  | 763627.7 | 2018-09-30 | 2018-09-25 | 2018-09-25 | 30 | 2018-10-25 | 2018-10-21 | 53707553.1 | 0 | [5 empty] | 496495.08 | 0 | 0 | 763627.7 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10717 | EMAAR-PKG#107-MARASSI17
PK #107 | 1 | 18 | 989048.54 | 1069591.54 | 80543 | 1341459.14 | 1054265.617 | -287193.523 |  |  |  | 940988.93 | 2019-04-30 | 2019-04-25 | 2019-06-13 | 30 | 2019-07-13 | 2019-07-30 | 54696601.64 | [6 empty] | 1898258.43 | 0 | 0 | 0 | EMAAR-PKG#107-MARASSI |  |  |  | PK #10718 | EMAAR-PKG#107-MARASSI18
PK #117 | 1 | 1 | 4130129.14 | 0 | -4130129.14 | 4130129.12 | 0 | -4130129.12 |  |  |  | 4130129.14 | 2017-12-31 | 2018-01-01 | 2018-01-18 | 30 | 2018-02-17 | 2018-02-13 | 4130129.14 | [6 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG117- MARASSI |  |  |  | PK #1171 | EMAAR-PKG117- MARASSI1
PK #117 | 1 | 2 | 7803090.39 | 0 | -7803090.39 | 6455421.01 | 0 | -6455421.01 |  |  |  | 6455421.01 | 2018-01-31 | 2018-02-15 | 2018-02-15 | 30 | 2018-03-17 | 2018-03-07 | 7803090.39 | 0 | [5 empty] | 60159.47 | 7803090.35 | 7803090.35 | 6466420.97 | EMAAR-PKG117- MARASSI |  |  |  | PK #1172 | EMAAR-PKG117- MARASSI2
PK #117 | 1 | 3 | 4332593.51 | 0 | -4332593.51 | 4502026.51 | 0 | -4502026.51 |  |  |  | 4502026.52 | 2018-02-28 | 2018-03-05 | 2018-03-07 | 30 | 2018-04-06 | 2018-03-29 | 12135683.86 | 1176749.78 | [5 empty] | 106021.19 | 4332593.51 | 12135683.86 | 4502026.52 | EMAAR-PKG117- MARASSI |  |  |  | PK #1173 | EMAAR-PKG117- MARASSI3
PK #117 | 1 | 4 | 4131277.1774 | 0 | -4131277.1774 | 3740180.08 | 0 | -3740180.08 |  |  |  | 3740180.271 | 2018-03-31 | 2018-04-01 | 2018-04-01 | 30 | 2018-05-01 | 2018-04-19 | 16266961.0374 | 1578005.405 | [5 empty] | 134455.7716 | 4131277.1774 | 16266961.0374 | 3740180.271 | EMAAR-PKG117- MARASSI |  |  |  | PK #1174 | EMAAR-PKG117- MARASSI4
PK #117 | 1 | 5 | 6909334.9826 | 6909335.09 | 0.10744 | 4762507.56 | 5093815.29 | 331307.73 |  |  |  | 4762507.55 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 30 | 2018-05-30 | 2018-05-22 | 23176296.02 | 364792.48 | [5 empty] | 171850.1 | 6909334.9826 | 23176296.02 | 4762507.55 | EMAAR-PKG117- MARASSI |  |  |  | PK #1175 | EMAAR-PKG117- MARASSI5
PK #117 | 1 | 6 | 6677875.24 | 6677875.14 | -0.1 | 5347404.79 | 5722280.397 | 374875.607 |  |  |  | 5347404.79 | 2018-05-31 | 2018-06-04 | 2018-06-05 | 30 | 2018-07-05 | 2018-07-12 | 29854171.26 | 229256.92 | [5 empty] | 302952.2979 | 6651333.71 | 29827629.73 | 5347404.79 | EMAAR-PKG117- MARASSI |  |  |  | PK #1176 | EMAAR-PKG117- MARASSI6
PK #117 | 1 | 7 | -0.01 | 0 | 0.01 | 118938.86 | 0 | -118938.86 |  |  |  | 119713.18 | 2018-06-30 | 2018-06-15 | 2018-06-25 | 30 | 2018-07-25 | 2018-12-30 | 29854171.25 | 384118.8 | [5 empty] | 115837.505 | -0.01 | 29854171.25 | 119713.18 | EMAAR-PKG117- MARASSI |  |  |  | PK #1177 | EMAAR-PKG117- MARASSI7
PK #117 | 1 | 8 | 4511257.49 | 0 | -4511257.49 | 3896343.98 | 0 | -3896343.98 |  |  |  | 3896343.98 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 30 | 2019-01-04 | 2018-12-30 | 34365428.74 | 79445.62 | [5 empty] | 575019.525 | 4511257.49 | 34365428.74 | 3896343.98 | EMAAR-PKG117- MARASSI |  |  |  | PK #1178 | EMAAR-PKG117- MARASSI8
PK #117 | 1 | 9 | 3153415.09 | 3150407.65 | -3007.44 | 2578109.73 | 2971025.94 | 392916.21 |  |  |  | 2578109.66 | 2018-12-31 | 2018-12-30 | 2018-12-29 | 30 | 2019-01-28 | 2019-01-30 | 37518843.83 | 48842.25 | [5 empty] | 599014.4 | 3153415.09 | 37518843.83 | 2578109.66 | EMAAR-PKG117- MARASSI |  |  |  | PK #1179 | EMAAR-PKG117- MARASSI9
PK #117 | 1 | 10 | 1068867.24 | 2201208.6 | 1132341.36 | 882296.11 | 1794005.32 | 911709.21 |  |  |  | 882296.18 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 30 | 2019-03-04 | 2019-02-28 | 38587711.07 | 48842.25 | [5 empty] | 653139.594 | 992195.9681 | 38511039.7981 | 147972.1048 | EMAAR-PKG117- MARASSI |  |  |  | PK #11710 | EMAAR-PKG117- MARASSI10
PK #117 | 1 | 11 | 1134851.86 | 0 | -1134851.86 | 809762.24 | 0 | -809762.24 |  |  |  | 810342.08 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-30 | 39722562.93 | [6 empty] | 737679.72 | 0 | 0 | 0 | EMAAR-PKG117- MARASSI |  |  |  | PK #11711 | EMAAR-PKG117- MARASSI11
PK #117 | 1 | 12 | 2921413.42 | 2921423.41 | 9.99 | 3376927.91 | 3430971.3805 | 54043.4705 |  |  |  | 3376348.1 | 2019-08-31 | 2019-08-26 | 2019-08-26 | 30 | 2019-09-25 | 2019-09-25 | 42643976.35 | 0 | [5 empty] | 1681581.22 | 2921413.42 | 42643976.35 | 3376348.1 | EMAAR-PKG117- MARASSI |  |  |  | PK #11712 | EMAAR-PKG117- MARASSI12
PK #117 | 1 | 13 | 2611652.87 | 2573072.88 | -38579.99 | 3145907.11 | 3439963.734 | 294056.624 |  |  |  | 3145779.21 | 2019-10-31 | 2019-10-30 | 2019-10-29 | 30 | 2019-11-28 | 2019-11-12 | 45255629.22 | 0 | [5 empty] | 975332.15 | 2611652.87 | 45255629.22 | 3145779.21 | EMAAR-PKG117- MARASSI |  |  |  | PK #11713 | EMAAR-PKG117- MARASSI13
PK #117 | 1 | 14 | 1659370.81 | 0 | -1659370.81 | 2483342.5 | 0 | -2483342.5 |  |  |  | 2238761.46 | 2020-04-30 | 2020-04-14 | 2020-06-24 | 30 | 2020-07-24 | 2020-09-27 | 46915000.03 | [6 empty] | 943850.91 | 1169069.6666 | 46915000.03 | 2238761.46 | EMAAR-PKG117- MARASSI |  |  |  | PK #11714 | EMAAR-PKG117- MARASSI14
PK#22 | 1 | 37 |  | 0 | 0 | 780036 | 0 | -780036 |  |  |  | 471641.26 | 2019-02-28 | 2019-02-27 | 2019-07-31 | 30 | 2019-08-30 | 2019-08-07 | 35147992.22 | [6 empty] | 990333.95 | 0 | 0 | 0 | EMAAR-PKG#22-MARASSI |  |  |  | PK#2237 | EMAAR-PKG#22-MARASSI37
PK#32 | 1 | 30 |  | 0 | 0 | 900093.35 | 0 | -900093.35 |  |  |  |  | 2017-06-30 | 2017-06-05 | 2022-03-14 | 30 | 2022-04-13 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PK#3230 | 030
PKG#101 | 1 | 1 | 1738465.6667 | 1738465.67 | 0.0033333 | 9752735.82 | 1029594.8135 | -8723141.0065 | 8723141 |  |  | 1029594.82 | 2019-01-31 | 2019-01-31 | 2019-02-03 | 40 | 2019-03-15 | 2019-02-17 | 1738465.6667 | [6 empty] | 48253.89 | 1738465.6667 | 1738465.6667 | 1124562.5468 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1011 | EMAAR-PKG# 101-UPTOWN1
PKG#101 | 1 | 2 | 1610908.8476 | 0 | -1610908.8476 | 2222206.65 | 0 | -2222206.65 |  |  |  | 2222206.65 | 2019-02-28 | 2019-02-28 | 2019-03-05 | 40 | 2019-04-14 | 2019-03-19 | 3349374.5143 | 2240156.84 | [5 empty] | 147570 | 1610908.8476 | 3349374.5143 | 2222206.65 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1012 | EMAAR-PKG# 101-UPTOWN2
PKG#101 | 1 | 3 | 4030400.2476 | 3744391.54 | -286008.7076 | 2246109.51 | 2222206.627 | -23902.883 |  |  |  | 2246109.51 | 2019-03-31 | 2019-04-11 | 2019-04-14 | 40 | 2019-05-24 | 2019-05-05 | 7379774.7619 | 1904790.84 | [5 empty] | 202283 | 4030395.5429 | 7379770.0571 | 2379437.34 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1013 | EMAAR-PKG# 101-UPTOWN3
PKG#101 | 1 | 4 | 4428897.7238 | 1896917.55 | -2531980.1738 | 2512749.68 | 2246109.51 | -266640.17 |  |  |  | 2512749.68 | 2019-04-30 | 2019-05-15 | 2019-05-20 | 40 | 2019-06-29 | 2019-05-29 | 11808672.4857 | 1592100.01 | [5 empty] | 250813.43 | 4428897.7238 | 11808672.4857 | 2512749.68 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1014 | EMAAR-PKG# 101-UPTOWN4
PKG#101 | 1 | 5 | 2224631.7143 | 4428897.72 | 2204266.0057 | 2051541.96 | 2512749.703 | 461207.743 |  |  |  | 2051541.96 | 2019-06-30 | 2019-06-30 | 2019-07-01 | 40 | 2019-08-10 | 2019-07-24 | 14033304.2 | 2808836.8 | [5 empty] | 296997.23 | 2224631.7143 | 14033304.2 | 2051541.96 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1015 | EMAAR-PKG# 101-UPTOWN5
PKG#101 | 1 | 6 | 3491880.8381 | 2226073.87 | -1265806.9681 | 1988552.05 | 2051541.97 | 62989.92 |  |  |  | 1988552.05 | 2019-07-31 | 2019-08-05 | 2019-08-07 | 40 | 2019-09-16 | 2019-08-28 | 17525185.0381 | 2620517.54 | [5 empty] | 362213.26 | 3491880.8381 | 17525185.0381 | 1988552.05 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1016 | EMAAR-PKG# 101-UPTOWN6
PKG#101 | 1 | 7 | 3123640.9905 | 3491880.84 | 368239.8495 | 1824097.57 | 1988552.05 | 164454.48 |  |  |  | 1824097.57 | 2019-08-31 | 2019-09-10 | 2019-09-15 | 40 | 2019-10-25 | 2019-09-26 | 20648826.0286 | 2373278.98 | [5 empty] | 374469.49 | 3120848.981 | 20646034.019 | 1794285.02 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1017 | EMAAR-PKG# 101-UPTOWN7
PKG#101 | 1 | 8 | 4704887.4039 | 3123640.99 | -1581246.4139 | 2104893.84 | 1824097.56 | -280796.28 |  |  |  | 2104893.8329 | 2019-09-30 | 2019-10-15 | 2019-10-17 | 40 | 2019-11-26 | 2019-11-05 | 25353713.4325 | 1078135.3004 | [5 empty] | 421854.3373 | 4703530.9524 | 25352356.981 | 2127121.14 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1018 | EMAAR-PKG# 101-UPTOWN8
PKG#101 | 1 | 9 | 3179849.8818 | 4704887.4 | 1525037.5182 | 1424816.56 | 2104893.84 | 680077.28 |  |  |  | 1424816.56 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 40 | 2019-12-27 | 2019-12-03 | 28533563.3143 | 297444.34 | [5 empty] | 505055.04 | 3179849.8818 | 28533563.3143 | 1424816.56 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#1019 | EMAAR-PKG# 101-UPTOWN9
PKG#101 | 1 | 10 | 3100706.8857 | 0 | -3100706.8857 | 1976416.89 | 0 | -1976416.89 |  |  |  | 1976416.89 | 2019-11-30 | 2019-11-15 | 2019-12-18 | 40 | 2020-01-27 | 2020-01-06 | 31634270.2 | [6 empty] | 515167.31 | 3111780.0857 | 31645343.4 | 1948071.2 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10110 | EMAAR-PKG# 101-UPTOWN10
PKG#101 | 1 | 11 | 361420.4 | 3104755.66 | 2743335.26 | 1709961.04 | 1976416.883 | 266455.843 |  |  |  | 1709961.04 | 2020-01-31 | 2020-01-30 | 2020-02-08 | 40 | 2020-03-19 | 2020-02-27 | 31995690.6 | 2008107.01 | [5 empty] | 646968.58 | 382240.2571 | 32016510.4571 | 2026574.82 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10111 | EMAAR-PKG# 101-UPTOWN11
PKG#101 | 1 | 12 | 2584477.6667 | 361420.4 | -2223057.2667 | 1146998.21 | 1829340.96 | 682342.75 |  |  |  | 1146998.22 | 2020-02-29 | 2020-03-23 | 2020-03-24 | 40 | 2020-05-03 | 2020-04-08 | 34580168.2667 | 1288346.31 | [5 empty] | 677344.97 | 2584477.6667 | 34580168.2667 | 1146998.22 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10112 | EMAAR-PKG# 101-UPTOWN12
PKG#101 | 1 | 13 | 2595711.6476 | 2584477.67 | -11233.9776 | 1343055.6 | 1246695.2535 | -96360.3465 |  |  |  | 1407211.96 | 2020-03-31 | 2020-04-23 | 2020-04-23 | 40 | 2020-06-02 | 2020-05-04 | 37175879.9143 | 1005027.63 | [5 empty] | 712181.29 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10113 | EMAAR-PKG# 101-UPTOWN13
PKG#101 | 1 | 14 | 4659441.8571 | 2596223.72 | -2063218.1371 | 191421.72 | 1459609.626 | 1268187.906 |  |  |  | 191421.72 | 2020-06-30 | 2020-06-30 | 2020-07-12 | 40 | 2020-08-21 | 2020-09-09 | 41835321.7714 | [6 empty] | 763224.31 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10114 | EMAAR-PKG# 101-UPTOWN14
PKG#101 | 1 | 15 | 181866.4762 | 4658928.78 | 4477062.3038 | 303853.8 | 1268535.189 | 964681.389 |  |  |  | 303853.8 | 2020-09-30 | 2020-08-12 | 2020-12-09 | 40 | 2021-01-18 | 2021-01-20 | 42017188.2476 | [6 empty] | 174031.17 | 440607.3155 | 42275929.0869 | 1392185.4448 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10115 | EMAAR-PKG# 101-UPTOWN15
PKG#101 | 1 | 16 | 0.001 | 181866.48 | 181866.479 | 866491 | 1873125.774 | 1006634.774 |  |  |  | 866491.01 | 2020-09-30 | 2020-09-30 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-15 | 42017188.2476 | [6 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10116 | EMAAR-PKG# 101-UPTOWN16
PKG#101 | 1 | 17 | 0.001 | 0 | -0.001 | 3321316.23 | 0 | -3321316.23 |  |  |  | 3321316.23 | 2021-03-31 | 2021-04-05 | 2021-04-13 | 40 | 2021-05-23 | 2021-04-26 | 42017188.2476 | [6 empty] | 270662.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10117 | EMAAR-PKG# 101-UPTOWN17
PKG#101 | 1 | 18 | 1071378.1714 | 0 | -1071378.1714 | 1192690.23 | 0 | -1192690.23 |  |  |  | 1192690.23 | 2021-04-30 | 2021-04-05 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-05 | 43088566.419 | 949450.54 | [5 empty] | 275887.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10118 | EMAAR-PKG# 101-UPTOWN18
PKG#101 | 1 | 19 | 1322361.8352 | 1071378.16 | -250983.6752 | 596242.89 | 1296410.108 | 700167.218 |  |  |  | 596242.89 | 2021-04-30 | 2021-05-05 | 2021-05-17 | 40 | 2021-06-26 | 2021-06-03 | 44410928.2543 | 615651.133 | [5 empty] | 288697.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10119 | EMAAR-PKG# 101-UPTOWN19
PKG#101 | 1 | 20 | 952923.8886 | 1322361.65 | 369437.7614 | 759353.32 | 648976.9025 | -110376.4175 |  |  |  | 759353.31 | 2021-05-31 | 2021-06-05 | 2021-06-10 | 40 | 2021-07-20 | 2021-06-27 | 45363852.1429 | 505736.36 | [5 empty] | 238697.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10120 | EMAAR-PKG# 101-UPTOWN20
PKG#101 | 1 | 21 | 2547253.7048 | 952924.081 | -1594329.6238 | 1584188.58 | 803886.0851 | -780302.4949 |  |  |  | 1584188.57 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 40 | 2021-08-20 | 2021-08-09 | 47911105.8476 | 618555.37 | [5 empty] | 264186.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10121 | EMAAR-PKG# 101-UPTOWN21
PKG#101 | 1 | 22 | 2544618.2857 | 2547253.71 | 2635.4243 | 594123.32 | 1912651.7855 | 1318528.4655 |  |  |  | 594122.92 | 2021-08-31 | 2021-08-15 | 2021-09-20 | 40 | 2021-10-30 | 2021-10-12 | 50455724.1333 | 0 | [5 empty] | 299725.92 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10122 | EMAAR-PKG# 101-UPTOWN22
PKG#101 | 1 | 23 |  | 2544618.3 | 2544618.3 | 189091.52 | 594123.335 | 405031.815 |  |  |  |  | 2022-04-30 | 2022-04-10 | 2022-04-21 | 40 | 2022-05-31 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10123 | EMAAR-PKG# 101-UPTOWN23
PKG#101 | 1 | 24 |  | 270197.08 | 270197.08 | 546994.62 | 546994.614 | -0.006 |  |  |  |  | 2022-04-30 | 2022-04-10 | 2023-03-27 | 40 | 2023-05-06 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG# 101-UPTOWN |  |  |  | PKG#10124 | EMAAR-PKG# 101-UPTOWN24
PKG#144 | 1 | 2 | 4125990.87 | 4125990.87 | 0 | 2532120.6 | 2748735.1235 | 216614.5235 |  |  |  | 2532120.6 | 2018-12-31 | 2018-12-26 | 2018-12-26 | 30 | 2019-01-25 | 2019-01-20 | 4125990.87 | [6 empty] | 25993.74 | 4125990.87 | 4125990.87 | 2532120.6 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1442 | EMAAR-PKG# 144, Marassi2
PKG#144 | 1 | 3 | 6872046.13 | 6872046.63 | 0.5 | 6189125.05 | 6189125.0415 | -0.0085 |  |  |  | 6190737.99 | 2019-01-31 | 2019-01-30 | 2019-01-31 | 30 | 2019-03-02 | 2019-02-20 | 10998037 | 3387217.5 | [5 empty] | 95995.9412 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1443 | EMAAR-PKG# 144, Marassi3
PKG#144 | 1 | 4 | 11224614.67 | 11222644.64 | -1970.03 | 6887337.01 | 6887337.022 | 0.012 |  |  |  | 6888545.72 | 2019-02-28 | 2019-02-27 | 2019-02-27 | 30 | 2019-03-29 | 2019-03-11 | 22222651.67 | 3387217.5 | [5 empty] | 166711.01 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1444 | EMAAR-PKG# 144, Marassi4
PKG#144 | 1 | 5 | 0 | 0 | 0 | 7206339.73 | 0 | -7206339.73 |  |  |  | 7206339.73 | 2019-02-28 | 2019-03-11 | 2019-03-11 | 30 | 2019-04-10 | 2019-03-11 | 22222651.67 | 3387217.5 | [5 empty] | 166711.64 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1445 | EMAAR-PKG# 144, Marassi5
PKG#144 | 1 | 6 | 24444079.39 | 24446048.93 | 1969.54 | 14929468.44 | 14929446.3565 | -22.0835 |  |  |  | 14801921.82 | 2019-03-31 | 2019-03-14 | 2019-03-14 | 30 | 2019-04-13 | 2019-03-21 | 46666731.06 | 3262056.75 | [5 empty] | 319957.75 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1446 | EMAAR-PKG# 144, Marassi6
PKG#144 | 1 | 7 | 20465525.6228 | 20465525.62 | -0.0027857 | 12477244.23 | 12627238.511 | 149994.281 |  |  |  | 12603636.3289 | 2019-03-31 | 2019-03-30 | 2019-03-30 | 30 | 2019-04-29 | 2019-04-11 | 67132256.6828 | 3501000 | [5 empty] | 672293.8257 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1447 | EMAAR-PKG# 144, Marassi7
PKG#144 | 1 | 8 | 16379645.0372 | 16360599.32 | -19045.7172 | 8906660.63 | 8934848.896 | 28188.266 |  |  |  | 8909777.64 | 2019-04-30 | 2019-04-15 | 2019-04-15 | 30 | 2019-05-15 | 2019-05-04 | 83511901.72 | 0 | [5 empty] | 795592.47 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1448 | EMAAR-PKG# 144, Marassi8
PKG#144 | 1 | 9 | 10281327.2057 | 10299181.31 | 17854.1043 | 9782161.34 | 9830068.4255 | 47907.0855 |  |  |  | 9777923.5506 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 30 | 2019-06-04 | 2019-05-15 | 93793228.9257 | 816900 | [5 empty] | 900089.7717 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#1449 | EMAAR-PKG# 144, Marassi9
PKG#144 | 1 | 10 | 13881511.5343 | 13884342.32 | 2830.7857 | 11074114.43 | 11330349.466 | 256235.036 |  |  |  | 11184527.72 | 2019-05-31 | 2019-05-20 | 2019-05-20 | 30 | 2019-06-19 | 2019-05-30 | 107674740.46 | [6 empty] | 1113537.73 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14410 | EMAAR-PKG# 144, Marassi10
PKG#144 | 1 | 11 | 9087190.46 | 8979474.51 | -107715.95 | 7386054.95 | 7386054.95 | 0 |  |  |  | 7486833.97 | 2019-06-30 | 2019-06-20 | 2019-06-18 | 30 | 2019-07-18 | 2019-07-11 | 116761930.92 | 0 | [5 empty] | 1199420.77 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14411 | EMAAR-PKG# 144, Marassi11
PKG#144 | 1 | 12 | 34717376.42 | 34831219.06 | 113842.64 | 21073691.31 | 32281831.2825 | 11208139.9725 |  |  |  | 22411649.36 | 2019-08-31 | 2019-09-05 | 2019-09-04 | 30 | 2019-10-04 | 2019-10-03 | 151479307.34 | [6 empty] | 8633180.89 | 34717376.42 | 151479307.34 | 22411649.36 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14412 | EMAAR-PKG# 144, Marassi12
PKG#144 | 1 | 13 | 11410387.23 | 0 | -11410387.23 | 14000000 | 0 | -14000000 |  |  |  | 14635108.89 | 2019-12-31 | 2019-12-25 | 2019-12-25 | 30 | 2020-01-24 | 2020-01-22 | 162889694.57 | [6 empty] | 9246101.93 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14413 | EMAAR-PKG# 144, Marassi13
PKG#144 | 1 | 14 | 10733689.1131 | 10733689.11 | -0.0031386 | 10173240.83 | 10786798.0055 | 613557.1755 |  |  |  | 10377806.9192 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 30 | 2020-03-04 | 2020-02-19 | 173623383.6831 | [6 empty] | 8262612.0833 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14414 | EMAAR-PKG# 144, Marassi14
PKG#144 | 1 | 15 | 2638692.2969 | 2638692.38 | 0.083139 | 9960243.27 | 5968624.239 | -3991619.031 |  |  |  | 10405304.53 | 2020-08-31 | 2020-08-20 | 2020-12-13 | 30 | 2021-01-12 | 2020-12-13 | 176262075.98 | [6 empty] | 2614017.44 | 0 | 0 | 0 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14415 | EMAAR-PKG# 144, Marassi15
PKG#144 | 1 | 16 | 150533.34 | 0 | -150533.34 | 1116473.97 | 0 | -1116473.97 |  |  |  | 1132971.99 | 2021-01-31 | 2021-01-20 | 2021-01-21 | 30 | 2021-02-20 | 2021-03-25 | 176412609.32 | [6 empty] | 2496617.44 | 150533.34 | 176412609.32 | 1132971.99 | EMAAR-PKG# 144, Marassi |  |  |  | PKG#14416 | EMAAR-PKG# 144, Marassi16
PKG#162 | 1 | 2 | 8785941.99 | 17264889.03 | 8478947.04 | 7794726.52 | 17974031.2815 | 10179304.7615 |  |  |  | 7794726.52 | 2020-02-29 | 2020-02-29 | 2020-03-05 | 40 | 2020-04-14 | 2020-03-22 | 8785941.99 | 749579.79 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1622 | EMAAR-Pkg#162/163- Marassi2
PKG#162 | 1 | 3 | 6446622.36 | 12082357.79 | 5635735.43 | 5119599.34 | 16268974.4395 | 11149375.0995 |  |  |  | 5119599.35 | 2020-03-31 | 2020-03-18 | 2020-03-21 | 40 | 2020-04-30 | 2020-03-30 | 15232564.35 | 531683.98 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1623 | EMAAR-Pkg#162/163- Marassi3
PKG#162 | 1 | 4 | 7314177.64 | 14694850.77 | 7380673.13 | 6336538.23 | 17742432.8485 | 11405894.6185 |  |  |  | 6336538.23 | 2020-03-31 | 2020-04-06 | 2020-04-06 | 40 | 2020-05-16 | 2020-04-22 | 22546741.99 | 1033463.45 | [5 empty] | 57000 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1624 | EMAAR-Pkg#162/163- Marassi4
PKG#162 | 1 | 5 | 8006098.57 | 8006098.571 | 0.001 | 6124877.69 | 7958142.0485 | 1833264.3585 |  |  |  | 6124877.69 | 2020-04-30 | 2020-05-05 | 2020-05-04 | 40 | 2020-06-13 | 2020-05-13 | 30552840.56 | 592328.38 | [5 empty] | 157000 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1625 | EMAAR-Pkg#162/163- Marassi5
PKG#162 | 1 | 6 | 5990865.4963 | 14622817.211 | 8631951.7147 | 4824045.39 | 13427541.4454 | 8603496.0554 |  |  |  | 4824045.381 | 2020-05-31 | 2020-06-06 | 2020-06-10 | 40 | 2020-07-20 | 2020-06-26 | 36543706.0563 | 474838.875 | [5 empty] | 157000 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1626 | EMAAR-Pkg#162/163- Marassi6
PKG#162 | 1 | 7 | 8577628.8704 | 12998247.66 | 4420618.7896 | 7215874.2121 | 12964361.5377 | 5748487.3256 |  |  |  | 7215874.2121 | 2020-06-30 | 2020-07-06 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-29 | 45121334.9266 | 834531.375 | [5 empty] | 260419 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1627 | EMAAR-Pkg#162/163- Marassi7
PKG#162 | 1 | 8 | 12161063.3859 | 27347974.52 | 15186911.1341 | 9432027.72 | 22259454.996 | 12827427.276 |  |  |  | 9432027.7177 | 2020-07-31 | 2020-08-10 | 2020-08-16 | 40 | 2020-09-25 | 2020-09-03 | 57282398.3125 | 136265.25 | [5 empty] | 261806 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1628 | EMAAR-Pkg#162/163- Marassi8
PKG#162 | 1 | 9 | 10973106.5017 | 15911837.121 | 4938730.6193 | 9889305 | 20607532.6031 | 10718227.6031 |  |  |  | 9889305.1266 | 2020-08-31 | 2020-09-05 | 2020-09-09 | 40 | 2020-10-19 | 2020-09-28 | 68255504.8142 | 1100385 | [5 empty] | 61806 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1629 | EMAAR-Pkg#162/163- Marassi9
PKG#162 | 1 | 10 | 14493217.0374 | 18387668.6001 | 3894451.5627 | 13282474.2108 | 18192775.4801 | 4910301.2693 |  |  |  | 13282474.2108 | 2020-09-30 | 2020-10-05 | 2020-10-07 | 40 | 2020-11-16 | 2020-11-03 | 82748721.8517 | 1005156.4395 | [5 empty] | 61806 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16210 | EMAAR-Pkg#162/163- Marassi10
PKG#162 | 1 | 11 | 9303551.5202 | 13136177.8201 | 3832626.2999 | 7840185.48 | 13368148.5779 | 5527963.0979 |  |  |  | 7840185.4913 | 2020-10-31 | 2020-11-05 | 2020-11-05 | 40 | 2020-12-15 | 2020-12-02 | 92052273.3719 | [6 empty] | 93807 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16211 | EMAAR-Pkg#162/163- Marassi11
PKG#162 | 1 | 12 | 7499598.7681 | 28306050.31 | 20806451.5419 | 4608392 | 21347264.7774 | 16738872.7774 |  |  |  | 4608392 | 2020-11-30 | 2020-12-01 | 2020-12-13 | 40 | 2021-01-22 | 2021-02-02 | 99551872.14 | 0 | [5 empty] | 2426668.64 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16212 | EMAAR-Pkg#162/163- Marassi12
PKG#162 | 1 | 13 | 709528.8141 | 7085309.261 | 6375780.4469 | 3429815.246 | 16955957.474 | 13526142.228 |  |  |  | 3429815.246 | 2020-12-31 | 2021-01-01 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-09 | 100261400.9541 | [6 empty] | 2376668.64 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16213 | EMAAR-Pkg#162/163- Marassi13
PKG#162 | 1 | 14 | -0.004055 | 13281620.941 | 13281620.9451 | 502581.43 | 15373453.508 | 14870872.078 |  |  |  | 502581.44 | 2021-01-31 | 2021-02-01 | 2021-02-03 | 40 | 2021-03-15 | 2021-02-24 | 100261400.95 | [6 empty] | 1926668.64 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16214 | EMAAR-Pkg#162/163- Marassi14
PKG#162 | 1 | 15 | 0.05 | 7388288.7 | 7388288.65 | 3999402.59 | 4317541.565 | 318138.975 |  |  |  | 3683579.28 | 2021-01-31 | 2021-02-01 | 2021-11-18 | 40 | 2021-12-28 | 2022-03-07 | 100261401 | [6 empty] | 926668 | 0.01 | 100261400.96 | 3683579.28 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16215 | EMAAR-Pkg#162/163- Marassi15
PKG#163 | 1 | 2 | 167514.17 | 17264889.03 | 17097374.86 | 1068966.43 | 17974031.2815 | 16905064.8515 |  |  |  | 1068966.43 | 2020-06-30 | 2020-07-07 | 2020-07-07 | 40 | 2020-08-16 | 2020-07-22 | 167514.17 | 1392714.35 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1632 | EMAAR-Pkg#162/163- Marassi2
PKG#163 | 1 | 3 | 1873525.03 | 12082357.79 | 10208832.76 | 2977091.11 | 16268974.4395 | 13291883.3295 |  |  |  | 2977091.11 | 2020-07-31 | 2020-08-10 | 2020-08-18 | 40 | 2020-09-27 | 2020-08-26 | 2041039.2 | 3794104.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1633 | EMAAR-Pkg#162/163- Marassi3
PKG#163 | 1 | 4 | 3480646.03 | 14694850.77 | 11214204.74 | 6845695.77 | 17742432.8485 | 10896737.0785 |  |  |  | 6845695.77 | 2020-08-31 | 2020-09-03 | 2020-09-03 | 40 | 2020-10-13 | 2020-09-23 | 5521685.23 | 10183594.03 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1634 | EMAAR-Pkg#162/163- Marassi4
PKG#163 | 1 | 5 | 3896848.6915 | 8006098.571 | 4109249.8795 | 3782501.29 | 7958142.0485 | 4175640.7585 |  |  |  | 3782501.2803 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 40 | 2020-11-09 | 2020-10-22 | 9418533.9215 | 11640240.8375 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1635 | EMAAR-Pkg#162/163- Marassi5
PKG#163 | 1 | 6 | 8635132.0099 | 14622817.211 | 5987685.2011 | 6255172.17 | 13427541.4454 | 7172369.2754 |  |  |  | 6255172.4375 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 40 | 2020-12-13 | 2020-11-29 | 18053665.9314 | 11614831.0892 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1636 | EMAAR-Pkg#162/163- Marassi6
PKG#163 | 1 | 7 | 4420616.8286 | 12998247.66 | 8577630.8314 | 4922193.5 | 12964361.5377 | 8042168.0377 |  |  |  | 4922193.5 | 2020-11-30 | 2020-12-07 | 2020-12-08 | 40 | 2021-01-17 | 2020-12-23 | 22474282.76 | 14196023.04 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1637 | EMAAR-Pkg#162/163- Marassi7
PKG#163 | 1 | 8 | 7415396.32 | 27347974.52 | 19932578.2 | 6050639.77 | 22259454.996 | 16208815.226 |  |  |  | 6050639.7742 | 2020-12-31 | 2021-01-05 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-02 | 29889679.08 | 15239713.55 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1638 | EMAAR-Pkg#162/163- Marassi8
PKG#163 | 1 | 9 | 5020188.6174 | 15911837.121 | 10891648.5036 | 4602212.16 | 20607532.6031 | 16005320.4431 |  |  |  | 4602212.1569 | 2021-01-31 | 2021-01-25 | 2021-02-25 | 40 | 2021-04-06 | 2021-03-08 | 34909867.6974 | 16642238.4803 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1639 | EMAAR-Pkg#162/163- Marassi9
PKG#163 | 1 | 10 | 3812993.5626 | 18387668.6001 | 14574675.0375 | 2532838.57 | 18192775.4801 | 15659936.9101 |  |  |  | 2532838.57 | 2021-02-28 | 2021-02-25 | 2021-03-03 | 40 | 2021-04-12 | 2021-10-23 | 38722861.26 | 16355289.4 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16310 | EMAAR-Pkg#162/163- Marassi10
PKG#163 | 1 | 11 | 3832626.3 | 13136177.8201 | 9303551.5201 | 3799097.57 | 13368148.5779 | 9569051.0079 |  |  |  | 3799097.57 | 2021-03-31 | 2021-03-25 | 2021-03-31 | 40 | 2021-05-10 | 2021-04-25 | 42555487.56 | 17842244.91 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16311 | EMAAR-Pkg#162/163- Marassi11
PKG#163 | 1 | 12 | 3268183.05 | 28306050.31 | 25037867.26 | 2215480.09 | 21347264.7774 | 19131784.6874 |  |  |  | 2215480.09 | 2021-04-30 | 2021-04-25 | 2021-05-04 | 40 | 2021-06-13 | 2021-06-03 | 45823670.61 | 17661654.17 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16312 | EMAAR-Pkg#162/163- Marassi12
PKG#163 | 1 | 13 | 6375780.44 | 7085309.261 | 709528.821 | 3821253.39 | 16955957.474 | 13134704.084 |  |  |  | 3821253.39 | 2021-05-31 | 2021-05-25 | 2021-05-31 | 40 | 2021-07-10 | 2021-06-21 | 52199451.05 | 16405178.95 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16313 | EMAAR-Pkg#162/163- Marassi13
PKG#163 | 1 | 14 | 13281620.95 | 13281620.941 | -0.009 | 10697999.42 | 15373453.508 | 4675454.088 |  |  |  | 10697999.42 | 2021-06-30 | 2021-06-26 | 2021-07-01 | 40 | 2021-08-10 | 2021-08-02 | 65481072 | 18157750.16 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16314 | EMAAR-Pkg#162/163- Marassi14
PKG#163 | 1 | 15 | 7388288.7 | 7388288.7 | 1.2107e-08 | 4024676.65 | 4317541.565 | 292864.915 |  |  |  | 4024675.65 | 2021-07-31 | 2021-07-25 | 2021-08-02 | 40 | 2021-09-11 | 2021-08-26 | 72869360.7 | 16257345.38 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16315 | EMAAR-Pkg#162/163- Marassi15
PKG#163 | 1 | 16 | 6043601.4 | 55287937 | 49244335.6 | 3611195.74 | 15368075.701 | 11756879.961 |  |  |  | 3611195.73 | 2021-08-31 | 2021-08-25 | 2021-09-06 | 40 | 2021-10-16 | 2021-09-30 | 78912962.1 | 15138470.41 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16316 | EMAAR-Pkg#162/163- Marassi16
PKG#163 | 1 | 17 | 5496981.8 | 5496981.8001 | 9.9988e-05 | 2445757.34 | 2956365.1601 | 510607.8201 |  |  |  | 2445757.34 | 2021-09-30 | 2021-09-25 | 2021-10-03 | 40 | 2021-11-12 | 2021-10-27 | 84409943.9 | 12955550.43 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16317 | EMAAR-Pkg#162/163- Marassi17
PKG#163 | 1 | 18 | 3301294.98 | 16225112.87 | 12923817.89 | 2445757.34 | 19270685.5835 | 16824928.2435 |  |  |  | 3026069.35 | 2021-10-31 | 2021-10-25 | 2021-11-01 | 40 | 2021-12-11 | 2021-11-15 | 87711238.88 | 13929653.03 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16318 | EMAAR-Pkg#162/163- Marassi18
PKG#163 | 1 | 19 | 9320216.47 | 9320216.4901 | 0.0201 | 6520369.14 | 15003262.3046 | 8482893.1646 |  |  |  | 7895027.24 | 2021-11-30 | 2021-11-25 | 2021-11-30 | 40 | 2022-01-09 | 2021-12-16 | 97031455.35 | 15728609.99 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16319 | EMAAR-Pkg#162/163- Marassi19
PKG#163 | 1 | 20 | 4346059.97 | 14793463.46 | 10447403.49 | 3715617.2 | 10622091.773 | 6906474.573 |  |  |  | 2340959.11 | 2021-12-31 | 2021-12-25 | 2022-01-02 | 40 | 2022-02-11 | 2022-01-19 | 101377515.32 | 14609274.92 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16320 | EMAAR-Pkg#162/163- Marassi20
PKG#163 | 1 | 21 | 5919076.73 | 16895262.31 | 10976185.58 | 5322260.63 | 11574799.0555 | 6252538.4255 |  |  |  | 5322260.63 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 40 | 2022-03-15 | 2022-03-17 | 107296592.05 | 15284733.68 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16321 | EMAAR-Pkg#162/163- Marassi21
PKG#163 | 1 | 22 | 2632588.63 | 10221216.4 | 7588627.77 | 2261775.79 | 6046552.498 | 3784776.708 |  |  |  | 2261775.79 | 2022-02-28 | 2022-02-28 | 2022-03-01 | 40 | 2022-04-10 | 2022-03-23 | 109929180.68 | 15087666.62 |  |  |  | 3262202.645 | 3262202.645 | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16322 | EMAAR-Pkg#162/163- Marassi22
PKG#163 | 1 | 23 | 6399693.2 | 11084383.47 | 4684690.27 | 3449740.5053 | 8263496.6735 | 4813756.1682 |  |  |  | 3449740.51 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 40 | 2022-05-17 | 2022-09-06 | 116328873.88 | 12447737.11 |  |  |  | 3363997.5 | 3363997.5 | 139451 | 0 | 0 | 3449740.5053 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16323 | EMAAR-Pkg#162/163- Marassi23
PKG#163 | 1 | 24 | 6669347.19 | 12620775.22 | 5951428.03 | 5681606.5237 | 11118548.566 | 5436942.0423 |  |  |  | 5681606.52 | 2022-04-30 | 2022-04-20 | 2022-04-28 | 40 | 2022-06-07 | 2022-09-06 | 122998221.07 | 11928679.08 | 79159509 |  | 106910.74 | 3526010 | 3526010 | 170264.36 | 5789760.2558 | 115718940.9358 | 5681606.5237 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16324 | EMAAR-Pkg#162/163- Marassi24
PKG#163 | 1 | 25 | 12929046.56 | 16552264.24 | 3623217.68 | 11730565.831 | 16704168.777 | 4973602.946 |  |  |  | 11730565.83 | 2022-05-31 | 2022-05-25 | 2022-06-02 | 40 | 2022-07-12 | 2022-09-06 | 135927267.63 | 11655699.31 | 84070405.07 |  | 214226.97 | 3858707 | 3858707 | 170264.36 | 22617186.6357 | 145615407.7057 | 11730565.831 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16325 | EMAAR-Pkg#162/163- Marassi25
PKG#163 | 1 | 26 | 6526578.31 | 7856344.54 | 1329766.23 | 6014332.37 | 8378952.377 | 2364620.007 |  |  |  | 6014332.37 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 40 | 2022-08-14 | 2022-09-19 | 142453845.94 | 11222354.42 | 87095709.46 |  | 214226.97 | 4019196.11 | 4019196.11 | 170264 | 20328767.6537 | 156256035.2837 | 8194504.6617 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16326 | EMAAR-Pkg#162/163- Marassi26
PKG#163 | 1 | 27 | 4132634.87 | 4132634.87 | 2.5146e-08 | 3457484.33 | 3653603.3235 | 196118.9935 |  |  |  | 3457484.33 | 2022-07-31 | 2022-07-31 | 2022-08-09 | 40 | 2022-09-18 | 2022-09-25 | 146586480.81 | 10805467.52 | 88908671.92 |  | 214226.97 | 4117255.5 | 4117255.5 | 170264 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16327 | EMAAR-Pkg#162/163- Marassi27
PKG#163 | 1 | 28 | 17622733.92 | 22582028.69 | 4959294.77 | 18331730.1 | 23295212.1945 | 4963482.0945 |  |  |  | 18331730.1 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 40 | 2022-10-22 | 2022-11-10 | 164209214.73 | 13098222.27 | 70785988.93 |  | 693580.47 | 4637171.235 | 4637171.235 | 0 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16328 | EMAAR-Pkg#162/163- Marassi28
PKG#163 | 1 | 29 | 20296742.22 | 20296742.21 | -0.01 | 18785649.76 | 19850779.098 | 1065129.338 |  |  |  | 18785649.76 | 2022-09-30 | 2022-09-30 | 2022-10-20 | 40 | 2022-11-29 | 2023-01-15 | 184505956.95 | 13098222.27 | 159762353.93 |  | 693580.47 | 5169960.72 | 5169960.72 | 170264.36 | 17622733.92 | 181831948.65 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16329 | EMAAR-Pkg#162/163- Marassi29
PKG#163 | 1 | 30 | 8788912.25 | 27617784.67 | 18828872.42 | 3193802.31 | 15359271.0135 | 12165468.7035 |  |  |  | 3193802.31 | 2023-01-31 | 2023-01-18 | 2023-01-18 | 40 | 2023-02-27 | 2023-08-09 | 193294869.2 | 8080616.05 | 66836818.15 |  | 624222.43 | 5275229.5 | 5275229.5 | 688139.36 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16330 | EMAAR-Pkg#162/163- Marassi30
PKG#163 | 1 | 31 | -406906.47 | 10357799.14 | 10764705.61 | 1079324.09 | 10109132.947 | 9029808.857 |  |  |  | 1079324.1 | 2023-02-28 | 2023-02-28 | 2023-03-15 | 40 | 2023-04-24 | 2023-08-09 | 192887962.73 | 9732318.5 | 56933789.25 |  | 1100688.83 | 5305840.78 | 5305840.78 | 688139.36 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16331 | EMAAR-Pkg#162/163- Marassi31
PKG#163 | 1 | 32 | 5753296.48 | 11583000.46 | 5829703.98 | 4562478.02 | 15273972.9335 | 10711494.9135 |  |  |  | 4562478.01 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 40 | 2023-06-23 | 2023-12-13 | 198641259.21 | 8867308.69 | 66948753.43 |  | 1100688.83 | 5435239.565 | 5435239.565 | 688139.36 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16332 | EMAAR-Pkg#162/163- Marassi32
PKG#163 | 1 | 33 |  | 4083110.28 | 4083110.28 | 0.0001 | 3354959.084 | 3354959.0839 |  |  |  | 5000000 | 2023-05-31 | 2023-05-31 | 2023-06-11 | 40 | 2023-07-21 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16333 | EMAAR-Pkg#162/163- Marassi33
PKG#163 | 1 | 34 |  | 0 | 0 | 0.0001 | 0 | -0.0001 |  |  |  | 5000000 | 2023-06-30 | 2023-07-10 | 2023-07-13 | 40 | 2023-08-22 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16334 | EMAAR-Pkg#162/163- Marassi34
PKG#163 | 1 | 35 |  | 20620247.8 | 20620247.8 | 0.0001 | 15928851.3665 | 15928851.3664 |  |  |  | 5000000 | 2023-10-31 | 2023-11-14 | 2023-11-15 | 40 | 2023-12-25 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16335 | EMAAR-Pkg#162/163- Marassi35
PKG#163 | 1 | 36 |  | 42116952.2 | 42116952.2 | 0 | 36331150.12 | 36331150.12 |  |  |  | 10852799 | 2024-05-31 | 2024-05-21 | 2024-05-26 | 40 | 2024-07-05 |  | 221749507 | [6 empty] | 0 | 0 | 0 | 10852799 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#16336 | EMAAR-Pkg#162/163- Marassi36
PKG#177 | 1 | 2 | 8478947.03 | 17264889.03 | 8785942 | 10240448.36 | 17974031.2815 | 7733582.9215 |  |  |  | 10240448.36 | 2021-04-30 | 2021-04-30 | 2021-04-26 | 30 | 2021-05-26 | 2021-05-12 | 8478947.03 | 4144486.18 | [5 empty] | 16912.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1772 | EMAAR-Pkg#162/163- Marassi2
PKG#177 | 1 | 3 | 9.9998e-05 | 12082357.79 | 12082357.7899 | 3893019.54 | 16268974.4395 | 12375954.8995 |  |  |  | 3893019.54 | 2021-04-30 | 2021-04-25 | 2021-05-05 | 30 | 2021-06-04 | 2021-05-26 | 8478947.03 | 9209962.12 | [5 empty] | 16912.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1773 | EMAAR-Pkg#162/163- Marassi3
PKG#177 | 1 | 4 | 5088605.14 | 14694850.77 | 9606245.63 | 14139690.65 | 17742432.8485 | 3602742.1985 |  | 10000000 |  | 4135304.94 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 30 | 2021-06-09 | 2021-05-27 | 13567552.17 | 9209962.12 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1774 | EMAAR-Pkg#162/163- Marassi4
PKG#177 | 1 | 5 | 0.0001 | 8006098.571 | 8006098.5709 | 11890262.73 | 7958142.0485 | -3932120.6815 |  | 10000000 |  | 1889110.9 | 2021-05-31 | 2021-05-25 | 2021-05-26 | 30 | 2021-06-25 | 2021-06-03 | 13567552.17 | 11628798.1 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1775 | EMAAR-Pkg#162/163- Marassi5
PKG#177 | 1 | 6 | 0.0001 | 14622817.211 | 14622817.2109 | 12069539.45 | 13427541.4454 | 1358001.9954 |  | 10000000 |  | 2069539.45 | 2021-05-31 | 2021-05-25 | 2021-05-30 | 30 | 2021-06-29 | 2021-06-21 | 13567552.17 | 14278656.55 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1776 | EMAAR-Pkg#162/163- Marassi6
PKG#177 | 1 | 7 | 0.0001 | 12998247.66 | 12998247.6599 | 40000000 | 12964361.5377 | -27035638.4623 |  | 10000000 |  | 30000000 | 2021-05-31 | 2021-05-25 | 2021-06-02 | 30 | 2021-07-02 | 2021-06-21 | 13567552.17 | 14278656.55 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1777 | EMAAR-Pkg#162/163- Marassi7
PKG#177 | 1 | 8 | 7777231.12 | 27347974.52 | 19570743.4 | 16325726.09 | 22259454.996 | 5933728.906 |  | 10000000 |  | 6324855.08 | 2021-05-31 | 2021-05-25 | 2021-06-06 | 30 | 2021-07-06 | 2021-06-21 | 21344783.29 | 14212069.8 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1778 | EMAAR-Pkg#162/163- Marassi8
PKG#177 | 1 | 9 | 0.0001 | 15911837.121 | 15911837.1209 | 11386804.78 | 20607532.6031 | 9220727.8231 |  | 10000000 |  | 1386804.78 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 30 | 2021-07-09 | 2021-06-21 | 21344783.29 | 15987748.13 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#1779 | EMAAR-Pkg#162/163- Marassi9
PKG#177 | 1 | 10 | 9.9996e-05 | 18387668.6001 | 18387668.6 | 11031892.42 | 18192775.4801 | 7160883.0601 |  | 10000000 |  | 1030274.11 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 21344783.29 | 17306921.13 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17710 | EMAAR-Pkg#162/163- Marassi10
PKG#177 | 1 | 11 | 0.00010001 | 13136177.8201 | 13136177.82 | 11623911.78 | 13368148.5779 | 1744236.7979 |  | 10000000 |  | 1623911.78 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 21344783.29 | 19386193.57 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17711 | EMAAR-Pkg#162/163- Marassi11
PKG#177 | 1 | 12 | 17543747.3405 | 28306050.31 | 10762302.9695 | 11867471.98 | 21347264.7774 | 9479792.7974 |  |  |  | 11864115.6307 | 2021-05-31 | 2021-06-10 | 2021-06-17 | 30 | 2021-07-17 | 2021-07-08 | 38888530.6305 | 16150782.833 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17712 | EMAAR-Pkg#162/163- Marassi12
PKG#177 | 1 | 13 | -0.0001 | 7085309.261 | 7085309.2611 | 4287396.18 | 16955957.474 | 12668561.294 |  |  |  | 4287396.18 | 2021-05-31 | 2021-06-10 | 2021-06-24 | 30 | 2021-07-24 | 2021-07-08 | 38888530.6305 | 21640406.623 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17713 | EMAAR-Pkg#162/163- Marassi13
PKG#177 | 1 | 14 | -0.0006304 | 13281620.941 | 13281620.9416 | 3654358.5 | 15373453.508 | 11719095.008 |  |  |  | 3654358.5 | 2021-06-30 | 2021-07-10 | 2021-07-07 | 30 | 2021-08-06 | 2021-07-08 | 38888530.63 | 26319482.8 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17714 | EMAAR-Pkg#162/163- Marassi14
PKG#177 | 1 | 15 | 0.00043038 | 7388288.7 | 7388288.6996 | 30000000 | 4317541.565 | -25682458.435 |  |  |  | 30000000 | 2021-06-30 | 2021-07-10 | 2021-07-11 | 30 | 2021-08-10 | 2021-07-15 | 38888530.6305 | 26319482.803 | [5 empty] | 57062.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17715 | EMAAR-Pkg#162/163- Marassi15
PKG#177 | 1 | 16 | 49248459.9349 | 55287937 | 6039477.0651 | 8978914.16 | 15368075.701 | 6389161.541 |  |  |  | 8979568.5092 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 30 | 2021-08-14 | 2021-08-08 | 88136990.5654 | 24945340.303 | [5 empty] | 415112.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17716 | EMAAR-Pkg#162/163- Marassi16
PKG#177 | 1 | 17 | 0.0045094 | 5496981.8001 | 5496981.7956 | 311248.17 | 2956365.1601 | 2645116.9901 |  |  |  | 311058.51 | 2021-06-30 | 2021-07-10 | 2021-07-28 | 30 | 2021-08-27 | 2021-08-10 | 88136990.57 | 25343622.64 | [5 empty] | 415112.5 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17717 | EMAAR-Pkg#162/163- Marassi17
PKG#177 | 1 | 18 | 12925810.52 | 16225112.87 | 3299302.35 | 15059090.32 | 19270685.5835 | 4211595.2635 |  |  |  | 15056356.09 | 2021-06-30 | 2021-07-10 | 2021-08-02 | 30 | 2021-09-01 | 2021-09-02 | 101062801.09 | 31043670.3 | [5 empty] | 415112.5 | 12925810.52 | 101062801.09 | 15056356.09 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17718 | EMAAR-Pkg#162/163- Marassi18
PKG#177 | 1 | 19 | -0.0001 | 9320216.4901 | 9320216.4902 | 6143418.31 | 15003262.3046 | 8859843.9946 |  |  |  | 6139746.33 | 2021-07-31 | 2021-07-25 | 2021-08-05 | 30 | 2021-09-04 | 2021-09-16 | 101062801.09 | 38754821.03 | [5 empty] | 528137.5 | -0.0001 | 101062801.09 | -0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17719 | EMAAR-Pkg#162/163- Marassi19
PKG#177 | 1 | 20 | 10455877.97 | 14793463.46 | 4337585.49 | 7621726.83 | 10622091.773 | 3000364.943 |  |  |  | 7622310.5 | 2021-07-31 | 2021-07-25 | 2021-08-08 | 30 | 2021-09-07 | 2021-10-19 | 111518679.06 | 37529135.79 | [5 empty] | 528137.5 | -0.001 | 101062801.09 | -0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17720 | EMAAR-Pkg#162/163- Marassi20
PKG#177 | 1 | 21 | 10986391.49 | 16895262.31 | 5908870.82 | 5553244.96 | 11574799.0555 | 6021554.0955 |  |  |  | 5555354.29 | 2021-07-31 | 2021-07-25 | 2021-08-17 | 30 | 2021-09-16 | 2021-11-18 | 122505070.55 | 33099520.87 | [5 empty] | 528137.5 | -0.0001 | 111518679.06 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17721 | EMAAR-Pkg#162/163- Marassi21
PKG#177 | 1 | 22 | 7592601.09 | 10221216.4 | 2628615.31 | 3436603.03 | 6046552.498 | 2609949.468 |  |  |  | 3438276.09 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 30 | 2021-09-30 | 2021-12-07 | 130097671.64 | 29527784.9 | [5 empty] | 528137.5 | -0.0001 | 122505070.55 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17722 | EMAAR-Pkg#162/163- Marassi22
PKG#177 | 1 | 23 | 4755868.7 | 11084383.47 | 6328514.77 | 4324164.09 | 8263496.6735 | 3939332.5835 |  |  |  | 4323818.2 | 2021-08-31 | 2021-09-05 | 2021-09-08 | 30 | 2021-10-08 | 2022-01-04 | 134853540.34 | 30254166.65 | [5 empty] | 674051.5 | -0.0001 | 130097671.64 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17723 | EMAAR-Pkg#162/163- Marassi23
PKG#177 | 1 | 24 | 5954515.89 | 12620775.22 | 6666259.33 | 4835218.42 | 11118548.566 | 6283330.146 |  |  |  | 4835550.93 | 2021-08-31 | 2021-09-05 | 2021-09-12 | 30 | 2021-10-12 | 2022-01-26 | 140808056.23 | 29555882.9 | [5 empty] | 0 | -0.0001 | 134853540.34 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17724 | EMAAR-Pkg#162/163- Marassi24
PKG#177 | 1 | 25 | 3618126.71 | 16552264.24 | 12934137.53 | 4062657.22 | 16704168.777 | 12641511.557 |  |  |  | 4062127.69 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 30 | 2021-11-05 | 2022-02-28 | 144426182.94 | 30667900.14 | [5 empty] | 0 | -0.0001 | 140808056.23 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17725 | EMAAR-Pkg#162/163- Marassi25
PKG#177 | 1 | 26 | -0.00099997 | 7856344.54 | 7856344.541 | 30000000 | 8378952.377 | -21621047.623 |  |  |  | 30000000 | 2021-10-31 | 2021-10-25 | 2021-11-03 | 30 | 2021-12-03 | 2022-03-13 | 144426182.94 | 30667900.14 | [5 empty] | 0 | 0 | 0 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17726 | EMAAR-Pkg#162/163- Marassi26
PKG#177 | 1 | 27 | 1336271.1 | 4132634.87 | 2796363.77 | 1920749.49 | 3653603.3235 | 1732853.8335 |  |  |  | 1920178.92 | 2021-11-30 | 2021-11-25 | 2021-12-07 | 30 | 2022-01-06 | 2022-03-23 | 145762454.04 | 31729493.34 | [5 empty] | 0 | 0 | 0 | -0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17727 | EMAAR-Pkg#162/163- Marassi27
PKG#177 | 1 | 28 | 4959294.77 | 22582028.69 | 17622733.92 | 3761281.17 | 23295212.1945 | 19533931.0245 |  |  |  | 3761592.26 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-03-30 | 150721748.81 | 31076204.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17728 | EMAAR-Pkg#162/163- Marassi28
PKG#177 | 1 | 29 | -0.0001 | 20296742.21 | 20296742.2101 | 30000000 | 19850779.098 | -10149220.902 |  |  |  | 30000000 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-04-05 | 150721748.81 | 31076204.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17729 | EMAAR-Pkg#162/163- Marassi29
PKG#177 | 1 | 30 | 13573272.69 | 27617784.67 | 14044511.98 | 11174297.33 | 15359271.0135 | 4184973.6835 |  |  |  | 11173851.87 | 2021-12-31 | 2021-12-30 | 2022-01-05 | 30 | 2022-02-04 | 2022-04-18 | 164295021.5 | 32011659.59 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17730 | EMAAR-Pkg#162/163- Marassi30
PKG#177 | 1 | 31 | -0.0001 | 10357799.14 | 10357799.1401 | 20000000 | 10109132.947 | -9890867.053 |  |  |  | 20000000 | 2022-04-30 | 2022-04-18 | 2022-04-18 | 30 | 2022-05-18 | 2022-04-19 | 164295021.5 | 32011659.59 | [5 empty] | 1244836 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17731 | EMAAR-Pkg#162/163- Marassi31
PKG#177 | 1 | 32 | 10655190.55 | 11583000.46 | 927809.91 | 9586612.72 | 15273972.9335 | 5687360.2135 |  |  |  | 9586713.98 | 2022-01-31 | 2022-01-31 | 2022-02-10 | 30 | 2022-03-12 | 2022-05-10 | 174950212.05 | 31704142.35 | [5 empty] | 0 | 0 | 0 | 1200000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17732 | EMAAR-Pkg#162/163- Marassi32
PKG#177 | 1 | 33 |  | 4083110.28 | 4083110.28 | 9774603.63 | 3354959.084 | -6419644.546 |  |  |  |  | 2022-03-31 | 2022-03-28 | 2022-05-22 | 30 | 2022-06-21 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17733 | EMAAR-Pkg#162/163- Marassi33
PKG#177 | 1 | 34 | 4083110.25 | 0 | -4083110.25 | 3243420.79 | 0 | -3243420.79 |  |  |  | 3242747.22 | 2022-02-28 | 2022-03-01 | 2022-03-06 | 30 | 2022-04-05 | 2022-06-01 | 189971239 | 33248463 |  |  |  | 5813429 | 5813429 | 1266148 | 3016331.1152 | 188904459.8652 | 16000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17734 | EMAAR-Pkg#162/163- Marassi34
PKG#177 | 1 | 35 | 20620247 | 20620247.8 | 0.8 | 14874314 | 15928851.3665 | 1054537.3665 |  |  |  | 14874314.24 | 2022-04-30 | 2022-04-20 | 2022-06-08 | 30 | 2022-07-08 | 2022-06-08 | 210591486 | 32687951 |  |  |  | 6340697.5 | 6340697.5 | 1273436 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17735 | EMAAR-Pkg#162/163- Marassi35
PKG#177 | 1 | 36 | 41964961.54 | 42116952.2 | 151990.66 | 32974130.9 | 36331150.12 | 3357019.22 |  |  |  | 32974130.9 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 | 2022-08-04 | 252556447.54 | 55952679 |  |  |  | 8027886.035 | 8027886.035 | 2506369.82 | 2649851.22 | 213241337.22 | 15000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17736 | EMAAR-Pkg#162/163- Marassi36
PKG#177 | 1 | 37 | 3201525.38 | 3201525.38 | 6.3796e-08 | 2963171.82 | 3131251.909 | 168080.089 |  |  |  | 2963171.82 | 2022-03-31 | 2022-04-12 | 2022-04-12 | 30 | 2022-05-12 | 2022-08-14 | 255757972.92 | 55952679 |  |  |  | 8111926.08 | 8111926.08 | 1543023.5 | 3201524.52 | 255757972.06 | 2963171.8184 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17737 | EMAAR-Pkg#162/163- Marassi37
PKG#177 | 1 | 38 | 113074932.04 | 113074931.25 | -0.79 | 40830987.19 | 46024929.671 | 5193942.481 |  |  |  | 40830987.19 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 | 2022-08-15 | 368832904.96 | 41102851 |  |  | 430147 | 10708897.325 | 10708897.325 | 8967998.5 | -0.86 | 255757972.06 | 0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17738 | EMAAR-Pkg#162/163- Marassi38
PKG#177 | 1 | 39 | 62332263.27 | 62325696.1 | -6567.17 | 24380106.6 | 27439277.805 | 3059171.205 |  |  |  | 24380106.6 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 | 2022-10-03 | 431165168.23 | 36844292 | [5 empty] | 0 | -178832904.96 | 190000000 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17739 | EMAAR-Pkg#162/163- Marassi39
PKG#177 | 1 | 40 | 2265658.58 | 2265659.38 | 0.8 | 0.0001 | 118928.159 | 118928.1589 |  |  |  | 0.0001 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 30 | 2022-08-30 | 2022-11-22 | 433430826.81 | 36844292 |  |  | 430147 |  |  | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17740 | EMAAR-Pkg#162/163- Marassi40
PKG#177 | 1 | 41 | 16308262.76 | 16303582.18 | -4680.58 | 1e-05 | 180103.25 | 180103.25 |  |  |  | 0.0001 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 | 2022-11-22 | 449739089.57 | 23473659 | [5 empty] | 0 | -11904090.5837 | 421526736.2263 | 10330863.574 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17741 | EMAAR-Pkg#162/163- Marassi41
PKG#177 | 1 | 42 | 25575904.54 | 2102245.55 | -23473658.99 | 4198626.99 | 4316245.8075 | 117618.8175 |  |  |  | 4207031.92 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 30 | 2022-10-30 | 2023-02-22 | 475314994.11 | [6 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17742 | EMAAR-Pkg#162/163- Marassi42
PKG#177 | 1 | 43 | -1403499.79 | 15896560.84 | 17300060.63 | 14488992.22 | 15323561.672 | 834569.452 |  |  |  | 14488837.89 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-04-13 | 473911494.32 | 23473659 | 399954494 |  | 430147.49 | 12864128.305 | 12864128.305 | 3512870.7 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17743 | EMAAR-Pkg#162/163- Marassi43
PKG#177 | 1 | 44 | 59788309.64 | 54841445.41 | -4946864.23 | 17144236.06 | 19396451.9605 | 2252215.9005 |  |  |  | 17144236.06 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-05-25 | 533699803.96 | 11107434 | 448361770 |  | 430147.49 | 13994560.62 | 13994560.62 | 4392870.7 | 0 | 0 | 20000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17744 | EMAAR-Pkg#162/163- Marassi44
PKG#177 | 1 | 45 | 102598790.27 | 26509803.46 | -76088986.81 | 15002016.49 | 16466307.981 | 1464291.491 |  |  |  | 15002016.49 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 30 | 2022-10-07 | 2023-06-15 | 576510284.59 | 12544287.37 | 474871564.16 |  | 430147.49 | 14726364.3 | 14726364.3 | 4392870.7 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17745 | EMAAR-Pkg#162/163- Marassi45
PKG#177 | 1 | 46 | -22395666.32 | 5007444.76 | 27403111.08 | 3048300.98 | 3319156.348 | 270855.368 |  |  |  | 3056265.5 | 2022-09-30 | 2022-09-25 | 2022-10-17 | 30 | 2022-11-16 | 2023-07-16 | 554114618.27 | 12544287.37 | 479879018.92 |  | 430147 | 14857839.5 | 14857839.5 | 8396085.7 | 0 | 0 | 10000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17746 | EMAAR-Pkg#162/163- Marassi46
PKG#177 | 1 | 47 | 6780617.51 | 6785617.6 | 5000.09 | 4274072.25 | 4548162.03 | 274089.78 |  |  |  | 4274854.67 | 2023-06-30 | 2023-06-25 | 2023-02-15 | 30 | 2023-03-17 | 2023-08-03 | 560895235.78 | 10901184.51 | 486669436 |  | 430147 | 14994854.5 | 14994854.5 | 8396085.7 | 21331767.9853 | 575446386.2553 | 4375831.9851 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17747 | EMAAR-Pkg#162/163- Marassi47
PKG#177 | 1 | 48 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 4111000 | 2023-03-31 | 2023-03-25 | 2023-03-26 | 30 | 2023-04-25 | [8 empty] | 0 | 0 | 0 | 4111000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17748 | EMAAR-Pkg#162/163- Marassi48
PKG#177 | 1 | 49 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 0.0001 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 30 | 2023-06-13 | [8 empty] | 0 | 0 | 0 | 0.0001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17749 | EMAAR-Pkg#162/163- Marassi49
PKG#177 | 1 | 50 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 0.001 | 2023-05-31 | 2023-05-31 | 2023-06-04 | 30 | 2023-07-04 | [8 empty] | 0 | 0 | 0 | 0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17750 | EMAAR-Pkg#162/163- Marassi50
PKG#177 | 1 | 51 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 0.001 | 2023-06-30 | 2023-06-25 | 2023-06-25 | 30 | 2023-07-25 | [8 empty] | 0 | 0 | 0 | 0.001 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17751 | EMAAR-Pkg#162/163- Marassi51
PKG#177 | 1 | 52 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 45000000 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 30 | 2023-09-13 | [8 empty] | 0 | 0 | 0 | 45000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17752 | EMAAR-Pkg#162/163- Marassi52
PKG#177 | 1 | 53 |  | 0 | 0 | 1e-06 | 0 | -1e-06 |  |  |  | 5000000 | 2023-10-31 | 2023-11-14 | 2023-11-14 | 30 | 2023-12-14 | [8 empty] | 0 | 0 | 0 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17753 | EMAAR-Pkg#162/163- Marassi53
PKG#177 | 1 | 54 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 14081143 | 2024-05-31 | 2024-06-04 | 2024-06-05 | 30 | 2024-07-05 |  | 626950196.89 | [6 empty] | 0 | 0 | 0 | 14081143 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#17754 | EMAAR-Pkg#162/163- Marassi54
PKG#177 - DP | 1 | 1 |  | 1493908.79 | 1493908.79 | 0 | 1068966.4295 | 1068966.4295 |  |  |  | 22337274.9 | 2021-03-31 | 2021-03-24 | 2021-03-24 | 30 | 2021-04-23 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - DP1 | EMAAR-Pkg#162/163- Marassi1
PKG#177 - SWI 07 | 1 | 1 |  | 1493908.79 | 1493908.79 | 0 | 1068966.4295 | 1068966.4295 |  |  |  | 1800000 | 2021-11-30 | 2021-12-15 | 2021-12-13 | 30 | 2022-01-12 | [8 empty] | 0 | 0 | 0 | 1800000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 071 | EMAAR-Pkg#162/163- Marassi1
PKG#177 - SWI 07 | 1 | 2 |  | 17264889.03 | 17264889.03 | 0 | 17974031.2815 | 17974031.2815 |  |  |  | 4300000 | 2021-12-31 | 2021-12-31 | 2022-01-03 | 30 | 2022-02-02 | [8 empty] | 0 | 0 | 0 | 4300000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 072 | EMAAR-Pkg#162/163- Marassi2
PKG#177 - SWI 07 | 1 | 3 |  | 12082357.79 | 12082357.79 | 0 | 16268974.4395 | 16268974.4395 |  |  |  | 5800000 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 | [8 empty] | 0 | 0 | 0 | 5800000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 073 | EMAAR-Pkg#162/163- Marassi3
PKG#177 - SWI 07 | 1 | 4 |  | 14694850.77 | 14694850.77 | 0 | 17742432.8485 | 17742432.8485 |  |  |  |  | 2022-02-28 | 2022-02-28 | 2022-03-02 | 30 | 2022-04-01 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 074 | EMAAR-Pkg#162/163- Marassi4
PKG#177 - SWI 07 | 1 | 5 |  | 8006098.571 | 8006098.571 | 0 | 7958142.0485 | 7958142.0485 |  |  |  | 9500000 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 | [8 empty] | 0 | 0 | 0 | 9500000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 075 | EMAAR-Pkg#162/163- Marassi5
PKG#177 - SWI 07 | 1 | 6 | 3141613.418 | 14622817.211 | 11481203.793 | 0 | 13427541.4454 | 13427541.4454 |  |  |  | 5000000 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 |  | 31868573.268 |  |  |  | 1025274 |  |  | 0 | 3141613.418 | 31868573.268 | 5000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 076 | EMAAR-Pkg#162/163- Marassi6
PKG#177 - SWI 07 | 1 | 7 | 10847798.8446 | 12998247.66 | 2150448.8154 | 0 | 12964361.5377 | 12964361.5377 |  |  |  | 4000000 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 |  | 42716372.1126 | [6 empty] | 0 | 10847798.8446 | 42716372.1126 | 4000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 077 | EMAAR-Pkg#162/163- Marassi7
PKG#177 - SWI 07 | 1 | 8 |  | 27347974.52 | 27347974.52 | 0 | 22259454.996 | 22259454.996 |  |  |  | 500000 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 | [8 empty] | 0 | 0 | 0 | 500000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 078 | EMAAR-Pkg#162/163- Marassi8
PKG#177 - SWI 07 | 1 | 9 |  | 15911837.121 | 15911837.121 | 0 | 20607532.6031 | 20607532.6031 |  |  |  | 4000000 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 30 | 2022-09-09 | [8 empty] | 0 | 0 | 0 | 4000000 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 079 | EMAAR-Pkg#162/163- Marassi9
PKG#177 - SWI 07 | 1 | 10 |  | 18387668.6001 | 18387668.6001 | 1e-05 | 18192775.4801 | 18192775.4801 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-17 | 30 | 2022-11-16 | [8 empty] | 0 | 0 | 0 | 0 | EMAAR-Pkg#162/163- Marassi |  |  |  | PKG#177 - SWI 0710 | EMAAR-Pkg#162/163- Marassi10
PKG#178 | 1 | 1 |  | 0 | 0 | 3747170.2 | 0 | -3747170.2 | 3747170.2 |  | 1276787.15 | 3747170.2 | 2021-01-31 | 2021-01-25 | 2021-01-25 | 30 | 2021-02-24 | 2021-02-02 | [7 empty] | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1781 | BKG#178-Lagoon Discharge1
PKG#178 | 1 | 2 | 16123744.18 | 15355946.84 | -767797.34 | 13230338.29 | 13230338.292 | 0.002 |  |  | 392599.98 | 13230338.29 | 2021-02-28 | 2021-02-28 | 2021-03-04 | 30 | 2021-04-03 | 2021-04-14 | 16123744.18 | [6 empty] | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1782 | BKG#178-Lagoon Discharge2
PKG#178 | 1 | 3 | 8196011.07 | 7805724.83 | -390286.24 | 6675236.88 | 7952024.0415 | 1276787.1615 |  |  | 887343.85 | 6675236.88 | 2021-03-31 | 2021-03-31 | 2021-04-04 | 30 | 2021-05-04 | 2021-04-28 | 24319755.25 | 1215987.76 | [5 empty] | 50000 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1783 | BKG#178-Lagoon Discharge3
PKG#178 | 1 | 4 | 7478094.91 | 8636178.5 | 1158083.59 | 6081013.29 | 6473613.265 | 392599.975 |  |  |  | 6081013.28 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 30 | 2021-06-04 | 2021-06-03 | 31797850.16 | [6 empty] | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1784 | BKG#178-Lagoon Discharge4
PKG#178 | 1 | 5 | 10300781.8 | 10300781.79 | -0.01 | 9125492.66 | 9666283.6995 | 540791.0395 |  |  |  | 9125492.66 | 2021-05-31 | 2021-06-07 | 2021-06-08 | 30 | 2021-07-08 | 2021-06-21 | 42098631.96 | [6 empty] | 105137.6 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1785 | BKG#178-Lagoon Discharge5
PKG#178 | 1 | 6 | 4524611.34 | 4524611.34 | 0 | 2730279.03 | 2967821.117 | 237542.087 |  |  |  | 2730279.03 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 30 | 2021-08-10 | 2021-09-21 | 46623243.3 | 0 | [5 empty] | 1562612.5 | 4524611.3442 | 46623243.3042 | 4030279.0303 | BKG#178-Lagoon Discharge |  |  |  | PKG#1786 | BKG#178-Lagoon Discharge6
PKG#178 | 1 | 7 | 686559 | 686559 | -7.4506e-09 | 1644401.99 | 1680446.34 | 36044.35 |  |  |  | 1844728.45 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 30 | 2021-12-02 | 2021-12-02 | 47309802.3 | 0 | [5 empty] | 1595537.5 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1787 | BKG#178-Lagoon Discharge7
PKG#178 | 1 | 8 | 1389835.54 | 1389835.52 | -0.02 | 595920.45 | 668886.796 | 72966.346 |  |  |  | 595920.46 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 | 2022-02-28 | 48699637.84 |  |  |  |  | 1278365.495 | 1278365.495 | 0 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1788 | BKG#178-Lagoon Discharge8
PKG#178 | 1 | 9 | 31809.52 | 31809.53 | 0.01 | 289077.6 | 2524652.5565 | 2235574.9565 |  |  |  | 88751.13 | 2022-08-31 | 2022-08-28 | 2022-08-30 | 30 | 2022-09-29 | 2022-10-09 | 48731447.36 |  |  |  |  | 1279200.495 | 1279200.495 | 2370468.93 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#1789 | BKG#178-Lagoon Discharge9
PKG#178 | 1 | 10 | -0.0001 | 0 | 0.0001 | 2235574.97 | 0 | -2235574.97 |  |  |  | 2080200.49 | 2023-01-31 | 2023-01-25 | 2023-05-29 | 30 | 2023-06-28 | 2023-06-02 | 48731447.36 |  | 12630627.58 |  | 413484.78 |  |  | 1769468.93 | 0 | 0 | 0 | BKG#178-Lagoon Discharge |  |  |  | PKG#17810 | BKG#178-Lagoon Discharge10
PKG#205 | 1 | 2 | 1935314 | 0 | -1935314 | 1181605.96 | 0 | -1181605.96 |  |  |  | 1181605.96 | 2022-04-30 | 2022-04-28 | 2022-05-24 | 30 | 2022-06-23 | 2022-05-24 | 1935314 | 0 | 0 |  | 0 | 50801.99 | 50801.99 | 0 | 0 | 0 | 0 | 0 |  |  |  | PKG#2052 | 02
PKG#205 | 1 | 3 | 2048098 | 0 | -2048098 | 1250466.11 | 0 | -1250466.11 |  |  |  | 1250466.11 | 2022-05-31 | 2022-05-31 | 2022-06-13 | 30 | 2022-07-13 | 2022-06-13 | 3983412 |  |  |  | 63808.49 | 104564.5 | 104564.5 | 0 | 0 | 0 | 0 | 0 |  |  |  | PKG#2053 | 03
PKG#220B | 1 | 2 | 12159328.08 | 35084150.1 | 22924822.02 | 8261597.76 | 5980500.04 | -2281097.72 |  |  |  | 8261597.76 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 30 | 2023-07-07 | 2023-06-20 | 12159328.08 |  |  |  |  | 319182.36 | 319182.36 | 0 | 0 | 0 | 0 | SOL Town PKG.220 |  |  |  | PKG#220B2 | SOL Town PKG.2202
PKG#220B | 1 | 3 | 11462411.01 | 1345226.9 | -10117184.11 | 5980500.04 | 348202.56 | -5632297.48 |  |  |  | 5980500.04 | 2023-06-30 | 2023-07-05 | 2023-07-10 | 30 | 2023-08-09 | 2023-08-14 | 23621739.09 |  |  |  |  | 620070.65 | 620070.65 | 1017875 | 0 | 0 | 0 | SOL Town PKG.220 |  |  |  | PKG#220B3 | SOL Town PKG.2203
PKG#220B | 1 | 4 |  | 1274131.45 | 1274131.45 | 2300000 | 1849642.29 | -450357.71 |  |  |  | 2300000 | 2023-07-31 | 2023-08-05 | 2023-08-07 | 30 | 2023-09-06 | [8 empty] | 0 | 0 | 0 | 2300000 | SOL Town PKG.220 |  |  |  | PKG#220B4 | SOL Town PKG.2204
PKG#220B - DP | 1 | 1 |  | 12159328.08 | 12159328.08 | 0 | 8261597.76 | 8261597.76 |  |  |  |  | 2023-05-31 | 2023-05-21 | 2023-05-21 | 30 | 2023-06-20 | [8 empty] | 0 | 0 | 0 | 0 | SOL Town PKG.220 |  |  |  | PKG#220B - DP1 | SOL Town PKG.2201
PKG#45 | 1 | 46 |  | 0 | 0 | 1844931.02 | 0 | -1844931.02 |  |  |  | 1069392.54 | 2018-06-30 | 2018-07-15 | 2018-09-18 |  | 2018-12-15 | 2018-11-21 | 59167173.46 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | PKG#4546 | 046
PKG#58 | 1 | 22 | 0 | 0 | 0 | 327696.29 | 0 | -327696.29 |  |  |  | 317558.66 | 2015-12-31 | 2015-12-29 | 2015-12-29 |  | 2018-11-15 | 2018-10-21 | 4831971.92 | [7 empty] | 0 | 0 | 0 | 0 |  |  |  | PKG#5822 | 022
PKG#85 | 1 | 5 |  | 0 | 0 | 1729285.15 | 0 | -1729285.15 |  |  |  |  | 2018-10-31 | 2018-10-17 | 2018-11-11 | 30 | 2018-12-11 | [9 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#855 | EMAAR-PKG#85-UPTOWN5
PKG#85 | 1 | 6 | 2033193.5852 | 0 | -2033193.5852 | 768766.59 | 0 | -768766.59 |  |  |  | 768766.5752 | 2019-02-28 | 2019-02-28 | 2019-03-09 | 30 | 2019-04-08 | 2019-05-20 | 8147064.8613 | [7 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#856 | EMAAR-PKG#85-UPTOWN6
PKG#85 | 1 | 7 |  | 0 | 0 | 29830.3 | 0 | -29830.3 |  |  |  |  | 2019-05-31 | 2019-05-15 | 2019-06-10 | 30 | 2019-07-10 | [9 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#857 | EMAAR-PKG#85-UPTOWN7
PKG#85 | 1 | 8 |  | 0 | 0 | 1391898.96 | 0 | -1391898.96 |  |  |  |  | 2019-10-31 | 2019-10-11 | 2019-11-18 | 30 | 2019-12-18 | [9 empty] | 0 | 0 | 0 | EMAAR-PKG#85-UPTOWN |  |  |  | PKG#858 | EMAAR-PKG#85-UPTOWN8
PO#11687 | 1 | 1 |  | 0 | 0 | 1090584 | 0 | -1090584 |  |  |  |  | 2018-12-31 | 2019-01-10 | 2019-01-10 | 15 | 2019-01-25 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116871 | 01
PO#11687 | 1 | 2 |  | 0 | 0 | 451528 | 0 | -451528 |  |  |  |  | 2019-02-28 | 2019-02-28 | 2019-02-28 | 15 | 2019-03-15 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116872 | 02
PO#11687 | 1 | 3 |  | 0 | 0 | 293788 | 0 | -293788 |  |  |  |  | 2019-03-31 | 2019-04-14 | 2019-08-22 | 15 | 2019-09-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116873 | 03
PO#11687 | 1 | 5 |  | 0 | 0 | 343200 | 0 | -343200 |  |  |  |  | 2019-11-30 | 2019-12-18 | 2019-12-19 | 15 | 2020-01-03 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PO#116875 | 05
Port Said Silos | 1 | 1 | 9011475.2 | 21214607.02 | 12203131.82 | 37788892.4 | 16089595.0422 | -21699297.3578 | 26540249.4 |  |  | 5248643 | 2022-03-31 | 2022-03-25 | 2022-03-05 | 21 | 2022-03-26 | 2022-04-24 | 9011475.2 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos1 | Port Said Port Silos1
Port Said Silos | 1 | 2 | 2334108.9048 | 1883535.14 | -450573.7648 | 21773106 | 1586748.547 | -20186357.453 | 15000000 |  |  | 1688672.941 | 2022-04-30 | 2022-04-25 | 2022-04-28 | 21 | 2022-05-19 | 2022-05-17 | 11345584.1048 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos2 | Port Said Port Silos2
Port Said Silos | 1 | 3 |  | 9057943.58 | 9057943.58 | 14623869 | 14589360.9503 | -34508.0497 |  |  |  |  | 2022-05-31 | 2022-05-25 | 2022-06-02 | 21 | 2022-06-23 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos3 | Port Said Port Silos3
Port Said Silos | 1 | 4 |  | 7714268.4141 | 7714268.4141 | 22560435 | 16638639.8855 | -5921795.1145 |  |  |  |  | 2022-06-30 | 2022-06-29 | 2022-06-29 | 21 | 2022-07-20 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos4 | Port Said Port Silos4
Port Said Silos | 1 | 5 | 5318356.3714 | 8597357.386 | 3279001.0146 | 14009921 | 14928020.4333 | 918099.4333 |  |  |  | 4009921 | 2022-07-31 | 2022-07-31 | 2022-08-02 | 21 | 2022-08-23 | 2022-08-09 | 25985299.3429 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos5 | Port Said Port Silos5
Port Said Silos | 1 | 6 | 9017880.2762 | 10082374.64 | 1064494.3638 | 21842722 | 19981317.606 | -1861404.394 |  |  |  | 6842722 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 21 | 2022-09-21 | 2022-09-13 | 35003179.619 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos6 | Port Said Port Silos6
Port Said Silos | 1 | 7 | 4021476.8571 | 9573941.61 | 5552464.7529 | 3061822 | 44244322.128 | 41182500.128 |  |  |  | 3061822 | 2022-09-30 | 2022-09-30 | 2022-10-02 | 21 | 2022-10-23 | 2022-10-18 | 39024656.4762 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos7 | Port Said Port Silos7
Port Said Silos | 1 | 8 | 22573115.9429 | 25167994.38 | 2594878.4371 | 17260533 | 29006884.597 | 11746351.597 |  |  |  | 17260533 | 2022-10-31 | 2022-10-31 | 2022-11-07 | 21 | 2022-11-28 | 2022-11-21 | 61597772.419 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos8 | Port Said Port Silos8
Port Said Silos | 1 | 9 | 3139225.2286 | 3139228.09 | 2.8614 | 2370710 | 2756360.9335 | 385650.9335 |  |  |  | 2370710 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 21 | 2022-12-26 | 2022-12-19 | 64736997.6476 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos9 | Port Said Port Silos9
Port Said Silos | 1 | 10 | 8366928.5333 | 8366928.53 | -0.0033333 | 6384571 | 7412449.0665 | 1027878.0665 |  |  |  | 6384571 | 2022-12-31 | 2022-12-30 | 2023-01-01 | 21 | 2023-01-22 | 2023-01-22 | 73103926.19 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos10 | Port Said Port Silos10
Port Said Silos | 1 | 11 | 5057462.5238 | 5057462.52 | -0.0038095 | 3852337 | 4473647.986 | 621310.986 |  |  |  | 3852337 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-02-15 | 78161388.7138 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos11 | Port Said Port Silos11
Port Said Silos | 1 | 12 | 2086813.5333 | 5974560.53 | 3887746.9967 | 1587432 | 1843797.0112 | 256365.0112 |  |  |  | 1587432 | 2023-02-28 | 2023-02-28 | 2023-03-01 | 21 | 2023-03-22 | 2023-03-20 | 80248202.2471 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos12 | Port Said Port Silos12
Port Said Silos | 1 | 13 | 612060.8329 | 612060 | -0.83286 | 460093 | 535282.8844 | 75189.8844 |  |  |  | 451211.246 | 2023-03-31 | 2023-03-31 | 2023-04-02 | 21 | 2023-04-23 | 2023-04-02 | 80860263.08 | [6 empty] | 0 | 612060.8329 | 80860263.08 | 451211.246 | Port Said Port Silos |  |  |  | Port Said Silos13 | Port Said Port Silos13
Port Said Silos | 1 | 14 |  | 2803566.38 | 2803566.38 | 2136487 | 2480905.1552 | 344418.1552 |  |  |  |  | 2023-04-30 | 2023-04-30 | 2023-05-02 | 21 | 2023-05-23 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos14 | Port Said Port Silos14
Port Said Silos | 1 | 15 | 10044463.5619 | 10044463.56 | -0.0019048 | 7663669 | 8897631.4024 | 1233962.4024 |  |  |  | 7663669 | 2023-05-31 | 2023-05-30 | 2023-06-03 | 21 | 2023-06-24 | 2023-07-05 | 93708293.0229 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos15 | Port Said Port Silos15
Port Said Silos | 1 | 16 | 12501707.0667 | 12501707.07 | 0.0033333 | 9649102 | 11072420.0228 | 1423318.0228 |  |  |  | 9649102 | 2023-06-30 | 2023-06-30 | 2023-07-08 | 21 | 2023-07-29 | 2023-07-17 | 106210000.0895 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos16 | Port Said Port Silos16
Port Said Silos | 1 | 17 | 7676679.5524 | 7676679.55 | -0.002381 | 5738977 | 6794573.092 | 1055596.092 |  |  |  | 5738977 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 21 | 2023-08-21 | 2023-08-15 | 113886679.6419 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos17 | Port Said Port Silos17
Port Said Silos | 1 | 18 | 7866196.5143 | 7866196.51 | -0.0042857 | 2991787 | 3958149.4004 | 966362.4004 |  |  |  | 2991787 | 2023-08-31 | 2023-08-31 | 2023-09-03 | 21 | 2023-09-24 | 2023-10-03 | 121752876.1562 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos18 | Port Said Port Silos18
Port Said Silos | 1 | 19 | 17118439.2571 | 17118439.26 | 0.0028571 | 12748959 | 14851957.9104 | 2102998.9104 |  |  |  | 12748959 | 2023-09-30 | 2023-09-30 | 2023-10-01 | 21 | 2023-10-22 | 2023-10-16 | 138871315.4133 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos19 | Port Said Port Silos19
Port Said Silos | 1 | 20 | 12988784 | 12988783.81 | -0.19 | 6593857 | 8189528.9592 | 1595671.9592 |  |  |  | 6593857 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 21 | 2023-11-22 | 2023-11-22 | 151860099.4133 | [6 empty] | 0 | 13732229.2267 | 152603544.64 | 10123399.3859 | Port Said Port Silos |  |  |  | Port Said Silos20 | Port Said Port Silos20
Port Said Silos | 1 | 21 | 15886446.6476 | 15886445.71 | -0.93762 | 11818794 | 13770443.8984 | 1951649.8984 |  |  |  | 11818794 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 21 | 2023-12-21 | 2023-12-23 | 167746546.061 | [6 empty] | 0 | 15886446.6567 | 167746546.07 | 11711488.4753 | Port Said Port Silos |  |  |  | Port Said Silos21 | Port Said Port Silos21
Port Said Silos | 1 | 22 | 6713332.6667 | 6713332.67 | 0.0033333 | 4826684 | 5651416.0035 | 824732.0035 |  |  |  | 4826684 | 2023-12-31 | 2023-12-13 | 2023-12-14 | 21 | 2024-01-04 | 2023-12-27 | 174459878.7276 | [6 empty] | 0 | 6713332.669 | 174459878.73 | 4949068.8436 | Port Said Port Silos |  |  |  | Port Said Silos22 | Port Said Port Silos22
Port Said Silos | 1 | 23 | 3587901.4571 | 3587901.46 | 0.0028571 | 2411082.19 | 2851855.8684 | 440773.6784 |  |  |  | 2411082.19 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 21 | 2024-01-25 | 2024-01-18 | 178047780.1848 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos23 | Port Said Port Silos23
Port Said Silos | 1 | 24 | 4764115.7714 | 4764115.24 | -0.53143 | 3306186 | 3891455.9996 | 585269.9996 |  |  |  | 3306186 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 21 | 2024-02-27 | 2024-02-21 | 182811895.9562 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos24 | Port Said Port Silos24
Port Said Silos | 1 | 25 | 4504742.6762 | 4504741.9 | -0.77619 | 3280048 | 3280047.566 | -0.434 |  |  |  | 3280048 | 2024-02-29 | 2024-02-29 | 2024-03-04 | 21 | 2024-03-25 | 2024-04-07 | 187316638.6324 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos25 | Port Said Port Silos25
Port Said Silos | 1 | 26 | 2227046.781 | 2227046.78 | -0.00095238 | 426108 | 426108.0312 | 0.0312 |  |  |  | 426108 | 2024-03-31 | 2024-03-31 | 2024-04-04 | 21 | 2024-04-25 | 2024-05-07 | 189543685.4133 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos26 | Port Said Port Silos26
Port Said Silos | 1 | 27 | 1522665.14 | 1478728.71 | -43936.43 | 0 | 0 | 0 |  |  |  | 0.0001 | 2024-04-30 | 2024-05-01 | 2024-05-01 | 21 | 2024-05-22 | 2024-05-27 | 191066350.5533 | [6 empty] | 0 | 1478728.71 | 191022414.13 | 1090118.805 | Port Said Port Silos |  |  |  | Port Said Silos27 | Port Said Port Silos27
Port Said Silos | 1 | 28 | 3379589.9429 | 3379589.94 | -0.0028571 | 1239632 | 2663473.997 | 1423841.997 |  |  |  | 1239632 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 21 | 2024-06-23 | 2024-07-01 | 194445940.4962 | [6 empty] | 0 | 3335653.5067 | 194402004.06 | 2459043.7651 | Port Said Port Silos |  |  |  | Port Said Silos28 | Port Said Port Silos28
Port Said Silos | 1 | 29 | 2107663.7333 | 2107663.51 | -0.22333 | 337130 | 596055.2424 | 258925.2424 |  |  |  | 337130 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 21 | 2024-07-28 | 2024-08-07 | 196553604.2295 | [6 empty] | 0 | 2063726.5038 | 196509667 | 1521379.1786 | Port Said Port Silos |  |  |  | Port Said Silos29 | Port Said Port Silos29
Port Said Silos | 1 | 30 | 3191368.2381 | 3191368.24 | 0.0019048 | 100641 | 100639.5696 | -1.4304 |  |  |  | 100641 | 2024-07-31 | 2024-07-31 | 2024-08-03 | 21 | 2024-08-24 | 2024-08-22 | 199744972.4676 | [6 empty] | 0 | 3191369.04 | 199701036.04 | 2352677.2563 | Port Said Port Silos |  |  |  | Port Said Silos30 | Port Said Port Silos30
Port Said Silos | 1 | 31 | 2906595.6404 | 3155732.38 | 249136.7396 | 727554 | 2284436.52 | 1556882.52 |  |  |  | 727554 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 202651568.108 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos31 | Port Said Port Silos31
Port Said Silos | 1 | 32 | 4167368.41 | 3968922.29 | -198446.12 | 2193035.35 | 2296974.7655 | 103939.4155 |  |  |  | 2193035.35 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-11-03 | 206818936.518 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos32 | Port Said Port Silos32
Port Said Silos | 1 | 33 |  | 4525360.97 | 4525360.97 | 2711136 | 2711136 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos33 | Port Said Port Silos33
Port Said Silos - Foreigner Supply | 1 | 1 | 5539353.23 | 21214607.02 | 15675253.79 | 5206992 | 16089595.0422 | 10882603.0422 |  |  |  | 5206992.0362 | 2023-09-30 | 2023-09-30 | 2023-09-24 | 21 | 2023-10-15 | 2023-11-06 | 5539353.23 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Foreigner Supply1 | Port Said Port Silos1
Port Said Silos - Foreigner Supply | 1 | 2 |  | 1883535.14 | 1883535.14 | 775509.45 | 1586748.547 | 811239.097 |  |  |  |  | 2023-10-31 | 2023-10-31 | 2023-12-05 | 21 | 2023-12-26 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Foreigner Supply2 | Port Said Port Silos2
Port Said Silos - Local Supply | 1 | 1 | 673851.6 | 21214607.02 | 20540755.42 | 655657.61 | 16089595.0422 | 15433937.4322 |  |  |  | 438003.54 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-03-16 | 673851.6 | [6 empty] | 0 | 673851.6 | 673851.6 | 438003.54 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply1 | Port Said Port Silos1
Port Said Silos - Local Supply | 1 | 2 | 1194976.6491 | 1883535.14 | 688558.4909 | 1162711.94 | 1586748.547 | 424036.607 |  |  |  | 1162711.94 | 2023-09-30 | 2023-09-30 | 2023-10-18 | 21 | 2023-11-08 | 2023-11-06 | 1868828.2491 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply2 | Port Said Port Silos2
Port Said Silos - Local Supply | 1 | 3 | 3085091.6316 | 9057943.58 | 5972851.9484 | 2307930.88 | 14589360.9503 | 12281430.0703 |  |  |  | 2307930.88 | 2024-02-29 | 2024-02-29 | 2024-03-13 | 21 | 2024-04-03 | 2024-03-31 | 4953919.8807 | [6 empty] | 0 | 3085091.6309 | 4953919.88 | 2005309.5601 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply3 | Port Said Port Silos3
Port Said Silos - Local Supply | 1 | 4 | 4365732.3333 | 7714268.4141 | 3348536.0808 | 3416710 | 16638639.8855 | 13221929.8855 |  |  |  | 3416710 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 21 | 2024-04-28 | 2024-05-07 | 9319652.214 | [6 empty] | 0 | 4365732.3293 | 9319652.21 | 2837726.014 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply4 | Port Said Port Silos4
Port Said Silos - Local Supply | 1 | 5 | 3278709.2807 | 8597357.386 | 5318648.1053 | 2565984 | 14928020.4333 | 12362036.4333 |  |  |  | 2565984 | 2024-04-30 | 2024-04-30 | 2024-05-12 | 21 | 2024-06-02 | 2024-05-27 | 12598361.4947 | [6 empty] | 0 | 3278709.276 | 12598361.49 | 2131161.0294 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply5 | Port Said Port Silos5
Port Said Silos - Local Supply | 1 | 6 | 1064669.3947 | 10082374.64 | 9017705.2453 | 833240 | 19981317.606 | 19148077.606 |  |  |  | 833240 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 21 | 2024-06-30 | 2024-07-01 | 13663030.8895 | [6 empty] | 0 | 1064669.3953 | 13663030.89 | 692035.1069 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply6 | Port Said Port Silos6
Port Said Silos - Local Supply | 1 | 7 | 5552464.7544 | 9573941.61 | 4021476.8556 | 4345468 | 44244322.128 | 39898854.128 |  |  |  | 4345468 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 21 | 2024-08-06 | 2024-08-06 | 19215495.6439 | [6 empty] | 0 | 5552464.1105 | 19215495 | 3609101.6718 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply7 | Port Said Port Silos7
Port Said Silos - Local Supply | 1 | 8 | 2594878.4386 | 25167994.38 | 22573115.9414 | 1794648.84 | 29006884.597 | 27212235.757 |  |  |  | 1794648.84 | 2024-07-31 | 2024-07-31 | 2024-08-18 | 21 | 2024-09-08 | 2024-09-01 | 21810374.0825 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply8 | Port Said Port Silos8
Port Said Silos - Local Supply | 1 | 9 | 3231641.7018 | 3139228.09 | -92413.6118 | 2529147 | 2756360.9335 | 227213.9335 |  |  |  | 2529147 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 25042015.7842 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply9 | Port Said Port Silos9
Port Said Silos - Local Supply | 1 | 10 | 622795.91 | 8366928.53 | 7744132.62 | 494192 | 7412449.0665 | 6918257.0665 |  |  |  | 494192 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-10-03 | 25664811.6942 | [6 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply10 | Port Said Port Silos10
Port Said Silos - Local Supply | 1 | 11 |  | 5057462.52 | 5057462.52 | 833789.82 | 4473647.986 | 3639858.166 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 | [8 empty] | 0 | 0 | 0 | 0 | Port Said Port Silos |  |  |  | Port Said Silos - Local Supply11 | Port Said Port Silos11
PSP Substation | 1 | 2 | 1669926.8 | 0 | -1669926.8 | 1160599 | 0 | -1160599 |  |  |  | 1244095.47 | 2018-06-30 | 2018-07-03 | 2018-07-05 | 30 | 2018-08-04 | 2018-07-22 | 1669926.8 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation2 | 02
PSP Substation | 1 | 3 | 2696322.9906 | 0 | -2696322.9906 | 1834172.07 | 0 | -1834172.07 |  |  |  | 1834172.07 | 2018-07-31 | 2018-08-05 | 2018-08-06 | 30 | 2018-09-05 | 2018-10-11 | 4366249.7906 | [6 empty] | 0 | 2696322.9906 | 4366249.7906 | 1834172.07 | 0 |  |  |  | PSP Substation3 | 03
PSP Substation | 1 | 4 |  | 0 | 0 | 1268627.7 | 0 | -1268627.7 |  |  |  |  | 2018-08-31 | 2018-09-10 | 2018-09-11 | 30 | 2018-10-11 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation4 | 04
PSP Substation | 1 | 5 | 6439927.8 | 0 | -6439927.8 | 3991290.99 | 0 | -3991290.99 |  |  |  | 5046458.33 | 2018-09-30 | 2018-10-08 | 2018-10-08 | 30 | 2018-11-07 | 2018-10-16 | 12694557.6 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation5 | 05
PSP Substation | 1 | 6 | 4012970.52 | 0 | -4012970.52 | 3047586.1 | 0 | -3047586.1 |  |  |  | 3047586.1 | 2018-10-31 | 2018-11-10 | 2018-11-11 | 30 | 2018-12-11 | 2018-11-21 | 16707528.12 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation6 | 06
PSP Substation | 1 | 7 | 3355601.28 | 0 | -3355601.28 | 1780094.35 | 0 | -1780094.35 |  |  |  | 2548357.58 | 2018-11-30 | 2018-12-10 | 2018-12-10 | 30 | 2019-01-09 | 2019-01-06 | 20063129.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation7 | 07
PSP Substation | 1 | 8 | 2786776.25 | 0 | -2786776.25 | 1829713.21 | 0 | -1829713.21 |  |  |  | 2116372.52 | 2018-12-31 | 2019-01-12 | 2019-01-16 | 30 | 2019-02-15 | 2019-02-05 | 22849905.65 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation8 | 08
PSP Substation | 1 | 9 | 2055054.9 | 0 | -2055054.9 | 1314287.28 | 0 | -1314287.28 |  |  |  | 1560678.78 | 2019-01-31 | 2019-02-10 | 2019-02-23 | 30 | 2019-03-25 | 2019-04-11 | 24904960.55 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation9 | 09
PSP Substation | 1 | 10 | 4978707.75 | 0 | -4978707.75 | 3264225.8 | 0 | -3264225.8 |  |  |  | 3808343.08 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-23 | 29883668.3 | [6 empty] | 0 | 4978707.75 | 29883668.3 | 3808343.08 | 0 |  |  |  | PSP Substation10 | 010
PSP Substation | 1 | 11 |  | 0 | 0 | 2606365.14 | 0 | -2606365.14 |  |  |  |  | 2019-06-30 | 2019-06-25 | 2019-12-22 | 30 | 2020-01-21 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation11 | 011
PSP Substation | 1 | 12 | 54510.7209 | 0 | -54510.7209 | 28515 | 0 | -28515 |  |  |  | 28515 | 2019-06-30 | 2019-06-25 | 2020-12-06 | 30 | 2021-01-05 | 2020-12-09 | 32341773.9509 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | PSP Substation12 | 012
Rabigh Ext. - Piles | 1 | 1 | 1098993.1 | 824244.82 | -274748.28 | 947881.6 | 2843644.65 | 1895763.05 |  |  |  | 947881.6 | 2024-02-29 | 2024-02-29 | 2024-03-05 | 57 | 2024-05-01 | 2024-03-18 | 1098993.1 |  |  |  |  | 54949.66 |  | 0 | 1098993.1 | 1098993.1 | 947881.6 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles1 | Rabigh PP - Piling Works1
Rabigh Ext. - Piles | 1 | 2 | 1361202.3 | 1020901.72 | -340300.58 | 1174037 | 3091630.75 | 1917593.75 |  |  |  | 1174036.98 | 2024-04-30 | 2024-04-24 | 2024-04-24 | 57 | 2024-06-20 | 2024-05-02 | 2460195.4 |  |  |  |  | 123009.77 |  | 0 | 1361202.3 | 2460195.4 | 1174036.98 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles2 | Rabigh PP - Piling Works2
Rabigh Ext. - Piles | 1 | 3 |  | 840198 | 840198 | 966227 | 2898683.1 | 1932456.1 |  |  |  |  | 2024-04-30 | 2024-05-14 | 2024-05-14 | 57 | 2024-07-10 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles3 | Rabigh PP - Piling Works3
Rabigh Ext. - Piles | 1 | 4 | 2071949.5 | 1553962.12 | -517987.38 | 1787056 | 5361169.32 | 3574113.32 |  |  |  | 1787056.4438 | 2024-05-31 | 2024-06-01 | 2024-06-10 | 57 | 2024-08-06 | 2024-07-08 | 5652409 |  |  |  |  | 282620.45 |  | 0 | 2071949.5 | 5652409 | 1787056.4437 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles4 | Rabigh PP - Piling Works4
Rabigh Ext. - Piles | 1 | 5 |  | 983150.55 | 983150.55 | 1130623 | 3391869.39 | 2261246.39 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-10 | 57 | 2024-09-05 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles5 | Rabigh PP - Piling Works5
Rabigh Ext. - Piles | 1 | 6 |  | 1751171.77 | 1751171.77 | 2013847.54 | 6041514.12 | 4027666.58 |  |  |  |  | 2024-07-31 | 2024-07-31 | 2024-08-14 | 57 | 2024-10-10 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles6 | Rabigh PP - Piling Works6
Rabigh Ext. - Piles | 1 | 7 |  | 2703528.67 | 2703528.67 | 0 | 9327173.91 | 9327173.91 |  |  |  |  | 2024-08-31 | 2024-08-31 | 2024-09-07 | 57 | 2024-11-03 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles7 | Rabigh PP - Piling Works7
Rabigh Ext. - Piles | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-30 | 2024-10-19 | 57 | 2024-12-15 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh PP - Piling Works |  |  |  | Rabigh Ext. - Piles8 | Rabigh PP - Piling Works8
Rabigh Ext. -Building | 1 | 1 | 2561755.35 | 2313265.08 | -248490.27 | 2660254.84 | 7980764.49 | 5320509.65 |  |  |  | 2283164.46 | 2024-06-30 | 2024-06-30 | 2024-07-09 | 75 | 2024-09-22 | 2024-07-10 | 2561755.35 |  |  |  |  | 128087.77 |  | 0 | 0 | 0 | 0 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building1 | Rabigh CCPP-Civil1
Rabigh Ext. -Building | 1 | 2 | 5727560.34 | 4110954.32 | -1616606.02 | 4708047.77 | 14182792.41 | 9474744.64 |  |  |  | 4957387.2204 | 2024-07-31 | 2024-07-31 | 2024-08-05 | 75 | 2024-10-19 | 2024-08-25 | 8289315.69 |  |  |  |  | 414465.7845 |  | 0 | 5727560.34 | 8289315.69 | 4957387.2204 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building2 | Rabigh CCPP-Civil2
Rabigh Ext. -Building | 1 | 3 | 5121658.33 | 3935285.21 | -1186373.12 | 0 | 18102311.96 | 18102311.96 |  |  |  | 4088042.3344 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 75 | 2024-11-19 | 2024-09-19 | 13410974.02 |  |  |  |  | 670548.701 |  | 0 | 5121658.33 | 13410974.02 | 4088042.3344 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building3 | Rabigh CCPP-Civil3
Rabigh Ext. -Building | 1 | 4 | 6246650.22 | 0 | -6246650.22 | 0 | 0 | 0 |  |  |  | 4796196.0024 | 2024-09-30 | 2024-09-30 | 2024-10-06 | 75 | 2024-12-20 | 2024-10-23 | 19657624.24 |  |  |  |  | 982881.212 |  | 0 | 6246650.22 | 19657624.24 | 4796196.0024 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building4 | Rabigh CCPP-Civil4
Rabigh Ext. -Building | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-31 | 2024-11-03 | 75 | 2025-01-17 | [8 empty] | 0 | 0 | 0 | 0 | Rabigh CCPP-Civil |  |  |  | Rabigh Ext. -Building5 | Rabigh CCPP-Civil5
Radamis-Concrete | 1 | 1 |  | 0 | 0 | 10000000 | 0 | -10000000 | 10000000 |  |  |  | 2022-04-30 | 2022-04-25 | 2022-04-25 | 30 | 2022-05-25 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete1 | 01
Radamis-Concrete | 1 | 2 |  | 0 | 0 | 10000000 | 0 | -10000000 | 10000000 |  |  |  | 2022-05-31 | 2022-05-25 | 2022-05-26 | 30 | 2022-06-25 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete2 | 02
Radamis-Concrete | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-06-30 | 2022-07-07 | 2022-07-03 | 30 | 2022-08-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete3 | 03
Radamis-Concrete | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-07-31 | 2022-07-31 | 2022-08-14 | 30 | 2022-09-13 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete4 | 04
Radamis-Concrete | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete5 | 05
Radamis-Concrete | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete6 | 06
Radamis-Concrete | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete7 | 07
Radamis-Concrete | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete8 | 08
Radamis-Concrete | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-01-31 | 2023-01-25 | 2023-01-30 | 30 | 2023-03-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete9 | 09
Radamis-Concrete | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete10 | 010
Radamis-Concrete | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete11 | 011
Radamis-Concrete | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete12 | 012
Radamis-Concrete | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete13 | 013
Radamis-Concrete | 1 | 14 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete14 | 014
Radamis-Concrete | 1 | 15 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete15 | 015
Radamis-Concrete | 1 | 16 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete16 | 016
Radamis-Concrete | 1 | 17 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete17 | 017
Radamis-Concrete | 1 | 18 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete18 | 018
Radamis-Concrete | 1 | 19 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete19 | 019
Radamis-Concrete | 1 | 20 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete20 | 020
Radamis-Concrete | 1 | 21 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete21 | 021
Radamis-Concrete | 1 | 22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete22 | 022
Radamis-Concrete | 1 | 23 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete23 | 023
Radamis-Concrete | 1 | 24 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete24 | 024
Radamis-Concrete | 1 | 25 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete25 | 025
Radamis-Concrete | 1 | 26 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete26 | 026
Radamis-Concrete | 1 | 27 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete27 | 027
Radamis-Concrete | 1 | 28 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete28 | 028
Radamis-Concrete | 1 | 29 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete29 | 029
Radamis-Concrete | 1 | 30 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Concrete30 | 030
Radamis-H1 Main Builidng | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng1 | 01
Radamis-H1 Main Builidng | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng2 | 02
Radamis-H1 Main Builidng | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng3 | 03
Radamis-H1 Main Builidng | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng4 | 04
Radamis-H1 Main Builidng | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng5 | 05
Radamis-H1 Main Builidng | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng6 | 06
Radamis-H1 Main Builidng | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng7 | 07
Radamis-H1 Main Builidng | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng8 | 08
Radamis-H1 Main Builidng | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng9 | 09
Radamis-H1 Main Builidng | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng10 | 010
Radamis-H1 Main Builidng | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng11 | 011
Radamis-H1 Main Builidng | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng12 | 012
Radamis-H1 Main Builidng | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-H1 Main Builidng13 | 013
Radamis-Rooms Fitout | 1 | 1 |  | 0 | 0 | 250000 | 0 | -250000 | 250000 |  |  |  | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout1 | 01
Radamis-Rooms Fitout | 1 | 2 |  | 0 | 0 | 500000 | 0 | -500000 | 500000 |  |  |  | 2023-07-31 | 2023-07-20 | 2023-08-05 | 30 | 2023-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout2 | 02
Radamis-Rooms Fitout | 1 | 3 |  | 0 | 0 | 15000000 | 0 | -15000000 | 15000000 |  |  |  | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout3 | 03
Radamis-Rooms Fitout | 1 | 4 |  | 0 | 0 | 4000000 | 0 | -4000000 | 4000000 |  |  |  | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout4 | 04
Radamis-Rooms Fitout | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout5 | 05
Radamis-Rooms Fitout | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout6 | 06
Radamis-Rooms Fitout | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout7 | 07
Radamis-Rooms Fitout | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-07 | 30 | 2024-03-08 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout8 | 08
Radamis-Rooms Fitout | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout9 | 09
Radamis-Rooms Fitout | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout10 | 010
Radamis-Rooms Fitout | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout11 | 011
Radamis-Rooms Fitout | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout12 | 012
Radamis-Rooms Fitout | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout13 | 013
Radamis-Rooms Fitout | 1 | 14 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout14 | 014
Radamis-Rooms Fitout | 1 | 15 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout15 | 015
Radamis-Rooms Fitout | 1 | 16 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout16 | 016
Radamis-Rooms Fitout | 1 | 17 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Rooms Fitout17 | 017
Radamis-Villas Finishes | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes1 | 01
Radamis-Villas Finishes | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes2 | 02
Radamis-Villas Finishes | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes3 | 03
Radamis-Villas Finishes | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes4 | 04
Radamis-Villas Finishes | 1 | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-01-31 | 2023-01-30 | 2023-01-30 | 30 | 2023-03-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes5 | 05
Radamis-Villas Finishes | 1 | 6 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes6 | 06
Radamis-Villas Finishes | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes7 | 07
Radamis-Villas Finishes | 1 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes8 | 08
Radamis-Villas Finishes | 1 | 9 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes9 | 09
Radamis-Villas Finishes | 1 | 10 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes10 | 010
Radamis-Villas Finishes | 1 | 11 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes11 | 011
Radamis-Villas Finishes | 1 | 12 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes12 | 012
Radamis-Villas Finishes | 1 | 13 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes13 | 013
Radamis-Villas Finishes | 1 | 14 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes14 | 014
Radamis-Villas Finishes | 1 | 15 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes15 | 015
Radamis-Villas Finishes | 1 | 16 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes16 | 016
Radamis-Villas Finishes | 1 | 17 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes17 | 017
Radamis-Villas Finishes | 1 | 18 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes18 | 018
Radamis-Villas Finishes | 1 | 19 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes19 | 019
Radamis-Villas Finishes | 1 | 20 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes20 | 020
Radamis-Villas Finishes | 1 | 21 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes21 | 021
Radamis-Villas Finishes | 1 | 22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes22 | 022
Radamis-Villas Finishes | 1 | 23 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes23 | 023
Radamis-Villas Finishes | 1 | 24 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes24 | 024
Radamis-Villas Finishes | 1 | 25 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes25 | 025
Radamis-Villas Finishes | 1 | 26 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Radamis-Villas Finishes26 | 026
Red Sea Museum | 1 | 1 | 3172518.7149 | 2538014.97 | -634503.7449 | 5218717 | 8756151.66 | 3537434.66 |  |  |  | 3648396.5221 | 2024-04-30 | 2024-04-30 | 2024-05-23 | 70 | 2024-08-01 | 2024-05-23 | 3172518.7149 | [6 empty] | 0 | 3172518.7149 | 3172518.7149 | 3648396.5221 | Red Sea Museum-Bab El-Bunt |  |  |  | Red Sea Museum1 | Red Sea Museum-Bab El-Bunt1
Red Sea Museum | 1 | 2 | 2298644.2851 | 1838915.59 | -459728.6951 | 4414752.93 | 6344258.76 | 1929505.83 |  |  |  | 2114752.93 | 2024-05-31 | 2024-05-31 | 2024-05-23 | 70 | 2024-08-01 | 2024-08-21 | 5471163 |  |  |  |  | 114932 | 114932 | 0 | 2298644.2851 | 5471163 | 2114752.93 | Red Sea Museum-Bab El-Bunt |  |  |  | Red Sea Museum2 | Red Sea Museum-Bab El-Bunt2
Red Sea Museum | 1 | 3 | 1331566 | 1065253.06 | -266312.94 | 4443406 | 3675123.09 | -768282.91 |  |  |  | 1225041 | 2024-08-31 | 2024-09-02 | 2024-09-02 | 70 | 2024-11-11 | 2024-09-02 | 6802729 | [6 empty] | 0 | 1331566 | 6802729 | 1225041 | Red Sea Museum-Bab El-Bunt |  |  |  | Red Sea Museum3 | Red Sea Museum-Bab El-Bunt3
Ring Road - El Marg | 2 | 1 |  | 82038369.78 | 82038369.78 | 45719198.4 | 63763876.2605 | 18044677.8605 |  |  |  |  | 2021-02-28 | 2021-02-20 | 2021-02-20 | 60 | 2021-04-21 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg1 | RING ROAD MARYOTIA EXPANSION1
Ring Road - El Marg | 2 | 2 |  | 33380372.87 | 33380372.87 | 9576635.3 | 19829292.129 | 10252656.829 |  |  |  |  | 2021-03-31 | 2021-04-15 | 2021-04-15 | 60 | 2021-06-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg2 | RING ROAD MARYOTIA EXPANSION2
Ring Road - El Marg | 2 | 3 |  | 28745170.99 | 28745170.99 | 13773926.1 | 25943818.8695 | 12169892.7695 |  |  |  |  | 2021-04-30 | 2021-05-15 | 2021-05-15 | 60 | 2021-07-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg3 | RING ROAD MARYOTIA EXPANSION3
Ring Road - El Marg | 2 | 4 |  | 11371133.17 | 11371133.17 | 4525661.3 | 10132951.9 | 5607290.6 |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-08 | 60 | 2021-08-07 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg4 | RING ROAD MARYOTIA EXPANSION4
Ring Road - El Marg | 2 | 5 |  | 15036563.72 | 15036563.72 | 2097964.3 | 8684506.216 | 6586541.916 |  |  |  |  | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg5 | RING ROAD MARYOTIA EXPANSION5
Ring Road - El Marg | 2 | 6 |  | 8863613 | 8863613 | 1156719 | 7129991.824 | 5973272.824 |  |  |  |  | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg6 | RING ROAD MARYOTIA EXPANSION6
Ring Road - El Marg | 2 | 7 |  | 32591663.95 | 32591663.95 | 2151897.3 | 4667862.096 | 2515964.796 |  |  |  | 25237352 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | [8 empty] | 0 | 0 | 0 | 25237352 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg7 | RING ROAD MARYOTIA EXPANSION7
Ring Road - El Marg | 2 | 8 | 4446069.4 | 7329890.16 | 2883820.76 | 3742254.85 | 6443416.8 | 2701161.95 |  |  |  | 3601316.214 | 2021-09-30 | 2021-09-30 | 2021-10-05 | 60 | 2021-12-04 | 2021-10-24 | 142263915.035 | [6 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg8 | RING ROAD MARYOTIA EXPANSION8
Ring Road - El Marg | 2 | 9 | 4763028.235 | 14419705.47 | 9656677.235 | 4020500.85 | 7876622.257 | 3856121.407 |  |  |  | 3858052.8704 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 60 | 2022-01-05 | 2021-11-24 | 147026943.27 | [6 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg9 | RING ROAD MARYOTIA EXPANSION9
Ring Road - El Marg | 2 | 10 | 3312818.46 | 20599647.58 | 17286829.12 | 2795847.4 | 13738602.73 | 10942755.33 |  |  |  | 2683382.9526 | 2021-11-30 | 2021-11-30 | 2021-12-08 | 60 | 2022-02-06 | 2022-01-25 | 150339761.73 | [6 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg10 | RING ROAD MARYOTIA EXPANSION10
Ring Road - El Marg | 2 | 11 |  | 29094868.16 | 29094868.16 | 0.0001 | 3708396.57 | 3708396.5699 |  |  |  |  | 2022-01-31 | 2022-01-31 | 2022-02-02 | 60 | 2022-04-03 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg11 | RING ROAD MARYOTIA EXPANSION11
Ring Road - El Marg | 2 | 12 |  | 19159167.62 | 19159167.62 | 0.0001 | 18678770.82 | 18678770.8199 |  |  |  |  | 2022-02-28 | 2022-02-28 | 2022-03-02 | 60 | 2022-05-01 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg12 | RING ROAD MARYOTIA EXPANSION12
Ring Road - El Marg | 2 | 13 |  | 53815173.27 | 53815173.27 | 0.0001 | 41457209.53 | 41457209.5299 |  |  |  |  | 2022-05-31 | 2022-05-30 | 2022-06-02 | 60 | 2022-08-01 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - El Marg13 | RING ROAD MARYOTIA EXPANSION13
Ring Road - Mounib | 2 | 1 |  | 82038369.78 | 82038369.78 | 26333646.7391 | 63763876.2605 | 37430229.5214 |  |  |  |  | 2020-08-31 | 2020-08-31 | 2020-08-31 | 60 | 2020-10-30 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib1 | RING ROAD MARYOTIA EXPANSION1
Ring Road - Mounib | 2 | 2 |  | 33380372.87 | 33380372.87 | 7157243.6 | 19829292.129 | 12672048.529 |  |  |  |  | 2020-10-31 | 2020-10-31 | 2020-10-31 | 60 | 2020-12-30 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib2 | RING ROAD MARYOTIA EXPANSION2
Ring Road - Mounib | 2 | 3 |  | 28745170.99 | 28745170.99 | 10759736.15 | 25943818.8695 | 15184082.7195 |  |  |  |  | 2020-12-31 | 2020-12-31 | 2020-12-31 | 60 | 2021-03-01 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib3 | RING ROAD MARYOTIA EXPANSION3
Ring Road - Mounib | 2 | 4 |  | 11371133.17 | 11371133.17 | 4521989.75 | 10132951.9 | 5610962.15 |  |  |  |  | 2021-01-31 | 2021-01-31 | 2021-02-08 | 60 | 2021-04-09 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib4 | RING ROAD MARYOTIA EXPANSION4
Ring Road - Mounib | 2 | 5 |  | 15036563.72 | 15036563.72 | 6026340.35 | 8684506.216 | 2658165.866 |  |  |  |  | 2021-02-28 | 2021-02-28 | 2021-03-17 | 60 | 2021-05-16 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib5 | RING ROAD MARYOTIA EXPANSION5
Ring Road - Mounib | 2 | 6 |  | 8863613 | 8863613 | 4751540.0144 | 7129991.824 | 2378451.8096 |  |  |  |  | 2021-03-31 | 2021-03-31 | 2021-04-15 | 60 | 2021-06-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib6 | RING ROAD MARYOTIA EXPANSION6
Ring Road - Mounib | 2 | 7 |  | 32591663.95 | 32591663.95 | 3640291.7356 | 4667862.096 | 1027570.3604 |  |  |  |  | 2021-04-30 | 2021-04-30 | 2021-05-15 | 60 | 2021-07-14 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib7 | RING ROAD MARYOTIA EXPANSION7
Ring Road - Mounib | 2 | 8 |  | 7329890.16 | 7329890.16 | 2701161.75 | 6443416.8 | 3742255.05 |  |  |  |  | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib8 | RING ROAD MARYOTIA EXPANSION8
Ring Road - Mounib | 2 | 9 | 4536613.5882 | 14419705.47 | 9883091.8818 | 3856121.55 | 7876622.257 | 4020500.707 |  |  |  | 3856121.55 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 |  | 98438363.943 | [6 empty] | 0 | 4536613.5882 | 98438363.943 | 3856121.55 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib9 | RING ROAD MARYOTIA EXPANSION9
Ring Road - Mounib | 2 | 10 | 18316815 | 20599647.58 | 2282832.58 | 10942755.35 | 13738602.73 | 2795847.38 |  |  |  | 12662306 | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 |  | 116755178.943 | [6 empty] | 0 | 18316815 | 116755178.943 | 12662306 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib10 | RING ROAD MARYOTIA EXPANSION10
Ring Road - Mounib | 2 | 11 | 30549611.057 | 29094868.16 | -1454742.897 | 3708396 | 3708396.57 | 0.57 |  |  |  | 19857247.187 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | 2021-09-07 | 147304790 | [6 empty] | 0 | 30549611.057 | 147304790 | 19857247.187 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib11 | RING ROAD MARYOTIA EXPANSION11
Ring Road - Mounib | 2 | 12 | 20117126 | 19159167.62 | -957958.38 | 14886673.24 | 18678770.82 | 3792097.58 |  |  |  | 14886673.24 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-10-16 | 167421916 | [6 empty] | 0 | 20117126 | 167421916 | 14886673.24 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib12 | RING ROAD MARYOTIA EXPANSION12
Ring Road - Mounib | 2 | 13 | 56505929 | 53815173.27 | -2690755.73 | 32998633.21 | 41457209.53 | 8458576.32 |  |  |  | 41814387.46 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 60 | 2022-01-07 | 2021-11-13 | 223927845 | [6 empty] | 0 | 56505929 | 223927845 | 41814387.46 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib13 | RING ROAD MARYOTIA EXPANSION13
Ring Road - Mounib | 2 | 14 | 46948185.4 | 44712557.52 | -2235627.88 | 14957307.9 | 14554103.9 | -403204 |  |  |  | 0 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 60 | 2022-02-07 | 2022-12-29 | 270876030.4 | [6 empty] | 0 | 46948185.4 | 270876030.4 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib14 | RING ROAD MARYOTIA EXPANSION14
Ring Road - Mounib | 2 | 15 | 30552404.425 | 29097528.02 | -1454876.405 | 10950094.1 | 11321780.291 | 371686.191 |  |  |  | 0 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-01-20 | 301428434.825 | [6 empty] | 0 | 30552404.425 | 301428434.825 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib15 | RING ROAD MARYOTIA EXPANSION15
Ring Road - Mounib | 2 | 16 | 161507041.625 | 40484939.8 | -121022101.825 | 131490711.85 | 40080090.4 | -91410621.45 |  |  |  | 0 | 2022-06-30 | 2022-07-10 | 2022-07-27 | 60 | 2022-09-25 | 2022-07-27 | 462935476.45 | [6 empty] | 0 | 161507041.625 | 462935476.45 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib16 | RING ROAD MARYOTIA EXPANSION16
Ring Road - Mounib | 2 | 17 | 6933306.55 | 48376193.13 | 41442886.58 | 1170803.2 | 46456883.7495 | 45286080.5495 |  |  |  | 5130646.847 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 60 | 2022-10-09 | 2022-08-10 | 469868783 | [6 empty] | 0 | 6933306.55 | 469868783 | 5130646.847 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib17 | RING ROAD MARYOTIA EXPANSION17
Ring Road - Mounib | 2 | 18 | 4715315.145 | 31753157.62 | 27037842.475 | 2897048.5 | 30929623.491 | 28032574.991 |  |  |  | 3489333.2073 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 | 2022-09-12 | 474584098.145 | [6 empty] | 0 | 4715315.145 | 474584098.145 | 3489333.2073 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib18 | RING ROAD MARYOTIA EXPANSION18
Ring Road - Mounib | 2 | 19 |  | 17982890.24 | 17982890.24 | 1351162.1 | 17532860.3445 | 16181698.2445 |  |  |  |  | 2022-09-30 | 2022-09-30 | 2022-10-17 | 60 | 2022-12-16 | [8 empty] | 0 | 0 | 0 | 0 | RING ROAD MARYOTIA EXPANSION |  |  |  | Ring Road - Mounib19 | RING ROAD MARYOTIA EXPANSION19
RO Apply -Mech- SSC | 1 | 1 | 2250265.4 | 0 | -2250265.4 | 1730229.07 | 0 | -1730229.07 |  |  |  | 1730229.07 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 2250265.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Apply -Mech- SSC1 | 01
RO Apply -Mech- SSC | 1 | 2 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Apply -Mech- SSC2 | 02
RO Apply -Mech- SSC | 1 | 4 | 4449602.38 | 0 | -4449602.38 | 0.001 | 0 | -0.001 |  |  |  | 1195633.38 | 2023-11-30 | 2023-11-12 | 2023-11-12 | 15 | 2023-11-27 | 2023-12-25 | 8242992.05 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Apply -Mech- SSC4 | 04
RO Eriction | 1 | 1 | 6000000 | 0 | -6000000 | 0 | 0 | 0 |  |  |  | 6660000 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 6000000 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Eriction1 | 01
RO Pump Room | 1 | 1 | 22392582.54 | 0 | -22392582.54 | 0 | 0 | 0 |  |  |  | 2216012.07 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 22392582.54 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump Room1 | 01
RO - Supply - Electric | 1 | 1 | 5322406.46 | 0 | -5322406.46 | 1e-05 | 0 | -1e-05 |  |  |  | 745136.9 | 2023-01-31 | 2023-01-16 | 2023-01-17 | 15 | 2023-02-01 | 2023-01-17 | 5322406.46 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO - Supply - Electric1 | 01
RO - Supply - Electric | 1 | 2 | 3040804.44 | 0 | -3040804.44 | 1e-05 | 0 | -1e-05 |  |  |  | 1847082.53 | 2023-02-28 | 2023-02-16 | 2023-03-08 | 15 | 2023-03-23 | 2023-03-15 | 8363210.9 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO - Supply - Electric2 | 02
RO - Supply - Electric | 1 | 3 | 11778923.84 | 0 | -11778923.84 | 2225665.9095 | 0 | -2225665.9095 |  |  |  | 1649065.6 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 15 | 2023-04-25 | 2023-04-10 | 20142134.74 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO - Supply - Electric3 | 03
RO Supply -Mech- SSC | 1 | 1 | 16503981 | 0 | -16503981 | 13698304.23 | 0 | -13698304.23 |  |  |  | 13698304.23 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-07 | 16503981 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC1 | 01
RO Supply -Mech- SSC | 1 | 2 | 1896616.8 | 0 | -1896616.8 | 1574191.94 | 0 | -1574191.94 |  |  |  | 1574191.94 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-14 | 18400597.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC2 | 02
RO Supply -Mech- SSC | 1 | 3 | 28179089.25 | 0 | -28179089.25 | 8116147.9035 | 0 | -8116147.9035 |  |  |  | 8116147.9 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 28179089.25 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC3 | 03
RO Supply -Mech- SSC | 1 | 4 | 7605000 | 0 | -7605000 | 6312150 | 0 | -6312150 |  |  |  | 6312150 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 15 | 2023-05-16 | 2023-05-08 | 35784089.25 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC4 | 04
RO Supply -Mech- SSC | 1 | 5 | 4510403.17 | 0 | -4510403.17 | 2149698.33 | 0 | -2149698.33 |  |  |  | 3743634.63 | 2023-07-31 | 2023-07-31 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-26 | 40294492.42 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC5 | 05
RO Supply -Mech- SSC | 1 | 8 | 14223589.16 | 0 | -14223589.16 | 0 | 0 | 0 |  |  |  | 1418035.09 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 15 | 2024-03-11 | 2024-02-27 | 54518081.58 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Supply -Mech- SSC8 | 08
RO 2 | 1 | 1 | 35549128.54 | 0 | -35549128.54 | 0 | 0 | 0 |  |  |  | 28083811.55 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 35549128.54 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO 21 | 01
RO 2 | 1 | 2 | 1807831.26 | 0 | -1807831.26 | 0 | 0 | 0 |  |  |  | 1880144.51 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 15 | 2024-05-16 | 2024-05-02 | 37356959.8 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO 22 | 02
RO 2 | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-01 | 15 | 2024-07-16 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO 23 | 03
RO Pump room - SSC - price diff. | 1 | 1 | 14675847.72 | 0 | -14675847.72 | 15849915.53 | 0 | -15849915.53 |  |  |  | 16583707.92 | 2023-02-28 | 2023-03-08 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-13 | 14675847.72 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.1 | 01
RO Pump room - SSC - price diff. | 1 | 2 | 1686530.02 | 0 | -1686530.02 | 918959 | 0 | -918959 |  |  |  | 1905778.92 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-15 | 16362377.74 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.2 | 02
RO Pump room - SSC - price diff. | 1 | 3 | 8704005.47 | 0 | -8704005.47 | 9400325.92 | 0 | -9400325.92 |  |  |  | 9835526.19 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 25066383.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.3 | 03
RO Pump room - SSC - price diff. | 1 | 4 | 6762600 | 0 | -6762600 | 7294244.17 | 0 | -7294244.17 |  |  |  | 7303608 | 2023-04-30 | 2023-05-01 | 2023-05-09 | 15 | 2023-05-24 | 2023-05-09 | 31828983.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO Pump room - SSC - price diff.4 | 04
RO.2 | 1 | 1 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 15 | 2023-07-15 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | RO.21 | 01
Rolling Mill #4-TRAESUEZ | 1 | 1 | 21476647.48 | 1143460 | -20333187.48 | 125716551.51 | 823066.73 | -124893484.78 |  |  |  | 17181317.99 | 2021-12-31 | 2022-01-10 | 2022-01-11 | 42 | 2022-02-22 | 2022-02-28 | 21476647.48 | [6 empty] | 0 | 21476647.48 | 21476647.48 | 17181317.99 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ1 | EGAT New Rolling Mill 41
Rolling Mill #4-TRAESUEZ | 1 | 2 | 13583921.53 | 0 | -13583921.53 | 12106800.04 | 0 | -12106800.04 |  |  |  | 11564103.96 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-22 | 35060569.01 | [6 empty] | 0 | 13583921.53 | 35060569.01 | 11564103.96 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ2 | EGAT New Rolling Mill 42
Rolling Mill #4-TRAESUEZ | 1 | 3 | 12117327 | 0 | -12117327 | 10231445.3 | 0 | -10231445.3 |  |  |  | 10352618.57 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-20 | 47177896.01 | [6 empty] | 0 | 12117327 | 47177896.01 | 10352618.57 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ3 | EGAT New Rolling Mill 43
Rolling Mill #4-TRAESUEZ | 1 | 4 | 8075015.79 | 0 | -8075015.79 | 6596541.38 | 0 | -6596541.38 |  |  |  | 6677291.55 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-17 | 55252911.8 | [6 empty] | 0 | 8075015.79 | 55252911.8 | 6677291.55 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ4 | EGAT New Rolling Mill 44
Rolling Mill #4-TRAESUEZ | 1 | 5 | 9905844.43 | 0 | -9905844.43 | 9293714.72 | 0 | -9293714.72 |  |  |  | 8140659.04 | 2022-05-31 | 2022-06-05 | 2022-06-07 | 42 | 2022-07-19 | 2022-07-06 | 65158756.23 | 7155944.45 | [5 empty] | 0 | 9905844.43 | 65158756.23 | 8140659.04 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ5 | EGAT New Rolling Mill 45
Rolling Mill #4-TRAESUEZ | 1 | 6 | 5743581.36 | 0 | -5743581.36 | 4622509.21 | 0 | -4622509.21 |  |  |  | 4679965.02 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-07 | 70902337.59 |  | 7496344.15 |  |  |  |  | 0 | 5743581.36 | 70902337.59 | 4679965.02 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ6 | EGAT New Rolling Mill 46
Rolling Mill #4-TRAESUEZ | 1 | 7 | 16796950.93 | 0 | -16796950.93 | 13289718.96 | 0 | -13289718.96 |  |  |  | 13457708.47 | 2022-07-31 | 2022-08-05 | 2022-08-06 | 42 | 2022-09-17 | 2022-08-24 | 87699288.52 |  | 7576935.06 |  |  |  |  | 0 | 16796950.93 | 87699288.52 | 13457708.47 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ7 | EGAT New Rolling Mill 47
Rolling Mill #4-TRAESUEZ | 1 | 8 | 18519200.97 | 0 | -18519200.97 | 16970562.32 | 0 | -16970562.32 |  |  |  | 14944026.92 | 2022-08-31 | 2022-09-10 | 2022-09-12 | 42 | 2022-10-24 | 2022-09-27 | 106218489.49 |  | 8091599.65 |  |  |  |  | 0 | 18519200.97 | 106218489.49 | 14944026.92 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ8 | EGAT New Rolling Mill 48
Rolling Mill #4-TRAESUEZ | 1 | 9 | 17686791.21 | 0 | -17686791.21 | 15728855.47 | 0 | -15728855.47 |  |  |  | 14162374.17 | 2022-09-30 | 2022-10-10 | 2022-10-12 | 42 | 2022-11-23 | 2022-11-07 | 123905280.7 |  | 8143364.44 |  |  |  |  | 0 | 17686791.21 | 123905280.7 | 14162374.17 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ9 | EGAT New Rolling Mill 49
Rolling Mill #4-TRAESUEZ | 1 | 10 | 15395023.2 | 0 | -15395023.2 | 10380808.5 | 0 | -10380808.5 |  |  |  | 12338644.38 | 2022-10-31 | 2022-11-07 | 2022-11-08 | 42 | 2022-12-20 | 2022-12-14 | 139300303.9 |  | 8233867.7 |  |  |  |  | 0 | 15395023.2 | 139300303.9 | 12338644.38 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ10 | EGAT New Rolling Mill 410
Rolling Mill #4-TRAESUEZ | 1 | 11 | 16145745 | 0 | -16145745 | 9072857.69 | 0 | -9072857.69 |  |  |  | 13316234.88 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2023-01-17 | 155446048.9 |  | 9832423.2 |  |  |  |  | 0 | 16145745 | 155446048.9 | 13316234.88 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ11 | EGAT New Rolling Mill 411
Rolling Mill #4-TRAESUEZ | 1 | 12 | 16694409.39 | 0 | -16694409.39 | 13213191.25 | 0 | -13213191.25 |  |  |  | 13380155.34 | 2022-12-31 | 2023-01-15 | 2023-01-18 | 42 | 2023-03-01 | 2023-02-07 | 172140458.29 |  | 9930934.56 |  |  |  |  | 0 | 16694409.39 | 172140458.29 | 13380155.34 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ12 | EGAT New Rolling Mill 412
Rolling Mill #4-TRAESUEZ | 1 | 13 | 14485776.58 | 0 | -14485776.58 | 1e-05 | 0 | -1e-05 |  |  |  | 11700102.46 | 2023-01-31 | 2023-02-15 | 2023-02-16 | 42 | 2023-03-30 | 2023-03-08 | 186626234.87 |  | 10376859 |  |  |  |  | 0 | 14485776.58 | 186626234.87 | 11700102.46 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ13 | EGAT New Rolling Mill 413
Rolling Mill #4-TRAESUEZ | 1 | 14 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-02-28 | 2023-03-10 | 2023-03-20 | 42 | 2023-05-01 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ14 | EGAT New Rolling Mill 414
Rolling Mill #4-TRAESUEZ | 1 | 15 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ15 | EGAT New Rolling Mill 415
Rolling Mill #4-TRAESUEZ | 1 | 16 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ16 | EGAT New Rolling Mill 416
Rolling Mill #4-TRAESUEZ | 1 | 17 | 619836241 | 0 | -619836241 | 0 | 0 | 0 |  |  |  | 385850750.2 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 619836241 | [6 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ17 | EGAT New Rolling Mill 417
Rolling Mill #4-TRAESUEZ | 1 | 18 | 16836028.82 | 0 | -16836028.82 | 0 | 0 | 0 |  |  |  | 17509470.02 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 636672269.82 |  | 105081618.32 |  |  |  |  | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ18 | EGAT New Rolling Mill 418
Rolling Mill #4-TRAESUEZ | 1 | 19 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [8 empty] | 0 | 0 | 0 | 0 | EGAT New Rolling Mill 4 |  |  |  | Rolling Mill #4-TRAESUEZ19 | EGAT New Rolling Mill 419
Royal City | 1 | 2 | 8875548.87 | 1714285.71 | -7161263.16 | 4892835.45 | 4006344.6355 | -886490.8145 |  |  |  | 5235331.6 | 2017-09-30 | 2017-09-30 | 2017-10-01 | 34 | 2017-11-04 | 2017-10-11 | 8875548.87 | 3953206.73 | [5 empty] | 34013.75 | 5127541.59 | 9046023.16 | 5203476.09 | Royal City |  |  |  | Royal City2 | Royal City2
Royal City | 1 | 3 | 8111601.4206 | 2055285.71 | -6056315.7106 | 7926742.1 | 2422662.0255 | -5504080.0745 |  |  |  | 7926742.1 | 2017-10-31 | 2017-10-31 | 2017-11-04 | 34 | 2017-12-08 | 2017-11-14 | 16987150.2906 | 5848040.712 | [5 empty] | 103062.25 | 8536189.79 | 17411738.66 | 8396278.07 | Royal City |  |  |  | Royal City3 | Royal City3
Royal City | 1 | 4 | 10259671.7094 | 4548914.9 | -5710756.8094 | 10437271.65 | 4400341.915 | -6036929.735 |  |  |  | 10437271.65 | 2017-11-30 | 2017-12-03 | 2017-12-03 | 34 | 2018-01-06 | 2017-12-24 | 27246822 | 8775298.38 | [5 empty] | 103062.25 | 0 | 0 | 0 | Royal City |  |  |  | Royal City4 | Royal City4
Royal City | 1 | 5 | 11565536.4187 | 0 | -11565536.4187 | 5169557.65 | 0 | -5169557.65 |  |  |  | 6381832.9445 | 2017-12-31 | 2017-12-30 | 2018-01-03 | 34 | 2018-02-06 | 2018-01-22 | 38812358.4187 | 5702856.6 | [5 empty] | 166539 | 11565536.4187 | 38812358.4187 | 6381832.9445 | Royal City |  |  |  | Royal City5 | Royal City5
Royal City | 1 | 6 | 15834199.4413 | 29417027.49 | 13582828.0487 | 12495801.4 | 21736703.6495 | 9240902.2495 |  |  |  | 12495801.39 | 2018-03-31 | 2018-03-31 | 2018-02-20 | 34 | 2018-03-26 | 2018-05-21 | 54646557.86 | 3811475.98 | [5 empty] | 348145 | 17361811.89 | 54716858.14 | 11493260.03 | Royal City |  |  |  | Royal City6 | Royal City6
Royal City | 1 | 7 | 11881365.61 | 17794057.54 | 5912691.93 | 8703262.4 | 15145986.237 | 6442723.837 |  |  |  | 8703262.41 | 2018-04-30 | 2018-04-30 | 2018-05-07 | 34 | 2018-06-10 | 2018-06-11 | 66527923.47 | 3172251.35 | [5 empty] | 582017.44 | 11988097.7 | 66634655.56 | 8439569.37 | Royal City |  |  |  | Royal City7 | Royal City7
Royal City | 1 | 8 | 7845708.0075 | 24651268.82 | 16805560.8125 | 6085844.5 | 18753229.9225 | 12667385.4225 |  |  |  | 7600061.0338 | 2018-05-31 | 2018-05-31 | 2018-06-05 | 34 | 2018-07-09 | 2018-06-24 | 74373631.4775 | 5502031.137 | [5 empty] | 2646288.4432 | 7845708.0075 | 74373631.4775 | 7600061.0338 | Royal City |  |  |  | Royal City8 | Royal City8
Royal City | 1 | 9 | 7890492.132 | 13776239.27 | 5885747.138 | 6397146.2 | 13382223.5235 | 6985077.3235 |  |  |  | 6018082.2865 | 2018-06-30 | 2018-06-30 | 2018-07-10 | 34 | 2018-08-13 | 2018-07-26 | 82264123.6095 | 5685747.237 | [5 empty] | 3049998.998 | 7890492.132 | 82264123.6095 | 6018082.2865 | Royal City |  |  |  | Royal City9 | Royal City9
Royal City | 1 | 10 | 8199169.349 | 11745905.81 | 3546736.461 | 5786688.5 | 8903897.6715 | 3117209.1715 |  |  |  | 5554331.9836 | 2018-07-31 | 2018-07-31 | 2018-08-08 | 34 | 2018-09-11 | 2018-08-27 | 90463292.9586 | 4944412.0842 | [5 empty] | 3422890.7078 | 8199169.349 | 90463292.9586 | 5554331.9836 | Royal City |  |  |  | Royal City10 | Royal City10
Royal City | 1 | 11 | 2707034.9014 | 7770604.14 | 5063569.2386 | 61982306.95 | 8393935.087 | -53588371.863 |  |  |  | 3237608.64 | 2018-08-31 | 2018-08-31 | 2018-09-12 | 34 | 2018-10-16 | 2018-09-24 | 93170327.86 | 6546266.4 | [5 empty] | 3614328.412 | 2707034.9014 | 93170327.86 | 3237608.64 | Royal City |  |  |  | Royal City11 | Royal City11
Royal City | 1 | 12 | 12651464.27 | 21173807.09 | 8522342.82 | 9822648.05 | 16099158.9745 | 6276510.9245 |  |  |  | 8503935.74 | 2018-09-30 | 2018-09-30 | 2018-10-09 | 34 | 2018-11-12 | 2018-11-07 | 105821792.13 | 8045747.81 | [5 empty] | 669617.5401 | 9032801.23 | 102203129.09 | 7860724.87 | Royal City |  |  |  | Royal City12 | Royal City12
Royal City | 1 | 13 | 11315357.62 | 14375270.26 | 3059912.64 | 6339338.45 | 8476906.9292 | 2137568.4792 |  |  |  | 6339338.47 | 2018-10-31 | 2018-10-31 | 2018-11-07 | 34 | 2018-12-11 | 2018-12-04 | 117137149.75 | 6383924.621 | [5 empty] | 0 | 7318551.3313 | 113140343.4613 | 5548576.504 | Royal City |  |  |  | Royal City13 | Royal City13
Royal City | 1 | 14 | 3293171.7405 | 9094787.68 | 5801615.9395 | 5980045.3 | 7268872.3764 | 1288827.0764 |  |  |  | 13062023.4527 | 2018-11-30 | 2018-11-30 | 2018-12-06 | 34 | 2019-01-09 | 2018-12-29 | 120430321.4905 | 8435330.6159 | [5 empty] | 558453.95 | 3293171.7405 | 120430321.4905 | 13062023.4527 | Royal City |  |  |  | Royal City14 | Royal City14
Royal City | 1 | 15 | 16384822.4548 | 11859360.39 | -4525462.0648 | 6570751.8 | 8843457.1828 | 2272705.3828 |  |  |  | 9343372.736 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 34 | 2019-02-09 | 2019-01-20 | 136815143.9453 | 9384080.2453 | [5 empty] | 653055.6603 | 16384822.4548 | 136815143.9453 | 9343372.736 | Royal City |  |  |  | Royal City15 | Royal City15
Royal City | 1 | 16 | 11488490.3339 | 10225071.97 | -1263418.3639 | 7847127.4 | 8700605.8785 | 853478.4785 |  |  |  | 10141562.9942 | 2019-01-31 | 2019-01-31 | 2019-02-07 | 34 | 2019-03-13 | 2019-02-25 | 148303634.2792 | 12235459.3471 | [5 empty] | 320713.8483 | 11488490.3339 | 148303634.2792 | 10141562.9942 | Royal City |  |  |  | Royal City16 | Royal City16
Royal City | 1 | 17 | 9063503.9339 | 9888548.33 | 825044.3961 | 5868379.55 | 7926704.1265 | 2058324.5765 |  |  |  | 6226878.8549 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 34 | 2019-04-09 | 2019-04-01 | 157367138.2131 | 15116649.6688 | [5 empty] | 370976.9746 | 9063503.9339 | 157367138.2131 | 6226878.8549 | Royal City |  |  |  | Royal City17 | Royal City17
Royal City | 1 | 18 | 8621924.8043 | 11007990.23 | 2386065.4257 | 4501953.5 | 5608968.3915 | 1107014.8915 |  |  |  | 6196039.396 | 2019-03-31 | 2019-03-31 | 2019-04-09 | 34 | 2019-05-13 | 2019-04-18 | 165989063.0174 | 14343940.1395 | [5 empty] | 296046.8071 | 8621924.8043 | 165989063.0174 | 6196039.396 | Royal City |  |  |  | Royal City18 | Royal City18
Royal City | 1 | 19 | 15549148.0486 | 15449696.42 | -99451.6286 | 9999974.75 | 11100376.271 | 1100401.521 |  |  |  | 10933183.0202 | 2019-04-30 | 2019-04-30 | 2019-05-08 | 34 | 2019-06-11 | 2019-05-23 | 181538211.066 | 16047073.0222 | [5 empty] | 222365.6932 | 15549148.0486 | 181538211.066 | 10933183.0202 | Royal City |  |  |  | Royal City19 | Royal City19
Royal City | 1 | 20 | 7876990.4815 | 9923971.4 | 2046980.9185 | 5072118 | 6164410 | 1092292 |  |  |  | 5643448.8191 | 2019-05-31 | 2019-05-31 | 2019-06-01 | 34 | 2019-07-05 | 2019-06-26 | 189415201.5475 | 15380569.1286 | [5 empty] | 176894.1812 | 7876990.4815 | 189415201.5475 | 5643448.8191 | Royal City |  |  |  | Royal City20 | Royal City20
Royal City | 1 | 21 | 7532294.3265 | 9561619.77 | 2029325.4435 | 5000000 | 7420122.4285 | 2420122.4285 |  |  |  | 5151160.3487 | 2019-06-30 | 2019-06-30 | 2019-07-08 | 34 | 2019-08-11 | 2019-07-18 | 196947495.8739 | 17429947.3127 | [5 empty] | 252279.4582 | 7532294.3265 | 196947495.8739 | 5151160.3487 | Royal City |  |  |  | Royal City21 | Royal City21
Royal City | 1 | 22 | 24265130.1959 | 21793392.51 | -2471737.6859 | 36824453.7 | 20152080.9255 | -16672372.7745 |  |  |  | 17540056.799 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 34 | 2019-09-08 | 2019-09-02 | 221212626.0698 | 24953179.7402 | [5 empty] | 327502.3224 | 24265130.1959 | 221212626.0698 | 17540056.799 | Royal City |  |  |  | Royal City22 | Royal City22
Royal City | 1 | 23 | 6268692.5562 | 8598719.65 | 2330027.0938 | 6453450.6 | 6578450.5925 | 124999.9925 |  |  |  | 4319851.8787 | 2019-08-31 | 2019-08-31 | 2019-09-11 |  | 2019-10-18 | 2019-09-28 | 227481318.626 | 25361645.3681 | [5 empty] | 418117.1746 | 6268692.5562 | 227481318.626 | 4319851.8787 | Royal City |  |  |  | Royal City23 | Royal City23
Royal City | 1 | 24 | 17799666.736 | 18486909.34 | 687242.604 | 9088642.9 | 9213642.983 | 125000.083 |  |  |  | 10214838.0645 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-24 | 245280985.3621 | 23478699.1038 | [5 empty] | 383536.5601 | 17799666.736 | 245280985.3621 | 10214838.0645 | Royal City |  |  |  | Royal City24 | Royal City24
Royal City | 1 | 25 | 17503083.0268 | 17584623.17 | 81540.1432 | 9972683.95 | 9972683.9685 | 0.0185 |  |  |  | 12249365.624 | 2019-10-31 | 2019-10-31 | 2019-11-07 | 34 | 2019-12-11 | 2019-11-27 | 262784068.3888 | 23043660.2023 | [5 empty] | 462163.6487 | 17503083.0268 | 262784068.3888 | 12249365.624 | Royal City |  |  |  | Royal City25 | Royal City25
Royal City | 1 | 26 | 10595979.9301 | 0 | -10595979.9301 | 8025338.3 | 0 | -8025338.3 |  |  |  | 7456675.6367 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 273380048.3189 | 22399832.276 | [5 empty] | 481328.1283 | 10595979.9301 | 273380048.3189 | 7456675.6367 | Royal City |  |  |  | Royal City26 | Royal City26
Royal City | 1 | 27 | 20586377.6301 | 23615681.47 | 3029303.8399 | 11895943.7 | 11636419.9 | -259523.8 |  |  |  | 14587648.3106 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 293966425.9491 | 19245051.8837 | [5 empty] | 481881.6236 | 20586377.6301 | 293966425.9491 | 14587648.3106 | Royal City |  |  |  | Royal City27 | Royal City27
Royal City | 1 | 28 | 15640549.4851 | 18900076.14 | 3259526.6549 | 10500306.77 | 10500306.76 | -0.01 |  |  |  | 10986396.5553 | 2020-01-31 | 2020-01-31 | 2020-02-17 | 34 | 2020-03-22 | 2020-03-16 | 309606975.4342 | 16026544.9251 | [5 empty] | 606431.6143 | 15640549.4851 | 309606975.4342 | 10986396.5553 | Royal City |  |  |  | Royal City28 | Royal City28
Royal City | 1 | 29 | 18804604.7977 | 17649893.88 | -1154710.9177 | 12838209.35 | 12838209.344 | -0.006 |  |  |  | 13166441.5288 | 2020-02-29 | 2020-02-29 | 2020-03-18 | 34 | 2020-04-21 | 2020-04-05 | 328411580.2319 | 16972896.7219 | [5 empty] | 637326.7814 | 18804604.7977 | 328411580.2319 | 13166441.5288 | Royal City |  |  |  | Royal City29 | Royal City29
Royal City | 1 | 30 | 13862319.0142 | 16056421.67 | 2194102.6558 | 9831952.135 | 9421690.2835 | -410261.8515 |  |  |  | 9831952.135 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 342273899.2462 | 14581690.3962 | [5 empty] | 637621.4818 | 13862319.0142 | 342273899.2462 | 9831952.135 | Royal City |  |  |  | Royal City30 | Royal City30
Royal City | 1 | 31 | 10234077.8776 | 12028045.18 | 1793967.3024 | 6475508.58 | 6475509.799 | 1.219 |  |  |  | 7550426.1692 | 2020-04-30 | 2020-04-30 | 2020-05-14 | 34 | 2020-06-17 | 2020-07-02 | 352507977.1238 | 12931292.2437 | [5 empty] | 0 | 10234077.8776 | 352507977.1238 | 7550426.1692 | Royal City |  |  |  | Royal City31 | Royal City31
Royal City | 1 | 32 | 3761397.6023 | 4150837.54 | 389439.9377 | 2151533.38 | 2151533.367 | -0.013 |  |  |  | 2648440.2256 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 356269374.7261 | 12829313.7893 | [5 empty] | 0 | 3761397.6023 | 356269374.7261 | 2648440.2256 | Royal City |  |  |  | Royal City32 | Royal City32
Royal City | 1 | 33 | 13830917.4352 | 11787102.13 | -2043815.3052 | 9101413.8171 | 8559155.6765 | -542258.1406 |  |  |  | 9101413.8171 | 2020-06-30 | 2020-06-30 | 2020-07-20 | 34 | 2020-08-23 | 2020-08-12 | 370100292.1612 | 14873462.0847 | [5 empty] | 1198898.3783 | 13830917.4352 | 370100292.1612 | 9101413.8171 | Royal City |  |  |  | Royal City33 | Royal City33
Royal City | 1 | 34 | 7811639.6921 | 0 | -7811639.6921 | 5373442.9261 | 0 | -5373442.9261 |  |  |  | 5373442.9261 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-14 | 377911931.8534 | 13214988.4567 | [5 empty] | 1376502.8422 | 7811639.6921 | 377911931.8534 | 5373442.9261 | Royal City |  |  |  | Royal City34 | Royal City34
Royal City | 1 | 35 | 3980750.5222 | 6572349.74 | 2591599.2178 | 3237336.5863 | 2752213.4436 | -485123.1427 |  |  |  | 3237336.5863 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 381892682.3756 | 10629015.9927 | [5 empty] | 1052872.9373 | 3980750.5222 | 381892682.3756 | 3237336.5863 | Royal City |  |  |  | Royal City35 | Royal City35
Royal City | 1 | 36 | 8343396.9284 | 8120768.31 | -222628.6184 | 5231425.19 | 5231425.2055 | 0.0155 |  |  |  | 5231425.19 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 390236079.304 | 10856647.4404 | [5 empty] | 1034872.9373 | 8343396.9284 | 390236079.304 | 4982664.9588 | Royal City |  |  |  | Royal City36 | Royal City36
Royal City | 1 | 37 | 5412454.8663 | 8335559.1 | 2923104.2337 | 3663343.67 | 3663301.675 | -41.995 |  |  |  | 5574033.5344 | 2020-10-31 | 2020-10-31 | 2020-11-07 | 34 | 2020-12-11 | 2020-11-26 | 395648534.1703 | 7933674.7404 | [5 empty] | 998604.3353 | 5412454.8663 | 395648534.1703 | 5574033.5344 | Royal City |  |  |  | Royal City37 | Royal City37
Royal City | 1 | 38 | 3712322.3219 | 4991557.65 | 1279235.3281 | 2267127.88 | 3951088.5025 | 1683960.6225 |  |  |  | 3838809.8865 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 399360856.4923 | 6223962.4617 | [5 empty] | 944047.2982 | 3712322.3219 | 399360856.4923 | 3838809.8865 | Royal City |  |  |  | Royal City38 | Royal City38
Royal City | 1 | 39 | 1174176.5076 | 1409870.69 | 235694.1824 | 1002773.1926 | 872368.1645 | -130405.0281 |  |  |  | 1002773.1926 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 400535032.9999 | 6288699.0447 | [5 empty] | 899047.2982 | 1174176.5076 | 400535032.9999 | 1002773.1926 | Royal City |  |  |  | Royal City39 | Royal City39
Royal City | 1 | 40 | 5847326.4556 | 7356711.98 | 1509385.5244 | 5979686.67 | 5481051.519 | -498635.151 |  |  |  | 5979686.6716 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 406382359.4555 | 4784431.8697 | [5 empty] | 823521.4569 | 5847326.4556 | 406382359.4555 | 5979686.6716 | Royal City |  |  |  | Royal City40 | Royal City40
Royal City | 1 | 41 | 5256684.0377 | 6547385.9 | 1290701.8623 | 5714023.3138 | 5167630.645 | -546392.6688 |  |  |  | 5714023.3138 | 2021-08-31 | 2021-09-01 | 2021-09-19 | 34 | 2021-10-23 | 2021-11-01 | 411639043.4932 | 3493730 | [5 empty] | 414348.8107 | 5256684.0377 | 411639043.4932 | 5714023.3138 | Royal City |  |  |  | Royal City41 | Royal City41
Royal City | 1 | 42 | 7571387.8468 | 10349949.34 | 2778561.4932 | 35161782.8 | 20407465.3582 | -14754317.4418 |  |  |  | 29397549.59 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 419210431.34 | 715168.5 | 18621503.12 |  | 45928934.7 |  |  | 225000 | 7571387.8468 | 419210431.34 | 29397549.59 | Royal City |  |  |  | Royal City42 | Royal City42
Royal City | 1 | 43 | 13484961.26 | 14387671.43 | 902710.17 | 0 | 0 | 0 |  |  |  | 13488633.46 | 2023-07-31 | 2023-08-08 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 432695392.6 |  | 18307280.08 |  | 46946119.05 |  |  | 225000 | 13484961.26 | 432695392.6 | 13488633.46 | Royal City |  |  |  | Royal City43 | Royal City43
Royal City - Landscape | 1 | 1 |  | 1714285.71 | 1714285.71 | 1782000 | 1782857.1355 | 857.1355 |  |  |  | 1800000 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 34 | 2019-09-09 | [8 empty] | 0 | 0 | 0 | 1800000 | Royal City |  |  |  | Royal City - Landscape1 | Royal City1
Royal City - Landscape | 1 | 2 |  | 1714285.71 | 1714285.71 | 4014037.5 | 4006344.6355 | -7692.8645 |  |  |  | 4032037.5 | 2019-08-31 | 2019-08-31 | 2019-09-11 | 34 | 2019-10-15 | 2019-09-25 |  | 2976050 | [5 empty] | 0 | 0 | 0 | 4032037.5 | Royal City |  |  |  | Royal City - Landscape2 | Royal City2
Royal City - Landscape | 1 | 3 | 341000 | 2055285.71 | 1714285.71 | 2421804.9 | 2422662.0255 | 857.1255 |  |  |  | 2443214.8875 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-23 | 341000 | 3475619.85 | [5 empty] | 0 | 341000 | 341000 | 2443214.8875 | Royal City |  |  |  | Royal City - Landscape3 | Royal City3
Royal City - Landscape | 1 | 4 | 2839877.7881 | 4548914.9 | 1709037.1119 | 4390934.75 | 4400341.915 | 9407.165 |  |  |  | 4441415.442 | 2019-10-31 | 2019-10-30 | 2019-11-07 | 34 | 2019-12-11 | 2019-12-25 | 3180877.7881 | 4015635.4285 | [5 empty] | 0 | 2839877.7881 | 3180877.7881 | 4441415.442 | Royal City |  |  |  | Royal City - Landscape4 | Royal City4
Royal City - Landscape | 1 | 5 | 5896802.2265 | 0 | -5896802.2265 | 7060326.8 | 0 | -7060326.8 |  |  |  | 7147476.0332 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 9077680.0146 | 4953961.135 | [5 empty] | 0 | 5896802.2265 | 9077680.0146 | 7147476.0332 | Royal City |  |  |  | Royal City - Landscape5 | Royal City5
Royal City - Landscape | 1 | 6 | 12932194.6154 | 29417027.49 | 16484832.8746 | 9240902.25 | 21736703.6495 | 12495801.3995 |  |  |  | 9619287.67 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 22009874.63 | 4200873.67 | [5 empty] | 0 | 12932194.6154 | 22009874.63 | 9619287.67 | Royal City |  |  |  | Royal City - Landscape6 | Royal City6
Royal City - Landscape | 1 | 7 | 6479189.8549 | 17794057.54 | 11314867.6851 | 6442723.35 | 15145986.237 | 8703262.887 |  |  |  | 6246175.7955 | 2020-01-31 | 2020-01-31 | 2020-02-11 | 34 | 2020-03-16 | 2020-03-16 | 28489064.4849 | 5725958.7255 | [5 empty] | 0 | 6479189.8549 | 28489064.4849 | 6246175.7955 | Royal City |  |  |  | Royal City - Landscape7 | Royal City7
Royal City - Landscape | 1 | 8 | 17137734.2822 | 24651268.82 | 7513534.5378 | 12356243.75 | 18753229.9225 | 6396986.1725 |  |  |  | 12899186.0747 | 2020-02-29 | 2020-02-29 | 2020-03-17 | 34 | 2020-04-20 | 2020-04-05 | 45626798.7671 | 4930252.4954 | [5 empty] | 0 | 17137734.2822 | 45626798.7671 | 12899186.0747 | Royal City |  |  |  | Royal City - Landscape8 | Royal City8
Royal City - Landscape | 1 | 9 | 6296234.5253 | 13776239.27 | 7480004.7447 | 4886117.91 | 13382223.5235 | 8496105.6135 |  |  |  | 4988413.7416 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 51923033.2924 | 4970424.566 | [5 empty] | 0 | 6296234.5253 | 51923033.2924 | 4988413.7416 | Royal City |  |  |  | Royal City - Landscape9 | Royal City9
Royal City - Landscape | 1 | 10 | 3937848.897 | 11745905.81 | 7808056.913 | 3061010.97 | 8903897.6715 | 5842886.7015 |  |  |  | 3101056.0064 | 2020-04-30 | 2020-04-30 | 2020-05-18 | 34 | 2020-06-21 | 2020-07-02 | 55860882.1894 | 4970424.566 | [5 empty] | 0 | 3937848.897 | 55860882.1894 | 3101056.0064 | Royal City |  |  |  | Royal City - Landscape10 | Royal City10
Royal City - Landscape | 1 | 11 | 5192701.4937 | 7770604.14 | 2577902.6463 | 4947910.42 | 8393935.087 | 3446024.667 |  |  |  | 3973857.736 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 61053583.6831 | 4816564.979 | [5 empty] | 0 | 5192701.4937 | 61053583.6831 | 3973857.736 | Royal City |  |  |  | Royal City - Landscape11 | Royal City11
Royal City - Landscape | 1 | 12 | 8940402.3014 | 21173807.09 | 12233404.7886 | 7029456.4155 | 16099158.9745 | 9069702.559 |  |  |  | 7029456.4155 | 2020-06-30 | 2020-06-30 | 2020-07-19 | 34 | 2020-08-22 | 2020-08-12 | 69993985.9845 | 6160052.1105 | [5 empty] | 0 | 8940402.3014 | 69993985.9845 | 7029456.4155 | Royal City |  |  |  | Royal City - Landscape12 | Royal City12
Royal City - Landscape | 1 | 13 | 3598777.1179 | 14375270.26 | 10776493.1421 | 2173267.6157 | 8476906.9292 | 6303639.3135 |  |  |  | 2173267.6157 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-07 | 73592763.1024 | 4428817.741 | [5 empty] | 0 | 3598777.1179 | 73592763.1024 | 2173267.6157 | Royal City |  |  |  | Royal City - Landscape13 | Royal City13
Royal City - Landscape | 1 | 14 | 2137131.084 | 9094787.68 | 6957656.596 | 1308214.7555 | 7268872.3764 | 5960657.6209 |  |  |  | 1308214.7555 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 75729894.1864 | 3929116.4435 | [5 empty] | 0 | 2137131.084 | 75729894.1864 | 1308214.7555 | Royal City |  |  |  | Royal City - Landscape14 | Royal City14
Royal City - Landscape | 1 | 15 | 3135305.5981 | 11859360.39 | 8724054.7919 | 2272705.37 | 8843457.1828 | 6570751.8128 |  |  |  | 2272705.37 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 78865199.7846 | 3708912.5587 | [5 empty] | 0 | 3135305.5981 | 78865199.7846 | 2303900.245 | Royal City |  |  |  | Royal City - Landscape15 | Royal City15
Royal City - Landscape | 1 | 16 | 1582061.2622 | 10225071.97 | 8643010.7078 | 650222.9433 | 8700605.8785 | 8050382.9352 |  |  |  | 853478.48 | 2020-10-31 | 2020-10-31 | 2020-11-09 | 34 | 2020-12-13 | 2020-11-26 | 80447261.0467 | 3206907.765 | [5 empty] | 0 | 1582061.2622 | 80447261.0467 | 869369.6486 | Royal City |  |  |  | Royal City - Landscape16 | Royal City16
Royal City - Landscape | 1 | 17 | 3716309.8261 | 9888548.33 | 6172238.5039 | 2820044.2305 | 7926704.1265 | 5106659.896 |  |  |  | 2058324.55 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 84163570.8728 | 1876563.015 | [5 empty] | 45000 | 3716309.8261 | 84163570.8728 | 1883835.4255 | Royal City |  |  |  | Royal City - Landscape17 | Royal City17
Royal City - Landscape | 1 | 18 | 1163660.8736 | 11007990.23 | 9844329.3564 | 819297.0816 | 5608968.3915 | 4789671.3099 |  |  |  | 819297.0816 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 85327231.7464 | 1969454.449 | [5 empty] | 0 | 1163660.8736 | 85327231.7464 | 819297.0816 | Royal City |  |  |  | Royal City - Landscape18 | Royal City18
Royal City - Landscape | 1 | 19 | 2029657.8338 | 15449696.42 | 13420038.5862 | 1116339.8935 | 11100376.271 | 9984036.3775 |  |  |  | 1116339.8935 | 2021-01-31 | 2021-01-31 | 2021-02-09 | 34 | 2021-03-15 | 2021-03-02 | 87356889.5802 | 1814848.008 | [5 empty] | 60000 | 2029657.8338 | 87356889.5802 | 1116339.8935 | Royal City |  |  |  | Royal City - Landscape19 | Royal City19
Royal City - Landscape | 1 | 20 | 1366613.9629 | 9923971.4 | 8557357.4371 | 1105876.6944 | 6164410 | 5058533.3056 |  |  |  | 1105876.6944 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 88723503.543 | 1854405.6062 | [5 empty] | 60000 | 1366613.9629 | 88723503.543 | 1105876.6944 | Royal City |  |  |  | Royal City - Landscape20 | Royal City20
Royal City - Landscape | 1 | 21 | 4112536.457 | 9561619.77 | 5449083.313 | 2806313.404 | 7420122.4285 | 4613809.0245 |  |  |  | 3011690.98 | 2021-05-31 | 2021-05-31 | 2021-06-13 | 34 | 2021-07-17 | 2021-07-13 | 92836040 | 1631829.995 | [5 empty] | 120000 | 4112536.457 | 92836040 | 3011690.98 | Royal City |  |  |  | Royal City - Landscape21 | Royal City21
Royal City - Landscape | 1 | 22 | 3299640.8 | 21793392.51 | 18493751.71 | 1838217.2 | 20152080.9255 | 18313863.7255 |  |  |  | 2526109.9 | 2021-08-31 | 2021-09-01 | 2021-09-14 | 34 | 2021-10-18 | 2021-11-01 | 96135680.8 | 1159231.18 | [5 empty] | 165000 | 3299640.8 | 96135680.8 | 2526109.9 | Royal City |  |  |  | Royal City - Landscape22 | Royal City22
Royal City - Landscape | 1 | 23 | 10826725.43 | 8598719.65 | -2228005.78 | 13000000 | 6578450.5925 | -6421549.4075 |  |  |  | 15313915.32 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 106962406.23 | [6 empty] | 165000 | 10826725.43 | 106962406.23 | 15313915.32 | Royal City |  |  |  | Royal City - Landscape23 | Royal City23
Royal City - Landscape | 1 | 24 | 3256136.08 | 18486909.34 | 15230773.26 | 0 | 9213642.983 | 9213642.983 |  |  |  | 3247942.88 | 2023-06-30 | 2023-07-11 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 110218542.31 | [6 empty] | 0 | 3256136.08 | 110218542.31 | 3247942.88 | Royal City |  |  |  | Royal City - Landscape24 | Royal City24
Saint Gobain Factory - DP | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-09-30 | 2024-09-25 | 2024-09-25 | 28 | 2024-10-23 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Saint Gobain Factory - DP1 | 01
SIEMENS - Sokhna | 1 | 1 |  | 0 | 0 | 93300000 | 0 | -93300000 |  |  |  | 93300000 | 2017-11-30 | 2017-11-30 | 2017-11-29 | 45 | 2018-01-13 | 2017-12-06 | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna1 | 01
SIEMENS - Sokhna | 1 | 2 | 4401847.1 | 0 | -4401847.1 | 3059283.73 | 0 | -3059283.73 |  |  |  | 3059283.73 | 2017-12-31 | 2017-12-25 | 2018-01-16 | 45 | 2018-03-02 | 2018-01-16 | 4401847.1 | 0 | [5 empty] | 0 | 4401847.1 | 4401847.1 | 3059283.73 | 0 |  |  |  | SIEMENS - Sokhna2 | 02
SIEMENS - Sokhna | 1 | 3 | 10401972.73 | 0 | -10401972.73 | 7201577.05 | 0 | -7201577.05 |  |  |  | 7201577.05 | 2018-01-31 | 2018-02-03 | 2018-02-05 | 45 | 2018-03-22 | 2018-02-05 | 14803819.83 | 0 | [5 empty] | 27794 | 10401972.73 | 14803819.83 | 7201577.05 | 0 |  |  |  | SIEMENS - Sokhna3 | 03
SIEMENS - Sokhna | 1 | 4 | 15960664.31 | 0 | -15960664.31 | 11065687.7 | 0 | -11065687.7 |  |  |  | 11065687.7 | 2018-02-28 | 2018-03-04 | 2018-03-05 | 45 | 2018-04-19 | 2018-03-14 | 30764484.14 | 0 | [5 empty] | 54768 | 15960664.31 | 30764484.14 | 11065687.7 | 0 |  |  |  | SIEMENS - Sokhna4 | 04
SIEMENS - Sokhna | 1 | 5 | 19051976.33 | 0 | -19051976.33 | 13218163.56 | 0 | -13218163.56 |  |  |  | 13218163.55 | 2018-03-31 | 2018-04-08 | 2018-04-10 | 45 | 2018-05-25 | 2018-04-15 | 49816460.47 | 0 | [5 empty] | 77728 | 19051976.33 | 49816460.47 | 13218163.55 | 0 |  |  |  | SIEMENS - Sokhna5 | 05
SIEMENS - Sokhna | 1 | 6 | 10481549.5128 | 0 | -10481549.5128 | 7060448.908 | 0 | -7060448.908 |  |  |  | 7060448.908 | 2018-04-30 | 2018-05-03 | 2018-05-07 | 45 | 2018-06-21 | 2018-05-20 | 60298009.9828 | 0 | [5 empty] | 301956 | 10481549.5128 | 60298009.9828 | 7060448.908 | 0 |  |  |  | SIEMENS - Sokhna6 | 06
SIEMENS - Sokhna | 1 | 7 | 12587450.0972 | 0 | -12587450.0972 | 8833159.82 | 0 | -8833159.82 |  |  |  | 8833159.82 | 2018-05-31 | 2018-06-06 | 2018-06-14 | 45 | 2018-07-29 | 2018-07-04 | 72885460.08 | 0 | [5 empty] | 217074 | 12587450.0972 | 72885460.08 | 8833159.82 | 0 |  |  |  | SIEMENS - Sokhna7 | 07
SIEMENS - Sokhna | 1 | 8 | 18208993.38 | 0 | -18208993.38 | 12641621.4 | 0 | -12641621.4 |  |  |  | 12641621.4 | 2018-06-30 | 2018-07-05 | 2018-06-28 | 45 | 2018-08-12 | 2018-07-19 | 91094453.46 | 0 | [5 empty] | 230703 | 18208993.38 | 91094453.46 | 12641621.4 | 0 |  |  |  | SIEMENS - Sokhna8 | 08
SIEMENS - Sokhna | 1 | 9 | 19922320.61 | 0 | -19922320.61 | 13673026.82 | 0 | -13673026.82 |  |  |  | 13673026.82 | 2018-07-31 | 2018-08-01 | 2018-08-05 | 45 | 2018-09-19 | 2018-09-03 | 111016774.07 | 0 | [5 empty] | 403689 | 19922320.61 | 111016774.07 | 13673026.82 | 0 |  |  |  | SIEMENS - Sokhna9 | 09
SIEMENS - Sokhna | 1 | 10 | 9128690.32 | 0 | -9128690.32 | 6271528.33 | 0 | -6271528.33 |  |  |  | 6271528.33 | 2018-08-31 | 2018-09-06 | 2018-09-17 | 45 | 2018-11-01 | 2018-09-25 | 120145464.39 | 0 | [5 empty] | 430957 | 9128690.32 | 120145464.39 | 6271528.33 | 0 |  |  |  | SIEMENS - Sokhna10 | 010
SIEMENS - Sokhna | 1 | 11 | 7601906.76 | 0 | -7601906.76 | 5230123.67 | 0 | -5230123.67 |  |  |  | 5230123.66 | 2018-09-30 | 2018-09-30 | 2018-10-01 | 45 | 2018-11-15 | 2018-11-05 | 127747371.15 | 0 | [5 empty] | 446149 | 7601906.76 | 127747371.15 | 5230123.66 | 0 |  |  |  | SIEMENS - Sokhna11 | 011
SIEMENS - Sokhna | 1 | 12 | 28930012.4 | 0 | -28930012.4 | 20041232.56 | 0 | -20041232.56 |  |  |  | 20041232.56 | 2018-10-31 | 2018-10-28 | 2018-10-28 | 45 | 2018-12-12 | 2018-11-07 | 156677383.55 | [6 empty] | 366625 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna12 | 012
SIEMENS - Sokhna | 1 | 13 | 25830140.07 | 0 | -25830140.07 | 17822796.65 | 0 | -17822796.65 |  |  |  | 17822796.65 | 2018-11-30 | 2018-11-22 | 2018-11-22 | 45 | 2019-01-06 | 2018-11-27 | 182507523.62 | [6 empty] | 366625 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna13 | 013
SIEMENS - Sokhna | 1 | 14 | 28983532 | 0 | -28983532 | 20002003.08 | 0 | -20002003.08 |  |  |  | 20002003.08 | 2018-12-31 | 2018-12-09 | 2018-12-19 | 45 | 2019-02-02 | 2019-02-05 | 211491055.62 | [6 empty] | 363259 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna14 | 014
SIEMENS - Sokhna | 1 | 15 | 10573229.89 | 0 | -10573229.89 | 2699428.63 | 0 | -2699428.63 |  |  |  | 2699428.63 | 2018-12-31 | 2018-12-27 | 2019-01-05 | 45 | 2019-02-19 | 2019-02-05 | 222064285.51 | [6 empty] | 4959359 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna15 | 015
SIEMENS - Sokhna | 1 | 16 | 32022484.92 | 0 | -32022484.92 | 25271545.73 | 0 | -25271545.73 |  |  |  | 25271545.73 | 2018-12-31 | 2018-12-30 | 2019-01-15 | 45 | 2019-03-01 | 2019-01-23 | 254086770.43 | [6 empty] | 4959359 | 32022484.92 | 254086770.43 | 25271545.73 | 0 |  |  |  | SIEMENS - Sokhna16 | 016
SIEMENS - Sokhna | 1 | 17 | 57817326.87 | 0 | -57817326.87 | 20418831.59 | 0 | -20418831.59 |  |  |  | 20418831.59 | 2019-02-28 | 2019-02-21 | 2019-01-31 | 45 | 2019-03-17 | 2019-04-22 | 311904097.3 | [6 empty] | 26029681 | 57817326.87 | 311904097.3 | 20418831.59 | 0 |  |  |  | SIEMENS - Sokhna17 | 017
SIEMENS - Sokhna | 1 | 18 | 11495973.02 | 0 | -11495973.02 | 12124718 | 0 | -12124718 |  |  |  | 12124718 | 2019-07-31 | 2019-08-07 | 2019-08-20 | 45 | 2019-10-04 | 2019-10-02 | 323400070.32 | [6 empty] | 20785977 | 0 | 0 | 15000000 | 0 |  |  |  | SIEMENS - Sokhna18 | 018
SIEMENS - Sokhna | 1 | 19 |  | 0 | 0 | 25672200.91 | 0 | -25672200.91 |  |  |  |  | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna19 | 019
SIEMENS - Sokhna | 1 | 20 |  | 0 | 0 | 15319191.73 | 0 | -15319191.73 |  |  |  |  | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 | 2023-10-25 | [7 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna20 | 020
SIEMENS - Sokhna | 1 | 21 |  | 0 | 0 | 888628.7 | 0 | -888628.7 |  |  |  |  | 2020-07-31 | 2020-07-15 | 2020-07-15 | 45 | 2020-08-29 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SIEMENS - Sokhna21 | 021
SMP1 - Revamp | 1 | 1 | 3199345.21 | 0 | -3199345.21 | 13906048.2 | 0 | -13906048.2 |  |  |  | 2399508.91 | 2022-12-31 | 2023-01-02 | 2023-01-04 | 42 | 2023-02-15 | 2023-02-02 | 3199345.21 | [6 empty] | 0 | 3199345.21 | 3199345.21 | 2399508.91 | 0 |  |  |  | SMP1 - Revamp1 | 01
SMP1 - Revamp | 1 | 2 | 1797569.47 | 0 | -1797569.47 | 25693427.5 | 0 | -25693427.5 |  |  |  | 1348177.1 | 2023-01-31 | 2023-02-14 | 2023-02-15 | 42 | 2023-03-29 | 2023-05-02 | 4996914.68 | [6 empty] | 0 | 1797569.47 | 4996914.68 | 1348177.1 | 0 |  |  |  | SMP1 - Revamp2 | 02
SMP1 - Revamp | 1 | 3 | 2879525.92 | 0 | -2879525.92 | 16806572.5 | 0 | -16806572.5 |  |  |  | 2159644.45 | 2023-04-30 | 2023-05-03 | 2023-05-24 | 42 | 2023-07-05 |  | 7876440.6 | [6 empty] | 0 | 2879525.92 | 7876440.6 | 2159644.45 | 0 |  |  |  | SMP1 - Revamp3 | 03
SMP1 - Revamp | 1 | 4 | 3836789.63 | 0 | -3836789.63 | 2647384.8437 | 0 | -2647384.8437 |  |  |  | 2877592.22 | 2023-05-31 | 2023-06-06 | 2023-07-13 | 42 | 2023-08-24 | 2023-09-01 | 11713230.23 | [6 empty] | 0 | 3836789.63 | 11713230.23 | 2877592.22 | 0 |  |  |  | SMP1 - Revamp4 | 04
SMP1 - Revamp | 1 | 5 | 4135898.1 | 0 | -4135898.1 | 2853769.6857 | 0 | -2853769.6857 |  |  |  | 3101923.57 | 2023-07-31 | 2023-07-25 | 2023-07-25 | 42 | 2023-09-05 | 2023-09-12 | 15849128.33 | [6 empty] | 0 | 4135898.1 | 15849128.33 | 3101923.57 | 0 |  |  |  | SMP1 - Revamp5 | 05
SMP1 - Revamp | 1 | 6 | 8858061.69 | 0 | -8858061.69 | 6112062.5631 | 0 | -6112062.5631 |  |  |  | 6643546.26 | 2023-08-31 | 2023-08-30 | 2023-09-06 | 42 | 2023-10-18 | 2023-10-10 | 24707190.02 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Revamp6 | 06
SMP1 - Revamp | 1 | 7 | 4571797.25 | 0 | -4571797.25 | 3154540.1 | 0 | -3154540.1 |  |  |  | 3428847.94 | 2023-10-31 | 2023-10-15 | 2023-10-15 | 42 | 2023-11-26 | 2023-11-21 | 29278987.27 | [6 empty] | 0 | 4571797.25 | 29278987.27 | 3428847.94 | 0 |  |  |  | SMP1 - Revamp7 | 07
SMP1 - Revamp | 1 | 8 | 2887080.34 | 0 | -2887080.34 | 1992085.4366 | 0 | -1992085.4366 |  |  |  | 2165310.25 | 2023-12-31 | 2023-12-06 | 2023-12-06 | 42 | 2024-01-17 | 2024-01-15 | 32166067.61 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Revamp8 | 08
SMP1 - Revamp | 1 | 9 | 1572976.38 | 0 | -1572976.38 | 0 | 0 | 0 |  |  |  | 1179732.3 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-28 | 33739043.99 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Revamp9 | 09
SMP1 - Revamp | 1 | 10 | 5011477.79 | 0 | -5011477.79 | 0 | 0 | 0 |  |  |  | 3758608.34 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-06-04 | 38750521.78 | [6 empty] | 0 | 5011477.79 | 38750521.78 | 3758608.34 | 0 |  |  |  | SMP1 - Revamp10 | 010
SMP1 - Shut Down | 1 | 1 | 15192302.49 | 0 | -15192302.49 | 5388381.94 | 0 | -5388381.94 |  |  |  | 8203843.34 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2023-10-18 | 15192302.49 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Shut Down1 | 01
SMP1 - Shut Down | 1 | 2 | 17650842.77 | 0 | -17650842.77 | 15140879.8914 | 0 | -15140879.8914 |  |  |  | 9531455.1 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2024-04-07 | 32843145.26 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Shut Down2 | 02
SMP1 - Shut Down | 1 | 3 |  | 0 | 0 | 8648912.9484 | 0 | -8648912.9484 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-04-24 | 42 | 2024-06-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP1 - Shut Down3 | 03
SMP2 - Shut Down | 1 | 2 | 17053490.95 | 0 | -17053490.95 | 5426194.9513 | 0 | -5426194.9513 |  |  |  | 5979888.32 | 2023-12-31 | 2023-12-09 | 2023-12-09 | 42 | 2024-01-20 | 2024-01-07 | 49896636.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP2 - Shut Down2 | 02
SMP2 - Shut Down | 1 | 3 | 1490218.79 | 0 | -1490218.79 | 581185.34 | 0 | -581185.34 |  |  |  | 804718.15 | 2024-02-29 | 2024-02-27 | 2024-02-27 | 42 | 2024-04-09 | 2024-04-07 | 51386855 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SMP2 - Shut Down3 | 03
Sodic Club House | 1 | 23 | 10526350.27 | 0 | -10526350.27 | 2727407.25 | 0 | -2727407.25 |  |  |  | 2727407.23 | 2017-09-30 | 2017-09-19 | 2017-11-01 | 35 | 2017-12-06 | 2017-11-05 | 55308912.13 | 10641245.16 | [5 empty] | 83598.95 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House23 | Sodic Club House23
Sodic Club House | 1 | 24 | 6326663.77 | 0 | -6326663.77 | 4528572.66 | 0 | -4528572.66 |  |  |  | 4528572.66 | 2017-10-31 | 2017-11-01 | 2017-11-03 | 35 | 2017-12-08 | 2017-12-17 | 61635575.9 | 10347994.62 | [5 empty] | 33598.95 | 7208751.86 | 64461008.2542 | 4713913.05 | Sodic Club House |  |  |  | Sodic Club House24 | Sodic Club House24
Sodic Club House | 1 | 25 | 3617825.39 | 1334415.96 | -2283409.43 | 894280.83 | 992455.088 | 98174.258 |  |  |  | 894280.74 | 2017-11-30 | 2017-12-01 | 2017-12-10 | 35 | 2018-01-14 | 2018-01-24 | 65253401.29 | 8215432.94 | [5 empty] | 33598.95 | 4060848.9478 | 65696424.8478 | 1796642.04 | Sodic Club House |  |  |  | Sodic Club House25 | Sodic Club House25
Sodic Club House | 1 | 26 | 4263027.4013 | 0 | -4263027.4013 | 2563543.65 | 0 | -2563543.65 |  |  |  | 2563543.8087 | 2017-12-31 | 2018-01-16 | 2018-01-16 | 35 | 2018-02-20 | 2018-02-22 | 69516428.6913 | 7922726.9562 | [5 empty] | 33598.95 | 5215631.634 | 70469032.924 | 3193789.29 | Sodic Club House |  |  |  | Sodic Club House26 | Sodic Club House26
Sodic Club House | 1 | 27 | 6447136.9087 | 0 | -6447136.9087 | 7171420.81 | 0 | -7171420.81 |  |  |  | 7171420.74 | 2018-02-28 | 2018-02-20 | 2018-03-01 | 35 | 2018-04-05 | 2018-04-01 | 86100596.85 | 8271503.62 | [5 empty] | 133598.95 | 6347559.6681 | 86021988.3593 | 4891559.01 | Sodic Club House |  |  |  | Sodic Club House27 | Sodic Club House27
Sodic Club House | 1 | 28 | 3235550.4912 | 5110738.79 | 1875188.2988 | 3643251.2 | 5960049.8995 | 2316798.6995 |  |  |  | 3643251.21 | 2018-03-31 | 2018-03-20 | 2018-03-20 | 35 | 2018-04-24 | 2018-05-08 | 89336147.3412 | 10814924.0552 | [5 empty] | 133598.95 | 4455128.7309 | 90555725.5809 | 4314232.28 | Sodic Club House |  |  |  | Sodic Club House28 | Sodic Club House28
Sodic Club House | 1 | 29 | 5735280.6088 | 6355200.49 | 619919.8812 | 2927170 | 6349192.7245 | 3422022.7245 |  |  |  | 2949189.68 | 2018-04-30 | 2018-04-20 | 2018-04-21 | 35 | 2018-05-26 | 2018-05-17 | 95071427.95 | 13429692.21 | [5 empty] | 133598.95 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House29 | Sodic Club House29
Sodic Club House | 1 | 30 | 5753955.1349 | 3864214.5 | -1889740.6349 | 1523667.33 | 3772207.955 | 2248540.625 |  |  |  | 1501648.1708 | 2018-05-31 | 2018-05-25 | 2018-05-28 | 35 | 2018-07-02 | 2018-06-26 | 100825383.0849 | 13579694.3883 | [5 empty] | 39041.91 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House30 | Sodic Club House30
Sodic Club House | 1 | 31 | 4997405.8346 | 2806299.13 | -2191106.7046 | 3752933.22 | 6752933.2165 | 2999999.9965 |  |  |  | 1752933.23 | 2018-06-30 | 2018-07-02 | 2018-07-04 | 35 | 2018-08-08 | 2018-08-02 | 105822788.9195 | 13390603.7948 | [5 empty] | 41801.91 | 9473412.9251 | 110298796.01 | 4843252.93 | Sodic Club House |  |  |  | Sodic Club House31 | Sodic Club House31
Sodic Club House | 1 | 32 | 7298776.2492 | 6867125.7 | -431650.5492 | 1851323.25 | 1852842.635 | 1519.385 |  |  |  | 1851323.2394 | 2018-07-31 | 2018-08-01 | 2018-07-30 | 35 | 2018-09-03 | 2018-09-04 | 113121565.1688 | 11999237.9332 | [5 empty] | 45521.91 | 11500368.6175 | 117323157.537 | 5655167.4 | Sodic Club House |  |  |  | Sodic Club House32 | Sodic Club House32
Sodic Club House | 1 | 33 | 6841826.5835 | 6742632.54 | -99194.0435 | 5028067.13 | 5855002.737 | 826935.607 |  |  |  | 5028067.13 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 35 | 2018-10-11 | 2018-10-09 | 119963391.7522 | 12452865.1519 | [5 empty] | 76081.91 | 7276853.7793 | 124600011.3163 | 7190786.09 | Sodic Club House |  |  |  | Sodic Club House33 | Sodic Club House33
Sodic Club House | 1 | 34 | 9547045.4302 | 7360347.44 | -2186697.9902 | 1372787.19 | 6269587.212 | 4896800.022 |  |  |  | 1372787.19 | 2018-09-30 | 2018-10-15 | 2018-10-15 | 35 | 2018-11-19 | 2018-11-21 | 129510437.1825 | 9699552.55 | [5 empty] | 541161.91 | 14426802.9732 | 134390194.7255 | 10029446.47 | Sodic Club House |  |  |  | Sodic Club House34 | Sodic Club House34
Sodic Club House | 1 | 35 | 17370468.2779 | 4583109.75 | -12787358.5279 | 2061960.96 | 2565043.8775 | 503082.9175 |  |  |  | 2061960.9553 | 2018-11-30 | 2018-11-25 | 2018-11-25 | 35 | 2018-12-30 | 2019-12-20 | 146880905.4603 | 8284813.5766 | [5 empty] | 557361.91 | 10886083.2297 | 140396520.4122 | 6956090.906 | Sodic Club House |  |  |  | Sodic Club House35 | Sodic Club House35
Sodic Club House | 1 | 36 | 15653205.9497 | 29270095.76 | 13616889.8103 | 9516540.66 | 10543541.848 | 1027001.188 |  |  |  | 3000000 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 56 | 2019-08-27 | 2019-12-19 | 162534111.41 | [6 empty] | 4804784.65 | 0 | 0 | 7000000 | Sodic Club House |  |  |  | Sodic Club House36 | Sodic Club House36
Sodic Club House | 1 | 37 |  | 0 | 0 | 4028521 | 0 | -4028521 |  |  |  |  | 2020-08-31 | 2020-08-11 | 2020-08-11 | 56 | 2020-10-06 | [8 empty] | 0 | 0 | 0 | 0 | Sodic Club House |  |  |  | Sodic Club House37 | Sodic Club House37
Sodic Eastown | 1 | 1 | 9063098.3369 | 9063098.33 | -0.0068571 | 138789620.12 | 6789620.1165 | -132000000.0035 | 122000000 | 10000000 |  | 6785088.5699 | 2019-03-31 | 2019-03-17 | 2019-03-17 | 42 | 2019-04-28 | 2019-03-20 | 9063098.3369 | [6 empty] | 0 | 9063098.3369 | 9063098.3369 | 6785088.5699 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown1 | EDNC Retail & Offices Civil1
Sodic Eastown | 1 | 2 | 20887437.3108 | 20887437.31 | -0.00076191 | 21566541.66 | 15638373.6555 | -5928168.0045 | 5928168 |  |  | 15652355.21 | 2019-04-30 | 2019-04-20 | 2019-04-16 | 42 | 2019-05-28 | 2019-04-18 | 29950535.6476 | [6 empty] | 0 | 20887437.3108 | 29950535.6476 | 15652355.21 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown2 | EDNC Retail & Offices Civil2
Sodic Eastown | 1 | 3 | 2101069.4381 | 2101069.44 | 0.0019048 | 1574016.18 | 1574016.182 | 0.002 |  |  |  | 1574016.17 | 2019-05-31 | 2019-05-20 | 2019-05-19 | 42 | 2019-06-30 | 2019-05-23 | 32051605.0857 | [6 empty] | 0 | 2101069.4381 | 32051605.0857 | 1574016.17 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown3 | EDNC Retail & Offices Civil3
Sodic Eastown | 1 | 4 | 22270031.4 | 36280262.26 | 14010230.86 | 25688338.61 | 26537436.313 | 849097.703 |  |  |  | 26267292.44 | 2019-06-30 | 2019-06-25 | 2019-06-23 | 42 | 2019-08-04 | 2019-07-08 | 54321636.4857 | [6 empty] | 0 | 22270031.4 | 54321636.4857 | 26267292.44 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown4 | EDNC Retail & Offices Civil4
Sodic Eastown | 1 | 5 | 45005158.6118 | 50370296.9 | 5365138.2882 | 37056568.4 | 37056568.405 | 0.005 |  |  |  | 22056568.4027 | 2019-07-31 | 2019-07-25 | 2019-07-25 | 42 | 2019-09-05 | 2019-08-01 | 99326795.0975 | 20344137.6 | [5 empty] | 144395.63 | 45005158.6118 | 99326795.0975 | 22056568.4027 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown5 | EDNC Retail & Offices Civil5
Sodic Eastown | 1 | 6 | 38734277.1501 | 38734277.15 | -9.5248e-05 | 28554847.67 | 28614412.9875 | 59565.3175 |  |  |  | 28554847.68 | 2019-08-31 | 2019-08-25 | 2019-08-19 | 42 | 2019-09-30 | 2019-09-08 | 138061072.2476 | 20344137.6 | [5 empty] | 607331.68 | 38734277.1501 | 138061072.2476 | 28554847.68 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown6 | EDNC Retail & Offices Civil6
Sodic Eastown | 1 | 7 | 65627417.1905 | 46252048.05 | -19375369.1405 | 38197130.95 | 38197130.9705 | 0.0205 |  |  |  |  | 2019-09-30 | 2019-09-25 | 2019-09-16 | 42 | 2019-10-28 | 2019-11-03 | 203688489.4381 | 5537718 | [5 empty] | 921272.68 | 0 | 0 | 38890621.0473 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown7 | EDNC Retail & Offices Civil7
Sodic Eastown | 1 | 8 | 85059782.1524 | 82004688.27 | -3055093.8824 | 55532397.61 | 59087057.7335 | 3554660.1235 |  |  |  | 58794871.95 | 2019-10-31 | 2019-10-30 | 2019-11-02 | 42 | 2019-12-14 | 2019-11-14 | 288748271.5905 | 1266429.46 | [5 empty] | 707331.68 | 85059782.1524 | 288748271.5905 | 58794871.95 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown8 | EDNC Retail & Offices Civil8
Sodic Eastown | 1 | 9 | 16046909.9143 | 19102003.8 | 3055093.8857 | 40504812.26 | 40883545.558 | 378733.298 |  |  |  | 40504812.26 | 2019-11-30 | 2019-11-30 | 2019-12-03 | 42 | 2020-01-14 | 2019-12-30 | 304795181.5048 | 39767000.8 | [5 empty] | 2750976.18 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown9 | EDNC Retail & Offices Civil9
Sodic Eastown | 1 | 10 | 82638241.0762 | 82638241.08 | 0.0038105 | 32553581.24 | 33486093.464 | 932512.224 |  |  |  | 32553581.24 | 2019-12-31 | 2019-12-31 | 2020-01-07 | 42 | 2020-02-18 | 2020-01-20 | 387433422.581 | 1e-06 | [5 empty] | 3038523.68 | 88119712.7238 | 392914894.2286 | 36785436.36 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown10 | EDNC Retail & Offices Civil10
Sodic Eastown | 1 | 11 | 36710088.5775 | 36710088.58 | 0.0025457 | 27179529.3929 | 29504362.289 | 2324832.8961 |  |  |  | 27179529.3929 | 2020-01-31 | 2020-01-31 | 2020-02-03 | 42 | 2020-03-16 | 2020-02-19 | 424143511.1584 | [6 empty] | 3038523.68 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown11 | EDNC Retail & Offices Civil11
Sodic Eastown | 1 | 12 | 26833421.413 | 33309635.84 | 6476214.427 | 19553108.79 | 24940111.3195 | 5387002.5295 |  |  |  | 19553108.77 | 2020-02-29 | 2020-02-29 | 2020-03-04 | 42 | 2020-04-15 | 2020-03-29 | 450976932.5714 | [6 empty] | 3314791.44 | 26833421.413 | 450976932.5714 | 19553108.77 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown12 | EDNC Retail & Offices Civil12
Sodic Eastown | 1 | 13 | 22228765.6121 | 15752551.19 | -6476214.4221 | 16201534.04 | 13698867.9095 | -2502666.1305 |  |  |  | 16201534.04 | 2020-03-31 | 2020-03-24 | 2020-03-25 | 42 | 2020-05-06 | 2020-05-17 | 473205698.1835 | [6 empty] | 2704423.44 | 26192906.0286 | 477169838.6 | 19217788.54 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown13 | EDNC Retail & Offices Civil13
Sodic Eastown | 1 | 14 | 24418089.9689 | 24418089.97 | 0.00114 | 16537461.58 | 17859899.4785 | 1322437.8985 |  |  |  | 16537461.58 | 2020-04-30 | 2020-05-07 | 2020-05-10 | 42 | 2020-06-21 | 2020-06-15 | 497623788.1524 | [6 empty] | 3495935.44 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown14 | EDNC Retail & Offices Civil14
Sodic Eastown | 1 | 15 | 19101976.1176 | 19101976.12 | 0.0023695 | 12895954 | 12895954 | 0 |  |  |  | 12895953.9558 | 2020-05-31 | 2020-06-02 | 2020-06-06 | 42 | 2020-07-18 | 2020-06-23 | 516725764.27 | [6 empty] | 4174771.13 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown15 | EDNC Retail & Offices Civil15
Sodic Eastown | 1 | 16 | 42785902.7013 | 42785902.69 | -0.01126 | 30145771.57 | 31947230.0345 | 1801458.4645 |  |  |  | 30145771.5315 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 42 | 2020-08-15 | 2020-08-10 | 559511666.9713 | [6 empty] | 4707294.52 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown16 | EDNC Retail & Offices Civil16
Sodic Eastown | 1 | 17 | 30425304.0673 | 30425304.07 | 0.00268 | 20899381.34 | 23516460.0735 | 2617078.7335 |  |  |  | 20899381.3823 | 2020-07-31 | 2020-08-08 | 2020-08-10 | 42 | 2020-09-21 | 2020-09-07 | 589936971.0386 | [6 empty] | 5466992.46 | 33693489.0097 | 593205155.981 | 22896073.3381 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown17 | EDNC Retail & Offices Civil17
Sodic Eastown | 1 | 18 | 36663335.5424 | 39729323.85 | 3065988.3076 | 22406610.78 | 26361312.3025 | 3954701.5225 |  |  |  | 22406610.78 | 2020-08-31 | 2020-08-31 | 2020-09-03 | 42 | 2020-10-15 | 2020-10-11 | 626600306.581 | [6 empty] | 5860427.46 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown18 | EDNC Retail & Offices Civil18
Sodic Eastown | 1 | 19 | 48818243.381 | 45752255.09 | -3065988.291 | 34417592.72 | 30462891.204 | -3954701.516 |  |  |  | 34417592.72 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 42 | 2020-11-15 | 2020-11-15 | 675418549.9619 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown19 | EDNC Retail & Offices Civil19
Sodic Eastown | 1 | 20 | 81649174.4522 | 45598330.5 | -36050843.9522 | 31197031.83 | 31197031.845 | 0.015 |  |  |  | 31197031.7827 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 42 | 2020-12-15 | 2020-12-14 | 757067724.4141 | [6 empty] | 6575145.76 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown20 | EDNC Retail & Offices Civil20
Sodic Eastown | 1 | 21 | 8971634.0811 | 45022478.11 | 36050844.0289 | 29743783.32 | 32167186.0755 | 2423402.7555 |  |  |  | 29743783.27 | 2020-11-30 | 2020-11-30 | 2020-12-03 | 42 | 2021-01-14 | 2021-01-20 | 766039358.4952 | [6 empty] | 7317323.76 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown21 | EDNC Retail & Offices Civil21
Sodic Eastown | 1 | 22 | 29539477.0571 | 29539476.98 | -0.077143 | 19964135.7 | 19964135.699 | -0.001 |  |  |  | 19964135.7 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 42 | 2021-02-16 | 2021-02-09 | 795578835.5524 | [6 empty] | 7664787.88 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown22 | EDNC Retail & Offices Civil22
Sodic Eastown | 1 | 23 | 23832998.7215 | 23832998.72 | -0.0014571 | 19672746.63 | 15672746.626 | -4000000.004 |  |  |  | 19672746.6443 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 42 | 2021-03-18 | 2021-03-04 | 819411834.2738 | [6 empty] | 8075062.48 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown23 | EDNC Retail & Offices Civil23
Sodic Eastown | 1 | 24 | 24555503.3928 | 24555503.39 | -0.0028286 | 14713744.17 | 18782844.0895 | 4069099.9195 |  |  |  | 14713744.16 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 42 | 2021-04-18 | 2021-04-11 | 843967337.6667 | [6 empty] | 8705062.48 | 25445155.6214 | 844856989.8952 | 17436083.38 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown24 | EDNC Retail & Offices Civil24
Sodic Eastown | 1 | 25 | 29789861.881 | 29789862.02 | 0.13897 | 18632387.16 | 22686187.95 | 4053800.79 |  |  |  | 18632387.0541 | 2021-03-31 | 2021-03-31 | 2021-04-05 | 42 | 2021-05-17 | 2021-05-18 | 873757199.5477 | [6 empty] | 9572854.12 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown25 | EDNC Retail & Offices Civil25
Sodic Eastown | 1 | 26 | 45459659.9094 | 45459659.77 | -0.13945 | 32407888.61 | 33907888.6085 | 1499999.9985 |  |  |  | 32407888.61 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 42 | 2021-06-16 | 2021-06-17 | 919216859.4571 | [6 empty] | 9252854.12 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown26 | EDNC Retail & Offices Civil26
Sodic Eastown | 1 | 27 | 30032935.1619 | 30032935.16 | -0.0019049 | 21101612.82 | 23241827.868 | 2140215.048 |  |  |  | 21101612.82 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-07-11 | 949249794.619 | [6 empty] | 8752562.48 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown27 | EDNC Retail & Offices Civil27
Sodic Eastown | 1 | 28 | 37125243.7619 | 37125243.76 | -0.0019046 | 41708616.23 | 26708616.218 | -15000000.012 |  |  |  | 41708616.23 | 2021-06-30 | 2021-06-30 | 2021-07-07 | 42 | 2021-08-18 | 2021-08-09 | 986375038.381 | [6 empty] | 11397821.25 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown28 | EDNC Retail & Offices Civil28
Sodic Eastown | 1 | 29 | 26258236.2286 | 26258236.23 | 0.0014285 | 10880905.48 | 20811984.9815 | 9931079.5015 |  |  |  | 10880905.48 | 2021-07-31 | 2021-07-24 | 2021-08-07 | 42 | 2021-09-18 | 2021-09-06 | 1012633274.6095 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown29 | EDNC Retail & Offices Civil29
Sodic Eastown | 1 | 30 | 27535188.381 | 27535188.38 | -0.00095248 | 25479297.36 | 24351196.859 | -1128100.501 |  |  |  | 25479297.36 | 2021-08-31 | 2021-08-31 | 2021-09-07 | 42 | 2021-10-19 | 2021-10-17 | 1040168462.9905 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown30 | EDNC Retail & Offices Civil30
Sodic Eastown | 1 | 31 | 20856328.3905 | 20856328.39 | -0.00047611 | 22493923.41 | 17493923.131 | -5000000.279 |  |  |  | 22493923.51 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 42 | 2021-11-21 | 2021-11-14 | 1061024791.381 | [6 empty] | 9824319.61 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown31 | EDNC Retail & Offices Civil31
Sodic Eastown | 1 | 32 | 17472419.8762 | 17472419.88 | 0.0038096 | 15680621.74 | 19068785.824 | 3388164.084 |  |  |  | 15680621.74 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 42 | 2021-12-20 | 2021-12-07 | 1078497211.2571 | [6 empty] | 9524319.61 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown32 | EDNC Retail & Offices Civil32
Sodic Eastown | 1 | 33 | 15003172.5524 | 15003172.55 | -0.002381 | 19311419.98 | 13807649.9075 | -5503770.0725 |  |  |  | 19311419.98 | 2021-11-30 | 2021-11-30 | 2021-12-07 | 42 | 2022-01-18 | 2021-12-14 | 1093500383.8095 | [6 empty] | 10022759.48 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown33 | EDNC Retail & Offices Civil33
Sodic Eastown | 1 | 34 | 4991381.7048 | 4991381.7 | -0.0047617 | 4602037.61 | 2767127.555 | -1834910.055 |  |  |  | 4602037.62 | 2021-12-31 | 2021-12-31 | 2021-12-27 | 42 | 2022-02-07 | 2022-03-10 | 1098491765.5143 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown34 | EDNC Retail & Offices Civil34
Sodic Eastown | 1 | 35 | 46695355.6476 | 46695355.64 | -0.0076193 | 12555804.9 | 45515831.938 | 32960027.038 |  |  |  | 12555805.27 | 2022-04-30 | 2022-04-30 | 2022-05-18 | 42 | 2022-06-29 | 2022-06-14 | 1145187121.1619 |  | 110343302 |  | -4596809 | 30061161 | 30061161 | 28213034 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown35 | EDNC Retail & Offices Civil35
Sodic Eastown | 1 | 36 | -0.0001 | 0 | 0.0001 | 6254389.49 | 0 | -6254389.49 |  |  |  | 3904269.49 | 2022-07-31 | 2022-08-13 | 2022-08-15 | 42 | 2022-09-26 | 2022-09-12 | 1145187121.1619 |  | 110343302.03 |  | -2378666.59 | 30061161.93 | 30061161.93 | 32117303 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown36 | EDNC Retail & Offices Civil36
Sodic Eastown | 1 | 37 | -1e-05 | 0 | 1e-05 | 5035428.4 | 0 | -5035428.4 |  |  |  | 5035428.4 | 2022-12-31 | 2022-12-26 | 2023-01-01 | 42 | 2023-02-12 | 2023-01-22 | 1145187121.1619 |  | 110343302.03 |  | -2378666.59 | 18874299.6215 | 18874299.6215 | 19273337.4308 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown37 | EDNC Retail & Offices Civil37
Sodic Eastown | 1 | 38 | -0.00011 | 0 | 0.00011 | 2231188 | 0 | -2231188 |  |  |  | 2231188.43 | 2022-06-30 | 2022-06-12 | 2023-06-22 | 42 | 2023-08-03 | 2023-08-01 | 1145187121.1619 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown38 | EDNC Retail & Offices Civil38
Sodic Eastown | 1 | 39 |  | 0 | 0 | 17894573 | 0 | -17894573 |  |  |  | 28315194.9811 | 2023-06-30 | 2023-06-30 | 2023-10-22 | 42 | 2023-12-03 | 2023-10-29 | 1145187121.1619 |  | 110343302.92 |  | -4596809.26 | 30061161.9302 | 30061161.9302 | -12704609.7849 | 0 | 0 | 0 | EDNC Retail & Offices Civil |  |  |  | Sodic Eastown39 | EDNC Retail & Offices Civil39
Sodic Eastown - Landscape | 1 | 1 | 1310241.4095 | 1310241.41 | 0.00047619 | 1545976.54 | 1589312.7705 | 43336.2305 |  |  |  | 1545976.52 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 42 | 2022-02-20 | 2022-02-14 | 1310241.4095 | 710231.1 | [5 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape1 | EDNC Hardscape Package1
Sodic Eastown - Landscape | 1 | 2 | 3185965.6857 | 3188822.83 | 2857.1443 | 2689319.17 | 2794789.4915 | 105470.3215 |  |  |  | 2689319.17 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 42 | 2022-03-17 | 2022-03-10 | 4496207.0952 | 1064088.68 | [5 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape2 | EDNC Hardscape Package2
Sodic Eastown - Landscape | 1 | 3 | 5417455.381 | 5414598.24 | -2857.141 | 5060960.68 | 5240048.512 | 179087.832 |  |  |  | 8060960.68 | 2022-03-31 | 2022-03-15 | 2022-03-17 | 42 | 2022-04-28 | 2022-03-31 | 9913662.4762 | [6 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape3 | EDNC Hardscape Package3
Sodic Eastown - Landscape | 1 | 4 | 1923818.4 | 1923818.4 | 0 | 4237695.68 | 4301325.99 | 63630.31 |  |  |  | 4237695.69 | 2022-04-30 | 2022-04-13 | 2022-04-13 | 42 | 2022-05-25 | 2022-04-14 | 11837480.8762 | 7645419.29 | [5 empty] | 433157 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape4 | EDNC Hardscape Package4
Sodic Eastown - Landscape | 1 | 5 | 8146275.9524 | 8146275.95 | -0.002381 | 2847434.11 | 3116872.1575 | 269438.0475 |  |  |  | 2847434.08 | 2022-04-30 | 2022-05-10 | 2022-05-11 | 42 | 2022-06-22 | 2022-05-11 | 19983756.8286 | 4687295.11 | 494379.4 |  |  | 641755.99 | 641755.99 | 477225 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape5 | EDNC Hardscape Package5
Sodic Eastown - Landscape | 1 | 6 | 2241713.4381 | 2241713.44 | 0.0019048 | 1865468.85 | 1939613.522 | 74144.672 |  |  |  | 1865468.85 | 2022-05-31 | 2022-05-17 | 2022-05-22 | 42 | 2022-07-03 | 2022-05-24 | 22225470.2667 | 4887618.75 | 704722.2 |  |  | 705609.06 | 705609.06 | 477225 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape6 | EDNC Hardscape Package6
Sodic Eastown - Landscape | 1 | 7 |  | 5611542.56 | 5611542.56 | 2249247.81 | 2434849.578 | 185601.768 |  |  |  |  | 2022-05-31 | 2022-06-10 | 2022-06-14 | 42 | 2022-07-26 | [8 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape7 | EDNC Hardscape Package7
Sodic Eastown - Landscape | 1 | 8 | 19106378.3905 | 16821952.2 | -2284426.1905 | 8937999.74 | 9494386.1475 | 556386.4075 |  |  |  | 13407927.22 | 2022-06-30 | 2022-06-26 | 2022-07-03 | 42 | 2022-08-14 | 2022-07-27 | 46943391.219 | 2302349.81 | 17134472.44 |  |  | 1289822.765 | 1289822.765 | 380000 | 19106378.3905 | 46943391.219 | 13407927.22 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape8 | EDNC Hardscape Package8
Sodic Eastown - Landscape | 1 | 9 | 2763176 | 5047602.19 | 2284426.19 | 837296.03 | 1004245.4695 | 166949.4395 |  |  |  | 837296.04 | 2022-08-31 | 2022-08-25 | 2022-08-30 | 42 | 2022-10-11 | 2022-09-13 | 49706567.219 |  | 17105387 |  |  | 1304797 | 1304797 | 489137 | 2763176 | 49706567.219 | 837296.04 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape9 | EDNC Hardscape Package9
Sodic Eastown - Landscape | 1 | 10 | 3106667.3429 | 3106667.35 | 0.0071429 | 2965081 | 3067833.9875 | 102752.9875 |  |  |  | 2965080.9889 | 2022-08-31 | 2022-08-28 | 2022-10-19 | 42 | 2022-11-30 | 2022-10-20 | 52813234.5619 | [6 empty] | 0 | 1723810.5333 | 51430377.7524 | 5311032.49 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape10 | EDNC Hardscape Package10
Sodic Eastown - Landscape | 1 | 11 | 2478048.6476 | 1095191.83 | -1382856.8176 | 970278.45 | 1006501.9215 | 36223.4715 |  |  |  | 970278.46 | 2022-09-30 | 2022-09-28 | 2022-11-05 | 42 | 2022-12-17 | 2022-11-15 | 53908426.4 |  | 20753354 |  |  |  |  | 581609 | 1095191.5143 | 52525569.2667 | 7657014.05 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape11 | EDNC Hardscape Package11
Sodic Eastown - Landscape | 1 | 12 | 2146120.2476 | 2146120.25 | 0.002381 | 2038310.81 | 2109293.391 | 70982.581 |  |  |  | 2038310.82 | 2022-10-31 | 2022-10-28 | 2022-11-15 | 42 | 2022-12-27 | 2022-11-22 | 56054546.6476 |  | 23518667 |  |  | 1471431.85 | 1471431.85 | 591609 | 1256657.1048 | 55165083.5048 | 8902796.13 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape12 | EDNC Hardscape Package12
Sodic Eastown - Landscape | 1 | 13 |  | 0 | 0 | 4532604.51 | 0 | -4532604.51 |  |  |  |  | 2023-05-31 | 2023-06-01 | 2023-10-16 | 42 | 2023-11-27 | [8 empty] | 0 | 0 | 0 | 0 | EDNC Hardscape Package |  |  |  | Sodic Eastown - Landscape13 | EDNC Hardscape Package13
Sokhna Port Expansion | 1 | 1 | 28642092.8 | 86955688.28 | 58313595.48 | 201618177 | 58103513.543 | -143514663.457 |  |  |  | 16602157.8 | 2022-01-31 | 2022-01-31 | 2022-03-14 | 53 | 2022-05-06 | 2022-03-24 | 28642092.8 | [6 empty] | 0 | 28642092.8 | 28642092.8 | 16602157.8 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion1 | Sokhna Port Expansion1
Sokhna Port Expansion | 1 | 2 | 30329196.74 | 52581626.44 | 22252429.7 | 52996310.3 | 29716122.1035 | -23280188.1965 |  |  |  | 19713977.881 | 2022-02-28 | 2022-02-28 | 2022-03-31 | 53 | 2022-05-23 | 2022-04-17 | 58971289.54 | [6 empty] | 0 | 30329196.74 | 58971289.54 | 19713977.881 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion2 | Sokhna Port Expansion2
Sokhna Port Expansion | 1 | 3 |  | 109972559.74 | 109972559.74 | 55802951.65 | 66267866.722 | 10464915.072 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-14 | 53 | 2022-06-06 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion3 | Sokhna Port Expansion3
Sokhna Port Expansion | 1 | 4 | 26384347.91 | 36792580.1 | 10408232.19 | 16604871.85 | 24902787.955 | 8297916.105 |  |  |  | 16604871.85 | 2022-04-30 | 2022-04-30 | 2022-05-25 | 53 | 2022-07-17 | 2022-07-31 | 174022377.11 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion4 | Sokhna Port Expansion4
Sokhna Port Expansion | 1 | 5 | 90184360.23 | 89304785.57 | -879574.66 | 59014964.55 | 62315765.265 | 3300800.715 |  |  |  | 58619834.1495 | 2022-06-30 | 2022-06-30 | 2022-07-28 | 53 | 2022-09-19 | 2022-09-30 | 264206737.34 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion5 | Sokhna Port Expansion5
Sokhna Port Expansion | 1 | 6 | 41088510.15 | 68200901.21 | 27112391.06 | 26209033.35 | 46645772.6455 | 20436739.2955 |  |  |  | 26707531.5975 | 2022-07-31 | 2022-07-31 | 2022-09-19 | 53 | 2022-11-11 | 2022-10-19 | 305295247.49 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion6 | Sokhna Port Expansion6
Sokhna Port Expansion | 1 | 7 |  | 58683528.55 | 58683528.55 | 36803665.95 | 39568483.31 | 2764817.36 |  |  |  |  | 2022-08-31 | 2022-08-31 | 2022-10-23 | 53 | 2022-12-15 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion7 | Sokhna Port Expansion7
Sokhna Port Expansion | 1 | 8 | 55834648.2 | 52378217.65 | -3456430.55 | 36284090.45 | 36284089.65 | -0.8 |  |  |  | 36284090.45 | 2022-09-30 | 2022-09-30 | 2022-11-16 | 53 | 2023-01-08 | 2022-12-20 | 418825805.92 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion8 | Sokhna Port Expansion8
Sokhna Port Expansion | 1 | 9 | 46210885.16 | 43350211.2 | -2860673.96 | 30030028.45 | 30030028.52 | 0.07 |  |  |  | 30030028.45 | 2022-10-31 | 2022-10-31 | 2022-12-15 | 53 | 2023-02-06 | 2023-01-02 | 465036691.08 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion9 | Sokhna Port Expansion9
Sokhna Port Expansion | 1 | 10 | 42258919.66 | 39642891.35 | -2616028.31 | 27461819.5 | 27461819.55 | 0.05 |  |  |  | 27468297.779 | 2022-11-30 | 2022-11-30 | 2023-01-08 | 53 | 2023-03-02 | 2023-01-24 | 507295610.74 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion10 | Sokhna Port Expansion10
Sokhna Port Expansion | 1 | 11 | 69343976.76 | 73288962.77 | 3944986.01 | 50769799.2 | 50769799.2 | 0 |  |  |  | 50769799.2 | 2022-12-31 | 2022-12-31 | 2023-01-25 | 53 | 2023-03-19 | 2023-07-05 | 576639587.5 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion11 | Sokhna Port Expansion11
Sokhna Port Expansion | 1 | 12 | 106701066.13 | 101620062.95 | -5081003.18 | 70395885.55 | 70395885.55 | 0 |  |  |  | 70395885.55 | 2023-01-31 | 2023-01-31 | 2023-02-13 | 53 | 2023-04-07 | 2023-07-05 | 683340653.63 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion12 | Sokhna Port Expansion12
Sokhna Port Expansion | 1 | 13 | 41939163.73 | 29580920.45 | -12358243.28 | 491489.95 | 491489.95 | 0 |  |  |  | 27260456.4245 | 2023-02-28 | 2023-02-28 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 725279817.36 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion13 | Sokhna Port Expansion13
Sokhna Port Expansion | 1 | 14 | 18010876.44 | 31141539.9 | 13130663.46 | 6704080.85 | 6704080.85 | 0 |  |  |  | 11707069.686 | 2023-03-31 | 2023-03-31 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 743290693.8 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion14 | Sokhna Port Expansion14
Sokhna Port Expansion | 1 | 15 | 15185688.98 | 14245622.5 | -940066.48 | 4368115.65 | 4368115.65 | 0 |  |  |  | 9870697.837 | 2023-04-30 | 2023-04-30 | 2023-07-01 | 53 | 2023-08-23 | 2023-07-15 | 758476382.78 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion15 | Sokhna Port Expansion15
Sokhna Port Expansion | 1 | 16 | 37404208.29 | 35088709.6 | -2315498.69 | 23966243.5 | 23966243.524 | 0.024 |  |  |  | 24312735.3885 | 2023-05-31 | 2023-05-31 | 2023-08-07 | 53 | 2023-09-29 | 2023-08-07 | 795880591.07 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion16 | Sokhna Port Expansion16
Sokhna Port Expansion | 1 | 17 | 22411649.53 | 0 | -22411649.53 | 14567572.19 | 0 | -14567572.19 |  |  |  | 14567572.1945 | 2023-06-30 | 2023-06-30 | 2023-08-27 | 53 | 2023-10-19 | 2023-08-27 | 818292240.6 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion17 | Sokhna Port Expansion17
Sokhna Port Expansion | 1 | 18 |  | 0 | 0 | 14135207.0055 | 0 | -14135207.0055 |  |  |  |  | 2023-07-31 | 2023-07-31 | 2023-07-31 | 53 | 2023-09-22 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion18 | Sokhna Port Expansion18
Sokhna Port Expansion | 1 | 19 | 15685272.2 | 14714279.15 | -970993.05 | 10049896.61 | 10049896.6085 | -0.0015 |  |  |  | 10195426.93 | 2023-08-31 | 2023-08-31 | 2023-08-31 | 53 | 2023-10-23 | 2023-10-17 | 856365557.7 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion19 | Sokhna Port Expansion19
Sokhna Port Expansion | 1 | 20 | 20920498.28 | 19625420 | -1295078.28 | 13204353 | 13204354.1 | 1.1 |  |  |  | 13598323.882 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 53 | 2023-12-17 | 2023-11-20 | 877286055.98 | [6 empty] | 0 | 20920498.28 | 877286055.98 | 13598323.882 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion20 | Sokhna Port Expansion20
Sokhna Port Expansion | 1 | 21 | 9034186.8 | 8474927 | -559259.8 | 5788234 | 5788233.11 | -0.89 |  |  |  | 5872221.42 | 2023-10-31 | 2023-10-31 | 2023-12-27 | 53 | 2024-02-18 | 2023-12-27 | 886320242.78 | [6 empty] | 0 | 9034186.8 | 886320242.78 | 5872221.42 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion21 | Sokhna Port Expansion21
Sokhna Port Expansion | 1 | 22 | 3862923.74 | 3517168 | -345755.74 | 2510900.431 | 2087493.15 | -423407.281 |  |  |  | 2510900.431 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 53 | 2024-04-05 | 2024-02-05 | 890183166.52 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion22 | Sokhna Port Expansion22
Sokhna Port Expansion | 1 | 23 | 943826.94 | 0 | -943826.94 | 568614.519 | 0 | -568614.519 |  |  |  | 613487.511 | 2023-12-31 | 2023-12-31 | 2024-03-09 | 53 | 2024-05-01 | 2024-02-25 | 891126993.46 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion23 | Sokhna Port Expansion23
Sokhna Port Expansion- 100m | 1 | 1 |  | 86955688.28 | 86955688.28 | 39700885.25 | 58103513.543 | 18402628.293 |  |  |  |  | 2023-02-28 | 2023-02-28 | 2023-02-28 | 60 | 2023-04-29 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m1 | Sokhna Port Expansion1
Sokhna Port Expansion- 100m | 1 | 2 | 24129951.39 | 52581626.44 | 28451675.05 | 10628517.75 | 29716122.1035 | 19087604.3535 |  |  |  | 15684468.4035 | 2023-03-31 | 2023-03-31 | 2023-07-01 | 60 | 2023-08-30 | 2023-07-01 | 82118084.22 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m2 | Sokhna Port Expansion2
Sokhna Port Expansion- 100m | 1 | 3 | 26794714.09 | 109972559.74 | 83177845.65 | 10464912.35 | 66267866.722 | 55802954.372 |  |  |  | 17416564.1585 | 2023-04-30 | 2023-04-30 | 2023-08-07 | 60 | 2023-10-06 | 2023-08-07 | 108912798.31 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m3 | Sokhna Port Expansion3
Sokhna Port Expansion- 100m | 1 | 4 | 13246168.7303 | 36792580.1 | 23546411.3697 | 8297916 | 24902787.955 | 16604871.955 |  |  |  | 8610009.6747 | 2023-09-30 | 2023-09-30 | 2023-09-07 | 60 | 2023-11-06 | 2023-10-17 | 122158967.0403 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m4 | Sokhna Port Expansion4
Sokhna Port Expansion- 100m | 1 | 5 | 4703266.4897 | 89304785.57 | 84601519.0803 | 3240800 | 62315765.265 | 59074965.265 |  |  |  | 3057123.2183 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 60 | 2023-12-24 | 2023-11-20 | 126862233.53 | [6 empty] | 0 | 4703266.4897 | 126862233.53 | 3057123.2183 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m5 | Sokhna Port Expansion5
Sokhna Port Expansion- 100m | 1 | 6 | 29655965.57 | 68200901.21 | 38544935.64 | 20436714.5 | 46645772.6455 | 26209058.1455 |  |  |  | 29655965 | 2023-10-31 | 2023-10-31 | 2023-10-25 | 60 | 2023-12-24 | 2023-12-27 | 156518199.1 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m6 | Sokhna Port Expansion6
Sokhna Port Expansion- 100m | 1 | 7 | 4532607.67 | 58683528.55 | 54150920.88 | 3976775.9 | 39568483.31 | 35591707.41 |  |  |  | 2946194.9855 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 60 | 2024-04-12 | 2024-02-05 | 161050806.77 | [6 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion- 100m7 | Sokhna Port Expansion7
Sokhna Port Expansion-internal roads | 1 | 1 |  | 86955688.28 | 86955688.28 | 1800470.45 | 58103513.543 | 56303043.093 |  |  |  |  | 2022-07-31 | 2022-07-19 | 2022-10-31 | 60 | 2022-12-30 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion-internal roads1 | Sokhna Port Expansion1
Sokhna Port Expansion-internal roads | 1 | 2 |  | 52581626.44 | 52581626.44 | 3219.75 | 29716122.1035 | 29712902.3535 |  |  |  |  | 2022-08-31 | 2022-08-01 | 2022-11-28 | 60 | 2023-01-27 | [8 empty] | 0 | 0 | 0 | 0 | Sokhna Port Expansion |  |  |  | Sokhna Port Expansion-internal roads2 | Sokhna Port Expansion2
Sports Hall - Civil Works | 2 | 3 |  | 142963649.2 | 142963649.2 | 2493330 | 9602955 | 7109625 |  |  |  |  | 2021-01-31 | 2021-01-17 | 2021-01-17 | 60 | 2021-03-18 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works3 | Olympic Multi – Sports Hall3
Sports Hall - Civil Works | 2 | 4 |  | 61004415.08 | 61004415.08 | 10576930 | 14275990 | 3699060 |  |  |  |  | 2021-03-31 | 2021-03-17 | 2021-03-18 | 60 | 2021-05-17 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works4 | Olympic Multi – Sports Hall4
Sports Hall - Civil Works | 2 | 5 | 47849709.5 | 104965807.38 | 57116097.88 | 17108045 | 28228654.99 | 11120609.99 |  |  |  | 17108050 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 60 | 2021-07-30 | 2021-09-13 | 381426324.58 | [6 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works5 | Olympic Multi – Sports Hall5
Sports Hall - Civil Works | 2 | 6 | 51027855.5 | 63397792.5 | 12369937 | 414025 | 10835295 | 10421270 |  |  |  | 414030 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-11-23 | 432454180.08 | [6 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works6 | Olympic Multi – Sports Hall6
Sports Hall - Civil Works | 2 | 7 |  | 16168000 | 16168000 | 0 | 14222372.5 | 14222372.5 |  |  |  | 12888184 | 2021-11-30 | 2021-11-30 | 2021-12-14 | 60 | 2022-02-12 | [8 empty] | 0 | 0 | 0 | 12888184 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works7 | Olympic Multi – Sports Hall7
Sports Hall - Civil Works | 2 | 8 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Civil Works8 | Olympic Multi – Sports Hall8
Sports Hall - Finishes | 2 | 1 |  | 421069815.32 | 421069815.32 | 1388840 | 62661946.02 | 61273106.02 |  |  |  |  | 2021-05-31 | 2021-05-23 | 2021-05-23 | 60 | 2021-07-22 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes1 | Olympic Multi – Sports Hall1
Sports Hall - Finishes | 2 | 2 |  | 195957824.35 | 195957824.35 | 13091760 | 45292969.02 | 32201209.02 |  |  |  |  | 2021-08-31 | 2021-09-02 | 2021-09-11 | 60 | 2021-11-10 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes2 | Olympic Multi – Sports Hall2
Sports Hall - Finishes | 2 | 3 | 91998353.75 | 142963649.2 | 50965295.45 | 7109625 | 9602955 | 2493330 |  |  |  | 77278617 | 2021-10-31 | 2021-10-31 | 2021-10-11 | 60 | 2021-12-10 | 2021-11-17 | 178494684.93 | [6 empty] | 0 | 91998353.75 | 178494684.93 | 77278617 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes3 | Olympic Multi – Sports Hall3
Sports Hall - Finishes | 2 | 4 |  | 61004415.08 | 61004415.08 | 3699060 | 14275990 | 10576930 |  |  |  |  | 2022-07-31 | 2022-07-31 | 2022-08-09 | 60 | 2022-10-08 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes4 | Olympic Multi – Sports Hall4
Sports Hall - Finishes - ADD.01 | 2 | 1 | 9145259 | 421069815.32 | 411924556.32 | 5941290 | 62661946.02 | 56720656.02 |  |  |  | 5944418.35 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 60 | 2022-03-12 | 2022-02-22 | 9145259 | [6 empty] | 0 | 9145259 | 9145259 | 5944418.35 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes - ADD.011 | Olympic Multi – Sports Hall1
Sports Hall - Finishes - ADD.01 | 2 | 2 |  | 195957824.35 | 195957824.35 | 2631750 | 45292969.02 | 42661219.02 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes - ADD.012 | Olympic Multi – Sports Hall2
Sports Hall - Finishes - Landscape | 2 | 1 |  | 421069815.32 | 421069815.32 | 0.0003 | 62661946.02 | 62661946.0197 |  |  |  |  | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - Finishes - Landscape1 | Olympic Multi – Sports Hall1
Sports Hall - MEP | 2 | 1 |  | 421069815.32 | 421069815.32 | 67417715 | 62661946.02 | -4755768.98 |  |  |  |  | 2022-02-28 | 2022-02-24 | 2022-02-24 | 60 | 2022-04-25 | [8 empty] | 0 | 0 | 0 | 0 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - MEP1 | Olympic Multi – Sports Hall1
Sports Hall - MEP | 2 | 2 |  | 195957824.35 | 195957824.35 | 1103175 | 45292969.02 | 44189794.02 |  |  |  | 13327738 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [8 empty] | 0 | 0 | 0 | 13327738 | Olympic Multi – Sports Hall |  |  |  | Sports Hall - MEP2 | Olympic Multi – Sports Hall2
Suez Intake & P Stations-ABB apply | 1 | 1 | 779997.07 | 0 | -779997.07 | 509186.43 | 0 | -509186.43 |  |  |  | 524786.37 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 779997.07 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply1 | 01
Suez Intake & P Stations-ABB apply | 1 | 2 | 1514111.97 | 0 | -1514111.97 | 988420.71 | 0 | -988420.71 |  |  |  | 988420.71 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 2294109.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply2 | 02
Suez Intake & P Stations-ABB apply | 1 | 3 | 1605876.32 | 0 | -1605876.32 | 1048324.9964 | 0 | -1048324.9964 |  |  |  | 1048325 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 3899985.36 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply3 | 03
Suez Intake & P Stations-ABB apply | 1 | 6 | 6098633.64 | 0 | -6098633.64 | 0 | 0 | 0 |  |  |  | 573225.5 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 9998619 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB apply6 | 06
Suez Intake & P Stations-ABB supply | 1 | 1 | 5874834 | 0 | -5874834 | 5134498.57 | 0 | -5134498.57 |  |  |  | 5134498.57 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 5874834 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply1 | 01
Suez Intake & P Stations-ABB supply | 1 | 2 | 8551701.56 | 0 | -8551701.56 | 7437727.82 | 0 | -7437727.82 |  |  |  | 7437727.82 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 14426535.56 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply2 | 02
Suez Intake & P Stations-ABB supply | 1 | 3 | 1037578.56 | 0 | -1037578.56 | 814872.95 | 0 | -814872.95 |  |  |  | 814872.96 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 15464114.12 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply3 | 03
Suez Intake & P Stations-ABB supply | 1 | 4 |  | 0 | 0 | 3667977.98 | 0 | -3667977.98 |  |  |  |  | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply4 | 04
Suez Intake & P Stations-ABB supply | 1 | 8 | 24332063.94 | 0 | -24332063.94 | 1e-05 | 0 | -1e-05 |  |  |  | 817934.28 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 40613282 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-ABB supply8 | 08
Suez Intake & P Stations-SSC apply | 1 | 1 | 1124419.48 | 0 | -1124419.48 | 1102291.62 | 0 | -1102291.62 |  |  |  | 1102291.62 | 2023-01-31 | 2023-01-16 | 2023-01-15 | 42 | 2023-02-26 | 2023-01-16 | 1124419.48 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply1 | 01
Suez Intake & P Stations-SSC apply | 1 | 2 | 3081346.71 | 0 | -3081346.71 | 3020707.78 | 0 | -3020707.78 |  |  |  | 3020707.78 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 4205766.19 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply2 | 02
Suez Intake & P Stations-SSC apply | 1 | 3 | 788338.19 | 0 | -788338.19 | 772824.1924 | 0 | -772824.1924 |  |  |  | 772824.19 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 4994104.38 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply3 | 03
Suez Intake & P Stations-SSC apply | 1 | 7 | 12349144.72 | 0 | -12349144.72 | 0 | 0 | 0 |  |  |  | 6963227.52 | 2024-02-29 | 2024-02-26 | 2024-02-26 | 42 | 2024-04-08 | 2024-02-27 | 17343249.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply7 | 07
Suez Intake & P Stations-SSC apply | 1 | 8 | 1924769.3 | 0 | -1924769.3 | 1886891.07 | 0 | -1886891.07 |  |  |  | 1886891.07 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 19268018.4 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC apply8 | 08
Suez Intake & P Stations-SSC supply | 1 | 1 | 10223133.6 | 0 | -10223133.6 | 8726326.42 | 0 | -8726326.42 |  |  |  | 8726335.42 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 10223133.6 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply1 | 01
Suez Intake & P Stations-SSC supply | 1 | 2 | 3765789.87 | 0 | -3765789.87 | 3190893.09 | 0 | -3190893.09 |  |  |  | 3190884.06 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 13988923.47 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply2 | 02
Suez Intake & P Stations-SSC supply | 1 | 3 | 374122.68 | 0 | -374122.68 | 283552.06 | 0 | -283552.06 |  |  |  | 283552.06 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 14363046.15 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply3 | 03
Suez Intake & P Stations-SSC supply | 1 | 4 |  | 0 | 0 | 1e-05 | 0 | -1e-05 |  |  |  |  | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply4 | 04
Suez Intake & P Stations-SSC supply | 1 | 8 | 9321912.4 | 0 | -9321912.4 | 0 | 0 | 0 |  |  |  | 1886800.52 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 24074956.74 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Suez Intake & P Stations-SSC supply8 | 08
SVC | 1 | 1 | 3212437.04 | 0 | -3212437.04 | 3375312.6616 | 0 | -3375312.6616 | 1158731.1 |  |  | 2377203.41 | 2024-02-29 | 2024-02-17 | 2024-04-01 | 42 | 2024-05-13 | 2024-04-01 | 3212437.04 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SVC1 | 01
SVC | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2024-05-31 | 2024-05-25 | 2024-06-12 | 42 | 2024-07-24 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | SVC2 | 02
Uptown PK #53 | 1 | 25 |  | 0 | 0 | 12009168.61 | 0 | -12009168.61 |  |  |  | 12105864.365 | 2017-09-30 | 2017-10-10 | 2017-11-11 | 40 | 2017-12-21 | 2017-11-28 | 210168675.9558 | 8286463.8075 | [5 empty] | 1299409.2216 | 0 | 0 | 12023138.6423 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5325 | EMAAR-PKG#53-UPTOWN25
Uptown PK #53 | 1 | 26 | 18341001.0169 | 0 | -18341001.0169 | 13124888.11 | 0 | -13124888.11 |  |  |  | 13230735.7159 | 2017-10-31 | 2017-11-10 | 2017-11-28 | 40 | 2018-01-07 | 2017-12-21 | 228815469.9927 | 6928080.7619 | [5 empty] | 1215618.2216 | 18228071.6884 | 228353712.8741 | 12833527.9648 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5326 | EMAAR-PKG#53-UPTOWN26
Uptown PK #53 | 1 | 27 | 11525442.3347 | 0 | -11525442.3347 | 9593936.7945 | 0 | -9593936.7945 |  |  |  | 9723398.7945 | 2017-11-30 | 2017-12-10 | 2017-12-26 | 40 | 2018-02-04 | 2018-01-08 | 240340912.3274 | 8309746.418 | [5 empty] | 1307409.2216 | 11525442.3347 | 240340912.3274 | 9723398.7945 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5327 | EMAAR-PKG#53-UPTOWN27
Uptown PK #53 | 1 | 28 | 13381649.8939 | 0 | -13381649.8939 | 13320601.43 | 0 | -13320601.43 |  |  |  | 13380241.7057 | 2017-12-31 | 2018-01-10 | 2018-01-16 | 40 | 2018-02-25 | 2018-02-15 | 253722562.2213 | 4669320.168 | [5 empty] | 1464327.5816 | 13381649.8939 | 253722562.2213 | 7567160.0657 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5328 | EMAAR-PKG#53-UPTOWN28
Uptown PK #53 | 1 | 29 | 17500846.4172 | 0 | -17500846.4172 | 10942287.56 | 0 | -10942287.56 |  |  |  | 11043112.6231 | 2018-01-31 | 2018-02-10 | 2018-02-15 | 40 | 2018-03-27 | 2018-03-06 | 271223408.6385 | 3636537.0679 | [5 empty] | 1444327.5816 | 17114848.1247 | 270837410.346 | 10749580.8339 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5329 | EMAAR-PKG#53-UPTOWN29
Uptown PK #53 | 1 | 30 | 15321007.8734 | 0 | -15321007.8734 | 11348802.26 | 0 | -11348802.26 |  |  |  | 11437376.0467 | 2018-02-28 | 2018-03-10 | 2018-03-17 | 40 | 2018-04-26 | 2018-04-04 | 286544416.4997 | 2782555.8001 | [5 empty] | 3125936.127 | 15380090.6234 | 286603499.2497 | 9526356.8077 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5330 | EMAAR-PKG#53-UPTOWN30
Uptown PK #53 | 1 | 31 | 11220346.2103 | 17457747.57 | 6237401.3597 | 7033824.83 | 11753104.21 | 4719279.38 |  |  |  | 7091661.81 | 2018-03-31 | 2018-04-10 | 2018-04-18 | 40 | 2018-05-28 | 2018-05-20 | 297764762.71 | 1008898.49 | [5 empty] | 4001808.9907 | 10847277.7132 | 297391694.2129 | 6774937.5373 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5331 | EMAAR-PKG#53-UPTOWN31
Uptown PK #53 | 1 | 32 | 4916024.5037 | 4777477.68 | -138546.8237 | 2358051.13 | 2883132.62 | 525081.49 |  |  |  | 2387351.5744 | 2018-04-30 | 2018-05-10 | 2018-05-17 | 40 | 2018-06-26 | 2018-05-29 | 302680787.2137 | 878601.9171 | [5 empty] | 4488322.2907 | 4916024.5037 | 302680787.2137 | 2387351.5744 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5332 | EMAAR-PKG#53-UPTOWN32
Uptown PK #53 | 1 | 33 | 3312628.1623 | 3219269.97 | -93358.1923 | 2690853.59 | 2214577.5 | -476276.09 |  |  |  | 2709512.38 | 2018-05-31 | 2018-06-15 | 2018-06-24 | 40 | 2018-08-03 | 2018-07-10 | 305993415.376 | 613573.28 | [5 empty] | 4562822.2907 | 3312628.1576 | 305993415.3712 | 3964599.8564 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5333 | EMAAR-PKG#53-UPTOWN33
Uptown PK #53 | 1 | 34 | 73574.6923 | 62924.2 | -10650.4923 | 1431626.0807 | 1344501.4 | -87124.6807 |  |  |  | 1431626.0807 | 2018-06-30 | 2018-07-10 | 2018-07-17 | 40 | 2018-08-26 | 2018-07-26 | 306066990.0683 | 613573.2833 | [5 empty] | 4285977.9307 | 73574.6923 | 306066990.0683 | 1431626.0807 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5334 | EMAAR-PKG#53-UPTOWN34
Uptown PK #53 | 1 | 35 | 3416261.3696 | 3328558.25 | -87703.1196 | 2466454.76 | 2331143.99 | -135310.77 |  |  |  | 2488623.0127 | 2018-07-31 | 2018-08-10 | 2018-08-16 | 40 | 2018-09-25 | 2018-09-12 | 309483251.4379 | 385285.6486 | [5 empty] | 4958858.9291 | 3416261.3696 | 309483251.4379 | 2488623.0127 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5335 | EMAAR-PKG#53-UPTOWN35
Uptown PK #53 | 1 | 36 | 2041348.5871 | 1983817.89 | -57530.6971 | 2490213.39 | 3652834.8365 | 1162621.4465 |  |  |  | 2502552.38 | 2018-08-31 | 2018-09-10 | 2018-09-19 | 40 | 2018-10-29 | 2018-10-20 | 311524600.025 | 359304.445 | [5 empty] | 4948858.9291 | 2041348.5942 | 311524600.0321 | 4689979.7631 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5336 | EMAAR-PKG#53-UPTOWN36
Uptown PK #53 | 1 | 37 | 1273110.6827 | 0 | -1273110.6827 | 1746850.68 | 0 | -1746850.68 |  |  |  | 1753673.2424 | 2018-09-30 | 2018-10-10 | 2018-10-22 | 40 | 2018-12-01 | 2018-12-16 | 312797710.7077 | 200543.77 | [5 empty] | 5687765.7473 | 1273110.6827 | 312797710.7077 | 1753673.2424 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5337 | EMAAR-PKG#53-UPTOWN37
Uptown PK #53 | 1 | 38 | 747405.6143 | 944067.24 | 196661.6257 | 1902092.11 | 3125949.802 | 1223857.692 |  |  |  | 1048789.58 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 40 | 2019-02-25 | 2019-02-18 | 313545116.322 | 200543.77 | [5 empty] | 6192106.3873 | 747405.6143 | 313545116.322 | 1048789.58 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5338 | EMAAR-PKG#53-UPTOWN38
Uptown PK #53 | 1 | 39 | 32300.9957 | 0 | -32300.9957 | 943725.79 | 0 | -943725.79 |  |  |  | 929614.0301 | 2019-03-31 | 2019-04-10 | 2019-04-11 | 40 | 2019-05-21 | 2019-04-21 | 313577417.3177 | 200543.77 | [5 empty] | 5191842.6873 | 32300.9957 | 313577417.3177 | 929614.0301 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5339 | EMAAR-PKG#53-UPTOWN39
Uptown PK #53 | 1 | 40 | 52815.0023 | 51326.53 | -1488.4723 | 1435222.17 | 11242137.74 | 9806915.57 |  |  |  | 1435222.17 | 2019-05-31 | 2019-06-15 | 2019-06-18 | 40 | 2019-07-28 | 2019-07-16 | 313630232.32 | 200543.77 | [5 empty] | 0 | 52815.0023 | 313630232.32 | 1435222.17 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5340 | EMAAR-PKG#53-UPTOWN40
Uptown PK #53 | 1 | 41 | 0 | 0 | 0 | 4202366.45 | 0 | -4202366.45 |  |  |  | 4202366.45 | 2019-08-31 | 2019-08-15 | 2019-08-20 | 40 | 2019-09-29 | 2019-08-20 | 313630232.32 | 200543.77 | [5 empty] | 0 | 0 | 0 | 4202366.45 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5341 | EMAAR-PKG#53-UPTOWN41
Uptown PK #53 | 1 | 42 | 4356349.94 | 0 | -4356349.94 | 1380970.95 | 0 | -1380970.95 |  |  |  | 1380970.95 | 2019-12-31 | 2019-12-15 | 2019-12-19 | 40 | 2020-01-28 | 2020-01-26 | 317986582.26 | 200543.77 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5342 | EMAAR-PKG#53-UPTOWN42
Uptown PK #53 | 1 | 43 | 3411373.56 | 0 | -3411373.56 | 4834138.97 | 0 | -4834138.97 |  |  |  | 3747539.31 | 2020-02-29 | 2020-02-25 | 2020-03-10 | 40 | 2020-04-19 | 2020-04-15 | 321397955.82 | 200543.77 | [5 empty] | 0 | 0 | 0 | 0 | EMAAR-PKG#53-UPTOWN |  |  |  | Uptown PK #5343 | EMAAR-PKG#53-UPTOWN43
Uptown PK #62 | 1 | 7 |  | 0 | 0 | 1684908.09 | 0 | -1684908.09 |  |  |  | 1684908.08 | 2017-09-30 | 2017-09-30 | 2017-10-04 | 40 | 2017-11-13 | 2017-10-18 | 18419996.59 | 0 | [5 empty] | 136775.69 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #627 | EMAAR-PKG#62-UPTOWN7
Uptown PK #62 | 1 | 8 | 4024169.64 | 0 | -4024169.64 | 2970870.89 | 0 | -2970870.89 |  |  |  | 2970870.89 | 2017-10-31 | 2017-10-31 | 2017-11-02 | 40 | 2017-12-12 | 2017-11-14 | 22444166.23 | 1403336.04 | [5 empty] | 169833.53 | 4024169.64 | 22444166.23 | 2970870.89 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #628 | EMAAR-PKG#62-UPTOWN8
Uptown PK #62 | 1 | 9 | 3353637.028 | 0 | -3353637.028 | 2124952.16 | 0 | -2124952.16 |  |  |  | 2124952.16 | 2017-11-30 | 2017-11-30 | 2017-12-04 | 40 | 2018-01-13 | 2017-12-21 | 25797803.258 | 1883218.402 | [5 empty] | 193475.95 | 3353637.028 | 25797803.258 | 2124952.16 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #629 | EMAAR-PKG#62-UPTOWN9
Uptown PK #62 | 1 | 10 | 3315629.905 | 0 | -3315629.905 | 2207449.91 | 0 | -2207449.91 |  |  |  | 2207449.91 | 2017-12-31 | 2017-12-27 | 2017-12-30 | 40 | 2018-02-08 | 2018-01-18 | 29113433.163 | 2376274.377 | [5 empty] | 216794.47 | 3315629.905 | 29113433.163 | 2207449.91 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6210 | EMAAR-PKG#62-UPTOWN10
Uptown PK #62 | 1 | 11 | 3273536.577 | 0 | -3273536.577 | 1524280.94 | 0 | -1524280.94 |  |  |  | 1524280.94 | 2018-01-31 | 2018-01-31 | 2018-02-03 | 40 | 2018-03-15 | 2018-02-15 | 32386969.74 | 1872928.9681 | [5 empty] | 233754.86 | 3260036.5785 | 32373469.7415 | 1516852.746 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6211 | EMAAR-PKG#62-UPTOWN11
Uptown PK #62 | 1 | 12 | 2806216.291 | 0 | -2806216.291 | 1565019.14 | 0 | -1565019.14 |  |  |  | 1565019.15 | 2018-02-28 | 2018-02-28 | 2018-03-01 | 40 | 2018-04-10 | 2018-03-18 | 35193186.031 | 1983635.499 | [5 empty] | 291613.6 | 2806216.291 | 35193186.031 | 1565019.15 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6212 | EMAAR-PKG#62-UPTOWN12
Uptown PK #62 | 1 | 13 | 6967775.654 | 0 | -6967775.654 | 2219134.03 | 0 | -2219134.03 |  |  |  | 2219134.03 | 2018-03-31 | 2018-03-31 | 2018-04-02 | 40 | 2018-05-12 | 2018-05-08 | 42160961.685 | 301154.885 | [5 empty] | 1040317.09 | 6967775.65 | 42160961.681 | 3417923.56 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6213 | EMAAR-PKG#62-UPTOWN13
Uptown PK #62 | 1 | 14 | 3891325.445 | 3683223.04 | -208102.405 | 854854.29 | 815558.87 | -39295.42 |  |  |  | 854854.3 | 2018-04-30 | 2018-05-08 | 2018-05-08 | 40 | 2018-06-17 | 2018-06-26 | 46052287.13 | 0 | [5 empty] | 2182913.11 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6214 | EMAAR-PKG#62-UPTOWN14
Uptown PK #62 | 1 | 15 | 1266868.51 | 1329599.07 | 62730.56 | 2299870.99 | 5710409.5735 | 3410538.5835 |  |  |  | 2299870.97 | 2018-07-31 | 2018-07-24 | 2018-08-14 | 40 | 2018-09-23 | 2018-09-06 | 47319155.64 | 0 | [5 empty] | 2396855.11 | 1266868.51 | 47319155.64 | 2299870.97 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6215 | EMAAR-PKG#62-UPTOWN15
Uptown PK #62 | 1 | 16 | -245868.22 | 0 | 245868.22 | 931895.88 | 0 | -931895.88 |  |  |  | 931895.88 | 2018-09-30 | 2018-10-03 | 2018-10-04 | 40 | 2018-11-13 | 2018-11-25 | 47073287.42 | [6 empty] | 1241550.872 | -245868.22 | 47073287.42 | 931895.88 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6216 | EMAAR-PKG#62-UPTOWN16
Uptown PK #62 | 1 | 17 | 0 | 0 | 0 | 419078.79 | 0 | -419078.79 |  |  |  | 419078.79 | 2019-03-31 | 2019-03-25 | 2019-03-24 | 40 | 2019-05-03 | 2019-04-11 | 47073287.42 | [6 empty] | 928608.274 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6217 | EMAAR-PKG#62-UPTOWN17
Uptown PK #62 | 1 | 18 | 0 | 0 | 0 | 864260.36 | 0 | -864260.36 |  |  |  | 864260.36 | 2019-09-30 | 2019-10-09 | 2019-10-09 | 40 | 2019-11-18 | 2019-11-03 | 47073287.42 | [6 empty] | 987399.24 | 0 | 0 | 0 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6218 | EMAAR-PKG#62-UPTOWN18
Uptown PK #62 | 1 | 19 | 22437 | 1831902.3 | 1809465.3 | 1416810.93 | 1275390.455 | -141420.475 |  |  |  | 1195853.88 | 2019-12-31 | 2019-12-18 | 2019-12-19 | 40 | 2020-01-28 | 2020-07-19 | 47095724.42 | [6 empty] | 990172.52 | 22437 | 47095724.42 | 1195853.88 | EMAAR-PKG#62-UPTOWN |  |  |  | Uptown PK #6219 | EMAAR-PKG#62-UPTOWN19
Wady Halfa | 1 | 1 | 3078932.9 | 64486200.86 | 61407267.96 | 22733360.9 | 22733362.34 | 1.44 | 19000000 |  |  | 33029517.9 | 2022-11-30 | 2022-11-30 | 2022-12-11 | 30 | 2023-01-10 | 2022-12-18 | 3078932.9 | 33200100 | [5 empty] | 0 | 3078932.9 | 3078932.9 | 33029517.9 | Wadi Halfa Port |  |  |  | Wady Halfa1 | Wadi Halfa Port1
Wady Halfa | 1 | 2 | 23601516.1 | 11905090.1 | -11696426 | 8196261.85 | 8196261.45 | -0.4 | 11000000 |  |  | 11905091.98 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 30 | 2023-03-10 | 2023-02-14 | 26680449 | 18254159 | [5 empty] | 0 | 23601516.1 | 26680449 | 11905091.98 | Wadi Halfa Port |  |  |  | Wady Halfa2 | Wadi Halfa Port2
Wady Halfa | 1 | 3 | 17962793.18 | 4077802.86 | -13884990.32 | 2807166.9 | 2807168.5814 | 1.6814 |  |  |  | 14516628.581 | 2023-02-28 | 2023-02-28 | 2023-03-16 | 30 | 2023-04-15 | 2023-03-16 | 44643242.18 | 4370481.56 | [5 empty] | 0 | 17962793.18 | 44643242.18 | 14516628.581 | Wadi Halfa Port |  |  |  | Wady Halfa3 | Wadi Halfa Port3
Wady Halfa | 1 | 4 | 8749053.22 | 4379885.32 | -4369167.9 | 3015154.3 | 3015154.5668 | 0.2668 |  |  |  | 3679103.55 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 30 | 2023-05-10 | 2023-05-08 | 53392295.4 | [6 empty] | 0 | 0 | 0 | 0 | Wadi Halfa Port |  |  |  | Wady Halfa4 | Wadi Halfa Port4
Wady Halfa | 1 | 5 |  | 10144199.04 | 10144199.04 | 2984537.1 | 2984537.1 | 0 |  |  |  |  | 2024-03-31 | 2024-03-15 | 2024-03-15 | 30 | 2024-04-14 | [8 empty] | 0 | 0 | 0 | 0 | Wadi Halfa Port |  |  |  | Wady Halfa5 | Wadi Halfa Port5
Western Fence | 1 | 1 | 762742.21 | 0 | -762742.21 | 418218.39 | 0 | -418218.39 |  |  |  | 792870.53 | 2023-10-31 | 2023-10-31 | 2023-10-30 | 42 | 2023-12-11 | 2023-11-02 | 762742.21 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Western Fence1 | 01
Zayed Park | 0 | 1 | 191006.802 | 0 | -191006.802 | 505797 | 0 | -505797 |  |  |  | 505797.14 | 2019-10-31 | 2019-10-28 | 2019-10-28 | 30 | 2019-11-27 | 2019-11-07 | 191006.802 | 410791.498 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Zayed Park1 | 01
Zayed Park | 0 | 2 | 842290.974 | 0 | -842290.974 | 264423.21 | 0 | -264423.21 |  |  |  | 352690.39 | 2019-12-31 | 2019-12-31 | 2020-01-11 | 30 | 2020-02-10 | 2020-09-21 | 1033297.776 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Zayed Park2 | 02
|  |  | 19805227693.4556 | 25899319453.4928 | 6094091760.0372 | 18501728387.8624 | 17889422003.4697 | -612306384.3927 | 1901673988.52 | 890783556.123 | 40056730.98 | 15454594032.6016 | [7 empty] | 11199832140.5956 | 28218786789.695 | 107915790.6 | 12523278641.5813 | 2970327920.4235 | 2614672939.897 | 2165045374.0028 | [7 empty] | 0
Note on N876: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Claims
Note on N877: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Claims
Note on N1150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Social Insurance
Note on N1151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Social Insurance
Note on N1152: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Social Insurance

## collection only
Project | Invoice No. | invoice round down | concact | Collection amount
6TH October tunnel | 1 | 1 | 6TH October tunnel1 | 1520548
6TH October tunnel | 2 | 2 | 6TH October tunnel2 | 3208372.9
6TH October tunnel | 2.1 | 2 | 6TH October tunnel2 | 300000
6TH October tunnel | 3 | 3 | 6TH October tunnel3 | 0.001
6TH October tunnel | 4 | 4 | 6TH October tunnel4 | 5155347
6TH October tunnel | 5 | 5 | 6TH October tunnel5 | 2856009
6TH October tunnel | 6 | 6 | 6TH October tunnel6 | 1337162.6
Abo Ghaleb Bridge | 1 | 1 | Abo Ghaleb Bridge1 | 175270.85
Abo Ghaleb Bridge | 2 | 2 | Abo Ghaleb Bridge2 | 2494611.027
Abo Ghaleb Bridge | 3 | 3 | Abo Ghaleb Bridge3 | 2045810.923
Abo Ghaleb Bridge | 4 | 4 | Abo Ghaleb Bridge4 | 12711007.22
Abo Ghaleb Bridge | 5 | 5 | Abo Ghaleb Bridge5 | 1645829.28
Abo Ghaleb Bridge | 6 | 6 | Abo Ghaleb Bridge6 | 0.0001
AEON | 1 | 1 | AEON1 | 1264914.16
AEON | 2 | 2 | AEON2 | 1513146.56
AEON | 3 | 3 | AEON3 | 780253.07
AEON | 4 | 4 | AEON4 | 484406.35
Al Jazi | 1 | 1 | Al Jazi1 | 2199495
Al Jazi | 2 | 2 | Al Jazi2 | 2330066
Al Jazi | 3 | 3 | Al Jazi3 | 3090062.9
Al Jazi | 4 | 4 | Al Jazi4 | 3867947.36
Al Jazi | 5 | 5 | Al Jazi5 | 4039155
Al Jazi | 6 | 6 | Al Jazi6 | 2383592
Al Jazi | 7 | 7 | Al Jazi7 | 4138160
Al Jazi | 8 | 8 | Al Jazi8 | 6905844.19
Al Jazi | 9 | 9 | Al Jazi9 | 1762571
Al Jazi | 10 | 10 | Al Jazi10 | 2302251
Al Jazi | 11 | 11 | Al Jazi11 | 3838772.36
Al Jazi | 12 | 12 | Al Jazi12 | 922154
Al Jazi | 13 | 13 | Al Jazi13 | 2994292.79
Al Jazi | 14 | 14 | Al Jazi14 | 1629015.64
Al Jazi | 15 | 15 | Al Jazi15 | 2107757
Al Jazi | 16 | 16 | Al Jazi16 | 120989.08
Al Jazi | 17 | 17 | Al Jazi17 | 2935343.72
Al Jazi | 18 | 18 | Al Jazi18 | 2748544.1
Al Jazi | 19 | 19 | Al Jazi19 | 2000000
Al Jazi | 19.1 | 19 | Al Jazi19 | 1100493.11
Al Jazi | 20 | 20 | Al Jazi20 | 371543.5
Al Jazi | 21 | 21 | Al Jazi21 | 0.0001
Al Jazi | 22 | 22 | Al Jazi22 | 2500000
Al Jazi | 22.1 | 22 | Al Jazi22 | 2000000
Al Jazi | 22.2 | 22 | Al Jazi22 | 848568.49
Al Jazi | 22.3 | 22 | Al Jazi22 | 1000000
Al Jazi | 22.4 | 22 | Al Jazi22 | 1000000
Al Jazi | 22.5 | 22 | Al Jazi22 | 1242872
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 90608.89
Al Jazi - Center Zone | 2 | 2 | Al Jazi - Center Zone2 | 1686320.29
Al Jazi - Center Zone | 3 | 3 | Al Jazi - Center Zone3 | 360179.68
Al Jazi - Center Zone | 4 | 4 | Al Jazi - Center Zone4 | 370581.69
Al Jazi - Center Zone | 5 | 5 | Al Jazi - Center Zone5 | 858100
Al Jazi - Center Zone | 6 | 6 | Al Jazi - Center Zone6 | -0.01
Al Jazi - Center Zone | 7 | 7 | Al Jazi - Center Zone7 | 151431.32
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 14666580.12
Al Jazi - Social Insurance | 1 | 1 | Al Jazi - Social Insurance1 | 266994
Al Jazi | 1 | 1 | Al Jazi1 | 53125000
Alfa Lab | 1 | 1 | Alfa Lab1 | 1459340
Allegria-New Modifications | 1 | 1 | Allegria-New Modifications1 | 659568.2
Astoria - Sharm | 2 | 2 | Astoria - Sharm2 | 837813.8
Astoria - Sharm | 3 | 3 | Astoria - Sharm3 | 269728
Astoria - Sharm | 4 | 4 | Astoria - Sharm4 | 1641108
Astoria - Sharm | 5 | 5 | Astoria - Sharm5 | 709627
Astoria - Sharm | 6 | 6 | Astoria - Sharm6 | 244817
Astoria - Sharm | 7 | 7 | Astoria - Sharm7 | 654151
Astoria - Sharm | 8 | 8 | Astoria - Sharm8 | 1160836
Astoria - Sharm | 1 | 1 | Astoria - Sharm1 | 1365525
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 4511122
Astoria Hotel | 2 | 2 | Astoria Hotel2 | 2448868
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 5421697
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 4634265
Astoria Hotel | 5 | 5 | Astoria Hotel5 | 5818860
Astoria Hotel | 6 | 6 | Astoria Hotel6 | 3446328.13
Astoria Hotel | 6.1 | 6 | Astoria Hotel6 | 5000000
Astoria Hotel | 7 | 7 | Astoria Hotel7 | 8710615
Astoria Hotel | 8 | 8 | Astoria Hotel8 | 2805916
Astoria Hotel | 9 | 9 | Astoria Hotel9 | 2000000
Astoria Hotel | 9.1 | 9 | Astoria Hotel9 | 4286403
Astoria Hotel | 10 | 10 | Astoria Hotel10 | 4982321
Astoria Hotel | 11 | 11 | Astoria Hotel11 | 10757000
Astoria Hotel | 12 | 12 | Astoria Hotel12 | 2603000
Astoria Hotel | 13 | 13 | Astoria Hotel13 | 5389256
Astoria Hotel | 14 | 14 | Astoria Hotel14 | 6216098
Astoria Hotel | 15 | 15 | Astoria Hotel15 | 4185662
Astoria Hotel | 16 | 16 | Astoria Hotel16 | 3225683
Astoria Hotel | 17 | 17 | Astoria Hotel17 | 2804159
Astoria Hotel | 18 | 18 | Astoria Hotel18 | 4819756
Astoria Hotel | 19 | 19 | Astoria Hotel19 | 1511334.24
Astoria Hotel | 20 | 20 | Astoria Hotel20 | 0.0001
Astoria Hotel | 21 | 21 | Astoria Hotel21 | 0.0001
Astoria Hotel | 22 | 22 | Astoria Hotel22 | 1e-05
Astoria Hotel | 23 | 23 | Astoria Hotel23 | 17286732.59
Astoria Hotel | 24 | 24 | Astoria Hotel24 | 10400000
Astoria Hotel | 25 | 25 | Astoria Hotel25 | 3117985
Astoria Hotel-DP | 1 | 1 | Astoria Hotel-DP1 | 46039744.5
Astoria Hotel-DP | 2 | 2 | Astoria Hotel-DP2 | 18415897.8
Astoria Hotel-DP | 3 | 3 | Astoria Hotel-DP3 | 9207948.9
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 9207948.9
Astoria Hotel - Final Retention | 1 | 1 | Astoria Hotel - Final Retention1 | 5000000
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 2000000
Astoria Hotel - Social Insurrance | 1 | 1 | Astoria Hotel - Social Insurrance1 | 959926
Astoria Hotel - Spare Parts V.O 137 | 1 | 1 | Astoria Hotel - Spare Parts V.O 1371 | 1929946
Astoria Hotel IPCs 15-20 | 1 | 1 | Astoria Hotel IPCs 15-201 | 1409611.34
Baraka Land Fence | 1 | 1 | Baraka Land Fence1 | 2467026
Baraka Land Fence | 2 | 2 | Baraka Land Fence2 | 8497787.46
Baraka Land Fence | 3 | 3 | Baraka Land Fence3 | 15418299.78
Baraka Land Fence | 4 | 4 | Baraka Land Fence4 | 6072172.61
Benban - Aswan | 2 | 2 | Benban - Aswan2 | 21842173.61
Benban - Aswan | 3 | 3 | Benban - Aswan3 | 10577813.02
Benban - Aswan | 4 | 4 | Benban - Aswan4 | 15006351.74
Benban - Aswan | 5 | 5 | Benban - Aswan5 | 37440497.15
Benban - Aswan | 6 | 6 | Benban - Aswan6 | 23886898.7775
Benban - Aswan | 7 | 7 | Benban - Aswan7 | 25237199.4694
Benban - Aswan | 8 | 8 | Benban - Aswan8 | 28236383.5819
Benban - Aswan | 9 | 9 | Benban - Aswan9 | 33103432.2978
Benban - Aswan | 10 | 10 | Benban - Aswan10 | 12102732.036
Benban - Aswan | 11 | 11 | Benban - Aswan11 | 2222964.1737
Benban - Aswan | 12 | 12 | Benban - Aswan12 | 16625097.353
Benban - Aswan | 13 | 13 | Benban - Aswan13 | 36700.14
Benban - Aswan | 14 | 14 | Benban - Aswan14 | 1174778.08
Benban - Aswan | 1 | 1 | Benban - Aswan1 | 24677038.56
Cement Plant | 14 | 14 | Cement Plant14 | 7309725
Cement Plant | 15 | 15 | Cement Plant15 | 6696657.1239
Cement Plant | 16 | 16 | Cement Plant16 | 6990595.3607
Cement Plant | 17 | 17 | Cement Plant17 | 7424114.8339
Cement Plant | 18 | 18 | Cement Plant18 | 6925479.9129
Cement Plant | 19 | 19 | Cement Plant19 | 12791497.7957
Cement Plant | 20 | 20 | Cement Plant20 | 10152661.36
Cement Plant -Last Claim | 3 | 3 | Cement Plant -Last Claim3 | 5224000
CFC | 1 | 1 | CFC1 | 6200445.37
CFC | 2 | 2 | CFC2 | 17105598.33
CFC | 3 | 3 | CFC3 | 12263695.26
CFC | 4 | 4 | CFC4 | 32660833.58
CFC | 5 | 5 | CFC5 | 24749111.95
CFC | 6 | 6 | CFC6 | 31500278.62
CFC | 7 | 7 | CFC7 | 19510038
CFC | 8 | 8 | CFC8 | 21459124.497
CFC | 9 | 9 | CFC9 | 24499895.82
CFC | 10 | 10 | CFC10 | 39448595.84
CFC | 11 | 11 | CFC11 | 18030565.73
CFC | 12 | 12 | CFC12 | 29691194.9757
CFC | 13 | 13 | CFC13 | 23213756.67
CFC | 14 | 14 | CFC14 | 19708943.72
CFC | 15 | 15 | CFC15 | 40379659.8985
CFC | 16 | 16 | CFC16 | 22871121.16
CFC | 17 | 17 | CFC17 | 15047803.35
CFC | 18 | 18 | CFC18 | 12196441.12
CFC | 19 | 19 | CFC19 | 14008565.7
CFC | 20 | 20 | CFC20 | 23721354.77
CFC | 21 | 21 | CFC21 | 17156725.12
CFC | 22 | 22 | CFC22 | 13410069.82
CFC | 23 | 23 | CFC23 | 15440459.23
CFC | 24 | 24 | CFC24 | 7464480.35
CFC | 25 | 25 | CFC25 | 9682524.46
CFC | 26 | 26 | CFC26 | 2397254.3033
CFC | 27 | 27 | CFC27 | 10793868.64
CFC | 28 | 28 | CFC28 | 10367935.31
CFC | 29 | 29 | CFC29 | 15034318.2703
CFC - Final Retention | 1 | 1 | CFC - Final Retention1 | 12637074.78
CFC-DP | 1 | 1 | CFC-DP1 | 62134944.55
Comoros | 1 | 1 | Comoros1 | 3891360.8
Comoros - Off Shore | 1 | 1 | Comoros - Off Shore1 | 2555388
Comoros - Off Shore | 2 | 2 | Comoros - Off Shore2 | 910154
Comoros - On Shore | 1 | 1 | Comoros - On Shore1 | 830840.75
Comoros - On Shore | 2 | 2 | Comoros - On Shore2 | 405450.99
Comoros - On Shore | 1 | 1 | Comoros - On Shore1 | 263708.26
Creeks - URBN K | 1 | 1 | Creeks - URBN K1 | 10729515
Creeks - URBN K | 2 | 2 | Creeks - URBN K2 | 3863139
Creeks - URBN K | 3 | 3 | Creeks - URBN K3 | 21808950
Creeks - URBN K | 4 | 4 | Creeks - URBN K4 | 8830426
Creeks - URBN K | 5 | 5 | Creeks - URBN K5 | 13533059
Creeks - URBN K | 6 | 6 | Creeks - URBN K6 | 19608847
Creeks - URBN K | 7 | 7 | Creeks - URBN K7 | 16761479
Creeks - URBN K | 8 | 8 | Creeks - URBN K8 | 16707965
Creeks - URBN K | 9 | 9 | Creeks - URBN K9 | 16997068
Creeks - URBN K | 10 | 10 | Creeks - URBN K10 | 19246723
Creeks - URBN K | 11 | 11 | Creeks - URBN K11 | 11569432
Creeks - URBN K | 12 | 12 | Creeks - URBN K12 | 8618325
Creeks - URBN K | 13 | 13 | Creeks - URBN K13 | 23221916
Creeks - URBN K | 14 | 14 | Creeks - URBN K14 | 6223873.19
Creeks - URBN K | 15 | 15 | Creeks - URBN K15 | 10206848
Creeks - URBN K | 16 | 16 | Creeks - URBN K16 | 6345314
Creeks - URBN K | 17 | 17 | Creeks - URBN K17 | 8554807
Creeks - URBN K | 18 | 18 | Creeks - URBN K18 | 9363450
Damietta Port - Civil | 2 | 2 | Damietta Port - Civil2 | 1520770.91
Damietta Port - Civil | 3 | 3 | Damietta Port - Civil3 | 1496696.18
Damietta Port - Civil | 1 | 1 | Damietta Port - Civil1 | 4058690.9
Damietta Port - Infra | 1 | 1 | Damietta Port - Infra1 | 6541975.22
DP World Sokhna | 1 | 1 | DP World Sokhna1 | 15998139
DP World Sokhna | 2 | 2 | DP World Sokhna2 | 18062199.23
DP World Sokhna | 3 | 3 | DP World Sokhna3 | 15357944.03
DP World Sokhna | 4 | 4 | DP World Sokhna4 | 27940477.28
DP World Sokhna | 5 | 5 | DP World Sokhna5 | 13161622.85
DP World Sokhna | 6 | 6 | DP World Sokhna6 | 24492163.72
DP World Sokhna | 7 | 7 | DP World Sokhna7 | 29974844.16
DP World Sokhna | 8 | 8 | DP World Sokhna8 | 29128813.98
DP World Sokhna | 9 | 9 | DP World Sokhna9 | 40031882.73
DP World Sokhna | 10 | 10 | DP World Sokhna10 | 66994289.3
DP World Sokhna | 11 | 11 | DP World Sokhna11 | 76494532.33
DP World Sokhna | 12 | 12 | DP World Sokhna12 | 59999695.78
DP World Sokhna | 12.1 | 12 | DP World Sokhna12 | 49675726.5
DP World Sokhna | 13 | 13 | DP World Sokhna13 | 46089743
DP World Sokhna | 13.1 | 13 | DP World Sokhna13 | 46089743
DP World Sokhna | 14 | 14 | DP World Sokhna14 | 52189292.94
DP World Sokhna | 14.1 | 14 | DP World Sokhna14 | 52189292.94
DP World Sokhna | 15 | 15 | DP World Sokhna15 | 81940298.01
DP World Sokhna | 16 | 16 | DP World Sokhna16 | 63998840.71
DP World Sokhna | 17 | 17 | DP World Sokhna17 | 41776446.85
DP World Sokhna | 18 | 18 | DP World Sokhna18 | 44310014.32
DP World Sokhna | 19 | 19 | DP World Sokhna19 | 25431108.58
DP World Sokhna | 20 | 20 | DP World Sokhna20 | 31817254.2
DP World Sokhna | 21 | 21 | DP World Sokhna21 | 25746407.39
DP World Sokhna | 22 | 22 | DP World Sokhna22 | 17720371
DP World Sokhna | 23 | 23 | DP World Sokhna23 | 26545255.12
DP World Sokhna | 24 | 24 | DP World Sokhna24 | 20867275.72
DP World Sokhna | 25 | 25 | DP World Sokhna25 | 10313601.64
DP World Sokhna | 26 | 26 | DP World Sokhna26 | 22617919.57
DP World Sokhna | 27 | 27 | DP World Sokhna27 | 15718793.62
DP World Sokhna | 28 | 28 | DP World Sokhna28 | 19977105.85
DP World Sokhna | 29 | 29 | DP World Sokhna29 | 20394668.34
DP World Sokhna | 30 | 30 | DP World Sokhna30 | 10739490.38
DP World Sokhna | 31 | 31 | DP World Sokhna31 | 10014939.05
DP World Sokhna | 32 | 32 | DP World Sokhna32 | 12304801.83
DP World Sokhna | 33 | 33 | DP World Sokhna33 | 15048235.01
DP World Sokhna | 34 | 34 | DP World Sokhna34 | 8899770.44
DP World Sokhna | 35 | 35 | DP World Sokhna35 | 2915333
DP World Sokhna | 36 | 36 | DP World Sokhna36 | 50000000
DP World Sokhna | 36.1 | 36 | DP World Sokhna36 | 30556058.47
DP World Sokhna | 1 | 1 | DP World Sokhna1 | 241563831.68
DPW - Ph.02 | 1 | 1 | DPW - Ph.021 | 21783711.58
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 19448762.45
DPW - Ph.02 | 3 | 3 | DPW - Ph.023 | 28493360.54
DPW - Ph.02 | 4 | 4 | DPW - Ph.024 | 27398639.54
DPW - Ph.02 | 5 | 5 | DPW - Ph.025 | 30104833.54
DPW - Ph.02 | 6 | 6 | DPW - Ph.026 | 23809772.84
DPW - Ph.02 | 7 | 7 | DPW - Ph.027 | 15918348.27
DPW - Ph.02 | 8 | 8 | DPW - Ph.028 | 20524928.94
DPW - Ph.02 | 9 | 9 | DPW - Ph.029 | 49445572.72
DPW - Ph.02 | 10 | 10 | DPW - Ph.0210 | 34610141.8
DPW - Ph.02 | 11 | 11 | DPW - Ph.0211 | 40236573.85
DPW - Ph.02 | 12 | 12 | DPW - Ph.0212 | 15678173.8779
DPW - Ph.02 | 13 | 13 | DPW - Ph.0213 | 18805485.48
DPW - Ph.02 | 14 | 14 | DPW - Ph.0214 | 35568315.9
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 63597656.14
DPW - Ph.02 | 2.1 | 2 | DPW - Ph.022 | 1460242.27
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 4836368.8
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 10019256.26
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 3347979.5
EGAT Pelletizing Plant | 3.1 | 3 | EGAT Pelletizing Plant3 | 766737.3
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 6000000
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 13990653.63
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 10253665.39
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 13147791.3
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 11455129.95
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 14888447
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 16034098.6
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 14151886.79
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 8500000
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 18397068.58
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 7794639.63
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 15000000
EGAT Pelletizing Plant | 15.1 | 15 | EGAT Pelletizing Plant15 | 4186530.1
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 13336148.65
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 19257376.65
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 10000000
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 10000000
EGAT Pelletizing Plant | 19.1 | 19 | EGAT Pelletizing Plant19 | 12197351.2
EGAT Pelletizing Plant | 20 | 20 | EGAT Pelletizing Plant20 | 1e-05
EGAT Pelletizing Plant | 21 | 21 | EGAT Pelletizing Plant21 | 1e-05
EGAT Pelletizing Plant | 22 | 22 | EGAT Pelletizing Plant22 | 1e-05
EGAT Pelletizing Plant - Supply | 1 | 1 | EGAT Pelletizing Plant - Supply1 | 1570903.44
EGAT Pelletizing Plant-Concrete Infra | 1 | 1 | EGAT Pelletizing Plant-Concrete Infra1 | 1e-05
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 10000000
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 2000000
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 5000000
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 20500000
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 28804143.3
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 100000000
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 100000000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 200000000
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 26309409.25
EGAT Pelletizing Plant-Escalation | 1 | 1 | EGAT Pelletizing Plant-Escalation1 | 7000000
EGAT Pelletizing Plant-Mechanical Installation | 1 | 1 | EGAT Pelletizing Plant-Mechanical Installation1 | 1e-05
EGAT Pelletizing Plant-MEP | 1 | 1 | EGAT Pelletizing Plant-MEP1 | 1e-05
EGAT Pelletizing Plant-MEP | 2 | 2 | EGAT Pelletizing Plant-MEP2 | 1e-05
EGAT Pelletizing Plant-MEP | 3 | 3 | EGAT Pelletizing Plant-MEP3 | 1e-05
EGAT Pelletizing Plant-MEP Coordination | 1 | 1 | EGAT Pelletizing Plant-MEP Coordination1 | 1e-05
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 1769274.74
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 15000000
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 50000000
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 23690590.75
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 100000000
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 50000000
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 50000000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 30000000
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 30000000
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 25000000
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 20000000
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 15000000
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 35000000
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 10000000
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 10000000
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 10000000
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 20000000
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 25000000
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 20000000
EGAT Pelletizing Plant | 20 | 20 | EGAT Pelletizing Plant20 | 40000000
EGAT Pelletizing Plant | 21 | 21 | EGAT Pelletizing Plant21 | 20000000
EGAT Pelletizing Plant | 22 | 22 | EGAT Pelletizing Plant22 | 50000000
EGAT Pelletizing Plant | 23 | 23 | EGAT Pelletizing Plant23 | 15000000
EGAT Pelletizing Plant | 24 | 24 | EGAT Pelletizing Plant24 | 10000000
EGAT Pelletizing Plant | 25 | 25 | EGAT Pelletizing Plant25 | 10000000
EGAT Pelletizing Plant | 26 | 26 | EGAT Pelletizing Plant26 | 15000000
EGAT Pelletizing Plant | 27 | 27 | EGAT Pelletizing Plant27 | 10000000
EGAT Pelletizing Plant | 28 | 28 | EGAT Pelletizing Plant28 | 10000000
EGAT Pelletizing Plant | 29 | 29 | EGAT Pelletizing Plant29 | 10000000
EGAT Pelletizing Plant | 30 | 30 | EGAT Pelletizing Plant30 | 15000000
EGAT Pelletizing Plant | 32 | 32 | EGAT Pelletizing Plant32 | 20000000
EGAT Pelletizing Plant | 33 | 33 | EGAT Pelletizing Plant33 | 100000000
EGAT Pelletizing Plant | 34 | 34 | EGAT Pelletizing Plant34 | 20000000
EGAT Pelletizing Plant | 35 | 35 | EGAT Pelletizing Plant35 | 15000000
EGAT Pelletizing Plant | 36 | 36 | EGAT Pelletizing Plant36 | 20000000
EGAT Pelletizing Plant | 37 | 37 | EGAT Pelletizing Plant37 | 5000000
EGAT Pelletizing Plant | 38 | 38 | EGAT Pelletizing Plant38 | 15000000
EGAT Pelletizing Plant | 39 | 39 | EGAT Pelletizing Plant39 | 25000000
EGAT Pelletizing Plant | 40 | 40 | EGAT Pelletizing Plant40 | 15000000
EGAT Pelletizing Plant | 41 | 41 | EGAT Pelletizing Plant41 | 20000000
EGAT Pelletizing Plant | 42 | 42 | EGAT Pelletizing Plant42 | 10000000
EGAT Pelletizing Plant | 43 | 43 | EGAT Pelletizing Plant43 | 35000000
EGAT Pelletizing Plant | 44 | 44 | EGAT Pelletizing Plant44 | 35000000
EGAT Pelletizing Plant | 45 | 45 | EGAT Pelletizing Plant45 | 20000000
EGAT Pelletizing Plant | 46 | 46 | EGAT Pelletizing Plant46 | 32000000
EGAT Pelletizing Plant | 47 | 47 | EGAT Pelletizing Plant47 | 10000000
EGAT Pelletizing Plant | 48 | 48 | EGAT Pelletizing Plant48 | 10000000
EGAT Pelletizing Plant | 49 | 49 | EGAT Pelletizing Plant49 | 10000000
EGAT Pelletizing Plant | 50 | 50 | EGAT Pelletizing Plant50 | 10000000
EGAT Pelletizing Plant | 51 | 51 | EGAT Pelletizing Plant51 | 10000000
EGAT Pelletizing Plant | 52 | 52 | EGAT Pelletizing Plant52 | 10000000
EGAT Pelletizing Plant | 53 | 53 | EGAT Pelletizing Plant53 | 5000000
EGAT Pelletizing Plant | 54 | 54 | EGAT Pelletizing Plant54 | 15000000
EGAT Pelletizing Plant | 55 | 55 | EGAT Pelletizing Plant55 | 7500000
EGAT Pelletizing Plant | 56 | 56 | EGAT Pelletizing Plant56 | 5000000
EGAT Pelletizing Plant-Water Tank | 1 | 1 | EGAT Pelletizing Plant-Water Tank1 | 3241734.16
EGAT Pelletizing Plant-Water Tank | 2 | 2 | EGAT Pelletizing Plant-Water Tank2 | 2008304.1
EGAT Pelletizing Plant-Water Tank | 3 | 3 | EGAT Pelletizing Plant-Water Tank3 | 718104.27
EGAT Pelletizing Plant-Water Tank | 4 | 4 | EGAT Pelletizing Plant-Water Tank4 | 758512.36
EGAT Pelletizing Plant-Water Tank | 5 | 5 | EGAT Pelletizing Plant-Water Tank5 | 914358.66
EGAT Pelletizing Plant-Water Tank | 6 | 6 | EGAT Pelletizing Plant-Water Tank6 | 1449673.43
EGAT Pelletizing Plant-Water Tank | 7 | 7 | EGAT Pelletizing Plant-Water Tank7 | 395732.02
EGAT Pelletizing Plant-Water Tank | 8 | 8 | EGAT Pelletizing Plant-Water Tank8 | 304153.94
EGAT Pelletizing Plant-Water Tank | 9 | 9 | EGAT Pelletizing Plant-Water Tank9 | 967200
EGAT Pelletizing Plant-Water Tank | 10 | 10 | EGAT Pelletizing Plant-Water Tank10 | 3505322.5
EGAT Pelletizing Plant-Water Tank | 11 | 11 | EGAT Pelletizing Plant-Water Tank11 | 3903900.34
EGAT Pelletizing Plant-Water Tank | 12 | 12 | EGAT Pelletizing Plant-Water Tank12 | 1e-05
EGAT Pelletizing Plant-Water Tank | 13 | 13 | EGAT Pelletizing Plant-Water Tank13 | 391272.95
EGAT Pelletizing Plant-Water Tank | 14 | 14 | EGAT Pelletizing Plant-Water Tank14 | 1e-05
EGAT-Asphalt | 1 | 1 | EGAT-Asphalt1 | 598688
EGAT-Asphalt - Retenion Release | 1 | 1 | EGAT-Asphalt - Retenion Release1 | 291975.34
EGAT-EGAT | 1 | 1 | EGAT-EGAT1 | 12000000
EGAT-EGAT | 2 | 2 | EGAT-EGAT2 | 6000000
EGAT-EGAT | 3 | 3 | EGAT-EGAT3 | 6000000
EGAT-EGAT | 4 | 4 | EGAT-EGAT4 | 1500000
EGAT-Fence | 1 | 1 | EGAT-Fence1 | 195752.6
EGAT-Fence | 2 | 2 | EGAT-Fence2 | 0.001
EGAT-Fence | 3 | 3 | EGAT-Fence3 | 457138.81
EGAT-Fence | 3.1 | 3 | EGAT-Fence3 | 237906.8728
EGAT-Fence | 4.1 | 4 | EGAT-Fence4 | 838441.7922
EGAT-Fence | 4.2 | 4 | EGAT-Fence4 | 1000000
EGAT-Fence | 4.3 | 4 | EGAT-Fence4 | 750000
EGAT-Fence | 4.4 | 4 | EGAT-Fence4 | 302594.27
EGAT-Fence - Retenion Release | 1 | 1 | EGAT-Fence - Retenion Release1 | 1161544.2
EGAT-Fence - Retenion Release | 1.1 | 1 | EGAT-Fence - Retenion Release1 | 1e-05
EGAT-HeliPad | 1 | 1 | EGAT-HeliPad1 | 755798.13
EGAT-HeliPad | 2 | 2 | EGAT-HeliPad2 | 500000
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 4717110.35
EGAT-Lock & Load | 2 | 2 | EGAT-Lock & Load2 | 2773213.88
EGAT-Lock & Load | 3 | 3 | EGAT-Lock & Load3 | 1665986.92
EGAT-Lock & Load | 4 | 4 | EGAT-Lock & Load4 | 747255.39
EGAT-Lock & Load | 5 | 5 | EGAT-Lock & Load5 | 2436487.51
EGAT-Lock & Load | 6 | 6 | EGAT-Lock & Load6 | 3176089.21
EGAT-Lock & Load | 7 | 7 | EGAT-Lock & Load7 | 275994.22
EGAT-Lock & Load | 7.1 | 7 | EGAT-Lock & Load7 | 1043113.27
EGAT-Lock & Load | 8 | 8 | EGAT-Lock & Load8 | 2619387.85
EGAT-Lock & Load | 9 | 9 | EGAT-Lock & Load9 | 3741613.11
EGAT-Lock & Load | 10 | 10 | EGAT-Lock & Load10 | 871396.81
EGAT-Lock & Load | 10.1 | 10 | EGAT-Lock & Load10 | 227993.12
EGAT-Lock & Load | 11 | 11 | EGAT-Lock & Load11 | 1873296.27
EGAT-Lock & Load | 12 | 12 | EGAT-Lock & Load12 | 1672142.68
EGAT-Lock & Load | 13 | 13 | EGAT-Lock & Load13 | 1e-05
EGAT-Lock & Load | 14 | 14 | EGAT-Lock & Load14 | 1e-05
EGAT-Lock & Load | 15 | 15 | EGAT-Lock & Load15 | 1e-05
EGAT-Lock & Load | 16 | 16 | EGAT-Lock & Load16 | 1e-05
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 5400000
EGAT-SZ | 1 | 1 | EGAT-SZ1 | 4624356.65
EGAT-SZ | 2 | 2 | EGAT-SZ2 | 10000000
EGAT-SZ | 3 | 3 | EGAT-SZ3 | 6070502.71
EGAT-Warehouse | 1 | 1 | EGAT-Warehouse1 | 923651.335
EIPICO | 1 | 1 | EIPICO1 | 12050858.57
EIPICO | 2 | 2 | EIPICO2 | 13338534.97
EIPICO | 3 | 3 | EIPICO3 | 13033885
EIPICO | 4 | 4 | EIPICO4 | 7344659
EIPICO | 5 | 5 | EIPICO5 | 10064340.12
EIPICO | 6 | 6 | EIPICO6 | 5949568.74
EIPICO | 7 | 7 | EIPICO7 | 6395645.73
EIPICO | 8 | 8 | EIPICO8 | 20317361.34
EIPICO | 9 | 9 | EIPICO9 | 34650000
EIPICO | 10 | 10 | EIPICO10 | 1e-05
EIPICO | 11 | 11 | EIPICO11 | 6263190.12
EIPICO | 11.1 | 11 | EIPICO11 | 17000000
EIPICO | 12 | 12 | EIPICO12 | 25548194.95
EIPICO | 13 | 13 | EIPICO13 | 2882568.41
EIPICO | 14 | 14 | EIPICO14 | 26305980.07
EIPICO | 15 | 15 | EIPICO15 | 25000000
EIPICO | 15.1 | 15 | EIPICO15 | 4236256.89
EIPICO | 16 | 16 | EIPICO16 | 26363887.4
EIPICO | 17 | 17 | EIPICO17 | 13161378.75
EIPICO | 18 | 18 | EIPICO18 | 25000000
EIPICO | 18.1 | 18 | EIPICO18 | 10188037.3
EIPICO | 19 | 19 | EIPICO19 | 10000000
EIPICO | 19.1 | 19 | EIPICO19 | 12436578.36
EIPICO | 20 | 20 | EIPICO20 | 20000000
EIPICO | 1 | 1 | EIPICO1 | 83482074.8
EIPICO | 1 | 1 | EIPICO1 | 85000000
EIPICO | 2 | 2 | EIPICO2 | 10000000
El Sewedy Uni.-PKG.1 | 1 | 1 | El Sewedy Uni.-PKG.11 | 1917993.24
El Sewedy Uni.-PKG.1 | 2 | 2 | El Sewedy Uni.-PKG.12 | 881744.36
El Sewedy Uni.-PKG.1 | 3 | 3 | El Sewedy Uni.-PKG.13 | 1214989
El Sewedy Uni.-PKG.1 | 4 | 4 | El Sewedy Uni.-PKG.14 | 1204112.8596
El Sewedy Uni.-PKG.1 | 5 | 5 | El Sewedy Uni.-PKG.15 | 185635.0557
El Sewedy Uni.-PKG.1 | 6 | 6 | El Sewedy Uni.-PKG.16 | 142702.12
El Sewedy Uni.-PKG.1 | 7 | 7 | El Sewedy Uni.-PKG.17 | 284879.77
El Sewedy Uni.-PKG.1 | 8 | 8 | El Sewedy Uni.-PKG.18 | 235901.48
El Sewedy Uni.-PKG.1 | 9 | 9 | El Sewedy Uni.-PKG.19 | 72777.3
El Sewedy Uni.-PKG.1 | 10 | 10 | El Sewedy Uni.-PKG.110 | -8913.92
El Sewedy Uni.-PKG.11 | 1 | 1 | El Sewedy Uni.-PKG.111 | 2898141.12
El Sewedy Uni.-PKG.2 | 1 | 1 | El Sewedy Uni.-PKG.21 | 3110956.56
El Sewedy Uni.-PKG.2 | 2 | 2 | El Sewedy Uni.-PKG.22 | 6754267.57
El Sewedy Uni.-PKG.2 | 3 | 3 | El Sewedy Uni.-PKG.23 | 3212953.45
El Sewedy Uni.-PKG.2 | 4 | 4 | El Sewedy Uni.-PKG.24 | 3208255.76
El Sewedy Uni.-PKG.2 | 5 | 5 | El Sewedy Uni.-PKG.25 | 4527299.68
El Sewedy Uni.-PKG.2 | 6 | 6 | El Sewedy Uni.-PKG.26 | 7457797.24
El Sewedy Uni.-PKG.2 | 7 | 7 | El Sewedy Uni.-PKG.27 | 2278076.64
El Sewedy Uni.-PKG.2 | 8 | 8 | El Sewedy Uni.-PKG.28 | 2625161.63
El Sewedy Uni.-PKG.2 | 9 | 9 | El Sewedy Uni.-PKG.29 | 1116423
El Sewedy Uni.-PKG.22 | 1 | 1 | El Sewedy Uni.-PKG.221 | 8589000
El Sewedy Uni.-PKG.2-Social Insurrance | 1 | 1 | El Sewedy Uni.-PKG.2-Social Insurrance1 | 1120262.65
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 1727255.6
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 3185421.17
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 5785718.63
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 1785482.76
El Sewedy Uni.-PKG.3 | 5 | 5 | El Sewedy Uni.-PKG.35 | 24218860.6
El Sewedy Uni.-PKG.3 | 6 | 6 | El Sewedy Uni.-PKG.36 | 26716091.61
El Sewedy Uni.-PKG.3 | 7 | 7 | El Sewedy Uni.-PKG.37 | 17000000
El Sewedy Uni.-PKG.3 | 7.1 | 7 | El Sewedy Uni.-PKG.37 | 5410862.51
El Sewedy Uni.-PKG.3 | 8 | 8 | El Sewedy Uni.-PKG.38 | 12292368.36
El Sewedy Uni.-PKG.3 | 9 | 9 | El Sewedy Uni.-PKG.39 | 19287810.69
El Sewedy Uni.-PKG.3 | 10 | 10 | El Sewedy Uni.-PKG.310 | 20919758.8
El Sewedy Uni.-PKG.3 | 11 | 11 | El Sewedy Uni.-PKG.311 | 2318161.39
El Sewedy Uni.-PKG.3 | 12 | 12 | El Sewedy Uni.-PKG.312 | 1515470
El Sewedy Uni.-PKG.3 | 13 | 13 | El Sewedy Uni.-PKG.313 | 6845790.3
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 15000000
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 24971065.75
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 8000000
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 12000000
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 4931187
El Sewedy Uni.-PKG.3-Social Insurrance | 1 | 1 | El Sewedy Uni.-PKG.3-Social Insurrance1 | 253659.18
El Sewedy Uni.-PKG.3-Social Insurrance | 2 | 2 | El Sewedy Uni.-PKG.3-Social Insurrance2 | 267208.33
El Sewedy Uni.-PKG.3-Social Insurrance | 3 | 3 | El Sewedy Uni.-PKG.3-Social Insurrance3 | 3183056.54
El Sewedy Uni.-PKG.3-Social Insurrance | 4 | 4 | El Sewedy Uni.-PKG.3-Social Insurrance4 | 185944.54
Elco Steel | 1 | 1 | Elco Steel1 | 13532577.04
Elco Steel | 2 | 2 | Elco Steel2 | 42881105.07
Elco Steel | 3 | 3 | Elco Steel3 | 54829579.72
Elco Steel | 4 | 4 | Elco Steel4 | 35932469.35
Elco Steel | 5 | 5 | Elco Steel5 | 12038252.26
Elco Steel | 6 | 6 | Elco Steel6 | 20100303
Elco Steel | 7 | 7 | Elco Steel7 | 7919870.17
Elco Steel | 8 | 8 | Elco Steel8 | 6348055.64
Elco Steel | 9 | 9 | Elco Steel9 | 740665.09
Elco Steel | 10 | 10 | Elco Steel10 | 4000000
Elco Steel | 11 | 11 | Elco Steel11 | 7075101.66
Elco Steel | 12 | 12 | Elco Steel12 | 2485656
Elco Steel | 13 | 13 | Elco Steel13 | 2518616.18
Elco Steel | 14 | 14 | Elco Steel14 | 2857649.27
Elco Steel | 15 | 15 | Elco Steel15 | 1595365.5
Elco Steel | 16 | 16 | Elco Steel16 | 310509.31
Elco Steel | 17 | 17 | Elco Steel17 | 1079101.72
Elco Steel - ADMIN. | 1 | 1 | Elco Steel - ADMIN.1 | 1253543.1806
Elco Steel - ADMIN. | 2 | 2 | Elco Steel - ADMIN.2 | 2897721.63
Elco Steel - ADMIN. | 3 | 3 | Elco Steel - ADMIN.3 | 3188918.44
Elco Steel - ADMIN. | 4 | 4 | Elco Steel - ADMIN.4 | 3617002.31
Elco Steel - ADMIN. | 5 | 5 | Elco Steel - ADMIN.5 | 1819035.22
Elco Steel - ADMIN. | 6 | 6 | Elco Steel - ADMIN.6 | 5058047.58
Elco Steel - ADMIN. | 7 | 7 | Elco Steel - ADMIN.7 | 5750618.5816
Elco Steel - ADMIN. | 8 | 8 | Elco Steel - ADMIN.8 | 3289926.92
Elco Steel - ADMIN. | 9 | 9 | Elco Steel - ADMIN.9 | 1940428
Elco Steel - ADMIN. | 10 | 10 | Elco Steel - ADMIN.10 | 2335545.55
Elco Steel - ADMIN. | 11 | 11 | Elco Steel - ADMIN.11 | 2179703.08
Elco Steel - ADMIN. | 12 | 12 | Elco Steel - ADMIN.12 | 1394236.8
Elco Steel - ADMIN. | 13 | 13 | Elco Steel - ADMIN.13 | 117652.86
Elco Steel - ADMIN. | 14 | 14 | Elco Steel - ADMIN.14 | 105992.48
Elco Steel - ADMIN. | 15 | 15 | Elco Steel - ADMIN.15 | 259861.3
Elco Steel - MEP | 1 | 1 | Elco Steel - MEP1 | 331328.322
Elco Steel - MEP | 2 | 2 | Elco Steel - MEP2 | 2059899.63
Elco Steel - MEP | 3 | 3 | Elco Steel - MEP3 | 1986502.95
Elco Steel - MEP | 4 | 4 | Elco Steel - MEP4 | 2505278.83
Elco Steel - MEP | 5 | 5 | Elco Steel - MEP5 | 2440101.67
Elco Steel - MEP | 6 | 6 | Elco Steel - MEP6 | 2133379.76
Elco Steel - MEP | 7 | 7 | Elco Steel - MEP7 | 2606150.307
Elco Steel - MEP | 8 | 8 | Elco Steel - MEP8 | 1980608.55
Elco Steel - MEP | 9 | 9 | Elco Steel - MEP9 | 2178754.66
Elco Steel - MEP | 10 | 10 | Elco Steel - MEP10 | 2629432.67
Elco Steel - MEP | 11 | 11 | Elco Steel - MEP11 | 1720441.01
Elco Steel - MEP | 12 | 12 | Elco Steel - MEP12 | 1037321.78
Elco Steel - MEP | 13 | 13 | Elco Steel - MEP13 | 388339.4
Elco Steel - MEP | 14 | 14 | Elco Steel - MEP14 | 317040.71
Elco Steel - MEP - Social Insurance | 1 | 1 | Elco Steel - MEP - Social Insurance1 | 1700000
Elco Steel - Social Insurance | 1 | 1 | Elco Steel - Social Insurance1 | 13218500
Elco Steel - Social Insurance | 2 | 2 | Elco Steel - Social Insurance2 | 2250000
Elco Steel - Social Insurance | 3 | 3 | Elco Steel - Social Insurance3 | 1573000
Elco Steel - Social Insurance | 4 | 4 | Elco Steel - Social Insurance4 | 134252.42
Elco Steel EGAT | 1 | 1 | Elco Steel EGAT1 | 10000000
Elco Steel V.O | 1 | 1 | Elco Steel V.O1 | 4160000
Elco Steel V.O | 1 | 1 | Elco Steel V.O1 | 500000
Elco Steel V.O-Infra. Network | 1 | 1 | Elco Steel V.O-Infra. Network1 | 767138.81
Elco Steel V.O-Infra. Network | 1.1 | 1 | Elco Steel V.O-Infra. Network1 | 292861.19
El-Gouna | 1 | 1 | El-Gouna1 | 2327690.6
El-Gouna | 2 | 2 | El-Gouna2 | 3867767.27
El-Gouna | 3 | 3 | El-Gouna3 | 2286139.86
El-Gouna | 4 | 4 | El-Gouna4 | 2572404.48
El-Gouna | 5 | 5 | El-Gouna5 | 1808595.27
El-Gouna | 6 | 6 | El-Gouna6 | 4246133.4
El-Gouna | 7 | 7 | El-Gouna7 | 2145687.36
El-Gouna | 8 | 8 | El-Gouna8 | 1922134.77
El-Gouna | 9 | 9 | El-Gouna9 | 1030964.27
El-Gouna | 10 | 10 | El-Gouna10 | 1173489.52
El-Gouna | 11 | 11 | El-Gouna11 | 1750027.3
El-Gouna | 12 | 12 | El-Gouna12 | 1942857.14
El-Gouna | 13 | 13 | El-Gouna13 | 1951940.18
El-Gouna | 14 | 14 | El-Gouna14 | 3058799.81
El-Gouna | 15 | 15 | El-Gouna15 | 3002136.21
El-Gouna | 16 | 16 | El-Gouna16 | 3166964.63
El-Gouna | 17 | 17 | El-Gouna17 | 2526942.2
El-Gouna | 18 | 18 | El-Gouna18 | 5636281.25
El-Gouna-DP | 1 | 1 | El-Gouna-DP1 | 13625000
El-Gouna - Equip. Rental | 1 | 1 | El-Gouna - Equip. Rental1 | 73813.12
El-Gouna - Equip. Rental | 2 | 2 | El-Gouna - Equip. Rental2 | 16757
El-Gouna - Equip. Rental | 3 | 3 | El-Gouna - Equip. Rental3 | 74100
El-Gouna - Equip. Rental | 4 | 4 | El-Gouna - Equip. Rental4 | 3281.25
El-Gouna - Equip. Rental | 5 | 5 | El-Gouna - Equip. Rental5 | 15750
El-Gouna - Temp. Fence | 1 | 1 | El-Gouna - Temp. Fence1 | 425568
El-Gouna - Temp. Fence | 2 | 2 | El-Gouna - Temp. Fence2 | 441526.8
El-Gouna - Temp. Fence | 3 | 3 | El-Gouna - Temp. Fence3 | 173749.2
EUA | 1 | 1 | EUA1 | 120000000
Existing Intake Apply -SSC-Mech | 1 | 1 | Existing Intake Apply -SSC-Mech1 | 1e-05
Existing Intake Supply -SSC-Mech | 1 | 1 | Existing Intake Supply -SSC-Mech1 | 2311727.07
FIEM | 210 | 210 | FIEM210 | 1523916.51
FIEM | 211 | 211 | FIEM211 | 218510
FIEM | 212 | 212 | FIEM212 | 1205285.3
FIEM | 213 | 213 | FIEM213 | 335237.946
FIEM - Retention | 1 | 1 | FIEM - Retention1 | 286904.18
FIEM-Site Offices Rental Payment Request | 1 | 1 | FIEM-Site Offices Rental Payment Request1 | 93000
FIEM-Site Offices Rental Payment Request | 2 | 2 | FIEM-Site Offices Rental Payment Request2 | 93000
FIEM-Site Offices Rental Payment Request | 3 | 3 | FIEM-Site Offices Rental Payment Request3 | 91140
FIEM-Site Offices Rental Payment Request | 4 | 4 | FIEM-Site Offices Rental Payment Request4 | 91140
FIEM-Site Offices Rental Payment Request | 5 | 5 | FIEM-Site Offices Rental Payment Request5 | 91140
FIEM-Site Offices Rental Payment Request | 6 | 6 | FIEM-Site Offices Rental Payment Request6 | 93000
H1 Solaymaneya-MEP | 1 | 1 | H1 Solaymaneya-MEP1 | 1165148
H1 Solaymaneya-MEP | 1 | 1 | H1 Solaymaneya-MEP1 | 4000000
HQ - CFC | 1 | 1 | HQ - CFC1 | 6847513.64
HQ - CFC | 2 | 2 | HQ - CFC2 | 8021127.82
HQ - CFC | 3 | 3 | HQ - CFC3 | 8213720.11
HQ - CFC | 4 | 4 | HQ - CFC4 | 7815807.73
HQ - CFC | 5 | 5 | HQ - CFC5 | 3447418.19
HQ - CFC | 6 | 6 | HQ - CFC6 | 13157200.99
HQ - CFC | 7 | 7 | HQ - CFC7 | 14942810.84
HQ - CFC | 8 | 8 | HQ - CFC8 | 10012745.7
HQ - CFC | 9 | 9 | HQ - CFC9 | 17174919.84
HQ - CFC | 10 | 10 | HQ - CFC10 | 7981881.94
HQ - CFC | 11 | 11 | HQ - CFC11 | 27417402.1
HQ - CFC | 12 | 12 | HQ - CFC12 | 11342066.99
HQ - CFC | 13 | 13 | HQ - CFC13 | 10869511.32
HQ - CFC | 14 | 14 | HQ - CFC14 | 6179916.44
HQ - CFC | 15 | 15 | HQ - CFC15 | 10437699.8
HQ - CFC | 16 | 16 | HQ - CFC16 | 1064612.28
HQ - CFC | 17 | 17 | HQ - CFC17 | 8013147.43
HQ - CFC | 18 | 18 | HQ - CFC18 | 12964666.86
HQ - CFC | 19 | 19 | HQ - CFC19 | 2123375.29
HQ - CFC | 20 | 20 | HQ - CFC20 | 9324446.8
HQ - CFC | 21 | 21 | HQ - CFC21 | 1704646.05
HQ - CFC | 23 | 23 | HQ - CFC23 | 10000000
HQ - CFC | 24 | 24 | HQ - CFC24 | 5681250.46
HQ - CFC | 25 | 25 | HQ - CFC25 | 9125697.43
HQ - CFC | 26 | 26 | HQ - CFC26 | 10915757.94
HQ - CFC | 26.1 | 26 | HQ - CFC26 | 315339.47
HQ - CFC-DP | 1 | 1 | HQ - CFC-DP1 | 103231218.3
HQ - CFC - Retention release | 1 | 1 | HQ - CFC - Retention release1 | 7311955.09
HQ - CFC - Social Insurrance | 1 | 1 | HQ - CFC - Social Insurrance1 | 586840.71
HyperOne | 1 | 1 | HyperOne1 | 2499090
HyperOne | 2 | 2 | HyperOne2 | 8063620
HyperOne | 3 | 3 | HyperOne3 | 6681009
HyperOne | 4 | 4 | HyperOne4 | 6318712
HyperOne | 5 | 5 | HyperOne5 | 3307335
HyperOne | 6 | 6 | HyperOne6 | 8598544
HyperOne | 7 | 7 | HyperOne7 | 8960935
HyperOne | 8 | 8 | HyperOne8 | 3276433
HyperOne | 9 | 9 | HyperOne9 | 1277872
HyperOne | 10 | 10 | HyperOne10 | 4688664
HyperOne | 11 | 11 | HyperOne11 | 6700148
HyperOne | 12 | 12 | HyperOne12 | 1896315
HyperOne | 13 | 13 | HyperOne13 | 6738702
HyperOne | 14 | 14 | HyperOne14 | 4476191
HyperOne | 15 | 15 | HyperOne15 | 2754557
HyperOne | 1 | 1 | HyperOne1 | 33750000
HyperOne-Steel Supply | 1 | 1 | HyperOne-Steel Supply1 | 4724997
HyperOne-Steel Supply | 2 | 2 | HyperOne-Steel Supply2 | 980000
HyperOne-Steel Supply | 3 | 3 | HyperOne-Steel Supply3 | 1165162
HyperOne-Steel Supply | 4 | 4 | HyperOne-Steel Supply4 | 4993651
HyperOne-Steel Supply | 5 | 5 | HyperOne-Steel Supply5 | 305602
HyperOne-Steel Supply | 6 | 6 | HyperOne-Steel Supply6 | 3490984
HyperOne-VAT 1,2,3 | 1 | 1 | HyperOne-VAT 1,2,31 | 1171706
IKEA | 1 | 1 | IKEA1 | 4032556.9
IKEA | 2 | 2 | IKEA2 | 10633715.55
IKEA | 3 | 3 | IKEA3 | 7184168.18
IKEA | 4 | 4 | IKEA4 | 8278802.07
IKEA | 5 | 5 | IKEA5 | 7929959.808
IKEA | 6 | 6 | IKEA6 | 3899213.68
IKEA | 7 | 7 | IKEA7 | 6161858.91
IKEA | 8 | 8 | IKEA8 | 13080191.13
IKEA | 9 | 9 | IKEA9 | 21936362.84
IKEA | 10 | 10 | IKEA10 | 10981834.92
IKEA | 11 | 11 | IKEA11 | 16592416.38
IKEA | 12 | 12 | IKEA12 | 15898929.26
IKEA | 13 | 13 | IKEA13 | 5400893.31
IKEA | 14 | 14 | IKEA14 | 15116863.46
IKEA | 1 | 1 | IKEA1 | 5000000
IKEA | 2 | 2 | IKEA2 | 428986.9
IKEA | 3 | 3 | IKEA3 | 4951900.8
IKEA | 4 | 4 | IKEA4 | 2116049.37
IKEA | 5 | 5 | IKEA5 | 21562500
IKEA | 6 | 6 | IKEA6 | 1818917
IKEA | 7 | 7 | IKEA7 | 3751873.62
IKEA | 8 | 8 | IKEA8 | 525633.83
IKEA-Retention Release | 1 | 1 | IKEA-Retention Release1 | 5552983.6
JICA | 19 | 19 | JICA19 | 1141675.91
JICA | 20 | 20 | JICA20 | 413014.8
JICA-Site Offices Rental Payment Request | 1 | 1 | JICA-Site Offices Rental Payment Request1 | 75000
JICA-Site Offices Rental Payment Request | 2 | 2 | JICA-Site Offices Rental Payment Request2 | 75000
JICA-Site Offices Rental Payment Request | 3 | 3 | JICA-Site Offices Rental Payment Request3 | 75000
JICA-Site Offices Rental Payment Request | 4 | 4 | JICA-Site Offices Rental Payment Request4 | 75000
Kafr Shokr | 1 | 1 | Kafr Shokr 1 | 28845197.4
Kafr Shokr | 2 | 2 | Kafr Shokr 2 | 6242742.2
Kafr Shokr | 3 | 3 | Kafr Shokr 3 | 8372664.9
Kafr Shokr | 4 | 4 | Kafr Shokr 4 | 8190447.9
Kafr Shokr | 5 | 5 | Kafr Shokr 5 | 5371513.65
Kafr Shokr | 6 | 6 | Kafr Shokr 6 | 444257.7
Kafr Shokr | 7 | 7 | Kafr Shokr 7 | 26652960.08
Kafr Shokr | 8 | 8 | Kafr Shokr 8 | 2028646.62
Kafr Shokr | 9 | 9 | Kafr Shokr 9 | 678824.25
Kafr Shokr | 9.1 | 9 | Kafr Shokr 9 | 4133066.85
Kafr Shokr | 10 | 10 | Kafr Shokr 10 | 2390708.7
Kafr Shokr - Retention Release | 1 | 1 | Kafr Shokr - Retention Release1 | 884808.35
Katameya - Creeks | 1 | 1 | Katameya - Creeks1 | 2741191.29
Katameya - Creeks | 2 | 2 | Katameya - Creeks2 | 11302769.9409
Katameya - Creeks | 3 | 3 | Katameya - Creeks3 | 39570120.9
Katameya - Creeks | 4 | 4 | Katameya - Creeks4 | 9000000
Katameya - Creeks | 4.1 | 4 | Katameya - Creeks4 | 20688637.31
Katameya - Creeks | 5 | 5 | Katameya - Creeks5 | 40006572.36
Katameya - Creeks | 6 | 6 | Katameya - Creeks6 | 29363826.77
Katameya - Creeks | 7 | 7 | Katameya - Creeks7 | 24380443
Katameya - Creeks | 7.1 | 7 | Katameya - Creeks7 | 20000000
Katameya - Creeks | 8 | 8 | Katameya - Creeks8 | 20000000
Katameya - Creeks | 8.1 | 8 | Katameya - Creeks8 | 20343227.98
Katameya - Creeks | 9 | 9 | Katameya - Creeks9 | 20000000
Katameya - Creeks | 9.1 | 9 | Katameya - Creeks9 | 10000000
Katameya - Creeks | 9.2 | 9 | Katameya - Creeks9 | 13056438.19
Katameya - Creeks | 10 | 10 | Katameya - Creeks10 | 61159972.97
Katameya - Creeks | 11 | 11 | Katameya - Creeks11 | 43214038.28
Katameya - Creeks | 12 | 12 | Katameya - Creeks12 | 36461301.55
Katameya - Creeks | 13 | 13 | Katameya - Creeks13 | 39353596.01
Katameya - Creeks | 14 | 14 | Katameya - Creeks14 | 45904629.98
Katameya - Creeks | 15 | 15 | Katameya - Creeks15 | 49567395
Katameya - Creeks | 16 | 16 | Katameya - Creeks16 | 25000000
Katameya - Creeks | 16.1 | 16 | Katameya - Creeks16 | 19583744
Katameya - Creeks | 17 | 17 | Katameya - Creeks17 | 20000000
Katameya - Creeks | 17.1 | 17 | Katameya - Creeks17 | 16501027.74
Katameya - Creeks | 18 | 18 | Katameya - Creeks18 | 21565441.8
Katameya - Creeks | 18.1 | 18 | Katameya - Creeks18 | 20000000
Katameya - Creeks | 19 | 19 | Katameya - Creeks19 | 20000000
Katameya - Creeks | 19.1 | 19 | Katameya - Creeks19 | 16081249.47
Katameya - Creeks | 20 | 20 | Katameya - Creeks20 | 15000000
Katameya - Creeks | 20.1 | 20 | Katameya - Creeks20 | 9569045
Katameya - Creeks | 21 | 21 | Katameya - Creeks21 | 20000000
Katameya - Creeks | 21.1 | 21 | Katameya - Creeks21 | 15259435.93
Katameya - Creeks | 22 | 22 | Katameya - Creeks22 | 10000000
Katameya - Creeks | 22.1 | 22 | Katameya - Creeks22 | 21299260.01
Katameya - Creeks | 23 | 23 | Katameya - Creeks23 | 8700739.99
Katameya - Creeks | 23.1 | 23 | Katameya - Creeks23 | 21133993.08
Katameya - Creeks | 24 | 24 | Katameya - Creeks24 | 3866006.92
Katameya - Creeks | 24.1 | 24 | Katameya - Creeks24 | 34010573
Katameya - Creeks | 25 | 25 | Katameya - Creeks25 | 45191848.31
Katameya - Creeks | 26 | 26 | Katameya - Creeks26 | 30000000
Katameya - Creeks | 26.1 | 26 | Katameya - Creeks26 | 44263221
Katameya - Creeks | 27 | 27 | Katameya - Creeks27 | 35452924
Katameya - Creeks | 28 | 28 | Katameya - Creeks28 | 28650459
Katameya - Creeks | 29 | 29 | Katameya - Creeks29 | 40904481
Katameya - Creeks | 30 | 30 | Katameya - Creeks30 | 43084120
Katameya - Creeks | 31 | 31 | Katameya - Creeks31 | 37106226
Katameya - Creeks | 32 | 32 | Katameya - Creeks32 | 41216438
Katameya - Creeks | 33 | 33 | Katameya - Creeks33 | 47329833
Katameya - Creeks | 34 | 34 | Katameya - Creeks34 | 40000000
Katameya - Creeks | 34.1 | 34 | Katameya - Creeks34 | 30308953
Katameya - Creeks | 35 | 35 | Katameya - Creeks35 | 46816344
Katameya - Creeks | 36 | 36 | Katameya - Creeks36 | 33146996.78
Katameya - Creeks | 36.1 | 36 | Katameya - Creeks36 | 17383228
Katameya - Creeks | 37 | 37 | Katameya - Creeks37 | 40000000
Katameya - Creeks | 37.1 | 37 | Katameya - Creeks37 | 22109565
Katameya - Creeks | 38 | 38 | Katameya - Creeks38 | 79235150
Katameya - Creeks | 39 | 39 | Katameya - Creeks39 | 66261026
Katameya - Creeks | 40 | 40 | Katameya - Creeks40 | 30000000
Katameya - Creeks | 40.1 | 40 | Katameya - Creeks40 | 22039038
Katameya - Creeks | 41 | 41 | Katameya - Creeks41 | 24776126.81
Katameya - Creeks | 41.1 | 41 | Katameya - Creeks41 | 20564552
Katameya - Creeks | 42 | 42 | Katameya - Creeks42 | 25000000
Katameya - Creeks | 42.1 | 42 | Katameya - Creeks42 | 27791233
Katameya - Creeks | 43 | 43 | Katameya - Creeks43 | 21224102
Katameya - Creeks | 44 | 44 | Katameya - Creeks44 | 8345106.3
Katameya - Creeks | 45 | 45 | Katameya - Creeks45 | 8654893.7
Katameya - Creeks-DP | 1 | 1 | Katameya - Creeks-DP1 | 200000000
Katameya - Creeks - Alu Glass | 2 | 2 | Katameya - Creeks - Alu Glass2 | 10000000
Katameya - Creeks | 2 | 2 | Katameya - Creeks2 | 45000000
Katameya - Creeks | 3 | 3 | Katameya - Creeks3 | 45000000
Katameya - Creeks | 4 | 4 | Katameya - Creeks4 | 20000000
KFW | 109 | 109 | KFW109 | 128570.36
KFW | 110 | 110 | KFW110 | 377225.16
KFW-Road Signals | 1 | 1 | KFW-Road Signals 1 | 35249.2
Khatatba Bridge | 1 | 1 | Khatatba Bridge1 | 803531.75
Khatatba Bridge | 2 | 2 | Khatatba Bridge2 | 7509538.3
Khatatba Bridge | 4 | 4 | Khatatba Bridge4 | 36303482.3
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 252408.0531
KSA-Tarek AbdelHakim Center | 2 | 2 | KSA-Tarek AbdelHakim Center2 | 562894.3581
KSA-Tarek AbdelHakim Center | 3 | 3 | KSA-Tarek AbdelHakim Center3 | 194180.7389
KSA-Tarek AbdelHakim Center | 4 | 4 | KSA-Tarek AbdelHakim Center4 | 242494.97
KSA-Tarek AbdelHakim Center | 5 | 5 | KSA-Tarek AbdelHakim Center5 | 260811.86
KSA-Tarek AbdelHakim Center | 6 | 6 | KSA-Tarek AbdelHakim Center6 | 253333.77
KSA-Tarek AbdelHakim Center | 7 | 7 | KSA-Tarek AbdelHakim Center7 | 450546.16
KSA-Tarek AbdelHakim Center | 8 | 8 | KSA-Tarek AbdelHakim Center8 | 630195.46
KSA-Tarek AbdelHakim Center | 9 | 9 | KSA-Tarek AbdelHakim Center9 | 1513478.59
KSA-Tarek AbdelHakim Center | 10 | 10 | KSA-Tarek AbdelHakim Center10 | 1468894.06
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 930841.52
LEKELA | 1 | 1 | LEKELA1 | 1670902.46
LEKELA | 2 | 2 | LEKELA2 | 1067868.0976
LEKELA | 3 | 3 | LEKELA3 | 1758948.8952
LEKELA | 4 | 4 | LEKELA4 | 652923.5
LEKELA | 5 | 5 | LEKELA5 | 7094954.7715
LEKELA | 6 | 6 | LEKELA6 | 14840272.4231
LEKELA | 7 | 7 | LEKELA7 | 15073158.35
LEKELA | 8 | 8 | LEKELA8 | 32746957.2169
LEKELA | 8.1 | 8 | LEKELA8 | 610200
LEKELA | 9 | 9 | LEKELA9 | 18594958.1925
LEKELA | 10 | 10 | LEKELA10 | 21709399.51
LEKELA | 11 | 11 | LEKELA11 | 14896483.6
LEKELA | 12 | 12 | LEKELA12 | 21477147.745
LEKELA | 13 | 13 | LEKELA13 | 2329136.4958
LEKELA | 14 | 14 | LEKELA14 | 12951636.6142
LEKELA | 15 | 15 | LEKELA15 | 203400
LEKELA | 15.1 | 15 | LEKELA15 | 406481.34
LEKELA | 15.2 | 15 | LEKELA15 | 3229199.85
LEKELA | 16 | 16 | LEKELA16 | 8212932
LEKELA - Supply Bill | 1 | 1 | LEKELA - Supply Bill1 | 124228
LEKELA- | 1 | 1 | LEKELA-1 | 3229199.85
LEKELA Remedial | 2 | 2 | LEKELA Remedial2 | 7000000.52
LEKELA Remedial | 3 | 3 | LEKELA Remedial3 | 3000357.34
LEKELA Remedial | 4 | 4 | LEKELA Remedial4 | 6400022.32
LEKELA Remedial | 1 | 1 | LEKELA Remedial1 | 6281009.56
LEKELA | 1 | 1 | LEKELA1 | 36300000
MDF Factory | 1 | 1 | MDF Factory1 | 6231879
MDF Factory | 2 | 2 | MDF Factory2 | 7093735
MDF Factory | 3 | 3 | MDF Factory3 | 8598867
MDF Factory | 4 | 4 | MDF Factory4 | 8359615
MDF Factory | 5 | 5 | MDF Factory5 | 10000000
MDF Factory | 5.1 | 5 | MDF Factory5 | 11785508.92
MDF Factory | 6 | 6 | MDF Factory6 | 10000000
MDF Factory | 6.1 | 6 | MDF Factory6 | 7171193.33
MDF Factory | 7 | 7 | MDF Factory7 | 13606480
MDF Factory | 8 | 8 | MDF Factory8 | 13352571.68
MDF Factory | 9 | 9 | MDF Factory9 | 5188292.65
MDF Factory | 10 | 10 | MDF Factory10 | 10230767.51
MDF Factory | 11 | 11 | MDF Factory11 | 8835349.23
MDF Factory | 12 | 12 | MDF Factory12 | 25380982.3
MDF Factory | 13 | 13 | MDF Factory13 | 2351273.22
MDF Factory | 14 | 14 | MDF Factory14 | 10000000
MDF Factory | 14.1 | 14 | MDF Factory14 | 1219362.36
MDF Factory | 15 | 15 | MDF Factory15 | 10000000
MDF Factory | 15.1 | 15 | MDF Factory15 | 812468.25
MDF Factory | 16 | 16 | MDF Factory16 | 10000000
MDF Factory | 16.1 | 16 | MDF Factory16 | 601848.06
MDF Factory | 17 | 17 | MDF Factory17 | 7000000
MDF Factory | 17.1 | 17 | MDF Factory17 | 6701835.53
MDF Factory | 18 | 18 | MDF Factory18 | 3474417.48
MDF Factory | 19 | 19 | MDF Factory19 | 8855940.16
MDF Factory | 20 | 20 | MDF Factory20 | 1506264.66
MDF Factory | 21 | 21 | MDF Factory21 | 10000000
MDF Factory | 21.1 | 21 | MDF Factory21 | 6783340.22
MDF Factory | 22 | 22 | MDF Factory22 | 9454487.21
MDF Factory | 23 | 23 | MDF Factory23 | 10035885.59
MDF Factory | 24 | 24 | MDF Factory24 | 5923051.17
MDF Factory | 25 | 25 | MDF Factory25 | 4519315.77
MDF Factory | 26 | 26 | MDF Factory26 | 12901160.06
MDF Factory | 27 | 27 | MDF Factory27 | 13230747.82
MDF Factory | 27.1 | 27 | MDF Factory27 | 5946852.52
MDF Factory | 28 | 28 | MDF Factory28 | 5380287.99
MDF Factory | 29 | 29 | MDF Factory29 | 10038430.32
MDF Factory | 30 | 30 | MDF Factory30 | 11530799.53
MDF Factory | 31 | 31 | MDF Factory31 | 18846610.6
MDF Factory | 32 | 32 | MDF Factory32 | 2726460
MDF Factory | 33 | 33 | MDF Factory33 | 8808260.33
MDF Factory | 34 | 34 | MDF Factory34 | 12466636.78
MDF Factory | 35 | 35 | MDF Factory35 | 11964736.84
MDF Factory | 36 | 36 | MDF Factory36 | 10194821.77
MDF Factory | 37 | 37 | MDF Factory37 | 4465149.39
MDF Factory | 38 | 38 | MDF Factory38 | 9539881.65
MDF Factory | 39 | 39 | MDF Factory39 | 6984174.92
MDF Factory | 40 | 40 | MDF Factory40 | 13054639.6
MDF Factory | 41 | 41 | MDF Factory41 | 8347962.7
MDF Factory | 42 | 42 | MDF Factory42 | 3999590
MDF Factory | 42.1 | 42 | MDF Factory42 | 3602411.04
MDF Factory | 43 | 43 | MDF Factory43 | 44999590
MDF Factory | 43.1 | 43 | MDF Factory43 | 999590
MDF Factory - Equip. | 1 | 1 | MDF Factory - Equip.1 | 479255
MDF Factory - Equip. | 2 | 2 | MDF Factory - Equip.2 | 2957905.39
MDF Factory - Equip. | 3 | 3 | MDF Factory - Equip.3 | 2467707.5
MDF Factory - Equip. | 4 | 4 | MDF Factory - Equip.4 | 2118826
MDF Factory - Equip. | 5 | 5 | MDF Factory - Equip.5 | 2067056
MDF Factory - Equip. | 6 | 6 | MDF Factory - Equip.6 | 569764
MDF Factory - Equip. | 7 | 7 | MDF Factory - Equip.7 | 795032
MDF Factory - Equip. | 8 | 8 | MDF Factory - Equip.8 | 322760
MDF Factory - Equip. | 9 | 9 | MDF Factory - Equip.9 | 1546900
MDF Factory - Equip. | 10 | 10 | MDF Factory - Equip.10 | 362327.85
MDF Factory - Equip. | 11 | 11 | MDF Factory - Equip.11 | 115740.16
MDF Factory - Equip. | 12 | 12 | MDF Factory - Equip.12 | 617997.99
MDF Factory - Equip. | 13 | 13 | MDF Factory - Equip.13 | 1033353.65
MDF Factory - Equip. | 14 | 14 | MDF Factory - Equip.14 | 1342515
MDF Factory - Equip. | 15 | 15 | MDF Factory - Equip.15 | 1508230
MDF Factory - Equip. | 16 | 16 | MDF Factory - Equip.16 | 963455.46
MDF Factory - Equip. | 17 | 17 | MDF Factory - Equip.17 | 359356.67
MDF Factory - Equip. | 18 | 18 | MDF Factory - Equip.18 | 536737.62
MDF Factory - Equip. | 19 | 19 | MDF Factory - Equip.19 | 1190791
MDF Factory - Equip. | 20 | 20 | MDF Factory - Equip.20 | 606416.12
MDF Factory - Equip. | 21 | 21 | MDF Factory - Equip.21 | 600370.17
MDF Factory - Equip. | 22 | 22 | MDF Factory - Equip.22 | 205199.38
MDF Factory - Equip. | 23 | 23 | MDF Factory - Equip.23 | 545334.31
MDF Factory - Equip. | 24 | 24 | MDF Factory - Equip.24 | 345289.58
MDF Factory - Equip. | 25 | 25 | MDF Factory - Equip.25 | 637190.72
MDF Factory - Local Fabrication | 1 | 1 | MDF Factory - Local Fabrication1 | 920351.25
MDF Factory - Local Fabrication | 2 | 2 | MDF Factory - Local Fabrication2 | 711105.4
MDF Factory - Local Fabrication | 3 | 3 | MDF Factory - Local Fabrication3 | 897908
MDF Factory - Local Fabrication | 4 | 4 | MDF Factory - Local Fabrication4 | 667444
MDF Factory - Local Fabrication | 5 | 5 | MDF Factory - Local Fabrication5 | 2517907.41
MDF Factory - Local Fabrication | 6 | 6 | MDF Factory - Local Fabrication6 | 737043.71
MDF Factory - Local Fabrication | 7 | 7 | MDF Factory - Local Fabrication7 | 785269
MDF Factory - Local Fabrication | 8 | 8 | MDF Factory - Local Fabrication8 | 381060.37
MDF Factory - Local Fabrication | 9 | 9 | MDF Factory - Local Fabrication9 | 1752018.76
MDF Factory - Local Fabrication | 10 | 10 | MDF Factory - Local Fabrication10 | 2881529.05
MDF Factory - Local Fabrication | 11 | 11 | MDF Factory - Local Fabrication11 | 2412700.43
MDF Factory - Local Fabrication | 14 | 14 | MDF Factory - Local Fabrication14 | 10315795
MDF Factory - Local Fabrication | 15 | 15 | MDF Factory - Local Fabrication15 | 2970230
MDF Factory - Local Fabrication | 16 | 16 | MDF Factory - Local Fabrication16 | 1262500
MDF Factory - Local Fabrication | 18 | 18 | MDF Factory - Local Fabrication18 | 4265111
MDF Factory - Local Fabrication | 19 | 19 | MDF Factory - Local Fabrication19 | 3358613
MDF Factory | 1 | 1 | MDF Factory1 | 41622365.4
MDF Factory | 2 | 2 | MDF Factory2 | 6300000
MDF Factory | 3 | 3 | MDF Factory3 | 2000000
MDF Factory | 4 | 4 | MDF Factory4 | 2000000
MDF Factory | 5 | 5 | MDF Factory5 | 10016624.86
MDF Factory | 6 | 6 | MDF Factory6 | 7332000
MDF Factory | 7 | 7 | MDF Factory7 | 6000000
MDF Factory | 8 | 8 | MDF Factory8 | 11000000
MDF Factory | 9 | 9 | MDF Factory9 | 13754630
MDF Factory | 10 | 10 | MDF Factory10 | 1488562.75
MDF Factory | 11 | 11 | MDF Factory11 | 3000000
MDF Factory-F.F V.O | 1 | 1 | MDF Factory-F.F V.O1 | 8500000
MDF Factory-F.F V.O | 2 | 2 | MDF Factory-F.F V.O2 | 7800000
MDF Factory-Hold Amount release | 1 | 1 | MDF Factory-Hold Amount release1 | 2000000
MDF Factory-Local Fab. | 1 | 1 | MDF Factory-Local Fab.1 | 3500000
MDF Factory | 3 | 3 | MDF Factory3 | 7811797.56
MDF Factory | 4 | 4 | MDF Factory4 | 9000000
MDF Factory | 5 | 5 | MDF Factory5 | 7000000
MDF Factory | 6 | 6 | MDF Factory6 | 4000000
MDF Factory | 7 | 7 | MDF Factory7 | 40000000
MDF Factory | 8 | 8 | MDF Factory8 | 5000000
MDF Factory solera | 1 | 1 | MDF Factory solera1 | 8000000
MDF Factory solera | 2 | 2 | MDF Factory solera2 | 18121000
MDF Factory solera | 3 | 3 | MDF Factory solera3 | 7600000
MDF Factory-P.O | 3 | 3 | MDF Factory-P.O3 | 23100000
Mechanical Installation | 1 | 1 | Mechanical Installation1 | 15000000
Mintra | 1 | 1 | Mintra1 | 5500000
Mintra | 2 | 2 | Mintra2 | 3000000
Mintra | 3 | 3 | Mintra3 | 2220782.14
Mintra | 4 | 4 | Mintra4 | 3500000
Mintra | 5 | 5 | Mintra5 | 8000000
Mintra | 6 | 6 | Mintra6 | 6000000
Mintra | 7 | 7 | Mintra7 | 2005948.91
Mintra | 1 | 1 | Mintra1 | 10000000
Mintra-Hanger 1200m2 | 1 | 1 | Mintra-Hanger 1200m21 | 531998.67
Mintra-Hanger 1200m2 | 2 | 2 | Mintra-Hanger 1200m22 | -6217.18
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 2533668.0255
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 2620895.13
Mivida-PK#140 | 3 | 3 | Mivida-PK#1403 | 4070832.3885
Mivida-PK#140 | 4 | 4 | Mivida-PK#1404 | 999645.4398
Mivida-PK#140 | 5 | 5 | Mivida-PK#1405 | 1337507.07
Mivida-PK#140 | 6 | 6 | Mivida-PK#1406 | 10719905.22
Mivida-PK#140 | 7 | 7 | Mivida-PK#1407 | 6547225.82
Mivida-PK#140 | 8 | 8 | Mivida-PK#1408 | 4740517.5525
Mivida-PK#140 | 9 | 9 | Mivida-PK#1409 | 4559999.09
Mivida-PK#140 | 10 | 10 | Mivida-PK#14010 | 5679423.0614
Mivida-PK#140 | 11 | 11 | Mivida-PK#14011 | 2647674.17
Mivida-PK#140 | 12 | 12 | Mivida-PK#14012 | 4687303.44
Mivida-PK#140 | 13 | 13 | Mivida-PK#14013 | 1169770.65
Mivida-PK#140 | 14 | 14 | Mivida-PK#14014 | 7336701.1
Mivida-PK#140 | 15 | 15 | Mivida-PK#14015 | 10305723.52
Mivida-PK#140 | 16 | 16 | Mivida-PK#14016 | 10553431.24
Mivida-PK#140 | 17 | 17 | Mivida-PK#14017 | 11726998.43
Mivida-PK#140 | 18 | 18 | Mivida-PK#14018 | 3831058.93
Mivida-PK#140 | 19 | 19 | Mivida-PK#14019 | 8885358.62
Mivida-PK#140 | 20 | 20 | Mivida-PK#14020 | 5084359.83
Mivida-PK#140 | 21 | 21 | Mivida-PK#14021 | 8185193.83
Mivida-PK#140 | 22 | 22 | Mivida-PK#14022 | 4603109.14
Mivida-PK#140 | 23 | 23 | Mivida-PK#14023 | 3870461.7
Mivida-PK#140 | 24 | 24 | Mivida-PK#14024 | 3732732.7981
Mivida-PK#140 | 25 | 25 | Mivida-PK#14025 | 9016182.24
Mivida-PK#140 | 26 | 26 | Mivida-PK#14026 | 3143991.8
Mivida-PK#140 | 27 | 27 | Mivida-PK#14027 | 5157960.04
Mivida-PK#140- Social Insurance | 1 | 1 | Mivida-PK#140- Social Insurance1 | 509706.15
Mivida-PK#140- Social Insurance | 2 | 2 | Mivida-PK#140- Social Insurance2 | 1677431
Mivida-PK#140- Social Insurance | 3 | 3 | Mivida-PK#140- Social Insurance3 | 596538.75
Mivida-PK#140- Social Insurance | 4 | 4 | Mivida-PK#140- Social Insurance4 | 908034.47
Mivida-PK#140- Social Insurance | 5 | 5 | Mivida-PK#140- Social Insurance5 | 1805452.05
Mivida-PK#140- Social Insurance | 6 | 6 | Mivida-PK#140- Social Insurance6 | 976304.25
Mivida-PK#140- Social Insurance | 7 | 7 | Mivida-PK#140- Social Insurance7 | 871421.04
Mivida-PK#140- Social Insurance | 8 | 8 | Mivida-PK#140- Social Insurance8 | 1298461.89
Mivida-PK#140- Social Insurance | 9 | 9 | Mivida-PK#140- Social Insurance9 | 494886.87
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 15567604.3
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 7313962.6
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 18095262.89
Mivida-PK#189 | 2 | 2 | Mivida-PK#1892 | 22529255.88
Mivida-PK#189 | 3 | 3 | Mivida-PK#1893 | 19800407.88
Mivida-PK#189 | 4 | 4 | Mivida-PK#1894 | 27644756.83
Mivida-PK#189 | 5 | 5 | Mivida-PK#1895 | 46638711.45
Mivida-PK#189 | 6 | 6 | Mivida-PK#1896 | 70000000
Mivida-PK#189 | 7 | 7 | Mivida-PK#1897 | 38664242.89
Mivida-PK#189 | 8 | 8 | Mivida-PK#1898 | 62566272.8
Mivida-PK#189 | 9 | 9 | Mivida-PK#1899 | 37089198
Mivida-PK#189 | 10 | 10 | Mivida-PK#18910 | 22123110.41
Mivida-PK#189 | 11 | 11 | Mivida-PK#18911 | 18794302.39
Mivida-PK#189 | 12 | 12 | Mivida-PK#18912 | 16890748.06
Mivida-PK#189 | 13 | 13 | Mivida-PK#18913 | 50032149.11
Mivida-PK#189 | 14 | 14 | Mivida-PK#18914 | 22045664.4
Mivida-PK#189 | 15 | 15 | Mivida-PK#18915 | 20013901.02
Mivida-PK#189 | 16 | 16 | Mivida-PK#18916 | 22512171.88
Mivida-PK#189 | 17 | 17 | Mivida-PK#18917 | 47104890.0563
Mivida-PK#189 | 18 | 18 | Mivida-PK#18918 | 20024965.62
Mivida-PK#189 | 19 | 19 | Mivida-PK#18919 | 23323710.11
Mivida-PK#189 | 21 | 21 | Mivida-PK#18921 | 14476604.63
Mivida-PK#189 | 22 | 22 | Mivida-PK#18922 | 17552608.99
Mivida-PK#189 | 23 | 23 | Mivida-PK#18923 | 14242173.09
Mivida-PK#189 | 24 | 24 | Mivida-PK#18924 | 13803484.92
Mivida-PK#189 | 25 | 25 | Mivida-PK#18925 | 28360739.45
Mivida-PK#189 | 26 | 26 | Mivida-PK#18926 | 14177811.26
Mivida-PK#189 | 27 | 27 | Mivida-PK#18927 | 4389859.04
Mivida-PK#189 | 28 | 28 | Mivida-PK#18928 | 2409288.21
Mivida-PK#189 | 29 | 29 | Mivida-PK#18929 | 2690517.47
Mivida-PK#189 | 30 | 30 | Mivida-PK#18930 | 14412191.12
Mivida-PK#189 | 20 | 20 | Mivida-PK#18920 | 135145955
Mivida-PK#189 - Social insurance | 1 | 1 | Mivida-PK#189 - Social insurance1 | 5182786.9
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 99600000
MOC | 1 | 1 | MOC1 | 33350000
New Gas Station | 1 | 1 | New Gas Station1 | 2201210.4
New Gas Station | 2 | 2 | New Gas Station2 | 1419355.25
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 23161171
New Giza Hospital | 2 | 2 | New Giza Hospital2 | 13964209
New Giza Hospital | 3 | 3 | New Giza Hospital3 | 7088017
New Giza Hospital | 4 | 4 | New Giza Hospital4 | 25531752
New Giza Hospital | 5 | 5 | New Giza Hospital5 | 9692684
New Giza Hospital | 6 | 6 | New Giza Hospital6 | 12645886
New Giza Hospital | 7 | 7 | New Giza Hospital7 | 12694720
New Giza Hospital | 8 | 8 | New Giza Hospital8 | 11865059
New Giza Hospital | 9 | 9 | New Giza Hospital9 | 15594713
New Giza Hospital | 10 | 10 | New Giza Hospital10 | 14931468
New Giza Hospital | 11 | 11 | New Giza Hospital11 | 19979218
New Giza Hospital | 12 | 12 | New Giza Hospital12 | 21023839
New Giza Hospital | 13 | 13 | New Giza Hospital13 | 17903308
New Giza Hospital | 14 | 14 | New Giza Hospital14 | 15197022
New Giza Hospital | 15 | 15 | New Giza Hospital15 | 7535461
New Giza Hospital | 16 | 16 | New Giza Hospital16 | 7643976
New Giza Hospital | 18 | 18 | New Giza Hospital18 | 14511461
New Giza Hospital | 19 | 19 | New Giza Hospital19 | 3705542
New Giza Hospital | 20 | 20 | New Giza Hospital20 | 18995740
New Giza Hospital | 21 | 21 | New Giza Hospital21 | 4008305
New Giza Hospital | 22 | 22 | New Giza Hospital22 | 6681249
New Giza Hospital | 23 | 23 | New Giza Hospital23 | 3104562
New Giza Hospital | 24 | 24 | New Giza Hospital24 | 4494905.88
New Giza Hospital | 25 | 25 | New Giza Hospital25 | 10195246
New Giza Hospital | 26 | 26 | New Giza Hospital26 | 2983818.1724
New Giza Hospital | 26.1 | 26 | New Giza Hospital26 | 15145301
New Giza Hospital | 27 | 27 | New Giza Hospital27 | 2051894
New Giza Hospital | 28 | 28 | New Giza Hospital28 | 5534314
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 73512565
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 15000000
New Giza Hospital | 2 | 2 | New Giza Hospital2 | 2983818.1724
New Giza Hospital-Social Insurance | 1 | 1 | New Giza Hospital-Social Insurance1 | 3128055
New Giza Hospital-Social Insurance | 2 | 2 | New Giza Hospital-Social Insurance2 | 4605279
New Giza Hospital-Social Insurance | 3 | 3 | New Giza Hospital-Social Insurance3 | 2326029.9476
New Giza Hospital-Social Insurance | 4 | 4 | New Giza Hospital-Social Insurance4 | 1019222
NGU 2 | 25 | 25 | NGU 225 | 2468493.7
NGU 2 | 26 | 26 | NGU 226 | 4990186
NGU 2 | 27 | 27 | NGU 227 | 2104161
NGU 2 - Retension release | 1 | 1 | NGU 2 - Retension release1 | 313708
Old H1 remaining IPC | 1 | 1 | Old H1 remaining IPC1 | 250000
ORA - ZED | 1 | 1 | ORA - ZED1 | 9787286.79
ORA - ZED | 2 | 2 | ORA - ZED2 | 37532508
ORA - ZED | 3 | 3 | ORA - ZED3 | 27896354
ORA - ZED | 4 | 4 | ORA - ZED4 | 20888247.393
ORA - ZED | 5 | 5 | ORA - ZED5 | 33744386.154
ORA - ZED | 6 | 6 | ORA - ZED6 | 4374377.19
ORA - ZED | 7 | 7 | ORA - ZED7 | 5782895.78
ORA - ZED | 8 | 8 | ORA - ZED8 | 24387331.1
ORA - ZED | 9 | 9 | ORA - ZED9 | 22624923.97
ORA - ZED | 10 | 10 | ORA - ZED10 | 29047725.55
ORA - ZED | 20.1 | 20 | ORA - ZED20 | 16483569.19
ORA - ZED | 21 | 21 | ORA - ZED21 | 7443623.53
ORA - ZED | 22 | 22 | ORA - ZED22 | 8098825.75
ORA - ZED | 23 | 23 | ORA - ZED23 | 20215840.09
ORA - ZED | 24 | 24 | ORA - ZED24 | 6648903.39
ORA - ZED | 25 | 25 | ORA - ZED25 | 2e-05
ORA - ZED | 26 | 26 | ORA - ZED26 | 6863669.19
ORA - ZED | 26.1 | 26 | ORA - ZED26 | 1824548.9
ORA - ZED | 26.2 | 26 | ORA - ZED26 | 1119976.03
ORA - ZED | 27 | 27 | ORA - ZED27 | 8872947.14
ORA - ZED | 28 | 28 | ORA - ZED28 | 9105384.7
ORA - ZED | 29 | 29 | ORA - ZED29 | 10687601.99
ORA - ZED | 30 | 30 | ORA - ZED30 | 11585957.67
ORA - ZED | 31 | 31 | ORA - ZED31 | 5000000
ORA - ZED | 31.1 | 31 | ORA - ZED31 | 5253641.2
ORA - ZED | 32 | 32 | ORA - ZED32 | 8010573.17
ORA - ZED | 33 | 33 | ORA - ZED33 | 12164893.39
ORA - ZED | 34 | 34 | ORA - ZED34 | 9568963.5
ORA - ZED | 35 | 35 | ORA - ZED35 | 7391485.26
ORA - ZED | 36 | 36 | ORA - ZED36 | 7054023.71
ORA - ZED | 37 | 37 | ORA - ZED37 | 23554316.1
ORA - ZED | 38 | 38 | ORA - ZED38 | 17627053.17
ORA - ZED | 39 | 39 | ORA - ZED39 | 7606231.63
ORA - ZED | 40 | 40 | ORA - ZED40 | 3717952.37
ORA - ZED | 41 | 41 | ORA - ZED41 | 4428778.21
ORA - ZED | 42 | 42 | ORA - ZED42 | 70851.77
ORA - ZED | 43 | 43 | ORA - ZED43 | 6004454.53
ORA - ZED - Compansation | 1 | 1 | ORA - ZED - Compansation1 | 12000000
ORA - ZED | 1 | 1 | ORA - ZED1 | 91380773
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 2167633.67
ORA - ZED - Landscape | 2 | 2 | ORA - ZED - Landscape2 | 1719649.2
ORA - ZED - Landscape | 3 | 3 | ORA - ZED - Landscape3 | 1775205.58
ORA - ZED - Landscape | 4 | 4 | ORA - ZED - Landscape4 | 4074938.81
ORA - ZED - Landscape | 5 | 5 | ORA - ZED - Landscape5 | 2726488.3
ORA - ZED - Landscape | 6 | 6 | ORA - ZED - Landscape6 | 3120690.89
ORA - ZED - Landscape | 7 | 7 | ORA - ZED - Landscape7 | 964764.3
ORA - ZED - Landscape | 8 | 8 | ORA - ZED - Landscape8 | 5158038.94
ORA - ZED - Landscape | 9 | 9 | ORA - ZED - Landscape9 | 3636861
ORA - ZED - Landscape | 9.1 | 9 | ORA - ZED - Landscape9 | 226226.97
ORA - ZED - Landscape | 10 | 10 | ORA - ZED - Landscape10 | 6562980.72
ORA - ZED - Landscape | 11 | 11 | ORA - ZED - Landscape11 | 5312426.17
ORA - ZED - Landscape | 12 | 12 | ORA - ZED - Landscape12 | 6030251.47
ORA - ZED - Landscape | 14 | 14 | ORA - ZED - Landscape14 | 868255.79
ORA - ZED - Landscape | 15 | 15 | ORA - ZED - Landscape15 | 3165189.2
ORA - ZED - Landscape | 16 | 16 | ORA - ZED - Landscape16 | 1521916.47
ORA - ZED - Landscape | 17 | 17 | ORA - ZED - Landscape17 | 1313619.66
ORA - ZED - Landscape | 18 | 18 | ORA - ZED - Landscape18 | 975356.43
ORA - ZED - Landscape | 19 | 19 | ORA - ZED - Landscape19 | 618692.48
ORA - ZED - Landscape | 20 | 20 | ORA - ZED - Landscape20 | 1177303.85
ORA - ZED - Landscape | 21 | 21 | ORA - ZED - Landscape21 | 108767.39
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 9635108.4
ORA - ZED | 2 | 2 | ORA - ZED2 | 256451321
ORA - ZED | 3 | 3 | ORA - ZED3 | 50172571.863
ORA - ZED | 4 | 4 | ORA - ZED4 | 25000000
ORA - ZED | 5 | 5 | ORA - ZED5 | 50000000
ORA - ZED | 6 | 6 | ORA - ZED6 | 10000000
ORA - ZED | 7 | 7 | ORA - ZED7 | 5000000
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 14536704.19
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 20471935.63
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 9325142.71
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 28728856.89
ORA - ZED - ph.02 | 5 | 5 | ORA - ZED - ph.025 | 12407121.98
ORA - ZED - ph.02 | 6 | 6 | ORA - ZED - ph.026 | 16610991.38
ORA - ZED - ph.02 | 7 | 7 | ORA - ZED - ph.027 | 8000000
ORA - ZED - ph.02 | 7.1 | 7 | ORA - ZED - ph.027 | 16000000
ORA - ZED - ph.02 | 7.2 | 7 | ORA - ZED - ph.027 | 8100387.28
ORA - ZED - ph.02 | 8 | 8 | ORA - ZED - ph.028 | 8595540.37
ORA - ZED - ph.02 | 9 | 9 | ORA - ZED - ph.029 | 7163536.59
ORA - ZED - ph.02 | 10 | 10 | ORA - ZED - ph.0210 | 20828447.26
ORA - ZED - ph.02 | 11 | 11 | ORA - ZED - ph.0211 | 12170282.5
ORA - ZED - ph.02 | 12 | 12 | ORA - ZED - ph.0212 | 14759397.95
ORA - ZED - ph.02 | 13 | 13 | ORA - ZED - ph.0213 | 13268244.56
ORA - ZED - ph.02 | 14 | 14 | ORA - ZED - ph.0214 | 15256729.38
ORA - ZED - ph.02 | 15 | 15 | ORA - ZED - ph.0215 | 11384143.67
ORA - ZED - ph.02 | 16 | 16 | ORA - ZED - ph.0216 | 9858410.94
ORA - ZED - ph.02 | 17 | 17 | ORA - ZED - ph.0217 | 8988166.12
ORA - ZED - ph.02 | 18 | 18 | ORA - ZED - ph.0218 | 13223027.75
ORA - ZED - ph.02 | 19 | 19 | ORA - ZED - ph.0219 | 6921352.11
ORA - ZED - ph.02 | 20 | 20 | ORA - ZED - ph.0220 | 3038540.29
ORA - ZED - ph.02 | 21 | 21 | ORA - ZED - ph.0221 | 4532160.06
ORA - ZED - ph.02 | 22 | 22 | ORA - ZED - ph.0222 | 8297638.82
ORA - ZED - ph.02 | 23 | 23 | ORA - ZED - ph.0223 | 564270
ORA - ZED - ph.02 | 24 | 24 | ORA - ZED - ph.0224 | 1374587.38
ORA - ZED - ph.02 | 25 | 25 | ORA - ZED - ph.0225 | 996461.29
ORA - ZED - ph.02 | 26 | 26 | ORA - ZED - ph.0226 | 2944524.93
ORA - ZED - ph.02 | 27 | 27 | ORA - ZED - ph.0227 | 5268993.93
ORA - ZED - ph.02 | 28 | 28 | ORA - ZED - ph.0228 | 1922751.71
ORA - ZED - ph.02 | 29 | 29 | ORA - ZED - ph.0229 | 5009481.72
ORA - ZED - ph.02 | 30 | 30 | ORA - ZED - ph.0230 | 73017
ORA - ZED - ph.02 | 31 | 31 | ORA - ZED - ph.0231 | 3717995
ORA - ZED - ph.02 | 32 | 32 | ORA - ZED - ph.0232 | 2836390.67
ORA - ZED - ph.02 | 33 | 33 | ORA - ZED - ph.0233 | 1e-05
ORA - ZED - ph.02 | 34 | 34 | ORA - ZED - ph.0234 | 1e-05
ORA - ZED - ph.02 | 35 | 35 | ORA - ZED - ph.0235 | 1e-05
ORA - ZED - ph.02 | 36 | 36 | ORA - ZED - ph.0236 | 4160916.8
ORA - ZED - ph.02 | 37 | 37 | ORA - ZED - ph.0237 | 8601492.56
ORA - ZED - ph.02 | 38 | 38 | ORA - ZED - ph.0238 | 3811960.86
ORA - ZED - ph.02 - DP | 1 | 1 | ORA - ZED - ph.02 - DP1 | 25000000
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 3000000
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 26000000
ORA - ZED - Social Insurrance | 1 | 1 | ORA - ZED - Social Insurrance1 | 4101935.6
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | PH.2-El Sewedy Uni. - Enabling1 | 2832501.18
PH.2-El Sewedy Uni. - Enabling | 2 | 2 | PH.2-El Sewedy Uni. - Enabling2 | 13318143.89
PH.2-El Sewedy Uni. - Enabling | 3 | 3 | PH.2-El Sewedy Uni. - Enabling3 | 17089175.5
PH.2-El Sewedy Uni. - Enabling | 4 | 4 | PH.2-El Sewedy Uni. - Enabling4 | 14773850.81
PH.2-El Sewedy Uni. - Enabling | 5 | 5 | PH.2-El Sewedy Uni. - Enabling5 | 2392694.9
PH.2-El Sewedy Uni. - Enabling | 6 | 6 | PH.2-El Sewedy Uni. - Enabling6 | 7788095.22
PH.2-El Sewedy Uni. - Enabling | 7 | 7 | PH.2-El Sewedy Uni. - Enabling7 | 3548357.43
PH.2-El Sewedy Uni. - Enabling | 8 | 8 | PH.2-El Sewedy Uni. - Enabling8 | 1607563.1
PH.2-El Sewedy Uni. - Enabling | 9 | 9 | PH.2-El Sewedy Uni. - Enabling9 | 8739144.88
PH.2-El Sewedy Uni. - Enabling | 10 | 10 | PH.2-El Sewedy Uni. - Enabling10 | 7703511.41
PH.2-El Sewedy Uni. - Enabling - Retention release | 1 | 1 | PH.2-El Sewedy Uni. - Enabling - Retention release1 | 2972186.2
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 15636298.9
PH.2-El Sewedy Uni. - Finishes | 1.1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 20000000
PH.2-El Sewedy Uni. - Finishes | 2 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 5698476.15
PH.2-El Sewedy Uni. - Finishes | 2.1 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 21059913.65
PH.2-El Sewedy Uni. - Finishes | 3 | 3 | PH.2-El Sewedy Uni. - Finishes3 | 23262698.8
PH.2-El Sewedy Uni. - Finishes | 4 | 4 | PH.2-El Sewedy Uni. - Finishes4 | 18322600.95
PH.2-El Sewedy Uni. - Finishes | 5 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 10000000
PH.2-El Sewedy Uni. - Finishes | 5.1 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 54006362.98
PH.2-El Sewedy Uni. - Finishes | 6 | 6 | PH.2-El Sewedy Uni. - Finishes6 | 8883254.07
PH.2-El Sewedy Uni. - Finishes | 7 | 7 | PH.2-El Sewedy Uni. - Finishes7 | 25755604.75
PH.2-El Sewedy Uni. - Finishes | 8 | 8 | PH.2-El Sewedy Uni. - Finishes8 | 25127325.53
PH.2-El Sewedy Uni. - Finishes | 9 | 9 | PH.2-El Sewedy Uni. - Finishes9 | 20493846.09
PH.2-El Sewedy Uni. - Finishes | 10 | 10 | PH.2-El Sewedy Uni. - Finishes10 | 9765894.8
PH.2-El Sewedy Uni. - Finishes | 11 | 11 | PH.2-El Sewedy Uni. - Finishes11 | 13851401.63
PH.2-El Sewedy Uni. - Finishes | 12 | 12 | PH.2-El Sewedy Uni. - Finishes12 | 23340124.9
PH.2-El Sewedy Uni. - Finishes | 13 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 10000000
PH.2-El Sewedy Uni. - Finishes | 13.1 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 5069000
PH.2-El Sewedy Uni. - Finishes | 13.2 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 1e-06
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 15000000
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 1 | 1 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance1 | 1023770.56
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 2 | 2 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance2 | 9146959.2
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 3 | 3 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance3 | 11400000
PH.2-El Sewedy Uni. | 1 | 1 | PH.2-El Sewedy Uni.1 | 31397824
PH.2-El Sewedy Uni. | 2 | 2 | PH.2-El Sewedy Uni.2 | 71347886
PI Parks - ELSEWEDY | 1 | 1 | PI Parks - ELSEWEDY1 | 3779007.23
PI Parks - ELSEWEDY | 2 | 2 | PI Parks - ELSEWEDY2 | 3366014.15
PI Parks - ELSEWEDY | 3 | 3 | PI Parks - ELSEWEDY3 | 823701.85
PI Parks - ELSEWEDY | 4 | 4 | PI Parks - ELSEWEDY4 | 2572231.81
PI Parks - ELSEWEDY | 5 | 5 | PI Parks - ELSEWEDY5 | 1175600.49
PI Parks - ELSEWEDY | 6 | 6 | PI Parks - ELSEWEDY6 | 689110.93
PI Parks - ELSEWEDY | 7 | 7 | PI Parks - ELSEWEDY7 | 1209313.47
PI Parks - ELSEWEDY | 8 | 8 | PI Parks - ELSEWEDY8 | 1492654.2
PI Parks - ELSEWEDY | 9 | 9 | PI Parks - ELSEWEDY9 | 1471457.2
PI Parks - ELSEWEDY | 10 | 10 | PI Parks - ELSEWEDY10 | 2470019.34
PI Parks - ELSEWEDY | 11 | 11 | PI Parks - ELSEWEDY11 | 945860.23
PI Parks - ELSEWEDY | 12 | 12 | PI Parks - ELSEWEDY12 | 1347803.37
PI Parks - ELSEWEDY | 13 | 13 | PI Parks - ELSEWEDY13 | 719804.13
PI Parks - ELSEWEDY | 14 | 14 | PI Parks - ELSEWEDY14 | 775351.46
PI Parks - ELSEWEDY | 15 | 15 | PI Parks - ELSEWEDY15 | 4484634.14
PI Parks - ELSEWEDY | 16 | 16 | PI Parks - ELSEWEDY16 | 4125986.43
PI Parks - ELSEWEDY | 17 | 17 | PI Parks - ELSEWEDY17 | 1375431.38
PI Parks - ELSEWEDY | 18 | 18 | PI Parks - ELSEWEDY18 | 3699864.67
PI Parks - ELSEWEDY | 19 | 19 | PI Parks - ELSEWEDY19 | 2311261.81
PI Parks - ELSEWEDY | 20 | 20 | PI Parks - ELSEWEDY20 | 1466574.4
PI Parks - ELSEWEDY | 21 | 21 | PI Parks - ELSEWEDY21 | 4361327.46
PI Parks - ELSEWEDY | 21.1 | 21 | PI Parks - ELSEWEDY21 | 972238.28
PI Parks - MEP | 1 | 1 | PI Parks - MEP1 | 7818631.64
PI Parks - MEP | 2 | 2 | PI Parks - MEP2 | 3907009.94
PI Parks - MEP | 3 | 3 | PI Parks - MEP3 | 3921714.73
PI Parks - MEP | 4 | 4 | PI Parks - MEP4 | 3366511.48
PI Parks - MEP | 5 | 5 | PI Parks - MEP5 | 6350059.5
PI Parks - MEP | 6 | 6 | PI Parks - MEP6 | 919139.23
PI Parks - MEP | 7 | 7 | PI Parks - MEP7 | 2661364.08
PI Parks - MEP | 8 | 8 | PI Parks - MEP8 | 1478131.5
PI Parks - MEP | 9 | 9 | PI Parks - MEP9 | 4813799.42
PI Parks - MEP1 | 1 | 1 | PI Parks - MEP11 | 5000000
PI Parks - MEP2 | 2 | 2 | PI Parks - MEP22 | 7600000
PK #107 | 8 | 8 | PK #1078 | 3005745.85
PK #107 | 9 | 9 | PK #1079 | 1418090.5
PK #107 | 10 | 10 | PK #10710 | 1453205.38
PK #107 | 11 | 11 | PK #10711 | 2354508.52
PK #107 | 12 | 12 | PK #10712 | 4193998
PK #107 | 13 | 13 | PK #10713 | 3281572.56
PK #107 | 14 | 14 | PK #10714 | 166316.41
PK #107 | 15 | 15 | PK #10715 | 1406606.27
PK #107 | 16 | 16 | PK #10716 | 131256.74
PK #107 | 17 | 17 | PK #10717 | 763627.7
PK #107 | 18 | 18 | PK #10718 | 1341459.14
PK #117 | 1 | 1 | PK #1171 | 4130129.12
PK #117 | 2 | 2 | PK #1172 | 6455421.01
PK #117 | 3 | 3 | PK #1173 | 4502026.51
PK #117 | 4 | 4 | PK #1174 | 3740180.08
PK #117 | 5 | 5 | PK #1175 | 4762507.56
PK #117 | 6 | 6 | PK #1176 | 5347404.79
PK #117 | 7 | 7 | PK #1177 | 118938.86
PK #117 | 8 | 8 | PK #1178 | 3896343.98
PK #117 | 9 | 9 | PK #1179 | 2578109.73
PK #117 | 10 | 10 | PK #11710 | 882296.11
PK #117 | 11 | 11 | PK #11711 | 809762.24
PK #117 | 12 | 12 | PK #11712 | 3376927.91
PK #117 | 13 | 13 | PK #11713 | 3145907.11
PK #117 | 14 | 14 | PK #11714 | 2483342.5
PK #117 - Social Insurance | 1 | 1 | PK #117 - Social Insurance1 | 229049.99
PK #117 - Social Insurance | 2 | 2 | PK #117 - Social Insurance2 | 163866
PK #117 - Social Insurance | 3 | 3 | PK #117 - Social Insurance3 | 56058.22
PK #117 - Social Insurance | 4 | 4 | PK #117 - Social Insurance4 | 57062.55
PK #117 - Social Insurance | 5 | 5 | PK #117 - Social Insurance5 | 285951.45
PK #22 - Social Insurance | 1 | 1 | PK #22 - Social Insurance1 | 263550
PK#22 | 37 | 37 | PK#2237 | 780036
PK#32 | 30 | 30 | PK#3230 | 900093.35
PKG#101 | 1 | 1 | PKG#1011 | 1029594.82
PKG#101 | 2 | 2 | PKG#1012 | 2222206.65
PKG#101 | 3 | 3 | PKG#1013 | 2246109.51
PKG#101 | 4 | 4 | PKG#1014 | 2512749.68
PKG#101 | 5 | 5 | PKG#1015 | 2051541.96
PKG#101 | 6 | 6 | PKG#1016 | 1988552.05
PKG#101 | 7 | 7 | PKG#1017 | 1824097.57
PKG#101 | 8 | 8 | PKG#1018 | 2104893.84
PKG#101 | 9 | 9 | PKG#1019 | 1424816.56
PKG#101 | 10 | 10 | PKG#10110 | 1976416.89
PKG#101 | 11 | 11 | PKG#10111 | 1709961.04
PKG#101 | 12 | 12 | PKG#10112 | 1146998.21
PKG#101 | 13 | 13 | PKG#10113 | 1343055.6
PKG#101 | 14 | 14 | PKG#10114 | 191421.72
PKG#101 | 15 | 15 | PKG#10115 | 303853.8
PKG#101 | 16 | 16 | PKG#10116 | 866491
PKG#101 | 17 | 17 | PKG#10117 | 3321316.23
PKG#101 | 18 | 18 | PKG#10118 | 1192690.23
PKG#101 | 19 | 19 | PKG#10119 | 596242.89
PKG#101 | 20 | 20 | PKG#10120 | 759353.32
PKG#101 | 21 | 21 | PKG#10121 | 1584188.58
PKG#101 | 22 | 22 | PKG#10122 | 594123.32
PKG#101 | 23 | 23 | PKG#10123 | 189091.52
PKG#101 | 24 | 24 | PKG#10124 | 546994.62
PKG#101- Social Insurance | 1 | 1 | PKG#101- Social Insurance1 | 877190.31
PKG#101- Social Insurance | 2 | 2 | PKG#101- Social Insurance2 | 693232.98
PKG#101 | 1 | 1 | PKG#1011 | 8723141
PKG#101-VO1&VO2 AP | 1 | 1 | PKG#101-VO1&VO2 AP1 | 7091710.52
PKG#144 | 2 | 2 | PKG#1442 | 2532120.6
PKG#144 | 3 | 3 | PKG#1443 | 6189125.05
PKG#144 | 4 | 4 | PKG#1444 | 6887337.01
PKG#144 | 5 | 5 | PKG#1445 | 7206339.73
PKG#144 | 6 | 6 | PKG#1446 | 14929468.44
PKG#144 | 7 | 7 | PKG#1447 | 12477244.23
PKG#144 | 8 | 8 | PKG#1448 | 8906660.63
PKG#144 | 9 | 9 | PKG#1449 | 9782161.34
PKG#144 | 10 | 10 | PKG#14410 | 11074114.43
PKG#144 | 11 | 11 | PKG#14411 | 7386054.95
PKG#144 | 12 | 12 | PKG#14412 | 15000000
PKG#144 | 12.1 | 12 | PKG#14412 | 6073691.31
PKG#144 | 13 | 13 | PKG#14413 | 14000000
PKG#144 | 14 | 14 | PKG#14414 | 10173240.83
PKG#144 | 15 | 15 | PKG#14415 | 9960243.27
PKG#144 | 16 | 16 | PKG#14416 | 1116473.97
PKG#144 - Social Insurance | 1 | 1 | PKG#144 - Social Insurance1 | 216614.52
PKG#144 - Social Insurance | 2 | 2 | PKG#144 - Social Insurance2 | 4748411.06
PKG#144 - Social Insurance | 3 | 3 | PKG#144 - Social Insurance3 | 506192.12
PKG#144 - Social Insurance | 4 | 4 | PKG#144 - Social Insurance4 | 687983.17
PKG#144 - Social Insurance | 5 | 5 | PKG#144 - Social Insurance5 | 2262789.43
PKG#144 - Social Insurance | 6 | 6 | PKG#144 - Social Insurance6 | 1430834.93
PKG#144 - Social Insurance | 7 | 7 | PKG#144 - Social Insurance7 | 596740.76
PKG#144 - Social Insurance | 8 | 8 | PKG#144 - Social Insurance8 | 342218.65
PKG#144 | 1 | 1 | PKG#1441 | 24600000
PKG#162 | 2 | 2 | PKG#1622 | 7794726.52
PKG#162 | 3 | 3 | PKG#1623 | 5119599.34
PKG#162 | 4 | 4 | PKG#1624 | 6336538.23
PKG#162 | 5 | 5 | PKG#1625 | 6124877.69
PKG#162 | 6 | 6 | PKG#1626 | 4824045.39
PKG#162 | 7 | 7 | PKG#1627 | 7215874.2121
PKG#162 | 8 | 8 | PKG#1628 | 9432027.72
PKG#162 | 9 | 9 | PKG#1629 | 9889305
PKG#162 | 10 | 10 | PKG#16210 | 13282474.2108
PKG#162 | 11 | 11 | PKG#16211 | 7840185.48
PKG#162 | 12 | 12 | PKG#16212 | 4608392
PKG#162 | 13 | 13 | PKG#16213 | 3429815.246
PKG#162 | 14 | 14 | PKG#16214 | 502581.43
PKG#162 | 15 | 15 | PKG#16215 | 3999402.59
PKG#162- Social Insurance | 1 | 1 | PKG#162- Social Insurance1 | 829293.83
PKG#162- Social Insurance | 2 | 2 | PKG#162- Social Insurance2 | 1584302
PKG#162- Social Insurance | 3 | 3 | PKG#162- Social Insurance3 | 1223560.05
PKG#162- Social Insurance | 4 | 4 | PKG#162- Social Insurance4 | 760409.01
PKG#162- Social Insurance | 5 | 5 | PKG#162- Social Insurance5 | 438178.63
PKG#162- Social Insurance | 6 | 6 | PKG#162- Social Insurance6 | 37250.26
PKG#162 | 1 | 1 | PKG#1621 | 7681619.5
PKG#163 | 2 | 2 | PKG#1632 | 1068966.43
PKG#163 | 3 | 3 | PKG#1633 | 2977091.11
PKG#163 | 4 | 4 | PKG#1634 | 6845695.77
PKG#163 | 5 | 5 | PKG#1635 | 3782501.29
PKG#163 | 6 | 6 | PKG#1636 | 6255172.17
PKG#163 | 7 | 7 | PKG#1637 | 4922193.5
PKG#163 | 8 | 8 | PKG#1638 | 6050639.77
PKG#163 | 9 | 9 | PKG#1639 | 4602212.16
PKG#163 | 10 | 10 | PKG#16310 | 2532838.57
PKG#163 | 11 | 11 | PKG#16311 | 3799097.57
PKG#163 | 12 | 12 | PKG#16312 | 2215480.09
PKG#163 | 13 | 13 | PKG#16313 | 3821253.39
PKG#163 | 14 | 14 | PKG#16314 | 10697999.42
PKG#163 | 15 | 15 | PKG#16315 | 4024676.65
PKG#163 | 16 | 16 | PKG#16316 | 3611195.74
PKG#163 | 17 | 17 | PKG#16317 | 2445757.34
PKG#163 | 18 | 18 | PKG#16318 | 2445757.34
PKG#163 | 19 | 19 | PKG#16319 | 6520369.14
PKG#163 | 20 | 20 | PKG#16320 | 3715617.2
PKG#163 | 21 | 21 | PKG#16321 | 5322260.63
PKG#163 | 22 | 22 | PKG#16322 | 2261775.79
PKG#163 | 23 | 23 | PKG#16323 | 3449740.5053
PKG#163 | 24 | 24 | PKG#16324 | 5681606.5237
PKG#163 | 25 | 25 | PKG#16325 | 11730565.831
PKG#163 | 26 | 26 | PKG#16326 | 6014332.37
PKG#163 | 27 | 27 | PKG#16327 | 3457484.33
PKG#163 | 28 | 28 | PKG#16328 | 18331730.1
PKG#163 | 29 | 29 | PKG#16329 | 18785649.76
PKG#163 | 30 | 30 | PKG#16330 | 3193802.31
PKG#163 | 31 | 31 | PKG#16331 | 1079324.09
PKG#163 | 32 | 32 | PKG#16332 | 4562478.02
PKG#163 | 33 | 33 | PKG#16333 | 0.0001
PKG#163 | 34 | 34 | PKG#16334 | 0.0001
PKG#163 | 35 | 35 | PKG#16335 | 0.0001
PKG#163- Social Insurance | 1 | 1 | PKG#163- Social Insurance1 | 78430
PKG#163- Social Insurance | 2 | 2 | PKG#163- Social Insurance2 | 720699.2
PKG#163- Social Insurance | 3 | 3 | PKG#163- Social Insurance3 | 277522.63
PKG#163- Social Insurance | 4 | 4 | PKG#163- Social Insurance4 | 451906.96
PKG#163- Social Insurance | 5 | 5 | PKG#163- Social Insurance5 | 754870.94
PKG#163- Social Insurance | 6 | 6 | PKG#163- Social Insurance6 | 961013.69
PKG#163- Social Insurance | 7 | 7 | PKG#163- Social Insurance7 | 275560.66
PKG#163- Social Insurance | 8 | 8 | PKG#163- Social Insurance8 | 434454.78
PKG#163- Social Insurance | 9 | 9 | PKG#163- Social Insurance9 | 2963675.17
PKG#163- Social Insurance | 10 | 10 | PKG#163- Social Insurance10 | 258797.58
PKG#163 | 1 | 1 | PKG#1631 | 24950583
PKG#177 | 2 | 2 | PKG#1772 | 10240448.36
PKG#177 | 3 | 3 | PKG#1773 | 3893019.54
PKG#177 | 4 | 4 | PKG#1774 | 4139690.65
PKG#177 | 5 | 5 | PKG#1775 | 1890262.73
PKG#177 | 6 | 6 | PKG#1776 | 2069539.45
PKG#177 | 7 | 7 | PKG#1777 | 30000000
PKG#177 | 8 | 8 | PKG#1778 | 6325726.09
PKG#177 | 9 | 9 | PKG#1779 | 1386804.78
PKG#177 | 10 | 10 | PKG#17710 | 1031892.42
PKG#177 | 11 | 11 | PKG#17711 | 1623911.78
PKG#177 | 12 | 12 | PKG#17712 | 11867471.98
PKG#177 | 13 | 13 | PKG#17713 | 4287396.18
PKG#177 | 14 | 14 | PKG#17714 | 3654358.5
PKG#177 | 15 | 15 | PKG#17715 | 30000000
PKG#177 | 16 | 16 | PKG#17716 | 8978914.16
PKG#177 | 17 | 17 | PKG#17717 | 311248.17
PKG#177 | 18 | 18 | PKG#17718 | 15059090.32
PKG#177 | 19 | 19 | PKG#17719 | 6143418.31
PKG#177 | 20 | 20 | PKG#17720 | 7621726.83
PKG#177 | 21 | 21 | PKG#17721 | 5553244.96
PKG#177 | 22 | 22 | PKG#17722 | 3436603.03
PKG#177 | 23 | 23 | PKG#17723 | 4324164.09
PKG#177 | 24 | 24 | PKG#17724 | 4835218.42
PKG#177 | 25 | 25 | PKG#17725 | 4062657.22
PKG#177 | 26 | 26 | PKG#17726 | 30000000
PKG#177 | 27 | 27 | PKG#17727 | 1920749.49
PKG#177 | 28 | 28 | PKG#17728 | 3761281.17
PKG#177 | 29 | 29 | PKG#17729 | 30000000
PKG#177 | 30 | 30 | PKG#17730 | 11174297.33
PKG#177 | 31 | 31 | PKG#17731 | 20000000
PKG#177 | 32 | 32 | PKG#17732 | 9586612.72
PKG#177 | 33 | 33 | PKG#17733 | 9774603.63
PKG#177 | 34 | 34 | PKG#17734 | 3243420.79
PKG#177 | 35 | 35 | PKG#17735 | 14874314
PKG#177 | 36 | 36 | PKG#17736 | 32974130.9
PKG#177 | 37 | 37 | PKG#17737 | 2963171.82
PKG#177 | 38 | 38 | PKG#17738 | 40830987.19
PKG#177 | 39 | 39 | PKG#17739 | 24380106.6
PKG#177 | 40 | 40 | PKG#17740 | 0.0001
PKG#177 | 41 | 41 | PKG#17741 | 1e-05
PKG#177 | 42 | 42 | PKG#17742 | 4198626.99
PKG#177 | 43 | 43 | PKG#17743 | 14488992.22
PKG#177 | 44 | 44 | PKG#17744 | 17144236.06
PKG#177 | 45 | 45 | PKG#17745 | 15002016.49
PKG#177 | 46 | 46 | PKG#17746 | 3048300.98
PKG#177 | 47 | 47 | PKG#17747 | 4274072.25
PKG#177 | 48 | 48 | PKG#17748 | 1e-06
PKG#177 | 49 | 49 | PKG#17749 | 1e-06
PKG#177 | 50 | 50 | PKG#17750 | 1e-06
PKG#177 | 51 | 51 | PKG#17751 | 1e-06
PKG#177 | 52 | 52 | PKG#17752 | 1e-06
PKG#177 | 53 | 53 | PKG#17753 | 1e-06
PKG#177 | 1 | 1 | PKG#1771 | 22337274.9
PKG#177 | 4 | 4 | PKG#1774 | 10000000
PKG#177 | 5 | 5 | PKG#1775 | 10000000
PKG#177 | 6 | 6 | PKG#1776 | 10000000
PKG#177 | 7 | 7 | PKG#1777 | 10000000
PKG#177 | 8 | 8 | PKG#1778 | 10000000
PKG#177 | 9 | 9 | PKG#1779 | 10000000
PKG#177 | 10 | 10 | PKG#17710 | 10000000
PKG#177 | 11 | 11 | PKG#17711 | 10000000
PKG#177 - SWI 07 | 10 | 10 | PKG#177 - SWI 0710 | 1e-05
PKG#177- Social Insurance | 1 | 1 | PKG#177- Social Insurance1 | 1919688.42
PKG#177- Social Insurance | 2 | 2 | PKG#177- Social Insurance2 | 8305203.5
PKG#177- Social Insurance | 3 | 3 | PKG#177- Social Insurance3 | 2456503.82
PKG#177- Social Insurance | 4 | 4 | PKG#177- Social Insurance4 | 8736398.9
PKG#177- Social Insurance | 5 | 5 | PKG#177- Social Insurance5 | 3475892.52
PKG#177- Social Insurance | 6 | 6 | PKG#177- Social Insurance6 | 274089.78
PKG#178 | 2 | 2 | PKG#1782 | 13230338.29
PKG#178 | 3 | 3 | PKG#1783 | 6675236.88
PKG#178 | 4 | 4 | PKG#1784 | 6081013.29
PKG#178 | 5 | 5 | PKG#1785 | 9125492.66
PKG#178 | 6 | 6 | PKG#1786 | 2730279.03
PKG#178 | 7 | 7 | PKG#1787 | 1644401.99
PKG#178 | 8 | 8 | PKG#1788 | 595920.45
PKG#178 | 9 | 9 | PKG#1789 | 289077.6
PKG#178 | 10 | 10 | PKG#17810 | 2235574.97
PKG#178 | 1 | 1 | PKG#1781 | 3747170.2
PKG#178- Social Insurance | 1 | 1 | PKG#178- Social Insurance1 | 1276787.15
PKG#178- Social Insurance | 2 | 2 | PKG#178- Social Insurance2 | 392599.98
PKG#178- Social Insurance | 3 | 3 | PKG#178- Social Insurance3 | 887343.85
PKG#205 | 2 | 2 | PKG#2052 | 1181605.96
PKG#205 | 3 | 3 | PKG#2053 | 1250466.11
PKG#205 | 1 | 1 | PKG#2051 | 1260000
PKG#205-Social Insurance | 1 | 1 | PKG#205-Social Insurance1 | 209129.12
PKG#220B | 2 | 2 | PKG#220B2 | 8261597.76
PKG#220B | 3 | 3 | PKG#220B3 | 5980500.04
PKG#220B | 4 | 4 | PKG#220B4 | 2300000
PKG#220B | 1 | 1 | PKG#220B1 | 7500000
PKG#45 | 46 | 46 | PKG#4546 | 1844931.02
PKG#58 | 22 | 22 | PKG#5822 | 327696.29
PKG#85 | 5 | 5 | PKG#855 | 1729285.15
PKG#85 | 6 | 6 | PKG#856 | 768766.59
PKG#85 | 7 | 7 | PKG#857 | 29830.3
PKG#85 | 8 | 8 | PKG#858 | 1391898.96
PO#11687 | 1 | 1 | PO#116871 | 1090584
PO#11687 | 2 | 2 | PO#116872 | 451528
PO#11687 | 3 | 3 | PO#116873 | 293788
PO#11687 | 5 | 5 | PO#116875 | 343200
Port Said Silos | 1 | 1 | Port Said Silos1 | 5248643
Port Said Silos | 2 | 2 | Port Said Silos2 | 1773106
Port Said Silos | 3 | 3 | Port Said Silos3 | 4623869
Port Said Silos | 4 | 4 | Port Said Silos4 | 2560435
Port Said Silos | 5 | 5 | Port Said Silos5 | 4009921
Port Said Silos | 6 | 6 | Port Said Silos6 | 6842722
Port Said Silos | 7 | 7 | Port Said Silos7 | 3061822
Port Said Silos | 8 | 8 | Port Said Silos8 | 17260533
Port Said Silos | 9 | 9 | Port Said Silos9 | 2370710
Port Said Silos | 10 | 10 | Port Said Silos10 | 6384571
Port Said Silos | 11 | 11 | Port Said Silos11 | 3852337
Port Said Silos | 12 | 12 | Port Said Silos12 | 1587432
Port Said Silos | 13 | 13 | Port Said Silos13 | 460093
Port Said Silos | 14 | 14 | Port Said Silos14 | 2136487
Port Said Silos | 15 | 15 | Port Said Silos15 | 7663669
Port Said Silos | 16 | 16 | Port Said Silos16 | 9649102
Port Said Silos | 17 | 17 | Port Said Silos17 | 5738977
Port Said Silos | 18 | 18 | Port Said Silos18 | 2991787
Port Said Silos | 19 | 19 | Port Said Silos19 | 12748959
Port Said Silos | 20 | 20 | Port Said Silos20 | 6593857
Port Said Silos | 21 | 21 | Port Said Silos21 | 11818794
Port Said Silos | 22 | 22 | Port Said Silos22 | 4826684
Port Said Silos | 23 | 23 | Port Said Silos23 | 2411082.19
Port Said Silos | 24 | 24 | Port Said Silos24 | 3306186
Port Said Silos | 25 | 25 | Port Said Silos25 | 3280048
Port Said Silos | 26 | 26 | Port Said Silos26 | 426108
Port Said Silos | 28 | 28 | Port Said Silos28 | 1239632
Port Said Silos | 29 | 29 | Port Said Silos29 | 337130
Port Said Silos | 30 | 30 | Port Said Silos30 | 100641
Port Said Silos | 31 | 31 | Port Said Silos31 | 727554
Port Said Silos | 32 | 32 | Port Said Silos32 | 2193035.35
Port Said Silos | 33 | 33 | Port Said Silos33 | 2711136
Port Said Silos - Foreigner Supply | 1 | 1 | Port Said Silos - Foreigner Supply1 | 5206992
Port Said Silos - Foreigner Supply | 2 | 2 | Port Said Silos - Foreigner Supply2 | 775509.45
Port Said Silos - Local Supply | 1 | 1 | Port Said Silos - Local Supply1 | 655657.61
Port Said Silos - Local Supply | 2 | 2 | Port Said Silos - Local Supply2 | 1162711.94
Port Said Silos - Local Supply | 3 | 3 | Port Said Silos - Local Supply3 | 2307930.88
Port Said Silos - Local Supply | 4 | 4 | Port Said Silos - Local Supply4 | 3416710
Port Said Silos - Local Supply | 5 | 5 | Port Said Silos - Local Supply5 | 2565984
Port Said Silos - Local Supply | 6 | 6 | Port Said Silos - Local Supply6 | 833240
Port Said Silos - Local Supply | 7 | 7 | Port Said Silos - Local Supply7 | 4345468
Port Said Silos - Local Supply | 8 | 8 | Port Said Silos - Local Supply8 | 1794648.84
Port Said Silos - Local Supply | 9 | 9 | Port Said Silos - Local Supply9 | 2529147
Port Said Silos - Local Supply | 10 | 10 | Port Said Silos - Local Supply10 | 494192
Port Said Silos - Local Supply | 11 | 11 | Port Said Silos - Local Supply11 | 833789.82
Port Said Silos | 1 | 1 | Port Said Silos1 | 26540249.4
Port Said Silos | 2 | 2 | Port Said Silos2 | 15000000
Port Said Silos | 1 | 1 | Port Said Silos1 | 6000000
Port Said Silos | 2 | 2 | Port Said Silos2 | 5000000
Port Said Silos | 3 | 3 | Port Said Silos3 | 10000000
Port Said Silos | 4 | 4 | Port Said Silos4 | 20000000
Port Said Silos | 5 | 5 | Port Said Silos5 | 10000000
Port Said Silos | 6 | 6 | Port Said Silos6 | 15000000
Port Said Silos-Social Insurrance | 1 | 1 | Port Said Silos-Social Insurrance1 | 2127569.59
Port Said Silos-Social Insurrance | 2 | 2 | Port Said Silos-Social Insurrance2 | 411364.07
Port Said Silos-Social Insurrance | 3 | 3 | Port Said Silos-Social Insurrance3 | 653360.08
Port Said Silos-Social Insurrance | 4 | 4 | Port Said Silos-Social Insurrance4 | 2773108
Port Said Silos-Social Insurrance | 5 | 5 | Port Said Silos-Social Insurrance5 | 344418
Port Said Silos-Social Insurrance | 6 | 6 | Port Said Silos-Social Insurrance6 | 1595672
Port Said Silos-Social Insurrance | 7 | 7 | Port Said Silos-Social Insurrance7 | 440773.7
Port Said Silos-Social Insurrance | 8 | 8 | Port Said Silos-Social Insurrance8 | 585270
Port Said Silos-Social Insurrance | 9 | 9 | Port Said Silos-Social Insurrance9 | 2996951.24
Port Said Silos-Social Insurrance | 10 | 10 | Port Said Silos-Social Insurrance10 | 999516
Port Said Silos-Social Insurrance | 11 | 11 | Port Said Silos-Social Insurrance11 | 1556882.52
PSP Substation | 2 | 2 | PSP Substation2 | 1160599
PSP Substation | 3 | 3 | PSP Substation3 | 1834172.07
PSP Substation | 4 | 4 | PSP Substation4 | 1268627.7
PSP Substation | 5 | 5 | PSP Substation5 | 3991290.99
PSP Substation | 6 | 6 | PSP Substation6 | 3047586.1
PSP Substation | 7 | 7 | PSP Substation7 | 1780094.35
PSP Substation | 8 | 8 | PSP Substation8 | 1829713.21
PSP Substation | 9 | 9 | PSP Substation9 | 1314287.28
PSP Substation | 10 | 10 | PSP Substation10 | 3264225.8
PSP Substation | 11 | 11 | PSP Substation11 | 2606365.14
PSP Substation | 12 | 12 | PSP Substation12 | 28515
PSP Substation - Beni Suef | 29 | 29 | PSP Substation - Beni Suef29 | 4326586.5
PSP Substation | 1 | 1 | PSP Substation1 | 6647052.2
PSP Substation-Retention | 1 | 1 | PSP Substation-Retention1 | 597560.88
PSP Substation-Retention | 2 | 2 | PSP Substation-Retention2 | 480264.83
PSP Substation-Retention | 3 | 3 | PSP Substation-Retention3 | 536537.44
PSP Substation-Retention | 4 | 4 | PSP Substation-Retention4 | 1617088.7
Rabigh Ext. - Piles | 1 | 1 | Rabigh Ext. - Piles1 | 947881.6
Rabigh Ext. - Piles | 2 | 2 | Rabigh Ext. - Piles2 | 1174037
Rabigh Ext. - Piles | 3 | 3 | Rabigh Ext. - Piles3 | 966227
Rabigh Ext. - Piles | 4 | 4 | Rabigh Ext. - Piles4 | 1787056
Rabigh Ext. - Piles | 5 | 5 | Rabigh Ext. - Piles5 | 1130623
Rabigh Ext. - Piles | 6 | 6 | Rabigh Ext. - Piles6 | 2013847.54
Rabigh Ext. - Piles- DP | 1 | 1 | Rabigh Ext. - Piles- DP1 | 195500
Rabigh Ext. - Piles- DP | 2 | 2 | Rabigh Ext. - Piles- DP2 | 5181540
Rabigh Ext. -Building | 1 | 1 | Rabigh Ext. -Building1 | 2660254.84
Rabigh Ext. -Building | 2 | 2 | Rabigh Ext. -Building2 | 4708047.77
Rabigh Ext. -Building- DP | 1 | 1 | Rabigh Ext. -Building- DP1 | 10000000
Rabigh Ext. -Building- DP | 2 | 2 | Rabigh Ext. -Building- DP2 | 5000000
Rabigh Ext. -Building- DP | 3 | 3 | Rabigh Ext. -Building- DP3 | 49209592.04
Radamis-Concrete | 1 | 1 | Radamis-Concrete1 | 10000000
Radamis-Concrete | 2 | 2 | Radamis-Concrete2 | 10000000
Radamis-H1 | 1 | 1 | Radamis-H11 | 5000000
Radamis-H1 | 2 | 2 | Radamis-H12 | 3000000
Radamis-H1 | 3 | 3 | Radamis-H13 | 5000000
Radamis-H1 | 4 | 4 | Radamis-H14 | 3000000
Radamis-H1 | 5 | 5 | Radamis-H15 | 10000000
Radamis-H1 | 6 | 6 | Radamis-H16 | 10000000
Radamis-H1 | 7 | 7 | Radamis-H17 | 5000000
Radamis-H1 | 8 | 8 | Radamis-H18 | 10000000
Radamis-H1 | 9 | 9 | Radamis-H19 | 10000000
Radamis-H1 | 10 | 10 | Radamis-H110 | 10000000
Radamis-H1 | 11 | 11 | Radamis-H111 | 15000000
Radamis-H1 | 13 | 13 | Radamis-H113 | 10000000
Radamis-H1 | 15 | 15 | Radamis-H115 | 10000000
Radamis-H1 | 16 | 16 | Radamis-H116 | 15000000
Radamis-H1 | 17 | 17 | Radamis-H117 | 18000000
Radamis-H1 | 18 | 18 | Radamis-H118 | 10000000
Radamis-H1 | 19 | 19 | Radamis-H119 | 16000000
Radamis-H1 | 20 | 20 | Radamis-H120 | 10000000
Radamis-H1 | 21 | 21 | Radamis-H121 | 10000000
Radamis-H1 | 22 | 22 | Radamis-H122 | 10000000
Radamis-H1 | 23 | 23 | Radamis-H123 | 10000000
Radamis-H1 | 24 | 24 | Radamis-H124 | 10000000
Radamis-H1 | 25 | 25 | Radamis-H125 | 10000000
Radamis-H1 | 26 | 26 | Radamis-H126 | 10000000
Radamis-H1 | 27 | 27 | Radamis-H127 | 10000000
Radamis-H1 | 28 | 28 | Radamis-H128 | 10000000
Radamis-H1 | 29 | 29 | Radamis-H129 | 10000000
Radamis-H1 | 30 | 30 | Radamis-H130 | 10000000
Radamis-H1 | 31 | 31 | Radamis-H131 | 20000000
Radamis-H1 | 32 | 32 | Radamis-H132 | 30000000
Radamis-H1 | 33 | 33 | Radamis-H133 | 30000000
Radamis-H1 | 34 | 34 | Radamis-H134 | 10000000
Radamis-H1 | 35 | 35 | Radamis-H135 | 20000000
Radamis-H1 | 36 | 36 | Radamis-H136 | 25000000
Radamis-H1 | 37 | 37 | Radamis-H137 | 20000000
Radamis-H1 | 38 | 38 | Radamis-H138 | 10000000
Radamis-H1 | 39 | 39 | Radamis-H139 | 20000000
Radamis-H1 | 40 | 40 | Radamis-H140 | 20000000
Radamis-Rooms Fitout | 1 | 1 | Radamis-Rooms Fitout1 | 250000
Radamis-Rooms Fitout | 2 | 2 | Radamis-Rooms Fitout2 | 500000
Radamis-Rooms Fitout | 3 | 3 | Radamis-Rooms Fitout3 | 15000000
Radamis-Rooms Fitout | 4 | 4 | Radamis-Rooms Fitout4 | 4000000
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 2918717
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 2114752.93
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 2300000
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 2300000
Red Sea Museum | 3 | 3 | Red Sea Museum3 | 4443406
Ring Road - El Marg | 1 | 1 | Ring Road - El Marg1 | 45719198.4
Ring Road - El Marg | 2 | 2 | Ring Road - El Marg2 | 9576635.3
Ring Road - El Marg | 3 | 3 | Ring Road - El Marg3 | 13773926.1
Ring Road - El Marg | 4 | 4 | Ring Road - El Marg4 | 4525661.3
Ring Road - El Marg | 5 | 5 | Ring Road - El Marg5 | 2097964.3
Ring Road - El Marg | 6 | 6 | Ring Road - El Marg6 | 1156719
Ring Road - El Marg | 7 | 7 | Ring Road - El Marg7 | 2151897.3
Ring Road - El Marg | 8 | 8 | Ring Road - El Marg8 | 3742254.85
Ring Road - El Marg | 9 | 9 | Ring Road - El Marg9 | 4020500.85
Ring Road - El Marg | 10 | 10 | Ring Road - El Marg10 | 2795847.4
Ring Road - El Marg | 11 | 11 | Ring Road - El Marg11 | 0.0001
Ring Road - El Marg | 12 | 12 | Ring Road - El Marg12 | 0.0001
Ring Road - El Marg | 13 | 13 | Ring Road - El Marg13 | 0.0001
Ring Road - El Marg - Retention Release | 1 | 1 | Ring Road - El Marg - Retention Release1 | 1436312.4
Ring Road - Mounib | 1 | 1 | Ring Road - Mounib1 | 26333646.7391
Ring Road - Mounib | 2 | 2 | Ring Road - Mounib2 | 7157243.6
Ring Road - Mounib | 3 | 3 | Ring Road - Mounib3 | 10759736.15
Ring Road - Mounib | 4 | 4 | Ring Road - Mounib4 | 4521989.75
Ring Road - Mounib | 5 | 5 | Ring Road - Mounib5 | 6026340.35
Ring Road - Mounib | 6 | 6 | Ring Road - Mounib6 | 4751540.0144
Ring Road - Mounib | 7 | 7 | Ring Road - Mounib7 | 3640291.7356
Ring Road - Mounib | 8 | 8 | Ring Road - Mounib8 | 2701161.75
Ring Road - Mounib | 9 | 9 | Ring Road - Mounib9 | 3856121.55
Ring Road - Mounib | 10 | 10 | Ring Road - Mounib10 | 10942755.35
Ring Road - Mounib | 11 | 11 | Ring Road - Mounib11 | 2713820.35
Ring Road - Mounib | 11.1 | 11 | Ring Road - Mounib11 | 994575.65
Ring Road - Mounib | 12 | 12 | Ring Road - Mounib12 | 14886673.24
Ring Road - Mounib | 13 | 13 | Ring Road - Mounib13 | 4632929.96
Ring Road - Mounib | 13.1 | 13 | Ring Road - Mounib13 | 21269971.05
Ring Road - Mounib | 13.2 | 13 | Ring Road - Mounib13 | 6375786
Ring Road - Mounib | 13.3 | 13 | Ring Road - Mounib13 | 719946.2
Ring Road - Mounib | 14 | 14 | Ring Road - Mounib14 | 5086863.5
Ring Road - Mounib | 14.1 | 14 | Ring Road - Mounib14 | 9870444.4
Ring Road - Mounib | 15 | 15 | Ring Road - Mounib15 | 10573632.35
Ring Road - Mounib | 15.1 | 15 | Ring Road - Mounib15 | 376461.75
Ring Road - Mounib | 16 | 16 | Ring Road - Mounib16 | 96448162.4
Ring Road - Mounib | 16.1 | 16 | Ring Road - Mounib16 | 35042549.45
Ring Road - Mounib | 17 | 17 | Ring Road - Mounib17 | 1170803.2
Ring Road - Mounib | 18 | 18 | Ring Road - Mounib18 | 2897048.5
Ring Road - Mounib | 19 | 19 | Ring Road - Mounib19 | 1351162.1
Ring Road - Mounib - refund | 1 | 1 | Ring Road - Mounib - refund1 | 11410289.1
Ring Road - Mounib - Social Insurance | 1 | 1 | Ring Road - Mounib - Social Insurance1 | 337945.75
RO Apply -Mech- SSC | 1 | 1 | RO Apply -Mech- SSC1 | 1730229.07
RO Apply -Mech- SSC | 2 | 2 | RO Apply -Mech- SSC2 | 1e-05
RO Apply -Mech- SSC | 4 | 4 | RO Apply -Mech- SSC4 | 0.001
RO - Supply - Electric | 1 | 1 | RO - Supply - Electric1 | 1e-05
RO - Supply - Electric | 2 | 2 | RO - Supply - Electric2 | 1e-05
RO - Supply - Electric | 3 | 3 | RO - Supply - Electric3 | 2225665.9095
RO Supply -Mech- SSC | 1 | 1 | RO Supply -Mech- SSC1 | 13698304.23
RO Supply -Mech- SSC | 2 | 2 | RO Supply -Mech- SSC2 | 1574191.94
RO Supply -Mech- SSC | 3 | 3 | RO Supply -Mech- SSC3 | 8116147.9035
RO Supply -Mech- SSC | 4 | 4 | RO Supply -Mech- SSC4 | 6312150
RO Supply -Mech- SSC | 5 | 5 | RO Supply -Mech- SSC5 | 2149698.33
RO Pump room - SSC - price diff. | 1 | 1 | RO Pump room - SSC - price diff.1 | 15849915.53
RO Pump room - SSC - price diff. | 2 | 2 | RO Pump room - SSC - price diff.2 | 918959
RO Pump room - SSC - price diff. | 3 | 3 | RO Pump room - SSC - price diff.3 | 9400325.92
RO Pump room - SSC - price diff. | 4 | 4 | RO Pump room - SSC - price diff.4 | 7294244.17
RO.2 | 1 | 1 | RO.21 | 1e-05
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 10000000
Rolling Mill #4-TRAESUEZ | 1.1 | 1 | Rolling Mill #4-TRAESUEZ1 | 6966551.51
Rolling Mill #4-TRAESUEZ | 2 | 2 | Rolling Mill #4-TRAESUEZ2 | 12106800.04
Rolling Mill #4-TRAESUEZ | 3 | 3 | Rolling Mill #4-TRAESUEZ3 | 10231445.3
Rolling Mill #4-TRAESUEZ | 4 | 4 | Rolling Mill #4-TRAESUEZ4 | 6596541.38
Rolling Mill #4-TRAESUEZ | 5 | 5 | Rolling Mill #4-TRAESUEZ5 | 9293714.72
Rolling Mill #4-TRAESUEZ | 6 | 6 | Rolling Mill #4-TRAESUEZ6 | 4622509.21
Rolling Mill #4-TRAESUEZ | 7 | 7 | Rolling Mill #4-TRAESUEZ7 | 13289718.96
Rolling Mill #4-TRAESUEZ | 8 | 8 | Rolling Mill #4-TRAESUEZ8 | 16970562.32
Rolling Mill #4-TRAESUEZ | 9 | 9 | Rolling Mill #4-TRAESUEZ9 | 15728855.47
Rolling Mill #4-TRAESUEZ | 10 | 10 | Rolling Mill #4-TRAESUEZ10 | 10380808.5
Rolling Mill #4-TRAESUEZ | 11 | 11 | Rolling Mill #4-TRAESUEZ11 | 9072857.69
Rolling Mill #4-TRAESUEZ | 12 | 12 | Rolling Mill #4-TRAESUEZ12 | 13213191.25
Rolling Mill #4-TRAESUEZ | 13 | 13 | Rolling Mill #4-TRAESUEZ13 | 1e-05
Rolling Mill #4-TRAESUEZ | 14 | 14 | Rolling Mill #4-TRAESUEZ14 | 1e-05
Rolling Mill #4-TRAESUEZ | 15 | 15 | Rolling Mill #4-TRAESUEZ15 | 1e-05
Rolling Mill #4-TRAESUEZ | 16 | 16 | Rolling Mill #4-TRAESUEZ16 | 1e-05
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 108750000
Royal City | 2 | 2 | Royal City2 | 4892835.45
Royal City | 3 | 3 | Royal City3 | 7926742.1
Royal City | 4 | 4 | Royal City4 | 10437271.65
Royal City | 5 | 5 | Royal City5 | 5169557.65
Royal City | 6 | 6 | Royal City6 | 12495801.4
Royal City | 7 | 7 | Royal City7 | 8703262.4
Royal City | 8 | 8 | Royal City8 | 6085844.5
Royal City | 9 | 9 | Royal City9 | 6397146.2
Royal City | 10 | 10 | Royal City10 | 5786688.5
Royal City | 11 | 11 | Royal City11 | 3482306.95
Royal City | 12 | 12 | Royal City12 | 9822648.05
Royal City | 13 | 13 | Royal City13 | 6339338.45
Royal City | 14 | 14 | Royal City14 | 5980045.3
Royal City | 15 | 15 | Royal City15 | 6570751.8
Royal City | 16 | 16 | Royal City16 | 7847127.4
Royal City | 17 | 17 | Royal City17 | 5868379.55
Royal City | 18 | 18 | Royal City18 | 4501953.5
Royal City | 19 | 19 | Royal City19 | 9999974.75
Royal City | 20 | 20 | Royal City20 | 5072118
Royal City | 21 | 21 | Royal City21 | 5000000
Royal City | 22 | 22 | Royal City22 | 16824453.7
Royal City | 23 | 23 | Royal City23 | 6453450.6
Royal City | 24 | 24 | Royal City24 | 9088642.9
Royal City | 25 | 25 | Royal City25 | 9972683.95
Royal City | 26 | 26 | Royal City26 | 8025338.3
Royal City | 27 | 27 | Royal City27 | 5000000
Royal City | 27.1 | 27 | Royal City27 | 5150000
Royal City | 27.2 | 27 | Royal City27 | 1745943.7
Royal City | 28 | 28 | Royal City28 | 7000000
Royal City | 28.1 | 28 | Royal City28 | 3500306.77
Royal City | 29 | 29 | Royal City29 | 12838209.35
Royal City | 30 | 30 | Royal City30 | 7400000
Royal City | 30.1 | 30 | Royal City30 | 2431952.135
Royal City | 31 | 31 | Royal City31 | 2500000
Royal City | 31.1 | 31 | Royal City31 | 3975508.58
Royal City | 32 | 32 | Royal City32 | 2151533.38
Royal City | 33 | 33 | Royal City33 | 5000000
Royal City | 33.1 | 33 | Royal City33 | 4101413.8171
Royal City | 34 | 34 | Royal City34 | 1294144.2829
Royal City | 34.1 | 34 | Royal City34 | 4079298.6432
Royal City | 35 | 35 | Royal City35 | 3237336.5863
Royal City | 36 | 36 | Royal City36 | 1578133.6205
Royal City | 36.1 | 36 | Royal City36 | 3653291.5695
Royal City | 37 | 37 | Royal City37 | 3663343.67
Royal City | 38 | 38 | Royal City38 | 2267127.88
Royal City | 39 | 39 | Royal City39 | 1002773.1926
Royal City | 40 | 40 | Royal City40 | 955713.1379
Royal City | 40.1 | 40 | Royal City40 | 5023973.5321
Royal City | 41 | 41 | Royal City41 | 5714023.3138
Royal City | 42 | 42 | Royal City42 | 15000000
Royal City | 42.1 | 42 | Royal City42 | 4161782.8
Royal City | 42.2 | 42 | Royal City42 | 16000000
Royal City - Landscape | 1 | 1 | Royal City - Landscape1 | 1782000
Royal City - Landscape | 2 | 2 | Royal City - Landscape2 | 4014037.5
Royal City - Landscape | 3 | 3 | Royal City - Landscape3 | 2421804.9
Royal City - Landscape | 4 | 4 | Royal City - Landscape4 | 4390934.75
Royal City - Landscape | 5 | 5 | Royal City - Landscape5 | 7060326.8
Royal City - Landscape | 6 | 6 | Royal City - Landscape6 | 9240902.25
Royal City - Landscape | 7 | 7 | Royal City - Landscape7 | 5000000
Royal City - Landscape | 7.1 | 7 | Royal City - Landscape7 | 1442723.35
Royal City - Landscape | 8 | 8 | Royal City - Landscape8 | 2161790.65
Royal City - Landscape | 8.1 | 8 | Royal City - Landscape8 | 10194453.1
Royal City - Landscape | 9 | 9 | Royal City - Landscape9 | 4886117.91
Royal City - Landscape | 10 | 10 | Royal City - Landscape10 | 2500000
Royal City - Landscape | 10.1 | 10 | Royal City - Landscape10 | 561010.97
Royal City - Landscape | 11 | 11 | Royal City - Landscape11 | 4947910.42
Royal City - Landscape | 12 | 12 | Royal City - Landscape12 | 5000000
Royal City - Landscape | 12.1 | 12 | Royal City - Landscape12 | 2029456.4155
Royal City - Landscape | 13 | 13 | Royal City - Landscape13 | 2173267.6157
Royal City - Landscape | 14 | 14 | Royal City - Landscape14 | 1308214.7555
Royal City - Landscape | 15 | 15 | Royal City - Landscape15 | 2272705.37
Royal City - Landscape | 16 | 16 | Royal City - Landscape16 | 650222.9433
Royal City - Landscape | 17 | 17 | Royal City - Landscape17 | 1288827.45
Royal City - Landscape | 17.1 | 17 | Royal City - Landscape17 | 1531216.7805
Royal City - Landscape | 18 | 18 | Royal City - Landscape18 | 819297.0816
Royal City - Landscape | 19 | 19 | Royal City - Landscape19 | 1116339.8935
Royal City - Landscape | 20 | 20 | Royal City - Landscape20 | 1105876.6944
Royal City - Landscape | 21 | 21 | Royal City - Landscape21 | 520336.7179
Royal City - Landscape | 21.1 | 21 | Royal City - Landscape21 | 2285976.6862
Royal City - Landscape | 22 | 22 | Royal City - Landscape22 | 1838217.2
Royal City - Landscape | 23 | 23 | Royal City - Landscape23 | 9000000
Royal City - Landscape | 23.1 | 23 | Royal City - Landscape23 | 4000000
Royal City 3 | 3 | 3 | Royal City 33 | 20000000
Royal City 4 | 4 | 4 | Royal City 44 | 20093247.4
Royal City1 | 1 | 1 | Royal City11 | 58500000
Royal City2 | 2 | 2 | Royal City22 | 20000000
Saint Gobain Factory | 1 | 1 | Saint Gobain Factory1 | 103530970.24
Saint Gobain Factory | 2 | 2 | Saint Gobain Factory2 | 26538435
SIEMENS - Sokhna | 1 | 1 | SIEMENS - Sokhna1 | 93300000
SIEMENS - Sokhna | 2 | 2 | SIEMENS - Sokhna2 | 3059283.73
SIEMENS - Sokhna | 3 | 3 | SIEMENS - Sokhna3 | 7201577.05
SIEMENS - Sokhna | 4 | 4 | SIEMENS - Sokhna4 | 11065687.7
SIEMENS - Sokhna | 5 | 5 | SIEMENS - Sokhna5 | 13218163.56
SIEMENS - Sokhna | 6 | 6 | SIEMENS - Sokhna6 | 7060448.908
SIEMENS - Sokhna | 7 | 7 | SIEMENS - Sokhna7 | 8833159.82
SIEMENS - Sokhna | 8 | 8 | SIEMENS - Sokhna8 | 12641621.4
SIEMENS - Sokhna | 9 | 9 | SIEMENS - Sokhna9 | 13673026.82
SIEMENS - Sokhna | 10 | 10 | SIEMENS - Sokhna10 | 6271528.33
SIEMENS - Sokhna | 11 | 11 | SIEMENS - Sokhna11 | 5230123.67
SIEMENS - Sokhna | 12 | 12 | SIEMENS - Sokhna12 | 20041232.56
SIEMENS - Sokhna | 13 | 13 | SIEMENS - Sokhna13 | 17822796.65
SIEMENS - Sokhna | 14 | 14 | SIEMENS - Sokhna14 | 20002003.08
SIEMENS - Sokhna | 15 | 15 | SIEMENS - Sokhna15 | 2699428.63
SIEMENS - Sokhna | 16 | 16 | SIEMENS - Sokhna16 | 25271545.73
SIEMENS - Sokhna | 17 | 17 | SIEMENS - Sokhna17 | 20418831.59
SIEMENS - Sokhna | 18 | 18 | SIEMENS - Sokhna18 | 12124718
SIEMENS - Sokhna | 19 | 19 | SIEMENS - Sokhna19 | 25672200.91
SIEMENS - Sokhna | 20 | 20 | SIEMENS - Sokhna20 | 15319191.73
SIEMENS - Sokhna | 21 | 21 | SIEMENS - Sokhna21 | 888628.7
SIEMENS - Sokhna - Bill | 1 | 1 | SIEMENS - Sokhna - Bill1 | 144907
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 2207548.2
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 1e-05
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 | 1e-05
SMP1 - Revamp | 4 | 4 | SMP1 - Revamp4 | 2647384.8437
SMP1 - Revamp | 5 | 5 | SMP1 - Revamp5 | 2853769.6857
SMP1 - Revamp | 6 | 6 | SMP1 - Revamp6 | 6112062.5631
SMP1 - Revamp | 7 | 7 | SMP1 - Revamp7 | 3154540.1
SMP1 - Revamp | 8 | 8 | SMP1 - Revamp8 | 1992085.4366
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 11698500
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 25693427.5
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 | 16806572.5
SMP1 - Shut Down | 1 | 1 | SMP1 - Shut Down1 | 5388381.94
SMP1 - Shut Down | 2 | 2 | SMP1 - Shut Down2 | 15140879.8914
SMP1 - Shut Down | 3 | 3 | SMP1 - Shut Down3 | 8648912.9484
SMP1 - Shut Down- Final Retention | 1 | 1 | SMP1 - Shut Down- Final Retention1 | 2700753.58
SMP2 - Shut Down | 2 | 2 | SMP2 - Shut Down2 | 5426194.9513
SMP2 - Shut Down | 3 | 3 | SMP2 - Shut Down3 | 581185.34
SMP2 - Shut Down- Retention release | 1 | 1 | SMP2 - Shut Down- Retention release1 | 553693.36
SMP2 - Shut Down- V.O | 1 | 1 | SMP2 - Shut Down- V.O1 | 20000000
Sodic Club House | 23 | 23 | Sodic Club House23 | 2727407.25
Sodic Club House | 24 | 24 | Sodic Club House24 | 4528572.66
Sodic Club House | 25 | 25 | Sodic Club House25 | 894280.83
Sodic Club House | 26 | 26 | Sodic Club House26 | 2563543.65
Sodic Club House | 27 | 27 | Sodic Club House27 | 7171420.81
Sodic Club House | 28 | 28 | Sodic Club House28 | 3643251.2
Sodic Club House | 29 | 29 | Sodic Club House29 | 2927170
Sodic Club House | 30 | 30 | Sodic Club House30 | 1523667.33
Sodic Club House | 31 | 31 | Sodic Club House31 | 3752933.22
Sodic Club House | 32 | 32 | Sodic Club House32 | 1851323.25
Sodic Club House | 33 | 33 | Sodic Club House33 | 5028067.13
Sodic Club House | 34 | 34 | Sodic Club House34 | 1372787.19
Sodic Club House | 35 | 35 | Sodic Club House35 | 2061960.96
Sodic Club House | 36 | 36 | Sodic Club House36 | 3000000
Sodic Club House | 36.1 | 36 | Sodic Club House36 | 6516540.66
Sodic Club House | 37 | 37 | Sodic Club House37 | 4028521
Sodic Club House - Social Insurance | 1 | 1 | Sodic Club House - Social Insurance1 | 184729.32
Sodic Club House - Social Insurance | 2 | 2 | Sodic Club House - Social Insurance2 | 503082.9
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 6789620.12
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 15638373.66
Sodic Eastown | 3 | 3 | Sodic Eastown3 | 1574016.18
Sodic Eastown | 4 | 4 | Sodic Eastown4 | 25688338.61
Sodic Eastown | 5 | 5 | Sodic Eastown5 | 37056568.4
Sodic Eastown | 6 | 6 | Sodic Eastown6 | 18000000
Sodic Eastown | 6.1 | 6 | Sodic Eastown6 | 10554847.67
Sodic Eastown | 7 | 7 | Sodic Eastown7 | 35000000
Sodic Eastown | 7.1 | 7 | Sodic Eastown7 | 3197130.95
Sodic Eastown | 8 | 8 | Sodic Eastown8 | 46000000
Sodic Eastown | 8.1 | 8 | Sodic Eastown8 | 9532397.61
Sodic Eastown | 9 | 9 | Sodic Eastown9 | 40504812.26
Sodic Eastown | 10 | 10 | Sodic Eastown10 | 32553581.24
Sodic Eastown | 11 | 11 | Sodic Eastown11 | 27179529.3929
Sodic Eastown | 12 | 12 | Sodic Eastown12 | 19553108.79
Sodic Eastown | 13 | 13 | Sodic Eastown13 | 10000000
Sodic Eastown | 13.1 | 13 | Sodic Eastown13 | 6201534.04
Sodic Eastown | 14 | 14 | Sodic Eastown14 | 15000000
Sodic Eastown | 14.1 | 14 | Sodic Eastown14 | 1537461.58
Sodic Eastown | 15 | 15 | Sodic Eastown15 | 12895954
Sodic Eastown | 16 | 16 | Sodic Eastown16 | 30145771.57
Sodic Eastown | 17 | 17 | Sodic Eastown17 | 20000000
Sodic Eastown | 17.1 | 17 | Sodic Eastown17 | 899381.34
Sodic Eastown | 18 | 18 | Sodic Eastown18 | 15000000
Sodic Eastown | 18.1 | 18 | Sodic Eastown18 | 7406610.78
Sodic Eastown | 19 | 19 | Sodic Eastown19 | 25500000
Sodic Eastown | 19.1 | 19 | Sodic Eastown19 | 8917592.72
Sodic Eastown | 20 | 20 | Sodic Eastown20 | 27000000
Sodic Eastown | 20.1 | 20 | Sodic Eastown20 | 4197031.83
Sodic Eastown | 21 | 21 | Sodic Eastown21 | 25000000
Sodic Eastown | 21.1 | 21 | Sodic Eastown21 | 4743783.32
Sodic Eastown | 22 | 22 | Sodic Eastown22 | 15000000
Sodic Eastown | 22.1 | 22 | Sodic Eastown22 | 4964135.7
Sodic Eastown | 23 | 23 | Sodic Eastown23 | 12000000
Sodic Eastown | 23.1 | 23 | Sodic Eastown23 | 7672746.63
Sodic Eastown | 24 | 24 | Sodic Eastown24 | 12000000
Sodic Eastown | 24.1 | 24 | Sodic Eastown24 | 2713744.17
Sodic Eastown | 25 | 25 | Sodic Eastown25 | 15000000
Sodic Eastown | 25.1 | 25 | Sodic Eastown25 | 3632387.16
Sodic Eastown | 26 | 26 | Sodic Eastown26 | 19000000
Sodic Eastown | 26.1 | 26 | Sodic Eastown26 | 13407888.61
Sodic Eastown | 27 | 27 | Sodic Eastown27 | 19000000
Sodic Eastown | 27.1 | 27 | Sodic Eastown27 | 2101612.82
Sodic Eastown | 28 | 28 | Sodic Eastown28 | 30000000
Sodic Eastown | 28.1 | 28 | Sodic Eastown28 | 11708616.23
Sodic Eastown | 29 | 29 | Sodic Eastown29 | 10880905.48
Sodic Eastown | 30 | 30 | Sodic Eastown30 | 20000000
Sodic Eastown | 30.1 | 30 | Sodic Eastown30 | 5479297.36
Sodic Eastown | 31 | 31 | Sodic Eastown31 | 22493923.41
Sodic Eastown | 32 | 32 | Sodic Eastown32 | 15680621.74
Sodic Eastown | 33 | 33 | Sodic Eastown33 | 19311419.98
Sodic Eastown | 34 | 34 | Sodic Eastown34 | 4602037.61
Sodic Eastown | 35 | 35 | Sodic Eastown35 | 12555804.9
Sodic Eastown | 36 | 36 | Sodic Eastown36 | 2350120
Sodic Eastown | 36.1 | 36 | Sodic Eastown36 | 3904269.49
Sodic Eastown | 37 | 37 | Sodic Eastown37 | 5035428.4
Sodic Eastown | 38 | 38 | Sodic Eastown38 | 2231188
Sodic Eastown | 39 | 39 | Sodic Eastown39 | 17894573
Sodic Eastown - Landscape | 1 | 1 | Sodic Eastown - Landscape1 | 1545976.54
Sodic Eastown - Landscape | 2 | 2 | Sodic Eastown - Landscape2 | 2689319.17
Sodic Eastown - Landscape | 3 | 3 | Sodic Eastown - Landscape3 | 5060960.68
Sodic Eastown - Landscape | 4 | 4 | Sodic Eastown - Landscape4 | 4237695.68
Sodic Eastown - Landscape | 5 | 5 | Sodic Eastown - Landscape5 | 2847434.11
Sodic Eastown - Landscape | 6 | 6 | Sodic Eastown - Landscape6 | 1865468.85
Sodic Eastown - Landscape | 7 | 7 | Sodic Eastown - Landscape7 | 2249247.81
Sodic Eastown - Landscape | 8 | 8 | Sodic Eastown - Landscape8 | 8937999.74
Sodic Eastown - Landscape | 9 | 9 | Sodic Eastown - Landscape9 | 837296.03
Sodic Eastown - Landscape | 10 | 10 | Sodic Eastown - Landscape10 | 2965081
Sodic Eastown - Landscape | 11 | 11 | Sodic Eastown - Landscape11 | 970278.45
Sodic Eastown - Landscape | 12 | 12 | Sodic Eastown - Landscape12 | 2038310.81
Sodic Eastown - Landscape | 13 | 13 | Sodic Eastown - Landscape13 | 4532604.51
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 10000000
Sodic Eastown - Social Insurance | 1 | 1 | Sodic Eastown - Social Insurance1 | 849097.69
Sodic Eastown - Social Insurance | 2 | 2 | Sodic Eastown - Social Insurance2 | 59565.32
Sodic Eastown - Social Insurance | 3 | 3 | Sodic Eastown - Social Insurance3 | 3554660.12
Sodic Eastown - Social Insurance | 4 | 4 | Sodic Eastown - Social Insurance4 | 1311245.56
Sodic Eastown - Social Insurance | 5 | 5 | Sodic Eastown - Social Insurance5 | 2324833
Sodic Eastown - Social Insurance | 6 | 6 | Sodic Eastown - Social Insurance6 | 2884335.94
Sodic Eastown - Social Insurance | 7 | 7 | Sodic Eastown - Social Insurance7 | 1801458.51
Sodic Eastown - Social Insurance | 8 | 8 | Sodic Eastown - Social Insurance8 | 1322438.36
Sodic Eastown - Social Insurance | 9 | 9 | Sodic Eastown - Social Insurance9 | 1754521.36
Sodic Eastown - Social Insurance | 10 | 10 | Sodic Eastown - Social Insurance10 | 862557.37
Sodic Eastown - Social Insurance | 11 | 11 | Sodic Eastown - Social Insurance11 | 2423402.76
Sodic Eastown - Social Insurance | 12 | 12 | Sodic Eastown - Social Insurance12 | 2569099.92
Sodic Eastown - Social Insurance | 13 | 13 | Sodic Eastown - Social Insurance13 | 1513109.68
Sodic Eastown - Social Insurance | 14 | 14 | Sodic Eastown - Social Insurance14 | 1540691.11
Sodic Eastown - Social Insurance | 15 | 15 | Sodic Eastown - Social Insurance15 | 2140215.06
Sodic Eastown - Social Insurance | 16 | 16 | Sodic Eastown - Social Insurance16 | 1796921.66
Sodic Eastown - Social Insurance | 17 | 17 | Sodic Eastown - Social Insurance17 | 1371899.5
Sodic Eastown - Social Insurance | 18 | 18 | Sodic Eastown - Social Insurance18 | 327894.39
Sodic Eastown - Social Insurance | 19 | 19 | Sodic Eastown - Social Insurance19 | 944267.32
Sodic Eastown - Social Insurance | 20 | 20 | Sodic Eastown - Social Insurance20 | 1149200.87
Sodic Eastown - Social Insurance | 21 | 21 | Sodic Eastown - Social Insurance21 | 6876328.15
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 122000000
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 5928168
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 16602157.8
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 19087604.3
Sokhna Port Expansion | 3 | 3 | Sokhna Port Expansion3 | 55802951.65
Sokhna Port Expansion | 4 | 4 | Sokhna Port Expansion4 | 16604871.85
Sokhna Port Expansion | 5 | 5 | Sokhna Port Expansion5 | 24339603.2
Sokhna Port Expansion | 5.1 | 5 | Sokhna Port Expansion5 | 19863057.3
Sokhna Port Expansion | 5.2 | 5 | Sokhna Port Expansion5 | 14812304.05
Sokhna Port Expansion | 6 | 6 | Sokhna Port Expansion6 | 4879591.2
Sokhna Port Expansion | 6.1 | 6 | Sokhna Port Expansion6 | 10735001.15
Sokhna Port Expansion | 6.2 | 6 | Sokhna Port Expansion6 | 10594441
Sokhna Port Expansion | 7 | 7 | Sokhna Port Expansion7 | 36803665.95
Sokhna Port Expansion | 8 | 8 | Sokhna Port Expansion8 | 36284090.45
Sokhna Port Expansion | 9 | 9 | Sokhna Port Expansion9 | 30030028.45
Sokhna Port Expansion | 10 | 10 | Sokhna Port Expansion10 | 27461819.5
Sokhna Port Expansion | 11 | 11 | Sokhna Port Expansion11 | 50769799.2
Sokhna Port Expansion | 12 | 12 | Sokhna Port Expansion12 | 70395885.55
Sokhna Port Expansion | 13 | 13 | Sokhna Port Expansion13 | 491489.95
Sokhna Port Expansion | 14 | 14 | Sokhna Port Expansion14 | 6704080.85
Sokhna Port Expansion | 15 | 15 | Sokhna Port Expansion15 | 4368115.65
Sokhna Port Expansion | 16 | 16 | Sokhna Port Expansion16 | 23966243.5
Sokhna Port Expansion | 17 | 17 | Sokhna Port Expansion17 | 14567572.19
Sokhna Port Expansion | 18 | 18 | Sokhna Port Expansion18 | 14135207.0055
Sokhna Port Expansion | 19 | 19 | Sokhna Port Expansion19 | 10049896.61
Sokhna Port Expansion | 20 | 20 | Sokhna Port Expansion20 | 13204353
Sokhna Port Expansion | 21 | 21 | Sokhna Port Expansion21 | 5788234
Sokhna Port Expansion | 22 | 22 | Sokhna Port Expansion22 | 2510900.431
Sokhna Port Expansion | 23 | 23 | Sokhna Port Expansion23 | 568614.519
Sokhna Port Expansion- 100m | 1 | 1 | Sokhna Port Expansion- 100m1 | 39700885.25
Sokhna Port Expansion- 100m | 2 | 2 | Sokhna Port Expansion- 100m2 | 10628517.75
Sokhna Port Expansion- 100m | 3 | 3 | Sokhna Port Expansion- 100m3 | 10464912.35
Sokhna Port Expansion- 100m | 4 | 4 | Sokhna Port Expansion- 100m4 | 8297916
Sokhna Port Expansion- 100m | 5 | 5 | Sokhna Port Expansion- 100m5 | 3240800
Sokhna Port Expansion- 100m | 6 | 6 | Sokhna Port Expansion- 100m6 | 20436714.5
Sokhna Port Expansion- 100m | 7 | 7 | Sokhna Port Expansion- 100m7 | 3976775.9
Sokhna Port Expansion 100m- Escalation | 1 | 1 | Sokhna Port Expansion 100m- Escalation1 | 11758235
Sokhna Port Expansion 100m- Escalation | 2 | 2 | Sokhna Port Expansion 100m- Escalation2 | 6484391
Sokhna Port Expansion- EDECS | 1 | 1 | Sokhna Port Expansion- EDECS1 | 478776
Sokhna Port Expansion- Escalation | 1 | 1 | Sokhna Port Expansion- Escalation1 | 20947176.65
Sokhna Port Expansion- Escalation | 2 | 2 | Sokhna Port Expansion- Escalation2 | 39132293.55
Sokhna Port Expansion- Escalation | 3 | 3 | Sokhna Port Expansion- Escalation3 | 103409321
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 185016019.2
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 33908706
Sokhna Port Expansion-internal roads | 1 | 1 | Sokhna Port Expansion-internal roads1 | 1800470.45
Sokhna Port Expansion-internal roads | 2 | 2 | Sokhna Port Expansion-internal roads2 | 3219.75
Sports Hall - Civil Works | 3 | 3 | Sports Hall - Civil Works3 | 2493330
Sports Hall - Civil Works | 4 | 4 | Sports Hall - Civil Works4 | 10576930
Sports Hall - Civil Works | 5 | 5 | Sports Hall - Civil Works5 | 17108045
Sports Hall - Civil Works | 6 | 6 | Sports Hall - Civil Works6 | 414025
Sports Hall - Finishes | 1 | 1 | Sports Hall - Finishes1 | 1388840
Sports Hall - Finishes | 2 | 2 | Sports Hall - Finishes2 | 13091760
Sports Hall - Finishes | 3 | 3 | Sports Hall - Finishes3 | 7109625
Sports Hall - Finishes | 4 | 4 | Sports Hall - Finishes4 | 3699060
Sports Hall - Finishes - ADD.01 | 1 | 1 | Sports Hall - Finishes - ADD.011 | 5941290
Sports Hall - Finishes - ADD.01 | 2 | 2 | Sports Hall - Finishes - ADD.012 | 2631750
Sports Hall - Finishes - ADD.01 - Final Retention | 1 | 1 | Sports Hall - Finishes - ADD.01 - Final Retention1 | 790505
Sports Hall - Finishes - Landscape | 1 | 1 | Sports Hall - Finishes - Landscape1 | 0.0003
Sports Hall - Finishes - Landscape - Final Retention | 1 | 1 | Sports Hall - Finishes - Landscape - Final Retention1 | 2595335
Sports Hall - Finishes - Social Insurance | 1 | 1 | Sports Hall - Finishes - Social Insurance1 | 12888786
Sports Hall - MEP | 1 | 1 | Sports Hall - MEP1 | 19417720
Sports Hall - MEP | 2 | 2 | Sports Hall - MEP2 | 1103175
Sports Hall - MEP | 1 | 1 | Sports Hall - MEP1 | 47999995
Sports Hall - MEP - Final Retention | 1 | 1 | Sports Hall - MEP - Final Retention1 | 2580450
Suez Intake & P Stations-ABB apply | 1 | 1 | Suez Intake & P Stations-ABB apply1 | 509186.43
Suez Intake & P Stations-ABB apply | 2 | 2 | Suez Intake & P Stations-ABB apply2 | 988420.71
Suez Intake & P Stations-ABB apply | 3 | 3 | Suez Intake & P Stations-ABB apply3 | 1048324.9964
Suez Intake & P Stations-ABB supply | 1 | 1 | Suez Intake & P Stations-ABB supply1 | 5134498.57
Suez Intake & P Stations-ABB supply | 2 | 2 | Suez Intake & P Stations-ABB supply2 | 7437727.82
Suez Intake & P Stations-ABB supply | 3 | 3 | Suez Intake & P Stations-ABB supply3 | 814872.95
Suez Intake & P Stations-ABB supply | 4 | 4 | Suez Intake & P Stations-ABB supply4 | 3667977.98
Suez Intake & P Stations-ABB supply | 8 | 8 | Suez Intake & P Stations-ABB supply8 | 1e-05
Suez Intake & P Stations-ABB-Escalation | 1 | 1 | Suez Intake & P Stations-ABB-Escalation1 | 35028257.79
Suez Intake & P Stations-ABB-Escalation | 2 | 2 | Suez Intake & P Stations-ABB-Escalation2 | 7725580.34
Suez Intake & P Stations-SSC apply | 1 | 1 | Suez Intake & P Stations-SSC apply1 | 1102291.62
Suez Intake & P Stations-SSC apply | 2 | 2 | Suez Intake & P Stations-SSC apply2 | 3020707.78
Suez Intake & P Stations-SSC apply | 3 | 3 | Suez Intake & P Stations-SSC apply3 | 772824.1924
Suez Intake & P Stations-SSC apply | 8 | 8 | Suez Intake & P Stations-SSC apply8 | 1886891.07
Suez Intake & P Stations-SSC supply | 1 | 1 | Suez Intake & P Stations-SSC supply1 | 8726326.42
Suez Intake & P Stations-SSC supply | 2 | 2 | Suez Intake & P Stations-SSC supply2 | 3190893.09
Suez Intake & P Stations-SSC supply | 3 | 3 | Suez Intake & P Stations-SSC supply3 | 283552.06
Suez Intake & P Stations-SSC supply | 4 | 4 | Suez Intake & P Stations-SSC supply4 | 1e-05
Suez Steel Intake & P Stations | 1 | 1 | Suez Steel Intake & P Stations1 | 19045714
Suez Steel Intake & P Stations | 2 | 2 | Suez Steel Intake & P Stations2 | 28804143
Suez Steel Intake & P Stations | 3 | 3 | Suez Steel Intake & P Stations3 | 25468559.95
Suez Steel-Al Baraka | 1 | 1 | Suez Steel-Al Baraka1 | 19326786
Suez Steel-Gas Station | 1 | 1 | Suez Steel-Gas Station1 | 5014142.1
SVC | 1 | 1 | SVC1 | 2216581.5616
SVC | 1 | 1 | SVC1 | 1158731.1
Uptown PK #53 | 25 | 25 | Uptown PK #5325 | 12009168.61
Uptown PK #53 | 26 | 26 | Uptown PK #5326 | 13124888.11
Uptown PK #53 | 27 | 27 | Uptown PK #5327 | 9593936.7945
Uptown PK #53 | 28 | 28 | Uptown PK #5328 | 13320601.43
Uptown PK #53 | 29 | 29 | Uptown PK #5329 | 10942287.56
Uptown PK #53 | 30 | 30 | Uptown PK #5330 | 11348802.26
Uptown PK #53 | 31 | 31 | Uptown PK #5331 | 7033824.83
Uptown PK #53 | 32 | 32 | Uptown PK #5332 | 2358051.13
Uptown PK #53 | 33 | 33 | Uptown PK #5333 | 2690853.59
Uptown PK #53 | 34 | 34 | Uptown PK #5334 | 1431626.0807
Uptown PK #53 | 35 | 35 | Uptown PK #5335 | 2466454.76
Uptown PK #53 | 36 | 36 | Uptown PK #5336 | 2490213.39
Uptown PK #53 | 37 | 37 | Uptown PK #5337 | 1746850.68
Uptown PK #53 | 38 | 38 | Uptown PK #5338 | 1902092.11
Uptown PK #53 | 39 | 39 | Uptown PK #5339 | 943725.79
Uptown PK #53 | 40 | 40 | Uptown PK #5340 | 1435222.17
Uptown PK #53 | 41 | 41 | Uptown PK #5341 | 4202366.45
Uptown PK #53 | 42 | 42 | Uptown PK #5342 | 1380970.95
Uptown PK #53 | 43 | 43 | Uptown PK #5343 | 4834138.97
Uptown PK #62 | 7 | 7 | Uptown PK #627 | 1684908.09
Uptown PK #62 | 8 | 8 | Uptown PK #628 | 2970870.89
Uptown PK #62 | 9 | 9 | Uptown PK #629 | 2124952.16
Uptown PK #62 | 10 | 10 | Uptown PK #6210 | 2207449.91
Uptown PK #62 | 11 | 11 | Uptown PK #6211 | 1524280.94
Uptown PK #62 | 12 | 12 | Uptown PK #6212 | 1565019.14
Uptown PK #62 | 13 | 13 | Uptown PK #6213 | 2219134.03
Uptown PK #62 | 14 | 14 | Uptown PK #6214 | 854854.29
Uptown PK #62 | 15 | 15 | Uptown PK #6215 | 2299870.99
Uptown PK #62 | 16 | 16 | Uptown PK #6216 | 931895.88
Uptown PK #62 | 17 | 17 | Uptown PK #6217 | 419078.79
Uptown PK #62 | 18 | 18 | Uptown PK #6218 | 864260.36
Uptown PK #62 | 19 | 19 | Uptown PK #6219 | 1416810.93
Uptown PK #62 - Retention | 17 | 17 | Uptown PK #62 - Retention17 | 148822.86
Uptown PK #62 - Retention | 18 | 18 | Uptown PK #62 - Retention18 | 504922.64
Wady Halfa | 1 | 1 | Wady Halfa1 | 22733360.9
Wady Halfa | 2 | 2 | Wady Halfa2 | 8196261.85
Wady Halfa | 3 | 3 | Wady Halfa3 | 2807166.9
Wady Halfa | 4 | 4 | Wady Halfa4 | 3015154.3
Wady Halfa | 5 | 5 | Wady Halfa5 | 2984537.1
Wady Halfa-DP | 1 | 1 | Wady Halfa-DP1 | 19000000
Wady Halfa-DP | 2 | 2 | Wady Halfa-DP2 | 11000000
Wady Halfa - Escalation Claim | 1 | 1 | Wady Halfa - Escalation Claim1 | 14076920.26
Wady Halfa - Escalation Claim | 2 | 2 | Wady Halfa - Escalation Claim2 | 10413528.42
Wady Halfa - Stoppage Period | 1 | 1 | Wady Halfa - Stoppage Period1 | 8364831
Western Fence | 1 | 1 | Western Fence1 | 418218.39
Western Fence-PO | 1 | 1 | Western Fence-PO1 | 5200000
Zayed Park | 1 | 1 | Zayed Park1 | 505797
Zayed Park | 2 | 2 | Zayed Park2 | 264423.21

## consultant-gross (hidden)
Project | Invoice No. | invoice round down | concact | Approval Date (By Consultant) | Monthly Amount Approved (By Consultant) | Cummulative amount Approved (By Consultant) | Approval Date (By Client)
PK #107 | 9 | 9 | PK #1079 | 43061 | 1856322.11 | 38038903.52 | 43067
JICA | 19 | 19 | JICA19 | 43038 | 1210863.76 | 117203462.77 | 43038
FIEM | 210 | 210 | FIEM210 | 43031 | 2236443.87 | 69808024.8 | 43031
Cement Plant | 15 | 15 | Cement Plant15 | 43054 | 8583366.193 | 228271708.9079 | 43054
PI Parks - ELSEWEDY | 1 | 1 | PI Parks - ELSEWEDY1 | 43038 | 3990886.7187 | 3990886.7187 | 43043
PI Parks - ELSEWEDY | 2 | 2 | PI Parks - ELSEWEDY2 | 43061 | 4642464.2724 | 7590402.3632 | 43067
Sodic Club House | 24 | 24 | Sodic Club House24 | 43065 | 7208751.86 | 64461008.2542 | 43086
Royal City | 2 | 2 | Royal City2 | 43019 | 5127541.59 | 9046023.16 | 43019
Royal City | 3 | 3 | Royal City3 | 43048 | 8536189.79 | 17411738.66 | 43053
Uptown PK #62 | 8 | 8 | Uptown PK #628 | 43047 | 4024169.64 | 22444166.23 | 43053
Uptown PK #53 | 26 | 26 | Uptown PK #5326 | 43088 | 18228071.6884 | 228353712.8741 | 43090
PK #107 | 10 | 10 | PK #10710 | 43093 | 2025124.41 | 40064027.93 | 43096
PI Parks - ELSEWEDY | 3 | 3 | PI Parks - ELSEWEDY3 | 43092 | 1837652.48 | 9383809.13 | 43094
Uptown PK #62 | 9 | 9 | Uptown PK #629 | 43087 | 3353637.028 | 25797803.258 | 43090
Sodic Club House | 25 | 25 | Sodic Club House25 | 43106 | 4060848.9478 | 65696424.8478 | 43124
SIEMENS - Sokhna | 2 | 2 | SIEMENS - Sokhna2 | 43116 | 4401847.1 | 4401847.1
PK #107 | 11 | 11 | PK #10711 | 43115 | 3591068.23 | 43655096.16
Uptown PK #62 | 10 | 10 | Uptown PK #6210 | 43118 | 3315629.905 | 29113433.163
Uptown PK #53 | 27 | 27 | Uptown PK #5327 | 43108 | 11525442.3347 | 240340912.3274
Royal City | 5 | 5 | Royal City5 | 43122 | 11565536.4187 | 38812358.4187
PI Parks - ELSEWEDY | 4 | 4 | PI Parks - ELSEWEDY4 | 43131 | 3758163.8696 | 12907472.9296 | 43146
Sodic Club House | 26 | 26 | Sodic Club House26 | 43138 | 5215631.634 | 70469032.924 | 43153
Uptown PK #53 | 28 | 28 | Uptown PK #5328 | 43135 | 13381649.8939 | 253722562.2213 | 43146
Uptown PK #62 | 11 | 11 | Uptown PK #6211 | 43138 | 3260036.5785 | 32373469.7415 | 43146
PI Parks - ELSEWEDY | 5 | 5 | PI Parks - ELSEWEDY5 | 43170 | 1927670.8 | 14835143.73 | 43195
SIEMENS - Sokhna | 3 | 3 | SIEMENS - Sokhna3 | 43136 | 10401972.73 | 14803819.83
PK #117 | 2 | 2 | PK #1172 | 43152 | 7803090.35 | 7803090.35 | 43166
Uptown PK #53 | 29 | 29 | Uptown PK #5329 | 43157 | 17114848.1247 | 270837410.346 | 43165
NGU 2 | 26 | 26 | NGU 226 | 43131 | 6579666.5395 | 147069957.5395 | 43243
Uptown PK #62 | 12 | 12 | Uptown PK #6212 | 43177 | 2806216.291 | 35193186.031
Sodic Club House | 27 | 27 | Sodic Club House27 | 43169 | 6347559.6681 | 86021988.3593 | 43191
SIEMENS - Sokhna | 4 | 4 | SIEMENS - Sokhna4 | 43173 | 15960664.31 | 30764484.14
PK #117 | 3 | 3 | PK #1173 | 43173 | 4332593.51 | 12135683.86 | 43188
PI Parks - ELSEWEDY | 6 | 6 | PI Parks - ELSEWEDY6 | 43201 | 694638.63 | 15017848.53 | 43205
PK #107 | 13 | 13 | PK #10713 | 43192 | 2719252.37 | 52257607.28 | 43194
Uptown PK #53 | 30 | 30 | Uptown PK #5330 | 43188 | 15380090.6234 | 286603499.2497 | 43194
Sodic Club House | 28 | 28 | Sodic Club House28 | 43194 | 4455128.7309 | 90555725.5809 | 43228
Uptown PK #62 | 13 | 13 | Uptown PK #6213 | 43208 | 6967775.65 | 42160961.681 | 43228
PK #117 | 4 | 4 | PK #1174 | 43200 | 4131277.1774 | 16266961.0374 | 43209
Royal City | 6 | 6 | Royal City6 | 43214 | 17361811.89 | 54716858.14 | 43241
PI Parks - ELSEWEDY | 7 | 7 | PI Parks - ELSEWEDY7 | 43211 | 667972.21 | 15685820.74
SIEMENS - Sokhna | 5 | 5 | SIEMENS - Sokhna5 | 43205 | 19051976.33 | 49816460.47
PK #107 | 14 | 14 | PK #10714 | 43219 | 1449945.81 | 53707553.09
Mintra | 1 | 1 | Mintra1 | 43361 | 26487256.44 | 26487256.44
Uptown PK #53 | 31 | 31 | Uptown PK #5331 | 43220 | 10847277.7132 | 297391694.2129 | 43240
PK #117 | 5 | 5 | PK #1175 | 43227 | 6909334.9826 | 23176296.02 | 43242
Royal City | 7 | 7 | Royal City7 | 43242 | 11988097.7 | 66634655.56 | 43262
SIEMENS - Sokhna | 6 | 6 | SIEMENS - Sokhna6 | 43240 | 10481549.5128 | 60298009.9828
PI Parks - ELSEWEDY | 8 | 8 | PI Parks - ELSEWEDY8 | 43237 | 1892096.0888 | 17577916.8288 | 43253
Uptown PK #53 | 32 | 32 | Uptown PK #5332 | 43249 | 4916024.5037 | 302680787.2137
Al Jazi | 1 | 1 | Al Jazi1 | 43249 | 9888666.63 | 9888666.63 | 43254
PK #117 | 6 | 6 | PK #1176 | 43272 | 6651333.71 | 29827629.73 | 43293
Royal City | 8 | 8 | Royal City8 | 43275 | 7845708.0075 | 74373631.4775
SIEMENS - Sokhna | 7 | 7 | SIEMENS - Sokhna7 | 43285 | 12587450.0972 | 72885460.08
PI Parks - ELSEWEDY | 9 | 9 | PI Parks - ELSEWEDY9 | 43263 | 1491159.5592 | 19036617.1592
Uptown PK #53 | 33 | 33 | Uptown PK #5333 | 43284 | 3312628.1576 | 305993415.3712 | 43291
PI Parks - ELSEWEDY | 10 | 10 | PI Parks - ELSEWEDY10 | 43303 | 4758616.5674 | 23795233.7266 | 43313
PK #117 | 7 | 7 | PK #1177 | 43464 | -0.01 | 29854171.25
Al Jazi | 2 | 2 | Al Jazi2 | 43262 | 6959342.1 | 16848008.73 | 43277
SIEMENS - Sokhna | 8 | 8 | SIEMENS - Sokhna8 | 43300 | 18208993.38 | 91094453.46 | 43300
Sodic Club House | 31 | 31 | Sodic Club House31 | 43305 | 9473412.9251 | 110298796.01 | 43314
Al Jazi | 3 | 3 | Al Jazi3 | 43292 | 6863158.19 | 23711166.92 | 43306
Royal City | 9 | 9 | Royal City9 | 43307 | 7890492.132 | 82264123.6095
Uptown PK #53 | 34 | 34 | Uptown PK #5334 | 43307 | 73574.6923 | 306066990.0683
Al Jazi | 4 | 4 | Al Jazi4 | 43305 | 6873307.38 | 30584400.79 | 43310
Mintra | 2 | 2 | Mintra2 | 43366 | 16295714.9 | 42782971.34
Sodic Club House | 32 | 32 | Sodic Club House32 | 43328 | 11500368.6175 | 117323157.537 | 43347
PI Parks - ELSEWEDY | 11 | 11 | PI Parks - ELSEWEDY11 | 43320 | 891495.1766 | 23128178.0466 | 43356
SIEMENS - Sokhna | 9 | 9 | SIEMENS - Sokhna9 | 43346 | 19922320.61 | 111016774.07
PSP Substation | 3 | 3 | PSP Substation3 | 43384 | 2696322.9906 | 4366249.7906
Royal City | 10 | 10 | Royal City10 | 43339 | 8199169.349 | 90463292.9586
Al Jazi | 5 | 5 | Al Jazi5 | 43325 | 7893373.579 | 38477684.259 | 43342
Uptown PK #62 | 15 | 15 | Uptown PK #6215 | 43349 | 1266868.51 | 47319155.64
Uptown PK #53 | 35 | 35 | Uptown PK #5335 | 43355 | 3416261.3696 | 309483251.4379
Al Jazi | 6 | 6 | Al Jazi6 | 43353 | 4850391.56 | 43327773.16
Sodic Club House | 33 | 33 | Sodic Club House33 | 43368 | 7276853.7793 | 124600011.3163 | 43382
PI Parks - ELSEWEDY | 12 | 12 | PI Parks - ELSEWEDY12 | 43369 | 1804540.7798 | 24932718.8264
El Sewedy Uni.-PKG.1 | 1 | 1 | El Sewedy Uni.-PKG.11 | 43388 | 2762087.0381 | 2762087.0381 | 43388
SIEMENS - Sokhna | 10 | 10 | SIEMENS - Sokhna10 | 43368 | 9128690.32 | 120145464.39
Royal City | 11 | 11 | Royal City11 | 43367 | 2707034.9014 | 93170327.86
Uptown PK #53 | 36 | 36 | Uptown PK #5336 | 43376 | 2041348.5942 | 311524600.0321 | 43393
Mintra | 3 | 3 | Mintra3 | 43388 | 19469085.79 | 62252057.13
El Sewedy Uni.-PKG.2 | 1 | 1 | El Sewedy Uni.-PKG.21 | 43391 | 4165158.06 | 4165158.06
PI Parks - MEP | 1 | 1 | PI Parks - MEP1 | 43383 | 4100153.37 | 4100153.37
SIEMENS - Sokhna | 11 | 11 | SIEMENS - Sokhna11 | 43409 | 7601906.76 | 127747371.15
Al Jazi | 7 | 7 | Al Jazi7 | 43383 | 9361764.45 | 52689537.61 | 43389
PI Parks - ELSEWEDY | 13 | 13 | PI Parks - ELSEWEDY13 | 43383 | 1076504.1197 | 26009222.9461
Royal City | 12 | 12 | Royal City12 | 43397 | 9032801.23 | 102203129.09 | 43411
Uptown PK #62 | 16 | 16 | Uptown PK #6216 | 43429 | -245868.22 | 47073287.42
Sodic Club House | 34 | 34 | Sodic Club House34 | 43404 | 14426802.9732 | 134390194.7255 | 43425
Mintra-Hanger 1200m2 | 1 | 1 | Mintra-Hanger 1200m21 | 43402 | 1411985.3421 | 1411985.3421
El Sewedy Uni.-PKG.1 | 2 | 2 | El Sewedy Uni.-PKG.12 | 43398 | 1370079.6319 | 4132166.67
Uptown PK #53 | 37 | 37 | Uptown PK #5337 | 43450 | 1273110.6827 | 312797710.7077
Mintra | 4 | 4 | Mintra4 | 43422 | 9723925.4204 | 71975982.5504
Al Jazi | 8 | 8 | Al Jazi8 | 43410 | 13305889.63 | 65994656.05
Royal City | 13 | 13 | Royal City13 | 43425 | 7318551.3313 | 113140343.4613 | 43438
PI Parks - ELSEWEDY | 14 | 14 | PI Parks - ELSEWEDY14 | 43419 | 2476006.3139 | 28485229.26 | 43436
PI Parks - MEP | 2 | 2 | PI Parks - MEP2 | 43419 | 3824663.6 | 7924816.97 | 43436
El Sewedy Uni.-PKG.1 | 3 | 3 | El Sewedy Uni.-PKG.13 | 43431 | 1749696.33 | 5881863
El Sewedy Uni.-PKG.2 | 2 | 2 | El Sewedy Uni.-PKG.22 | 43412 | 5976536.23 | 10141694.29
Al Jazi | 9 | 9 | Al Jazi9 | 43432 | 11249079.12 | 77243735.17
El Sewedy Uni.-PKG.1 | 4 | 4 | El Sewedy Uni.-PKG.14 | 43444 | 807197.6524 | 7615896.5 | 43444
Royal City | 14 | 14 | Royal City14 | 43463 | 3293171.7405 | 120430321.4905
PK #117 | 8 | 8 | PK #1178 | 43464 | 4511257.49 | 34365428.74
PI Parks - MEP | 3 | 3 | PI Parks - MEP3 | 43449 | 4229682.9 | 12154499.87 | 43460
PI Parks - ELSEWEDY | 15 | 15 | PI Parks - ELSEWEDY15 | 43449 | 7576900.68 | 34774839.86 | 43460
El Sewedy Uni.-PKG.1 | 5 | 5 | El Sewedy Uni.-PKG.15 | 43452 | 267331.59 | 7883228.09
Al Jazi | 10 | 10 | Al Jazi10 | 43453 | 7201307.23 | 84445042.4
Al Jazi | 11 | 11 | Al Jazi11 | 43473 | 10407080.28 | 94852122.68
El Sewedy Uni.-PKG.2 | 4 | 4 | El Sewedy Uni.-PKG.24 | 43475 | 5121900.2295 | 19721961.8801
PKG#144 | 2 | 2 | PKG#1442 | 43485 | 4125990.87 | 4125990.87
El Sewedy Uni.-PKG.1 | 6 | 6 | El Sewedy Uni.-PKG.16 | 43473 | 205504.28 | 8088732.37
PK #117 | 9 | 9 | PK #1179 | 43495 | 3153415.09 | 37518843.83
Sodic Club House | 35 | 35 | Sodic Club House35 | 43434 | 10886083.2297 | 140396520.4122 | 43819
PI Parks - MEP | 4 | 4 | PI Parks - MEP4 | 43479 | 13292686.78 | 23744138.61
PI Parks - ELSEWEDY | 16 | 16 | PI Parks - ELSEWEDY16 | 43479 | 6344223.5299 | 40029120.3299 | 43492
Royal City | 15 | 15 | Royal City15 | 43485 | 16384822.4548 | 136815143.9453
SIEMENS - Sokhna | 16 | 16 | SIEMENS - Sokhna16 | 43485 | 32022484.92 | 254086770.43 | 43488
El Sewedy Uni.-PKG.1 | 7 | 7 | El Sewedy Uni.-PKG.17 | 43487 | 410253.12 | 8498985.49
Uptown PK #53 | 38 | 38 | Uptown PK #5338 | 43514 | 747405.6143 | 313545116.322
Al Jazi | 12 | 12 | Al Jazi12 | 43500 | 8329656 | 103181778.68
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 43544 | 9063098.3369 | 9063098.3369
PK #117 | 10 | 10 | PK #11710 | 43506 | 992195.9681 | 38511039.7981 | 43524
PKG#101 | 1 | 1 | PKG#1011 | 43508 | 1738465.6667 | 1738465.6667 | 43513
El Sewedy Uni.-PKG.2 | 5 | 5 | El Sewedy Uni.-PKG.25 | 43506 | 8018043.8084 | 27740005.6885
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 43514 | 1805053.3662 | 1805053.3662
El Sewedy Uni.-PKG.1 | 8 | 8 | El Sewedy Uni.-PKG.18 | 43502 | 339720.12 | 8838705.61
PI Parks - MEP | 5 | 5 | PI Parks - MEP5 | 43512 | 7765619.63 | 31509758.24 | 43537
SIEMENS - Sokhna | 17 | 17 | SIEMENS - Sokhna17 | 43577 | 57817326.87 | 311904097.3
PI Parks - ELSEWEDY | 17 | 17 | PI Parks - ELSEWEDY17 | 43512 | 3393993.12 | 42011770.38 | 43537
Royal City | 16 | 16 | Royal City16 | 43521 | 11488490.3339 | 148303634.2792
Al Jazi | 13 | 13 | Al Jazi13 | 43528 | 8749208.76 | 111930987.44
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 43515 | 3340179.702 | 3340179.702
El Sewedy Uni.-PKG.2 | 6 | 6 | El Sewedy Uni.-PKG.26 | 43535 | 8105230.8115 | 35845236.5
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 43536 | 2400436.8318 | 7545669.9
PI Parks - MEP | 6 | 6 | PI Parks - MEP6 | 43541 | 3555303.77 | 35065062.01 | 43550
PKG#101 | 2 | 2 | PKG#1012 | 43543 | 1610908.8476 | 3349374.5143
Royal City | 17 | 17 | Royal City17 | 43556 | 9063503.9339 | 157367138.2131
PI Parks - ELSEWEDY | 18 | 18 | PI Parks - ELSEWEDY18 | 43541 | 4573274.545 | 46585044.925 | 43551
Al Jazi | 14 | 14 | Al Jazi14 | 43563 | 9382086.37 | 121313073.81
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 43563 | 2377467.23 | 2377467.23 | 43579
El Sewedy Uni.-PKG.1 | 9 | 9 | El Sewedy Uni.-PKG.19 | 43565 | 104805.89 | 8943511.5
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 43565 | 6026842.9 | 13572512.8
PI Parks - MEP | 7 | 7 | PI Parks - MEP7 | 43572 | 4908164.7774 | 39969524.1674 | 43599
PSP Substation | 10 | 10 | PSP Substation10 | 43578 | 4978707.75 | 29883668.3
Royal City | 18 | 18 | Royal City18 | 43573 | 8621924.8043 | 165989063.0174
Uptown PK #53 | 39 | 39 | Uptown PK #5339 | 43576 | 32300.9957 | 313577417.3177
El Sewedy Uni.-PKG.2 | 7 | 7 | El Sewedy Uni.-PKG.27 | 43565 | 4929812 | 40775048.5
PKG#101 | 3 | 3 | PKG#1013 | 43578 | 4030395.5429 | 7379770.0571 | 43590
PI Parks - ELSEWEDY | 19 | 19 | PI Parks - ELSEWEDY19 | 43572 | 4823264.9186 | 49467914.3986 | 43599
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 43573 | 20887437.3108 | 29950535.6476
El Sewedy Uni.-PKG.3 | 5 | 5 | El Sewedy Uni.-PKG.35 | 43590 | 27458064.6 | 41030577.4
PI Parks - MEP | 8 | 8 | PI Parks - MEP8 | 43604 | 2655162.8183 | 42624686.9424
Al Jazi | 15 | 15 | Al Jazi15 | 43594 | 9011217.19 | 130324291
PI Parks - ELSEWEDY | 20 | 20 | PI Parks - ELSEWEDY20 | 43604 | 4018450.9279 | 51315568.4279
Royal City | 19 | 19 | Royal City19 | 43608 | 15549148.0486 | 181538211.066
Al Jazi | 16 | 16 | Al Jazi16 | 43617 | 9502208.88 | 139826499.88
Al Jazi - Center Zone | 2 | 2 | Al Jazi - Center Zone2 | 43614 | 6291718.01 | 8640525.61
PKG#101 | 4 | 4 | PKG#1014 | 43614 | 4428897.7238 | 11808672.4857
Sodic Eastown | 3 | 3 | Sodic Eastown3 | 43608 | 2101069.4381 | 32051605.0857
El Sewedy Uni.-PKG.2 | 8 | 8 | El Sewedy Uni.-PKG.28 | 43684 | 1755356.8 | 42530405.3
El Sewedy Uni.-PKG.3 | 6 | 6 | El Sewedy Uni.-PKG.36 | 43632 | 30765208.3 | 71795785.7
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 43643 | 4797449.5194 | 4797449.5194
Royal City | 20 | 20 | Royal City20 | 43642 | 7876990.4815 | 189415201.5475
Uptown PK #53 | 40 | 40 | Uptown PK #5340 | 43662 | 52815.0023 | 313630232.32
PI Parks - ELSEWEDY | 21 | 21 | PI Parks - ELSEWEDY21 | 43751 | 598299.7921 | 51913868.22
PI Parks - MEP | 9 | 9 | PI Parks - MEP9 | 43751 | 3596767.6976 | 46221454.64
Al Jazi | 17 | 17 | Al Jazi17 | 43652 | 7664029.32 | 147490529.2
Sodic Eastown | 4 | 4 | Sodic Eastown4 | 43654 | 22270031.4 | 54321636.4857
PKG#101 | 5 | 5 | PKG#1015 | 43670 | 2224631.7143 | 14033304.2
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 43667 | 4911239.0806 | 9708688.6
Royal City | 21 | 21 | Royal City21 | 43664 | 7532294.3265 | 196947495.8739
El Sewedy Uni.-PKG.3 | 7 | 7 | El Sewedy Uni.-PKG.37 | 43671 | 41332921.1 | 113128706.8
Al Jazi | 18 | 18 | Al Jazi18 | 43673 | 7401622.43 | 154892151.63
Al Jazi - Center Zone | 3 | 3 | Al Jazi - Center Zone3 | 43673 | 12038969.26 | 20679494.87 | 43709
Sodic Eastown | 5 | 5 | Sodic Eastown5 | 43678 | 45005158.6118 | 99326795.0975
Mivida-PK#140 | 3 | 3 | Mivida-PK#1403 | 43697 | 6244069.8629 | 15952758.4629
Royal City | 22 | 22 | Royal City22 | 43710 | 24265130.1959 | 221212626.0698
PKG#101 | 6 | 6 | PKG#1016 | 43705 | 3491880.8381 | 17525185.0381
El Sewedy Uni.-PKG.3 | 8 | 8 | El Sewedy Uni.-PKG.38 | 43701 | 23588218.3 | 136716925.1
El Sewedy Uni.-PKG.1 | 10 | 10 | El Sewedy Uni.-PKG.110 | 43684 | 2360 | 8945871.5
Sodic Eastown | 6 | 6 | Sodic Eastown6 | 43716 | 38734277.1501 | 138061072.2476
Al Jazi | 19 | 19 | Al Jazi19 | 43718 | 9504587.63 | 164396739.26
Al Jazi - Center Zone | 4 | 4 | Al Jazi - Center Zone4 | 43718 | 4840645.74 | 25519840.19
El Sewedy Uni.-PKG.3 | 9 | 9 | El Sewedy Uni.-PKG.39 | 43705 | 30130968 | 166847893.1
PK #117 | 12 | 12 | PK #11712 | 43733 | 2921413.42 | 42643976.35
Mivida-PK#140 | 4 | 4 | Mivida-PK#1404 | 43725 | 2442385.7689 | 18395144.2317
PKG#144 | 12 | 12 | PKG#14412 | 43741 | 34717376.42 | 151479307.34
Royal City | 23 | 23 | Royal City23 | 43736 | 6268692.5562 | 227481318.626
PKG#101 | 7 | 7 | PKG#1017 | 43729 | 3120848.981 | 20646034.019 | 43734
El Sewedy Uni.-PKG.3 | 10 | 10 | El Sewedy Uni.-PKG.310 | 43737 | 28039187.7 | 194887080.8
Mivida-PK#140 | 5 | 5 | Mivida-PK#1405 | 43761 | 1994559.8383 | 20389704.07
Al Jazi | 20 | 20 | Al Jazi20 | 43772 | 8799095.49 | 173195834.75
Al Jazi - Center Zone | 5 | 5 | Al Jazi - Center Zone5 | 43772 | 7051826.31 | 32571666.5
Royal City | 24 | 24 | Royal City24 | 43762 | 17799666.736 | 245280985.3621
Royal City - Landscape | 3 | 3 | Royal City - Landscape3 | 43761 | 341000 | 341000
PKG#101 | 8 | 8 | PKG#1018 | 43772 | 4703530.9524 | 25352356.981 | 43774
PK #117 | 13 | 13 | PK #11713 | 43781 | 2611652.87 | 45255629.22
Sodic Eastown | 8 | 8 | Sodic Eastown8 | 43783 | 85059782.1524 | 288748271.5905
Royal City | 25 | 25 | Royal City25 | 43796 | 17503083.0268 | 262784068.3888
Royal City - Landscape | 4 | 4 | Royal City - Landscape4 | 43824 | 2839877.7881 | 3180877.7881
Mivida-PK#140 | 6 | 6 | Mivida-PK#1406 | 43789 | 12232780.5437 | 32622484.6137 | 43809
HyperOne | 1 | 1 | HyperOne1 | 43793 | 1684523.66 | 1684523.66
PKG#101 | 9 | 9 | PKG#1019 | 43802 | 3179849.8818 | 28533563.3143
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | PH.2-El Sewedy Uni. - Enabling1 | 43810 | 1222080 | 1222080
Mivida-PK#140 | 7 | 7 | Mivida-PK#1407 | 43818 | 7170532.1164 | 39793016.7264
HyperOne | 2 | 2 | HyperOne2 | 43811 | 11473372.17 | 13157895.83
Royal City | 26 | 26 | Royal City26 | 43835 | 10595979.9301 | 273380048.3189
Royal City - Landscape | 5 | 5 | Royal City - Landscape5 | 43835 | 5896802.2265 | 9077680.0146
PKG#101 | 10 | 10 | PKG#10110 | 43828 | 3111780.0857 | 31645343.4 | 43836
CFC | 1 | 1 | CFC1 | 43842 | 6586123.18 | 6586123.18
Uptown PK #62 | 19 | 19 | Uptown PK #6219 | 43944 | 22437 | 47095724.42 | 44031
PH.2-El Sewedy Uni. - Enabling | 2 | 2 | PH.2-El Sewedy Uni. - Enabling2 | 43841 | 19989408.99 | 21211488.99
HyperOne | 3 | 3 | HyperOne3 | 43843 | 10276217.5887 | 23434113.4187
Mivida-PK#140 | 8 | 8 | Mivida-PK#1408 | 43858 | 6113446.7507 | 45906463.4771 | 43874
Sodic Eastown | 10 | 10 | Sodic Eastown10 | 43856 | 88119712.7238 | 392914894.2286 | 43850
CFC | 2 | 2 | CFC2 | 43872 | 16003200.38 | 22589323.56
Royal City | 27 | 27 | Royal City27 | 43871 | 20586377.6301 | 293966425.9491
Royal City - Landscape | 6 | 6 | Royal City - Landscape6 | 43871 | 12932194.6154 | 22009874.63
El-Gouna - Equip. Rental | 1 | 1 | El-Gouna - Equip. Rental1 | 43863 | 80875 | 80875
El-Gouna - Temp. Fence | 1 | 1 | El-Gouna - Temp. Fence1 | 43891 | 409200 | 409200
Al Jazi | 21 | 21 | Al Jazi21 | 43914 | 33097306.6205 | 206293141.3705
CFC | 3 | 3 | CFC3 | 43901 | 16743766.83 | 39333090.39
HyperOne | 4 | 4 | HyperOne4 | 43874 | 12451224.3668 | 35885337.7855 | 43884
PH.2-El Sewedy Uni. - Enabling | 3 | 3 | PH.2-El Sewedy Uni. - Enabling3 | 43866 | 22171564.66 | 43383053.65
PKG#101 | 11 | 11 | PKG#10111 | 43874 | 382240.2571 | 32016510.4571 | 43888
Mivida-PK#140 | 9 | 9 | Mivida-PK#1409 | 43884 | 4233335.7568 | 50139799.2368 | 43908
Al Jazi - Center Zone | 6 | 6 | Al Jazi - Center Zone6 | 43914 | 6082957.03 | 38654623.53
HyperOne | 5 | 5 | HyperOne5 | 43884 | 5616638.2145 | 41501976
Royal City | 28 | 28 | Royal City28 | 43906 | 15640549.4851 | 309606975.4342
Royal City - Landscape | 7 | 7 | Royal City - Landscape7 | 43906 | 6479189.8549 | 28489064.4849
El-Gouna | 5 | 5 | El-Gouna5 | 43884 | 3430037.61 | 17346579.72
HyperOne | 6 | 6 | HyperOne6 | 43897 | 10976157.5052 | 52478133.5052
Mivida-PK#140 | 10 | 10 | Mivida-PK#14010 | 43950 | 6612227.7834 | 56752027.0202
Sodic Eastown | 12 | 12 | Sodic Eastown12 | 43919 | 26833421.413 | 450976932.5714
PH.2-El Sewedy Uni. - Enabling | 4 | 4 | PH.2-El Sewedy Uni. - Enabling4 | 43906 | 17471458.95 | 60854512.6
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 43912 | 39552087.9 | 39552087.9
CFC | 4 | 4 | CFC4 | 43923 | 35226223.2 | 74559313.59
El-Gouna | 6 | 6 | El-Gouna6 | 43908 | 6540676.19 | 23887255.91 | 43908
HyperOne | 7 | 7 | HyperOne7 | 43913 | 12354446.4948 | 64832580
CFC | 5 | 5 | CFC5 | 43943 | 30502560.31 | 105061873.9
Mivida-PK#140 | 11 | 11 | Mivida-PK#14011 | 43950 | 3124627.5928 | 59876654.613
Royal City | 29 | 29 | Royal City29 | 43926 | 18804604.7977 | 328411580.2319
Royal City - Landscape | 8 | 8 | Royal City - Landscape8 | 43926 | 17137734.2822 | 45626798.7671
PKG#101 | 12 | 12 | PKG#10112 | 43929 | 2584477.6667 | 34580168.2667
PH.2-El Sewedy Uni. - Enabling | 5 | 5 | PH.2-El Sewedy Uni. - Enabling5 | 43930 | 7891719.6 | 68746232.2
Sodic Eastown | 13 | 13 | Sodic Eastown13 | 43943 | 26192906.0286 | 477169838.6 | 43968
HyperOne | 8 | 8 | HyperOne8 | 43933 | 7228560.7301 | 72061140.7301
PH.2-El Sewedy Uni. - Finishes | 2 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 43943 | 33281363.92 | 72833451.82
CFC | 6 | 6 | CFC6 | 43955 | 42011127.9851 | 147073001.8851
Royal City | 30 | 30 | Royal City30 | 43956 | 13862319.0142 | 342273899.2462
Royal City - Landscape | 9 | 9 | Royal City - Landscape9 | 43956 | 6296234.5253 | 51923033.2924
HyperOne | 9 | 9 | HyperOne9 | 43947 | 2029339.2699 | 74090480
El-Gouna | 7 | 7 | El-Gouna7 | 43942 | 3114205.16 | 27001461.07 | 43942
PH.2-El Sewedy Uni. - Enabling | 6 | 6 | PH.2-El Sewedy Uni. - Enabling6 | 43957 | 18379179.4 | 87125411.6
Mivida-PK#140 | 12 | 12 | Mivida-PK#14012 | 43972 | 1875813.048 | 61752467.661
PH.2-El Sewedy Uni. - Finishes | 3 | 3 | PH.2-El Sewedy Uni. - Finishes3 | 43970 | 24169965.9076 | 97003417.7276
CFC | 7 | 7 | CFC7 | 43986 | 17879880.0649 | 164952881.95
Royal City - Landscape | 10 | 10 | Royal City - Landscape10 | 44014 | 3937848.897 | 55860882.1894
Royal City | 31 | 31 | Royal City31 | 44014 | 10234077.8776 | 352507977.1238
HyperOne | 10 | 10 | HyperOne10 | 43983 | 7741768.3647 | 81832248.3647
PH.2-El Sewedy Uni. - Enabling | 7 | 7 | PH.2-El Sewedy Uni. - Enabling7 | 44023 | 9076073.5 | 96201485.1
CFC | 8 | 8 | CFC8 | 44019 | 31008098.6054 | 195960980.5554
PH.2-El Sewedy Uni. - Finishes | 4 | 4 | PH.2-El Sewedy Uni. - Finishes4 | 44000 | 24591514.8424 | 121594932.57
HyperOne | 11 | 11 | HyperOne11 | 44005 | 9960645.6353 | 91792894
Royal City | 32 | 32 | Royal City32 | 44020 | 3761397.6023 | 356269374.7261
Royal City - Landscape | 11 | 11 | Royal City - Landscape11 | 44020 | 5192701.4937 | 61053583.6831
PK #117 | 14 | 14 | PK #11714 | 44082 | 1169069.6666 | 46915000.03 | 44101
CFC | 9 | 9 | CFC9 | 44039 | 29660399.8248 | 225621380.3802
HyperOne | 12 | 12 | HyperOne12 | 44023 | 3093528.5715 | 94886422.5715
El-Gouna | 8 | 8 | El-Gouna8 | 44018 | 3250029.8 | 30251490.87 | 44018
Mivida-PK#140 | 14 | 14 | Mivida-PK#14014 | 44033 | 2429362.3736 | 65607696.3436
PH.2-El Sewedy Uni. - Enabling | 8 | 8 | PH.2-El Sewedy Uni. - Enabling8 | 44021 | 2504382.4 | 98705867.5
PH.2-El Sewedy Uni. - Finishes | 5 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 44025 | 77007398.3 | 198602330.87
Royal City | 33 | 33 | Royal City33 | 44055 | 13830917.4352 | 370100292.1612
Royal City - Landscape | 12 | 12 | Royal City - Landscape12 | 44055 | 8940402.3014 | 69993985.9845
PH.2-El Sewedy Uni. - Finishes | 6 | 6 | PH.2-El Sewedy Uni. - Finishes6 | 44041 | 22875033.55 | 221477364.42
PH.2-El Sewedy Uni. - Enabling | 9 | 9 | PH.2-El Sewedy Uni. - Enabling9 | 44070 | 9452002.7 | 108157870.2
CFC | 10 | 10 | CFC10 | 44069 | 46257284.4262 | 271878664.8064
Mivida-PK#140 | 15 | 15 | Mivida-PK#14015 | 44067 | 16266667.6714 | 81874364.0149
HyperOne | 13 | 13 | HyperOne13 | 44062 | 9161230.539 | 104047653.1105
Royal City - Landscape | 13 | 13 | Royal City - Landscape13 | 44081 | 3598777.1179 | 73592763.1024
Royal City | 34 | 34 | Royal City34 | 44088 | 7811639.6921 | 377911931.8534
PH.2-El Sewedy Uni. - Finishes | 7 | 7 | PH.2-El Sewedy Uni. - Finishes7 | 44069 | 54216090.64 | 275693455.06
Sodic Eastown | 17 | 17 | Sodic Eastown17 | 44065 | 33693489.0097 | 593205155.981 | 44081
CFC | 11 | 11 | CFC11 | 44103 | 22706553.5236 | 294585218.33
Mivida-PK#140 | 16 | 16 | Mivida-PK#14016 | 44089 | 19380294.5984 | 101254658.6133
HyperOne | 14 | 14 | HyperOne14 | 44087 | 5698538.8895 | 109746192
PH.2-El Sewedy Uni. - Finishes | 8 | 8 | PH.2-El Sewedy Uni. - Finishes8 | 44091 | 61814968.03 | 337508423.09
Royal City | 35 | 35 | Royal City35 | 44109 | 3980750.5222 | 381892682.3756
Royal City - Landscape | 14 | 14 | Royal City - Landscape14 | 44109 | 2137131.084 | 75729894.1864
HyperOne | 15 | 15 | HyperOne15 | 44447 | 16067546 | 125813738
Mivida-PK#140 | 17 | 17 | Mivida-PK#14017 | 44123 | 16610857.3328 | 117865515.946
Royal City | 36 | 36 | Royal City36 | 44132 | 8343396.9284 | 390236079.304
Royal City - Landscape | 15 | 15 | Royal City - Landscape15 | 44132 | 3135305.5981 | 78865199.7846
CFC | 12 | 12 | CFC12 | 44139 | 35304714.2417 | 329889932.5717
PH.2-El Sewedy Uni. - Finishes | 9 | 9 | PH.2-El Sewedy Uni. - Finishes9 | 44124 | 56169721.37 | 393678144.46
AEON | 2 | 2 | AEON2 | 44147 | 1300835.2032 | 2626046.4794 | 44180
CFC | 13 | 13 | CFC13 | 44174 | 13502068.4452 | 343392001.0169
Royal City | 37 | 37 | Royal City37 | 44161 | 5412454.8663 | 395648534.1703
Mivida-PK#140 | 18 | 18 | Mivida-PK#14018 | 44164 | 4603925.7609 | 122469441.707
Royal City - Landscape | 16 | 16 | Royal City - Landscape16 | 44161 | 1582061.2622 | 80447261.0467
PH.2-El Sewedy Uni. - Finishes | 10 | 10 | PH.2-El Sewedy Uni. - Finishes10 | 44154 | 33204826.41 | 426882970.87
ORA - ZED | 1 | 1 | ORA - ZED1 | 44213 | 2407390.5714 | 2407390.5714
CFC | 14 | 14 | CFC14 | 44207 | 29172801.673 | 372564802.6899
PKG#101 | 15 | 15 | PKG#10115 | 44182 | 440607.3155 | 42275929.0869 | 44216
Mivida-PK#140 | 19 | 19 | Mivida-PK#14019 | 44186 | 11459315.8636 | 133928757.5706 | 44186
Royal City | 38 | 38 | Royal City38 | 44201 | 3712322.3219 | 399360856.4923
Royal City - Landscape | 17 | 17 | Royal City - Landscape17 | 44201 | 3716309.8261 | 84163570.8728
PH.2-El Sewedy Uni. - Finishes | 11 | 11 | PH.2-El Sewedy Uni. - Finishes11 | 44186 | 20698550.4 | 447581521.27
AEON | 3 | 3 | AEON3 | 44200 | 799158.9955 | 3737551.6717
ORA - ZED | 2 | 2 | ORA - ZED2 | 44202 | 43865060.0886 | 46272450.66 | 44202
Mivida-PK#140 | 20 | 20 | Mivida-PK#14020 | 44231 | 5957491.0722 | 139886248.6428
CFC | 15 | 15 | CFC15 | 44249 | 46288367.9197 | 418853170.6096
Royal City - Landscape | 18 | 18 | Royal City - Landscape18 | 44230 | 1163660.8736 | 85327231.7464
Royal City | 39 | 39 | Royal City39 | 44230 | 1174176.5076 | 400535032.9999
PKG#144 | 16 | 16 | PKG#14416 | 44256 | 150533.34 | 176412609.32 | 44280
ORA - ZED | 3 | 3 | ORA - ZED3 | 44244 | 23073312.5238 | 70686130.1714 | 44244
CFC | 16 | 16 | CFC16 | 44276 | 25170121.1048 | 444023291.7144
Mivida-PK#140 | 21 | 21 | Mivida-PK#14021 | 44244 | 9991628.9775 | 149877877.6203 | 44245
HQ - CFC | 1 | 1 | HQ - CFC1 | 44249 | 1435679.4 | 1435679.4
Royal City - Landscape | 19 | 19 | Royal City - Landscape19 | 44257 | 2029657.8338 | 87356889.5802
PH.2-El Sewedy Uni. - Finishes | 12 | 12 | PH.2-El Sewedy Uni. - Finishes12 | 44271 | 36099063.7776 | 483680585.0476 | 44277
CFC | 17 | 17 | CFC17 | 44280 | 23196101.9456 | 467219393.66
CFC | 18 | 18 | CFC18 | 44292 | 16880809.49 | 484100203.15
ORA - ZED | 4 | 4 | ORA - ZED4 | 44279 | 21833038.3714 | 96213963.4667 | 44279
HQ - CFC | 2 | 2 | HQ - CFC2 | 44277 | 7766126.7 | 9201806.1
Sodic Eastown | 24 | 24 | Sodic Eastown24 | 44284 | 25445155.6214 | 844856989.8952 | 44297
Royal City | 40 | 40 | Royal City40 | 44298 | 5847326.4556 | 406382359.4555
Royal City - Landscape | 20 | 20 | Royal City - Landscape20 | 44298 | 1366613.9629 | 88723503.543
CFC | 19 | 19 | CFC19 | 44306 | 20398722.16 | 504498925.31
CFC | 20 | 20 | CFC20 | 44340 | 23102145.85 | 527601071.16
ORA - ZED | 5 | 5 | ORA - ZED5 | 44339 | 41442903.7055 | 142416997.3436 | 44327
HQ - CFC | 3 | 3 | HQ - CFC3 | 44301 | 12533035.1 | 21734841.2
Mivida-PK#140 | 23 | 23 | Mivida-PK#14023 | 44327 | 1777689.2863 | 157122573.9763 | 44342
HQ - CFC | 4 | 4 | HQ - CFC4 | 44342 | 11480730.2 | 33215571.4
CFC | 21 | 21 | CFC21 | 44364 | 23568050.8 | 551169121.96
CFC | 22 | 22 | CFC22 | 44376 | 19833699.32 | 571002821.28
ORA - ZED | 6 | 6 | ORA - ZED6 | 44343 | 15678333.3286 | 156246633.6714 | 44355
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 44362 | 5145072.89 | 5145072.89
EGAT Pelletizing Plant-Water Tank | 1 | 1 | EGAT Pelletizing Plant-Water Tank1 | 44369 | 3274479.04 | 3274479.04
Royal City | 41 | 41 | Royal City41 | 44501 | 5256684.0377 | 411639043.4932
PH.2-El Sewedy Uni. - Finishes | 13 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 44678 | 13891238 | 494664244.29
Royal City - Landscape | 21 | 21 | Royal City - Landscape21 | 44390 | 4112536.457 | 92836040
EGAT Pelletizing Plant-MEP | 1 | 1 | EGAT Pelletizing Plant-MEP1 | 44433 | 2011978.5 | 2011978.5
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 44389 | 10496612.58 | 15641685.47
CFC | 23 | 23 | CFC23 | 44426 | 19569971.41 | 590572792.69
Katameya - Creeks | 7 | 7 | Katameya - Creeks7 | 44404 | 46826693.78 | 204907885.73
PKG#178 | 6 | 6 | PKG#1786 |  | 4524611.3442 | 46623243.3042 | 44460
EGAT Pelletizing Plant-Water Tank | 2 | 2 | EGAT Pelletizing Plant-Water Tank2 | 44389 | 2028589.79 | 5303068.83
CFC | 24 | 24 | CFC24 | 44462 | 14455028.52 | 605027821.21
PKG#177 | 18 | 18 | PKG#17718 | 44440 | 12925810.52 | 101062801.09 | 44441
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 44427 | 4383722.29 | 20025407.76
EGAT Pelletizing Plant-Water Tank | 3 | 3 | EGAT Pelletizing Plant-Water Tank3 | 44427 | 725357.85 | 6028426.68
PKG#177 | 19 | 19 | PKG#17719 |  | -0.0001 | 101062801.09 | 44455
PKG#177 | 20 | 20 | PKG#17720 |  | -0.001 | 101062801.09 | 44488
ORA - ZED | 9 | 9 | ORA - ZED9 | 44448 | 29833656.4571 | 222298531.4286 | 44459
CFC | 25 | 25 | CFC25 | 44494 | 13190112.67 | 618217933.88
PKG#177 | 21 | 21 | PKG#17721 |  | -0.0001 | 111518679.06 | 44518
Ring Road - Mounib | 9 | 9 | Ring Road - Mounib9 |  | 4536613.5882 | 98438363.943
Ring Road - Mounib | 10 | 10 | Ring Road - Mounib10 |  | 18316815 | 116755178.943
PKG#177 | 22 | 22 | PKG#17722 |  | -0.0001 | 122505070.55 | 44537
EGAT Pelletizing Plant-Water Tank | 4 | 4 | EGAT Pelletizing Plant-Water Tank4 | 44444 | 766173.48 | 6794600.16
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 44466 | 6320391.6 | 26345799.36
Ring Road - Mounib | 11 | 11 | Ring Road - Mounib11 | 44446 | 30549611.057 | 147304790
CFC | 26 | 26 | CFC26 | 44518 | 6460765.9427 | 624678699.8227
HQ - CFC | 7 | 7 | HQ - CFC7 | 44448 | 14463563.8 | 59130669.9
PKG#177 | 23 | 23 | PKG#17723 |  | -0.0001 | 130097671.64 | 44565
ORA - ZED | 10 | 10 | ORA - ZED10 | 44465 | 32858070.0667 | 252726343.0667
PKG#177 | 24 | 24 | PKG#17724 |  | -0.0001 | 134853540.34 | 44587
Royal City - Landscape | 22 | 22 | Royal City - Landscape22 | 44501 | 3299640.8 | 96135680.8
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 44489 | 14624189 | 40969988.36
EGAT Pelletizing Plant-Water Tank | 5 | 5 | EGAT Pelletizing Plant-Water Tank5 | 44481 | 923594.34 | 7718194.5
PKG#177 | 25 | 25 | PKG#17725 |  | -0.0001 | 140808056.23 | 44620
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 44482 | 13196047.2 | 13196047.2 | 44482
HQ - CFC | 8 | 8 | HQ - CFC8 | 44482 | 12903651.6 | 72034321.5 | 44486
Ring Road - Mounib | 12 | 12 | Ring Road - Mounib12 | 44485 | 20117126 | 167421916
Kafr Shokr | 7 | 7 | Kafr Shokr 7 |  | 31881474.95 | 108184525
CFC | 27 | 27 | CFC27 | 44522 | 7714993.7673 | 632393693.59
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 44514 | 11102739.54 | 52072727.9
EGAT Pelletizing Plant-Water Tank | 6 | 6 | EGAT Pelletizing Plant-Water Tank6 | 44509 | 1464316.6 | 9182511.1
HQ - CFC | 9 | 9 | HQ - CFC9 | 44511 | 11039038.4 | 83025202.3
Royal City - Landscape | 23 | 23 | Royal City - Landscape23 | 44970 | 10826725.43 | 106962406.23
Ring Road - Mounib | 13 | 13 | Ring Road - Mounib13 | 44513 | 56505929 | 223927845
Sports Hall - Finishes | 3 | 3 | Sports Hall - Finishes3 | 44517 | 91998353.75 | 178494684.93
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 44514 | 21711682.2014 | 34907729.4014 | 44514
PKG#162 | 15 | 15 | PKG#16215 | 44613 | 0.01 | 100261400.96 | 44627
Kafr Shokr | 8 | 8 | Kafr Shokr 8 | 44555 | 2504502 | 110689027
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 44579 | 15579509.1856 | 50487238.587 | 44579
HQ - CFC | 10 | 10 | HQ - CFC10 | 44546 | 10645458.9 | 93670661.2
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 44550 | 14005522.66 | 66078250.56
EGAT Pelletizing Plant-Water Tank | 7 | 7 | EGAT Pelletizing Plant-Water Tank7 | 44539 | 399729.3 | 9582240.4
MDF Factory | 6 | 6 | MDF Factory6 | 44581 | 17937654.1261 | 68968353.37
Ring Road - Mounib | 14 | 14 | Ring Road - Mounib14 | 44924 | 46948185.4 | 270876030.4
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 44570 | 34505631.6966 | 84992870.2836 | 44607
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 44579 | 12121253.25 | 78199503.81
EGAT Pelletizing Plant-Water Tank | 8 | 8 | EGAT Pelletizing Plant-Water Tank8 | 44567 | 307226.2 | 9889466.6
Kafr Shokr | 9 | 9 | Kafr Shokr 9 | 44780 | 5785188 | 116474215
Ring Road - Mounib | 15 | 15 | Ring Road - Mounib15 | 44581 | 30552404.425 | 301428434.825
HQ - CFC | 11 | 11 | HQ - CFC11 | 44578 | 21606397.9 | 115277059.1 | 44854
Sports Hall - Finishes - ADD.01 | 1 | 1 | Sports Hall - Finishes - ADD.011 | 44614 | 9145259 | 9145259
MDF Factory | 7 | 7 | MDF Factory7 | 44594 | 16588591.02 | 85556944.39 | 44606
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 44620 | 21476647.48 | 21476647.48
Ring Road - Mounib | 16 | 16 | Ring Road - Mounib16 | 44769 | 161507041.625 | 462935476.45
Kafr Shokr | 10 | 10 | Kafr Shokr 10 | 44830 | 2841975 | 119316190
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 44606 | 34312846.6 | 34312846.6
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 44616 | 15797419.96 | 93996923.77
EGAT Pelletizing Plant-Water Tank | 9 | 9 | EGAT Pelletizing Plant-Water Tank9 | 44622 | 1064224 | 10953690.6
Rolling Mill #4-TRAESUEZ | 2 | 2 | Rolling Mill #4-TRAESUEZ2 | 44642 | 13583921.53 | 35060569.01
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 44616 | 5018202.5 | 5018202.5
Katameya - Creeks | 14 | 14 | Katameya - Creeks14 | 44616 | 45239351.95 | 505191976.74
MDF Factory | 8 | 8 | MDF Factory8 | 44621 | 12291002.2884 | 97340309.44
ORA - ZED - ph.02 | 5 | 5 | ORA - ZED - ph.025 | 44617 | 9902335.4874 | 94895205.771 | 44643
HQ - CFC | 12 | 12 | HQ - CFC12 | 44616 | 11990804.88 | 127267864.5
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 44620 | 6707988.52 | 6707988.52
ORA - ZED | 15 | 15 | ORA - ZED15 |  | 27710999.5475 | 424404904.8142 | 44651
EGAT Pelletizing Plant-MEP | 2 | 2 | EGAT Pelletizing Plant-MEP2 | 44614 | 112937.5 | 2124916
CFC | 28 | 28 | CFC28 | 44690 | 5026145.47 | 637419839.06
PKG#177 | 34 | 34 | PKG#17734 |  | 3016331.1152 | 188904459.8652 | 44713
Abo Ghaleb Bridge | 2 | 2 | Abo Ghaleb Bridge2 | 44627 | 3079766.7 | 15845653.7
MDF Factory | 9 | 9 | MDF Factory9 | 44658 | 8038787.77 | 105379097.21
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 44663 | 13671163.11 | 107668086.88
EGAT-Lock & Load | 2 | 2 | EGAT-Lock & Load2 | 44626 | 2362059.16 | 7380261.66
EGAT Pelletizing Plant-Water Tank | 10 | 10 | EGAT Pelletizing Plant-Water Tank10 | 44634 | 3540729.8 | 14494420.4
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 44644 | 28642092.8 | 28642092.8
HQ - CFC | 13 | 13 | HQ - CFC13 | 44648 | 23373232.3 | 150641096.8
ORA - ZED | 16 | 16 | ORA - ZED16 |  | 28676537.6669 | 453081442.4811 | 44663
ORA - ZED - ph.02 | 6 | 6 | ORA - ZED - ph.026 | 44691 | 23225104.4643 | 118120310.2353
Abo Ghaleb Bridge | 3 | 3 | Abo Ghaleb Bridge3 | 44655 | 3857104.5 | 19702758.2
ORA - ZED - ph.02 | 7 | 7 | ORA - ZED - ph.027 | 44780 | 42383851.5888 | 160504161.8242
ORA - ZED | 17 | 17 | ORA - ZED17 | 44692 | 31100661.1293 | 484182103.6103 | 44692
PKG#177 | 36 | 36 | PKG#17736 |  | 2649851.22 | 213241337.22 | 44777
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 44672 | 6522225.37 | 16737694.31
EGAT-Lock & Load | 3 | 3 | EGAT-Lock & Load3 | 44663 | 1772326.51 | 9152588.17
Rolling Mill #4-TRAESUEZ | 3 | 3 | Rolling Mill #4-TRAESUEZ3 | 44671 | 12117327 | 47177896.01
EGAT Pelletizing Plant-Water Tank | 11 | 11 | EGAT Pelletizing Plant-Water Tank11 | 44796 | 3753750.32 | 18248170.72
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 44672 | 14893958.07 | 122562044.95
PKG#177 | 37 | 37 | PKG#17737 | 44780 | 3201524.52 | 255757972.06 | 44787
MDF Factory | 10 | 10 | MDF Factory10 | 44678 | 6155129.99 | 111534227.2
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 44668 | 30329196.74 | 58971289.54
Abo Ghaleb Bridge | 4 | 4 | Abo Ghaleb Bridge4 | 44782 | 17739438 | 37442196.2
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 44704 | 8116943.05 | 130678988
Rolling Mill #4-TRAESUEZ | 4 | 4 | Rolling Mill #4-TRAESUEZ4 | 44698 | 8075015.79 | 55252911.8
ORA - ZED - ph.02 | 8 | 8 | ORA - ZED - ph.028 | 44719 | 8766077.2795 | 169270239.1037 | 44721
ORA - ZED | 18 | 18 | ORA - ZED18 | 44707 | 11112905.9801 | 495295009.5905 | 44707
PKG#163 | 24 | 24 | PKG#16324 |  | 5789760.2558 | 115718940.9358 | 44810
PKG#177 | 38 | 38 | PKG#17738 |  | -0.86 | 255757972.06 | 44788
PKG#177 - SWI 07 | 6 | 6 | PKG#177 - SWI 076 |  | 3141613.418 | 31868573.268
HQ - CFC | 15 | 15 | HQ - CFC15 | 44698 | 16353901 | 182179087
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 44712 | 5466647.24 | 22204341.55
MDF Factory | 11 | 11 | MDF Factory11 | 44719 | 9364100.8 | 120898328
Abo Ghaleb Bridge | 5 | 5 | Abo Ghaleb Bridge5 | 44794 | 2031888 | 39474084.2
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 44728 | 15323108.5333 | 15323108.5333
PKG#177 | 39 | 39 | PKG#17739 |  | -178832904.96 | 190000000 | 44837
PKG#163 | 25 | 25 | PKG#16325 |  | 22617186.6357 | 145615407.7057 | 44810
PKG#177 - SWI 07 | 7 | 7 | PKG#177 - SWI 077 |  | 10847798.8446 | 42716372.1126
Astoria Hotel | 5 | 5 | Astoria Hotel5 | 44740 | 3030560.1014 | 25234901.6514
EGAT-Lock & Load | 5 | 5 | EGAT-Lock & Load5 | 44719 | 3180176.34 | 13211888.51
EGAT Pelletizing Plant-MEP | 3 | 3 | EGAT Pelletizing Plant-MEP3 | 44969 | 1723067.19 | 3847983.19
ORA - ZED - ph.02 | 9 | 9 | ORA - ZED - ph.029 | 44746 | 8712415.4916 | 177982654.5953 | 44781
ORA - ZED | 19 | 19 | ORA - ZED19 | 44740 | 20070332.8941 | 515365342.4846 | 44740
Rolling Mill #4-TRAESUEZ | 5 | 5 | Rolling Mill #4-TRAESUEZ5 | 44748 | 9905844.43 | 65158756.23
MDF Factory | 12 | 12 | MDF Factory12 | 44741 | 27509389.27 | 148407717.27
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 44747 | 13958441.79 | 144637429.79
HQ - CFC | 16 | 16 | HQ - CFC16 | 44727 | 8911604.3 | 191090691.3
Astoria - Sharm | 2 | 2 | Astoria - Sharm2 | 44748 | 1243970 | 1243970
Astoria Hotel | 6 | 6 | Astoria Hotel6 | 44748 | 14829494.3486 | 40064396
HQ - CFC | 17 | 17 | HQ - CFC17 | 44760 | 17076484.2 | 208167175.5
PKG#163 | 26 | 26 | PKG#16326 |  | 20328767.6537 | 156256035.2837 | 44823
PKG#177 | 41 | 41 | PKG#17741 |  | -11904090.5837 | 421526736.2263 | 44887
ORA - ZED - ph.02 | 10 | 10 | ORA - ZED - ph.0210 | 44773 | 25761823.8629 | 203744478.4582 | 44795
MDF Factory | 13 | 13 | MDF Factory13 | 44780 | 15343913.47 | 163751630.74
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 44796 | 8283062.84 | 152920492.63
EGAT-Lock & Load | 6 | 6 | EGAT-Lock & Load6 | 44748 | 3378839.59 | 16590728.1
Rolling Mill #4-TRAESUEZ | 6 | 6 | Rolling Mill #4-TRAESUEZ6 | 44780 | 5743581.36 | 70902337.59
ORA - ZED | 20 | 20 | ORA - ZED20 | 44780 | 25297815.7756 | 540663158.2602 | 44801
Mivida-PK#189 | 2 | 2 | Mivida-PK#1892 | 44779 | 28497042.4952 | 43820151.0286
Sodic Eastown - Landscape | 8 | 8 | Sodic Eastown - Landscape8 | 44769 | 19106378.3905 | 46943391.219
MDF Factory - Equip. | 8 | 8 | MDF Factory - Equip.8 | 44775 | 340101.34 | 11819751.78
Astoria - Sharm | 3 | 3 | Astoria - Sharm3 | 44782 | 401082.65 | 1645052.65
Astoria Hotel | 7 | 7 | Astoria Hotel7 | 44781 | 11030217.63 | 51094613.63
HQ - CFC | 18 | 18 | HQ - CFC18 | 44790 | 15625697.2 | 223792872.7
Katameya - Creeks | 20 | 20 | Katameya - Creeks20 | 44794 | 23863809.78 | 737934504.85
ORA - ZED | 21 | 21 | ORA - ZED21 | 44805 | 9295356.7831 | 549958515.0433 | 44815
Ring Road - Mounib | 17 | 17 | Ring Road - Mounib17 | 44783 | 6933306.55 | 469868783
ORA - ZED - ph.02 | 11 | 11 | ORA - ZED - ph.0211 | 44798 | 10555360.8465 | 214299839.3048 | 44818
MDF Factory | 14 | 14 | MDF Factory14 | 44810 | 12301138.79 | 176052769.53 | 44829
EGAT-Lock & Load | 7 | 7 | EGAT-Lock & Load7 | 44789 | 1415984.07 | 18006712.17
Mivida-PK#189 | 3 | 3 | Mivida-PK#1893 | 44808 | 24279069.6762 | 68099220.7048
Rolling Mill #4-TRAESUEZ | 7 | 7 | Rolling Mill #4-TRAESUEZ7 | 44797 | 16796950.93 | 87699288.52
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 44797 | 20298475.01 | 173218967.64
Astoria Hotel | 8 | 8 | Astoria Hotel8 | 44812 | 14516248.37 | 65610862
Astoria - Sharm | 4 | 4 | Astoria - Sharm4 | 44809 | 2440310 | 4085362.65
Katameya - Creeks | 21 | 21 | Katameya - Creeks21 | 44824 | 37145495.17 | 775080000.02
ORA - ZED | 22 | 22 | ORA - ZED22 | 44819 | 9997079.1377 | 559955594.181 | 44832
MDF Factory | 15 | 15 | MDF Factory15 | 44843 | 8651043.7332 | 184308580.87
HQ - CFC | 19 | 19 | HQ - CFC19 | 44850 | 11070593.3 | 234863466
EGAT-Lock & Load | 8 | 8 | EGAT-Lock & Load8 | 44815 | 2786604.1 | 20793316.27
Rolling Mill #4-TRAESUEZ | 8 | 8 | Rolling Mill #4-TRAESUEZ8 | 44831 | 18519200.97 | 106218489.49
Ring Road - Mounib | 18 | 18 | Ring Road - Mounib18 | 44816 | 4715315.145 | 474584098.145
ORA - ZED - ph.02 | 12 | 12 | ORA - ZED - ph.0212 | 44843 | 16545380.5429 | 230845219.8476 | 44846
New Giza Hospital | 9 | 9 | New Giza Hospital9 | 44826 | 23318711.12 | 196318952.57
Mivida-PK#189 | 4 | 4 | Mivida-PK#1894 | 44843 | 28546026.8476 | 96645247.5524
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 44844 | 14282809.35 | 187501776.99
Astoria Hotel | 9 | 9 | Astoria Hotel9 | 44830 | 10555127.63 | 76165989.63
Astoria Hotel | 10 | 10 | Astoria Hotel10 | 44840 | 9739259.16 | 85905248.79
ORA - ZED - ph.02 | 13 | 13 | ORA - ZED - ph.0213 | 44856 | 20581919.2571 | 251427139.1048
ORA - ZED | 23 | 23 | ORA - ZED23 | 44861 | 27314036.0095 | 587269630.1905
Astoria - Sharm | 5 | 5 | Astoria - Sharm5 | 44840 | 1055208 | 5140570.65
Sodic Eastown - Landscape | 9 | 9 | Sodic Eastown - Landscape9 | 44817 | 2763176 | 49706567.219
MDF Factory | 16 | 16 | MDF Factory16 | 44871 | 21753082.06 | 206061662.93
New Giza Hospital | 10 | 10 | New Giza Hospital10 | 44868 | 22254898.64 | 218573851.21
EGAT-Lock & Load | 9 | 9 | EGAT-Lock & Load9 | 44852 | 3980460.75 | 24773777.02
HQ - CFC | 20 | 20 | HQ - CFC20 | 44845 | 43687204.7 | 278550670.7 | 44851
Rolling Mill #4-TRAESUEZ | 9 | 9 | Rolling Mill #4-TRAESUEZ9 | 44872 | 17686791.21 | 123905280.7
Mivida-PK#189 | 5 | 5 | Mivida-PK#1895 | 44870 | 57245166.7876 | 153890414.34
PKG#163 | 29 | 29 | PKG#16329 |  | 17622733.92 | 181831948.65 | 44941
Astoria Hotel | 11 | 11 | Astoria Hotel11 | 44865 | 22454296.86 | 108359545.65
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 44888 | 16943574.98 | 204445351.97
Astoria - Sharm | 6 | 6 | Astoria - Sharm6 | 44864 | 314831.49 | 5455402.14
EGAT-Lock & Load | 10 | 10 | EGAT-Lock & Load10 | 44868 | 1157252.56 | 25931029.58
Astoria Hotel | 12 | 12 | Astoria Hotel12 | 44875 | 7707398.94 | 116066944.59
Rolling Mill #4-TRAESUEZ | 10 | 10 | Rolling Mill #4-TRAESUEZ10 | 44909 | 15395023.2 | 139300303.9
HQ - CFC | 21 | 21 | HQ - CFC21 | 44885 | 6969185.9 | 285519856.6
ORA - ZED - ph.02 | 14 | 14 | ORA - ZED - ph.0214 | 44910 | 19311587.7934 | 270738726.8982
MDF Factory | 17 | 17 | MDF Factory17 | 44888 | 3503748.7 | 209565411.63
Sodic Eastown - Landscape | 10 | 10 | Sodic Eastown - Landscape10 | 44854 | 1723810.5333 | 51430377.7524 | 44854
Sodic Eastown - Landscape | 11 | 11 | Sodic Eastown - Landscape11 | 44872 | 1095191.5143 | 52525569.2667 | 44880
New Giza Hospital | 11 | 11 | New Giza Hospital11 | 44902 | 29701638.2 | 248275489.41
Sodic Eastown - Landscape | 12 | 12 | Sodic Eastown - Landscape12 | 44885 | 1256657.1048 | 55165083.5048 | 44887
Mivida-PK#189 | 6 | 6 | Mivida-PK#1896 | 44900 | -0.0001 | 153890414.34
Astoria Hotel | 13 | 13 | Astoria Hotel13 | 44893 | 11273556.71 | 127340501.3
6TH October tunnel | 4 | 4 | 6TH October tunnel4 | 44878 | 7663602.64 | 12262958.79 | 44879
6TH October tunnel | 5 | 5 | 6TH October tunnel5 | 44882 | 6157467.55 | 17807278.45 | 44890
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 44914 | 13727755.25 | 218173107.22
MDF Factory | 18 | 18 | MDF Factory18 | 44906 | 4093790.13 | 213659201.76
EGAT-Lock & Load | 11 | 11 | EGAT-Lock & Load11 | 44902 | 1992889.65 | 27923919.23
Mivida-PK#189 | 7 | 7 | Mivida-PK#1897 | 44900 | 39773865.3076 | 193664279.6476
Katameya - Creeks | 24 | 24 | Katameya - Creeks24 | 44921 | 30975620.82 | 858923356.91
ORA - ZED - ph.02 | 15 | 15 | ORA - ZED - ph.0215 | 44915 | 14179983.4542 | 284918710.3524
New Giza Hospital | 12 | 12 | New Giza Hospital12 | 44924 | 25988546.64 | 274264036.05
Rolling Mill #4-TRAESUEZ | 11 | 11 | Rolling Mill #4-TRAESUEZ11 | 44943 | 16145745 | 155446048.9
Astoria Hotel | 14 | 14 | Astoria Hotel14 | 44915 | 13597376.25 | 140937877.55
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 44915 | 2611606.8286 | 2611606.8286
MDF Factory | 19 | 19 | MDF Factory19 | 44923 | 12077854.33 | 225737056.09
Wady Halfa | 1 | 1 | Wady Halfa1 | 44913 | 3078932.9 | 3078932.9
HQ - CFC | 24 | 24 | HQ - CFC24 | 44922 | 25568878.3 | 320704119.6
Mivida-PK#189 | 8 | 8 | Mivida-PK#1898 | 44927 | 90047890.8024 | 283712170.45
ORA - ZED | 24 | 24 | ORA - ZED24 | 44976 | 11751887.1042 | 599021517.2946 | 45007
MDF Factory | 20 | 20 | MDF Factory20 | 44938 | 10662163.65 | 236399219.74
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 44971 | 20329650.19 | 238502757.41
Astoria Hotel | 15 | 15 | Astoria Hotel15 | 44951 | 9032753.11 | 149970630.66
EGAT-Lock & Load | 12 | 12 | EGAT-Lock & Load12 | 44923 | 1778896.47 | 29702815.7
Katameya - Creeks | 25 | 25 | Katameya - Creeks25 | 44951 | 21870157.41 | 880793514.32
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 44959 | 3199345.21 | 3199345.21
ORA - ZED - ph.02 | 16 | 16 | ORA - ZED - ph.0216 | 44962 | 11487525.8247 | 296406236.1771
ORA - ZED - Landscape | 2 | 2 | ORA - ZED - Landscape2 | 44958 | 2071867.5333 | 4683474.3619
HQ - CFC | 25 | 25 | HQ - CFC25 | 44956 | 17887580.019 | 338591699.619
ORA - ZED | 25 | 25 | ORA - ZED25 | 45026 | 50310527.2958 | 649332044.5905
Mivida-PK#189 | 9 | 9 | Mivida-PK#1899 | 44950 | 42271935.09 | 325984105.54
New Giza Hospital | 13 | 13 | New Giza Hospital13 | 44963 | 24670486.27 | 298934522.32
Royal City | 42 | 42 | Royal City42 | 44970 | 7571387.8468 | 419210431.34
Rolling Mill #4-TRAESUEZ | 12 | 12 | Rolling Mill #4-TRAESUEZ12 | 44964 | 16694409.39 | 172140458.29
MDF Factory | 21 | 21 | MDF Factory21 | 44963 | 18933899.86 | 255333119.6
ORA - ZED - Landscape | 3 | 3 | ORA - ZED - Landscape3 | 44983 | 2138801.7905 | 6822276.1524
ORA - ZED - ph.02 | 17 | 17 | ORA - ZED - ph.0217 | 44994 | 9516947.0875 | 305923183.2647 | 45004
Port Said Silos - Local Supply | 1 | 1 | Port Said Silos - Local Supply1 | 45001 | 673851.6 | 673851.6
EGAT-Lock & Load | 13 | 13 | EGAT-Lock & Load13 | 44964 | 2116780.43 | 31819596.13
DPW - Ph.02 | 1 | 1 | DPW - Ph.021 | 44973 | 23907099.3 | 23907099.3
Katameya - Creeks | 26 | 26 | Katameya - Creeks26 | 44985 | 41254688.36 | 922048202.68
Mivida-PK#189 | 10 | 10 | Mivida-PK#18910 | 44983 | 29038558.46 | 355022664
HQ - CFC | 26 | 26 | HQ - CFC26 | 45337 | 15848994.2857 | 354440693.9048
MDF Factory | 22 | 22 | MDF Factory22 | 44982 | 3256087.31 | 258589206.91
Astoria Hotel | 16 | 16 | Astoria Hotel16 | 44982 | 9372213.83 | 159342844.49
New Giza Hospital | 14 | 14 | New Giza Hospital14 | 44999 | 21692266.85 | 320626789.17
Rolling Mill #4-TRAESUEZ | 13 | 13 | Rolling Mill #4-TRAESUEZ13 | 44993 | 14485776.58 | 186626234.87
Wady Halfa | 2 | 2 | Wady Halfa2 | 44971 | 23601516.1 | 26680449
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 45048 | 1797569.47 | 4996914.68
PKG#177 | 47 | 47 | PKG#17747 | 45141 | 21331767.9853 | 575446386.2553 | 45141
LEKELA | 16 | 16 | LEKELA16 | 45016 | -0.0001 | 207000000
ORA - ZED - ph.02 | 18 | 18 | ORA - ZED - ph.0218 | 45014 | 15495416.059 | 321418599.3237 | 45034
ORA - ZED - Landscape | 4 | 4 | ORA - ZED - Landscape4 | 45026 | 4909563.9143 | 11731840.0667
EIPICO | 4 | 4 | EIPICO4 | 45000 | 8374674.1725 | 42276520.7525
EGAT-Lock & Load | 14 | 14 | EGAT-Lock & Load14 | 44993 | 2768145.62 | 34587741.75
MDF Factory | 23 | 23 | MDF Factory23 | 45007 | 38888289.8 | 297477496.71
New Gas Station | 1 | 1 | New Gas Station1 | 45232 | 3190160 | 3190160
Mivida-PK#189 | 11 | 11 | Mivida-PK#18911 | 45026 | 23000800.56 | 378023464.56
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 45007 | 30365704.8 | 54272804.1
Astoria Hotel | 17 | 17 | Astoria Hotel17 | 45018 | 7818140.35 | 167160984.84
New Giza Hospital | 15 | 15 | New Giza Hospital15 | 45034 | 23725978.81 | 344352767.98
Wady Halfa | 3 | 3 | Wady Halfa3 | 45001 | 17962793.18 | 44643242.18
EIPICO | 5 | 5 | EIPICO5 | 45026 | 13210447.2775 | 55486968.03
Port Said Silos | 13 | 13 | Port Said Silos13 | 45018 | 612060.8329 | 80860263.08
MDF Factory | 24 | 24 | MDF Factory24 | 45046 | 18681389.16 | 316158885.87
DPW - Ph.02 | 3 | 3 | DPW - Ph.023 | 45012 | 1809093.47 | 56081897.57
Katameya - Creeks | 28 | 28 | Katameya - Creeks28 | 45050 | 26373696.19 | 972370839.89
ORA - ZED - ph.02 | 19 | 19 | ORA - ZED - ph.0219 | 45047 | 8053943.7501 | 329472543.0738
ORA - ZED - Landscape | 5 | 5 | ORA - ZED - Landscape5 | 45047 | 3861209.6 | 15593049.6667
Mivida-PK#189 | 12 | 12 | Mivida-PK#18912 | 45054 | 15682494.86 | 393705959.42
ORA - ZED | 26 | 26 | ORA - ZED26 | 45047 | 19434003.5361 | 668766048.1265
New Giza Hospital | 16 | 16 | New Giza Hospital16 | 45060 | 22492246.1 | 366845014.08
EIPICO | 6 | 6 | EIPICO6 | 45063 | 6910722.77 | 62397690.8
DPW - Ph.02 | 4 | 4 | DPW - Ph.024 | 45085 | 38567084.81 | 94648982.38
Katameya - Creeks | 29 | 29 | Katameya - Creeks29 | 45080 | 23994845.49 | 996365685.38
Mivida-PK#189 | 13 | 13 | Mivida-PK#18913 | 45083 | 16636045.76 | 410342005.18
ORA - ZED - Landscape | 6 | 6 | ORA - ZED - Landscape6 | 45084 | 3232045.3524 | 18825095.019
ORA - ZED - ph.02 | 20 | 20 | ORA - ZED - ph.0220 | 45078 | 4423045.841 | 333895588.9148
ORA - ZED | 27 | 27 | ORA - ZED27 | 45092 | 10662740.4195 | 679428788.546
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 45090 | 1174788.1 | 1174788.1
DPW - Ph.02 | 5 | 5 | DPW - Ph.025 | 45102 | 77833745.07 | 172482727.45
New Giza Hospital | 17 | 17 | New Giza Hospital17 | 45111 | 21612019.52 | 388457033.6
ORA - ZED - ph.02 | 21 | 21 | ORA - ZED - ph.0221 | 45116 | 4766150.0798 | 338661738.9946 | 45152
Astoria Hotel | 19 | 19 | Astoria Hotel19 | 45096 | 12873774.1358 | 190455674.5258
MDF Factory | 26 | 26 | MDF Factory26 | 45098 | 21011393.06 | 347654910.69
Mivida-PK#140 | 28 | 28 | Mivida-PK#14028 | 45365 | 924591.9704 | 174986240.73 | 45482
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 |  | 2879525.92 | 7876440.6
KSA-Tarek AbdelHakim Center | 2 | 2 | KSA-Tarek AbdelHakim Center2 | 45090 | 2619891.03 | 3794679.13
Mivida-PK#189 | 14 | 14 | Mivida-PK#18914 | 45122 | 22729528.92 | 433071534.1
Creeks - URBN K | 3 | 3 | Creeks - URBN K3 | 45095 | 40661954.88 | 71628367.6
ORA - ZED - Landscape | 7 | 7 | ORA - ZED - Landscape7 | 45124 | 1440674.7619 | 20265769.781
ORA - ZED | 28 | 28 | ORA - ZED28 | 45116 | 24304667.5968 | 703733456.1429
KSA-Tarek AbdelHakim Center | 3 | 3 | KSA-Tarek AbdelHakim Center3 | 45132 | 1124829.43 | 4919508.56
DPW - Ph.02 | 6 | 6 | DPW - Ph.026 | 45138 | 32227821.34 | 204710548.79
MDF Factory | 27 | 27 | MDF Factory27 | 45119 | 10160280.74 | 357815191.43
EIPICO | 8 | 8 | EIPICO8 | 45132 | 24151774.29 | 88477871.42 | 45169
ORA - ZED - Landscape | 8 | 8 | ORA - ZED - Landscape8 | 45147 | 11600772.2694 | 31866542.0504
Katameya - Creeks | 31 | 31 | Katameya - Creeks31 | 45138 | 34090513.58 | 1112307883.94
ORA - ZED - ph.02 | 22 | 22 | ORA - ZED - ph.0222 | 45147 | 11000140.3008 | 349661879.2913
New Giza Hospital | 18 | 18 | New Giza Hospital18 | 45144 | 9332664.78 | 397789698.38
Astoria Hotel | 20 | 20 | Astoria Hotel20 | 45140 | 3956219.0142 | 194411893.54
ORA - ZED | 29 | 29 | ORA - ZED29 | 45162 | 27532348.019 | 731265804.1619
MDF Factory | 28 | 28 | MDF Factory28 | 45138 | 4632219.77 | 362447411.2
Mivida-PK#189 | 15 | 15 | Mivida-PK#18915 | 45145 | 18379426.49 | 451450960.59
KSA-Tarek AbdelHakim Center | 4 | 4 | KSA-Tarek AbdelHakim Center4 | 45132 | 1181749.35 | 6101257.91
SMP1 - Revamp | 4 | 4 | SMP1 - Revamp4 | 45170 | 3836789.63 | 11713230.23
DPW - Ph.02 | 7 | 7 | DPW - Ph.027 | 45166 | 21546507.22 | 226257056.01
Astoria Hotel | 21 | 21 | Astoria Hotel21 | 45183 | 1422437.2 | 195834330.74
MDF Factory | 29 | 29 | MDF Factory29 | 45179 | 7201895.8 | 369649307
ORA - ZED - Landscape | 9 | 9 | ORA - ZED - Landscape9 | 45186 | 3994751.4353 | 35861293.4857
ORA - ZED - ph.02 | 23 | 23 | ORA - ZED - ph.0223 | 45186 | 1051681.4414 | 350713560.7327
New Giza Hospital | 19 | 19 | New Giza Hospital19 | 45183 | 18985757.51 | 416775455.89
ORA - ZED | 30 | 30 | ORA - ZED30 | 45186 | 26015241.1905 | 757281045.3524
Creeks - URBN K | 5 | 5 | Creeks - URBN K5 | 45161 | 21068069.1 | 118665999.82
Mivida-PK#189 | 16 | 16 | Mivida-PK#18916 | 45189 | 24459783.7762 | 475910744.3662
EIPICO | 10 | 10 | EIPICO10 | 45166 | 9818518.79 | 133296390.21 | 45228
Royal City - Landscape | 24 | 24 | Royal City - Landscape24 | 45173 | 3256136.08 | 110218542.31
Royal City | 43 | 43 | Royal City43 | 45173 | 13484961.26 | 432695392.6
DPW - Ph.02 | 8 | 8 | DPW - Ph.028 | 45173 | 27781672.69 | 254038728.7
EIPICO | 11 | 11 | EIPICO11 | 45209 | 27259074.64 | 160555464.85 | 45258
ORA - ZED - ph.02 | 24 | 24 | ORA - ZED - ph.0224 | 45186 | 1619984.7524 | 352333545.4851
MDF Factory | 30 | 30 | MDF Factory30 | 45188 | 42878737.92 | 412528044.92
Katameya - Creeks | 33 | 33 | Katameya - Creeks33 | 45200 | 61801377.92 | 1210803657.22
SMP1 - Revamp | 5 | 5 | SMP1 - Revamp5 | 45181 | 4135898.1 | 15849128.33
Creeks - URBN K | 6 | 6 | Creeks - URBN K6 | 45196 | 18829649.55 | 137495649.37
ORA - ZED | 31 | 31 | ORA - ZED31 | 45196 | 26102241.2286 | 783383286.581
ORA - ZED - Landscape | 10 | 10 | ORA - ZED - Landscape10 | 45209 | 3258480.2857 | 39119773.7714
MDF Factory - Local Fabrication | 15 | 15 | MDF Factory - Local Fabrication15 | 45278 | 5403242.47 | 47293093.98
DPW - Ph.02 | 9 | 9 | DPW - Ph.029 | 45230 | 66926760.56 | 320965489.26
MDF Factory | 31 | 31 | MDF Factory31 | 45206 | 26984773 | 439512817.92
EIPICO | 12 | 12 | EIPICO12 | 45251 | 13086699.85 | 173642164.7 | 45293
ORA - ZED - Landscape | 11 | 11 | ORA - ZED - Landscape11 | 45234 | 6742108.1048 | 45861881.8762
Katameya - Creeks | 34 | 34 | Katameya - Creeks34 | 45232 | 67431952.34 | 1278235609.56
ORA - ZED - ph.02 | 25 | 25 | ORA - ZED - ph.0225 | 45237 | 1429470.734 | 353763016.219
New Giza Hospital | 20 | 20 | New Giza Hospital20 | 45202 | -1e-07 | 416775455.89
Astoria Hotel | 22 | 22 | Astoria Hotel22 | 45208 | 13661357.26 | 209495688 | 45213
ORA - ZED | 32 | 32 | ORA - ZED32 | 45241 | 24532813.9714 | 807916100.5524
MDF Factory | 32 | 32 | MDF Factory32 | 45225 | 2754000 | 442266817.92
Mivida-PK#189 | 17 | 17 | Mivida-PK#18917 | 45216 | 30434807.7338 | 506345552.1
Port Said Silos | 20 | 20 | Port Said Silos20 | 45231 | 13732229.2267 | 152603544.64 | 45252
DPW - Ph.02 | 10 | 10 | DPW - Ph.0210 | 45259 | 59028304.35 | 379993793.61
Astoria Hotel | 23 | 23 | Astoria Hotel23 | 45253 | 13277404.55 | 219912624
MDF Factory | 33 | 33 | MDF Factory33 | 45255 | 20665276.54 | 462932094.46
Katameya - Creeks | 35 | 35 | Katameya - Creeks35 | 45266 | 61247331.12 | 1339482940.68
ORA - ZED - Landscape | 12 | 12 | ORA - ZED - Landscape12 | 45250 | 9303031.3714 | 55164913.2476
ORA - ZED - ph.02 | 26 | 26 | ORA - ZED - ph.0226 | 45274 | 3475331.4095 | 357238347.6286
ORA - ZED | 33 | 33 | ORA - ZED33 | 45277 | 20642302.219 | 828558402.7714
Mivida-PK#189 | 18 | 18 | Mivida-PK#18918 | 45262 | 18563752.6 | 524909304.7
Sokhna Port Expansion | 20 | 20 | Sokhna Port Expansion20 | 45224 | 20920498.28 | 877286055.98 | 45250
New Giza Hospital | 21 | 21 | New Giza Hospital21 | 45215 | 12758386.3 | 429533842.19
Sokhna Port Expansion- 100m | 5 | 5 | Sokhna Port Expansion- 100m5 | 45224 | 4703266.4897 | 126862233.53 | 45250
Baraka Land Fence | 1 | 1 | Baraka Land Fence1 | 45236 | 3575400 | 3575400
New Giza Hospital | 22 | 22 | New Giza Hospital22 | 45260 | 18598623.84 | 448132466.03
Sokhna Port Expansion | 21 | 21 | Sokhna Port Expansion21 | 45287 | 9034186.8 | 886320242.78 | 45287
SMP1 - Revamp | 7 | 7 | SMP1 - Revamp7 | 45251 | 4571797.25 | 29278987.27
Port Said Silos | 21 | 21 | Port Said Silos21 | 45260 | 15886446.6567 | 167746546.07 | 45283
DPW - Ph.02 | 11 | 11 | DPW - Ph.0211 | 45291 | 54711779.1 | 434705572.71
EIPICO | 13 | 13 | EIPICO13 | 45281 | 50645387.03 | 224287551.73 | 45292
Mivida-PK#189 | 19 | 19 | Mivida-PK#18919 | 45293 | 21710553.3095 | 546619858.0095
MDF Factory | 34 | 34 | MDF Factory34 | 45280 | 25469525.62 | 488401620.08
Katameya - Creeks | 36 | 36 | Katameya - Creeks36 | 45290 | 74463161.12 | 1413946101.8
New Giza Hospital | 23 | 23 | New Giza Hospital23 | 45318 | 9056705.71 | 457189171.74
Port Said Silos | 22 | 22 | Port Said Silos22 | 45274 | 6713332.669 | 174459878.73 | 45287
ORA - ZED | 34 | 34 | ORA - ZED34 | 45319 | 14702199.581 | 843260602.3524
ORA - ZED - ph.02 | 27 | 27 | ORA - ZED - ph.0227 | 45305 | 3041219.2755 | 360279566.9041
MDF Factory - Equip. | 21 | 21 | MDF Factory - Equip.21 | 45285 | 540952.41 | 22578347.52 | 45328
KSA-Tarek AbdelHakim Center | 11 | 11 | KSA-Tarek AbdelHakim Center11 | 45295 | 6272151.58 | 34906557.56
MDF Factory | 35 | 35 | MDF Factory35 | 45312 | 7460561 | 495862181.08
DPW - Ph.02 | 12 | 12 | DPW - Ph.0212 | 45326 | 17644384.08 | 452349956.79
Mivida-PK#189 | 20 | 20 | Mivida-PK#18920 | 45302 | -0.0003 | 546619858.0095
Mivida-PK#189 | 21 | 21 | Mivida-PK#18921 | 45315 | 22586754.7048 | 569206612.7143
EIPICO | 14 | 14 | EIPICO14 | 45326 | 69127444.9 | 293414996.63 | 45358
Katameya - Creeks | 37 | 37 | Katameya - Creeks37 | 45313 | 53331460.14 | 1467277561.94
ORA - ZED | 35 | 35 | ORA - ZED35 | 45333 | 13918410.7524 | 857179013.1048
Creeks - URBN K | 10 | 10 | Creeks - URBN K10 | 45326 | 21707049.44 | 217734751.99 | 45366
ORA - ZED - ph.02 | 28 | 28 | ORA - ZED - ph.0228 | 45354 | 5861894.8952 | 366141461.7993
ORA - ZED - Landscape | 13 | 13 | ORA - ZED - Landscape13 | 45342 | -692002.6286 | 54472910.619
ORA - ZED - Landscape | 14 | 14 | ORA - ZED - Landscape14 | 45371 | 1197004.6952 | 55669915.3143
EIPICO | 15 | 15 | EIPICO15 | 45371 | 41894786.25 | 335309782.88
Mivida-PK#189 | 22 | 22 | Mivida-PK#18922 | 45349 | 23140993.5357 | 592347606.25
MDF Factory | 36 | 36 | MDF Factory36 | 45350 | 24220349.75 | 520082530.83
ORA - ZED - Landscape | 15 | 15 | ORA - ZED - Landscape15 | 45402 | 3753240.219 | 59423155.5333
Katameya - Creeks | 38 | 38 | Katameya - Creeks38 | 45357 | 83842743.6 | 1551120305.54
ORA - ZED | 36 | 36 | ORA - ZED36 | 45363 | 9427629.6762 | 866606642.781
ORA - ZED - ph.02 | 29 | 29 | ORA - ZED - ph.0229 | 45385 | 2577878.9747 | 368719340.774 | 45397
New Giza Hospital | 24 | 24 | New Giza Hospital24 | 45383 | 30645299.93 | 487834471.67
Creeks - URBN K | 11 | 11 | Creeks - URBN K11 | 45361 | 19399852.91 | 247787306.4
Rabigh Ext. - Piles | 1 | 1 | Rabigh Ext. - Piles1 | 45369 | 1098993.1 | 1098993.1
Mivida-PK#189 | 23 | 23 | Mivida-PK#18923 | 45403 | 30858954.27 | 623206560.52
ORA - ZED - Landscape | 16 | 16 | ORA - ZED - Landscape16 | 45381 | 1773392.8381 | 61196548.3714
DPW - Ph.02 | 13 | 13 | DPW - Ph.0213 | 45383 | 13655091.11 | 466005047.9
Katameya - Creeks | 39 | 39 | Katameya - Creeks39 | 45384 | 81688930.92 | 1632809236.46
MDF Factory | 37 | 37 | MDF Factory37 | 45384 | 18799337.86 | 538881868.69
ORA - ZED | 37 | 37 | ORA - ZED37 | 45388 | 11141064.9524 | 877747707.7333 | 45406
Port Said Silos - Local Supply | 3 | 3 | Port Said Silos - Local Supply3 | 45364 | 3085091.6309 | 4953919.88 | 45382
DPW - Ph.02 | 14 | 14 | DPW - Ph.0214 | 45426 | -0.0001 | 466005047.9
Creeks - URBN K | 12 | 12 | Creeks - URBN K12 | 45385 | 13939506.69 | 261726813.09
ORA - ZED - ph.02 | 30 | 30 | ORA - ZED - ph.0230 | 45385 | 2066668.4036 | 370786009.1777 | 45411
EIPICO | 16 | 16 | EIPICO16 | 45406 | 54812520.11 | 390122302.99
New Giza Hospital | 25 | 25 | New Giza Hospital25 | 45296 | 12955562.12 | 500790033.79
ORA - ZED - Landscape | 17 | 17 | ORA - ZED - Landscape17 | 45419 | 1582674.7048 | 62779223.0762 | 45410
ORA - ZED | 38 | 38 | ORA - ZED38 | 45421 | 15909843.4381 | 893657551.1714
MDF Factory | 38 | 38 | MDF Factory38 | 45406 | 25264630.57 | 564146499.26
Port Said Silos - Local Supply | 4 | 4 | Port Said Silos - Local Supply4 | 45389 | 4365732.3293 | 9319652.21 | 45419
ORA - ZED - ph.02 | 31 | 31 | ORA - ZED - ph.0231 | 45419 | 7992050.6 | 378778059.7777 | 45427
Mivida-PK#189 | 24 | 24 | Mivida-PK#18924 | 45434 | 16112816.1181 | 639319376.6381
Port Said Silos | 27 | 27 | Port Said Silos27 | 45413 | 1478728.71 | 191022414.13 | 45439
Rabigh Ext. - Piles | 2 | 2 | Rabigh Ext. - Piles2 | 45414 | 1361202.3 | 2460195.4
ORA - ZED - Landscape | 18 | 18 | ORA - ZED - Landscape18 | 45426 | 1979868.8571 | 64759091.9333
ORA - ZED - ph.02 | 32 | 32 | ORA - ZED - ph.0232 | 45448 | 2766734.981 | 381544794.7714
MDF Factory | 39 | 39 | MDF Factory39 | 45434 | 17461783.47 | 581608282.73
Katameya - Creeks | 41 | 41 | Katameya - Creeks41 | 45437 | 47455342.03 | 1746847240.53
ORA - ZED | 39 | 39 | ORA - ZED39 | 45449 | 9971577.2286 | 903629128.4
Mivida-PK#189 | 25 | 25 | Mivida-PK#18925 | 45449 | 29437278.3119 | 668756654.95
New Giza Hospital | 26 | 26 | New Giza Hospital26 | 45456 | 15191903.43 | 515981937.22
EIPICO | 17 | 17 | EIPICO17 | 45456 | 30260072.01 | 420382375
Port Said Silos - Local Supply | 5 | 5 | Port Said Silos - Local Supply5 | 45424 | 3278709.276 | 12598361.49 | 45439
Port Said Silos | 28 | 28 | Port Said Silos28 | 45445 | 3335653.5067 | 194402004.06 | 45474
ORA - ZED - Landscape | 19 | 19 | ORA - ZED - Landscape19 | 45480 | 1453055.0476 | 66212146.981
ORA - ZED - ph.02 | 33 | 33 | ORA - ZED - ph.0233 | 45474 | 6575447.0667 | 388120241.8381
ORA - ZED | 40 | 40 | ORA - ZED40 | 45474 | 7576454.8952 | 911205583.2952
Katameya - Creeks | 42 | 42 | Katameya - Creeks42 | 45480 | 56995945.47 | 1803843186
Port Said Silos - Local Supply | 6 | 6 | Port Said Silos - Local Supply6 | 45452 | 1064669.3953 | 13663030.89 | 45474
Rabigh Ext. - Piles | 4 | 4 | Rabigh Ext. - Piles4 | 45481 | 2071949.5 | 5652409
Creeks - URBN K | 15 | 15 | Creeks - URBN K15 | 45455 | 15151516.49 | 306639839.44
Baraka Land Fence | 4 | 4 | Baraka Land Fence4 | 45433 | 11760884 | 49997280
SMP1 - Revamp | 10 | 10 | SMP1 - Revamp10 | 45447 | 5011477.79 | 38750521.78
Mivida-PK#189 | 26 | 26 | Mivida-PK#18926 | 45476 | 16876594.42 | 685633249.37
EIPICO | 18 | 18 | EIPICO18 | 45503 | 61471115.83 | 481853490.83
ORA - ZED - ph.02 | 34 | 34 | ORA - ZED - ph.0234 | 45510 | 1412666.8095 | 389532908.6476
ORA - ZED - Landscape | 20 | 20 | ORA - ZED - Landscape20 | 45496 | 1399335.6857 | 67611482.6667
MDF Factory | 42 | 42 | MDF Factory42 | 45497 | 750284.2 | 608911678.68
Port Said Silos | 29 | 29 | Port Said Silos29 | 45481 | 2063726.5038 | 196509667 | 45511
Mivida-PK#189 | 27 | 27 | Mivida-PK#18927 | 45505 | 14919836.13 | 700553085.5
Katameya - Creeks | 43 | 43 | Katameya - Creeks43 | 45500 | 56437240.4362 | 1860280426.4362
Creeks - URBN K | 16 | 16 | Creeks - URBN K16 | 45502 | 8934038.52 | 315573877.96
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 45435 | 3172518.7149 | 3172518.7149
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 45525 | 2298644.2851 | 5471163
New Giza Hospital | 27 | 27 | New Giza Hospital27 | 45522 | 16227230.2 | 532209167.42
ORA - ZED | 41 | 41 | ORA - ZED41 | 45535 | 4542501.819 | 915748085.1143
Port Said Silos - Local Supply | 7 | 7 | Port Said Silos - Local Supply7 | 45491 | 5552464.1105 | 19215495 | 45510
Mivida-PK#189 | 28 | 28 | Mivida-PK#18928 | 45535 | 3487392.66 | 704040478.16
Rabigh Ext. -Building | 2 | 2 | Rabigh Ext. -Building2 | 45529 | 5727560.34 | 8289315.69
Port Said Silos | 30 | 30 | Port Said Silos30 | 45509 | 3191369.04 | 199701036.04 | 45526
MDF Factory | 43 | 43 | MDF Factory43 | 45525 | 11210135.32 | 620121814
ORA - ZED | 42 | 42 | ORA - ZED42 | 45536 | 5377971.181 | 921126056.2952
ORA - ZED - ph.02 | 35 | 35 | ORA - ZED - ph.0235 | 45535 | 7262978.339 | 396795886.9866
Katameya - Creeks | 44 | 44 | Katameya - Creeks44 | 45535 | 49427006.6938 | 1909707433.13
Creeks - URBN K | 17 | 17 | Creeks - URBN K17 | 45540 | 8615746.66 | 324189624.62
ORA - ZED - Landscape | 21 | 21 | ORA - ZED - Landscape21 | 45540 | 422349.9905 | 68033832.6571
ORA - ZED - ph.02 | 36 | 36 | ORA - ZED - ph.0236 | 45540 | 0.003893 | 396795886.9905
EIPICO | 19 | 19 | EIPICO19 | 45557 | 35463786.17 | 517317277 | 45591
Red Sea Museum | 3 | 3 | Red Sea Museum3 | 45537 | 1331566 | 6802729
MDF Factory | 44 | 44 | MDF Factory44 | 45561 | 10205950.6 | 630327764.6
ORA - ZED - Landscape | 22 | 22 | ORA - ZED - Landscape22 | 45551 | 4226377.8476 | 72260210.5048
ORA - ZED - ph.02 | 37 | 37 | ORA - ZED - ph.0237 | 45572 | 12000518.9238 | 408796405.9143
ORA - ZED | 43 | 43 | ORA - ZED43 | 45557 | 11538786.4 | 932664842.6952
Rabigh Ext. -Building | 3 | 3 | Rabigh Ext. -Building3 | 45554 | 5121658.33 | 13410974.02
Creeks - URBN K | 18 | 18 | Creeks - URBN K18 | 45560 | 9557078 | 333746702.62
Baraka Land Fence | 5 | 5 | Baraka Land Fence5 | 45524 | 7617134 | 57614414
New Giza Hospital | 28 | 28 | New Giza Hospital28 | 45568 | 69437921.36 | 601647088.78
Mivida-PK#189 | 29 | 29 | Mivida-PK#18929 | 45561 | 369049.79 | 704409527.95
ORA - ZED - ph.02 | 38 | 38 | ORA - ZED - ph.0238 | 45572 | -0.0095238 | 408796405.9048
ORA - ZED - ph.02 | 39 | 39 | ORA - ZED - ph.0239 | 45605 | 13783192.8762 | 422579598.781
ORA - ZED | 44 | 44 | ORA - ZED44 | 45580 | 5304711.9524 | 937969554.6476
ORA - ZED - Landscape | 23 | 23 | ORA - ZED - Landscape23 | 45580 | 1124749.1714 | 73384959.6762
Rabigh Ext. -Building | 4 | 4 | Rabigh Ext. -Building4 | 45588 | 6246650.22 | 19657624.24
MDF Factory | 45 | 45 | MDF Factory45 | 45600 | 16259922.8 | 646587687.4
Katameya - Creeks | 46 | 46 | Katameya - Creeks46 | 45600 | 42454238 | 2019963202
Creeks - URBN K | 19 | 19 | Creeks - URBN K19 | 45598 | 6248543.66 | 339995246.28
Mivida-PK#189 | 30 | 30 | Mivida-PK#18930 | 45608 | 17653522.66 | 722063050.61

## consultant-net (hidden)
Project | Invoice No. | invoice round down | concact | Approval Date (By Consultant) | Monthly Amount Approved (By Consultant)
PK #107 | 9 | 9 | PK #1079 | 43061 | 1418090.5
JICA | 19 | 19 | JICA19 | 43038 | 1141675.91
FIEM | 210 | 210 | FIEM210 | 43031 | 1524934.13
Cement Plant | 15 | 15 | Cement Plant15 | 43054 | 6696657.1239
PI Parks - ELSEWEDY | 1 | 1 | PI Parks - ELSEWEDY1 | 43038 | 5549711.3149
PI Parks - ELSEWEDY | 2 | 2 | PI Parks - ELSEWEDY2 | 43061 | 4153538.7944
Sodic Club House | 24 | 24 | Sodic Club House24 | 43065 | 4713913.05
Royal City | 2 | 2 | Royal City2 | 43019 | 5203476.09
Royal City | 3 | 3 | Royal City3 | 43048 | 8396278.07
Uptown PK #62 | 8 | 8 | Uptown PK #628 | 43047 | 2970870.89
Uptown PK #53 | 25 | 25 | Uptown PK #5325 | 43052 | 12023138.6423
Uptown PK #53 | 26 | 26 | Uptown PK #5326 | 43088 | 12833527.9648
PK #107 | 10 | 10 | PK #10710 | 43093 | 1453205.39
PI Parks - ELSEWEDY | 3 | 3 | PI Parks - ELSEWEDY3 | 43092 | 1754857.27
Uptown PK #62 | 9 | 9 | Uptown PK #629 | 43087 | 2124952.16
Sodic Club House | 25 | 25 | Sodic Club House25 | 43106 | 1796642.04
SIEMENS - Sokhna | 2 | 2 | SIEMENS - Sokhna2 | 43116 | 3059283.73
PK #107 | 11 | 11 | PK #10711 | 43115 | 2604921.36
Uptown PK #62 | 10 | 10 | Uptown PK #6210 | 43118 | 2207449.91
Uptown PK #53 | 27 | 27 | Uptown PK #5327 | 43108 | 9723398.7945
Royal City | 5 | 5 | Royal City5 | 43122 | 6381832.9445
PI Parks - ELSEWEDY | 4 | 4 | PI Parks - ELSEWEDY4 | 43131 | 3155027.6241
Sodic Club House | 26 | 26 | Sodic Club House26 | 43138 | 3193789.29
Uptown PK #53 | 28 | 28 | Uptown PK #5328 | 43135 | 7567160.0657
Uptown PK #62 | 11 | 11 | Uptown PK #6211 | 43138 | 1516852.746
PI Parks - ELSEWEDY | 5 | 5 | PI Parks - ELSEWEDY5 | 43170 | 1692874.42
SIEMENS - Sokhna | 3 | 3 | SIEMENS - Sokhna3 | 43136 | 7201577.05
PK #117 | 2 | 2 | PK #1172 | 43152 | 6466420.97
Uptown PK #53 | 29 | 29 | Uptown PK #5329 | 43157 | 10749580.8339
NGU 2 | 26 | 26 | NGU 226 | 43131 | 3027155.9789
Uptown PK #62 | 12 | 12 | Uptown PK #6212 | 43177 | 1565019.15
Sodic Club House | 27 | 27 | Sodic Club House27 | 43169 | 4891559.01
SIEMENS - Sokhna | 4 | 4 | SIEMENS - Sokhna4 | 43173 | 11065687.7
PK #117 | 3 | 3 | PK #1173 | 43173 | 4502026.52
PI Parks - ELSEWEDY | 6 | 6 | PI Parks - ELSEWEDY6 | 43201 | 306624.33
PK #107 | 13 | 13 | PK #10713 | 43192 | 2462800.95
Uptown PK #53 | 30 | 30 | Uptown PK #5330 | 43188 | 9526356.8077
Sodic Club House | 28 | 28 | Sodic Club House28 | 43194 | 4314232.28
Uptown PK #62 | 13 | 13 | Uptown PK #6213 | 43208 | 3417923.56
PK #117 | 4 | 4 | PK #1174 | 43200 | 3740180.271
Royal City | 6 | 6 | Royal City6 | 43214 | 11493260.03
PI Parks - ELSEWEDY | 7 | 7 | PI Parks - ELSEWEDY7 | 43211 | 1938615.93
SIEMENS - Sokhna | 5 | 5 | SIEMENS - Sokhna5 | 43205 | 13218163.55
PK #107 | 14 | 14 | PK #10714 | 43219 | 166316.41
Mintra | 1 | 1 | Mintra1 | 43361 | 2860852.09
Uptown PK #53 | 31 | 31 | Uptown PK #5331 | 43220 | 6774937.5373
PK #117 | 5 | 5 | PK #1175 | 43227 | 4762507.55
Royal City | 7 | 7 | Royal City7 | 43242 | 8439569.37
PK #107 | 15 | 15 | PK #10715 | 43241 | 1406606.27
SIEMENS - Sokhna | 6 | 6 | SIEMENS - Sokhna6 | 43240 | 7060448.908
PI Parks - ELSEWEDY | 8 | 8 | PI Parks - ELSEWEDY8 | 43237 | 1633991.6379
Uptown PK #53 | 32 | 32 | Uptown PK #5332 | 43249 | 2387351.5744
Al Jazi | 1 | 1 | Al Jazi1 | 43249 | 2462056.64
PK #117 | 6 | 6 | PK #1176 | 43272 | 5347404.79
Royal City | 8 | 8 | Royal City8 | 43275 | 7600061.0338
SIEMENS - Sokhna | 7 | 7 | SIEMENS - Sokhna7 | 43285 | 8833159.82
PI Parks - ELSEWEDY | 9 | 9 | PI Parks - ELSEWEDY9 | 43263 | 1607545.8276
Uptown PK #53 | 33 | 33 | Uptown PK #5333 | 43284 | 3964599.8564
PI Parks - ELSEWEDY | 10 | 10 | PI Parks - ELSEWEDY10 | 43303 | 3824599.4146
PK #117 | 7 | 7 | PK #1177 | 43464 | 119713.18
Al Jazi | 2 | 2 | Al Jazi2 | 43262 | 3686157.94
SIEMENS - Sokhna | 8 | 8 | SIEMENS - Sokhna8 | 43300 | 12641621.4
Sodic Club House | 31 | 31 | Sodic Club House31 | 43305 | 4843252.93
Al Jazi | 3 | 3 | Al Jazi3 | 43292 | 3748572.21
Royal City | 9 | 9 | Royal City9 | 43307 | 6018082.2865
Uptown PK #53 | 34 | 34 | Uptown PK #5334 | 43307 | 1431626.0807
Al Jazi | 4 | 4 | Al Jazi4 | 43305 | 4444997.23
Mintra | 2 | 2 | Mintra2 | 43366 | 1791407.73
Sodic Club House | 32 | 32 | Sodic Club House32 | 43328 | 5655167.4
PI Parks - ELSEWEDY | 11 | 11 | PI Parks - ELSEWEDY11 | 43320 | 442152.4951
SIEMENS - Sokhna | 9 | 9 | SIEMENS - Sokhna9 | 43346 | 13673026.82
PSP Substation | 3 | 3 | PSP Substation3 | 43384 | 1834172.07
Royal City | 10 | 10 | Royal City10 | 43339 | 5554331.9836
Al Jazi | 5 | 5 | Al Jazi5 | 43325 | 4854984.5363
Uptown PK #62 | 15 | 15 | Uptown PK #6215 | 43349 | 2299870.97
Uptown PK #53 | 35 | 35 | Uptown PK #5335 | 43355 | 2488623.0127
Al Jazi | 6 | 6 | Al Jazi6 | 43353 | 2965400.21
Sodic Club House | 33 | 33 | Sodic Club House33 | 43368 | 7190786.09
PI Parks - ELSEWEDY | 12 | 12 | PI Parks - ELSEWEDY12 | 43369 | 1530660.1341
El Sewedy Uni.-PKG.1 | 1 | 1 | El Sewedy Uni.-PKG.11 | 43388 | 2002513.1
SIEMENS - Sokhna | 10 | 10 | SIEMENS - Sokhna10 | 43368 | 6271528.33
Royal City | 11 | 11 | Royal City11 | 43367 | 3237608.64
Uptown PK #53 | 36 | 36 | Uptown PK #5336 | 43376 | 4689979.7631
Mintra | 3 | 3 | Mintra3 | 43388 | 2220782.14
PK #107 | 17 | 17 | PK #10717 | 43394 | 763627.7
El Sewedy Uni.-PKG.2 | 1 | 1 | El Sewedy Uni.-PKG.21 | 43391 | 3110956.56
PI Parks - MEP | 1 | 1 | PI Parks - MEP1 | 43383 | 7818631.64
SIEMENS - Sokhna | 11 | 11 | SIEMENS - Sokhna11 | 43409 | 5230123.66
Al Jazi | 7 | 7 | Al Jazi7 | 43383 | 5019788.5
PI Parks - ELSEWEDY | 13 | 13 | PI Parks - ELSEWEDY13 | 43383 | 716605.5327
Royal City | 12 | 12 | Royal City12 | 43397 | 7860724.87
Uptown PK #62 | 16 | 16 | Uptown PK #6216 | 43429 | 931895.88
Sodic Club House | 34 | 34 | Sodic Club House34 | 43404 | 10029446.47
Mintra-Hanger 1200m2 | 1 | 1 | Mintra-Hanger 1200m21 | 43402 | 531998.6721
El Sewedy Uni.-PKG.1 | 2 | 2 | El Sewedy Uni.-PKG.12 | 43398 | 951383.3
Uptown PK #53 | 37 | 37 | Uptown PK #5337 | 43450 | 1753673.2424
Mintra | 4 | 4 | Mintra4 | 43422 | 2907075.5801
Al Jazi | 8 | 8 | Al Jazi8 | 43410 | 7730375.21
Royal City | 13 | 13 | Royal City13 | 43425 | 5548576.504
PI Parks - ELSEWEDY | 14 | 14 | PI Parks - ELSEWEDY14 | 43419 | 1986968.45
PI Parks - MEP | 2 | 2 | PI Parks - MEP2 | 43419 | 3978690.02
El Sewedy Uni.-PKG.1 | 3 | 3 | El Sewedy Uni.-PKG.13 | 43431 | 1214989.1272
El Sewedy Uni.-PKG.2 | 2 | 2 | El Sewedy Uni.-PKG.22 | 43412 | 6088678.96
Al Jazi | 9 | 9 | Al Jazi9 | 43432 | 3297350.06
El Sewedy Uni.-PKG.1 | 4 | 4 | El Sewedy Uni.-PKG.14 | 43444 | 1204112.8596
Royal City | 14 | 14 | Royal City14 | 43463 | 13062023.4527
PK #117 | 8 | 8 | PK #1178 | 43464 | 3896343.98
PI Parks - MEP | 3 | 3 | PI Parks - MEP3 | 43449 | 4042223.64
PI Parks - ELSEWEDY | 15 | 15 | PI Parks - ELSEWEDY15 | 43449 | 5773335.65
El Sewedy Uni.-PKG.1 | 5 | 5 | El Sewedy Uni.-PKG.15 | 43452 | 185635.0557
Al Jazi | 10 | 10 | Al Jazi10 | 43453 | 3398127.58
Al Jazi | 11 | 11 | Al Jazi11 | 43473 | 4227710.49
El Sewedy Uni.-PKG.2 | 4 | 4 | El Sewedy Uni.-PKG.24 | 43475 | 3208255.2815
PKG#144 | 2 | 2 | PKG#1442 | 43485 | 2532120.6
El Sewedy Uni.-PKG.1 | 6 | 6 | El Sewedy Uni.-PKG.16 | 43473 | 142702.1677
PK #117 | 9 | 9 | PK #1179 | 43495 | 2578109.66
Sodic Club House | 35 | 35 | Sodic Club House35 | 43434 | 6956090.906
PI Parks - MEP | 4 | 4 | PI Parks - MEP4 | 43479 | 3514249.7617
PI Parks - ELSEWEDY | 16 | 16 | PI Parks - ELSEWEDY16 | 43479 | 5768808.1936
DP World Sokhna-AP | 1 | 1 | DP World Sokhna-AP1 | 43472 | 241563831.68
Royal City | 15 | 15 | Royal City15 | 43485 | 9343372.736
SIEMENS - Sokhna | 16 | 16 | SIEMENS - Sokhna16 | 43485 | 25271545.73
El Sewedy Uni.-PKG.1 | 7 | 7 | El Sewedy Uni.-PKG.17 | 43487 | 284879.76
Uptown PK #53 | 38 | 38 | Uptown PK #5338 | 43514 | 1048789.58
Al Jazi | 12 | 12 | Al Jazi12 | 43500 | 2264521.51
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 43544 | 6785088.5699
PK #117 | 10 | 10 | PK #11710 | 43506 | 147972.1048
PKG#101 | 1 | 1 | PKG#1011 | 43508 | 1124562.5468
El Sewedy Uni.-PKG.2 | 5 | 5 | El Sewedy Uni.-PKG.25 | 43506 | 4527299.6695
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 43514 | 1727255.5662
El Sewedy Uni.-PKG.1 | 8 | 8 | El Sewedy Uni.-PKG.18 | 43502 | 235901.6556
PI Parks - MEP | 5 | 5 | PI Parks - MEP5 | 43512 | 6241537.12
SIEMENS - Sokhna | 17 | 17 | SIEMENS - Sokhna17 | 43577 | 20418831.59
PI Parks - ELSEWEDY | 17 | 17 | PI Parks - ELSEWEDY17 | 43512 | 3296251.57
Royal City | 16 | 16 | Royal City16 | 43521 | 10141562.9942
Al Jazi | 13 | 13 | Al Jazi13 | 43528 | 3848045.61
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 43515 | 3185421.0011
El Sewedy Uni.-PKG.2 | 6 | 6 | El Sewedy Uni.-PKG.26 | 43535 | 7457797.2
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 43536 | 5785718.6
PI Parks - MEP | 6 | 6 | PI Parks - MEP6 | 43541 | 2455515.29
PKG#101 | 2 | 2 | PKG#1012 | 43543 | 2222206.65
Royal City | 17 | 17 | Royal City17 | 43556 | 6226878.8549
PI Parks - ELSEWEDY | 18 | 18 | PI Parks - ELSEWEDY18 | 43541 | 5638741.9194
Al Jazi | 14 | 14 | Al Jazi14 | 43563 | 1995238.89
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 43563 | 909309.25
El Sewedy Uni.-PKG.1 | 9 | 9 | El Sewedy Uni.-PKG.19 | 43565 | 72777.3
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 43565 | 1785483.1
PI Parks - MEP | 7 | 7 | PI Parks - MEP7 | 43572 | 4844170.7079
PSP Substation | 10 | 10 | PSP Substation10 | 43578 | 3808343.08
Royal City | 18 | 18 | Royal City18 | 43573 | 6196039.396
Uptown PK #53 | 39 | 39 | Uptown PK #5339 | 43576 | 929614.0301
El Sewedy Uni.-PKG.2 | 7 | 7 | El Sewedy Uni.-PKG.27 | 43565 | 2278076.6
PKG#101 | 3 | 3 | PKG#1013 | 43578 | 2379437.34
PI Parks - ELSEWEDY | 19 | 19 | PI Parks - ELSEWEDY19 | 43572 | 4754946.3629
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 43573 | 15652355.21
El Sewedy Uni.-PKG.3 | 5 | 5 | El Sewedy Uni.-PKG.35 | 43590 | 24218860.6
PI Parks - MEP | 8 | 8 | PI Parks - MEP8 | 43604 | 1686090.7908
SIEMENS - Sokhna | 18 | 18 | SIEMENS - Sokhna18 |  | 15000000
Al Jazi | 15 | 15 | Al Jazi15 | 43594 | 2738501.15
PI Parks - ELSEWEDY | 20 | 20 | PI Parks - ELSEWEDY20 | 43604 | 1816746.614
Royal City | 19 | 19 | Royal City19 | 43608 | 10933183.0202
Al Jazi | 16 | 16 | Al Jazi16 | 43617 | 1009779.23
Al Jazi - Center Zone | 2 | 2 | Al Jazi - Center Zone2 | 43614 | 2035039.03
PKG#101 | 4 | 4 | PKG#1014 | 43614 | 2512749.68
Sodic Eastown | 3 | 3 | Sodic Eastown3 | 43608 | 1574016.17
El Sewedy Uni.-PKG.2 | 8 | 8 | El Sewedy Uni.-PKG.28 | 43684 | 2625161.5
El Sewedy Uni.-PKG.3 | 6 | 6 | El Sewedy Uni.-PKG.36 | 43632 | 26656864.3
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 43643 | 2533668.0255
Royal City | 20 | 20 | Royal City20 | 43642 | 5643448.8191
Uptown PK #53 | 40 | 40 | Uptown PK #5340 | 43662 | 1435222.17
PI Parks - ELSEWEDY | 21 | 21 | PI Parks - ELSEWEDY21 | 43751 | 5879272.6391
PI Parks - MEP | 9 | 9 | PI Parks - MEP9 | 43751 | 5081340.66
Al Jazi | 17 | 17 | Al Jazi17 | 43652 | 3577364.85
Sodic Eastown | 4 | 4 | Sodic Eastown4 | 43654 | 26267292.44
PKG#101 | 5 | 5 | PKG#1015 | 43670 | 2051541.96
Sodic Club House | 36 | 36 | Sodic Club House36 |  | 7000000
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 43667 | 2620895.13
NGU 2 | 27 | 27 | NGU 227 |  | 2440072.7285
Royal City | 21 | 21 | Royal City21 | 43664 | 5151160.3487
El Sewedy Uni.-PKG.3 | 7 | 7 | El Sewedy Uni.-PKG.37 | 43671 | 22410862.51
Al Jazi | 18 | 18 | Al Jazi18 | 43673 | 3297235.7
Al Jazi - Center Zone | 3 | 3 | Al Jazi - Center Zone3 | 43673 | 1152186.95
Sodic Eastown | 5 | 5 | Sodic Eastown5 | 43678 | 22056568.4027
Mivida-PK#140 | 3 | 3 | Mivida-PK#1403 | 43697 | 4070832.3885
Royal City | 22 | 22 | Royal City22 | 43710 | 17540056.799
PKG#101 | 6 | 6 | PKG#1016 | 43705 | 1988552.05
Royal City - Landscape | 1 | 1 | Royal City - Landscape1 |  | 1800000
El Sewedy Uni.-PKG.3 | 8 | 8 | El Sewedy Uni.-PKG.38 | 43701 | 13598061.6
El Sewedy Uni.-PKG.1 | 10 | 10 | El Sewedy Uni.-PKG.110 | 43684 | -8913.92
Sodic Eastown | 6 | 6 | Sodic Eastown6 | 43716 | 28554847.68
Uptown PK #53 | 41 | 41 | Uptown PK #5341 | 43697 | 4202366.45
Al Jazi | 19 | 19 | Al Jazi19 | 43718 | 4336532.29
Al Jazi - Center Zone | 4 | 4 | Al Jazi - Center Zone4 | 43718 | 1090291.72
El Sewedy Uni.-PKG.3 | 9 | 9 | El Sewedy Uni.-PKG.39 | 43705 | 19410255.3
PK #117 | 12 | 12 | PK #11712 | 43733 | 3376348.1
Mivida-PK#140 | 4 | 4 | Mivida-PK#1404 | 43725 | 999645.4398
PKG#144 | 12 | 12 | PKG#14412 | 43741 | 22411649.36
Royal City | 23 | 23 | Royal City23 | 43736 | 4319851.8787
Royal City - Landscape | 2 | 2 | Royal City - Landscape2 | 43733 | 4032037.5
PKG#101 | 7 | 7 | PKG#1017 | 43729 | 1794285.02
El Sewedy Uni.-PKG.3 | 10 | 10 | El Sewedy Uni.-PKG.310 | 43737 | 20919758.8
Sodic Eastown | 7 | 7 | Sodic Eastown7 | 43746 | 38890621.0473
Mivida-PK#140 | 5 | 5 | Mivida-PK#1405 | 43761 | 1337507.07
Al Jazi | 20 | 20 | Al Jazi20 | 43772 | 2000000
Al Jazi - Center Zone | 5 | 5 | Al Jazi - Center Zone5 | 43772 | 1000000
Royal City | 24 | 24 | Royal City24 | 43762 | 10214838.0645
Royal City - Landscape | 3 | 3 | Royal City - Landscape3 | 43761 | 2443214.8875
PKG#101 | 8 | 8 | PKG#1018 | 43772 | 2127121.14
PK #117 | 13 | 13 | PK #11713 | 43781 | 3145779.21
Sodic Eastown | 8 | 8 | Sodic Eastown8 | 43783 | 58794871.95
Royal City | 25 | 25 | Royal City25 | 43796 | 12249365.624
Royal City - Landscape | 4 | 4 | Royal City - Landscape4 | 43824 | 4441415.442
Mivida-PK#140 | 6 | 6 | Mivida-PK#1406 | 43789 | 10719905.2391
HyperOne | 1 | 1 | HyperOne1 | 43793 | 2673900.95
PKG#101 | 9 | 9 | PKG#1019 | 43802 | 1424816.56
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | PH.2-El Sewedy Uni. - Enabling1 | 43810 | 2841415.8
Mivida-PK#140 | 7 | 7 | Mivida-PK#1407 | 43818 | 6547225.8223
HyperOne | 2 | 2 | HyperOne2 | 43811 | 8554552.61
Royal City | 26 | 26 | Royal City26 | 43835 | 7456675.6367
Royal City - Landscape | 5 | 5 | Royal City - Landscape5 | 43835 | 7147476.0332
CFC-DP | 1 | 1 | CFC-DP1 | 43842 | 62134944.55
PKG#101 | 10 | 10 | PKG#10110 | 43828 | 1948071.2
CFC | 1 | 1 | CFC1 | 43842 | 6200445.37
Uptown PK #62 | 19 | 19 | Uptown PK #6219 | 43944 | 1195853.88
PH.2-El Sewedy Uni. - Enabling | 2 | 2 | PH.2-El Sewedy Uni. - Enabling2 | 43841 | 13446882.5
HyperOne | 3 | 3 | HyperOne3 | 43843 | 7194819.7145
Mivida-PK#140 | 8 | 8 | Mivida-PK#1408 | 43858 | 4740517.5525
Sodic Eastown | 10 | 10 | Sodic Eastown10 | 43856 | 36785436.36
CFC | 2 | 2 | CFC2 | 43872 | 17323666.18
Royal City | 27 | 27 | Royal City27 | 43871 | 14587648.3106
Royal City - Landscape | 6 | 6 | Royal City - Landscape6 | 43871 | 9619287.67
El-Gouna - Equip. Rental | 1 | 1 | El-Gouna - Equip. Rental1 | 43863 | 73813.12
El-Gouna - Temp. Fence | 1 | 1 | El-Gouna - Temp. Fence1 | 43891 | 429660
Al Jazi | 21 | 21 | Al Jazi21 | 43914 | 5243962.1948
CFC | 3 | 3 | CFC3 | 43901 | 12263695.26
HyperOne | 4 | 4 | HyperOne4 | 43874 | 7092200.1311
PH.2-El Sewedy Uni. - Enabling | 3 | 3 | PH.2-El Sewedy Uni. - Enabling3 | 43866 | 17089175.5
PKG#101 | 11 | 11 | PKG#10111 | 43874 | 2026574.82
Mivida-PK#140 | 9 | 9 | Mivida-PK#1409 | 43884 | 4559999.0726
Al Jazi - Center Zone | 6 | 6 | Al Jazi - Center Zone6 | 43914 | -2446690.14
HyperOne | 5 | 5 | HyperOne5 | 43884 | 3307335
Royal City | 28 | 28 | Royal City28 | 43906 | 10986396.5553
Royal City - Landscape | 7 | 7 | Royal City - Landscape7 | 43906 | 6246175.7955
El-Gouna | 5 | 5 | El-Gouna5 | 43884 | 1815739.6
HyperOne | 6 | 6 | HyperOne6 | 43897 | 8598545.1487
Mivida-PK#140 | 10 | 10 | Mivida-PK#14010 | 43950 | 5679423.0614
Sodic Eastown | 12 | 12 | Sodic Eastown12 | 43919 | 19553108.77
PH.2-El Sewedy Uni. - Enabling | 4 | 4 | PH.2-El Sewedy Uni. - Enabling4 | 43906 | 14773850.7
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 43912 | 35636298.9
CFC | 4 | 4 | CFC4 | 43923 | 32660833.58
El-Gouna | 6 | 6 | El-Gouna6 | 43908 | 6823693.4
HyperOne | 7 | 7 | HyperOne7 | 43913 | 8896507
CFC | 5 | 5 | CFC5 | 43943 | 24749111.95
Mivida-PK#140 | 11 | 11 | Mivida-PK#14011 | 43950 | 2647674.1799
Royal City | 29 | 29 | Royal City29 | 43926 | 13166441.5288
Royal City - Landscape | 8 | 8 | Royal City - Landscape8 | 43926 | 12899186.0747
El Sewedy Uni.-PKG.2 | 9 | 9 | El Sewedy Uni.-PKG.29 | 43913 | 1116423.1
PKG#101 | 12 | 12 | PKG#10112 | 43929 | 1146998.22
PH.2-El Sewedy Uni. - Enabling | 5 | 5 | PH.2-El Sewedy Uni. - Enabling5 | 43930 | 2392694.9
Sodic Eastown | 13 | 13 | Sodic Eastown13 | 43943 | 19217788.54
HyperOne | 8 | 8 | HyperOne8 | 43933 | 3400669
PH.2-El Sewedy Uni. - Finishes | 2 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 43943 | 26758389.8
CFC | 6 | 6 | CFC6 | 43955 | 31500278.62
Royal City | 30 | 30 | Royal City30 | 43956 | 9831952.135
Royal City - Landscape | 9 | 9 | Royal City - Landscape9 | 43956 | 4988413.7416
HyperOne | 9 | 9 | HyperOne9 | 43947 | 1277872
El-Gouna | 7 | 7 | El-Gouna7 | 43942 | 2158979.11
PH.2-El Sewedy Uni. - Enabling | 6 | 6 | PH.2-El Sewedy Uni. - Enabling6 | 43957 | 7788095.2
Mivida-PK#140 | 12 | 12 | Mivida-PK#14012 | 43972 | 4687303.4253
PH.2-El Sewedy Uni. - Finishes | 3 | 3 | PH.2-El Sewedy Uni. - Finishes3 | 43970 | 23262698.8
CFC | 7 | 7 | CFC7 | 43986 | 19510038
Royal City - Landscape | 10 | 10 | Royal City - Landscape10 | 44014 | 3101056.0064
Royal City | 31 | 31 | Royal City31 | 44014 | 7550426.1692
HyperOne | 10 | 10 | HyperOne10 | 43983 | 4810581.9155
PH.2-El Sewedy Uni. - Enabling | 7 | 7 | PH.2-El Sewedy Uni. - Enabling7 | 44023 | 3548357.4
CFC | 8 | 8 | CFC8 | 44019 | 21459124.497
PH.2-El Sewedy Uni. - Finishes | 4 | 4 | PH.2-El Sewedy Uni. - Finishes4 | 44000 | 18322601
HyperOne | 11 | 11 | HyperOne11 | 44005 | 6700151
Royal City | 32 | 32 | Royal City32 | 44020 | 2648440.2256
Royal City - Landscape | 11 | 11 | Royal City - Landscape11 | 44020 | 3973857.736
El Sewedy Uni.-PKG.3 | 12 | 12 | El Sewedy Uni.-PKG.312 | 44003 | 1515470
PK #117 | 14 | 14 | PK #11714 | 44082 | 2238761.46
CFC | 9 | 9 | CFC9 | 44039 | 24499895.52
HyperOne | 12 | 12 | HyperOne12 | 44023 | 1896314.4172
El-Gouna | 8 | 8 | El-Gouna8 | 44018 | 1933855.68
Mivida-PK#140 | 14 | 14 | Mivida-PK#14014 | 44033 | 7336701.0997
PH.2-El Sewedy Uni. - Enabling | 8 | 8 | PH.2-El Sewedy Uni. - Enabling8 | 44021 | 1607563.1
PH.2-El Sewedy Uni. - Finishes | 5 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 44025 | 64006362.8
Royal City | 33 | 33 | Royal City33 | 44055 | 9101413.8171
Royal City - Landscape | 12 | 12 | Royal City - Landscape12 | 44055 | 7029456.4155
PH.2-El Sewedy Uni. - Finishes | 6 | 6 | PH.2-El Sewedy Uni. - Finishes6 | 44041 | 8883254.2
PH.2-El Sewedy Uni. - Enabling | 9 | 9 | PH.2-El Sewedy Uni. - Enabling9 | 44070 | 8526565.2
CFC | 10 | 10 | CFC10 | 44069 | 39448595.5711
Mivida-PK#140 | 15 | 15 | Mivida-PK#14015 | 44067 | 10305723.5244
HyperOne | 13 | 13 | HyperOne13 | 44062 | 6738701.3468
Royal City - Landscape | 13 | 13 | Royal City - Landscape13 | 44081 | 2173267.6157
Royal City | 34 | 34 | Royal City34 | 44088 | 5373442.9261
PH.2-El Sewedy Uni. - Finishes | 7 | 7 | PH.2-El Sewedy Uni. - Finishes7 | 44069 | 30755604.9
Sodic Eastown | 17 | 17 | Sodic Eastown17 | 44065 | 22896073.3381
CFC | 11 | 11 | CFC11 | 44103 | 18030565.73
Mivida-PK#140 | 16 | 16 | Mivida-PK#14016 | 44089 | 10553431.2394
HyperOne | 14 | 14 | HyperOne14 | 44087 | 4476191
PH.2-El Sewedy Uni. - Finishes | 8 | 8 | PH.2-El Sewedy Uni. - Finishes8 | 44091 | 30127325.7
Royal City | 35 | 35 | Royal City35 | 44109 | 3237336.5863
Royal City - Landscape | 14 | 14 | Royal City - Landscape14 | 44109 | 1308214.7555
HyperOne | 15 | 15 | HyperOne15 | 44447 | 2800899.62
Mivida-PK#140 | 17 | 17 | Mivida-PK#14017 | 44123 | 11726998.4266
Royal City | 36 | 36 | Royal City36 | 44132 | 4982664.9588
Royal City - Landscape | 15 | 15 | Royal City - Landscape15 | 44132 | 2303900.245
CFC | 12 | 12 | CFC12 | 44139 | 29691194.9757
PH.2-El Sewedy Uni. - Finishes | 9 | 9 | PH.2-El Sewedy Uni. - Finishes9 | 44124 | 20493846
AEON | 2 | 2 | AEON2 | 44147 | 1610113.5212
CFC | 13 | 13 | CFC13 | 44174 | 23213755.7909
Royal City | 37 | 37 | Royal City37 | 44161 | 5574033.5344
Mivida-PK#140 | 18 | 18 | Mivida-PK#14018 | 44164 | 3831058.93
Royal City - Landscape | 16 | 16 | Royal City - Landscape16 | 44161 | 869369.6486
PH.2-El Sewedy Uni. - Finishes | 10 | 10 | PH.2-El Sewedy Uni. - Finishes10 | 44154 | 9765894.8
ORA - ZED | 1 | 1 | ORA - ZED1 | 44213 | 10345156.8
CFC | 14 | 14 | CFC14 | 44207 | 19708944.2711
PKG#101 | 15 | 15 | PKG#10115 | 44182 | 1392185.4448
Mivida-PK#140 | 19 | 19 | Mivida-PK#14019 | 44186 | 8885358.6191
Royal City | 38 | 38 | Royal City38 | 44201 | 3838809.8865
Royal City - Landscape | 17 | 17 | Royal City - Landscape17 | 44201 | 1883835.4255
PH.2-El Sewedy Uni. - Finishes | 11 | 11 | PH.2-El Sewedy Uni. - Finishes11 | 44186 | 13851401.2
AEON | 3 | 3 | AEON3 | 44200 | 780253.0677
ORA - ZED | 2 | 2 | ORA - ZED2 | 44202 | 37827388.6601
Mivida-PK#140 | 20 | 20 | Mivida-PK#14020 | 44231 | 5084359.8248
CFC | 15 | 15 | CFC15 | 44249 | 40379659.8985
Royal City - Landscape | 18 | 18 | Royal City - Landscape18 | 44230 | 819297.0816
Royal City | 39 | 39 | Royal City39 | 44230 | 1002773.1926
PKG#144 | 16 | 16 | PKG#14416 | 44256 | 1132971.99
ORA - ZED | 3 | 3 | ORA - ZED3 | 44244 | 28404325.826
CFC | 16 | 16 | CFC16 | 44276 | 22871121.15
Mivida-PK#140 | 21 | 21 | Mivida-PK#14021 | 44244 | 8185193.8344
HQ - CFC | 1 | 1 | HQ - CFC1 | 44249 | 6847513.7311
Royal City - Landscape | 19 | 19 | Royal City - Landscape19 | 44257 | 1116339.8935
PH.2-El Sewedy Uni. - Finishes | 12 | 12 | PH.2-El Sewedy Uni. - Finishes12 | 44271 | 26122387
CFC | 17 | 17 | CFC17 | 44280 | 15047803.36
CFC | 18 | 18 | CFC18 | 44292 | 12196441.11
ORA - ZED | 4 | 4 | ORA - ZED4 | 44279 | 21185755.528
HQ - CFC | 2 | 2 | HQ - CFC2 | 44277 | 8021127.94
Sodic Eastown | 24 | 24 | Sodic Eastown24 | 44284 | 17436083.38
Royal City | 40 | 40 | Royal City40 | 44298 | 5979686.6716
Royal City - Landscape | 20 | 20 | Royal City - Landscape20 | 44298 | 1105876.6944
CFC | 19 | 19 | CFC19 | 44306 | 14008565.71
CFC | 20 | 20 | CFC20 | 44340 | 23721354.77
ORA - ZED | 5 | 5 | ORA - ZED5 | 44339 | 35278804.6637
HQ - CFC | 3 | 3 | HQ - CFC3 | 44301 | 8213719.76
Mivida-PK#140 | 23 | 23 | Mivida-PK#14023 | 44327 | 1458682.9494
HQ - CFC | 4 | 4 | HQ - CFC4 | 44342 | 7815807.64
CFC | 21 | 21 | CFC21 | 44364 | 17156225.13
CFC | 22 | 22 | CFC22 | 44376 | 13410069.82
ORA - ZED | 6 | 6 | ORA - ZED6 | 44343 | 4544122.0162
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 44362 | 4887819.25
EGAT Pelletizing Plant-Water Tank | 1 | 1 | EGAT Pelletizing Plant-Water Tank1 | 44369 | 3438202.99
Royal City | 41 | 41 | Royal City41 | 44501 | 5714023.3138
PH.2-El Sewedy Uni. - Finishes | 13 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 44678 | 19693398.5
Royal City - Landscape | 21 | 21 | Royal City - Landscape21 | 44390 | 3011690.98
EGAT Pelletizing Plant-MEP | 1 | 1 | EGAT Pelletizing Plant-MEP1 | 44433 | 2112577.42
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 44389 | 10124222.67
CFC | 23 | 23 | CFC23 | 44426 | 15440458.92
Katameya - Creeks | 7 | 7 | Katameya - Creeks7 | 44404 | 44596069.78
PKG#178 | 6 | 6 | PKG#1786 |  | 4030279.0303
EGAT Pelletizing Plant-Water Tank | 2 | 2 | EGAT Pelletizing Plant-Water Tank2 | 44389 | 2130019.28
CFC | 24 | 24 | CFC24 | 44462 | 7464840.35
PKG#177 | 18 | 18 | PKG#17718 | 44440 | 15056356.09
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 44427 | 4165165.88
EGAT Pelletizing Plant-Water Tank | 3 | 3 | EGAT Pelletizing Plant-Water Tank3 | 44427 | 761625.75
PKG#177 | 19 | 19 | PKG#17719 |  | -0.001
PKG#177 | 20 | 20 | PKG#17720 |  | -0.001
ORA - ZED | 9 | 9 | ORA - ZED9 | 44448 | 26728065.13
CFC | 25 | 25 | CFC25 | 44494 | 9682524.47
PKG#177 | 21 | 21 | PKG#17721 |  | -0.0001
Ring Road - Mounib | 9 | 9 | Ring Road - Mounib9 |  | 3856121.55
Ring Road - Mounib | 10 | 10 | Ring Road - Mounib10 |  | 12662306
PKG#177 | 22 | 22 | PKG#17722 |  | -0.0001
EGAT Pelletizing Plant-Water Tank | 4 | 4 | EGAT Pelletizing Plant-Water Tank4 | 44444 | 804482.15
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 44466 | 6104444.17
Ring Road - Mounib | 11 | 11 | Ring Road - Mounib11 | 44446 | 19857247.187
CFC | 26 | 26 | CFC26 | 44518 | 2397254.3033
HQ - CFC | 7 | 7 | HQ - CFC7 | 44448 | 14942810.8492
PKG#177 | 23 | 23 | PKG#17723 |  | -0.0001
Ring Road - El Marg | 7 | 7 | Ring Road - El Marg7 |  | 25237352
ORA - ZED | 10 | 10 | ORA - ZED10 | 44465 | 29047725.55
PKG#177 | 24 | 24 | PKG#17724 |  | -0.0001
Royal City - Landscape | 22 | 22 | Royal City - Landscape22 | 44501 | 2526109.9
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 44489 | 14109093.06
EGAT Pelletizing Plant-Water Tank | 5 | 5 | EGAT Pelletizing Plant-Water Tank5 | 44481 | 969774.05
PKG#177 | 25 | 25 | PKG#17725 |  | -0.0001
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 44482 | 14536703.8371
HQ - CFC | 8 | 8 | HQ - CFC8 | 44482 | 10059001.5
Ring Road - Mounib | 12 | 12 | Ring Road - Mounib12 | 44485 | 14886673.24
Kafr Shokr | 7 | 7 | Kafr Shokr 7 |  | 25823994.7095
CFC | 27 | 27 | CFC27 | 44522 | 10793868.55
PKG#177 | 26 | 26 | PKG#17726 |  | -0.0001
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 44514 | 10385277.48
EGAT Pelletizing Plant-Water Tank | 6 | 6 | EGAT Pelletizing Plant-Water Tank6 | 44509 | 1537532.43
HQ - CFC | 9 | 9 | HQ - CFC9 | 44511 | 17174919.86
Royal City - Landscape | 23 | 23 | Royal City - Landscape23 | 44970 | 15313915.32
Ring Road - Mounib | 13 | 13 | Ring Road - Mounib13 | 44513 | 41814387.46
Sports Hall - Finishes | 3 | 3 | Sports Hall - Finishes3 | 44517 | 77278617
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 44514 | 20471935.8674
PKG#162 | 15 | 15 | PKG#16215 | 44613 | 3683579.28
Kafr Shokr | 8 | 8 | Kafr Shokr 8 | 44555 | 2028646.62
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 44579 | 9325143.2186
HQ - CFC | 10 | 10 | HQ - CFC10 | 44546 | 7981881.9284
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 44550 | 13304274.45
EGAT Pelletizing Plant-Water Tank | 7 | 7 | EGAT Pelletizing Plant-Water Tank7 | 44539 | 419715.76
PKG#177 | 27 | 27 | PKG#17727 |  | -0.0001
PKG#177 - SWI 07 | 1 | 1 | PKG#177 - SWI 071 |  | 1800000
MDF Factory | 6 | 6 | MDF Factory6 | 44581 | 17171193.3155
Sports Hall - Civil Works | 7 | 7 | Sports Hall - Civil Works7 |  | 12888184
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 44570 | 28860252.4316
PKG#177 - SWI 07 | 2 | 2 | PKG#177 - SWI 072 |  | 4300000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 44579 | 11576342.49
EGAT Pelletizing Plant-Water Tank | 8 | 8 | EGAT Pelletizing Plant-Water Tank8 | 44567 | 322587.51
HQ - CFC | 11 | 11 | HQ - CFC11 | 44578 | 17417402.1321
Sports Hall - Finishes - ADD.01 | 1 | 1 | Sports Hall - Finishes - ADD.011 | 44614 | 5944418.35
MDF Factory | 7 | 7 | MDF Factory7 | 44594 | 14851309.99
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 44620 | 17181317.99
PKG#177 - SWI 07 | 3 | 3 | PKG#177 - SWI 073 |  | 5800000
Kafr Shokr | 10 | 10 | Kafr Shokr 10 | 44830 | 2301999.75
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 44606 | 23504299.92
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 44616 | 15046421.2
EGAT Pelletizing Plant-Water Tank | 9 | 9 | EGAT Pelletizing Plant-Water Tank9 | 44622 | 1117435.2
Rolling Mill #4-TRAESUEZ | 2 | 2 | Rolling Mill #4-TRAESUEZ2 | 44642 | 11564103.96
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 44616 | 4767292.38
Katameya - Creeks | 14 | 14 | Katameya - Creeks14 | 44616 | 45904629.98
MDF Factory | 8 | 8 | MDF Factory8 | 44621 | 12391060.05
PKG#177 | 32 | 32 | PKG#17732 |  | 1200000
ORA - ZED - ph.02 | 5 | 5 | ORA - ZED - ph.025 | 44617 | 12407122.3694
HQ - CFC | 12 | 12 | HQ - CFC12 | 44616 | 11342067.06
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 44620 | 4511122
ORA - ZED | 15 | 15 | ORA - ZED15 |  | 25550073.0625
EGAT Pelletizing Plant-MEP | 2 | 2 | EGAT Pelletizing Plant-MEP2 | 44614 | 118584.38
CFC | 28 | 28 | CFC28 | 44690 | 10367935.42
PKG#177 | 34 | 34 | PKG#17734 |  | 16000000
Abo Ghaleb Bridge | 2 | 2 | Abo Ghaleb Bridge2 | 44627 | 2494611.027
MDF Factory | 9 | 9 | MDF Factory9 | 44658 | 7655361.33
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 44663 | 13017478.47
EGAT-Lock & Load | 2 | 2 | EGAT-Lock & Load2 | 44626 | 2243956.2
EGAT Pelletizing Plant-Water Tank | 10 | 10 | EGAT Pelletizing Plant-Water Tank10 | 44634 | 3717766.29
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 44644 | 16602157.8
HQ - CFC | 13 | 13 | HQ - CFC13 | 44648 | 869511.3183
ORA - ZED | 16 | 16 | ORA - ZED16 |  | 21942762.0737
ORA - ZED - ph.02 | 6 | 6 | ORA - ZED - ph.026 | 44691 | 16610990.7481
Abo Ghaleb Bridge | 3 | 3 | Abo Ghaleb Bridge3 | 44655 | 3124254.645
ORA - ZED - ph.02 | 7 | 7 | ORA - ZED - ph.027 | 44780 | 32100388.5958
ORA - ZED | 17 | 17 | ORA - ZED17 | 44692 | 26182539.8028
PKG#177 | 36 | 36 | PKG#17736 |  | 15000000
PKG#177 - SWI 07 | 5 | 5 | PKG#177 - SWI 075 |  | 9500000
PKG#163 | 23 | 23 | PKG#16323 |  | 3449740.5053
Sports Hall - MEP | 2 | 2 | Sports Hall - MEP2 |  | 13327738
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 44672 | 5421697
EGAT-Lock & Load | 3 | 3 | EGAT-Lock & Load3 | 44663 | 1683710.18
Rolling Mill #4-TRAESUEZ | 3 | 3 | Rolling Mill #4-TRAESUEZ3 | 44671 | 10352618.57
EGAT Pelletizing Plant-Water Tank | 11 | 11 | EGAT Pelletizing Plant-Water Tank11 | 44796 | 3941437.84
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 44672 | 14300826.37
HQ - CFC | 14 | 14 | HQ - CFC14 |  | 1748564.91
PKG#177 | 37 | 37 | PKG#17737 | 44780 | 2963171.8184
MDF Factory | 10 | 10 | MDF Factory10 | 44678 | 11119452.63
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 44668 | 19713977.881
Abo Ghaleb Bridge | 4 | 4 | Abo Ghaleb Bridge4 | 44782 | 6555212.9406
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 44704 | 7722438.9
Rolling Mill #4-TRAESUEZ | 4 | 4 | Rolling Mill #4-TRAESUEZ4 | 44698 | 6677291.55
ORA - ZED - ph.02 | 8 | 8 | ORA - ZED - ph.028 | 44719 | 8595538.9026
ORA - ZED | 18 | 18 | ORA - ZED18 | 44707 | 9292712.69
PKG#163 | 24 | 24 | PKG#16324 |  | 5681606.5237
PKG#177 | 38 | 38 | PKG#17738 |  | 0.0001
PKG#177 - SWI 07 | 6 | 6 | PKG#177 - SWI 076 |  | 5000000
HQ - CFC | 15 | 15 | HQ - CFC15 | 44698 | 10437709.6267
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 44712 | 4634265
MDF Factory | 11 | 11 | MDF Factory11 | 44719 | 9991684.94
Abo Ghaleb Bridge | 5 | 5 | Abo Ghaleb Bridge5 | 44794 | 1645829.28
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 44728 | 18095262.89
PKG#163 | 25 | 25 | PKG#16325 |  | 11730565.831
PKG#177 - SWI 07 | 7 | 7 | PKG#177 - SWI 077 |  | 4000000
Astoria Hotel | 5 | 5 | Astoria Hotel5 | 44740 | 5818860
EGAT-Lock & Load | 5 | 5 | EGAT-Lock & Load5 | 44719 | 3021167.52
EGAT Pelletizing Plant-MEP | 3 | 3 | EGAT Pelletizing Plant-MEP3 | 44969 | 1329462.73
ORA - ZED - ph.02 | 9 | 9 | ORA - ZED - ph.029 | 44746 | 7163536.3546
ORA - ZED | 19 | 19 | ORA - ZED19 | 44740 | 16483568.4889
Rolling Mill #4-TRAESUEZ | 5 | 5 | Rolling Mill #4-TRAESUEZ5 | 44748 | 8140659.04
MDF Factory | 12 | 12 | MDF Factory12 | 44741 | 29337407.23
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 44747 | 13285393.01
HQ - CFC | 16 | 16 | HQ - CFC16 | 44727 | 1064612.35
Astoria - Sharm | 2 | 2 | Astoria - Sharm2 | 44748 | 836570
Astoria Hotel | 6 | 6 | Astoria Hotel6 | 44748 | 8446328.13
HQ - CFC | 17 | 17 | HQ - CFC17 | 44760 | 8013147.4
PKG#177 - SWI 07 | 8 | 8 | PKG#177 - SWI 078 |  | 500000
PKG#163 | 26 | 26 | PKG#16326 |  | 8194504.6617
PKG#177 | 41 | 41 | PKG#17741 |  | 10330863.574
ORA - ZED - ph.02 | 10 | 10 | ORA - ZED - ph.0210 | 44773 | 20828447.3064
MDF Factory | 13 | 13 | MDF Factory13 | 44780 | 19866888.03
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 44796 | 7877469.99
EGAT-Lock & Load | 6 | 6 | EGAT-Lock & Load6 | 44748 | 3209897.61
Rolling Mill #4-TRAESUEZ | 6 | 6 | Rolling Mill #4-TRAESUEZ6 | 44780 | 4679965.02
ORA - ZED | 20 | 20 | ORA - ZED20 | 44780 | 8935027.0512
ORA - ZED | 20.1 | 20 | ORA - ZED20 | 44780 | 11075167.13
Mivida-PK#189 | 2 | 2 | Mivida-PK#1892 | 44779 | 22529255.8764
Sodic Eastown - Landscape | 8 | 8 | Sodic Eastown - Landscape8 | 44769 | 13407927.22
MDF Factory - Equip. | 8 | 8 | MDF Factory - Equip.8 | 44775 | 324002.35
Astoria - Sharm | 3 | 3 | Astoria - Sharm3 | 44782 | 269728
Astoria Hotel | 7 | 7 | Astoria Hotel7 | 44781 | 8710615
HQ - CFC | 18 | 18 | HQ - CFC18 | 44790 | 13019444.4
Katameya - Creeks | 20 | 20 | Katameya - Creeks20 | 44794 | 24569045.01
PKG#163 | 27 | 27 | PKG#16327 |  | 20000000
ORA - ZED | 21 | 21 | ORA - ZED21 | 44805 | 7443624.2902
Ring Road - Mounib | 17 | 17 | Ring Road - Mounib17 | 44783 | 5130646.847
PKG#177 - SWI 07 | 9 | 9 | PKG#177 - SWI 079 |  | 4000000
ORA - ZED - ph.02 | 11 | 11 | ORA - ZED - ph.0211 | 44798 | 12170283.1854
MDF Factory | 14 | 14 | MDF Factory14 | 44810 | 15316196.46
PKG#177 | 44 | 44 | PKG#17744 |  | 20000000
EGAT-Lock & Load | 7 | 7 | EGAT-Lock & Load7 | 44789 | 1345184.87
Mivida-PK#189 | 3 | 3 | Mivida-PK#1893 | 44808 | 19800407.88
Rolling Mill #4-TRAESUEZ | 7 | 7 | Rolling Mill #4-TRAESUEZ7 | 44797 | 13457708.47
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 44797 | 19389514.84
Astoria Hotel | 8 | 8 | Astoria Hotel8 | 44812 | 2805916
Astoria - Sharm | 4 | 4 | Astoria - Sharm4 | 44809 | 1641108
Katameya - Creeks | 21 | 21 | Katameya - Creeks21 | 44824 | 35259435.93
PKG#177 | 45 | 45 | PKG#17745 |  | 5000000
ORA - ZED | 22 | 22 | ORA - ZED22 | 44819 | 8098824.8775
MDF Factory | 15 | 15 | MDF Factory15 | 44843 | 15409194.69
HQ - CFC | 19 | 19 | HQ - CFC19 | 44850 | 2123376.4
EGAT-Lock & Load | 8 | 8 | EGAT-Lock & Load8 | 44815 | 2647273.89
PKG#163 | 28 | 28 | PKG#16328 |  | 20000000
Rolling Mill #4-TRAESUEZ | 8 | 8 | Rolling Mill #4-TRAESUEZ8 | 44831 | 14944026.92
Ring Road - Mounib | 18 | 18 | Ring Road - Mounib18 | 44816 | 3489333.2073
ORA - ZED - ph.02 | 12 | 12 | ORA - ZED - ph.0212 | 44843 | 14639634.3822
New Giza Hospital | 9 | 9 | New Giza Hospital9 | 44826 | 15620677.42
Mivida-PK#189 | 4 | 4 | Mivida-PK#1894 | 44843 | 27644756.83
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 44844 | 14238994.72
Astoria Hotel | 9 | 9 | Astoria Hotel9 | 44830 | 6286403
Astoria Hotel | 10 | 10 | Astoria Hotel10 | 44840 | 4982321
ORA - ZED - ph.02 | 13 | 13 | ORA - ZED - ph.0213 | 44856 | 17432997.712
ORA - ZED | 23 | 23 | ORA - ZED23 | 44861 | 22964574.875
Astoria - Sharm | 5 | 5 | Astoria - Sharm5 | 44840 | 709627
Sodic Eastown - Landscape | 9 | 9 | Sodic Eastown - Landscape9 | 44817 | 837296.04
MDF Factory | 16 | 16 | MDF Factory16 | 44871 | 22014291.85
New Giza Hospital | 10 | 10 | New Giza Hospital10 | 44868 | 14944068.34
EGAT-Lock & Load | 9 | 9 | EGAT-Lock & Load9 | 44852 | 3781437.71
HQ - CFC | 20 | 20 | HQ - CFC20 | 44845 | 9324446.7637
Rolling Mill #4-TRAESUEZ | 9 | 9 | Rolling Mill #4-TRAESUEZ9 | 44872 | 14162374.17
Mivida-PK#189 | 5 | 5 | Mivida-PK#1895 | 44870 | 46638711.45
PKG#177 | 46 | 46 | PKG#17746 |  | 10000000
PKG#163 | 29 | 29 | PKG#16329 |  | 20000000
Astoria Hotel | 11 | 11 | Astoria Hotel11 | 44865 | 10757000
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 44888 | 16138518.46
Astoria - Sharm | 6 | 6 | Astoria - Sharm6 | 44864 | 244817
EGAT-Lock & Load | 10 | 10 | EGAT-Lock & Load10 | 44868 | 1099389.93
Astoria Hotel | 12 | 12 | Astoria Hotel12 | 44875 | 2603000
Rolling Mill #4-TRAESUEZ | 10 | 10 | Rolling Mill #4-TRAESUEZ10 | 44909 | 12338644.38
HQ - CFC | 21 | 21 | HQ - CFC21 | 44885 | 1704646.05
ORA - ZED - ph.02 | 14 | 14 | ORA - ZED - ph.0214 | 44910 | 15411600.8685
MDF Factory | 17 | 17 | MDF Factory17 | 44888 | 15156893.21
Sodic Eastown - Landscape | 10 | 10 | Sodic Eastown - Landscape10 | 44854 | 5311032.49
Sodic Eastown - Landscape | 11 | 11 | Sodic Eastown - Landscape11 | 44872 | 7657014.05
New Giza Hospital | 11 | 11 | New Giza Hospital11 | 44902 | 19999087.83
Sodic Eastown - Landscape | 12 | 12 | Sodic Eastown - Landscape12 | 44885 | 8902796.13
Mivida-PK#189 | 6 | 6 | Mivida-PK#1896 | 44900 | 70000000
Astoria Hotel | 13 | 13 | Astoria Hotel13 | 44893 | 5389256
6TH October tunnel | 4 | 4 | 6TH October tunnel4 | 44878 | 3604450.6683
6TH October tunnel | 5 | 5 | 6TH October tunnel5 | 44882 | 3524900.34
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 44914 | 12845007.22
MDF Factory | 18 | 18 | MDF Factory18 | 44906 | 5028798.98
EGAT-Lock & Load | 11 | 11 | EGAT-Lock & Load11 | 44902 | 1893245.16
Mivida-PK#189 | 7 | 7 | Mivida-PK#1897 | 44900 | 38664242.9
Katameya - Creeks | 24 | 24 | Katameya - Creeks24 | 44921 | 37876581.29
ORA - ZED - ph.02 | 15 | 15 | ORA - ZED - ph.0215 | 44915 | 11605388.8976
New Giza Hospital | 12 | 12 | New Giza Hospital12 | 44924 | 21046664.64
Rolling Mill #4-TRAESUEZ | 11 | 11 | Rolling Mill #4-TRAESUEZ11 | 44943 | 13316234.88
Astoria Hotel | 14 | 14 | Astoria Hotel14 | 44915 | 6216098
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 44915 | 2167633.6703
MDF Factory | 19 | 19 | MDF Factory19 | 44923 | 9756751.36
Wady Halfa | 1 | 1 | Wady Halfa1 | 44913 | 33029517.9
HQ - CFC | 24 | 24 | HQ - CFC24 | 44922 | 5979128.01
Mivida-PK#189 | 8 | 8 | Mivida-PK#1898 | 44927 | 62566272.81
ORA - ZED | 24 | 24 | ORA - ZED24 | 44976 | 7490234.3814
MDF Factory | 20 | 20 | MDF Factory20 | 44938 | 14838164.52
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 44971 | 19373062.69
Astoria Hotel | 15 | 15 | Astoria Hotel15 | 44951 | 4185662
EGAT-Lock & Load | 12 | 12 | EGAT-Lock & Load12 | 44923 | 1689951.65
Katameya - Creeks | 25 | 25 | Katameya - Creeks25 | 44951 | 45191848.32
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 44959 | 2399508.91
ORA - ZED - ph.02 | 16 | 16 | ORA - ZED - ph.0216 | 44962 | 9858411.1445
ORA - ZED - Landscape | 2 | 2 | ORA - ZED - Landscape2 | 44958 | 1719650.0563
HQ - CFC | 25 | 25 | HQ - CFC25 | 44956 | 10125697.7641
ORA - ZED | 25 | 25 | ORA - ZED25 | 45026 | -9163815.8569
Mivida-PK#189 | 9 | 9 | Mivida-PK#1899 | 44950 | 37089197.56
New Giza Hospital | 13 | 13 | New Giza Hospital13 | 44963 | 18169651.25
Royal City | 42 | 42 | Royal City42 | 44970 | 29397549.59
PKG#163 | 30 | 30 | PKG#16330 |  | 20000000
Rolling Mill #4-TRAESUEZ | 12 | 12 | Rolling Mill #4-TRAESUEZ12 | 44964 | 13380155.34
MDF Factory | 21 | 21 | MDF Factory21 | 44963 | 18749752.53
ORA - ZED - Landscape | 3 | 3 | ORA - ZED - Landscape3 | 44983 | 1775205.4809
ORA - ZED - ph.02 | 17 | 17 | ORA - ZED - ph.0217 | 44994 | 8988165.9521
Port Said Silos - Local Supply | 1 | 1 | Port Said Silos - Local Supply1 | 45001 | 438003.54
EGAT-Lock & Load | 13 | 13 | EGAT-Lock & Load13 | 44964 | 2010941.41
DPW - Ph.02 | 1 | 1 | DPW - Ph.021 | 44973 | 21516389.4
Katameya - Creeks | 26 | 26 | Katameya - Creeks26 | 44985 | 74263221.64
Mivida-PK#189 | 10 | 10 | Mivida-PK#18910 | 44983 | 22123110.41
HQ - CFC | 26 | 26 | HQ - CFC26 | 45337 | 24450753.15
MDF Factory | 22 | 22 | MDF Factory22 | 44982 | 3016784.72
Astoria Hotel | 16 | 16 | Astoria Hotel16 | 44982 | 3225683
New Giza Hospital | 14 | 14 | New Giza Hospital14 | 44999 | 14731551.62
Rolling Mill #4-TRAESUEZ | 13 | 13 | Rolling Mill #4-TRAESUEZ13 | 44993 | 11700102.46
Wady Halfa | 2 | 2 | Wady Halfa2 | 44971 | 11905091.98
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 45048 | 1348177.1
DPW - Ph.02 - DP | 2 | 2 | DPW - Ph.02 - DP2 | 44978 | 63597656.25
PKG#177 | 47 | 47 | PKG#17747 | 45141 | 4375831.9851
LEKELA | 16 | 16 | LEKELA16 | 45016 | 8212932.01
ORA - ZED - ph.02 | 18 | 18 | ORA - ZED - ph.0218 | 45014 | 13331568.0485
ORA - ZED - Landscape | 4 | 4 | ORA - ZED - Landscape4 | 45026 | 4074938.0511
EIPICO | 4 | 4 | EIPICO4 | 45000 | 7345011.2
EGAT-Lock & Load | 14 | 14 | EGAT-Lock & Load14 | 44993 | 2629738.34
MDF Factory | 23 | 23 | MDF Factory23 | 45007 | 26140854.32
New Gas Station | 1 | 1 | New Gas Station1 | 45232 | 2360718.4
Mivida-PK#189 | 11 | 11 | Mivida-PK#18911 | 45026 | 18794302.38
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 45007 | 19188213.6
Astoria Hotel | 17 | 17 | Astoria Hotel17 | 45018 | 2804159
PKG#163 | 31 | 31 | PKG#16331 |  | 5000000
New Giza Hospital | 15 | 15 | New Giza Hospital15 | 45034 | 14839693.08
Wady Halfa | 3 | 3 | Wady Halfa3 | 45001 | 14516628.581
PKG#177 | 48 | 48 | PKG#17748 |  | 4111000
EIPICO | 5 | 5 | EIPICO5 | 45026 | 10066271.07
Port Said Silos | 13 | 13 | Port Said Silos13 | 45018 | 451211.246
MDF Factory | 24 | 24 | MDF Factory24 | 45046 | 13504786.11
DPW - Ph.02 | 3 | 3 | DPW - Ph.023 | 45012 | 19827820.72
Katameya - Creeks | 28 | 28 | Katameya - Creeks28 | 45050 | 28650459.02
ORA - ZED - ph.02 | 19 | 19 | ORA - ZED - ph.0219 | 45047 | 6921352.2914
ORA - ZED - Landscape | 5 | 5 | ORA - ZED - Landscape5 | 45047 | 3204803.968
Mivida-PK#189 | 12 | 12 | Mivida-PK#18912 | 45054 | 16890748.07
ORA - ZED | 26 | 26 | ORA - ZED26 | 45047 | 16993731.7513
New Giza Hospital | 16 | 16 | New Giza Hospital16 | 45060 | 15222233.72
EIPICO | 6 | 6 | EIPICO6 | 45063 | 5949977.84
DPW - Ph.02 | 4 | 4 | DPW - Ph.024 | 45085 | 28925313.53
Katameya - Creeks | 29 | 29 | Katameya - Creeks29 | 45080 | 40904481.77
Mivida-PK#189 | 13 | 13 | Mivida-PK#18913 | 45083 | 50032149.1
PKG#177 | 49 | 49 | PKG#17749 |  | 0.0001
PKG#163 | 32 | 32 | PKG#16332 |  | 5000000
ORA - ZED - Landscape | 6 | 6 | ORA - ZED - Landscape6 | 45084 | 3160913.3163
ORA - ZED - ph.02 | 20 | 20 | ORA - ZED - ph.0220 | 45078 | 3302213.7069
ORA - ZED | 27 | 27 | ORA - ZED27 | 45092 | 9042387.5614
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 45090 | 951578.36
DPW - Ph.02 | 5 | 5 | DPW - Ph.025 | 45102 | 30561302.57
New Giza Hospital | 17 | 17 | New Giza Hospital17 | 45111 | 12680990.84
ORA - ZED - ph.02 | 21 | 21 | ORA - ZED - ph.0221 | 45116 | 4532159.6508
PKG#177 | 50 | 50 | PKG#17750 |  | 0.001
Astoria Hotel | 19 | 19 | Astoria Hotel19 | 45096 | 1511334.2104
MDF Factory | 26 | 26 | MDF Factory26 | 45098 | 18123054.07
Mivida-PK#140 | 28 | 28 | Mivida-PK#14028 | 45365 | 1577397.44
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 |  | 2159644.45
PKG#163 | 33 | 33 | PKG#16333 |  | 5000000
KSA-Tarek AbdelHakim Center | 2 | 2 | KSA-Tarek AbdelHakim Center2 | 45090 | 2122111.73
Mivida-PK#189 | 14 | 14 | Mivida-PK#18914 | 45122 | 22045664.4
Creeks - URBN K | 3 | 3 | Creeks - URBN K3 | 45095 | 21808950.42
ORA - ZED - Landscape | 7 | 7 | ORA - ZED - Landscape7 | 45124 | 1045760.0532
ORA - ZED | 28 | 28 | ORA - ZED28 | 45116 | 10264179.63
KSA-Tarek AbdelHakim Center | 3 | 3 | KSA-Tarek AbdelHakim Center3 | 45132 | 911111.84
PKG#177 | 51 | 51 | PKG#17751 |  | 0.001
DPW - Ph.02 | 6 | 6 | DPW - Ph.026 | 45138 | 24170866.16
MDF Factory | 27 | 27 | MDF Factory27 | 45119 | 21231778.46
EIPICO | 8 | 8 | EIPICO8 | 45132 | 20317779.3
ORA - ZED - Landscape | 8 | 8 | ORA - ZED - Landscape8 | 45147 | 9578640.9799
Katameya - Creeks | 31 | 31 | Katameya - Creeks31 | 45138 | 37106226.16
Creeks - URBN K | 4 | 4 | Creeks - URBN K4 | 45138 | 8830426.33
ORA - ZED - ph.02 | 22 | 22 | ORA - ZED - ph.0222 | 45147 | 8466780.16
New Giza Hospital | 18 | 18 | New Giza Hospital18 | 45144 | 14934202.65
PKG#163 | 34 | 34 | PKG#16334 |  | 5000000
Astoria Hotel | 20 | 20 | Astoria Hotel20 | 45140 | 3400772
ORA - ZED | 29 | 29 | ORA - ZED29 | 45162 | 13678389.68
MDF Factory | 28 | 28 | MDF Factory28 | 45138 | 5471658.1245
Mivida-PK#189 | 15 | 15 | Mivida-PK#18915 | 45145 | 20013901.03
KSA-Tarek AbdelHakim Center | 4 | 4 | KSA-Tarek AbdelHakim Center4 | 45132 | 957216.97
SMP1 - Revamp | 4 | 4 | SMP1 - Revamp4 | 45170 | 2877592.22
DPW - Ph.02 | 7 | 7 | DPW - Ph.027 | 45166 | 16159880.26
Astoria Hotel | 21 | 21 | Astoria Hotel21 | 45183 | 854979
PKG#220B | 4 | 4 | PKG#220B4 |  | 2300000
MDF Factory | 29 | 29 | MDF Factory29 | 45179 | 13138195.96
Katameya - Creeks | 32 | 32 | Katameya - Creeks32 |  | 53390542.82
ORA - ZED - Landscape | 9 | 9 | ORA - ZED - Landscape9 | 45186 | 3636861.9198
ORA - ZED - ph.02 | 23 | 23 | ORA - ZED - ph.0223 | 45186 | 564270.13
New Giza Hospital | 19 | 19 | New Giza Hospital19 | 45183 | 5705542.36
PKG#177 | 52 | 52 | PKG#17752 |  | 45000000
ORA - ZED | 30 | 30 | ORA - ZED30 | 45186 | 13092650.18
Creeks - URBN K | 5 | 5 | Creeks - URBN K5 | 45161 | 13533059.96
Mivida-PK#189 | 16 | 16 | Mivida-PK#18916 | 45189 | 22512171.8728
EIPICO | 10 | 10 | EIPICO10 | 45166 | 6328837.05
Royal City - Landscape | 24 | 24 | Royal City - Landscape24 | 45173 | 3247942.88
Royal City | 43 | 43 | Royal City43 | 45173 | 13488633.46
DPW - Ph.02 | 8 | 8 | DPW - Ph.028 | 45173 | 20836254.44
EIPICO | 11 | 11 | EIPICO11 | 45209 | 30655535.07
ORA - ZED - ph.02 | 24 | 24 | ORA - ZED - ph.0224 | 45186 | 1374588.34
MDF Factory | 30 | 30 | MDF Factory30 | 45188 | 12581507.75
Katameya - Creeks | 33 | 33 | Katameya - Creeks33 | 45200 | 47329832.99
SMP1 - Revamp | 5 | 5 | SMP1 - Revamp5 | 45181 | 3101923.57
Creeks - URBN K | 6 | 6 | Creeks - URBN K6 | 45196 | 19608846.96
ORA - ZED | 31 | 31 | ORA - ZED31 | 45196 | 12746258.22
ORA - ZED - Landscape | 10 | 10 | ORA - ZED - Landscape10 | 45209 | 2654538.63
MDF Factory - Local Fabrication | 15 | 15 | MDF Factory - Local Fabrication15 | 45278 | 5457274.9
PKG#177 | 53 | 53 | PKG#17753 |  | 5000000
DPW - Ph.02 | 9 | 9 | DPW - Ph.029 | 45230 | 50195070.42
MDF Factory | 31 | 31 | MDF Factory31 | 45206 | 20429584.53
EIPICO | 12 | 12 | EIPICO12 | 45251 | 28595406.99
ORA - ZED - Landscape | 11 | 11 | ORA - ZED - Landscape11 | 45234 | 6014170.71
Katameya - Creeks | 34 | 34 | Katameya - Creeks34 | 45232 | 70308953.76
ORA - ZED - ph.02 | 25 | 25 | ORA - ZED - ph.0225 | 45237 | 996460.71
New Giza Hospital | 20 | 20 | New Giza Hospital20 | 45202 | 18995740.42
PKG#163 | 35 | 35 | PKG#16335 |  | 5000000
Astoria Hotel | 22 | 22 | Astoria Hotel22 | 45208 | 44838437.05
ORA - ZED | 32 | 32 | ORA - ZED32 | 45241 | 17052495.52
MDF Factory | 32 | 32 | MDF Factory32 | 45225 | 2726460
Mivida-PK#189 | 17 | 17 | Mivida-PK#18917 | 45216 | 47104890.06
Port Said Silos | 20 | 20 | Port Said Silos20 | 45231 | 10123399.3859
DPW - Ph.02 | 10 | 10 | DPW - Ph.0210 | 45259 | 44271228.34
Astoria Hotel | 23 | 23 | Astoria Hotel23 | 45253 | 17286732.59
MDF Factory | 33 | 33 | MDF Factory33 | 45255 | 12154985.64
Katameya - Creeks | 35 | 35 | Katameya - Creeks35 | 45266 | 46816344.41
ORA - ZED - Landscape | 12 | 12 | ORA - ZED - Landscape12 | 45250 | 7521516.04
ORA - ZED - ph.02 | 26 | 26 | ORA - ZED - ph.0226 | 45274 | 2944525.07
ORA - ZED | 33 | 33 | ORA - ZED33 | 45277 | 13971110.85
Mivida-PK#189 | 18 | 18 | Mivida-PK#18918 | 45262 | 20024965.62
Sokhna Port Expansion | 20 | 20 | Sokhna Port Expansion20 | 45224 | 13598323.882
CFC - Final Retention | 1 | 1 | CFC - Final Retention1 | 45213 | 12637074.78
New Giza Hospital | 21 | 21 | New Giza Hospital21 | 45215 | 8010369.24
Sokhna Port Expansion- 100m | 5 | 5 | Sokhna Port Expansion- 100m5 | 45224 | 3057123.2183
Baraka Land Fence | 1 | 1 | Baraka Land Fence1 | 45236 | 2645796
New Giza Hospital | 22 | 22 | New Giza Hospital22 | 45260 | 8695249.6
Sokhna Port Expansion | 21 | 21 | Sokhna Port Expansion21 | 45287 | 5872221.42
SMP1 - Revamp | 7 | 7 | SMP1 - Revamp7 | 45251 | 3428847.94
Port Said Silos | 21 | 21 | Port Said Silos21 | 45260 | 11711488.4753
DPW - Ph.02 | 11 | 11 | DPW - Ph.0211 | 45291 | 40849045.03
EIPICO | 13 | 13 | EIPICO13 | 45281 | 3870961.12
Mivida-PK#189 | 19 | 19 | Mivida-PK#18919 | 45293 | 23323710.1
MDF Factory | 34 | 34 | MDF Factory34 | 45280 | 13093494.9
Katameya - Creeks | 36 | 36 | Katameya - Creeks36 | 45290 | 50530225.45
New Giza Hospital | 23 | 23 | New Giza Hospital23 | 45318 | 4604562.68
Port Said Silos | 22 | 22 | Port Said Silos22 | 45274 | 4949068.8436
ORA - ZED | 34 | 34 | ORA - ZED34 | 45319 | 11514703.33
ORA - ZED - ph.02 | 27 | 27 | ORA - ZED - ph.0227 | 45305 | 6012429.48
MDF Factory - Equip. | 21 | 21 | MDF Factory - Equip.21 | 45285 | 592013.93
KSA-Tarek AbdelHakim Center | 11 | 11 | KSA-Tarek AbdelHakim Center11 | 45295 | 5080442.78
MDF Factory | 35 | 35 | MDF Factory35 | 45312 | 14005346.87
DPW - Ph.02 | 12 | 12 | DPW - Ph.0212 | 45326 | 15879945.92
Mivida-PK#189 - on account | 20 | 20 | Mivida-PK#189 - on account20 | 45302 | 135145955
Mivida-PK#189 | 21 | 21 | Mivida-PK#18921 | 45315 | 14476604.63
EIPICO | 14 | 14 | EIPICO14 | 45326 | 26305980.07
Katameya - Creeks | 37 | 37 | Katameya - Creeks37 | 45313 | 62109565.07
ORA - ZED | 35 | 35 | ORA - ZED35 | 45333 | 11302280.92
Creeks - URBN K | 10 | 10 | Creeks - URBN K10 | 45326 | 18357105.31
ORA - ZED - ph.02 | 28 | 28 | ORA - ZED - ph.0228 | 45354 | 1674078.17
ORA - ZED - Landscape | 13 | 13 | ORA - ZED - Landscape13 | 45342 | -674362.19
ORA - ZED - Landscape | 14 | 14 | ORA - ZED - Landscape14 | 45371 | 1008333.54
EIPICO | 15 | 15 | EIPICO15 | 45371 | 29236256.02
EIPICO | 15.1 | 15 | EIPICO15 |  | 29236256.02
Mivida-PK#189 | 22 | 22 | Mivida-PK#18922 | 45349 | 17552609
MDF Factory | 36 | 36 | MDF Factory36 | 45350 | 12150509.06
ORA - ZED - Landscape | 15 | 15 | ORA - ZED - Landscape15 | 45402 | 5175911.36
Katameya - Creeks | 38 | 38 | Katameya - Creeks38 | 45357 | 79235149.9
ORA - ZED | 36 | 36 | ORA - ZED36 | 45363 | 30791363.32
ORA - ZED - ph.02 | 29 | 29 | ORA - ZED - ph.0229 | 45385 | 651831.843
New Giza Hospital | 24 | 24 | New Giza Hospital24 | 45383 | 5494905.78
Creeks - URBN K | 11 | 11 | Creeks - URBN K11 | 45361 | 11569432.7
Rabigh Ext. - Piles | 1 | 1 | Rabigh Ext. - Piles1 | 45369 | 947881.6
Mivida-PK#189 | 23 | 23 | Mivida-PK#18923 | 45403 | 14242173.08
ORA - ZED - Landscape | 16 | 16 | ORA - ZED - Landscape16 | 45381 | 1521916.05
DPW - Ph.02 | 13 | 13 | DPW - Ph.0213 | 45383 | 18632592.11
Katameya - Creeks | 39 | 39 | Katameya - Creeks39 | 45384 | 66261026.21
MDF Factory | 37 | 37 | MDF Factory37 | 45384 | 7449862.86
ORA - ZED | 37 | 37 | ORA - ZED37 | 45388 | 9469567.93
Port Said Silos - Local Supply | 3 | 3 | Port Said Silos - Local Supply3 | 45364 | 2005309.5601
DPW - Ph.02 | 14 | 14 | DPW - Ph.0214 | 45426 | 35418927.4
Creeks - URBN K | 12 | 12 | Creeks - URBN K12 | 45385 | 8618325.74
ORA - ZED - ph.02 | 30 | 30 | ORA - ZED - ph.0230 | 45385 | -2279827.56
EIPICO | 16 | 16 | EIPICO16 | 45406 | 26365248.98
New Giza Hospital | 25 | 25 | New Giza Hospital25 | 45296 | 10195246.28
ORA - ZED - Landscape | 17 | 17 | ORA - ZED - Landscape17 | 45419 | 775773.82
ORA - ZED | 38 | 38 | ORA - ZED38 | 45421 | 12665876.69
MDF Factory | 38 | 38 | MDF Factory38 | 45406 | 10129299.6901
Port Said Silos - Local Supply | 4 | 4 | Port Said Silos - Local Supply4 | 45389 | 2837726.014
ORA - ZED - ph.02 | 31 | 31 | ORA - ZED - ph.0231 | 45419 | 3758520.95
Mivida-PK#189 | 24 | 24 | Mivida-PK#18924 | 45434 | 13803484.93
Port Said Silos | 27 | 27 | Port Said Silos27 | 45413 | 1090118.805
Rabigh Ext. - Piles | 2 | 2 | Rabigh Ext. - Piles2 | 45414 | 1174036.98
ORA - ZED - Landscape | 18 | 18 | ORA - ZED - Landscape18 | 45426 | 1643291.15
ORA - ZED - ph.02 | 32 | 32 | ORA - ZED - ph.0232 | 45448 | 2943652.2
MDF Factory | 39 | 39 | MDF Factory39 | 45434 | 7951387.28
Katameya - Creeks | 41 | 41 | Katameya - Creeks41 | 45437 | 45340679.8
ORA - ZED | 39 | 39 | ORA - ZED39 | 45449 | 7606231.5
Mivida-PK#189 | 25 | 25 | Mivida-PK#18925 | 45449 | 28360739.45
New Giza Hospital | 26 | 26 | New Giza Hospital26 | 45456 | 17232986.3
EIPICO | 17 | 17 | EIPICO17 | 45456 | 13161378
Port Said Silos - Local Supply | 5 | 5 | Port Said Silos - Local Supply5 | 45424 | 2131161.0294
PKG#163 | 36 | 36 | PKG#16336 |  | 10852799
PKG#177 | 54 | 54 | PKG#17754 |  | 14081143
Port Said Silos | 28 | 28 | Port Said Silos28 | 45445 | 2459043.7651
Wady Halfa - Escalation Claim | 3 | 3 | Wady Halfa - Escalation Claim3 | 45444 | 18633826.665
Wady Halfa - Escalation Claim | 3.1 | 3 | Wady Halfa - Escalation Claim3 | 45444 | 167704439.985
ORA - ZED - Landscape | 19 | 19 | ORA - ZED - Landscape19 | 45480 | 168189.5
ORA - ZED - ph.02 | 33 | 33 | ORA - ZED - ph.0233 | 45474 | 1631186.62
ORA - ZED | 40 | 40 | ORA - ZED40 | 45474 | 6599009.58
Katameya - Creeks | 42 | 42 | Katameya - Creeks42 | 45480 | 52791233.92
Port Said Silos - Local Supply | 6 | 6 | Port Said Silos - Local Supply6 | 45452 | 692035.1069
Rabigh Ext. - Piles | 4 | 4 | Rabigh Ext. - Piles4 | 45481 | 1787056.4437
Creeks - URBN K | 15 | 15 | Creeks - URBN K15 | 45455 | 10206848.68
Baraka Land Fence | 4 | 4 | Baraka Land Fence4 | 45433 | 8703054.16
SMP1 - Revamp | 10 | 10 | SMP1 - Revamp10 | 45447 | 3758608.34
Mivida-PK#189 | 26 | 26 | Mivida-PK#18926 | 45476 | 14177811.24
EIPICO | 18 | 18 | EIPICO18 | 45503 | 38010351.15
ORA - ZED - ph.02 | 34 | 34 | ORA - ZED - ph.0234 | 45510 | 3368948.46
ORA - ZED - Landscape | 20 | 20 | ORA - ZED - Landscape20 | 45496 | 1244123
MDF Factory | 42 | 42 | MDF Factory42 | 45497 | 7547918.7
Port Said Silos | 29 | 29 | Port Said Silos29 | 45481 | 1521379.1786
Mivida-PK#189 | 27 | 27 | Mivida-PK#18927 | 45505 | 4389859.04
Katameya - Creeks | 43 | 43 | Katameya - Creeks43 | 45500 | 30082113.9462
Creeks - URBN K | 16 | 16 | Creeks - URBN K16 | 45502 | 6345313.67
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 45435 | 3648396.5221
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 45525 | 2114752.93
New Giza Hospital | 27 | 27 | New Giza Hospital27 | 45522 | 13715277.6
ORA - ZED | 41 | 41 | ORA - ZED41 | 45535 | 3961614.17
Port Said Silos - Local Supply | 7 | 7 | Port Said Silos - Local Supply7 | 45491 | 3609101.6718
Mivida-PK#189 | 28 | 28 | Mivida-PK#18928 | 45535 | 2409288.21
Rabigh Ext. -Building | 2 | 2 | Rabigh Ext. -Building2 | 45529 | 4957387.2204
Port Said Silos | 30 | 30 | Port Said Silos30 | 45509 | 2352677.2563
MDF Factory | 43 | 43 | MDF Factory43 | 45525 | 57977475.46
ORA - ZED | 42 | 42 | ORA - ZED42 | 45536 | 3504951.97
ORA - ZED - ph.02 | 35 | 35 | ORA - ZED - ph.0235 | 45535 | 6454315.65
Katameya - Creeks | 44 | 44 | Katameya - Creeks44 | 45535 | 8345106.3
Creeks - URBN K | 17 | 17 | Creeks - URBN K17 | 45540 | 8554807.45
ORA - ZED - Landscape | 21 | 21 | ORA - ZED - Landscape21 | 45540 | 189683.6223
ORA - ZED - ph.02 | 36 | 36 | ORA - ZED - ph.0236 | 45540 | 6578211.32
EIPICO | 19 | 19 | EIPICO19 | 45557 | 29978125.14
Red Sea Museum | 3 | 3 | Red Sea Museum3 | 45537 | 1225041
MDF Factory | 44 | 44 | MDF Factory44 | 45561 | 13417821.66
ORA - ZED - Landscape | 22 | 22 | ORA - ZED - Landscape22 | 45551 | 1388299.8
ORA - ZED - ph.02 | 37 | 37 | ORA - ZED - ph.0237 | 45572 | 9153293.69
ORA - ZED | 43 | 43 | ORA - ZED43 | 45557 | 11004454.56
Rabigh Ext. -Building | 3 | 3 | Rabigh Ext. -Building3 | 45554 | 4088042.3344
Creeks - URBN K | 18 | 18 | Creeks - URBN K18 | 45560 | 9363449.62
Baraka Land Fence | 5 | 5 | Baraka Land Fence5 | 45524 | 5636679.16
New Giza Hospital | 28 | 28 | New Giza Hospital28 | 45568 | 6800969.24
Mivida-PK#189 | 29 | 29 | Mivida-PK#18929 | 45561 | 2690517.47
ORA - ZED - ph.02 | 38 | 38 | ORA - ZED - ph.0238 | 45572 | 3851310.01
ORA - ZED - ph.02 | 39 | 39 | ORA - ZED - ph.0239 | 45605 | 14526906.83
ORA - ZED | 44 | 44 | ORA - ZED44 | 45580 | 4559905.68
ORA - ZED - Landscape | 23 | 23 | ORA - ZED - Landscape23 | 45580 | 1551640.48
Rabigh Ext. -Building | 4 | 4 | Rabigh Ext. -Building4 | 45588 | 4796196.0024
MDF Factory | 45 | 45 | MDF Factory45 | 45600 | 21518034.22
Katameya - Creeks | 46 | 46 | Katameya - Creeks46 | 45600 | 22007540.78
Creeks - URBN K | 19 | 19 | Creeks - URBN K19 | 45598 | 6696306.5
Mivida-PK#189 | 30 | 30 | Mivida-PK#18930 | 45608 | 14412191.13

## eslam-to-invoicing
project name | must be
6TH October tunnel | October Under-Railway Tunnel
Abo Ghaleb Bridge | Abo Ghaleb
AEON
Al Jazi | Aljazi Project
Al Jazi - Center Zone | Aljazi Project
Al Jazi - Center Zone-DP | Aljazi Project
Al Jazi - Social Insurance | Aljazi Project
Al Jazi-DP | Aljazi Project
Alfa Lab | Alfa New Central Labs
Allegria-New Modifications
Astoria - Sharm | Astoria Sharm elSheikh
Astoria - Sharm-DP | Astoria Sharm elSheikh
Astoria Hotel | Waldorf Astoria Cairo
Astoria Hotel - DP | Waldorf Astoria Cairo
Astoria Hotel - Final Retention | Waldorf Astoria Cairo
Astoria Hotel - On Account | Waldorf Astoria Cairo
Astoria Hotel - Social Insurrance | Waldorf Astoria Cairo
Astoria Hotel - Spare Parts V.O 137 | Waldorf Astoria Cairo
Astoria Hotel IPCs 15-20 | Waldorf Astoria Cairo
Baraka Land Fence
Benban - Aswan
Benban - Aswan - DP
Cement Plant | Cement Factory-Beni Suef
Cement Plant -Last Claim | Cement Factory-Beni Suef
CFC | CFC Podium 2
CFC - Final Retention | CFC Podium 2
CFC-DP | CFC Podium 2
Comoros - DP | Le Galawa Hotel Resort
Comoros - Off Shore | Le Galawa Hotel Resort
Comoros - On Shore | Le Galawa Hotel Resort
Comoros - On Shore - On Account | Le Galawa Hotel Resort
Creeks - URBN K | Creeks URBN-K
Creeks - URBN K - DP | Creeks URBN-K
Creeks - URBN K - On Account | Creeks URBN-K
Damietta Port - Civil | Damietta Container Termin
Damietta Port - Civil - DP | Damietta Container Termin
Damietta Port - Infra - DP | Damietta Container Termin
DP World Sokhna | DPW Onshore Port & Terminal
DP World Sokhna-AP | DPW Onshore Port & Terminal
DPW - Ph.02 | DP World Basin 2 Ph2
DPW - Ph.02 - DP | DP World Basin 2 Ph2
EGAT Pelletizing Plant | EGAT Pelletizing Plant
EGAT Pelletizing Plant - Admin Building | EGAT Pelletizing Plant
EGAT Pelletizing Plant - Supply | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Concrete Infra | EGAT Pelletizing Plant
EGAT Pelletizing Plant-DP | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Escalation | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Mechanical Installation | EGAT Pelletizing Plant
EGAT Pelletizing Plant-MEP | EGAT Pelletizing Plant
EGAT Pelletizing Plant-MEP Coordination | EGAT Pelletizing Plant
EGAT Pelletizing Plant-On account | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Water Tank | EGAT Pelletizing Plant
EGAT-Asphalt
EGAT-Asphalt - Retenion Release
EGAT-EGAT ON Account
EGAT-Fence
EGAT-Fence - Retenion Release
EGAT-HeliPad
EGAT-Lock & Load | EGAT Lock & Load
EGAT-Lock & Load-AP | EGAT Lock & Load
EGAT-SZ
EGAT-Warehouse
EIPICO | EPICO 3 Facility
EIPICO-DP | EPICO 3 Facility
EIPICO-On Account | EPICO 3 Facility
El Sewedy Uni.-PKG.1 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.1-DP1 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2-DP2 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2-Social Insurrance | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3 - On Account | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3-DP | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3-Social Insurrance | Elsewedy Univ - Enabling Works
Elco Steel | Substation Elco Steel
Elco Steel - ADMIN. | Substation Elco Steel
Elco Steel - MEP | Substation Elco Steel
Elco Steel - MEP - Social Insurance | Substation Elco Steel
Elco Steel - Social Insurance | Substation Elco Steel
Elco Steel EGAT-DP | Substation Elco Steel
Elco Steel V.O | Substation Elco Steel
Elco Steel V.O-DP | Substation Elco Steel
Elco Steel V.O-Infra. Network | Substation Elco Steel
El-Gouna | DoubleTree Mangroovy ElGouna
El-Gouna - DP | DoubleTree Mangroovy ElGouna
El-Gouna - Equip. Rental | DoubleTree Mangroovy ElGouna
El-Gouna - Temp. Fence | DoubleTree Mangroovy ElGouna
EUA-DP
Existing Intake Apply -SSC-Mech
Existing Intake Supply -SSC-Mech
FIEM
FIEM - Retention
FIEM-Site Offices Rental Payment Request
H1 Solaymaneya-MEP
H1 Solaymaneya-MEP-DP
HQ - CFC | ElSewedy HQ Internal Finishing
HQ - CFC - DP | ElSewedy HQ Internal Finishing
HQ - CFC - Retention release | ElSewedy HQ Internal Finishing
HQ - CFC - Social Insurrance | ElSewedy HQ Internal Finishing
HyperOne | HyperOne Zayed Extension
HyperOne-DP | HyperOne Zayed Extension
HyperOne-Steel Supply | HyperOne Zayed Extension
HyperOne-VAT 1,2,3 | HyperOne Zayed Extension
IKEA | IKEA Extension MoA
IKEA-DP | IKEA Extension MoA
IKEA-Retention Release | IKEA Extension MoA
JICA
JICA-Site Offices Rental Payment Request
Kafr Shokr | Kafr Shokr Bridge
Kafr Shokr - Retention Release | Kafr Shokr Bridge
Katameya - Creeks | Kattameya Creeks
Katameya - Creeks - DP | Kattameya Creeks
Katameya - Creeks - DP - Alu Glass | Kattameya Creeks
Katameya - Creeks - On Account | Kattameya Creeks
KFW
KFW-Road Signals
Khatatba Bridge | El Khatatba Bridge
KSA-Tarek AbdelHakim Center
KSA-Tarek AbdelHakim Center - DP
LEKELA | Lekela 250MW Wind Farm
LEKELA - Supply Bill | Lekela 250MW Wind Farm
LEKELA- On Account | Lekela 250MW Wind Farm
LEKELA Remedial | Lekela 250MW Wind Farm
LEKELA Remedial-DP | Lekela 250MW Wind Farm
LEKELA-DP | Lekela 250MW Wind Farm
MDF Factory | MDF Factory
MDF Factory - Equip. | MDF Factory
MDF Factory - Local Fabrication | MDF Factory
MDF Factory-DP | MDF Factory
MDF Factory-F.F V.O-on account | MDF Factory
MDF Factory-Hold Amount release | MDF Factory
MDF Factory-Local Fab.-on account | MDF Factory
MDF Factory-on account | MDF Factory
MDF Factory-on account solera | MDF Factory
MDF Factory-P.O-on account | MDF Factory
Mechanical Installation | EGAT Mechanical Installations
Mechanical Installation-DP | EGAT Mechanical Installations
Mintra
Mintra-DP
Mintra-Hanger 1200m2
Mivida-PK#140 | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#140- Social Insurance | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#140-DP | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#189 | Mivida BP#189
Mivida-PK#189 - on account | Mivida BP#189
Mivida-PK#189 - Social insurance | Mivida BP#189
Mivida-PK#189-DP | Mivida BP#189
Mobilization
MOC | MOC HQ at Diriyah
MOC - DP | MOC HQ at Diriyah
New Gas Station | New Giza Teaching Hospital
New Giza Hospital | New Giza Teaching Hospital
New Giza Hospital-DP | New Giza Teaching Hospital
New Giza Hospital-On Account | New Giza Teaching Hospital
New Giza Hospital-Social Insurance | New Giza Teaching Hospital
NGU 2 | New Giza 2
NGU 2 - Retension release | New Giza 2
Old H1 remaining IPC
ORA - ZED | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Compansation | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Deficit | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - DP | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - On account | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Social Insurrance | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Landscape | Ora Zed Landscape Ph1
ORA - ZED - Landscape - Deficit | Ora Zed Landscape Ph1
ORA - ZED - Landscape - DP | Ora Zed Landscape Ph1
ORA - ZED - ph.02 | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - Claims | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - Deficit | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - On Account | ORA ZED-Ph 2-Pkgs A&D
PH.2-El Sewedy Uni. - Enabling | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Enabling - Retention release | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes - on account | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni.-DP | ESU Ph2-Enabling & Struc
PI Parks - ELSEWEDY
PI Parks - MEP
PI Parks - MEP-DP1
PI Parks - MEP-DP2
PK #107 | EMAAR-PKG#107-MARASSI
PK #117 | EMAAR-PKG117- MARASSI
PK #117 - Social Insurance | EMAAR-PKG117- MARASSI
PK #22 - Social Insurance | EMAAR-PKG#22-MARASSI
PK#22 | EMAAR-PKG#22-MARASSI
PK#32
PKG#101 | EMAAR-PKG# 101-UPTOWN
PKG#101- Social Insurance | EMAAR-PKG# 101-UPTOWN
PKG#101-DP | EMAAR-PKG# 101-UPTOWN
PKG#101-VO1&VO2 AP | EMAAR-PKG# 101-UPTOWN
PKG#144 | EMAAR-PKG# 144, Marassi
PKG#144 - Social Insurance | EMAAR-PKG# 144, Marassi
PKG#144-DP | EMAAR-PKG# 144, Marassi
PKG#162 | EMAAR-Pkg#162/163- Marassi
PKG#162- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#162-DP | EMAAR-Pkg#162/163- Marassi
PKG#163 | EMAAR-Pkg#162/163- Marassi
PKG#163- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#163-DP | EMAAR-Pkg#162/163- Marassi
PKG#177 | EMAAR-Pkg#162/163- Marassi
PKG#177 - DP | EMAAR-Pkg#162/163- Marassi
PKG#177 - on account | EMAAR-Pkg#162/163- Marassi
PKG#177 - SWI 07 | EMAAR-Pkg#162/163- Marassi
PKG#177- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#178 | BKG#178-Lagoon Discharge
PKG#178 - DP | BKG#178-Lagoon Discharge
PKG#178- Social Insurance | BKG#178-Lagoon Discharge
PKG#205
PKG#205 - DP
PKG#205-Social Insurance
PKG#220B | SOL Town PKG.220
PKG#220B - DP | SOL Town PKG.220
PKG#45
PKG#58
PKG#85 | EMAAR-PKG#85-UPTOWN
PO#11687
Port Said Silos | Port Said Port Silos
Port Said Silos - Foreigner Supply | Port Said Port Silos
Port Said Silos - Local Supply | Port Said Port Silos
Port Said Silos-DP | Port Said Port Silos
Port Said Silos-On account | Port Said Port Silos
Port Said Silos-Social Insurrance | Port Said Port Silos
PSP Substation
PSP Substation - Beni Suef
PSP Substation - DP
PSP Substation-Retention
Rabigh Ext. - Piles | Rabigh PP - Piling Works
Rabigh Ext. - Piles- DP | Rabigh PP - Piling Works
Rabigh Ext. -Building | Rabigh CCPP-Civil
Rabigh Ext. -Building- DP | Rabigh CCPP-Civil
Radamis-Concrete
Radamis-Concrete-DP
Radamis-H1 Main Builidng
Radamis-H1-On Account
Radamis-Rooms Fitout
Radamis-Rooms Fitout-DP
Radamis-Villas Finishes
Red Sea Museum | Red Sea Museum-Bab El-Bunt
Red Sea Museum - DP | Red Sea Museum-Bab El-Bunt
Ring Road - El Marg | RING ROAD MARYOTIA EXPANSION
Ring Road - El Marg - Retention Release | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib - refund | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib - Social Insurance | RING ROAD MARYOTIA EXPANSION
RO Apply -Mech- SSC
RO Eriction
RO Pump Room
RO - Supply - Electric
RO Supply -Mech- SSC
RO 2
RO Pump room - SSC - price diff.
RO.2
Rolling Mill #4-TRAESUEZ | EGAT New Rolling Mill 4
Rolling Mill #4-TRAESUEZ -AP | EGAT New Rolling Mill 4
Royal City | Royal City
Royal City - Landscape | Royal City
Royal City-DP 3 | Royal City
Royal City-DP 4 | Royal City
Royal City-DP1 | Royal City
Royal City-DP2 | Royal City
Saint Gobain Factory - DP
SIEMENS - Sokhna
SIEMENS - Sokhna - Bill
SMP1 - Revamp
SMP1 - Revamp - DP
SMP1 - Shut Down
SMP1 - Shut Down- Final Retention
SMP2 - Shut Down
SMP2 - Shut Down- Retention release
SMP2 - Shut Down- V.O
Sodic Club House | Sodic Club House
Sodic Club House - Social Insurance | Sodic Club House
Sodic Eastown | EDNC Retail & Offices Civil
Sodic Eastown - Landscape | EDNC Hardscape Package
Sodic Eastown - On Account | EDNC Retail & Offices Civil
Sodic Eastown - Social Insurance | EDNC Retail & Offices Civil
Sodic Eastown-DP | EDNC Retail & Offices Civil
Sokhna Port Expansion | Sokhna Port Expansion
Sokhna Port Expansion- 100m | Sokhna Port Expansion
Sokhna Port Expansion 100m- Escalation | Sokhna Port Expansion
Sokhna Port Expansion- EDECS | Sokhna Port Expansion
Sokhna Port Expansion- Escalation | Sokhna Port Expansion
Sokhna Port Expansion-AP | Sokhna Port Expansion
Sokhna Port Expansion-internal roads | Sokhna Port Expansion
Sports Hall - Civil Works | Olympic Multi – Sports Hall
Sports Hall - Finishes | Olympic Multi – Sports Hall
Sports Hall - Finishes - ADD.01 | Olympic Multi – Sports Hall
Sports Hall - Finishes - ADD.01 - Final Retention | Olympic Multi – Sports Hall
Sports Hall - Finishes - Landscape | Olympic Multi – Sports Hall
Sports Hall - Finishes - Landscape - Final Retention | Olympic Multi – Sports Hall
Sports Hall - Finishes - Social Insurance | Olympic Multi – Sports Hall
Sports Hall - MEP | Olympic Multi – Sports Hall
Sports Hall - MEP - DP | Olympic Multi – Sports Hall
Sports Hall - MEP - Final Retention | Olympic Multi – Sports Hall
Suez Intake & P Stations-ABB apply
Suez Intake & P Stations-ABB supply
Suez Intake & P Stations-ABB-Escalation
Suez Intake & P Stations-SSC apply
Suez Intake & P Stations-SSC supply
Suez Steel Intake & P Stations-DP
Suez Steel-Al Baraka-DP
Suez Steel-Gas Station-DP
SVC
SVC-DP
Uptown PK #53 | EMAAR-PKG#53-UPTOWN
Uptown PK #62 | EMAAR-PKG#62-UPTOWN
Uptown PK #62 - Retention | EMAAR-PKG#62-UPTOWN
Wady Halfa | Wadi Halfa Port
Wady Halfa - DP | Wadi Halfa Port
Wady Halfa - Escalation Claim | Wadi Halfa Port
Wady Halfa - Stoppage Period | Wadi Halfa Port
Western Fence
Western Fence-PO
Zayed Park

## data-from-invoicing
PROJECT_NAME | INV_NUM | invoice_number | concact | gross | collection from applied | on account from applied | collection
Cameron EDC | 013/2019 |  | Cameron EDC | 1465931.71 | 1464726.49 | 0 | 1464726.49
Cameron EDC | 006/2018 |  | Cameron EDC | 1261922.85 | 1260761.68 | 0 | 1260761.68
Cameron EDC | 029/2021 |  | Cameron EDC | 95747998.8 | 95747998.8 | 0 | 95747998.8
Cameron EDC | 023/202+L9+L7:Q7 |  | Cameron EDC | 69576437.45 | 13915287.49 | 0 | 34788218.49
Kuwait | Other Charge/J003 |  | Kuwait | 10656.5 | 6926.72 | 0 | 6926.72
Kuwait | Supply/H009 |  | Kuwait | 41451.49 | 26943.47 | 0 | 26943.47
Al-Shabab PP Phase II (CP-117) | 542 |  | Al-Shabab PP Phase II (CP-117) | 9940.36 | 9568.95 | 1708.5 | 11277.45
W Dam PP Phase II (CP-117) | 524 |  | W Dam PP Phase II (CP-117) | 28516.39 | 25202.32 | 4499.78 | 29702.1
W Dam PP Phase II (CP-117) | 180103 |  | W Dam PP Phase II (CP-117) | 5125.59 | 4583.19 | 808.8 | 5391.99
W Dam PP Phase II (CP-117) | 180099 |  | W Dam PP Phase II (CP-117) | 37929.47 | 33915.73 | 5985.13 | 39900.86
W Dam PP Phase II (CP-117) | 180092 |  | W Dam PP Phase II (CP-117) | 45343.38 | 40545.08 | 7155.02 | 47700.1
W Dam PP Phase II (CP-117) | 180090 |  | W Dam PP Phase II (CP-117) | 81098.89 | 72516.91 | 12797.1 | 85314.01
W Dam PP Phase II (CP-117) | 180042 |  | W Dam PP Phase II (CP-117) | 351162.1333 | 0 | 0 | 368720.24
Al-Shabab PP Phase II (CP-117) | 180030 |  | Al-Shabab PP Phase II (CP-117) | 128840.419 | 0 | 0 | 135282.44
Al-Shabab PP Phase II (CP-117) | 180029 |  | Al-Shabab PP Phase II (CP-117) | 72035.2857 | 0 | 0 | 75637.05
Al-Shabab PP Phase II (CP-117) | 180024 |  | Al-Shabab PP Phase II (CP-117) | 149161.9714 | 0 | 22642.79 | 22642.79
Al-Shabab PP Phase II (CP-117) | Inv 29 Shabab Egy | 29 | Al-Shabab PP Phase II (CP-117)29 | 143493.8212 | 128309.13 | 22642.79 | 150951.92
W Dam PP Phase II (CP-117) | 23 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 341586.6381 | 304866.07 | 53799.9 | 358665.97
W Dam PP Phase II (CP-117) | 8 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 12401061.796 | 8241564.96 | 1873180.7 | 12669314.2001
Al-Shabab PP Phase II (CP-117) | 13 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2938328.9619 | -314874.28 | 462786.81 | 452339.97
Al-Shabab PP Phase II (CP-117) | 17 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 259030.0857 | 244213.97 | 40797.24 | 285011.21
W Dam PP Phase II (CP-117) | 7 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 1070847.7778 | 844130.92 | 160471.5 | 1124390.1667
Al-Shabab PP Phase II (CP-117) | 3 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2508074.5751 | 0 | 380725.72 | 2538171.47
Suez Gulf Substation | 180047 |  | Suez Gulf Substation | 336722.54 | 318808.92 | 35423.21 | 354232.13
Suez Gulf Substation | 16 EGP-progress repo |  | Suez Gulf Substation | 3142077.2571 | 0 | 0 | 0
Suez Gulf Substation | Inv 4 EGP VO SG | 4 | Suez Gulf Substation4 | 229413.8 | 216800.04 | 24084.45 | 240884.49
Suez Gulf Substation | 8 EGP Suez Gulf |  | Suez Gulf Substation | 2957422.0857 | 2791958.72 | 0 | 2791958.72
Suez Gulf Substation | 481 |  | Suez Gulf Substation | 670083.38 | 634419.9 | 70491.1 | 704911
Suez Gulf Substation | 14 USD Suez Gulf |  | Suez Gulf Substation | 296941 | 280609.24 | 31178.81 | 311788.05
Suez Gulf Substation | 14 USD - Suez Gulf |  | Suez Gulf Substation | 296940.9905 | 0 | 31178.8 | 31178.8
Suez Gulf Substation | 11 USD - Suez Gulf |  | Suez Gulf Substation | 73364.13 | 0 | 7336.41 | 73364.13
Pyramids Industrial P - East | Inv. 16 PIP EAST | 16 | Pyramids Industrial P - East16 | 18308153.18 | 7212729.5094 | 1317140.66 | 8529870.1694
Abou El Matameer and Sammanoud | Abo Matamir 1 |  | Abou El Matameer and Sammanoud | 27483009.5 | 19875810.07 | 4122451.43 | 23998261.5
Siemens 6x500/220 KV GIS-MOU | Inv 63 P15 Banha Fin | 63 | Siemens 6x500/220 KV GIS-MOU63 | 1037425.1 | 750473.31 | 155613.77 | 906087.08
Barwa 2x60/22 KV S/S | Inv 29 Barwa | 29 | Barwa 2x60/22 KV S/S29 | 1921317.79 | 1359198.33 | 288197.67 | 1647396
Barwa 2x60/22 KV S/S | Inv 19 Barwa | 19 | Barwa 2x60/22 KV S/S19 | 5822687.66 | 4119121.2 | 873403.15 | 4992524.35
Damac 2x60/22 KV S/S | Inv 27 Damac | 27 | Damac 2x60/22 KV S/S27 | 3197424.84 | 2261973.2 | 479613.73 | 2741586.93
Damac 2x60/22 KV S/S | inv 18 Damac | 18 | Damac 2x60/22 KV S/S18 | 1454300.47 | 1028483.12 | 218145.1 | 1246628.22
IRAQ - Substations Soil Invest | 6 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
Abo Quir - Badr 500KV | 1 |  | Abo Quir - Badr 500KV | 12972376.91 | 915776.51 | 0 | 986999.16
South Helwan PP (CP-117) | 2 EGP - South Helwan |  | South Helwan PP (CP-117) | 3216085.3429 | 3376889.61 | 0 | 3376889.61
Abu Qir PP (CP-118) | 448 EGP - Avice |  | Abu Qir PP (CP-118) | 50265.29 | 55291.819 | 0 | 55291.819
Al-Shabab PP Phase II (CP-117) | 11 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 200592 | 30088.8 | 0 | 30088.8
Al-Shabab PP Phase II (CP-117) | 10 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 8803626.76 | 7337016.45 | 0 | 8803626.76
New Capital | Inv. 4 ElTebeen | 4 | New Capital4 | 992670.47 | 757742.66 | 104230.41 | 861973.07
South Helwan PP (CP-117) | 180066 |  | South Helwan PP (CP-117) | -178521.44 | 0 | -28117.13 | -28117.13
Gabal Elgalalaa | ختامى |  | Gabal Elgalalaa | 2159417.2 | 2273473.76 | 0 | 1136736.88
Berket Ghelion | Gheleon 7 |  | Berket Ghelion | 14736103 | 8804450.07 | 3684025.75 | 12488475.82
Berket Ghelion | 3 gheleon |  | Berket Ghelion | 1054874.93 | 629864.1 | 263718.75 | 893582.85
Beni-Suef Power Plant EPC | DEC ADJ 74 |  | Beni-Suef Power Plant EPC | 1868344294.99 | 300000000 | 0 | 300000000
Ismailiya East Substation | ISE-CW-EGP-19 | 19 | Ismailiya East Substation19 | 2021873 | 1496186.02 | 303280.95 | 1799466.97
Ismailiya East Substation | ISE-SD-EURO-02 | 2 | Ismailiya East Substation2 | 415477.11 | 338629.09 | 31145.54 | 369774.63
Tamey El-amdeed Substation | TAM-SW-EGP-10 | 10 | Tamey El-amdeed Substation10 | 350000 | 0 | 52500 | 52500
Tamey El-amdeed Substation | TAM-CW-EURO-07 | 7 | Tamey El-amdeed Substation7 | 910634.32 | 673869.4 | 136595.15 | 810464.55
Tamey El-amdeed Substation | TAM-CW-EGP-16 | 16 | Tamey El-amdeed Substation16 | 3130125.15 | 2316292.61 | 469518.77 | 2785811.38
Ismailiya East Substation | ISE-SW-EGP-03 | 3 | Ismailiya East Substation3 | 1730063 | 1280246.62 | 259509.45 | 1539756.07
Beni Suef Substation R61 | BSF-CW-EGP-16 | 16 | Beni Suef Substation R6116 | 4519671.75 | 3344557.09 | 677950.76 | 4022507.85
Tamey El-amdeed Substation | TAM-SW-EGP-06 | 6 | Tamey El-amdeed Substation6 | 774375 | 572427.4 | 116156.25 | 688583.65
Ismailiya East Substation | ISE-CW-EGP-13 | 13 | Ismailiya East Substation13 | 2014407 | 1490661.18 | 302161.05 | 1792822.23
Tamey El-amdeed Substation | 19100029 |  | Tamey El-amdeed Substation | 7806604.04 | 6557547.39 | 1170990.61 | 7728538
Tamey El-amdeed Substation | 19100018 |  | Tamey El-amdeed Substation | 3170363.04 | 2346068.65 | 475554.46 | 2821623.11
Tamey El-amdeed Substation | TAM-SW-EGP-03 | 3 | Tamey El-amdeed Substation3 | 1662500 | 1230250 | 249375 | 1479625
Beni Suef Substation R61 | BSF-CW-EUR-04 | 4 | Beni Suef Substation R614 | 660160.21 | 491819.36 | 99024.03 | 590843.39
Al Mostathmreen GIS Substation | MOS-SD-EURO-09 | 9 | Al Mostathmreen GIS Substation9 | 1774768.17 | 1286706.92 | 266215.23 | 1552922.15
Tamey El-amdeed Substation | TAM-SD-EURO-02 | 2 | Tamey El-amdeed Substation2 | 3063622.83 | 2588761.29 | 459543.43 | 3048304.72
Beni Suef Substation R61 | BSF-CW-EGP-9 | 9 | Beni Suef Substation R619 | 2915086 | 2171210.17 | 437262.9 | 2608473.07
Beni Suef Substation R61 | BINI SUEF SD-EG-IPC2 | 2 | Beni Suef Substation R612 | 212655 | 157932.21 | 31898.25 | 189830.46
Beni Suef Substation R61 | (4)cw beni suif |  | Beni Suef Substation R61 | 12888090 | 9601100.35 | 1933213.5 | 11534313.85
Al Mostathmreen GIS Substation | 19sd mosstasmreen |  | Al Mostathmreen GIS Substation | 3892392 | 2899694.34 | 583939.8 | 3483634.14
Al Mostathmreen GIS Substation | 12 cw mosstasmreen |  | Al Mostathmreen GIS Substation | 3371467 | 2511742.83 | 505720.1 | 3017462.93
Al Mostathmreen GIS Substation | MOS (2) |  | Al Mostathmreen GIS Substation | 1418842 | 1057037.16 | 212826.38 | 1269863.54
Al Mostathmreen GIS Substation | (14)SD EGP |  | Al Mostathmreen GIS Substation | 4364100 | 2875908.09 | 654615 | 3530523.09
Al-Shabab PP Phase II (CP-117) | 180129 |  | Al-Shabab PP Phase II (CP-117) | 106768.36 | 95470 | 16847.65 | 112317.65
Al-Shabab PP Phase II (CP-117) | 24 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 275367.2 | 245765.23 | 43370.33 | 289135.56
W Dam PP Phase II (CP-117) | 21 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 229506.4381 | 204834.5 | 36147.26 | 240981.76
W Dam PP Phase II (CP-117) | Adv. 6 USD - Domiat |  | W Dam PP Phase II (CP-117) | 34554.57 | 0 | 34554.57 | 34554.57
Al-Shabab PP Phase II (CP-117) | 180032 |  | Al-Shabab PP Phase II (CP-117) | 283629.7048 | 0 | 0 | 297811.19
Sodic Club House | SODIC CLUB-IPC 30 | 30 | Sodic Club House30 | 3864214.5 | 3772207.955 | 457665.76 | 4229873.715
Sodic Club House | (24) SODIC CLUB |  | Sodic Club House | 5827019 | 4702936.55 | 492791.84 | 5195728.39
Berket Ghelion | 2 ghelion |  | Berket Ghelion | 1054185.23 | 374553.85 | 263546.35 | 638100.2
Berket Ghelion | Gheleon 8 |  | Berket Ghelion | 5661090 | 3382272.35 | 1415272.5 | 4797544.85
Berket Ghelion | Gheleon 9 |  | Berket Ghelion | 2168291.8 | 1295466.6 | 542072.95 | 1837539.55
Sodic Club House | (18) SODIC CLUB |  | Sodic Club House | 3502070 | 2242406.65 | 683045.8 | 2925452.45
New Giza 2 | (22)new giza 2 |  | New Giza 2 | 5330400 | 3766112.21 | 1119384.19 | 4885496.4
EMAAR-PKG#53-UPTOWN | (24)pkg#53 |  | EMAAR-PKG#53-UPTOWN | 10899351 | 8522042.54 | 1665924.29 | 10187966.83
EMAAR-PKG#62-UPTOWN | (4) pkg#62 |  | EMAAR-PKG#62-UPTOWN | 2488472 | 1557907.49 | 896223.49 | 2454130.98
EMAAR-PKG#62-UPTOWN | (2) pkg#62 |  | EMAAR-PKG#62-UPTOWN | 1439963.03 | 954127.9315 | 518602.69 | 1472730.6215
EMAAR-PKG#107-MARASSI | (2) PKG#107 |  | EMAAR-PKG#107-MARASSI | 7583995 | 5882564.35 | 1104841.46 | 6987405.81
Berket Ghelion | 5 |  | Berket Ghelion | 7680073.2 | 4588843.68 | 1920018.3 | 6508861.98
Beni Seuf - 358 | Inv. 14 Oewon Mousa | 14 | Beni Seuf - 35814 | 26621468.3 | 0 | 4584283.15 | 4584283.15
Beni Seuf - 358 | Inv. 3 Oewon Mousa | 3 | Beni Seuf - 3583 | 54100230.27 | 37478143.6 | 9048054.44 | 46526198.04
Beni Seuf - 358 | Inv No 1 Abo matamir | 1 | Beni Seuf - 3581 | 164349234 | 130657641.03 | 24652385.1 | 155310026.13
New Capital | inv 3 ABO ZAABL | 3 | New Capital3 | 13724989.7 | 10650512.42 | 1441123.92 | 12091636.34
Al-Shabab PP Phase II (CP-117) | 6 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2584814.8617 | 2156279.45 | 392374.9 | 2615832.64
W Dam PP Phase II (CP-117) | 5 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 80929.5238 | 70046.78 | 12746.4 | 84976
Siemens 6x500/220 KV GIS-MOU | inv 43 P 11 maghaha | 43 | Siemens 6x500/220 KV GIS-MOU43 | 5068762.7 | 4173619.21 | 760314.41 | 4933933.62
Kayan 3 New Cairo Capital City | (1)elkayan mep |  | Kayan 3 New Cairo Capital City | 42618766.5 | 23793093.25 | 11000000 | 34793093.25
Giza North PP Ph I,II (CP-117) | 36 EGP-Giza No. I&II |  | Giza North PP Ph I,II (CP-117) | 3410847.2762 | 3156334.72 | 0 | 3161444.44
Giza North PP Ph I,II (CP-117) | Inv 38 Giza I,II EGP | 38 | Giza North PP Ph I,II (CP-117)38 | 19232.0762 | 20193.68 | 0 | 20193.68
South Helwan PP (CP-117) | 5 EGP - South Helwan |  | South Helwan PP (CP-117) | 110060.2 | 115563.21 | 0 | 115563.21
K047 FDH JV | Inv. No.14 KWD Floor | 14 | K047 FDH JV14 | 46962.58 | 42266.32 | 0 | 42266.32
Royal City | royal city-ipc21 | 21 | Royal City21 | 5449100.47 | 4449615.6735 | 2171112.14 | 6620727.8135
Royal City | ROYAL CITY-IPC19 | 19 | Royal City19 | 13865958.08 | 9999974.764 | 4561622.58 | 14561597.344
Royal City | ROYAL CITY- IPC 16 | 16 | Royal City16 | 8643111 | 7847127.4 | 3339460.9 | 11186588.3
Royal City | royal city- ipc(6) | 6 | Royal City6 | 16468073.59 | 12495801.3995 | 1991776.18 | 14487577.5795
Royal City | 4 royal city |  | Royal City | 9771128.39 | 10437271.5995 | 1978041.37 | 12415312.9695
Sodic Club House | (20) SODIC CLUB |  | Sodic Club House | 6271752 | 4786483.4 | 652247.67 | 5438731.07
New Heliopolis | Inv. 14 Heliopolise | 14 | New Heliopolis14 | 9889428.05 | 7854991.7 | 971141.84 | 8826133.54
New Heliopolis | Inv. 12 Heliopolise | 12 | New Heliopolis12 | 14257265.95 | 10545252.1 | 1400063.55 | 11945315.65
New Heliopolis | Inv. 11 Heliopolise | 11 | New Heliopolis11 | 6739225.68 | 1995725.2 | 246785.55 | 6468645.38
New Heliopolis | Inv. 9 Heliopolise | 9 | New Heliopolis9 | 11369259.7 | 9026182.05 | 1116461.35 | 10142643.4
New Heliopolis | Inv.3 Heliopolis | 3 | New Heliopolis3 | 17434357.5 | 13932862.5 | 1712053.95 | 15644916.45
New Heliopolis | Inv.2 Heliopolis | 2 | New Heliopolis2 | 1307027.35 | 427219.65 | 743412.6 | 1170632.25
Berket Ghelion | 4 |  | Berket Ghelion | 783945 | 468407.13 | 195986.25 | 664393.38
Barwa and Damac 220 OHTL | Inv. 1 Wattany 220 | 1 | Barwa and Damac 220 OHTL1 | 9000846.47 | 6271671.2 | 1350127 | 7621798.2
Siemens 6x500/220 KV GIS-MOU | Inv 47 P10 Banha | 47 | Siemens 6x500/220 KV GIS-MOU47 | 859781.95 | 621966.26 | 128967.29 | 750933.55
Siemens 6x500/220 KV GIS-MOU | Soc. 48 Wadi 13 |  | Siemens 6x500/220 KV GIS-MOU | 65762.69 | 65762.68 | 0 | 65762.68
Damac 2x60/22 KV S/S | 11 |  | Damac 2x60/22 KV S/S | 4981194.27 | 3221710.1 | 683140.5 | 4331774.87
Damac 2x60/22 KV S/S | Inv 29 Damac | 29 | Damac 2x60/22 KV S/S29 | 1921317.79 | 1359197.92 | 288197.67 | 1647395.59
Flour project | 10072 |  | Flour project | 129525.085 | 129525.005 | 0 | 129525.005
Siemens 6x500/220 KV GIS-MOU | inv 45 P 9 Banha | 45 | Siemens 6x500/220 KV GIS-MOU45 | 1258161.08 | 910153.73 | 188724.16 | 1098877.89
Barwa 2x60/22 KV S/S | Inv 27 Barwa | 27 | Barwa 2x60/22 KV S/S27 | 3197424.84 | 2261955.56 | 479613.74 | 2741569.3
South Helwan PP (CP-117) | 2009210004 |  | South Helwan PP (CP-117) | 149277.25 | 133480.55 | 23555.39 | 157035.94
W Dam PP Phase II (CP-117) | 12 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 256784.1143 | 229179.82 | 40443.5 | 269623.32
Al-Shabab PP Phase II (CP-117) | 10 USD-Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 889996.619 | 794321.98 | 140174.47 | 934496.45
South Helwan PP (CP-117) | 180139 |  | South Helwan PP (CP-117) | 218299.92 | 217221.36 | 0 | 217221.36
South Helwan PP (CP-117) | 180072 |  | South Helwan PP (CP-117) | 3090453.78 | 2763418.24 | 487662.04 | 3251080.28
South Helwan PP (CP-117) | 180071 |  | South Helwan PP (CP-117) | 146028.99 | 130576.02 | 23042.83 | 153618.85
South Helwan PP (CP-117) | 180062 |  | South Helwan PP (CP-117) | -201244.72 | -179948.77 | -31755.66 | -211704.43
South Helwan PP (CP-117) | 19 EGP Rev. 2 |  | South Helwan PP (CP-117) | 186278.98 | 166253.99 | 29338.94 | 195592.93
South Helwan PP (CP-117) | 14 EGP - South Helwa |  | South Helwan PP (CP-117) | 79351.92 | 70954.8 | 12521.44 | 83476.24
Suez Gulf Substation | 13 USD Suez Gulf |  | Suez Gulf Substation | 81842.19 | 81842.19 | 0 | 81842.19
Suez Gulf Substation | 6 USD Suez Gulf |  | Suez Gulf Substation | 334563.84 | 134563.84 | 0 | 134563.84
W Dam PP Phase II (CP-117) | 20 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 466026.0571 | 415928.26 | 73399.1 | 489327.36
Al-Shabab PP Phase II (CP-117) | 21 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 362995.381 | 323973.38 | 57171.77 | 381145.15
Beni Suef ISKRA | Iskra Inv 7 | 7 | Beni Suef ISKRA7 | 139090.69 | 118227.09 | 20863.6 | 139090.69
Abu Qir PP (CP-118) | Inv No AC017454 Avic |  | Abu Qir PP (CP-118) | 528790.94 | 528790.94 | 0 | 528790.94
Apache Electrical Works | Apachi Inv No PC.#25 |  | Apache Electrical Works | 82071.34 | 82071.34 | 0 | 82071.34
Beni Suef Substation R61 | (20)bine seuf 2 |  | Beni Suef Substation R61 | 10654535 | 7387528.75 | 2639340.9 | 10026869.65
Sodic Club House | (23) sodic culb |  | Sodic Club House | 4559187 | 2843967.14 | 3462410.52 | 6306377.66
Tunnel of Sokhna Road | SOKHNA TUNNLE-FINAL |  | Tunnel of Sokhna Road | 1226927.69 | 2871215 | 567657.25 | 3438872.25
Al Mostathmreen GIS Substation | cw (7) mosstasmreen |  | Al Mostathmreen GIS Substation | 1714985 | 1277663.74 | 257247.8 | 1534911.54
Ghana | 30/P/10/ER/2017/USDD |  | Ghana | 281189.93 | 281187.43 | 0 | 281187.43
W Dam PP Phase II (CP-117) | 9 USD- West Domiat |  | W Dam PP Phase II (CP-117) | 70239.86 | 70239.86 | 0 | 70239.86
South Helwan PP (CP-117) | 7 EuroSouth Helwan |  | South Helwan PP (CP-117) | 18669.41 | 18669.41 | 0 | 18669.41
EMAAR-PKG#62-UPTOWN | (5) pkg#62 |  | EMAAR-PKG#62-UPTOWN | 3571360 | 2126676.82 | 1395651.53 | 3522328.35
Suez Gulf Substation | 14 EGP - Suez Gulf |  | Suez Gulf Substation | 4048783.0476 | 3902894.09 | 348328.11 | 4251222.2
Military 110 Kayan Project | Inv No1 ElKean 220 | 1 | Military 110 Kayan Project1 | 91633182.6 | 64333443.95 | 0 | 64333443.95
Beni Suef Substation R61 | (21)BINE SUIF 2 |  | Beni Suef Substation R61 | 6009985 | 3530944.84 | 1330933.16 | 4861878
Barwa and Damac 220 OHTL | Inv No2 Wattanya220 | 2 | Barwa and Damac 220 OHTL2 | 6435005.73 | 4809754.28 | 965250.9 | 5775005.18
Kuraimate - Samalot 500KV | remaining advance |  | Kuraimate - Samalot 500KV | 22053.6 | 22053.6 | 0 | 22053.6
Al-Shabab PP Phase II (CP-117) | 5 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 873061.28 | 0 | 0 | 873061.28
Suez Gulf Substation | Inv 2 SG VO | 2 | Suez Gulf Substation2 | 71428.5714 | 67500 | 7500 | 75000
EMAAR-PKG#62-UPTOWN | (7) pkg#62 |  | EMAAR-PKG#62-UPTOWN | 2975812 | 1863217.83 | 1071738.87 | 2934956.7
Royal City | (2) royal city |  | Royal City | 4721022 | 4894014.77 | 930098.25 | 5824113.02
Al Mostathmreen GIS Substation | (11) CW |  | Al Mostathmreen GIS Substation | 1411925 | 1083124.51 | 211788.86 | 1294913.37
Ghana | 35/P/10/ER/2017/USD |  | Ghana | 117167.53 | 117165.03 | 0 | 117165.03
Kuwait | 2-132KVA-H | 132 | Kuwait132 | 46009.19 | 34506.88 | 0 | 34506.88
Amal Bridge Lock & Load | (1) ALAMAL BRIDGE |  | Amal Bridge Lock & Load | 18987162 | 7381482.4 | 6000000 | 17910234.2
Al-Shabab PP Phase II (CP-117) | 23 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 340212.3048 | 303639.48 | 53583.44 | 357222.92
Al-Shabab PP Phase II (CP-117) | 19 EGP -Shabab |  | Al-Shabab PP Phase II (CP-117) | 2478340.69 | 2211919.06 | 390338.66 | 2602257.72
Al-Shabab PP Phase II (CP-117) | 19 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 2580132 | 0 | 0 | 2709138.6
Akhmem Assiut | Inv.41 Assuit Akhmem | 41 | Akhmem Assiut41 | 2815401.73 | 2139705.31 | 422310.26 | 2562015.57
Akhmem Assiut | Inv.29 Assuit Akhmem | 29 | Akhmem Assiut29 | 4146362.89 | 2466557 | 621954.44 | 3088511.44
Akhmem Assiut | Inv.23 Assuit Akhmem | 23 | Akhmem Assiut23 | 13770214.33 | 10946791.69 | 2065532.15 | 13012323.84
Akhmem Assiut | Inv.1 Assuit / Akhme | 1 | Akhmem Assiut1 | 54753996.0608 | 32578627.6108 | 8213099.42 | 40791727.0308
Akhmem - Qena | Inv.42 Qena Akhmem | 42 | Akhmem - Qena42 | 11371428.68 | 7902614.02 | 1705714.3 | 9608328.32
Akhmem - Qena | Inv.31 Akhmem Qena | 31 | Akhmem - Qena31 | 6426120.19 | 4466153.53 | 963918.03 | 5430071.56
Akhmem - Qena | Inv.24 Akhmem Qena | 24 | Akhmem - Qena24 | 697914.13 | 554841.73 | 104687.12 | 659528.85
Akhmem - Qena | Inv.19 Qena - Akhmem | 19 | Akhmem - Qena19 | 7654643.15 | 6085441.3 | 1148196.47 | 7233637.77
Akhmem - Qena | Inv.13 Qena - Akhmem | 13 | Akhmem - Qena13 | 22634732.33 | 17994612.21 | 3395209.85 | 21389822.06
Bani Suef Old Substation | (23-24) bine suef2 | 24 | Bani Suef Old Substation24 | 7945021 | 21570743.94 | 0 | 21645237.44
W Dam PP Phase II (CP-117) | 26 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 730604.419 | 652064.44 | 115070.2 | 767134.64
W Dam PP Phase II (CP-117) | 28 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 837248.1333 | 747243.96 | 131866.58 | 879110.54
South Helwan PP (CP-117) | 16 EGP - South Helwa |  | South Helwan PP (CP-117) | 135908.81 | 121526.78 | 21445.9 | 142972.68
EMAAR-PKG#62-UPTOWN | OB-SI-PKG#62 |  | EMAAR-PKG#62-UPTOWN | 136616.41 | 135307.5 | 0 | 135307.5
Sodic Club House | IPC 25 Sodic club | 25 | Sodic Club House25 | 1334415.96 | 992455.088 | 367373.93 | 1359829.018
EMAAR-PKG#53-UPTOWN | (27) pkg#53 |  | EMAAR-PKG#53-UPTOWN | 11200624.22 | 10524733.29 | 1975581.31 | 12500314.6
Siemens 6x500/220 KV GIS-MOU | Ret. Maghaghah |  | Siemens 6x500/220 KV GIS-MOU | 3027063.98 | 3027063.98 | 0 | 3027063.98
Ismailiya East Substation | (2)CW esma3liya |  | Ismailiya East Substation | 4449390 | 3314795.55 | 667408.5 | 3982204.05
Ghana | 38/P/10/ER/2017/USD |  | Ghana | 597383.57 | 597369.07 | 0 | 597369.07
Sodic Club House | SODIC CLUB-IPC(29) | 29 | Sodic Club House29 | 6355200.49 | 6349192.7245 | 1525799.46 | 7874992.1845
Abou El Matameer and Sammanoud | Inv101 P13- Sammound | 101 | Abou El Matameer and Sammanoud101 | 1134164.257 | 814759.3749 | 170124.64 | 984884.0149
Abou El Matameer and Sammanoud | Inv102 P14- Sammound | 102 | Abou El Matameer and Sammanoud102 | 4372281.31 | 3578275.03 | 655842.2 | 4234117.23
Abou El Matameer and Sammanoud | Inv 90 P8- Sammound | 90 | Abou El Matameer and Sammanoud90 | 2776641.7 | 1994739.39 | 416496.26 | 2411235.65
Abou El Matameer and Sammanoud | Inv 89P10Abo Matamir | 89 | Abou El Matameer and Sammanoud89 | 2696183.68 | 1936938.35 | 404427.55 | 2341365.9
Abou El Matameer and Sammanoud | Abo Matamir 2 |  | Abou El Matameer and Sammanoud | 22131315.02 | 16009793.28 | 3319697.25 | 19329490.53
El Mostakbal City Project | Inv. 14 Mostakbal | 14 | El Mostakbal City Project14 | 24883709.07 | 19537665 | 5225578.9 | 24763243.9
El Mostakbal City Project | Inv. 13 Mostakbal | 13 | El Mostakbal City Project13 | 56614142.4 | 46989738.2 | 11888969.9 | 58878708.1
EMAAR-PKG#53-UPTOWN | (26)pkg#53 |  | EMAAR-PKG#53-UPTOWN | 18120127 | 14111649.09 | 2646190.12 | 16757839.21
Akhmem Assiut | inv. 2 Assuit Akhmem | 2 | Akhmem Assiut2 | 97876463.87 | 58236496.0392 | 14681469.57 | 72917965.6092
Badr | Inv. 26 Badr | 26 | Badr26 | 4555798.45 | 3133978.5 | 683369.8 | 3817348.3
Badr | Inv. 18 Badr | 18 | Badr18 | 10138245.91 | 615386.2 | 1520736.89 | 2136123.09
Badr | Inv. 11 Badr | 11 | Badr11 | 8380645.68 | 6222215.2 | 1257096.9 | 7479312.1
Badr | Inv. 7 Badr | 7 | Badr7 | 4936937.6 | 3665267.2 | 740540.65 | 4405807.85
Sodic Club House | (22)sodic club |  | Sodic Club House | 2015405 | 1742662.28 | 331069.04 | 2073731.32
Siemens 6x500/220 KV GIS-MOU | Inv 66 P19El Natroun | 66 | Siemens 6x500/220 KV GIS-MOU66 | 2481044.326 | 1794787.46 | 372156.65 | 2166944.11
Siemens 6x500/220 KV GIS-MOU | Inv 70 P9 Assuit | 70 | Siemens 6x500/220 KV GIS-MOU70 | 4499678.017 | 3255067.077 | 674951.7 | 3930018.777
EMAAR-PKG#107-MARASSI | (10) pkg#107 |  | EMAAR-PKG#107-MARASSI | 2025522 | 1551018.61 | 294867.37 | 1845885.98
EMAAR-PKG#53-UPTOWN | PKG#53-IPC 32 | 32 | EMAAR-PKG#53-UPTOWN32 | 4777477.68 | 2883132.62 | 1500499.95 | 4383632.57
Suez Gulf Substation | 180088 |  | Suez Gulf Substation | 3536.21 | 3720 | 0 | 3720
Siemens 6x500/220 KV GIS-MOU | Inv 72 P10 Assuit | 72 | Siemens 6x500/220 KV GIS-MOU72 | 4810720.93 | 3480075.52 | 721608.14 | 4201683.66
Military 110 Kayan Project | Inv. 8 Elkayan | 8 | Military 110 Kayan Project8 | 40307587.08 | 33287405.75 | 0 | 33287405.75
Military 110 Kayan Project | Inv. 9 Elkayan | 9 | Military 110 Kayan Project9 | 17854430.61 | 16123682.4 | 0 | 16123682.4
Suez Gulf Substation | 5 EGP-VO Shipping |  | Suez Gulf Substation | 958678.0762 | 905950.78 | 100661.2 | 1006611.98
Al Mostathmreen GIS Substation | 29sd elmostsmrin |  | Al Mostathmreen GIS Substation | 30622.5 | 22813.76 | 4593.38 | 27407.14
Mohamed Ali Palace Restoration | MOHAMED ALY-IPC01 | 1 | Mohamed Ali Palace Restoration1 | 36588393.1 | 26154902.9 | 7848900.9 | 34003803.8
Sodic Club House | SODIC CLUB-IPC34 | 34 | Sodic Club House34 | 7360347.44 | 6269587.212 | 797297.45 | 7066884.662
Akhmem Assiut | Inv.7 Assuit Akhmem | 7 | Akhmem Assiut7 | 2346262.04 | 1396025.91 | 351939.31 | 1747965.22
New Heliopolis | Inv.5 Heliopolis | 5 | New Heliopolis5 | 5941573.01 | 4747493.5 | 583462.5 | 5330956
Akhmem - Qena | Inv. 4 Akhmem Qena | 4 | Akhmem - Qena4 | 66780125.09 | 39734174.42 | 10017018.76 | 49751193.18
New Heliopolis | Inv.4 Heliopolis | 4 | New Heliopolis4 | 3078445.11 | 2458182.91 | 302303.3 | 2760486.21
EMAAR-PKG#53-UPTOWN | 18100062 |  | EMAAR-PKG#53-UPTOWN | 8335628.58 | 6775827.66 | 2812863.86 | 9588691.52
Sodic Club House | sodic culb-ipc36fin | 36 | Sodic Club House36 | 29270095.76 | 10543541.848 | 3624395.8275 | 14167937.6755
Al Mostathmreen GIS Substation | 14sd EURO |  | Al Mostathmreen GIS Substation | 347042.64 | 251605.91 | 52056.4 | 303662.31
Assuit PP (CP-118) | 220721005 |  | Assuit PP (CP-118) | 287213.19 | 256337.7795 | 45236.07 | 301573.8495
Assuit PP (CP-118) | 2110210007 |  | Assuit PP (CP-118) | 1073141.24 | 1126798.3 | 0 | 1126798.3
Assuit PP (CP-118) | 2105210005 |  | Assuit PP (CP-118) | 8792.516 | 9255.28 | 0 | 9255.28
Assuit PP (CP-118) | 2006210003 |  | Assuit PP (CP-118) | 391200 | 349146 | 61614 | 410760
Assuit PP (CP-118) | 510 |  | Assuit PP (CP-118) | 537594.53 | 479803.12 | 84671.14 | 564474.26
Assuit PP (CP-118) | 509 |  | Assuit PP (CP-118) | 309532.08 | 276257.38 | 48751.3 | 325008.68
Assuit PP (CP-118) | 1903210004 |  | Assuit PP (CP-118) | 162829.8 | 145325.6 | 25645.69 | 170971.29
Assuit PP (CP-118) | 2110210001 |  | Assuit PP (CP-118) | 21435135.47 | 22292540.89 | 0 | 22292540.89
Assuit PP (CP-118) | 2108210005 |  | Assuit PP (CP-118) | 1095754.59 | 957141.63 | 172581.35 | 1129722.98
Assuit PP (CP-118) | 2105210001 |  | Assuit PP (CP-118) | 1666445.9 | 1754153.58 | 0 | 1754153.58
Assuit PP (CP-118) | 2101210001 |  | Assuit PP (CP-118) | 4812655.59 | 4247168.46 | 757993.25 | 5005161.71
Assuit PP (CP-118) | 2107210001 |  | Assuit PP (CP-118) | 202587.46 | 542427.93 | 95722.56 | 212716.83
Assuit PP (CP-118) | 1905210004 |  | Assuit PP (CP-118) | 1630074.72 | 1385563.51 | 244511.21 | 1630074.72
South Helwan PP (CP-117) | 180015 |  | South Helwan PP (CP-117) | 366814.29 | 327997.56 | 57881.92 | 385879.48
South Helwan PP (CP-117) | Dr-Memo-Inv#18+20EGP | 18 | South Helwan PP (CP-117)18 | 45606.6 | 45606.6 | 0 | 45606.6
W Dam PP Phase II (CP-117) | 180095 |  | W Dam PP Phase II (CP-117) | 108597.48 | 97105.56 | 17136.28 | 114241.84
Marsa Matrouh 500KV | Inv.66 Borg Alarab | 66 | Marsa Matrouh 500KV66 | 7809555.43 | 5272170.77 | 820003.32 | 6092174.09
Marsa Matrouh 500KV | Inv.58 Borg Alarab | 58 | Marsa Matrouh 500KV58 | 255947.73 | 223572.84 | 26874.51 | 250447.35
Marsa Matrouh 500KV | Inv.57 Borg Alarab | 57 | Marsa Matrouh 500KV57 | 2458523.81 | 2147519.25 | 258145 | 2405664.25
Marsa Matrouh 500KV | Inv.42 Borg Alarab | 42 | Marsa Matrouh 500KV42 | 15403211.29 | 13454709.96 | 1617337.19 | 15072047.15
Marsa Matrouh 500KV | Inv.39 Borg Alarab | 39 | Marsa Matrouh 500KV39 | 12222654.28 | 10676488.4 | 1283378.7 | 11959867.1
Marsa Matrouh 500KV | Inv.26 Borg Alarab | 26 | Marsa Matrouh 500KV26 | 655957.14 | 572981.18 | 68875.5 | 641856.68
Marsa Matrouh 500KV | Inv.19 Borg Alarab | 19 | Marsa Matrouh 500KV19 | 3554680.69 | 3105013.7 | 373241.47 | 3478255.17
Marsa Matrouh 500KV | Inv.21Usd borg alarb | 21 | Marsa Matrouh 500KV21 | 65358.6 | 56633.6324 | 6862.65 | 63496.2824
Marsa Matrouh 500KV | Inv.9 Borg Alarab | 9 | Marsa Matrouh 500KV9 | 2843745.9 | 2484012.76 | 298593.32 | 2782606.08
Marsa Matrouh 500KV | Inv. 4 Borg Alarab | 4 | Marsa Matrouh 500KV4 | 10378117.8 | 9065289.96 | 1089702.37 | 10154992.33
Marsa Matrouh 500KV | Inv. 3 Borg Alarab | 3 | Marsa Matrouh 500KV3 | 10523603.44 | 9192367.02 | 1104978.36 | 10297345.38
Marsa Matrouh 500KV | Inv. 3 usd Borg Arab | 3 | Marsa Matrouh 500KV3 | 5305066.97 | 4620578.82 | 557032.03 | 5177610.85
Royal City | (1) royal city |  | Royal City | 3731890 | 5236267.51 | 994216.1 | 6230483.61
Akhmem Assiut | Inv.10 Assuit Akhmem | 10 | Akhmem Assiut10 | 3120723.9883 | 2460471.64 | 464239.93 | 2978872.8967
Siemens 6x500/220 KV GIS-MOU | Inv 78 P11 Assuit | 78 | Siemens 6x500/220 KV GIS-MOU78 | 1986409.19 | 1436968.4 | 297961.38 | 1734929.78
K047 FDH JV | Inv. No.13 KWD Floor | 13 | K047 FDH JV13 | 62138.64 | 55924.78 | 0 | 55924.78
Akhmem - Qena | Inv.11 Qena - Akhmem | 11 | Akhmem - Qena11 | 29704926.34 | 17674431.18 | 4455738.95 | 22130170.13
Akhmem - Qena | Inv.10 Qena - Akhmem | 10 | Akhmem - Qena10 | 13530422.5 | 10756685.89 | 2029563.38 | 12786249.27
MAYSAN 400/132kV SS | 201 |  | MAYSAN 400/132kV SS | 4798431.61 | 0 | 0 | 0
MOTHANA 400/132kV SS | 200 |  | MOTHANA 400/132kV SS | 4216144.83 | 0 | 0 | 0
Kayan 3 New Cairo Capital City | KAYAN FINSHING-IPC 4 | 4 | Kayan 3 New Cairo Capital City4 | 35496295 | 11062482.8 | 21150000 | 32212482.8
SHAT Al ARAB 400/132kV SS | 212 |  | SHAT Al ARAB 400/132kV SS | 5361669.87 | 5361669.87 | 0 | 5361669.87
Al Mostathmreen GIS Substation | 10 sd euro mostsmrin |  | Al Mostathmreen GIS Substation | 173242.08 | 125600.51 | 25986.31 | 151586.82
Cairo Capital S1 | Cr. 1% |  | Cairo Capital S1 | 0 | 0 | 0 | 0
Cairo Capital S1 | Final Credit |  | Cairo Capital S1 | 0 | 0 | -12387804.45 | -12387804.45
Tamey El-amdeed Substation | 18100063 |  | Tamey El-amdeed Substation | 3295440.04 | 2454573.85 | 494316.01 | 2948889.86
Beni Suef Substation R61 | 18100065 |  | Beni Suef Substation R61 | 2992524 | 2242929.38 | 448878.6 | 2691807.98
Ministries Buildings | MinisAlocation IPC08 | 8 | Ministries Buildings8 | 19178923.72 | 653919.99 | 15653924.9 | 16307844.89
EMAAR-PKG117- MARASSI | (1) pkg#117 |  | EMAAR-PKG117- MARASSI | 7803090.39 | 6865083.2495 | 819324.49 | 7684407.7395
New Giza 2 | NEW GIZA2- IPC 26 | 26 | New Giza 226 | 5057706.62 | 3584772.179 | 835258.8 | 4420030.979
Attaqa Power Plant | remaining Inv. 1 USD | 1 | Attaqa Power Plant1 | 67573333.34 | 67573333.34 | 0 | 67573333.34
Abo Quir - Badr 500KV | Ret.Part1 EGP |  | Abo Quir - Badr 500KV | 6253944.58 | 175120.05 | 0 | 175120.05
EMAAR-PKG117- MARASSI | 18100050 |  | EMAAR-PKG117- MARASSI | 4131277.05 | 3977930.2825 | 473909.65 | 4451839.9325
Akhmem Assiut | Inv.3 Assuit Akhmem$ | 3 | Akhmem Assiut3 | 5148236.69 | 4320494.29 | 0 | 4320494.29
Akhmem - Qena | Inv.6 Qena - Akhmem$ | 6 | Akhmem - Qena6 | 3012460.29 | 2558181.18 | 0 | 2558181.18
Akhmem - Qena | Inv.1 Qena - Akhmem$ | 1 | Akhmem - Qena1 | 2270390.51 | 1604817.44 | 0 | 1604817.44
Akhmem Assiut | Inv.13 Assuit Akhmem | 13 | Akhmem Assiut13 | 9813635.49 | 7801840.21 | 1472045.32 | 9273885.53
Akhmem Assiut | Inv.16 Assuit Akhmem | 16 | Akhmem Assiut16 | 3219311.35 | 2559352.52 | 482896.7 | 3042249.22
Akhmem Assiut | Inv.11 Assuit Akhmem | 11 | Akhmem Assiut11 | 66793963.3314 | 39460547.12 | 9948037.09 | 52298252.1286
Suez Gulf Substation | 180054 |  | Suez Gulf Substation | 5090.42 | 4819.5 | 535.5 | 5355
Substation Elco Steel | PSP ELCO-IPC 02 | 2 | Substation Elco Steel2 | 1669926.8 | 1160599.13 | 333985.36 | 1494584.49
Sodic Club House | IPC31-SODIC CLUB | 31 | Sodic Club House31 | 2806299.13 | 6752933.2165 | 603924.4 | 7356857.6165
EMAAR-PKG#107-MARASSI | 18100061 |  | EMAAR-PKG#107-MARASSI | 3636142.56 | 4202126.67 | 0 | 4202126.67
Akhmem - Qena | Inv.25 Akhmem Qena | 25 | Akhmem - Qena25 | 8788664.36 | 6252137.1 | 1318299.66 | 7570436.76
Akhmem - Qena | Inv.22 Akhmem Qena | 22 | Akhmem - Qena22 | 10941173.49 | 6509998.21 | 1641176.03 | 8151174.24
Akhmem - Qena | Inv.30 Akhmem Qena | 30 | Akhmem - Qena30 | 5411732.1 | 2678807.41 | 811759.83 | 3490567.24
Mohamed Ali Palace Restoration | Mohamed Aly - IPC04 | 4 | Mohamed Ali Palace Restoration4 | 7637765.43 | 3597182.7 | 3105457.05 | 6702639.75
EL-Hegaz Square Bridge | ELHEGAZ-IPC FINAL |  | EL-Hegaz Square Bridge | 5915483.87 | 0 | 16091824.758 | 17047344.758
New bridge Ismailiya Nefisha | NFISHA BRIDGE-IPC01 | 1 | New bridge Ismailiya Nefisha1 | 51811685.08 | 12381198.65 | 3000000 | 42498928.65
Beni Suef Substation R61 | 18100067 |  | Beni Suef Substation R61 | 1837500 | 1368937.5 | 275625 | 1644562.5
Beni Suef Substation R61 | 18100066 |  | Beni Suef Substation R61 | 558884.47 | 405191.24 | 83832.67 | 489023.91
Akhmem - Qena | Inv.2 Qena - Akhmem$ | 2 | Akhmem - Qena2 | 200830.69 | 169676.91 | 0 | 169676.91
Akhmem - Qena | Inv.20 Qena- Akhmem$ | 20 | Akhmem - Qena20 | 1517387.42 | 1282168.99 | 0 | 1282168.99
Akhmem - Qena | Inv.37 Akhmem Qena | 37 | Akhmem - Qena37 | 8568.16 | 5954.86 | 1285.22 | 7240.08
Akhmem Assiut | Inv.28 Assuit Akhmem | 28 | Akhmem Assiut28 | 15695290.1 | 12477755.62 | 2354293.52 | 14832049.14
P-28-16 Balat Owinat Lot 3 | Inv. 12 Balat lot 3 | 12 | P-28-16 Balat Owinat Lot 312 | 3737851.54 | 2791779.12 | 392474.41 | 3184253.53
P-28-16 Balat Owinat Lot 3 | Inv. 7 Balat lot 3 | 7 | P-28-16 Balat Owinat Lot 37 | 2058983.71 | 1537666.88 | 216193.29 | 1753860.17
P-28-16 Balat Owinat Lot 3 | Inv. 5 Balat lot 3 | 5 | P-28-16 Balat Owinat Lot 35 | 8978757.19 | 6706735.64 | 942769.51 | 7649505.15
P-28-16 Balat Owinat Lot 3 | Inv. 1 Balat lot 3 | 1 | P-28-16 Balat Owinat Lot 31 | 11498554.02 | 8589022.06 | 1207348.17 | 9796370.23
Elsewedy Univ - Enabling Works | 19100032 |  | Elsewedy Univ - Enabling Works | 205504.2 | 142702.12 | 64733.82 | 207435.94
Elsewedy Univ - Enabling Works | ELSEWEDY UNY-IPC03 | 3 | Elsewedy Univ - Enabling Works3 | 1749696.33 | 1214989.1265 | 551154.35 | 1766143.4765
Elsewedy Univ - Enabling Works | ELSWEDY-UN-MEP-IPC02 | 2 | Elsewedy Univ - Enabling Works2 | 4165158.06 | 3110956.553 | 874683.19 | 3985639.743
Elsewedy Univ - Enabling Works | EL SEWEDY UNI-IPC-02 | 2 | Elsewedy Univ - Enabling Works2 | 2762087.04 | 1917993.242 | 870057.42 | 2788050.662
NUCA R05 - Z02 | R5-IPC27 | 27 | NUCA R05 - Z0227 | 12195893.27 | 8400109.47 | 1073714.35 | 9473823.82
NUCA R05 - Z02 | R5 - IPC20 | 20 | NUCA R05 - Z0220 | 40939275.15 | 33414942.65 | 4099408.55 | 37514351.2
NUCA R05 - Z02 | R5 - IPC 19 | 19 | NUCA R05 - Z0219 | 86399294.85 | 66398297.5 | 8301205.5 | 74699503
NUCA R05 - Z02 | R5 - IPC14 | 14 | NUCA R05 - Z0214 | 48665536.25 | 37605923.5 | 4699561.65 | 42305485.15
NUCA R05 - Z02 | R5-IPC013 | 13 | NUCA R05 - Z0213 | 35089427.4 | 21697982.73 | 2763742.75 | 24461725.48
NUCA R05 - Z02 | R5 - IPC11 | 11 | NUCA R05 - Z0211 | 35072197.95 | 29923408.95 | 3712337.3 | 33635746.25
R5 Mix-Use Complex Project | R5 ZONE1- IPC05 | 5 | R5 Mix-Use Complex Project5 | 12663442.81 | 10925527.29 | 1338513.24 | 12264040.53
R5 Mix-Use Complex Project | R5-ZONE1-IPC 01 | 1 | R5 Mix-Use Complex Project1 | 18101215.9 | 17393287.24 | 2144069.05 | 19537356.29
South Helwan PP (CP-117) | South Helwan inv.ded |  | South Helwan PP (CP-117) | 0 | -5827.6 | 0 | -5827.6
South Helwan PP (CP-117) | 180134 |  | South Helwan PP (CP-117) | 357494.32 | 386131.21 | 0 | 386131.21
Royal City | ROYAL CITY -IPC 10 | 10 | Royal City10 | 7808914.21 | 5842887.9205 | 1102431.68 | 6945319.6005
Mohamed Ali Palace Restoration | PO - Mohamed Aly 107 |  | Mohamed Ali Palace Restoration | 486912.65 | 345055 | 115022.3 | 460077.3
Ministries Buildings | MIN-FIT OUT-IPC04 | 4 | Ministries Buildings4 | 3272449.8 | 877175 | 1920769.33 | 2797944.33
Akhmem Assiut | Inv.19 Assuit Akhmem | 19 | Akhmem Assiut19 | 31146513.1 | 18532175.28 | 4671976.97 | 23204152.25
Akhmem Assiut | Inv.18 Assuit Akhmem | 18 | Akhmem Assiut18 | 10588594.32 | 8417932.49 | 1588289.15 | 10006221.64
Akhmem - Qena | Inv.20 Qena - Akhmem | 20 | Akhmem - Qena20 | 8032650.24 | 6385956.94 | 1204897.54 | 7590854.48
Beni Seuf - 358 | Inv.5 Beni Souf 358 | 5 | Beni Seuf - 3585 | 6081377.46 | 4834166.15 | 912206.65 | 5746372.8
Ministries Buildings | MINISTIRY-IPC 1 | 1 | Ministries Buildings1 | 509004396 | 54035277 | 171000000 | 456293797
New Heliopolis | Inv.8. Heliopolis | 8 | New Heliopolis8 | 11772146.9 | 9407047.7 | 1156024.85 | 10563072.55
Akhmem Assiut | Inv.16Assuit Akhmem$ | 16 | Akhmem Assiut16 | 1844140.24 | 1564199.11 | 0 | 1564199.11
Beni Suef COMCAVI | 180117 |  | Beni Suef COMCAVI | 1692.37 | 1692.36 | 0.01 | 1692.37
Marsa Matrouh 500KV | Inv.4 Usd borg alarb | 4 | Marsa Matrouh 500KV4 | 1278838.88 | 1116174 | 134278.08 | 1250452.08
Canal Regional Control Center | Inv.9 Rcc | 9 | Canal Regional Control Center9 | 7592326.84 | 4600900.6 | 1594388.64 | 6195289.24
Marsa Matrouh 500KV | Inv.6 Usd borg alarb | 6 | Marsa Matrouh 500KV6 | 1278838.88 | 1111185.2753 | 134278.08 | 1245463.3553
Marsa Matrouh 500KV | Inv.7 Usd borg alarb | 7 | Marsa Matrouh 500KV7 | 1053161.82 | 919198.7435 | 110581.99 | 1029780.7335
P-28-16 Balat Owinat Lot 2 | Inv. 16 Balat Lot 2 | 16 | P-28-16 Balat Owinat Lot 216 | 6149117.66 | 866294.3 | 3747170.08 | 4613464.38
P-28-16 Balat Owinat Lot 2 | Inv. 14 Balat Lot 2 | 14 | P-28-16 Balat Owinat Lot 214 | 17486066.67 | 11313091.93 | 1836036.996 | 13149128.926
Sodic Club House | SODIC CLUB-IPC-33 | 33 | Sodic Club House33 | 6742632.54 | 5855002.737 | 1015115.8 | 6870118.537
El Boghaz Brigde | 10004 |  | El Boghaz Brigde | 2960083.5 | 2960083.5 | 0 | 2960083.5
P-28-16 Balat Owinat Lot 2 | Inv. 2 Balat Lot 2 | 2 | P-28-16 Balat Owinat Lot 22 | 3984852.38 | 2996213.88 | 418409.5 | 3414623.38
Akhmem - Qena | ints 20%Q3-11-22-41ض | 11 | Akhmem - Qena11 | 7885398.68 | 7884869.77 | 0 | 7884869.77
Akhmem - Qena | Inv.38 Akhmem Qena | 38 | Akhmem - Qena38 | 386676.68 | 268740.28 | 58001.5 | 326741.78
Akhmem - Qena | Inv.19 Qena- Akhmem$ | 19 | Akhmem - Qena19 | 1066345.9 | 902025.21 | 0 | 902025.21
Akhmem - Qena | Inv.18 Qena- Akhmem$ | 18 | Akhmem - Qena18 | 2075250.42 | 1744206.53 | 0 | 1744206.53
Akhmem - Qena | Inv.17 Qena- Akhmem$ | 17 | Akhmem - Qena17 | 145713.66 | 117272.46 | 0 | 117272.46
Akhmem - Qena | Inv.4 Qena - Akhmem$ | 4 | Akhmem - Qena4 | 3029589.88 | 2550157.16 | 0 | 2550157.16
W Dam PP Phase II (CP-117) | 180146 |  | W Dam PP Phase II (CP-117) | 2642.57 | 2362.93 | 416.99 | 2779.92
PIP- Zonafranca | Sett. Inv. Zona |  | PIP- Zonafranca | 16936102.15 | 13174716.3368 | 0 | 13174716.3368
Akhmem Assiut | Soci.29:33EGP Assuit |  | Akhmem Assiut | 820565.8 | 820565.8 | 0 | 820565.8
Akhmem Assiut | Inv.19Assuit Akhmem$ | 19 | Akhmem Assiut19 | 695510.92 | 587529.12 | 0 | 587529.12
Akhmem Assiut | Inv.4 Assuit Akhmem$ | 4 | Akhmem Assiut4 | 2023.28 | 1198.45 | 0 | 1198.45
Substation Elco Steel | PSP ELCO-IPC04 | 4 | Substation Elco Steel4 | 1838590.86 | 1268627.7 | 367718.17 | 1636345.87
NUCA R05 - Z02 | R05 - IPC028 | 28 | NUCA R05 - Z0228 | 1730474.75 | 1265141.05 | 160837.5 | 1425978.55
Akhmem Assiut | Inv.43 Assuit Akhmem | 43 | Akhmem Assiut43 | 1314333.18 | 985138.27 | 197149.98 | 1182288.25
Tamey El-amdeed Substation | (1) CW .TAM |  | Tamey El-amdeed Substation | 7657332.77 | 5704712.91 | 1148599.92 | 6853312.83
AWEER POWER STATION 'H' Phase | LOC/025 |  | AWEER POWER STATION 'H' Phase | 612800.38 | 537902.55 | 68088.93 | 605991.48
AWEER POWER STATION 'H' Phase | IMP/070 |  | AWEER POWER STATION 'H' Phase | 72124.99 | 47782.7993 | 18031.25 | 65814.0493
AWEER POWER STATION 'H' Phase | LOC/020 |  | AWEER POWER STATION 'H' Phase | 288571.16 | 253301.3498 | 32063.46 | 285364.8098
AWEER POWER STATION 'H' Phase | LOC/021 |  | AWEER POWER STATION 'H' Phase | 2202248.84 | 1933085.09 | 244694.32 | 2177779.41
AWEER POWER STATION 'H' Phase | IMP/065 |  | AWEER POWER STATION 'H' Phase | 597697.12 | 395974.3394 | 149424.28 | 545398.6194
AWEER POWER STATION 'H' Phase | CON/023 |  | AWEER POWER STATION 'H' Phase | 425899.55 | 373845.1575 | 47322.17 | 421167.3275
AWEER POWER STATION 'H' Phase | CON/018 |  | AWEER POWER STATION 'H' Phase | 10221589.19 | 10108015.972 | 0 | 10108015.972
AWEER POWER STATION 'H' Phase | 10408 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
AWEER POWER STATION 'H' Phase | 10407 |  | AWEER POWER STATION 'H' Phase | 958273.98 | 841151.609 | 106474.89 | 947626.499
AWEER POWER STATION 'H' Phase | 10327 |  | AWEER POWER STATION 'H' Phase | 2591086.05 | 2274397.7525 | 287898.45 | 2562296.2025
AWEER POWER STATION 'H' Phase | 10328 |  | AWEER POWER STATION 'H' Phase | 2141093.13 | 1879403.9665 | 237899.24 | 2117303.2065
AWEER POWER STATION 'H' Phase | 10287 |  | AWEER POWER STATION 'H' Phase | 4321381.71 | 1272406.83 | 3000959.5238 | 4273366.3538
AWEER POWER STATION 'H' Phase | 10172 |  | AWEER POWER STATION 'H' Phase | 31169386.77 | 30823060.2485 | 0 | 30823060.2485
P-28-16 Balat Owinat Lot 3 | Inv. 3 Balat lot 3 | 3 | P-28-16 Balat Owinat Lot 33 | 16666140.62 | 12449214.67 | 1749944.77 | 14199159.44
P-28-16 Balat Owinat Lot 2 | Inv. 3 Balat Lot 2 | 3 | P-28-16 Balat Owinat Lot 23 | 138801.49 | 103289.16 | 14574.16 | 117863.32
El Boghaz Brigde | IPC#16 | 16 | El Boghaz Brigde16 | 2447010 | 2250939.4 | 0 | 2250939.4
EDNC Retail & Offices Civil | Sodic Soreal IPC028 | 28 | EDNC Retail & Offices Civil28 | 37125243.76 | 26708616.218 | 111564.97 | 26820181.188
EDNC Retail & Offices Civil | SOREAL-IPC20 | 20 | EDNC Retail & Offices Civil20 | 45598330.5 | 31197031.845 | 3213756.88 | 34410788.725
EDNC Retail & Offices Civil | SOREAL-IPC19 | 19 | EDNC Retail & Offices Civil19 | 45752255.09 | 30462891.204 | 2757896.6 | 33220787.804
EDNC Retail & Offices Civil | SOREAL-IPC05 | 5 | EDNC Retail & Offices Civil5 | 50370296.9 | 37056568.405 | 11141101.87 | 48197670.275
EDNC Retail & Offices Civil | SOREAL-IPC03 | 3 | EDNC Retail & Offices Civil3 | 2101069.44 | 1574016.182 | 441224.58 | 2015240.762
Abou El Matameer and Sammanoud | Social 13 Matamir |  | Abou El Matameer and Sammanoud | 43758.1 | 43758.08 | 0 | 43758.08
Marsa Matrouh 500KV | Inv.14Usd borg alarb | 14 | Marsa Matrouh 500KV14 | 543102.44 | 472678.5791 | 57025.76 | 529704.3391
Beni Suef Substation R61 | BSF-CW-10 | 10 | Beni Suef Substation R6110 | 1355795 | 1010067.27 | 203369.25 | 1213436.52
Beni Suef Substation R61 | BSF-CW-EUR-03 | 3 | Beni Suef Substation R613 | 1571844.23 | 1171023.96 | 235776.63 | 1406800.59
New Capital Tunnels | M.B.Z TUNNLE-IPC5 | 5 | New Capital Tunnels5 | 14354311.59 | 6080870.45 | 6080874 | 12954361.45
EMAAR-PKG# 101-UPTOWN | PKG#101 -IPC04 | 4 | EMAAR-PKG# 101-UPTOWN4 | 1896917.55 | 2246109.51 | 1168966.28 | 3415075.79
Mall Of Egypt | MALL EGYPT-FINAL 2 |  | Mall Of Egypt | 22665950.54 | 27653663.75 | 0 | 27653663.75
Tamey El-amdeed Substation | TAM-CW-EGP-09 | 9 | Tamey El-amdeed Substation9 | 2847217.55 | 2106940.99 | 427082.63 | 2534023.62
EMAAR-PKG#62-UPTOWN | PKG#62-IPC-15 | 15 | EMAAR-PKG#62-UPTOWN15 | 1329599.07 | 5710409.5735 | 0 | 5710409.5735
Abou El Matameer and Sammanoud | Social 14 Matamir |  | Abou El Matameer and Sammanoud | 78199.75 | 78199.75 | 0 | 78199.75
Asec Spare-Parts | Inv 1 EUR Asec Spare | 1 | Asec Spare-Parts1 | 332173.8 | 0 | 373175.87 | 373175.87
DPW Onshore Port & Terminal | DP WORLD-IPC04 | 4 | DPW Onshore Port & Terminal4 | 20754393.51 | 15357944.03 | 3113159.03 | 18471103.06
DPW Onshore Port & Terminal | DP WORLD -IPC02 | 2 | DPW Onshore Port & Terminal2 | 24408793.92 | 18062199.23 | 3661319.09 | 21723518.32
DPW Onshore Port & Terminal | DPW IPC34 | 34 | DPW Onshore Port & Terminal34 | 12548237.84 | 8899770.35 | 2268161.33 | 11167931.68
DPW Onshore Port & Terminal | DP WORLD-IPC25 | 25 | DPW Onshore Port & Terminal25 | 13937299.51 | 10313601.63 | 2090594.93 | 12404196.56
DPW Onshore Port & Terminal | DP WORLD-IPC19 | 19 | DPW Onshore Port & Terminal19 | 34366362.95 | 25431108.58 | 5154954.44 | 30586063.02
DPW Onshore Port & Terminal | DP WORLD -IPC18 | 18 | DPW Onshore Port & Terminal18 | 59878397.73 | 44310014.32 | 8981759.66 | 53291773.98
C5 Bridge 2 New Alamein | IPC# 1 | 1 | C5 Bridge 2 New Alamein1 | 1571000 | 1523870 | 0 | 1523870
Akhmem - Qena | Inv.45 Qena Akhmem | 45 | Akhmem - Qena45 | 10746993.68 | 7401028.2 | 1612049.05 | 9013077.25
Assuit PP (CP-118) | 180164 |  | Assuit PP (CP-118) | 125735.38 | 112218.83 | 19803.32 | 132022.15
Marsa Matrouh 500KV | Inv.10 Borg Alarab | 10 | Marsa Matrouh 500KV10 | 58454700.72 | 50858223.23 | 6137743.58 | 56995966.81
Marsa Matrouh 500KV | Inv.7 Borg Alarab | 7 | Marsa Matrouh 500KV7 | 3453119.23 | 3016303.72 | 362577.52 | 3378881.24
Manshiet Nasser Substation | 180173 |  | Manshiet Nasser Substation | 949135.31 | 996592.08 | 0 | 996592.08
Zafranaa - Ras Ghareb | Advance invoice due |  | Zafranaa - Ras Ghareb | 376090.02 | 50000 | 0 | 58034.1
Elsewedy Univ - Enabling Works | UNI FI&MEP -IPC06 | 6 | Elsewedy Univ - Enabling Works6 | 33456554.93 | 19684684.46 | 7876979.84 | 27561664.3
Elsewedy Univ - Enabling Works | SEWEDY UNI MEP-IPC06 | 6 | Elsewedy Univ - Enabling Works6 | 8105230.79 | 7457796.8695 | 1702098.47 | 9159895.3395
Al Mostathmreen GIS Substation | MOS-SD-EGP-28 | 28 | Al Mostathmreen GIS Substation28 | 10207.5 | 3205336.71 | 1531.13 | 3206867.84
Tamey El-amdeed Substation | 19100028 |  | Tamey El-amdeed Substation | 1605178.4 | 1187832.02 | 240776.76 | 1428608.78
Akhmem Assiut | Inv.6 Assuit Akhmem | 6 | Akhmem Assiut6 | 2453962.67 | 1460107.79 | 368094.4 | 1828202.19
Akhmem Assiut | Inv.35 Assuit Akhmem | 35 | Akhmem Assiut35 | 18483513.92 | 10997161.89 | 2772527.09 | 13769688.98
Kuwait | Civil/H011 |  | Kuwait | 33876.01 | 25407.01 | 0 | 25407.01
Akhmem - Qena | Ref. Insral 1 $ Qena |  | Akhmem - Qena | 1801758.09 | 1762008 | 0 | 1762008
kayan wall lock & Load | 19100016 |  | kayan wall lock & Load | 11712600 | 10570220.8 | 0 | 10570220.8
EMAAR-PKG#53-UPTOWN | 19100046 |  | EMAAR-PKG#53-UPTOWN | 1320000 | 1156584 | 0 | 1156584
Abu Sultan Road Extension | Abu soultan -ipc 1 | 1 | Abu Sultan Road Extension1 | 17732625.58 | 1785123.35 | 1721657.85 | 14787256.2
P-28-16 Balat Owinat Lot 2 | Inv. 5 Balat Lot 2 | 5 | P-28-16 Balat Owinat Lot 25 | 13925519.05 | 10401964.62 | 1462179.5 | 11864144.12
Akhmem - Qena | Inv.26 Qena- Akhmem$ | 26 | Akhmem - Qena26 | 344866.84 | 282634.2165 | 0 | 282634.2165
Flour project | 10049 |  | Flour project | 227629.106 | 227629.106 | 0 | 227629.106
RME-Abu Sultan Bridge | IPC#3 | 3 | RME-Abu Sultan Bridge3 | 1149500 | 1138005 | 0 | 1138005
RME-Abu Sultan Bridge | Final Invice |  | RME-Abu Sultan Bridge | 756050 | 736639.5 | 0 | 736639.5
kayan wall lock & Load | KAYAN RADM2-IPC01 | 1 | kayan wall lock & Load1 | 4000000 | 2503435 | 1001140 | 3504575
Development of Mahmudiyah axis | FPC |  | Development of Mahmudiyah axis | 900000 | 859800 | 0 | 859800
Substation Elco Steel | PSP-ELCO-IPC07 | 7 | Substation Elco Steel7 | 3187107.5 | 2228843.15 | 607682.54 | 2836525.69
Substation Elco Steel | PSP-ELCO-IPC 06 | 6 | Substation Elco Steel6 | 3766431.24 | 2598837.56 | 753286.25 | 3352123.81
P-28-16 Balat Owinat Lot 3 | Inv. 6 Balat lot 3 | 6 | P-28-16 Balat Owinat Lot 36 | 36165596.5 | 27015303.16 | 3797387.63 | 30812690.79
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC12 | 12 | EMAAR- Pkg 140-ITP-Mivida12 | 1875812.84 | 4687303.232 | 599801.18 | 5287104.412
EMAAR- Pkg 140-ITP-Mivida | PKG#140 -IPC08 | 8 | EMAAR- Pkg 140-ITP-Mivida8 | 6113446.74 | 5253107.1475 | 607173.66 | 5860280.8075
HAC CCC JV | IPC#9 | 9 | HAC CCC JV9 | 2004324 | 1847986.73 | 0 | 1847986.73
Kayan 3 New Cairo Capital City | EL KAYAN-IPC FINAL |  | Kayan 3 New Cairo Capital City | 179948517.95 | 74379903.95 | 0 | 161801582.45
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC 07 | 7 | Elsewedy Univ - Enabling Works7 | 410253.12 | 284879.766 | 129229.73 | 414109.496
Beni Suef Substation R61 | 19100024 |  | Beni Suef Substation R61 | 1589921 | 1176541.54 | 238488.15 | 1415029.69
Tamey El-amdeed Substation | TAM-CW-EURO-04 | 4 | Tamey El-amdeed Substation4 | 1899677.92 | 1405761.66 | 284951.69 | 1690713.35
Manshiet Nasser Substation | 2008210010 |  | Manshiet Nasser Substation | 3197756.28 | 0 | 479663.44 | 479663.44
Manshiet Nasser Substation | 2002210022 |  | Manshiet Nasser Substation | 3847.66 | 827.55 | 577.15 | 1404.7
Manshiet Nasser Substation | 2001210019 |  | Manshiet Nasser Substation | 157776.72 | 118565.85 | 25393.99 | 143959.84
Manshiet Nasser Substation | 1901210017 |  | Manshiet Nasser Substation | 5428.57 | 5089.96 | 555.75 | 5645.71
Manshiet Nasser Substation | 1908210019 |  | Manshiet Nasser Substation | 22917.97 | 18170.76 | 3437.7 | 21608.46
El Mostakbal City Project | Inv. 2 Mostakbal | 2 | El Mostakbal City Project2 | 10792497.87 | 8956071.67 | 2266424.55 | 11222496.22
Akhmem Assiut | Inv.36 Assuit Akhmem | 36 | Akhmem Assiut36 | 2816945.25 | 1676082.41 | 422541.79 | 2098624.2
Akhmem Assiut | Inv.32 Assuit Akhmem | 32 | Akhmem Assiut32 | 6237116.6 | 4958507.69 | 935567.49 | 5894075.18
Akhmem Assiut | Inv.26 Assuit Akhmem | 26 | Akhmem Assiut26 | 8568.16 | 6811.68 | 1285.22 | 8096.9
Akhmem Assiut | Inv.17 Assuit Akhmem | 17 | Akhmem Assiut17 | 25765250.1 | 15330323.81 | 3864787.52 | 19195111.33
New Capital | Inv. 6 Eltbeen | 6 | New Capital6 | 519950.32 | 377465.49 | 54594.78 | 432060.27
EMAAR-PKG# 144, Marassi | PKG#144 - IPC07 | 7 | EMAAR-PKG# 144, Marassi7 | 20465525.62 | 12627238.511 | 6479678.86 | 19106917.371
EMAAR-PKG# 144, Marassi | PKG#144 - IPC8 | 8 | EMAAR-PKG# 144, Marassi8 | 16360599.32 | 8934848.896 | 3164355.69 | 12099204.586
New Capital | Inv. 9 Abo Zabal | 9 | New Capital9 | 1629223.77 | 1182729.97 | 171068.5 | 1353798.47
Elsewedy Univ - Enabling Works | UNI -FIN&MEP-IPC02 | 2 | Elsewedy Univ - Enabling Works2 | 1535126.31 | 3185421.0755 | 0 | 3185421.0755
P-28-16 Balat Owinat Lot 2 | Inv. 7 Balat Lot 2 | 7 | P-28-16 Balat Owinat Lot 27 | 32063076.51 | 23950725.04 | 3366623.03 | 27317348.07
Mauritania-Lot 2 | Inv.7 – Lot 2 | 7 | Mauritania-Lot 27 | 268557.09 | 255129.24 | 0 | 255129.24
Mauritania Lot 1 | Inv.7 - Lot 1 | 7 | Mauritania Lot 17 | 1773715.17 | 1684999.41 | 0 | 1684999.41
Substation Elco Steel | PSP ELCO-IPC-08 | 8 | Substation Elco Steel8 | 2651758.28 | 1829713.22 | 530351.66 | 2360064.88
El Boghaz Brigde | IPC#18 | 18 | El Boghaz Brigde18 | 1141351.02 | 1072869.96 | 0 | 1072869.96
Cameron EDC | 007/2018 |  | Cameron EDC | 867905.03 | 867070.07 | 0 | 867070.07
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC09 | 9 | Elsewedy Univ - Enabling Works9 | 104806.23 | 258721.9915 | 33013.96 | 291735.9515
Air Defense College | air defense(2) ipc01 | 1 | Air Defense College1 | 50231345.82 | 13182605 | 5900000 | 41477425
Alamein Coastal Road Bridge | Alamein bridge ipc01 | 1 | Alamein Coastal Road Bridge1 | 227857516.19 | 40221875 | 46800000 | 213711604.9995
Kayan 3 New Cairo Capital City | KAYAN SAHY-IPC03 | 3 | Kayan 3 New Cairo Capital City3 | 6042938 | 874466.9 | 5341846.25 | 6216313.15
Ministries Buildings | MIN.ALLOCATION-IPC04 | 4 | Ministries Buildings4 | 22501315.97 | 7703215 | 11478750.3 | 19181965.3
Ministries Buildings | MIN-ELCTROMIK-IPC02 | 2 | Ministries Buildings2 | 184148104 | 101591695 | 55364904 | 156956599
Kayan 3 New Cairo Capital City | KAYAN MEP- IPC5 | 5 | Kayan 3 New Cairo Capital City5 | 19786515 | 18381367.45 | 12079435.45 | 30460802.9
MAYSAN 400/132kV SS | 228 |  | MAYSAN 400/132kV SS | 1126195.85 | 1125384.76 | 0 | 1125384.76
South Helwan PP (CP-117) | 1901210012 |  | South Helwan PP (CP-117) | 241539.51 | 276764.02 | 0 | 276764.02
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC05 | 5 | EMAAR-PKG# 101-UPTOWN5 | 4428897.72 | 2512749.703 | 1301295.53 | 3814045.233
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 20 | 20 | Benban 500 K.V/95 K.M20 | 16047120.51 | 13174693.03 | 1684947.65 | 14859640.68
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 28 | 28 | Benban 500 K.V/95 K.M28 | 83461.1 | 64355.64 | 8763.42 | 73119.06
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 27 | 27 | Benban 500 K.V/95 K.M27 | 2840729.66 | 2190203.14 | 298276.61 | 2488479.75
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 29 | 29 | Benban 500 K.V / 100 K.M29 | 415439.94 | 320311.16 | 43621.19 | 363932.35
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 23 | 23 | Benban 500 K.V / 100 K.M23 | 14580822.99 | 11241224.59 | 1530986.41 | 12772211
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 10 | 10 | Benban 500 K.V / 100 K.M10 | 104470 | 80553.6 | 10969.35 | 91522.95
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 9 | 9 | Benban 500 K.V / 100 K.M9 | 340490.56 | 262525.63 | 35751.51 | 298277.14
Assuit PP (CP-118) | 1903210003 |  | Assuit PP (CP-118) | 284204.9 | 253652.87 | 44762.27 | 298415.14
Cameron EDC | 016/2019 |  | Cameron EDC | 1185.83 | 1126.83 | 0 | 1126.83
Marsa Matrouh 500KV | Inv.16 Borg Alarab | 16 | Marsa Matrouh 500KV16 | 4512426.67 | 3941611.3 | 473804.8 | 4415416.1
EMAAR-PKG117- MARASSI | PKG#117-IPC 6 | 6 | EMAAR-PKG117- MARASSI6 | 6677875.14 | 5722280.397 | 687623.33 | 6409903.727
Canal Sugar OHTL | Inv.02 Sugar OHTL | 2 | Canal Sugar OHTL2 | 18349632 | 14496209.28 | 2752444.8 | 17248654.08
Canal Sugar S/s | Inv 1 Sugar S/s | 1 | Canal Sugar S/s1 | 12212036.75 | 7508017.53 | 3971297.02 | 11479314.55
Marsa Matrouh 500KV | Inv.20 Borg Alarab | 20 | Marsa Matrouh 500KV20 | 4164056.26 | 3637306.65 | 437225.91 | 4074532.56
Attaqa Power Plant | Inv. 2 USD. | 2 | Attaqa Power Plant2 | 117713333 | 117713333 | 0 | 117713333
Akhmem - Qena | Social Inv. 47 Qena | 47 | Akhmem - Qena47 | 29277.5 | 29277.5 | 0 | 29277.5
MAYSAN 400/132kV SS | 221 |  | MAYSAN 400/132kV SS | 859504.74 | 859504.74 | 0 | 859504.74
HAC CCC JV | IPC#12 | 12 | HAC CCC JV12 | 1436628.15 | 1308201.36 | 0 | 1308201.36
EMAAR-PKG# 144, Marassi | PKG#144 - IPC10 | 10 | EMAAR-PKG# 144, Marassi10 | 13884342.32 | 11330349.466 | 1033903.34 | 12364252.806
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 1 | 1 | Benban 500 K.V / 100 K.M1 | 25879088.97 | 19947781.4 | 2717304.34 | 22665085.74
Benban 500 K.V / 100 K.M | Benban Lot1 Inv15USD | 15 | Benban 500 K.V / 100 K.M15 | 96045.76 | 0 | 90763.25 | 90763.25
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 3USD | 3 | Benban 500 K.V / 100 K.M3 | 644227.92 | 541151.46 | 67643.93 | 608795.39
Benban 500 K.V/95 K.M | Benban Lot2 Inv 14 $ | 14 | Benban 500 K.V/95 K.M14 | 6491.31 | 5452.7 | 681.59 | 6134.29
Benban 500 K.V/95 K.M | Benban Lot2 Inv 4 $ | 4 | Benban 500 K.V/95 K.M4 | 206822.3 | 173730.73 | 21716.34 | 195447.07
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC023 | 23 | EMAAR- Pkg 140-ITP-Mivida23 | 4716911.47 | 3870461.7235 | 495275.7 | 4365737.4235
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC21 | 21 | EMAAR- Pkg 140-ITP-Mivida21 | 9991628.97 | 8185193.8285 | 1047401.56 | 9232595.3885
Tunnel of Sokhna Road (2) | SOKHNA TU 2 -IPC01 | 1 | Tunnel of Sokhna Road (2)1 | 17783725 | 6746486.9 | 5185204.9 | 15728967.8
NUCA R05 - Z02 | R5-ZONE2-IPC04 | 4 | NUCA R05 - Z024 | 39628486.3 | 30518029.655 | 3814812.09 | 34332841.745
4 SS - Technical Service | 240 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Manshiet Nasser Substation | 1903210013 |  | Manshiet Nasser Substation | 510317.14 | 474467.36 | 56262.47 | 530729.83
Manshiet Nasser Substation | 1903210017 |  | Manshiet Nasser Substation | 3471619.05 | 3591790.48 | 0 | 3591790.48
Manshiet Nasser Substation | 1902210008 |  | Manshiet Nasser Substation | 1378837.86 | 1433991.37 | 0 | 1433991.37
Manshiet Nasser Substation | 1901210019 |  | Manshiet Nasser Substation | 5428.57 | 5645.71 | 0 | 5645.71
Manshiet Nasser Substation | 1903210016 |  | Manshiet Nasser Substation | 2266861.89 | 1988299.43 | 357030.75 | 2345330.18
Manshiet Nasser Substation | 1904210006 |  | Manshiet Nasser Substation | 701937.71 | 616451.73 | 110555.19 | 727006.92
Manshiet Nasser Substation | 1904210007 |  | Manshiet Nasser Substation | 1350167.86 | 1398388.14 | 0 | 1398388.14
Royal City | 20100005 |  | Royal City | 11082459.93 | 8006173.81 | 3699299.17 | 11705472.98
Royal City | ROYAL CITY-IC34 |  | Royal City | 9492258.84 | 4107326.4576 | 2281723.84 | 6389050.2976
AbuSultan Rd Bridge2 Extension | ABU SULTAN2-IPC 1 | 1 | AbuSultan Rd Bridge2 Extension1 | 47855181.9 | 16049067.35 | 4000000 | 44899067.35
El Mostakbal City Project | Inv. 4 Mostakbal | 4 | El Mostakbal City Project4 | 11156975.42 | 9251512.46 | 2342964.84 | 11594477.3
Canal Sugar OHTL | Inv.02 $ Sugar OHTL | 2 | Canal Sugar OHTL2 | 1663396.09 | 1314082.91 | 249509.41 | 1563592.32
Canal Sugar S/s | Inv 3 $ Sugar S/s | 3 | Canal Sugar S/s3 | 87120.81 | 68825.44 | 13068.12 | 81893.56
P-28-16 Balat Owinat Lot 3 | Inv. 10 Balat lot 3 | 10 | P-28-16 Balat Owinat Lot 310 | 3152312.34 | 2354386.33 | 330992.8 | 2685379.13
Benban 500 K.V/95 K.M | Benban Lot2 Inv1 $ | 1 | Benban 500 K.V/95 K.M1 | 189105.54 | 158749.66 | 19856.08 | 178605.74
Abou El Matameer and Sammanoud | Inv 98 P11- Sammound | 98 | Abou El Matameer and Sammanoud98 | 3556387.0081 | 2554908.4281 | 533458.05 | 3088366.4781
Abou El Matameer and Sammanoud | Inv.10 Samanod 95 | 10 | Abou El Matameer and Sammanoud10 | 1414240.74 | 1015990.55 | 212136.11 | 1228126.66
Development of Mahmudiyah axis | IPC# 4&5 | 4 | Development of Mahmudiyah axis4 | 3195000 | 3105540 | 0 | 3105540
Road El Farag Axis | 10003 |  | Road El Farag Axis | 288778 | 264330 | 0 | 264330
Port Said Subs 220/66 | Port Said Inv. 2 | 2 | Port Said Subs 220/662 | 61841695.5 | 40351295 | 15460428.88 | 55811723.88
DPW Onshore Port & Terminal | DP WORLD-IPC05 | 5 | DPW Onshore Port & Terminal5 | 37757872.1 | 27940477.28 | 5663680.82 | 33604158.1
P-28-16 Balat Owinat Lot 2 | Inv. 11 Balat Lot 2 | 11 | P-28-16 Balat Owinat Lot 211 | 17383519.05 | 12985090.6 | 1825269.5 | 14810360.1
Akhmem Assiut | Inv.42 Assuit Akhmem | 42 | Akhmem Assiut42 | 4462784.38 | 3302460.43 | 669417.66 | 3971878.09
Akhmem Assiut | Inv.34 Assuit Akhmem | 34 | Akhmem Assiut34 | 7809897.24 | 6208868.3 | 1171484.59 | 7380352.89
Akhmem Assiut | inv. 5 Assuit Akhmem | 5 | Akhmem Assiut5 | 74172564.53 | 44132675.89 | 11125884.68 | 55258560.57
EMAAR- Pkg 140-ITP-Mivida | PKG#140 -IPC 02 | 2 | EMAAR- Pkg 140-ITP-Mivida2 | 4911239.08 | 2620895.13 | 1924702.2 | 4545597.33
MOTHANA 400/132kV SS | 242 |  | MOTHANA 400/132kV SS | 927892.49 | 927892.49 | 0 | 927892.49
Akhmem - Qena | Inv.47 Qena Akhmem | 47 | Akhmem - Qena47 | 1084342.74 | 746978.97 | 162651.41 | 909630.38
Akhmem - Qena | Inv. 9 Qena - Akhmem | 9 | Akhmem - Qena9 | 40389347.35 | 32109531.11 | 6058402.13 | 38167933.24
Akhmem - Qena | Inv.8 Qena Akhmem | 8 | Akhmem - Qena8 | 850515.9 | 676160.14 | 127577.39 | 803737.53
Akhmem - Qena | Inv.7 Qena Akhmem | 7 | Akhmem - Qena7 | 43280910.52 | 25752141.77 | 6492136.58 | 32244278.35
Akhmem - Qena | Inv.33 Akhmem Qena | 33 | Akhmem - Qena33 | 1433432.22 | 709548.94 | 215014.84 | 924563.78
Akhmem - Qena | Inv.28 Akhmem Qena | 28 | Akhmem - Qena28 | 5566802.4 | 4425607.91 | 835020.36 | 5260628.27
Akhmem - Qena | Inv.23 Akhmem Qena | 23 | Akhmem - Qena23 | 4662531.26 | 3706712.34 | 699379.69 | 4406092.03
Akhmem - Qena | Inv.17 Qena - Akhmem | 17 | Akhmem - Qena17 | 8906791.57 | 7080899.29 | 1336018.74 | 8416918.03
Akhmem - Qena | Inv.14 Qena - Akhmem | 14 | Akhmem - Qena14 | 10040812.8 | 7982446.17 | 1506121.92 | 9488568.09
Akhmem - Qena | Inv.12 Qena - Akhmem | 12 | Akhmem - Qena12 | 25588009.7 | 20342467.71 | 3838201.46 | 24180669.17
Ministries Buildings | MI.ALLOCATION-IPC01 | 1 | Ministries Buildings1 | 18644827.24 | 9798900.515 | 5233060 | 15031960.515
Zambia Project | SCD4/004 |  | Zambia Project | 83278.01 | 0 | 0 | 83278.01
Elco Steel 220/33 KV SS | 1908210009 |  | Elco Steel 220/33 KV SS | 464081.18 | 487285.14 | 0 | 487285.14
C5 Bridge 2 New Alamein | IPC#6 | 6 | C5 Bridge 2 New Alamein6 | 1975750 | 1916477.5 | 0 | 1916477.5
Marsa Matrouh 500KV | Inv.8 Usd borg alarb | 8 | Marsa Matrouh 500KV8 | 1316451.44 | 1146000.26 | 138227.4 | 1284227.66
MAYSAN 400/132kV SS | 258 |  | MAYSAN 400/132kV SS | 1997759.13 | 1997759.13 | 0 | 1997759.13
MAYSAN 400/132kV SS | 250 |  | MAYSAN 400/132kV SS | 523836.53 | 523836.53 | 0 | 523836.53
NUCA R05 - Z02 | R5-ZONE 2-IPC6 | 6 | NUCA R05 - Z026 | 28390914 | 23245614.83 | 2882582.99 | 26128197.82
Latin Quarter- New Alamein | inv ( 2 ) 28-11-2020 | 2 | Latin Quarter- New Alamein2 | 18884313.36 | 9044315.26 | 0 | 9044315.26
Latin Compound - New Alamin | INV(1-8)010420 | 1 | Latin Compound - New Alamin1 | 4686640 | 3783823.86 | 0 | 3783823.86
Zambia Project | SCD1/004 |  | Zambia Project | 1677127.55 | 1509395.98 | 0 | 1509395.98
Safeer Square Bridge | SAFIER BRIDGE-IPC02F | 2 | Safeer Square Bridge2 | 7069691 | 3478470 | 1159496.2 | 10756091.2
Ministries Buildings | MINISTRIY CORE-IPC01 | 1 | Ministries Buildings1 | 36181016.75 | 20128404 | 10452262.5 | 30580666.5
LAYYAH CCPP | 504 |  | LAYYAH CCPP | 256625 | 229037.81 | 38493.75 | 267531.56
DoubleTree Mangroovy ElGouna | MANGROVE-IPC13 | 13 | DoubleTree Mangroovy ElGouna13 | 2664148.65 | 1951940.1825 | 605589.02 | 2557529.2025
DoubleTree Mangroovy ElGouna | MANGOROVE-IPC05 | 5 | DoubleTree Mangroovy ElGouna5 | 2635327.18 | 1810211.333 | 691773.39 | 2501984.723
DoubleTree Mangroovy ElGouna | 20100007 |  | DoubleTree Mangroovy ElGouna | 3318054.9 | 2286139.795 | 870989.43 | 3157129.225
DoubleTree Mangroovy ElGouna | MANGORVE-IPC02 | 2 | DoubleTree Mangroovy ElGouna2 | 5630968.01 | 3867767.2605 | 1478129.1 | 5345896.3605
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 4 | 4 | Benban 500 K.V/95 K.M4 | 270579.14 | 208615.72 | 28410.81 | 237026.53
Marsa Matrouh 500KV | Inv.37 Borg Alarab | 37 | Marsa Matrouh 500KV37 | 40728189.49 | 29161385.37 | 4276459.9 | 33437845.27
Ismailiya East Substation | ISE-CW-EGP-17 | 17 | Ismailiya East Substation17 | 2428316 | 1796953.84 | 364247.4 | 2161201.24
AWEER POWER STATION 'H' Phase | 10309 |  | AWEER POWER STATION 'H' Phase | 2890591.9 | 851118.7096 | 2007355.5025 | 2858474.2121
AWEER POWER STATION 'H' Phase | 10187 |  | AWEER POWER STATION 'H' Phase | 3617336.637 | 3175217.7147 | 401926.293 | 3577144.0077
Nagaa Hamady/Assuit OHTL | Naga Hmdy Inv.1 Equ | 1 | Nagaa Hamady/Assuit OHTL1 | 1223014 | 875812.9 | 134399.82 | 1010212.72
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 2 | 2 | Nagaa Hamady/Assuit OHTL2 | 6553246.67 | 4724893.85 | 688090.9 | 5412984.75
Fish Market | SOUQ ELSAMAK-IPC01 | 1 | Fish Market1 | 37032038.02 | 1511734 | 18018671.05 | 25631505.05
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 9 | 9 | Benban 500 K.V/95 K.M9 | 206389.5 | 159132.8 | 21670.9 | 180803.7
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 3 | 3 | Marsa Alam/ Bernes LOT2 OHTL3 | 11819509.69 | 0 | 1294808.2 | 1294808.2
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 2 | 2 | Marsa Alam/ Bernes LOT2 OHTL2 | 45934.1 | 0 | 4823.08 | 4823.08
Akhmem - Qena | Inv.48 Qena Akhmem | 48 | Akhmem - Qena48 | 17873297.89 | 12331379.24 | 2680994.68 | 15012373.92
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 5 | 5 | Marsa Alam/ Bernes LOT2 OHTL5 | 9745824.7 | 5857233.06 | 1015174.97 | 6872408.03
Port Saad Industiral zone | IPC#1 | 1 | Port Saad Industiral zone1 | 2704500 | 2604433.5 | 0 | 2604433.5
Canal Sugar 33KV OHTL | Inv. 4 Sugar 33 OHTL | 4 | Canal Sugar 33KV OHTL4 | 9076854.62 | 6913988.49 | 855947.01 | 8336455.52
33KV Canal Farm Grid | Inv. 15 Farm | 15 | 33KV Canal Farm Grid15 | 10359130.15 | 7904016.31 | 1553869.52 | 9457885.83
Port Said Subs 220/66 | Port Said Inv. 3 | 3 | Port Said Subs 220/663 | 91810868.9 | 59217605 | 22952717.35 | 82170322.35
Asec Spare-Parts | Inv 1 Asec Sparepart | 1 | Asec Spare-Parts1 | 439525.4 | 353176 | 109881.35 | 463057.35
Canal Regional Control Center | Inv.2 RCC | 2 | Canal Regional Control Center2 | 9728408.52 | 6478491.45 | 2042965.79 | 8521457.24
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 4USD | 4 | Benban 500 K.V / 100 K.M4 | 67188.57 | 49383.6 | 14109.6 | 63493.2
Benban 500 K.V/95 K.M | Benban Lot2 Inv 9 $ | 9 | Benban 500 K.V/95 K.M9 | 251500.72 | 211001.61 | 26407.58 | 237409.19
Celia | IPC#3 | 3 | Celia3 | 216937.25 | 198063.71 | 0 | 205613.126
Manshiet Nasser Substation | 1906210010 |  | Manshiet Nasser Substation | 321986.71 | 290233.48 | 52116.03 | 342349.51
HyperOne Zayed Extension | HYPER ONE- IPC10 | 10 | HyperOne Zayed Extension10 | 7629179.05 | 4688663.2125 | 1907295 | 6595958.2125
HyperOne Zayed Extension | HYPER ONE- IPC07 | 7 | HyperOne Zayed Extension7 | 12419046 | 8960289.48 | 3088611.5 | 13214062.98
HyperOne Zayed Extension | HYPER ONE2-IPC03 | 3 | HyperOne Zayed Extension3 | 10276217.14 | 7194819.68 | 2569054.29 | 10912969.97
HyperOne Zayed Extension | HYPER -IPC01 | 1 | HyperOne Zayed Extension1 | 1684524 | 2583316 | 421131 | 3004447
R5 Mix-Use Complex Project | R5-ZONE 1- IPC7 | 7 | R5 Mix-Use Complex Project7 | 4353324 | 3418442.3 | 426675.87 | 3845118.17
Safir bridge | IPC#1 | 1 | Safir bridge1 | 1183500 | 837650 | 75000 | 1144865
Suez Gulf Substation | 16 EGP VO Shippment |  | Suez Gulf Substation | 10444.25 | 9888.38 | 1098.71 | 10987.09
Ismailiya East Substation | ISE-SW-EGP-04 | 4 | Ismailiya East Substation4 | 1297188 | 959919.12 | 194578.2 | 1154497.32
Asher Mn Ramadan Bridge No2 | AlAsher Brdg 2 Final |  | Asher Mn Ramadan Bridge No2 | 9426336.26 | 494880 | 5610484.5 | 6105364.5
Ministries Buildings | MIN.ANASER WATER-02 | 2 | Ministries Buildings2 | 2113563 | 501405 | 1300000 | 1801405
Ministries Buildings | MIN-SHELL-IPC02 | 2 | Ministries Buildings2 | 27529574.79 | 8072902 | 16772114.7 | 24845016.7
Royal City | royal city-ipc22 | 22 | Royal City22 | 18490927.23 | 17384865.3315 | 7484058.67 | 24868924.0015
Royal City | ROYAL ZONE-IPC02 | 2 | Royal City2 | 1714285.71 | 4006344.6355 | 595210 | 4601554.6355
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC08 | 8 | EMAAR-PKG# 101-UPTOWN8 | 3123640.99 | 1824097.56 | 909775.35 | 2733872.91
Benban 500 K.V / 100 K.M | Benban Lot1 Inv10USD | 10 | Benban 500 K.V / 100 K.M10 | 1077864.38 | 905406.08 | 113175.76 | 1018581.84
Benban 500 K.V / 100 K.M | Benban Lot1 Inv13USD | 13 | Benban 500 K.V / 100 K.M13 | 62875.18 | 52815.15 | 6601.89 | 59417.04
Benban 500 K.V/95 K.M | Benban Lot2 Inv 5 $ | 5 | Benban 500 K.V/95 K.M5 | 1709958.6 | 1436365.23 | 179545.65 | 1615910.88
Manshiet Nasser Substation | 1908210017 |  | Manshiet Nasser Substation | 290843.58 | 169734.67 | 0 | 169734.67
SHAT Al ARAB 400/132kV SS | 265 |  | SHAT Al ARAB 400/132kV SS | 68360.02 | 68360.02 | 0 | 68360.02
LAYYAH CCPP | 508 |  | LAYYAH CCPP | 14441700 | 12866072.1 | 2188298 | 15054370.1
LAYYAH CCPP | 496 |  | LAYYAH CCPP | 3237480 | 3380409.6 | 18328 | 3398737.6
LAYYAH CCPP | 490 |  | LAYYAH CCPP | 6538440 | 6025344 | 513096 | 6538440
OHTL Mostakable East Boundary | Inv. 01 Future OHTL | 1 | OHTL Mostakable East Boundary1 | 14461699.54 | 12003203.62 | 3036956.9 | 15040160.52
Asec Spare-Parts | Inv 4 Asec Sparepart | 4 | Asec Spare-Parts4 | 2766152 | 2353637 | 788353.46 | 3141990.46
Akhmem Assiut | Istill.4 lot 1 Akhme |  | Akhmem Assiut | 1440616.76 | 1439034 | 0 | 1439034
El Katameya Mall | inv(6)100320 | 6 | El Katameya Mall6 | 312760 | 190730.28 | 0 | 190730.28
El Katameya Mall | inv(3)251219 | 3 | El Katameya Mall3 | 585760 | 458205.31 | 0 | 458205.31
El Katameya Mall | inv(1)101119 | 1 | El Katameya Mall1 | 418387.2 | 311704.71 | 0 | 311704.71
MOTHANA 400/132kV SS | 273 |  | MOTHANA 400/132kV SS | 1318474.25 | 1318474.25 | 0 | 1318474.25
C5 Bridge 2 New Alamein | IPC#3 | 3 | C5 Bridge 2 New Alamein3 | 1933000 | 1875010 | 0 | 1875010
C5 Bridge 2 New Alamein | IPC#2 | 2 | C5 Bridge 2 New Alamein2 | 2602250 | 2522282.5 | 0 | 2522282.5
NUCA R05 - Z02 | R05 PH2 IPC013 | 13 | NUCA R05 - Z0213 | 25243578 | 20731287.35 | 2608113.2 | 23339400.55
NUCA R05 - Z02 | R5 FINSHING-IPC08 | 8 | NUCA R05 - Z028 | 16500636.8 | 12951782.63 | 1650063.7 | 14601846.33
NUCA R05 - Z02 | R5 FINSHING-IPC07 | 7 | NUCA R05 - Z027 | 10813860.39 | 8569582.89 | 1081386.05 | 9650968.94
NUCA R05 - Z02 | R5 FINSHING-IPC06 | 6 | NUCA R05 - Z026 | 15286382 | 12114056.05 | 1528638.2 | 13642694.25
Mauritania Lot 1 | Inv.1 - Lot 1 | 1 | Mauritania Lot 11 | 255854.38 | 208279.69 | 0 | 255839.38
Celia | IPC#1 | 1 | Celia1 | 664719.63 | 606889.02 | 0 | 624238.203
Suez Gulf Substation | 22 EGP VO TOAC |  | Suez Gulf Substation | 474531.48 | 434236.4 | 49919.53 | 484155.93
MOTHANA 400/132kV SS | 290 |  | MOTHANA 400/132kV SS | 194047.08 | 194047.08 | 0 | 194047.08
Ismailiya East Substation | ISE-SW-EGP-05 | 5 | Ismailiya East Substation5 | 835625 | 618362.5 | 125343.75 | 743706.25
ESU Ph2-Enabling & Struc | ESU PHASE2-IPC08 | 8 | ESU Ph2-Enabling & Struc8 | 2504382.36 | 1607563.008 | 788880.47 | 2396443.478
ESU Ph2-Enabling & Struc | SEWEDY UNI 2- IPC04 | 4 | ESU Ph2-Enabling & Struc4 | 17471458.95 | 14773672.5575 | 5503509.61 | 20277182.1675
ESU Ph2-Enabling & Struc | E.S.U PH2-IPC01 | 1 | ESU Ph2-Enabling & Struc1 | 1222080 | 2832679.4325 | 384955.2 | 3217634.6325
Cairo Capital Cables Tunnel | Tunnel Inv. 11 | 11 | Cairo Capital Cables Tunnel11 | 18539568.45 | 12291733.7 | 4634892.13 | 16926625.83
Cairo Capital Cables Tunnel | Tunnel Inv. 3 | 3 | Cairo Capital Cables Tunnel3 | 38855418.3 | 26149696.4 | 9713854.6 | 35863551
Cairo Capital Cables Tunnel | Tunnel Inv. 2 + | 2 | Cairo Capital Cables Tunnel2 | 41945.4 | 31459.05 | 10486.35 | 41945.4
EDNC Retail & Offices Civil | SOREAL-IPC08 | 8 | EDNC Retail & Offices Civil8 | 82004688.27 | 59087057.7335 | 17186679.54 | 76273737.2735
Assuit PP (CP-118) | 491 |  | Assuit PP (CP-118) | 262534.21 | 234311.78 | 41349.14 | 275660.92
Abu Sultan Road Extension | ABUSOULTAN 1 -FINAL |  | Abu Sultan Road Extension | 1040367.67 | 495270 | 495279 | 990549
Ministries Buildings | MIN.LONG LIGHT-IPC01 | 1 | Ministries Buildings1 | 78087000.75 | 18867582 | 49728549.94 | 68596131.94
Mahmoudia Additional Scope | 528 |  | Mahmoudia Additional Scope | 19798312.5 | 19798312.5 | 0 | 19798312.5
Kayan 3 New Cairo Capital City | KAYAN MEP2-IPC01 | 1 | Kayan 3 New Cairo Capital City1 | 55642027 | 20757211 | 28054365.5 | 48811576.5
Manshiet Nasser Substation | 1903210018 |  | Manshiet Nasser Substation | 11144.9 | 9473.16 | 1671.74 | 11144.9
Manshiet Nasser Substation | 1902210012 |  | Manshiet Nasser Substation | 424161.5 | 360537.28 | 63624.22 | 424161.5
Royal City | ROYAL CENTER-IPC04 | 4 | Royal City4 | 4548914.9 | 4400341.915 | 703274.95 | 5103616.865
HyperOne Zayed Extension | HYPER ONE-IPC02 | 2 | HyperOne Zayed Extension2 | 11473371.43 | 8637288.8615 | 2868342.86 | 11505631.7215
Beni Seuf - 358 | Inv.1 Temmay Amded | 1 | Beni Seuf - 3581 | 248553194.86 | 177318239.51 | 56320584.39 | 233638823.9
Manshiet Nasser Substation | 180169 |  | Manshiet Nasser Substation | 1995650.91 | 1855456.44 | 220020.51 | 2075476.95
Manshiet Nasser Substation | 180168 |  | Manshiet Nasser Substation | 1074522.15 | 1009782.19 | 118466.07 | 1128248.26
OHTL Mostakable East Boundary | Inv. 02 Future OHTL | 2 | OHTL Mostakable East Boundary2 | 3111029.43 | 2582154.43 | 653316.18 | 3235470.61
Canal Sugar OHTL | Inv.01 $ Sugar OHTL | 1 | Canal Sugar OHTL1 | 1759769.56 | 1390217.95 | 263965.43 | 1654183.38
Elco Steel 220/33 KV SS | 1903210010 |  | Elco Steel 220/33 KV SS | 572013.87 | 600614.56 | 0 | 600614.56
IKEA Extension MoA | IKEA-IPC02 | 2 | IKEA Extension MoA2 | 10719807.9 | 10688939.41 | 1339618.13 | 12028557.54
Abou El Matameer and Sammanoud | Inv 103P16Abo Matami | 103 | Abou El Matameer and Sammanoud103 | 4158694.75 | 3403475.78 | 623804.21 | 4027279.99
Abou El Matameer and Sammanoud | aboelmatamir 8inv.86 | 86 | Abou El Matameer and Sammanoud86 | 4651061.61 | 3364577.97 | 697659.24 | 4062237.21
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .23 | 23 | Benban 3/ Toshka 2 LOT 423 | 2513.14 | 1961.36 | 263.88 | 2225.24
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .15 | 15 | Benban 3/ Toshka 2 LOT 415 | 5299865.74 | 3614113.45 | 556485.9 | 4170599.35
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .20 | 20 | Benban 3/ Toshka 2 LOT 420 | 8559000.85 | 6735539.87 | 898695.09 | 7634234.96
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .14 | 14 | Benban 3/ Toshka 2 LOT 414 | 84072046.09 | 66164306.88 | 8827564.84 | 74991871.72
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .8 | 8 | Benban 3/ Toshka 2 LOT 48 | 4524558.18 | 3488147.4 | 475078.61 | 3963226.01
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .10 | 10 | Benban 3/ Toshka 2 LOT 410 | 29273363.1 | 20959734.15 | 3073703.13 | 24033437.28
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .5 | 5 | Benban 3/ Toshka 2 LOT 45 | 3823275.89 | 2947751.18 | 401443.97 | 3349195.15
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $3 | 3 | Benban 3/ Toshka 2 LOT 43 | 2188091.87 | 1837672.66 | 229749.65 | 2067422.31
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $9 | 9 | Benban 3/ Toshka 2 LOT 49 | 208365.78 | 113861.73 | 21878.41 | 135740.14
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .8 | 8 | Benban 3/ Toshka 2 LOT 48 | 31261604.28 | 25665776.55 | 3282468.45 | 28948245
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $6 | 6 | Benban 3/ Toshka 2 LOT 46 | 963603.78 | 800622.27 | 101178.4 | 901800.67
CFC Podium 2 | IPC-03-CFC Podium | 3 | CFC Podium 23 | 17039700.42 | 12263842.721 | 3991464.73 | 16255307.451
Royal City | ROYAL CITY-IPC23 | 23 | Royal City23 | 8598719.65 | 6578450.5925 | 1887253.3 | 8465703.8925
Badr 500 S/S / Zizenia 220 Kv | Badr-Zizenia Inv.3 | 3 | Badr 500 S/S / Zizenia 220 Kv3 | 5745036 | 3373685.25 | 1436259 | 4809944.25
SHAT Al ARAB 400/132kV SS | 294 |  | SHAT Al ARAB 400/132kV SS | 98101.83 | 98101.83 | 0 | 98101.83
MAYSAN 400/132kV SS | 296 |  | MAYSAN 400/132kV SS | 1205121.23 | 1205121.23 | 0 | 1205121.23
C5 Bridge 2 New Alamein | IPC#5 | 5 | C5 Bridge 2 New Alamein5 | 3805000 | 3687050 | 0 | 3687050
Ismailiya East Substation | ISE-SD-EURO-04 | 4 | Ismailiya East Substation4 | 322973.65 | 261417.57 | 26028.98 | 287446.55
Badr | Inv. 20 Badr | 20 | Badr20 | 18402201.51 | 9946520.02 | 2760330.08 | 12706850.1
IKEA Extension MoA | IKEA-IPC03 | 3 | IKEA Extension MoA3 | 10066585.31 | 7184168.17 | 868064.09 | 8052232.26
Nuweibaa (Swro) | 2002210002 |  | Nuweibaa (Swro) | 62581 | 50064.8 | 12516.2 | 62581
Asec Spare-Parts | Inv 6 EUR Asec Spare | 6 | Asec Spare-Parts6 | 180000 | 73854 | 51300 | 125154
Asec Spare-Parts | Inv 5 EUR Asec Spare | 5 | Asec Spare-Parts5 | 616545.07 | 486959 | 199827.96 | 686786.96
LAYYAH CCPP | MP-06 | 6 | LAYYAH CCPP6 | 10283760 | 0 | 10283760 | 10283760
Port Saad Industiral zone | IPC#5 | 5 | Port Saad Industiral zone5 | 10439080 | 10052834.04 | 0 | 10052834.04
CFC Podium 2 | CFC-IPC19 | 19 | CFC Podium 219 | 20398722.15 | 14008565.7 | 2676327.95 | 16684893.65
Latin Quarter- New Alamein | INV(1)250620 | 1 | Latin Quarter- New Alamein1 | 9564233.64 | 5246592.96 | 0 | 5246592.96
El Boghaz Brigde | IPC#23 | 23 | El Boghaz Brigde23 | 737330.04 | 141664.58 | 0 | 728287.62
El Boghaz Brigde | IPC#24 | 24 | El Boghaz Brigde24 | 801174.2 | 752488.75 | 0 | 752488.75
Wadi El Natroun | IPC#1 | 1 | Wadi El Natroun1 | 2585700 | 2348313.95 | 0 | 2348313.95
Museum of Egyp. Civilization | IPC#5 | 5 | Museum of Egyp. Civilization5 | 1290723.75 | 1151012.23 | 0 | 1151012.23
ORA Zed Park LOCK&LOAD | ORA ZED-IPC02 | 2 | ORA Zed Park LOCK&LOAD2 | 299629.7 | 264423.205 | 0 | 264423.205
Assuit PP (CP-118) | 2001210008 |  | Assuit PP (CP-118) | 2659221.99 | 2346725.01 | 418827.46 | 2765552.47
Manshiet Nasser Substation | 530 |  | Manshiet Nasser Substation | 1019830.46 | 766362.85 | 164140.6 | 930503.45
marassi inland marina | IPC#7 | 7 | marassi inland marina7 | 1678674.16 | 2706690.9 | 0 | 1437279.16
Toshka GIS 500 kV | Toshka Sub Inv. 22 $ | 22 | Toshka GIS 500 kV22 | 261121.27 | 97273.66 | 68544.33 | 165817.99
EMAAR-Pkg#162/163- Marassi | PKG#162 - IPC07 | 7 | EMAAR-Pkg#162/163- Marassi7 | 8577630.83 | 8042168.0415 | 936620.49 | 8978788.5315
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC06 | 6 | EMAAR-Pkg#162/163- Marassi6 | 5990865.5 | 4824045.385 | 617291.93 | 5441337.315
IKEA Extension MoA | IKEA-IPC09 | 9 | IKEA Extension MoA9 | 19195362.4 | 21335051.85 | 7587881.06 | 28922932.91
Juba PV | Inv. No.1- Juba Proj | 1 | Juba PV1 | 20000000 | 20000000 | 0 | 20000000
Beni Seuf - 358 | Inv.6 kafr zeat itay | 6 | Beni Seuf - 3586 | 7338147.52 | 6524020 | 1106466.8 | 7630486.8
ESU Ph2-Enabling & Struc | E.S.U2-MEP-IPC07 | 7 | ESU Ph2-Enabling & Struc7 | 56805725.81 | 25755604.8065 | 5532944.21 | 31288549.0165
MOTHANA 400/132kV SS | 302 |  | MOTHANA 400/132kV SS | 2954651.29 | 2954651.29 | 0 | 2954651.29
Kayan 3 New Cairo Capital City | KAYAN-MEP2-IPC02 | 2 | Kayan 3 New Cairo Capital City2 | 48674390.5 | 32946170 | 10982056.5 | 43928226.5
CFC Podium 2 | CFC IPC022 | 22 | CFC Podium 222 | 19833699.33 | 13410069.82 | 2562732.734 | 15972802.554
CFC Podium 2 | CFC-IPC02 | 2 | CFC Podium 22 | 15707266.4 | 17105451.15 | 2038078.37 | 19143529.52
DPW Onshore Port & Terminal | DP WORLD-IPC12 | 12 | DPW Onshore Port & Terminal12 | 148210852.69 | 109675422.28 | 22231627.9 | 131907050.18
Royal City | ROYAL CITY -IPC27 | 27 | Royal City27 | 23615681.47 | 11636419.9 | 5597473.3 | 17233893.2
Elmaragha Bridge - Sohag | IPC#2 | 2 | Elmaragha Bridge - Sohag2 | 252646.1538 | 451363.5 | 0 | 224855.0769
Multi Sport Hall | 10018 |  | Multi Sport Hall | 456945 | 406681.05 | 0 | 406681.05
Villa Fabio | 10028 |  | Villa Fabio | 76131.46 | 62300 | 10262.51 | 72562.51
Villa Fabio | 10027 |  | Villa Fabio | 39737.49 | 0 | 39737.49 | 39737.49
Ministries Building ROOF | 10002 |  | Ministries Building ROOF | 216236.09 | 203261.93 | 0 | 203261.93
Rail Way Tunnel Zagazig | IPC002 | 2 | Rail Way Tunnel Zagazig2 | 552520 | 514948.64 | 0 | 514948.64
Maspiro Towers | IPC#3 | 3 | Maspiro Towers3 | 538200 | 532818 | 0 | 533894.4
Canal Sugar OHTL | Inv.05 Sugar OHTL | 5 | Canal Sugar OHTL5 | 7293163.42 | 5761599.11 | 1093974.51 | 6855573.62
Ismailiya East Substation | ISE-SD-EGP-01 | 1 | Ismailiya East Substation1 | 244285 | 241842.15 | 0 | 241842.15
Marsa Matrouh 500KV | Inv.29 Borg Alarab | 29 | Marsa Matrouh 500KV29 | 31843663.25 | 22408230.01 | 3343584.64 | 25751814.65
Marsa Matrouh 500KV | Inv.25 Borg Alarab | 25 | Marsa Matrouh 500KV25 | 36010234.62 | 31454945.04 | 3781074.64 | 35236019.68
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC019 | 19 | EMAAR-Pkg#162/163- Marassi19 | 9320216.49 | 8474286.4545 | 2317036.86 | 10791323.3145
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC017 | 17 | EMAAR-Pkg#162/163- Marassi17 | 5496981.8 | 2625202.88 | 717782.18 | 3342985.06
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC01 | 1 | EMAAR-Pkg#162/163- Marassi1 | 1493908.79 | 1068966.4295 | 313720.85 | 1382687.2795
Vila Palm Hills | 10026 |  | Vila Palm Hills | 65347.64 | 3900 | 50000 | 53900
Marsa Matrouh 500KV | Inv.26Usd borg alarb | 26 | Marsa Matrouh 500KV26 | 624.47 | 369.79 | 0 | 369.79
EMAAR-PKG# 144, Marassi | PKG#144 -IPC14 | 14 | EMAAR-PKG# 144, Marassi14 | 10733689.11 | 10786798.0055 | 38643.69 | 10825441.6955
DoubleTree Mangroovy ElGouna | MANGOROVE RENT-IPC3 | 3 | DoubleTree Mangroovy ElGouna3 | 424545 | 441526.8 | 0 | 441526.8
Marsa Matrouh 500KV | Inv.65 Borg Alarab | 65 | Marsa Matrouh 500KV65 | 6452201.13 | 4619780.78 | 677481.12 | 5297261.9
Marsa Matrouh 500KV | Inv.63 Borg Alarab | 63 | Marsa Matrouh 500KV63 | 16797542.59 | 14672652.31 | 1763741.97 | 16436394.28
Ministries Buildings | MIN.SHELL-IPC03 | 3 | Ministries Buildings3 | 27623195.09 | 7792410 | 2137092.65 | 24929511.5
Sodic East | 10011 |  | Sodic East | 282795.84 | 149855.37 | 98978.54 | 248833.91
Sodic East | 10012 |  | Sodic East | 55306.44 | 33499.57 | 19357.25 | 52856.82
SHAT Al ARAB 400/132kV SS | 325 |  | SHAT Al ARAB 400/132kV SS | 218382.25 | 218382.25 | 0 | 218382.25
SHATRA 400/132kV SS | 333 |  | SHATRA 400/132kV SS | 68245.97 | 68245.97 | 0 | 68245.97
SHATRA 400/132kV SS | 332 |  | SHATRA 400/132kV SS | 925089.06 | 925089.06 | 0 | 925089.06
MAYSAN 400/132kV SS | 310 |  | MAYSAN 400/132kV SS | 419711.08 | 419711.08 | 0 | 419711.08
MOTHANA 400/132kV SS | 336 |  | MOTHANA 400/132kV SS | 130535.22 | 130535.22 | 0 | 130535.22
MOTHANA 400/132kV SS | 334 |  | MOTHANA 400/132kV SS | 30918.9 | 30918.9 | 0 | 30918.9
Ministries Buildings | 20100004 |  | Ministries Buildings | 1326870 | 965552 | 83450.9 | 1049002.9
Miscellaneous Projects | 2003210013 |  | Miscellaneous Projects | 114320.62 | 126895.89 | 0 | 126895.89
HyperOne Zayed Extension | HYPER ONE- IPC08 | 8 | HyperOne Zayed Extension8 | 7092750.29 | 3276433 | 1789290 | 5371325.34
AWEER POWER STATION 'H' Phase | Eng-25 rev0 | 25 | AWEER POWER STATION 'H' Phase25 | 226423.5 | 237672.87 | 0 | 237672.87
Sodic East | 10007 |  | Sodic East | 99314.4 | 51848.84 | 34760.04 | 86608.88
Air Defence College | TR46 IPC 11 | 11 | Air Defence College11 | 190510.2 | 0.2 | 0 | 190510.2
Royal City | ROYAL CITY-IPC28 | 28 | Royal City28 | 18900076.14 | 10500306.76 | 4655389.5 | 15155696.26
ESU Ph2-Enabling & Struc | E.S.U-PHASE2-MEP-01 | 1 | ESU Ph2-Enabling & Struc1 | 11716231.9 | 15636298.9 | 3410819.37 | 39047118.27
EDNC Retail & Offices Civil | SOREAL - IPC13 | 13 | EDNC Retail & Offices Civil13 | 15752551.19 | 13698867.9095 | 1739779.19 | 15438647.0995
Cameron EDC | 024/2020 FCV |  | Cameron EDC | 69315041.94 | 33157520.97 | 0 | 36157520.97
DPW Onshore Port & Terminal | DP WORLD- IPC13 | 13 | DPW Onshore Port & Terminal13 | 124566873.87 | 92179486 | 18685031.08 | 110864517.08
Angola Emergency fast-track | ANG-Cam-Inv 6 - Ints | 6 | Angola Emergency fast-track6 | 6921724.66 | 5075026.78 | 0 | 5075026.78
EMAAR-Pkg#162/163- Marassi | PKG#162 -IPC02 | 2 | EMAAR-Pkg#162/163- Marassi2 | 8785942 | 7794726.53 | 997481.89 | 8792208.42
AWEER POWER STATION 'H' Phase | IMP-036prog for 35 | 36 | AWEER POWER STATION 'H' Phase36 | 402668.77 | 353309.752 | 44740.97 | 398050.722
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC13 | 13 | EMAAR-PKG# 101-UPTOWN13 | 2584477.67 | 1246695.2535 | 598182.26 | 1844877.5135
Port Saad Industiral zone | IPC#8 | 8 | Port Saad Industiral zone8 | 66900 | 0 | 0 | 66900
Royal City | ROYAL CENTR ZONE-07 | 7 | Royal City7 | 6478470.72 | 6442723.346 | 1735335.48 | 8178058.826
P-28-16 Balat Owinat Lot 2 | Inv. 8 Balat Lot 2 | 8 | P-28-16 Balat Owinat Lot 28 | 13500978.1 | 10084836.64 | 1417602.7 | 11502439.34
P-28-16 Balat Owinat Lot 2 | Inv. 6 Balat Lot 2 | 6 | P-28-16 Balat Owinat Lot 26 | 5902339.3 | 4408656.71 | 619745.63 | 5028402.34
AWEER POWER STATION 'H' Phase | IMP-042 Rev0 | 42 | AWEER POWER STATION 'H' Phase42 | 3897039.52 | 3853667.08 | 0 | 3853667.08
IKEA Extension MoA | IEKA-IPC12 | 12 | IKEA Extension MoA12 | 27691689.43 | 15913350.29 | 6651541.01 | 22564891.3
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .3 | 3 | Benban 3/ Toshka 2 LOT 43 | 21849242 | 17938232.85 | 2294170.41 | 20232403.26
LAYAN Substation | 11743 |  | LAYAN Substation | 149657.2245 | 252920.7115 | 0 | 126460.3557
LAYAN Substation | 10722 |  | LAYAN Substation | 236362.4835 | 798905.2 | 0 | 199726.3
LAYAN Substation | 10662 |  | LAYAN Substation | 1033864.3999 | 8736154.2 | 0 | 873615.42
LAYAN Substation | 10604 |  | LAYAN Substation | 946488.368 | 3142341.4 | 0 | 785585.35
LAYAN Substation | 10583 |  | LAYAN Substation | 722308.48 | 1199032.08 | 0 | 599516.04
LAYAN Substation | 10442 |  | LAYAN Substation | 709095.52 | 1177098.5 | 0 | 588549.25
LAYAN Substation | 10302 |  | LAYAN Substation | 352345.6 | 292446.85 | 0 | 292446.85
LAYAN Substation | 10263 |  | LAYAN Substation | 352345.6 | 292446.85 | 0 | 292446.85
LAYAN Substation | 10150 |  | LAYAN Substation | 4542691.37 | 3770433.83 | 0 | 3770433.83
CFC Podium 2 | CFC-IPC06 | 6 | CFC Podium 26 | 42011128.3 | 31500278.46 | 6008704.37 | 37508982.83
R5 | inv(6)050320 | 6 | R56 | 841260 | 282423.4133 | 0 | 740601.9
Museum of Egyp. Civilization | IPC#1&2 | 1 | Museum of Egyp. Civilization1 | 1217123.25 | 1109107.77 | 0 | 1109107.77
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC11 | 11 | EMAAR- Pkg 140-ITP-Mivida11 | 3121472.23 | 2644790.7215 | 339824.7 | 2984615.4215
AWEER POWER STATION 'H' Phase | ENG/026 Rev0 adj |  | AWEER POWER STATION 'H' Phase | 19285.1 | 20177.541 | 0 | 20177.541
Olympic Multi – Sports Hall | Olympic IPC Final |  | Olympic Multi – Sports Hall | 36243472.6 | 28568817.5 | 19458253.1 | 48361770.6
Banha PP (CP-117) | 2005210005 |  | Banha PP (CP-117) | 29.19 | 29.19 | 0 | 29.19
SHAT Al ARAB 400/132kV SS | 348 |  | SHAT Al ARAB 400/132kV SS | 3125240.64 | 3125240.64 | 0 | 3125240.64
MOTHANA 400/132kV SS | 337 |  | MOTHANA 400/132kV SS | 26465.8 | 26465.8 | 0 | 26465.8
MOTHANA 400/132kV SS | 338 |  | MOTHANA 400/132kV SS | 447875.61 | 447875.61 | 0 | 447875.61
Minis Building(Polyurethane) | 10095 |  | Minis Building(Polyurethane) | 314193.87 | 279632.55 | 0 | 279632.55
Minis Building(Polyurethane) | 10193 |  | Minis Building(Polyurethane) | 146060.09 | 129993.49 | 0 | 129993.49
Museum of Egyp. Civilization | IPC#4 | 4 | Museum of Egyp. Civilization4 | 1111309.4643 | 1014935.73 | 0 | 1028434.0186
ESU Ph2-Enabling & Struc | SewedyUNi 2- IPC03 | 3 | ESU Ph2-Enabling & Struc3 | 19830117.9 | 23262698.715 | 6177834.6 | 29440533.315
Assuit PP (CP-118) | 2005210001 |  | Assuit PP (CP-118) | 191842.74 | 171219.65 | 30215.23 | 201434.88
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC14 | 14 | EMAAR-PKG# 101-UPTOWN14 | 2596223.72 | 1459609.626 | 699324.21 | 2158933.836
Royal City | ROYAL C.ZONE- IPC08 | 8 | Royal City8 | 17136692.17 | 12356243.75 | 3340696.2 | 15696939.95
Ministries A13-A14 | 10195 |  | Ministries A13-A14 | 860590 | 746992.12 | 0 | 746992.12
Canal Sugar OHTL | Inv.09 Sugar OHTL | 9 | Canal Sugar OHTL9 | 1904197.79 | 957352.17 | 232187.76 | 1189539.93
SHAT Al ARAB 400/132kV SS | 353 |  | SHAT Al ARAB 400/132kV SS | 1174480.63 | 1174480.63 | 0 | 1174480.63
SHATRA 400/132kV SS | 352 |  | SHATRA 400/132kV SS | 3459441.19 | 3459441.19 | 0 | 3459441.19
Marsa Matrouh 500KV | Inv.35 Borg Alarab | 35 | Marsa Matrouh 500KV35 | 1344380.95 | 1174323.24 | 141160 | 1315483.24
ESU Ph2-Enabling & Struc | ESU2-IPC4-MEP | 4 | ESU Ph2-Enabling & Struc4 | 27676491.14 | 18322600.95 | 8629523 | 26952123.95
Benban 500 K.V/95 K.M | Benban Lot2 Inv 15 $ | 15 | Benban 500 K.V/95 K.M15 | 2054162.73 | 1725397.7 | 215687.09 | 1941084.79
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 08 | 8 | Suez Gulf/S4 - 500KV OHTL8 | 2135496.86 | 1731877.41 | 224227.17 | 1956104.58
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 07 | 7 | Suez Gulf/S4 - 500KV OHTL7 | 120800.77 | 97961.63 | 12684.08 | 110645.71
Damac 2x60/22 KV S/S | Inv. 38 Damac | 38 | Damac 2x60/22 KV S/S38 | 1978003.49 | 1389391.15 | 296700.51 | 1686091.66
Oasis Buildings- New Capital | Inv(6)200620 | 6 | Oasis Buildings- New Capital6 | 2174220 | 2060723.86 | 0 | 2060723.86
MAYSAN 400/132kV SS | 356 |  | MAYSAN 400/132kV SS | 1630876.81 | 1630876.81 | 0 | 1630876.81
Elhegaz | Final |  | Elhegaz | 225520 | 0 | 0 | 223264.8
Akhmem Assiut | Inv.52 Assuit Akhmem | 52 | Akhmem Assiut52 | 5830729.68 | 4023203.47 | 874609.45 | 4897812.92
Ministries A17-A18 | 10133 |  | Ministries A17-A18 | 511215.2 | 431976.85 | 0 | 431976.85
Royal City | ROYAL CITY-IPC31 | 31 | Royal City31 | 12028045.18 | 6475509.799 | 3074149.35 | 9549659.149
SHAT Al ARAB 400/132kV SS | 358 |  | SHAT Al ARAB 400/132kV SS | 1702946.28 | 1702946.28 | 0 | 1702946.28
El Katameya Mall | inv(9)150720 | 9 | El Katameya Mall9 | 820120 | 658722.58 | 0 | 658722.58
Ain-Sokhna PP (CP-117) | 200023 |  | Ain-Sokhna PP (CP-117) | 283800 | 962082 | 0 | 320694
Angola Emergency fast-track | ANG-Cam-Inv 5 | 5 | Angola Emergency fast-track5 | 2845800 | 1926983.6 | 0 | 1926983.6
Mohamed Ali Palace | 10253 |  | Mohamed Ali Palace | 30504.6 | 23473.86 | 0 | 23473.86
Ghana | 40B/P/10/ER/2017/USD |  | Ghana | 35924.09 | 35924.09 | 0 | 35924.09
Ameria | IPC#1 | 1 | Ameria1 | 976800 | 805870 | 0 | 805870
HyperOne Zayed Extension | IPC-FINAL-HYPER MEP |  | HyperOne Zayed Extension | 5715164 | 5165148 | 0 | 5165148
SHATRA 400/132kV SS | 362 |  | SHATRA 400/132kV SS | 4709636.05 | 4709636.05 | 0 | 4709636.05
4 SS - Technical Service | 368 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
EDNC Retail & Offices Civil | SOREAL-IPC16 | 16 | EDNC Retail & Offices Civil16 | 42785902.69 | 31947230.0345 | 6235511.4 | 38182741.4345
Royal City | ROYAL ZONE-IPC10 | 10 | Royal City10 | 3936991.6 | 3061009.751 | 826768.24 | 3887777.991
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .6 | 6 | Benban 3/ Toshka 2 LOT 46 | 292365.93 | 225420.43 | 30698.42 | 256118.85
R5 | inv(7)100320 | 7 | R57 | 1697040 | 276552 | 0 | 1570563.18
Badr 500 S/S / Zizenia 220 Kv | Badr-Zizenia Inv.1 | 1 | Badr 500 S/S / Zizenia 220 Kv1 | 31255806.45 | 19814066.15 | 7813951.61 | 27628017.76
Angola Emergency fast-track | ANG-Mor-Inv.-5 | 5 | Angola Emergency fast-track5 | 10302977.71 | 6364856.45 | 0 | 6364856.45
Angola Emergency fast-track | ANG-Mor-Inv.-3 | 3 | Angola Emergency fast-track3 | 34487599.53 | 21651818.02 | 0 | 21651818.02
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .4 | 4 | Benban 3/ Toshka 2 LOT 44 | 15686510.91 | 12877553.82 | 1646945.98 | 14525810.91
LAYAN Substation | 10149 |  | LAYAN Substation | 4774415.23 | 3962764.64 | 0 | 3962764.64
Racecores 3092-16 132KV C | 11403 |  | Racecores 3092-16 132KV C | 2402432.68 | 9970095.6 | 0 | 1994019.12
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC04 | 4 | EMAAR-Pkg#162/163- Marassi4 | 3481812.47 | 6845695.7735 | 2009078.49 | 8854774.2635
33KV Canal Farm Grid | Inv. 08 Farm | 8 | 33KV Canal Farm Grid8 | 9953272.35 | 7594346.8 | 1492990.85 | 9087337.65
Ismailiya East Substation | ISE-SD-EURO-06 | 6 | Ismailiya East Substation6 | 915357.61 | 814668.27 | 0 | 814668.27
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $5 | 5 | Benban 3/ Toshka 2 LOT 45 | 781087.62 | 656012.61 | 82014.2 | 738026.81
NUCA R05 - Z02 | R05(2) IPC 51 | 51 | NUCA R05 - Z0251 | 25554941.85 | 21483828.77 | 2821079 | 24304907.77
NUCA R05 - Z02 | R052 ipc40 | 40 | NUCA R05 - Z0240 | 8606103.72 | 10606046.67 | 1301058.28 | 11907104.95
NUCA R05 - Z02 | R5 2 IPC37 | 37 | NUCA R05 - Z0237 | 8133883.45 | 3569378.99 | 492306.42 | 4061685.41
Ministries A17-A18 | IPC_5_gama_ministry |  | Ministries A17-A18 | 331014.5 | 279305.26 | 0 | 279305.26
Nuweibaa (Swro) | 2006210001 |  | Nuweibaa (Swro) | 634878.02 | 507902.42 | 126975.6 | 634878.02
SHAT Al ARAB 400/132kV SS | 361 |  | SHAT Al ARAB 400/132kV SS | 3461798.5 | 3461798.5 | 0 | 3461798.5
SHATRA 400/132kV SS | 367 |  | SHATRA 400/132kV SS | 3012885.67 | 3012885.5 | 0 | 3012885.5
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.05 | 5 | Mostakbal 2 Package No. (8)5 | 49890202.61 | 41408868.16 | 10476942.55 | 51885810.71
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.02 | 2 | Mostakbal 2 Package No. (8)2 | 1951436.55 | 1619692.34 | 409801.67 | 2029494.01
Olympic Multi – Sports Hall | OLYMPIC-IPC02 | 2 | Olympic Multi – Sports Hall2 | 85003516.9 | 13887855 | 43526899.2 | 72465094.2
EDNC Retail & Offices Civil | SOREAL-IPC17 | 17 | EDNC Retail & Offices Civil17 | 30425304.07 | 23516460.0735 | 4121239.46 | 27637699.5335
AWEER POWER STATION 'H' Phase | IMP-049 | 49 | AWEER POWER STATION 'H' Phase49 | 5375241.63 | 5315422.1115 | 0 | 5315422.1115
Beni Suef Substation R61 | BSF-CW-EGP-15 | 15 | Beni Suef Substation R6115 | 2347798.34 | 1737370.78 | 352169.75 | 2089540.53
Beni Suef Substation R61 | BSF-SW-06 | 6 | Beni Suef Substation R616 | 1004938 | 748678.81 | 150740.7 | 899419.51
Tamey El-amdeed Substation | TAM-CW-EGP-21 | 21 | Tamey El-amdeed Substation21 | 138782.46 | 102699.02 | 20817.37 | 123516.39
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.07 | 7 | Mostakbal 2 Package No. (8)7 | 13640499.21 | 10830556.37 | 2864504.83 | 13695061.2
Nuweibaa (Swro) | 2008210007 |  | Nuweibaa (Swro) | 234443.98 | 187555.18 | 46888.8 | 234443.98
El Katameya Mall | inv ( 11 ) 15-9-2020 | 11 | El Katameya Mall11 | 113960 | 50000 | 45351.14 | 95351.14
Marsa Matrouh 500KV | Inv.22Usd borg alarb | 22 | Marsa Matrouh 500KV22 | 70010.28 | 68090.37 | 0 | 68090.37
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC15 | 15 | EMAAR-PKG# 101-UPTOWN15 | 4658928.78 | 1268535.189 | 3599545.25 | 4868080.439
Mivida | 10293 |  | Mivida | 522840 | 517611.6 | 0 | 517611.6
Almaza Bridge - Safir 2 | S-003 | 3 | Almaza Bridge - Safir 23 | 501472.5 | 50000 | 0 | 457788.5
Substation Elco Steel | PSP ELCO-IPC11 | 11 | Substation Elco Steel11 | 4095222.62 | 3142902.52 | 1038383.05 | 4181285.57
AWEER POWER STATION 'H' Phase | ENG/035 |  | AWEER POWER STATION 'H' Phase | 177611.9 | 186492.495 | 0 | 186492.495
AWEER POWER STATION 'H' Phase | IMP- 056/058 | 56 | AWEER POWER STATION 'H' Phase56 | 1870689.35 | 3699807.84 | 0 | 1849903.92
Group # 1 - 25 LX | Reailway PSP Inv. 01 | 1 | Group # 1 - 25 LX1 | 1765500 | 1747845 | 0 | 1747845
Daraw Bridge | IPC#1 | 1 | Daraw Bridge1 | 1100000 | 920224.04 | 0 | 920224.04
EMAAR-Pkg#162/163- Marassi | PKG#163 -IPC03 | 3 | EMAAR-Pkg#162/163- Marassi3 | 547130.31 | 3055521.3155 | 873718.3 | 3929239.6155
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .14 | 14 | Benban 3/ Toshka 2 LOT 414 | 4391685.55 | 3561657.15 | 461126.98 | 4022784.13
El-Moneeb Bridge | IPC#1 | 1 | El-Moneeb Bridge1 | 1345000 | 1221940 | 0 | 1221940
IKEA Extension MoA | IKEA-IPC10 | 10 | IKEA Extension MoA10 | 16241435.02 | 10892925.95 | 3871917.19 | 14764843.14
AWEER POWER STATION 'H' Phase | Con-015 | 15 | AWEER POWER STATION 'H' Phase15 | 1277689.64 | 1263493 | 0 | 1263493
El Katameya Mall | inv(14 ) 10-2020 | 14 | El Katameya Mall14 | 125160 | 105711.42 | 0 | 105711.42
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 1 | 1 | Nagaa Hamady/Assuit OHTL1 | 17444824.76 | 13444963.31 | 1831706.6 | 15276669.91
DoubleTree Mangroovy ElGouna | MANGROVE-IPC10 | 10 | DoubleTree Mangroovy ElGouna10 | 1714004.8 | 1173489.49 | 449926.27 | 1623415.76
Rail Way Tunnel Zagazig | IPC#1 | 1 | Rail Way Tunnel Zagazig1 | 714780 | 666174.96 | 0 | 666174.96
Mauritania-Lot 2 | Inv.6 – Lot 2 | 6 | Mauritania-Lot 26 | 446297.21 | 422283.94 | 0 | 424071.74
Cairo-Alex Railway | Cairo-alex ipc32 | 32 | Cairo-Alex Railway32 | 33689843.81 | 1706221.9 | 3537433.6 | 5243655.5
Cairo-Alex Railway | cairo-alex ipc 25 | 25 | Cairo-Alex Railway25 | 3085109.98 | 1937782.079 | 323936.55 | 2261718.629
Cairo-Alex Railway | cairo-alex ipc22 | 22 | Cairo-Alex Railway22 | 19703504.7 | 13469137.195 | 2068867.99 | 15538005.185
Cairo-Alex Railway | cairo-alex ipc21 | 21 | Cairo-Alex Railway21 | 81561902.6 | 56387458.34 | 8563999.77 | 64951458.11
Cairo-Alex Railway | CAIRO-ALEX IPC18 | 18 | Cairo-Alex Railway18 | 17641968.1 | 12140086.085 | 1852406.65 | 13992492.735
Cairo-Alex Railway | Cairo-Alex IPC014 | 14 | Cairo-Alex Railway14 | 7078617 | 4915700.63 | 743254.8 | 5658955.43
Cairo-Alex Railway | Cairo-Alex IPC09 | 9 | Cairo-Alex Railway9 | 26297538.1 | 19182714.45 | 2629753.81 | 21812468.26
Sodic East | IPC_15_Rowad_SEast |  | Sodic East | 529135.77 | 468842.81 | 0 | 468842.81
Racecores 3092-17 132KV E | 11640 |  | Racecores 3092-17 132KV E | 96835.365 | 80373.3332 | 0 | 80373.3332
Racecores 3092-17 132KV E | 11288 |  | Racecores 3092-17 132KV E | 244946 | 203305.18 | 0 | 203305.18
Racecores 3092-17 132KV E | 10949 |  | Racecores 3092-17 132KV E | 203062.68 | 343175.94 | 0 | 171587.97
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.6 | 6 | Nagaa Hamady/Assuit OHTL6 | 281761.9 | 159480.24 | 29585 | 189065.24
SHAT Al ARAB 400/132kV SS | 370 |  | SHAT Al ARAB 400/132kV SS | 2193735.91 | 2193735.91 | 0 | 2193735.91
LAYYAH CCPP | 493 |  | LAYYAH CCPP | 15425640 | 13051321.5 | 2995810 | 16047131.5
Lekela 250MW Wind Farm | LEKELA-IPC10 | 10 | Lekela 250MW Wind Farm10 | 24782925.38 | 21709399.519 | 4107306.79 | 25816706.309
ESU Ph2-Enabling & Struc | E.S.U 2-MEP-IPC09 | 9 | ESU Ph2-Enabling & Struc9 | 85288754.95 | 20493846.4475 | 13976306.88 | 34470153.3275
EMAAR-PKG#22-MARASSI | PKG#22-IPC FINAL |  | EMAAR-PKG#22-MARASSI | 558773.62 | 408194.001 | 0 | 408194.001
Latin Compound - New Alamin | inv ( 20) 9-12-2020 | 20 | Latin Compound - New Alamin20 | 1013339.6 | 619516.54 | 202667.92 | 822184.46
Museum of Egyp. Civilization | IPC#7 | 7 | Museum of Egyp. Civilization7 | 2175660 | 1990728.9 | 0 | 1990728.9
Ministries Buildings | MIN.FIT OUT-IPC02 | 2 | Ministries Buildings2 | 6142805.64 | 3865825 | 1309079.9 | 5174904.9
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC 17 | 17 | ORA ZED - Ph 01B - Pkgs A&D17 | 31100661.13 | 27837999.2465 | 3310918.88 | 31148918.1265
ORA ZED - Ph 01B - Pkgs A&D | ora zed ipc14 | 14 | ORA ZED - Ph 01B - Pkgs A&D14 | 45635766.95 | 38191818.9175 | 4547728.4 | 42739547.3175
ORA ZED - Ph 01B - Pkgs A&D | ORa zed ipc13 | 13 | ORA ZED - Ph 01B - Pkgs A&D13 | 30511414.97 | 25426794.8085 | 3025284.37 | 28452079.1785
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED PH1 IPC010 | 10 | ORA ZED - Ph 01B - Pkgs A&D10 | 32858070.07 | 30886238.8435 | 3677026.6 | 34563265.4435
ORA ZED - Ph 01B - Pkgs A&D | Ora Zed IPC08 | 8 | ORA ZED - Ph 01B - Pkgs A&D8 | 26950096.62 | 25931572.791 | 3088483.39 | 29020056.181
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED 1- IPC02 | 2 | ORA ZED - Ph 01B - Pkgs A&D2 | 45205416.45 | 39936351.7025 | 4807707.27 | 44744058.9725
Vila Fabio (North Coast) | IPC-Fabio |  | Vila Fabio (North Coast) | 42750 | 42750 | 0 | 42750
IKEA Extension MoA | IKEA - IPC11 | 11 | IKEA Extension MoA11 | 40022086.82 | 16989482.64 | 6710363.39 | 23699846.03
Angola Emergency fast-track | ANG-Mor-Inv 5 - Ints | 5 | Angola Emergency fast-track5 | 3773923.09 | 2512234.44 | 0 | 2512234.44
Toshka GIS 500 kV | Toshka Sub Inv. 12 $ | 12 | Toshka GIS 500 kV12 | 234441.9 | 142577.6 | 61541 | 204118.6
Toshka GIS 500 kV | Toshka Sub Inv. 09 $ | 9 | Toshka GIS 500 kV9 | 86989.71 | 49666.56 | 22834.8 | 72501.36
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .9 | 9 | Benban 3/ Toshka 2 LOT 49 | 25121385.67 | 20622939.37 | 2637525.02 | 23262564.09
Asher Mn Ramadan Bridge No2 | 10M RMADAN BRIDGE-01 | 1 | Asher Mn Ramadan Bridge No21 | 72699012 | 9442270 | 7235771.2 | 64034869.2
AWEER POWER STATION 'H' Phase | Con-017 | 17 | AWEER POWER STATION 'H' Phase17 | 958273.98 | 947554.6784 | 0 | 947554.6784
Miscellaneous Projects | 2009210014 |  | Miscellaneous Projects | 204326.74 | 232932.48 | 0 | 232932.48
10th of Ramadan Railway | IPC#7 - HAC | 7 | 10th of Ramadan Railway7 | 940625 | 118618.24 | 0 | 118618.24
10th of Ramadan Railway | IPC#5 10 of Ramadan | 5 | 10th of Ramadan Railway5 | 454041 | 430203.85 | 0 | 430203.85
SHATRA 400/132kV SS | 375 |  | SHATRA 400/132kV SS | 904185.84 | 904185.84 | 0 | 904185.84
MOTHANA 400/132kV SS | 384 |  | MOTHANA 400/132kV SS | 268815.46 | 268815.46 | 0 | 268815.46
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $7 | 7 | Benban 3/ Toshka 2 LOT 47 | 226619.37 | 187860.59 | 23795.03 | 211655.62
Minis Building(Polyurethane) | IPC_16_Rowad_Poly |  | Minis Building(Polyurethane) | 59220.7 | 52706.41 | 0 | 52706.41
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC09 | 9 | EMAAR-Pkg#162/163- Marassi9 | 10891648.49 | 12697982.5806 | 1240035.07 | 13938017.6506
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC10 | 10 | EMAAR-Pkg#162/163- Marassi10 | 14574675.04 | 14201933.972 | 413306.08 | 14615240.052
Assuit PP (CP-118) | 2012210002 |  | Assuit PP (CP-118) | 204766.04 | 174051.1283 | 30714.91 | 204766.0383
Museum of Egyp. Civilization | IPC#2 PhaseII | 2 | Museum of Egyp. Civilization2 | 446310 | 408373.65 | 0 | 408373.65
RING ROAD MARYOTIA EXPANSION | Marytia-R-R-IPC01* | 1 | RING ROAD MARYOTIA EXPANSION1 | 153919.35 | 153919.33 | 0 | 153919.33
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .2 | 2 | Benban 3/ Toshka 2 LOT 42 | 17605222.78 | 12222792.55 | 1848548.39 | 14071340.94
Minis Building(Polyurethane) | IPC_17_Rowad_Roly | 17 | Minis Building(Polyurethane)17 | 143610.5 | 127813.33 | 0 | 127813.33
Latin Compound - New Alamin | inv ( 25 )20/12/2020 | 25 | Latin Compound - New Alamin25 | 592631.2 | 389051.75 | 115432.27 | 504484.02
ElSewedy HQ Internal Finishing | elsewedy HQ-IPC04 | 4 | ElSewedy HQ Internal Finishing4 | 11480730.19 | 7530697.05 | 3180833.19 | 10996640.92
El-Nyaba El-Ama | El-Nayba Inv. 1 | 1 | El-Nyaba El-Ama1 | 777826 | 630455.08 | 58336.95 | 688792.03
Port Said Subs 220/66 | Port Said Inv. 1 | 1 | Port Said Subs 220/661 | 96480795.67 | 62748290 | 24120198.92 | 86868488.92
Berket Ghelion | Inv.21 Final Ghelion | 21 | Berket Ghelion21 | 1125841.04 | 669738.6 | 281461.1005 | 951199.7005
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 01 | 1 | Toshka-04 GIS Substation1 | 16439400.55 | 14658355.1 | 1726137.06 | 16384492.16
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 04 | 4 | Suez Gulf/S4 - 500KV OHTL4 | 5712160.88 | 4346940.88 | 599776.89 | 4946717.77
ORA-ZED Towers01B | IPC_1_Rowad_Ora | 1 | ORA-ZED Towers01B1 | 191179.09 | 164127.27 | 0 | 164127.27
Ministries Buildings | MIN.ELCTROM-IPC03 | 3 | Ministries Buildings3 | 104773160.9 | 30488417.99 | 14162802 | 88751987.99
Ministries Buildings | MIN-ANASER SAHY-IPC1 | 1 | Ministries Buildings1 | 1854632 | 273930 | 1205839.96 | 1479769.96
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 02 | 2 | Suez Gulf/S4 - 500KV OHTL2 | 80012 | 60874.24 | 8401.26 | 69275.5
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $8 | 8 | Benban 3/ Toshka 2 LOT 48 | 168773.68 | 133050.03 | 17721.24 | 150771.27
33KV Canal Farm Grid | Inv. 03 Farm | 3 | 33KV Canal Farm Grid3 | 29404681.7 | 23229284.27 | 4410702.26 | 27639986.53
33KV Canal Farm Grid | Inv. 06 Farm | 6 | 33KV Canal Farm Grid6 | 21870002.84 | 17277302.24 | 3280500.43 | 20557802.67
33KV Canal Farm Grid | Inv. 02 Farm | 2 | 33KV Canal Farm Grid2 | 25824875.03 | 20401651.28 | 3873731.25 | 24275382.53
Canal Sugar S/s | Inv 7 Sugar S/s | 7 | Canal Sugar S/s7 | 13488150.68 | 10655639.03 | 2023222.6 | 12678861.63
Canal Sugar S/s | Inv 5 Sugar S/s | 5 | Canal Sugar S/s5 | 7656082.15 | 6048304.9 | 1148412.32 | 7196717.22
DPW Onshore Port & Terminal | DP WORLD-IPC21 | 21 | DPW Onshore Port & Terminal21 | 34792442.42 | 25746407.4 | 5218866.36 | 30965273.76
Kattameya Creeks | Katamya Creeks ipc41 | 41 | Kattameya Creeks41 | 44558913.7 | 45340679.808 | 818731.44 | 46159411.248
Kattameya Creeks | Katameya ipc 29 | 29 | Kattameya Creeks29 | 40212630.08 | 40904481 | 704758.51 | 41609239.51
Kattameya Creeks | katameya IPC 28 | 28 | Kattameya Creeks28 | 28889381.89 | 28650459 | 1394498.15 | 30044957.15
Kattameya Creeks | katameya ipc15 | 15 | Kattameya Creeks15 | 51903318.98 | 49567394.569 | 4401937.17 | 53969331.739
Kattameya Creeks | Katmeya Creeks IPC08 | 8 | Kattameya Creeks8 | 43370006.73 | 40343227.9665 | 4506979.03 | 44850206.9965
Taval Sarai 52 | IPC_5_Gama_Salary | 5 | Taval Sarai 525 | 251219 | 157993.34 | 0 | 157993.34
Azab Tex Factory | inv ( 2 ) 18-2-2021 | 2 | Azab Tex Factory2 | 651000 | 627575 | 0 | 627575
Lahoon 220/22/22 | Al-Lahoon Sub Inv 03 | 3 | Lahoon 220/22/223 | 47309215.98 | 30408055.58 | 12288108.05 | 42696163.63
MR3 Bridge L&L | MR3L&L-IPC1FINAL | 1 | MR3 Bridge L&L1 | 1778990.75 | 714789.99 | 714792.5 | 1429582.49
Royal City | ROYAL CITY-IPC37 | 37 | Royal City37 | 8335559.1 | 3663301.675 | 0 | 3663301.675
Beni Suef Substation R61 | BSF-CW-EGP-17 FINAL | 17 | Beni Suef Substation R6117 | 664622.04 | 8495990.66 | 0 | 8495990.66
2B3 | IPC-1-2B3 | 1 | 2B31 | 75000 | 75000 | 0 | 75000
Mivida | IPC_5_Mivida | 5 | Mivida5 | 121130 | 119918.7 | 0 | 119918.7
AWEER POWER STATION 'H' Phase | IMP-063 | 63 | AWEER POWER STATION 'H' Phase63 | 1050051.08 | 892543.4118 | 116672.34 | 1009215.7518
Mangrouve Hotel - Gouna | IPC_3_RME_Gouna | 3 | Mangrouve Hotel - Gouna3 | 20276.74 | 17955.04 | 0 | 17955.04
ORA-ZED Towers01B | IPC_3_Rowad_ORA | 3 | ORA-ZED Towers01B3 | 100289.08 | 86098.18 | 0 | 86098.18
ORA-ZED Towers01B | IPC_2_Rowad_ORA | 2 | ORA-ZED Towers01B2 | 111198.38 | 95463.81 | 0 | 95463.81
Miscellaneous Projects | 2007210003 |  | Miscellaneous Projects | 34725 | 39239.25 | 0 | 39239.25
EMAAR-PKG# 144, Marassi | PKG#144 - IPC12 | 12 | EMAAR-PKG# 144, Marassi12 | 34831219.06 | 32281831.2825 | 4027726.64 | 36309557.9225
SHAT Al ARAB 400/132kV SS | 385 |  | SHAT Al ARAB 400/132kV SS | 4555728.68 | 4555728.68 | 0 | 4555728.68
MAYSAN 400/132kV SS | 389 |  | MAYSAN 400/132kV SS | 29634.24 | 29634.24 | 0 | 29634.24
ITS | Adv.Adv.ITS Inv. 01 | 1 | ITS1 | 8999900 | 8999900 | 0 | 8999900
Suez Bridge | 1st & FPC |  | Suez Bridge | 193930 | 188112.1 | 0 | 188112.1
Coastal road Bridge Extension | IPC#6 Coastal Road | 6 | Coastal road Bridge Extension6 | 277830 | 243050.29 | 0 | 243050.29
El Boghaz Brigde | IPC#25 | 25 | El Boghaz Brigde25 | 621372.66 | 584090.3 | 0 | 584090.3
Koning Food V2 - LP-08-20 | 8 |  | Koning Food V2 - LP-08-20 | 54070.17 | 61640 | 0 | 61640
LAYYAH CCPP | 497 |  | LAYYAH CCPP | 10252020 | 8674025.85 | 1991043 | 10665068.85
BKG#178-Lagoon Discharge | PKG #178 IPC04 | 4 | BKG#178-Lagoon Discharge4 | 8636178.5 | 6473613.265 | 785199.97 | 7258813.235
Angola Emergency fast-track | ANG-Mor-Inv 6 - Ints | 6 | Angola Emergency fast-track6 | 734052.88 | 511511.17 | 0 | 511511.17
Babil WBS | 200123 |  | Babil WBS | 24800 | 24552 | 0 | 24552
Miscellaneous Projects | 2006210006 |  | Miscellaneous Projects | 4499.71 | 4994.6794 | 0 | 4994.6794
Hassan El Mamoun Bridge | م 1 كوبرى حسن المأمو | 1 | Hassan El Mamoun Bridge1 | 67928433.82 | 6575875 | 6575893.7 | 49850608.7
LRT Project | IPC_3_LRT | 3 | LRT Project3 | 56100 | 47488.65 | 0 | 47488.65
DoubleTree Mangroovy ElGouna | MANGROVE WALL-IPC4 | 4 | DoubleTree Mangroovy ElGouna4 | 8100 | 8424 | 0 | 8424
DPW Onshore Port & Terminal | DP WORLD-IPC23 | 23 | DPW Onshore Port & Terminal23 | 35871966.38 | 26545255.12 | 5380794.96 | 31926050.08
Latin Compound - New Alamin | inv ( 23 )15-12-2020 | 23 | Latin Compound - New Alamin23 | 747986.4 | 481829.36 | 149597.28 | 631426.64
Taval Sarai 52 | tr0025 |  | Taval Sarai 52 | 296812.8 | 234483.03 | 0 | 234483.03
Olympic Multi – Sports Hall | OLYMPIC-IPC03 | 3 | Olympic Multi – Sports Hall3 | 36935466.2 | 2493330 | 19395007.75 | 31381672.5
EGAT Pelletizing Plant | Elco EGAT-IPC17 | 17 | EGAT Pelletizing Plant17 | 20596124.76 | 0 | 0 | 21625930.998
LRT | IPC#2 - LRT | 2 | LRT2 | 1101240 | 998205.6 | 0 | 998205.6
Coastal road Bridge Extension | IPC#1 | 1 | Coastal road Bridge Extension1 | 1811040 | 1742136.52 | 0 | 1742136.52
IKEA Extension MoA | IKEA-IPC08 | 8 | IKEA Extension MoA8 | 18401730.5 | 13497644.42 | 8132475 | 21630119.42
IKEA Extension MoA | IKEA - IPC07 | 7 | IKEA Extension MoA7 | 9400137.01 | 6567550.07 | 1919443.91 | 8486993.98
Royal City | ROYAL CITY-IPC39 | 39 | Royal City39 | 1409870.69 | 872368.1645 | 0 | 872368.1645
Latin Compound - New Alamin | inv ( 17 ) 3-12-2020 | 17 | Latin Compound - New Alamin17 | 648309.2 | 416637.65 | 129661.84 | 546299.49
Oasis Buildings- New Capital | Inv(7)270820 | 7 | Oasis Buildings- New Capital7 | 1347725 | 1264758.63 | 0 | 1264758.63
MOTHANA 400/132kV SS | 394 |  | MOTHANA 400/132kV SS | 22225.68 | 22225.68 | 0 | 22225.68
SHATRA 400/132kV SS | 396 |  | SHATRA 400/132kV SS | 1283093.03 | 1283093.03 | 0 | 1283093.03
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $4 | 4 | Benban 3/ Toshka 2 LOT 44 | 442325.83 | 363503.98 | 46444.21 | 409948.19
West Port Said 220 kV GIS | P-45-Portsaid Inv.01 | 1 | West Port Said 220 kV GIS1 | 72911614.29 | 54165616.26 | 7655719.5 | 61821335.76
New Babil 400/132KV Substation | 2103210004 |  | New Babil 400/132KV Substation | 286636.43 | 286636.43 | 0 | 286636.43
National Batteries LP-05-20 | 21 |  | National Batteries LP-05-20 | 1157895 | 683539.125 | 330000.245 | 1013539.37
EDNC Retail & Offices Civil | Sodic Soreal IPC025 | 25 | EDNC Retail & Offices Civil25 | 29789862.02 | 22686187.95 | 2622078.36 | 25308266.31
Museum of Egyp. Civilization | IPC#4 PII | 4 | Museum of Egyp. Civilization4 | 151118.5 | 151118.5 | 0 | 151118.5
NUCA R05 - Z02 | R5-IPC25 | 25 | NUCA R05 - Z0225 | 20378846.31 | 18194731.96 | 2191402.15 | 20386134.11
Kattameya Creeks | KATAMEYA CREEKS-IPC1 | 1 | Kattameya Creeks1 | 2919397.4 | 2748675.4515 | 287497.83 | 3036173.2815
CFC Podium 2 | CFC-IPC15 | 15 | CFC Podium 215 | 42273319.3 | 40379659.08 | 7601026.25 | 47980685.33
EMAAR-Pkg#162/163- Marassi | PKG162#IPC12 | 12 | EMAAR-Pkg#162/163- Marassi12 | 7499598.77 | 5549152.6804 | 0 | 5549152.6804
Maspiro Towers | IPC#4 | 4 | Maspiro Towers4 | 424000 | 419760 | 0 | 419760
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC01 | 1 | ElSewedy HQ Internal Finishing1 | 1435679.43 | 6886276.98 | 715.5 | 6886992.48
LAYAN Substation | 10466 |  | LAYAN Substation | 619583.3862 | 2094191.84 | 0 | 523547.96
LAYAN Substation | 10465 |  | LAYAN Substation | 31077.615 | 52521.16 | 0 | 26260.58
LAYAN Substation | 10463 |  | LAYAN Substation | 4591717.47 | 3811125.5 | 0 | 3811125.5
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 01 | 1 | Suez Gulf/S4 - 500KV OHTL1 | 76552.57 | 64304.16 | 8038.02 | 72342.18
Zone(J) South Valley Toshka | South Valley Inv. 09 | 9 | Zone(J) South Valley Toshka9 | 54493670 | 40318258.45 | 6975189.81 | 47293448.26
Zone(J) South Valley Toshka | South Valley Inv. 03 | 3 | Zone(J) South Valley Toshka3 | 60204591 | 45875011.95 | 7706449.05 | 53581461
Zone(J) South Valley Toshka | South Valley Inv. 02 | 2 | Zone(J) South Valley Toshka2 | 53192168.25 | 40508508.25 | 6808336.2 | 47316844.45
4 SS - Technical Service | 406 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHAT Al ARAB 400/132kV SS | 391 |  | SHAT Al ARAB 400/132kV SS | 998346.38 | 998346.38 | 0 | 998346.38
MOTHANA 400/132kV SS | 403 |  | MOTHANA 400/132kV SS | 486033.93 | 486033.93 | 0 | 486033.93
NUCA R05 - Z02 | R5-IPC24 | 24 | NUCA R05 - Z0224 | 25733237.29 | 20726444.04 | 2611761.25 | 23338205.29
Angola Emergency fast-track | ANG-Cam-Inv 4 | 4 | Angola Emergency fast-track4 | 22812526.63 | 17352918.87 | 0 | 17352918.87
Ahl Misr Walkway | IPC#2 Ahl Misr | 2 | Ahl Misr Walkway2 | 894212 | 841821.26 | 0 | 841821.26
Koning Food V3 LP-09-20 | 18 |  | Koning Food V3 LP-09-20 | 3907.02 | 2227.02 | 2227 | 4454.02
Koning Food V3 LP-09-20 | 17 |  | Koning Food V3 LP-09-20 | 99912.28 | 56950 | 56950 | 113900
Ministries Buildings | MIN-SHELL-IPC07 | 7 | Ministries Buildings7 | 8605109.8 | 2174820.01 | 5074580.45 | 7249400.46
GOV2 - Infra | GOV 2 IPC 27+28 | 27 | GOV2 - Infra27 | 8993472.71 | 0 | 184362.78 | 184362.78
GOV2 - Infra | GOV2 IPC06 | 6 | GOV2 - Infra6 | 7370174.33 | 52077106.78 | 6103720.7 | 58180827.48
Mohamed Ali Palace | IPC_6_MohamedAli | 6 | Mohamed Ali Palace6 | 73816.4 | 62005.78 | 0 | 62005.78
Royal City | ROYAL CITY-IPC40 | 40 | Royal City40 | 7356711.98 | 5481051.519 | 0 | 5481051.519
R5 | inv(9)300620 | 9 | R59 | 754500 | 113175 | 0 | 683331.88
Elsewedy Univ - Enabling Works | sewedy uni-mep-08 | 8 | Elsewedy Univ - Enabling Works8 | 1755356.86 | 2678875.465 | 120962.58 | 2799838.045
Corporate Project LP-02-21 | 39 |  | Corporate Project LP-02-21 | 224640.7 | 175270.05 | 80820.35 | 256090.4
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC013 | 13 | EMAAR-Pkg#162/163- Marassi13 | 0.001 | 4564491.481 | 548962.38 | 5113453.861
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC012 | 12 | EMAAR-Pkg#162/163- Marassi12 | 17538268.49 | 12621618.3045 | 1517977.12 | 14139595.4245
CFC Podium 2 | CFC - IPC018 | 18 | CFC Podium 218 | 16880809.49 | 12196441.12 | 3936267.26 | 16132708.38
Industria Sadat | Sadat Indust Inv. 01 | 1 | Industria Sadat1 | 22759251.19 | 26600720.6 | 2531453.9 | 29132174.5
Akhmem - Qena | Inv.5 Qena Akhmem | 5 | Akhmem - Qena5 | 66637833.28 | 39649510.79 | 9995674.99 | 49645185.78
Toshka GIS 500 kV | Toshka Sub Inv. 06 | 6 | Toshka GIS 500 kV6 | 49689283.81 | 28279012.91 | 13043437 | 41322449.91
Akhmem Assiut | Ref.Ret Asuit akh |  | Akhmem Assiut | 10000000 | 10000000 | 0 | 10000000
Al Montaza Hotels - Alexandria | Inv ( 1 ) montazha | 1 | Al Montaza Hotels - Alexandria1 | 555104 | 555104 | 0 | 555104
GOV2 - Infra | Gov2 ipc 17 | 17 | GOV2 - Infra17 | 583461.9 | 145061.2825 | 32128.34 | 177189.6225
GOV2 - Infra | GOV 2 IPC08 | 8 | GOV2 - Infra8 | 51149312.9 | 17404967.45 | 2733165.6 | 20138133.05
Miscellaneous Projects | 2103210008 |  | Miscellaneous Projects | 57114.88 | 65110.9629 | 0 | 65110.9629
Miscellaneous Projects | 2103210007 |  | Miscellaneous Projects | 62144 | 70844.16 | 0 | 70844.16
Bridge Axis Firdaws | inv- ( 1 ) |  | Bridge Axis Firdaws | 4225600 | 4225600 | 0 | 4225600
UIC Project (LP-04-21) | 58 |  | UIC Project (LP-04-21) | 48750 | 0 | 0 | 48750
Coastal road Bridge Extension | IPC#4 | 4 | Coastal road Bridge Extension4 | 1400726.25 | 1348899.38 | 0 | 1348899.38
Cairo Monorail - 6th October | IPC#1 - Monorail | 1 | Cairo Monorail - 6th October1 | 2708300 | 2708300 | 0 | 2708300
ORA ZED - Ph 01B - Pkgs A&D | ora zed ph1 ipc11 | 11 | ORA ZED - Ph 01B - Pkgs A&D11 | 34769848.6 | 33022101.84 | 3931072.58 | 36953174.42
ORA ZED-Ph 2-Pkgs A&D | ora Zed2-ipc01 | 1 | ORA ZED-Ph 2-Pkgs A&D1 | 13196047.2 | 15456194.14 | 1838980.61 | 17295174.75
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED Ph1 IPC06 | 6 | ORA ZED - Ph 01B - Pkgs A&D6 | 13829636.33 | 4832623.5365 | 577003.05 | 5409626.5865
Bahr ElBakar – Power Station | IPC#07 -Madkour | 7 | Bahr ElBakar – Power Station7 | 3172890 | 0 | 0 | 3172890
Bahr ElBakar – Power Station | IPC#4 - Madkour | 4 | Bahr ElBakar – Power Station4 | 2706288 | 2679225.12 | 0 | 2679225.12
Bahr ElBakar – Power Station | IPC#1 - Madkour | 1 | Bahr ElBakar – Power Station1 | 1380900 | 1143553.68 | 0 | 1143553.68
Shenzo Aby Bridge - Haggana | IPC#1 Shenzo Aby | 1 | Shenzo Aby Bridge - Haggana1 | 1390700 | 1265346.25 | 0 | 1265346.25
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC02 | 2 | EMAAR-Pkg#162/163- Marassi2 | 8478947.03 | 10179304.7515 | 1304738.06 | 11484042.8115
Mauritania Lot 1 | Inv.16 - Lot 1 | 16 | Mauritania Lot 116 | 497882 | 425674.36 | 0 | 475462.56
Mauritania Lot 1 | Inv.11 - Lot 1 | 11 | Mauritania Lot 111 | 497200 | 472323 | 0 | 472323
Mauritania Lot 1 | Inv.10 - Lot 1 | 10 | Mauritania Lot 110 | 1318961.79 | 1252998.71 | 0 | 1252998.71
Mauritania Lot 1 | Inv.3 - Lot 1 | 3 | Mauritania Lot 13 | 1276811.56 | 1212955.98 | 0 | 1212955.98
Mauritania-Lot 2 | Inv. 9 – Lot 2 | 9 | Mauritania-Lot 29 | 2395607.55 | 2275827.17 | 0 | 2275827.17
Mauritania-Lot 2 | Inv.1 - Lot 2 | 1 | Mauritania-Lot 21 | 71899.6 | 68304.62 | 0 | 68304.62
Mauritania-Lot 2 | Inv.5 – Lot 2 | 5 | Mauritania-Lot 25 | 1284803.55 | 1220563.37 | 0 | 1220563.37
Mauritania-Lot 2 | Inv. 10 – Lot 2 | 10 | Mauritania-Lot 210 | 41450.37 | 39377.85 | 0 | 39377.85
Mauritania-Lot 2 | Inv. 8 – Lot 2 | 8 | Mauritania-Lot 28 | 52491.74 | 49867.15 | 0 | 49867.15
Mauritania-Lot 2 | Inv.2 - Lot 2 | 2 | Mauritania-Lot 22 | 622044.98 | 590942.73 | 0 | 590942.73
Angola Emergency fast-track | ANG-Mor-Inv 6 | 6 | Angola Emergency fast-track6 | 1858950 | 1295368.14 | 0 | 1295368.14
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.02 | 2 | Toshka 2/Owinat East LOT2 OHTL2 | 20597393.87 | 18372485.06 | 2162726.36 | 20535211.42
BKG#178-Lagoon Discharge | PKG#178-IPC03 | 3 | BKG#178-Lagoon Discharge3 | 7805724.83 | 7952024.0415 | 860581.16 | 8812605.2015
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC023 | 23 | EMAAR-PKG# 101-UPTOWN23 | 2544618.3 | 594123.335 | 1279165.17 | 1873288.505
Lekela 250MW Wind Farm | LEKELA-IPC11 | 11 | Lekela 250MW Wind Farm11 | 16648813.83 | 14823033.5915 | 2531638.98 | 17354672.5715
Nuweibaa (Swro) | 2104210002 |  | Nuweibaa (Swro) | 95628.61 | 76502.89 | 19125.72 | 95628.61
Miscellaneous Projects | 2105210017 |  | Miscellaneous Projects | 250000 | 285000 | 0 | 285000
Industria Sadat | Sadat Indust Inv. 02 | 2 | Industria Sadat2 | 27642440.51 | 13234888.76 | 528023.86 | 36658109.81
Akhmem - Qena | Inv.32 Akhmem Qena | 32 | Akhmem - Qena32 | 2008162.56 | 1596489.25 | 301224.38 | 1897713.63
Akhmem - Qena | Inv.21 Qena - Akhmem | 21 | Akhmem - Qena21 | 458158.19 | 364235.76 | 68723.73 | 432959.49
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC012 | 12 | EMAAR-Pkg#162/163- Marassi12 | 3268183.05 | 3176493.7925 | 650200.29 | 3826694.0825
Diplomatic District - Infra | Diplomatic ipc15 | 15 | Diplomatic District - Infra15 | 19671467.57 | 13848783.6757 | 2013157.2 | 15861940.8757
Diplomatic District - Infra | diplomatic ipc11 | 11 | Diplomatic District - Infra11 | 40616631.67 | 33118965.0735 | 4420746.2 | 37539711.2735
Air Force Project | Air Force Inv . 16 | 16 | Air Force Project16 | 34679470.06 | 19300720 | 14199224.58 | 33499944.58
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC016 | 16 | EMAAR-Pkg#162/163- Marassi16 | 49248459.94 | 11495751.178 | 35033674.049 | 46529425.227
Asher Mn Ramadan Bridge No2 | ALAASHER BRIDGE-FINA |  | Asher Mn Ramadan Bridge No2 | 11622150.08 | 7626410 | 7076659 | 14703069
Faculty of Medicine | mansora ipc11 | 11 | Faculty of Medicine11 | 6950534.29 | 5880793.8545 | 347526.71 | 6228320.5645
Faculty of Medicine | Mansoura UNI IPC05 | 5 | Faculty of Medicine5 | 20306602.86 | 17182030.01 | 1015330.14 | 18197360.15
Faculty of Medicine | Mansoura Uni IPC02 | 2 | Faculty of Medicine2 | 13705788.32 | 11596749 | 685289.42 | 12282038.42
NUCA R05 - Z02 | R5 FINSHING-IPC02 | 2 | NUCA R05 - Z022 | 4570313.65 | 4124306.65 | 0 | 4124306.65
NUCA R05 - Z02 | R5 - IPC15 | 15 | NUCA R05 - Z0215 | 48673674 | 47390161.3 | 5828144.4 | 53218305.7
R5 Mix-Use Complex Project | R5-ZONE1-IPC04 | 4 | R5 Mix-Use Complex Project4 | 4897147.5 | 3771309.275 | 471420.92 | 4242730.195
October Dry Port | Dry Port Inv. 10 | 10 | October Dry Port10 | 9358947.94 | 6331059.12 | 2456723.84 | 8787782.96
GOV2 - Infra | Gov2 ipc 21+22 | 21 | GOV2 - Infra21 | 41093940.1 | 23795284.2259 | 3851424.58 | 27646708.8059
GOV2 - Infra | gov2 ipc 20 | 20 | GOV2 - Infra20 | 21567902.14 | 11507176.8086 | 1684882.83 | 13192059.6386
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 1 | 1 | Marsa Alam/ Bernes LOT2 OHTL1 | 2753615.85 | 1733413.48 | 289129.66 | 2022543.14
RING ROAD MARYOTIA EXPANSION | Maryotya IPC07 | 7 | RING ROAD MARYOTIA EXPANSION7 | 7591896.43 | 2515964.776 | 5000000 | 7515964.776
RING ROAD MARYOTIA EXPANSION | Maryotya IPC06 | 6 | RING ROAD MARYOTIA EXPANSION6 | 9909425.48 | 5875866.974 | 0 | 5875866.974
Taval Sarai 52 | IPC_10_Saray | 10 | Taval Sarai 5210 | 892512.2 | 678029.79 | 0 | 678029.79
October Dry Port | Dry Port Inv. 02 | 2 | October Dry Port2 | 543210.26 | 4515924.87 | 142592.69 | 4658517.56
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 07 | 7 | Hosh Essa 220 KV OHTL7 | 474026.67 | 284893.2 | 49772.8 | 334666
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 03 | 3 | Hosh Essa 220 KV OHTL3 | 9303701.3 | 5591524.8 | 976888.64 | 6568413.44
Toshka GIS 500 kV | Toshka Sub Inv. 21 $ | 21 | Toshka GIS 500 kV21 | 522242.54 | 328392.81 | 137088.67 | 465481.48
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC (44) | 44 | EMAAR-Pkg#162/163- Marassi44 | 54841445.41 | 19396451.9605 | 23114817.1 | 42511269.0605
EDNC Retail & Offices Civil | Sodic Soreal IPC029 | 29 | EDNC Retail & Offices Civil29 | 26258236.23 | 20811984.9815 | 0 | 20811984.9815
Coastal road Bridge Extension | IPC#4 - Gharably | 4 | Coastal road Bridge Extension4 | 1230941.25 | 1150131.37 | 0 | 1150131.37
AbuSultan Rd Bridge2 Extension | ELSAWEP-IPC01 | 1 | AbuSultan Rd Bridge2 Extension1 | 10957813.82 | 4381590 | 3830500 | 8212090
seashell Playa | IPC-4-PLAYA | 4 | seashell Playa4 | 92761.8 | 64757.004 | 14841.9 | 79598.904
marassi inland marina | FPC Marassi |  | marassi inland marina | 212142 | 0 | 0 | 14413.48
Capital One | inv ( 2 ) 1-8-2021 | 2 | Capital One2 | 460284.74 | 460284.74 | 0 | 460284.74
Bridge Axis Firdaws | INV ( 2 ) | 2 | Bridge Axis Firdaws2 | 820800 | 771552 | 0 | 771552
EGAT Pelletizing Plant | EGATpelletizingIPC19 | 19 | EGAT Pelletizing Plant19 | 20329650.19 | 19169766.1895 | 1973070.01 | 21142836.1995
NUCA R05 - Z02 | R05 IPC030 | 30 | NUCA R05 - Z0230 | 32070763.5 | 13912382.036 | 1902983.85 | 15815365.886
LAYYAH CCPP | 512 |  | LAYYAH CCPP | 7402941 | 6292499.85 | 1110441.15 | 7402941
10Th of Ramadan LRT | LRT 10Ramadan Inv.03 | 3 | 10Th of Ramadan LRT3 | 5789746.19 | 2460607.5 | 416709.28 | 4499970.18
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC014 | 14 | EMAAR-Pkg#162/163- Marassi14 | 13281620.94 | 11482913.077 | 3139654.64 | 14622567.717
NUCA R05 - Z02 | R05 Zone 2 IPC015 | 15 | NUCA R05 - Z0215 | 19873627.9 | 15888919.345 | 2003450.4 | 17892369.745
October Dry Port | Dry Port Inv. 01 | 1 | October Dry Port1 | 374166 | 3220148.37 | 98219.12 | 3318367.49
Angola Emergency fast-track | ANG-Mor-Inv.-7 | 7 | Angola Emergency fast-track7 | 11344616.16 | 5640030.45 | 0 | 5640030.45
Angola Emergency fast-track | ANG-Mor-Inv 4 | 4 | Angola Emergency fast-track4 | 11414314.93 | 7507137.74 | 0 | 7507137.74
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .26 | 26 | Benban 3/ Toshka 2 LOT 426 | 2767595.56 | 2468297.77 | 0 | 2468297.77
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .24 | 24 | Benban 3/ Toshka 2 LOT 424 | 4186616.13 | 3734064.31 | 0 | 3734064.31
CFC Podium 2 | CFC IPC021 | 21 | CFC Podium 221 | 23565050.79 | 19156725.1095 | 3655193.01 | 22811918.1195
AWEER POWER STATION 'H' Phase | CON/024 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.48 | 141966.52 | 1263502
AWEER POWER STATION 'H' Phase | ENG/042 |  | AWEER POWER STATION 'H' Phase | 344195.19 | 361404.9495 | 0 | 361404.9495
4 SS - Technical Service | 422 |  | 4 SS - Technical Service | 493890.57 | 493890.57 | 0 | 493890.57
Lahoon 220/22/22 | Al-Lahoon Sub Inv 02 | 2 | Lahoon 220/22/222 | 11588904.14 | 6845805.5 | 2766564.04 | 10135017.52
Miscellaneous Projects | 2007210009 |  | Miscellaneous Projects | 1111973.86 | 1267650.2004 | 0 | 1267650.2004
ORA ZED - Ph 01B - Pkgs A&D | Ora zed ph.1 IPC18 | 18 | ORA ZED - Ph 01B - Pkgs A&D18 | 9690075.24 | 7029281.442 | 836345.1 | 7865626.542
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC 16 | 16 | ORA ZED - Ph 01B - Pkgs A&D16 | 28676537.67 | 23357925.2135 | 2830326.27 | 26188251.4835
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc 27 | 27 | ORA ZED-Ph 2-Pkgs A&D27 | 6420474.62 | 5328993.921 | 674149.84 | 6003143.761
10th of Ramadan Railway | IPC#6 | 6 | 10th of Ramadan Railway6 | 932871 | 762121.31 | 0 | 762121.31
33KV Canal Farm Grid | Inv. 14 Farm | 14 | 33KV Canal Farm Grid14 | 15483945.5 | 11814250.42 | 2322591.83 | 14136842.25
RING ROAD MARYOTIA EXPANSION | El Marg IPC04 | 4 | RING ROAD MARYOTIA EXPANSION4 | 7006735.31 | 6191957.41 | 0 | 6191957.41
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC022 | 22 | EMAAR-PKG# 101-UPTOWN22 | 2547253.71 | 1912651.7855 | 836230.61 | 2748882.3955
LAYYAH CCPP | 514 |  | LAYYAH CCPP | 5428824 | 4614500.4 | 814323.6 | 5428824
New Babil 400/132KV GIS Substa | 2107210001 |  | New Babil 400/132KV GIS Substa | 444051.52 | 444051.52 | 0 | 444051.52
Faculty of Medicine | Mansoura UNI IPC04 | 4 | Faculty of Medicine4 | 10896948.57 | 9220050.36 | 544847.43 | 9764897.79
Cairo-Alex Railway | Railway IPC06 | 6 | Cairo-Alex Railway6 | 18621679.05 | 13109805.9125 | 1862167.9 | 14971973.8125
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC024 | 24 | EMAAR- Pkg 140-ITP-Mivida24 | 4573435.86 | 4604153.83 | 480210.76 | 5084364.59
Mansoura University | IPC#2 - Mansura Proj | 2 | Mansoura University2 | 808132.5 | 776190.97 | 0 | 776190.97
GOV2 - Infra | GOV 2 IPC07 | 7 | GOV2 - Infra7 | 15231382.33 | 21950412.282 | 2806208.25 | 24756620.532
TZ – Offshore E&M Procurement | 429 |  | TZ – Offshore E&M Procurement | 2181.32 | 1745.05 | 436.27 | 2181.32
P.I.Parks - Plot 10 | PIP indust Inv.01 | 1 | P.I.Parks - Plot 101 | 3919953.93 | 14845483.72 | 1878225.2 | 16723708.92
Group # 1 - 25 LX | Reailway PSP Inv. 05 | 5 | Group # 1 - 25 LX5 | 840000 | 831600 | 0 | 831600
Playa Resort | 21000005 |  | Playa Resort | 70034022.4 | 0 | 138667364.352 | 69333682.176
East Owainat 5 LOTS | East Owainat Inv.1 V | 1 | East Owainat 5 LOTS1 | 60208802.8 | 24091026.87 | 31609621.46 | 55700648.33
Museum of Egyp. Civilization | IPC#4 - Fianl Museum | 4 | Museum of Egyp. Civilization4 | 90000 | 82350 | 0 | 82350
Museum of Egyp. Civilization | FPC - Egy Museum |  | Museum of Egyp. Civilization | 519537.25 | 462531.51 | 0 | 462531.51
seashell Playa | IPC-3-PLAYA | 3 | seashell Playa3 | 66653.75 | 46530.9821 | 10664.6 | 57195.5821
El Salam Bridge | IPC#1 | 1 | El Salam Bridge1 | 2538210 | 2231281.07 | 0 | 2231281.07
Bahr ElBakar – Power Station | IPC02 Madkour | 2 | Bahr ElBakar – Power Station2 | 1357812 | 1344233.88 | 0 | 1344233.88
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 12 | 12 | Benban 500 K.V / 100 K.M12 | 87149410.25 | 70307183.38 | 9150688.08 | 79457871.46
Bridge Axis Firdaws | INV ( 4 ) | 4 | Bridge Axis Firdaws4 | 2505721.6 | 2355378.31 | 0 | 2355378.31
Transportation Hub | inv ( 1 ) T0020 | 1 | Transportation Hub1 | 2541840 | 2453890 | 0 | 2453890
Railway Bridge - Assuit | IPC#3 Assuit | 3 | Railway Bridge - Assuit3 | 1072500 | 571603.96 | 0 | 571603.96
ElSewedy HQ Internal Finishing | elsewedy hq-ipc06 | 6 | ElSewedy HQ Internal Finishing6 | 5418722.29 | 8157201.3445 | 1580547.38 | 14737748.7245
Racecores 3092-16 132KV C | 10903 |  | Racecores 3092-16 132KV C | 14571.84 | 12094.63 | 0 | 12094.63
ElMoneeb 2 | IPC#1 | 1 | ElMoneeb 21 | 677700 | 324903.16 | 0 | 670923
New Babil 400/132KV GIS Substa | 2107210003 |  | New Babil 400/132KV GIS Substa | 904549.4 | 904549.4 | 0 | 904549.4
New Babil 400/132KV GIS Substa | 2108210002 |  | New Babil 400/132KV GIS Substa | 1014974.91 | 1014974.91 | 0 | 1014974.91
MDF Factory | MDF IPC04 | 4 | MDF Factory4 | 9184332.61 | 8359615.9705 | 2410887.31 | 10770503.2805
Royal City | Royal city ipc (41) | 41 | Royal City41 | 6547385.9 | 5167630.645 | 0 | 5167630.645
Royal City | royal center ipc 22 | 22 | Royal City22 | 3302465.28 | 2767215.594 | 0 | 2767215.594
Ain Sokhna Port Development | IPC#04 - Sokhna Port | 4 | Ain Sokhna Port Development4 | 2140008 | 1963215.39 | 0 | 1963215.39
Ras El Teen Hangar | RasElTeenHangarIPC04 | 4 | Ras El Teen Hangar4 | 2573991.89 | 3007594.1505 | 42819.1 | 3050413.2505
Ras El Teen Hangar | Ras El Teen IPC03 | 3 | Ras El Teen Hangar3 | 2982066.9 | 1914188.735 | 939351.08 | 2853539.815
Ras El Teen Hangar | Ras El Teen IPC02 | 2 | Ras El Teen Hangar2 | 1926606.45 | 1843569.7125 | 0 | 1843569.7125
AMRIYA WWTP (3RD STAGE) | 220621002 |  | AMRIYA WWTP (3RD STAGE) | 4934047.47 | 4185828.48 | 493404.75 | 4801212.2
AMRIYA WWTP (3RD STAGE) | 220221003 |  | AMRIYA WWTP (3RD STAGE) | 2057234 | 1479111.1 | 411446.92 | 1933799.94
MDF Factory | MDF3- IPC 10 | 10 | MDF Factory10 | 4189749.3 | 3120120.2186 | 1044499.31 | 4164619.5286
MDF Factory | MDF FACTORY3 IPC 6+7 | 6 | MDF Factory6 | 3298482.11 | 2391399.5354 | 940067.4 | 3331466.9354
MDF Factory | MDF FACTORY3 IPC04 | 4 | MDF Factory4 | 785880.92 | 569763.6688 | 223976.06 | 793739.7288
MDF Factory | MDF FACTORY3 IPC02 | 2 | MDF Factory2 | 5118766.06 | 711105.3884 | 1458848.33 | 5169953.7184
Mar Girgis Church- R3 | IPC-1-Margirgs | 1 | Mar Girgis Church- R31 | 185600 | 185600 | 0 | 185600
ESU Ph2-Enabling & Struc | ESU2 MEP IPC-Final |  | ESU Ph2-Enabling & Struc | 14749060.76 | 35615959.8175 | 0 | 55309357.688
Museum of Egyp. Civilization | IPC#3 | 3 | Museum of Egyp. Civilization3 | 224307.5 | 206163.22 | 0 | 209943.665
Lekela 250MW Wind Farm | LEKELA-IPC08 | 8 | Lekela 250MW Wind Farm8 | 38206684.39 | 33513527.4795 | 6289039.17 | 39802566.6495
Capital One | inv ( 4 ) Captal 1 | 4 | Capital One4 | 788311.94 | 775825.97 | 0 | 775825.97
ENR-Signaling Inst. | ENR-Sign Inst Inv01 | 1 | ENR-Signaling Inst.1 | 1196205 | 1004812.57 | 119620.5 | 1124433.07
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.06 | 6 | Toshka 2/Owinat East LOT2 OHTL6 | 33344735.68 | 27992509.03 | 3501197.25 | 31493706.28
Cairo Monorail - 6th October | IPC#2 - Monorail | 2 | Cairo Monorail - 6th October2 | 1197000 | 1160780 | 0 | 1160780
10Th of Ramadan LRT | LRT 10Ramadan Inv.02 | 2 | 10Th of Ramadan LRT2 | 16485062.01 | 9190680.29 | 1496260.66 | 12209396.35
Al-Ula Towers | inv ( 2 ) ULA | 2 | Al-Ula Towers2 | 613093.2 | 637616.92 | 0 | 637616.92
Capital One | inv ( 6 ) Captal one | 6 | Capital One6 | 2030906.9 | 2010597.835 | 0 | 2010597.835
Toshka Farm | Toshka Farm Inv. 02 | 2 | Toshka Farm2 | 20313113.04 | 8632709.75 | 10664384.35 | 19297094.1
Angola Emergency fast-track | ANG-MOR-Inv 7 - Ints | 7 | Angola Emergency fast-track7 | 2363420.65 | 1231785.37 | 0 | 1231785.37
Angola Emergency fast-track | ANG-Cam-Inv 7 | 7 | Angola Emergency fast-track7 | 13411588.85 | 6782413.8 | 0 | 6782413.8
158E/2019 33kv Project | 10922 |  | 158E/2019 33kv Project | 430399.8608 | 451919.8538 | 0 | 451919.8538
Ahl Misr P3 – Zamalek Sector | IPC#3 Ahl Misr Zamal | 3 | Ahl Misr P3 – Zamalek Sector3 | 391500 | 375776.25 | 0 | 375776.25
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC08 | 8 | ElSewedy HQ Internal Finishing8 | 12855494 | 10012746.11 | 3360337.15 | 13373083.26
Kattameya Creeks | Katamya creeks ipc45 | 45 | Kattameya Creeks45 | 50790503.79 | 24274088.3716 | 28259040.56 | 52533128.9316
Kattameya Creeks | Katamya Creeks ipc44 | 44 | Kattameya Creeks44 | 34374886.21 | 8345106.3084 | 27116604.35 | 35461710.6584
Kattameya Creeks | katamye creeks ipc43 | 43 | Kattameya Creeks43 | 42016089.18 | 21224102 | 22275160.68 | 43499262.68
Kattameya Creeks | Katameya ipc 40 | 40 | Kattameya Creeks40 | 52383248.29 | 52039038 | 2137757.92 | 54176795.92
Kattameya Creeks | ipc27 katameya creek | 27 | Kattameya Creeks27 | 35445373.6 | 35452924 | 1410264.47 | 37664003.47
Kattameya Creeks | Katameya Creks IPC09 | 9 | Kattameya Creeks9 | 45658900.57 | 43056438.1785 | 4405818.41 | 47462256.5885
Ain Sokhna Bridge – RME | IPC#8 Sokhna Bridge | 8 | Ain Sokhna Bridge – RME8 | 1223300 | 907134.89 | 0 | 1124332.75
Ain Sokhna Bridge – RME | IPC#2 -Sokhna Bridge | 2 | Ain Sokhna Bridge – RME2 | 1012226.3 | 995406.31 | 0 | 995406.31
R06 Loack & Load | R6 L&L ipc1(final) | 1 | R06 Loack & Load1 | 1050000 | 997500 | 0 | 997500
Governmental Campus-N2 | 29 |  | Governmental Campus-N2 | 1024799.6 | 1024517.7776 | 0 | 1024517.7776
Governmental Campus-N2 | 31 |  | Governmental Campus-N2 | 2651.47 | 2601.1071 | 0 | 2601.1071
Governmental Campus-N2 | 30 |  | Governmental Campus-N2 | 18925.51 | 18872.8783 | 0 | 18872.8783
SHATRA 400/132kV SS | 433 |  | SHATRA 400/132kV SS | 38812.4 | 38812.4 | 0 | 38812.4
Waldorf Astoria Cairo | Astoria IPC8 | 8 | Waldorf Astoria Cairo8 | 9001222.98 | 2805915.699 | 2865083.61 | 5670999.309
Al Montaza Hotels - Alexandria | inv ( 4 ) montazha | 4 | Al Montaza Hotels - Alexandria4 | 1596381.5 | 1576281.5 | 0 | 1576281.5
Lekela 250MW Wind Farm | LEKELA IPC015 | 15 | Lekela 250MW Wind Farm15 | 15041907.67 | 8754195.8235 | 0 | 8754195.8235
New Babil 400/132KV GIS Substa | 2111210001 |  | New Babil 400/132KV GIS Substa | 1083109.8 | 1083109.8 | 0 | 1083109.8
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.09 | 9 | Toshka 2/Owinat East LOT2 OHTL9 | 1906856.72 | 1509835.43 | 200219.96 | 1710055.39
Ext.110 S. Military 220 Kv S/S | Extension kayn Inv 2 | 2 | Ext.110 S. Military 220 Kv S/S2 | 43930695.69 | 28334900 | 10982673.92 | 39317573.92
October Dry Port | Dry Port Inv. 04 | 4 | October Dry Port4 | 4494774.84 | 4307238.86 | 1179878.4 | 5487117.26
Akhmem - Qena | Ref.Ret Qen-akh 5 |  | Akhmem - Qena | 11634107.57 | 0 | 0 | 11634107.57
Akhmem - Qena | Ret Qen-akh 5 T |  | Akhmem - Qena | 11634107.57 | 11634107.57 | 0 | 11634107.57
Faculty of Medicine | FacultyMedcine IPC06 | 6 | Faculty of Medicine6 | 22540491.43 | 19072236.24 | 1127024.57 | 20199260.81
Racecores 3092-17 132KV E | 11162 |  | Racecores 3092-17 132KV E | 3031979.8732 | 7549629.9 | 0 | 2516543.3
158E/2019 33kv Project | 10983 |  | 158E/2019 33kv Project | 45900 | 48195 | 0 | 48195
EGAT Pelletizing Plant | EGAT WaterTank IPC03 | 3 | EGAT Pelletizing Plant3 | 725357.86 | 718104.283 | 0 | 718104.283
EGAT Pelletizing Plant | EGAT WaterTank IPC05 | 5 | EGAT Pelletizing Plant5 | 923594.33 | 914358.3865 | 0 | 914358.3865
El Taameer Axis Expansion | IPC#01 | 1 | El Taameer Axis Expansion1 | 490050 | 473388.3 | 0 | 473388.3
Pridge 5 | inv ( 1 Fina ) pridg | 1 | Pridge 51 | 2500000 | 1964967 | 0 | 1964967
Ministries Buildings | Minist Core IPC08 | 8 | Ministries Buildings8 | 14605110.03 | 6152200 | 6152200 | 12304400
Al Montaza Hotels - Alexandria | inv ( 6 ) Montazha | 6 | Al Montaza Hotels - Alexandria6 | 1120815.3 | 1113915.3 | 0 | 1113915.3
Get Business Complex | INV ( 12 ) GET | 12 | Get Business Complex12 | 159042.1 | 149499.58 | 0 | 149499.58
EDNC Retail & Offices Civil | soreal-ipc32 | 32 | EDNC Retail & Offices Civil32 | 17472419.88 | 19068785.824 | 0 | 19068785.824
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.04 | 4 | 10th Ramadan Indu Park Plot114 | 3650724.08 | 0 | 574989.04 | 574989.04
Ring Road Bridges Project | inv ( 1 ) | 1 | Ring Road Bridges Project1 | 345747.5 | 18843.23 | 0 | 309789.76
New Babil 400/132KV GIS Substa | 2112210003 |  | New Babil 400/132KV GIS Substa | 65899.31 | 65899.31 | 0 | 65899.31
New Babil 400/132KV GIS Substa | 2112210002 |  | New Babil 400/132KV GIS Substa | 234031.6 | 234031.6 | 0 | 234031.6
LAYYAH CCPP | 517 |  | LAYYAH CCPP | 15933480 | 12250264 | 3683216 | 15933480
Ministries Buildings | MinistSHELL IPC08 | 8 | Ministries Buildings8 | 11226263.85 | 4728860 | 4728862.5 | 9457722.5
Playa Resort | 005/2022 |  | Playa Resort | 65139712 | 0 | 128976629.76 | 64488314.88
Sokhna Port Expansion | SPX.1 ipc 22+23 | 22 | Sokhna Port Expansion22 | 3517168 | 2087493.15 | 946930 | 3034423.15
Sokhna Port Expansion | sokhna port ex ipc03 | 3 | Sokhna Port Expansion3 | 83177845.64 | 55802954.372 | 17467347.58 | 73270301.952
Olympic Multi – Sports Hall | Olympic MEP IPC2 | 2 | Olympic Multi – Sports Hall2 | 42437483 | 1103175 | 35000000.9 | 36103175.9
RING ROAD MARYOTIA EXPANSION | Maryotia IPC013 | 13 | RING ROAD MARYOTIA EXPANSION13 | 53815173.27 | 41457209.53 | 4159591.2 | 45616800.73
seashell Playa | IPC-1-PLAYA | 1 | seashell Playa1 | 70125 | 48954.26 | 11220 | 60174.26
Port Said Grain Storage | IPC#4 GSCC PortSaeid | 4 | Port Said Grain Storage4 | 1039500 | 744399.45 | 0 | 887185.95
Port Said Grain Storage | IPC7 PORTSAID | 7 | Port Said Grain Storage7 | 1270500 | 833414.09 | 0 | 875764.94
Ring Road Bridges Project | INV ( 4 ) Ring R | 4 | Ring Road Bridges Project4 | 1437004.5 | 1296029.35 | 0 | 1296029.35
AWEER POWER STATION 'H' Phase | ENG/045 |  | AWEER POWER STATION 'H' Phase | 76984.73 | 80833.9665 | 0 | 80833.9665
AWEER POWER STATION 'H' Phase | ENG/049 |  | AWEER POWER STATION 'H' Phase | 177536.41 | 186413.2305 | 0 | 186413.2305
TZ – Offshore E&M Procurement | 427 |  | TZ – Offshore E&M Procurement | 33185.28 | 26548.22 | 6637.06 | 33185.28
TZ – Offshore E&M Procurement | 449 |  | TZ – Offshore E&M Procurement | 80448.15 | 68380.93 | 12067.22 | 80448.15
Benban 500 K.V / 100 K.M | رد تامين2بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 15000000 | 15000000 | 0 | 15000000
El Taameer Axis Expansion | IPC#3 Taamer Axis | 3 | El Taameer Axis Expansion3 | 1404810 | 1329632.46 | 0 | 1329632.46
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC 10 | 10 | ElSewedy HQ Internal Finishing10 | 10645458.95 | 0 | 2838099.58 | 10819981.5175
Racecores 3092-17 132KV E | 11142 |  | Racecores 3092-17 132KV E | 3674.19 | 3674.19 | 0 | 3674.19
Racecores 3092-17 132KV E | 11143 |  | Racecores 3092-17 132KV E | 3152 | 3152 | 0 | 3152
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.8 | 8 | Nagaa Hamady/Assuit OHTL8 | 2306137.06 | 1382954.13 | 242144.39 | 1625098.52
RING ROAD MARYOTIA EXPANSION | RING ROAD ELMARG-01 | 1 | RING ROAD MARYOTIA EXPANSION1 | 53196756.68 | 47818510.6105 | 0 | 47818510.6105
New Giza Teaching Hospital | new giza hos ipc 23 | 23 | New Giza Teaching Hospital23 | 8466924.1 | 3527907.892 | 2289022.09 | 7316929.982
New Giza Teaching Hospital | New giza IPC7 | 7 | New Giza Teaching Hospital7 | 20034184.42 | 13696429.151 | 1934334.62 | 15630763.771
New Giza Teaching Hospital | newgizahospital ipc6 | 6 | New Giza Teaching Hospital6 | 21174583.68 | 13704613.324 | 1755133.01 | 15459746.334
Miscellaneous Projects | 2111210002 |  | Miscellaneous Projects | 40500 | 46170 | 0 | 46170
Egat Rolling Mill no.4 | Rolling mill-IPC10 | 10 | Egat Rolling Mill no.410 | 7998755.08 | 6084201.904 | 2234503.38 | 8318705.284
Egat Rolling Mill no.4 | ROLLING MILL IPC05 | 5 | Egat Rolling Mill no.45 | 11462591.69 | 9293714.7045 | 2627380.65 | 11921095.3545
Egat Rolling Mill no.4 | ROLLING MILL IPC 02 | 2 | Egat Rolling Mill no.42 | 14442827.29 | 12106800.3045 | 2913740.08 | 15020540.3845
EGAT Lock & Load | Lock& Load ipc 16 | 16 | EGAT Lock & Load16 | 1100000 | 1134000.01 | 9999.99 | 1144000
EGAT Lock & Load | EGAT L&L ipc 09 | 9 | EGAT Lock & Load9 | 3980460.75 | 3741633.0975 | 398046.08 | 4139679.1775
EGAT Lock & Load | EGAT L&L IPC04 | 4 | EGAT Lock & Load4 | 879124 | 826376.56 | 87912.4 | 914288.96
New Babil 400/132KV GIS Substa | 2112210005 |  | New Babil 400/132KV GIS Substa | 1644635.27 | 1644635.27 | 0 | 1644635.27
ElSewedy HQ Internal Finishing | Elsewedy HQIPC23(24) | 23 | ElSewedy HQ Internal Finishing23 | 25519032.04 | 1915761.653 | 7296526.369 | 12977797.222
Ain Sokhna Port Development | IPC#5 - Sokhna Port | 5 | Ain Sokhna Port Development5 | 1262056 | 1139198.12 | 0 | 1139198.12
Cairo-Alex Railway | Railway IPC05 | 5 | Cairo-Alex Railway5 | 22089260.95 | 15620324.6875 | 2208926.1 | 17829250.7875
Cairo-Alex Railway | Railway IPC04 | 4 | Cairo-Alex Railway4 | 9667643.81 | 6825060.3005 | 966764.38 | 7791824.6805
Cairo-Alex Railway | CAIRO-ALEX-IPC01 | 1 | Cairo-Alex Railway1 | 7627640.67 | 5389084.49 | 762764.7 | 6151849.19
Egyptian Exchange building | IPC-3-BORSA | 3 | Egyptian Exchange building3 | 80683.9 | 71445.6 | 0 | 71445.6
Egyptian Exchange building | IPC-1-BORSA | 1 | Egyptian Exchange building1 | 147272.73 | 130009.99 | 0 | 130009.99
Benban 500 K.V / 100 K.M | Ref-Ret-benban 1 $ T |  | Benban 500 K.V / 100 K.M | 1145169.37 | 964639.99 | 180529.38 | 1145169.37
Tamey El-amdeed Substation | Tam CW Final |  | Tamey El-amdeed Substation | 2457951.55 | 14135046.53 | 0 | 14135046.53
Port Said Port Silos | port said ipc18 | 18 | Port Said Port Silos18 | 7866196.51 | 3958149.4004 | 3786619.65 | 7744769.0504
Port Said Port Silos | port said ipc12 | 12 | Port Said Port Silos12 | 2086813.53 | 1843797.0112 | 208681.35 | 2052478.3612
Port Said Port Silos | portsaid soils ipc32 | 32 | Port Said Port Silos32 | 3968922.29 | 2296974.7655 | 396892.23 | 2693866.9955
Port Said Port Silos | supply egp ipc 3 | 3 | Port Said Port Silos3 | 3085091.63 | 9231726.9128 | 1234036.64 | 2616440.8882
Angola Emergency fast-track | ANG-Mor-Inv 3 - Ints | 3 | Angola Emergency fast-track3 | 13452980.7 | 8544758.08 | 0 | 8544758.08
Angola Emergency fast-track | ANG-Cam-Inv 8 - Ints | 8 | Angola Emergency fast-track8 | 630183.71 | 349104.59 | 0 | 349104.59
MDF Factory | IPC07-MDF | 7 | MDF Factory7 | 15235053.51 | 14452381.0155 | 2109738.13 | 16562119.1455
PLAYA ROOF & Wet Areas | IPC-3-PLAYA ROOF | 3 | PLAYA ROOF & Wet Areas3 | 27985.3 | 24014.18 | 0 | 24014.18
Ain Sokhna Bridge – RME | IPC#5 SOKHNA BRIDG | 5 | Ain Sokhna Bridge – RME5 | 1178375 | 929687.14 | 0 | 1132649.55
Port Saad Industiral zone | IPC#2 | 2 | Port Saad Industiral zone2 | 2861100 | 2755239.3 | 0 | 2755239.3
Ain Sokhna Bridge – RME | IPC#6 Sokhna Bridge | 6 | Ain Sokhna Bridge – RME6 | 1633000 | 1563825.52 | 0 | 1566925.77
Egat Rolling Mill no.4 | Rolling Mill ipc 01 | 1 | Egat Rolling Mill no.41 | 21476647.49 | 16966551.5245 | 5369161.87 | 22335713.3945
Port Saeed East - OHTL | Port said OHTL Inv.1 | 1 | Port Saeed East - OHTL1 | 5342562.5 | 3413080 | 0 | 3413080
New Babil 400/132KV GIS Substa | 2112210009 |  | New Babil 400/132KV GIS Substa | 138115.2 | 138115.2 | 0 | 138115.2
Racecores 3092-16 132KV C | 11456 |  | Racecores 3092-16 132KV C | 484878.9 | 804898.95 | 0 | 402449.475
MDF Factory | mdf factory2 ipc02 | 2 | MDF Factory2 | 2969783.71 | 2999481.5494 | 0 | 2999481.5494
El Taameer Axis Expansion | IPC#4 - Taamer Axis | 4 | El Taameer Axis Expansion4 | 1047618 | 1011998.99 | 0 | 1011998.99
EDNC Retail & Offices Civil | sodic soreal ipc34 | 34 | EDNC Retail & Offices Civil34 | 4991381.7 | 2767127.555 | 0 | 2767127.555
SHAT Al ARAB 400/132kV SS | 435 |  | SHAT Al ARAB 400/132kV SS | 508993.48 | 508993.48 | 0 | 508993.48
SHATRA 400/132kV SS | 441 |  | SHATRA 400/132kV SS | 4928 | 4928 | 0 | 4928
LAYAN Substation | 11302 |  | LAYAN Substation | 13800 | 14490 | 0 | 14490
Houd Negaih | Houd Negaih Inv.01 | 1 | Houd Negaih1 | 1956673.81 | 1360213 | 205450.75 | 1565663.75
AWEER POWER STATION 'H' Phase | CON/028 |  | AWEER POWER STATION 'H' Phase | 159712.34 | 140191.9385 | 17745.82 | 157937.7585
EGAT Lock & Load | EGAT L&L IPC02 | 2 | EGAT Lock & Load2 | 2362059.16 | 2220335.608 | 236205.92 | 2456541.528
Racecores 3092-16 132KV C | 11366 |  | Racecores 3092-16 132KV C | 2885225.48 | 26818170.83 | 0 | 2438015.53
Royal City | ROYAL CITY2-IPC17 | 17 | Royal City17 | 3716185.79 | 2058324.5495 | 0 | 2058324.5495
AWEER POWER STATION 'H' Phase | LOC/023 |  | AWEER POWER STATION 'H' Phase | 569423.12 | 499826.95 | 63269.24 | 563096.19
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 2 Equ | 2 | Hosh Essa 220 KV OHTL2 | 6276017.62 | 3768594.85 | 662276.76 | 4430871.61
Ain Sokhna Port Development | IPC#8 Sokhna Port | 8 | Ain Sokhna Port Development8 | 1481544 | 1147950.32 | 0 | 1384041.14
PLAYA ROOF & Wet Areas | IPC-5-PLAYA ROOF | 5 | PLAYA ROOF & Wet Areas5 | 259426.25 | 222613.67 | 0 | 222613.67
Playa Resort | 006/2022 |  | Playa Resort | 127114464 | 0 | 246119024.4 | 123059512.2
Racecores 3092-16 132KV C | 11425 |  | Racecores 3092-16 132KV C | 13800 | 14490 | 0 | 14490
158E/2019 33kv Project | 11384 |  | 158E/2019 33kv Project | 0 | -33940 | 0 | -33940
EGAT Pelletizing Plant | EGAT WATER TANK IPC9 | 9 | EGAT Pelletizing Plant9 | 930000 | 920700 | 0 | 920700
MDF Factory | MDF ipc12 | 12 | MDF Factory12 | 35128478.15 | 25430949.4775 | 4011840.31 | 29442789.7875
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC38 | 38 | EMAAR-Pkg#162/163- Marassi38 | 113074931.25 | 46024929.671 | 44314466.39 | 90339396.061
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 11 | 11 | Suez Gulf/S4 - 500KV OHTL11 | 243376.33 | 72921.11 | 0 | 72921.11
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 16 | 16 | Suez Gulf/S4 - 500KV OHTL16 | 192316.29 | 76135.36 | 0 | 76135.36
TZ – Offshore E&M Procurement | 474 |  | TZ – Offshore E&M Procurement | 3038500.01 | 2126950.01 | 303850 | 2430800.01
AWEER POWER STATION 'H' Phase | CON/030 |  | AWEER POWER STATION 'H' Phase | 2044317.83 | 1794456.76 | 227146.43 | 2021603.19
Luxor North Axis Bridge | IPC#5 - Luxor Onshor | 5 | Luxor North Axis Bridge5 | 1696950 | 1646041.5 | 0 | 1646041.5
MDF Factory | ipc 22 Mdf Factory | 22 | MDF Factory22 | 9440396.83 | 9131113.5915 | 875083.18 | 10006196.7715
LAYYAH CCPP | 521 |  | LAYYAH CCPP | 14441700 | 12253402 | 2188298 | 14441700
MDF Factory | MDF Factory ipc 41 | 41 | MDF Factory41 | 12031521.12 | 7229637.5348 | 4743990.95 | 11973628.4848
MDF Factory | MDF IPC 17 | 17 | MDF Factory17 | 12397151.01 | 13200508.7005 | 1846776.8 | 15047285.5005
East Owainat 5 LOTS | East Owainat Inv. 06 | 6 | East Owainat 5 LOTS6 | 31589348.53 | 12888446.17 | 16584407.98 | 29472854.15
PLAYA ROOF & Wet Areas | IPC-7-PLAYA ROOF | 7 | PLAYA ROOF & Wet Areas7 | 157743.65 | 95534.82 | 0 | 95534.82
Racecores 3092-17 132KV E | 11458 |  | Racecores 3092-17 132KV E | 51311.145 | 127764.72 | 0 | 42588.24
IKEA Extension MoA | IKEA Final IPC014 | 14 | IKEA Extension MoA14 | 10453317.84 | 20582119.9 | 0 | 20582119.9
Playa Resort | 007/2022 |  | Playa Resort | 260936078 | 30000000 | 475224433.8 | 252612216.9
Sokhna Port Expansion | sokhna port ex ipc01 | 1 | Sokhna Port Expansion1 | 26869010.86 | 16602157.843 | 5642492.28 | 22244650.123
Olympic Multi – Sports Hall | OLYMPIC MEP IPC01 | 1 | Olympic Multi – Sports Hall1 | 127782862.01 | 21998170 | 84159086.65 | 106157256.65
Air Defense College | air devance ipc02 | 2 | Air Defense College2 | 43054725.7 | 5061464.99 | 15184410 | 36435094.99
October Dry Port | Dry Port Inv. 03 | 3 | October Dry Port3 | 8842219.45 | 3831410.7 | 2321082.61 | 6152493.31
Waldorf Astoria Cairo | waldorf- IPC 14 | 14 | Waldorf Astoria Cairo14 | 13597376.25 | 6216098 | 6350420.2 | 12566518.2
Waldorf Astoria Cairo | waldorf- IPC13 | 13 | Waldorf Astoria Cairo13 | 11273556.71 | 5389256 | 5505974.65 | 10895230.65
Waldorf Astoria Cairo | Waldorf_IPC 11 | 11 | Waldorf Astoria Cairo11 | 22454296.86 | 10757000 | 11695677.26 | 22452677.26
New Babil 400/132KV GIS Substa | 220321002 |  | New Babil 400/132KV GIS Substa | 2062842.53 | 2062842.53 | 0 | 2062842.53
ElSewedy HQ Internal Finishing | EL SEWEDY HQ IPC14+ | 14 | ElSewedy HQ Internal Finishing14 | 227373.9 | 93658.425 | 125227.8 | 218886.225
EMAAR-Pkg#162/163- Marassi | pkg#177 ipc 26+27 | 26 | EMAAR-Pkg#162/163- Marassi26 | 1329766.23 | 2043641.8815 | 245784.77 | 2289426.6515
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC30 | 30 | EMAAR-Pkg#162/163- Marassi30 | 18828872.42 | 11954931.111 | 2185712.29 | 14140643.401
Mivida BP#189 | ipc 10 Emaar pkg#189 | 10 | Mivida BP#18910 | 29038558.46 | 23647399.753 | 4548578.7 | 28195978.453
Mivida BP#189 | Emaar pkg #189ipc16 | 16 | Mivida BP#18916 | 24459783.78 | 22512171.879 | 6258221.77 | 28770393.649
Mivida BP#189 | Emaar PKG#189-IPC 13 | 13 | Mivida BP#18913 | 16636045.76 | 53623446.998 | 6413031.96 | 60036478.958
Mivida BP#189 | pkg#189- IPC8 | 8 | Mivida BP#1898 | 80364676.81 | 66596247.2075 | 8059948.84 | 74656196.0475
Ismailiya East Substation | ISE-CW-EGP-27 | 27 | Ismailiya East Substation27 | 395246 | 10729225.46 | 0 | 10729225.46
New Giza Teaching Hospital | giza hospital ipc04 | 4 | New Giza Teaching Hospital4 | 36077726.42 | 27335611.781 | 5103959.99 | 32439571.771
Abou Ghaleb Bridge | Abo Ghaleb ipc03 | 3 | Abou Ghaleb Bridge3 | 3122399.3 | 2053971.909 | 0 | 2053971.909
ElSewedy HQ Internal Finishing | el sewedy HQ ipc14 | 14 | ElSewedy HQ Internal Finishing14 | 15184089.24 | 1654906.512 | 5800933.2 | 11887191.492
Kuwait | Inv.4988/Sp/H&J-01 | 4988 | Kuwait4988 | 39217 | 37256.15 | 0 | 37256.15
Ain Sokhna Port Development | IPC#10 - Sokhna Port | 10 | Ain Sokhna Port Development10 | 548720 | 409779.02 | 0 | 512223.77
Ain Sokhna Port Development | IPC#13 - Sokhna Port | 13 | Ain Sokhna Port Development13 | 555579 | 518768.03 | 0 | 518768.03
Faculty of Medicine | mansora finish ipc20 | 20 | Faculty of Medicine20 | 17457823.81 | 13025752 | 2618673.57 | 15644425.57
Faculty of Medicine | mansura finish ipc16 | 16 | Faculty of Medicine16 | 14959073.33 | 11161308 | 2243861 | 13405169
Faculty of Medicine | mansura finish ipc14 | 14 | Faculty of Medicine14 | 7273839.05 | 5426974.862 | 1091075.86 | 6518050.722
Faculty of Medicine | mansora finish ipc 5 | 5 | Faculty of Medicine5 | 4557213.33 | 3399965.3765 | 683582 | 4083547.3765
Faculty of Medicine | mansora finish ipc04 | 4 | Faculty of Medicine4 | 3531509.52 | 2634634.64 | 529726.43 | 3164361.07
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 16 | 16 | Benban 500 K.V / 100 K.M16 | 640951.31 | 494176.02 | 67299.89 | 561475.91
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.06 | 6 | Mostakbal 2 Package No. (8)6 | 22763756.44 | 18074422.61 | 4780388.85 | 22854811.46
Capital One | inv ( 5 ) Captal 1 | 5 | Capital One5 | 2411182.78 | 2387070.949 | 0 | 2387070.949
Ain Sokhna Port Development | IPC#12 - Sokhna port | 12 | Ain Sokhna Port Development12 | 809362 | 604055.74 | 0 | 755069.68
Cairo Monorail - 6th October | IPC#9 Monorail | 9 | Cairo Monorail - 6th October9 | 576000 | 545915 | 0 | 545915
AMRIYA WWTP (3RD STAGE) | 220621001 |  | AMRIYA WWTP (3RD STAGE) | 2816523.26 | 2436825.98 | 281652.33 | 2788358.03
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 7 | 7 | Marsa Alam/ Bernes LOT2 OHTL7 | 11944.76 | 10276.45 | 0 | 10276.45
Ain Sokhna Port Development | IPC#11 Sokhna Port | 11 | Ain Sokhna Port Development11 | 2537830 | 1874852.74 | 0 | 2375288.8
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .21 | 21 | Benban 3/ Toshka 2 LOT 421 | 5065984.71 | 3986536.02 | 531928.4 | 4518464.42
The Open Channel Project | Open chanel1 IPC fin |  | The Open Channel Project | 299730184.76 | 63060050 | 214584480.64 | 277644530.64
Mohamed Ali Palace Restoration | mohamed aly 4 ipc01 | 1 | Mohamed Ali Palace Restoration1 | 62417589.1 | 51394790.0005 | 0 | 51394790.0005
Ora Zed Landscape Ph1 | Ora landscape ipc 17 | 17 | Ora Zed Landscape Ph117 | 1582674.29 | 1313619.66 | 166180.8 | 1479800.46
Ora Zed Landscape Ph1 | Ora landsacape ipc 8 | 8 | Ora Zed Landscape Ph18 | 6274745.71 | 5158038.9355 | 658848.3 | 5816887.2355
Ora Zed Landscape Ph1 | Ora Landscap ipc (5) | 5 | Ora Zed Landscape Ph15 | 3284925.66 | 2898946.893 | 344917.19 | 3243864.083
Ora Zed Landscape Ph1 | Ora landscape ipc3 | 3 | Ora Zed Landscape Ph13 | 2138801.9 | 1887492.675 | 224574.2 | 2112066.875
Beymen Fit Out | PKG#205 IPC02 | 2 | Beymen Fit Out2 | 1935313.99 | 1283209.9395 | 609623.91 | 1892833.8495
EMAAR-Pkg#162/163- Marassi | Emar Pkg#177 ipc(45) | 45 | EMAAR-Pkg#162/163- Marassi45 | 26509803.46 | 16466307.981 | 10800000 | 27266307.981
ORA ZED-Ph 2-Pkgs A&D | ora zed2 ipc06 | 6 | ORA ZED-Ph 2-Pkgs A&D6 | 23225104.47 | 17674903.7 | 2127824.64 | 19802728.34
RING ROAD MARYOTIA EXPANSION | Maryotia IPC011 | 11 | RING ROAD MARYOTIA EXPANSION11 | 29094868.16 | 3708396.57 | 0 | 26708396.57
Sokhna Port Expansion | SOKHNA PORT EX IPC02 | 2 | Sokhna Port Expansion2 | 28451675.04 | 19087604.352 | 5974851.76 | 25062456.112
West Domiatte 500KV TowersZT60 | West Domiatte Inv.01 | 1 | West Domiatte 500KV TowersZT601 | 2452240.2 | 1873789.17 | 0 | 1873789.17
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 08 | 8 | Hosh Essa 220 KV OHTL8 | 1951059.05 | 0 | 204861.2 | 204861.2
Al-Ula Towers | INV ( 5 ) FINAL | 5 | Al-Ula Towers5 | 544770 | 539322.3 | 0 | 545859.54
Ghana Street lighting | MIDA Sply. Inv.1 4 | 1 | Ghana Street lighting1 | 105344.73 | 94747.51 | 0 | 94747.51
Luxor North Axis Bridge-Off | IPC#2-Luxoroffshore | 2 | Luxor North Axis Bridge-Off2 | 2759040 | 2200390.65 | 0 | 2200390.65
TZ – Offshore E&M Procurement | 473 |  | TZ – Offshore E&M Procurement | 496399.75 | 347479.82 | 99279.95 | 446759.77
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $10 | 10 | Benban 3/ Toshka 2 LOT 410 | -125258.82 | -131521.76 | 0 | -131521.76
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 3 | 3 | Marsa Alam/ Bernes LOT2 OHTL3 | 95885.29 | 80543.63 | 10067.96 | 90611.59
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 04 | 4 | Toshka-04 GIS Substation4 | 28562090.56 | 19907383.61 | 2999019.51 | 22906403.12
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .25 | 25 | Benban 3/ Toshka 2 LOT 425 | 10971975.5 | 9786573.09 | 0 | 9786573.09
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .23 | 23 | Benban 3/ Toshka 2 LOT 423 | 6805892.98 | 6070461.77 | 0 | 6070461.77
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .19 | 19 | Benban 3/ Toshka 2 LOT 419 | 4894980.83 | 3337982.9 | 513972.99 | 3851955.89
Benban 500 K.V/95 K.M | Ref-Ret-Benban lot2 |  | Benban 500 K.V/95 K.M | 15330832.04 | 0 | 0 | 15330832.04
LAYYAH CCPP | 501 |  | LAYYAH CCPP | 485125 | 432974.06 | 72768.75 | 505742.81
Infra Project 2524 | 220421006 |  | Infra Project 2524 | 76438931 | 76438931 | 0 | 76438931
EGAT New Rolling Mill 4 | IPC#1 EGAT | 1 | EGAT New Rolling Mill 41 | 1143460 | 823066.73 | 0 | 1028833.41
MDF Factory | MDF factory ipc(28) | 28 | MDF Factory28 | 4537395.02 | 5380287.99 | 1905652.45 | 7285940.44
Ain Sokhna Port Development | IPC#14 - Sokhna Port | 14 | Ain Sokhna Port Development14 | 1234620 | 1123032.9 | 0 | 1153791.13
DPW Onshore Port & Terminal | DPW IPC 35 | 35 | DPW Onshore Port & Terminal35 | 3275655.01 | 83471391.43 | 0 | 83471391.43
Railway Bridge - Assuit | IPC#06 - Assuit | 6 | Railway Bridge - Assuit6 | 2680410 | 2465977.2 | 0 | 2465977.2
EDNC Hardscape Package | Soreal hardscapeipc6 | 6 | EDNC Hardscape Package6 | 2241713.44 | 1939613.522 | 0 | 1939613.522
PLAYA ROOF & Wet Areas | IPC-11-Playa Roof | 11 | PLAYA ROOF & Wet Areas11 | 360191.53 | 308640.34 | 0 | 308640.34
seashell Playa | IPC-12-PLAYA | 12 | seashell Playa12 | 316449.3 | 220913.25 | 50631.89 | 271545.14
Egyptian Exchange building | IPC-6-BORSA | 6 | Egyptian Exchange building6 | 18812.7 | 16658.63 | 0 | 16658.63
EMAAR-Pkg#162/163- Marassi | pkg#177 IPC 28 | 28 | EMAAR-Pkg#162/163- Marassi28 | 4959294.77 | 3923650.8385 | 0 | 3923650.8385
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC020 | 20 | EMAAR-Pkg#162/163- Marassi20 | 10455877.96 | 8109376.158 | 975298.66 | 9084674.818
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC016 | 16 | EMAAR-Pkg#162/163- Marassi16 | 6039477.06 | 3872324.523 | 1044515.19 | 4916839.713
WADY EL-NATROUN BRIDGE(HST) | IPC#1 Wadi ElNatroun | 1 | WADY EL-NATROUN BRIDGE(HST)1 | 659470 | 568724.7 | 0 | 568724.7
Port Said Grain Storage | IPC#2 Port saeid | 2 | Port Said Grain Storage2 | 577500 | 428922.59 | 0 | 512090.25
W Dam PP Phase II (CP-117) | 25 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 565157.2762 | 477890.9595 | 89012.27 | 566903.2295
W Dam PP Phase II (CP-117) | 180158 |  | W Dam PP Phase II (CP-117) | 3803.7 | 3401.19 | 600.21 | 4001.4
Air Defense College | Air defence3 IPC1 | 1 | Air Defense College1 | 13550058.5 | 1311645 | 3700000 | 11343443
Waldorf Astoria Cairo | Waldorf Astoria IPC6 | 6 | Waldorf Astoria Cairo6 | 14843761.8 | 8446327.45 | 2880129.65 | 11326457.1
Air Defense College | Air Defense2 IPC2 | 2 | Air Defense College2 | 33237226.2 | 10422915 | 0 | 28178893
Racecores 3092-17 132KV E | 11770 |  | Racecores 3092-17 132KV E | 11700 | 12285 | 0 | 12285
LINX Tower | inv ( 1 ) LINX | 1 | LINX Tower1 | 2451943.5 | 2304826.875 | 0 | 2321173.1667
SSC Suez Steel Company Project | SUEZ STEEL ABB IPC 1 | 1 | SSC Suez Steel Company Project1 | 5874834 | 5134498.04 | 1504064.38 | 6638562.42
SSC Suez Steel Company Project | inte&retu app ipc 3 | 3 | SSC Suez Steel Company Project3 | 788338.18 | 772824.1852 | 102231.19 | 875055.3752
SSC Suez Steel Company Project | In&Re apply abb ipc6 | 6 | SSC Suez Steel Company Project6 | 878095.32 | 573224.032 | 401460.29 | 974684.322
SSC Suez Steel Company Project | i&r apply (Abb)ipc4 | 4 | SSC Suez Steel Company Project4 | 2495283.55 | 0 | 1140829.76 | 2769764.737
Port Said Port Silos | port said silos ipc6 | 6 | Port Said Port Silos6 | 9017880.28 | 7950568.754 | 901788.03 | 8852356.784
Astoria Sharm elSheikh | astoria sharm IPC2 | 2 | Astoria Sharm elSheikh2 | 401082.65 | 269728 | 105284.2 | 375012.2
EPICO 3 Facility | Eipico ipc 14 | 14 | EPICO 3 Facility14 | 69127444.9 | 36305980.07 | 35009073.56 | 71315053.63
EPICO 3 Facility | Eipico ipc( 7) | 7 | EPICO 3 Facility7 | 7955142.87 | 6395645.73 | 2166091.43 | 8561737.16
WADY EL-NATROUN BRIDGE(HST) | IPC#3 Wadi ElNatroun | 3 | WADY EL-NATROUN BRIDGE(HST)3 | 493185 | 365809.04 | 0 | 407261.3
EDNC Retail & Offices Civil | soreal ipc35 | 35 | EDNC Retail & Offices Civil35 | 46695355.64 | 45515831.938 | 34500000.284 | 90436453.782
Egat Rolling Mill no.4 | Rolling mill ipc07 | 7 | Egat Rolling Mill no.47 | 16796950.48 | 13289718.96 | 4179109.544 | 17468828.504
WADY EL-NATROUN BRIDGE(HST) | IPC#2 Wadi ElNatroun | 2 | WADY EL-NATROUN BRIDGE(HST)2 | 851865 | 733336.11 | 0 | 733336.11
Air Defense College | Air Defence 4 ipc1 | 1 | Air Defense College1 | 36699589.5 | 2794415 | 16200000 | 30756980
Bahr ElBakar – Power Station | IPC#7 Bahr Elbaqar | 7 | Bahr ElBakar – Power Station7 | 597432 | 581392.68 | 0 | 581392.68
El Taameer Axis Expansion | IPC#3 Taamer PII | 3 | El Taameer Axis Expansion3 | 803880 | 776548.08 | 0 | 776548.08
BridgeNasr Rd w Abbas El-Akkad | AbasAlaqad2 IPCFinal |  | BridgeNasr Rd w Abbas El-Akkad | 18721056.27 | 7730640.01 | 9800000 | 17530640.01
CS-20 Mall | inv ( 4:12 ) CS-20 | 4 | CS-20 Mall4 | 64469.93 | 60601.73 | 0 | 60601.73
Kattameya Creeks | katameya IPC19 | 19 | Kattameya Creeks19 | 37484144.91 | 36075433.1155 | 2903017.59 | 38978450.7055
ElSewedy HQ Internal Finishing | elsewedy HQ ipc18 | 18 | ElSewedy HQ Internal Finishing18 | 15535743.72 | 11331892.376 | 10220010 | 23184676.836
Railway Bridge - El Hammam | IPC#6 ElHammam | 6 | Railway Bridge - El Hammam6 | 767288 | 597016.89 | 0 | 597016.89
GOV2 - Infra | GOV2 IPC 11 | 11 | GOV2 - Infra11 | 23184283 | 38068615.4 | 4723524.7 | 42792140.1
seashell Playa | 21 |  | seashell Playa | 711318.54 | 610382.44 | 0 | 610382.44
Ministries Buildings | Minist MEP IPC05 | 5 | Ministries Buildings5 | 47392701.8 | 295005 | 0 | 40779504.61
HST Bridges-Sokhna & Mahager | Elsokhna 4.5 ipc 3+4 | 3 | HST Bridges-Sokhna & Mahager3 | 10960142.86 | 9099910.583 | 0 | 9099910.583
Mivida BP#189 | pkg#189- IPC 5 | 5 | Mivida BP#1895 | 28546026.85 | 29417050.3325 | 3544586.98 | 32961637.3125
Luxor North Axis Bridge-Off | IPC#3 Offshore | 3 | Luxor North Axis Bridge-Off3 | 2121585.6 | 1951150.03 | 0 | 1951150.03
Ain Sokhna Port Development | IPC#20 Sokhna Port | 20 | Ain Sokhna Port Development20 | 1111158 | 833955.58 | 0 | 1042444.47
EDNC Hardscape Package | EDNC HARDESCAPE IPC4 | 4 | EDNC Hardscape Package4 | 1923818.4 | 4301325.99 | 0 | 4301325.99
EDNC Retail & Offices Civil | ednc sodic ipc33 | 33 | EDNC Retail & Offices Civil33 | 15003172.55 | 13807649.9075 | 0 | 13807649.9075
EMAAR-Pkg#162/163- Marassi | PKG#163- IPC26 | 26 | EMAAR-Pkg#162/163- Marassi26 | 6526578.31 | 6335310.4955 | 0 | 6335310.4955
Olympic Multi – Sports Hall | Olympic Finsh IPC3+ | 3 | Olympic Multi – Sports Hall3 | 54667923.35 | -36601001.09 | 83049200 | 46448198.91
Ministries Buildings | min mep ipc 6 | 6 | Ministries Buildings6 | 40277149 | 33933085 | 0 | 33933085
CFC Podium 2 | CFC IPC024 | 24 | CFC Podium 224 | 14455028.51 | 9889480.3655 | 0 | 9889480.3655
Ameria | FPC - Ameria Project |  | Ameria | 120000 | 112800 | 0 | 112800
Egat Rolling Mill no.4 | Rolling mill ipc 04 | 4 | Egat Rolling Mill no.44 | 8075015.79 | 6811267.8195 | 1586748.6 | 8398016.4195
Egat Rolling Mill no.4 | rolling mill- IPC10 | 10 | Egat Rolling Mill no.410 | 19073639.83 | 0 | 0 | 20027321.8215
MDF Factory | MDF FACTORY2 IPC06 | 6 | MDF Factory6 | 660835.92 | 667444.2788 | 0 | 667444.2788
MDF Factory | MDF FACTORY IPC09 | 9 | MDF Factory9 | 6053905.51 | 5166802.9655 | 950994.49 | 6117797.4555
EL -mahager Bridge Ain sokhna | IPC#1 - HST Mahager | 1 | EL -mahager Bridge Ain sokhna1 | 1795000 | 0 | 0 | 1795000
Ain Sokhna Bridge – RME | FPC - Sokhna Bridge |  | Ain Sokhna Bridge – RME | 62525 | 48344.83 | 0 | 61899.75
Mohamed Ali Palace Restoration | mohamed aly3 Ipc2 | 2 | Mohamed Ali Palace Restoration2 | 1900257.14 | 1593935 | 0 | 1593935
Air Defense College | Air def IPC4 | 4 | Air Defense College4 | 2263082 | 1561455 | 0 | 1909712
Waldorf Astoria Cairo | waldorf Astoria IPC9 | 9 | Waldorf Astoria Cairo9 | 16070153.02 | 6286403 | 6421058.51 | 12707461.51
PLAYA ROOF & Wet Areas | IPC014-Playa Roof | 14 | PLAYA ROOF & Wet Areas14 | 105243.51 | 88240.2 | 0 | 88240.2
Port Said Port Silos | port said silos ipc8 | 8 | Port Said Port Silos8 | 22573115.94 | 20033640.397 | 2257311.59 | 22290951.987
WADY EL-NATROUN BRIDGE(HST) | IPC 6 WADIELNATRON | 6 | WADY EL-NATROUN BRIDGE(HST)6 | 269100 | 160767.86 | 0 | 200959.83
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC 20 | 20 | ElSewedy HQ Internal Finishing20 | 43687204.67 | 10136401.93 | 14678900.67 | 31315302.57
New Giza Teaching Hospital | New giza - IPC10 | 10 | New Giza Teaching Hospital10 | 22234302.84 | 16043183.482 | 4106456.49 | 20149639.972
New Giza Teaching Hospital | new giza IPC9 | 9 | New Giza Teaching Hospital9 | 23282485.08 | 16758838.084 | 3068734.89 | 19827572.974
Expansion of Ring Road NRCC | IPC#1 - NRCC | 1 | Expansion of Ring Road NRCC1 | 699000 | 657060 | 0 | 657060
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC16 | 16 | EMAAR-PKG# 101-UPTOWN16 | 181866.48 | 1873125.774 | 57287.94 | 1930413.714
MDF Factory | MDF Local - IPC8 | 8 | MDF Factory8 | 570451.1 | 413577.054 | 162578.56 | 576155.614
Air Defense College | Defense6 IPC1 | 1 | Air Defense College1 | 15431378 | 13555895 | 0 | 13555895
Ministries Buildings | Mini MEP IPC6 | 6 | Ministries Buildings6 | 22769892 | 17664815 | 0 | 17664815
Cairo-Alex Railway | cairo-alex ipc 26 | 26 | Cairo-Alex Railway26 | 32853592.5 | 22794741.105 | 3449627.21 | 26244368.315
MDF Factory | MDF - IPC 16 | 16 | MDF Factory16 | 11688118.01 | 10601848.06 | 3062673.45 | 13664521.51
Air Defense College | Defense5 IPC1 | 1 | Air Defense College1 | 6178705 | 1663625 | 3400000 | 5121298
Creeks URBN-K | Urbnk- ipc 1 | 1 | Creeks URBN-K1 | 10988694.51 | 10729515 | 465817.73 | 11195332.73
EGAT Pelletizing Plant | EGAT IPC06 | 6 | EGAT Pelletizing Plant6 | 11102739.54 | 10274250.077 | 1272599.04 | 11546849.117
Port Said Grain Storage | IPC 5 PORT SAID | 5 | Port Said Grain Storage5 | 1155000 | 722257.8 | 0 | 902822.25
WADY EL-NATROUN BRIDGE(HST) | IPC 8 WADI ELNATRON | 8 | WADY EL-NATROUN BRIDGE(HST)8 | 551985 | 392263.34 | 0 | 454413.58
SSC Suez Steel Company Project | revamp ipc(5) | 5 | SSC Suez Steel Company Project5 | 4135898.1 | 2853769.694 | 1240769.43 | 4094539.124
Port Said Grain Storage | IPC#7 Portsaid | 7 | Port Said Grain Storage7 | 2407900 | 1710478.54 | 0 | 1710478.54
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC09 | 9 | ORA ZED - Ph 01B - Pkgs A&D9 | 27403398.03 | 24054179.0515 | 2858510.2 | 26912689.2515
Royal City | Royal city ipc (42) | 42 | Royal City42 | 10349949.34 | 20407465.3582 | 116680.4388 | 20524145.797
EMAAR-Pkg#162/163- Marassi | pkg#177-IPC37 | 37 | EMAAR-Pkg#162/163- Marassi37 | 3201525.38 | 3131251.909 | 0 | 3131251.909
BKG#178-Lagoon Discharge | PKG#178- IPC 9 | 9 | BKG#178-Lagoon Discharge9 | 31809.53 | 2524652.5565 | 0 | 2524652.5565
EGAT Lock & Load | EGAT L&L-IPC11 | 11 | EGAT Lock & Load11 | 1992889.65 | 1873316.2725 | 199288.96 | 2072605.2325
EGAT Lock & Load | EGAT L&L IPC12 | 12 | EGAT Lock & Load12 | 1778896.47 | 1672162.6835 | 177889.65 | 1850052.3335
Cairo-Alex Railway | Cairo-alex ipc 35 | 35 | Cairo-Alex Railway35 | 3020585.71 | 2097397.78 | 317161.5 | 2414559.28
GOV2 - Infra | Gov2 ipc(12) | 12 | GOV2 - Infra12 | 42288546.24 | 23775725.082 | 3343428.6 | 27119153.682
ORA-ZED Towers P01B | 181022 |  | ORA-ZED Towers P01B | 85537.5 | 75743.46 | 0 | 75743.46
Royal City | Royal centerzone(23) |  | Royal City | 10826725.43 | 9589993.4272 | 0 | 9589993.4272
Diplomatic District - Infra | Diplomatic ipc12 | 12 | Diplomatic District - Infra12 | 13260789.9 | 18429485.685 | 2322442.3 | 20751927.985
Diplomatic District - Infra | Diplo Dist. IPC05 | 5 | Diplomatic District - Infra5 | 17394365.29 | 35617387.94 | 4410162.68 | 40027550.62
Get Business Complex | INV ( 1 ) GET | 1 | Get Business Complex1 | 716040 | 673077.6 | 0 | 673077.6
Railway Bridge - Assuit | IPC#7 - Assuit | 7 | Railway Bridge - Assuit7 | 1199450 | 1090306.8 | 0 | 1090306.8
Kemet Tower | inv ( 6-7-8 ) kemet | 6 | Kemet Tower6 | 400480 | 52023.46 | 0 | 52023.46
PLAYA ROOF & Wet Areas | IPC#00015 | 15 | PLAYA ROOF & Wet Areas15 | 176307.75 | 0 | 0 | 176307.75
Ring Road El Mansoria | INV (2 ) AL Mansorya | 2 | Ring Road El Mansoria2 | 467280 | 415879.2 | 0 | 415879.2
Ain Sokhna Bridge – RME | IPC#7 - Sokhna Bridg | 7 | Ain Sokhna Bridge – RME7 | 2211015 | 2169565.39 | 0 | 2169565.39
Kattameya Creeks | katameyacreeks-IPC26 | 26 | Kattameya Creeks26 | 73494584.17 | 74263221 | 2140175.7 | 76403396.7
Abou Ghaleb Bridge | ABOGHALEB 6+7+8+9+10 |  | Abou Ghaleb Bridge | 40668563.14 | 724954.0286 | 0 | 22208792.4286
Get Business Complex | INV ( 3 ) GET | 3 | Get Business Complex3 | 531048 | 499185.12 | 0 | 499185.12
Get Business Complex | INV ( 2 ) GET | 2 | Get Business Complex2 | 550800 | 517752 | 0 | 517752
MAF HQ Renovation | carrefour RBS IPC 4 | 4 | MAF HQ Renovation4 | 3030094 | 2037738.2 | 795399.68 | 2833137.88
MAF HQ Renovation | Carrefour RBS IPC(2) | 2 | MAF HQ Renovation2 | 1856061.8 | 1248201.56 | 487216.22 | 1735417.78
U4,U8 Seashell Playa | IPC3 TR60 | 3 | U4,U8 Seashell Playa3 | 85655.1 | 73971.06 | 0 | 73971.06
MDF Factory | MDF FACTORY IPC (26) | 26 | MDF Factory26 | 20422067.95 | 12481160.25 | 5399138.77 | 17880299.02
Ministries Buildings | Min long lead Ipc4 | 4 | Ministries Buildings4 | 9323069 | 7854280 | 0 | 7854280
Cairo Monorail - 6th October | FPC Monorail |  | Cairo Monorail - 6th October | 415000 | 392280 | 0 | 392280
GOV2 - Infra | Gov2 ipc18+19 | 18 | GOV2 - Infra18 | 18621245.71 | 44407465.9255 | 5459594.17 | 49867060.0955
Ain Sokhna Port Development | IPC#18 Sokhna Port | 18 | Ain Sokhna Port Development18 | 1481544 | 1009287.17 | 0 | 1009287.17
Capital One | inv ( 8 ) Captal one | 8 | Capital One8 | 946708.37 | 937241.2885 | 0 | 937241.2885
Katameya Creeks - RME | IPC00000003 | 3 | Katameya Creeks - RME3 | 9219.82 | 8164.15 | 0 | 8164.15
El-Herafeen brigde | IPC#1&2 | 1 | El-Herafeen brigde1 | 1263235 | 1032775.58 | 0 | 1032775.58
WADY EL-NATROUN BRIDGE(HST) | IPC# 12 WADI | 12 | WADY EL-NATROUN BRIDGE(HST)12 | 1119960 | 1017035.68 | 0 | 1017035.68
Air Defense College | Air7 Fin IPC2 | 2 | Air Defense College2 | 18663776 | 14703820 | 0 | 15734139
ORA ZED-Ph 2-Pkgs A&D | ORA Ph.2 - IPC 14 | 14 | ORA ZED-Ph 2-Pkgs A&D14 | 12548033.06 | 15106729.373 | 1911092.27 | 17017821.643
MDF Factory | MDF - IPC 25 | 25 | MDF Factory25 | 10389113.75 | 4423185.2685 | 10664897.85 | 15088083.1185
Hyper One Badr | INV ( 10 ) Hipper | 10 | Hyper One Badr10 | 1090333.7 | 970396.98 | 0 | 970396.98
MDF Factory | MDF - IPC19 | 19 | MDF Factory19 | 12911250.9 | 8856995.725 | 2093318.3 | 10950314.025
MDF Factory | MDF 2 - IPC11 | 11 | MDF Factory11 | 411623.92 | 415740.1688 | 0 | 415740.1688
HST - 6 October - Arab Cont. | IPC#1 HSR ARAB | 1 | HST - 6 October - Arab Cont.1 | 2621800 | 1040770 | 0 | 1040770
Egat Rolling Mill no.4 | rolling mill- IPC11 | 11 | Egat Rolling Mill no.411 | 16145745 | 13154777.42 | 3636797.38 | 16791574.8
Air Defence College | IPC000009 | 9 | Air Defence College9 | 1124369.82 | 954589.98 | 0 | 954589.98
Kattameya Creeks | katameyacreeks-IPC25 | 25 | Kattameya Creeks25 | 45327391.41 | 45191848.31 | 1948638.75 | 47140487.06
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 26 | 26 | ORA ZED - Ph 01B - Pkgs A&D26 | 68520137.14 | 6863669.1846 | 57181187.41 | 64044856.5946
U3 & U5 | IPC2-TR55 | 2 | U3 & U52 | 439984.49 | 375220.61 | 0 | 375220.61
U4,U8 Seashell Playa | IPC007 TR60 | 7 | U4,U8 Seashell Playa7 | 431538.63 | 372676.76 | 0 | 372676.76
Irrigation Tank | IPC001 Tank | 1 | Irrigation Tank1 | 815585.1 | 704339.29 | 0 | 704339.29
EMAAR-Pkg#162/163- Marassi | ipc42 Emar PKG177 | 42 | EMAAR-Pkg#162/163- Marassi42 | 2102245.55 | 4316245.8075 | 1120.74 | 4317366.5475
HSR-6th of October | IPC#7 HSR | 7 | HSR-6th of October7 | 1671344 | 1447805.88 | 0 | 1447805.88
EGAT Mechanical Installations | Egat Mechnical ipc 7 | 7 | EGAT Mechanical Installations7 | 3744476.64 | 2845427.8 | 936119.1704 | 3781546.9704
Business District Hyde Park | INV ( 1 ) HY Bark | 1 | Business District Hyde Park1 | 795000 | 678930 | 0 | 678930
Capital One | inv ( 7 ) Captal one | 7 | Capital One7 | 1168346.98 | 1156663.509 | 0 | 1156663.509
MDF Factory | MDF FACTORY IPC10 | 10 | MDF Factory10 | 7456023.43 | 10970767.5315 | 1032725.89 | 12003493.4215
DP World Basin 2 Ph2 | Dp world ipc 12 | 12 | DP World Basin 2 Ph212 | 54623534 | 40236573.85 | 8155016.63 | 48391590.48
MDF Factory | MDF Factory IPC23 | 23 | MDF Factory23 | 37280017.77 | 14012432.1696 | 19477192.18 | 33489624.3496
EGAT Pelletizing Plant | RO Eriction ipc 1 | 1 | EGAT Pelletizing Plant1 | 6000000 | 6660000 | 0 | 6660000
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 - IPC12 | 12 | ORA ZED-Ph 2-Pkgs A&D12 | 16689354.47 | 15225579.9035 | 1929327.26 | 17154907.1635
Ora Zed Landscape Ph1 | ipc 1 Ora landscape | 1 | Ora Zed Landscape Ph11 | 2611606.83 | 2304743.0232 | 274218.72 | 2578961.7432
DP World Basin 2 Ph2 | ipc 3 | 3 | DP World Basin 2 Ph23 | 38504541.13 | 28493360.4387 | 5775681.17 | 34269041.6087
Sokhna Port Expansion | Spx.2 ipc 07 | 7 | Sokhna Port Expansion7 | 4559269.9 | 2764829.36 | 1154245.58 | 3919074.94
Wady El Natroon Bridge | WADY ELNATRON IPC 01 | 1 | Wady El Natroon Bridge1 | 51983282.43 | 15425224.3757 | 0 | 35854126.5757
Kattameya Creeks | Katamya Creeks ipc30 | 30 | Kattameya Creeks30 | 55298315.11 | 43084120 | 14139199.7 | 57223319.7
Ministries Buildings | Minis Core IPC12 | 12 | Ministries Buildings12 | 13450696 | 11331810 | 0 | 11331810
RING ROAD MARYOTIA EXPANSION | Mryotia - IPC02 | 2 | RING ROAD MARYOTIA EXPANSION2 | 25572365.97 | 12664735.77 | 0 | 12664735.77
RING ROAD MARYOTIA EXPANSION | ElMarg IPC03 | 3 | RING ROAD MARYOTIA EXPANSION3 | 16544270.99 | 14603087.4595 | 0 | 14603087.4595
RING ROAD MARYOTIA EXPANSION | El-Marg IPC05 | 5 | RING ROAD MARYOTIA EXPANSION5 | 2520054.67 | 2231198.92 | 0 | 2231198.92
MDF Factory | Mdf factory ipc 42 | 42 | MDF Factory42 | 19536964.22 | 7602001.04 | 5864798.66 | 13466799.7
Air Defense College | Air Dev sihi IPC1 | 1 | Air Defense College1 | 7144552 | 1203150 | 4752000 | 5955150
Port Said Port Silos | port said silosipc11 | 11 | Port Said Port Silos11 | 5057462.52 | 4473647.986 | 505746.25 | 4979394.236
Get Business Complex | INV ( 5 ) GET | 5 | Get Business Complex5 | 838442.4 | 788135.86 | 0 | 788135.86
ORA-ZED Towers P01B | IPC007 | 7 | ORA-ZED Towers P01B7 | 278338.2 | 246468.48 | 0 | 246468.48
Kattameya Creeks | Katamya Creeks ipc36 | 36 | Kattameya Creeks36 | 64452457.92 | 50530224.78 | 16258366.39 | 66788591.17
EGAT Pelletizing Plant | Admin Building ipc 2 | 2 | EGAT Pelletizing Plant2 | 53673231.5 | 23616221.86 | 32203938.9 | 55820160.76
Air Defence College | IPC00010 | 10 | Air Defence College10 | 738309.8 | 626825.02 | 0 | 626825.02
U4,U8 Seashell Playa | IPC001TR0060 | 1 | U4,U8 Seashell Playa1 | 888790.35 | 767559.34 | 0 | 767559.34
Air Defence College | IPC000007 | 7 | Air Defence College7 | 914159.54 | 776121.45 | 0 | 776121.45
Air Defence College | IPC0000008 | 8 | Air Defence College8 | 37865.02 | 32147.41 | 0 | 32147.41
Abo Shanab El Agamien | abo shanab ipc 3 | 3 | Abo Shanab El Agamien3 | 16847053.46 | 15139736.4 | 4206110.44 | 19345846.84
Abo Shanab El Agamien | ABO SHANAB IPC2 | 2 | Abo Shanab El Agamien2 | 10144780.21 | 20803096.04 | 0 | 20803096.04
ORA ZED-Ph 2-Pkgs A&D | Ora Zed (2) ipc 17 | 17 | ORA ZED-Ph 2-Pkgs A&D17 | 9516947.6 | 8988166.1131 | 1130124 | 10118290.1131
EDNC Hardscape Package | sorealhardscapeIPC12 | 12 | EDNC Hardscape Package12 | 2146120.25 | 2109293.391 | 0 | 2109293.391
Faculty of Medicine | mansora finish ipc09 | 9 | Faculty of Medicine9 | 7118203.18 | 5310846.8319 | 1067730.57 | 6378577.4019
Seashell Playa 5 Villas | Playa c038 - ipc 2 | 2 | Seashell Playa 5 Villas2 | 1451.6 | 1503.85 | 0 | 1503.85
Ministries Buildings | Minis Core IPC13 | 13 | Ministries Buildings13 | 9298463 | 7833550 | 0 | 7833550
EPICO 3 Facility | Eipico - ipc 6 | 6 | EPICO 3 Facility6 | 6910722.77 | 5949568.74 | 2014420.72 | 7963989.46
Air Defence College | IPC0015 TR46 | 15 | Air Defence College15 | 462908.64 | 393009.43 | 0 | 393009.43
Air Defense College | Air Dev Alum IPC1 | 1 | Air Defense College1 | 34615195 | 7139800 | 21800000 | 28939800
East Port Said Industrial Area | FPC Orascom HA JV |  | East Port Said Industrial Area | 336092 | 199065.45 | 0 | 199065.45
Air Defense College | Air Dev finsh IPC1 | 1 | Air Defense College1 | 150765535.8 | 29417950 | 95700000 | 126015484.8
EGAT Mechanical Installations | Egat mech Equip ipc1 | 1 | EGAT Mechanical Installations1 | 4715732.2 | 3583484.902 | 1178933.05 | 4762417.952
Port Said Port Silos | ipc 14 port said | 14 | Port Said Port Silos14 | 2803566.38 | 2480905.1552 | 280356.64 | 2761261.7952
Port Said Port Silos | portsaid silos ipc17 | 17 | Port Said Port Silos17 | 7676679.55 | 6794573.092 | 767667.96 | 7562241.052
El Khatatba Bridge | EL KHATTBA IPC 7+8+9 | 7 | El Khatatba Bridge7 | 60988369.64 | 47315333.8936 | 0 | 54315333.8936
EMAAR-Pkg#162/163- Marassi | Emaar pkg#177 ipc 46 | 46 | EMAAR-Pkg#162/163- Marassi46 | 5007444.76 | 3319156.348 | 1500000 | 4819156.348
Faculty of Medicine | mansora finish ipc10 | 10 | Faculty of Medicine10 | 7295367.62 | 5443038.3238 | 1094305.14 | 6537343.4638
SOL Town PKG.220 | pgk#220 ipc (1) | 1 | SOL Town PKG.2201 | 12159328.08 | 8261597.76 | 2992468.34 | 11254066.1
British International School | bis ipc 4 | 4 | British International School4 | 8650967.52 | 9749342.807 | 2412436.23 | 12161779.037
British International School | BIS IPC 3+ | 3 | British International School3 | 7190987.06 | 1015237.193 | 2849417.81 | 3864655.003
SEASHELL TECHNICAL ROOM | IPC0003TR65 | 3 | SEASHELL TECHNICAL ROOM3 | 122521.28 | 69859.38 | 0 | 69859.38
Wadi Halfa Port | wady halfa esc.1 |  | Wadi Halfa Port | 14802651.3 | 14076920.267 | 0 | 14076920.267
Katameya Creeks - RME | IPC007 TR53 | 7 | Katameya Creeks - RME7 | 177303.61 | 158382.35 | 0 | 158382.35
RING ROAD MARYOTIA EXPANSION | MARIOTYA IPC 17 | 17 | RING ROAD MARYOTIA EXPANSION17 | 6790889.14 | 5287432.8 | 0 | 5287432.8
Cairo-Alex Railway | Cairo-alex ipc 36 | 36 | Cairo-Alex Railway36 | 16514223.81 | 11468729.61 | 1733993.5 | 13202723.11
Cairo-Alex Railway | cairo-alex ipc 27 | 27 | Cairo-Alex Railway27 | 35051897.79 | 24323344.11 | 3680449.27 | 28003793.38
Sixty Iconic Tower | inv ( 2 ) sixty | 2 | Sixty Iconic Tower2 | 1356885 | 1275471.9 | 0 | 1275471.9
Al-Parco | INV ( 4 ) ALparco | 4 | Al-Parco4 | 4279952.5 | 4023155.34 | 0 | 4023155.34
Venice Mall | inv ( 1 ) vensia | 1 | Venice Mall1 | 76160 | 75398.4 | 0 | 75398.4
Olympic Multi – Sports Hall | OLYMPIC FIN-IPC01 | 1 | Olympic Multi – Sports Hall1 | 21103731.73 | 2217431.02 | 0 | 2217431.02
Port Said Port Silos | port said silosipc16 | 16 | Port Said Port Silos16 | 12501707.07 | 11072420.0228 | 1250170.71 | 12322590.7328
EGAT Lock & Load | EGAT L&L IPC7 | 7 | EGAT Lock & Load7 | 1415984.07 | 1331025.0235 | 141598.41 | 1472623.4335
MDF Factory | mdf factory ipc 33 | 33 | MDF Factory33 | 18965945.93 | 10638561.7072 | 7963981.26 | 18602542.9672
Creeks URBN-K | KatamUrbnk ipc ( 2) | 2 | Creeks URBN-K2 | 19977718.2 | 3863139 | 16088291.57 | 19951430.57
Faculty of Medicine | mansora finish ipc11 | 11 | Faculty of Medicine11 | 4515174.29 | 3368595.1616 | 677277 | 4045872.1616
Faculty of Medicine | mansora finish ipc12 | 12 | Faculty of Medicine12 | 7819043.81 | 5833780.5619 | 1172856.57 | 7006637.1319
Sokhna Port Expansion | esc.1:10 spx1 |  | Sokhna Port Expansion | 34853225.9 | 20947176.6 | 0 | 30947176.6
New Giza Teaching Hospital | New Giza ipc ( 18) | 18 | New Giza Teaching Hospital18 | 24967998.04 | 15759862.1875 | 1871545.2245 | 17631407.412
Sokhna Port Expansion | sokhna port ex ipc14 | 14 | Sokhna Port Expansion14 | 16895917.4 | 6704080.85 | 3379183.48 | 15083264.33
Tarek Abdel-Hakim Center | TAH ipc 10 | 10 | Tarek Abdel-Hakim Center10 | 7158353.14 | 5508352.73 | 644251.78 | 6152604.51
Tarek Abdel-Hakim Center | TAH ipc 6 | 6 | Tarek Abdel-Hakim Center6 | 1234570.04 | 950001.64 | 111111.3 | 1061112.94
Tarek Abdel-Hakim Center | TAH ipc02 | 2 | Tarek Abdel-Hakim Center2 | 2619891.03 | 2016006.15 | 235790.19 | 2251796.34
HST - 6 October - Arab Cont. | IPC 2 HSR ARAB | 2 | HST - 6 October - Arab Cont.2 | 2062300 | 1769659.63 | 0 | 1769659.63
Air Defence College | TR46-IPC1FEB | 1 | Air Defence College1 | 900680 | 764677.32 | 0 | 764677.32
Sokhna Port Expansion | sokhna port ex ipc15 | 15 | Sokhna Port Expansion15 | 14245622.5 | 4368115.65 | 2849124.5 | 12217240.15
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 18 | 18 | ORA ZED-Ph 2-Pkgs A&D18 | 15364644.61 | 13333027.7475 | 1686708.33 | 15019736.0775
SSC Suez Steel Company Project | R.O IPC (2) | 2 | SSC Suez Steel Company Project2 | 1543124.26 | 0 | 526359.69 | 1712867.9264
Monoril | inv ( 2 ) monoril | 2 | Monoril2 | 2472386.9 | 462097.56 | 0 | 462097.56
Seashell Playa 5 Villas | Playa -c038 ipc 6 | 6 | Seashell Playa 5 Villas6 | 96357.37 | 27877.46 | 0 | 27877.46
Egat Rolling Mill no.4 | Rolling Mill ipc 14 | 14 | Egat Rolling Mill no.414 | 433210006.09 | 385850769.7576 | 64687636.576 | 450538406.3336
ora zed orascom | IPC03TR0069 | 3 | ora zed orascom3 | 1066558.05 | 975100.71 | 0 | 975100.71
ora zed orascom | IPC 001 TR0069 | 1 | ora zed orascom1 | 129308.62 | 73676.72 | 0 | 73676.72
ora zed orascom | IPC02TR0069 | 2 | ora zed orascom2 | 409594.56 | 374471.822 | 0 | 374471.822
Olympic Multi – Sports Hall | Olympic Elec IPC1 | 1 | Olympic Multi – Sports Hall1 | 30233454 | 4864900 | 20394000 | 25258900
Cairo-Alex Railway | Escalation ipc 29:39 | 29 | Cairo-Alex Railway29 | 40207347.22 | 32145375.561 | 0 | 32145375.561
KATAMYA GREEKS LAND SCAPE STAR | IPC01TR0081 | 1 | KATAMYA GREEKS LAND SCAPE STAR1 | 10196792 | 10080548.3125 | 0 | 10080548.3125
Beni Suef Substation R61 | 1 final bani suef |  | Beni Suef Substation R61 | 3726195.81 | 3608397.35 | 0 | 3608397.35
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 23 | 23 | ORA ZED-Ph 2-Pkgs A&D23 | 1051680.08 | 534269.994 | 67588.37 | 601858.364
New Giza Teaching Hospital | New Giza Hos ipc 24 | 24 | New Giza Teaching Hospital24 | 29604524.13 | 4494905.8665 | 15934743.3 | 21429649.1665
VILLA CLUSTER C | IPC2&3TR0078 | 2 | VILLA CLUSTER C2 | 149742 | 129317.19 | 0 | 129317.19
VILLA CLUSTER C | IPC01TR0078 | 1 | VILLA CLUSTER C1 | 182595 | 83789.04 | 0 | 83789.04
VILLA CLUSTRER B | IPC05TR0077 | 5 | VILLA CLUSTRER B5 | 76986 | 66485.11 | 0 | 66485.11
U3 & U5 | IPC14TR0055 | 14 | U3 & U514 | 67890.85 | 58630.54 | 0 | 58630.54
Mohamed Ali Palace Restoration | Mohamed Ali IPC02 | 2 | Mohamed Ali Palace Restoration2 | 2130706.9 | 1115219.3 | 891500 | 2006719.3
New Giza Teaching Hospital | new giza IPC8 | 8 | New Giza Teaching Hospital8 | 18146654.72 | 12772392.376 | 1948641.22 | 14721033.596
New Giza Teaching Hospital | new giza- IPC12 | 12 | New Giza Teaching Hospital12 | 30417445.78 | 22544712.249 | 3413984.84 | 25958697.089
Jawhara Palace Restoratio | Gawhara IPC7 | 7 | Jawhara Palace Restoratio7 | 805468.71 | 430073.04 | 201367.18 | 631440.22
Faculty of Medicine | mansora finish ipc15 | 15 | Faculty of Medicine15 | 18818900.95 | 14041319.478 | 2822835.15 | 16864154.628
Blue Planet Sharm. | IPC01TR0082 | 1 | Blue Planet Sharm.1 | 3067328.84 | 2772865.27 | 0 | 2772865.27
EGAT Pelletizing Plant | Egat Peletizing ip20 |  | EGAT Pelletizing Plant | 288087581.53 | 284426280.451 | 15202204.3355 | 299628484.7865
EGAT Mechanical Installations | Egat Mech Equip ipc3 | 3 | EGAT Mechanical Installations3 | 37089317.7 | 28184172.5069 | 9272329.43 | 37456501.9369
U6T11 PART1 Palay | IPC03TR0075 | 3 | U6T11 PART1 Palay3 | 11605 | 10602.33 | 0 | 10602.33
New Giza Teaching Hospital | New Giza Hosp ipc15 | 15 | New Giza Teaching Hospital15 | 22076508.27 | 8639287.3435 | 9433643.48 | 18072930.8235
New Giza Hos | IPC01TR0073 | 1 | New Giza Hos1 | 37026.08 | 31772.1 | 0 | 31772.1
EGAT Injection | IPC11TR0048 | 11 | EGAT Injection11 | 62266.05 | 53430.5 | 0 | 53430.5
Ain Sokhna Bridge | Inv ( 3 ) A.S | 3 | Ain Sokhna Bridge3 | 999373.19 | 829854.43 | 0 | 829854.43
HST Bridges-Sokhna & Mahager | sokhna ipc11+12+13 | 11 | HST Bridges-Sokhna & Mahager11 | 88535946.43 | 8673315.8657 | 0 | 69212368.9657
Faculty of Medicine | mansora finish ipc13 | 13 | Faculty of Medicine13 | 10289196.19 | 7676883.0381 | 1543379.43 | 9220262.4681
Faculty of Medicine | Mansoura UNI IPC07 | 7 | Faculty of Medicine7 | 20048289.52 | 16967969.04 | 1002414.48 | 17970383.52
GOV2 - Infra | GOV2 IPC13+14 | 13 | GOV2 - Infra13 | 59475220.33 | 26834651.1805 | 3939718.2 | 30774369.3805
NUCA R05 - Z02 | R05(2) ipc 29+30 | 29 | NUCA R05 - Z0229 | 43098025.9 | 32757037.12 | 4145164.9 | 36902202.02
EIPICO Factory | IPC04 TR0054 | 4 | EIPICO Factory4 | 13401.6 | 11499.91 | 0 | 11499.91
Seashell Playa 5 Villas | playa-c045 ipc 6 | 6 | Seashell Playa 5 Villas6 | 16932.79 | 13000.86 | 0 | 13000.86
U7-SEASHELL | IPC11TR0064 | 11 | U7-SEASHELL11 | 318171.36 | 274084.83 | 0 | 274084.83
Astoria Sharm elSheikh | Woldorf sharm ipc 6 | 6 | Astoria Sharm elSheikh6 | 172304.78 | 621397.339 | 0 | 621397.339
New Giza Teaching Hospital | New Giza ipc (21) | 21 | New Giza Teaching Hospital21 | 12130160.82 | 4614812.92 | 1724826.24 | 10339639.16
Ain Sokhna Port Development | IPC26 elsokhna | 26 | Ain Sokhna Port Development26 | 587716 | 143440 | 0 | 143440
DP World Basin 2 Ph2 | Dp world PH2 ipc (9) | 9 | DP World Basin 2 Ph29 | 27736619.9 | 20524928.94 | 4160492.98 | 24685421.92
Qasr Rashwan - Lot B | QASRRASHWANLOT BIPC2 | 2 | Qasr Rashwan - Lot B2 | 47683707.83 | 39817532 | 11146475.84 | 50964007.84
Seashell Playa 5 Villas | Playa c038 ipc 8 | 8 | Seashell Playa 5 Villas8 | 75415.45 | 56128.78 | 0 | 56128.78
seashell Playa | IPC29TR0038 | 29 | seashell Playa29 | 93920 | 43642.75 | 0 | 43642.75
NUCA R05 - Z02 | R05(2) ipc 33 | 33 | NUCA R05 - Z0233 | 20759999.65 | 14925414.0035 | 1906629.1 | 16832043.1035
ORA-ZED Towers P01B | IPC13 TR51 | 13 | ORA-ZED Towers P01B13 | 45403 | 40204.36 | 0 | 40204.36
EIPICO C002-23 | IPC04TR0068 | 4 | EIPICO C002-234 | 24832 | 21308.34 | 0 | 21308.34
MDF Factory | ipc 15- MDF Local | 15 | MDF Factory15 | 5402784.59 | 2970230 | 2486382.36 | 5456612.36
Central Capital | INV ( 2 ) Central Ca | 2 | Central Capital2 | 162792 | 153024.48 | 0 | 153024.48
SSC Suez Steel Company Project | Revamp 2 SMP2- IPC 1 | 1 | SSC Suez Steel Company Project1 | 38822768.95 | 20964295.228 | 19411384.48 | 40375679.708
DP World Basin 2 Ph2 | Dp world ipc (4) | 4 | DP World Basin 2 Ph24 | 37025201.2 | 27398648.888 | 5553780.18 | 32952429.068
Mivida BP#189 | Emaar pkg#189 ipc 18 | 18 | Mivida BP#18918 | 18563752.6 | 20024965.62 | 2557410.37 | 22582375.99
Al Montaza Hotels - Alexandria | inv ( 5 ) Montazha | 5 | Al Montaza Hotels - Alexandria5 | 830679.3 | 826579.297 | 0 | 826579.297
ZED Phase 2 | IPC04TR0062 | 4 | ZED Phase 24 | 9698.943 | 8239.25 | 0 | 8239.25
Luxor North Axis Bridge | IPC final HA luxor o |  | Luxor North Axis Bridge | 1134519 | 759721.91 | 0 | 759721.91
ACWA POWER & NOMAC HQ | Acwa Power ipc 1. | 1 | ACWA POWER & NOMAC HQ1 | 85714.29 | 90000 | 0 | 90000
Mivida BP#189 | Emaar Pkg#189 ipc22 | 22 | Mivida BP#18922 | 23140993.33 | 17552608.8365 | 11648218.95 | 29200827.7865
Ora Zed Landscape Ph1 | ora landscape ipc 12 | 12 | Ora Zed Landscape Ph112 | 7506327.07 | 6030251.47 | 788164.34 | 6818415.81
EGAT Injection | IPC12TR0048 | 12 | EGAT Injection12 | 421941.77 | 362068.23 | 0 | 362068.23
R05 (New) | IPC06TR0059 | 6 | R05 (New)6 | 149869 | 127103.9 | 0 | 127103.9
Air Defence College | IPC20TR0046 | 20 | Air Defence College20 | 116192.22 | 98647.2 | 0 | 98647.2
Egyptian Exchange building | IPC12&13 TR39 | 12 | Egyptian Exchange building12 | 47993.87 | 41868.58 | 0 | 41868.58
Waldorf Astoria Cairo | Woldorf Astor ipc 22 | 22 | Waldorf Astoria Cairo22 | 10800888.32 | 1999998.286 | 0 | 9327545.216
EL Baragil Bridge | inv ( 3 ) Baragill B | 3 | EL Baragil Bridge3 | 4166890 | 3916876.6 | 0 | 3916876.6
RADAMIS CITY | IPC01TR0084 | 1 | RADAMIS CITY1 | 375875.1 | 332837.39 | 0 | 332837.39
Mivida BP#189 | pkg#189-IPC 7 | 7 | Mivida BP#1897 | 49447555.48 | 41131640.064 | 4934794.35 | 46066434.414
Air Defense College | Air Dev Elec IPC3 | 3 | Air Defense College3 | 17021156 | 14339910 | 0 | 14339910
Port Said Port Silos | PORT SAID IPC 22 | 22 | Port Said Port Silos22 | 6713332.67 | 5651416.0035 | 671333.27 | 6322749.2735
ORA-ZED Towers P01B | IPC14TR0051 | 14 | ORA-ZED Towers P01B14 | 338998.03 | 300182.76 | 0 | 300182.76
Haramein Columns Transfer | Harmain ipc01 | 1 | Haramein Columns Transfer1 | 672000 | 384000 | 576000 | 672000
Seashell Playa 5 Villas | playa-c038 ipc 10 | 10 | Seashell Playa 5 Villas10 | 98071.67 | 84694.55 | 0 | 84694.55
Tarek AbdelHakim Center - KSA | K0001,2 |  | Tarek AbdelHakim Center - KSA | 8530625.81 | 0 | 0 | 8829197.72
Seashell Playa 5 Villas | Playa C045- IPC 8 | 8 | Seashell Playa 5 Villas8 | 89569.81 | 10805.81 | 0 | 10805.81
ZED Phase 2 | IPC06TR0062 | 6 | ZED Phase 26 | 71183.98 | 60470.63 | 0 | 60470.63
Beymen Fit Out | Emaar pkg#205 ipc7 | 7 | Beymen Fit Out7 | 13811986.27 | 6631409.93 | 6182724.5 | 12814134.43
Jawhara Palace Restoratio | Gawhara IPC2 | 2 | Jawhara Palace Restoratio2 | 2251351 | 1511775.91 | 562837.75 | 2074613.66
PLAYA Main Gate | IPC01TR0092 | 1 | PLAYA Main Gate1 | 155883 | 134620.56 | 0 | 134620.56
ACWA POWER & NOMAC HQ | Acwa power ipc 2 | 2 | ACWA POWER & NOMAC HQ2 | 185714.29 | 194459.5267 | 0 | 194594.6461
Diplomatic District - Infra | diplo ipc 16:25 | 16 | Diplomatic District - Infra16 | 212015193.47 | 155990435.38 | 6227631.11 | 162218066.49
HST Bridges-Sokhna & Mahager | sokhna bri esc.17+18 |  | HST Bridges-Sokhna & Mahager | 22048150.62 | 19657734.21 | 0 | 19657734.21
EIPICO Factory | IPC005TR0054 | 5 | EIPICO Factory5 | 24663.69 | 18504.54 | 0 | 6168.18
The Open Channel Project | Open chanel2 IPC1 | 1 | The Open Channel Project1 | 227652446.67 | 81660860 | 104857050.55 | 186517910.55
Irrigation Tank | IPC07TR0061 | 7 | Irrigation Tank7 | 161702.49 | 139646.29 | 0 | 139646.29
EMAAR-Pkg#162/163- Marassi | Emaar pkg#163 ipc 32 | 32 | EMAAR-Pkg#162/163- Marassi32 | 5753296.59 | 4821275.6 | 0 | 4821275.6
DP World Basin 2 Ph2 | Dp World ipc 13 | 13 | DP World Basin 2 Ph213 | 17615925.7 | 15678173.87 | 0 | 15678173.87
MAF HQ Renovation | carrefour RBS IPC 5 | 5 | MAF HQ Renovation5 | 799314.48 | 537538.96 | 209820.05 | 747359.01
Open Channal | IPC05TR0074 | 5 | Open Channal5 | 206751.68 | 178344 | 0 | 178344
Air Defence College | IPC23TR0046 | 23 | Air Defence College23 | 38601.9 | 32773 | 0 | 32773
RADAMIS CITY | IPC02TR0084 | 2 | RADAMIS CITY2 | 36031.95 | 31906.29 | 0 | 31906.29
MDF Factory | mdf local -ipc 18 | 18 | MDF Factory18 | 4222095.24 | 4264311.8578 | 0 | 4264311.8578
Port Said Grain Storage | Rent-001 | 1 | Port Said Grain Storage1 | 81050 | 89600.77 | 0 | 89600.77
Koumassi Flyover | INV 5 | 5 | Koumassi Flyover5 | 144227401 | 129804661 | 0 | 129804661
EPICO 3 Facility | EIPICO ipc 16 | 16 | EPICO 3 Facility16 | 54812520.18 | 26363887.4 | 26509463.43 | 52873350.83
Main Spine | IPC02TR0096 | 2 | Main Spine2 | 279278.12 | 220284.88 | 0 | 220284.88
NUCA R05 - Z02 | R05 2 IPC38 | 38 | NUCA R05 - Z0238 | 12550873.3 | 9307818.385 | 1244727.98 | 10552546.365
Senator | Inv ( 1 ) Sentor | 1 | Senator1 | 630091 | 0 | 0 | 0
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 30+31 | 30 | ORA ZED-Ph 2-Pkgs A&D30 | 10058718.7 | 3791012.07 | 625067.79 | 4416079.86
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 38 | 38 | ORA ZED - Ph 01B - Pkgs A&D38 | 19627458.83 | 17627053.17 | 514793.83 | 18141847
NUCA R05 - Z02 | R05(2) ipc 43 | 43 | NUCA R05 - Z0243 | 16120059.71 | 10598999.12 | 1480670.8 | 12079669.92
Wadi Halfa Port | WADY HALFA IPC05 | 5 | Wadi Halfa Port5 | 5072099.52 | 2984537.1 | 1065140.9 | 4049678
Koumassi Flyover | INV no7 | 7 | Koumassi Flyover7 | 209390747.91 | 591705701.61 | 0 | 197235233.87
EGAT Pelletizing Plant | RO2 ipc 2 | 2 | EGAT Pelletizing Plant2 | 1807831.25 | 1880144.5 | 0 | 1880144.5
Luxor North Axis Bridge-Off | IPC#4 Offshore | 4 | Luxor North Axis Bridge-Off4 | 1618800 | 1473781 | 0 | 1473781
Luxor North Axis Bridge-Off | IPC 5 luxoroff | 5 | Luxor North Axis Bridge-Off5 | 60574 | 47824 | 0 | 47824
EGAT Lock & Load | Egat Lock&Load ipc15 | 15 | EGAT Lock & Load15 | 19312258.25 | 18153522.75 | 1931225.83 | 20084748.58
DP World Basin 2 Ph2 | Dp World ipc 14 | 14 | DP World Basin 2 Ph214 | 21130152.28 | 18805485.48 | 0 | 18805485.48
Al Alamein Marina Towers | IPC#1 Marina Towers | 1 | Al Alamein Marina Towers1 | 2174997.85 | 1868125.47 | 0 | 1868125.47
Mivida BP#189 | PKG#189 IPC 24 | 24 | Mivida BP#18924 | 16112816.1 | 13803484.915 | 11685453.37 | 25488938.285
SSC Suez Steel Company Project | NEW Gas station ipc4 | 4 | SSC Suez Steel Company Project4 | 6707619.99 | 4628257.7896 | 2012286 | 6640543.7896
MDF Factory | MDf Equip -ipc 22 | 22 | MDF Factory22 | 203073.94 | 205104.6816 | 0 | 205104.6816
MDF Factory | MDF Factory ipc 37 | 37 | MDF Factory37 | 18482561.46 | 4465149.39 | 7763808.28 | 12228957.67
Seashell Playa 5 Villas | Playa c469 - ipc 1 | 1 | Seashell Playa 5 Villas1 | 345870 | 315986.83 | 0 | 315986.83
HSR | inv.1 HSR-oct2-5-24 | 1 | HSR1 | 81800571.89 | 0 | 99375886.24 | 99375886.24
Al-Parco | INV ( 8 ) ALparco | 8 | Al-Parco8 | 2102406 | 860732.04 | 0 | 860732.04
Al-Parco | INV ( 6 ) ALparco | 6 | Al-Parco6 | 1433390 | 1347386.6 | 0 | 1347386.6
EIPICO C002-23 | IPC07TR0068 | 7 | EIPICO C002-237 | 81334.5 | 69793.11 | 0 | 69793.11
Olympic MultiSport Hall | IPC04TR0079 | 4 | Olympic MultiSport Hall4 | 88250.4 | 74262.71 | 0 | 74262.71
Koumassi Flyover | INV no8 | 8 | Koumassi Flyover8 | 118967977.65 | 107071179.89 | 0 | 107071179.89
Irrigation Tank | IPC10TR0061 | 10 | Irrigation Tank10 | 188224.4 | 162550.59 | 0 | 162550.59
Sokhna Port Expansion | sokhna port ex 17+18 |  | Sokhna Port Expansion | 42026380.1 | 28702779.44 | 8825539.85 | 37528319.29
RING ROAD MARYOTIA EXPANSION | Escalation13:19. |  | RING ROAD MARYOTIA EXPANSION | 34267873.67 | 30336910.98 | 0 | 30336910.98
RING ROAD MARYOTIA EXPANSION | elmarg 11 final |  | RING ROAD MARYOTIA EXPANSION | 1786099.76 | 8888501.068 | 0 | 8888501.068
HST Bridges-Sokhna & Mahager | SOKHNABRI.IPC21FINAL | 21 | HST Bridges-Sokhna & Mahager21 | 6514011.29 | 4685138 | 0 | 4685138
Sokhna Port Expansion | spx.2 ipc 4 | 4 | Sokhna Port Expansion4 | 12041549 | 8297916.02 | 2408310 | 10706226.02
RING ROAD MARYOTIA EXPANSION | Mariotya ipc20+21+22 | 20 | RING ROAD MARYOTIA EXPANSION20 | 13407964 | 8461342.16 | 0 | 11701263.16
RING ROAD MARYOTIA EXPANSION | Mariotya Rem.esc1:22 |  | RING ROAD MARYOTIA EXPANSION | 24626471.33 | 23788774.43 | 0 | 23788774.43
Abou Ghaleb Bridge | Abo ghaleb ipc 11:18 | 11 | Abou Ghaleb Bridge11 | 39992967.52 | 24492789.55 | 0 | 35492789.55
RING ROAD MARYOTIA EXPANSION | mariotya ipc15 | 15 | RING ROAD MARYOTIA EXPANSION15 | 29097528.02 | 11321780.291 | 0 | 27321780.291
Luxor North Axis Bridge | IPC#1-Luxor onshore | 1 | Luxor North Axis Bridge1 | 1162500 | 1069500 | 0 | 1069500
MDF Factory | MDF Equip ipc 25 | 25 | MDF Factory25 | 631230.84 | 637190.72 | 0 | 637190.72
Faculty of Medicine | IPC23FINISH MANSOURA | 23 | Faculty of Medicine23 | 15044995.24 | 11225320 | 2256749.29 | 13482069.29
Ring Road - Service Road | SERVICE ROAD IPC 1 | 1 | Ring Road - Service Road1 | 42094949.9 | 16760404.48 | 0 | 36760404.48
Roubiky Hassan Allam | IPC#1#Roubiky | 1 | Roubiky Hassan Allam1 | 377625 | 328533.75 | 0 | 328533.75
NUCA R05 - Z02 | RO5(2) IPC 50 | 50 | NUCA R05 - Z0250 | 24169557.35 | 11116977.38 | 1661467.3 | 12778444.68
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 39 | 39 | ORA ZED - Ph 01B - Pkgs A&D39 | 9971577.14 | 7606231.63 | 0 | 7606231.63
EIPICO C002-23 | IPC09TR0068 | 9 | EIPICO C002-239 | 72112.1 | 61879.39 | 0 | 61879.39
BISC New Society Bldg | Society Build ipc1 | 1 | BISC New Society Bldg1 | 2946690.48 | 1732655 | 928207 | 2660862
Wadi Halfa Port | wady halfa claim |  | Wadi Halfa Port | 8796238.1 | 8364831 | 0 | 8364831
Roubiky Hassan Allam | IPC#3#Roubiky | 3 | Roubiky Hassan Allam3 | 527250 | 439726.5 | 0 | 439726.5
ORA ZED-Ph 2-Pkgs A&D | Ora Ph2 ipc 37+38 | 37 | ORA ZED-Ph 2-Pkgs A&D37 | 12751303.62 | 12413453.42 | 2944618.73 | 15358072.15
Roubiky Hassan Allam | IPC#2#Roubiky | 2 | Roubiky Hassan Allam2 | 377625 | 315782.25 | 0 | 315782.25
Cairo Monorail - 6th October | IPC#3 - Monorail | 3 | Cairo Monorail - 6th October3 | 913500 | 559140 | 0 | 559140
Cairo Monorail - 6th October | IPC#6 - Monorai | 6 | Cairo Monorail - 6th October6 | 927500 | 918225 | 0 | 918225
Rabigh CCPP-Civil | Inv-02 Civil | 2 | Rabigh CCPP-Civil2 | 4110954.32 | 14182792.41 | 0 | 4727597.47
El Taameer Axis Expansion | IPC#2 Taamer PII | 2 | El Taameer Axis Expansion2 | 832590 | 804281.94 | 0 | 804281.94
Open Channel 2 | IPC01TR0099 | 1 | Open Channel 21 | 1537200 | 1306921.67 | 0 | 1306921.67
Wady El Natroon Bridge | WADYELNATRONIPC11+12 | 11 | Wady El Natroon Bridge11 | 11132010.48 | 9924903.8 | 0 | 9924903.8
HSR | Inv 2 HSR | 2 | HSR2 | 140860565.14 | 0 | 99501314.727 | 99501314.727
Cairo-Alex Railway | CAIRO-ALEX IPC19 | 19 | Cairo-Alex Railway19 | 8739158.4 | 6068946.64 | 917611.63 | 6986558.27
Sultana Malak Restoration | Sultana Ma Zer Final |  | Sultana Malak Restoration | 1063414.29 | 1042010 | 0 | 1042010
RADAMIS CITY | IPC05TR0084 | 5 | RADAMIS CITY5 | 174292.23 | 154335.77 | 0 | 154335.77
EIPICO Factory | IPC07TR0054 | 7 | EIPICO Factory7 | 42358 | 56197.4 | 0 | 56197.4
U7-SEASHELL | IPC22TR0064 | 22 | U7-SEASHELL22 | 143143.85 | 123619.03 | 0 | 123619.03
Port Said Port Silos | supply egp ipc8 | 8 | Port Said Port Silos8 | 2594878.44 | 8973244.2 | 1297439.2 | 2054136.68
Port Said Port Silos | IPC 5 SUPPLY PORT SA | 5 | Port Said Port Silos5 | 3279001.016 | 10264739.1548 | 1311483.72 | 2894055.7187
New Giza Teaching Hospital | New Giza ipc 28 | 28 | New Giza Teaching Hospital28 | 12973500.18 | 5534314 | 497979.91 | 6429944.91
EIPICO C002-23 | IPC12TR0068 | 12 | EIPICO C002-2312 | 228534.45 | 196105.42 | 0 | 196105.42
Coastal road Bridge Extension | IPC007 - Gharably | 7 | Coastal road Bridge Extension7 | 674730 | 649764.99 | 0 | 649764.99
SSC Suez Steel Company Project | Revamp ipc 10 | 10 | SSC Suez Steel Company Project10 | 5011477.79 | 1348297.2816 | 1503443.34 | 4864487.3216
Ring Road - Service Road | SERVICE ROAD IPC 2 | 2 | Ring Road - Service Road2 | 9399923.14 | 8307635.02 | 0 | 8307635.02
Sokhna Port Expansion | SPX.2 ESC 1:7 |  | Sokhna Port Expansion | 20628970 | 18242626.1738 | 0 | 18242626.1738
KATAMYA GREEKS LAND SCAPE STAR | IPC03TR0081(1) | 3 | KATAMYA GREEKS LAND SCAPE STAR3 | 1207954.22 | 1194183.541 | 0 | 1194183.541
Port Said Port Silos | PORT SAID IPC 29 | 29 | Port Said Port Silos29 | 2107663.51 | 596055.2424 | 210766.35 | 806821.5924
Air Defense College | air dev finish ipc1 | 1 | Air Defense College1 | 47270869 | 31773530 | 0 | 39610730
Red Sea Museum-Bab El-Bunt | Inv-02 RS | 2 | Red Sea Museum-Bab El-Bunt2 | 1838915.59 | 6344258.76 | 0 | 2114752.92
Olympic MultiSport Hall | IPC07TR0079 | 7 | Olympic MultiSport Hall7 | 25709.6 | 21634.63 | 0 | 21634.63
Open Chanel Epoxy | IPC02TR0101 | 2 | Open Chanel Epoxy2 | 2210880 | 1771381 | 0 | 1771381
EGAT ADMIN (Pelletizing) | IPC02TR0094 | 2 | EGAT ADMIN (Pelletizing)2 | 102715.8 | 88140.43 | 0 | 88140.43
Katameya Creeks - RME | IPC19TR0053 | 19 | Katameya Creeks - RME19 | 152389.58 | 134940.97 | 0 | 134940.97
Katameya Creeks - RME | IPC23TR0053 | 23 | Katameya Creeks - RME23 | 183424.69 | 162422.57 | 0 | 162422.57
MDF Factory - Sadat | IPC02TR0093 | 2 | MDF Factory - Sadat2 | 138106.8 | 118509.44 | 0 | 118509.44
October Under-Railway Tunnel | OCTOBER TUNNELIPC10 | 10 | October Under-Railway Tunnel10 | 5992741.71 | 5395295.85 | 0 | 5395295.85
Ahl Misr P3 – Zamalek Sector | IPC#5 | 5 | Ahl Misr P3 – Zamalek Sector5 | 469800 | 54620.37 | 0 | 54620.37
Creeks URBN-K | Katamya Urbnk ipc 3 | 3 | Creeks URBN-K3 | 40661954.89 | 0 | 40274438.44 | 40274438.44
Seashell Playa 5 Villas | Playa C-469 ipc 5 | 5 | Seashell Playa 5 Villas5 | 19567.53 | 17876.89 | 0 | 17876.89
Seashell Playa 5 Villas | Playa c469 ipc 6 | 6 | Seashell Playa 5 Villas6 | 35218.72 | 32175.82 | 0 | 32175.82
Port Said Port Silos | PORT SAID SUP. 10 |  | Port Said Port Silos | 546312.2 | 1501265.934 | 163893.66 | 555053.198
HSR | HSR-OCT4 |  | HSR | 53545345.27 | 0 | 33769924.9835 | 33769924.9835
ORA-ZED Towers P01B | IPC16TR0051 | 16 | ORA-ZED Towers P01B16 | 1104877.42 | 803370.14 | 0 | 803370.14
EIPICO C002-23 | IPC14TR0068 | 14 | EIPICO C002-2314 | 212340.9 | 182209.72 | 0 | 182209.72
Pushing Tunnel | Inv ( 3 ) T. Pushing | 3 | Pushing Tunnel3 | 2712250 | 2191769.35 | 0 | 2191769.35
Ahl Misr P3 – Zamalek Sector | IPC#4 Ahl Misr Zamal | 4 | Ahl Misr P3 – Zamalek Sector4 | 430650 | 43065 | 0 | 43065
Seashell Playa 5 Villas | Playa C469 ipc 10 | 10 | Seashell Playa 5 Villas10 | 31559.6 | 28832.84 | 0 | 28832.84
Kafr Shokr Bridge | Kafr Shokr 11 final |  | Kafr Shokr Bridge | 5393674.1 | 9511261.9 | 0 | 9511261.9
Cairo Monorail - 6th October | IPC#7` | 7 | Cairo Monorail - 6th October7 | 1281000 | 1268190 | 0 | 1268190
Open Channal | IPC1TR74 | 1 | Open Channal1 | 322560 | 283852.8 | 0 | 283852.8
Oasis Buildings- New Capital | inv ( 12 ) 12-2020 | 12 | Oasis Buildings- New Capital12 | 1849863.6 | 1753693.64 | 0 | 1753693.64
Rabigh CCPP-Civil | K0006 Inv-03 | 3 | Rabigh CCPP-Civil3 | 3935285.21 | 18102311.96 | 0 | 4525577.99
Red Sea Museum-Bab El-Bunt | K0003 Inv-03 | 3 | Red Sea Museum-Bab El-Bunt3 | 1065253.06 | 3675123.09 | 0 | 1225041.03
EMAAR-PKG#22-MARASSI | OB-RE-PKG#22 |  | EMAAR-PKG#22-MARASSI | 441828.87 | 0 | 0 | #DIV/0!
Al-Parco | cr INV ( 3 ) ALparco | 3 | Al-Parco3 | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Cr.Compensation |  | Siemens 6x500/220 KV GIS-MOU | 0 | 0 | 0 | #DIV/0!
Roots -Kafr ElSheikh Bridge | D0009-OB-Dec-2020/Cr | 2020 | Roots -Kafr ElSheikh Bridge2020 | 0 | 0 | 0 | #DIV/0!
El Zagazig Railway P2 | D0044-OB-Dec-2020/Cr | 2020 | El Zagazig Railway P22020 | 0 | 0 | 0 | #DIV/0!
Ghana | -1 | 1 | Ghana1 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Dividend Netting off |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Luxor North Axis Bridge-Off | Credit - IPC2 | 2 | Luxor North Axis Bridge-Off2 | 0 | 0 | 0 | #DIV/0!
Get Business Complex | Cr.INV ( 13 ) GET | 13 | Get Business Complex13 | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Cr Adj. Inv. 22 | 22 | Siemens 6x500/220 KV GIS-MOU22 | 0 | 0 | 0 | #DIV/0!
FX-04-22 U.Communities-UE | 68 |  | FX-04-22 U.Communities-UE | 383620.06 | 0 | 0 | #DIV/0!
Get Business Complex | CR - INV ( 6 ) GET | 6 | Get Business Complex6 | 0 | 0 | 0 | #DIV/0!
New Capital | ref.1 |  | New Capital | 0 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | Cr-40 EGP - Giza III | 40 | Giza North PP Phase3(CP-117)40 | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | kafr shokr ipc9+ | 9 | Kafr Shokr Bridge9 | 0 | 0 | 0 | #DIV/0!
AIRDEFNSE -EPOXY | IPC09TR0066 | 9 | AIRDEFNSE -EPOXY9 | 394112.5 | 0 | 0 | #DIV/0!
Cairo North PP Rehabilitation | 7 EGP - Cairo North |  | Cairo North PP Rehabilitation | 41928.07 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 259 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 8 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 665214.6667 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | IPC#FINAL#D0073 |  | WADY EL-NATROUN BRIDGE(HST) | 9940 | 0 | 0 | #DIV/0!
El-Moneeb Bridge | D0038-OB-Dec-2020/Cr | 2020 | El-Moneeb Bridge2020 | 0 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 69 |  | FX-02-22 Decent Life-UE | 585842.11 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR 180057 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cr.91 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_inv.6 | 6 | Akhmem Assiut6 | 0 | 0 | 0 | #DIV/0!
Beni Suef COMCAVI | 180005 |  | Beni Suef COMCAVI | -198497.8 | 0 | 0 | #DIV/0!
Open Channel 2 | CAN.IPC02TR0099(02) | 2 | Open Channel 22 | 0 | 0 | 0 | #DIV/0!
Port Said Grain Storage | rent_004 |  | Port Said Grain Storage | 147900 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/003AdjCnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.CR.Soc Inv44/47 | 44 | Akhmem Assiut44 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR-5-Euro-South helw | 5 | South Helwan PP (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Palm Hill-Infra Str(Elec.Work) | Retention bal. ded. |  | Palm Hill-Infra Str(Elec.Work) | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | DEC ADJ 22 |  | Banha PP (CP-117) | 7447625.25 | 0 | 0 | #DIV/0!
Waldorf Astoria Cairo | CR Waldorf IPC 20 | 20 | Waldorf Astoria Cairo20 | 0 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 101 |  | FX-02-22 Decent Life-UE | 593161.81 | 0 | 0 | #DIV/0!
Mohamed Ali Palace | CR.TR0015CLOSING.DEC |  | Mohamed Ali Palace | 0 | 0 | 0 | #DIV/0!
Baron Palace | 10075 |  | Baron Palace | 0 | 0 | 0 | #DIV/0!
Sewage Treatment Plant | CR-IPC#1 | 1 | Sewage Treatment Plant1 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 14 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 15152.72 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | adj commercial fees |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 15 EGP - Beni Suef |  | Beni-Suef Power Plant EPC | 37500216.58 | 37541346 | 0 | 37541346
ZED Phase 2 | IPC09TR0062 | 9 | ZED Phase 29 | 14083.82 | 0 | 0 | #DIV/0!
ARAB ALMADABEG WWTP 105000 CMD | 220621006 |  | ARAB ALMADABEG WWTP 105000 CMD | 11451061.78 | 0 | 0 | #DIV/0!
New Capital | cm 12 |  | New Capital | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 52 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
LRT Project | CR.TR0028CLOSING.DEC |  | LRT Project | 0 | 0 | 0 | #DIV/0!
LP-09-22 Koning Buzz | 91 |  | LP-09-22 Koning Buzz | 635778 | 0 | 0 | #DIV/0!
Houd Negaih | P-44-EGY Hاتحاد تشيد | 44 | Houd Negaih44 | 5000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 106 |  | Al-Shabab PP Phase II (CP-117) | -29361310.7738 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 56 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Waldorf Astoria Cairo | CR Waldorf IPC 19 | 19 | Waldorf Astoria Cairo19 | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 86 |  | Governmental Campus-N2 | 225372 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | reverse |  | South Helwan PP (CP-117) | -181104.17 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | CR-IPC#1. | 1 | Elmaragha Bridge - Sohag1 | 0 | 0 | 0 | #DIV/0!
Hadaek ElAharam | D0037-OB-Dec-2020/Cr | 2020 | Hadaek ElAharam2020 | 0 | 0 | 0 | #DIV/0!
LRT | D0045-OB-Dec-2020/Cr | 2020 | LRT2020 | 0 | 0 | 0 | #DIV/0!
Barwa and Damac 220 OHTL | CR adj inv. 3 | 3 | Barwa and Damac 220 OHTL3 | 0 | 0 | 0 | #DIV/0!
Koumassi Flyover | CR INV 1 | 1 | Koumassi Flyover1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | rev.( 16 EGP-Shabab |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 8 EGP - South Helwan |  | South Helwan PP (CP-117) | 185480.3714 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | rev.( 2 EGP - Sou. H |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Guinea 2 | Cr.P-2S-10 | 2 | Guinea 22 | 0 | 0 | 0 | #DIV/0!
Business District Hyde Park | INV ( 4 ) HY Bark CR | 4 | Business District Hyde Park4 | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2103220002 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Industria Sadat | Cr.Sadat Indust Inv2 | 2 | Industria Sadat2 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Cr (4EGP-South.Helw) |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Capital One | Cr-10Captal 1 | 10 | Capital One10 | 0 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 478 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Koning Food V3 LP-09-20 | 15 |  | Koning Food V3 LP-09-20 | 0 | 0 | 0 | #DIV/0!
New Capital | ref.3 |  | New Capital | 0 | 0 | 0 | #DIV/0!
6th Oct. Ph2 PP-Elect Work | 2104220005 |  | 6th Oct. Ph2 PP-Elect Work | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-Tah ipc 5 | 5 | Tarek Abdel-Hakim Center5 | 0 | 0 | 0 | #DIV/0!
Sixty Iconic Tower | Inv ( 8) sixty | 8 | Sixty Iconic Tower8 | 280430 | 0 | 0 | #DIV/0!
Toshka GIS 500 kV | CRToshka Sub Inv. 24 | 24 | Toshka GIS 500 kV24 | 0 | 0 | 0 | #DIV/0!
Mohamed Ali Palace Restoration | Mohamed aly3 3final |  | Mohamed Ali Palace Restoration | 1493361.02 | 0 | 0 | #DIV/0!
SHUQAIQ High Voltage Works | 1 |  | SHUQAIQ High Voltage Works | 3611412.1 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-005 | 5 | Maspiro Towers5 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv-04 Final | 4 | MOC HQ at Diriyah4 | 16246137.192 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11583 |  | FURJAN Cable Works | 60494.4 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 7 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1899620.581 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC#2 | 2 | Maspiro Towers2 | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2008210011 |  | Manshiet Nasser Substation | 4193511.78 | 0 | 0 | #DIV/0!
Roubiky Hassan Allam | IPC#FINAL#Roubiky |  | Roubiky Hassan Allam | 107587.5 | 0 | 0 | #DIV/0!
Sodic East | CR.TR0004CLOSING.DEC |  | Sodic East | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180077 |  | Suez Gulf Substation | 8156.34 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.9 | 9 | Akhmem - Qena9 | 0 | 0 | 0 | #DIV/0!
FX-05-22 Close compound | 79 |  | FX-05-22 Close compound | 117784.8 | 0 | 0 | #DIV/0!
EL -mahager Bridge Ain sokhna | CR - Mahager Project |  | EL -mahager Bridge Ain sokhna | 0 | 0 | 0 | #DIV/0!
Almaza Bridge - Safir 2 | CR-S003 |  | Almaza Bridge - Safir 2 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 47 |  | Suez Gulf Substation | 631298.1144 | 0 | 0 | #DIV/0!
MOTHANA 400/132kV SS | 216 |  | MOTHANA 400/132kV SS | 0 | 0 | 0 | #DIV/0!
Benban 500 K.V/95 K.M | CR.Ret Benban Lot 2 |  | Benban 500 K.V/95 K.M | 0 | 0 | 0 | #DIV/0!
Port Said Grain Storage | CR-IPC#5 GSCC | 5 | Port Said Grain Storage5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 242 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Toshka-04 GIS Substation | Deb.adv. $ Toshka 4. |  | Toshka-04 GIS Substation | 11677.59 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 13 EUR Rev. 2 |  | South Helwan PP (CP-117) | 145002.645 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 16 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 126742.8 | 0 | 0 | #DIV/0!
U3 & U5 | CR-55/2 | 55 | U3 & U555 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 51 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 5 EGP- Suez Gulf |  | Suez Gulf Substation | 100898.24 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2105210014 |  | Miscellaneous Projects | -10500 | 0 | 0 | #DIV/0!
FX-04-22 U.Communities-UE | 72 |  | FX-04-22 U.Communities-UE | 4732.43 | 0 | 0 | #DIV/0!
Berty Badr Bridge | INV ( 2 ) Berty Badr | 2 | Berty Badr Bridge2 | 78559.31 | 0 | 0 | #DIV/0!
Tarek AbdelHakim Center - KSA | CR K0001-3 | 3 | Tarek AbdelHakim Center - KSA3 | 0 | 0 | 0 | #DIV/0!
ARAB ALMADABEG WWTP 105000 CMD | 220421002 |  | ARAB ALMADABEG WWTP 105000 CMD | 13746900.25 | 0 | 0 | #DIV/0!
Akhmem Assiut | Inv.54 Assuit Akhmem | 54 | Akhmem Assiut54 | 21492512.99 | 0 | 0 | #DIV/0!
Benban 3/ Toshka 2 LOT 4 | Cr.Tos Lot6 Inv.9 | 9 | Benban 3/ Toshka 2 LOT 49 | 0 | 0 | 0 | #DIV/0!
ACWA POWER & NOMAC HQ | CR Acwa ipc 2 | 2 | ACWA POWER & NOMAC HQ2 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 267 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 50 |  | Suez Gulf Substation | 12874016.5632 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC#3 | 3 | Maspiro Towers3 | 0 | 0 | 0 | #DIV/0!
Hyper One Badr | INV ( 12 ) Hyper | 12 | Hyper One Badr12 | 116377.44 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR- W. Dom invs 2018 | 2018 | W Dam PP Phase II (CP-117)2018 | 0 | 0 | 0 | #DIV/0!
Port Said Port Silos | PORTSAID SUPPLYIPC12 | 12 | Port Said Port Silos12 | 3887747 | 0 | 0 | #DIV/0!
October Under-Railway Tunnel | cr-oct.tunnel ipc 1 | 1 | October Under-Railway Tunnel1 | 0 | 0 | 0 | #DIV/0!
Cameroon EAR | CR.P-09-13 AccRev | 9 | Cameroon EAR9 | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 1901220004 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 295 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Ministries Buildings | cr-mini core ipc 11 | 11 | Ministries Buildings11 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 1904220002 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Safir bridge | D0021-OB-Dec-2020/CR | 2020 | Safir bridge2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 245 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 9 EGP - Shabab | 9 | Al-Shabab PP Phase II (CP-117)9 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR IPC-12-Saray | 12 | Taval Sarai 5212 | 0 | 0 | 0 | #DIV/0!
Infra Project 4514 | 220621005 |  | Infra Project 4514 | 133333333.33 | 0 | 0 | #DIV/0!
New Giza 2 | OB-SI-New Giza 2 |  | New Giza 2 | 1317483.36 | 0 | 0 | #DIV/0!
Almaza | Cr Adj Inv 11 | 11 | Almaza11 | 0 | 0 | 0 | #DIV/0!
LP-07-22 Koning GPS | 84 |  | LP-07-22 Koning GPS | 13650 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Cr -5-Euro-South hel | 5 | South Helwan PP (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Soci.Timay.358K.M |  | Beni Seuf - 358 | 300100 | 0 | 0 | #DIV/0!
Royal City | Royal Cen Zone ipc24 | 24 | Royal City24 | 3256136.08 | 0 | 0 | 3256136.08
Sokhna Port Expansion | SPX ROADS 2 FINAL |  | Sokhna Port Expansion | 56070.14 | 0 | 0 | 58873.647
RING ROAD MARYOTIA EXPANSION | Mariotya ESC.19 est |  | RING ROAD MARYOTIA EXPANSION | 2260334.86 | 0 | 0 | 2373351.603
Residence 8 ( S05 ) | Inv ( 1 ) S05 | 1 | Residence 8 ( S05 )1 | 1401400 | 0 | 0 | 1401400
Residence 8 ( k12 ) | INV ( 1 ) R08-K12 | 1 | Residence 8 ( k12 )1 | 1024100 | 0 | 0 | 1024100
Central Capital | INV ( 5 ) Central Ca | 5 | Central Capital5 | 33984 | 0 | 0 | 33984
Get Business Complex | INV ( 15 ) GET | 15 | Get Business Complex15 | 1172197.1 | 0 | 0 | 1172197.1
Get Business Complex | INV ( 13 ) GET | 13 | Get Business Complex13 | 3065708.74 | 0 | 0 | 3065708.74
Seashell Playa 5 Villas | 20/12/2023 |  | Seashell Playa 5 Villas | 33072.33 | 0 | 0 | 37702.4562
Katameya Creeks - RME | IPC15TR0053 | 15 | Katameya Creeks - RME15 | 132898.04 | 0 | 0 | 132898.04
U3 & U5 | IPC001 | 1 | U3 & U51 | 741275.46 | 0 | 0 | 741275.46
RING ROAD MARYOTIA EXPANSION | فروق اسعار المريوطية |  | RING ROAD MARYOTIA EXPANSION | 6037054.86 | 0 | 0 | 6338907.603
Egyptian Exchange Building | Egy Exch IPC1 | 1 | Egyptian Exchange Building1 | 185780585 | 0 | 0 | 185780585
Port Said Grain Storage | IPC#5Port Said 2 | 5 | Port Said Grain Storage5 | 866250 | 0 | 0 | 1155000
ARAB ALMADABEG WWTP 105000 CMD | 220421001 |  | ARAB ALMADABEG WWTP 105000 CMD | 24188122.11 | 15510764 | 4595743.2 | 21153072.35
TZ – Offshore E&M Procurement | 457 |  | TZ – Offshore E&M Procurement | 455556.64 | 0 | 0 | 455556.64
Nuweibaa (Swro) | 220321003 |  | Nuweibaa (Swro) | 846941.68 | 0 | 0 | 846941.68
UIC Project (LP-04-21) | 62 |  | UIC Project (LP-04-21) | 48750 | 0 | 0 | 48750
Playa Resort | 21000004 |  | Playa Resort | 62370158.7667 | 0 | 0 | 78586400.046
Benban 500 K.V/95 K.M | Ref.Ret Benban Lot 2 |  | Benban 500 K.V/95 K.M | 11755279.89 | 0 | 0 | 11755279.89
Akhmem - Qena | Ref.Ret Qen-akh 7 |  | Akhmem - Qena | 50000000 | 0 | 0 | 50000000
SHATRA 400/132kV SS | 426 |  | SHATRA 400/132kV SS | 772.46 | 772.46 | 0 | 772.46
Containment Data Center- | 33 |  | Containment Data Center- | 9750258 | 0 | 0 | 9750258
SHAT Al ARAB 400/132kV SS | 420 |  | SHAT Al ARAB 400/132kV SS | 1406409.99 | 1406409.99 | 0 | 1406409.99
Taval Sarai 52 | IPC-12-Saray | 12 | Taval Sarai 5212 | 1506383.64 | 1302893.97 | 0 | 1302893.975
MAYSAN 400/132kV SS | 399 |  | MAYSAN 400/132kV SS | 377377.62 | 373453.82 | 0 | 377377.62
Assuit PP (CP-118) | 2105210002 |  | Assuit PP (CP-118) | 2466531.65 | 2596349.11 | 0 | 2596349.11
AWEER POWER STATION 'H' Phase | LOC/014 |  | AWEER POWER STATION 'H' Phase | 2578692.06 | 2037166.721 | 257869.206 | 2552905.137
Railway Bridge - Alex | FPC - Mohamed Kamel |  | Railway Bridge - Alex | 1515464.85 | 0 | 0 | 1515464.85
South Helwan PP (CP-117) | 2012210036 |  | South Helwan PP (CP-117) | -4180518.1 | 0 | 0 | -4180518.1
Marsa Alam/ Bernes LOT2 OHTL | Inv. 27 Usd | 27 | Marsa Alam/ Bernes LOT2 OHTL27 | 24764.46 | 0 | 0 | 24764.46
Ghana Street lighting | MIDA Sply. Inv. 5 | 5 | Ghana Street lighting5 | 186469.51 | 0 | 0 | 186469.51
Rail Way Tunnel Zagazig | D0025-OB-Dec-2020 | 2020 | Rail Way Tunnel Zagazig2020 | 2022800 | 0 | 0 | 2022800
marassi inland marina | D0029-OB-Dec-2020 | 2020 | marassi inland marina2020 | 13255239.56 | 0 | 0 | 13255239.56
Masr ELgedeeda | D0040-OB-Dec-2020 | 2020 | Masr ELgedeeda2020 | 1720937.5 | 0 | 0 | 1720937.5
El Salam Bridge | D0048 OB-Dec-2020 | 2020 | El Salam Bridge2020 | 2538210 | 0 | 0 | 2538210
Mangrouve Hotel - Gouna | TR0021DEC.Clocing |  | Mangrouve Hotel - Gouna | 43967 | 0 | 0 | 43967
Celia | D0020-OB-Dec-2020 | 2020 | Celia2020 | 2241458.81 | 0 | 0 | 2241458.81
Development of Mahmudiyah axis | D0012-OB-Dec-2020 | 2020 | Development of Mahmudiyah axis2020 | 7537500 | 0 | 0 | 7537500
El Boghaz Brigde | IPC#22 | 22 | El Boghaz Brigde22 | 2932623.73 | 2709847.84 | 0 | 2754385.57
Taval Sarai 52 | IPC_1_SARAYA_GAMA |  | Taval Sarai 52 | 198511.2 | 0 | 0 | 198511.2
Assuit PP (CP-118) | 2010210004 |  | Assuit PP (CP-118) | 1585185.63 | 1398926.31 | 249666.74 | 1648593.05
Celia | IPC0006 | 6 | Celia6 | 797127.72 | 346249.32 | 0 | 764000.45
Assuit PP (CP-118) | 2010210001 |  | Assuit PP (CP-118) | 1732764.79 | 1529164.94 | 272910.45 | 1802075.39
Manshiet Nasser Substation | 2004210012 |  | Manshiet Nasser Substation | 591061.51 | 539289.67 | 0 | 539289.67
Al-Shabab PP Phase II (CP-117) | 2002210019 |  | Al-Shabab PP Phase II (CP-117) | 2599657.87 | 2707751.75 | 0 | 2707751.75
Manshiet Nasser Substation | 2004210010 |  | Manshiet Nasser Substation | 4193511.78 | 0 | 0 | 4193511.78
Manshiet Nasser Substation | 2004210009 |  | Manshiet Nasser Substation | 3197756.28 | 0 | 0 | 3197756.28
W Dam PP Phase II (CP-117) | 2002210027 |  | W Dam PP Phase II (CP-117) | 2107952.45 | 1965342.9 | 0 | 1965342.9
Al-Shabab PP Phase II (CP-117) | 2002210018 |  | Al-Shabab PP Phase II (CP-117) | 968202.61 | 166622.15 | 491178.51 | 657800.66
Ministries A13-A14 | 10097 |  | Ministries A13-A14 | 205000 | 0 | 0 | 205000
Beni Seuf - 358 | Inv.1 Temmay 500 k.v | 1 | Beni Seuf - 3581 | 14975339.35 | 0 | 0 | 14975339.35
Manshiet Nasser Substation | 2001210004 |  | Manshiet Nasser Substation | 1414421.75 | 1290530.76 | 0 | 1290530.76
Manshiet Nasser Substation | 533 |  | Manshiet Nasser Substation | 163356.13 | 149051.8 | 0 | 149051.8
Al-Shabab PP Phase II (CP-117) | 180155 |  | Al-Shabab PP Phase II (CP-117) | 5468.65 | 797.54 | 0 | 6266.16
LAYYAH CCPP | 471 |  | LAYYAH CCPP | 10283760 | 0 | 0 | 10283760
6th Oct. Ph2 PP-Elect Work | 14 EGP - October |  | 6th Oct. Ph2 PP-Elect Work | 157479.07 | 157479.07 | 0 | 157479.07
Suez Gulf Substation | 10 EGP - Suez Gulf |  | Suez Gulf Substation | 431640.3238 | 407900.11 | 45322.23 | 453222.34
Suez Gulf Substation | 16 EGP VO Progress |  | Suez Gulf Substation | 61047.25 | 57798.16 | 6422.02 | 64220.18
Suez Gulf Substation | 19 EGP MRR Main |  | Suez Gulf Substation | 25487.3 | 24130.8 | 2681.2 | 26812
Manshiet Nasser Substation | 180172 |  | Manshiet Nasser Substation | 1074277.06 | 1127990.91 | 0 | 1127990.91
Manshiet Nasser Substation | 1906210009 |  | Manshiet Nasser Substation | 542417.17 | 486789.72 | 87301.45 | 574091.17
Maspiro Towers | IPC#1 | 1 | Maspiro Towers1 | 892200 | 883278 | 0 | 886252
Suez Gulf Substation | 1909210013 |  | Suez Gulf Substation | 300804.72 | 300804.72 | 0 | 300804.72
Assuit PP (CP-118) | 1906210016 |  | Assuit PP (CP-118) | 1315675.08 | 1161085.37 | 207216.84 | 1368302.21
Assuit PP (CP-118) | 1906210017 |  | Assuit PP (CP-118) | 519518.29 | 458474.88 | 81824.14 | 540299.02
Zambia Project | SCD4/003 |  | Zambia Project | 175449.71 | 0 | 0 | 175449.71
Beni-Suef Power Plant EPC | Adj. 180178 |  | Beni-Suef Power Plant EPC | 427482390.92 | 427482390.92 | 0 | 427482390.92
Akhmem - Qena | Soc Inv 26 $ Quna | 26 | Akhmem - Qena26 | 159039 | 0 | 0 | 159039
Beni-Suef Power Plant EPC | 180132 |  | Beni-Suef Power Plant EPC | 283799492.53 | 283799492.53 | 0 | 283799492.53
Akhmem Assiut | Ref . Soc Inv 48Asui | 48 | Akhmem Assiut48 | 2182603.5 | 0 | 0 | 2182603.5
Assuit PP (CP-118) | 1901210008 |  | Assuit PP (CP-118) | 3183036.9747 | 0 | 0 | 3183036.9747
Military 110 Kayan Project | Refund Retention Kay |  | Military 110 Kayan Project | 19499900 | 0 | 0 | 19499900
Al-Shabab PP Phase II (CP-117) | 28 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 2957512.2381 | 2639579.67 | 465808.18 | 3105387.85
Al-Shabab PP Phase II (CP-117) | 26 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 483945.1429 | 431921.04 | 76221.36 | 508142.4
W Dam PP Phase II (CP-117) | 29 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 3185721.0095 | 2843256 | 501751.06 | 3345007.06
Al-Shabab PP Phase II (CP-117) | 11 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 434762.5333 | 0 | 0 | 456500.66
MOTHANA 400/132kV SS | 204 |  | MOTHANA 400/132kV SS | 98778.12 | 0 | 0 | 98778.12
Suez Gulf Substation | 180163 |  | Suez Gulf Substation | 3515018.46 | 3515018.46 | 0 | 3515018.46
Suez Gulf Substation | 180162 |  | Suez Gulf Substation | 31206884.82 | 31206884.82 | 0 | 31206884.82
Al-Shabab PP Phase II (CP-117) | 180106 |  | Al-Shabab PP Phase II (CP-117) | 24798.34 | 22174.15 | 3913.09 | 26087.24
Beni-Suef Power Plant EPC | 180154 |  | Beni-Suef Power Plant EPC | 92867910.38 | 0 | 0 | 92867910.38
Marsa Matrouh 500KV | Inv, 6 usd Borg Arab | 6 | Marsa Matrouh 500KV6 | 1342780.82 | 0 | 0 | 1342780.82
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 06 |  | Giza North PP Ph I,II (CP-117) | 2688.11 | 2688.11 | 0 | 2688.11
Abu Qir PP (CP-117) | Abo Quir Invces |  | Abu Qir PP (CP-117) | 235181.73 | 54746.7 | 0 | 54746.7
K047 FDH JV | Inv. No.15 KWD Floor | 15 | K047 FDH JV15 | 86543.43 | 51901.47 | 0 | 77889.09
Zafranaa - Ras Ghareb | Adj. Inv.18 | 18 | Zafranaa - Ras Ghareb18 | 42553580.77 | 0 | 0 | 42553580.77
Abou El Matameer and Sammanoud | Inv 90 P8 Sammound | 90 | Abou El Matameer and Sammanoud90 | 2776641.7 | 0 | 0 | 2776641.7
Beni-Suef Power Plant EPC | 103 |  | Beni-Suef Power Plant EPC | 5051717777.8083 | 0 | 0 | 5051717777.8083
South Helwan PP (CP-117) | 180123 |  | South Helwan PP (CP-117) | 200016.25 | 210412.1 | 0 | 210412.1
Cairo South PP Rehabilitation | 89 |  | Cairo South PP Rehabilitation | 4052526.3401 | 0 | 0 | 4052526.3401
W Dam PP Phase II (CP-117) | 180043 |  | W Dam PP Phase II (CP-117) | 39427.781 | 0 | 0 | 41399.17
W Dam PP Phase II (CP-117) | 180039 |  | W Dam PP Phase II (CP-117) | 67012.6857 | 0 | 0 | 70363.32
W Dam PP Phase II (CP-117) | 180038 |  | W Dam PP Phase II (CP-117) | 23518.0667 | 0 | 0 | 24693.97
Ain-Sokhna PP (CP-117) | 24 |  | Ain-Sokhna PP (CP-117) | 60401842 | 0 | 0 | 60401842
Banha PP (CP-117) | 23 |  | Banha PP (CP-117) | 28330354 | 0 | 0 | 28330354
W Dam PP Phase II (CP-117) | 180045 |  | W Dam PP Phase II (CP-117) | 271925.6762 | 0 | 0 | 285521.96
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 03 |  | Giza North PP Ph I,II (CP-117) | 940885.4 | 940885.4 | 0 | 940885.4
Abou El Matameer and Sammanoud | Samanoud 5 inv.81 | 81 | Abou El Matameer and Sammanoud81 | 8005328.32 | 0 | 0 | 8005328.32
Cairo South PP Rehabilitation | 6 USD - Cairo South |  | Cairo South PP Rehabilitation | 5565.27 | 5565.27 | 0 | 5565.27
Al-Wukair 11 Substation | Inv 20 Qatar | 20 | Al-Wukair 11 Substation20 | 807356.9 | 807356.9 | 0 | 807356.9
Berket Ghelion | Inv 18 Ghelion | 18 | Berket Ghelion18 | 5444747.64 | 0 | 0 | 5444747.64
Strining Lot A- Elegect | 1 Elegict |  | Strining Lot A- Elegect | 1898745.45 | 104426 | 0 | 1877346.815
Siemens 6x500/220 KV GIS-MOU | 3 |  | Siemens 6x500/220 KV GIS-MOU | 5058485.66 | 0 | 0 | 5058485.66
Al-Shabab PP Phase II (CP-117) | 4 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 7561970.1779 | 5929576.75 | 1147907.07 | 7385453.44
Al-Shabab PP Phase II (CP-117) | 3 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 7552112.2233 | 5417959.4 | 1146410.64 | 7042783.37
Al-Shabab PP Phase II (CP-117) | 7 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 13708468.4881 | 11294420.55 | 2080945.52 | 18079323.97
Al-Shabab PP Phase II (CP-117) | 9 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 380734.4762 | 339805.52 | 59965.68 | 738191.2
Suez Gulf Substation | 1 EGP - Suez Gulf |  | Suez Gulf Substation | 1604181.77 | 0 | 165070.3 | 1650703.0412
Palm Hill-Infra Str(Elec.Work) | 4 - palm hills |  | Palm Hill-Infra Str(Elec.Work) | 53794 | 0 | 0 | 59173.4
Suez Gulf Substation | 3 USD/123/2011/2012 |  | Suez Gulf Substation | 74110.6719 | 0 | 0 | 75000
Cameron EDC | 018/2019 |  | Cameron EDC | 77795 | 76040.41 | 0 | 76040.41
Cameron EDC | 014/2019 |  | Cameron EDC | 282606.67 | 282346.18 | 0 | 282346.18
Cameron EDC | 011/2019 |  | Cameron EDC | 84301.3 | 84142.91 | 0 | 84142.91
Cameron EDC | 027/2020 FCV |  | Cameron EDC | 184618730.63 | 92309365.31 | 0 | 92309365.31
Cameron EDC | 026/2020 FCV |  | Cameron EDC | 29020647.18 | 14510323.59 | 0 | 14510323.59
Cameron EDC | 025/2020 FCV |  | Cameron EDC | 30447892.13 | 15223946.43 | 0 | 15223946.43
Kuwait | 35-132KVA(9H) | 132 | Kuwait132 | 42039.91 | 31529.93 | 0 | 31529.93
Kuwait | 31-132KVA-J | 132 | Kuwait132 | 37179.26 | 27884.44 | 0 | 27884.44
Al-Shabab PP Phase II (CP-117) | 180108 |  | Al-Shabab PP Phase II (CP-117) | 31339.17 | 28022.82 | 4945.2 | 32968.02
Al-Shabab PP Phase II (CP-117) | 180105 |  | Al-Shabab PP Phase II (CP-117) | 144986.81 | 129644.13 | 22878.38 | 152522.51
W Dam PP Phase II (CP-117) | 180104 |  | W Dam PP Phase II (CP-117) | 11649.65 | 10416.87 | 1838.27 | 12255.14
W Dam PP Phase II (CP-117) | 180094 |  | W Dam PP Phase II (CP-117) | 22624.38 | 20230.24 | 3570.04 | 23800.28
W Dam PP Phase II (CP-117) | 10 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 110389.9429 | 0 | 17386.42 | 22905.92
W Dam PP Phase II (CP-117) | 6 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 39462.1429 | 32694.3 | 6215.29 | 41435.25
Al-Shabab PP Phase II (CP-117) | 543 |  | Al-Shabab PP Phase II (CP-117) | 145473.04 | 141684.68 | 25003.18 | 166687.86
W Dam PP Phase II (CP-117) | 527 |  | W Dam PP Phase II (CP-117) | 527399.68 | 513665.31 | 90646.82 | 604312.13
W Dam PP Phase II (CP-117) | 180113 |  | W Dam PP Phase II (CP-117) | 134475.89 | 120245.49 | 21219.79 | 141465.28
Al-Shabab PP Phase II (CP-117) | 5 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 1027130.92 | 0 | 0 | 1078487.466
Al-Shabab PP Phase II (CP-117) | 9 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 102943.42 | 108090.591 | 0 | 108090.591
Suez Gulf Substation | 7 EGP - (VO)progress |  | Suez Gulf Substation | 411301.5524 | 0 | 0 | 0
Suez Gulf Substation | 6 EGP - VO MRR |  | Suez Gulf Substation | 221233.4 | 209065.56 | 23229.51 | 232295.07
Suez Gulf Substation | Inv 1 EGP VO SG | 1 | Suez Gulf Substation1 | 463979.7238 | 438460.84 | 48717.87 | 487178.71
Suez Gulf Substation | 1 USD - Suez Gulf |  | Suez Gulf Substation | 342296.42 | 0 | 0 | 342296.42
Siemens 6x500/220 KV GIS-MOU | Inv 62 P5Assuit | 62 | Siemens 6x500/220 KV GIS-MOU62 | 3244052.91 | 2346747.88 | 486607.94 | 2833355.82
Damac 2x60/22 KV S/S | Inv 28 Damac | 28 | Damac 2x60/22 KV S/S28 | 1604314.25 | 1134949.53 | 240647.15 | 1375596.68
Abu Qir PP (CP-117) | 16 Euro-Abo Qeir 117 |  | Abu Qir PP (CP-117) | 139632.24 | 139632.24 | 0 | 139632.24
South Helwan PP (CP-117) | 180149 |  | South Helwan PP (CP-117) | 45702.85 | 49249.6 | 0 | 49249.6
South Helwan PP (CP-117) | 4 EGP - South Helwan |  | South Helwan PP (CP-117) | 118200.5048 | 122787.84 | 0 | 124110.52
New Capital | Inv. 7 Abozabaal | 7 | New Capital7 | 2859185.04 | 2075681.5 | 300214.43 | 2375895.93
Giza North PP Phase3(CP-117) | 32 EGP- Giza North 3 |  | Giza North PP Phase3(CP-117) | 73108.7619 | 65249.57 | 11514.63 | 76764.2
Al-Shabab PP Phase II (CP-117) | 180007 |  | Al-Shabab PP Phase II (CP-117) | 99981.77 | 89401.58 | 15776.75 | 105178.33
Tamey El-amdeed Substation | TAM-CW-EGP-13 | 13 | Tamey El-amdeed Substation13 | 5917379.64 | 4378250.65 | 887606.95 | 5265857.6
Tamey El-amdeed Substation | TAM-SW-EGP-07 | 7 | Tamey El-amdeed Substation7 | 695625 | 514762.5 | 104343.75 | 619106.25
Ismailiya East Substation | 19100023 |  | Ismailiya East Substation | 831250 | 615125 | 124687.5 | 739812.5
Tamey El-amdeed Substation | 19100020 |  | Tamey El-amdeed Substation | 875000 | 644613.98 | 131250 | 775863.98
Beni Suef Substation R61 | BSF-SW-EGP-08 | 8 | Beni Suef Substation R618 | 190312 | 140830.88 | 28546.8 | 169377.68
Beni Suef Substation R61 | BSF-SW-04 | 4 | Beni Suef Substation R614 | 695625 | 518240.62 | 104343.75 | 622584.37
Ismailiya East Substation | ISE-CW-EGP-08 | 8 | Ismailiya East Substation8 | 2301280 | 1714453.6 | 345192 | 2059645.6
Ismailiya East Substation | ISE-CW-EGP-07 | 7 | Ismailiya East Substation7 | 3492730 | 2602083.85 | 523909.5 | 3125993.35
Tamey El-amdeed Substation | TAM-SD-EGP-02 | 2 | Tamey El-amdeed Substation2 | 212655 | 158427.97 | 31898.25 | 190326.22
Tamey El-amdeed Substation | TAM-SD-EURO-01 | 1 | Tamey El-amdeed Substation1 | 3278673.89 | 2770479.44 | 491801.08 | 3262280.52
Al Mostathmreen GIS Substation | MOS-CW-EURO-IPC3 F | 3 | Al Mostathmreen GIS Substation3 | 3098157.44 | 2246164.14 | 464723.62 | 2710887.76
Beni Suef Substation R61 | BSF-SW-IPC2 | 2 | Beni Suef Substation R612 | 1478750 | 1101668.75 | 221812.5 | 1323481.25
Beni Suef Substation R61 | 18100069 |  | Beni Suef Substation R61 | 2694612.34 | 1953593.95 | 404191.85 | 2357785.8
Al Mostathmreen GIS Substation | 16 sd euro mostsmrin |  | Al Mostathmreen GIS Substation | 914791.17 | 663223.59 | 137218.68 | 800442.27
Ismailiya East Substation | (3)cw elasmailya |  | Ismailiya East Substation | 5141665.53 | 3830540.82 | 771249.83 | 4601790.65
Al Mostathmreen GIS Substation | 15sd EURO |  | Al Mostathmreen GIS Substation | 1388170.54 | 1006423.65 | 208225.58 | 1214649.23
Al Mostathmreen GIS Substation | 15 sd mosstasmreen |  | Al Mostathmreen GIS Substation | 242226 | 180458.14 | 36334.04 | 216792.18
Al Mostathmreen GIS Substation | SD(11) |  | Al Mostathmreen GIS Substation | 275602 | 205323.36 | 41340.38 | 246663.74
W Dam PP Phase II (CP-117) | 180130 |  | W Dam PP Phase II (CP-117) | 261592.5 | 233910.46 | 41278.32 | 275188.78
W Dam PP Phase II (CP-117) | 180046 |  | W Dam PP Phase II (CP-117) | 139787.8286 | 0 | 0 | 146777.22
Berket Ghelion | Inv 12 Ghelion | 12 | Berket Ghelion12 | 5871600.89 | 3507993.24 | 1467900.23 | 4975893.47
Ain-Sokhna PP (CP-117) | 41 Euro - Sokhna 117 |  | Ain-Sokhna PP (CP-117) | 556064.6 | 529860 | 0 | 529860
Sodic Club House | (19) sodic club |  | Sodic Club House | 2166022 | 1675962.94 | 426600.33 | 2102563.27
Berket Ghelion | Inv 17 Ghelion | 17 | Berket Ghelion17 | 1830141 | 1093088.28 | 457535.25 | 1550623.53
Kayan 3 New Cairo Capital City | OB-ST-EL Kayaan |  | Kayan 3 New Cairo Capital City | 58640899.2 | 50223564.95 | 0 | 53223564.95
New Giza 2 | (24)new giza 2 |  | New Giza 2 | 2116618 | 9060571.89 | 444489.89 | 9505061.78
New Giza 2 | (23) new giza 2 |  | New Giza 2 | 3256456 | 2470878.11 | 683855.77 | 3154733.88
EMAAR-PKG#53-UPTOWN | (22) pkg#53 |  | EMAAR-PKG#53-UPTOWN | 7192945 | 5904345.47 | 1122160.67 | 7026506.14
EMAAR-PKG#62-UPTOWN | (10)pkg#62 |  | EMAAR-PKG#62-UPTOWN | 3222186.55 | 2427820.0525 | 1333040.06 | 3760860.1125
EMAAR-PKG#107-MARASSI | (11)pkg#107 |  | EMAAR-PKG#107-MARASSI | 3590048.6 | 2773227.83 | 424438.28 | 3197666.11
Giza North PP Phase3(CP-117) | 40 EGP-Giza N. III |  | Giza North PP Phase3(CP-117) | 342624.2667 | 0 | 0 | 359755.48
Giza North PP Phase3(CP-117) | 37 EGP-Giza North 3 |  | Giza North PP Phase3(CP-117) | 408653.1714 | 364722.96 | 0 | 364722.96
Giza North PP Ph I,II (CP-117) | 39 EGP-Giza N. I&II |  | Giza North PP Ph I,II (CP-117) | 446737.6286 | 469074.51 | 0 | 469074.51
Beni Seuf - 358 | Inv. 15 Oewon Mousa | 15 | Beni Seuf - 35815 | 61546180.3 | 0 | 10584954.05 | 10584954.05
Beni Seuf - 358 | Inv.4 Temmay Amded | 4 | Beni Seuf - 3584 | 10937952 | 0 | 1911218.05 | 1911218.05
Beni Seuf - 358 | Inv.3 Temmay Amded | 3 | Beni Seuf - 3583 | 5651862.05 | 0 | 981389.96 | 981389.96
Beni Seuf - 358 | Inv. 6 Oewon Mousa | 6 | Beni Seuf - 3586 | 15856660.9 | 11039533.3 | 2724048.45 | 13763581.75
Beni Seuf - 358 | Inv. 2 Oewon Mousa | 2 | Beni Seuf - 3582 | 17413669.91 | 12842618.6 | 2988821 | 15831439.6
Beni Seuf - 358 | Inv.4kafr zeat itay | 4 | Beni Seuf - 3584 | 92797520.75 | 73223007.77 | 14006063.32 | 87229071.09
Beni Seuf - 358 | Inv.Banysouf 4-358 | 358 | Beni Seuf - 358358 | 29559860.57 | 23499501.26 | 4433979.08 | 27933480.34
Beni Seuf - 358 | Inv No1 Abo Kirr | 1 | Beni Seuf - 3581 | 23236416 | 18472950.72 | 3485462.4 | 21958413.12
Ismalia Bridge | (1) blagat asmaaliya |  | Ismalia Bridge | 10499675 | 2670207.95 | 2500000 | 9183028.95
Ismalia Bridge | (1) Ismailia U 4 |  | Ismalia Bridge | 7011092 | 2940613.5 | 3300000 | 6240613.5
Ismalia Bridge | (1) Ismailia U 3 |  | Ismalia Bridge | 5631432 | 2995087.15 | 2000000 | 4995087.15
W Dam PP Phase II (CP-117) | 17 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 412796.7524 | 143661.14 | 65015.49 | 208676.63
Barwa and Damac 220 OHTL | Inv No5 Wattanya220 | 5 | Barwa and Damac 220 OHTL5 | 4810035.12 | 3595090.15 | 721505.3 | 4316595.45
Barwa and Damac 220 OHTL | Inv No3 Wattanya220 | 3 | Barwa and Damac 220 OHTL3 | 6591618.8 | 4926830.75 | 988742.85 | 5915573.6
K047 FDH JV | Inv. NO.8 KWT Floor | 8 | K047 FDH JV8 | 196177.26 | 176559.53 | 0 | 176559.53
EMAAR-PKG#53-UPTOWN | (20)PKG#53 |  | EMAAR-PKG#53-UPTOWN | 12728277 | 9029077.68 | 1763984.99 | 10793062.67
Beni Suef Substation R61 | (17)beni suif 2 |  | Beni Suef Substation R61 | 6481496 | 1520156.85 | 5516775.56 | 7036932.41
Royal City | Royal city fin ipc43 | 43 | Royal City43 | 14387671.43 | 0 | 0 | 14387671.43
EMAAR-PKG#107-MARASSI | (1) PKG#107 |  | EMAAR-PKG#107-MARASSI | 5089749 | 5437394.56 | 1029158.15 | 6466552.71
Kayan 3 New Cairo Capital City | (3) ELKAYAN |  | Kayan 3 New Cairo Capital City | 54597030 | 35643751.5 | 4140013 | 49546399.5
PIP Zona 2 | Inv.5 Zona 2 | 5 | PIP Zona 25 | 3906247.87 | 3671872.9935 | 0 | 3671872.9935
PIP Zona 2 | Inv.04 zona2 | 4 | PIP Zona 24 | 8593695.56 | 8078073.828 | 0 | 8078073.828
Pyramids Industrial Park | Inv.1 PIP west | 1 | Pyramids Industrial Park1 | 1674247.23 | 1573792.3915 | 0 | 1573792.3915
Siemens 6x500/220 KV GIS-MOU | Inv 46 P12El Natroun | 46 | Siemens 6x500/220 KV GIS-MOU46 | 1405349.41 | 1016629.76 | 210802.41 | 1227432.17
Barwa 2x60/22 KV S/S | Inv 28 Barwa | 28 | Barwa 2x60/22 KV S/S28 | 1058684.5 | 748945.6 | 158802.68 | 907748.28
New Capital | INV 3 El Teben | 3 | New Capital3 | 3833054.35 | 5718734.14 | 804941.42 | 3261837.78
New Capital | Inv 4 Abo Zaabl | 4 | New Capital4 | 4071533.33 | 2792988.17 | 427511 | 3220499.17
New Capital | Inv 5 Abo Zaabl | 5 | New Capital5 | 2105923.446 | 1423524.06 | 221121.96 | 1644646.02
Attaqa Power Plant | Attka Sand Feb |  | Attaqa Power Plant | 25250000 | 25250000 | 0 | 25250000
Pyramids Industrial Park | Inv. 2 PIP West | 2 | Pyramids Industrial Park2 | 5625856.05 | 1741561.87 | 0 | 5288304.68
South Helwan PP (CP-117) | 2009210005 |  | South Helwan PP (CP-117) | 1254514.12 | 1039786.63 | 279930.93 | 1319717.56
W Dam PP Phase II (CP-117) | 14 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 1256341.1524 | 1121284.48 | 197873.73 | 1319158.21
South Helwan PP (CP-117) | 2009210007 |  | South Helwan PP (CP-117) | 239840.14 | 211966.82 | 37845.88 | 249812.7
South Helwan PP (CP-117) | 2001210003 |  | South Helwan PP (CP-117) | 333734.18 | 294948.86 | 52662 | 347610.86
South Helwan PP (CP-117) | 180143 |  | South Helwan PP (CP-117) | 146691.18 | 152767.4 | 0 | 152767.4
South Helwan PP (CP-117) | 180124 |  | South Helwan PP (CP-117) | 129154.25 | 135867.05 | 0 | 135867.05
South Helwan PP (CP-117) | 180009 |  | South Helwan PP (CP-117) | 2803954.29 | 2507236.47 | 442453.49 | 2949689.96
South Helwan PP (CP-117) | 180008 |  | South Helwan PP (CP-117) | 451832.26 | 404018.82 | 71297.45 | 475316.27
South Helwan PP (CP-117) | Inv 10,11,13 SH | 10 | South Helwan PP (CP-117)10 | 705941.181 | 630052.5 | 111185.74 | 741238.24
Mall Of Egypt | OB-ST-Mall Of Egypt |  | Mall Of Egypt | 4010646.22 | 5574585.6 | 0 | 8914585.6
West Damietta PP Phase I | Collec 13,14,15 WD |  | West Damietta PP Phase I | 738082.37 | 738082.37 | 0 | 738082.37
Al-Shabab PP Phase II (CP-117) | 18 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 293419.819 | 261877.19 | 46213.62 | 308090.81
Beni Suef Substation R61 | (22) bine suef 2 |  | Beni Suef Substation R61 | 27000000 | 26703000 | 0 | 26703000
Kayan 3 New Cairo Capital City | PO.1 Kayan Healthy |  | Kayan 3 New Cairo Capital City | 3608661 | 1700365 | 1700380 | 3400745
New Capital Tunnels | (1) M.B.ZAYID |  | New Capital Tunnels | 188609742 | 56697814.75 | 65000000 | 166697814.75
Al Mostathmreen GIS Substation | SD (12) |  | Al Mostathmreen GIS Substation | 1211134 | 902294.7 | 181670.18 | 1083964.88
Al Mostathmreen GIS Substation | SD (9) MOSSTASMREEN |  | Al Mostathmreen GIS Substation | 1027945 | 765818.93 | 154191.8 | 920010.73
Al-Wukair 11 Substation | Inv 12 Qatar | 12 | Al-Wukair 11 Substation12 | 1983553 | 1983553 | 0 | 1983553
Al-Shabab PP Phase II (CP-117) | 22 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 520207.3619 | 464285.07 | 81932.66 | 546217.73
Abu Qir PP (CP-117) | Abu Quir march |  | Abu Qir PP (CP-117) | 224568.65 | 224568.65 | 0 | 224568.65
EMAAR-PKG#62-UPTOWN | (6) pkg#62 |  | EMAAR-PKG#62-UPTOWN | 2621461 | 1639531.84 | 944119.35 | 2583651.19
EMAAR-PKG#107-MARASSI | (5)pkg#107 |  | EMAAR-PKG#107-MARASSI | 5459726 | 4307013.3 | 812311.36 | 5119324.66
Barwa 2x60/22 KV S/S | Inv 31 Barwa | 31 | Barwa 2x60/22 KV S/S31 | 179906.67 | 127275.43 | 26986 | 154261.43
New Heliopolis | Inv.1 Helepolice | 1 | New Heliopolis1 | 20034607.73 | 16623290.15 | 1352336 | 17975626.15
Siemens 6x500/220 KV GIS-MOU | Soc Inv 40 Itay 11 | 40 | Siemens 6x500/220 KV GIS-MOU40 | 54225.87 | 54225.87 | 0 | 54225.87
Siemens 6x500/220 KV GIS-MOU | Ret.55kafre 3 Final |  | Siemens 6x500/220 KV GIS-MOU | 25441.51 | 25441.48 | 0 | 25441.48
EMAAR-PKG#53-UPTOWN | (19) PKG#53 |  | EMAAR-PKG#53-UPTOWN | 5695269 | 8766058.58 | 1666048.58 | 10432107.16
Tebbin PP Rehabitation(CP-124) | 1 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 156965.77 | 156965.77 | 0 | 156965.77
Suez Gulf Substation | 180053 |  | Suez Gulf Substation | 52869.27 | 50055.44 | 5561.71 | 55617.15
EMAAR-PKG#53-UPTOWN | (25)pkg#53 |  | EMAAR-PKG#53-UPTOWN | 16867950 | 12929508.46 | 2415185.85 | 15344694.31
EMAAR-PKG#53-UPTOWN | PKG#85 - IPC FINAL |  | EMAAR-PKG#53-UPTOWN | 4791697.91 | 1421729.26 | 3834934.12 | 5256663.38
Tebbin PP Rehabitation(CP-124) | 4 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 6441887 | 3761593.3 | 0 | 3761593.3
Cairo South PP Rehabilitation | 7 USD - Cairo South |  | Cairo South PP Rehabilitation | 21238.01 | 21238.01 | 0 | 21238.01
W Dam PP Phase II (CP-117) | 22 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 477822.3619 | 426456.46 | 75257.02 | 501713.48
Akhmem Assiut | Inv.53 Assuit Akhmem | 53 | Akhmem Assiut53 | 51642070.07 | 38227356.19 | 0 | 38227356.19
Akhmem Assiut | Inv.51 Assuit Akhmem | 51 | Akhmem Assiut51 | 23472356.1 | 11791613.76 | 3520853.42 | 15312467.18
Akhmem Assiut | Inv.48 Assuit Akhmem | 48 | Akhmem Assiut48 | 80837160.01 | 63860746.41 | 12125574 | 75986320.41
Akhmem Assiut | Inv.47 Assuit Akhmem | 47 | Akhmem Assiut47 | 3633884.9 | 2507380.58 | 545082.74 | 3052463.32
Akhmem Assiut | Inv.33 Assuit Akhmem | 33 | Akhmem Assiut33 | 5953611.3 | 4733120.98 | 893041.7 | 5626162.68
Akhmem Assiut | Inv.24 Assuit Akhmem | 24 | Akhmem Assiut24 | 13890660.64 | 11043075.21 | 2083599.1 | 13126674.31
Akhmem Assiut | inv. 3 Assuit Akhmem | 3 | Akhmem Assiut3 | 8913441.23 | 5303497.531 | 1337016.18 | 6640513.711
Akhmem - Qena | Inv.36 Akhmem Qena | 36 | Akhmem - Qena36 | 1803910.73 | 892935.81 | 270586.61 | 1163522.42
Akhmem - Qena | Inv.27 Akhmem Qena | 27 | Akhmem - Qena27 | 8505159.06 | 6761601.44 | 1275773.86 | 8037375.3
Akhmem - Qena | Inv.16 Qena - Akhmem | 16 | Akhmem - Qena16 | 6417286.1 | 5101742.45 | 962592.92 | 6064335.37
Akhmem - Qena | Inv.6 Qena Akhmem | 6 | Akhmem - Qena6 | 17246098.29 | 13710648.14 | 2586914.74 | 16297562.88
Al-Shabab PP Phase II (CP-117) | 25 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 103603 | 92465.68 | 16317.47 | 108783.15
Ghana | 41/P/10/ER/2017/USD |  | Ghana | 424039.64 | 424025.14 | 0 | 424025.14
Sodic Club House | (21)sodic club |  | Sodic Club House | 10206715 | 3793458.2 | 717720.45 | 4511178.65
EMAAR-PKG#53-UPTOWN | (21)pkg#53 |  | EMAAR-PKG#53-UPTOWN | 14681306 | 6077165.95 | 7105289.78 | 13182455.73
Military 110 Kayan Project | Inv. 5 El Kayan | 5 | Military 110 Kayan Project5 | 10205893.83 | 8876021.5 | 0 | 8876021.5
Abou El Matameer and Sammanoud | Inv 96 P13Abo Matami | 96 | Abou El Matameer and Sammanoud96 | 2012061.48 | 1445464.97 | 301809.22 | 1747274.19
Abou El Matameer and Sammanoud | Inv 79 P6Abo Matamir | 79 | Abou El Matameer and Sammanoud79 | 5178875.91 | 3746398.833 | 776831.387 | 4523230.22
El Mostakbal City Project | Inv. 11 Mostakbal | 11 | El Mostakbal City Project11 | 42486137.44 | 35261057.1 | 8922088.86 | 44183145.96
El Mostakbal City Project | Inv. 9 Mostakbal | 9 | El Mostakbal City Project9 | 29276861.32 | 24299794.9 | 6148140.88 | 30447935.78
El Mostakbal City Project | Inv. 8 Mostakbal | 8 | El Mostakbal City Project8 | 39792585.3 | 33027845.81 | 8356442.91 | 41384288.72
El Mostakbal City Project | Inv. 5 Mostakbal | 5 | El Mostakbal City Project5 | 43065772.12 | 35741010.54 | 9043812.15 | 44784822.69
Badr | Inv. 19 Badr | 19 | Badr19 | 21523272 | 14904446.93 | 3228490.65 | 18132937.58
Badr | Inv. 9 Badr | 9 | Badr9 | 4803637.35 | 3566286.45 | 720545.6 | 4286832.05
Badr | Inv. 6 Badr | 6 | Badr6 | 69127091.1 | 51326431.75 | 10369063.7 | 61695495.45
EMAAR-PKG117- MARASSI | 19100003 |  | EMAAR-PKG117- MARASSI | 0.01 | 121416.67 | 15486.19 | 136902.86
Kayan 3 New Cairo Capital City | (1)elkayan fainishin |  | Kayan 3 New Cairo Capital City | 47740260 | 20148095.55 | 20000000 | 40148095.55
Bani Suef Old Substation | (26)bini suif 2 |  | Bani Suef Old Substation | 400000 | 395600 | 0 | 395600
Suez Gulf Substation | 180110 |  | Suez Gulf Substation | 8441.26 | 7992 | 888 | 8880
Suez Gulf Substation | 20 EGP VO CCC Supply |  | Suez Gulf Substation | 474531.48 | 449275.75 | 49919.53 | 499195.28
Suez Gulf Substation | 17 EGP VO MRR |  | Suez Gulf Substation | 2407.93 | 2279.77 | 253.31 | 2533.08
Suez Gulf Substation | 180079 |  | Suez Gulf Substation | 3598.07 | 3406.57 | 378.51 | 3785.08
Suez Gulf Substation | 180048 |  | Suez Gulf Substation | 77707.05 | 73571.29 | 8174.59 | 81745.88
Al Mostathmreen GIS Substation | (27)sd elmostsmrin |  | Al Mostathmreen GIS Substation | 13610 | 10139.45 | 2041.5 | 12180.95
Beni Suef COMCAVI | 180002 |  | Beni Suef COMCAVI | 1124820.87 | 1124820.87 | 0 | 1124820.87
kayan wall lock & Load | KAYAN LOAK&LOAD-IPC4 | 4 | kayan wall lock & Load4 | 9337500 | 5426691.7 | 3000000 | 8426691.7
Ain-Sokhna PP (CP-117) | 180055 |  | Ain-Sokhna PP (CP-117) | 561762.4 | 561762.4 | 0 | 561762.4
Akhmem Assiut | inv. 4 Assuit Akhmem | 4 | Akhmem Assiut4 | 36927133.69 | 21971652.64 | 5539067.05 | 27510719.69
South Helwan PP (CP-117) | 180064 |  | South Helwan PP (CP-117) | 108901.12 | 97377.06 | 17184.2 | 114561.26
Akhmem - Qena | Inv. 3 Akhmem Qena | 3 | Akhmem - Qena3 | 289210582.83 | 172080296.79 | 43381587.42 | 215461884.21
Beni Seuf - 358 | Inv No 1 Bani suef | 1 | Beni Seuf - 3581 | 19501875.06 | 15503384.65 | 2925281.26 | 18428665.91
Assuit PP (CP-118) | 2106210002 |  | Assuit PP (CP-118) | 138463.73 | 123578.88 | 21808.04 | 145386.92
Assuit PP (CP-118) | 2106210001 |  | Assuit PP (CP-118) | 5370.43 | 4793.11 | 845.84 | 5638.95
Assuit PP (CP-118) | 495 |  | Assuit PP (CP-118) | 148202.43 | 132270.66 | 23341.88 | 155612.54
Assuit PP (CP-118) | 1901210010 |  | Assuit PP (CP-118) | 268880.58 | 239975.92 | 42348.69 | 282324.61
Assuit PP (CP-118) | 2103210014 |  | Assuit PP (CP-118) | 2168386.48 | 0 | 0 | 2282512.08
Assuit PP (CP-118) | 2009210003 |  | Assuit PP (CP-118) | 1593564.06 | 1406314.56 | 250986.34 | 1657300.9
Assuit PP (CP-118) | 2110210004 |  | Assuit PP (CP-118) | 30111.96 | 31617.56 | 0 | 31617.56
Assuit PP (CP-118) | 2108210009 |  | Assuit PP (CP-118) | 12404.69 | 11036.19 | 1953.74 | 12989.93
Assuit PP (CP-118) | 2105210007 |  | Assuit PP (CP-118) | 37663.2345 | 39645.51 | 0 | 39645.51
Assuit PP (CP-118) | 523 |  | Assuit PP (CP-118) | 165215.06 | 147454.44 | 26021.37 | 173475.81
Al-Shabab PP Phase II (CP-117) | 180100 |  | Al-Shabab PP Phase II (CP-117) | 138618.98 | 123950.15 | 21873.56 | 145823.71
W Dam PP Phase II (CP-117) | 180098 |  | W Dam PP Phase II (CP-117) | 337817.97 | 302069.67 | 53306.41 | 355376.08
W Dam PP Phase II (CP-117) | 180096 |  | W Dam PP Phase II (CP-117) | 51479.85 | 46032.19 | 8123.33 | 54155.52
Al-Shabab PP Phase II (CP-117) | 180020 |  | Al-Shabab PP Phase II (CP-117) | 2020199.56 | 0 | 0 | 2020199.56
Al-Shabab PP Phase II (CP-117) | 13 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 225523.9143 | 201280.09 | 35520.02 | 236800.11
Al-Shabab PP Phase II (CP-117) | 12 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 329145.7714 | 293762.6 | 51840.46 | 345603.06
Al-Wukair 11 Substation | 180073 |  | Al-Wukair 11 Substation | 7641356.9 | 7641356.9 | 0 | 7641356.9
Marsa Matrouh 500KV | Inv.63- Borg Alarab | 63 | Marsa Matrouh 500KV63 | 8459991.43 | 7389805.4 | 888299.1 | 8278104.5
Marsa Matrouh 500KV | Inv.53 Borg Alarab | 53 | Marsa Matrouh 500KV53 | 9299425.66 | 6658395.6 | 976439.69 | 7634835.29
Marsa Matrouh 500KV | Inv.50 Borg Alarab | 50 | Marsa Matrouh 500KV50 | 1817057.14 | 1587202.93 | 190791 | 1777993.93
Marsa Matrouh 500KV | Inv.23 Borg Alarab | 23 | Marsa Matrouh 500KV23 | 898345.08 | 784710.53 | 94326.23 | 879036.76
Marsa Matrouh 500KV | Inv.21 Borg Alarab | 21 | Marsa Matrouh 500KV21 | 56450073.46 | 39368912.93 | 5927257.71 | 45296170.64
Marsa Matrouh 500KV | Inv.15 Borg Alarab | 15 | Marsa Matrouh 500KV15 | 255135895.46 | 222861206.65 | 26789269.02 | 249650475.67
Marsa Matrouh 500KV | Inv.13 Borg Alarab | 13 | Marsa Matrouh 500KV13 | 34848618.38 | 26978945.51 | 3659104.93 | 30638050.44
EMAAR-PKG#107-MARASSI | PKG#107-IPC (14) | 14 | EMAAR-PKG#107-MARASSI14 | 1449945.92 | 2534475.77 | 0 | 2534475.77
Kayan 3 New Cairo Capital City | IPC4-KAYAN FAINSHING | 4 | Kayan 3 New Cairo Capital City4 | 41958350 | 30076698.55 | 8000000 | 38076698.55
Beni Suef Substation R61 | 18100064 |  | Beni Suef Substation R61 | 6146056 | 4578811.72 | 921908.4 | 5500720.12
MAYSAN 400/132kV SS | 210 |  | MAYSAN 400/132kV SS | 11507875.67 | 22841165.14 | 0 | 11507875.67
Ismailiya East Substation | (6)cw elasmaaliya |  | Ismailiya East Substation | 653189 | 486625.8 | 97978.35 | 584604.15
Ministries Buildings | Minis Core IPC07 | 7 | Ministries Buildings7 | 8616849.02 | 1814815 | 5444475.65 | 7259290.65
Apache Electrical Works | 44649.31 |  | Apache Electrical Works | 44400.7 | 44400.7 | 0 | 44400.7
W Dam PP Phase II (CP-117) | 180037 |  | W Dam PP Phase II (CP-117) | 509875.4952 | 0 | 0 | 535369.27
Amal Bridge Lock & Load | (1)alamal lock&load |  | Amal Bridge Lock & Load | 6193188.7 | 5500870.85 | 0 | 5500870.85
Beni Suef Substation R61 | BSF-CW-IPC 7 | 7 | Beni Suef Substation R617 | 2536550 | 1919216.56 | 380482.5 | 2299699.06
Lina Farm Substation | 1 USD - Lina |  | Lina Farm Substation | 69591.61 | 69591.61 | 0 | 69591.61
Akhmem - Qena | Inv.9 Qena - Akhmem$ | 9 | Akhmem - Qena9 | 2103143.58 | 1785989.17 | 0 | 1785989.17
Abou El Matameer and Sammanoud | Inv.80Samanood 4 | 80 | Abou El Matameer and Sammanoud80 | 5875862.85 | 4250599.18 | 881379.43 | 5131978.61
Akhmem Assiut | Inv.1 Assuit Akhmem$ | 1 | Akhmem Assiut1 | 730800.55 | 284979.66 | 0 | 284979.66
Substation Elco Steel | PSP ELCO-IPC 03 | 3 | Substation Elco Steel3 | 2658220.39 | 1834172.07 | 531644.08 | 2365816.15
Akhmem Assiut | Inv.21 Assuit Akhmem | 21 | Akhmem Assiut21 | 8221653.7 | 6536214.69 | 1233248.06 | 7769462.75
Angola Emergency fast-track | Inv. No. 3 | 3 | Angola Emergency fast-track3 | 74095221.35 | 60981767.22 | 0 | 60981767.22
Mohamed Ali Palace Restoration | MOHAMED ALY-IPC02 | 2 | Mohamed Ali Palace Restoration2 | 878559.52 | 603154.4 | 193732.7 | 796887.1
Air Defense College | AIR DEFENSE IPC01 | 1 | Air Defense College1 | 178355894.3 | 25742460 | 39690270 | 139299631
Tunnel of Sokhna Road | SOKHNA TUNNEL-IPC1 | 1 | Tunnel of Sokhna Road1 | 40297018 | 17624309.3 | 2000000 | 36090216.3
South Helwan PP (CP-117) | Commercial fees SH |  | South Helwan PP (CP-117) | 108518.8 | 108518.8 | 0 | 108518.8
Akhmem - Qena | Inv.10 Qena- Akhmem$ | 10 | Akhmem - Qena10 | 2008306.86 | 1705453.33 | 0 | 1705453.33
Akhmem - Qena | Inv.34 Akhmem Qena | 34 | Akhmem - Qena34 | 3086479.32 | 1527278.57 | 462971.9 | 1990250.47
Abou El Matameer and Sammanoud | 01042018 |  | Abou El Matameer and Sammanoud | 7920883.43 | 5729967.07 | 1188132.52 | 6918099.59
Badr | Inv.1-2 Project Badr | 1 | Badr1 | 35625269.15 | 11608780.25 | 5343790.4 | 16952570.65
P-28-16 Balat Owinat Lot 3 | Inv. 13 Balat lot 3 | 13 | P-28-16 Balat Owinat Lot 313 | 20489981.23 | 13133684 | 2151448.03 | 15285132.03
P-28-16 Balat Owinat Lot 3 | Inv. 11 Balat lot 3 | 11 | P-28-16 Balat Owinat Lot 311 | 22018272.86 | 16447258.48 | 2311918.65 | 18759177.13
P-28-16 Balat Owinat Lot 3 | Inv. 8 | 8 | P-28-16 Balat Owinat Lot 38 | 19805695.33 | 14794457.87 | 2079598.01 | 16874055.88
P-28-16 Balat Owinat Lot 3 | Inv. 4 Balat lot 3 | 4 | P-28-16 Balat Owinat Lot 34 | 6449395.47 | 4817309.13 | 677186.52 | 5494495.65
Sodic Club House | SODIC CLUB-IPC 32 | 32 | Sodic Club House32 | 6867125.7 | 1852842.635 | 693560.3 | 2546402.935
Elsewedy Univ - Enabling Works | ELSEWEDY MEP-IPC05 | 5 | Elsewedy Univ - Enabling Works5 | 8018043.81 | 4527299.6805 | 1589066.44 | 6116366.1205
Elsewedy Univ - Enabling Works | ELSEWEDY UNI- IPC06 | 6 | Elsewedy Univ - Enabling Works6 | 339719.88 | 235901.484 | 107011.76 | 342913.244
Elsewedy Univ - Enabling Works | 19100031 |  | Elsewedy Univ - Enabling Works | 267331.59 | 185635.0495 | 84209.45 | 269844.4995
Elsewedy Univ - Enabling Works | 19100030 |  | Elsewedy Univ - Enabling Works | 5121900.87 | 3208255.7535 | 1075599.18 | 4283854.9335
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-MEP-03 | 3 | Elsewedy Univ - Enabling Works3 | 4458365.84 | 3212953.442 | 936256.83 | 4149210.272
Akhmem Assiut | Inv.11Assuit Akhmem$ | 11 | Akhmem Assiut11 | 3279975.01 | 2771864 | 0 | 2771864
Bani Suef Old Substation | bani suif 2-ipc 28 | 28 | Bani Suef Old Substation28 | 1803926.68 | 1720326.28 | 0 | 1720326.28
EMAAR-PKG#53-UPTOWN | PKG#53 -IPC 35 | 35 | EMAAR-PKG#53-UPTOWN35 | 3328558.25 | 2331143.99 | 0 | 2331143.99
Ministries Buildings | MinisLandscape IPC05 | 5 | Ministries Buildings5 | 5135274.68 | 2197700 | 2197690 | 4395390
Hassan El Mamoun Bridge | Hassan Mamoun Final |  | Hassan El Mamoun Bridge | 4216610.86 | 5441365.003 | 1875138.85 | 7316503.853
Mohamed Ali Palace Restoration | PO - Mohamed Aly 105 |  | Mohamed Ali Palace Restoration | 483986.35 | 343355 | 114455.7 | 457810.7
Mohamed Ali Palace Restoration | PO - Mohamed Aly 114 |  | Mohamed Ali Palace Restoration | 483236.15 | 342825 | 114277.5 | 457102.5
Baron Fence | ELBARON-IPC FINAL |  | Baron Fence | 3562756.1 | 2033350 | 2033370 | 4066720
Akhmem Assiut | ref.soci12-16 Assuit | 16 | Akhmem Assiut16 | 2232266.01 | 2232266.01 | 0 | 2232266.01
New Capital Tunnels | M.B.Z.TUNNEL IPC 4 | 4 | New Capital Tunnels4 | 11676873.05 | 3408205.8 | 1115000 | 9937980.8
Marsa Matrouh 500KV | Inv.1 Borg Alarab | 1 | Marsa Matrouh 500KV1 | 128259940.46 | 128259940.46 | 0 | 128259940.46
Akhmem - Qena | Inv.23 Qena- Akhmem$ | 23 | Akhmem - Qena23 | 122979.52 | 103749.29 | 0 | 103749.29
Canal Regional Control Center | Inv.8 Rcc | 8 | Canal Regional Control Center8 | 7912822.95 | 4478650.2 | 1661692.82 | 6140343.02
Canal Regional Control Center | Inv.5 Rcc | 5 | Canal Regional Control Center5 | 14317304.05 | 8102976.37 | 3006633.85 | 11109610.22
Badr | Inv. 2 Badr | 2 | Badr2 | 13460693.5 | 9994146.6 | 2019104.05 | 12013250.65
Tamey El-amdeed Substation | TAM-CW-EGP-06 | 6 | Tamey El-amdeed Substation6 | 2763337.82 | 2058686.68 | 414500.67 | 2473187.35
Beni Suef Substation R61 | 2cw bine suif |  | Beni Suef Substation R61 | 10571146.54 | 7913165.95 | 1585671.98 | 9498837.93
Akhmem - Qena | Inv.44 Qena Akhmem | 44 | Akhmem - Qena44 | 803265.02 | 558269.19 | 120489.75 | 678758.94
Akhmem Assiut | Inv.37 Assuit Akhmem | 37 | Akhmem Assiut37 | 8582153.7 | 6822812.19 | 1287323.06 | 8110135.25
P-28-16 Balat Owinat Lot 2 | Inv. 15 Balat Lot 2 | 15 | P-28-16 Balat Owinat Lot 215 | 3764174.84 | 2980834.24 | 0 | 2980834.24
Akhmem Assiut | Inv.10Assuit Akhmem$ | 10 | Akhmem Assiut10 | 3251534.26 | 2741835.94 | 0 | 2741835.94
P-28-16 Balat Owinat Lot 2 | Inv. 4 Balat Lot 2 | 4 | P-28-16 Balat Owinat Lot 24 | 6749613.52 | 5041564.14 | 708709.42 | 5750273.56
P-28-16 Balat Owinat Lot 2 | Inv. 1 Balat Lot 2 | 1 | P-28-16 Balat Owinat Lot 21 | 35668193.1 | 26643741.23 | 3745160.5 | 30388901.73
Marsa Matrouh 500KV | Inv10 Usd borg alarb | 10 | Marsa Matrouh 500KV10 | 5555561.09 | 4606754.58 | 555556.11 | 5426861.22
K047 FDH JV | Inv. No.10 KWD Floor | 10 | K047 FDH JV10 | 25274.2 | 22746.78 | 0 | 22746.78
Abou El Matameer and Sammanoud | Inv 94P9Abo Matami | 94 | Abou El Matameer and Sammanoud94 | 3180991.96 | 2285224.62 | 477148.79 | 2762373.41
Akhmem - Qena | Inv.3 Qena - Akhmem$ | 3 | Akhmem - Qena3 | 1801897.56 | 1515450.87 | 0 | 1515450.87
South Helwan PP (CP-117) | 180141 |  | South Helwan PP (CP-117) | 200061.46 | 208603.47 | 0 | 208603.47
Beni Suef Substation R61 | BSF-SW-05 | 5 | Beni Suef Substation R615 | 725375 | 539875.47 | 108806.25 | 648681.72
Manshiet Nasser Substation | 180171 |  | Manshiet Nasser Substation | 908445.29 | 953867.56 | 0 | 953867.56
South Helwan PP (CP-117) | 180148 |  | South Helwan PP (CP-117) | 233646.38 | 244575.79 | 0 | 244575.79
Akhmem Assiut | Inv.21Assuit Akhmem$ | 21 | Akhmem Assiut21 | 418013.32 | 290171.67 | 0 | 290171.67
Akhmem Assiut | Inv.18Assuit Akhmem$ | 18 | Akhmem Assiut18 | 1405814.84 | 1187878.74 | 0 | 1187878.74
NUCA R05 - Z02 | R05 IPC#032 | 32 | NUCA R05 - Z0232 | 8394775.5 | 0 | 805622.55 | 805622.55
NUCA R05 - Z02 | R5-IPC23 | 23 | NUCA R05 - Z0223 | 88626920.85 | 72093367.1 | 9076871.1 | 81170238.2
AWEER POWER STATION 'H' Phase | LOC 027 |  | AWEER POWER STATION 'H' Phase | 8676.56 | 0 | 964.06 | 964.06
AWEER POWER STATION 'H' Phase | LOC/019 |  | AWEER POWER STATION 'H' Phase | 816011.56 | 716276.81 | 90667.95 | 806944.76
AWEER POWER STATION 'H' Phase | LOC/017 |  | AWEER POWER STATION 'H' Phase | 2594016.68 | 2276970.19 | 288224.08 | 2565194.27
AWEER POWER STATION 'H' Phase | CON/021 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
AWEER POWER STATION 'H' Phase | IMP-055 | 55 | AWEER POWER STATION 'H' Phase55 | 1524830.95 | 1507601.2245 | 0 | 1507601.2245
AWEER POWER STATION 'H' Phase | IMP-052 | 52 | AWEER POWER STATION 'H' Phase52 | 554585.89 | 553663.02 | 0 | 553663.02
AWEER POWER STATION 'H' Phase | IMP-037prog for33/34 | 37 | AWEER POWER STATION 'H' Phase37 | 10012746.61 | 8788966.4705 | 1112527.4 | 9901493.8705
AWEER POWER STATION 'H' Phase | 10387 |  | AWEER POWER STATION 'H' Phase | 4152520.61 | 3644990.3105 | 461391.18 | 4106381.4905
AWEER POWER STATION 'H' Phase | 10370 |  | AWEER POWER STATION 'H' Phase | 1916547.97 | 1682303.2085 | 212949.78 | 1895252.9885
Kayan 3 New Cairo Capital City | KAYAN SIHY-IPC 1 | 1 | Kayan 3 New Cairo Capital City1 | 3060785 | 1998988.35 | 450000 | 2448988.35
EDNC Retail & Offices Civil | SOREAL-IPC12 | 12 | EDNC Retail & Offices Civil12 | 33309635.84 | 24940111.3195 | 6343196.86 | 31283308.1795
EDNC Retail & Offices Civil | SOREAL-IPC11 | 11 | EDNC Retail & Offices Civil11 | 36710088.58 | 29504362.289 | 1807968.97 | 31312331.259
EDNC Retail & Offices Civil | soreal - ipc 02 | 2 | EDNC Retail & Offices Civil2 | 20887437.31 | 15638373.6555 | 4386361.84 | 20024735.4955
SHATRA 400/132kV SS | 213 |  | SHATRA 400/132kV SS | 6339895.72 | 6339895.72 | 0 | 6339895.72
Tamey El-amdeed Substation | TAM-SD-EGP-03 | 3 | Tamey El-amdeed Substation3 | 648000 | 479520 | 97200 | 576720
South Helwan PP (CP-117) | 180150 |  | South Helwan PP (CP-117) | 791434.01 | 897916.35 | 0 | 897916.35
EMAAR-PKG# 144, Marassi | PKG#144- IPC04 | 4 | EMAAR-PKG# 144, Marassi4 | 11222644.64 | 6887337.022 | 3535133.06 | 10422470.082
Al Mostathmreen GIS Substation | MOS-SD-EURO-13 | 13 | Al Mostathmreen GIS Substation13 | 209034.12 | 3735409.96 | 31355.12 | 3766765.08
Tamey El-amdeed Substation | 19100019 |  | Tamey El-amdeed Substation | 2369397.12 | 1753353.87 | 355409.57 | 2108763.44
Asec Spare-Parts | Inv 3 EUR Asec Spare | 3 | Asec Spare-Parts3 | 5090 | 3797 | 1601.2 | 5398.2
DPW Onshore Port & Terminal | DPW IPC031 | 31 | DPW Onshore Port & Terminal31 | 13597917.63 | 10014939.05 | 2039687.64 | 12054626.69
DPW Onshore Port & Terminal | DP World IPC026 | 26 | DPW Onshore Port & Terminal26 | 30564756.18 | 22617919.57 | 4584713.43 | 27202633
Akhmem - Qena | Soc Inv 42-43-44Quna | 42 | Akhmem - Qena42 | 574975.25 | 574975.25 | 0 | 574975.25
Akhmem - Qena | Ref Soc Inv 25 quna | 25 | Akhmem - Qena25 | 91566.75 | 91566.75 | 0 | 91566.75
Marsa Matrouh 500KV | Inv.17Usd borg alarb | 17 | Marsa Matrouh 500KV17 | 332662 | 289440.57 | 34929.51 | 324370.08
Marsa Matrouh 500KV | Inv.11 Borg Alarab | 11 | Marsa Matrouh 500KV11 | 1466699.73 | 1232282.51 | 154003.47 | 1386285.98
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC05 | 5 | Elsewedy Univ - Enabling Works5 | 18231859.57 | 121094303.2925 | 27208425.8 | 29660545.8185
Tamey El-amdeed Substation | 19100027 |  | Tamey El-amdeed Substation | 734564.04 | 543577.39 | 110184.61 | 653762
Akhmem Assiut | Inv.40 Assuit Akhmem | 40 | Akhmem Assiut40 | 3239324.7 | 2545198.51 | 485898.71 | 3031097.22
Akhmem Assiut | Inv.46 Assuit Akhmem | 46 | Akhmem Assiut46 | 2857281.59 | 2000097.1 | 428592.24 | 2428689.34
Akhmem Assiut | Inv.20Assuit Akhmem$ | 20 | Akhmem Assiut20 | 1244034.52 | 1030051.79 | 0 | 1030051.79
Akhmem - Qena | Inv.7 Qena - Akhmem$ | 7 | Akhmem - Qena7 | 1482882.32 | 1259261.66 | 0 | 1259261.66
Flour project | 10077 |  | Flour project | 36786 | 36786 | 0 | 36786
RME- Marassi Sidi Abdel Rahman | Sales-03 | 3 | RME- Marassi Sidi Abdel Rahman3 | 150000 | 150000 | 0 | 150000
MOTHANA 400/132kV SS | 211 |  | MOTHANA 400/132kV SS | 6708419.33 | 6708419.33 | 0 | 6708419.33
kayan wall lock & Load | KAYAN LOAK&LOAD-IPC7 | 7 | kayan wall lock & Load7 | 9270000 | 2718297 | 5647472.9 | 8365769.9
Kayan 3 New Cairo Capital City | KAYAN SAHY- IPC02 | 2 | Kayan 3 New Cairo Capital City2 | 6155815 | 1804764 | 3750450 | 5555214
Royal City | ROYAL CITY-IPC15 | 15 | Royal City15 | 8723893.09 | 6570751.8245 | 2830535.65 | 9401287.4745
Beni Suef Substation R61 | BSF-CW-EURO-05 | 5 | Beni Suef Substation R615 | 4505119.11 | 3356313.73 | 675767.87 | 4032081.6
New Capital | Inv. 8 Abo Zabal | 8 | New Capital8 | 1565685.9 | 905936.5 | 164397.02 | 1070333.52
Beni Suef Substation R61 | 19100025 |  | Beni Suef Substation R61 | 202562 | 149895.88 | 30384.3 | 180280.18
Al-Wukair 11 Substation | 1902210007 |  | Al-Wukair 11 Substation | 5694082.79 | 5694082.79 | 0 | 5694082.79
EMAAR-PKG117- MARASSI | PKG#117 -IPC 10 | 10 | EMAAR-PKG117- MARASSI10 | 1067786.52 | 938354.286 | 112117.59 | 1050471.876
Manshiet Nasser Substation | 2011210002 |  | Manshiet Nasser Substation | 12360.29 | 2658.44 | 1854.04 | 4512.48
Manshiet Nasser Substation | 2001210005 |  | Manshiet Nasser Substation | 1090204.98 | 819235.17 | 175467.3 | 994702.47
Manshiet Nasser Substation | 545 |  | Manshiet Nasser Substation | 321701.84 | 241745.72 | 51777.56 | 293523.28
Manshiet Nasser Substation | 506 |  | Manshiet Nasser Substation | 401551.96 | 119347.17 | 60232.79 | 179579.96
Manshiet Nasser Substation | 488 |  | Manshiet Nasser Substation | 966716.73 | 792055.07 | 156470.55 | 948525.62
Manshiet Nasser Substation | 1908210016 |  | Manshiet Nasser Substation | 1206654.4 | 848817.86 | 194209.7 | 1043027.56
Manshiet Nasser Substation | 1908210015 |  | Manshiet Nasser Substation | 242625.47 | 114459.02 | 39050.3 | 153509.32
Manshiet Nasser Substation | 180175 |  | Manshiet Nasser Substation | 1243908.62 | 1168963.12 | 137140.93 | 1306104.05
Manshiet Nasser Substation | 180167 |  | Manshiet Nasser Substation | 968498.97 | 910146.91 | 106777.01 | 1016923.92
Manshiet Nasser Substation | 180177 |  | Manshiet Nasser Substation | 437296.6 | 371702.11 | 65594.49 | 437296.6
Military 110 Kayan Project | Elkayan Inv.16 | 16 | Military 110 Kayan Project16 | 3660653.12 | 3303334.3 | 0 | 3303334.3
Manshiet Nasser Substation | 2004210013 |  | Manshiet Nasser Substation | 27280.96 | 20306.88 | 4307.52 | 24614.4
Manshiet Nasser Substation | 505 |  | Manshiet Nasser Substation | 153924.49 | 0 | 23088.67 | 23088.67
El Mostakbal City Project | Inv. 3 Mostakbal | 3 | El Mostakbal City Project3 | 5587780.17 | 4637139.7 | 1173433.84 | 5810573.54
Akhmem Assiut | Inv.22 Assuit Akhmem | 22 | Akhmem Assiut22 | 9922685.59 | 7888535.04 | 1488402.84 | 9376937.88
Beni Seuf - 358 | Inv.5 kafr zeat itay | 5 | Beni Seuf - 3585 | 67332375 | 53128795.9 | 10163025 | 63291820.9
Beni Seuf - 358 | Insu. inv.3 itay 358 | 3 | Beni Seuf - 3583 | 1009906 | 1004770.86 | 0 | 1004770.86
Abou El Matameer and Sammanoud | Inv100 P12- Sammound | 100 | Abou El Matameer and Sammanoud100 | 4186152.58 | 3007332 | 627922.89 | 3635254.89
EMAAR-PKG# 144, Marassi | pkg#144-IPC11 | 11 | EMAAR-PKG# 144, Marassi11 | 8979474.51 | 7386054.95 | 924705.34 | 8310760.29
EMAAR-PKG# 144, Marassi | PKG#144-IPC-02 | 2 | EMAAR-PKG# 144, Marassi2 | 4125990.87 | 2748735.1235 | 1299687.12 | 4048422.2435
Cameron EDC | 009/2019 |  | Cameron EDC | 193370.11 | 188146.27 | 0 | 188146.27
NUCA R05 - Z02 | R5-ZONE 2-IPC 01 | 1 | NUCA R05 - Z021 | 69830383.75 | 67099356.65 | 8271331.91 | 75370688.56
New Capital | Inv. 7 Eltbeen | 7 | New Capital7 | 1754884.33 | 1320021.28 | 138268.58 | 1458289.86
Assuit PP (CP-118) | 1902210003 |  | Assuit PP (CP-118) | 72541.64 | 64743.41 | 11425.31 | 76168.72
Assuit PP (CP-118) | 1902210002 |  | Assuit PP (CP-118) | 74364.24 | 66370.08 | 11712.37 | 78082.45
MOTHANA 400/132kV SS | 223 |  | MOTHANA 400/132kV SS | 1045788.16 | 1045788.16 | 0 | 1045788.16
4 SS - Technical Service | 226 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Kuwait | Civil/J011 |  | Kuwait | 38063.33 | 28547.5 | 0 | 28547.5
Development of Mahmudiyah axis | IPC#3 | 3 | Development of Mahmudiyah axis3 | 1372500 | 1334070 | 0 | 1334070
EDNC Retail & Offices Civil | SOREAL- IPC 01 | 1 | EDNC Retail & Offices Civil1 | 9063098.33 | 6789620.1165 | 1903250.65 | 8692870.7665
Bani Suef Old Substation | (27)bini suif 2 |  | Bani Suef Old Substation | 2949400.18 | 2738736.37 | 0 | 2738736.37
Substation Elco Steel | PSPELCO-IPC09 | 9 | Substation Elco Steel9 | 1904763.72 | 1314286.96 | 380952.74 | 1695239.7
Badr | Inv. 10 Badr | 10 | Badr10 | 106542720 | 79107431.75 | 15981408 | 95088839.75
EMAAR-PKG#22-MARASSI | (36) PKG#22 |  | EMAAR-PKG#22-MARASSI | 150622 | 739720.27 | 15499.05 | 755219.32
SHATRA 400/132kV SS | 231 |  | SHATRA 400/132kV SS | 503921.87 | 503921.87 | 0 | 503921.87
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC03 | 3 | EMAAR-PKG# 101-UPTOWN3 | 3744391.54 | 2222206.627 | 1179483.34 | 3401689.967
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 34 | 34 | Benban 500 K.V/95 K.M34 | 10623483.11 | 8190712.81 | 1115465.73 | 9306178.54
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 15 | 15 | Benban 500 K.V/95 K.M15 | 21346551.17 | 16458190 | 2241387.87 | 18699577.87
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 32 | 32 | Benban 500 K.V / 100 K.M32 | 2736724.03 | 2110014.74 | 287356.02 | 2397370.76
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 17 | 17 | Benban 500 K.V / 100 K.M17 | 85828107.45 | 69189323.23 | 9011951.28 | 78201274.51
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 30 | 30 | Benban 500 K.V / 100 K.M30 | 4207664.99 | 3244109.7 | 441804.82 | 3685914.52
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 22 | 22 | Benban 500 K.V / 100 K.M22 | 40851099.66 | 28496201.74 | 4289365.46 | 32785567.2
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 27 | 27 | Benban 500 K.V / 100 K.M27 | 294497.14 | 227064.76 | 30922.2 | 257986.96
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 25 | 25 | Benban 500 K.V / 100 K.M25 | 3537359.2 | 2727310.16 | 371422.72 | 3098732.88
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 5 | 5 | Benban 500 K.V / 100 K.M5 | 705434.09 | 543896.58 | 74070.58 | 617967.16
Ismailiya East Substation | ISE-CW-EGP-14 | 14 | Ismailiya East Substation14 | 1815042 | 1343131.08 | 272256.3 | 1615387.38
Ismailiya East Substation | ISE-CW-EGP-15 | 15 | Ismailiya East Substation15 | 5774580 | 4273189.2 | 866187 | 5139376.2
Abou El Matameer and Sammanoud | Soci. 16 Fin. Matmer |  | Abou El Matameer and Sammanoud | 90443 | 90442.81 | 0 | 90442.81
Canal Sugar OHTL | Inv.08 Sugar OHTL | 8 | Canal Sugar OHTL8 | 2463262.79 | 412075.77 | 369489.42 | 781565.19
Marsa Matrouh 500KV | Inv.27 Borg Alarab | 27 | Marsa Matrouh 500KV27 | 25596171.43 | 22358260.29 | 2687598 | 25045858.29
Elco Steel 220/33 KV SS | 1901210015 |  | Elco Steel 220/33 KV SS | 4884581.7 | 5128810.79 | 0 | 5128810.79
Elco Steel 220/33 KV SS | 1901210006 |  | Elco Steel 220/33 KV SS | 2473969.04 | 2597667.49 | 0 | 2597667.49
Substation Elco Steel | PSP ELCO-IPC10 | 10 | Substation Elco Steel10 | 4730762.03 | 3744490.63 | 946152.41 | 4690643.04
Elsewedy Univ - Enabling Works | UNI-FIN&MEP-IPC10 | 10 | Elsewedy Univ - Enabling Works10 | 30617684.7 | 20919758.826 | 5586427.55 | 26506186.376
MOTHANA 400/132kV SS | 236 |  | MOTHANA 400/132kV SS | 568086.84 | 568086.84 | 0 | 568086.84
Manshiet Nasser Substation | 1904210016 |  | Manshiet Nasser Substation | 551062.32 | 468402.97 | 82659.35 | 551062.32
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 1USD | 1 | Benban 500 K.V / 100 K.M1 | 571610.74 | 480153.02 | 60019.13 | 540172.15
SHAT Al ARAB 400/132kV SS | 230 |  | SHAT Al ARAB 400/132kV SS | 673168.29 | 666703.01 | 0 | 673168.29
MOTHANA 400/132kV SS | 234 |  | MOTHANA 400/132kV SS | 547002.82 | 547002.82 | 0 | 547002.82
Manshiet Nasser Substation | 180174 |  | Manshiet Nasser Substation | 1718539.45 | 1787279.9 | 0 | 1787279.9
Royal City | ROYAL CITY-IPC35 | 35 | Royal City35 | 6572349.74 | 2752213.4436 | 1237553.21 | 3989766.6536
Royal City | ROYAL ZONE2-IPC18 | 18 | Royal City18 | 1609316.03 | 1107014.8815 | 299495.48 | 1406510.3615
Cairo Capital S1 | Inv. 7 Project S 1 | 7 | Cairo Capital S17 | 101859241.52 | 76648660.65 | 15278894.25 | 91927554.9
Amal Bridge Lock & Load | AMAL LOCK&LOAD-FINAL |  | Amal Bridge Lock & Load | 1991284.16 | 1257449.1 | 948500 | 2205949.1
Cairo Capital S1 | Inv. 6 Project S 1 | 6 | Cairo Capital S16 | 120888968.38 | 90968547.85 | 18133345.26 | 109101893.11
EDNC Retail & Offices Civil | SOREAL-IPC04 | 4 | EDNC Retail & Offices Civil4 | 36280262.26 | 26537436.313 | 9089929.31 | 35627365.623
Zambia Project | SCD4/003Adj |  | Zambia Project | 96528.24 | 0 | 0 | 96528.24
Port Said Subs 220/66 | Port Said Inv. 4 | 4 | Port Said Subs 220/664 | 39009058.49 | 25160420 | 9752264.62 | 34912684.62
Port Said Subs 220/66 | Adv.CR. Port Said |  | Port Said Subs 220/66 | 0 | 0 | -5500000 | -5500000
Akhmem Assiut | Inv.9 Assuit Akhmem | 9 | Akhmem Assiut9 | 28602698.23 | 17018605.45 | 4290404.73 | 21309010.18
Akhmem Assiut | Inv.8 Assuit Akhmem | 8 | Akhmem Assiut8 | 39473811.19 | 23486917.65 | 5921071.68 | 29407989.33
Badr | Inv. 13 Badr | 13 | Badr13 | 19087247 | 14171862.65 | 2863087.05 | 17034949.7
AWEER POWER STATION 'H' Phase | 10127 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
Elsewedy Univ - Enabling Works | uni fi&mep-ipc 07 | 7 | Elsewedy Univ - Enabling Works7 | 35759955.8 | 37410862.9635 | 6397823 | 43808685.9635
Assuit PP (CP-118) | 1907210002 |  | Assuit PP (CP-118) | 184213.03 | 164410.13 | 29013.55 | 193423.68
Cameron EDC | 021/2019 |  | Cameron EDC | 126058.47 | 125908.06 | 0 | 125908.06
MAYSAN 400/132kV SS | 248 |  | MAYSAN 400/132kV SS | 159025.9 | 159025.9 | 0 | 159025.9
Akhmem - Qena | Inv.35 Akhmem Qena | 35 | Akhmem - Qena35 | 394117 | 273911.31 | 59117.55 | 333028.86
Elco Steel 220/33 KV SS | 1908210005 |  | Elco Steel 220/33 KV SS | 364073.7 | 382277.38 | 0 | 382277.38
Suez IPB | 2*4 EGP - Suez Steel |  | Suez IPB | 10535.48 | 10535.48 | 0 | 10535.48
MAYSAN 400/132kV SS | 256 |  | MAYSAN 400/132kV SS | 252646.56 | 252646.56 | 0 | 252646.56
4 SS - Technical Service | 262 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Latin Quarter- New Alamein | inv ( 3 ) 23-5-2021 | 3 | Latin Quarter- New Alamein3 | 9566707.5 | 3832849.47 | 0 | 3832849.47
Latin Compound - New Alamin | INV(12)310520 | 12 | Latin Compound - New Alamin12 | 222020.4 | 185272.25 | 0 | 185272.25
Neighborhood New Capital R5 | inv ( 1 ) 21-12-2020 | 1 | Neighborhood New Capital R51 | 7790560 | 6219826.36 | 0 | 6219826.36
LAYYAH CCPP | 510 |  | LAYYAH CCPP | 4935294 | 4194999.9 | 740294.1 | 4935294
LAYYAH CCPP | 503 |  | LAYYAH CCPP | 335375 | 299322.19 | 50306.25 | 349628.44
DoubleTree Mangroovy ElGouna | MANGROVE-IPC09 | 9 | DoubleTree Mangroovy ElGouna9 | 1505090.04 | 1030964.272 | 395086.14 | 1426050.412
DoubleTree Mangroovy ElGouna | MANGROVE-IPC08 | 8 | DoubleTree Mangroovy ElGouna8 | 2806757.16 | 1896543.798 | 736773.76 | 2633317.558
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 5 | 5 | Benban 500 K.V/95 K.M5 | 2486577.93 | 1917150.79 | 261090.68 | 2178241.47
Beni Suef Substation R61 | BSF-SW-EGP-10 | 10 | Beni Suef Substation R6110 | 74375 | 55037.5 | 11156.25 | 66193.75
EMAAR-PKG# 101-UPTOWN | PKG#101- IPC12 | 12 | EMAAR-PKG# 101-UPTOWN12 | 361420.4 | 1829340.96 | 716279.53 | 2545620.49
MAYSAN 400/132kV SS | 247 |  | MAYSAN 400/132kV SS | 1403399.06 | 2806798.12 | 0 | 1403399.06
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 4 | 4 | Benban 500 K.V / 100 K.M4 | 56869419.86 | 43846329.48 | 5971289.09 | 49817618.57
Tamey El-amdeed Substation | TAM-SW-EGP-08 | 8 | Tamey El-amdeed Substation8 | 843500 | 348952.51 | 126525 | 475477.51
Canal Sugar 33KV OHTL | Inv. 1 Sugar 33 OHTL | 1 | Canal Sugar 33KV OHTL1 | 9703293.36 | 7665601.76 | 1455494 | 9121095.76
33KV Canal Farm Grid | Inv. 10 Farm | 10 | 33KV Canal Farm Grid10 | 535000 | 408205 | 80250 | 488455
EMAAR-PKG#53-UPTOWN | PKG#53 - IPC40 | 40 | EMAAR-PKG#53-UPTOWN40 | 51326.53 | 11242137.74 | 0 | 11242137.74
P-28-16 Balat Owinat Lot 2 | Inv. 12 Balat Lot 2 | 12 | P-28-16 Balat Owinat Lot 212 | 15855149.71 | 11843405.414 | 1664790.72 | 13508196.134
Alamein | ELALAMEEN ROAD-IPC01 | 1 | Alamein1 | 20204000 | 17014223.5 | 0 | 17976318.74
Benban 500 K.V/95 K.M | Benban Lot2 Inv 6 $ | 6 | Benban 500 K.V/95 K.M6 | 67461.72 | 56667.85 | 7083.48 | 63751.33
Mohamed Aly Fahmy Lock&Load | M.ALY FAHMY L&L-01 | 1 | Mohamed Aly Fahmy Lock&Load1 | 6313890 | 1660170 | 3652219 | 5312389
Benban 500 K.V/95 K.M | Benban Lot2 Inv 3 $ | 3 | Benban 500 K.V/95 K.M3 | 144197.92 | 121126.26 | 15140.78 | 136267.04
LAYYAH CCPP | 524 |  | LAYYAH CCPP | 9521850 | 0 | 2268593 | 2268593
LAYYAH CCPP | 513 |  | LAYYAH CCPP | 4411860 | 4171455 | 240405 | 4411860
LAYYAH CCPP | 499 |  | LAYYAH CCPP | 12854700 | 11387526.75 | 2046725 | 13434251.75
LAYYAH CCPP | 498 |  | LAYYAH CCPP | 10283760 | 8700880.65 | 1997207 | 10698087.65
LAYYAH CCPP | 487 |  | LAYYAH CCPP | 6538440 | 6483455 | 54985 | 6538440
Ghana Street lighting | MIDA Ins. Inv. 2 | 2 | Ghana Street lighting2 | 181312.03 | 181312.03 | 0 | 181312.03
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 11 | 11 | Benban 500 K.V / 100 K.M11 | 922953 | 711005.11 | 96910.07 | 807915.18
Nuweibaa (Swro) | Invoice No:11 |  | Nuweibaa (Swro) | 846941.68 | 677553.344 | 169388.336 | 846941.68
Nuweibaa (Swro) | 2002210001 |  | Nuweibaa (Swro) | 57926.6 | 46341.28 | 11585.32 | 57926.6
Beni-Suef Power Plant EPC | reclass rec 1020 |  | Beni-Suef Power Plant EPC | 986446760.8 | 535100901.48 | 0 | 986446760.8
Oasis Buildings- New Capital | Inv(2)090120 | 2 | Oasis Buildings- New Capital2 | 40551.6 | 33601.19 | 0 | 33601.19
Beni Suef Add-on Sales | 1908210010 |  | Beni Suef Add-on Sales | 381712.08 | 423700.34 | 0 | 423700.34
Olympic Multi – Sports Hall | OLYMPIC-IPC01 | 1 | Olympic Multi – Sports Hall1 | 155024274.9 | 3412855 | 65687110.54 | 134650985.79
Assuit PP (CP-118) | 494 |  | Assuit PP (CP-118) | 212481.68 | 189639.9 | 33465.86 | 223105.76
Celia | IPC#2 | 2 | Celia2 | 611543.5 | 558339.21 | 0 | 573540.4357
R5 Mix-Use Complex Project | R5-ZONE1-IPC08 | 8 | R5 Mix-Use Complex Project8 | 1463610.7 | 1229663.885 | 152720.23 | 1382384.115
Marsa Matrouh 500KV | Inv.44 Borg Alarab | 44 | Marsa Matrouh 500KV44 | 32018947.4 | 15966147.8 | 3361989.48 | 19328137.28
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 21 | 21 | Benban 500 K.V/95 K.M21 | 430790.51 | 332140.6 | 45233 | 377373.6
33KV Canal Farm Grid | Inv. 01 Farm | 1 | 33KV Canal Farm Grid1 | 31513076.75 | 24895153.72 | 4726961.51 | 29622115.23
Canal Sugar OHTL | Inv.03 Sugar OHTL | 3 | Canal Sugar OHTL3 | 27741223.11 | 21915566.26 | 4161183.47 | 26076749.73
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 24 | 24 | Benban 500 K.V/95 K.M24 | 7600808.43 | 5859632.23 | 798084.89 | 6657717.12
Sewage Treatment Plant | IPC#1 | 1 | Sewage Treatment Plant1 | 518585 | 0 | 0 | 518585
Lock&Load-30June w Sokhna Rd | 30YU GALALA-L&L-1FIN | 1 | Lock&Load-30June w Sokhna Rd1 | 1030928 | 454415 | 454429.05 | 908844.05
Ministries Buildings | MIN.ALLOCATION-IPC03 | 3 | Ministries Buildings3 | 9291713.23 | 1741265 | 6179524.33 | 7920789.33
Ministries Buildings | MINISTIRY OLD-IPC03 | 3 | Ministries Buildings3 | 20267785 | 35295710 | 7760638.6 | 43940248.6
Suez Gulf Substation | 486 |  | Suez Gulf Substation | 43989.39 | 41648.17 | 4627.57 | 46275.74
R5 | inv(4)101219 | 4 | R54 | 7087635 | 583758.67 | 0 | 1391663.81
DoubleTree Mangroovy ElGouna | MANGOROVE RENT-IPC01 | 1 | DoubleTree Mangroovy ElGouna1 | 80875 | 73813.1925 | 0 | 73813.1925
NUCA R05 - Z02 | R5-IPC10 | 10 | NUCA R05 - Z0210 | 26640996.55 | 23900162.4 | 2954891.2 | 26855053.6
Assuit PP (CP-118) | 511 |  | Assuit PP (CP-118) | 262453.06 | 234239.35 | 41336.36 | 275575.71
Elco Steel 220/33 KV SS | 1906210003 |  | Elco Steel 220/33 KV SS | 17487.27 | 17487.27 | 0 | 17487.27
Elco Steel 220/33 KV SS | 1903210008 |  | Elco Steel 220/33 KV SS | 1530321.21 | 1606837.27 | 0 | 1606837.27
SHAT Al ARAB 400/132kV SS | 282 |  | SHAT Al ARAB 400/132kV SS | 757999.5 | 757999.5 | 0 | 757999.5
EDNC Retail & Offices Civil | SOREAL -IPC09 | 9 | EDNC Retail & Offices Civil9 | 19102003.8 | 40883545.558 | 12988267.08 | 53871812.638
Akhmem Assiut | Inv.24Assuit Akhmem$ | 24 | Akhmem Assiut24 | 357869.09 | 304188.72 | 0 | 304188.72
Toshka GIS 500 kV | Toshka Sub Inv. 09 | 9 | Toshka GIS 500 kV9 | 36373061.91 | 18809143.05 | 9547928.75 | 28357071.8
Toshka GIS 500 kV | Toshka Sub Inv. 05 | 5 | Toshka GIS 500 kV5 | 15409476.01 | 9699875.6 | 4044987.45 | 13744863.05
Toshka GIS 500 kV | Toshka Sub Inv. 03 | 3 | Toshka GIS 500 kV3 | 12049713.8 | 7874488.39 | 3163049.87 | 11037538.26
Mauritania-Lot 2 | Inv.3 – Lot 2 | 3 | Mauritania-Lot 23 | 1830052.44 | 1738549.82 | 0 | 1738549.82
IKEA Extension MoA | IKEA-IPC+02 | 2 | IKEA Extension MoA2 | 535990.4 | 535990.4 | 0 | 535990.4
kayan wall lock & Load | KAYAN LOAK&LOAD08 |  | kayan wall lock & Load | 4230000 | 3785412 | 3766754.85 | 7552166.85
Assuit PP (CP-118) | 519 |  | Assuit PP (CP-118) | 3978934.7 | 3511409.88 | 626682.21 | 4138092.09
Canal Regional Control Center | Inv.4 Rcc | 4 | Canal Regional Control Center4 | 25537107.18 | 17006497.75 | 5362792.51 | 22369290.26
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 26 | 26 | Benban 500 K.V / 100 K.M26 | 43640.91 | 33646.9 | 4582.3 | 38229.2
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .19 | 19 | Benban 3/ Toshka 2 LOT 419 | 104127.38 | 81555.58 | 10933.38 | 92488.96
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .3 | 3 | Benban 3/ Toshka 2 LOT 43 | 34347471.75 | 26481907.97 | 3606484.53 | 30088392.5
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .21 | 21 | Benban 3/ Toshka 2 LOT 421 | 7997574.53 | 6931070.92 | 202367.91 | 7133438.83
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .12 | 12 | Benban 3/ Toshka 2 LOT 412 | 860775.16 | 698030.65 | 90381.39 | 788412.04
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $3 | 3 | Benban 3/ Toshka 2 LOT 43 | 203309.37 | 170779.88 | 21347.48 | 192127.36
Ismailiya East Substation | ISE-CW-EGP-20 | 20 | Ismailiya East Substation20 | 1803066 | 911386.14 | 270459.9 | 1181846.04
MAYSAN 400/132kV SS | 288 |  | MAYSAN 400/132kV SS | 860778.34 | 860778.34 | 0 | 860778.34
Sewage Treatment Plant | IPC#1`2`3 | 1 | Sewage Treatment Plant1 | 2051966 | 1260000 | 0 | 1260000
Ismailiya East Substation | ISE-SD-EURO-05 | 5 | Ismailiya East Substation5 | 5894418.46 | 5246032.43 | 0 | 5246032.43
Tamey El-amdeed Substation | TAM-CW-EURO-08 | 8 | Tamey El-amdeed Substation8 | 545955.53 | 273600.09 | 81893.33 | 355493.42
Marsa Matrouh 500KV | Inv.52 Borg Alarab | 52 | Marsa Matrouh 500KV52 | 12906921.58 | 9241358.14 | 1355226.77 | 10596584.91
Marsa Matrouh 500KV | Inv.47 Borg Alarab | 47 | Marsa Matrouh 500KV47 | 7470695.02 | 6525652.35 | 784422.98 | 7310075.33
Safeer Square Bridge | SAFIER BRIDGE-IPC01 | 1 | Safeer Square Bridge1 | 87966715.14 | 8754247 | 27885620.8 | 76674867.8
4 SS - Technical Service | 305 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
AWEER POWER STATION 'H' Phase | 10427 |  | AWEER POWER STATION 'H' Phase | 783780.49 | 822969.5145 | 0 | 822969.5145
El Mostakbal City Project | Inv. 7 Mostakbal | 7 | El Mostakbal City Project7 | 29176277.5 | 24216310.32 | 6127018.28 | 30343328.6
CFC Podium 2 | CFC-IPC16 | 16 | CFC Podium 216 | 29185169.72 | 22871121.156 | 4275462.48 | 27146583.636
Lekela 250MW Wind Farm | SiemensLEKELA IPC012 | 12 | Lekela 250MW Wind Farm12 | 24308181.24 | 21477147.752 | 3853754.81 | 25330902.562
Lekela 250MW Wind Farm | LEKELA-IPC05 | 5 | Lekela 250MW Wind Farm5 | 8446374.72 | 7094954.766 | 1689274.94 | 8784229.706
Lekela 250MW Wind Farm | LEKELA-IPC04 | 4 | Lekela 250MW Wind Farm4 | 777289.9 | 652923.515 | 155457.98 | 808381.495
ESU Ph2-Enabling & Struc | S.U.PHASE2-IPC03 | 3 | ESU Ph2-Enabling & Struc3 | 22372123.52 | 17089175.4 | 7047218.91 | 24136394.31
Toshka GIS 500 kV | Toshka Sub Inv. 03 $ | 3 | Toshka GIS 500 kV3 | 54782.86 | 36869.3 | 14380.5 | 51249.8
Toshka GIS 500 kV | Toshka Sub Inv. 11 $ | 11 | Toshka GIS 500 kV11 | 1792347.49 | 1222707.15 | 470491.22 | 1693198.37
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC04 | 4 | EMAAR-Pkg#162/163- Marassi4 | 7314175.65 | 6393536.5925 | 818166.39 | 7211702.9825
Asec Spare-Parts | Inv 4 EUR Asec Spare | 4 | Asec Spare-Parts4 | 15668.8 | 3352.4 | 5086.53 | 8438.93
Akhmem Assiut | Re. Soc inv 22 To 25 | 22 | Akhmem Assiut22 | 1630 | 1630 | 0 | 1630
marassi inland marina | IPC#4 | 4 | marassi inland marina4 | 3402063.63 | 2947834.13 | 0 | 3117937.31
SHATRA 400/132kV SS | 304 |  | SHATRA 400/132kV SS | 1836678.75 | 1836678.75 | 0 | 1836678.75
MAYSAN 400/132kV SS | 301 |  | MAYSAN 400/132kV SS | 2391478.77 | 2391478.77 | 0 | 2391478.77
Beni Suef Add-on Sales | 2003210006 |  | Beni Suef Add-on Sales | 250125 | 277638.75 | 0 | 277638.75
Sodic East | 10008 |  | Sodic East | 311151.96 | 166775.6 | 108903.18 | 275678.78
Dubai Port | 10013 |  | Dubai Port | 41020.52 | 36385.19 | 0 | 36385.19
Ministries Building ROOF | 10004 |  | Ministries Building ROOF | 65124.05 | 61216.61 | 0 | 61216.61
Multi Sport Hall | 10034 |  | Multi Sport Hall | 143453.4 | 127673.53 | 0 | 127673.53
Sodic East | 10038 |  | Sodic East | 108381 | 93918.94 | 0 | 93918.94
Mivida | 10040 |  | Mivida | 100012.5 | 12.5 | 100000 | 100012.5
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC09 | 9 | EMAAR- Pkg 140-ITP-Mivida9 | 4233335.77 | 6237430.1585 | 585903.85 | 6823334.0085
Canal Sugar OHTL | Inv.04 Sugar OHTL | 4 | Canal Sugar OHTL4 | 391185.52 | 309036.56 | 58677.83 | 367714.39
Canal Sugar S/s | Inv 4 Sugar S/s | 4 | Canal Sugar S/s4 | 8119668.06 | 6414537.76 | 1217950.21 | 7632487.97
Ismailiya East Substation | ISE-SD-EGP-03 | 3 | Ismailiya East Substation3 | 583200 | 519048 | 0 | 519048
HyperOne Zayed Extension | HYPERONE-IPC06 | 6 | HyperOne Zayed Extension6 | 10976158 | 8598918.82 | 2744039.5 | 12322958.32
Oasis Buildings- New Capital | Inv(3)250120 | 3 | Oasis Buildings- New Capital3 | 60630 | 57586.69 | 0 | 57586.69
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC018 | 18 | EMAAR-Pkg#162/163- Marassi18 | 3301294.96 | 3248092.448 | 888092.46 | 4136184.908
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC015 | 15 | EMAAR-Pkg#162/163- Marassi15 | 7388288.7 | 4317541.565 | 1171459.67 | 5489001.235
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC07 | 7 | EMAAR-Pkg#162/163- Marassi7 | 4420616.83 | 4922193.4962 | 1444568 | 6366761.4962
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC06 | 6 | EMAAR-Pkg#162/163- Marassi6 | 8631951.71 | 6532694.7794 | 1807627.83 | 8340322.6094
Mountain View | 10025 |  | Mountain View | 101817.9 | 20709 | 75000 | 95709
Albatross | 10030 |  | Albatross | 132750 | 0 | 100000 | 100000
Marsa Allam | 10031 |  | Marsa Allam | 57351.53 | 24807.06 | 40000 | 64807.06
Sodic East | 10005 |  | Sodic East | 56863.2 | 30430.55 | 19902.12 | 50332.67
Sodic East | 10009 |  | Sodic East | 79280.4 | 40006.58 | 27748.14 | 67754.72
Manshiet Nasser Substation | 514 |  | Manshiet Nasser Substation | 820387 | 541390.18 | 0 | 541390.18
Marsa Matrouh 500KV | Inv.59 Borg Alarab | 59 | Marsa Matrouh 500KV59 | 3459192.38 | 3021609.25 | 363215.2 | 3384824.45
Marsa Matrouh 500KV | Inv.56 Borg Alarab | 56 | Marsa Matrouh 500KV56 | 15166868.57 | 13248261.5 | 1592521.2 | 14840782.7
Marsa Matrouh 500KV | Inv.55 Borg Alarab | 55 | Marsa Matrouh 500KV55 | 6918384.76 | 6043215.55 | 726430.4 | 6769645.95
Ministries Buildings | MIN LAND ESCAPE-IPC1 | 1 | Ministries Buildings1 | 2983013.65 | 1782335 | 24480 | 1806815
Canal Regional Control Center | Inv.6 Rcc | 6 | Canal Regional Control Center6 | 10397764.96 | 5884648.05 | 2183530.64 | 8068178.69
SHATRA 400/132kV SS | 330 |  | SHATRA 400/132kV SS | 774447.07 | 774447.07 | 0 | 774447.07
SHATRA 400/132kV SS | 328 |  | SHATRA 400/132kV SS | 1133556.15 | 1133556.15 | 0 | 1133556.15
MOTHANA 400/132kV SS | 313 |  | MOTHANA 400/132kV SS | 138212.12 | 138212.12 | 0 | 138212.12
SHATRA 400/132kV SS | 331 |  | SHATRA 400/132kV SS | 357859.01 | 357859.01 | 0 | 357859.01
MAYSAN 400/132kV SS | 311 |  | MAYSAN 400/132kV SS | 58865.41 | 58865.41 | 0 | 58865.41
Cameron EDC | 023/2020 FCV |  | Cameron EDC | 69576437.45 | 20872931 | 0 | 34788218.49
Latin Compound - New Alamin | INV(9)150420 | 9 | Latin Compound - New Alamin9 | 392840 | 288562.49 | 37168.24 | 325730.73
Ministry Building EPOXY | 10033 |  | Ministry Building EPOXY | 10605.04 | 9968.74 | 0 | 9968.74
Beni Seuf - 358 | Inv. 1 Oewon Mousa | 1 | Beni Seuf - 3581 | 7234840.58 | 5340848.3 | 1242856.65 | 6583704.95
Marsa Matrouh 500KV | Inv.74 Borg Alarab | 74 | Marsa Matrouh 500KV74 | 1233333.33 | 1012572.65 | 0 | 1012572.65
HAC CCC JV | IPC#13 | 13 | HAC CCC JV13 | 949947.45 | 1150115.83 | 0 | 592291.964
Assuit PP (CP-118) | 2002210016 |  | Assuit PP (CP-118) | 2511298.31 | 2216220.76 | 395529.48 | 2611750.24
Sodic East | 10006 |  | Sodic East | 68304 | 33405.25 | 23906.4 | 57311.65
Angola Emergency fast-track | ANG-Cam-Inv 4 - Ints | 4 | Angola Emergency fast-track4 | 7623762.34 | 5866370.95 | 0 | 5866370.95
Elhegaz | FPC |  | Elhegaz | 438410 | -77808.5 | 0 | -77808.5
AWEER POWER STATION 'H' Phase | LOC/006 Rev0 |  | AWEER POWER STATION 'H' Phase | 1097950 | 963756.21 | 121994.346 | 1085750.556
Abu Qir PP (CP-117) | Adjust rec.qir 117 |  | Abu Qir PP (CP-117) | 196748.76 | 196748.76 | 0 | 196748.76
Abu Qir PP (CP-117) | Adjust 1907210013- |  | Abu Qir PP (CP-117) | 17136.36 | 17136.36 | 0 | 17136.36
Ghana | 43/P/10/ER/2017/USD |  | Ghana | 655736.54 | 655736.54 | 0 | 655736.54
LAYAN Substation | 10967 |  | LAYAN Substation | 132794.44 | 224422.62 | 0 | 112211.31
LAYAN Substation | 10886 |  | LAYAN Substation | 462317.3055 | 1562632.52 | 0 | 390658.13
LAYAN Substation | 10364 |  | LAYAN Substation | 298927.44 | 248109.77 | 0 | 248109.77
LAYAN Substation | 10222 |  | LAYAN Substation | 5123619.66 | 4252604.32 | 0 | 4252604.32
LAYAN Substation | 10141 |  | LAYAN Substation | 385736.25 | 651894.26 | 0 | 325947.13
Mahmoudia Additional Scope | 2003210003 |  | Mahmoudia Additional Scope | 8250000 | 8250000 | 0 | 8250000
Port Saad Industiral zone | IPC#6 | 6 | Port Saad Industiral zone6 | 8614362 | 8295630.61 | 0 | 8295630.61
Club House-Sodic Wesset | 10074 |  | Club House-Sodic Wesset | 117700 | 116523 | 0 | 116523
Oasis Buildings- New Capital | Inv(5)240320 | 5 | Oasis Buildings- New Capital5 | 620400 | 581146.2 | 0 | 581146.2
Ain-Sokhna PP (CP-117) | 2005210006 |  | Ain-Sokhna PP (CP-117) | 23.93 | 23.93 | 0 | 23.93
SHATRA 400/132kV SS | 347 |  | SHATRA 400/132kV SS | 2964376.28 | 2964376.28 | 0 | 2964376.28
NUCA R05 - Z02 | R5 - IPC16 | 16 | NUCA R05 - Z0216 | 41433707.7 | 26497123.5 | 3364474.8 | 29861598.3
Miscellaneous Projects | 2004210006 |  | Miscellaneous Projects | 140220 | 138990 | 0 | 158620.8
Minis Building(Polyurethane) | 10042 |  | Minis Building(Polyurethane) | 377685.68 | 336140.26 | 0 | 336140.26
Miscellaneous Projects | 2006210007 |  | Miscellaneous Projects | 8384.62 | 9558.4668 | 0 | 9558.4668
Minis Building(Polyurethane) | 10194 |  | Minis Building(Polyurethane) | 331477.68 | 295015.14 | 0 | 295015.14
Minis Building(Polyurethane) | 10173 |  | Minis Building(Polyurethane) | 81421.47 | 72465.12 | 0 | 72465.12
DoubleTree Mangroovy ElGouna | MANGROVY-IPC06 | 6 | DoubleTree Mangroovy ElGouna6 | 6170230.65 | 8251289.2525 | 1619685.21 | 9870974.4625
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC05 | 5 | EMAAR-Pkg#162/163- Marassi5 | 8006098.57 | 6067879.3275 | 796526.84 | 6864406.1675
W Dam PP Phase II (CP-117) | 538 |  | W Dam PP Phase II (CP-117) | 1136393.79 | 1290667.6 | 0 | 1290667.6
MOTHANA 400/132kV SS | 351 |  | MOTHANA 400/132kV SS | 1403301.15 | 1403301.15 | 0 | 1403301.15
Marsa Matrouh 500KV | Inv.31 Borg Alarab | 31 | Marsa Matrouh 500KV31 | 1466699.73 | 1281162.51 | 154003.47 | 1435165.98
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 01 | 1 | Suez Gulf/S4 - 500KV OHTL1 | 43356299.65 | 35513135.71 | 4552411.46 | 40065547.17
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 04 | 4 | Suez Gulf/S4 - 500KV OHTL4 | 115225.4 | 96789.33 | 12098.67 | 108888
East Owainat 5 LOTS | East Owainat Inv. 01 | 1 | East Owainat 5 LOTS1 | 38222459.48 | 15652082.11 | 20066791.22 | 35718873.33
Barwa 2x60/22 KV S/S | Inv. Barwa 38 |  | Barwa 2x60/22 KV S/S | 2683543.96 | 1884957.98 | 402531.59 | 2287489.57
DPW Onshore Port & Terminal | DP WORLD - IPC15 | 15 | DPW Onshore Port & Terminal15 | 110730132.45 | 81940298.01 | 16609519.87 | 98549817.88
SHATRA 400/132kV SS | 357 |  | SHATRA 400/132kV SS | 1635918.76 | 1635918.76 | 0 | 1635918.76
AWEER POWER STATION 'H' Phase | Imp-041 Rev0 | 41 | AWEER POWER STATION 'H' Phase41 | 3691844.34 | 3650823.84 | 0 | 3650823.84
AWEER POWER STATION 'H' Phase | Con-011 | 11 | AWEER POWER STATION 'H' Phase11 | 958273.98 | 947626.49 | 0 | 947626.49
Abbas El Akkad Bridge | inv(1)300620 | 1 | Abbas El Akkad Bridge1 | 800030 | 40001.5 | 0 | 748428.06
Canal Sugar S/s | Inv 2 $ Sugar S/s | 2 | Canal Sugar S/s2 | 1151235.65 | 909476.15 | 172685.35 | 1082161.5
NUCA R05 - Z02 | R5-FINSHING-IPC01 | 1 | NUCA R05 - Z021 | 4034106.35 | 3635379.6 | 0 | 3635379.6
4 SS - Technical Service | 363 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
CFC Podium 2 | CFC- IPC07 | 7 | CFC Podium 27 | 17879880.11 | 19510039.82 | 3717893.63 | 23227933.45
MAYSAN 400/132kV SS | 359 |  | MAYSAN 400/132kV SS | 844928.25 | 844928.25 | 0 | 844928.25
MOTHANA 400/132kV SS | 360 |  | MOTHANA 400/132kV SS | 1427199.69 | 1427199.69 | 0 | 1427199.69
Banha PP (CP-118) | 200067 |  | Banha PP (CP-118) | 255420 | 577249.2 | 0 | 288624.6
AWEER POWER STATION 'H' Phase | IMP-053 | 53 | AWEER POWER STATION 'H' Phase53 | 188611.15 | 181276.28 | 0 | 181276.28
AWEER POWER STATION 'H' Phase | Loc-007 Rev0 | 7 | AWEER POWER STATION 'H' Phase7 | 389235.05 | 384829.22 | 0 | 384829.22
ESU Ph2-Enabling & Struc | ESU2-ARCH&MEP-IPC05 | 5 | ESU Ph2-Enabling & Struc5 | 53567992 | 64006362.74 | 16799844.2 | 80806206.94
Minis Building(Polyurethane) | IPC_12_rowad_poly | 12 | Minis Building(Polyurethane)12 | 364117.38 | 322084.47 | 0 | 322084.47
Tanzania hydropower Project | 3 |  | Tanzania hydropower Project | 1202958.11 | 946870.06 | 0 | 946870.06
EDNC Retail & Offices Civil | SOREAL-IPC14 | 14 | EDNC Retail & Offices Civil14 | 24418089.97 | 17859899.4785 | 2751415.45 | 20611314.9285
AWEER POWER STATION 'H' Phase | IMP-048 | 48 | AWEER POWER STATION 'H' Phase48 | 3161126.03 | 3126002.41 | 0 | 3126002.41
AWEER POWER STATION 'H' Phase | Con-014 | 14 | AWEER POWER STATION 'H' Phase14 | 958273.98 | 947626.49 | 0 | 947626.49
Canal Sugar S/s | Inv 8 Sugar S/s | 8 | Canal Sugar S/s8 | 7381102.06 | 5831070.62 | 1107165.31 | 6938235.93
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .5 | 5 | Benban 3/ Toshka 2 LOT 45 | 8982538.39 | 6925535.95 | 943166.53 | 7868702.48
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .11 | 11 | Benban 3/ Toshka 2 LOT 411 | 3523015.64 | 2892398.98 | 369916.64 | 3262315.62
Ghana | 50/P/10/ER/2017/USD |  | Ghana | 588194.61 | 588207.78 | 0 | 588207.78
Racecores 3092-16 132KV C | 11542 |  | Racecores 3092-16 132KV C | 347388.21 | 1441661.1 | 0 | 288332.22
Racecores 3092-16 132KV C | 11457 |  | Racecores 3092-16 132KV C | 419038.5388 | 1416350.2628 | 0 | 354087.5657
33KV Canal Farm Grid | Inv. 07 Farm | 7 | 33KV Canal Farm Grid7 | 1120160.06 | 884926.44 | 168024.01 | 1052950.45
NUCA R05 - Z02 | R05(2) ipc46 | 46 | NUCA R05 - Z0246 | 28054197.43 | 22413765.21 | 2996461.96 | 25410227.17
NUCA R05 - Z02 | R05 Zone 2 IPC019 | 19 | NUCA R05 - Z0219 | 40013957.35 | 36068788.78 | 4689061.1 | 40757849.88
Canal Regional Control Center | Inv.7 Rcc | 7 | Canal Regional Control Center7 | 6051819.83 | 3425301.4 | 1270882.16 | 4696183.56
CFC Podium 2 | CFC-IPC09 | 9 | CFC Podium 29 | 29660400.78 | 24499896.0885 | 4666027.79 | 29165923.8785
Baron Fence | ELBARON-IPC01 | 1 | Baron Fence1 | 9980627.24 | 5993105 | 2554967.35 | 8548072.35
Azab Tex Factory | inv ( 1 ) 1-2-2021 | 1 | Azab Tex Factory1 | 620350 | 620350 | 0 | 620350
Zambia Project | SCD1x/007 |  | Zambia Project | 363025.44 | 326685.27 | 0 | 326685.27
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 3 | 3 | Marsa Alam/ Bernes LOT2 OHTL3 | 73253186.66 | 60140851.04 | 7691585.5 | 67832436.54
Taval Sarai 52 | IPC-15-Saray | 15 | Taval Sarai 5215 | 505176.7 | 381064.02 | 0 | 381064.02
Taval Sarai 52 | IPC_2_Gama_Saraya | 2 | Taval Sarai 522 | 125198.7 | 98529.87 | 0 | 98529.87
Manshiet Nasser Substation | 2008210008 |  | Manshiet Nasser Substation | 4538.92 | 4061.14 | 716.67 | 4777.81
Manshiet Nasser Substation | Adjust 180177- |  | Manshiet Nasser Substation | 919 | 919 | 0 | 919
Marsa Matrouh 500KV | Inv.24Usd borg alarb | 24 | Marsa Matrouh 500KV24 | 298146.74 | 214744.02 | 0 | 214744.02
Ministries A17-A18 | IPC_7_GAMA_A17 | 7 | Ministries A17-A187 | 544424 | 460854.92 | 0 | 460854.92
Minis Building(Polyurethane) | IPC_15_Rowad_Poly | 15 | Minis Building(Polyurethane)15 | 19944.02 | 17210.18 | 0 | 17210.18
NUCA R05 - Z02 | R5 FINSHING-IPC05 | 5 | NUCA R05 - Z025 | 14871150.8 | 11695928.75 | 1576171.85 | 13272100.6
Royal City | ROYAL ZONE-IPC12 | 12 | Royal City12 | 8940988.58 | 6296298.659 | 1702855.61 | 7999154.269
Cairo-Alex Railway | Cairo-alex ipc 38 | 38 | Cairo-Alex Railway38 | 11333077.14 | 7840424.02 | 1189973.1 | 9030397.12
Cairo-Alex Railway | Cairo-alex ipc 37 | 37 | Cairo-Alex Railway37 | 5830965.71 | 4049206.83 | 612251.4 | 4661458.23
Cairo-Alex Railway | cairo-alex ipc 29 | 29 | Cairo-Alex Railway29 | 56978233.6 | 4175868.4 | 40982714.53 | 45158582.93
Cairo-Alex Railway | CAIRO-ALEX IPC24 | 24 | Cairo-Alex Railway24 | 36781433.5 | 25544306.65 | 3862050.52 | 29406357.17
Cairo-Alex Railway | Cairo-Alex IPC011 | 11 | Cairo-Alex Railway11 | 22566567.8 | 15058027.95 | 2369489.65 | 17427517.6
Cairo-Alex Railway | Cairo-Alex IPC03 | 3 | Cairo-Alex Railway3 | 5582157.64 | 3953758.56 | 558215.76 | 4511974.32
Racecores 3092-17 132KV E | 11455 |  | Racecores 3092-17 132KV E | 257643.77 | 213844.3285 | 0 | 213844.3285
Racecores 3092-17 132KV E | 10663 |  | Racecores 3092-17 132KV E | 2768749.5 | 4596124.18 | 0 | 2298062.09
SHAT Al ARAB 400/132kV SS | 366 |  | SHAT Al ARAB 400/132kV SS | 1811715.34 | 1811715.34 | 0 | 1811715.34
MOTHANA 400/132kV SS | 382 |  | MOTHANA 400/132kV SS | 16614.19 | 16614.19 | 0 | 16614.19
Lekela 250MW Wind Farm | LEKELA-IPC03 | 3 | Lekela 250MW Wind Farm3 | 2093986.78 | 1758948.889 | 418797.36 | 2177746.249
Lekela 250MW Wind Farm | LEKELA-IPC02 | 2 | Lekela 250MW Wind Farm2 | 1271271.54 | 1067868.087 | 254254.31 | 1322122.397
Masr ELgedeeda | IPC#1 | 1 | Masr ELgedeeda1 | 1396750 | 1338784.5 | 0 | 1338784.5
NUCA R05 - Z02 | R5 - IPC21 | 21 | NUCA R05 - Z0221 | 36906800.17 | 23661440.9 | 3033508.46 | 26694949.36
DPW Onshore Port & Terminal | DP WORLD -IPC20 | 20 | DPW Onshore Port & Terminal20 | 42996289.46 | 31817254.2 | 6449443.42 | 38266697.62
LRT - El Shorouk Bridge | IPC#6 | 6 | LRT - El Shorouk Bridge6 | 1069480 | 789999.57 | 0 | 789999.57
Ministries Buildings | MIN-ALLOCATION-IPC02 | 2 | Ministries Buildings2 | 11312307.26 | 3367547 | 6841403.85 | 10208950.85
ORA ZED - Ph 01B - Pkgs A&D | Ora Ph 1 ipc 37 | 37 | ORA ZED - Ph 01B - Pkgs A&D37 | 29089779.62 | 23554316.1 | 3046679.76 | 26600995.86
ORA ZED - Ph 01B - Pkgs A&D | ORA ph 1 ipc (28) | 28 | ORA ZED - Ph 01B - Pkgs A&D28 | 22847215.74 | 8905384.6977 | 12391645.05 | 21297029.7477
ORA ZED - Ph 01B - Pkgs A&D | Ora Zed Ph1 IPC05 | 5 | ORA ZED - Ph 01B - Pkgs A&D5 | 41442903.7 | 33310478.505 | 3965163.77 | 37275642.275
EMAAR-PKG#62-UPTOWN | 18100052 |  | EMAAR-PKG#62-UPTOWN | 2727129.53 | 1778643.79 | 1001134.12 | 2779777.91
El Mostakbal City Project | Inv. 10 Mostakbal | 10 | El Mostakbal City Project10 | 12115411.8 | 10055791.79 | 2544236.48 | 12600028.27
Mohamed Ali Palace | 10273 |  | Mohamed Ali Palace | 190809 | 160279.56 | 0 | 160279.56
LAYAN Substation | 10204 |  | LAYAN Substation | 164273.805 | 272694.52 | 0 | 136347.26
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .9 | 9 | Benban 3/ Toshka 2 LOT 49 | 100778929.4 | 82739503.4 | 10581787.59 | 93321290.99
SHAT Al ARAB 400/132kV SS | 379 |  | SHAT Al ARAB 400/132kV SS | 460337.36 | 460337.36 | 0 | 460337.36
SHATRA 400/132kV SS | 380 |  | SHATRA 400/132kV SS | 306893.5 | 306893.5 | 0 | 306893.5
MAYSAN 400/132kV SS | 377 |  | MAYSAN 400/132kV SS | 1210817.35 | 1210817.35 | 0 | 1210817.35
Ministries Buildings | MIN-ALLOCATION-IPC5 | 5 | Ministries Buildings5 | 17481409.92 | 5853780 | 8873907.5 | 14727687.5
CFC Podium 2 | CFC-IPC12 | 12 | CFC Podium 212 | 34817130.72 | 29691195.016 | 4416272.34 | 34107467.356
Koning Food V2 - LP-08-20 | 6 |  | Koning Food V2 - LP-08-20 | 2642.98 | 3013 | 0 | 3013
ESU Ph2-Enabling & Struc | E.U2-ENABLING-10 | 10 | ESU Ph2-Enabling & Struc10 | 5068271.52 | 10675697.426 | 0 | 10675697.426
EMAAR-PKG117- MARASSI | PKG#117-IPC FINAL |  | EMAAR-PKG117- MARASSI | 1638134.38 | 2354224.5932 | 0 | 2354224.5932
Toshka GIS 500 kV | Toshka Sub Inv. 15 $ | 15 | Toshka GIS 500 kV15 | 46601.9 | 26327.6 | 12233 | 38560.6
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .13 | 13 | Benban 3/ Toshka 2 LOT 413 | 116650.71 | 91407.17 | 12248.33 | 103655.5
MAYSAN 400/132kV SS | 383 |  | MAYSAN 400/132kV SS | 5337437.44 | 5337437.44 | 0 | 5337437.44
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 03 | 3 | Toshka-04 GIS Substation3 | 101550754.44 | 84489796.66 | 10662829.22 | 95152625.88
Toshka GIS 500 kV | Toshka Sub Inv. 19 $ | 19 | Toshka GIS 500 kV19 | 3133454.29 | 1973556.2 | 822531.75 | 2796087.95
R5 | inv ( 13 ) | 13 | R513 | 1482000 | 297408.51 | 0 | 1368455.9
Miscellaneous Projects | 2012210001 |  | Miscellaneous Projects | 132158.8 | 150661.032 | 0 | 150661.032
Mivida | IPC_3_Mivida | 3 | Mivida3 | 212130 | 210008.7 | 0 | 210008.7
Taval Sarai 52 | IPC_3_Gama_Saray | 3 | Taval Sarai 523 | 158874.5 | 114823.68 | 0 | 114823.68
Canal Sugar S/s | Inv 3 Sugar S/s | 3 | Canal Sugar S/s3 | 4812648.74 | 3801992.51 | 721897.31 | 4523889.82
ElMarg | IPC#1 & Final | 1 | ElMarg1 | 1093100 | 1000000 | 0 | 1082169
Bani Suef Old Substation | BNI SUEF OLD-IPC FIN |  | Bani Suef Old Substation | 2627278.35 | 3467007.05 | 0 | 3467007.05
ESU Ph2-Enabling & Struc | E.US2-MEP-IPC11 | 11 | ESU Ph2-Enabling & Struc11 | 24045616.1 | 13851401.63 | 5913881.4 | 19765283.03
Kattameya Creeks | Katamya ipc (31) | 31 | Kattameya Creeks31 | 49290024.52 | 37106226 | 14155399.33 | 51261625.33
Kattameya Creeks | katameya-IPC23 | 23 | Kattameya Creeks23 | 30664402.09 | 29834733.0645 | 2056245.11 | 31890978.1745
Kattameya Creeks | Katameya IPC16 | 16 | Kattameya Creeks16 | 47021445.38 | 44583744.0045 | 4305908.79 | 48889652.7945
Kattameya Creeks | katmeyacreeks ipc12 | 12 | Kattameya Creeks12 | 39536093.61 | 36461301.5305 | 4638525.82 | 41099827.3505
Kattameya Creeks | KatameyaCreks IPC010 | 10 | Kattameya Creeks10 | 38757548.53 | 36159161.9365 | 4136038.53 | 40295200.4665
El Katameya Mall | inv ( 12 ) 30-9-2020 | 12 | El Katameya Mall12 | 85400 | 51371.74 | 0 | 51371.74
Latin Compound - New Alamin | inv (27) AL15-2-2021 | 27 | Latin Compound - New Alamin27 | 288078 | 244722.16 | 0 | 244722.16
Ismailiya East Substation | ISE-SD-EGP-02 | 2 | Ismailiya East Substation2 | 191389.5 | 170338 | 0 | 170338
Ismailiya East Substation | ISE-CW-EGP-25 | 25 | Ismailiya East Substation25 | 294276 | 261905.64 | 0 | 261905.64
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.01 | 1 | Toshka 2/Owinat East LOT2 OHTL1 | 33724388.22 | 30081763.99 | 3541060.76 | 33622824.75
Beni Seuf - 358 | Re Soc Inv.2 Temmay | 2 | Beni Seuf - 3582 | 580808 | 580808 | 0 | 580808
Royal City | ROYALZONE2-IPC13 | 13 | Royal City13 | 3598739.18 | 2137568.4452 | 579614.89 | 2717183.3352
DoubleTree Mangroovy ElGouna | MANGROVY CLAIM-IPC12 | 12 | DoubleTree Mangroovy ElGouna12 | 1904761.9 | 1942857.135 | 0 | 1942857.135
Shorouk Bridge-LRT | SHOROUK DRIDGE-IPC02 | 2 | Shorouk Bridge-LRT2 | 13091823.2 | 3040310.99 | 8000000 | 11040310.99
Shorouk Bridge-LRT | SHOROUK BRIDGE-IPC01 | 1 | Shorouk Bridge-LRT1 | 2491848.1 | 1959689.01 | 0 | 1959689.01
El-Moneeb Bridge | Final PC |  | El-Moneeb Bridge | 298500 | 254165 | 0 | 254165
Kayan 3 New Cairo Capital City | KAYAN MEP1-IPC06 | 6 | Kayan 3 New Cairo Capital City6 | 46122875 | 20582125 | 20582136 | 41164261
Sodic East | IPC_20_Rowad_Seast | 20 | Sodic East20 | 273153.72 | 181637.59 | 0 | 181637.59
Coastal road Bridge Extension | IPC#5 - Gharably | 5 | Coastal road Bridge Extension5 | 1553202 | 1495733.53 | 0 | 1495733.53
Coastal road Bridge Extension | IPC#1` - Gharably | 1 | Coastal road Bridge Extension1 | 1584660 | 1526027.58 | 0 | 1526027.58
El Boghaz Brigde | IPC#26 | 26 | El Boghaz Brigde26 | 564857.5 | 383976.81 | 0 | 383976.81
Royal City | ROYAL CITY2-IPC16 | 16 | Royal City16 | 1581960.97 | 853478.4785 | 0 | 853478.4785
Miscellaneous Projects | 2007210012 |  | Miscellaneous Projects | 34725 | 39239.25 | 0 | 39239.25
Beni Seuf - 358 | Inv. 10 Oewon Mousa | 10 | Beni Seuf - 35810 | 10543429.34 | 7151842.22 | 1810072.7 | 8961914.92
LRT | IPC#1 | 1 | LRT1 | 778080 | 552435.92 | 0 | 552435.92
ORA Zed Park LOCK&LOAD | ORA L&L-IPC03 | 3 | ORA Zed Park LOCK&LOAD3 | 145168.11 | 128110.8555 | 0 | 128110.8555
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED-IPC01 | 1 | ORA ZED - Ph 01B - Pkgs A&D1 | 2407390.57 | 10377230.16 | 1179886.73 | 11557116.89
Badr | Inv. 24 Badr | 24 | Badr24 | 9633352.5 | 6670347.3 | 1445002.9 | 8115350.2
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC20 | 20 | EMAAR- Pkg 140-ITP-Mivida20 | 5957491.28 | 6060664.08 | 605845.36 | 6666509.44
Manshiet Nasser Substation | 2102210002 |  | Manshiet Nasser Substation | 2889.29 | 2285.95 | 467.65 | 2753.6
Manshiet Nasser Substation | 2102210001 |  | Manshiet Nasser Substation | 115620.9524 | 82437.25 | 18210.3 | 100647.55
Development of Mahmudiyah axis | FPC closing |  | Development of Mahmudiyah axis | 26550 | 26550 | 0 | 26550
Mivida | IPC_6_Mivida | 6 | Mivida6 | 168310 | 102218 | 0 | 102218
EGAT Pelletizing Plant | elco egat ipc09 | 9 | EGAT Pelletizing Plant9 | 15797419.96 | 14888446.998 | 1540869.76 | 16429316.758
Minis Building(Polyurethane) | IPC_18_Rowad_Poly | 18 | Minis Building(Polyurethane)18 | 36617.1 | 165.96 | 0 | 32589.21
Miscellaneous Projects | 2012210028 |  | Miscellaneous Projects | 141787.4 | 161637.636 | 0 | 161637.636
IKEA Extension MoA | IKEA-IPC13 | 13 | IKEA Extension MoA13 | 3981119.65 | 4064871.9 | 0 | 4064871.9
Royal City | ROYAL CITY-IPC38 | 38 | Royal City38 | 4991557.65 | 3951088.5025 | 0 | 3951088.5025
IKEA Extension MoA | IKEA2-IPC03 | 3 | IKEA Extension MoA3 | 859270.7 | 823216.605 | 0 | 823216.605
Taval Sarai 52 | IPC_8_Saray | 8 | Taval Sarai 528 | 1550526.2 | 1284301.11 | 0 | 1284301.11
Sodic East | IPC_19_Rowad_S_east | 19 | Sodic East19 | 145284.8 | 92212.984 | 0 | 92212.984
EDNC Retail & Offices Civil | SOREAL-IPC23 | 23 | EDNC Retail & Offices Civil23 | 23832998.72 | 15672746.626 | 1461990.25 | 17134736.876
Railway Bridge - Assuit | IPC#1 Assuit | 1 | Railway Bridge - Assuit1 | 995880 | 679771.39 | 0 | 679771.39
158E/2019 33kv Project | 10382 |  | 158E/2019 33kv Project | 106200 | 95580 | 0 | 95580
BridgeNasr Rd w Abbas El-Akkad | ABASELAQAD-IPC1FINAL | 1 | BridgeNasr Rd w Abbas El-Akkad1 | 106237173.33 | 6904265 | 20000000 | 88369955
El Ameed 220 KV | ELAmeed Inv. 01 Fina | 1 | El Ameed 220 KV1 | 752380.95 | 690658.35 | 0 | 690658.35
Miscellaneous Projects | 2012210026 |  | Miscellaneous Projects | 10500 | 11970 | 0 | 11970
New Babil 400/132KV Substation | 2103210005 |  | New Babil 400/132KV Substation | 65785.41 | 65785.41 | 0 | 65785.41
MDF Factory | MDF - IPC 14 | 14 | MDF Factory14 | 12281779.55 | 11569223.8875 | 3542110.92 | 15111334.8075
MDF Factory | MDF IPC01 | 1 | MDF Factory1 | 2418808.57 | 6231879 | 634937.25 | 6866816.25
Marassi Inner Marina - PKG178 | IPC#1 .PKG#178 | 1 | Marassi Inner Marina - PKG1781 | 2247700 | 1967215.5 | 0 | 1967215.5
CFC Podium 2 | CFC-IPC17 | 17 | CFC Podium 217 | 23196101.95 | 15047803.35 | 2853816.14 | 17901619.49
Masr ELgedeeda | FPC |  | Masr ELgedeeda | 324187.5 | 310733.68 | 0 | 310733.68
4 SS - Technical Service | 410 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Al Montaza Hotels - Alexandria | inv ( 2 ) montazha | 2 | Al Montaza Hotels - Alexandria2 | 5399933 | 5129936.35 | 0 | 5129936.35
El Katameya Mall | INV (17 ) Final Kat | 17 | El Katameya Mall17 | 203840 | 151259.88 | 0 | 151259.88
Canal Sugar S/s | Inv 11 Sugar S/s | 11 | Canal Sugar S/s11 | 600377.29 | 458087.87 | 90056.59 | 548144.46
Canal Sugar 33KV OHTL | Inv. 6 Sugar 33 OHTL | 6 | Canal Sugar 33KV OHTL6 | 3384379.83 | 3089938.78 | 0 | 3089938.78
El Sewedy University | Inv(3)300420 | 3 | El Sewedy University3 | 962231.14 | 48111.56 | 0 | 884290.42
Wadi El Natroun | IPC#3 | 3 | Wadi El Natroun3 | 651015 | 0 | 0 | 0
Assuit PP (CP-118) | 2104210005 |  | Assuit PP (CP-118) | 3573738.67 | 7523660.34 | 0 | 3761830.17
Angola Emergency fast-track | ANG-Cam-Inv 6 | 6 | Angola Emergency fast-track6 | 21874849.84 | 14742271.02 | 0 | 14742271.02
Mohamed Ali Palace Restoration | M.ALY-IPC03 | 3 | Mohamed Ali Palace Restoration3 | 748821.44 | 488067.85 | 135600.01 | 623667.86
Ministries Buildings | MIN ALLOCATION-IPC06 | 6 | Ministries Buildings6 | 16905564.28 | 5711155 | 8598324.45 | 14309479.45
Marsa Alam/ Bernes LOT2 OHTL | Borg Inv. 27 USD | 27 | Marsa Alam/ Bernes LOT2 OHTL27 | 24764.46 | 9681.1205 | 0 | 9681.1205
East Owainat 5 LOTS | East Owainat Inv. 03 | 3 | East Owainat 5 LOTS3 | 80962475.52 | 33154132.72 | 42505299.65 | 75659432.37
BKG#178-Lagoon Discharge | PKG#178-IPC02 | 2 | BKG#178-Lagoon Discharge2 | 15355946.84 | 13230338.292 | 1692993.14 | 14923331.432
UIC Project (LP-04-21) | 53 |  | UIC Project (LP-04-21) | 858487.5 | 0 | 0 | 858487.5
EGYTEC A1,A3 ( LP-05-21) | 60 |  | EGYTEC A1,A3 ( LP-05-21) | 97500 | 0 | 65000 | 65000
Bahr ElBakar – Power Station | IPC#3 Madkour | 3 | Bahr ElBakar – Power Station3 | 994164 | 984222.36 | 0 | 984222.36
New Babil 400/132KV Substation | 2105210012 |  | New Babil 400/132KV Substation | 406584.8 | 406584.8 | 0 | 406584.8
OHTL Mostakable East Boundary | Inv. 04 Future OHTL | 4 | OHTL Mostakable East Boundary4 | 5953293.79 | 4295226.55 | 1896198.99 | 6191425.54
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC010 | 10 | EMAAR-Pkg#162/163- Marassi10 | 0.0001 | 1096860.9301 | 131917.3 | 1228778.2301
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC3,4 | 3 | EMAAR-Pkg#162/163- Marassi3 | 5088605.14 | 8093853.797 | 1040851.13 | 9134704.927
Mauritania Lot 1 | Inv.5 - Lot 1 | 5 | Mauritania Lot 15 | 78138.75 | 74231.81 | 0 | 74231.81
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $9 | 9 | Benban 3/ Toshka 2 LOT 49 | 151413.81 | 126727.6 | 15898.45 | 142626.05
Kafr Shokr Bridge | Kafr Shokr_IPC02 | 2 | Kafr Shokr Bridge2 | 7001830.48 | 6242742.164 | 0 | 6242742.164
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.01 | 1 | Mostakbal 2 Package No. (8)1 | 26909174.1 | 22334614.51 | 5650926.56 | 27985541.07
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC19 | 19 | EMAAR-PKG# 101-UPTOWN19 | 1071378.16 | 1296410.108 | 622319.28 | 1918729.388
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC19 | 19 | EMAAR- Pkg 140-ITP-Mivida19 | 11459315.86 | 8885358.623 | 1136996.72 | 10022355.343
Diplomatic District - Infra | Diplo Dist IPC06 | 6 | Diplomatic District - Infra6 | 15837044.05 | 12861043.65 | 1717677.2 | 14578720.85
EMAAR-Pkg#162/163- Marassi | PKG #163 IPC013 | 13 | EMAAR-Pkg#162/163- Marassi13 | 6375780.45 | 4255708.1825 | 1087618.85 | 5343327.0325
Air Force Project | Air Force Inv . 07 | 7 | Air Force Project7 | 4347859.2 | 3113067.1 | 1086964.8 | 4200031.9
Faculty of Medicine | Mansora ipc10 | 10 | Faculty of Medicine10 | 11906206.67 | 10074037.3535 | 595310.33 | 10669347.6835
Faculty of Medicine | faculty mansora-ipc1 | 1 | Faculty of Medicine1 | 21437884.76 | 18134261.11 | 1071895 | 19206156.11
NUCA R05 - Z02 | R5 FINSHING-IPC7* | 7 | NUCA R05 - Z027 | 828155.16 | 656313.01 | 82815.55 | 739128.56
R5 Mix-Use Complex Project | R5-ZONE01-IPC02 | 2 | R5 Mix-Use Complex Project2 | 25863589.7 | 28409615.74 | 3473696.8 | 31883312.54
Industria Sadat | Sadat Indust Inv. 07 | 7 | Industria Sadat7 | 50462508.82 | 22076559.21 | 10597126.85 | 32673686.06
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .18 | 18 | Benban 3/ Toshka 2 LOT 418 | 4806835.46 | 3277866.47 | 504717.72 | 3782584.19
Railway Bridge - Assuit | IPC#2 Assuit | 2 | Railway Bridge - Assuit2 | 1470820 | 1234799.4 | 0 | 1234799.4
DoubleTree Mangroovy ElGouna | Mangroovy IPC017 | 17 | DoubleTree Mangroovy ElGouna17 | 2987451.96 | 4581335.978 | 295357.13 | 4876693.108
Taval Sarai 52 | IPC-12-Saray-2 | 12 | Taval Sarai 5212 | 406979.33 | 0 | 0 | 406979.33
Taval Sarai 52 | IPC_11_Saray | 11 | Taval Sarai 5211 | 340654 | 259739.51 | 0 | 259739.51
October Dry Port | Dry Port Inv. 05 | 5 | October Dry Port5 | 5651684.01 | 3374772.3 | 1483567.05 | 4858339.35
October Dry Port Railway | ODP ipc3 | 3 | October Dry Port Railway3 | 12846917.73 | 14255254.3995 | 2774511.07 | 17029765.4695
October Dry Port Railway | ODP IPC01 | 1 | October Dry Port Railway1 | 21142097.5 | 13456945.045 | 4439840.48 | 17896785.525
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 05 | 5 | Hosh Essa 220 KV OHTL5 | 22976443.83 | 18633902.9 | 2412526.6 | 21046429.5
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 04 | 4 | Hosh Essa 220 KV OHTL4 | 2366293.31 | 1422148 | 248460.8 | 1670608.8
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 3 Equ | 3 | Hosh Essa 220 KV OHTL3 | 897994.32 | 476335 | 94792.34 | 571127.34
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 74079252.27 | 60783836.38 | 7778321.49 | 68562157.87
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.03 | 3 | Toshka 2/Owinat East LOT2 OHTL3 | 10920854.1 | 9741006.73 | 1146689.68 | 10887696.41
Wadi El Natroun | IPC#2 | 2 | Wadi El Natroun2 | 2142630 | 2000897.2 | 0 | 2000897.2
EGAT Pelletizing Plant | EGAT Water Tank IPC1 | 1 | EGAT Pelletizing Plant1 | 3274479.04 | 3241734.16 | 0 | 3241734.16
Sultana Malak Restoration | Sultana Malak IPC01 | 1 | Sultana Malak Restoration1 | 38453824.39 | 2505968.75 | 32000000 | 34505968.75
Royal City | Royal City IPC20 | 20 | Royal City20 | 1366660.7 | 1092291.595 | 294922.19 | 1387213.785
Royal City | ROYAL CITY2-IPC19 | 19 | Royal City19 | 1583738.34 | 1100401.507 | 301663.7 | 1402065.207
Royal City | Royal City IPC021 | 21 | Royal City21 | 4112519.3 | 2970506.755 | 819101.85 | 3789608.605
Racecores 3092-17 132KV E | 10785 |  | Racecores 3092-17 132KV E | 2145082.775 | 1780418.7 | 0 | 1780418.7
ElMoneeb 2 | IPC#2 Moneeb | 2 | ElMoneeb 22 | 290450 | 287545.5 | 0 | 287545.5
Kattameya Creeks | Katameya Creks IPC07 | 7 | Kattameya Creeks7 | 48280873.42 | 44380444.2275 | 5093038.59 | 49473482.8175
Lekela 250MW Wind Farm | lekela-po2 |  | Lekela 250MW Wind Farm | 342857.14 | 356571.427 | 0 | 356571.427
Lekela 250MW Wind Farm | lekela- po01 |  | Lekela 250MW Wind Farm | 171428.57 | 178285.7085 | 0 | 178285.7085
seashell Playa | IPC-9-Playa | 9 | seashell Playa9 | 385682.5 | 269244.94 | 61709.2 | 330954.14
seashell Playa | IPC-8-PLAYA | 8 | seashell Playa8 | 190902.5 | 133269.02 | 30544.4 | 163813.42
seashell Playa | IPC-6-PLAYA | 6 | seashell Playa6 | 284839.6 | 198456.51 | 45574.34 | 244030.85
Capital One | inv ( 3 ) Captal 1 | 3 | Capital One3 | 787497.0238 | 779622.055 | 0 | 779622.055
EGAT Pelletizing Plant | EGAT-IPC18 | 18 | EGAT Pelletizing Plant18 | 930523.4 | 0 | 1170012.11 | 1170012.11
GOV2 - Infra | GOV2 IPC05 | 5 | GOV2 - Infra5 | 5869423.06 | 47185643.463 | 4507237.7 | 51692881.163
Multi Sport Hall | IPC_14_IndoorHall | 14 | Multi Sport Hall14 | 98166 | 186499.29 | 0 | 186499.29
Mauritania Lot 1 | Inv.12 - Lot 1 | 12 | Mauritania Lot 112 | 331802.75 | 315197.61 | 0 | 315197.61
LAYAN Substation | 10822 |  | LAYAN Substation | 271525.22 | 450731.84 | 0 | 225365.92
Angola Emergency fast-track | ANG-Cam-Inv 8 | 8 | Angola Emergency fast-track8 | 1360018.02 | 753412.56 | 0 | 753412.56
Ext.110 S. Military 220 Kv S/S | Extension kayn Inv 1 | 1 | Ext.110 S. Military 220 Kv S/S1 | 22316542.56 | 13993725 | 5579135.6 | 19572860.6
Assuit PP (CP-118) | inv. 30,31,33 EUR | 30 | Assuit PP (CP-118)30 | 135368.9 | 364529.1 | 60916.02 | 141815.04
Assuit PP (CP-118) | 2106210003 |  | Assuit PP (CP-118) | 308474.46 | 272228.71 | 48584.73 | 320813.44
Miscellaneous Projects | 2008210003 |  | Miscellaneous Projects | 118487.2 | 135075.408 | 0 | 135075.408
Kafr Shokr Bridge | Kafr Shokr IPC04 | 4 | Kafr Shokr Bridge4 | 14900014.29 | 8190447.9 | 0 | 13190447.9
ORA ZED-Ph 2-Pkgs A&D | ora ph 2 ipc 24 | 24 | ORA ZED-Ph 2-Pkgs A&D24 | 1619984.79 | 1344587.3795 | 170098.4 | 1514685.7795
ORA ZED-Ph 2-Pkgs A&D | ORA PH.2- IPC13 | 13 | ORA ZED-Ph 2-Pkgs A&D13 | 20487173.63 | 0 | 0 | 21511532.3115
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.05 | 5 | Toshka 2/Owinat East LOT2 OHTL5 | 11321211.29 | 10093128.56 | 1188727.19 | 11281855.75
10th of Ramadan Railway | IPC#4 HAC | 4 | 10th of Ramadan Railway4 | 2237031 | 2109086.87 | 0 | 2109086.87
East Owainat 5 LOTS | East Owainat Inv. 05 | 5 | East Owainat 5 LOTS5 | 75135244.44 | 30655170.85 | 39446003.33 | 70101174.18
Air Force Project | Air Force Inv . 05 | 5 | Air Force Project5 | 8870694.64 | 6351412.1 | 2217673.66 | 8569085.76
Cairo Monorail - 6th October | IPC#2 Monorail | 2 | Cairo Monorail - 6th October2 | 661500 | 588301 | 0 | 588301
French District | INV (1) Final | 1 | French District1 | 118269 | 110271 | 0 | 110271
NUCA R05 - Z02 | R05 Zone 2 IPC016 | 16 | NUCA R05 - Z0216 | 17343363.3 | 13513254.955 | 1788090.7 | 15301345.655
LAYAN Substation | 10824 |  | LAYAN Substation | 188174.572 | 312369.82 | 0 | 156184.91
Ahl Misr Walkway | IPC03 | 3 | Ahl Misr Walkway3 | 780648 | 650681.36 | 0 | 650681.36
Ahl Misr P3 – Zamalek Sector | IPC#1 - Ahl Misr Gha | 1 | Ahl Misr P3 – Zamalek Sector1 | 1354340 | 1310323.95 | 0 | 1310323.95
MDF Factory | MDF IPC02 | 2 | MDF Factory2 | 6157903.81 | 7093735.0205 | 1616449.75 | 8710184.7705
East Owainat 5 LOTS | East Owainat Inv.2 V | 2 | East Owainat 5 LOTS2 | 48368024.66 | 19353246 | 25393212.95 | 44746458.95
Cairo-Alex Railway | Cairo Alex IPC08 | 8 | Cairo-Alex Railway8 | 10272730.48 | 7275497.89 | 1027273.05 | 8302770.94
Akhmem Assiut | Ref.Ret Asuit. akhm |  | Akhmem Assiut | 36316843.16 | 36316843.16 | 0 | 36316843.16
AWEER POWER STATION 'H' Phase | ENG/043 |  | AWEER POWER STATION 'H' Phase | 181703.73 | 190788.9165 | 0 | 190788.9165
LAYAN Substation | 10742 |  | LAYAN Substation | 109607.22 | 90973.98 | 0 | 90973.98
Racecores 3092-16 132KV C | 10904 |  | Racecores 3092-16 132KV C | 2938654.4 | 2439083.15 | 0 | 2439083.15
Central Bus Station | inv ( 1 ) 30112021 | 1 | Central Bus Station1 | 1908940 | 1908940 | 0 | 1908940
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC018 | 18 | EMAAR-Pkg#162/163- Marassi18 | 12923817.91 | 16022593.1355 | 1927005.65 | 17949598.7855
Le Galawa Hotel Resort | 23000001 |  | Le Galawa Hotel Resort | 510933569 | 510933569 | 0 | 510933569
EDNC Retail & Offices Civil | Sodic Soreal IPC027 | 27 | EDNC Retail & Offices Civil27 | 30032935.16 | 23241827.868 | 72314.2 | 23314142.068
Ain Sokhna Port Development | IPC#1 - Sokhna Port | 1 | Ain Sokhna Port Development1 | 513976 | 477312.78 | 0 | 477312.78
Assuit PP (CP-118) | 2108210011 |  | Assuit PP (CP-118) | 156485.31 | 139663.14 | 24646.44 | 164309.58
Taval Sarai 52 | IPC-13-Saray | 13 | Taval Sarai 5213 | 722955.4 | 468255.3424 | 0 | 468255.3424
Assuit PP (CP-118) | 2108210004 |  | Assuit PP (CP-118) | 1474362.89 | 1273398.7 | 232212.15 | 1505610.85
GOV2 - Infra | GOV 2 - IPC04 | 4 | GOV2 - Infra4 | 1463173.5 | 8057561.675 | 2016166 | 10073727.675
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .27 | 27 | Benban 3/ Toshka 2 LOT 427 | 538032.67 | 479531.63 | 0 | 479531.63
New Heliopolis | Inv. 15 Heliopolise | 15 | New Heliopolis15 | 3830219.65 | 3021627.35 | 376127.6 | 3397754.95
C5 Bridge 2 New Alamein | FPC |  | C5 Bridge 2 New Alamein | 342167.5 | 303527.47 | 0 | 303527.47
Lekela 250MW Wind Farm | SiemensLEKELA IPC013 | 13 | Lekela 250MW Wind Farm13 | 2899145.1 | 2329136.495 | 680919.87 | 3010056.365
Canal Sugar S/s | Inv 12 Sugar S/s | 12 | Canal Sugar S/s12 | 6246012.16 | 6327210.32 | 0 | 6327210.32
Assuit PP (CP-118) | 2110210006 |  | Assuit PP (CP-118) | 1048910.1 | 1101355.61 | 0 | 1101355.61
EGAT Pelletizing Plant | EGAT IPC05 | 5 | EGAT Pelletizing Plant5 | 14565397.44 | 13963438.372 | 1184574.97 | 15148013.342
Cement Factory-Beni Suef | IPC_1_Cement | 1 | Cement Factory-Beni Suef1 | 188320 | 177020.8 | 0 | 177020.8
Racecores 3092-17 132KV E | 11025 |  | Racecores 3092-17 132KV E | 310105.62 | 1544326.02 | 0 | 257387.67
Racecores 3092-17 132KV E | 11028 |  | Racecores 3092-17 132KV E | 68166 | 226311.12 | 0 | 56577.78
Kattameya Creeks | Katamya Creeks ipc33 | 33 | Kattameya Creeks33 | 61236907.71 | 47329832.9684 | 16356551.05 | 63686384.0184
Kattameya Creeks | Katameya CreeksIPC24 | 24 | Kattameya Creeks24 | 38710056.01 | 37876579.918 | 2381876.96 | 40258456.878
Ain Sokhna Bridge – RME | IPC#1-Sokhna Bridge | 1 | Ain Sokhna Bridge – RME1 | 1250625 | 1220827.23 | 0 | 1220827.23
Governmental Campus-N2 | 28 |  | Governmental Campus-N2 | 78507.47 | 78446.5317 | 0 | 78446.5317
Water pumping New Obour City | Wat Pump Obour Inv.7 | 7 | Water pumping New Obour City7 | 15594116.43 | 11913117.95 | 1637382.23 | 13550500.18
Water pumping New Obour City | Wat Pump Obour Inv.5 | 5 | Water pumping New Obour City5 | 15963212.25 | 12195071.5 | 1676137.3 | 13871208.8
Zafranaa - Beni Suef | Zafra Souf Final4Ins |  | Zafranaa - Beni Suef | 22452.48 | 9647.41 | 0 | 9647.41
Nuweibaa (Swro) | 2107210002 |  | Nuweibaa (Swro) | 1828538.48 | 1462830.78 | 365707.7 | 1828538.48
Waldorf Astoria Cairo | WALDORF ASTORIA IPC5 | 5 | Waldorf Astoria Cairo5 | 3030560.1 | 5818860.175 | 3770501.32 | 9589361.495
RING ROAD MARYOTIA EXPANSION | El-Marg IPC07+ | 7 | RING ROAD MARYOTIA EXPANSION7 | 18579510.81 | 364133.09 | 0 | 16364133.09
RING ROAD MARYOTIA EXPANSION | Maryotia IPC012 | 12 | RING ROAD MARYOTIA EXPANSION12 | 19159167.62 | 18678770.82 | 0 | 18678770.82
Akhmem Assiut | Ref.Ret Asuit akh 4 |  | Akhmem Assiut | 20000000 | 0 | 0 | 20000000
Assuit PP (CP-118) | 2110210002 |  | Assuit PP (CP-118) | 6599096.98 | 6863060.86 | 0 | 6863060.86
TZ – Offshore E&M Procurement | 456 |  | TZ – Offshore E&M Procurement | 497407.06 | 497407.06 | 0 | 497407.06
TZ – Offshore E&M Procurement | 467 |  | TZ – Offshore E&M Procurement | 566418.92 | 566418.92 | 0 | 566418.92
Mehwar elsalam Lock & Load | MAHWER ELSALAM-IPC1F | 1 | Mehwar elsalam Lock & Load1 | 19057081.62 | 3184783.11 | 13530390 | 16715173.11
Bahr ElBakar – Power Station | IPC#6 - Madkour | 6 | Bahr ElBakar – Power Station6 | 1901604 | 1882587.96 | 0 | 1882587.96
El-Moneeb Bridge | IPC#2 | 2 | El-Moneeb Bridge2 | 991250 | 1146244.31 | 0 | 1146244.31
El Taameer Axis Expansion | IPC#02 | 2 | El Taameer Axis Expansion2 | 457380 | 441543.08 | 0 | 441543.08
EMAAR-Pkg#162/163- Marassi | pkg #177 IPC021 | 21 | EMAAR-Pkg#162/163- Marassi21 | 10986391.5 | 5908549.745 | 710609.62 | 6619159.365
Racecores 3092-16 132KV C | 11292 |  | Racecores 3092-16 132KV C | 7050341.92 | 5851783.79 | 0 | 5851783.79
Racecores 3092-17 132KV E | 11003 |  | Racecores 3092-17 132KV E | 4969 | 4969 | 0 | 4969
Ring Road Bridges Project | inv ( 2 ) Ring R | 2 | Ring Road Bridges Project2 | 132252.5 | 64945.6 | 0 | 64945.6
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.04 | 4 | Mostakbal 2 Package No. (8)4 | 15370280.74 | 12204002.89 | 3227758.96 | 15431761.85
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC026 | 26 | EMAAR- Pkg 140-ITP-Mivida26 | 3380977.62 | 3321493.111 | 0 | 3321493.111
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 02 | 2 | Toshka-04 GIS Substation2 | 15346707.65 | 13688866.77 | 1611404.3 | 15300271.07
Sokhna Port Expansion | SPX.1 IPC 21 | 21 | Sokhna Port Expansion21 | 8474927 | 5788233.11 | 1779735 | 7567968.11
Sokhna Port Expansion | Spx.1 ipc20 | 20 | Sokhna Port Expansion20 | 19625420 | 13204354.1 | 4121338 | 17325692.1
Sokhna Port Expansion | spx1 ipc19 | 19 | Sokhna Port Expansion19 | 14714279.15 | 10049896.6085 | 3089999 | 13139895.6085
Sokhna Port Expansion | sokhna port ipc16 | 16 | Sokhna Port Expansion16 | 35088709.6 | 23966243.524 | 7368630 | 31334873.524
Olympic Multi – Sports Hall | HALLFINISHING2 IPC01 | 1 | Olympic Multi – Sports Hall1 | 9145259 | 7189055 | 809504.75 | 7998559.75
Railway Bridge - Assuit | IPC#04 Assuit | 4 | Railway Bridge - Assuit4 | 3847180 | 3179102.28 | 0 | 3179102.28
AMRIYA WWTP (3RD STAGE) | 2112210001 |  | AMRIYA WWTP (3RD STAGE) | 2057234.48 | 2036565.64 | 0 | 2036565.64
Cairo Monorail - 6th October | IPC#5 - Monorail | 5 | Cairo Monorail - 6th October5 | 1333500 | 1320165 | 0 | 1320165
TZ – Offshore E&M Procurement | 428 |  | TZ – Offshore E&M Procurement | 173418.41 | 138734.73 | 34683.68 | 173418.41
Akhmem Assiut | Ref. Akhmem Asuit4T |  | Akhmem Assiut | 5000000 | 0 | 0 | 5000000
Akhmem Assiut | Ref. Akhmem Asuit5T |  | Akhmem Assiut | 10000000 | 0 | 0 | 10000000
EGY TECH V2 LP-12-21 | 41 |  | EGY TECH V2 LP-12-21 | 4560 | 5198.4 | 0 | 5198.4
New Babil 400/132KV GIS Substa | 2112210006 |  | New Babil 400/132KV GIS Substa | 1646984.75 | 1646984.75 | 0 | 1646984.75
LAYAN Substation | 11263 |  | LAYAN Substation | 570799.88 | 947527.78 | 0 | 473763.89
LAYAN Substation | 11182 |  | LAYAN Substation | 8562 | 8562 | 0 | 8562
New Giza Teaching Hospital | NEW GIZA HOS IPC27 | 27 | New Giza Teaching Hospital27 | 16173467.3 | 3376911.615 | 891532 | 14606809.615
New Giza Teaching Hospital | New Giza Hos ipc(17) | 17 | New Giza Teaching Hospital17 | 21552600.91 | 1077630.05 | 9087007.5955 | 17664637.6455
Central Bus Station | inv ( 2 ) | 2 | Central Bus Station2 | 421520 | 421520 | 0 | 421520
EGAT Lock & Load | EGAT L&L IPC6 | 6 | EGAT Lock & Load6 | 3378839.59 | 3176109.2095 | 337883.96 | 3513993.1695
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC023 | 23 | EMAAR-Pkg#162/163- Marassi23 | 4755868.69 | 4610166.2945 | 572004.39 | 5182170.6845
Industria Sadat | Sadat Indust Inv. 05 | 5 | Industria Sadat5 | 21467211.7 | 26560136.48 | 4508114.46 | 31068250.94
EGAT Pelletizing Plant | EGAT IPC08 | 8 | EGAT Pelletizing Plant8 | 12121253.24 | 11455129.952 | 1150973.42 | 12606103.372
TZ – Offshore E&M Procurement | 437 |  | TZ – Offshore E&M Procurement | 549036.35 | 439229.08 | 109807.27 | 549036.35
TZ – Offshore E&M Procurement | 464 |  | TZ – Offshore E&M Procurement | 183666.84 | 0 | 183666.6 | 183666.6
Taval Sarai 52 | IPC-20-SARAY | 20 | Taval Sarai 5220 | 141230.9 | 19510.0478 | 0 | 19510.0478
Taval Sarai 52 | IPC-19-SARAY | 19 | Taval Sarai 5219 | 386115.9 | 321685.35 | 0 | 321685.35
R05 | IPC-Final-R05 |  | R05 | 1848 | 1533.84 | 0 | 1533.84
TZ – Offshore E&M Procurement | 460 |  | TZ – Offshore E&M Procurement | 257383.87 | 454020.96 | 1030 | 227525.48
Al Montaza Hotels - Alexandria | inv 7-8-9 Montazha | 7 | Al Montaza Hotels - Alexandria7 | 4353038.9 | 4128486.95 | 0 | 4128486.95
Port Said Port Silos | port said ipc21 | 21 | Port Said Port Silos21 | 15886445.71 | 13770443.8984 | 1588644.57 | 15359088.4684
Port Said Port Silos | port said silosipc19 | 19 | Port Said Port Silos19 | 17118439.26 | 14851957.9104 | 1711843.93 | 16563801.8404
Port Said Port Silos | port said silos ipc7 | 7 | Port Said Port Silos7 | 4021476.86 | 3555860.488 | 402147.69 | 3958008.178
Port Said Port Silos | Port Said Silos IPC2 | 2 | Port Said Port Silos2 | 1883535.14 | 1586748.547 | 245081.44 | 1831829.987
Port Said Port Silos | IPC 7 SUPPLY EGP | 7 | Port Said Port Silos7 | 5552464.75 | 40688461.64 | 4441971.84 | 5641304.185
Port Said Port Silos | PORT SAIED IPC 28 | 28 | Port Said Port Silos28 | 3379589.94 | 2663473.997 | 337959 | 3001432.997
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC 20 | 20 | EMAAR-Pkg#162/163- Marassi20 | 4337585.5 | 2512715.615 | 687025.94 | 3199741.555
Angola Emergency fast-track | ANG-Cam-Inv 5 - Ints | 5 | Angola Emergency fast-track5 | 904750.97 | 663364.14 | 0 | 663364.14
Luxor North Axis Bridge | IPC#3 Luxor offshore | 3 | Luxor North Axis Bridge3 | 843750 | 814508.97 | 0 | 814508.97
IKEA Extension MoA | ikea 2 ipc04 | 4 | IKEA Extension MoA4 | 327656.68 | 441442.804 | 0 | 441442.804
Ghana Street lighting | MIDA Ins.inv.11 | 11 | Ghana Street lighting11 | 53870.62 | 48483.56 | 0 | 48483.56
Racecores 3092-16 132KV C | 11405 |  | Racecores 3092-16 132KV C | 19200 | 20160 | 0 | 20160
EGAT Pelletizing Plant | egat water tank ipc8 | 8 | EGAT Pelletizing Plant8 | 307226.2 | 304153.94 | 0 | 304153.94
Racecores 3092-17 132KV E | 11369 |  | Racecores 3092-17 132KV E | 109587.78 | 92601.68 | 0 | 92601.68
ElSewedy HQ Internal Finishing | ELSEWEDY HQ ipc12 | 12 | ElSewedy HQ Internal Finishing12 | 11990805.42 | 8175767.971 | 2987529.52 | 14329596.631
159E | 11323 |  | 159E | 281422.51 | 281422.51 | 0 | 281422.51
Koning Food LP-04-20 | 47 |  | Koning Food LP-04-20 | 35420 | 40378.8 | 0 | 40378.8
LP-01-22 Citrix Workspace | 73 |  | LP-01-22 Citrix Workspace | 48245.58 | 26773.9404 | 0 | 26773.9404
Faculty of Medicine | FacultyMedcine IPC08 | 8 | Faculty of Medicine8 | 16934024 | 14328324.06 | 846701.2 | 15175025.26
Luxor North Axis Bridge | IPC#4 Luxor Offshore | 4 | Luxor North Axis Bridge4 | 874800 | 804816 | 0 | 804816
Port Said Subs 220/66 | Port Said Inv. 5 | 5 | Port Said Subs 220/665 | 69948870.51 | 45116620 | 17487217.63 | 62603837.63
West Port Said 220 kV GIS | P-45-Portsaid Inv.2$ | 2 | West Port Said 220 kV GIS2 | 323893.33 | 258802.4734 | 34008.8 | 292811.2734
TZ – Offshore E&M Procurement | 451 |  | TZ – Offshore E&M Procurement | 321582.39 | 241186.79 | 48237.36 | 289424.15
Abo Quir - Badr 500KV | Inv 73 Abu Quir Badr | 73 | Abo Quir - Badr 500KV73 | 972401.74 | 384098.71 | 194480.35 | 578579.06
LP-23-21 UMC – 5000 RFID | 70 |  | LP-23-21 UMC – 5000 RFID | 27650 | 31244.5 | 0 | 31244.5
LAYAN Substation | 11747 |  | LAYAN Substation | 177273.88 | 294274.628 | 0 | 147137.314
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 15 | 15 | Suez Gulf/S4 - 500KV OHTL15 | 38381.1 | 25134.23 | 0 | 25134.23
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 06 | 6 | Hosh Essa 220 KV OHTL6 | 1661546.67 | 998588.4 | 174462.4 | 1173050.8
MDF Factory | mdf factory2 ipc01 | 1 | MDF Factory1 | 474511.19 | 487660.3966 | 0 | 487660.3966
Bridge Axis Firdaws | inv ( final ) |  | Bridge Axis Firdaws | 1609889.6 | 865548.8818 | 0 | 865548.8818
Infra Project 4428 | 220421008 |  | Infra Project 4428 | -151428571.43 | -159000000.0015 | 0 | -159000000.0015
Miscellaneous Projects | 220321001 |  | Miscellaneous Projects | 131175 | 149539.5 | 0 | 149539.5
MDF Factory | MDF Factory ipc 36 | 36 | MDF Factory36 | 24401575.22 | 10167393.0388 | 10247566.72 | 20414959.7588
LAYYAH CCPP | 522 |  | LAYYAH CCPP | 2824860 | 2584455 | 240405 | 2824860
Racecores 3092-15 132KV A | 11454 |  | Racecores 3092-15 132KV A | 177580.98 | 294784.418 | 0 | 147392.209
Phosfat | Ret Phosfat T |  | Phosfat | 170472.3 | 170472.3 | 0 | 170472.3
October Dry Port | Dry Port Inv. 08 | 8 | October Dry Port8 | 21727736.72 | 14779027.61 | 5703530.89 | 20482558.5
October Dry Port | Dry Port Inv. 06 | 6 | October Dry Port6 | 12004782.93 | 13713419.57 | 3151255.52 | 16864675.09
Waldorf Astoria Cairo | Waldorf- IPC 19 | 19 | Waldorf Astoria Cairo19 | 9183542.25 | 1409611.34 | 3376215.79 | 4887548.4025
Waldorf Astoria Cairo | waldorf IPC 12 | 12 | Waldorf Astoria Cairo12 | 7707398.93 | 2602999.7165 | 2658217.51 | 5261217.2265
Mivida BP#189 | Pkg#189 ipc02 | 2 | Mivida BP#1892 | 16089263.96 | 19214635.628 | 2238745.48 | 21453381.108
Mivida BP#189 | pkg #189 ipc 11 | 11 | Mivida BP#18911 | 23000800.56 | 19983996.088 | 2379387.42 | 22363383.508
Wadi Halfa Port | wady halfa ipc 4 | 4 | Wadi Halfa Port4 | 4379885.32 | 3015154.5668 | 919775.92 | 3934930.4868
Wadi Halfa Port | wady halfa ipc02 | 2 | Wadi Halfa Port2 | 11905090.1 | 8196261.45 | 2500069.32 | 10696330.77
Wadi Halfa Port | Wadi Halfa ipc 01 | 1 | Wadi Halfa Port1 | 33029518 | 22733362.34 | 6936198.78 | 29669561.12
Racecores 3092-17 132KV E | 11599 |  | Racecores 3092-17 132KV E | 96761.48 | 160624.048 | 0 | 80312.024
Racecores 3092-17 132KV E | 11541 |  | Racecores 3092-17 132KV E | 691244.2769 | 4088709.9451 | 0 | 584101.4207
Ghana Street lighting | MIDA Sply.inv.12 | 12 | Ghana Street lighting12 | 69621.7 | 62659.53 | 0 | 62659.53
Abou Ghaleb Bridge | abo Ghaleb ipc02 | 2 | Abou Ghaleb Bridge2 | 669446.33 | 662751.87 | 0 | 662751.87
Abou Ghaleb Bridge | ABO GHALEB IPC01 | 1 | Abou Ghaleb Bridge1 | 12157987.62 | 1998969.021 | 0 | 7589747.021
Industria Sadat | Sadat Indust Inv. 04 | 4 | Industria Sadat4 | 14944151.43 | 10726695.29 | 3138271.8 | 13864967.09
Kuwait | Inv.4988/Sp/H&J-02 | 4988 | Kuwait4988 | 22585.37 | 21456.1 | 0 | 21456.1
New Babil 400/132KV GIS Substa | 220421003 |  | New Babil 400/132KV GIS Substa | 825040.8 | 825040.8 | 0 | 825040.8
New Babil 400/132KV GIS Substa | 220421002 |  | New Babil 400/132KV GIS Substa | 247512.24 | 247512.24 | 0 | 247512.24
Elhegaz | D0028-OB-Dec-2020D.M | 2020 | Elhegaz2020 | 19094677.06 | 19094677.06 | 0 | 19094677.06
HST Bridges-Sokhna & Mahager | hst sokhna ipc01 | 1 | HST Bridges-Sokhna & Mahager1 | 67034460.71 | 56136552.2355 | 0 | 59136552.2355
GOV2 - Infra | Gov 2 - IPC03 | 3 | GOV2 - Infra3 | 9273010.19 | 7895653.18 | 2158016.15 | 10053669.33
Faculty of Medicine | MANSOURA FINISHIPC28 | 28 | Faculty of Medicine28 | 39981757.14 | 0 | 5997263.57 | 5997263.57
Faculty of Medicine | Mansora Finish ipc06 | 6 | Faculty of Medicine6 | 4638751.43 | 3460801.25 | 695812.71 | 4156613.96
MDF Factory | MDF FACTORY3 IPC03 | 3 | MDF Factory3 | 1238493.58 | 897907.8412 | 352970.67 | 1250878.5112
Racecores 3092-16 132KV C | 11620 |  | Racecores 3092-16 132KV C | 2626.81 | 2626.81 | 0 | 2626.81
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 19 | 19 | Benban 500 K.V/95 K.M19 | 641158.81 | 494337.86 | 67321.68 | 561659.54
EMAAR-Pkg#162/163- Marassi | Pkg#177 IPC32 | 32 | EMAAR-Pkg#162/163- Marassi32 | 5829703.87 | 10452697.3335 | 2179865.32 | 12632562.6535
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 2490376.38 | 1682555.26 | 235322.57 | 2281542.72
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv15 | 15 | Marsa Alam/ Bernes LOT2 OHTL15 | 8912653.97 | 6717169.16 | 0 | 6717169.16
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv12 | 12 | Marsa Alam/ Bernes LOT2 OHTL12 | 148021.88 | 133009.55 | 0 | 133009.55
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv10 | 10 | Marsa Alam/ Bernes LOT2 OHTL10 | 4517079.02 | 4073899.58 | 0 | 4073899.58
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .25 | 25 | Benban 3/ Toshka 2 LOT 425 | 36459593.62 | 29137204.39 | 1814998.04 | 30952202.43
Ora Zed Landscape Ph1 | Ora landscape ipc 20 | 20 | Ora Zed Landscape Ph120 | 1318831.15 | 1177303.85 | 505803.07 | 1683106.92
Ora Zed Landscape Ph1 | Ora Landscape ipc 19 | 19 | Ora Zed Landscape Ph119 | 1347822.27 | 618692.48 | 141521.34 | 760213.82
Ora Zed Landscape Ph1 | Ora Landsca ipc13-14 | 13 | Ora Zed Landscape Ph113 | 1148717.83 | 868255.79 | 120615.37 | 988871.16
AWEER POWER STATION 'H' Phase | LOC/026 |  | AWEER POWER STATION 'H' Phase | 529432.1 | 464723.7331 | 58825.79 | 523549.5231
Zambia Project | SCD4x/0013 |  | Zambia Project | 30567.27 | 30537.52 | 0 | 30537.52
2 track mach | 2 track mach Inv.01 | 1 | 2 track mach1 | 10526315.79 | 3000000 | 1200000 | 4200000
EMAAR-Pkg#162/163- Marassi | pkg#177-IPC35 | 35 | EMAAR-Pkg#162/163- Marassi35 | 20620247.8 | 15928851.3665 | 3692100.026 | 19620951.3925
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $10 | 10 | Benban 3/ Toshka 2 LOT 410 | 150190.95 | 125704.4 | 15770.05 | 141474.45
PLAYA ROOF & Wet Areas | IPC-10-PLAYA ROOF | 10 | PLAYA ROOF & Wet Areas10 | 234166.18 | 177538 | 0 | 177538
EGAT Pelletizing Plant | egat ipc 13 | 13 | EGAT Pelletizing Plant13 | 22223108.96 | 21580273.568 | 1531759.75 | 23112033.318
EGAT Pelletizing Plant | EGAT IPC04 | 4 | EGAT Pelletizing Plant4 | 7555014.44 | 7145933.742 | 711281.28 | 7857215.022
New Giza Teaching Hospital | new giza hos ipc05 | 5 | New Giza Teaching Hospital5 | 14819091.38 | 10433639.459 | 2251618.11 | 12685257.569
Benban 3/ Toshka 2 Lot 6 | Ref-Ret-Toshka Lot6T |  | Benban 3/ Toshka 2 Lot 6 | 39490847.01 | 39490847.01 | 0 | 39490847.01
Benban 500 K.V / 100 K.M | Ref-Ret-Benba lot1T |  | Benban 500 K.V / 100 K.M | 15330832.04 | 15330832.04 | 0 | 15330832.04
LAYYAH CCPP | 505 |  | LAYYAH CCPP | 493529 | 429174.42 | 74029.35 | 503203.77
LAYYAH CCPP | 507 |  | LAYYAH CCPP | 5141880 | 4527710.6 | 842908 | 5370618.6
LAYYAH CCPP | 502 |  | LAYYAH CCPP | 256625 | 229037.81 | 38493.75 | 267531.56
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC 22 | 22 | EMAAR-Pkg#162/163- Marassi22 | 2631392.92 | 2390070.524 | 0 | 2390070.524
Ain Sokhna Port Development | IPC#15 - Sokhna Port | 15 | Ain Sokhna Port Development15 | 493848 | 365799.5 | 0 | 457249.37
Infra Project 2531 | 220321001 |  | Infra Project 2531 | 480723957.15 | 410882610 | 0 | 410882610
GSM-02-22 IHS | 85 |  | GSM-02-22 IHS | 2215649.1 | 2525839.99 | 0 | 2525839.99
TZ – Offshore E&M Procurement | 469 |  | TZ – Offshore E&M Procurement | 274863.23 | 274863.23 | 0 | 274863.23
Zone(J) South Valley Toshka | South Valley Inv. 15 | 15 | Zone(J) South Valley Toshka15 | 55134638.9 | 33347809.15 | 6205443.52 | 39553252.67
PLAYA ROOF & Wet Areas | IPC-9-PLAYA ROOF | 9 | PLAYA ROOF & Wet Areas9 | 64076.15 | 54983.74 | 0 | 54983.74
Marassi - Anti carbonation | IPC-01-PK177.ANTI | 1 | Marassi - Anti carbonation1 | 234306 | 207477.96 | 0 | 207477.96
ORA ZED-Ph 2-Pkgs A&D | ORAZEHD PH.2 IPC8 | 8 | ORA ZED-Ph 2-Pkgs A&D8 | 8766077.29 | 9151883.2345 | 1112688.66 | 10264571.8945
Playa Epoxy | IPC-Playa Epoxy |  | Playa Epoxy | 492872.4 | 422930.8889 | 0 | 422930.8889
seashell Playa | IPC-19-Playa | 19 | seashell Playa19 | 527180.57 | 452373.64 | 0 | 452373.64
seashell Playa | IPC-10-PLAYA | 10 | seashell Playa10 | 280285.45 | 195667.29 | 44845.67 | 240512.96
Egyptian Exchange building | IPC-7-Borsa | 7 | Egyptian Exchange building7 | 14146.6 | 12502.1547 | 0 | 12502.1547
Egyptian Exchange building | IPC-4-BORSA | 4 | Egyptian Exchange building4 | 126224.8 | 111772.06 | 0 | 111772.06
Marassi - Anti carbonation | IPC-2-PK#177Anticarb | 2 | Marassi - Anti carbonation2 | 17867.7 | 317.84 | 0 | 317.84
Egyptian Exchange building | IPC-05-BORSA | 5 | Egyptian Exchange building5 | 99273.45 | 87906.65 | 0 | 87906.65
Sodic East | 10093 |  | Sodic East | 180165.97 | 159807.15 | 0 | 159807.15
EMAAR-Pkg#162/163- Marassi | pkg#177 ipc22 | 22 | EMAAR-Pkg#162/163- Marassi22 | 7589823.48 | 3656481.974 | 439757.87 | 4096239.844
BKG#178-Lagoon Discharge | PKG #178 IPC06 | 6 | BKG#178-Lagoon Discharge6 | 4524611.34 | 2967821.117 | 0 | 2967821.117
RING ROAD MARYOTIA EXPANSION | MARIOTYIA IPC17 | 17 | RING ROAD MARYOTIA EXPANSION17 | 41585303.99 | 41169450.9495 | 0 | 41169450.9495
NUCA R05 - Z02 | R05 Zone2 IPC017 | 17 | NUCA R05 - Z0217 | 19906898.8 | 21166577.92 | 2865993.9 | 24032571.82
LINX Tower | inv ( 2 ) LINX | 2 | LINX Tower2 | 283672.26 | 266651.933 | 0 | 266651.933
Ain Sokhna Port Development | IPC#17 -Sokhna Port | 17 | Ain Sokhna Port Development17 | 679041 | 510216.64 | 0 | 637770.8
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC25 | 25 | EMAAR-Pkg#162/163- Marassi25 | 12934137.54 | 12395959.047 | 0 | 12395959.047
SSC Suez Steel Company Project | int&ret sup sscipc 8 | 8 | SSC Suez Steel Company Project8 | 2489471.85 | 1886800.519 | 926302.67 | 2813103.189
SSC Suez Steel Company Project | Int&Ret APP(ssc)ipc6 | 6 | SSC Suez Steel Company Project6 | 7103010.22 | 6571472.514 | 921113.82 | 7492586.334
ORA ZED-Ph 2-Pkgs A&D | ora zed 2 ipc 7 | 7 | ORA ZED-Ph 2-Pkgs A&D7 | 42383851.59 | 34124964.2595 | 4049151.33 | 38174115.5895
ElSewedy HQ Internal Finishing | el sewedy hq ipc13 | 13 | ElSewedy HQ Internal Finishing13 | 23373232.29 | 869511.3245 | 15100757.78 | 25970269.1045
Kattameya Creeks | Katameya CreeksIPC18 | 18 | Kattameya Creeks18 | 42935687.01 | 41641258.1345 | 3011856.35 | 44653114.4845
EPICO 3 Facility | Eipico ipc11 | 11 | EPICO 3 Facility11 | 27259074.64 | 23263190.12 | 10328302.36 | 33591492.48
EPICO 3 Facility | Eipico ipc 10 | 10 | EPICO 3 Facility10 | 9818518.79 | 0 | 2172763.92 | 2172763.92
Bahr ElBakar – Power Station | IPC#8 Madkour | 8 | Bahr ElBakar – Power Station8 | 2993842.95 | 2486747.58 | 0 | 2486747.58
Playa Epoxy | 02 |  | Playa Epoxy | 137956.4 | 62280.39 | 0 | 62280.39
Sultana Malak Restoration | sultana malk3 ipc01 | 1 | Sultana Malak Restoration1 | 12615078.24 | 10367530 | 0 | 10367530
Al-Parco | INV ( 1 ) ALparco | 1 | Al-Parco1 | 1879350 | 1766589 | 0 | 1766589
EGAT Pelletizing Plant | Elco egat ipc14 | 14 | EGAT Pelletizing Plant14 | 8283062.86 | 7794639.393 | 819745.98 | 8614385.373
EGAT Pelletizing Plant | Elco Egat ipc15 | 15 | EGAT Pelletizing Plant15 | 20298475.24 | 19186530.252 | 1923884 | 21110414.252
Diplomatic District - Infra | Diplomatic ipc 13 | 13 | Diplomatic District - Infra13 | 16548362.5 | 5939031.605 | 900944.24 | 6839975.845
HSR-6th of October | IPC#3 HSR | 3 | HSR-6th of October3 | 1408920 | 1225760.4 | 0 | 1225760.4
CS-20 Mall | inv ( 2 ) CS-20 | 2 | CS-20 Mall2 | 971119.35 | 912852.19 | 0 | 912852.19
El Khatatba Bridge | El Khataba ipc3+4 | 3 | El Khatatba Bridge3 | 24106000 | 20047104.85 | 0 | 20047104.85
Sokhna Port Expansion | sokhna port ex ipc5 | 5 | Sokhna Port Expansion5 | 84601518.57 | 59074965.265 | 17766318.9 | 76841284.165
Railway Bridge - El Hammam | IPC#1 - ElHammam Pro | 1 | Railway Bridge - El Hammam1 | 1803303.5 | 1694038.06 | 0 | 1694038.06
Port Said Port Silos | port said silos ipc4 | 4 | Port Said Port Silos4 | 3348506.91 | 2971799.8855 | 334850.69 | 3306650.5755
EGAT Pelletizing Plant | plant supp Ro puipc4 | 4 | EGAT Pelletizing Plant4 | 2453301.65 | 2216012.061 | 556218.8 | 2772230.861
Kafr Shokr Bridge | KafrShokr Brdg IPC06 | 6 | Kafr Shokr Bridge6 | 2805242.86 | 444257.73 | 0 | 2444257.73
Port Said Port Silos | port said silos ipc5 | 5 | Port Said Port Silos5 | 5318356.37 | 4663281.2785 | 531835.64 | 5195116.9185
EL -mahager Bridge Ain sokhna | ipc 2 mahger | 2 | EL -mahager Bridge Ain sokhna2 | 3450000 | 5737910.4 | 0 | 3058955.2
EL -mahager Bridge Ain sokhna | IPC 2 ELMAHAGER | 2 | EL -mahager Bridge Ain sokhna2 | 3450000 | 0 | 0 | 3450000
Egat Rolling Mill no.4 | Rolling mill ipc06 | 6 | Egat Rolling Mill no.46 | 5743580.95 | 4622529.1875 | 1350795 | 5973324.1875
EMAAR-Pkg#162/163- Marassi | pkg#163- IPC28 | 28 | EMAAR-Pkg#162/163- Marassi28 | 17622733.92 | 19371561.356 | 0 | 19371561.356
WADY EL-NATROUN BRIDGE(HST) | IPC#4 - Wadi El Natr | 4 | WADY EL-NATROUN BRIDGE(HST)4 | 717360 | 512147.7 | 0 | 642434.62
EDNC Hardscape Package | sorealhardscapeIPC10 | 10 | EDNC Hardscape Package10 | 3106667.35 | 3067833.9875 | 0 | 3067833.9875
EGAT Injection | IPC01EGATINJECTION | 1 | EGAT Injection1 | 175000 | 149217.5 | 0 | 149217.5
EGAT Pelletizing Plant | EGAT - IPC17 | 17 | EGAT Pelletizing Plant17 | 16943574.98 | 15969082.719 | 1652235.26 | 17621317.979
Expansion of Ring Road NRCC | IPC#2 NRCC | 2 | Expansion of Ring Road NRCC2 | 849400 | 522665.3 | 0 | 522665.3
Kattameya Creeks | Katameya IPC21 | 21 | Kattameya Creeks21 | 36255948.47 | 35259435.93 | 2446750.47 | 37706186.4
Waldorf Astoria Cairo | waldorf IPC10 | 10 | Waldorf Astoria Cairo10 | 9739259.16 | 4982321 | 5090575.7 | 10072896.7
Hyper One Badr | INV ( 4:9 ) Hipper | 4 | Hyper One Badr4 | 2586336.17 | 2301839.19 | 0 | 2301839.19
Faculty of Medicine | mansorafinshing ipc1 | 1 | Faculty of Medicine1 | 8775226.67 | 6542217.0052 | 1316284 | 7858501.0052
SODIC Allegria Villa f100 | Sodic VillaF100 IPC1 | 1 | SODIC Allegria Villa f1001 | 5146090.48 | 1600000 | 3776500 | 5376500
Air Defense College | Air def4 IPC2 | 2 | Air Defense College2 | 527000 | 443595 | 0 | 443595
Air Defense College | Air def2 IPC3 | 3 | Air Defense College3 | 6165128 | 2399535 | 0 | 5221935
HSR-6th of October | IPC#4 HSR | 4 | HSR-6th of October4 | 307440 | 267472.8 | 0 | 267472.8
GOV2 - Infra | GOV 2 IPC09 | 9 | GOV2 - Infra9 | 39828531.57 | 12242703.7 | 1976985.55 | 14219689.25
RING ROAD MARYOTIA EXPANSION | ESC.1:17 (Estsmar) |  | RING ROAD MARYOTIA EXPANSION | 14285714.29 | 13925317.49 | 0 | 13925317.49
MDF Factory | MDF 2 - IPC 12 | 12 | MDF Factory12 | 447300.74 | 451773.7436 | 0 | 451773.7436
PVD - El Hammam | IPC1 PVD | 1 | PVD - El Hammam1 | 312473.03 | 276226.16 | 0 | 276226.16
EMAAR-Pkg#162/163- Marassi | pkg#177- IPC36 | 36 | EMAAR-Pkg#162/163- Marassi36 | 42116952.2 | 36331150.12 | 26252727.91 | 62583878.03
GOV2 - Infra | GOV2 IPC010 | 10 | GOV2 - Infra10 | 19212935.81 | 23359592.71 | 2865073.75 | 26224666.46
Kattameya Creeks | Katameya IPC 22 | 22 | Kattameya Creeks22 | 32375932.35 | 31299260.0175 | 2371709.63 | 33670969.6475
Diplomatic District - Infra | DIPLOMATIC IPC10 | 10 | Diplomatic District - Infra10 | 16607651.9 | 18657092.23 | 2398226.8 | 21055319.03
Diplomatic District - Infra | diplomatic ipc 14 | 14 | Diplomatic District - Infra14 | 12173381.9 | 4045239.4587 | 678285.3 | 4723524.7587
WADY EL-NATROUN BRIDGE(HST) | IPC#11 Wadinatron | 11 | WADY EL-NATROUN BRIDGE(HST)11 | 1601250 | 1454095.12 | 0 | 1454095.12
Pushing Tunnel | Inv ( 4 ) T. Pushing | 4 | Pushing Tunnel4 | 5985000 | 4836478.37 | 0 | 4836478.37
Pushing Tunnel | Inv ( 2 ) T. Pushing | 2 | Pushing Tunnel2 | 3231900 | 2511698.39 | 0 | 2511698.39
HSR-6th of October | IPC9 HSR6th | 9 | HSR-6th of October9 | 1136000 | 918710.41 | 0 | 918710.41
Seashell Playa 5 Villas | seashell playa-IPC3 | 3 | Seashell Playa 5 Villas3 | 383747.94 | 255255.5 | 0 | 255255.5
Al-Parco | INV ( 2 ) ALparco | 2 | Al-Parco2 | 285175 | 268064.5 | 0 | 268064.5
HSR-6th of October | IPC#6 HSR | 6 | HSR-6th of October6 | 596290 | 518772.3 | 0 | 518772.3
Al-Ula Towers - ( 2 ) | INV ( 1 ) Al-Ula-2 | 1 | Al-Ula Towers - ( 2 )1 | 3385443.4 | 2800000 | 0 | 2800000
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC (29) | 29 | EMAAR-Pkg#162/163- Marassi29 | 20296742.21 | 19850779.098 | 0 | 19850779.098
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 33 | 33 | ORA ZED - Ph 01B - Pkgs A&D33 | 18602239.47 | 12164893.39 | 4938944.34 | 17103837.73
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc32 | 32 | ORA ZED - Ph 01B - Pkgs A&D32 | 17918865.67 | 8010573.17 | 10032784.1 | 18043357.27
DP World Basin 2 Ph2 | DP World ph.2 IPC2 | 2 | DP World Basin 2 Ph22 | 31312811.13 | 19472869.78 | 8394835.91 | 27867705.69
October Under-Railway Tunnel | october tunnel ipc 5 | 5 | October Under-Railway Tunnel5 | 3663513.71 | 2856009 | 0 | 2856009
Irrigation Tank | IPC2&3TR0061 | 2 | Irrigation Tank2 | 727407.2 | 591238.85 | 0 | 591238.85
EMAAR-Pkg#162/163- Marassi | PKG#177- IPC41 | 41 | EMAAR-Pkg#162/163- Marassi41 | 16303582.18 | 180103.25 | 3311188.669 | 3491291.919
MDF Factory | MDF Factory ipc (24) | 24 | MDF Factory24 | 20265495.39 | 2096504.5956 | 13271764.92 | 15368269.5156
ORA ZED-Ph 2-Pkgs A&D | ORA PH.2 - IPC15 | 15 | ORA ZED-Ph 2-Pkgs A&D15 | 20441047.55 | 11268654.1775 | 1426947.75 | 12695601.9275
SSC Suez Steel Company Project | R.O. Sup. adj. IPC4 | 4 | SSC Suez Steel Company Project4 | 6753929.79 | 7294244.1727 | 0 | 7294244.1727
Sokhna Port Expansion | spx2 ipc 2 | 2 | Sokhna Port Expansion2 | 24129951.4 | 10628517.7515 | 4825990.28 | 21454508.0315
Railway Bridge - El Hammam | IPC 7 elswedy | 7 | Railway Bridge - El Hammam7 | 949018.9 | 771783.98 | 0 | 771783.98
WADY EL-NATROUN BRIDGE(HST) | IPC no15 wadinatroun | 15 | WADY EL-NATROUN BRIDGE(HST)15 | 1853290 | 1346373.51 | 0 | 1346373.51
Kattameya Creeks | katamya creeks ipc32 | 32 | Kattameya Creeks32 | 52360770.17 | 41216438 | 13238762.34 | 54455200.34
Air Defense College | Air Def finish IPC3 | 3 | Air Defense College3 | 3051528 | 2335760 | 0 | 2572876
New Giza Teaching Hospital | new geza Hosp ipc 14 | 14 | New Giza Teaching Hospital14 | 21572565.8 | 16275653.05 | 2250467.33 | 18526120.38
PVD - El Hammam | IPC#3 PVD Hamam | 3 | PVD - El Hammam3 | 217061 | 169279.39 | 0 | 169279.39
Kattameya Creeks | Katamya Creeks ipc34 | 34 | Kattameya Creeks34 | 82997244.56 | 70308953 | 15196003.57 | 85504956.57
ORA-ZED Towers P01B | IPC008 | 8 | ORA-ZED Towers P01B8 | 360594 | 319305.99 | 0 | 319305.99
Katameya Creeks - RME | IPC0006 | 6 | Katameya Creeks - RME6 | 102468.56 | 90735.9 | 0 | 90735.9
MAF HQ Renovation | Carrefour H off ipc3 | 3 | MAF HQ Renovation3 | 8617729.61 | 5795423.13 | 2262154.02 | 8057577.15
SEASHELL TECHNICAL ROOM | IPC06TR0065 | 6 | SEASHELL TECHNICAL ROOM6 | 115200.05 | 99486.77 | 0 | 99486.77
Ministries Buildings | Minis Alloc IPc12 | 12 | Ministries Buildings12 | 13385562 | 22553870 | 0 | 11276935
Waldorf Astoria Cairo | Waldrof Asto ipc 18 | 18 | Waldorf Astoria Cairo18 | 10421093.88 | 3217413.914 | 4923966.86 | 12961136.774
MDF Factory | Mdf local ipc 14 | 14 | MDF Factory14 | 12194201.3 | 10315795 | 2000199.6458 | 12315994.6458
EPICO 3 Facility | EIPICO IPC (5) | 5 | EPICO 3 Facility5 | 13210447.27 | 10064340.12 | 3404105.19 | 13468445.31
Seashell Playa 5 Villas | Playa c045 - ipc 1 | 1 | Seashell Playa 5 Villas1 | 71198.7 | 18553.19 | 0 | 18553.19
Port Said Port Silos | port saidsilos ipc15 | 15 | Port Said Port Silos15 | 10044463.56 | 8897631.4024 | 1004446.36 | 9902077.7624
Air Defence College | IPC0013 TR0046 | 13 | Air Defence College13 | 1607066.54 | 1364399.49 | 0 | 1364399.49
Air Defense College | Air Dev16 IPC4 | 4 | Air Defense College4 | 6831127 | 462800 | 0 | 5808267
SSC Suez Steel Company Project | Shutdown smp2 ipc(2) | 2 | SSC Suez Steel Company Project2 | 11073867.25 | 5979888.32 | 5536933.62 | 11516821.94
SSC Suez Steel Company Project | Shutdown smp1 -ipc 2 | 2 | SSC Suez Steel Company Project2 | 17650842.77 | 8648912.9484 | 8825421.39 | 17474334.3384
NUCA R05 - Z02 | R05(2) ipc 35 | 35 | NUCA R05 - Z0235 | 18335541.14 | 14613599.29 | 1875883.5 | 16489482.79
Air Defence College | 11 |  | Air Defence College | 190510.2 | 161743.16 | 0 | 161743.16
ORA-ZED Towers P01B | IPC009 | 9 | ORA-ZED Towers P01B9 | 202026 | 178894.02 | 0 | 178894.02
Get Business Complex | INV ( 7 ) GET | 7 | Get Business Complex7 | 1164549.6 | 1094676.624 | 0 | 1094676.624
RING ROAD MARYOTIA EXPANSION | mariotya ipc20 be16 | 20 | RING ROAD MARYOTIA EXPANSION20 | 28422356.38 | 9762780.95 | 0 | 9762780.95
Mohamed Nader Villa's | Mohamed N villa ipc1 | 1 | Mohamed Nader Villa's1 | 4289255.33 | 2070213.9265 | 2165425.71 | 4235639.6365
Air Defense College | Air dev Shapcat IPC1 | 1 | Air Defense College1 | 23046232 | 3048570 | 16200000 | 19248570
Cairo-Alex Railway | Cairo-alex ipc 34 | 34 | Cairo-Alex Railway34 | 40544596.19 | 28066864.95 | 4257182.6 | 32324047.55
Cairo-Alex Railway | Cairo Alex IPC010 | 10 | Cairo-Alex Railway10 | 21071680 | 14375414.95 | 2107168 | 16482582.95
Cairo-Alex Railway | Cairo-Alex IPC013 | 13 | Cairo-Alex Railway13 | 22436876.43 | 13355344.72 | 3111549.1 | 16466893.82
Sixty Iconic Tower | Inv ( 3 ) sixty | 3 | Sixty Iconic Tower3 | 127635.78 | 116807.63 | 0 | 116807.63
ORA ZED-Ph 2-Pkgs A&D | Ora ph 2 ipc (20) | 20 | ORA ZED-Ph 2-Pkgs A&D20 | 4105367.03 | 3188540.2834 | 403369.56 | 3591909.8434
Ora Zed Landscape Ph1 | ora landscape ipc 6 | 6 | Ora Zed Landscape Ph16 | 3759868.55 | 3318083.9875 | 394786.2 | 3712870.1875
Air Defense College | Air Finsh IPC4 | 4 | Air Defense College4 | 2385006 | 1808529.97 | 0 | 2010982.97
Port Said Port Silos | portsaid silos ipc20 | 20 | Port Said Port Silos20 | 12988783.81 | 8189528.9592 | 4298878.38 | 12488407.3392
EGAT Pelletizing Plant | IPC1 PLANTSUPPLY RO | 1 | EGAT Pelletizing Plant1 | 5322406.46 | 691912.8398 | 5322406.46 | 6014319.2998
EGAT Pelletizing Plant | CementPriceEscaltion |  | EGAT Pelletizing Plant | 7000000.28 | 7280000.294 | 0 | 7280000.294
EPICO 3 Facility | Eipico Ipc ( 8) | 8 | EPICO 3 Facility8 | 18125037.75 | 20317361.34 | 6844285.93 | 27161647.27
Air Defense College | Air Def finish IPC2 | 2 | Air Defense College2 | 6347561 | 4905910 | 0 | 4905910
EPICO 3 Facility | Eipico ipc 17 | 17 | EPICO 3 Facility17 | 30615959.94 | 13161378.737 | 17000000 | 30161378.737
EPICO 3 Facility | Eipico ipc 13 | 13 | EPICO 3 Facility13 | 50645327.08 | 2882568.41 | 24139643.31 | 27022211.72
Ain Sokhna Bridge | inv ( 1 ) A.S | 1 | Ain Sokhna Bridge1 | 28963170 | 659833.69 | 0 | 659833.69
Tarek Abdel-Hakim Center | TAH IPC04 | 4 | Tarek Abdel-Hakim Center4 | 1181749.35 | 909356.12 | 106357.44 | 1015713.56
Sokhna Port Expansion | sokhna port ipc 13 | 13 | Sokhna Port Expansion13 | 29580920.45 | 491489.95 | 5916184.09 | 26407674.04
El Taameer Axis Expansion | IPC#4 - Taamer PII | 4 | El Taameer Axis Expansion4 | 344520 | 332806.32 | 0 | 332806.32
WADY EL-NATROUN BRIDGE(HST) | IPC no16 D0073 | 16 | WADY EL-NATROUN BRIDGE(HST)16 | 1124077.5 | 491817.82 | 0 | 491817.82
Seashell Playa 5 Villas | Playa c038 ipc 7 | 7 | Seashell Playa 5 Villas7 | 37979.47 | 32799.07 | 0 | 32799.07
Tarek Abdel-Hakim Center | TAH ipc03 | 3 | Tarek Abdel-Hakim Center3 | 1124829.43 | 865556.24 | 101234.65 | 966790.89
SSC Suez Steel Company Project | I&R apply (ssc) ipc4 | 4 | SSC Suez Steel Company Project4 | 2492009.61 | 0 | 323162.22 | 2766130.6654
Seashell Playa 5 Villas | playa-c234 ipc (1) | 1 | Seashell Playa 5 Villas1 | 353841.09 | 323269.22 | 0 | 323269.22
Faculty of Medicine | mansora ipc16 final | 16 | Faculty of Medicine16 | 34226738.1 | 44569890.39 | 230114.95 | 44800005.34
U4,U8 Seashell Playa | IPC08 TR60 | 8 | U4,U8 Seashell Playa8 | 601043.97 | 514061.57 | 0 | 514061.57
U7-SEASHELL | IPC08 TR64 | 8 | U7-SEASHELL8 | 193306.24 | 166939.27 | 0 | 166939.27
Haramein Columns Transfer | Haramin ipc02 | 2 | Haramein Columns Transfer2 | 288000 | 240000 | 0 | 240000
Katameya Creeks - RME | IPC 11 TR53 | 11 | Katameya Creeks - RME11 | 169347.16 | 149956.91 | 0 | 149956.91
R05 (New) | IPC04 TR59 | 4 | R05 (New)4 | 88932 | 75423.23 | 0 | 75423.23
U3 & U5 | IPC12&13TR0055 | 12 | U3 & U512 | 226988.84 | 153144.54 | 0 | 153144.54
VILLA CLUSTRER B | IPC1&2 TR0077 | 1 | VILLA CLUSTRER B1 | 701780.5 | 606057.55 | 0 | 606057.55
HST El Mahager Bridge | mahager bridge ipc4 | 4 | HST El Mahager Bridge4 | 6289028.57 | 1120148.4028 | 0 | 5572311.4028
ora zed orascom | IPC07TR0069 | 7 | ora zed orascom7 | 629136.31 | 570187.87 | 0 | 570187.87
Sixty Iconic Tower | Inv ( 4 ) sixty | 4 | Sixty Iconic Tower4 | 1553224.22 | 1470030.77 | 0 | 1470030.77
GOV2 - Infra | GOV2 IPC 23 | 23 | GOV2 - Infra23 | 6553172.38 | 2581681.46 | 470072.51 | 3051753.97
ZED Phase 2 | IPC02TR0062 | 2 | ZED Phase 22 | 27001.998 | 22938.21 | 0 | 22938.21
SSC Suez Steel Company Project | I&R Supply SSC-IPC5 | 5 | SSC Suez Steel Company Project5 | 2293673.98 | 2650.0808 | 853448.63 | 2280322.6996
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc (22) | 22 | ORA ZED-Ph 2-Pkgs A&D22 | 10796355.55 | 8347638.3819 | 1056026.6 | 9403664.9819
Get Business Complex | INV ( 9 & 10) GET | 9 | Get Business Complex9 | 275623.72 | 259086.29 | 0 | 259086.29
VILLA CLUSTER C | IPC05TR0078 | 5 | VILLA CLUSTER C5 | 11515.09 | 9944.44 | 0 | 9944.44
VILLA CLUSTRER B | IPC04TR0077 | 4 | VILLA CLUSTRER B4 | 47134.89 | 40705.7 | 0 | 40705.7
Jawhara Palace Restoratio | Gawhara IPC6 | 6 | Jawhara Palace Restoratio6 | 2297237.99 | 1561600 | 574309.5 | 2135909.5
MDF Factory | MDF - IPC 13 | 13 | MDF Factory13 | 16038148.23 | 2376884.4693 | 17060757.9 | 19437642.3693
MDF Factory | MDF Factory ipc 31 | 31 | MDF Factory31 | 25781281.67 | 18542599.6668 | 10832542.51 | 29375142.1768
EGAT Pelletizing Plant | Egat Ro2 ipc 1 | 1 | EGAT Pelletizing Plant1 | 35549128.54 | 36971093.6816 | 0 | 36971093.6816
MDF Factory | mdf factory ipc 32 | 32 | MDF Factory32 | 2754000 | 2726460 | 0 | 2726460
Air Defence College | IPC018 TR46 | 18 | Air Defence College18 | 330011.54 | 298679.8 | 0 | 298679.8
U7-SEASHELL | IPC012TR0064 | 12 | U7-SEASHELL12 | 24350.2 | 21028.83 | 0 | 21028.83
Air Defense College | Air Def Elic IPC1 | 1 | Air Defense College1 | 102970206 | 16646860 | 68500000 | 85146860
Capital One | inv ( 9 ) Captal one | 9 | Capital One9 | 629166.35 | 427706.6285 | 195168.059 | 622874.6875
Quarry Bridge | inv ( 2 ) MAHGER Br | 2 | Quarry Bridge2 | 548000 | 405646 | 0 | 405646
EL Baragil Bridge | inv ( 2 ) Baragill B | 2 | EL Baragil Bridge2 | 446414.15 | 419629.3 | 0 | 419629.3
Port Said Port Silos | port said silosipc13 | 13 | Port Said Port Silos13 | 612060 | 535282.8844 | 61206 | 596488.8844
Tarek Abdel-Hakim Center | TAH ipc 5 | 5 | Tarek Abdel-Hakim Center5 | 1271012.98 | 978044.48 | 114391.17 | 1092435.65
Faculty of Medicine | Mansora Finish ipc02 | 2 | Faculty of Medicine2 | 4554326.67 | 3397808.9835 | 683149 | 4080957.9835
NUCA R05 - Z02 | R05(2) ipc 27 | 27 | NUCA R05 - Z0227 | 15628361.76 | 11664288.388 | 1490079.6 | 13154367.988
HST El Mahager Bridge | mahager bridge ipc06 | 6 | HST El Mahager Bridge6 | 12916195.24 | 11444643.79 | 0 | 11444643.79
EMAAR-Pkg#162/163- Marassi | Emar Pkg#177 ipc 47 | 47 | EMAAR-Pkg#162/163- Marassi47 | 6785617.6 | 4548162.03 | 500000 | 5048162.03
Lekela 250MW Wind Farm | Lekela 2 ipc 1=3 | 1 | Lekela 250MW Wind Farm1 | 15655160.98 | 3000357.339 | 13281010.08 | 16281367.419
EL Sewedy University Tec. | INV (1 ) S.UNI | 1 | EL Sewedy University Tec.1 | 552921.6 | 459695.04 | 0 | 459695.04
Astoria Sharm elSheikh | astoria sharm-IPC5 | 5 | Astoria Sharm elSheikh5 | 314831.49 | 278242.2245 | 16125.22 | 294367.4445
SSC Suez Steel Company Project | New Gas ipc 3 | 3 | SSC Suez Steel Company Project3 | 1936661.4 | 1336296.366 | 580998.42 | 1917294.786
SSC Suez Steel Company Project | New Gas sta ipc2 | 2 | SSC Suez Steel Company Project2 | 2057036.6 | 1419355.254 | 617110.98 | 2036466.234
U7-SEASHELL | IPC10TR0064 | 10 | U7-SEASHELL10 | 235112.74 | 199846.01 | 0 | 199846.01
Egyptian Exchange Building | Egyptian exch IPC4 | 4 | Egyptian Exchange Building4 | 35233128.57 | 1076790 | 0 | 27908290
SSC Suez Steel Company Project | Revamp ipc 7 | 7 | SSC Suez Steel Company Project7 | 4571797.25 | 3154540.11 | 1371539.17 | 4526079.28
Koumassi Flyover | INV 2 | 2 | Koumassi Flyover2 | 282048968 | 253844034 | 0 | 253844034
AIRDEFNSE -EPOXY | IPC06TR0066 | 6 | AIRDEFNSE -EPOXY6 | 127428 | 108186.37 | 0 | 108186.37
Luxor North Axis Bridge-Off | IPC no5 luxor off | 5 | Luxor North Axis Bridge-Off5 | 672192 | 672192 | 0 | 672192
Ora Zed Landscape Ph1 | Ora Landscape ipc 11 | 11 | Ora Zed Landscape Ph111 | 6460754.42 | 5312426.17 | 678379.21 | 5990805.38
HST El Mahager Bridge | el mahager ipc 07 | 7 | HST El Mahager Bridge7 | 1393130.24 | 234090.6 | 0 | 1234090.6
Katameya Creeks - RME | IPC009 TR53 | 9 | Katameya Creeks - RME9 | 24448.35 | 21649.0135 | 0 | 21649.0135
R05 (New) | tr0059 IPC002 | 2 | R05 (New)2 | 33748.3667 | 74543 | 0 | 29298.0667
EIPICO C002-23 | IPC02 TR68 | 2 | EIPICO C002-232 | 71999.09 | 61782.42 | 0 | 61782.42
ORA ZED TOWER #2 | IPC001 TR49 | 1 | ORA ZED TOWER #21 | 33000 | 29221.5 | 0 | 29221.5
October Under-Railway Tunnel | october tunnel ipc8 | 8 | October Under-Railway Tunnel8 | 5216969.9 | 4696818.58 | 0 | 4696818.58
ORA ZED - Ph 01B - Pkgs A&D | ORA ph.1 IPC19 | 19 | ORA ZED - Ph 01B - Pkgs A&D19 | 21493163.81 | 17518053.2705 | 2068970.4 | 19587023.6705
Air Defence College | IPC22TR0046 | 22 | Air Defence College22 | 278157.9 | 236156.05 | 0 | 236156.05
Irrigation Tank | IPC05TR0061 | 5 | Irrigation Tank5 | 1272596.7 | 1016514.34 | 0 | 1016514.34
Waldorf Astoria Cairo | Waldorf astori ipc24 | 24 | Waldorf Astoria Cairo24 | 10000000 | 22455841.54 | 0 | 22455841.54
El-Warraq | inv 1.2 d0081 | 1 | El-Warraq1 | 1415294 | 1149573.6 | 0 | 1149573.6
El Zomor Axis (2) - Leaaba | IPC#1#LEABA | 1 | El Zomor Axis (2) - Leaaba1 | 352000 | 274596 | 0 | 274596
Egyptian Exchange Building | Egy Ex awnash IPC1 | 1 | Egyptian Exchange Building1 | 7063290.48 | 5385220 | 0 | 5385220
Kattmeya Creeks Urban | IPC07TR0071 | 7 | Kattmeya Creeks Urban7 | 103122.42 | 91314.91 | 0 | 91314.91
HSR | HSR-OCT-5 | 5 | HSR5 | 36253472.15 | 0 | 36862391.5075 | 36862391.5075
HSR | HSR - OCT 3 |  | HSR | 39650249.66 | 5947537.45 | 22750962.593 | 28698500.043
New Giza Teaching Hospital | New Giza Hosp ipc 22 | 22 | New Giza Teaching Hospital22 | 12179338.16 | 7290216.108 | 1844615.96 | 11134832.068
Wady El Natroon Bridge | wady elnatron ipc8 | 8 | Wady El Natroon Bridge8 | 11709710.48 | 1980.8 | 0 | 10439980.8
MDF Factory | Mdf Factory ipc 35 | 35 | MDF Factory35 | 8184195.01 | 11964736.84 | 3437361.19 | 15402098.03
Roof-Playa Cluster A,B,C | IPC06TR0088 | 6 | Roof-Playa Cluster A,B,C6 | 326911 | 282320.34 | 0 | 282320.34
Sixty Iconic Tower | Inv ( 5 ) sixty | 5 | Sixty Iconic Tower5 | 1765230 | 1659316.2 | 0 | 1659316.2
Seashell Playa 5 Villas | Playa c234 - ipc 4 | 4 | Seashell Playa 5 Villas4 | 56708.36 | 51808.76 | 0 | 51808.76
MDF Factory | MDF Equip ipc 21 | 21 | MDF Factory21 | 594425.9 | 600370.156 | 0 | 600370.156
HST Bridges-Sokhna & Mahager | Sokhna ipc17+18+19 | 17 | HST Bridges-Sokhna & Mahager17 | 17594286.57 | 13930069.0043 | 0 | 15142069.0043
Roof-Playa Cluster A,B,C | IPC01TR0088 | 1 | Roof-Playa Cluster A,B,C1 | 1326588 | 1145641.39 | 0 | 1145641.39
3A-L2M Building | ACUD Mar.24 |  | 3A-L2M Building | 22281960.78 | 18337374.889 | 1000000 | 19337374.889
Sixty Iconic Tower | Inv ( 7 ) sixty | 7 | Sixty Iconic Tower7 | 1771175 | 893857.65 | 0 | 893857.65
Kattameya Creeks | Katameya creek ipc37 | 37 | Kattameya Creeks37 | 60819348.36 | 62109565 | 890952.21 | 63000517.21
EGAT Injection | IPC14TR0048 | 14 | EGAT Injection14 | 98815.4 | 84793.5 | 0 | 84793.5
Mohamed Ali Palace Restoration | Mohamed aly271 IPC1 | 1 | Mohamed Ali Palace Restoration1 | 4604016.19 | 1277660 | 2547414.15 | 3825074.15
Ministries Buildings | Mini Fit out IPC5 | 5 | Ministries Buildings5 | 2752100 | 2318220 | 0 | 2318220
Tarek AbdelHakim Center - KSA | K0001-3 | 3 | Tarek AbdelHakim Center - KSA3 | 15666254.07 | 0 | 0 | 18016192.18
R05 (New) | IPC07TR0059 | 7 | R05 (New)7 | 53504.78 | 45377.4 | 0 | 45377.4
Sultana Malak Restoration | Sultana malak22 IPC2 | 2 | Sultana Malak Restoration2 | 77855043.81 | 16986360 | 43648959.61 | 60635319.61
Faculty of Medicine | mansora finish ipc18 | 18 | Faculty of Medicine18 | 14334453.33 | 10672749 | 2150168 | 12822917
EL Baragil Bridge | inv ( 4 ) Baragill B | 4 | EL Baragil Bridge4 | 3105830 | 828921.2 | 0 | 828921.2
Koumassi Flyover | INV 3 | 3 | Koumassi Flyover3 | 357151711 | 321436537 | 0 | 321436537
SSC Suez Steel Company Project | R.o 500:800 sup ipc8 | 8 | SSC Suez Steel Company Project8 | 4444683.99 | 1418034.9086 | 3604458 | 5022492.9086
Roof-Playa Cluster A,B,C | IPC03TR0088 | 3 | Roof-Playa Cluster A,B,C3 | 84568 | 73032.92 | 0 | 73032.92
SSC Suez Steel Company Project | Shutdown SMP2 IPC 3 | 3 | SSC Suez Steel Company Project3 | 1490218.8 | 730207.212 | 745109.4 | 1475316.612
SSC Suez Steel Company Project | SVC- ipc 1 | 1 | SSC Suez Steel Company Project1 | 3212437.04 | 2216581.5616 | 963731.11 | 3180312.6716
U4,U8 Seashell Playa | IPC14TR0060 | 14 | U4,U8 Seashell Playa14 | 131368.7 | 113450 | 0 | 113450
Main Spine | IPC01TR0096 | 1 | Main Spine1 | 870899.98 | 752109.22 | 0 | 752109.22
NUCA R05 - Z02 | R05(2) ipc 41 | 41 | NUCA R05 - Z0241 | 13676567.6 | 20810136.565 | 2582936.8 | 23393073.365
NUCA R05 - Z02 | R05(2)IPC48 | 48 | NUCA R05 - Z0248 | 13607864.7 | 12385600.7 | 1665704.42 | 14051305.12
Hosh Eisa Hospital | IPC02TR0086 | 2 | Hosh Eisa Hospital2 | 222500.25 | 190927.47 | 0 | 190927.47
ORA ZED - Ph 01B - Pkgs A&D | ora zed ipc 24 | 24 | ORA ZED - Ph 01B - Pkgs A&D24 | 10139035.7 | 8591385.3318 | 1085626.55 | 9677011.8818
Maspiro Towers | IPC#2 | 2 | Maspiro Towers2 | 702000 | 694980 | 0 | 696735
EGAT Pelletizing Plant | Egat Water tan ipc14 | 14 | EGAT Pelletizing Plant14 | 1893022.3 | 2909387.535 | 0 | 2909387.535
Port Said Grain Storage | IPC6 PORT SAID | 6 | Port Said Grain Storage6 | 300300 | 89493.48 | 0 | 99503.68
MDF Factory | MDF Factory ipc 38 | 38 | MDF Factory38 | 25020067.65 | 9539881.65 | 10508616.79 | 20048498.44
EGAT Pelletizing Plant | Pelletizing ipc 21 | 21 | EGAT Pelletizing Plant21 | 37437141.5 | 38934627.165 | 0 | 38934627.165
HST Bridges-Sokhna & Mahager | sokhna bri.esc19 |  | HST Bridges-Sokhna & Mahager | 2260344.86 | 2014925.441 | 0 | 2014925.441
ZED Phase 2 | IPC11TR0062 | 11 | ZED Phase 211 | 38142.25 | 28102.83 | 0 | 28102.83
Qani bay Al rammah Mosque | Qani bay IPC1 | 1 | Qani bay Al rammah Mosque1 | 8571603.81 | 6624100 | 0 | 6624100
Al-Parco | INV ( 7 ) ALparco | 7 | Al-Parco7 | 2823676 | 54255.44 | 0 | 54255.44
PLAYA ROOF & Wet Areas | IPC25TR0041 | 25 | PLAYA ROOF & Wet Areas25 | 27822.02 | 23874.08 | 0 | 23874.08
U3 & U5 | IPC21TR0055 | 21 | U3 & U521 | 556690.63 | 400758.03 | 0 | 400758.03
Port Said Port Silos | supply egp ipc6 | 6 | Port Said Port Silos6 | 1064494.36 | 12030748.852 | 532334.65 | 2512616.7004
Wady El Natroon Bridge | ipc4 wady elnatroon | 4 | Wady El Natroon Bridge4 | 11433601.9 | 10274726.196 | 0 | 10274726.196
RING ROAD MARYOTIA EXPANSION | El-Marg IPC08 | 8 | RING ROAD MARYOTIA EXPANSION8 | 4234352.07 | 3742255.05 | 0 | 3742255.05
HST El Mahager Bridge | El Mahager ipc08 | 8 | HST El Mahager Bridge8 | 47025180.48 | 41625139.7 | 0 | 41625139.7
El Khatatba Bridge | EL KHATATBA IPC03 | 3 | El Khatatba Bridge3 | 16420583.33 | 16256377.4965 | 0 | 16256377.4965
Port Said Port Silos | PORT SAID IPC26 | 26 | Port Said Port Silos26 | 2227046.78 | 426108.0312 | 222704.68 | 648812.7112
Luxor North Axis Bridge-Off | IPC#1 Luxor offshore | 1 | Luxor North Axis Bridge-Off1 | 1644720 | 1537678.4 | 0 | 1537678.4
Luxor North Axis Bridge | IPC#2-Luxor onshore | 2 | Luxor North Axis Bridge2 | 843750 | 818437 | 0 | 818437
Jawhara Palace Restoratio | Gawhara IPC5 | 5 | Jawhara Palace Restoratio5 | 2268323.02 | 1542000 | 567080.76 | 2109080.76
Creeks URBN-K | U-rbnk ipc (4) | 4 | Creeks URBN-K4 | 25969563.12 | 8830426 | 16931112.88 | 25761538.88
Koumassi Flyover | INV no.9 | 9 | Koumassi Flyover9 | 1174417959.9 | 1153318675.27 | 0 | 1153318675.27
Jawhara Palace Restoratio | Gawhara IPC1 | 1 | Jawhara Palace Restoratio1 | 1944820.33 | 1321600 | 486205.08 | 1807805.08
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc 35+36 | 35 | ORA ZED-Ph 2-Pkgs A&D35 | 7262978.01 | 3820917.5505 | 10380361.56 | 14201279.1105
ORA ZED-Ph 2-Pkgs A&D | Ora Ph2 ipc 33+34 | 33 | ORA ZED-Ph 2-Pkgs A&D33 | 7988113.29 | 5000134.02 | 838751.9 | 5838885.92
Air Defense College | Air dev 27 IPC1 | 1 | Air Defense College1 | 72686330 | 6332230 | 54350990 | 60683220
Senator | Inv ( 4 ) Sentor | 4 | Senator4 | 147888 | 122000 | 0 | 122000
El Taameer Axis Expansion | FPC - Taamer Axis |  | El Taameer Axis Expansion | 568601 | 542548.57 | 0 | 542548.57
Port Said Port Silos | port said ipc 31 | 31 | Port Said Port Silos31 | 3155732.38 | 2284436.52 | 315573.24 | 2600009.76
Port Said Port Silos | port said supp.9 |  | Port Said Port Silos | 3231641.7 | 20233176 | 2585313.36 | 2852311.17
SSC Suez Steel Company Project | L7776/2022 |  | SSC Suez Steel Company Project | 10000000 | 7082500 | 0 | 7082500
Faculty of Medicine | MANSOURA FINISHIPC24 | 24 | Faculty of Medicine24 | 5200547.62 | 3879988 | 780082.14 | 4660070.14
SSC Suez Steel Company Project | Shutdown smp1 ipc 3 | 3 | SSC Suez Steel Company Project3 | 770000 | 333693.13 | 384999.87 | 718693
Wady El Natroon Bridge | WADY ELNATROON IPC10 | 10 | Wady El Natroon Bridge10 | 9636546.67 | 8591548.13 | 0 | 8591548.13
VILLA CLUSTER C | IPC07TR0078 | 7 | VILLA CLUSTER C7 | 24246.87 | 20939.6 | 0 | 20939.6
El Taameer Axis Expansion | IPC#5 - Taamer Axis | 5 | El Taameer Axis Expansion5 | 806355 | 778938.93 | 0 | 778938.93
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc 25 | 25 | ORA ZED-Ph 2-Pkgs A&D25 | 1429471.43 | 1086725.0887 | 150094.5 | 1236819.5887
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 29 | 29 | ORA ZED-Ph 2-Pkgs A&D29 | 7868267.11 | 5059481.7155 | 652009.74 | 5711491.4555
Port Said Port Silos | PORT SAID IPC 33 | 33 | Port Said Port Silos33 | 4525360.97 | 2711136 | 452536.1 | 3163672.1
Rabigh PP - Piling Works | K0004 Inv-06 | 6 | Rabigh PP - Piling Works6 | 1751171.77 | 6041514.12 | 0 | 2013838.04
Koumassi Flyover | INV no.12 | 12 | Koumassi Flyover12 | 1141878222.44 | 1027690400.19 | 0 | 1027690400.19
Abou Ghaleb Bridge | abou ghaleb ipc25+26 | 25 | Abou Ghaleb Bridge25 | 3342110.29 | 3057591.05 | 0 | 3057591.05
KATAMYA GREEKS LAND SCAPE STAR | IPC05TR0081 | 5 | KATAMYA GREEKS LAND SCAPE STAR5 | 1438507.13 | 1422108.1465 | 0 | 1422108.1465
Damietta Container Termin | Damietta PKG#3 IPC 2 | 2 | Damietta Container Termin2 | 1592229.98 | 1496696.18 | 0 | 1496696.18
October Under-Railway Tunnel | october tunnel ipc9 | 9 | October Under-Railway Tunnel9 | 6996014.86 | 6298618.2 | 0 | 6298618.2
U7-SEASHELL | IPC23TR0064 | 23 | U7-SEASHELL23 | 276276.03 | 159591.78 | 0 | 159591.78
EDNC Hardscape Package | Haedescape ipc final |  | EDNC Hardscape Package | 14588321.68 | 4532604.51 | 0 | 11805658.06
EPICO 3 Facility | Eipico ipc 19 | 19 | EPICO 3 Facility19 | 35463786.32 | 22436578.356 | 0 | 22436578.356
Hosh Eisa | IPC03TR0091 | 3 | Hosh Eisa3 | 61151.5 | 52474.09 | 0 | 52474.09
Katameya Creeks - RME | IPC22TR0053 | 22 | Katameya Creeks - RME22 | 116200.85 | 100895.86 | 0 | 100895.86
MDF Factory - Sadat | IPC01TR0093 | 1 | MDF Factory - Sadat1 | 331476.6 | 284440.07 | 0 | 284440.07
Coastal road Bridge Extension | IPC#8 -Coastal Roa | 8 | Coastal road Bridge Extension8 | 952560 | 917315.28 | 0 | 917315.28
Coastal road Bridge Extension | IPC#2 Gharably | 2 | Coastal road Bridge Extension2 | 1797850 | 1667329.55 | 0 | 1667329.55
Wady El Natroon Bridge | WADYELNATRON ESC1:8 |  | Wady El Natroon Bridge | 6190476.19 | 911603 | 0 | 5979603
Wady El Natroon Bridge | wadyelntron13+14+15 |  | Wady El Natroon Bridge | 47518136.19 | 866773.5 | 0 | 42366773.5
Seashell Playa 5 Villas | Playa c185 - ipc 4 | 4 | Seashell Playa 5 Villas4 | 57833.47 | 49944.99 | 0 | 49944.99
Seashell Playa 5 Villas | playa C469 IPC 9 | 9 | Seashell Playa 5 Villas9 | 23166.2 | 21164.64 | 0 | 21164.64
Faculty of Medicine | IPC25MANSOURAFINISHN | 25 | Faculty of Medicine25 | 4162992.38 | 2738988.36 | 624448.86 | 3363437.22
EL -mahager Bridge Ain sokhna | IPC#1#ElMahager | 1 | EL -mahager Bridge Ain sokhna1 | 946500 | 65719.28 | 0 | 65719.28
ElMoneeb 2 | IPC#5 - Moneeb | 5 | ElMoneeb 25 | 160893 | 159284.07 | 0 | 159284.07
Jawhara Palace Restoratio | GAWHARA IPC8 | 8 | Jawhara Palace Restoratio8 | 1389436.83 | 823726.96 | 347359.21 | 1171086.17
Roof-Playa Cluster A,B,C | IPC12&13TR0088 | 12 | Roof-Playa Cluster A,B,C12 | 418018.9 | 0 | 0 | 0
Seashell Playa 5 Villas | Playa C470- ipc 8 | 8 | Seashell Playa 5 Villas8 | 176010.2 | 152002.4 | 0 | 152002.4
Capital One | inv (12 ) Captal one | 12 | Capital One12 | 911829.3 | 161150.005 | 0 | 161150.005
Cairo Monorail - 6th October | IPC#10 Monorail | 10 | Cairo Monorail - 6th October10 | 921600 | 912384 | 0 | 912384
Seashell Playa 5 Villas | Cr 20/12/2023 |  | Seashell Playa 5 Villas | 0 | 0 | 0 | #DIV/0!
Daraw Bridge | D0033-OB-Dec-2020/Cr | 2020 | Daraw Bridge2020 | 0 | 0 | 0 | #DIV/0!
Canal Sugar OHTL | Inv.11 Sugar OHTL | 11 | Canal Sugar OHTL11 | 604632.9 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Deductions inv.29 | 29 | South Helwan PP (CP-117)29 | 0 | 0 | 0 | #DIV/0!
South Dabaa Axis | IPC#5# South Dabaa | 5 | South Dabaa Axis5 | 110000 | 0 | 0 | #DIV/0!
New Capital | Credit memo inv 5 El | 5 | New Capital5 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 17 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 168175.4286 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR-5-Euro-South he | 5 | South Helwan PP (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Alamein | CR-ipc1 elalamin | 1 | Alamein1 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | Cr-Lahoon Sub Inv 02 | 2 | Lahoon 220/22/222 | 0 | 0 | 0 | #DIV/0!
Benban 500 K.V / 100 K.M | تشيد بنبان |  | Benban 500 K.V / 100 K.M | 5000 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | Cr. Adj Inv 19 | 19 | Barwa 2x60/22 KV S/S19 | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | cr.soci 72 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Re Soc Inv.3 Temmay | 3 | Beni Seuf - 3583 | 154841 | 0 | 0 | #DIV/0!
Playa Resort | 41 |  | Playa Resort | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 249 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Monoril | inv ( 3 ) monoril | 3 | Monoril3 | 273420 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10105 |  | AWEER POWER STATION 'H' Phase | 2395684.97 | 0 | 0 | #DIV/0!
Playa Resort | 6 |  | Playa Resort | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 180067 |  | South Helwan PP (CP-117) | -13638.44 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | IPC#5#draw | 5 | Aswan axis - Daraw5 | 144552 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_INV.8 | 8 | Akhmem - Qena8 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr. Inn 49 Ass |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | 6 |  | Barwa 2x60/22 KV S/S | 1126765.27 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 28 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Rail Way Tunnel Zagazig | D0025-OB-Dec-2020/Cr | 2020 | Rail Way Tunnel Zagazig2020 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 7 Euro-South Helwan |  | South Helwan PP (CP-117) | 20918.1048 | 0 | 0 | #DIV/0!
Port Said Grain Storage | Rent-008 | 8 | Port Said Grain Storage8 | 166650 | 0 | 0 | #DIV/0!
Wadi Halfa Port | cr-wadi halfa ipc01 | 1 | Wadi Halfa Port1 | 0 | 0 | 0 | #DIV/0!
Aljazi Project | Cr. Al - Jazi Inv. 2 | 2 | Aljazi Project2 | 0 | 0 | 0 | #DIV/0!
Get Business Complex | C r .INV ( 15 ) GET | 15 | Get Business Complex15 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | inv.5 cancl | 5 | Ghana Street lighting5 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ret Asuit akh 4 |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | cr-kafr shokr ipc09 | 9 | Kafr Shokr Bridge9 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 83 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Parco | INV ( 13 ) ALparco | 13 | Al-Parco13 | 394596 | 0 | 0 | #DIV/0!
ACWA POWER & NOMAC HQ | Acwa power ipc 3 | 3 | ACWA POWER & NOMAC HQ3 | 30565.84 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180083 |  | Suez Gulf Substation | 310156.26 | 0 | 0 | #DIV/0!
Sokhna Port Expansion | cr-ipc14 sokhna port | 14 | Sokhna Port Expansion14 | 0 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 05 | 5 | Suez Gulf/S4 - 500KV OHTL5 | 231265.09 | 0 | 0 | #DIV/0!
Solar ITS | P-06-EGY اتحاد تشيد | 6 | Solar ITS6 | 5000 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | rev.( 5 Euro-So. Hel |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 40 |  | Governmental Campus-N2 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 59 |  | Suez Gulf Substation | 1954696.02 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,11usd Borg Ar | 11 | Marsa Matrouh 500KV11 | 0 | 0 | 0 | #DIV/0!
Ministries Buildings | CR-MINI-IPC05+ | 5 | Ministries Buildings5 | 0 | 0 | 0 | #DIV/0!
Al-Wukair 11 Substation | inv(ESC-SA-Civil-08) | 8 | Al-Wukair 11 Substation8 | 2169739.56 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 477 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | DR. 13 Oewon Mousa |  | Beni Seuf - 358 | 4940.63 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen-akh 5 |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
LP-03-22 IIoT - UIC | 90 |  | LP-03-22 IIoT - UIC | 6750 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr. Egytec |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11585 |  | FURJAN Cable Works | 1227202.49 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 2 |  | Zafranaa - Ras Ghareb | 50000 | 0 | 0 | #DIV/0!
New Capital | Edit inv 5 | 5 | New Capital5 | 265.33 | 0 | 0 | #DIV/0!
Al-Parco | crINV ( 3 )ALparco | 3 | Al-Parco3 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 61 |  | Suez Gulf Substation | 777135.78 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr. Socil 4-8:19 ass | 8 | Akhmem Assiut8 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr Soc Inv 49 Asuit | 49 | Akhmem Assiut49 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply. Inv.4 Ret | 4 | Ghana Street lighting4 | 21465.37 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 105 |  | Al-Shabab PP Phase II (CP-117) | 203669103.2878 | 0 | 0 | #DIV/0!
HST Bridge - Arab Contractors | IPC#1#D0083 HST | 1 | HST Bridge - Arab Contractors1 | 684550 | 0 | 0 | #DIV/0!
U3 & U5 | 55-CR2F |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | اتحاد تشيدو بناءP-81 | 81 | Lahoon 220/22/2281 | 5000 | 0 | 0 | #DIV/0!
Palm Hill-Infra Str(Elec.Work) | DEC ADJ 106 |  | Palm Hill-Infra Str(Elec.Work) | 0 | 0 | 0 | #DIV/0!
Zayed Monorail 66/22 KV GIS | P-29-EGY اتحاد تشيد | 29 | Zayed Monorail 66/22 KV GIS29 | 5000 | 0 | 0 | #DIV/0!
Closed | OB-ST-Ismailya B |  | Closed | 586996.5 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | 11-07-2018 | 7 | Siemens 6x500/220 KV GIS-MOU7 | 0 | 0 | 0 | #DIV/0!
Business District Hyde Park | CR-4HY Bark | 4 | Business District Hyde Park4 | 0 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 26 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2103210012 |  | Miscellaneous Projects | -10500 | 0 | 0 | #DIV/0!
Cairo North PP Rehabilitation | CN last Inv Cairo N |  | Cairo North PP Rehabilitation | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR- 19 EGP- Shabab | 19 | Al-Shabab PP Phase II (CP-117)19 | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | Cr-Egy Ex IPC1 | 1 | Egyptian Exchange Building1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 244 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Celia | CR-IPC#1 | 1 | Celia1 | 0 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 22 ) GET | 22 | Get Business Complex22 | 1989686.7 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cr . Adj Inv. 15 | 15 | Abou El Matameer and Sammanoud15 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 248 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
ZED Phase 2 | IPC05TR0062 | 5 | ZED Phase 25 | 93654.83 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 452 |  | TZ – Offshore E&M Procurement | 274863.23 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | ADJUST TAX OF INV.32 | 32 | South Helwan PP (CP-117)32 | 0 | 10785.57 | 0 | 10785.57
marassi inland marina | D0029-OB-Dec-2020/Cr | 2020 | marassi inland marina2020 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen-akh 6 |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | Reduction inv no 210 | 210 | MAYSAN 400/132kV SS210 | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr. Ref Retention Ma |  | Marsa Matrouh 500KV | 0 | 0 | 0 | #DIV/0!
Air Defence College | Cancel IPC11 TR46 | 11 | Air Defence College11 | -190510.2 | 0 | 0 | #DIV/0!
El Boghaz Brigde | IPC#27/28 | 27 | El Boghaz Brigde27 | 1276221.84 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 74 |  | W Dam PP Phase II (CP-117) | -49628984.48 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | IPC NRCC 3 |  | Expansion of Ring Road NRCC | 0 | 0 | 0 | #DIV/0!
Central Capital | Cr.INV ( 5 ) Central | 5 | Central Capital5 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | credit Ref. Inst |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | inv.5 cancle | 5 | Ghana Street lighting5 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 15 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 537 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
LAYAN Substation | 11460 |  | LAYAN Substation | 0 | 0 | 0 | #DIV/0!
Wadi El Natroun | IPC#5#Wadi Elnatron | 5 | Wadi El Natroun5 | 745809 | 0 | 0 | #DIV/0!
U3 & U5 | TR55-CR1 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 251 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | Re soc Inv 24. Quna | 24 | Akhmem - Qena24 | 588.61 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | Cr - 5 USD - West D. | 5 | W Dam PP Phase II (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 5 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 978219.9238 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 21 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 362995.381 | 0 | 0 | #DIV/0!
Racecores 3092-15 132KV A | 11521 |  | Racecores 3092-15 132KV A | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | Adjust billing |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | inv ( 4 ) final CR | 4 | Al-Ula Towers4 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR -15-West D. 117 | 15 | W Dam PP Phase II (CP-117)15 | 0 | 0 | 0 | #DIV/0!
Road El Farag Axis | D0006-OB-Dec-2020/Cr | 2020 | Road El Farag Axis2020 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | CN Q3 Beni Suef |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 24 ) GET | 24 | Get Business Complex24 | 240090.71 | 0 | 0 | #DIV/0!
Akhmem - Qena | Cr Adj Inv 10 | 10 | Akhmem - Qena10 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 90 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
ENR-Signaling Inst. | P-42-EGY اتحاد تشيد | 42 | ENR-Signaling Inst.42 | 5000 | 0 | 0 | #DIV/0!
Al-Ula Towers | inv ( 4 ) final CR2 | 4 | Al-Ula Towers4 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Ins.Inv.2Ret. | 2 | Ghana Street lighting2 | 20145.78 | 0 | 0 | #DIV/0!
Containment Data Center- | 48 |  | Containment Data Center- | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 77 |  | Governmental Campus-N2 | 460454.41 | 0 | 0 | #DIV/0!
Strining Lot A- Elegect | Elegict |  | Strining Lot A- Elegect | 0 | 0 | 0 | #DIV/0!
P.I.Parks - Plot 10 | P-33-EGY اتحاد تشيد | 33 | P.I.Parks - Plot 1033 | 5000 | 0 | 0 | #DIV/0!
Kayan 3 New Cairo Capital City | CR ARMY/KYAN/1446 |  | Kayan 3 New Cairo Capital City | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial P - East | Cr Adj inv 4 | 4 | Pyramids Industrial P - East4 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 3 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 1188435.9048 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 6 USD - Suez Gulf |  | Suez Gulf Substation | 371737.6 | 0 | 0 | #DIV/0!
Canal Sugar S/s | Inv 6 $ Sugar S/s | 6 | Canal Sugar S/s6 | 1443919.39 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 207 |  | MAYSAN 400/132kV SS | -4798431.61 | 0 | 0 | #DIV/0!
El Katameya Mall | CRinv ( 13 )10-2020 | 13 | El Katameya Mall13 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 13 USD- Suez Gulf |  | Suez Gulf Substation | 90935.77 | 0 | 0 | #DIV/0!
Ghana Street lighting | Pole.Cvr.Inv.2.Cncl | 2 | Ghana Street lighting2 | 0 | 0 | 0 | #DIV/0!
Kayan 3 New Cairo Capital City | 30/11/22 Armed force |  | Kayan 3 New Cairo Capital City | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange building | FINALTR0039 |  | Egyptian Exchange building | 474028.93 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 86 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv 04 | 4 | MOC HQ at Diriyah4 | 16246137.77 | 0 | 0 | 23353823.04
Air Defence College | IPC26TR0046. | 26 | Air Defence College26 | 4159.68 | 0 | 0 | 4159.68
Open Channel 2 | IPC02TR0099(02) | 2 | Open Channel 22 | 2440060 | 0 | 0 | 2440060
MAF HQ Renovation | maf Po.0020024000370 |  | MAF HQ Renovation | 80510.4 | 0 | 0 | 95553.717
Residence 8 ( S05 ) | Inv ( 1 ) S 05 | 1 | Residence 8 ( S05 )1 | 69311.35 | 0 | 0 | 69311.35
TOSHKA MADKOUR | IPC01TR0083 | 1 | TOSHKA MADKOUR1 | 1127761.2 | 0 | 0 | 1127761.2
Port Said Port Silos | port said EUR ipc01 | 1 | Port Said Port Silos1 | 5539353.23 | 0 | 0 | 5539353.23
Ain Sokhna Bridge | Inv ( 5 ) A.S | 5 | Ain Sokhna Bridge5 | 333124.5 | 0 | 0 | 333124.5
Open Channal | IPC01TR0074 | 1 | Open Channal1 | 294368.26 | 0 | 0 | 294368.26
Waldorf Astoria Cairo | Waldorf Asto ipc(20) | 20 | Waldorf Astoria Cairo20 | 3956218.97 | 0 | 0 | 4154029.9185
EL Sewedy University Tec. | INV ( 2 ) S.UNIV | 2 | EL Sewedy University Tec.2 | 140678.4 | 0 | 0 | 140678.4
Sokhna Port Expansion | ipc14 sokhna port ex | 14 | Sokhna Port Expansion14 | 14245622.5 | 0 | 0 | 14245622.5
British International School | Bis ipc (2) | 2 | British International School2 | 11138109 | 0 | 0 | 12697444.26
Cairo-Alex Railway | CAIRO-ALEX IPC40 | 40 | Cairo-Alex Railway40 | 21031085.3 | 0 | 0 | 22082639.565
Al-Ula Towers | inv ( 5 ) FINAL Ola | 5 | Al-Ula Towers5 | 544770 | 0 | 0 | 572008.5
U3 & U5 | TR55-IPC1 | 1 | U3 & U51 | 741275.46 | 0 | 0 | 741275.46
U3 & U5 | TR55-IPC2 | 2 | U3 & U52 | 439984.49 | 0 | 0 | 439984.49
U3 & U5 | TR55/IPC/03 | 3 | U3 & U53 | 34000.72 | 0 | 0 | 34000.72
U3 & U5 | TR55/IPC/02 | 2 | U3 & U52 | 439984.49 | 0 | 0 | 439984.49
Wadi Halfa Port | wadi halfa ipc01 | 1 | Wadi Halfa Port1 | 31456682.86 | 0 | 0 | 33029517.003
Seashell Playa 5 Villas | seashell playa- IPC1 | 1 | Seashell Playa 5 Villas1 | 161096.6 | 0 | 0 | 169151.43
Egyptian Exchange Building | Egy Ex IPC1 | 1 | Egyptian Exchange Building1 | 185780585 | 0 | 0 | 185780585
Kafr Shokr Bridge | م 10 كفر شكر | 10 | Kafr Shokr Bridge10 | 2706642.86 | 0 | 0 | 2841975.003
Ministries Buildings | minis MEP05+ |  | Ministries Buildings | 121861476.8 | 0 | 0 | 121861476.8
Racecores 3092-17 132KV E | 11768 |  | Racecores 3092-17 132KV E | 12214.2857 | 0 | 0 | 12825
Infra Project 4428 | 2112210003 |  | Infra Project 4428 | 134285714.29 | 141000000.0045 | 0 | 141000000.0045
Assuit PP (CP-118) | 220621002 |  | Assuit PP (CP-118) | 820286.39 | 0 | 0 | 861300.7095
FURJAN Cable Works | 11560 |  | FURJAN Cable Works | 1227202.49 | 0 | 0 | 1288562.6145
Racecores 3092-15 132KV A | 11497 |  | Racecores 3092-15 132KV A | 3551.62 | 0 | 0 | 3551.62
Racecores 3092-17 132KV E | 11447 |  | Racecores 3092-17 132KV E | 5152.88 | 0 | 0 | 5152.88
Beni Seuf - 358 | Inv. 11 Oewon Mousa | 11 | Beni Seuf - 35811 | 20054291.17 | 0 | 3449628.8 | 3473303.99
Infra Project 2524 | 220221001 |  | Infra Project 2524 | 91421211.43 | 0 | 0 | 95992272
Ministries Buildings | Minist SHELL IPC08 | 8 | Ministries Buildings8 | 26226263.88 | 0 | 0 | 26226263.88
Miscellaneous Projects | 2010210003 |  | Miscellaneous Projects | 37075635 | 0 | 0 | 37075635
Toshka GIS 500 kV | Toshka Sub Inv. 24 $ | 24 | Toshka GIS 500 kV24 | 25418.1 | 0 | 0 | 25418.1
Kafr Shokr Bridge | Kafr Shokr-IPC01 | 1 | Kafr Shokr Bridge1 | 32770679.81 | 0 | 0 | 37358574.9834
Ain-Sokhna PP (CP-117) | 2012210038 |  | Ain-Sokhna PP (CP-117) | -687552.29 | 0 | 0 | -687552.29
Assuit PP (CP-118) | 2103210015 |  | Assuit PP (CP-118) | 1405352.19 | 0 | 0 | 1479318.09
El Boghaz Brigde | D0007-OB-Dec-2020 | 2020 | El Boghaz Brigde2020 | 19573481.82 | 0 | 0 | 19573481.82
LRT - El Shorouk Bridge | D0034-OB-Dec-2020 | 2020 | LRT - El Shorouk Bridge2020 | 4118500 | 0 | 0 | 4118500
Minis Building(Polyurethane) | TR0020DEC.Closing |  | Minis Building(Polyurethane) | 3085900.98 | 0 | 0 | 3085900.98
Club House-Sodic Wesset | TR0019DEC.Closing |  | Club House-Sodic Wesset | 117700 | 0 | 0 | 117700
Mohamed Ali Palace | TR0015DEC.Closing |  | Mohamed Ali Palace | 324612.4 | 0 | 0 | 324612.4
El-Moneeb Bridge | D0038-OB-Dec-2020 | 2020 | El-Moneeb Bridge2020 | 2634750 | 0 | 0 | 2634750
Suez Bridge | D0017-OB-Dec-2020 | 2020 | Suez Bridge2020 | 193930 | 0 | 0 | 193930
IRAQ - Al-Diwaniya Power Plant | 2012210030 |  | IRAQ - Al-Diwaniya Power Plant | 192535.65 | 0 | 0 | 192535.65
Miscellaneous Projects | 2012210003 |  | Miscellaneous Projects | 115548.79 | 110085.7301 | 0 | 131725.6206
Aljazi Project | Al - Jazi Inv. 2 | 2 | Aljazi Project2 | 322383 | 151797.77 | 0 | 181638.77
South Helwan PP (CP-117) | 2009210008 |  | South Helwan PP (CP-117) | 239912.09 | 212030.41 | 37857.23 | 249887.64
Miscellaneous Projects | 2009210012 |  | Miscellaneous Projects | 137787.2 | 0 | 0 | 137787.2
Miscellaneous Projects | 2004210003 |  | Miscellaneous Projects | 815592 | 0 | 0 | 929774.88
Siemens 6x500/220 KV GIS-MOU | Compensation Banha |  | Siemens 6x500/220 KV GIS-MOU | 4476190.48 | 0 | 0 | 4700000.004
LAYYAH CCPP | 485 |  | LAYYAH CCPP | 6501455 | 6501455 | 0 | 6501455
Nagaa Hamady/Assuit OHTL | Soc.2020 تشيد نجع |  | Nagaa Hamady/Assuit OHTL | 5000 | 0 | 0 | 5000
Elniger | Close El Niger |  | Elniger | 562545.476 | 0 | 0 | 562545.476
Pyramids Industrial Park | Closing PIP |  | Pyramids Industrial Park | 25345136.15 | 0 | 0 | 25345136.15
Suez Gulf Substation | 11 EGP - Suez Gulf |  | Suez Gulf Substation | 299591.8667 | 283114.31 | 31457.15 | 314571.46
Assuit PP (CP-118) | 1909210017 |  | Assuit PP (CP-118) | 3016678.67 | 2662218.93 | 475126.89 | 3137345.82
Manshiet Nasser Substation | 1907210016 |  | Manshiet Nasser Substation | 1421598.43 | 1504611.48 | 0 | 1504611.48
Manshiet Nasser Substation | 1906210011 |  | Manshiet Nasser Substation | 929969.05 | 984273.81 | 0 | 984273.81
Suez Gulf Substation | 1909210011 |  | Suez Gulf Substation | 601609.45 | 601609.45 | 0 | 601609.45
Suez Gulf Substation | 1909210009 |  | Suez Gulf Substation | 348508.68 | 348508.68 | 0 | 348508.68
Suez Gulf Substation | 1909210008 |  | Suez Gulf Substation | 2533.08 | 2533.08 | 0 | 2533.08
Zambia Project | SCD4/004Adj |  | Zambia Project | 71791.41 | 0 | 0 | 71791.41
Beni Seuf - 358 | Soc inv 4-5 Itay | 4 | Beni Seuf - 3584 | 4122636 | 0 | 0 | 4122636
Phosfat | Inv.6 Phosfat | 6 | Phosfat6 | 1426885 | 0 | 0 | 1426885
South Helwan PP (CP-117) | 1901210011 |  | South Helwan PP (CP-117) | 36546.75 | 41461.55 | 0 | 41461.55
Ethiopia S/S | P-27-09 AccRev | 27 | Ethiopia S/S27 | 103540391.93 | 0 | 0 | 103540391.93
Akhmem Assiut | Soc Inv 48 ASUIT | 48 | Akhmem Assiut48 | 2182603.5 | 0 | 0 | 2182603.5
Manshiet Nasser Substation | 1903210019 |  | Manshiet Nasser Substation | -7593753.66 | -7593753.66 | 0 | -7593753.66
Abu Qir PP (CP-117) | 180151 |  | Abu Qir PP (CP-117) | 735093.49 | 735093.49 | 0 | 735093.49
Akhmem Assiut | Ref.Install.1Assuit |  | Akhmem Assiut | 85910.91 | 0 | 0 | 85910.91
Beni-Suef Power Plant EPC | 180140 |  | Beni-Suef Power Plant EPC | 44018941.66 | 44018941.66 | 0 | 44018941.66
Al-Shabab PP Phase II (CP-117) | 8 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 1178172.06 | 0 | 0 | 1178172.06
Al-Shabab PP Phase II (CP-117) | 7 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 1695411.37 | 0 | 0 | 1695411.37
W Dam PP Phase II (CP-117) | 18 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 368421.1 | 0 | 0 | 368421.1
Suez Gulf Substation | 180060 |  | Suez Gulf Substation | 3136178.1 | 2969263.01 | 329918.11 | 3299181.12
W Dam PP Phase II (CP-117) | 13 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 12764.38 | 12764.38 | 0 | 12764.38
Al-Shabab PP Phase II (CP-117) | 16 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 430785.67 | 430785.67 | 0 | 430785.67
Al-Wukair 11 Substation | 180161 |  | Al-Wukair 11 Substation | 7641356.97 | 7641356.97 | 0 | 7641356.97
Marsa Matrouh 500KV | Inv, 5 usd Borg Arab | 5 | Marsa Matrouh 500KV5 | 1382274.01 | 0 | 0 | 1382274.01
Damac 2x60/22 KV S/S | Adj. iNV. 20 | 20 | Damac 2x60/22 KV S/S20 | 48778576.27 | 0 | 0 | 48778576.27
Barwa 2x60/22 KV S/S | Adj. Inv. 19 | 19 | Barwa 2x60/22 KV S/S19 | 46223782.89 | 0 | 0 | 46223782.89
W Dam PP Phase II (CP-117) | 180112 |  | W Dam PP Phase II (CP-117) | 276348.34 | 0 | 0 | 290711.56
South Helwan PP (CP-117) | 180127 |  | South Helwan PP (CP-117) | 157312.61 | 170906.47 | 0 | 170906.47
Abu Qir PP (CP-118) | 30 |  | Abu Qir PP (CP-118) | 2553558.4572 | 0 | 0 | 2553558.4572
Suez PP (CP-106) | 81 |  | Suez PP (CP-106) | 9471955.02 | 0 | 0 | 9471955.02
Al-Shabab PP Phase II (CP-117) | 180026 |  | Al-Shabab PP Phase II (CP-117) | 678293.2 | 0 | 0 | 712207.86
Al-Shabab PP Phase II (CP-117) | 180022 |  | Al-Shabab PP Phase II (CP-117) | 2073161.5524 | 0 | 0 | 2176819.63
Al-Shabab PP Phase II (CP-117) | 180017 |  | Al-Shabab PP Phase II (CP-117) | 156620.07 | 0 | 0 | 156620.07
Attaqa Power Plant | 119 |  | Attaqa Power Plant | -2694457109.9679 | 0 | 0 | -2694457109.9679
IRAQ - Substations Soil Invest | 39 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
Banha PP (CP-118) | 97 |  | Banha PP (CP-118) | 10569356.3243 | 0 | 0 | 10569356.3243
Ain-Sokhna PP(CP-102) | 114 |  | Ain-Sokhna PP(CP-102) | 699578 | 0 | 0 | 699578
Beni-Suef PP Site Preparation | 18 |  | Beni-Suef PP Site Preparation | 84425984.25 | 0 | 0 | 84425984.25
Beni-Suef Power Plant EPC | 1 |  | Beni-Suef Power Plant EPC | 727472080.7817 | 0 | 0 | 727472080.7817
IRAQ - Al-Diwaniya Power Plant | 21 |  | IRAQ - Al-Diwaniya Power Plant | 507140001 | 0 | 0 | 507140001
Ain-Sokhna PP (CP-117) | 68 |  | Ain-Sokhna PP (CP-117) | 54452776.9989 | 0 | 0 | 54452776.9989
Giza North PP Ph I,II (CP-117) | 85 |  | Giza North PP Ph I,II (CP-117) | 60934040.024 | 0 | 0 | 60934040.024
South Helwan PP (CP-117) | 107 |  | South Helwan PP (CP-117) | 191119874.7274 | 0 | 0 | 191119874.7274
6th Oct. Ph2 PP-Elect Work | 111 |  | 6th Oct. Ph2 PP-Elect Work | -955723.6659 | 0 | 0 | -955723.6659
South Helwan PP (CP-117) | 180057 |  | South Helwan PP (CP-117) | 346909.02 | 0 | 0 | 364939.63
W Dam PP Phase II (CP-117) | 49 |  | W Dam PP Phase II (CP-117) | 13861916.9184 | 0 | 0 | 13861916.9184
New Heliopolis | Inv.9 Heliopolis | 9 | New Heliopolis9 | 11490807.56 | 0 | 0 | 11490807.56
Cairo North PP Rehabilitation | Last Invoice Cairo N |  | Cairo North PP Rehabilitation | 232789.5273 | 217658.21 | 23278.95 | 240937.16
Abou El Matameer and Sammanoud | Inv 81 P5 Sammound | 81 | Abou El Matameer and Sammanoud81 | 11846425.95 | 0 | 0 | 11846425.95
Akhmem Assiut | inv. 8 Assuit Akhmem | 8 | Akhmem Assiut8 | 41447501.75 | 0 | 0 | 41447501.75
Akhmem Assiut | inv. 6 Assuit Akhmem | 6 | Akhmem Assiut6 | 2576660.8 | 0 | 0 | 2576660.8
Beni-Suef Power Plant EPC | 8 beni Suef - 1020 | 1020 | Beni-Suef Power Plant EPC1020 | 950809783.62 | 950809783.62 | 0 | 950809783.62
Beni-Suef Power Plant EPC | 7 beni Suef - 1020 | 1020 | Beni-Suef Power Plant EPC1020 | 1360598246 | 1360598246 | 0 | 1360598246
New Capital | 12 |  | New Capital | 3945791.24 | 0 | 0 | 3945791.24
New Capital | Inv 1 Abo Zaabel | 1 | New Capital1 | 32887642.82 | 0 | 0 | 32887642.82
EMAAR-PKG#107-MARASSI | VAT 2 PKG107 |  | EMAAR-PKG#107-MARASSI | -29967.5 | 0 | 0 | -29967.5
Giza North PP Ph I,II (CP-117) | 36 EGP-Giza North 1& |  | Giza North PP Ph I,II (CP-117) | 9865294.1714 | 0 | 0 | 10358558.88
Al-Shabab PP Phase II (CP-117) | 12 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 171306.181 | 150492.48 | 26980.72 | 179871.49
Suez Gulf Substation | 2 EGP - Suez Gulf |  | Suez Gulf Substation | 1431237.0867 | 850 | 217218.78 | 1448408.5317
Cameron EDC | 019/2019 |  | Cameron EDC | 606773.67 | 603773.77 | 0 | 603773.77
Cameron EDC | 010/2019 |  | Cameron EDC | 238190.92 | 237942.78 | 0 | 237942.78
Cameron EDC | 022/2020 FCV |  | Cameron EDC | 148684449.87 | 148684449.87 | 0 | 148684449.87
Al-Shabab PP Phase II (CP-117) | 2002210017 |  | Al-Shabab PP Phase II (CP-117) | 71210.11 | 62934.34 | 11236.69 | 74171.03
W Dam PP Phase II (CP-117) | 525 |  | W Dam PP Phase II (CP-117) | 952433.46 | 899273.1 | 11231.87 | 910504.97
Al-Shabab PP Phase II (CP-117) | 180109 |  | Al-Shabab PP Phase II (CP-117) | 123920.19 | 110806.81 | 19554.14 | 130360.95
W Dam PP Phase II (CP-117) | 180102 |  | W Dam PP Phase II (CP-117) | 10048.19 | 8984.88 | 1585.57 | 10570.45
W Dam PP Phase II (CP-117) | 180040 |  | W Dam PP Phase II (CP-117) | 53513.3619 | 0 | 0 | 56189.03
Al-Shabab PP Phase II (CP-117) | 18 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 3859716.7333 | 0 | 607905.39 | 607905.39
W Dam PP Phase II (CP-117) | 11 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 114713.0476 | 86857.13 | 18067.31 | 120448.7
Al-Shabab PP Phase II (CP-117) | 180006 |  | Al-Shabab PP Phase II (CP-117) | 296307.11 | 264951.54 | 46756.15 | 311707.69
W Dam PP Phase II (CP-117) | 10 USD- West Domiat |  | W Dam PP Phase II (CP-117) | 2928987.5048 | 2614121.35 | 461315.53 | 3075436.88
W Dam PP Phase II (CP-117) | 9 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 78700.1238 | 0 | 12395.27 | 12395.27
W Dam PP Phase II (CP-117) | 8 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 665214.67 | 0 | 104771.31 | 104771.31
W Dam PP Phase II (CP-117) | 4 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 575161.01 | 0 | 86274.15 | 603919.0605
Suez Gulf Substation | 17 EGP Main Progress |  | Suez Gulf Substation | 1500870.19 | 1420990.2 | 157887.8 | 1578878
Suez Gulf Substation | 180049 |  | Suez Gulf Substation | 321619.02 | 304501.66 | 33833.52 | 338335.18
Suez Gulf Substation | 8 EGP - Suez Gulf |  | Suez Gulf Substation | 2957422.0857 | 0 | 310529.32 | 310529.32
Siemens 6x500/220 KV GIS-MOU | Inv 65 P7 Assuit | 65 | Siemens 6x500/220 KV GIS-MOU65 | 2021471.726 | 1462332.646 | 303220.76 | 1765553.406
Siemens 6x500/220 KV GIS-MOU | Inv 49 P14El Natroun | 49 | Siemens 6x500/220 KV GIS-MOU49 | 1797920.4 | 1300615.62 | 269688.06 | 1570303.68
Siemens 6x500/220 KV GIS-MOU | inv 42 P 8 Banha | 42 | Siemens 6x500/220 KV GIS-MOU42 | 3035091.3933 | 3293377.67 | 682895.56 | 3976273.23
Barwa 2x60/22 KV S/S | Inv 21 Barwa | 21 | Barwa 2x60/22 KV S/S21 | 1280709.49 | 905860.59 | 192106.44 | 1097967.03
Barwa 2x60/22 KV S/S | Inv 18 Barwa | 18 | Barwa 2x60/22 KV S/S18 | 1446935.6 | 1023280.9 | 217040.35 | 1240321.25
Damac 2x60/22 KV S/S | Inv 31 Damac | 31 | Damac 2x60/22 KV S/S31 | 752180.07 | 532133.79 | 112827 | 644960.79
New Capital | new acpital zabaal 2 |  | New Capital | 21843369.1 | 16950369.245 | 2293553.75 | 19243922.995
New Capital | inv 2 Eltbeen | 2 | New Capital2 | 4808268.97 | 3731130.19 | 504868.24 | 4235998.43
PIP- Zonafranca | Zona franka inv.17 F | 17 | PIP- Zonafranca17 | 15307277.27 | 0 | 2635752.57 | 2635752.57
South Helwan PP (CP-117) | Inv 12,13 SH | 12 | South Helwan PP (CP-117)12 | 1964148.8 | 1596079.82 | 309353.44 | 1905433.26
Al-Wukair 11 Substation | inv(ESC-SA-Civil-06) | 6 | Al-Wukair 11 Substation6 | 2799081.89 | 0 | 0 | 0
Al-Wukair 11 Substation | inv(ESC-SA-Civil-05) | 5 | Al-Wukair 11 Substation5 | 1368448.54 | 0 | 0 | 0
Berket Ghelion | 4 gheleon |  | Berket Ghelion | 4933391 | 2947383.32 | 1233347.75 | 4180731.07
Giza North PP Ph I,II (CP-117) | 29 Euro - Giza N.12 |  | Giza North PP Ph I,II (CP-117) | 477446.8476 | 426121.31 | 0 | 426121.31
Beni Suef Substation R61 | (19)BINE SUIF2 |  | Beni Suef Substation R61 | 5980776 | 3827674.29 | 1388851.53 | 5216525.82
Beni Suef Substation R61 | (18) bine suif 2 |  | Beni Suef Substation R61 | 10069327 | 2929689.9 | 6136645.4 | 9066335.3
Tamey El-amdeed Substation | TAM-CW-EGP-23 | 23 | Tamey El-amdeed Substation23 | 56099.67 | 41513.75 | 8414.95 | 49928.7
Beni Suef Substation R61 | BSF-CW-EURO-08 | 8 | Beni Suef Substation R618 | 37786.41 | 27362.5 | 5667.96 | 33030.46
Tamey El-amdeed Substation | TAM-SW-EGP-12 | 12 | Tamey El-amdeed Substation12 | 203875 | 0 | 30581.25 | 30581.25
Tamey El-amdeed Substation | TAM-SW-EGP-11 | 11 | Tamey El-amdeed Substation11 | 98875 | 0 | 14831.25 | 14831.25
Beni Suef Substation R61 | BSF-CW-EURO-06 | 6 | Beni Suef Substation R616 | 1215235.59 | 851195.7 | 182285.34 | 1033481.04
Ismailiya East Substation | ISE-CW-EGP-10 | 10 | Ismailiya East Substation10 | 3542671 | 2621576.54 | 531400.65 | 3152977.19
Ismailiya East Substation | ISE-CW-EGP-09 | 9 | Ismailiya East Substation9 | 3918783 | 2919493.33 | 587817.45 | 3507310.78
Al Mostathmreen GIS Substation | MOS-SD-EURO-11 | 11 | Al Mostathmreen GIS Substation11 | 852581.03 | 618121.25 | 127887.15 | 746008.4
Al Mostathmreen GIS Substation | 30sd elmostsmrin |  | Al Mostathmreen GIS Substation | 45275.2 | 33730.02 | 6791.28 | 40521.3
Al Mostathmreen GIS Substation | 24sd elmostsmrin |  | Al Mostathmreen GIS Substation | 685296.9 | 510546.19 | 102794.54 | 613340.73
Al Mostathmreen GIS Substation | 16sd mosstasmreen |  | Al Mostathmreen GIS Substation | 2618460 | 1950752.7 | 392769 | 2343521.7
Al Mostathmreen GIS Substation | (6)SD EURO |  | Al Mostathmreen GIS Substation | 568387 | 423448.22 | 85258.1 | 508706.32
Berket Ghelion | Gheleon 10 |  | Berket Ghelion | 2368503.48 | 1415084.9 | 592125.9 | 2007210.8
New Capital | new capital zabal 1 |  | New Capital | 32887642.83 | 25520721.12 | 3453202.5 | 28973923.62
Al-Shabab PP Phase II (CP-117) | 10 USD- Shabab |  | Al-Shabab PP Phase II (CP-117) | 1159738.7714 | 0 | 0 | 0
Berket Ghelion | inv 11 Ghalion | 11 | Berket Ghelion11 | 2749343.96 | 1642314.3 | 687336 | 2329650.3
Beni Suef ISKRA | 180004 |  | Beni Suef ISKRA | 653726.26 | 555667.32 | 98058.94 | 653726.26
Sodic Club House | (26) sodic club |  | Sodic Club House | 2960542.86 | 2678644.803 | 653831.8 | 3332476.603
Berket Ghelion | Gheleon 19 |  | Berket Ghelion | 1176766.28 | 702704.95 | 294191.6 | 996896.55
Berket Ghelion | Inv. 18 Gheleon | 18 | Berket Ghelion18 | 2724599.02 | 1627535.32 | 681147.5 | 2308682.82
New Giza 2 | 19 new giza 2 |  | New Giza 2 | 5851987.78 | 4160256.439 | 1228917.43 | 5389173.869
New Giza 2 | NEW GIZA2 -IPC 27 | 27 | New Giza 227 | 6000000 | 6000000 | 0 | 6000000
EMAAR-PKG#62-UPTOWN | 18100054 |  | EMAAR-PKG#62-UPTOWN | 6771404.91 | 2219134.03 | 2160771.53 | 4379905.56
EMAAR-PKG#62-UPTOWN | (11) pkg#62 |  | EMAAR-PKG#62-UPTOWN | 3181279.48 | 1665617.5 | 989355.77 | 2654973.27
EMAAR-PKG#107-MARASSI | (9) pkg#107 |  | EMAAR-PKG#107-MARASSI | 1856943 | 1514267.88 | 288382.69 | 1802650.57
Giza North PP Ph I,II (CP-117) | 31 Euro -Giza N.I&II |  | Giza North PP Ph I,II (CP-117) | 253624.381 | 226359.75 | 0 | 226359.75
Beni Seuf - 358 | Banha-Zagazg Inv.03 | 3 | Beni Seuf - 3583 | 40028672 | 0 | 6884070 | 6884070
Beni Seuf - 358 | Inv No 3 Bani swif | 3 | Beni Seuf - 3583 | 1979440.05 | 1573654.84 | 296916.01 | 1870570.85
Al-Shabab PP Phase II (CP-117) | 8 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 59558.6571 | 51550.07 | 9380.49 | 61795.06
New Giza 2 | (20)NEW GIZA 2 |  | New Giza 2 | 7075292 | 5821574.98 | 1485811.48 | 7307386.46
Ismalia Bridge | 2alblagat |  | Ismalia Bridge | 6537625 | 2307926.3 | 2700000 | 5932494.3
Barwa and Damac 220 OHTL | Inv No8 Wattanya220 | 8 | Barwa and Damac 220 OHTL8 | 2393557.75 | 1776805.5 | 359033.7 | 2135839.2
Beni-Suef Power Plant EPC | Beni Swef Inv March |  | Beni-Suef Power Plant EPC | 220000000 | 220000000 | 0 | 220000000
Abo Quir - Badr 500KV | Payment No.5 |  | Abo Quir - Badr 500KV | 631413.27 | 17678.88 | 0 | 17678.88
Wall - New Giza | (4) new giza wall |  | Wall - New Giza | 612721 | 664733.66 | 0 | 664733.66
Royal City | ROYAL CITY-IPC24 | 24 | Royal City24 | 15230773.26 | 9213642.983 | 3240464.39 | 12454107.373
Royal City | Royal City -IPC14 | 14 | Royal City14 | 6957536.92 | 5980044.91 | 2619847.9 | 8599892.81
Royal City | ROYALCITY-IPC13 | 13 | Royal City13 | 10776531.08 | 6339338.484 | 2702989.64 | 9042328.124
Royal City | ROYALCITY-IPC-11 | 11 | Royal City11 | 2576874.1 | 3446024.635 | 662407.85 | 4108432.485
Shubra-Banha lock&load | SHOBRE/BANHA-NILL FI |  | Shubra-Banha lock&load | 2839375.76 | 1590000 | 0 | 1590000
PIP Zona 2 | Inv.2 Zona 2 | 2 | PIP Zona 22 | 8474156.16 | 7965706.808 | 0 | 7965706.808
PIP Zona 2 | Inv,1 ZONA 2 | 1 | PIP Zona 21 | 7467710.59 | 7019647.9595 | 0 | 7019647.9595
Siemens 6x500/220 KV GIS-MOU | Inv 48 P13 El Natrun | 48 | Siemens 6x500/220 KV GIS-MOU48 | 2740112.21 | 1982197.18 | 411016.83 | 2393214.01
Barwa 2x60/22 KV S/S | 10 |  | Barwa 2x60/22 KV S/S | 4981194.27 | 2818929.29 | 597743.34 | 4412911.47
Gabal Elgalalaa | Ref. Ret Elgagalah |  | Gabal Elgalalaa | 1488429.26 | 1488429.26 | 0 | 1488429.26
Al-Shabab PP Phase II (CP-117) | 5 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2584814.8617 | 59961.44 | 392374.9 | 454205.18
Al-Shabab PP Phase II (CP-117) | 14 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 866936.2381 | 718254.94 | 136542.46 | 910283.05
South Helwan PP (CP-117) | 180133 |  | South Helwan PP (CP-117) | 254108.84 | 265995.42 | 0 | 265995.42
South Helwan PP (CP-117) | 180063 |  | South Helwan PP (CP-117) | 181104.17 | 0 | 0 | 0
Abu Qir PP (CP-117) | Inv Abu Quir |  | Abu Qir PP (CP-117) | 10613.08 | 10613.08 | 0 | 10613.08
GPC-Gupco (Automation) | 1 EGP - GPC Gupco |  | GPC-Gupco (Automation) | 58232.96 | 58232.96 | 0 | 58232.96
Apache Electrical Works | Apachi Inv No P.C#15 | 15 | Apache Electrical Works15 | 51656.33 | 51656.33 | 0 | 51656.33
Al Mostathmreen GIS Substation | (13)SD EGP |  | Al Mostathmreen GIS Substation | 438810 | 326913.35 | 65821.56 | 392734.91
Al Mostathmreen GIS Substation | SD EURO (5) |  | Al Mostathmreen GIS Substation | 3123383 | 2326920.15 | 468507.56 | 2795427.71
Al Mostathmreen GIS Substation | SD(10) mosstsmareen |  | Al Mostathmreen GIS Substation | 333395 | 248379.27 | 50009.25 | 298388.52
Al-Wukair 11 Substation | Inv April Qatar |  | Al-Wukair 11 Substation | 1952766 | 1952766 | 0 | 1952766
EMAAR-PKG#107-MARASSI | (8) PKG#107 |  | EMAAR-PKG#107-MARASSI | 4398604 | 3203756.07 | 609850.77 | 3813606.84
Flour project | 10078 |  | Flour project | 36786 | 37050.735 | 0 | 37050.735
Siemens 6x500/220 KV GIS-MOU | ret40 itay 11 |  | Siemens 6x500/220 KV GIS-MOU | 225941.11 | 225881.11 | 0 | 225881.11
Military 110 Kayan Project | Inv No2 ElKean 220 | 2 | Military 110 Kayan Project2 | 12238166.24 | 11105732.24 | 0 | 11105732.24
Banha PP (CP-118) | 22 USD - Banha 118 |  | Banha PP (CP-118) | 27229.07 | 27229.07 | 0 | 27229.07
Beni Seuf - 358 | Inv No1 Itay | 1 | Beni Seuf - 3581 | 187803669.9 | 149303317.58 | 28170550.49 | 177473868.07
Beni Seuf - 358 | Inv No 2 Bani swif | 2 | Beni Seuf - 3582 | 37272961.99 | 29632004.78 | 5590944.3 | 35222949.08
Kuwait | 1-132KVA-J | 132 | Kuwait132 | 119660.254 | 89745.2 | 0 | 89745.2
Beni Seuf - 358 | Inv No2 Itay | 2 | Beni Seuf - 3582 | 40910481.25 | 32397412.17 | 6262992.61 | 38660404.78
Kayan 3 New Cairo Capital City | (4) kayan |  | Kayan 3 New Cairo Capital City | 79493687 | 10553941.5 | 12000000 | 72140121.5
Beni Suef Substation R61 | 1cw beni suif |  | Beni Suef Substation R61 | 15153556 | 11289399.22 | 2273033.4 | 13562432.62
Al Mostathmreen GIS Substation | 17sd mosstasmreen |  | Al Mostathmreen GIS Substation | 3402 | 2534.36 | 510.38 | 3044.74
W Dam PP Phase II (CP-117) | 18 EGP-West Domiat |  | W Dam PP Phase II (CP-117) | 405120.56 | 361570.1 | 63806.49 | 425376.59
Ministries Buildings | Min.long lead Ipc3 | 3 | Ministries Buildings3 | 34860731 | 329295 | 29333800.9 | 29663095.9
Akhmem Assiut | Inv.25 Assuit Akhmem | 25 | Akhmem Assiut25 | 6024487.68 | 4789467.7 | 903673.15 | 5693140.85
Akhmem - Qena | Inv.18 Qena - Akhmem | 18 | Akhmem - Qena18 | 1166508.66 | 927374.37 | 174976.3 | 1102350.67
EMAAR-PKG#53-UPTOWN | (23) pkg#53 |  | EMAAR-PKG#53-UPTOWN | 16028014 | 14265897.01 | 2725624.69 | 16991521.7
EMAAR-PKG#62-UPTOWN | (9)PKG#62 |  | EMAAR-PKG#62-UPTOWN | 3259122 | 2334147.17 | 1341717.37 | 3675864.54
Abou El Matameer and Sammanoud | Inv 93P12Abo Matami | 93 | Abou El Matameer and Sammanoud93 | 3714366.88 | 2686973.01 | 557155.03 | 3244128.04
Abou El Matameer and Sammanoud | Inv 91P11Abo Matamir | 91 | Abou El Matameer and Sammanoud91 | 1798421.83 | 0 | 0 | 1798421.83
Abou El Matameer and Sammanoud | aboelmatamir 9inv.87 | 87 | Abou El Matameer and Sammanoud87 | 2590933.68 | 1874281.42 | 388640.05 | 2262921.47
Abou El Matameer and Sammanoud | aboelmatamir 7inv.83 | 83 | Abou El Matameer and Sammanoud83 | 4724256.33 | 3417527.03 | 708638.45 | 4126165.48
Abou El Matameer and Sammanoud | Inv 76 P3 Sammound | 76 | Abou El Matameer and Sammanoud76 | 8537190.36 | 6175803.497 | 1280578.563 | 7456382.06
PIP Zona 2 | Inv. 6 Zona Franka | 6 | PIP Zona 26 | 3651791.61 | 3432684.1305 | 0 | 3432684.1305
El Mostakbal City Project | Inv. 6 Mostakbal | 6 | El Mostakbal City Project6 | 60125306.65 | 49904004.51 | 12626314.4 | 62530318.91
Damac 2x60/22 KV S/S | Damac |  | Damac 2x60/22 KV S/S | 985085.3 | 696884.85 | 147762.78 | 844647.63
Bani Suef Old Substation | (25)bini suif 2 |  | Bani Suef Old Substation | 3992998.03 | 5924419.67 | 0 | 5924419.67
Barwa 2x60/22 KV S/S | Inv. Barwa 34 |  | Barwa 2x60/22 KV S/S | 1263037.4 | 893325.1 | 189455.6 | 1082780.7
Barwa 2x60/22 KV S/S | Inv. Barwa 35 |  | Barwa 2x60/22 KV S/S | 853918.98 | 603957.5 | 128087.85 | 732045.35
GPC-Gupco (Automation) | Petrofac Mobilisatio |  | GPC-Gupco (Automation) | 16130 | 16130 | 0 | 16130
Damac 2x60/22 KV S/S | Inv. 35 Damac | 35 | Damac 2x60/22 KV S/S35 | 640404.04 | 452909.17 | 96060.6 | 548969.77
Abou El Matameer and Sammanoud | Soc 73 Abo almat3 |  | Abou El Matameer and Sammanoud | 217153.6 | 217153.6 | 0 | 217153.6
Suez Gulf Substation | 180080 |  | Suez Gulf Substation | 830.32 | 786.13 | 87.35 | 873.48
Suez Gulf Substation | 180051 |  | Suez Gulf Substation | 903901.01 | 855793.18 | 95088.13 | 950881.31
Sodic Club House | SODIC CLUB-IPC35 | 35 | Sodic Club House35 | 4583109.75 | 2565043.8775 | 1550001.44 | 4115045.3175
Sodic Club House | (27) sodic club |  | Sodic Club House | 5615979.81 | 4546610.8405 | 404780.93 | 4951391.7705
South Helwan PP (CP-117) | 180001 |  | South Helwan PP (CP-117) | 1064344.63 | 951714.4 | 167949.6 | 1119664
Al-Wukair 11 Substation | 180011 |  | Al-Wukair 11 Substation | 1946741.9 | 1946741.9 | 0 | 1946741.9
Abou El Matameer and Sammanoud | soc 74 abo elmatamer |  | Abou El Matameer and Sammanoud | 84546.1 | 84546.05 | 0 | 84546.05
Al Mostathmreen GIS Substation | 31sd elmostsmrin |  | Al Mostathmreen GIS Substation | 33956.3 | 25297.44 | 5093.45 | 30390.89
Assuit PP (CP-118) | Adj Invoice.25 EUR |  | Assuit PP (CP-118) | 419062.41 | 374013.2 | 66002.33 | 440015.53
Assuit PP (CP-118) | 2002210003 |  | Assuit PP (CP-118) | 436928.47 | 389958.66 | 68816.23 | 458774.89
Assuit PP (CP-118) | 1907210003 |  | Assuit PP (CP-118) | 678103.04 | 605206.96 | 106801.23 | 712008.19
Assuit PP (CP-118) | 1903210001 |  | Assuit PP (CP-118) | 238723.8 | 213060.99 | 37599 | 250659.99
Assuit PP (CP-118) | 2108210003 |  | Assuit PP (CP-118) | 943539.19 | 824181.48 | 148607.42 | 972788.9
Assuit PP (CP-118) | 2007210001 |  | Assuit PP (CP-118) | 1594743.24 | 1407360.91 | 251172.06 | 1658532.97
Assuit PP (CP-118) | 2006210002 |  | Assuit PP (CP-118) | 278437.33 | 245720.95 | 43853.88 | 289574.83
Assuit PP (CP-118) | 2005210003 |  | Assuit PP (CP-118) | 1844124.47 | 1627439.84 | 290449.6 | 1917889.44
Assuit PP (CP-118) | 492 |  | Assuit PP (CP-118) | 44109.57 | 39367.79 | 6947.26 | 46315.05
South Helwan PP (CP-117) | 180014 |  | South Helwan PP (CP-117) | 366239.64 | 314696.57 | 55534.69 | 370231.26
Ain-Sokhna PP (CP-111) | Inv No 15 Sokhna 111 | 15 | Ain-Sokhna PP (CP-111)15 | 1366926.6762 | 1435273.01 | 0 | 1435273.01
Marsa Matrouh 500KV | Inv.67 Borg Alarab | 67 | Marsa Matrouh 500KV67 | 5800662.04 | 4379139.92 | 383203.54 | 4762343.46
Marsa Matrouh 500KV | Inv.60 Borg Alarab | 60 | Marsa Matrouh 500KV60 | 8205741.9 | 7167716.2 | 861602.9 | 8029319.1
Marsa Matrouh 500KV | Inv.51 Borg Alarab | 51 | Marsa Matrouh 500KV51 | 15572219.05 | 11149713.81 | 1635083 | 12784796.81
Marsa Matrouh 500KV | Inv.36 Borg Alarab | 36 | Marsa Matrouh 500KV36 | 20515172.85 | 17676141.19 | 2154093.15 | 19830234.34
Marsa Matrouh 500KV | Inv.30 Borg Alarab | 30 | Marsa Matrouh 500KV30 | 62842694.49 | 44832215.44 | 6598482.92 | 51430698.36
Marsa Matrouh 500KV | Inv.24 Borg Alarab | 24 | Marsa Matrouh 500KV24 | 2126242.02 | 1857277.58 | 223255.41 | 2080532.99
Marsa Matrouh 500KV | Inv.15Usd borg alarb | 15 | Marsa Matrouh 500KV15 | 242857.1 | 211255.95 | 25500 | 236755.95
Marsa Matrouh 500KV | Inv.18Usd borg alarb | 18 | Marsa Matrouh 500KV18 | 787370.4 | 685349.7388 | 82673.89 | 768023.6288
Marsa Matrouh 500KV | Inv.8 Borg Alarab | 8 | Marsa Matrouh 500KV8 | 3554680.7 | 3105013.72 | 373241.47 | 3478255.19
Marsa Matrouh 500KV | Inv.19Usd borg alarb | 19 | Marsa Matrouh 500KV19 | 1738927.5 | 1296421.1 | 182587.39 | 1479008.49
Marsa Matrouh 500KV | Inv. 2 usd Borg Arab | 2 | Marsa Matrouh 500KV2 | 3843466.97 | 3338972.49 | 403564.03 | 3742536.52
EMAAR-PKG117- MARASSI | PKG#117-IPC(5) | 5 | EMAAR-PKG117- MARASSI5 | 6909335.09 | 5093815.29 | 603547.82 | 5697363.11
Military 110 Kayan Project | Elkayan Inv. 11 | 11 | Military 110 Kayan Project11 | 16122958.23 | 14631191.7 | 0 | 14631191.7
kayan wall lock & Load | IPC3-KAYAN LOAK&LOAD | 3 | kayan wall lock & Load3 | 5542200 | 3329140.4 | 1700000 | 5029140.4
Royal City | (5) ROYAL CITY |  | Royal City | 9626900.5 | 7170078.235 | 1373608.88 | 8543687.115
EMAAR-PKG#53-UPTOWN | (29) pkg#53 |  | EMAAR-PKG#53-UPTOWN | 17007596.13 | 11883297.1 | 4020621.88 | 15903918.98
kayan wall lock & Load | KAYAN LOCK&LOAD-IPC2 | 2 | kayan wall lock & Load2 | 9801900 | 8894827.6 | 0 | 8894827.6
4 SS - Technical Service | 214 |  | 4 SS - Technical Service | 889003.08 | 889003.08 | 0 | 889003.08
Cairo Capital S1 | Inv. 8 Project S 1 | 8 | Cairo Capital S18 | 49197972.07 | 37021072 | 7379695.81 | 44400767.81
Cairo Capital S1 | Inv. 5 Project S 1 | 5 | Cairo Capital S15 | 294355018.7 | 221501738 | 44153252.81 | 265654990.81
EMAAR-PKG#53-UPTOWN | PKG#53-IPC(31) | 31 | EMAAR-PKG#53-UPTOWN31 | 17457747.57 | 11753104.21 | 2818389.38 | 14571493.59
Ministries Buildings | Mini Alocation IPC07 | 7 | Ministries Buildings7 | 19093536.78 | 2150095 | 14011412.8 | 16161507.8
Al-Wukair 11 Substation | 180074 |  | Al-Wukair 11 Substation | 301343 | 301343 | 0 | 301343
Suez Gulf Substation | 180050 |  | Suez Gulf Substation | 74219.77 | 70269.62 | 7807.73 | 78077.35
New Capital Tunnels | M.B.Z-IPC (2) | 2 | New Capital Tunnels2 | 72366701.1 | 2372381.85 | 0 | 65672381.85
Lina Farm Substation | 2 USD - Lina |  | Lina Farm Substation | 104405.9 | 104405.9 | 0 | 104405.9
Attaqa Power Plant | PV Sep |  | Attaqa Power Plant | 0.01 | 0.01 | 0 | 0.01
EMAAR-PKG117- MARASSI | 18100047 |  | EMAAR-PKG117- MARASSI | 4332593.54 | 4793875.01 | 571929.38 | 5365804.39
Akhmem - Qena | Inv.12 Qena- Akhmem$ | 12 | Akhmem - Qena12 | 370999.7 | 313121.63 | 0 | 313121.63
Cairo Capital S1 | Inv. 3 Project S 1 | 3 | Cairo Capital S13 | 30202891.45 | 22727273.95 | 4530433.7 | 27257707.65
Akhmem - Qena | Inv.11 Qena- Akhmem$ | 11 | Akhmem - Qena11 | 2023.28 | 1477.09 | 0 | 1477.09
South Helwan PP (CP-117) | 180125 |  | South Helwan PP (CP-117) | 52552.49 | 55283.91 | 0 | 55283.91
EMAAR-PKG#53-UPTOWN | IPC (34) - PKG#53 | 34 | EMAAR-PKG#53-UPTOWN34 | 62924.2 | 1344501.4 | 0 | 1344501.4
Kayan 3 New Cairo Capital City | Kayan finishing-ipc5 | 5 | Kayan 3 New Cairo Capital City5 | 54046053.75 | 39276155.35 | 9500000 | 48776155.35
Tamey El-amdeed Substation | TAM-CW-IPC5 | 5 | Tamey El-amdeed Substation5 | 5185072.85 | 3862879.27 | 777760.93 | 4640640.2
Beni Suef Substation R61 | BSF-CW-IPC 8 | 8 | Beni Suef Substation R618 | 1776658 | 1323610.21 | 266498.7 | 1590108.91
Akhmem - Qena | Inv.14 Qena- Akhmem$ | 14 | Akhmem - Qena14 | 221966.15 | 188492.15 | 0 | 188492.15
Akhmem - Qena | Inv.15 Qena- Akhmem$ | 15 | Akhmem - Qena15 | 1896734.28 | 1602794.48 | 0 | 1602794.48
Akhmem - Qena | Inv.13 Qena- Akhmem$ | 13 | Akhmem - Qena13 | 2370917.85 | 2008736.88 | 0 | 2008736.88
Akhmem Assiut | Inv.8 Assuit Akhmem$ | 8 | Akhmem Assiut8 | 1941363.36 | 1646606.21 | 0 | 1646606.21
South Helwan PP (CP-117) | SH Comm fees inv.29 | 29 | South Helwan PP (CP-117)29 | 9043.58 | 9043.58 | 0 | 9043.58
South Helwan PP (CP-117) | 180131 |  | South Helwan PP (CP-117) | 171275.5 | 152260.72 | 27026.63 | 179287.35
Akhmem - Qena | Inv.39 Akhmem Qena | 39 | Akhmem - Qena39 | 9958390.94 | 6921081.87 | 1493758.64 | 8414840.51
Elsewedy Univ - Enabling Works | els-uni-fin&mep-11 F | 11 | Elsewedy Univ - Enabling Works11 | 17614054.86 | 16620031.47 | 16132569 | 32752600.47
NUCA R05 - Z02 | R5 ZONE 2- IPC05 | 5 | NUCA R05 - Z025 | 33184894.04 | 28985192.51 | 3507610.12 | 32492802.63
South Helwan PP (CP-117) | Commercial fees SH/ |  | South Helwan PP (CP-117) | 41456.9 | 41456.9 | 0 | 41456.9
South Helwan PP (CP-117) | South Helwan insuran |  | South Helwan PP (CP-117) | 0 | -5724.34 | 0 | -5724.34
Ministries Buildings | MIN-OLD-IPC04 | 4 | Ministries Buildings4 | 52589933.5 | 19470465 | 19470471.05 | 41610936.05
Mohamed Ali Palace Restoration | PO - Mohamed Aly 113 |  | Mohamed Ali Palace Restoration | 483236.15 | 342825 | 114279.25 | 457104.25
Ministries Buildings | MIN-LONGLEAD-IPC02 | 2 | Ministries Buildings2 | 33902917.25 | 2019275 | 17497350 | 30529073.16
Kayan 3 New Cairo Capital City | KAYAN FIER-IPC01 | 1 | Kayan 3 New Cairo Capital City1 | 10380000 | 1712930 | 5700000 | 7412930
Middle Tunnel Lock Load | ALAWSATY L&L-1 FINAL | 1 | Middle Tunnel Lock Load1 | 1024820 | 677590 | 225865.1 | 903455.1
Akhmem Assiut | Inv.12 Assuit Akhmem | 12 | Akhmem Assiut12 | 21802696.35 | 17333143.6 | 3270404.45 | 20603548.05
Akhmem Assiut | Ref.Instil No,1 Assu |  | Akhmem Assiut | 50551945.28 | 50551945.28 | 0 | 50551945.28
Marsa Matrouh 500KV | Inv, 1 usd Borg Arab | 1 | Marsa Matrouh 500KV1 | 3897349.44 | 2595001.89 | 409221.69 | 3004223.58
Akhmem Assiut | Inv.17Assuit Akhmem$ | 17 | Akhmem Assiut17 | 1472758.41 | 1238711.97 | 0 | 1238711.97
Akhmem - Qena | Inv.21 Qena- Akhmem$ | 21 | Akhmem - Qena21 | 474183.57 | 398269.57 | 0 | 398269.57
Canal Regional Control Center | Inv.3 Rcc | 3 | Canal Regional Control Center3 | 27085715.32 | 18037871.44 | 5688000.22 | 23725871.66
Al Mostathmreen GIS Substation | MOS-SD-EGP-IPC 33 | 33 | Al Mostathmreen GIS Substation33 | 968907.6 | 721836.16 | 145336.14 | 867172.3
Marsa Matrouh 500KV | Inv11 Usd borg alarb | 11 | Marsa Matrouh 500KV11 | 543102.44 | 473023.621 | 57025.76 | 530049.381
Cairo Capital S1 | Inv. 2 Project S 1 | 2 | Cairo Capital S12 | 18225360.19 | 13714173.65 | 2733804.94 | 16447978.59
Akhmem - Qena | Inv.25 Qena- Akhmem$ | 25 | Akhmem - Qena25 | 189673.43 | 160185.42 | 0 | 160185.42
AWEER POWER STATION 'H' Phase | 10003 |  | AWEER POWER STATION 'H' Phase | 443645.36 | 443645.36 | 0 | 443645.36
Abou El Matameer and Sammanoud | Soc Inv 12 Abo Almat | 12 | Abou El Matameer and Sammanoud12 | 80779.65 | 80779.63 | 0 | 80779.63
Akhmem - Qena | Inv.16 Qena- Akhmem$ | 16 | Akhmem - Qena16 | 1807476.18 | 1533101.07 | 0 | 1533101.07
Akhmem - Qena | Inv.5 Qena - Akhmem$ | 5 | Akhmem - Qena5 | 3135559.87 | 2637502.47 | 0 | 2637502.47
Manshiet Nasser Substation | 180170 |  | Manshiet Nasser Substation | 1290995.17 | 1355544.93 | 0 | 1355544.93
Tamey El-amdeed Substation | TAM-CW-EGP-08 | 8 | Tamey El-amdeed Substation8 | 4576661.83 | 3409613.07 | 686499.27 | 4096112.34
Akhmem Assiut | Inv.31 Assuit Akhmem | 31 | Akhmem Assiut31 | 12474233.2 | 9917015.39 | 1871134.98 | 11788150.37
Akhmem Assiut | ref Instill 3 Assuit |  | Akhmem Assiut | 3232586.7 | 3232586.7 | 0 | 3232586.7
Ismailiya East Substation | (4)cw elasmailya |  | Ismailiya East Substation | 5057617 | 3798259.66 | 758642.55 | 4556902.21
Marsa Matrouh 500KV | Inv.9 Usd borg alarb | 9 | Marsa Matrouh 500KV9 | 1542129.34 | 1342501.02 | 161923.58 | 1504424.6
Marsa Matrouh 500KV | Inv12 Usd borg alarb | 12 | Marsa Matrouh 500KV12 | 1689419.1 | 1470642.726 | 177389.01 | 1648031.736
AWEER POWER STATION 'H' Phase | CON 034 |  | AWEER POWER STATION 'H' Phase | 2214677.66 | 0 | 246075.3 | 246075.3
AWEER POWER STATION 'H' Phase | CON/031 |  | AWEER POWER STATION 'H' Phase | 1107338.83 | 971997.4166 | 123037.65 | 1095035.0666
AWEER POWER STATION 'H' Phase | LOC/022 |  | AWEER POWER STATION 'H' Phase | 463333.89 | 406704.1897 | 51481.54 | 458185.7297
AWEER POWER STATION 'H' Phase | CON/027 |  | AWEER POWER STATION 'H' Phase | 266187.22 | 233653.22 | 29576.36 | 263229.58
AWEER POWER STATION 'H' Phase | LOC/011 |  | AWEER POWER STATION 'H' Phase | 37500.07 | 37011.6085 | 0 | 37011.6085
AWEER POWER STATION 'H' Phase | 10207 |  | AWEER POWER STATION 'H' Phase | 30045509.98 | 8846733.49 | 20864937.488 | 29711670.978
Marsa Matrouh 500KV | Inv. 2 Borg Alarab | 2 | Marsa Matrouh 500KV2 | 65050776.78 | 56821854.48 | 6830331.56 | 63652186.04
Marsa Matrouh 500KV | Inv. 1 Borg Alarab | 1 | Marsa Matrouh 500KV1 | 128259940.46 | 112028060.46 | 13467293.75 | 125495354.21
EDNC Retail & Offices Civil | Sodic Soreal - IPC24 | 24 | EDNC Retail & Offices Civil24 | 24555503.39 | 18782844.0895 | 2052633.3 | 20835477.3895
EDNC Retail & Offices Civil | SOREAL-IPC21 | 21 | EDNC Retail & Offices Civil21 | 45022478.11 | 32167186.0755 | 2969464.09 | 35136650.1655
EDNC Retail & Offices Civil | SOREA-IPC18 | 18 | EDNC Retail & Offices Civil18 | 39729323.85 | 26361312.3025 | 3416876.44 | 29778188.7425
Siemens 6x500/220 KV GIS-MOU | Inv 92- P14 Assuit | 92 | Siemens 6x500/220 KV GIS-MOU92 | 2399962.85 | 1720133.38 | 359994.43 | 2080127.81
Tunnel of Sokhna Road | SOKHNA TUNNLE-IPC 2 | 2 | Tunnel of Sokhna Road2 | 5115560.44 | 3305891.9 | 0 | 4616391.9
South Helwan PP (CP-117) | SH Inv.37 ded&comm | 37 | South Helwan PP (CP-117)37 | 2104.52 | 2104.52 | 0 | 2104.52
Al Mostathmreen GIS Substation | MOS-SW-EGP- IPC 5 | 5 | Al Mostathmreen GIS Substation5 | 2072122.5 | 1543731.26 | 310818.38 | 1854549.64
South Helwan PP (CP-117) | 180138 |  | South Helwan PP (CP-117) | 318759.39 | 335326.93 | 0 | 335326.93
EMAAR-PKG# 101-UPTOWN | PKG#101 -IPC09 | 9 | EMAAR-PKG# 101-UPTOWN9 | 4704887.4 | 2104893.84 | 1093496.43 | 3198390.27
Asec Spare-Parts | Inv 5 Asec Sparepart | 5 | Asec Spare-Parts5 | 115200 | 0 | 131328 | 131328
DPW Onshore Port & Terminal | DP WORLD-IPC16 | 16 | DPW Onshore Port & Terminal16 | 86484919.88 | 63998840.71 | 12972737.85 | 76971578.56
DPW Onshore Port & Terminal | DP WORLD-IPC08 | 8 | DPW Onshore Port & Terminal8 | 40506959.46 | 29974844.16 | 6076043.92 | 36050888.08
DPW Onshore Port & Terminal | DP WORLD-IPC006 | 6 | DPW Onshore Port & Terminal6 | 17786446.66 | 13161622.85 | 2667967 | 15829589.85
DPW Onshore Port & Terminal | DP WORLD-IPC24 | 24 | DPW Onshore Port & Terminal24 | 28199021.24 | 20867275.72 | 4229853.19 | 25097128.91
DPW Onshore Port & Terminal | DP WORLD-IPC22 | 22 | DPW Onshore Port & Terminal22 | 23946448.25 | 17720371.7 | 3591967.24 | 21312338.94
DPW Onshore Port & Terminal | DP WORLD-IPC17 | 17 | DPW Onshore Port & Terminal17 | 56454657.9 | 41776446.84 | 8468198.69 | 50244645.53
Akhmem - Qena | Inv.46 Qena Akhmem | 46 | Akhmem - Qena46 | 2174961.72 | 1500723.59 | 326244.26 | 1826967.85
HAC CCC JV | IPC#8 | 8 | HAC CCC JV8 | 2823626 | 2589783.17 | 0 | 2589783.17
Elsewedy Univ - Enabling Works | uni-fin&mep-ipc08 | 8 | Elsewedy Univ - Enabling Works8 | 22047683.73 | 12292368.36 | 4990650.83 | 17283019.19
Akhmem Assiut | Inv.44 Assuit Akhmem | 44 | Akhmem Assiut44 | 71871078.86 | 35934921.07 | 10780661.83 | 46715582.9
Kuwait | Other Charge/J002 |  | Kuwait | 160091.58 | 104059.53 | 0 | 104059.53
Zambia Project | SCD3/002 |  | Zambia Project | 61134.56 | 61115.75 | 0 | 61115.75
Ghana | 39/P/10/ER/2017/USD |  | Ghana | 963291.46 | 963291.46 | 0 | 963291.46
Ismailiya East Substation | 19100022 |  | Ismailiya East Substation | 2593944 | 1919518.56 | 389091.6 | 2308610.16
Beni Suef Substation R61 | BSF-SD-EUR-03 | 3 | Beni Suef Substation R613 | 2707740.55 | 2017266.71 | 406161.08 | 2423427.79
Tamey El-amdeed Substation | 19100021 |  | Tamey El-amdeed Substation | 844375 | 624537.5 | 126656.25 | 751193.75
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC14 | 14 | EMAAR- Pkg 140-ITP-Mivida14 | 2429362.37 | 7336701.0985 | 938825.93 | 8275527.0285
EMAAR- Pkg 140-ITP-Mivida | PKG#140 -IPC07 | 7 | EMAAR- Pkg 140-ITP-Mivida7 | 12232780.52 | 10719905.22 | 1371750.71 | 12091655.93
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC04 | 4 | EMAAR- Pkg 140-ITP-Mivida4 | 2442385.78 | 999645.44 | 1260904.72 | 2260550.16
New Capital | Inv 5 El Tbeen | 5 | New Capital5 | 291721.43 | 211574.23 | 30602.89 | 242707.78
Zambia Project | SCD4/0012 |  | Zambia Project | 228771.79 | 228771.79 | 0 | 228771.79
Zambia Project | Inv 8 Zambia | 8 | Zambia Project8 | 450718.84 | 405646.2 | 0 | 405646.2
Zambia Project | SCD1/003 |  | Zambia Project | 1090304.15 | 981254.93 | 0 | 981254.93
Beni Suef Substation R61 | BSF-SW-07 | 7 | Beni Suef Substation R617 | 1126562.5 | 839289.06 | 168984.38 | 1008273.44
Metro 2L Rehabitation Cable | 10 EGP - Metro |  | Metro 2L Rehabitation Cable | 803126.24 | 1591777.48 | 0 | 795888.74
Manshiet Nasser Substation | 515 |  | Manshiet Nasser Substation | 1160236 | 716945.6 | 186738.71 | 903684.31
Manshiet Nasser Substation | 499 |  | Manshiet Nasser Substation | 16207.95 | 3486 | 2431.19 | 5917.19
Manshiet Nasser Substation | 498 |  | Manshiet Nasser Substation | 197970.92 | 168275.28 | 29695.64 | 197970.92
Akhmem Assiut | Inv.27 Assuit Akhmem | 27 | Akhmem Assiut27 | 1273348.85 | 757642.61 | 191002.31 | 948644.92
Akhmem Assiut | Inv.20 Assuit Akhmem | 20 | Akhmem Assiut20 | 4701462.93 | 3737663.02 | 705219.44 | 4442882.46
AbuSultan Rd Bridge2 Extension | ABU SOULTAN2-IPC02FI | 2 | AbuSultan Rd Bridge2 Extension2 | 19900418.1 | 6214797 | 6214800 | 18954747
Manshiet Nasser Substation | 1902210013 |  | Manshiet Nasser Substation | -11569820.5395 | -11569820.5395 | 0 | -11569820.5395
Manshiet Nasser Substation | 1902210010 |  | Manshiet Nasser Substation | 11569820.5395 | 11569820.5395 | 0 | 11569820.5395
Cameron EDC | 008/2019 |  | Cameron EDC | 731475.72 | 730847.21 | 0 | 730847.21
SHAT Al ARAB 400/132kV SS | 218 |  | SHAT Al ARAB 400/132kV SS | 85444.47 | 85444.47 | 0 | 85444.47
Elsewedy Univ - Enabling Works | SEWEDY UNI-FI&MEP-03 | 3 | Elsewedy Univ - Enabling Works3 | 4205490.22 | 5785718.662 | 0 | 5785718.662
Akhmem Assiut | Ref.Ret 2 assuit akh |  | Akhmem Assiut | 308632.14 | 306443 | 0 | 306443
SHATRA 400/132kV SS | 225 |  | SHATRA 400/132kV SS | 281724.77 | 281724.77 | 0 | 281724.77
Akhmem - Qena | Ref.Ret 4 Qena akh |  | Akhmem - Qena | 434907.38 | 431946.99 | 0 | 431946.99
HAC CCC JV | IPC#11 | 11 | HAC CCC JV11 | 785640.6 | 717522.48 | 0 | 717522.48
Development of Mahmudiyah axis | IPC# 1&2 | 1 | Development of Mahmudiyah axis1 | 2070000 | 2012040 | 0 | 2012040
Cameron EDC | 012/2019 |  | Cameron EDC | 284467 | 284200.77 | 0 | 284200.77
Attaqa Power Plant | inv. 3 USD. | 3 | Attaqa Power Plant3 | 117713333 | 117397708.65 | 0 | 117397708.65
Akhmem Assiut | Inv.5 Assuit Akhmem$ | 5 | Akhmem Assiut5 | 1077242.34 | 908182.12 | 0 | 908182.12
Manshiet Nasser Substation | 1902210006 |  | Manshiet Nasser Substation | 1724596.17 | 1617024.49 | 176555.53 | 1793580.02
Hyper El-Temsah | hyper eltemsah-IPC01 | 1 | Hyper El-Temsah1 | 87773321.47 | 5986334.4505 | 51376020.75 | 74009065.2005
Kayan Landscape | KAYAN RAWDA-IPC01 | 1 | Kayan Landscape1 | 41368778 | 15494720 | 15494728.45 | 30989448.45
kayan wall lock & Load | KAYAN LOAK&LOAD-IPC6 | 6 | kayan wall lock & Load6 | 3367800 | 1519519.25 | 1519522.25 | 3039041.5
Manshiet Nasser Substation | 1902210009 |  | Manshiet Nasser Substation | 2765359.42 | 2875973.8 | 0 | 2875973.8
EMAAR-PKG#53-UPTOWN | PKG#53-VO-IPC02 | 2 | EMAAR-PKG#53-UPTOWN2 | 440000 | 451528 | 0 | 451528
Tamey El-amdeed Substation | TAM-CW-EURO-06 | 6 | Tamey El-amdeed Substation6 | 1163547.87 | 861025.42 | 174532.18 | 1035557.6
Ismailiya East Substation | ISE-CW-EGP-11 | 11 | Ismailiya East Substation11 | 3544526 | 2622949.24 | 531678.9 | 3154628.14
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 36 | 36 | Benban 500 K.V/95 K.M36 | -99992664.48 | -101703146.02 | 8110012.09 | -93593133.93
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 35 | 35 | Benban 500 K.V / 100 K.M35 | 23321019.39 | 14102819.07 | 4893750.83 | 18996569.9
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 34 | 34 | Benban 500 K.V / 100 K.M34 | 15524050.7 | 12590008.58 | 1630025.32 | 14220033.9
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 33 | 33 | Benban 500 K.V / 100 K.M33 | 11901237.74 | 9175859.44 | 1249629.96 | 10425489.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 21 | 21 | Benban 500 K.V / 100 K.M21 | 621621.59 | 479269.83 | 65270.27 | 544540.1
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 15 | 15 | Benban 500 K.V / 100 K.M15 | 894191.35 | 689426.25 | 93890.09 | 783316.34
Assuit PP (CP-118) | 1904210003 |  | Assuit PP (CP-118) | 397913.84 | 355138.1 | 62671.43 | 417809.53
Kuwait | Erection/J001 |  | Kuwait | 57389.81 | 37303.38 | 0 | 37303.38
Badr | Inv. 12 Badr | 12 | Badr12 | 9125593 | 6775339.15 | 1368838.95 | 8144178.1
P-28-16 Balat Owinat Lot 3 | Inv. 9 Balat lot 3 | 9 | P-28-16 Balat Owinat Lot 39 | 19007880.37 | 14198491.76 | 1995827.44 | 16194319.2
Canal Sugar S/s | Inv 9 Sugar S/s | 9 | Canal Sugar S/s9 | 9045358.6 | 7145812.42 | 1356803.79 | 8502616.21
Marsa Matrouh 500KV | Inv.28 Borg Alarab | 28 | Marsa Matrouh 500KV28 | 32681632.39 | 28547405.59 | 3431571.4 | 31978976.99
Assuit PP (CP-118) | 1904210005 |  | Assuit PP (CP-118) | 264451.2 | 236022.7 | 41651.06 | 277673.76
Assuit PP (CP-118) | 1905210002 |  | Assuit PP (CP-118) | 350280.73 | 297738.62 | 52542.11 | 350280.73
MAYSAN 400/132kV SS | 233 |  | MAYSAN 400/132kV SS | 17454.6 | 17454.6 | 0 | 17454.6
Elco Steel 220/33 KV SS | 1904210009 |  | Elco Steel 220/33 KV SS | 1532770.52 | 4828227.12 | 0 | 1609409.04
Benban 500 K.V/95 K.M | Benban Lot2 Inv 13 $ | 13 | Benban 500 K.V/95 K.M13 | 206501.3 | 173461.09 | 21682.64 | 195143.73
Benban 500 K.V/95 K.M | Benban Lot2 Inv 10 $ | 10 | Benban 500 K.V/95 K.M10 | 157187.95 | 132037.88 | 16504.74 | 148542.62
Suez Gulf Substation | custom clearance |  | Suez Gulf Substation | 3379.7 | 3379.7 | 0 | 3379.7
Assuit PP (CP-118) | 1905210003 |  | Assuit PP (CP-118) | 792686.09 | 673783.18 | 118902.91 | 792686.09
Manshiet Nasser Substation | 1906210012 |  | Manshiet Nasser Substation | 166472.19 | 177000.08 | 0 | 177000.08
El Boghaz Brigde | IPC#21 | 21 | El Boghaz Brigde21 | 4406158.08 | 4120470.6 | 0 | 4120470.6
Royal City | royal city- ipc20 | 20 | Royal City20 | 8557310.7 | 5072118.405 | 2329228.6 | 7401347.005
P-28-16 Balat Owinat Lot 2 | Inv. 10 Balat Lot 2 | 10 | P-28-16 Balat Owinat Lot 210 | 4458789.24 | 3330319.846 | 468172.874 | 3798492.72
EMAAR-PKG117- MARASSI | PKG#117 - IPC10 | 10 | EMAAR-PKG117- MARASSI10 | 1133422.08 | 855651.034 | 87857.74 | 943508.774
P-28-16 Balat Owinat Lot 2 | Inv. 9 Balat Lot 2 | 9 | P-28-16 Balat Owinat Lot 29 | 4160100.05 | 3107201.55 | 436810.61 | 3544012.16
Elco Steel 220/33 KV SS | 1906210006 |  | Elco Steel 220/33 KV SS | 1135836.53 | 2385256.72 | 0 | 1192628.36
Akhmem Assiut | Inv.49 Assuit Akhmem | 49 | Akhmem Assiut49 | 1803910.73 | 883291.619 | 270586.61 | 1153878.229
Akhmem Assiut | Inv.50 Assuit Akhmem | 50 | Akhmem Assiut50 | 4716318.7 | 3253660 | 707447.81 | 3961107.81
AWEER POWER STATION 'H' Phase | 10138 |  | AWEER POWER STATION 'H' Phase | 193376.33 | 56938.5945 | 134289.11 | 191227.7045
Akhmem - Qena | ٍSoc inv 9 Quana | 9 | Akhmem - Qena9 | 145402 | 145402 | 0 | 145402
Akhmem - Qena | Inv.26 Akhmem Qena | 26 | Akhmem - Qena26 | 1620414 | 964146.33 | 243062.1 | 1207208.43
Akhmem - Qena | Inv.15 Qena - Akhmem | 15 | Akhmem - Qena15 | 8195570.2 | 6515478.31 | 1229335.53 | 7744813.84
Elco Steel 220/33 KV SS | 1908210008 |  | Elco Steel 220/33 KV SS | 2384034.06 | 7509707.28 | 0 | 2503235.76
Elco Steel 220/33 KV SS | 1907210011 |  | Elco Steel 220/33 KV SS | 352785.17 | 370424.43 | 0 | 370424.43
Elco Steel 220/33 KV SS | 1907210010 |  | Elco Steel 220/33 KV SS | 106741.38 | 224156.9 | 0 | 112078.45
Marsa Matrouh 500KV | Inv16 Usd borg alarb | 16 | Marsa Matrouh 500KV16 | 1671146.66 | 1454833.25 | 175470.4 | 1630303.65
Beni Seuf - 358 | Soc inv 4-5 Itay T | 4 | Beni Seuf - 3584 | 4112636 | 4112636 | 0 | 4112636
MAYSAN 400/132kV SS | 249 |  | MAYSAN 400/132kV SS | 69890.56 | 69890.56 | 0 | 69890.56
MOTHANA 400/132kV SS | 217 |  | MOTHANA 400/132kV SS | 793142.51 | 793142.51 | 0 | 793142.51
Latin Compound - New Alamin | inv ( 18 ) 5-12-2020 | 18 | Latin Compound - New Alamin18 | 261822.4 | 168908.89 | 52364.48 | 221273.37
Latin Compound - New Alamin | inv ( 16 ) 2-12-2020 | 16 | Latin Compound - New Alamin16 | 665963.2 | 426391.14 | 133192.64 | 559583.78
LAYYAH CCPP | 516 |  | LAYYAH CCPP | 7402941 | 6292499.85 | 1110441.15 | 7402941
LAYYAH CCPP | 515 |  | LAYYAH CCPP | 3948235 | 3355999.75 | 592235.25 | 3948235
LAYYAH CCPP | 509 |  | LAYYAH CCPP | 1233824 | 1048750.4 | 185073.6 | 1233824
LAYYAH CCPP | 500 |  | LAYYAH CCPP | 571625 | 510175.31 | 85743.75 | 595919.06
LAYYAH CCPP | 495 |  | LAYYAH CCPP | 217625 | 194230.31 | 32643.75 | 226874.06
AWEER POWER STATION 'H' Phase | 10147 |  | AWEER POWER STATION 'H' Phase | 9955116.776 | 2931228.8318 | 6913275.536 | 9844504.3678
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 6 | 6 | Benban 500 K.V/95 K.M6 | 30330357.26 | 23384711.66 | 3184687.51 | 26569399.17
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 6 | 6 | Benban 500 K.V / 100 K.M6 | 196467.63 | 151483.75 | 20629.1 | 172112.85
Marsa Matrouh 500KV | Inv.34 Borg Alarab | 34 | Marsa Matrouh 500KV34 | 3164011.42 | 2763767.08 | 332221.2 | 3095988.28
Beni-Suef Power Plant EPC | Adj.180119-180120 | 180120 | Beni-Suef Power Plant EPC180120 | 514357853.75 | 195226674.9 | 0 | 514357853.75
AWEER POWER STATION 'H' Phase | 10004 |  | AWEER POWER STATION 'H' Phase | 603796 | 633985.8 | 0 | 633985.8
SHAT Al ARAB 400/132kV SS | 264 |  | SHAT Al ARAB 400/132kV SS | 103370.75 | 103370.75 | 0 | 103370.75
MAYSAN 400/132kV SS | 275 |  | MAYSAN 400/132kV SS | 764872.91 | 764872.91 | 0 | 764872.91
Nagaa Hamady/Assuit OHTL | Naga Hmdy Inv.2 Equ | 2 | Nagaa Hamady/Assuit OHTL2 | 1678008.52 | 1125946.77 | 176190.9 | 1302137.67
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.7 | 7 | Nagaa Hamady/Assuit OHTL7 | 86548.57 | 48989.48 | 9087.6 | 58077.08
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 4 | 4 | Nagaa Hamady/Assuit OHTL4 | 3302738.1 | 2381277.81 | 346787.5 | 2728065.31
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv. 3 | 3 | Nagaa Hamady/Assuit OHTL3 | 28754334.29 | 20731878.03 | 3019206.1 | 23751084.13
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 2 | 2 | Marsa Alam/ Bernes LOT2 OHTL2 | 1897557.22 | 1154933.67 | 203707.31 | 1358640.98
Canal Sugar 33KV OHTL | Inv. 2 Sugar 33 OHTL | 2 | Canal Sugar 33KV OHTL2 | 14000095.18 | 11060075.19 | 2100014.28 | 13160089.47
33KV Canal Farm Grid | Inv. 09 Farm | 9 | 33KV Canal Farm Grid9 | 15435576.01 | 11777344.5 | 2315336.4 | 14092680.9
EMAAR-PKG#53-UPTOWN | (28) PKG#53 |  | EMAAR-PKG#53-UPTOWN | 13004518.87 | 556642.39 | 8811607.74 | 9368250.13
Ministries Buildings | MINISTRIY OLD-IPC02 | 2 | Ministries Buildings2 | 20749090 | 5695997 | 5303248.3 | 15941317.3
Almaza | Inv. 02 Almaza | 2 | Almaza2 | 3005859.27 | 2862672 | 0 | 2862672
Manshiet Nasser Substation | 1904210017 |  | Manshiet Nasser Substation | 844020 | 844020 | 0 | 844020
HyperOne Zayed Extension | HYPER ONE-IPC04 | 4 | HyperOne Zayed Extension4 | 12451225.71 | 6318712 | 3112806.43 | 11998135.8755
Assuit PP (CP-118) | 1908210001 |  | Assuit PP (CP-118) | 155640.55 | 138909.19 | 24513.39 | 163422.58
Tamey El-amdeed Substation | TAM-CW-EURO-09 | 9 | Tamey El-amdeed Substation9 | 709911.17 | 453949.5 | 106486.68 | 560436.18
Ministries Buildings | MIN.FIT OUT- PC01 |  | Ministries Buildings | 8504450 | 4352874 | 2556654.4 | 6909528.4
Ismalia Bridge | Ismailia U4-ipc 2 | 2 | Ismalia Bridge2 | 5416102.82 | 5491516.5 | 9690 | 5501206.5
Ministries Buildings | MIN-CORE- IPC02 | 2 | Ministries Buildings2 | 14861602.7 | 4426417 | 8985770 | 13412187
Manshiet Nasser Substation | 1908210018 |  | Manshiet Nasser Substation | 1647733.85 | 1695847.04 | 0 | 1695847.04
Asec Spare-Parts | Inv 2 EUR Asec Spare | 2 | Asec Spare-Parts2 | 39684.48 | 0 | 33644.11 | 33644.11
Ghana Street lighting | MIDA Sply. Inv. 4 | 4 | Ghana Street lighting4 | 193188.28 | 193188.28 | 0 | 193188.28
Ghana Street lighting | inv 5 Sup | 5 | Ghana Street lighting5 | 204923.64 | 204923.64 | 0 | 204923.64
AWEER POWER STATION 'H' Phase | 10308 |  | AWEER POWER STATION 'H' Phase | 750671.33 | 221030.99 | 521299.5356 | 742330.5256
Kayan 3 New Cairo Capital City | KAYAN FINSH-IPC07 | 7 | Kayan 3 New Cairo Capital City7 | 30167296.25 | 9223514 | 18002052 | 27225566
Nuweibaa (Swro) | Invoice No:12 |  | Nuweibaa (Swro) | 308452.2 | 246761.76 | 61690.44 | 308452.2
Nuweibaa (Swro) | 2010210005 |  | Nuweibaa (Swro) | 489160.25 | 391328.2 | 97832.05 | 489160.25
Oasis Buildings- New Capital | inv ( 9 ) | 9 | Oasis Buildings- New Capital9 | 1607046.56 | 1338245.83 | 0 | 1338245.83
Oasis Buildings- New Capital | inv ( 13 ) final | 13 | Oasis Buildings- New Capital13 | 1082880 | 805095.09 | 0 | 805095.09
Oasis Buildings- New Capital | Inv(4)240220 | 4 | Oasis Buildings- New Capital4 | 103400 | 98374.2 | 0 | 98374.2
El Katameya Mall | inv(7)150320 | 7 | El Katameya Mall7 | 135800 | 114954.7 | 0 | 114954.7
Beni Suef Add-on Sales | 513 |  | Beni Suef Add-on Sales | 7500.2 | 8475.228 | 0 | 8475.228
ORA Zed Park LOCK&LOAD | ORA-IPC01 | 1 | ORA Zed Park LOCK&LOAD1 | 573141.24 | 505797.142 | 0 | 505797.142
AWEER POWER STATION 'H' Phase | 10249 |  | AWEER POWER STATION 'H' Phase | 4152520.61 | 3644990.31 | 461391.18 | 4106381.49
4 SS - Technical Service | 295 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHAT Al ARAB 400/132kV SS | 266 |  | SHAT Al ARAB 400/132kV SS | 1096738.5 | 1096738.5 | 0 | 1096738.5
Marsa Matrouh 500KV | Inv.40 Borg Alarab | 40 | Marsa Matrouh 500KV40 | 5469207.46 | 4777357.59 | 574266.78 | 5351624.37
Marsa Matrouh 500KV | Inv.41 Borg Alarab | 41 | Marsa Matrouh 500KV41 | 10215165.34 | 7314062.88 | 1072592.36 | 8386655.24
Marsa Matrouh 500KV | Inv.43 Borg Alarab | 43 | Marsa Matrouh 500KV43 | 23264035.62 | 16657052.82 | 2442723.74 | 19099776.56
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 20 | 20 | Benban 500 K.V / 100 K.M20 | 1542525.84 | 1188693.31 | 161965.21 | 1350658.52
EDNC Retail & Offices Civil | SOREAL-IPC07 | 7 | EDNC Retail & Offices Civil7 | 46252048.05 | 38197130.9705 | 11112412.04 | 49309543.0105
Sodic Club House | VO-SODIC CULB-IPC01 | 1 | Sodic Club House1 | 463906.48 | 13881.354 | 0 | 13881.354
Ministries Buildings | MIN SHELL-IPC04 | 4 | Ministries Buildings4 | 34298619.7 | 21929379.985 | 7309793.955 | 29239173.94
Fish Market | SOUQ ELSAMEK ELCTROF |  | Fish Market | 4026352.38 | 2008212.379 | 1715149 | 3723361.379
Ministries Buildings | MIN.SHELL-IPC05 | 5 | Ministries Buildings5 | 22857093.65 | 14328225 | 5157030.6 | 19485255.6
Elco Steel 220/33 KV SS | 522 |  | Elco Steel 220/33 KV SS | 173928.97 | 365250.84 | 0 | 182625.42
Assuit PP (CP-118) | 512 |  | Assuit PP (CP-118) | 1818894.09 | 1623362.97 | 286475.82 | 1909838.79
Elco Steel 220/33 KV SS | 1903210007 |  | Elco Steel 220/33 KV SS | 2652793.71 | 2785433.4 | 0 | 2785433.4
Elco Steel 220/33 KV SS | 521 |  | Elco Steel 220/33 KV SS | 24234.26 | 25445.97 | 0 | 25445.97
Elco Steel 220/33 KV SS | 1904210010 |  | Elco Steel 220/33 KV SS | 657082 | 689936.1 | 0 | 689936.1
Akhmem Assiut | Inv.23Assuit Akhmem$ | 23 | Akhmem Assiut23 | 762952.66 | 615405.36 | 0 | 615405.36
Toshka GIS 500 kV | Toshka Sub Inv. 08 | 8 | Toshka GIS 500 kV8 | 57678393.93 | 32847455.1 | 15140578.41 | 47988033.51
Toshka GIS 500 kV | Toshka Sub Inv. 07 | 7 | Toshka GIS 500 kV7 | 89330611.48 | 56095136.22 | 23449285.51 | 79544421.73
Toshka GIS 500 kV | Toshka Sub Inv. 04 | 4 | Toshka GIS 500 kV4 | 9162410.86 | 4502990.71 | 2405132.85 | 6908123.56
Safir bridge | FPC |  | Safir bridge | 642300 | 0 | 0 | 635877
Al Mostathmreen GIS Substation | MOS-VO-CLAIM |  | Al Mostathmreen GIS Substation | 2000000 | 2000000 | 0 | 2000000
Marsa Matrouh 500KV | Inv.20Usd borg alarb | 20 | Marsa Matrouh 500KV20 | 497761.9 | 432327.8 | 52265 | 484592.8
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .18 | 18 | Benban 3/ Toshka 2 LOT 418 | 17240856.77 | 13568145.27 | 1810289.96 | 15378435.23
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .4 | 4 | Benban 3/ Toshka 2 LOT 44 | 3108120.7 | 2396365.15 | 326352.67 | 2722717.82
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .7 | 7 | Benban 3/ Toshka 2 LOT 47 | 16280991.51 | 10843143.2 | 1709504.11 | 12552647.31
Benban 3/ Toshka 2 LOT 4 | Ref-Ret-Toshka Lot4$ |  | Benban 3/ Toshka 2 LOT 4 | 821146.29 | 787059.18 | 34087.11 | 821146.29
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $1 | 1 | Benban 3/ Toshka 2 LOT 41 | 193691.41 | 162700.78 | 20337.6 | 183038.38
CFC Podium 2 | CFC IPC023 | 23 | CFC Podium 223 | 19569971.41 | 15440458.9205 | 1462273.54 | 16902732.4605
Assuit PP (CP-118) | 541 |  | Assuit PP (CP-118) | 2960039.95 | 2612235.26 | 466206.29 | 3078441.55
Royal City | ROYAL CITY-IPC(7) | 7 | Royal City7 | 11315586.82 | 8703262.891 | 1686321.23 | 10389584.121
Royal City | ROYAL CITY-IPC25 | 25 | Royal City25 | 17584623.17 | 9972683.9685 | 5048068.09 | 15020752.0585
Ismailiya East Substation | ISE-CW-EGP-21 | 21 | Ismailiya East Substation21 | 1368194 | 1012463.56 | 205229.1 | 1217692.66
SHATRA 400/132kV SS | 299 |  | SHATRA 400/132kV SS | 762454.65 | 762454.65 | 0 | 762454.65
Ismailiya East Substation | ISE-SD-EURO-03 | 3 | Ismailiya East Substation3 | 2044384.61 | 1664874.01 | 164850.22 | 1829724.23
Manshiet Nasser Substation | 535 |  | Manshiet Nasser Substation | 702446.4 | 256448.7 | 0 | 256448.7
DPW Onshore Port & Terminal | DP WORLD-IPC11 | 11 | DPW Onshore Port & Terminal11 | 102020049.91 | 75494532.33 | 15303007.49 | 90797539.82
Akhmem - Qena | Inv.49 Qena Akhmem | 49 | Akhmem - Qena49 | 68054750.3 | 48967466.83 | 8197931.14 | 57165397.97
AWEER POWER STATION 'H' Phase | 10388 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
Canal Sugar OHTL | Inv.06 Sugar OHTL | 6 | Canal Sugar OHTL6 | 7441226.84 | 5878569.2 | 1116184.03 | 6994753.23
Lekela 250MW Wind Farm | LEKELA IPC014 | 14 | Lekela 250MW Wind Farm14 | 18187988.27 | 12931636.6285 | 6018471.255 | 18950107.8835
Lekela 250MW Wind Farm | LEKELA-IPC09 | 9 | Lekela 250MW Wind Farm9 | 21219483.49 | 18594958.1945 | 3509999.5 | 22104957.6945
Lekela 250MW Wind Farm | LEKELA-IPC07 | 7 | Lekela 250MW Wind Farm7 | 17619865.65 | 15073158.3375 | 3264476.755 | 18337635.0925
Toshka GIS 500 kV | Toshka Sub Inv. 20 $ | 20 | Toshka GIS 500 kV20 | 8473.33 | 4533.35 | 2224.25 | 6757.6
Toshka GIS 500 kV | Toshka Sub Inv. 14 $ | 14 | Toshka GIS 500 kV14 | 14498.29 | 7962.76 | 3805.8 | 11768.56
Toshka GIS 500 kV | Toshka Sub Inv. 13 $ | 13 | Toshka GIS 500 kV13 | 14498.29 | 7962.76 | 3805.8 | 11768.56
EMAAR-Pkg#162/163- Marassi | PKG#162 - IPC03 | 3 | EMAAR-Pkg#162/163- Marassi3 | 6446622.34 | 5119599.327 | 655105.77 | 5774705.097
Beni Suef Add-on Sales | 2002210024 |  | Beni Suef Add-on Sales | 45000 | 50850 | 0 | 50850
IKEA Extension MoA | IKEA-IPC04 | 4 | IKEA Extension MoA4 | 12574283.57 | 8514192.76 | 1013594.38 | 9527787.14
SHAT Al ARAB 400/132kV SS | 303 |  | SHAT Al ARAB 400/132kV SS | 2354642.18 | 2354642.18 | 0 | 2354642.18
AWEER POWER STATION 'H' Phase | IMP-031 | 31 | AWEER POWER STATION 'H' Phase31 | 627024.39 | 572087.95 | 0 | 572087.95
Dubai Port | 10014 |  | Dubai Port | 41428.63 | 36747.19 | 0 | 36747.19
Ministry Building EPOXY | 10016 |  | Ministry Building EPOXY | 76145.16 | 71576.45 | 0 | 71576.45
Ministry Building EPOXY | 10015 |  | Ministry Building EPOXY | 34960 | 32862.4 | 0 | 32862.4
Al-Kayan | 10021 |  | Al-Kayan | 27716 | 26053.04 | 0 | 26053.04
Multi Sport Hall | 10041 |  | Multi Sport Hall | 401155 | 356932.95 | 0 | 356932.95
Ministries Building ROOF | 10003 |  | Ministries Building ROOF | 138261.5 | 129965.8 | 0 | 129965.8
EMAAR-Pkg#162/163- Marassi | pkg#163 ipc 21 | 21 | EMAAR-Pkg#162/163- Marassi21 | 5908870.81 | 5666249.3105 | 742095.54 | 6408344.8505
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam Equ Inv 1 | 1 | Marsa Alam/ Bernes LOT2 OHTL1 | 24729788.77 | 13790114.92 | 2679730.5 | 16469845.42
4 SS - Technical Service | 306 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
MOTHANA 400/132kV SS | 315 |  | MOTHANA 400/132kV SS | 38529.77 | 38529.77 | 0 | 38529.77
MOTHANA 400/132kV SS | 319 |  | MOTHANA 400/132kV SS | 46429.57 | 46429.57 | 0 | 46429.57
Marsa Matrouh 500KV | Inv.69 Borg Alarab | 69 | Marsa Matrouh 500KV69 | 8195904.76 | 6728839.95 | 0 | 6728839.95
Manshiet Nasser Substation | 531 |  | Manshiet Nasser Substation | 232430.43 | 174664.95 | 37409.42 | 212074.37
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC10 | 10 | EMAAR- Pkg 140-ITP-Mivida10 | 6612227.79 | 5679423.0695 | 726755.74 | 6406178.8095
Miscellaneous Projects | 2004210008 |  | Miscellaneous Projects | 29110.15 | 29413.9 | 0 | 29527.82
Marsa Matrouh 500KV | Inv.73 Borg Alarab | 73 | Marsa Matrouh 500KV73 | 1026992.63 | 1004915.2 | 0 | 1004915.2
IKEA Extension MoA | IKEA - IPC 05 | 5 | IKEA Extension MoA5 | 9421690.84 | 7739970.29 | 952538.84 | 8692509.13
South Helwan PP (CP-117) | 2004210004 |  | South Helwan PP (CP-117) | 35208.17 | 31116.42 | 5555.72 | 36672.14
Ext.110 S. Military 220 Kv S/S | Cr. Adv MILITARY Ext |  | Ext.110 S. Military 220 Kv S/S | 0 | 0 | -849955 | -849955
Abu Qir PP (CP-117) | 200000 |  | Abu Qir PP (CP-117) | 595980 | 2020372.2 | 0 | 673457.4
Cairo Capital Cables Tunnel | Tunnel Inv. 2 | 2 | Cairo Capital Cables Tunnel2 | 34582914.95 | 23271071.9 | 8645728.74 | 31916800.64
LAYAN Substation | 11744 |  | LAYAN Substation | 157084.49 | 265472.789 | 0 | 132736.3945
LAYAN Substation | 10462 |  | LAYAN Substation | 4777349.72 | 3965200.26 | 0 | 3965200.26
LAYAN Substation | 10223 |  | LAYAN Substation | 394584.492 | 327505.01 | 0 | 327505.01
ESU Ph2-Enabling & Struc | E.S.U-PH2-IPC02 | 2 | ESU Ph2-Enabling & Struc2 | 19788850.1 | 13318143.9085 | 6233487.78 | 19551631.6885
Mivida | IPC_4_Mivida | 4 | Mivida4 | 171950 | 170230.5 | 0 | 170230.5
Banha PP (CP-117) | Adjust receivable |  | Banha PP (CP-117) | 6111.71 | 6111.71 | 0 | 6111.71
Ain-Sokhna PP (CP-117) | adjust rec.180137 |  | Ain-Sokhna PP (CP-117) | 5000.88 | 5000.88 | 0 | 5000.88
MAYSAN 400/132kV SS | 350 |  | MAYSAN 400/132kV SS | 1949503.47 | 1949503.47 | 0 | 1949503.47
MOTHANA 400/132kV SS | 339 |  | MOTHANA 400/132kV SS | 803170.22 | 803170.22 | 0 | 803170.22
Miscellaneous Projects | 2006210008 |  | Miscellaneous Projects | -8384.62 | -9558.4668 | 0 | -9558.4668
DoubleTree Mangroovy ElGouna | mangrove rent-ipc04 | 4 | DoubleTree Mangroovy ElGouna4 | 16112.5 | 16757 | 0 | 16757
Al-Shabab PP Phase II (CP-117) | 2002210020 |  | Al-Shabab PP Phase II (CP-117) | 2104756.26 | 1532686.78 | 681464.3 | 2214151.08
Latin Compound - New Alamin | INV(10)300420 | 10 | Latin Compound - New Alamin10 | 168280 | 139591.24 | 0 | 139591.24
El Katameya Mall | inv(10 )29720 | 10 | El Katameya Mall10 | 183120 | 153277.71 | 0 | 153277.71
Giza North PP Ph I,II (CP-117) | 2001210014 |  | Giza North PP Ph I,II (CP-117) | 216000 | 216000 | 0 | 216000
W Dam PP Phase II (CP-117) | 2002210028 |  | W Dam PP Phase II (CP-117) | 10030.51 | 10447.58 | 0 | 10447.58
W Dam PP Phase II (CP-117) | 2002210026 |  | W Dam PP Phase II (CP-117) | 199624.51 | 207924.9 | 0 | 207924.9
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .1 | 1 | Benban 3/ Toshka 2 LOT 41 | 285228.43 | 214916.17 | 29948.99 | 244865.16
Samaya Electronics factory | INV(1)Fainal12-2020 | 1 | Samaya Electronics factory1 | 880000 | 880000 | 0 | 880000
MOTHANA 400/132kV SS | 345 |  | MOTHANA 400/132kV SS | 6054750.89 | 6054750.89 | 0 | 6054750.89
Benban 500 K.V / 100 K.M | Benban Lot1 Inv14USD | 14 | Benban 500 K.V / 100 K.M14 | 2939950.85 | 2461143.4 | 308694.84 | 2769838.24
Kayan Landscape | KAYAN ROUDA-IPC02 | 2 | Kayan Landscape2 | 12633326.95 | 95 | 11571630 | 11571725
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 09 | 9 | Suez Gulf/S4 - 500KV OHTL9 | 1277396.49 | 901707.68 | 134126.63 | 1035834.31
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 05 | 5 | Suez Gulf/S4 - 500KV OHTL5 | 1866661.38 | 1420520.26 | 195999.45 | 1616519.71
East Owainat 5 LOTS | East Owainat Inv. 04 | 4 | East Owainat 5 LOTS4 | 88684448.28 | 36183246.89 | 46559335.35 | 82742582.24
Royal City | ROYAL CITY- IPC32 | 32 | Royal City32 | 4150837.54 | 2151533.367 | 1027610.78 | 3179144.147
Minis Building(Polyurethane) | 10216 |  | Minis Building(Polyurethane) | 414221.73 | 368533.59 | 0 | 368533.59
AWEER POWER STATION 'H' Phase | Eng-28 | 28 | AWEER POWER STATION 'H' Phase28 | 293486.56 | 308160.888 | 0 | 308160.888
Bahr El Baqar Treatment Plant | IPC#1 | 1 | Bahr El Baqar Treatment Plant1 | 1212810.3 | 1088370 | 0 | 1088370
Sodic East | 10233 |  | Sodic East | 1030744.99 | 534792.31 | 0 | 534792.31
Nuweibaa (Swro) | 2004210007 |  | Nuweibaa (Swro) | 491518.2 | 393214.56 | 98303.64 | 491518.2
DoubleTree Mangroovy ElGouna | MANGROOVE-IPC07 | 7 | DoubleTree Mangroovy ElGouna7 | 3133496.53 | 2166123.4165 | 822542.84 | 2988666.2565
Marsa Matrouh 500KV | Inv.46 Borg Alarab | 46 | Marsa Matrouh 500KV46 | 10217560.62 | 8925038.24 | 1072843.87 | 9997882.11
Ministries A17-A18 | 10214 |  | Ministries A17-A18 | 687998.3 | 581270.76 | 0 | 581270.76
El Banna project | 444 |  | El Banna project | 591.819 | 0 | 591.819 | 591.819
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .10 | 10 | Benban 3/ Toshka 2 LOT 410 | 3039893.5 | 2495754.6 | 319188.82 | 2814943.42
Ghana | 40A/P/10/ER/2017/USD |  | Ghana | 317437.42 | 317437.42 | 0 | 317437.42
Racecores 3092-16 132KV C | 11367 |  | Racecores 3092-16 132KV C | 288932.7876 | 976592.84 | 0 | 244148.21
Racecores 3092-16 132KV C | 11293 |  | Racecores 3092-16 132KV C | 808180.13 | 4024737.06 | 0 | 670789.51
Racecores 3092-16 132KV C | 11024 |  | Racecores 3092-16 132KV C | 3197203.6 | 2653678.99 | 0 | 2653678.99
Racecores 3092-16 132KV C | 11023 |  | Racecores 3092-16 132KV C | 339157.1 | 1407501.95 | 0 | 281500.39
Sodic East | IPC_13_rowad_s_east | 13 | Sodic East13 | 558167.95 | 459462.47 | 0 | 459462.47
Minis Building(Polyurethane) | IPC_13_Rowad_poly | 13 | Minis Building(Polyurethane)13 | 246382.79 | 219280.68 | 0 | 219280.68
Badr | Inv. 22 Badr | 22 | Badr22 | 10694183 | 7940011.5 | 1604127.45 | 9544138.95
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $5 | 5 | Benban 3/ Toshka 2 LOT 45 | 2063994.43 | 1733755.31 | 216719.42 | 1950474.73
NUCA R05 - Z02 | R05(2) ipc 36 | 36 | NUCA R05 - Z0236 | 22042535.4 | 18265544.716 | 2344204 | 20609748.716
LRT - El Shorouk Bridge | IPC#3 | 3 | LRT - El Shorouk Bridge3 | 324540 | 290950.11 | 0 | 290950.11
Rail Way Tunnel Zagazig | IPC#3 | 3 | Rail Way Tunnel Zagazig3 | 755500 | 704126 | 0 | 704126
Latin Compound - New Alamin | INV(11)100520 | 11 | Latin Compound - New Alamin11 | 116760 | 95592.65 | 0 | 95592.65
El Katameya Mall | inv(4)260120 | 4 | El Katameya Mall4 | 861126 | 689960 | 0 | 689960
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .6 | 6 | Benban 3/ Toshka 2 LOT 46 | 32160469.9 | 21418880.19 | 3376849.34 | 24795729.53
ESU Ph2-Enabling & Struc | E.S.U2-MEP-IPC08 | 8 | ESU Ph2-Enabling & Struc8 | 69627433.52 | 25127325.53 | 0 | 25127325.53
Beni Seuf - 358 | Inv.2 Temmay Amded | 2 | Beni Seuf - 3582 | 21463160.11 | 15663959.2 | 3671792.45 | 19335751.65
CFC Podium 2 | CFC-IPC10 | 10 | CFC Podium 210 | 52098964.43 | 39448595.5715 | 7527197.56 | 46975793.1315
OHTL Mostakable East Boundary | Inv. 03 Future OHTL | 3 | OHTL Mostakable East Boundary3 | 11586090.14 | 9616454.81 | 2433078.93 | 12049533.74
Taval Sarai 52 | IPC_9_Saray | 9 | Taval Sarai 529 | 446889.6 | 325460.13 | 0 | 325460.13
Ministries A17-A18 | IPC_6_gama_ministry | 6 | Ministries A17-A186 | 210000 | 178395 | 0 | 178395
SHATRA 400/132kV SS | 371 |  | SHATRA 400/132kV SS | 1112566.76 | 1112566.76 | 0 | 1112566.76
Oasis Buildings- New Capital | inv ( 11 ) 11-11-20 | 11 | Oasis Buildings- New Capital11 | 2857656.4 | 2739063.67 | 0 | 2739063.67
4 SS - Technical Service | 381 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Abas El Akkad Bridge | FPC |  | Abas El Akkad Bridge | 370000 | 109010 | 0 | 109010
AWEER POWER STATION 'H' Phase | IMP051-50 | 50 | AWEER POWER STATION 'H' Phase50 | 1053708.68 | 1042000.81 | 0 | 1042000.81
Cairo-Alex Railway | Cairo-alex ipc 39 | 39 | Cairo-Alex Railway39 | 20355575.24 | 14136532.37 | 2137335.4 | 16273867.77
Cairo-Alex Railway | Cairo-Alex ipc 31 | 31 | Cairo-Alex Railway31 | 13108737.6 | 9103619.27 | 1376417.45 | 10480036.72
Cairo-Alex Railway | CAIRO-ALEX IPC20 | 20 | Cairo-Alex Railway20 | 31478677.3 | 21861542.435 | 3305261.12 | 25166803.555
Racecores 3092-17 132KV E | 11540 |  | Racecores 3092-17 132KV E | 131913.7695 | 111467.138 | 0 | 111467.138
Racecores 3092-17 132KV E | 11450 |  | Racecores 3092-17 132KV E | 331266.34 | 549901.11 | 0 | 274950.555
Racecores 3092-17 132KV E | 11289 |  | Racecores 3092-17 132KV E | 210133.33 | 174410.66 | 0 | 174410.66
Oasis Buildings- New Capital | inv ( 10 ) 20-10-20 | 10 | Oasis Buildings- New Capital10 | 2553158.44 | 2310191.58 | 0 | 2310191.58
EMAAR-Pkg#162/163- Marassi | PKG#163 - IPC04 | 4 | EMAAR-Pkg#162/163- Marassi4 | 3898862.65 | 4503200.4825 | 1110090.52 | 5613291.0025
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 31 | 31 | ORA ZED - Ph 01B - Pkgs A&D31 | 21322773.91 | 10153641.2135 | 11425404.25 | 21579045.4635
ORA ZED - Ph 01B - Pkgs A&D | ORA ph1 ipc (29) | 29 | ORA ZED - Ph 01B - Pkgs A&D29 | 23928989.08 | 10687601.99 | 11496925.55 | 22184527.54
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED IPC12 | 12 | ORA ZED - Ph 01B - Pkgs A&D12 | 33050531.68 | 26088449.724 | 3104008.18 | 29192457.904
NUCA R05 - Z02 | R5 FINSHING-IPC05** | 5 | NUCA R05 - Z025 | 14524996.2 | 22412957.55 | 3513309.85 | 12963133.7
Toshka GIS 500 kV | Toshka Sub Inv. 04 $ | 4 | Toshka GIS 500 kV4 | 4243622.98 | 2863582.78 | 1113951.03 | 3977533.81
Toshka GIS 500 kV | Toshka Sub Inv. 08 $ | 8 | Toshka GIS 500 kV8 | 86989.71 | 49566.56 | 22834.8 | 72401.36
Miscellaneous Projects | 2009210011 |  | Miscellaneous Projects | 118487.2 | 135075.41 | 0 | 135075.41
Miscellaneous Projects | 2007210011 |  | Miscellaneous Projects | 151344.64 | 172532.8896 | 0 | 172532.8896
Miscellaneous Projects | 2007210010 |  | Miscellaneous Projects | 118487.2 | 135075.408 | 0 | 135075.408
Ministries Buildings | MIN.ANASER WATER-03 | 3 | Ministries Buildings3 | 1513476 | 956020 | 318676 | 1274696
Sodic East | IPC_17_Rowad_S_east | 17 | Sodic East17 | 341704.4 | 240579.246 | 0 | 240579.246
Manshiet Nasser Substation | 2008210009 |  | Manshiet Nasser Substation | 17607.02 | 3397.85 | 2780.06 | 6177.91
Toshka GIS 500 kV | Toshka Sub Inv. 02 | 2 | Toshka GIS 500 kV2 | 11781697.61 | 6599339.66 | 3092695.62 | 9692035.28
Royal City | ROYAL CITY-IPC33 | 33 | Royal City33 | 11787102.13 | 8559155.6765 | 4188755.42 | 12747911.0965
Miscellaneous Projects | 2007210004 |  | Miscellaneous Projects | 10895.41 | 12093.91 | 0 | 12093.91
Koning Food V2 - LP-08-20 | 5 |  | Koning Food V2 - LP-08-20 | 67587.71 | 77049.99 | 0 | 77049.99
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC18 | 18 | EMAAR- Pkg 140-ITP-Mivida18 | 4603925.77 | 3831058.9285 | 490233.61 | 4321292.5385
Toshka GIS 500 kV | Toshka Sub Inv. 18 $ | 18 | Toshka GIS 500 kV18 | 22453.52 | 12581.91 | 5894.05 | 18475.96
Port Saad Industiral zone | IPC-7 | 7 | Port Saad Industiral zone7 | 740658 | 713253.65 | 0 | 713253.65
El Katameya Mall | inv ( 15 ) 12-2020 | 15 | El Katameya Mall15 | 546000 | 447055.25 | 0 | 447055.25
4 SS - Technical Service | 388 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Mohamed Aly Fahmy Lock&Load | M.A.FAHMYL&L-FINAL |  | Mohamed Aly Fahmy Lock&Load | 332310 | 458890 | 152975 | 611865
AWEER POWER STATION 'H' Phase | IMP-059 | 59 | AWEER POWER STATION 'H' Phase59 | 1082826.83 | 1136968.1715 | 0 | 1136968.1715
El-Nyaba El-Ama | El-Nayba Inv. 2 | 2 | El-Nyaba El-Ama2 | 1719317.55 | 1405134.12 | 128948.85 | 1534082.97
R5 | inv ( 15 )25-12-2020 | 15 | R515 | 894000 | 413577.86 | 0 | 824289.25
Mohamed Ali Palace | IPC_3_Rowad_M.Ali | 3 | Mohamed Ali Palace3 | 22480.2 | 16149.368 | 0 | 16149.368
El Mostaqbal lock & load | MOSTQBALL&L-IPC02F | 2 | El Mostaqbal lock & load2 | 410006 | 182760 | 182767 | 365527
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $4 | 4 | Benban 3/ Toshka 2 LOT 44 | 1018343.2 | 855408.28 | 106926.04 | 962334.32
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $6 | 6 | Benban 3/ Toshka 2 LOT 46 | 207833.62 | 174580.24 | 21822.53 | 196402.77
marassi inland marina | IPC#9 | 9 | marassi inland marina9 | 546388.78 | 32867.96 | 0 | 306823.06
Huawei Technologies LP-11-20 | 11 |  | Huawei Technologies LP-11-20 | 220000 | 248600 | 0 | 248600
Kattameya Creeks | KATAMYA CREEKS IPC14 | 14 | Kattameya Creeks14 | 48574512.67 | 45904629.9935 | 4560213.18 | 50464843.1735
Kattameya Creeks | Kattameya IPC04 | 4 | Kattameya Creeks4 | 31881858.16 | 29687637.308 | 3469495.18 | 33157132.488
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.10 | 10 | Toshka 2/Owinat East LOT2 OHTL10 | 16006857.57 | 0 | 1680720.05 | 1680720.05
Canal Sugar OHTL | Inv.03 $ Sugar OHTL | 3 | Canal Sugar OHTL3 | 340101 | 284629.38 | 35065.56 | 319694.94
Royal City | ROYAL CITY-IPC36 | 36 | Royal City36 | 8120768.31 | 5231425.2055 | 0 | 5231425.2055
Museum of Egyp. Civilization | IPC#3 PhaseII | 3 | Museum of Egyp. Civilization3 | 496630 | 438036.45 | 0 | 438036.45
Daraw Bridge | IPC#2 | 2 | Daraw Bridge2 | 2478560 | 2029775.96 | 0 | 2029775.96
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC16 | 16 | EMAAR- Pkg 140-ITP-Mivida16 | 19380294.6 | 13266917.76 | 1350448.21 | 14617365.97
Ahl Misr Walkway | IPC#1 Ahl Misr | 1 | Ahl Misr Walkway1 | 1546834.5 | 1490375.03 | 0 | 1490375.03
CFC Podium 2 | CFC-IPC14 | 14 | CFC Podium 214 | 29172801.68 | 19708944.274 | 3762123.59 | 23471067.864
Miscellaneous Projects | 2011210007 |  | Miscellaneous Projects | 34725 | 39239.25 | 0 | 39239.25
Taval Sarai 52 | Adj.06-2022 | 2022 | Taval Sarai 522022 | 83165.78 | 63165.784 | 0 | 63165.784
Koning Food V2 - LP-08-20 | 9 |  | Koning Food V2 - LP-08-20 | 2114.38 | 2410.4 | 0 | 2410.4
BKG#178-Lagoon Discharge | PKG #178 IPC05 | 5 | BKG#178-Lagoon Discharge5 | 10300781.79 | 9666283.6995 | 408395.93 | 10074679.6295
Ghana Street lighting | 5MIDA Sply. Inv. |  | Ghana Street lighting | 280444.21 | 252399.78 | 0 | 252399.78
Cairo Capital S1 | Inv.9Project S1Fina | 9 | Cairo Capital S19 | 143454958.65 | 112402834.94 | 21518234.87 | 133921069.81
Canal Sugar S/s | Inv 5 $ Sugar S/s | 5 | Canal Sugar S/s5 | 97902.6 | 74699.68 | 14685.39 | 89385.07
DoubleTree Mangroovy ElGouna | MANGROVE WALL-IPC03 | 3 | DoubleTree Mangroovy ElGouna3 | 189255 | 165325.2 | 0 | 165325.2
Latin Compound - New Alamin | inv ( 21 ) 11-12-20 | 21 | Latin Compound - New Alamin21 | 383227.6 | 248906.33 | 76645.52 | 325551.85
Toshka-04 GIS Substation | Toshka Sub 4 Inv.3 $ | 3 | Toshka-04 GIS Substation3 | 432429.07 | 0 | 45405.05 | 45405.05
EGAT Pelletizing Plant | EGAT IPC07+ | 7 | EGAT Pelletizing Plant7 | 1175831.28 | 1088853.474 | 116611.05 | 1205464.524
Mohamed Ali Palace | IPC_4_Rowad_M.Ali | 4 | Mohamed Ali Palace4 | 80818.6 | 67887.62 | 0 | 67887.62
Ismailiya East Substation | ISE-SW-EGP-09 | 9 | Ismailiya East Substation9 | 356563 | 317341.07 | 0 | 317341.07
Beni Suef Substation R61 | BSF-SD-EURO-03 | 3 | Beni Suef Substation R613 | 7944201.1 | 4793506.78 | 0 | 4793506.78
IKEA Extension MoA | IKEA - IPC06 | 6 | IKEA Extension MoA6 | 5112809.05 | 4141935.79 | 628358.81 | 4770294.6
SHAT Al ARAB 400/132kV SS | 395 |  | SHAT Al ARAB 400/132kV SS | 1369521.06 | 1369521.06 | 0 | 1369521.06
Sodic East | IPC_22_Rowad_Seast | 22 | Sodic East22 | 228288.29 | 202149.28 | 0 | 202149.28
Tanzania hydropower Project | 2 |  | Tanzania hydropower Project | 152041.56 | 152041.56 | 0 | 152041.56
Hadaek ElAharam | FPC |  | Hadaek ElAharam | 900592.5 | 599713 | 0 | 599713
Maspiro Towers | FPC |  | Maspiro Towers | 556650 | 544124.2 | 0 | 544124.2
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC11 | 11 | EMAAR-Pkg#162/163- Marassi11 | 9303551.52 | 7840185.4928 | 0 | 7840185.4928
Koning Food V2 - LP-08-20 | 12 |  | Koning Food V2 - LP-08-20 | 13517.54 | 30820 | 0 | 15410
Suez Gulf/S4 - 500KV OHTL | Suez S4 Equ Inv. +1 |  | Suez Gulf/S4 - 500KV OHTL | 1261 | 1324.05 | 0 | 1324.05
AWEER POWER STATION 'H' Phase | LOC-013 | 13 | AWEER POWER STATION 'H' Phase13 | 1083247.22 | 827963.34 | 120360.8 | 948324.14
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 03 | 3 | Suez Gulf/S4 - 500KV OHTL3 | 444301.13 | 371196.04 | 46651.62 | 417847.66
Ministries Buildings | MIN.SAHY&N-IPC02 | 2 | Ministries Buildings2 | 168220 | 66865 | 75200 | 142065
Zone(J) South Valley Toshka | South Valley Inv. 14 | 14 | Zone(J) South Valley Toshka14 | 29992616.95 | 22473314.85 | 3839055 | 26312369.85
Zone(J) South Valley Toshka | South Valley Inv. 05 | 5 | Zone(J) South Valley Toshka5 | 37030481.2 | 28216824.15 | 4739901.6 | 32956725.75
NUCA R05 - Z02 | R5PHASE2-IPC09 | 9 | NUCA R05 - Z029 | 19752275.4 | 15653276.7 | 1975227.6 | 17628504.3
MDF Factory | MDF FACTORY IPC11 | 11 | MDF Factory11 | 9266643.76 | 8835349.208 | 683594.29 | 9518943.498
Sodic East | IPC_23_SodicEast | 23 | Sodic East23 | 278336.98 | 246467.36 | 0 | 246467.36
New Babil 400/132KV Substation | 2103210016 |  | New Babil 400/132KV Substation | 211453.11 | 211453.11 | 0 | 211453.11
LAYAN Substation | 10527 |  | LAYAN Substation | 327177.32 | 543114.38 | 0 | 271557.19
R5 | inv(8)100620 | 8 | R58 | 1842000 | 276300 | 0 | 1698022.47
R5 | inv(17)28-2-21-R5 | 17 | R517 | 1296000 | 1199448 | 0 | 1199448
R5 | inv ( 16 ) R511-2-21 | 16 | R516 | 483000 | 446766.5 | 0 | 446766.5
El Sewedy University | Inv(4)300620 | 4 | El Sewedy University4 | 292158.15 | 14607.91 | 0 | 247493.3733
El Sewedy University | Inv(2)150420 | 2 | El Sewedy University2 | 553379.86 | 27668.99 | 0 | 481256.09
RING ROAD MARYOTIA EXPANSION | RING MARYITIA-IPC05 | 5 | RING ROAD MARYOTIA EXPANSION5 | 12516509.05 | 6453307.296 | 5000000 | 11453307.296
ESU Ph2-Enabling & Struc | E.S.U2-ARC&MEP-IPC12 | 12 | ESU Ph2-Enabling & Struc12 | 38061417.81 | 23340124.2605 | 2482953.77 | 25823078.0305
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC011 | 11 | EMAAR-Pkg#162/163- Marassi11 | 0.0001 | 1728865.5301 | 207927.24 | 1936792.7701
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC05 | 5 | EMAAR-Pkg#162/163- Marassi5 | 0.001 | 1890262.721 | 241883.6 | 2132146.321
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC10 | 10 | EMAAR-Pkg#162/163- Marassi10 | 3812993.56 | 2893980.578 | 743338.83 | 3637319.408
Koning Food V4 LP-01-21 | 46 |  | Koning Food V4 LP-01-21 | 62280.7 | 71000 | 0 | 71000
Kattameya Creeks | Kattameya IPC05 | 5 | Kattameya Creeks5 | 43155172.94 | 40007572.367 | 4873807.49 | 44881379.857
Kattameya Creeks | Katameya - IPC03 | 3 | Kattameya Creeks3 | 41751425.71 | 39570120.8955 | 3851361.84 | 43421482.7355
EDNC Retail & Offices Civil | Sodic Soreal IPC026 | 26 | EDNC Retail & Offices Civil26 | 45459659.77 | 33907888.6085 | 3686071.34 | 37593959.9485
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED PH.1 IPC07 | 7 | ORA ZED - Ph 01B - Pkgs A&D7 | 9268144.68 | 4340903.024 | 524341.16 | 4865244.184
Phosfat | Ref Retention fosfat |  | Phosfat | 360062.3 | 360062.3 | 0 | 360062.3
Mauritania Lot 1 | Inv.9 - Lot 1 | 9 | Mauritania Lot 19 | 73563.54 | 69885.36 | 0 | 69885.36
Mauritania Lot 1 | Inv.8 - Lot 1 | 8 | Mauritania Lot 18 | 71454.71 | 67881.97 | 0 | 67881.97
LAYYAH CCPP | 506 |  | LAYYAH CCPP | 12854700 | 11016258.75 | 2400425 | 13416683.75
DoubleTree Mangroovy ElGouna | Mangrove - IPC015 | 15 | DoubleTree Mangroovy ElGouna15 | 4199870.68 | 3002136.214 | 1008716.05 | 4010852.264
Diplomatic District - Infra | Diplo. Dist. IPC08 | 8 | Diplomatic District - Infra8 | 21256216.29 | 14841823.49 | 2025993.3 | 16867816.79
Air Force Project | Air Force Inv . 14 | 14 | Air Force Project14 | 4524624.26 | 3239516.96 | 1131156.05 | 4370673.01
Air Force Project | Air Force Inv . 13 | 13 | Air Force Project13 | 7847514 | 5618528.04 | 1961878.5 | 7580406.54
Air Force Project | Air Force Inv . 09 | 9 | Air Force Project9 | 5241355.52 | 3752405 | 1310338.85 | 5062743.85
Air Force Project | Air Force Inv . 02 | 2 | Air Force Project2 | 11154054.56 | 8253995 | 2788513.65 | 11042508.65
Faculty of Medicine | mansora uni ipc 15 | 15 | Faculty of Medicine15 | 14787583.81 | 12512110.79 | 739379.19 | 13251489.98
R5 Mix-Use Complex Project | R5-ZONE1-IPC6 | 6 | R5 Mix-Use Complex Project6 | 5139407 | 4207989.02 | 521813.76 | 4729802.78
Assuit PP (CP-118) | inv. 19-20 USD | 19 | Assuit PP (CP-118)19 | 351753.41 | 627879.84 | 110802.32 | 369341.08
NUCA R05 - Z02 | R5-ZONE 02- IPC02 | 2 | NUCA R05 - Z022 | 4448510 | 4886423.66 | 597472.17 | 5483895.83
NUCA R05 - Z02 | R5 - IPC17 | 17 | NUCA R05 - Z0217 | 40451064.68 | 28741122.464 | 3615988 | 32357110.464
GOV2 - Infra | GOV2 ipc25 | 25 | GOV2 - Infra25 | 8593894.33 | 3564488.5967 | 543005.59 | 4107494.1867
Group # 1 - 25 LX | Reailway PSP Inv. 04 | 4 | Group # 1 - 25 LX4 | 840000 | 831600 | 0 | 831600
LAYAN Substation | 10602 |  | LAYAN Substation | 221632.06 | 749116.36 | 0 | 187279.09
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 1 Equ | 1 | Hosh Essa 220 KV OHTL1 | 7784834.86 | 4673291.85 | 822803.11 | 5496094.96
Toshka GIS 500 kV | Toshka Sub Inv. 10 $ | 10 | Toshka GIS 500 kV10 | 226768.1 | 145305.66 | 59526.63 | 204832.29
SHATRA 400/132kV SS | 413 |  | SHATRA 400/132kV SS | 4636804.66 | 4636804.66 | 0 | 4636804.66
33KV Canal Farm Grid | Inv. +12 Farm |  | 33KV Canal Farm Grid | 655399.49 | 500069.81 | 98309.92 | 598379.73
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC014 | 14 | EMAAR-Pkg#162/163- Marassi14 | 0.001 | 3890540.431 | 467907.62 | 4358448.051
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC021.C | 21 | EMAAR-PKG# 101-UPTOWN21 | 0.001 | 0.0011 | 0 | 0.0011
EGAT Pelletizing Plant | EGAT IPC02 | 2 | EGAT Pelletizing Plant2 | 10496612.58 | 10019256.4705 | 897220.53 | 10916477.0005
LAYAN Substation | 10603 |  | LAYAN Substation | 51814.4 | 87566.34 | 0 | 43783.17
158E/2019 33kv Project | 10624 |  | 158E/2019 33kv Project | 731700 | 1975590 | 0 | 658530
seashell Playa | IPC-13-Playa | 13 | seashell Playa13 | 894385.1 | 619657.06 | 97184 | 716841.06
Marassi Inner Marina - PKG178 | IPC#2 - Marassi#178 | 2 | Marassi Inner Marina - PKG1782 | 797294 | 244127.1 | 0 | 709591.66
EGAT Pelletizing Plant | EGAT-IPC16 | 16 | EGAT Pelletizing Plant16 | 14282809.35 | 14096166.6275 | 757955.1 | 14854121.7275
10Th of Ramadan LRT | LRT 10Ramadan Inv.01 | 1 | 10Th of Ramadan LRT1 | 4534198.52 | 2520041.33 | 453419.85 | 2973461.18
R05 | IPC_1_R5_RME | 1 | R051 | 77798.38 | 52616.82 | 0 | 52616.82
AWEER POWER STATION 'H' Phase | IMP/064 |  | AWEER POWER STATION 'H' Phase | 1172089.69 | 1230694.1693 | 0 | 1230694.1693
Miscellaneous Projects | 2009210016 |  | Miscellaneous Projects | 151344.64 | 172532.89 | 0 | 172532.89
Miscellaneous Projects | 2009210015 |  | Miscellaneous Projects | 118487.2 | 135075.41 | 0 | 135075.41
ORA ZED - Ph 01B - Pkgs A&D | ora zed ipc15 | 15 | ORA ZED - Ph 01B - Pkgs A&D15 | 27710999.54 | 27179982.227 | 3259818.36 | 30439800.587
ORA ZED-Ph 2-Pkgs A&D | ORA PH2 IPC 19 | 19 | ORA ZED-Ph 2-Pkgs A&D19 | 8053943.79 | 7571824.5446 | 0 | 7571824.5446
Faculty of Medicine | Mansoura UNI IPC03 | 3 | Faculty of Medicine3 | 25228213.33 | 21346449.9965 | 1261410.67 | 22607860.6665
NUCA R05 - Z02 | R05 Zone1 IPC031 | 31 | NUCA R05 - Z0231 | 6928611.25 | 1721656.15 | 432416.15 | 2154072.3
LRT Project | IPC_4_LRT | 4 | LRT Project4 | 48870 | 41028.55 | 0 | 41028.55
Diplomatic District - Infra | Diplo Dist IPC03 | 3 | Diplomatic District - Infra3 | 454008.2 | 3105738.66 | 366118.54 | 3471857.2
Borg El Arab Bridge - Km 21 | IPC001 Kilo 21 | 1 | Borg El Arab Bridge - Km 211 | 1450916 | 900000 | 0 | 900000
RING ROAD MARYOTIA EXPANSION | Maryotia IPC09 | 9 | RING ROAD MARYOTIA EXPANSION9 | 9883488.33 | 3856121.53 | 5000000 | 8856121.53
Zone(J) South Valley Toshka | South Valley Inv. 08 | 8 | Zone(J) South Valley Toshka8 | 29880449.15 | 22768493.05 | 3824697.5 | 26593190.55
Marsa Alam/ Bernes LOT2 OHTL | Ref.Ret marsa Alam |  | Marsa Alam/ Bernes LOT2 OHTL | 1440292.025 | 2880584.05 | 0 | 1440292.025
Mostakbal 2 Package No. (8) | Mostakbal-8 Inv.03 | 3 | Mostakbal 2 Package No. (8)3 | 22861094.86 | 18974708.73 | 4800829.92 | 23775538.65
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC05 | 5 | ElSewedy HQ Internal Finishing5 | 6032812.38 | 3447418.189 | 1357462.2 | 4804880.389
Mansoura University | IPC03 - Mansoura | 3 | Mansoura University3 | 132413.92 | 131089.78 | 0 | 131089.78
EDNC Retail & Offices Civil | Sodic Soreal IPC031 | 31 | EDNC Retail & Offices Civil31 | 20856328.39 | 17493923.131 | 1136280.1985 | 18630203.3295
DoubleTree Mangroovy ElGouna | IPC05RENT-MANGROVY | 5 | DoubleTree Mangroovy ElGouna5 | 15000 | 15600 | 0 | 15600
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC017 | 17 | EMAAR-Pkg#162/163- Marassi17 | 0.0001 | 331162.2801 | 39828.23 | 370990.5101
Ain Sokhna Port Development | IPC#6 Sokhna Port | 6 | Ain Sokhna Port Development6 | 2194880 | 1694447.36 | 0 | 2063187.2
Ain Sokhna Port Development | IPC#2 - Sokhna Port | 2 | Ain Sokhna Port Development2 | 932824 | 872648.58 | 0 | 872648.58
Assuit PP (CP-118) | 2108210010 |  | Assuit PP (CP-118) | 165003.75 | 147265.84 | 25988.09 | 173253.93
RING ROAD MARYOTIA EXPANSION | Maryotia IPC010 | 10 | RING ROAD MARYOTIA EXPANSION10 | 17444582.38 | 10942755.33 | 5000000 | 15942755.33
SHAT Al ARAB 400/132kV SS | 424 |  | SHAT Al ARAB 400/132kV SS | 4634741.62 | 4634741.62 | 0 | 4634741.62
AWEER POWER STATION 'H' Phase | ENG/047 |  | AWEER POWER STATION 'H' Phase | 459843.86 | 482836.053 | 0 | 482836.053
Assuit PP (CP-118) | 2108210008 |  | Assuit PP (CP-118) | 3107208.26 | 2714138.3 | 489385.3 | 3203523.6
LAYAN Substation | 10823 |  | LAYAN Substation | 282320.7 | 468652.36 | 0 | 234326.18
Beni Suef Substation R61 | BSF-SD-EGP-03 | 3 | Beni Suef Substation R613 | 648000 | 576720 | 0 | 576720
ENR-Signaling Inst. | ENR-Sign Inst Inv02 | 2 | ENR-Signaling Inst.2 | 2907052.4 | 2441924.02 | 290705.24 | 2732629.26
Water pumping New Obour City | Wat Pump Obour Inv.1 | 1 | Water pumping New Obour City1 | 26712563.09 | 20413018.34 | 2804819.12 | 23217837.46
SHATRA 400/132kV SS | 386 |  | SHATRA 400/132kV SS | 1908512.08 | 1908512.08 | 0 | 1908512.08
MOTHANA 400/132kV SS | 415 |  | MOTHANA 400/132kV SS | 102959.11 | 102959.11 | 0 | 102959.11
Olympic Multi – Sports Hall | Olymipc Hall IPC06 | 6 | Olympic Multi – Sports Hall6 | 51027855.5 | 414025 | 23764386.15 | 43206241.15
Ain Sokhna Port Development | IPC#3 - Ain Sokhna P | 3 | Ain Sokhna Port Development3 | 1097440 | 1027834.55 | 0 | 1027834.55
Air Force Project | Air Force Inv . 17 | 17 | Air Force Project17 | 2559995.42 | 2472550 | 0 | 2472550
Racecores 3092-16 132KV C | 10966 |  | Racecores 3092-16 132KV C | 3123917.5 | 2592851.53 | 0 | 2592851.53
TZ – Offshore E&M Procurement | 430 |  | TZ – Offshore E&M Procurement | 2050.1 | 1640.08 | 410.02 | 2050.1
EGYTEC A1,A3 ( LP-05-21) | 44 |  | EGYTEC A1,A3 ( LP-05-21) | 2597090 | 1662137.6 | 1298545 | 2960682.6
Cables Egypt (LP-03-21) | 42 |  | Cables Egypt (LP-03-21) | 579060 | 355594.4 | 304530 | 660124.4
Hadaek ElAharam | IPC#1 | 1 | Hadaek ElAharam1 | 314087.5 | 267077.56 | 0 | 267077.56
Akhmem - Qena | Ret Qen-akh 8 T |  | Akhmem - Qena | 10000000 | 10000000 | 0 | 10000000
ENR-Signaling Inst. | ENR-Sign Inst Inv03 | 3 | ENR-Signaling Inst.3 | 3591140 | 3016557.6 | 359114 | 3375671.6
New Babil 400/132KV GIS Substa | 2112210001 |  | New Babil 400/132KV GIS Substa | 352324.8 | 352324.8 | 0 | 352324.8
Diplomatic District - Infra | Diplo Dist IPC07 | 7 | Diplomatic District - Infra7 | 20531079.1428 | 12611623.7628 | 1829209.53 | 14440833.2928
Benban 500 K.V / 100 K.M | Ref.1 benban Lot 1 T |  | Benban 500 K.V / 100 K.M | 4228160.14 | 4228160.14 | 0 | 4228160.14
Racecores 3092-17 132KV E | 11027 |  | Racecores 3092-17 132KV E | 1059711.84 | 879560.82 | 0 | 879560.82
MDF Factory | MDF IPC06 | 6 | MDF Factory6 | 17710147.67 | 17171362.1535 | 2532882.9 | 19704245.0535
Racecores 3092-16 132KV C | 11042 |  | Racecores 3092-16 132KV C | 9960 | 10458 | 0 | 10458
LP-24-21 Autostrada | 75 |  | LP-24-21 Autostrada | 1742695.64 | 1990457.1666 | 0 | 1990457.1666
Cairo Capital S1 | Ref. Capital S 1 T |  | Cairo Capital S1 | 54766270 | 54766270 | 0 | 54766270
Racecores 3092-16 132KV C | 11083 |  | Racecores 3092-16 132KV C | 10500 | 11025 | 0 | 11025
New Babil 400/132KV GIS Substa | 2112210008 |  | New Babil 400/132KV GIS Substa | 3676765.6 | 3676765.6 | 0 | 3676765.6
Mauritania-Lot 2 | Inv.15 – Lot 2 | 15 | Mauritania-Lot 215 | 339125.39 | 322112.87 | 0 | 322112.87
New Giza Teaching Hospital | new giza Hos ipc 25 | 25 | New Giza Teaching Hospital25 | 12359506.46 | 10195246.193 | 370205.76 | 10565451.953
New Giza Teaching Hospital | ipc13 New giza HOS | 13 | New Giza Teaching Hospital13 | 26683802.78 | 19237495.901 | 2273488.27 | 21510984.171
New Giza Teaching Hospital | new giza - ipc 11 | 11 | New Giza Teaching Hospital11 | 29644027.2 | 21461419.72 | 2942233.57 | 24403653.29
Ring Road -General Nile Co | INV ( 1 ) Fianl | 1 | Ring Road -General Nile Co1 | 656138 | 649576.62 | 0 | 649576.62
Egat Rolling Mill no.4 | Rolling mill IPC13 | 13 | Egat Rolling Mill no.413 | 14485776.56 | 11555244.6722 | 3509962.95 | 15065207.6222
EGAT Lock & Load | ipc14 Egad lock&load | 14 | EGAT Lock & Load14 | 2768145.62 | 2602056.8848 | 276814.56 | 2878871.4448
EGAT Lock & Load | EGAT L&L - IPC 13 | 13 | EGAT Lock & Load13 | 2116780.44 | 1989773.622 | 211678.04 | 2201451.662
EGAT Lock & Load | EGAT L&L-IPC 10+ | 10 | EGAT Lock & Load10 | 225255.97 | 211740.6085 | 22525.6 | 234266.2085
EGAT Lock & Load | EGAT L&L IPC 05 | 5 | EGAT Lock & Load5 | 3180176.34 | 2989365.767 | 318017.63 | 3307383.397
EGAT Lock & Load | EGAT L&L IPC03 | 3 | EGAT Lock & Load3 | 1772326.5 | 1665986.905 | 177232.65 | 1843219.555
EGAT Lock & Load | EGAT L&L ipc 01 | 1 | EGAT Lock & Load1 | 5018202.5 | 4717110.345 | 501820.25 | 5218930.595
Alfa New Central Labs | alfa lab ipc1(final) | 1 | Alfa New Central Labs1 | 1403211.67 | 1459340 | 0 | 1459340
New Babil 400/132KV GIS Substa | 2112210007 |  | New Babil 400/132KV GIS Substa | 221036.88 | 221036.88 | 0 | 221036.88
Hyper El-Temsah | ELTEMSAH MEP-IPC01 | 1 | Hyper El-Temsah1 | 2904234.6 | 2250174.87 | 0 | 2250174.87
Ain Sokhna Bridge – RME | IPC1 Supply Sokhna B | 1 | Ain Sokhna Bridge – RME1 | 617310 | 611895 | 0 | 611895
Cairo-Alex Railway | CAIRO-ALEX-IPC02 | 2 | Cairo-Alex Railway2 | 5895813.28 | 4164802.05 | 589581.33 | 4754383.38
Taval Sarai 52 | IPC-18-SARAY | 18 | Taval Sarai 5218 | 103870.5 | 79334.97 | 0 | 79334.97
TZ – Offshore E&M Procurement | 448 |  | TZ – Offshore E&M Procurement | 65739.99 | 65739.99 | 0 | 65739.99
Port Said Port Silos | Port Said Silos ipc1 | 1 | Port Said Port Silos1 | 9462048.96 | 6828805.57 | 946204.9 | 7775010.47
Port Said Port Silos | PORTSAID IPCSUPPLY11 |  | Port Said Port Silos | 921722.52 | 5002738.92 | 553033.5 | 925962.07
LP-26-21 Koning Food V5 | 49 |  | LP-26-21 Koning Food V5 | 25264 | 28764.48 | 0 | 28764.48
Ghana Street lighting | MIDA Sply. Inv.9 | 9 | Ghana Street lighting9 | 59165.18 | 53248.66 | 0 | 53248.66
Ghana Street lighting | MIDA Ins. Inv.9 | 9 | Ghana Street lighting9 | 17260.99 | 15534.89 | 0 | 15534.89
LP-13-21 -UIC | 43 |  | LP-13-21 -UIC | 44500 | 50285 | 0 | 50285
SHAT Al ARAB 400/132kV SS | 440 |  | SHAT Al ARAB 400/132kV SS | 37913.43 | 4928 | 0 | 4928
MAYSAN 400/132kV SS | 439 |  | MAYSAN 400/132kV SS | 2772 | 2772 | 0 | 2772
MOTHANA 400/132kV SS | 431 |  | MOTHANA 400/132kV SS | 2968 | 2968 | 0 | 2968
ORA ZED-Ph 2-Pkgs A&D | ora zed ph2 ipc03 | 3 | ORA ZED-Ph 2-Pkgs A&D3 | 15579509.09 | 9914986.5145 | 1179686.78 | 11094673.2945
ORA ZED-Ph 2-Pkgs A&D | ORA ZED 2 IPC04 | 4 | ORA ZED-Ph 2-Pkgs A&D4 | 34347323.22 | 30546043.101 | 3634373.4 | 34180416.501
Akhmem Assiut | Ret Asuit akh USD T |  | Akhmem Assiut | 1229629.86 | 1228184.73 | 0 | 1228184.73
AWEER POWER STATION 'H' Phase | ENG/051 |  | AWEER POWER STATION 'H' Phase | 43581.87 | 45760.9635 | 0 | 45760.9635
New Babil 400/132KV GIS Substa | 220221002 |  | New Babil 400/132KV GIS Substa | 1367396.75 | 1367396.75 | 0 | 1367396.75
Racecores 3092-16 132KV C | 11365 |  | Racecores 3092-16 132KV C | 207125.04 | 175020.66 | 0 | 175020.66
seashell Playa | IPC-14-PLAYA | 14 | seashell Playa14 | 523173.5 | 448935.17 | 0 | 448935.17
New Giza Teaching Hospital | newgizahospital ipc2 | 2 | New Giza Teaching Hospital2 | 20687718.13 | 14998595.6465 | 4298668.01 | 19297263.6565
158E/2019 33kv Project | 11383 |  | 158E/2019 33kv Project | 55442 | 249489 | 0 | 49897.8
TZ – Offshore E&M Procurement | 462 |  | TZ – Offshore E&M Procurement | 87296.9 | 87296.9 | 0 | 87296.9
Port Saeed East - OHTL | Port said OHTL Inv.2 | 2 | Port Saeed East - OHTL2 | 11828320.9 | 10556355 | 0 | 10556355
TZ – Offshore E&M Procurement | 453 |  | TZ – Offshore E&M Procurement | 495071.03 | 495071.03 | 0 | 495071.03
Water pumping New Obour City | Wat Pump Obour Inv.4 | 4 | Water pumping New Obour City4 | 23249198.38 | 22418611.4 | 3007923.25 | 25426534.65
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 10 | 10 | Suez Gulf/S4 - 500KV OHTL10 | 14755772.95 | 6692205.17 | 0 | 6692205.17
Ismailiya East Substation | تعويضات الاسماعلية |  | Ismailiya East Substation | 5847209 | 5847209 | 0 | 5847209
AWEER POWER STATION 'H' Phase | ENG/053 |  | AWEER POWER STATION 'H' Phase | 1087021.4 | 1141372.47 | 0 | 1141372.47
MDF Factory | MDF-ipc 21 | 21 | MDF Factory21 | 13626930.9 | 6432396.485 | 6988438.9 | 13420835.385
seashell Playa | IPC-15-PLAYA | 15 | seashell Playa15 | 339333.4 | 291181.99 | 0 | 291181.99
LAYAN Substation | 11503 |  | LAYAN Substation | 942937.7179 | 3187129.48 | 0 | 796782.37
ORA ZED-Ph 2-Pkgs A&D | ora zed2 ipc5 | 5 | ORA ZED-Ph 2-Pkgs A&D5 | 10060644.07 | 13201853.2135 | 1589461.07 | 14791314.2835
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 14 | 14 | Suez Gulf/S4 - 500KV OHTL14 | 4206178.63 | 1852832.03 | 0 | 1852832.03
Water pumping New Obour City | Wat Pump Obour Inv.3 | 3 | Water pumping New Obour City3 | 13488823.98 | 10305064.43 | 1416326.52 | 11721390.95
East Owainat 5 LOTS | East Owainat Inv. 07 | 7 | East Owainat 5 LOTS7 | 25352298.03 | 10343728.9 | 13309956.47 | 23653685.37
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC31 | 31 | EMAAR-Pkg#162/163- Marassi31 | 10357799.14 | 10109132.947 | 0 | 10109132.947
Mivida BP#189 | Emaar Pkg#189 ipc 26 | 26 | Mivida BP#18926 | 16876594.44 | 14177811.26 | 11952085.3 | 26129896.56
Mivida BP#189 | pkg#189 ipc 25 | 25 | Mivida BP#18925 | 29437278.32 | 28360739.446 | 3616556.37 | 31977295.816
Mivida BP#189 | Emaar PKG#189 IPC12 | 12 | Mivida BP#18912 | 15682494.86 | 17976827.49 | 2172158.86 | 20148986.35
AWEER POWER STATION 'H' Phase | IMP/068 |  | AWEER POWER STATION 'H' Phase | 108589.53 | 31973.58 | 12065.5 | 44039.08
Racecores 3092-17 132KV E | 11539 |  | Racecores 3092-17 132KV E | 155284.9823 | 262431.6229 | 0 | 131215.8114
Ghana Street lighting | MIDA Sply.inv.13 | 13 | Ghana Street lighting13 | 69408.34 | 62467.5 | 0 | 62467.5
Angola Emergency fast-track | ANG-Cam-Inv 7 - Int. | 7 | Angola Emergency fast-track7 | 4736059.02 | 2468374.87 | 0 | 2468374.87
EGAT Pelletizing Plant | ELCO EGAT IPC03 | 3 | EGAT Pelletizing Plant3 | 4383722.29 | 4121328.6545 | 437742.53 | 4559071.1845
CFC Podium 2 | CFC IPC 28 | 28 | CFC Podium 228 | 5026145.48 | 34503065.494 | 0 | 34503065.494
Ghana Street lighting | MIDA Ins.inv.13 | 13 | Ghana Street lighting13 | 19576.71 | 17619.04 | 0 | 17619.04
Industria Sadat | Sadat Indust Inv. 06 | 6 | Industria Sadat6 | 9594113.03 | 14389560.81 | 2014763.74 | 16404324.55
El Khatatba Bridge | EL KHATATBA ipc01 | 1 | El Khatatba Bridge1 | 40855295.24 | 6931826.092 | 0 | 27828222.092
Faculty of Medicine | MANSOURAFINSH IPC 26 | 26 | Faculty of Medicine26 | 7416829.52 | 5533663 | 1112524.43 | 6646187.43
Faculty of Medicine | Mansora finish ipc21 | 21 | Faculty of Medicine21 | 9255149.52 | 6905326 | 1388272.43 | 8293598.43
Faculty of Medicine | mansora finish ipc07 | 7 | Faculty of Medicine7 | 5805872.38 | 4331651.78 | 870880.86 | 5202532.64
Faculty of Medicine | mansora finish ipc03 | 3 | Faculty of Medicine3 | 1401587.62 | 1045391.37 | 210238.14 | 1255629.51
Al Montaza Hotels - Alexandria | inv ( 10 ) montazha | 10 | Al Montaza Hotels - Alexandria10 | 587463 | 556939.85 | 0 | 556939.85
Mauritania-Lot 2 | Inv.16 - Lot 2 | 16 | Mauritania-Lot 216 | 335843.79 | 318995.35 | 0 | 318995.35
Fish Market | م 1 سوق السمك صحى/حر | 1 | Fish Market1 | 3955199.05 | 1303149.0025 | 2357104.35 | 3660253.3525
NUCA R05 - Z02 | R05 Zone2 IPC018 | 18 | NUCA R05 - Z0218 | 24098912.8 | 23625902.74 | 2928079.6 | 26553982.34
NUCA R05 - Z02 | R05 Finishing IPC014 | 14 | NUCA R05 - Z0214 | 9342241 | 9916188.05 | 1285435.7 | 11201623.75
EDNC Hardscape Package | sodichardescape ipc1 | 1 | EDNC Hardscape Package1 | 1310241.41 | 1589312.7705 | 0 | 1589312.7705
EDNC Hardscape Package | EDNC hardscape IPC05 | 5 | EDNC Hardscape Package5 | 8146275.95 | 3116872.1575 | 0 | 3116872.1575
Racecores 3092-16 132KV C | 11660 |  | Racecores 3092-16 132KV C | 5591.34 | 5591.34 | 0 | 5591.34
EMAAR-Pkg#162/163- Marassi | PKG#177-IPC39 | 39 | EMAAR-Pkg#162/163- Marassi39 | 62325696.1 | 27439277.805 | 36110671.44 | 63549949.245
Port Said Port Silos | Port Said Silos ipc3 | 3 | Port Said Port Silos3 | 5972851.95 | 5357634.0375 | 540557.26 | 5898191.2975
Astoria Sharm elSheikh | Astoria sharm IPC3 | 3 | Astoria Sharm elSheikh3 | 2440310 | 1641108 | 640581.38 | 2281689.38
AWEER POWER STATION 'H' Phase | CON/033 |  | AWEER POWER STATION 'H' Phase | 638849.32 | 560767.73 | 70983.26 | 631750.99
Ghana Street lighting | MIDA SPLY.7 |  | Ghana Street lighting | 171991.53 | 154792.38 | 0 | 154792.38
Diplomatic District - Infra | Diplomatic ipc09 | 9 | Diplomatic District - Infra9 | 23246376.48 | 12693962.184 | 1807211.4 | 14501173.584
Benban 3/ Toshka 2 Lot 6 | Ref-Ret-Toshka Lot6$ |  | Benban 3/ Toshka 2 Lot 6 | 462416.26 | 24639.42 | 437776.84 | 462416.26
kayan wall lock & Load | kyan L&L final |  | kayan wall lock & Load | 3600000 | 3392590 | 0 | 3392590
Water pumping New Obour City | Wat Pump Obour Inv.6 | 6 | Water pumping New Obour City6 | 17761555.87 | 9755616.46 | 1360358.25 | 11115974.71
Beymen Fit Out | PKG#205 IPC03 | 3 | Beymen Fit Out3 | 2048097.8 | 1357991.24 | 645150.81 | 2003142.05
TZ – Offshore E&M Procurement | 461 |  | TZ – Offshore E&M Procurement | 71176.47 | 71176.47 | 0 | 71176.47
Business District Hyde Park | INV ( 6-9 ) HY Bark | 6 | Business District Hyde Park6 | 3114104.19 | 0 | 0 | 3114104.19
Business District Hyde Park | INV ( 5 ) HY Bark | 5 | Business District Hyde Park5 | 1536000 | 1284209.74 | 0 | 1284209.74
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 35 | 35 | Benban 500 K.V/95 K.M35 | 6264980.64 | 4602136.03 | 657822.97 | 5259959
Racecores 3092-17 132KV E | 11683 |  | Racecores 3092-17 132KV E | 99481.9048 | 104456 | 0 | 104456
HSR-6th of October | IPC#1 - HSR | 1 | HSR-6th of October1 | 285860 | 248698.2 | 0 | 248698.2
Monorail | 220621009 |  | Monorail | 1453192 | 1642106.96 | 0 | 1642106.96
MDF Factory | MDF - IPC 20 | 20 | MDF Factory20 | 10304099.23 | 1506264.6515 | 7842049.02 | 9348313.6715
El Sadat City | Sadat City Inv. 01 | 1 | El Sadat City1 | 79292831.19 | 52376438.56 | 0 | 52376438.56
seashell Playa | IPC-17-PLAYA | 17 | seashell Playa17 | 359096.5 | 254541.27 | 0 | 254541.27
Cairo Monorail - 6th October | IPC#8 Monorail | 8 | Cairo Monorail - 6th October8 | 1476000 | 1412565 | 0 | 1412565
New Babil 400/132KV GIS Substa | 220721003 |  | New Babil 400/132KV GIS Substa | 134678.4 | 134678.4 | 0 | 134678.4
East Owainat 5 LOTS | East Owainat Inv.3 V | 3 | East Owainat 5 LOTS3 | 58903586.5 | 23336380.69 | 30924382.91 | 54260763.6
Expansion of Ring Road | IPC#1 - Tiger | 1 | Expansion of Ring Road1 | 303400 | 300366 | 0 | 300366
EDNC Hardscape Package | SODIC HARD IPC02 | 2 | EDNC Hardscape Package2 | 3188822.83 | 2794789.4915 | 0 | 2794789.4915
seashell Playa | IPC-2-PLAYA | 2 | seashell Playa2 | 99925.05 | 69757.644 | 15988.05 | 85745.694
Marassi - Water proofing | IPC-2-PKG#177 Water | 2 | Marassi - Water proofing2 | 28370.27 | 25121.88 | 0 | 25121.88
Sodic East | IPC_18_Rowad_Seast | 18 | Sodic East18 | 554998.17 | 653719.408 | 0 | 653719.408
EMAAR-Pkg#162/163- Marassi | pkg#177 ipc 24 | 24 | EMAAR-Pkg#162/163- Marassi24 | 5954515.9 | 5112916.32 | 0 | 5112916.32
HSR-6th of October | IPC#2 HSR | 2 | HSR-6th of October2 | 699340 | 608425.8 | 0 | 608425.8
W Dam PP Phase II (CP-117) | 15 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 16158.31 | 16158.31 | 0 | 16158.31
Assuit PP (CP-118) | 220721004 |  | Assuit PP (CP-118) | 44375.66 | 46594.443 | 0 | 46594.443
Faculty of Medicine | MANSOURA IPC12 | 12 | Faculty of Medicine12 | 5167995.24 | 4434711.832 | 258399.76 | 4693111.592
ElSewedy HQ Internal Finishing | sewedy HQ IPC17 | 17 | ElSewedy HQ Internal Finishing17 | 17076484.19 | 2847047.2295 | 7737698.68 | 15750846.1095
Waldorf Astoria Cairo | Waldorf Astoria IPC3 | 3 | Waldorf Astoria Cairo3 | 6522225.37 | 5421697.4285 | 3511949.46 | 8933646.8885
Port Said Grain Storage | IPC#3 GSCC Port | 3 | Port Said Grain Storage3 | 693000 | 497431.1 | 0 | 592913.3
LINX Tower | Inv ( Final ) Linx |  | LINX Tower | 912123.24 | 689404.152 | 0 | 689404.152
PO3092200025 | 11703 |  | PO3092200025 | 0 | -125 | 0 | -125
SSC Suez Steel Company Project | In&ReSupply(ssc)IPC3 | 3 | SSC Suez Steel Company Project3 | 374122.68 | 283552.0652 | 139206.56 | 422758.6252
SSC Suez Steel Company Project | int&ret supAbb ipc8 | 8 | SSC Suez Steel Company Project8 | 1041476.54 | 817934.2656 | 358934.22 | 1176868.4856
SSC Suez Steel Company Project | In&ReApply(ABB)IPC2 | 2 | SSC Suez Steel Company Project2 | 1514111.96 | 988420.7044 | 692243.57 | 1680664.2744
SSC Suez Steel Company Project | in&re.app abb ipc 3 | 3 | SSC Suez Steel Company Project3 | 1605876.32 | 1048324.9852 | 734197.73 | 1782522.7152
Waldorf Astoria Cairo | waldorf - IPC16 | 16 | Waldorf Astoria Cairo16 | 9372213.84 | 0 | 3294201.48 | 6519884.48
Waldorf Astoria Cairo | Waldorf- IPC 15 | 15 | Waldorf Astoria Cairo15 | 9032753.1 | 0 | 4276171.2 | 8461832.735
Air Defence College | TR0046-IPC002 | 2 | Air Defence College2 | 223641.12 | 189871.3 | 0 | 189871.3
Waldorf Astoria Cairo | ipc17woldoef astoria | 17 | Waldorf Astoria Cairo17 | 7818140.35 | 0 | 2863892.36 | 5668051.36
EPICO 3 Facility | Eipico 3 ipc 12 | 12 | EPICO 3 Facility12 | 13086699.86 | 25548194.95 | 9585575.71 | 35133770.66
ORA ZED-Ph 2-Pkgs A&D | ora ph.2 ipc9 | 9 | ORA ZED-Ph 2-Pkgs A&D9 | 8712415.5 | 7614021.055 | 900969.93 | 8514990.985
Al Montaza Hotels - Alexandria | inv ( 11 ) montazha | 11 | Al Montaza Hotels - Alexandria11 | 426809.5 | 403719.02 | 0 | 403719.02
EDNC Hardscape Package | Soreal HardscapeIPC7 | 7 | EDNC Hardscape Package7 | 5611542.56 | 2434849.578 | 0 | 2434849.578
El Taameer Axis Expansion | IPC#1 Taamer PII | 1 | El Taameer Axis Expansion1 | 172260 | 166403.16 | 0 | 166403.16
CS-20 Mall | inv ( 3 ) CS-20 | 3 | CS-20 Mall3 | 3929643.6 | 821864.65 | 0 | 821864.65
Mivida BP#189 | PKG#189 IPC3 | 3 | Mivida BP#1893 | 27730887.07 | 23971236.1335 | 2883960.5 | 26855196.6335
NUCA R05 - Z02 | R05(2) ipc26 | 26 | NUCA R05 - Z0226 | 12786322.39 | 10853224.66 | 1359017.8 | 12212242.46
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC13 | 13 | EMAAR-Pkg#162/163- Marassi13 | 709528.81 | 8135757.8105 | 0 | 8135757.8105
HST Bridges-Sokhna & Mahager | SOKHNA BRIDGE 8+9+10 |  | HST Bridges-Sokhna & Mahager | 43660371.43 | 637790.3157 | 0 | 39637790.3157
EDNC Hardscape Package | sorealhardscape IPC8 | 8 | EDNC Hardscape Package8 | 16821952.2 | 9494386.1475 | 0 | 9494386.1475
The American School ASE | INV ( FINAL ) USA S |  | The American School ASE | 306353.5 | 303289.96 | 0 | 303289.96
The American School ASE | INV ( 1 ) USA S | 1 | The American School ASE1 | 202972.5 | 200942.77 | 0 | 200942.77
Mivida BP#189 | PKG#189- IPC6 | 6 | Mivida BP#1896 | 57254690.6 | 49630186.51 | 5982950.12 | 55613136.63
Air Defense College | Ari Dev3 IPC2 | 2 | Air Defense College2 | 679505 | 285725 | 0 | 574970
WADY EL-NATROUN BRIDGE(HST) | IPC9 WADI | 9 | WADY EL-NATROUN BRIDGE(HST)9 | 1299480 | 1140233.66 | 0 | 1140233.66
RING ROAD MARYOTIA EXPANSION | mariotya ipc 18 | 18 | RING ROAD MARYOTIA EXPANSION18 | 4431970 | 3881647.75 | 0 | 3881647.75
HST Bridges-Sokhna & Mahager | elsokhna ipc5+6+7 | 5 | HST Bridges-Sokhna & Mahager5 | 16141864.29 | 14250689.3 | 0 | 14250689.3
Get Business Complex | INV ( 21 ) GET | 21 | Get Business Complex21 | 2445777.04 | 133942.41 | 0 | 133942.41
Ain Sokhna Port Development | IPC22-AIN SOKHNA | 22 | Ain Sokhna Port Development22 | 1172898 | 1918789.58 | 0 | 991565.91
SSC Suez Steel Company Project | Revamp- IPC 6 | 6 | SSC Suez Steel Company Project6 | 8858061.69 | 6112062.5676 | 2657418.51 | 8769481.0776
SSC Suez Steel Company Project | Revamp ipc(2) | 2 | SSC Suez Steel Company Project2 | 1797569.47 | 0 | 539270.84 | 1869472.2488
Kafr Shokr Bridge | kafr shokr ipc 10 | 10 | Kafr Shokr Bridge10 | 2706642.86 | 2390708.77 | 0 | 2390708.77
Ministries Buildings | Min Core ipc 11 | 11 | Ministries Buildings11 | 21402202 | 16836655 | 0 | 16836655
Egyptian Exchange Building | Egy Ex ipc 01 | 1 | Egyptian Exchange Building1 | 176933890.48 | 36951715 | 82622000 | 155263715
Sokhna Port Expansion | sokhna port ex ipc09 | 9 | Sokhna Port Expansion9 | 43350211.2 | 30030028.52 | 8670042.24 | 38700070.76
SSC Suez Steel Company Project | R.o(50:80) supp ipc7 | 7 | SSC Suez Steel Company Project7 | 7188907.18 | 5966792.9552 | 2156672.16 | 8123465.1152
SSC Suez Steel Company Project | ro(5000:800)app ipc3 | 3 | SSC Suez Steel Company Project3 | 2894610.35 | 2225665.8924 | 987351.58 | 3213017.4724
EGAT Injection | IPC00004 | 4 | EGAT Injection4 | 546308.7 | 468787.5 | 0 | 468787.5
Olympic Multi – Sports Hall | Olympic finsh IPC2 | 2 | Olympic Multi – Sports Hall2 | 3124225 | 2631750 | 0 | 2631750
PLAYA ROOF & Wet Areas | IPC0000017 | 17 | PLAYA ROOF & Wet Areas17 | 155162.83 | 133145.22 | 0 | 133145.22
Port Said Port Silos | port said silosipc10 | 10 | Port Said Port Silos10 | 8366928.53 | 7412449.0665 | 836692.85 | 8249141.9165
October Under-Railway Tunnel | october tunnel ipc2 | 2 | October Under-Railway Tunnel2 | 4380339.19 | 3508352.9 | 0 | 3508352.9
MAF HQ Renovation | Carrefour H Off ipc4 | 4 | MAF HQ Renovation4 | 2486161.49 | 1402420.1797 | 922140.81 | 2324560.9897
Kayan 3 New Cairo Capital City | Kayan fin Ipc fin |  | Kayan 3 New Cairo Capital City | 1710756 | 1611980 | 0 | 1611980
Jawhar El-Lala Mosque | IPC000001 | 1 | Jawhar El-Lala Mosque1 | 16500 | 14008.5 | 0 | 14008.5
Egyptian Exchange Building | Eg Exchge IPC2 | 2 | Egyptian Exchange Building2 | 18198998.1 | 16187610 | 0 | 16187610
ORA-ZED Towers P01B | IPC006 | 6 | ORA-ZED Towers P01B6 | 400980.93 | 355068.61 | 0 | 355068.61
SSC Suez Steel Company Project | R.O. - SUPPLY IPC 1 | 1 | SSC Suez Steel Company Project1 | 16503981 | 13698304.23 | 4951194.3 | 18649498.53
DP World Basin 2 Ph2 | Dp world IPC10 | 10 | DP World Basin 2 Ph210 | 66818227.5 | 49445488.36 | 10022734.12 | 59468222.48
Monoril | inv ( 1 ) monoril | 1 | Monoril1 | 783613.1 | 744432.44 | 0 | 744432.44
MAF HQ Renovation | IPC 1 head office | 1 | MAF HQ Renovation1 | 4184919.24 | 2814358.19 | 1098541.3 | 3912899.49
Sokhna Port Expansion | spx.2 ipc 03 | 3 | Sokhna Port Expansion3 | 26794714.1 | 10464912.35 | 5358942.82 | 23823855.17
MAF HQ Renovation | carrefour H off ipc2 | 2 | MAF HQ Renovation2 | 4612182.33 | 3101692.62 | 1210697.86 | 4312390.48
Port Said Port Silos | port said inv.1-supp | 1 | Port Said Port Silos1 | 673851.6 | 3278288.02 | 336925.8 | 723042.764
WADY EL-NATROUN BRIDGE(HST) | IPC#13 WADI | 13 | WADY EL-NATROUN BRIDGE(HST)13 | 538020 | 482679.16 | 0 | 482679.16
Seashell Playa 5 Villas | playa -c185 ipc 3 | 3 | Seashell Playa 5 Villas3 | 70343.21 | 56077.3 | 0 | 56077.3
Seashell Playa 5 Villas | Playa - C185 ipc 2 | 2 | Seashell Playa 5 Villas2 | 23604.6 | 20384.93 | 0 | 20384.93
Katameya Creeks - RME | IPC004 | 4 | Katameya Creeks - RME4 | 11585.51 | 10258.96 | 0 | 10258.96
El Taameer Axis Expansion | FPC - Tamer Axis PII |  | El Taameer Axis Expansion | 398750 | 384917.5 | 0 | 384917.5
Alamein Coastal Road Bridge | sahilil IPC final |  | Alamein Coastal Road Bridge | 25444414.29 | 14904090 | 0 | 21361140
EPICO 3 Facility | Eipico ipc 4 | 4 | EPICO 3 Facility4 | 8374674.18 | 7344658.43 | 2480166.71 | 9824825.14
Cairo Monorail - 6th October | IPC#11 Monorail | 11 | Cairo Monorail - 6th October11 | 144000 | 142560 | 0 | 142560
HST - 6 October - Arab Cont. | IPC#3 HSR ARAB | 3 | HST - 6 October - Arab Cont.3 | 2016995 | 500000 | 0 | 500000
U3 & U5 | IPC09 TR55 | 9 | U3 & U59 | 82039.18 | 34899.03 | 0 | 34899.03
U3 & U5 | IPC005 TR55 | 5 | U3 & U55 | 280104.2 | 241897.99 | 0 | 241897.99
Seashell Playa 5 Villas | PLAYA c045 - ipc 2 | 2 | Seashell Playa 5 Villas2 | 334116.69 | 215718.58 | 0 | 215718.58
Seashell Playa 5 Villas | playa c038- ipc 1 | 1 | Seashell Playa 5 Villas1 | 145532.4 | 59531.13 | 0 | 59531.13
U4,U8 Seashell Playa | IPC004 TR60 | 4 | U4,U8 Seashell Playa4 | 496585.97 | 428851.64 | 0 | 428851.64
U7-SEASHELL | IPC002 TR64 | 2 | U7-SEASHELL2 | 62188.74 | 53706.19 | 0 | 53706.19
U4,U8 Seashell Playa | IPC005 TR60 | 5 | U4,U8 Seashell Playa5 | 404752.89 | 349544.6 | 0 | 349544.6
seashell Playa | IPC00027TR38 | 27 | seashell Playa27 | 224545.02 | 192682.08 | 0 | 192682.08
Wadi Halfa Port | wady halfa esc.2 |  | Wadi Halfa Port | 10950490.88 | 10413528.9712 | 0 | 10413528.9712
Wadi Halfa Port | wadi halfa ipc 03 | 3 | Wadi Halfa Port3 | 4077802.86 | 2807168.5814 | 856338.6 | 3663507.1814
R05 (New) | IPC003 TR59 | 3 | R05 (New)3 | 52098 | 44184.31 | 0 | 44184.31
RING ROAD MARYOTIA EXPANSION | mariotya ipc19 | 19 | RING ROAD MARYOTIA EXPANSION19 | 15814702.29 | 15656555.2745 | 0 | 15656555.2745
EL Sewedy University Tec. | INV ( 3 ) S.UNIV | 3 | EL Sewedy University Tec.3 | 69115.2 | 57950.96 | 0 | 57950.96
Wady El Natroon Bridge | ipc 3 wady elnatroon | 3 | Wady El Natroon Bridge3 | 8683485.71 | 7741398.95 | 0 | 7741398.95
ORA ZED - Ph 01B - Pkgs A&D | ORA PH.1 - IPC 21 | 21 | ORA ZED - Ph 01B - Pkgs A&D21 | 9295357.14 | 8181176.157 | 974442.67 | 9155618.827
Egat Rolling Mill no.4 | Rolling Mill- IPC12 | 12 | Egat Rolling Mill no.412 | 16694409.38 | 13213211.259 | 4148974.5 | 17362185.759
Ora Zed Landscape Ph1 | Ora landscape ipc 7 | 7 | Ora Zed Landscape Ph17 | 1343089.52 | 1035276.496 | 141024.4 | 1176300.896
Olympic Multi – Sports Hall | Olympic Finsh3 IPC1 | 1 | Olympic Multi – Sports Hall1 | 21127578 | 4019720 | 12400000.51 | 16419720.51
EMAAR-Pkg#162/163- Marassi | pkg#163- Inv. 27 | 27 | EMAAR-Pkg#162/163- Marassi27 | 4132634.87 | 3653603.3235 | 0 | 3653603.3235
Kemet Tower | CR INV ( 09 ) KEMET | 9 | Kemet Tower9 | 185120 | 158851.46 | 0 | 158851.46
Tarek Abdel-Hakim Center | TAH ipc09 | 9 | Tarek Abdel-Hakim Center9 | 7602439.9 | 5675544.71 | 684219.59 | 6359764.3
ORA ZED-Ph 2-Pkgs A&D | ora ph2 ipc (21) | 21 | ORA ZED-Ph 2-Pkgs A&D21 | 4766150.56 | 4432160.4921 | 560694.95 | 4992855.4421
SSC Suez Steel Company Project | i&R apply (ssc)ipc 1 | 1 | SSC Suez Steel Company Project1 | 573500 | 0 | 0 | 636585
SSC Suez Steel Company Project | intake&return S ipc4 | 4 | SSC Suez Steel Company Project4 | 817103.94 | 0 | 281606.5 | 923327.4522
Seashell Playa 5 Villas | playa-c038ipc(5) | 5 | Seashell Playa 5 Villas5 | 205614.11 | 154045.02 | 0 | 154045.02
ora zed orascom | IPC08TR0069 | 8 | ora zed orascom8 | 343689.62 | 68737.92 | 0 | 68737.92
KATAMYA GREEKS LAND SCAPE STAR | IPC04TR0081 | 4 | KATAMYA GREEKS LAND SCAPE STAR4 | 1354395.24 | 1338955.132 | 0 | 1338955.132
Creeks URBN-K | URBN-K IPC (5) | 5 | Creeks URBN-K5 | 29818122.52 | 13533059 | 16464358.31 | 29997417.31
SSC Suez Steel Company Project | In.&Re. Sup.SSC-IPC6 | 6 | SSC Suez Steel Company Project6 | 1555469.69 | 1178909.0902 | 578771.64 | 1757680.7302
SSC Suez Steel Company Project | R.O. Supply- IPC 6 | 6 | SSC Suez Steel Company Project6 | 2589997.98 | 2149698.3272 | 776999.39 | 2926697.7172
Mohamed Ali Palace Restoration | MOHAMED ALY2 IPC03 | 3 | Mohamed Ali Palace Restoration3 | 1398734.39 | 439447.0995 | 877758.5 | 1317205.5995
Mohamed Ali Palace Restoration | MohamedAly 2 - IPC01 | 1 | Mohamed Ali Palace Restoration1 | 8726957.14 | 5993163.6 | 2023560 | 8016723.6
Ora Zed Landscape Ph1 | Ora Landscape ipc 9 | 9 | Ora Zed Landscape Ph19 | 4486249.0225 | 3863087.97 | 463402.7 | 4479909.2558
EGAT Pelletizing Plant | Admin Building ipc 1 | 1 | EGAT Pelletizing Plant1 | 61566718.68 | 27089356.2172 | 36940031.21 | 64029387.4272
Port Said Port Silos | portsaid 2-supp.EGP |  | Port Said Port Silos | 1194976.65 | 4650847.76 | 477990.64 | 1282209.6
Al-Parco | INV ( 5 ) ALparco | 5 | Al-Parco5 | 3424286 | 3187658.86 | 0 | 3187658.86
Air Defense College | Air dev Finish3 IPC3 | 3 | Air Defense College3 | 3116565 | 2122130 | 0 | 2630384
Ain Sokhna Bridge | Inv ( 2 ) A.S | 2 | Ain Sokhna Bridge2 | 2683648.47 | 2066484.69 | 0 | 2066484.69
Waldorf Astoria Cairo | woldorf astori ipc23 | 23 | Waldorf Astoria Cairo23 | 13277404.76 | 20506021.05 | 0 | 20933799.87
SSC Suez Steel Company Project | revamp(smp1)ipc1 | 1 | SSC Suez Steel Company Project1 | 15192302.49 | 7667227.3596 | 7596151.24 | 15799994.6096
TOSHKA MADKOUR | IPC02TR0083 | 2 | TOSHKA MADKOUR2 | 597774.24 | 532019.08 | 0 | 532019.08
Mivida BP#189 | Emaar pkg#189ipc17 | 17 | Mivida BP#18917 | 30434807.73 | 47104890.0565 | 2724540.31 | 49829430.3665
U3 & U5 | IPC16TR0055 | 16 | U3 & U516 | 95367.68 | 82359.53 | 0 | 82359.53
Hyper El-Temsah | ELTAMSAH-كهرو MEP-01 | 1 | Hyper El-Temsah1 | 65420317 | 24429401.35 | 30000000 | 54429401.35
Mohamed Ali Palace Restoration | Mohamed Aly IPC05 | 5 | Mohamed Ali Palace Restoration5 | 8004368.18 | 2197969.3 | 4715628.9 | 6913598.2
Ora Zed Landscape Ph1 | Ora Landscape ipc 4 | 4 | Ora Zed Landscape Ph14 | 4909564.83 | 4332690.6 | 515504.31 | 4848194.91
Air Defense College | Air Dev Elec IPC1 | 1 | Air Defense College1 | 111172167 | 48691810 | 229975490 | 92889100
NUCA R05 - Z02 | R5 (2) ipc34 | 34 | NUCA R05 - Z0234 | 15591657.65 | 12417472.88 | 1587374.7 | 14004847.58
South Dabaa Axis | ipc 1 south dabaa | 1 | South Dabaa Axis1 | 1048928 | 300348.5 | 0 | 300348.5
El-Warraq | IPC final elwaraq |  | El-Warraq | 198000 | 147117.32 | 0 | 147117.32
EMAAR-Pkg#162/163- Marassi | PKG#163 IPC (30) | 30 | EMAAR-Pkg#162/163- Marassi30 | 8788912.25 | 3404339.9025 | 0 | 3404339.9025
SSC Suez Steel Company Project | int&ret sup ssc ipc7 | 7 | SSC Suez Steel Company Project7 | 2983296.88 | 2261076.4232 | 1110049.05 | 3371125.4732
SSC Suez Steel Company Project | int&ret sup abb ipc7 | 7 | SSC Suez Steel Company Project7 | 10394599.15 | 8151504.971 | 3582392.07 | 11733897.041
RING ROAD MARYOTIA EXPANSION | Mariotya ipc24 zomor | 24 | RING ROAD MARYOTIA EXPANSION24 | 1630460.9 | 1574628.39 | 0 | 1574628.39
RING ROAD MARYOTIA EXPANSION | Mariotya ipc 24 | 24 | RING ROAD MARYOTIA EXPANSION24 | 4972835.81 | 4218639.41 | 0 | 4218639.41
AIRDEFNSE -EPOXY | IPC02 TR66 | 2 | AIRDEFNSE -EPOXY2 | 123592.6 | 104930.11 | 0 | 104930.11
Kattmeya Creeks Urban | IPC 2 TR71 | 2 | Kattmeya Creeks Urban2 | 497936.61 | 440922.87 | 0 | 440922.87
AIRDEFNSE -EPOXY | ipc006 TR66 | 6 | AIRDEFNSE -EPOXY6 | 673170.6 | 571521.83 | 0 | 571521.83
AIRDEFNSE -EPOXY | IPC04TR0066 | 4 | AIRDEFNSE -EPOXY4 | 13737.9 | 11663.47 | 0 | 11663.47
Waldorf Astoria Cairo | Woldorf Asto ipc 21 | 21 | Waldorf Astoria Cairo21 | 1422437.2 | 0 | 0 | 854978.78
October Under-Railway Tunnel | october tunnelipc3+4 | 3 | October Under-Railway Tunnel3 | 5911928.1 | 5155347.1955 | 0 | 5155347.1955
October Under-Railway Tunnel | october tunnel ipc7 | 7 | October Under-Railway Tunnel7 | 10389360.67 | 9353909.62 | 0 | 9353909.62
SOL Town PKG.220 | PKG#220- IPC3 | 3 | SOL Town PKG.2203 | 1345226.9 | 348202.56 | 896872.19 | 1245074.75
El- Hussein Mosque | Hussein Mos IPC1 | 1 | El- Hussein Mosque1 | 5007440 | 3865320 | 0 | 3865320
Roof-Playa Cluster A,B,C | IPC05TR0088 | 5 | Roof-Playa Cluster A,B,C5 | 234659 | 202651.51 | 0 | 202651.51
Residence 8 ( S07 ) | Inv ( 1 ) S07 | 1 | Residence 8 ( S07 )1 | 1134750 | 1025814 | 0 | 1025814
Olympic Multi – Sports Hall | Olym Finish IPC1 | 1 | Olympic Multi – Sports Hall1 | 6741326 | 5145260 | 0 | 5145260
Seashell Playa 5 Villas | Playa C045- IPC 9 | 9 | Seashell Playa 5 Villas9 | 29477.74 | 10456.56 | 0 | 10456.56
Air Defense College | Air Dev Elic IPC1 | 1 | Air Defense College1 | 79552681 | 14817370 | 51678000 | 66495370
HST Bridges-Sokhna & Mahager | sokhna esc.14+15 |  | HST Bridges-Sokhna & Mahager | 29623249.9 | 26774104.45 | 0 | 26774104.45
Jawhara Palace Restoratio | Gawhara IPC3 | 3 | Jawhara Palace Restoratio3 | 4244400 | 2850324 | 1061100 | 3911424
HST Bridges-Sokhna & Mahager | sokhna esc.14+15 (2) |  | HST Bridges-Sokhna & Mahager | 5454047.52 | 4500020.22 | 0 | 4500020.22
Roof-Playa Cluster A,B,C | IPC02TR0088 | 2 | Roof-Playa Cluster A,B,C2 | 648565 | 508950.72 | 0 | 508950.72
Jawhar Al-Lala Mosque | Gawhar LALA IPC1 | 1 | Jawhar Al-Lala Mosque1 | 8815759 | 1979890 | 4951647 | 6931537
Sixty Iconic Tower | Inv ( 6 ) sixty | 6 | Sixty Iconic Tower6 | 1434485 | 1338415.9 | 0 | 1338415.9
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 28 | 28 | ORA ZED-Ph 2-Pkgs A&D28 | 2340664.72 | 1922751.71 | 245769.8 | 2168521.51
Olympic MultiSport Hall | IPC02TR0079 | 2 | Olympic MultiSport Hall2 | 9861.6 | 8298.53 | 0 | 8298.53
Faculty of Medicine | Mansora finish ipc19 | 19 | Faculty of Medicine19 | 20526102.86 | 15315146 | 3078915.43 | 18394061.43
Open Channal | IPC04TR0074 | 4 | Open Channal4 | 173568 | 149719.76 | 0 | 149719.76
U4,U8 Seashell Playa | IPC15TR0060 | 15 | U4,U8 Seashell Playa15 | 319683.13 | 156078.35 | 0 | 156078.35
ora zed orascom | IPC05TR0069 | 5 | ora zed orascom5 | 1021612.84 | 734012.43 | 0 | 734012.43
New Giza Teaching Hospital | New Giza Hosp ipc 26 | 26 | New Giza Teaching Hospital26 | 68532450.22 | 16494091.451 | 15936037.38 | 47830128.831
EGAT Mechanical Installations | Egat Mechnical ipc 6 | 6 | EGAT Mechanical Installations6 | 13673922.93 | 10390813.8998 | 3418480.8625 | 13809294.7623
Sokhna Port Expansion | esc.spx1 11+12 |  | Sokhna Port Expansion | 50432113 | 39132293.62 | 0 | 44780293.62
U7-SEASHELL | IPC17TR0064 | 17 | U7-SEASHELL17 | 96073.6 | 78411.52 | 0 | 78411.52
Port Said Port Silos | port said silo ipc24 | 24 | Port Said Port Silos24 | 4764115.24 | 3891455.9996 | 476411.52 | 4367867.5196
Port Said Grain Storage | RENT-006 | 6 | Port Said Grain Storage6 | 150400 | 166267.2 | 0 | 166267.2
MDF Factory | MDF Equip ipc 24 | 24 | MDF Factory24 | 342224.81 | 345289.58 | 0 | 345289.58
Ora Zed Landscape Ph1 | Ora Landscap ipc 16 | 16 | Ora Zed Landscape Ph116 | 1773393.33 | 1521916.4665 | 186206.3 | 1708122.7665
U4,U8 Seashell Playa | IPC16TR0060 | 16 | U4,U8 Seashell Playa16 | 274667.4 | 237202.77 | 0 | 237202.77
Egyptian Exchange building | IPC15TR0039 | 15 | Egyptian Exchange building15 | 618281.6 | 547488.35 | 0 | 547488.35
EGAT Injection | IPC15TR0048 | 15 | EGAT Injection15 | 270868.46 | 232432.23 | 0 | 232432.23
EIPICO C002-23 | IPC10TR0068 | 10 | EIPICO C002-2310 | 88548.1 | 87118.11 | 0 | 87118.11
Jawhara Palace Restoratio | Jawhara IPC4 | 4 | Jawhara Palace Restoratio4 | 1280722.15 | 859800 | 320180.54 | 1179980.54
Abou Ghaleb Bridge | Aboghaleb Esc.1:20 p |  | Abou Ghaleb Bridge | 9228962.71 | 8914781.18 | 0 | 8914781.18
Abou Ghaleb Bridge | ABOGHALEBIPC19+20 | 19 | Abou Ghaleb Bridge19 | 8316366.29 | 7383581.7645 | 0 | 7383581.7645
Olympic Multi – Sports Hall | olympic mic IPC1 | 1 | Olympic Multi – Sports Hall1 | 5172988 | 4565825 | 0 | 4565825
SSC Suez Steel Company Project | In&Re apply ssc ipc7 | 7 | SSC Suez Steel Company Project7 | 1924769.3 | 1886891.062 | 249602.86 | 2136493.922
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 32 | 32 | ORA ZED-Ph 2-Pkgs A&D32 | 2766735.75 | 2836390.6675 | 290507.25 | 3126897.9175
SSC Suez Steel Company Project | V.O SMP1 IPC 1 | 1 | SSC Suez Steel Company Project1 | 18867171.15 | 18678499.436 | 0 | 18678499.436
Mivida BP#189 | Emaar Pkg#189 ipc 27 | 27 | Mivida BP#18927 | 14919836.12 | 4389859.036 | 7016517.49 | 11406376.526
Port Said Port Silos | PORT SAID IPC 30 | 30 | Port Said Port Silos30 | 3191368.24 | 100639.5696 | 319136.82 | 419776.3896
UGC Factory | IPC01TR0100 | 1 | UGC Factory1 | 2989546 | 2810173.24 | 0 | 2810173.24
EIPICO C002-23 | IPC08TR0068 | 8 | EIPICO C002-238 | 72216.7 | 61969.13 | 0 | 61969.13
EIPICO C002-23 | IPC06TR0068 | 6 | EIPICO C002-236 | 187923.2 | 136256.9 | 0 | 136256.9
ora zed orascom | IPC06TR0069 | 6 | ora zed orascom6 | 471168.59 | 430765.86 | 0 | 430765.86
EDNC Retail - SEOUDI MODI | Ednc Saudi ipc 2 | 2 | EDNC Retail - SEOUDI MODI2 | 1783835.43 | 951910.44 | 900626.7 | 1852537.14
R05 (New) | IPC09TR0059 | 9 | R05 (New)9 | 14256 | 10660.52 | 0 | 10660.52
Olympic MultiSport Hall | IPC06TR0079 | 6 | Olympic MultiSport Hall6 | 25956 | 21841.98 | 0 | 21841.98
RADAMIS CITY | IPC03TR0084 | 3 | RADAMIS CITY3 | 328264.64 | 290680.85 | 0 | 290680.85
Al-Parco | INV (11-12 ) ALparco | 11 | Al-Parco11 | 2482854.5 | 506062.79 | 0 | 506062.79
Egyptian Exchange Building | Exch EGY BIM1 |  | Egyptian Exchange Building | 1958660 | 1696720 | 0 | 1696720
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 43 | 43 | ORA ZED - Ph 01B - Pkgs A&D43 | 11538786.67 | 10554454.5368 | 0 | 10554454.5368
RADAMIS CITY | IPC09TR0084 | 9 | RADAMIS CITY9 | 111692.66 | 98903.2 | 0 | 98903.2
EIPICO C002-23 | IPC13TR0068 | 13 | EIPICO C002-2313 | 76962.2 | 66041.27 | 0 | 66041.27
Egyptian Exchange building | IPC17TR0039 | 17 | Egyptian Exchange building17 | 198913.68 | 176138.07 | 0 | 176138.07
EGAT Injection | IPC16TR0048 | 16 | EGAT Injection16 | 1453896.97 | 1247588.98 | 0 | 1247588.98
Katameya Creeks - RME | IPC18TR0053 | 18 | Katameya Creeks - RME18 | 260398.2 | 229632.61 | 0 | 229632.61
Open Channel 2 | IPC02TR0099(01) | 2 | Open Channel 22 | 2440060 | 2086495.82 | 0 | 2086495.82
Abou Ghaleb Bridge | Abo Ghaleb ipc 24 | 24 | Abou Ghaleb Bridge24 | 954963.05 | 851501.28 | 0 | 851501.28
RING ROAD MARYOTIA EXPANSION | El Marg Esc.1:11 fin |  | RING ROAD MARYOTIA EXPANSION | 1247276.95 | 1170796.25 | 0 | 1170796.25
Creeks URBN-K | Urbn-k ipc 6 | 6 | Creeks URBN-K6 | 21266246.93 | 19608846.9472 | 1672033.24 | 21280880.1872
Koumassi Flyover | INV no.11 | 11 | Koumassi Flyover11 | 630376785.33 | 567339106.8 | 0 | 567339106.8
Seashell Playa 5 Villas | Playa c469 ipc 7 | 7 | Seashell Playa 5 Villas7 | 79103.1 | 72268.59 | 0 | 72268.59
ElMoneeb 2 | IPC#06 Moneeb | 6 | ElMoneeb 26 | 759410 | 568314.32 | 0 | 568314.32
EPICO 3 Facility | Eipico ipc 20 | 20 | EPICO 3 Facility20 | 71749002.23 | 62225320.01 | 0 | 62225320.01
Coastal road Bridge Extension | ipc 9 D0051 | 9 | Coastal road Bridge Extension9 | 1242615.5 | 1179338.8 | 0 | 1179338.8
Ahl Misr P3 – Zamalek Sector | IPC#2 Ahl Misr Zamal | 2 | Ahl Misr P3 – Zamalek Sector2 | 511560 | 491934.3 | 0 | 491934.3
Railway Bridge - El Hammam | IPC#2 ElHammam | 2 | Railway Bridge - El Hammam2 | 710698.02 | 668889.36 | 0 | 668889.36
MDF Factory | MDF-Local ipc 20 | 20 | MDF Factory20 | 1480493.38 | 1495298.3132 | 0 | 1495298.3132
Qasr Rashwan Lot A | QASR RASHWAN A IPC 2 | 2 | Qasr Rashwan Lot A2 | 18076035.38 | 22109153.08 | 5979189.16 | 28088342.24
Cairo Monorail - 6th October | IPC#12 Monorail | 12 | Cairo Monorail - 6th October12 | 412800 | 408672 | 0 | 408672
Sohag HSR Station | HSR SOHAG IPC 1 | 1 | Sohag HSR Station1 | 14703480.67 | 7843918.88 | 0 | 13008126.88
W Dam PP Phase II (CP-117) | 17 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 168175.4286 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 240 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Kayan | IPC_3_Rowad_Kayan | 3 | Al-Kayan3 | 3145.52 | 0 | 0 | #DIV/0!
Taval Sarai 52 | 1 |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 93 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2105210019 |  | Miscellaneous Projects | 10500 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Cr. Inv. Retent. USD |  | Abo Quir - Badr 500KV | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Cr Soc inv 4-5 Itay | 4 | Beni Seuf - 3584 | 0 | 0 | 0 | #DIV/0!
Lina Farm Substation | Green Power EGP |  | Lina Farm Substation | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | Cr.Social |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
Canal Sugar S/s | Soc.2020 تشيد سكر مح |  | Canal Sugar S/s | 5000 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Inv.35&36 deductions | 35 | South Helwan PP (CP-117)35 | 0 | 0 | 0 | #DIV/0!
Air Defence College | IPC27TR0046// | 27 | Air Defence College27 | 52264.8 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.7 | 7 | Akhmem - Qena7 | 0 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | inv 1.2 d0080 | 1 | Expansion of Ring Road NRCC1 | 344835 | 0 | 0 | #DIV/0!
Kemet Tower | CR inv ( 9 ) Kemt | 9 | Kemet Tower9 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_INV. 9 | 9 | Akhmem Assiut9 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Inv 44 to 47 | 44 | Akhmem Assiut44 | 0 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Inv.16 - Lot 1 Rduc. | 16 | Mauritania Lot 116 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply.Inv.5 Ret | 5 | Ghana Street lighting5 | 22769.29 | 0 | 0 | #DIV/0!
El Sadat City | Sadat City Inv. 02 | 2 | El Sadat City2 | 15265218.98 | 0 | 0 | #DIV/0!
Cameron EDC | 024/2020adj |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Elsewedy Univ - Enabling Works | cr-sewedy uni-mep-07 | 7 | Elsewedy Univ - Enabling Works7 | 0 | 0 | 0 | #DIV/0!
Air Defense College | Air Def Fini5 IPC1 | 1 | Air Defense College1 | 46112467.5 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 245 |  | MAYSAN 400/132kV SS | 0 | 0 | 0 | #DIV/0!
New Capital | ref.2 |  | New Capital | 0 | 0 | 0 | #DIV/0!
UIC Project (LP-04-21) | 63 |  | UIC Project (LP-04-21) | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_INV.6 | 6 | Akhmem - Qena6 | 0 | 0 | 0 | #DIV/0!
Sodic East | crIPC12_sodic_east | 12 | Sodic East12 | 0 | 0 | 0 | #DIV/0!
Ora Zed Landscape Ph1 | CR Ora LandscapeIPC2 | 2 | Ora Zed Landscape Ph12 | 0 | 0 | 0 | #DIV/0!
Royal City | Cr Royal Zone ipc24 | 24 | Royal City24 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR-(10+11) USD-Shaba | 10 | Al-Shabab PP Phase II (CP-117)10 | 0 | 0 | 0 | #DIV/0!
Attaqa Power Plant | reverse |  | Attaqa Power Plant | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | OB.Ret. Cobra500 |  | Abo Quir - Badr 500KV | 24491299.16 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.11 | 11 | Akhmem - Qena11 | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11586 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | IPC 4 Aswan | 4 | Aswan axis - Daraw4 | 431029.25 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 59 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Ins. Inv.4 Ret | 4 | Ghana Street lighting4 | 6106.61 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 07 | 7 | Suez Gulf/S4 - 500KV OHTL7 | 36466.19 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 52 |  | Suez Gulf Substation | 2970926.8992 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 239 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 6 |  | Zafranaa - Beni Suef | 45355.35 | 0 | 0 | #DIV/0!
10th of Ramadan Railway | D0046 OB-Dec-2020/Cr | 2020 | 10th of Ramadan Railway2020 | 0 | 0 | 0 | #DIV/0!
Infra Project 4428 | 220621010 |  | Infra Project 4428 | 133177460.95 | 0 | 0 | #DIV/0!
Elhegaz | D0028-OB-Dec-2020Can | 2020 | Elhegaz2020 | 0 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC#1 | 1 | Maspiro Towers1 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | cr-Inv-01 MOC | 1 | MOC HQ at Diriyah1 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | close billing reclas |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | Reten.OB Zafrasouf |  | Zafranaa - Beni Suef | 1114578.04 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 13 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 12764.38 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 180065 |  | South Helwan PP (CP-117) | 2832.31 | 0 | 0 | #DIV/0!
Benban 4 As El-Nakra 220 K.V | تشيد النقره |  | Benban 4 As El-Nakra 220 K.V | 3651 | 0 | 0 | #DIV/0!
Port Said Grain Storage | Rent 002 |  | Port Said Grain Storage | 79400 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 9 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 98041.3524 | 0 | 0 | #DIV/0!
EGAT ADMIN (Pelletizing) | IPC03TR0094 | 3 | EGAT ADMIN (Pelletizing)3 | 59189.6 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 283 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
UIC Project (LP-04-21) | 61 |  | UIC Project (LP-04-21) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 110 |  | Suez Gulf Substation | -10577962.952 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Inv.20 - Lot 1 | 20 | Mauritania Lot 120 | 58223.2 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | Ref 2 |  | Barwa 2x60/22 KV S/S | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Inv.1 Temmay Cancel | 1 | Beni Seuf - 3581 | 0 | 0 | 0 | #DIV/0!
Tebbin PP Rehabitation(CP-124) | last inv. (4 EGP)113 |  | Tebbin PP Rehabitation(CP-124) | 1970173.27 | 0 | 0 | #DIV/0!
EIPICO Factory | Addition Work IPC07 | 7 | EIPICO Factory7 | 19850 | 0 | 0 | #DIV/0!
Bani Suef Old Substation | cr (23+24) |  | Bani Suef Old Substation | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 1 USD -El Tebein 113 |  | Miscellaneous Projects | 24940 | 0 | 0 | #DIV/0!
Mivida | CR.TR0009CLOSING.DEC |  | Mivida | 0 | 0 | 0 | #DIV/0!
MOTHANA 400/132kV SS | 205 |  | MOTHANA 400/132kV SS | -4216144.83 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 266 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 45 |  | Al-Shabab PP Phase II (CP-117) | 6504806.75 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CrMemo W.hold 12-EGP |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | Egy Ex awnash 2final |  | Egyptian Exchange Building | 7165085.715 | 0 | 0 | 7416455.004
Governmental Campus-N2 | 88 |  | Governmental Campus-N2 | 210662 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | reclass of rec. acco |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Mozambique TL | CR.P-50-12 AccRev | 50 | Mozambique TL50 | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 5 | 5 | Marsa Alam/ Bernes LOT2 OHTL5 | 12519.37 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Stamps inv.38 EGP | 38 | South Helwan PP (CP-117)38 | 0 | 0 | 0 | #DIV/0!
33KV Canal Farm Grid | Inv. 20 Farm | 20 | 33KV Canal Farm Grid20 | 4030952.04 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 15 EGP - Shabab | 15 | Al-Shabab PP Phase II (CP-117)15 | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-118) | DEC10 |  | Banha PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Cairo North PP Rehabilitation | 88 |  | Cairo North PP Rehabilitation | -1726617.7594 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.10 | 10 | Akhmem - Qena10 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Tax 73-74 cobra | 74 | Abo Quir - Badr 500KV74 | 140024.95 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | CR-MOC Inv 04 | 4 | MOC HQ at Diriyah4 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 53 |  | Al-Shabab PP Phase II (CP-117) | 4843098.61 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 10 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 93003.52 | 0 | 0 | #DIV/0!
IRAQ - Al-Diwaniya Power Plant | 2012220007 |  | IRAQ - Al-Diwaniya Power Plant | 0 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 198 |  | MAYSAN 400/132kV SS | -37109.952 | 0 | 0 | #DIV/0!
Military 110 Kayan Project | CR.refund ret. |  | Military 110 Kayan Project | 0 | 0 | 0 | #DIV/0!
Business District Hyde Park | Cr.( 6-9 ) HY Bark | 9 | Business District Hyde Park9 | 0 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 1 |  | MAYSAN 400/132kV SS | 37109.952 | 0 | 0 | #DIV/0!
Playa Resort | 41. |  | Playa Resort | 0 | 0 | 0 | #DIV/0!
Mostakbal 2 Package No. (8) | اتحاد تشيد P-62 | 62 | Mostakbal 2 Package No. (8)62 | 5000 | 0 | 0 | #DIV/0!
Infra Project 4428 | 2112220001 |  | Infra Project 4428 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr. Ins. Abolila |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
Maspiro Towers | CR-IPC005 | 5 | Maspiro Towers5 | 0 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 476 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | Cancel Inv#10 USD VO | 10 | Suez Gulf Substation10 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Part Inv 14 USD Shab | 14 | Al-Shabab PP Phase II (CP-117)14 | 40246.0652 | 0 | 0 | #DIV/0!
El-Warraq | CR IPC3 elwaraq | 3 | El-Warraq3 | -736709.2 | 0 | 0 | #DIV/0!
Katameya Creeks - RME | C..IPC13TR53 | 13 | Katameya Creeks - RME13 | 0 | 0 | 0 | #DIV/0!
Ora Zed Landscape Ph1 | CR ora landscapeIPC9 | 9 | Ora Zed Landscape Ph19 | 0 | 0 | 0 | #DIV/0!
Air Defence College | IPC26TR0046 | 26 | Air Defence College26 | 126903.32 | 0 | 0 | 126903.32
EPICO 3 Facility | Eipico material ipc3 | 3 | EPICO 3 Facility3 | 4676968.58 | 0 | 0 | 4910817.009
EPICO 3 Facility | Material On Site |  | EPICO 3 Facility | 57323484.33 | 0 | 0 | 60189658.5465
KATAMYA GREEKS LAND SCAPE STAR | IPC03TR0081 | 3 | KATAMYA GREEKS LAND SCAPE STAR3 | 1207954.09 | 0 | 0 | 1207954.09
Wadi Halfa Port | wady halfa ipc 5 | 5 | Wadi Halfa Port5 | 5072099.52 | 0 | 0 | 5325704.496
Residence 8 ( S09 ) | Inv ( 1 ) S09 | 1 | Residence 8 ( S09 )1 | 1390620 | 0 | 0 | 1390620
Tarek Abdel-Hakim Center | TAH ipc05 | 5 | Tarek Abdel-Hakim Center5 | 1271012.98 | 0 | 0 | 1271012.98
EIPICO Factory | IPC05TR54 | 5 | EIPICO Factory5 | 6138.09 | 0 | 0 | 6138.09
Al-Parco | INV ( 3 ) ALparco | 3 | Al-Parco3 | 2422608 | 0 | 0 | 2422608
Kemet Tower | inv ( 9 ) Kemt | 9 | Kemet Tower9 | 185120 | 0 | 0 | 185120
Business District Hyde Park | INV ( 4 ) HY Bark | 4 | Business District Hyde Park4 | 624167.75 | 0 | 0 | 624167.75
U3 & U5 | TR55-IPC3 | 3 | U3 & U53 | 34000.72 | 0 | 0 | 34000.72
Playa Resort | kantine 6 |  | Playa Resort | 35000 | 0 | 0 | 35000
Egyptian Exchange building | IPC000010 | 10 | Egyptian Exchange building10 | 85472.01 | 0 | 0 | 85472.01
HST - 6 October - Arab Cont. | IPC 1 HSR ARAB CONST | 1 | HST - 6 October - Arab Cont.1 | 2928500 | 0 | 0 | 2928500
Pridge 5 | inv ( 1 ) pridg 5 | 1 | Pridge 51 | 2100300 | 0 | 0 | 2100300
Infra Project 2531 | 220621004 |  | Infra Project 2531 | 154992519.05 | 0 | 0 | 162742145.0025
Infra Project 4428 | 220321003 |  | Infra Project 4428 | 110196949.52 | 0 | 0 | 115706796.996
Akhmem Assiut | Ref. Akhme Asuit T |  | Akhmem Assiut | 5000000 | 0 | 0 | 5000000
MDF Factory | MDF FACTORY IPC07 | 7 | MDF Factory7 | 15382008.96 | 0 | 0 | 16151109.408
New Babil 400/132KV GIS Substa | 2201210001 |  | New Babil 400/132KV GIS Substa | 2800720.76 | 2240576.61 | 0 | 2800720.76
Containment Data Center- | 36 |  | Containment Data Center- | 46429800 | 14645486 | 4875129 | 21952375.78
Containment Data Center- | 32 |  | Containment Data Center- | 19500516 | 0 | 0 | 19500516
Industria Sadat | Sadat Indust Inv. 03 | 3 | Industria Sadat3 | 10151330.88 | 10107509.75 | 4747538.81 | 15336604.57
Assuit PP (CP-118) | 2105210003 |  | Assuit PP (CP-118) | 96467.1135 | 101544.33 | 0 | 101544.33
Kafr Shokr Bridge | Kafr Shokr-IPC02 | 2 | Kafr Shokr Bridge2 | 7001830.48 | 0 | 0 | 7982086.7472
Ain-Sokhna PP(CP-102) | 2012210039 |  | Ain-Sokhna PP(CP-102) | 161718.62 | 0 | 0 | 161718.62
6th Oct. Ph2 PP-Elect Work | 2012210035 |  | 6th Oct. Ph2 PP-Elect Work | 3001868.6659 | 0 | 0 | 3001868.6659
LRT Project | TR0028DEC.Closing |  | LRT Project | 103200 | 0 | 0 | 103200
Taval Sarai 52 | TR0025DEC.Closing |  | Taval Sarai 52 | 662315.7 | 0 | 0 | 662315.7
Ministry Building EPOXY | TR0018DEC.Closing |  | Ministry Building EPOXY | 129748.87 | 0 | 0 | 129748.87
Taval Sarai 52 | IPC_5_Gama_Saray | 5 | Taval Sarai 525 | 251219 | 0 | 0 | 251219
Maspiro Towers | D0019-OB-Dec-2020 | 2020 | Maspiro Towers2020 | 3479650 | 0 | 0 | 3479650
HAC CCC JV | D0008-OB-Dec-2020 | 2020 | HAC CCC JV2020 | 11272720.57 | 0 | 0 | 11272720.57
Bahr El Baqar Treatment Plant | D0036-OB-Dec-2020 | 2020 | Bahr El Baqar Treatment Plant2020 | 1212810.3 | 0 | 0 | 1212810.3
South Helwan PP (CP-117) | 2009210006 |  | South Helwan PP (CP-117) | 239840.14 | 211966.82 | 37845.88 | 249812.7
Assuit PP (CP-118) | 2009210002 |  | Assuit PP (CP-118) | 2536557.0286 | 2238502.52 | 399507.73 | 2638010.25
Beni Suef Add-on Sales | 2005210009 |  | Beni Suef Add-on Sales | -1267421.32 | 0 | 0 | -1267421.32
Giza North PP Ph I,II (CP-117) | 2001210013 |  | Giza North PP Ph I,II (CP-117) | 9538.75 | 9538.75 | 0 | 9538.75
Baron Palace | 10035 |  | Baron Palace | 13094.4 | 0 | 0 | 13094.4
Manshiet Nasser Substation | 544 |  | Manshiet Nasser Substation | 258532.38 | 235887.19 | 0 | 235887.19
Manshiet Nasser Substation | 1907210015 |  | Manshiet Nasser Substation | 1226665.08 | 1105695.54 | 198545.2 | 1304240.74
LAYYAH CCPP | 472 |  | LAYYAH CCPP | 10283760 | 0 | 0 | 10283760
Benban 4 As El-Nakra 220 K.V | Inv. 1 Final ElNokra | 1 | Benban 4 As El-Nakra 220 K.V1 | 6953627.16 | 0 | 0 | 6953627.16
Suez Gulf Substation | 20 EGP TOAC Main |  | Suez Gulf Substation | 3168848.91 | 3000195 | 333355 | 3333550
Zafranaa - Ras Ghareb | Amend - Ras Ghareb |  | Zafranaa - Ras Ghareb | -3460.5 | 0 | 0 | -3460.5
Manshiet Nasser Substation | 1901210016 |  | Manshiet Nasser Substation | 640004.93 | 600084.62 | 65520.51 | 665605.13
Suez Gulf Substation | 1909210006 |  | Suez Gulf Substation | 64220.18 | 64220.18 | 0 | 64220.18
Suez Gulf Substation | 1909210001 |  | Suez Gulf Substation | 1500870.19 | 1578878 | 0 | 1578878
Zambia Project | SCD4/002 |  | Zambia Project | 78921.47 | 0 | 0 | 78921.47
AWEER POWER STATION 'H' Phase | 10167 |  | AWEER POWER STATION 'H' Phase | 211328.6 | 0 | 0 | 221895.03
Beni Suef ISKRA | 1907210008 |  | Beni Suef ISKRA | 369202415.3024 | 0 | 0 | 369202415.3024
Banha PP (CP-117) | 180135 |  | Banha PP (CP-117) | 5837.5 | 6111.71 | 0 | 6111.71
Beni-Suef Power Plant EPC | 180119 |  | Beni-Suef Power Plant EPC | 497965535.18 | 497965535.18 | 0 | 497965535.18
Ain-Sokhna PP (CP-117) | 180136 |  | Ain-Sokhna PP (CP-117) | 4785.53 | 5000.88 | 0 | 5000.88
Akhmem Assiut | Soc In 49 Asuit |  | Akhmem Assiut | 48705.75 | 0 | 0 | 48705.75
Al-Shabab PP Phase II (CP-117) | 180107 |  | Al-Shabab PP Phase II (CP-117) | 696722.97 | 622994.9 | 109940.28 | 732935.18
Al-Shabab PP Phase II (CP-117) | 27 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 32388.8762 | 28907.07 | 5101.25 | 34008.32
Elniger | 5004 ADJ |  | Elniger | 32830869.85 | 0 | 0 | 32830869.85
W Dam PP Phase II (CP-117) | 16 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 113117.95 | 0 | 0 | 113117.95
Suez Gulf Substation | 16 USD - Suez Gulf |  | Suez Gulf Substation | 704911 | 614419.9 | 70491.1 | 684911
W Dam PP Phase II (CP-117) | 19 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 370511.34 | 370511.34 | 0 | 370511.34
Lina Farm Substation | 7 EGP - Lina |  | Lina Farm Substation | 853142.14 | 853142.14 | 0 | 853142.14
Abou El Matameer and Sammanoud | 13-12-2018 | 12 | Abou El Matameer and Sammanoud12 | 4186152.58 | 0 | 0 | 4186152.58
South Helwan PP (CP-117) | SH Inv.35&36 comm | 35 | South Helwan PP (CP-117)35 | 21317.45 | 21317.45 | 0 | 21317.45
Marsa Matrouh 500KV | Inv, 4 usd Borg Arab | 4 | Marsa Matrouh 500KV4 | 1342780.82 | 0 | 0 | 1342780.82
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 05 |  | Giza North PP Ph I,II (CP-117) | 362626.33 | 362626.33 | 0 | 362626.33
Berket Ghelion | Adj Inv 7 | 7 | Berket Ghelion7 | 38242338.08 | 0 | 0 | 38242338.08
PIP Zona 2 | Adj inv 1 | 1 | PIP Zona 21 | 35598824.34 | 0 | 0 | 35598824.34
Mahmoudia Power Plant | 121 |  | Mahmoudia Power Plant | -1796304922.0321 | 0 | 0 | -1796304922.0321
Tebbin PP Rehabitation(CP-124) | 91 |  | Tebbin PP Rehabitation(CP-124) | 7260610.64 | 0 | 0 | 7260610.64
Cairo North PP Rehabilitation | 87 |  | Cairo North PP Rehabilitation | 1434708.9941 | 0 | 0 | 1434708.9941
KSA - PP-12 | 123 |  | KSA - PP-12 | 31773079.5235 | 0 | 0 | 31773079.5235
Attaqa Power Plant | 15 |  | Attaqa Power Plant | 2694458200 | 0 | 0 | 2694458200
Attaqa Power Plant | 118 |  | Attaqa Power Plant | 4536718951.9679 | 0 | 0 | 4536718951.9679
IRAQ - Substations Soil Invest | 36 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
IRAQ - Substations Soil Invest | 116 |  | IRAQ - Substations Soil Invest | 4177500 | 0 | 0 | 4177500
GPC-Gupco (Automation) | 12 |  | GPC-Gupco (Automation) | 1420317 | 0 | 0 | 1420317
Beni-Suef PP Site Preparation | 104 |  | Beni-Suef PP Site Preparation | 141694313.7565 | 0 | 0 | 141694313.7565
Banha PP (CP-117) | 71 |  | Banha PP (CP-117) | 30941490.9995 | 0 | 0 | 30941490.9995
South Helwan PP (CP-117) | 108 |  | South Helwan PP (CP-117) | 6765880.53 | 0 | 0 | 6765880.53
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 01 |  | Giza North PP Ph I,II (CP-117) | 23371.75 | 23371.75 | 0 | 23371.75
Lina Farm Substation | 5 EGP - Lina |  | Lina Farm Substation | 1337130.24 | 1337130.24 | 0 | 1337130.24
Attaqa Power Plant | Discount USD Reverse |  | Attaqa Power Plant | 2038853.32 | 2038853.32 | 0 | 2038853.32
Attaqa Power Plant | close interest |  | Attaqa Power Plant | 2038853.32 | 2038853.32 | 0 | 2038853.32
Attaqa Power Plant | close discointerests |  | Attaqa Power Plant | 2038853.32 | 2038853.32 | 0 | 2038853.32
New Heliopolis | Inv.8 Heliopolis | 8 | New Heliopolis8 | 5936553.33 | 0 | 0 | 5936553.33
Akhmem - Qena | Inv. 7 Akhmem Qena | 7 | Akhmem - Qena7 | 45444956.05 | 0 | 0 | 45444956.05
Akhmem Assiut | inv. 9 Assuit Akhmem | 9 | Akhmem Assiut9 | 30032833.14 | 0 | 0 | 30032833.14
Akhmem Assiut | inv. 7 Assuit Akhmem | 7 | Akhmem Assiut7 | 2463575.15 | 0 | 0 | 2463575.15
Pyramids Industrial Park | Ret.Inv.4 PIP West | 4 | Pyramids Industrial Park4 | 4975053.05 | 0 | 0 | 4646549.86
Pyramids Industrial Park | Inv.3 PIP West | 3 | Pyramids Industrial Park3 | 5283083.53 | 0 | 0 | 4966098.52
Pyramids Industrial Park | 18/1 |  | Pyramids Industrial Park | 755365.83 | 0 | 0 | 30000.01
Barwa 2x60/22 KV S/S | 1 |  | Barwa 2x60/22 KV S/S | 1000 | 0 | 0 | 1000
EMAAR-PKG#62-UPTOWN | Amend VAT PKG#62(1) |  | EMAAR-PKG#62-UPTOWN | 55761.79 | 0 | 0 | 55761.79
Suez Gulf Substation | 4 EGP - Suez Gulf |  | Suez Gulf Substation | 853245.26 | 0 | 86348.42 | 863484.2031
Suez Gulf Substation | 9 USD - Suez Gulf |  | Suez Gulf Substation | 130549.7 | 0 | 13054.97 | 130549.7
Al-Shabab PP Phase II (CP-117) | 7 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 1994601.61 | 0 | 0 | 2094331.6905
Suez Gulf Substation | 8 USD/123/2011/2012 |  | Suez Gulf Substation | 38468 | 0 | 0 | 38468
Suez Gulf Substation | 10 USD - Suez Gulf |  | Suez Gulf Substation | 2063047.78 | 0 | 206304.78 | 2063047.78
West Damietta PP Phase I | 40 |  | West Damietta PP Phase I | 9072886 | 0 | 0 | 18145772
Algeria S/Ss | M-D-003 | 3 | Algeria S/Ss3 | 2824154.24 | 2541738.82 | 0 | 2541738.82
Kuwait | Erection/H001 |  | Kuwait | 57389.81 | 37303.38 | 0 | 37303.38
Kuwait | 29-132KVA-H | 132 | Kuwait132 | 559622.7 | 363754.75 | 0 | 363754.75
W Dam PP Phase II (CP-117) | 180035 |  | W Dam PP Phase II (CP-117) | 94997.1048 | 0 | 0 | 99746.96
Al-Shabab PP Phase II (CP-117) | 180025 |  | Al-Shabab PP Phase II (CP-117) | 144094.5714 | 0 | 0 | 151299.3
W Dam PP Phase II (CP-117) | 24 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 134928.7048 | 120423.87 | 21251.27 | 141675.14
Al-Shabab PP Phase II (CP-117) | 20 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 43165.1619 | 0 | 6798.52 | 6798.52
W Dam PP Phase II (CP-117) | 14 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 236760.7905 | 0 | 37289.82 | 37289.82
W Dam PP Phase II (CP-117) | 2002210029 |  | W Dam PP Phase II (CP-117) | 1378109.92 | 1362246.19 | 87491.06 | 1449737.25
Al-Shabab PP Phase II (CP-117) | 11 USD -Shabab |  | Al-Shabab PP Phase II (CP-117) | 4623986.05 | 4134670.27 | 729647.7 | 4864317.97
Al-Shabab PP Phase II (CP-117) | 11 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 434762.5333 | 0 | 0 | 68475.1
Al-Shabab PP Phase II (CP-117) | 6 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 3046336.89 | 0 | 456950.53 | 3198653.7345
Al-Shabab PP Phase II (CP-117) | 4 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 434081.1364 | 0 | 65893.52 | 439290.11
Al-Shabab PP Phase II (CP-117) | 2 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 5630200.6621 | 0 | 854664.46 | 5697763.07
IRAQ - Substations Soil Invest | 5 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
Suez Gulf Substation | Inv 2 EGP VO SG | 2 | Suez Gulf Substation2 | 107072.2476 | 101183.27 | 11242.59 | 112425.86
Suez Gulf Substation | 5EGP rema Tax Balanc |  | Suez Gulf Substation | 100898.24 | 24104.13 | 76794.11 | 100898.24
Suez Gulf Substation | 3 EGP - Suez Gulf |  | Suez Gulf Substation | 3697395.95 | 0 | 374176.47 | 3741764.7014
Suez Gulf Substation | 7 USD/123/2011/2012 |  | Suez Gulf Substation | 565715.37 | 0 | 0 | 565715.37
Siemens 6x500/220 KV GIS-MOU | Inv 67 P8 Assuit | 67 | Siemens 6x500/220 KV GIS-MOU67 | 3458421.51 | 2501822.12 | 518763.23 | 3020585.35
Siemens 6x500/220 KV GIS-MOU | inv 44 P11El Natroun | 44 | Siemens 6x500/220 KV GIS-MOU44 | 2586656.06 | 1871186.99 | 387998.41 | 2259185.4
Damac 2x60/22 KV S/S | Inv. 33 Damac | 33 | Damac 2x60/22 KV S/S33 | 514651.22 | 364082.81 | 77197.67 | 441280.48
Damac 2x60/22 KV S/S | Inv 20 Damac | 20 | Damac 2x60/22 KV S/S20 | 1067206.57 | 754829.17 | 160081.01 | 914910.18
South Helwan PP (CP-117) | 8 EGP South Helwan |  | South Helwan PP (CP-117) | 185480.3714 | 194754.39 | 0 | 194754.39
Abu Qir PP (CP-118) | 449 Euro - Avice |  | Abu Qir PP (CP-118) | 257674.92 | 243948.8495 | 0 | 257674.92
Berket Ghelion | 1 Ghelion |  | Berket Ghelion | 5097870.6 | 3294440.45 | 1274468.9 | 4568909.35
New Capital | Inv 6 Abo Zaabl | 6 | New Capital6 | 168895.238 | 122537.5 | 17734 | 140271.5
PIP- Zonafranca | Inv. 16 Zona franka | 16 | PIP- Zonafranca16 | 15496914.06 | 0 | 12620915.75 | 12620915.75
Giza North PP Phase3(CP-117) | 40 EGP-Giza No III |  | Giza North PP Phase3(CP-117) | 20673.1143 | 16815.76 | 4693.13 | 21706.77
Giza North PP Phase3(CP-117) | 38 EGP-Giza N. III |  | Giza North PP Phase3(CP-117) | 5005.7524 | 4467.63 | 788.41 | 5256.04
South Helwan PP (CP-117) | 8 Euro- South Helwan |  | South Helwan PP (CP-117) | 257510.019 | 40557.83 | 0 | 40557.83
Shanghai CO. | 10079 |  | Shanghai CO. | 14140 | 14140 | 0 | 14140
Tamey El-amdeed Substation | TAM-CW-EURO-10 | 10 | Tamey El-amdeed Substation10 | 366629.05 | 0 | 54994.36 | 54994.36
Tamey El-amdeed Substation | TAM-CW-EGP-18 | 18 | Tamey El-amdeed Substation18 | 1445564.75 | 1069717.91 | 216834.71 | 1286552.62
Tamey El-amdeed Substation | TAM-CW-EGP-20 | 20 | Tamey El-amdeed Substation20 | 1522593.91 | 1126719.49 | 228389.09 | 1355108.58
Ismailiya East Substation | ISE-CW-EGP-16 | 16 | Ismailiya East Substation16 | 1655757 | 1225260.18 | 248363.55 | 1473623.73
Tamey El-amdeed Substation | TAM-CW-EGP-15 | 15 | Tamey El-amdeed Substation15 | 3498515.21 | 2588901.26 | 524777.28 | 3113678.54
Tamey El-amdeed Substation | TAM-CW-EURO-05 | 5 | Tamey El-amdeed Substation5 | 949834.91 | 702877.83 | 142475.24 | 845353.07
Beni Suef Substation R61 | 19100026 |  | Beni Suef Substation R61 | 2222634 | 1644749.16 | 333395.1 | 1978144.26
Beni Suef Substation R61 | BSF-CW-EGP-13 | 13 | Beni Suef Substation R6113 | 2287835 | 1692963.19 | 343175.25 | 2036138.44
Al Mostathmreen GIS Substation | MOS-SD-EGP-IPC 25 | 25 | Al Mostathmreen GIS Substation25 | 27165 | 20237.92 | 4074.75 | 24312.67
Al Mostathmreen GIS Substation | 18sd mosstasmreen |  | Al Mostathmreen GIS Substation | 67912 | 50594.24 | 10186.92 | 60781.16
Al Mostathmreen GIS Substation | MOS (3) |  | Al Mostathmreen GIS Substation | 571620 | 425856.9 | 85743 | 511599.9
Al-Shabab PP Phase II (CP-117) | 20 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 43165.1619 | 0 | 0 | 45323.42
W Dam PP Phase II (CP-117) | 17 EGP -West Domiat |  | W Dam PP Phase II (CP-117) | 6435.43 | 0 | 26487.63 | 26487.63
Al-Shabab PP Phase II (CP-117) | 180111 |  | Al-Shabab PP Phase II (CP-117) | 272851.77 | 243978.27 | 43054.99 | 287033.26
Berket Ghelion | Inv 13 Ghelion | 13 | Berket Ghelion13 | 2633893.65 | 1573622.06 | 658473.41 | 2232095.47
Berket Ghelion | Gheleon 5 |  | Berket Ghelion | 1683956.45 | 1006052.23 | 420989.1 | 1427041.33
Berket Ghelion | 9 |  | Berket Ghelion | 1302086.52 | 777996.67 | 325521.65 | 1103518.32
Berket Ghelion | Gheleon 6 |  | Berket Ghelion | 2204220.59 | 1316967.13 | 551055.1495 | 1868022.2795
EMAAR-PKG#107-MARASSI | (5) pkg#107 |  | EMAAR-PKG#107-MARASSI | 3207732.59 | 8441515.754 | 1667094.28 | 5054305.017
Giza North PP Phase3(CP-117) | 26 EUR - Giza N. III |  | Giza North PP Phase3(CP-117) | 338411.5429 | 302032.3 | 0 | 302032.3
Giza North PP Ph I,II (CP-117) | 37 EGP-Giza North 1& |  | Giza North PP Ph I,II (CP-117) | 564966.8762 | 593215.22 | 0 | 593215.22
Beni Seuf - 358 | Inv. 17 Oewon Mousa | 17 | Beni Seuf - 35817 | 14506308.05 | 0 | 2494851.9 | 2494851.9
Beni Seuf - 358 | Inv. 13 Oewon Mousa | 13 | Beni Seuf - 35813 | 4049842.32 | 0 | 697384.05 | 697384.05
W Dam PP Phase II (CP-117) | 3 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 1700567.1146 | 437023.56 | 258146.09 | 932288.7
Damac 2x60/22 KV S/S | Inv 21 Damac | 21 | Damac 2x60/22 KV S/S21 | 1280709.49 | 905861.84 | 192106.44 | 1097968.28
Damac 2x60/22 KV S/S | Inv 19 Damac | 19 | Damac 2x60/22 KV S/S19 | 5822687.66 | 4119121.2 | 873403.15 | 4992524.35
Al-Wukair 11 Substation | close un appl sak |  | Al-Wukair 11 Substation | 9492793.9 | 9492793.9 | 0 | 9492793.9
Al-Wukair 11 Substation | Inv 11 Qatar accrual | 11 | Al-Wukair 11 Substation11 | 11877918 | 11877918 | 0 | 11877918
Al-Shabab PP Phase II (CP-117) | 16 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 825100.019 | 305616.11 | 129953.25 | 435569.36
IRAQ - Al-Diwaniya Power Plant | Inv No 65 Dewania | 65 | IRAQ - Al-Diwaniya Power Plant65 | 1113366.44 | 1113366.44 | 0 | 1113366.44
Beni-Suef Power Plant EPC | Beni Swef Inv April |  | Beni-Suef Power Plant EPC | 175000000 | 175000000 | 0 | 175000000
New Giza 2 | (21)new giza 2 |  | New Giza 2 | 6348768 | 4635241.34 | 1333241.35 | 5968482.69
Royal City | ROYAL CITY-IPC17 | 17 | Royal City17 | 6172362.54 | 5868379.577 | 2768560.39 | 8636939.967
Attaqa Power Plant | Sand Attaqa May |  | Attaqa Power Plant | 25250000 | 25250000 | 0 | 25250000
ASEC-El Menya | Inv 24 Asec | 24 | ASEC-El Menya24 | 825530.61 | 532467.24 | 247659.18 | 780126.42
Abu Qir PP (CP-118) | Invoices Abo Quer, |  | Abu Qir PP (CP-118) | 796701.63 | 796701.63 | 0 | 796701.63
Banha PP (CP-118) | Banha 118 Invoice |  | Banha PP (CP-118) | 26588.39 | 0 | 0 | 0
South Helwan PP (CP-117) | 1905210007 |  | South Helwan PP (CP-117) | 15678.6 | 14019.48 | 2474.02 | 16493.5
South Helwan PP (CP-117) | 180142 |  | South Helwan PP (CP-117) | 213738.98 | 224848.07 | 0 | 224848.07
Al-Shabab PP Phase II (CP-117) | 180157 |  | Al-Shabab PP Phase II (CP-117) | 11502.34 | 0 | 0 | 12100.17
W Dam PP Phase II (CP-117) | 13 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 48329.6 | 43134.17 | 7611.91 | 50746.08
South Helwan PP (CP-117) | 1906210008 |  | South Helwan PP (CP-117) | 237562.42 | 209953.83 | 37486.46 | 247440.29
South Helwan PP (CP-117) | 180012 |  | South Helwan PP (CP-117) | -2803954.29 | -2507236.47 | -442453.49 | -2949689.96
South Helwan PP (CP-117) | 180010 |  | South Helwan PP (CP-117) | 3254690.99 | 0 | 513578.06 | 513578.06
Apache Electrical Works | Apachi Inv No P.C#17 | 17 | Apache Electrical Works17 | 60976.03 | 60976.03 | 0 | 60976.03
Suez PP (CP-106) | 5 EGP - Suez 106 |  | Suez PP (CP-106) | 947195.5 | 928251.58 | 0 | 928251.58
EMAAR-PKG#53-UPTOWN | OB-SI-PKG#53 |  | EMAAR-PKG#53-UPTOWN | 6555257.77 | 6555257.56 | 0 | 6555257.56
Al Mostathmreen GIS Substation | cw (8) mosstsmren |  | Al Mostathmreen GIS Substation | 384924 | 286768.31 | 57738.64 | 344506.95
South Helwan PP (CP-117) | 9 Euro-South Helwan |  | South Helwan PP (CP-117) | 1895104.9524 | 1989860.2 | 0 | 1989860.2
South Helwan PP (CP-117) | 8 EuroSouth Helwan |  | South Helwan PP (CP-117) | 229827.69 | 229827.69 | 0 | 229827.69
South Helwan PP (CP-117) | 10 Euro-South Helwan |  | South Helwan PP (CP-117) | 40293.5333 | 42308.21 | 0 | 42308.21
Al Mostathmreen GIS Substation | (9) CW |  | Al Mostathmreen GIS Substation | 454520 | 338617.23 | 68178.1 | 406795.33
Banha PP (CP-118) | 20 USD - Banha 118 |  | Banha PP (CP-118) | 18951.29 | 18951.29 | 0 | 18951.29
Tebbin PP Rehabitation(CP-124) | 3 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 1081541.48 | 1081541.48 | 0 | 1081541.48
Suez Gulf Substation | 487 |  | Suez Gulf Substation | 43989.39 | 41648.17 | 4627.57 | 46275.74
Al-Wukair 11 Substation | Inv Qatar (13 to 18) |  | Al-Wukair 11 Substation | 4711367.06 | 4711367.06 | 0 | 4711367.06
Al-Wukair 11 Substation | Inv 19 Qatar | 19 | Al-Wukair 11 Substation19 | 721597.55 | 721597.55 | 0 | 721597.55
New Giza 2 | new giza2-ipc 26+ | 26 | New Giza 226 | 1338966.63 | 1405914.9615 | 0 | 1405914.9615
EMAAR-PKG#85-UPTOWN | IPC 01 PKG#85 | 1 | EMAAR-PKG#85-UPTOWN1 | 2036311.19 | 813632.5095 | 850500 | 1664132.5095
Al Mostathmreen GIS Substation | 8sd euro mosstsmreen |  | Al Mostathmreen GIS Substation | 2082255 | 1509634.65 | 312338.37 | 1821973.02
Al Mostathmreen GIS Substation | 4sw mosstsmreen |  | Al Mostathmreen GIS Substation | 2504240 | 1865658.8 | 375636 | 2241294.8
Ismailiya East Substation | 1cw ismailya |  | Ismailiya East Substation | 5586802 | 4162167.49 | 838020.3 | 5000187.79
Ministries Buildings | Allocation IPC10+ | 10 | Ministries Buildings10 | 23464170 | 14358824.53 | 3231139 | 17589963.53
Akhmem Assiut | Inv.45 Assuit Akhmem | 45 | Akhmem Assiut45 | 5322395.74 | 3832124.92 | 798359.36 | 4630484.28
Akhmem Assiut | Inv.39 Assuit Akhmem | 39 | Akhmem Assiut39 | 5268473.53 | 4162094.09 | 790271.03 | 4952365.12
Akhmem Assiut | Inv.38 Assuit Akhmem | 38 | Akhmem Assiut38 | 2186851.82 | 1727084.04 | 328027.77 | 2055111.81
Akhmem - Qena | Inv.43 Qena Akhmem | 43 | Akhmem - Qena43 | 9120685.97 | 6338876.74 | 1368102.9 | 7706979.64
Akhmem - Qena | Inv. 2 Akhmem Qena | 2 | Akhmem - Qena2 | 18072311.52 | 10753025.3375 | 2710846.73 | 13463872.0675
Al-Shabab PP Phase II (CP-117) | 14 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1073779.3048 | 718392.43 | 126775.13 | 845167.56
W Dam PP Phase II (CP-117) | refund CSI |  | W Dam PP Phase II (CP-117) | 4940.27 | 4940.27 | 0 | 4940.27
Ghana | 34/P/10/ER/2017/USD |  | Ghana | 430731.22 | 430716.72 | 0 | 430716.72
Abou El Matameer and Sammanoud | Inv 88 P7 Sammound | 88 | Abou El Matameer and Sammanoud88 | 4187340.43 | 3029122.07 | 628101.07 | 3657223.14
Abou El Matameer and Sammanoud | Inv 74 P2 Sammound | 74 | Abou El Matameer and Sammanoud74 | 16166738.95 | 11695018.96 | 2425010.84 | 14120029.8
Siemens 6x500/220 KV GIS-MOU | Ret. Banh refund |  | Siemens 6x500/220 KV GIS-MOU | 3779078.8 | 3779078.8 | 0 | 3779078.8
Badr | Inv. 17 Badr | 17 | Badr17 | 7183281.24 | 5333175.13 | 1077492.19 | 6410667.32
Badr | Inv. 16 Badr | 16 | Badr16 | 7449098.4 | 5530955.56 | 1117364.76 | 6648320.32
Badr | Inv. 15 Badr | 15 | Badr15 | 26672144 | 19804066.92 | 4000821.6 | 23804888.52
Barwa and Damac 220 OHTL | Inv No4 Wattanya220 | 4 | Barwa and Damac 220 OHTL4 | 5491423.39 | 3178530.8 | 823713.54 | 4002244.34
Suez Gulf Substation | 180087 |  | Suez Gulf Substation | 5242.42 | 4963.41 | 551.49 | 5514.9
Suez Gulf Substation | 180052 |  | Suez Gulf Substation | 273875.83 | 259299.49 | 28811.05 | 288110.54
Siemens 6x500/220 KV GIS-MOU | ref.reten wadi elnat |  | Siemens 6x500/220 KV GIS-MOU | 5115619.9 | 5115619.9 | 0 | 5115619.9
Al Mostathmreen GIS Substation | 23sd elmostsmrin |  | Al Mostathmreen GIS Substation | 666790 | 496758.55 | 100018.5 | 596777.05
Abou El Matameer and Sammanoud | Inv 75 P4Abo Matamir | 75 | Abou El Matameer and Sammanoud75 | 3887553.2 | 2812255.98 | 583132.98 | 3395388.96
Beni Seuf - 358 | Itay inv.4 -358- | 4 | Beni Seuf - 3584 | 37404136.65 | 29619797.6 | 5727111.54 | 35346909.14
Military 110 Kayan Project | Elkayan Inv.10 | 10 | Military 110 Kayan Project10 | 37956407.49 | 33595160.8 | 0 | 33595160.8
South Helwan PP (CP-117) | 180059 |  | South Helwan PP (CP-117) | 181627.02 | 162407.03 | 28660.06 | 191067.09
Tamey El-amdeed Substation | (2)cw almansora |  | Tamey El-amdeed Substation | 5988139.38 | 4460637.4 | 898220.91 | 5358858.31
Sodic Club House | SODIC CLUB-IPC (28) | 28 | Sodic Club House28 | 5110738.79 | 5960049.8995 | 509871.31 | 6469921.2095
Beni Seuf - 358 | Soci. Proj.358K.M |  | Beni Seuf - 358 | 12713394.33 | 12699012.67 | 0 | 12699012.67
Assuit PP (CP-118) | 2105210004 |  | Assuit PP (CP-118) | 17216.9925 | 18123.15 | 0 | 18123.15
Assuit PP (CP-118) | 1906210013 |  | Assuit PP (CP-118) | 173545.25 | 154889.13 | 27333.38 | 182222.51
Assuit PP (CP-118) | 1904210004 |  | Assuit PP (CP-118) | 367639.92 | 328118.63 | 57903.29 | 386021.92
Assuit PP (CP-118) | 2007210005 |  | Assuit PP (CP-118) | 2666762.73 | 2353418.12 | 420015.13 | 2773433.25
Assuit PP (CP-118) | 2001210015 |  | Assuit PP (CP-118) | 3840.35 | 3427.51 | 604.86 | 4032.37
Assuit PP (CP-118) | 2005210002 |  | Assuit PP (CP-118) | 278047.9 | 248157.75 | 43792.54 | 291950.29
Assuit PP (CP-118) | 1908210002 |  | Assuit PP (CP-118) | 191141.48 | 170593.77 | 30104.78 | 200698.55
Marsa Matrouh 500KV | Inv.64 Borg Alarab | 64 | Marsa Matrouh 500KV64 | 16170508.44 | 11578082.6 | 1697903.39 | 13275985.99
Marsa Matrouh 500KV | Inv.45 Borg Alarab | 45 | Marsa Matrouh 500KV45 | 3559594.29 | 3109304.96 | 373757.4 | 3483062.36
Marsa Matrouh 500KV | Inv.38 Borg Alarab | 38 | Marsa Matrouh 500KV38 | 25694937.82 | 18397577.91 | 2697968.47 | 21095546.38
Marsa Matrouh 500KV | Inv.5 Usd borg alarb | 5 | Marsa Matrouh 500KV5 | 1316451.44 | 911498.9551 | 138227.4 | 1049726.3551
El Amal Bridge | ALAMAL BRIDGE- FINAL |  | El Amal Bridge | 10084716.7 | 6785022.95 | 0 | 9539124.95
Lina Farm Substation | 3 EGP - Lina |  | Lina Farm Substation | 1347809.11 | 1347809.11 | 0 | 1347809.11
Cairo Capital S1 | C.R 1-2% | 2 | Cairo Capital S12 | 0 | 0 | 0 | 0
New Heliopolis | Heliopolise 6 |  | New Heliopolis | 18174477.52 | 14524441.85 | 1784733.74 | 16309175.59
MAYSAN 400/132kV SS | 199 |  | MAYSAN 400/132kV SS | 98778.12 | 98778.12 | 0 | 98778.12
Apache Electrical Works | Apachi Inv No PC.#28 |  | Apache Electrical Works | 50471.54 | 50471.54 | 0 | 50471.54
Cairo Capital S1 | Inv. 4 Project S 1 | 4 | Cairo Capital S14 | 413660683.46 | 311279259.7 | 62049102.52 | 373328362.22
South Helwan PP (CP-117) | 180126 |  | South Helwan PP (CP-117) | 187204.53 | 196934.5 | 0 | 196934.5
South Helwan PP (CP-117) | 180122 |  | South Helwan PP (CP-117) | 127880.98 | 134527.6 | 0 | 134527.6
New Heliopolis | Inv.7. Heliopolis | 7 | New Heliopolis7 | 9286928 | 7420621.5 | 911976.35 | 8332597.85
Beni Suef Substation R61 | 18100068 |  | Beni Suef Substation R61 | 271650 | 202379.25 | 40747.5 | 243126.75
Beni Suef Substation R61 | BSF-SW-IPC3 | 3 | Beni Suef Substation R613 | 1063125 | 792028.12 | 159468.75 | 951496.87
Royal City | IPC9-ROYAL CITY | 9 | Royal City9 | 7480024.23 | 8085844.5015 | 1527570.78 | 9613415.2815
Kuraiamte Lot1&2 | Inv 1 Kuraiamte | 1 | Kuraiamte Lot1&21 | 263157.89 | 242528.11 | 0 | 242528.11
NUCA R05 - Z02 | R5-IPC26 | 26 | NUCA R05 - Z0226 | 16808375.6 | 14141308.65 | 1775540.1 | 15916848.75
NUCA R05 - Z02 | R5 - IPC18 | 18 | NUCA R05 - Z0218 | 28976061.4 | 23864722.8 | 2968175.15 | 26832897.95
Hassan El Mamoun Bridge | امر توريد حسن المأمو |  | Hassan El Mamoun Bridge | 6631000 | 4799695 | 1599903.15 | 6399598.15
Akhmem Assiut | Inv.14 Assuit Akhmem | 14 | Akhmem Assiut14 | 6852900.15 | 5448055.63 | 1027935.02 | 6475990.65
Tamey El-amdeed Substation | TAM-CW-EURO-01 | 1 | Tamey El-amdeed Substation1 | 583741.07 | 434887.09 | 87561.16 | 522448.25
Suez Gulf Substation | 180089 |  | Suez Gulf Substation | 8156.34 | 7722.24 | 858.03 | 8580.27
Marsa Matrouh 500KV | Inv.5 Borg Alarab | 5 | Marsa Matrouh 500KV5 | 14324722.8 | 14324722.8 | 0 | 14324722.8
Akhmem - Qena | Inv.22 Qena- Akhmem$ | 22 | Akhmem - Qena22 | 125345.85 | 105686.39 | 0 | 105686.39
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-IPC2 | 2 | Elsewedy Univ - Enabling Works2 | 1370079.63 | 881744.3515 | 431575.08 | 1313319.4315
Phosfat | Inv.1 Phosfat | 1 | Phosfat1 | 1181861.15 | 1052493.75 | 0 | 1052493.75
P-28-16 Balat Owinat Lot 2 | Inv. 13 Balat Lot 2 | 13 | P-28-16 Balat Owinat Lot 213 | 11083923.08 | 7104400.21 | 1163811.92 | 8268212.13
New Capital Tunnels | TUNNLE- IPC FINAL |  | New Capital Tunnels | 1188000 | 1118669.8 | 0 | 1118669.8
Akhmem Assiut | So.$4-8:19Assuit | 8 | Akhmem Assiut8 | 10725414 | 10725414 | 0 | 10725414
Akhmem Assiut | Inv.14Assuit Akhmem$ | 14 | Akhmem Assiut14 | 2945516.82 | 2489224.57 | 0 | 2489224.57
NUCA R05 - Z02 | R5 (1) ipc 33 final | 33 | NUCA R05 - Z0233 | 43004105 | 0 | 81448677.66 | 81448677.66
AWEER POWER STATION 'H' Phase | CON/032 |  | AWEER POWER STATION 'H' Phase | 798561.66 | 700959.6754 | 88729.07 | 789688.7454
AWEER POWER STATION 'H' Phase | LOC/024 |  | AWEER POWER STATION 'H' Phase | 669432.45 | 587612.9257 | 74381.38 | 661994.3057
AWEER POWER STATION 'H' Phase | Con-012 Rev0 | 12 | AWEER POWER STATION 'H' Phase12 | 1597123.3 | 1579377.49 | 0 | 1579377.49
AWEER POWER STATION 'H' Phase | 10389 |  | AWEER POWER STATION 'H' Phase | 1148623.04 | 1008235.782 | 127624.78 | 1135860.562
AWEER POWER STATION 'H' Phase | 10371 |  | AWEER POWER STATION 'H' Phase | 1754426.81 | 1189996.8491 | 544936.3214 | 1734933.1705
Marsa Matrouh 500KV | Inv. 5 Borg Alarab | 5 | Marsa Matrouh 500KV5 | 14324722.8 | 12512645.87 | 1504095.89 | 14016741.76
EDNC Retail & Offices Civil | Soreal IPC030 | 30 | EDNC Retail & Offices Civil30 | 27535188.38 | 24351196.859 | 5630.52 | 24356827.379
Al Mostathmreen GIS Substation | MOS-CW-EGP-IPC14 F | 14 | Al Mostathmreen GIS Substation14 | 5028521.25 | 3753066.3 | 754278.26 | 4507344.56
Military 110 Kayan Project | Refund Retention K |  | Military 110 Kayan Project | 19499892 | 19499892 | 0 | 19499892
DPW Onshore Port & Terminal | DP WORLD - IPC14 | 14 | DPW Onshore Port & Terminal14 | 141052143.07 | 104378585.87 | 21157821.46 | 125536407.33
Elsewedy Univ - Enabling Works | ELSWEDYUNI-MEP-IPC07 | 7 | Elsewedy Univ - Enabling Works7 | 4929812 | 2278076.58 | 1035260.52 | 3313337.1
Elsewedy Univ - Enabling Works | ELSWEDYUNI-F&M-IPC04 | 4 | Elsewedy Univ - Enabling Works4 | 2548899.1 | 1785482.76 | 1253062.6 | 3038545.36
Elsewedy Univ - Enabling Works | uni-fin&mep-ipc09 | 9 | Elsewedy Univ - Enabling Works9 | 43369350.27 | 19287810.0535 | 10318111.12 | 29605921.1735
Badr | Inv. 8 Badr | 8 | Badr8 | 18293266 | 13582332.05 | 2743989.9 | 16326321.95
EMAAR-PKG117- MARASSI | PKG#117- IPC 09 | 9 | EMAAR-PKG117- MARASSI9 | 3150407.65 | 2971025.94 | 327732.45 | 3298758.39
Manshiet Nasser Substation | 1907210014 |  | Manshiet Nasser Substation | 1176546.89 | 1055886.42 | 189363.93 | 1245250.35
Manshiet Nasser Substation | 180176 |  | Manshiet Nasser Substation | 112126.2 | 95307.27 | 16818.93 | 112126.2
Manshiet Nasser Substation | 516 |  | Manshiet Nasser Substation | 12761.25 | 7059.53 | 1914.19 | 8973.72
El Mostakbal City Project | Inv. 1 Mostakbal | 1 | El Mostakbal City Project1 | 59088562.35 | 49042372.38 | 12408598.09 | 61450970.47
Fish Market | SOUQ ELSAMAK-PO01 |  | Fish Market | 13284991.95 | 9151350 | 3050451.2 | 12201801.2
Elsewedy Univ - Enabling Works | UNI-FIN&MEP-IPC1 | 1 | Elsewedy Univ - Enabling Works1 | 1805053.36 | 1727255.568 | 0 | 1727255.568
SHAT Al ARAB 400/132kV SS | 224 |  | SHAT Al ARAB 400/132kV SS | 181470.42 | 181470.42 | 0 | 181470.42
SHATRA 400/132kV SS | 219 |  | SHATRA 400/132kV SS | 482066.18 | 482066.18 | 0 | 482066.18
Manshiet Nasser Substation | 1901210018 |  | Manshiet Nasser Substation | 1010008.2 | 1050408.53 | 0 | 1050408.53
Kayan 3 New Cairo Capital City | KAYAN FINSH1-IPC08 | 8 | Kayan 3 New Cairo Capital City8 | 53003261.27 | 13840715 | 49707094.9 | 64025572.75
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 32 | 32 | Benban 500 K.V/95 K.M32 | 3122671.24 | 2407579.56 | 327880.48 | 2735460.04
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 31 | 31 | Benban 500 K.V/95 K.M31 | 396624.49 | 305212.96 | 41645.57 | 346858.53
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 23 | 23 | Benban 500 K.V/95 K.M23 | 65885.56 | 50799.73 | 6917.98 | 57717.71
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 14 | 14 | Benban 500 K.V/95 K.M14 | 989858.15 | 763182.34 | 103935.11 | 867117.45
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 12 | 12 | Benban 500 K.V/95 K.M12 | 359948.42 | 277522.77 | 37794.58 | 315317.35
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 7 | 7 | Benban 500 K.V/95 K.M7 | 37912946.57 | 29230289.22 | 3980859.39 | 33211148.61
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 3 | 3 | Benban 500 K.V/95 K.M3 | 1353959.24 | 1043905.2 | 142165.72 | 1186070.92
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 28 | 28 | Benban 500 K.V / 100 K.M28 | 83072.66 | 64052.67 | 8722.63 | 72775.3
Kuwait | Supply/J009 |  | Kuwait | 41451.49 | 26943.47 | 0 | 26943.47
Canal Sugar OHTL | Inv.01 Sugar OHTL | 1 | Canal Sugar OHTL1 | 12530046 | 9898736.34 | 1879506.9 | 11778243.24
Canal Sugar S/s | Inv 2 Sugar S/s | 2 | Canal Sugar S/s2 | 5832260.77 | 4607486 | 874839.12 | 5482325.12
Akhmem Assiut | Re.Inst6-7-11-29asui | 7 | Akhmem Assiut7 | 1240250.27 | 1239644.37 | 0 | 1239644.37
Elco Steel 220/33 KV SS | 1904210008 |  | Elco Steel 220/33 KV SS | 1901928.56 | 3994049.98 | 0 | 1997024.99
Elco Steel 220/33 KV SS | 1903210006 |  | Elco Steel 220/33 KV SS | 1678021.52 | 1761922.6 | 0 | 1761922.6
SHAT Al ARAB 400/132kV SS | 237 |  | SHAT Al ARAB 400/132kV SS | 166594.11 | 166594.11 | 0 | 166594.11
Cameron EDC | 017/2019 |  | Cameron EDC | 43120.36 | 43034.16 | 0 | 43034.16
NUCA R05 - Z02 | R05-ZONE02-IPC03 | 3 | NUCA R05 - Z023 | 22465025.75 | 23506061.7675 | 2882241.83 | 26388303.5975
C5 Bridge 2 New Alamein | IPC#4 | 4 | C5 Bridge 2 New Alamein4 | 1105500 | 1072335 | 0 | 1072335
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 6USD | 6 | Benban 500 K.V / 100 K.M6 | 2628048.26 | 2207049.53 | 275945.07 | 2482994.6
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 2USD | 2 | Benban 500 K.V / 100 K.M2 | 137265.81 | 115303.28 | 14412.91 | 129716.19
Benban 500 K.V/95 K.M | Benban Lot2 Inv 2 $ | 2 | Benban 500 K.V/95 K.M2 | 345253.77 | 289914.16 | 36251.65 | 326165.81
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC17 | 17 | EMAAR- Pkg 140-ITP-Mivida17 | 16610857.34 | 11726998.4315 | 1462374.69 | 13189373.1215
Ismailiya East Substation | ISE-CW-EURO-02 | 2 | Ismailiya East Substation2 | 2402322.37 | 1788929.4 | 60858.46 | 1849787.86
Royal City | Center Zone final 24 |  | Royal City | 3252689.52 | 0 | 155227.22 | 155227.22
Royal City | ROYAL CITY2-IPC15 | 15 | Royal City15 | 3135467.3 | 2272705.3583 | 465023.7367 | 2737729.095
New bridge Ismailiya Nefisha | NFISHA BRIDGE-FINAL |  | New bridge Ismailiya Nefisha | 19116412.92 | 11694567.55 | 9103989.25 | 20798556.8
Canal Sugar S/s | Inv 1 + $ Sugar S/s | 1 | Canal Sugar S/s1 | 1000000 | 800000 | 150000 | 950000
Canal Sugar S/s | Inv 1 $ Sugar S/s | 1 | Canal Sugar S/s1 | 2522829.2 | 1983035.07 | 378424.38 | 2361459.45
Elco Steel 220/33 KV SS | 1906210001 |  | Elco Steel 220/33 KV SS | 1474212.24 | 3095845.7 | 0 | 1547922.85
Assuit PP (CP-118) | 1906210015 |  | Assuit PP (CP-118) | 126316.7 | 112737.66 | 19894.88 | 132632.54
SHATRA 400/132kV SS | 244 |  | SHATRA 400/132kV SS | 679747.06 | 679747.06 | 0 | 679747.06
Badr | Inv. 14 Badr | 14 | Badr14 | 4102122.6 | 3045406.1 | 615318.39 | 3660724.49
SHAT Al ARAB 400/132kV SS | 251 |  | SHAT Al ARAB 400/132kV SS | 45835.53 | 45835.53 | 0 | 45835.53
SHATRA 400/132kV SS | 252 |  | SHATRA 400/132kV SS | 638589.44 | 638589.44 | 0 | 638589.44
MOTHANA 400/132kV SS | 259 |  | MOTHANA 400/132kV SS | 1994813.66 | 1994813.66 | 0 | 1994813.66
New Capital Tunnels | M.Z TUNNLE-FINAL |  | New Capital Tunnels | 16934976.78 | 24267384 | 8100000 | 32367384
Latin Compound - New Alamin | inv ( 15 ) 1-12-2020 | 15 | Latin Compound - New Alamin15 | 684160.4 | 472070.68 | 136832.08 | 608902.76
AWEER POWER STATION 'H' Phase | 10188 |  | AWEER POWER STATION 'H' Phase | 33075247.752 | 29032717.47 | 3675027.528 | 32707744.998
AWEER POWER STATION 'H' Phase | 10133 |  | AWEER POWER STATION 'H' Phase | 241518.4 | 253594.32 | 0 | 253594.32
AWEER POWER STATION 'H' Phase | 10134 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
AWEER POWER STATION 'H' Phase | 10128 |  | AWEER POWER STATION 'H' Phase | 734401.79 | 644641.5695 | 81600.2 | 726241.7695
LAYYAH CCPP | 511 |  | LAYYAH CCPP | 4935294 | 4194999.9 | 740294.1 | 4935294
LAYYAH CCPP | 491 |  | LAYYAH CCPP | 2467647 | 2097499.95 | 370147.05 | 2467647
LAYYAH CCPP | OF/MP-04 | 4 | LAYYAH CCPP4 | 1233824 | 0 | 1233809.78 | 1233809.78
DoubleTree Mangroovy ElGouna | MANGROVY-IPC11 | 11 | DoubleTree Mangroovy ElGouna11 | 2596008.28 | 1750027.305 | 681452.17 | 2431479.475
DoubleTree Mangroovy ElGouna | mangrove-IPC04 | 4 | DoubleTree Mangroovy ElGouna4 | 3743616.44 | 2572404.492 | 982699.32 | 3555103.812
Marsa Matrouh 500KV | Inv.33 Borg Alarab | 33 | Marsa Matrouh 500KV33 | 176638.1 | 154293.13 | 18547 | 172840.13
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC11 | 11 | EMAAR-PKG# 101-UPTOWN11 | 3104755.66 | 1976416.883 | 888764.73 | 2865181.613
AWEER POWER STATION 'H' Phase | 10106 |  | AWEER POWER STATION 'H' Phase | 2395684.97 | 2102879.03 | 266187.22 | 2369066.25
SHAT Al ARAB 400/132kV SS | 257 |  | SHAT Al ARAB 400/132kV SS | 205273 | 205273 | 0 | 205273
SHATRA 400/132kV SS | 268 |  | SHATRA 400/132kV SS | 85752.96 | 85752.96 | 0 | 85752.96
Beni Suef Add-on Sales | 1908210013 |  | Beni Suef Add-on Sales | 804160 | 892617.6 | 0 | 892617.6
EDNC Retail & Offices Civil | SOREAL - IPC06 | 6 | EDNC Retail & Offices Civil6 | 38734277.15 | 28614412.9875 | 8134198.2 | 36748611.1875
Port Said | Inv 8 Portsaid.final | 8 | Port Said8 | 2319220.01 | 2090205.9 | 0 | 2090205.9
EMAAR-PKG#53-UPTOWN | PO-PKG#53-IPC03 | 3 | EMAAR-PKG#53-UPTOWN3 | 335238.1 | 293735.625 | 0 | 293735.625
Alamein | ALALAMEN ROAD-IPC02 | 2 | Alamein2 | 7800501.9 | 8545086 | 0 | 8545086
HyperOne Zayed Extension | hyper one- IPC09 | 9 | HyperOne Zayed Extension9 | 2100740 | 9493853 | 525232.57 | 10019085.57
HyperOne Zayed Extension | Hyperone-IPC05 | 5 | HyperOne Zayed Extension5 | 5616447.62 | 3307335 | 1404111.9 | 5989384.521
IKEA Extension MoA | IKEA-IPC01 | 1 | IKEA Extension MoA1 | 2651353 | 4032556.16 | 480066.21 | 4512622.37
Manshiet Nasser Substation | 1907210018 |  | Manshiet Nasser Substation | 14087.45 | 11974.33 | 2113.12 | 14087.45
Benban 500 K.V/95 K.M | Benban Lot2 Inv 11 $ | 11 | Benban 500 K.V/95 K.M11 | 691626.99 | 580966.67 | 72620.83 | 653587.5
Benban 500 K.V/95 K.M | Benban Lot2 Inv 7 $ | 7 | Benban 500 K.V/95 K.M7 | 2980768.71 | 2503845.71 | 312980.72 | 2816826.43
4 SS - Technical Service | 284 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
MAYSAN 400/132kV SS | 278 |  | MAYSAN 400/132kV SS | 366953.06 | 366953.06 | 0 | 366953.06
LAYYAH CCPP | 494 |  | LAYYAH CCPP | 6538440 | 5387963.1 | 1429318 | 6817281.1
Ghana Street lighting | inv 5 Ghana | 5 | Ghana Street lighting5 | 58117.7 | 58117.7 | 0 | 58117.7
AWEER POWER STATION 'H' Phase | 10189 |  | AWEER POWER STATION 'H' Phase | 271708.2 | 285293.61 | 0 | 285293.61
EMAAR- Pkg 140-ITP-Mivida | pkg#140 - ipc 05 | 5 | EMAAR- Pkg 140-ITP-Mivida5 | 1994559.84 | 1337507.07 | 508557.79 | 1846064.86
Suez Gulf Substation | 18 EGP Shipping Main |  | Suez Gulf Substation | 110445.58 | 104567.4 | 11618.6 | 116186
Suez Gulf Substation | 13 EGP - Suez Gulf |  | Suez Gulf Substation | 1150418 | 1087145.01 | 120793.89 | 1207938.9
NUCA R05 - Z02 | R5 ZONE2-IPC09 | 9 | NUCA R05 - Z029 | 22914593.8 | 21320239.56 | 2629597.49 | 23949837.05
Alamein | ALAMEEN SUPPLY-IPC02 | 2 | Alamein2 | 8700060 | 8403859 | 0 | 8403859
AWEER POWER STATION 'H' Phase | 10248 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
SHATRA 400/132kV SS | 283 |  | SHATRA 400/132kV SS | 862182.06 | 862182.06 | 0 | 862182.06
MAYSAN 400/132kV SS | 287 |  | MAYSAN 400/132kV SS | 682124.94 | 682124.94 | 0 | 682124.94
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 13 | 13 | Benban 500 K.V / 100 K.M13 | 89987.1 | 69382.92 | 9448.65 | 78831.57
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 22 | 22 | Benban 500 K.V/95 K.M22 | 4266234.77 | 3289272.12 | 447954.65 | 3737226.77
Suez Gulf Substation | 484 |  | Suez Gulf Substation | 46341.4 | 43875 | 4875 | 48750
Suez Gulf Substation | 483 |  | Suez Gulf Substation | 2782.01 | 2633.94 | 292.66 | 2926.6
Elco Steel 220/33 KV SS | 529 |  | Elco Steel 220/33 KV SS | 86762.1 | 91100.2 | 0 | 91100.2
AWEER POWER STATION 'H' Phase | 10329 |  | AWEER POWER STATION 'H' Phase | 535245.65 | 469826.73 | 59471.74 | 529298.47
EMAAR-PKG117- MARASSI | PKG#117-IPC13 | 13 | EMAAR-PKG117- MARASSI13 | 2573072.88 | 3439963.734 | 0 | 3439963.734
Manshiet Nasser Substation | 1902210005 |  | Manshiet Nasser Substation | 1427239.89 | 1326976.29 | 157353.2 | 1484329.49
Elco Steel 220/33 KV SS | 1908210007 |  | Elco Steel 220/33 KV SS | 836902.86 | 878748 | 0 | 878748
Elco Steel 220/33 KV SS | 1904210001 |  | Elco Steel 220/33 KV SS | 392207.96 | 411818.36 | 0 | 411818.36
Elco Steel 220/33 KV SS | 1901210001 |  | Elco Steel 220/33 KV SS | 2636244 | 2636244 | 0 | 2636244
4 SS - Technical Service | 300 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Akhmem - Qena | Inv.24 Qena- Akhmem$ | 24 | Akhmem - Qena24 | 2443255.76 | 1958679.7522 | 0 | 1958679.7522
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 25 | 25 | Benban 500 K.V/95 K.M25 | 14651164.3 | 11295460.8 | 1538372.25 | 12833833.05
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 24 | 24 | Benban 500 K.V / 100 K.M24 | 838750.91 | 646677.7 | 88068.85 | 734746.55
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .17 | 17 | Benban 3/ Toshka 2 LOT 417 | 2453842.55 | 1673125.41 | 257653.47 | 1930778.88
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .7 | 7 | Benban 3/ Toshka 2 LOT 47 | 7683788.62 | 5924202.11 | 806797.81 | 6730999.92
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .2 | 2 | Benban 3/ Toshka 2 LOT 42 | 4605753.15 | 3551036.46 | 483604.08 | 4034640.54
CFC Podium 2 | CFC- IPC04 | 4 | CFC Podium 24 | 35226223.59 | 32660832.57 | 6209770.32 | 38870602.89
Manshiet Nasser Substation | 534 |  | Manshiet Nasser Substation | 304492.05 | 65489.96 | 45673.81 | 111163.77
EMAAR-PKG# 144, Marassi | 20100003 |  | EMAAR-PKG# 144, Marassi | 11410387.23 | 16262789.43 | 0 | 16262789.43
Royal City | ROYAL CENTER-IPC03 | 3 | Royal City3 | 2055285.71 | 2422662.0255 | 171523.97 | 2594185.9955
Ismailiya East Substation | ISE-SW-EGP-07 | 7 | Ismailiya East Substation7 | 564375 | 417637.5 | 84656.25 | 502293.75
Ismailiya East Substation | ISE-SW-EGP-06 | 6 | Ismailiya East Substation6 | 813750 | 602175 | 122062.5 | 724237.5
Manshiet Nasser Substation | 500 |  | Manshiet Nasser Substation | 322603.53 | 322603.53 | 0 | 322603.53
Manshiet Nasser Substation | 489 |  | Manshiet Nasser Substation | 1513677.92 | 1609404.58 | 0 | 1609404.58
Marsa Matrouh 500KV | Inv.49 Borg Alarab | 49 | Marsa Matrouh 500KV49 | 5808093.56 | 5073373.57 | 609849.82 | 5683223.39
AWEER POWER STATION 'H' Phase | 10430 |  | AWEER POWER STATION 'H' Phase | 959258.69 | 842015.9549 | 106584.299 | 948600.2539
LAYYAH CCPP | MP-07 | 7 | LAYYAH CCPP7 | 10283760 | 0 | 10283760 | 10283760
Oasis Buildings- New Capital | Inv(1)131219 | 1 | Oasis Buildings- New Capital1 | 476918.4 | 455241.42 | 0 | 455241.42
El Katameya Mall | inv(2)251119 | 2 | El Katameya Mall2 | 848332.8 | 674811.8 | 0 | 674811.8
Toshka GIS 500 kV | Toshka Sub Inv. 23 $ | 23 | Toshka GIS 500 kV23 | 179449.52 | 102912.1 | 47105.5 | 150017.6
Toshka GIS 500 kV | Toshka Sub Inv. 02 $ | 2 | Toshka GIS 500 kV2 | 133433.33 | 90488 | 35026.25 | 125514.25
kayan wall lock & Load | KAYAN RADM1-FINAL |  | kayan wall lock & Load | 1080000 | 792797 | 721500 | 1514297
Akhmem - Qena | Social Inv.24$Qen 2 | 24 | Akhmem - Qena24 | 1059445 | 1059445 | 0 | 1059445
Akhmem Assiut | Inv.25Assuit Akhmem$ | 25 | Akhmem Assiut25 | 68058.91 | 54002.8082 | 0 | 54002.8082
Manshiet Nasser Substation | 508 |  | Manshiet Nasser Substation | 92079.11 | 22875.65 | 13811.87 | 36687.52
NUCA R05 - Z02 | R5-IPC012 | 12 | NUCA R05 - Z0212 | 26622562.5 | 22980846.275 | 2848719.75 | 25829566.025
Marsa Matrouh 500KV | Inv.22 Borg Alarab | 22 | Marsa Matrouh 500KV22 | 4695452.67 | 4101484.97 | 493022.53 | 4594507.5
Marsa Matrouh 500KV | Inv.14 Borg Alarab | 14 | Marsa Matrouh 500KV14 | 14312845.4 | 12434102.74 | 1502848.77 | 13936951.51
Marsa Matrouh 500KV | Inv.12 Borg Alarab | 12 | Marsa Matrouh 500KV12 | 3453119.23 | 3016303.71 | 362577.52 | 3378881.23
Manshiet Nasser Substation | 532 |  | Manshiet Nasser Substation | 1415891.22 | 1291874.42 | 0 | 1291874.42
Marsa Matrouh 500KV | Inv.61 Borg Alarab | 61 | Marsa Matrouh 500KV61 | 16797557.46 | 14672665.43 | 1763743.53 | 16436408.96
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $2 | 2 | Benban 3/ Toshka 2 LOT 42 | 579518.63 | 486795.64 | 60849.46 | 547645.1
SHATRA 400/132kV SS | 329 |  | SHATRA 400/132kV SS | 789960.33 | 789960.33 | 0 | 789960.33
SHAT Al ARAB 400/132kV SS | 323 |  | SHAT Al ARAB 400/132kV SS | 129313.49 | 129313.49 | 0 | 129313.49
MAYSAN 400/132kV SS | 340 |  | MAYSAN 400/132kV SS | 130535.22 | 130535.22 | 0 | 130535.22
MOTHANA 400/132kV SS | 335 |  | MOTHANA 400/132kV SS | 9.6 | 9.6 | 0 | 9.6
Marsa Matrouh 500KV | Inv.70 Borg Alarab | 70 | Marsa Matrouh 500KV70 | 8198409.53 | 6632044.06 | 0 | 6632044.06
El Katameya Mall | inv(5)250220 | 5 | El Katameya Mall5 | 501354 | 376578.78 | 0 | 376578.78
Alamein | ELALAMEN ROAD-IPC3F | 3 | Alamein3 | 6519021.9 | 6296976 | 0 | 6296976
P-28-16 Balat Owinat Lot 3 | Inv. 14 Balat lot 3 | 14 | P-28-16 Balat Owinat Lot 314 | 16668938.86 | 10784409.09 | 1750238.58 | 12534647.67
Manshiet Nasser Substation | 2003210010 |  | Manshiet Nasser Substation | 1730649.42 | 1730646.22 | 0 | 1730646.22
LAYAN Substation | 10362 |  | LAYAN Substation | 616180.18 | 2082689.04 | 0 | 520672.26
AWEER POWER STATION 'H' Phase | ENG/026 Rev0 |  | AWEER POWER STATION 'H' Phase | 8359233.58 | 8777195.259 | 0 | 8777195.259
MAYSAN 400/132kV SS | 346 |  | MAYSAN 400/132kV SS | 7628130.2 | 7628130.2 | 0 | 7628130.2
New Babil 400/132KV Substation | 2008210005 |  | New Babil 400/132KV Substation | 5200000 | 0 | 5200000 | 5200000
Al-Shabab PP Phase II (CP-117) | 2002210021 |  | Al-Shabab PP Phase II (CP-117) | 18181.2 | 19126.16 | 0.01 | 19126.17
W Dam PP Phase II (CP-117) | 526 |  | W Dam PP Phase II (CP-117) | 15041.7 | 2050.71 | 0 | 2050.71
East Owainat 5 LOTS | East Owainat Inv. 02 | 2 | East Owainat 5 LOTS2 | 106378543.3 | 43557012.68 | 55848735.2 | 99405747.88
Royal City | ROYAL CITY-IPC30 | 30 | Royal City30 | 16056421.67 | 9421690.2835 | 4051126.93 | 13472817.2135
EL-Hegaz Square Bridge | ELHEGAZ BRIDGE-IPC01 | 1 | EL-Hegaz Square Bridge1 | 113016687 | 0 | 56206942.64 | 94350192.64
EDNC Retail & Offices Civil | SOREAL-IPC15 | 15 | EDNC Retail & Offices Civil15 | 19101976.12 | 12895954 | 2540503.47 | 15436457.47
Safir bridge | Claim-01 | 1 | Safir bridge1 | 204725 | 0 | 0 | 204725
marassi inland marina | IPC#1 | 1 | marassi inland marina1 | 2662846.12 | 665711.53 | 0 | 2216391.95
Elco Steel 220/33 KV SS | 2007210007 |  | Elco Steel 220/33 KV SS | 6135.73 | 6442.52 | 0 | 6442.52
Elco Steel 220/33 KV SS | 2007210008 |  | Elco Steel 220/33 KV SS | 196544.45 | 206371.67 | 0 | 206371.67
Nagaa Hamady/Assuit OHTL | Nagaa Hamady Inv.5 | 5 | Nagaa Hamady/Assuit OHTL5 | 7739586.67 | 4055546.71 | 812656.6 | 4868203.31
MOTHANA 400/132kV SS | 355 |  | MOTHANA 400/132kV SS | 2129638.81 | 2129638.81 | 0 | 2129638.81
AWEER POWER STATION 'H' Phase | Con-013 Rev0 | 13 | AWEER POWER STATION 'H' Phase13 | 5110794.6 | 5053945.49 | 0 | 5053945.49
Manshiet Nasser Substation | 2004210011 |  | Manshiet Nasser Substation | 402473.13 | 302441.35 | 64777.61 | 367218.96
Alamein | ELALAMEEN SUPPLAY-03 | 3 | Alamein3 | 5466463 | 5280204 | 0 | 5280204
Marsa Matrouh 500KV | Inv.54 Borg Alarab | 54 | Marsa Matrouh 500KV54 | 26482057.8 | 18695111.68 | 2780616.07 | 21475727.75
NUCA R05 - Z02 | R5 FINSHING-IPC03 | 3 | NUCA R05 - Z023 | 1781134.95 | 1602620.05 | 0 | 1602620.05
ESU Ph2-Enabling & Struc | ESU2-ARCH&MEP-IPC06 | 6 | ESU Ph2-Enabling & Struc6 | 28648432.29 | 8883253.7545 | 9024256.2 | 17907509.9545
marassi inland marina | IPC#3 | 3 | marassi inland marina3 | 663963.54 | 572187.32 | 0 | 572714.25
HyperOne Zayed Extension | HYPER ONE-IPC13 | 13 | HyperOne Zayed Extension13 | 9161231 | 6738702 | 2290307 | 9029009
Racecores 3092-16 132KV C | 11639 |  | Racecores 3092-16 132KV C | 260727.385 | 440629.2685 | 0 | 220314.6343
Royal City | ROYAL ZONE-IPC11 | 11 | Royal City11 | 5193730.04 | 4947910.452 | 1333292.73 | 6281203.182
NUCA R05 - Z02 | R05(2) ipc 39 | 39 | NUCA R05 - Z0239 | 3376069.65 | 3267429.02 | 407101.7 | 3674530.72
NUCA R05 - Z02 | R5(2) ipc25 | 25 | NUCA R05 - Z0225 | 11651556.19 | 10910719.5895 | 1356479.4 | 12267198.9895
NUCA R05 - Z02 | R05(2) ipc24 | 24 | NUCA R05 - Z0224 | 29648308.83 | 25146494.8315 | 3148906.7 | 28295401.5315
NUCA R05 - Z02 | R5(2) ipc(22) | 22 | NUCA R05 - Z0222 | 25000432.9 | 22004708.9 | 2801059.7 | 24805768.6
NUCA R05 - Z02 | R05(2) ipc21 | 21 | NUCA R05 - Z0221 | 26517040.75 | 28326949.3975 | 3491447.6 | 31818396.9975
Ismailiya East Substation | ISE-CW-EGP-26 | 26 | Ismailiya East Substation26 | 315559 | 201880.61 | 0 | 201880.61
Ismailiya East Substation | ISE-CW-EGP-24 | 24 | Ismailiya East Substation24 | 210887 | 187689.43 | 0 | 187689.43
EMAAR-Pkg#162/163- Marassi | PKG#162-IPC08 | 8 | EMAAR-Pkg#162/163- Marassi8 | 12161063.39 | 9432027.7295 | 1207085.04 | 10639112.7695
MOTHANA 400/132kV SS | 369 |  | MOTHANA 400/132kV SS | 826943.05 | 826943.05 | 0 | 826943.05
Toshka Farm | Toshka Farm Inv. 01 | 1 | Toshka Farm1 | 65868984.38 | 27994050.29 | 34581216.8 | 62575267.09
Assuit PP (CP-118) | 2008210001 |  | Assuit PP (CP-118) | 320723.44 | 286245.67 | 50513.94 | 336759.61
marassi inland marina | IPC#6 | 6 | marassi inland marina6 | 1553205.04 | 1333389.29 | 0 | 1411049.54
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .11 | 11 | Benban 3/ Toshka 2 LOT 411 | 1071195.52 | 868744.32 | 112475.53 | 981219.85
Ministries Buildings | MIN-CORE-IPC05 | 5 | Ministries Buildings5 | 21144751.9 | 13360535 | 4453514.44 | 17814049.44
Ministries Buildings | MIN.LAND SCAPE-IPC02 | 2 | Ministries Buildings2 | 4132505.23 | 2590775 | 946244.5 | 3537019.5
Closed | final new giza1 |  | Closed | 6274164 | 4874780.03 | 0 | 4874780.03
Cairo-Alex Railway | Cairo-alex ipc 33 | 33 | Cairo-Alex Railway33 | 7420969.19 | 5153463.7795 | 779201.77 | 5932665.5495
Cairo-Alex Railway | cairo-alex ipc23 | 23 | Cairo-Alex Railway23 | 4053596.4 | 2796823.77 | 425627.62 | 3222451.39
Racecores 3092-17 132KV E | 11502 |  | Racecores 3092-17 132KV E | 328893.9222 | 818945.88 | 0 | 272981.96
Racecores 3092-17 132KV E | 11223 |  | Racecores 3092-17 132KV E | 962159.8537 | 4878150.48 | 0 | 813025.08
Racecores 3092-17 132KV E | 11222 |  | Racecores 3092-17 132KV E | 337466.7771 | 570318.86 | 0 | 285159.43
Racecores 3092-17 132KV E | 11291 |  | Racecores 3092-17 132KV E | 4974582.55 | 33031228.08 | 0 | 4128903.51
Racecores 3092-17 132KV E | 10605 |  | Racecores 3092-17 132KV E | 530278.198 | 1792340.32 | 0 | 448085.08
MOTHANA 400/132kV SS | 373 |  | MOTHANA 400/132kV SS | 4383461.53 | 4383461.53 | 0 | 4383461.53
MAYSAN 400/132kV SS | 364 |  | MAYSAN 400/132kV SS | 1748788.82 | 1748788.82 | 0 | 1748788.82
RING ROAD MARYOTIA EXPANSION | RINING ROAD-IPC02 | 2 | RING ROAD MARYOTIA EXPANSION2 | 7808006.9 | 7164556.359 | 0 | 7164556.359
Miscellaneous Projects | 2010210008 |  | Miscellaneous Projects | 2705.17 | 5410.34 | 0 | 2705.17
Beni Suef Add-on Sales | 2010210006 |  | Beni Suef Add-on Sales | -1049.8 | -1049.8 | 0 | -1049.8
El Katameya Mall | inv ( 16)30-12-2020 | 16 | El Katameya Mall16 | 182000 | 100309 | 0 | 100309
Taval Sarai 52 | IPC_1_Gama_Saraya | 1 | Taval Sarai 521 | 198511.2 | 140320.0476 | 0 | 140320.0476
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 34 | 34 | ORA ZED - Ph 01B - Pkgs A&D34 | 12357935.4 | 10018963.4932 | 1297583.22 | 11316546.7132
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc 30 | 30 | ORA ZED - Ph 01B - Pkgs A&D30 | 24199949.01 | 11085957.6804 | 11540994.65 | 22626952.3304
ORA ZED - Ph 01B - Pkgs A&D | ora ph.1 - ipc 23 | 23 | ORA ZED - Ph 01B - Pkgs A&D23 | 24141553.78 | 21483271.639 | 2514002.85 | 23997274.489
Angola Emergency fast-track | ANG-Mor-Inv 4 - Ints | 4 | Angola Emergency fast-track4 | 4452515.49 | 2964043.81 | 0 | 2964043.81
Miscellaneous Projects | 2009210017 |  | Miscellaneous Projects | 28907.82 | 32954.91 | 0 | 32954.91
South Helwan PP (CP-117) | 2010210002 |  | South Helwan PP (CP-117) | 136989.63 | 142685.66 | 0 | 142685.66
10th of Ramadan Railway | IPC#2 | 2 | 10th of Ramadan Railway2 | 1911600 | 1811241 | 0 | 1811241
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $8 | 8 | Benban 3/ Toshka 2 LOT 48 | 79234.23 | 65619.61 | 8319.59 | 73939.2
Cairo Capital Cables Tunnel | Tunnel Inv. 6 | 6 | Cairo Capital Cables Tunnel6 | 27606172.95 | 18302892.55 | 6901543.25 | 25204435.8
RING ROAD MARYOTIA EXPANSION | MARIYTIA-R.R-IPC01 | 1 | RING ROAD MARYOTIA EXPANSION1 | 28687693.75 | 15791446.32 | 10000000 | 25791446.32
Cairo Capital Cables Tunnel | Tunnel Inv. 7 | 7 | Cairo Capital Cables Tunnel7 | 33277514.85 | 22062992.25 | 8319378.71 | 30382370.96
EMAAR-PKG117- MARASSI | 19100004 |  | EMAAR-PKG117- MARASSI | 4505534.5 | 3905373.095 | 430595.5 | 4335968.595
ElSewedy HQ Internal Finishing | EL SEWEDY HQ IPC16 | 16 | ElSewedy HQ Internal Finishing16 | 8911604.29 | 0.0045 | 5994299.1 | 7058911.3845
ElSewedy HQ Internal Finishing | ELSEWEDY IPC 11 | 11 | ElSewedy HQ Internal Finishing11 | 21606397.82 | 17417402.071 | 4830762.9 | 22248164.971
Marsa Matrouh 500KV | Inv.75 Borg Alarab | 75 | Marsa Matrouh 500KV75 | 4985146.67 | 4855331.33 | 0 | 4855331.33
Marsa Matrouh 500KV | Inv.76 Borg Alarab | 76 | Marsa Matrouh 500KV76 | 519370.87 | 483451.93 | 0 | 483451.93
P-28-16 Balat Owinat Lot 3 | Inv. 15 Balat lot 3 | 15 | P-28-16 Balat Owinat Lot 315 | 4089500.19 | 2809088.34 | 429397.52 | 3238485.86
Beni Seuf - 358 | Inv. 9 Oewon Mousa | 9 | Beni Seuf - 3589 | 42062234.7 | 29057490.98 | 7116030.86 | 36173521.84
Canal Sugar 33KV OHTL | Inv. 3 Sugar 33 OHTL | 3 | Canal Sugar 33KV OHTL3 | 23399301.19 | 18485447.83 | 3509895.18 | 21995343.01
Kattameya Creeks | Katamya chreek ipc39 | 39 | Kattameya Creeks39 | 66379928.69 | 66261026 | 2575496.63 | 68836522.63
Kattameya Creeks | KATAMEYA GREEKS-IPC6 | 6 | Kattameya Creeks6 | 32255415.11 | 29363826.7655 | 4181804.95 | 33545631.7155
Marsa Matrouh 500KV | Inv.25Usd borg alarb | 25 | Marsa Matrouh 500KV25 | 15090.57 | 14101.14 | 0 | 14101.14
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .15 | 15 | Benban 3/ Toshka 2 LOT 415 | 6329953.5 | 4981279.18 | 664645.12 | 5645924.3
Beni Suef Substation R61 | BSF-CW-EURO-9FINAL | 9 | Beni Suef Substation R619 | 16399.71 | 2415310.91 | 0 | 2415310.91
IKEA Extension MoA | IKEA2-IPC02 | 2 | IKEA Extension MoA2 | 1613181.4 | 1513146.56 | 0 | 1513146.56
Royal City | ROYAL ZONE-IPC14 | 14 | Royal City14 | 2137250.76 | 1288827.4664 | 349386.65 | 1638214.1164
LRT Project | IPC_1_LRT | 1 | LRT Project1 | 103200 | 87358.8 | 0 | 87358.8
10th of Ramadan Railway | IPC#1 | 1 | 10th of Ramadan Railway1 | 1574154 | 1491510.92 | 0 | 1491510.92
Fish Market | SOUQ ELSAMAK-IPC02 | 2 | Fish Market2 | 9650509.57 | 0.9985 | 0 | 0.9985
SHATRA 400/132kV SS | 392 |  | SHATRA 400/132kV SS | 1821535.32 | 1821535.32 | 0 | 1821535.32
Canal Sugar 33KV OHTL | Ref Ret Sugar 33OHTL |  | Canal Sugar 33KV OHTL | 5666669.06 | 5666669.06 | 0 | 5666669.06
VM Horizon Cloud LP-07-20 | 7 |  | VM Horizon Cloud LP-07-20 | 95497.83 | 108867.53 | 0 | 108867.53
Mid Town - Condo | IPC-Condo |  | Mid Town - Condo | 40000 | 40000 | 0 | 40000
Miscellaneous Projects | 2012210004 |  | Miscellaneous Projects | 237172.84 | 263261.85 | 0 | 263261.85
West Port Said 220 kV GIS | P-45-Portsaid Inv.05 | 5 | West Port Said 220 kV GIS5 | 5477475.88 | 0 | 575134.97 | 575134.97
New Babil 400/132KV Substation | 2103210002 |  | New Babil 400/132KV Substation | 9397.92 | 9397.92 | 0 | 9397.92
RING ROAD MARYOTIA EXPANSION | RING MARYOTUA-IPC03 | 3 | RING ROAD MARYOTIA EXPANSION3 | 12200900 | 11340731.41 | 0 | 11340731.41
EDNC Retail & Offices Civil | SOREAL-IPC22 | 22 | EDNC Retail & Offices Civil22 | 29539476.98 | 19964135.699 | 2567491.44 | 22531627.139
GOV2 - Infra | GOV2-IPC 1MOS+2 | 1 | GOV2 - Infra1 | 4159678.82 | 8793510.21 | 0 | 8793510.21
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC09 | 9 | EMAAR-Pkg#162/163- Marassi9 | 5020188.63 | 4602212.1515 | 1334744.6 | 5936956.7515
LAYAN Substation | 10464 |  | LAYAN Substation | 201990.6 | 341364.12 | 0 | 170682.06
Koning Food V2 - LP-08-20 | 10 |  | Koning Food V2 - LP-08-20 | 528.59 | 602.6 | 0 | 602.6
Akhmem - Qena | Inv.51 Qena Akhmem | 51 | Akhmem - Qena51 | 4985924.64 | 3958824.16 | 0 | 3958824.16
Cairo Capital Cables Tunnel | Tunnel Inv. 9 | 9 | Cairo Capital Cables Tunnel9 | 44464806.1 | 29480166.25 | 11116201.53 | 40596367.78
Zone(J) South Valley Toshka | South Valley Inv. 06 | 6 | Zone(J) South Valley Toshka6 | 40847011.3 | 31125008.3 | 5228417.45 | 36353425.75
SHAT Al ARAB 400/132kV SS | 401 |  | SHAT Al ARAB 400/132kV SS | 635924.84 | 635924.84 | 0 | 635924.84
SHATRA 400/132kV SS | 400 |  | SHATRA 400/132kV SS | 1067997.84 | 1067997.84 | 0 | 1067997.84
Ismailiya East Substation | ISE-SW-EGP-08 | 8 | Ismailiya East Substation8 | 467875 | 416408.75 | 0 | 416408.75
Akhmem - Qena | Inv.50 Qena Akhmem | 50 | Akhmem - Qena50 | 1793358.01 | 1506420.9 | 0 | 1506420.9
SHAT Al ARAB 400/132kV SS | 404 |  | SHAT Al ARAB 400/132kV SS | 1432167.03 | 1432167.03 | 0 | 1432167.03
DoubleTree Mangroovy ElGouna | MANROVE-IPC14 | 14 | DoubleTree Mangroovy ElGouna14 | 4271693.53 | 3058799.81 | 1027682.3 | 4086482.11
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC 25 | 25 | EMAAR-Pkg#162/163- Marassi25 | 3618126.7 | 4308209.73 | 80309.95 | 4388519.68
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC019 | 19 | EMAAR-Pkg#162/163- Marassi19 | 0.0001 | 6528975.8501 | 771115.07 | 7300090.9201
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC09 | 9 | EMAAR-Pkg#162/163- Marassi9 | 0.001 | 3307337.871 | 177567.83 | 3484905.701
NUCA R05 - Z02 | R5 FINSHING-IPC11 | 11 | NUCA R05 - Z0211 | 19871625.75 | 15747861.85 | 1987162.6 | 17735024.45
Mauritania Lot 1 | Inv.19 - Lot 1 | 19 | Mauritania Lot 119 | 232841.21 | 58214.53 | 0 | 58214.53
Mauritania-Lot 2 | Inv.17 - Lot 2 | 17 | Mauritania-Lot 217 | 644058.64 | 212578.18 | 0 | 212578.18
Mauritania-Lot 2 | Inv.14 – Lot 2 | 14 | Mauritania-Lot 214 | 627289.8 | 595869.06 | 0 | 595869.06
Mauritania-Lot 2 | Inv. 11 – Lot 2 | 11 | Mauritania-Lot 211 | 1364266.56 | 1296053.23 | 0 | 1296053.23
EGAT Pelletizing Plant | elco egat ipc10 | 10 | EGAT Pelletizing Plant10 | 17027897.29 | 16034098.6 | 1674914.5845 | 17709013.1845
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC020 | 20 | EMAAR-PKG# 101-UPTOWN20 | 1322361.65 | 648976.9025 | 316404.16 | 965381.0625
VM Horizon Cloud LP-07-20 | 19 |  | VM Horizon Cloud LP-07-20 | 14150 | 16131 | 0 | 16131
Miscellaneous Projects | 2105210016 |  | Miscellaneous Projects | 114299.76 | 130301.7264 | 0 | 130301.7264
Capital One | INV( 1 ) 21-6-2021 | 1 | Capital One1 | 526448.5 | 521184.025 | 0 | 521184.025
NUCA R05 - Z02 | R05 Finishng - IPC12 | 12 | NUCA R05 - Z0212 | 18550221 | 14700646.05 | 1855022.1 | 16555668.15
Diplomatic District - Infra | Diplo Dist IPC04 | 4 | Diplomatic District - Infra4 | 2419418.571 | 10569264.03 | 1258854.31 | 11828118.34
Air Force Project | Air Force Inv . 04 | 4 | Air Force Project4 | 11951632.64 | 8556972 | 2987908.16 | 11544880.16
Faculty of Medicine | mansoura ipc 09 | 9 | Faculty of Medicine9 | 18326568.57 | 15506621.9085 | 916328.43 | 16422950.3385
NUCA R05 - Z02 | R5 - IPC22 | 22 | NUCA R05 - Z0222 | 29282126.25 | 24705356.85 | 3101185.15 | 27806542
Kafr Shokr Bridge | Kafr Shokr IPC03 | 3 | Kafr Shokr Bridge3 | 9630317.86 | 8372664.936 | 0 | 8372664.936
Zone(J) South Valley Toshka | South Valley Inv. 04 | 4 | Zone(J) South Valley Toshka4 | 39115686 | 29805752.9 | 5006807.85 | 34812560.75
LAYAN Substation | 10582 |  | LAYAN Substation | 172869.56 | 286963.48 | 0 | 143481.74
MIDELEC 66 KV OHTL | Midor Inv. 01 | 1 | MIDELEC 66 KV OHTL1 | 1787986.2 | 1501908.41 | 268197.93 | 1770106.34
October Dry Port Railway | ODP ipc03 | 3 | October Dry Port Railway3 | 13511957.5 | 0 | 0 | 14187555.375
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 11 | 11 | Hosh Essa 220 KV OHTL11 | 2240000 | 0 | 235200 | 235200
Toshka GIS 500 kV | Toshka Sub Inv. 01 $ | 1 | Toshka GIS 500 kV1 | 8268188.57 | 5460447.72 | 2170399.5 | 7630847.22
Miscellaneous Projects | 2101210005 |  | Miscellaneous Projects | 10500 | 11655 | 0 | 11655
DPW Onshore Port & Terminal | DP World IPC028 | 28 | DPW Onshore Port & Terminal28 | 27099548.46 | 19977105.85 | 4064932.27 | 24042038.12
Olympic Multi – Sports Hall | OLYMPIC CIVIL-IPC04 | 4 | Olympic Multi – Sports Hall4 | 56613357.08 | 10576930 | 36483374.25 | 47964451.75
Shenzo Aby Bridge - Haggana | FPC - Shenzo Aby |  | Shenzo Aby Bridge - Haggana | 162900 | 121982.25 | 0 | 121982.25
LAYAN Substation | 10623 |  | LAYAN Substation | 138800 | 437220 | 0 | 145740
National Batteries LP-05-20 | 20 |  | National Batteries LP-05-20 | 1157895 | 683539.125 | 330000.245 | 1013539.37
seashell Playa | IPC-7-PLAYA | 7 | seashell Playa7 | 393993.05 | 273306.55 | 63038.89 | 336345.44
10Th of Ramadan LRT | LRT 10Ramadan Inv.04 | 4 | 10Th of Ramadan LRT4 | 7953536.78 | 539392.5 | 795353.68 | 1334746.18
Governmental Campus-N2 | 25 |  | Governmental Campus-N2 | 2564261.48 | 2564261.48 | 0 | 2564261.48
Tamey El-amdeed Substation | TAM-CW-EGP-24 | 24 | Tamey El-amdeed Substation24 | 112131.3 | 160139 | 0 | 160139
MOTHANA 400/132kV SS | 414 |  | MOTHANA 400/132kV SS | 43876.07 | 43876.07 | 0 | 43876.07
Miscellaneous Projects | 2012210013 |  | Miscellaneous Projects | 36431.91 | 41532.3774 | 0 | 41532.3774
New Heliopolis | Inv. 13 Heliopolise | 13 | New Heliopolis13 | 8453388 | 6563573.05 | 830122.7 | 7393695.75
ElMoneeb 2 | IPC#3 - ElMoneeb | 3 | ElMoneeb 23 | 727800 | 248132.74 | 0 | 677282.63
Marassi Inner Marina - PKG178 | FPC - PKG#178 |  | Marassi Inner Marina - PKG178 | 61650 | 54868.5 | 0 | 54868.5
Bridge Axis Firdaws | INV ( 3 ) | 3 | Bridge Axis Firdaws3 | 1601988.8 | 1505869.47 | 0 | 1505869.47
AWEER POWER STATION 'H' Phase | LOC/018 |  | AWEER POWER STATION 'H' Phase | 455396.7 | 399737.1007 | 50599.63 | 450336.7307
Akhmem Assiut | Ref.Ret Asuit akhm |  | Akhmem Assiut | 10000000 | 10000000 | 0 | 10000000
Canal Sugar S/s | Ref.Ret Sugar Sub $ |  | Canal Sugar S/s | 123689.55 | 123689.55 | 0 | 123689.55
HyperOne Zayed Extension | IPC-FINAL-HYPER ONE |  | HyperOne Zayed Extension | 16067538.5 | 2754557 | 6313451.95 | 9068008.95
Zone(J) South Valley Toshka | South Valley Inv. 01 | 1 | Zone(J) South Valley Toshka1 | 47619261.45 | 33899453.3 | 6095265.5 | 39994718.8
Racecores 3092-16 132KV C | 10902 |  | Racecores 3092-16 132KV C | 2016458.7 | 1673660.72 | 0 | 1673660.72
EMAAR- Pkg 140-ITP-Mivida | PKG #140 IPC025 | 25 | EMAAR- Pkg 140-ITP-Mivida25 | 5220299.96 | 9290247.798 | 261808.31 | 9552056.108
Olympic Multi – Sports Hall | Olympic Hall IPC05 | 5 | Olympic Multi – Sports Hall5 | 89184449.38 | 17108044.99 | 57918857.35 | 75550834.84
Zone(J) South Valley Toshka | South Valley Inv. 07 | 7 | Zone(J) South Valley Toshka7 | 36376001.8 | 27718098.9 | 4656128.25 | 32374227.15
Air Force Project | Air Force Inv . 12 | 12 | Air Force Project12 | 9743768.2 | 6976135 | 2435942.05 | 9412077.05
MDF Factory | MDF FACTORY3 IPC01 | 1 | MDF Factory1 | 1269450 | 920351.25 | 361793.25 | 1282144.5
LAYAN Substation | 10804 |  | LAYAN Substation | 36500 | 268275 | 0 | 38325
BRSH-JHRC | 11723 |  | BRSH-JHRC | 506746.2476 | 50674.62 | 0 | 50674.62
Cairo Monorail - 6th October | IPC4 - Monorail | 4 | Cairo Monorail - 6th October4 | 1260000 | 1247400 | 0 | 1247400
MDF Factory | MDF IPC05 | 5 | MDF Factory5 | 23254260.42 | 21785509.721 | 1346981.76 | 23132491.481
Ahl Misr P3 – Zamalek Sector | IPC#6` | 6 | Ahl Misr P3 – Zamalek Sector6 | 234900 | 224265.75 | 0 | 224265.75
SHATRA 400/132kV SS | 425 |  | SHATRA 400/132kV SS | 105926.91 | 105926.91 | 0 | 105926.91
Olympic Multi – Sports Hall | Olympic Hall IPC02 | 2 | Olympic Multi – Sports Hall2 | 36131324.45 | 25980535.02 | 17523700 | 43504235.02
Waldorf Astoria Cairo | Waldorf IPC7 | 7 | Waldorf Astoria Cairo7 | 14720271.03 | 8710614.8515 | 5943712.87 | 14654327.7215
CFC Podium 2 | CFC IPC027 | 27 | CFC Podium 227 | 7714993.76 | 7405131.708 | 0 | 7405131.708
New Babil 400/132KV GIS Substa | 2108210001 |  | New Babil 400/132KV GIS Substa | 4032620.32 | 4032620.32 | 0 | 4032620.32
Zafranaa - Beni Suef | Ref.Ret Zafra-B-Suef |  | Zafranaa - Beni Suef | 1114579.04 | 0 | 0 | 1114579.04
Racecores 3092-17 132KV E | 10982 |  | Racecores 3092-17 132KV E | 12380.9524 | 26000 | 0 | 13000
Akhmem - Qena | Ret Qen-akh 7 T |  | Akhmem - Qena | 50000000 | 50000000 | 0 | 50000000
Akhmem Assiut | Ref.Ret Asuit akh 5 |  | Akhmem Assiut | 4316843.16 | 0 | 0 | 4316843.16
CFC Podium 2 | CFC IPC026 | 26 | CFC Podium 226 | 6460765.95 | 4897254.2975 | 0 | 4897254.2975
Air Force Project | Air Force Inv . 19 | 19 | Air Force Project19 | 1557454.2 | 1504371.53 | 0 | 1504371.53
Air Force Project | Air Force Inv . 18 | 18 | Air Force Project18 | 3225717.12 | 3115768.47 | 0 | 3115768.47
Get Business Complex | INV ( 4 ) GET | 4 | Get Business Complex4 | 126432 | 118846.08 | 0 | 118846.08
EGAT Pelletizing Plant | EGAT WaterTank IPC06 | 6 | EGAT Pelletizing Plant6 | 1464316.6 | 1449673.43 | 0 | 1449673.43
Kattameya Creeks | katamya ipc11 | 11 | Kattameya Creeks11 | 46662391.16 | 43214038.288 | 5304728.52 | 48518766.808
LAYYAH CCPP | 519 |  | LAYYAH CCPP | 11458140 | 9066879 | 2391258 | 11458137
Ministries Buildings | Minist Core IPC09 | 9 | Ministries Buildings9 | 6450238.37 | 5433920.01 | 0 | 5433920.01
TZ – Offshore E&M Procurement | 443 |  | TZ – Offshore E&M Procurement | 695957.09 | 553405.1 | 71276 | 624681.1
Sokhna Port Expansion | sokhna port ipc 12 | 12 | Sokhna Port Expansion12 | 101620062.95 | 70395885.55 | 20324012.59 | 90719898.14
Sokhna Port Expansion | sokhna port ex ipc06 | 6 | Sokhna Port Expansion6 | 38544935.71 | 26209057.4855 | 8094436.5 | 34303493.9855
Mauritania Lot 1 | Inv.15 - Lot 1 | 15 | Mauritania Lot 115 | 345052 | 327784.78 | 0 | 327784.78
Port Said Grain Storage | IPC#5 GSCC Port Said | 5 | Port Said Grain Storage5 | 1155000 | 0 | 0 | 1155000
Port Said Grain Storage | IPC#1-Port Saeid | 1 | Port Said Grain Storage1 | 1131900 | 807661.47 | 0 | 948264.64
Ahl Misr Walkway | 120721 |  | Ahl Misr Walkway | 22760 | 18473.89 | 0 | 18473.89
October Dry Port Railway | ODP IPC02 | 2 | October Dry Port Railway2 | 19648020 | 12505964.73 | 4126084.2 | 16632048.93
Akhmem Assiut | Ref. Akhmem Asuit2T |  | Akhmem Assiut | 15000000 | 0 | 0 | 15000000
Racecores 3092-16 132KV C | 11082 |  | Racecores 3092-16 132KV C | 22300 | 23415 | 0 | 23415
Racecores 3092-17 132KV E | 11144 |  | Racecores 3092-17 132KV E | 2227.22 | 2227.22 | 0 | 2227.22
ENR-Signaling Inst. | ENR-Sign Inst Inv04 | 4 | ENR-Signaling Inst.4 | 6948000.16 | 5836320.13 | 694800.02 | 6531120.15
Egat Rolling Mill no.4 | Rolling mill ipc 03 | 3 | Egat Rolling Mill no.43 | 12117327 | 10231445.3 | 2370574.78 | 12602020.08
Water pumping New Obour City | Wat Pump Obour Inv.2 | 2 | Water pumping New Obour City2 | 22613426.64 | 17284740.87 | 2374409.8 | 19659150.67
Benban 500 K.V/95 K.M | Benban Lot2 Inv 12 $ | 12 | Benban 500 K.V/95 K.M12 | 205796.67 | 172869.2 | 21608.65 | 194477.85
Tamey El-amdeed Substation | Tam SW Final |  | Tamey El-amdeed Substation | 43750.92 | 38938.32 | 0 | 38938.32
Ismailiya East Substation | SW Final |  | Ismailiya East Substation | 943311 | 7865054.79 | 0 | 7865054.79
Port Said Port Silos | PORT SAID IPC 27 | 27 | Port Said Port Silos27 | 1478728.71 | 0 | 147871.1884 | 147871.1884
PLAYA ROOF & Wet Areas | IPC-4-Playa Roof | 4 | PLAYA ROOF & Wet Areas4 | 61197.5 | 52513.56 | 0 | 52513.56
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 02 | 2 | Hosh Essa 220 KV OHTL2 | 1585131.64 | 952668.25 | 166438.82 | 1119107.07
Al-Parco | INV ( 3 )ALparco | 3 | Al-Parco3 | 2422608 | 0 | 0 | 2422608
Racecores 3092-17 132KV E | 11283 |  | Racecores 3092-17 132KV E | 769.67 | 769.67 | 0 | 769.67
Racecores 3092-17 132KV E | 11282 |  | Racecores 3092-17 132KV E | 4933.41 | 4933.41 | 0 | 4933.41
Racecores 3092-16 132KV C | 11286 |  | Racecores 3092-16 132KV C | 36036.49 | 36036.49 | 0 | 36036.49
LP-15-21 UIC | 54 |  | LP-15-21 UIC | 30000 | 33900 | 0 | 33900
Cairo-Alex Railway | cairo-alex ipc 17 | 17 | Cairo-Alex Railway17 | 34296433.2 | 23818474.05 | 3601125.49 | 27419599.54
Ain Sokhna Port Development | IPC#9 - Spkhna port | 9 | Ain Sokhna Port Development9 | 1591288 | 1454830.83 | 0 | 1483644.59
MDF Factory | MDF FACTORY IPC08 | 8 | MDF Factory8 | 7024663.54 | 12778186.187 | 807862.18 | 13586048.367
Racecores 3092-16 132KV C | 11363 |  | Racecores 3092-16 132KV C | 5210.82 | 5210.82 | 0 | 5210.82
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.02 | 2 | 10th Ramadan Indu Park Plot112 | 1 | 27960735.63 | 0 | 27960735.63
EGAT Pelletizing Plant | egat watertank ipc10 | 10 | EGAT Pelletizing Plant10 | 3540729.8 | 3505322.5 | 0 | 3505322.5
Hyper El-Temsah | HYPER ELCTRO-FINAL |  | Hyper El-Temsah | 164642.05 | 0.38 | 0 | 0.38
Expansion of Ring Road | FPC - Tiger |  | Expansion of Ring Road | 51800 | 49634 | 0 | 49634
LAYAN Substation | 11746 |  | LAYAN Substation | 177273.88 | 294274.628 | 0 | 147137.314
Infra Project 4428 | 220421005 |  | Infra Project 4428 | 285714285.72 | 300000000.006 | 0 | 300000000.006
LAYYAH CCPP | 520 |  | LAYYAH CCPP | 10283760 | 8231475 | 2052285 | 10283760
EGAT Pelletizing Plant | ELCO EGAT IPC 11 | 11 | EGAT Pelletizing Plant11 | 14893958.08 | 14151886.794 | 1337829.61 | 15489716.404
158E/2019 33kv Project | 11519 |  | 158E/2019 33kv Project | 497217.6 | 1342487.52 | 0 | 447495.84
Waldorf Astoria Cairo | WALDORF astoria IPC1 | 1 | Waldorf Astoria Cairo1 | 6707988.52 | 4511122.119 | 1760846.99 | 6271969.109
New Babil 400/132KV GIS Substa | 220321001 |  | New Babil 400/132KV GIS Substa | 1268718.64 | 1268718.64 | 0 | 1268718.64
Mivida BP#189 | Emaar pkg#189 ipc 31 | 31 | Mivida BP#18931 | 19514716.97 | 0 | 3602734.16 | 3602734.16
Mivida BP#189 | Emaar PKG#189 IPC28 | 28 | Mivida BP#18928 | 3487392.64 | 2409288.192 | 309513.68 | 2718801.872
Mivida BP#189 | Emaar pkg#189 ipc 14 | 14 | Mivida BP#18914 | 22729528.92 | 23637153.386 | 2841944.63 | 26479098.016
seashell Playa | IPC-16-PLAYA | 16 | seashell Playa16 | 1252671.35 | 1074917.34 | 0 | 1074917.34
AWEER POWER STATION 'H' Phase | IMP/069 |  | AWEER POWER STATION 'H' Phase | 90156.23 | 94664.0415 | 0 | 94664.0415
EGAT Pelletizing Plant | Elco EGAT IPC12 | 12 | EGAT Pelletizing Plant12 | 8116942.79 | 8095552.3195 | 346068.18 | 8441620.4995
P.I.Parks - Plot 10 | PIP indust Inv.02 | 2 | P.I.Parks - Plot 102 | 6152138.66 | 11344920.68 | 1453489.88 | 12798410.56
Faculty of Medicine | mansora finish ipc22 | 22 | Faculty of Medicine22 | 11782769.52 | 8785418.9948 | 1767415.43 | 10552834.4248
MDF Factory | Mdf factory2 ipc05 | 5 | MDF Factory5 | 2046589.82 | 2067055.7248 | 0 | 2067055.7248
Ora Zed Landscape Ph1 | Ora landscape ipc 10 | 10 | Ora Zed Landscape Ph110 | 3148169.54 | 2562980.717 | 330557.8 | 2893538.517
Astoria Sharm elSheikh | astoria sharm ipc 01 | 1 | Astoria Sharm elSheikh1 | 1119573 | 837813.8 | 326542.1 | 1164355.9
LAYYAH CCPP | 523 |  | LAYYAH CCPP | 10283760 | 3174000 | 1380785 | 4554785
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv $11 | 11 | Benban 3/ Toshka 2 LOT 411 | -339705.29 | -356690.55 | 0 | -356690.55
seashell Playa | IPC-18-PLAYA | 18 | seashell Playa18 | 526143.1 | 451483.39 | 0 | 451483.39
Air Defense College | air devance ipc03 | 3 | Air Defense College3 | 3832891.1 | 1188779.99 | 0 | 3249422.99
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.03 | 3 | 10th Ramadan Indu Park Plot113 | 16472966.76 | 26056793.31 | 2594492.26 | 28651285.57
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .16 | 16 | Benban 3/ Toshka 2 LOT 416 | 95081746.73 | 74828938.59 | 9983583.41 | 84812522
LAYAN Substation | 11682 |  | LAYAN Substation | 47897.2472 | 50292.1096 | 0 | 50292.1096
LAYYAH CCPP | 10020 |  | LAYYAH CCPP | 0 | 5733920.97 | 0 | 5733920.97
AWEER POWER STATION 'H' Phase | ENG/055 |  | AWEER POWER STATION 'H' Phase | 22065.16 | 23168.418 | 0 | 23168.418
Infra Project 2531 | 220421003 |  | Infra Project 2531 | 69095346.19 | 43618300 | 14357670 | 57975970
Infra Project 2524 | 220321002 |  | Infra Project 2524 | 90398178.05 | 90398178.05 | 0 | 90398178.05
158E/2019 33kv Project | 10342 |  | 158E/2019 33kv Project | 2539278.61 | 2285350.75 | 0 | 2285350.75
Governmental Campus-N2 | 64 |  | Governmental Campus-N2 | 697588.06 | 697588.06 | 0 | 697588.06
Monorail | 220621008 |  | Monorail | 363298 | 410526.74 | 0 | 410526.74
LP-20-21 ACUD Fiber optics | 71 |  | LP-20-21 ACUD Fiber optics | 1166400 | 1318032 | 0 | 1318032
MDF Factory | MDF Factory ipc (27) | 27 | MDF Factory27 | 7649824.31 | 19177600.34 | 3212977.19 | 22390577.53
New Babil 400/132KV GIS Substa | 220721001 |  | New Babil 400/132KV GIS Substa | 217380.8 | 217380.8 | 0 | 217380.8
New Babil 400/132KV GIS Substa | 220721004 |  | New Babil 400/132KV GIS Substa | 1787953.49 | 1787953.49 | 0 | 1787953.49
NUCA R05 - Z02 | R5(2) ipc 23 | 23 | NUCA R05 - Z0223 | 30312335.29 | 24605476.43 | 3166889.7 | 27772366.13
South Helwan PP (CP-117) | 180056 |  | South Helwan PP (CP-117) | 201244.72 | 179948.77 | 31755.66 | 211704.43
Port Saad Industiral zone | IPC#4 | 4 | Port Saad Industiral zone4 | 1095780 | 1055236.14 | 0 | 1055236.14
MDF Factory | MDF (2) - IPC 8 | 8 | MDF Factory8 | 338870.79 | 322759.5006 | 0 | 322759.5006
Central Bus Station | inv ( final ) T0022 |  | Central Bus Station | 274780 | 274780 | 0 | 274780
Al Montaza Hotels - Alexandria | inv ( 3 ) montazha | 3 | Al Montaza Hotels - Alexandria3 | 939729 | 892742.55 | 0 | 892742.55
Olympic Multi – Sports Hall | olmpiclandscape ipc1 | 1 | Olympic Multi – Sports Hall1 | 23918543.68 | 3791250 | 17031510 | 20822760
New Giza Teaching Hospital | New Giza Hosp ipc16 | 16 | New Giza Teaching Hospital16 | 22109235.45 | 8749433.6065 | 2152996.48 | 18402430.0865
LAYAN Substation | 11619 |  | LAYAN Substation | 267278.0523 | 677549.8648 | 0 | 225849.9549
SSC Suez Steel Company Project | SUEZ STEEL SSC IPC 1 | 1 | SSC Suez Steel Company Project1 | 10223133.6 | 8726335.414 | 2825805.55 | 11552140.964
SSC Suez Steel Company Project | In&ReApply(SSC)IPC2 | 2 | SSC Suez Steel Company Project2 | 3081346.71 | 3020707.7794 | 399587.07 | 3420294.8494
SSC Suez Steel Company Project | intak&ret apply ipc5 | 5 | SSC Suez Steel Company Project5 | 2725254.77 | 1779061.4678 | 1245971.33 | 3025032.7978
SSC Suez Steel Company Project | In&reApply(ABB)ipc1 | 1 | SSC Suez Steel Company Project1 | 779997.07 | 509186.4298 | 356610.32 | 865796.7498
EGAT Injection | TR0048-00002 | 2 | EGAT Injection2 | 98000 | 84093.8 | 0 | 84093.8
GOV2 - Infra | Gov2 ipc 15+16 | 15 | GOV2 - Infra15 | 15963362.95 | 10956705.9675 | 1490940.99 | 12447646.9575
EGAT Pelletizing Plant | EGAT Watertank-IPC12 | 12 | EGAT Pelletizing Plant12 | 698940.32 | 691950.916 | 0 | 691950.916
Ministries Buildings | minis shel ipc09 | 9 | Ministries Buildings9 | 3018358 | 2542560 | 0 | 2542560
MDF Factory | MDF (2) - IPC9 | 9 | MDF Factory9 | 1654996.96 | 1671546.9244 | 0 | 1671546.9244
Ring Road El Mansoria | INV ( 1 ) ALmansorya | 1 | Ring Road El Mansoria1 | 332760 | 174309.36 | 0 | 174309.36
CS-20 Mall | inv ( 15 ) CS-20 | 15 | CS-20 Mall15 | 155689.45 | 60718.89 | 0 | 60718.89
CS-20 Mall | inv ( 16 ) CS-20 | 16 | CS-20 Mall16 | 520583.43 | 173151.91 | 0 | 173151.91
CS-20 Mall | inv ( 1 ) CS-20 | 1 | CS-20 Mall1 | 945878.85 | 889126.12 | 0 | 889126.12
Kafr Shokr Bridge | kafr shokr ipc#9 | 9 | Kafr Shokr Bridge9 | 5509702.86 | 4811892.2 | 0 | 4811892.2
Ministries Buildings | Min MEP. IPC5 | 5 | Ministries Buildings5 | 121861476.8 | 0 | 0 | 76281582.83
LRT | FPC - LRT ARABCo |  | LRT | 882948 | 829971.12 | 0 | 829971.12
Egat Rolling Mill no.4 | ROLLING MILL IPC 09 | 9 | Egat Rolling Mill no.49 | 19868885.15 | 15728875.4675 | 4934765.09 | 20663640.5575
Olympic Multi – Sports Hall | Finishing IPC02 | 2 | Olympic Multi – Sports Hall2 | 29261275 | 1689654 | 25815944.5 | 27505598.5
Astoria Sharm elSheikh | Astoria sharm- IPC4 | 4 | Astoria Sharm elSheikh4 | 1055208 | 709627 | 276992.1 | 986619.1
New Giza Teaching Hospital | new giza hos ipc3 | 3 | New Giza Teaching Hospital3 | 7560552.29 | 7466045.3845 | 0 | 7466045.3845
Railway Bridge - Assuit | IPC#1&2 -Assuit Rent | 1 | Railway Bridge - Assuit1 | 410400 | 796176 | 0 | 398088
Dwelling Villas Seashell Playa | IPC001 Dewalling | 1 | Dwelling Villas Seashell Playa1 | 75551.56 | 65246.33 | 0 | 65246.33
ElSewedy HQ Internal Finishing | Elsewedy HQ IPC19 | 19 | ElSewedy HQ Internal Finishing19 | 11160546.75 | 0 | 8749943.6 | 10873318.8875
EMAAR-PKG# 101-UPTOWN | PKG #101 IPC021. | 21 | EMAAR-PKG# 101-UPTOWN21 | 952924.08 | 803886.084 | 446634.21 | 1250520.294
MDF Factory | MDF IPC15 | 15 | MDF Factory15 | 8189110.5 | 11311884.995 | 2340438.88 | 13652323.875
Get Business Complex | INV ( 17 ) GET | 17 | Get Business Complex17 | 3177489.8 | 179900.41 | 0 | 179900.41
Sokhna Port Expansion | sokhna port ex ipc07 | 7 | Sokhna Port Expansion7 | 54124258.65 | 36803653.95 | 11366094.32 | 48169748.27
ElSewedy HQ Internal Finishing | elsewedy HQ- IPC21 | 21 | ElSewedy HQ Internal Finishing21 | 6969185.9 | 0 | 2341646.56 | 4046292.505
Katameya Creeks - RME | IPC00001 | 1 | Katameya Creeks - RME1 | 67028.72 | 59353.94 | 0 | 59353.94
Playa Resort | 43- kantine 5 |  | Playa Resort | 35000 | 35000 | 0 | 35000
Creeks URBN-K | Urbn-k IPC 7 | 7 | Creeks URBN-K7 | 18657407.33 | 16761479 | 1761482.87 | 18522961.87
Sokhna Port Expansion | sokhna port ex ipc 8 | 8 | Sokhna Port Expansion8 | 52378217.65 | 36284089.65 | 10475643.53 | 46759733.18
SSC Suez Steel Company Project | Revamp ipc(4) | 4 | SSC Suez Steel Company Project4 | 3836789.63 | 2647384.8452 | 1151036.89 | 3798421.7352
ORA-ZED Towers P01B | IPC#00002 | 2 | ORA-ZED Towers P01B2 | 30183.08 | 26727.11 | 0 | 26727.11
Air Defence College | IPC004 Air Defense | 4 | Air Defence College4 | 247985.38 | 207914.59 | 0 | 207914.59
Port Said Port Silos | port said silos ipc9 | 9 | Port Said Port Silos9 | 3139228.09 | 2756360.9335 | 313922.81 | 3070283.7435
EPICO 3 Facility | EIPICO3 - IPC1 | 1 | EPICO 3 Facility1 | 12192163.2 | 12050858.57 | 0 | 12050858.57
ORA-ZED Towers P01B | IPC0000001 | 1 | ORA-ZED Towers P01B1 | 113671.35 | 100655.98 | 0 | 100655.98
Kemet Tower | INV ( 2-3-4 ) KEMET | 2 | Kemet Tower2 | 467520 | 401178.91 | 0 | 401178.91
seashell Playa | IPC#000015 | 15 | seashell Playa15 | 314783.01 | 270115.3 | 0 | 270115.3
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC25 | 25 | ElSewedy HQ Internal Finishing25 | 17937426.6 | 4987239.22 | 0 | 9125697.86
WADY EL-NATROUN BRIDGE(HST) | IPC#5 WADI | 5 | WADY EL-NATROUN BRIDGE(HST)5 | 328425 | 298242.74 | 0 | 298242.74
WADY EL-NATROUN BRIDGE(HST) | IPC#7 WADI | 7 | WADY EL-NATROUN BRIDGE(HST)7 | 767070 | 655166.26 | 0 | 655166.26
U4,U8 Seashell Playa | IPC006 TR60 | 6 | U4,U8 Seashell Playa6 | 87496.95 | 39612.11 | 0 | 39612.11
Olympic Multi – Sports Hall | Olypic sehe IPC1 | 1 | Olympic Multi – Sports Hall1 | 10647712 | 1893920 | 7000000 | 8893920
DP World Basin 2 Ph2 | Dp world ph.2-IPC 2 | 2 | DP World Basin 2 Ph22 | 31327285.45 | 0 | 0 | 31327285.45
HST El Mahager Bridge | ipc 2 elmahager | 2 | HST El Mahager Bridge2 | 10987767.86 | 3492288.9 | 0 | 3492288.9
Ora Zed Landscape Ph1 | Ora ph landscap ipc2 | 2 | Ora Zed Landscape Ph12 | 2071866.5 | 1828422.185 | 217545.98 | 2045968.165
WADY EL-NATROUN BRIDGE(HST) | IPC#10 WADI | 10 | WADY EL-NATROUN BRIDGE(HST)10 | 1255380 | 1214339.67 | 0 | 1214339.67
El-Warraq | IPC# 1 WARAAQ | 1 | El-Warraq1 | 1440000 | 909064 | 0 | 909064
MDF Factory | MDF 2 IPC (15) | 15 | MDF Factory15 | 1493437.21 | 1508253.0542 | 0 | 1508253.0542
Sokhna Port Expansion | sokhna port ex ipc11 | 11 | Sokhna Port Expansion11 | 73288962.77 | 50769799.2 | 14657792.55 | 65427591.75
SSC Suez Steel Company Project | in.&ret.sup sscipc1 | 1 | SSC Suez Steel Company Project1 | 2140488 | 2311727.04 | 0 | 2311727.04
SSC Suez Steel Company Project | R.O.SU.PRIC.ADJ.IPC3 | 3 | SSC Suez Steel Company Project3 | 8704005.47 | 9400325.9111 | 0 | 9400325.9111
Seashell Playa 5 Villas | playa-c185 pic 1 |  | Seashell Playa 5 Villas | 74965.5 | 48301.29 | 0 | 48301.29
Seashell Playa 5 Villas | playa c-204 ipc 2 | 2 | Seashell Playa 5 Villas2 | 24044.74 | 20765.03 | 0 | 20765.03
Seashell Playa 5 Villas | seashell playa ipc04 | 4 | Seashell Playa 5 Villas4 | 208421.31 | 89386.81 | 0 | 89386.81
Seashell Playa 5 Villas | seashell playa ipc 6 | 6 | Seashell Playa 5 Villas6 | 421226.03 | 278628.8 | 0 | 278628.8
October Under-Railway Tunnel | october tunnel ipc06 | 6 | October Under-Railway Tunnel6 | 1809302.29 | 1337162.5545 | 0 | 1337162.5545
Creeks URBN-K | Urbn-k ipc (8) | 8 | Creeks URBN-K8 | 18875663.98 | 16707944.9992 | 1948483.69 | 18656428.6892
Kattameya Creeks | Katameya Creek ipc35 | 35 | Kattameya Creeks35 | 59094596.48 | 46816344 | 14334625.91 | 61150969.91
Katameya Creeks - RME | IPC005 | 5 | Katameya Creeks - RME5 | 86893.7 | 76944.36 | 0 | 76944.36
EDNC Hardscape Package | sorealhardscapeIPC11 | 11 | EDNC Hardscape Package11 | 1095191.83 | 1006501.9215 | 0 | 1006501.9215
U7-SEASHELL | IPC03 TR64 | 3 | U7-SEASHELL3 | 113020.28 | 97604.33 | 0 | 97604.33
Creeks URBN-K | Katameya urbnk ipc9 | 9 | Creeks URBN-K9 | 18620717.8 | 16997068 | 1578985.46 | 18576053.46
EGAT Mechanical Installations | Egat Piping ipc 2 | 2 | EGAT Mechanical Installations2 | 71294.74 | 54176.8715 | 17823.68 | 72000.5515
MDF Factory | MDF Factory ipc 29 | 29 | MDF Factory29 | 6882776.19 | 10041845.6384 | 2890766 | 12932611.6384
Seashell Playa 5 Villas | seashell playa ipc 5 | 5 | Seashell Playa 5 Villas5 | 125965.27 | 94159.07 | 0 | 94159.07
U7-SEASHELL | IPC001 TR64 | 1 | U7-SEASHELL1 | 383850.75 | 331493.5 | 0 | 331493.5
Al Montaza Hotels - Alexandria | inv ( final) montazh |  | Al Montaza Hotels - Alexandria | 343024.5 | 223870.183 | 0 | 223870.183
Ministries Buildings | Minis MEP IPC8 | 8 | Ministries Buildings8 | 30376066 | 25591430 | 0 | 25591430
Egyptian Exchange building | IPC0011 | 11 | Egyptian Exchange building11 | 160250 | 127526.37 | 0 | 127526.37
Central Capital | INV ( 1 ) Central Ca | 1 | Central Capital1 | 168300 | 158202 | 0 | 158202
RING ROAD MARYOTIA EXPANSION | MARIOTYIA IPC16 | 16 | RING ROAD MARYOTIA EXPANSION16 | 40484939.8 | 40080090.4 | 0 | 40080090.4
Olympic Multi – Sports Hall | Olympic fins ipc5 | 5 | Olympic Multi – Sports Hall5 | 15781358 | 11120610 | 0 | 11120610
Air Defense College | air def finish4 IPC1 | 1 | Air Defense College1 | 29831422 | 6284750 | 18612000 | 24896750
British International School | Bis school ipc (1) | 1 | British International School1 | 6616812.11 | 8894097.5 | 4137870.4 | 13031967.9
Pushing Tunnel | inv ( 1 ) T. Pushing | 1 | Pushing Tunnel1 | 4121100 | 3330260.91 | 0 | 3330260.91
Royal City | Royal City Final 43 |  | Royal City | 13228025 | 19699829.51 | 0 | 19699829.51
26th of July Corridor New | IPC FINAL 26th |  | 26th of July Corridor New | 937500 | 804468.75 | 0 | 804468.75
Borg El Arab Bridge - Km 21 | IPC#002 - Kilo21 | 2 | Borg El Arab Bridge - Km 212 | 726647.4 | 610933.56 | 0 | 610933.56
Bahr El Baqar Treatment Plant | IPC#2 Bahr El Baqar | 2 | Bahr El Baqar Treatment Plant2 | 134756.7 | 61300 | 0 | 61300
U4,U8 Seashell Playa | IPC09 TR60 | 9 | U4,U8 Seashell Playa9 | 189602.64 | 163740.84 | 0 | 163740.84
U7-SEASHELL | IPC6&7TR0064 | 6 | U7-SEASHELL6 | 952362.67 | 734764.32 | 0 | 734764.32
Egyptian Exchange Building | Egy Exchange IPC3 | 3 | Egyptian Exchange Building3 | 67025016.19 | 8019519.9995 | 0 | 60139519.9995
ora zed orascom | IPC04TR0069 | 4 | ora zed orascom4 | 634024.87 | 573657.258 | 0 | 573657.258
ORA-ZED Towers P01B | IPC10,11 TR51 | 10 | ORA-ZED Towers P01B10 | 294299.88 | 260602.55 | 0 | 260602.55
MDF Factory | Mdf Factory ipc 30 | 30 | MDF Factory30 | 46563799.32 | 11554812.9428 | 19556786 | 31111598.9428
SSC Suez Steel Company Project | int&rut sup ABB ipc6 | 6 | SSC Suez Steel Company Project6 | 4670440.09 | 3667977.9926 | 1609619.31 | 5277597.3026
Waldorf Astoria Cairo | Waldorf IPC 20 | 20 | Waldorf Astoria Cairo20 | 3956218.97 | 0 | 0 | 3400771.9975
VILLA CLUSTER C | IPC06TR0078 | 6 | VILLA CLUSTER C6 | 180226.88 | 155643.94 | 0 | 155643.94
Mohamed Ali Palace Restoration | Mohamed Aly IPC Fin |  | Mohamed Ali Palace Restoration | 1527763.81 | 1438745 | 0 | 1438745
MAF HQ Renovation | Carrefour Head ipc 5 | 5 | MAF HQ Renovation5 | 1000709.81 | 935663.6624 | 0 | 935663.6624
U3 & U5 | IPC15TR0055 | 15 | U3 & U515 | 37130.4 | 28388.9 | 0 | 28388.9
Air Defense College | Air Dev fire IPC2 | 2 | Air Defense College2 | 402502 | 338700 | 0 | 338700
Air Defense College | Air dev elec IPC2 | 2 | Air Defense College2 | 34088309 | 28718990 | 0 | 28718990
R05 (New) | IPC001 TR59 | 1 | R05 (New)1 | 100800 | 85488.48 | 0 | 85488.48
New Giza Teaching Hospital | New Giza ipc 19 | 19 | New Giza Teaching Hospital19 | 8254281.5 | 4118256.08 | 1119307 | 7237562.975
HST Bridges-Sokhna & Mahager | sokhna Br. ipc14+15 | 14 | HST Bridges-Sokhna & Mahager14 | 84796100 | 10610468.95 | 0 | 76158305.95
Faculty of Medicine | mansora finish ipc08 | 8 | Faculty of Medicine8 | 5998094.29 | 4475076.3245 | 899714.14 | 5374790.4645
Faculty of Medicine | MANSOURA IPC13 | 13 | Faculty of Medicine13 | 2416869.52 | 2044633.986 | 120843.48 | 2165477.466
NUCA R05 - Z02 | R05(2) ipc 28 | 28 | NUCA R05 - Z0228 | 33756896.45 | 27484539.3825 | 3452627.4 | 30937166.7825
Seashell Playa 5 Villas | playa c072- ipc 5 | 5 | Seashell Playa 5 Villas5 | 16407.14 | 13662.44 | 0 | 13662.44
Astoria Sharm elSheikh | Woldorf sharm ipc 7 | 7 | Astoria Sharm elSheikh7 | 1116626 | 1160163.51 | 0 | 1160163.51
SSC Suez Steel Company Project | Baraka Fance ipc 2 | 2 | SSC Suez Steel Company Project2 | 12315634 | 8497787.46 | 3694690.2 | 12192477.66
SSC Suez Steel Company Project | Baraka Fance ipc 1 | 1 | SSC Suez Steel Company Project1 | 3575400 | 2467026 | 1072620 | 3539646
SSC Suez Steel Company Project | New Gas Station ipc1 | 1 | SSC Suez Steel Company Project1 | 3190160 | 2201210.4 | 957048 | 3158258.4
SSC Suez Steel Company Project | svc ipc 2 | 2 | SSC Suez Steel Company Project2 | 649999.96 | 438843.8784 | 194999.99 | 633843.8684
Capital One | inv ( 11 ) Captal 1 | 11 | Capital One11 | 695119.09 | 0 | 204831.941 | 204831.941
Air Defense College | Air dif finish4 IPC2 | 2 | Air Defense College2 | 2903787 | 2446040 | 0 | 2446040
U6T11 PART1 Palay | IPC02TR0075 | 2 | U6T11 PART1 Palay2 | 9785.91 | 8940.4 | 0 | 8940.4
VILLA CLUSTER C | IPC04TR0078 | 4 | VILLA CLUSTER C4 | 25709 | 19802.29 | 0 | 19802.29
NUCA R05 - Z02 | R05(2) ipc 42 | 42 | NUCA R05 - Z0242 | 11620344.48 | 18419500.05 | 2288683.38 | 20708183.43
El-Warraq | IPC 3 elwaraq | 3 | El-Warraq3 | 500000 | 250000 | 0 | 250000
Wady El Natroon Bridge | Wady elnatroon ipc07 | 7 | Wady El Natroon Bridge7 | 83651195.24 | 34583009.36 | 0 | 74583009.36
MAF HQ Renovation | Carrefour RBS IPC 3 | 3 | MAF HQ Renovation3 | 4802157.24 | 3229450.7297 | 1260566.28 | 4490017.0097
HST Bridges-Sokhna & Mahager | Sokhna Bri esc.1:13 |  | HST Bridges-Sokhna & Mahager | 60656018.52 | 54080509.31 | 0 | 54080509.31
Mivida BP#189 | Emaar pkg#189 ipc 23 | 23 | Mivida BP#18923 | 30858954.29 | 14242173.0845 | 11334411.03 | 25576584.1145
EGAT Injection | IPC09&10 TR48 | 9 | EGAT Injection9 | 645079.47 | 553542.7 | 0 | 553542.7
Katameya Creeks - RME | IPC 12 TR53 | 12 | Katameya Creeks - RME12 | 5318.22 | 4709.29 | 0 | 4709.29
Kattmeya Creeks Urban | IPC03TR0071 | 3 | Kattmeya Creeks Urban3 | 41136.72 | 36426.55 | 0 | 36426.55
Egyptian Exchange building | IPC14TR0039 | 14 | Egyptian Exchange building14 | 109001.62 | 96520.93 | 0 | 96520.93
ORA ZED-Ph 2-Pkgs A&D | ora zed ph2 ipc02 | 2 | ORA ZED-Ph 2-Pkgs A&D2 | 21711682.2 | 21766847.47 | 2589823.21 | 24356670.68
Alamein Coastal Road Bridge | Alamein L&L IPCFin |  | Alamein Coastal Road Bridge | 986396.2 | 814290 | 0 | 814290
NUCA R05 - Z02 | R05(2) ipc44 | 44 | NUCA R05 - Z0244 | 12139548.9 | 10677961.28 | 1397680.9 | 12075642.18
Port Said Port Silos | Silos supp.EUR ipc01 | 1 | Port Said Port Silos1 | 5539353.23 | 5982501.4522 | 0 | 5982501.4522
SOL Town PKG.220 | PKG#220-IPC5=6 | 5 | SOL Town PKG.2205 | 618792.62 | 1020348.63 | 0 | 1020348.63
South Dabaa Axis | IPC#003 | 3 | South Dabaa Axis3 | 985584 | 872734.53 | 0 | 872734.53
WADY EL-NATROUN BRIDGE(HST) | IPC no14.. | 14 | WADY EL-NATROUN BRIDGE(HST)14 | 1043040 | 212337.14 | 0 | 212337.14
TOSHKA MADKOUR | IPC1TR0083 | 1 | TOSHKA MADKOUR1 | 1127761.2 | 983613.269 | 0 | 983613.269
Central Capital | INV ( 3 ) Central Ca | 3 | Central Capital3 | 160704 | 151061.76 | 0 | 151061.76
U3 & U5 | IPC18TR0055 | 18 | U3 & U518 | 180942.4 | 156261.82 | 0 | 156261.82
EGAT Injection | IPC13TR0048 | 13 | EGAT Injection13 | 631336.15 | 536749.55 | 0 | 536749.55
U4,U8 Seashell Playa | IPC11TR0060 | 11 | U4,U8 Seashell Playa11 | 394380 | 340586.57 | 0 | 340586.57
EPICO 3 Facility | Eipico ipc 15 | 15 | EPICO 3 Facility15 | 41894786.25 | 29236255.9825 | 9828182.53 | 39064438.5125
Kayan Landscape | El ROUDA Final |  | Kayan Landscape | 45197888 | 22844380 | 20804601.2 | 43648981.2
Port Said Port Silos | port said ipc23 | 23 | Port Said Port Silos23 | 3587901.46 | 2851855.8684 | 358790.15 | 3210646.0184
Mivida BP#189 | pkg#189-IPC9 | 9 | Mivida BP#1899 | 42271935.1 | 39465389.045 | 4752382.96 | 44217772.005
ORA ZED - Ph 01B - Pkgs A&D | Ora ph.1 - IPC 22 | 22 | ORA ZED - Ph 01B - Pkgs A&D22 | 9997079.14 | 8609716.257 | 1021782.75 | 9631499.007
Maspiro Towers | Final |  | Maspiro Towers | 366600 | 182637.31 | 0 | 182637.31
Egat Rolling Mill no.4 | Rolling Mill ipc 15 | 15 | Egat Rolling Mill no.415 | 16836028.87 | 17509470.0248 | 0 | 17509470.0248
Rabigh PP - Piling Works | Inv-02 | 2 | Rabigh PP - Piling Works2 | 833736.43 | 2876390.67 | 0 | 958796.89
Cairo-Alex Railway | Cairo-alex Esc.20:41 |  | Cairo-Alex Railway | 53378141.9 | 33855194.7 | 0 | 33855194.7
Sokhna Port Expansion | SPX.2 ipc06 | 6 | Sokhna Port Expansion6 | 29655965.5 | 20436715.16 | 5931193.1 | 26367908.26
EGAT Mechanical Installations | Egat Mechnical ipc 4 | 4 | EGAT Mechanical Installations4 | 1192474.42 | 906161.31 | 298118.6161 | 1204279.9261
Irrigation Tank | IPC08TR0061 | 8 | Irrigation Tank8 | 14632.2 | 12618.37 | 0 | 12618.37
Qasr Rashwan Lot A | QASRRASHWAN A 1 |  | Qasr Rashwan Lot A | 14222820.57 | 28292815.4 | 0 | 28292815.4
SSC Suez Steel Company Project | L4283/2024 |  | SSC Suez Steel Company Project | 5000000 | 4450000 | 0 | 4450000
SSC Suez Steel Company Project | L 4291/2024 |  | SSC Suez Steel Company Project | 35000000 | 31150000 | 0 | 31150000
Abou Ghaleb Bridge | ABOGHALEBIPC21+22+23 | 21 | Abou Ghaleb Bridge21 | 12272074.19 | 11210771.93 | 0 | 11210771.93
Qasr Rashwan - Lot B | QASR RASHWAN B IPC1 | 1 | Qasr Rashwan - Lot B1 | 14763938.35 | 53919655.04 | 0 | 53919655.04
U4,U8 Seashell Playa | IPC17TR0060 | 17 | U4,U8 Seashell Playa17 | 413660.75 | 324493.78 | 0 | 324493.78
Irrigation Tank | IPC11TR0061 | 11 | Irrigation Tank11 | 821545.02 | 528535.34 | 0 | 528535.34
R05 (New) | IPC08TR0059 | 8 | R05 (New)8 | 252601 | 214230.91 | 0 | 214230.91
El Khatatba Bridge | el khatatba ipc05 | 5 | El Khatatba Bridge5 | 3556116.67 | 3052936.75 | 0 | 3052936.75
HST El Mahager Bridge | Elmahager esc.2:7 |  | HST El Mahager Bridge | 16043483.57 | 14216135.8443 | 0 | 14216135.8443
Seashell Playa 5 Villas | Playa - C470 ipc 2 | 2 | Seashell Playa 5 Villas2 | 23114.7 | 19961.84 | 0 | 19961.84
Ain Sokhna Bridge | Inv ( 6 ) A.S | 6 | Ain Sokhna Bridge6 | 333124.5 | 89916.11 | 0 | 89916.11
EPICO 3 Facility | Eipico ipc 18 | 18 | EPICO 3 Facility18 | 61115227.87 | 35188037.3 | 17000000 | 52188037.3
Roubiky Hassan Allam | IPC#4#Roubiky | 4 | Roubiky Hassan Allam4 | 498750 | 415957.5 | 0 | 415957.5
Lekela 250MW Wind Farm | LEKELA IPC2=4 | 2 | Lekela 250MW Wind Farm2 | 6153867.61 | 6400022.31 | 0 | 6400022.31
Rabigh PP - Piling Works | Inv-05 | 5 | Rabigh PP - Piling Works5 | 983150.55 | 3391869.39 | 0 | 1130623.13
El Khatatba Bridge | EL KHATBA ESC 1:12 |  | El Khatatba Bridge | 2221940 | 2145997.56 | 0 | 2145997.56
Abou Ghaleb Bridge | ABO GHALEB ESC 1:20 |  | Abou Ghaleb Bridge | 10360450.48 | 10007798.33 | 0 | 10007798.33
RADAMIS CITY | IPC06TR0084 | 6 | RADAMIS CITY6 | 236604.69 | 209513.46 | 0 | 209513.46
Damietta Container Termin | Damietta Pkg 3 ipc 1 | 1 | Damietta Container Termin1 | 1617841.39 | 1520770.9061 | 0 | 1520770.9061
EIPICO C002-23 | IPC11TR0068 | 11 | EIPICO C002-2311 | 45656.8 | 39178.09 | 0 | 39178.09
Irrigation Tank | IPC13TR0061 | 13 | Irrigation Tank13 | 956644.13 | 826157.86 | 0 | 826157.86
EGAT Injection | IPC08 TR48 | 8 | EGAT Injection8 | 42833.9 | 36755.76 | 0 | 36755.76
6 Octobar Stores | IPC01TR0072 | 1 | 6 Octobar Stores1 | 215768 | 60000 | 0 | 60000
Port Saad Industiral zone | IPC#3 | 3 | Port Saad Industiral zone3 | 5078250 | 4888354.75 | 0 | 4888354.75
Seashell Playa 5 Villas | Playa c470 ipc 5 | 5 | Seashell Playa 5 Villas5 | 165704.92 | 143102.76 | 0 | 143102.76
Seashell Playa 5 Villas | playa C469 IPC 8 | 8 | Seashell Playa 5 Villas8 | 75504.2 | 18980.64 | 0 | 18980.64
Seashell Playa 5 Villas | Playa c470 ipc 4 | 4 | Seashell Playa 5 Villas4 | 327640.22 | 265950.1 | 0 | 265950.1
Abo Ghaleb | IPC #1 Abo Ghaleb | 1 | Abo Ghaleb1 | 1116000 | 1007589.6 | 0 | 1007589.6
AL-JAWHARA PALACE | IPC02TR0095 | 2 | AL-JAWHARA PALACE2 | 41343.75 | 35352.85 | 0 | 35352.85
Roof-Playa Cluster A,B,C | IPC14TR0088 | 14 | Roof-Playa Cluster A,B,C14 | 484211.55 | 418165.09 | 0 | 418165.09
U4,U8 Seashell Playa | IPC20TR0060 | 20 | U4,U8 Seashell Playa20 | 193785.15 | 167352.86 | 0 | 167352.86
Suez Gulf Substation | 180082 |  | Suez Gulf Substation | -34750.14 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 9 EGP South Helwan |  | South Helwan PP (CP-117) | 306120.3143 | 0 | 0 | #DIV/0!
Kuwait | Cr.P-10-14 | 10 | Kuwait10 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | CN Semeins |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
El-Warraq | IPC4 elwaraq | 4 | El-Warraq4 | 198000 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 5001-3 | 3 | AWEER POWER STATION 'H' Phase3 | 20326473.22 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | Credit closing pip |  | Pyramids Industrial Park | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 60 |  | Suez Gulf Substation | 3367588.23 | 0 | 0 | #DIV/0!
Suez Gulf Substation | CR-Inv#180163 | 180163 | Suez Gulf Substation180163 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 94 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | CR - IPC#23 | 23 | El Boghaz Brigde23 | 0 | 0 | 0 | #DIV/0!
Toshka Farm | CR.Toshka Farm Inv.3 | 3 | Toshka Farm3 | 0 | 0 | 0 | #DIV/0!
Nagaa Hamady/Assuit OHTL | Soc.2020 تشيد سكرخط |  | Nagaa Hamady/Assuit OHTL | 5000 | 0 | 0 | #DIV/0!
Masr ELgedeeda | D0040-OB-Dec-2020/Cr | 2020 | Masr ELgedeeda2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 34 |  | Al-Shabab PP Phase II (CP-117) | 69952.76 | 0 | 0 | #DIV/0!
Hosh Essa 220 KV OHTL | Hosh Essa USD Inv.01 | 1 | Hosh Essa 220 KV OHTL1 | 148906.67 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 20 ) GET | 20 | Get Business Complex20 | 1252073.23 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 5 |  | Zafranaa - Ras Ghareb | 184627.45 | 0 | 0 | #DIV/0!
10th Ramadan Indu Park Plot11 | P-30-EGY اتحاد تشيد | 30 | 10th Ramadan Indu Park Plot1130 | 5000 | 0 | 0 | #DIV/0!
Railway Bridge - Assuit | final inv Assuit |  | Railway Bridge - Assuit | 834490 | 0 | 0 | #DIV/0!
Abo Shanab El Agamien | cr-abo shanab ipc01 | 1 | Abo Shanab El Agamien1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 11 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 191040 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | Zafra Souf Final7civ |  | Zafranaa - Beni Suef | 39761 | 0 | 0 | #DIV/0!
SSC Suez Steel Company Project | L965/2024 |  | SSC Suez Steel Company Project | 34361114 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180086 |  | Suez Gulf Substation | -314814.82 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 1907220003 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | IPC-3 | 3 | Taval Sarai 523 | 0 | 0 | 0 | #DIV/0!
Nagaa Hamady/Assuit OHTL | تجديد تشيد وبناء2020 |  | Nagaa Hamady/Assuit OHTL | 5250 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 64 |  | Al-Shabab PP Phase II (CP-117) | 43006715.6568 | 0 | 0 | #DIV/0!
Residence 8 ( S09 ) | Cr. Inv ( 1 ) S 09 | 1 | Residence 8 ( S09 )1 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | Pole.Cvr.Inv.1.Cncl | 1 | Ghana Street lighting1 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv12 | 12 | Akhmem - Qena12 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj.180132 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Residence 8 ( K10 ) | Inv ( 2 ) K 10 | 2 | Residence 8 ( K10 )2 | 125124.61 | 0 | 0 | #DIV/0!
Ministries Buildings | CR-MinistSHELLIPC08 | 8 | Ministries Buildings8 | 0 | 0 | 0 | #DIV/0!
Bahr ElBakar – Power Station | CR IPC#7 Madkour | 7 | Bahr ElBakar – Power Station7 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 66 |  | Al-Shabab PP Phase II (CP-117) | 3315761.7192 | 0 | 0 | #DIV/0!
Railway Bridge - Alex | Credit Memo FPC |  | Railway Bridge - Alex | 0 | 0 | 0 | #DIV/0!
Canal Sugar 33KV OHTL | Cr. 4 Sugar 33 OHTL |  | Canal Sugar 33KV OHTL | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | ipc no2 aswan | 2 | Aswan axis - Daraw2 | 529916 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2103220003 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr.Adj Inv. 18 | 18 | Zafranaa - Ras Ghareb18 | 0 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | 31 EGP-Giza Nor.III |  | Giza North PP Phase3(CP-117) | 613545.1238 | 0 | 0 | #DIV/0!
EMAAR-PKG#62-UPTOWN | OB-RE-PKG#62 |  | EMAAR-PKG#62-UPTOWN | 136616.41 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | CR ipc4 aswan | 4 | Aswan axis - Daraw4 | -431029.25 | 0 | 0 | #DIV/0!
Air Defence College | CAN. IPC26TR0046 | 26 | Air Defence College26 | 0 | 0 | 0 | #DIV/0!
Port Saad Industiral zone | CR-IPC#8 | 8 | Port Saad Industiral zone8 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | ENG 056 |  | AWEER POWER STATION 'H' Phase | 804156.68 | 0 | 0 | #DIV/0!
158E/2019 33kv Project | 11544 |  | 158E/2019 33kv Project | 203400 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_INV.10 | 10 | Akhmem Assiut10 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv-03 | 3 | MOC HQ at Diriyah3 | 4468396.86 | 0 | 0 | #DIV/0!
Almaza | Cr. Inv 02 | 2 | Almaza2 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | Cr -7-EGP-West D.117 | 7 | W Dam PP Phase II (CP-117)7 | 0 | 0 | 0 | #DIV/0!
Beni Suef Substation R61 | BSF-SW-EGP-12 FINAL | 12 | Beni Suef Substation R6112 | 8750 | 0 | 0 | #DIV/0!
Racecores 3092-16 132KV C | 11343 |  | Racecores 3092-16 132KV C | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 55 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180085 |  | Suez Gulf Substation | 873.48 | 0 | 0 | #DIV/0!
Port Said Grain Storage | Credit |  | Port Said Grain Storage | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Proj-CR Adj. Inv. 15 | 15 | Abou El Matameer and Sammanoud15 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 8 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1320080.7429 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/004Cnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2104210004 |  | Manshiet Nasser Substation | 130476.19 | 0 | 0 | #DIV/0!
Taval Sarai 52 | IPC-21-SARAY | 21 | Taval Sarai 5221 | 249351.7 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Cr. Inv. 27 Usd | 27 | Marsa Alam/ Bernes LOT2 OHTL27 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 19 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 415138.7619 | 0 | 0 | #DIV/0!
Sewage Treatment Plant | D0024-OB-Dec-2020/Cr | 2020 | Sewage Treatment Plant2020 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 6 Euro-South Helwan |  | South Helwan PP (CP-117) | 919171.0286 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180023 |  | Suez Gulf Substation | -336730.54 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply. Inv.5 Ret | 5 | Ghana Street lighting5 | 6457.52 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 470 |  | TZ – Offshore E&M Procurement | 1624155.5 | 0 | 0 | #DIV/0!
EL Baragil Bridge | inv ( 5 ) Baragill B | 5 | EL Baragil Bridge5 | 1052415 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 271 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
K047 FDH JV | CR.10-16(2) | 16 | K047 FDH JV16 | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 346 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Ref.1 samanud-mat T |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
Aswan- Belana 60K m³/day WWTP | 10225 |  | Aswan- Belana 60K m³/day WWTP | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | 10007 |  | El Boghaz Brigde | 401882.16 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH inv.32 deductions | 32 | South Helwan PP (CP-117)32 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 15 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 146711.5048 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | 7 |  | Barwa 2x60/22 KV S/S | 1280709.49 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 475 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref Akhmm Asuit2T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Almaza | Credit Retention |  | Almaza | 0 | 0 | 0 | #DIV/0!
10Th of Ramadan LRT | CR.10Ramadan Inv.02 | 2 | 10Th of Ramadan LRT2 | 0 | 0 | 0 | #DIV/0!
Bashteel - Tahya Masr Bridge | IPC#3# FINAL#TAHYA M | 3 | Bashteel - Tahya Masr Bridge3 | 1528500 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 468 |  | TZ – Offshore E&M Procurement | 0 | 0 | 0 | #DIV/0!
Port Said Grain Storage | credit ipc 11 | 11 | Port Said Grain Storage11 | -1014666 | 0 | 0 | #DIV/0!
El Salam Bridge | D0048 OB-Dec-2020/Cr | 2020 | El Salam Bridge2020 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 284 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Inv.5 Deductions | 5 | Assuit PP (CP-118)5 | 0 | 0 | 0 | #DIV/0!
PIP- Zonafranca | Cr Adj Inv 5 | 5 | PIP- Zonafranca5 | 0 | 0 | 0 | #DIV/0!
The Open Channel Project | OPEN CHANEL IPC 2 | 2 | The Open Channel Project2 | 125541216 | 0 | 0 | #DIV/0!
SHUQAIQ High Voltage Works | 2 |  | SHUQAIQ High Voltage Works | 2881950.1 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11661 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
El-Herafeen brigde | D0042-OB-Dec-2020/Cr | 2020 | El-Herafeen brigde2020 | 0 | 0 | 0 | #DIV/0!
U3 & U5 | CR-55/1 | 55 | U3 & U555 | 0 | 0 | 0 | #DIV/0!
Baron Palace | CR.TR0014CLOSING.DEC |  | Baron Palace | 0 | 0 | 0 | #DIV/0!
Closed | OB-ST |  | Closed | 0.89 | 0 | 0 | #DIV/0!
Suez Gulf Substation | CR-Closing #180162 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
EIPICO Factory | ipc05 tr0054 | 5 | EIPICO Factory5 | 0 | 0 | 0 | #DIV/0!
Elsewedy Univ - Enabling Works | CMsewedy uni-mep-07 | 7 | Elsewedy Univ - Enabling Works7 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 2104220007 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Algeria S/Ss | Cr.P-14-12 | 14 | Algeria S/Ss14 | 0 | 0 | 0 | #DIV/0!
Beni Suef COMCAVI | 1907220004 |  | Beni Suef COMCAVI | 0 | 0 | 0 | #DIV/0!
El-Warraq | CR IPC4 elwaraq | 4 | El-Warraq4 | -198000 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 254 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
New Capital | Credit inv5 El Tbeen | 5 | New Capital5 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 252 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | cr ( inv 5 ) ola | 5 | Al-Ula Towers5 | 0 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/003Cnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
U3 & U5 | TR55-CR3 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2008220003 |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
Attaqa Power Plant | Discount int. |  | Attaqa Power Plant | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Refund reten.closing |  | Zafranaa - Ras Ghareb | 39998.65 | 0 | 0 | #DIV/0!
Sodic East | 10113 |  | Sodic East | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2012210007 |  | Manshiet Nasser Substation | 16138.58 | 0 | 0 | #DIV/0!
New Heliopolis | Cancel inv. 7 | 7 | New Heliopolis7 | 0 | 0 | 0 | #DIV/0!
Berket Ghelion | Cr Adj Inv 7 | 7 | Berket Ghelion7 | 0 | 0 | 0 | #DIV/0!
K047 FDH JV | CR.p-10-16 | 10 | K047 FDH JV10 | 0 | 0 | 0 | #DIV/0!
U3 & U5 | TR055-Cr 1 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
HSR-6th of October | ipc 8 hsr | 8 | HSR-6th of October8 | 279040 | 0 | 0 | #DIV/0!
Infra Project 2524 | 2112210002 |  | Infra Project 2524 | 86140000 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | rev. ( 8 EGP-West D. |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Canal Sugar 33KV OHTL | Soc.2020 تشيدسكر 33 |  | Canal Sugar 33KV OHTL | 5000 | 0 | 0 | #DIV/0!
Katameya Creeks - RME | CREDITIPC15 | 15 | Katameya Creeks - RME15 | 0 | 0 | 0 | #DIV/0!
Canal Sugar OHTL | Inv.12 Fi Sugar OHTL | 12 | Canal Sugar OHTL12 | 258580.7 | 0 | 0 | #DIV/0!
Akhmem Assiut | Ref.soci 53-54 Asut | 54 | Akhmem Assiut54 | 1949254 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 89 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr - 2 USD - Shabab | 2 | Al-Shabab PP Phase II (CP-117)2 | 0 | 0 | 0 | #DIV/0!
Industria Sadat | Cr.Sadat Indust Inv3 | 3 | Industria Sadat3 | 0 | 0 | 0 | #DIV/0!
October Dry Port Railway | CR-ODP ipc03 | 3 | October Dry Port Railway3 | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | 2104220004 |  | Banha PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Benban 4 As El-Nakra 220 K.V | CR. 1 Final ElNokra |  | Benban 4 As El-Nakra 220 K.V | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-KAFR SHOKR1 |  | Kafr Shokr Bridge | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | Cr-egy exch Ipc1 | 1 | Egyptian Exchange Building1 | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-Kafr shokr-IPC02 | 2 | Kafr Shokr Bridge2 | 0 | 0 | 0 | #DIV/0!
EPICO 3 Facility | material ipc 3 | 3 | EPICO 3 Facility3 | 4910817.01 | 0 | 0 | 5156357.8605
Open Channel 2 | IPC02TR0099 | 2 | Open Channel 22 | 1537200 | 0 | 0 | 1537200
Abo Ghaleb | IPC#2#Abo Ghaleb | 2 | Abo Ghaleb2 | 1272000 | 0 | 0 | 1272000
Hosh Eisa Hospit. | IPC02TR0089 | 2 | Hosh Eisa Hospit.2 | 222500.25 | 0 | 0 | 222500.25
Open Channal | IPC01TR00074 | 1 | Open Channal1 | 322560 | 0 | 0 | 0
U7-SEASHELL | IPC12TR0064 | 12 | U7-SEASHELL12 | 24635.46 | 0 | 0 | 24635.46
PLAYA ROOF & Wet Areas | IPC00022 TR41 | 22 | PLAYA ROOF & Wet Areas22 | 254226.68 | 0 | 0 | 254226.68
Kemet Tower | INV ( 9 ) Kemet | 9 | Kemet Tower9 | 185120 | 0 | 0 | 185120
Al-Ula Towers | inv ( 4 ) final | 4 | Al-Ula Towers4 | 564113.41 | 0 | 0 | 592319.0805
U3 & U5 | TR0055 |  | U3 & U5 | 439984.49 | 0 | 0 | 439984.49
ORA ZED - Ph 01B - Pkgs A&D | ORA PH.1- IPC23 | 23 | ORA ZED - Ph 01B - Pkgs A&D23 | 27314036.02 | 0 | 0 | 28679737.821
Ministries Buildings | Mini Core IPC11 | 11 | Ministries Buildings11 | 27963228 | 0 | 0 | 27963228
Kayan 3 New Cairo Capital City | 30/11/22Armed Force |  | Kayan 3 New Cairo Capital City | 313092002.03 | 0 | 0 | 313092002.03
Assuit PP (CP-118) | 220721002 |  | Assuit PP (CP-118) | 688101.53 | 0 | 0 | 720868.27
Ghana Street lighting | MCBs inv. No.1 | 1 | Ghana Street lighting1 | 37125 | 0 | 0 | 37125
Ghana Street lighting | Pole. Cvr. Inv.1 | 1 | Ghana Street lighting1 | 11690 | 0 | 0 | 11690
LAYAN Substation | 11459 |  | LAYAN Substation | 204999.08 | 0 | 0 | 215249.034
Racecores 3092-17 132KV E | 11448 |  | Racecores 3092-17 132KV E | 6625.33 | 0 | 0 | 6625.33
Cairo Monorail - 6th October | IPC#7 - Monorail | 7 | Cairo Monorail - 6th October7 | 1271000 | 0 | 0 | 1271000
Assuit PP (CP-118) | 2110210003 |  | Assuit PP (CP-118) | 13996866.29 | 14556740.94 | 0 | 14556740.94
Ahl Misr P3 – Zamalek Sector | IPC#5 Zamalek | 5 | Ahl Misr P3 – Zamalek Sector5 | 193800 | 0 | 0 | 193800
R05 | IPC_1_R5 | 1 | R051 | 77798.38 | 0 | 0 | 77798.38
Kafr Shokr Bridge | Kafr Shokr - IPC02 | 2 | Kafr Shokr Bridge2 | 7001830.48 | 0 | 0 | 7351922.004
Street Lighting Fayoum | Fayoum Street Inv.01 | 1 | Street Lighting Fayoum1 | 32271820 | 24688585 | 0 | 26225338.33
ORA-ZED Towers01B | TR0029DEC.Closing |  | ORA-ZED Towers01B | 402666.55 | 0 | 0 | 402666.55
ElMarg | D0043-OB-Dec-2020 | 2020 | ElMarg2020 | 1093100 | 0 | 0 | 1093100
El Zagazig Railway P2 | D0044-OB-Dec-2020 | 2020 | El Zagazig Railway P22020 | 489480 | 0 | 0 | 489480
Baron Palace | TR0014DEC.Closing |  | Baron Palace | 25484.8 | 0 | 0 | 25484.8
Al-Kayan | TR0012DEC.Closing |  | Al-Kayan | 30861.52 | 0 | 0 | 30861.52
Port Saad Industiral zone | D0022-OB-Dec-2020 | 2020 | Port Saad Industiral zone2020 | 32210212.84 | 0 | 0 | 32210212.84
C5 Bridge 2 New Alamein | D0011-OB-Dec-2020 | 2020 | C5 Bridge 2 New Alamein2020 | 13334667.5 | 0 | 0 | 13334667.5
Almaza Bridge - Safir 2 | D0023-OB-Dec-2020 | 2020 | Almaza Bridge - Safir 22020 | 444300 | 0 | 0 | 444300
Ministries A13-A14 | IPC_3_RedSea | 3 | Ministries A13-A143 | 48401 | 0 | 0 | 48401
El Mostakbal City Project | مد وثيقة تامين P-76 | 76 | El Mostakbal City Project76 | 279055 | 0 | 0 | 279055
Manshiet Nasser Substation | 496 |  | Manshiet Nasser Substation | 851958.87 | 73380.4 | 137121.85 | 210502.25
LAYYAH CCPP | 473 |  | LAYYAH CCPP | 1233824 | 0 | 0 | 1233824
Maspiro Towers | IPC005 | 5 | Maspiro Towers5 | 556650 | 277111.8 | 0 | -279538.2
Suez Gulf Substation | 12 EGP - Suez Gulf |  | Suez Gulf Substation | 598540.9905 | 565621.24 | 62846.8 | 628468.04
Suez Gulf Substation | 19 EGP VO Progress |  | Suez Gulf Substation | 331289.87 | 313657.81 | 34850.87 | 348508.68
Manshiet Nasser Substation | 1903210014 |  | Manshiet Nasser Substation | 952380.95 | 990476.19 | 0 | 990476.19
Abu Qir PP (CP-117) | 1907210013 |  | Abu Qir PP (CP-117) | 17136.36 | 17136.36 | 0 | 17136.36
Suez Gulf Substation | 1909210010 |  | Suez Gulf Substation | 499195.28 | 499195.28 | 0 | 499195.28
Suez Gulf Substation | custom release inv. |  | Suez Gulf Substation | 3379.7 | 0 | 0 | 3379.7
Beni-Suef Power Plant EPC | reclass of rec acc |  | Beni-Suef Power Plant EPC | 986446760.8 | 986446760.8 | 0 | 986446760.8
Ain-Sokhna PP (CP-117) | 180137 |  | Ain-Sokhna PP (CP-117) | 28054.69 | 28251.08 | 0 | 28251.08
Beni-Suef Power Plant EPC | 14 Egp - Beni Suef |  | Beni-Suef Power Plant EPC | 178425894.88 | 52519653.75 | 0 | 118140371.3333
Beni-Suef Power Plant EPC | INV 11,12,13 | 11 | Beni-Suef Power Plant EPC11 | 373718132 | 355718132.02 | 0 | 355718132.02
Akhmem Assiut | Soc Inv 44 To 47 Asu | 44 | Akhmem Assiut44 | 2259485.5 | 0 | 0 | 2259485.5
EMAAR-PKG#53-UPTOWN | PKG#85/53- IPC5 | 5 | EMAAR-PKG#53-UPTOWN5 | 1941977.98 | 0 | 0 | 1941977.98
MAYSAN 400/132kV SS | Cancel Cr no. 227 |  | MAYSAN 400/132kV SS | 87293.1 | 0 | 0 | 87293.1
Algeria S/Ss | P-14-12 ADJ | 14 | Algeria S/Ss14 | 5381425.43 | 0 | 0 | 5381425.43
Angola Emergency fast-track | P-13-2016 ADJ | 13 | Angola Emergency fast-track13 | 213247445.16 | 0 | 0 | 213247445.16
Cameron EDC | 5007 ADJ |  | Cameron EDC | 158805.85 | 0 | 0 | 158805.85
W Dam PP Phase II (CP-117) | 180097 |  | W Dam PP Phase II (CP-117) | 204014.88 | 182425.78 | 32192.78 | 214618.56
South Helwan PP (CP-117) | 180160 |  | South Helwan PP (CP-117) | 474288.1 | 474288.1 | 0 | 474288.1
W Dam PP Phase II (CP-117) | DM for wrong CR |  | W Dam PP Phase II (CP-117) | 368421.1 | 368421.1 | 0 | 368421.1
W Dam PP Phase II (CP-117) | 14 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 15152.72 | 15152.72 | 0 | 15152.72
South Helwan PP (CP-117) | 180159 |  | South Helwan PP (CP-117) | 10765415.4579 | 10765415.4579 | 0 | 10765415.4579
W Dam PP Phase II (CP-117) | 5 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 1559713.65 | 0 | 0 | 1637699.3325
Al-Shabab PP Phase II (CP-117) | 180101 |  | Al-Shabab PP Phase II (CP-117) | 763512.3 | 682716.51 | 120479.38 | 803195.89
Al-Shabab PP Phase II (CP-117) | 9 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 87501.91 | 0 | 0 | 87501.91
Zafranaa - Beni Suef | Adj. Inv. 13 | 13 | Zafranaa - Beni Suef13 | 10668740.42 | 0 | 0 | 10668740.42
Abo Quir - Badr 500KV | Adj. Inv. 12 | 12 | Abo Quir - Badr 500KV12 | 936845184.82 | 0 | 0 | 936845184.82
Almaza | Adj Inv 11 | 11 | Almaza11 | 57111431.15 | 0 | 0 | 57111431.15
IRAQ - Al-Diwaniya Power Plant | Adjust |  | IRAQ - Al-Diwaniya Power Plant | 2.48 | 2.48 | 0 | 2.48
Al-Shabab PP Phase II (CP-117) | 180128 |  | Al-Shabab PP Phase II (CP-117) | 112317.65 | 0 | 0 | 112317.65
Siemens 6x500/220 KV GIS-MOU | Inv 92 P14 Assuit | 92 | Siemens 6x500/220 KV GIS-MOU92 | 2399962.85 | 0 | 0 | 2399962.85
Cairo Capital S1 | Inv. 1 S1 | 1 | Cairo Capital S11 | 66935348.57 | 0 | 0 | 66935348.57
Cairo South PP Rehabilitation | 17 |  | Cairo South PP Rehabilitation | 4211339 | 0 | 0 | 4211339
Beni Suef ISKRA | 180114 |  | Beni Suef ISKRA | 59610.29 | 0 | 0 | 59610.29
Abu Qir PP (CP-118) | 29 |  | Abu Qir PP (CP-118) | 505247.8464 | 0 | 0 | 505247.8464
Al-Shabab PP Phase II (CP-117) | 180027 |  | Al-Shabab PP Phase II (CP-117) | 150713.9429 | 0 | 0 | 158249.64
Ain-Sokhna PP(CP-102) | 115 |  | Ain-Sokhna PP(CP-102) | -456119.6566 | 0 | 0 | -456119.6566
GPC-Gupco (Automation) | 102 |  | GPC-Gupco (Automation) | 536503 | 0 | 0 | 536503
Banha PP (CP-117) | 72 |  | Banha PP (CP-117) | 4796013 | 0 | 0 | 4796013
Abu Qir PP (CP-117) | 92 |  | Abu Qir PP (CP-117) | 37084218.9299 | 0 | 0 | 37084218.9299
Giza North PP Ph I,II (CP-117) | 86 |  | Giza North PP Ph I,II (CP-117) | -32558726.54 | 0 | 0 | -32558726.54
Ain-Sokhna PP (CP-111) | 25 |  | Ain-Sokhna PP (CP-111) | 14463227 | 0 | 0 | 14463227
Palm Hill-Infra Str(Elec.Work) | 80 |  | Palm Hill-Infra Str(Elec.Work) | 1990286.4 | 0 | 0 | 1990286.4
W Dam PP Phase II (CP-117) | 180091 |  | W Dam PP Phase II (CP-117) | 91387.21 | 81716.51 | 14420.56 | 96137.07
W Dam PP Phase II (CP-117) | 76 |  | W Dam PP Phase II (CP-117) | 25302754.0435 | 0 | 0 | 25302754.0435
W Dam PP Phase II (CP-117) | 43 |  | W Dam PP Phase II (CP-117) | 1462827.83 | 0 | 0 | 1462827.83
W Dam PP Phase II (CP-117) | 46 |  | W Dam PP Phase II (CP-117) | 34268600.208 | 0 | 0 | 34268600.208
Akhmem - Qena | Inv. 9 Akhmem Qena | 9 | Akhmem - Qena9 | 42408814.91 | 0 | 0 | 42408814.91
New Capital | Inv 7 Abo Zaabl | 7 | New Capital7 | 2859712.238 | 0 | 0 | 2859712.238
Abou El Matameer and Sammanoud | Soc73 abo almatamer |  | Abou El Matameer and Sammanoud | 217153.6 | 0 | 0 | 217153.6
W Dam PP Phase II (CP-117) | 4 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 117410.219 | -63008.75 | 18492.11 | 123280.73
Suez Gulf Substation | 4 USD/123/2011/2012 |  | Suez Gulf Substation | 78991.25 | 0 | 0 | 78991.25
Cameron EDC | 015/2019 |  | Cameron EDC | 153779165.65 | 153779165.65 | 0 | 153779165.65
Kuwait | Civil/H010 |  | Kuwait | 17126.78 | 12845.09 | 0 | 12845.09
Kuwait | Other Charge/H003 |  | Kuwait | 10656.5 | 6926.72 | 0 | 6926.72
Kuwait | Other Charge/H002 |  | Kuwait | 160091.58 | 104059.53 | 0 | 104059.53
Kuwait | 32-132KVA-H | 132 | Kuwait132 | 35058.07 | 26293.55 | 0 | 26293.55
Al-Shabab PP Phase II (CP-117) | 539 |  | Al-Shabab PP Phase II (CP-117) | 3454947.4 | 3290417.99 | 593819.09 | 3884237.08
W Dam PP Phase II (CP-117) | 180093 |  | W Dam PP Phase II (CP-117) | 490500.23 | 438594.9 | 77399.1 | 515994
W Dam PP Phase II (CP-117) | 18 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 415138.7524 | 0 | 65384.35 | 65384.35
Al-Shabab PP Phase II (CP-117) | 10 USD - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 1159738.7714 | 0 | 0 | 182658.86
W Dam PP Phase II (CP-117) | 2 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 4486255.0593 | 0 | 681013.52 | 4540090.12
Suez Gulf Substation | 9 EGP - Suez Gulf |  | Suez Gulf Substation | 1870441.4095 | 1767567.13 | 196396.35 | 1963963.48
Suez Gulf Substation | 5 USD/123/2011/2012 |  | Suez Gulf Substation | 1610862.93 | 0 | 0 | 1610862.93
Barwa 2x60/22 KV S/S | Inv. Barwa 36 |  | Barwa 2x60/22 KV S/S | 1878094 | 1327624.65 | 281714.11 | 1609338.76
Barwa 2x60/22 KV S/S | Barwa 32 |  | Barwa 2x60/22 KV S/S | 361862.04 | 255985.36 | 54279.31 | 310264.67
Barwa 2x60/22 KV S/S | Inv 20 Barwa | 20 | Barwa 2x60/22 KV S/S20 | 1126765.28 | 796961.01 | 169014.8 | 965975.81
Damac 2x60/22 KV S/S | Inv. 34 Damac | 34 | Damac 2x60/22 KV S/S34 | 1035314.67 | 732199.48 | 155297.2 | 887496.68
South Helwan PP (CP-117) | 3 Euro- South Helwan |  | South Helwan PP (CP-117) | 2295948.56 | 344392.28 | 0 | 2410745.988
South Helwan PP (CP-117) | 9 EGP - South Helwan |  | South Helwan PP (CP-117) | 306120.3143 | 0 | 0 | 321426.33
South Helwan PP (CP-117) | 7 EGP South Helwan |  | South Helwan PP (CP-117) | 59582.1048 | 62561.21 | 0 | 62561.21
W Dam PP Phase II (CP-117) | 9 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 83661 | 12549.15 | 0 | 12549.15
Al-Shabab PP Phase II (CP-117) | 2 EGP - East Delta |  | Al-Shabab PP Phase II (CP-117) | 81321.502 | 69952.76 | 12344.6 | 82297.36
South Helwan PP (CP-117) | 11 Euro-South Helwan |  | South Helwan PP (CP-117) | 178521.4381 | 187447.51 | 0 | 187447.51
Al-Wukair 11 Substation | inv(ESC-SA-Civil-04) | 4 | Al-Wukair 11 Substation4 | 3479489.42 | 3131540 | 0 | 3131540
Al-Wukair 11 Substation | close unappl.sak |  | Al-Wukair 11 Substation | 5953437 | 5953437 | 0 | 5953437
Bani Suef Old Substation | (16) bani suf 2 |  | Bani Suef Old Substation | 20050269.42 | 9400122.62 | 8412274.32 | 17812396.94
Beni Suef Substation R61 | BSF-CW-EURO-07 | 7 | Beni Suef Substation R617 | 190702.25 | 141119.67 | 28605.34 | 169725.01
Ismailiya East Substation | ISE-CW-EGP-18 | 18 | Ismailiya East Substation18 | 4228827 | 3129331.98 | 634324.05 | 3763656.03
Tamey El-amdeed Substation | TAM-SW-EGP-09 | 9 | Tamey El-amdeed Substation9 | 743750 | 546530.01 | 111562.5 | 658092.51
Tamey El-amdeed Substation | TAM-CW-EGP-14 | 14 | Tamey El-amdeed Substation14 | 2825630.53 | 2090966.59 | 423844.58 | 2514811.17
Beni Suef Substation R61 | BSF-CW-12 | 12 | Beni Suef Substation R6112 | 1706896 | 1271637.52 | 256034.4 | 1527671.92
Beni Suef Substation R61 | BSF-CW-11 | 11 | Beni Suef Substation R6111 | 616504 | 459295.48 | 92475.6 | 551771.08
Beni Suef COMCAVI | 180116 |  | Beni Suef COMCAVI | 1064503.13 | 904573.8 | 159929.33 | 1064503.13
Berket Ghelion | Inv.20 Ghelion | 20 | Berket Ghelion20 | 2159222.36 | 1289715.1 | 539805.61 | 1829520.71
New Giza 2 | (25)new giza 2 |  | New Giza 2 | 3460724 | 5457989.56 | 726752.09 | 6184741.65
Giza North PP Ph I,II (CP-117) | Inv 41 Giza I,II | 41 | Giza North PP Ph I,II (CP-117)41 | 37658.6381 | 39541.57 | 0 | 39541.57
Giza North PP Phase3(CP-117) | 31 EGP - Giza N. III |  | Giza North PP Phase3(CP-117) | 613545.1238 | 547589.01 | 0 | 547589.01
Beni Seuf - 358 | Inv. 18 Oewon Mousa | 18 | Beni Seuf - 35818 | 7444976.6 | 0 | 1280375.85 | 1280375.85
Beni Seuf - 358 | Inv. 5 Oewon Mousa | 5 | Beni Seuf - 3585 | 18196108.24 | 12555353.5 | 3093299.6 | 15648653.1
Beni Seuf - 358 | Inv. 4 Oewon Mousa | 4 | Beni Seuf - 3584 | 10374574.63 | 7187026.67 | 1735107.52 | 8922134.19
Barwa and Damac 220 OHTL | Inv No6 Wattanya220 | 6 | Barwa and Damac 220 OHTL6 | 5207897.62 | 3892503.6 | 781184.97 | 4673688.57
K047 FDH JV | Inv. NO.9 KWT Floor | 9 | K047 FDH JV9 | 86916.94 | 78225.24 | 0 | 78225.24
EMAAR-PKG#62-UPTOWN | (3)PKG#62 |  | EMAAR-PKG#62-UPTOWN | 2148477 | 1345054.04 | 773773.99 | 2118828.03
Bani Suef Old Substation | (12) BENI SUIF1 |  | Bani Suef Old Substation | 1145904 | 993957.12 | 114590.41 | 1108547.53
Closed | (2)shobra/banha |  | Closed | 459012 | 413932.49 | 0 | 413932.49
Suez Gulf Substation | Inv No 2 Suez Gulf | 2 | Suez Gulf Substation2 | 390457.1429 | 409980 | 0 | 409980
W Dam PP Phase II (CP-117) | 11 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 159164.381 | 142054.21 | 25068.39 | 167122.6
Beni Suef Substation R61 | beni suif 2 (1) |  | Beni Suef Substation R61 | 16367759.65 | 16367759.65 | 0 | 16367759.65
South Helwan PP (CP-117) | 2009210010 |  | South Helwan PP (CP-117) | 591337.4 | 202896.33 | 413028.9 | 615925.23
South Helwan PP (CP-117) | 1905210001 |  | South Helwan PP (CP-117) | 170823.56 | 143512.05 | 25623.53 | 169135.58
South Helwan PP (CP-117) | 1902210004 |  | South Helwan PP (CP-117) | 104612.25 | 109029.61 | 0 | 109029.61
Apache Electrical Works | Apachi Inv No PC,21 |  | Apache Electrical Works | 29512.94 | 29512.94 | 0 | 29512.94
Apache Electrical Works | Apachi Inv No P.C#20 | 20 | Apache Electrical Works20 | 90792.85 | 90792.85 | 0 | 90792.85
El Amal Bridge | 19100047 |  | El Amal Bridge | 2850725 | 1178671.7 | 1178000 | 2356671.7
Abu Qir PP (CP-118) | Inv Rent Abu quir |  | Abu Qir PP (CP-118) | 37884.13 | 37884.13 | 0 | 37884.13
Kuwait | 1-132KVA-H | 132 | Kuwait132 | 136683.654 | 102512.74 | 0 | 102512.74
Siemens 6x500/220 KV GIS-MOU | Inv 64 P6 Assuit | 64 | Siemens 6x500/220 KV GIS-MOU64 | 4291540.811 | 3104500.631 | 643731.12 | 3748231.751
Ministries Buildings | alloccation ipc10 | 10 | Ministries Buildings10 | 3632523 | 3232945.47 | 0 | 3232945.47
Mohamed Ali Palace Restoration | mohamed aly ipc06 | 6 | Mohamed Ali Palace Restoration6 | 3655924.33 | 956829.8465 | 2294711.4 | 3251541.2465
Akhmem - Qena | Inv.1 Quna Akhmem | 1 | Akhmem - Qena1 | 129881572.05 | 77279535.3625 | 19482235.81 | 96761771.1725
Al-Shabab PP Phase II (CP-117) | refund CSI - SH |  | Al-Shabab PP Phase II (CP-117) | 11687 | 11687 | 0 | 11687
EMAAR-PKG#62-UPTOWN | (8) pkg#62 |  | EMAAR-PKG#62-UPTOWN | 3910757 | 3300873.4 | 1899641.41 | 5200514.81
Ghana | 36/P/10/ER/2017/USD |  | Ghana | 590122.61 | 590108.11 | 0 | 590108.11
Abou El Matameer and Sammanoud | Inv 97 P14Abo Matami | 97 | Abou El Matameer and Sammanoud97 | 3595740.3948 | 2583179.9048 | 539361.06 | 3122540.9648
Abou El Matameer and Sammanoud | Inv 91P11Abo Matami | 91 | Abou El Matameer and Sammanoud91 | 1798421.83 | 1300978.35 | 269763.28 | 1570741.63
Military 110 Kayan Project | Inv. 7 Elkayan | 7 | Military 110 Kayan Project7 | 77825867.69 | 70626580.75 | 0 | 70626580.75
Badr | Inv. 25 Badr | 25 | Badr25 | 8876075.73 | 6106319.35 | 1331411.38 | 7437730.73
Beni Suef Substation R61 | (3)cw beni suif |  | Beni Suef Substation R61 | 4371751.46 | 3256954.83 | 655762.72 | 3912717.55
Suez Gulf Substation | 15EGP/on-shore train |  | Suez Gulf Substation | 104823.8095 | 99058.5 | 11006.5 | 110065
Al Mostathmreen GIS Substation | 20sd elmostsmrin |  | Al Mostathmreen GIS Substation | 2595288 | 1933489.56 | 389293.2 | 2322782.76
Ministries Buildings | MIN.ELECTRO-IPC01 | 1 | Ministries Buildings1 | 71805669.2 | 47786690 | 4754005.45 | 52540695.45
Assuit PP (CP-118) | 2108210006 |  | Assuit PP (CP-118) | 1881270.96 | 1624840.3 | 296300.18 | 1921140.48
Assuit PP (CP-118) | 2108210002 |  | Assuit PP (CP-118) | 263386.67 | 230068.25 | 41483.4 | 271551.65
Assuit PP (CP-118) | 1905210008 |  | Assuit PP (CP-118) | 2656403.42 | 2344276.02 | 418383.54 | 2762659.56
Assuit PP (CP-118) | 1908210003 |  | Assuit PP (CP-118) | 62135.66 | 55456.07 | 9786.37 | 65242.44
Marsa Matrouh 500KV | Inv.48 Borg Alarab | 48 | Marsa Matrouh 500KV48 | 5514081.46 | 4816553.89 | 578978.55 | 5395532.44
K047 FDH JV | Inv. No.12 KWD Floor | 12 | K047 FDH JV12 | 110152.48 | 99137.22 | 0 | 99137.22
SHATRA 400/132kV SS | 203 |  | SHATRA 400/132kV SS | 4640388.65 | 0 | 0 | 0
kayan wall lock & Load | 19100015 |  | kayan wall lock & Load | 9720000 | 7568893 | 550000 | 8118893
New Giza 2 | new giza2 vo-ipc1 | 1 | New Giza 21 | 651117.59 | 613678.3295 | 0 | 613678.3295
Kayan 3 New Cairo Capital City | ELKAYAM MEP-IPC (2) | 2 | Kayan 3 New Cairo Capital City2 | 54383758.5 | 39352862.65 | 10000000 | 49352862.65
Al Mostathmreen GIS Substation | 12 sd euro mostsmrin |  | Al Mostathmreen GIS Substation | 278712.16 | 202066.32 | 41806.82 | 243873.14
Ministries Buildings | MIN-OLD-IPC05 | 5 | Ministries Buildings5 | 8139701.5 | 0 | 7264287.16 | 7264287.16
Apache Electrical Works | Apachi Inv No PC.#27 |  | Apache Electrical Works | 380181.56 | 380181.56 | 0 | 380181.56
Lina Farm Substation | Green power balance |  | Lina Farm Substation | 126891.55 | 126891.55 | 0 | 126891.55
Siemens 6x500/220 KV GIS-MOU | soc 12 siemen assuit |  | Siemens 6x500/220 KV GIS-MOU | 69984.65 | 69984.65 | 0 | 69984.65
Akhmem Assiut | Inv.15 Assuit Akhmem | 15 | Akhmem Assiut15 | 40987975.56 | 24387845.46 | 6148196.33 | 30536041.79
Suez Gulf Substation | Inv 1 VO SG | 1 | Suez Gulf Substation1 | 309523.8095 | 292500 | 32500 | 325000
Royal City | IPC8-ROYAL CITY | 8 | Royal City8 | 7514576.65 | 6396986.1725 | 1211103.24 | 7608089.4125
Kuwait | 34-132KVA(8J) | 132 | Kuwait132 | 108631.37 | 70610.39 | 0 | 70610.39
Kuwait | 33-132KVA(8H) | 132 | Kuwait132 | 108631.37 | 70610.39 | 0 | 70610.39
Akhmem - Qena | Inv.8 Qena - Akhmem$ | 8 | Akhmem - Qena8 | 2209137.55 | 1876320.38 | 0 | 1876320.38
Akhmem - Qena | Inv. 40 Akhmem Qena | 40 | Akhmem - Qena40 | 3352844.51 | 2330226.93 | 502926.68 | 2833153.61
P-28-16 Balat Owinat Lot 3 | Inv. 16 Balat lot 3 | 16 | P-28-16 Balat Owinat Lot 316 | 1076785.84 | 705823.98 | 0 | 705823.98
Akhmem Assiut | Inv.6 Assuit Akhmem$ | 6 | Akhmem Assiut6 | 540926.3 | 459353.32 | 0 | 459353.32
R5 Mix-Use Complex Project | R05-ZONE01-IPC03 | 3 | R5 Mix-Use Complex Project3 | 9108844 | 9530950.57 | 1168656.18 | 10699606.75
Akhmem Assiut | Inv.30 Assuit Akhmem | 30 | Akhmem Assiut30 | 1580001.39 | 1256101.11 | 237000.21 | 1493101.32
Akhmem - Qena | Inv. 41 Akhmem Qena | 41 | Akhmem - Qena41 | 2794311.34 | 1382655.21 | 419146.7 | 1801801.91
Akhmem - Qena | Inv.29 Akhmem Qena | 29 | Akhmem - Qena29 | 790778.03 | 628668.54 | 118616.7 | 747285.24
Marsa Matrouh 500KV | Inv.3 Borg Alarab | 3 | Marsa Matrouh 500KV3 | 10523603.44 | 10523603.44 | 0 | 10523603.44
Lina Farm Substation | 4 EGP - Lina |  | Lina Farm Substation | 2894707.22 | 2894707.22 | 0 | 2894707.22
Canal Regional Control Center | Inv.1 RCC | 1 | Canal Regional Control Center1 | 6034785.3 | 4018565.62 | 1267304.91 | 5285870.53
Tamey El-amdeed Substation | TAM-CW-EGP-07 | 7 | Tamey El-amdeed Substation7 | 2823851.52 | 2103769.38 | 423577.73 | 2527347.11
Al Mostathmreen GIS Substation | MOS-SD-EGP-21 | 21 | Al Mostathmreen GIS Substation21 | 270269.6 | 201350.85 | 40540.44 | 241891.29
Royal City | ROYAL ZONE-IPC09 | 9 | Royal City9 | 6296215.04 | 5296379.022 | 1429157.65 | 6725536.672
Ismalia Bridge | ISMAILIA BLAJT-IPC03 | 3 | Ismalia Bridge3 | 16962557.79 | 6056328.15 | 5204469.36 | 17008301.51
South Helwan PP (CP-117) | 180147 |  | South Helwan PP (CP-117) | 233646.38 | 244575.79 | 0 | 244575.79
Akhmem Assiut | Ref Ret. Inst 2 Asut |  | Akhmem Assiut | 18342857.27 | 18342328.37 | 0 | 18342328.37
EMAAR-PKG#53-UPTOWN | PKG#53-IPC-36 | 36 | EMAAR-PKG#53-UPTOWN36 | 1983817.89 | 3652834.8365 | 0 | 3652834.8365
Marsa Matrouh 500KV | Inv13 Usd borg alarb | 13 | Marsa Matrouh 500KV13 | 9224.32 | 6559.22 | 968.55 | 7527.77
AWEER POWER STATION 'H' Phase | CON/029 |  | AWEER POWER STATION 'H' Phase | 266187.22 | 233653.22 | 29576.36 | 263229.58
AWEER POWER STATION 'H' Phase | IMP/066 |  | AWEER POWER STATION 'H' Phase | 871641.16 | 256649.8977 | 96849.02 | 353498.9177
AWEER POWER STATION 'H' Phase | CON/019 |  | AWEER POWER STATION 'H' Phase | 425899.55 | 373845.1575 | 47322.17 | 421167.3275
AWEER POWER STATION 'H' Phase | Loc-009 | 9 | AWEER POWER STATION 'H' Phase9 | 1022976.47 | 1011610.07 | 0 | 1011610.07
AWEER POWER STATION 'H' Phase | IMP047-39 | 39 | AWEER POWER STATION 'H' Phase39 | 2089097.1 | 2068848.77 | 0 | 2068848.77
AWEER POWER STATION 'H' Phase | Con/009 |  | AWEER POWER STATION 'H' Phase | 558993.16 | 490671.77 | 62110.35 | 552782.12
AWEER POWER STATION 'H' Phase | 10137 |  | AWEER POWER STATION 'H' Phase | 1278118.38 | 376334.479 | 887582.56 | 1263917.039
Marsa Matrouh 500KV | Inv. 9 Borg Alarab | 9 | Marsa Matrouh 500KV9 | 87830687.53 | 62019089.46 | 9222222.19 | 71241311.65
New Heliopolis | Inv. 10 Heliopolise | 10 | New Heliopolis10 | 10052362 | 7984172.7 | 987141.95 | 8971314.65
Tamey El-amdeed Substation | TAM-SW-EGP-02 | 2 | Tamey El-amdeed Substation2 | 980000 | 725200 | 147000 | 872200
EMAAR-PKG# 144, Marassi | PKG#144 -IPC3 | 3 | EMAAR-PKG# 144, Marassi3 | 6872046.63 | 6189125.0415 | 3180859.94 | 9369984.9815
EMAAR-PKG# 101-UPTOWN | PKG#101 - IPC07 | 7 | EMAAR-PKG# 101-UPTOWN7 | 3491880.84 | 1988552.05 | 1042992.41 | 3031544.46
EMAAR-PKG# 101-UPTOWN | PKG#101-IPC-01 | 1 | EMAAR-PKG# 101-UPTOWN1 | 1738465.67 | 1029594.8135 | 547616.69 | 1577211.5035
4 SS - Technical Service | 215 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
EMAAR-PKG#53-UPTOWN | 19100002 |  | EMAAR-PKG#53-UPTOWN | 1237230.98 | 1753673.249 | 0 | 1753673.249
Elsewedy Univ - Enabling Works | 19100017 |  | Elsewedy Univ - Enabling Works | 1734033.5 | 1204112.855 | 546220.55 | 1750333.405
DPW Onshore Port & Terminal | DP WORLD -IPC10 | 10 | DPW Onshore Port & Terminal10 | 90533235.47 | 66994289.3 | 13579985.32 | 80574274.62
DPW Onshore Port & Terminal | DP WORLD-IPC008 | 8 | DPW Onshore Port & Terminal8 | 39363674.81 | 29128813.98 | 5904551.22 | 35033365.2
DPW Onshore Port & Terminal | DP World IPC030 | 30 | DPW Onshore Port & Terminal30 | 14579181.6 | 10739490.38 | 2186877.24 | 12926367.62
DPW Onshore Port & Terminal | DPW IPC027 | 27 | DPW Onshore Port & Terminal27 | 21307969.76 | 15718793.62 | 3196195.46 | 18914989.08
Closed | (1) shobra/banha |  | Closed | 407864 | 234380.8 | 0 | 234380.8
Zafranaa - Ras Ghareb | ref. reten.zafra gha |  | Zafranaa - Ras Ghareb | 9785281.7 | 9785281.7 | 0 | 9785281.7
Akhmem Assiut | Soc Inv 34To37 Asuit | 34 | Akhmem Assiut34 | 1017697.8 | 1017697.8 | 0 | 1017697.8
Akhmem Assiut | Soc Inv 20-21 Asuit | 20 | Akhmem Assiut20 | 802370.5 | 802370.5 | 0 | 802370.5
Ministries Buildings | MINISTRIY SHELL-IPC1 | 1 | Ministries Buildings1 | 111319928.44 | 42783984 | 54507678.25 | 97291662.25
HAC CCC JV | IPC#10 | 10 | HAC CCC JV10 | 1144744.5 | 1043263.01 | 0 | 1043263.01
EMAAR- Pkg 140-ITP-Mivida | PKG#140 - IPC03 | 3 | EMAAR- Pkg 140-ITP-Mivida3 | 6247225.23 | 4070832.4 | 1894295.14 | 5965127.54
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC01 | 1 | EMAAR- Pkg 140-ITP-Mivida1 | 4797449.52 | 2533668.016 | 1906611.38 | 4440279.396
Assuit PP (CP-118) | 1901210009 |  | Assuit PP (CP-118) | 173380.07 | 154741.71 | 27307.36 | 182049.07
New Capital | Inv. 8 Eltbeen | 8 | New Capital8 | 150157.14 | 139770.72 | 0 | 139770.72
Ministries Buildings | MIN-SHELL-IPC06 | 6 | Ministries Buildings6 | 6523952.65 | 4122020 | 1374009.35 | 5496029.35
Suez Road Tunnel RES | SUEZ ROADL&L- FINAL |  | Suez Road Tunnel RES | 1959389.44 | 1311260 | 437087.5 | 1748347.5
EMAAR-PKG# 144, Marassi | PKG#144 -IPC06 | 6 | EMAAR-PKG# 144, Marassi6 | 24446048.93 | 14929446.3565 | 7662957.19 | 22592403.5465
Mauritania Lot 1 | Inv.6 - Lot 1 | 6 | Mauritania Lot 16 | 485571.01 | 461277.45 | 0 | 461277.45
El Boghaz Brigde | IPC#19 | 19 | El Boghaz Brigde19 | 1512327.9 | 1399517.22 | 0 | 1399517.22
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 11 | 11 | Benban 500 K.V/95 K.M11 | 466471.68 | 359656.9 | 48979.53 | 408636.43
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 2 | 2 | Benban 500 K.V/95 K.M2 | 24071994.55 | 18558911.74 | 2527559.43 | 21086471.17
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 2 | 2 | Benban 500 K.V / 100 K.M2 | 69743781.24 | 53771861.26 | 7323097.03 | 61094958.29
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 7 | 7 | Benban 500 K.V / 100 K.M7 | 26539062.6 | 20461620.83 | 2786601.57 | 23248222.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 3 | 3 | Benban 500 K.V / 100 K.M3 | 1353959.24 | 1043307.55 | 142165.72 | 1185473.27
EMAAR-PKG#53-UPTOWN | PKG#53 -IPC38 | 38 | EMAAR-PKG#53-UPTOWN38 | 217725.59 | 841731.1795 | 0 | 841731.1795
Elco Steel 220/33 KV SS | 1903210011 |  | Elco Steel 220/33 KV SS | 15713070.57 | 16498724.1 | 0 | 16498724.1
Elco Steel 220/33 KV SS | 1901210003 |  | Elco Steel 220/33 KV SS | 4532833.5 | 4759475.18 | 0 | 4759475.18
Phosfat | Inv.6 Phosfat II | 6 | Phosfat6 | 1426885 | 1201754.75 | 0 | 1201754.75
Beni-Suef Power Plant EPC | coll of beni suef ga |  | Beni-Suef Power Plant EPC | 158808 | 158808 | 0 | 158808
El Boghaz Brigde | IPC#20 | 20 | El Boghaz Brigde20 | 1241851.62 | 968113.12 | 0 | 968113.12
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 8USD | 8 | Benban 500 K.V / 100 K.M8 | 30502.13 | 22419.07 | 6405.45 | 28824.52
Benban 500 K.V / 100 K.M | Benban Lot1 Inv12USD | 12 | Benban 500 K.V / 100 K.M12 | 72994.38 | 61315.28 | 7664.41 | 68979.69
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 7USD | 7 | Benban 500 K.V / 100 K.M7 | 237904.83 | 199840.06 | 24980.01 | 224820.07
Akhmem Assiut | Social 44-47 Assuit | 47 | Akhmem Assiut47 | 2259485.5 | 2259485.5 | 0 | 2259485.5
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 1 | 1 | Benban 500 K.V/95 K.M1 | 211577781.63 | 163120869.42 | 22215667.07 | 185336536.49
Manshiet Nasser Substation | Civil5 to Shipp 5 |  | Manshiet Nasser Substation | 0 | -254029.86 | 0 | -254029.86
Military 110 Kayan Project | Elkayan Inv.17 | 17 | Military 110 Kayan Project17 | 4361899.16 | 3761744.4 | 0 | 3761744.4
Abou El Matameer and Sammanoud | Inv 85 P6 Sammound | 85 | Abou El Matameer and Sammanoud85 | 6990113.13 | 5056647.84 | 1048516.97 | 6105164.81
Cameron EDC | 020/2019 |  | Cameron EDC | 65260.87 | 65173.91 | 0 | 65173.91
4 SS - Technical Service | 254 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHATRA 400/132kV SS | 238 |  | SHATRA 400/132kV SS | 234988.19 | 234988.19 | 0 | 234988.19
MAYSAN 400/132kV SS | 241 |  | MAYSAN 400/132kV SS | 1603335.49 | 1603335.49 | 0 | 1603335.49
Elco Steel 220/33 KV SS | 1908210006 |  | Elco Steel 220/33 KV SS | 629653.39 | 1322272.12 | 0 | 661136.06
Suez IPB | 5 EGP - Suez Steel |  | Suez IPB | 66203.91 | 66203.91 | 0 | 66203.91
Suez IPB | 2*3 EGP - Suez Steel |  | Suez IPB | 27500 | 27500 | 0 | 27500
Suez IPB | 2*1 USD - Suez Steel |  | Suez IPB | 295 | 295 | 0 | 295
MOTHANA 400/132kV SS | 253 |  | MOTHANA 400/132kV SS | 674732.7 | 674732.7 | 0 | 674732.7
El Katameya Mall | INV ( 13 ) 22-10-20 | 13 | El Katameya Mall13 | 440720 | 152282.11 | 221563.53 | 373845.64
Latin Compound - New Alamin | inv ( 19 ) 7-12-2020 | 19 | Latin Compound - New Alamin19 | 193379.2 | 125599.79 | 38675.84 | 164275.63
Ministries Buildings | minist allocat ipc09 | 9 | Ministries Buildings9 | 8828085.8 | 507250 | 7000000 | 7507250
DoubleTree Mangroovy ElGouna | MANGOROVE-IPC01 | 1 | DoubleTree Mangroovy ElGouna1 | 3393576.4 | 2327690.59 | 890813.81 | 3218504.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 8 | 8 | Benban 500 K.V / 100 K.M8 | 46533060.33 | 35876993.06 | 4885971.34 | 40762964.4
EMAAR-PKG# 101-UPTOWN | 20100002 |  | EMAAR-PKG# 101-UPTOWN | 3175801.11 | 1424816.56 | 766170.06 | 2190986.62
DPW Onshore Port & Terminal | DP WORLD-IPC07 | 7 | DPW Onshore Port & Terminal7 | 33097932.28 | 24492163.72 | 4964689.84 | 29456853.56
Beni Seuf - 358 | Ref. Ret. itay 358 |  | Beni Seuf - 358 | 42624818.36 | 42624220.71 | 0 | 42624220.71
Akhmem - Qena | Soc.Inv. 48 Qena | 48 | Akhmem - Qena48 | 482579.5 | 482579.5 | 0 | 482579.5
Akhmem Assiut | Soc.Inv. 50 Assuit | 50 | Akhmem Assiut50 | 127340.6 | 127340.6 | 0 | 127340.6
33KV Canal Farm Grid | Inv. 17 Farm | 17 | 33KV Canal Farm Grid17 | 5700819.11 | 4349724.98 | 855122.87 | 5204847.85
33KV Canal Farm Grid | Inv. 16 Farm | 16 | 33KV Canal Farm Grid16 | 7174437 | 5474095.43 | 1076165.55 | 6550260.98
33KV Canal Farm Grid | Inv. 05 Farm | 5 | 33KV Canal Farm Grid5 | 3210869.8 | 2536587.14 | 481630.47 | 3018217.61
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 5USD | 5 | Benban 500 K.V / 100 K.M5 | 425824.1 | 357692.25 | 44711.53 | 402403.78
HyperOne Zayed Extension | HYPER ONE-IPC12 | 12 | HyperOne Zayed Extension12 | 3093527.62 | 1896313.721 | 773382 | 2669695.721
HyperOne Zayed Extension | HYPER ONE-IPC11 | 11 | HyperOne Zayed Extension11 | 10073235.24 | 6700148 | 2518309 | 9218457
Suez Gulf Substation | 21 EGP VO CCC Instal |  | Suez Gulf Substation | 571885.66 | 541448.5 | 60160.95 | 601609.45
Benban 500 K.V / 100 K.M | Benban Lot1 Inv 9USD | 9 | Benban 500 K.V / 100 K.M9 | 1708275.44 | 1434692.37 | 179368.92 | 1614061.29
Benban 500 K.V / 100 K.M | Benban Lot1 Inv11USD | 11 | Benban 500 K.V / 100 K.M11 | 205796.67 | 151260.55 | 43217.3 | 194477.85
Asec Spare-Parts | Inv 3 Asec Sparepart | 3 | Asec Spare-Parts3 | 3106710 | 2601745 | 932474.94 | 3534219.94
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 17 | 17 | Benban 500 K.V/95 K.M17 | 9286.4 | 7165.39 | 975.07 | 8140.46
AWEER POWER STATION 'H' Phase | 10247 |  | AWEER POWER STATION 'H' Phase | 241518.4 | 253594.32 | 0 | 253594.32
SHATRA 400/132kV SS | 270 |  | SHATRA 400/132kV SS | 68360.02 | 68360.02 | 0 | 68360.02
El Mostaqbal lock & load | ELMOUSTQBAL -IPC 01 | 1 | El Mostaqbal lock & load1 | 3690070 | 1530897 | 1438657.45 | 2969554.45
NUCA R05 - Z02 | R5-ZONE2-IPC08 | 8 | NUCA R05 - Z028 | 31690867.8 | 26625328.57 | 3306778.62 | 29932107.19
AWEER POWER STATION 'H' Phase | 10307 |  | AWEER POWER STATION 'H' Phase | 211328.6 | 221895.03 | 0 | 221895.03
ESU Ph2-Enabling & Struc | E.S.U 2-ENABLE-IPC06 | 6 | ESU Ph2-Enabling & Struc6 | 18379179.43 | 7788095.2015 | 5789441.6 | 13577536.8015
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 14 | 14 | Benban 500 K.V / 100 K.M14 | 2345850.61 | 1808652.48 | 246314.31 | 2054966.79
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 19 | 19 | Benban 500 K.V / 100 K.M19 | 3761270.73 | 2899945.16 | 394933.43 | 3294878.59
Cairo Capital Cables Tunnel | Tunnel Inv. 5 | 5 | Cairo Capital Cables Tunnel5 | 32015241.75 | 21546257.6 | 8003810.44 | 29550068.04
Cairo Capital Cables Tunnel | Tunnel Inv. 1 | 1 | Cairo Capital Cables Tunnel1 | 28355172.25 | 19078030.75 | 7088793.1 | 26166823.85
Suez Road Tunnel RES | SUEZ ROAD L&L-IPC01 | 1 | Suez Road Tunnel RES1 | 5025000.75 | 2837565 | 945859.64 | 3783424.64
Suez Gulf Substation | 485 |  | Suez Gulf Substation | 10694.17 | 10125 | 1125 | 11250
Suez Gulf Substation | 482 |  | Suez Gulf Substation | 3898.86 | 3691.35 | 410.15 | 4101.5
Elco Steel 220/33 KV SS | 1901210014 |  | Elco Steel 220/33 KV SS | 1695469.23 | 1780242.69 | 0 | 1780242.69
Elco Steel 220/33 KV SS | 493 |  | Elco Steel 220/33 KV SS | 138416.67 | 145337.5 | 0 | 145337.5
Elco Steel 220/33 KV SS | 1908210004 |  | Elco Steel 220/33 KV SS | 20676.1 | 21709.9 | 0 | 21709.9
Elco Steel 220/33 KV SS | 1907210012 |  | Elco Steel 220/33 KV SS | 13493.3 | 14168 | 0 | 14168
Elco Steel 220/33 KV SS | 1906210002 |  | Elco Steel 220/33 KV SS | 25454.04 | 26726.74 | 0 | 26726.74
Elco Steel 220/33 KV SS | 1901210007 |  | Elco Steel 220/33 KV SS | 595016.75 | 624767.59 | 0 | 624767.59
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .16 | 16 | Benban 3/ Toshka 2 LOT 416 | 4739932.63 | 3232239.62 | 497692.93 | 3729932.55
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .20 | 20 | Benban 3/ Toshka 2 LOT 420 | 16284436.24 | 12815461.43 | 1709865.81 | 14525327.24
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .13 | 13 | Benban 3/ Toshka 2 LOT 413 | 6884480.29 | 5583320.82 | 722870.43 | 6306191.25
CFC Podium 2 | CFC-IPC08 | 8 | CFC Podium 28 | 31008097.6 | 21459123.66 | 4120101.75 | 25579225.41
CFC Podium 2 | CFC - IPC05 | 5 | CFC Podium 25 | 30502560 | 24749111.52 | 4714808.38 | 29463919.9
MOTHANA 400/132kV SS | 291 |  | MOTHANA 400/132kV SS | 529642.01 | 529642.01 | 0 | 529642.01
Al-Shabab PP Phase II (CP-117) | 180156 |  | Al-Shabab PP Phase II (CP-117) | 48089.64 | 46837.3 | 8265.41 | 55102.71
Akhmem - Qena | Soc 49 Quana |  | Akhmem - Qena | 1837479 | 1837479 | 0 | 1837479
AWEER POWER STATION 'H' Phase | 10390 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
LAYYAH CCPP | MP-11 | 11 | LAYYAH CCPP11 | 12854700 | 0 | 12854700 | 12854700
Port Said | Refund Ret.Port Said |  | Port Said | 2631979.65 | 2631979.65 | 0 | 2631979.65
Lekela 250MW Wind Farm | LEKELA-IPC06 | 6 | Lekela 250MW Wind Farm6 | 17262367.14 | 14840272.417 | 3128774.36 | 17969046.777
Lekela 250MW Wind Farm | LEKELA-IPC01 | 1 | Lekela 250MW Wind Farm1 | 1989169.6 | 1670902.46 | 397833.92 | 2068736.38
Toshka GIS 500 kV | Toshka Sub Inv. 07 $ | 7 | Toshka GIS 500 kV7 | 86989.71 | 49566.56 | 22834.8 | 72401.36
DoubleTree Mangroovy ElGouna | MANGROVE RENT-IPC02 | 2 | DoubleTree Mangroovy ElGouna2 | 409200 | 425568 | 0 | 425568
Elmaragha Bridge - Sohag | IPC#1 | 1 | Elmaragha Bridge - Sohag1 | 968500 | 826340 | 0 | 826340
Multi Sport Hall | 10020 |  | Multi Sport Hall | 146493 | 130378.77 | 0 | 130378.77
Mahmoudia Additional Scope | 2003210002 |  | Mahmoudia Additional Scope | 11268062.5 | 11268062.5 | 0 | 11268062.5
Badr | Inv. 21 Badr | 21 | Badr21 | 6356891.83 | 4719583.38 | 953533.8 | 5673117.18
AWEER POWER STATION 'H' Phase | 3 |  | AWEER POWER STATION 'H' Phase | 211328.6 | 221823.22 | 0 | 221823.22
EL-Hegaz Square Bridge | ELHEGAZ2-IPC1FINAL | 1 | EL-Hegaz Square Bridge1 | 12477199.24 | 0 | 10961702.722 | 10961702.722
EMAAR-Pkg#162/163- Marassi | PKG#163 - IPC011 | 11 | EMAAR-Pkg#162/163- Marassi11 | 3832626.3 | 3799097.555 | 1102242.63 | 4901340.185
EMAAR-Pkg#162/163- Marassi | PKG#163-IPC08 | 8 | EMAAR-Pkg#162/163- Marassi8 | 7415396.3 | 6502546.725 | 1765971.33 | 8268518.055
Marsa Allam | 10032 |  | Marsa Allam | 22368.42 | 24828.9488 | 0 | 24828.9488
Ministries Buildings | MIN -CORE- IPC03 | 3 | Ministries Buildings3 | 8446258.05 | 5400020 | 1800008 | 7200028
MOTHANA 400/132kV SS | 314 |  | MOTHANA 400/132kV SS | 45864.43 | 45864.43 | 0 | 45864.43
MAYSAN 400/132kV SS | 312 |  | MAYSAN 400/132kV SS | 202057.11 | 202057.11 | 0 | 202057.11
Dubai Port | 10039 |  | Dubai Port | 9741.75 | 8240.9275 | 0 | 8240.9275
Marsa Matrouh 500KV | Inv.71 Borg Alarab | 71 | Marsa Matrouh 500KV71 | 30722273.12 | 25118658.37 | 0 | 25118658.37
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 31 | 31 | Benban 500 K.V / 100 K.M31 | 26697762.16 | 20583975.48 | 2803265.03 | 23387240.51
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 2 | 2 | Marsa Alam/ Bernes LOT2 OHTL2 | 19134441.78 | 10734410.81 | 2009116.39 | 12743527.2
ESU Ph2-Enabling & Struc | E.S.U2- IPC 05 | 5 | ESU Ph2-Enabling & Struc5 | 7891719.62 | 2392694.8 | 2485891.6 | 4878586.4
Minis Building(Polyurethane) | 10036 |  | Minis Building(Polyurethane) | 334776 | 297950.64 | 0 | 297950.64
P-28-16 Balat Owinat Lot 3 | Inv. 2 Balat lot 3 | 2 | P-28-16 Balat Owinat Lot 32 | 4181384.51 | 3144010.85 | 439045.37 | 3583056.22
Manshiet Nasser Substation | 2003210009 |  | Manshiet Nasser Substation | 1386244.94 | 1178308.2 | 207936.74 | 1386244.94
Beni Seuf - 358 | Re. Soc Inv 1 Temay | 1 | Beni Seuf - 3581 | 6287397 | 6287397 | 0 | 6287397
LAYAN Substation | 10526 |  | LAYAN Substation | 263056.2 | 218336.75 | 0 | 218336.75
Royal City | ROYAL CITY-IPC29 | 29 | Royal City29 | 17649893.88 | 12838209.344 | 5454040.89 | 18292250.234
Assuit PP (CP-118) | 2005210004 |  | Assuit PP (CP-118) | 806149.42 | 711426.86 | 126968.53 | 838395.39
Mangrouve Hotel - Gouna | 10196 |  | Mangrouve Hotel - Gouna | 11855.16 | 10551.07 | 0 | 10551.07
Canal Sugar OHTL | Inv.10 Sugar OHTL | 10 | Canal Sugar OHTL10 | 4053275.4 | 1538890.85 | 0 | 1538890.85
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 03 | 3 | Suez Gulf/S4 - 500KV OHTL3 | 24468424.76 | 18620460.06 | 2569184.6 | 21189644.66
Ismailiya East Substation | ISE-CW-EGP-23 | 23 | Ismailiya East Substation23 | 1466046 | 1304780.94 | 0 | 1304780.94
Aljazi Project | Al - Jazi Inv. 1 | 1 | Aljazi Project1 | 278661 | 230795 | 0 | 230795
Ministries Buildings | MIN CORE - IPC04 | 4 | Ministries Buildings4 | 30453148.95 | 19470665 | 6490226 | 25960891
Ghana | 42/P/10/ER/2017/USD |  | Ghana | 631405.86 | 631405.86 | 0 | 631405.86
Al-Wukair 11 Substation | 2006210004 |  | Al-Wukair 11 Substation | 1525153.7 | 1525153.7 | 0 | 1525153.7
Sodic East | IPC_12_rowad_s_east | 12 | Sodic East12 | 388943.4 | 156832.48 | 0 | 156832.48
Mahmoudia Additional Scope | 2003210004 |  | Mahmoudia Additional Scope | 8250000 | 8250000 | 0 | 8250000
El Banna project | 455 |  | El Banna project | 2825393.32 | 2825393.32 | 0 | 2825393.32
Museum of Egyp. Civilization | IPC#6 | 6 | Museum of Egyp. Civilization6 | 480649.5 | 306508.29 | 0 | 306508.29
Racecores 3092-16 132KV C | 10803 |  | Racecores 3092-16 132KV C | 284262.36 | 471875.46 | 0 | 235937.73
Iskraemeco show room | 1 |  | Iskraemeco show room | 741585.97 | 845408 | 0 | 845408
NUCA R05 - Z02 | R5(2) IPC 52 | 52 | NUCA R05 - Z0252 | 37170105.92 | 18222028.76 | 3816290.32 | 22038319.08
NUCA R05 - Z02 | R05(2) ipc45 | 45 | NUCA R05 - Z0245 | 27953981.45 | 22913073.64 | 3053354.24 | 25966427.88
NUCA R05 - Z02 | R05(2) ipc 31 | 31 | NUCA R05 - Z0231 | 25879322.45 | 22239327.6 | 2782115.7 | 25021443.3
Port Saad Industiral zone | IPC#7 | 7 | Port Saad Industiral zone7 | 676482.84 | 670548.78 | 0 | 670548.78
Marsa Matrouh 500KV | Ref Retention.Matroh |  | Marsa Matrouh 500KV | 28997790.2 | 0 | 0 | 28997790.2
Tamey El-amdeed Substation | TAM-CW-EGP-22 | 22 | Tamey El-amdeed Substation22 | 125719.78 | 93032.63 | 18857.97 | 111890.6
EMAAR- Pkg 140-ITP-Mivida | PKG#140-IPC15 | 15 | EMAAR- Pkg 140-ITP-Mivida15 | 16266667.66 | 10902262.273 | 1321629.97 | 12223892.243
Taval Sarai 52 | IPC_4_Gama_Saray | 4 | Taval Sarai 524 | 179731.3 | 122105.01 | 0 | 122105.01
Toshka Farm | Toshka Farm Inv. 03 | 3 | Toshka Farm3 | 19732011.69 | 17360481.66 | 877900.85 | 18771715.84
Cairo-Alex Railway | Cairo-Alex ipc 40* | 40 | Cairo-Alex Railway40 | 21031085.3 | 7949386.8 | 8636872.63 | 16586259.43
Racecores 3092-17 132KV E | 11102 |  | Racecores 3092-17 132KV E | 535383.64 | 2221842.25 | 0 | 444368.45
Marsa Matrouh 500KV | Inv.23Usd borg alarb | 23 | Marsa Matrouh 500KV23 | 812.09 | 794.98 | 0 | 794.98
LAYAN Substation | 10303 |  | LAYAN Substation | 4742492.09 | 3936268.44 | 0 | 3936268.44
Ministries A13-A14 | IPC_3_RedSea_Ministy | 3 | Ministries A13-A143 | 55760 | 48401 | 0 | 48401
Celia | FPC |  | Celia | 105196.81 | 74516.56 | 0 | 74516.56
ORA ZED - Ph 01B - Pkgs A&D | ora ph1 ipc (27) | 27 | ORA ZED - Ph 01B - Pkgs A&D27 | 10547653.65 | 8722947.15 | 1106531.13 | 9829478.28
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED1-IPC03 | 3 | ORA ZED - Ph 01B - Pkgs A&D3 | 26768118.08 | 29651159.334 | 3529598.47 | 33180757.804
EMAAR-PKG#53-UPTOWN | IPC-05- PKG#85/53 | 5 | EMAAR-PKG#53-UPTOWN5 | 1849502.84 | 1729285.152 | 0 | 1729285.152
Mohamed Ali Palace | IPC_5_Rowad_M.Ali | 5 | Mohamed Ali Palace5 | 18719.6 | 15724.46 | 0 | 15724.46
AWEER POWER STATION 'H' Phase | ENG/033 |  | AWEER POWER STATION 'H' Phase | 408011.58 | 428412.159 | 0 | 428412.159
Ghana Street lighting | MIDA Ins. Inv.1 | 1 | Ghana Street lighting1 | 105593.4 | 95034.06 | 0 | 95034.06
Miscellaneous Projects | 2008210004 |  | Miscellaneous Projects | 151344.64 | 172532.8896 | 0 | 172532.8896
10th of Ramadan Railway | 2000001 |  | 10th of Ramadan Railway | 1528353 | 1448114.47 | 0 | 1448114.47
ESU Ph2-Enabling & Struc | ESU2-MEP-IPC10 | 10 | ESU Ph2-Enabling & Struc10 | 44073475.24 | 9765894.202 | 12724287.74 | 22490181.942
Lekela 250MW Wind Farm | LEKELA-SUPPLY-IPC01 | 1 | Lekela 250MW Wind Farm1 | 125000 | 124228 | 0 | 124228
Toshka GIS 500 kV | Toshka Sub Inv. 01 | 1 | Toshka GIS 500 kV1 | 28800522.23 | 18816139.97 | 7560137.09 | 26376277.06
Toshka GIS 500 kV | Toshka Sub Inv. 16 $ | 16 | Toshka GIS 500 kV16 | 179629.71 | 103266.16 | 47152.8 | 150418.96
R5 | inv ( 12 ) | 12 | R512 | 2196000 | 329400 | 0 | 2031742.96
Miscellaneous Projects | 2011210004 |  | Miscellaneous Projects | 158424.28 | 180603.6792 | 0 | 180603.6792
Miscellaneous Projects | 2011210003 |  | Miscellaneous Projects | 140230.2 | 159862.428 | 0 | 159862.428
Beni Seuf - 358 | Inv. 8 Oewon Mousa | 8 | Beni Seuf - 3588 | 12574794.7 | 8528325.5 | 2160249.89 | 10688575.39
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $7 | 7 | Benban 3/ Toshka 2 LOT 47 | 946341.06 | 794926.49 | 99365.81 | 894292.3
Canal Sugar OHTL | Inv.07 Sugar OHTL | 7 | Canal Sugar OHTL7 | 21618233.86 | 17078404.74 | 3242735.08 | 20321139.82
Group # 1 - 25 LX | Reailway PSP Inv. 02 | 2 | Group # 1 - 25 LX2 | 1212400 | 1200276 | 0 | 1200276
Lahoon 220/22/22 | Al-Lahoon Sub Inv 04 | 4 | Lahoon 220/22/224 | 17396351.17 | 0 | 4349087.79 | 4349087.79
Lahoon 220/22/22 | Al-Lahoon Sub Inv 01 | 1 | Lahoon 220/22/221 | 13414631.32 | 7899886.77 | 3484319.83 | 11384206.6
Sherouk Bridge- LOCK&LOAD | SHOROUK L&L-IPC01 | 1 | Sherouk Bridge- LOCK&LOAD1 | 728000 | 550000 | 0 | 550000
Ismailiya East Substation | ISE-CW-EURO-03 | 3 | Ismailiya East Substation3 | 4429057.2 | 3700957.79 | 0 | 3700957.79
AWEER POWER STATION 'H' Phase | LOC/012 |  | AWEER POWER STATION 'H' Phase | 192126.31 | 189991.58 | 0 | 189991.58
4 SS - Technical Service | 397 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Miscellaneous Projects | 2007210002 |  | Miscellaneous Projects | 115.06 | 0 | 0 | 0
Ministries A17-A18 | IPC_8_Gama_17-18 | 18 | Ministries A17-A1818 | 232012 | 195031.426 | 0 | 195031.426
Koning Food LP-04-20 | 4 |  | Koning Food LP-04-20 | 18900 | 21546 | 0 | 21546
Nuweibaa (Swro) | 2012210005 |  | Nuweibaa (Swro) | 1208131.98 | 966505.58 | 241626.4 | 1208131.98
Cairo Capital S1 | Inv. 1 S1 | 1 | Cairo Capital S11 | 66935348.57 | 50698102.41 | 10040302.29 | 60738404.7
Taval Sarai 52 | IPC_7_Saray_Gama | 7 | Taval Sarai 527 | 345987.1 | 276290.17 | 0 | 276290.17
EGAT Pelletizing Plant | EGAT IPC01 | 1 | EGAT Pelletizing Plant1 | 5145072.9 | 4836368.8 | 514507.29 | 5350876.09
LRT | IPC#1` | 1 | LRT1 | 80892 | 36288.48 | 0 | 36288.48
West Port Said 220 kV GIS | P-45-Portsaid Inv.03 | 3 | West Port Said 220 kV GIS3 | 18587846.66 | 0 | 1951723.9 | 1951723.9
New Babil 400/132KV Substation | 2103210001 |  | New Babil 400/132KV Substation | 446401 | 446401 | 0 | 446401
Assuit PP (CP-118) | 2101210004 |  | Assuit PP (CP-118) | 1956 | 1745.73 | 308.07 | 2053.8
Al-Wukair 11 Substation | 2103210018 |  | Al-Wukair 11 Substation | 284086.66 | 284086.66 | 0 | 284086.66
AWEER POWER STATION 'H' Phase | ENG-036 | 36 | AWEER POWER STATION 'H' Phase36 | 289170.02 | 303628.52 | 0 | 303628.52
NUCA R05 - Z02 | R5 FINSHING-IPC10 | 10 | NUCA R05 - Z0210 | 11021038.6 | 8733759.6 | 1102103.9 | 9835863.5
Miscellaneous Projects | 2102210005 |  | Miscellaneous Projects | 119999.34 | 136799.2476 | 0 | 136799.2476
ORA-ZED Towers01B | IPC_5_ORA | 5 | ORA-ZED Towers01B5 | 167989.23 | 123937.39 | 0 | 123937.39
New Babil 400/132KV Substation | 2103210017 |  | New Babil 400/132KV Substation | 155065.61 | 155065.61 | 0 | 155065.61
158E/2019 33kv Project | 10482 |  | 158E/2019 33kv Project | 29440 | 52992 | 0 | 26496
LAYAN Substation | 10525 |  | LAYAN Substation | 733262.83 | 4956856.24 | 0 | 619607.03
Miscellaneous Projects | 2103210006 |  | Miscellaneous Projects | 10500 | 11655 | 0 | 11655
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC08 | 8 | EMAAR-Pkg#162/163- Marassi8 | 7771514.83 | 6324880.5415 | 809350.38 | 7134230.9215
Ghana Street lighting | MIDA Sply. Inv.6 | 6 | Ghana Street lighting6 | 382165.22 | 343948.7 | 0 | 343948.7
SHATRA 400/132kV SS | 405 |  | SHATRA 400/132kV SS | 1639704.94 | 1639704.94 | 0 | 1639704.94
Bahr ElBakar – Power Station | IPC005 - Mdkour | 5 | Bahr ElBakar – Power Station5 | 1513632 | 1498495.68 | 0 | 1498495.68
New Babil 400/132KV Substation | 2105210011 |  | New Babil 400/132KV Substation | 103377.07 | 103377.07 | 0 | 103377.07
Mauritania Lot 1 | Inv.2 - Lot 1 | 2 | Mauritania Lot 12 | 222136.46 | 211029.64 | 0 | 211029.64
Akhmem Assiut | Ref.Ret Asuit akh 2 |  | Akhmem Assiut | 20000000 | 20000000 | 0 | 20000000
Miscellaneous Projects | 2105210015 |  | Miscellaneous Projects | 58260 | 66416.4 | 0 | 66416.4
DoubleTree Mangroovy ElGouna | Mangroovy - IPC016 | 16 | DoubleTree Mangroovy ElGouna16 | 4424891.64 | 3166964.612 | 1067784.06 | 4234748.672
Cairo Capital Cables Tunnel | Tunnel Inv. 10 | 10 | Cairo Capital Cables Tunnel10 | 24621268.7 | 16323901 | 6155317.2 | 22479218.2
Faculty of Medicine | Mansoura IPC 14 | 14 | Faculty of Medicine14 | 12586444.76 | 10649618.27 | 629322.24 | 11278940.51
R5 Mix-Use Complex Project | R5 ZONE1-IPC09 | 9 | R5 Mix-Use Complex Project9 | 1179207.85 | 1097160.7825 | 135321.71 | 1232482.4925
Ministries Buildings | MIN ELCTRO-IPC04 | 4 | Ministries Buildings4 | 158785151.6 | 19340990 | 52365755.85 | 134736623.85
AWEER POWER STATION 'H' Phase | CON/020 |  | AWEER POWER STATION 'H' Phase | 1277698.65 | 1121535.4725 | 141966.52 | 1263501.9925
AWEER POWER STATION 'H' Phase | CON/022 |  | AWEER POWER STATION 'H' Phase | 425899.55 | 373845.1575 | 47322.17 | 421167.3275
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .24 | 24 | Benban 3/ Toshka 2 LOT 424 | 61292.22 | 47845.8 | 6435.68 | 54281.48
4 SS - Technical Service | 418 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
33KV Canal Farm Grid | Inv. 12 Farm | 12 | 33KV Canal Farm Grid12 | 22843959.67 | 17429941.23 | 3426593.95 | 20856535.18
33KV Canal Farm Grid | Inv. 13 Farm | 13 | 33KV Canal Farm Grid13 | 11233898.71 | 8571464.72 | 1685084.81 | 10256549.53
Sultana Malak Restoration | Sultana Malak IPC02 | 2 | Sultana Malak Restoration2 | 9278913.66 | 0 | 7562784.65 | 7562784.65
158E/2019 33kv Project | 10625 |  | 158E/2019 33kv Project | 482736 | 1303387.2 | 0 | 434462.4
Solera LP-08-21 | 37 |  | Solera LP-08-21 | 723400.12 | 704264 | 0 | 704264
seashell Playa | IPC-5-PLAYA | 5 | seashell Playa5 | 109610 | 76518.745 | 17537.6 | 94056.345
MAYSAN 400/132kV SS | 412 |  | MAYSAN 400/132kV SS | 83995.03 | 83995.03 | 0 | 83995.03
AWEER POWER STATION 'H' Phase | ENG/041 |  | AWEER POWER STATION 'H' Phase | 187950.14 | 197347.647 | 0 | 197347.647
Miscellaneous Projects | 2105210013 |  | Miscellaneous Projects | 21000 | 23940 | 0 | 11970
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.04 | 4 | Toshka 2/Owinat East LOT2 OHTL4 | 4622103.87 | 4122523.81 | 485320.91 | 4607844.72
ORA ZED-Ph 2-Pkgs A&D | Ora ph2 ipc 26 | 26 | ORA ZED-Ph 2-Pkgs A&D26 | 3475331.25 | 2884524.9425 | 364909.78 | 3249434.7225
ORA ZED-Ph 2-Pkgs A&D | ipc16 ora zed(2) | 16 | ORA ZED-Ph 2-Pkgs A&D16 | 11487525.58 | 9768410.9408 | 1235762.83 | 11004173.7708
ORA ZED - Ph 01B - Pkgs A&D | ora ph.1 - IPC20 | 20 | ORA ZED - Ph 01B - Pkgs A&D20 | 25297815.24 | 21744431.032 | 2587156.1 | 24331587.132
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 - IPC13 | 13 | ORA ZED-Ph 2-Pkgs A&D13 | 15564144.34 | 13357287.557 | 1689777.34 | 15047064.897
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 - inv. 11 | 11 | ORA ZED-Ph 2-Pkgs A&D11 | 10555360.84 | 12170282.5 | 1533288.84 | 13703571.34
Air Force Project | Air Force Inv . 10 | 10 | Air Force Project10 | 5938733.6 | 4251725 | 1484683.4 | 5736408.4
Air Force Project | Air Force Inv . 03 | 3 | Air Force Project3 | 8572918.36 | 6138209.5 | 2143229.59 | 8281439.09
Mansoura University | IPC#3 - Mansoura | 3 | Mansoura University3 | 159601.58 | 153875.91 | 0 | 153875.91
RING ROAD MARYOTIA EXPANSION | Maryotia IPC08+ | 8 | RING ROAD MARYOTIA EXPANSION8 | 541409.52 | 172574.47 | 0 | 172574.47
Kafr Shokr Bridge | Kafr Shokr IPC05 | 5 | Kafr Shokr Bridge5 | 6107250 | 5371513.65 | 0 | 5371513.65
EMAAR-PKG# 144, Marassi | IPC-FINAL-PKG#144 |  | EMAAR-PKG# 144, Marassi | 150533.25 | 1116473.9425 | 0 | 1116473.9425
LP-07-21 Petrojet | 45 |  | LP-07-21 Petrojet | 6396932 | 3081350.89 | 1599233 | 4680583.89
Berty Badr Bridge | Inv (1) PBadr | 1 | Berty Badr Bridge1 | 707034.36 | 400000 | 0 | 400000
Supply E.S. Kit - MAUR. | Inv. No.1 MRT Supply | 1 | Supply E.S. Kit - MAUR.1 | 29938 | 29935.38 | 0 | 29935.38
Mauritania-Lot 2 | Inv.13 – Lot 2 | 13 | Mauritania-Lot 213 | 395815.79 | 375968.88 | 0 | 375968.88
Mauritania-Lot 2 | Inv.12 - Lot 2 | 12 | Mauritania-Lot 212 | 516333.64 | 490516.96 | 0 | 490516.96
ElMoneeb 2 | IPC#5 - Additional | 5 | ElMoneeb 25 | 67870 | 67870 | 0 | 67870
Koning Food LP-04-20 | 23 |  | Koning Food LP-04-20 | 51860 | 59120.4 | 0 | 59120.4
DoubleTree Mangroovy ElGouna | Mngrovy Final IPC018 | 18 | DoubleTree Mangroovy ElGouna18 | 2844607.33 | 5619891.3535 | 0 | 5619891.3535
MDF Factory | MDF IPC03 | 3 | MDF Factory3 | 9210979.01 | 8598866.2305 | 2417881.99 | 11016748.2205
TNYA-WSHP | 11545 |  | TNYA-WSHP | 740609.528 | 1877445.1332 | 0 | 625815.0444
Ras El Teen Hangar | Ras El Teen IPC01 | 1 | Ras El Teen Hangar1 | 3705155.84 | 2378339.532 | 1167124.09 | 3545463.622
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC07 | 7 | ElSewedy HQ Internal Finishing7 | 14463563.81 | 9724934.81 | 4152776.12 | 19095586.9605
Akhmem Assiut | Ref.Ret Asuit akh 3 |  | Akhmem Assiut | 22000000 | 22000000 | 0 | 22000000
Racecores 3092-16 132KV C | 11022 |  | Racecores 3092-16 132KV C | 124343 | 619228.14 | 0 | 103204.69
SHAT Al ARAB 400/132kV SS | 434 |  | SHAT Al ARAB 400/132kV SS | 38812.4 | 38812.4 | 0 | 38812.4
Racecores 3092-17 132KV E | 11026 |  | Racecores 3092-17 132KV E | 386877.49 | 2568866.64 | 0 | 321108.33
Playa Resort | 21000006 |  | Playa Resort | 30749470 | 0 | 34746901.1 | 34746901.1
New Babil 400/132KV GIS Substa | 2107210002 |  | New Babil 400/132KV GIS Substa | 1355660 | 1355660 | 0 | 1355660
Akhmem - Qena | Ret Qen-akh 6 T |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
Akhmem - Qena | Ref.Ret Qen-akh 6 |  | Akhmem - Qena | 5000000 | 0 | 0 | 5000000
Akhmem Assiut | Ret Asuit akh 5 T |  | Akhmem Assiut | 4316843.16 | 4316843.16 | 0 | 4316843.16
Cairo-Alex Railway | Cairo-Alex IPC012 | 12 | Cairo-Alex Railway12 | 29658847.99 | 19205171.1 | 3114179.04 | 22319350.14
Racecores 3092-16 132KV C | 11002 |  | Racecores 3092-16 132KV C | 105755.13 | 105755.13 | 0 | 105755.13
Get Business Complex | INV ( 11 ) GET | 11 | Get Business Complex11 | 197003.64 | 185183.42 | 0 | 185183.42
Get Business Complex | INV ( 8 ) GET | 8 | Get Business Complex8 | 896679.8 | 842879.01 | 0 | 842879.01
Senator | Inv ( 2 ) Sentor | 2 | Senator2 | 296549 | 171000 | 0 | 171000
Ring Road Bridges Project | INV ( 3 ) Ring R | 3 | Ring Road Bridges Project3 | 503859.8 | 392881.91 | 0 | 392881.91
LAYYAH CCPP | 518 |  | LAYYAH CCPP | 7712820 | 6402637 | 1310183 | 7712820
EGAT Pelletizing Plant | EGAT IPC07 | 7 | EGAT Pelletizing Plant7 | 12829691.38 | 12058937.829 | 1283941.21 | 13342879.039
Air Force Project | Air Force Inv . 20 | 20 | Air Force Project20 | 3250344.96 | 3139668 | 0 | 3139668
Ain Sokhna Bridge – RME | IPC#03 - Sokhna Brid | 3 | Ain Sokhna Bridge – RME3 | 1355125 | 135512.5 | 0 | 1334241.5
Akhmem Assiut | Ref-Ret-Assuit $ T |  | Akhmem Assiut | 3471149.12 | 3431960.96 | 0 | 3431960.96
TZ – Offshore E&M Procurement | 466 |  | TZ – Offshore E&M Procurement | 135857 | 122271.3 | 0 | 122271.3
Akhmem - Qena | رد تامين اخميم قنا |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
Akhmem - Qena | رد تامين اخميم قنا 2 |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
Racecores 3092-17 132KV E | 11202 |  | Racecores 3092-17 132KV E | 10080 | 10584 | 0 | 10584
Kafr Shokr Bridge | Kafr Shokr_IPC01 | 1 | Kafr Shokr Bridge1 | 32770679.81 | 29730005.7605 | 0 | 29730005.7605
Ain Sokhna Bridge – RME | IPC#4 - Sokhna Bridg | 4 | Ain Sokhna Bridge – RME4 | 1558625 | 360619.75 | 0 | 1543038.75
Cairo-Alex Railway | Railway IPC07 | 7 | Cairo-Alex Railway7 | 24014920 | 16990381.6 | 2401492 | 19391873.6
TZ – Offshore E&M Procurement | 446 |  | TZ – Offshore E&M Procurement | 5830.48 | 5830.48 | 0 | 5830.48
Benban 500 K.V/95 K.M | Ref-Ret-benban 2 $ T |  | Benban 500 K.V/95 K.M | 1447097.67 | 1447097.67 | 0 | 1447097.67
Racecores 3092-16 132KV C | 11344 |  | Racecores 3092-16 132KV C | 10500 | 11025 | 0 | 11025
TZ – Offshore E&M Procurement | 450 |  | TZ – Offshore E&M Procurement | 275681.7 | 192977.22 | 55136.09 | 248113.31
SHATRA 400/132kV SS | 436 |  | SHATRA 400/132kV SS | 134990.29 | 134990.29 | 0 | 134990.29
Racecores 3092-16 132KV C | 11345 |  | Racecores 3092-16 132KV C | 11400 | 11970 | 0 | 11970
RING ROAD MARYOTIA EXPANSION | Maryotia IPC014 | 14 | RING ROAD MARYOTIA EXPANSION14 | 44712557.52 | 14554103.9 | 0 | 39554103.9
Racecores 3092-17 132KV E | 11163 |  | Racecores 3092-17 132KV E | 331266.34 | 1099804.24 | 0 | 274951.06
Hyper One Badr | inv ( 1-2-3 ) Hayper | 1 | Hyper One Badr1 | 1835955 | 1633999.95 | 0 | 1633999.95
Ghana Street lighting | MIDA Sply.inv.11 | 11 | Ghana Street lighting11 | 190827.34 | 171744.6 | 0 | 171744.6
Akhmem - Qena | Ret Quana akh USD T |  | Akhmem - Qena | 283226.77 | 276511.9 | 0 | 276511.9
Zone(J) South Valley Toshka | South Valley Inv. 13 | 13 | Zone(J) South Valley Toshka13 | 81984536 | 61573816.85 | 10494020.64 | 72067837.49
Mangrouve Hotel - Gouna | IPC-4-GOUNA | 4 | Mangrouve Hotel - Gouna4 | 5069.28 | 4488.86 | 0 | 4488.86
New Giza Hospital | IPC-2-NEW GIZA | 2 | New Giza Hospital2 | 49576.04 | 42541.21 | 0 | 42541.21
Racecores 3092-16 132KV C | 11426 |  | Racecores 3092-16 132KV C | 7000 | 7350 | 0 | 7350
Abou Matamer & Samanoud | Ref Ret Samanod& mat |  | Abou Matamer & Samanoud | 4561945.18 | 4561945.18 | 0 | 4561945.18
Governmental Campus-N2 | 65 |  | Governmental Campus-N2 | 136850 | 136850 | 0 | 136850
Infra Project 4428 | 220421004 |  | Infra Project 4428 | -134285714.29 | 0 | 0 | 0
Racecores 3092-17 132KV E | 11501 |  | Racecores 3092-17 132KV E | 1452.53 | 1452.53 | 0 | 1452.53
Racecores 3092-17 132KV E | 11446 |  | Racecores 3092-17 132KV E | 58508.73 | 49440.3765 | 0 | 49440.3765
October Dry Port | Dry Port Inv. 07 | 7 | October Dry Port7 | 25984270.5 | 6366407.68 | 6820871.01 | 13187278.69
MDF Factory | MDF FACTORY2 IPC04 | 4 | MDF Factory4 | 2097847.2 | 2118825.668 | 0 | 2118825.668
Mivida BP#189 | PKG#189 IPC 29 | 29 | Mivida BP#18929 | 369049.79 | 2690517.4595 | 357346.78 | 3047864.2395
Ghana Street lighting | MIDA Ins.inv.12 | 12 | Ghana Street lighting12 | 19782.53 | 17804.28 | 0 | 17804.28
PLAYA ROOF & Wet Areas | IPC-8-PLAYA ROOF | 8 | PLAYA ROOF & Wet Areas8 | 211822.15 | 180758.74 | 0 | 180758.74
EGAT Pelletizing Plant | EGAT WaterTank IPC07 | 7 | EGAT Pelletizing Plant7 | 399729.3 | 395732.005 | 0 | 395732.005
AWEER POWER STATION 'H' Phase | ENG/054 |  | AWEER POWER STATION 'H' Phase | 1230673.4 | 1292207.07 | 0 | 1292207.07
Faculty of Medicine | mansora finish ipc17 | 17 | Faculty of Medicine17 | 33386477.14 | 24807431 | 5007971.57 | 29815402.57
October Dry Port | Dry Port Inv. 09 | 9 | October Dry Port9 | 21934548.75 | 15623254.08 | 5757819.05 | 21381073.13
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv14 | 14 | Marsa Alam/ Bernes LOT2 OHTL14 | 424162.49 | 382089.84 | 0 | 382089.84
Ora Zed Landscape Ph1 | Ora Landsape ipc 21 | 21 | Ora Zed Landscape Ph121 | 324859.52 | 108767.386 | 144976.25 | 253743.636
Ora Zed Landscape Ph1 | Ora Landscape ipc 15 | 15 | Ora Zed Landscape Ph115 | 3753240.01 | 3165189.2 | 394090.2 | 3559279.4
Railway Bridge - El Hammam | IPC#5 ElHammam | 5 | Railway Bridge - El Hammam5 | 468238 | 426786.65 | 0 | 426786.65
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 09 | 9 | Hosh Essa 220 KV OHTL9 | 7150106.67 | 1037876.75 | 750761.2 | 1788637.95
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 10 | 10 | Hosh Essa 220 KV OHTL10 | 182617.6 | 96969.45 | 19174.85 | 116144.3
Hassan El Mamoun Bridge | hasan Mamoun 2 Final |  | Hassan El Mamoun Bridge | 21747325.71 | 2283455 | 17968704.18 | 20252159.18
New Babil 400/132KV GIS Substa | 220621001 |  | New Babil 400/132KV GIS Substa | 2734793.51 | 2734793.51 | 0 | 2734793.51
HST Bridges-Sokhna & Mahager | sokhna bridge ipc02 | 2 | HST Bridges-Sokhna & Mahager2 | 15445843.81 | 13771117.5205 | 0 | 13771117.5205
Neighborhood New Capital R5 | inv ( 2 ) fainal | 2 | Neighborhood New Capital R52 | 326600 | 301125.2 | 0 | 301125.2
Benban 3/ Toshka 2 LOT 4 | Ref-Ret-Toshka Lot4T |  | Benban 3/ Toshka 2 LOT 4 | 33020632.09 | 33020632.09 | 0 | 33020632.09
Abo Quir - Badr 500KV | Ref.Abu Quir Badr-T |  | Abo Quir - Badr 500KV | 113544.93 | 113544.93 | 0 | 113544.93
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .28 | 28 | Benban 3/ Toshka 2 LOT 428 | 14932972.26 | 9369229.26 | 0 | 9369229.26
TZ – Offshore E&M Procurement | 475 |  | TZ – Offshore E&M Procurement | -274863.23 | -274863.23 | 0 | -274863.23
TZ – Offshore E&M Procurement | 471 |  | TZ – Offshore E&M Procurement | 832010.31 | 624008.19 | 124801.09 | 748809.28
Marassi - Water proofing | IPC-1-PK177-Waterpro | 1 | Marassi - Water proofing1 | 73972.36 | 65502.52 | 0 | 65502.52
BKG#178-Lagoon Discharge | pkg#178 ipc08 | 8 | BKG#178-Lagoon Discharge8 | 1389835.52 | 668886.796 | 0 | 668886.796
NUCA R05 - Z02 | Ro5 (2) ipc 20 | 20 | NUCA R05 - Z0220 | 32863219.49 | 27573057.68 | 3515743.2 | 31088800.88
PLAYA ROOF & Wet Areas | 12 |  | PLAYA ROOF & Wet Areas | 805054.453 | 690817.233 | 0 | 690817.233
seashell Playa | IPC020 | 20 | seashell Playa20 | 579335.07 | 497127.43 | 0 | 497127.43
Sultana Malak Restoration | sultana malak2 ipc01 | 1 | Sultana Malak Restoration1 | 8421662.9 | 7827175 | 0 | 7827175
EMAAR-Pkg#162/163- Marassi | pkg#163 ipc 23 | 23 | EMAAR-Pkg#162/163- Marassi23 | 6328514.78 | 3653330.379 | 0 | 3653330.379
EMAAR-Pkg#162/163- Marassi | pkg#163- IPC24 | 24 | EMAAR-Pkg#162/163- Marassi24 | 6666259.32 | 6005632.246 | 0 | 6005632.246
Kattameya Creeks | kattamya ipc17 | 17 | Kattameya Creeks17 | 37521775.17 | 36571027.7485 | 2451618.43 | 39022646.1785
SSC Suez Steel Company Project | Supply SSC IPC 4 | 4 | SSC Suez Steel Company Project4 | 389998.19 | 0 | 145113.66 | 440697.9566
SSC Suez Steel Company Project | I&RSUPPLY (ABB) IPC5 | 5 | SSC Suez Steel Company Project5 | 8225548.17 | 0 | 2834850.89 | 9294869.4338
SSC Suez Steel Company Project | In&ReSupply ABB-IPC2 | 2 | SSC Suez Steel Company Project2 | 8551701.56 | 7437728.3384 | 2225694.42 | 9663422.7584
SSC Suez Steel Company Project | int&ret app(ssc)ipc5 | 5 | SSC Suez Steel Company Project5 | 2754124.9 | 2699925.476 | 357153.16 | 3057078.636
Air Defence College | TR0046/1 |  | Air Defence College | 434589 | 368966.06 | 0 | 368966.06
Egyptian Exchange building | TR0039-IPC0039 | 39 | Egyptian Exchange building39 | 15357.47 | 12569.04 | 0 | 12569.04
PLAYA ROOF & Wet Areas | 13 |  | PLAYA ROOF & Wet Areas | 141699.04 | 121591.95 | 0 | 121591.95
Playa Resort | kantine 2 |  | Playa Resort | 35000 | 0 | 35000 | 35000
Ministries Buildings | العناصر المائية ipc4 | 4 | Ministries Buildings4 | 2124658 | 1789620 | 0 | 1789620
Ring Road El Mansoria | INV (3 ) AL Mansorya | 3 | Ring Road El Mansoria3 | 145140 | 58056 | 0 | 58056
Railway Bridge - El Hammam | IPC#4 ELHammam | 4 | Railway Bridge - El Hammam4 | 1811308 | 1523339.51 | 0 | 1523339.51
ORA ZED-Ph 2-Pkgs A&D | Ora ph.2 ipc10 | 10 | ORA ZED-Ph 2-Pkgs A&D10 | 25761823.86 | 22199070.249 | 2641249.36 | 24840319.609
Railway Bridge - El Hammam | IPC#3 ElHammam | 3 | Railway Bridge - El Hammam3 | 532834.48 | 498466.66 | 0 | 498466.66
EMAAR- Pkg 140-ITP-Mivida | pkg#140 ipc27 | 27 | EMAAR- Pkg 140-ITP-Mivida27 | 825139.18 | 6499741.709 | 0 | 6499741.709
Ministries Buildings | SHELL IPC09 | 9 | Ministries Buildings9 | 18018358 | 0 | 0 | 16036338.62
Egat Rolling Mill no.4 | Rolling Mill IPC8 | 8 | Egat Rolling Mill no.48 | 21317723 | 16970582.32 | 5199849.6 | 22170431.92
MDF Factory | MDF Factory3 IPC5 | 5 | MDF Factory5 | 3536061.27 | 2517907.4178 | 1007777.46 | 3525684.8778
Railway Bridge - Assuit | IPC#8 Assuit | 8 | Railway Bridge - Assuit8 | 1153260 | 1060999.2 | 0 | 1060999.2
Ismailiya East Substation | ismalyia ipc28 final | 28 | Ismailiya East Substation28 | 2858104.7 | 2294947.36 | 0 | 2294947.36
Sokhna Port Expansion | sokh.port roads ipc1 | 1 | Sokhna Port Expansion1 | 2098544.62 | 1800470.45 | 0 | 1800470.45
Get Business Complex | Cr.INV ( 14 ) GET | 14 | Get Business Complex14 | 230869.31 | 217017.15 | 0 | 217017.15
seashell Playa | IPC00024 | 24 | seashell Playa24 | 867016.27 | 743981.76 | 0 | 743981.76
seashell Playa | IPC#023 | 23 | seashell Playa23 | 617575.14 | 499891.23 | 0 | 499891.23
Cairo-Alex Railway | cairo - alex ipc 30 | 30 | Cairo-Alex Railway30 | 12783976.19 | 617363.65 | 9603026.5 | 10220390.15
seashell Playa | IPC#22 | 22 | seashell Playa22 | 621903.28 | 507755.22 | 0 | 507755.22
Creeks URBN-K | URBIN-K IPC 10+ | 10 | Creeks URBN-K10 | 20086171.5 | 889617.682 | 20000000 | 20889617.682
HSR-6th of October | IPC#5 HSR | 5 | HSR-6th of October5 | 1253000 | 1090110 | 0 | 1090110
Sixty Iconic Tower | Inv ( 9 ) sixty | 9 | Sixty Iconic Tower9 | 1120470 | 315202.5 | 0 | 315202.5
Kayan 3 New Cairo Capital City | Kayan IPC4 | 4 | Kayan 3 New Cairo Capital City4 | 2093783 | 1972990 | 0 | 1972990
Seashell Playa 5 Villas | seashell playa-IPC1 | 1 | Seashell Playa 5 Villas1 | 161096.6 | 130727.19 | 0 | 130727.19
SSC Suez Steel Company Project | Revamp ipc 9 | 9 | SSC Suez Steel Company Project9 | 1572976.38 | 1085353.7052 | 471892.91 | 1557246.6152
SSC Suez Steel Company Project | Revamp ipc (3) | 3 | SSC Suez Steel Company Project3 | 2879525.93 | 0 | 863857.79 | 2994706.9672
SSC Suez Steel Company Project | Revamp IPC1 | 1 | SSC Suez Steel Company Project1 | 3199345.21 | 2207548.1984 | 959803.56 | 3167351.7584
Air Defense College | Airdevance7 IPC1 | 1 | Air Defense College1 | 90222127 | 14363600 | 53500000 | 74274425
PLAYA ROOF & Wet Areas | IPC0000000015 | 15 | PLAYA ROOF & Wet Areas15 | 94886.04 | 51371.71 | 0 | 51371.71
ORA ZED - Ph 01B - Pkgs A&D | ORA ZED1-IPC04 | 4 | ORA ZED - Ph 01B - Pkgs A&D4 | 26593168.54 | 26411905.937 | 3145501.01 | 29557406.947
SSC Suez Steel Company Project | R.O. Supply-IPC3 | 3 | SSC Suez Steel Company Project3 | 9778491.46 | 8116147.9144 | 2933547.44 | 11049695.3544
ORA-ZED Towers P01B | IPC#00005 | 5 | ORA-ZED Towers P01B5 | 189600 | 167890.8 | 0 | 167890.8
EGAT Lock & Load | L&L IPC10 | 10 | EGAT Lock & Load10 | 931996.59 | 876076.7895 | 93199.66 | 969276.4495
Kemet Tower | inv ( 5 ) Kemt | 5 | Kemet Tower5 | 237600 | 163708.56 | 0 | 163708.56
PLAYA ROOF & Wet Areas | IPC000018 | 18 | PLAYA ROOF & Wet Areas18 | 32805.45 | 26544.77 | 0 | 26544.77
seashell Playa | 26 |  | seashell Playa | 64275.61 | 55154.9 | 0 | 55154.9
U4,U8 Seashell Playa | IPC002 TR60 | 2 | U4,U8 Seashell Playa2 | 572180.64 | 353035.2 | 0 | 353035.2
Olympic Multi – Sports Hall | Olym Fire IPC1 | 1 | Olympic Multi – Sports Hall1 | 887566 | 160730 | 580000 | 740730
EGAT Injection | IPC0000005 | 5 | EGAT Injection5 | 18749.55 | 16088.99 | 0 | 16088.99
Egyptian Exchange building | IPC0000010 | 10 | Egyptian Exchange building10 | 85472.01 | 75685.47 | 0 | 75685.47
Kayan 3 New Cairo Capital City | Kayan MEP IPC fin |  | Kayan 3 New Cairo Capital City | 29771651 | 13451220 | 0 | 13451220
NUCA R05 - Z02 | R05(2) ipc 32 | 32 | NUCA R05 - Z0232 | 29719120.95 | 22951401.3805 | 2895575.5 | 25846976.8805
HST El Mahager Bridge | EL MAHAGER IPC 01 | 1 | HST El Mahager Bridge1 | 42907858.33 | 3290022.0867 | 0 | 37408234.0867
HST Culverts | Hst Culverts ipc 01 | 1 | HST Culverts1 | 39779000.76 | 22255333.2376 | 0 | 36255333.2376
MDF Factory | ipc14 mdf factory2 | 14 | MDF Factory14 | 1329223.07 | 1342515 | 0 | 1342515
SSC Suez Steel Company Project | R.Osup Pri ADJ. IPC1 | 1 | SSC Suez Steel Company Project1 | 14675847.72 | 15849915.5156 | 0 | 15849915.5156
DP World Basin 2 Ph2 | Dp world ph2 ipc 11 | 11 | DP World Basin 2 Ph211 | 58932579.7 | 43610108.98 | 8839886.95 | 52449995.93
DP World Basin 2 Ph2 | dp world ipc(7=8) | 7 | DP World Basin 2 Ph27 | 21511754.48 | 15918423.282 | 3226763.17 | 19145186.452
EGAT Pelletizing Plant | Egat Mep Mobili ipc4 | 4 | EGAT Pelletizing Plant4 | 456912.02 | 475188.5008 | 0 | 475188.5008
Wady El Natroon Bridge | wady el natroon ipc2 | 2 | Wady El Natroon Bridge2 | 10422940 | 3115862.55 | 0 | 3115862.55
HST Culverts | HST CULVERTS IPC 2 | 2 | HST Culverts2 | 524792.19 | 433670.8 | 0 | 433670.8
Sixty Iconic Tower | inv ( 1 ) sixty | 1 | Sixty Iconic Tower1 | 1454355 | 4101281.1 | 0 | 1367093.7
SSC Suez Steel Company Project | R.O(5000:8000)SIPC.4 | 4 | SSC Suez Steel Company Project4 | 7605000 | 6312150 | 2281500 | 8593650
Olympic Multi – Sports Hall | Oly elec IPC1 | 1 | Olympic Multi – Sports Hall1 | 7086895 | 1590500 | 4300000 | 5890500
SSC Suez Steel Company Project | R.O 5:8 APPLY IPC 1 | 1 | SSC Suez Steel Company Project1 | 2250265.4 | 1730229.064 | 767565.53 | 2497794.594
SSC Suez Steel Company Project | R.O - supply ipc 2 | 2 | SSC Suez Steel Company Project2 | 1896616.8 | 1574191.942 | 568985.04 | 2143176.982
RING ROAD MARYOTIA EXPANSION | El-Marg IPC06 | 6 | RING ROAD MARYOTIA EXPANSION6 | 1415139.9 | 1254124.85 | 0 | 1254124.85
Seashell Playa 5 Villas | playa c-204 ipc 1 | 1 | Seashell Playa 5 Villas1 | 106544.39 | 92011.74 | 0 | 92011.74
Expansion of Ring Road-CFA | IPC 1/2 CFA | 1 | Expansion of Ring Road-CFA1 | 1739849.5 | 110000 | 0 | 110000
Olympic Multi – Sports Hall | Olympic Hall IPC03 | 3 | Olympic Multi – Sports Hall3 | 51360259.65 | 43710626.09 | 0 | 43710626.09
Ahl Misr P3 – Zamalek Sector | FPC Zamalek |  | Ahl Misr P3 – Zamalek Sector | 587250 | 568164.37 | 0 | 568164.37
PVD - El Hammam | IPC 2 PVD | 2 | PVD - El Hammam2 | 231328.57 | 204494.45 | 0 | 204494.45
AIRDEFNSE -EPOXY | IPC05TR0066 | 5 | AIRDEFNSE -EPOXY5 | 381884.4 | 324219.86 | 0 | 324219.86
U7-SEASHELL | IPC04 TR64 | 4 | U7-SEASHELL4 | 454840.57 | 392800.31 | 0 | 392800.31
Alamein Coastal Road Bridge | Alamein sahely IPC1 | 1 | Alamein Coastal Road Bridge1 | 3743238.1 | 2832840 | 0 | 2832840
EGAT Mechanical Installations | Egat Mech Equip ipc2 | 2 | EGAT Mechanical Installations2 | 24000790.6 | 18238200.7161 | 6000197.65 | 24238398.3661
Seashell Playa 5 Villas | playa c045- ipc 3 | 3 | Seashell Playa 5 Villas3 | 49879.56 | 70606.1 | 0 | 70606.1
SEASHELL TECHNICAL ROOM | IPC0001TR65 | 1 | SEASHELL TECHNICAL ROOM1 | 74256 | 64127.43 | 0 | 64127.43
PLAYA ROOF & Wet Areas | IPC0023 TR41 | 23 | PLAYA ROOF & Wet Areas23 | 55933.7 | 47996.7 | 0 | 47996.7
U3 & U5 | IPC008 TR55 | 8 | U3 & U58 | 230620.4 | 199163.78 | 0 | 199163.78
Katameya Creeks - RME | IPC 008 TR0055 | 8 | Katameya Creeks - RME8 | 266794.69 | 236246.7 | 0 | 236246.7
Central Capital | INV ( 4 ) Central Ca | 4 | Central Capital4 | 147420 | 55211.76 | 0 | 55211.76
Sokhna Port Expansion | spx.2 ipc 01 | 1 | Sokhna Port Expansion1 | 57988132.8 | 39700885.25 | 11597626.56 | 51298511.81
Cairo-Alex Railway | cairo-alex ipc 41* | 41 | Cairo-Alex Railway41 | 6779667 | 77863291.8 | 0 | 77863291.8
Cairo-Alex Railway | cairo-alex ipc15 | 15 | Cairo-Alex Railway15 | 94581172.88 | 65617126.41 | 9931023.15 | 75548149.56
EGAT Lock & Load | EGAT L&L IPC8 | 8 | EGAT Lock & Load8 | 2786604.1 | 2619407.855 | 278660.41 | 2898068.265
EGAT Pelletizing Plant | EGAT MEP- IPC3 | 3 | EGAT Pelletizing Plant3 | 1266155.18 | 1316801.3872 | 0 | 1316801.3872
EGAT Pelletizing Plant | EGAT MEP-IPC 1 | 1 | EGAT Pelletizing Plant1 | 2011978.5 | 2092457.64 | 0 | 2092457.64
Playa Resort | 230000001 |  | Playa Resort | 35000 | 35000 | 0 | 35000
Tarek Abdel-Hakim Center | TAH ipc 01 | 1 | Tarek Abdel-Hakim Center1 | 1174788.1 | 903999.44 | 105730.93 | 1009730.37
Air Defence College | IPC017 TR46 | 17 | Air Defence College17 | 121741.26 | 103358.324 | 0 | 103358.324
Air Defence College | ipc00016 tr46 | 16 | Air Defence College16 | 51341.93 | 55089.29 | 0 | 55089.29
SOL Town PKG.220 | pkg#220-ipc2 | 2 | SOL Town PKG.2202 | 11462411.01 | 5980500.04 | 3610659.47 | 9591159.51
Seashell Playa 5 Villas | Playa -c234 ipc (2) | 2 | Seashell Playa 5 Villas2 | 251899.5 | 230135.37 | 0 | 230135.37
Seashell Playa 5 Villas | playa-c234 ipc (3) | 3 | Seashell Playa 5 Villas3 | 55618.05 | 50812.87 | 0 | 50812.87
Seashell Playa 5 Villas | Playa-c038 ipc (3) | 3 | Seashell Playa 5 Villas3 | 35410.74 | 20973.67 | 0 | 20973.67
Seashell Playa 5 Villas | Playa -c072 ipc (2) | 2 | Seashell Playa 5 Villas2 | 281581.79 | 243173.96 | 0 | 243173.96
PLAYA ROOF & Wet Areas | IPC24 TR41 | 24 | PLAYA ROOF & Wet Areas24 | 7711.2 | 6616.98 | 0 | 6616.98
Air Defence College | IPC0019 TR46 | 19 | Air Defence College19 | 160397.93 | 143427.84 | 0 | 143427.84
GOV2 - Infra | IPC 24 GOV2 | 24 | GOV2 - Infra24 | 6866553.95 | 2728755.6533 | 415258.04 | 3144013.6933
Villa Clustera Playa | IPC01TR0076 | 1 | Villa Clustera Playa1 | 874855 | 653224.78 | 0 | 653224.78
U6T11 PART1 Palay | IPC01TR0075 | 1 | U6T11 PART1 Palay1 | 19226.59 | 17565.41 | 0 | 17565.41
Olympic Multi – Sports Hall | Olympic Finish IPC6 | 6 | Olympic Multi – Sports Hall6 | 12369937 | 10421270 | 0 | 10421270
Ministries Buildings | Minis alloc IPC13 | 13 | Ministries Buildings13 | 2077967 | 1750290 | 0 | 1750290
SSC Suez Steel Company Project | Baraka Fance ipc 3 | 3 | SSC Suez Steel Company Project3 | 22345362 | 15418299.78 | 6703608.6 | 22121908.38
EL Baragil Bridge | inv ( 1 ) Baragill B | 1 | EL Baragil Bridge1 | 1685715.85 | 1584572.9 | 0 | 1584572.9
Irrigation Tank | IPC04TR0061 | 4 | Irrigation Tank4 | 69919.2 | 60382.22 | 0 | 60382.22
ORA-ZED Towers P01B | IPC12 TR51 | 12 | ORA-ZED Towers P01B12 | 110583.5 | 97921.67 | 0 | 97921.67
Open Channal | IPC02TR0074 | 2 | Open Channal2 | 78848 | 68014.28 | 0 | 68014.28
AIRDEFNSE -EPOXY | IPC07TR0066 | 7 | AIRDEFNSE -EPOXY7 | 38228.4 | 32455.91 | 0 | 32455.91
El-Warraq | ipc no3 elwaraq | 3 | El-Warraq3 | 736709.2 | 0 | 0 | 0
Sokhna Port Expansion | spx.2 ipc5 | 5 | Sokhna Port Expansion5 | 4703267 | 3240800 | 940653.4 | 4181453.4
Sultana Malak Restoration | sultana IPC final |  | Sultana Malak Restoration | 368114 | 346340 | 0 | 346340
HST Bridges-Sokhna & Mahager | sokhna bridge ipc16+ | 16 | HST Bridges-Sokhna & Mahager16 | 9873400 | 7751054.1 | 0 | 7751054.1
Wady El Natroon Bridge | wady elnatron ipc06 | 6 | Wady El Natroon Bridge6 | 21784193.33 | 4693085.97 | 0 | 19693085.97
Katameya Creeks - RME | IPC013 TR0053 | 13 | Katameya Creeks - RME13 | 36591.65 | 32401.91 | 0 | 32401.91
Katameya Creeks - RME | IPC0015TR0053 | 15 | Katameya Creeks - RME15 | 96306.39 | 85279.31 | 0 | 85279.31
EIPICO Factory | tr0054 |  | EIPICO Factory | 58672.5 | 50346.85 | 0 | 50346.85
Marassi - Water proofing | IPC004 TR0044 | 4 | Marassi - Water proofing4 | 76374.4 | 67629.54 | 0 | 67629.54
VILLA CLUSTRER B | IPC06TR0077 | 6 | VILLA CLUSTRER B6 | 47940 | 41400.98 | 0 | 41400.98
U7-SEASHELL | IPC13TR0064 | 13 | U7-SEASHELL13 | 16346.4 | 14116.75 | 0 | 14116.75
El Zomor Axis (2) - Leaaba | IPC#Final#Leaaba |  | El Zomor Axis (2) - Leaaba | 49500 | 43065 | 0 | 43065
SSC Suez Steel Company Project | fence western ipc 1 | 1 | SSC Suez Steel Company Project1 | 762742.21 | 418218.3524 | 0 | 755114.7524
Roof-Playa Cluster A,B,C | IPC04TR0088 | 4 | Roof-Playa Cluster A,B,C4 | 2177425 | 1819674.23 | 0 | 1819674.23
Residence 8 ( K10 ) | Inv ( 1 ) K 10 | 1 | Residence 8 ( K10 )1 | 802825 | 725753 | 0 | 725753
Tarek AbdelHakim Center - KSA | K0001 |  | Tarek AbdelHakim Center - KSA | 1799632.85 | 0 | 0 | 1862620
South Dabaa Axis | IPC#004 | 4 | South Dabaa Axis4 | 557198.4 | 493399.19 | 0 | 493399.19
Beymen Fit Out | Emaar Pkg#205 ipc6 | 6 | Beymen Fit Out6 | 494969.77 | 484105.18 | 0 | 484105.18
U3 & U5 | IPC19TR0055 | 19 | U3 & U519 | 100891.1 | 87129.54 | 0 | 87129.54
Creeks URBN-K | katamya Urbn-k ipc10 | 10 | Creeks URBN-K10 | 20145681.95 | 18357105.318 | 1729602.61 | 20086707.928
ZED Phase 2 | IPC07TR0062 | 7 | ZED Phase 27 | 72261.55 | 61385.8 | 0 | 61385.8
ElSewedy HQ Internal Finishing | HQ final ipc 26 | 26 | ElSewedy HQ Internal Finishing26 | 15848994.31 | 11230610.0055 | 0 | 23450753.0855
Port Said Port Silos | PORT SAID IPC25 | 25 | Port Said Port Silos25 | 4504741.9 | 3280047.566 | 450474.19 | 3730521.756
Air Defence College | IPC24TR0046 | 24 | Air Defence College24 | 33825.6 | 28717.93 | 0 | 28717.93
Katameya Creeks - RME | IPC17TR0053 | 17 | Katameya Creeks - RME17 | 137202.31 | 121492.64 | 0 | 121492.64
Kattameya Creeks | Katameya Creek ipc38 | 38 | Kattameya Creeks38 | 78865309.72 | 79235149.8888 | 2486946.22 | 81722096.1088
Koumassi Flyover | INV 4 | 4 | Koumassi Flyover4 | 161714858 | 145543371 | 0 | 145543371
Koumassi Flyover | INV 6 | 6 | Koumassi Flyover6 | 225560250 | 203004225 | 0 | 203004225
Irrigation Tank | IPC09TR0061 | 9 | Irrigation Tank9 | 1116341.1 | 964072.17 | 0 | 964072.17
U3 & U5 | IPC20TR0055 | 20 | U3 & U520 | 169727.9 | 146577.02 | 0 | 146577.02
Hosh Eisa Hospital | IPC01TR0086 | 1 | Hosh Eisa Hospital1 | 364500 | 312777.45 | 0 | 312777.45
EGAT Mechanical Installations | Eagt Mechnical ipc 5 | 5 | EGAT Mechanical Installations5 | 12224551.86 | 9289436.96 | 3056137.9746 | 12345574.9346
U4,U8 Seashell Playa | IPC13TR0060 | 13 | U4,U8 Seashell Playa13 | 147841.6 | 127676 | 0 | 127676
Port Said Grain Storage | Rent-003 | 3 | Port Said Grain Storage3 | 153350 | 141836.22 | 0 | 141836.22
Sokhna Port Expansion | Spx.2 (7) part2 |  | Sokhna Port Expansion | 1211958 | 1211958 | 0 | 1211958
HST Bridges-Sokhna & Mahager | Sokhna bri esc.20+21 |  | HST Bridges-Sokhna & Mahager | 4655327.38 | 3150292.95 | 0 | 3150292.95
Rabigh PP - Piling Works | Inv-03 | 3 | Rabigh PP - Piling Works3 | 840198 | 2898683.1 | 0 | 966227.7
Olympic MultiSport Hall | IPC05TR0079 | 5 | Olympic MultiSport Hall5 | 25760 | 21677.04 | 0 | 21677.04
Air Defence College | IPC25TR0046 | 25 | Air Defence College25 | 20217.6 | 17164.74 | 0 | 17164.74
SSC Suez Steel Company Project | Baraka Fance ipc 4 | 4 | SSC Suez Steel Company Project4 | 11760884 | 6072172.61 | 3528265.2 | 11547684.17
EDNC Retail - SEOUDI MODI | Ednc saudi ipc 1 | 1 | EDNC Retail - SEOUDI MODI1 | 1533908.63 | 622410.12 | 691590.61 | 1314000.73
Kattmeya Creeks Urban | IPC08TR0071 | 8 | Kattmeya Creeks Urban8 | 57380.28 | 50810.25 | 0 | 50810.25
MDF Factory | MDF Factory ipc 40 | 40 | MDF Factory40 | 759488.56 | 14022964.76 | 624505.64 | 14647470.4
Kattameya Creeks | katamya Creeks ipc42 | 42 | Kattameya Creeks42 | 52161798.49 | 52791233 | 1154383.5 | 53945616.5
Sokhna Port Expansion | Spx.1 esc.13:23 |  | Sokhna Port Expansion | 116453697 | 103409321 | 0 | 103409321
MDF Factory - Sadat | IPC03TR0093 | 3 | MDF Factory - Sadat3 | 200465.2 | 151770.12 | 0 | 151770.12
Roof-Playa Cluster A,B,C | IPC08TR0088 | 8 | Roof-Playa Cluster A,B,C8 | 153525 | 109906.58 | 0 | 109906.58
Open Chanel Epoxy | IPC01TR0101 | 1 | Open Chanel Epoxy1 | 470400 | 266016 | 0 | 266016
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC03 | 3 | ElSewedy HQ Internal Finishing3 | 12533035.14 | 8552112.06 | 3483377.1 | 12035489.16
Red Sea Museum-Bab El-Bunt | K0003 Inv 01 | 1 | Red Sea Museum-Bab El-Bunt1 | 2538014.97 | 8756151.66 | 0 | 2918717.22
R05 (New) | IPC10TR0059 | 10 | R05 (New)10 | 31236.6 | 33246.76 | 0 | 33246.76
Open Channal | IPC08TR0074 | 8 | Open Channal8 | 118939.8 | 102597.47 | 0 | 102597.47
Koumassi Flyover | INV no.10 | 10 | Koumassi Flyover10 | 326864217.55 | 294177795.8 | 0 | 294177795.8
WADY EL-NATROUN BRIDGE(HST) | IPC no14 | 14 | WADY EL-NATROUN BRIDGE(HST)14 | 937184.63 | 838200.28 | 0 | 838200.28
Wadi El Natroun Bridge | inv ( 2 ) W. Natron | 2 | Wadi El Natroun Bridge2 | 1931400 | 55379.88 | 0 | 55379.88
Seashell Playa 5 Villas | Playa C470- ipc 7 | 7 | Seashell Playa 5 Villas7 | 99466.1 | 85898.91 | 0 | 85898.91
Capital One | inv (13 ) Captal one | 13 | Capital One13 | 678083.6 | 108089.995 | 0 | 108089.995
Faculty of Medicine | mansora finish ipc27 | 27 | Faculty of Medicine27 | 30831221.9 | 13404311 | 4624683.29 | 18028994.29
FX-05-22 Close compound | 102 |  | FX-05-22 Close compound | 71615.63 | 0 | 0 | #DIV/0!
Suez Gulf Substation | Forex |  | Suez Gulf Substation | 0.1 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 180068 |  | Beni-Suef Power Plant EPC | -202616757 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 16 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 430785.67 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 4 |  | Zafranaa - Ras Ghareb | 21538.63 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR-(7/8/12)EGP-Domia | 7 | W Dam PP Phase II (CP-117)7 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | Al-Lahoon Sub Inv +1 | 1 | Lahoon 220/22/221 | 522647.98 | 0 | 0 | #DIV/0!
Closed | CR(3_p.o52/156 |  | Closed | 0 | 0 | 0 | #DIV/0!
New Capital | Cr,Inv.7 | 7 | New Capital7 | 0 | 0 | 0 | #DIV/0!
Canal Sugar OHTL | تشيد سكر خط 220 |  | Canal Sugar OHTL | 5000 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | Cr. Adj Inv. 13 | 13 | Zafranaa - Beni Suef13 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Inv other ded. |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Open Channal | CAN.CR |  | Open Channal | 0 | 0 | 0 | #DIV/0!
Celia | CR-IPC#3 | 3 | Celia3 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 2 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 35142.34 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Rev (9 USD Shabab) |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Gabal Elgalalaa | Ret.OB Galalah |  | Gabal Elgalalaa | 1213769.83 | 0 | 0 | #DIV/0!
Containment Data Center- | 34 |  | Containment Data Center- | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10168 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
EGYTEC A1,A3 ( LP-05-21) | 59 |  | EGYTEC A1,A3 ( LP-05-21) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 272 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 6 | 6 | Marsa Alam/ Bernes LOT2 OHTL6 | 24428.57 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | Al-Lahoon Sub Inv +3 | 3 | Lahoon 220/22/223 | 1843216.21 | 0 | 0 | #DIV/0!
Maspiro Towers | D0019-OB-Dec-2020/Cr | 2020 | Maspiro Towers2020 | 0 | 0 | 0 | #DIV/0!
Central Capital | INV ( 6 ) Central Ca | 6 | Central Capital6 | 16380 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 8 EGP- Suez Gulf |  | Suez Gulf Substation | 2957422.0857 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 15 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 16158.31 | 0 | 0 | #DIV/0!
Mivida | IPC_7_Mivida | 7 | Mivida7 | 118510 | 0 | 0 | #DIV/0!
Ain Sokhna Port Development | ipc 23+24 elsokhna | 23 | Ain Sokhna Port Development23 | 925596 | 0 | 0 | #DIV/0!
Wadi Halfa Port | cr-wad halfa ipc05 | 5 | Wadi Halfa Port5 | 0 | 0 | 0 | #DIV/0!
West Port Said 220 kV GIS | P-45-EGY اتحاد تشيد | 45 | West Port Said 220 kV GIS45 | 5000 | 0 | 0 | #DIV/0!
ElMarg | D0043-OB-Dec-2020/Cr | 2020 | ElMarg2020 | 0 | 0 | 0 | #DIV/0!
ORA ZED - Ph 01B - Pkgs A&D | cr-ORA PH.1-IPC23 | 23 | ORA ZED - Ph 01B - Pkgs A&D23 | 0 | 0 | 0 | #DIV/0!
HSR | cancelHSR oct-5 | 5 | HSR5 | 0 | 0 | 0 | #DIV/0!
Ministry Building EPOXY | CR.TR0018CLOSING.DEC |  | Ministry Building EPOXY | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | CR 9 EGP-South Helw |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 44 |  | Suez Gulf Substation | 666000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 246 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Club House-Sodic Wesset | CR.TR0019CLOSING.DEC |  | Club House-Sodic Wesset | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | Refu.retention |  | Pyramids Industrial Park | 2262130.78 | 0 | 0 | #DIV/0!
ORA-ZED Towers01B | CR.IPC_4_ORA | 4 | ORA-ZED Towers01B4 | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-Kafr ShokrIPC01 | 1 | Kafr Shokr Bridge1 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11451 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
Giza North PP Ph I,II (CP-117) | CR-36 EGP-GizaN.I&II | 36 | Giza North PP Ph I,II (CP-117)36 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Trans.usd toegp |  | Abo Quir - Badr 500KV | 233093.09 | 0 | 0 | #DIV/0!
Air Defence College | IPC26TR0046.. | 26 | Air Defence College26 | 135222.68 | 0 | 0 | #DIV/0!
Damac 2x60/22 KV S/S | 8 |  | Damac 2x60/22 KV S/S | 1280709.49 | 0 | 0 | #DIV/0!
Borg El Arab Bridge - Km 21 | IPC#4#Kilo 21 | 4 | Borg El Arab Bridge - Km 214 | 122668.6 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Soci.1 To12 Mousa358 |  | Beni Seuf - 358 | 8174127 | 0 | 0 | #DIV/0!
October Under-Railway Tunnel | cr-oct.tunnel ipc2 | 2 | October Under-Railway Tunnel2 | 0 | 0 | 0 | #DIV/0!
Port Said | Cr. Adj Inv. 17 | 17 | Port Said17 | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange Building | cr.egy ex awnash 2fi |  | Egyptian Exchange Building | 0 | 0 | 0 | #DIV/0!
Infra Project 2524 | 220222001 |  | Infra Project 2524 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr.So12-16 assui | 16 | Akhmem Assiut16 | 0 | 0 | 0 | #DIV/0!
Zayed Monorail 66/22 KV GIS | Zayed Monorail Inv.1 | 1 | Zayed Monorail 66/22 KV GIS1 | 7123937.84 | 0 | 0 | #DIV/0!
MAYSAN 400/132kV SS | 227 |  | MAYSAN 400/132kV SS | 0 | 0 | 0 | #DIV/0!
October Dry Port | P-32-EGY اتحاد تشيد | 32 | October Dry Port32 | 5000 | 0 | 0 | #DIV/0!
SHAT Al ARAB 400/132kV SS | 208 |  | SHAT Al ARAB 400/132kV SS | -4240533.36 | 0 | 0 | #DIV/0!
Ameria | D0030-OB-Dec-2020/Cr | 2020 | Ameria2020 | 0 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | Invoice 23 (10) | 23 | Barwa 2x60/22 KV S/S23 | 0 | 0 | 0 | #DIV/0!
WPS Substation 3 | P-11-EGY اتحاد تشيد | 11 | WPS Substation 311 | 5000 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | CR_80 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
ORA ZED-Ph 2-Pkgs A&D | Cr Ora ph1 ipc(22) | 22 | ORA ZED-Ph 2-Pkgs A&D22 | 0 | 0 | 0 | #DIV/0!
LP-17-21 ODP-Computing | 92 |  | LP-17-21 ODP-Computing | 211225.15 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 53 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 7 EGP-(VO) adjust. |  | Suez Gulf Substation | 20565.0776 | 0 | 0 | #DIV/0!
Hosh Essa 220 KV OHTL | Hosh Essa USD Inv.02 | 2 | Hosh Essa 220 KV OHTL2 | 13116.19 | 0 | 0 | #DIV/0!
Cameron EDC | 024/2020cncl |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 180033 |  | Al-Shabab PP Phase II (CP-117) | -2073161.5524 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | CR_Inv 81 | 81 | Abou El Matameer and Sammanoud81 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | Inv.52 Qena Akhmem | 52 | Akhmem - Qena52 | 688.6 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 20 EGP - Shabab | 20 | Al-Shabab PP Phase II (CP-117)20 | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 87 |  | Governmental Campus-N2 | 234313 | 0 | 0 | #DIV/0!
Expansion of Ring Road-CFA | inv no2.2 d0079 | 2 | Expansion of Ring Road-CFA2 | 58014 | 0 | 0 | #DIV/0!
EPICO 3 Facility | cr material on site |  | EPICO 3 Facility | 0 | 0 | 0 | #DIV/0!
Abas El Akkad Bridge | D0035-OB-Dec-2020/Cr | 2020 | Abas El Akkad Bridge2020 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Close Zaafarana |  | Zafranaa - Ras Ghareb | 8035.51 | 0 | 0 | #DIV/0!
EGYTEC A1,A3 ( LP-05-21) | 51 |  | EGYTEC A1,A3 ( LP-05-21) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2008210002 |  | Miscellaneous Projects | 815592 | 0 | 0 | #DIV/0!
Akhmem - Qena | Ref.soci 51-52 Quna | 52 | Akhmem - Qena52 | 83237 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | 9/2 |  | Pyramids Industrial Park | 551706.16 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 91 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
EMAAR-PKG#107-MARASSI | cr VAT 2 PKG107 |  | EMAAR-PKG#107-MARASSI | 0 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 19 | 19 | Suez Gulf/S4 - 500KV OHTL19 | 194271.05 | 0 | 0 | #DIV/0!
New Giza 2 | OB-RE-New Giza 2 |  | New Giza 2 | 5444916.45 | 0 | 0 | #DIV/0!
MDF Factory | cr-mdfipc07 | 7 | MDF Factory7 | 0 | 0 | 0 | #DIV/0!
El Katameya Mall | CRINV(14) 28-10-20 | 14 | El Katameya Mall14 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_inv.5 | 5 | Akhmem - Qena5 | 0 | 0 | 0 | #DIV/0!
Ring Road Bridges Project | INV ( 10 ) Ring R | 10 | Ring Road Bridges Project10 | 6900702 | 0 | 0 | #DIV/0!
Al-Wukair 11 Substation | Cr.Memo-Expenses |  | Al-Wukair 11 Substation | 0 | 0 | 0 | #DIV/0!
Racecores 3092-15 132KV A | 11452 |  | Racecores 3092-15 132KV A | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | CR.Ret Zafra-B-Suef |  | Zafranaa - Beni Suef | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11582 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
Egyptian Exchange building | IPC00000010 | 10 | Egyptian Exchange building10 | 0 | 0 | 0 | #DIV/0!
Ghana | Cr.P 161 |  | Ghana | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180019 |  | Suez Gulf Substation | 336730.54 | 0 | 0 | #DIV/0!
JICA lot 02 | JICA lot 02 Inv.$ 02 |  | JICA lot 02 | 5909653.38 | 0 | 0 | #DIV/0!
British International School | cr-Bis ipc (2) | 2 | British International School2 | 0 | 0 | 0 | #DIV/0!
EGAT Injection | IPC17TR0048 | 17 | EGAT Injection17 | 52956 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cancle13-12-2018 | 12 | Abou El Matameer and Sammanoud12 | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 89 |  | Governmental Campus-N2 | 248466 | 0 | 0 | #DIV/0!
Benban 500 K.V / 100 K.M | تشيد بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 5000 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | MOC Inv-02 | 2 | MOC HQ at Diriyah2 | 2521761.64 | 0 | 0 | #DIV/0!
LP-19-21 N2 Extension | 99 |  | LP-19-21 N2 Extension | 3282236 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2007220004 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 57 |  | Al-Shabab PP Phase II (CP-117) | 2530842.34 | 0 | 0 | #DIV/0!
Ethiopia S/S | CR.P-27-09 AccRev | 27 | Ethiopia S/S27 | 0 | 0 | 0 | #DIV/0!
Bahr El Baqar Treatment Plant | D0036-OB-Dec-2020/Cr | 2020 | Bahr El Baqar Treatment Plant2020 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 41 |  | Suez Gulf Substation | 2886000 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Cr. Adj Inv 14 | 14 | Siemens 6x500/220 KV GIS-MOU14 | 0 | 0 | 0 | #DIV/0!
Dubai Port | CR.TR0005CLOSING.DEC |  | Dubai Port | 0 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 486 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180076 |  | Suez Gulf Substation | 3536.21 | 0 | 0 | #DIV/0!
New Heliopolis | Cr.Inv. 11 Heliopols | 11 | New Heliopolis11 | 0 | 0 | 0 | #DIV/0!
Air Force Project | P-12-EGY اتحاد تشيد | 12 | Air Force Project12 | 5000 | 0 | 0 | #DIV/0!
Ain-Sokhna PP (CP-117) | 2104220003 |  | Ain-Sokhna PP (CP-117) | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 256 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 61 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Closed | OB-ST-EL WAHAT |  | Closed | 2320.56 | 0 | 0 | #DIV/0!
Ring Road El Monib | inv ( 1 ) R.EL Monib | 1 | Ring Road El Monib1 | 1781000 | 0 | 0 | #DIV/0!
Port Said Grain Storage | rent-005 | 5 | Port Said Grain Storage5 | 144600 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 8 Euro-South Helwan |  | South Helwan PP (CP-117) | 257510.019 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2004220005 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR-18 EGP-West Domia | 18 | W Dam PP Phase II (CP-117)18 | 0 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | CR#10 WADY |  | WADY EL-NATROUN BRIDGE(HST) | -1255380 | 0 | 0 | #DIV/0!
Ahl Misr P3 – Zamalek Sector | CR-IPC#6 | 6 | Ahl Misr P3 – Zamalek Sector6 | 0 | 0 | 0 | #DIV/0!
Fish Market | CM SOUQ-SAMAK-IPC01 | 1 | Fish Market1 | -1763430.4 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 2004210014 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Club House-Sodic Wesset | 10073 |  | Club House-Sodic Wesset | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 88 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
6 Octobar Stores | IPC02TR0072 | 2 | 6 Octobar Stores2 | 70056 | 0 | 0 | #DIV/0!
FX-03-22 Urban Communities-WD | 98 |  | FX-03-22 Urban Communities-WD | 231883.8 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/004/adjCnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
Pridge 5 | CR/INV1 PRIDE 5 | 1 | Pridge 51 | 0 | 0 | 0 | #DIV/0!
Air Defence College | cancel TR46 IPC 11 | 11 | Air Defence College11 | 0 | 0 | 0 | #DIV/0!
ITS | Cr.Adv. ITS Inv. 01 | 1 | ITS1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 19 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 2580132 | 0 | 0 | #DIV/0!
Ministries A13-A14 | CR IPC_3_RedSea | 3 | Ministries A13-A143 | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Soc Abo.matmr labour |  | Abou El Matameer and Sammanoud | 397908 | 0 | 0 | #DIV/0!
UIC Project (LP-04-21) | 57 |  | UIC Project (LP-04-21) | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | D0007-OB-Dec-2020/Cr | 2020 | El Boghaz Brigde2020 | 0 | 0 | 0 | #DIV/0!
EMAAR-PKG#53-UPTOWN | CR-PKG#85/53 |  | EMAAR-PKG#53-UPTOWN | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | CR.Ma Alam Equ Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 11 EGP - Shabab | 11 | Al-Shabab PP Phase II (CP-117)11 | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-Tarekabdelhakim 1 |  | Tarek Abdel-Hakim Center | 0 | 0 | 0 | #DIV/0!
Residence 8 ( K10 ) | Inv ( 2 ) K 10 | 2 | Residence 8 ( K10 )2 | 125124.61 | 0 | 0 | 125124.61
Residence 8 ( S09 ) | Inv ( 1 ) S 09 | 1 | Residence 8 ( S09 )1 | 52676.63 | 0 | 0 | 52676.63
Tarek Abdel-Hakim Center | TAH ipc06 | 6 | Tarek Abdel-Hakim Center6 | 1234570.04 | 0 | 0 | 1234570.04
Tarek Abdel-Hakim Center | TAH ipc07 | 7 | Tarek Abdel-Hakim Center7 | 2195644.04 | 0 | 0 | 2195644.04
Tarek Abdel-Hakim Center | Tarek abdelhakim 01 |  | Tarek Abdel-Hakim Center | 1021554.87 | 0 | 0 | 1021554.87
Waldorf Astoria Cairo | Waldorf astoripc(19) | 19 | Waldorf Astoria Cairo19 | 12873774.16 | 0 | 0 | 13517462.868
El Katameya Mall | inv ( 13 )10-2020 | 13 | El Katameya Mall13 | 44072 | 0 | 0 | 44072
Ora Zed Landscape Ph1 | ora Landscape ipc 2 | 2 | Ora Zed Landscape Ph12 | 2071866.5 | 0 | 0 | 2175459.825
Cairo-Alex Railway | cairo alex ipc41 | 41 | Cairo-Alex Railway41 | 6779667 | 0 | 0 | 7118650.35
U3 & U5 | TR55/IPC/01 | 1 | U3 & U51 | 741275.46 | 0 | 0 | 741275.46
Port Said Port Silos | port said 1-supply |  | Port Said Port Silos | 673851.6 | 0 | 0 | 768190.824
October Under-Railway Tunnel | OCTOBER TUNNELIPC2 | 2 | October Under-Railway Tunnel2 | 4380339.19 | 0 | 0 | 4599356.1495
184E Substation | 11763 |  | 184E Substation | 155857.75 | 0 | 0 | 160157.75
Infra Project 2524 | 220621003 |  | Infra Project 2524 | 81703008.09 | 0 | 0 | 85788158.4945
Port Said Grain Storage | IPC#1 Port Saeid | 1 | Port Said Grain Storage1 | 1709400 | 0 | 0 | 1709400
Assuit PP (CP-118) | 220621001 |  | Assuit PP (CP-118) | 2850495.23 | 0 | 0 | 2993019.99
Ameria | FPC - Ameryia |  | Ameria | 120000 | 0 | 0 | 120000
Racecores 3092-17 132KV E | 11498 |  | Racecores 3092-17 132KV E | 11778.21 | 0 | 0 | 12109.4765
Nuweibaa (Swro) | 220321004 |  | Nuweibaa (Swro) | 308452.2 | 0 | 0 | 308452.2
Akhmem Assiut | Ref. Akhmem Asuit3T |  | Akhmem Assiut | 5000000 | 0 | 0 | 5000000
Ahl Misr P3 – Zamalek Sector | IPC#5&6 | 5 | Ahl Misr P3 – Zamalek Sector5 | 425700 | 0 | 0 | 425700
Ahl Misr P3 – Zamalek Sector | IPC#6 - Zamalek | 6 | Ahl Misr P3 – Zamalek Sector6 | 231900 | 0 | 0 | 231900
Miscellaneous Projects | 2102210004 |  | Miscellaneous Projects | 239998.68 | 479997.36 | 0 | 239998.68
AWEER POWER STATION 'H' Phase | ENG/040 |  | AWEER POWER STATION 'H' Phase | 371821.23 | 371821.23 | 0 | 389527
ORA-ZED Towers01B | IPC_4_Rowad_Ora | 4 | ORA-ZED Towers01B4 | 132779.22 | 0 | 0 | 132779.22
Abas El Akkad Bridge | D0035-OB-Dec-2020 | 2020 | Abas El Akkad Bridge2020 | 1393425 | 0 | 0 | 1393425
El-Herafeen brigde | D0042-OB-Dec-2020 | 2020 | El-Herafeen brigde2020 | 1263235 | 0 | 0 | 1263235
Sodic East | 10043 |  | Sodic East | 180185.97 | 0 | 0 | 180185.97
Ain-Sokhna PP (CP-117) | adj. rec 180137- |  | Ain-Sokhna PP (CP-117) | 28251.08 | 28251.08 | 0 | 28251.08
El Mostakbal City Project | Clo.مد وثيقة التامين |  | El Mostakbal City Project | 279055 | 0 | 0 | 279055
Benban 500 K.V/95 K.M | تشيد بنبان لوط 2 |  | Benban 500 K.V/95 K.M | 5000 | 0 | 0 | 5000
Cameron EDC | 022/2020 |  | Cameron EDC | 148684449.87 | 0 | 0 | 148684449.87
LAYYAH CCPP | MP-09 | 9 | LAYYAH CCPP9 | 8569800 | 0 | 0 | 8569800
AWEER POWER STATION 'H' Phase | 5001/12 |  | AWEER POWER STATION 'H' Phase | 13096334.05 | 13096334.05 | 0 | 13096334.05
Suez Gulf Substation | 1909210012 |  | Suez Gulf Substation | 499195.28 | 499195.28 | 0 | 499195.28
Suez Gulf Substation | 1909210004 |  | Suez Gulf Substation | 26812 | 26812 | 0 | 26812
Beni-Suef Power Plant EPC | Adj inv.180132 | 180132 | Beni-Suef Power Plant EPC180132 | 283799492.53 | 283799492.53 | 0 | 283799492.53
DPW Onshore Port & Terminal | DP WORLD-IPC06 | 6 | DPW Onshore Port & Terminal6 | 66782711.19 | 0 | 0 | 66782711.19
Beni-Suef Power Plant EPC | Inv. 17 EGP | 17 | Beni-Suef Power Plant EPC17 | 24516559.48 | 24516559.48 | 0 | 24516559.48
Mozambique TL | P-50-12 AccRev | 50 | Mozambique TL50 | 4823630 | 0 | 0 | 4823630
Zambia | P-2-10 AccRev | 2 | Zambia2 | 146431587 | 0 | 0 | 146431587
Abu Qir PP (CP-117) | 180152 |  | Abu Qir PP (CP-117) | 4019577.17 | 4019577.17 | 0 | 4019577.17
Kuwait | P-10-14 ADJ | 10 | Kuwait10 | 10946097.72 | 0 | 0 | 10946097.72
Ghana | P 161 ADJ |  | Ghana | 86324678.53 | 0 | 0 | 86324678.53
Suez Gulf Substation | 180078 |  | Suez Gulf Substation | 294832.33 | 279140.63 | 31015.63 | 310156.26
Suez Gulf Substation | 180061 |  | Suez Gulf Substation | 410529.35 | 388679.97 | 43186.66 | 431866.63
W Dam PP Phase II (CP-117) | 10 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 93003.52 | 93003.52 | 0 | 93003.52
Zafranaa - Ras Ghareb | In.1-14/2-14/3-12gha | 14 | Zafranaa - Ras Ghareb14 | 639342.58 | 0 | 0 | 3387.56
Barwa and Damac 220 OHTL | Adj Inv 3 | 3 | Barwa and Damac 220 OHTL3 | 9000846.43 | 0 | 0 | 9000846.43
PIP West 2 | Adj Inv 2 | 2 | PIP West 22 | 21544102.56 | 0 | 0 | 21544102.56
Beni-Suef Power Plant EPC | 180069 |  | Beni-Suef Power Plant EPC | 71416141.32 | 0 | 0 | 71416141.32
Apache Electrical Works | 5 |  | Apache Electrical Works | 76066343 | 0 | 0 | 76066343
Tebbin PP Rehabitation(CP-124) | 13 |  | Tebbin PP Rehabitation(CP-124) | 12876077 | 0 | 0 | 12876077
Suez IPB | 122 |  | Suez IPB | 6959007.1398 | 0 | 0 | 6959007.1398
W Dam PP Phase II (CP-117) | 180044 |  | W Dam PP Phase II (CP-117) | 10445.3048 | 0 | 0 | 10967.57
Abu Qir PP (CP-118) | 31 |  | Abu Qir PP (CP-118) | 420405.0921 | 0 | 0 | 420405.0921
Tebbin PP Rehabitation (CP106) | 82 |  | Tebbin PP Rehabitation (CP106) | 125133.41 | 0 | 0 | 125133.41
Al-Wukair 11 Substation | 77 |  | Al-Wukair 11 Substation | 276134509.4865 | 0 | 0 | 276134509.4865
W Dam PP Phase II (CP-117) | 180036 |  | W Dam PP Phase II (CP-117) | 47134.4857 | 0 | 0 | 49491.21
IRAQ - Substations Soil Invest | 37 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
Giza North PP Ph I,II (CP-117) | 4 |  | Giza North PP Ph I,II (CP-117) | 43917116 | 0 | 0 | 43917116
Giza North PP Phase3(CP-117) | 7 |  | Giza North PP Phase3(CP-117) | 29807353.76 | 0 | 0 | 29807353.76
Giza North PP Phase3(CP-117) | 84 |  | Giza North PP Phase3(CP-117) | -24375617.1533 | 0 | 0 | -24375617.1533
6th Oct. Ph2 PP-Elect Work | 9 |  | 6th Oct. Ph2 PP-Elect Work | 11271114 | 0 | 0 | 11271114
Giza North PP Ph I,II (CP-117) | DR - VAT - Egytech |  | Giza North PP Ph I,II (CP-117) | 345309.59 | 345309.59 | 0 | 345309.59
W Dam PP Phase II (CP-117) | 35 |  | W Dam PP Phase II (CP-117) | 35639.52 | 0 | 0 | 35639.52
New Heliopolis | Inv.7 Heliopolis | 7 | New Heliopolis7 | 3631713.98 | 0 | 0 | 3631713.98
Abou El Matameer and Sammanoud | Inv 80 P4 Sammound | 80 | Abou El Matameer and Sammanoud80 | 5875862.86 | 0 | 0 | 5875862.86
Akhmem - Qena | Inv.12 Akhmem Qena | 12 | Akhmem - Qena12 | 26867410.18 | 0 | 0 | 26867410.18
Akhmem - Qena | Inv.11 Akhmem Qena | 11 | Akhmem - Qena11 | 31190172.66 | 0 | 0 | 31190172.66
Akhmem - Qena | Inv.10 Akhmem Qena | 10 | Akhmem - Qena10 | 14206943.63 | 0 | 0 | 14206943.63
Akhmem - Qena | Inv. 8 Akhmem Qena | 8 | Akhmem - Qena8 | 893041.7 | 0 | 0 | 893041.7
Akhmem - Qena | Inv. 5 Akhmem Qena | 5 | Akhmem - Qena5 | 69969724.95 | 0 | 0 | 69969724.95
Beni-Suef Power Plant EPC | Dr on Sewedy Holding |  | Beni-Suef Power Plant EPC | 232187 | 232187 | 0 | 232187
Barwa 2x60/22 KV S/S | 2 |  | Barwa 2x60/22 KV S/S | 1000 | 0 | 0 | 1000
Kayan 3 New Cairo Capital City | OB-SI-EL Kayaan |  | Kayan 3 New Cairo Capital City | 132593.05 | 0 | 0 | 132593.05
IRAQ - Al-Diwaniya Power Plant | 65 USD - Diwaniya |  | IRAQ - Al-Diwaniya Power Plant | 1178165.5524 | 0 | 0 | 1237073.83
Palm Hill-Infra Str(Elec.Work) | 7 EGP - palm hills |  | Palm Hill-Infra Str(Elec.Work) | 699577.96 | 0 | 0 | 769535.756
Suez Gulf Substation | 2 USD/123/2011/2012 |  | Suez Gulf Substation | 321146.2451 | 0 | 0 | 325000
Cameron EDC | 028/2020 FCV |  | Cameron EDC | 175964727.63 | 87982363.81 | 0 | 87982363.81
W Dam PP Phase II (CP-117) | 180041 |  | W Dam PP Phase II (CP-117) | 212073.6762 | 0 | 0 | 222677.36
Al-Shabab PP Phase II (CP-117) | 180028 |  | Al-Shabab PP Phase II (CP-117) | 25777.9143 | 0 | 0 | 27066.81
Al-Shabab PP Phase II (CP-117) | 19 EGP - Shabab 117 |  | Al-Shabab PP Phase II (CP-117) | 2580132 | 0 | 406370.79 | 406370.79
W Dam PP Phase II (CP-117) | 15 EGP -West D. 117 |  | W Dam PP Phase II (CP-117) | 252473.1714 | 0 | 39764.52 | 39764.52
W Dam PP Phase II (CP-117) | 2 EGP - West.D 117 |  | W Dam PP Phase II (CP-117) | 41431.67 | 35639.52 | 6289.33 | 41928.85
W Dam PP Phase II (CP-117) | 3 USD - West D. 117 |  | W Dam PP Phase II (CP-117) | 1814725.2767 | 0 | 275475.3 | 1836501.98
Suez Gulf Substation | 6 USD/123/2011/2012 |  | Suez Gulf Substation | 371737.6 | 0 | 0 | 371737.6
Abo Quir - Badr 500KV | Inv 74 Abu Quir Badr | 74 | Abo Quir - Badr 500KV74 | 1639063.13 | 0 | 327812.63 | 327812.63
Damac 2x60/22 KV S/S | Damac 14 |  | Damac 2x60/22 KV S/S | 2415534.88 | 1708800.38 | 362330.25 | 2071130.63
South Helwan PP (CP-117) | 2 Euro- South Helwan |  | South Helwan PP (CP-117) | 55261.12 | 58024.176 | 0 | 58024.176
Beni Suef Substation R61 | BSF-SD-EUR-02 | 2 | Beni Suef Substation R612 | 650978.28 | 538871.07 | 97646.74 | 636517.81
Al Mostathmreen GIS Substation | MOS-SD-EGP-22 | 22 | Al Mostathmreen GIS Substation22 | 1745640 | 1300501.8 | 261846 | 1562347.8
Tamey El-amdeed Substation | TAM-SW-EGP-01 | 1 | Tamey El-amdeed Substation1 | 634375 | 472609.37 | 95156.25 | 567765.62
Tamey El-amdeed Substation | (3)cw almansora |  | Tamey El-amdeed Substation | 3819167.14 | 2844752.9 | 572875.07 | 3417627.97
Al Mostathmreen GIS Substation | 7sd euro mosstasmree |  | Al Mostathmreen GIS Substation | 1114848 | 808264.12 | 167227.3 | 975491.42
Beni Seuf - 358 | Inv. 16 Oewon Mousa | 16 | Beni Seuf - 35816 | 5877613.75 | 0 | 1010855.15 | 1010855.15
Beni Seuf - 358 | Inv. 7 Oewon Mousa | 7 | Beni Seuf - 3587 | 3768028.61 | 2603908.97 | 636595.64 | 3240504.61
New Giza 2 | OB-ST-New Giza 2 |  | New Giza 2 | 115829.98 | 115829.98 | 0 | 115829.98
Giza North PP Ph I,II (CP-117) | 40 EGP-Giza N. I&II |  | Giza North PP Ph I,II (CP-117) | 28871.3333 | 30314.9 | 0 | 30314.9
EMAAR-PKG#53-UPTOWN | OB-ST- PKG#53 |  | EMAAR-PKG#53-UPTOWN | 308431.19 | 308431.19 | 0 | 308431.19
PIP Zona 2 | Inv. 3 Zona 2 | 3 | PIP Zona 23 | 3505222.55 | 3294909.1975 | 0 | 3294909.1975
Borolos Over Head | Balance |  | Borolos Over Head | 2100000 | 1870602.15 | 0 | 1970602.15
Suez Gulf Substation | Colle Suez Gul 34567 |  | Suez Gulf Substation | 7191000 | 7191000 | 0 | 7191000
Beni Suef COMCAVI | Inv 7 Comcavi | 7 | Beni Suef COMCAVI7 | 2036941.11 | 2036941.11 | 0 | 2036941.11
Apache Electrical Works | Apachi Inv No PC.#19 |  | Apache Electrical Works | 39634.79 | 39634.79 | 0 | 39634.79
Kayan 3 New Cairo Capital City | EL KAYAN MEP- IPC 3 | 3 | Kayan 3 New Cairo Capital City3 | 76333661 | 66272397.35 | 3000000 | 69272397.35
EMAAR-PKG#53-UPTOWN | OB-RE-PKG#53 |  | EMAAR-PKG#53-UPTOWN | 6555257.77 | 0 | 0 | 0
Al Mostathmreen GIS Substation | (10) CW |  | Al Mostathmreen GIS Substation | 670146 | 499258.57 | 100522.02 | 599780.59
W Dam PP Phase II (CP-117) | 8 USD- West Domiat |  | W Dam PP Phase II (CP-117) | 593704.09 | 593704.09 | 0 | 593704.09
Kuwait | 2-132KVA-J | 132 | Kuwait132 | 54755.32 | 41066.49 | 0 | 41066.49
Royal City | (3)royal city |  | Royal City | 7725328 | 7924629.02 | 1500964.3 | 9425593.32
Cairo South PP Rehabilitation | 9 USD - Cairo South |  | Cairo South PP Rehabilitation | 27162.77 | 27162.77 | 0 | 27162.77
Ghana | 37/P/10/ER/2017/USD |  | Ghana | 59795.74 | 59781.25 | 0 | 59781.25
Siemens 6x500/220 KV GIS-MOU | Inv 84 P13 Assuit | 84 | Siemens 6x500/220 KV GIS-MOU84 | 1473372.7 | 1056015.33 | 221005.91 | 1277021.24
Abou El Matameer and Sammanoud | Inv 73 P3Abo Matamir | 73 | Abou El Matameer and Sammanoud73 | 9985043.36 | 7223180.36 | 1497756.5 | 8720936.86
Badr | Inv. 23 Badr | 23 | Badr23 | 4554739.85 | 3381482.8 | 683211 | 4064693.8
Badr | Inv. 5 Badr | 5 | Badr5 | 7202522.86 | 5347452.7 | 1080378.45 | 6427831.15
Siemens 6x500/220 KV GIS-MOU | Soci. 72Asuit 10 |  | Siemens 6x500/220 KV GIS-MOU | 115457.3 | 115457.3 | 0 | 115457.3
Suez Gulf Substation | Inv 3 EGP VO SG | 3 | Suez Gulf Substation3 | 993961.3619 | 939293.49 | 104365.94 | 1043659.43
Kayan 3 New Cairo Capital City | (2)elkayan fainshing |  | Kayan 3 New Cairo Capital City | 26989555 | 11242619.75 | 13250000 | 24492619.75
Al Mostathmreen GIS Substation | (32)sd elmostsmrin |  | Al Mostathmreen GIS Substation | 139309 | 108531.2 | 20896.35 | 129427.55
New Heliopolis | ref.siite electricit |  | New Heliopolis | 2000 | 1998.79 | 0 | 1998.79
Akhmem - Qena | Soci. 1&2 Qina Akhme |  | Akhmem - Qena | 3994754.86 | 3994754.86 | 0 | 3994754.86
Assuit PP (CP-118) | 2110210005 |  | Assuit PP (CP-118) | 463083.99 | 486238.19 | 0 | 486238.19
Assuit PP (CP-118) | 2101210002 |  | Assuit PP (CP-118) | 70200.44 | 62653.89 | 11056.57 | 73710.46
Assuit PP (CP-118) | 1906210014 |  | Assuit PP (CP-118) | 108568.3 | 96897.21 | 17099.51 | 113996.72
Assuit PP (CP-118) | 2002210015 |  | Assuit PP (CP-118) | 2116105.4 | 1867463.02 | 333286.6 | 2200749.62
Assuit PP (CP-118) | 520 |  | Assuit PP (CP-118) | 2559390.19 | 2258661.85 | 403103.95 | 2661765.8
Assuit PP (CP-118) | 1907210001 |  | Assuit PP (CP-118) | 269254.5 | 240309.65 | 42407.58 | 282717.23
Assuit PP (CP-118) | 180165 |  | Assuit PP (CP-118) | 163099.07 | 145565.92 | 25688.1 | 171254.02
South Helwan PP (CP-117) | Dr-Memo_Inv#19-EGP02 | 19 | South Helwan PP (CP-117)19 | 23885.1 | 23885.1 | 0 | 23885.1
Marsa Matrouh 500KV | Inv.32 Borg Alarab | 32 | Marsa Matrouh 500KV32 | 95611.43 | 83516.09 | 10039.2 | 93555.29
Akhmem Assiut | Ref.Social.4/5 Assui |  | Akhmem Assiut | 2999691.3 | 2999691.3 | 0 | 2999691.3
Abou El Matameer and Sammanoud | Inv 77 P5Abo Matamir | 77 | Abou El Matameer and Sammanoud77 | 6735132.2 | 4872194.63 | 1010269.83 | 5882464.46
kayan wall lock & Load | (1)elkayan lock+load |  | kayan wall lock & Load | 21438000 | 18666574.1 | 0 | 18666574.1
Military 110 Kayan Project | Elkayan Inv.12 | 12 | Military 110 Kayan Project12 | 8621922.75 | 7462365.75 | 0 | 7462365.75
Apache Electrical Works | ApatchiInv No P.C#16 |  | Apache Electrical Works | 281018.5 | 281018.5 | 0 | 281018.5
Lina Farm Substation | Ret. Balance |  | Lina Farm Substation | 66596.54 | 66596.54 | 0 | 66596.54
Akhmem Assiut | Inv.2 Assuit Akhmem$ | 2 | Akhmem Assiut2 | 1023877.33 | 865978.87 | 0 | 865978.87
Military 110 Kayan Project | Elkayan Inv.13 | 13 | Military 110 Kayan Project13 | 11919021.38 | 10816106.25 | 0 | 10816106.25
Akhmem Assiut | Inv.9 Assuit Akhmem$ | 9 | Akhmem Assiut9 | 1110147.4 | 937877.35 | 0 | 937877.35
NUCA R05 - Z02 | R5-ZONE2- IPC7 | 7 | NUCA R05 - Z027 | 32455409 | 25485572.57 | 3181003.7 | 28666576.27
New Capital Tunnels | IPC3-M.ZAYD TUNNLE | 3 | New Capital Tunnels3 | 39415048.58 | 18748.3 | 0 | 35368748.3
Akhmem - Qena | Ref.InstilNo.1 Qena |  | Akhmem - Qena | 50866194.1 | 50866194.1 | 0 | 50866194.1
El-Nyaba El-Ama | El-Nayba Inv. 3 | 3 | El-Nyaba El-Ama3 | 3364450.65 | 2750033.55 | 252333.8 | 3002367.35
Marsa Matrouh 500KV | Inv.2 Borg Alarab | 2 | Marsa Matrouh 500KV2 | 65050776.78 | 65050776.78 | 0 | 65050776.78
Akhmem Assiut | Inv.13Assuit Akhmem$ | 13 | Akhmem Assiut13 | 1422550.68 | 1206606.61 | 0 | 1206606.61
Al Mostathmreen GIS Substation | MOS-SD-EGP-26 | 26 | Al Mostathmreen GIS Substation26 | 658215.6 | 490370.62 | 98732.34 | 589102.96
Akhmem - Qena | Ref Installation 2 Q |  | Akhmem - Qena | 35936571.43 | 35936571.43 | 0 | 35936571.43
Military 110 Kayan Project | Elkayan Inv.14 | 14 | Military 110 Kayan Project14 | 4202691.67 | 3792524.7 | 0 | 3792524.7
Tamey El-amdeed Substation | TAM-SD-EGP-01 | 1 | Tamey El-amdeed Substation1 | 271650 | 202379.25 | 40747.5 | 243126.75
Akhmem Assiut | Inv.7 Assuit Akhmem$ | 7 | Akhmem Assiut7 | 2317274.58 | 1953940.23 | 0 | 1953940.23
Substation Elco Steel | PSPELCO-IPC 05 | 5 | Substation Elco Steel5 | 5784479.69 | 4588851.87 | 1156895.94 | 5745747.81
Military 110 Kayan Project | Elkayan Inv.15 | 15 | Military 110 Kayan Project15 | 2387909.47 | 2154686.65 | 0 | 2154686.65
Elsewedy Univ - Enabling Works | ELSEWEDY UNI-MEP2 |  | Elsewedy Univ - Enabling Works | 5976537.11 | 6754267.5655 | 1255072.79 | 8009340.3555
AWEER POWER STATION 'H' Phase | CON 035 |  | AWEER POWER STATION 'H' Phase | 319424.66 | 0 | 35491.63 | 35491.63
AWEER POWER STATION 'H' Phase | IMP/062 Rev0 |  | AWEER POWER STATION 'H' Phase | 1352629.53 | 1149663.2875 | 150292.17 | 1299955.4575
AWEER POWER STATION 'H' Phase | IMP/060 |  | AWEER POWER STATION 'H' Phase | 866261.45 | 790463.57 | 0 | 790463.57
AWEER POWER STATION 'H' Phase | Loc-008 | 8 | AWEER POWER STATION 'H' Phase8 | 1387024.56 | 1371591.18 | 0 | 1371591.18
AWEER POWER STATION 'H' Phase | Con-010 rev0 | 10 | AWEER POWER STATION 'H' Phase10 | 1419665.16 | 1263430.18 | 0 | 1405396.69
AWEER POWER STATION 'H' Phase | CON-008 | 8 | AWEER POWER STATION 'H' Phase8 | 1277698.65 | 1121535.47 | 141966.521 | 1263501.991
South Helwan PP (CP-117) | 180153 |  | South Helwan PP (CP-117) | 70286.47 | 73208.98 | 0 | 73208.98
Beni Suef Substation R61 | BSF-CW-EUR-02 | 2 | Beni Suef Substation R612 | 660897.29 | 503546.17 | 99134.59 | 602680.76
Phosfat | Inv.4 Phosfat | 4 | Phosfat4 | 400851 | 357362.9 | 0 | 357362.9
Asec Spare-Parts | Inv 2 Asec Sparepart | 2 | Asec Spare-Parts2 | 905120 | 800208 | 226280 | 1026488
DPW Onshore Port & Terminal | DPW IPC029 | 29 | DPW Onshore Port & Terminal29 | 27690935.6 | 20394668.34 | 4153640.34 | 24548308.68
Zafranaa - Ras Ghareb | Sus.Penalety Ghareeb |  | Zafranaa - Ras Ghareb | -8034.1 | 0 | 0 | -8034.1
Akhmem Assiut | Soc.38-43 Assuit | 43 | Akhmem Assiut43 | 520753.57 | 520753.57 | 0 | 520753.57
Phosfat | Inv.3 Phosfat | 3 | Phosfat3 | 1155861.3 | 1031209.75 | 0 | 1031209.75
Kuwait | Civil/J010 |  | Kuwait | 35275.18 | 26456.39 | 0 | 26456.39
Akhmem Assiut | Ref.Instal1$ Assuit |  | Akhmem Assiut | 85910.91 | 85060 | 0 | 85060
Ismalia Bridge | Ismailia U3 -IPC2 | 2 | Ismalia Bridge2 | 4468989.34 | 4256312.3 | 0 | 4256312.3
Roots -Kafr ElSheikh Bridge | IPC# Final |  | Roots -Kafr ElSheikh Bridge | 40800 | 0 | 0 | 39984
Manshiet Nasser Substation | 2102210003 |  | Manshiet Nasser Substation | 62140.65 | 13365.15 | 9321.1 | 22686.25
Manshiet Nasser Substation | 546 |  | Manshiet Nasser Substation | 3763.04 | 2801 | 594.16 | 3395.16
Manshiet Nasser Substation | 1904210018 |  | Manshiet Nasser Substation | 9322.65 | 7924.25 | 1398.4 | 9322.65
EMAAR-PKG#53-UPTOWN | PKG#53 -IPC 38 | 38 | EMAAR-PKG#53-UPTOWN38 | 726341.65 | 2284218.6225 | 0 | 2284218.6225
Abou El Matameer and Sammanoud | Inv 99 P15Abo Matami | 99 | Abou El Matameer and Sammanoud99 | 4435698.44 | 3059273.97 | 665354.77 | 3724628.74
Kayan 3 New Cairo Capital City | KAYAN FINISHING-IPC6 | 6 | Kayan 3 New Cairo Capital City6 | 44346905.25 | 20011341.75 | 20011344 | 40022685.75
Phosfat | Inv.5 Phosfat | 5 | Phosfat5 | 396824.45 | 353768.05 | 0 | 353768.05
MOTHANA 400/132kV SS | 229 |  | MOTHANA 400/132kV SS | 608929.16 | 608929.16 | 0 | 608929.16
AWEER POWER STATION 'H' Phase | 10050 |  | AWEER POWER STATION 'H' Phase | 286803.1 | 301143.255 | 0 | 301143.255
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 29 | 29 | Benban 500 K.V/95 K.M29 | 294497.14 | 227064.7 | 30922.2 | 257986.9
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 18 | 18 | Benban 500 K.V/95 K.M18 | 4365592.53 | 3365276.96 | 458387.22 | 3823664.18
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 16 | 16 | Benban 500 K.V/95 K.M16 | 2348261.32 | 1810514.82 | 246567.44 | 2057082.26
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 8 | 8 | Benban 500 K.V/95 K.M8 | 922953 | 711599.33 | 96910.07 | 808509.4
Benban 500 K.V / 100 K.M | Benban Lot 1 Inv. 18 | 18 | Benban 500 K.V / 100 K.M18 | 609441.4 | 469886.28 | 63991.35 | 533877.63
South Helwan PP (CP-117) | Inv.40 deductions | 40 | South Helwan PP (CP-117)40 | 7459.4 | 7459.4 | 0 | 7459.4
Marsa Matrouh 500KV | Inv.17 Borg Alarab | 17 | Marsa Matrouh 500KV17 | 4562801.6 | 3985608.41 | 479094.17 | 4464702.58
Marsa Matrouh 500KV | Inv.18 Borg Alarab | 18 | Marsa Matrouh 500KV18 | 43700303.53 | 38172221.76 | 4588531.87 | 42760753.63
Canal Sugar S/s | Inv 6 Sugar S/s | 6 | Canal Sugar S/s6 | 60958313.15 | 48157067.39 | 9143746.97 | 57300814.36
Elco Steel 220/33 KV SS | 1903210015 |  | Elco Steel 220/33 KV SS | 4045768.95 | 8496114.8 | 0 | 4248057.4
4 SS - Technical Service | 239 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Akhmem - Qena | Ref.Ret 20%Qena |  | Akhmem - Qena | 1774568.26 | 1773966.11 | 0 | 1773966.11
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC22 | 22 | EMAAR- Pkg 140-ITP-Mivida22 | 5467007.05 | 4603109.1525 | 574035.74 | 5177144.8925
Akhmem Assiut | Social 49 Assuit |  | Akhmem Assiut | 48705.75 | 48705.75 | 0 | 48705.75
Royal City | ROYAL CITY FIN-IPC06 | 6 | Royal City6 | 12948953.9 | 9240902.25 | 2498771.15 | 11739673.4
Port Said Subs 220/66 | Port Said Inv. 7 | 7 | Port Said Subs 220/667 | 36684942.02 | 21827135 | 9171235.51 | 30998370.51
Tamey El-amdeed Substation | TAM-CW-EGP-17 | 17 | Tamey El-amdeed Substation17 | 3347787.42 | 2477362.7 | 502168.11 | 2979530.81
EMAAR-PKG# 101-UPTOWN | PKG#101 -IPC06 | 6 | EMAAR-PKG# 101-UPTOWN6 | 2226073.87 | 2051541.97 | 1066234.31 | 3117776.28
Suez IPB | 2 USD - Suez Steel |  | Suez IPB | 675.89 | 675.89 | 0 | 675.89
SHAT Al ARAB 400/132kV SS | 243 |  | SHAT Al ARAB 400/132kV SS | 255045.23 | 255045.23 | 0 | 255045.23
SHATRA 400/132kV SS | 261 |  | SHATRA 400/132kV SS | 544712.1 | 544712.1 | 0 | 544712.1
MOTHANA 400/132kV SS | 255 |  | MOTHANA 400/132kV SS | 608298.72 | 608298.72 | 0 | 608298.72
Latin Compound - New Alamin | inv ( 22 ) 13-12-20 | 22 | Latin Compound - New Alamin22 | 786553.6 | 49725.46 | 157310.72 | 207036.18
Latin Compound - New Alamin | INV(13)150620 | 13 | Latin Compound - New Alamin13 | 304463.6 | 249907.38 | 0 | 249907.38
Mahmoudia Additional Scope | Inv. 1 EUR & EGP AMm | 1 | Mahmoudia Additional Scope1 | 19798312.5 | 19540937.37 | 0 | 19540937.37
Beni Suef Add-on Sales | 1908210011 |  | Beni Suef Add-on Sales | 255228.8 | 283303.97 | 0 | 283303.97
SHATRA 400/132kV SS | 267 |  | SHATRA 400/132kV SS | 500773.71 | 500773.71 | 0 | 500773.71
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 1 | 1 | Marsa Alam/ Bernes LOT2 OHTL1 | 44190920.45 | 24791099.66 | 4640046.65 | 29431146.31
Ismailiya East Substation | ISE-SD-EURO-01 | 1 | Ismailiya East Substation1 | 2652366.6 | 2163351.2 | 197255.07 | 2360606.27
33KV Canal Farm Grid | Inv. 11 Farm | 11 | 33KV Canal Farm Grid11 | 16845205.87 | 12852892.08 | 2526780.88 | 15379672.96
Tunnel of Sokhna Road (2) | SOKHNA TUNLE2-IPC02F | 2 | Tunnel of Sokhna Road (2)2 | 4550425 | 2166935.25 | 2166940 | 4333875.25
HyperOne Zayed Extension | HYPER ONE-IPC14 | 14 | HyperOne Zayed Extension14 | 5698546.6 | 4476191 | 1424635 | 5900826
Gesr El suez | Claim |  | Gesr El suez | 75000 | 75000 | 0 | 75000
Benban 500 K.V/95 K.M | Benban Lot2 Inv 8 $ | 8 | Benban 500 K.V/95 K.M8 | 46035.04 | 38669.43 | 4833.68 | 43503.11
SHATRA 400/132kV SS | 269 |  | SHATRA 400/132kV SS | 147363.81 | 147363.81 | 0 | 147363.81
MAYSAN 400/132kV SS | 277 |  | MAYSAN 400/132kV SS | 872403.51 | 872403.51 | 0 | 872403.51
Ghana Street lighting | MIDA Ins. Inv.5 | 5 | Ghana Street lighting5 | 79814.12 | 71829.75 | 0 | 71829.75
Ghana Street lighting | MIDA Ins. Inv. 4 | 4 | Ghana Street lighting4 | 54959.5 | 54959.5 | 0 | 54959.5
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 13 | 13 | Benban 500 K.V/95 K.M13 | 224967.76 | 173452.84 | 23621.62 | 197074.46
EMAAR-PKG117- MARASSI | PKG#117-IPC12 | 12 | EMAAR-PKG117- MARASSI12 | 2921423.41 | 3430971.3805 | 0 | 3430971.3805
MAYSAN 400/132kV SS | 280 |  | MAYSAN 400/132kV SS | 951144.62 | 951144.62 | 0 | 951144.62
MAYSAN 400/132kV SS | 279 |  | MAYSAN 400/132kV SS | 95508.96 | 95508.96 | 0 | 95508.96
MOTHANA 400/132kV SS | 281 |  | MOTHANA 400/132kV SS | 1488764.49 | 1488764.49 | 0 | 1488764.49
ESU Ph2-Enabling & Struc | ESU2 ENABLE-IPC2 | 2 | ESU Ph2-Enabling & Struc2 | 9229848.29 | 8526565.2945 | 305476.53 | 8832041.8245
Celia | IPC#4 | 4 | Celia4 | 263685.03 | 240744.43 | 0 | 240744.43
Mahmoudia Additional Scope | Cr. Note reclass |  | Mahmoudia Additional Scope | 0 | -19798312.5 | 0 | -19798312.5
Beni-Suef Power Plant EPC | 1907210005 |  | Beni-Suef Power Plant EPC | 15575298.86 | 15575298.86 | 0 | 15575298.86
Elco Steel 220/33 KV SS | 1901210005 |  | Elco Steel 220/33 KV SS | 3867608.88 | 4060989.32 | 0 | 4060989.32
MAYSAN 400/132kV SS | 286 |  | MAYSAN 400/132kV SS | 57277.09 | 57277.09 | 0 | 57277.09
MAYSAN 400/132kV SS | 285 |  | MAYSAN 400/132kV SS | 535440.2 | 535440.2 | 0 | 535440.2
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .22 | 22 | Benban 3/ Toshka 2 LOT 422 | 1185100.78 | 932281.41 | 124435.58 | 1056716.99
CFC Podium 2 | CFC-IPC01 | 1 | CFC Podium 21 | 6586123.18 | 6200445.359 | 746907.51 | 6947352.869
Royal City | ROYAL ZONE-IPC01 | 1 | Royal City1 | 1714285.71 | 1782857.1355 | 0 | 1782857.1355
EMAAR- Pkg 140-ITP-Mivida | 20100001 |  | EMAAR- Pkg 140-ITP-Mivida | 7170532.11 | 6547225.82 | 840511.96 | 7387737.78
Badr 500 S/S / Zizenia 220 Kv | Badr-Zizenia Inv.2 | 2 | Badr 500 S/S / Zizenia 220 Kv2 | 2936556 | 1725832.9 | 734139 | 2459971.9
Zafranaa - Ras Ghareb | Abolila Zafra kharb- |  | Zafranaa - Ras Ghareb | 69944 | 66749.5 | 0 | 66749.5
Manshiet Nasser Substation | 504 |  | Manshiet Nasser Substation | 4964442.6 | 2708454.87 | 0 | 2708454.87
CFC Podium 2 | CFC-IPC13 | 13 | CFC Podium 213 | 13989651.96 | 23213755.8 | 4308604.78 | 27522360.58
EDNC Retail & Offices Civil | SOREAL-IPC10 | 10 | EDNC Retail & Offices Civil10 | 82638241.08 | 33486093.464 | 0 | 33486093.464
Toshka GIS 500 kV | Toshka Sub Inv. 24.$ | 24 | Toshka GIS 500 kV24 | 25418.1 | 14193.95 | 6672.25 | 20866.2
Miscellaneous Projects | 2002210025 |  | Miscellaneous Projects | 2705.17 | 3002.73 | 0 | 3002.73
Akhmem - Qena | Re soc Inv 24 Quna | 24 | Akhmem - Qena24 | 730.39 | 730.39 | 0 | 730.39
Ministry Building EPOXY | 10017 |  | Ministry Building EPOXY | 8038.67 | 7556.35 | 0 | 7556.35
Baron Palace | 10076 |  | Baron Palace | 13094.4 | 11654.02 | 0 | 11654.02
Sodic Wesset | 10023 |  | Sodic Wesset | 81830 | 74710.7958 | 0 | 74710.7958
SHAT Al ARAB 400/132kV SS | 320 |  | SHAT Al ARAB 400/132kV SS | 427366.81 | 427366.81 | 0 | 427366.81
MAYSAN 400/132kV SS | 309 |  | MAYSAN 400/132kV SS | 38529.77 | 38529.77 | 0 | 38529.77
SHAT Al ARAB 400/132kV SS | 324 |  | SHAT Al ARAB 400/132kV SS | 342052.44 | 342052.44 | 0 | 342052.44
SHATRA 400/132kV SS | 341 |  | SHATRA 400/132kV SS | 794555.75 | 794555.75 | 0 | 794555.75
MOTHANA 400/132kV SS | 318 |  | MOTHANA 400/132kV SS | 511828.9 | 511828.9 | 0 | 511828.9
MOTHANA 400/132kV SS | 317 |  | MOTHANA 400/132kV SS | 276832.06 | 276832.06 | 0 | 276832.06
MOTHANA 400/132kV SS | 316 |  | MOTHANA 400/132kV SS | 125524.85 | 125524.85 | 0 | 125524.85
Elhegaz | IPC#1 | 1 | Elhegaz1 | 2073000 | 77808.5 | 0 | 2052270
4 SS - Technical Service | 344 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Benban 4 As El-Nakra 220 K.V | Inv.1 Final ElNokra. | 1 | Benban 4 As El-Nakra 220 K.V1 | 6953627.16 | 6456442.88 | 0 | 6456442.88
AWEER POWER STATION 'H' Phase | Eng-027 rev0 | 27 | AWEER POWER STATION 'H' Phase27 | 35689.97 | 37474.4685 | 0 | 37474.4685
ESU Ph2-Enabling & Struc | E.S.U2 ARCH&MEP-IPC2 | 2 | ESU Ph2-Enabling & Struc2 | 21431317.62 | 5698476.15 | 6675234.63 | 33433624.13
R5 | inv(5)100220 | 5 | R55 | 1399065 | 740392.25 | 0 | 1273424.31
Multi Sport Hall | 10153 |  | Multi Sport Hall | 150313.25 | 133778.8 | 0 | 133778.8
W Dam PP Phase II (CP-117) | 2002210030 |  | W Dam PP Phase II (CP-117) | 19430.12 | 20440 | 0 | 20440
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .1 | 1 | Benban 3/ Toshka 2 LOT 41 | 4009745.48 | 3086514.46 | 421023.28 | 3507537.74
Multi Sport Hall | 10215 |  | Multi Sport Hall | 364760 | 320824 | 0 | 320824
Baron Palace | 10213 |  | Baron Palace | 1816.32 | 1616.52 | 0 | 1616.52
Elhegaz | Calim-001 | 1 | Elhegaz1 | 310102.8 | 0 | 0 | 307382.6
El Sewedy University | Inv(1)010320 | 1 | El Sewedy University1 | 628419.21 | 31420.96 | 0 | 536342.25
Miscellaneous Projects | 2008210006 |  | Miscellaneous Projects | -16071.1 | -17838.924 | 0 | -17838.924
LAYYAH CCPP | 489 |  | LAYYAH CCPP | 6538440 | 5861484.65 | 971207 | 6832691.65
LAYYAH CCPP | 488 |  | LAYYAH CCPP | 527000 | 895900 | 158100 | 527000
Marsa Matrouh 500KV | Ref Retention Matroh |  | Marsa Matrouh 500KV | 61395309.93 | 56937414.75 | 0 | 56937414.75
MOTHANA 400/132kV SS | 365 |  | MOTHANA 400/132kV SS | 1192960.62 | 1192960.62 | 0 | 1192960.62
NUCA R05 - Z02 | IPC 49 R05 (2) | 49 | NUCA R05 - Z0249 | 12129061.24 | 14397594.5 | 1885695.51 | 16283290.01
Marsa Matrouh 500KV | Ref.Retention Matroh |  | Marsa Matrouh 500KV | 77665491.48 | 77549954.22 | 0 | 77549954.22
Sodic East | IPC_14_Rowad_seast | 14 | Sodic East14 | 1150616.1 | 719286.82 | 0 | 719286.82
Minis Building(Polyurethane) | IPC_14_Rowad_poly | 14 | Minis Building(Polyurethane)14 | 140805.4 | 125316.81 | 0 | 125316.81
Sodic East | IPC_16_rowad_s_east | 16 | Sodic East16 | 509144.6 | 450847.5433 | 0 | 450847.5433
EMAAR-PKG#22-MARASSI | OB-ST- PKG#22 |  | EMAAR-PKG#22-MARASSI | 80820.93 | 80820.93 | 0 | 80820.93
Multi Sport Hall | IPC_13_Rowad_IndoorH | 13 | Multi Sport Hall13 | 49020 | 43627.8 | 0 | 43627.8
SHAT Al ARAB 400/132kV SS | 374 |  | SHAT Al ARAB 400/132kV SS | 46724.52 | 46724.52 | 0 | 46724.52
Assuit PP (CP-118) | 2009210018 |  | Assuit PP (CP-118) | 402402.68 | 359105.39 | 63378.42 | 422483.81
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 36 | 36 | ORA ZED - Ph 01B - Pkgs A&D36 | 9427628.57 | 7054023.71 | 989901 | 8043924.71
Mohamed Ali Palace | colsing tr0015 |  | Mohamed Ali Palace | 46349.8 | 16222.43 | 0 | 16222.43
Toshka GIS 500 kV | Toshka Sub Inv. 05 $ | 5 | Toshka GIS 500 kV5 | 75446.67 | 51022.35 | 19804.75 | 70827.1
Toshka GIS 500 kV | Toshka Sub Inv. 06 $ | 6 | Toshka GIS 500 kV6 | 226768.1 | 145455.66 | 59526.63 | 204982.29
AWEER POWER STATION 'H' Phase | Con-016 | 16 | AWEER POWER STATION 'H' Phase16 | 638849.32 | 631751 | 0 | 631751
Ghana Street lighting | MIDA Sply. Inv. 1 | 1 | Ghana Street lighting1 | 374376.6 | 336938.94 | 0 | 336938.94
Ministries Buildings | MIN-LAND SCAPE-IPC03 | 3 | Ministries Buildings3 | 3144575.84 | 2018500 | 672850 | 2691350
Ghana Street lighting | MIDA Sply. Inv. 2 | 2 | Ghana Street lighting2 | 640139.36 | 640139.36 | 0 | 640139.36
Canal Sugar S/s | Inv 10 Sugar S/s | 10 | Canal Sugar S/s10 | 19475165.77 | 14859551.48 | 2921274.87 | 17780826.35
Latin Compound - New Alamin | inv ( 24 )17-12-2020 | 24 | Latin Compound - New Alamin24 | 815614.8 | 487553.77 | 203903.7 | 691457.47
ElSewedy HQ Internal Finishing | ELSEWEDY HQ-IPC02 | 2 | ElSewedy HQ Internal Finishing2 | 7766126.67 | 8230813.242 | 1075170.11 | 9305983.352
Toshka-04 GIS Substation | Toshka Sub 4 Inv. 05 | 5 | Toshka-04 GIS Substation5 | 5476607.65 | 0 | 575043.8 | 575043.8
Miscellaneous Projects | 2011210005 |  | Miscellaneous Projects | 4035.7 | 4600.7 | 0 | 4600.7
Substation Elco Steel | PSP ELCO-IPC FINAL |  | Substation Elco Steel | 54510.72 | 1648328.74 | 0 | 1648328.74
Kattameya Creeks | KATAMYA CREEKS IPC13 | 13 | Kattameya Creeks13 | 41829784.58 | 39353596.009 | 4126609.95 | 43480205.959
Kattameya Creeks | KATAMYA CREEKS-IPC02 | 2 | Kattameya Creeks2 | 12368012.17 | 11295285.7785 | 1567446.9 | 12862732.6785
Al-Ula Towers | inv ( 1 )3-2021 | 1 | Al-Ula Towers1 | 406211.6 | 402149.49 | 0 | 402149.49
Minis Building(Polyurethane) | IPC_19_Rowad_Poly | 19 | Minis Building(Polyurethane)19 | 75366.57 | 67076.24 | 0 | 67076.24
EMAAR-PKG# 144, Marassi | PKG#144-IPC15 | 15 | EMAAR-PKG# 144, Marassi15 | 2638692.38 | 5968624.239 | 0 | 5968624.239
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 06 | 6 | Suez Gulf/S4 - 500KV OHTL6 | 1340748.22 | 1087338.54 | 140778.56 | 1228117.1
Ministries Buildings | MIN-LONG LEAD-IPC03 | 3 | Ministries Buildings3 | 6495102.12 | 231155 | 0 | 5864232.84
Toshka-04 GIS Substation | Toshka Sub 4 Inv.1 $ | 1 | Toshka-04 GIS Substation1 | 5356664.94 | 0 | 562449.82 | 562449.82
HAC CCC JV | FPC - HAC CCC JV |  | HAC CCC JV | 260595 | 223127.83 | 0 | 223127.83
Miscellaneous Projects | 2012210029 |  | Miscellaneous Projects | 249355.92 | 284265.7488 | 0 | 284265.7488
West Port Said 220 kV GIS | P-45-Portsaid Inv.3$ | 3 | West Port Said 220 kV GIS3 | 1248647.62 | 0 | 131108 | 131108
West Port Said 220 kV GIS | P-45-Portsaid Inv.1$ | 1 | West Port Said 220 kV GIS1 | 4122810.48 | 0 | 432895.1 | 432895.1
New Babil 400/132KV Substation | 2103210003 |  | New Babil 400/132KV Substation | 225549.98 | 225549.98 | 0 | 225549.98
Ahl Misr Walkway | IPC#1` EDECS | 1 | Ahl Misr Walkway1 | 230152 | 221751.46 | 0 | 221751.46
Suez Gulf/S4 - 500KV OHTL | Suez S4 Equ Inv. 01 | 1 | Suez Gulf/S4 - 500KV OHTL1 | 724268.61 | 548598.15 | 78376.21 | 626974.36
Zone(J) South Valley Toshka | South Valley Inv. 12 | 12 | Zone(J) South Valley Toshka12 | 33976423.1 | 25600265.35 | 4348982.2 | 29949247.55
Zone(J) South Valley Toshka | South Valley Inv. 10 | 10 | Zone(J) South Valley Toshka10 | 39027367.43 | 29518000.8 | 4995503.08 | 34513503.88
Phosfat | Final Inv.7 Phosfat | 7 | Phosfat7 | 1607817.98 | 1346953.2 | 0 | 1346953.2
AWEER POWER STATION 'H' Phase | ENG/037 |  | AWEER POWER STATION 'H' Phase | 149868.45 | 157361.87 | 0 | 157361.87
EMAAR-Pkg#162/163- Marassi | PKG #177 IPC06 | 6 | EMAAR-Pkg#162/163- Marassi6 | 0.001 | 2070801.281 | 264985.85 | 2335787.131
Marsa Alam/ Bernes LOT2 OHTL | Ref.Ret Marsa Alam 5 |  | Marsa Alam/ Bernes LOT2 OHTL | 2046623.19 | 1301246.19 | 0 | 1301246.19
AWEER POWER STATION 'H' Phase | ENG/039 |  | AWEER POWER STATION 'H' Phase | 198675.86 | 208609.653 | 0 | 208609.653
Badr | Inv. 27 Badr | 27 | Badr27 | 16367375.55 | 11259705.15 | 2455106.35 | 13714811.5
Mauritania Lot 1 | Inv.14 - Lot 1 | 14 | Mauritania Lot 114 | 242060.67 | 229943.01 | 0 | 229943.01
Mauritania Lot 1 | Inv.13 - Lot 1 | 13 | Mauritania Lot 113 | 216173.948 | 205350.63 | 0 | 205350.63
Ghana Street lighting | MIDA Ins.7 |  | Ghana Street lighting | 49881.79 | 44893.61 | 0 | 44893.61
Akhmem - Qena | Ref.Ret Quana akh 2 |  | Akhmem - Qena | 30000000 | 0 | 0 | 0
Diplomatic District - Infra | Diplo Dist. IPC01 | 1 | Diplomatic District - Infra1 | 0.001 | 1022317.681 | 123339.89 | 1145657.571
Air Force Project | Air Force Inv . 06 | 6 | Air Force Project6 | 8495366.5 | 6082682.3 | 2123841.65 | 8206523.95
Air Force Project | Air Force Inv . 01 | 1 | Air Force Project1 | 15160757.98 | 10587000 | 3790189.5 | 14377189.5
SHATRA 400/132kV SS | 409 |  | SHATRA 400/132kV SS | 758009.99 | 758009.99 | 0 | 758009.99
EGAT Pelletizing Plant | EGAT WaterTank IPC02 | 2 | EGAT Pelletizing Plant2 | 2028589.79 | 2008303.8895 | 0 | 2008303.8895
LAYAN Substation | 10622 |  | LAYAN Substation | 18500 | 19425 | 0 | 19425
New Babil 400/132KV GIS Substa | 2106210001 |  | New Babil 400/132KV GIS Substa | 136269.78 | 136269.78 | 0 | 136269.78
Elco Steel 220/33 KV SS | 2106210005 |  | Elco Steel 220/33 KV SS | 3839.94 | 4031.937 | 0 | 4031.937
Koning Food LP-04-20 | 22 |  | Koning Food LP-04-20 | 20000 | 17764.174 | 5000 | 22764.174
Mehwar elsalam Lock & Load | م 1 الطوارىء لوك لود | 1 | Mehwar elsalam Lock & Load1 | 2777108.86 | 2471626.89 | 0 | 2471626.89
SHATRA 400/132kV SS | 417 |  | SHATRA 400/132kV SS | 149957.89 | 149957.89 | 0 | 149957.89
Assuit PP (CP-118) | 2108210001 |  | Assuit PP (CP-118) | -6446.14 | -6446.14 | 0 | -6446.14
Miscellaneous Projects | 2009210013 |  | Miscellaneous Projects | 132787.2 | 151377.41 | 0 | 151377.41
RING ROAD MARYOTIA EXPANSION | Maryotya IPC08 | 8 | RING ROAD MARYOTIA EXPANSION8 | 2554128.57 | 2528587.28 | 0 | 2528587.28
Canal Sugar S/s | Ref.Ret Sugar Sub |  | Canal Sugar S/s | 11335814.58 | 11335814.58 | 0 | 11335814.58
Canal Sugar 33KV OHTL | Ref Ret Sugar 33 -OH |  | Canal Sugar 33KV OHTL | 338437.98 | 338437.98 | 0 | 338437.98
South Mohamed Ben Zayed S.L | Ben Zayed Inv. 01 | 1 | South Mohamed Ben Zayed S.L1 | 21877894.1 | 17754986.46 | 0 | 17754986.46
Manshiet Nasser Substation | 2104210003 |  | Manshiet Nasser Substation | 104206.18 | 67811.25 | 16771.87 | 84583.12
EGAT Pelletizing Plant | EGAT WaterTank IPC04 | 4 | EGAT Pelletizing Plant4 | 766173.48 | 758512.36 | 0 | 758512.36
LRT Project | IPC-05-LRT | 5 | LRT Project5 | 215928.65 | 170000 | 0 | 170000
MAYSAN 400/132kV SS | 423 |  | MAYSAN 400/132kV SS | 7852.01 | 7852.01 | 0 | 7852.01
Waldorf Astoria Cairo | waldorf astoria IPC4 | 4 | Waldorf Astoria Cairo4 | 5452379.98 | 4634265 | 4727040.72 | 9361305.72
New Babil 400/132KV GIS Substa | 2111210002 |  | New Babil 400/132KV GIS Substa | 737736.39 | 737736.39 | 0 | 737736.39
Air Force Project | Air Force Inv . 15 | 15 | Air Force Project15 | 6930616.41 | 6694570 | 0 | 6694570
Akhmem Assiut | Ret Asuit akh 4 T |  | Akhmem Assiut | 20000000 | 20000000 | 0 | 20000000
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.07 | 7 | Toshka 2/Owinat East LOT2 OHTL7 | 5119267.58 | 4297214.97 | 537523.1 | 4834738.07
Racecores 3092-17 132KV E | 10964 |  | Racecores 3092-17 132KV E | 74618.74 | 74618.74 | 0 | 74618.74
Taval Sarai 52 | IPC-14-Saray | 14 | Taval Sarai 5214 | 609504.8 | 62502.662 | 0 | 62502.662
ElSewedy HQ Internal Finishing | ElSEWEDY HQ IPC09 | 9 | ElSewedy HQ Internal Finishing9 | 11039038.38 | 10415313.809 | 2893338.07 | 20068257.919
Get Business Complex | INV ( 16 ) GET | 16 | Get Business Complex16 | 1172197.1 | 841428.096 | 0 | 841428.096
New Babil 400/132KV GIS Substa | 2112210004 |  | New Babil 400/132KV GIS Substa | 234031.6 | 234031.6 | 0 | 234031.6
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 01 | 1 | Hosh Essa 220 KV OHTL1 | 12313722.65 | 7395451.78 | 1292940.88 | 8688392.66
Railway Bridge - Assuit | IPC#5 - Assuit | 5 | Railway Bridge - Assuit5 | 1021200 | 880194 | 0 | 880194
Benban 500 K.V / 100 K.M | رد تامين3بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 5000000 | 5000000 | 0 | 5000000
Racecores 3092-15 132KV A | 11122 |  | Racecores 3092-15 132KV A | 2663.71 | 2663.71 | 0 | 2663.71
New Giza Teaching Hospital | newgizahospital ipc1 | 1 | New Giza Teaching Hospital1 | 34312846.59 | 24876813.7695 | 9007122.23 | 33883935.9995
RING ROAD MARYOTIA EXPANSION | el marg ipc10 | 10 | RING ROAD MARYOTIA EXPANSION10 | 3155065.2 | 2795847.4 | 0 | 2795847.4
Port Said Port Silos | supply egp ipc.4 | 4 | Port Said Port Silos4 | 4365761.5041 | 13666840 | 1746292.92 | 3853283.23
Racecores 3092-17 132KV E | 11284 |  | Racecores 3092-17 132KV E | 4969 | 4969 | 0 | 4969
Racecores 3092-16 132KV C | 11287 |  | Racecores 3092-16 132KV C | 733.71 | 733.71 | 0 | 733.71
LP-25-21 UIC4 Printers | 52 |  | LP-25-21 UIC4 Printers | 12719.25 | 14372.75 | 0 | 14372.75
Racecores 3092-16 132KV C | 11242 |  | Racecores 3092-16 132KV C | 10500 | 0 | 0 | 11025
DEWA 36 (OPGW) | 11364 |  | DEWA 36 (OPGW) | 50442 | 50442 | 0 | 50442
Port Said Subs 220/66 | Port Said Inv. 6 | 6 | Port Said Subs 220/666 | 103208213.09 | 61408475 | 25802053.3 | 87210528.3
MDF Factory | MDF FACTORY2 IPC03 | 3 | MDF Factory3 | 2443274.75 | 2459303.395 | 0 | 2459303.395
AWEER POWER STATION 'H' Phase | IMP/067 |  | AWEER POWER STATION 'H' Phase | 60327.52 | 63343.896 | 0 | 63343.896
Beni Seuf - 358 | Inv. 12 Oewon Mousa | 12 | Beni Seuf - 35812 | 91294935.39 | 50000000 | 15704052.4 | 65811831.08
El Taameer Axis Expansion | IPC#7 Taamer | 7 | El Taameer Axis Expansion7 | 911196 | 880215.34 | 0 | 880215.34
Sodic East | IPC-Final-Sodic East |  | Sodic East | -261545 | 120750.94 | 0 | 120750.94
EGAT Pelletizing Plant | watertank IPC 11 | 11 | EGAT Pelletizing Plant11 | 1787146.2 | 1769274.74 | 0 | 1769274.74
Ghana Street lighting | MIDA Sply. Inv.10 | 10 | Ghana Street lighting10 | 45614.39 | 41052.95 | 0 | 41052.95
Racecores 3092-17 132KV E | 11476 |  | Racecores 3092-17 132KV E | 1451.42 | 1451.42 | 0 | 1451.42
LP-27-21-Elsewedy1000RFID | 74 |  | LP-27-21-Elsewedy1000RFID | 5530 | 6304.2 | 0 | 6304.2
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 13 | 13 | Suez Gulf/S4 - 500KV OHTL13 | 5214701.88 | 1776644.04 | 0 | 1776644.04
TZ – Offshore E&M Procurement | 447 |  | TZ – Offshore E&M Procurement | 249384.72 | 174569.3 | 49876.94 | 224446.24
Miscellaneous Projects | 220321002 |  | Miscellaneous Projects | 648182 | 738927.48 | 0 | 738927.48
PLAYA ROOF & Wet Areas | IPC-6-PLAYA ROOF | 6 | PLAYA ROOF & Wet Areas6 | 156120.8 | 133577.26 | 0 | 133577.26
New Babil 400/132KV GIS Substa | 220221001 |  | New Babil 400/132KV GIS Substa | 721910.7 | 577528.56 | 0 | 721910.7
Mivida BP#189 | Emaar Pkg#189 ipc 21 | 21 | Mivida BP#18921 | 22586754.17 | 14476604.0585 | 1839999.52 | 16316603.5785
Beymen Fit Out | pkg #205 ipc 4 | 4 | Beymen Fit Out4 | 355037.33 | 323379.51 | 23864.74 | 347244.25
New Babil 400/132KV GIS Substa | 220421001 |  | New Babil 400/132KV GIS Substa | 2589125.81 | 2589125.81 | 0 | 2589125.81
EDNC Hardscape Package | EDNC HARDESCAPE IPC3 | 3 | EDNC Hardscape Package3 | 5414598.24 | 5240048.512 | 0 | 5240048.512
Al-Ula Towers | inv ( 3 ) 15-6-2022 | 3 | Al-Ula Towers3 | 704867.2 | 470009.89 | 0 | 470009.89
Ghana Street lighting | MIDA Ins. Inv. 14 | 14 | Ghana Street lighting14 | 30507.77 | 27456.99 | 0 | 27456.99
Mahmoudia Additional Scope | 2005210008 |  | Mahmoudia Additional Scope | 625000 | 225000 | 400000 | 625000
Kayan 3 New Cairo Capital City | كيان صحى م 4 | 4 | Kayan 3 New Cairo Capital City4 | 2205970 | 1578873.1 | 0 | 1578873.1
Assuit PP (CP-118) | Invoice # 27 Assuit |  | Assuit PP (CP-118) | 2850495.23 | 2993019.99 | 0 | 2993019.99
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .22 | 22 | Benban 3/ Toshka 2 LOT 422 | 3132051.3 | 2793396.41 | 0 | 2793396.41
Benban 500 K.V / 100 K.M | Ref-Ret-Benban lot1 |  | Benban 500 K.V / 100 K.M | 6000000 | 6000000 | 0 | 6000000
158E/2019 33kv Project | 11543 |  | 158E/2019 33kv Project | 2198273.88 | 2587844.86 | 0 | 1293922.43
MDF Factory | MDF - IPC18 | 18 | MDF Factory18 | 3979485.33 | 3423126.0965 | 1306895.58 | 4730021.6765
PLAYA ROOF & Wet Areas | IPC-2-PLAYA ROOF | 2 | PLAYA ROOF & Wet Areas2 | 60260.25 | 51709.33 | 0 | 51709.33
Baron Palace | 10024 |  | Baron Palace | 8025.6 | 7142.784 | 0 | 7142.784
Al-Shabab PP Phase II (CP-117) | 2001220002 |  | Al-Shabab PP Phase II (CP-117) | 0 | -0.03 | 0 | -0.03
MDF Factory | MDF factory(2) IPC7 | 7 | MDF Factory7 | 787160.02 | 795031.6228 | 0 | 795031.6228
Racecores 3092-16 132KV C | 11767 |  | Racecores 3092-16 132KV C | 10800 | 11340 | 0 | 11340
SSC Suez Steel Company Project | In&ReSupply(ABB)ipc3 | 3 | SSC Suez Steel Company Project3 | 1037578.56 | 814872.9584 | 357590.81 | 1172463.7684
LP-16-21 VC Elsewedy P. | 80 |  | LP-16-21 VC Elsewedy P. | 1635028.68 | 931966.35 | 0 | 931966.35
RING ROAD MARYOTIA EXPANSION | mariotya ipc18 | 18 | RING ROAD MARYOTIA EXPANSION18 | 27321187.62 | 27047975.741 | 0 | 27047975.741
Cairo-Alex Railway | cairo-alex ipc 28 | 28 | Cairo-Alex Railway28 | 2127149 | 1545725.91 | 223350.65 | 1769076.56
Ain Sokhna Port Development | IPC#19 Sokhna Port | 19 | Ain Sokhna Port Development19 | 740772 | 555082.66 | 0 | 693853.32
EDNC Hardscape Package | Sorealhardscape IPC9 | 9 | EDNC Hardscape Package9 | 5047602.19 | 1004245.4695 | 0 | 1004245.4695
Ministries Buildings | MINISTIRYFITOUT IPC4 | 4 | Ministries Buildings4 | 37243120.9 | 31376920 | 0 | 31376920
Abou Ghaleb Bridge | Abo ghaleb ipc 05 | 5 | Abou Ghaleb Bridge5 | 13460041.27 | 11836953.4135 | 0 | 11836953.4135
October Under-Railway Tunnel | october tunnel ipc1 | 1 | October Under-Railway Tunnel1 | 802790.71 | 1520548 | 0 | 1520548
El Khatatba Bridge | el khatatba ipc 06 | 6 | El Khatatba Bridge6 | 11047474.29 | 9612859.45 | 0 | 9612859.45
seashell Playa | IPC000024' | 24 | seashell Playa24 | 34.51 | 34.51 | 0 | 34.51
Creeks URBN-K | urbn-k ipc 11 | 11 | Creeks URBN-K11 | 13885723.37 | 11569432 | 1914479.74 | 13483911.74
Creeks URBN-K | URBN-K IPC 12 | 12 | Creeks URBN-K12 | 10141133.17 | 8618325 | 1285635.17 | 9903960.17
Seashell Playa 5 Villas | seashell playa- IPC2 | 2 | Seashell Playa 5 Villas2 | 297533.35 | 249026.8 | 0 | 249026.8
Sokhna Port Expansion | sokhna port ex ipc04 | 4 | Sokhna Port Expansion4 | 24751031.1 | 16604871.935 | 5197716.53 | 21802588.465
SSC Suez Steel Company Project | R.O(5:8) APP ipc 4 | 4 | SSC Suez Steel Company Project4 | 1554992.04 | 1195633.3756 | 530407.79 | 1726041.1656
SSC Suez Steel Company Project | R.O. Supply - IPC5 | 5 | SSC Suez Steel Company Project5 | 4510403.17 | 0 | 1353120.95 | 5096755.5838
ORA-ZED Towers P01B | IPC000003 | 3 | ORA-ZED Towers P01B3 | 128121.83 | 113451.88 | 0 | 113451.88
Playa Epoxy | 4 |  | Playa Epoxy | 84594.2 | 72590.28 | 0 | 72590.28
HSR-6th of October | final HSR |  | HSR-6th of October | 1275240 | 1001891.28 | 0 | 1001891.28
EPICO 3 Facility | EIPICO3- IPC 2 | 2 | EPICO 3 Facility2 | 13487203.1 | 13338534.97 | 0 | 13338534.97
Katameya Creeks - RME | IPC000002 | 2 | Katameya Creeks - RME2 | 13243.47 | 11227.1 | 0 | 11227.1
MDF Factory | MDF 2 - IPC 10 | 10 | MDF Factory10 | 606265.2 | 612327.848 | 0 | 612327.848
U3 & U5 | IPC1-TR055 | 1 | U3 & U51 | 741275.46 | 640165 | 0 | 640165
El-Warraq | IPC#1 Warraq | 1 | El-Warraq1 | 860000 | 763766 | 0 | 763766
MAF HQ Renovation | Carrefour RBS IPC1 | 1 | MAF HQ Renovation1 | 1198156.2 | 805760.048 | 314516 | 1120276.048
MDF Factory | MDF Factory2 ipc 16 | 16 | MDF Factory16 | 953893.47 | 963432.4058 | 0 | 963432.4058
Hyper One Badr | INV ( 11 ) Hyper | 11 | Hyper One Badr11 | 553473.99 | 476513.88 | 0 | 476513.88
Asmarat Roads L&L | asmarat IPC Final |  | Asmarat Roads L&L | 2917810 | 2256420 | 0 | 2256420
PLAYA ROOF & Wet Areas | IPC0020 | 20 | PLAYA ROOF & Wet Areas20 | 118402.29 | 101601.02 | 0 | 101601.02
EPICO 3 Facility | Eipico ipc 3 | 3 | EPICO 3 Facility3 | 8222480.29 | 13033885 | 0 | 13033885
MDF Factory | Mdf Factory 3 ipc 13 | 13 | MDF Factory13 | 3743051.03 | 0 | 3780481.5442 | 3780481.5442
Abo Shanab El Agamien | Abo shanab ipc 4 | 4 | Abo Shanab El Agamien4 | 14117757.67 | 0 | 4383784.66 | 4383784.66
Air Defence College | IPC0014 TR46 | 14 | Air Defence College14 | 277883.72 | 235923.26 | 0 | 235923.26
Playa Resort | 230000010 |  | Playa Resort | 35000 | 35000 | 0 | 35000
MDF Factory | MDF factory ipc 34 | 34 | MDF Factory34 | 27337098.5 | 12636241.38 | 11483337.33 | 24119578.71
EIPICO Factory | IPC001 TR54 | 1 | EIPICO Factory1 | 176320 | 151300.19 | 0 | 151300.19
Closed | (29)pkg#32 |  | Closed | 539887 | 1228520.89 | 0 | 1228520.89
SEASHELL TECHNICAL ROOM | IPC002TR65 | 2 | SEASHELL TECHNICAL ROOM2 | 373089.4 | 322200.01 | 0 | 322200.01
EGAT Mechanical Installations | Egat Piping ipc 1 | 1 | EGAT Mechanical Installations1 | 42583.33 | 32359.0662 | 10645.83 | 43004.8962
EGAT Pelletizing Plant | ipc2 supply of RO | 2 | EGAT Pelletizing Plant2 | 2837834.44 | 1818704.1772 | 1388048.74 | 3206752.9172
EGAT Pelletizing Plant | EGAT MEP- IPC2 | 2 | EGAT Pelletizing Plant2 | 112937.5 | 117455 | 0 | 117455
MDF Factory | MDF2 IPC ( 18) | 18 | MDF Factory18 | 355884.12 | 359356.67 | 0 | 359356.67
Sultana Malak Restoration | Sultana 034 IPC Fin |  | Sultana Malak Restoration | 3151023.81 | 2967850 | 0 | 2967850
EMAAR-Pkg#162/163- Marassi | pkg#177- IPC 40 | 40 | EMAAR-Pkg#162/163- Marassi40 | 2265659.38 | 118928.159 | 0 | 118928.159
HST - 6 October - Arab Cont. | IPC 4 D0076 | 4 | HST - 6 October - Arab Cont.4 | 5781955 | 4959479.76 | 0 | 4959479.76
Wadi El Natroun | IPC#4 | 4 | Wadi El Natroun4 | 750915 | 698815.1 | 0 | 698815.1
El Salam Bridge | IPC#2 | 2 | El Salam Bridge2 | 348690 | -128634.3 | 0 | -128634.3
Sultana Malak Restoration | sultana malak2 final |  | Sultana Malak Restoration | 212099.05 | 199390 | 0 | 199390
U3 & U5 | IPC11 TR55 | 11 | U3 & U511 | 234462.55 | 202481.85 | 0 | 202481.85
VILLA CLUSTRER B | IPC07TR0077 | 7 | VILLA CLUSTRER B7 | 204666.5 | 176749.97 | 0 | 176749.97
ZED Phase 2 | IPC001 TR62 | 1 | ZED Phase 21 | 75881.78 | 64461.55 | 0 | 64461.55
MDF Factory | mdf equip ipc 19 | 19 | MDF Factory19 | 1179001.02 | 1190791 | 0 | 1190791
Mivida BP#189 | pkg#189-IPC4 | 4 | Mivida BP#1894 | 24279069.68 | 21067752.4505 | 2534689.17 | 23602441.6205
HST Bridges-Sokhna & Mahager | sokhna bridge ipc16 | 16 | HST Bridges-Sokhna & Mahager16 | 16000000 | 4888975.7 | 0 | 14888975.7
EIPICO C002-23 | IPC03TR0068 | 3 | EIPICO C002-233 | 167886.92 | 144063.76 | 0 | 144063.76
Wady El Natroon Bridge | wady elnatroon ipc5 | 5 | Wady El Natroon Bridge5 | 8632100 | 7689057.6 | 0 | 7689057.6
Tarek Abdel-Hakim Center | TAH ipc 7 | 7 | Tarek Abdel-Hakim Center7 | 2195644.04 | 1689548.1 | 197607.96 | 1887156.06
U7-SEASHELL | IPC09TR0064 | 9 | U7-SEASHELL9 | 502420.5 | 433890.33 | 0 | 433890.33
Seashell Playa 5 Villas | PLAYA - C072 IPC 4 | 4 | Seashell Playa 5 Villas4 | 16406.84 | 14168.95 | 0 | 14168.95
Abo Shanab El Agamien | Abo Shanab ipc01 | 1 | Abo Shanab El Agamien1 | 8743501.28 | 19325460.17 | 0 | 19325460.17
EIPICO Factory | IPC05TR0054 | 5 | EIPICO Factory5 | 24286.4 | 20840.16 | 0 | 20840.16
Mivida BP#189 | Emaar pkg#189 ipc 19 | 19 | Mivida BP#18919 | 21710553.31 | 23323710.1055 | 2962118.09 | 26285828.1955
Kattmeya Creeks Urban | IPC04TR0071 | 4 | Kattmeya Creeks Urban4 | 81683.7 | 72330.9 | 0 | 72330.9
AIRDEFNSE -EPOXY | IPC01 TR66 | 1 | AIRDEFNSE -EPOXY1 | 25160 | 21360.84 | 0 | 21360.84
Kattmeya Creeks Urban | IPC001 TR71 | 1 | Kattmeya Creeks Urban1 | 863894.37 | 764978.47 | 0 | 764978.47
Ora Zed -Landscape | IPC001 TR70 | 1 | Ora Zed -Landscape1 | 43231.19 | 37096.69 | 0 | 37096.69
R05 (New) | IPC05TR0559 | 5 | R05 (New)5 | 88844 | 75348.59 | 0 | 75348.59
U3 & U5 | IPC17TR0055 | 17 | U3 & U517 | 254302.57 | 219615.69 | 0 | 219615.69
Kattmeya Creeks Urban | IPC05TR0071 | 5 | Kattmeya Creeks Urban5 | 64024.38 | 56693.59 | 0 | 56693.59
Roof-Playa Cluster A,B,C | IPC07TR0088 | 7 | Roof-Playa Cluster A,B,C7 | 628606.13 | 542864.25 | 0 | 542864.25
Seashell Playa 5 Villas | Playa C038- IPC11 | 11 | Seashell Playa 5 Villas11 | 60385.23 | 11638.46 | 0 | 11638.46
WADY EL-NATROUN BRIDGE(HST) | IPC17 wadyelnatroun | 17 | WADY EL-NATROUN BRIDGE(HST)17 | 1667492.5 | 777131.41 | 0 | 777131.41
EIPICO C002-23 | IPC05TR0068 | 5 | EIPICO C002-235 | 30916.9 | 26529.78 | 0 | 26529.78
Port Said Grain Storage | ipc 11 | 11 | Port Said Grain Storage11 | 1200866 | 76901.19 | 0 | 76901.19
ZED Phase 2 | IPC08TR0062 | 8 | ZED Phase 28 | 88072.621 | 74817.41 | 0 | 74817.41
U7-SEASHELL | IPC15TR0064 | 15 | U7-SEASHELL15 | 38381 | 33145.84 | 0 | 33145.84
GOV2 - Infra | Gov2 ipc 26 | 26 | GOV2 - Infra26 | 12717028 | 4895688.12 | 825933.51 | 5721621.63
Tarek Abdel-Hakim Center | TAH ipc 11 | 11 | Tarek Abdel-Hakim Center11 | 6272151.58 | 4826420.64 | 564493.64 | 5390914.28
WADY EL-NATROUN BRIDGE(HST) | IPC#18#WADI ELNATROU | 18 | WADY EL-NATROUN BRIDGE(HST)18 | 859617.5 | 767908.49 | 0 | 767908.49
U7-SEASHELL | IPC16TR0064 | 16 | U7-SEASHELL16 | 26208 | 22633.22 | 0 | 22633.22
U7-SEASHELL | IPC18TR0064 | 18 | U7-SEASHELL18 | 83992.9 | 72536.26 | 0 | 72536.26
VILLA CLUSTRER B | IPC08TR0077 | 8 | VILLA CLUSTRER B8 | 371481.88 | 291405.93 | 0 | 291405.93
Samaya Factory - 2 | Samaya factory ( 1 ) |  | Samaya Factory - 2 | 386925 | 360000 | 0 | 360000
Seashell Playa 5 Villas | Playa - c469 ipc 3 | 3 | Seashell Playa 5 Villas3 | 119758.36 | 109411.24 | 0 | 109411.24
MDF Factory | Mdf Factory ipc 39 | 39 | MDF Factory39 | 17738610.9 | 6984174.92 | 7449976.85 | 14434151.77
Waldorf Astoria Cairo | Waldorf Spare ipc 1 | 1 | Waldorf Astoria Cairo1 | 1707917.54 | 1929946 | 0 | 1929946
DP World Basin 2 Ph2 | Dp World PH2 ipc 15 | 15 | DP World Basin 2 Ph215 | 98969.1 | 35568315.9 | 0 | 35568315.9
MDF Factory | MDF Equip ipc 23 | 23 | MDF Factory23 | 539932.48 | 545331.8072 | 0 | 545331.8072
Kafr Shokr Bridge | kafr shokr ipc08 | 8 | Kafr Shokr Bridge8 | 1839476.19 | 1610960.6295 | 0 | 1610960.6295
Sokhna Port Expansion | SPX.1(22+23) part 2 |  | Sokhna Port Expansion | 992022 | 992022 | 0 | 992022
ElSewedy HQ Internal Finishing | ELSEWEDY HQ- IPC 22 | 22 | ElSewedy HQ Internal Finishing22 | 9615384.76 | 10000000.148 | 0 | 10000000.148
ElSewedy HQ Internal Finishing | ELSEWEDY HQ IPC15 | 15 | ElSewedy HQ Internal Finishing15 | 16126527.14 | 10437709.627 | 3444305.6 | 13882015.227
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 41 | 41 | ORA ZED - Ph 01B - Pkgs A&D41 | 8233965.99 | 6728778.2096 | 0 | 6728778.2096
Abo Ghaleb | IPC#2 Abo Galab | 2 | Abo Ghaleb2 | 156000 | 142483.6 | 0 | 142483.6
Cairo-Alex Railway | Escalation ipc 1:28 | 1 | Cairo-Alex Railway1 | 79609401.55 | 42043714.07 | 0 | 42043714.07
Creeks URBN-K | Katamya Urbnk ipc 13 | 13 | Creeks URBN-K13 | 23806990.16 | 23221916 | 1024902.32 | 24246818.32
RADAMIS CITY | IPC07TR0084 | 7 | RADAMIS CITY7 | 105622.27 | 93528.53 | 0 | 93528.53
RADAMIS CITY | IPC08TR0084 | 8 | RADAMIS CITY8 | 354795.02 | 314170.99 | 0 | 314170.99
Wady El Natroon Bridge | Wady elnatron esc1:8 |  | Wady El Natroon Bridge | 18408122.38 | 15951714.1562 | 0 | 15951714.1562
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 42 | 42 | ORA ZED - Ph 01B - Pkgs A&D42 | 9191767.67 | 7070851.77 | 0 | 7070851.77
Open Channel 2 | IPC03TR0099 | 3 | Open Channel 23 | 1105489.57 | 953595.3 | 0 | 953595.3
Katameya Creeks - RME | IPC20TR0053 | 20 | Katameya Creeks - RME20 | 270410.98 | 239448.92 | 0 | 239448.92
Katameya Creeks - RME | IPC21TR0053 | 21 | Katameya Creeks - RME21 | 63517.06 | 56244.36 | 0 | 56244.36
R05 (New) | IPC11TR0059 | 11 | R05 (New)11 | 135138 | 114610.54 | 0 | 114610.54
AL-JAWHARA PALACE | IPC01TR0095 | 1 | AL-JAWHARA PALACE1 | 29531.25 | 26282.82 | 0 | 26282.82
New Giza Hos | IPC02TR0073 | 2 | New Giza Hos2 | 84721.52 | 76295.93 | 0 | 76295.93
Koumassi Flyover | INV no.13 | 13 | Koumassi Flyover13 | 928223426.66 | 841697209.67 | 0 | 841697209.67
Seashell Playa 5 Villas | PLAYA C470 IPC3 | 3 | Seashell Playa 5 Villas3 | 28196.79 | 24350.74 | 0 | 24350.74
MDF Factory | Mdf Equip ipc 26 | 26 | MDF Factory26 | 1237478.6 | 1249700.047 | 0 | 1249700.047
Wadi El Natroun Bridge | inv ( 1 ) W. Natron | 1 | Wadi El Natroun Bridge1 | 2861070 | 240852.3 | 0 | 240852.3
Cairo-Alex Railway | CR cairo alex ipc 40 | 40 | Cairo-Alex Railway40 | 0 | 0 | 0 | #DIV/0!
Air Defence College | CAN.. |  | Air Defence College | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 62 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
SHATRA 400/132kV SS | 206 |  | SHATRA 400/132kV SS | -4640388.65 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 78 |  | FX-02-22 Decent Life-UE | 2084153.94 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CRIPC_1_SARAYA_GAMA2 |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial Park | Ref.Ret PIPWst inv.4 | 4 | Pyramids Industrial Park4 | 30000 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref.Akhme Asuit T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-Tah ipc07 | 7 | Tarek Abdel-Hakim Center7 | 0 | 0 | 0 | #DIV/0!
ORA-ZED Towers01B | cr.IPC_4_Rowad_Ora | 4 | ORA-ZED Towers01B4 | 0 | 0 | 0 | #DIV/0!
DP World Basin 2 Ph2 | Cr DPworldph.2-IPC2 | 2 | DP World Basin 2 Ph22 | 0 | 0 | 0 | #DIV/0!
33KV Canal Farm Grid | Inv. 19 Farm | 19 | 33KV Canal Farm Grid19 | 1466133.62 | 0 | 0 | #DIV/0!
El Mostakbal City Project | CR.2 مد وثيقة تامين |  | El Mostakbal City Project | 0 | 0 | 0 | #DIV/0!
Ministries Buildings | landscape ipc06 | 6 | Ministries Buildings6 | 2042482 | 0 | 0 | #DIV/0!
Al Alamein Marina Towers | FPC- Marina Towers |  | Al Alamein Marina Towers | 308073.15 | 0 | 0 | #DIV/0!
Cairo Capital S1 | Cr, Inv. 1 S1 | 1 | Cairo Capital S11 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11769 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 83 |  | FX-01-22 Decent Life-WD | 1481446.62 | 0 | 0 | #DIV/0!
Residence 8 ( S05 ) | Cr.Inv ( 1 ) S05 | 1 | Residence 8 ( S05 )1 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | DEC ADJ 67 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
184E Substation | 11766 |  | 184E Substation | 0 | 0 | 0 | #DIV/0!
IRAQ - Al-Diwaniya Power Plant | Inv.68 Bank charges | 68 | IRAQ - Al-Diwaniya Power Plant68 | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | ipc1 aswan | 1 | Aswan axis - Daraw1 | 1015991.43 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 14 USD- Suez Gulf |  | Suez Gulf Substation | 296941 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 1 EGP -El Tebein 113 |  | Miscellaneous Projects | 1190173.27 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 48 |  | Al-Shabab PP Phase II (CP-117) | 2223457.74 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 58 |  | Suez Gulf Substation | 1485632.74 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Inv.3&4 deductions | 3 | Assuit PP (CP-118)3 | 0 | 0 | 0 | #DIV/0!
K047 FDH JV | ADJ-Inv.15 | 15 | K047 FDH JV15 | 0 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | Cr.P-13-2016 | 13 | Angola Emergency fast-track13 | 0 | 0 | 0 | #DIV/0!
Port Said Port Silos | Cr-port said EURipc1 | 1 | Port Said Port Silos1 | 0 | 0 | 0 | #DIV/0!
Elniger | CR Close El Niger |  | Elniger | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 51 |  | Al-Shabab PP Phase II (CP-117) | 2223457.74 | 0 | 0 | #DIV/0!
33KV Canal Farm Grid | Soc.2020 تشيد وبناء |  | 33KV Canal Farm Grid | 5000 | 0 | 0 | #DIV/0!
Air Defense College | Air def harek IPC1 | 1 | Air Defense College1 | 65275424.71 | 0 | 0 | #DIV/0!
KATAMYA GREEKS LAND SCAPE STAR | C.IPC03TR0081 | 3 | KATAMYA GREEKS LAND SCAPE STAR3 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR- 18 EGP Domiat | 18 | W Dam PP Phase II (CP-117)18 | 0 | 0 | 0 | #DIV/0!
SSC Suez Steel Company Project | CR R.O Sup. adj ipc4 | 4 | SSC Suez Steel Company Project4 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | adj. 180010 &180013 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
FX-03-22 Urban Communities-WD | 96 |  | FX-03-22 Urban Communities-WD | 696935.72 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 7 EGP - South Helwan |  | South Helwan PP (CP-117) | 59582.1048 | 0 | 0 | #DIV/0!
LAYYAH CCPP | 474 |  | LAYYAH CCPP | 0 | 0 | 0 | #DIV/0!
Air Defence College | 2Cancel IPC11 TR46 | 11 | Air Defence College11 | 190510.2 | 0 | 0 | #DIV/0!
Military 110 Kayan Project | CR.refund ret.kay |  | Military 110 Kayan Project | 0 | 0 | 0 | #DIV/0!
TNYA-WSHP | 11663 |  | TNYA-WSHP | -74312 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,7 usd Borg Ar | 7 | Marsa Matrouh 500KV7 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11523 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 109 |  | Suez Gulf Substation | 75670023.9137 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 536 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
U3 & U5 | TR55-CR2 |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
JICA lot 02 | اتحاد تشيدP-29-EGY | 29 | JICA lot 0229 | 5000 | 0 | 0 | #DIV/0!
Mangrouve Hotel - Gouna | CR.TR0021CLOSING.DEC |  | Mangrouve Hotel - Gouna | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 8 |  | Zafranaa - Beni Suef | 103212.25 | 0 | 0 | #DIV/0!
Hosh Eisa Hospit. | can IPC02TR0089 | 2 | Hosh Eisa Hospit.2 | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr Inv 10 Usd Borg | 10 | Marsa Matrouh 500KV10 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | رد تامين الزعفرانه غ |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
U3 & U5 | 55-CR3F |  | U3 & U5 | 0 | 0 | 0 | #DIV/0!
Egat Rolling Mill no.4 | CR-rolling millIPC10 | 10 | Egat Rolling Mill no.410 | 0 | 0 | 0 | #DIV/0!
Ghana Street lighting | MCBs inv.No.1.Cncl | 1 | Ghana Street lighting1 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Inv deductions |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10429 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
GPC-Gupco (Automation) | GPC inv. deductions |  | GPC-Gupco (Automation) | 0 | 0 | 0 | #DIV/0!
El Katameya Mall | CR(14)281020 |  | El Katameya Mall | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 304 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 27 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 16 EGP-progress adj. |  | Suez Gulf Substation | 157103.8629 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR-invs 2018 | 2018 | Al-Shabab PP Phase II (CP-117)2018 | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | Refund .Reten.banha |  | Siemens 6x500/220 KV GIS-MOU | 377907.88 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | CR. 12 Oewon Mousa |  | Beni Seuf - 358 | 0 | 0 | 0 | #DIV/0!
EMAAR-PKG#62-UPTOWN | CR Amend vat |  | EMAAR-PKG#62-UPTOWN | 0 | 0 | 0 | #DIV/0!
Aswan axis - Daraw | ipc no3 aswan | 3 | Aswan axis - Daraw3 | 257712 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR IPC_1_SARAYA_GAMA | 1 | Taval Sarai 521 | 0 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | refund 1 |  | Barwa 2x60/22 KV S/S | 0 | 0 | 0 | #DIV/0!
ACWA POWER & NOMAC HQ | CR ACWA IPC1 | 1 | ACWA POWER & NOMAC HQ1 | 0 | 0 | 0 | #DIV/0!
Military 110 Kayan Project | Ref.Ret. 8 EGP |  | Military 110 Kayan Project | 8 | 0 | 0 | #DIV/0!
R05 (New) | IPC12TR0059 | 12 | R05 (New)12 | 182340 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr-17 EGP - Shabab | 17 | Al-Shabab PP Phase II (CP-117)17 | 0 | 0 | 0 | #DIV/0!
Tarek Abdel-Hakim Center | Cr-TAH ipc06 | 6 | Tarek Abdel-Hakim Center6 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 260 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 257 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 60 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR.TR0025CLOSING.DEC |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Al Alamein Marina Towers | final inv elalamien |  | Al Alamein Marina Towers | 442239 | 0 | 0 | #DIV/0!
Residence 8 ( k12 ) | Cr.INV ( 1 ) R08-K12 | 1 | Residence 8 ( k12 )1 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180084 |  | Suez Gulf Substation | 3785.08 | 0 | 0 | #DIV/0!
RING ROAD MARYOTIA EXPANSION | crفروق اسعار مريوطية |  | RING ROAD MARYOTIA EXPANSION | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj .1904210014 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Governmental Campus-N2 | 76 |  | Governmental Campus-N2 | 335629 | 0 | 0 | #DIV/0!
IRAQ - Al-Diwaniya Power Plant | rev. ( 65 USD -Diwan |  | IRAQ - Al-Diwaniya Power Plant | 0 | 0 | 0 | #DIV/0!
Beni Suef ISKRA | 258 |  | Beni Suef ISKRA | 0 | 0 | 0 | #DIV/0!
HST Bridges-Sokhna & Mahager | SOKHNA BRI. ESC1:21F |  | HST Bridges-Sokhna & Mahager | 7685556 | 0 | 0 | #DIV/0!
HST Bridge - Arab Contractors | ipc#2#harm city d083 | 2 | HST Bridge - Arab Contractors2 | 1253062.5 | 0 | 0 | #DIV/0!
Kuraimate - Samalot 500KV | Ret.OB Korimat500 |  | Kuraimate - Samalot 500KV | 14168726.79 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | 270 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
Siemens 6x500/220 KV GIS-MOU | CR_in 37 |  | Siemens 6x500/220 KV GIS-MOU | 0 | 0 | 0 | #DIV/0!
Bahr ElBakar – Power Station | IPC#02 Madkour CR | 2 | Bahr ElBakar – Power Station2 | 0 | 0 | 0 | #DIV/0!
Multi Sport Hall | CR.TR0013CLOSING.DEC |  | Multi Sport Hall | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR - 7 USD - West D. | 7 | W Dam PP Phase II (CP-117)7 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180075 |  | Suez Gulf Substation | 5242.42 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | IPC#3 - NRCC | 3 | Expansion of Ring Road NRCC3 | 215300 | 0 | 0 | #DIV/0!
Expansion of Ring Road NRCC | inv 1.2 d0080 CR | 1 | Expansion of Ring Road NRCC1 | -344835 | 0 | 0 | #DIV/0!
MAF HQ Renovation | CR po 0020024000370 |  | MAF HQ Renovation | 0 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | CR. 11 Oewon Mousa |  | Beni Seuf - 358 | 0 | 0 | 0 | #DIV/0!
CS-20 Mall | Inv ( 17 ) CS-20 | 17 | CS-20 Mall17 | 173039.56 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Cr.Memo Reten.usd |  | Abo Quir - Badr 500KV | 0 | 0 | 0 | #DIV/0!
PLAYA ROOF & Wet Areas | IPC0022_CR | 22 | PLAYA ROOF & Wet Areas22 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 84 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | Credit-inv4-final | 4 | Al-Ula Towers4 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Inv 29 Shaba EGP | 29 | Al-Shabab PP Phase II (CP-117)29 | 730337.3898 | 0 | 0 | #DIV/0!
Zambia Project | SCD4/002Cnl |  | Zambia Project | 0 | 0 | 0 | #DIV/0!
El Mostakbal City Project | CR.مد وثيقة التامين |  | El Mostakbal City Project | 0 | 0 | 0 | #DIV/0!
LP-08-22 CFC Digital-Signage | 93 |  | LP-08-22 CFC Digital-Signage | 377358.8 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Cr-memo W.hold 9-EGP |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Mivida BP#189 | cr-emarpkg#189 ipc18 | 18 | Mivida BP#18918 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR_IPC_!_Saraya_Gama |  | Taval Sarai 52 | 0 | 0 | 0 | #DIV/0!
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 06 | 6 | Suez Gulf/S4 - 500KV OHTL6 | 25379.35 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.inv.11 Assuit Akh | 11 | Akhmem Assiut11 | 0 | 0 | 0 | #DIV/0!
Suez Bridge | D0017-OB-Dec-2020/Cr | 2020 | Suez Bridge2020 | 0 | 0 | 0 | #DIV/0!
EPICO 3 Facility | crEipi material ipc3 | 3 | EPICO 3 Facility3 | 0 | 0 | 0 | #DIV/0!
Al-Kayan | CR.TR0012CLOSING.DEC |  | Al-Kayan | 0 | 0 | 0 | #DIV/0!
VILLA CLUSTRER B | IPC09TR0077 | 9 | VILLA CLUSTRER B9 | 3205 | 0 | 0 | #DIV/0!
10Th of Ramadan LRT | CR.10Ramadan Inv.03 | 3 | 10Th of Ramadan LRT3 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR IPC-12-Saray-2 | 12 | Taval Sarai 5212 | 0 | 0 | 0 | #DIV/0!
Al-Ula Towers | inv (5) final CA | 5 | Al-Ula Towers5 | 0 | 0 | 0 | #DIV/0!
HSR | HSR-OCT 5 |  | HSR | 44291359.78 | 0 | 0 | 44291359.78
MOC HQ at Diriyah | MOC Inv-01 | 1 | MOC HQ at Diriyah1 | 11546313 | 0 | 0 | 16597824.65
Mivida BP#189 | Emar PKG#189 IPC18 | 18 | Mivida BP#18918 | 18563752.6 | 0 | 0 | 21162677.964
SSC Suez Steel Company Project | R.O(50:80)S adj ipc4 | 4 | SSC Suez Steel Company Project4 | 6762600 | 0 | 0 | 7709364
Capital One | inv ( 10 ) Captal 1 | 10 | Capital One10 | 314044.9 | 0 | 0 | 314044.9
ElSewedy HQ Internal Finishing | elsewedy HQ- IPC24 | 24 | ElSewedy HQ Internal Finishing24 | 25519032.04 | 0 | 0 | 26794983.642
Kafr Shokr Bridge | kafr shokr ipc 9+ | 9 | Kafr Shokr Bridge9 | 1131554.29 | 0 | 0 | 1188132.0045
Kafr Shokr Bridge | kafr shokr ipc09 | 9 | Kafr Shokr Bridge9 | 4378148.57 | 0 | 0 | 4597055.9985
Ghana Street lighting | Pole. Cvr. Inv.2 | 2 | Ghana Street lighting2 | 13755 | 0 | 0 | 13755
FURJAN Cable Works | 11559 |  | FURJAN Cable Works | 4868005.51 | 0 | 0 | 5111405.7855
LAYAN Substation | 11496 |  | LAYAN Substation | 204999.08 | 0 | 0 | 215249.034
Governmental Campus-N2 | 27 |  | Governmental Campus-N2 | 19087.57 | 19075.1844 | 0 | 19084.1844
Bahr ElBakar – Power Station | IPC#02 - Madkour | 2 | Bahr ElBakar – Power Station2 | 1357812 | 0 | 0 | 1357812
Assuit PP (CP-118) | 2108210012 |  | Assuit PP (CP-118) | 188091.51 | 188091.51 | 0 | 188091.51
Elsewedy Univ - Enabling Works | sewedy uni-mep-07 | 7 | Elsewedy Univ - Enabling Works7 | 4929812 | 0 | 0 | 4929812
Elhegaz | D0028-OB-Dec-2020 | 2020 | Elhegaz2020 | 19094677.06 | 0 | 0 | 19094677.06
Ghana Street lighting | MIDA Ins. Inv. 5 | 5 | Ghana Street lighting5 | 51879.18 | 0 | 0 | 51879.18
Ameria | D0030-OB-Dec-2020 | 2020 | Ameria2020 | 976800 | 0 | 0 | 976800
Koning Food V3 LP-09-20 | 14 |  | Koning Food V3 LP-09-20 | 3907.02 | 0 | 0 | 3907.02
Elhegaz | D0028-OB-Dec-20202 | 20202 | Elhegaz20202 | 3047032.8 | 0 | 0 | 3047032.8
ORA-ZED Towers01B | IPC_4_ORA | 4 | ORA-ZED Towers01B4 | 265558.44 | 0 | 0 | 265558.44
Safir bridge | D0021-OB-Dec-2020 | 2020 | Safir bridge2020 | 2137025 | 0 | 0 | 2137025
Multi Sport Hall | TR0013DEC.Closing |  | Multi Sport Hall | 1884465 | 0 | 0 | 1884465
Ministries Building ROOF | TR0010DEC.Closing |  | Ministries Building ROOF | 419621.64 | 0 | 0 | 419621.64
Mivida | TR0009DEC.Closing |  | Mivida | 1128062.5 | 0 | 0 | 1128062.5
Dubai Port | TR0005DEC.Closing |  | Dubai Port | 92190.9 | 0 | 0 | 92190.9
Sodic East | TR0004DEC.Closing |  | Sodic East | 6723457.11 | 0 | 0 | 6723457.11
Sewage Treatment Plant | D0024-OB-Dec-2020 | 2020 | Sewage Treatment Plant2020 | 3309831 | 0 | 0 | 3309831
Museum of Egyp. Civilization | D0027-OB-Dec-2020 | 2020 | Museum of Egyp. Civilization2020 | 7444035.25 | 0 | 0 | 7444035.25
AWEER POWER STATION 'H' Phase | IMP/061 |  | AWEER POWER STATION 'H' Phase | 1334822.56 | 0 | 0 | 1401563.688
LRT Project | IPC_1_GRowad_LRT | 1 | LRT Project1 | 103200 | 0 | 0 | 103200
Assuit PP (CP-118) | 2011210010 |  | Assuit PP (CP-118) | 3790219.4004 | 0 | 0 | 3790219.4004
Assuit PP (CP-118) | 2009210001 |  | Assuit PP (CP-118) | 2796554.1345 | 0 | 0 | 2796554.1345
Club House-Sodic Wesset | 10037 |  | Club House-Sodic Wesset | 117700 | 0 | 0 | 117700
Manshiet Nasser Substation | 2001210020 |  | Manshiet Nasser Substation | 112340.62 | 102500.56 | 0 | 102500.56
West Damietta PP Phase I | 7 USD - West D. Khor |  | West Damietta PP Phase I | 206295.53 | 206295.53 | 0 | 206295.53
Suez Gulf Substation | 23 EGP VO TOAC |  | Suez Gulf Substation | 285942.83 | 270724.25 | 30080.47 | 300804.72
Elmaragha Bridge - Sohag | IPC#1. | 1 | Elmaragha Bridge - Sohag1 | 1108500 | 0 | 0 | 1108500
Ghana | 30/P/10/ER/2017/USD |  | Ghana | 281189.93 | 0 | 0 | 281189.93
Port Said | Adj Inv 8 Final | 8 | Port Said8 | 2319219.99 | 0 | 0 | 2319219.99
Beni-Suef Power Plant EPC | 180179 |  | Beni-Suef Power Plant EPC | 23871736.05 | 23871736.05 | 0 | 23871736.05
Beni-Suef Power Plant EPC | 6 beni Suef - 1020 | 1020 | Beni-Suef Power Plant EPC1020 | 578156812.05 | 578156812.05 | 0 | 578156812.05
Guinea 2 | P-2S-10 ADJ | 2 | Guinea 22 | 11554466.6 | 0 | 0 | 11554466.6
Al-Shabab PP Phase II (CP-117) | 11 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 170503.2 | 0 | 0 | 170503.2
Marsa Matrouh 500KV | Inv,11 usd Borg Arab | 11 | Marsa Matrouh 500KV11 | 570257.56 | 0 | 0 | 570257.56
Beni-Suef Power Plant EPC | 180121 |  | Beni-Suef Power Plant EPC | 72447911.34 | 0 | 0 | 72447911.34
Akhmem - Qena | Adj Inv 10 | 10 | Akhmem - Qena10 | 129881573.54 | 0 | 0 | 129881573.54
New Heliopolis | Adj Inv 8 | 8 | New Heliopolis8 | 20034607.72 | 0 | 0 | 20034607.72
Siemens 6x500/220 KV GIS-MOU | Adj. Inv. 14 | 14 | Siemens 6x500/220 KV GIS-MOU14 | 146872878.87 | 0 | 0 | 146872878.87
New Capital | Adj Inv. 21 | 21 | New Capital21 | -2859976.89 | 0 | 0 | -2859976.89
Metro 2L Rehabitation Cable | 11 |  | Metro 2L Rehabitation Cable | 23433781 | 0 | 0 | 23433781
Mahmoudia Power Plant | 16 |  | Mahmoudia Power Plant | 1796305467 | 0 | 0 | 1796305467
Cairo South PP Rehabilitation | 90 |  | Cairo South PP Rehabilitation | -1879699.6962 | 0 | 0 | -1879699.6962
Abu Qir PP (CP-118) | 95 |  | Abu Qir PP (CP-118) | 162534882.5048 | 0 | 0 | 162534882.5048
Lina Farm Substation | 6 |  | Lina Farm Substation | 47077633 | 0 | 0 | 47077633
Ain-Sokhna PP (CP-117) | 70 |  | Ain-Sokhna PP (CP-117) | -60401841.9989 | 0 | 0 | -60401841.9989
Banha PP (CP-117) | 73 |  | Banha PP (CP-117) | -28330353.9995 | 0 | 0 | -28330353.9995
Giza North PP Phase3(CP-117) | 83 |  | Giza North PP Phase3(CP-117) | 45181023.2033 | 0 | 0 | 45181023.2033
W Dam PP Phase II (CP-117) | 75 |  | W Dam PP Phase II (CP-117) | 162173895.3701 | 0 | 0 | 162173895.3701
Lina Farm Substation | 2 EGP - Lina |  | Lina Farm Substation | 1056047.85 | 1056047.85 | 0 | 1056047.85
Cairo South PP Rehabilitation | 4 USD - Cairo South |  | Cairo South PP Rehabilitation | 124324.15 | 124324.15 | 0 | 124324.15
Banha PP (CP-118) | 2 USD - Banha 118 |  | Banha PP (CP-118) | 3971.55 | 0 | 0 | 3971.55
Cameron EDC | 030/2021 |  | Cameron EDC | 91259811.22 | 91259810.69 | 0 | 91259810.69
Lina Farm Substation | 6 EGP - Lina |  | Lina Farm Substation | 1281616.08 | 1281616.08 | 0 | 1281616.08
W Dam PP Phase II (CP-117) | 180034 |  | W Dam PP Phase II (CP-117) | 84300.8476 | 0 | 0 | 88515.89
W Dam PP Phase II (CP-117) | 16 EGP - West D. 117 |  | W Dam PP Phase II (CP-117) | 126741.8571 | 0 | 19961 | 19961
Ismailiya East Substation | ISE-SW-EGP-02 | 2 | Ismailiya East Substation2 | 910000 | 673400 | 136500 | 809900
Beni Suef Substation R61 | BSF-SW-EGP-11 | 11 | Beni Suef Substation R6111 | 342125 | 253172.5 | 51318.75 | 304491.25
W Dam PP Phase II (CP-117) | 27 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 149316.5714 | 133265.04 | 23517.36 | 156782.4
IRAQ - Al-Diwaniya Power Plant | 65 USD -Diwaniya |  | IRAQ - Al-Diwaniya Power Plant | 1178165.5524 | 0 | 0 | 0
Giza North PP Phase3(CP-117) | 24 Euro - Giza N.III |  | Giza North PP Phase3(CP-117) | 338411.5429 | 302032.3 | 0 | 302032.3
Beni Seuf - 358 | Banha-Zagazg Inv.02 | 2 | Beni Seuf - 3582 | 14936190.2 | 0 | 2568703.2 | 2568703.2
Kayan 3 New Cairo Capital City | OB-SI-EL Kayaan2 |  | Kayan 3 New Cairo Capital City | 6017614.8 | 6017614.8 | 0 | 6017614.8
Closed | (3) p.o52/156 |  | Closed | 827640 | 0 | 0 | 943509.6
Giza North PP Phase3(CP-117) | Inv 43 EGP Giza III | 43 | Giza North PP Phase3(CP-117)43 | 883836.4667 | 928028.29 | 0 | 928028.29
South Helwan PP (CP-117) | 6 EGP - South Helwan |  | South Helwan PP (CP-117) | 761181.781 | 771723.2 | 0 | 799240.87
Barwa and Damac 220 OHTL | Inv No7 Wattanya220 | 7 | Barwa and Damac 220 OHTL7 | 1088147.3 | 807539.65 | 163222.1 | 970761.75
EMAAR-PKG#107-MARASSI | (4) pkg#107 |  | EMAAR-PKG#107-MARASSI | 5849287 | 4822188.97 | 910581.7 | 5732770.67
Royal City | ROYALCITY-IPC-12 | 12 | Royal City12 | 12232818.51 | 9802860.3155 | 1521591.13 | 11324451.4455
Abo Quir - Badr 500KV | Ref.Ret Bridge2 |  | Abo Quir - Badr 500KV | 167850 | 4699.8 | 0 | 4699.8
South Helwan PP (CP-117) | 180013 |  | South Helwan PP (CP-117) | -3593016.45 | 0 | -1540734.18 | -513578.06
Suez Gulf Substation | 11 USD Suez Gulf |  | Suez Gulf Substation | 66027.72 | 66027.72 | 0 | 66027.72
Suez Gulf Substation | 10 USD Suez Gulf |  | Suez Gulf Substation | 1856743 | 1856743 | 0 | 1856743
Apache Electrical Works | Apachi Inv No PC.#26 |  | Apache Electrical Works | 67749.77 | 67749.77 | 0 | 67749.77
Apache Electrical Works | Abachi Inv No P.C#18 |  | Apache Electrical Works | 44649.31 | 44649.31 | 0 | 44649.31
Al-Wukair 11 Substation | Inv June Qatar |  | Al-Wukair 11 Substation | 10595856.35 | 10595856.35 | 0 | 10595856.35
South Helwan PP (CP-117) | 6 EuroSouth Helwan |  | South Helwan PP (CP-117) | 820360.14 | 820360.14 | 0 | 820360.14
South Helwan PP (CP-117) | 5 EuroSouth Helwan |  | South Helwan PP (CP-117) | 2248485.57 | 2248485.57 | 0 | 2248485.57
EMAAR-PKG#107-MARASSI | (6) pkg#107 |  | EMAAR-PKG#107-MARASSI | 4593486 | 3381863.35 | 640822.23 | 4022685.58
Tebbin PP Rehabitation(CP-124) | 2 EGP - El Tebin 124 |  | Tebbin PP Rehabitation(CP-124) | 9992.26 | 9992.26 | 0 | 9992.26
Strining Lot A- Elegect | Inv No 3 Elegect | 3 | Strining Lot A- Elegect3 | 1018903.51 | 934690.99 | 0 | 934690.99
EMAAR-PKG#85-UPTOWN | (2) pkg#85 |  | EMAAR-PKG#85-UPTOWN | 632221.85 | 293424.1225 | 270591.53 | 564015.6525
Cairo South PP Rehabilitation | Inv 11 Cairo south | 11 | Cairo South PP Rehabilitation11 | 128240.16 | 128240.16 | 0 | 128240.16
Siemens 6x500/220 KV GIS-MOU | Assuit 82 Inv.12 | 12 | Siemens 6x500/220 KV GIS-MOU12 | 2916027.27 | 2090013.95 | 437404.09 | 2527418.04
El Mostakbal City Project | Inv. 16 Mostakbal | 16 | El Mostakbal City Project16 | 89999706 | 0 | 0 | 0
Badr | Inv. 3-4 Badr | 3 | Badr3 | 6253355 | 4642692.35 | 938003.25 | 5580695.6
Siemens 6x500/220 KV GIS-MOU | Ref. Reten 66 wadi19 |  | Siemens 6x500/220 KV GIS-MOU | 248104.43 | 248104.43 | 0 | 248104.43
Abou El Matameer and Sammanoud | Sammound Inv No 1 | 1 | Abou El Matameer and Sammanoud1 | 23528662.92 | 17015634.76 | 3529299.44 | 20544934.2
South Helwan PP (CP-117) | 180058 |  | South Helwan PP (CP-117) | 26982.57 | 24127.24 | 4257.75 | 28384.99
EMAAR-PKG#107-MARASSI | (11) pkg#107 |  | EMAAR-PKG#107-MARASSI | 4966368.53 | 4454492.696 | 0 | 4454492.696
Akhmem Assiut | Soci 1&2 Asuit Akhme |  | Akhmem Assiut | 4121022.42 | 4121022.42 | 0 | 4121022.42
Assuit PP (CP-118) | 2108210007 |  | Assuit PP (CP-118) | 410432.59 | 358519.77 | 64643.13 | 423162.9
Assuit PP (CP-118) | 220721003 |  | Assuit PP (CP-118) | 655334.79 | 585170.6 | 102881.34 | 688051.94
Assuit PP (CP-118) | 2105210006 |  | Assuit PP (CP-118) | 296502.505 | 312107.9 | 0 | 312107.9
Assuit PP (CP-118) | 1903210002 |  | Assuit PP (CP-118) | 373943.67 | 333744.72 | 58896.13 | 392640.85
Al-Shabab PP Phase II (CP-117) | 180031 |  | Al-Shabab PP Phase II (CP-117) | 724244.2476 | 0 | 0 | 760456.46
Abou El Matameer and Sammanoud | Soc 5 abou almatamer |  | Abou El Matameer and Sammanoud | 146474.9 | 146474.88 | 0 | 146474.88
Ismailiya East Substation | (5)cw elasmaaliya |  | Ismailiya East Substation | 4978600.47 | 3709057.35 | 746790.07 | 4455847.42
Ministries Buildings | Mini Landscape IPC04 | 4 | Ministries Buildings4 | 6846859.74 | 1465114.99 | 4395390 | 5860504.99
Apache Electrical Works | Closing Morganti USD |  | Apache Electrical Works | 192916.42 | 145020.88 | 0 | 145020.88
Apache Electrical Works | Closing Morganti bal |  | Apache Electrical Works | 232520.8 | 162104.78 | 0 | 162104.78
Lina Farm Substation | Green power EUR |  | Lina Farm Substation | 14868 | 14868 | 0 | 14868
EMAAR-PKG#53-UPTOWN | PKG#53-IPC 33 | 33 | EMAAR-PKG#53-UPTOWN33 | 3219269.97 | 2214577.5 | 0 | 2214577.5
Kuwait | 36-132KVA(9J) | 132 | Kuwait132 | 57009.91 | 42757.43 | 0 | 42757.43
Akhmem Assiut | Inv.12Assuit Akhmem$ | 12 | Akhmem Assiut12 | 2343024.65 | 1978207.74 | 0 | 1978207.74
Ministries Buildings | MIN-CORE-IPC06 | 6 | Ministries Buildings6 | 13037164.63 | 8237545 | 2745852 | 10983397
Ministries Buildings | MIN-FIT OUT-IPC03 | 3 | Ministries Buildings3 | 1567410.24 | 0 | 1279230.67 | 1279230.67
Marsa Matrouh 500KV | Inv.4 Borg Alarab | 4 | Marsa Matrouh 500KV4 | 10378117.8 | 10378117.8 | 0 | 10378117.8
Abou El Matameer and Sammanoud | Soc.Inv.12 Matamet | 12 | Abou El Matameer and Sammanoud12 | 80779.65 | 80779.65 | 0 | 80779.65
Akhmem Assiut | Inv.15Assuit Akhmem$ | 15 | Akhmem Assiut15 | 502505.24 | 424567.38 | 0 | 424567.38
Akhmem - Qena | Soci.41EGP Qena Akh |  | Akhmem - Qena | 75446.45 | 75446.45 | 0 | 75446.45
Phosfat | Inv.2 Phosfat | 2 | Phosfat2 | 655555.42 | 584675.65 | 0 | 584675.65
South Helwan PP (CP-117) | SH inv.33&34 ded | 33 | South Helwan PP (CP-117)33 | 0 | -7244.06 | 0 | -7244.06
Akhmem - Qena | Ref Instil 4 Qena |  | Akhmem - Qena | 32572164.39 | 32572164.39 | 0 | 32572164.39
AWEER POWER STATION 'H' Phase | CON/026 |  | AWEER POWER STATION 'H' Phase | 266187.22 | 233653.222 | 29576.358 | 263229.58
AWEER POWER STATION 'H' Phase | CON/025 |  | AWEER POWER STATION 'H' Phase | 638849.32 | 560767.7317 | 70983.2583 | 631750.99
AWEER POWER STATION 'H' Phase | LOC/015 |  | AWEER POWER STATION 'H' Phase | 140566.43 | 123386.0815 | 15618.49 | 139004.5715
AWEER POWER STATION 'H' Phase | LOC/010 |  | AWEER POWER STATION 'H' Phase | 2676366.4 | 2646629 | 0 | 2646629
Mall Of Egypt | mall masr-IPC FINAL |  | Mall Of Egypt | 43407790.67 | 237867.55 | 0 | 19146767.55
DPW Onshore Port & Terminal | DP WORLD- IPC 01 | 1 | DPW Onshore Port & Terminal1 | 21619523.77 | 15998139 | 3242928.57 | 19241067.57
DPW Onshore Port & Terminal | dpw ipc33 | 33 | DPW Onshore Port & Terminal33 | 20335452.72 | 15048235.01 | 3050317.91 | 18098552.92
Akhmem - Qena | Social Inv.45-46 Qen | 45 | Akhmem - Qena45 | 348892.8 | 348892.8 | 0 | 348892.8
Strining Lot A- Elegect | Ref.ret.198200 krimt |  | Strining Lot A- Elegect | 198200 | 198200 | 0 | 198200
EMAAR- Pkg 140-ITP-Mivida | PKG#140- IPC13 | 13 | EMAAR- Pkg 140-ITP-Mivida13 | 1425866.3 | 1169767.915 | 149687.31 | 1319455.225
Beni Suef Substation R61 | BSF-CW-EURO-04 | 4 | Beni Suef Substation R614 | 196177.99 | 146152.6 | 29426.7 | 175579.3
Akhmem Assiut | Ref.Ret 3 assuit akh |  | Akhmem Assiut | 605789.54 | 601778 | 0 | 601778
Akhmem - Qena | Ref.Ret 2-3 Qena akh | 3 | Akhmem - Qena3 | 812733.22 | 807520 | 0 | 807520
Kuraiamte Lot1&2 | Ref.reten korimat |  | Kuraiamte Lot1&2 | 15000 | 15000 | 0 | 15000
Al-Wukair 11 Substation | 1905210010 |  | Al-Wukair 11 Substation | 366979.21 | 366979.21 | 0 | 366979.21
MAYSAN 400/132kV SS | 222 |  | MAYSAN 400/132kV SS | 154958.54 | 154958.54 | 0 | 154958.54
AWEER POWER STATION 'H' Phase | 10049 |  | AWEER POWER STATION 'H' Phase | 724555.2 | 1521472.3 | 0 | 760736.15
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 30 | 30 | Benban 500 K.V/95 K.M30 | 52220398.44 | 37261933.77 | 5483141.84 | 42745075.61
Elco Steel 220/33 KV SS | 1903210012 |  | Elco Steel 220/33 KV SS | 61593.9 | 64673.6 | 0 | 64673.6
Benban 500 K.V/95 K.M | Benban Lot2 Inv 16F$ | 16 | Benban 500 K.V/95 K.M16 | 4519011.34 | 3795620.54 | 409820.99 | 4205441.53
MAYSAN 400/132kV SS | 235 |  | MAYSAN 400/132kV SS | 2203500.54 | 2203500.54 | 0 | 2203500.54
Royal City | 20100006 |  | Royal City | 7597991.64 | 7075066.885 | 1423243.71 | 8498310.595
Canal Sugar S/s | Inv 4 $ Sugar S/s | 4 | Canal Sugar S/s4 | 1127442.46 | 860238.6 | 169116.37 | 1029354.97
Akhmem - Qena | Soc Inv 26 $ Quna T | 26 | Akhmem - Qena26 | 159039 | 157735.2 | 0 | 157735.2
Akhmem - Qena | Soc Inv .... Quana |  | Akhmem - Qena | 247339 | 247339 | 0 | 247339
Akhmem - Qena | Soc Inv ...Quana |  | Akhmem - Qena | 1249900 | 1249900 | 0 | 1249900
Suez IPB | 3*14 EGP- Suez Steel |  | Suez IPB | 14182.89 | 14182.89 | 0 | 14182.89
LAYYAH CCPP | 492 |  | LAYYAH CCPP | 2467647 | 2097499.95 | 370147.05 | 2467647
4 SS - Technical Service | 263 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
MAYSAN 400/132kV SS | 276 |  | MAYSAN 400/132kV SS | 419182.98 | 419182.98 | 0 | 419182.98
MOTHANA 400/132kV SS | 271 |  | MOTHANA 400/132kV SS | 656229.68 | 656229.68 | 0 | 656229.68
Akhmem - Qena | soc inv 48 labor Qua | 48 | Akhmem - Qena48 | 64345 | 64345 | 0 | 64345
Akhmem Assiut | Soc Inv 50 labor Asu | 50 | Akhmem Assiut50 | 63670.5 | 63670.5 | 0 | 63670.5
33KV Canal Farm Grid | Inv. 18 Farm | 18 | 33KV Canal Farm Grid18 | 1193427.22 | 0 | 179014.08 | 179014.08
Manshiet Nasser Substation | 1907210017 |  | Manshiet Nasser Substation | 2825453.4 | 3004138.18 | 0 | 3004138.18
Akhmem - Qena | Instill.Pay 5 Akhme2 |  | Akhmem - Qena | 310306.56 | 308124 | 0 | 308124
Siemens 6x500/220 KV GIS-MOU | Refund.Ret.Assuit |  | Siemens 6x500/220 KV GIS-MOU | 4388302.89 | 4383302.89 | 0 | 4383302.89
Latin Compound - New Alamin | inv ( 29 ) 30-9-21 | 29 | Latin Compound - New Alamin29 | 838474 | 14586.29 | 0 | 14586.29
MOTHANA 400/132kV SS | 274 |  | MOTHANA 400/132kV SS | 88777.26 | 88777.26 | 0 | 88777.26
Tamey El-amdeed Substation | TAM-CW-EGP-19 | 19 | Tamey El-amdeed Substation19 | 1066428.5 | 789157.08 | 159964.28 | 949121.36
AWEER POWER STATION 'H' Phase | 10267 |  | AWEER POWER STATION 'H' Phase | 301898 | 316992.9 | 0 | 316992.9
Cairo Capital Cables Tunnel | Tunnel Inv. 8 | 8 | Cairo Capital Cables Tunnel8 | 9223841.7 | 6115406.9 | 2305960.43 | 8421367.33
Beni Suef Add-on Sales | 518 |  | Beni Suef Add-on Sales | 7336866 | 8290658.58 | 0 | 8290658.58
Abu Ghazala Lock & Load | ABO GHZALA L&L-IPC01 | 1 | Abu Ghazala Lock & Load1 | 2200000 | 1459070 | 454462 | 1913532
Beni-Suef Power Plant EPC | Adj.1904210014 |  | Beni-Suef Power Plant EPC | 16897401.78 | 16897401.78 | 0 | 16897401.78
Manshiet Nasser Substation | 180166 |  | Manshiet Nasser Substation | 1438442.16 | 1351776.02 | 158588.25 | 1510364.27
Elco Steel 220/33 KV SS | 1903210005 |  | Elco Steel 220/33 KV SS | 190732.29 | 200268.9 | 0 | 200268.9
Elco Steel 220/33 KV SS | 1904210011 |  | Elco Steel 220/33 KV SS | 17518.63 | 18394.56 | 0 | 18394.56
Elco Steel 220/33 KV SS | 1901210002 |  | Elco Steel 220/33 KV SS | 723284.22 | 759448.43 | 0 | 759448.43
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 26 | 26 | Benban 500 K.V/95 K.M26 | 838750.91 | 646086.4 | 88068.85 | 734155.25
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 6 Inv .17 | 17 | Benban 3/ Toshka 2 LOT 417 | 2028697.87 | 1383175.4 | 213013.28 | 1596188.68
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $2 | 2 | Benban 3/ Toshka 2 LOT 42 | 1237182.5 | 1039025.81 | 129904.16 | 1168929.97
Royal City | ROYAL CITY- IPC0018 | 18 | Royal City18 | 9398674.2 | 4501953.51 | 2391545.92 | 6893499.43
New Giza 2 | NEW GIZA2-IPC FINAL |  | New Giza 2 | 3590050.37 | 2104161 | 0 | 2104161
SHAT Al ARAB 400/132kV SS | 298 |  | SHAT Al ARAB 400/132kV SS | 1441961.89 | 1441961.89 | 0 | 1441961.89
MOTHANA 400/132kV SS | 297 |  | MOTHANA 400/132kV SS | 721322.01 | 721322.01 | 0 | 721322.01
Zafranaa - Ras Ghareb | Inv. Ins10-1/15-12-3 | 1 | Zafranaa - Ras Ghareb1 | 558641.95 | 55475.98 | 0 | 56564.03
Manshiet Nasser Substation | 507 |  | Manshiet Nasser Substation | 648100.62 | 307367.77 | 0 | 307367.77
Tamey El-amdeed Substation | TAM-CALIM-01 | 1 | Tamey El-amdeed Substation1 | 5000000 | 4999415.55 | 0 | 4999415.55
marassi inland marina | IPC#2 | 2 | marassi inland marina2 | 1069424.13 | 267356.03 | 0 | 929929.96
Akhmem Assiut | So.22:25$assuit lot1 |  | Akhmem Assiut | 870270 | 870270 | 0 | 870270
Beni Seuf - 358 | Social Ins.Itay6/358 |  | Beni Seuf - 358 | 179941 | 179941 | 0 | 179941
Akhmem Assiut | Inv.22Assuit Akhmem$ | 22 | Akhmem Assiut22 | 818106.75 | 528417.337 | 0 | 528417.337
ESU Ph2-Enabling & Struc | ESU2-IPC7-ENABLE | 7 | ESU Ph2-Enabling & Struc7 | 9076073.5 | 3548357.425 | 2858963.1 | 6407320.525
Ismailiya East Substation | ISE-CW-EGP-22 | 22 | Ismailiya East Substation22 | 1460588 | 1153864.52 | 0 | 1153864.52
Beni Suef Add-on Sales | 2003210007 |  | Beni Suef Add-on Sales | 250125 | 277638.75 | 0 | 277638.75
Manshiet Nasser Substation | 501 |  | Manshiet Nasser Substation | 20726.78 | 7566.93 | 0 | 7566.93
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv $1 | 1 | Benban 3/ Toshka 2 LOT 41 | 414484.03 | 348166.59 | 43520.82 | 391687.41
SHAT Al ARAB 400/132kV SS | 321 |  | SHAT Al ARAB 400/132kV SS | 225008.85 | 225008.85 | 0 | 225008.85
MAYSAN 400/132kV SS | 307 |  | MAYSAN 400/132kV SS | 138212.12 | 138212.12 | 0 | 138212.12
SHAT Al ARAB 400/132kV SS | 342 |  | SHAT Al ARAB 400/132kV SS | 118204.19 | 118204.19 | 0 | 118204.19
Abu Qir PP (CP-117) | 2003210011 |  | Abu Qir PP (CP-117) | 4875 | 4875 | 0 | 4875
Marsa Matrouh 500KV | Inv.68 Borg Alarab | 68 | Marsa Matrouh 500KV68 | 9614502.86 | 9407789.55 | 0 | 9407789.55
Katamia Dunes Villa | 10029 |  | Katamia Dunes Villa | 47667.26 | 2000 | 30000 | 32000
Marsa Matrouh 500KV | Inv.72 Borg Alarab | 72 | Marsa Matrouh 500KV72 | 2000875.6 | 1642720.75 | 0 | 1642720.75
LAYAN Substation | 10363 |  | LAYAN Substation | 200736 | 339243.84 | 0 | 169621.92
Miscellaneous Projects | 2005210011 |  | Miscellaneous Projects | 2779934.65 | 3141326.15 | 0 | 3141326.15
Baron Palace | 10197 |  | Baron Palace | 2548.48 | 2268.16 | 0 | 2268.16
Miscellaneous Projects | 2004210002 |  | Miscellaneous Projects | 6479.38 | 7321.7 | 0 | 7321.7
Multi Sport Hall | 10096 |  | Multi Sport Hall | 100370.35 | 89329.61 | 0 | 89329.61
R5 | inv(10)50720 | 10 | R510 | 934500 | 140175 | 0 | 871364.75
El Banna project | 442 |  | El Banna project | 1384734.8553 | 0 | 1384734.8553 | 1384734.8553
ESU Ph2-Enabling & Struc | EL.S.U.2-ENABLE-09* | 9 | ESU Ph2-Enabling & Struc9 | 222154.38 | 212579.529 | 0 | 212579.529
LRT - El Shorouk Bridge | IPC#2 | 2 | LRT - El Shorouk Bridge2 | 1168200 | 1047291.3 | 0 | 1047291.3
LRT - El Shorouk Bridge | IPC#1 | 1 | LRT - El Shorouk Bridge1 | 1118700 | 1002914.55 | 0 | 1002914.55
4 SS - Technical Service | 376 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
R5 | inv ( 11 ) | 11 | R511 | 1563000 | 78150 | 0 | 1419380.31
IKEA Extension MoA | IEKA2-MARAKZ-IPC01 | 1 | IKEA Extension MoA1 | 1325211.28 | 1264914.16 | 0 | 1264914.16
MAYSAN 400/132kV SS | 372 |  | MAYSAN 400/132kV SS | 483418.29 | 483418.29 | 0 | 483418.29
LRT - El Shorouk Bridge | IPC#4 | 4 | LRT - El Shorouk Bridge4 | 437580 | 386290.47 | 0 | 386290.47
Benban 3/ Toshka 2 LOT 4 | Toshka Lot 4 Inv .12 | 12 | Benban 3/ Toshka 2 LOT 412 | 14409711.26 | 11686276.22 | 1513019.68 | 13199295.9
Governmental Campus-N2 | 26 |  | Governmental Campus-N2 | 2543859.68 | 0 | 2543859.68 | 2543859.68
El Zagazig Railway P2 | IPC#1 | 1 | El Zagazig Railway P21 | 489480 | 89750.4 | 0 | 89750.4
AWEER POWER STATION 'H' Phase | ENG/034 |  | AWEER POWER STATION 'H' Phase | 172442.17 | 181064.2785 | 0 | 181064.2785
MOTHANA 400/132kV SS | 390 |  | MOTHANA 400/132kV SS | 284952.79 | 284952.79 | 0 | 284952.79
Miscellaneous Projects | 2006210009 |  | Miscellaneous Projects | 8384.62 | 9306.9268 | 0 | 9306.9268
AWEER POWER STATION 'H' Phase | ENG/035 Rev0 |  | AWEER POWER STATION 'H' Phase | 105856.05 | 111148.8525 | 0 | 111148.8525
LRT Project | IPC_2_LRT | 2 | LRT Project2 | 136000 | 115124 | 0 | 115124
DoubleTree Mangroovy ElGouna | MANGROVERENT-IPC3 | 3 | DoubleTree Mangroovy ElGouna3 | 71250 | 74100 | 0 | 74100
Toshka-04 GIS Substation | Cre.adv. $ Toshka 4. |  | Toshka-04 GIS Substation | 0 | 0 | -11677.59 | -11677.59
Assuit PP (CP-118) | 2101210003 |  | Assuit PP (CP-118) | 165327.09 | 147554.42 | 26039.02 | 173593.44
MAYSAN 400/132kV SS | 393 |  | MAYSAN 400/132kV SS | 22225.68 | 22225.68 | 0 | 22225.68
West Port Said 220 kV GIS | P-45-Portsaid Inv.04 | 4 | West Port Said 220 kV GIS4 | 12362859.05 | 0 | 1298100.2 | 1298100.2
Sodic East | IPC_21_Rowad_Seast | 21 | Sodic East21 | 78423.4 | 69443.916 | 0 | 69443.916
ORA-ZED Towers01B | IPC_Ora_4 | 4 | ORA-ZED Towers01B4 | 132779.22 | 113990.96 | 0 | 113990.96
Suez Gulf/S4 - 500KV OHTL | Suez S4 USD Inv. 02 | 2 | Suez Gulf/S4 - 500KV OHTL2 | 1293439.8 | 1083630.81 | 135811.18 | 1219441.99
RING ROAD MARYOTIA EXPANSION | RING MARYOTUA-IPC04 | 4 | RING ROAD MARYOTIA EXPANSION4 | 4364397.86 | 3940994.49 | 0 | 3940994.49
Selwa 220 KV - 27 KM OHTL | Selwa OHTL Inv . 01 | 1 | Selwa 220 KV - 27 KM OHTL1 | 3353492.41 | 3423925.56 | 0 | 3423925.56
Zone(J) South Valley Toshka | South Valley Inv. 11 | 11 | Zone(J) South Valley Toshka11 | 70904705.85 | 52919426.25 | 9075802.35 | 61995228.6
Marazik Railway Bridge | IPC#1 Marazik | 1 | Marazik Railway Bridge1 | 208500 | 184558.32 | 0 | 184558.32
DoubleTree Mangroovy ElGouna | MANGROVE-IPC5B RENT | 5 | DoubleTree Mangroovy ElGouna5 | 3125 | 3187.5 | 0 | 3187.5
AWEER POWER STATION 'H' Phase | Eng/038 |  | AWEER POWER STATION 'H' Phase | 389425.46 | 408896.73 | 0 | 408896.73
MAYSAN 400/132kV SS | 402 |  | MAYSAN 400/132kV SS | 148556.58 | 148556.58 | 0 | 148556.58
Air Force Project | Air Force Inv . 08 | 8 | Air Force Project8 | 11311470.02 | 8098605.6 | 2827867.51 | 10926473.11
Asher Mn Ramadan Bridge No2 | alasher bridge-f+ |  | Asher Mn Ramadan Bridge No2 | 33000 | 33000 | 0 | 33000
Hosh Essa 220 KV OHTL | Hosh Essa Inv. 12 | 12 | Hosh Essa 220 KV OHTL12 | 104897.12 | 0 | 11014.2 | 11014.2
SHAT Al ARAB 400/132kV SS | 408 |  | SHAT Al ARAB 400/132kV SS | 1526892.63 | 1526892.63 | 0 | 1526892.63
MOTHANA 400/132kV SS | 407 |  | MOTHANA 400/132kV SS | 129783.64 | 129783.64 | 0 | 129783.64
33KV Canal Farm Grid | Refund retention 01 |  | 33KV Canal Farm Grid | 4768632.85 | 4768632.85 | 0 | 4768632.85
TZ – Offshore E&M Procurement | 421 |  | TZ – Offshore E&M Procurement | 70670.23 | 70670.23 | 0 | 70670.23
ElMarg | IPC#2 - Marg | 2 | ElMarg2 | 49450 | 39555.5 | 0 | 39555.5
10Th of Ramadan LRT | LRT 10Ramadan Inv.05 | 5 | 10Th of Ramadan LRT5 | 1063082.52 | 0 | 106308.25 | 106308.25
Governmental Campus-N2 | 24 |  | Governmental Campus-N2 | 485707.7 | 485707.7 | 0 | 485707.7
4 SS - Technical Service | 419 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
AWEER POWER STATION 'H' Phase | LOC/016 |  | AWEER POWER STATION 'H' Phase | 1811602.76 | 1590184.64 | 201289.2 | 1791473.84
Air Force Project | Air Force Inv . 11 | 11 | Air Force Project11 | 6851572.16 | 4905315 | 1712893.05 | 6618208.05
El Ameed 220 KV | Ref.Ret ELAmeed |  | El Ameed 220 KV | 39500 | 39500 | 0 | 39500
CFC Podium 2 | CFC IPC025 | 25 | CFC Podium 225 | 13190112.67 | 9682524.4635 | 0 | 9682524.4635
RING ROAD MARYOTIA EXPANSION | El-Marg IPC07 | 7 | RING ROAD MARYOTIA EXPANSION7 | 6420256.71 | 1787764.23 | 0 | 5787764.23
Benban 500 K.V/95 K.M | Ret Benban Lot 2 T |  | Benban 500 K.V/95 K.M | 11755279.89 | 11755279.89 | 0 | 11755279.89
Toshka 2/Owinat East LOT2 OHTL | Toshka Lot4OH Inv.08 | 8 | Toshka 2/Owinat East LOT2 OHTL8 | 2074893.94 | 1533989.24 | 217863.86 | 1751853.1
DRCC | Credit Memo DRCC |  | DRCC | 0 | 0 | -113.49 | -113.49
33KV Canal Farm Grid | Ref.2 sugar Farm T |  | 33KV Canal Farm Grid | 6831156.24 | 6831156.24 | 0 | 6831156.24
Benban 500 K.V/95 K.M | Ref.3 benban Lot 2 T |  | Benban 500 K.V/95 K.M | 10000000 | 10000000 | 0 | 10000000
Akhmem - Qena | Ref.8 Akhme Quana T |  | Akhmem - Qena | 10000000 | 10000000 | 0 | 10000000
NUCA R05 - Z02 | R05 IPC029 | 29 | NUCA R05 - Z0229 | 1322169.7 | 898252.5 | 115012 | 1013264.5
Sokhna Port Expansion | sokhna port ex ipc10 | 10 | Sokhna Port Expansion10 | 39642891.35 | 27461819.55 | 7928578.26 | 35390397.81
158E/2019 33kv Project | 11062 |  | 158E/2019 33kv Project | 104000 | 109200 | 0 | 109200
Air Force Project | Air Force Inv . 21 | 21 | Air Force Project21 | 4593369.44 | 4436962 | 0 | 4436962
Ring Road Bridges Project | INV ( 7 ) Ring R | 7 | Ring Road Bridges Project7 | 4235172 | 3553200.32 | 0 | 3553200.32
TZ – Offshore E&M Procurement | 472 |  | TZ – Offshore E&M Procurement | 78872.94 | 0 | 15774.59 | 15774.59
TZ – Offshore E&M Procurement | 463 |  | TZ – Offshore E&M Procurement | 86394.34 | 8056.76 | 0 | 8056.76
Benban 500 K.V / 100 K.M | رد تامين بنبان لوط 1 |  | Benban 500 K.V / 100 K.M | 10000000 | 10000000 | 0 | 10000000
PLAYA ROOF & Wet Areas | IPC-1-PLAYA ROOF | 1 | PLAYA ROOF & Wet Areas1 | 465527.7 | 399466.31 | 0 | 399466.31
Taval Sarai 52 | IPC-16-SARAY | 16 | Taval Sarai 5216 | 31911.3 | 27447.1702 | 0 | 27447.1702
Egyptian Exchange building | IPC-2-BORSA | 2 | Egyptian Exchange building2 | 157350.13 | 139333.53 | 0 | 139333.53
seashell Playa | IPC-11-PLAYA | 11 | seashell Playa11 | 151371.6 | 105672.51 | 24219.46 | 129891.97
Ain Sokhna Port Development | IPC#7 Sokhna Port | 7 | Ain Sokhna Port Development7 | 1426672 | 1101390.78 | 0 | 1341071.68
New Babil 400/132KV GIS Substa | 2201210002 |  | New Babil 400/132KV GIS Substa | 461933.6 | 461933.6 | 0 | 461933.6
10th Ramadan Indu Park Plot11 | 10th Ind Park Inv.01 | 1 | 10th Ramadan Indu Park Plot111 | 6065851.81 | 4179371.89 | 955371.66 | 5134743.55
Cairo-Alex Railway | cairo-alex ipc16 | 16 | Cairo-Alex Railway16 | 26294302.62 | 18095195.25 | 2760901.78 | 20856097.03
Racecores 3092-17 132KV E | 11368 |  | Racecores 3092-17 132KV E | 701153.6942 | 3554849.22 | 0 | 592474.87
Ghana Street lighting | MIDA Ins. Inv.10 | 10 | Ghana Street lighting10 | 12865.6 | 11579.04 | 0 | 11579.04
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 17 | 17 | Suez Gulf/S4 - 500KV OHTL17 | 814311.61 | 245883.04 | 0 | 245883.04
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 12 | 12 | Suez Gulf/S4 - 500KV OHTL12 | 1597816.61 | 463592.36 | 0 | 463592.36
Mivida BP#189 | PKG#189 IPC 30 | 30 | Mivida BP#18930 | 22415427.41 | 14412191.1105 | 2417376.75 | 16829567.8605
National Batteries LP-05-20 | 38 |  | National Batteries LP-05-20 | 2412280.71 | 2750000.01 | 0 | 2750000.01
El Mostakbal City Project | Inv. 15 Mostakbal | 15 | El Mostakbal City Project15 | 117317404.76 | 37374677.67 | 21472965.19 | 58847642.86
El Khatatba Bridge | EL KHATATBA IPC02 | 2 | El Khatatba Bridge2 | 2437694.05 | 1381244.0525 | 0 | 1381244.0525
Aljazi Project | Al - Jazi Inv. 3 | 3 | Aljazi Project3 | 121070 | 58174.3 | 0 | 58174.3
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv13 | 13 | Marsa Alam/ Bernes LOT2 OHTL13 | 228072.6 | 205215.78 | 0 | 205215.78
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 9 | 9 | Marsa Alam/ Bernes LOT2 OHTL9 | 62479.21 | 55854.37 | 0 | 55854.37
Selwa / New Isna 220KV OHTL | Selwa - Isna Inv. 01 | 1 | Selwa / New Isna 220KV OHTL1 | 2177093.48 | 2015950.57 | 0 | 2015950.57
HST Bridges-Sokhna & Mahager | SOKHNA BRIDGE IPC03 | 3 | HST Bridges-Sokhna & Mahager3 | 4418251.43 | 4374068.9215 | 0 | 4374068.9215
Ain Sokhna Port Development | IPC#16 - Sokhna Port | 16 | Ain Sokhna Port Development16 | 246924 | 185420.68 | 0 | 231775.85
Assuit PP (CP-118) | 220721006 |  | Assuit PP (CP-118) | 1365739.79 | 1400586.7175 | 33401.06 | 1433987.7775
SSC Suez Steel Company Project | in&reSupply-SSC IPC2 | 2 | SSC Suez Steel Company Project2 | 3765789.87 | 3190884.0818 | 1064458.47 | 4255342.5518
SSC Suez Steel Company Project | In&ReApply(SSC)-IPC1 | 1 | SSC Suez Steel Company Project1 | 1124419.48 | 1102291.6272 | 145814 | 1248105.6272
Marassi Epoxy | TR0047-IPC00001 | 1 | Marassi Epoxy1 | 83820 | 71925.94 | 0 | 71925.94
CS-20 Mall | inv ( 14 ) CS-20 | 14 | CS-20 Mall14 | 67848.81 | 63777.88 | 0 | 63777.88
CS-20 Mall | inv ( 12 ) CS-20 | 12 | CS-20 Mall12 | 376497.27 | 150598.91 | 0 | 150598.91
Kattameya Creeks | Kattameya IPC20 | 20 | Kattameya Creeks20 | 25275496.94 | 24429045.007 | 1857471.81 | 26286516.817
EGAT Pelletizing Plant | Plant supply Ro ipc3 | 3 | EGAT Pelletizing Plant3 | 11779040 | 1531275.2 | 11779040 | 13310315.2
RING ROAD MARYOTIA EXPANSION | ipc23 el maryotia | 23 | RING ROAD MARYOTIA EXPANSION23 | 1935881.9 | 1673762.43 | 0 | 1673762.43
Ministries Buildings | Mini Core IPC10 | 10 | Ministries Buildings10 | 6320819 | 5324885 | 0 | 5324885
EGAT Pelletizing Plant | EGAT watertank IPC13 | 13 | EGAT Pelletizing Plant13 | 376223.99 | 391272.9495 | 0 | 391272.9495
New Giza Hospital | IPC005RMENEWGIZAHOSP | 5 | New Giza Hospital5 | 36839.36 | 30804.8 | 0 | 30804.8
Mivida BP#189 | PKG#189- IPC (15) | 15 | Mivida BP#18915 | 18379426.48 | 20013901.014 | 4268668.94 | 24282569.954
Abou Ghaleb Bridge | abo ghaleb ipc04 | 4 | Abou Ghaleb Bridge4 | 2545336.5 | 2519883.145 | 0 | 2519883.145
Get Business Complex | INV ( 18 ) GET | 18 | Get Business Complex18 | 298864.75 | 59772.95 | 0 | 59772.95
Creeks URBN-K | Katamya Urbnk ipc14 | 14 | Creeks URBN-K14 | 7646354.5 | 6223872.155 | 1152224.35 | 7376096.505
RING ROAD MARYOTIA EXPANSION | Mariotya ipc 19 | 19 | RING ROAD MARYOTIA EXPANSION19 | 2168187.95 | 1876305.07 | 0 | 1876305.07
MDF Factory | MDF3 - IPC9 | 9 | MDF Factory9 | 2622768.25 | 1901506.985 | 747488.95 | 2648995.935
EGAT Injection | IPC00003 | 3 | EGAT Injection3 | 43330.5 | 37181.9 | 0 | 37181.9
Air Defence College | IPC#005 air defense | 5 | Air Defence College5 | 211750.14 | 179775.86 | 0 | 179775.86
Egyptian Exchange building | IPC09-Exchange RME | 9 | Egyptian Exchange building9 | 96748.76 | 85671.02 | 0 | 85671.02
Business District Hyde Park | INV ( 3 ) HY Bark | 3 | Business District Hyde Park3 | 347415 | 296692.41 | 0 | 296692.41
Business District Hyde Park | INV ( 2 ) HY Bark | 2 | Business District Hyde Park2 | 1127787 | 963130.1 | 0 | 963130.1
PLAYA ROOF & Wet Areas | IPC0000016 | 16 | PLAYA ROOF & Wet Areas16 | 40852.24 | 35055.31 | 0 | 35055.31
PLAYA ROOF & Wet Areas | IPC0019 | 19 | PLAYA ROOF & Wet Areas19 | 264385.95 | 226869.57 | 0 | 226869.57
Expansion of Ring Road-CFA | IPC 3 CFA | 3 | Expansion of Ring Road-CFA3 | 169935 | 150000 | 0 | 150000
DP World Basin 2 Ph2 | DP World ph.2-IPC 1 | 1 | DP World Basin 2 Ph21 | 24448993.55 | 21759604.25 | 0 | 21759604.25
MDF Factory | MDF 2 - IPC 13 | 13 | MDF Factory13 | 478450.77 | 483235.2778 | 0 | 483235.2778
Ministries Buildings | Minis MEP IPC7 | 7 | Ministries Buildings7 | 177952479 | 118055250 | 0 | 118055250
MDF Factory | MDF 3 IPC( 11) | 11 | MDF Factory11 | 1606948.05 | 1123017.527 | 500000 | 1623017.527
Air Defense College | Air sihi IPC1 | 1 | Air Defense College1 | 4288332 | 1280760 | 2300000 | 3580760
PLAYA ROOF & Wet Areas | IPC0021 TR41 | 21 | PLAYA ROOF & Wet Areas21 | 132780.21 | 113938.19 | 0 | 113938.19
EMAAR-Pkg#162/163- Marassi | EMaarPKG#177 IPC 43 | 43 | EMAAR-Pkg#162/163- Marassi43 | 15896560.84 | 15323561.672 | 0 | 15323561.672
SEASHELL TECHNICAL ROOM | IPC04 TR65 | 4 | SEASHELL TECHNICAL ROOM4 | 3974.32 | 3432.22 | 0 | 3432.22
U3 & U5 | IPC10 TR55 | 10 | U3 & U510 | 21350.8 | 18438.55 | 0 | 18438.55
HST El Mahager Bridge | ipc 3 elmahager | 3 | HST El Mahager Bridge3 | 7054473.33 | 6250171.5 | 0 | 6250171.5
Seashell Playa 5 Villas | playa c104- ipc 7 | 7 | Seashell Playa 5 Villas7 | 279706.62 | 232507.66 | 0 | 232507.66
Marassi - Water proofing | IPC 3 TR0044 | 3 | Marassi - Water proofing3 | 45658.84 | 35430.91 | 0 | 35430.91
Marassi - Anti carbonation | IPC003 TR43 | 3 | Marassi - Anti carbonation3 | 59705.1 | 17868.86 | 0 | 17868.86
Olympic City Lock&Load | Olympic L&L IPC1 | 1 | Olympic City Lock&Load1 | 3638578 | 3022610 | 0 | 3022610
EGAT Pelletizing Plant | egat P supply ipc 1 | 1 | EGAT Pelletizing Plant1 | 1390180.04 | 1570903.4452 | 0 | 1570903.4452
DP World Basin 2 Ph2 | Dp World ph2 ipc(6) | 6 | DP World Basin 2 Ph26 | 32175841.3 | 23809772.84 | 4826376.19 | 28636149.03
MDF Factory | mdf 2 ipc (17) | 17 | MDF Factory17 | 614911.7 | 536737.62 | 0 | 536737.62
British International School | BIS IPC (3) | 3 | British International School3 | 11138109 | 10414131.92 | 0 | 10414131.92
DP World Basin 2 Ph2 | DP world ipc (5) | 5 | DP World Basin 2 Ph25 | 40682207.5 | 30104833.54 | 6102331.12 | 36207164.66
British International School | Bis ipc ( 2) | 2 | British International School2 | 8895320.4 | 4500000 | 0 | 4500000
Tarek Abdel-Hakim Center | TAH ipc08 | 8 | Tarek Abdel-Hakim Center8 | 3071127.97 | 2363232.97 | 276401.52 | 2639634.49
26th of July Corridor New | IPC 1 26th july | 1 | 26th of July Corridor New1 | 612000 | 525157.2 | 0 | 525157.2
Borg El Arab Bridge - Km 21 | IPC#03 Kilo 21 | 3 | Borg El Arab Bridge - Km 213 | 153140 | 143951.6 | 0 | 143951.6
El-Herafeen brigde | IPC#1 Credit | 1 | El-Herafeen brigde1 | -18585 | -18585 | 0 | -18585
Ameria | 310321 |  | Ameria | -120000 | -120000 | 0 | -120000
Seashell Playa 5 Villas | Playa c104 ipc 8 | 8 | Seashell Playa 5 Villas8 | 731710.17 | 522023.35 | 0 | 522023.35
Seashell Playa 5 Villas | PLAYA - C072 IPC 3 | 3 | Seashell Playa 5 Villas3 | 93725.55 | 65948.14 | 0 | 65948.14
U4,U8 Seashell Playa | IPC10TR0060 | 10 | U4,U8 Seashell Playa10 | 31445.08 | 27155.97 | 0 | 27155.97
Mohamed Ali Palace Restoration | MOHAMED ALY2 FINAL |  | Mohamed Ali Palace Restoration | 271501.23 | 255350 | 0 | 255350
KATAMYA GREEKS LAND SCAPE STAR | IPC02TR0081 | 2 | KATAMYA GREEKS LAND SCAPE STAR2 | 1470429.19 | 1453666.51 | 0 | 1453666.51
Sultana Malak Restoration | sultana malak ipc03 | 3 | Sultana Malak Restoration3 | 1079127.29 | 282361.25 | 677115 | 959476.25
Air Defense College | Air dev shabkat IPC2 | 2 | Air Defense College2 | 5675439 | 4781150 | 0 | 4781150
Venice Mall | inv ( 2 ) vensia | 2 | Venice Mall2 | 58480 | 52047.2 | 0 | 52047.2
EIPICO C002-23 | IPC0001 TR68 | 1 | EIPICO C002-231 | 106044.19 | 90996.52 | 0 | 90996.52
Quarry Bridge | inv ( 1 ) MAHGER Br | 1 | Quarry Bridge1 | 4110000 | 810561 | 0 | 810561
SSC Suez Steel Company Project | Baraka Fence ipc 5 | 5 | SSC Suez Steel Company Project5 | 7617134 | 0 | 2285140.2 | 2285140.2
Seashell Playa 5 Villas | playa-c045 ipc 5 | 5 | Seashell Playa 5 Villas5 | 20694.48 | 17871.75 | 0 | 17871.75
Olympic MultiSport Hall | IPC01TR0079 | 1 | Olympic MultiSport Hall1 | 49280 | 41469.12 | 0 | 41469.12
Ora Zed -Landscape | IPC002 TR70 | 2 | Ora Zed -Landscape2 | 43452.13 | 32464.11 | 0 | 32464.11
Seashell Playa 5 Villas | Playa-c038 ipc 9 | 9 | Seashell Playa 5 Villas9 | 33072.33 | 28561.17 | 0 | 28561.17
Katameya Creeks - RME | IPC14TR0053 | 14 | Katameya Creeks - RME14 | 10371.46 | 9183.94 | 0 | 9183.94
Katameya Creeks - RME | IPC10 TR53 | 10 | Katameya Creeks - RME10 | 12213.55 | 10815.1 | 0 | 10815.1
EIPICO Factory | IPC003 TR54 | 3 | EIPICO Factory3 | 34283.4 | 29418.58 | 0 | 29418.58
SOL Town PKG.220 | pkg#220- ipc 4 | 4 | SOL Town PKG.2204 | 1274131.45 | 1849642.29 | 0 | 1849642.29
SSC Suez Steel Company Project | Revamp ipc 8 | 8 | SSC Suez Steel Company Project8 | 2887080.34 | 1992085.4336 | 866124.1 | 2858209.5336
Irrigation Tank | IPC06TR0061 | 6 | Irrigation Tank6 | 289444.8 | 249964.53 | 0 | 249964.53
U7-SEASHELL | IPC14TR0064 | 14 | U7-SEASHELL14 | 62375.6 | 53867.56 | 0 | 53867.56
AIRDEFNSE -EPOXY | IPC08TR0066 | 8 | AIRDEFNSE -EPOXY8 | 104010.4 | 88304.83 | 0 | 88304.83
MDF Factory | mdf local ipc 17 | 17 | MDF Factory17 | 791.23 | 799.1422 | 0 | 799.1422
U4,U8 Seashell Playa | IPC12TR0060 | 12 | U4,U8 Seashell Playa12 | 724900 | 574873.65 | 0 | 574873.65
Abou Ghaleb Bridge | ABO GHALEB ESC 1:11 |  | Abou Ghaleb Bridge | 3359523.81 | 3244903.17 | 0 | 3244903.17
Seashell Playa 5 Villas | Playa-c470 ipc 1 | 1 | Seashell Playa 5 Villas1 | 215083.62 | 185746.2 | 0 | 185746.2
Wady El Natroon Bridge | wady elnatron ipc9 | 9 | Wady El Natroon Bridge9 | 9721357.14 | 8667165 | 0 | 8667165
Sokhna Port Expansion | SPX INT.ROADS2 FINAL |  | Sokhna Port Expansion | 56070.14 | 3219.75 | 0 | 3219.75
MDF Factory | MDf Local ipc 19 | 19 | MDF Factory19 | 4087720.52 | 3358613 | 0 | 3358613
RING ROAD MARYOTIA EXPANSION | mariotya esc 1:22 es |  | RING ROAD MARYOTIA EXPANSION | 1247325.71 | 1204519.8 | 0 | 1204519.8
Seashell Playa 5 Villas | Playa c469 - ipc 2 | 2 | Seashell Playa 5 Villas2 | 297812.93 | 272081.89 | 0 | 272081.89
U7-SEASHELL | IPC21TR0064 | 21 | U7-SEASHELL21 | 633528.25 | 500000 | 0 | 500000
Open Channal | IPC06TR0074 | 6 | Open Channal6 | 332096.32 | 286466.28 | 0 | 286466.28
Olympic MultiSport Hall | IPC03TR0079 | 3 | Olympic MultiSport Hall3 | 40252.8 | 33872.73 | 0 | 33872.73
Ora Zed Landscape Ph1 | Ora landscape-IPC18 | 18 | Ora Zed Landscape Ph118 | 1175128.22 | 975356.43 | 123388.46 | 1098744.89
SSC Suez Steel Company Project | V.O Smp2 ipc 1 | 1 | SSC Suez Steel Company Project1 | 1132829 | 1121500.71 | 0 | 1121500.71
Senator | Inv ( 3 ) Sentor | 3 | Senator3 | 153232 | 83000 | 0 | 83000
Rabigh PP - Piling Works | Inv-04 | 4 | Rabigh PP - Piling Works4 | 1553962.12 | 5361169.32 | 0 | 1787056.44
Roof-Playa Cluster A,B,C | IPC09TR0088 | 9 | Roof-Playa Cluster A,B,C9 | 371928.37 | 321197.34 | 0 | 321197.34
Al-Parco | INV ( 10 ) ALparco | 10 | Al-Parco10 | 2205121.51 | 241095.43 | 0 | 241095.43
ORA-ZED Towers P01B | IPC15TR0051 | 15 | ORA-ZED Towers P01B15 | 143352.86 | 126936.46 | 0 | 126936.46
Open Channal | IPC07TR0074 | 7 | Open Channal7 | 125000 | 107825 | 0 | 107825
Roof-Playa Cluster A,B,C | IPC10TR0088 | 10 | Roof-Playa Cluster A,B,C10 | 534780.49 | 393479.26 | 0 | 393479.26
U4,U8 Seashell Playa | IPC18TR0060 | 18 | U4,U8 Seashell Playa18 | 284793.15 | 216564.36 | 0 | 216564.36
Katameya Creeks - RME | IPC24TR0053 | 24 | Katameya Creeks - RME24 | 800341.7 | 708702.08 | 0 | 708702.08
Open Channal | IPC03TR0074 | 3 | Open Channal3 | 110592 | 95396.66 | 0 | 95396.66
U4,U8 Seashell Playa | IPC19TR0060 | 19 | U4,U8 Seashell Playa19 | 697767.53 | 568772.71 | 0 | 568772.71
Roof-Playa Cluster A,B,C | IPC11TR0088 | 11 | Roof-Playa Cluster A,B,C11 | 1087452.41 | 925073.9 | 0 | 925073.9
Seashell Playa 5 Villas | Playa c470 ipc 6 | 6 | Seashell Playa 5 Villas6 | 54184.3 | 46793.55 | 0 | 46793.55
Kemet Tower | INV(10 final ) Kemet | 10 | Kemet Tower10 | 112800 | 96793.68 | 0 | 96793.68
JICA lot 02 | JICA lot 02 Inv. 01 | 1 | JICA lot 021 | 29289728.56 | 0 | 0 | #DIV/0!
RING ROAD MARYOTIA EXPANSION | crMaryotya IPC06 | 6 | RING ROAD MARYOTIA EXPANSION6 | -2460952.38 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | IPC# FINAL SUHAG |  | Elmaragha Bridge - Sohag | 346077.5 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | 10001 |  | Abo Quir - Badr 500KV | 34370.43 | 0 | 0 | #DIV/0!
Celia | IPC#006CR | 6 | Celia6 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 33 |  | Suez Gulf Substation | 2735633.8944 | 0 | 0 | #DIV/0!
MDF Factory | CR-MDF IPC13 | 13 | MDF Factory13 | 0 | 0 | 0 | #DIV/0!
Lahoon 220/22/22 | CR.Al Lahoon Inv 01 | 1 | Lahoon 220/22/221 | 0 | 0 | 0 | #DIV/0!
ORA ZED-Ph 2-Pkgs A&D | cr-ora zed2 ipc16 | 16 | ORA ZED-Ph 2-Pkgs A&D16 | 0 | 0 | 0 | #DIV/0!
LP-07-21 Petrojet | 82 |  | LP-07-21 Petrojet | 28249911.55 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10171 |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
Palm Hill-Infra Str(Elec.Work) | DEC ADJ 107 |  | Palm Hill-Infra Str(Elec.Work) | 0 | 0 | 0 | #DIV/0!
Sewage Treatment Plant | IPC#4&5 | 4 | Sewage Treatment Plant4 | 1257865 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | Adjust 180177 |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
Royal City | Cr Royal fin ipc43 | 43 | Royal City43 | 0 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11453 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
LP-18-21 ODP Passive & DC | 97 |  | LP-18-21 ODP Passive & DC | 2790163.2473 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Assuit Inv.2 ded | 2 | Assuit PP (CP-118)2 | 1172138.01 | 2344276.02 | 0 | 2344276.02
W Dam PP Phase II (CP-117) | 262 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Infra Project 4428 | 220621007 |  | Infra Project 4428 | 285714285.72 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | Cr.90 |  | Abou El Matameer and Sammanoud | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH Inv.27&28 ded. | 27 | South Helwan PP (CP-117)27 | 0 | 0 | 0 | #DIV/0!
Benban 500 K.V/95 K.M | CR.Ref-Ret-Benban2 |  | Benban 500 K.V/95 K.M | 0 | 0 | 0 | #DIV/0!
C5 Bridge 2 New Alamein | D0011-OB-Dec-2020/Cr | 2020 | C5 Bridge 2 New Alamein2020 | 0 | 0 | 0 | #DIV/0!
EGAT Pelletizing Plant | CR ELCO EGAT IPC17 | 17 | EGAT Pelletizing Plant17 | 0 | 0 | 0 | #DIV/0!
El-Warraq | IPC#FINAL#El-Warraq |  | El-Warraq | 984000 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 264 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 94 |  | FX-01-22 Decent Life-WD | 76178.17 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj 180119-180120 | 180120 | Beni-Suef Power Plant EPC180120 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 18 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 293419.819 | 0 | 0 | #DIV/0!
TOSHKA MADKOUR | C.1 |  | TOSHKA MADKOUR | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref Akhmm Asuit4T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Beni Suef ISKRA | 1907220005 |  | Beni Suef ISKRA | 0 | 0 | 0 | #DIV/0!
ORA ZED - Ph 01B - Pkgs A&D | Ora Zed ipc 38 M | 38 | ORA ZED - Ph 01B - Pkgs A&D38 | 3482324.82 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 4 EUR - South Helwan |  | South Helwan PP (CP-117) | 504604.0762 | 0 | 0 | #DIV/0!
Haramein Columns Transfer | cr-haramin ipc01 | 1 | Haramein Columns Transfer1 | 0 | 0 | 0 | #DIV/0!
Port Said | Cr Adj Inv 8 Final | 8 | Port Said8 | 0 | 0 | 0 | #DIV/0!
Cameron EDC | 5007 Credit |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Residence 8 ( S09 ) | Cr.Inv ( 1 ) S09 | 1 | Residence 8 ( S09 )1 | 0 | 0 | 0 | #DIV/0!
LRT - El Shorouk Bridge | D0034-OB-Dec-2020/Cr | 2020 | LRT - El Shorouk Bridge2020 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ref Akhmm Asuit5T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Residence 8 ( K10 ) | Cr.Inv ( 2 ) K 10 | 2 | Residence 8 ( K10 )2 | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | CR-KAFR SHOKR2 |  | Kafr Shokr Bridge | 0 | 0 | 0 | #DIV/0!
Celia | CR-IPC#2 | 2 | Celia2 | 0 | 0 | 0 | #DIV/0!
Port Said | Cr. Inv. 8 Bortsaid | 8 | Port Said8 | 0 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Inv.18 - Lot 1 | 18 | Mauritania Lot 118 | 117062 | 0 | 0 | #DIV/0!
SSC Suez Steel Company Project | L967/2024 |  | SSC Suez Steel Company Project | 7476526 | 0 | 0 | #DIV/0!
U3 & U5 | IPC007TR55 | 7 | U3 & U57 | 44347.28 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | DEC ADJ 23 |  | Giza North PP Phase3(CP-117) | 342523.91 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR- 16 EGP - West D. | 16 | W Dam PP Phase II (CP-117)16 | 0 | 0 | 0 | #DIV/0!
Seashell Playa 5 Villas | CRseashell playaIPC1 | 1 | Seashell Playa 5 Villas1 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10428 |  | AWEER POWER STATION 'H' Phase | 1065842.99 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 220722001 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Hosh Eisa Hospit. | can. IPC01TR0089 | 1 | Hosh Eisa Hospit.1 | 0 | 0 | 0 | #DIV/0!
Berket Ghelion | RE 18 |  | Berket Ghelion | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR- 8 USD- Shabab | 8 | Al-Shabab PP Phase II (CP-117)8 | 0 | 0 | 0 | #DIV/0!
Ain-Sokhna PP (CP-111) | close client |  | Ain-Sokhna PP (CP-111) | 0 | 0 | 0 | #DIV/0!
RING ROAD MARYOTIA EXPANSION | cr mariotya esc.19es |  | RING ROAD MARYOTIA EXPANSION | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 11 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 434762.5333 | 0 | 0 | #DIV/0!
Get Business Complex | INV ( 23 ) GET | 23 | Get Business Complex23 | 208126.81 | 0 | 0 | #DIV/0!
ZED Phase 2 | IPC12TR0062 | 12 | ZED Phase 212 | 19091.11 | 0 | 0 | #DIV/0!
Attaqa Power Plant | Discount interest |  | Attaqa Power Plant | 0 | 0 | 0 | #DIV/0!
EL -mahager Bridge Ain sokhna | 2 |  | EL -mahager Bridge Ain sokhna | 0 | 0 | 0 | #DIV/0!
HAC CCC JV | D0008-OB-Dec-2020/Cr | 2020 | HAC CCC JV2020 | 0 | 0 | 0 | #DIV/0!
Port Said Port Silos | cr-port said1-supply |  | Port Said Port Silos | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180081 |  | Suez Gulf Substation | 17815.17 | 0 | 0 | #DIV/0!
Open Channal | C.ipc01 | 1 | Open Channal1 | 0 | 0 | 0 | #DIV/0!
R05 | CR-IPC_1_R5 | 1 | R051 | 0 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | Inv. No. 3 - intrest | 3 | Angola Emergency fast-track3 | 23797596.41 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 303 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
JICA lot 02 | JICA lot 02 Inv.$ 01 |  | JICA lot 02 | 2067501.12 | 0 | 0 | #DIV/0!
Banha PP (CP-118) | DEC ADJ 11 |  | Banha PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Kafr Shokr Bridge | Cr-م 10 كفر شكر | 10 | Kafr Shokr Bridge10 | 0 | 0 | 0 | #DIV/0!
Abou El Matameer and Sammanoud | CR Samanoud 5 inv.81 | 81 | Abou El Matameer and Sammanoud81 | 0 | 0 | 0 | #DIV/0!
Wadi El Natroun | D0014-OB-Dec-2020/Cr | 2020 | Wadi El Natroun2020 | 0 | 0 | 0 | #DIV/0!
Pyramids Industrial P - East | Inv. 17 Fin PIP EAST | 17 | Pyramids Industrial P - East17 | 5689276.96 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2007220003 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2011220006 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Museum of Egyp. Civilization | CR-IPC#4 | 4 | Museum of Egyp. Civilization4 | 0 | 0 | 0 | #DIV/0!
East Owainat | 15 |  | East Owainat | -11517.22 | 0 | 0 | #DIV/0!
PIP West 2 | Cr Adj inv 2 | 2 | PIP West 22 | 0 | 0 | 0 | #DIV/0!
DRCC | P-44-EGY اتحاد تشيد | 44 | DRCC44 | 5000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 92 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2009220001 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | CR1IPC_5_Gama_Saray | 5 | Taval Sarai 525 | 0 | 0 | 0 | #DIV/0!
Marsa Alam/ Bernes LOT2 OHTL | Soc.2020 تشيد مرسى |  | Marsa Alam/ Bernes LOT2 OHTL | 5000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 85 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 65 |  | Al-Shabab PP Phase II (CP-117) | 19158118.26 | 0 | 0 | #DIV/0!
Kayan 3 New Cairo Capital City | OB-RE-EL Kayaan |  | Kayan 3 New Cairo Capital City | 6017614.8 | 0 | 0 | #DIV/0!
Benban 500 K.V/95 K.M | CR.2 benban Lot 2 |  | Benban 500 K.V/95 K.M | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 63 |  | Al-Shabab PP Phase II (CP-117) | -7373940.95 | 0 | 0 | #DIV/0!
Zambia | CR.P-2-10 AccRev | 2 | Zambia2 | 0 | 0 | 0 | #DIV/0!
Manshiet Nasser Substation | 2008220004 |  | Manshiet Nasser Substation | 0 | 0 | 0 | #DIV/0!
EL Sewedy University Tec. | CR-INV ( 2 ) S.UNIV | 2 | EL Sewedy University Tec.2 | 0 | 0 | 0 | #DIV/0!
Taval Sarai 52 | Cr.IPC_5_Gama_salary | 5 | Taval Sarai 525 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR-19 EGP- Shabab | 19 | Al-Shabab PP Phase II (CP-117)19 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | cr Soc inv 48 As | 48 | Akhmem Assiut48 | 0 | 0 | 0 | #DIV/0!
Expansion of Ring Road-CFA | IPC#4 CFA | 4 | Expansion of Ring Road-CFA4 | 377421.5 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | ANG-Cam-Inv 4 - part | 4 | Angola Emergency fast-track4 | 16100 | 0 | 0 | #DIV/0!
Ghana Street lighting | MIDA Sply.Inv.2Ret. | 2 | Ghana Street lighting2 | 71126.5 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 48 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Abu Qir PP (CP-118) | DEC ADJ 29 |  | Abu Qir PP (CP-118) | 0 | 0 | 0 | #DIV/0!
Open Channel 2 | C.INV.2 | 2 | Open Channel 22 | 0 | 0 | 0 | #DIV/0!
FX-05-22 Close compound | 95 |  | FX-05-22 Close compound | 199533.21 | 0 | 0 | #DIV/0!
LAYAN Substation | 11520 |  | LAYAN Substation | 0 | 0 | 0 | #DIV/0!
Museum of Egyp. Civilization | D0027-OB-Dec-2020/Cr | 2020 | Museum of Egyp. Civilization2020 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DEC ADJ 82 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
El Boghaz Brigde | IPC#22 CR | 22 | El Boghaz Brigde22 | 0 | 0 | 0 | #DIV/0!
Sokhna Port Expansion | cr-SPX ROADS 2 FINAL |  | Sokhna Port Expansion | 0 | 0 | 0 | #DIV/0!
Mauritania-Lot 2 | Inv.6 – Lot 2 RDC | 6 | Mauritania-Lot 26 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Cr. Amend - Ras Gha |  | Zafranaa - Ras Ghareb | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 250 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Residence 8 ( S05 ) | Cr . Inv ( 1 ) S 05 | 1 | Residence 8 ( S05 )1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR - 11 USD- Shabab | 11 | Al-Shabab PP Phase II (CP-117)11 | 0 | 0 | 0 | #DIV/0!
Ain-Sokhna PP(CP-102) | 2104220006 |  | Ain-Sokhna PP(CP-102) | 0 | 0 | 0 | #DIV/0!
Sultana Malak Restoration | Sultana mlk22 2final |  | Sultana Malak Restoration | 5285834.29 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR Akhmem Asuit3T |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | DEC ADJ 66 |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2009220004 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
PIP Zona 2 | Cr Adj inv 1 | 1 | PIP Zona 21 | 0 | 0 | 0 | #DIV/0!
LP-22-21 ECMEI–6000–RFID | 55 |  | LP-22-21 ECMEI–6000–RFID | 33180 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,4 usd Borg Ar | 4 | Marsa Matrouh 500KV4 | 0 | 0 | 0 | #DIV/0!
U7-SEASHELL | CANCEL IPC12 | 12 | U7-SEASHELL12 | 0 | 0 | 0 | #DIV/0!
PLAYA ROOF & Wet Areas | Credut Memo IPC00015 | 15 | PLAYA ROOF & Wet Areas15 | 0 | 0 | 0 | #DIV/0!
EPICO 3 Facility | CR Material ipc3 | 3 | EPICO 3 Facility3 | 0 | 0 | 0 | #DIV/0!
Al-Wukair 11 Substation | Cr.Memo-Expenses. |  | Al-Wukair 11 Substation | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 9 |  | Zafranaa - Beni Suef | 79487.99 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | Inv.6&7 Deductions | 6 | Assuit PP (CP-118)6 | 0 | 0 | 0 | #DIV/0!
Ain Sokhna Port Development | IPC no25 | 25 | Ain Sokhna Port Development25 | 214074 | 0 | 0 | #DIV/0!
Luxor North Axis Bridge-Off | cr ipc 5 luxoroff | 5 | Luxor North Axis Bridge-Off5 | -672192 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 255 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Beni-Suef Power Plant EPC | Adj.180178 |  | Beni-Suef Power Plant EPC | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | ENG/040 C |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 67 |  | FX-01-22 Decent Life-WD | 1794527.17 | 0 | 0 | #DIV/0!
Ain Sokhna Bridge | Cr. Inv ( 5 ) A.S | 5 | Ain Sokhna Bridge5 | 0 | 0 | 0 | #DIV/0!
Celia | D0020-OB-Dec-2020/Cr | 2020 | Celia2020 | 0 | 0 | 0 | #DIV/0!
New Heliopolis | cancel inv 8 | 8 | New Heliopolis8 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | Cr adj inv12 | 12 | Abo Quir - Badr 500KV12 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | SH inv.39 deductions | 39 | South Helwan PP (CP-117)39 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | Cr.Cr. Soc Inv. 48 | 48 | Akhmem Assiut48 | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2008220002 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Giza North PP Ph I,II (CP-117) | Cr-36 EGP-Giza I&II | 36 | Giza North PP Ph I,II (CP-117)36 | 0 | 0 | 0 | #DIV/0!
Museum of Egyp. Civilization | CR-IPC#3 | 3 | Museum of Egyp. Civilization3 | 0 | 0 | 0 | #DIV/0!
El Katameya Mall | CR inv ( 13 ) | 13 | El Katameya Mall13 | 0 | 0 | 0 | #DIV/0!
Abo Quir - Badr 500KV | de. transfer to EGP. |  | Abo Quir - Badr 500KV | 0 | 0 | 0 | #DIV/0!
Elhegaz | D0028-OB-Dec-202/Cr | 202 | Elhegaz202 | 0 | 0 | 0 | #DIV/0!
Ahl Misr P3 – Zamalek Sector | CR-IPC#5&6 | 5 | Ahl Misr P3 – Zamalek Sector5 | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | adjust |  | South Helwan PP (CP-117) | -108901.12 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | rev.( 8 EGP-West D.) |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 180063 rev. |  | South Helwan PP (CP-117) | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | Inv-01 MOC | 1 | MOC HQ at Diriyah1 | 9771187.56 | 0 | 0 | 13219842
Haramein Columns Transfer | Haramin ipc01 | 1 | Haramein Columns Transfer1 | 5354496 | 0 | 0 | 5354496
Hosh Eisa Hospit. | IPC01TR0089 | 1 | Hosh Eisa Hospit.1 | 364500 | 0 | 0 | 364500
ORA ZED-Ph 2-Pkgs A&D | Ora Ph1 ipc (22) | 22 | ORA ZED-Ph 2-Pkgs A&D22 | 10796355.55 | 0 | 0 | 11336173.3275
SOL Town PKG.220 | PKG#220- IPC2 | 2 | SOL Town PKG.2202 | 23621739.09 | 0 | 0 | 26928782.5626
Get Business Complex | INV ( 6 ) GET | 6 | Get Business Complex6 | 1164549.6 | 0 | 0 | 1164549.6
El Katameya Mall | INV ( 14 ) 28-10-20 | 14 | El Katameya Mall14 | 169232 | 0 | 0 | 169232
Sixty Iconic Tower | inv ( 1) sixty | 1 | Sixty Iconic Tower1 | 1454355 | 0 | 0 | 1454355
Playa Resort | 41- مردودات بنكية |  | Playa Resort | 218.5 | 0 | 0 | 218.5
October Under-Railway Tunnel | october tunnel ipc01 | 1 | October Under-Railway Tunnel1 | 802790.71 | 0 | 0 | 842930.2455
MDF Factory | MDF_ IPC 13 | 13 | MDF Factory13 | 15274426.88 | 0 | 0 | 15274426.88
LAYAN Substation | 11745 |  | LAYAN Substation | 3545.48 | 0 | 0 | 3545.48
Nuweibaa (Swro) | 220621003 |  | Nuweibaa (Swro) | 46666.67 | 0 | 0 | 46666.67
Luxor North Axis Bridge-Off | IPC#2-Luxoroffshor | 2 | Luxor North Axis Bridge-Off2 | 2759054.4 | 0 | 0 | 2759054.4
Racecores 3092-15 132KV A | 11449 |  | Racecores 3092-15 132KV A | 3551.62 | 0 | 0 | 3551.62
EGYTEC A1,A3 ( LP-05-21) | 50 |  | EGYTEC A1,A3 ( LP-05-21) | 572325 | 0 | 0 | 572325
EGYTEC A1,A3 ( LP-05-21) | 56 |  | EGYTEC A1,A3 ( LP-05-21) | 1716975 | 0 | 0 | 1716975
Kafr Shokr Bridge | Kafr Shokr - IPC01 | 1 | Kafr Shokr Bridge1 | 32770679.81 | 0 | 0 | 34409213.8005
Banha PP (CP-117) | 2012210037 |  | Banha PP (CP-117) | -129460.88 | 0 | 0 | -129460.88
Daraw Bridge | D0033-OB-Dec-2020 | 2020 | Daraw Bridge2020 | 3578560 | 0 | 0 | 3578560
Elmaragha Bridge - Sohag | D0015-OB-Dec-2020 | 2020 | Elmaragha Bridge - Sohag2020 | 1475650 | 0 | 0 | 1475650
Road El Farag Axis | D0006-OB-Dec-2020 | 2020 | Road El Farag Axis2020 | 344798 | 0 | 0 | 344798
10th of Ramadan Railway | D0046 OB-Dec-2020 | 2020 | 10th of Ramadan Railway2020 | 5014107 | 0 | 0 | 5014107
Roots -Kafr ElSheikh Bridge | D0009-OB-Dec-2020 | 2020 | Roots -Kafr ElSheikh Bridge2020 | 421141.5 | 0 | 0 | 421141.5
LRT | D0045-OB-Dec-2020 | 2020 | LRT2020 | 778080 | 0 | 0 | 778080
Lahoon 220/22/22 | Al Lahoon Sub Inv 01 | 1 | Lahoon 220/22/221 | 13414631.32 | 0 | 0 | 13414631.32
Taval Sarai 52 | IPC_3_Saray_Gama | 3 | Taval Sarai 523 | 158874.5 | 0 | 0 | 158874.5
Sodic East | IPC12_sodic_east | 12 | Sodic East12 | 2661271.6 | 0 | 0 | 2661271.6
Manshiet Nasser Substation | 497 |  | Manshiet Nasser Substation | 969125.29 | 83472.1 | 0 | 83472.1
Cameron EDC | 024/2020 |  | Cameron EDC | 69576437.45 | 0 | 0 | 69576437.45
Cameron EDC | 023/2020 |  | Cameron EDC | 66315041.94 | 0 | 0 | 66315041.94
Suez Gulf Substation | 1909210007 |  | Suez Gulf Substation | 10987.09 | 10987.09 | 0 | 10987.09
Suez Gulf Substation | 1909210005 |  | Suez Gulf Substation | 3333550 | 3333550 | 0 | 3333550
Suez Gulf Substation | 1909210003 |  | Suez Gulf Substation | 116186 | 116186 | 0 | 116186
AWEER POWER STATION 'H' Phase | 5001 |  | AWEER POWER STATION 'H' Phase | 117898343.39 | 353695030.17 | 0 | 117898343.39
Beni-Suef Power Plant EPC | 67 |  | Beni-Suef Power Plant EPC | 0.01 | 0.01 | 0 | 0.01
Beni Suef COMCAVI | 1907210007 |  | Beni Suef COMCAVI | 611368269.3372 | 611368269.3372 | 0 | 611368269.3372
Beni-Suef Power Plant EPC | 1904210014 |  | Beni-Suef Power Plant EPC | 16897401.78 | 16897401.78 | 0 | 16897401.78
Beni-Suef Power Plant EPC | 180178 |  | Beni-Suef Power Plant EPC | 427482390.92 | 427482390.92 | 0 | 427482390.92
Cameroon EAR | P-09-13 AccRev | 9 | Cameroon EAR9 | 287923.24 | 0 | 0 | 287923.24
K047 FDH JV | p-10-16 ADJ | 10 | K047 FDH JV10 | 5651248 | 0 | 0 | 5651248
W Dam PP Phase II (CP-117) | DM for wrong credit |  | W Dam PP Phase II (CP-117) | 113117.95 | 0 | 0 | 113117.95
W Dam PP Phase II (CP-117) | 17 EGP-West Domiat |  | W Dam PP Phase II (CP-117) | 6435.43 | 6435.43 | 0 | 6435.43
Port Said | Adj.Inv. 17 | 17 | Port Said17 | 23601397.56 | 0 | 0 | 23601397.56
PIP- Zonafranca | Adj Inv 5 | 5 | PIP- Zonafranca5 | 56503324.28 | 0 | 0 | 56503324.28
Beni-Suef Power Plant EPC | 180070 |  | Beni-Suef Power Plant EPC | 96760325.43 | 0 | 0 | 96760325.43
Beni-Suef Power Plant EPC | 180118 |  | Beni-Suef Power Plant EPC | 487337915.43 | 487337915.43 | 0 | 487337915.43
Apache Electrical Works | 113 |  | Apache Electrical Works | -62239131.5949 | 0 | 0 | -62239131.5949
Abu Qir PP (CP-118) | 96 |  | Abu Qir PP (CP-118) | -282927272.3471 | 0 | 0 | -282927272.3471
Abu Qir PP (CP-118) | 28 |  | Abu Qir PP (CP-118) | 3115665.5712 | 0 | 0 | 3115665.5712
Abu Qir PP (CP-118) | 27 |  | Abu Qir PP (CP-118) | 55291.82 | 0 | 0 | 55291.82
IRAQ - Substations Soil Invest | 117 |  | IRAQ - Substations Soil Invest | -4177500 | 0 | 0 | -4177500
Lina Farm Substation | 100 |  | Lina Farm Substation | -4252794.1107 | 0 | 0 | -4252794.1107
Beni-Suef PP Site Preparation | 2 |  | Beni-Suef PP Site Preparation | 237544015.6515 | 0 | 0 | 237544015.6515
IRAQ - Al-Diwaniya Power Plant | 79 |  | IRAQ - Al-Diwaniya Power Plant | 583608125.3815 | 0 | 0 | 583608125.3815
IRAQ - Al-Diwaniya Power Plant | 78 |  | IRAQ - Al-Diwaniya Power Plant | -507140001 | 0 | 0 | -507140001
Ain-Sokhna PP (CP-117) | 69 |  | Ain-Sokhna PP (CP-117) | 18001724 | 0 | 0 | 18001724
Cairo South PP Rehabilitation | 10 USD - Cairo South |  | Cairo South PP Rehabilitation | 27162.77 | 27162.77 | 0 | 27162.77
Akhmem - Qena | Inv. 6 Akhmem Qena | 6 | Akhmem - Qena6 | 18108403.21 | 0 | 0 | 18108403.21
Siemens 6x500/220 KV GIS-MOU | ٍSoc 72 Asuit 10 |  | Siemens 6x500/220 KV GIS-MOU | 115457.3 | 0 | 0 | 115457.3
South Helwan PP (CP-117) | adj. 180010 & 180013 |  | South Helwan PP (CP-117) | 338325.46 | 338325.46 | 0 | 338325.46
Pyramids Industrial Park | Inv.5 PIP West | 5 | Pyramids Industrial Park5 | 3985862.7 | 0 | 0 | 3746710.95
New Capital | Inv 1 El Tbeen | 1 | New Capital1 | 17707402.209 | 0 | 0 | 17707402.209
New Capital | Inv 2 Abo Zaabl | 2 | New Capital2 | 21843369.1 | 0 | 0 | 21843369.1
Banha PP (CP-118) | 1 USD - Banha 118 |  | Banha PP (CP-118) | 159437.19 | 0 | 0 | 159437.19
Kuwait | 30-132KVA-J | 132 | Kuwait132 | 559622.7 | 363754.75 | 0 | 363754.75
IRAQ - Substations Soil Invest | 7 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
IRAQ - Substations Soil Invest | 8 USD - Hitachi |  | IRAQ - Substations Soil Invest | 62500 | 62500 | 0 | 62500
New Capital | new acpita tbeen 1 |  | New Capital | 17707402.5 | 12208229.095 | 1859277.26 | 14067506.355
Siemens 6x500/220 KV GIS-MOU | Social 37 Bnha 6 |  | Siemens 6x500/220 KV GIS-MOU | 47216.96 | 47216.96 | 0 | 47216.96
Ismailiya East Substation | ISE-CW-EURO-01 | 1 | Ismailiya East Substation1 | 1513092.67 | 1044033.94 | 226963.9 | 1270997.84
Tamey El-amdeed Substation | TAM-CW-EGP-10 | 10 | Tamey El-amdeed Substation10 | 4385067.75 | 3244950.23 | 657760.16 | 3902710.39
Al Mostathmreen GIS Substation | (13)cw mostsmrin |  | Al Mostathmreen GIS Substation | 2554107.7 | 1902810.23 | 383116.16 | 2285926.39
Beni Suef ISKRA | 180115 |  | Beni Suef ISKRA | 59610.29 | 50668.75 | 8941.54 | 59610.29
Beni Suef COMCAVI | 180003 |  | Beni Suef COMCAVI | 396995.6 | 0 | 397030.9 | 198515.45
Beni Suef ISKRA | inv no(2 Euro-Iskrae | 2 | Beni Suef ISKRA2 | 13771766.91 | 13771766.91 | 0 | 13771766.91
Beni Seuf - 358 | Banha-Zagazg Inv.01 | 1 | Beni Seuf - 3581 | 24118240.19 | 0 | 4163750.7 | 4163750.7
Abu Qir PP (CP-117) | 49 Euro Abo Qir 117 |  | Abu Qir PP (CP-117) | 223059.5333 | 185384.04 | 0 | 185384.04
Banha PP (CP-118) | Collection |  | Banha PP (CP-118) | 162591.7 | 162591.7 | 0 | 162591.7
Apache Electrical Works | Apachi Inv No PC.#24 |  | Apache Electrical Works | 30425.9 | 30425.9 | 0 | 30425.9
Apache Electrical Works | Apachi Inv No PC.#22 |  | Apache Electrical Works | 50046.57 | 50046.57 | 0 | 50046.57
kayan wall lock & Load | مستخلص 2 كيان ردم 2 | 2 | kayan wall lock & Load2 | 2493680 | 1050255 | 1050264.4 | 2100519.4
South Helwan PP (CP-117) | 4 EUR South Helwan |  | South Helwan PP (CP-117) | 450359.14 | 450359.14 | 0 | 450359.14
Ghana | 33/P/10/ER/2017/USD |  | Ghana | 740200.21 | 740185.71 | 0 | 740185.71
Siemens 6x500/220 KV GIS-MOU | Ret.Itay sub |  | Siemens 6x500/220 KV GIS-MOU | 3682736.56 | 3682736.56 | 0 | 3682736.56
KSA - Rabegh PMS | INV PMS S.A |  | KSA - Rabegh PMS | 22502.2 | 22502.2 | 0 | 22502.2
Military 110 Kayan Project | Inv No3 ElKean 220 | 3 | Military 110 Kayan Project3 | 10659874.49 | 9673442.05 | 0 | 9673442.05
Cairo North PP Rehabilitation | 7 EGP - Cairo North |  | Cairo North PP Rehabilitation | 41928.07 | 41928.07 | 0 | 41928.07
Cairo South PP Rehabilitation | 8 USD - Cairo South |  | Cairo South PP Rehabilitation | 21238.01 | 21238.01 | 0 | 21238.01
Siemens 6x500/220 KV GIS-MOU | Ret. Kafr Elzayat |  | Siemens 6x500/220 KV GIS-MOU | 352432.62 | 352432.62 | 0 | 352432.62
El Mostakbal City Project | Inv. 12 Mostakbal | 12 | El Mostakbal City Project12 | 10382302.18 | 7745197.51 | 2180283.46 | 9925480.97
Military 110 Kayan Project | Inv.4 Elkayan | 4 | Military 110 Kayan Project4 | 7708606.29 | 6995162.45 | 0 | 6995162.45
Military 110 Kayan Project | Inv No 6 ElKean 220 | 6 | Military 110 Kayan Project6 | 12792300.22 | 11994040.85 | 0 | 11994040.85
South Helwan PP (CP-117) | Commercial fees SH- |  | South Helwan PP (CP-117) | 152890.19 | 152890.19 | 0 | 152890.19
Ain-Sokhna PP (CP-111) | Ret... Balance... |  | Ain-Sokhna PP (CP-111) | 1446650.57 | 1446650.57 | 0 | 1446650.57
Akhmem Assiut | Soc 3 Asuit |  | Akhmem Assiut | 240662.91 | 240662.91 | 0 | 240662.91
Siemens 6x500/220 KV GIS-MOU | Soc 11 east asuit |  | Siemens 6x500/220 KV GIS-MOU | 47673.85 | 47673.82 | 0 | 47673.82
SHAT Al ARAB 400/132kV SS | 202 |  | SHAT Al ARAB 400/132kV SS | 4240533.36 | 0 | 0 | 0
EMAAR-PKG#62-UPTOWN | PKG#62- IPC 14 | 14 | EMAAR-PKG#62-UPTOWN14 | 3683223.04 | 815558.87 | 0 | 815558.87
Abou El Matameer and Sammanoud | Social 10 matamer 89 |  | Abou El Matameer and Sammanoud | 58636.3 | 58636.29 | 0 | 58636.29
Marsa Matrouh 500KV | Inv.6 Borg Alarab | 6 | Marsa Matrouh 500KV6 | 87830687.53 | 87830687.53 | 0 | 87830687.53
Akhmem - Qena | Soci.$11-16:23Qena | 16 | Akhmem - Qena16 | 3541868.1 | 3541868.1 | 0 | 3541868.1
Kayan 3 New Cairo Capital City | Kayan MEP- ipc 4 | 4 | Kayan 3 New Cairo Capital City4 | 58955037 | 53206512.5 | 0 | 53206512.5
DPW Onshore Port & Terminal | DP WORLD-IPC09 | 9 | DPW Onshore Port & Terminal9 | 54097551.55 | 40031882.73 | 8114632.73 | 48146515.46
DPW Onshore Port & Terminal | DP World IPC032 | 32 | DPW Onshore Port & Terminal32 | 16694467.33 | 12304801.83 | 2504170.1 | 14808971.93
Closed | (3)Sobra-banha |  | Closed | 159125 | 220385.54 | 0 | 220385.54
Manshiet Nasser Substation | 503 |  | Manshiet Nasser Substation | 4028410.81 | 2391144.23 | 604261.62 | 2995405.85
Manshiet Nasser Substation | 502 |  | Manshiet Nasser Substation | 119663 | 0 | 17949.45 | 17949.45
Manshiet Nasser Substation | 490 |  | Manshiet Nasser Substation | 39228.15 | 0 | 5884.22 | 5884.22
EMAAR-PKG# 144, Marassi | PKG#144-IPC09 | 9 | EMAAR-PKG# 144, Marassi9 | 10299181.31 | 9830068.4255 | 458688.86 | 10288757.2855
4 SS - Technical Service | 220 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
El Boghaz Brigde | IPC#17 | 17 | El Boghaz Brigde17 | 436620.18 | 410422.97 | 0 | 410422.97
4 SS - Technical Service | 232 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 33 | 33 | Benban 500 K.V/95 K.M33 | 4275995.22 | 3254035.3 | 448979.5 | 3703014.8
Benban 500 K.V/95 K.M | Benban Lot 2 Inv. 10 | 10 | Benban 500 K.V/95 K.M10 | 296011.5 | 228227.96 | 31081.21 | 259309.17
Elco Steel 220/33 KV SS | 1904210002 |  | Elco Steel 220/33 KV SS | 426459.2 | 447782.16 | 0 | 447782.16
Elco Steel 220/33 KV SS | 1903210009 |  | Elco Steel 220/33 KV SS | 2989549.75 | 6278054.46 | 0 | 3139027.23
Akhmem Assiut | Social 48 Assuit |  | Akhmem Assiut | 2182603.5 | 2182603.5 | 0 | 2182603.5
Akhmem Assiut | Soc inv 1to49 Asuit | 1 | Akhmem Assiut1 | 1915923.61 | 1915923.61 | 0 | 1915923.61
Suez IPB | 1 USD - Suez Steel |  | Suez IPB | 1980 | 1980 | 0 | 1980
SHAT Al ARAB 400/132kV SS | 260 |  | SHAT Al ARAB 400/132kV SS | 372746.38 | 372746.38 | 0 | 372746.38
AWEER POWER STATION 'H' Phase | 10136 |  | AWEER POWER STATION 'H' Phase | 226423.5 | 237744.675 | 0 | 237744.675
MOTHANA 400/132kV SS | 272 |  | MOTHANA 400/132kV SS | 68410.54 | 68410.54 | 0 | 68410.54
33KV Canal Farm Grid | Inv. 04 Farm | 4 | 33KV Canal Farm Grid4 | 22354576.27 | 17660115.25 | 3353186.44 | 21013301.69
Alamein | ALALAMEN SUPPLY-01 | 1 | Alamein1 | 5635700 | 4067203 | 0 | 4067203
Beni Suef Add-on Sales | 1908210014 |  | Beni Suef Add-on Sales | 117000 | 132210 | 0 | 132210
Beni Suef Substation R61 | BSF- CLIAM-EGP-01 | 1 | Beni Suef Substation R611 | 10000000 | 9999405.8 | 0 | 9999405.8
Elco Steel 220/33 KV SS | 517 |  | Elco Steel 220/33 KV SS | 61491.53 | 64566.11 | 0 | 64566.11
Cairo Capital Cables Tunnel | Tunnel Inv. 4 | 4 | Cairo Capital Cables Tunnel4 | 14140637.9 | 9516649.2 | 3535159.48 | 13051808.68
EMAAR-PKG#107-MARASSI | PKG#107-IPC18 | 18 | EMAAR-PKG#107-MARASSI18 | 1069591.54 | 1054265.617 | 0 | 1054265.617
Elco Steel 220/33 KV SS | 1907210009 |  | Elco Steel 220/33 KV SS | 15950.22 | 16747.73 | 0 | 16747.73
Elco Steel 220/33 KV SS | 1901210004 |  | Elco Steel 220/33 KV SS | 241517.84 | 253593.73 | 0 | 253593.73
SHATRA 400/132kV SS | 293 |  | SHATRA 400/132kV SS | 522747.52 | 522747.52 | 0 | 522747.52
MOTHANA 400/132kV SS | 289 |  | MOTHANA 400/132kV SS | 715698.36 | 715698.36 | 0 | 715698.36
Safir bridge | IPC#2 | 2 | Safir bridge2 | 106500 | 0 | 0 | 67533.6
Beni Seuf - 358 | Soci. 4-5Banysof 358 | 5 | Beni Seuf - 3585 | 868383 | 868383 | 0 | 868383
SHAT Al ARAB 400/132kV SS | 327 |  | SHAT Al ARAB 400/132kV SS | 429 | 429 | 0 | 429
MOTHANA 400/132kV SS | 292 |  | MOTHANA 400/132kV SS | 766712.41 | 766712.41 | 0 | 766712.41
LAYYAH CCPP | MP -09 | 9 | LAYYAH CCPP9 | 8569800 | 7284322.89 | 1285477.11 | 8569800
Zafranaa - Ras Ghareb | Abolila Zafra Instal |  | Zafranaa - Ras Ghareb | 799.68 | 799.68 | 0 | 799.68
Zafranaa - Ras Ghareb | Ref. Ghareeb |  | Zafranaa - Ras Ghareb | 0 | -173025.16 | 0 | -173025.16
Akhmem - Qena | Soc 49 Quana labour |  | Akhmem - Qena | 306247 | 305657.78 | 0 | 305657.78
CFC Podium 2 | CFC-IPC11 | 11 | CFC Podium 211 | 16864873.52 | 18030566.05 | 3463044.876 | 21493610.926
Toshka GIS 500 kV | Toshka Sub Inv. 17 $ | 17 | Toshka GIS 500 kV17 | 38060 | 21544.65 | 9990.75 | 31535.4
Phosfat | Inv.7 Phosfat | 7 | Phosfat7 | 375611.1 | 315903.65 | 0 | 315903.65
CFC Podium 2 | CFC IPC020 | 20 | CFC Podium 220 | 23105145.86 | 23721354.77 | 4488317.19 | 28209671.96
Multi Sport Hall | 10019 |  | Multi Sport Hall | 71955 | 64039.95 | 0 | 64039.95
AWEER POWER STATION 'H' Phase | ENG-023/Rev0 | 23 | AWEER POWER STATION 'H' Phase23 | 211328.6 | 221895.03 | 0 | 221895.03
Manshiet Nasser Substation | 2002210023 |  | Manshiet Nasser Substation | 4588.2 | 1675.05 | 0 | 1675.05
Sodic Wesset | 10022 |  | Sodic Wesset | 52649.24 | 48068.76 | 0 | 48068.76
4 SS - Technical Service | 343 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
SHAT Al ARAB 400/132kV SS | 322 |  | SHAT Al ARAB 400/132kV SS | 291176.33 | 291176.33 | 0 | 291176.33
MAYSAN 400/132kV SS | 308 |  | MAYSAN 400/132kV SS | 103659.09 | 103659.09 | 0 | 103659.09
SHAT Al ARAB 400/132kV SS | 326 |  | SHAT Al ARAB 400/132kV SS | 516459.01 | 516459.01 | 0 | 516459.01
Miscellaneous Projects | 2003210012 |  | Miscellaneous Projects | 140 | 155.4 | 0 | 155.4
4 SS - Technical Service | 349 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Miscellaneous Projects | 2004210001 |  | Miscellaneous Projects | 194088 | 219319.44 | 0 | 219319.44
4 SS - Technical Service | 354 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Abas El Akkad Bridge | IPC#1 | 1 | Abas El Akkad Bridge1 | 1023425 | 0 | 0 | 1013190.75
Al-Wukair 11 Substation | 2006210005 |  | Al-Wukair 11 Substation | 2521965.63 | 2521965.63 | 0 | 2521965.63
Miscellaneous Projects | 2007210006 |  | Miscellaneous Projects | 19570.71 | 21723.494 | 0 | 21723.494
AWEER POWER STATION 'H' Phase | Eng-029 Rev0 | 29 | AWEER POWER STATION 'H' Phase29 | 288828.17 | 303247.5785 | 0 | 303247.5785
AWEER POWER STATION 'H' Phase | Eng/030 |  | AWEER POWER STATION 'H' Phase | 135084.69 | 141767.11 | 0 | 141767.11
Beni Suef Add-on Sales | 1908210012 |  | Beni Suef Add-on Sales | 158042.56 | 175427.24 | 0 | 175427.24
NUCA R05 - Z02 | R05(2) IPC 47 | 47 | NUCA R05 - Z0247 | 22597861.91 | 20170545 | 2643691.59 | 22814236.59
Mahmoudia Additional Scope | 2003210005 |  | Mahmoudia Additional Scope | 625000 | 625000 | 0 | 625000
Zambia Project | SCD1/007 |  | Zambia Project | 82886.4 | 74597.76 | 0 | 74597.76
South Helwan PP (CP-117) | 2009210009 |  | South Helwan PP (CP-117) | 348942.6 | 363451.65 | 0 | 363451.65
AWEER POWER STATION 'H' Phase | ENG-031 | 31 | AWEER POWER STATION 'H' Phase31 | 539333.84 | 566300.532 | 0 | 566300.532
Racecores 3092-17 132KV E | 11290 |  | Racecores 3092-17 132KV E | 148481.03 | 123239.24 | 0 | 123239.24
ORA ZED - Ph 01B - Pkgs A&D | Ora ph1 ipc 35 | 35 | ORA ZED - Ph 01B - Pkgs A&D35 | 9206608.75 | 7391485.26 | 966693.92 | 8358179.18
EMAAR-PKG#62-UPTOWN | Pkg 162- IPC 19 | 19 | EMAAR-PKG#62-UPTOWN19 | 1831902.3 | 1275390.455 | 0 | 1275390.455
MOTHANA 400/132kV SS | 378 |  | MOTHANA 400/132kV SS | 40000 | 40000 | 0 | 40000
4 SS - Technical Service | 387 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Latin Compound - New Alamin | inv ( 26 )23-12-2020 | 26 | Latin Compound - New Alamin26 | 357456.4 | 303745.85 | 0 | 303745.85
Abu Quir Timmay Alamdid 500KV | Abo-Qair-Temay Inv.1 | 1 | Abu Quir Timmay Alamdid 500KV1 | 2740005.3 | 2110682.6 | 0 | 2110682.6
Canal Sugar 33KV OHTL | Inv. 5 Sugar 33 OHTL | 5 | Canal Sugar 33KV OHTL5 | 1053666.22 | 961997.25 | 0 | 961997.25
Lahoon 220/22/22 | Al-Lahoon Sub Inv 05 | 5 | Lahoon 220/22/225 | 106376100.95 | 0 | 26594025.24 | 26594025.24
Fish Market | FISH MARKER-MEP+1FIN |  | Fish Market | 201317.62 | 201317.62 | 0 | 201317.62
Mahmoudia Additional Scope | 2005210007 |  | Mahmoudia Additional Scope | 8250000 | 8250000 | 0 | 8250000
Mansoura University | IPC#01 - Mansoura | 1 | Mansoura University1 | 1548130.5 | 1000000 | 0 | 1503741.64
Toshka-04 GIS Substation | Toshka Sub 4 Inv.2 $ | 2 | Toshka-04 GIS Substation2 | 794984.46 | 0 | 39749.22 | 39749.22
4 SS - Technical Service | 398 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
West Port Said 220 kV GIS | P-45-Portsaid Inv.02 | 2 | West Port Said 220 kV GIS2 | 15693269.47 | 12570305.27 | 1647793.29 | 14218098.56
Shorouk Bridge-LRT | SHROUK BDRIDG-IPC03 | 3 | Shorouk Bridge-LRT3 | 7701312.1 | 6500000 | 0 | 6500000
Group # 1 - 25 LX | Reailway PSP Inv. 03 | 3 | Group # 1 - 25 LX3 | 840000 | 831600 | 0 | 831600
R5 | inv ( 14 ) | 14 | R514 | 1467000 | 1320105.5 | 0 | 1320105.5
Ghana Street lighting | MIDA Ins. Inv.6 | 6 | Ghana Street lighting6 | 110082.95 | 99074.65 | 0 | 99074.65
Akhmem - Qena | Ref.Ret Quana akh |  | Akhmem - Qena | 9060111.33 | 0 | 0 | 0
Mauritania Lot 1 | Inv.17 - Lot 1 | 17 | Mauritania Lot 117 | 265232.96 | 251956.56 | 0 | 251956.56
4 SS - Technical Service | 411 |  | 4 SS - Technical Service | 98778.12 | 98778.12 | 0 | 98778.12
Akhmem Assiut | Ref.Ret Asuit akh 1 |  | Akhmem Assiut | 10000000 | 10000000 | 0 | 10000000
SHAT Al ARAB 400/132kV SS | 416 |  | SHAT Al ARAB 400/132kV SS | 891552.99 | 891552.99 | 0 | 891552.99
ElMoneeb 2 | IPC#04 Moneeb Bridge | 4 | ElMoneeb 24 | 312855 | 309726.45 | 0 | 309726.45
Waldorf Astoria Cairo | WALDORF ASTORIA IPC2 | 2 | Waldorf Astoria Cairo2 | 3507480.42 | 2448867.881 | 955903.96 | 3404771.841
Zafranaa - Beni Suef | Ret Zafra-B-Suef T |  | Zafranaa - Beni Suef | 1114579.04 | 1114579.04 | 0 | 1114579.04
Racecores 3092-17 132KV E | 10965 |  | Racecores 3092-17 132KV E | 45479.7 | 45479.7 | 0 | 45479.7
Racecores 3092-16 132KV C | 10963 |  | Racecores 3092-16 132KV C | 47958.05 | 47958.05 | 0 | 47958.05
Benban 500 K.V/95 K.M | Ref.2 benban Lot 2 T |  | Benban 500 K.V/95 K.M | 10000000 | 10000000 | 0 | 10000000
BKG#178-Lagoon Discharge | pkg#178 ipc07 | 7 | BKG#178-Lagoon Discharge7 | 686559 | 1680446.34 | 0 | 1680446.34
Akhmem - Qena | Ret Qen-akh 9 T |  | Akhmem - Qena | 3599122.18 | 3450778.99 | 0 | 3450778.99
Akhmem - Qena | ref,ret,Qena - Akhme |  | Akhmem - Qena | 5000000 | 5000000 | 0 | 5000000
RING ROAD MARYOTIA EXPANSION | elmarg ipc09 | 9 | RING ROAD MARYOTIA EXPANSION9 | 4536217.14 | 4020500.727 | 0 | 4020500.727
TZ – Offshore E&M Procurement | 454 |  | TZ – Offshore E&M Procurement | 455556.64 | 0 | 68333.5 | 68333.5
Ring Road Bridges Project | inv ( 5 ) 12-12-2021 | 5 | Ring Road Bridges Project5 | 2202635.7 | 1846142.42 | 0 | 1846142.42
Kemet Tower | inv ( 1 ) 9-12-2021 | 1 | Kemet Tower1 | 132480 | 113681.09 | 0 | 113681.09
AWEER POWER STATION 'H' Phase | ENG/050 |  | AWEER POWER STATION 'H' Phase | 52620.22 | 55251.231 | 0 | 55251.231
Taval Sarai 52 | IPC-17-SARAY | 17 | Taval Sarai 5217 | 53244 | 45230.78 | 0 | 45230.78
TZ – Offshore E&M Procurement | 445 |  | TZ – Offshore E&M Procurement | 193636.12 | 193636.12 | 0 | 193636.12
Racecores 3092-16 132KV C | 11285 |  | Racecores 3092-16 132KV C | 7273.18 | 7273.18 | 0 | 7273.18
MAYSAN 400/132kV SS | 432 |  | MAYSAN 400/132kV SS | 2968 | 2968 | 0 | 2968
MOTHANA 400/132kV SS | 438 |  | MOTHANA 400/132kV SS | 4928 | 4928 | 0 | 4928
MRINACMN KSWG & FRDH Circuit | 11322 |  | MRINACMN KSWG & FRDH Circuit | 19207.5 | 19207.5 | 0 | 19207.5
AWEER POWER STATION 'H' Phase | Eng/052 |  | AWEER POWER STATION 'H' Phase | 421109.11 | 442164.5655 | 0 | 442164.5655
LAYAN Substation | 11445 |  | LAYAN Substation | 276190.4762 | 290000 | 0 | 290000
New Giza Hospital | IPC-1-New Giza | 1 | New Giza Hospital1 | 412689.21 | 354128.62 | 0 | 354128.62
LAYAN Substation | 11461 |  | LAYAN Substation | 10249.95 | 10249.95 | 0 | 10249.95
Suez Gulf/S4 - 500KV OHTL | Suez S4 Inv. 18 | 18 | Suez Gulf/S4 - 500KV OHTL18 | 12894915.94 | 11811722 | 0 | 11811722
Racecores 3092-17 132KV E | 11500 |  | Racecores 3092-17 132KV E | 3816.96 | 3816.96 | 0 | 3816.96
Solar ITS | ITS Solar Inv. 01 | 1 | Solar ITS1 | 14119547.5 | 11039280 | 0 | 11039280
TEst | 001 |  | TEst | 44143.76 | 149647.3392 | 0 | 49882.4464
National Batteries LP-05-20 | 81 |  | National Batteries LP-05-20 | 578947.37 | 213315.34 | 0 | 213315.34
TZ – Offshore E&M Procurement | 465 |  | TZ – Offshore E&M Procurement | 167285.32 | 167285.32 | 0 | 167285.32
Kafr Shokr Bridge | kafr shokr IPC07 | 7 | Kafr Shokr Bridge7 | 30363309.48 | 27070646.13 | 0 | 27070646.13
FURJAN Cable Works | 11587 |  | FURJAN Cable Works | 4868005.51 | 132896550.4233 | 0 | 5111405.7855
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 6 | 6 | Marsa Alam/ Bernes LOT2 OHTL6 | 2436089.29 | 2196846.98 | 0 | 2196846.98
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv11 | 11 | Marsa Alam/ Bernes LOT2 OHTL11 | 414591.11 | 373460.2 | 0 | 373460.2
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam EGP Inv 8 | 8 | Marsa Alam/ Bernes LOT2 OHTL8 | 209328.02 | 188310.4 | 0 | 188310.4
TNYA-WSHP | 11662 |  | TNYA-WSHP | 0 | -78027.6 | 0 | -78027.6
PO3092200025 | 11702 |  | PO3092200025 | 123220.12 | 123220.12 | 0 | 123220.12
EMAAR-Pkg#162/163- Marassi | PKG#177 IPC 33+34 | 33 | EMAAR-Pkg#162/163- Marassi33 | 4083110.28 | 3354959.084 | 0 | 3354959.084
Assuit PP (CP-118) | Invoice # 39 Assuit |  | Assuit PP (CP-118) | 820286.39 | 861300.7095 | 0 | 861300.7095
Benban 500 K.V/95 K.M | Ref-Ret-Benban-lot2 |  | Benban 500 K.V/95 K.M | 4000000 | 4000000 | 0 | 4000000
New Giza Hospital | IPC-3-NEW GIZA | 3 | New Giza Hospital3 | 64993.96 | 37962.83 | 0 | 37962.83
New Babil 400/132KV GIS Substa | 220721002 |  | New Babil 400/132KV GIS Substa | 888398.4 | 888398.4 | 0 | 888398.4
New Giza Hospital | IPC-4-NEW GIZA | 4 | New Giza Hospital4 | 46975 | 37529.21 | 0 | 37529.21
W Dam PP Phase II (CP-117) | 2 EGP- West Domiat |  | W Dam PP Phase II (CP-117) | 35142.34 | 35142.34 | 0 | 35142.34
Playa Epoxy | 03 |  | Playa Epoxy | 53171.2 | 45626.21 | 0 | 45626.21
Playa Resort | 37 |  | Playa Resort | 6763.71 | 6763.71 | 0 | 6763.71
EGAT Pelletizing Plant | Water tank IPC 11+ | 11 | EGAT Pelletizing Plant11 | 1966603.81 | 1946937.7705 | 0 | 1946937.7705
Playa Resort | kantine.4 -40 | 40 | Playa Resort40 | 35000 | 35000 | 0 | 35000
Get Business Complex | INV ( 19 ) GET | 19 | Get Business Complex19 | 105763.25 | 99417.46 | 0 | 99417.46
Air Defence College | IPC003 | 3 | Air Defence College3 | 412839.98 | 350501.14 | 0 | 350501.14
Creeks URBN-K | katameya urbnk ipc15 | 15 | Creeks URBN-K15 | 10771231.15 | 10206848 | 267101.62 | 10473949.62
Air Defence College | IPC00006 | 6 | Air Defence College6 | 69600 | 59090.4 | 0 | 59090.4
Olympic Multi – Sports Hall | Olympic IPC1 | 1 | Olympic Multi – Sports Hall1 | 2197625 | 1812330 | 0 | 1812330
Olympic Multi – Sports Hall | Oly fin IPC4 | 4 | Olympic Multi – Sports Hall4 | 4391058 | 3699060 | 0 | 3699060
EGAT Mechanical Installations | Egat piping ipc 3 | 3 | EGAT Mechanical Installations3 | 1042361.93 | 849902.8302 | 260590.48 | 1110493.3102
SSC Suez Steel Company Project | R.O sup pri adj.ipc2 | 2 | SSC Suez Steel Company Project2 | 1686530.02 | 918958.5973 | 0 | 918958.5973
U3 & U5 | IPC3-TR55 | 3 | U3 & U53 | 34000.72 | 28363.02 | 0 | 28363.02
Olympic Multi – Sports Hall | SPORT HALL IPC 07 | 7 | Olympic Multi – Sports Hall7 | 16168000 | 14222372.5 | 0 | 14222372.5
U3 & U5 | IPC004 TR55 | 4 | U3 & U54 | 186640.4 | 161182.65 | 0 | 161182.65
MDF Factory | Mdf Factory 3 ipc 12 | 12 | MDF Factory12 | 1715548.54 | 0 | 1732936.45 | 1732936.45
SEASHELL TECHNICAL ROOM | IPC05TR0065 | 5 | SEASHELL TECHNICAL ROOM5 | 381327.19 | 329314.16 | 0 | 329314.16
Air Defense College | Air Tahsen IPC Fin |  | Air Defense College | 4238538 | 3570560 | 0 | 3570560
PLAYA ROOF & Wet Areas | IPC0022 TR41 | 22 | PLAYA ROOF & Wet Areas22 | 127113.34 | 109075.77 | 0 | 109075.77
U3 & U5 | IPC06 TR0055 | 6 | U3 & U56 | 73568.7 | 63533.92 | 0 | 63533.92
EPICO 3 Facility | Eipico ipc (9) | 9 | EPICO 3 Facility9 | 35000000 | 34650000 | 0 | 34650000
Seashell Playa 5 Villas | playa-c045 ipc 4 | 4 | Seashell Playa 5 Villas4 | 59845.85 | 46508.62 | 0 | 46508.62
Seashell Playa 5 Villas | playa-c072 ipc (1) | 1 | Seashell Playa 5 Villas1 | 115275.25 | 83551.7 | 0 | 83551.7
Seashell Playa 5 Villas | Playa-c038 ipc(4) | 4 | Seashell Playa 5 Villas4 | 78107.46 | 67453.6 | 0 | 67453.6
Air Defense College | Air Dev Allom IPC2 | 2 | Air Defense College2 | 3044221 | 2564350 | 0 | 2564350
HST El Mahager Bridge | ipc 5 elmahager | 5 | HST El Mahager Bridge5 | 7551825 | 6691275.33 | 0 | 6691275.33
VILLA CLUSTRER B | IPC03TR0077 | 3 | VILLA CLUSTRER B3 | 74105 | 63997.08 | 0 | 63997.08
U7-SEASHELL | IPC08TR0064 | 8 | U7-SEASHELL8 | 546742.03 | 459198.66 | 0 | 459198.66
MDF Factory | Mdf Equip ipc 20 | 20 | MDF Factory20 | 640115.15 | 606416.12 | 0 | 606416.12
Air Defense College | Air Dev sihi IPC2 | 2 | Air Defense College2 | 1074100 | 904520 | 0 | 904520
Ain Sokhna Bridge | Inv ( 4 ) A.S | 4 | Ain Sokhna Bridge4 | 333124.3 | 273490.77 | 0 | 273490.77
ZED Phase 2 | IPC03TR0062 | 3 | ZED Phase 23 | 15613.821 | 13263.94 | 0 | 13263.94
EGAT Injection | IPC006 TR48 | 6 | EGAT Injection6 | 52237.38 | 44824.9 | 0 | 44824.9
seashell Playa | IPC28TR0038 | 28 | seashell Playa28 | 267610.19 | 229636.3 | 0 | 229636.3
Creeks URBN-K | ipc16 katamya urbnk | 16 | Creeks URBN-K16 | 6516046.61 | 6345313.6705 | 0 | 6345313.6705
October Dry Port Railway | ODP Dry port ipc 4 | 4 | October Dry Port Railway4 | 650753.99 | 4734676.94 | 0 | 4734676.94
South Dabaa Axis | ipc final..2 elwaraq |  | South Dabaa Axis | 891923.1 | 789798.79 | 0 | 789798.79
Seashell Playa 5 Villas | Playa-c045 ipc 7 | 7 | Seashell Playa 5 Villas7 | 119128.39 | 72006.28 | 0 | 72006.28
Air Defence College | IPC21TR0046 | 21 | Air Defence College21 | 515431.5 | 437601.33 | 0 | 437601.33
EGAT Injection | IPC07 | 7 | EGAT Injection7 | 28544.81 | 24494.3 | 0 | 24494.3
Creeks URBN-K | Urbn-k ipc 17 | 17 | Creeks URBN-K17 | 8554341.9 | 8554807.445 | 0 | 8554807.445
Katameya Creeks - RME | IPC16TR0053 | 16 | Katameya Creeks - RME16 | 156756.24 | 138807.66 | 0 | 138807.66
Kattmeya Creeks Urban | IPC06TR0071 | 6 | Kattmeya Creeks Urban6 | 153630.36 | 136039.68 | 0 | 136039.68
MDF Factory | mdf local ipc 16 | 16 | MDF Factory16 | 1249666.24 | 1262162.9036 | 0 | 1262162.9036
seashell Playa | IPC30TR0038 | 30 | seashell Playa30 | 6489.78 | 5568.88 | 0 | 5568.88
HST Bridges-Sokhna & Mahager | sokhna bri ipc 20 | 20 | HST Bridges-Sokhna & Mahager20 | 5229351.9 | 4655093.281 | 0 | 4655093.281
Ministries Buildings | Mini Long lead IPC5 | 5 | Ministries Buildings5 | 3048577 | 2568010 | 0 | 2568010
HST Bridges-Sokhna & Mahager | sokhna esc.16 |  | HST Bridges-Sokhna & Mahager | 29623249.9 | 26411692.75 | 0 | 26411692.75
Creeks URBN-K | Urbnk ipc 18 | 18 | Creeks URBN-K18 | 9384875.1 | 9363449.555 | 0 | 9363449.555
Rabigh PP - Piling Works | Inv-1 | 1 | Rabigh PP - Piling Works1 | 824244.82 | 2843644.65 | 0 | 947881.55
U7-SEASHELL | IPC19TR0064 | 19 | U7-SEASHELL19 | 109721.9 | 94755.82 | 0 | 94755.82
Rabigh PP - Piling Works | Remaning Inv-2 | 2 | Rabigh PP - Piling Works2 | 187165.29 | 215240.08 | 0 | 215240.08
Port Said Grain Storage | RENT-007 | 7 | Port Said Grain Storage7 | 131650 | 150081 | 0 | 150081
El Khatatba Bridge | KHATATBA IPC10+11+12 | 10 | El Khatatba Bridge10 | 9666748.9 | 7237461.1 | 0 | 7237461.1
ORA ZED - Ph 01B - Pkgs A&D | ORA PH1 IPC 40 | 40 | ORA ZED - Ph 01B - Pkgs A&D40 | 4495110.55 | 3717952.37 | 0 | 3717952.37
Sultana Malak Restoration | sultana malak Damage |  | Sultana Malak Restoration | 178949.52 | 176047.4 | 0 | 176047.4
U7-SEASHELL | IPC20TR0064 | 20 | U7-SEASHELL20 | 26097.3 | 22537.64 | 0 | 22537.64
Seashell Playa 5 Villas | playa - c469 ipc4 | 4 | Seashell Playa 5 Villas4 | 67230.66 | 61421.93 | 0 | 61421.93
EMAAR-PKG# 101-UPTOWN | Emaar pkg#101 ipc 24 | 24 | EMAAR-PKG# 101-UPTOWN24 | 270197.08 | 546994.614 | 0 | 546994.614
EGAT ADMIN (Pelletizing) | IPC01TR0094 | 1 | EGAT ADMIN (Pelletizing)1 | 310640 | 266560.18 | 0 | 266560.18
Rabigh CCPP-Civil | Inv-01 | 1 | Rabigh CCPP-Civil1 | 2313265.08 | 7980764.49 | 0 | 2660254.83
U3 & U5 | IPC22TR0055 | 22 | U3 & U522 | 242534.58 | 158302.85 | 0 | 158302.85
Abou Ghaleb Bridge | abo ghaleb esc.1:11 |  | Abou Ghaleb Bridge | 26616364.1 | 25711010.9 | 0 | 25711010.9
EDNC Mobilization Works | EDNC PO NO. (3349T) |  | EDNC Mobilization Works | 609204.24 | 633572.41 | 0 | 633572.41
RADAMIS CITY | IPC04TR0084 | 4 | RADAMIS CITY4 | 24234.05 | 21459.26 | 0 | 21459.26
RADAMIS CITY | IPC10TR0084 | 10 | RADAMIS CITY10 | 383921.2 | 272636.36 | 0 | 272636.36
Irrigation Tank | IPC12TR0061 | 12 | Irrigation Tank12 | 689048.85 | 499792.67 | 0 | 499792.67
Egyptian Exchange building | IPC16TR0039 | 16 | Egyptian Exchange building16 | 624770.85 | 553234.59 | 0 | 553234.59
Katameya Creeks - RME | IPC21(1)TR0053 | 21 | Katameya Creeks - RME21 | 529445.82 | 462161.77 | 0 | 462161.77
U7-SEASHELL | IPC24TR0064 | 24 | U7-SEASHELL24 | 83712.08 | 43465.65 | 0 | 43465.65
WADY EL-NATROUN BRIDGE(HST) | IPC#19 wady elnatron | 19 | WADY EL-NATROUN BRIDGE(HST)19 | 109940 | 34465.36 | 0 | 34465.36
U7-SEASHELL | IPC25TR0064 | 25 | U7-SEASHELL25 | 231425 | 0 | 0 | 0
Wady El Natroon Bridge | WADY ELNATROON IPC12 | 12 | Wady El Natroon Bridge12 | 13068802.86 | 11651747.9 | 0 | 11651747.9
Rabigh PP - Piling Works | K0004 Inv-07 | 7 | Rabigh PP - Piling Works7 | 2703528.67 | 9327173.91 | 0 | 3109057.97
Marsa Alam/ Bernes LOT2 OHTL | Marsa Alam USD Inv 4 | 4 | Marsa Alam/ Bernes LOT2 OHTL4 | 1199.73 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | DECADJ 81 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | CR-IPC 4 | 4 | WADY EL-NATROUN BRIDGE(HST)4 | -937184.64 | 0 | 0 | #DIV/0!
Koning Food V3 LP-09-20 | 16 |  | Koning Food V3 LP-09-20 | 0 | 0 | 0 | #DIV/0!
LINX Tower | CR-INV(1)LINX | 1 | LINX Tower1 | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | 30 Euro - Banha 117 |  | Banha PP (CP-117) | 41716.7333 | 0 | 0 | #DIV/0!
Al-Parco | INV ( 9 ) ALparco | 9 | Al-Parco9 | 4925521.5 | 0 | 0 | #DIV/0!
SOL Town PKG.220 | CR PKG#220- IPC 2 | 2 | SOL Town PKG.2202 | 0 | 0 | 0 | #DIV/0!
ElSewedy HQ Internal Finishing | CR-Elsewedy HQ-IPC24 | 24 | ElSewedy HQ Internal Finishing24 | 0 | 0 | 0 | #DIV/0!
East Port Said Industrial Area | FPC - Orascom HA |  | East Port Said Industrial Area | 50000 | 0 | 0 | #DIV/0!
Cameron EDC | 022/2020cncl |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Ahl Misr P3 – Zamalek Sector | CR-IPC#5 | 5 | Ahl Misr P3 – Zamalek Sector5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 247 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Kemet Tower | CR INV ( 9 ) KEMET | 9 | Kemet Tower9 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr-Sales tax USD inv |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Assuit PP (CP-118) | 2103220004 |  | Assuit PP (CP-118) | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | 5 Euro-South Helwan |  | South Helwan PP (CP-117) | 2519311.5619 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2103210013 |  | Miscellaneous Projects | 10500 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 88 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Wadi El Natroun Bridge | inv ( 3 ) W. Natron | 3 | Wadi El Natroun Bridge3 | 9507300 | 0 | 0 | #DIV/0!
Barwa 2x60/22 KV S/S | 28 |  | Barwa 2x60/22 KV S/S | 430464.18 | 0 | 0 | #DIV/0!
SHAT Al ARAB 400/132kV SS | 246 |  | SHAT Al ARAB 400/132kV SS | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 9 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 78700.1238 | 0 | 0 | #DIV/0!
Akhmem - Qena | close Adj Inv 10 | 10 | Akhmem - Qena10 | 0 | 0 | 0 | #DIV/0!
Amal Bridge Lock & Load | cr(1) ALAMAL BRIDGE |  | Amal Bridge Lock & Load | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | CR MOC Inv-01 | 1 | MOC HQ at Diriyah1 | 0 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | IPC#4 - Maragha Brid | 4 | Elmaragha Bridge - Sohag4 | 219822.5 | 0 | 0 | #DIV/0!
Almaza Bridge - Safir 2 | D0023-OB-Dec-2020/Cr | 2020 | Almaza Bridge - Safir 22020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 10 USD - Shabab |  | Al-Shabab PP Phase II (CP-117) | 1159738.7714 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | LOC/014CR |  | AWEER POWER STATION 'H' Phase | 0 | 0 | 0 | #DIV/0!
ORA ZED-Ph 2-Pkgs A&D | Cr-ORA PH.2-ipc13 | 13 | ORA ZED-Ph 2-Pkgs A&D13 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR_INV.13 | 13 | Akhmem - Qena13 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 18 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 412796.7524 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 20 EGP - Shabab |  | Al-Shabab PP Phase II (CP-117) | 43165.1619 | 0 | 0 | #DIV/0!
Ministries Buildings | Ministiry MEP ipc09 | 9 | Ministries Buildings9 | 68533369.3 | 0 | 0 | #DIV/0!
ElMoneeb 2 | D0041-OB-Dec-2020/Cr | 2020 | ElMoneeb 22020 | 0 | 0 | 0 | #DIV/0!
MOC HQ at Diriyah | Inv-001 MOC | 1 | MOC HQ at Diriyah1 | 11546312.44 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2012220003 |  | Miscellaneous Projects | 0 | 0 | 0 | #DIV/0!
Mauritania Lot 1 | Adj on inv.1 lot 1 | 1 | Mauritania Lot 11 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_INV.7 | 7 | Akhmem Assiut7 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 241 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Water pumping New Obour City | DR.Pump Obour Inv.6 | 6 | Water pumping New Obour City6 | 159283.13 | 0 | 0 | #DIV/0!
Sixty Iconic Tower | Cr inv ( 1 ) sixty | 1 | Sixty Iconic Tower1 | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR.Ret Asuit akh 5 |  | Akhmem Assiut | 0 | 0 | 0 | #DIV/0!
Abo Ghaleb | IPC#2#Abo Ghaleb cr | 2 | Abo Ghaleb2 | 0 | 0 | 0 | #DIV/0!
Elmaragha Bridge - Sohag | D0015-OB-Dec-20/Cr | 20 | Elmaragha Bridge - Sohag20 | 0 | 0 | 0 | #DIV/0!
FX-01-22 Decent Life-WD | 66 |  | FX-01-22 Decent Life-WD | 1083168.5 | 0 | 0 | #DIV/0!
Infra Project 4428 | 220322002 |  | Infra Project 4428 | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | IMP-61 | 61 | AWEER POWER STATION 'H' Phase61 | 0 | 0 | 0 | #DIV/0!
Containment Data Center- | 35 |  | Containment Data Center- | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 64 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
LRT Project | Cancel IPC_1_GRowad | 1 | LRT Project1 | 0 | 0 | 0 | #DIV/0!
Miscellaneous Projects | 2105210018 |  | Miscellaneous Projects | -10500 | 0 | 0 | #DIV/0!
TZ – Offshore E&M Procurement | 476 |  | TZ – Offshore E&M Procurement | 3240000 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | DEC ADJ 87 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Akhmem Assiut | CR_inv. 8 | 8 | Akhmem Assiut8 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 2004220006 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
AWEER POWER STATION 'H' Phase | 10367 |  | AWEER POWER STATION 'H' Phase | 2129497.75 | 0 | 0 | #DIV/0!
Beni Seuf - 358 | Cr. Inv. 1 Temmay | 1 | Beni Seuf - 3581 | 0 | 0 | 0 | #DIV/0!
Angola Emergency fast-track | Inv. No. 3 -Int.part | 3 | Angola Emergency fast-track3 | 946963.18 | 0 | 0 | #DIV/0!
Benban 3/ Toshka 2 LOT 4 | Cr.Tos Lot6 Inv.4 | 4 | Benban 3/ Toshka 2 LOT 44 | 0 | 0 | 0 | #DIV/0!
Development of Mahmudiyah axis | D0012-OB-Dec-2020/Cr | 2020 | Development of Mahmudiyah axis2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 243 |  | Al-Shabab PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
Latin Quarter- New Alamein | Cr 4-2021 | 2021 | Latin Quarter- New Alamein2021 | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,6 usd Borg Ar | 6 | Marsa Matrouh 500KV6 | 0 | 0 | 0 | #DIV/0!
ORA-ZED Towers01B | CR.TR0029DEC.Closing |  | ORA-ZED Towers01B | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 265 |  | W Dam PP Phase II (CP-117) | 0 | 0 | 0 | #DIV/0!
WADY EL-NATROUN BRIDGE(HST) | inv no 15.2 d0073 | 15 | WADY EL-NATROUN BRIDGE(HST)15 | 57555 | 0 | 0 | #DIV/0!
Ministries Building ROOF | CR.TR0010CLOSING.DEC |  | Ministries Building ROOF | 0 | 0 | 0 | #DIV/0!
Al-Parco | cr inv ( 3 ) | 3 | Al-Parco3 | 0 | 0 | 0 | #DIV/0!
Port Saad Industiral zone | D0022-OB-Dec-2020/Cr | 2020 | Port Saad Industiral zone2020 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 42 |  | Al-Shabab PP Phase II (CP-117) | 6496326.93 | 0 | 0 | #DIV/0!
Sodic East Town(EDNC) | IPC01TR0090 | 1 | Sodic East Town(EDNC)1 | 328820.4 | 0 | 0 | #DIV/0!
Damac 2x60/22 KV S/S | CR.ADJ.inv.20 | 20 | Damac 2x60/22 KV S/S20 | 0 | 0 | 0 | #DIV/0!
New Heliopolis | cancel inv. 9 | 9 | New Heliopolis9 | 0 | 0 | 0 | #DIV/0!
Cameron EDC | 023/2020cncl |  | Cameron EDC | 0 | 0 | 0 | #DIV/0!
Open Channal | CANCELLED |  | Open Channal | 0 | 0 | 0 | #DIV/0!
WPS Substations 1&2 | P-10-EGY اتحاد تشيد | 10 | WPS Substations 1&210 | 5000 | 0 | 0 | #DIV/0!
Racecores 3092-17 132KV E | 11522 |  | Racecores 3092-17 132KV E | 0 | 0 | 0 | #DIV/0!
FURJAN Cable Works | 11584 |  | FURJAN Cable Works | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 10 EGP- Suez Gulf |  | Suez Gulf Substation | 431640.3238 | 0 | 0 | #DIV/0!
Beni Suef Add-on Sales | 2005220004 |  | Beni Suef Add-on Sales | 0 | 0 | 0 | #DIV/0!
Banha PP (CP-117) | 31 EUR - Banha 117 ) |  | Banha PP (CP-117) | 10450.4762 | 0 | 0 | #DIV/0!
Phosfat | Cr Inv.6 Phosfat | 6 | Phosfat6 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 10 USD - West Domiat |  | W Dam PP Phase II (CP-117) | 2928987.5048 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | Retention OB |  | Zafranaa - Ras Ghareb | 10024979.95 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 56 |  | Suez Gulf Substation | 4828633.4664 | 0 | 0 | #DIV/0!
New Capital | CrAdj Inv. 21 | 21 | New Capital21 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | Cr- 5 + 7 USD-Shabab | 5 | Al-Shabab PP Phase II (CP-117)5 | 0 | 0 | 0 | #DIV/0!
Cairo-Alex Railway | CR cairo alex ipc41 | 41 | Cairo-Alex Railway41 | 0 | 0 | 0 | #DIV/0!
ZED Phase 2 | IPC10TR0062 | 10 | ZED Phase 210 | 60814.55 | 0 | 0 | #DIV/0!
Street Lighting Fayoum | CR.Fayoum Inv.01 | 1 | Street Lighting Fayoum1 | 0 | 0 | 0 | #DIV/0!
Residence 8 ( k12 ) | CrINV( 1 ) R08 - K12 | 1 | Residence 8 ( k12 )1 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Ras Ghareb | 3 |  | Zafranaa - Ras Ghareb | 118994.99 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | CR-16 EGP- West D. | 16 | W Dam PP Phase II (CP-117)16 | 0 | 0 | 0 | #DIV/0!
Akhmem - Qena | CR.Ret Qen-akh |  | Akhmem - Qena | 0 | 0 | 0 | #DIV/0!
South Helwan PP (CP-117) | Inv13 SH EUR | 13 | South Helwan PP (CP-117)13 | 167451.4286 | 0 | 0 | #DIV/0!
Giza North PP Phase3(CP-117) | CR-40 EGP-Giza N.III | 40 | Giza North PP Phase3(CP-117)40 | 0 | 0 | 0 | #DIV/0!
Zafranaa - Beni Suef | 7 |  | Zafranaa - Beni Suef | 26717.69 | 0 | 0 | #DIV/0!
HST - 6 October - Arab Cont. | CR IPC#1 HSR | 1 | HST - 6 October - Arab Cont.1 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | CR- 5 USD - Shabab | 5 | Al-Shabab PP Phase II (CP-117)5 | 0 | 0 | 0 | #DIV/0!
10Th of Ramadan LRT | P-37-EGY اتحاد تشيد | 37 | 10Th of Ramadan LRT37 | 5000 | 0 | 0 | #DIV/0!
Hyper One Badr | INV ( 13 fin ) Hyper | 13 | Hyper One Badr13 | 187199.31 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180018 |  | Suez Gulf Substation | -354232.13 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 180016 |  | Suez Gulf Substation | 354232.13 | 0 | 0 | #DIV/0!
LAYAN Substation | 11748 |  | LAYAN Substation | 0 | 0 | 0 | #DIV/0!
Minis Building(Polyurethane) | CR.TR0020CLOSING.DEC |  | Minis Building(Polyurethane) | 0 | 0 | 0 | #DIV/0!
New Heliopolis | Cr Adj Inv 8 | 8 | New Heliopolis8 | 0 | 0 | 0 | #DIV/0!
W Dam PP Phase II (CP-117) | 20 EGP - West Domiat |  | W Dam PP Phase II (CP-117) | 466026.0571 | 0 | 0 | #DIV/0!
MDF Factory | CR-MDF FACTORY-IPC07 | 7 | MDF Factory7 | 0 | 0 | 0 | #DIV/0!
Suez Gulf Substation | 9 EGP- Suez Gulf |  | Suez Gulf Substation | 1870441.4095 | 0 | 0 | #DIV/0!
Suez Gulf Substation | DEC ADJ 50 |  | Suez Gulf Substation | 0 | 0 | 0 | #DIV/0!
Marsa Matrouh 500KV | Cr.Inv,5 usd Borg Ar | 5 | Marsa Matrouh 500KV5 | 0 | 0 | 0 | #DIV/0!
Al-Shabab PP Phase II (CP-117) | 180021 |  | Al-Shabab PP Phase II (CP-117) | -2176819.63 | 0 | 0 | #DIV/0!
DPW Onshore Port & Terminal | CR-DP WORLD-IPC06 | 6 | DPW Onshore Port & Terminal6 | 0 | 0 | 0 | #DIV/0!
Ameria | Credit FPC04 |  | Ameria | 0 | 0 | 0 | #DIV/0!
FX-02-22 Decent Life-UE | 100 |  | FX-02-22 Decent Life-UE | 1200671.97 | 0 | 0 | #DIV/0!
Capital One | inv ( 10 ) Captal Cr | 10 | Capital One10 | 0 | 0 | 0 | #DIV/0!
Cairo Monorail - 6th October | CR IPC#7 | 7 | Cairo Monorail - 6th October7 | 0 | 0 | 0 | #DIV/0!
Elniger | 5004 Credit |  | Elniger | 0 | 0 | 0 | #DIV/0!
Residence 8 ( k12 ) | INV ( 1 ) R08 - K12 | 1 | Residence 8 ( k12 )1 | 19407.18 | 0 | 0 | 19407.18
ACWA POWER & NOMAC HQ | Acwa Power ipc 1 | 1 | ACWA POWER & NOMAC HQ1 | 85714.29 | 0 | 0 | 90000.0045
Abo Shanab El Agamien | ABO SHANAB IPC 2 | 2 | Abo Shanab El Agamien2 | 1014478 | 0 | 0 | 1014478
Katameya Creeks - RME | IPC13TR53 | 13 | Katameya Creeks - RME13 | 36591.65 | 0 | 0 | 0
Koumassi Flyover | INV 1 | 1 | Koumassi Flyover1 | 464398 | 0 | 0 | 464398
Al-Parco | INV (3 ) | 3 | Al-Parco3 | 2422608 | 0 | 0 | 2422608
ORA ZED-Ph 2-Pkgs A&D | ora zed (2) ipc 16 | 16 | ORA ZED-Ph 2-Pkgs A&D16 | 12061901.86 | 0 | 0 | 12664996.953
Expansion of Ring Road NRCC | IPC 3 NRCC | 3 | Expansion of Ring Road NRCC3 | 169935 | 0 | 0 | 169935
FURJAN Cable Works | 11561 |  | FURJAN Cable Works | 60494.4 | 0 | 0 | 63519.12
Beni-Suef Power Plant EPC | Inv. 26 | 26 | Beni-Suef Power Plant EPC26 | 779.29 | 0 | 0 | 779.29
Wadi El Natroun | D0014-OB-Dec-2020 | 2020 | Wadi El Natroun2020 | 6130260 | 0 | 0 | 6130260
ElMoneeb 2 | D0041-OB-Dec-2020 | 2020 | ElMoneeb 22020 | 677700 | 0 | 0 | 677700
ITS | Adv. ITS Inv. 01 | 1 | ITS1 | 8999900 | 0 | 0 | 8999900
Koning Food V3 LP-09-20 | 13 |  | Koning Food V3 LP-09-20 | 99912.28 | 0 | 0 | 99912.28
Hadaek ElAharam | D0037-OB-Dec-2020 | 2020 | Hadaek ElAharam2020 | 1214680 | 0 | 0 | 1214680
Assuit PP (CP-118) | 2001210018 |  | Assuit PP (CP-118) | 419062.41 | 0 | 0 | 440015.53
Al-Shabab PP Phase II (CP-117) | 2001210010 |  | Al-Shabab PP Phase II (CP-117) | 696.0051 | 0 | 0 | 797.51
LAYYAH CCPP | 470 |  | LAYYAH CCPP | 12854700 | 0 | 0 | 12854700
AWEER POWER STATION 'H' Phase | 10170 |  | AWEER POWER STATION 'H' Phase | 34632651.97 | 0 | 0 | 36364284.5685
Beni-Suef Power Plant EPC | 1907210004 |  | Beni-Suef Power Plant EPC | 31670696.4 | 31670696.4 | 0 | 31670696.4
Beni-Suef Power Plant EPC | 180120 |  | Beni-Suef Power Plant EPC | 16392318.57 | 16392318.57 | 0 | 16392318.57
Abu Qir PP (CP-117) | 1902210011 |  | Abu Qir PP (CP-117) | 196748.76 | 196748.76 | 0 | 196748.76
Beni-Suef Power Plant EPC | In 9+10 Beni Suef |  | Beni-Suef Power Plant EPC | 234962660.6 | 234962660.6 | 0 | 234962660.6
Akhmem Assiut | Soc Inv 49 Asuit | 49 | Akhmem Assiut49 | 48705.75 | 0 | 0 | 48705.75
Akhmem Assiut | Soc Inv 44 To 47 Qun | 44 | Akhmem Assiut44 | 2259485.5 | 0 | 0 | 2259485.5
Abou El Matameer and Sammanoud | Adj. Inv. 15 | 15 | Abou El Matameer and Sammanoud15 | 2916027.28 | 0 | 0 | 5832054.56
Siemens 6x500/220 KV GIS-MOU | Adj. Inv. 22 | 22 | Siemens 6x500/220 KV GIS-MOU22 | 2916027.23 | 0 | 0 | 2916027.23
K047 FDH JV | p-10-16 ADJ 2 | 10 | K047 FDH JV10 | 182114.96 | 0 | 0 | 182114.96
Al-Shabab PP Phase II (CP-117) | DR-Sales tax USD inv |  | Al-Shabab PP Phase II (CP-117) | 71027.48 | 71027.48 | 0 | 71027.48
Al-Shabab PP Phase II (CP-117) | DM-CR-19 EGP- Shabab | 19 | Al-Shabab PP Phase II (CP-117)19 | 2580132 | 0 | 0 | 2709138.6
Al-Shabab PP Phase II (CP-117) | 15 EGP- Shabab |  | Al-Shabab PP Phase II (CP-117) | 130940.02 | 0 | 0 | 130940.02
Marsa Matrouh 500KV | Inv, 7 usd Borg Arab | 7 | Marsa Matrouh 500KV7 | 1105819.91 | 0 | 0 | 1105819.91
South Helwan PP (CP-117) | 180145 |  | South Helwan PP (CP-117) | 245790.16 | 0 | 0 | 245790.16
South Helwan PP (CP-117) | 180144 |  | South Helwan PP (CP-117) | 245790.16 | 0 | 0 | 245790.16
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 04 |  | Giza North PP Ph I,II (CP-117) | 695709.53 | 695709.53 | 0 | 695709.53
South Helwan PP (CP-117) | Commercial fees |  | South Helwan PP (CP-117) | 11551.94 | 11551.94 | 0 | 11551.94
Pyramids Industrial P - East | Adj Inv 4 | 4 | Pyramids Industrial P - East4 | 85372216.25 | 0 | 0 | 85372216.25
Akhmem Assiut | Soc.$4-8:19Assuit | 8 | Akhmem Assiut8 | 10725414 | 0 | 0 | 10725414
Abu Qir PP (CP-118) | 441 EGP-Abo qeir 118 |  | Abu Qir PP (CP-118) | 3204257 | 3204257 | 0 | 3204257
Apache Electrical Works | 112 |  | Apache Electrical Works | 65105214.1353 | 0 | 0 | 65105214.1353
Mahmoudia Power Plant | 120 |  | Mahmoudia Power Plant | 2268359476.0321 | 0 | 0 | 2268359476.0321
Abu Qir PP (CP-118) | 19 |  | Abu Qir PP (CP-118) | 317532447 | 0 | 0 | 317532447
IRAQ - Substations Soil Invest | 22 |  | IRAQ - Substations Soil Invest | 1957500 | 0 | 0 | 1957500
IRAQ - Substations Soil Invest | 38 |  | IRAQ - Substations Soil Invest | 555000 | 0 | 0 | 555000
Ain-Sokhna PP(CP-102) | 26 |  | Ain-Sokhna PP(CP-102) | 16867317 | 0 | 0 | 16867317
Lina Farm Substation | 99 |  | Lina Farm Substation | 3820219.5717 | 0 | 0 | 3820219.5717
Beni-Suef Power Plant EPC | 3 |  | Beni-Suef Power Plant EPC | 45492840.03 | 0 | 0 | 45492840.03
Abu Qir PP (CP-117) | 20 |  | Abu Qir PP (CP-117) | 50353425 | 0 | 0 | 50353425
Abu Qir PP (CP-117) | 93 |  | Abu Qir PP (CP-117) | -38338457.9583 | 0 | 0 | -38338457.9583
Abu Qir PP (CP-117) | 32 |  | Abu Qir PP (CP-117) | 1383755.4984 | 0 | 0 | 1383755.4984
Ain-Sokhna PP (CP-111) | 98 |  | Ain-Sokhna PP (CP-111) | 937757.98 | 0 | 0 | 937757.98
KSA - Rabegh PMS | 124 |  | KSA - Rabegh PMS | 1462768.8503 | 0 | 0 | 1462768.8503
Palm Hill-Infra Str(Elec.Work) | 10 |  | Palm Hill-Infra Str(Elec.Work) | 5669708 | 0 | 0 | 5669708
Giza North PP Ph I,II (CP-117) | DR - VAT- Egytech 02 |  | Giza North PP Ph I,II (CP-117) | 182670.58 | 182670.58 | 0 | 182670.58
Cairo South PP Rehabilitation | 5 USD - Cairo South |  | Cairo South PP Rehabilitation | 5565.27 | 5565.27 | 0 | 5565.27
Akhmem - Qena | Inv.13 Akhmem Qena | 13 | Akhmem - Qena13 | 23766468.95 | 0 | 0 | 23766468.95
Abu Qir PP (CP-118) | 452 Euro - Avice |  | Abu Qir PP (CP-118) | 42422.31 | 0 | 0 | 42422.31
Abu Qir PP (CP-118) | 451 USD - Avice |  | Abu Qir PP (CP-118) | 56897.28 | 0 | 0 | 56897.28
Abu Qir PP (CP-118) | 450 USD - Avice |  | Abu Qir PP (CP-118) | 350863.24 | 0 | 0 | 350863.24

## Sheet1
project name | operation
6TH October tunnel | 2
Abo Ghaleb Bridge | 2
AEON
Al Jazi | 1
Al Jazi - Center Zone | 1
Al Jazi - Center Zone-DP | 1
Al Jazi - Social Insurance | 1
Al Jazi-DP | 1
Alfa Lab | 1
Allegria-New Modifications | 1
Astoria - Sharm | 1
Astoria - Sharm-DP | 1
Astoria Hotel | 1
Astoria Hotel - DP | 1
Astoria Hotel - Final Retention | 1
Astoria Hotel - On Account | 1
Astoria Hotel - Social Insurrance | 1
Astoria Hotel - Spare Parts V.O 137 | 1
Astoria Hotel IPCs 15-20 | 1
Baraka Land Fence | 1
Benban - Aswan | 1
Benban - Aswan - DP | 1
Cement Plant | 1
Cement Plant -Last Claim | 1
CFC | 1
CFC - Final Retention | 1
CFC-DP | 1
Comoros - DP | 1
Comoros - Off Shore | 1
Comoros - On Shore | 1
Comoros - On Shore - On Account | 1
Creeks - URBN K | 1
Creeks - URBN K - DP | 1
Creeks - URBN K - On Account | 1
Damietta Port - Civil | 1
Damietta Port - Civil - DP | 1
Damietta Port - Infra - DP | 1
1
DP World Sokhna | 1
DP World Sokhna-AP | 1
DPW - Ph.02 | 1
DPW - Ph.02 - DP | 1
EGAT Pelletizing Plant | 1
EGAT Pelletizing Plant - Admin Building | 1
EGAT Pelletizing Plant - Supply | 1
EGAT Pelletizing Plant-Concrete Infra | 1
EGAT Pelletizing Plant-DP | 1
EGAT Pelletizing Plant-Escalation | 1
EGAT Pelletizing Plant-Mechanical Installation | 1
EGAT Pelletizing Plant-MEP | 1
EGAT Pelletizing Plant-MEP Coordination | 1
EGAT Pelletizing Plant-On account | 1
EGAT Pelletizing Plant-Water Tank | 1
EGAT-Asphalt | 1
EGAT-Asphalt - Retenion Release | 1
EGAT-EGAT ON Account | 1
EGAT-Fence | 1
EGAT-Fence - Retenion Release | 1
EGAT-HeliPad | 1
EGAT-Lock & Load | 1
EGAT-Lock & Load-AP | 1
EGAT-SZ | 1
EGAT-Warehouse | 1
EIPICO | 1
EIPICO-DP | 1
EIPICO-On Account | 1
El Sewedy Uni.-PKG.1 | 1
El Sewedy Uni.-PKG.1-DP1 | 1
El Sewedy Uni.-PKG.2 | 1
El Sewedy Uni.-PKG.2-DP2 | 1
El Sewedy Uni.-PKG.2-Social Insurrance | 1
El Sewedy Uni.-PKG.3 | 1
El Sewedy Uni.-PKG.3 - On Account | 1
El Sewedy Uni.-PKG.3-DP | 1
El Sewedy Uni.-PKG.3-Social Insurrance | 1
Elco Steel | 1
Elco Steel - ADMIN. | 1
Elco Steel - MEP | 1
Elco Steel - MEP - Social Insurance | 1
Elco Steel - Social Insurance | 1
Elco Steel EGAT-DP | 1
Elco Steel V.O | 1
Elco Steel V.O-DP | 1
Elco Steel V.O-Infra. Network | 1
El-Gouna | 1
El-Gouna - DP | 1
El-Gouna - Equip. Rental | 1
El-Gouna - Temp. Fence | 1
EUA-DP
Existing Intake Apply -SSC-Mech | 1
Existing Intake Supply -SSC-Mech | 1
FIEM | 1
FIEM - Retention | 1
FIEM-Site Offices Rental Payment Request | 1
H1 Solaymaneya-MEP | 1
H1 Solaymaneya-MEP-DP | 1
HQ - CFC | 1
HQ - CFC - DP | 1
HQ - CFC - Retention release | 1
HQ - CFC - Social Insurrance | 1
HyperOne | 1
HyperOne-DP | 1
HyperOne-Steel Supply | 1
HyperOne-VAT 1,2,3 | 1
IKEA | 1
IKEA-DP | 1
IKEA-Retention Release | 1
JICA | 1
JICA-Site Offices Rental Payment Request | 1
Kafr Shokr | 2
Kafr Shokr - Retention Release | 2
Katameya - Creeks | 1
Katameya - Creeks - DP | 1
Katameya - Creeks - DP - Alu Glass | 1
Katameya - Creeks - On Account | 1
KFW | 1
KFW-Road Signals | 1
Khatatba Bridge | 2
KSA-Tarek AbdelHakim Center | 1
KSA-Tarek AbdelHakim Center - DP | 1
LEKELA | 1
LEKELA - Supply Bill | 1
LEKELA- On Account | 1
LEKELA Remedial | 1
LEKELA Remedial-DP | 1
LEKELA-DP | 1
MDF Factory | 1
MDF Factory - Equip. | 1
MDF Factory - Local Fabrication | 1
MDF Factory-DP | 1
MDF Factory-F.F V.O-on account | 1
MDF Factory-Hold Amount release | 1
MDF Factory-Local Fab.-on account | 1
MDF Factory-on account | 1
MDF Factory-on account solera | 1
MDF Factory-P.O-on account | 1
Mechanical Installation | 1
Mechanical Installation-DP | 1
Mintra | 1
Mintra-DP | 1
Mintra-Hanger 1200m2 | 1
Mivida-PK#140 | 1
Mivida-PK#140- Social Insurance | 1
Mivida-PK#140-DP | 1
Mivida-PK#189 | 1
Mivida-PK#189 - on account | 1
Mivida-PK#189 - Social insurance | 1
Mivida-PK#189-DP | 1
Mobilization
MOC | 1
MOC - DP | 1
New Gas Station | 1
New Giza Hospital | 1
New Giza Hospital-DP | 1
New Giza Hospital-On Account | 1
New Giza Hospital-Social Insurance | 1
NGU 2 | 1
NGU 2 - Retension release | 1
Old H1 remaining IPC
ORA - ZED | 1
ORA - ZED - Compansation | 1
ORA - ZED - Deficit | 1
ORA - ZED - DP | 1
ORA - ZED - On account | 1
ORA - ZED - Social Insurrance | 1
ORA - ZED - Landscape | 1
ORA - ZED - Landscape - Deficit | 1
ORA - ZED - Landscape - DP | 1
ORA - ZED - ph.02 | 1
ORA - ZED - ph.02 - Claims | 1
ORA - ZED - ph.02 - Deficit | 1
ORA - ZED - ph.02 - On Account | 1
PH.2-El Sewedy Uni. - Enabling | 1
PH.2-El Sewedy Uni. - Enabling - Retention release | 1
PH.2-El Sewedy Uni. - Finishes | 1
PH.2-El Sewedy Uni. - Finishes - on account | 1
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 1
PH.2-El Sewedy Uni.-DP | 1
PI Parks - ELSEWEDY | 1
PI Parks - MEP | 1
PI Parks - MEP-DP1 | 1
PI Parks - MEP-DP2 | 1
PK #107 | 1
PK #117 | 1
PK #117 - Social Insurance | 1
PK #22 - Social Insurance | 1
PK#22 | 1
PK#32 | 1
PKG#101 | 1
PKG#101- Social Insurance | 1
PKG#101-DP | 1
PKG#101-VO1&VO2 AP | 1
PKG#144 | 1
PKG#144 - Social Insurance | 1
PKG#144-DP | 1
PKG#162 | 1
PKG#162- Social Insurance | 1
PKG#162-DP | 1
PKG#163 | 1
PKG#163- Social Insurance | 1
PKG#163-DP | 1
PKG#177 | 1
PKG#177 - DP | 1
PKG#177 - on account | 1
PKG#177 - SWI 07 | 1
PKG#177- Social Insurance | 1
PKG#178 | 1
PKG#178 - DP | 1
PKG#178- Social Insurance | 1
PKG#205 | 1
PKG#205 - DP | 1
PKG#205-Social Insurance | 1
PKG#220B | 1
PKG#220B - DP | 1
PKG#45 | 1
PKG#58 | 1
PKG#85 | 1
PO#11687 | 1
Port Said Silos | 1
Port Said Silos - Foreigner Supply | 1
Port Said Silos - Local Supply | 1
Port Said Silos-DP | 1
Port Said Silos-On account | 1
Port Said Silos-Social Insurrance | 1
PSP Substation | 1
PSP Substation - Beni Suef | 1
PSP Substation - DP | 1
PSP Substation-Retention | 1
Rabigh Ext. - Piles | 1
Rabigh Ext. - Piles- DP | 1
Rabigh Ext. -Building | 1
Rabigh Ext. -Building- DP | 1
Radamis-Concrete | 1
Radamis-Concrete-DP | 1
Radamis-H1 Main Builidng | 1
Radamis-H1-On Account | 1
Radamis-Rooms Fitout | 1
Radamis-Rooms Fitout-DP | 1
Radamis-Villas Finishes | 1
Red Sea Museum | 1
Red Sea Museum - DP | 1
Ring Road - El Marg | 2
Ring Road - El Marg - Retention Release | 2
Ring Road - Mounib | 2
Ring Road - Mounib - refund | 2
Ring Road - Mounib - Social Insurance | 2
RO Apply -Mech- SSC | 1
RO Eriction | 1
RO Pump Room | 1
RO - Supply - Electric | 1
RO Supply -Mech- SSC | 1
RO 2 | 1
RO Pump room - SSC - price diff. | 1
RO.2 | 1
Rolling Mill #4-TRAESUEZ | 1
Rolling Mill #4-TRAESUEZ -AP | 1
Royal City | 1
Royal City - Landscape | 1
Royal City-DP 3 | 1
Royal City-DP 4 | 1
Royal City-DP1 | 1
Royal City-DP2 | 1
Saint Gobain Factory - DP | 1
SIEMENS - Sokhna | 1
SIEMENS - Sokhna - Bill | 1
SMP1 - Revamp | 1
SMP1 - Revamp - DP | 1
SMP1 - Shut Down | 1
SMP1 - Shut Down- Final Retention | 1
SMP2 - Shut Down | 1
SMP2 - Shut Down- Retention release | 1
SMP2 - Shut Down- V.O | 1
Sodic Club House | 1
Sodic Club House - Social Insurance | 1
Sodic Eastown | 1
Sodic Eastown - Landscape | 1
Sodic Eastown - On Account | 1
Sodic Eastown - Social Insurance | 1
Sodic Eastown-DP | 1
Sokhna Port Expansion | 1
Sokhna Port Expansion- 100m | 1
Sokhna Port Expansion 100m- Escalation | 1
Sokhna Port Expansion- EDECS | 1
Sokhna Port Expansion- Escalation | 1
Sokhna Port Expansion-AP | 1
Sokhna Port Expansion-internal roads | 1
Sports Hall - Civil Works | 2
Sports Hall - Finishes | 2
Sports Hall - Finishes - ADD.01 | 2
Sports Hall - Finishes - ADD.01 - Final Retention | 2
Sports Hall - Finishes - Landscape | 2
Sports Hall - Finishes - Landscape - Final Retention | 2
Sports Hall - Finishes - Social Insurance | 2
Sports Hall - MEP | 2
Sports Hall - MEP - DP | 2
Sports Hall - MEP - Final Retention | 2
Suez Intake & P Stations-ABB apply | 1
Suez Intake & P Stations-ABB supply | 1
Suez Intake & P Stations-ABB-Escalation | 1
Suez Intake & P Stations-SSC apply | 1
Suez Intake & P Stations-SSC supply | 1
Suez Steel Intake & P Stations-DP | 1
Suez Steel-Al Baraka-DP | 1
Suez Steel-Gas Station-DP | 1
SVC | 1
SVC-DP | 1
Uptown PK #53 | 1
Uptown PK #62 | 1
Uptown PK #62 - Retention | 1
Wady Halfa | 1
Wady Halfa - DP | 1
Wady Halfa - Escalation Claim | 1
Wady Halfa - Stoppage Period | 1
Western Fence | 1
Western Fence-PO | 1
Zayed Park