## Index
|  |  |  | Report No.#: | 1
CLIENT.: | DP WORLD |  |  | DATE: | 2018-12-09
CONSULTANT.: | PACER |  |  | REV: | 0
MAIN CONTRACTOR | ROWAD MODERN ENGINEERING |  |  | Project Start Date | 2018-11-12
PROJECT NAME: | DPW SOKHNA PORT |  |  | Project Completion Date | 2020-05-10
PROJECT NO.: |  |  |  | Days Elapsed | 27
CONTRACT NO.: |  |  |  | Duration % Complete | 4.954%
Contents
|  |  | 1- | ENVIROMENTAL, HEALTH AND SAFETY
|  |  | 2- | DAILY INDIRECT/DIRECT RECORD
|  |  | 3- | DAILY EQUIPMENT RECORD
|  | Project Photo | 4- | DAILY SITE ACTIVITIES AND AREA OF CONCERN
|  |  | 5- | DAILY SITE PROGRESS PHOTOS

## Staff
DAILY INDIRECT/DIRECT RECORD
Report No.#:37
June 28-2018
Indirect Manpower
Job Title | Day Shift | Night Shift
Project Manger | 1 | 0
Project Control Manager | 1 | 0
Cost Engineer | 0 | 0 | site | 1
Planning Engineer | 1 | 0 | eng | 1
Technical Office Manager | 1 | 0 | surv | 3
Technical Office Engineer | 0 | 0 | carponter | 5
Site Manager | 0 | 0 | to manager | 1
Construction Engineer | 0 | 0 | pm | 1
Civil Supervisor | 1 | 0
Finishing Supervisor | 0 | 0
Surveying Engineer | 0 | 0
Surveyors | 0 | 0
QC/QA Engineers | 0 | 0
HSE Superintendent | 0 | 0
HSE Officer | 0 | 0
Store Keeper | 0 | 0
Document Controller | 0 | 0
Admin | 0 | 0
Sub Total | 5 | 0
Total Indirect Manpower | 5
Direct Manpower
Job Title | Day Shift | Night Shift
Labor | 0 | 0
Casting Labor | 0 | 0
Carpenters | 4 | 0
Steel Fixer | 0 | 0
Blacksmith forman | 0 | 0
Welder | 0 | 0
Electrician | 0 | 0
Sccaffolder | 0 | 0
Masonry | 0 | 0
Rigger | 0 | 0
Plaster | 0 | 0
Sub Total | 4 | 0
Total Direct Manpower | 4
Grand Total (Direct + Indirect) | 9

## Equipment
DAILY EQUIPMENT RECORD
Report No.#:37
| Equipment | Day Shift | Night Shift
| Excvator | 0 | 0
| Loader | 0 | 0
| Trucks | 0 | 0
| Compactor | 0 | 0
| Roller Compactor | 0 | 0
| JCP | 0 | 0
| Bobcat | 0 | 0
| Helicoptar | 0 | 0
| Vibrator | 0 | 0
| Forklift | 0 | 0
| Mobile Crane | 0 | 0
| Concrete Pump | 0 | 0
| Welding Machine | 0 | 0
| Equipment Total | 0

## Daily Activity Description
DAILY SITE ACTIVITIES AND AREA OF CONCERN
Package No./Name:____________
Activity ID | AREA | Actual Date |  | Activity Description | %Progress |  |  | Area of Concern
|  | Start | Finish |  | % Previous | % Current | % Total
Mobilization
|  |  |  | Site Enabling | 100% | 100% | 100%
|  |  |  | Site Clearance | 0% | 0% | 0%
|  |  |  | Installation of Site offices and their Facilities | 0% | 0% | 0%

## Photos
DAILY SITE PROGRESS PHOTOS