## Sheet1
SITE_DEDUCTION | DEBIT_MEMO | OTHER_DEDUCTION | DEDUCTION_RETURN | MATERIAL_ON_SITE | SC_NO | DEDUCTION_NAME | WITHOLDING_TAX_AMNT | LABOUR_OFFICE_AMNT | SOCIAL_INSURANCE_AMNT | LABOUR_OFFICE | BID_RETENTION_AMNT | PERFORM_RETENTION_AMNT | TAX | PO_DISTRIBUTION_ID | TAX_RATE | PO_HEADER_ID | REVISION_NUM | SC_MANUAL | SUPPLIER_NAME | SUPP_CODE | VENDOR_SITE_CODE | PROJECT_NAME | AUTHORIZATION_STATUS | TOTAL_SC | CURRENCY_CODE | CREATION_DATE | BUYER_NAME | LINE_NUM | ITEM_DESCRIPTION | CATEGORY_ID | PRICE | NEED_BY_DATE | PAYMENT_TYPE | DESCRIPTION | QUANTITY | PRICE_OVERRIDE | AMOUNT | AMOUNT_OLD | PROJECT | TASK | EXPENDITURE_TYPE | EXPENDITURE_ITEM_DATE | EXPENDITURE_ORGANIZATION | PROGRESS | INVOICE_AMT_INT | QUANTITY_RECEIVED | CUMULATIVE_QTY | INVOICE_AMT | VENDOR_NUM | LAST_WC | PAY_ITEM_UOM | WRK_PKG | BILLED_AMOUNT | NET_AMOUNT | WC_AMNT | AREA
0 | 0 | 0 | 0 | 0 | 10315 | [8 empty] | 357874 |  | 175510 | 0 | 1019-SC-022 | Magdy Muhtadi Hafez | 149 | PSP | Suez Gulf Substation | APPROVED | 220500 | EGP | 2018-10-30 | Mohamed Abdel Hafiz Abdel Rehim, Mr. | 1 | per square meter deliver and cast asphalt layers for new main road (EL Sheikh Fadl road) | 6183 | 220500 |  | RATE | per square meter deliver and cast asphalt layers for new main road (EL Sheikh Fadl road) | 490 | 450 | 220500 | 220500 | Suez Gulf Substation | 21.02.02 | SUB-Civil Works | 2018-11-04 |  | 100 |  | 490 |  | 220500 | 149 | 2018-11-15 | Square Meter | Others | 220500 | 220500 | 220500
0 | 0 | 0 | 0 | 0 | 7066 | [8 empty] | 315136 |  | 153836 | 2 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation | APPROVED | 23752245.4 | EGP | 2018-02-12 | Amr Mahmoud Tawfik El Aisawy, Mr. | 5 | Civil Works | 6183 | 953607 |  | LUMPSUM | Civil Works |  |  | 953607 | 0 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-06-13 |  | 100 |  | 953607 |  | 953607 | 176 | 2018-12-20 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 81 | [8 empty] | 56241 |  | 67025 | 0 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation | APPROVED | 13232155.16 | EGP | 2016-10-09 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Civil Works | 6183 | 11004910.64 |  | LUMPSUM | Civil Works |  |  | 11004910.64 | 0 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2016-10-09 |  | 100 |  | 11004910.64 |  | 11004910.64 | 176 | 2017-05-04 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 7066 | [8 empty] | 251285 |  | 153836 | 2 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation | APPROVED | 23752245.4 | EGP | 2018-02-12 | Amr Mahmoud Tawfik El Aisawy, Mr. | 2 | Remesure items | 6183 | 2227244.52 |  | LUMPSUM | Civil Works |  |  | 2227244.52 | 0 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2016-10-09 |  | 0 |  | 0 |  | 0 | 176 | 2018-12-20 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 7066 | [8 empty] | 251283 |  | 153836 | 2 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation | APPROVED | 23752245.4 | EGP | 2018-02-12 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Civil Works | 6183 | 11004910.64 |  | ADVANCE | Advance - Civil Works |  |  | 2750478.2 | 0 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2016-10-09 |  | 0 |  | 0 |  | 0 | 176 | 2018-12-20 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 81 | [8 empty] | 56242 |  | 67025 | 0 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation | APPROVED | 13232155.16 | EGP | 2016-10-09 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Civil Works | 6183 | 11004910.64 |  | ADVANCE | Advance - Civil Works |  |  | 2750478.2 | 0 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2016-10-09 |  | 0 |  | 0 |  | 0 | 176 | 2017-05-04 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 7066 | [8 empty] | 263729 |  | 153836 | 2 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation | APPROVED | 23752245.4 | EGP | 2018-02-12 | Amr Mahmoud Tawfik El Aisawy, Mr. | 4 | civil works | 6183 | 8286209.79 |  | LUMPSUM | Civil Works |  |  | 8286209.79 | 0 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2016-10-09 |  | 100 |  | 8286209.79 |  | 8286209.79 | 176 | 2018-12-20 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 7065 | [8 empty] | 251280 |  | 153835 | 0 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation |  | 13232155.16 | EGP | 2018-02-12 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Civil Works | 6183 | 11004910.64 |  | ADVANCE | Advance - Civil Works |  |  | 2750478.2 | 0 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2016-10-09 |  | 0 |  | 0 |  | 0 | 176 |  |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 7066 | [8 empty] | 251284 |  | 153836 | 2 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation | APPROVED | 23752245.4 | EGP | 2018-02-12 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Civil Works | 6183 | 11004910.64 |  | LUMPSUM | Civil Works |  |  | 11004910.64 | 0 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2016-10-09 |  | 0 |  | 0 |  | 0 | 176 | 2018-12-20 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 7065 | [8 empty] | 251281 |  | 153835 | 0 | 1019Sc001 | المدار للمشروعات الهندسية والتوريدات العمومية | 176 | PSP | Suez Gulf Substation |  | 13232155.16 | EGP | 2018-02-12 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Civil Works | 6183 | 11004910.64 |  | LUMPSUM | Civil Works |  |  | 11004910.64 | 0 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2016-10-09 |  | 0 |  | 0 |  | 0 | 176 |  |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 3214 | [8 empty] | 192219 |  | 139469 | 1 | 1019/SC/015 | CASCO | 189 | PSP | Suez Gulf Substation | APPROVED | 129600 | EGP | 2017-06-13 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | H.V Cable Termination | 6185 | 129600 | 2017-04-22 | RATE | H.V Cable TerminationTermination Type TF1 .245-11 | 3 | 20700 | 62100 | 62100 | Suez Gulf Substation | 2.01.01 | SUB-Electrical Works | 2017-04-01 |  | 100 |  | 3 |  | 62100 | 189 | 2017-09-19 | Each | Construction Services | 62100 | 62100 | 62100
0 | 0 | 0 | 0 | 0 | 3214 | [8 empty] | 192220 |  | 139469 | 1 | 1019/SC/015 | CASCO | 189 | PSP | Suez Gulf Substation | APPROVED | 129600 | EGP | 2017-06-13 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | H.V Cable Termination | 6185 | 129600 | 2017-04-22 | RATE | Termination Type TE1.245-01 | 3 | 22500 | 67500 | 67500 | Suez Gulf Substation | 2.01.01 | SUB-Electrical Works | 2017-04-01 |  | 100 |  | 3 |  | 67500 | 189 | 2017-09-19 | Each | Construction Services | 67500 | 67500 | 67500
0 | 0 | 0 | 0 | 0 | 488 | [8 empty] | 128472 |  | 120425 | 1 | 1019/Sc/007 | Gulf Engneering Projects (Gepco) | 228 | PSP | Suez Gulf Substation | APPROVED | 2172575 | EGP | 2016-11-23 | Sarah Ali Youssef Abo Ashour, Ms. | 1 | ELECTRICAL WORKS | 6185 | 2000000 |  | LUMPSUM | Cable Laying and Termination |  |  | 2000000 | 0 | Suez Gulf Substation | 2.01.01 | SUB-Electrical Works | 2016-11-23 | Suez Gulf Substation | 94.98 |  | 1899500.59 |  | 1899500.59 | 228 | 2018-05-14 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 488 | [8 empty] | 283636 |  | 120425 | 1 | 1019/Sc/007 | Gulf Engneering Projects (Gepco) | 228 | PSP | Suez Gulf Substation | APPROVED | 2172575 | EGP | 2016-11-23 | Sarah Ali Youssef Abo Ashour, Ms. | 2 | ELECTRICAL WORKS | 6185 | 172575 |  | LUMPSUM | Cable Laying and Termination |  |  | 172575 | 0 | Suez Gulf Substation | 2.01.01 | SUB-Electrical Works | 2016-11-23 | Suez Gulf Substation | 100 |  | 172575 |  | 172575 | 228 | 2018-05-14 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 83 | [8 empty] | 221528 |  | 67028 | 1 | 1019Sc003 | المهندسون المتخصصون للاعمال الكهروميكانيكية ( امبى ) | 500 | PSP | Suez Gulf Substation | APPROVED | 6586831.37 | EGP | 2016-10-09 | Amr Mahmoud Tawfik El Aisawy, Mr. | 2 | Electromechanical Works | 6187 | 628850 |  | LUMPSUM | Electromechanical Works |  |  | 628850 | 0 | Suez Gulf Substation | 2.02.01 | SUB-MEP Works | 2016-10-09 |  | 100 |  | 628850 |  | 628850 | 500 | 2018-06-04 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 83 | [8 empty] | 57232 |  | 67028 | 1 | 1019Sc003 | المهندسون المتخصصون للاعمال الكهروميكانيكية ( امبى ) | 500 | PSP | Suez Gulf Substation | APPROVED | 6586831.37 | EGP | 2016-10-09 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Electromechanical Works | 6187 | 5957981.37 |  | ADVANCE | Advance - Electromechanical Works |  |  | 689022.7 | 0 | Suez Gulf Substation | 2.02.01 | SUB-MEP Works | 2016-10-09 |  | 0 |  | 0 |  | 0 | 500 | 2018-06-04 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 83 | [8 empty] | 57231 |  | 67028 | 1 | 1019Sc003 | المهندسون المتخصصون للاعمال الكهروميكانيكية ( امبى ) | 500 | PSP | Suez Gulf Substation | APPROVED | 6586831.37 | EGP | 2016-10-09 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Electromechanical Works | 6187 | 5957981.37 |  | LUMPSUM | Electromechanical Works |  |  | 5957981.37 | 0 | Suez Gulf Substation | 2.02.01 | SUB-MEP Works | 2016-10-09 |  | 100 |  | 5957981.37 |  | 5957981.27 | 500 | 2018-06-04 |  | Construction Services |  |  | 0
0 | 0 | 0 | 0 | 0 | 7283 | [8 empty] | 262080 |  | 154570 | 1 | 1008/SC/009 | مصر كونسلت جروب | 868 | PSP | Manshiet Nasser Substation | APPROVED | 95000 | EGP | 2018-02-25 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 3 | PILE TESTING SUPERVISION | 6183 | 77000 |  | RATE | Supervision and preparing the analysis report of Pile lateral destructive load test for CFA piles Dia 500 mm according to | 1 | 5000 | 5000 | 5000 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2018-03-19 |  | 100 |  | 1 |  | 5000 | 868 | 2018-08-02 | Each | Construction Services | 5000 | 5000 | 5000
0 | 0 | 0 | 0 | 0 | 7283 | [8 empty] | 262077 |  | 154570 | 1 | 1008/SC/009 | مصر كونسلت جروب | 868 | PSP | Manshiet Nasser Substation | APPROVED | 95000 | EGP | 2018-02-25 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 3 | PILE TESTING SUPERVISION | 6183 | 77000 |  | RATE | Supervision and preparing the analysis report of Piles compression destructive load test for CFA piles Dia 500 mm | 1 | 8000 | 8000 | 8000 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2018-03-19 |  | 100 |  | 1 |  | 8000 | 868 | 2018-08-02 | Each | Construction Services | 8000 | 8000 | 8000
0 | 0 | 0 | 0 | 0 | 7283 | [8 empty] | 262071 |  | 154570 | 1 | 1008/SC/009 | مصر كونسلت جروب | 868 | PSP | Manshiet Nasser Substation | APPROVED | 95000 | EGP | 2018-02-25 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 3 | PILE TESTING SUPERVISION | 6183 | 77000 |  | RATE | Supervision and preparing the analysis report of Piles compression destructive load test for CFA piles Dia 600 mm | 1 | 8000 | 8000 | 8000 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2018-03-19 |  | 100 |  | 1 |  | 8000 | 868 | 2018-08-02 | Each | Construction Services | 8000 | 8000 | 8000
0 | 0 | 0 | 0 | 0 | 7283 | [8 empty] | 262076 |  | 154570 | 1 | 1008/SC/009 | مصر كونسلت جروب | 868 | PSP | Manshiet Nasser Substation | APPROVED | 95000 | EGP | 2018-02-25 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 3 | PILE TESTING SUPERVISION | 6183 | 77000 |  | RATE | Supervision and preparing the analysis report of Pile lateral destructive load test for CFA piles Dia 600 mm according to | 1 | 8000 | 8000 | 8000 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2018-03-19 |  | 500 |  | 5 |  | 24000 | 868 | 2018-08-02 | Each | Construction Services | 40000 | 40000 | 40000
0 | 0 | 0 | 0 | 0 | 82 | [8 empty] | 56248 |  | 67027 | 0 | 1019Sc002 | Structure and geotechnical research center | 2024 | psp | Suez Gulf Substation | APPROVED | 56950 | EGP | 2016-10-09 | Amr Mahmoud Tawfik El Aisawy, Mr. | 1 | Civil and Arch Design Works | 16124 | 56950 |  | LUMPSUM | Civil and Arch Design Works |  |  | 56950 | 0 | Suez Gulf Substation | 5.03.02 | ENG-Outsource Engineering | 2016-10-09 |  | 0 |  | 0 |  | 0 | 2024 | [5 empty] | 0
0 | 0 | 0 | 0 | 0 | 9181 | [8 empty] | 331793 |  | 167799 | 0 |  | Power for Trading and Contracting | 2609 | psp | Suez Gulf Substation | APPROVED | 30191 | EGP | 2018-08-07 | Mohamed Abdel Hafiz Abdel Rehim, Mr. | 1 | Concrete Penetration 16 mm | 6183 | 22344 |  | RATE | Concrete Penetration 16 mm and 20 mm | 168 | 133 | 22344 | 22344 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2018-08-09 | Suez Gulf Substation | 100 |  | 168 |  | 22344 | 2609 | 2018-10-03 | Each | Others | 22344 | 22344 | 22344
0 | 0 | 0 | 0 | 0 | 9181 | [8 empty] | 331805 |  | 167799 | 0 |  | Power for Trading and Contracting | 2609 | psp | Suez Gulf Substation | APPROVED | 30191 | EGP | 2018-08-07 | Mohamed Abdel Hafiz Abdel Rehim, Mr. | 2 | Concrete Penetration 20 mm | 6183 | 7847 |  | RATE | Concrete Penetration 16 mm and 20 mm | 59 | 133 | 7847 | 7847 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2018-08-09 | Suez Gulf Substation | 100 |  | 59 |  | 7847 | 2609 | 2018-10-03 | Each | Others | 7847 | 7847 | 7847
0 | 0 | 0 | 0 | 0 | 5105 | [8 empty] | 254727 |  | 145137 | 4 | 1019sc017 | .توكسيدو | 2777 | psp | Suez Gulf Substation | APPROVED | 97500 | EGP | 2017-10-11 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | pest control company | 6165 | 45000 | 2017-09-21 | RATE | pest control company | 3 | 7500 | 22499.997 | 22499.997 | Suez Gulf Substation | 7.04.04 | ODC-Utilities Accommodation | 2018-01-02 |  | 99.99 |  | 2.9996 |  | 22497 | 2777 | 2019-09-12 | Monthly | Others | 22497 | 22497 | 22497
0 | 0 | 0 | 0 | 0 | 7191 | [8 empty] | 254700 |  | 154318 | 0 | 1019/SC/019 | .توكسيدو | 2777 | psp | Suez Gulf Substation |  | 44000 | EGP | 2018-02-20 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 3 | 1019/SC/019 | 6139 |  |  | MILESTONE | 1019/SC/019 | 6 | 4000 | 24000 | 24000 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2018-02-22 |  |  |  | 0 |  | 0 | 2777 |  | Monthly | Others | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5105 | [8 empty] | 318020 |  | 145137 | 4 | 1019sc017 | .توكسيدو | 2777 | psp | Suez Gulf Substation | APPROVED | 97500 | EGP | 2017-10-11 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 2 | renewal of pest control services | 6165 | 52500 |  | RATE | renewal of pest control services | 7 | 7500 | 52500 | 52500 | Suez Gulf Substation | 27.04.02 | ODC-Utilities Accommodation | 2018-07-10 |  | 101.3 |  | 7.0912 |  | 38868.2488 | 2777 | 2019-09-12 | Monthly | Others | 53184 | 53184 | 53184
0 | 0 | 0 | 0 | 0 | 7192 | [8 empty] | 254719 |  | 154321 | 0 | 1019/SC/019 | .توكسيدو | 2777 | psp | Suez Gulf Substation | APPROVED | 24000 | EGP | 2018-02-20 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | 1019/SC/019 | 6139 | 24000 |  | RATE | 1019/SC/019 | 6 | 4000 | 24000 | 24000 | Suez Gulf Substation | 7.07.01 | ODC-Safety Supplies | 2018-01-02 |  | 33.33 |  | 2 |  | 4000 | 2777 | 2018-02-20 | Monthly | Others | 8000 | 8000 | 8000
0 | 0 | 0 | 0 | 0 | 5933 | [8 empty] | 270230 |  | 148985 | 1 | 1019/SC/019 | .توكسيدو | 2777 | psp | Suez Gulf Substation | APPROVED | 24000 | EGP | 2017-12-10 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 5 | 1019/SC/019 | 6139 | 24000 |  | RATE | 1019/SC/019 | 6 | 4000 | 24000 | 24000 | Suez Gulf Substation | 7.04.01 | ODC-Utilities Accommodation | 2018-04-10 |  | 50 |  | 3 |  | 8000 | 2777 | 2018-04-19 | Monthly | Others | 12000 | 12000 | 12000
0 | 0 | 0 | 0 | 0 | 962 | [8 empty] | 208900 |  | 129866 | 2 | 1019/SC/008 | الفتح للمقاولات و التوريدات | 2774 | psp | Suez Gulf Substation | REQUIRES REAPPROVAL | 101460 | EGP | 2017-01-22 | Mohamed Osama Osman Ibrahim Mohamed Khashaba, Mr. | 2 | Installation and Erection of false ceiling at the control building | 6183 | 25460 |  | RATE | remeasure effect | 134 | 190 | 25460 | 25460 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2017-10-31 |  | 0 |  | 0 |  | 0 | 2774 | 2017-03-07 | Square Meter |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 962 | [8 empty] | 208897 |  | 129866 | 2 | 1019/SC/008 | الفتح للمقاولات و التوريدات | 2774 | psp | Suez Gulf Substation | REQUIRES REAPPROVAL | 101460 | EGP | 2017-01-22 | Mohamed Osama Osman Ibrahim Mohamed Khashaba, Mr. | 1 | Installation and Erection of false ceiling at the control building | 6183 | 76000 | 2016-10-03 | RATE | Installation and Erection of false ceiling at the control building | 400 | 190 | 76000 | 76000 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2017-10-31 |  | 0 |  | 0 |  | 0 | 2774 | 2017-03-07 | Square Meter |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 6382 | [8 empty] | 252796 |  | 150424 | 4 | 1019/SC/014 | GEO EGYPT | 3311 | psp | Suez Gulf Substation | APPROVED | 132000 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Laboratory for all the tests required for civil work with the required test equipment and manpower | 6183 | 22000 |  | RATE | Laboratory for all the tests required for civil work with the required test equipment and manpower | 2 | 11000 | 22000 | 22000 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-02-15 |  | 100 |  | 2 |  | 22000 | 3311 | 2018-08-06 | Monthly | Construction Services | 22000 | 22000 | 22000
0 | 0 | 0 | 0 | 0 | 6382 | [8 empty] | 326087 |  | 150424 | 4 | 1019/SC/014 | GEO EGYPT | 3311 | psp | Suez Gulf Substation | APPROVED | 132000 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 24 | Additional Works 1 | 6183 | 11000 |  | RATE | Additional Works 1 | 1 | 11000 | 11000 | 11000 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-07-29 | Suez Gulf Substation | 0 |  | 0 |  | 0 | 3311 | 2018-08-06 | Monthly | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 6382 | [8 empty] | 254214 |  | 150424 | 4 | 1019/SC/014 | GEO EGYPT | 3311 | psp | Suez Gulf Substation | APPROVED | 132000 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 22 | Additional Works | 6183 | 88000 |  | RATE | Additional Works | 8 | 11000 | 88000 | 88000 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-02-15 |  | 100 |  | 8 |  | 88000 | 3311 | 2018-08-06 | Monthly | Construction Services | 88000 | 88000 | 88000
0 | 0 | 0 | 0 | 0 | 6382 | [8 empty] | 254215 |  | 150424 | 4 | 1019/SC/014 | GEO EGYPT | 3311 | psp | Suez Gulf Substation | APPROVED | 132000 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 23 | Overtime Hours | 6183 | 10000 |  | RATE | Overtime Hours | 500 | 20 | 10000 | 10000 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-02-15 |  | 90.4 |  | 452 |  | 9040 | 3311 | 2018-08-06 | Hour | Construction Services | 9040 | 9040 | 9040
0 | 0 | 0 | 0 | 0 | 6382 | [8 empty] | 326088 |  | 150424 | 4 | 1019/SC/014 | GEO EGYPT | 3311 | psp | Suez Gulf Substation | APPROVED | 132000 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 25 | Overtime Hours | 6183 | 1000 |  | RATE | Overtime Hours | 50 | 20 | 1000 | 1000 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-07-29 | Suez Gulf Substation | 0 |  | 0 |  | 0 | 3311 | 2018-08-06 | Hour | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 3251 | [8 empty] | 246122 |  | 139569 | 1 | 1019/Sc/013 | Mahmoud Hamdy Hussein | 3323 | psp | Suez Gulf Substation | APPROVED | 98720 | EGP | 2017-06-15 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | supply tools for form work of concrete slabs and finishing surface with helicopter | 6183 | 98720 | 2017-05-10 | RATE | supply tools for form work of concrete slabs and finishing surface with helicopter | 2532.7 | 16 | 40523.2 | 40523.2 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2018-01-30 |  | 86.44 |  | 2189.16 |  | 35026.56 | 3323 | 2018-01-30 | Square Meter | Construction Services | 35026.56 | 35026.56 | 35026.56
0 | 0 | 0 | 0 | 0 | 3212 | [8 empty] | 263302 |  | 139464 | 1 | 1019/SC/010 | Ahmed Abdelafattah | 3294 | psp | Suez Gulf Substation | APPROVED | 246800 | EGP | 2017-06-13 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Cutting & fixing steel bars and finishing concrete surfaces with hardner and all requirments as specified | 6183 | 246800 |  | RATE | Cutting & fixing steel bars and finishing concrete surfaces with hardner and all requirments as specified | 1277.4 | 40 | 51096 | 51096 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2018-03-14 |  | 0.26 |  | 3.36 |  | 134.4 | 3294 | 2018-03-19 | Square Meter | Construction Services | 134.4 | 134.4 | 134.4
0 | 0 | 0 | 0 | 0 | 3191 | [8 empty] | 234101 |  | 139441 | 2 | 1019/SC/009 | Ahmed Abdelafattah | 3294 | psp | Suez Gulf Substation | APPROVED | 64620 | EGP | 2017-06-12 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | installation of concrete curb stone 50*30*15 cm | 6183 | 27000 |  | RATE | installation of concrete curb stone 50*30*15 cm | 251.7 | 20 | 5034 | 5034 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2018-01-10 |  | 100 |  | 251.7 |  | 5034 | 3294 | 2018-01-24 | Meter | Construction Services | 5034 | 5034 | 5034
0 | 0 | 0 | 0 | 0 | 3191 | [8 empty] | 234123 |  | 139441 | 2 | 1019/SC/009 | Ahmed Abdelafattah | 3294 | psp | Suez Gulf Substation | APPROVED | 64620 | EGP | 2017-06-12 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 2 | Remeassured item | 6183 | 37620 |  | RATE | Remeassured item | 1881 | 20 | 37620 | 37620 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2018-01-10 |  | 37.95 |  | 713.86 |  | 14277.2 | 3294 | 2018-01-24 | Meter | Construction Services | 14277.2 | 14277.2 | 14277.2
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231246 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for foundation/sub structure with diameter (Y 12 ) | 29.402 | 1300 | 38222.6 | 38222.6 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 29.43 |  | 8.652 |  | 38222.6 | 3653 | 2018-04-17 | Ton | Construction Services | 11247.6 | 11247.6 | 11247.6
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231426 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per linear meter Expansion joint including water stop , joint sealant and all requirement as Specified | 97.85 | 30 | 2935.5 | 2935.5 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 100 |  | 97.85 |  | 2935.5 | 3653 | 2018-04-17 | Meter | Construction Services | 2935.5 | 2935.5 | 2935.5
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231433 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | fixing steel plates variance dims | 96 | 120 | 11520 | 11520 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-29 |  | 100 |  | 96 |  | 11520 | 3653 | 2018-04-17 | Each | Construction Services | 11520 | 11520 | 11520
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231415 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per square meter : Supply and installation of gravel layer 20cm thickness ( max agg. Size 64mm ) over grating as Specified. | 1255 | 30 | 37650 | 37650 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Each | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231435 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | light weight concrete | 18 | 200 | 3600 | 3600 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-29 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Cubic Meter | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231292 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for columns and walls in with diameter (Y 10 ) . | 0.81 | 1300 | 1053 | 1053 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Ton | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231291 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | "Apply Fare face reinforced concrete ""RC"" Grade C32/40 for TR"Apply Fare face reinforced concrete ""RC"" Grade C32/40 for TRENCHES COVER . | 22.68 | 750 | 17010 | 17010 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Ton | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231297 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per cubic meter backfiling by the excavated material | 3208 | 25 | 80200 | 80200 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Cubic Meter | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231219 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | "Apply Lean concrete ""all shape, all thickness"" including shuttering ,vabor barrier 200 micron, mechanical trowling, and as specified | 130.02 | 220 | 28604.4 | 28604.4 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 31.7 |  | 41.22 |  | 28603.96 | 3653 | 2018-04-17 | Cubic Meter | Construction Services | 9068.4 | 9068.4 | 9068.4
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231229 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for foundation/sub structure with diameter (Y 10 ) | 7.581 | 1300 | 9855.3 | 9855.3 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 62.51 |  | 4.739 |  | 9855.3 | 3653 | 2018-04-17 | Ton | Construction Services | 6160.7 | 6160.7 | 6160.7
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231287 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for columns and walls in with diameter (Y 10 ) . | 2.85 | 1300 | 3705 | 3705 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 99.84 |  | 2.8454 |  | 3699.02 | 3653 | 2018-04-17 | Ton | Construction Services | 3699.02 | 3699.02 | 3699.02
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231284 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | "Apply Fare face reinforced concrete ""RC"" Grade C32/40 for columns and walls . | 499.545 | 750 | 374658.75 | 374658.75 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 100 |  | 499.545 |  | 374658.75 | 3653 | 2018-04-17 | Cubic Meter | Construction Services | 374658.75 | 374658.75 | 374658.75
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231294 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for columns and walls in with diameter (Y 12 ) . | 3.16 | 1300 | 4108 | 4108 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Ton | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231431 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Saveto for fire walls | 1334.63 | 70 | 93424.1 | 93424.1 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-29 |  | 100 |  | 1334.63 |  | 93424.1 | 3653 | 2018-04-17 | Meter | Construction Services | 93424.1 | 93424.1 | 93424.1
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231417 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per number : Instaullation of steel anchor bolt as Specified. | 408 | 10 | 4080 | 4080 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 100 |  | 408 |  | 4080 | 3653 | 2018-04-17 | Each | Construction Services | 4080 | 4080 | 4080
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231260 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for foundation/sub structure with diameter (Y 22 ) | 3.825 | 1300 | 4972.5 | 4972.5 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 4972.5 | 3653 | 2018-04-17 | Ton | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231301 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Per square meter: supply and apply Internal insulation using oil resistance epoxy painting as specified. | 695.29 | 25 | 17382.25 | 17382.25 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Square Meter | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231288 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for columns and walls in with diameter (Y 12 ) . | 7.292 | 1300 | 9479.6 | 9479.6 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 100 |  | 7.292 |  | 9479.6 | 3653 | 2018-04-17 | Ton | Construction Services | 9479.6 | 9479.6 | 9479.6
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231428 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per liner meter galvanized angels as specified | 275.09 | 30 | 8252.7 | 8252.7 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-29 |  | 100 |  | 275.09 |  | 8252.7 | 3653 | 2018-04-17 | Meter | Construction Services | 8252.7 | 8252.7 | 8252.7
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231298 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Per cubic meter : Delivery Non shrink grout as per Specified. | 22 | 350 | 7700 | 7700 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Cubic Meter | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231228 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Apply Fare faceReinforced Concrete for sub structure/ underground structure | 438.943 | 400 | 175577.2 | 175577.2 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 14.63 |  | 64.23 |  | 175576.4 | 3653 | 2018-04-17 | Cubic Meter | Construction Services | 25692 | 25692 | 25692
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231413 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per linear : Supply and erection of Rails including painting & base plate and its fixation& installation requirement as Specified. | 300 | 300 | 90000 | 90000 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Each | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231423 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Per square meter : supply and apply three prependiculare coats of bituminous paints as specified | 1298.964 | 25 | 32474.1 | 32474.1 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 100 |  | 1298.964 |  | 32474.1 | 3653 | 2018-04-17 | Square Meter | Construction Services | 32474.1 | 32474.1 | 32474.1
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231233 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for foundation/sub structure with diameter (Y 12 ) | 14.002 | 1300 | 18202.6 | 18202.6 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 64.71 |  | 9.06 |  | 18202.6 | 3653 | 2018-04-17 | Ton | Construction Services | 11778 | 11778 | 11778
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231349 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per square meter : Galvanized grating including supporting beams & installation requirement as Specified. | 190 | 30 | 5700 | 5700 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 0 |  | 0 |  | 0 | 3653 | 2018-04-17 | Square Meter | Construction Services | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231235 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for foundation/sub structure with diameter (Y 12 ) | 28.927 | 1300 | 37605.1 | 37605.1 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 24.58 |  | 7.111 |  | 37605.1 | 3653 | 2018-04-17 | Ton | Construction Services | 9244.3 | 9244.3 | 9244.3
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231290 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | Fabrication, Supply and install Rebars for columns and walls in with diameter (Y 18 ) . | 16.68 | 1300 | 21684 | 21684 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 100 |  | 16.68 |  | 21684 | 3653 | 2018-04-17 | Ton | Construction Services | 21684 | 21684 | 21684
0 | 0 | 0 | 0 | 0 | 5581 | [8 empty] | 231412 |  | 147411 | 4 | 1019/Sc/016 | مؤسسة النور للمقاولات | 3653 | psp | Suez Gulf Substation | APPROVED | 905253.45 | EGP | 2017-11-08 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Install and apply the civil works activity as per the attached BOQ, the work shall include the followings:Manpower, tools, equipment, workshop, accommodation, transportation, safety PPE and any other requirements to furnish the works. | 6183 | 905253.45 | 2017-11-12 | RATE | per unit :Supply and erection of pulling hock steel section (IPE 300) including painting & installation requirement as Specified. | 6 | 5000 | 30000 | 30000 | Suez Gulf Substation | 22.03.01 | SUB-Civil Works | 2017-12-28 |  | 100 |  | 6 |  | 30000 | 3653 | 2018-04-17 | Each | Construction Services | 30000 | 30000 | 30000
0 | 0 | 0 | 0 | 0 | 5579 | [8 empty] | 223955 |  | 147399 | 1 | 1019/Sc/018 | الوراد للأعمال التخصصية والمقاولات | 3654 | psp | Suez Gulf Substation | APPROVED | 46648.8 | EGP | 2017-11-07 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | applying membrane 4 mm | 6183 | 46648.8 |  | RATE | تركيب ممبرين لخزانات الصرف | 290 | 21.72 | 6298.8 | 6298.8 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2017-12-07 |  | 100 |  | 290 |  | 6298.8 | 3654 | 2017-12-07 | Square Meter | Construction Services | 6298.8 | 6298.8 | 6298.8
0 | 0 | 0 | 0 | 0 | 6392 | [8 empty] | 311141 |  | 150440 | 2 | 1019/SC/020 | الوراد للأعمال التخصصية والمقاولات | 3654 | psp | Suez Gulf Substation | APPROVED | 182225.5618 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | Epoxy Painting for autotransformer (Scope of supplying and applying) | 6195 | 113550.541 |  | RATE | Epoxy Painting for autotransformer (Scope of supplying and applying) | 640 | 177.4227 | 113550.541 | 113550.541 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-05-31 |  | 100 |  | 640 |  | 113550.541 | 3654 | 2018-11-04 | Square Meter | Construction Services | 113550.541 | 113550.541 | 113550.541
0 | 0 | 0 | 0 | 0 | 5579 | [8 empty] | 223946 |  | 147399 | 1 | 1019/Sc/018 | الوراد للأعمال التخصصية والمقاولات | 3654 | psp | Suez Gulf Substation | APPROVED | 46648.8 | EGP | 2017-11-07 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | applying membrane 4 mm | 6183 | 46648.8 |  | RATE | اعمال المعالجة للخزان | 85 | 150 | 12750 | 12750 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2017-12-07 |  | 100 |  | 85 |  | 12750 | 3654 | 2017-12-07 | Square Meter | Construction Services | 12750 | 12750 | 12750
0 | 0 | 0 | 0 | 0 | 5579 | [8 empty] | 223954 |  | 147399 | 1 | 1019/Sc/018 | الوراد للأعمال التخصصية والمقاولات | 3654 | psp | Suez Gulf Substation | APPROVED | 46648.8 | EGP | 2017-11-07 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 1 | applying membrane 4 mm | 6183 | 46648.8 |  | RATE | اعمال المعالجة لخزان المباني | 115 | 240 | 27600 | 27600 | Suez Gulf Substation | 2.03.01 | SUB-Civil Works | 2017-12-07 |  | 100 |  | 115 |  | 27600 | 3654 | 2017-12-07 | Square Meter | Construction Services | 27600 | 27600 | 27600
0 | 0 | 0 | 0 | 0 | 6392 | [8 empty] | 326024 |  | 150440 | 2 | 1019/SC/020 | الوراد للأعمال التخصصية والمقاولات | 3654 | psp | Suez Gulf Substation | APPROVED | 182225.5618 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 4 | Skirting | 6195 | 11680.62 |  | RATE | Skirting | 243.6 | 47.95 | 11680.62 | 11680.62 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-07-29 | Suez Gulf Substation | 100 |  | 243.6 |  | 11680.62 | 3654 | 2018-11-04 | Meter | Construction Services | 11680.62 | 11680.62 | 11680.62
0 | 0 | 0 | 0 | 0 | 6392 | [8 empty] | 326012 |  | 150440 | 2 | 1019/SC/020 | الوراد للأعمال التخصصية والمقاولات | 3654 | psp | Suez Gulf Substation | APPROVED | 182225.5618 | EGP | 2018-01-01 | Karim Samy Ahmed Ibrahim El tantawy, Mr. | 3 | Epoxy Painting for autotransformer (Scope of supplying and applying) Rev.01 | 6195 | 56994.4008 |  | RATE | Epoxy Painting for autotransformer (Scope of supplying and applying) | 321.24 | 177.42 | 56994.4008 | 56994.4008 | Suez Gulf Substation | 21.08.01 | Civil Material | 2018-07-29 | Suez Gulf Substation | 100 |  | 321.24 |  | 56994.4008 | 3654 | 2018-11-04 | Square Meter | Construction Services | 56994.4008 | 56994.4008 | 56994.4008