## eslam.data
project | invoice no. | invoice month | cut off date | submittal date | duration of pay | pay due date | approval_date | Gross | Net | Collection | cummulative amount approved | dp amount | on account amount | material on site cummulative amount approved | v.o. cummulative amount approved | ncr cummulative amount approved | escalation cummulative amount approved | 1st retention cummulative amount approved | 2nd retention cummulative amount approved | total deductions | project name in invoicing | Collection from ERP | Collection Cases | Gross From ERP | Gross Cases | Notes | Gross - Material on Site (both eslam) | Gross Cases (MOS Deducted) | concact
6TH October tunnel | 1 | 2022-05-31 | 2022-06-08 | 2022-06-15 | 60 | 2022-08-14 | 2022-09-11 | 842930 | 1520548 | 1520548 | 842930 |  |  | 1367190 | [5 empty] | 0 | October Under-Railway Tunnel | [7 empty] | 6TH October tunnel1
6TH October tunnel | 2 | 2022-07-31 | 2022-08-10 | 2022-08-21 | 60 | 2022-10-20 | 2022-09-25 | 3756426.15 | 3208372.9 | 3508372.9 | 4599356.15 |  |  | 921846.75 | [5 empty] | 0 | October Under-Railway Tunnel | [7 empty] | 6TH October tunnel2
6TH October tunnel | 3 | 2022-08-31 | 2022-09-06 | 2022-09-07 | 60 | 2022-11-06 |  |  |  | 0.001 | [9 empty] | 0 | October Under-Railway Tunnel | [7 empty] | 6TH October tunnel3
6TH October tunnel | 4 | 2022-09-30 | 2022-10-01 | 2022-11-13 | 60 | 2023-01-12 | 2022-11-14 | 7050454.75 | 5155347.5 | 5155347 | 11649810.9 |  |  | 750750 | [5 empty] | 0 | October Under-Railway Tunnel | [7 empty] | 6TH October tunnel4
6TH October tunnel | 5 | 2022-10-31 | 2022-11-15 | 2022-11-17 | 60 | 2023-01-16 | 2022-11-25 | 3846689.4 | 3524900.34 | 2856009 | 15496500.3 |  |  | 298295 | [5 empty] | 0 | October Under-Railway Tunnel | [7 empty] | 6TH October tunnel5
6TH October tunnel | 6 | 2022-12-31 | 2022-12-15 | 2023-01-09 | 60 | 2023-03-10 | 2023-02-12 | 1899766.7 | 1337162.6 | 1337162.6 | 17396267 | [8 empty] | 0 | October Under-Railway Tunnel | [7 empty] | 6TH October tunnel6
Abo Ghaleb Bridge | 1 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 60 | 2022-04-04 |  |  |  | 175270.85 | [9 empty] | 0 | Abo Ghaleb | [7 empty] | Abo Ghaleb Bridge1
Abo Ghaleb Bridge | 2 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 3079766.7 | 2494611.027 | 2494611.027 | 15845653.7 | [8 empty] | 0 | Abo Ghaleb | [7 empty] | Abo Ghaleb Bridge2
Abo Ghaleb Bridge | 3 | 2022-03-31 | 2022-03-31 | 2022-04-04 | 60 | 2022-06-03 | 2022-04-04 | 3857104.5 | 3124254.645 | 2045810.923 | 19702758.2 | [8 empty] | 0 | Abo Ghaleb | [7 empty] | Abo Ghaleb Bridge3
Abo Ghaleb Bridge | 4 | 2022-04-30 | 2022-04-30 | 2022-04-15 | 60 | 2022-06-14 | 2022-08-09 | 17739438 | 6555212.9406 | 12711007.22 | 37442196.2 | [8 empty] | 0 | Abo Ghaleb | [7 empty] | Abo Ghaleb Bridge4
Abo Ghaleb Bridge | 5 | 2022-07-31 | 2022-07-31 | 2022-08-21 | 60 | 2022-10-20 | 2022-08-21 | 2031888 | 1645829.28 | 1645829.28 | 39474084.2 | [8 empty] | 0 | Abo Ghaleb | [7 empty] | Abo Ghaleb Bridge5
Abo Ghaleb Bridge | 6 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 |  |  |  | 0.0001 | [9 empty] | 0 | Abo Ghaleb | [7 empty] | Abo Ghaleb Bridge6
AEON | 1 | 2020-09-30 | 2020-09-16 | 2020-09-20 | 56 | 2020-11-15 | 2020-09-22 | 1325211.2762 | 1264914.16 | 1264914.16 | 1325211.2762 | [8 empty] | 0 | 0 | [7 empty] | AEON1
AEON | 2 | 2020-10-31 | 2020-11-03 | 2020-11-03 | 56 | 2020-12-29 | 2020-12-15 | 1613181.4 | 1513146.56 | 1513146.56 | 2938392.6762 | [8 empty] | 0 | 0 | [7 empty] | AEON2
AEON | 3 | 2020-12-31 | 2020-12-20 | 2020-12-21 | 56 | 2021-02-15 | 2021-01-04 | 799158.9955 | 780253.0677 | 780253.07 | 3737551.6717 |  |  | 20153.7514 | [5 empty] | 27500 | 0 | [7 empty] | AEON3
AEON | 4 | 2021-02-28 | 2021-02-28 | 2021-06-24 | 56 | 2021-08-19 |  |  |  | 484406.35 | [9 empty] | 0 | 0 | [7 empty] | AEON4
Al Jazi | 1 | 2018-04-30 | 2018-05-21 | 2018-05-21 | 15 | 2018-06-05 | 2018-06-03 | 9888666.63 | 2199496 | 55324495 | 9888666.63 | 53125000 |  | 0 | [5 empty] | 5395000 | Aljazi Project | [7 empty] | Al Jazi1
Al Jazi | 2 | 2018-05-31 | 2018-06-05 | 2018-06-07 | 15 | 2018-06-22 | 2018-06-26 | 6959342.1 | 2330066 | 2330066 | 16848008.73 |  |  | 0 | [5 empty] | 8409664 | Aljazi Project | [7 empty] | Al Jazi2
Al Jazi | 3 | 2018-06-30 | 2018-07-04 | 2018-07-07 | 15 | 2018-07-22 | 2018-07-25 | 6863084.68 | 3357056.9 | 3090062.9 | 23711093.41 |  |  | 0 | [5 empty] | 10989780.0001 | Aljazi Project | [7 empty] | Al Jazi3
Al Jazi | 4 | 2018-07-31 | 2018-07-24 | 2018-07-24 | 15 | 2018-08-08 | 2018-07-29 | 6873217.27 | 3867947.36 | 3867947.36 | 30584310.68 |  |  | 0 | [5 empty] | 12001158.5 | Aljazi Project | [7 empty] | Al Jazi4
Al Jazi | 5 | 2018-07-31 | 2018-08-08 | 2018-08-11 | 15 | 2018-08-26 | 2018-08-30 | 7893070.92 | 4039155 | 4039155 | 38477381.6 |  |  | 1152162.9504 | [5 empty] | 15549196.5 | Aljazi Project | [7 empty] | Al Jazi5
Al Jazi | 6 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 15 | 2018-09-21 | 2018-09-10 | 4850391.56 | 2965400.21 | 2383592 | 43327773.16 |  |  | 1152162.95 | [5 empty] | 16838621.5 | Aljazi Project | [7 empty] | Al Jazi6
Al Jazi | 7 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 15 | 2018-10-17 | 2018-10-16 | 9360993.26 | 4138160 | 4138160 | 52688766.42 |  |  | 782387 | [5 empty] | 19429378.5 | Aljazi Project | [7 empty] | Al Jazi7
Al Jazi | 8 | 2018-10-31 | 2018-10-28 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-06 | 13305889.63 | 7730375.21 | 6905844.19 | 65994656.05 |  |  | 684096.75 | [5 empty] | 22966415.34 | Aljazi Project | [7 empty] | Al Jazi8
Al Jazi | 9 | 2018-11-30 | 2018-11-19 | 2018-11-19 | 15 | 2018-12-04 | 2018-11-28 | 11249079.12 | 3297350.06 | 1762571 | 77243735.17 |  |  | 504071.29 | [5 empty] | 28710343.34 | Aljazi Project | [7 empty] | Al Jazi9
Al Jazi | 10 | 2018-12-31 | 2018-12-04 | 2018-12-04 | 15 | 2018-12-19 | 2018-12-19 | 7201307.23 | 3398127.58 | 2302251 | 84445042.4 |  |  | 324045.83 | [5 empty] | 32846001.3 | Aljazi Project | [7 empty] | Al Jazi10
Al Jazi | 11 | 2018-12-31 | 2018-12-24 | 2018-12-24 | 15 | 2019-01-08 | 2019-01-08 | 10407080.28 | 4227710.49 | 3838772.36 | 94852122.68 |  |  | 0.001 | [5 empty] | 37611714.98 | Aljazi Project | [7 empty] | Al Jazi11
Al Jazi | 12 | 2019-01-31 | 2019-01-21 | 2019-01-22 | 15 | 2019-02-06 | 2019-02-04 | 8329656 | 2264521.51 | 922154 | 103181778.68 |  |  | 0.001 | [5 empty] | 42316559.84 | Aljazi Project | [7 empty] | Al Jazi12
Al Jazi | 13 | 2019-02-28 | 2019-02-17 | 2019-02-19 | 15 | 2019-03-06 | 2019-03-04 | 8749208.76 | 3848045.61 | 2994292.79 | 111930987.44 |  |  | 347539.5 | [5 empty] | 47070296.16 | Aljazi Project | [7 empty] | Al Jazi13
Al Jazi | 14 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-08 | 9382086.37 | 1995238.89 | 1629015.64 | 121313073.81 |  |  | 104261.85 | [5 empty] | 52347380.67 | Aljazi Project | [7 empty] | Al Jazi14
Al Jazi | 15 | 2019-04-30 | 2019-04-21 | 2019-04-24 | 15 | 2019-05-09 | 2019-05-09 | 9011217.19 | 2738501.15 | 2107757 | 130324291 |  |  | 208523.7 | [5 empty] | 56948226.2 | Aljazi Project | [7 empty] | Al Jazi15
Al Jazi | 16 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-06-01 | 9502208.88 | 1009779.23 | 120989.08 | 139826499.88 |  |  | 0.0001 | [5 empty] | 63851171.86 | Aljazi Project | [7 empty] | Al Jazi16
Al Jazi | 17 | 2019-06-30 | 2019-06-16 | 2019-06-18 | 15 | 2019-07-03 | 2019-07-06 | 7664029.32 | 3577364.85 | 2935343.72 | 147490529.2 |  |  | 0 | [5 empty] | 67191637.78 | Aljazi Project | [7 empty] | Al Jazi17
Al Jazi | 18 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-07-27 | 7401622.43 | 3297235.7 | 2748544.1 | 154892151.63 | [8 empty] | 70366044.94 | Aljazi Project | [7 empty] | Al Jazi18
Al Jazi | 19 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 9504587.63 | 4336532.29 | 3100493.11 | 164396739.26 | [8 empty] | 74067058.47 | Aljazi Project | [7 empty] | Al Jazi19
Al Jazi | 20 | 2019-09-30 | 2019-09-30 | 2019-10-07 | 15 | 2019-10-22 | 2019-11-03 | 8799095.49 | 2000000 | 371543.5 | 173195834.75 | [8 empty] | 80216713.09 | Aljazi Project | [7 empty] | Al Jazi20
Al Jazi | 21 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 33097306.6205 | 5243962.1948 | 0.0001 | 206293141.3705 | [8 empty] | 93639432.282 | Aljazi Project | [7 empty] | Al Jazi21
Al Jazi | 22 | 2020-04-30 | 2020-04-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 4356240.1195 | 8742870.72 | 8591440.49 | 210649381.49 | [9 empty] | Aljazi Project | [7 empty] | Al Jazi22
Al Jazi - Center Zone | 1 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-24 | 2348807.6 | 90608.89 | 14757189.01 | 2348807.6 | 14666580.12 | [7 empty] | 1554730.83 | Aljazi Project | [7 empty] | Al Jazi - Center Zone1
Al Jazi - Center Zone | 2 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-05-29 | 6291718.01 | 2035039.03 | 1686320.29 | 8640525.61 | [8 empty] | 4268341.03 | Aljazi Project | [7 empty] | Al Jazi - Center Zone2
Al Jazi - Center Zone | 3 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-09-01 | 12038668.84 | 360179.68 | 360179.68 | 20679194.45 | [8 empty] | 12373789.15 | Aljazi Project | [7 empty] | Al Jazi - Center Zone3
Al Jazi - Center Zone | 4 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 4840645.74 | 1090291.72 | 370581.69 | 25519840.19 | [8 empty] | 15657190.5 | Aljazi Project | [7 empty] | Al Jazi - Center Zone4
Al Jazi - Center Zone | 5 | 2019-09-30 | 2019-09-30 | 2019-10-08 | 15 | 2019-10-23 | 2019-11-03 | 7051826.31 | 1000000 | 858100 | 32571666.5 | [8 empty] | 20595342.09 | Aljazi Project | [7 empty] | Al Jazi - Center Zone5
Al Jazi - Center Zone | 6 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 6082957.03 | -2446690.14 | -0.01 | 38654623.53 | [8 empty] | 22479352.29 | Aljazi Project | [7 empty] | Al Jazi - Center Zone6
Al Jazi - Center Zone | 7 | 2020-03-31 | 2020-03-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 966768.0649 | 151431.3187 | 151431.32 | 39621391.5949 | [9 empty] | Aljazi Project | [7 empty] | Al Jazi - Center Zone7
Alfa Lab | 1 | 2021-10-31 | 2021-10-31 | 2021-12-05 | 30 | 2022-01-04 |  |  |  | 1459340 | [9 empty] | 0 | Alfa New Central Labs | [7 empty] | Alfa Lab1
Allegria-New Modifications | 1 | 2019-06-30 | 2019-07-02 | 2019-08-22 | 31 | 2019-09-22 |  |  |  | 659568.2 | [9 empty] | 0 | 0 | [7 empty] | Allegria-New Modifications1
Astoria - Sharm | 2 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 42 | 2022-08-16 | 2022-07-06 | 1243970 | 836570 | 837813.8 | 1243970 | [6 empty] | 65308.425 | 65308.425 | 0 | Astoria Sharm elSheikh | [7 empty] | Astoria - Sharm2
Astoria - Sharm | 3 | 2022-07-31 | 2022-07-31 | 2022-08-03 | 42 | 2022-09-14 | 2022-08-09 | 401082.65 | 269728 | 269728 | 1645052.65 |  |  |  | 98567.65 |  |  | 21056.84 | 21056.84 | 0 | Astoria Sharm elSheikh | [7 empty] | Astoria - Sharm3
Astoria - Sharm | 4 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 42 | 2022-10-12 | 2022-09-05 | 2440310 | 1641108 | 1641108 | 4085362.65 |  |  |  | 98567.65 |  |  | 128116.275 | 128116.275 | 0 | Astoria Sharm elSheikh | [7 empty] | Astoria - Sharm4
Astoria - Sharm | 5 | 2022-09-30 | 2022-09-30 | 2022-10-04 | 42 | 2022-11-15 | 2022-10-06 | 1055208 | 709627 | 709627 | 5140570.65 |  |  |  | 98567.65 |  | 33170 | 55398 | 55398 | 0 | Astoria Sharm elSheikh | [7 empty] | Astoria - Sharm5
Astoria - Sharm | 6 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 42 | 2022-12-09 | 2022-10-30 | 314831.49 | 244817 | 244817 | 5455402.14 |  |  |  | 98567.65 |  |  | 221100 | 221100 | 0 | Astoria Sharm elSheikh | [7 empty] | Astoria - Sharm6
Astoria - Sharm | 7 | 2022-11-30 | 2022-11-28 | 2022-11-28 | 42 | 2023-01-09 |  |  |  | 654151 | [9 empty] | 0 | Astoria Sharm elSheikh | [7 empty] | Astoria - Sharm7
Astoria - Sharm | 8 | 2023-01-31 | 2023-02-01 | 2023-02-01 | 42 | 2023-03-15 |  |  |  | 1160836 | [9 empty] | 0 | Astoria Sharm elSheikh | [7 empty] | Astoria - Sharm8
Astoria Hotel | 1 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 42 | 2022-03-29 | 2022-02-28 | 6707988.52 | 4511122 | 52550866.5 | 6707988.52 |  | 2000000 | [6 empty] | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel1
Astoria Hotel | 2 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 42 | 2022-04-20 | 2022-03-23 | 3507480.42 | 2448868 | 20864765.8 | 10215468.94 |  |  | 140761.4 |  |  |  | 191180.79 | 191180.79 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel2
Astoria Hotel | 3 | 2022-03-31 | 2022-03-31 | 2022-04-07 | 42 | 2022-05-19 | 2022-04-21 | 6522225.37 | 5421697 | 14629645.9 | 16737694.31 |  |  | 3185804.68 |  |  |  | 501707.065 | 501707.065 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel3
Astoria Hotel | 4 | 2022-04-30 | 2022-05-10 | 2022-05-17 | 42 | 2022-06-28 | 2022-05-31 | 5466647.24 | 4634265 | 13842213.9 | 22204341.55 |  |  | 4790259 | 987281.94 |  |  | 1171022.63 | 1171022.63 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel4
Astoria Hotel | 5 | 2022-05-31 | 2022-06-01 | 2022-06-05 | 42 | 2022-07-17 | 2022-06-28 | 3030560.1014 | 5818860 | 5818860 | 25234901.6514 |  |  | 9900984.5198 | 1091283.222 |  |  | 538643.0456 | 538643.0456 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel5
Astoria Hotel | 6 | 2022-06-30 | 2022-06-28 | 2022-06-29 | 42 | 2022-08-10 | 2022-07-06 | 14829494.3486 | 8446328.13 | 8446328.13 | 40064396 |  |  | 11427302 | 2183203.94 |  |  | 2103380.5 | 2103380.5 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel6
Astoria Hotel | 7 | 2022-07-31 | 2022-08-03 | 2022-08-04 | 42 | 2022-09-15 | 2022-08-08 | 11030217.63 | 8710615 | 8710615 | 51094613.63 |  |  | 12186248.36 | 2194500 |  |  | 849101.84 | 849101.84 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel7
Astoria Hotel | 8 | 2022-08-31 | 2022-08-20 | 2022-08-25 | 42 | 2022-10-06 | 2022-09-08 | 14516248.37 | 2805916 | 2805916 | 65610862 |  |  | 13343046 | 6856879.13 |  |  | 3444570.26 | 3444570.26 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel8
Astoria Hotel | 9 | 2022-09-30 | 2022-09-15 | 2022-09-21 | 42 | 2022-11-02 | 2022-09-26 | 10555127.63 | 6286403 | 6286403 | 76165989.63 |  |  | 6497174.95 | 1117474.28 |  |  | 713450.5 | 713450.5 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel9
Astoria Hotel | 10 | 2022-09-30 | 2022-09-27 | 2022-10-03 | 42 | 2022-11-14 | 2022-10-06 | 9739259.16 | 4982321 | 4982321 | 85905248.79 |  |  | 7583343.27 | 4748282.13 |  |  | 565619.52 | 565619.52 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel10
Astoria Hotel | 11 | 2022-10-31 | 2022-10-17 | 2022-10-23 | 42 | 2022-12-04 | 2022-10-31 | 22454296.86 | 10757000 | 10757000 | 108359545.65 |  |  | 9996725.48 | 8116978.46 |  |  | 6188712.42 | 6188712.42 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel11
Astoria Hotel | 12 | 2022-10-31 | 2022-10-31 | 2022-11-03 | 42 | 2022-12-15 | 2022-11-10 | 7707398.94 | 2603000 | 2603000 | 116066944.59 |  |  | 7811106.63 | 9547937.37 |  |  | 6484069.92 | 6484069.92 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel12
Astoria Hotel | 13 | 2022-11-30 | 2022-11-19 | 2022-11-22 | 42 | 2023-01-03 | 2022-11-28 | 11273556.71 | 5389256 | 5389256 | 127340501.3 |  |  | 8209371.3 | 13101564.96 |  |  | 7095844.885 | 7095844.885 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel13
Astoria Hotel | 14 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2022-12-20 | 13597376.25 | 6216098 | 6216098 | 140937877.55 |  |  | 8044171.13 | 13024305.91 |  |  | 7801447.13 | 7801447.13 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel14
Astoria Hotel | 15 | 2022-12-31 | 2022-12-31 | 2022-12-26 | 42 | 2023-02-06 | 2023-01-25 | 9032753.11 | 4185662 | 4185662 | 149970630.66 |  |  | 8062383.03 | 14785109.7 |  |  | 8276577.26 | 8276577.26 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel15
Astoria Hotel | 16 | 2023-01-31 | 2023-02-08 | 2023-02-09 | 42 | 2023-03-23 | 2023-02-25 | 9372213.83 | 3225683 | 3225683 | 159342844.49 |  |  | 5542006.23 | 15892420.28 |  |  | 8642599.645 | 8642599.645 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel16
Astoria Hotel | 17 | 2023-02-28 | 2023-03-09 | 2023-03-13 | 42 | 2023-04-24 | 2023-04-02 | 7818140.35 | 2804159 | 2804159 | 167160984.84 |  |  | 3697164.11 | 15797479.81 |  |  | 8960809.91 | 8960809.91 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel17
Astoria Hotel | 18 | 2023-04-30 | 2023-04-19 | 2023-04-19 | 42 | 2023-05-31 | 2023-05-10 | 10420915.55 | 4819756 | 4819756 | 177581900.39 |  |  | 3697164.11 | 22952907.31 |  |  | 9507907.975 | 9507907.975 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel18
Astoria Hotel | 19 | 2023-05-31 | 2023-06-07 | 2023-06-08 | 42 | 2023-07-20 | 2023-06-19 | 12873774.1358 | 1511334.2104 | 1511334.24 | 190455674.5258 |  |  |  | 28856915.5258 |  |  | 10019924.47 | 10019924.47 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel19
Astoria Hotel | 20 | 2023-06-30 | 2023-07-13 | 2023-07-13 | 42 | 2023-08-24 | 2023-08-02 | 3956219.0142 | 3400772 | 0.0001 | 194411893.54 |  |  | 84871.19 | 34031882.79 |  |  | 10210867.97 | 10210867.97 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel20
Astoria Hotel | 21 | 2023-07-31 | 2023-08-15 | 2023-08-15 | 42 | 2023-09-26 | 2023-09-14 | 1422437.2 | 854979 | 0.0001 | 195834330.74 |  |  | 84871.19 | 37786420.4 |  |  | 10285545.925 | 10285545.925 | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel21
Astoria Hotel | 22 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 42 | 2023-11-13 | 2023-10-14 | 10800888.71 | 9327545.58 | 1e-05 | 206635219.45 |  |  |  | 43324930.66 |  |  | 10848349.02 | 10848349.02 | 1170750 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel22
Astoria Hotel | 23 | 2023-10-31 | 2023-11-12 | 2023-11-12 | 42 | 2023-12-24 | 2023-11-23 | 13277404.55 | 17286732.59 | 17286732.59 | 219912624 |  |  |  | 44280344.8 |  | 10667080 | 10985391.04 | 10985391.04 | 8403824.77 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel23
Astoria Hotel | 24 | 2023-11-30 | 2023-11-28 | 2023-11-28 | 42 | 2024-01-09 |  |  |  | 10400000 | [9 empty] | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel24
Astoria Hotel | 25 | 2023-11-30 | 2023-11-30 | 2024-02-07 | 42 | 2024-03-20 |  |  |  | 3117985 | [9 empty] | 0 | Waldorf Astoria Cairo | [7 empty] | Astoria Hotel25
Baraka Land Fence | 1 | 2023-10-31 | 2023-10-30 | 2023-11-06 | 42 | 2023-12-18 | 2023-11-06 | 3575400 | 2645796 | 2467026 | 3575400 | [8 empty] | 0 | 0 | [7 empty] | Baraka Land Fence1
Baraka Land Fence | 2 | 2023-11-30 | 2023-11-30 | 2023-12-04 | 42 | 2024-01-15 |  |  |  | 8497787.46 | [9 empty] | 0 | 0 | [7 empty] | Baraka Land Fence2
Baraka Land Fence | 3 | 2024-02-29 | 2024-03-11 | 2024-03-11 | 42 | 2024-04-22 | 2024-03-20 | 23602796 | 16535567.88 | 15418299.78 | 38236396 | [8 empty] | 0 | 0 | [7 empty] | Baraka Land Fence3
Baraka Land Fence | 4 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-05-21 | 11760884 | 8703054.16 | 6072172.61 | 49997280 | [8 empty] | 0 | 0 | [7 empty] | Baraka Land Fence4
Baraka Land Fence | 5 | 2024-08-31 | 2024-08-20 | 2024-08-20 | 42 | 2024-10-01 | 2024-08-20 | 7617134 | 5636679.16 | 0 | 57614414 | [8 empty] | 0 | 0 | [7 empty] | Baraka Land Fence5
Benban - Aswan | 2 | 2018-06-30 | 2018-07-11 | 2018-07-11 | 60 | 2018-09-09 | 2018-07-26 | 22287932.1928 | 21953613.1594 | 21842173.61 | 22287932.1928 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | Benban - Aswan2
Benban - Aswan | 3 | 2018-07-31 | 2018-07-31 | 2018-08-05 | 60 | 2018-10-04 | 2018-09-11 | 10786951.8956 | 10577813.1577 | 10577813.02 | 33074884.0884 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | Benban - Aswan3
Benban - Aswan | 4 | 2018-08-31 | 2018-08-31 | 2018-09-05 | 60 | 2018-11-04 | 2018-09-20 | 15307380.738 | 15006351.7412 | 15006351.74 | 48382264.8264 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | Benban - Aswan4
Benban - Aswan | 5 | 2018-09-30 | 2018-09-30 | 2018-10-08 | 60 | 2018-12-07 | 2018-10-30 | 36144803.3444 | 37440886.7444 | 37440497.15 | 84527068.1708 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan5
Benban - Aswan | 6 | 2018-10-31 | 2018-10-31 | 2018-11-11 | 60 | 2019-01-10 | 2018-11-28 | 23770609.3964 | 23958997.0448 | 23886898.7775 | 108297677.5672 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan6
Benban - Aswan | 7 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 60 | 2019-02-03 | 2018-12-08 | 25005235.2928 | 25352621.3844 | 25237199.4694 | 133302912.86 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan7
Benban - Aswan | 8 | 2018-12-31 | 2019-01-03 | 2019-01-03 | 60 | 2019-03-04 | 2019-01-06 | 27760540.7682 | 28073115.5265 | 28236383.5819 | 161063453.6282 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan8
Benban - Aswan | 9 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 60 | 2019-04-01 | 2019-02-03 | 31169325.9933 | 33103432.2978 | 33103432.2978 | 192232779.6215 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan9
Benban - Aswan | 10 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 60 | 2019-05-05 | 2019-03-10 | 12107665.0539 | 12014082.9225 | 12102732.036 | 204340444.6754 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan10
Benban - Aswan | 11 | 2019-03-31 | 2019-03-31 | 2019-04-01 | 60 | 2019-05-31 | 2019-04-07 | 2235914.343 | 2314903.9752 | 2222964.1737 | 206576359.0184 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan11
Benban - Aswan | 12 | 2019-04-30 | 2019-05-01 | 2019-05-01 | 60 | 2019-06-30 | 2019-05-09 | 15216014.8348 | 16690051.1455 | 16625097.353 | 221792373.8532 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan12
Benban - Aswan | 13 | 2019-05-31 | 2019-05-31 | 2019-05-30 | 60 | 2019-07-29 | 2019-07-11 | 1724157.1613 | 36947.2012 | 36700.14 | 223516531.0145 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan13
Benban - Aswan | 14 | 2019-06-30 | 2019-07-02 | 2019-07-02 | 60 | 2019-08-31 | 2019-07-11 | 30114 | 1206378.8856 | 1174778.08 | 223546645.0145 | [8 empty] | 0 | 0 | [7 empty] | Benban - Aswan14
Cement Plant | 14 | 2017-09-30 | 2017-09-25 | 2017-10-03 | 45 | 2017-11-17 | 2017-10-19 | 6421251.87 | 7309725 | 7309725 | 219688342.71 | [8 empty] | 0 | Cement Factory-Beni Suef | [7 empty] | Cement Plant14
Cement Plant | 15 | 2017-10-31 | 2017-10-25 | 2017-11-02 | 45 | 2017-12-17 | 2017-11-15 | 8583366.193 | 6696657.1239 | 6696657.1239 | 228271708.9079 | [8 empty] | 139900 | Cement Factory-Beni Suef | [7 empty] | Cement Plant15
Cement Plant | 16 | 2017-11-30 | 2017-11-25 | 2017-12-05 | 45 | 2018-01-19 | 2017-12-14 | 6621784.9509 | 6990595.3607 | 6990595.3607 | 234893493.8588 | [8 empty] | 149900 | Cement Factory-Beni Suef | [7 empty] | Cement Plant16
Cement Plant | 17 | 2017-12-31 | 2017-12-25 | 2018-01-04 | 45 | 2018-02-18 | 2018-01-15 | 6642565.2352 | 7424114.8339 | 7424114.8339 | 241536059.094 | [8 empty] | 159900 | Cement Factory-Beni Suef | [7 empty] | Cement Plant17
Cement Plant | 18 | 2018-01-31 | 2018-01-25 | 2018-01-23 | 45 | 2018-03-09 | 2018-01-29 | 5438078.8724 | 6925479.9129 | 6925479.9129 | 246974137.9664 |  |  | 0 | [5 empty] | 185884 | Cement Factory-Beni Suef | [7 empty] | Cement Plant18
Cement Plant | 19 | 2018-02-28 | 2018-02-25 | 2018-02-28 | 45 | 2018-04-14 | 2018-03-17 | 12265173.6434 | 12791498.7957 | 12791497.7957 | 269687311.6098 |  |  | 0 | [5 empty] | 195884 | Cement Factory-Beni Suef | [7 empty] | Cement Plant19
Cement Plant | 20 | 2018-06-30 | 2018-06-25 | 2018-12-04 |  | 2019-01-30 | 2019-01-20 | 4976388.8902 | 10152661.36 | 10152661.36 | 274663700.5 | [9 empty] | Cement Factory-Beni Suef | [7 empty] | Cement Plant20
CFC | 1 | 2019-11-30 | 2019-11-25 | 2019-12-10 | 60 | 2020-02-08 | 2020-01-12 | 6586123.18 | 6200445.37 | 68335389.92 | 6586123.18 | 62134944.55 |  | 553645.74 | [5 empty] | 0 | CFC Podium 2 |  |  | 6586123.18 | 0 |  | 6032477.44 | 553645.74 | CFC1
CFC | 2 | 2019-12-31 | 2019-12-25 | 2020-01-09 | 60 | 2020-03-09 | 2020-02-11 | 16003200.38 | 17323666.18 | 48173070.33 | 22589323.56 | 31067472 |  | 4441799.42 | [5 empty] | 143549.58 | CFC Podium 2 |  |  | 15707266.4 | -295933.98 |  | 11561400.96 | 4145865.44 | CFC2
CFC | 3 | 2020-01-31 | 2020-01-25 | 2020-02-05 | 60 | 2020-04-05 | 2020-03-11 | 16743766.83 | 12263695.26 | 12263695.26 | 39333090.39 |  |  | 3876592.5 | [5 empty] | 60000 | CFC Podium 2 |  |  | 17039700.42 | 295933.59 |  | 12867174.33 | 4172526.09 | CFC3
CFC | 4 | 2020-02-29 | 2020-02-25 | 2020-03-11 | 60 | 2020-05-10 | 2020-04-02 | 35226223.2 | 32660833.58 | 32660833.58 | 74559313.59 |  |  | 8287526.25 | [5 empty] | 60000 | CFC Podium 2 |  |  | 35226223.59 | 0.39 |  | 26938696.95 | 8287526.64 | CFC4
CFC | 5 | 2020-03-31 | 2020-03-17 | 2020-03-21 | 60 | 2020-05-20 | 2020-04-22 | 30502560.31 | 24749111.95 | 24749111.95 | 105061873.9 |  |  | 7691894.47 | [5 empty] | 0 | CFC Podium 2 |  |  | 30502560 | -0.31 |  | 22810665.84 | 7691894.16 | CFC5
CFC | 6 | 2020-03-31 | 2020-03-25 | 2020-04-07 | 60 | 2020-06-06 | 2020-05-04 | 42011127.9851 | 31500278.62 | 31500278.62 | 147073001.8851 |  |  | 3638239.2055 | [5 empty] | 60000 | CFC Podium 2 |  |  | 42011128.3 | 0.31492 |  | 38372888.7796 | 3638239.5204 | CFC6
CFC | 7 | 2020-04-30 | 2020-04-25 | 2020-05-07 | 60 | 2020-07-06 | 2020-06-04 | 17879880.0649 | 19510038 | 19510038 | 164952881.95 |  |  | 9650322 | [5 empty] | 0 | CFC Podium 2 |  |  | 17879880.11 | 0.045077 |  | 8229558.0649 | 9650322.0451 | CFC7
CFC | 8 | 2020-05-31 | 2020-05-25 | 2020-06-08 | 60 | 2020-08-07 | 2020-07-07 | 31008098.6054 | 21459124.497 | 21459124.497 | 195960980.5554 |  |  | 4559164.5 | [5 empty] | 0 | CFC Podium 2 |  |  | 31008097.6 | -1.0054 |  | 26448934.1054 | 4559163.4946 | CFC8
CFC | 9 | 2020-06-30 | 2020-06-25 | 2020-07-01 | 60 | 2020-08-30 | 2020-07-27 | 29660399.8248 | 24499895.52 | 24499895.82 | 225621380.3802 |  |  | 4522595.5868 | [5 empty] | 0 | CFC Podium 2 | 38508461.52 | 14008565.7 | 29660400.78 | 0.95519 |  | 25137804.2381 | 4522596.5419 | CFC9
CFC | 10 | 2020-07-31 | 2020-07-25 | 2020-07-28 | 60 | 2020-09-26 | 2020-08-26 | 46257284.4262 | 39448595.5711 | 39448595.84 | 271878664.8064 | [8 empty] | 353049.48 | CFC Podium 2 |  |  | 52098964.43 | 5841680.0038 |  | 46257284.4262 | 5841680.0038 | CFC10
CFC | 11 | 2020-08-31 | 2020-08-25 | 2020-08-31 | 60 | 2020-10-30 | 2020-09-29 | 22706553.5236 | 18030565.73 | 18030565.73 | 294585218.33 |  |  | 5378850.75 | [5 empty] | 0 | CFC Podium 2 |  |  | 16864873.52 | -5841680.0036 |  | 17327702.7736 | -462829.2536 | CFC11
CFC | 12 | 2020-09-30 | 2020-09-25 | 2020-10-07 | 60 | 2020-12-06 | 2020-11-04 | 35304714.2417 | 29691194.9757 | 29691194.9757 | 329889932.5717 |  |  | 5192537.25 | [5 empty] | 0 | CFC Podium 2 |  |  | 34817130.72 | -487583.5217 |  | 30112176.9917 | 4704953.7283 | CFC12
CFC | 13 | 2020-10-31 | 2020-10-25 | 2020-11-05 | 60 | 2021-01-04 | 2020-12-09 | 13502068.4452 | 23213755.7909 | 23213756.67 | 343392001.0169 |  |  | 19923580.7274 | [5 empty] | 0 | CFC Podium 2 |  |  | 13989651.96 | 487583.5148 |  | -6421512.2822 | 20411164.2422 | CFC13
CFC | 14 | 2020-11-30 | 2020-11-25 | 2020-12-05 | 60 | 2021-02-03 | 2021-01-11 | 29172801.673 | 19708944.2711 | 19708943.72 | 372564802.6899 |  |  | 14613590.8525 | [5 empty] | 0 | CFC Podium 2 | 19708943.72 | 0 | 29172801.68 | 0.0070295 |  | 14559210.8205 | 14613590.8595 | CFC14
CFC | 15 | 2020-12-31 | 2020-12-25 | 2021-01-06 | 60 | 2021-03-07 | 2021-02-22 | 46288367.9197 | 40379659.8985 | 40379659.8985 | 418853170.6096 |  |  | 17260909.7245 | [5 empty] | 1045046 | CFC Podium 2 | 40379659.63 | -0.26848 | 42273319.3 | -4015048.6197 |  | 29027458.1953 | 13245861.1047 | CFC15
CFC | 16 | 2021-01-31 | 2021-01-25 | 2021-02-03 | 60 | 2021-04-04 | 2021-03-21 | 25170121.1048 | 22871121.15 | 22871121.16 | 444023291.7144 |  |  | 19535751.2059 | [5 empty] | 0 | CFC Podium 2 |  |  | 29185169.72 | 4015048.6152 |  | 5634369.899 | 23550799.821 | CFC16
CFC | 17 | 2021-01-31 | 2021-02-10 | 2021-02-15 | 60 | 2021-04-16 | 2021-03-25 | 23196101.9456 | 15047803.36 | 15047803.35 | 467219393.66 |  |  | 14368442.92 | [5 empty] | 0 | CFC Podium 2 |  |  | 23196101.95 | 0.0044488 |  | 8827659.0256 | 14368442.9244 | CFC17
CFC | 18 | 2021-02-28 | 2021-02-25 | 2021-03-02 | 60 | 2021-05-01 | 2021-04-06 | 16880809.49 | 12196441.11 | 12196441.12 | 484100203.15 |  |  | 14078602.67 | [5 empty] | 0 | CFC Podium 2 |  |  | 16880809.49 | 4.8429e-08 |  | 2802206.82 | 14078602.67 | CFC18
CFC | 19 | 2021-03-31 | 2021-03-10 | 2021-03-17 | 60 | 2021-05-16 | 2021-04-20 | 20398722.16 | 14008565.71 | 14008565.7 | 504498925.31 |  |  | 10502130.78 | [5 empty] | 0 | CFC Podium 2 |  |  | 20398722.15 | -0.01 |  | 9896591.38 | 10502130.77 | CFC19
CFC | 20 | 2021-03-31 | 2021-03-25 | 2021-03-29 | 60 | 2021-05-28 | 2021-05-24 | 23102145.85 | 23721354.77 | 23721354.77 | 527601071.16 |  |  | 16161812.22 | [5 empty] | 992616.34 | CFC Podium 2 |  |  | 23105145.86 | 3000.01 |  | 6940333.63 | 16164812.23 | CFC20
CFC | 21 | 2021-04-30 | 2021-04-10 | 2021-04-15 | 60 | 2021-06-14 | 2021-06-17 | 23568050.8 | 17156225.13 | 17156725.12 | 551169121.96 |  |  | 15788492.2694 | [5 empty] | 3023908.26 | CFC Podium 2 |  |  | 23565050.79 | -3000.01 |  | 7779558.5306 | 15785492.2594 | CFC21
CFC | 22 | 2021-04-30 | 2021-04-25 | 2021-05-06 | 60 | 2021-07-05 | 2021-06-29 | 19833699.32 | 13410069.82 | 13410069.82 | 571002821.28 |  |  | 12047992.86 | [5 empty] | 0 | CFC Podium 2 |  |  | 19833699.33 | 0.01 |  | 7785706.46 | 12047992.87 | CFC22
CFC | 23 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 60 | 2021-08-29 | 2021-08-18 | 19569971.41 | 15440458.92 | 15440459.23 | 590572792.69 |  |  | 9696296.63 | [5 empty] | 0 | CFC Podium 2 |  |  | 19569971.41 | -8.9407e-08 |  | 9873674.78 | 9696296.63 | CFC23
CFC | 24 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 60 | 2021-09-13 | 2021-09-23 | 14455028.52 | 7464840.35 | 7464480.35 | 605027821.21 |  |  | 5161877.98 | [5 empty] | 5612498.72 | CFC Podium 2 |  |  | 14455028.51 | -0.01 |  | 9293150.54 | 5161877.97 | CFC24
CFC | 25 | 2021-07-31 | 2021-08-10 | 2021-08-16 | 60 | 2021-10-15 | 2021-10-25 | 13190112.67 | 9682524.47 | 9682524.46 | 618217933.88 |  |  | 1715079.08 | [5 empty] | 0 | CFC Podium 2 |  |  | 13190112.67 | 3.9116e-08 |  | 11475033.59 | 1715079.08 | CFC25
CFC | 26 | 2021-08-31 | 2021-08-25 | 2021-09-02 | 60 | 2021-11-01 | 2021-11-18 | 6460765.9427 | 2397254.3033 | 2397254.3033 | 624678699.8227 |  |  | 200294.3722 | [5 empty] | 0 | CFC Podium 2 |  |  | 6460765.95 | 0.0073488 |  | 6260471.5705 | 200294.3795 | CFC26
CFC | 27 | 2021-09-30 | 2021-09-10 | 2021-09-19 | 60 | 2021-11-18 | 2021-11-22 | 7714993.7673 | 10793868.55 | 10793868.64 | 632393693.59 | [8 empty] | 4776768.68 | CFC Podium 2 |  |  | 7714993.76 | -0.0073489 |  | 7714993.7673 | -0.0073489 | CFC27
CFC | 28 | 2021-09-30 | 2021-09-14 | 2022-03-07 | 60 | 2022-05-06 | 2022-05-09 | 5026145.47 | 10367935.42 | 10367935.31 | 637419839.06 | [6 empty] | 16732270.78 | 16732270.78 | 0 | CFC Podium 2 | [5 empty] | 5026145.47 | -5026145.47 | CFC28
CFC | 29 | 2021-09-30 | 2021-09-14 | 2022-10-03 | 60 | 2022-12-02 |  |  |  | 15034318.2703 | [9 empty] | 0 | CFC Podium 2 | [7 empty] | CFC29
Comoros - Off Shore | 1 | 2022-06-30 | 2022-06-23 | 2022-06-23 | 45 | 2022-08-07 |  |  |  | 2555388 | [9 empty] | 0 | Le Galawa Hotel Resort | [7 empty] | Comoros - Off Shore1
Comoros - Off Shore | 2 | 2023-01-31 | 2023-01-28 | 2023-03-21 | 45 | 2023-05-05 | 2023-03-21 | 1137692.89 | 910154.31 | 910154 | 4331928.01 | [8 empty] | 0 | Le Galawa Hotel Resort | [7 empty] | Comoros - Off Shore2
Comoros - Off Shore | 3 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 |  |  |  | 0 | [9 empty] | 0 | Le Galawa Hotel Resort | [7 empty] | Comoros - Off Shore3
Comoros - On Shore | 1 | 2023-01-31 | 2023-01-28 | 2023-03-23 | 45 | 2023-05-07 | 2023-03-23 | 1038550.94 | 830840.75 | 1094549.01 | 1038550.94 |  | 263708.26 | [6 empty] | 0 | Le Galawa Hotel Resort | [7 empty] | Comoros - On Shore1
Comoros - On Shore | 2 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 | 2023-10-12 | 506813.73 | 405450.99 | 405450.99 | 1545364.67 | [8 empty] | 0 | Le Galawa Hotel Resort | [7 empty] | Comoros - On Shore2
Creeks - URBN K | 1 | 2023-03-31 | 2023-04-10 | 2023-04-13 | 54 | 2023-06-06 | 2023-05-17 | 6070824.52 | 10729515.71 | 10729515 | 6070824.52 | 25000000 | 57750000 | 4917870 |  |  | 1412647.23 | 116454.43 | 116454.43 | 0 | Creeks URBN-K | 10729515 | 0 | 10988694.51 | 4917869.99 |  | 1152954.52 | 9835739.99 | Creeks - URBN K1
Creeks - URBN K | 2 | 2023-04-30 | 2023-05-10 | 2023-05-17 | 54 | 2023-07-10 | 2023-06-01 | 24895588.2 | 3863139.56 | 3863139 | 30966412.72 | [5 empty] | 9774769.5 | 529152.325 | 529152.325 | 0 | Creeks URBN-K | 3863139 | 0 | 19977718.2 | -4917870 |  | 24895588.2 | -4917870 | Creeks - URBN K2
Creeks - URBN K | 3 | 2023-05-31 | 2023-06-10 | 2023-06-13 | 54 | 2023-08-06 | 2023-06-18 | 40661954.88 | 21808950.42 | 21808950 | 71628367.6 | [5 empty] | 10182390.98 | 1536149.435 | 1536149.435 | 0 | Creeks URBN-K | 21808950 | 0 | 40661954.89 | 0.01 |  | 40661954.88 | 0.01 | Creeks - URBN K3
Creeks - URBN K | 4 | 2023-06-30 | 2023-07-10 | 2023-07-11 | 54 | 2023-09-03 | 2023-07-19 | 25969563.12 | 8830426.33 | 8830426 | 97597930.72 | [5 empty] | 11215823.74 | 2159552.5 | 2159552.5 | 0 | Creeks URBN-K | 8830426 | 0 | 25969563.12 | 0 |  | 25969563.12 | 0 | Creeks - URBN K4
Creeks - URBN K | 5 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 54 | 2023-10-07 | 2023-08-23 | 21068069.1 | 13533059.96 | 13533059 | 118665999.82 |  |  | 8750053.42 |  |  | 12015310.55 | 2666267.23 | 2666267.23 | 0 | Creeks URBN-K | 13533059 | 0 | 29818122.52 | 8750053.42 |  | 12318015.68 | 17500106.84 | Creeks - URBN K5
Creeks - URBN K | 6 | 2023-08-31 | 2023-09-13 | 2023-09-14 | 54 | 2023-11-07 | 2023-09-27 | 18829649.55 | 19608846.96 | 19608847 | 137495649.37 |  |  | 11186650.81 |  |  | 14124627.7 | 3084275.5 | 3084275.5 | 0 | Creeks URBN-K | 19608847 | 0 | 21266246.93 | 2436597.38 |  | 7642998.74 | 13623248.19 | Creeks - URBN K6
Creeks - URBN K | 7 | 2023-09-30 | 2023-10-13 | 2023-10-15 | 54 | 2023-12-08 | 2023-11-02 | 18845217.25 | 16761479.32 | 16761479 | 156340866.62 |  |  | 10998840.9 |  |  | 15355016.01 | 3524646.26 | 3524646.26 | 0 | Creeks URBN-K | 16761479 | 0 | 18657407.33 | -187809.92 |  | 7846376.35 | 10811030.98 | Creeks - URBN K7
Creeks - URBN K | 8 | 2023-10-31 | 2023-10-13 | 2023-11-15 | 54 | 2024-01-08 | 2023-12-02 | 21024971.71 | 16707965 | 16707965 | 177365838.33 |  |  | 8849533.16 | 524238 |  | 16370912 | 8023534 |  | 0 | Creeks URBN-K | 16707965 | 0 | 18875663.98 | -2149307.73 |  | 12175438.55 | 6700225.43 | Creeks - URBN K8
Creeks - URBN K | 9 | 2023-11-30 | 2023-12-13 | 2023-12-17 | 54 | 2024-02-09 | 2023-12-28 | 18661864.22 | 16997068.33 | 16997068 | 196027702.55 |  |  | 8808386.74 | 549978 |  | 19145680.99 | 8813027.1 |  | 0 | Creeks URBN-K | 16997068 | 0 | 18620717.8 | -41146.42 |  | 9853477.48 | 8767240.32 | Creeks - URBN K9
Creeks - URBN K | 10 | 2023-12-31 | 2024-01-13 | 2024-01-15 | 54 | 2024-03-09 | 2024-03-15 | 32359750.94 | 19246723.67 | 19246723 | 228387453.49 |  |  | 16680489.26 | 713540 |  | 34117344 | 9677828.4 |  | 0 | Creeks URBN-K | 19246723 | 0 | 40231853.45 | 7872102.51 | 2 lines in invoicing | 15679261.68 | 24552591.77 | Creeks - URBN K10
Creeks - URBN K | 11 | 2024-01-31 | 2024-02-13 | 2024-02-15 | 54 | 2024-04-09 | 2024-03-10 | 19399852.91 | 11569432.7 | 11569432 | 247787306.4 |  |  | 11166359.72 | 713540 |  | 34372400 | 10635068.27 |  | 0 | Creeks URBN-K | 11569432 | 0 | 13885723.37 | -5514129.54 |  | 8233493.19 | 5652230.18 | Creeks - URBN K11
Creeks - URBN K | 12 | 2024-02-29 | 2024-03-13 | 2024-03-16 | 54 | 2024-05-09 | 2024-04-03 | 13939506.69 | 8618325.74 | 8618325 | 261726813.09 |  |  | 7367986.2 | 777032.73 |  | 35392063.88 | 11277885.86 |  | 0 | Creeks URBN-K | 8618325 | 0 | 10141133.17 | -3798373.52 |  | 6571520.49 | 3569612.68 | Creeks - URBN K12
Creeks - URBN K | 13 | 2024-03-31 | 2024-03-13 | 2024-04-17 | 54 | 2024-06-10 | 2024-04-24 | 17837569.29 | 23221916.29 | 23221916 | 279564382.38 |  |  | 13337407.07 | 777032 |  | 42980609.88 | 11790337 |  | 0 | Creeks URBN-K | 23221916 | 0 | 23806990.16 | 5969420.87 |  | 4500162.22 | 19306827.94 | Creeks - URBN K13
Creeks - URBN K | 14 | 2024-04-30 | 2024-05-13 | 2024-05-16 | 54 | 2024-07-09 | 2024-05-22 | 11923940.57 | 6223873.19 | 6223873.19 | 291488322.95 |  |  | 9059823 | 777032.73 |  | 43382302 | 12366449.19 |  | 0 | Creeks URBN-K | 0 | -6223873.19 | 7646354.5 | -4277586.07 | collection with creeks | 2864117.57 | 4782236.93 | Creeks - URBN K14
Creeks - URBN K | 15 | 2024-05-31 | 2024-06-13 | 2024-06-11 | 54 | 2024-08-04 | 2024-06-12 | 15151516.49 | 10206848.68 | 10206848 | 306639839.44 |  |  | 4679535.56 | 777032 |  | 43540689 | 13094578 |  | 0 | Creeks URBN-K | 10206848 | 0 | 10771231.15 | -4380285.34 |  | 10471980.93 | 299250.22 | Creeks - URBN K15
Creeks - URBN K | 16 | 2024-06-30 | 2024-07-13 | 2024-07-15 | 54 | 2024-09-07 | 2024-07-29 | 8934038.52 | 6345313.67 | 6345314 | 315573877.96 |  |  | 2261543.76 | 777032.73 |  | 44277783.1705 | 13525953 |  | 0 | Creeks URBN-K | 6345314 | 0 | 6516046.61 | -2417991.91 |  | 6672494.76 | -156448.15 | Creeks - URBN K16
Creeks - URBN K | 17 | 2024-07-31 | 2024-08-13 | 2024-08-15 | 54 | 2024-10-08 | 2024-09-05 | 8615746.66 | 8554807.45 | 8554807 | 324189624.62 |  |  | 2200139 | 777032 |  | 46059367 | 13867661 |  | 0 | Creeks URBN-K | 17918257 | 9363450 | 8554341.9 | -61404.76 | 17,18 togeather | 6415607.66 | 2138734.24 | Creeks - URBN K17
Creeks - URBN K | 18 | 2024-08-31 | 2024-09-13 | 2024-09-15 | 54 | 2024-11-08 | 2024-09-25 | 9557078 | 9363449.62 | 9363450 | 333746702.62 |  |  | 2027936.1 | 777032 |  | 47680035 | 7132240.5 | 7132240.5 | 0 | Creeks URBN-K | 0 | -9363450 | 9384875.1 | -172202.9 |  | 7529141.9 | 1855733.2 | Creeks - URBN K18
Creeks - URBN K | 19 | 2024-10-31 | 2024-10-13 | 2024-10-15 | 54 | 2024-12-08 | 2024-11-02 | 6248543.66 | 6696306.5 | 0 | 339995246.28 |  |  | 2452144.43 | 777032 |  | 49061466 | 7253918.5 | 7253918.5 | 0 | Creeks URBN-K | [7 empty] | Creeks - URBN K19
Creeks - URBN K | 20 | 2024-11-30 | 2024-11-13 | 2024-11-14 | 54 | 2025-01-07 |  |  |  | 0 | [9 empty] | 0 | Creeks URBN-K | [7 empty] | Creeks - URBN K20
Damietta Port - Civil | 2 | 2024-10-31 | 2024-10-17 | 2024-10-17 | 42 | 2024-11-28 |  |  |  | 1520770.91 | [9 empty] | 0 | Damietta Container Termin | [7 empty] | Damietta Port - Civil2
Damietta Port - Civil | 3 | 2024-10-31 | 2024-10-30 | 2024-10-30 | 42 | 2024-12-11 |  |  |  | 1496696.18 | [9 empty] | 0 | Damietta Container Termin | [7 empty] | Damietta Port - Civil3
Damietta Port - Civil | 1 | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 |  |  |  | 4058690.9 |  | 4058690.9 | [7 empty] | 0 | Damietta Container Termin | [7 empty] | Damietta Port - Civil1
Damietta Port - Infra | 1 | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 |  |  |  | 6541975.22 |  | 6541975.22 | [7 empty] | 0 | #N/A | [7 empty] | Damietta Port - Infra1
DP World Sokhna | 1 | 2019-01-31 | 2019-02-04 | 2019-02-04 | 56 | 2019-04-01 | 2019-02-11 | 21619523.77 | 16214642.83 | 257561970.68 | 21619523.77 |  |  | 0 | [5 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna1
DP World Sokhna | 2 | 2019-02-28 | 2019-02-28 | 2019-03-04 | 56 | 2019-04-29 | 2019-03-05 | 24408793.91 | 18306595.43 | 18062199.23 | 46028317.68 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna2
DP World Sokhna | 3 | 2019-03-31 | 2019-03-31 | 2019-04-02 | 56 | 2019-05-28 | 2019-04-11 | 20754393.51 | 15565795.14 | 15357944.03 | 66782711.19 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna3
DP World Sokhna | 4 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 56 | 2019-06-30 | 2019-05-16 | 37757872.09 | 28318404.08 | 27940477.28 | 104540583.28 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna4
DP World Sokhna | 5 | 2019-05-31 | 2019-05-31 | 2019-06-02 | 56 | 2019-07-28 | 2019-06-16 | 17786446.66 | 13339835 | 13161622.85 | 122327029.94 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna5
DP World Sokhna | 6 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 56 | 2019-09-07 | 2019-08-06 | 33097932.28 | 24823449.22 | 24492163.72 | 155424962.22 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna6
DP World Sokhna | 7 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 56 | 2019-10-01 | 2019-08-22 | 40506959.47 | 30380219.6 | 29974844.16 | 195931921.69 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna7
DP World Sokhna | 8 | 2019-08-31 | 2019-09-05 | 2019-09-05 | 56 | 2019-10-31 | 2019-09-17 | 39363674.8 | 29522756.11 | 29128813.98 | 235295596.49 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna8
DP World Sokhna | 9 | 2019-09-30 | 2019-10-06 | 2019-10-08 | 56 | 2019-12-03 | 2019-10-23 | 54097551.55 | 40573163.66 | 40031882.73 | 289393148.04 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna9
DP World Sokhna | 10 | 2019-10-31 | 2019-11-17 | 2019-11-11 | 56 | 2020-01-06 | 2019-11-24 | 90533235.47 | 67899926.6 | 66994289.3 | 379926383.51 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna10
DP World Sokhna | 11 | 2019-11-30 | 2019-12-12 | 2019-12-12 | 56 | 2020-02-06 | 2019-12-22 | 102020049.91 | 76515037.44 | 76494532.33 | 481946433.42 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna11
DP World Sokhna | 12 | 2019-12-31 | 2020-01-15 | 2020-01-15 | 56 | 2020-03-11 | 2020-02-16 | 148210852.7 | 111158139.52 | 109675422.28 | 630157286.12 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna12
DP World Sokhna | 13 | 2020-01-31 | 2020-02-15 | 2020-02-18 | 56 | 2020-04-14 | 2020-03-16 | 124566872.96 | 93425154.72 | 92179486 | 754724159.08 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna13
DP World Sokhna | 14 | 2020-02-29 | 2020-03-17 | 2020-03-17 | 56 | 2020-05-12 | 2020-04-14 | 141052143.0757 | 105789107.3061 | 104378585.88 | 895776302.1557 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna14
DP World Sokhna | 15 | 2020-03-31 | 2020-04-15 | 2020-04-19 | 56 | 2020-06-14 | 2020-05-17 | 110730132.4543 | 83047599.34 | 81940298.01 | 1006506434.61 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna15
DP World Sokhna | 16 | 2020-04-30 | 2020-05-19 | 2020-05-19 | 56 | 2020-07-14 | 2020-06-21 | 86484919.88 | 64863689.91 | 63998840.71 | 1092991354.49 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna16
DP World Sokhna | 17 | 2020-05-31 | 2020-06-18 | 2020-06-18 | 56 | 2020-08-13 | 2020-07-22 | 56454657.9 | 42340993.43 | 41776446.85 | 1149446012.39 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna17
DP World Sokhna | 18 | 2020-06-30 | 2020-07-23 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-19 | 59878397.73 | 44908798.3 | 44310014.32 | 1209324410.12 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna18
DP World Sokhna | 19 | 2020-07-31 | 2020-08-19 | 2020-08-19 | 56 | 2020-10-14 | 2020-09-16 | 34366362.95 | 25774772.21 | 25431108.58 | 1243690773.07 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna19
DP World Sokhna | 20 | 2020-08-31 | 2020-09-17 | 2020-09-17 | 56 | 2020-11-12 | 2020-10-13 | 42996289.46 | 32247217.1 | 31817254.2 | 1286687062.53 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna20
DP World Sokhna | 21 | 2020-09-30 | 2020-10-15 | 2020-10-15 | 56 | 2020-12-10 | 2020-10-28 | 34792442.43 | 26094331.82 | 25746407.39 | 1321479504.96 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna21
DP World Sokhna | 22 | 2020-10-31 | 2020-11-13 | 2020-11-13 | 56 | 2021-01-08 | 2020-12-20 | 23946448.24 | 17959836.19 | 17720371 | 1345425953.2 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna22
DP World Sokhna | 23 | 2020-11-30 | 2020-12-10 | 2020-12-15 | 56 | 2021-02-09 | 2021-01-19 | 35871966.38 | 26903974.78 | 26545255.12 | 1381297919.58 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna23
DP World Sokhna | 24 | 2020-12-31 | 2021-01-10 | 2021-01-10 | 56 | 2021-03-07 | 2021-02-15 | 28199021.24 | 21149265.93 | 20867275.72 | 1409496940.82 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna24
DP World Sokhna | 25 | 2021-01-31 | 2021-02-16 | 2021-02-17 | 56 | 2021-04-14 | 2021-03-21 | 13937299.51 | 10452974.64 | 10313601.64 | 1423434240.33 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna25
DP World Sokhna | 26 | 2021-02-28 | 2021-03-17 | 2021-03-25 | 56 | 2021-05-20 | 2021-04-14 | 30564756.18 | 22923567.13 | 22617919.57 | 1453998996.51 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna26
DP World Sokhna | 27 | 2021-03-31 | 2021-04-15 | 2021-04-15 | 56 | 2021-06-10 | 2021-05-19 | 21307969.76 | 15980977.32 | 15718793.62 | 1475306966.27 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna27
DP World Sokhna | 28 | 2021-05-31 | 2021-05-23 | 2021-05-23 | 56 | 2021-07-18 | 2021-06-24 | 27099548.45 | 20324661.34 | 19977105.85 | 1502406514.72 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna28
DP World Sokhna | 29 | 2021-06-30 | 2021-06-24 | 2021-06-24 | 56 | 2021-08-19 | 2021-07-30 | 27690935.6 | 20768201.7 | 20394668.34 | 1530097450.32 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna29
DP World Sokhna | 30 | 2021-07-31 | 2021-07-29 | 2021-07-29 | 56 | 2021-09-23 | 2021-09-07 | 14579181.6 | 10934386.2 | 10739490.38 | 1544676631.92 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna30
DP World Sokhna | 31 | 2021-08-31 | 2021-09-02 | 2021-09-02 | 56 | 2021-10-28 | 2021-10-11 | 13597917.64 | 10198438.22 | 10014939.05 | 1558274549.56 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna31
DP World Sokhna | 32 | 2021-09-30 | 2021-10-05 | 2021-10-13 | 56 | 2021-12-08 | 2021-12-19 | 16694467.33 | 12520850.5 | 12304801.83 | 1574969016.89 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna32
DP World Sokhna | 33 | 2021-12-31 | 2021-12-22 | 2021-12-22 | 56 | 2022-02-16 | 2022-01-11 | 20335452.71 | 15251589.54 | 15048235.01 | 1595304469.6 | [8 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna33
DP World Sokhna | 34 | 2022-03-31 | 2022-04-06 | 2022-04-06 | 56 | 2022-06-01 | 2022-04-12 | 12548237.84 | 9025252.81 | 8899770.44 | 1607852707.44 | [6 empty] | 80392635.37 | 80392635.37 | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna34
DP World Sokhna | 35 | 2022-04-30 | 2022-05-15 | 2022-05-15 | 56 | 2022-07-10 | 2022-06-08 | 3275655.02 | 2948089.53 | 2915333 | 1611128362.46 |  |  |  | 37040890.72 |  |  | 80556418.125 | 80556418.125 | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna35
DP World Sokhna | 36 | 2022-05-31 | 2022-06-08 | 2022-06-08 | 56 | 2022-08-03 |  |  |  | 80556058.47 | [9 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna36
DP World Sokhna | 37 | 2023-02-28 | 2023-02-19 | 2023-02-19 | 56 | 2023-04-16 |  |  |  | 0 | [9 empty] | 0 | DPW Onshore Port & Terminal | [7 empty] | DP World Sokhna37
DPW - Ph.02 | 1 | 2023-01-31 | 2023-01-25 | 2023-01-31 | 56 | 2023-03-28 | 2023-02-16 | 23907099.3 | 21516389.4 | 21783711.58 | 23907099.3 | [6 empty] | 1195354.95 | 1195354.95 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.021
DPW - Ph.02 | 2 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 56 | 2023-04-27 | 2023-03-22 | 30365704.8 | 19188213.6 | 84506660.86 | 54272804.1 | [6 empty] | 2713640.25 | 2713640.25 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.022
DPW - Ph.02 | 3 | 2023-03-31 | 2023-03-25 | 2023-04-03 | 56 | 2023-05-29 | 2023-03-27 | 1809093.47 | 19827820.72 | 28493360.54 | 56081897.57 | [6 empty] | 2804094.925 | 2804094.925 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.023
DPW - Ph.02 | 4 | 2023-04-30 | 2023-04-25 | 2023-05-08 | 56 | 2023-07-03 | 2023-06-08 | 38567084.81 | 28925313.53 | 27398639.54 | 94648982.38 | [6 empty] | 9464898.3 | 9464898.3 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.024
DPW - Ph.02 | 5 | 2023-05-31 | 2023-05-25 | 2023-06-03 | 56 | 2023-07-29 | 2023-06-25 | 77833745.07 | 30561302.57 | 30104833.54 | 172482727.45 | [6 empty] | 8624122.5 | 8624122.5 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.025
DPW - Ph.02 | 6 | 2023-06-30 | 2023-06-25 | 2023-06-26 | 56 | 2023-08-21 | 2023-07-31 | 32227821.34 | 24170866.16 | 23809772.84 | 204710548.79 | [6 empty] | 10235527.455 | 10235527.455 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.026
DPW - Ph.02 | 7 | 2023-07-31 | 2023-07-25 | 2023-08-01 | 56 | 2023-09-26 | 2023-08-28 | 21546507.22 | 16159880.26 | 15918348.27 | 226257056.01 | [6 empty] | 11312852.785 | 11312852.785 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.027
DPW - Ph.02 | 8 | 2023-08-31 | 2023-08-25 | 2023-09-04 | 56 | 2023-10-30 | 2023-09-04 | 27781672.69 | 20836254.44 | 20524928.94 | 254038728.7 | [6 empty] | 12701936.435 | 12701936.435 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.028
DPW - Ph.02 | 9 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 56 | 2023-11-28 | 2023-10-31 | 66926760.56 | 50195070.42 | 49445572.72 | 320965489.26 | [6 empty] | 16048266 | 16048266 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.029
DPW - Ph.02 | 10 | 2023-10-31 | 2023-10-25 | 2023-11-01 | 56 | 2023-12-27 | 2023-11-29 | 59028304.35 | 44271228.34 | 34610141.8 | 379993793.61 | [6 empty] | 18999683 | 18999683 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.0210
DPW - Ph.02 | 11 | 2023-11-30 | 2023-11-25 | 2023-11-30 | 56 | 2024-01-25 | 2023-12-31 | 54711779.1 | 40849045.03 | 40236573.85 | 434705572.71 | [6 empty] | 21735278.62 | 21735278.62 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.0211
DPW - Ph.02 | 12 | 2023-12-31 | 2023-12-25 | 2024-01-01 | 56 | 2024-02-26 | 2024-02-04 | 17644384.08 | 15879945.92 | 15678173.8779 | 452349956.79 |  |  |  | 25824647.96 |  |  | 22617497.855 | 22617497.855 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.0212
DPW - Ph.02 | 13 | 2024-02-29 | 2024-03-09 | 2024-03-09 | 56 | 2024-05-04 | 2024-04-01 | 13655091.11 | 18632592.11 | 18805485.48 | 466005047.9 |  |  |  | 44215690.5 |  |  | 33822947.025 | 33822947.025 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.0213
DPW - Ph.02 | 14 | 2024-02-29 | 2024-03-10 | 2024-03-13 | 56 | 2024-05-08 | 2024-05-14 | -0.0001 | 35418927.4 | 35568315.9 | 466005047.9 |  |  |  | 30459697.9 |  |  | 23300252.395 | 23300252.395 | 0 | DP World Basin 2 Ph2 | [7 empty] | DPW - Ph.0214
EGAT Pelletizing Plant | 1 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-15 | 5145072.89 | 4887819.25 | 16605643.54 | 5145072.89 | 10000000 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant1
EGAT Pelletizing Plant | 2 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 10496612.58 | 10124222.67 | 27019256.26 | 15641685.47 | 2000000 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant2
EGAT Pelletizing Plant | 3 | 2021-07-31 | 2021-07-31 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 4383722.29 | 4165165.88 | 59114716.8 | 20025407.76 | 5000000 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant3
EGAT Pelletizing Plant | 4 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-27 | 6320391.6 | 6104444.17 | 50190590.75 | 26345799.36 | 20500000 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant4
EGAT Pelletizing Plant | 5 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-20 | 14624189 | 14109093.06 | 142794796.93 | 40969988.36 | 28804143.3 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant5
EGAT Pelletizing Plant | 6 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-14 | 11102739.54 | 10385277.48 | 160253665.39 | 52072727.9 | 100000000 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant6
EGAT Pelletizing Plant | 7 | 2021-11-30 | 2021-12-05 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-20 | 14005522.66 | 13304274.45 | 163147791.3 | 66078250.56 | 100000000 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant7
EGAT Pelletizing Plant | 8 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-18 | 12121253.25 | 11576342.49 | 241455129.95 | 78199503.81 | 200000000 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant8
EGAT Pelletizing Plant | 9 | 2022-01-31 | 2022-02-05 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 15797419.96 | 15046421.2 | 71197856.25 | 93996923.77 | 26309409.25 | [7 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant9
EGAT Pelletizing Plant | 10 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-04-12 | 13671163.11 | 13017478.47 | 41034098.6 | 107668086.88 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant10
EGAT Pelletizing Plant | 11 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-21 | 14893958.07 | 14300826.37 | 34151886.79 | 122562044.95 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant11
EGAT Pelletizing Plant | 12 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-23 | 8116943.05 | 7722438.9 | 23500000 | 130678988 |  |  |  | 5987660 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant12
EGAT Pelletizing Plant | 13 | 2022-05-31 | 2022-06-05 | 2022-06-12 | 42 | 2022-07-24 | 2022-07-05 | 13958441.79 | 13285393.01 | 53397068.58 | 144637429.79 |  |  |  | 6236391 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant13
EGAT Pelletizing Plant | 14 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-23 | 8283062.84 | 7877469.99 | 17794639.63 | 152920492.63 |  |  |  | 6321993.82 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant14
EGAT Pelletizing Plant | 15 | 2022-07-31 | 2022-08-10 | 2022-08-15 | 42 | 2022-09-26 | 2022-08-24 | 20298475.01 | 19389514.84 | 29186530.1 | 173218967.64 |  |  |  | 7381629.61 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant15
EGAT Pelletizing Plant | 16 | 2022-08-31 | 2022-09-10 | 2022-09-20 | 42 | 2022-11-01 | 2022-10-10 | 14282809.35 | 14238994.72 | 23336148.65 | 187501776.99 |  |  |  | 14084887.93 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant16
EGAT Pelletizing Plant | 17 | 2022-10-31 | 2022-10-25 | 2022-10-27 | 42 | 2022-12-08 | 2022-11-23 | 16943574.98 | 16138518.46 | 39257376.65 | 204445351.97 |  |  |  | 14506110.34 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant17
EGAT Pelletizing Plant | 18 | 2022-11-30 | 2022-11-20 | 2022-11-24 | 42 | 2023-01-05 | 2022-12-19 | 13727755.25 | 12845007.22 | 35000000 | 218173107.22 |  |  |  | 14925857.7 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant18
EGAT Pelletizing Plant | 19 | 2022-12-31 | 2022-12-27 | 2022-12-27 | 42 | 2023-02-07 | 2023-02-14 | 20329650.19 | 19373062.69 | 42197351.2 | 238502757.41 |  |  |  | 15524807.77 |  |  |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant19
EGAT Pelletizing Plant | 20 | 2023-03-31 | 2023-03-30 | 2023-03-30 | 42 | 2023-05-11 |  |  |  | 40000000 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant20
EGAT Pelletizing Plant | 21 | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 |  |  |  | 20000000 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant21
EGAT Pelletizing Plant | 22 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 |  |  |  | 50000000 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant22
EGAT Pelletizing Plant | 23 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 165505167.47 | 284426280.45 | 15000000 | 533590339.98 |  |  |  | 85167648 |  | 7000000 |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant23
EGAT Pelletizing Plant | 24 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 65988515.57 | 38934626.46 | 10000000 | 599578855.55 |  |  |  | 96518287.15 |  | 7000000 |  |  | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant24
EGAT Pelletizing Plant | 25 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 |  |  |  | 10000000 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant25
EGAT Pelletizing Plant - Admin Building | 1 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 61566718.68 | 27089356.22 | 0 | 61566718.68 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant - Admin Building1
EGAT Pelletizing Plant - Admin Building | 2 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 53673231.5 | 23616221.86 | 0 | 115239950.18 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant - Admin Building2
EGAT Pelletizing Plant - Admin Building | 3 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 |  |  |  | 0 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant - Admin Building3
EGAT Pelletizing Plant - Supply | 1 | 2023-07-31 | 2023-07-26 | 2023-07-26 | 42 | 2023-09-06 | 2023-07-26 | 1390180.36 | 1584805.61 | 1570903.44 | 1390180.36 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant - Supply1
EGAT Pelletizing Plant-Concrete Infra | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Concrete Infra1
EGAT Pelletizing Plant-Mechanical Installation | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Mechanical Installation1
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-01-31 |  |  | 42 | 1900-02-10 |  |  |  | 0 | [10 empty] | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Mechanical Installation
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-02-29 |  |  | 42 | 1900-02-10 |  |  |  | 0 | [10 empty] | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Mechanical Installation
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-03-31 |  |  | 42 | 1900-02-10 |  |  |  | 0 | [10 empty] | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Mechanical Installation
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-04-30 |  |  | 42 | 1900-02-10 |  |  |  | 0 | [10 empty] | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Mechanical Installation
EGAT Pelletizing Plant-MEP | 1 | 2021-04-30 | 2021-04-30 | 2021-05-11 | 42 | 2021-06-22 | 2021-08-25 | 2011978.5 | 2112577.42 | 1e-05 | 2011978.5 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-MEP1
EGAT Pelletizing Plant-MEP | 2 | 2022-02-28 | 2022-02-22 | 2022-02-24 | 42 | 2022-04-07 | 2022-02-22 | 112937.5 | 118584.38 | 1e-05 | 2124916 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-MEP2
EGAT Pelletizing Plant-MEP | 3 | 2022-05-31 | 2022-06-05 | 2022-06-06 | 42 | 2022-07-18 | 2023-02-12 | 1723067.19 | 1329462.73 | 1e-05 | 3847983.19 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-MEP3
EGAT Pelletizing Plant-MEP Coordination | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-MEP Coordination1
EGAT Pelletizing Plant-Water Tank | 1 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-22 | 3274479.04 | 3438202.99 | 3241734.16 | 3274479.04 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank1
EGAT Pelletizing Plant-Water Tank | 2 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 2028589.79 | 2130019.28 | 2008304.1 | 5303068.83 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank2
EGAT Pelletizing Plant-Water Tank | 3 | 2021-07-31 | 2021-08-04 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 725357.85 | 761625.75 | 718104.27 | 6028426.68 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank3
EGAT Pelletizing Plant-Water Tank | 4 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-05 | 766173.48 | 804482.15 | 758512.36 | 6794600.16 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank4
EGAT Pelletizing Plant-Water Tank | 5 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-12 | 923594.34 | 969774.05 | 914358.66 | 7718194.5 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank5
EGAT Pelletizing Plant-Water Tank | 6 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-09 | 1464316.6 | 1537532.43 | 1449673.43 | 9182511.1 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank6
EGAT Pelletizing Plant-Water Tank | 7 | 2021-11-30 | 2021-12-06 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-09 | 399729.3 | 419715.76 | 395732.02 | 9582240.4 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank7
EGAT Pelletizing Plant-Water Tank | 8 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-06 | 307226.2 | 322587.51 | 304153.94 | 9889466.6 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank8
EGAT Pelletizing Plant-Water Tank | 9 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-03-02 | 1064224 | 1117435.2 | 967200 | 10953690.6 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank9
EGAT Pelletizing Plant-Water Tank | 10 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-14 | 3540729.8 | 3717766.29 | 3505322.5 | 14494420.4 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank10
EGAT Pelletizing Plant-Water Tank | 11 | 2022-03-31 | 2022-03-05 | 2022-06-06 | 42 | 2022-07-18 | 2022-08-23 | 3753750.32 | 3941437.84 | 3903900.34 | 18248170.72 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank11
EGAT Pelletizing Plant-Water Tank | 12 | 2022-09-30 | 2022-09-15 | 2022-09-19 | 42 | 2022-10-31 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank12
EGAT Pelletizing Plant-Water Tank | 13 | 2022-10-31 | 2022-10-10 | 2022-11-01 | 42 | 2022-12-13 |  |  |  | 391272.95 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank13
EGAT Pelletizing Plant-Water Tank | 14 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank14
EGAT Pelletizing Plant-Water Tank | 15 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 0.19 | 2909387.53 | 0 | 21082133.03 | [8 empty] | 0 | EGAT Pelletizing Plant | [7 empty] | EGAT Pelletizing Plant-Water Tank15
EGAT-Asphalt | 1 | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 |  |  |  | 598688 | [10 empty] | 0 | [7 empty] | EGAT-Asphalt1
EGAT-Fence | 1 | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 |  |  |  | 195752.6 | [10 empty] | 0 | [7 empty] | EGAT-Fence1
EGAT-Fence | 2 | 2019-08-31 | 2019-08-31 | 2019-09-10 | 15 | 2019-09-25 | 2019-10-08 | -616810.92 | -575046.5692 | 0.001 | 18362278.12 | [9 empty] | 0 | [7 empty] | EGAT-Fence2
EGAT-Fence | 3 | 2019-09-30 | 2019-09-30 | 2019-10-14 | 15 | 2019-10-29 |  |  |  | 695045.6828 | [10 empty] | 0 | [7 empty] | EGAT-Fence3
EGAT-Fence | 4 | 2019-10-31 | 2019-12-19 | 2020-02-09 | 15 | 2020-02-24 |  |  |  | 2891036.0622 | [10 empty] | 0 | [7 empty] | EGAT-Fence4
EGAT-HeliPad | 1 | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16 |  |  |  | 755798.13 | [10 empty] | 0 | [7 empty] | EGAT-HeliPad1
EGAT-HeliPad | 2 | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20 |  |  |  | 500000 | [10 empty] | 0 | [7 empty] | EGAT-HeliPad2
EGAT-Lock & Load | 1 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 5018202.5 | 4767292.38 | 10117110.35 | 5018202.5 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load1
EGAT-Lock & Load | 2 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-06 | 2362059.16 | 2243956.2 | 2773213.88 | 7380261.66 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load2
EGAT-Lock & Load | 3 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-12 | 1772326.51 | 1683710.18 | 1665986.92 | 9152588.17 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load3
EGAT-Lock & Load | 4 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 |  |  |  | 747255.39 | [9 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load4
EGAT-Lock & Load | 5 | 2022-05-31 | 2022-05-28 | 2022-06-06 | 42 | 2022-07-18 | 2022-06-07 | 3180176.34 | 3021167.52 | 2436487.51 | 13211888.51 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load5
EGAT-Lock & Load | 6 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-07-06 | 3378839.59 | 3209897.61 | 3176089.21 | 16590728.1 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load6
EGAT-Lock & Load | 7 | 2022-07-31 | 2022-08-10 | 2022-08-16 | 42 | 2022-09-27 | 2022-08-16 | 1415984.07 | 1345184.87 | 1319107.49 | 18006712.17 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load7
EGAT-Lock & Load | 8 | 2022-08-31 | 2022-09-10 | 2022-09-11 | 42 | 2022-10-23 | 2022-09-11 | 2786604.1 | 2647273.89 | 2619387.85 | 20793316.27 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load8
EGAT-Lock & Load | 9 | 2022-09-30 | 2022-09-10 | 2022-10-17 | 42 | 2022-11-28 | 2022-10-18 | 3980460.75 | 3781437.71 | 3741613.11 | 24773777.02 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load9
EGAT-Lock & Load | 10 | 2022-10-31 | 2022-10-31 | 2022-11-01 | 42 | 2022-12-13 | 2022-11-03 | 1157252.56 | 1099389.93 | 1099389.93 | 25931029.58 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load10
EGAT-Lock & Load | 11 | 2022-11-30 | 2022-11-30 | 2022-11-30 | 42 | 2023-01-11 | 2022-12-07 | 1992889.65 | 1893245.16 | 1873296.27 | 27923919.23 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load11
EGAT-Lock & Load | 12 | 2022-12-31 | 2022-12-25 | 2022-12-28 | 42 | 2023-02-08 | 2022-12-28 | 1778896.47 | 1689951.65 | 1672142.68 | 29702815.7 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load12
EGAT-Lock & Load | 13 | 2023-01-31 | 2023-01-31 | 2023-02-01 | 42 | 2023-03-15 | 2023-02-07 | 2116780.43 | 2010941.41 | 1e-05 | 31819596.13 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load13
EGAT-Lock & Load | 14 | 2023-02-28 | 2023-02-28 | 2023-03-02 | 42 | 2023-04-13 | 2023-03-08 | 2768145.62 | 2629738.34 | 1e-05 | 34587741.75 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load14
EGAT-Lock & Load | 15 | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load15
EGAT-Lock & Load | 16 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load16
EGAT-Lock & Load | 17 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-02-28 | -100000 | 18153522.75 | 0 | 53900000 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load17
EGAT-Lock & Load | 18 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 1100000 | 1134000 | 0 | 55000000 | [8 empty] | 0 | EGAT Lock & Load | [7 empty] | EGAT-Lock & Load18
EGAT-SZ | 1 | 2019-03-31 | 2019-03-27 | 2019-03-27 | 15 | 2019-04-11 | 2019-04-01 | 6085108 | 4624356.65 | 4624356.65 | 6085108 | [9 empty] | 0 | [7 empty] | EGAT-SZ1
EGAT-SZ | 2 | 2019-03-31 | 2019-04-10 | 2019-04-03 | 15 | 2019-04-18 |  |  |  | 10000000 | [10 empty] | 0 | [7 empty] | EGAT-SZ2
EGAT-SZ | 3 | 2019-06-30 | 2019-06-26 | 2019-08-01 | 15 | 2019-08-16 |  |  |  | 6070502.71 | [10 empty] | 0 | [7 empty] | EGAT-SZ3
EGAT-Warehouse | 1 | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20 |  |  |  | 923651.335 | [10 empty] | 0 | [7 empty] | EGAT-Warehouse1
EIPICO | 1 | 2022-11-30 | 2022-11-25 | 2022-12-19 | 35 | 2023-01-23 | 2022-12-25 | 9332911.16 | 12050858.57 | 180532933.37 | 9332911.16 | 83482074.8 |  | 2859252.04 | 393834.3 |  |  | 304804.08 | 304804.08 | 0 | EPICO 3 Facility | [7 empty] | EIPICO1
EIPICO | 2 | 2022-12-31 | 2022-12-25 | 2022-12-27 | 35 | 2023-01-31 | 2023-02-20 | 13142288.21 | 13338534.97 | 23338534.97 | 22475199.37 |  |  | 3204166.92 | 795852.42 |  |  | 641984.155 | 641984.155 | 0 | EPICO 3 Facility | [7 empty] | EIPICO2
EIPICO | 3 | 2023-01-31 | 2023-01-25 | 2023-02-12 | 35 | 2023-03-19 | 2023-03-14 | 11426647.21 | 13033884.61 | 13033885 | 33901846.58 |  |  | 4910817.01 | 1876208.86 |  | 611410.75 | 847546.165 | 847546.165 | 0 | EPICO 3 Facility | [7 empty] | EIPICO3
EIPICO | 4 | 2023-02-28 | 2023-02-28 | 2023-02-27 | 35 | 2023-04-03 | 2023-03-15 | 8374674.1725 | 7345011.2 | 7344659 | 42276520.7525 |  |  | 6456809.6644 | 3032593.7925 |  | 611410.7518 | 1056913.015 | 1056913.015 | 0 | EPICO 3 Facility | [7 empty] | EIPICO4
EIPICO | 5 | 2023-03-31 | 2023-03-31 | 2023-03-28 | 35 | 2023-05-02 | 2023-04-10 | 13210447.2775 | 10066271.07 | 10064340.12 | 55486968.03 |  |  | 6862783.17 | 3640633.73 |  | 4882891.89 | 1387174.2 | 1387174.2 | 0 | EPICO 3 Facility | [7 empty] | EIPICO5
EIPICO | 6 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 35 | 2023-06-05 | 2023-05-17 | 6910722.77 | 5949977.84 | 5949568.74 | 62397690.8 |  |  | 8009743.26 | 3788186.81 |  | 4882891.89 | 1559942.27 | 1559942.27 | 0 | EPICO 3 Facility | [7 empty] | EIPICO6
EIPICO | 7 | 2023-05-31 | 2023-05-30 | 2023-06-13 | 35 | 2023-07-18 | 2023-07-16 | 1928406.33 | 6395645.73 | 6395645.73 | 64326097.13 |  |  | 8718966.12 | 6026736.54 |  | 4882891.89 | 1758820.84 | 1758820.84 | 0 | EPICO 3 Facility | [7 empty] | EIPICO7
EIPICO | 8 | 2023-06-30 | 2023-06-30 | 2023-07-06 | 35 | 2023-08-10 | 2023-08-31 | 24151774.29 | 20317361.34 | 20317361.34 | 88477871.42 |  |  | 17971072.1 | 8593156.6 |  | 15010831.83 | 2211946.785 | 2211946.785 | 0 | EPICO 3 Facility | [7 empty] | EIPICO8
EIPICO | 9 | 2023-07-31 | 2023-07-31 | 2023-08-02 | 35 | 2023-09-06 | 2023-08-22 | 35000000 | 34650000 | 34650000 | 123477871.42 |  |  | 17971072.1 | 43593156.6 |  | 15010831.83 | 3086946.785 | 3086946.785 | 0 | EPICO 3 Facility | [7 empty] | EIPICO9
EIPICO | 10 | 2023-07-31 | 2023-07-31 | 2023-08-28 | 35 | 2023-10-02 | 2023-10-29 | 9818518.79 | 6328465.78 | 1e-05 | 133296390.21 |  |  | 16843609 | 47694027.06 |  | 15663610.71 | 3332409.755 | 3332409.755 | 0 | EPICO 3 Facility | [7 empty] | EIPICO10
EIPICO | 11 | 2023-09-30 | 2023-09-30 | 2023-10-10 | 35 | 2023-11-14 | 2023-11-28 | 27259074.64 | 30654533.46 | 23263190.12 | 160555464.85 |  |  | 30897743.79 | 49443090.43 |  | 24919582.39 | 4013886.62 | 4013886.62 | 0 | EPICO 3 Facility | [7 empty] | EIPICO11
EIPICO | 12 | 2023-10-31 | 2023-10-31 | 2023-10-29 | 35 | 2023-12-03 | 2024-01-02 | 13086699.85 | 25548194.95 | 25548194.95 | 173642164.7 |  |  | 56153346.77 | 51092750.03 |  | 24919582.39 | 4341054.12 | 4341054.12 | 0 | EPICO 3 Facility | [7 empty] | EIPICO12
EIPICO | 13 | 2023-11-30 | 2023-11-30 | 2023-12-03 | 35 | 2024-01-07 | 2024-01-01 | 50645327.08 | 3870916.75 | 2882568.41 | 224287491.78 |  |  | 34066592.92 | 51710056.53 |  | 25596151.45 | 5607188.795 | 5607188.795 | 1e-05 | EPICO 3 Facility | [7 empty] | EIPICO13
EIPICO | 14 | 2023-12-31 | 2023-12-31 | 2024-01-06 | 35 | 2024-02-10 | 2024-03-07 | 69127504.85 | 26305980.07 | 26305980.07 | 293414996.63 |  |  | 36975442.25 | 57799027.37 |  | 60908341.96 | 7335374.915 | 7335374.915 | 0 | EPICO 3 Facility | [7 empty] | EIPICO14
EIPICO | 15 | 2024-01-31 | 2024-01-31 | 2024-02-04 | 35 | 2024-03-10 | 2024-03-20 | 41894786.25 | 29236256.02 | 29236256.89 | 335309782.88 |  |  | 34393385.98 | 69350170.39 |  | 63104446.32 | 8382744.57 | 8382744.57 | 0 | EPICO 3 Facility | [7 empty] | EIPICO15
EIPICO | 16 | 2024-03-31 | 2024-03-31 | 2024-04-03 | 35 | 2024-05-08 | 2024-04-24 | 54812520.11 | 26365248.98 | 26363887.4 | 390122302.99 |  |  | 33031508.83 | 74589819.54 |  | 94064398.16 | 9753057.575 | 9753057.575 | 0 | EPICO 3 Facility | [7 empty] | EIPICO16
EIPICO | 17 | 2024-04-30 | 2024-04-30 | 2024-05-28 | 35 | 2024-07-02 | 2024-06-13 | 30260072.01 | 13161378 | 13161378.75 | 420382375 |  |  | 32932557 | 81926235 |  | 110270621 | 10518279.5 | 10518279.5 | 0 | EPICO 3 Facility | [7 empty] | EIPICO17
EIPICO | 18 | 2024-06-30 | 2024-06-30 | 2024-07-15 | 35 | 2024-08-19 | 2024-07-30 | 61471115.83 | 38010351.15 | 35188037.3 | 481853490.83 |  |  | 27876972.92 | 86364959.21 |  | 143970319.09 | 12046337.27 | 12046337.27 | 0 | EPICO 3 Facility | [7 empty] | EIPICO18
EIPICO | 19 | 2024-08-31 | 2024-08-31 | 2024-09-03 | 35 | 2024-10-08 | 2024-10-26 | 35463786.17 | 22436578.36 | 22436578.36 | 517317277 |  |  | 23341078 | 95950976 |  | 145234855 | 12932931.5 | 12932931.5 | 17754935 | EPICO 3 Facility | [7 empty] | EIPICO19
EIPICO | 20 | 2024-09-30 | 2024-09-30 | 2024-10-29 | 35 | 2024-12-03 |  |  |  | 20000000 | [9 empty] | 0 | EPICO 3 Facility | [7 empty] | EIPICO20
El Sewedy Uni.-PKG.1 | 1 | 2018-07-31 | 2018-08-31 | 2018-09-03 | 4 | 2018-10-19 | 2018-10-15 | 2762087.0381 | 2002513.1 | 1917993.24 | 2762087.0381 |  |  | 0 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.11
El Sewedy Uni.-PKG.1 | 2 | 2018-09-30 | 2018-10-15 | 2018-10-18 | 4 | 2018-10-29 | 2018-10-25 | 1370079.6319 | 951383.3 | 881744.36 | 4132166.67 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.12
El Sewedy Uni.-PKG.1 | 3 | 2018-10-31 | 2018-11-15 | 2018-11-14 | 4 | 2018-12-01 | 2018-11-27 | 1749696.33 | 1214989.1272 | 1214989 | 5881863 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.13
El Sewedy Uni.-PKG.1 | 4 | 2018-11-30 | 2018-11-30 | 2018-12-02 | 4 | 2018-12-14 | 2018-12-10 | 1734033.5 | 1204112.8596 | 1204112.8596 | 7615896.5 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.14
El Sewedy Uni.-PKG.1 | 5 | 2018-12-31 | 2018-12-15 | 2018-12-17 | 4 | 2018-12-22 | 2018-12-18 | 267331.59 | 185635.0557 | 185635.0557 | 7883228.09 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.15
El Sewedy Uni.-PKG.1 | 6 | 2018-12-31 | 2018-12-25 | 2018-12-29 | 4 | 2019-01-12 | 2019-01-08 | 205504.28 | 142702.1677 | 142702.12 | 8088732.37 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.16
El Sewedy Uni.-PKG.1 | 7 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 4 | 2019-01-26 | 2019-01-22 | 410253.12 | 284879.76 | 284879.77 | 8498985.49 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.17
El Sewedy Uni.-PKG.1 | 8 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 4 | 2019-02-10 | 2019-02-06 | 339720.12 | 235901.6556 | 235901.48 | 8838705.61 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.18
El Sewedy Uni.-PKG.1 | 9 | 2019-03-31 | 2019-03-25 | 2019-03-26 | 4 | 2019-04-14 | 2019-04-10 | 104805.89 | 72777.3 | 72777.3 | 8943511.5 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.19
El Sewedy Uni.-PKG.1 | 10 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 4 | 2019-08-11 | 2019-08-07 | 2360 | -8913.92 | -8913.92 | 8945871.5 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.110
El Sewedy Uni.-PKG.2 | 1 | 2018-09-30 | 2018-09-25 | 2018-09-27 | 17 | 2018-10-14 | 2018-10-18 | 4165158.06 | 3110956.56 | 3110956.56 | 4165158.06 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.21
El Sewedy Uni.-PKG.2 | 2 | 2018-10-31 | 2018-10-31 | 2018-10-31 | 17 | 2018-11-17 | 2018-11-08 | 5976536.23 | 6088678.96 | 6754267.57 | 10141694.29 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.22
El Sewedy Uni.-PKG.2 | 3 | 2018-11-30 | 2018-11-25 | 2018-11-27 | 17 | 2018-12-14 | 2018-12-10 | 4458367.3606 | 3212953.6168 | 3212953.45 | 14600061.6506 |  |  | 2173392 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.23
El Sewedy Uni.-PKG.2 | 4 | 2018-12-31 | 2018-12-25 | 2018-12-31 | 17 | 2019-01-17 | 2019-01-10 | 5121900.2295 | 3208255.2815 | 3208255.76 | 19721961.8801 |  |  | 1556100 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.24
El Sewedy Uni.-PKG.2 | 5 | 2019-01-31 | 2019-01-25 | 2019-01-31 | 17 | 2019-02-17 | 2019-02-10 | 8018043.8084 | 4527299.6695 | 4527299.68 | 27740005.6885 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.25
El Sewedy Uni.-PKG.2 | 6 | 2019-02-28 | 2019-02-25 | 2019-03-02 | 17 | 2019-03-19 | 2019-03-11 | 8105230.8115 | 7457797.2 | 7457797.24 | 35845236.5 |  |  | 1404000 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.26
El Sewedy Uni.-PKG.2 | 7 | 2019-03-31 | 2019-03-25 | 2019-04-08 | 17 | 2019-04-25 | 2019-04-10 | 4929812 | 2278076.6 | 2278076.64 | 40775048.5 |  |  | 0 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.27
El Sewedy Uni.-PKG.2 | 8 | 2019-05-31 | 2019-05-23 | 2019-05-23 | 17 | 2019-06-09 | 2019-08-07 | 1755356.8 | 2625161.5 | 2625161.63 | 42530405.3 | [8 empty] | 50000 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.28
El Sewedy Uni.-PKG.2 | 9 | 2020-03-31 | 2020-07-31 | 2020-03-22 |  | 2020-03-31 | 2020-03-23 | 0 | 1116423.1 | 1116423 | 42530405.3 | [8 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.29
El Sewedy Uni.-PKG.3 | 1 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 14 | 2019-02-14 | 2019-02-18 | 1805053.3662 | 1727255.5662 | 41698321.35 | 1805053.3662 | 24971065.75 | 15000000 | [6 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.31
El Sewedy Uni.-PKG.3 | 2 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 14 | 2019-02-16 | 2019-02-19 | 3340179.702 | 3185421.0011 | 11185421.17 | 3340179.702 | 8000000 | [7 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.32
El Sewedy Uni.-PKG.3 | 3 | 2019-02-28 | 2019-02-21 | 2019-02-27 | 14 | 2019-03-13 | 2019-03-12 | 2400436.8318 | 5785718.6 | 17785718.63 | 7545669.9 | 12000000 |  | 3477943.8 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.33
El Sewedy Uni.-PKG.3 | 4 | 2019-03-31 | 2019-03-21 | 2019-03-24 | 14 | 2019-04-07 | 2019-04-10 | 6026842.9 | 1785483.1 | 6716669.76 | 13572512.8 | 4931187 |  | 4077447.9 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.34
El Sewedy Uni.-PKG.3 | 5 | 2019-04-30 | 2019-04-21 | 2019-04-23 | 14 | 2019-05-07 | 2019-05-05 | 27458064.6 | 24218860.6 | 24218860.6 | 41030577.4 |  |  | 16291927.3 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.35
El Sewedy Uni.-PKG.3 | 6 | 2019-05-31 | 2019-05-25 | 2019-06-01 | 14 | 2019-06-15 | 2019-06-16 | 30765208.3 | 26656864.3 | 26716091.61 | 71795785.7 |  |  | 10815243.6 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.36
El Sewedy Uni.-PKG.3 | 7 | 2019-06-30 | 2019-07-04 | 2019-07-08 | 14 | 2019-07-22 | 2019-07-25 | 41332921.1 | 22410862.51 | 22410862.51 | 113128706.8 |  |  | 20405227.9 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.37
El Sewedy Uni.-PKG.3 | 8 | 2019-07-31 | 2019-07-31 | 2019-08-08 | 14 | 2019-08-22 | 2019-08-24 | 23588218.3 | 13598061.6 | 12292368.36 | 136716925.1 |  |  | 16590818.6 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.38
El Sewedy Uni.-PKG.3 | 9 | 2019-08-31 | 2019-08-21 | 2019-08-24 | 14 | 2019-09-07 | 2019-08-28 | 30130968 | 19410255.3 | 19287810.69 | 166847893.1 |  |  | 4696608.5 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.39
El Sewedy Uni.-PKG.3 | 10 | 2019-08-31 | 2019-09-10 | 2019-09-16 | 14 | 2019-09-30 | 2019-09-29 | 28039187.7 | 20919758.8 | 20919758.8 | 194887080.8 |  |  | 1904733.1 | [5 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.310
El Sewedy Uni.-PKG.3 | 11 | 2019-10-31 | 2019-10-31 | 2019-12-22 | 14 | 2020-01-05 | 2020-01-01 | 16304632.1 | 2318168.2 | 2318161.39 | 211191712.9 | [8 empty] | 3221774.75 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.311
El Sewedy Uni.-PKG.3 | 12 | 2019-10-31 | 2019-10-31 | 2020-06-08 | 14 | 2020-06-22 | 2020-06-21 | 0 | 1515470 | 1515470 | 211191712.9 | [8 empty] | 1706304.8 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.312
El Sewedy Uni.-PKG.3 | 13 | 2020-09-30 | 2020-09-17 | 2020-11-15 | 14 | 2020-11-29 |  |  |  | 6845790.3 | [9 empty] | 0 | Elsewedy Univ - Enabling Works | [7 empty] | El Sewedy Uni.-PKG.313
Elco Steel | 1 | 2017-09-30 | 2017-10-01 | 2017-10-01 | 15 | 2017-10-16 | 2017-10-08 | 17022109.47 | 13617687.58 | 13532577.04 | 17022109.47 | [8 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel1
Elco Steel | 2 | 2017-10-31 | 2017-10-25 | 2017-10-25 | 15 | 2017-11-09 | 2017-10-29 | 54045554.24 | 42881105.07 | 42881105.07 | 71067663.71 | [8 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel2
Elco Steel | 3 | 2017-11-30 | 2017-11-30 | 2017-11-27 | 15 | 2017-12-12 | 2017-11-28 | 68968024.81 | 54829579.72 | 54829579.72 | 140035688.52 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel3
Elco Steel | 4 | 2017-12-31 | 2017-12-31 | 2017-12-27 | 15 | 2018-01-11 | 2018-01-02 | 45198074.67 | 35932469.36 | 35932469.35 | 185233763.18 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel4
Elco Steel | 5 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 15262763.5 | 12133896.98 | 12038252.26 | 200496526.68 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel5
Elco Steel | 6 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 23107300.22 | 19914658.95 | 20100303 | 223603826.9 |  |  | 0 | [5 empty] | 95644.72 | Substation Elco Steel | [7 empty] | Elco Steel6
Elco Steel | 7 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 9962100.82 | 7919870.15 | 7919870.17 | 233565927.72 |  |  | 0 | [5 empty] | 95644.72 | Substation Elco Steel | [7 empty] | Elco Steel7
Elco Steel | 8 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 7984975.64 | 6348055.64 | 6348055.64 | 241550903.36 |  |  | 0 | [5 empty] | 95644.72 | Substation Elco Steel | [7 empty] | Elco Steel8
Elco Steel | 9 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 1027177.94 | 740665.1 | 740665.09 | 242578081.3 |  |  | 0 | [5 empty] | 171586.08 | Substation Elco Steel | [7 empty] | Elco Steel9
Elco Steel | 10 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 5032217.21 | 4000612.68 | 4000000 | 247610298.51 |  |  | 0 | [5 empty] | 171586.08 | Substation Elco Steel | [7 empty] | Elco Steel10
Elco Steel | 11 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 8902176.76 | 7077230.5163 | 7075101.66 | 256512475.27 |  |  | 0 | [5 empty] | 171586.08 | Substation Elco Steel | [7 empty] | Elco Steel11
Elco Steel | 12 | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 |  |  |  | 2485656 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel12
Elco Steel | 13 | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 |  |  |  | 2518616.18 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel13
Elco Steel | 14 | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 |  |  |  | 2857649.27 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel14
Elco Steel | 15 | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 |  |  |  | 1595365.5 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel15
Elco Steel | 16 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 |  |  |  | 310509.31 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel16
Elco Steel | 17 | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 |  |  |  | 1079101.72 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel17
Elco Steel - ADMIN. | 1 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 1576783.88 | 1253543.1806 | 1253543.1806 | 1576783.88 | [8 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.1
Elco Steel - ADMIN. | 2 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 3644932.88 | 2897721.64 | 2897721.63 | 5221716.76 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.2
Elco Steel - ADMIN. | 3 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 4011218.17 | 3188918.45 | 3188918.44 | 9232934.93 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.3
Elco Steel - ADMIN. | 4 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 4549688.44 | 3617002.31 | 3617002.31 | 13782623.37 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.4
Elco Steel - ADMIN. | 5 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 2288094.62 | 1819035.23 | 1819035.22 | 16070717.99 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.5
Elco Steel - ADMIN. | 6 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 6362324.03 | 5094386.24 | 5058047.58 | 22433042.02 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.6
Elco Steel - ADMIN. | 7 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 7233482.49 | 5750618.5816 | 5750618.5816 | 29666524.51 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.7
Elco Steel - ADMIN. | 8 | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 |  |  |  | 3289926.92 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.8
Elco Steel - ADMIN. | 9 | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 |  |  |  | 1940428 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.9
Elco Steel - ADMIN. | 10 | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 |  |  |  | 2335545.55 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.10
Elco Steel - ADMIN. | 11 | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 |  |  |  | 2179703.08 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.11
Elco Steel - ADMIN. | 12 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 |  |  |  | 1394236.8 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.12
Elco Steel - ADMIN. | 13 | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 |  |  |  | 117652.86 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.13
Elco Steel - ADMIN. | 14 | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 |  |  |  | 105992.48 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.14
Elco Steel - ADMIN. | 15 | 2019-03-31 | 2019-04-10 | 2019-04-16 | 15 | 2019-05-01 |  |  |  | 259861.3 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - ADMIN.15
Elco Steel - MEP | 1 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 444736.0027 | 331328.322 | 331328.322 | 444736.0027 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP1
Elco Steel - MEP | 2 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 2764965.97 | 2059899.65 | 2059899.63 | 3209701.97 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP2
Elco Steel - MEP | 3 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 2666446.92 | 1986502.96 | 1986502.95 | 5876148.87 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP3
Elco Steel - MEP | 4 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 3362790.38 | 2505278.83 | 2505278.83 | 9238939.25 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP4
Elco Steel - MEP | 5 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 3275304.26 | 2440101.69 | 2440101.67 | 12514243.51 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP5
Elco Steel - MEP | 6 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 2863596.99 | 2133379.78 | 2133379.76 | 15377840.5 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP6
Elco Steel - MEP | 7 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 3498188.3161 | 2606150.307 | 2606150.307 | 18876028.8161 |  |  | 0 | [5 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP7
Elco Steel - MEP | 8 | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 |  |  |  | 1980608.55 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP8
Elco Steel - MEP | 9 | 2018-09-30 | 2018-10-09 | 2018-10-10 | 15 | 2018-10-25 |  |  |  | 2178754.66 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP9
Elco Steel - MEP | 10 | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 |  |  |  | 2629432.67 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP10
Elco Steel - MEP | 11 | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 |  |  |  | 1720441.01 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP11
Elco Steel - MEP | 12 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 |  |  |  | 1037321.78 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP12
Elco Steel - MEP | 13 | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 |  |  |  | 388339.4 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP13
Elco Steel - MEP | 14 | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 |  |  |  | 317040.71 | [9 empty] | 0 | Substation Elco Steel | [7 empty] | Elco Steel - MEP14
Elco Steel V.O-Infra. Network | 1 | 2019-06-30 | 2019-07-03 | 2019-07-03 | 15 | 2019-07-18 |  |  |  | 1060000 | [10 empty] | Substation Elco Steel | [7 empty] | Elco Steel V.O-Infra. Network1
El-Gouna | 1 | 2019-09-30 | 2019-10-15 | 2019-11-04 | 21 | 2019-11-25 | 2019-11-24 | 3393576.42 | 2338174.15 | 15952690.6 | 3393576.42 | [8 empty] | 0 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna1
El-Gouna | 2 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 21 | 2019-12-08 | 2019-11-24 | 3546875.03 | 3879736.97 | 3867767.27 | 6940451.45 |  |  | 2084092.99 | [5 empty] | 0 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna2
El-Gouna | 3 | 2019-11-30 | 2019-12-15 | 2019-12-16 | 21 | 2020-01-06 | 2019-12-19 | 4290021.36 | 2286139.86 | 2286139.86 | 11230472.81 |  |  | 1112126.59 | [5 empty] | 10483.55 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna3
El-Gouna | 4 | 2019-12-31 | 2020-01-15 | 2020-01-21 | 21 | 2020-02-11 | 2020-01-21 | 2686069.3 | 2572404.48 | 2572404.48 | 13916542.11 |  |  | 2169673.66 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna4
El-Gouna | 5 | 2020-01-31 | 2020-02-15 | 2020-02-19 | 21 | 2020-03-11 | 2020-02-23 | 3430037.61 | 1815739.6 | 1808595.27 | 17346579.72 |  |  | 1374961.99 | [5 empty] | 10483.55 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna5
El-Gouna | 6 | 2020-02-29 | 2020-03-15 | 2020-03-18 | 21 | 2020-04-08 | 2020-03-18 | 6540676.19 | 4271724.93 | 4246133.4 | 23887255.91 |  |  | 1023807.82 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna6
El-Gouna | 7 | 2020-03-31 | 2020-04-15 | 2020-04-18 | 21 | 2020-05-09 | 2020-04-21 | 3114205.16 | 2145687.36 | 2145687.36 | 27001461.07 |  |  | 1023807.82 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna7
El-Gouna | 8 | 2020-06-30 | 2020-07-01 | 2020-07-05 | 21 | 2020-07-26 | 2020-07-06 | 3250029.8 | 1922134.77 | 1922134.77 | 30251490.87 |  |  | 580535.19 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna8
El-Gouna | 9 | 2020-07-31 | 2020-08-01 | 2020-07-26 | 21 | 2020-08-16 | 2020-07-27 | 1882490 | 1037007.36 | 1030964.27 | 32133980.87 |  |  | 203135.69 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna9
El-Gouna | 10 | 2020-08-31 | 2020-09-01 | 2020-09-05 | 21 | 2020-09-26 | 2020-09-05 | 1889241.5387 | 1180949.3351 | 1173489.52 | 34023222.4087 |  |  | 27898.992 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna10
El-Gouna | 11 | 2020-11-30 | 2020-11-30 | 2020-12-09 | 21 | 2020-12-30 | 2020-12-19 | 881976.7757 | 1788649.6992 | 1750027.3 | 34905199.1844 |  |  | 1741930.488 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna11
El-Gouna | 12 | 2020-11-30 | 2020-11-30 | 2020-12-23 | 21 | 2021-01-13 | 2020-12-23 | -0.0044313 | 2000000 | 1942857.14 | 34905199.18 |  |  | 1741930.49 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna12
El-Gouna | 13 | 2020-12-31 | 2020-12-31 | 2021-01-10 | 21 | 2021-01-31 | 2021-01-12 | 2225492.71 | 1964526.99 | 1951940.18 | 37130691.89 |  |  | 1823017.32 | [5 empty] | 29400.49 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna13
El-Gouna | 14 | 2021-01-31 | 2021-01-31 | 2021-02-14 | 21 | 2021-03-07 | 2021-03-03 | 3901532.2 | 3061707.07 | 3058799.81 | 41032224.09 |  |  | 1836465.31 | [5 empty] | 120415.29 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna14
El-Gouna | 15 | 2021-02-28 | 2021-03-11 | 2021-03-13 | 21 | 2021-04-03 | 2021-04-17 | 4440680.41 | 3011925.18 | 3002136.21 | 45472904.5 |  |  | 1238512.71 | [5 empty] | 120415.29 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna15
El-Gouna | 16 | 2021-03-31 | 2021-04-12 | 2021-04-15 | 21 | 2021-05-06 | 2021-04-27 | 4113209.61 | 3166964.63 | 3166964.63 | 49586114.11 |  |  | 1193051.88 | [5 empty] | 120415.29 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna16
El-Gouna | 17 | 2021-05-31 | 2021-05-31 | 2021-06-03 | 21 | 2021-06-24 | 2021-06-14 | 3640319.41 | 2547089.28 | 2526942.2 | 53226433.52 |  |  | 540181.99 | [5 empty] | 120415.29 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna17
El-Gouna | 18 | 2021-08-31 | 2021-08-26 | 2021-08-26 | 21 | 2021-09-16 | 2021-08-26 | 3384789.31 | 5636285.41 | 5636281.25 | 56611222.83 | [8 empty] | 195708.06 | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna18
El-Gouna - Equip. Rental | 1 | 2019-12-31 | 2019-12-31 | 2019-12-12 | 21 | 2020-01-02 | 2020-02-02 | 80875 | 73813.12 | 73813.12 | 80875 | [9 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Equip. Rental1
El-Gouna - Equip. Rental | 2 | 2020-03-31 | 2020-03-31 | 2020-03-18 | 21 | 2020-04-08 |  |  |  | 16757 | [10 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Equip. Rental2
El-Gouna - Equip. Rental | 3 | 2020-06-30 | 2020-07-09 | 2020-07-09 | 21 | 2020-07-30 |  |  |  | 74100 | [10 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Equip. Rental3
El-Gouna - Equip. Rental | 4 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 21 | 2021-04-21 |  |  |  | 3281.25 | [10 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Equip. Rental4
El-Gouna - Equip. Rental | 5 | 2021-05-31 | 2021-05-24 | 2021-05-24 | 21 | 2021-06-14 | 2021-06-24 | 15000 | 15750 | 15750 | 186362.5 | [9 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Equip. Rental5
El-Gouna - Temp. Fence | 1 | 2019-12-31 | 2020-01-15 | 2020-01-18 | 21 | 2020-02-08 | 2020-03-01 | 409200 | 429660 | 425568 | 409200 | [9 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Temp. Fence1
El-Gouna - Temp. Fence | 2 | 2020-01-31 | 2020-02-15 | 2020-02-23 | 21 | 2020-03-15 |  |  |  | 441526.8 | [10 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Temp. Fence2
El-Gouna - Temp. Fence | 3 | 2020-05-31 | 2020-06-06 | 2020-06-06 | 21 | 2020-06-27 |  |  |  | 173749.2 | [10 empty] | DoubleTree Mangroovy ElGouna | [7 empty] | El-Gouna - Temp. Fence3
Existing Intake Apply -SSC-Mech | 1 | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-30 | 573500 | 636585 | 1e-05 | 573500 | [8 empty] | 0 | 0 | [7 empty] | Existing Intake Apply -SSC-Mech1
Existing Intake Supply -SSC-Mech | 1 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 2140488 | 2418751.44 | 2311727.07 | 2140488 | [8 empty] | 0 | 0 | [7 empty] | Existing Intake Supply -SSC-Mech1
FIEM | 210 | 2017-10-31 | 2017-10-20 | 2017-10-20 | 60 | 2017-12-19 | 2017-10-23 | 2236443.87 | 1524934.13 | 1523916.51 | 69807649.46 | [8 empty] | 0 | 0 | [7 empty] | FIEM210
FIEM | 211 | 2017-11-30 | 2017-12-04 | 2018-01-02 | 60 | 2018-03-03 | 2018-01-19 | 342199.52 | 221255.83 | 218510 | 70149848.98 | [8 empty] | 0 | 0 | [7 empty] | FIEM211
FIEM | 212 | 2018-05-31 | 2018-06-12 | 2018-07-12 | 60 | 2018-09-10 | 2018-10-24 | 1955183.63 | 1546005.35 | 1205285.3 | 72105032.61 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | FIEM212
FIEM | 213 | 2018-08-31 | 2018-08-15 | 2018-10-21 | 60 | 2018-12-20 | 2018-10-24 | 336328.97 | 335237.946 | 335237.946 | 72441361.58 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | FIEM213
HQ - CFC | 1 | 2021-01-31 | 2021-01-31 | 2021-02-03 | 21 | 2021-02-24 | 2021-02-22 | 1435679.4 | 6847513.7311 | 110078731.94 | 1435679.4 |  |  | 5469259.14 | [5 empty] | 0 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC1
HQ - CFC | 2 | 2021-02-28 | 2021-02-28 | 2021-03-08 | 21 | 2021-03-29 | 2021-03-22 | 7766126.7 | 8021127.94 | 8021127.82 | 9201806.1 |  |  | 7106192.52 | [5 empty] | 0 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC2
HQ - CFC | 3 | 2021-03-31 | 2021-03-31 | 2021-04-10 | 21 | 2021-05-01 | 2021-04-15 | 12533035.1 | 8213719.76 | 8213720.11 | 21734841.2 |  |  | 6815308.56 | [5 empty] | 50000 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC3
HQ - CFC | 4 | 2021-04-30 | 2021-04-30 | 2021-05-06 | 21 | 2021-05-27 | 2021-05-26 | 11480730.2 | 7815807.64 | 7815807.73 | 33215571.4 |  |  | 6784708.63 | [5 empty] | 50000 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC4
HQ - CFC | 5 | 2021-06-30 | 2021-06-30 | 2021-07-06 | 21 | 2021-07-27 | 2021-07-14 | 6032812.4 | 3447418.19 | 3447418.19 | 39248383.8 |  |  | 6043914.88 | [5 empty] | 298842.16 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC5
HQ - CFC | 6 | 2021-07-31 | 2021-07-31 | 2021-08-04 | 21 | 2021-08-25 | 2021-08-17 | 5418722.3 | 13157201.34 | 13157200.99 | 44667106.1 |  |  | 15536980.84 | [5 empty] | 258842.16 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC6
HQ - CFC | 7 | 2021-08-31 | 2021-09-06 | 2021-09-07 | 21 | 2021-09-28 | 2021-09-09 | 14463563.8 | 14942810.8492 | 14942810.84 | 59130669.9 |  |  | 20740314.76 | [5 empty] | 258842.16 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC7
HQ - CFC | 8 | 2021-09-30 | 2021-10-06 | 2021-10-09 | 21 | 2021-10-30 | 2021-10-17 | 12855494 | 10012746.11 | 10012745.7 | 71986163.9 |  |  | 21760696.01 | [5 empty] | 253842.16 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC8
HQ - CFC | 9 | 2021-10-31 | 2021-11-03 | 2021-11-04 | 21 | 2021-11-25 | 2021-11-11 | 11039038.4 | 17174919.86 | 17174919.84 | 83025202.3 |  |  | 31225957.6 | [5 empty] | 253842.16 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC9
HQ - CFC | 10 | 2021-11-30 | 2021-12-04 | 2021-12-07 | 21 | 2021-12-28 | 2021-12-16 | 10645458.9 | 7981881.9284 | 7981881.94 | 93670661.2 |  |  | 32240807.02 | [5 empty] | 673673.38 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC10
HQ - CFC | 11 | 2021-12-31 | 2022-01-09 | 2022-01-10 | 21 | 2022-01-31 | 2022-10-20 | 21606398.42 | 17417402.06 | 27417402.1 | 115277059.62 |  |  | 33736026.89 | [5 empty] | 673673.38 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC11
HQ - CFC | 12 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 21 | 2022-03-08 | 2022-02-24 | 11990804.88 | 11342067.06 | 11342066.99 | 127267864.5 |  |  | 36548454.91 | [5 empty] | 0 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC12
HQ - CFC | 13 | 2022-02-28 | 2022-03-10 | 2022-03-15 | 21 | 2022-04-05 | 2022-03-28 | 23373232.3 | 869511.3183 | 10869511.32 | 150641096.8 |  |  | 40068734.4 |  |  |  | 3954328.79 | 3954328.79 | 0 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC13
HQ - CFC | 14 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 21 | 2022-05-04 |  |  | 1748564.91 | 6179916.44 | [9 empty] | 0 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC14
HQ - CFC | 15 | 2022-04-30 | 2022-04-30 | 2022-05-10 | 21 | 2022-05-31 | 2022-05-17 | 16353901 | 10437709.6267 | 10437699.8 | 182179087 |  |  | 36127505.39 | 42019925.8 |  | 380603 | 4782201.035 | 4782201.035 | 28096 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC15
HQ - CFC | 16 | 2022-05-31 | 2022-05-31 | 2022-06-12 | 21 | 2022-07-03 | 2022-06-15 | 8911604.3 | 1064612.35 | 1064612.28 | 191090691.3 |  |  | 35019448 | 44132357 |  | 534156.21 | 5016130.5 | 5016130.5 | 1429217 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC16
HQ - CFC | 17 | 2022-06-30 | 2022-06-30 | 2022-07-04 | 21 | 2022-07-25 | 2022-07-18 | 17076484.2 | 8013147.4 | 8013147.43 | 208167175.5 |  |  | 34368331.94 | 46825994 |  | 855446.95 | 5464388 | 5464388 | 28096.4 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC17
HQ - CFC | 18 | 2022-07-31 | 2022-07-31 | 2022-08-06 | 21 | 2022-08-27 | 2022-08-17 | 15625697.2 | 13019444.4 | 12964666.86 | 223792872.7 |  |  | 42794128.97 | 51289544.4 |  | 1216434.1435 | 5874504.1475 | 5874504.1475 | 28096.4 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC18
HQ - CFC | 19 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 21 | 2022-09-28 | 2022-10-16 | 11070593.3 | 2123376.4 | 2123375.29 | 234863466 |  |  | 43167126 | 53959703 |  | 1482872 | 6165165.5 | 6165165.5 | 23096 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC19
HQ - CFC | 20 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 21 | 2022-11-01 | 2022-10-17 | 43687204.7 | 9324446.7637 | 9324446.8 | 278550670.7 |  |  | 25330248.86 | 72413577.8 |  | 2630548.1069 | 7311955.105 | 7311955.105 | 23096.4 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC20
HQ - CFC | 21 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 21 | 2022-11-29 | 2022-11-20 | 6969185.9 | 1704646.05 | 1704646.05 | 285519856.6 |  |  | 22835242 | 75563462.2 |  | 2846115 | 7494896 | 7494896 | 0 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC21
HQ - CFC | 23 | 2022-11-30 | 2022-11-30 | 2022-12-07 | 21 | 2022-12-28 | 2022-12-14 | 9615384.7 | 10000000.1524 | 10000000 | 295135241.3 |  |  | 22835242.98 | 85178846.6 |  | 2846115.9564 | 7494896.235 | 7494896.235 | 2085744.58 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC23
HQ - CFC | 24 | 2022-11-30 | 2022-11-30 | 2022-12-13 | 21 | 2023-01-03 | 2022-12-27 | 25568878.3 | 5979128.01 | 5681250.46 | 320704119.6 |  |  | 12624923 | 98574568 |  | 4317722 | 7311955.09 | 9525011.19 | 325973.55 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC24
HQ - CFC | 25 | 2022-12-31 | 2022-12-31 | 2023-01-11 | 21 | 2023-02-01 | 2023-01-30 | 17887580.019 | 10125697.7641 | 9125697.43 | 338591699.619 |  |  | 5521723.78 | 103716174.2 |  | 5354076.6018 | 7311955.09 | 10464109.14 | 297877.55 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC25
HQ - CFC | 26 | 2023-01-31 | 2023-01-31 | 2023-11-22 | 21 | 2023-12-13 | 2024-02-15 | 15848994.2857 | 24450753.15 | 11231097.41 | 354440693.9048 |  |  | 2203336.47 | 119098372.4 |  | 6380098.57 | 9304068.215 | 9304068.215 | 0 | ElSewedy HQ Internal Finishing | [7 empty] | HQ - CFC26
HyperOne | 1 | 2019-10-31 | 2019-11-10 | 2019-11-11 | 14 | 2019-11-25 | 2019-11-24 | 1684523.66 | 2673900.95 | 36249090 | 1684523.66 | 33750000 |  | 1191900 | [5 empty] | 0 | HyperOne Zayed Extension | [7 empty] | HyperOne1
HyperOne | 2 | 2019-11-30 | 2019-12-07 | 2019-12-08 | 14 | 2019-12-22 | 2019-12-12 | 11473372.17 | 8554552.61 | 8063620 | 13157895.83 |  |  | 478500 | [5 empty] | 0 | HyperOne Zayed Extension | [7 empty] | HyperOne2
HyperOne | 3 | 2019-12-31 | 2019-12-31 | 2020-01-02 | 14 | 2020-01-16 | 2020-01-13 | 10276217.5887 | 7194819.7145 | 6681009 | 23434113.4187 |  |  | 478500 | [5 empty] | 1194684.3216 | HyperOne Zayed Extension | [7 empty] | HyperOne3
HyperOne | 4 | 2020-01-31 | 2020-01-31 | 2020-02-06 | 14 | 2020-02-20 | 2020-02-23 | 12451224.3668 | 6318712 | 6318712 | 35885337.7855 | [8 empty] | 4562652.7636 | HyperOne Zayed Extension | [7 empty] | HyperOne4
HyperOne | 5 | 2020-02-29 | 2020-02-14 | 2020-02-18 | 14 | 2020-03-03 | 2020-02-23 | 5616638.2145 | 3307335 | 3307335 | 41501976 | [8 empty] | 5067252 | HyperOne Zayed Extension | [7 empty] | HyperOne5
HyperOne | 6 | 2020-02-29 | 2020-02-29 | 2020-03-03 | 14 | 2020-03-17 | 2020-03-07 | 10976157.5052 | 8598545.1487 | 8598544 | 52478133.5052 | [8 empty] | 6203130.8054 | HyperOne Zayed Extension | [7 empty] | HyperOne6
HyperOne | 7 | 2020-03-31 | 2020-03-16 | 2020-03-19 | 14 | 2020-04-02 | 2020-03-23 | 12354446.4948 | 8896507 | 8960935 | 64832580 | [8 empty] | 7392793.3392 | HyperOne Zayed Extension | [7 empty] | HyperOne7
HyperOne | 8 | 2020-03-31 | 2020-03-31 | 2020-04-04 | 14 | 2020-04-18 | 2020-04-12 | 7228560.7301 | 3400669 | 3276433 | 72061140.7301 | [8 empty] | 9893521.3392 | HyperOne Zayed Extension | [7 empty] | HyperOne8
HyperOne | 9 | 2020-04-30 | 2020-04-16 | 2020-04-19 | 14 | 2020-05-03 | 2020-04-26 | 2029339.2699 | 1277872 | 1277872 | 74090480 | [8 empty] | 10272402 | HyperOne Zayed Extension | [7 empty] | HyperOne9
HyperOne | 10 | 2020-05-31 | 2020-05-15 | 2020-05-17 | 14 | 2020-05-31 | 2020-06-01 | 7741768.3647 | 4810581.9155 | 4688664 | 81832248.3647 | [8 empty] | 11782199.7246 | HyperOne Zayed Extension | [7 empty] | HyperOne10
HyperOne | 11 | 2020-06-30 | 2020-06-15 | 2020-06-18 | 14 | 2020-07-02 | 2020-06-23 | 9960645.6353 | 6700151 | 6700148 | 91792894 | [8 empty] | 13305539 | HyperOne Zayed Extension | [7 empty] | HyperOne11
HyperOne | 12 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 14 | 2020-07-18 | 2020-07-11 | 3093528.5715 | 1896314.4172 | 1896315 | 94886422.5715 | [8 empty] | 13935080.9072 | HyperOne Zayed Extension | [7 empty] | HyperOne12
HyperOne | 13 | 2020-07-31 | 2020-07-31 | 2020-08-09 | 14 | 2020-08-23 | 2020-08-19 | 9161230.539 | 6738701.3468 | 6738702 | 104047653.1105 | [8 empty] | 14675608.1725 | HyperOne Zayed Extension | [7 empty] | HyperOne13
HyperOne | 14 | 2020-08-31 | 2020-08-31 | 2020-09-02 | 14 | 2020-09-16 | 2020-09-13 | 5698538.8895 | 4476191 | 4476191 | 109746192 | [8 empty] | 14851704 | HyperOne Zayed Extension | [7 empty] | HyperOne14
HyperOne | 15 | 2020-12-31 | 2020-12-31 | 2021-07-10 | 14 | 2021-07-24 | 2021-09-08 | 16067546 | 2800899.62 | 2754557 | 125813738 | [8 empty] | 18113646 | HyperOne Zayed Extension | [7 empty] | HyperOne15
IKEA | 1 | 2019-10-31 | 2019-10-24 | 2019-10-29 | 56 | 2019-12-24 | 2019-11-13 | 2651353.89 | 4032556.9 | 9032556.9 | 2651353.89 | 5000000 |  | 2149309.09 | [5 empty] | 0 | IKEA Extension MoA | [7 empty] | IKEA1
IKEA | 2 | 2019-11-30 | 2019-11-30 | 2019-12-01 | 56 | 2020-01-26 | 2019-12-23 | 11255708.29 | 10633715.55 | 11062702.45 | 13907062.18 | 428986.9 |  | 4289692.08 | [5 empty] | 619021.13 | IKEA Extension MoA | [7 empty] | IKEA2
IKEA | 3 | 2019-12-31 | 2019-12-31 | 2019-12-29 | 56 | 2020-02-23 | 2020-01-27 | 10066585.32 | 7184168.18 | 12136068.98 | 23973647.5 | 4951900.8 |  | 2903747.63 | [5 empty] | 726571.28 | IKEA Extension MoA | [7 empty] | IKEA3
IKEA | 4 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 56 | 2020-03-30 | 2020-02-26 | 12574283.5677 | 8278802.0663 | 10394851.44 | 36547931.0677 | 2116049.37 |  | 465407.831 | [5 empty] | 919175.0927 | IKEA Extension MoA | [7 empty] | IKEA4
IKEA | 5 | 2020-02-29 | 2020-02-29 | 2020-03-02 | 56 | 2020-04-27 | 2020-03-29 | 9421690.8414 | 7929959.808 | 29492459.808 | 45969621.9091 | 21562500 |  | 371420 | [5 empty] | 847495.2609 | IKEA Extension MoA | [7 empty] | IKEA5
IKEA | 6 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 56 | 2020-05-26 | 2020-04-23 | 5112809.0459 | 3899213.6765 | 5718130.68 | 51082430.955 | 1818917 |  | 371420 | [5 empty] | 1125963.2758 | IKEA Extension MoA | [7 empty] | IKEA6
IKEA | 7 | 2020-04-30 | 2020-05-03 | 2020-05-05 | 56 | 2020-06-30 | 2020-06-07 | 9400137.0091 | 6161858.9082 | 9913732.53 | 60482567.9642 | 3751873.62 | [7 empty] | 1472106.3608 | IKEA Extension MoA | [7 empty] | IKEA7
IKEA | 8 | 2020-06-30 | 2020-06-23 | 2020-06-23 | 56 | 2020-08-18 | 2020-07-15 | 17657618.9509 | 13080191.1331 | 13605824.96 | 78140186.9151 | 525633.83 |  | 5848353.145 | [5 empty] | 2079486.5167 | IKEA Extension MoA | [7 empty] | IKEA8
IKEA | 9 | 2020-07-31 | 2020-07-22 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-13 | 19939473.9502 | 21936362.8422 | 21936362.84 | 98079660.8653 |  |  | 17006675.991 | [5 empty] | 1611811.9037 | IKEA Extension MoA | [7 empty] | IKEA9
IKEA | 10 | 2020-08-31 | 2020-08-15 | 2020-08-18 | 56 | 2020-10-13 | 2020-09-27 | 16241524.1447 | 10981834.92 | 10981834.92 | 114321185.01 |  |  | 16856139.28 | [5 empty] | 2394063.2 | IKEA Extension MoA | [7 empty] | IKEA10
IKEA | 11 | 2020-09-30 | 2020-10-12 | 2020-10-14 | 56 | 2020-12-09 | 2020-11-15 | 40022086.8222 | 16592416.38 | 16592416.38 | 154343271.8322 |  |  | 2685460.4477 | [5 empty] | 3391607 | IKEA Extension MoA | [7 empty] | IKEA11
IKEA | 12 | 2020-11-30 | 2020-11-25 | 2020-11-29 | 56 | 2021-01-24 | 2021-12-30 | 27619584.4178 | 15898929.26 | 15898929.26 | 181962856.25 |  |  | -4332571 | [5 empty] | 0 | IKEA Extension MoA | [7 empty] | IKEA12
IKEA | 13 | 2020-12-31 | 2021-01-10 | 2021-01-13 | 56 | 2021-03-10 | 2021-02-18 | 3981119.65 | 5400893.31 | 5400893.31 | 185943975.9 | [8 empty] | 4547790.9 | IKEA Extension MoA | [7 empty] | IKEA13
IKEA | 14 | 2021-04-30 | 2021-04-19 | 2021-06-24 | 56 | 2021-08-19 | 2021-08-09 | 10525422.84 | 15116863.46 | 15116863.46 | 196469398.74 | [8 empty] | 0 | IKEA Extension MoA | [7 empty] | IKEA14
JICA | 19 | 2017-10-31 | 2017-10-28 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-30 | 1210863.76 | 1141675.91 | 1141675.91 | 117203462.77 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | JICA19
JICA | 20 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 283125.01 | 413014.8 | 413014.8 | 117486587.78 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | JICA20
Kafr Shokr | 1 | 2021-03-31 | 2021-03-14 | 2021-03-17 | 60 | 2021-05-16 |  |  |  | 28845197.4 | [9 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 1
Kafr Shokr | 2 | 2021-03-31 | 2021-03-31 | 2021-04-07 | 60 | 2021-06-06 |  |  |  | 6242742.2 | [9 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 2
Kafr Shokr | 3 | 2021-04-30 | 2021-04-30 | 2021-05-23 | 60 | 2021-07-22 |  |  |  | 8372664.9 | [9 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 3
Kafr Shokr | 4 | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 |  |  |  | 8190447.9 | [9 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 4
Kafr Shokr | 5 | 2021-07-31 | 2021-07-31 | 2021-08-12 | 60 | 2021-10-11 |  |  |  | 5371513.65 | [9 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 5
Kafr Shokr | 6 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 |  |  |  | 444257.7 | [9 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 6
Kafr Shokr | 7 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 60 | 2021-12-09 |  | 31881474.95 | 25823994.7095 | 26652960.08 | 108184525 | [8 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 7
Kafr Shokr | 8 | 2021-11-30 | 2021-11-30 | 2021-11-30 | 60 | 2022-01-29 | 2021-12-25 | 2504502 | 2028646.62 | 2028646.62 | 110689027 | [8 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 8
Kafr Shokr | 9 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-08-07 | 5785188 | 0 | 4811891.1 | 116474215 | [8 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 9
Kafr Shokr | 10 | 2021-12-31 | 2021-12-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-09-26 | 2841975 | 2301999.75 | 2390708.7 | 119316190 | [8 empty] | 0 | Kafr Shokr Bridge | [7 empty] | Kafr Shokr 10
Katameya - Creeks | 1 | 2020-12-31 | 2020-12-31 | 2021-01-14 | 40 | 2021-02-23 | 2021-01-31 | 2910883.3063 | 2741191.2884 | 202741191.29 | 2910883.3063 | [8 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks1
Katameya - Creeks | 2 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 40 | 2021-03-16 | 2021-02-18 | 11780609.6823 | 11302769.9409 | 56302769.9409 | 14691492.9885 |  | 45000000 | 595916.5854 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks2
Katameya - Creeks | 3 | 2021-02-28 | 2021-02-28 | 2021-03-06 | 40 | 2021-04-15 | 2021-03-21 | 36329559.9323 | 39570120.8973 | 84570120.9 | 51021052.9208 |  | 45000000 | 6017782.3615 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks3
Katameya - Creeks | 4 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 40 | 2021-05-16 | 2021-04-22 | 30128591.4792 | 29688637.31 | 49688637.31 | 81149644.4 |  | 20000000 | 7771049.05 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks4
Katameya - Creeks | 5 | 2021-04-30 | 2021-05-06 | 2021-05-06 | 40 | 2021-06-15 | 2021-05-23 | 41641437.57 | 40006572.36 | 40006572.36 | 122791081.97 |  |  | 9284784.42 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks5
Katameya - Creeks | 6 | 2021-05-31 | 2021-06-06 | 2021-06-06 | 40 | 2021-07-16 | 2021-06-29 | 35290109.98 | 29363826.77 | 29363826.77 | 158081191.95 |  |  | 6250089.55 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks6
Katameya - Creeks | 7 | 2021-06-30 | 2021-07-06 | 2021-07-06 | 40 | 2021-08-15 | 2021-07-27 | 46826693.78 | 44596069.78 | 44380443 | 204907885.73 |  |  | 7704269.19 | [5 empty] | 523000 | Kattameya Creeks | [7 empty] | Katameya - Creeks7
Katameya - Creeks | 8 | 2021-07-31 | 2021-08-07 | 2021-08-07 | 40 | 2021-09-16 | 2021-08-07 | 41480221.37 | 40343227.98 | 40343227.98 | 246388107.1 |  |  | 9594054.56 | [5 empty] | 777600 | Kattameya Creeks | [7 empty] | Katameya - Creeks8
Katameya - Creeks | 9 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 40 | 2021-10-15 | 2021-09-23 | 44965022.45 | 43056438.19 | 43056438.19 | 291353129.55 |  |  | 10287932.68 | [5 empty] | 800600 | Kattameya Creeks | [7 empty] | Katameya - Creeks9
Katameya - Creeks | 10 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 40 | 2021-11-15 | 2021-10-28 | 37520387.97 | 36159161.93 | 61159972.97 | 328873517.52 |  |  | 11525093.24 | [5 empty] | 813250 | Kattameya Creeks | [7 empty] | Katameya - Creeks10
Katameya - Creeks | 11 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 40 | 2021-12-16 | 2021-11-22 |  | 43214038.28 | 43214038.28 | 379505848.55 |  |  | 7555153.37 | [5 empty] | 823370 | Kattameya Creeks | [7 empty] | Katameya - Creeks11
Katameya - Creeks | 12 | 2021-11-30 | 2021-11-30 | 2021-12-06 | 40 | 2022-01-15 | 2021-12-27 | 40810274.28 | 36461301.55 | 36461301.55 | 420316122.83 |  |  | 6280972.71 | [5 empty] | 841080 | Kattameya Creeks | [7 empty] | Katameya - Creeks12
Katameya - Creeks | 13 | 2021-12-31 | 2021-12-31 | 2022-01-08 | 40 | 2022-02-17 | 2022-01-27 | 39636501.96 | 39353596.01 | 39353596.01 | 459952624.79 |  |  | 8474255.32 | [5 empty] | 863850 | Kattameya Creeks | [7 empty] | Katameya - Creeks13
Katameya - Creeks | 14 | 2022-01-31 | 2022-01-31 | 2022-02-07 | 40 | 2022-03-19 | 2022-02-24 | 45239351.95 | 45904629.98 | 45904629.98 | 505191976.74 |  |  | 11809416.04 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks14
Katameya - Creeks | 15 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 40 | 2022-04-14 | 2022-03-14 | 47493723.66 | 49567394.59 | 49567395 | 552685700.4 |  |  | 16219011.36 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks15
Katameya - Creeks | 16 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 40 | 2022-05-16 | 2022-04-17 | 48315079.39 | 44583744.4 | 44583744 | 601000779.79 |  |  | 14925377.35 | [5 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks16
Katameya - Creeks | 17 | 2022-04-30 | 2022-04-30 | 2022-05-07 | 40 | 2022-06-16 | 2022-05-29 | 37444918.46 | 36501027.74 | 36501027.74 | 638445698.25 |  |  | 15002234.06 | 50675010 |  | 97675643 |  |  | 1009270 | Kattameya Creeks | [7 empty] | Katameya - Creeks17
Katameya - Creeks | 18 | 2022-05-31 | 2022-05-31 | 2022-06-05 | 40 | 2022-07-15 | 2022-06-05 | 37748158.21 | 41565441.8 | 41565441.8 | 676193856.46 |  |  | 20189762.86 | 59495615 |  | 103801771 |  |  | 1085086 | Kattameya Creeks | [7 empty] | Katameya - Creeks18
Katameya - Creeks | 19 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-03 | 37876838.61 | 36081249.47 | 36081249.47 | 714070695.07 |  |  | 19797069.17 | 71508662.79 |  | 108653109.7 |  |  | 1084330 | Kattameya Creeks | [7 empty] | Katameya - Creeks19
Katameya - Creeks | 20 | 2022-07-31 | 2022-07-31 | 2022-08-07 | 40 | 2022-09-16 | 2022-08-21 | 23863809.78 | 24569045.01 | 24569045 | 737934504.85 |  |  | 21208756.33 | 79759027 |  | 110507501 |  |  | 944330 | Kattameya Creeks | [7 empty] | Katameya - Creeks20
Katameya - Creeks | 21 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 40 | 2022-10-15 | 2022-09-20 | 37145495.17 | 35259435.93 | 35259435.93 | 775080000.02 |  |  | 20319209.63 | 93957089.31 |  | 115330857 |  |  | 944330 | Kattameya Creeks | [7 empty] | Katameya - Creeks21
Katameya - Creeks | 22 | 2022-09-30 | 2022-09-30 | 2022-10-06 | 40 | 2022-11-15 | 2022-10-22 | 28622135.19 | 31299260.01 | 31299260.01 | 803702135.21 |  |  | 24073006.79 | 104402623 |  | 118783626 |  |  | 944330 | Kattameya Creeks | [7 empty] | Katameya - Creeks22
Katameya - Creeks | 23 | 2022-10-31 | 2022-10-25 | 2022-11-06 | 40 | 2022-12-16 | 2022-11-28 | 24245600.88 | 29834733.07 | 29834733.07 | 827947736.09 |  |  | 30491808 | 110827191.37 |  | 121373214 |  |  | 944330 | Kattameya Creeks | [7 empty] | Katameya - Creeks23
Katameya - Creeks | 24 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 40 | 2023-01-14 | 2022-12-26 | 30975620.82 | 37876581.29 | 37876579.92 | 858923356.91 |  |  | 38226243.19 | 123338828 |  | 123817551 |  |  | 944330 | Kattameya Creeks | [7 empty] | Katameya - Creeks24
Katameya - Creeks | 25 | 2022-12-31 | 2022-12-31 | 2023-01-03 | 40 | 2023-02-12 | 2023-01-25 | 21870157.41 | 45191848.32 | 45191848.31 | 880793514.32 |  |  | 61683477.19 | 133104770 |  | 126424933 |  |  | 944330 | Kattameya Creeks | [7 empty] | Katameya - Creeks25
Katameya - Creeks | 26 | 2023-01-31 | 2023-01-31 | 2023-02-05 | 40 | 2023-03-17 | 2023-02-28 | 41254688.36 | 74263221.64 | 74263221 | 922048202.68 |  |  | 93923373 | 158579085 |  | 130310913 |  |  | 975300.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks26
Katameya - Creeks | 27 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 40 | 2023-04-14 | 2023-03-30 | 23948941.02 | 35452924.06 | 35452924 | 945997143.7 |  |  | 105419805.57 | 170052796 |  | 133396502 |  |  | 975300 | Kattameya Creeks | [7 empty] | Katameya - Creeks27
Katameya - Creeks | 28 | 2023-03-31 | 2023-03-30 | 2023-04-06 | 40 | 2023-05-16 | 2023-05-04 | 26373696.19 | 28650459.02 | 28650459 | 972370839.89 |  |  | 107935491.27 | 183454579.15 |  | 136180192 |  |  | 975300 | Kattameya Creeks | [7 empty] | Katameya - Creeks28
Katameya - Creeks | 29 | 2023-04-30 | 2023-04-30 | 2023-05-10 | 40 | 2023-06-19 | 2023-06-03 | 23994845.49 | 40904481.77 | 40904481 | 996365685.38 |  |  | 124153275.86 | 196775586 |  | 138759517 |  |  | 1187195.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks29
Katameya - Creeks | 30 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 40 | 2023-07-17 | 2023-06-22 | 81851684.98 | 43084120.03 | 43084120 | 1078217370.36 |  |  | 97599905.99 | 269087133.95 |  | 142922586 |  |  | 1474123.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks30
Katameya - Creeks | 31 | 2023-06-30 | 2023-06-30 | 2023-07-09 | 40 | 2023-08-18 | 2023-07-31 | 34090513.58 | 37106226.16 | 37106226 | 1112307883.94 |  |  | 112799416.94 | 291661196 |  | 146035580.84 |  |  | 1474123.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks31
Katameya - Creeks | 32 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 40 | 2023-09-17 | 2023-09-04 | 36694395.36 | 53216438.64 | 41216438 | 1149002279.3 |  |  | 128465791.75 | 319241513 |  | 149874135 |  |  | 1474123.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks32
Katameya - Creeks | 33 | 2023-08-31 | 2023-08-31 | 2023-09-07 | 40 | 2023-10-17 | 2023-10-01 | 61801377.92 | 47329832.99 | 47329833 | 1210803657.22 |  |  | 127901321.55 | 370075065.87 |  | 154477701.6 |  |  | 1474123.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks33
Katameya - Creeks | 34 | 2023-09-30 | 2023-09-30 | 2023-10-08 | 40 | 2023-11-17 | 2023-11-02 | 67431952.34 | 70308953.76 | 70308953 | 1278235609.56 |  |  | 143466613.76 | 421285092.94 |  | 161880059 |  |  | 2286300.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks34
Katameya - Creeks | 35 | 2023-10-31 | 2023-10-31 | 2023-11-08 | 40 | 2023-12-18 | 2023-12-06 | 61247331.12 | 46816344.41 | 46816344 | 1339482940.68 |  |  | 141313879.12 | 467826001.19 |  | 169260713.53 |  |  | 2593710.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks35
Katameya - Creeks | 36 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 40 | 2024-01-16 | 2023-12-30 | 74463161.12 | 50530225.45 | 50530224.78 | 1413946101.8 |  |  | 131303175.93 | 514457815.28 |  | 175537623 |  |  | 2835674.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks36
Katameya - Creeks | 37 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-01-22 | 53331460.14 | 62109565.07 | 62109565 | 1467277561.94 |  |  | 138791064.14 | 557616767.77 |  | 179660456 |  |  | 3087279.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks37
Katameya - Creeks | 38 | 2024-01-31 | 2024-01-31 | 2024-02-08 | 40 | 2024-03-19 | 2024-03-06 | 83842743.6 | 79235149.9 | 79235150 | 1551120305.54 |  |  | 133813630.27 | 619119624.83 |  | 194495708 |  |  | 3385105 | Kattameya Creeks | [7 empty] | Katameya - Creeks38
Katameya - Creeks | 39 | 2024-02-29 | 2024-02-29 | 2024-03-10 | 40 | 2024-04-19 | 2024-04-02 | 81688930.92 | 66261026.21 | 66261026 | 1632809236.46 |  |  | 118504628.04 | 681574347 |  | 206803236 |  |  | 3583708 | Kattameya Creeks | [7 empty] | Katameya - Creeks39
Katameya - Creeks | 40 | 2024-03-31 | 2024-03-31 | 2024-04-06 | 40 | 2024-05-16 | 2024-05-02 | 66582662.04 | 52039038.12 | 52039038 | 1699391898.5 |  |  | 104305214.28 | 732184516 |  | 217702929 |  |  | 3885490.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks40
Katameya - Creeks | 41 | 2024-04-30 | 2024-04-30 | 2024-05-08 | 40 | 2024-06-17 | 2024-05-25 | 47455342.03 | 45340679.8 | 45340678.81 | 1746847240.53 |  |  | 101408785.94 | 771118051 |  | 224726984.46 |  |  | 4067349.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks41
Katameya - Creeks | 42 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 40 | 2024-07-19 | 2024-07-07 | 56995945.47 | 52791233.92 | 52791233 | 1803843186 |  |  | 96574638 | 816861989 |  | 232964321 |  |  | 4370002 | Kattameya Creeks | [7 empty] | Katameya - Creeks42
Katameya - Creeks | 43 | 2024-06-30 | 2024-06-30 | 2024-07-10 | 40 | 2024-08-19 | 2024-07-27 | 56437240.4362 | 30082113.9462 | 21224102 | 1860280426.4362 |  |  | 90480931.8131 | 861619431.0834 |  | 241015625.4571 |  |  | 4370002.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks43
Katameya - Creeks | 44 | 2024-07-31 | 2024-07-31 | 2024-08-10 | 40 | 2024-09-19 | 2024-08-31 | 49427006.6938 | 8345106.3 | 8345106.3 | 1909707433.13 |  |  | 67101367.22 | 899419335 |  | 247392879 |  |  | 4855643.2 | Kattameya Creeks | [7 empty] | Katameya - Creeks44
Katameya - Creeks | 45 | 2024-08-31 | 2024-08-31 | 2024-09-09 | 40 | 2024-10-19 | 2024-10-03 | 67801530.87 | 24274088.38 | 8654893.7 | 1977508964 |  |  | 50090340 | 947220416 |  | 256761214 |  |  | 5144638 | Kattameya Creeks | [7 empty] | Katameya - Creeks45
Katameya - Creeks | 46 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 40 | 2024-11-19 | 2024-11-04 | 42454238 | 22007540.78 | 0 | 2019963202 |  |  | 39951618 | 976799080 |  | 264112905 |  |  | 5327913 | Kattameya Creeks | [7 empty] | Katameya - Creeks46
Katameya - Creeks | 47 | 2024-10-31 | 2024-10-31 | 2024-11-09 | 40 | 2024-12-19 |  |  |  | 0 | [9 empty] | 0 | Kattameya Creeks | [7 empty] | Katameya - Creeks47
KFW | 109 | 2017-09-30 | 2017-10-09 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-23 | 156311.35 | 128570.36 | 128570.36 | 20308378.88 | [8 empty] | 0 | 0 | [7 empty] | KFW109
KFW | 110 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 357187.5 | 377225.16 | 377225.16 | 20665566.38 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | KFW110
Khatatba Bridge | 1 | 2022-01-31 | 2022-01-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-02-08 | 42898060 | 8313070.05 | 803531.75 | 42898060 | [8 empty] | 0 | El Khatatba Bridge | [7 empty] | Khatatba Bridge1
Khatatba Bridge | 2 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 10581515 | 10363626.0758 | 7509538.3 | 53479575 | [8 empty] | 0 | El Khatatba Bridge | [7 empty] | Khatatba Bridge2
Khatatba Bridge | 4 | 2022-07-31 | 2022-08-01 | 2022-08-15 | 60 | 2022-10-14 | 2022-08-15 | 50062250 | 49031394.797 | 36303482.3 | 103541825 | [8 empty] | 0 | El Khatatba Bridge | [7 empty] | Khatatba Bridge4
KSA-Tarek AbdelHakim Center | 1 | 2023-02-28 | 2023-02-28 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 1174788.1 | 951578.36 | 1183249.5731 | 1174788.1 | [6 empty] | 117478.81 |  | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center1
KSA-Tarek AbdelHakim Center | 2 | 2023-03-31 | 2023-03-31 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 2619891.03 | 2122111.73 | 562894.3581 | 3794679.13 | [6 empty] | 379467.91 |  | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center2
KSA-Tarek AbdelHakim Center | 3 | 2023-04-30 | 2023-04-30 | 2023-06-22 | 75 | 2023-09-05 | 2023-07-25 | 1124829.43 | 911111.84 | 194180.7389 | 4919508.56 | [6 empty] | 491950.85 |  | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center3
KSA-Tarek AbdelHakim Center | 4 | 2023-05-31 | 2023-05-31 | 2023-07-24 | 75 | 2023-10-07 | 2023-07-25 | 1181749.35 | 957216.97 | 242494.97 | 6101257.91 | [6 empty] | 610125.78 |  | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center4
KSA-Tarek AbdelHakim Center | 5 | 2023-06-30 | 2023-06-30 | 2023-09-14 | 75 | 2023-11-28 |  |  |  | 260811.86 | [9 empty] | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center5
KSA-Tarek AbdelHakim Center | 6 | 2023-07-31 | 2023-07-31 | 2023-09-14 | 75 | 2023-11-28 |  |  |  | 253333.77 | [9 empty] | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center6
KSA-Tarek AbdelHakim Center | 7 | 2023-08-31 | 2023-08-31 | 2023-09-14 | 75 | 2023-11-28 |  |  |  | 450546.16 | [9 empty] | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center7
KSA-Tarek AbdelHakim Center | 8 | 2023-09-30 | 2023-09-30 | 2023-10-17 | 75 | 2023-12-31 |  |  |  | 630195.46 | [9 empty] | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center8
KSA-Tarek AbdelHakim Center | 9 | 2023-10-31 | 2023-11-06 | 2023-11-06 | 75 | 2024-01-20 |  |  |  | 1513478.59 | [9 empty] | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center9
KSA-Tarek AbdelHakim Center | 10 | 2023-11-30 | 2023-11-21 | 2023-11-21 | 75 | 2024-02-04 |  |  |  | 1468894.06 | [9 empty] | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center10
KSA-Tarek AbdelHakim Center | 11 | 2023-12-31 | 2023-12-24 | 2023-12-24 | 75 | 2024-03-08 | 2024-01-04 | 6272151.58 | 5080442.78 | 0 | 34906557.56 | [6 empty] | 3367198.74 |  | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center11
KSA-Tarek AbdelHakim Center | 12 | 2024-04-30 | 2024-05-09 | 2024-09-24 | 75 | 2024-12-08 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | KSA-Tarek AbdelHakim Center12
LEKELA | 1 | 2020-03-31 | 2020-03-15 | 2020-07-19 | 60 | 2020-09-17 |  |  |  | 37970902.46 |  | 36300000 | [7 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA1
LEKELA | 2 | 2020-06-30 | 2020-06-30 | 2020-07-19 | 60 | 2020-09-17 |  |  |  | 1067868.0976 | [9 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA2
LEKELA | 3 | 2020-07-31 | 2020-07-27 | 2020-07-27 | 60 | 2020-09-25 |  |  |  | 1758948.8952 | [9 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA3
LEKELA | 4 | 2020-08-31 | 2020-08-31 | 2020-09-12 | 60 | 2020-11-11 |  |  |  | 652923.5 | [9 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA4
LEKELA | 5 | 2020-09-30 | 2020-09-29 | 2020-09-30 | 60 | 2020-11-29 | 2020-10-08 | 8446374.726 | 7094954.7715 | 7094954.7715 | 14578092.546 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA5
LEKELA | 6 | 2020-10-31 | 2020-10-28 | 2020-10-28 | 60 | 2020-12-27 | 2020-11-12 | 20620363.18 | 14840272.4231 | 14840272.4231 | 35198455.726 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA6
LEKELA | 7 | 2020-11-30 | 2020-11-22 | 2020-11-23 | 60 | 2021-01-22 | 2020-12-02 | 19433463.8412 | 15073158.3499 | 15073158.35 | 54631919.5672 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA7
LEKELA | 8 | 2020-12-31 | 2020-12-28 | 2020-12-28 | 60 | 2021-02-26 | 2021-01-19 | 41700595.0348 | 33513527.4715 | 33357157.2169 | 96332514.602 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA8
LEKELA | 9 | 2021-01-31 | 2021-01-15 | 2021-01-31 | 60 | 2021-04-01 | 2021-02-05 | 23169483.21 | 18594958.1925 | 18594958.1925 | 119501997.812 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA9
LEKELA | 10 | 2021-02-28 | 2021-02-15 | 2021-02-17 | 60 | 2021-04-18 | 2021-03-11 | 27064762.4727 | 21709399.51 | 21709399.51 | 146566760.2847 |  |  | 0 | [5 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA10
LEKELA | 11 | 2021-03-31 | 2021-03-15 | 2021-03-16 | 60 | 2021-05-15 | 2021-05-20 | 18055279.9362 | 14823033.596 | 14896483.6 | 164622040.2209 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA11
LEKELA | 12 | 2021-04-30 | 2021-04-15 | 2021-04-20 | 60 | 2021-06-19 | 2021-05-24 | 26449156.1285 | 21477147.745 | 21477147.745 | 191071196.3494 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA12
LEKELA | 13 | 2021-05-31 | 2021-05-15 | 2021-05-24 | 60 | 2021-07-23 | 2021-08-01 | 6179424.4906 | 2329136.4958 | 2329136.4958 | 197250620.84 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA13
LEKELA | 14 | 2021-06-30 | 2021-06-15 | 2021-07-26 | 60 | 2021-09-24 |  |  |  | 12951636.6142 | [9 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA14
LEKELA | 15 | 2021-10-31 | 2021-10-15 | 2022-11-15 | 60 | 2023-01-14 | 2022-12-14 | 6597023.32 | 3229199.86 | 3839081.19 | 207000000 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA15
LEKELA | 16 | 2022-11-30 | 2022-11-20 | 2023-02-22 | 60 | 2023-04-23 | 2023-03-31 | -0.0001 | 8212932.01 | 8212932 | 207000000 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA16
LEKELA Remedial | 2 | 2024-01-31 | 2024-01-30 | 2024-02-26 | 60 | 2024-04-26 |  |  |  | 7000000.52 | [9 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA Remedial2
LEKELA Remedial | 3 | 2024-05-31 | 2024-05-19 | 2024-08-19 | 60 | 2024-10-18 | 2024-08-21 | 2884958.98 | 3000357.86 | 3000357.34 | 15655160.98 | [8 empty] | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA Remedial3
LEKELA Remedial | 4 | 2024-08-31 | 2024-08-20 | 2024-08-21 | 60 | 2024-10-20 | 2024-10-20 | 6153867.61 | 6400022.32 | 6400022.32 | 21809028.59 | [5 empty] | 2290980.91 |  |  | 0 | Lekela 250MW Wind Farm | [7 empty] | LEKELA Remedial4
MDF Factory | 1 | 2021-06-30 | 2021-06-30 | 2021-07-05 | 28 | 2021-08-02 | 2021-08-17 | 3709029.4 | 6231879.24 | 47854244.4 | 3709029.4 | 41622365.4 |  | 4472196.39 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory1
MDF Factory | 2 | 2021-07-31 | 2021-08-08 | 2021-08-08 | 28 | 2021-09-05 | 2021-08-31 | 5178414.72 | 7093735 | 13393735 | 8887444.12 | 6300000 |  | 7086056.01 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory2
MDF Factory | 3 | 2021-08-31 | 2021-08-31 | 2021-09-06 | 28 | 2021-10-04 | 2021-09-22 | 9214079.17 | 8598866.23 | 18410664.56 | 18101523.29 | 2000000 |  | 8983935.87 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory3
MDF Factory | 4 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 28 | 2021-11-03 | 2021-10-27 | 9266652.88 | 8359615.97 | 19359615 | 27368176.17 | 2000000 |  | 10661948.66 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory4
MDF Factory | 5 | 2021-10-31 | 2021-10-31 | 2021-11-07 | 28 | 2021-12-05 | 2021-12-05 | 23662523.0739 | 21785509.71 | 38802133.78 | 51030699.2439 | 10016624.86 |  | 10195623.7568 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory5
MDF Factory | 6 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 28 | 2022-01-06 | 2022-01-20 | 17937654.1261 | 17171193.3155 | 28503193.33 | 68968353.37 | 7332000 |  | 11973915.52 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory6
MDF Factory | 7 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 28 | 2022-02-08 | 2022-02-14 | 16080953.7816 | 14452550.5619 | 59606480 | 85049307.1516 | 6000000 |  | 12658184.96 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory7
MDF Factory | 8 | 2022-01-31 | 2022-01-31 | 2022-02-09 | 28 | 2022-03-09 | 2022-03-01 | 12291002.2884 | 12391060.05 | 29352571.68 | 97340309.44 | 11000000 |  | 14426942.06 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory8
MDF Factory | 9 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 28 | 2022-04-06 | 2022-04-07 | 8038787.77 | 7655361.33 | 18942922.65 | 105379097.21 | 13754630 |  | 14289033.25 |  |  |  | 2526800.69 | 2526800.69 | 0 | MDF Factory | [7 empty] | MDF Factory9
MDF Factory | 10 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 28 | 2022-05-11 | 2022-04-27 | 6155129.99 | 11119452.63 | 11719330.26 | 111534227.2 | 1488562.75 |  | 19004034.21 | [5 empty] | 0 | MDF Factory | [7 empty] | MDF Factory10
MDF Factory | 11 | 2022-04-30 | 2022-04-30 | 2022-04-28 | 28 | 2022-05-26 | 2022-06-07 | 9364100.8 | 9991684.94 | 11835349.23 | 120898328 | 3000000 |  | 19378872 | 6694496.17 |  | 8943366.16 | 2938817.5 | 2938817.5 | 985000 | MDF Factory | [7 empty] | MDF Factory11
MDF Factory | 12 | 2022-05-31 | 2022-05-31 | 2022-06-11 | 28 | 2022-07-09 | 2022-06-29 | 27509389.27 | 29337407.23 | 25380982.3 | 148407717.27 |  |  | 21048487.96 | 9413326 |  | 14867864 | 3374171 | 3374171 | 0 | MDF Factory | [7 empty] | MDF Factory12
MDF Factory | 13 | 2022-06-30 | 2022-06-30 | 2022-07-06 | 28 | 2022-08-03 | 2022-08-07 | 15343913.47 | 19866888.03 | 2351273.22 | 163751630.74 |  |  | 25112316.18 | 10650525.16 |  | 15407262.1 | 3894039.675 | 3894039.675 | 1300000 | MDF Factory | [7 empty] | MDF Factory13
MDF Factory | 14 | 2022-07-31 | 2022-07-25 | 2022-08-14 | 28 | 2022-09-11 | 2022-09-25 | 11905906.3968 | 11219361.6633 | 11219362.36 | 175657537.1368 |  |  | 28064532.2963 | 10473927.4807 |  | 17096495.4946 | 4266369.805 | 4266369.805 | 3250000 | MDF Factory | [7 empty] | MDF Factory14
MDF Factory | 15 | 2022-08-31 | 2022-08-31 | 2022-09-08 | 28 | 2022-10-06 | 2022-10-09 | 8651043.7332 | 15409194.69 | 10812468.25 | 184308580.87 |  |  | 33441117.05 | 10616746 |  | 16229441.88 | 4412077.4 | 4412077.4 | 1350000 | MDF Factory | [7 empty] | MDF Factory15
MDF Factory | 16 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 28 | 2022-11-08 | 2022-11-06 | 21753082.06 | 22014291.85 | 10601848.06 | 206061662.93 |  |  | 35882692.55 | 10827826.68 |  | 16039161.03 | 4776541.575 | 4776541.575 | 3300000 | MDF Factory | [7 empty] | MDF Factory16
MDF Factory | 17 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 28 | 2022-12-06 | 2022-11-23 | 3503748.7 | 15156893.21 | 13701835.53 | 209565411.63 |  |  | 38117303.52 | 12364842.71 |  | 20883147.71 | 5114135 | 5114135 | 2890000 | MDF Factory | [7 empty] | MDF Factory17
MDF Factory | 18 | 2022-11-30 | 2022-11-15 | 2022-11-27 | 28 | 2022-12-25 | 2022-12-11 | 4093790.13 | 5028798.98 | 3474417.48 | 213659201.76 |  |  | 38907634.85 | 12512881.83 |  | 19805682.68 | 5216480 | 5216480 | 2840000 | MDF Factory | [7 empty] | MDF Factory18
MDF Factory | 19 | 2022-11-30 | 2022-11-30 | 2022-12-12 | 28 | 2023-01-09 | 2022-12-28 | 12077854.33 | 9756751.36 | 8855940.16 | 225737056.09 |  |  | 37074813.73 | 17269270.26 |  | 19805682.68 | 5518426.4 | 5518426.4 | 1240000 | MDF Factory | [7 empty] | MDF Factory19
MDF Factory | 20 | 2022-12-31 | 2022-12-25 | 2022-12-22 | 28 | 2023-01-19 | 2023-01-12 | 10662163.65 | 14838164.52 | 1506264.66 | 236399219.74 |  |  | 44141114.86 | 18934354.95 |  | 21551157.34 | 5784980.495 | 5784980.495 | 1240000 | MDF Factory | [7 empty] | MDF Factory20
MDF Factory | 21 | 2023-01-31 | 2023-01-12 | 2023-01-19 | 28 | 2023-02-16 | 2023-02-06 | 18933899.86 | 18749752.53 | 16783340.22 | 255333119.6 |  |  | 44152242.9 | 21222761.6 |  | 32601298.43 | 6258327.99 | 6258327.99 | 890000 | MDF Factory | [7 empty] | MDF Factory21
MDF Factory | 22 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 28 | 2023-03-08 | 2023-02-25 | 3256087.31 | 3016784.72 | 9454487.21 | 258589206.91 |  |  | 44812446.87 | 22595375.04 | 400000 | 31182122.08 | 6339730 | 6339730 | 490000 | MDF Factory | [7 empty] | MDF Factory22
MDF Factory | 23 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 28 | 2023-04-02 | 2023-03-22 | 38888289.8 | 26140854.32 | 10035885.59 | 297477496.71 |  |  | 41744854.59 | 37403483.04 | 400000 | 31433209.86 | 7311937.42 | 7311937.42 | 470000 | MDF Factory | [7 empty] | MDF Factory23
MDF Factory | 24 | 2023-03-31 | 2023-03-31 | 2023-04-04 | 28 | 2023-05-02 | 2023-04-30 | 18681389.16 | 13504786.11 | 5923051.17 | 316158885.87 |  |  | 36725913.89 | 48869956.89 | 400000 | 31459228.76 | 7778972.145 | 7778972.145 | 470000 | MDF Factory | [7 empty] | MDF Factory24
MDF Factory | 25 | 2023-04-30 | 2023-04-30 | 2023-05-08 | 28 | 2023-06-05 | 2023-06-05 | 10484631.76 | 14874774.09 | 4519315.77 | 326643517.63 |  |  | 41744047.17 | 58047371.04 | 650000 | 31459228.76 | 8041087.94 | 8041087.94 | 400000 | MDF Factory | [7 empty] | MDF Factory25
MDF Factory | 26 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 28 | 2023-07-06 | 2023-06-21 | 21011393.06 | 18123054.07 | 12901160.06 | 347654910.69 |  |  | 39628505.18 | 73625314.2 | 200000 | 33225314.57 | 8566372.765 | 8566372.765 | 450000 | MDF Factory | [7 empty] | MDF Factory26
MDF Factory | 27 | 2023-06-30 | 2023-06-30 | 2023-06-26 | 28 | 2023-07-24 | 2023-07-12 | 10160280.74 | 21231778.46 | 19177600.34 | 357815191.43 |  |  | 54504636.34 | 81071518.94 | 250000 | 33210812.42 | 8820379.785 | 8820379.785 | 450000 | MDF Factory | [7 empty] | MDF Factory27
MDF Factory | 28 | 2023-07-31 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 | 2023-07-31 | 4632219.77 | 5471658.1245 | 5380287.99 | 362447411.2 |  |  | 57298682.38 | 84101651.16 | 200000 | 33299495.32 | 8936185.28 | 8936185.28 | 500000 | MDF Factory | [7 empty] | MDF Factory28
MDF Factory | 29 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 28 | 2023-09-05 | 2023-09-10 | 7201895.8 | 13138195.96 | 10038430.32 | 369649307 |  |  | 63433973.15 | 88923223.93 | 200000 | 35138135.49 | 9116232.675 | 9116232.675 | 520000 | MDF Factory | [7 empty] | MDF Factory29
MDF Factory | 30 | 2023-08-31 | 2023-08-30 | 2023-09-10 | 28 | 2023-10-08 | 2023-09-19 | 42878737.92 | 12581507.75 | 11530799.53 | 412528044.92 |  |  | 48447410.77 | 120743192.13 | 200000 | 35183358.23 | 10188201.125 | 10188201.125 | 550000 | MDF Factory | [7 empty] | MDF Factory30
MDF Factory | 31 | 2023-09-30 | 2023-09-30 | 2023-10-05 | 28 | 2023-11-02 | 2023-10-07 | 26984773 | 20429584.53 | 18846610.6 | 439512817.92 |  |  | 52299084.09 | 141277943.84 | 200000 | 34937145.36 | 10862820.45 | 10862820.45 | 250000 | MDF Factory | [7 empty] | MDF Factory31
MDF Factory | 32 | 2023-10-31 | 2023-10-25 | 2023-10-26 | 28 | 2023-11-23 | 2023-10-26 | 2754000 | 2726460 | 2726460 | 442266817.92 |  |  | 52299084.09 | 144031943.84 | 200000 | 34937145.36 | 10931670.45 | 10931670.45 | 250000 | MDF Factory | [7 empty] | MDF Factory32
MDF Factory | 33 | 2023-10-31 | 2023-10-31 | 2023-11-07 | 28 | 2023-12-05 | 2023-11-25 | 20665276.54 | 12154985.64 | 8808260.33 | 462932094.46 |  |  | 52125340.59 | 161100913.16 | 250000 | 35201311.24 | 11448302 | 11448302 | 200000 | MDF Factory | [7 empty] | MDF Factory33
MDF Factory | 34 | 2023-11-30 | 2023-11-30 | 2023-12-09 | 28 | 2024-01-06 | 2023-12-20 | 25469525.62 | 13093494.9 | 12466636.78 | 488401620.08 |  |  | 49181191.79 | 181875990.6 | 250000 | 35200228.82 | 12085040.5 | 12085040.5 | 200000 | MDF Factory | [7 empty] | MDF Factory34
MDF Factory | 35 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 28 | 2024-01-28 | 2024-01-21 | 7460561 | 14005346.87 | 11964736.84 | 495862181.08 |  |  | 56480937.48 | 187067355.65 | 100000 | 35200149.54 | 12271554.525 | 12271554.525 | 350000 | MDF Factory | [7 empty] | MDF Factory35
MDF Factory | 36 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-28 | 24220349.75 | 12150509.06 | 10194821.77 | 520082530.83 |  |  | 52738337.77 | 208687659.78 | 200000 | 35240386.14 | 12877063.27 | 12877063.27 | 220000 | MDF Factory | [7 empty] | MDF Factory36
MDF Factory | 37 | 2024-02-29 | 2024-02-29 | 2024-03-11 | 28 | 2024-04-08 | 2024-04-02 | 18799337.86 | 7449862.86 | 4465149.39 | 538881868.69 |  |  | 47546890.76 | 225598759.07 | 1500000 | 35240386.14 | 13347046.715 | 13347046.715 | 700000 | MDF Factory | [7 empty] | MDF Factory37
MDF Factory | 38 | 2024-03-31 | 2024-03-31 | 2024-04-08 | 28 | 2024-05-06 | 2024-04-24 | 25264630.57 | 10129299.6901 | 9539881.65 | 564146499.26 |  |  | 42828938.17 | 247874489.5 | 200000 | 35240386.14 | 13978662.48 | 13978662.48 | 253450 | MDF Factory | [7 empty] | MDF Factory38
MDF Factory | 39 | 2024-04-30 | 2024-04-30 | 2024-05-07 | 28 | 2024-06-04 | 2024-05-22 | 17461783.47 | 7951387.28 | 6984174.92 | 581608282.73 |  |  | 39702840.21 | 261893208.84 | 200000 | 35240386.14 | 14415207 | 14415207 | 253450 | MDF Factory | [7 empty] | MDF Factory39
MDF Factory | 40 | 2024-04-30 | 2024-04-30 | 2024-05-26 | 28 | 2024-06-23 | 2024-06-12 | -0.73 | 13055049.84 | 13054639.6 | 581608282 |  |  | 39702840 | 261893208 |  | 35240386 | 6101647 |  | 453450 | MDF Factory | [7 empty] | MDF Factory40
MDF Factory | 41 | 2024-05-31 | 2024-05-31 | 2024-06-06 | 28 | 2024-07-04 | 2024-06-13 | 26553112.48 | 25000718.68 | 8347962.7 | 608161394.48 |  |  | 40071589.73 | 273875725.24 |  | 35240386.14 | 7033092.855 | 7033092.855 | 303450 | MDF Factory | [7 empty] | MDF Factory41
MDF Factory | 42 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 28 | 2024-08-04 | 2024-07-24 | 750284.2 | 7547918.7 | 7602001.04 | 608911678.68 |  |  | 33497125 | 289636214 |  | 35240386 | 7100876.5 | 7100876.5 | 453450 | MDF Factory | [7 empty] | MDF Factory42
MDF Factory | 43 | 2024-07-31 | 2024-07-31 | 2024-08-06 | 28 | 2024-09-03 | 2024-08-21 | 11210135.32 | 57977475.46 | 45999180 | 620121814 |  |  | 31321429 | 299419159 |  | 35243045 | 7887682 | 7887682 | 553450 | MDF Factory | [7 empty] | MDF Factory43
MDF Factory | 44 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 28 | 2024-10-03 | 2024-09-26 | 10205950.6 | 13417821.66 | 0 | 630327764.6 |  |  | 30187176.6062 | 308819628.409 |  | 35266531.1337 | 15775364.249 |  | 4593450 | MDF Factory | [7 empty] | MDF Factory44
MDF Factory | 45 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 28 | 2024-11-07 | 2024-11-04 | 16259922.8 | 21518034.22 | 0 | 646587687.4 |  |  | 21616659 | 325129806 |  | 34015260 | 15775364 |  | 3833450 | MDF Factory | [7 empty] | MDF Factory45
MDF Factory - Equip. | 1 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-16 | 474511.19 | 487660.4 | 479255 | 474511.19 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.1
MDF Factory - Equip. | 2 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-18 | 2969783.71 | 2999481.54 | 2957905.39 | 3444294.9 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.2
MDF Factory - Equip. | 3 | 2022-01-31 | 2022-02-15 | 2022-02-22 | 28 | 2022-03-22 | 2022-03-01 | 2443276.13 | 2478572.15 | 2467707.5 | 5887571.03 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.3
MDF Factory - Equip. | 4 | 2022-03-31 | 2022-03-15 | 2022-03-29 | 28 | 2022-04-26 |  |  |  | 2118826 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.4
MDF Factory - Equip. | 5 | 2022-04-30 | 2022-04-15 | 2022-04-24 | 28 | 2022-05-22 |  |  |  | 2067056 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.5
MDF Factory - Equip. | 6 | 2022-05-31 | 2022-05-15 | 2022-05-24 | 28 | 2022-06-21 |  |  |  | 569764 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.6
MDF Factory - Equip. | 7 | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 |  |  |  | 795032 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.7
MDF Factory - Equip. | 8 | 2022-07-31 | 2022-07-15 | 2022-07-25 | 28 | 2022-08-22 | 2022-08-02 | 340101.34 | 324002.35 | 322760 | 11819751.78 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.8
MDF Factory - Equip. | 9 | 2022-08-31 | 2022-08-15 | 2022-08-29 | 28 | 2022-09-26 |  |  |  | 1546900 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.9
MDF Factory - Equip. | 10 | 2022-09-30 | 2022-09-15 | 2022-09-20 | 28 | 2022-10-18 |  |  |  | 362327.85 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.10
MDF Factory - Equip. | 11 | 2022-10-31 | 2022-10-15 | 2022-11-01 | 28 | 2022-11-29 |  |  |  | 115740.16 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.11
MDF Factory - Equip. | 12 | 2022-11-30 | 2022-11-15 | 2022-11-30 | 28 | 2022-12-28 |  |  |  | 617997.99 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.12
MDF Factory - Equip. | 13 | 2022-12-31 | 2022-12-15 | 2023-01-04 | 28 | 2023-02-01 |  |  |  | 1033353.65 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.13
MDF Factory - Equip. | 14 | 2023-01-31 | 2023-01-15 | 2023-02-05 | 28 | 2023-03-05 |  |  |  | 1342515 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.14
MDF Factory - Equip. | 15 | 2023-02-28 | 2023-02-15 | 2023-03-05 | 28 | 2023-04-02 |  |  |  | 1508230 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.15
MDF Factory - Equip. | 16 | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 |  |  |  | 963455.46 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.16
MDF Factory - Equip. | 17 | 2023-05-31 | 2023-06-15 | 2023-06-18 | 28 | 2023-07-16 |  |  |  | 359356.67 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.17
MDF Factory - Equip. | 18 | 2023-06-30 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 |  |  |  | 536737.62 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.18
MDF Factory - Equip. | 19 | 2023-08-31 | 2023-08-30 | 2023-09-09 | 28 | 2023-10-07 | 2023-10-02 | 461776.49 | 1199203.75 | 1190791 | 21352041.9 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.19
MDF Factory - Equip. | 20 | 2023-09-30 | 2023-09-30 | 2023-10-16 | 28 | 2023-11-13 |  |  |  | 606416.12 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.20
MDF Factory - Equip. | 21 | 2023-12-31 | 2023-12-20 | 2023-12-25 | 28 | 2024-01-22 | 2024-02-06 | 540952.41 | 592013.93 | 600370.17 | 22578347.52 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.21
MDF Factory - Equip. | 22 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 28 | 2024-04-28 |  |  |  | 205199.38 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.22
MDF Factory - Equip. | 23 | 2024-04-30 | 2024-04-15 | 2024-05-02 | 28 | 2024-05-30 | 2024-05-08 | 539934.96 | 638068.17 | 545334.31 | 23413265.89 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.23
MDF Factory - Equip. | 24 | 2024-04-30 | 2024-04-15 | 2024-05-08 | 28 | 2024-06-05 | 2024-05-21 | 250311 | 252814.11 | 345289.58 | 23663576.89 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.24
MDF Factory - Equip. | 25 | 2024-06-30 | 2024-06-30 | 2024-06-26 | 28 | 2024-07-24 | 2024-07-01 | 631287.83 | 637600.71 | 637190.72 | 24294864.72 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.25
MDF Factory - Equip. | 26 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 28 | 2024-09-29 | 2024-10-02 | 1237289.1 | 1250071.98 | 0 | 25532153.82 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.26
MDF Factory - Equip. | 27 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 28 | 2024-10-28 | 2024-10-17 | 20666.66 | 2574782 | 0 | 25552820.48 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Equip.27
MDF Factory - Local Fabrication | 1 | 2022-02-28 | 2022-02-15 | 2022-03-03 | 28 | 2022-03-31 |  |  |  | 920351.25 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication1
MDF Factory - Local Fabrication | 2 | 2022-03-31 | 2022-03-15 | 2022-03-21 | 28 | 2022-04-18 |  |  |  | 711105.4 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication2
MDF Factory - Local Fabrication | 3 | 2022-03-31 | 2022-04-10 | 2022-04-13 | 28 | 2022-05-11 | 2022-05-10 | 1275030.41 | 926763.57 | 897908 | 7663208.07 | [6 empty] | 330996.915 | 330996.915 | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication3
MDF Factory - Local Fabrication | 4 | 2022-05-31 | 2022-05-15 | 2022-05-26 | 28 | 2022-06-23 |  |  |  | 667444 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication4
MDF Factory - Local Fabrication | 5 | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 | 2022-06-20 | 3437985.57 | 2517906.93 | 2517907.41 | 11948651.83 | [6 empty] | 597432.59 | 597432.59 | 45737 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication5
MDF Factory - Local Fabrication | 6 | 2022-07-31 | 2022-07-15 | 2022-08-11 | 28 | 2022-09-08 | 2022-09-22 | 1016613.3233 | 737044.172 | 737043.71 | 12965265.1533 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication6
MDF Factory - Local Fabrication | 7 | 2022-08-31 | 2022-08-15 | 2022-08-30 | 28 | 2022-09-27 | 2022-09-22 | 2281868.7949 | 785269.1906 | 785269 | 15247133.9482 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication7
MDF Factory - Local Fabrication | 8 | 2022-09-30 | 2022-09-15 | 2022-09-22 | 28 | 2022-10-20 | 2022-09-22 | 619278.6162 | 1318063.6318 | 381060.37 | 15866412.5644 | [8 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication8
MDF Factory - Local Fabrication | 9 | 2022-10-31 | 2022-11-15 | 2022-11-16 | 28 | 2022-12-14 |  |  |  | 1752018.76 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication9
MDF Factory - Local Fabrication | 10 | 2022-11-30 | 2022-12-15 | 2022-12-26 | 28 | 2023-01-23 |  |  |  | 2881529.05 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication10
MDF Factory - Local Fabrication | 11 | 2023-01-31 | 2023-01-15 | 2023-02-18 | 28 | 2023-03-18 |  |  |  | 2412700.43 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication11
MDF Factory - Local Fabrication | 12 | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 |  |  |  | 0 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication12
MDF Factory - Local Fabrication | 13 | 2023-06-30 | 2023-06-15 | 2023-06-21 | 28 | 2023-07-19 |  |  |  | 0 | [9 empty] | 0 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication13
MDF Factory - Local Fabrication | 14 | 2023-07-31 | 2023-08-15 | 2023-08-29 | 28 | 2023-09-26 | 2023-10-02 | 12083527.18 | 11829412.85 | 10315795 | 41889851.51 |  |  |  | 24971308.61 |  |  | 2094492.575 | 2094492.575 | 112541 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication14
MDF Factory - Local Fabrication | 15 | 2023-08-31 | 2023-10-15 | 2023-11-08 | 28 | 2023-12-06 | 2023-12-18 | 5403242.47 | 5457274.9 | 2970230 | 47293093.98 | [6 empty] | 2364654.7 | 2364654.7 | 112541 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication15
MDF Factory - Local Fabrication | 16 | 2023-11-30 | 2023-11-15 | 2023-12-03 | 28 | 2023-12-31 | 2024-02-11 | 1250000 | 1262500 | 1262500 | 48543093.98 | [6 empty] | 2427154.7 | 2427154.7 | 66804 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication16
MDF Factory - Local Fabrication | 17 | 2023-12-31 | 2023-12-25 | 2023-12-25 | 28 | 2024-01-22 | 2024-04-22 | -0.001 | 0.0001 | 0 | 48543093.98 | [6 empty] | 2427154.7 | 2427154.7 | 112541 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication17
MDF Factory - Local Fabrication | 18 | 2024-01-31 | 2024-01-15 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-22 | 4414101.95 | 4458904.86 | 4265111 | 52957195.93 | [6 empty] | 2647859.795 | 2647859.795 | 112541 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication18
MDF Factory - Local Fabrication | 19 | 2024-02-29 | 2024-03-15 | 2024-03-20 | 28 | 2024-04-17 | 2024-04-04 | 4220898.94 | 4456901.8 | 3358613 | 57178094.87 | [6 empty] | 2858904.5 | 2858904.5 | 882541 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication19
MDF Factory - Local Fabrication | 20 | 2024-05-31 | 2024-05-15 | 2024-07-03 | 28 | 2024-07-31 | 2024-07-29 | 1196029.38 | 2286278.72 | 0 | 58374124.25 | [6 empty] | 2918706 | 2918706 | 66804 | MDF Factory | [7 empty] | MDF Factory - Local Fabrication20
Mechanical Installation | 1 | 2024-01-31 | 2024-01-31 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 96641266.36 | 2845427.8 | 15000000 | 96641266.36 | 15000000 | [7 empty] | 0 | EGAT Mechanical Installations | [7 empty] | Mechanical Installation1
Mechanical Installation | 9 | 2024-05-31 | 2024-05-31 | 2024-06-01 | 42 | 2024-07-13 |  |  |  | 0 | [9 empty] | 0 | EGAT Mechanical Installations | [7 empty] | Mechanical Installation9
Mintra | 1 | 2018-05-31 | 2018-05-29 | 2018-07-09 | 15 | 2018-07-24 | 2018-09-18 | 26487256.44 | 2860852.09 | 15500000 | 26487256.44 | 10000000 |  | 0 | [5 empty] | 17226261.898 | 0 | [7 empty] | Mintra1
Mintra | 2 | 2018-07-31 | 2018-07-21 | 2018-07-25 | 15 | 2018-08-09 | 2018-09-23 | 16295714.9 | 1791407.73 | 3000000 | 42782971.34 |  |  | 3426213 | [5 empty] | 31002926.91 | 0 | [7 empty] | Mintra2
Mintra | 3 | 2018-08-31 | 2018-09-15 | 2018-09-23 | 15 | 2018-10-08 | 2018-10-15 | 19469085.79 | 2220782.14 | 2220782.14 | 62252057.13 |  |  | 0 | [5 empty] | 41220014.7 | 0 | [7 empty] | Mintra3
Mintra | 4 | 2018-09-30 | 2018-10-10 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-18 | 9723925.4204 | 2907075.5801 | 3500000 | 71975982.5504 | [8 empty] | 47988244.922 | 0 | [7 empty] | Mintra4
Mintra | 5 | 2018-11-30 | 2018-12-10 | 2018-12-18 | 15 | 2019-01-02 |  |  |  | 8000000 | [9 empty] | 0 | 0 | [7 empty] | Mintra5
Mintra | 6 | 2019-03-31 | 2019-03-28 | 2019-04-15 | 15 | 2019-04-30 |  |  |  | 6000000 | [9 empty] | 0 | 0 | [7 empty] | Mintra6
Mintra | 7 | 2019-09-30 | 2019-11-17 | 2021-02-03 | 15 | 2021-02-18 |  |  |  | 2005948.91 | [10 empty] | 0 | [7 empty] | Mintra7
Mintra-Hanger 1200m2 | 1 | 2018-10-31 | 2018-10-18 | 2018-10-21 | 15 | 2018-11-05 | 2018-10-29 | 1411985.3421 | 531998.6721 | 531998.67 | 1411985.3421 | [8 empty] | 879986.67 | 0 | [7 empty] | Mintra-Hanger 1200m21
Mintra-Hanger 1200m2 | 2 | 2019-09-30 | 2019-09-30 | 2021-02-03 | 15 | 2021-02-18 |  |  |  | -6217.18 | [9 empty] | 0 | 0 | [7 empty] | Mintra-Hanger 1200m22
Mivida-PK#140 | 1 | 2019-05-31 | 2019-05-31 | 2019-06-10 | 40 | 2019-07-20 | 2019-06-27 | 4797449.5194 | 2533668.0255 | 18101272.3255 | 4797449.5194 | 15567604.3 |  | 0 | [5 empty] | 45335.898 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1401
Mivida-PK#140 | 2 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 40 | 2019-08-13 | 2019-07-21 | 4911239.0806 | 2620895.13 | 9934857.73 | 9708688.6 | 7313962.6 | [7 empty] | 91747.11 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1402
Mivida-PK#140 | 3 | 2019-07-31 | 2019-07-31 | 2019-08-04 | 40 | 2019-09-13 | 2019-08-20 | 6244069.8629 | 4070832.3885 | 4070832.3885 | 15952758.4629 |  |  | 207615.6315 | [5 empty] | 152651.9264 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1403
Mivida-PK#140 | 4 | 2019-08-31 | 2019-08-31 | 2019-09-01 | 40 | 2019-10-11 | 2019-09-17 | 2442385.7689 | 999645.4398 | 999645.4398 | 18395144.2317 |  |  | 207615.6315 | [5 empty] | 175732.4719 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1404
Mivida-PK#140 | 5 | 2019-09-30 | 2019-09-30 | 2019-10-02 | 40 | 2019-11-11 | 2019-10-23 | 1994559.8383 | 1337507.07 | 1337507.07 | 20389704.07 |  |  | 207615.63 | [5 empty] | 194581.06 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1405
Mivida-PK#140 | 6 | 2019-10-31 | 2019-11-06 | 2019-11-06 | 40 | 2019-12-16 | 2019-12-10 | 12232780.54 | 10719905.2391 | 10719905.22 | 32622484.61 |  |  | 1084016.3529 | [5 empty] | 318038.6268 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1406
Mivida-PK#140 | 7 | 2019-11-30 | 2019-12-05 | 2019-12-05 | 40 | 2020-01-14 | 2019-12-19 | 7170532.1164 | 6547225.8223 | 6547225.82 | 39793016.7264 |  |  | 1960077.2048 | [5 empty] | 414859.7029 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1407
Mivida-PK#140 | 8 | 2019-12-31 | 2020-01-06 | 2020-01-06 | 40 | 2020-02-15 | 2020-02-13 | 6113446.7536 | 4740517.5525 | 4740517.5525 | 45906463.48 |  |  | 1612694.6715 | [5 empty] | 473905.3319 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1408
Mivida-PK#140 | 9 | 2020-01-31 | 2020-02-05 | 2020-02-06 | 40 | 2020-03-17 | 2020-03-18 | 4233335.7568 | 4559999.0726 | 4559999.09 | 50139799.2368 |  |  | 3026730.6056 | [5 empty] | 545336.6782 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#1409
Mivida-PK#140 | 10 | 2020-02-29 | 2020-03-05 | 2020-03-05 | 40 | 2020-04-14 | 2020-04-29 | 6612227.7834 | 5679423.0614 | 5679423.0614 | 56752027.0202 |  |  | 3351448.8206 | [5 empty] | 610744.6947 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14010
Mivida-PK#140 | 11 | 2020-03-31 | 2020-04-02 | 2020-04-02 | 40 | 2020-05-12 | 2020-04-29 | 3124627.5928 | 2647674.1799 | 2647674.17 | 59876654.613 |  |  | 3468836.925 | [5 empty] | 649303.9184 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14011
Mivida-PK#140 | 12 | 2020-04-30 | 2020-05-02 | 2020-05-03 | 40 | 2020-06-12 | 2020-05-21 | 1875813.048 | 4687303.4253 | 4687303.44 | 61752467.661 |  |  | 7497245.0417 | [5 empty] | 703286.0248 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14012
Mivida-PK#140 | 13 | 2020-05-31 | 2020-06-01 | 2020-06-01 | 40 | 2020-07-11 | 2020-06-21 | 1425866.309 | 1169770.65 | 1169770.65 | 63178333.97 |  |  | 7496958.47 | [5 empty] | 52250 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14013
Mivida-PK#140 | 14 | 2020-06-30 | 2020-07-01 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-21 | 2429362.3736 | 7336701.0997 | 7336701.1 | 65607696.3436 |  |  | 14334387.2636 | [5 empty] | 52250 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14014
Mivida-PK#140 | 15 | 2020-07-31 | 2020-07-28 | 2020-08-06 | 40 | 2020-09-15 | 2020-08-24 | 16266667.6714 | 10305723.5244 | 10305723.52 | 81874364.0149 |  |  | 10470685.8866 | [5 empty] | 74750 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14015
Mivida-PK#140 | 16 | 2020-08-31 | 2020-09-01 | 2020-09-01 | 40 | 2020-10-11 | 2020-09-15 | 19380294.5984 | 10553431.2394 | 10553431.24 | 101254658.6133 |  |  | 3625858.6756 | [5 empty] | 74750 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14016
Mivida-PK#140 | 17 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 40 | 2020-11-13 | 2020-10-19 | 16610857.3328 | 11726998.4266 | 11726998.43 | 117865515.946 |  |  | 808207.3196 | [5 empty] | 74750 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14017
Mivida-PK#140 | 18 | 2020-10-31 | 2020-11-04 | 2020-11-09 | 40 | 2020-12-19 | 2020-11-29 | 4603925.7609 | 3831058.93 | 3831058.93 | 122469441.707 |  |  | 876421.358 | [5 empty] | 74750 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14018
Mivida-PK#140 | 19 | 2020-11-30 | 2020-12-03 | 2020-12-06 | 40 | 2021-01-15 | 2020-12-21 | 11459315.8636 | 8885358.6191 | 8885358.62 | 133928757.5706 |  |  | 214106.8575 | [5 empty] | 74750 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14019
Mivida-PK#140 | 20 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-04 | 5957491.0722 | 5084359.8248 | 5084359.83 | 139886248.6428 |  |  | 17194.8 | [5 empty] | 85700 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14020
Mivida-PK#140 | 21 | 2021-01-31 | 2021-02-04 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-18 | 9991628.9772 | 8185193.8344 | 8185193.83 | 149877877.62 | [8 empty] | 85700 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14021
Mivida-PK#140 | 22 | 2021-02-28 | 2021-03-04 | 2021-03-15 | 40 | 2021-04-24 | 2021-04-01 | 5467007.07 | 4603109.16 | 4603109.14 | 155344884.69 | [8 empty] | 85700 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14022
Mivida-PK#140 | 23 | 2021-03-31 | 2021-04-04 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-26 | 4716911.44 | 3870461.69 | 3870461.7 | 160061796.13 | [8 empty] | 85700 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14023
Mivida-PK#140 | 24 | 2021-05-31 | 2021-06-04 | 2021-06-30 | 40 | 2021-08-09 | 2021-07-15 | 4573435.8657 | 3732732.7981 | 3732732.7981 | 164635231.9957 | [8 empty] | 105700 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14024
Mivida-PK#140 | 25 | 2021-06-30 | 2021-06-29 | 2021-08-18 | 40 | 2021-09-27 | 2021-08-31 | 5220299.9543 | 9016182.24 | 9016182.24 | 169855531.95 | [8 empty] | 623487.51 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14025
Mivida-PK#140 | 26 | 2021-10-31 | 2021-10-31 | 2021-11-02 | 40 | 2021-12-12 | 2021-11-21 | 3380977.62 | 3143991.79 | 3143991.8 | 173236509.57 | [8 empty] | 623487.51 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14026
Mivida-PK#140 | 27 | 2022-01-31 | 2022-01-15 | 2022-01-25 | 40 | 2022-03-06 | 2022-03-01 | 825139.1896 | 5157960.0562 | 5157960.04 | 174061648.7596 | [6 empty] | 4569118.28 | 4569118.28 | 0 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14027
Mivida-PK#140 | 28 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 40 | 2023-07-18 | 2024-07-09 | 924592.0104 | 1576397.44 | 0 | 174986240.77 | [6 empty] | 4593388.82 | 4593388.82 | 909436.51 | EMAAR- Pkg 140-ITP-Mivida | [7 empty] | Mivida-PK#14028
Mivida-PK#189 | 1 | 2022-05-31 | 2022-05-25 | 2022-05-26 | 40 | 2022-07-05 | 2022-06-16 | 15323108.5333 | 18095262.89 | 117695262.89 | 15323108.5333 | 99600000 |  | 5493727.64 |  |  |  | 559686.37 | 559686.37 | 100000 | Mivida BP#189 | [7 empty] | Mivida-PK#1891
Mivida-PK#189 | 2 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-06 | 28497042.4952 | 22529255.8764 | 22529255.88 | 43820151.0286 |  |  | 5215901.19 |  |  | 1210923 | 1280676.495 | 1280676.495 | 108208.75 | Mivida BP#189 | [7 empty] | Mivida-PK#1892
Mivida-PK#189 | 3 | 2022-07-31 | 2022-08-06 | 2022-08-06 | 40 | 2022-09-15 | 2022-09-04 | 24279069.6762 | 19800407.88 | 19800407.88 | 68099220.7048 |  |  | 5069769.75 |  |  | 4205865.52 | 1914348.785 | 1914348.785 | 115793.25 | Mivida BP#189 | [7 empty] | Mivida-PK#1893
Mivida-PK#189 | 4 | 2022-08-31 | 2022-09-05 | 2022-09-06 | 40 | 2022-10-16 | 2022-10-09 | 28546026.8476 | 27644756.83 | 27644756.83 | 96645247.5524 |  |  | 10542311 |  |  | 4205865.52 | 2800495.535 | 2800495.535 | 171139 | Mivida BP#189 | [7 empty] | Mivida-PK#1894
Mivida-PK#189 | 5 | 2022-09-30 | 2022-10-12 | 2022-10-12 | 40 | 2022-11-21 | 2022-11-05 | 57245166.7876 | 46638711.45 | 46638711.45 | 153890414.34 |  |  | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759 | Mivida BP#189 | [7 empty] | Mivida-PK#1895
Mivida-PK#189 | 6 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | -0.0001 | 70000000 | 70000000 | 153890414.34 |  |  | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759 | Mivida BP#189 | [7 empty] | Mivida-PK#1896
Mivida-PK#189 | 7 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | 39773865.3076 | 38664242.9 | 38664242.89 | 193664279.6476 |  |  | 7682397 |  |  | 14543436.55 | 5529931.65 | 5529931.65 | 187759 | Mivida BP#189 | [7 empty] | Mivida-PK#1897
Mivida-PK#189 | 8 | 2022-11-30 | 2022-12-12 | 2022-12-14 | 40 | 2023-01-23 | 2023-01-01 | 90047890.8024 | 62566272.81 | 62566272.8 | 283712170.45 |  |  | 3898975.5 |  |  | 19923003.68 | 7544918.86 | 7544918.86 | 608067.35 | Mivida BP#189 | [7 empty] | Mivida-PK#1898
Mivida-PK#189 | 9 | 2022-12-31 | 2023-01-05 | 2023-01-09 | 40 | 2023-02-18 | 2023-01-24 | 42271935.09 | 37089197.56 | 37089198 | 325984105.54 |  |  | 7037273.25 |  |  | 24970230.92 | 8733014.6 | 8733014.6 | 657611 | Mivida BP#189 | [7 empty] | Mivida-PK#1899
Mivida-PK#189 | 10 | 2023-01-31 | 2023-02-01 | 2023-02-01 | 40 | 2023-03-13 | 2023-02-26 | 29038558.46 | 22123110.41 | 22123110.41 | 355022664 |  |  | 7032573.83 |  | 285000 | 27238935.45 | 9495159.275 | 9495159.275 | 573417.35 | Mivida BP#189 | [7 empty] | Mivida-PK#18910
Mivida-PK#189 | 11 | 2023-02-28 | 2023-03-01 | 2023-03-08 | 40 | 2023-04-17 | 2023-04-10 | 23000800.56 | 18794302.38 | 18794302.39 | 378023464.56 |  |  | 6675607.4 |  | 55000 | 34635720.71 | 10090006.13 | 10090006.13 | 603461 | Mivida BP#189 | [7 empty] | Mivida-PK#18911
Mivida-PK#189 | 12 | 2023-03-31 | 2023-04-01 | 2023-04-09 | 40 | 2023-05-19 | 2023-05-08 | 15682494.86 | 16890748.07 | 16890748.06 | 393705959.42 |  |  | 11930576.4 |  | 90000 | 36499853.4 | 10633045.845 | 10633045.845 | 652617.35 | Mivida BP#189 | [7 empty] | Mivida-PK#18912
Mivida-PK#189 | 13 | 2023-04-30 | 2023-05-05 | 2023-05-09 | 40 | 2023-06-18 | 2023-06-06 | 16636045.76 | 50032149.1 | 50032149.11 | 410342005.18 |  |  | 58593047.95 | 1714555.5 | 140000 | 38456764.67 | 12236303.835 | 12236303.835 | 686786.1 | Mivida BP#189 | [7 empty] | Mivida-PK#18913
Mivida-PK#189 | 14 | 2023-05-31 | 2023-06-05 | 2023-06-05 | 40 | 2023-07-15 | 2023-07-15 | 22729528.92 | 22045664.4 | 22045664.4 | 433071534.1 |  |  | 63146488.9 | 3995594.72 | 240000 | 42393533.94 | 12946789.995 | 12946789.995 | 750242.35 | Mivida BP#189 | [7 empty] | Mivida-PK#18914
Mivida-PK#189 | 15 | 2023-06-30 | 2023-07-13 | 2023-07-18 | 40 | 2023-08-27 | 2023-08-07 | 18379426.49 | 20013901.03 | 20013901.02 | 451450960.59 |  |  | 71534780.44 | 7645358.03 | 330000 | 45605336.83 | 13638957.225 | 13638957.225 | 782829.85 | Mivida BP#189 | [7 empty] | Mivida-PK#18915
Mivida-PK#189 | 16 | 2023-07-31 | 2023-08-15 | 2023-08-17 | 40 | 2023-09-26 | 2023-09-20 | 24459783.7762 | 22512171.8728 | 22512171.88 | 475910744.3662 |  |  | 78434225.1876 | 8773118.9707 | 230000 | 50069955.0917 | 14453512.665 | 14453512.665 | 832885.35 | Mivida BP#189 | [7 empty] | Mivida-PK#18916
Mivida-PK#189 | 17 | 2023-09-30 | 2023-09-25 | 2023-09-27 | 40 | 2023-11-06 | 2023-10-17 | 30434807.7338 | 47104890.06 | 47104890.0563 | 506345552.1 |  |  | 73723080.15 | 9982715.55 | 390000 | 53354142.27 | 15134647.745 | 15134647.745 | 859629.1 | Mivida BP#189 | [7 empty] | Mivida-PK#18917
Mivida-PK#189 | 18 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 40 | 2023-12-10 | 2023-12-02 | 18563752.6 | 20024965.62 | 20024965.62 | 524909304.7 |  |  | 79805243.6 | 11738051.38 | 340000 | 54783582.6 | 15774000.34 | 15774000.34 | 870216.6 | Mivida BP#189 | [7 empty] | Mivida-PK#18918
Mivida-PK#189 | 19 | 2023-11-30 | 2023-11-25 | 2023-12-02 | 40 | 2024-01-11 | 2024-01-02 | 21710553.3095 | 23323710.1 | 23323710.11 | 546619858.0095 |  |  | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1 | Mivida BP#189 | [7 empty] | Mivida-PK#18919
Mivida-PK#189 | 20 | 2023-11-30 | 2023-11-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-11 | -0.0003 |  | 135145955 | 546619858.0095 |  | 135145955 | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1 | Mivida BP#189 | [7 empty] | Mivida-PK#18920
Mivida-PK#189 | 21 | 2023-12-31 | 2023-12-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-24 | 22586754.7048 | 14476604.63 | 14476604.63 | 569206612.7143 |  |  | 81314246.26 | 16546391.27 | 130000 | 59318989.42 | 16974529.74 | 16974529.74 | 807307.6 | Mivida BP#189 | [7 empty] | Mivida-PK#18921
Mivida-PK#189 | 22 | 2024-01-31 | 2024-01-30 | 2024-02-04 | 40 | 2024-03-15 | 2024-02-27 | 23140993.5357 | 17552609 | 17552608.99 | 592347606.25 |  |  | 88194427.7 | 17630743.31 | 130000 | 61582414.39 | 17753985.355 | 17753985.355 | 900122.85 | Mivida BP#189 | [7 empty] | Mivida-PK#18922
Mivida-PK#189 | 23 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 40 | 2024-04-15 | 2024-04-21 | 30858954.27 | 14242173.08 | 14242173.09 | 623206560.52 |  |  | 84128553.28 | 31879195.04 | 260000 | 64992287.15 | 18462386.045 | 18462386.045 | 912222.85 | Mivida BP#189 | [7 empty] | Mivida-PK#18923
Mivida-PK#189 | 24 | 2024-03-31 | 2024-03-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-05-22 | 16112816.1181 | 13803484.93 | 13803484.92 | 639319376.6381 |  |  | 96423729.78 | 32655160.1 | 130000 | 66746916.67 | 19192726.88 | 19192726.88 | 1304406.85 | Mivida BP#189 | [7 empty] | Mivida-PK#18924
Mivida-PK#189 | 25 | 2024-04-30 | 2024-04-30 | 2024-05-09 | 40 | 2024-06-18 | 2024-06-06 | 29437278.3119 | 28360739.45 | 28360739.45 | 668756654.95 |  |  | 101680151.25 | 44526060.5 | 30000 | 69988148.31 | 20096865.975 | 20096865.975 | 1306194.35 | Mivida BP#189 | [7 empty] | Mivida-PK#18925
Mivida-PK#189 | 26 | 2024-05-31 | 2024-05-30 | 2024-06-01 | 40 | 2024-07-11 | 2024-07-03 | 16876594.42 | 14177811.24 | 14177811.26 | 685633249.37 |  |  | 113839940.35 | 49627280.83 | 230000 | 71860776.18 | 20843871.305 | 20843871.305 | 1314994.35 | Mivida BP#189 | [7 empty] | Mivida-PK#18926
Mivida-PK#189 | 27 | 2024-06-30 | 2024-06-30 | 2024-07-01 | 40 | 2024-08-10 | 2024-08-01 | 14919836.13 | 4389859.04 | 4389859.04 | 700553085.5 |  |  | 115715406.16 | 55352768.73 | 130000 | 73509397.76 | 21282403.65 | 21282403.65 | 5470850.6 | Mivida BP#189 | [7 empty] | Mivida-PK#18927
Mivida-PK#189 | 28 | 2024-07-31 | 2024-07-30 | 2024-08-01 | 40 | 2024-09-10 | 2024-08-31 | 3487392.66 | 2409288.21 | 2409288.21 | 704040478.16 |  |  | 115148780.66 | 49698695.44 | 130000 | 73901796.57 | 21359782.07 | 21359782.07 | 5480338.1 | Mivida BP#189 | [7 empty] | Mivida-PK#18928
Mivida-PK#189 | 29 | 2024-08-31 | 2024-08-31 | 2024-09-18 | 40 | 2024-10-28 | 2024-09-26 | 369049.79 | 2690517.47 | 2690517.47 | 704409527.95 |  |  | 118334746.14 | 36219473.08 | 230000 | 73927905.13 | 21449118.76 | 21449118.76 | 5482400 | Mivida BP#189 | [7 empty] | Mivida-PK#18929
Mivida-PK#189 | 30 | 2024-09-30 | 2024-09-30 | 2024-10-09 | 40 | 2024-11-18 | 2024-11-12 | 17653522.66 | 14412191.13 | 14412191.12 | 722063050.61 |  |  | 118972314.89 | 37380637.32 | 230000 | 80926432.97 | 22053462.95 | 22053462.95 | 9961433.24 | Mivida BP#189 | [7 empty] | Mivida-PK#18930
Mivida-PK#189 | 31 | 2024-10-31 | 2024-10-31 | 2024-11-01 | 40 | 2024-12-11 |  |  |  | 0 | [9 empty] | 0 | Mivida BP#189 | [7 empty] | Mivida-PK#18931
Mobilization | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-02-28 | 3847983.19 | 475188.5 | 0 | 3847983.19 | [8 empty] | 0 | 0 | [7 empty] | Mobilization1
MOC | 1 | 2024-05-31 | 2024-06-08 | 2024-05-05 | 40 | 2024-06-14 |  |  |  | 33350000 | [9 empty] | 0 | MOC HQ at Diriyah | [7 empty] | MOC1
MOC | 2 | 2024-06-30 | 2024-07-15 | 2024-07-15 | 40 | 2024-08-24 |  |  |  | 0 | [9 empty] | 0 | MOC HQ at Diriyah | [7 empty] | MOC2
MOC - DP | 1 | 2024-04-30 | 2024-04-01 | 2024-04-01 | 40 | 2024-05-11 |  |  |  | 0 | [9 empty] | 0 | MOC HQ at Diriyah | [7 empty] | MOC - DP1
New Gas Station | 1 | 2023-10-31 | 2023-10-31 | 2023-11-02 | 42 | 2023-12-14 | 2023-11-02 | 3190160 | 2360718.4 | 2201210.4 | 3190160 | [8 empty] | 0 | New Giza Teaching Hospital | [7 empty] | New Gas Station1
New Gas Station | 2 | 2023-12-31 | 2023-12-31 | 2024-01-01 | 42 | 2024-02-12 |  |  |  | 1419355.25 | [9 empty] | 0 | New Giza Teaching Hospital | [7 empty] | New Gas Station2
New Gas Station | 3 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 42 | 2024-03-14 | 2024-02-07 | 2793703.2 | 1433129.44 | 0 | 7183858 | [8 empty] | 0 | New Giza Teaching Hospital | [7 empty] | New Gas Station3
New Gas Station | 4 | 2024-04-30 | 2024-04-21 | 2024-04-21 | 42 | 2024-06-02 | 2024-04-28 | 6707619.99 | 4963638.79 | 0 | 13891477.99 | [8 empty] | 0 | New Giza Teaching Hospital | [7 empty] | New Gas Station4
New Giza Hospital | 1 | 2022-01-31 | 2022-01-30 | 2022-02-01 | 51 | 2022-03-24 | 2022-02-14 | 34312846.6 | 23504299.92 | 111673736 | 34312846.6 | 73512565 | [7 empty] | 0 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital1
New Giza Hospital | 2 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 51 | 2022-04-25 | 2022-03-21 | 20701192.62 | 13966904.63 | 16948027.1724 | 55014039.22 | [8 empty] | 0 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital2
New Giza Hospital | 3 | 2022-03-31 | 2022-03-15 | 2022-03-20 | 51 | 2022-05-10 | 2022-03-28 | -0.0001 | 7088017.77 | 7088017 | 55014039.22 | [6 empty] | 1642229.32 | 1642229.32 | 0 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital3
New Giza Hospital | 4 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 51 | 2022-05-27 | 2022-04-24 | 43472048.71 | 25608972.36 | 25531752 | 98486087.93 | [6 empty] | 2584225.375 | 2584225.375 | 0 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital4
New Giza Hospital | 5 | 2022-04-30 | 2022-05-10 | 2022-05-10 | 51 | 2022-06-30 | 2022-05-25 | 15040366.17 | 10219240.4 | 9692684 | 113526454.1 | [5 empty] | 12821619 | 2978829.635 | 2978829.635 | 447088.63 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital5
New Giza Hospital | 6 | 2022-05-31 | 2022-05-31 | 2022-06-15 | 51 | 2022-08-05 | 2022-06-21 | 21219859 | 14292844 | 12645886 | 134746313.1 | [5 empty] | 12821619 | 3534103.595 | 3534103.595 | 0 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital6
New Giza Hospital | 7 | 2022-06-30 | 2022-06-30 | 2022-06-23 | 51 | 2022-08-13 | 2022-07-04 | 20073764.28 | 13315074.93 | 12694720 | 154820077.38 | [5 empty] | 12821619.84 | 4060000.94 | 4060000.94 | 0 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital7
New Giza Hospital | 8 | 2022-07-31 | 2022-08-07 | 2022-08-23 | 51 | 2022-10-13 | 2022-08-28 | 18180164.07 | 12573205.03 | 11865059 | 173000241.45 | [5 empty] | 12821619 | 4536350.625 | 4536350.625 | 2987283.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital8
New Giza Hospital | 9 | 2022-08-31 | 2022-09-11 | 2022-09-14 | 51 | 2022-11-04 | 2022-09-22 | 23318711.12 | 15620677.42 | 15594713 | 196318952.57 | [5 empty] | 12821619.84 | 5147515.86 | 5147515.86 | 3790429.25 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital9
New Giza Hospital | 10 | 2022-09-30 | 2022-10-15 | 2022-10-18 | 51 | 2022-12-08 | 2022-11-03 | 22254898.64 | 14944068.34 | 14931468 | 218573851.21 | [5 empty] | 12821619.84 | 5731166.305 | 5731166.305 | 3910342.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital10
New Giza Hospital | 11 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 51 | 2022-12-31 | 2022-12-07 | 29701638.2 | 19999087.83 | 19979218 | 248275489.41 |  |  |  | 47447.2 |  | 12821619.84 | 6509322.02 | 6509322.02 | 3819797.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital11
New Giza Hospital | 12 | 2022-11-30 | 2022-12-06 | 2022-12-08 | 51 | 2023-01-28 | 2022-12-29 | 25988546.64 | 21046664.64 | 21023839 | 274264036.05 |  |  | 4878335.3 | 1113844.57 |  | 12821619.84 | 7307779.5 | 7307779.5 | 3966447.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital12
New Giza Hospital | 13 | 2022-12-31 | 2023-01-05 | 2023-01-08 | 51 | 2023-02-28 | 2023-02-06 | 24670486.27 | 18169651.25 | 17903308 | 298934522.32 |  |  | 7074573 | 1237105.25 |  | 12821619.84 | 8008229.795 | 8008229.795 | 3886497.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital13
New Giza Hospital | 14 | 2023-01-31 | 2023-02-11 | 2023-02-09 | 51 | 2023-04-01 | 2023-03-14 | 21692266.85 | 14731551.62 | 15197022 | 320626789.17 |  |  | 6879606.09 | 1773014.33 |  | 12821619.84 | 8574509.66 | 8574509.66 | 4107797.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital14
New Giza Hospital | 15 | 2023-02-28 | 2023-03-14 | 2023-03-16 | 51 | 2023-05-06 | 2023-04-18 | 23725978.81 | 14839693.08 | 7535461 | 344352767.98 |  |  | 5193267.92 | 2584321.32 |  | 12821619.84 | 9154018.005 | 9154018.005 | 4143497.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital15
New Giza Hospital | 16 | 2023-04-30 | 2023-04-19 | 2023-04-30 | 51 | 2023-06-20 | 2023-05-14 | 22492246.1 | 15222233.72 | 7643976 | 366845014.08 |  |  | 4834698.32 | 3206608.76 |  | 12821619.84 | 9734385.435 | 9734385.435 | 3938997.85 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital16
New Giza Hospital | 17 | 2023-05-31 | 2023-05-31 | 2023-06-03 | 51 | 2023-07-24 | 2023-07-04 | 21612019.52 | 12680990.84 | 0 | 388457033.6 |  |  | 4817538.46 | 3364840.52 |  | 12821619.84 | 10300141.21 | 10300141.21 | 6117327.71 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital17
New Giza Hospital | 18 | 2023-06-30 | 2023-07-09 | 2023-07-12 | 51 | 2023-09-01 | 2023-08-06 | 9332664.78 | 14934202.65 | 14511461 | 397789698.38 |  |  | 21298296.55 | 3366900.3 |  | 12821619.84 | 10955551.155 | 10955551.155 | 6117327.71 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital18
New Giza Hospital | 19 | 2023-08-31 | 2023-08-12 | 2023-08-13 | 51 | 2023-10-03 | 2023-09-14 | 18985757.51 | 5705542.36 | 3705542 | 416775455.89 |  |  | 10041623.17 | 3890054.47 |  | 12821619.84 | 11172226.045 | 11172226.045 | 6117327.71 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital19
New Giza Hospital | 20 | 2023-09-30 | 2023-09-30 | 2023-09-27 | 51 | 2023-11-17 | 2023-10-03 | -1e-07 | 18995740.42 | 18995740 | 416775455.89 |  |  | 10041623.17 | 3890054.47 |  | 12821619.84 | 22344452.09 |  | 6117327.71 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital20
New Giza Hospital | 21 | 2023-09-30 | 2023-09-30 | 2023-10-16 | 51 | 2023-12-06 | 2023-10-16 | 12758386.3 | 8010369.24 | 4008305 | 429533842.19 |  |  | 9402295.53 | 3259999.96 |  | 12821619 | 22981285.53 |  | 6117327.71 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital21
New Giza Hospital | 22 | 2023-10-31 | 2023-11-05 | 2023-11-08 | 51 | 2023-12-29 | 2023-11-30 | 18598623.84 | 8695249.6 | 6681249 | 448132466.03 |  |  | 2678290.23 | 4983458.07 |  | 12821619.84 | 23620700.79 |  | 6119391.71 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital22
New Giza Hospital | 23 | 2023-11-30 | 2023-12-10 | 2023-12-12 | 51 | 2024-02-01 | 2024-01-27 | 9056705.71 | 4604562.68 | 3104562 | 457189171.74 |  |  | 2083276.16 | 4983458.07 |  | 12821619.84 | 24065214.3 |  | 6133391.71 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital23
New Giza Hospital | 24 | 2024-01-31 | 2024-02-12 | 2024-02-13 | 51 | 2024-04-04 | 2024-04-01 | 30645299.93 | 5494905.78 | 4494905.88 | 487834471.67 |  |  | 1034048.23 | 5018947.83 |  | 12821619.84 | 25619451 |  | 8956130 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital24
New Giza Hospital | 25 | 2024-03-31 | 2024-04-06 | 2024-04-07 | 51 | 2024-05-28 | 2024-01-05 | 12955562.12 | 10195246.28 | 10195246 | 500790033.79 |  |  | 421352.25 | 12168583.45 |  | 12821619.84 | 26268325.91 |  | 8956130.8 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital25
New Giza Hospital | 26 | 2024-04-30 | 2024-05-12 | 2024-05-29 | 51 | 2024-07-19 | 2024-06-13 | 15191903.43 | 17232986.3 | 18129119.1724 | 515981937.22 |  |  | 268661.25 | 14260202.71 |  |  | 27057529.55 |  | 23641604 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital26
New Giza Hospital | 27 | 2024-06-30 | 2024-07-14 | 2024-07-16 | 51 | 2024-09-05 | 2024-08-18 | 16227230.2 | 13715277.6 | 2051894 | 532209167.42 |  |  | 268661.25 | 14260202 |  | 56175000 | 30715749 |  | 20879747 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital27
New Giza Hospital | 28 | 2024-08-31 | 2024-09-11 | 2024-09-12 | 51 | 2024-11-02 | 2024-10-03 | 69437921.36 | 6800969.24 | 5534314 | 601647088.78 |  |  | 268661 | 18531949 |  | 56175000 | 15698247.5 | 15698247.5 | 9038450 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital28
New Giza Hospital | 29 | 2024-10-31 | 2024-10-17 | 2024-10-19 | 51 | 2024-12-09 |  |  |  | 0 | [9 empty] | 0 | New Giza Teaching Hospital | [7 empty] | New Giza Hospital29
NGU 2 | 25 | 2017-09-30 | 2017-10-01 | 2017-09-16 | 28 | 2017-10-14 | 2017-10-11 | 3430150 |  | 2468493.7 | 140490291 |  |  | 1675290.17 | [5 empty] | 807366.8348 | New Giza 2 | [7 empty] | NGU 225
NGU 2 | 26 | 2017-11-30 | 2017-11-30 | 2018-01-23 | 28 | 2018-02-20 | 2018-05-23 | 10391625.25 | 6719251.6 | 4990186 | 150881916.25 |  |  | 0 | [5 empty] | 699355.4648 | New Giza 2 | [7 empty] | NGU 226
NGU 2 | 27 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 28 | 2019-08-01 | 2019-11-02 | 3035230.3681 | 1589855.1267 | 2104161 | 153917146.6181 |  |  | 734008.68 | [5 empty] | 0 | New Giza 2 | [7 empty] | NGU 227
ORA - ZED | 1 | 2020-11-30 | 2020-11-25 | 2020-11-22 | 56 | 2021-01-17 | 2021-01-17 | 2407390.5714 | 10345156.8 | 101168059.79 | 2407390.5714 |  |  | 9271107.2 | [5 empty] | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED1
ORA - ZED | 2 | 2020-12-31 | 2020-12-31 | 2020-12-22 | 56 | 2021-02-16 | 2021-01-06 | 45205427.0762 | 37532508 | 293983829 | 47612817.6476 |  | 256451321 | 9882492.63 | [5 empty] | 10718.8648 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED2
ORA - ZED | 3 | 2021-01-31 | 2021-02-03 | 2021-01-31 | 56 | 2021-03-28 | 2021-02-17 | 26768107.4476 | 27896354 | 78068925.863 | 74380925.0952 |  | 50172571.863 | 17071953.36 | [5 empty] | 24994.28 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED3
ORA - ZED | 4 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 56 | 2021-05-02 | 2021-03-24 | 26593168.5429 | 20888247.393 | 45888247.393 | 100974093.6381 |  | 25000000 | 20604136.5 | [5 empty] | 50275.41 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED4
ORA - ZED | 5 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 56 | 2021-06-01 | 2021-05-11 | 39594206.7048 | 33744386.154 | 83744386.154 | 140568300.3429 |  | 50000000 | 16740725.26 | [5 empty] | 66054.2648 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED5
ORA - ZED | 6 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 56 | 2021-07-05 | 2021-06-08 | 13625124.4935 | 4374377.19 | 14374377.19 | 154193424.8364 |  | 10000000 | 7989637.5618 | [5 empty] | 83003.9348 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED6
ORA - ZED | 7 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 56 | 2021-08-04 | 2021-07-15 | 11321353.516 | 5782895.78 | 10782895.78 | 165514778.3524 |  | 5000000 | 3501497.22 | [5 empty] | 99063.49 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED7
ORA - ZED | 8 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 56 | 2021-08-25 | 2021-08-12 | 26950096.619 | 24387331.1 | 24387331.1 | 192464874.9714 |  |  | 6088729.64 | [5 empty] | 175458.21 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED8
ORA - ZED | 9 | 2021-07-31 | 2021-07-25 | 2021-08-10 | 56 | 2021-10-05 | 2021-09-20 | 27403398.0286 | 22624923.97 | 22624923.97 | 219868273 |  |  | 5900263.67 | [5 empty] | 146376.75 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED9
ORA - ZED | 10 | 2021-08-31 | 2021-08-25 | 2021-09-09 | 56 | 2021-11-04 | 2021-09-26 | 32858070.0667 | 29047725.55 | 29047725.55 | 252726343.0667 |  |  | 8169556.06 | [5 empty] | 164670.96 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED10
ORA - ZED | 11 | 2021-09-30 | 2021-09-25 | 2021-10-14 | 56 | 2021-12-09 | 2021-11-18 | 34769848.6 | 31056565.55 | 0 | 287496191.6667 |  |  | 10971940.82 | [5 empty] | 182298.18 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED11
ORA - ZED | 12 | 2021-10-31 | 2021-10-25 | 2021-11-24 | 56 | 2022-01-19 | 2021-12-07 | 33050531.6762 | 24536445.63 | 0 | 320546723.3429 |  |  | 7308964.38 | [5 empty] | 182298.18 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED12
ORA - ZED | 13 | 2021-11-30 | 2021-11-25 | 2021-12-14 | 56 | 2022-02-08 | 2021-12-21 | 30511414.9714 | 23914152.624 | 0 | 351058138.3143 |  |  | 5524822.34 | [5 empty] | 182298.18 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED13
ORA - ZED | 14 | 2021-12-31 | 2021-12-25 | 2021-12-23 | 56 | 2022-02-17 | 2022-01-18 | 45635766.9524 | 35917954.71 | 0 | 396693905.2667 |  |  | 3084551.02 | [5 empty] | 213053.66 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED14
ORA - ZED | 15 | 2022-01-31 | 2022-01-25 | 2022-02-17 | 56 | 2022-04-14 | 2022-03-31 | 27710999.5429 | 25550073.0625 | 0 | 424404904.8095 |  |  | 6586185.1 | [5 empty] | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED15
ORA - ZED | 16 | 2022-02-28 | 2022-02-25 | 2022-03-16 | 56 | 2022-05-11 | 2022-04-12 | 28676537.6667 | 21942762.07 | 0 | 453081442.4762 |  |  | 4779083.27 |  |  |  | 12012864.945 | 12012864.945 | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED16
ORA - ZED | 17 | 2022-03-31 | 2022-03-25 | 2022-04-06 | 56 | 2022-06-01 | 2022-05-11 | 30883724.2667 | 26002482 | 0 | 483965166.7429 |  |  | 5232577.92 | [5 empty] | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED17
ORA - ZED | 18 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-05-26 | 9956410.019 | 6791166 | 0 | 493921576.7619 |  |  | 3421449.48 | [5 empty] | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED18
ORA - ZED | 19 | 2022-05-31 | 2022-05-25 | 2022-06-06 | 56 | 2022-08-01 | 2022-06-28 | 21443765.7238 | 16483568.4889 | 0 | 515365342.4857 |  |  | 1543331.93 | [5 empty] | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED19
ORA - ZED | 20 | 2022-06-30 | 2022-06-25 | 2022-07-06 | 56 | 2022-08-31 | 2022-08-28 | 25297815.7745 | 8954952.87 | 16483569.19 | 540663158.2602 |  |  | 852186.4268 | [5 empty] | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED20
ORA - ZED | 21 | 2022-07-31 | 2022-07-25 | 2022-08-09 | 56 | 2022-10-04 | 2022-09-11 | 9295356.7831 | 7443624.2902 | 7443623.53 | 549958515.0433 |  |  | 836488.6182 | 81555880.4439 |  | 36726721.206 | 14457323.235 | 14457323.235 | 1401842.4693 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED21
ORA - ZED | 22 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 56 | 2022-11-02 | 2022-09-28 | 9997079.1377 | 8098824.8775 | 8098825.75 | 559955594.181 |  |  | 557383.0572 | 85664325.1821 |  | 36749996.0022 | 14712768.92 | 14712768.92 | 1379966.9772 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED22
ORA - ZED | 23 | 2022-09-30 | 2022-09-25 | 2022-10-09 | 56 | 2022-12-04 | 2022-10-27 | 27314036.0095 | 22964574.875 | 20215840.09 | 587269630.1905 |  |  | 479281.1936 | 93161830.5539 |  | 36812284.0164 | 15427809.82 | 15427809.82 | 1232906.9943 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED23
ORA - ZED | 24 | 2022-12-31 | 2022-12-25 | 2023-01-18 | 56 | 2023-03-15 | 2023-03-22 | 11751887.1042 | 7490234.3814 | 6648903.39 | 599021517.2946 |  |  | 269002.8006 | 98882541.0407 |  | 36839181.7521 | 15725824.83 | 15725824.83 | 3165623.4593 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED24
ORA - ZED | 25 | 2023-02-28 | 2023-02-25 | 2023-03-12 | 56 | 2023-05-07 | 2023-04-10 | 50310527.2958 | -9163815.8569 | 2e-05 | 649332044.5905 |  |  | 241736.3176 | 113559937.642 | 3600000 | 36956312.6915 | 17045794.51 | 17045794.51 | 465623.4593 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED25
ORA - ZED | 26 | 2023-03-31 | 2023-03-25 | 2023-04-16 | 56 | 2023-06-11 | 2023-05-01 | 19434003.5361 | 16993731.7513 | 9808194.12 | 668766048.1265 |  |  | 239033.6571 | 121577515.47 | 2750000 | 37000350.0494 | 17553262 | 17553262 | 465623.4593 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED26
ORA - ZED | 27 | 2023-04-30 | 2023-04-25 | 2023-05-15 | 56 | 2023-07-10 | 2023-06-15 | 10662740.4195 | 9042387.5614 | 8872947.14 | 679428788.546 |  |  | 229309.1567 | 124928010.98 | 2550000 | 37025174.6113 | 17832915.825 | 17832915.825 | 465623.4593 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED27
ORA - ZED | 28 | 2023-05-31 | 2023-05-25 | 2023-06-15 | 56 | 2023-08-10 | 2023-07-09 | 24304667.5968 | 10264179.63 | 9105384.7 | 703733456.1429 |  |  | 156183.3 | 132876310.5982 | 2350000 | 37192477.1578 | 18469085.205 | 18469085.205 | 489541.1493 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED28
ORA - ZED | 29 | 2023-06-30 | 2023-06-25 | 2023-07-17 | 56 | 2023-09-11 | 2023-08-24 | 27532348.019 | 13678389.68 | 10687601.99 | 731265804.1619 |  |  |  | 143774737.6483 | 2400000 | 37381001.7016 | 19187904.7592 | 19187904.7592 | 489541.1493 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED29
ORA - ZED | 30 | 2023-07-31 | 2023-07-25 | 2023-08-15 | 56 | 2023-10-10 | 2023-09-17 | 26015241.1905 | 13092650.18 | 11585957.67 | 757281045.3524 |  |  |  | 149337289.3675 | 1900000 | 37609920.1669 | 19870804.84 | 19870804.84 | 489541.1493 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED30
ORA - ZED | 31 | 2023-08-31 | 2023-08-25 | 2023-09-17 | 56 | 2023-11-12 | 2023-09-27 | 26102241.2286 | 12746258.22 | 10253641.2 | 783383286.581 |  |  |  | 156088918.0852 | 1800000 | 37790500.7321 | 20555988.67 | 20555988.67 | 508143.1541 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED31
ORA - ZED | 32 | 2023-09-30 | 2023-09-25 | 2023-10-12 | 56 | 2023-12-07 | 2023-11-11 | 24532813.9714 | 17052495.52 | 8010573.17 | 807916100.5524 |  |  |  | 169479041.6436 | 1800000 | 37962018.2328 | 21199975.0395 | 21199975.0395 | 566244.2563 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED32
ORA - ZED | 33 | 2023-10-31 | 2023-10-25 | 2023-11-11 | 56 | 2024-01-06 | 2023-12-17 | 20642302.219 | 13971110.85 | 12164893.39 | 828558402.7714 |  |  |  | 183850209.8662 | 1800000 | 38104925.5449 | 21741835.4727 | 21741835.4727 | 728244.2563 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED33
ORA - ZED | 34 | 2023-11-30 | 2023-11-25 | 2023-12-17 | 56 | 2024-02-11 | 2024-01-28 | 14702199.581 | 11514703.33 | 9568963.5 | 843260602.3524 |  |  |  | 188799507.8 | 2350000 | 38207159.3831 | 22127768.21 | 22127768.21 | 866366.5763 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED34
ORA - ZED | 35 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-02-11 | 13918410.7524 | 11302280.92 | 7391485.26 | 857179013.1048 |  |  |  | 199336628.67 | 2600000 | 40055372.1837 | 22493126.49 | 22493126.49 | 866366.5763 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED35
ORA - ZED | 36 | 2024-01-31 | 2024-01-25 | 2024-02-11 | 56 | 2024-04-07 | 2024-03-12 | 9427629.6762 | 30791363.32 | 7054023.71 | 866606642.781 |  |  |  | 202490336.7307 | 2950000 | 40124683.5553 | 22740601.77 | 22740601.77 | 1287275.408 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED36
ORA - ZED | 37 | 2024-02-29 | 2024-02-25 | 2024-03-12 | 56 | 2024-05-07 | 2024-04-24 | 11141064.9524 | 9469567.93 | 23554316.1 | 877747707.7333 |  |  |  | 205574473.0325 | 3350000 | 40202154.5368 | 23033054.728 | 23033054.728 | 1416236.983 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED37
ORA - ZED | 38 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-09 | 15909843.4381 | 12665876.69 | 17627053.17 | 893657551.1714 |  |  |  | 212207212.1568 | 3550000 | 40322143.2235 | 23450688.1182 | 23450688.1182 | 1426063.9 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED38
ORA - ZED | 39 | 2024-04-30 | 2024-04-25 | 2024-05-09 | 56 | 2024-07-04 | 2024-06-06 | 9971577.2286 | 7606231.5 | 7606231.63 | 903629128.4 |  |  |  | 212836770.28 | 5150000 | 40471225.4023 | 23712442.02 | 23712442.02 | 1543257.113 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED39
ORA - ZED | 40 | 2024-05-31 | 2024-05-25 | 2024-06-06 | 56 | 2024-08-01 | 2024-07-01 | 7576454.8952 | 6599009.58 | 3717952.37 | 911205583.2952 |  |  |  | 217295013.586 | 5311993 | 40584498.7969 | 23911323.96 | 23911323.96 | 1866239.86 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED40
ORA - ZED | 41 | 2024-06-30 | 2024-06-25 | 2024-07-16 | 56 | 2024-09-10 | 2024-08-31 | 4542501.819 | 3961614.17 | 4428778.21 | 915748085.1143 |  |  |  | 218624574.9261 | 4611993 | 40652412.433 | 24038387.2343 | 24038387.2343 | 2836219.6905 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED41
ORA - ZED | 42 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-01 | 5377971.181 | 3504951.97 | 70851.77 | 921126056.2952 |  |  |  | 221585074.8608 | 5650000 | 40732816.931 | 24179558.9777 | 24179558.9777 | 3321663.778 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED42
ORA - ZED | 43 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-22 | 11538786.4 | 11004454.56 | 6004454.53 | 932664842.6952 |  |  |  | 225919078.57 | 5200000 | 40983305.2755 | 24482452.12 | 24482452.12 | 3555974.5005 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED43
ORA - ZED | 44 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 5304711.9524 | 4559905.68 | 0 | 937969554.6476 |  |  |  | 231364687.5663 | 5600000 | 41098461.9713 | 24621700.8095 | 24621700.8095 | 3555974.5005 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED44
ORA - ZED | 45 | 2024-10-31 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 |  |  |  | 0 | [9 empty] | 0 | ORA ZED - Ph 01B - Pkgs A&D | [7 empty] | ORA - ZED45
ORA - ZED - Landscape | 1 | 2022-11-30 | 2022-11-25 | 2022-12-11 | 56 | 2023-02-05 | 2022-12-20 | 2611606.8286 | 2167633.6703 | 11802742.07 | 2611606.8286 |  |  |  | 503419.5862 |  |  | 68554.675 | 68554.675 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape1
ORA - ZED - Landscape | 2 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-01 | 2071867.5333 | 1719650.0563 | 1719649.2 | 4683474.3619 |  |  |  | 1329550.324 |  | 30299.3908 | 122941.2 | 122941.2 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape2
ORA - ZED - Landscape | 3 | 2023-01-31 | 2023-01-25 | 2023-01-25 | 56 | 2023-03-22 | 2023-02-26 | 2138801.7905 | 1775205.4809 | 1775205.58 | 6822276.1524 |  |  |  | 2116384.0303 |  | 118260.296 | 179084.745 | 179084.745 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape3
ORA - ZED - Landscape | 4 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-10 | 4909563.9143 | 4074938.0511 | 4074938.81 | 11731840.0667 |  |  |  | 4050371.3819 |  | 639071.4395 | 307960.8 | 307960.8 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape4
ORA - ZED - Landscape | 5 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 3861209.6 | 3204803.968 | 2726488.3 | 15593049.6667 |  |  |  | 5404662.8768 |  | 772348.3981 | 409317.55 | 409317.55 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape5
ORA - ZED - Landscape | 6 | 2023-04-30 | 2023-04-25 | 2023-05-11 | 56 | 2023-07-06 | 2023-06-07 | 3232045.3524 | 3160913.3163 | 3120690.89 | 18825095.019 |  |  |  | 6624089.2242 |  | 816946.8694 | 494158.74 | 494158.74 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape6
ORA - ZED - Landscape | 7 | 2023-05-31 | 2023-05-25 | 2023-06-07 | 56 | 2023-08-02 | 2023-07-17 | 1440674.7619 | 1045760.0532 | 964764.3 | 20265769.781 |  |  |  | 7155995.1362 |  | 835084.5832 | 531976.455 | 531976.455 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape7
ORA - ZED - Landscape | 8 | 2023-06-30 | 2023-06-25 | 2023-07-09 | 56 | 2023-09-03 | 2023-08-09 | 11600772.2694 | 9578640.9799 | 5158038.94 | 31866542.0504 |  |  |  | 10056562.0507 | 200000 | 5892201.0451 | 836496.7288 | 836496.7288 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape8
ORA - ZED - Landscape | 9 | 2023-07-31 | 2023-07-25 | 2023-08-07 | 56 | 2023-10-02 | 2023-09-17 | 3994751.4353 | 3636861.9198 | 3863087.97 | 35861293.4857 |  |  |  | 10889989.7064 |  | 5974589.29 | 941358.95 | 941358.95 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape9
ORA - ZED - Landscape | 10 | 2023-08-31 | 2023-08-25 | 2023-09-10 | 56 | 2023-11-05 | 2023-10-10 | 3258480.2857 | 2654538.63 | 6562980.72 | 39119773.7714 |  |  |  | 12128157.28 | 50000 | 6008554.2 | 1026894.06 | 1026894.06 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape10
ORA - ZED - Landscape | 11 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-04 | 6742108.1048 | 6014170.71 | 5312426.17 | 45861881.8762 |  |  |  | 14252099.55 | 100000 | 6064800 | 1203874 | 1203874 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape11
ORA - ZED - Landscape | 12 | 2023-10-31 | 2023-10-25 | 2023-11-06 | 56 | 2024-01-01 | 2023-11-20 | 9303031.3714 | 7521516.04 | 6030251.47 | 55164913.2476 |  |  |  | 16356170.6 | 300000 | 6136800.24 | 1448078.975 | 1448078.975 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape12
ORA - ZED - Landscape | 13 | 2023-11-30 | 2023-11-25 | 2023-12-11 | 56 | 2024-02-05 | 2024-02-20 | -692002.6286 | -674362.19 | 0 | 54472910.619 |  |  |  | 13854310.92 | 400000 | 6133954.27 | 1429913.905 | 1429913.905 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape13
ORA - ZED - Landscape | 14 | 2023-12-31 | 2023-12-25 | 2024-01-16 | 56 | 2024-03-12 | 2024-03-20 | 1197004.6952 | 1008333.54 | 868255.79 | 55669915.3143 |  |  |  | 14304471.38 | 385180.36 | 6143327.5 | 1461335.275 | 1461335.275 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape14
ORA - ZED - Landscape | 15 | 2024-01-31 | 2024-01-25 | 2024-02-06 | 56 | 2024-04-02 | 2024-04-20 | 3753240.219 | 5175911.36 | 3165189.2 | 59423155.5333 |  |  |  | 16680600.84 | 335180.36 | 5731208.99 | 1559857.835 | 1559857.835 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape15
ORA - ZED - Landscape | 16 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-03-30 | 1773392.8381 | 1521916.05 | 1521916.47 | 61196548.3714 |  |  |  | 14544514.79 | 285180.36 | 5755565.16 | 1606409.395 | 1606409.395 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape16
ORA - ZED - Landscape | 17 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-04-28 | 1582674.7048 | 1313620 | 1313619.66 | 62779223.0762 |  |  |  | 15060209.78 | 285180.36 | 5766649.95 | 1647954.605 | 1647954.605 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape17
ORA - ZED - Landscape | 18 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-05-14 | 1979868.8571 | 1643291.15 | 975356.43 | 64759091.9333 |  |  |  | 16924136.12 | 285180.36 | 5796250.4 | 1699926.165 | 1699926.165 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape18
ORA - ZED - Landscape | 19 | 2024-05-31 | 2024-05-25 | 2024-06-04 | 56 | 2024-07-30 | 2024-07-07 | 1453055.0476 | 168189.5 | 618692.48 | 66212146.981 |  |  |  | 17189828.91 | 785180.36 | 5817974.6 | 1738068.86 | 1738068.86 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape19
ORA - ZED - Landscape | 20 | 2024-06-30 | 2024-06-25 | 2024-07-07 | 56 | 2024-09-01 | 2024-07-23 | 1399335.6857 | 1244123 | 1177303.85 | 67611482.6667 |  |  |  | 17563515.19 | 335180.36 | 5838895.67 | 1774801.42 | 1774801.42 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape20
ORA - ZED - Landscape | 21 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-05 | 422349.9905 | 189683.6223 | 108767.39 | 68033832.6571 |  |  |  | 17849734.0836 | 385180.36 | 5845210.1017 | 1785888.105 | 1785888.105 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape21
ORA - ZED - Landscape | 22 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-16 | 4226377.8476 | 1388299.8 | 0 | 72260210.5048 |  |  |  | 19837405.71 | 935180.36 | 5908397.46 | 1896830.525 | 1896830.525 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape22
ORA - ZED - Landscape | 23 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 1124749.1714 | 1551640.48 | 0 | 73384959.6762 |  |  |  | 20272182.95 | 435180.36 | 5961374.39 | 1926355.19 | 1926355.19 | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape23
ORA - ZED - Landscape | 24 | 2024-10-31 | 2024-10-25 | 2024-11-10 | 56 | 2025-01-05 |  |  |  | 0 | [9 empty] | 0 | Ora Zed Landscape Ph1 | [7 empty] | ORA - ZED - Landscape24
ORA - ZED - ph.02 | 1 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 56 | 2021-12-01 | 2021-10-13 | 13196047.2 | 14536703 | 39536704.19 | 13196047.2 |  | 25000000 | 4533956.5 | [5 empty] | 0 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.021
ORA - ZED - ph.02 | 2 | 2021-10-31 | 2021-10-25 | 2021-11-15 | 56 | 2022-01-10 | 2021-11-14 | 21711682.2 | 20471935.87 | 35471935.63 | 34907729.4 |  | 15000000 | 7634922.31 | [5 empty] | 0 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.022
ORA - ZED - ph.02 | 3 | 2021-11-30 | 2021-11-25 | 2021-12-05 | 56 | 2022-01-30 | 2022-01-18 | 15579509.1905 | 9325143.2186 | 12325142.71 | 50487238.5905 |  | 3000000 | 3073305.59 | [5 empty] | 0 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.023
ORA - ZED - ph.02 | 4 | 2021-12-31 | 2021-12-26 | 2021-12-26 | 56 | 2022-02-20 | 2022-02-15 | 34347323.4857 | 28728856.62 | 54728856.89 | 84834562.0762 |  | 26000000 | 3352350.21 | [5 empty] | 0 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.024
ORA - ZED - ph.02 | 5 | 2022-01-31 | 2022-01-25 | 2022-02-10 | 56 | 2022-04-07 | 2022-03-23 | 10060643.6952 | 12407122.37 | 12407121.98 | 94895205.7714 |  |  | 8683284.6 | [5 empty] | 0 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.025
ORA - ZED - ph.02 | 6 | 2022-02-28 | 2022-02-25 | 2022-03-21 | 56 | 2022-05-16 | 2022-05-10 | 23225104.4643 | 16610990.7481 | 16610991.38 | 118120310.2353 |  |  | 5575171.2714 |  |  |  | 3240037.4255 | 3240037.4255 | 0 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.026
ORA - ZED - ph.02 | 7 | 2022-03-31 | 2022-03-25 | 2022-04-04 | 56 | 2022-05-30 | 2022-08-07 | 42383851.5888 | 32100388.5958 | 32100387.28 | 160504161.8242 |  |  | 1563640.4346 |  |  |  | 4252325.255 | 4252325.255 | 273333.59 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.027
ORA - ZED - ph.02 | 8 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-06-09 | 8766077.2795 | 8595538.9026 | 8595540.37 | 169270239.1037 |  |  | 3486145.8511 |  |  | 32252330.5602 | 4530497.42 | 4530497.42 | 473333.59 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.028
ORA - ZED - ph.02 | 9 | 2022-05-31 | 2022-05-25 | 2022-06-05 | 56 | 2022-07-31 | 2022-08-08 | 8712415.4916 | 7163536.3546 | 7163536.59 | 177982654.5953 |  |  | 3347808.9149 | 15346414.5805 |  | 32754709.2407 | 4755739.905 | 4755739.905 | 431750.04 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.029
ORA - ZED - ph.02 | 10 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 56 | 2022-08-30 | 2022-08-22 | 25761823.8629 | 20828447.3064 | 20828447.26 | 203744478.4582 |  |  | 2710387.4388 | 19184341.5109 |  | 44374111.2806 | 5416052.245 | 5416052.245 | 481750.04 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0210
ORA - ZED - ph.02 | 11 | 2022-07-31 | 2022-07-25 | 2022-08-10 | 56 | 2022-10-05 | 2022-09-14 | 10555360.8465 | 12170283.1854 | 12170282.5 | 214299839.3048 |  |  | 6960146.9261 | 21459521.0485 |  | 44831361.1808 | 5799374.45 | 5799374.45 | 431750.04 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0211
ORA - ZED - ph.02 | 12 | 2022-08-31 | 2022-08-25 | 2022-09-08 | 56 | 2022-11-03 | 2022-10-12 | 16689354.4631 | 14759398 | 14759397.95 | 230989193.7679 |  |  | 8729597.3 | 23666966.21 |  | 45632622.2463 | 6281714.5 | 6281714.5 | 923489 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0212
ORA - ZED - ph.02 | 13 | 2022-09-30 | 2022-09-25 | 2022-10-02 | 56 | 2022-11-27 | 2022-10-22 | 20581919.2571 | 17432997.712 | 13268244.56 | 251427139.1048 |  |  | 9285019.1626 | 25526704.6029 |  | 54138067.1729 | 6832087.88 | 6832087.88 | 1012532.93 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0213
ORA - ZED - ph.02 | 14 | 2022-10-31 | 2022-10-25 | 2022-11-09 | 56 | 2023-01-04 | 2022-12-15 | 19311587.7934 | 15411600.8685 | 15256729.38 | 270738726.8982 |  |  | 8366501.3369 | 26771100.6571 |  | 60073669.5278 | 7316054.1145 | 7316054.1145 | 862532.9342 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0214
ORA - ZED - ph.02 | 15 | 2022-11-30 | 2022-11-25 | 2022-12-05 | 56 | 2023-01-30 | 2022-12-20 | 14179983.4542 | 11605388.8976 | 11384143.67 | 284918710.3524 |  |  | 8026884.6944 | 27159626.8647 |  | 63560657.3095 | 7679788.26 | 7679788.26 | 758071.44 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0215
ORA - ZED - ph.02 | 16 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-05 | 11487525.8247 | 9858411.1445 | 9858410.94 | 296406236.1771 |  |  | 8322611.144 | 27430483.1297 |  | 65684472.9994 | 7988728.975 | 7988728.975 | 668071.44 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0216
ORA - ZED - ph.02 | 17 | 2023-01-31 | 2023-01-25 | 2023-01-28 | 56 | 2023-03-25 | 2023-03-19 | 9516947.0875 | 8988165.9521 | 8988166.12 | 305923183.2647 |  |  | 9631056.1321 | 28105199.965 |  | 66254957.5517 | 8271259.96 | 8271259.96 | 613266.18 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0217
ORA - ZED - ph.02 | 18 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-18 | 15495416.059 | 13331568.0485 | 13223027.75 | 321418599.3237 |  |  | 10365262.5801 | 28915218.0403 | 400000 | 72791890.9694 | 8696369.795 | 8696369.795 | 323266.18 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0218
ORA - ZED - ph.02 | 19 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 8053943.7501 | 6921352.2914 | 6921352.11 | 329472543.0738 |  |  | 10413345.9625 | 29296490.0269 | 200000 | 76001927.9044 | 8908987.9 | 8908987.9 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0219
ORA - ZED - ph.02 | 20 | 2023-04-30 | 2023-04-25 | 2023-05-10 | 56 | 2023-07-05 | 2023-06-01 | 4423045.841 | 3302213.7069 | 3038540.29 | 333895588.9148 |  |  | 10136406.1294 | 30236499.4184 | 350000 | 76323656.7997 | 9018169.36 | 9018169.36 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0220
ORA - ZED - ph.02 | 21 | 2023-05-31 | 2023-05-25 | 2023-06-04 | 56 | 2023-07-30 | 2023-08-14 | 4766150.0757 | 4532159.65 | 4532160.06 | 338661738.9905 |  |  | 10738897.52 | 27714328.99 | 250000 | 79032701.56 | 9158343.085 | 9158343.085 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0221
ORA - ZED - ph.02 | 22 | 2023-06-30 | 2023-06-25 | 2023-07-12 | 56 | 2023-09-06 | 2023-08-09 | 11000140.3008 | 8466780.16 | 8297638.82 | 349661879.2913 |  |  | 9962990.1626 | 30646302.9038 | 300000 | 84045575.3164 | 9427699.0855 | 9427699.0855 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0222
ORA - ZED - ph.02 | 23 | 2023-07-31 | 2023-07-25 | 2023-08-09 | 56 | 2023-10-04 | 2023-09-17 | 1051681.4414 | 564270.13 | 564270 | 350713560.7327 |  |  | 9534609.8107 | 30624495.36 | 270001 | 84127290.1745 | 9444596.21 | 9444596.21 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0223
ORA - ZED - ph.02 | 24 | 2023-08-31 | 2023-08-25 | 2023-09-09 | 56 | 2023-11-04 | 2023-09-17 | 1619984.7524 | 1374588.34 | 1374587.38 | 352333545.4851 |  |  | 9534609.8107 | 30639873.392 | 240000 | 84127290.1745 | 9487120.81 | 9487120.81 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0224
ORA - ZED - ph.02 | 25 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-07 | 1429470.734 | 996460.71 | 996461.29 | 353763016.219 |  |  | 9534609.81 | 30639873.4 | 430000 | 84470961.01 | 9524644.42 | 9524644.42 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0225
ORA - ZED - ph.02 | 26 | 2023-10-31 | 2023-10-25 | 2023-11-07 | 56 | 2024-01-02 | 2023-12-14 | 3475331.4095 | 2944525.07 | 2944524.93 | 357238347.6286 |  |  | 9534609.81 | 30760806.2 | 370000 | 84664884.26 | 9615871.87 | 9615871.87 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0226
ORA - ZED - ph.02 | 27 | 2023-11-30 | 2023-11-25 | 2023-12-14 | 56 | 2024-02-08 | 2024-01-14 | 3041219.2755 | 6012429.48 | 5268993.93 | 360279566.9041 |  |  | 9534609.8107 | 31106243.5594 | 430000 | 84803721.0331 | 9695703.875 | 9695703.875 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0227
ORA - ZED - ph.02 | 28 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-03-03 | 5861894.8952 | 1674078.17 | 1922751.71 | 366141461.7993 |  |  | 9534609.8107 | 32767206.4615 | 450000 | 88600538.3056 | 9849578.6176 | 9849578.6176 | 324695.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0228
ORA - ZED - ph.02 | 29 | 2024-01-31 | 2024-01-25 | 2024-02-13 | 56 | 2024-04-09 | 2024-04-15 | 2577878.9747 | 622103 | 5009481.72 | 368719340.774 |  |  | 7793026.7073 | 32686135.972 | 500000 | 89023126.49 | 9873708.36 | 9873708.36 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0229
ORA - ZED - ph.02 | 30 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-04-29 | 2066668.4069 | 73017 | 73017 | 370786009.181 |  |  | 6499733.7 | 32340261.62 | 1120000 | 89409590.24 | 9895626.085 | 9895626.085 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0230
ORA - ZED - ph.02 | 31 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-15 | 7992050.6095 | 3717995 | 3717995 | 378778059.7905 |  |  | 3482050.01 | 39683396.61 | 1650000 | 88674483.32 | 10029975.32 | 10029975.32 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0231
ORA - ZED - ph.02 | 32 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-06-05 | 2766734.981 | 2943652.2 | 2836390.67 | 381544794.7714 |  |  | 3482050.01 | 39914992.15 | 1110000 | 89539810.97 | 10102602.115 | 10102602.115 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0232
ORA - ZED - ph.02 | 33 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 56 | 2024-07-31 | 2024-07-01 | 6575447.0667 | 1631186.62 | 1e-05 | 388120241.8381 |  |  | 3482050.01 | 40131194.96 | 2270000 | 90446780.46 | 10188156.35 | 10188156.35 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0233
ORA - ZED - ph.02 | 34 | 2024-06-30 | 2024-06-25 | 2024-07-06 | 56 | 2024-08-31 | 2024-08-06 | 1412666.8095 | 3368948.46 | 1e-05 | 389532908.6476 |  |  | 3482050.01 | 40483731.09 | 2740000 | 92888843.55 | 10312290.1 | 10312290.1 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0234
ORA - ZED - ph.02 | 35 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-08-31 | 7262978.339 | 6454315.65 | 1e-05 | 396795886.9866 |  |  | 3482050.0134 | 42071751.0265 | 2400000 | 94659153.4844 | 10502943.2837 | 10502943.2837 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0235
ORA - ZED - ph.02 | 36 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 56 | 2024-10-27 | 2024-09-05 | 0.003893 | 6578211.32 | 4160916.8 | 396795886.9905 |  |  | 11803883.61 | 42071751.03 | 2400000 | 94659153.49 | 10710989.125 | 10710989.125 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0236
ORA - ZED - ph.02 | 37 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-10-07 | 12000518.9238 | 9153293.69 | 8601492.56 | 408796405.9143 |  |  | 10593047.63 | 43987735.96 | 2250000 | 101066779.38 | 10995731.845 | 10995731.845 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0237
ORA - ZED - ph.02 | 38 | 2024-09-30 | 2024-09-16 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-07 | -0.0095238 | 3851310.01 | 3811960.86 | 408796405.9048 |  |  | 15718197.44 | 43987735.96 | 2450000 | 101066779.38 | 11123860.59 | 11123860.59 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0238
ORA - ZED - ph.02 | 39 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-11-09 | 13783192.8762 | 14526906.83 | 0 | 422579598.781 |  |  | 19699160.8 | 49807541.52 | 2510000 | 103795295.53 | 11585193.49 | 11585193.49 | 419195.97 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0239
ORA - ZED - ph.02 | 40 | 2024-10-30 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 |  |  |  | 0 | [9 empty] | 0 | ORA ZED-Ph 2-Pkgs A&D | [7 empty] | ORA - ZED - ph.0240
PH.2-El Sewedy Uni. - Enabling | 1 | 2019-11-30 | 2019-12-05 | 2019-12-07 | 7 | 2019-12-14 | 2019-12-11 | 1222080 | 2841415.8 | 2832501.18 | 1222080 |  |  | 2056962.6 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling1
PH.2-El Sewedy Uni. - Enabling | 2 | 2019-12-31 | 2020-01-02 | 2020-01-02 | 7 | 2020-01-09 | 2020-01-11 | 19989408.99 | 13446882.5 | 13318143.89 | 21211488.99 |  |  | 2672643.6 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling2
PH.2-El Sewedy Uni. - Enabling | 3 | 2020-01-31 | 2020-01-30 | 2020-01-30 | 7 | 2020-02-06 | 2020-02-05 | 22171564.66 | 17089175.5 | 17089175.5 | 43383053.65 |  |  | 5401152.9 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling3
PH.2-El Sewedy Uni. - Enabling | 4 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 7 | 2020-03-14 | 2020-03-16 | 17471458.95 | 14773850.7 | 14773850.81 | 60854512.6 |  |  | 8960074.2 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling4
PH.2-El Sewedy Uni. - Enabling | 5 | 2020-03-31 | 2020-03-15 | 2020-03-26 | 7 | 2020-04-02 | 2020-04-09 | 7891719.6 | 2392694.9 | 2392694.9 | 68746232.2 |  |  | 6287074.2 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling5
PH.2-El Sewedy Uni. - Enabling | 6 | 2020-04-30 | 2020-04-15 | 2020-04-26 | 7 | 2020-05-03 | 2020-05-06 | 18379179.4 | 7788095.2 | 7788095.22 | 87125411.6 |  |  | 2277574.2 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling6
PH.2-El Sewedy Uni. - Enabling | 7 | 2020-05-31 | 2020-05-31 | 2020-06-08 | 7 | 2020-06-15 | 2020-07-11 | 9076073.5 | 3548357.4 | 3548357.43 | 96201485.1 |  |  | 0 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling7
PH.2-El Sewedy Uni. - Enabling | 8 | 2020-06-30 | 2020-06-30 | 2020-07-07 | 7 | 2020-07-14 | 2020-07-09 | 2504382.4 | 1607563.1 | 1607563.1 | 98705867.5 | [8 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling8
PH.2-El Sewedy Uni. - Enabling | 9 | 2020-07-31 | 2020-08-15 | 2020-08-17 | 7 | 2020-08-24 | 2020-08-27 | 9452002.7 | 8526565.2 | 8739144.88 | 108157870.2 | [8 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling9
PH.2-El Sewedy Uni. - Enabling | 10 | 2020-11-30 | 2020-11-15 | 2020-11-22 | 7 | 2020-11-29 | 2020-11-22 | 5068271.5 | 7703511.3 | 7703511.41 | 113226141.7 | [8 empty] | 118504 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Enabling10
PH.2-El Sewedy Uni. - Finishes | 1 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 14 | 2020-03-21 | 2020-03-22 | 39552087.9 | 35636298.9 | 50636298.9 | 39552087.9 |  | 15000000 | 27835856 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes1
PH.2-El Sewedy Uni. - Finishes | 2 | 2020-03-31 | 2020-03-31 | 2020-04-05 | 14 | 2020-04-19 | 2020-04-22 | 33281363.92 | 26758389.8 | 26758389.8 | 72833451.82 |  |  | 40761852.6 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes2
PH.2-El Sewedy Uni. - Finishes | 3 | 2020-04-30 | 2020-04-30 | 2020-05-06 | 14 | 2020-05-20 | 2020-05-19 | 24169965.9076 | 23262698.8 | 23262698.8 | 97003417.7276 |  |  | 51226946.1 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes3
PH.2-El Sewedy Uni. - Finishes | 4 | 2020-05-31 | 2020-05-31 | 2020-06-14 | 14 | 2020-06-28 | 2020-06-18 | 24591514.8424 | 18322601 | 18322600.95 | 121594932.57 |  |  | 51695436 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes4
PH.2-El Sewedy Uni. - Finishes | 5 | 2020-06-30 | 2020-06-30 | 2020-07-08 | 14 | 2020-07-22 | 2020-07-13 | 77007398.3 | 64006362.8 | 64006362.98 | 198602330.87 |  |  | 81242431.4 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes5
PH.2-El Sewedy Uni. - Finishes | 6 | 2020-07-31 | 2020-07-15 | 2020-07-27 | 14 | 2020-08-10 | 2020-07-29 | 22875033.55 | 8883254.2 | 8883254.07 | 221477364.42 |  |  | 71736256.5 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes6
PH.2-El Sewedy Uni. - Finishes | 7 | 2020-08-31 | 2020-08-15 | 2020-08-17 | 14 | 2020-08-31 | 2020-08-26 | 54216090.64 | 30755604.9 | 25755604.75 | 275693455.06 |  |  | 65901640.4 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes7
PH.2-El Sewedy Uni. - Finishes | 8 | 2020-08-31 | 2020-08-31 | 2020-09-10 | 14 | 2020-09-24 | 2020-09-17 | 61814968.03 | 30127325.7 | 25127325.53 | 337508423.09 |  |  | 51289431.9 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes8
PH.2-El Sewedy Uni. - Finishes | 9 | 2020-09-30 | 2020-09-15 | 2020-10-18 | 14 | 2020-11-01 | 2020-10-20 | 56169721.37 | 20493846 | 20493846.09 | 393678144.46 |  |  | 22011525 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes9
PH.2-El Sewedy Uni. - Finishes | 10 | 2020-10-31 | 2020-10-25 | 2020-11-10 | 14 | 2020-11-24 | 2020-11-19 | 33204826.41 | 9765894.8 | 9765894.8 | 426882970.87 |  |  | 8412160.7 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes10
PH.2-El Sewedy Uni. - Finishes | 11 | 2020-11-30 | 2020-12-01 | 2020-12-15 | 14 | 2020-12-29 | 2020-12-21 | 20698550.4 | 13851401.2 | 13851401.63 | 447581521.27 |  |  | 6756406.26 | [5 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes11
PH.2-El Sewedy Uni. - Finishes | 12 | 2021-01-31 | 2021-02-10 | 2021-02-14 | 14 | 2021-02-28 | 2021-03-22 | 33191485.02 | 23340124.9 | 23340124.9 | 480773006.29 | [8 empty] | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes12
PH.2-El Sewedy Uni. - Finishes | 13 | 2021-05-31 | 2021-06-09 | 2022-03-28 | 14 | 2022-04-11 | 2022-04-27 | 13891238 | 19693398.5 | 15069000 | 494664244.29 | [6 empty] | 12984936.4125 | 12984936.4125 | 0 | ESU Ph2-Enabling & Struc | [7 empty] | PH.2-El Sewedy Uni. - Finishes13
PI Parks - ELSEWEDY | 1 | 2017-09-30 | 2017-10-03 | 2017-10-18 | 15 | 2017-11-16 | 2017-11-04 | 2947938.09 | 3779007.23 | 3779007.23 | 2947938.09 |  |  | 2165254 | [5 empty] | 350000 | 0 | [7 empty] | PI Parks - ELSEWEDY1
PI Parks - ELSEWEDY | 2 | 2017-10-31 | 2017-11-04 | 2017-11-06 | 15 | 2017-12-09 | 2017-11-28 | 4598153.29 | 3366014.15 | 3366014.15 | 7546090.84 |  |  | 1128937.5 | [5 empty] | 360362.87 | 0 | [7 empty] | PI Parks - ELSEWEDY2
PI Parks - ELSEWEDY | 3 | 2017-11-30 | 2017-12-04 | 2017-12-04 | 15 | 2018-01-09 | 2017-12-25 | 1603218.21 | 823701.84 | 823701.85 | 9149309.06 |  |  | 1055385.4 | [5 empty] | 360362.87 | 0 | [7 empty] | PI Parks - ELSEWEDY3
PI Parks - ELSEWEDY | 4 | 2017-12-31 | 2017-12-31 | 2018-01-04 | 15 | 2018-02-17 | 2018-02-15 |  | 2572231.81 | 2572231.81 | 12280064.67 |  |  | 862309.875 | [5 empty] | 711378.1905 | 0 | [7 empty] | PI Parks - ELSEWEDY4
PI Parks - ELSEWEDY | 5 | 2018-01-31 | 2018-02-07 | 2018-02-07 | 15 | 2018-03-28 | 2018-04-05 | 2043145.23 | 1175600.49 | 1175600.49 | 14323209.9 |  |  | 439890.2 | [5 empty] | 110286.54 | 0 | [7 empty] | PI Parks - ELSEWEDY5
PI Parks - ELSEWEDY | 6 | 2018-02-28 | 2018-03-10 | 2018-03-11 | 15 | 2018-04-28 | 2018-04-15 | 662608.11 | 689113.69 | 689110.93 | 14985818.01 |  |  | 602282.21 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY6
PI Parks - ELSEWEDY | 7 | 2018-03-31 | 2018-04-10 | 2018-04-16 | 15 | 2018-05-08 | 2018-04-21 | 667972.21 | 1938615.93 | 1209313.47 | 15685820.74 |  |  | 1491568.3 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY7
PI Parks - ELSEWEDY | 8 | 2018-04-30 | 2018-05-09 | 2018-05-09 | 15 | 2018-06-03 | 2018-06-02 | 1859636.86 | 1633991.6379 | 1492654.2 | 17545457.6 |  |  | 1274527.689 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY8
PI Parks - ELSEWEDY | 9 | 2018-05-31 | 2018-06-09 | 2018-06-09 | 15 | 2018-06-29 | 2018-06-12 | 1491159.5592 | 1607545.8276 | 1471457.2 | 19036617.1592 |  |  | 1586317.356 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY9
PI Parks - ELSEWEDY | 10 | 2018-06-30 | 2018-07-08 | 2018-07-10 | 15 | 2018-08-08 | 2018-08-01 | 3200065.7108 | 2470019.34 | 2470019.34 | 22236682.87 |  |  | 1486479.93 | [5 empty] | 115532.14 | 0 | [7 empty] | PI Parks - ELSEWEDY10
PI Parks - ELSEWEDY | 11 | 2018-07-31 | 2018-08-02 | 2018-08-07 | 15 | 2018-08-25 | 2018-09-13 | 890276.26 | 945860.23 | 945860.23 | 23126959.13 |  |  | 1734570.528 | [5 empty] | 125532.14 | 0 | [7 empty] | PI Parks - ELSEWEDY11
PI Parks - ELSEWEDY | 12 | 2018-08-31 | 2018-09-06 | 2018-09-08 | 15 | 2018-10-13 | 2018-09-26 | 1804540.7798 | 1530660.1341 | 1347803.37 | 24932718.8264 |  |  | 1713142.271 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY12
PI Parks - ELSEWEDY | 13 | 2018-09-30 | 2018-10-04 | 2018-10-04 | 15 | 2018-10-27 | 2018-10-10 | 1076504.1197 | 716605.5327 | 719804.13 | 26009222.9461 |  |  | 1579309.545 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY13
PI Parks - ELSEWEDY | 14 | 2018-10-31 | 2018-11-05 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 1188716.2339 | 775351.46 | 775351.46 | 27197939.18 |  |  | 1430574.85 | [5 empty] | 194651.72 | 0 | [7 empty] | PI Parks - ELSEWEDY14
PI Parks - ELSEWEDY | 15 | 2018-11-30 | 2018-12-06 | 2018-12-06 | 15 | 2019-01-01 | 2018-12-26 | 6486957.62 | 4484634.17 | 4484634.14 | 33684896.8 |  |  | 1125214.43 | [5 empty] | 209651.72 | 0 | [7 empty] | PI Parks - ELSEWEDY15
PI Parks - ELSEWEDY | 16 | 2018-12-31 | 2019-01-06 | 2019-01-06 | 15 | 2019-01-31 | 2019-01-27 | 4932880.46 | 4125986.43 | 4125986.43 | 38617777.26 |  |  | 889716.88 | [5 empty] | 245586.01 | 0 | [7 empty] | PI Parks - ELSEWEDY16
PI Parks - ELSEWEDY | 17 | 2019-01-31 | 2019-02-05 | 2019-02-07 | 15 | 2019-03-05 | 2019-03-13 | 1718123.55 | 1375431.38 | 1375431.38 | 40335900.81 |  |  | 584649.66 | [5 empty] | 261703.2 | 0 | [7 empty] | PI Parks - ELSEWEDY17
PI Parks - ELSEWEDY | 18 | 2019-02-28 | 2019-03-05 | 2019-03-06 | 15 | 2019-04-03 | 2019-03-27 | 4308748.67 | 3699864.67 | 3699864.67 | 44644649.48 |  |  | 439815.151 | [5 empty] | 261703.2 | 0 | [7 empty] | PI Parks - ELSEWEDY18
PI Parks - ELSEWEDY | 19 | 2019-03-31 | 2019-04-06 | 2019-04-06 | 15 | 2019-05-04 | 2019-05-14 | 2652468.02 | 2311261.81 | 2311261.81 | 47297117.5 |  |  | 171933.6095 | [5 empty] | 276703.2 | 0 | [7 empty] | PI Parks - ELSEWEDY19
PI Parks - ELSEWEDY | 20 | 2019-04-30 | 2019-05-05 | 2019-05-07 | 15 | 2019-06-05 | 2019-05-19 | 4018450.9279 | 1816746.614 | 1466574.4 | 51315568.4279 |  |  | 161583.8345 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY20
PI Parks - ELSEWEDY | 21 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 598299.7921 | 5879272.6391 | 5333565.74 | 51913868.22 |  |  | 179052.64 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - ELSEWEDY21
PI Parks - MEP | 1 | 2018-09-30 | 2018-10-04 | 2018-09-27 | 15 | 2018-10-27 | 2018-10-10 | 4100153.37 | 7818631.64 | 7818631.64 | 4100153.37 |  |  | 4989525.8132 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP1
PI Parks - MEP | 2 | 2018-10-31 | 2018-11-02 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 3824663.6 | 3907009.94 | 3907009.94 | 7924816.97 |  |  | 5871509.91 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP2
PI Parks - MEP | 3 | 2018-11-30 | 2018-12-10 | 2018-12-03 | 15 | 2019-01-01 | 2018-12-26 | 2526634.86 | 3921714.73 | 3921714.73 | 10451451.83 |  |  | 8435854.55 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP3
PI Parks - MEP | 4 | 2018-12-31 | 2019-01-05 | 2019-01-05 | 15 | 2019-01-31 | 2019-01-14 | 13292686.78 | 3514249.7617 | 3366511.48 | 23744138.61 |  |  | 6341086.69 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP4
PI Parks - MEP | 5 | 2019-01-31 | 2019-02-05 | 2019-02-05 | 15 | 2019-03-05 | 2019-03-13 | 8084326 | 6350059.5 | 6350059.5 | 31828464.61 |  |  | 8184608.01 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP5
PI Parks - MEP | 6 | 2019-02-28 | 2019-03-05 | 2019-03-05 | 15 | 2019-04-03 | 2019-03-26 | 3232894.78 | 919139.23 | 919139.23 | 35061359.39 |  |  | 6744285.61 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP6
PI Parks - MEP | 7 | 2019-03-31 | 2019-04-01 | 2019-04-04 | 15 | 2019-05-04 | 2019-05-14 | 4908164.7341 | 2661364.08 | 2661364.08 | 39969524.1241 |  |  | 4404706.2941 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP7
PI Parks - MEP | 8 | 2019-04-30 | 2019-05-05 | 2019-05-06 | 15 | 2019-06-05 | 2019-05-19 | 2655162.8183 | 1686090.7908 | 1478131.5 | 42624686.9424 |  |  | 3262993.985 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP8
PI Parks - MEP | 9 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 3596767.6976 | 5081340.66 | 4813799.42 | 46221454.64 |  |  | 42070.75 | [5 empty] | 0 | 0 | [7 empty] | PI Parks - MEP9
PK #107 | 8 | 2017-09-30 | 2017-09-28 | 2017-09-28 | 30 | 2017-10-28 | 2017-10-15 |  | 3005745.85 | 3005745.85 | 36182581.41 |  |  | 1713544.64 | [5 empty] | 238645.64 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #1078
PK #107 | 9 | 2017-10-31 | 2017-10-31 | 2017-11-01 | 30 | 2017-12-01 | 2017-11-28 | 1856322.11 | 1418090.5 | 1418090.5 | 38038903.52 |  |  | 1713544.64 | [5 empty] | 253179.82 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #1079
PK #107 | 10 | 2017-11-30 | 2017-11-28 | 2017-11-28 | 30 | 2017-12-28 | 2017-12-27 | 2025124.41 | 1453205.39 | 1453205.38 | 40064027.93 |  |  | 1875947.9 | [5 empty] | 264974.51 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10710
PK #107 | 11 | 2017-12-31 | 2017-12-25 | 2017-12-27 | 30 | 2018-01-26 | 2018-01-15 | 3591068.23 | 2604921.36 | 2354508.52 | 43655096.16 |  |  | 1188936.54 | [5 empty] | 282897.2 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10711
PK #107 | 12 | 2018-01-31 | 2018-01-25 | 2018-01-25 | 30 | 2018-02-24 | 2018-02-26 | 5883258.75 | 5012769.61 | 4193998 | 49538354.91 |  |  | 366842.14 | [5 empty] | 315029.17 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10712
PK #107 | 13 | 2018-02-28 | 2018-03-10 | 2018-03-12 | 30 | 2018-04-11 | 2018-04-04 | 2719252.37 | 2462800.95 | 3281572.56 | 52257607.28 |  |  | 323504.14 | [5 empty] | 369537.93 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10713
PK #107 | 14 | 2018-03-31 | 2018-04-10 | 2018-04-11 | 30 | 2018-05-11 | 2018-04-29 | 1449945.81 | 166316.41 | 166316.41 | 53707553.09 |  |  | 0 | [5 empty] | 1275350.71 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10714
PK #107 | 15 | 2018-04-30 | 2018-05-05 | 2018-05-06 | 30 | 2018-06-05 | 2018-05-23 | 0 | 1406606.27 | 1406606.27 | 53707553.09 |  |  | 0 | [5 empty] | 1275350.71 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10715
PK #107 | 16 | 2018-05-31 | 2018-06-01 | 2018-05-30 | 30 | 2018-06-29 | 2018-06-28 | 0.01 | 131256.74 | 131256.74 | 53707553.1 |  |  | 0 | [5 empty] | 1292122.78 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10716
PK #107 | 17 | 2018-09-30 | 2018-09-25 | 2018-09-25 | 30 | 2018-10-25 | 2018-10-21 | 0 | 763627.7 | 763627.7 | 53707553.1 |  |  | 0 | [5 empty] | 496495.08 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10717
PK #107 | 18 | 2019-04-30 | 2019-04-25 | 2019-06-13 | 30 | 2019-07-13 | 2019-07-30 | 989048.54 | 940988.93 | 1341459.14 | 54696601.64 | [8 empty] | 1898258.43 | EMAAR-PKG#107-MARASSI | [7 empty] | PK #10718
PK #117 | 1 | 2017-12-31 | 2018-01-01 | 2018-01-18 | 30 | 2018-02-17 | 2018-02-13 | 4130129.14 | 4130129.14 | 4130129.12 | 4130129.14 | [8 empty] | 0 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1171
PK #117 | 2 | 2018-01-31 | 2018-02-15 | 2018-02-15 | 30 | 2018-03-17 | 2018-03-07 | 7803090.39 | 6455421.01 | 6455421.01 | 7803090.39 |  |  | 0 | [5 empty] | 60159.47 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1172
PK #117 | 3 | 2018-02-28 | 2018-03-05 | 2018-03-07 | 30 | 2018-04-06 | 2018-03-29 | 4332593.51 | 4502026.52 | 4502026.51 | 12135683.86 |  |  | 1176749.78 | [5 empty] | 106021.19 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1173
PK #117 | 4 | 2018-03-31 | 2018-04-01 | 2018-04-01 | 30 | 2018-05-01 | 2018-04-19 | 4131277.1774 | 3740180.271 | 3740180.08 | 16266961.0374 |  |  | 1578005.405 | [5 empty] | 134455.7716 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1174
PK #117 | 5 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 30 | 2018-05-30 | 2018-05-22 | 6909334.9826 | 4762507.55 | 4762507.56 | 23176296.02 |  |  | 364792.48 | [5 empty] | 171850.1 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1175
PK #117 | 6 | 2018-05-31 | 2018-06-04 | 2018-06-05 | 30 | 2018-07-05 | 2018-07-12 | 6677875.24 | 5347404.79 | 5347404.79 | 29854171.26 |  |  | 229256.92 | [5 empty] | 302952.2979 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1176
PK #117 | 7 | 2018-06-30 | 2018-06-15 | 2018-06-25 | 30 | 2018-07-25 | 2018-12-30 | -0.01 | 119713.18 | 118938.86 | 29854171.25 |  |  | 384118.8 | [5 empty] | 115837.505 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1177
PK #117 | 8 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 30 | 2019-01-04 | 2018-12-30 | 4511257.49 | 3896343.98 | 3896343.98 | 34365428.74 |  |  | 79445.62 | [5 empty] | 575019.525 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1178
PK #117 | 9 | 2018-12-31 | 2018-12-30 | 2018-12-29 | 30 | 2019-01-28 | 2019-01-30 | 3153415.09 | 2578109.66 | 2578109.73 | 37518843.83 |  |  | 48842.25 | [5 empty] | 599014.4 | EMAAR-PKG117- MARASSI | [7 empty] | PK #1179
PK #117 | 10 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 30 | 2019-03-04 | 2019-02-28 | 1068867.24 | 882296.18 | 882296.11 | 38587711.07 |  |  | 48842.25 | [5 empty] | 653139.594 | EMAAR-PKG117- MARASSI | [7 empty] | PK #11710
PK #117 | 11 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-30 | 1134851.86 | 810342.08 | 809762.24 | 39722562.93 | [8 empty] | 737679.72 | EMAAR-PKG117- MARASSI | [7 empty] | PK #11711
PK #117 | 12 | 2019-08-31 | 2019-08-26 | 2019-08-26 | 30 | 2019-09-25 | 2019-09-25 | 2921413.42 | 3376348.1 | 3376927.91 | 42643976.35 |  |  | 0 | [5 empty] | 1681581.22 | EMAAR-PKG117- MARASSI | [7 empty] | PK #11712
PK #117 | 13 | 2019-10-31 | 2019-10-30 | 2019-10-29 | 30 | 2019-11-28 | 2019-11-12 | 2611652.87 | 3145779.21 | 3145907.11 | 45255629.22 |  |  | 0 | [5 empty] | 975332.15 | EMAAR-PKG117- MARASSI | [7 empty] | PK #11713
PK #117 | 14 | 2020-04-30 | 2020-04-14 | 2020-06-24 | 30 | 2020-07-24 | 2020-09-27 | 1659370.81 | 2238761.46 | 2483342.5 | 46915000.03 | [8 empty] | 943850.91 | EMAAR-PKG117- MARASSI | [7 empty] | PK #11714
PK#22 | 37 | 2019-02-28 | 2019-02-27 | 2019-07-31 | 30 | 2019-08-30 | 2019-08-07 |  | 471641.26 | 780036 | 35147992.22 | [8 empty] | 990333.95 | EMAAR-PKG#22-MARASSI | [7 empty] | PK#2237
PK#32 | 30 | 2017-06-30 | 2017-06-05 | 2022-03-14 | 30 | 2022-04-13 |  |  |  | 900093.35 | [9 empty] | 0 | 0 | [7 empty] | PK#3230
PKG#101 | 1 | 2019-01-31 | 2019-01-31 | 2019-02-03 | 40 | 2019-03-15 | 2019-02-17 | 1738465.6667 | 1029594.82 | 9752735.82 | 1738465.6667 | 8723141 | [7 empty] | 48253.89 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1011
PKG#101 | 2 | 2019-02-28 | 2019-02-28 | 2019-03-05 | 40 | 2019-04-14 | 2019-03-19 | 1610908.8476 | 2222206.65 | 2222206.65 | 3349374.5143 |  |  | 2240156.84 | [5 empty] | 147570 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1012
PKG#101 | 3 | 2019-03-31 | 2019-04-11 | 2019-04-14 | 40 | 2019-05-24 | 2019-05-05 | 4030400.2476 | 2246109.51 | 2246109.51 | 7379774.7619 |  |  | 1904790.84 | [5 empty] | 202283 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1013
PKG#101 | 4 | 2019-04-30 | 2019-05-15 | 2019-05-20 | 40 | 2019-06-29 | 2019-05-29 | 4428897.7238 | 2512749.68 | 2512749.68 | 11808672.4857 |  |  | 1592100.01 | [5 empty] | 250813.43 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1014
PKG#101 | 5 | 2019-06-30 | 2019-06-30 | 2019-07-01 | 40 | 2019-08-10 | 2019-07-24 | 2224631.7143 | 2051541.96 | 2051541.96 | 14033304.2 |  |  | 2808836.8 | [5 empty] | 296997.23 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1015
PKG#101 | 6 | 2019-07-31 | 2019-08-05 | 2019-08-07 | 40 | 2019-09-16 | 2019-08-28 | 3491880.8381 | 1988552.05 | 1988552.05 | 17525185.0381 |  |  | 2620517.54 | [5 empty] | 362213.26 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1016
PKG#101 | 7 | 2019-08-31 | 2019-09-10 | 2019-09-15 | 40 | 2019-10-25 | 2019-09-26 | 3123640.9905 | 1824097.57 | 1824097.57 | 20648826.0286 |  |  | 2373278.98 | [5 empty] | 374469.49 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1017
PKG#101 | 8 | 2019-09-30 | 2019-10-15 | 2019-10-17 | 40 | 2019-11-26 | 2019-11-05 | 4704887.4039 | 2104893.8329 | 2104893.84 | 25353713.4325 |  |  | 1078135.3004 | [5 empty] | 421854.3373 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1018
PKG#101 | 9 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 40 | 2019-12-27 | 2019-12-03 | 3179849.8818 | 1424816.56 | 1424816.56 | 28533563.3143 |  |  | 297444.34 | [5 empty] | 505055.04 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#1019
PKG#101 | 10 | 2019-11-30 | 2019-11-15 | 2019-12-18 | 40 | 2020-01-27 | 2020-01-06 | 3100706.8857 | 1976416.89 | 1976416.89 | 31634270.2 | [8 empty] | 515167.31 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10110
PKG#101 | 11 | 2020-01-31 | 2020-01-30 | 2020-02-08 | 40 | 2020-03-19 | 2020-02-27 | 361420.4 | 1709961.04 | 1709961.04 | 31995690.6 |  |  | 2008107.01 | [5 empty] | 646968.58 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10111
PKG#101 | 12 | 2020-02-29 | 2020-03-23 | 2020-03-24 | 40 | 2020-05-03 | 2020-04-08 | 2584477.6667 | 1146998.22 | 1146998.21 | 34580168.2667 |  |  | 1288346.31 | [5 empty] | 677344.97 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10112
PKG#101 | 13 | 2020-03-31 | 2020-04-23 | 2020-04-23 | 40 | 2020-06-02 | 2020-05-04 | 2595711.6476 | 1407211.96 | 1343055.6 | 37175879.9143 |  |  | 1005027.63 | [5 empty] | 712181.29 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10113
PKG#101 | 14 | 2020-06-30 | 2020-06-30 | 2020-07-12 | 40 | 2020-08-21 | 2020-09-09 | 4659441.8571 | 191421.72 | 191421.72 | 41835321.7714 | [8 empty] | 763224.31 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10114
PKG#101 | 15 | 2020-09-30 | 2020-08-12 | 2020-12-09 | 40 | 2021-01-18 | 2021-01-20 | 181866.4762 | 303853.8 | 303853.8 | 42017188.2476 | [8 empty] | 174031.17 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10115
PKG#101 | 16 | 2020-09-30 | 2020-09-30 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-15 | 0.001 | 866491.01 | 866491 | 42017188.2476 | [8 empty] | 0 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10116
PKG#101 | 17 | 2021-03-31 | 2021-04-05 | 2021-04-13 | 40 | 2021-05-23 | 2021-04-26 | 0.001 | 3321316.23 | 3321316.23 | 42017188.2476 | [8 empty] | 270662.92 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10117
PKG#101 | 18 | 2021-04-30 | 2021-04-05 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-05 | 1071378.1714 | 1192690.23 | 1192690.23 | 43088566.419 |  |  | 949450.54 | [5 empty] | 275887.92 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10118
PKG#101 | 19 | 2021-04-30 | 2021-05-05 | 2021-05-17 | 40 | 2021-06-26 | 2021-06-03 | 1322361.8352 | 596242.89 | 596242.89 | 44410928.2543 |  |  | 615651.133 | [5 empty] | 288697.92 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10119
PKG#101 | 20 | 2021-05-31 | 2021-06-05 | 2021-06-10 | 40 | 2021-07-20 | 2021-06-27 | 952923.8886 | 759353.31 | 759353.32 | 45363852.1429 |  |  | 505736.36 | [5 empty] | 238697.92 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10120
PKG#101 | 21 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 40 | 2021-08-20 | 2021-08-09 | 2547253.7048 | 1584188.57 | 1584188.58 | 47911105.8476 |  |  | 618555.37 | [5 empty] | 264186.92 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10121
PKG#101 | 22 | 2021-08-31 | 2021-08-15 | 2021-09-20 | 40 | 2021-10-30 | 2021-10-12 | 2544618.2857 | 594122.92 | 594123.32 | 50455724.1333 |  |  | 0 | [5 empty] | 299725.92 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10122
PKG#101 | 23 | 2022-04-30 | 2022-04-10 | 2022-04-21 | 40 | 2022-05-31 |  |  |  | 189091.52 | [9 empty] | 0 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10123
PKG#101 | 24 | 2022-04-30 | 2022-04-10 | 2023-03-27 | 40 | 2023-05-06 |  |  |  | 546994.62 | [9 empty] | 0 | EMAAR-PKG# 101-UPTOWN | [7 empty] | PKG#10124
PKG#144 | 2 | 2018-12-31 | 2018-12-26 | 2018-12-26 | 30 | 2019-01-25 | 2019-01-20 | 4125990.87 | 2532120.6 | 2532120.6 | 4125990.87 | [8 empty] | 25993.74 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1442
PKG#144 | 3 | 2019-01-31 | 2019-01-30 | 2019-01-31 | 30 | 2019-03-02 | 2019-02-20 | 6872046.13 | 6190737.99 | 6189125.05 | 10998037 |  |  | 3387217.5 | [5 empty] | 95995.9412 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1443
PKG#144 | 4 | 2019-02-28 | 2019-02-27 | 2019-02-27 | 30 | 2019-03-29 | 2019-03-11 | 11224614.67 | 6888545.72 | 6887337.01 | 22222651.67 |  |  | 3387217.5 | [5 empty] | 166711.01 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1444
PKG#144 | 5 | 2019-02-28 | 2019-03-11 | 2019-03-11 | 30 | 2019-04-10 | 2019-03-11 | 0 | 7206339.73 | 7206339.73 | 22222651.67 |  |  | 3387217.5 | [5 empty] | 166711.64 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1445
PKG#144 | 6 | 2019-03-31 | 2019-03-14 | 2019-03-14 | 30 | 2019-04-13 | 2019-03-21 | 24444079.39 | 14801921.82 | 14929468.44 | 46666731.06 |  |  | 3262056.75 | [5 empty] | 319957.75 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1446
PKG#144 | 7 | 2019-03-31 | 2019-03-30 | 2019-03-30 | 30 | 2019-04-29 | 2019-04-11 | 20465525.6228 | 12603636.3289 | 12477244.23 | 67132256.6828 |  |  | 3501000 | [5 empty] | 672293.8257 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1447
PKG#144 | 8 | 2019-04-30 | 2019-04-15 | 2019-04-15 | 30 | 2019-05-15 | 2019-05-04 | 16379645.0372 | 8909777.64 | 8906660.63 | 83511901.72 |  |  | 0 | [5 empty] | 795592.47 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1448
PKG#144 | 9 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 30 | 2019-06-04 | 2019-05-15 | 10281327.2057 | 9777923.5506 | 9782161.34 | 93793228.9257 |  |  | 816900 | [5 empty] | 900089.7717 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#1449
PKG#144 | 10 | 2019-05-31 | 2019-05-20 | 2019-05-20 | 30 | 2019-06-19 | 2019-05-30 | 13881511.5343 | 11184527.72 | 11074114.43 | 107674740.46 | [8 empty] | 1113537.73 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#14410
PKG#144 | 11 | 2019-06-30 | 2019-06-20 | 2019-06-18 | 30 | 2019-07-18 | 2019-07-11 | 9087190.46 | 7486833.97 | 7386054.95 | 116761930.92 |  |  | 0 | [5 empty] | 1199420.77 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#14411
PKG#144 | 12 | 2019-08-31 | 2019-09-05 | 2019-09-04 | 30 | 2019-10-04 | 2019-10-03 | 34717376.42 | 22411649.36 | 21073691.31 | 151479307.34 | [8 empty] | 8633180.89 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#14412
PKG#144 | 13 | 2019-12-31 | 2019-12-25 | 2019-12-25 | 30 | 2020-01-24 | 2020-01-22 | 11410387.23 | 14635108.89 | 14000000 | 162889694.57 | [8 empty] | 9246101.93 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#14413
PKG#144 | 14 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 30 | 2020-03-04 | 2020-02-19 | 10733689.1131 | 10377806.9192 | 10173240.83 | 173623383.6831 | [8 empty] | 8262612.0833 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#14414
PKG#144 | 15 | 2020-08-31 | 2020-08-20 | 2020-12-13 | 30 | 2021-01-12 | 2020-12-13 | 2638692.2969 | 10405304.53 | 9960243.27 | 176262075.98 | [8 empty] | 2614017.44 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#14415
PKG#144 | 16 | 2021-01-31 | 2021-01-20 | 2021-01-21 | 30 | 2021-02-20 | 2021-03-25 | 150533.34 | 1132971.99 | 1116473.97 | 176412609.32 | [8 empty] | 2496617.44 | EMAAR-PKG# 144, Marassi | [7 empty] | PKG#14416
PKG#162 | 2 | 2020-02-29 | 2020-02-29 | 2020-03-05 | 40 | 2020-04-14 | 2020-03-22 | 8785941.99 | 7794726.52 | 7794726.52 | 8785941.99 |  |  | 749579.79 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1622
PKG#162 | 3 | 2020-03-31 | 2020-03-18 | 2020-03-21 | 40 | 2020-04-30 | 2020-03-30 | 6446622.36 | 5119599.35 | 5119599.34 | 15232564.35 |  |  | 531683.98 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1623
PKG#162 | 4 | 2020-03-31 | 2020-04-06 | 2020-04-06 | 40 | 2020-05-16 | 2020-04-22 | 7314177.64 | 6336538.23 | 6336538.23 | 22546741.99 |  |  | 1033463.45 | [5 empty] | 57000 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1624
PKG#162 | 5 | 2020-04-30 | 2020-05-05 | 2020-05-04 | 40 | 2020-06-13 | 2020-05-13 | 8006098.57 | 6124877.69 | 6124877.69 | 30552840.56 |  |  | 592328.38 | [5 empty] | 157000 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1625
PKG#162 | 6 | 2020-05-31 | 2020-06-06 | 2020-06-10 | 40 | 2020-07-20 | 2020-06-26 | 5990865.4963 | 4824045.381 | 4824045.39 | 36543706.0563 |  |  | 474838.875 | [5 empty] | 157000 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1626
PKG#162 | 7 | 2020-06-30 | 2020-07-06 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-29 | 8577628.8704 | 7215874.2121 | 7215874.2121 | 45121334.9266 |  |  | 834531.375 | [5 empty] | 260419 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1627
PKG#162 | 8 | 2020-07-31 | 2020-08-10 | 2020-08-16 | 40 | 2020-09-25 | 2020-09-03 | 12161063.3859 | 9432027.7177 | 9432027.72 | 57282398.3125 |  |  | 136265.25 | [5 empty] | 261806 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1628
PKG#162 | 9 | 2020-08-31 | 2020-09-05 | 2020-09-09 | 40 | 2020-10-19 | 2020-09-28 | 10973106.5017 | 9889305.1266 | 9889305 | 68255504.8142 |  |  | 1100385 | [5 empty] | 61806 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1629
PKG#162 | 10 | 2020-09-30 | 2020-10-05 | 2020-10-07 | 40 | 2020-11-16 | 2020-11-03 | 14493217.0374 | 13282474.2108 | 13282474.2108 | 82748721.8517 |  |  | 1005156.4395 | [5 empty] | 61806 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16210
PKG#162 | 11 | 2020-10-31 | 2020-11-05 | 2020-11-05 | 40 | 2020-12-15 | 2020-12-02 | 9303551.5202 | 7840185.4913 | 7840185.48 | 92052273.3719 | [8 empty] | 93807 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16211
PKG#162 | 12 | 2020-11-30 | 2020-12-01 | 2020-12-13 | 40 | 2021-01-22 | 2021-02-02 | 7499598.7681 | 4608392 | 4608392 | 99551872.14 |  |  | 0 | [5 empty] | 2426668.64 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16212
PKG#162 | 13 | 2020-12-31 | 2021-01-01 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-09 | 709528.8141 | 3429815.246 | 3429815.246 | 100261400.9541 | [8 empty] | 2376668.64 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16213
PKG#162 | 14 | 2021-01-31 | 2021-02-01 | 2021-02-03 | 40 | 2021-03-15 | 2021-02-24 | -0.004055 | 502581.44 | 502581.43 | 100261400.95 | [8 empty] | 1926668.64 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16214
PKG#162 | 15 | 2021-01-31 | 2021-02-01 | 2021-11-18 | 40 | 2021-12-28 | 2022-03-07 | 0.05 | 3683579.28 | 3999402.59 | 100261401 | [8 empty] | 926668 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16215
PKG#163 | 2 | 2020-06-30 | 2020-07-07 | 2020-07-07 | 40 | 2020-08-16 | 2020-07-22 | 167514.17 | 1068966.43 | 1068966.43 | 167514.17 |  |  | 1392714.35 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1632
PKG#163 | 3 | 2020-07-31 | 2020-08-10 | 2020-08-18 | 40 | 2020-09-27 | 2020-08-26 | 1873525.03 | 2977091.11 | 2977091.11 | 2041039.2 |  |  | 3794104.59 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1633
PKG#163 | 4 | 2020-08-31 | 2020-09-03 | 2020-09-03 | 40 | 2020-10-13 | 2020-09-23 | 3480646.03 | 6845695.77 | 6845695.77 | 5521685.23 |  |  | 10183594.03 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1634
PKG#163 | 5 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 40 | 2020-11-09 | 2020-10-22 | 3896848.6915 | 3782501.2803 | 3782501.29 | 9418533.9215 |  |  | 11640240.8375 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1635
PKG#163 | 6 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 40 | 2020-12-13 | 2020-11-29 | 8635132.0099 | 6255172.4375 | 6255172.17 | 18053665.9314 |  |  | 11614831.0892 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1636
PKG#163 | 7 | 2020-11-30 | 2020-12-07 | 2020-12-08 | 40 | 2021-01-17 | 2020-12-23 | 4420616.8286 | 4922193.5 | 4922193.5 | 22474282.76 |  |  | 14196023.04 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1637
PKG#163 | 8 | 2020-12-31 | 2021-01-05 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-02 | 7415396.32 | 6050639.7742 | 6050639.77 | 29889679.08 |  |  | 15239713.55 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1638
PKG#163 | 9 | 2021-01-31 | 2021-01-25 | 2021-02-25 | 40 | 2021-04-06 | 2021-03-08 | 5020188.6174 | 4602212.1569 | 4602212.16 | 34909867.6974 |  |  | 16642238.4803 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1639
PKG#163 | 10 | 2021-02-28 | 2021-02-25 | 2021-03-03 | 40 | 2021-04-12 | 2021-10-23 | 3812993.5626 | 2532838.57 | 2532838.57 | 38722861.26 |  |  | 16355289.4 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16310
PKG#163 | 11 | 2021-03-31 | 2021-03-25 | 2021-03-31 | 40 | 2021-05-10 | 2021-04-25 | 3832626.3 | 3799097.57 | 3799097.57 | 42555487.56 |  |  | 17842244.91 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16311
PKG#163 | 12 | 2021-04-30 | 2021-04-25 | 2021-05-04 | 40 | 2021-06-13 | 2021-06-03 | 3268183.05 | 2215480.09 | 2215480.09 | 45823670.61 |  |  | 17661654.17 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16312
PKG#163 | 13 | 2021-05-31 | 2021-05-25 | 2021-05-31 | 40 | 2021-07-10 | 2021-06-21 | 6375780.44 | 3821253.39 | 3821253.39 | 52199451.05 |  |  | 16405178.95 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16313
PKG#163 | 14 | 2021-06-30 | 2021-06-26 | 2021-07-01 | 40 | 2021-08-10 | 2021-08-02 | 13281620.95 | 10697999.42 | 10697999.42 | 65481072 |  |  | 18157750.16 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16314
PKG#163 | 15 | 2021-07-31 | 2021-07-25 | 2021-08-02 | 40 | 2021-09-11 | 2021-08-26 | 7388288.7 | 4024675.65 | 4024676.65 | 72869360.7 |  |  | 16257345.38 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16315
PKG#163 | 16 | 2021-08-31 | 2021-08-25 | 2021-09-06 | 40 | 2021-10-16 | 2021-09-30 | 6043601.4 | 3611195.73 | 3611195.74 | 78912962.1 |  |  | 15138470.41 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16316
PKG#163 | 17 | 2021-09-30 | 2021-09-25 | 2021-10-03 | 40 | 2021-11-12 | 2021-10-27 | 5496981.8 | 2445757.34 | 2445757.34 | 84409943.9 |  |  | 12955550.43 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16317
PKG#163 | 18 | 2021-10-31 | 2021-10-25 | 2021-11-01 | 40 | 2021-12-11 | 2021-11-15 | 3301294.98 | 3026069.35 | 2445757.34 | 87711238.88 |  |  | 13929653.03 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16318
PKG#163 | 19 | 2021-11-30 | 2021-11-25 | 2021-11-30 | 40 | 2022-01-09 | 2021-12-16 | 9320216.47 | 7895027.24 | 6520369.14 | 97031455.35 |  |  | 15728609.99 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16319
PKG#163 | 20 | 2021-12-31 | 2021-12-25 | 2022-01-02 | 40 | 2022-02-11 | 2022-01-19 | 4346059.97 | 2340959.11 | 3715617.2 | 101377515.32 |  |  | 14609274.92 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16320
PKG#163 | 21 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 40 | 2022-03-15 | 2022-03-17 | 5919076.73 | 5322260.63 | 5322260.63 | 107296592.05 |  |  | 15284733.68 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16321
PKG#163 | 22 | 2022-02-28 | 2022-02-28 | 2022-03-01 | 40 | 2022-04-10 | 2022-03-23 | 2632588.63 | 2261775.79 | 2261775.79 | 109929180.68 |  |  | 15087666.62 |  |  |  | 3262202.645 | 3262202.645 | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16322
PKG#163 | 23 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 40 | 2022-05-17 | 2022-09-06 | 6399693.2 | 3449740.51 | 3449740.5053 | 116328873.88 |  |  | 12447737.11 |  |  |  | 3363997.5 | 3363997.5 | 139451 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16323
PKG#163 | 24 | 2022-04-30 | 2022-04-20 | 2022-04-28 | 40 | 2022-06-07 | 2022-09-06 | 6669347.19 | 5681606.52 | 5681606.5237 | 122998221.07 |  |  | 11928679.08 | 79159509 |  | 106910.74 | 3526010 | 3526010 | 170264.36 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16324
PKG#163 | 25 | 2022-05-31 | 2022-05-25 | 2022-06-02 | 40 | 2022-07-12 | 2022-09-06 | 12929046.56 | 11730565.83 | 11730565.831 | 135927267.63 |  |  | 11655699.31 | 84070405.07 |  | 214226.97 | 3858707 | 3858707 | 170264.36 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16325
PKG#163 | 26 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 40 | 2022-08-14 | 2022-09-19 | 6526578.31 | 6014332.37 | 6014332.37 | 142453845.94 |  |  | 11222354.42 | 87095709.46 |  | 214226.97 | 4019196.11 | 4019196.11 | 170264 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16326
PKG#163 | 27 | 2022-07-31 | 2022-07-31 | 2022-08-09 | 40 | 2022-09-18 | 2022-09-25 | 4132634.87 | 3457484.33 | 3457484.33 | 146586480.81 |  |  | 10805467.52 | 88908671.92 |  | 214226.97 | 4117255.5 | 4117255.5 | 170264 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16327
PKG#163 | 28 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 40 | 2022-10-22 | 2022-11-10 | 17622733.92 | 18331730.1 | 18331730.1 | 164209214.73 |  |  | 13098222.27 | 70785988.93 |  | 693580.47 | 4637171.235 | 4637171.235 | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16328
PKG#163 | 29 | 2022-09-30 | 2022-09-30 | 2022-10-20 | 40 | 2022-11-29 | 2023-01-15 | 20296742.22 | 18785649.76 | 18785649.76 | 184505956.95 |  |  | 13098222.27 | 159762353.93 |  | 693580.47 | 5169960.72 | 5169960.72 | 170264.36 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16329
PKG#163 | 30 | 2023-01-31 | 2023-01-18 | 2023-01-18 | 40 | 2023-02-27 | 2023-08-09 | 8788912.25 | 3193802.31 | 3193802.31 | 193294869.2 |  |  | 8080616.05 | 66836818.15 |  | 624222.43 | 5275229.5 | 5275229.5 | 688139.36 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16330
PKG#163 | 31 | 2023-02-28 | 2023-02-28 | 2023-03-15 | 40 | 2023-04-24 | 2023-08-09 | -406906.47 | 1079324.1 | 1079324.09 | 192887962.73 |  |  | 9732318.5 | 56933789.25 |  | 1100688.83 | 5305840.78 | 5305840.78 | 688139.36 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16331
PKG#163 | 32 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 40 | 2023-06-23 | 2023-12-13 | 5753296.48 | 4562478.01 | 4562478.02 | 198641259.21 |  |  | 8867308.69 | 66948753.43 |  | 1100688.83 | 5435239.565 | 5435239.565 | 688139.36 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16332
PKG#163 | 33 | 2023-05-31 | 2023-05-31 | 2023-06-11 | 40 | 2023-07-21 |  |  | 5000000 | 0.0001 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16333
PKG#163 | 34 | 2023-06-30 | 2023-07-10 | 2023-07-13 | 40 | 2023-08-22 |  |  | 5000000 | 0.0001 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16334
PKG#163 | 35 | 2023-10-31 | 2023-11-14 | 2023-11-15 | 40 | 2023-12-25 |  |  | 5000000 | 0.0001 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16335
PKG#163 | 36 | 2024-05-31 | 2024-05-21 | 2024-05-26 | 40 | 2024-07-05 |  |  | 10852799 | 0 | 221749507 | [8 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#16336
PKG#177 | 2 | 2021-04-30 | 2021-04-30 | 2021-04-26 | 30 | 2021-05-26 | 2021-05-12 | 8478947.03 | 10240448.36 | 10240448.36 | 8478947.03 |  |  | 4144486.18 | [5 empty] | 16912.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1772
PKG#177 | 3 | 2021-04-30 | 2021-04-25 | 2021-05-05 | 30 | 2021-06-04 | 2021-05-26 | 9.9998e-05 | 3893019.54 | 3893019.54 | 8478947.03 |  |  | 9209962.12 | [5 empty] | 16912.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1773
PKG#177 | 4 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 30 | 2021-06-09 | 2021-05-27 | 5088605.14 | 4135304.94 | 14139690.65 | 13567552.17 |  | 10000000 | 9209962.12 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1774
PKG#177 | 5 | 2021-05-31 | 2021-05-25 | 2021-05-26 | 30 | 2021-06-25 | 2021-06-03 | 0.0001 | 1889110.9 | 11890262.73 | 13567552.17 |  | 10000000 | 11628798.1 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1775
PKG#177 | 6 | 2021-05-31 | 2021-05-25 | 2021-05-30 | 30 | 2021-06-29 | 2021-06-21 | 0.0001 | 2069539.45 | 12069539.45 | 13567552.17 |  | 10000000 | 14278656.55 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1776
PKG#177 | 7 | 2021-05-31 | 2021-05-25 | 2021-06-02 | 30 | 2021-07-02 | 2021-06-21 | 0.0001 | 30000000 | 40000000 | 13567552.17 |  | 10000000 | 14278656.55 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1777
PKG#177 | 8 | 2021-05-31 | 2021-05-25 | 2021-06-06 | 30 | 2021-07-06 | 2021-06-21 | 7777231.12 | 6324855.08 | 16325726.09 | 21344783.29 |  | 10000000 | 14212069.8 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1778
PKG#177 | 9 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 30 | 2021-07-09 | 2021-06-21 | 0.0001 | 1386804.78 | 11386804.78 | 21344783.29 |  | 10000000 | 15987748.13 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#1779
PKG#177 | 10 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 9.9996e-05 | 1030274.11 | 11031892.42 | 21344783.29 |  | 10000000 | 17306921.13 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17710
PKG#177 | 11 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 0.00010001 | 1623911.78 | 11623911.78 | 21344783.29 |  | 10000000 | 19386193.57 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17711
PKG#177 | 12 | 2021-05-31 | 2021-06-10 | 2021-06-17 | 30 | 2021-07-17 | 2021-07-08 | 17543747.3405 | 11864115.6307 | 11867471.98 | 38888530.6305 |  |  | 16150782.833 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17712
PKG#177 | 13 | 2021-05-31 | 2021-06-10 | 2021-06-24 | 30 | 2021-07-24 | 2021-07-08 | -0.0001 | 4287396.18 | 4287396.18 | 38888530.6305 |  |  | 21640406.623 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17713
PKG#177 | 14 | 2021-06-30 | 2021-07-10 | 2021-07-07 | 30 | 2021-08-06 | 2021-07-08 | -0.0006304 | 3654358.5 | 3654358.5 | 38888530.63 |  |  | 26319482.8 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17714
PKG#177 | 15 | 2021-06-30 | 2021-07-10 | 2021-07-11 | 30 | 2021-08-10 | 2021-07-15 | 0.00043038 | 30000000 | 30000000 | 38888530.6305 |  |  | 26319482.803 | [5 empty] | 57062.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17715
PKG#177 | 16 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 30 | 2021-08-14 | 2021-08-08 | 49248459.9349 | 8979568.5092 | 8978914.16 | 88136990.5654 |  |  | 24945340.303 | [5 empty] | 415112.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17716
PKG#177 | 17 | 2021-06-30 | 2021-07-10 | 2021-07-28 | 30 | 2021-08-27 | 2021-08-10 | 0.0045094 | 311058.51 | 311248.17 | 88136990.57 |  |  | 25343622.64 | [5 empty] | 415112.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17717
PKG#177 | 18 | 2021-06-30 | 2021-07-10 | 2021-08-02 | 30 | 2021-09-01 | 2021-09-02 | 12925810.52 | 15056356.09 | 15059090.32 | 101062801.09 |  |  | 31043670.3 | [5 empty] | 415112.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17718
PKG#177 | 19 | 2021-07-31 | 2021-07-25 | 2021-08-05 | 30 | 2021-09-04 | 2021-09-16 | -0.0001 | 6139746.33 | 6143418.31 | 101062801.09 |  |  | 38754821.03 | [5 empty] | 528137.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17719
PKG#177 | 20 | 2021-07-31 | 2021-07-25 | 2021-08-08 | 30 | 2021-09-07 | 2021-10-19 | 10455877.97 | 7622310.5 | 7621726.83 | 111518679.06 |  |  | 37529135.79 | [5 empty] | 528137.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17720
PKG#177 | 21 | 2021-07-31 | 2021-07-25 | 2021-08-17 | 30 | 2021-09-16 | 2021-11-18 | 10986391.49 | 5555354.29 | 5553244.96 | 122505070.55 |  |  | 33099520.87 | [5 empty] | 528137.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17721
PKG#177 | 22 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 30 | 2021-09-30 | 2021-12-07 | 7592601.09 | 3438276.09 | 3436603.03 | 130097671.64 |  |  | 29527784.9 | [5 empty] | 528137.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17722
PKG#177 | 23 | 2021-08-31 | 2021-09-05 | 2021-09-08 | 30 | 2021-10-08 | 2022-01-04 | 4755868.7 | 4323818.2 | 4324164.09 | 134853540.34 |  |  | 30254166.65 | [5 empty] | 674051.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17723
PKG#177 | 24 | 2021-08-31 | 2021-09-05 | 2021-09-12 | 30 | 2021-10-12 | 2022-01-26 | 5954515.89 | 4835550.93 | 4835218.42 | 140808056.23 |  |  | 29555882.9 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17724
PKG#177 | 25 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 30 | 2021-11-05 | 2022-02-28 | 3618126.71 | 4062127.69 | 4062657.22 | 144426182.94 |  |  | 30667900.14 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17725
PKG#177 | 26 | 2021-10-31 | 2021-10-25 | 2021-11-03 | 30 | 2021-12-03 | 2022-03-13 | -0.00099997 | 30000000 | 30000000 | 144426182.94 |  |  | 30667900.14 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17726
PKG#177 | 27 | 2021-11-30 | 2021-11-25 | 2021-12-07 | 30 | 2022-01-06 | 2022-03-23 | 1336271.1 | 1920178.92 | 1920749.49 | 145762454.04 |  |  | 31729493.34 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17727
PKG#177 | 28 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-03-30 | 4959294.77 | 3761592.26 | 3761281.17 | 150721748.81 |  |  | 31076204.59 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17728
PKG#177 | 29 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-04-05 | -0.0001 | 30000000 | 30000000 | 150721748.81 |  |  | 31076204.59 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17729
PKG#177 | 30 | 2021-12-31 | 2021-12-30 | 2022-01-05 | 30 | 2022-02-04 | 2022-04-18 | 13573272.69 | 11173851.87 | 11174297.33 | 164295021.5 |  |  | 32011659.59 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17730
PKG#177 | 31 | 2022-04-30 | 2022-04-18 | 2022-04-18 | 30 | 2022-05-18 | 2022-04-19 | -0.0001 | 20000000 | 20000000 | 164295021.5 |  |  | 32011659.59 | [5 empty] | 1244836 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17731
PKG#177 | 32 | 2022-01-31 | 2022-01-31 | 2022-02-10 | 30 | 2022-03-12 | 2022-05-10 | 10655190.55 | 9586713.98 | 9586612.72 | 174950212.05 |  |  | 31704142.35 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17732
PKG#177 | 33 | 2022-03-31 | 2022-03-28 | 2022-05-22 | 30 | 2022-06-21 |  |  |  | 9774603.63 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17733
PKG#177 | 34 | 2022-02-28 | 2022-03-01 | 2022-03-06 | 30 | 2022-04-05 | 2022-06-01 | 4083110.25 | 3242747.22 | 3243420.79 | 189971239 |  |  | 33248463 |  |  |  | 5813429 | 5813429 | 1266148 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17734
PKG#177 | 35 | 2022-04-30 | 2022-04-20 | 2022-06-08 | 30 | 2022-07-08 | 2022-06-08 | 20620247 | 14874314.24 | 14874314 | 210591486 |  |  | 32687951 |  |  |  | 6340697.5 | 6340697.5 | 1273436 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17735
PKG#177 | 36 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 | 2022-08-04 | 41964961.54 | 32974130.9 | 32974130.9 | 252556447.54 |  |  | 55952679 |  |  |  | 8027886.035 | 8027886.035 | 2506369.82 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17736
PKG#177 | 37 | 2022-03-31 | 2022-04-12 | 2022-04-12 | 30 | 2022-05-12 | 2022-08-14 | 3201525.38 | 2963171.82 | 2963171.82 | 255757972.92 |  |  | 55952679 |  |  |  | 8111926.08 | 8111926.08 | 1543023.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17737
PKG#177 | 38 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 | 2022-08-15 | 113074932.04 | 40830987.19 | 40830987.19 | 368832904.96 |  |  | 41102851 |  |  | 430147 | 10708897.325 | 10708897.325 | 8967998.5 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17738
PKG#177 | 39 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 | 2022-10-03 | 62332263.27 | 24380106.6 | 24380106.6 | 431165168.23 |  |  | 36844292 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17739
PKG#177 | 40 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 30 | 2022-08-30 | 2022-11-22 | 2265658.58 | 0.0001 | 0.0001 | 433430826.81 |  |  | 36844292 |  |  | 430147 |  |  | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17740
PKG#177 | 41 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 | 2022-11-22 | 16308262.76 | 0.0001 | 1e-05 | 449739089.57 |  |  | 23473659 | [5 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17741
PKG#177 | 42 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 30 | 2022-10-30 | 2023-02-22 | 25575904.54 | 4207031.92 | 4198626.99 | 475314994.11 | [8 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17742
PKG#177 | 43 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-04-13 | -1403499.79 | 14488837.89 | 14488992.22 | 473911494.32 |  |  | 23473659 | 399954494 |  | 430147.49 | 12864128.305 | 12864128.305 | 3512870.7 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17743
PKG#177 | 44 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-05-25 | 59788309.64 | 17144236.06 | 17144236.06 | 533699803.96 |  |  | 11107434 | 448361770 |  | 430147.49 | 13994560.62 | 13994560.62 | 4392870.7 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17744
PKG#177 | 45 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 30 | 2022-10-07 | 2023-06-15 | 102598790.27 | 15002016.49 | 15002016.49 | 576510284.59 |  |  | 12544287.37 | 474871564.16 |  | 430147.49 | 14726364.3 | 14726364.3 | 4392870.7 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17745
PKG#177 | 46 | 2022-09-30 | 2022-09-25 | 2022-10-17 | 30 | 2022-11-16 | 2023-07-16 | -22395666.32 | 3056265.5 | 3048300.98 | 554114618.27 |  |  | 12544287.37 | 479879018.92 |  | 430147 | 14857839.5 | 14857839.5 | 8396085.7 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17746
PKG#177 | 47 | 2023-06-30 | 2023-06-25 | 2023-02-15 | 30 | 2023-03-17 | 2023-08-03 | 6780617.51 | 4274854.67 | 4274072.25 | 560895235.78 |  |  | 10901184.51 | 486669436 |  | 430147 | 14994854.5 | 14994854.5 | 8396085.7 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17747
PKG#177 | 48 | 2023-03-31 | 2023-03-25 | 2023-03-26 | 30 | 2023-04-25 |  |  | 4111000 | 1e-06 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17748
PKG#177 | 49 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 30 | 2023-06-13 |  |  | 0.0001 | 1e-06 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17749
PKG#177 | 50 | 2023-05-31 | 2023-05-31 | 2023-06-04 | 30 | 2023-07-04 |  |  | 0.001 | 1e-06 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17750
PKG#177 | 51 | 2023-06-30 | 2023-06-25 | 2023-06-25 | 30 | 2023-07-25 |  |  | 0.001 | 1e-06 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17751
PKG#177 | 52 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 30 | 2023-09-13 |  |  | 45000000 | 1e-06 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17752
PKG#177 | 53 | 2023-10-31 | 2023-11-14 | 2023-11-14 | 30 | 2023-12-14 |  |  | 5000000 | 1e-06 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17753
PKG#177 | 54 | 2024-05-31 | 2024-06-04 | 2024-06-05 | 30 | 2024-07-05 |  |  | 14081143 | 0 | 626950196.89 | [8 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#17754
PKG#177 - DP | 1 | 2021-03-31 | 2021-03-24 | 2021-03-24 | 30 | 2021-04-23 |  |  | 22337274.9 | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - DP1
PKG#177 - SWI 07 | 1 | 2021-11-30 | 2021-12-15 | 2021-12-13 | 30 | 2022-01-12 |  |  | 1800000 | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 071
PKG#177 - SWI 07 | 2 | 2021-12-31 | 2021-12-31 | 2022-01-03 | 30 | 2022-02-02 |  |  | 4300000 | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 072
PKG#177 - SWI 07 | 3 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 |  |  | 5800000 | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 073
PKG#177 - SWI 07 | 4 | 2022-02-28 | 2022-02-28 | 2022-03-02 | 30 | 2022-04-01 |  |  |  | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 074
PKG#177 - SWI 07 | 5 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 |  |  | 9500000 | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 075
PKG#177 - SWI 07 | 6 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 |  | 3141613.418 | 5000000 | 0 | 31868573.268 | [5 empty] | 1025274 |  |  | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 076
PKG#177 - SWI 07 | 7 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 |  | 10847798.8446 | 4000000 | 0 | 42716372.1126 | [8 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 077
PKG#177 - SWI 07 | 8 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 |  |  | 500000 | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 078
PKG#177 - SWI 07 | 9 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 30 | 2022-09-09 |  |  | 4000000 | 0 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 079
PKG#177 - SWI 07 | 10 | 2022-09-30 | 2022-09-30 | 2022-10-17 | 30 | 2022-11-16 |  |  |  | 1e-05 | [9 empty] | 0 | EMAAR-Pkg#162/163- Marassi | [7 empty] | PKG#177 - SWI 0710
PKG#178 | 2 | 2021-02-28 | 2021-02-28 | 2021-03-04 | 30 | 2021-04-03 | 2021-04-14 | 16123744.18 | 13230338.29 | 13230338.29 | 16123744.18 | [8 empty] | 0 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1782
PKG#178 | 3 | 2021-03-31 | 2021-03-31 | 2021-04-04 | 30 | 2021-05-04 | 2021-04-28 | 8196011.07 | 6675236.88 | 6675236.88 | 24319755.25 |  |  | 1215987.76 | [5 empty] | 50000 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1783
PKG#178 | 4 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 30 | 2021-06-04 | 2021-06-03 | 7478094.91 | 6081013.28 | 6081013.29 | 31797850.16 | [8 empty] | 0 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1784
PKG#178 | 5 | 2021-05-31 | 2021-06-07 | 2021-06-08 | 30 | 2021-07-08 | 2021-06-21 | 10300781.8 | 9125492.66 | 9125492.66 | 42098631.96 | [8 empty] | 105137.6 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1785
PKG#178 | 6 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 30 | 2021-08-10 | 2021-09-21 | 4524611.34 | 2730279.03 | 2730279.03 | 46623243.3 |  |  | 0 | [5 empty] | 1562612.5 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1786
PKG#178 | 7 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 30 | 2021-12-02 | 2021-12-02 | 686559 | 1844728.45 | 1644401.99 | 47309802.3 |  |  | 0 | [5 empty] | 1595537.5 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1787
PKG#178 | 8 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 | 2022-02-28 | 1389835.54 | 595920.46 | 595920.45 | 48699637.84 | [6 empty] | 1278365.495 | 1278365.495 | 0 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1788
PKG#178 | 9 | 2022-08-31 | 2022-08-28 | 2022-08-30 | 30 | 2022-09-29 | 2022-10-09 | 31809.52 | 88751.13 | 289077.6 | 48731447.36 | [6 empty] | 1279200.495 | 1279200.495 | 2370468.93 | BKG#178-Lagoon Discharge | [7 empty] | PKG#1789
PKG#178 | 10 | 2023-01-31 | 2023-01-25 | 2023-05-29 | 30 | 2023-06-28 | 2023-06-02 | -0.0001 | 2080200.49 | 2235574.97 | 48731447.36 |  |  |  | 12630627.58 |  | 413484.78 |  |  | 1769468.93 | BKG#178-Lagoon Discharge | [7 empty] | PKG#17810
PKG#178 - DP | 1 | 2021-01-31 | 2021-01-25 | 2021-01-25 | 30 | 2021-02-24 | 2021-02-02 |  | 3747170.2 | 0 | [9 empty] | 0 | BKG#178-Lagoon Discharge | [7 empty] | PKG#178 - DP1
PKG#205 | 2 | 2022-04-30 | 2022-04-28 | 2022-05-24 | 30 | 2022-06-23 | 2022-05-24 | 1935314 | 1181605.96 | 1181605.96 | 1935314 |  |  | 0 | 0 |  | 0 | 50801.99 | 50801.99 | 0 | 0 | [7 empty] | PKG#2052
PKG#205 | 3 | 2022-05-31 | 2022-05-31 | 2022-06-13 | 30 | 2022-07-13 | 2022-06-13 | 2048098 | 1250466.11 | 1250466.11 | 3983412 | [5 empty] | 63808.49 | 104564.5 | 104564.5 | 0 | 0 | [7 empty] | PKG#2053
PKG#220B | 2 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 30 | 2023-07-07 | 2023-06-20 | 12159328.08 | 8261597.76 | 8261597.76 | 12159328.08 | [6 empty] | 319182.36 | 319182.36 | 0 | SOL Town PKG.220 | [7 empty] | PKG#220B2
PKG#220B | 3 | 2023-06-30 | 2023-07-05 | 2023-07-10 | 30 | 2023-08-09 | 2023-08-14 | 11462411.01 | 5980500.04 | 5980500.04 | 23621739.09 | [6 empty] | 620070.65 | 620070.65 | 1017875 | SOL Town PKG.220 | [7 empty] | PKG#220B3
PKG#220B | 4 | 2023-07-31 | 2023-08-05 | 2023-08-07 | 30 | 2023-09-06 |  |  | 2300000 | 2300000 | [9 empty] | 0 | SOL Town PKG.220 | [7 empty] | PKG#220B4
PKG#220B - DP | 1 | 2023-05-31 | 2023-05-21 | 2023-05-21 | 30 | 2023-06-20 |  |  |  | 0 | [9 empty] | 0 | SOL Town PKG.220 | [7 empty] | PKG#220B - DP1
PKG#45 | 46 | 2018-06-30 | 2018-07-15 | 2018-09-18 |  | 2018-12-15 | 2018-11-21 |  | 1069392.54 | 1844931.02 | 59167173.46 | [9 empty] | 0 | [7 empty] | PKG#4546
PKG#58 | 22 | 2015-12-31 | 2015-12-29 | 2015-12-29 |  | 2018-11-15 | 2018-10-21 | 0 | 317558.66 | 327696.29 | 4831971.92 | [9 empty] | 0 | [7 empty] | PKG#5822
PKG#85 | 5 | 2018-10-31 | 2018-10-17 | 2018-11-11 | 30 | 2018-12-11 |  |  |  | 1729285.15 | [10 empty] | EMAAR-PKG#85-UPTOWN | [7 empty] | PKG#855
PKG#85 | 6 | 2019-02-28 | 2019-02-28 | 2019-03-09 | 30 | 2019-04-08 | 2019-05-20 | 2033193.5852 | 768766.5752 | 768766.59 | 8147064.8613 | [9 empty] | EMAAR-PKG#85-UPTOWN | [7 empty] | PKG#856
PKG#85 | 7 | 2019-05-31 | 2019-05-15 | 2019-06-10 | 30 | 2019-07-10 |  |  |  | 29830.3 | [10 empty] | EMAAR-PKG#85-UPTOWN | [7 empty] | PKG#857
PKG#85 | 8 | 2019-10-31 | 2019-10-11 | 2019-11-18 | 30 | 2019-12-18 |  |  |  | 1391898.96 | [10 empty] | EMAAR-PKG#85-UPTOWN | [7 empty] | PKG#858
PO#11687 | 1 | 2018-12-31 | 2019-01-10 | 2019-01-10 | 15 | 2019-01-25 |  |  |  | 1090584 | [9 empty] | 0 | 0 | [7 empty] | PO#116871
PO#11687 | 2 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 15 | 2019-03-15 |  |  |  | 451528 | [9 empty] | 0 | 0 | [7 empty] | PO#116872
PO#11687 | 3 | 2019-03-31 | 2019-04-14 | 2019-08-22 | 15 | 2019-09-06 |  |  |  | 293788 | [9 empty] | 0 | 0 | [7 empty] | PO#116873
PO#11687 | 5 | 2019-11-30 | 2019-12-18 | 2019-12-19 | 15 | 2020-01-03 |  |  |  | 343200 | [9 empty] | 0 | 0 | [7 empty] | PO#116875
Port Said Silos | 1 | 2022-03-31 | 2022-03-25 | 2022-03-05 | 21 | 2022-03-26 | 2022-04-24 | 9011475.2 | 5248643 | 37788892.4 | 9011475.2 | 26540249.4 | [7 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos1
Port Said Silos | 2 | 2022-04-30 | 2022-04-25 | 2022-04-28 | 21 | 2022-05-19 | 2022-05-17 | 2334108.9048 | 1688672.941 | 21773106 | 11345584.1048 | 15000000 | [7 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos2
Port Said Silos | 3 | 2022-05-31 | 2022-05-25 | 2022-06-02 | 21 | 2022-06-23 |  |  |  | 14623869 | [9 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos3
Port Said Silos | 4 | 2022-06-30 | 2022-06-29 | 2022-06-29 | 21 | 2022-07-20 |  |  |  | 22560435 | [9 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos4
Port Said Silos | 5 | 2022-07-31 | 2022-07-31 | 2022-08-02 | 21 | 2022-08-23 | 2022-08-09 | 5318356.3714 | 4009921 | 14009921 | 25985299.3429 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos5
Port Said Silos | 6 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 21 | 2022-09-21 | 2022-09-13 | 9017880.2762 | 6842722 | 21842722 | 35003179.619 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos6
Port Said Silos | 7 | 2022-09-30 | 2022-09-30 | 2022-10-02 | 21 | 2022-10-23 | 2022-10-18 | 4021476.8571 | 3061822 | 3061822 | 39024656.4762 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos7
Port Said Silos | 8 | 2022-10-31 | 2022-10-31 | 2022-11-07 | 21 | 2022-11-28 | 2022-11-21 | 22573115.9429 | 17260533 | 17260533 | 61597772.419 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos8
Port Said Silos | 9 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 21 | 2022-12-26 | 2022-12-19 | 3139225.2286 | 2370710 | 2370710 | 64736997.6476 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos9
Port Said Silos | 10 | 2022-12-31 | 2022-12-30 | 2023-01-01 | 21 | 2023-01-22 | 2023-01-22 | 8366928.5333 | 6384571 | 6384571 | 73103926.19 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos10
Port Said Silos | 11 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-02-15 | 5057462.5238 | 3852337 | 3852337 | 78161388.7138 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos11
Port Said Silos | 12 | 2023-02-28 | 2023-02-28 | 2023-03-01 | 21 | 2023-03-22 | 2023-03-20 | 2086813.5333 | 1587432 | 1587432 | 80248202.2471 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos12
Port Said Silos | 13 | 2023-03-31 | 2023-03-31 | 2023-04-02 | 21 | 2023-04-23 | 2023-04-02 | 612060.8329 | 451211.246 | 460093 | 80860263.08 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos13
Port Said Silos | 14 | 2023-04-30 | 2023-04-30 | 2023-05-02 | 21 | 2023-05-23 |  |  |  | 2136487 | [9 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos14
Port Said Silos | 15 | 2023-05-31 | 2023-05-30 | 2023-06-03 | 21 | 2023-06-24 | 2023-07-05 | 10044463.5619 | 7663669 | 7663669 | 93708293.0229 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos15
Port Said Silos | 16 | 2023-06-30 | 2023-06-30 | 2023-07-08 | 21 | 2023-07-29 | 2023-07-17 | 12501707.0667 | 9649102 | 9649102 | 106210000.0895 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos16
Port Said Silos | 17 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 21 | 2023-08-21 | 2023-08-15 | 7676679.5524 | 5738977 | 5738977 | 113886679.6419 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos17
Port Said Silos | 18 | 2023-08-31 | 2023-08-31 | 2023-09-03 | 21 | 2023-09-24 | 2023-10-03 | 7866196.5143 | 2991787 | 2991787 | 121752876.1562 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos18
Port Said Silos | 19 | 2023-09-30 | 2023-09-30 | 2023-10-01 | 21 | 2023-10-22 | 2023-10-16 | 17118439.2571 | 12748959 | 12748959 | 138871315.4133 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos19
Port Said Silos | 20 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 21 | 2023-11-22 | 2023-11-22 | 12988784 | 6593857 | 6593857 | 151860099.4133 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos20
Port Said Silos | 21 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 21 | 2023-12-21 | 2023-12-23 | 15886446.6476 | 11818794 | 11818794 | 167746546.061 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos21
Port Said Silos | 22 | 2023-12-31 | 2023-12-13 | 2023-12-14 | 21 | 2024-01-04 | 2023-12-27 | 6713332.6667 | 4826684 | 4826684 | 174459878.7276 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos22
Port Said Silos | 23 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 21 | 2024-01-25 | 2024-01-18 | 3587901.4571 | 2411082.19 | 2411082.19 | 178047780.1848 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos23
Port Said Silos | 24 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 21 | 2024-02-27 | 2024-02-21 | 4764115.7714 | 3306186 | 3306186 | 182811895.9562 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos24
Port Said Silos | 25 | 2024-02-29 | 2024-02-29 | 2024-03-04 | 21 | 2024-03-25 | 2024-04-07 | 4504742.6762 | 3280048 | 3280048 | 187316638.6324 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos25
Port Said Silos | 26 | 2024-03-31 | 2024-03-31 | 2024-04-04 | 21 | 2024-04-25 | 2024-05-07 | 2227046.781 | 426108 | 426108 | 189543685.4133 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos26
Port Said Silos | 27 | 2024-04-30 | 2024-05-01 | 2024-05-01 | 21 | 2024-05-22 | 2024-05-27 | 1522665.14 | 0.0001 | 0 | 191066350.5533 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos27
Port Said Silos | 28 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 21 | 2024-06-23 | 2024-07-01 | 3379589.9429 | 1239632 | 1239632 | 194445940.4962 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos28
Port Said Silos | 29 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 21 | 2024-07-28 | 2024-08-07 | 2107663.7333 | 337130 | 337130 | 196553604.2295 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos29
Port Said Silos | 30 | 2024-07-31 | 2024-07-31 | 2024-08-03 | 21 | 2024-08-24 | 2024-08-22 | 3191368.2381 | 100641 | 100641 | 199744972.4676 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos30
Port Said Silos | 31 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 2906595.6404 | 727554 | 727554 | 202651568.108 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos31
Port Said Silos | 32 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-11-03 | 4167368.41 | 2193035.35 | 2193035.35 | 206818936.518 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos32
Port Said Silos | 33 | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 |  |  |  | 2711136 | [9 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos33
Port Said Silos - Foreigner Supply | 1 | 2023-09-30 | 2023-09-30 | 2023-09-24 | 21 | 2023-10-15 | 2023-11-06 | 5539353.23 | 5206992.0362 | 5206992 | 5539353.23 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Foreigner Supply1
Port Said Silos - Foreigner Supply | 2 | 2023-10-31 | 2023-10-31 | 2023-12-05 | 21 | 2023-12-26 |  |  |  | 775509.45 | [9 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Foreigner Supply2
Port Said Silos - Local Supply | 1 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-03-16 | 673851.6 | 438003.54 | 655657.61 | 673851.6 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply1
Port Said Silos - Local Supply | 2 | 2023-09-30 | 2023-09-30 | 2023-10-18 | 21 | 2023-11-08 | 2023-11-06 | 1194976.6491 | 1162711.94 | 1162711.94 | 1868828.2491 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply2
Port Said Silos - Local Supply | 3 | 2024-02-29 | 2024-02-29 | 2024-03-13 | 21 | 2024-04-03 | 2024-03-31 | 3085091.6316 | 2307930.88 | 2307930.88 | 4953919.8807 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply3
Port Said Silos - Local Supply | 4 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 21 | 2024-04-28 | 2024-05-07 | 4365732.3333 | 3416710 | 3416710 | 9319652.214 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply4
Port Said Silos - Local Supply | 5 | 2024-04-30 | 2024-04-30 | 2024-05-12 | 21 | 2024-06-02 | 2024-05-27 | 3278709.2807 | 2565984 | 2565984 | 12598361.4947 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply5
Port Said Silos - Local Supply | 6 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 21 | 2024-06-30 | 2024-07-01 | 1064669.3947 | 833240 | 833240 | 13663030.8895 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply6
Port Said Silos - Local Supply | 7 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 21 | 2024-08-06 | 2024-08-06 | 5552464.7544 | 4345468 | 4345468 | 19215495.6439 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply7
Port Said Silos - Local Supply | 8 | 2024-07-31 | 2024-07-31 | 2024-08-18 | 21 | 2024-09-08 | 2024-09-01 | 2594878.4386 | 1794648.84 | 1794648.84 | 21810374.0825 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply8
Port Said Silos - Local Supply | 9 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 3231641.7018 | 2529147 | 2529147 | 25042015.7842 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply9
Port Said Silos - Local Supply | 10 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-10-03 | 622795.91 | 494192 | 494192 | 25664811.6942 | [8 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply10
Port Said Silos - Local Supply | 11 | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 |  |  |  | 833789.82 | [9 empty] | 0 | Port Said Port Silos | [7 empty] | Port Said Silos - Local Supply11
PSP Substation | 2 | 2018-06-30 | 2018-07-03 | 2018-07-05 | 30 | 2018-08-04 | 2018-07-22 | 1669926.8 | 1244095.47 | 1160599 | 1669926.8 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | PSP Substation2
PSP Substation | 3 | 2018-07-31 | 2018-08-05 | 2018-08-06 | 30 | 2018-09-05 | 2018-10-11 | 2696322.9906 | 1834172.07 | 1834172.07 | 4366249.7906 | [8 empty] | 0 | 0 | [7 empty] | PSP Substation3
PSP Substation | 4 | 2018-08-31 | 2018-09-10 | 2018-09-11 | 30 | 2018-10-11 |  |  |  | 1268627.7 | [9 empty] | 0 | 0 | [7 empty] | PSP Substation4
PSP Substation | 5 | 2018-09-30 | 2018-10-08 | 2018-10-08 | 30 | 2018-11-07 | 2018-10-16 | 6439927.8 | 5046458.33 | 3991290.99 | 12694557.6 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | PSP Substation5
PSP Substation | 6 | 2018-10-31 | 2018-11-10 | 2018-11-11 | 30 | 2018-12-11 | 2018-11-21 | 4012970.52 | 3047586.1 | 3047586.1 | 16707528.12 | [8 empty] | 0 | 0 | [7 empty] | PSP Substation6
PSP Substation | 7 | 2018-11-30 | 2018-12-10 | 2018-12-10 | 30 | 2019-01-09 | 2019-01-06 | 3355601.28 | 2548357.58 | 1780094.35 | 20063129.4 | [8 empty] | 0 | 0 | [7 empty] | PSP Substation7
PSP Substation | 8 | 2018-12-31 | 2019-01-12 | 2019-01-16 | 30 | 2019-02-15 | 2019-02-05 | 2786776.25 | 2116372.52 | 1829713.21 | 22849905.65 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | PSP Substation8
PSP Substation | 9 | 2019-01-31 | 2019-02-10 | 2019-02-23 | 30 | 2019-03-25 | 2019-04-11 | 2055054.9 | 1560678.78 | 1314287.28 | 24904960.55 | [8 empty] | 0 | 0 | [7 empty] | PSP Substation9
PSP Substation | 10 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-23 | 4978707.75 | 3808343.08 | 3264225.8 | 29883668.3 | [8 empty] | 0 | 0 | [7 empty] | PSP Substation10
PSP Substation | 11 | 2019-06-30 | 2019-06-25 | 2019-12-22 | 30 | 2020-01-21 |  |  |  | 2606365.14 | [9 empty] | 0 | 0 | [7 empty] | PSP Substation11
PSP Substation | 12 | 2019-06-30 | 2019-06-25 | 2020-12-06 | 30 | 2021-01-05 | 2020-12-09 | 54510.7209 | 28515 | 28515 | 32341773.9509 | [8 empty] | 0 | 0 | [7 empty] | PSP Substation12
Rabigh Ext. - Piles | 1 | 2024-02-29 | 2024-02-29 | 2024-03-05 | 57 | 2024-05-01 | 2024-03-18 | 1098993.1 | 947881.6 | 947881.6 | 1098993.1 | [6 empty] | 54949.66 |  | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles1
Rabigh Ext. - Piles | 2 | 2024-04-30 | 2024-04-24 | 2024-04-24 | 57 | 2024-06-20 | 2024-05-02 | 1361202.3 | 1174036.98 | 1174037 | 2460195.4 | [6 empty] | 123009.77 |  | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles2
Rabigh Ext. - Piles | 3 | 2024-04-30 | 2024-05-14 | 2024-05-14 | 57 | 2024-07-10 |  |  |  | 966227 | [9 empty] | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles3
Rabigh Ext. - Piles | 4 | 2024-05-31 | 2024-06-01 | 2024-06-10 | 57 | 2024-08-06 | 2024-07-08 | 2071949.5 | 1787056.4438 | 1787056 | 5652409 | [6 empty] | 282620.45 |  | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles4
Rabigh Ext. - Piles | 5 | 2024-06-30 | 2024-06-30 | 2024-07-10 | 57 | 2024-09-05 |  |  |  | 1130623 | [9 empty] | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles5
Rabigh Ext. - Piles | 6 | 2024-07-31 | 2024-07-31 | 2024-08-14 | 57 | 2024-10-10 |  |  |  | 2013847.54 | [9 empty] | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles6
Rabigh Ext. - Piles | 7 | 2024-08-31 | 2024-08-31 | 2024-09-07 | 57 | 2024-11-03 |  |  |  | 0 | [9 empty] | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles7
Rabigh Ext. - Piles | 8 | 2024-09-30 | 2024-09-30 | 2024-10-19 | 57 | 2024-12-15 |  |  |  | 0 | [9 empty] | 0 | Rabigh PP - Piling Works | [7 empty] | Rabigh Ext. - Piles8
Rabigh Ext. -Building | 1 | 2024-06-30 | 2024-06-30 | 2024-07-09 | 75 | 2024-09-22 | 2024-07-10 | 2561755.35 | 2283164.46 | 2660254.84 | 2561755.35 | [6 empty] | 128087.77 |  | 0 | Rabigh CCPP-Civil | [7 empty] | Rabigh Ext. -Building1
Rabigh Ext. -Building | 2 | 2024-07-31 | 2024-07-31 | 2024-08-05 | 75 | 2024-10-19 | 2024-08-25 | 5727560.34 | 4957387.2204 | 4708047.77 | 8289315.69 | [6 empty] | 414465.7845 |  | 0 | Rabigh CCPP-Civil | [7 empty] | Rabigh Ext. -Building2
Rabigh Ext. -Building | 3 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 75 | 2024-11-19 | 2024-09-19 | 5121658.33 | 4088042.3344 | 0 | 13410974.02 | [6 empty] | 670548.701 |  | 0 | Rabigh CCPP-Civil | [7 empty] | Rabigh Ext. -Building3
Rabigh Ext. -Building | 4 | 2024-09-30 | 2024-09-30 | 2024-10-06 | 75 | 2024-12-20 | 2024-10-23 | 6246650.22 | 4796196.0024 | 0 | 19657624.24 | [6 empty] | 982881.212 |  | 0 | Rabigh CCPP-Civil | [7 empty] | Rabigh Ext. -Building4
Rabigh Ext. -Building | 5 | 2024-10-31 | 2024-10-31 | 2024-11-03 | 75 | 2025-01-17 |  |  |  | 0 | [9 empty] | 0 | Rabigh CCPP-Civil | [7 empty] | Rabigh Ext. -Building5
Radamis-Concrete | 1 | 2022-04-30 | 2022-04-25 | 2022-04-25 | 30 | 2022-05-25 |  |  |  | 10000000 |  | 10000000 | [7 empty] | 0 | 0 | [7 empty] | Radamis-Concrete1
Radamis-Concrete | 2 | 2022-05-31 | 2022-05-25 | 2022-05-26 | 30 | 2022-06-25 |  |  |  | 10000000 |  | 10000000 | [7 empty] | 0 | 0 | [7 empty] | Radamis-Concrete2
Radamis-Concrete | 3 | 2022-06-30 | 2022-07-07 | 2022-07-03 | 30 | 2022-08-02 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete3
Radamis-Concrete | 4 | 2022-07-31 | 2022-07-31 | 2022-08-14 | 30 | 2022-09-13 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete4
Radamis-Concrete | 5 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete5
Radamis-Concrete | 6 | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete6
Radamis-Concrete | 7 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete7
Radamis-Concrete | 8 | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete8
Radamis-Concrete | 9 | 2023-01-31 | 2023-01-25 | 2023-01-30 | 30 | 2023-03-01 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete9
Radamis-Concrete | 10 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete10
Radamis-Concrete | 11 | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete11
Radamis-Concrete | 12 | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete12
Radamis-Concrete | 13 | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete13
Radamis-Concrete | 14 | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete14
Radamis-Concrete | 15 | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete15
Radamis-Concrete | 16 | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete16
Radamis-Concrete | 17 | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete17
Radamis-Concrete | 18 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete18
Radamis-Concrete | 19 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete19
Radamis-Concrete | 20 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete20
Radamis-Concrete | 21 | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete21
Radamis-Concrete | 22 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete22
Radamis-Concrete | 23 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete23
Radamis-Concrete | 24 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete24
Radamis-Concrete | 25 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete25
Radamis-Concrete | 26 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete26
Radamis-Concrete | 27 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete27
Radamis-Concrete | 28 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete28
Radamis-Concrete | 29 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete29
Radamis-Concrete | 30 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Concrete30
Radamis-H1 Main Builidng | 1 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng1
Radamis-H1 Main Builidng | 2 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng2
Radamis-H1 Main Builidng | 3 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng3
Radamis-H1 Main Builidng | 4 | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng4
Radamis-H1 Main Builidng | 5 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng5
Radamis-H1 Main Builidng | 6 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng6
Radamis-H1 Main Builidng | 7 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng7
Radamis-H1 Main Builidng | 8 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng8
Radamis-H1 Main Builidng | 9 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng9
Radamis-H1 Main Builidng | 10 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng10
Radamis-H1 Main Builidng | 11 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng11
Radamis-H1 Main Builidng | 12 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng12
Radamis-H1 Main Builidng | 13 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-H1 Main Builidng13
Radamis-Rooms Fitout | 1 | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 |  |  |  | 250000 |  | 250000 | [7 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout1
Radamis-Rooms Fitout | 2 | 2023-07-31 | 2023-07-20 | 2023-08-05 | 30 | 2023-09-04 |  |  |  | 500000 |  | 500000 | [7 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout2
Radamis-Rooms Fitout | 3 | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 |  |  |  | 15000000 |  | 15000000 | [7 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout3
Radamis-Rooms Fitout | 4 | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 |  |  |  | 4000000 |  | 4000000 | [7 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout4
Radamis-Rooms Fitout | 5 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout5
Radamis-Rooms Fitout | 6 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout6
Radamis-Rooms Fitout | 7 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout7
Radamis-Rooms Fitout | 8 | 2024-01-31 | 2024-01-25 | 2024-02-07 | 30 | 2024-03-08 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout8
Radamis-Rooms Fitout | 9 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout9
Radamis-Rooms Fitout | 10 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout10
Radamis-Rooms Fitout | 11 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout11
Radamis-Rooms Fitout | 12 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout12
Radamis-Rooms Fitout | 13 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout13
Radamis-Rooms Fitout | 14 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout14
Radamis-Rooms Fitout | 15 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout15
Radamis-Rooms Fitout | 16 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout16
Radamis-Rooms Fitout | 17 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Rooms Fitout17
Radamis-Villas Finishes | 1 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes1
Radamis-Villas Finishes | 2 | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes2
Radamis-Villas Finishes | 3 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes3
Radamis-Villas Finishes | 4 | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes4
Radamis-Villas Finishes | 5 | 2023-01-31 | 2023-01-30 | 2023-01-30 | 30 | 2023-03-01 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes5
Radamis-Villas Finishes | 6 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes6
Radamis-Villas Finishes | 7 | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes7
Radamis-Villas Finishes | 8 | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes8
Radamis-Villas Finishes | 9 | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes9
Radamis-Villas Finishes | 10 | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes10
Radamis-Villas Finishes | 11 | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes11
Radamis-Villas Finishes | 12 | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes12
Radamis-Villas Finishes | 13 | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes13
Radamis-Villas Finishes | 14 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes14
Radamis-Villas Finishes | 15 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes15
Radamis-Villas Finishes | 16 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes16
Radamis-Villas Finishes | 17 | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes17
Radamis-Villas Finishes | 18 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes18
Radamis-Villas Finishes | 19 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes19
Radamis-Villas Finishes | 20 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes20
Radamis-Villas Finishes | 21 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes21
Radamis-Villas Finishes | 22 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes22
Radamis-Villas Finishes | 23 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes23
Radamis-Villas Finishes | 24 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes24
Radamis-Villas Finishes | 25 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes25
Radamis-Villas Finishes | 26 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Radamis-Villas Finishes26
Red Sea Museum | 1 | 2024-04-30 | 2024-04-30 | 2024-05-23 | 70 | 2024-08-01 | 2024-05-23 | 3172518.7149 | 3648396.5221 | 5218717 | 3172518.7149 | [8 empty] | 0 | Red Sea Museum-Bab El-Bunt | [7 empty] | Red Sea Museum1
Red Sea Museum | 2 | 2024-05-31 | 2024-05-31 | 2024-05-23 | 70 | 2024-08-01 | 2024-08-21 | 2298644.2851 | 2114752.93 | 4414752.93 | 5471163 | [6 empty] | 114932 | 114932 | 0 | Red Sea Museum-Bab El-Bunt | [7 empty] | Red Sea Museum2
Red Sea Museum | 3 | 2024-08-31 | 2024-09-02 | 2024-09-02 | 70 | 2024-11-11 | 2024-09-02 | 1331566 | 1225041 | 4443406 | 6802729 | [8 empty] | 0 | Red Sea Museum-Bab El-Bunt | [7 empty] | Red Sea Museum3
Ring Road - El Marg | 1 | 2021-02-28 | 2021-02-20 | 2021-02-20 | 60 | 2021-04-21 |  |  |  | 45719198.4 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg1
Ring Road - El Marg | 2 | 2021-03-31 | 2021-04-15 | 2021-04-15 | 60 | 2021-06-14 |  |  |  | 9576635.3 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg2
Ring Road - El Marg | 3 | 2021-04-30 | 2021-05-15 | 2021-05-15 | 60 | 2021-07-14 |  |  |  | 13773926.1 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg3
Ring Road - El Marg | 4 | 2021-05-31 | 2021-06-08 | 2021-06-08 | 60 | 2021-08-07 |  |  |  | 4525661.3 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg4
Ring Road - El Marg | 5 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 |  |  |  | 2097964.3 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg5
Ring Road - El Marg | 6 | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 |  |  |  | 1156719 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg6
Ring Road - El Marg | 7 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 |  |  | 25237352 | 2151897.3 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg7
Ring Road - El Marg | 8 | 2021-09-30 | 2021-09-30 | 2021-10-05 | 60 | 2021-12-04 | 2021-10-24 | 4446069.4 | 3601316.214 | 3742254.85 | 142263915.035 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg8
Ring Road - El Marg | 9 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 60 | 2022-01-05 | 2021-11-24 | 4763028.235 | 3858052.8704 | 4020500.85 | 147026943.27 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg9
Ring Road - El Marg | 10 | 2021-11-30 | 2021-11-30 | 2021-12-08 | 60 | 2022-02-06 | 2022-01-25 | 3312818.46 | 2683382.9526 | 2795847.4 | 150339761.73 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg10
Ring Road - El Marg | 11 | 2022-01-31 | 2022-01-31 | 2022-02-02 | 60 | 2022-04-03 |  |  |  | 0.0001 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg11
Ring Road - El Marg | 12 | 2022-02-28 | 2022-02-28 | 2022-03-02 | 60 | 2022-05-01 |  |  |  | 0.0001 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg12
Ring Road - El Marg | 13 | 2022-05-31 | 2022-05-30 | 2022-06-02 | 60 | 2022-08-01 |  |  |  | 0.0001 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - El Marg13
Ring Road - Mounib | 1 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 60 | 2020-10-30 |  |  |  | 26333646.7391 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib1
Ring Road - Mounib | 2 | 2020-10-31 | 2020-10-31 | 2020-10-31 | 60 | 2020-12-30 |  |  |  | 7157243.6 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib2
Ring Road - Mounib | 3 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 60 | 2021-03-01 |  |  |  | 10759736.15 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib3
Ring Road - Mounib | 4 | 2021-01-31 | 2021-01-31 | 2021-02-08 | 60 | 2021-04-09 |  |  |  | 4521989.75 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib4
Ring Road - Mounib | 5 | 2021-02-28 | 2021-02-28 | 2021-03-17 | 60 | 2021-05-16 |  |  |  | 6026340.35 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib5
Ring Road - Mounib | 6 | 2021-03-31 | 2021-03-31 | 2021-04-15 | 60 | 2021-06-14 |  |  |  | 4751540.0144 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib6
Ring Road - Mounib | 7 | 2021-04-30 | 2021-04-30 | 2021-05-15 | 60 | 2021-07-14 |  |  |  | 3640291.7356 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib7
Ring Road - Mounib | 8 | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 |  |  |  | 2701161.75 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib8
Ring Road - Mounib | 9 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 |  | 4536613.5882 | 3856121.55 | 3856121.55 | 98438363.943 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib9
Ring Road - Mounib | 10 | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 |  | 18316815 | 12662306 | 10942755.35 | 116755178.943 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib10
Ring Road - Mounib | 11 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | 2021-09-07 | 30549611.057 | 19857247.187 | 3708396 | 147304790 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib11
Ring Road - Mounib | 12 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-10-16 | 20117126 | 14886673.24 | 14886673.24 | 167421916 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib12
Ring Road - Mounib | 13 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 60 | 2022-01-07 | 2021-11-13 | 56505929 | 41814387.46 | 32998633.21 | 223927845 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib13
Ring Road - Mounib | 14 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 60 | 2022-02-07 | 2022-12-29 | 46948185.4 | 0 | 14957307.9 | 270876030.4 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib14
Ring Road - Mounib | 15 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-01-20 | 30552404.425 | 0 | 10950094.1 | 301428434.825 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib15
Ring Road - Mounib | 16 | 2022-06-30 | 2022-07-10 | 2022-07-27 | 60 | 2022-09-25 | 2022-07-27 | 161507041.625 | 0 | 131490711.85 | 462935476.45 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib16
Ring Road - Mounib | 17 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 60 | 2022-10-09 | 2022-08-10 | 6933306.55 | 5130646.847 | 1170803.2 | 469868783 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib17
Ring Road - Mounib | 18 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 | 2022-09-12 | 4715315.145 | 3489333.2073 | 2897048.5 | 474584098.145 | [8 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib18
Ring Road - Mounib | 19 | 2022-09-30 | 2022-09-30 | 2022-10-17 | 60 | 2022-12-16 |  |  |  | 1351162.1 | [9 empty] | 0 | RING ROAD MARYOTIA EXPANSION | [7 empty] | Ring Road - Mounib19
RO Apply -Mech- SSC | 1 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 2250265.4 | 1730229.07 | 1730229.07 | 2250265.4 | [8 empty] | 0 | 0 | [7 empty] | RO Apply -Mech- SSC1
RO Apply -Mech- SSC | 2 | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 |  |  |  | 1e-05 | [9 empty] | 0 | 0 | [7 empty] | RO Apply -Mech- SSC2
RO Apply -Mech- SSC | 4 | 2023-11-30 | 2023-11-12 | 2023-11-12 | 15 | 2023-11-27 | 2023-12-25 | 4449602.38 | 1195633.38 | 0.001 | 8242992.05 | [8 empty] | 0 | 0 | [7 empty] | RO Apply -Mech- SSC4
RO Eriction | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 6000000 | 6660000 | 0 | 6000000 | [8 empty] | 0 | 0 | [7 empty] | RO Eriction1
RO Pump Room | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 22392582.54 | 2216012.07 | 0 | 22392582.54 | [8 empty] | 0 | 0 | [7 empty] | RO Pump Room1
RO - Supply - Electric | 1 | 2023-01-31 | 2023-01-16 | 2023-01-17 | 15 | 2023-02-01 | 2023-01-17 | 5322406.46 | 745136.9 | 1e-05 | 5322406.46 | [8 empty] | 0 | 0 | [7 empty] | RO - Supply - Electric1
RO - Supply - Electric | 2 | 2023-02-28 | 2023-02-16 | 2023-03-08 | 15 | 2023-03-23 | 2023-03-15 | 3040804.44 | 1847082.53 | 1e-05 | 8363210.9 | [8 empty] | 0 | 0 | [7 empty] | RO - Supply - Electric2
RO - Supply - Electric | 3 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 15 | 2023-04-25 | 2023-04-10 | 11778923.84 | 1649065.6 | 2225665.9095 | 20142134.74 | [8 empty] | 0 | 0 | [7 empty] | RO - Supply - Electric3
RO Supply -Mech- SSC | 1 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-07 | 16503981 | 13698304.23 | 13698304.23 | 16503981 | [8 empty] | 0 | 0 | [7 empty] | RO Supply -Mech- SSC1
RO Supply -Mech- SSC | 2 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-14 | 1896616.8 | 1574191.94 | 1574191.94 | 18400597.8 | [8 empty] | 0 | 0 | [7 empty] | RO Supply -Mech- SSC2
RO Supply -Mech- SSC | 3 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 28179089.25 | 8116147.9 | 8116147.9035 | 28179089.25 | [8 empty] | 0 | 0 | [7 empty] | RO Supply -Mech- SSC3
RO Supply -Mech- SSC | 4 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 15 | 2023-05-16 | 2023-05-08 | 7605000 | 6312150 | 6312150 | 35784089.25 | [8 empty] | 0 | 0 | [7 empty] | RO Supply -Mech- SSC4
RO Supply -Mech- SSC | 5 | 2023-07-31 | 2023-07-31 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-26 | 4510403.17 | 3743634.63 | 2149698.33 | 40294492.42 | [8 empty] | 0 | 0 | [7 empty] | RO Supply -Mech- SSC5
RO Supply -Mech- SSC | 8 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 15 | 2024-03-11 | 2024-02-27 | 14223589.16 | 1418035.09 | 0 | 54518081.58 | [8 empty] | 0 | 0 | [7 empty] | RO Supply -Mech- SSC8
RO 2 | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 35549128.54 | 28083811.55 | 0 | 35549128.54 | [8 empty] | 0 | 0 | [7 empty] | RO 21
RO 2 | 2 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 15 | 2024-05-16 | 2024-05-02 | 1807831.26 | 1880144.51 | 0 | 37356959.8 | [8 empty] | 0 | 0 | [7 empty] | RO 22
RO 2 | 3 | 2024-06-30 | 2024-06-30 | 2024-07-01 | 15 | 2024-07-16 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | RO 23
RO Pump room - SSC - price diff. | 1 | 2023-02-28 | 2023-03-08 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-13 | 14675847.72 | 16583707.92 | 15849915.53 | 14675847.72 | [8 empty] | 0 | 0 | [7 empty] | RO Pump room - SSC - price diff.1
RO Pump room - SSC - price diff. | 2 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-15 | 1686530.02 | 1905778.92 | 918959 | 16362377.74 | [8 empty] | 0 | 0 | [7 empty] | RO Pump room - SSC - price diff.2
RO Pump room - SSC - price diff. | 3 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 8704005.47 | 9835526.19 | 9400325.92 | 25066383.21 | [8 empty] | 0 | 0 | [7 empty] | RO Pump room - SSC - price diff.3
RO Pump room - SSC - price diff. | 4 | 2023-04-30 | 2023-05-01 | 2023-05-09 | 15 | 2023-05-24 | 2023-05-09 | 6762600 | 7303608 | 7294244.17 | 31828983.21 | [8 empty] | 0 | 0 | [7 empty] | RO Pump room - SSC - price diff.4
RO.2 | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 15 | 2023-07-15 |  |  |  | 1e-05 | [9 empty] | 0 | 0 | [7 empty] | RO.21
Rolling Mill #4-TRAESUEZ | 1 | 2021-12-31 | 2022-01-10 | 2022-01-11 | 42 | 2022-02-22 | 2022-02-28 | 21476647.48 | 17181317.99 | 125716551.51 | 21476647.48 | [8 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ1
Rolling Mill #4-TRAESUEZ | 2 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-22 | 13583921.53 | 11564103.96 | 12106800.04 | 35060569.01 | [8 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ2
Rolling Mill #4-TRAESUEZ | 3 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-20 | 12117327 | 10352618.57 | 10231445.3 | 47177896.01 | [8 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ3
Rolling Mill #4-TRAESUEZ | 4 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-17 | 8075015.79 | 6677291.55 | 6596541.38 | 55252911.8 | [8 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ4
Rolling Mill #4-TRAESUEZ | 5 | 2022-05-31 | 2022-06-05 | 2022-06-07 | 42 | 2022-07-19 | 2022-07-06 | 9905844.43 | 8140659.04 | 9293714.72 | 65158756.23 |  |  | 7155944.45 | [5 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ5
Rolling Mill #4-TRAESUEZ | 6 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-07 | 5743581.36 | 4679965.02 | 4622509.21 | 70902337.59 |  |  |  | 7496344.15 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ6
Rolling Mill #4-TRAESUEZ | 7 | 2022-07-31 | 2022-08-05 | 2022-08-06 | 42 | 2022-09-17 | 2022-08-24 | 16796950.93 | 13457708.47 | 13289718.96 | 87699288.52 |  |  |  | 7576935.06 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ7
Rolling Mill #4-TRAESUEZ | 8 | 2022-08-31 | 2022-09-10 | 2022-09-12 | 42 | 2022-10-24 | 2022-09-27 | 18519200.97 | 14944026.92 | 16970562.32 | 106218489.49 |  |  |  | 8091599.65 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ8
Rolling Mill #4-TRAESUEZ | 9 | 2022-09-30 | 2022-10-10 | 2022-10-12 | 42 | 2022-11-23 | 2022-11-07 | 17686791.21 | 14162374.17 | 15728855.47 | 123905280.7 |  |  |  | 8143364.44 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ9
Rolling Mill #4-TRAESUEZ | 10 | 2022-10-31 | 2022-11-07 | 2022-11-08 | 42 | 2022-12-20 | 2022-12-14 | 15395023.2 | 12338644.38 | 10380808.5 | 139300303.9 |  |  |  | 8233867.7 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ10
Rolling Mill #4-TRAESUEZ | 11 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2023-01-17 | 16145745 | 13316234.88 | 9072857.69 | 155446048.9 |  |  |  | 9832423.2 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ11
Rolling Mill #4-TRAESUEZ | 12 | 2022-12-31 | 2023-01-15 | 2023-01-18 | 42 | 2023-03-01 | 2023-02-07 | 16694409.39 | 13380155.34 | 13213191.25 | 172140458.29 |  |  |  | 9930934.56 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ12
Rolling Mill #4-TRAESUEZ | 13 | 2023-01-31 | 2023-02-15 | 2023-02-16 | 42 | 2023-03-30 | 2023-03-08 | 14485776.58 | 11700102.46 | 1e-05 | 186626234.87 |  |  |  | 10376859 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ13
Rolling Mill #4-TRAESUEZ | 14 | 2023-02-28 | 2023-03-10 | 2023-03-20 | 42 | 2023-05-01 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ14
Rolling Mill #4-TRAESUEZ | 15 | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ15
Rolling Mill #4-TRAESUEZ | 16 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 |  |  |  | 1e-05 | [9 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ16
Rolling Mill #4-TRAESUEZ | 17 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 619836241 | 385850750.2 | 0 | 619836241 | [8 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ17
Rolling Mill #4-TRAESUEZ | 18 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 16836028.82 | 17509470.02 | 0 | 636672269.82 |  |  |  | 105081618.32 |  |  |  |  | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ18
Rolling Mill #4-TRAESUEZ | 19 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 |  |  |  | 0 | [9 empty] | 0 | EGAT New Rolling Mill 4 | [7 empty] | Rolling Mill #4-TRAESUEZ19
Royal City | 2 | 2017-09-30 | 2017-09-30 | 2017-10-01 | 34 | 2017-11-04 | 2017-10-11 | 8875548.87 | 5235331.6 | 4892835.45 | 8875548.87 |  |  | 3953206.73 | [5 empty] | 34013.75 | Royal City | [7 empty] | Royal City2
Royal City | 3 | 2017-10-31 | 2017-10-31 | 2017-11-04 | 34 | 2017-12-08 | 2017-11-14 | 8111601.4206 | 7926742.1 | 7926742.1 | 16987150.2906 |  |  | 5848040.712 | [5 empty] | 103062.25 | Royal City | [7 empty] | Royal City3
Royal City | 4 | 2017-11-30 | 2017-12-03 | 2017-12-03 | 34 | 2018-01-06 | 2017-12-24 | 10259671.7094 | 10437271.65 | 10437271.65 | 27246822 |  |  | 8775298.38 | [5 empty] | 103062.25 | Royal City | [7 empty] | Royal City4
Royal City | 5 | 2017-12-31 | 2017-12-30 | 2018-01-03 | 34 | 2018-02-06 | 2018-01-22 | 11565536.4187 | 6381832.9445 | 5169557.65 | 38812358.4187 |  |  | 5702856.6 | [5 empty] | 166539 | Royal City | [7 empty] | Royal City5
Royal City | 6 | 2018-03-31 | 2018-03-31 | 2018-02-20 | 34 | 2018-03-26 | 2018-05-21 | 15834199.4413 | 12495801.39 | 12495801.4 | 54646557.86 |  |  | 3811475.98 | [5 empty] | 348145 | Royal City | [7 empty] | Royal City6
Royal City | 7 | 2018-04-30 | 2018-04-30 | 2018-05-07 | 34 | 2018-06-10 | 2018-06-11 | 11881365.61 | 8703262.41 | 8703262.4 | 66527923.47 |  |  | 3172251.35 | [5 empty] | 582017.44 | Royal City | [7 empty] | Royal City7
Royal City | 8 | 2018-05-31 | 2018-05-31 | 2018-06-05 | 34 | 2018-07-09 | 2018-06-24 | 7845708.0075 | 7600061.0338 | 6085844.5 | 74373631.4775 |  |  | 5502031.137 | [5 empty] | 2646288.4432 | Royal City | [7 empty] | Royal City8
Royal City | 9 | 2018-06-30 | 2018-06-30 | 2018-07-10 | 34 | 2018-08-13 | 2018-07-26 | 7890492.132 | 6018082.2865 | 6397146.2 | 82264123.6095 |  |  | 5685747.237 | [5 empty] | 3049998.998 | Royal City | [7 empty] | Royal City9
Royal City | 10 | 2018-07-31 | 2018-07-31 | 2018-08-08 | 34 | 2018-09-11 | 2018-08-27 | 8199169.349 | 5554331.9836 | 5786688.5 | 90463292.9586 |  |  | 4944412.0842 | [5 empty] | 3422890.7078 | Royal City | [7 empty] | Royal City10
Royal City | 11 | 2018-08-31 | 2018-08-31 | 2018-09-12 | 34 | 2018-10-16 | 2018-09-24 | 2707034.9014 | 3237608.64 | 61982306.95 | 93170327.86 |  |  | 6546266.4 | [5 empty] | 3614328.412 | Royal City | [7 empty] | Royal City11
Royal City | 12 | 2018-09-30 | 2018-09-30 | 2018-10-09 | 34 | 2018-11-12 | 2018-11-07 | 12651464.27 | 8503935.74 | 9822648.05 | 105821792.13 |  |  | 8045747.81 | [5 empty] | 669617.5401 | Royal City | [7 empty] | Royal City12
Royal City | 13 | 2018-10-31 | 2018-10-31 | 2018-11-07 | 34 | 2018-12-11 | 2018-12-04 | 11315357.62 | 6339338.47 | 6339338.45 | 117137149.75 |  |  | 6383924.621 | [5 empty] | 0 | Royal City | [7 empty] | Royal City13
Royal City | 14 | 2018-11-30 | 2018-11-30 | 2018-12-06 | 34 | 2019-01-09 | 2018-12-29 | 3293171.7405 | 13062023.4527 | 5980045.3 | 120430321.4905 |  |  | 8435330.6159 | [5 empty] | 558453.95 | Royal City | [7 empty] | Royal City14
Royal City | 15 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 34 | 2019-02-09 | 2019-01-20 | 16384822.4548 | 9343372.736 | 6570751.8 | 136815143.9453 |  |  | 9384080.2453 | [5 empty] | 653055.6603 | Royal City | [7 empty] | Royal City15
Royal City | 16 | 2019-01-31 | 2019-01-31 | 2019-02-07 | 34 | 2019-03-13 | 2019-02-25 | 11488490.3339 | 10141562.9942 | 7847127.4 | 148303634.2792 |  |  | 12235459.3471 | [5 empty] | 320713.8483 | Royal City | [7 empty] | Royal City16
Royal City | 17 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 34 | 2019-04-09 | 2019-04-01 | 9063503.9339 | 6226878.8549 | 5868379.55 | 157367138.2131 |  |  | 15116649.6688 | [5 empty] | 370976.9746 | Royal City | [7 empty] | Royal City17
Royal City | 18 | 2019-03-31 | 2019-03-31 | 2019-04-09 | 34 | 2019-05-13 | 2019-04-18 | 8621924.8043 | 6196039.396 | 4501953.5 | 165989063.0174 |  |  | 14343940.1395 | [5 empty] | 296046.8071 | Royal City | [7 empty] | Royal City18
Royal City | 19 | 2019-04-30 | 2019-04-30 | 2019-05-08 | 34 | 2019-06-11 | 2019-05-23 | 15549148.0486 | 10933183.0202 | 9999974.75 | 181538211.066 |  |  | 16047073.0222 | [5 empty] | 222365.6932 | Royal City | [7 empty] | Royal City19
Royal City | 20 | 2019-05-31 | 2019-05-31 | 2019-06-01 | 34 | 2019-07-05 | 2019-06-26 | 7876990.4815 | 5643448.8191 | 5072118 | 189415201.5475 |  |  | 15380569.1286 | [5 empty] | 176894.1812 | Royal City | [7 empty] | Royal City20
Royal City | 21 | 2019-06-30 | 2019-06-30 | 2019-07-08 | 34 | 2019-08-11 | 2019-07-18 | 7532294.3265 | 5151160.3487 | 5000000 | 196947495.8739 |  |  | 17429947.3127 | [5 empty] | 252279.4582 | Royal City | [7 empty] | Royal City21
Royal City | 22 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 34 | 2019-09-08 | 2019-09-02 | 24265130.1959 | 17540056.799 | 36824453.7 | 221212626.0698 |  |  | 24953179.7402 | [5 empty] | 327502.3224 | Royal City | [7 empty] | Royal City22
Royal City | 23 | 2019-08-31 | 2019-08-31 | 2019-09-11 |  | 2019-10-18 | 2019-09-28 | 6268692.5562 | 4319851.8787 | 6453450.6 | 227481318.626 |  |  | 25361645.3681 | [5 empty] | 418117.1746 | Royal City | [7 empty] | Royal City23
Royal City | 24 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-24 | 17799666.736 | 10214838.0645 | 9088642.9 | 245280985.3621 |  |  | 23478699.1038 | [5 empty] | 383536.5601 | Royal City | [7 empty] | Royal City24
Royal City | 25 | 2019-10-31 | 2019-10-31 | 2019-11-07 | 34 | 2019-12-11 | 2019-11-27 | 17503083.0268 | 12249365.624 | 9972683.95 | 262784068.3888 |  |  | 23043660.2023 | [5 empty] | 462163.6487 | Royal City | [7 empty] | Royal City25
Royal City | 26 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 10595979.9301 | 7456675.6367 | 8025338.3 | 273380048.3189 |  |  | 22399832.276 | [5 empty] | 481328.1283 | Royal City | [7 empty] | Royal City26
Royal City | 27 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 20586377.6301 | 14587648.3106 | 11895943.7 | 293966425.9491 |  |  | 19245051.8837 | [5 empty] | 481881.6236 | Royal City | [7 empty] | Royal City27
Royal City | 28 | 2020-01-31 | 2020-01-31 | 2020-02-17 | 34 | 2020-03-22 | 2020-03-16 | 15640549.4851 | 10986396.5553 | 10500306.77 | 309606975.4342 |  |  | 16026544.9251 | [5 empty] | 606431.6143 | Royal City | [7 empty] | Royal City28
Royal City | 29 | 2020-02-29 | 2020-02-29 | 2020-03-18 | 34 | 2020-04-21 | 2020-04-05 | 18804604.7977 | 13166441.5288 | 12838209.35 | 328411580.2319 |  |  | 16972896.7219 | [5 empty] | 637326.7814 | Royal City | [7 empty] | Royal City29
Royal City | 30 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 13862319.0142 | 9831952.135 | 9831952.135 | 342273899.2462 |  |  | 14581690.3962 | [5 empty] | 637621.4818 | Royal City | [7 empty] | Royal City30
Royal City | 31 | 2020-04-30 | 2020-04-30 | 2020-05-14 | 34 | 2020-06-17 | 2020-07-02 | 10234077.8776 | 7550426.1692 | 6475508.58 | 352507977.1238 |  |  | 12931292.2437 | [5 empty] | 0 | Royal City | [7 empty] | Royal City31
Royal City | 32 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 3761397.6023 | 2648440.2256 | 2151533.38 | 356269374.7261 |  |  | 12829313.7893 | [5 empty] | 0 | Royal City | [7 empty] | Royal City32
Royal City | 33 | 2020-06-30 | 2020-06-30 | 2020-07-20 | 34 | 2020-08-23 | 2020-08-12 | 13830917.4352 | 9101413.8171 | 9101413.8171 | 370100292.1612 |  |  | 14873462.0847 | [5 empty] | 1198898.3783 | Royal City | [7 empty] | Royal City33
Royal City | 34 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-14 | 7811639.6921 | 5373442.9261 | 5373442.9261 | 377911931.8534 |  |  | 13214988.4567 | [5 empty] | 1376502.8422 | Royal City | [7 empty] | Royal City34
Royal City | 35 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 3980750.5222 | 3237336.5863 | 3237336.5863 | 381892682.3756 |  |  | 10629015.9927 | [5 empty] | 1052872.9373 | Royal City | [7 empty] | Royal City35
Royal City | 36 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 8343396.9284 | 5231425.19 | 5231425.19 | 390236079.304 |  |  | 10856647.4404 | [5 empty] | 1034872.9373 | Royal City | [7 empty] | Royal City36
Royal City | 37 | 2020-10-31 | 2020-10-31 | 2020-11-07 | 34 | 2020-12-11 | 2020-11-26 | 5412454.8663 | 5574033.5344 | 3663343.67 | 395648534.1703 |  |  | 7933674.7404 | [5 empty] | 998604.3353 | Royal City | [7 empty] | Royal City37
Royal City | 38 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 3712322.3219 | 3838809.8865 | 2267127.88 | 399360856.4923 |  |  | 6223962.4617 | [5 empty] | 944047.2982 | Royal City | [7 empty] | Royal City38
Royal City | 39 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 1174176.5076 | 1002773.1926 | 1002773.1926 | 400535032.9999 |  |  | 6288699.0447 | [5 empty] | 899047.2982 | Royal City | [7 empty] | Royal City39
Royal City | 40 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 5847326.4556 | 5979686.6716 | 5979686.67 | 406382359.4555 |  |  | 4784431.8697 | [5 empty] | 823521.4569 | Royal City | [7 empty] | Royal City40
Royal City | 41 | 2021-08-31 | 2021-09-01 | 2021-09-19 | 34 | 2021-10-23 | 2021-11-01 | 5256684.0377 | 5714023.3138 | 5714023.3138 | 411639043.4932 |  |  | 3493730 | [5 empty] | 414348.8107 | Royal City | [7 empty] | Royal City41
Royal City | 42 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 7571387.8468 | 29397549.59 | 35161782.8 | 419210431.34 |  |  | 715168.5 | 18621503.12 |  | 45928934.7 |  |  | 225000 | Royal City | [7 empty] | Royal City42
Royal City | 43 | 2023-07-31 | 2023-08-08 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 13484961.26 | 13488633.46 | 0 | 432695392.6 |  |  |  | 18307280.08 |  | 46946119.05 |  |  | 225000 | Royal City | [7 empty] | Royal City43
Royal City - Landscape | 1 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 34 | 2019-09-09 |  |  | 1800000 | 1782000 | [9 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape1
Royal City - Landscape | 2 | 2019-08-31 | 2019-08-31 | 2019-09-11 | 34 | 2019-10-15 | 2019-09-25 |  | 4032037.5 | 4014037.5 |  |  |  | 2976050 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape2
Royal City - Landscape | 3 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-23 | 341000 | 2443214.8875 | 2421804.9 | 341000 |  |  | 3475619.85 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape3
Royal City - Landscape | 4 | 2019-10-31 | 2019-10-30 | 2019-11-07 | 34 | 2019-12-11 | 2019-12-25 | 2839877.7881 | 4441415.442 | 4390934.75 | 3180877.7881 |  |  | 4015635.4285 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape4
Royal City - Landscape | 5 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 5896802.2265 | 7147476.0332 | 7060326.8 | 9077680.0146 |  |  | 4953961.135 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape5
Royal City - Landscape | 6 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 12932194.6154 | 9619287.67 | 9240902.25 | 22009874.63 |  |  | 4200873.67 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape6
Royal City - Landscape | 7 | 2020-01-31 | 2020-01-31 | 2020-02-11 | 34 | 2020-03-16 | 2020-03-16 | 6479189.8549 | 6246175.7955 | 6442723.35 | 28489064.4849 |  |  | 5725958.7255 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape7
Royal City - Landscape | 8 | 2020-02-29 | 2020-02-29 | 2020-03-17 | 34 | 2020-04-20 | 2020-04-05 | 17137734.2822 | 12899186.0747 | 12356243.75 | 45626798.7671 |  |  | 4930252.4954 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape8
Royal City - Landscape | 9 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 6296234.5253 | 4988413.7416 | 4886117.91 | 51923033.2924 |  |  | 4970424.566 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape9
Royal City - Landscape | 10 | 2020-04-30 | 2020-04-30 | 2020-05-18 | 34 | 2020-06-21 | 2020-07-02 | 3937848.897 | 3101056.0064 | 3061010.97 | 55860882.1894 |  |  | 4970424.566 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape10
Royal City - Landscape | 11 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 5192701.4937 | 3973857.736 | 4947910.42 | 61053583.6831 |  |  | 4816564.979 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape11
Royal City - Landscape | 12 | 2020-06-30 | 2020-06-30 | 2020-07-19 | 34 | 2020-08-22 | 2020-08-12 | 8940402.3014 | 7029456.4155 | 7029456.4155 | 69993985.9845 |  |  | 6160052.1105 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape12
Royal City - Landscape | 13 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-07 | 3598777.1179 | 2173267.6157 | 2173267.6157 | 73592763.1024 |  |  | 4428817.741 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape13
Royal City - Landscape | 14 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 2137131.084 | 1308214.7555 | 1308214.7555 | 75729894.1864 |  |  | 3929116.4435 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape14
Royal City - Landscape | 15 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 3135305.5981 | 2272705.37 | 2272705.37 | 78865199.7846 |  |  | 3708912.5587 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape15
Royal City - Landscape | 16 | 2020-10-31 | 2020-10-31 | 2020-11-09 | 34 | 2020-12-13 | 2020-11-26 | 1582061.2622 | 853478.48 | 650222.9433 | 80447261.0467 |  |  | 3206907.765 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape16
Royal City - Landscape | 17 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 3716309.8261 | 2058324.55 | 2820044.2305 | 84163570.8728 |  |  | 1876563.015 | [5 empty] | 45000 | Royal City | [7 empty] | Royal City - Landscape17
Royal City - Landscape | 18 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 1163660.8736 | 819297.0816 | 819297.0816 | 85327231.7464 |  |  | 1969454.449 | [5 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape18
Royal City - Landscape | 19 | 2021-01-31 | 2021-01-31 | 2021-02-09 | 34 | 2021-03-15 | 2021-03-02 | 2029657.8338 | 1116339.8935 | 1116339.8935 | 87356889.5802 |  |  | 1814848.008 | [5 empty] | 60000 | Royal City | [7 empty] | Royal City - Landscape19
Royal City - Landscape | 20 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 1366613.9629 | 1105876.6944 | 1105876.6944 | 88723503.543 |  |  | 1854405.6062 | [5 empty] | 60000 | Royal City | [7 empty] | Royal City - Landscape20
Royal City - Landscape | 21 | 2021-05-31 | 2021-05-31 | 2021-06-13 | 34 | 2021-07-17 | 2021-07-13 | 4112536.457 | 3011690.98 | 2806313.404 | 92836040 |  |  | 1631829.995 | [5 empty] | 120000 | Royal City | [7 empty] | Royal City - Landscape21
Royal City - Landscape | 22 | 2021-08-31 | 2021-09-01 | 2021-09-14 | 34 | 2021-10-18 | 2021-11-01 | 3299640.8 | 2526109.9 | 1838217.2 | 96135680.8 |  |  | 1159231.18 | [5 empty] | 165000 | Royal City | [7 empty] | Royal City - Landscape22
Royal City - Landscape | 23 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 10826725.43 | 15313915.32 | 13000000 | 106962406.23 | [8 empty] | 165000 | Royal City | [7 empty] | Royal City - Landscape23
Royal City - Landscape | 24 | 2023-06-30 | 2023-07-11 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 3256136.08 | 3247942.88 | 0 | 110218542.31 | [8 empty] | 0 | Royal City | [7 empty] | Royal City - Landscape24
Saint Gobain Factory - DP | 1 | 2024-09-30 | 2024-09-25 | 2024-09-25 | 28 | 2024-10-23 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | Saint Gobain Factory - DP1
SIEMENS - Sokhna | 1 | 2017-11-30 | 2017-11-30 | 2017-11-29 | 45 | 2018-01-13 | 2017-12-06 |  | 93300000 | 93300000 | [9 empty] | 0 | 0 | [7 empty] | SIEMENS - Sokhna1
SIEMENS - Sokhna | 2 | 2017-12-31 | 2017-12-25 | 2018-01-16 | 45 | 2018-03-02 | 2018-01-16 | 4401847.1 | 3059283.73 | 3059283.73 | 4401847.1 |  |  | 0 | [5 empty] | 0 | 0 | [7 empty] | SIEMENS - Sokhna2
SIEMENS - Sokhna | 3 | 2018-01-31 | 2018-02-03 | 2018-02-05 | 45 | 2018-03-22 | 2018-02-05 | 10401972.73 | 7201577.05 | 7201577.05 | 14803819.83 |  |  | 0 | [5 empty] | 27794 | 0 | [7 empty] | SIEMENS - Sokhna3
SIEMENS - Sokhna | 4 | 2018-02-28 | 2018-03-04 | 2018-03-05 | 45 | 2018-04-19 | 2018-03-14 | 15960664.31 | 11065687.7 | 11065687.7 | 30764484.14 |  |  | 0 | [5 empty] | 54768 | 0 | [7 empty] | SIEMENS - Sokhna4
SIEMENS - Sokhna | 5 | 2018-03-31 | 2018-04-08 | 2018-04-10 | 45 | 2018-05-25 | 2018-04-15 | 19051976.33 | 13218163.55 | 13218163.56 | 49816460.47 |  |  | 0 | [5 empty] | 77728 | 0 | [7 empty] | SIEMENS - Sokhna5
SIEMENS - Sokhna | 6 | 2018-04-30 | 2018-05-03 | 2018-05-07 | 45 | 2018-06-21 | 2018-05-20 | 10481549.5128 | 7060448.908 | 7060448.908 | 60298009.9828 |  |  | 0 | [5 empty] | 301956 | 0 | [7 empty] | SIEMENS - Sokhna6
SIEMENS - Sokhna | 7 | 2018-05-31 | 2018-06-06 | 2018-06-14 | 45 | 2018-07-29 | 2018-07-04 | 12587450.0972 | 8833159.82 | 8833159.82 | 72885460.08 |  |  | 0 | [5 empty] | 217074 | 0 | [7 empty] | SIEMENS - Sokhna7
SIEMENS - Sokhna | 8 | 2018-06-30 | 2018-07-05 | 2018-06-28 | 45 | 2018-08-12 | 2018-07-19 | 18208993.38 | 12641621.4 | 12641621.4 | 91094453.46 |  |  | 0 | [5 empty] | 230703 | 0 | [7 empty] | SIEMENS - Sokhna8
SIEMENS - Sokhna | 9 | 2018-07-31 | 2018-08-01 | 2018-08-05 | 45 | 2018-09-19 | 2018-09-03 | 19922320.61 | 13673026.82 | 13673026.82 | 111016774.07 |  |  | 0 | [5 empty] | 403689 | 0 | [7 empty] | SIEMENS - Sokhna9
SIEMENS - Sokhna | 10 | 2018-08-31 | 2018-09-06 | 2018-09-17 | 45 | 2018-11-01 | 2018-09-25 | 9128690.32 | 6271528.33 | 6271528.33 | 120145464.39 |  |  | 0 | [5 empty] | 430957 | 0 | [7 empty] | SIEMENS - Sokhna10
SIEMENS - Sokhna | 11 | 2018-09-30 | 2018-09-30 | 2018-10-01 | 45 | 2018-11-15 | 2018-11-05 | 7601906.76 | 5230123.66 | 5230123.67 | 127747371.15 |  |  | 0 | [5 empty] | 446149 | 0 | [7 empty] | SIEMENS - Sokhna11
SIEMENS - Sokhna | 12 | 2018-10-31 | 2018-10-28 | 2018-10-28 | 45 | 2018-12-12 | 2018-11-07 | 28930012.4 | 20041232.56 | 20041232.56 | 156677383.55 | [8 empty] | 366625 | 0 | [7 empty] | SIEMENS - Sokhna12
SIEMENS - Sokhna | 13 | 2018-11-30 | 2018-11-22 | 2018-11-22 | 45 | 2019-01-06 | 2018-11-27 | 25830140.07 | 17822796.65 | 17822796.65 | 182507523.62 | [8 empty] | 366625 | 0 | [7 empty] | SIEMENS - Sokhna13
SIEMENS - Sokhna | 14 | 2018-12-31 | 2018-12-09 | 2018-12-19 | 45 | 2019-02-02 | 2019-02-05 | 28983532 | 20002003.08 | 20002003.08 | 211491055.62 | [8 empty] | 363259 | 0 | [7 empty] | SIEMENS - Sokhna14
SIEMENS - Sokhna | 15 | 2018-12-31 | 2018-12-27 | 2019-01-05 | 45 | 2019-02-19 | 2019-02-05 | 10573229.89 | 2699428.63 | 2699428.63 | 222064285.51 | [8 empty] | 4959359 | 0 | [7 empty] | SIEMENS - Sokhna15
SIEMENS - Sokhna | 16 | 2018-12-31 | 2018-12-30 | 2019-01-15 | 45 | 2019-03-01 | 2019-01-23 | 32022484.92 | 25271545.73 | 25271545.73 | 254086770.43 | [8 empty] | 4959359 | 0 | [7 empty] | SIEMENS - Sokhna16
SIEMENS - Sokhna | 17 | 2019-02-28 | 2019-02-21 | 2019-01-31 | 45 | 2019-03-17 | 2019-04-22 | 57817326.87 | 20418831.59 | 20418831.59 | 311904097.3 | [8 empty] | 26029681 | 0 | [7 empty] | SIEMENS - Sokhna17
SIEMENS - Sokhna | 18 | 2019-07-31 | 2019-08-07 | 2019-08-20 | 45 | 2019-10-04 | 2019-10-02 | 11495973.02 | 12124718 | 12124718 | 323400070.32 | [8 empty] | 20785977 | 0 | [7 empty] | SIEMENS - Sokhna18
SIEMENS - Sokhna | 19 | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 |  |  |  | 25672200.91 | [9 empty] | 0 | 0 | [7 empty] | SIEMENS - Sokhna19
SIEMENS - Sokhna | 20 | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 | 2023-10-25 |  |  | 15319191.73 | [9 empty] | 0 | 0 | [7 empty] | SIEMENS - Sokhna20
SIEMENS - Sokhna | 21 | 2020-07-31 | 2020-07-15 | 2020-07-15 | 45 | 2020-08-29 |  |  |  | 888628.7 | [9 empty] | 0 | 0 | [7 empty] | SIEMENS - Sokhna21
SMP1 - Revamp | 1 | 2022-12-31 | 2023-01-02 | 2023-01-04 | 42 | 2023-02-15 | 2023-02-02 | 3199345.21 | 2399508.91 | 13906048.2 | 3199345.21 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp1
SMP1 - Revamp | 2 | 2023-01-31 | 2023-02-14 | 2023-02-15 | 42 | 2023-03-29 | 2023-05-02 | 1797569.47 | 1348177.1 | 25693427.5 | 4996914.68 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp2
SMP1 - Revamp | 3 | 2023-04-30 | 2023-05-03 | 2023-05-24 | 42 | 2023-07-05 |  | 2879525.92 | 2159644.45 | 16806572.5 | 7876440.6 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp3
SMP1 - Revamp | 4 | 2023-05-31 | 2023-06-06 | 2023-07-13 | 42 | 2023-08-24 | 2023-09-01 | 3836789.63 | 2877592.22 | 2647384.8437 | 11713230.23 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp4
SMP1 - Revamp | 5 | 2023-07-31 | 2023-07-25 | 2023-07-25 | 42 | 2023-09-05 | 2023-09-12 | 4135898.1 | 3101923.57 | 2853769.6857 | 15849128.33 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp5
SMP1 - Revamp | 6 | 2023-08-31 | 2023-08-30 | 2023-09-06 | 42 | 2023-10-18 | 2023-10-10 | 8858061.69 | 6643546.26 | 6112062.5631 | 24707190.02 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp6
SMP1 - Revamp | 7 | 2023-10-31 | 2023-10-15 | 2023-10-15 | 42 | 2023-11-26 | 2023-11-21 | 4571797.25 | 3428847.94 | 3154540.1 | 29278987.27 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp7
SMP1 - Revamp | 8 | 2023-12-31 | 2023-12-06 | 2023-12-06 | 42 | 2024-01-17 | 2024-01-15 | 2887080.34 | 2165310.25 | 1992085.4366 | 32166067.61 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp8
SMP1 - Revamp | 9 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-28 | 1572976.38 | 1179732.3 | 0 | 33739043.99 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp9
SMP1 - Revamp | 10 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-06-04 | 5011477.79 | 3758608.34 | 0 | 38750521.78 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Revamp10
SMP1 - Shut Down | 1 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2023-10-18 | 15192302.49 | 8203843.34 | 5388381.94 | 15192302.49 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Shut Down1
SMP1 - Shut Down | 2 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2024-04-07 | 17650842.77 | 9531455.1 | 15140879.8914 | 32843145.26 | [8 empty] | 0 | 0 | [7 empty] | SMP1 - Shut Down2
SMP1 - Shut Down | 3 | 2024-05-31 | 2024-05-25 | 2024-04-24 | 42 | 2024-06-05 |  |  |  | 8648912.9484 | [9 empty] | 0 | 0 | [7 empty] | SMP1 - Shut Down3
SMP2 - Shut Down | 2 | 2023-12-31 | 2023-12-09 | 2023-12-09 | 42 | 2024-01-20 | 2024-01-07 | 17053490.95 | 5979888.32 | 5426194.9513 | 49896636.21 | [8 empty] | 0 | 0 | [7 empty] | SMP2 - Shut Down2
SMP2 - Shut Down | 3 | 2024-02-29 | 2024-02-27 | 2024-02-27 | 42 | 2024-04-09 | 2024-04-07 | 1490218.79 | 804718.15 | 581185.34 | 51386855 | [8 empty] | 0 | 0 | [7 empty] | SMP2 - Shut Down3
Sodic Club House | 23 | 2017-09-30 | 2017-09-19 | 2017-11-01 | 35 | 2017-12-06 | 2017-11-05 | 10526350.27 | 2727407.23 | 2727407.25 | 55308912.13 |  |  | 10641245.16 | [5 empty] | 83598.95 | Sodic Club House | [7 empty] | Sodic Club House23
Sodic Club House | 24 | 2017-10-31 | 2017-11-01 | 2017-11-03 | 35 | 2017-12-08 | 2017-12-17 | 6326663.77 | 4528572.66 | 4528572.66 | 61635575.9 |  |  | 10347994.62 | [5 empty] | 33598.95 | Sodic Club House | [7 empty] | Sodic Club House24
Sodic Club House | 25 | 2017-11-30 | 2017-12-01 | 2017-12-10 | 35 | 2018-01-14 | 2018-01-24 | 3617825.39 | 894280.74 | 894280.83 | 65253401.29 |  |  | 8215432.94 | [5 empty] | 33598.95 | Sodic Club House | [7 empty] | Sodic Club House25
Sodic Club House | 26 | 2017-12-31 | 2018-01-16 | 2018-01-16 | 35 | 2018-02-20 | 2018-02-22 | 4263027.4013 | 2563543.8087 | 2563543.65 | 69516428.6913 |  |  | 7922726.9562 | [5 empty] | 33598.95 | Sodic Club House | [7 empty] | Sodic Club House26
Sodic Club House | 27 | 2018-02-28 | 2018-02-20 | 2018-03-01 | 35 | 2018-04-05 | 2018-04-01 | 6447136.9087 | 7171420.74 | 7171420.81 | 86100596.85 |  |  | 8271503.62 | [5 empty] | 133598.95 | Sodic Club House | [7 empty] | Sodic Club House27
Sodic Club House | 28 | 2018-03-31 | 2018-03-20 | 2018-03-20 | 35 | 2018-04-24 | 2018-05-08 | 3235550.4912 | 3643251.21 | 3643251.2 | 89336147.3412 |  |  | 10814924.0552 | [5 empty] | 133598.95 | Sodic Club House | [7 empty] | Sodic Club House28
Sodic Club House | 29 | 2018-04-30 | 2018-04-20 | 2018-04-21 | 35 | 2018-05-26 | 2018-05-17 | 5735280.6088 | 2949189.68 | 2927170 | 95071427.95 |  |  | 13429692.21 | [5 empty] | 133598.95 | Sodic Club House | [7 empty] | Sodic Club House29
Sodic Club House | 30 | 2018-05-31 | 2018-05-25 | 2018-05-28 | 35 | 2018-07-02 | 2018-06-26 | 5753955.1349 | 1501648.1708 | 1523667.33 | 100825383.0849 |  |  | 13579694.3883 | [5 empty] | 39041.91 | Sodic Club House | [7 empty] | Sodic Club House30
Sodic Club House | 31 | 2018-06-30 | 2018-07-02 | 2018-07-04 | 35 | 2018-08-08 | 2018-08-02 | 4997405.8346 | 1752933.23 | 3752933.22 | 105822788.9195 |  |  | 13390603.7948 | [5 empty] | 41801.91 | Sodic Club House | [7 empty] | Sodic Club House31
Sodic Club House | 32 | 2018-07-31 | 2018-08-01 | 2018-07-30 | 35 | 2018-09-03 | 2018-09-04 | 7298776.2492 | 1851323.2394 | 1851323.25 | 113121565.1688 |  |  | 11999237.9332 | [5 empty] | 45521.91 | Sodic Club House | [7 empty] | Sodic Club House32
Sodic Club House | 33 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 35 | 2018-10-11 | 2018-10-09 | 6841826.5835 | 5028067.13 | 5028067.13 | 119963391.7522 |  |  | 12452865.1519 | [5 empty] | 76081.91 | Sodic Club House | [7 empty] | Sodic Club House33
Sodic Club House | 34 | 2018-09-30 | 2018-10-15 | 2018-10-15 | 35 | 2018-11-19 | 2018-11-21 | 9547045.4302 | 1372787.19 | 1372787.19 | 129510437.1825 |  |  | 9699552.55 | [5 empty] | 541161.91 | Sodic Club House | [7 empty] | Sodic Club House34
Sodic Club House | 35 | 2018-11-30 | 2018-11-25 | 2018-11-25 | 35 | 2018-12-30 | 2019-12-20 | 17370468.2779 | 2061960.9553 | 2061960.96 | 146880905.4603 |  |  | 8284813.5766 | [5 empty] | 557361.91 | Sodic Club House | [7 empty] | Sodic Club House35
Sodic Club House | 36 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 56 | 2019-08-27 | 2019-12-19 | 15653205.9497 | 3000000 | 9516540.66 | 162534111.41 | [8 empty] | 4804784.65 | Sodic Club House | [7 empty] | Sodic Club House36
Sodic Club House | 37 | 2020-08-31 | 2020-08-11 | 2020-08-11 | 56 | 2020-10-06 |  |  |  | 4028521 | [9 empty] | 0 | Sodic Club House | [7 empty] | Sodic Club House37
Sodic Eastown | 1 | 2019-03-31 | 2019-03-17 | 2019-03-17 | 42 | 2019-04-28 | 2019-03-20 | 9063098.3369 | 6785088.5699 | 138789620.12 | 9063098.3369 | 122000000 | 10000000 | [6 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown1
Sodic Eastown | 2 | 2019-04-30 | 2019-04-20 | 2019-04-16 | 42 | 2019-05-28 | 2019-04-18 | 20887437.3108 | 15652355.21 | 21566541.66 | 29950535.6476 | 5928168 | [7 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown2
Sodic Eastown | 3 | 2019-05-31 | 2019-05-20 | 2019-05-19 | 42 | 2019-06-30 | 2019-05-23 | 2101069.4381 | 1574016.17 | 1574016.18 | 32051605.0857 | [8 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown3
Sodic Eastown | 4 | 2019-06-30 | 2019-06-25 | 2019-06-23 | 42 | 2019-08-04 | 2019-07-08 | 22270031.4 | 26267292.44 | 25688338.61 | 54321636.4857 | [8 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown4
Sodic Eastown | 5 | 2019-07-31 | 2019-07-25 | 2019-07-25 | 42 | 2019-09-05 | 2019-08-01 | 45005158.6118 | 22056568.4027 | 37056568.4 | 99326795.0975 |  |  | 20344137.6 | [5 empty] | 144395.63 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown5
Sodic Eastown | 6 | 2019-08-31 | 2019-08-25 | 2019-08-19 | 42 | 2019-09-30 | 2019-09-08 | 38734277.1501 | 28554847.68 | 28554847.67 | 138061072.2476 |  |  | 20344137.6 | [5 empty] | 607331.68 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown6
Sodic Eastown | 7 | 2019-09-30 | 2019-09-25 | 2019-09-16 | 42 | 2019-10-28 | 2019-11-03 | 65627417.1905 |  | 38197130.95 | 203688489.4381 |  |  | 5537718 | [5 empty] | 921272.68 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown7
Sodic Eastown | 8 | 2019-10-31 | 2019-10-30 | 2019-11-02 | 42 | 2019-12-14 | 2019-11-14 | 85059782.1524 | 58794871.95 | 55532397.61 | 288748271.5905 |  |  | 1266429.46 | [5 empty] | 707331.68 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown8
Sodic Eastown | 9 | 2019-11-30 | 2019-11-30 | 2019-12-03 | 42 | 2020-01-14 | 2019-12-30 | 16046909.9143 | 40504812.26 | 40504812.26 | 304795181.5048 |  |  | 39767000.8 | [5 empty] | 2750976.18 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown9
Sodic Eastown | 10 | 2019-12-31 | 2019-12-31 | 2020-01-07 | 42 | 2020-02-18 | 2020-01-20 | 82638241.0762 | 32553581.24 | 32553581.24 | 387433422.581 |  |  | 1e-06 | [5 empty] | 3038523.68 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown10
Sodic Eastown | 11 | 2020-01-31 | 2020-01-31 | 2020-02-03 | 42 | 2020-03-16 | 2020-02-19 | 36710088.5775 | 27179529.3929 | 27179529.3929 | 424143511.1584 | [8 empty] | 3038523.68 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown11
Sodic Eastown | 12 | 2020-02-29 | 2020-02-29 | 2020-03-04 | 42 | 2020-04-15 | 2020-03-29 | 26833421.413 | 19553108.77 | 19553108.79 | 450976932.5714 | [8 empty] | 3314791.44 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown12
Sodic Eastown | 13 | 2020-03-31 | 2020-03-24 | 2020-03-25 | 42 | 2020-05-06 | 2020-05-17 | 22228765.6121 | 16201534.04 | 16201534.04 | 473205698.1835 | [8 empty] | 2704423.44 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown13
Sodic Eastown | 14 | 2020-04-30 | 2020-05-07 | 2020-05-10 | 42 | 2020-06-21 | 2020-06-15 | 24418089.9689 | 16537461.58 | 16537461.58 | 497623788.1524 | [8 empty] | 3495935.44 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown14
Sodic Eastown | 15 | 2020-05-31 | 2020-06-02 | 2020-06-06 | 42 | 2020-07-18 | 2020-06-23 | 19101976.1176 | 12895953.9558 | 12895954 | 516725764.27 | [8 empty] | 4174771.13 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown15
Sodic Eastown | 16 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 42 | 2020-08-15 | 2020-08-10 | 42785902.7013 | 30145771.5315 | 30145771.57 | 559511666.9713 | [8 empty] | 4707294.52 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown16
Sodic Eastown | 17 | 2020-07-31 | 2020-08-08 | 2020-08-10 | 42 | 2020-09-21 | 2020-09-07 | 30425304.0673 | 20899381.3823 | 20899381.34 | 589936971.0386 | [8 empty] | 5466992.46 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown17
Sodic Eastown | 18 | 2020-08-31 | 2020-08-31 | 2020-09-03 | 42 | 2020-10-15 | 2020-10-11 | 36663335.5424 | 22406610.78 | 22406610.78 | 626600306.581 | [8 empty] | 5860427.46 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown18
Sodic Eastown | 19 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 42 | 2020-11-15 | 2020-11-15 | 48818243.381 | 34417592.72 | 34417592.72 | 675418549.9619 | [8 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown19
Sodic Eastown | 20 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 42 | 2020-12-15 | 2020-12-14 | 81649174.4522 | 31197031.7827 | 31197031.83 | 757067724.4141 | [8 empty] | 6575145.76 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown20
Sodic Eastown | 21 | 2020-11-30 | 2020-11-30 | 2020-12-03 | 42 | 2021-01-14 | 2021-01-20 | 8971634.0811 | 29743783.27 | 29743783.32 | 766039358.4952 | [8 empty] | 7317323.76 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown21
Sodic Eastown | 22 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 42 | 2021-02-16 | 2021-02-09 | 29539477.0571 | 19964135.7 | 19964135.7 | 795578835.5524 | [8 empty] | 7664787.88 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown22
Sodic Eastown | 23 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 42 | 2021-03-18 | 2021-03-04 | 23832998.7215 | 19672746.6443 | 19672746.63 | 819411834.2738 | [8 empty] | 8075062.48 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown23
Sodic Eastown | 24 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 42 | 2021-04-18 | 2021-04-11 | 24555503.3928 | 14713744.16 | 14713744.17 | 843967337.6667 | [8 empty] | 8705062.48 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown24
Sodic Eastown | 25 | 2021-03-31 | 2021-03-31 | 2021-04-05 | 42 | 2021-05-17 | 2021-05-18 | 29789861.881 | 18632387.0541 | 18632387.16 | 873757199.5477 | [8 empty] | 9572854.12 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown25
Sodic Eastown | 26 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 42 | 2021-06-16 | 2021-06-17 | 45459659.9094 | 32407888.61 | 32407888.61 | 919216859.4571 | [8 empty] | 9252854.12 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown26
Sodic Eastown | 27 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-07-11 | 30032935.1619 | 21101612.82 | 21101612.82 | 949249794.619 | [8 empty] | 8752562.48 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown27
Sodic Eastown | 28 | 2021-06-30 | 2021-06-30 | 2021-07-07 | 42 | 2021-08-18 | 2021-08-09 | 37125243.7619 | 41708616.23 | 41708616.23 | 986375038.381 | [8 empty] | 11397821.25 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown28
Sodic Eastown | 29 | 2021-07-31 | 2021-07-24 | 2021-08-07 | 42 | 2021-09-18 | 2021-09-06 | 26258236.2286 | 10880905.48 | 10880905.48 | 1012633274.6095 | [8 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown29
Sodic Eastown | 30 | 2021-08-31 | 2021-08-31 | 2021-09-07 | 42 | 2021-10-19 | 2021-10-17 | 27535188.381 | 25479297.36 | 25479297.36 | 1040168462.9905 | [8 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown30
Sodic Eastown | 31 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 42 | 2021-11-21 | 2021-11-14 | 20856328.3905 | 22493923.51 | 22493923.41 | 1061024791.381 | [8 empty] | 9824319.61 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown31
Sodic Eastown | 32 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 42 | 2021-12-20 | 2021-12-07 | 17472419.8762 | 15680621.74 | 15680621.74 | 1078497211.2571 | [8 empty] | 9524319.61 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown32
Sodic Eastown | 33 | 2021-11-30 | 2021-11-30 | 2021-12-07 | 42 | 2022-01-18 | 2021-12-14 | 15003172.5524 | 19311419.98 | 19311419.98 | 1093500383.8095 | [8 empty] | 10022759.48 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown33
Sodic Eastown | 34 | 2021-12-31 | 2021-12-31 | 2021-12-27 | 42 | 2022-02-07 | 2022-03-10 | 4991381.7048 | 4602037.62 | 4602037.61 | 1098491765.5143 | [8 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown34
Sodic Eastown | 35 | 2022-04-30 | 2022-04-30 | 2022-05-18 | 42 | 2022-06-29 | 2022-06-14 | 46695355.6476 | 12555805.27 | 12555804.9 | 1145187121.1619 |  |  |  | 110343302 |  | -4596809 | 30061161 | 30061161 | 28213034 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown35
Sodic Eastown | 36 | 2022-07-31 | 2022-08-13 | 2022-08-15 | 42 | 2022-09-26 | 2022-09-12 | -0.0001 | 3904269.49 | 6254389.49 | 1145187121.1619 |  |  |  | 110343302.03 |  | -2378666.59 | 30061161.93 | 30061161.93 | 32117303 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown36
Sodic Eastown | 37 | 2022-12-31 | 2022-12-26 | 2023-01-01 | 42 | 2023-02-12 | 2023-01-22 | -1e-05 | 5035428.4 | 5035428.4 | 1145187121.1619 |  |  |  | 110343302.03 |  | -2378666.59 | 18874299.6215 | 18874299.6215 | 19273337.4308 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown37
Sodic Eastown | 38 | 2022-06-30 | 2022-06-12 | 2023-06-22 | 42 | 2023-08-03 | 2023-08-01 | -0.00011 | 2231188.43 | 2231188 | 1145187121.1619 | [8 empty] | 0 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown38
Sodic Eastown | 39 | 2023-06-30 | 2023-06-30 | 2023-10-22 | 42 | 2023-12-03 | 2023-10-29 |  | 28315194.9811 | 17894573 | 1145187121.1619 |  |  |  | 110343302.92 |  | -4596809.26 | 30061161.9302 | 30061161.9302 | -12704609.7849 | EDNC Retail & Offices Civil | [7 empty] | Sodic Eastown39
Sodic Eastown - Landscape | 1 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 42 | 2022-02-20 | 2022-02-14 | 1310241.4095 | 1545976.52 | 1545976.54 | 1310241.4095 |  |  | 710231.1 | [5 empty] | 0 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape1
Sodic Eastown - Landscape | 2 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 42 | 2022-03-17 | 2022-03-10 | 3185965.6857 | 2689319.17 | 2689319.17 | 4496207.0952 |  |  | 1064088.68 | [5 empty] | 0 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape2
Sodic Eastown - Landscape | 3 | 2022-03-31 | 2022-03-15 | 2022-03-17 | 42 | 2022-04-28 | 2022-03-31 | 5417455.381 | 8060960.68 | 5060960.68 | 9913662.4762 | [8 empty] | 0 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape3
Sodic Eastown - Landscape | 4 | 2022-04-30 | 2022-04-13 | 2022-04-13 | 42 | 2022-05-25 | 2022-04-14 | 1923818.4 | 4237695.69 | 4237695.68 | 11837480.8762 |  |  | 7645419.29 | [5 empty] | 433157 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape4
Sodic Eastown - Landscape | 5 | 2022-04-30 | 2022-05-10 | 2022-05-11 | 42 | 2022-06-22 | 2022-05-11 | 8146275.9524 | 2847434.08 | 2847434.11 | 19983756.8286 |  |  | 4687295.11 | 494379.4 |  |  | 641755.99 | 641755.99 | 477225 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape5
Sodic Eastown - Landscape | 6 | 2022-05-31 | 2022-05-17 | 2022-05-22 | 42 | 2022-07-03 | 2022-05-24 | 2241713.4381 | 1865468.85 | 1865468.85 | 22225470.2667 |  |  | 4887618.75 | 704722.2 |  |  | 705609.06 | 705609.06 | 477225 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape6
Sodic Eastown - Landscape | 7 | 2022-05-31 | 2022-06-10 | 2022-06-14 | 42 | 2022-07-26 |  |  |  | 2249247.81 | [9 empty] | 0 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape7
Sodic Eastown - Landscape | 8 | 2022-06-30 | 2022-06-26 | 2022-07-03 | 42 | 2022-08-14 | 2022-07-27 | 19106378.3905 | 13407927.22 | 8937999.74 | 46943391.219 |  |  | 2302349.81 | 17134472.44 |  |  | 1289822.765 | 1289822.765 | 380000 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape8
Sodic Eastown - Landscape | 9 | 2022-08-31 | 2022-08-25 | 2022-08-30 | 42 | 2022-10-11 | 2022-09-13 | 2763176 | 837296.04 | 837296.03 | 49706567.219 |  |  |  | 17105387 |  |  | 1304797 | 1304797 | 489137 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape9
Sodic Eastown - Landscape | 10 | 2022-08-31 | 2022-08-28 | 2022-10-19 | 42 | 2022-11-30 | 2022-10-20 | 3106667.3429 | 2965080.9889 | 2965081 | 52813234.5619 | [8 empty] | 0 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape10
Sodic Eastown - Landscape | 11 | 2022-09-30 | 2022-09-28 | 2022-11-05 | 42 | 2022-12-17 | 2022-11-15 | 2478048.6476 | 970278.46 | 970278.45 | 53908426.4 |  |  |  | 20753354 |  |  |  |  | 581609 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape11
Sodic Eastown - Landscape | 12 | 2022-10-31 | 2022-10-28 | 2022-11-15 | 42 | 2022-12-27 | 2022-11-22 | 2146120.2476 | 2038310.82 | 2038310.81 | 56054546.6476 |  |  |  | 23518667 |  |  | 1471431.85 | 1471431.85 | 591609 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape12
Sodic Eastown - Landscape | 13 | 2023-05-31 | 2023-06-01 | 2023-10-16 | 42 | 2023-11-27 |  |  |  | 4532604.51 | [9 empty] | 0 | EDNC Hardscape Package | [7 empty] | Sodic Eastown - Landscape13
Sokhna Port Expansion | 1 | 2022-01-31 | 2022-01-31 | 2022-03-14 | 53 | 2022-05-06 | 2022-03-24 | 28642092.8 | 16602157.8 | 201618177 | 28642092.8 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion1
Sokhna Port Expansion | 2 | 2022-02-28 | 2022-02-28 | 2022-03-31 | 53 | 2022-05-23 | 2022-04-17 | 30329196.74 | 19713977.881 | 52996310.3 | 58971289.54 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion2
Sokhna Port Expansion | 3 | 2022-03-31 | 2022-03-31 | 2022-04-14 | 53 | 2022-06-06 |  |  |  | 55802951.65 | [9 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion3
Sokhna Port Expansion | 4 | 2022-04-30 | 2022-04-30 | 2022-05-25 | 53 | 2022-07-17 | 2022-07-31 | 26384347.91 | 16604871.85 | 16604871.85 | 174022377.11 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion4
Sokhna Port Expansion | 5 | 2022-06-30 | 2022-06-30 | 2022-07-28 | 53 | 2022-09-19 | 2022-09-30 | 90184360.23 | 58619834.1495 | 59014964.55 | 264206737.34 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion5
Sokhna Port Expansion | 6 | 2022-07-31 | 2022-07-31 | 2022-09-19 | 53 | 2022-11-11 | 2022-10-19 | 41088510.15 | 26707531.5975 | 26209033.35 | 305295247.49 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion6
Sokhna Port Expansion | 7 | 2022-08-31 | 2022-08-31 | 2022-10-23 | 53 | 2022-12-15 |  |  |  | 36803665.95 | [9 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion7
Sokhna Port Expansion | 8 | 2022-09-30 | 2022-09-30 | 2022-11-16 | 53 | 2023-01-08 | 2022-12-20 | 55834648.2 | 36284090.45 | 36284090.45 | 418825805.92 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion8
Sokhna Port Expansion | 9 | 2022-10-31 | 2022-10-31 | 2022-12-15 | 53 | 2023-02-06 | 2023-01-02 | 46210885.16 | 30030028.45 | 30030028.45 | 465036691.08 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion9
Sokhna Port Expansion | 10 | 2022-11-30 | 2022-11-30 | 2023-01-08 | 53 | 2023-03-02 | 2023-01-24 | 42258919.66 | 27468297.779 | 27461819.5 | 507295610.74 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion10
Sokhna Port Expansion | 11 | 2022-12-31 | 2022-12-31 | 2023-01-25 | 53 | 2023-03-19 | 2023-07-05 | 69343976.76 | 50769799.2 | 50769799.2 | 576639587.5 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion11
Sokhna Port Expansion | 12 | 2023-01-31 | 2023-01-31 | 2023-02-13 | 53 | 2023-04-07 | 2023-07-05 | 106701066.13 | 70395885.55 | 70395885.55 | 683340653.63 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion12
Sokhna Port Expansion | 13 | 2023-02-28 | 2023-02-28 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 41939163.73 | 27260456.4245 | 491489.95 | 725279817.36 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion13
Sokhna Port Expansion | 14 | 2023-03-31 | 2023-03-31 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 18010876.44 | 11707069.686 | 6704080.85 | 743290693.8 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion14
Sokhna Port Expansion | 15 | 2023-04-30 | 2023-04-30 | 2023-07-01 | 53 | 2023-08-23 | 2023-07-15 | 15185688.98 | 9870697.837 | 4368115.65 | 758476382.78 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion15
Sokhna Port Expansion | 16 | 2023-05-31 | 2023-05-31 | 2023-08-07 | 53 | 2023-09-29 | 2023-08-07 | 37404208.29 | 24312735.3885 | 23966243.5 | 795880591.07 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion16
Sokhna Port Expansion | 17 | 2023-06-30 | 2023-06-30 | 2023-08-27 | 53 | 2023-10-19 | 2023-08-27 | 22411649.53 | 14567572.1945 | 14567572.19 | 818292240.6 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion17
Sokhna Port Expansion | 18 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 53 | 2023-09-22 |  |  |  | 14135207.0055 | [9 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion18
Sokhna Port Expansion | 19 | 2023-08-31 | 2023-08-31 | 2023-08-31 | 53 | 2023-10-23 | 2023-10-17 | 15685272.2 | 10195426.93 | 10049896.61 | 856365557.7 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion19
Sokhna Port Expansion | 20 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 53 | 2023-12-17 | 2023-11-20 | 20920498.28 | 13598323.882 | 13204353 | 877286055.98 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion20
Sokhna Port Expansion | 21 | 2023-10-31 | 2023-10-31 | 2023-12-27 | 53 | 2024-02-18 | 2023-12-27 | 9034186.8 | 5872221.42 | 5788234 | 886320242.78 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion21
Sokhna Port Expansion | 22 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 53 | 2024-04-05 | 2024-02-05 | 3862923.74 | 2510900.431 | 2510900.431 | 890183166.52 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion22
Sokhna Port Expansion | 23 | 2023-12-31 | 2023-12-31 | 2024-03-09 | 53 | 2024-05-01 | 2024-02-25 | 943826.94 | 613487.511 | 568614.519 | 891126993.46 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion23
Sokhna Port Expansion- 100m | 1 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 60 | 2023-04-29 |  |  |  | 39700885.25 | [9 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion- 100m1
Sokhna Port Expansion- 100m | 2 | 2023-03-31 | 2023-03-31 | 2023-07-01 | 60 | 2023-08-30 | 2023-07-01 | 24129951.39 | 15684468.4035 | 10628517.75 | 82118084.22 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion- 100m2
Sokhna Port Expansion- 100m | 3 | 2023-04-30 | 2023-04-30 | 2023-08-07 | 60 | 2023-10-06 | 2023-08-07 | 26794714.09 | 17416564.1585 | 10464912.35 | 108912798.31 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion- 100m3
Sokhna Port Expansion- 100m | 4 | 2023-09-30 | 2023-09-30 | 2023-09-07 | 60 | 2023-11-06 | 2023-10-17 | 13246168.7303 | 8610009.6747 | 8297916 | 122158967.0403 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion- 100m4
Sokhna Port Expansion- 100m | 5 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 60 | 2023-12-24 | 2023-11-20 | 4703266.4897 | 3057123.2183 | 3240800 | 126862233.53 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion- 100m5
Sokhna Port Expansion- 100m | 6 | 2023-10-31 | 2023-10-31 | 2023-10-25 | 60 | 2023-12-24 | 2023-12-27 | 29655965.57 | 29655965 | 20436714.5 | 156518199.1 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion- 100m6
Sokhna Port Expansion- 100m | 7 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 60 | 2024-04-12 | 2024-02-05 | 4532607.67 | 2946194.9855 | 3976775.9 | 161050806.77 | [8 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion- 100m7
Sokhna Port Expansion-internal roads | 1 | 2022-07-31 | 2022-07-19 | 2022-10-31 | 60 | 2022-12-30 |  |  |  | 1800470.45 | [9 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion-internal roads1
Sokhna Port Expansion-internal roads | 2 | 2022-08-31 | 2022-08-01 | 2022-11-28 | 60 | 2023-01-27 |  |  |  | 3219.75 | [9 empty] | 0 | Sokhna Port Expansion | [7 empty] | Sokhna Port Expansion-internal roads2
Sports Hall - Civil Works | 3 | 2021-01-31 | 2021-01-17 | 2021-01-17 | 60 | 2021-03-18 |  |  |  | 2493330 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Civil Works3
Sports Hall - Civil Works | 4 | 2021-03-31 | 2021-03-17 | 2021-03-18 | 60 | 2021-05-17 |  |  |  | 10576930 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Civil Works4
Sports Hall - Civil Works | 5 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 60 | 2021-07-30 | 2021-09-13 | 47849709.5 | 17108050 | 17108045 | 381426324.58 | [8 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Civil Works5
Sports Hall - Civil Works | 6 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-11-23 | 51027855.5 | 414030 | 414025 | 432454180.08 | [8 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Civil Works6
Sports Hall - Civil Works | 7 | 2021-11-30 | 2021-11-30 | 2021-12-14 | 60 | 2022-02-12 |  |  | 12888184 | 0 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Civil Works7
Sports Hall - Civil Works | 8 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 |  |  |  | 0 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Civil Works8
Sports Hall - Finishes | 1 | 2021-05-31 | 2021-05-23 | 2021-05-23 | 60 | 2021-07-22 |  |  |  | 1388840 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Finishes1
Sports Hall - Finishes | 2 | 2021-08-31 | 2021-09-02 | 2021-09-11 | 60 | 2021-11-10 |  |  |  | 13091760 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Finishes2
Sports Hall - Finishes | 3 | 2021-10-31 | 2021-10-31 | 2021-10-11 | 60 | 2021-12-10 | 2021-11-17 | 91998353.75 | 77278617 | 7109625 | 178494684.93 | [8 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Finishes3
Sports Hall - Finishes | 4 | 2022-07-31 | 2022-07-31 | 2022-08-09 | 60 | 2022-10-08 |  |  |  | 3699060 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Finishes4
Sports Hall - Finishes - ADD.01 | 1 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 60 | 2022-03-12 | 2022-02-22 | 9145259 | 5944418.35 | 5941290 | 9145259 | [8 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Finishes - ADD.011
Sports Hall - Finishes - ADD.01 | 2 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 |  |  |  | 2631750 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Finishes - ADD.012
Sports Hall - Finishes - Landscape | 1 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 |  |  |  | 0.0003 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - Finishes - Landscape1
Sports Hall - MEP | 1 | 2022-02-28 | 2022-02-24 | 2022-02-24 | 60 | 2022-04-25 |  |  |  | 67417715 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - MEP1
Sports Hall - MEP | 2 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 |  |  | 13327738 | 1103175 | [9 empty] | 0 | Olympic Multi – Sports Hall | [7 empty] | Sports Hall - MEP2
Suez Intake & P Stations-ABB apply | 1 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 779997.07 | 524786.37 | 509186.43 | 779997.07 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB apply1
Suez Intake & P Stations-ABB apply | 2 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 1514111.97 | 988420.71 | 988420.71 | 2294109.04 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB apply2
Suez Intake & P Stations-ABB apply | 3 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 1605876.32 | 1048325 | 1048324.9964 | 3899985.36 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB apply3
Suez Intake & P Stations-ABB apply | 6 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 6098633.64 | 573225.5 | 0 | 9998619 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB apply6
Suez Intake & P Stations-ABB supply | 1 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 5874834 | 5134498.57 | 5134498.57 | 5874834 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB supply1
Suez Intake & P Stations-ABB supply | 2 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 8551701.56 | 7437727.82 | 7437727.82 | 14426535.56 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB supply2
Suez Intake & P Stations-ABB supply | 3 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 1037578.56 | 814872.96 | 814872.95 | 15464114.12 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB supply3
Suez Intake & P Stations-ABB supply | 4 | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 |  |  |  | 3667977.98 | [9 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB supply4
Suez Intake & P Stations-ABB supply | 8 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 24332063.94 | 817934.28 | 1e-05 | 40613282 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-ABB supply8
Suez Intake & P Stations-SSC apply | 1 | 2023-01-31 | 2023-01-16 | 2023-01-15 | 42 | 2023-02-26 | 2023-01-16 | 1124419.48 | 1102291.62 | 1102291.62 | 1124419.48 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC apply1
Suez Intake & P Stations-SSC apply | 2 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 3081346.71 | 3020707.78 | 3020707.78 | 4205766.19 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC apply2
Suez Intake & P Stations-SSC apply | 3 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 788338.19 | 772824.19 | 772824.1924 | 4994104.38 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC apply3
Suez Intake & P Stations-SSC apply | 7 | 2024-02-29 | 2024-02-26 | 2024-02-26 | 42 | 2024-04-08 | 2024-02-27 | 12349144.72 | 6963227.52 | 0 | 17343249.1 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC apply7
Suez Intake & P Stations-SSC apply | 8 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 1924769.3 | 1886891.07 | 1886891.07 | 19268018.4 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC apply8
Suez Intake & P Stations-SSC supply | 1 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 10223133.6 | 8726335.42 | 8726326.42 | 10223133.6 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC supply1
Suez Intake & P Stations-SSC supply | 2 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 3765789.87 | 3190884.06 | 3190893.09 | 13988923.47 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC supply2
Suez Intake & P Stations-SSC supply | 3 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 374122.68 | 283552.06 | 283552.06 | 14363046.15 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC supply3
Suez Intake & P Stations-SSC supply | 4 | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 |  |  |  | 1e-05 | [9 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC supply4
Suez Intake & P Stations-SSC supply | 8 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 9321912.4 | 1886800.52 | 0 | 24074956.74 | [8 empty] | 0 | 0 | [7 empty] | Suez Intake & P Stations-SSC supply8
SVC | 1 | 2024-02-29 | 2024-02-17 | 2024-04-01 | 42 | 2024-05-13 | 2024-04-01 | 3212437.04 | 2377203.41 | 3375312.6616 | 3212437.04 | 1158731.1 | [7 empty] | 0 | 0 | [7 empty] | SVC1
SVC | 2 | 2024-05-31 | 2024-05-25 | 2024-06-12 | 42 | 2024-07-24 |  |  |  | 0 | [9 empty] | 0 | 0 | [7 empty] | SVC2
Uptown PK #53 | 25 | 2017-09-30 | 2017-10-10 | 2017-11-11 | 40 | 2017-12-21 | 2017-11-28 |  | 12105864.365 | 12009168.61 | 210168675.9558 |  |  | 8286463.8075 | [5 empty] | 1299409.2216 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5325
Uptown PK #53 | 26 | 2017-10-31 | 2017-11-10 | 2017-11-28 | 40 | 2018-01-07 | 2017-12-21 | 18341001.0169 | 13230735.7159 | 13124888.11 | 228815469.9927 |  |  | 6928080.7619 | [5 empty] | 1215618.2216 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5326
Uptown PK #53 | 27 | 2017-11-30 | 2017-12-10 | 2017-12-26 | 40 | 2018-02-04 | 2018-01-08 | 11525442.3347 | 9723398.7945 | 9593936.7945 | 240340912.3274 |  |  | 8309746.418 | [5 empty] | 1307409.2216 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5327
Uptown PK #53 | 28 | 2017-12-31 | 2018-01-10 | 2018-01-16 | 40 | 2018-02-25 | 2018-02-15 | 13381649.8939 | 13380241.7057 | 13320601.43 | 253722562.2213 |  |  | 4669320.168 | [5 empty] | 1464327.5816 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5328
Uptown PK #53 | 29 | 2018-01-31 | 2018-02-10 | 2018-02-15 | 40 | 2018-03-27 | 2018-03-06 | 17500846.4172 | 11043112.6231 | 10942287.56 | 271223408.6385 |  |  | 3636537.0679 | [5 empty] | 1444327.5816 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5329
Uptown PK #53 | 30 | 2018-02-28 | 2018-03-10 | 2018-03-17 | 40 | 2018-04-26 | 2018-04-04 | 15321007.8734 | 11437376.0467 | 11348802.26 | 286544416.4997 |  |  | 2782555.8001 | [5 empty] | 3125936.127 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5330
Uptown PK #53 | 31 | 2018-03-31 | 2018-04-10 | 2018-04-18 | 40 | 2018-05-28 | 2018-05-20 | 11220346.2103 | 7091661.81 | 7033824.83 | 297764762.71 |  |  | 1008898.49 | [5 empty] | 4001808.9907 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5331
Uptown PK #53 | 32 | 2018-04-30 | 2018-05-10 | 2018-05-17 | 40 | 2018-06-26 | 2018-05-29 | 4916024.5037 | 2387351.5744 | 2358051.13 | 302680787.2137 |  |  | 878601.9171 | [5 empty] | 4488322.2907 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5332
Uptown PK #53 | 33 | 2018-05-31 | 2018-06-15 | 2018-06-24 | 40 | 2018-08-03 | 2018-07-10 | 3312628.1623 | 2709512.38 | 2690853.59 | 305993415.376 |  |  | 613573.28 | [5 empty] | 4562822.2907 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5333
Uptown PK #53 | 34 | 2018-06-30 | 2018-07-10 | 2018-07-17 | 40 | 2018-08-26 | 2018-07-26 | 73574.6923 | 1431626.0807 | 1431626.0807 | 306066990.0683 |  |  | 613573.2833 | [5 empty] | 4285977.9307 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5334
Uptown PK #53 | 35 | 2018-07-31 | 2018-08-10 | 2018-08-16 | 40 | 2018-09-25 | 2018-09-12 | 3416261.3696 | 2488623.0127 | 2466454.76 | 309483251.4379 |  |  | 385285.6486 | [5 empty] | 4958858.9291 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5335
Uptown PK #53 | 36 | 2018-08-31 | 2018-09-10 | 2018-09-19 | 40 | 2018-10-29 | 2018-10-20 | 2041348.5871 | 2502552.38 | 2490213.39 | 311524600.025 |  |  | 359304.445 | [5 empty] | 4948858.9291 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5336
Uptown PK #53 | 37 | 2018-09-30 | 2018-10-10 | 2018-10-22 | 40 | 2018-12-01 | 2018-12-16 | 1273110.6827 | 1753673.2424 | 1746850.68 | 312797710.7077 |  |  | 200543.77 | [5 empty] | 5687765.7473 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5337
Uptown PK #53 | 38 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 40 | 2019-02-25 | 2019-02-18 | 747405.6143 | 1048789.58 | 1902092.11 | 313545116.322 |  |  | 200543.77 | [5 empty] | 6192106.3873 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5338
Uptown PK #53 | 39 | 2019-03-31 | 2019-04-10 | 2019-04-11 | 40 | 2019-05-21 | 2019-04-21 | 32300.9957 | 929614.0301 | 943725.79 | 313577417.3177 |  |  | 200543.77 | [5 empty] | 5191842.6873 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5339
Uptown PK #53 | 40 | 2019-05-31 | 2019-06-15 | 2019-06-18 | 40 | 2019-07-28 | 2019-07-16 | 52815.0023 | 1435222.17 | 1435222.17 | 313630232.32 |  |  | 200543.77 | [5 empty] | 0 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5340
Uptown PK #53 | 41 | 2019-08-31 | 2019-08-15 | 2019-08-20 | 40 | 2019-09-29 | 2019-08-20 | 0 | 4202366.45 | 4202366.45 | 313630232.32 |  |  | 200543.77 | [5 empty] | 0 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5341
Uptown PK #53 | 42 | 2019-12-31 | 2019-12-15 | 2019-12-19 | 40 | 2020-01-28 | 2020-01-26 | 4356349.94 | 1380970.95 | 1380970.95 | 317986582.26 |  |  | 200543.77 | [5 empty] | 0 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5342
Uptown PK #53 | 43 | 2020-02-29 | 2020-02-25 | 2020-03-10 | 40 | 2020-04-19 | 2020-04-15 | 3411373.56 | 3747539.31 | 4834138.97 | 321397955.82 |  |  | 200543.77 | [5 empty] | 0 | EMAAR-PKG#53-UPTOWN | [7 empty] | Uptown PK #5343
Uptown PK #62 | 7 | 2017-09-30 | 2017-09-30 | 2017-10-04 | 40 | 2017-11-13 | 2017-10-18 |  | 1684908.08 | 1684908.09 | 18419996.59 |  |  | 0 | [5 empty] | 136775.69 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #627
Uptown PK #62 | 8 | 2017-10-31 | 2017-10-31 | 2017-11-02 | 40 | 2017-12-12 | 2017-11-14 | 4024169.64 | 2970870.89 | 2970870.89 | 22444166.23 |  |  | 1403336.04 | [5 empty] | 169833.53 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #628
Uptown PK #62 | 9 | 2017-11-30 | 2017-11-30 | 2017-12-04 | 40 | 2018-01-13 | 2017-12-21 | 3353637.028 | 2124952.16 | 2124952.16 | 25797803.258 |  |  | 1883218.402 | [5 empty] | 193475.95 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #629
Uptown PK #62 | 10 | 2017-12-31 | 2017-12-27 | 2017-12-30 | 40 | 2018-02-08 | 2018-01-18 | 3315629.905 | 2207449.91 | 2207449.91 | 29113433.163 |  |  | 2376274.377 | [5 empty] | 216794.47 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6210
Uptown PK #62 | 11 | 2018-01-31 | 2018-01-31 | 2018-02-03 | 40 | 2018-03-15 | 2018-02-15 | 3273536.577 | 1524280.94 | 1524280.94 | 32386969.74 |  |  | 1872928.9681 | [5 empty] | 233754.86 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6211
Uptown PK #62 | 12 | 2018-02-28 | 2018-02-28 | 2018-03-01 | 40 | 2018-04-10 | 2018-03-18 | 2806216.291 | 1565019.15 | 1565019.14 | 35193186.031 |  |  | 1983635.499 | [5 empty] | 291613.6 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6212
Uptown PK #62 | 13 | 2018-03-31 | 2018-03-31 | 2018-04-02 | 40 | 2018-05-12 | 2018-05-08 | 6967775.654 | 2219134.03 | 2219134.03 | 42160961.685 |  |  | 301154.885 | [5 empty] | 1040317.09 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6213
Uptown PK #62 | 14 | 2018-04-30 | 2018-05-08 | 2018-05-08 | 40 | 2018-06-17 | 2018-06-26 | 3891325.445 | 854854.3 | 854854.29 | 46052287.13 |  |  | 0 | [5 empty] | 2182913.11 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6214
Uptown PK #62 | 15 | 2018-07-31 | 2018-07-24 | 2018-08-14 | 40 | 2018-09-23 | 2018-09-06 | 1266868.51 | 2299870.97 | 2299870.99 | 47319155.64 |  |  | 0 | [5 empty] | 2396855.11 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6215
Uptown PK #62 | 16 | 2018-09-30 | 2018-10-03 | 2018-10-04 | 40 | 2018-11-13 | 2018-11-25 | -245868.22 | 931895.88 | 931895.88 | 47073287.42 | [8 empty] | 1241550.872 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6216
Uptown PK #62 | 17 | 2019-03-31 | 2019-03-25 | 2019-03-24 | 40 | 2019-05-03 | 2019-04-11 | 0 | 419078.79 | 419078.79 | 47073287.42 | [8 empty] | 928608.274 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6217
Uptown PK #62 | 18 | 2019-09-30 | 2019-10-09 | 2019-10-09 | 40 | 2019-11-18 | 2019-11-03 | 0 | 864260.36 | 864260.36 | 47073287.42 | [8 empty] | 987399.24 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6218
Uptown PK #62 | 19 | 2019-12-31 | 2019-12-18 | 2019-12-19 | 40 | 2020-01-28 | 2020-07-19 | 22437 | 1195853.88 | 1416810.93 | 47095724.42 | [8 empty] | 990172.52 | EMAAR-PKG#62-UPTOWN | [7 empty] | Uptown PK #6219
Wady Halfa | 1 | 2022-11-30 | 2022-11-30 | 2022-12-11 | 30 | 2023-01-10 | 2022-12-18 | 3078932.9 | 33029517.9 | 41733360.9 | 3078932.9 |  |  | 33200100 | [5 empty] | 0 | Wadi Halfa Port | [7 empty] | Wady Halfa1
Wady Halfa | 2 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 30 | 2023-03-10 | 2023-02-14 | 23601516.1 | 11905091.98 | 19196261.85 | 26680449 |  |  | 18254159 | [5 empty] | 0 | Wadi Halfa Port | [7 empty] | Wady Halfa2
Wady Halfa | 3 | 2023-02-28 | 2023-02-28 | 2023-03-16 | 30 | 2023-04-15 | 2023-03-16 | 17962793.18 | 14516628.581 | 2807166.9 | 44643242.18 |  |  | 4370481.56 | [5 empty] | 0 | Wadi Halfa Port | [7 empty] | Wady Halfa3
Wady Halfa | 4 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 30 | 2023-05-10 | 2023-05-08 | 8749053.22 | 3679103.55 | 3015154.3 | 53392295.4 | [8 empty] | 0 | Wadi Halfa Port | [7 empty] | Wady Halfa4
Wady Halfa | 5 | 2024-03-31 | 2024-03-15 | 2024-03-15 | 30 | 2024-04-14 |  |  |  | 2984537.1 | [9 empty] | 0 | Wadi Halfa Port | [7 empty] | Wady Halfa5
Western Fence | 1 | 2023-10-31 | 2023-10-31 | 2023-10-30 | 42 | 2023-12-11 | 2023-11-02 | 762742.21 | 792870.53 | 418218.39 | 762742.21 | [8 empty] | 0 | 0 | [7 empty] | Western Fence1
Zayed Park | 1 | 2019-10-31 | 2019-10-28 | 2019-10-28 | 30 | 2019-11-27 | 2019-11-07 | 191006.802 | 505797.14 | 505797 | 191006.802 |  |  | 410791.498 | [5 empty] | 0 | 0 | [7 empty] | Zayed Park1
Zayed Park | 2 | 2019-12-31 | 2019-12-31 | 2020-01-11 | 30 | 2020-02-10 | 2020-09-21 | 842290.974 | 352690.39 | 264423.21 | 1033297.776 | [8 empty] | 0 | 0 | [7 empty] | Zayed Park2
[8 empty] | 19805227693.4556 | 15454594032.6016 | 19051703443.7124 |  | 1477407008.82 | 890783556.123 | 11199832140.5956 | 28218786789.695 | 107915790.6 | 12523278641.5813 | 2970327920.4235 | 2614672939.897 | 2165045374.0028 | [8 empty] | 0

## collection only
Project | Invoice No. | invoice round down | concact | Collection amount
6TH October tunnel | 1 | 1 | 6TH October tunnel1 | 1520548
6TH October tunnel | 2 | 2 | 6TH October tunnel2 | 3208372.9
6TH October tunnel | 2.1 | 2 | 6TH October tunnel2 | 300000
6TH October tunnel | 3 | 3 | 6TH October tunnel3 | 0.001
6TH October tunnel | 4 | 4 | 6TH October tunnel4 | 5155347
6TH October tunnel | 5 | 5 | 6TH October tunnel5 | 2856009
6TH October tunnel | 6 | 6 | 6TH October tunnel6 | 1337162.6
Abo Ghaleb Bridge | 1 | 1 | Abo Ghaleb Bridge1 | 175270.85
Abo Ghaleb Bridge | 2 | 2 | Abo Ghaleb Bridge2 | 2494611.027
Abo Ghaleb Bridge | 3 | 3 | Abo Ghaleb Bridge3 | 2045810.923
Abo Ghaleb Bridge | 4 | 4 | Abo Ghaleb Bridge4 | 12711007.22
Abo Ghaleb Bridge | 5 | 5 | Abo Ghaleb Bridge5 | 1645829.28
Abo Ghaleb Bridge | 6 | 6 | Abo Ghaleb Bridge6 | 0.0001
AEON | 1 | 1 | AEON1 | 1264914.16
AEON | 2 | 2 | AEON2 | 1513146.56
AEON | 3 | 3 | AEON3 | 780253.07
AEON | 4 | 4 | AEON4 | 484406.35
Al Jazi | 1 | 1 | Al Jazi1 | 2199495
Al Jazi | 2 | 2 | Al Jazi2 | 2330066
Al Jazi | 3 | 3 | Al Jazi3 | 3090062.9
Al Jazi | 4 | 4 | Al Jazi4 | 3867947.36
Al Jazi | 5 | 5 | Al Jazi5 | 4039155
Al Jazi | 6 | 6 | Al Jazi6 | 2383592
Al Jazi | 7 | 7 | Al Jazi7 | 4138160
Al Jazi | 8 | 8 | Al Jazi8 | 6905844.19
Al Jazi | 9 | 9 | Al Jazi9 | 1762571
Al Jazi | 10 | 10 | Al Jazi10 | 2302251
Al Jazi | 11 | 11 | Al Jazi11 | 3838772.36
Al Jazi | 12 | 12 | Al Jazi12 | 922154
Al Jazi | 13 | 13 | Al Jazi13 | 2994292.79
Al Jazi | 14 | 14 | Al Jazi14 | 1629015.64
Al Jazi | 15 | 15 | Al Jazi15 | 2107757
Al Jazi | 16 | 16 | Al Jazi16 | 120989.08
Al Jazi | 17 | 17 | Al Jazi17 | 2935343.72
Al Jazi | 18 | 18 | Al Jazi18 | 2748544.1
Al Jazi | 19 | 19 | Al Jazi19 | 2000000
Al Jazi | 19.1 | 19 | Al Jazi19 | 1100493.11
Al Jazi | 20 | 20 | Al Jazi20 | 371543.5
Al Jazi | 21 | 21 | Al Jazi21 | 0.0001
Al Jazi | 22 | 22 | Al Jazi22 | 2500000
Al Jazi | 22.1 | 22 | Al Jazi22 | 2000000
Al Jazi | 22.2 | 22 | Al Jazi22 | 848568.49
Al Jazi | 22.3 | 22 | Al Jazi22 | 1000000
Al Jazi | 22.4 | 22 | Al Jazi22 | 1000000
Al Jazi | 22.5 | 22 | Al Jazi22 | 1242872
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 90608.89
Al Jazi - Center Zone | 2 | 2 | Al Jazi - Center Zone2 | 1686320.29
Al Jazi - Center Zone | 3 | 3 | Al Jazi - Center Zone3 | 360179.68
Al Jazi - Center Zone | 4 | 4 | Al Jazi - Center Zone4 | 370581.69
Al Jazi - Center Zone | 5 | 5 | Al Jazi - Center Zone5 | 858100
Al Jazi - Center Zone | 6 | 6 | Al Jazi - Center Zone6 | -0.01
Al Jazi - Center Zone | 7 | 7 | Al Jazi - Center Zone7 | 151431.32
Al Jazi - Center Zone | 1 | 1 | Al Jazi - Center Zone1 | 14666580.12
Al Jazi - Social Insurance | 1 | 1 | Al Jazi - Social Insurance1 | 266994
Al Jazi | 1 | 1 | Al Jazi1 | 53125000
Alfa Lab | 1 | 1 | Alfa Lab1 | 1459340
Allegria-New Modifications | 1 | 1 | Allegria-New Modifications1 | 659568.2
Astoria - Sharm | 2 | 2 | Astoria - Sharm2 | 837813.8
Astoria - Sharm | 3 | 3 | Astoria - Sharm3 | 269728
Astoria - Sharm | 4 | 4 | Astoria - Sharm4 | 1641108
Astoria - Sharm | 5 | 5 | Astoria - Sharm5 | 709627
Astoria - Sharm | 6 | 6 | Astoria - Sharm6 | 244817
Astoria - Sharm | 7 | 7 | Astoria - Sharm7 | 654151
Astoria - Sharm | 8 | 8 | Astoria - Sharm8 | 1160836
Astoria - Sharm | 1 | 1 | Astoria - Sharm1 | 1365525
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 4511122
Astoria Hotel | 2 | 2 | Astoria Hotel2 | 2448868
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 5421697
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 4634265
Astoria Hotel | 5 | 5 | Astoria Hotel5 | 5818860
Astoria Hotel | 6 | 6 | Astoria Hotel6 | 3446328.13
Astoria Hotel | 6.1 | 6 | Astoria Hotel6 | 5000000
Astoria Hotel | 7 | 7 | Astoria Hotel7 | 8710615
Astoria Hotel | 8 | 8 | Astoria Hotel8 | 2805916
Astoria Hotel | 9 | 9 | Astoria Hotel9 | 2000000
Astoria Hotel | 9.1 | 9 | Astoria Hotel9 | 4286403
Astoria Hotel | 10 | 10 | Astoria Hotel10 | 4982321
Astoria Hotel | 11 | 11 | Astoria Hotel11 | 10757000
Astoria Hotel | 12 | 12 | Astoria Hotel12 | 2603000
Astoria Hotel | 13 | 13 | Astoria Hotel13 | 5389256
Astoria Hotel | 14 | 14 | Astoria Hotel14 | 6216098
Astoria Hotel | 15 | 15 | Astoria Hotel15 | 4185662
Astoria Hotel | 16 | 16 | Astoria Hotel16 | 3225683
Astoria Hotel | 17 | 17 | Astoria Hotel17 | 2804159
Astoria Hotel | 18 | 18 | Astoria Hotel18 | 4819756
Astoria Hotel | 19 | 19 | Astoria Hotel19 | 1511334.24
Astoria Hotel | 20 | 20 | Astoria Hotel20 | 0.0001
Astoria Hotel | 21 | 21 | Astoria Hotel21 | 0.0001
Astoria Hotel | 22 | 22 | Astoria Hotel22 | 1e-05
Astoria Hotel | 23 | 23 | Astoria Hotel23 | 17286732.59
Astoria Hotel | 24 | 24 | Astoria Hotel24 | 10400000
Astoria Hotel | 25 | 25 | Astoria Hotel25 | 3117985
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 46039744.5
Astoria Hotel | 2 | 2 | Astoria Hotel2 | 18415897.8
Astoria Hotel | 3 | 3 | Astoria Hotel3 | 9207948.9
Astoria Hotel | 4 | 4 | Astoria Hotel4 | 9207948.9
Astoria Hotel - Final Retention | 1 | 1 | Astoria Hotel - Final Retention1 | 5000000
Astoria Hotel | 1 | 1 | Astoria Hotel1 | 2000000
Astoria Hotel - Social Insurrance | 1 | 1 | Astoria Hotel - Social Insurrance1 | 959926
Astoria Hotel - Spare Parts V.O 137 | 1 | 1 | Astoria Hotel - Spare Parts V.O 1371 | 1929946
Astoria Hotel IPCs 15-20 | 1 | 1 | Astoria Hotel IPCs 15-201 | 1409611.34
Baraka Land Fence | 1 | 1 | Baraka Land Fence1 | 2467026
Baraka Land Fence | 2 | 2 | Baraka Land Fence2 | 8497787.46
Baraka Land Fence | 3 | 3 | Baraka Land Fence3 | 15418299.78
Baraka Land Fence | 4 | 4 | Baraka Land Fence4 | 6072172.61
Benban - Aswan | 2 | 2 | Benban - Aswan2 | 21842173.61
Benban - Aswan | 3 | 3 | Benban - Aswan3 | 10577813.02
Benban - Aswan | 4 | 4 | Benban - Aswan4 | 15006351.74
Benban - Aswan | 5 | 5 | Benban - Aswan5 | 37440497.15
Benban - Aswan | 6 | 6 | Benban - Aswan6 | 23886898.7775
Benban - Aswan | 7 | 7 | Benban - Aswan7 | 25237199.4694
Benban - Aswan | 8 | 8 | Benban - Aswan8 | 28236383.5819
Benban - Aswan | 9 | 9 | Benban - Aswan9 | 33103432.2978
Benban - Aswan | 10 | 10 | Benban - Aswan10 | 12102732.036
Benban - Aswan | 11 | 11 | Benban - Aswan11 | 2222964.1737
Benban - Aswan | 12 | 12 | Benban - Aswan12 | 16625097.353
Benban - Aswan | 13 | 13 | Benban - Aswan13 | 36700.14
Benban - Aswan | 14 | 14 | Benban - Aswan14 | 1174778.08
Benban - Aswan | 1 | 1 | Benban - Aswan1 | 24677038.56
Cement Plant | 14 | 14 | Cement Plant14 | 7309725
Cement Plant | 15 | 15 | Cement Plant15 | 6696657.1239
Cement Plant | 16 | 16 | Cement Plant16 | 6990595.3607
Cement Plant | 17 | 17 | Cement Plant17 | 7424114.8339
Cement Plant | 18 | 18 | Cement Plant18 | 6925479.9129
Cement Plant | 19 | 19 | Cement Plant19 | 12791497.7957
Cement Plant | 20 | 20 | Cement Plant20 | 10152661.36
Cement Plant -Last Claim | 3 | 3 | Cement Plant -Last Claim3 | 5224000
CFC | 1 | 1 | CFC1 | 6200445.37
CFC | 2 | 2 | CFC2 | 17105598.33
CFC | 3 | 3 | CFC3 | 12263695.26
CFC | 4 | 4 | CFC4 | 32660833.58
CFC | 5 | 5 | CFC5 | 24749111.95
CFC | 6 | 6 | CFC6 | 31500278.62
CFC | 7 | 7 | CFC7 | 19510038
CFC | 8 | 8 | CFC8 | 21459124.497
CFC | 9 | 9 | CFC9 | 24499895.82
CFC | 10 | 10 | CFC10 | 39448595.84
CFC | 11 | 11 | CFC11 | 18030565.73
CFC | 12 | 12 | CFC12 | 29691194.9757
CFC | 13 | 13 | CFC13 | 23213756.67
CFC | 14 | 14 | CFC14 | 19708943.72
CFC | 15 | 15 | CFC15 | 40379659.8985
CFC | 16 | 16 | CFC16 | 22871121.16
CFC | 17 | 17 | CFC17 | 15047803.35
CFC | 18 | 18 | CFC18 | 12196441.12
CFC | 19 | 19 | CFC19 | 14008565.7
CFC | 20 | 20 | CFC20 | 23721354.77
CFC | 21 | 21 | CFC21 | 17156725.12
CFC | 22 | 22 | CFC22 | 13410069.82
CFC | 23 | 23 | CFC23 | 15440459.23
CFC | 24 | 24 | CFC24 | 7464480.35
CFC | 25 | 25 | CFC25 | 9682524.46
CFC | 26 | 26 | CFC26 | 2397254.3033
CFC | 27 | 27 | CFC27 | 10793868.64
CFC | 28 | 28 | CFC28 | 10367935.31
CFC | 29 | 29 | CFC29 | 15034318.2703
CFC - Final Retention | 1 | 1 | CFC - Final Retention1 | 12637074.78
CFC | 1 | 1 | CFC1 | 62134944.55
CFC | 2 | 2 | CFC2 | 31067472
Comoros | 1 | 1 | Comoros1 | 3891360.8
Comoros - Off Shore | 1 | 1 | Comoros - Off Shore1 | 2555388
Comoros - Off Shore | 2 | 2 | Comoros - Off Shore2 | 910154
Comoros - On Shore | 1 | 1 | Comoros - On Shore1 | 830840.75
Comoros - On Shore | 2 | 2 | Comoros - On Shore2 | 405450.99
Comoros - On Shore | 1 | 1 | Comoros - On Shore1 | 263708.26
Creeks - URBN K | 1 | 1 | Creeks - URBN K1 | 10729515
Creeks - URBN K | 2 | 2 | Creeks - URBN K2 | 3863139
Creeks - URBN K | 3 | 3 | Creeks - URBN K3 | 21808950
Creeks - URBN K | 4 | 4 | Creeks - URBN K4 | 8830426
Creeks - URBN K | 5 | 5 | Creeks - URBN K5 | 13533059
Creeks - URBN K | 6 | 6 | Creeks - URBN K6 | 19608847
Creeks - URBN K | 7 | 7 | Creeks - URBN K7 | 16761479
Creeks - URBN K | 8 | 8 | Creeks - URBN K8 | 16707965
Creeks - URBN K | 9 | 9 | Creeks - URBN K9 | 16997068
Creeks - URBN K | 10 | 10 | Creeks - URBN K10 | 19246723
Creeks - URBN K | 11 | 11 | Creeks - URBN K11 | 11569432
Creeks - URBN K | 12 | 12 | Creeks - URBN K12 | 8618325
Creeks - URBN K | 13 | 13 | Creeks - URBN K13 | 23221916
Creeks - URBN K | 14 | 14 | Creeks - URBN K14 | 6223873.19
Creeks - URBN K | 15 | 15 | Creeks - URBN K15 | 10206848
Creeks - URBN K | 16 | 16 | Creeks - URBN K16 | 6345314
Creeks - URBN K | 17 | 17 | Creeks - URBN K17 | 8554807
Creeks - URBN K | 18 | 18 | Creeks - URBN K18 | 9363450
Damietta Port - Civil | 2 | 2 | Damietta Port - Civil2 | 1520770.91
Damietta Port - Civil | 3 | 3 | Damietta Port - Civil3 | 1496696.18
Damietta Port - Civil | 1 | 1 | Damietta Port - Civil1 | 4058690.9
Damietta Port - Infra | 1 | 1 | Damietta Port - Infra1 | 6541975.22
DP World Sokhna | 1 | 1 | DP World Sokhna1 | 15998139
DP World Sokhna | 2 | 2 | DP World Sokhna2 | 18062199.23
DP World Sokhna | 3 | 3 | DP World Sokhna3 | 15357944.03
DP World Sokhna | 4 | 4 | DP World Sokhna4 | 27940477.28
DP World Sokhna | 5 | 5 | DP World Sokhna5 | 13161622.85
DP World Sokhna | 6 | 6 | DP World Sokhna6 | 24492163.72
DP World Sokhna | 7 | 7 | DP World Sokhna7 | 29974844.16
DP World Sokhna | 8 | 8 | DP World Sokhna8 | 29128813.98
DP World Sokhna | 9 | 9 | DP World Sokhna9 | 40031882.73
DP World Sokhna | 10 | 10 | DP World Sokhna10 | 66994289.3
DP World Sokhna | 11 | 11 | DP World Sokhna11 | 76494532.33
DP World Sokhna | 12 | 12 | DP World Sokhna12 | 59999695.78
DP World Sokhna | 12.1 | 12 | DP World Sokhna12 | 49675726.5
DP World Sokhna | 13 | 13 | DP World Sokhna13 | 46089743
DP World Sokhna | 13.1 | 13 | DP World Sokhna13 | 46089743
DP World Sokhna | 14 | 14 | DP World Sokhna14 | 52189292.94
DP World Sokhna | 14.1 | 14 | DP World Sokhna14 | 52189292.94
DP World Sokhna | 15 | 15 | DP World Sokhna15 | 81940298.01
DP World Sokhna | 16 | 16 | DP World Sokhna16 | 63998840.71
DP World Sokhna | 17 | 17 | DP World Sokhna17 | 41776446.85
DP World Sokhna | 18 | 18 | DP World Sokhna18 | 44310014.32
DP World Sokhna | 19 | 19 | DP World Sokhna19 | 25431108.58
DP World Sokhna | 20 | 20 | DP World Sokhna20 | 31817254.2
DP World Sokhna | 21 | 21 | DP World Sokhna21 | 25746407.39
DP World Sokhna | 22 | 22 | DP World Sokhna22 | 17720371
DP World Sokhna | 23 | 23 | DP World Sokhna23 | 26545255.12
DP World Sokhna | 24 | 24 | DP World Sokhna24 | 20867275.72
DP World Sokhna | 25 | 25 | DP World Sokhna25 | 10313601.64
DP World Sokhna | 26 | 26 | DP World Sokhna26 | 22617919.57
DP World Sokhna | 27 | 27 | DP World Sokhna27 | 15718793.62
DP World Sokhna | 28 | 28 | DP World Sokhna28 | 19977105.85
DP World Sokhna | 29 | 29 | DP World Sokhna29 | 20394668.34
DP World Sokhna | 30 | 30 | DP World Sokhna30 | 10739490.38
DP World Sokhna | 31 | 31 | DP World Sokhna31 | 10014939.05
DP World Sokhna | 32 | 32 | DP World Sokhna32 | 12304801.83
DP World Sokhna | 33 | 33 | DP World Sokhna33 | 15048235.01
DP World Sokhna | 34 | 34 | DP World Sokhna34 | 8899770.44
DP World Sokhna | 35 | 35 | DP World Sokhna35 | 2915333
DP World Sokhna | 36 | 36 | DP World Sokhna36 | 50000000
DP World Sokhna | 36.1 | 36 | DP World Sokhna36 | 30556058.47
DP World Sokhna | 1 | 1 | DP World Sokhna1 | 241563831.68
DPW - Ph.02 | 1 | 1 | DPW - Ph.021 | 21783711.58
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 19448762.45
DPW - Ph.02 | 3 | 3 | DPW - Ph.023 | 28493360.54
DPW - Ph.02 | 4 | 4 | DPW - Ph.024 | 27398639.54
DPW - Ph.02 | 5 | 5 | DPW - Ph.025 | 30104833.54
DPW - Ph.02 | 6 | 6 | DPW - Ph.026 | 23809772.84
DPW - Ph.02 | 7 | 7 | DPW - Ph.027 | 15918348.27
DPW - Ph.02 | 8 | 8 | DPW - Ph.028 | 20524928.94
DPW - Ph.02 | 9 | 9 | DPW - Ph.029 | 49445572.72
DPW - Ph.02 | 10 | 10 | DPW - Ph.0210 | 34610141.8
DPW - Ph.02 | 11 | 11 | DPW - Ph.0211 | 40236573.85
DPW - Ph.02 | 12 | 12 | DPW - Ph.0212 | 15678173.8779
DPW - Ph.02 | 13 | 13 | DPW - Ph.0213 | 18805485.48
DPW - Ph.02 | 14 | 14 | DPW - Ph.0214 | 35568315.9
DPW - Ph.02 | 2 | 2 | DPW - Ph.022 | 63597656.14
DPW - Ph.02 | 2.1 | 2 | DPW - Ph.022 | 1460242.27
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 4836368.8
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 10019256.26
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 3347979.5
EGAT Pelletizing Plant | 3.1 | 3 | EGAT Pelletizing Plant3 | 766737.3
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 6000000
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 13990653.63
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 10253665.39
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 13147791.3
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 11455129.95
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 14888447
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 16034098.6
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 14151886.79
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 8500000
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 18397068.58
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 7794639.63
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 15000000
EGAT Pelletizing Plant | 15.1 | 15 | EGAT Pelletizing Plant15 | 4186530.1
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 13336148.65
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 19257376.65
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 10000000
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 10000000
EGAT Pelletizing Plant | 19.1 | 19 | EGAT Pelletizing Plant19 | 12197351.2
EGAT Pelletizing Plant | 20 | 20 | EGAT Pelletizing Plant20 | 1e-05
EGAT Pelletizing Plant | 21 | 21 | EGAT Pelletizing Plant21 | 1e-05
EGAT Pelletizing Plant | 22 | 22 | EGAT Pelletizing Plant22 | 1e-05
EGAT Pelletizing Plant - Supply | 1 | 1 | EGAT Pelletizing Plant - Supply1 | 1570903.44
EGAT Pelletizing Plant-Concrete Infra | 1 | 1 | EGAT Pelletizing Plant-Concrete Infra1 | 1e-05
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 10000000
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 2000000
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 5000000
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 20500000
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 28804143.3
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 100000000
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 100000000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 200000000
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 26309409.25
EGAT Pelletizing Plant-Escalation | 1 | 1 | EGAT Pelletizing Plant-Escalation1 | 7000000
EGAT Pelletizing Plant-Mechanical Installation | 1 | 1 | EGAT Pelletizing Plant-Mechanical Installation1 | 1e-05
EGAT Pelletizing Plant-MEP | 1 | 1 | EGAT Pelletizing Plant-MEP1 | 1e-05
EGAT Pelletizing Plant-MEP | 2 | 2 | EGAT Pelletizing Plant-MEP2 | 1e-05
EGAT Pelletizing Plant-MEP | 3 | 3 | EGAT Pelletizing Plant-MEP3 | 1e-05
EGAT Pelletizing Plant-MEP Coordination | 1 | 1 | EGAT Pelletizing Plant-MEP Coordination1 | 1e-05
EGAT Pelletizing Plant | 1 | 1 | EGAT Pelletizing Plant1 | 1769274.74
EGAT Pelletizing Plant | 2 | 2 | EGAT Pelletizing Plant2 | 15000000
EGAT Pelletizing Plant | 3 | 3 | EGAT Pelletizing Plant3 | 50000000
EGAT Pelletizing Plant | 4 | 4 | EGAT Pelletizing Plant4 | 23690590.75
EGAT Pelletizing Plant | 5 | 5 | EGAT Pelletizing Plant5 | 100000000
EGAT Pelletizing Plant | 6 | 6 | EGAT Pelletizing Plant6 | 50000000
EGAT Pelletizing Plant | 7 | 7 | EGAT Pelletizing Plant7 | 50000000
EGAT Pelletizing Plant | 8 | 8 | EGAT Pelletizing Plant8 | 30000000
EGAT Pelletizing Plant | 9 | 9 | EGAT Pelletizing Plant9 | 30000000
EGAT Pelletizing Plant | 10 | 10 | EGAT Pelletizing Plant10 | 25000000
EGAT Pelletizing Plant | 11 | 11 | EGAT Pelletizing Plant11 | 20000000
EGAT Pelletizing Plant | 12 | 12 | EGAT Pelletizing Plant12 | 15000000
EGAT Pelletizing Plant | 13 | 13 | EGAT Pelletizing Plant13 | 35000000
EGAT Pelletizing Plant | 14 | 14 | EGAT Pelletizing Plant14 | 10000000
EGAT Pelletizing Plant | 15 | 15 | EGAT Pelletizing Plant15 | 10000000
EGAT Pelletizing Plant | 16 | 16 | EGAT Pelletizing Plant16 | 10000000
EGAT Pelletizing Plant | 17 | 17 | EGAT Pelletizing Plant17 | 20000000
EGAT Pelletizing Plant | 18 | 18 | EGAT Pelletizing Plant18 | 25000000
EGAT Pelletizing Plant | 19 | 19 | EGAT Pelletizing Plant19 | 20000000
EGAT Pelletizing Plant | 20 | 20 | EGAT Pelletizing Plant20 | 40000000
EGAT Pelletizing Plant | 21 | 21 | EGAT Pelletizing Plant21 | 20000000
EGAT Pelletizing Plant | 22 | 22 | EGAT Pelletizing Plant22 | 50000000
EGAT Pelletizing Plant | 23 | 23 | EGAT Pelletizing Plant23 | 15000000
EGAT Pelletizing Plant | 24 | 24 | EGAT Pelletizing Plant24 | 10000000
EGAT Pelletizing Plant | 25 | 25 | EGAT Pelletizing Plant25 | 10000000
EGAT Pelletizing Plant | 26 | 26 | EGAT Pelletizing Plant26 | 15000000
EGAT Pelletizing Plant | 27 | 27 | EGAT Pelletizing Plant27 | 10000000
EGAT Pelletizing Plant | 28 | 28 | EGAT Pelletizing Plant28 | 10000000
EGAT Pelletizing Plant | 29 | 29 | EGAT Pelletizing Plant29 | 10000000
EGAT Pelletizing Plant | 30 | 30 | EGAT Pelletizing Plant30 | 15000000
EGAT Pelletizing Plant | 32 | 32 | EGAT Pelletizing Plant32 | 20000000
EGAT Pelletizing Plant | 33 | 33 | EGAT Pelletizing Plant33 | 100000000
EGAT Pelletizing Plant | 34 | 34 | EGAT Pelletizing Plant34 | 20000000
EGAT Pelletizing Plant | 35 | 35 | EGAT Pelletizing Plant35 | 15000000
EGAT Pelletizing Plant | 36 | 36 | EGAT Pelletizing Plant36 | 20000000
EGAT Pelletizing Plant | 37 | 37 | EGAT Pelletizing Plant37 | 5000000
EGAT Pelletizing Plant | 38 | 38 | EGAT Pelletizing Plant38 | 15000000
EGAT Pelletizing Plant | 39 | 39 | EGAT Pelletizing Plant39 | 25000000
EGAT Pelletizing Plant | 40 | 40 | EGAT Pelletizing Plant40 | 15000000
EGAT Pelletizing Plant | 41 | 41 | EGAT Pelletizing Plant41 | 20000000
EGAT Pelletizing Plant | 42 | 42 | EGAT Pelletizing Plant42 | 10000000
EGAT Pelletizing Plant | 43 | 43 | EGAT Pelletizing Plant43 | 35000000
EGAT Pelletizing Plant | 44 | 44 | EGAT Pelletizing Plant44 | 35000000
EGAT Pelletizing Plant | 45 | 45 | EGAT Pelletizing Plant45 | 20000000
EGAT Pelletizing Plant | 46 | 46 | EGAT Pelletizing Plant46 | 32000000
EGAT Pelletizing Plant | 47 | 47 | EGAT Pelletizing Plant47 | 10000000
EGAT Pelletizing Plant | 48 | 48 | EGAT Pelletizing Plant48 | 10000000
EGAT Pelletizing Plant | 49 | 49 | EGAT Pelletizing Plant49 | 10000000
EGAT Pelletizing Plant | 50 | 50 | EGAT Pelletizing Plant50 | 10000000
EGAT Pelletizing Plant | 51 | 51 | EGAT Pelletizing Plant51 | 10000000
EGAT Pelletizing Plant | 52 | 52 | EGAT Pelletizing Plant52 | 10000000
EGAT Pelletizing Plant | 53 | 53 | EGAT Pelletizing Plant53 | 5000000
EGAT Pelletizing Plant | 54 | 54 | EGAT Pelletizing Plant54 | 15000000
EGAT Pelletizing Plant | 55 | 55 | EGAT Pelletizing Plant55 | 7500000
EGAT Pelletizing Plant | 56 | 56 | EGAT Pelletizing Plant56 | 5000000
EGAT Pelletizing Plant-Water Tank | 1 | 1 | EGAT Pelletizing Plant-Water Tank1 | 3241734.16
EGAT Pelletizing Plant-Water Tank | 2 | 2 | EGAT Pelletizing Plant-Water Tank2 | 2008304.1
EGAT Pelletizing Plant-Water Tank | 3 | 3 | EGAT Pelletizing Plant-Water Tank3 | 718104.27
EGAT Pelletizing Plant-Water Tank | 4 | 4 | EGAT Pelletizing Plant-Water Tank4 | 758512.36
EGAT Pelletizing Plant-Water Tank | 5 | 5 | EGAT Pelletizing Plant-Water Tank5 | 914358.66
EGAT Pelletizing Plant-Water Tank | 6 | 6 | EGAT Pelletizing Plant-Water Tank6 | 1449673.43
EGAT Pelletizing Plant-Water Tank | 7 | 7 | EGAT Pelletizing Plant-Water Tank7 | 395732.02
EGAT Pelletizing Plant-Water Tank | 8 | 8 | EGAT Pelletizing Plant-Water Tank8 | 304153.94
EGAT Pelletizing Plant-Water Tank | 9 | 9 | EGAT Pelletizing Plant-Water Tank9 | 967200
EGAT Pelletizing Plant-Water Tank | 10 | 10 | EGAT Pelletizing Plant-Water Tank10 | 3505322.5
EGAT Pelletizing Plant-Water Tank | 11 | 11 | EGAT Pelletizing Plant-Water Tank11 | 3903900.34
EGAT Pelletizing Plant-Water Tank | 12 | 12 | EGAT Pelletizing Plant-Water Tank12 | 1e-05
EGAT Pelletizing Plant-Water Tank | 13 | 13 | EGAT Pelletizing Plant-Water Tank13 | 391272.95
EGAT Pelletizing Plant-Water Tank | 14 | 14 | EGAT Pelletizing Plant-Water Tank14 | 1e-05
EGAT-Asphalt | 1 | 1 | EGAT-Asphalt1 | 598688
EGAT-Asphalt - Retenion Release | 1 | 1 | EGAT-Asphalt - Retenion Release1 | 291975.34
EGAT-EGAT | 1 | 1 | EGAT-EGAT1 | 12000000
EGAT-EGAT | 2 | 2 | EGAT-EGAT2 | 6000000
EGAT-EGAT | 3 | 3 | EGAT-EGAT3 | 6000000
EGAT-EGAT | 4 | 4 | EGAT-EGAT4 | 1500000
EGAT-Fence | 1 | 1 | EGAT-Fence1 | 195752.6
EGAT-Fence | 2 | 2 | EGAT-Fence2 | 0.001
EGAT-Fence | 3 | 3 | EGAT-Fence3 | 457138.81
EGAT-Fence | 3.1 | 3 | EGAT-Fence3 | 237906.8728
EGAT-Fence | 4.1 | 4 | EGAT-Fence4 | 838441.7922
EGAT-Fence | 4.2 | 4 | EGAT-Fence4 | 1000000
EGAT-Fence | 4.3 | 4 | EGAT-Fence4 | 750000
EGAT-Fence | 4.4 | 4 | EGAT-Fence4 | 302594.27
EGAT-Fence - Retenion Release | 1 | 1 | EGAT-Fence - Retenion Release1 | 1161544.2
EGAT-Fence - Retenion Release | 1.1 | 1 | EGAT-Fence - Retenion Release1 | 1e-05
EGAT-HeliPad | 1 | 1 | EGAT-HeliPad1 | 755798.13
EGAT-HeliPad | 2 | 2 | EGAT-HeliPad2 | 500000
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 4717110.35
EGAT-Lock & Load | 2 | 2 | EGAT-Lock & Load2 | 2773213.88
EGAT-Lock & Load | 3 | 3 | EGAT-Lock & Load3 | 1665986.92
EGAT-Lock & Load | 4 | 4 | EGAT-Lock & Load4 | 747255.39
EGAT-Lock & Load | 5 | 5 | EGAT-Lock & Load5 | 2436487.51
EGAT-Lock & Load | 6 | 6 | EGAT-Lock & Load6 | 3176089.21
EGAT-Lock & Load | 7 | 7 | EGAT-Lock & Load7 | 275994.22
EGAT-Lock & Load | 7.1 | 7 | EGAT-Lock & Load7 | 1043113.27
EGAT-Lock & Load | 8 | 8 | EGAT-Lock & Load8 | 2619387.85
EGAT-Lock & Load | 9 | 9 | EGAT-Lock & Load9 | 3741613.11
EGAT-Lock & Load | 10 | 10 | EGAT-Lock & Load10 | 871396.81
EGAT-Lock & Load | 10.1 | 10 | EGAT-Lock & Load10 | 227993.12
EGAT-Lock & Load | 11 | 11 | EGAT-Lock & Load11 | 1873296.27
EGAT-Lock & Load | 12 | 12 | EGAT-Lock & Load12 | 1672142.68
EGAT-Lock & Load | 13 | 13 | EGAT-Lock & Load13 | 1e-05
EGAT-Lock & Load | 14 | 14 | EGAT-Lock & Load14 | 1e-05
EGAT-Lock & Load | 15 | 15 | EGAT-Lock & Load15 | 1e-05
EGAT-Lock & Load | 16 | 16 | EGAT-Lock & Load16 | 1e-05
EGAT-Lock & Load | 1 | 1 | EGAT-Lock & Load1 | 5400000
EGAT-SZ | 1 | 1 | EGAT-SZ1 | 4624356.65
EGAT-SZ | 2 | 2 | EGAT-SZ2 | 10000000
EGAT-SZ | 3 | 3 | EGAT-SZ3 | 6070502.71
EGAT-Warehouse | 1 | 1 | EGAT-Warehouse1 | 923651.335
EIPICO | 1 | 1 | EIPICO1 | 12050858.57
EIPICO | 2 | 2 | EIPICO2 | 13338534.97
EIPICO | 3 | 3 | EIPICO3 | 13033885
EIPICO | 4 | 4 | EIPICO4 | 7344659
EIPICO | 5 | 5 | EIPICO5 | 10064340.12
EIPICO | 6 | 6 | EIPICO6 | 5949568.74
EIPICO | 7 | 7 | EIPICO7 | 6395645.73
EIPICO | 8 | 8 | EIPICO8 | 20317361.34
EIPICO | 9 | 9 | EIPICO9 | 34650000
EIPICO | 10 | 10 | EIPICO10 | 1e-05
EIPICO | 11 | 11 | EIPICO11 | 6263190.12
EIPICO | 11.1 | 11 | EIPICO11 | 17000000
EIPICO | 12 | 12 | EIPICO12 | 25548194.95
EIPICO | 13 | 13 | EIPICO13 | 2882568.41
EIPICO | 14 | 14 | EIPICO14 | 26305980.07
EIPICO | 15 | 15 | EIPICO15 | 25000000
EIPICO | 15.1 | 15 | EIPICO15 | 4236256.89
EIPICO | 16 | 16 | EIPICO16 | 26363887.4
EIPICO | 17 | 17 | EIPICO17 | 13161378.75
EIPICO | 18 | 18 | EIPICO18 | 25000000
EIPICO | 18.1 | 18 | EIPICO18 | 10188037.3
EIPICO | 19 | 19 | EIPICO19 | 10000000
EIPICO | 19.1 | 19 | EIPICO19 | 12436578.36
EIPICO | 20 | 20 | EIPICO20 | 20000000
EIPICO | 1 | 1 | EIPICO1 | 83482074.8
EIPICO | 1 | 1 | EIPICO1 | 85000000
EIPICO | 2 | 2 | EIPICO2 | 10000000
El Sewedy Uni.-PKG.1 | 1 | 1 | El Sewedy Uni.-PKG.11 | 1917993.24
El Sewedy Uni.-PKG.1 | 2 | 2 | El Sewedy Uni.-PKG.12 | 881744.36
El Sewedy Uni.-PKG.1 | 3 | 3 | El Sewedy Uni.-PKG.13 | 1214989
El Sewedy Uni.-PKG.1 | 4 | 4 | El Sewedy Uni.-PKG.14 | 1204112.8596
El Sewedy Uni.-PKG.1 | 5 | 5 | El Sewedy Uni.-PKG.15 | 185635.0557
El Sewedy Uni.-PKG.1 | 6 | 6 | El Sewedy Uni.-PKG.16 | 142702.12
El Sewedy Uni.-PKG.1 | 7 | 7 | El Sewedy Uni.-PKG.17 | 284879.77
El Sewedy Uni.-PKG.1 | 8 | 8 | El Sewedy Uni.-PKG.18 | 235901.48
El Sewedy Uni.-PKG.1 | 9 | 9 | El Sewedy Uni.-PKG.19 | 72777.3
El Sewedy Uni.-PKG.1 | 10 | 10 | El Sewedy Uni.-PKG.110 | -8913.92
El Sewedy Uni.-PKG.11 | 1 | 1 | El Sewedy Uni.-PKG.111 | 2898141.12
El Sewedy Uni.-PKG.2 | 1 | 1 | El Sewedy Uni.-PKG.21 | 3110956.56
El Sewedy Uni.-PKG.2 | 2 | 2 | El Sewedy Uni.-PKG.22 | 6754267.57
El Sewedy Uni.-PKG.2 | 3 | 3 | El Sewedy Uni.-PKG.23 | 3212953.45
El Sewedy Uni.-PKG.2 | 4 | 4 | El Sewedy Uni.-PKG.24 | 3208255.76
El Sewedy Uni.-PKG.2 | 5 | 5 | El Sewedy Uni.-PKG.25 | 4527299.68
El Sewedy Uni.-PKG.2 | 6 | 6 | El Sewedy Uni.-PKG.26 | 7457797.24
El Sewedy Uni.-PKG.2 | 7 | 7 | El Sewedy Uni.-PKG.27 | 2278076.64
El Sewedy Uni.-PKG.2 | 8 | 8 | El Sewedy Uni.-PKG.28 | 2625161.63
El Sewedy Uni.-PKG.2 | 9 | 9 | El Sewedy Uni.-PKG.29 | 1116423
El Sewedy Uni.-PKG.22 | 1 | 1 | El Sewedy Uni.-PKG.221 | 8589000
El Sewedy Uni.-PKG.2-Social Insurrance | 1 | 1 | El Sewedy Uni.-PKG.2-Social Insurrance1 | 1120262.65
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 1727255.6
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 3185421.17
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 5785718.63
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 1785482.76
El Sewedy Uni.-PKG.3 | 5 | 5 | El Sewedy Uni.-PKG.35 | 24218860.6
El Sewedy Uni.-PKG.3 | 6 | 6 | El Sewedy Uni.-PKG.36 | 26716091.61
El Sewedy Uni.-PKG.3 | 7 | 7 | El Sewedy Uni.-PKG.37 | 17000000
El Sewedy Uni.-PKG.3 | 7.1 | 7 | El Sewedy Uni.-PKG.37 | 5410862.51
El Sewedy Uni.-PKG.3 | 8 | 8 | El Sewedy Uni.-PKG.38 | 12292368.36
El Sewedy Uni.-PKG.3 | 9 | 9 | El Sewedy Uni.-PKG.39 | 19287810.69
El Sewedy Uni.-PKG.3 | 10 | 10 | El Sewedy Uni.-PKG.310 | 20919758.8
El Sewedy Uni.-PKG.3 | 11 | 11 | El Sewedy Uni.-PKG.311 | 2318161.39
El Sewedy Uni.-PKG.3 | 12 | 12 | El Sewedy Uni.-PKG.312 | 1515470
El Sewedy Uni.-PKG.3 | 13 | 13 | El Sewedy Uni.-PKG.313 | 6845790.3
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 15000000
El Sewedy Uni.-PKG.3 | 1 | 1 | El Sewedy Uni.-PKG.31 | 24971065.75
El Sewedy Uni.-PKG.3 | 2 | 2 | El Sewedy Uni.-PKG.32 | 8000000
El Sewedy Uni.-PKG.3 | 3 | 3 | El Sewedy Uni.-PKG.33 | 12000000
El Sewedy Uni.-PKG.3 | 4 | 4 | El Sewedy Uni.-PKG.34 | 4931187
El Sewedy Uni.-PKG.3-Social Insurrance | 1 | 1 | El Sewedy Uni.-PKG.3-Social Insurrance1 | 253659.18
El Sewedy Uni.-PKG.3-Social Insurrance | 2 | 2 | El Sewedy Uni.-PKG.3-Social Insurrance2 | 267208.33
El Sewedy Uni.-PKG.3-Social Insurrance | 3 | 3 | El Sewedy Uni.-PKG.3-Social Insurrance3 | 3183056.54
El Sewedy Uni.-PKG.3-Social Insurrance | 4 | 4 | El Sewedy Uni.-PKG.3-Social Insurrance4 | 185944.54
Elco Steel | 1 | 1 | Elco Steel1 | 13532577.04
Elco Steel | 2 | 2 | Elco Steel2 | 42881105.07
Elco Steel | 3 | 3 | Elco Steel3 | 54829579.72
Elco Steel | 4 | 4 | Elco Steel4 | 35932469.35
Elco Steel | 5 | 5 | Elco Steel5 | 12038252.26
Elco Steel | 6 | 6 | Elco Steel6 | 20100303
Elco Steel | 7 | 7 | Elco Steel7 | 7919870.17
Elco Steel | 8 | 8 | Elco Steel8 | 6348055.64
Elco Steel | 9 | 9 | Elco Steel9 | 740665.09
Elco Steel | 10 | 10 | Elco Steel10 | 4000000
Elco Steel | 11 | 11 | Elco Steel11 | 7075101.66
Elco Steel | 12 | 12 | Elco Steel12 | 2485656
Elco Steel | 13 | 13 | Elco Steel13 | 2518616.18
Elco Steel | 14 | 14 | Elco Steel14 | 2857649.27
Elco Steel | 15 | 15 | Elco Steel15 | 1595365.5
Elco Steel | 16 | 16 | Elco Steel16 | 310509.31
Elco Steel | 17 | 17 | Elco Steel17 | 1079101.72
Elco Steel - ADMIN. | 1 | 1 | Elco Steel - ADMIN.1 | 1253543.1806
Elco Steel - ADMIN. | 2 | 2 | Elco Steel - ADMIN.2 | 2897721.63
Elco Steel - ADMIN. | 3 | 3 | Elco Steel - ADMIN.3 | 3188918.44
Elco Steel - ADMIN. | 4 | 4 | Elco Steel - ADMIN.4 | 3617002.31
Elco Steel - ADMIN. | 5 | 5 | Elco Steel - ADMIN.5 | 1819035.22
Elco Steel - ADMIN. | 6 | 6 | Elco Steel - ADMIN.6 | 5058047.58
Elco Steel - ADMIN. | 7 | 7 | Elco Steel - ADMIN.7 | 5750618.5816
Elco Steel - ADMIN. | 8 | 8 | Elco Steel - ADMIN.8 | 3289926.92
Elco Steel - ADMIN. | 9 | 9 | Elco Steel - ADMIN.9 | 1940428
Elco Steel - ADMIN. | 10 | 10 | Elco Steel - ADMIN.10 | 2335545.55
Elco Steel - ADMIN. | 11 | 11 | Elco Steel - ADMIN.11 | 2179703.08
Elco Steel - ADMIN. | 12 | 12 | Elco Steel - ADMIN.12 | 1394236.8
Elco Steel - ADMIN. | 13 | 13 | Elco Steel - ADMIN.13 | 117652.86
Elco Steel - ADMIN. | 14 | 14 | Elco Steel - ADMIN.14 | 105992.48
Elco Steel - ADMIN. | 15 | 15 | Elco Steel - ADMIN.15 | 259861.3
Elco Steel - MEP | 1 | 1 | Elco Steel - MEP1 | 331328.322
Elco Steel - MEP | 2 | 2 | Elco Steel - MEP2 | 2059899.63
Elco Steel - MEP | 3 | 3 | Elco Steel - MEP3 | 1986502.95
Elco Steel - MEP | 4 | 4 | Elco Steel - MEP4 | 2505278.83
Elco Steel - MEP | 5 | 5 | Elco Steel - MEP5 | 2440101.67
Elco Steel - MEP | 6 | 6 | Elco Steel - MEP6 | 2133379.76
Elco Steel - MEP | 7 | 7 | Elco Steel - MEP7 | 2606150.307
Elco Steel - MEP | 8 | 8 | Elco Steel - MEP8 | 1980608.55
Elco Steel - MEP | 9 | 9 | Elco Steel - MEP9 | 2178754.66
Elco Steel - MEP | 10 | 10 | Elco Steel - MEP10 | 2629432.67
Elco Steel - MEP | 11 | 11 | Elco Steel - MEP11 | 1720441.01
Elco Steel - MEP | 12 | 12 | Elco Steel - MEP12 | 1037321.78
Elco Steel - MEP | 13 | 13 | Elco Steel - MEP13 | 388339.4
Elco Steel - MEP | 14 | 14 | Elco Steel - MEP14 | 317040.71
Elco Steel - MEP - Social Insurance | 1 | 1 | Elco Steel - MEP - Social Insurance1 | 1700000
Elco Steel - Social Insurance | 1 | 1 | Elco Steel - Social Insurance1 | 13218500
Elco Steel - Social Insurance | 2 | 2 | Elco Steel - Social Insurance2 | 2250000
Elco Steel - Social Insurance | 3 | 3 | Elco Steel - Social Insurance3 | 1573000
Elco Steel - Social Insurance | 4 | 4 | Elco Steel - Social Insurance4 | 134252.42
Elco Steel EGAT | 1 | 1 | Elco Steel EGAT1 | 10000000
Elco Steel V.O | 1 | 1 | Elco Steel V.O1 | 4160000
Elco Steel V.O | 1 | 1 | Elco Steel V.O1 | 500000
Elco Steel V.O-Infra. Network | 1 | 1 | Elco Steel V.O-Infra. Network1 | 767138.81
Elco Steel V.O-Infra. Network | 1.1 | 1 | Elco Steel V.O-Infra. Network1 | 292861.19
El-Gouna | 1 | 1 | El-Gouna1 | 2327690.6
El-Gouna | 2 | 2 | El-Gouna2 | 3867767.27
El-Gouna | 3 | 3 | El-Gouna3 | 2286139.86
El-Gouna | 4 | 4 | El-Gouna4 | 2572404.48
El-Gouna | 5 | 5 | El-Gouna5 | 1808595.27
El-Gouna | 6 | 6 | El-Gouna6 | 4246133.4
El-Gouna | 7 | 7 | El-Gouna7 | 2145687.36
El-Gouna | 8 | 8 | El-Gouna8 | 1922134.77
El-Gouna | 9 | 9 | El-Gouna9 | 1030964.27
El-Gouna | 10 | 10 | El-Gouna10 | 1173489.52
El-Gouna | 11 | 11 | El-Gouna11 | 1750027.3
El-Gouna | 12 | 12 | El-Gouna12 | 1942857.14
El-Gouna | 13 | 13 | El-Gouna13 | 1951940.18
El-Gouna | 14 | 14 | El-Gouna14 | 3058799.81
El-Gouna | 15 | 15 | El-Gouna15 | 3002136.21
El-Gouna | 16 | 16 | El-Gouna16 | 3166964.63
El-Gouna | 17 | 17 | El-Gouna17 | 2526942.2
El-Gouna | 18 | 18 | El-Gouna18 | 5636281.25
El-Gouna | 1 | 1 | El-Gouna1 | 13625000
El-Gouna - Equip. Rental | 1 | 1 | El-Gouna - Equip. Rental1 | 73813.12
El-Gouna - Equip. Rental | 2 | 2 | El-Gouna - Equip. Rental2 | 16757
El-Gouna - Equip. Rental | 3 | 3 | El-Gouna - Equip. Rental3 | 74100
El-Gouna - Equip. Rental | 4 | 4 | El-Gouna - Equip. Rental4 | 3281.25
El-Gouna - Equip. Rental | 5 | 5 | El-Gouna - Equip. Rental5 | 15750
El-Gouna - Temp. Fence | 1 | 1 | El-Gouna - Temp. Fence1 | 425568
El-Gouna - Temp. Fence | 2 | 2 | El-Gouna - Temp. Fence2 | 441526.8
El-Gouna - Temp. Fence | 3 | 3 | El-Gouna - Temp. Fence3 | 173749.2
EUA | 1 | 1 | EUA1 | 120000000
Existing Intake Apply -SSC-Mech | 1 | 1 | Existing Intake Apply -SSC-Mech1 | 1e-05
Existing Intake Supply -SSC-Mech | 1 | 1 | Existing Intake Supply -SSC-Mech1 | 2311727.07
FIEM | 210 | 210 | FIEM210 | 1523916.51
FIEM | 211 | 211 | FIEM211 | 218510
FIEM | 212 | 212 | FIEM212 | 1205285.3
FIEM | 213 | 213 | FIEM213 | 335237.946
FIEM - Retention | 1 | 1 | FIEM - Retention1 | 286904.18
FIEM-Site Offices Rental Payment Request | 1 | 1 | FIEM-Site Offices Rental Payment Request1 | 93000
FIEM-Site Offices Rental Payment Request | 2 | 2 | FIEM-Site Offices Rental Payment Request2 | 93000
FIEM-Site Offices Rental Payment Request | 3 | 3 | FIEM-Site Offices Rental Payment Request3 | 91140
FIEM-Site Offices Rental Payment Request | 4 | 4 | FIEM-Site Offices Rental Payment Request4 | 91140
FIEM-Site Offices Rental Payment Request | 5 | 5 | FIEM-Site Offices Rental Payment Request5 | 91140
FIEM-Site Offices Rental Payment Request | 6 | 6 | FIEM-Site Offices Rental Payment Request6 | 93000
H1 Solaymaneya-MEP | 1 | 1 | H1 Solaymaneya-MEP1 | 1165148
H1 Solaymaneya-MEP | 1 | 1 | H1 Solaymaneya-MEP1 | 4000000
HQ - CFC | 1 | 1 | HQ - CFC1 | 6847513.64
HQ - CFC | 2 | 2 | HQ - CFC2 | 8021127.82
HQ - CFC | 3 | 3 | HQ - CFC3 | 8213720.11
HQ - CFC | 4 | 4 | HQ - CFC4 | 7815807.73
HQ - CFC | 5 | 5 | HQ - CFC5 | 3447418.19
HQ - CFC | 6 | 6 | HQ - CFC6 | 13157200.99
HQ - CFC | 7 | 7 | HQ - CFC7 | 14942810.84
HQ - CFC | 8 | 8 | HQ - CFC8 | 10012745.7
HQ - CFC | 9 | 9 | HQ - CFC9 | 17174919.84
HQ - CFC | 10 | 10 | HQ - CFC10 | 7981881.94
HQ - CFC | 11 | 11 | HQ - CFC11 | 27417402.1
HQ - CFC | 12 | 12 | HQ - CFC12 | 11342066.99
HQ - CFC | 13 | 13 | HQ - CFC13 | 10869511.32
HQ - CFC | 14 | 14 | HQ - CFC14 | 6179916.44
HQ - CFC | 15 | 15 | HQ - CFC15 | 10437699.8
HQ - CFC | 16 | 16 | HQ - CFC16 | 1064612.28
HQ - CFC | 17 | 17 | HQ - CFC17 | 8013147.43
HQ - CFC | 18 | 18 | HQ - CFC18 | 12964666.86
HQ - CFC | 19 | 19 | HQ - CFC19 | 2123375.29
HQ - CFC | 20 | 20 | HQ - CFC20 | 9324446.8
HQ - CFC | 21 | 21 | HQ - CFC21 | 1704646.05
HQ - CFC | 23 | 23 | HQ - CFC23 | 10000000
HQ - CFC | 24 | 24 | HQ - CFC24 | 5681250.46
HQ - CFC | 25 | 25 | HQ - CFC25 | 9125697.43
HQ - CFC | 26 | 26 | HQ - CFC26 | 10915757.94
HQ - CFC | 26.1 | 26 | HQ - CFC26 | 315339.47
HQ - CFC | 1 | 1 | HQ - CFC1 | 103231218.3
HQ - CFC - Retention release | 1 | 1 | HQ - CFC - Retention release1 | 7311955.09
HQ - CFC - Social Insurrance | 1 | 1 | HQ - CFC - Social Insurrance1 | 586840.71
HyperOne | 1 | 1 | HyperOne1 | 2499090
HyperOne | 2 | 2 | HyperOne2 | 8063620
HyperOne | 3 | 3 | HyperOne3 | 6681009
HyperOne | 4 | 4 | HyperOne4 | 6318712
HyperOne | 5 | 5 | HyperOne5 | 3307335
HyperOne | 6 | 6 | HyperOne6 | 8598544
HyperOne | 7 | 7 | HyperOne7 | 8960935
HyperOne | 8 | 8 | HyperOne8 | 3276433
HyperOne | 9 | 9 | HyperOne9 | 1277872
HyperOne | 10 | 10 | HyperOne10 | 4688664
HyperOne | 11 | 11 | HyperOne11 | 6700148
HyperOne | 12 | 12 | HyperOne12 | 1896315
HyperOne | 13 | 13 | HyperOne13 | 6738702
HyperOne | 14 | 14 | HyperOne14 | 4476191
HyperOne | 15 | 15 | HyperOne15 | 2754557
HyperOne | 1 | 1 | HyperOne1 | 33750000
HyperOne-Steel Supply | 1 | 1 | HyperOne-Steel Supply1 | 4724997
HyperOne-Steel Supply | 2 | 2 | HyperOne-Steel Supply2 | 980000
HyperOne-Steel Supply | 3 | 3 | HyperOne-Steel Supply3 | 1165162
HyperOne-Steel Supply | 4 | 4 | HyperOne-Steel Supply4 | 4993651
HyperOne-Steel Supply | 5 | 5 | HyperOne-Steel Supply5 | 305602
HyperOne-Steel Supply | 6 | 6 | HyperOne-Steel Supply6 | 3490984
HyperOne-VAT 1,2,3 | 1 | 1 | HyperOne-VAT 1,2,31 | 1171706
IKEA | 1 | 1 | IKEA1 | 4032556.9
IKEA | 2 | 2 | IKEA2 | 10633715.55
IKEA | 3 | 3 | IKEA3 | 7184168.18
IKEA | 4 | 4 | IKEA4 | 8278802.07
IKEA | 5 | 5 | IKEA5 | 7929959.808
IKEA | 6 | 6 | IKEA6 | 3899213.68
IKEA | 7 | 7 | IKEA7 | 6161858.91
IKEA | 8 | 8 | IKEA8 | 13080191.13
IKEA | 9 | 9 | IKEA9 | 21936362.84
IKEA | 10 | 10 | IKEA10 | 10981834.92
IKEA | 11 | 11 | IKEA11 | 16592416.38
IKEA | 12 | 12 | IKEA12 | 15898929.26
IKEA | 13 | 13 | IKEA13 | 5400893.31
IKEA | 14 | 14 | IKEA14 | 15116863.46
IKEA | 1 | 1 | IKEA1 | 5000000
IKEA | 2 | 2 | IKEA2 | 428986.9
IKEA | 3 | 3 | IKEA3 | 4951900.8
IKEA | 4 | 4 | IKEA4 | 2116049.37
IKEA | 5 | 5 | IKEA5 | 21562500
IKEA | 6 | 6 | IKEA6 | 1818917
IKEA | 7 | 7 | IKEA7 | 3751873.62
IKEA | 8 | 8 | IKEA8 | 525633.83
IKEA-Retention Release | 1 | 1 | IKEA-Retention Release1 | 5552983.6
JICA | 19 | 19 | JICA19 | 1141675.91
JICA | 20 | 20 | JICA20 | 413014.8
JICA-Site Offices Rental Payment Request | 1 | 1 | JICA-Site Offices Rental Payment Request1 | 75000
JICA-Site Offices Rental Payment Request | 2 | 2 | JICA-Site Offices Rental Payment Request2 | 75000
JICA-Site Offices Rental Payment Request | 3 | 3 | JICA-Site Offices Rental Payment Request3 | 75000
JICA-Site Offices Rental Payment Request | 4 | 4 | JICA-Site Offices Rental Payment Request4 | 75000
Kafr Shokr | 1 | 1 | Kafr Shokr 1 | 28845197.4
Kafr Shokr | 2 | 2 | Kafr Shokr 2 | 6242742.2
Kafr Shokr | 3 | 3 | Kafr Shokr 3 | 8372664.9
Kafr Shokr | 4 | 4 | Kafr Shokr 4 | 8190447.9
Kafr Shokr | 5 | 5 | Kafr Shokr 5 | 5371513.65
Kafr Shokr | 6 | 6 | Kafr Shokr 6 | 444257.7
Kafr Shokr | 7 | 7 | Kafr Shokr 7 | 26652960.08
Kafr Shokr | 8 | 8 | Kafr Shokr 8 | 2028646.62
Kafr Shokr | 9 | 9 | Kafr Shokr 9 | 678824.25
Kafr Shokr | 9.1 | 9 | Kafr Shokr 9 | 4133066.85
Kafr Shokr | 10 | 10 | Kafr Shokr 10 | 2390708.7
Kafr Shokr - Retention Release | 1 | 1 | Kafr Shokr - Retention Release1 | 884808.35
Katameya - Creeks | 1 | 1 | Katameya - Creeks1 | 2741191.29
Katameya - Creeks | 2 | 2 | Katameya - Creeks2 | 11302769.9409
Katameya - Creeks | 3 | 3 | Katameya - Creeks3 | 39570120.9
Katameya - Creeks | 4 | 4 | Katameya - Creeks4 | 9000000
Katameya - Creeks | 4.1 | 4 | Katameya - Creeks4 | 20688637.31
Katameya - Creeks | 5 | 5 | Katameya - Creeks5 | 40006572.36
Katameya - Creeks | 6 | 6 | Katameya - Creeks6 | 29363826.77
Katameya - Creeks | 7 | 7 | Katameya - Creeks7 | 24380443
Katameya - Creeks | 7.1 | 7 | Katameya - Creeks7 | 20000000
Katameya - Creeks | 8 | 8 | Katameya - Creeks8 | 20000000
Katameya - Creeks | 8.1 | 8 | Katameya - Creeks8 | 20343227.98
Katameya - Creeks | 9 | 9 | Katameya - Creeks9 | 20000000
Katameya - Creeks | 9.1 | 9 | Katameya - Creeks9 | 10000000
Katameya - Creeks | 9.2 | 9 | Katameya - Creeks9 | 13056438.19
Katameya - Creeks | 10 | 10 | Katameya - Creeks10 | 61159972.97
Katameya - Creeks | 11 | 11 | Katameya - Creeks11 | 43214038.28
Katameya - Creeks | 12 | 12 | Katameya - Creeks12 | 36461301.55
Katameya - Creeks | 13 | 13 | Katameya - Creeks13 | 39353596.01
Katameya - Creeks | 14 | 14 | Katameya - Creeks14 | 45904629.98
Katameya - Creeks | 15 | 15 | Katameya - Creeks15 | 49567395
Katameya - Creeks | 16 | 16 | Katameya - Creeks16 | 25000000
Katameya - Creeks | 16.1 | 16 | Katameya - Creeks16 | 19583744
Katameya - Creeks | 17 | 17 | Katameya - Creeks17 | 20000000
Katameya - Creeks | 17.1 | 17 | Katameya - Creeks17 | 16501027.74
Katameya - Creeks | 18 | 18 | Katameya - Creeks18 | 21565441.8
Katameya - Creeks | 18.1 | 18 | Katameya - Creeks18 | 20000000
Katameya - Creeks | 19 | 19 | Katameya - Creeks19 | 20000000
Katameya - Creeks | 19.1 | 19 | Katameya - Creeks19 | 16081249.47
Katameya - Creeks | 20 | 20 | Katameya - Creeks20 | 15000000
Katameya - Creeks | 20.1 | 20 | Katameya - Creeks20 | 9569045
Katameya - Creeks | 21 | 21 | Katameya - Creeks21 | 20000000
Katameya - Creeks | 21.1 | 21 | Katameya - Creeks21 | 15259435.93
Katameya - Creeks | 22 | 22 | Katameya - Creeks22 | 10000000
Katameya - Creeks | 22.1 | 22 | Katameya - Creeks22 | 21299260.01
Katameya - Creeks | 23 | 23 | Katameya - Creeks23 | 8700739.99
Katameya - Creeks | 23.1 | 23 | Katameya - Creeks23 | 21133993.08
Katameya - Creeks | 24 | 24 | Katameya - Creeks24 | 3866006.92
Katameya - Creeks | 24.1 | 24 | Katameya - Creeks24 | 34010573
Katameya - Creeks | 25 | 25 | Katameya - Creeks25 | 45191848.31
Katameya - Creeks | 26 | 26 | Katameya - Creeks26 | 30000000
Katameya - Creeks | 26.1 | 26 | Katameya - Creeks26 | 44263221
Katameya - Creeks | 27 | 27 | Katameya - Creeks27 | 35452924
Katameya - Creeks | 28 | 28 | Katameya - Creeks28 | 28650459
Katameya - Creeks | 29 | 29 | Katameya - Creeks29 | 40904481
Katameya - Creeks | 30 | 30 | Katameya - Creeks30 | 43084120
Katameya - Creeks | 31 | 31 | Katameya - Creeks31 | 37106226
Katameya - Creeks | 32 | 32 | Katameya - Creeks32 | 41216438
Katameya - Creeks | 33 | 33 | Katameya - Creeks33 | 47329833
Katameya - Creeks | 34 | 34 | Katameya - Creeks34 | 40000000
Katameya - Creeks | 34.1 | 34 | Katameya - Creeks34 | 30308953
Katameya - Creeks | 35 | 35 | Katameya - Creeks35 | 46816344
Katameya - Creeks | 36 | 36 | Katameya - Creeks36 | 33146996.78
Katameya - Creeks | 36.1 | 36 | Katameya - Creeks36 | 17383228
Katameya - Creeks | 37 | 37 | Katameya - Creeks37 | 40000000
Katameya - Creeks | 37.1 | 37 | Katameya - Creeks37 | 22109565
Katameya - Creeks | 38 | 38 | Katameya - Creeks38 | 79235150
Katameya - Creeks | 39 | 39 | Katameya - Creeks39 | 66261026
Katameya - Creeks | 40 | 40 | Katameya - Creeks40 | 30000000
Katameya - Creeks | 40.1 | 40 | Katameya - Creeks40 | 22039038
Katameya - Creeks | 41 | 41 | Katameya - Creeks41 | 24776126.81
Katameya - Creeks | 41.1 | 41 | Katameya - Creeks41 | 20564552
Katameya - Creeks | 42 | 42 | Katameya - Creeks42 | 25000000
Katameya - Creeks | 42.1 | 42 | Katameya - Creeks42 | 27791233
Katameya - Creeks | 43 | 43 | Katameya - Creeks43 | 21224102
Katameya - Creeks | 44 | 44 | Katameya - Creeks44 | 8345106.3
Katameya - Creeks | 45 | 45 | Katameya - Creeks45 | 8654893.7
Katameya - Creeks | 1 | 1 | Katameya - Creeks1 | 200000000
Katameya - Creeks - Alu Glass | 2 | 2 | Katameya - Creeks - Alu Glass2 | 10000000
Katameya - Creeks | 2 | 2 | Katameya - Creeks2 | 45000000
Katameya - Creeks | 3 | 3 | Katameya - Creeks3 | 45000000
Katameya - Creeks | 4 | 4 | Katameya - Creeks4 | 20000000
KFW | 109 | 109 | KFW109 | 128570.36
KFW | 110 | 110 | KFW110 | 377225.16
KFW-Road Signals | 1 | 1 | KFW-Road Signals 1 | 35249.2
Khatatba Bridge | 1 | 1 | Khatatba Bridge1 | 803531.75
Khatatba Bridge | 2 | 2 | Khatatba Bridge2 | 7509538.3
Khatatba Bridge | 4 | 4 | Khatatba Bridge4 | 36303482.3
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 252408.0531
KSA-Tarek AbdelHakim Center | 2 | 2 | KSA-Tarek AbdelHakim Center2 | 562894.3581
KSA-Tarek AbdelHakim Center | 3 | 3 | KSA-Tarek AbdelHakim Center3 | 194180.7389
KSA-Tarek AbdelHakim Center | 4 | 4 | KSA-Tarek AbdelHakim Center4 | 242494.97
KSA-Tarek AbdelHakim Center | 5 | 5 | KSA-Tarek AbdelHakim Center5 | 260811.86
KSA-Tarek AbdelHakim Center | 6 | 6 | KSA-Tarek AbdelHakim Center6 | 253333.77
KSA-Tarek AbdelHakim Center | 7 | 7 | KSA-Tarek AbdelHakim Center7 | 450546.16
KSA-Tarek AbdelHakim Center | 8 | 8 | KSA-Tarek AbdelHakim Center8 | 630195.46
KSA-Tarek AbdelHakim Center | 9 | 9 | KSA-Tarek AbdelHakim Center9 | 1513478.59
KSA-Tarek AbdelHakim Center | 10 | 10 | KSA-Tarek AbdelHakim Center10 | 1468894.06
KSA-Tarek AbdelHakim Center | 1 | 1 | KSA-Tarek AbdelHakim Center1 | 930841.52
LEKELA | 1 | 1 | LEKELA1 | 1670902.46
LEKELA | 2 | 2 | LEKELA2 | 1067868.0976
LEKELA | 3 | 3 | LEKELA3 | 1758948.8952
LEKELA | 4 | 4 | LEKELA4 | 652923.5
LEKELA | 5 | 5 | LEKELA5 | 7094954.7715
LEKELA | 6 | 6 | LEKELA6 | 14840272.4231
LEKELA | 7 | 7 | LEKELA7 | 15073158.35
LEKELA | 8 | 8 | LEKELA8 | 32746957.2169
LEKELA | 8.1 | 8 | LEKELA8 | 610200
LEKELA | 9 | 9 | LEKELA9 | 18594958.1925
LEKELA | 10 | 10 | LEKELA10 | 21709399.51
LEKELA | 11 | 11 | LEKELA11 | 14896483.6
LEKELA | 12 | 12 | LEKELA12 | 21477147.745
LEKELA | 13 | 13 | LEKELA13 | 2329136.4958
LEKELA | 14 | 14 | LEKELA14 | 12951636.6142
LEKELA | 15 | 15 | LEKELA15 | 203400
LEKELA | 15.1 | 15 | LEKELA15 | 406481.34
LEKELA | 15.2 | 15 | LEKELA15 | 3229199.85
LEKELA | 16 | 16 | LEKELA16 | 8212932
LEKELA - Supply Bill | 1 | 1 | LEKELA - Supply Bill1 | 124228
LEKELA- | 1 | 1 | LEKELA-1 | 3229199.85
LEKELA Remedial | 2 | 2 | LEKELA Remedial2 | 7000000.52
LEKELA Remedial | 3 | 3 | LEKELA Remedial3 | 3000357.34
LEKELA Remedial | 4 | 4 | LEKELA Remedial4 | 6400022.32
LEKELA Remedial | 1 | 1 | LEKELA Remedial1 | 6281009.56
LEKELA | 1 | 1 | LEKELA1 | 36300000
MDF Factory | 1 | 1 | MDF Factory1 | 6231879
MDF Factory | 2 | 2 | MDF Factory2 | 7093735
MDF Factory | 3 | 3 | MDF Factory3 | 8598867
MDF Factory | 4 | 4 | MDF Factory4 | 8359615
MDF Factory | 5 | 5 | MDF Factory5 | 10000000
MDF Factory | 5.1 | 5 | MDF Factory5 | 11785508.92
MDF Factory | 6 | 6 | MDF Factory6 | 10000000
MDF Factory | 6.1 | 6 | MDF Factory6 | 7171193.33
MDF Factory | 7 | 7 | MDF Factory7 | 13606480
MDF Factory | 8 | 8 | MDF Factory8 | 13352571.68
MDF Factory | 9 | 9 | MDF Factory9 | 5188292.65
MDF Factory | 10 | 10 | MDF Factory10 | 10230767.51
MDF Factory | 11 | 11 | MDF Factory11 | 8835349.23
MDF Factory | 12 | 12 | MDF Factory12 | 25380982.3
MDF Factory | 13 | 13 | MDF Factory13 | 2351273.22
MDF Factory | 14 | 14 | MDF Factory14 | 10000000
MDF Factory | 14.1 | 14 | MDF Factory14 | 1219362.36
MDF Factory | 15 | 15 | MDF Factory15 | 10000000
MDF Factory | 15.1 | 15 | MDF Factory15 | 812468.25
MDF Factory | 16 | 16 | MDF Factory16 | 10000000
MDF Factory | 16.1 | 16 | MDF Factory16 | 601848.06
MDF Factory | 17 | 17 | MDF Factory17 | 7000000
MDF Factory | 17.1 | 17 | MDF Factory17 | 6701835.53
MDF Factory | 18 | 18 | MDF Factory18 | 3474417.48
MDF Factory | 19 | 19 | MDF Factory19 | 8855940.16
MDF Factory | 20 | 20 | MDF Factory20 | 1506264.66
MDF Factory | 21 | 21 | MDF Factory21 | 10000000
MDF Factory | 21.1 | 21 | MDF Factory21 | 6783340.22
MDF Factory | 22 | 22 | MDF Factory22 | 9454487.21
MDF Factory | 23 | 23 | MDF Factory23 | 10035885.59
MDF Factory | 24 | 24 | MDF Factory24 | 5923051.17
MDF Factory | 25 | 25 | MDF Factory25 | 4519315.77
MDF Factory | 26 | 26 | MDF Factory26 | 12901160.06
MDF Factory | 27 | 27 | MDF Factory27 | 13230747.82
MDF Factory | 27.1 | 27 | MDF Factory27 | 5946852.52
MDF Factory | 28 | 28 | MDF Factory28 | 5380287.99
MDF Factory | 29 | 29 | MDF Factory29 | 10038430.32
MDF Factory | 30 | 30 | MDF Factory30 | 11530799.53
MDF Factory | 31 | 31 | MDF Factory31 | 18846610.6
MDF Factory | 32 | 32 | MDF Factory32 | 2726460
MDF Factory | 33 | 33 | MDF Factory33 | 8808260.33
MDF Factory | 34 | 34 | MDF Factory34 | 12466636.78
MDF Factory | 35 | 35 | MDF Factory35 | 11964736.84
MDF Factory | 36 | 36 | MDF Factory36 | 10194821.77
MDF Factory | 37 | 37 | MDF Factory37 | 4465149.39
MDF Factory | 38 | 38 | MDF Factory38 | 9539881.65
MDF Factory | 39 | 39 | MDF Factory39 | 6984174.92
MDF Factory | 40 | 40 | MDF Factory40 | 13054639.6
MDF Factory | 41 | 41 | MDF Factory41 | 8347962.7
MDF Factory | 42 | 42 | MDF Factory42 | 3999590
MDF Factory | 42.1 | 42 | MDF Factory42 | 3602411.04
MDF Factory | 43 | 43 | MDF Factory43 | 44999590
MDF Factory | 43.1 | 43 | MDF Factory43 | 999590
MDF Factory - Equip. | 1 | 1 | MDF Factory - Equip.1 | 479255
MDF Factory - Equip. | 2 | 2 | MDF Factory - Equip.2 | 2957905.39
MDF Factory - Equip. | 3 | 3 | MDF Factory - Equip.3 | 2467707.5
MDF Factory - Equip. | 4 | 4 | MDF Factory - Equip.4 | 2118826
MDF Factory - Equip. | 5 | 5 | MDF Factory - Equip.5 | 2067056
MDF Factory - Equip. | 6 | 6 | MDF Factory - Equip.6 | 569764
MDF Factory - Equip. | 7 | 7 | MDF Factory - Equip.7 | 795032
MDF Factory - Equip. | 8 | 8 | MDF Factory - Equip.8 | 322760
MDF Factory - Equip. | 9 | 9 | MDF Factory - Equip.9 | 1546900
MDF Factory - Equip. | 10 | 10 | MDF Factory - Equip.10 | 362327.85
MDF Factory - Equip. | 11 | 11 | MDF Factory - Equip.11 | 115740.16
MDF Factory - Equip. | 12 | 12 | MDF Factory - Equip.12 | 617997.99
MDF Factory - Equip. | 13 | 13 | MDF Factory - Equip.13 | 1033353.65
MDF Factory - Equip. | 14 | 14 | MDF Factory - Equip.14 | 1342515
MDF Factory - Equip. | 15 | 15 | MDF Factory - Equip.15 | 1508230
MDF Factory - Equip. | 16 | 16 | MDF Factory - Equip.16 | 963455.46
MDF Factory - Equip. | 17 | 17 | MDF Factory - Equip.17 | 359356.67
MDF Factory - Equip. | 18 | 18 | MDF Factory - Equip.18 | 536737.62
MDF Factory - Equip. | 19 | 19 | MDF Factory - Equip.19 | 1190791
MDF Factory - Equip. | 20 | 20 | MDF Factory - Equip.20 | 606416.12
MDF Factory - Equip. | 21 | 21 | MDF Factory - Equip.21 | 600370.17
MDF Factory - Equip. | 22 | 22 | MDF Factory - Equip.22 | 205199.38
MDF Factory - Equip. | 23 | 23 | MDF Factory - Equip.23 | 545334.31
MDF Factory - Equip. | 24 | 24 | MDF Factory - Equip.24 | 345289.58
MDF Factory - Equip. | 25 | 25 | MDF Factory - Equip.25 | 637190.72
MDF Factory - Local Fabrication | 1 | 1 | MDF Factory - Local Fabrication1 | 920351.25
MDF Factory - Local Fabrication | 2 | 2 | MDF Factory - Local Fabrication2 | 711105.4
MDF Factory - Local Fabrication | 3 | 3 | MDF Factory - Local Fabrication3 | 897908
MDF Factory - Local Fabrication | 4 | 4 | MDF Factory - Local Fabrication4 | 667444
MDF Factory - Local Fabrication | 5 | 5 | MDF Factory - Local Fabrication5 | 2517907.41
MDF Factory - Local Fabrication | 6 | 6 | MDF Factory - Local Fabrication6 | 737043.71
MDF Factory - Local Fabrication | 7 | 7 | MDF Factory - Local Fabrication7 | 785269
MDF Factory - Local Fabrication | 8 | 8 | MDF Factory - Local Fabrication8 | 381060.37
MDF Factory - Local Fabrication | 9 | 9 | MDF Factory - Local Fabrication9 | 1752018.76
MDF Factory - Local Fabrication | 10 | 10 | MDF Factory - Local Fabrication10 | 2881529.05
MDF Factory - Local Fabrication | 11 | 11 | MDF Factory - Local Fabrication11 | 2412700.43
MDF Factory - Local Fabrication | 14 | 14 | MDF Factory - Local Fabrication14 | 10315795
MDF Factory - Local Fabrication | 15 | 15 | MDF Factory - Local Fabrication15 | 2970230
MDF Factory - Local Fabrication | 16 | 16 | MDF Factory - Local Fabrication16 | 1262500
MDF Factory - Local Fabrication | 18 | 18 | MDF Factory - Local Fabrication18 | 4265111
MDF Factory - Local Fabrication | 19 | 19 | MDF Factory - Local Fabrication19 | 3358613
MDF Factory | 1 | 1 | MDF Factory1 | 41622365.4
MDF Factory | 2 | 2 | MDF Factory2 | 6300000
MDF Factory | 3 | 3 | MDF Factory3 | 2000000
MDF Factory | 4 | 4 | MDF Factory4 | 2000000
MDF Factory | 5 | 5 | MDF Factory5 | 10016624.86
MDF Factory | 6 | 6 | MDF Factory6 | 7332000
MDF Factory | 7 | 7 | MDF Factory7 | 6000000
MDF Factory | 8 | 8 | MDF Factory8 | 11000000
MDF Factory | 9 | 9 | MDF Factory9 | 13754630
MDF Factory | 10 | 10 | MDF Factory10 | 1488562.75
MDF Factory | 11 | 11 | MDF Factory11 | 3000000
MDF Factory-F.F V.O | 1 | 1 | MDF Factory-F.F V.O1 | 8500000
MDF Factory-F.F V.O | 2 | 2 | MDF Factory-F.F V.O2 | 7800000
MDF Factory-Hold Amount release | 1 | 1 | MDF Factory-Hold Amount release1 | 2000000
MDF Factory-Local Fab. | 1 | 1 | MDF Factory-Local Fab.1 | 3500000
MDF Factory | 3 | 3 | MDF Factory3 | 7811797.56
MDF Factory | 4 | 4 | MDF Factory4 | 9000000
MDF Factory | 5 | 5 | MDF Factory5 | 7000000
MDF Factory | 6 | 6 | MDF Factory6 | 4000000
MDF Factory | 7 | 7 | MDF Factory7 | 40000000
MDF Factory | 8 | 8 | MDF Factory8 | 5000000
MDF Factory solera | 1 | 1 | MDF Factory solera1 | 8000000
MDF Factory solera | 2 | 2 | MDF Factory solera2 | 18121000
MDF Factory solera | 3 | 3 | MDF Factory solera3 | 7600000
MDF Factory-P.O | 3 | 3 | MDF Factory-P.O3 | 23100000
Mechanical Installation | 1 | 1 | Mechanical Installation1 | 15000000
Mintra | 1 | 1 | Mintra1 | 5500000
Mintra | 2 | 2 | Mintra2 | 3000000
Mintra | 3 | 3 | Mintra3 | 2220782.14
Mintra | 4 | 4 | Mintra4 | 3500000
Mintra | 5 | 5 | Mintra5 | 8000000
Mintra | 6 | 6 | Mintra6 | 6000000
Mintra | 7 | 7 | Mintra7 | 2005948.91
Mintra | 1 | 1 | Mintra1 | 10000000
Mintra-Hanger 1200m2 | 1 | 1 | Mintra-Hanger 1200m21 | 531998.67
Mintra-Hanger 1200m2 | 2 | 2 | Mintra-Hanger 1200m22 | -6217.18
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 2533668.0255
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 2620895.13
Mivida-PK#140 | 3 | 3 | Mivida-PK#1403 | 4070832.3885
Mivida-PK#140 | 4 | 4 | Mivida-PK#1404 | 999645.4398
Mivida-PK#140 | 5 | 5 | Mivida-PK#1405 | 1337507.07
Mivida-PK#140 | 6 | 6 | Mivida-PK#1406 | 10719905.22
Mivida-PK#140 | 7 | 7 | Mivida-PK#1407 | 6547225.82
Mivida-PK#140 | 8 | 8 | Mivida-PK#1408 | 4740517.5525
Mivida-PK#140 | 9 | 9 | Mivida-PK#1409 | 4559999.09
Mivida-PK#140 | 10 | 10 | Mivida-PK#14010 | 5679423.0614
Mivida-PK#140 | 11 | 11 | Mivida-PK#14011 | 2647674.17
Mivida-PK#140 | 12 | 12 | Mivida-PK#14012 | 4687303.44
Mivida-PK#140 | 13 | 13 | Mivida-PK#14013 | 1169770.65
Mivida-PK#140 | 14 | 14 | Mivida-PK#14014 | 7336701.1
Mivida-PK#140 | 15 | 15 | Mivida-PK#14015 | 10305723.52
Mivida-PK#140 | 16 | 16 | Mivida-PK#14016 | 10553431.24
Mivida-PK#140 | 17 | 17 | Mivida-PK#14017 | 11726998.43
Mivida-PK#140 | 18 | 18 | Mivida-PK#14018 | 3831058.93
Mivida-PK#140 | 19 | 19 | Mivida-PK#14019 | 8885358.62
Mivida-PK#140 | 20 | 20 | Mivida-PK#14020 | 5084359.83
Mivida-PK#140 | 21 | 21 | Mivida-PK#14021 | 8185193.83
Mivida-PK#140 | 22 | 22 | Mivida-PK#14022 | 4603109.14
Mivida-PK#140 | 23 | 23 | Mivida-PK#14023 | 3870461.7
Mivida-PK#140 | 24 | 24 | Mivida-PK#14024 | 3732732.7981
Mivida-PK#140 | 25 | 25 | Mivida-PK#14025 | 9016182.24
Mivida-PK#140 | 26 | 26 | Mivida-PK#14026 | 3143991.8
Mivida-PK#140 | 27 | 27 | Mivida-PK#14027 | 5157960.04
Mivida-PK#140- Social Insurance | 1 | 1 | Mivida-PK#140- Social Insurance1 | 509706.15
Mivida-PK#140- Social Insurance | 2 | 2 | Mivida-PK#140- Social Insurance2 | 1677431
Mivida-PK#140- Social Insurance | 3 | 3 | Mivida-PK#140- Social Insurance3 | 596538.75
Mivida-PK#140- Social Insurance | 4 | 4 | Mivida-PK#140- Social Insurance4 | 908034.47
Mivida-PK#140- Social Insurance | 5 | 5 | Mivida-PK#140- Social Insurance5 | 1805452.05
Mivida-PK#140- Social Insurance | 6 | 6 | Mivida-PK#140- Social Insurance6 | 976304.25
Mivida-PK#140- Social Insurance | 7 | 7 | Mivida-PK#140- Social Insurance7 | 871421.04
Mivida-PK#140- Social Insurance | 8 | 8 | Mivida-PK#140- Social Insurance8 | 1298461.89
Mivida-PK#140- Social Insurance | 9 | 9 | Mivida-PK#140- Social Insurance9 | 494886.87
Mivida-PK#140 | 1 | 1 | Mivida-PK#1401 | 15567604.3
Mivida-PK#140 | 2 | 2 | Mivida-PK#1402 | 7313962.6
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 18095262.89
Mivida-PK#189 | 2 | 2 | Mivida-PK#1892 | 22529255.88
Mivida-PK#189 | 3 | 3 | Mivida-PK#1893 | 19800407.88
Mivida-PK#189 | 4 | 4 | Mivida-PK#1894 | 27644756.83
Mivida-PK#189 | 5 | 5 | Mivida-PK#1895 | 46638711.45
Mivida-PK#189 | 6 | 6 | Mivida-PK#1896 | 70000000
Mivida-PK#189 | 7 | 7 | Mivida-PK#1897 | 38664242.89
Mivida-PK#189 | 8 | 8 | Mivida-PK#1898 | 62566272.8
Mivida-PK#189 | 9 | 9 | Mivida-PK#1899 | 37089198
Mivida-PK#189 | 10 | 10 | Mivida-PK#18910 | 22123110.41
Mivida-PK#189 | 11 | 11 | Mivida-PK#18911 | 18794302.39
Mivida-PK#189 | 12 | 12 | Mivida-PK#18912 | 16890748.06
Mivida-PK#189 | 13 | 13 | Mivida-PK#18913 | 50032149.11
Mivida-PK#189 | 14 | 14 | Mivida-PK#18914 | 22045664.4
Mivida-PK#189 | 15 | 15 | Mivida-PK#18915 | 20013901.02
Mivida-PK#189 | 16 | 16 | Mivida-PK#18916 | 22512171.88
Mivida-PK#189 | 17 | 17 | Mivida-PK#18917 | 47104890.0563
Mivida-PK#189 | 18 | 18 | Mivida-PK#18918 | 20024965.62
Mivida-PK#189 | 19 | 19 | Mivida-PK#18919 | 23323710.11
Mivida-PK#189 | 21 | 21 | Mivida-PK#18921 | 14476604.63
Mivida-PK#189 | 22 | 22 | Mivida-PK#18922 | 17552608.99
Mivida-PK#189 | 23 | 23 | Mivida-PK#18923 | 14242173.09
Mivida-PK#189 | 24 | 24 | Mivida-PK#18924 | 13803484.92
Mivida-PK#189 | 25 | 25 | Mivida-PK#18925 | 28360739.45
Mivida-PK#189 | 26 | 26 | Mivida-PK#18926 | 14177811.26
Mivida-PK#189 | 27 | 27 | Mivida-PK#18927 | 4389859.04
Mivida-PK#189 | 28 | 28 | Mivida-PK#18928 | 2409288.21
Mivida-PK#189 | 29 | 29 | Mivida-PK#18929 | 2690517.47
Mivida-PK#189 | 30 | 30 | Mivida-PK#18930 | 14412191.12
Mivida-PK#189 | 20 | 20 | Mivida-PK#18920 | 135145955
Mivida-PK#189 - Social insurance | 1 | 1 | Mivida-PK#189 - Social insurance1 | 5182786.9
Mivida-PK#189 | 1 | 1 | Mivida-PK#1891 | 99600000
MOC | 1 | 1 | MOC1 | 33350000
New Gas Station | 1 | 1 | New Gas Station1 | 2201210.4
New Gas Station | 2 | 2 | New Gas Station2 | 1419355.25
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 23161171
New Giza Hospital | 2 | 2 | New Giza Hospital2 | 13964209
New Giza Hospital | 3 | 3 | New Giza Hospital3 | 7088017
New Giza Hospital | 4 | 4 | New Giza Hospital4 | 25531752
New Giza Hospital | 5 | 5 | New Giza Hospital5 | 9692684
New Giza Hospital | 6 | 6 | New Giza Hospital6 | 12645886
New Giza Hospital | 7 | 7 | New Giza Hospital7 | 12694720
New Giza Hospital | 8 | 8 | New Giza Hospital8 | 11865059
New Giza Hospital | 9 | 9 | New Giza Hospital9 | 15594713
New Giza Hospital | 10 | 10 | New Giza Hospital10 | 14931468
New Giza Hospital | 11 | 11 | New Giza Hospital11 | 19979218
New Giza Hospital | 12 | 12 | New Giza Hospital12 | 21023839
New Giza Hospital | 13 | 13 | New Giza Hospital13 | 17903308
New Giza Hospital | 14 | 14 | New Giza Hospital14 | 15197022
New Giza Hospital | 15 | 15 | New Giza Hospital15 | 7535461
New Giza Hospital | 16 | 16 | New Giza Hospital16 | 7643976
New Giza Hospital | 18 | 18 | New Giza Hospital18 | 14511461
New Giza Hospital | 19 | 19 | New Giza Hospital19 | 3705542
New Giza Hospital | 20 | 20 | New Giza Hospital20 | 18995740
New Giza Hospital | 21 | 21 | New Giza Hospital21 | 4008305
New Giza Hospital | 22 | 22 | New Giza Hospital22 | 6681249
New Giza Hospital | 23 | 23 | New Giza Hospital23 | 3104562
New Giza Hospital | 24 | 24 | New Giza Hospital24 | 4494905.88
New Giza Hospital | 25 | 25 | New Giza Hospital25 | 10195246
New Giza Hospital | 26 | 26 | New Giza Hospital26 | 2983818.1724
New Giza Hospital | 26.1 | 26 | New Giza Hospital26 | 15145301
New Giza Hospital | 27 | 27 | New Giza Hospital27 | 2051894
New Giza Hospital | 28 | 28 | New Giza Hospital28 | 5534314
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 73512565
New Giza Hospital | 1 | 1 | New Giza Hospital1 | 15000000
New Giza Hospital | 2 | 2 | New Giza Hospital2 | 2983818.1724
New Giza Hospital-Social Insurance | 1 | 1 | New Giza Hospital-Social Insurance1 | 3128055
New Giza Hospital-Social Insurance | 2 | 2 | New Giza Hospital-Social Insurance2 | 4605279
New Giza Hospital-Social Insurance | 3 | 3 | New Giza Hospital-Social Insurance3 | 2326029.9476
New Giza Hospital-Social Insurance | 4 | 4 | New Giza Hospital-Social Insurance4 | 1019222
NGU 2 | 25 | 25 | NGU 225 | 2468493.7
NGU 2 | 26 | 26 | NGU 226 | 4990186
NGU 2 | 27 | 27 | NGU 227 | 2104161
NGU 2 - Retension release | 1 | 1 | NGU 2 - Retension release1 | 313708
Old H1 remaining IPC | 1 | 1 | Old H1 remaining IPC1 | 250000
ORA - ZED | 1 | 1 | ORA - ZED1 | 9787286.79
ORA - ZED | 2 | 2 | ORA - ZED2 | 37532508
ORA - ZED | 3 | 3 | ORA - ZED3 | 27896354
ORA - ZED | 4 | 4 | ORA - ZED4 | 20888247.393
ORA - ZED | 5 | 5 | ORA - ZED5 | 33744386.154
ORA - ZED | 6 | 6 | ORA - ZED6 | 4374377.19
ORA - ZED | 7 | 7 | ORA - ZED7 | 5782895.78
ORA - ZED | 8 | 8 | ORA - ZED8 | 24387331.1
ORA - ZED | 9 | 9 | ORA - ZED9 | 22624923.97
ORA - ZED | 10 | 10 | ORA - ZED10 | 29047725.55
ORA - ZED | 20.1 | 20 | ORA - ZED20 | 16483569.19
ORA - ZED | 21 | 21 | ORA - ZED21 | 7443623.53
ORA - ZED | 22 | 22 | ORA - ZED22 | 8098825.75
ORA - ZED | 23 | 23 | ORA - ZED23 | 20215840.09
ORA - ZED | 24 | 24 | ORA - ZED24 | 6648903.39
ORA - ZED | 25 | 25 | ORA - ZED25 | 2e-05
ORA - ZED | 26 | 26 | ORA - ZED26 | 6863669.19
ORA - ZED | 26.1 | 26 | ORA - ZED26 | 1824548.9
ORA - ZED | 26.2 | 26 | ORA - ZED26 | 1119976.03
ORA - ZED | 27 | 27 | ORA - ZED27 | 8872947.14
ORA - ZED | 28 | 28 | ORA - ZED28 | 9105384.7
ORA - ZED | 29 | 29 | ORA - ZED29 | 10687601.99
ORA - ZED | 30 | 30 | ORA - ZED30 | 11585957.67
ORA - ZED | 31 | 31 | ORA - ZED31 | 5000000
ORA - ZED | 31.1 | 31 | ORA - ZED31 | 5253641.2
ORA - ZED | 32 | 32 | ORA - ZED32 | 8010573.17
ORA - ZED | 33 | 33 | ORA - ZED33 | 12164893.39
ORA - ZED | 34 | 34 | ORA - ZED34 | 9568963.5
ORA - ZED | 35 | 35 | ORA - ZED35 | 7391485.26
ORA - ZED | 36 | 36 | ORA - ZED36 | 7054023.71
ORA - ZED | 37 | 37 | ORA - ZED37 | 23554316.1
ORA - ZED | 38 | 38 | ORA - ZED38 | 17627053.17
ORA - ZED | 39 | 39 | ORA - ZED39 | 7606231.63
ORA - ZED | 40 | 40 | ORA - ZED40 | 3717952.37
ORA - ZED | 41 | 41 | ORA - ZED41 | 4428778.21
ORA - ZED | 42 | 42 | ORA - ZED42 | 70851.77
ORA - ZED | 43 | 43 | ORA - ZED43 | 6004454.53
ORA - ZED - Compansation | 1 | 1 | ORA - ZED - Compansation1 | 12000000
ORA - ZED | 1 | 1 | ORA - ZED1 | 91380773
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 2167633.67
ORA - ZED - Landscape | 2 | 2 | ORA - ZED - Landscape2 | 1719649.2
ORA - ZED - Landscape | 3 | 3 | ORA - ZED - Landscape3 | 1775205.58
ORA - ZED - Landscape | 4 | 4 | ORA - ZED - Landscape4 | 4074938.81
ORA - ZED - Landscape | 5 | 5 | ORA - ZED - Landscape5 | 2726488.3
ORA - ZED - Landscape | 6 | 6 | ORA - ZED - Landscape6 | 3120690.89
ORA - ZED - Landscape | 7 | 7 | ORA - ZED - Landscape7 | 964764.3
ORA - ZED - Landscape | 8 | 8 | ORA - ZED - Landscape8 | 5158038.94
ORA - ZED - Landscape | 9 | 9 | ORA - ZED - Landscape9 | 3636861
ORA - ZED - Landscape | 9.1 | 9 | ORA - ZED - Landscape9 | 226226.97
ORA - ZED - Landscape | 10 | 10 | ORA - ZED - Landscape10 | 6562980.72
ORA - ZED - Landscape | 11 | 11 | ORA - ZED - Landscape11 | 5312426.17
ORA - ZED - Landscape | 12 | 12 | ORA - ZED - Landscape12 | 6030251.47
ORA - ZED - Landscape | 14 | 14 | ORA - ZED - Landscape14 | 868255.79
ORA - ZED - Landscape | 15 | 15 | ORA - ZED - Landscape15 | 3165189.2
ORA - ZED - Landscape | 16 | 16 | ORA - ZED - Landscape16 | 1521916.47
ORA - ZED - Landscape | 17 | 17 | ORA - ZED - Landscape17 | 1313619.66
ORA - ZED - Landscape | 18 | 18 | ORA - ZED - Landscape18 | 975356.43
ORA - ZED - Landscape | 19 | 19 | ORA - ZED - Landscape19 | 618692.48
ORA - ZED - Landscape | 20 | 20 | ORA - ZED - Landscape20 | 1177303.85
ORA - ZED - Landscape | 21 | 21 | ORA - ZED - Landscape21 | 108767.39
ORA - ZED - Landscape | 1 | 1 | ORA - ZED - Landscape1 | 9635108.4
ORA - ZED | 2 | 2 | ORA - ZED2 | 256451321
ORA - ZED | 3 | 3 | ORA - ZED3 | 50172571.863
ORA - ZED | 4 | 4 | ORA - ZED4 | 25000000
ORA - ZED | 5 | 5 | ORA - ZED5 | 50000000
ORA - ZED | 6 | 6 | ORA - ZED6 | 10000000
ORA - ZED | 7 | 7 | ORA - ZED7 | 5000000
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 14536704.19
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 20471935.63
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 9325142.71
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 28728856.89
ORA - ZED - ph.02 | 5 | 5 | ORA - ZED - ph.025 | 12407121.98
ORA - ZED - ph.02 | 6 | 6 | ORA - ZED - ph.026 | 16610991.38
ORA - ZED - ph.02 | 7 | 7 | ORA - ZED - ph.027 | 8000000
ORA - ZED - ph.02 | 7.1 | 7 | ORA - ZED - ph.027 | 16000000
ORA - ZED - ph.02 | 7.2 | 7 | ORA - ZED - ph.027 | 8100387.28
ORA - ZED - ph.02 | 8 | 8 | ORA - ZED - ph.028 | 8595540.37
ORA - ZED - ph.02 | 9 | 9 | ORA - ZED - ph.029 | 7163536.59
ORA - ZED - ph.02 | 10 | 10 | ORA - ZED - ph.0210 | 20828447.26
ORA - ZED - ph.02 | 11 | 11 | ORA - ZED - ph.0211 | 12170282.5
ORA - ZED - ph.02 | 12 | 12 | ORA - ZED - ph.0212 | 14759397.95
ORA - ZED - ph.02 | 13 | 13 | ORA - ZED - ph.0213 | 13268244.56
ORA - ZED - ph.02 | 14 | 14 | ORA - ZED - ph.0214 | 15256729.38
ORA - ZED - ph.02 | 15 | 15 | ORA - ZED - ph.0215 | 11384143.67
ORA - ZED - ph.02 | 16 | 16 | ORA - ZED - ph.0216 | 9858410.94
ORA - ZED - ph.02 | 17 | 17 | ORA - ZED - ph.0217 | 8988166.12
ORA - ZED - ph.02 | 18 | 18 | ORA - ZED - ph.0218 | 13223027.75
ORA - ZED - ph.02 | 19 | 19 | ORA - ZED - ph.0219 | 6921352.11
ORA - ZED - ph.02 | 20 | 20 | ORA - ZED - ph.0220 | 3038540.29
ORA - ZED - ph.02 | 21 | 21 | ORA - ZED - ph.0221 | 4532160.06
ORA - ZED - ph.02 | 22 | 22 | ORA - ZED - ph.0222 | 8297638.82
ORA - ZED - ph.02 | 23 | 23 | ORA - ZED - ph.0223 | 564270
ORA - ZED - ph.02 | 24 | 24 | ORA - ZED - ph.0224 | 1374587.38
ORA - ZED - ph.02 | 25 | 25 | ORA - ZED - ph.0225 | 996461.29
ORA - ZED - ph.02 | 26 | 26 | ORA - ZED - ph.0226 | 2944524.93
ORA - ZED - ph.02 | 27 | 27 | ORA - ZED - ph.0227 | 5268993.93
ORA - ZED - ph.02 | 28 | 28 | ORA - ZED - ph.0228 | 1922751.71
ORA - ZED - ph.02 | 29 | 29 | ORA - ZED - ph.0229 | 5009481.72
ORA - ZED - ph.02 | 30 | 30 | ORA - ZED - ph.0230 | 73017
ORA - ZED - ph.02 | 31 | 31 | ORA - ZED - ph.0231 | 3717995
ORA - ZED - ph.02 | 32 | 32 | ORA - ZED - ph.0232 | 2836390.67
ORA - ZED - ph.02 | 33 | 33 | ORA - ZED - ph.0233 | 1e-05
ORA - ZED - ph.02 | 34 | 34 | ORA - ZED - ph.0234 | 1e-05
ORA - ZED - ph.02 | 35 | 35 | ORA - ZED - ph.0235 | 1e-05
ORA - ZED - ph.02 | 36 | 36 | ORA - ZED - ph.0236 | 4160916.8
ORA - ZED - ph.02 | 37 | 37 | ORA - ZED - ph.0237 | 8601492.56
ORA - ZED - ph.02 | 38 | 38 | ORA - ZED - ph.0238 | 3811960.86
ORA - ZED - ph.02 - Claims | 1 | 1 | ORA - ZED - ph.02 - Claims1 | 25000000
ORA - ZED - ph.02 - Claims | 2 | 2 | ORA - ZED - ph.02 - Claims2 | 12500000
ORA - ZED - ph.02 | 1 | 1 | ORA - ZED - ph.021 | 25000000
ORA - ZED - ph.02 | 2 | 2 | ORA - ZED - ph.022 | 15000000
ORA - ZED - ph.02 | 3 | 3 | ORA - ZED - ph.023 | 3000000
ORA - ZED - ph.02 | 4 | 4 | ORA - ZED - ph.024 | 26000000
ORA - ZED - Social Insurrance | 1 | 1 | ORA - ZED - Social Insurrance1 | 4101935.6
PH.2-El Sewedy Uni. - Enabling | 1 | 1 | PH.2-El Sewedy Uni. - Enabling1 | 2832501.18
PH.2-El Sewedy Uni. - Enabling | 2 | 2 | PH.2-El Sewedy Uni. - Enabling2 | 13318143.89
PH.2-El Sewedy Uni. - Enabling | 3 | 3 | PH.2-El Sewedy Uni. - Enabling3 | 17089175.5
PH.2-El Sewedy Uni. - Enabling | 4 | 4 | PH.2-El Sewedy Uni. - Enabling4 | 14773850.81
PH.2-El Sewedy Uni. - Enabling | 5 | 5 | PH.2-El Sewedy Uni. - Enabling5 | 2392694.9
PH.2-El Sewedy Uni. - Enabling | 6 | 6 | PH.2-El Sewedy Uni. - Enabling6 | 7788095.22
PH.2-El Sewedy Uni. - Enabling | 7 | 7 | PH.2-El Sewedy Uni. - Enabling7 | 3548357.43
PH.2-El Sewedy Uni. - Enabling | 8 | 8 | PH.2-El Sewedy Uni. - Enabling8 | 1607563.1
PH.2-El Sewedy Uni. - Enabling | 9 | 9 | PH.2-El Sewedy Uni. - Enabling9 | 8739144.88
PH.2-El Sewedy Uni. - Enabling | 10 | 10 | PH.2-El Sewedy Uni. - Enabling10 | 7703511.41
PH.2-El Sewedy Uni. - Enabling - Retention release | 1 | 1 | PH.2-El Sewedy Uni. - Enabling - Retention release1 | 2972186.2
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 15636298.9
PH.2-El Sewedy Uni. - Finishes | 1.1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 20000000
PH.2-El Sewedy Uni. - Finishes | 2 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 5698476.15
PH.2-El Sewedy Uni. - Finishes | 2.1 | 2 | PH.2-El Sewedy Uni. - Finishes2 | 21059913.65
PH.2-El Sewedy Uni. - Finishes | 3 | 3 | PH.2-El Sewedy Uni. - Finishes3 | 23262698.8
PH.2-El Sewedy Uni. - Finishes | 4 | 4 | PH.2-El Sewedy Uni. - Finishes4 | 18322600.95
PH.2-El Sewedy Uni. - Finishes | 5 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 10000000
PH.2-El Sewedy Uni. - Finishes | 5.1 | 5 | PH.2-El Sewedy Uni. - Finishes5 | 54006362.98
PH.2-El Sewedy Uni. - Finishes | 6 | 6 | PH.2-El Sewedy Uni. - Finishes6 | 8883254.07
PH.2-El Sewedy Uni. - Finishes | 7 | 7 | PH.2-El Sewedy Uni. - Finishes7 | 25755604.75
PH.2-El Sewedy Uni. - Finishes | 8 | 8 | PH.2-El Sewedy Uni. - Finishes8 | 25127325.53
PH.2-El Sewedy Uni. - Finishes | 9 | 9 | PH.2-El Sewedy Uni. - Finishes9 | 20493846.09
PH.2-El Sewedy Uni. - Finishes | 10 | 10 | PH.2-El Sewedy Uni. - Finishes10 | 9765894.8
PH.2-El Sewedy Uni. - Finishes | 11 | 11 | PH.2-El Sewedy Uni. - Finishes11 | 13851401.63
PH.2-El Sewedy Uni. - Finishes | 12 | 12 | PH.2-El Sewedy Uni. - Finishes12 | 23340124.9
PH.2-El Sewedy Uni. - Finishes | 13 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 10000000
PH.2-El Sewedy Uni. - Finishes | 13.1 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 5069000
PH.2-El Sewedy Uni. - Finishes | 13.2 | 13 | PH.2-El Sewedy Uni. - Finishes13 | 1e-06
PH.2-El Sewedy Uni. - Finishes | 1 | 1 | PH.2-El Sewedy Uni. - Finishes1 | 15000000
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 1 | 1 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance1 | 1023770.56
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 2 | 2 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance2 | 9146959.2
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | 3 | 3 | PH.2-El Sewedy Uni. - Finishes-Social Insurrance3 | 11400000
PH.2-El Sewedy Uni. | 1 | 1 | PH.2-El Sewedy Uni.1 | 31397824
PH.2-El Sewedy Uni. | 2 | 2 | PH.2-El Sewedy Uni.2 | 71347886
PI Parks - ELSEWEDY | 1 | 1 | PI Parks - ELSEWEDY1 | 3779007.23
PI Parks - ELSEWEDY | 2 | 2 | PI Parks - ELSEWEDY2 | 3366014.15
PI Parks - ELSEWEDY | 3 | 3 | PI Parks - ELSEWEDY3 | 823701.85
PI Parks - ELSEWEDY | 4 | 4 | PI Parks - ELSEWEDY4 | 2572231.81
PI Parks - ELSEWEDY | 5 | 5 | PI Parks - ELSEWEDY5 | 1175600.49
PI Parks - ELSEWEDY | 6 | 6 | PI Parks - ELSEWEDY6 | 689110.93
PI Parks - ELSEWEDY | 7 | 7 | PI Parks - ELSEWEDY7 | 1209313.47
PI Parks - ELSEWEDY | 8 | 8 | PI Parks - ELSEWEDY8 | 1492654.2
PI Parks - ELSEWEDY | 9 | 9 | PI Parks - ELSEWEDY9 | 1471457.2
PI Parks - ELSEWEDY | 10 | 10 | PI Parks - ELSEWEDY10 | 2470019.34
PI Parks - ELSEWEDY | 11 | 11 | PI Parks - ELSEWEDY11 | 945860.23
PI Parks - ELSEWEDY | 12 | 12 | PI Parks - ELSEWEDY12 | 1347803.37
PI Parks - ELSEWEDY | 13 | 13 | PI Parks - ELSEWEDY13 | 719804.13
PI Parks - ELSEWEDY | 14 | 14 | PI Parks - ELSEWEDY14 | 775351.46
PI Parks - ELSEWEDY | 15 | 15 | PI Parks - ELSEWEDY15 | 4484634.14
PI Parks - ELSEWEDY | 16 | 16 | PI Parks - ELSEWEDY16 | 4125986.43
PI Parks - ELSEWEDY | 17 | 17 | PI Parks - ELSEWEDY17 | 1375431.38
PI Parks - ELSEWEDY | 18 | 18 | PI Parks - ELSEWEDY18 | 3699864.67
PI Parks - ELSEWEDY | 19 | 19 | PI Parks - ELSEWEDY19 | 2311261.81
PI Parks - ELSEWEDY | 20 | 20 | PI Parks - ELSEWEDY20 | 1466574.4
PI Parks - ELSEWEDY | 21 | 21 | PI Parks - ELSEWEDY21 | 4361327.46
PI Parks - ELSEWEDY | 21.1 | 21 | PI Parks - ELSEWEDY21 | 972238.28
PI Parks - MEP | 1 | 1 | PI Parks - MEP1 | 7818631.64
PI Parks - MEP | 2 | 2 | PI Parks - MEP2 | 3907009.94
PI Parks - MEP | 3 | 3 | PI Parks - MEP3 | 3921714.73
PI Parks - MEP | 4 | 4 | PI Parks - MEP4 | 3366511.48
PI Parks - MEP | 5 | 5 | PI Parks - MEP5 | 6350059.5
PI Parks - MEP | 6 | 6 | PI Parks - MEP6 | 919139.23
PI Parks - MEP | 7 | 7 | PI Parks - MEP7 | 2661364.08
PI Parks - MEP | 8 | 8 | PI Parks - MEP8 | 1478131.5
PI Parks - MEP | 9 | 9 | PI Parks - MEP9 | 4813799.42
PI Parks - MEP1 | 1 | 1 | PI Parks - MEP11 | 5000000
PI Parks - MEP2 | 2 | 2 | PI Parks - MEP22 | 7600000
PK #107 | 8 | 8 | PK #1078 | 3005745.85
PK #107 | 9 | 9 | PK #1079 | 1418090.5
PK #107 | 10 | 10 | PK #10710 | 1453205.38
PK #107 | 11 | 11 | PK #10711 | 2354508.52
PK #107 | 12 | 12 | PK #10712 | 4193998
PK #107 | 13 | 13 | PK #10713 | 3281572.56
PK #107 | 14 | 14 | PK #10714 | 166316.41
PK #107 | 15 | 15 | PK #10715 | 1406606.27
PK #107 | 16 | 16 | PK #10716 | 131256.74
PK #107 | 17 | 17 | PK #10717 | 763627.7
PK #107 | 18 | 18 | PK #10718 | 1341459.14
PK #117 | 1 | 1 | PK #1171 | 4130129.12
PK #117 | 2 | 2 | PK #1172 | 6455421.01
PK #117 | 3 | 3 | PK #1173 | 4502026.51
PK #117 | 4 | 4 | PK #1174 | 3740180.08
PK #117 | 5 | 5 | PK #1175 | 4762507.56
PK #117 | 6 | 6 | PK #1176 | 5347404.79
PK #117 | 7 | 7 | PK #1177 | 118938.86
PK #117 | 8 | 8 | PK #1178 | 3896343.98
PK #117 | 9 | 9 | PK #1179 | 2578109.73
PK #117 | 10 | 10 | PK #11710 | 882296.11
PK #117 | 11 | 11 | PK #11711 | 809762.24
PK #117 | 12 | 12 | PK #11712 | 3376927.91
PK #117 | 13 | 13 | PK #11713 | 3145907.11
PK #117 | 14 | 14 | PK #11714 | 2483342.5
PK #117 - Social Insurance | 1 | 1 | PK #117 - Social Insurance1 | 229049.99
PK #117 - Social Insurance | 2 | 2 | PK #117 - Social Insurance2 | 163866
PK #117 - Social Insurance | 3 | 3 | PK #117 - Social Insurance3 | 56058.22
PK #117 - Social Insurance | 4 | 4 | PK #117 - Social Insurance4 | 57062.55
PK #117 - Social Insurance | 5 | 5 | PK #117 - Social Insurance5 | 285951.45
PK #22 - Social Insurance | 1 | 1 | PK #22 - Social Insurance1 | 263550
PK#22 | 37 | 37 | PK#2237 | 780036
PK#32 | 30 | 30 | PK#3230 | 900093.35
PKG#101 | 1 | 1 | PKG#1011 | 1029594.82
PKG#101 | 2 | 2 | PKG#1012 | 2222206.65
PKG#101 | 3 | 3 | PKG#1013 | 2246109.51
PKG#101 | 4 | 4 | PKG#1014 | 2512749.68
PKG#101 | 5 | 5 | PKG#1015 | 2051541.96
PKG#101 | 6 | 6 | PKG#1016 | 1988552.05
PKG#101 | 7 | 7 | PKG#1017 | 1824097.57
PKG#101 | 8 | 8 | PKG#1018 | 2104893.84
PKG#101 | 9 | 9 | PKG#1019 | 1424816.56
PKG#101 | 10 | 10 | PKG#10110 | 1976416.89
PKG#101 | 11 | 11 | PKG#10111 | 1709961.04
PKG#101 | 12 | 12 | PKG#10112 | 1146998.21
PKG#101 | 13 | 13 | PKG#10113 | 1343055.6
PKG#101 | 14 | 14 | PKG#10114 | 191421.72
PKG#101 | 15 | 15 | PKG#10115 | 303853.8
PKG#101 | 16 | 16 | PKG#10116 | 866491
PKG#101 | 17 | 17 | PKG#10117 | 3321316.23
PKG#101 | 18 | 18 | PKG#10118 | 1192690.23
PKG#101 | 19 | 19 | PKG#10119 | 596242.89
PKG#101 | 20 | 20 | PKG#10120 | 759353.32
PKG#101 | 21 | 21 | PKG#10121 | 1584188.58
PKG#101 | 22 | 22 | PKG#10122 | 594123.32
PKG#101 | 23 | 23 | PKG#10123 | 189091.52
PKG#101 | 24 | 24 | PKG#10124 | 546994.62
PKG#101- Social Insurance | 1 | 1 | PKG#101- Social Insurance1 | 877190.31
PKG#101- Social Insurance | 2 | 2 | PKG#101- Social Insurance2 | 693232.98
PKG#101 | 1 | 1 | PKG#1011 | 8723141
PKG#101-VO1&VO2 AP | 1 | 1 | PKG#101-VO1&VO2 AP1 | 7091710.52
PKG#144 | 2 | 2 | PKG#1442 | 2532120.6
PKG#144 | 3 | 3 | PKG#1443 | 6189125.05
PKG#144 | 4 | 4 | PKG#1444 | 6887337.01
PKG#144 | 5 | 5 | PKG#1445 | 7206339.73
PKG#144 | 6 | 6 | PKG#1446 | 14929468.44
PKG#144 | 7 | 7 | PKG#1447 | 12477244.23
PKG#144 | 8 | 8 | PKG#1448 | 8906660.63
PKG#144 | 9 | 9 | PKG#1449 | 9782161.34
PKG#144 | 10 | 10 | PKG#14410 | 11074114.43
PKG#144 | 11 | 11 | PKG#14411 | 7386054.95
PKG#144 | 12 | 12 | PKG#14412 | 15000000
PKG#144 | 12.1 | 12 | PKG#14412 | 6073691.31
PKG#144 | 13 | 13 | PKG#14413 | 14000000
PKG#144 | 14 | 14 | PKG#14414 | 10173240.83
PKG#144 | 15 | 15 | PKG#14415 | 9960243.27
PKG#144 | 16 | 16 | PKG#14416 | 1116473.97
PKG#144 - Social Insurance | 1 | 1 | PKG#144 - Social Insurance1 | 216614.52
PKG#144 - Social Insurance | 2 | 2 | PKG#144 - Social Insurance2 | 4748411.06
PKG#144 - Social Insurance | 3 | 3 | PKG#144 - Social Insurance3 | 506192.12
PKG#144 - Social Insurance | 4 | 4 | PKG#144 - Social Insurance4 | 687983.17
PKG#144 - Social Insurance | 5 | 5 | PKG#144 - Social Insurance5 | 2262789.43
PKG#144 - Social Insurance | 6 | 6 | PKG#144 - Social Insurance6 | 1430834.93
PKG#144 - Social Insurance | 7 | 7 | PKG#144 - Social Insurance7 | 596740.76
PKG#144 - Social Insurance | 8 | 8 | PKG#144 - Social Insurance8 | 342218.65
PKG#144 | 1 | 1 | PKG#1441 | 24600000
PKG#162 | 2 | 2 | PKG#1622 | 7794726.52
PKG#162 | 3 | 3 | PKG#1623 | 5119599.34
PKG#162 | 4 | 4 | PKG#1624 | 6336538.23
PKG#162 | 5 | 5 | PKG#1625 | 6124877.69
PKG#162 | 6 | 6 | PKG#1626 | 4824045.39
PKG#162 | 7 | 7 | PKG#1627 | 7215874.2121
PKG#162 | 8 | 8 | PKG#1628 | 9432027.72
PKG#162 | 9 | 9 | PKG#1629 | 9889305
PKG#162 | 10 | 10 | PKG#16210 | 13282474.2108
PKG#162 | 11 | 11 | PKG#16211 | 7840185.48
PKG#162 | 12 | 12 | PKG#16212 | 4608392
PKG#162 | 13 | 13 | PKG#16213 | 3429815.246
PKG#162 | 14 | 14 | PKG#16214 | 502581.43
PKG#162 | 15 | 15 | PKG#16215 | 3999402.59
PKG#162- Social Insurance | 1 | 1 | PKG#162- Social Insurance1 | 829293.83
PKG#162- Social Insurance | 2 | 2 | PKG#162- Social Insurance2 | 1584302
PKG#162- Social Insurance | 3 | 3 | PKG#162- Social Insurance3 | 1223560.05
PKG#162- Social Insurance | 4 | 4 | PKG#162- Social Insurance4 | 760409.01
PKG#162- Social Insurance | 5 | 5 | PKG#162- Social Insurance5 | 438178.63
PKG#162- Social Insurance | 6 | 6 | PKG#162- Social Insurance6 | 37250.26
PKG#162 | 1 | 1 | PKG#1621 | 7681619.5
PKG#163 | 2 | 2 | PKG#1632 | 1068966.43
PKG#163 | 3 | 3 | PKG#1633 | 2977091.11
PKG#163 | 4 | 4 | PKG#1634 | 6845695.77
PKG#163 | 5 | 5 | PKG#1635 | 3782501.29
PKG#163 | 6 | 6 | PKG#1636 | 6255172.17
PKG#163 | 7 | 7 | PKG#1637 | 4922193.5
PKG#163 | 8 | 8 | PKG#1638 | 6050639.77
PKG#163 | 9 | 9 | PKG#1639 | 4602212.16
PKG#163 | 10 | 10 | PKG#16310 | 2532838.57
PKG#163 | 11 | 11 | PKG#16311 | 3799097.57
PKG#163 | 12 | 12 | PKG#16312 | 2215480.09
PKG#163 | 13 | 13 | PKG#16313 | 3821253.39
PKG#163 | 14 | 14 | PKG#16314 | 10697999.42
PKG#163 | 15 | 15 | PKG#16315 | 4024676.65
PKG#163 | 16 | 16 | PKG#16316 | 3611195.74
PKG#163 | 17 | 17 | PKG#16317 | 2445757.34
PKG#163 | 18 | 18 | PKG#16318 | 2445757.34
PKG#163 | 19 | 19 | PKG#16319 | 6520369.14
PKG#163 | 20 | 20 | PKG#16320 | 3715617.2
PKG#163 | 21 | 21 | PKG#16321 | 5322260.63
PKG#163 | 22 | 22 | PKG#16322 | 2261775.79
PKG#163 | 23 | 23 | PKG#16323 | 3449740.5053
PKG#163 | 24 | 24 | PKG#16324 | 5681606.5237
PKG#163 | 25 | 25 | PKG#16325 | 11730565.831
PKG#163 | 26 | 26 | PKG#16326 | 6014332.37
PKG#163 | 27 | 27 | PKG#16327 | 3457484.33
PKG#163 | 28 | 28 | PKG#16328 | 18331730.1
PKG#163 | 29 | 29 | PKG#16329 | 18785649.76
PKG#163 | 30 | 30 | PKG#16330 | 3193802.31
PKG#163 | 31 | 31 | PKG#16331 | 1079324.09
PKG#163 | 32 | 32 | PKG#16332 | 4562478.02
PKG#163 | 33 | 33 | PKG#16333 | 0.0001
PKG#163 | 34 | 34 | PKG#16334 | 0.0001
PKG#163 | 35 | 35 | PKG#16335 | 0.0001
PKG#163- Social Insurance | 1 | 1 | PKG#163- Social Insurance1 | 78430
PKG#163- Social Insurance | 2 | 2 | PKG#163- Social Insurance2 | 720699.2
PKG#163- Social Insurance | 3 | 3 | PKG#163- Social Insurance3 | 277522.63
PKG#163- Social Insurance | 4 | 4 | PKG#163- Social Insurance4 | 451906.96
PKG#163- Social Insurance | 5 | 5 | PKG#163- Social Insurance5 | 754870.94
PKG#163- Social Insurance | 6 | 6 | PKG#163- Social Insurance6 | 961013.69
PKG#163- Social Insurance | 7 | 7 | PKG#163- Social Insurance7 | 275560.66
PKG#163- Social Insurance | 8 | 8 | PKG#163- Social Insurance8 | 434454.78
PKG#163- Social Insurance | 9 | 9 | PKG#163- Social Insurance9 | 2963675.17
PKG#163- Social Insurance | 10 | 10 | PKG#163- Social Insurance10 | 258797.58
PKG#163 | 1 | 1 | PKG#1631 | 24950583
PKG#177 | 2 | 2 | PKG#1772 | 10240448.36
PKG#177 | 3 | 3 | PKG#1773 | 3893019.54
PKG#177 | 4 | 4 | PKG#1774 | 4139690.65
PKG#177 | 5 | 5 | PKG#1775 | 1890262.73
PKG#177 | 6 | 6 | PKG#1776 | 2069539.45
PKG#177 | 7 | 7 | PKG#1777 | 30000000
PKG#177 | 8 | 8 | PKG#1778 | 6325726.09
PKG#177 | 9 | 9 | PKG#1779 | 1386804.78
PKG#177 | 10 | 10 | PKG#17710 | 1031892.42
PKG#177 | 11 | 11 | PKG#17711 | 1623911.78
PKG#177 | 12 | 12 | PKG#17712 | 11867471.98
PKG#177 | 13 | 13 | PKG#17713 | 4287396.18
PKG#177 | 14 | 14 | PKG#17714 | 3654358.5
PKG#177 | 15 | 15 | PKG#17715 | 30000000
PKG#177 | 16 | 16 | PKG#17716 | 8978914.16
PKG#177 | 17 | 17 | PKG#17717 | 311248.17
PKG#177 | 18 | 18 | PKG#17718 | 15059090.32
PKG#177 | 19 | 19 | PKG#17719 | 6143418.31
PKG#177 | 20 | 20 | PKG#17720 | 7621726.83
PKG#177 | 21 | 21 | PKG#17721 | 5553244.96
PKG#177 | 22 | 22 | PKG#17722 | 3436603.03
PKG#177 | 23 | 23 | PKG#17723 | 4324164.09
PKG#177 | 24 | 24 | PKG#17724 | 4835218.42
PKG#177 | 25 | 25 | PKG#17725 | 4062657.22
PKG#177 | 26 | 26 | PKG#17726 | 30000000
PKG#177 | 27 | 27 | PKG#17727 | 1920749.49
PKG#177 | 28 | 28 | PKG#17728 | 3761281.17
PKG#177 | 29 | 29 | PKG#17729 | 30000000
PKG#177 | 30 | 30 | PKG#17730 | 11174297.33
PKG#177 | 31 | 31 | PKG#17731 | 20000000
PKG#177 | 32 | 32 | PKG#17732 | 9586612.72
PKG#177 | 33 | 33 | PKG#17733 | 9774603.63
PKG#177 | 34 | 34 | PKG#17734 | 3243420.79
PKG#177 | 35 | 35 | PKG#17735 | 14874314
PKG#177 | 36 | 36 | PKG#17736 | 32974130.9
PKG#177 | 37 | 37 | PKG#17737 | 2963171.82
PKG#177 | 38 | 38 | PKG#17738 | 40830987.19
PKG#177 | 39 | 39 | PKG#17739 | 24380106.6
PKG#177 | 40 | 40 | PKG#17740 | 0.0001
PKG#177 | 41 | 41 | PKG#17741 | 1e-05
PKG#177 | 42 | 42 | PKG#17742 | 4198626.99
PKG#177 | 43 | 43 | PKG#17743 | 14488992.22
PKG#177 | 44 | 44 | PKG#17744 | 17144236.06
PKG#177 | 45 | 45 | PKG#17745 | 15002016.49
PKG#177 | 46 | 46 | PKG#17746 | 3048300.98
PKG#177 | 47 | 47 | PKG#17747 | 4274072.25
PKG#177 | 48 | 48 | PKG#17748 | 1e-06
PKG#177 | 49 | 49 | PKG#17749 | 1e-06
PKG#177 | 50 | 50 | PKG#17750 | 1e-06
PKG#177 | 51 | 51 | PKG#17751 | 1e-06
PKG#177 | 52 | 52 | PKG#17752 | 1e-06
PKG#177 | 53 | 53 | PKG#17753 | 1e-06
PKG#177 | 1 | 1 | PKG#1771 | 22337274.9
PKG#177 | 4 | 4 | PKG#1774 | 10000000
PKG#177 | 5 | 5 | PKG#1775 | 10000000
PKG#177 | 6 | 6 | PKG#1776 | 10000000
PKG#177 | 7 | 7 | PKG#1777 | 10000000
PKG#177 | 8 | 8 | PKG#1778 | 10000000
PKG#177 | 9 | 9 | PKG#1779 | 10000000
PKG#177 | 10 | 10 | PKG#17710 | 10000000
PKG#177 | 11 | 11 | PKG#17711 | 10000000
PKG#177 - SWI 07 | 10 | 10 | PKG#177 - SWI 0710 | 1e-05
PKG#177- Social Insurance | 1 | 1 | PKG#177- Social Insurance1 | 1919688.42
PKG#177- Social Insurance | 2 | 2 | PKG#177- Social Insurance2 | 8305203.5
PKG#177- Social Insurance | 3 | 3 | PKG#177- Social Insurance3 | 2456503.82
PKG#177- Social Insurance | 4 | 4 | PKG#177- Social Insurance4 | 8736398.9
PKG#177- Social Insurance | 5 | 5 | PKG#177- Social Insurance5 | 3475892.52
PKG#177- Social Insurance | 6 | 6 | PKG#177- Social Insurance6 | 274089.78
PKG#178 | 2 | 2 | PKG#1782 | 13230338.29
PKG#178 | 3 | 3 | PKG#1783 | 6675236.88
PKG#178 | 4 | 4 | PKG#1784 | 6081013.29
PKG#178 | 5 | 5 | PKG#1785 | 9125492.66
PKG#178 | 6 | 6 | PKG#1786 | 2730279.03
PKG#178 | 7 | 7 | PKG#1787 | 1644401.99
PKG#178 | 8 | 8 | PKG#1788 | 595920.45
PKG#178 | 9 | 9 | PKG#1789 | 289077.6
PKG#178 | 10 | 10 | PKG#17810 | 2235574.97
PKG#178 | 1 | 1 | PKG#1781 | 3747170.2
PKG#178- Social Insurance | 1 | 1 | PKG#178- Social Insurance1 | 1276787.15
PKG#178- Social Insurance | 2 | 2 | PKG#178- Social Insurance2 | 392599.98
PKG#178- Social Insurance | 3 | 3 | PKG#178- Social Insurance3 | 887343.85
PKG#205 | 2 | 2 | PKG#2052 | 1181605.96
PKG#205 | 3 | 3 | PKG#2053 | 1250466.11
PKG#205 | 1 | 1 | PKG#2051 | 1260000
PKG#205-Social Insurance | 1 | 1 | PKG#205-Social Insurance1 | 209129.12
PKG#220B | 2 | 2 | PKG#220B2 | 8261597.76
PKG#220B | 3 | 3 | PKG#220B3 | 5980500.04
PKG#220B | 4 | 4 | PKG#220B4 | 2300000
PKG#220B | 1 | 1 | PKG#220B1 | 7500000
PKG#45 | 46 | 46 | PKG#4546 | 1844931.02
PKG#58 | 22 | 22 | PKG#5822 | 327696.29
PKG#85 | 5 | 5 | PKG#855 | 1729285.15
PKG#85 | 6 | 6 | PKG#856 | 768766.59
PKG#85 | 7 | 7 | PKG#857 | 29830.3
PKG#85 | 8 | 8 | PKG#858 | 1391898.96
PO#11687 | 1 | 1 | PO#116871 | 1090584
PO#11687 | 2 | 2 | PO#116872 | 451528
PO#11687 | 3 | 3 | PO#116873 | 293788
PO#11687 | 5 | 5 | PO#116875 | 343200
Port Said Silos | 1 | 1 | Port Said Silos1 | 5248643
Port Said Silos | 2 | 2 | Port Said Silos2 | 1773106
Port Said Silos | 3 | 3 | Port Said Silos3 | 4623869
Port Said Silos | 4 | 4 | Port Said Silos4 | 2560435
Port Said Silos | 5 | 5 | Port Said Silos5 | 4009921
Port Said Silos | 6 | 6 | Port Said Silos6 | 6842722
Port Said Silos | 7 | 7 | Port Said Silos7 | 3061822
Port Said Silos | 8 | 8 | Port Said Silos8 | 17260533
Port Said Silos | 9 | 9 | Port Said Silos9 | 2370710
Port Said Silos | 10 | 10 | Port Said Silos10 | 6384571
Port Said Silos | 11 | 11 | Port Said Silos11 | 3852337
Port Said Silos | 12 | 12 | Port Said Silos12 | 1587432
Port Said Silos | 13 | 13 | Port Said Silos13 | 460093
Port Said Silos | 14 | 14 | Port Said Silos14 | 2136487
Port Said Silos | 15 | 15 | Port Said Silos15 | 7663669
Port Said Silos | 16 | 16 | Port Said Silos16 | 9649102
Port Said Silos | 17 | 17 | Port Said Silos17 | 5738977
Port Said Silos | 18 | 18 | Port Said Silos18 | 2991787
Port Said Silos | 19 | 19 | Port Said Silos19 | 12748959
Port Said Silos | 20 | 20 | Port Said Silos20 | 6593857
Port Said Silos | 21 | 21 | Port Said Silos21 | 11818794
Port Said Silos | 22 | 22 | Port Said Silos22 | 4826684
Port Said Silos | 23 | 23 | Port Said Silos23 | 2411082.19
Port Said Silos | 24 | 24 | Port Said Silos24 | 3306186
Port Said Silos | 25 | 25 | Port Said Silos25 | 3280048
Port Said Silos | 26 | 26 | Port Said Silos26 | 426108
Port Said Silos | 28 | 28 | Port Said Silos28 | 1239632
Port Said Silos | 29 | 29 | Port Said Silos29 | 337130
Port Said Silos | 30 | 30 | Port Said Silos30 | 100641
Port Said Silos | 31 | 31 | Port Said Silos31 | 727554
Port Said Silos | 32 | 32 | Port Said Silos32 | 2193035.35
Port Said Silos | 33 | 33 | Port Said Silos33 | 2711136
Port Said Silos - Foreigner Supply | 1 | 1 | Port Said Silos - Foreigner Supply1 | 5206992
Port Said Silos - Foreigner Supply | 2 | 2 | Port Said Silos - Foreigner Supply2 | 775509.45
Port Said Silos - Local Supply | 1 | 1 | Port Said Silos - Local Supply1 | 655657.61
Port Said Silos - Local Supply | 2 | 2 | Port Said Silos - Local Supply2 | 1162711.94
Port Said Silos - Local Supply | 3 | 3 | Port Said Silos - Local Supply3 | 2307930.88
Port Said Silos - Local Supply | 4 | 4 | Port Said Silos - Local Supply4 | 3416710
Port Said Silos - Local Supply | 5 | 5 | Port Said Silos - Local Supply5 | 2565984
Port Said Silos - Local Supply | 6 | 6 | Port Said Silos - Local Supply6 | 833240
Port Said Silos - Local Supply | 7 | 7 | Port Said Silos - Local Supply7 | 4345468
Port Said Silos - Local Supply | 8 | 8 | Port Said Silos - Local Supply8 | 1794648.84
Port Said Silos - Local Supply | 9 | 9 | Port Said Silos - Local Supply9 | 2529147
Port Said Silos - Local Supply | 10 | 10 | Port Said Silos - Local Supply10 | 494192
Port Said Silos - Local Supply | 11 | 11 | Port Said Silos - Local Supply11 | 833789.82
Port Said Silos | 1 | 1 | Port Said Silos1 | 26540249.4
Port Said Silos | 2 | 2 | Port Said Silos2 | 15000000
Port Said Silos | 1 | 1 | Port Said Silos1 | 6000000
Port Said Silos | 2 | 2 | Port Said Silos2 | 5000000
Port Said Silos | 3 | 3 | Port Said Silos3 | 10000000
Port Said Silos | 4 | 4 | Port Said Silos4 | 20000000
Port Said Silos | 5 | 5 | Port Said Silos5 | 10000000
Port Said Silos | 6 | 6 | Port Said Silos6 | 15000000
Port Said Silos-Social Insurrance | 1 | 1 | Port Said Silos-Social Insurrance1 | 2127569.59
Port Said Silos-Social Insurrance | 2 | 2 | Port Said Silos-Social Insurrance2 | 411364.07
Port Said Silos-Social Insurrance | 3 | 3 | Port Said Silos-Social Insurrance3 | 653360.08
Port Said Silos-Social Insurrance | 4 | 4 | Port Said Silos-Social Insurrance4 | 2773108
Port Said Silos-Social Insurrance | 5 | 5 | Port Said Silos-Social Insurrance5 | 344418
Port Said Silos-Social Insurrance | 6 | 6 | Port Said Silos-Social Insurrance6 | 1595672
Port Said Silos-Social Insurrance | 7 | 7 | Port Said Silos-Social Insurrance7 | 440773.7
Port Said Silos-Social Insurrance | 8 | 8 | Port Said Silos-Social Insurrance8 | 585270
Port Said Silos-Social Insurrance | 9 | 9 | Port Said Silos-Social Insurrance9 | 2996951.24
Port Said Silos-Social Insurrance | 10 | 10 | Port Said Silos-Social Insurrance10 | 999516
Port Said Silos-Social Insurrance | 11 | 11 | Port Said Silos-Social Insurrance11 | 1556882.52
PSP Substation | 2 | 2 | PSP Substation2 | 1160599
PSP Substation | 3 | 3 | PSP Substation3 | 1834172.07
PSP Substation | 4 | 4 | PSP Substation4 | 1268627.7
PSP Substation | 5 | 5 | PSP Substation5 | 3991290.99
PSP Substation | 6 | 6 | PSP Substation6 | 3047586.1
PSP Substation | 7 | 7 | PSP Substation7 | 1780094.35
PSP Substation | 8 | 8 | PSP Substation8 | 1829713.21
PSP Substation | 9 | 9 | PSP Substation9 | 1314287.28
PSP Substation | 10 | 10 | PSP Substation10 | 3264225.8
PSP Substation | 11 | 11 | PSP Substation11 | 2606365.14
PSP Substation | 12 | 12 | PSP Substation12 | 28515
PSP Substation - Beni Suef | 29 | 29 | PSP Substation - Beni Suef29 | 4326586.5
PSP Substation | 1 | 1 | PSP Substation1 | 6647052.2
PSP Substation-Retention | 1 | 1 | PSP Substation-Retention1 | 597560.88
PSP Substation-Retention | 2 | 2 | PSP Substation-Retention2 | 480264.83
PSP Substation-Retention | 3 | 3 | PSP Substation-Retention3 | 536537.44
PSP Substation-Retention | 4 | 4 | PSP Substation-Retention4 | 1617088.7
Rabigh Ext. - Piles | 1 | 1 | Rabigh Ext. - Piles1 | 947881.6
Rabigh Ext. - Piles | 2 | 2 | Rabigh Ext. - Piles2 | 1174037
Rabigh Ext. - Piles | 3 | 3 | Rabigh Ext. - Piles3 | 966227
Rabigh Ext. - Piles | 4 | 4 | Rabigh Ext. - Piles4 | 1787056
Rabigh Ext. - Piles | 5 | 5 | Rabigh Ext. - Piles5 | 1130623
Rabigh Ext. - Piles | 6 | 6 | Rabigh Ext. - Piles6 | 2013847.54
Rabigh Ext. - Piles- DP | 1 | 1 | Rabigh Ext. - Piles- DP1 | 195500
Rabigh Ext. - Piles- DP | 2 | 2 | Rabigh Ext. - Piles- DP2 | 5181540
Rabigh Ext. -Building | 1 | 1 | Rabigh Ext. -Building1 | 2660254.84
Rabigh Ext. -Building | 2 | 2 | Rabigh Ext. -Building2 | 4708047.77
Rabigh Ext. -Building- DP | 1 | 1 | Rabigh Ext. -Building- DP1 | 10000000
Rabigh Ext. -Building- DP | 2 | 2 | Rabigh Ext. -Building- DP2 | 5000000
Rabigh Ext. -Building- DP | 3 | 3 | Rabigh Ext. -Building- DP3 | 49209592.04
Radamis-Concrete | 1 | 1 | Radamis-Concrete1 | 10000000
Radamis-Concrete | 2 | 2 | Radamis-Concrete2 | 10000000
Radamis-H1 | 1 | 1 | Radamis-H11 | 5000000
Radamis-H1 | 2 | 2 | Radamis-H12 | 3000000
Radamis-H1 | 3 | 3 | Radamis-H13 | 5000000
Radamis-H1 | 4 | 4 | Radamis-H14 | 3000000
Radamis-H1 | 5 | 5 | Radamis-H15 | 10000000
Radamis-H1 | 6 | 6 | Radamis-H16 | 10000000
Radamis-H1 | 7 | 7 | Radamis-H17 | 5000000
Radamis-H1 | 8 | 8 | Radamis-H18 | 10000000
Radamis-H1 | 9 | 9 | Radamis-H19 | 10000000
Radamis-H1 | 10 | 10 | Radamis-H110 | 10000000
Radamis-H1 | 11 | 11 | Radamis-H111 | 15000000
Radamis-H1 | 13 | 13 | Radamis-H113 | 10000000
Radamis-H1 | 15 | 15 | Radamis-H115 | 10000000
Radamis-H1 | 16 | 16 | Radamis-H116 | 15000000
Radamis-H1 | 17 | 17 | Radamis-H117 | 18000000
Radamis-H1 | 18 | 18 | Radamis-H118 | 10000000
Radamis-H1 | 19 | 19 | Radamis-H119 | 16000000
Radamis-H1 | 20 | 20 | Radamis-H120 | 10000000
Radamis-H1 | 21 | 21 | Radamis-H121 | 10000000
Radamis-H1 | 22 | 22 | Radamis-H122 | 10000000
Radamis-H1 | 23 | 23 | Radamis-H123 | 10000000
Radamis-H1 | 24 | 24 | Radamis-H124 | 10000000
Radamis-H1 | 25 | 25 | Radamis-H125 | 10000000
Radamis-H1 | 26 | 26 | Radamis-H126 | 10000000
Radamis-H1 | 27 | 27 | Radamis-H127 | 10000000
Radamis-H1 | 28 | 28 | Radamis-H128 | 10000000
Radamis-H1 | 29 | 29 | Radamis-H129 | 10000000
Radamis-H1 | 30 | 30 | Radamis-H130 | 10000000
Radamis-H1 | 31 | 31 | Radamis-H131 | 20000000
Radamis-H1 | 32 | 32 | Radamis-H132 | 30000000
Radamis-H1 | 33 | 33 | Radamis-H133 | 30000000
Radamis-H1 | 34 | 34 | Radamis-H134 | 10000000
Radamis-H1 | 35 | 35 | Radamis-H135 | 20000000
Radamis-H1 | 36 | 36 | Radamis-H136 | 25000000
Radamis-H1 | 37 | 37 | Radamis-H137 | 20000000
Radamis-H1 | 38 | 38 | Radamis-H138 | 10000000
Radamis-H1 | 39 | 39 | Radamis-H139 | 20000000
Radamis-H1 | 40 | 40 | Radamis-H140 | 20000000
Radamis-Rooms Fitout | 1 | 1 | Radamis-Rooms Fitout1 | 250000
Radamis-Rooms Fitout | 2 | 2 | Radamis-Rooms Fitout2 | 500000
Radamis-Rooms Fitout | 3 | 3 | Radamis-Rooms Fitout3 | 15000000
Radamis-Rooms Fitout | 4 | 4 | Radamis-Rooms Fitout4 | 4000000
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 2918717
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 2114752.93
Red Sea Museum | 1 | 1 | Red Sea Museum1 | 2300000
Red Sea Museum | 2 | 2 | Red Sea Museum2 | 2300000
Red Sea Museum | 3 | 3 | Red Sea Museum3 | 4443406
Ring Road - El Marg | 1 | 1 | Ring Road - El Marg1 | 45719198.4
Ring Road - El Marg | 2 | 2 | Ring Road - El Marg2 | 9576635.3
Ring Road - El Marg | 3 | 3 | Ring Road - El Marg3 | 13773926.1
Ring Road - El Marg | 4 | 4 | Ring Road - El Marg4 | 4525661.3
Ring Road - El Marg | 5 | 5 | Ring Road - El Marg5 | 2097964.3
Ring Road - El Marg | 6 | 6 | Ring Road - El Marg6 | 1156719
Ring Road - El Marg | 7 | 7 | Ring Road - El Marg7 | 2151897.3
Ring Road - El Marg | 8 | 8 | Ring Road - El Marg8 | 3742254.85
Ring Road - El Marg | 9 | 9 | Ring Road - El Marg9 | 4020500.85
Ring Road - El Marg | 10 | 10 | Ring Road - El Marg10 | 2795847.4
Ring Road - El Marg | 11 | 11 | Ring Road - El Marg11 | 0.0001
Ring Road - El Marg | 12 | 12 | Ring Road - El Marg12 | 0.0001
Ring Road - El Marg | 13 | 13 | Ring Road - El Marg13 | 0.0001
Ring Road - El Marg - Retention Release | 1 | 1 | Ring Road - El Marg - Retention Release1 | 1436312.4
Ring Road - Mounib | 1 | 1 | Ring Road - Mounib1 | 26333646.7391
Ring Road - Mounib | 2 | 2 | Ring Road - Mounib2 | 7157243.6
Ring Road - Mounib | 3 | 3 | Ring Road - Mounib3 | 10759736.15
Ring Road - Mounib | 4 | 4 | Ring Road - Mounib4 | 4521989.75
Ring Road - Mounib | 5 | 5 | Ring Road - Mounib5 | 6026340.35
Ring Road - Mounib | 6 | 6 | Ring Road - Mounib6 | 4751540.0144
Ring Road - Mounib | 7 | 7 | Ring Road - Mounib7 | 3640291.7356
Ring Road - Mounib | 8 | 8 | Ring Road - Mounib8 | 2701161.75
Ring Road - Mounib | 9 | 9 | Ring Road - Mounib9 | 3856121.55
Ring Road - Mounib | 10 | 10 | Ring Road - Mounib10 | 10942755.35
Ring Road - Mounib | 11 | 11 | Ring Road - Mounib11 | 2713820.35
Ring Road - Mounib | 11.1 | 11 | Ring Road - Mounib11 | 994575.65
Ring Road - Mounib | 12 | 12 | Ring Road - Mounib12 | 14886673.24
Ring Road - Mounib | 13 | 13 | Ring Road - Mounib13 | 4632929.96
Ring Road - Mounib | 13.1 | 13 | Ring Road - Mounib13 | 21269971.05
Ring Road - Mounib | 13.2 | 13 | Ring Road - Mounib13 | 6375786
Ring Road - Mounib | 13.3 | 13 | Ring Road - Mounib13 | 719946.2
Ring Road - Mounib | 14 | 14 | Ring Road - Mounib14 | 5086863.5
Ring Road - Mounib | 14.1 | 14 | Ring Road - Mounib14 | 9870444.4
Ring Road - Mounib | 15 | 15 | Ring Road - Mounib15 | 10573632.35
Ring Road - Mounib | 15.1 | 15 | Ring Road - Mounib15 | 376461.75
Ring Road - Mounib | 16 | 16 | Ring Road - Mounib16 | 96448162.4
Ring Road - Mounib | 16.1 | 16 | Ring Road - Mounib16 | 35042549.45
Ring Road - Mounib | 17 | 17 | Ring Road - Mounib17 | 1170803.2
Ring Road - Mounib | 18 | 18 | Ring Road - Mounib18 | 2897048.5
Ring Road - Mounib | 19 | 19 | Ring Road - Mounib19 | 1351162.1
Ring Road - Mounib - refund | 1 | 1 | Ring Road - Mounib - refund1 | 11410289.1
Ring Road - Mounib - Social Insurance | 1 | 1 | Ring Road - Mounib - Social Insurance1 | 337945.75
RO Apply -Mech- SSC | 1 | 1 | RO Apply -Mech- SSC1 | 1730229.07
RO Apply -Mech- SSC | 2 | 2 | RO Apply -Mech- SSC2 | 1e-05
RO Apply -Mech- SSC | 4 | 4 | RO Apply -Mech- SSC4 | 0.001
RO - Supply - Electric | 1 | 1 | RO - Supply - Electric1 | 1e-05
RO - Supply - Electric | 2 | 2 | RO - Supply - Electric2 | 1e-05
RO - Supply - Electric | 3 | 3 | RO - Supply - Electric3 | 2225665.9095
RO Supply -Mech- SSC | 1 | 1 | RO Supply -Mech- SSC1 | 13698304.23
RO Supply -Mech- SSC | 2 | 2 | RO Supply -Mech- SSC2 | 1574191.94
RO Supply -Mech- SSC | 3 | 3 | RO Supply -Mech- SSC3 | 8116147.9035
RO Supply -Mech- SSC | 4 | 4 | RO Supply -Mech- SSC4 | 6312150
RO Supply -Mech- SSC | 5 | 5 | RO Supply -Mech- SSC5 | 2149698.33
RO Pump room - SSC - price diff. | 1 | 1 | RO Pump room - SSC - price diff.1 | 15849915.53
RO Pump room - SSC - price diff. | 2 | 2 | RO Pump room - SSC - price diff.2 | 918959
RO Pump room - SSC - price diff. | 3 | 3 | RO Pump room - SSC - price diff.3 | 9400325.92
RO Pump room - SSC - price diff. | 4 | 4 | RO Pump room - SSC - price diff.4 | 7294244.17
RO.2 | 1 | 1 | RO.21 | 1e-05
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 10000000
Rolling Mill #4-TRAESUEZ | 1.1 | 1 | Rolling Mill #4-TRAESUEZ1 | 6966551.51
Rolling Mill #4-TRAESUEZ | 2 | 2 | Rolling Mill #4-TRAESUEZ2 | 12106800.04
Rolling Mill #4-TRAESUEZ | 3 | 3 | Rolling Mill #4-TRAESUEZ3 | 10231445.3
Rolling Mill #4-TRAESUEZ | 4 | 4 | Rolling Mill #4-TRAESUEZ4 | 6596541.38
Rolling Mill #4-TRAESUEZ | 5 | 5 | Rolling Mill #4-TRAESUEZ5 | 9293714.72
Rolling Mill #4-TRAESUEZ | 6 | 6 | Rolling Mill #4-TRAESUEZ6 | 4622509.21
Rolling Mill #4-TRAESUEZ | 7 | 7 | Rolling Mill #4-TRAESUEZ7 | 13289718.96
Rolling Mill #4-TRAESUEZ | 8 | 8 | Rolling Mill #4-TRAESUEZ8 | 16970562.32
Rolling Mill #4-TRAESUEZ | 9 | 9 | Rolling Mill #4-TRAESUEZ9 | 15728855.47
Rolling Mill #4-TRAESUEZ | 10 | 10 | Rolling Mill #4-TRAESUEZ10 | 10380808.5
Rolling Mill #4-TRAESUEZ | 11 | 11 | Rolling Mill #4-TRAESUEZ11 | 9072857.69
Rolling Mill #4-TRAESUEZ | 12 | 12 | Rolling Mill #4-TRAESUEZ12 | 13213191.25
Rolling Mill #4-TRAESUEZ | 13 | 13 | Rolling Mill #4-TRAESUEZ13 | 1e-05
Rolling Mill #4-TRAESUEZ | 14 | 14 | Rolling Mill #4-TRAESUEZ14 | 1e-05
Rolling Mill #4-TRAESUEZ | 15 | 15 | Rolling Mill #4-TRAESUEZ15 | 1e-05
Rolling Mill #4-TRAESUEZ | 16 | 16 | Rolling Mill #4-TRAESUEZ16 | 1e-05
Rolling Mill #4-TRAESUEZ | 1 | 1 | Rolling Mill #4-TRAESUEZ1 | 108750000
Royal City | 2 | 2 | Royal City2 | 4892835.45
Royal City | 3 | 3 | Royal City3 | 7926742.1
Royal City | 4 | 4 | Royal City4 | 10437271.65
Royal City | 5 | 5 | Royal City5 | 5169557.65
Royal City | 6 | 6 | Royal City6 | 12495801.4
Royal City | 7 | 7 | Royal City7 | 8703262.4
Royal City | 8 | 8 | Royal City8 | 6085844.5
Royal City | 9 | 9 | Royal City9 | 6397146.2
Royal City | 10 | 10 | Royal City10 | 5786688.5
Royal City | 11 | 11 | Royal City11 | 3482306.95
Royal City | 12 | 12 | Royal City12 | 9822648.05
Royal City | 13 | 13 | Royal City13 | 6339338.45
Royal City | 14 | 14 | Royal City14 | 5980045.3
Royal City | 15 | 15 | Royal City15 | 6570751.8
Royal City | 16 | 16 | Royal City16 | 7847127.4
Royal City | 17 | 17 | Royal City17 | 5868379.55
Royal City | 18 | 18 | Royal City18 | 4501953.5
Royal City | 19 | 19 | Royal City19 | 9999974.75
Royal City | 20 | 20 | Royal City20 | 5072118
Royal City | 21 | 21 | Royal City21 | 5000000
Royal City | 22 | 22 | Royal City22 | 16824453.7
Royal City | 23 | 23 | Royal City23 | 6453450.6
Royal City | 24 | 24 | Royal City24 | 9088642.9
Royal City | 25 | 25 | Royal City25 | 9972683.95
Royal City | 26 | 26 | Royal City26 | 8025338.3
Royal City | 27 | 27 | Royal City27 | 5000000
Royal City | 27.1 | 27 | Royal City27 | 5150000
Royal City | 27.2 | 27 | Royal City27 | 1745943.7
Royal City | 28 | 28 | Royal City28 | 7000000
Royal City | 28.1 | 28 | Royal City28 | 3500306.77
Royal City | 29 | 29 | Royal City29 | 12838209.35
Royal City | 30 | 30 | Royal City30 | 7400000
Royal City | 30.1 | 30 | Royal City30 | 2431952.135
Royal City | 31 | 31 | Royal City31 | 2500000
Royal City | 31.1 | 31 | Royal City31 | 3975508.58
Royal City | 32 | 32 | Royal City32 | 2151533.38
Royal City | 33 | 33 | Royal City33 | 5000000
Royal City | 33.1 | 33 | Royal City33 | 4101413.8171
Royal City | 34 | 34 | Royal City34 | 1294144.2829
Royal City | 34.1 | 34 | Royal City34 | 4079298.6432
Royal City | 35 | 35 | Royal City35 | 3237336.5863
Royal City | 36 | 36 | Royal City36 | 1578133.6205
Royal City | 36.1 | 36 | Royal City36 | 3653291.5695
Royal City | 37 | 37 | Royal City37 | 3663343.67
Royal City | 38 | 38 | Royal City38 | 2267127.88
Royal City | 39 | 39 | Royal City39 | 1002773.1926
Royal City | 40 | 40 | Royal City40 | 955713.1379
Royal City | 40.1 | 40 | Royal City40 | 5023973.5321
Royal City | 41 | 41 | Royal City41 | 5714023.3138
Royal City | 42 | 42 | Royal City42 | 15000000
Royal City | 42.1 | 42 | Royal City42 | 4161782.8
Royal City | 42.2 | 42 | Royal City42 | 16000000
Royal City - Landscape | 1 | 1 | Royal City - Landscape1 | 1782000
Royal City - Landscape | 2 | 2 | Royal City - Landscape2 | 4014037.5
Royal City - Landscape | 3 | 3 | Royal City - Landscape3 | 2421804.9
Royal City - Landscape | 4 | 4 | Royal City - Landscape4 | 4390934.75
Royal City - Landscape | 5 | 5 | Royal City - Landscape5 | 7060326.8
Royal City - Landscape | 6 | 6 | Royal City - Landscape6 | 9240902.25
Royal City - Landscape | 7 | 7 | Royal City - Landscape7 | 5000000
Royal City - Landscape | 7.1 | 7 | Royal City - Landscape7 | 1442723.35
Royal City - Landscape | 8 | 8 | Royal City - Landscape8 | 2161790.65
Royal City - Landscape | 8.1 | 8 | Royal City - Landscape8 | 10194453.1
Royal City - Landscape | 9 | 9 | Royal City - Landscape9 | 4886117.91
Royal City - Landscape | 10 | 10 | Royal City - Landscape10 | 2500000
Royal City - Landscape | 10.1 | 10 | Royal City - Landscape10 | 561010.97
Royal City - Landscape | 11 | 11 | Royal City - Landscape11 | 4947910.42
Royal City - Landscape | 12 | 12 | Royal City - Landscape12 | 5000000
Royal City - Landscape | 12.1 | 12 | Royal City - Landscape12 | 2029456.4155
Royal City - Landscape | 13 | 13 | Royal City - Landscape13 | 2173267.6157
Royal City - Landscape | 14 | 14 | Royal City - Landscape14 | 1308214.7555
Royal City - Landscape | 15 | 15 | Royal City - Landscape15 | 2272705.37
Royal City - Landscape | 16 | 16 | Royal City - Landscape16 | 650222.9433
Royal City - Landscape | 17 | 17 | Royal City - Landscape17 | 1288827.45
Royal City - Landscape | 17.1 | 17 | Royal City - Landscape17 | 1531216.7805
Royal City - Landscape | 18 | 18 | Royal City - Landscape18 | 819297.0816
Royal City - Landscape | 19 | 19 | Royal City - Landscape19 | 1116339.8935
Royal City - Landscape | 20 | 20 | Royal City - Landscape20 | 1105876.6944
Royal City - Landscape | 21 | 21 | Royal City - Landscape21 | 520336.7179
Royal City - Landscape | 21.1 | 21 | Royal City - Landscape21 | 2285976.6862
Royal City - Landscape | 22 | 22 | Royal City - Landscape22 | 1838217.2
Royal City - Landscape | 23 | 23 | Royal City - Landscape23 | 9000000
Royal City - Landscape | 23.1 | 23 | Royal City - Landscape23 | 4000000
Royal City 3 | 3 | 3 | Royal City 33 | 20000000
Royal City 4 | 4 | 4 | Royal City 44 | 20093247.4
Royal City1 | 1 | 1 | Royal City11 | 58500000
Royal City2 | 2 | 2 | Royal City22 | 20000000
Saint Gobain Factory | 1 | 1 | Saint Gobain Factory1 | 103530970.24
Saint Gobain Factory | 2 | 2 | Saint Gobain Factory2 | 26538435
SIEMENS - Sokhna | 1 | 1 | SIEMENS - Sokhna1 | 93300000
SIEMENS - Sokhna | 2 | 2 | SIEMENS - Sokhna2 | 3059283.73
SIEMENS - Sokhna | 3 | 3 | SIEMENS - Sokhna3 | 7201577.05
SIEMENS - Sokhna | 4 | 4 | SIEMENS - Sokhna4 | 11065687.7
SIEMENS - Sokhna | 5 | 5 | SIEMENS - Sokhna5 | 13218163.56
SIEMENS - Sokhna | 6 | 6 | SIEMENS - Sokhna6 | 7060448.908
SIEMENS - Sokhna | 7 | 7 | SIEMENS - Sokhna7 | 8833159.82
SIEMENS - Sokhna | 8 | 8 | SIEMENS - Sokhna8 | 12641621.4
SIEMENS - Sokhna | 9 | 9 | SIEMENS - Sokhna9 | 13673026.82
SIEMENS - Sokhna | 10 | 10 | SIEMENS - Sokhna10 | 6271528.33
SIEMENS - Sokhna | 11 | 11 | SIEMENS - Sokhna11 | 5230123.67
SIEMENS - Sokhna | 12 | 12 | SIEMENS - Sokhna12 | 20041232.56
SIEMENS - Sokhna | 13 | 13 | SIEMENS - Sokhna13 | 17822796.65
SIEMENS - Sokhna | 14 | 14 | SIEMENS - Sokhna14 | 20002003.08
SIEMENS - Sokhna | 15 | 15 | SIEMENS - Sokhna15 | 2699428.63
SIEMENS - Sokhna | 16 | 16 | SIEMENS - Sokhna16 | 25271545.73
SIEMENS - Sokhna | 17 | 17 | SIEMENS - Sokhna17 | 20418831.59
SIEMENS - Sokhna | 18 | 18 | SIEMENS - Sokhna18 | 12124718
SIEMENS - Sokhna | 19 | 19 | SIEMENS - Sokhna19 | 25672200.91
SIEMENS - Sokhna | 20 | 20 | SIEMENS - Sokhna20 | 15319191.73
SIEMENS - Sokhna | 21 | 21 | SIEMENS - Sokhna21 | 888628.7
SIEMENS - Sokhna - Bill | 1 | 1 | SIEMENS - Sokhna - Bill1 | 144907
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 2207548.2
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 1e-05
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 | 1e-05
SMP1 - Revamp | 4 | 4 | SMP1 - Revamp4 | 2647384.8437
SMP1 - Revamp | 5 | 5 | SMP1 - Revamp5 | 2853769.6857
SMP1 - Revamp | 6 | 6 | SMP1 - Revamp6 | 6112062.5631
SMP1 - Revamp | 7 | 7 | SMP1 - Revamp7 | 3154540.1
SMP1 - Revamp | 8 | 8 | SMP1 - Revamp8 | 1992085.4366
SMP1 - Revamp | 1 | 1 | SMP1 - Revamp1 | 11698500
SMP1 - Revamp | 2 | 2 | SMP1 - Revamp2 | 25693427.5
SMP1 - Revamp | 3 | 3 | SMP1 - Revamp3 | 16806572.5
SMP1 - Shut Down | 1 | 1 | SMP1 - Shut Down1 | 5388381.94
SMP1 - Shut Down | 2 | 2 | SMP1 - Shut Down2 | 15140879.8914
SMP1 - Shut Down | 3 | 3 | SMP1 - Shut Down3 | 8648912.9484
SMP1 - Shut Down- Final Retention | 1 | 1 | SMP1 - Shut Down- Final Retention1 | 2700753.58
SMP2 - Shut Down | 2 | 2 | SMP2 - Shut Down2 | 5426194.9513
SMP2 - Shut Down | 3 | 3 | SMP2 - Shut Down3 | 581185.34
SMP2 - Shut Down- Retention release | 1 | 1 | SMP2 - Shut Down- Retention release1 | 553693.36
SMP2 - Shut Down- V.O | 1 | 1 | SMP2 - Shut Down- V.O1 | 20000000
Sodic Club House | 23 | 23 | Sodic Club House23 | 2727407.25
Sodic Club House | 24 | 24 | Sodic Club House24 | 4528572.66
Sodic Club House | 25 | 25 | Sodic Club House25 | 894280.83
Sodic Club House | 26 | 26 | Sodic Club House26 | 2563543.65
Sodic Club House | 27 | 27 | Sodic Club House27 | 7171420.81
Sodic Club House | 28 | 28 | Sodic Club House28 | 3643251.2
Sodic Club House | 29 | 29 | Sodic Club House29 | 2927170
Sodic Club House | 30 | 30 | Sodic Club House30 | 1523667.33
Sodic Club House | 31 | 31 | Sodic Club House31 | 3752933.22
Sodic Club House | 32 | 32 | Sodic Club House32 | 1851323.25
Sodic Club House | 33 | 33 | Sodic Club House33 | 5028067.13
Sodic Club House | 34 | 34 | Sodic Club House34 | 1372787.19
Sodic Club House | 35 | 35 | Sodic Club House35 | 2061960.96
Sodic Club House | 36 | 36 | Sodic Club House36 | 3000000
Sodic Club House | 36.1 | 36 | Sodic Club House36 | 6516540.66
Sodic Club House | 37 | 37 | Sodic Club House37 | 4028521
Sodic Club House - Social Insurance | 1 | 1 | Sodic Club House - Social Insurance1 | 184729.32
Sodic Club House - Social Insurance | 2 | 2 | Sodic Club House - Social Insurance2 | 503082.9
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 6789620.12
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 15638373.66
Sodic Eastown | 3 | 3 | Sodic Eastown3 | 1574016.18
Sodic Eastown | 4 | 4 | Sodic Eastown4 | 25688338.61
Sodic Eastown | 5 | 5 | Sodic Eastown5 | 37056568.4
Sodic Eastown | 6 | 6 | Sodic Eastown6 | 18000000
Sodic Eastown | 6.1 | 6 | Sodic Eastown6 | 10554847.67
Sodic Eastown | 7 | 7 | Sodic Eastown7 | 35000000
Sodic Eastown | 7.1 | 7 | Sodic Eastown7 | 3197130.95
Sodic Eastown | 8 | 8 | Sodic Eastown8 | 46000000
Sodic Eastown | 8.1 | 8 | Sodic Eastown8 | 9532397.61
Sodic Eastown | 9 | 9 | Sodic Eastown9 | 40504812.26
Sodic Eastown | 10 | 10 | Sodic Eastown10 | 32553581.24
Sodic Eastown | 11 | 11 | Sodic Eastown11 | 27179529.3929
Sodic Eastown | 12 | 12 | Sodic Eastown12 | 19553108.79
Sodic Eastown | 13 | 13 | Sodic Eastown13 | 10000000
Sodic Eastown | 13.1 | 13 | Sodic Eastown13 | 6201534.04
Sodic Eastown | 14 | 14 | Sodic Eastown14 | 15000000
Sodic Eastown | 14.1 | 14 | Sodic Eastown14 | 1537461.58
Sodic Eastown | 15 | 15 | Sodic Eastown15 | 12895954
Sodic Eastown | 16 | 16 | Sodic Eastown16 | 30145771.57
Sodic Eastown | 17 | 17 | Sodic Eastown17 | 20000000
Sodic Eastown | 17.1 | 17 | Sodic Eastown17 | 899381.34
Sodic Eastown | 18 | 18 | Sodic Eastown18 | 15000000
Sodic Eastown | 18.1 | 18 | Sodic Eastown18 | 7406610.78
Sodic Eastown | 19 | 19 | Sodic Eastown19 | 25500000
Sodic Eastown | 19.1 | 19 | Sodic Eastown19 | 8917592.72
Sodic Eastown | 20 | 20 | Sodic Eastown20 | 27000000
Sodic Eastown | 20.1 | 20 | Sodic Eastown20 | 4197031.83
Sodic Eastown | 21 | 21 | Sodic Eastown21 | 25000000
Sodic Eastown | 21.1 | 21 | Sodic Eastown21 | 4743783.32
Sodic Eastown | 22 | 22 | Sodic Eastown22 | 15000000
Sodic Eastown | 22.1 | 22 | Sodic Eastown22 | 4964135.7
Sodic Eastown | 23 | 23 | Sodic Eastown23 | 12000000
Sodic Eastown | 23.1 | 23 | Sodic Eastown23 | 7672746.63
Sodic Eastown | 24 | 24 | Sodic Eastown24 | 12000000
Sodic Eastown | 24.1 | 24 | Sodic Eastown24 | 2713744.17
Sodic Eastown | 25 | 25 | Sodic Eastown25 | 15000000
Sodic Eastown | 25.1 | 25 | Sodic Eastown25 | 3632387.16
Sodic Eastown | 26 | 26 | Sodic Eastown26 | 19000000
Sodic Eastown | 26.1 | 26 | Sodic Eastown26 | 13407888.61
Sodic Eastown | 27 | 27 | Sodic Eastown27 | 19000000
Sodic Eastown | 27.1 | 27 | Sodic Eastown27 | 2101612.82
Sodic Eastown | 28 | 28 | Sodic Eastown28 | 30000000
Sodic Eastown | 28.1 | 28 | Sodic Eastown28 | 11708616.23
Sodic Eastown | 29 | 29 | Sodic Eastown29 | 10880905.48
Sodic Eastown | 30 | 30 | Sodic Eastown30 | 20000000
Sodic Eastown | 30.1 | 30 | Sodic Eastown30 | 5479297.36
Sodic Eastown | 31 | 31 | Sodic Eastown31 | 22493923.41
Sodic Eastown | 32 | 32 | Sodic Eastown32 | 15680621.74
Sodic Eastown | 33 | 33 | Sodic Eastown33 | 19311419.98
Sodic Eastown | 34 | 34 | Sodic Eastown34 | 4602037.61
Sodic Eastown | 35 | 35 | Sodic Eastown35 | 12555804.9
Sodic Eastown | 36 | 36 | Sodic Eastown36 | 2350120
Sodic Eastown | 36.1 | 36 | Sodic Eastown36 | 3904269.49
Sodic Eastown | 37 | 37 | Sodic Eastown37 | 5035428.4
Sodic Eastown | 38 | 38 | Sodic Eastown38 | 2231188
Sodic Eastown | 39 | 39 | Sodic Eastown39 | 17894573
Sodic Eastown - Landscape | 1 | 1 | Sodic Eastown - Landscape1 | 1545976.54
Sodic Eastown - Landscape | 2 | 2 | Sodic Eastown - Landscape2 | 2689319.17
Sodic Eastown - Landscape | 3 | 3 | Sodic Eastown - Landscape3 | 5060960.68
Sodic Eastown - Landscape | 4 | 4 | Sodic Eastown - Landscape4 | 4237695.68
Sodic Eastown - Landscape | 5 | 5 | Sodic Eastown - Landscape5 | 2847434.11
Sodic Eastown - Landscape | 6 | 6 | Sodic Eastown - Landscape6 | 1865468.85
Sodic Eastown - Landscape | 7 | 7 | Sodic Eastown - Landscape7 | 2249247.81
Sodic Eastown - Landscape | 8 | 8 | Sodic Eastown - Landscape8 | 8937999.74
Sodic Eastown - Landscape | 9 | 9 | Sodic Eastown - Landscape9 | 837296.03
Sodic Eastown - Landscape | 10 | 10 | Sodic Eastown - Landscape10 | 2965081
Sodic Eastown - Landscape | 11 | 11 | Sodic Eastown - Landscape11 | 970278.45
Sodic Eastown - Landscape | 12 | 12 | Sodic Eastown - Landscape12 | 2038310.81
Sodic Eastown - Landscape | 13 | 13 | Sodic Eastown - Landscape13 | 4532604.51
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 10000000
Sodic Eastown - Social Insurance | 1 | 1 | Sodic Eastown - Social Insurance1 | 849097.69
Sodic Eastown - Social Insurance | 2 | 2 | Sodic Eastown - Social Insurance2 | 59565.32
Sodic Eastown - Social Insurance | 3 | 3 | Sodic Eastown - Social Insurance3 | 3554660.12
Sodic Eastown - Social Insurance | 4 | 4 | Sodic Eastown - Social Insurance4 | 1311245.56
Sodic Eastown - Social Insurance | 5 | 5 | Sodic Eastown - Social Insurance5 | 2324833
Sodic Eastown - Social Insurance | 6 | 6 | Sodic Eastown - Social Insurance6 | 2884335.94
Sodic Eastown - Social Insurance | 7 | 7 | Sodic Eastown - Social Insurance7 | 1801458.51
Sodic Eastown - Social Insurance | 8 | 8 | Sodic Eastown - Social Insurance8 | 1322438.36
Sodic Eastown - Social Insurance | 9 | 9 | Sodic Eastown - Social Insurance9 | 1754521.36
Sodic Eastown - Social Insurance | 10 | 10 | Sodic Eastown - Social Insurance10 | 862557.37
Sodic Eastown - Social Insurance | 11 | 11 | Sodic Eastown - Social Insurance11 | 2423402.76
Sodic Eastown - Social Insurance | 12 | 12 | Sodic Eastown - Social Insurance12 | 2569099.92
Sodic Eastown - Social Insurance | 13 | 13 | Sodic Eastown - Social Insurance13 | 1513109.68
Sodic Eastown - Social Insurance | 14 | 14 | Sodic Eastown - Social Insurance14 | 1540691.11
Sodic Eastown - Social Insurance | 15 | 15 | Sodic Eastown - Social Insurance15 | 2140215.06
Sodic Eastown - Social Insurance | 16 | 16 | Sodic Eastown - Social Insurance16 | 1796921.66
Sodic Eastown - Social Insurance | 17 | 17 | Sodic Eastown - Social Insurance17 | 1371899.5
Sodic Eastown - Social Insurance | 18 | 18 | Sodic Eastown - Social Insurance18 | 327894.39
Sodic Eastown - Social Insurance | 19 | 19 | Sodic Eastown - Social Insurance19 | 944267.32
Sodic Eastown - Social Insurance | 20 | 20 | Sodic Eastown - Social Insurance20 | 1149200.87
Sodic Eastown - Social Insurance | 21 | 21 | Sodic Eastown - Social Insurance21 | 6876328.15
Sodic Eastown | 1 | 1 | Sodic Eastown1 | 122000000
Sodic Eastown | 2 | 2 | Sodic Eastown2 | 5928168
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 16602157.8
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 19087604.3
Sokhna Port Expansion | 3 | 3 | Sokhna Port Expansion3 | 55802951.65
Sokhna Port Expansion | 4 | 4 | Sokhna Port Expansion4 | 16604871.85
Sokhna Port Expansion | 5 | 5 | Sokhna Port Expansion5 | 24339603.2
Sokhna Port Expansion | 5.1 | 5 | Sokhna Port Expansion5 | 19863057.3
Sokhna Port Expansion | 5.2 | 5 | Sokhna Port Expansion5 | 14812304.05
Sokhna Port Expansion | 6 | 6 | Sokhna Port Expansion6 | 4879591.2
Sokhna Port Expansion | 6.1 | 6 | Sokhna Port Expansion6 | 10735001.15
Sokhna Port Expansion | 6.2 | 6 | Sokhna Port Expansion6 | 10594441
Sokhna Port Expansion | 7 | 7 | Sokhna Port Expansion7 | 36803665.95
Sokhna Port Expansion | 8 | 8 | Sokhna Port Expansion8 | 36284090.45
Sokhna Port Expansion | 9 | 9 | Sokhna Port Expansion9 | 30030028.45
Sokhna Port Expansion | 10 | 10 | Sokhna Port Expansion10 | 27461819.5
Sokhna Port Expansion | 11 | 11 | Sokhna Port Expansion11 | 50769799.2
Sokhna Port Expansion | 12 | 12 | Sokhna Port Expansion12 | 70395885.55
Sokhna Port Expansion | 13 | 13 | Sokhna Port Expansion13 | 491489.95
Sokhna Port Expansion | 14 | 14 | Sokhna Port Expansion14 | 6704080.85
Sokhna Port Expansion | 15 | 15 | Sokhna Port Expansion15 | 4368115.65
Sokhna Port Expansion | 16 | 16 | Sokhna Port Expansion16 | 23966243.5
Sokhna Port Expansion | 17 | 17 | Sokhna Port Expansion17 | 14567572.19
Sokhna Port Expansion | 18 | 18 | Sokhna Port Expansion18 | 14135207.0055
Sokhna Port Expansion | 19 | 19 | Sokhna Port Expansion19 | 10049896.61
Sokhna Port Expansion | 20 | 20 | Sokhna Port Expansion20 | 13204353
Sokhna Port Expansion | 21 | 21 | Sokhna Port Expansion21 | 5788234
Sokhna Port Expansion | 22 | 22 | Sokhna Port Expansion22 | 2510900.431
Sokhna Port Expansion | 23 | 23 | Sokhna Port Expansion23 | 568614.519
Sokhna Port Expansion- 100m | 1 | 1 | Sokhna Port Expansion- 100m1 | 39700885.25
Sokhna Port Expansion- 100m | 2 | 2 | Sokhna Port Expansion- 100m2 | 10628517.75
Sokhna Port Expansion- 100m | 3 | 3 | Sokhna Port Expansion- 100m3 | 10464912.35
Sokhna Port Expansion- 100m | 4 | 4 | Sokhna Port Expansion- 100m4 | 8297916
Sokhna Port Expansion- 100m | 5 | 5 | Sokhna Port Expansion- 100m5 | 3240800
Sokhna Port Expansion- 100m | 6 | 6 | Sokhna Port Expansion- 100m6 | 20436714.5
Sokhna Port Expansion- 100m | 7 | 7 | Sokhna Port Expansion- 100m7 | 3976775.9
Sokhna Port Expansion 100m- Escalation | 1 | 1 | Sokhna Port Expansion 100m- Escalation1 | 11758235
Sokhna Port Expansion 100m- Escalation | 2 | 2 | Sokhna Port Expansion 100m- Escalation2 | 6484391
Sokhna Port Expansion- EDECS | 1 | 1 | Sokhna Port Expansion- EDECS1 | 478776
Sokhna Port Expansion- Escalation | 1 | 1 | Sokhna Port Expansion- Escalation1 | 20947176.65
Sokhna Port Expansion- Escalation | 2 | 2 | Sokhna Port Expansion- Escalation2 | 39132293.55
Sokhna Port Expansion- Escalation | 3 | 3 | Sokhna Port Expansion- Escalation3 | 103409321
Sokhna Port Expansion | 1 | 1 | Sokhna Port Expansion1 | 185016019.2
Sokhna Port Expansion | 2 | 2 | Sokhna Port Expansion2 | 33908706
Sokhna Port Expansion-internal roads | 1 | 1 | Sokhna Port Expansion-internal roads1 | 1800470.45
Sokhna Port Expansion-internal roads | 2 | 2 | Sokhna Port Expansion-internal roads2 | 3219.75
Sports Hall - Civil Works | 3 | 3 | Sports Hall - Civil Works3 | 2493330
Sports Hall - Civil Works | 4 | 4 | Sports Hall - Civil Works4 | 10576930
Sports Hall - Civil Works | 5 | 5 | Sports Hall - Civil Works5 | 17108045
Sports Hall - Civil Works | 6 | 6 | Sports Hall - Civil Works6 | 414025
Sports Hall - Finishes | 1 | 1 | Sports Hall - Finishes1 | 1388840
Sports Hall - Finishes | 2 | 2 | Sports Hall - Finishes2 | 13091760
Sports Hall - Finishes | 3 | 3 | Sports Hall - Finishes3 | 7109625
Sports Hall - Finishes | 4 | 4 | Sports Hall - Finishes4 | 3699060
Sports Hall - Finishes - ADD.01 | 1 | 1 | Sports Hall - Finishes - ADD.011 | 5941290
Sports Hall - Finishes - ADD.01 | 2 | 2 | Sports Hall - Finishes - ADD.012 | 2631750
Sports Hall - Finishes - ADD.01 - Final Retention | 1 | 1 | Sports Hall - Finishes - ADD.01 - Final Retention1 | 790505
Sports Hall - Finishes - Landscape | 1 | 1 | Sports Hall - Finishes - Landscape1 | 0.0003
Sports Hall - Finishes - Landscape - Final Retention | 1 | 1 | Sports Hall - Finishes - Landscape - Final Retention1 | 2595335
Sports Hall - Finishes - Social Insurance | 1 | 1 | Sports Hall - Finishes - Social Insurance1 | 12888786
Sports Hall - MEP | 1 | 1 | Sports Hall - MEP1 | 19417720
Sports Hall - MEP | 2 | 2 | Sports Hall - MEP2 | 1103175
Sports Hall - MEP | 1 | 1 | Sports Hall - MEP1 | 47999995
Sports Hall - MEP - Final Retention | 1 | 1 | Sports Hall - MEP - Final Retention1 | 2580450
Suez Intake & P Stations-ABB apply | 1 | 1 | Suez Intake & P Stations-ABB apply1 | 509186.43
Suez Intake & P Stations-ABB apply | 2 | 2 | Suez Intake & P Stations-ABB apply2 | 988420.71
Suez Intake & P Stations-ABB apply | 3 | 3 | Suez Intake & P Stations-ABB apply3 | 1048324.9964
Suez Intake & P Stations-ABB supply | 1 | 1 | Suez Intake & P Stations-ABB supply1 | 5134498.57
Suez Intake & P Stations-ABB supply | 2 | 2 | Suez Intake & P Stations-ABB supply2 | 7437727.82
Suez Intake & P Stations-ABB supply | 3 | 3 | Suez Intake & P Stations-ABB supply3 | 814872.95
Suez Intake & P Stations-ABB supply | 4 | 4 | Suez Intake & P Stations-ABB supply4 | 3667977.98
Suez Intake & P Stations-ABB supply | 8 | 8 | Suez Intake & P Stations-ABB supply8 | 1e-05
Suez Intake & P Stations-ABB-Escalation | 1 | 1 | Suez Intake & P Stations-ABB-Escalation1 | 35028257.79
Suez Intake & P Stations-ABB-Escalation | 2 | 2 | Suez Intake & P Stations-ABB-Escalation2 | 7725580.34
Suez Intake & P Stations-SSC apply | 1 | 1 | Suez Intake & P Stations-SSC apply1 | 1102291.62
Suez Intake & P Stations-SSC apply | 2 | 2 | Suez Intake & P Stations-SSC apply2 | 3020707.78
Suez Intake & P Stations-SSC apply | 3 | 3 | Suez Intake & P Stations-SSC apply3 | 772824.1924
Suez Intake & P Stations-SSC apply | 8 | 8 | Suez Intake & P Stations-SSC apply8 | 1886891.07
Suez Intake & P Stations-SSC supply | 1 | 1 | Suez Intake & P Stations-SSC supply1 | 8726326.42
Suez Intake & P Stations-SSC supply | 2 | 2 | Suez Intake & P Stations-SSC supply2 | 3190893.09
Suez Intake & P Stations-SSC supply | 3 | 3 | Suez Intake & P Stations-SSC supply3 | 283552.06
Suez Intake & P Stations-SSC supply | 4 | 4 | Suez Intake & P Stations-SSC supply4 | 1e-05
Suez Steel Intake & P Stations | 1 | 1 | Suez Steel Intake & P Stations1 | 19045714
Suez Steel Intake & P Stations | 2 | 2 | Suez Steel Intake & P Stations2 | 28804143
Suez Steel Intake & P Stations | 3 | 3 | Suez Steel Intake & P Stations3 | 25468559.95
Suez Steel-Al Baraka | 1 | 1 | Suez Steel-Al Baraka1 | 19326786
Suez Steel-Gas Station | 1 | 1 | Suez Steel-Gas Station1 | 5014142.1
SVC | 1 | 1 | SVC1 | 2216581.5616
SVC | 1 | 1 | SVC1 | 1158731.1
Uptown PK #53 | 25 | 25 | Uptown PK #5325 | 12009168.61
Uptown PK #53 | 26 | 26 | Uptown PK #5326 | 13124888.11
Uptown PK #53 | 27 | 27 | Uptown PK #5327 | 9593936.7945
Uptown PK #53 | 28 | 28 | Uptown PK #5328 | 13320601.43
Uptown PK #53 | 29 | 29 | Uptown PK #5329 | 10942287.56
Uptown PK #53 | 30 | 30 | Uptown PK #5330 | 11348802.26
Uptown PK #53 | 31 | 31 | Uptown PK #5331 | 7033824.83
Uptown PK #53 | 32 | 32 | Uptown PK #5332 | 2358051.13
Uptown PK #53 | 33 | 33 | Uptown PK #5333 | 2690853.59
Uptown PK #53 | 34 | 34 | Uptown PK #5334 | 1431626.0807
Uptown PK #53 | 35 | 35 | Uptown PK #5335 | 2466454.76
Uptown PK #53 | 36 | 36 | Uptown PK #5336 | 2490213.39
Uptown PK #53 | 37 | 37 | Uptown PK #5337 | 1746850.68
Uptown PK #53 | 38 | 38 | Uptown PK #5338 | 1902092.11
Uptown PK #53 | 39 | 39 | Uptown PK #5339 | 943725.79
Uptown PK #53 | 40 | 40 | Uptown PK #5340 | 1435222.17
Uptown PK #53 | 41 | 41 | Uptown PK #5341 | 4202366.45
Uptown PK #53 | 42 | 42 | Uptown PK #5342 | 1380970.95
Uptown PK #53 | 43 | 43 | Uptown PK #5343 | 4834138.97
Uptown PK #62 | 7 | 7 | Uptown PK #627 | 1684908.09
Uptown PK #62 | 8 | 8 | Uptown PK #628 | 2970870.89
Uptown PK #62 | 9 | 9 | Uptown PK #629 | 2124952.16
Uptown PK #62 | 10 | 10 | Uptown PK #6210 | 2207449.91
Uptown PK #62 | 11 | 11 | Uptown PK #6211 | 1524280.94
Uptown PK #62 | 12 | 12 | Uptown PK #6212 | 1565019.14
Uptown PK #62 | 13 | 13 | Uptown PK #6213 | 2219134.03
Uptown PK #62 | 14 | 14 | Uptown PK #6214 | 854854.29
Uptown PK #62 | 15 | 15 | Uptown PK #6215 | 2299870.99
Uptown PK #62 | 16 | 16 | Uptown PK #6216 | 931895.88
Uptown PK #62 | 17 | 17 | Uptown PK #6217 | 419078.79
Uptown PK #62 | 18 | 18 | Uptown PK #6218 | 864260.36
Uptown PK #62 | 19 | 19 | Uptown PK #6219 | 1416810.93
Uptown PK #62 - Retention | 17 | 17 | Uptown PK #62 - Retention17 | 148822.86
Uptown PK #62 - Retention | 18 | 18 | Uptown PK #62 - Retention18 | 504922.64
Wady Halfa | 1 | 1 | Wady Halfa1 | 22733360.9
Wady Halfa | 2 | 2 | Wady Halfa2 | 8196261.85
Wady Halfa | 3 | 3 | Wady Halfa3 | 2807166.9
Wady Halfa | 4 | 4 | Wady Halfa4 | 3015154.3
Wady Halfa | 5 | 5 | Wady Halfa5 | 2984537.1
Wady Halfa | 1 | 1 | Wady Halfa1 | 19000000
Wady Halfa | 2 | 2 | Wady Halfa2 | 11000000
Wady Halfa - Escalation Claim | 1 | 1 | Wady Halfa - Escalation Claim1 | 14076920.26
Wady Halfa - Escalation Claim | 2 | 2 | Wady Halfa - Escalation Claim2 | 10413528.42
Wady Halfa - Stoppage Period | 1 | 1 | Wady Halfa - Stoppage Period1 | 8364831
Western Fence | 1 | 1 | Western Fence1 | 418218.39
Western Fence-PO | 1 | 1 | Western Fence-PO1 | 5200000
Zayed Park | 1 | 1 | Zayed Park1 | 505797
Zayed Park | 2 | 2 | Zayed Park2 | 264423.21

## eslam-to-invoicing
project name | must be
6TH October tunnel | October Under-Railway Tunnel
Abo Ghaleb Bridge | Abo Ghaleb
AEON
Al Jazi | Aljazi Project
Al Jazi - Center Zone | Aljazi Project
Al Jazi - Center Zone-DP | Aljazi Project
Al Jazi - Social Insurance | Aljazi Project
Al Jazi-DP | Aljazi Project
Alfa Lab | Alfa New Central Labs
Allegria-New Modifications
Astoria - Sharm | Astoria Sharm elSheikh
Astoria - Sharm-DP | Astoria Sharm elSheikh
Astoria Hotel | Waldorf Astoria Cairo
Astoria Hotel - DP | Waldorf Astoria Cairo
Astoria Hotel - Final Retention | Waldorf Astoria Cairo
Astoria Hotel - On Account | Waldorf Astoria Cairo
Astoria Hotel - Social Insurrance | Waldorf Astoria Cairo
Astoria Hotel - Spare Parts V.O 137 | Waldorf Astoria Cairo
Astoria Hotel IPCs 15-20 | Waldorf Astoria Cairo
Baraka Land Fence
Benban - Aswan
Benban - Aswan - DP
Cement Plant | Cement Factory-Beni Suef
Cement Plant -Last Claim | Cement Factory-Beni Suef
CFC | CFC Podium 2
CFC - Final Retention | CFC Podium 2
CFC-DP | CFC Podium 2
Comoros - DP | Le Galawa Hotel Resort
Comoros - Off Shore | Le Galawa Hotel Resort
Comoros - On Shore | Le Galawa Hotel Resort
Comoros - On Shore - On Account | Le Galawa Hotel Resort
Creeks - URBN K | Creeks URBN-K
Creeks - URBN K - DP | Creeks URBN-K
Creeks - URBN K - On Account | Creeks URBN-K
Damietta Port - Civil | Damietta Container Termin
Damietta Port - Civil - DP | Damietta Container Termin
Damietta Port - Infra - DP | Damietta Container Termin
DP World Sokhna | DPW Onshore Port & Terminal
DP World Sokhna-AP | DPW Onshore Port & Terminal
DPW - Ph.02 | DP World Basin 2 Ph2
DPW - Ph.02 - DP | DP World Basin 2 Ph2
EGAT Pelletizing Plant | EGAT Pelletizing Plant
EGAT Pelletizing Plant - Admin Building | EGAT Pelletizing Plant
EGAT Pelletizing Plant - Supply | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Concrete Infra | EGAT Pelletizing Plant
EGAT Pelletizing Plant-DP | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Escalation | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Mechanical Installation | EGAT Pelletizing Plant
EGAT Pelletizing Plant-MEP | EGAT Pelletizing Plant
EGAT Pelletizing Plant-MEP Coordination | EGAT Pelletizing Plant
EGAT Pelletizing Plant-On account | EGAT Pelletizing Plant
EGAT Pelletizing Plant-Water Tank | EGAT Pelletizing Plant
EGAT-Asphalt
EGAT-Asphalt - Retenion Release
EGAT-EGAT ON Account
EGAT-Fence
EGAT-Fence - Retenion Release
EGAT-HeliPad
EGAT-Lock & Load | EGAT Lock & Load
EGAT-Lock & Load-AP | EGAT Lock & Load
EGAT-SZ
EGAT-Warehouse
EIPICO | EPICO 3 Facility
EIPICO-DP | EPICO 3 Facility
EIPICO-On Account | EPICO 3 Facility
El Sewedy Uni.-PKG.1 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.1-DP1 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2-DP2 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.2-Social Insurrance | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3 | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3 - On Account | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3-DP | Elsewedy Univ - Enabling Works
El Sewedy Uni.-PKG.3-Social Insurrance | Elsewedy Univ - Enabling Works
Elco Steel | Substation Elco Steel
Elco Steel - ADMIN. | Substation Elco Steel
Elco Steel - MEP | Substation Elco Steel
Elco Steel - MEP - Social Insurance | Substation Elco Steel
Elco Steel - Social Insurance | Substation Elco Steel
Elco Steel EGAT-DP | Substation Elco Steel
Elco Steel V.O | Substation Elco Steel
Elco Steel V.O-DP | Substation Elco Steel
Elco Steel V.O-Infra. Network | Substation Elco Steel
El-Gouna | DoubleTree Mangroovy ElGouna
El-Gouna - DP | DoubleTree Mangroovy ElGouna
El-Gouna - Equip. Rental | DoubleTree Mangroovy ElGouna
El-Gouna - Temp. Fence | DoubleTree Mangroovy ElGouna
EUA-DP
Existing Intake Apply -SSC-Mech
Existing Intake Supply -SSC-Mech
FIEM
FIEM - Retention
FIEM-Site Offices Rental Payment Request
H1 Solaymaneya-MEP
H1 Solaymaneya-MEP-DP
HQ - CFC | ElSewedy HQ Internal Finishing
HQ - CFC - DP | ElSewedy HQ Internal Finishing
HQ - CFC - Retention release | ElSewedy HQ Internal Finishing
HQ - CFC - Social Insurrance | ElSewedy HQ Internal Finishing
HyperOne | HyperOne Zayed Extension
HyperOne-DP | HyperOne Zayed Extension
HyperOne-Steel Supply | HyperOne Zayed Extension
HyperOne-VAT 1,2,3 | HyperOne Zayed Extension
IKEA | IKEA Extension MoA
IKEA-DP | IKEA Extension MoA
IKEA-Retention Release | IKEA Extension MoA
JICA
JICA-Site Offices Rental Payment Request
Kafr Shokr | Kafr Shokr Bridge
Kafr Shokr - Retention Release | Kafr Shokr Bridge
Katameya - Creeks | Kattameya Creeks
Katameya - Creeks - DP | Kattameya Creeks
Katameya - Creeks - DP - Alu Glass | Kattameya Creeks
Katameya - Creeks - On Account | Kattameya Creeks
KFW
KFW-Road Signals
Khatatba Bridge | El Khatatba Bridge
KSA-Tarek AbdelHakim Center
KSA-Tarek AbdelHakim Center - DP
LEKELA | Lekela 250MW Wind Farm
LEKELA - Supply Bill | Lekela 250MW Wind Farm
LEKELA- On Account | Lekela 250MW Wind Farm
LEKELA Remedial | Lekela 250MW Wind Farm
LEKELA Remedial-DP | Lekela 250MW Wind Farm
LEKELA-DP | Lekela 250MW Wind Farm
MDF Factory | MDF Factory
MDF Factory - Equip. | MDF Factory
MDF Factory - Local Fabrication | MDF Factory
MDF Factory-DP | MDF Factory
MDF Factory-F.F V.O-on account | MDF Factory
MDF Factory-Hold Amount release | MDF Factory
MDF Factory-Local Fab.-on account | MDF Factory
MDF Factory-on account | MDF Factory
MDF Factory-on account solera | MDF Factory
MDF Factory-P.O-on account | MDF Factory
Mechanical Installation | EGAT Mechanical Installations
Mechanical Installation-DP | EGAT Mechanical Installations
Mintra
Mintra-DP
Mintra-Hanger 1200m2
Mivida-PK#140 | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#140- Social Insurance | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#140-DP | EMAAR- Pkg 140-ITP-Mivida
Mivida-PK#189 | Mivida BP#189
Mivida-PK#189 - on account | Mivida BP#189
Mivida-PK#189 - Social insurance | Mivida BP#189
Mivida-PK#189-DP | Mivida BP#189
Mobilization
MOC | MOC HQ at Diriyah
MOC - DP | MOC HQ at Diriyah
New Gas Station | New Giza Teaching Hospital
New Giza Hospital | New Giza Teaching Hospital
New Giza Hospital-DP | New Giza Teaching Hospital
New Giza Hospital-On Account | New Giza Teaching Hospital
New Giza Hospital-Social Insurance | New Giza Teaching Hospital
NGU 2 | New Giza 2
NGU 2 - Retension release | New Giza 2
Old H1 remaining IPC
ORA - ZED | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Compansation | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Deficit | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - DP | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - On account | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Social Insurrance | ORA ZED - Ph 01B - Pkgs A&D
ORA - ZED - Landscape | Ora Zed Landscape Ph1
ORA - ZED - Landscape - Deficit | Ora Zed Landscape Ph1
ORA - ZED - Landscape - DP | Ora Zed Landscape Ph1
ORA - ZED - ph.02 | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - Claims | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - Deficit | ORA ZED-Ph 2-Pkgs A&D
ORA - ZED - ph.02 - On Account | ORA ZED-Ph 2-Pkgs A&D
PH.2-El Sewedy Uni. - Enabling | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Enabling - Retention release | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes - on account | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni. - Finishes-Social Insurrance | ESU Ph2-Enabling & Struc
PH.2-El Sewedy Uni.-DP | ESU Ph2-Enabling & Struc
PI Parks - ELSEWEDY
PI Parks - MEP
PI Parks - MEP-DP1
PI Parks - MEP-DP2
PK #107 | EMAAR-PKG#107-MARASSI
PK #117 | EMAAR-PKG117- MARASSI
PK #117 - Social Insurance | EMAAR-PKG117- MARASSI
PK #22 - Social Insurance | EMAAR-PKG#22-MARASSI
PK#22 | EMAAR-PKG#22-MARASSI
PK#32
PKG#101 | EMAAR-PKG# 101-UPTOWN
PKG#101- Social Insurance | EMAAR-PKG# 101-UPTOWN
PKG#101-DP | EMAAR-PKG# 101-UPTOWN
PKG#101-VO1&VO2 AP | EMAAR-PKG# 101-UPTOWN
PKG#144 | EMAAR-PKG# 144, Marassi
PKG#144 - Social Insurance | EMAAR-PKG# 144, Marassi
PKG#144-DP | EMAAR-PKG# 144, Marassi
PKG#162 | EMAAR-Pkg#162/163- Marassi
PKG#162- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#162-DP | EMAAR-Pkg#162/163- Marassi
PKG#163 | EMAAR-Pkg#162/163- Marassi
PKG#163- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#163-DP | EMAAR-Pkg#162/163- Marassi
PKG#177 | EMAAR-Pkg#162/163- Marassi
PKG#177 - DP | EMAAR-Pkg#162/163- Marassi
PKG#177 - on account | EMAAR-Pkg#162/163- Marassi
PKG#177 - SWI 07 | EMAAR-Pkg#162/163- Marassi
PKG#177- Social Insurance | EMAAR-Pkg#162/163- Marassi
PKG#178 | BKG#178-Lagoon Discharge
PKG#178 - DP | BKG#178-Lagoon Discharge
PKG#178- Social Insurance | BKG#178-Lagoon Discharge
PKG#205
PKG#205 - DP
PKG#205-Social Insurance
PKG#220B | SOL Town PKG.220
PKG#220B - DP | SOL Town PKG.220
PKG#45
PKG#58
PKG#85 | EMAAR-PKG#85-UPTOWN
PO#11687
Port Said Silos | Port Said Port Silos
Port Said Silos - Foreigner Supply | Port Said Port Silos
Port Said Silos - Local Supply | Port Said Port Silos
Port Said Silos-DP | Port Said Port Silos
Port Said Silos-On account | Port Said Port Silos
Port Said Silos-Social Insurrance | Port Said Port Silos
PSP Substation
PSP Substation - Beni Suef
PSP Substation - DP
PSP Substation-Retention
Rabigh Ext. - Piles | Rabigh PP - Piling Works
Rabigh Ext. - Piles- DP | Rabigh PP - Piling Works
Rabigh Ext. -Building | Rabigh CCPP-Civil
Rabigh Ext. -Building- DP | Rabigh CCPP-Civil
Radamis-Concrete
Radamis-Concrete-DP
Radamis-H1 Main Builidng
Radamis-H1-On Account
Radamis-Rooms Fitout
Radamis-Rooms Fitout-DP
Radamis-Villas Finishes
Red Sea Museum | Red Sea Museum-Bab El-Bunt
Red Sea Museum - DP | Red Sea Museum-Bab El-Bunt
Ring Road - El Marg | RING ROAD MARYOTIA EXPANSION
Ring Road - El Marg - Retention Release | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib - refund | RING ROAD MARYOTIA EXPANSION
Ring Road - Mounib - Social Insurance | RING ROAD MARYOTIA EXPANSION
RO Apply -Mech- SSC
RO Eriction
RO Pump Room
RO - Supply - Electric
RO Supply -Mech- SSC
RO 2
RO Pump room - SSC - price diff.
RO.2
Rolling Mill #4-TRAESUEZ | EGAT New Rolling Mill 4
Rolling Mill #4-TRAESUEZ -AP | EGAT New Rolling Mill 4
Royal City | Royal City
Royal City - Landscape | Royal City
Royal City-DP 3 | Royal City
Royal City-DP 4 | Royal City
Royal City-DP1 | Royal City
Royal City-DP2 | Royal City
Saint Gobain Factory - DP
SIEMENS - Sokhna
SIEMENS - Sokhna - Bill
SMP1 - Revamp
SMP1 - Revamp - DP
SMP1 - Shut Down
SMP1 - Shut Down- Final Retention
SMP2 - Shut Down
SMP2 - Shut Down- Retention release
SMP2 - Shut Down- V.O
Sodic Club House | Sodic Club House
Sodic Club House - Social Insurance | Sodic Club House
Sodic Eastown | EDNC Retail & Offices Civil
Sodic Eastown - Landscape | EDNC Hardscape Package
Sodic Eastown - On Account | EDNC Retail & Offices Civil
Sodic Eastown - Social Insurance | EDNC Retail & Offices Civil
Sodic Eastown-DP | EDNC Retail & Offices Civil
Sokhna Port Expansion | Sokhna Port Expansion
Sokhna Port Expansion- 100m | Sokhna Port Expansion
Sokhna Port Expansion 100m- Escalation | Sokhna Port Expansion
Sokhna Port Expansion- EDECS | Sokhna Port Expansion
Sokhna Port Expansion- Escalation | Sokhna Port Expansion
Sokhna Port Expansion-AP | Sokhna Port Expansion
Sokhna Port Expansion-internal roads | Sokhna Port Expansion
Sports Hall - Civil Works | Olympic Multi – Sports Hall
Sports Hall - Finishes | Olympic Multi – Sports Hall
Sports Hall - Finishes - ADD.01 | Olympic Multi – Sports Hall
Sports Hall - Finishes - ADD.01 - Final Retention | Olympic Multi – Sports Hall
Sports Hall - Finishes - Landscape | Olympic Multi – Sports Hall
Sports Hall - Finishes - Landscape - Final Retention | Olympic Multi – Sports Hall
Sports Hall - Finishes - Social Insurance | Olympic Multi – Sports Hall
Sports Hall - MEP | Olympic Multi – Sports Hall
Sports Hall - MEP - DP | Olympic Multi – Sports Hall
Sports Hall - MEP - Final Retention | Olympic Multi – Sports Hall
Suez Intake & P Stations-ABB apply
Suez Intake & P Stations-ABB supply
Suez Intake & P Stations-ABB-Escalation
Suez Intake & P Stations-SSC apply
Suez Intake & P Stations-SSC supply
Suez Steel Intake & P Stations-DP
Suez Steel-Al Baraka-DP
Suez Steel-Gas Station-DP
SVC
SVC-DP
Uptown PK #53 | EMAAR-PKG#53-UPTOWN
Uptown PK #62 | EMAAR-PKG#62-UPTOWN
Uptown PK #62 - Retention | EMAAR-PKG#62-UPTOWN
Wady Halfa | Wadi Halfa Port
Wady Halfa - DP | Wadi Halfa Port
Wady Halfa - Escalation Claim | Wadi Halfa Port
Wady Halfa - Stoppage Period | Wadi Halfa Port
Western Fence
Western Fence-PO
Zayed Park