## Sheet1
project | invoice_no. | invoice_month | cut_off_date | submittal_date | duration_of_pay | pay_due_date | approval_date | monthly_amount_approved | cummulative_amount_approved | dp_amount | on_account_amount | net_amount_monthly_approved | material_on_site_cummulative_amount_approved | v.o._cummulative_amount_approved | ncr_cummulative_amount_approved | escalation_cummulative_amount_approved | 1st_retention_cummulative_amount_approved | 2nd_retention_cummulative_amount_approved | total_deductions
6TH October tunnel | 1 | 2022-05-31 | 2022-06-08 | 2022-06-15 | 60 | 2022-08-14 | 2022-09-11 | 842930 | 842930 |  |  | 1520548 | 1367190 | [5 empty] | 0
6TH October tunnel | 2 | 2022-07-31 | 2022-08-10 | 2022-08-21 | 60 | 2022-10-20 | 2022-09-25 | 3756426.15 | 4599356.15 |  |  | 3208372.9 | 921846.75 | [5 empty] | 0
6TH October tunnel | 3 | 2022-08-31 | 2022-09-06 | 2022-09-07 | 60 | 2022-11-06 | [12 empty] | 0
6TH October tunnel | 4 | 2022-09-30 | 2022-10-01 | 2022-11-13 | 60 | 2023-01-12 | 2022-11-14 | 7050454.75 | 11649810.9 |  |  | 5155347.5 | 750750 | [5 empty] | 0
6TH October tunnel | 5 | 2022-10-31 | 2022-11-15 | 2022-11-17 | 60 | 2023-01-16 | 2022-11-25 | 3846689.4 | 15496500.3 |  |  | 3524900.34 | 298295 | [5 empty] | 0
6TH October tunnel | 6 | 2022-12-31 | 2022-12-15 | 2023-01-09 | 60 | 2023-03-10 | 2023-02-12 | 1899766.7 | 17396267 |  |  | 1337162.6 | [6 empty] | 0
Abo Ghaleb Bridge | 1 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 60 | 2022-04-04 | [12 empty] | 0
Abo Ghaleb Bridge | 2 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 3079766.7 | 15845653.7 |  |  | 2494611.027 | [6 empty] | 0
Abo Ghaleb Bridge | 3 | 2022-03-31 | 2022-03-31 | 2022-04-04 | 60 | 2022-06-03 | 2022-04-04 | 3857104.5 | 19702758.2 |  |  | 3124254.645 | [6 empty] | 0
Abo Ghaleb Bridge | 4 | 2022-04-30 | 2022-04-30 | 2022-04-15 | 60 | 2022-06-14 | 2022-08-09 | 17739438 | 37442196.2 |  |  | 6555212.9406 | [6 empty] | 0
Abo Ghaleb Bridge | 5 | 2022-07-31 | 2022-07-31 | 2022-08-21 | 60 | 2022-10-20 | 2022-08-21 | 2031888 | 39474084.2 |  |  | 1645829.28 | [6 empty] | 0
Abo Ghaleb Bridge | 6 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 | [12 empty] | 0
AEON | 1 | 2020-09-30 | 2020-09-16 | 2020-09-20 | 56 | 2020-11-15 | 2020-09-22 | 1325211.2762 | 1325211.2762 |  |  | 1264914.16 | [6 empty] | 0
AEON | 2 | 2020-10-31 | 2020-11-03 | 2020-11-03 | 56 | 2020-12-29 | 2020-12-15 | 1613181.4 | 2938392.6762 |  |  | 1513146.56 | [6 empty] | 0
AEON | 3 | 2020-12-31 | 2020-12-20 | 2020-12-21 | 56 | 2021-02-15 | 2021-01-04 | 799158.9955 | 3737551.6717 |  |  | 780253.0677 | 20153.7514 | [5 empty] | 27500
AEON | 4 | 2021-02-28 | 2021-02-28 | 2021-06-24 | 56 | 2021-08-19 | [12 empty] | 0
Al Jazi | 1 | 2018-04-30 | 2018-05-21 | 2018-05-21 | 15 | 2018-06-05 | 2018-06-03 | 9888666.63 | 9888666.63 | 53125000 |  | 2199496 | 0 | [5 empty] | 5395000
Al Jazi | 2 | 2018-05-31 | 2018-06-05 | 2018-06-07 | 15 | 2018-06-22 | 2018-06-26 | 6959342.1 | 16848008.73 |  |  | 2330066 | 0 | [5 empty] | 8409664
Al Jazi | 3 | 2018-06-30 | 2018-07-04 | 2018-07-07 | 15 | 2018-07-22 | 2018-07-25 | 6863084.68 | 23711093.41 |  |  | 3357056.9 | 0 | [5 empty] | 10989780.0001
Al Jazi | 4 | 2018-07-31 | 2018-07-24 | 2018-07-24 | 15 | 2018-08-08 | 2018-07-29 | 6873217.27 | 30584310.68 |  |  | 3867947.36 | 0 | [5 empty] | 12001158.5
Al Jazi | 5 | 2018-07-31 | 2018-08-08 | 2018-08-11 | 15 | 2018-08-26 | 2018-08-30 | 7893070.92 | 38477381.6 |  |  | 4039155 | 1152162.9504 | [5 empty] | 15549196.5
Al Jazi | 6 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 15 | 2018-09-21 | 2018-09-10 | 4850391.56 | 43327773.16 |  |  | 2965400.21 | 1152162.95 | [5 empty] | 16838621.5
Al Jazi | 7 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 15 | 2018-10-17 | 2018-10-16 | 9360993.26 | 52688766.42 |  |  | 4138160 | 782387 | [5 empty] | 19429378.5
Al Jazi | 8 | 2018-10-31 | 2018-10-28 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-06 | 13305889.63 | 65994656.05 |  |  | 7730375.21 | 684096.75 | [5 empty] | 22966415.34
Al Jazi | 9 | 2018-11-30 | 2018-11-19 | 2018-11-19 | 15 | 2018-12-04 | 2018-11-28 | 11249079.12 | 77243735.17 |  |  | 3297350.06 | 504071.29 | [5 empty] | 28710343.34
Al Jazi | 10 | 2018-12-31 | 2018-12-04 | 2018-12-04 | 15 | 2018-12-19 | 2018-12-19 | 7201307.23 | 84445042.4 |  |  | 3398127.58 | 324045.83 | [5 empty] | 32846001.3
Al Jazi | 11 | 2018-12-31 | 2018-12-24 | 2018-12-24 | 15 | 2019-01-08 | 2019-01-08 | 10407080.28 | 94852122.68 |  |  | 4227710.49 | 0.001 | [5 empty] | 37611714.98
Al Jazi | 12 | 2019-01-31 | 2019-01-21 | 2019-01-22 | 15 | 2019-02-06 | 2019-02-04 | 8329656 | 103181778.68 |  |  | 2264521.51 | 0.001 | [5 empty] | 42316559.84
Al Jazi | 13 | 2019-02-28 | 2019-02-17 | 2019-02-19 | 15 | 2019-03-06 | 2019-03-04 | 8749208.76 | 111930987.44 |  |  | 3848045.61 | 347539.5 | [5 empty] | 47070296.16
Al Jazi | 14 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-08 | 9382086.37 | 121313073.81 |  |  | 1995238.89 | 104261.85 | [5 empty] | 52347380.67
Al Jazi | 15 | 2019-04-30 | 2019-04-21 | 2019-04-24 | 15 | 2019-05-09 | 2019-05-09 | 9011217.19 | 130324291 |  |  | 2738501.15 | 208523.7 | [5 empty] | 56948226.2
Al Jazi | 16 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-06-01 | 9502208.88 | 139826499.88 |  |  | 1009779.23 | 0.0001 | [5 empty] | 63851171.86
Al Jazi | 17 | 2019-06-30 | 2019-06-16 | 2019-06-18 | 15 | 2019-07-03 | 2019-07-06 | 7664029.32 | 147490529.2 |  |  | 3577364.85 | 0 | [5 empty] | 67191637.78
Al Jazi | 18 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-07-27 | 7401622.43 | 154892151.63 |  |  | 3297235.7 | [6 empty] | 70366044.94
Al Jazi | 19 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 9504587.63 | 164396739.26 |  |  | 4336532.29 | [6 empty] | 74067058.47
Al Jazi | 20 | 2019-09-30 | 2019-09-30 | 2019-10-07 | 15 | 2019-10-22 | 2019-11-03 | 8799095.49 | 173195834.75 |  |  | 2000000 | [6 empty] | 80216713.09
Al Jazi | 21 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 33097306.6205 | 206293141.3705 |  |  | 5243962.1948 | [6 empty] | 93639432.282
Al Jazi | 22 | 2020-04-30 | 2020-04-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 4356240.1195 | 210649381.49 |  |  | 8742870.72
Al Jazi - Center Zone | 1 | 2019-03-31 | 2019-03-20 | 2019-03-21 | 15 | 2019-04-05 | 2019-04-24 | 2348807.6 | 2348807.6 | 14666580.12 |  | 90608.89 | [6 empty] | 1554730.83
Al Jazi - Center Zone | 2 | 2019-04-30 | 2019-05-09 | 2019-05-12 | 15 | 2019-05-27 | 2019-05-29 | 6291718.01 | 8640525.61 |  |  | 2035039.03 | [6 empty] | 4268341.03
Al Jazi - Center Zone | 3 | 2019-07-31 | 2019-07-15 | 2019-07-15 | 15 | 2019-07-30 | 2019-09-01 | 12038668.84 | 20679194.45 |  |  | 360179.68 | [6 empty] | 12373789.15
Al Jazi - Center Zone | 4 | 2019-08-31 | 2019-08-20 | 2019-08-21 | 15 | 2019-09-05 | 2019-09-10 | 4840645.74 | 25519840.19 |  |  | 1090291.72 | [6 empty] | 15657190.5
Al Jazi - Center Zone | 5 | 2019-09-30 | 2019-09-30 | 2019-10-08 | 15 | 2019-10-23 | 2019-11-03 | 7051826.31 | 32571666.5 |  |  | 1000000 | [6 empty] | 20595342.09
Al Jazi - Center Zone | 6 | 2020-01-31 | 2020-02-12 | 2020-02-12 | 15 | 2020-02-27 | 2020-03-24 | 6082957.03 | 38654623.53 |  |  | -2446690.14 | [6 empty] | 22479352.29
Al Jazi - Center Zone | 7 | 2020-03-31 | 2020-03-21 | 2022-01-02 | 15 | 2022-12-30 | 2022-01-24 | 966768.0649 | 39621391.5949 |  |  | 151431.3187
Alfa Lab | 1 | 2021-10-31 | 2021-10-31 | 2021-12-05 | 30 | 2022-01-04 | [12 empty] | 0
Allegria-New Modifications | 1 | 2019-06-30 | 2019-07-02 | 2019-08-22 | 31 | 2019-09-22 | [12 empty] | 0
Astoria - Sharm | 2 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 42 | 2022-08-16 | 2022-07-06 | 1243970 | 1243970 |  |  | 836570 |  |  |  |  | 65308.425 | 65308.425 | 0
Astoria - Sharm | 3 | 2022-07-31 | 2022-07-31 | 2022-08-03 | 42 | 2022-09-14 | 2022-08-09 | 401082.65 | 1645052.65 |  |  | 269728 |  | 98567.65 |  |  | 21056.84 | 21056.84 | 0
Astoria - Sharm | 4 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 42 | 2022-10-12 | 2022-09-05 | 2440310 | 4085362.65 |  |  | 1641108 |  | 98567.65 |  |  | 128116.275 | 128116.275 | 0
Astoria - Sharm | 5 | 2022-09-30 | 2022-09-30 | 2022-10-04 | 42 | 2022-11-15 | 2022-10-06 | 1055208 | 5140570.65 |  |  | 709627 |  | 98567.65 |  | 33170 | 55398 | 55398 | 0
Astoria - Sharm | 6 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 42 | 2022-12-09 | 2022-10-30 | 314831.49 | 5455402.14 |  |  | 244817 |  | 98567.65 |  |  | 221100 | 221100 | 0
Astoria - Sharm | 7 | 2022-11-30 | 2022-11-28 | 2022-11-28 | 42 | 2023-01-09 | [12 empty] | 0
Astoria - Sharm | 8 | 2023-01-31 | 2023-02-01 | 2023-02-01 | 42 | 2023-03-15 | [12 empty] | 0
Astoria Hotel | 1 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 42 | 2022-03-29 | 2022-02-28 | 6707988.52 | 6707988.52 |  | 2000000 | 4511122 | [6 empty] | 0
Astoria Hotel | 2 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 42 | 2022-04-20 | 2022-03-23 | 3507480.42 | 10215468.94 |  |  | 2448868 | 140761.4 |  |  |  | 191180.79 | 191180.79 | 0
Astoria Hotel | 3 | 2022-03-31 | 2022-03-31 | 2022-04-07 | 42 | 2022-05-19 | 2022-04-21 | 6522225.37 | 16737694.31 |  |  | 5421697 | 3185804.68 |  |  |  | 501707.065 | 501707.065 | 0
Astoria Hotel | 4 | 2022-04-30 | 2022-05-10 | 2022-05-17 | 42 | 2022-06-28 | 2022-05-31 | 5466647.24 | 22204341.55 |  |  | 4634265 | 4790259 | 987281.94 |  |  | 1171022.63 | 1171022.63 | 0
Astoria Hotel | 5 | 2022-05-31 | 2022-06-01 | 2022-06-05 | 42 | 2022-07-17 | 2022-06-28 | 3030560.1014 | 25234901.6514 |  |  | 5818860 | 9900984.5198 | 1091283.222 |  |  | 538643.0456 | 538643.0456 | 0
Astoria Hotel | 6 | 2022-06-30 | 2022-06-28 | 2022-06-29 | 42 | 2022-08-10 | 2022-07-06 | 14829494.3486 | 40064396 |  |  | 8446328.13 | 11427302 | 2183203.94 |  |  | 2103380.5 | 2103380.5 | 0
Astoria Hotel | 7 | 2022-07-31 | 2022-08-03 | 2022-08-04 | 42 | 2022-09-15 | 2022-08-08 | 11030217.63 | 51094613.63 |  |  | 8710615 | 12186248.36 | 2194500 |  |  | 849101.84 | 849101.84 | 0
Astoria Hotel | 8 | 2022-08-31 | 2022-08-20 | 2022-08-25 | 42 | 2022-10-06 | 2022-09-08 | 14516248.37 | 65610862 |  |  | 2805916 | 13343046 | 6856879.13 |  |  | 3444570.26 | 3444570.26 | 0
Astoria Hotel | 9 | 2022-09-30 | 2022-09-15 | 2022-09-21 | 42 | 2022-11-02 | 2022-09-26 | 10555127.63 | 76165989.63 |  |  | 6286403 | 6497174.95 | 1117474.28 |  |  | 713450.5 | 713450.5 | 0
Astoria Hotel | 10 | 2022-09-30 | 2022-09-27 | 2022-10-03 | 42 | 2022-11-14 | 2022-10-06 | 9739259.16 | 85905248.79 |  |  | 4982321 | 7583343.27 | 4748282.13 |  |  | 565619.52 | 565619.52 | 0
Astoria Hotel | 11 | 2022-10-31 | 2022-10-17 | 2022-10-23 | 42 | 2022-12-04 | 2022-10-31 | 22454296.86 | 108359545.65 |  |  | 10757000 | 9996725.48 | 8116978.46 |  |  | 6188712.42 | 6188712.42 | 0
Astoria Hotel | 12 | 2022-10-31 | 2022-10-31 | 2022-11-03 | 42 | 2022-12-15 | 2022-11-10 | 7707398.94 | 116066944.59 |  |  | 2603000 | 7811106.63 | 9547937.37 |  |  | 6484069.92 | 6484069.92 | 0
Astoria Hotel | 13 | 2022-11-30 | 2022-11-19 | 2022-11-22 | 42 | 2023-01-03 | 2022-11-28 | 11273556.71 | 127340501.3 |  |  | 5389256 | 8209371.3 | 13101564.96 |  |  | 7095844.885 | 7095844.885 | 0
Astoria Hotel | 14 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2022-12-20 | 13597376.25 | 140937877.55 |  |  | 6216098 | 8044171.13 | 13024305.91 |  |  | 7801447.13 | 7801447.13 | 0
Astoria Hotel | 15 | 2022-12-31 | 2022-12-31 | 2022-12-26 | 42 | 2023-02-06 | 2023-01-25 | 9032753.11 | 149970630.66 |  |  | 4185662 | 8062383.03 | 14785109.7 |  |  | 8276577.26 | 8276577.26 | 0
Astoria Hotel | 16 | 2023-01-31 | 2023-02-08 | 2023-02-09 | 42 | 2023-03-23 | 2023-02-25 | 9372213.83 | 159342844.49 |  |  | 3225683 | 5542006.23 | 15892420.28 |  |  | 8642599.645 | 8642599.645 | 0
Astoria Hotel | 17 | 2023-02-28 | 2023-03-09 | 2023-03-13 | 42 | 2023-04-24 | 2023-04-02 | 7818140.35 | 167160984.84 |  |  | 2804159 | 3697164.11 | 15797479.81 |  |  | 8960809.91 | 8960809.91 | 0
Astoria Hotel | 18 | 2023-04-30 | 2023-04-19 | 2023-04-19 | 42 | 2023-05-31 | 2023-05-10 | 10420915.55 | 177581900.39 |  |  | 4819756 | 3697164.11 | 22952907.31 |  |  | 9507907.975 | 9507907.975 | 0
Astoria Hotel | 19 | 2023-05-31 | 2023-06-07 | 2023-06-08 | 42 | 2023-07-20 | 2023-06-19 | 12873774.1358 | 190455674.5258 |  |  | 1511334.2104 |  | 28856915.5258 |  |  | 10019924.47 | 10019924.47 | 0
Astoria Hotel | 20 | 2023-06-30 | 2023-07-13 | 2023-07-13 | 42 | 2023-08-24 | 2023-08-02 | 3956219.0142 | 194411893.54 |  |  | 3400772 | 84871.19 | 34031882.79 |  |  | 10210867.97 | 10210867.97 | 0
Astoria Hotel | 21 | 2023-07-31 | 2023-08-15 | 2023-08-15 | 42 | 2023-09-26 | 2023-09-14 | 1422437.2 | 195834330.74 |  |  | 854979 | 84871.19 | 37786420.4 |  |  | 10285545.925 | 10285545.925 | 0
Astoria Hotel | 22 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 42 | 2023-11-13 | 2023-10-14 | 10800888.71 | 206635219.45 |  |  | 9327545.58 |  | 43324930.66 |  |  | 10848349.02 | 10848349.02 | 1170750
Astoria Hotel | 23 | 2023-10-31 | 2023-11-12 | 2023-11-12 | 42 | 2023-12-24 | 2023-11-23 | 13277404.55 | 219912624 |  |  | 17286732.59 |  | 44280344.8 |  | 10667080 | 10985391.04 | 10985391.04 | 8403824.77
Astoria Hotel | 24 | 2023-11-30 | 2023-11-28 | 2023-11-28 | 42 | 2024-01-09 | [12 empty] | 0
Astoria Hotel | 25 | 2023-11-30 | 2023-11-30 | 2024-02-07 | 42 | 2024-03-20 | [12 empty] | 0
Baraka Land Fence | 1 | 2023-10-31 | 2023-10-30 | 2023-11-06 | 42 | 2023-12-18 | 2023-11-06 | 3575400 | 3575400 |  |  | 2645796 | [6 empty] | 0
Baraka Land Fence | 2 | 2023-11-30 | 2023-11-30 | 2023-12-04 | 42 | 2024-01-15 | [12 empty] | 0
Baraka Land Fence | 3 | 2024-02-29 | 2024-03-11 | 2024-03-11 | 42 | 2024-04-22 | 2024-03-20 | 23602796 | 38236396 |  |  | 16535567.88 | [6 empty] | 0
Baraka Land Fence | 4 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-05-21 | 11760884 | 49997280 |  |  | 8703054.16 | [6 empty] | 0
Baraka Land Fence | 5 | 2024-08-31 | 2024-08-20 | 2024-08-20 | 42 | 2024-10-01 | 2024-08-20 | 7617134 | 57614414 |  |  | 5636679.16 | [6 empty] | 0
Benban - Aswan | 2 | 2018-06-30 | 2018-07-11 | 2018-07-11 | 60 | 2018-09-09 | 2018-07-26 | 22287932.1928 | 22287932.1928 |  |  | 21953613.1594 | 0 | [5 empty] | 0
Benban - Aswan | 3 | 2018-07-31 | 2018-07-31 | 2018-08-05 | 60 | 2018-10-04 | 2018-09-11 | 10786951.8956 | 33074884.0884 |  |  | 10577813.1577 | 0 | [5 empty] | 0
Benban - Aswan | 4 | 2018-08-31 | 2018-08-31 | 2018-09-05 | 60 | 2018-11-04 | 2018-09-20 | 15307380.738 | 48382264.8264 |  |  | 15006351.7412 | 0 | [5 empty] | 0
Benban - Aswan | 5 | 2018-09-30 | 2018-09-30 | 2018-10-08 | 60 | 2018-12-07 | 2018-10-30 | 36144803.3444 | 84527068.1708 |  |  | 37440886.7444 | [6 empty] | 0
Benban - Aswan | 6 | 2018-10-31 | 2018-10-31 | 2018-11-11 | 60 | 2019-01-10 | 2018-11-28 | 23770609.3964 | 108297677.5672 |  |  | 23958997.0448 | [6 empty] | 0
Benban - Aswan | 7 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 60 | 2019-02-03 | 2018-12-08 | 25005235.2928 | 133302912.86 |  |  | 25352621.3844 | [6 empty] | 0
Benban - Aswan | 8 | 2018-12-31 | 2019-01-03 | 2019-01-03 | 60 | 2019-03-04 | 2019-01-06 | 27760540.7682 | 161063453.6282 |  |  | 28073115.5265 | [6 empty] | 0
Benban - Aswan | 9 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 60 | 2019-04-01 | 2019-02-03 | 31169325.9933 | 192232779.6215 |  |  | 33103432.2978 | [6 empty] | 0
Benban - Aswan | 10 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 60 | 2019-05-05 | 2019-03-10 | 12107665.0539 | 204340444.6754 |  |  | 12014082.9225 | [6 empty] | 0
Benban - Aswan | 11 | 2019-03-31 | 2019-03-31 | 2019-04-01 | 60 | 2019-05-31 | 2019-04-07 | 2235914.343 | 206576359.0184 |  |  | 2314903.9752 | [6 empty] | 0
Benban - Aswan | 12 | 2019-04-30 | 2019-05-01 | 2019-05-01 | 60 | 2019-06-30 | 2019-05-09 | 15216014.8348 | 221792373.8532 |  |  | 16690051.1455 | [6 empty] | 0
Benban - Aswan | 13 | 2019-05-31 | 2019-05-31 | 2019-05-30 | 60 | 2019-07-29 | 2019-07-11 | 1724157.1613 | 223516531.0145 |  |  | 36947.2012 | [6 empty] | 0
Benban - Aswan | 14 | 2019-06-30 | 2019-07-02 | 2019-07-02 | 60 | 2019-08-31 | 2019-07-11 | 30114 | 223546645.0145 |  |  | 1206378.8856 | [6 empty] | 0
Cement Plant | 14 | 2017-09-30 | 2017-09-25 | 2017-10-03 | 45 | 2017-11-17 | 2017-10-19 | 6421251.87 | 219688342.71 |  |  | 7309725 | [6 empty] | 0
Cement Plant | 15 | 2017-10-31 | 2017-10-25 | 2017-11-02 | 45 | 2017-12-17 | 2017-11-15 | 8583366.193 | 228271708.9079 |  |  | 6696657.1239 | [6 empty] | 139900
Cement Plant | 16 | 2017-11-30 | 2017-11-25 | 2017-12-05 | 45 | 2018-01-19 | 2017-12-14 | 6621784.9509 | 234893493.8588 |  |  | 6990595.3607 | [6 empty] | 149900
Cement Plant | 17 | 2017-12-31 | 2017-12-25 | 2018-01-04 | 45 | 2018-02-18 | 2018-01-15 | 6642565.2352 | 241536059.094 |  |  | 7424114.8339 | [6 empty] | 159900
Cement Plant | 18 | 2018-01-31 | 2018-01-25 | 2018-01-23 | 45 | 2018-03-09 | 2018-01-29 | 5438078.8724 | 246974137.9664 |  |  | 6925479.9129 | 0 | [5 empty] | 185884
Cement Plant | 19 | 2018-02-28 | 2018-02-25 | 2018-02-28 | 45 | 2018-04-14 | 2018-03-17 | 12265173.6434 | 269687311.6098 |  |  | 12791498.7957 | 0 | [5 empty] | 195884
Cement Plant | 20 | 2018-06-30 | 2018-06-25 | 2018-12-04 |  | 2019-01-30 | 2019-01-20 | 4976388.8902 | 274663700.5 |  |  | 10152661.36
CFC | 1 | 2019-11-30 | 2019-11-25 | 2019-12-10 | 60 | 2020-02-08 | 2020-01-12 | 6586123.18 | 6586123.18 | 62134944.55 |  | 6200445.37 | 553645.74 | [5 empty] | 0
CFC | 2 | 2019-12-31 | 2019-12-25 | 2020-01-09 | 60 | 2020-03-09 | 2020-02-11 | 16003200.38 | 22589323.56 | 31067472 |  | 17323666.18 | 4441799.42 | [5 empty] | 143549.58
CFC | 3 | 2020-01-31 | 2020-01-25 | 2020-02-05 | 60 | 2020-04-05 | 2020-03-11 | 16743766.83 | 39333090.39 |  |  | 12263695.26 | 3876592.5 | [5 empty] | 60000
CFC | 4 | 2020-02-29 | 2020-02-25 | 2020-03-11 | 60 | 2020-05-10 | 2020-04-02 | 35226223.2 | 74559313.59 |  |  | 32660833.58 | 8287526.25 | [5 empty] | 60000
CFC | 5 | 2020-03-31 | 2020-03-17 | 2020-03-21 | 60 | 2020-05-20 | 2020-04-22 | 30502560.31 | 105061873.9 |  |  | 24749111.95 | 7691894.47 | [5 empty] | 0
CFC | 6 | 2020-03-31 | 2020-03-25 | 2020-04-07 | 60 | 2020-06-06 | 2020-05-04 | 42011127.9851 | 147073001.8851 |  |  | 31500278.62 | 3638239.2055 | [5 empty] | 60000
CFC | 7 | 2020-04-30 | 2020-04-25 | 2020-05-07 | 60 | 2020-07-06 | 2020-06-04 | 17879880.0649 | 164952881.95 |  |  | 19510038 | 9650322 | [5 empty] | 0
CFC | 8 | 2020-05-31 | 2020-05-25 | 2020-06-08 | 60 | 2020-08-07 | 2020-07-07 | 31008098.6054 | 195960980.5554 |  |  | 21459124.497 | 4559164.5 | [5 empty] | 0
CFC | 9 | 2020-06-30 | 2020-06-25 | 2020-07-01 | 60 | 2020-08-30 | 2020-07-27 | 29660399.8248 | 225621380.3802 |  |  | 24499895.52 | 4522595.5868 | [5 empty] | 0
CFC | 10 | 2020-07-31 | 2020-07-25 | 2020-07-28 | 60 | 2020-09-26 | 2020-08-26 | 46257284.4262 | 271878664.8064 |  |  | 39448595.5711 | [6 empty] | 353049.48
CFC | 11 | 2020-08-31 | 2020-08-25 | 2020-08-31 | 60 | 2020-10-30 | 2020-09-29 | 22706553.5236 | 294585218.33 |  |  | 18030565.73 | 5378850.75 | [5 empty] | 0
CFC | 12 | 2020-09-30 | 2020-09-25 | 2020-10-07 | 60 | 2020-12-06 | 2020-11-04 | 35304714.2417 | 329889932.5717 |  |  | 29691194.9757 | 5192537.25 | [5 empty] | 0
CFC | 13 | 2020-10-31 | 2020-10-25 | 2020-11-05 | 60 | 2021-01-04 | 2020-12-09 | 13502068.4452 | 343392001.0169 |  |  | 23213755.7909 | 19923580.7274 | [5 empty] | 0
CFC | 14 | 2020-11-30 | 2020-11-25 | 2020-12-05 | 60 | 2021-02-03 | 2021-01-11 | 29172801.673 | 372564802.6899 |  |  | 19708944.2711 | 14613590.8525 | [5 empty] | 0
CFC | 15 | 2020-12-31 | 2020-12-25 | 2021-01-06 | 60 | 2021-03-07 | 2021-02-22 | 46288367.9197 | 418853170.6096 |  |  | 40379659.8985 | 17260909.7245 | [5 empty] | 1045046
CFC | 16 | 2021-01-31 | 2021-01-25 | 2021-02-03 | 60 | 2021-04-04 | 2021-03-21 | 25170121.1048 | 444023291.7144 |  |  | 22871121.15 | 19535751.2059 | [5 empty] | 0
CFC | 17 | 2021-01-31 | 2021-02-10 | 2021-02-15 | 60 | 2021-04-16 | 2021-03-25 | 23196101.9456 | 467219393.66 |  |  | 15047803.36 | 14368442.92 | [5 empty] | 0
CFC | 18 | 2021-02-28 | 2021-02-25 | 2021-03-02 | 60 | 2021-05-01 | 2021-04-06 | 16880809.49 | 484100203.15 |  |  | 12196441.11 | 14078602.67 | [5 empty] | 0
CFC | 19 | 2021-03-31 | 2021-03-10 | 2021-03-17 | 60 | 2021-05-16 | 2021-04-20 | 20398722.16 | 504498925.31 |  |  | 14008565.71 | 10502130.78 | [5 empty] | 0
CFC | 20 | 2021-03-31 | 2021-03-25 | 2021-03-29 | 60 | 2021-05-28 | 2021-05-24 | 23102145.85 | 527601071.16 |  |  | 23721354.77 | 16161812.22 | [5 empty] | 992616.34
CFC | 21 | 2021-04-30 | 2021-04-10 | 2021-04-15 | 60 | 2021-06-14 | 2021-06-17 | 23568050.8 | 551169121.96 |  |  | 17156225.13 | 15788492.2694 | [5 empty] | 3023908.26
CFC | 22 | 2021-04-30 | 2021-04-25 | 2021-05-06 | 60 | 2021-07-05 | 2021-06-29 | 19833699.32 | 571002821.28 |  |  | 13410069.82 | 12047992.86 | [5 empty] | 0
CFC | 23 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 60 | 2021-08-29 | 2021-08-18 | 19569971.41 | 590572792.69 |  |  | 15440458.92 | 9696296.63 | [5 empty] | 0
CFC | 24 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 60 | 2021-09-13 | 2021-09-23 | 14455028.52 | 605027821.21 |  |  | 7464840.35 | 5161877.98 | [5 empty] | 5612498.72
CFC | 25 | 2021-07-31 | 2021-08-10 | 2021-08-16 | 60 | 2021-10-15 | 2021-10-25 | 13190112.67 | 618217933.88 |  |  | 9682524.47 | 1715079.08 | [5 empty] | 0
CFC | 26 | 2021-08-31 | 2021-08-25 | 2021-09-02 | 60 | 2021-11-01 | 2021-11-18 | 6460765.9427 | 624678699.8227 |  |  | 2397254.3033 | 200294.3722 | [5 empty] | 0
CFC | 27 | 2021-09-30 | 2021-09-10 | 2021-09-19 | 60 | 2021-11-18 | 2021-11-22 | 7714993.7673 | 632393693.59 |  |  | 10793868.55 | [6 empty] | 4776768.68
CFC | 28 | 2021-09-30 | 2021-09-14 | 2022-03-07 | 60 | 2022-05-06 | 2022-05-09 | 5026145.47 | 637419839.06 |  |  | 10367935.42 |  |  |  |  | 16732270.78 | 16732270.78 | 0
CFC | 29 | 2021-09-30 | 2021-09-14 | 2022-10-03 | 60 | 2022-12-02 | [12 empty] | 0
Comoros - Off Shore | 1 | 2022-06-30 | 2022-06-23 | 2022-06-23 | 45 | 2022-08-07 | [12 empty] | 0
Comoros - Off Shore | 2 | 2023-01-31 | 2023-01-28 | 2023-03-21 | 45 | 2023-05-05 | 2023-03-21 | 1137692.89 | 4331928.01 |  |  | 910154.31 | [6 empty] | 0
Comoros - Off Shore | 3 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 | [12 empty] | 0
Comoros - On Shore | 1 | 2023-01-31 | 2023-01-28 | 2023-03-23 | 45 | 2023-05-07 | 2023-03-23 | 1038550.94 | 1038550.94 |  | 263708.26 | 830840.75 | [6 empty] | 0
Comoros - On Shore | 2 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 45 | 2023-11-17 | 2023-10-12 | 506813.73 | 1545364.67 |  |  | 405450.99 | [6 empty] | 0
Creeks - URBN K | 1 | 2023-03-31 | 2023-04-10 | 2023-04-13 | 54 | 2023-06-06 | 2023-05-17 | 6070824.52 | 6070824.52 |  | 57750000 | 10729515.71 | 4917870 |  |  | 1412647.23 | 116454.43 | 116454.43 | 0
Creeks - URBN K | 2 | 2023-04-30 | 2023-05-10 | 2023-05-17 | 54 | 2023-07-10 | 2023-06-01 | 24895588.2 | 30966412.72 |  |  | 3863139.56 |  |  |  | 9774769.5 | 529152.325 | 529152.325 | 0
Creeks - URBN K | 3 | 2023-05-31 | 2023-06-10 | 2023-06-13 | 54 | 2023-08-06 | 2023-06-18 | 40661954.88 | 71628367.6 |  |  | 21808950.42 |  |  |  | 10182390.98 | 1536149.435 | 1536149.435 | 0
Creeks - URBN K | 4 | 2023-06-30 | 2023-07-10 | 2023-07-11 | 54 | 2023-09-03 | 2023-07-19 | 25969563.12 | 97597930.72 |  |  | 8830426.33 |  |  |  | 11215823.74 | 2159552.5 | 2159552.5 | 0
Creeks - URBN K | 5 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 54 | 2023-10-07 | 2023-08-23 | 21068069.1 | 118665999.82 |  |  | 13533059.96 | 8750053.42 |  |  | 12015310.55 | 2666267.23 | 2666267.23 | 0
Creeks - URBN K | 6 | 2023-08-31 | 2023-09-13 | 2023-09-14 | 54 | 2023-11-07 | 2023-09-27 | 18829649.55 | 137495649.37 |  |  | 19608846.96 | 11186650.81 |  |  | 14124627.7 | 3084275.5 | 3084275.5 | 0
Creeks - URBN K | 7 | 2023-09-30 | 2023-10-13 | 2023-10-15 | 54 | 2023-12-08 | 2023-11-02 | 18845217.25 | 156340866.62 |  |  | 16761479.32 | 10998840.9 |  |  | 15355016.01 | 3524646.26 | 3524646.26 | 0
Creeks - URBN K | 8 | 2023-10-31 | 2023-10-13 | 2023-11-15 | 54 | 2024-01-08 | 2023-12-02 | 21024971.71 | 177365838.33 |  |  | 16707965 | 8849533.16 | 524238 |  | 16370912 | 8023534 |  | 0
Creeks - URBN K | 9 | 2023-11-30 | 2023-12-13 | 2023-12-17 | 54 | 2024-02-09 | 2023-12-28 | 18661864.22 | 196027702.55 |  |  | 16997068.33 | 8808386.74 | 549978 |  | 19145680.99 | 8813027.1 |  | 0
Creeks - URBN K | 10 | 2023-12-31 | 2024-01-13 | 2024-01-15 | 54 | 2024-03-09 | 2024-03-15 | 32359750.94 | 228387453.49 |  |  | 19246723.67 | 16680489.26 | 713540 |  | 34117344 | 9677828.4 |  | 0
Creeks - URBN K | 11 | 2024-01-31 | 2024-02-13 | 2024-02-15 | 54 | 2024-04-09 | 2024-03-10 | 19399852.91 | 247787306.4 |  |  | 11569432.7 | 11166359.72 | 713540 |  | 34372400 | 10635068.27 |  | 0
Creeks - URBN K | 12 | 2024-02-29 | 2024-03-13 | 2024-03-16 | 54 | 2024-05-09 | 2024-04-03 | 13939506.69 | 261726813.09 |  |  | 8618325.74 | 7367986.2 | 777032.73 |  | 35392063.88 | 11277885.86 |  | 0
Creeks - URBN K | 13 | 2024-03-31 | 2024-03-13 | 2024-04-17 | 54 | 2024-06-10 | 2024-04-24 | 17837569.29 | 279564382.38 |  |  | 23221916.29 | 13337407.07 | 777032 |  | 42980609.88 | 11790337 |  | 0
Creeks - URBN K | 14 | 2024-04-30 | 2024-05-13 | 2024-05-16 | 54 | 2024-07-09 | 2024-05-22 | 11923940.57 | 291488322.95 |  |  | 6223873.19 | 9059823 | 777032.73 |  | 43382302 | 12366449.19 |  | 0
Creeks - URBN K | 15 | 2024-05-31 | 2024-06-13 | 2024-06-11 | 54 | 2024-08-04 | 2024-06-12 | 15151516.49 | 306639839.44 |  |  | 10206848.68 | 4679535.56 | 777032 |  | 43540689 | 13094578 |  | 0
Creeks - URBN K | 16 | 2024-06-30 | 2024-07-13 | 2024-07-15 | 54 | 2024-09-07 | 2024-07-29 | 8934038.52 | 315573877.96 |  |  | 6345313.67 | 2261543.76 | 777032.73 |  | 44277783.1705 | 13525953 |  | 0
Creeks - URBN K | 17 | 2024-07-31 | 2024-08-13 | 2024-08-15 | 54 | 2024-10-08 | 2024-09-05 | 8615746.66 | 324189624.62 |  |  | 8554807.45 | 2200139 | 777032 |  | 46059367 | 13867661 |  | 0
Creeks - URBN K | 18 | 2024-08-31 | 2024-09-13 | 2024-09-15 | 54 | 2024-11-08 | 2024-09-25 | 9557078 | 333746702.62 |  |  | 9363449.62 | 2027936.1 | 777032 |  | 47680035 | 7132240.5 | 7132240.5 | 0
Creeks - URBN K | 19 | 2024-10-31 | 2024-10-13 | 2024-10-15 | 54 | 2024-12-08 | 2024-11-02 | 6248543.66 | 339995246.28 |  |  | 6696306.5 | 2452144.43 | 777032 |  | 49061466 | 7253918.5 | 7253918.5 | 0
Creeks - URBN K | 20 | 2024-11-30 | 2024-11-13 | 2024-11-14 | 54 | 2025-01-07 | [12 empty] | 0
Damietta Port - Civil | 2 | 2024-10-31 | 2024-10-17 | 2024-10-17 | 42 | 2024-11-28 | [12 empty] | 0
Damietta Port - Civil | 3 | 2024-10-31 | 2024-10-30 | 2024-10-30 | 42 | 2024-12-11 | [12 empty] | 0
Damietta Port - Civil - DP | 1 | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 | [12 empty] | 0
Damietta Port - Infra - DP | 1 | 2024-09-30 | 2024-09-24 | 2024-11-14 | 42 | 2024-12-26 | [12 empty] | 0
DP World Sokhna | 1 | 2019-01-31 | 2019-02-04 | 2019-02-04 | 56 | 2019-04-01 | 2019-02-11 | 21619523.77 | 21619523.77 |  |  | 16214642.83 | 0 | [5 empty] | 0
DP World Sokhna | 2 | 2019-02-28 | 2019-02-28 | 2019-03-04 | 56 | 2019-04-29 | 2019-03-05 | 24408793.91 | 46028317.68 |  |  | 18306595.43 | [6 empty] | 0
DP World Sokhna | 3 | 2019-03-31 | 2019-03-31 | 2019-04-02 | 56 | 2019-05-28 | 2019-04-11 | 20754393.51 | 66782711.19 |  |  | 15565795.14 | [6 empty] | 0
DP World Sokhna | 4 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 56 | 2019-06-30 | 2019-05-16 | 37757872.09 | 104540583.28 |  |  | 28318404.08 | [6 empty] | 0
DP World Sokhna | 5 | 2019-05-31 | 2019-05-31 | 2019-06-02 | 56 | 2019-07-28 | 2019-06-16 | 17786446.66 | 122327029.94 |  |  | 13339835 | [6 empty] | 0
DP World Sokhna | 6 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 56 | 2019-09-07 | 2019-08-06 | 33097932.28 | 155424962.22 |  |  | 24823449.22 | [6 empty] | 0
DP World Sokhna | 7 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 56 | 2019-10-01 | 2019-08-22 | 40506959.47 | 195931921.69 |  |  | 30380219.6 | [6 empty] | 0
DP World Sokhna | 8 | 2019-08-31 | 2019-09-05 | 2019-09-05 | 56 | 2019-10-31 | 2019-09-17 | 39363674.8 | 235295596.49 |  |  | 29522756.11 | [6 empty] | 0
DP World Sokhna | 9 | 2019-09-30 | 2019-10-06 | 2019-10-08 | 56 | 2019-12-03 | 2019-10-23 | 54097551.55 | 289393148.04 |  |  | 40573163.66 | [6 empty] | 0
DP World Sokhna | 10 | 2019-10-31 | 2019-11-17 | 2019-11-11 | 56 | 2020-01-06 | 2019-11-24 | 90533235.47 | 379926383.51 |  |  | 67899926.6 | [6 empty] | 0
DP World Sokhna | 11 | 2019-11-30 | 2019-12-12 | 2019-12-12 | 56 | 2020-02-06 | 2019-12-22 | 102020049.91 | 481946433.42 |  |  | 76515037.44 | [6 empty] | 0
DP World Sokhna | 12 | 2019-12-31 | 2020-01-15 | 2020-01-15 | 56 | 2020-03-11 | 2020-02-16 | 148210852.7 | 630157286.12 |  |  | 111158139.52 | [6 empty] | 0
DP World Sokhna | 13 | 2020-01-31 | 2020-02-15 | 2020-02-18 | 56 | 2020-04-14 | 2020-03-16 | 124566872.96 | 754724159.08 |  |  | 93425154.72 | [6 empty] | 0
DP World Sokhna | 14 | 2020-02-29 | 2020-03-17 | 2020-03-17 | 56 | 2020-05-12 | 2020-04-14 | 141052143.0757 | 895776302.1557 |  |  | 105789107.3061 | [6 empty] | 0
DP World Sokhna | 15 | 2020-03-31 | 2020-04-15 | 2020-04-19 | 56 | 2020-06-14 | 2020-05-17 | 110730132.4543 | 1006506434.61 |  |  | 83047599.34 | [6 empty] | 0
DP World Sokhna | 16 | 2020-04-30 | 2020-05-19 | 2020-05-19 | 56 | 2020-07-14 | 2020-06-21 | 86484919.88 | 1092991354.49 |  |  | 64863689.91 | [6 empty] | 0
DP World Sokhna | 17 | 2020-05-31 | 2020-06-18 | 2020-06-18 | 56 | 2020-08-13 | 2020-07-22 | 56454657.9 | 1149446012.39 |  |  | 42340993.43 | [6 empty] | 0
DP World Sokhna | 18 | 2020-06-30 | 2020-07-23 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-19 | 59878397.73 | 1209324410.12 |  |  | 44908798.3 | [6 empty] | 0
DP World Sokhna | 19 | 2020-07-31 | 2020-08-19 | 2020-08-19 | 56 | 2020-10-14 | 2020-09-16 | 34366362.95 | 1243690773.07 |  |  | 25774772.21 | [6 empty] | 0
DP World Sokhna | 20 | 2020-08-31 | 2020-09-17 | 2020-09-17 | 56 | 2020-11-12 | 2020-10-13 | 42996289.46 | 1286687062.53 |  |  | 32247217.1 | [6 empty] | 0
DP World Sokhna | 21 | 2020-09-30 | 2020-10-15 | 2020-10-15 | 56 | 2020-12-10 | 2020-10-28 | 34792442.43 | 1321479504.96 |  |  | 26094331.82 | [6 empty] | 0
DP World Sokhna | 22 | 2020-10-31 | 2020-11-13 | 2020-11-13 | 56 | 2021-01-08 | 2020-12-20 | 23946448.24 | 1345425953.2 |  |  | 17959836.19 | [6 empty] | 0
DP World Sokhna | 23 | 2020-11-30 | 2020-12-10 | 2020-12-15 | 56 | 2021-02-09 | 2021-01-19 | 35871966.38 | 1381297919.58 |  |  | 26903974.78 | [6 empty] | 0
DP World Sokhna | 24 | 2020-12-31 | 2021-01-10 | 2021-01-10 | 56 | 2021-03-07 | 2021-02-15 | 28199021.24 | 1409496940.82 |  |  | 21149265.93 | [6 empty] | 0
DP World Sokhna | 25 | 2021-01-31 | 2021-02-16 | 2021-02-17 | 56 | 2021-04-14 | 2021-03-21 | 13937299.51 | 1423434240.33 |  |  | 10452974.64 | [6 empty] | 0
DP World Sokhna | 26 | 2021-02-28 | 2021-03-17 | 2021-03-25 | 56 | 2021-05-20 | 2021-04-14 | 30564756.18 | 1453998996.51 |  |  | 22923567.13 | [6 empty] | 0
DP World Sokhna | 27 | 2021-03-31 | 2021-04-15 | 2021-04-15 | 56 | 2021-06-10 | 2021-05-19 | 21307969.76 | 1475306966.27 |  |  | 15980977.32 | [6 empty] | 0
DP World Sokhna | 28 | 2021-05-31 | 2021-05-23 | 2021-05-23 | 56 | 2021-07-18 | 2021-06-24 | 27099548.45 | 1502406514.72 |  |  | 20324661.34 | [6 empty] | 0
DP World Sokhna | 29 | 2021-06-30 | 2021-06-24 | 2021-06-24 | 56 | 2021-08-19 | 2021-07-30 | 27690935.6 | 1530097450.32 |  |  | 20768201.7 | [6 empty] | 0
DP World Sokhna | 30 | 2021-07-31 | 2021-07-29 | 2021-07-29 | 56 | 2021-09-23 | 2021-09-07 | 14579181.6 | 1544676631.92 |  |  | 10934386.2 | [6 empty] | 0
DP World Sokhna | 31 | 2021-08-31 | 2021-09-02 | 2021-09-02 | 56 | 2021-10-28 | 2021-10-11 | 13597917.64 | 1558274549.56 |  |  | 10198438.22 | [6 empty] | 0
DP World Sokhna | 32 | 2021-09-30 | 2021-10-05 | 2021-10-13 | 56 | 2021-12-08 | 2021-12-19 | 16694467.33 | 1574969016.89 |  |  | 12520850.5 | [6 empty] | 0
DP World Sokhna | 33 | 2021-12-31 | 2021-12-22 | 2021-12-22 | 56 | 2022-02-16 | 2022-01-11 | 20335452.71 | 1595304469.6 |  |  | 15251589.54 | [6 empty] | 0
DP World Sokhna | 34 | 2022-03-31 | 2022-04-06 | 2022-04-06 | 56 | 2022-06-01 | 2022-04-12 | 12548237.84 | 1607852707.44 |  |  | 9025252.81 |  |  |  |  | 80392635.37 | 80392635.37 | 0
DP World Sokhna | 35 | 2022-04-30 | 2022-05-15 | 2022-05-15 | 56 | 2022-07-10 | 2022-06-08 | 3275655.02 | 1611128362.46 |  |  | 2948089.53 |  | 37040890.72 |  |  | 80556418.125 | 80556418.125 | 0
DP World Sokhna | 36 | 2022-05-31 | 2022-06-08 | 2022-06-08 | 56 | 2022-08-03 | [12 empty] | 0
DP World Sokhna | 37 | 2023-02-28 | 2023-02-19 | 2023-02-19 | 56 | 2023-04-16 | [12 empty] | 0
DPW - Ph.02 | 1 | 2023-01-31 | 2023-01-25 | 2023-01-31 | 56 | 2023-03-28 | 2023-02-16 | 23907099.3 | 23907099.3 |  |  | 21516389.4 |  |  |  |  | 1195354.95 | 1195354.95 | 0
DPW - Ph.02 | 2 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 56 | 2023-04-27 | 2023-03-22 | 30365704.8 | 54272804.1 |  |  | 19188213.6 |  |  |  |  | 2713640.25 | 2713640.25 | 0
DPW - Ph.02 | 3 | 2023-03-31 | 2023-03-25 | 2023-04-03 | 56 | 2023-05-29 | 2023-03-27 | 1809093.47 | 56081897.57 |  |  | 19827820.72 |  |  |  |  | 2804094.925 | 2804094.925 | 0
DPW - Ph.02 | 4 | 2023-04-30 | 2023-04-25 | 2023-05-08 | 56 | 2023-07-03 | 2023-06-08 | 38567084.81 | 94648982.38 |  |  | 28925313.53 |  |  |  |  | 9464898.3 | 9464898.3 | 0
DPW - Ph.02 | 5 | 2023-05-31 | 2023-05-25 | 2023-06-03 | 56 | 2023-07-29 | 2023-06-25 | 77833745.07 | 172482727.45 |  |  | 30561302.57 |  |  |  |  | 8624122.5 | 8624122.5 | 0
DPW - Ph.02 | 6 | 2023-06-30 | 2023-06-25 | 2023-06-26 | 56 | 2023-08-21 | 2023-07-31 | 32227821.34 | 204710548.79 |  |  | 24170866.16 |  |  |  |  | 10235527.455 | 10235527.455 | 0
DPW - Ph.02 | 7 | 2023-07-31 | 2023-07-25 | 2023-08-01 | 56 | 2023-09-26 | 2023-08-28 | 21546507.22 | 226257056.01 |  |  | 16159880.26 |  |  |  |  | 11312852.785 | 11312852.785 | 0
DPW - Ph.02 | 8 | 2023-08-31 | 2023-08-25 | 2023-09-04 | 56 | 2023-10-30 | 2023-09-04 | 27781672.69 | 254038728.7 |  |  | 20836254.44 |  |  |  |  | 12701936.435 | 12701936.435 | 0
DPW - Ph.02 | 9 | 2023-09-30 | 2023-09-30 | 2023-10-03 | 56 | 2023-11-28 | 2023-10-31 | 66926760.56 | 320965489.26 |  |  | 50195070.42 |  |  |  |  | 16048266 | 16048266 | 0
DPW - Ph.02 | 10 | 2023-10-31 | 2023-10-25 | 2023-11-01 | 56 | 2023-12-27 | 2023-11-29 | 59028304.35 | 379993793.61 |  |  | 44271228.34 |  |  |  |  | 18999683 | 18999683 | 0
DPW - Ph.02 | 11 | 2023-11-30 | 2023-11-25 | 2023-11-30 | 56 | 2024-01-25 | 2023-12-31 | 54711779.1 | 434705572.71 |  |  | 40849045.03 |  |  |  |  | 21735278.62 | 21735278.62 | 0
DPW - Ph.02 | 12 | 2023-12-31 | 2023-12-25 | 2024-01-01 | 56 | 2024-02-26 | 2024-02-04 | 17644384.08 | 452349956.79 |  |  | 15879945.92 |  | 25824647.96 |  |  | 22617497.855 | 22617497.855 | 0
DPW - Ph.02 | 13 | 2024-02-29 | 2024-03-09 | 2024-03-09 | 56 | 2024-05-04 | 2024-04-01 | 13655091.11 | 466005047.9 |  |  | 18632592.11 |  | 44215690.5 |  |  | 33822947.025 | 33822947.025 | 0
DPW - Ph.02 | 14 | 2024-02-29 | 2024-03-10 | 2024-03-13 | 56 | 2024-05-08 | 2024-05-14 | -0.0001 | 466005047.9 |  |  | 35418927.4 |  | 30459697.9 |  |  | 23300252.395 | 23300252.395 | 0
EGAT Pelletizing Plant | 1 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-15 | 5145072.89 | 5145072.89 | 10000000 |  | 4887819.25 | [6 empty] | 0
EGAT Pelletizing Plant | 2 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 10496612.58 | 15641685.47 | 2000000 |  | 10124222.67 | [6 empty] | 0
EGAT Pelletizing Plant | 3 | 2021-07-31 | 2021-07-31 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 4383722.29 | 20025407.76 | 5000000 |  | 4165165.88 | [6 empty] | 0
EGAT Pelletizing Plant | 4 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-27 | 6320391.6 | 26345799.36 | 20500000 |  | 6104444.17 | [6 empty] | 0
EGAT Pelletizing Plant | 5 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-20 | 14624189 | 40969988.36 | 28804143.3 |  | 14109093.06 | [6 empty] | 0
EGAT Pelletizing Plant | 6 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-14 | 11102739.54 | 52072727.9 | 100000000 |  | 10385277.48 | [6 empty] | 0
EGAT Pelletizing Plant | 7 | 2021-11-30 | 2021-12-05 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-20 | 14005522.66 | 66078250.56 | 100000000 |  | 13304274.45 | [6 empty] | 0
EGAT Pelletizing Plant | 8 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-18 | 12121253.25 | 78199503.81 | 200000000 |  | 11576342.49 | [6 empty] | 0
EGAT Pelletizing Plant | 9 | 2022-01-31 | 2022-02-05 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 15797419.96 | 93996923.77 | 26309409.25 |  | 15046421.2 | [6 empty] | 0
EGAT Pelletizing Plant | 10 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-04-12 | 13671163.11 | 107668086.88 |  |  | 13017478.47 | [6 empty] | 0
EGAT Pelletizing Plant | 11 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-21 | 14893958.07 | 122562044.95 |  |  | 14300826.37 | [6 empty] | 0
EGAT Pelletizing Plant | 12 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-23 | 8116943.05 | 130678988 |  |  | 7722438.9 |  | 5987660 |  |  |  |  | 0
EGAT Pelletizing Plant | 13 | 2022-05-31 | 2022-06-05 | 2022-06-12 | 42 | 2022-07-24 | 2022-07-05 | 13958441.79 | 144637429.79 |  |  | 13285393.01 |  | 6236391 |  |  |  |  | 0
EGAT Pelletizing Plant | 14 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-23 | 8283062.84 | 152920492.63 |  |  | 7877469.99 |  | 6321993.82 |  |  |  |  | 0
EGAT Pelletizing Plant | 15 | 2022-07-31 | 2022-08-10 | 2022-08-15 | 42 | 2022-09-26 | 2022-08-24 | 20298475.01 | 173218967.64 |  |  | 19389514.84 |  | 7381629.61 |  |  |  |  | 0
EGAT Pelletizing Plant | 16 | 2022-08-31 | 2022-09-10 | 2022-09-20 | 42 | 2022-11-01 | 2022-10-10 | 14282809.35 | 187501776.99 |  |  | 14238994.72 |  | 14084887.93 |  |  |  |  | 0
EGAT Pelletizing Plant | 17 | 2022-10-31 | 2022-10-25 | 2022-10-27 | 42 | 2022-12-08 | 2022-11-23 | 16943574.98 | 204445351.97 |  |  | 16138518.46 |  | 14506110.34 |  |  |  |  | 0
EGAT Pelletizing Plant | 18 | 2022-11-30 | 2022-11-20 | 2022-11-24 | 42 | 2023-01-05 | 2022-12-19 | 13727755.25 | 218173107.22 |  |  | 12845007.22 |  | 14925857.7 |  |  |  |  | 0
EGAT Pelletizing Plant | 19 | 2022-12-31 | 2022-12-27 | 2022-12-27 | 42 | 2023-02-07 | 2023-02-14 | 20329650.19 | 238502757.41 |  |  | 19373062.69 |  | 15524807.77 |  |  |  |  | 0
EGAT Pelletizing Plant | 20 | 2023-03-31 | 2023-03-30 | 2023-03-30 | 42 | 2023-05-11 | [12 empty] | 0
EGAT Pelletizing Plant | 21 | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [12 empty] | 0
EGAT Pelletizing Plant | 22 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [12 empty] | 0
EGAT Pelletizing Plant | 23 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 165505167.47 | 533590339.98 |  |  | 284426280.45 |  | 85167648 |  | 7000000 |  |  | 0
EGAT Pelletizing Plant | 24 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 65988515.57 | 599578855.55 |  |  | 38934626.46 |  | 96518287.15 |  | 7000000 |  |  | 0
EGAT Pelletizing Plant | 25 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [12 empty] | 0
EGAT Pelletizing Plant - Admin Building | 1 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-05-02 | 61566718.68 | 61566718.68 |  |  | 27089356.22 | [6 empty] | 0
EGAT Pelletizing Plant - Admin Building | 2 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 53673231.5 | 115239950.18 |  |  | 23616221.86 | [6 empty] | 0
EGAT Pelletizing Plant - Admin Building | 3 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [12 empty] | 0
EGAT Pelletizing Plant - Supply | 1 | 2023-07-31 | 2023-07-26 | 2023-07-26 | 42 | 2023-09-06 | 2023-07-26 | 1390180.36 | 1390180.36 |  |  | 1584805.61 | [6 empty] | 0
EGAT Pelletizing Plant-Concrete Infra | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [12 empty] | 0
EGAT Pelletizing Plant-Mechanical Installation | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [12 empty] | 0
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-01-31 |  |  | 42 | 1900-02-10
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-02-29 |  |  | 42 | 1900-02-10
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-03-31 |  |  | 42 | 1900-02-10
EGAT Pelletizing Plant-Mechanical Installation |  | 2024-04-30 |  |  | 42 | 1900-02-10
EGAT Pelletizing Plant-MEP | 1 | 2021-04-30 | 2021-04-30 | 2021-05-11 | 42 | 2021-06-22 | 2021-08-25 | 2011978.5 | 2011978.5 |  |  | 2112577.42 | [6 empty] | 0
EGAT Pelletizing Plant-MEP | 2 | 2022-02-28 | 2022-02-22 | 2022-02-24 | 42 | 2022-04-07 | 2022-02-22 | 112937.5 | 2124916 |  |  | 118584.38 | [6 empty] | 0
EGAT Pelletizing Plant-MEP | 3 | 2022-05-31 | 2022-06-05 | 2022-06-06 | 42 | 2022-07-18 | 2023-02-12 | 1723067.19 | 3847983.19 |  |  | 1329462.73 | [6 empty] | 0
EGAT Pelletizing Plant-MEP Coordination | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [12 empty] | 0
EGAT Pelletizing Plant-Water Tank | 1 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-06-22 | 3274479.04 | 3274479.04 |  |  | 3438202.99 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 2 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 42 | 2021-08-11 | 2021-07-12 | 2028589.79 | 5303068.83 |  |  | 2130019.28 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 3 | 2021-07-31 | 2021-08-04 | 2021-08-05 | 42 | 2021-09-16 | 2021-08-19 | 725357.85 | 6028426.68 |  |  | 761625.75 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 4 | 2021-08-31 | 2021-08-31 | 2021-09-01 | 42 | 2021-10-13 | 2021-09-05 | 766173.48 | 6794600.16 |  |  | 804482.15 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 5 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 42 | 2021-11-17 | 2021-10-12 | 923594.34 | 7718194.5 |  |  | 969774.05 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 6 | 2021-10-31 | 2021-11-06 | 2021-11-06 | 42 | 2021-12-18 | 2021-11-09 | 1464316.6 | 9182511.1 |  |  | 1537532.43 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 7 | 2021-11-30 | 2021-12-06 | 2021-12-06 | 42 | 2022-01-17 | 2021-12-09 | 399729.3 | 9582240.4 |  |  | 419715.76 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 8 | 2021-12-31 | 2022-01-05 | 2022-01-06 | 42 | 2022-02-17 | 2022-01-06 | 307226.2 | 9889466.6 |  |  | 322587.51 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 9 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-03-02 | 1064224 | 10953690.6 |  |  | 1117435.2 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 10 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-14 | 3540729.8 | 14494420.4 |  |  | 3717766.29 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 11 | 2022-03-31 | 2022-03-05 | 2022-06-06 | 42 | 2022-07-18 | 2022-08-23 | 3753750.32 | 18248170.72 |  |  | 3941437.84 | [6 empty] | 0
EGAT Pelletizing Plant-Water Tank | 12 | 2022-09-30 | 2022-09-15 | 2022-09-19 | 42 | 2022-10-31 | [12 empty] | 0
EGAT Pelletizing Plant-Water Tank | 13 | 2022-10-31 | 2022-10-10 | 2022-11-01 | 42 | 2022-12-13 | [12 empty] | 0
EGAT Pelletizing Plant-Water Tank | 14 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [12 empty] | 0
EGAT Pelletizing Plant-Water Tank | 15 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 0.19 | 21082133.03 |  |  | 2909387.53 | [6 empty] | 0
EGAT-Asphalt | 1 | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16
EGAT-Fence | 1 | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16
EGAT-Fence | 2 | 2019-08-31 | 2019-08-31 | 2019-09-10 | 15 | 2019-09-25 | 2019-10-08 | -616810.92 | 18362278.12 |  |  | -575046.5692
EGAT-Fence | 3 | 2019-09-30 | 2019-09-30 | 2019-10-14 | 15 | 2019-10-29
EGAT-Fence | 4 | 2019-10-31 | 2019-12-19 | 2020-02-09 | 15 | 2020-02-24
EGAT-HeliPad | 1 | 2019-07-31 | 2019-07-31 | 2019-08-01 | 15 | 2019-08-16
EGAT-HeliPad | 2 | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20
EGAT-Lock & Load | 1 | 2022-01-31 | 2022-02-07 | 2022-02-08 | 42 | 2022-03-22 | 2022-02-24 | 5018202.5 | 5018202.5 |  |  | 4767292.38 | [6 empty] | 0
EGAT-Lock & Load | 2 | 2022-02-28 | 2022-03-05 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-06 | 2362059.16 | 7380261.66 |  |  | 2243956.2 | [6 empty] | 0
EGAT-Lock & Load | 3 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-12 | 1772326.51 | 9152588.17 |  |  | 1683710.18 | [6 empty] | 0
EGAT-Lock & Load | 4 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | [12 empty] | 0
EGAT-Lock & Load | 5 | 2022-05-31 | 2022-05-28 | 2022-06-06 | 42 | 2022-07-18 | 2022-06-07 | 3180176.34 | 13211888.51 |  |  | 3021167.52 | [6 empty] | 0
EGAT-Lock & Load | 6 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-07-06 | 3378839.59 | 16590728.1 |  |  | 3209897.61 | [6 empty] | 0
EGAT-Lock & Load | 7 | 2022-07-31 | 2022-08-10 | 2022-08-16 | 42 | 2022-09-27 | 2022-08-16 | 1415984.07 | 18006712.17 |  |  | 1345184.87 | [6 empty] | 0
EGAT-Lock & Load | 8 | 2022-08-31 | 2022-09-10 | 2022-09-11 | 42 | 2022-10-23 | 2022-09-11 | 2786604.1 | 20793316.27 |  |  | 2647273.89 | [6 empty] | 0
EGAT-Lock & Load | 9 | 2022-09-30 | 2022-09-10 | 2022-10-17 | 42 | 2022-11-28 | 2022-10-18 | 3980460.75 | 24773777.02 |  |  | 3781437.71 | [6 empty] | 0
EGAT-Lock & Load | 10 | 2022-10-31 | 2022-10-31 | 2022-11-01 | 42 | 2022-12-13 | 2022-11-03 | 1157252.56 | 25931029.58 |  |  | 1099389.93 | [6 empty] | 0
EGAT-Lock & Load | 11 | 2022-11-30 | 2022-11-30 | 2022-11-30 | 42 | 2023-01-11 | 2022-12-07 | 1992889.65 | 27923919.23 |  |  | 1893245.16 | [6 empty] | 0
EGAT-Lock & Load | 12 | 2022-12-31 | 2022-12-25 | 2022-12-28 | 42 | 2023-02-08 | 2022-12-28 | 1778896.47 | 29702815.7 |  |  | 1689951.65 | [6 empty] | 0
EGAT-Lock & Load | 13 | 2023-01-31 | 2023-01-31 | 2023-02-01 | 42 | 2023-03-15 | 2023-02-07 | 2116780.43 | 31819596.13 |  |  | 2010941.41 | [6 empty] | 0
EGAT-Lock & Load | 14 | 2023-02-28 | 2023-02-28 | 2023-03-02 | 42 | 2023-04-13 | 2023-03-08 | 2768145.62 | 34587741.75 |  |  | 2629738.34 | [6 empty] | 0
EGAT-Lock & Load | 15 | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [12 empty] | 0
EGAT-Lock & Load | 16 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [12 empty] | 0
EGAT-Lock & Load | 17 | 2024-01-31 | 2024-01-31 | 2024-05-02 | 42 | 2024-06-13 | 2024-02-28 | -100000 | 53900000 |  |  | 18153522.75 | [6 empty] | 0
EGAT-Lock & Load | 18 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 1100000 | 55000000 |  |  | 1134000 | [6 empty] | 0
EGAT-SZ | 1 | 2019-03-31 | 2019-03-27 | 2019-03-27 | 15 | 2019-04-11 | 2019-04-01 | 6085108 | 6085108 |  |  | 4624356.65
EGAT-SZ | 2 | 2019-03-31 | 2019-04-10 | 2019-04-03 | 15 | 2019-04-18
EGAT-SZ | 3 | 2019-06-30 | 2019-06-26 | 2019-08-01 | 15 | 2019-08-16
EGAT-Warehouse | 1 | 2019-08-31 | 2019-09-12 | 2020-02-05 | 15 | 2020-02-20
EIPICO | 1 | 2022-11-30 | 2022-11-25 | 2022-12-19 | 35 | 2023-01-23 | 2022-12-25 | 9332911.16 | 9332911.16 | 83482074.8 |  | 12050858.57 | 2859252.04 | 393834.3 |  |  | 304804.08 | 304804.08 | 0
EIPICO | 2 | 2022-12-31 | 2022-12-25 | 2022-12-27 | 35 | 2023-01-31 | 2023-02-20 | 13142288.21 | 22475199.37 |  |  | 13338534.97 | 3204166.92 | 795852.42 |  |  | 641984.155 | 641984.155 | 0
EIPICO | 3 | 2023-01-31 | 2023-01-25 | 2023-02-12 | 35 | 2023-03-19 | 2023-03-14 | 11426647.21 | 33901846.58 |  |  | 13033884.61 | 4910817.01 | 1876208.86 |  | 611410.75 | 847546.165 | 847546.165 | 0
EIPICO | 4 | 2023-02-28 | 2023-02-28 | 2023-02-27 | 35 | 2023-04-03 | 2023-03-15 | 8374674.1725 | 42276520.7525 |  |  | 7345011.2 | 6456809.6644 | 3032593.7925 |  | 611410.7518 | 1056913.015 | 1056913.015 | 0
EIPICO | 5 | 2023-03-31 | 2023-03-31 | 2023-03-28 | 35 | 2023-05-02 | 2023-04-10 | 13210447.2775 | 55486968.03 |  |  | 10066271.07 | 6862783.17 | 3640633.73 |  | 4882891.89 | 1387174.2 | 1387174.2 | 0
EIPICO | 6 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 35 | 2023-06-05 | 2023-05-17 | 6910722.77 | 62397690.8 |  |  | 5949977.84 | 8009743.26 | 3788186.81 |  | 4882891.89 | 1559942.27 | 1559942.27 | 0
EIPICO | 7 | 2023-05-31 | 2023-05-30 | 2023-06-13 | 35 | 2023-07-18 | 2023-07-16 | 1928406.33 | 64326097.13 |  |  | 6395645.73 | 8718966.12 | 6026736.54 |  | 4882891.89 | 1758820.84 | 1758820.84 | 0
EIPICO | 8 | 2023-06-30 | 2023-06-30 | 2023-07-06 | 35 | 2023-08-10 | 2023-08-31 | 24151774.29 | 88477871.42 |  |  | 20317361.34 | 17971072.1 | 8593156.6 |  | 15010831.83 | 2211946.785 | 2211946.785 | 0
EIPICO | 9 | 2023-07-31 | 2023-07-31 | 2023-08-02 | 35 | 2023-09-06 | 2023-08-22 | 35000000 | 123477871.42 |  |  | 34650000 | 17971072.1 | 43593156.6 |  | 15010831.83 | 3086946.785 | 3086946.785 | 0
EIPICO | 10 | 2023-07-31 | 2023-07-31 | 2023-08-28 | 35 | 2023-10-02 | 2023-10-29 | 9818518.79 | 133296390.21 |  |  | 6328465.78 | 16843609 | 47694027.06 |  | 15663610.71 | 3332409.755 | 3332409.755 | 0
EIPICO | 11 | 2023-09-30 | 2023-09-30 | 2023-10-10 | 35 | 2023-11-14 | 2023-11-28 | 27259074.64 | 160555464.85 |  |  | 30654533.46 | 30897743.79 | 49443090.43 |  | 24919582.39 | 4013886.62 | 4013886.62 | 0
EIPICO | 12 | 2023-10-31 | 2023-10-31 | 2023-10-29 | 35 | 2023-12-03 | 2024-01-02 | 13086699.85 | 173642164.7 |  |  | 25548194.95 | 56153346.77 | 51092750.03 |  | 24919582.39 | 4341054.12 | 4341054.12 | 0
EIPICO | 13 | 2023-11-30 | 2023-11-30 | 2023-12-03 | 35 | 2024-01-07 | 2024-01-01 | 50645327.08 | 224287491.78 |  |  | 3870916.75 | 34066592.92 | 51710056.53 |  | 25596151.45 | 5607188.795 | 5607188.795 | 1e-05
EIPICO | 14 | 2023-12-31 | 2023-12-31 | 2024-01-06 | 35 | 2024-02-10 | 2024-03-07 | 69127504.85 | 293414996.63 |  |  | 26305980.07 | 36975442.25 | 57799027.37 |  | 60908341.96 | 7335374.915 | 7335374.915 | 0
EIPICO | 15 | 2024-01-31 | 2024-01-31 | 2024-02-04 | 35 | 2024-03-10 | 2024-03-20 | 41894786.25 | 335309782.88 |  |  | 29236256.02 | 34393385.98 | 69350170.39 |  | 63104446.32 | 8382744.57 | 8382744.57 | 0
EIPICO | 16 | 2024-03-31 | 2024-03-31 | 2024-04-03 | 35 | 2024-05-08 | 2024-04-24 | 54812520.11 | 390122302.99 |  |  | 26365248.98 | 33031508.83 | 74589819.54 |  | 94064398.16 | 9753057.575 | 9753057.575 | 0
EIPICO | 17 | 2024-04-30 | 2024-04-30 | 2024-05-28 | 35 | 2024-07-02 | 2024-06-13 | 30260072.01 | 420382375 |  |  | 13161378 | 32932557 | 81926235 |  | 110270621 | 10518279.5 | 10518279.5 | 0
EIPICO | 18 | 2024-06-30 | 2024-06-30 | 2024-07-15 | 35 | 2024-08-19 | 2024-07-30 | 61471115.83 | 481853490.83 |  |  | 38010351.15 | 27876972.92 | 86364959.21 |  | 143970319.09 | 12046337.27 | 12046337.27 | 0
EIPICO | 19 | 2024-08-31 | 2024-08-31 | 2024-09-03 | 35 | 2024-10-08 | 2024-10-26 | 35463786.17 | 517317277 |  |  | 22436578.36 | 23341078 | 95950976 |  | 145234855 | 12932931.5 | 12932931.5 | 17754935
EIPICO | 20 | 2024-09-30 | 2024-09-30 | 2024-10-29 | 35 | 2024-12-03 | [12 empty] | 0
El Sewedy Uni.-PKG.1 | 1 | 2018-07-31 | 2018-08-31 | 2018-09-03 | 4 | 2018-10-19 | 2018-10-15 | 2762087.0381 | 2762087.0381 |  |  | 2002513.1 | 0 | [5 empty] | 0
El Sewedy Uni.-PKG.1 | 2 | 2018-09-30 | 2018-10-15 | 2018-10-18 | 4 | 2018-10-29 | 2018-10-25 | 1370079.6319 | 4132166.67 |  |  | 951383.3 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 3 | 2018-10-31 | 2018-11-15 | 2018-11-14 | 4 | 2018-12-01 | 2018-11-27 | 1749696.33 | 5881863 |  |  | 1214989.1272 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 4 | 2018-11-30 | 2018-11-30 | 2018-12-02 | 4 | 2018-12-14 | 2018-12-10 | 1734033.5 | 7615896.5 |  |  | 1204112.8596 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 5 | 2018-12-31 | 2018-12-15 | 2018-12-17 | 4 | 2018-12-22 | 2018-12-18 | 267331.59 | 7883228.09 |  |  | 185635.0557 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 6 | 2018-12-31 | 2018-12-25 | 2018-12-29 | 4 | 2019-01-12 | 2019-01-08 | 205504.28 | 8088732.37 |  |  | 142702.1677 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 7 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 4 | 2019-01-26 | 2019-01-22 | 410253.12 | 8498985.49 |  |  | 284879.76 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 8 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 4 | 2019-02-10 | 2019-02-06 | 339720.12 | 8838705.61 |  |  | 235901.6556 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 9 | 2019-03-31 | 2019-03-25 | 2019-03-26 | 4 | 2019-04-14 | 2019-04-10 | 104805.89 | 8943511.5 |  |  | 72777.3 | [6 empty] | 0
El Sewedy Uni.-PKG.1 | 10 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 4 | 2019-08-11 | 2019-08-07 | 2360 | 8945871.5 |  |  | -8913.92 | [6 empty] | 0
El Sewedy Uni.-PKG.2 | 1 | 2018-09-30 | 2018-09-25 | 2018-09-27 | 17 | 2018-10-14 | 2018-10-18 | 4165158.06 | 4165158.06 |  |  | 3110956.56 | [6 empty] | 0
El Sewedy Uni.-PKG.2 | 2 | 2018-10-31 | 2018-10-31 | 2018-10-31 | 17 | 2018-11-17 | 2018-11-08 | 5976536.23 | 10141694.29 |  |  | 6088678.96 | [6 empty] | 0
El Sewedy Uni.-PKG.2 | 3 | 2018-11-30 | 2018-11-25 | 2018-11-27 | 17 | 2018-12-14 | 2018-12-10 | 4458367.3606 | 14600061.6506 |  |  | 3212953.6168 | 2173392 | [5 empty] | 0
El Sewedy Uni.-PKG.2 | 4 | 2018-12-31 | 2018-12-25 | 2018-12-31 | 17 | 2019-01-17 | 2019-01-10 | 5121900.2295 | 19721961.8801 |  |  | 3208255.2815 | 1556100 | [5 empty] | 0
El Sewedy Uni.-PKG.2 | 5 | 2019-01-31 | 2019-01-25 | 2019-01-31 | 17 | 2019-02-17 | 2019-02-10 | 8018043.8084 | 27740005.6885 |  |  | 4527299.6695 | [6 empty] | 0
El Sewedy Uni.-PKG.2 | 6 | 2019-02-28 | 2019-02-25 | 2019-03-02 | 17 | 2019-03-19 | 2019-03-11 | 8105230.8115 | 35845236.5 |  |  | 7457797.2 | 1404000 | [5 empty] | 0
El Sewedy Uni.-PKG.2 | 7 | 2019-03-31 | 2019-03-25 | 2019-04-08 | 17 | 2019-04-25 | 2019-04-10 | 4929812 | 40775048.5 |  |  | 2278076.6 | 0 | [5 empty] | 0
El Sewedy Uni.-PKG.2 | 8 | 2019-05-31 | 2019-05-23 | 2019-05-23 | 17 | 2019-06-09 | 2019-08-07 | 1755356.8 | 42530405.3 |  |  | 2625161.5 | [6 empty] | 50000
El Sewedy Uni.-PKG.2 | 9 | 2020-03-31 | 2020-07-31 | 2020-03-22 |  | 2020-03-31 | 2020-03-23 | 0 | 42530405.3 |  |  | 1116423.1 | [6 empty] | 0
El Sewedy Uni.-PKG.3 | 1 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 14 | 2019-02-14 | 2019-02-18 | 1805053.3662 | 1805053.3662 | 24971065.75 | 15000000 | 1727255.5662 | [6 empty] | 0
El Sewedy Uni.-PKG.3 | 2 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 14 | 2019-02-16 | 2019-02-19 | 3340179.702 | 3340179.702 | 8000000 |  | 3185421.0011 | [6 empty] | 0
El Sewedy Uni.-PKG.3 | 3 | 2019-02-28 | 2019-02-21 | 2019-02-27 | 14 | 2019-03-13 | 2019-03-12 | 2400436.8318 | 7545669.9 | 12000000 |  | 5785718.6 | 3477943.8 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 4 | 2019-03-31 | 2019-03-21 | 2019-03-24 | 14 | 2019-04-07 | 2019-04-10 | 6026842.9 | 13572512.8 | 4931187 |  | 1785483.1 | 4077447.9 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 5 | 2019-04-30 | 2019-04-21 | 2019-04-23 | 14 | 2019-05-07 | 2019-05-05 | 27458064.6 | 41030577.4 |  |  | 24218860.6 | 16291927.3 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 6 | 2019-05-31 | 2019-05-25 | 2019-06-01 | 14 | 2019-06-15 | 2019-06-16 | 30765208.3 | 71795785.7 |  |  | 26656864.3 | 10815243.6 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 7 | 2019-06-30 | 2019-07-04 | 2019-07-08 | 14 | 2019-07-22 | 2019-07-25 | 41332921.1 | 113128706.8 |  |  | 22410862.51 | 20405227.9 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 8 | 2019-07-31 | 2019-07-31 | 2019-08-08 | 14 | 2019-08-22 | 2019-08-24 | 23588218.3 | 136716925.1 |  |  | 13598061.6 | 16590818.6 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 9 | 2019-08-31 | 2019-08-21 | 2019-08-24 | 14 | 2019-09-07 | 2019-08-28 | 30130968 | 166847893.1 |  |  | 19410255.3 | 4696608.5 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 10 | 2019-08-31 | 2019-09-10 | 2019-09-16 | 14 | 2019-09-30 | 2019-09-29 | 28039187.7 | 194887080.8 |  |  | 20919758.8 | 1904733.1 | [5 empty] | 0
El Sewedy Uni.-PKG.3 | 11 | 2019-10-31 | 2019-10-31 | 2019-12-22 | 14 | 2020-01-05 | 2020-01-01 | 16304632.1 | 211191712.9 |  |  | 2318168.2 | [6 empty] | 3221774.75
El Sewedy Uni.-PKG.3 | 12 | 2019-10-31 | 2019-10-31 | 2020-06-08 | 14 | 2020-06-22 | 2020-06-21 | 0 | 211191712.9 |  |  | 1515470 | [6 empty] | 1706304.8
El Sewedy Uni.-PKG.3 | 13 | 2020-09-30 | 2020-09-17 | 2020-11-15 | 14 | 2020-11-29 | [12 empty] | 0
Elco Steel | 1 | 2017-09-30 | 2017-10-01 | 2017-10-01 | 15 | 2017-10-16 | 2017-10-08 | 17022109.47 | 17022109.47 |  |  | 13617687.58 | [6 empty] | 0
Elco Steel | 2 | 2017-10-31 | 2017-10-25 | 2017-10-25 | 15 | 2017-11-09 | 2017-10-29 | 54045554.24 | 71067663.71 |  |  | 42881105.07 | [6 empty] | 0
Elco Steel | 3 | 2017-11-30 | 2017-11-30 | 2017-11-27 | 15 | 2017-12-12 | 2017-11-28 | 68968024.81 | 140035688.52 |  |  | 54829579.72 | 0 | [5 empty] | 0
Elco Steel | 4 | 2017-12-31 | 2017-12-31 | 2017-12-27 | 15 | 2018-01-11 | 2018-01-02 | 45198074.67 | 185233763.18 |  |  | 35932469.36 | 0 | [5 empty] | 0
Elco Steel | 5 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 15262763.5 | 200496526.68 |  |  | 12133896.98 | 0 | [5 empty] | 0
Elco Steel | 6 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 23107300.22 | 223603826.9 |  |  | 19914658.95 | 0 | [5 empty] | 95644.72
Elco Steel | 7 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 9962100.82 | 233565927.72 |  |  | 7919870.15 | 0 | [5 empty] | 95644.72
Elco Steel | 8 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 7984975.64 | 241550903.36 |  |  | 6348055.64 | 0 | [5 empty] | 95644.72
Elco Steel | 9 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 1027177.94 | 242578081.3 |  |  | 740665.1 | 0 | [5 empty] | 171586.08
Elco Steel | 10 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 5032217.21 | 247610298.51 |  |  | 4000612.68 | 0 | [5 empty] | 171586.08
Elco Steel | 11 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 8902176.76 | 256512475.27 |  |  | 7077230.5163 | 0 | [5 empty] | 171586.08
Elco Steel | 12 | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [12 empty] | 0
Elco Steel | 13 | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 | [12 empty] | 0
Elco Steel | 14 | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [12 empty] | 0
Elco Steel | 15 | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [12 empty] | 0
Elco Steel | 16 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [12 empty] | 0
Elco Steel | 17 | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [12 empty] | 0
Elco Steel - ADMIN. | 1 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 1576783.88 | 1576783.88 |  |  | 1253543.1806 | [6 empty] | 0
Elco Steel - ADMIN. | 2 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 3644932.88 | 5221716.76 |  |  | 2897721.64 | 0 | [5 empty] | 0
Elco Steel - ADMIN. | 3 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 4011218.17 | 9232934.93 |  |  | 3188918.45 | 0 | [5 empty] | 0
Elco Steel - ADMIN. | 4 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 4549688.44 | 13782623.37 |  |  | 3617002.31 | 0 | [5 empty] | 0
Elco Steel - ADMIN. | 5 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 2288094.62 | 16070717.99 |  |  | 1819035.23 | 0 | [5 empty] | 0
Elco Steel - ADMIN. | 6 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 6362324.03 | 22433042.02 |  |  | 5094386.24 | 0 | [5 empty] | 0
Elco Steel - ADMIN. | 7 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 7233482.49 | 29666524.51 |  |  | 5750618.5816 | 0 | [5 empty] | 0
Elco Steel - ADMIN. | 8 | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [12 empty] | 0
Elco Steel - ADMIN. | 9 | 2018-09-30 | 2018-09-30 | 2018-10-10 | 15 | 2018-10-25 | [12 empty] | 0
Elco Steel - ADMIN. | 10 | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [12 empty] | 0
Elco Steel - ADMIN. | 11 | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [12 empty] | 0
Elco Steel - ADMIN. | 12 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [12 empty] | 0
Elco Steel - ADMIN. | 13 | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [12 empty] | 0
Elco Steel - ADMIN. | 14 | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 | [12 empty] | 0
Elco Steel - ADMIN. | 15 | 2019-03-31 | 2019-04-10 | 2019-04-16 | 15 | 2019-05-01 | [12 empty] | 0
Elco Steel - MEP | 1 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 15 | 2018-02-15 | 2018-02-12 | 444736.0027 | 444736.0027 |  |  | 331328.322 | 0 | [5 empty] | 0
Elco Steel - MEP | 2 | 2018-02-28 | 2018-03-04 | 2018-03-04 | 15 | 2018-03-19 | 2018-03-13 | 2764965.97 | 3209701.97 |  |  | 2059899.65 | 0 | [5 empty] | 0
Elco Steel - MEP | 3 | 2018-03-31 | 2018-03-27 | 2018-04-09 | 15 | 2018-04-24 | 2018-04-17 | 2666446.92 | 5876148.87 |  |  | 1986502.96 | 0 | [5 empty] | 0
Elco Steel - MEP | 4 | 2018-04-30 | 2018-04-30 | 2018-05-03 | 15 | 2018-05-18 | 2018-05-26 | 3362790.38 | 9238939.25 |  |  | 2505278.83 | 0 | [5 empty] | 0
Elco Steel - MEP | 5 | 2018-05-31 | 2018-05-31 | 2018-06-07 | 15 | 2018-06-22 | 2018-07-02 | 3275304.26 | 12514243.51 |  |  | 2440101.69 | 0 | [5 empty] | 0
Elco Steel - MEP | 6 | 2018-06-30 | 2018-06-30 | 2018-07-05 | 15 | 2018-07-20 | 2018-07-17 | 2863596.99 | 15377840.5 |  |  | 2133379.78 | 0 | [5 empty] | 0
Elco Steel - MEP | 7 | 2018-07-31 | 2018-07-31 | 2018-08-12 | 15 | 2018-08-27 | 2018-08-26 | 3498188.3161 | 18876028.8161 |  |  | 2606150.307 | 0 | [5 empty] | 0
Elco Steel - MEP | 8 | 2018-08-31 | 2018-09-12 | 2018-09-12 | 15 | 2018-09-27 | [12 empty] | 0
Elco Steel - MEP | 9 | 2018-09-30 | 2018-10-09 | 2018-10-10 | 15 | 2018-10-25 | [12 empty] | 0
Elco Steel - MEP | 10 | 2018-10-31 | 2018-10-31 | 2018-11-12 | 15 | 2018-11-27 | [12 empty] | 0
Elco Steel - MEP | 11 | 2018-11-30 | 2018-11-30 | 2018-12-12 | 15 | 2018-12-27 | [12 empty] | 0
Elco Steel - MEP | 12 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 15 | 2019-01-21 | [12 empty] | 0
Elco Steel - MEP | 13 | 2019-01-31 | 2019-01-31 | 2019-02-13 | 15 | 2019-02-28 | [12 empty] | 0
Elco Steel - MEP | 14 | 2019-02-28 | 2019-02-28 | 2019-03-18 | 15 | 2019-04-02 | [12 empty] | 0
Elco Steel V.O-Infra. Network | 1 | 2019-06-30 | 2019-07-03 | 2019-07-03 | 15 | 2019-07-18
El-Gouna | 1 | 2019-09-30 | 2019-10-15 | 2019-11-04 | 21 | 2019-11-25 | 2019-11-24 | 3393576.42 | 3393576.42 |  |  | 2338174.15 | [6 empty] | 0
El-Gouna | 2 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 21 | 2019-12-08 | 2019-11-24 | 3546875.03 | 6940451.45 |  |  | 3879736.97 | 2084092.99 | [5 empty] | 0
El-Gouna | 3 | 2019-11-30 | 2019-12-15 | 2019-12-16 | 21 | 2020-01-06 | 2019-12-19 | 4290021.36 | 11230472.81 |  |  | 2286139.86 | 1112126.59 | [5 empty] | 10483.55
El-Gouna | 4 | 2019-12-31 | 2020-01-15 | 2020-01-21 | 21 | 2020-02-11 | 2020-01-21 | 2686069.3 | 13916542.11 |  |  | 2572404.48 | 2169673.66 | [5 empty] | 29400.49
El-Gouna | 5 | 2020-01-31 | 2020-02-15 | 2020-02-19 | 21 | 2020-03-11 | 2020-02-23 | 3430037.61 | 17346579.72 |  |  | 1815739.6 | 1374961.99 | [5 empty] | 10483.55
El-Gouna | 6 | 2020-02-29 | 2020-03-15 | 2020-03-18 | 21 | 2020-04-08 | 2020-03-18 | 6540676.19 | 23887255.91 |  |  | 4271724.93 | 1023807.82 | [5 empty] | 29400.49
El-Gouna | 7 | 2020-03-31 | 2020-04-15 | 2020-04-18 | 21 | 2020-05-09 | 2020-04-21 | 3114205.16 | 27001461.07 |  |  | 2145687.36 | 1023807.82 | [5 empty] | 29400.49
El-Gouna | 8 | 2020-06-30 | 2020-07-01 | 2020-07-05 | 21 | 2020-07-26 | 2020-07-06 | 3250029.8 | 30251490.87 |  |  | 1922134.77 | 580535.19 | [5 empty] | 29400.49
El-Gouna | 9 | 2020-07-31 | 2020-08-01 | 2020-07-26 | 21 | 2020-08-16 | 2020-07-27 | 1882490 | 32133980.87 |  |  | 1037007.36 | 203135.69 | [5 empty] | 29400.49
El-Gouna | 10 | 2020-08-31 | 2020-09-01 | 2020-09-05 | 21 | 2020-09-26 | 2020-09-05 | 1889241.5387 | 34023222.4087 |  |  | 1180949.3351 | 27898.992 | [5 empty] | 29400.49
El-Gouna | 11 | 2020-11-30 | 2020-11-30 | 2020-12-09 | 21 | 2020-12-30 | 2020-12-19 | 881976.7757 | 34905199.1844 |  |  | 1788649.6992 | 1741930.488 | [5 empty] | 29400.49
El-Gouna | 12 | 2020-11-30 | 2020-11-30 | 2020-12-23 | 21 | 2021-01-13 | 2020-12-23 | -0.0044313 | 34905199.18 |  |  | 2000000 | 1741930.49 | [5 empty] | 29400.49
El-Gouna | 13 | 2020-12-31 | 2020-12-31 | 2021-01-10 | 21 | 2021-01-31 | 2021-01-12 | 2225492.71 | 37130691.89 |  |  | 1964526.99 | 1823017.32 | [5 empty] | 29400.49
El-Gouna | 14 | 2021-01-31 | 2021-01-31 | 2021-02-14 | 21 | 2021-03-07 | 2021-03-03 | 3901532.2 | 41032224.09 |  |  | 3061707.07 | 1836465.31 | [5 empty] | 120415.29
El-Gouna | 15 | 2021-02-28 | 2021-03-11 | 2021-03-13 | 21 | 2021-04-03 | 2021-04-17 | 4440680.41 | 45472904.5 |  |  | 3011925.18 | 1238512.71 | [5 empty] | 120415.29
El-Gouna | 16 | 2021-03-31 | 2021-04-12 | 2021-04-15 | 21 | 2021-05-06 | 2021-04-27 | 4113209.61 | 49586114.11 |  |  | 3166964.63 | 1193051.88 | [5 empty] | 120415.29
El-Gouna | 17 | 2021-05-31 | 2021-05-31 | 2021-06-03 | 21 | 2021-06-24 | 2021-06-14 | 3640319.41 | 53226433.52 |  |  | 2547089.28 | 540181.99 | [5 empty] | 120415.29
El-Gouna | 18 | 2021-08-31 | 2021-08-26 | 2021-08-26 | 21 | 2021-09-16 | 2021-08-26 | 3384789.31 | 56611222.83 |  |  | 5636285.41 | [6 empty] | 195708.06
El-Gouna - Equip. Rental | 1 | 2019-12-31 | 2019-12-31 | 2019-12-12 | 21 | 2020-01-02 | 2020-02-02 | 80875 | 80875 |  |  | 73813.12
El-Gouna - Equip. Rental | 2 | 2020-03-31 | 2020-03-31 | 2020-03-18 | 21 | 2020-04-08
El-Gouna - Equip. Rental | 3 | 2020-06-30 | 2020-07-09 | 2020-07-09 | 21 | 2020-07-30
El-Gouna - Equip. Rental | 4 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 21 | 2021-04-21
El-Gouna - Equip. Rental | 5 | 2021-05-31 | 2021-05-24 | 2021-05-24 | 21 | 2021-06-14 | 2021-06-24 | 15000 | 186362.5 |  |  | 15750
El-Gouna - Temp. Fence | 1 | 2019-12-31 | 2020-01-15 | 2020-01-18 | 21 | 2020-02-08 | 2020-03-01 | 409200 | 409200 |  |  | 429660
El-Gouna - Temp. Fence | 2 | 2020-01-31 | 2020-02-15 | 2020-02-23 | 21 | 2020-03-15
El-Gouna - Temp. Fence | 3 | 2020-05-31 | 2020-06-06 | 2020-06-06 | 21 | 2020-06-27
Existing Intake Apply -SSC-Mech | 1 | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-30 | 573500 | 573500 |  |  | 636585 | [6 empty] | 0
Existing Intake Supply -SSC-Mech | 1 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 2140488 | 2140488 |  |  | 2418751.44 | [6 empty] | 0
FIEM | 210 | 2017-10-31 | 2017-10-20 | 2017-10-20 | 60 | 2017-12-19 | 2017-10-23 | 2236443.87 | 69807649.46 |  |  | 1524934.13 | [6 empty] | 0
FIEM | 211 | 2017-11-30 | 2017-12-04 | 2018-01-02 | 60 | 2018-03-03 | 2018-01-19 | 342199.52 | 70149848.98 |  |  | 221255.83 | [6 empty] | 0
FIEM | 212 | 2018-05-31 | 2018-06-12 | 2018-07-12 | 60 | 2018-09-10 | 2018-10-24 | 1955183.63 | 72105032.61 |  |  | 1546005.35 | 0 | [5 empty] | 0
FIEM | 213 | 2018-08-31 | 2018-08-15 | 2018-10-21 | 60 | 2018-12-20 | 2018-10-24 | 336328.97 | 72441361.58 |  |  | 335237.946 | 0 | [5 empty] | 0
HQ - CFC | 1 | 2021-01-31 | 2021-01-31 | 2021-02-03 | 21 | 2021-02-24 | 2021-02-22 | 1435679.4 | 1435679.4 |  |  | 6847513.7311 | 5469259.14 | [5 empty] | 0
HQ - CFC | 2 | 2021-02-28 | 2021-02-28 | 2021-03-08 | 21 | 2021-03-29 | 2021-03-22 | 7766126.7 | 9201806.1 |  |  | 8021127.94 | 7106192.52 | [5 empty] | 0
HQ - CFC | 3 | 2021-03-31 | 2021-03-31 | 2021-04-10 | 21 | 2021-05-01 | 2021-04-15 | 12533035.1 | 21734841.2 |  |  | 8213719.76 | 6815308.56 | [5 empty] | 50000
HQ - CFC | 4 | 2021-04-30 | 2021-04-30 | 2021-05-06 | 21 | 2021-05-27 | 2021-05-26 | 11480730.2 | 33215571.4 |  |  | 7815807.64 | 6784708.63 | [5 empty] | 50000
HQ - CFC | 5 | 2021-06-30 | 2021-06-30 | 2021-07-06 | 21 | 2021-07-27 | 2021-07-14 | 6032812.4 | 39248383.8 |  |  | 3447418.19 | 6043914.88 | [5 empty] | 298842.16
HQ - CFC | 6 | 2021-07-31 | 2021-07-31 | 2021-08-04 | 21 | 2021-08-25 | 2021-08-17 | 5418722.3 | 44667106.1 |  |  | 13157201.34 | 15536980.84 | [5 empty] | 258842.16
HQ - CFC | 7 | 2021-08-31 | 2021-09-06 | 2021-09-07 | 21 | 2021-09-28 | 2021-09-09 | 14463563.8 | 59130669.9 |  |  | 14942810.8492 | 20740314.76 | [5 empty] | 258842.16
HQ - CFC | 8 | 2021-09-30 | 2021-10-06 | 2021-10-09 | 21 | 2021-10-30 | 2021-10-17 | 12855494 | 71986163.9 |  |  | 10012746.11 | 21760696.01 | [5 empty] | 253842.16
HQ - CFC | 9 | 2021-10-31 | 2021-11-03 | 2021-11-04 | 21 | 2021-11-25 | 2021-11-11 | 11039038.4 | 83025202.3 |  |  | 17174919.86 | 31225957.6 | [5 empty] | 253842.16
HQ - CFC | 10 | 2021-11-30 | 2021-12-04 | 2021-12-07 | 21 | 2021-12-28 | 2021-12-16 | 10645458.9 | 93670661.2 |  |  | 7981881.9284 | 32240807.02 | [5 empty] | 673673.38
HQ - CFC | 11 | 2021-12-31 | 2022-01-09 | 2022-01-10 | 21 | 2022-01-31 | 2022-10-20 | 21606398.42 | 115277059.62 |  |  | 17417402.06 | 33736026.89 | [5 empty] | 673673.38
HQ - CFC | 12 | 2022-01-31 | 2022-02-13 | 2022-02-15 | 21 | 2022-03-08 | 2022-02-24 | 11990804.88 | 127267864.5 |  |  | 11342067.06 | 36548454.91 | [5 empty] | 0
HQ - CFC | 13 | 2022-02-28 | 2022-03-10 | 2022-03-15 | 21 | 2022-04-05 | 2022-03-28 | 23373232.3 | 150641096.8 |  |  | 869511.3183 | 40068734.4 |  |  |  | 3954328.79 | 3954328.79 | 0
HQ - CFC | 14 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 21 | 2022-05-04 | [5 empty] | 1748564.91 | [6 empty] | 0
HQ - CFC | 15 | 2022-04-30 | 2022-04-30 | 2022-05-10 | 21 | 2022-05-31 | 2022-05-17 | 16353901 | 182179087 |  |  | 10437709.6267 | 36127505.39 | 42019925.8 |  | 380603 | 4782201.035 | 4782201.035 | 28096
HQ - CFC | 16 | 2022-05-31 | 2022-05-31 | 2022-06-12 | 21 | 2022-07-03 | 2022-06-15 | 8911604.3 | 191090691.3 |  |  | 1064612.35 | 35019448 | 44132357 |  | 534156.21 | 5016130.5 | 5016130.5 | 1429217
HQ - CFC | 17 | 2022-06-30 | 2022-06-30 | 2022-07-04 | 21 | 2022-07-25 | 2022-07-18 | 17076484.2 | 208167175.5 |  |  | 8013147.4 | 34368331.94 | 46825994 |  | 855446.95 | 5464388 | 5464388 | 28096.4
HQ - CFC | 18 | 2022-07-31 | 2022-07-31 | 2022-08-06 | 21 | 2022-08-27 | 2022-08-17 | 15625697.2 | 223792872.7 |  |  | 13019444.4 | 42794128.97 | 51289544.4 |  | 1216434.1435 | 5874504.1475 | 5874504.1475 | 28096.4
HQ - CFC | 19 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 21 | 2022-09-28 | 2022-10-16 | 11070593.3 | 234863466 |  |  | 2123376.4 | 43167126 | 53959703 |  | 1482872 | 6165165.5 | 6165165.5 | 23096
HQ - CFC | 20 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 21 | 2022-11-01 | 2022-10-17 | 43687204.7 | 278550670.7 |  |  | 9324446.7637 | 25330248.86 | 72413577.8 |  | 2630548.1069 | 7311955.105 | 7311955.105 | 23096.4
HQ - CFC | 21 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 21 | 2022-11-29 | 2022-11-20 | 6969185.9 | 285519856.6 |  |  | 1704646.05 | 22835242 | 75563462.2 |  | 2846115 | 7494896 | 7494896 | 0
HQ - CFC | 23 | 2022-11-30 | 2022-11-30 | 2022-12-07 | 21 | 2022-12-28 | 2022-12-14 | 9615384.7 | 295135241.3 |  |  | 10000000.1524 | 22835242.98 | 85178846.6 |  | 2846115.9564 | 7494896.235 | 7494896.235 | 2085744.58
HQ - CFC | 24 | 2022-11-30 | 2022-11-30 | 2022-12-13 | 21 | 2023-01-03 | 2022-12-27 | 25568878.3 | 320704119.6 |  |  | 5979128.01 | 12624923 | 98574568 |  | 4317722 | 7311955.09 | 9525011.19 | 325973.55
HQ - CFC | 25 | 2022-12-31 | 2022-12-31 | 2023-01-11 | 21 | 2023-02-01 | 2023-01-30 | 17887580.019 | 338591699.619 |  |  | 10125697.7641 | 5521723.78 | 103716174.2 |  | 5354076.6018 | 7311955.09 | 10464109.14 | 297877.55
HQ - CFC | 26 | 2023-01-31 | 2023-01-31 | 2023-11-22 | 21 | 2023-12-13 | 2024-02-15 | 15848994.2857 | 354440693.9048 |  |  | 24450753.15 | 2203336.47 | 119098372.4 |  | 6380098.57 | 9304068.215 | 9304068.215 | 0
HyperOne | 1 | 2019-10-31 | 2019-11-10 | 2019-11-11 | 14 | 2019-11-25 | 2019-11-24 | 1684523.66 | 1684523.66 | 33750000 |  | 2673900.95 | 1191900 | [5 empty] | 0
HyperOne | 2 | 2019-11-30 | 2019-12-07 | 2019-12-08 | 14 | 2019-12-22 | 2019-12-12 | 11473372.17 | 13157895.83 |  |  | 8554552.61 | 478500 | [5 empty] | 0
HyperOne | 3 | 2019-12-31 | 2019-12-31 | 2020-01-02 | 14 | 2020-01-16 | 2020-01-13 | 10276217.5887 | 23434113.4187 |  |  | 7194819.7145 | 478500 | [5 empty] | 1194684.3216
HyperOne | 4 | 2020-01-31 | 2020-01-31 | 2020-02-06 | 14 | 2020-02-20 | 2020-02-23 | 12451224.3668 | 35885337.7855 |  |  | 6318712 | [6 empty] | 4562652.7636
HyperOne | 5 | 2020-02-29 | 2020-02-14 | 2020-02-18 | 14 | 2020-03-03 | 2020-02-23 | 5616638.2145 | 41501976 |  |  | 3307335 | [6 empty] | 5067252
HyperOne | 6 | 2020-02-29 | 2020-02-29 | 2020-03-03 | 14 | 2020-03-17 | 2020-03-07 | 10976157.5052 | 52478133.5052 |  |  | 8598545.1487 | [6 empty] | 6203130.8054
HyperOne | 7 | 2020-03-31 | 2020-03-16 | 2020-03-19 | 14 | 2020-04-02 | 2020-03-23 | 12354446.4948 | 64832580 |  |  | 8896507 | [6 empty] | 7392793.3392
HyperOne | 8 | 2020-03-31 | 2020-03-31 | 2020-04-04 | 14 | 2020-04-18 | 2020-04-12 | 7228560.7301 | 72061140.7301 |  |  | 3400669 | [6 empty] | 9893521.3392
HyperOne | 9 | 2020-04-30 | 2020-04-16 | 2020-04-19 | 14 | 2020-05-03 | 2020-04-26 | 2029339.2699 | 74090480 |  |  | 1277872 | [6 empty] | 10272402
HyperOne | 10 | 2020-05-31 | 2020-05-15 | 2020-05-17 | 14 | 2020-05-31 | 2020-06-01 | 7741768.3647 | 81832248.3647 |  |  | 4810581.9155 | [6 empty] | 11782199.7246
HyperOne | 11 | 2020-06-30 | 2020-06-15 | 2020-06-18 | 14 | 2020-07-02 | 2020-06-23 | 9960645.6353 | 91792894 |  |  | 6700151 | [6 empty] | 13305539
HyperOne | 12 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 14 | 2020-07-18 | 2020-07-11 | 3093528.5715 | 94886422.5715 |  |  | 1896314.4172 | [6 empty] | 13935080.9072
HyperOne | 13 | 2020-07-31 | 2020-07-31 | 2020-08-09 | 14 | 2020-08-23 | 2020-08-19 | 9161230.539 | 104047653.1105 |  |  | 6738701.3468 | [6 empty] | 14675608.1725
HyperOne | 14 | 2020-08-31 | 2020-08-31 | 2020-09-02 | 14 | 2020-09-16 | 2020-09-13 | 5698538.8895 | 109746192 |  |  | 4476191 | [6 empty] | 14851704
HyperOne | 15 | 2020-12-31 | 2020-12-31 | 2021-07-10 | 14 | 2021-07-24 | 2021-09-08 | 16067546 | 125813738 |  |  | 2800899.62 | [6 empty] | 18113646
IKEA | 1 | 2019-10-31 | 2019-10-24 | 2019-10-29 | 56 | 2019-12-24 | 2019-11-13 | 2651353.89 | 2651353.89 | 5000000 |  | 4032556.9 | 2149309.09 | [5 empty] | 0
IKEA | 2 | 2019-11-30 | 2019-11-30 | 2019-12-01 | 56 | 2020-01-26 | 2019-12-23 | 11255708.29 | 13907062.18 | 428986.9 |  | 10633715.55 | 4289692.08 | [5 empty] | 619021.13
IKEA | 3 | 2019-12-31 | 2019-12-31 | 2019-12-29 | 56 | 2020-02-23 | 2020-01-27 | 10066585.32 | 23973647.5 | 4951900.8 |  | 7184168.18 | 2903747.63 | [5 empty] | 726571.28
IKEA | 4 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 56 | 2020-03-30 | 2020-02-26 | 12574283.5677 | 36547931.0677 | 2116049.37 |  | 8278802.0663 | 465407.831 | [5 empty] | 919175.0927
IKEA | 5 | 2020-02-29 | 2020-02-29 | 2020-03-02 | 56 | 2020-04-27 | 2020-03-29 | 9421690.8414 | 45969621.9091 | 21562500 |  | 7929959.808 | 371420 | [5 empty] | 847495.2609
IKEA | 6 | 2020-03-31 | 2020-03-31 | 2020-03-31 | 56 | 2020-05-26 | 2020-04-23 | 5112809.0459 | 51082430.955 | 1818917 |  | 3899213.6765 | 371420 | [5 empty] | 1125963.2758
IKEA | 7 | 2020-04-30 | 2020-05-03 | 2020-05-05 | 56 | 2020-06-30 | 2020-06-07 | 9400137.0091 | 60482567.9642 | 3751873.62 |  | 6161858.9082 | [6 empty] | 1472106.3608
IKEA | 8 | 2020-06-30 | 2020-06-23 | 2020-06-23 | 56 | 2020-08-18 | 2020-07-15 | 17657618.9509 | 78140186.9151 | 525633.83 |  | 13080191.1331 | 5848353.145 | [5 empty] | 2079486.5167
IKEA | 9 | 2020-07-31 | 2020-07-22 | 2020-07-23 | 56 | 2020-09-17 | 2020-08-13 | 19939473.9502 | 98079660.8653 |  |  | 21936362.8422 | 17006675.991 | [5 empty] | 1611811.9037
IKEA | 10 | 2020-08-31 | 2020-08-15 | 2020-08-18 | 56 | 2020-10-13 | 2020-09-27 | 16241524.1447 | 114321185.01 |  |  | 10981834.92 | 16856139.28 | [5 empty] | 2394063.2
IKEA | 11 | 2020-09-30 | 2020-10-12 | 2020-10-14 | 56 | 2020-12-09 | 2020-11-15 | 40022086.8222 | 154343271.8322 |  |  | 16592416.38 | 2685460.4477 | [5 empty] | 3391607
IKEA | 12 | 2020-11-30 | 2020-11-25 | 2020-11-29 | 56 | 2021-01-24 | 2021-12-30 | 27619584.4178 | 181962856.25 |  |  | 15898929.26 | -4332571 | [5 empty] | 0
IKEA | 13 | 2020-12-31 | 2021-01-10 | 2021-01-13 | 56 | 2021-03-10 | 2021-02-18 | 3981119.65 | 185943975.9 |  |  | 5400893.31 | [6 empty] | 4547790.9
IKEA | 14 | 2021-04-30 | 2021-04-19 | 2021-06-24 | 56 | 2021-08-19 | 2021-08-09 | 10525422.84 | 196469398.74 |  |  | 15116863.46 | [6 empty] | 0
JICA | 19 | 2017-10-31 | 2017-10-28 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-30 | 1210863.76 | 117203462.77 |  |  | 1141675.91 | 0 | [5 empty] | 0
JICA | 20 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 283125.01 | 117486587.78 |  |  | 413014.8 | 0 | [5 empty] | 0
Kafr Shokr | 1 | 2021-03-31 | 2021-03-14 | 2021-03-17 | 60 | 2021-05-16 | [12 empty] | 0
Kafr Shokr | 2 | 2021-03-31 | 2021-03-31 | 2021-04-07 | 60 | 2021-06-06 | [12 empty] | 0
Kafr Shokr | 3 | 2021-04-30 | 2021-04-30 | 2021-05-23 | 60 | 2021-07-22 | [12 empty] | 0
Kafr Shokr | 4 | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 | [12 empty] | 0
Kafr Shokr | 5 | 2021-07-31 | 2021-07-31 | 2021-08-12 | 60 | 2021-10-11 | [12 empty] | 0
Kafr Shokr | 6 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | [12 empty] | 0
Kafr Shokr | 7 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 60 | 2021-12-09 |  | 31881474.95 | 108184525 |  |  | 25823994.7095 | [6 empty] | 0
Kafr Shokr | 8 | 2021-11-30 | 2021-11-30 | 2021-11-30 | 60 | 2022-01-29 | 2021-12-25 | 2504502 | 110689027 |  |  | 2028646.62 | [6 empty] | 0
Kafr Shokr | 9 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-08-07 | 5785188 | 116474215 |  |  | 0 | [6 empty] | 0
Kafr Shokr | 10 | 2021-12-31 | 2021-12-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-09-26 | 2841975 | 119316190 |  |  | 2301999.75 | [6 empty] | 0
Katameya - Creeks | 1 | 2020-12-31 | 2020-12-31 | 2021-01-14 | 40 | 2021-02-23 | 2021-01-31 | 2910883.3063 | 2910883.3063 |  |  | 2741191.2884 | [6 empty] | 0
Katameya - Creeks | 2 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 40 | 2021-03-16 | 2021-02-18 | 11780609.6823 | 14691492.9885 |  | 45000000 | 11302769.9409 | 595916.5854 | [5 empty] | 0
Katameya - Creeks | 3 | 2021-02-28 | 2021-02-28 | 2021-03-06 | 40 | 2021-04-15 | 2021-03-21 | 36329559.9323 | 51021052.9208 |  | 45000000 | 39570120.8973 | 6017782.3615 | [5 empty] | 0
Katameya - Creeks | 4 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 40 | 2021-05-16 | 2021-04-22 | 30128591.4792 | 81149644.4 |  | 20000000 | 29688637.31 | 7771049.05 | [5 empty] | 0
Katameya - Creeks | 5 | 2021-04-30 | 2021-05-06 | 2021-05-06 | 40 | 2021-06-15 | 2021-05-23 | 41641437.57 | 122791081.97 |  |  | 40006572.36 | 9284784.42 | [5 empty] | 0
Katameya - Creeks | 6 | 2021-05-31 | 2021-06-06 | 2021-06-06 | 40 | 2021-07-16 | 2021-06-29 | 35290109.98 | 158081191.95 |  |  | 29363826.77 | 6250089.55 | [5 empty] | 0
Katameya - Creeks | 7 | 2021-06-30 | 2021-07-06 | 2021-07-06 | 40 | 2021-08-15 | 2021-07-27 | 46826693.78 | 204907885.73 |  |  | 44596069.78 | 7704269.19 | [5 empty] | 523000
Katameya - Creeks | 8 | 2021-07-31 | 2021-08-07 | 2021-08-07 | 40 | 2021-09-16 | 2021-08-07 | 41480221.37 | 246388107.1 |  |  | 40343227.98 | 9594054.56 | [5 empty] | 777600
Katameya - Creeks | 9 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 40 | 2021-10-15 | 2021-09-23 | 44965022.45 | 291353129.55 |  |  | 43056438.19 | 10287932.68 | [5 empty] | 800600
Katameya - Creeks | 10 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 40 | 2021-11-15 | 2021-10-28 | 37520387.97 | 328873517.52 |  |  | 36159161.93 | 11525093.24 | [5 empty] | 813250
Katameya - Creeks | 11 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 40 | 2021-12-16 | 2021-11-22 |  | 379505848.55 |  |  | 43214038.28 | 7555153.37 | [5 empty] | 823370
Katameya - Creeks | 12 | 2021-11-30 | 2021-11-30 | 2021-12-06 | 40 | 2022-01-15 | 2021-12-27 | 40810274.28 | 420316122.83 |  |  | 36461301.55 | 6280972.71 | [5 empty] | 841080
Katameya - Creeks | 13 | 2021-12-31 | 2021-12-31 | 2022-01-08 | 40 | 2022-02-17 | 2022-01-27 | 39636501.96 | 459952624.79 |  |  | 39353596.01 | 8474255.32 | [5 empty] | 863850
Katameya - Creeks | 14 | 2022-01-31 | 2022-01-31 | 2022-02-07 | 40 | 2022-03-19 | 2022-02-24 | 45239351.95 | 505191976.74 |  |  | 45904629.98 | 11809416.04 | [5 empty] | 0
Katameya - Creeks | 15 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 40 | 2022-04-14 | 2022-03-14 | 47493723.66 | 552685700.4 |  |  | 49567394.59 | 16219011.36 | [5 empty] | 0
Katameya - Creeks | 16 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 40 | 2022-05-16 | 2022-04-17 | 48315079.39 | 601000779.79 |  |  | 44583744.4 | 14925377.35 | [5 empty] | 0
Katameya - Creeks | 17 | 2022-04-30 | 2022-04-30 | 2022-05-07 | 40 | 2022-06-16 | 2022-05-29 | 37444918.46 | 638445698.25 |  |  | 36501027.74 | 15002234.06 | 50675010 |  | 97675643 |  |  | 1009270
Katameya - Creeks | 18 | 2022-05-31 | 2022-05-31 | 2022-06-05 | 40 | 2022-07-15 | 2022-06-05 | 37748158.21 | 676193856.46 |  |  | 41565441.8 | 20189762.86 | 59495615 |  | 103801771 |  |  | 1085086
Katameya - Creeks | 19 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-03 | 37876838.61 | 714070695.07 |  |  | 36081249.47 | 19797069.17 | 71508662.79 |  | 108653109.7 |  |  | 1084330
Katameya - Creeks | 20 | 2022-07-31 | 2022-07-31 | 2022-08-07 | 40 | 2022-09-16 | 2022-08-21 | 23863809.78 | 737934504.85 |  |  | 24569045.01 | 21208756.33 | 79759027 |  | 110507501 |  |  | 944330
Katameya - Creeks | 21 | 2022-08-31 | 2022-08-31 | 2022-09-05 | 40 | 2022-10-15 | 2022-09-20 | 37145495.17 | 775080000.02 |  |  | 35259435.93 | 20319209.63 | 93957089.31 |  | 115330857 |  |  | 944330
Katameya - Creeks | 22 | 2022-09-30 | 2022-09-30 | 2022-10-06 | 40 | 2022-11-15 | 2022-10-22 | 28622135.19 | 803702135.21 |  |  | 31299260.01 | 24073006.79 | 104402623 |  | 118783626 |  |  | 944330
Katameya - Creeks | 23 | 2022-10-31 | 2022-10-25 | 2022-11-06 | 40 | 2022-12-16 | 2022-11-28 | 24245600.88 | 827947736.09 |  |  | 29834733.07 | 30491808 | 110827191.37 |  | 121373214 |  |  | 944330
Katameya - Creeks | 24 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 40 | 2023-01-14 | 2022-12-26 | 30975620.82 | 858923356.91 |  |  | 37876581.29 | 38226243.19 | 123338828 |  | 123817551 |  |  | 944330
Katameya - Creeks | 25 | 2022-12-31 | 2022-12-31 | 2023-01-03 | 40 | 2023-02-12 | 2023-01-25 | 21870157.41 | 880793514.32 |  |  | 45191848.32 | 61683477.19 | 133104770 |  | 126424933 |  |  | 944330
Katameya - Creeks | 26 | 2023-01-31 | 2023-01-31 | 2023-02-05 | 40 | 2023-03-17 | 2023-02-28 | 41254688.36 | 922048202.68 |  |  | 74263221.64 | 93923373 | 158579085 |  | 130310913 |  |  | 975300.2
Katameya - Creeks | 27 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 40 | 2023-04-14 | 2023-03-30 | 23948941.02 | 945997143.7 |  |  | 35452924.06 | 105419805.57 | 170052796 |  | 133396502 |  |  | 975300
Katameya - Creeks | 28 | 2023-03-31 | 2023-03-30 | 2023-04-06 | 40 | 2023-05-16 | 2023-05-04 | 26373696.19 | 972370839.89 |  |  | 28650459.02 | 107935491.27 | 183454579.15 |  | 136180192 |  |  | 975300
Katameya - Creeks | 29 | 2023-04-30 | 2023-04-30 | 2023-05-10 | 40 | 2023-06-19 | 2023-06-03 | 23994845.49 | 996365685.38 |  |  | 40904481.77 | 124153275.86 | 196775586 |  | 138759517 |  |  | 1187195.2
Katameya - Creeks | 30 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 40 | 2023-07-17 | 2023-06-22 | 81851684.98 | 1078217370.36 |  |  | 43084120.03 | 97599905.99 | 269087133.95 |  | 142922586 |  |  | 1474123.2
Katameya - Creeks | 31 | 2023-06-30 | 2023-06-30 | 2023-07-09 | 40 | 2023-08-18 | 2023-07-31 | 34090513.58 | 1112307883.94 |  |  | 37106226.16 | 112799416.94 | 291661196 |  | 146035580.84 |  |  | 1474123.2
Katameya - Creeks | 32 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 40 | 2023-09-17 | 2023-09-04 | 36694395.36 | 1149002279.3 |  |  | 53216438.64 | 128465791.75 | 319241513 |  | 149874135 |  |  | 1474123.2
Katameya - Creeks | 33 | 2023-08-31 | 2023-08-31 | 2023-09-07 | 40 | 2023-10-17 | 2023-10-01 | 61801377.92 | 1210803657.22 |  |  | 47329832.99 | 127901321.55 | 370075065.87 |  | 154477701.6 |  |  | 1474123.2
Katameya - Creeks | 34 | 2023-09-30 | 2023-09-30 | 2023-10-08 | 40 | 2023-11-17 | 2023-11-02 | 67431952.34 | 1278235609.56 |  |  | 70308953.76 | 143466613.76 | 421285092.94 |  | 161880059 |  |  | 2286300.2
Katameya - Creeks | 35 | 2023-10-31 | 2023-10-31 | 2023-11-08 | 40 | 2023-12-18 | 2023-12-06 | 61247331.12 | 1339482940.68 |  |  | 46816344.41 | 141313879.12 | 467826001.19 |  | 169260713.53 |  |  | 2593710.2
Katameya - Creeks | 36 | 2023-11-30 | 2023-11-30 | 2023-12-07 | 40 | 2024-01-16 | 2023-12-30 | 74463161.12 | 1413946101.8 |  |  | 50530225.45 | 131303175.93 | 514457815.28 |  | 175537623 |  |  | 2835674.2
Katameya - Creeks | 37 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-01-22 | 53331460.14 | 1467277561.94 |  |  | 62109565.07 | 138791064.14 | 557616767.77 |  | 179660456 |  |  | 3087279.2
Katameya - Creeks | 38 | 2024-01-31 | 2024-01-31 | 2024-02-08 | 40 | 2024-03-19 | 2024-03-06 | 83842743.6 | 1551120305.54 |  |  | 79235149.9 | 133813630.27 | 619119624.83 |  | 194495708 |  |  | 3385105
Katameya - Creeks | 39 | 2024-02-29 | 2024-02-29 | 2024-03-10 | 40 | 2024-04-19 | 2024-04-02 | 81688930.92 | 1632809236.46 |  |  | 66261026.21 | 118504628.04 | 681574347 |  | 206803236 |  |  | 3583708
Katameya - Creeks | 40 | 2024-03-31 | 2024-03-31 | 2024-04-06 | 40 | 2024-05-16 | 2024-05-02 | 66582662.04 | 1699391898.5 |  |  | 52039038.12 | 104305214.28 | 732184516 |  | 217702929 |  |  | 3885490.2
Katameya - Creeks | 41 | 2024-04-30 | 2024-04-30 | 2024-05-08 | 40 | 2024-06-17 | 2024-05-25 | 47455342.03 | 1746847240.53 |  |  | 45340679.8 | 101408785.94 | 771118051 |  | 224726984.46 |  |  | 4067349.2
Katameya - Creeks | 42 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 40 | 2024-07-19 | 2024-07-07 | 56995945.47 | 1803843186 |  |  | 52791233.92 | 96574638 | 816861989 |  | 232964321 |  |  | 4370002
Katameya - Creeks | 43 | 2024-06-30 | 2024-06-30 | 2024-07-10 | 40 | 2024-08-19 | 2024-07-27 | 56437240.4362 | 1860280426.4362 |  |  | 30082113.9462 | 90480931.8131 | 861619431.0834 |  | 241015625.4571 |  |  | 4370002.2
Katameya - Creeks | 44 | 2024-07-31 | 2024-07-31 | 2024-08-10 | 40 | 2024-09-19 | 2024-08-31 | 49427006.6938 | 1909707433.13 |  |  | 8345106.3 | 67101367.22 | 899419335 |  | 247392879 |  |  | 4855643.2
Katameya - Creeks | 45 | 2024-08-31 | 2024-08-31 | 2024-09-09 | 40 | 2024-10-19 | 2024-10-03 | 67801530.87 | 1977508964 |  |  | 24274088.38 | 50090340 | 947220416 |  | 256761214 |  |  | 5144638
Katameya - Creeks | 46 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 40 | 2024-11-19 | 2024-11-04 | 42454238 | 2019963202 |  |  | 22007540.78 | 39951618 | 976799080 |  | 264112905 |  |  | 5327913
Katameya - Creeks | 47 | 2024-10-31 | 2024-10-31 | 2024-11-09 | 40 | 2024-12-19 | [12 empty] | 0
KFW | 109 | 2017-09-30 | 2017-10-09 | 2018-01-02 | 60 | 2018-03-03 | 2017-10-23 | 156311.35 | 20308378.88 |  |  | 128570.36 | [6 empty] | 0
KFW | 110 | 2018-08-31 | 2018-08-15 | 2018-08-15 | 60 | 2018-10-14 | 2018-08-18 | 357187.5 | 20665566.38 |  |  | 377225.16 | 0 | [5 empty] | 0
Khatatba Bridge | 1 | 2022-01-31 | 2022-01-31 | 2022-02-06 | 60 | 2022-04-07 | 2022-02-08 | 42898060 | 42898060 |  |  | 8313070.05 | [6 empty] | 0
Khatatba Bridge | 2 | 2022-02-28 | 2022-02-28 | 2022-03-07 | 60 | 2022-05-06 | 2022-03-07 | 10581515 | 53479575 |  |  | 10363626.0758 | [6 empty] | 0
Khatatba Bridge | 4 | 2022-07-31 | 2022-08-01 | 2022-08-15 | 60 | 2022-10-14 | 2022-08-15 | 50062250 | 103541825 |  |  | 49031394.797 | [6 empty] | 0
KSA-Tarek AbdelHakim Center | 1 | 2023-02-28 | 2023-02-28 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 1174788.1 | 1174788.1 |  |  | 951578.36 |  |  |  |  | 117478.81 |  | 0
KSA-Tarek AbdelHakim Center | 2 | 2023-03-31 | 2023-03-31 | 2023-06-12 | 75 | 2023-08-26 | 2023-06-13 | 2619891.03 | 3794679.13 |  |  | 2122111.73 |  |  |  |  | 379467.91 |  | 0
KSA-Tarek AbdelHakim Center | 3 | 2023-04-30 | 2023-04-30 | 2023-06-22 | 75 | 2023-09-05 | 2023-07-25 | 1124829.43 | 4919508.56 |  |  | 911111.84 |  |  |  |  | 491950.85 |  | 0
KSA-Tarek AbdelHakim Center | 4 | 2023-05-31 | 2023-05-31 | 2023-07-24 | 75 | 2023-10-07 | 2023-07-25 | 1181749.35 | 6101257.91 |  |  | 957216.97 |  |  |  |  | 610125.78 |  | 0
KSA-Tarek AbdelHakim Center | 5 | 2023-06-30 | 2023-06-30 | 2023-09-14 | 75 | 2023-11-28 | [12 empty] | 0
KSA-Tarek AbdelHakim Center | 6 | 2023-07-31 | 2023-07-31 | 2023-09-14 | 75 | 2023-11-28 | [12 empty] | 0
KSA-Tarek AbdelHakim Center | 7 | 2023-08-31 | 2023-08-31 | 2023-09-14 | 75 | 2023-11-28 | [12 empty] | 0
KSA-Tarek AbdelHakim Center | 8 | 2023-09-30 | 2023-09-30 | 2023-10-17 | 75 | 2023-12-31 | [12 empty] | 0
KSA-Tarek AbdelHakim Center | 9 | 2023-10-31 | 2023-11-06 | 2023-11-06 | 75 | 2024-01-20 | [12 empty] | 0
KSA-Tarek AbdelHakim Center | 10 | 2023-11-30 | 2023-11-21 | 2023-11-21 | 75 | 2024-02-04 | [12 empty] | 0
KSA-Tarek AbdelHakim Center | 11 | 2023-12-31 | 2023-12-24 | 2023-12-24 | 75 | 2024-03-08 | 2024-01-04 | 6272151.58 | 34906557.56 |  |  | 5080442.78 |  |  |  |  | 3367198.74 |  | 0
KSA-Tarek AbdelHakim Center | 12 | 2024-04-30 | 2024-05-09 | 2024-09-24 | 75 | 2024-12-08 | [12 empty] | 0
LEKELA | 1 | 2020-03-31 | 2020-03-15 | 2020-07-19 | 60 | 2020-09-17 |  |  |  | 36300000 | [8 empty] | 0
LEKELA | 2 | 2020-06-30 | 2020-06-30 | 2020-07-19 | 60 | 2020-09-17 | [12 empty] | 0
LEKELA | 3 | 2020-07-31 | 2020-07-27 | 2020-07-27 | 60 | 2020-09-25 | [12 empty] | 0
LEKELA | 4 | 2020-08-31 | 2020-08-31 | 2020-09-12 | 60 | 2020-11-11 | [12 empty] | 0
LEKELA | 5 | 2020-09-30 | 2020-09-29 | 2020-09-30 | 60 | 2020-11-29 | 2020-10-08 | 8446374.726 | 14578092.546 |  |  | 7094954.7715 | [6 empty] | 0
LEKELA | 6 | 2020-10-31 | 2020-10-28 | 2020-10-28 | 60 | 2020-12-27 | 2020-11-12 | 20620363.18 | 35198455.726 |  |  | 14840272.4231 | [6 empty] | 0
LEKELA | 7 | 2020-11-30 | 2020-11-22 | 2020-11-23 | 60 | 2021-01-22 | 2020-12-02 | 19433463.8412 | 54631919.5672 |  |  | 15073158.3499 | [6 empty] | 0
LEKELA | 8 | 2020-12-31 | 2020-12-28 | 2020-12-28 | 60 | 2021-02-26 | 2021-01-19 | 41700595.0348 | 96332514.602 |  |  | 33513527.4715 | [6 empty] | 0
LEKELA | 9 | 2021-01-31 | 2021-01-15 | 2021-01-31 | 60 | 2021-04-01 | 2021-02-05 | 23169483.21 | 119501997.812 |  |  | 18594958.1925 | [6 empty] | 0
LEKELA | 10 | 2021-02-28 | 2021-02-15 | 2021-02-17 | 60 | 2021-04-18 | 2021-03-11 | 27064762.4727 | 146566760.2847 |  |  | 21709399.51 | 0 | [5 empty] | 0
LEKELA | 11 | 2021-03-31 | 2021-03-15 | 2021-03-16 | 60 | 2021-05-15 | 2021-05-20 | 18055279.9362 | 164622040.2209 |  |  | 14823033.596 | [6 empty] | 0
LEKELA | 12 | 2021-04-30 | 2021-04-15 | 2021-04-20 | 60 | 2021-06-19 | 2021-05-24 | 26449156.1285 | 191071196.3494 |  |  | 21477147.745 | [6 empty] | 0
LEKELA | 13 | 2021-05-31 | 2021-05-15 | 2021-05-24 | 60 | 2021-07-23 | 2021-08-01 | 6179424.4906 | 197250620.84 |  |  | 2329136.4958 | [6 empty] | 0
LEKELA | 14 | 2021-06-30 | 2021-06-15 | 2021-07-26 | 60 | 2021-09-24 | [12 empty] | 0
LEKELA | 15 | 2021-10-31 | 2021-10-15 | 2022-11-15 | 60 | 2023-01-14 | 2022-12-14 | 6597023.32 | 207000000 |  |  | 3229199.86 | [6 empty] | 0
LEKELA | 16 | 2022-11-30 | 2022-11-20 | 2023-02-22 | 60 | 2023-04-23 | 2023-03-31 | -0.0001 | 207000000 |  |  | 8212932.01 | [6 empty] | 0
LEKELA Remedial | 2 | 2024-01-31 | 2024-01-30 | 2024-02-26 | 60 | 2024-04-26 | [12 empty] | 0
LEKELA Remedial | 3 | 2024-05-31 | 2024-05-19 | 2024-08-19 | 60 | 2024-10-18 | 2024-08-21 | 2884958.98 | 15655160.98 |  |  | 3000357.86 | [6 empty] | 0
LEKELA Remedial | 4 | 2024-08-31 | 2024-08-20 | 2024-08-21 | 60 | 2024-10-20 | 2024-10-20 | 6153867.61 | 21809028.59 |  |  | 6400022.32 |  |  |  | 2290980.91 |  |  | 0
MDF Factory | 1 | 2021-06-30 | 2021-06-30 | 2021-07-05 | 28 | 2021-08-02 | 2021-08-17 | 3709029.4 | 3709029.4 | 41622365.4 |  | 6231879.24 | 4472196.39 | [5 empty] | 0
MDF Factory | 2 | 2021-07-31 | 2021-08-08 | 2021-08-08 | 28 | 2021-09-05 | 2021-08-31 | 5178414.72 | 8887444.12 | 6300000 |  | 7093735 | 7086056.01 | [5 empty] | 0
MDF Factory | 3 | 2021-08-31 | 2021-08-31 | 2021-09-06 | 28 | 2021-10-04 | 2021-09-22 | 9214079.17 | 18101523.29 | 2000000 |  | 8598866.23 | 8983935.87 | [5 empty] | 0
MDF Factory | 4 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 28 | 2021-11-03 | 2021-10-27 | 9266652.88 | 27368176.17 | 2000000 |  | 8359615.97 | 10661948.66 | [5 empty] | 0
MDF Factory | 5 | 2021-10-31 | 2021-10-31 | 2021-11-07 | 28 | 2021-12-05 | 2021-12-05 | 23662523.0739 | 51030699.2439 | 10016624.86 |  | 21785509.71 | 10195623.7568 | [5 empty] | 0
MDF Factory | 6 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 28 | 2022-01-06 | 2022-01-20 | 17937654.1261 | 68968353.37 | 7332000 |  | 17171193.3155 | 11973915.52 | [5 empty] | 0
MDF Factory | 7 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 28 | 2022-02-08 | 2022-02-14 | 16080953.7816 | 85049307.1516 | 6000000 |  | 14452550.5619 | 12658184.96 | [5 empty] | 0
MDF Factory | 8 | 2022-01-31 | 2022-01-31 | 2022-02-09 | 28 | 2022-03-09 | 2022-03-01 | 12291002.2884 | 97340309.44 | 11000000 |  | 12391060.05 | 14426942.06 | [5 empty] | 0
MDF Factory | 9 | 2022-02-28 | 2022-02-28 | 2022-03-09 | 28 | 2022-04-06 | 2022-04-07 | 8038787.77 | 105379097.21 | 13754630 |  | 7655361.33 | 14289033.25 |  |  |  | 2526800.69 | 2526800.69 | 0
MDF Factory | 10 | 2022-03-31 | 2022-03-31 | 2022-04-13 | 28 | 2022-05-11 | 2022-04-27 | 6155129.99 | 111534227.2 | 1488562.75 |  | 11119452.63 | 19004034.21 | [5 empty] | 0
MDF Factory | 11 | 2022-04-30 | 2022-04-30 | 2022-04-28 | 28 | 2022-05-26 | 2022-06-07 | 9364100.8 | 120898328 | 3000000 |  | 9991684.94 | 19378872 | 6694496.17 |  | 8943366.16 | 2938817.5 | 2938817.5 | 985000
MDF Factory | 12 | 2022-05-31 | 2022-05-31 | 2022-06-11 | 28 | 2022-07-09 | 2022-06-29 | 27509389.27 | 148407717.27 |  |  | 29337407.23 | 21048487.96 | 9413326 |  | 14867864 | 3374171 | 3374171 | 0
MDF Factory | 13 | 2022-06-30 | 2022-06-30 | 2022-07-06 | 28 | 2022-08-03 | 2022-08-07 | 15343913.47 | 163751630.74 |  |  | 19866888.03 | 25112316.18 | 10650525.16 |  | 15407262.1 | 3894039.675 | 3894039.675 | 1300000
MDF Factory | 14 | 2022-07-31 | 2022-07-25 | 2022-08-14 | 28 | 2022-09-11 | 2022-09-25 | 11905906.3968 | 175657537.1368 |  |  | 11219361.6633 | 28064532.2963 | 10473927.4807 |  | 17096495.4946 | 4266369.805 | 4266369.805 | 3250000
MDF Factory | 15 | 2022-08-31 | 2022-08-31 | 2022-09-08 | 28 | 2022-10-06 | 2022-10-09 | 8651043.7332 | 184308580.87 |  |  | 15409194.69 | 33441117.05 | 10616746 |  | 16229441.88 | 4412077.4 | 4412077.4 | 1350000
MDF Factory | 16 | 2022-09-30 | 2022-09-30 | 2022-10-11 | 28 | 2022-11-08 | 2022-11-06 | 21753082.06 | 206061662.93 |  |  | 22014291.85 | 35882692.55 | 10827826.68 |  | 16039161.03 | 4776541.575 | 4776541.575 | 3300000
MDF Factory | 17 | 2022-10-31 | 2022-10-31 | 2022-11-08 | 28 | 2022-12-06 | 2022-11-23 | 3503748.7 | 209565411.63 |  |  | 15156893.21 | 38117303.52 | 12364842.71 |  | 20883147.71 | 5114135 | 5114135 | 2890000
MDF Factory | 18 | 2022-11-30 | 2022-11-15 | 2022-11-27 | 28 | 2022-12-25 | 2022-12-11 | 4093790.13 | 213659201.76 |  |  | 5028798.98 | 38907634.85 | 12512881.83 |  | 19805682.68 | 5216480 | 5216480 | 2840000
MDF Factory | 19 | 2022-11-30 | 2022-11-30 | 2022-12-12 | 28 | 2023-01-09 | 2022-12-28 | 12077854.33 | 225737056.09 |  |  | 9756751.36 | 37074813.73 | 17269270.26 |  | 19805682.68 | 5518426.4 | 5518426.4 | 1240000
MDF Factory | 20 | 2022-12-31 | 2022-12-25 | 2022-12-22 | 28 | 2023-01-19 | 2023-01-12 | 10662163.65 | 236399219.74 |  |  | 14838164.52 | 44141114.86 | 18934354.95 |  | 21551157.34 | 5784980.495 | 5784980.495 | 1240000
MDF Factory | 21 | 2023-01-31 | 2023-01-12 | 2023-01-19 | 28 | 2023-02-16 | 2023-02-06 | 18933899.86 | 255333119.6 |  |  | 18749752.53 | 44152242.9 | 21222761.6 |  | 32601298.43 | 6258327.99 | 6258327.99 | 890000
MDF Factory | 22 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 28 | 2023-03-08 | 2023-02-25 | 3256087.31 | 258589206.91 |  |  | 3016784.72 | 44812446.87 | 22595375.04 | 400000 | 31182122.08 | 6339730 | 6339730 | 490000
MDF Factory | 23 | 2023-02-28 | 2023-02-28 | 2023-03-05 | 28 | 2023-04-02 | 2023-03-22 | 38888289.8 | 297477496.71 |  |  | 26140854.32 | 41744854.59 | 37403483.04 | 400000 | 31433209.86 | 7311937.42 | 7311937.42 | 470000
MDF Factory | 24 | 2023-03-31 | 2023-03-31 | 2023-04-04 | 28 | 2023-05-02 | 2023-04-30 | 18681389.16 | 316158885.87 |  |  | 13504786.11 | 36725913.89 | 48869956.89 | 400000 | 31459228.76 | 7778972.145 | 7778972.145 | 470000
MDF Factory | 25 | 2023-04-30 | 2023-04-30 | 2023-05-08 | 28 | 2023-06-05 | 2023-06-05 | 10484631.76 | 326643517.63 |  |  | 14874774.09 | 41744047.17 | 58047371.04 | 650000 | 31459228.76 | 8041087.94 | 8041087.94 | 400000
MDF Factory | 26 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 28 | 2023-07-06 | 2023-06-21 | 21011393.06 | 347654910.69 |  |  | 18123054.07 | 39628505.18 | 73625314.2 | 200000 | 33225314.57 | 8566372.765 | 8566372.765 | 450000
MDF Factory | 27 | 2023-06-30 | 2023-06-30 | 2023-06-26 | 28 | 2023-07-24 | 2023-07-12 | 10160280.74 | 357815191.43 |  |  | 21231778.46 | 54504636.34 | 81071518.94 | 250000 | 33210812.42 | 8820379.785 | 8820379.785 | 450000
MDF Factory | 28 | 2023-07-31 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 | 2023-07-31 | 4632219.77 | 362447411.2 |  |  | 5471658.1245 | 57298682.38 | 84101651.16 | 200000 | 33299495.32 | 8936185.28 | 8936185.28 | 500000
MDF Factory | 29 | 2023-07-31 | 2023-07-31 | 2023-08-08 | 28 | 2023-09-05 | 2023-09-10 | 7201895.8 | 369649307 |  |  | 13138195.96 | 63433973.15 | 88923223.93 | 200000 | 35138135.49 | 9116232.675 | 9116232.675 | 520000
MDF Factory | 30 | 2023-08-31 | 2023-08-30 | 2023-09-10 | 28 | 2023-10-08 | 2023-09-19 | 42878737.92 | 412528044.92 |  |  | 12581507.75 | 48447410.77 | 120743192.13 | 200000 | 35183358.23 | 10188201.125 | 10188201.125 | 550000
MDF Factory | 31 | 2023-09-30 | 2023-09-30 | 2023-10-05 | 28 | 2023-11-02 | 2023-10-07 | 26984773 | 439512817.92 |  |  | 20429584.53 | 52299084.09 | 141277943.84 | 200000 | 34937145.36 | 10862820.45 | 10862820.45 | 250000
MDF Factory | 32 | 2023-10-31 | 2023-10-25 | 2023-10-26 | 28 | 2023-11-23 | 2023-10-26 | 2754000 | 442266817.92 |  |  | 2726460 | 52299084.09 | 144031943.84 | 200000 | 34937145.36 | 10931670.45 | 10931670.45 | 250000
MDF Factory | 33 | 2023-10-31 | 2023-10-31 | 2023-11-07 | 28 | 2023-12-05 | 2023-11-25 | 20665276.54 | 462932094.46 |  |  | 12154985.64 | 52125340.59 | 161100913.16 | 250000 | 35201311.24 | 11448302 | 11448302 | 200000
MDF Factory | 34 | 2023-11-30 | 2023-11-30 | 2023-12-09 | 28 | 2024-01-06 | 2023-12-20 | 25469525.62 | 488401620.08 |  |  | 13093494.9 | 49181191.79 | 181875990.6 | 250000 | 35200228.82 | 12085040.5 | 12085040.5 | 200000
MDF Factory | 35 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 28 | 2024-01-28 | 2024-01-21 | 7460561 | 495862181.08 |  |  | 14005346.87 | 56480937.48 | 187067355.65 | 100000 | 35200149.54 | 12271554.525 | 12271554.525 | 350000
MDF Factory | 36 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-28 | 24220349.75 | 520082530.83 |  |  | 12150509.06 | 52738337.77 | 208687659.78 | 200000 | 35240386.14 | 12877063.27 | 12877063.27 | 220000
MDF Factory | 37 | 2024-02-29 | 2024-02-29 | 2024-03-11 | 28 | 2024-04-08 | 2024-04-02 | 18799337.86 | 538881868.69 |  |  | 7449862.86 | 47546890.76 | 225598759.07 | 1500000 | 35240386.14 | 13347046.715 | 13347046.715 | 700000
MDF Factory | 38 | 2024-03-31 | 2024-03-31 | 2024-04-08 | 28 | 2024-05-06 | 2024-04-24 | 25264630.57 | 564146499.26 |  |  | 10129299.6901 | 42828938.17 | 247874489.5 | 200000 | 35240386.14 | 13978662.48 | 13978662.48 | 253450
MDF Factory | 39 | 2024-04-30 | 2024-04-30 | 2024-05-07 | 28 | 2024-06-04 | 2024-05-22 | 17461783.47 | 581608282.73 |  |  | 7951387.28 | 39702840.21 | 261893208.84 | 200000 | 35240386.14 | 14415207 | 14415207 | 253450
MDF Factory | 40 | 2024-04-30 | 2024-04-30 | 2024-05-26 | 28 | 2024-06-23 | 2024-06-12 | -0.73 | 581608282 |  |  | 13055049.84 | 39702840 | 261893208 |  | 35240386 | 6101647 |  | 453450
MDF Factory | 41 | 2024-05-31 | 2024-05-31 | 2024-06-06 | 28 | 2024-07-04 | 2024-06-13 | 26553112.48 | 608161394.48 |  |  | 25000718.68 | 40071589.73 | 273875725.24 |  | 35240386.14 | 7033092.855 | 7033092.855 | 303450
MDF Factory | 42 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 28 | 2024-08-04 | 2024-07-24 | 750284.2 | 608911678.68 |  |  | 7547918.7 | 33497125 | 289636214 |  | 35240386 | 7100876.5 | 7100876.5 | 453450
MDF Factory | 43 | 2024-07-31 | 2024-07-31 | 2024-08-06 | 28 | 2024-09-03 | 2024-08-21 | 11210135.32 | 620121814 |  |  | 57977475.46 | 31321429 | 299419159 |  | 35243045 | 7887682 | 7887682 | 553450
MDF Factory | 44 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 28 | 2024-10-03 | 2024-09-26 | 10205950.6 | 630327764.6 |  |  | 13417821.66 | 30187176.6062 | 308819628.409 |  | 35266531.1337 | 15775364.249 |  | 4593450
MDF Factory | 45 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 28 | 2024-11-07 | 2024-11-04 | 16259922.8 | 646587687.4 |  |  | 21518034.22 | 21616659 | 325129806 |  | 34015260 | 15775364 |  | 3833450
MDF Factory - Equip. | 1 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-16 | 474511.19 | 474511.19 |  |  | 487660.4 | [6 empty] | 0
MDF Factory - Equip. | 2 | 2022-01-31 | 2022-01-16 | 2022-01-16 | 28 | 2022-02-13 | 2022-01-18 | 2969783.71 | 3444294.9 |  |  | 2999481.54 | [6 empty] | 0
MDF Factory - Equip. | 3 | 2022-01-31 | 2022-02-15 | 2022-02-22 | 28 | 2022-03-22 | 2022-03-01 | 2443276.13 | 5887571.03 |  |  | 2478572.15 | [6 empty] | 0
MDF Factory - Equip. | 4 | 2022-03-31 | 2022-03-15 | 2022-03-29 | 28 | 2022-04-26 | [12 empty] | 0
MDF Factory - Equip. | 5 | 2022-04-30 | 2022-04-15 | 2022-04-24 | 28 | 2022-05-22 | [12 empty] | 0
MDF Factory - Equip. | 6 | 2022-05-31 | 2022-05-15 | 2022-05-24 | 28 | 2022-06-21 | [12 empty] | 0
MDF Factory - Equip. | 7 | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 | [12 empty] | 0
MDF Factory - Equip. | 8 | 2022-07-31 | 2022-07-15 | 2022-07-25 | 28 | 2022-08-22 | 2022-08-02 | 340101.34 | 11819751.78 |  |  | 324002.35 | [6 empty] | 0
MDF Factory - Equip. | 9 | 2022-08-31 | 2022-08-15 | 2022-08-29 | 28 | 2022-09-26 | [12 empty] | 0
MDF Factory - Equip. | 10 | 2022-09-30 | 2022-09-15 | 2022-09-20 | 28 | 2022-10-18 | [12 empty] | 0
MDF Factory - Equip. | 11 | 2022-10-31 | 2022-10-15 | 2022-11-01 | 28 | 2022-11-29 | [12 empty] | 0
MDF Factory - Equip. | 12 | 2022-11-30 | 2022-11-15 | 2022-11-30 | 28 | 2022-12-28 | [12 empty] | 0
MDF Factory - Equip. | 13 | 2022-12-31 | 2022-12-15 | 2023-01-04 | 28 | 2023-02-01 | [12 empty] | 0
MDF Factory - Equip. | 14 | 2023-01-31 | 2023-01-15 | 2023-02-05 | 28 | 2023-03-05 | [12 empty] | 0
MDF Factory - Equip. | 15 | 2023-02-28 | 2023-02-15 | 2023-03-05 | 28 | 2023-04-02 | [12 empty] | 0
MDF Factory - Equip. | 16 | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 | [12 empty] | 0
MDF Factory - Equip. | 17 | 2023-05-31 | 2023-06-15 | 2023-06-18 | 28 | 2023-07-16 | [12 empty] | 0
MDF Factory - Equip. | 18 | 2023-06-30 | 2023-07-15 | 2023-07-18 | 28 | 2023-08-15 | [12 empty] | 0
MDF Factory - Equip. | 19 | 2023-08-31 | 2023-08-30 | 2023-09-09 | 28 | 2023-10-07 | 2023-10-02 | 461776.49 | 21352041.9 |  |  | 1199203.75 | [6 empty] | 0
MDF Factory - Equip. | 20 | 2023-09-30 | 2023-09-30 | 2023-10-16 | 28 | 2023-11-13 | [12 empty] | 0
MDF Factory - Equip. | 21 | 2023-12-31 | 2023-12-20 | 2023-12-25 | 28 | 2024-01-22 | 2024-02-06 | 540952.41 | 22578347.52 |  |  | 592013.93 | [6 empty] | 0
MDF Factory - Equip. | 22 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 28 | 2024-04-28 | [12 empty] | 0
MDF Factory - Equip. | 23 | 2024-04-30 | 2024-04-15 | 2024-05-02 | 28 | 2024-05-30 | 2024-05-08 | 539934.96 | 23413265.89 |  |  | 638068.17 | [6 empty] | 0
MDF Factory - Equip. | 24 | 2024-04-30 | 2024-04-15 | 2024-05-08 | 28 | 2024-06-05 | 2024-05-21 | 250311 | 23663576.89 |  |  | 252814.11 | [6 empty] | 0
MDF Factory - Equip. | 25 | 2024-06-30 | 2024-06-30 | 2024-06-26 | 28 | 2024-07-24 | 2024-07-01 | 631287.83 | 24294864.72 |  |  | 637600.71 | [6 empty] | 0
MDF Factory - Equip. | 26 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 28 | 2024-09-29 | 2024-10-02 | 1237289.1 | 25532153.82 |  |  | 1250071.98 | [6 empty] | 0
MDF Factory - Equip. | 27 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 28 | 2024-10-28 | 2024-10-17 | 20666.66 | 25552820.48 |  |  | 2574782 | [6 empty] | 0
MDF Factory - Local Fabrication | 1 | 2022-02-28 | 2022-02-15 | 2022-03-03 | 28 | 2022-03-31 | [12 empty] | 0
MDF Factory - Local Fabrication | 2 | 2022-03-31 | 2022-03-15 | 2022-03-21 | 28 | 2022-04-18 | [12 empty] | 0
MDF Factory - Local Fabrication | 3 | 2022-03-31 | 2022-04-10 | 2022-04-13 | 28 | 2022-05-11 | 2022-05-10 | 1275030.41 | 7663208.07 |  |  | 926763.57 |  |  |  |  | 330996.915 | 330996.915 | 0
MDF Factory - Local Fabrication | 4 | 2022-05-31 | 2022-05-15 | 2022-05-26 | 28 | 2022-06-23 | [12 empty] | 0
MDF Factory - Local Fabrication | 5 | 2022-06-30 | 2022-06-15 | 2022-06-21 | 28 | 2022-07-19 | 2022-06-20 | 3437985.57 | 11948651.83 |  |  | 2517906.93 |  |  |  |  | 597432.59 | 597432.59 | 45737
MDF Factory - Local Fabrication | 6 | 2022-07-31 | 2022-07-15 | 2022-08-11 | 28 | 2022-09-08 | 2022-09-22 | 1016613.3233 | 12965265.1533 |  |  | 737044.172 | [6 empty] | 0
MDF Factory - Local Fabrication | 7 | 2022-08-31 | 2022-08-15 | 2022-08-30 | 28 | 2022-09-27 | 2022-09-22 | 2281868.7949 | 15247133.9482 |  |  | 785269.1906 | [6 empty] | 0
MDF Factory - Local Fabrication | 8 | 2022-09-30 | 2022-09-15 | 2022-09-22 | 28 | 2022-10-20 | 2022-09-22 | 619278.6162 | 15866412.5644 |  |  | 1318063.6318 | [6 empty] | 0
MDF Factory - Local Fabrication | 9 | 2022-10-31 | 2022-11-15 | 2022-11-16 | 28 | 2022-12-14 | [12 empty] | 0
MDF Factory - Local Fabrication | 10 | 2022-11-30 | 2022-12-15 | 2022-12-26 | 28 | 2023-01-23 | [12 empty] | 0
MDF Factory - Local Fabrication | 11 | 2023-01-31 | 2023-01-15 | 2023-02-18 | 28 | 2023-03-18 | [12 empty] | 0
MDF Factory - Local Fabrication | 12 | 2023-03-31 | 2023-03-15 | 2023-04-03 | 28 | 2023-05-01 | [12 empty] | 0
MDF Factory - Local Fabrication | 13 | 2023-06-30 | 2023-06-15 | 2023-06-21 | 28 | 2023-07-19 | [12 empty] | 0
MDF Factory - Local Fabrication | 14 | 2023-07-31 | 2023-08-15 | 2023-08-29 | 28 | 2023-09-26 | 2023-10-02 | 12083527.18 | 41889851.51 |  |  | 11829412.85 |  | 24971308.61 |  |  | 2094492.575 | 2094492.575 | 112541
MDF Factory - Local Fabrication | 15 | 2023-08-31 | 2023-10-15 | 2023-11-08 | 28 | 2023-12-06 | 2023-12-18 | 5403242.47 | 47293093.98 |  |  | 5457274.9 |  |  |  |  | 2364654.7 | 2364654.7 | 112541
MDF Factory - Local Fabrication | 16 | 2023-11-30 | 2023-11-15 | 2023-12-03 | 28 | 2023-12-31 | 2024-02-11 | 1250000 | 48543093.98 |  |  | 1262500 |  |  |  |  | 2427154.7 | 2427154.7 | 66804
MDF Factory - Local Fabrication | 17 | 2023-12-31 | 2023-12-25 | 2023-12-25 | 28 | 2024-01-22 | 2024-04-22 | -0.001 | 48543093.98 |  |  | 0.0001 |  |  |  |  | 2427154.7 | 2427154.7 | 112541
MDF Factory - Local Fabrication | 18 | 2024-01-31 | 2024-01-15 | 2024-02-06 | 28 | 2024-03-05 | 2024-02-22 | 4414101.95 | 52957195.93 |  |  | 4458904.86 |  |  |  |  | 2647859.795 | 2647859.795 | 112541
MDF Factory - Local Fabrication | 19 | 2024-02-29 | 2024-03-15 | 2024-03-20 | 28 | 2024-04-17 | 2024-04-04 | 4220898.94 | 57178094.87 |  |  | 4456901.8 |  |  |  |  | 2858904.5 | 2858904.5 | 882541
MDF Factory - Local Fabrication | 20 | 2024-05-31 | 2024-05-15 | 2024-07-03 | 28 | 2024-07-31 | 2024-07-29 | 1196029.38 | 58374124.25 |  |  | 2286278.72 |  |  |  |  | 2918706 | 2918706 | 66804
Mechanical Installation | 1 | 2024-01-31 | 2024-01-31 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 96641266.36 | 96641266.36 | 15000000 |  | 2845427.8 | [6 empty] | 0
Mechanical Installation | 9 | 2024-05-31 | 2024-05-31 | 2024-06-01 | 42 | 2024-07-13 | [12 empty] | 0
Mintra | 1 | 2018-05-31 | 2018-05-29 | 2018-07-09 | 15 | 2018-07-24 | 2018-09-18 | 26487256.44 | 26487256.44 | 10000000 |  | 2860852.09 | 0 | [5 empty] | 17226261.898
Mintra | 2 | 2018-07-31 | 2018-07-21 | 2018-07-25 | 15 | 2018-08-09 | 2018-09-23 | 16295714.9 | 42782971.34 |  |  | 1791407.73 | 3426213 | [5 empty] | 31002926.91
Mintra | 3 | 2018-08-31 | 2018-09-15 | 2018-09-23 | 15 | 2018-10-08 | 2018-10-15 | 19469085.79 | 62252057.13 |  |  | 2220782.14 | 0 | [5 empty] | 41220014.7
Mintra | 4 | 2018-09-30 | 2018-10-10 | 2018-10-29 | 15 | 2018-11-13 | 2018-11-18 | 9723925.4204 | 71975982.5504 |  |  | 2907075.5801 | [6 empty] | 47988244.922
Mintra | 5 | 2018-11-30 | 2018-12-10 | 2018-12-18 | 15 | 2019-01-02 | [12 empty] | 0
Mintra | 6 | 2019-03-31 | 2019-03-28 | 2019-04-15 | 15 | 2019-04-30 | [12 empty] | 0
Mintra | 7 | 2019-09-30 | 2019-11-17 | 2021-02-03 | 15 | 2021-02-18
Mintra-Hanger 1200m2 | 1 | 2018-10-31 | 2018-10-18 | 2018-10-21 | 15 | 2018-11-05 | 2018-10-29 | 1411985.3421 | 1411985.3421 |  |  | 531998.6721 | [6 empty] | 879986.67
Mintra-Hanger 1200m2 | 2 | 2019-09-30 | 2019-09-30 | 2021-02-03 | 15 | 2021-02-18 | [12 empty] | 0
Mivida-PK#140 | 1 | 2019-05-31 | 2019-05-31 | 2019-06-10 | 40 | 2019-07-20 | 2019-06-27 | 4797449.5194 | 4797449.5194 | 15567604.3 |  | 2533668.0255 | 0 | [5 empty] | 45335.898
Mivida-PK#140 | 2 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 40 | 2019-08-13 | 2019-07-21 | 4911239.0806 | 9708688.6 | 7313962.6 |  | 2620895.13 | [6 empty] | 91747.11
Mivida-PK#140 | 3 | 2019-07-31 | 2019-07-31 | 2019-08-04 | 40 | 2019-09-13 | 2019-08-20 | 6244069.8629 | 15952758.4629 |  |  | 4070832.3885 | 207615.6315 | [5 empty] | 152651.9264
Mivida-PK#140 | 4 | 2019-08-31 | 2019-08-31 | 2019-09-01 | 40 | 2019-10-11 | 2019-09-17 | 2442385.7689 | 18395144.2317 |  |  | 999645.4398 | 207615.6315 | [5 empty] | 175732.4719
Mivida-PK#140 | 5 | 2019-09-30 | 2019-09-30 | 2019-10-02 | 40 | 2019-11-11 | 2019-10-23 | 1994559.8383 | 20389704.07 |  |  | 1337507.07 | 207615.63 | [5 empty] | 194581.06
Mivida-PK#140 | 6 | 2019-10-31 | 2019-11-06 | 2019-11-06 | 40 | 2019-12-16 | 2019-12-10 | 12232780.54 | 32622484.61 |  |  | 10719905.2391 | 1084016.3529 | [5 empty] | 318038.6268
Mivida-PK#140 | 7 | 2019-11-30 | 2019-12-05 | 2019-12-05 | 40 | 2020-01-14 | 2019-12-19 | 7170532.1164 | 39793016.7264 |  |  | 6547225.8223 | 1960077.2048 | [5 empty] | 414859.7029
Mivida-PK#140 | 8 | 2019-12-31 | 2020-01-06 | 2020-01-06 | 40 | 2020-02-15 | 2020-02-13 | 6113446.7536 | 45906463.48 |  |  | 4740517.5525 | 1612694.6715 | [5 empty] | 473905.3319
Mivida-PK#140 | 9 | 2020-01-31 | 2020-02-05 | 2020-02-06 | 40 | 2020-03-17 | 2020-03-18 | 4233335.7568 | 50139799.2368 |  |  | 4559999.0726 | 3026730.6056 | [5 empty] | 545336.6782
Mivida-PK#140 | 10 | 2020-02-29 | 2020-03-05 | 2020-03-05 | 40 | 2020-04-14 | 2020-04-29 | 6612227.7834 | 56752027.0202 |  |  | 5679423.0614 | 3351448.8206 | [5 empty] | 610744.6947
Mivida-PK#140 | 11 | 2020-03-31 | 2020-04-02 | 2020-04-02 | 40 | 2020-05-12 | 2020-04-29 | 3124627.5928 | 59876654.613 |  |  | 2647674.1799 | 3468836.925 | [5 empty] | 649303.9184
Mivida-PK#140 | 12 | 2020-04-30 | 2020-05-02 | 2020-05-03 | 40 | 2020-06-12 | 2020-05-21 | 1875813.048 | 61752467.661 |  |  | 4687303.4253 | 7497245.0417 | [5 empty] | 703286.0248
Mivida-PK#140 | 13 | 2020-05-31 | 2020-06-01 | 2020-06-01 | 40 | 2020-07-11 | 2020-06-21 | 1425866.309 | 63178333.97 |  |  | 1169770.65 | 7496958.47 | [5 empty] | 52250
Mivida-PK#140 | 14 | 2020-06-30 | 2020-07-01 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-21 | 2429362.3736 | 65607696.3436 |  |  | 7336701.0997 | 14334387.2636 | [5 empty] | 52250
Mivida-PK#140 | 15 | 2020-07-31 | 2020-07-28 | 2020-08-06 | 40 | 2020-09-15 | 2020-08-24 | 16266667.6714 | 81874364.0149 |  |  | 10305723.5244 | 10470685.8866 | [5 empty] | 74750
Mivida-PK#140 | 16 | 2020-08-31 | 2020-09-01 | 2020-09-01 | 40 | 2020-10-11 | 2020-09-15 | 19380294.5984 | 101254658.6133 |  |  | 10553431.2394 | 3625858.6756 | [5 empty] | 74750
Mivida-PK#140 | 17 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 40 | 2020-11-13 | 2020-10-19 | 16610857.3328 | 117865515.946 |  |  | 11726998.4266 | 808207.3196 | [5 empty] | 74750
Mivida-PK#140 | 18 | 2020-10-31 | 2020-11-04 | 2020-11-09 | 40 | 2020-12-19 | 2020-11-29 | 4603925.7609 | 122469441.707 |  |  | 3831058.93 | 876421.358 | [5 empty] | 74750
Mivida-PK#140 | 19 | 2020-11-30 | 2020-12-03 | 2020-12-06 | 40 | 2021-01-15 | 2020-12-21 | 11459315.8636 | 133928757.5706 |  |  | 8885358.6191 | 214106.8575 | [5 empty] | 74750
Mivida-PK#140 | 20 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-04 | 5957491.0722 | 139886248.6428 |  |  | 5084359.8248 | 17194.8 | [5 empty] | 85700
Mivida-PK#140 | 21 | 2021-01-31 | 2021-02-04 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-18 | 9991628.9772 | 149877877.62 |  |  | 8185193.8344 | [6 empty] | 85700
Mivida-PK#140 | 22 | 2021-02-28 | 2021-03-04 | 2021-03-15 | 40 | 2021-04-24 | 2021-04-01 | 5467007.07 | 155344884.69 |  |  | 4603109.16 | [6 empty] | 85700
Mivida-PK#140 | 23 | 2021-03-31 | 2021-04-04 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-26 | 4716911.44 | 160061796.13 |  |  | 3870461.69 | [6 empty] | 85700
Mivida-PK#140 | 24 | 2021-05-31 | 2021-06-04 | 2021-06-30 | 40 | 2021-08-09 | 2021-07-15 | 4573435.8657 | 164635231.9957 |  |  | 3732732.7981 | [6 empty] | 105700
Mivida-PK#140 | 25 | 2021-06-30 | 2021-06-29 | 2021-08-18 | 40 | 2021-09-27 | 2021-08-31 | 5220299.9543 | 169855531.95 |  |  | 9016182.24 | [6 empty] | 623487.51
Mivida-PK#140 | 26 | 2021-10-31 | 2021-10-31 | 2021-11-02 | 40 | 2021-12-12 | 2021-11-21 | 3380977.62 | 173236509.57 |  |  | 3143991.79 | [6 empty] | 623487.51
Mivida-PK#140 | 27 | 2022-01-31 | 2022-01-15 | 2022-01-25 | 40 | 2022-03-06 | 2022-03-01 | 825139.1896 | 174061648.7596 |  |  | 5157960.0562 |  |  |  |  | 4569118.28 | 4569118.28 | 0
Mivida-PK#140 | 28 | 2023-05-31 | 2023-05-31 | 2023-06-08 | 40 | 2023-07-18 | 2024-07-09 | 924592.0104 | 174986240.77 |  |  | 1576397.44 |  |  |  |  | 4593388.82 | 4593388.82 | 909436.51
Mivida-PK#189 | 1 | 2022-05-31 | 2022-05-25 | 2022-05-26 | 40 | 2022-07-05 | 2022-06-16 | 15323108.5333 | 15323108.5333 | 99600000 |  | 18095262.89 | 5493727.64 |  |  |  | 559686.37 | 559686.37 | 100000
Mivida-PK#189 | 2 | 2022-06-30 | 2022-06-30 | 2022-07-05 | 40 | 2022-08-14 | 2022-08-06 | 28497042.4952 | 43820151.0286 |  |  | 22529255.8764 | 5215901.19 |  |  | 1210923 | 1280676.495 | 1280676.495 | 108208.75
Mivida-PK#189 | 3 | 2022-07-31 | 2022-08-06 | 2022-08-06 | 40 | 2022-09-15 | 2022-09-04 | 24279069.6762 | 68099220.7048 |  |  | 19800407.88 | 5069769.75 |  |  | 4205865.52 | 1914348.785 | 1914348.785 | 115793.25
Mivida-PK#189 | 4 | 2022-08-31 | 2022-09-05 | 2022-09-06 | 40 | 2022-10-16 | 2022-10-09 | 28546026.8476 | 96645247.5524 |  |  | 27644756.83 | 10542311 |  |  | 4205865.52 | 2800495.535 | 2800495.535 | 171139
Mivida-PK#189 | 5 | 2022-09-30 | 2022-10-12 | 2022-10-12 | 40 | 2022-11-21 | 2022-11-05 | 57245166.7876 | 153890414.34 |  |  | 46638711.45 | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759
Mivida-PK#189 | 6 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | -0.0001 | 153890414.34 |  |  | 70000000 | 10264387.5 |  |  | 12041167.31 | 4296233.065 | 4296233.065 | 287759
Mivida-PK#189 | 7 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 40 | 2022-12-20 | 2022-12-05 | 39773865.3076 | 193664279.6476 |  |  | 38664242.9 | 7682397 |  |  | 14543436.55 | 5529931.65 | 5529931.65 | 187759
Mivida-PK#189 | 8 | 2022-11-30 | 2022-12-12 | 2022-12-14 | 40 | 2023-01-23 | 2023-01-01 | 90047890.8024 | 283712170.45 |  |  | 62566272.81 | 3898975.5 |  |  | 19923003.68 | 7544918.86 | 7544918.86 | 608067.35
Mivida-PK#189 | 9 | 2022-12-31 | 2023-01-05 | 2023-01-09 | 40 | 2023-02-18 | 2023-01-24 | 42271935.09 | 325984105.54 |  |  | 37089197.56 | 7037273.25 |  |  | 24970230.92 | 8733014.6 | 8733014.6 | 657611
Mivida-PK#189 | 10 | 2023-01-31 | 2023-02-01 | 2023-02-01 | 40 | 2023-03-13 | 2023-02-26 | 29038558.46 | 355022664 |  |  | 22123110.41 | 7032573.83 |  | 285000 | 27238935.45 | 9495159.275 | 9495159.275 | 573417.35
Mivida-PK#189 | 11 | 2023-02-28 | 2023-03-01 | 2023-03-08 | 40 | 2023-04-17 | 2023-04-10 | 23000800.56 | 378023464.56 |  |  | 18794302.38 | 6675607.4 |  | 55000 | 34635720.71 | 10090006.13 | 10090006.13 | 603461
Mivida-PK#189 | 12 | 2023-03-31 | 2023-04-01 | 2023-04-09 | 40 | 2023-05-19 | 2023-05-08 | 15682494.86 | 393705959.42 |  |  | 16890748.07 | 11930576.4 |  | 90000 | 36499853.4 | 10633045.845 | 10633045.845 | 652617.35
Mivida-PK#189 | 13 | 2023-04-30 | 2023-05-05 | 2023-05-09 | 40 | 2023-06-18 | 2023-06-06 | 16636045.76 | 410342005.18 |  |  | 50032149.1 | 58593047.95 | 1714555.5 | 140000 | 38456764.67 | 12236303.835 | 12236303.835 | 686786.1
Mivida-PK#189 | 14 | 2023-05-31 | 2023-06-05 | 2023-06-05 | 40 | 2023-07-15 | 2023-07-15 | 22729528.92 | 433071534.1 |  |  | 22045664.4 | 63146488.9 | 3995594.72 | 240000 | 42393533.94 | 12946789.995 | 12946789.995 | 750242.35
Mivida-PK#189 | 15 | 2023-06-30 | 2023-07-13 | 2023-07-18 | 40 | 2023-08-27 | 2023-08-07 | 18379426.49 | 451450960.59 |  |  | 20013901.03 | 71534780.44 | 7645358.03 | 330000 | 45605336.83 | 13638957.225 | 13638957.225 | 782829.85
Mivida-PK#189 | 16 | 2023-07-31 | 2023-08-15 | 2023-08-17 | 40 | 2023-09-26 | 2023-09-20 | 24459783.7762 | 475910744.3662 |  |  | 22512171.8728 | 78434225.1876 | 8773118.9707 | 230000 | 50069955.0917 | 14453512.665 | 14453512.665 | 832885.35
Mivida-PK#189 | 17 | 2023-09-30 | 2023-09-25 | 2023-09-27 | 40 | 2023-11-06 | 2023-10-17 | 30434807.7338 | 506345552.1 |  |  | 47104890.06 | 73723080.15 | 9982715.55 | 390000 | 53354142.27 | 15134647.745 | 15134647.745 | 859629.1
Mivida-PK#189 | 18 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 40 | 2023-12-10 | 2023-12-02 | 18563752.6 | 524909304.7 |  |  | 20024965.62 | 79805243.6 | 11738051.38 | 340000 | 54783582.6 | 15774000.34 | 15774000.34 | 870216.6
Mivida-PK#189 | 19 | 2023-11-30 | 2023-11-25 | 2023-12-02 | 40 | 2024-01-11 | 2024-01-02 | 21710553.3095 | 546619858.0095 |  |  | 23323710.1 | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1
Mivida-PK#189 | 20 | 2023-11-30 | 2023-11-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-11 | -0.0003 | 546619858.0095 |  | 135145955 |  | 86630343.53 | 13959126.25 | 160000 | 57001636.73 | 16514529.86 | 16514529.86 | 874754.1
Mivida-PK#189 | 21 | 2023-12-31 | 2023-12-25 | 2024-01-02 | 40 | 2024-02-11 | 2024-01-24 | 22586754.7048 | 569206612.7143 |  |  | 14476604.63 | 81314246.26 | 16546391.27 | 130000 | 59318989.42 | 16974529.74 | 16974529.74 | 807307.6
Mivida-PK#189 | 22 | 2024-01-31 | 2024-01-30 | 2024-02-04 | 40 | 2024-03-15 | 2024-02-27 | 23140993.5357 | 592347606.25 |  |  | 17552609 | 88194427.7 | 17630743.31 | 130000 | 61582414.39 | 17753985.355 | 17753985.355 | 900122.85
Mivida-PK#189 | 23 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 40 | 2024-04-15 | 2024-04-21 | 30858954.27 | 623206560.52 |  |  | 14242173.08 | 84128553.28 | 31879195.04 | 260000 | 64992287.15 | 18462386.045 | 18462386.045 | 912222.85
Mivida-PK#189 | 24 | 2024-03-31 | 2024-03-31 | 2024-01-04 | 40 | 2024-02-13 | 2024-05-22 | 16112816.1181 | 639319376.6381 |  |  | 13803484.93 | 96423729.78 | 32655160.1 | 130000 | 66746916.67 | 19192726.88 | 19192726.88 | 1304406.85
Mivida-PK#189 | 25 | 2024-04-30 | 2024-04-30 | 2024-05-09 | 40 | 2024-06-18 | 2024-06-06 | 29437278.3119 | 668756654.95 |  |  | 28360739.45 | 101680151.25 | 44526060.5 | 30000 | 69988148.31 | 20096865.975 | 20096865.975 | 1306194.35
Mivida-PK#189 | 26 | 2024-05-31 | 2024-05-30 | 2024-06-01 | 40 | 2024-07-11 | 2024-07-03 | 16876594.42 | 685633249.37 |  |  | 14177811.24 | 113839940.35 | 49627280.83 | 230000 | 71860776.18 | 20843871.305 | 20843871.305 | 1314994.35
Mivida-PK#189 | 27 | 2024-06-30 | 2024-06-30 | 2024-07-01 | 40 | 2024-08-10 | 2024-08-01 | 14919836.13 | 700553085.5 |  |  | 4389859.04 | 115715406.16 | 55352768.73 | 130000 | 73509397.76 | 21282403.65 | 21282403.65 | 5470850.6
Mivida-PK#189 | 28 | 2024-07-31 | 2024-07-30 | 2024-08-01 | 40 | 2024-09-10 | 2024-08-31 | 3487392.66 | 704040478.16 |  |  | 2409288.21 | 115148780.66 | 49698695.44 | 130000 | 73901796.57 | 21359782.07 | 21359782.07 | 5480338.1
Mivida-PK#189 | 29 | 2024-08-31 | 2024-08-31 | 2024-09-18 | 40 | 2024-10-28 | 2024-09-26 | 369049.79 | 704409527.95 |  |  | 2690517.47 | 118334746.14 | 36219473.08 | 230000 | 73927905.13 | 21449118.76 | 21449118.76 | 5482400
Mivida-PK#189 | 30 | 2024-09-30 | 2024-09-30 | 2024-10-09 | 40 | 2024-11-18 | 2024-11-12 | 17653522.66 | 722063050.61 |  |  | 14412191.13 | 118972314.89 | 37380637.32 | 230000 | 80926432.97 | 22053462.95 | 22053462.95 | 9961433.24
Mivida-PK#189 | 31 | 2024-10-31 | 2024-10-31 | 2024-11-01 | 40 | 2024-12-11 | [12 empty] | 0
Mobilization | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-02-28 | 3847983.19 | 3847983.19 |  |  | 475188.5 | [6 empty] | 0
MOC | 1 | 2024-05-31 | 2024-06-08 | 2024-05-05 | 40 | 2024-06-14 | [12 empty] | 0
MOC | 2 | 2024-06-30 | 2024-07-15 | 2024-07-15 | 40 | 2024-08-24 | [12 empty] | 0
MOC - DP | 1 | 2024-04-30 | 2024-04-01 | 2024-04-01 | 40 | 2024-05-11 | [12 empty] | 0
New Gas Station | 1 | 2023-10-31 | 2023-10-31 | 2023-11-02 | 42 | 2023-12-14 | 2023-11-02 | 3190160 | 3190160 |  |  | 2360718.4 | [6 empty] | 0
New Gas Station | 2 | 2023-12-31 | 2023-12-31 | 2024-01-01 | 42 | 2024-02-12 | [12 empty] | 0
New Gas Station | 3 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 42 | 2024-03-14 | 2024-02-07 | 2793703.2 | 7183858 |  |  | 1433129.44 | [6 empty] | 0
New Gas Station | 4 | 2024-04-30 | 2024-04-21 | 2024-04-21 | 42 | 2024-06-02 | 2024-04-28 | 6707619.99 | 13891477.99 |  |  | 4963638.79 | [6 empty] | 0
New Giza Hospital | 1 | 2022-01-31 | 2022-01-30 | 2022-02-01 | 51 | 2022-03-24 | 2022-02-14 | 34312846.6 | 34312846.6 | 73512565 |  | 23504299.92 | [6 empty] | 0
New Giza Hospital | 2 | 2022-02-28 | 2022-02-28 | 2022-03-05 | 51 | 2022-04-25 | 2022-03-21 | 20701192.62 | 55014039.22 |  |  | 13966904.63 | [6 empty] | 0
New Giza Hospital | 3 | 2022-03-31 | 2022-03-15 | 2022-03-20 | 51 | 2022-05-10 | 2022-03-28 | -0.0001 | 55014039.22 |  |  | 7088017.77 |  |  |  |  | 1642229.32 | 1642229.32 | 0
New Giza Hospital | 4 | 2022-03-31 | 2022-03-31 | 2022-04-06 | 51 | 2022-05-27 | 2022-04-24 | 43472048.71 | 98486087.93 |  |  | 25608972.36 |  |  |  |  | 2584225.375 | 2584225.375 | 0
New Giza Hospital | 5 | 2022-04-30 | 2022-05-10 | 2022-05-10 | 51 | 2022-06-30 | 2022-05-25 | 15040366.17 | 113526454.1 |  |  | 10219240.4 |  |  |  | 12821619 | 2978829.635 | 2978829.635 | 447088.63
New Giza Hospital | 6 | 2022-05-31 | 2022-05-31 | 2022-06-15 | 51 | 2022-08-05 | 2022-06-21 | 21219859 | 134746313.1 |  |  | 14292844 |  |  |  | 12821619 | 3534103.595 | 3534103.595 | 0
New Giza Hospital | 7 | 2022-06-30 | 2022-06-30 | 2022-06-23 | 51 | 2022-08-13 | 2022-07-04 | 20073764.28 | 154820077.38 |  |  | 13315074.93 |  |  |  | 12821619.84 | 4060000.94 | 4060000.94 | 0
New Giza Hospital | 8 | 2022-07-31 | 2022-08-07 | 2022-08-23 | 51 | 2022-10-13 | 2022-08-28 | 18180164.07 | 173000241.45 |  |  | 12573205.03 |  |  |  | 12821619 | 4536350.625 | 4536350.625 | 2987283.85
New Giza Hospital | 9 | 2022-08-31 | 2022-09-11 | 2022-09-14 | 51 | 2022-11-04 | 2022-09-22 | 23318711.12 | 196318952.57 |  |  | 15620677.42 |  |  |  | 12821619.84 | 5147515.86 | 5147515.86 | 3790429.25
New Giza Hospital | 10 | 2022-09-30 | 2022-10-15 | 2022-10-18 | 51 | 2022-12-08 | 2022-11-03 | 22254898.64 | 218573851.21 |  |  | 14944068.34 |  |  |  | 12821619.84 | 5731166.305 | 5731166.305 | 3910342.85
New Giza Hospital | 11 | 2022-10-31 | 2022-11-10 | 2022-11-10 | 51 | 2022-12-31 | 2022-12-07 | 29701638.2 | 248275489.41 |  |  | 19999087.83 |  | 47447.2 |  | 12821619.84 | 6509322.02 | 6509322.02 | 3819797.85
New Giza Hospital | 12 | 2022-11-30 | 2022-12-06 | 2022-12-08 | 51 | 2023-01-28 | 2022-12-29 | 25988546.64 | 274264036.05 |  |  | 21046664.64 | 4878335.3 | 1113844.57 |  | 12821619.84 | 7307779.5 | 7307779.5 | 3966447.85
New Giza Hospital | 13 | 2022-12-31 | 2023-01-05 | 2023-01-08 | 51 | 2023-02-28 | 2023-02-06 | 24670486.27 | 298934522.32 |  |  | 18169651.25 | 7074573 | 1237105.25 |  | 12821619.84 | 8008229.795 | 8008229.795 | 3886497.85
New Giza Hospital | 14 | 2023-01-31 | 2023-02-11 | 2023-02-09 | 51 | 2023-04-01 | 2023-03-14 | 21692266.85 | 320626789.17 |  |  | 14731551.62 | 6879606.09 | 1773014.33 |  | 12821619.84 | 8574509.66 | 8574509.66 | 4107797.85
New Giza Hospital | 15 | 2023-02-28 | 2023-03-14 | 2023-03-16 | 51 | 2023-05-06 | 2023-04-18 | 23725978.81 | 344352767.98 |  |  | 14839693.08 | 5193267.92 | 2584321.32 |  | 12821619.84 | 9154018.005 | 9154018.005 | 4143497.85
New Giza Hospital | 16 | 2023-04-30 | 2023-04-19 | 2023-04-30 | 51 | 2023-06-20 | 2023-05-14 | 22492246.1 | 366845014.08 |  |  | 15222233.72 | 4834698.32 | 3206608.76 |  | 12821619.84 | 9734385.435 | 9734385.435 | 3938997.85
New Giza Hospital | 17 | 2023-05-31 | 2023-05-31 | 2023-06-03 | 51 | 2023-07-24 | 2023-07-04 | 21612019.52 | 388457033.6 |  |  | 12680990.84 | 4817538.46 | 3364840.52 |  | 12821619.84 | 10300141.21 | 10300141.21 | 6117327.71
New Giza Hospital | 18 | 2023-06-30 | 2023-07-09 | 2023-07-12 | 51 | 2023-09-01 | 2023-08-06 | 9332664.78 | 397789698.38 |  |  | 14934202.65 | 21298296.55 | 3366900.3 |  | 12821619.84 | 10955551.155 | 10955551.155 | 6117327.71
New Giza Hospital | 19 | 2023-08-31 | 2023-08-12 | 2023-08-13 | 51 | 2023-10-03 | 2023-09-14 | 18985757.51 | 416775455.89 |  |  | 5705542.36 | 10041623.17 | 3890054.47 |  | 12821619.84 | 11172226.045 | 11172226.045 | 6117327.71
New Giza Hospital | 20 | 2023-09-30 | 2023-09-30 | 2023-09-27 | 51 | 2023-11-17 | 2023-10-03 | -1e-07 | 416775455.89 |  |  | 18995740.42 | 10041623.17 | 3890054.47 |  | 12821619.84 | 22344452.09 |  | 6117327.71
New Giza Hospital | 21 | 2023-09-30 | 2023-09-30 | 2023-10-16 | 51 | 2023-12-06 | 2023-10-16 | 12758386.3 | 429533842.19 |  |  | 8010369.24 | 9402295.53 | 3259999.96 |  | 12821619 | 22981285.53 |  | 6117327.71
New Giza Hospital | 22 | 2023-10-31 | 2023-11-05 | 2023-11-08 | 51 | 2023-12-29 | 2023-11-30 | 18598623.84 | 448132466.03 |  |  | 8695249.6 | 2678290.23 | 4983458.07 |  | 12821619.84 | 23620700.79 |  | 6119391.71
New Giza Hospital | 23 | 2023-11-30 | 2023-12-10 | 2023-12-12 | 51 | 2024-02-01 | 2024-01-27 | 9056705.71 | 457189171.74 |  |  | 4604562.68 | 2083276.16 | 4983458.07 |  | 12821619.84 | 24065214.3 |  | 6133391.71
New Giza Hospital | 24 | 2024-01-31 | 2024-02-12 | 2024-02-13 | 51 | 2024-04-04 | 2024-04-01 | 30645299.93 | 487834471.67 |  |  | 5494905.78 | 1034048.23 | 5018947.83 |  | 12821619.84 | 25619451 |  | 8956130
New Giza Hospital | 25 | 2024-03-31 | 2024-04-06 | 2024-04-07 | 51 | 2024-05-28 | 2024-01-05 | 12955562.12 | 500790033.79 |  |  | 10195246.28 | 421352.25 | 12168583.45 |  | 12821619.84 | 26268325.91 |  | 8956130.8
New Giza Hospital | 26 | 2024-04-30 | 2024-05-12 | 2024-05-29 | 51 | 2024-07-19 | 2024-06-13 | 15191903.43 | 515981937.22 |  |  | 17232986.3 | 268661.25 | 14260202.71 |  |  | 27057529.55 |  | 23641604
New Giza Hospital | 27 | 2024-06-30 | 2024-07-14 | 2024-07-16 | 51 | 2024-09-05 | 2024-08-18 | 16227230.2 | 532209167.42 |  |  | 13715277.6 | 268661.25 | 14260202 |  | 56175000 | 30715749 |  | 20879747
New Giza Hospital | 28 | 2024-08-31 | 2024-09-11 | 2024-09-12 | 51 | 2024-11-02 | 2024-10-03 | 69437921.36 | 601647088.78 |  |  | 6800969.24 | 268661 | 18531949 |  | 56175000 | 15698247.5 | 15698247.5 | 9038450
New Giza Hospital | 29 | 2024-10-31 | 2024-10-17 | 2024-10-19 | 51 | 2024-12-09 | [12 empty] | 0
NGU 2 | 25 | 2017-09-30 | 2017-10-01 | 2017-09-16 | 28 | 2017-10-14 | 2017-10-11 | 3430150 | 140490291 |  |  |  | 1675290.17 | [5 empty] | 807366.8348
NGU 2 | 26 | 2017-11-30 | 2017-11-30 | 2018-01-23 | 28 | 2018-02-20 | 2018-05-23 | 10391625.25 | 150881916.25 |  |  | 6719251.6 | 0 | [5 empty] | 699355.4648
NGU 2 | 27 | 2019-06-30 | 2019-06-30 | 2019-07-04 | 28 | 2019-08-01 | 2019-11-02 | 3035230.3681 | 153917146.6181 |  |  | 1589855.1267 | 734008.68 | [5 empty] | 0
ORA - ZED | 1 | 2020-11-30 | 2020-11-25 | 2020-11-22 | 56 | 2021-01-17 | 2021-01-17 | 2407390.5714 | 2407390.5714 |  |  | 10345156.8 | 9271107.2 | [5 empty] | 0
ORA - ZED | 2 | 2020-12-31 | 2020-12-31 | 2020-12-22 | 56 | 2021-02-16 | 2021-01-06 | 45205427.0762 | 47612817.6476 |  | 256451321 | 37532508 | 9882492.63 | [5 empty] | 10718.8648
ORA - ZED | 3 | 2021-01-31 | 2021-02-03 | 2021-01-31 | 56 | 2021-03-28 | 2021-02-17 | 26768107.4476 | 74380925.0952 |  | 50172571.863 | 27896354 | 17071953.36 | [5 empty] | 24994.28
ORA - ZED | 4 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 56 | 2021-05-02 | 2021-03-24 | 26593168.5429 | 100974093.6381 |  | 25000000 | 20888247.393 | 20604136.5 | [5 empty] | 50275.41
ORA - ZED | 5 | 2021-03-31 | 2021-03-31 | 2021-04-06 | 56 | 2021-06-01 | 2021-05-11 | 39594206.7048 | 140568300.3429 |  | 50000000 | 33744386.154 | 16740725.26 | [5 empty] | 66054.2648
ORA - ZED | 6 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 56 | 2021-07-05 | 2021-06-08 | 13625124.4935 | 154193424.8364 |  | 10000000 | 4374377.19 | 7989637.5618 | [5 empty] | 83003.9348
ORA - ZED | 7 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 56 | 2021-08-04 | 2021-07-15 | 11321353.516 | 165514778.3524 |  | 5000000 | 5782895.78 | 3501497.22 | [5 empty] | 99063.49
ORA - ZED | 8 | 2021-06-30 | 2021-06-25 | 2021-06-30 | 56 | 2021-08-25 | 2021-08-12 | 26950096.619 | 192464874.9714 |  |  | 24387331.1 | 6088729.64 | [5 empty] | 175458.21
ORA - ZED | 9 | 2021-07-31 | 2021-07-25 | 2021-08-10 | 56 | 2021-10-05 | 2021-09-20 | 27403398.0286 | 219868273 |  |  | 22624923.97 | 5900263.67 | [5 empty] | 146376.75
ORA - ZED | 10 | 2021-08-31 | 2021-08-25 | 2021-09-09 | 56 | 2021-11-04 | 2021-09-26 | 32858070.0667 | 252726343.0667 |  |  | 29047725.55 | 8169556.06 | [5 empty] | 164670.96
ORA - ZED | 11 | 2021-09-30 | 2021-09-25 | 2021-10-14 | 56 | 2021-12-09 | 2021-11-18 | 34769848.6 | 287496191.6667 |  |  | 31056565.55 | 10971940.82 | [5 empty] | 182298.18
ORA - ZED | 12 | 2021-10-31 | 2021-10-25 | 2021-11-24 | 56 | 2022-01-19 | 2021-12-07 | 33050531.6762 | 320546723.3429 |  |  | 24536445.63 | 7308964.38 | [5 empty] | 182298.18
ORA - ZED | 13 | 2021-11-30 | 2021-11-25 | 2021-12-14 | 56 | 2022-02-08 | 2021-12-21 | 30511414.9714 | 351058138.3143 |  |  | 23914152.624 | 5524822.34 | [5 empty] | 182298.18
ORA - ZED | 14 | 2021-12-31 | 2021-12-25 | 2021-12-23 | 56 | 2022-02-17 | 2022-01-18 | 45635766.9524 | 396693905.2667 |  |  | 35917954.71 | 3084551.02 | [5 empty] | 213053.66
ORA - ZED | 15 | 2022-01-31 | 2022-01-25 | 2022-02-17 | 56 | 2022-04-14 | 2022-03-31 | 27710999.5429 | 424404904.8095 |  |  | 25550073.0625 | 6586185.1 | [5 empty] | 0
ORA - ZED | 16 | 2022-02-28 | 2022-02-25 | 2022-03-16 | 56 | 2022-05-11 | 2022-04-12 | 28676537.6667 | 453081442.4762 |  |  | 21942762.07 | 4779083.27 |  |  |  | 12012864.945 | 12012864.945 | 0
ORA - ZED | 17 | 2022-03-31 | 2022-03-25 | 2022-04-06 | 56 | 2022-06-01 | 2022-05-11 | 30883724.2667 | 483965166.7429 |  |  | 26002482 | 5232577.92 | [5 empty] | 0
ORA - ZED | 18 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-05-26 | 9956410.019 | 493921576.7619 |  |  | 6791166 | 3421449.48 | [5 empty] | 0
ORA - ZED | 19 | 2022-05-31 | 2022-05-25 | 2022-06-06 | 56 | 2022-08-01 | 2022-06-28 | 21443765.7238 | 515365342.4857 |  |  | 16483568.4889 | 1543331.93 | [5 empty] | 0
ORA - ZED | 20 | 2022-06-30 | 2022-06-25 | 2022-07-06 | 56 | 2022-08-31 | 2022-08-28 | 25297815.7745 | 540663158.2602 |  |  | 8954952.87 | 852186.4268 | [5 empty] | 0
ORA - ZED | 21 | 2022-07-31 | 2022-07-25 | 2022-08-09 | 56 | 2022-10-04 | 2022-09-11 | 9295356.7831 | 549958515.0433 |  |  | 7443624.2902 | 836488.6182 | 81555880.4439 |  | 36726721.206 | 14457323.235 | 14457323.235 | 1401842.4693
ORA - ZED | 22 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 56 | 2022-11-02 | 2022-09-28 | 9997079.1377 | 559955594.181 |  |  | 8098824.8775 | 557383.0572 | 85664325.1821 |  | 36749996.0022 | 14712768.92 | 14712768.92 | 1379966.9772
ORA - ZED | 23 | 2022-09-30 | 2022-09-25 | 2022-10-09 | 56 | 2022-12-04 | 2022-10-27 | 27314036.0095 | 587269630.1905 |  |  | 22964574.875 | 479281.1936 | 93161830.5539 |  | 36812284.0164 | 15427809.82 | 15427809.82 | 1232906.9943
ORA - ZED | 24 | 2022-12-31 | 2022-12-25 | 2023-01-18 | 56 | 2023-03-15 | 2023-03-22 | 11751887.1042 | 599021517.2946 |  |  | 7490234.3814 | 269002.8006 | 98882541.0407 |  | 36839181.7521 | 15725824.83 | 15725824.83 | 3165623.4593
ORA - ZED | 25 | 2023-02-28 | 2023-02-25 | 2023-03-12 | 56 | 2023-05-07 | 2023-04-10 | 50310527.2958 | 649332044.5905 |  |  | -9163815.8569 | 241736.3176 | 113559937.642 | 3600000 | 36956312.6915 | 17045794.51 | 17045794.51 | 465623.4593
ORA - ZED | 26 | 2023-03-31 | 2023-03-25 | 2023-04-16 | 56 | 2023-06-11 | 2023-05-01 | 19434003.5361 | 668766048.1265 |  |  | 16993731.7513 | 239033.6571 | 121577515.47 | 2750000 | 37000350.0494 | 17553262 | 17553262 | 465623.4593
ORA - ZED | 27 | 2023-04-30 | 2023-04-25 | 2023-05-15 | 56 | 2023-07-10 | 2023-06-15 | 10662740.4195 | 679428788.546 |  |  | 9042387.5614 | 229309.1567 | 124928010.98 | 2550000 | 37025174.6113 | 17832915.825 | 17832915.825 | 465623.4593
ORA - ZED | 28 | 2023-05-31 | 2023-05-25 | 2023-06-15 | 56 | 2023-08-10 | 2023-07-09 | 24304667.5968 | 703733456.1429 |  |  | 10264179.63 | 156183.3 | 132876310.5982 | 2350000 | 37192477.1578 | 18469085.205 | 18469085.205 | 489541.1493
ORA - ZED | 29 | 2023-06-30 | 2023-06-25 | 2023-07-17 | 56 | 2023-09-11 | 2023-08-24 | 27532348.019 | 731265804.1619 |  |  | 13678389.68 |  | 143774737.6483 | 2400000 | 37381001.7016 | 19187904.7592 | 19187904.7592 | 489541.1493
ORA - ZED | 30 | 2023-07-31 | 2023-07-25 | 2023-08-15 | 56 | 2023-10-10 | 2023-09-17 | 26015241.1905 | 757281045.3524 |  |  | 13092650.18 |  | 149337289.3675 | 1900000 | 37609920.1669 | 19870804.84 | 19870804.84 | 489541.1493
ORA - ZED | 31 | 2023-08-31 | 2023-08-25 | 2023-09-17 | 56 | 2023-11-12 | 2023-09-27 | 26102241.2286 | 783383286.581 |  |  | 12746258.22 |  | 156088918.0852 | 1800000 | 37790500.7321 | 20555988.67 | 20555988.67 | 508143.1541
ORA - ZED | 32 | 2023-09-30 | 2023-09-25 | 2023-10-12 | 56 | 2023-12-07 | 2023-11-11 | 24532813.9714 | 807916100.5524 |  |  | 17052495.52 |  | 169479041.6436 | 1800000 | 37962018.2328 | 21199975.0395 | 21199975.0395 | 566244.2563
ORA - ZED | 33 | 2023-10-31 | 2023-10-25 | 2023-11-11 | 56 | 2024-01-06 | 2023-12-17 | 20642302.219 | 828558402.7714 |  |  | 13971110.85 |  | 183850209.8662 | 1800000 | 38104925.5449 | 21741835.4727 | 21741835.4727 | 728244.2563
ORA - ZED | 34 | 2023-11-30 | 2023-11-25 | 2023-12-17 | 56 | 2024-02-11 | 2024-01-28 | 14702199.581 | 843260602.3524 |  |  | 11514703.33 |  | 188799507.8 | 2350000 | 38207159.3831 | 22127768.21 | 22127768.21 | 866366.5763
ORA - ZED | 35 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-02-11 | 13918410.7524 | 857179013.1048 |  |  | 11302280.92 |  | 199336628.67 | 2600000 | 40055372.1837 | 22493126.49 | 22493126.49 | 866366.5763
ORA - ZED | 36 | 2024-01-31 | 2024-01-25 | 2024-02-11 | 56 | 2024-04-07 | 2024-03-12 | 9427629.6762 | 866606642.781 |  |  | 30791363.32 |  | 202490336.7307 | 2950000 | 40124683.5553 | 22740601.77 | 22740601.77 | 1287275.408
ORA - ZED | 37 | 2024-02-29 | 2024-02-25 | 2024-03-12 | 56 | 2024-05-07 | 2024-04-24 | 11141064.9524 | 877747707.7333 |  |  | 9469567.93 |  | 205574473.0325 | 3350000 | 40202154.5368 | 23033054.728 | 23033054.728 | 1416236.983
ORA - ZED | 38 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-09 | 15909843.4381 | 893657551.1714 |  |  | 12665876.69 |  | 212207212.1568 | 3550000 | 40322143.2235 | 23450688.1182 | 23450688.1182 | 1426063.9
ORA - ZED | 39 | 2024-04-30 | 2024-04-25 | 2024-05-09 | 56 | 2024-07-04 | 2024-06-06 | 9971577.2286 | 903629128.4 |  |  | 7606231.5 |  | 212836770.28 | 5150000 | 40471225.4023 | 23712442.02 | 23712442.02 | 1543257.113
ORA - ZED | 40 | 2024-05-31 | 2024-05-25 | 2024-06-06 | 56 | 2024-08-01 | 2024-07-01 | 7576454.8952 | 911205583.2952 |  |  | 6599009.58 |  | 217295013.586 | 5311993 | 40584498.7969 | 23911323.96 | 23911323.96 | 1866239.86
ORA - ZED | 41 | 2024-06-30 | 2024-06-25 | 2024-07-16 | 56 | 2024-09-10 | 2024-08-31 | 4542501.819 | 915748085.1143 |  |  | 3961614.17 |  | 218624574.9261 | 4611993 | 40652412.433 | 24038387.2343 | 24038387.2343 | 2836219.6905
ORA - ZED | 42 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-01 | 5377971.181 | 921126056.2952 |  |  | 3504951.97 |  | 221585074.8608 | 5650000 | 40732816.931 | 24179558.9777 | 24179558.9777 | 3321663.778
ORA - ZED | 43 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-22 | 11538786.4 | 932664842.6952 |  |  | 11004454.56 |  | 225919078.57 | 5200000 | 40983305.2755 | 24482452.12 | 24482452.12 | 3555974.5005
ORA - ZED | 44 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 5304711.9524 | 937969554.6476 |  |  | 4559905.68 |  | 231364687.5663 | 5600000 | 41098461.9713 | 24621700.8095 | 24621700.8095 | 3555974.5005
ORA - ZED | 45 | 2024-10-31 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 | [12 empty] | 0
ORA - ZED - Landscape | 1 | 2022-11-30 | 2022-11-25 | 2022-12-11 | 56 | 2023-02-05 | 2022-12-20 | 2611606.8286 | 2611606.8286 |  |  | 2167633.6703 |  | 503419.5862 |  |  | 68554.675 | 68554.675 | 0
ORA - ZED - Landscape | 2 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-01 | 2071867.5333 | 4683474.3619 |  |  | 1719650.0563 |  | 1329550.324 |  | 30299.3908 | 122941.2 | 122941.2 | 0
ORA - ZED - Landscape | 3 | 2023-01-31 | 2023-01-25 | 2023-01-25 | 56 | 2023-03-22 | 2023-02-26 | 2138801.7905 | 6822276.1524 |  |  | 1775205.4809 |  | 2116384.0303 |  | 118260.296 | 179084.745 | 179084.745 | 0
ORA - ZED - Landscape | 4 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-10 | 4909563.9143 | 11731840.0667 |  |  | 4074938.0511 |  | 4050371.3819 |  | 639071.4395 | 307960.8 | 307960.8 | 0
ORA - ZED - Landscape | 5 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 3861209.6 | 15593049.6667 |  |  | 3204803.968 |  | 5404662.8768 |  | 772348.3981 | 409317.55 | 409317.55 | 0
ORA - ZED - Landscape | 6 | 2023-04-30 | 2023-04-25 | 2023-05-11 | 56 | 2023-07-06 | 2023-06-07 | 3232045.3524 | 18825095.019 |  |  | 3160913.3163 |  | 6624089.2242 |  | 816946.8694 | 494158.74 | 494158.74 | 0
ORA - ZED - Landscape | 7 | 2023-05-31 | 2023-05-25 | 2023-06-07 | 56 | 2023-08-02 | 2023-07-17 | 1440674.7619 | 20265769.781 |  |  | 1045760.0532 |  | 7155995.1362 |  | 835084.5832 | 531976.455 | 531976.455 | 0
ORA - ZED - Landscape | 8 | 2023-06-30 | 2023-06-25 | 2023-07-09 | 56 | 2023-09-03 | 2023-08-09 | 11600772.2694 | 31866542.0504 |  |  | 9578640.9799 |  | 10056562.0507 | 200000 | 5892201.0451 | 836496.7288 | 836496.7288 | 0
ORA - ZED - Landscape | 9 | 2023-07-31 | 2023-07-25 | 2023-08-07 | 56 | 2023-10-02 | 2023-09-17 | 3994751.4353 | 35861293.4857 |  |  | 3636861.9198 |  | 10889989.7064 |  | 5974589.29 | 941358.95 | 941358.95 | 0
ORA - ZED - Landscape | 10 | 2023-08-31 | 2023-08-25 | 2023-09-10 | 56 | 2023-11-05 | 2023-10-10 | 3258480.2857 | 39119773.7714 |  |  | 2654538.63 |  | 12128157.28 | 50000 | 6008554.2 | 1026894.06 | 1026894.06 | 0
ORA - ZED - Landscape | 11 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-04 | 6742108.1048 | 45861881.8762 |  |  | 6014170.71 |  | 14252099.55 | 100000 | 6064800 | 1203874 | 1203874 | 0
ORA - ZED - Landscape | 12 | 2023-10-31 | 2023-10-25 | 2023-11-06 | 56 | 2024-01-01 | 2023-11-20 | 9303031.3714 | 55164913.2476 |  |  | 7521516.04 |  | 16356170.6 | 300000 | 6136800.24 | 1448078.975 | 1448078.975 | 0
ORA - ZED - Landscape | 13 | 2023-11-30 | 2023-11-25 | 2023-12-11 | 56 | 2024-02-05 | 2024-02-20 | -692002.6286 | 54472910.619 |  |  | -674362.19 |  | 13854310.92 | 400000 | 6133954.27 | 1429913.905 | 1429913.905 | 0
ORA - ZED - Landscape | 14 | 2023-12-31 | 2023-12-25 | 2024-01-16 | 56 | 2024-03-12 | 2024-03-20 | 1197004.6952 | 55669915.3143 |  |  | 1008333.54 |  | 14304471.38 | 385180.36 | 6143327.5 | 1461335.275 | 1461335.275 | 0
ORA - ZED - Landscape | 15 | 2024-01-31 | 2024-01-25 | 2024-02-06 | 56 | 2024-04-02 | 2024-04-20 | 3753240.219 | 59423155.5333 |  |  | 5175911.36 |  | 16680600.84 | 335180.36 | 5731208.99 | 1559857.835 | 1559857.835 | 0
ORA - ZED - Landscape | 16 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-03-30 | 1773392.8381 | 61196548.3714 |  |  | 1521916.05 |  | 14544514.79 | 285180.36 | 5755565.16 | 1606409.395 | 1606409.395 | 0
ORA - ZED - Landscape | 17 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-04-28 | 1582674.7048 | 62779223.0762 |  |  | 1313620 |  | 15060209.78 | 285180.36 | 5766649.95 | 1647954.605 | 1647954.605 | 0
ORA - ZED - Landscape | 18 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-05-14 | 1979868.8571 | 64759091.9333 |  |  | 1643291.15 |  | 16924136.12 | 285180.36 | 5796250.4 | 1699926.165 | 1699926.165 | 0
ORA - ZED - Landscape | 19 | 2024-05-31 | 2024-05-25 | 2024-06-04 | 56 | 2024-07-30 | 2024-07-07 | 1453055.0476 | 66212146.981 |  |  | 168189.5 |  | 17189828.91 | 785180.36 | 5817974.6 | 1738068.86 | 1738068.86 | 0
ORA - ZED - Landscape | 20 | 2024-06-30 | 2024-06-25 | 2024-07-07 | 56 | 2024-09-01 | 2024-07-23 | 1399335.6857 | 67611482.6667 |  |  | 1244123 |  | 17563515.19 | 335180.36 | 5838895.67 | 1774801.42 | 1774801.42 | 0
ORA - ZED - Landscape | 21 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-09-05 | 422349.9905 | 68033832.6571 |  |  | 189683.6223 |  | 17849734.0836 | 385180.36 | 5845210.1017 | 1785888.105 | 1785888.105 | 0
ORA - ZED - Landscape | 22 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-09-16 | 4226377.8476 | 72260210.5048 |  |  | 1388299.8 |  | 19837405.71 | 935180.36 | 5908397.46 | 1896830.525 | 1896830.525 | 0
ORA - ZED - Landscape | 23 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-15 | 1124749.1714 | 73384959.6762 |  |  | 1551640.48 |  | 20272182.95 | 435180.36 | 5961374.39 | 1926355.19 | 1926355.19 | 0
ORA - ZED - Landscape | 24 | 2024-10-31 | 2024-10-25 | 2024-11-10 | 56 | 2025-01-05 | [12 empty] | 0
ORA - ZED - ph.02 | 1 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 56 | 2021-12-01 | 2021-10-13 | 13196047.2 | 13196047.2 |  | 25000000 | 14536703 | 4533956.5 | [5 empty] | 0
ORA - ZED - ph.02 | 2 | 2021-10-31 | 2021-10-25 | 2021-11-15 | 56 | 2022-01-10 | 2021-11-14 | 21711682.2 | 34907729.4 |  | 15000000 | 20471935.87 | 7634922.31 | [5 empty] | 0
ORA - ZED - ph.02 | 3 | 2021-11-30 | 2021-11-25 | 2021-12-05 | 56 | 2022-01-30 | 2022-01-18 | 15579509.1905 | 50487238.5905 |  | 3000000 | 9325143.2186 | 3073305.59 | [5 empty] | 0
ORA - ZED - ph.02 | 4 | 2021-12-31 | 2021-12-26 | 2021-12-26 | 56 | 2022-02-20 | 2022-02-15 | 34347323.4857 | 84834562.0762 |  | 26000000 | 28728856.62 | 3352350.21 | [5 empty] | 0
ORA - ZED - ph.02 | 5 | 2022-01-31 | 2022-01-25 | 2022-02-10 | 56 | 2022-04-07 | 2022-03-23 | 10060643.6952 | 94895205.7714 |  |  | 12407122.37 | 8683284.6 | [5 empty] | 0
ORA - ZED - ph.02 | 6 | 2022-02-28 | 2022-02-25 | 2022-03-21 | 56 | 2022-05-16 | 2022-05-10 | 23225104.4643 | 118120310.2353 |  |  | 16610990.7481 | 5575171.2714 |  |  |  | 3240037.4255 | 3240037.4255 | 0
ORA - ZED - ph.02 | 7 | 2022-03-31 | 2022-03-25 | 2022-04-04 | 56 | 2022-05-30 | 2022-08-07 | 42383851.5888 | 160504161.8242 |  |  | 32100388.5958 | 1563640.4346 |  |  |  | 4252325.255 | 4252325.255 | 273333.59
ORA - ZED - ph.02 | 8 | 2022-04-30 | 2022-04-25 | 2022-04-27 | 56 | 2022-06-22 | 2022-06-09 | 8766077.2795 | 169270239.1037 |  |  | 8595538.9026 | 3486145.8511 |  |  | 32252330.5602 | 4530497.42 | 4530497.42 | 473333.59
ORA - ZED - ph.02 | 9 | 2022-05-31 | 2022-05-25 | 2022-06-05 | 56 | 2022-07-31 | 2022-08-08 | 8712415.4916 | 177982654.5953 |  |  | 7163536.3546 | 3347808.9149 | 15346414.5805 |  | 32754709.2407 | 4755739.905 | 4755739.905 | 431750.04
ORA - ZED - ph.02 | 10 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 56 | 2022-08-30 | 2022-08-22 | 25761823.8629 | 203744478.4582 |  |  | 20828447.3064 | 2710387.4388 | 19184341.5109 |  | 44374111.2806 | 5416052.245 | 5416052.245 | 481750.04
ORA - ZED - ph.02 | 11 | 2022-07-31 | 2022-07-25 | 2022-08-10 | 56 | 2022-10-05 | 2022-09-14 | 10555360.8465 | 214299839.3048 |  |  | 12170283.1854 | 6960146.9261 | 21459521.0485 |  | 44831361.1808 | 5799374.45 | 5799374.45 | 431750.04
ORA - ZED - ph.02 | 12 | 2022-08-31 | 2022-08-25 | 2022-09-08 | 56 | 2022-11-03 | 2022-10-12 | 16689354.4631 | 230989193.7679 |  |  | 14759398 | 8729597.3 | 23666966.21 |  | 45632622.2463 | 6281714.5 | 6281714.5 | 923489
ORA - ZED - ph.02 | 13 | 2022-09-30 | 2022-09-25 | 2022-10-02 | 56 | 2022-11-27 | 2022-10-22 | 20581919.2571 | 251427139.1048 |  |  | 17432997.712 | 9285019.1626 | 25526704.6029 |  | 54138067.1729 | 6832087.88 | 6832087.88 | 1012532.93
ORA - ZED - ph.02 | 14 | 2022-10-31 | 2022-10-25 | 2022-11-09 | 56 | 2023-01-04 | 2022-12-15 | 19311587.7934 | 270738726.8982 |  |  | 15411600.8685 | 8366501.3369 | 26771100.6571 |  | 60073669.5278 | 7316054.1145 | 7316054.1145 | 862532.9342
ORA - ZED - ph.02 | 15 | 2022-11-30 | 2022-11-25 | 2022-12-05 | 56 | 2023-01-30 | 2022-12-20 | 14179983.4542 | 284918710.3524 |  |  | 11605388.8976 | 8026884.6944 | 27159626.8647 |  | 63560657.3095 | 7679788.26 | 7679788.26 | 758071.44
ORA - ZED - ph.02 | 16 | 2022-12-31 | 2022-12-25 | 2023-01-10 | 56 | 2023-03-07 | 2023-02-05 | 11487525.8247 | 296406236.1771 |  |  | 9858411.1445 | 8322611.144 | 27430483.1297 |  | 65684472.9994 | 7988728.975 | 7988728.975 | 668071.44
ORA - ZED - ph.02 | 17 | 2023-01-31 | 2023-01-25 | 2023-01-28 | 56 | 2023-03-25 | 2023-03-19 | 9516947.0875 | 305923183.2647 |  |  | 8988165.9521 | 9631056.1321 | 28105199.965 |  | 66254957.5517 | 8271259.96 | 8271259.96 | 613266.18
ORA - ZED - ph.02 | 18 | 2023-02-28 | 2023-02-25 | 2023-02-26 | 56 | 2023-04-23 | 2023-04-18 | 15495416.059 | 321418599.3237 |  |  | 13331568.0485 | 10365262.5801 | 28915218.0403 | 400000 | 72791890.9694 | 8696369.795 | 8696369.795 | 323266.18
ORA - ZED - ph.02 | 19 | 2023-03-31 | 2023-03-25 | 2023-04-10 | 56 | 2023-06-05 | 2023-05-01 | 8053943.7501 | 329472543.0738 |  |  | 6921352.2914 | 10413345.9625 | 29296490.0269 | 200000 | 76001927.9044 | 8908987.9 | 8908987.9 | 324695.97
ORA - ZED - ph.02 | 20 | 2023-04-30 | 2023-04-25 | 2023-05-10 | 56 | 2023-07-05 | 2023-06-01 | 4423045.841 | 333895588.9148 |  |  | 3302213.7069 | 10136406.1294 | 30236499.4184 | 350000 | 76323656.7997 | 9018169.36 | 9018169.36 | 324695.97
ORA - ZED - ph.02 | 21 | 2023-05-31 | 2023-05-25 | 2023-06-04 | 56 | 2023-07-30 | 2023-08-14 | 4766150.0757 | 338661738.9905 |  |  | 4532159.65 | 10738897.52 | 27714328.99 | 250000 | 79032701.56 | 9158343.085 | 9158343.085 | 324695.97
ORA - ZED - ph.02 | 22 | 2023-06-30 | 2023-06-25 | 2023-07-12 | 56 | 2023-09-06 | 2023-08-09 | 11000140.3008 | 349661879.2913 |  |  | 8466780.16 | 9962990.1626 | 30646302.9038 | 300000 | 84045575.3164 | 9427699.0855 | 9427699.0855 | 324695.97
ORA - ZED - ph.02 | 23 | 2023-07-31 | 2023-07-25 | 2023-08-09 | 56 | 2023-10-04 | 2023-09-17 | 1051681.4414 | 350713560.7327 |  |  | 564270.13 | 9534609.8107 | 30624495.36 | 270001 | 84127290.1745 | 9444596.21 | 9444596.21 | 324695.97
ORA - ZED - ph.02 | 24 | 2023-08-31 | 2023-08-25 | 2023-09-09 | 56 | 2023-11-04 | 2023-09-17 | 1619984.7524 | 352333545.4851 |  |  | 1374588.34 | 9534609.8107 | 30639873.392 | 240000 | 84127290.1745 | 9487120.81 | 9487120.81 | 324695.97
ORA - ZED - ph.02 | 25 | 2023-09-30 | 2023-09-25 | 2023-10-09 | 56 | 2023-12-04 | 2023-11-07 | 1429470.734 | 353763016.219 |  |  | 996460.71 | 9534609.81 | 30639873.4 | 430000 | 84470961.01 | 9524644.42 | 9524644.42 | 324695.97
ORA - ZED - ph.02 | 26 | 2023-10-31 | 2023-10-25 | 2023-11-07 | 56 | 2024-01-02 | 2023-12-14 | 3475331.4095 | 357238347.6286 |  |  | 2944525.07 | 9534609.81 | 30760806.2 | 370000 | 84664884.26 | 9615871.87 | 9615871.87 | 324695.97
ORA - ZED - ph.02 | 27 | 2023-11-30 | 2023-11-25 | 2023-12-14 | 56 | 2024-02-08 | 2024-01-14 | 3041219.2755 | 360279566.9041 |  |  | 6012429.48 | 9534609.8107 | 31106243.5594 | 430000 | 84803721.0331 | 9695703.875 | 9695703.875 | 324695.97
ORA - ZED - ph.02 | 28 | 2023-12-31 | 2023-12-25 | 2024-01-14 | 56 | 2024-03-10 | 2024-03-03 | 5861894.8952 | 366141461.7993 |  |  | 1674078.17 | 9534609.8107 | 32767206.4615 | 450000 | 88600538.3056 | 9849578.6176 | 9849578.6176 | 324695.97
ORA - ZED - ph.02 | 29 | 2024-01-31 | 2024-01-25 | 2024-02-13 | 56 | 2024-04-09 | 2024-04-15 | 2577878.9747 | 368719340.774 |  |  | 622103 | 7793026.7073 | 32686135.972 | 500000 | 89023126.49 | 9873708.36 | 9873708.36 | 419195.97
ORA - ZED - ph.02 | 30 | 2024-02-29 | 2024-02-25 | 2024-03-07 | 56 | 2024-05-02 | 2024-04-29 | 2066668.4069 | 370786009.181 |  |  | 73017 | 6499733.7 | 32340261.62 | 1120000 | 89409590.24 | 9895626.085 | 9895626.085 | 419195.97
ORA - ZED - ph.02 | 31 | 2024-03-31 | 2024-03-25 | 2024-04-07 | 56 | 2024-06-02 | 2024-05-15 | 7992050.6095 | 378778059.7905 |  |  | 3717995 | 3482050.01 | 39683396.61 | 1650000 | 88674483.32 | 10029975.32 | 10029975.32 | 419195.97
ORA - ZED - ph.02 | 32 | 2024-04-30 | 2024-04-25 | 2024-05-07 | 56 | 2024-07-02 | 2024-06-05 | 2766734.981 | 381544794.7714 |  |  | 2943652.2 | 3482050.01 | 39914992.15 | 1110000 | 89539810.97 | 10102602.115 | 10102602.115 | 419195.97
ORA - ZED - ph.02 | 33 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 56 | 2024-07-31 | 2024-07-01 | 6575447.0667 | 388120241.8381 |  |  | 1631186.62 | 3482050.01 | 40131194.96 | 2270000 | 90446780.46 | 10188156.35 | 10188156.35 | 419195.97
ORA - ZED - ph.02 | 34 | 2024-06-30 | 2024-06-25 | 2024-07-06 | 56 | 2024-08-31 | 2024-08-06 | 1412666.8095 | 389532908.6476 |  |  | 3368948.46 | 3482050.01 | 40483731.09 | 2740000 | 92888843.55 | 10312290.1 | 10312290.1 | 419195.97
ORA - ZED - ph.02 | 35 | 2024-07-31 | 2024-07-25 | 2024-08-07 | 56 | 2024-10-02 | 2024-08-31 | 7262978.339 | 396795886.9866 |  |  | 6454315.65 | 3482050.0134 | 42071751.0265 | 2400000 | 94659153.4844 | 10502943.2837 | 10502943.2837 | 419195.97
ORA - ZED - ph.02 | 36 | 2024-08-31 | 2024-08-15 | 2024-09-01 | 56 | 2024-10-27 | 2024-09-05 | 0.003893 | 396795886.9905 |  |  | 6578211.32 | 11803883.61 | 42071751.03 | 2400000 | 94659153.49 | 10710989.125 | 10710989.125 | 419195.97
ORA - ZED - ph.02 | 37 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 56 | 2024-10-31 | 2024-10-07 | 12000518.9238 | 408796405.9143 |  |  | 9153293.69 | 10593047.63 | 43987735.96 | 2250000 | 101066779.38 | 10995731.845 | 10995731.845 | 419195.97
ORA - ZED - ph.02 | 38 | 2024-09-30 | 2024-09-16 | 2024-10-07 | 56 | 2024-12-02 | 2024-10-07 | -0.0095238 | 408796405.9048 |  |  | 3851310.01 | 15718197.44 | 43987735.96 | 2450000 | 101066779.38 | 11123860.59 | 11123860.59 | 419195.97
ORA - ZED - ph.02 | 39 | 2024-09-30 | 2024-09-25 | 2024-10-07 | 56 | 2024-12-02 | 2024-11-09 | 13783192.8762 | 422579598.781 |  |  | 14526906.83 | 19699160.8 | 49807541.52 | 2510000 | 103795295.53 | 11585193.49 | 11585193.49 | 419195.97
ORA - ZED - ph.02 | 40 | 2024-10-30 | 2024-10-25 | 2024-11-09 | 56 | 2025-01-04 | [12 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 1 | 2019-11-30 | 2019-12-05 | 2019-12-07 | 7 | 2019-12-14 | 2019-12-11 | 1222080 | 1222080 |  |  | 2841415.8 | 2056962.6 | [5 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 2 | 2019-12-31 | 2020-01-02 | 2020-01-02 | 7 | 2020-01-09 | 2020-01-11 | 19989408.99 | 21211488.99 |  |  | 13446882.5 | 2672643.6 | [5 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 3 | 2020-01-31 | 2020-01-30 | 2020-01-30 | 7 | 2020-02-06 | 2020-02-05 | 22171564.66 | 43383053.65 |  |  | 17089175.5 | 5401152.9 | [5 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 4 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 7 | 2020-03-14 | 2020-03-16 | 17471458.95 | 60854512.6 |  |  | 14773850.7 | 8960074.2 | [5 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 5 | 2020-03-31 | 2020-03-15 | 2020-03-26 | 7 | 2020-04-02 | 2020-04-09 | 7891719.6 | 68746232.2 |  |  | 2392694.9 | 6287074.2 | [5 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 6 | 2020-04-30 | 2020-04-15 | 2020-04-26 | 7 | 2020-05-03 | 2020-05-06 | 18379179.4 | 87125411.6 |  |  | 7788095.2 | 2277574.2 | [5 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 7 | 2020-05-31 | 2020-05-31 | 2020-06-08 | 7 | 2020-06-15 | 2020-07-11 | 9076073.5 | 96201485.1 |  |  | 3548357.4 | 0 | [5 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 8 | 2020-06-30 | 2020-06-30 | 2020-07-07 | 7 | 2020-07-14 | 2020-07-09 | 2504382.4 | 98705867.5 |  |  | 1607563.1 | [6 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 9 | 2020-07-31 | 2020-08-15 | 2020-08-17 | 7 | 2020-08-24 | 2020-08-27 | 9452002.7 | 108157870.2 |  |  | 8526565.2 | [6 empty] | 0
PH.2-El Sewedy Uni. - Enabling | 10 | 2020-11-30 | 2020-11-15 | 2020-11-22 | 7 | 2020-11-29 | 2020-11-22 | 5068271.5 | 113226141.7 |  |  | 7703511.3 | [6 empty] | 118504
PH.2-El Sewedy Uni. - Finishes | 1 | 2020-02-29 | 2020-02-29 | 2020-03-07 | 14 | 2020-03-21 | 2020-03-22 | 39552087.9 | 39552087.9 |  | 15000000 | 35636298.9 | 27835856 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 2 | 2020-03-31 | 2020-03-31 | 2020-04-05 | 14 | 2020-04-19 | 2020-04-22 | 33281363.92 | 72833451.82 |  |  | 26758389.8 | 40761852.6 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 3 | 2020-04-30 | 2020-04-30 | 2020-05-06 | 14 | 2020-05-20 | 2020-05-19 | 24169965.9076 | 97003417.7276 |  |  | 23262698.8 | 51226946.1 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 4 | 2020-05-31 | 2020-05-31 | 2020-06-14 | 14 | 2020-06-28 | 2020-06-18 | 24591514.8424 | 121594932.57 |  |  | 18322601 | 51695436 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 5 | 2020-06-30 | 2020-06-30 | 2020-07-08 | 14 | 2020-07-22 | 2020-07-13 | 77007398.3 | 198602330.87 |  |  | 64006362.8 | 81242431.4 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 6 | 2020-07-31 | 2020-07-15 | 2020-07-27 | 14 | 2020-08-10 | 2020-07-29 | 22875033.55 | 221477364.42 |  |  | 8883254.2 | 71736256.5 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 7 | 2020-08-31 | 2020-08-15 | 2020-08-17 | 14 | 2020-08-31 | 2020-08-26 | 54216090.64 | 275693455.06 |  |  | 30755604.9 | 65901640.4 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 8 | 2020-08-31 | 2020-08-31 | 2020-09-10 | 14 | 2020-09-24 | 2020-09-17 | 61814968.03 | 337508423.09 |  |  | 30127325.7 | 51289431.9 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 9 | 2020-09-30 | 2020-09-15 | 2020-10-18 | 14 | 2020-11-01 | 2020-10-20 | 56169721.37 | 393678144.46 |  |  | 20493846 | 22011525 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 10 | 2020-10-31 | 2020-10-25 | 2020-11-10 | 14 | 2020-11-24 | 2020-11-19 | 33204826.41 | 426882970.87 |  |  | 9765894.8 | 8412160.7 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 11 | 2020-11-30 | 2020-12-01 | 2020-12-15 | 14 | 2020-12-29 | 2020-12-21 | 20698550.4 | 447581521.27 |  |  | 13851401.2 | 6756406.26 | [5 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 12 | 2021-01-31 | 2021-02-10 | 2021-02-14 | 14 | 2021-02-28 | 2021-03-22 | 33191485.02 | 480773006.29 |  |  | 23340124.9 | [6 empty] | 0
PH.2-El Sewedy Uni. - Finishes | 13 | 2021-05-31 | 2021-06-09 | 2022-03-28 | 14 | 2022-04-11 | 2022-04-27 | 13891238 | 494664244.29 |  |  | 19693398.5 |  |  |  |  | 12984936.4125 | 12984936.4125 | 0
PI Parks - ELSEWEDY | 1 | 2017-09-30 | 2017-10-03 | 2017-10-18 | 15 | 2017-11-16 | 2017-11-04 | 2947938.09 | 2947938.09 |  |  | 3779007.23 | 2165254 | [5 empty] | 350000
PI Parks - ELSEWEDY | 2 | 2017-10-31 | 2017-11-04 | 2017-11-06 | 15 | 2017-12-09 | 2017-11-28 | 4598153.29 | 7546090.84 |  |  | 3366014.15 | 1128937.5 | [5 empty] | 360362.87
PI Parks - ELSEWEDY | 3 | 2017-11-30 | 2017-12-04 | 2017-12-04 | 15 | 2018-01-09 | 2017-12-25 | 1603218.21 | 9149309.06 |  |  | 823701.84 | 1055385.4 | [5 empty] | 360362.87
PI Parks - ELSEWEDY | 4 | 2017-12-31 | 2017-12-31 | 2018-01-04 | 15 | 2018-02-17 | 2018-02-15 |  | 12280064.67 |  |  | 2572231.81 | 862309.875 | [5 empty] | 711378.1905
PI Parks - ELSEWEDY | 5 | 2018-01-31 | 2018-02-07 | 2018-02-07 | 15 | 2018-03-28 | 2018-04-05 | 2043145.23 | 14323209.9 |  |  | 1175600.49 | 439890.2 | [5 empty] | 110286.54
PI Parks - ELSEWEDY | 6 | 2018-02-28 | 2018-03-10 | 2018-03-11 | 15 | 2018-04-28 | 2018-04-15 | 662608.11 | 14985818.01 |  |  | 689113.69 | 602282.21 | [5 empty] | 0
PI Parks - ELSEWEDY | 7 | 2018-03-31 | 2018-04-10 | 2018-04-16 | 15 | 2018-05-08 | 2018-04-21 | 667972.21 | 15685820.74 |  |  | 1938615.93 | 1491568.3 | [5 empty] | 0
PI Parks - ELSEWEDY | 8 | 2018-04-30 | 2018-05-09 | 2018-05-09 | 15 | 2018-06-03 | 2018-06-02 | 1859636.86 | 17545457.6 |  |  | 1633991.6379 | 1274527.689 | [5 empty] | 0
PI Parks - ELSEWEDY | 9 | 2018-05-31 | 2018-06-09 | 2018-06-09 | 15 | 2018-06-29 | 2018-06-12 | 1491159.5592 | 19036617.1592 |  |  | 1607545.8276 | 1586317.356 | [5 empty] | 0
PI Parks - ELSEWEDY | 10 | 2018-06-30 | 2018-07-08 | 2018-07-10 | 15 | 2018-08-08 | 2018-08-01 | 3200065.7108 | 22236682.87 |  |  | 2470019.34 | 1486479.93 | [5 empty] | 115532.14
PI Parks - ELSEWEDY | 11 | 2018-07-31 | 2018-08-02 | 2018-08-07 | 15 | 2018-08-25 | 2018-09-13 | 890276.26 | 23126959.13 |  |  | 945860.23 | 1734570.528 | [5 empty] | 125532.14
PI Parks - ELSEWEDY | 12 | 2018-08-31 | 2018-09-06 | 2018-09-08 | 15 | 2018-10-13 | 2018-09-26 | 1804540.7798 | 24932718.8264 |  |  | 1530660.1341 | 1713142.271 | [5 empty] | 0
PI Parks - ELSEWEDY | 13 | 2018-09-30 | 2018-10-04 | 2018-10-04 | 15 | 2018-10-27 | 2018-10-10 | 1076504.1197 | 26009222.9461 |  |  | 716605.5327 | 1579309.545 | [5 empty] | 0
PI Parks - ELSEWEDY | 14 | 2018-10-31 | 2018-11-05 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 1188716.2339 | 27197939.18 |  |  | 775351.46 | 1430574.85 | [5 empty] | 194651.72
PI Parks - ELSEWEDY | 15 | 2018-11-30 | 2018-12-06 | 2018-12-06 | 15 | 2019-01-01 | 2018-12-26 | 6486957.62 | 33684896.8 |  |  | 4484634.17 | 1125214.43 | [5 empty] | 209651.72
PI Parks - ELSEWEDY | 16 | 2018-12-31 | 2019-01-06 | 2019-01-06 | 15 | 2019-01-31 | 2019-01-27 | 4932880.46 | 38617777.26 |  |  | 4125986.43 | 889716.88 | [5 empty] | 245586.01
PI Parks - ELSEWEDY | 17 | 2019-01-31 | 2019-02-05 | 2019-02-07 | 15 | 2019-03-05 | 2019-03-13 | 1718123.55 | 40335900.81 |  |  | 1375431.38 | 584649.66 | [5 empty] | 261703.2
PI Parks - ELSEWEDY | 18 | 2019-02-28 | 2019-03-05 | 2019-03-06 | 15 | 2019-04-03 | 2019-03-27 | 4308748.67 | 44644649.48 |  |  | 3699864.67 | 439815.151 | [5 empty] | 261703.2
PI Parks - ELSEWEDY | 19 | 2019-03-31 | 2019-04-06 | 2019-04-06 | 15 | 2019-05-04 | 2019-05-14 | 2652468.02 | 47297117.5 |  |  | 2311261.81 | 171933.6095 | [5 empty] | 276703.2
PI Parks - ELSEWEDY | 20 | 2019-04-30 | 2019-05-05 | 2019-05-07 | 15 | 2019-06-05 | 2019-05-19 | 4018450.9279 | 51315568.4279 |  |  | 1816746.614 | 161583.8345 | [5 empty] | 0
PI Parks - ELSEWEDY | 21 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 598299.7921 | 51913868.22 |  |  | 5879272.6391 | 179052.64 | [5 empty] | 0
PI Parks - MEP | 1 | 2018-09-30 | 2018-10-04 | 2018-09-27 | 15 | 2018-10-27 | 2018-10-10 | 4100153.37 | 4100153.37 |  |  | 7818631.64 | 4989525.8132 | [5 empty] | 0
PI Parks - MEP | 2 | 2018-10-31 | 2018-11-02 | 2018-11-07 | 15 | 2018-12-02 | 2018-12-02 | 3824663.6 | 7924816.97 |  |  | 3907009.94 | 5871509.91 | [5 empty] | 0
PI Parks - MEP | 3 | 2018-11-30 | 2018-12-10 | 2018-12-03 | 15 | 2019-01-01 | 2018-12-26 | 2526634.86 | 10451451.83 |  |  | 3921714.73 | 8435854.55 | [5 empty] | 0
PI Parks - MEP | 4 | 2018-12-31 | 2019-01-05 | 2019-01-05 | 15 | 2019-01-31 | 2019-01-14 | 13292686.78 | 23744138.61 |  |  | 3514249.7617 | 6341086.69 | [5 empty] | 0
PI Parks - MEP | 5 | 2019-01-31 | 2019-02-05 | 2019-02-05 | 15 | 2019-03-05 | 2019-03-13 | 8084326 | 31828464.61 |  |  | 6350059.5 | 8184608.01 | [5 empty] | 0
PI Parks - MEP | 6 | 2019-02-28 | 2019-03-05 | 2019-03-05 | 15 | 2019-04-03 | 2019-03-26 | 3232894.78 | 35061359.39 |  |  | 919139.23 | 6744285.61 | [5 empty] | 0
PI Parks - MEP | 7 | 2019-03-31 | 2019-04-01 | 2019-04-04 | 15 | 2019-05-04 | 2019-05-14 | 4908164.7341 | 39969524.1241 |  |  | 2661364.08 | 4404706.2941 | [5 empty] | 0
PI Parks - MEP | 8 | 2019-04-30 | 2019-05-05 | 2019-05-06 | 15 | 2019-06-05 | 2019-05-19 | 2655162.8183 | 42624686.9424 |  |  | 1686090.7908 | 3262993.985 | [5 empty] | 0
PI Parks - MEP | 9 | 2019-06-30 | 2019-06-30 | 2019-10-10 | 15 | 2019-10-30 | 2019-10-13 | 3596767.6976 | 46221454.64 |  |  | 5081340.66 | 42070.75 | [5 empty] | 0
PK #107 | 8 | 2017-09-30 | 2017-09-28 | 2017-09-28 | 30 | 2017-10-28 | 2017-10-15 |  | 36182581.41 |  |  | 3005745.85 | 1713544.64 | [5 empty] | 238645.64
PK #107 | 9 | 2017-10-31 | 2017-10-31 | 2017-11-01 | 30 | 2017-12-01 | 2017-11-28 | 1856322.11 | 38038903.52 |  |  | 1418090.5 | 1713544.64 | [5 empty] | 253179.82
PK #107 | 10 | 2017-11-30 | 2017-11-28 | 2017-11-28 | 30 | 2017-12-28 | 2017-12-27 | 2025124.41 | 40064027.93 |  |  | 1453205.39 | 1875947.9 | [5 empty] | 264974.51
PK #107 | 11 | 2017-12-31 | 2017-12-25 | 2017-12-27 | 30 | 2018-01-26 | 2018-01-15 | 3591068.23 | 43655096.16 |  |  | 2604921.36 | 1188936.54 | [5 empty] | 282897.2
PK #107 | 12 | 2018-01-31 | 2018-01-25 | 2018-01-25 | 30 | 2018-02-24 | 2018-02-26 | 5883258.75 | 49538354.91 |  |  | 5012769.61 | 366842.14 | [5 empty] | 315029.17
PK #107 | 13 | 2018-02-28 | 2018-03-10 | 2018-03-12 | 30 | 2018-04-11 | 2018-04-04 | 2719252.37 | 52257607.28 |  |  | 2462800.95 | 323504.14 | [5 empty] | 369537.93
PK #107 | 14 | 2018-03-31 | 2018-04-10 | 2018-04-11 | 30 | 2018-05-11 | 2018-04-29 | 1449945.81 | 53707553.09 |  |  | 166316.41 | 0 | [5 empty] | 1275350.71
PK #107 | 15 | 2018-04-30 | 2018-05-05 | 2018-05-06 | 30 | 2018-06-05 | 2018-05-23 | 0 | 53707553.09 |  |  | 1406606.27 | 0 | [5 empty] | 1275350.71
PK #107 | 16 | 2018-05-31 | 2018-06-01 | 2018-05-30 | 30 | 2018-06-29 | 2018-06-28 | 0.01 | 53707553.1 |  |  | 131256.74 | 0 | [5 empty] | 1292122.78
PK #107 | 17 | 2018-09-30 | 2018-09-25 | 2018-09-25 | 30 | 2018-10-25 | 2018-10-21 | 0 | 53707553.1 |  |  | 763627.7 | 0 | [5 empty] | 496495.08
PK #107 | 18 | 2019-04-30 | 2019-04-25 | 2019-06-13 | 30 | 2019-07-13 | 2019-07-30 | 989048.54 | 54696601.64 |  |  | 940988.93 | [6 empty] | 1898258.43
PK #117 | 1 | 2017-12-31 | 2018-01-01 | 2018-01-18 | 30 | 2018-02-17 | 2018-02-13 | 4130129.14 | 4130129.14 |  |  | 4130129.14 | [6 empty] | 0
PK #117 | 2 | 2018-01-31 | 2018-02-15 | 2018-02-15 | 30 | 2018-03-17 | 2018-03-07 | 7803090.39 | 7803090.39 |  |  | 6455421.01 | 0 | [5 empty] | 60159.47
PK #117 | 3 | 2018-02-28 | 2018-03-05 | 2018-03-07 | 30 | 2018-04-06 | 2018-03-29 | 4332593.51 | 12135683.86 |  |  | 4502026.52 | 1176749.78 | [5 empty] | 106021.19
PK #117 | 4 | 2018-03-31 | 2018-04-01 | 2018-04-01 | 30 | 2018-05-01 | 2018-04-19 | 4131277.1774 | 16266961.0374 |  |  | 3740180.271 | 1578005.405 | [5 empty] | 134455.7716
PK #117 | 5 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 30 | 2018-05-30 | 2018-05-22 | 6909334.9826 | 23176296.02 |  |  | 4762507.55 | 364792.48 | [5 empty] | 171850.1
PK #117 | 6 | 2018-05-31 | 2018-06-04 | 2018-06-05 | 30 | 2018-07-05 | 2018-07-12 | 6677875.24 | 29854171.26 |  |  | 5347404.79 | 229256.92 | [5 empty] | 302952.2979
PK #117 | 7 | 2018-06-30 | 2018-06-15 | 2018-06-25 | 30 | 2018-07-25 | 2018-12-30 | -0.01 | 29854171.25 |  |  | 119713.18 | 384118.8 | [5 empty] | 115837.505
PK #117 | 8 | 2018-11-30 | 2018-12-05 | 2018-12-05 | 30 | 2019-01-04 | 2018-12-30 | 4511257.49 | 34365428.74 |  |  | 3896343.98 | 79445.62 | [5 empty] | 575019.525
PK #117 | 9 | 2018-12-31 | 2018-12-30 | 2018-12-29 | 30 | 2019-01-28 | 2019-01-30 | 3153415.09 | 37518843.83 |  |  | 2578109.66 | 48842.25 | [5 empty] | 599014.4
PK #117 | 10 | 2019-01-31 | 2019-01-31 | 2019-02-02 | 30 | 2019-03-04 | 2019-02-28 | 1068867.24 | 38587711.07 |  |  | 882296.18 | 48842.25 | [5 empty] | 653139.594
PK #117 | 11 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-30 | 1134851.86 | 39722562.93 |  |  | 810342.08 | [6 empty] | 737679.72
PK #117 | 12 | 2019-08-31 | 2019-08-26 | 2019-08-26 | 30 | 2019-09-25 | 2019-09-25 | 2921413.42 | 42643976.35 |  |  | 3376348.1 | 0 | [5 empty] | 1681581.22
PK #117 | 13 | 2019-10-31 | 2019-10-30 | 2019-10-29 | 30 | 2019-11-28 | 2019-11-12 | 2611652.87 | 45255629.22 |  |  | 3145779.21 | 0 | [5 empty] | 975332.15
PK #117 | 14 | 2020-04-30 | 2020-04-14 | 2020-06-24 | 30 | 2020-07-24 | 2020-09-27 | 1659370.81 | 46915000.03 |  |  | 2238761.46 | [6 empty] | 943850.91
PK#22 | 37 | 2019-02-28 | 2019-02-27 | 2019-07-31 | 30 | 2019-08-30 | 2019-08-07 |  | 35147992.22 |  |  | 471641.26 | [6 empty] | 990333.95
PK#32 | 30 | 2017-06-30 | 2017-06-05 | 2022-03-14 | 30 | 2022-04-13 | [12 empty] | 0
PKG#101 | 1 | 2019-01-31 | 2019-01-31 | 2019-02-03 | 40 | 2019-03-15 | 2019-02-17 | 1738465.6667 | 1738465.6667 | 8723141 |  | 1029594.82 | [6 empty] | 48253.89
PKG#101 | 2 | 2019-02-28 | 2019-02-28 | 2019-03-05 | 40 | 2019-04-14 | 2019-03-19 | 1610908.8476 | 3349374.5143 |  |  | 2222206.65 | 2240156.84 | [5 empty] | 147570
PKG#101 | 3 | 2019-03-31 | 2019-04-11 | 2019-04-14 | 40 | 2019-05-24 | 2019-05-05 | 4030400.2476 | 7379774.7619 |  |  | 2246109.51 | 1904790.84 | [5 empty] | 202283
PKG#101 | 4 | 2019-04-30 | 2019-05-15 | 2019-05-20 | 40 | 2019-06-29 | 2019-05-29 | 4428897.7238 | 11808672.4857 |  |  | 2512749.68 | 1592100.01 | [5 empty] | 250813.43
PKG#101 | 5 | 2019-06-30 | 2019-06-30 | 2019-07-01 | 40 | 2019-08-10 | 2019-07-24 | 2224631.7143 | 14033304.2 |  |  | 2051541.96 | 2808836.8 | [5 empty] | 296997.23
PKG#101 | 6 | 2019-07-31 | 2019-08-05 | 2019-08-07 | 40 | 2019-09-16 | 2019-08-28 | 3491880.8381 | 17525185.0381 |  |  | 1988552.05 | 2620517.54 | [5 empty] | 362213.26
PKG#101 | 7 | 2019-08-31 | 2019-09-10 | 2019-09-15 | 40 | 2019-10-25 | 2019-09-26 | 3123640.9905 | 20648826.0286 |  |  | 1824097.57 | 2373278.98 | [5 empty] | 374469.49
PKG#101 | 8 | 2019-09-30 | 2019-10-15 | 2019-10-17 | 40 | 2019-11-26 | 2019-11-05 | 4704887.4039 | 25353713.4325 |  |  | 2104893.8329 | 1078135.3004 | [5 empty] | 421854.3373
PKG#101 | 9 | 2019-10-31 | 2019-11-15 | 2019-11-17 | 40 | 2019-12-27 | 2019-12-03 | 3179849.8818 | 28533563.3143 |  |  | 1424816.56 | 297444.34 | [5 empty] | 505055.04
PKG#101 | 10 | 2019-11-30 | 2019-11-15 | 2019-12-18 | 40 | 2020-01-27 | 2020-01-06 | 3100706.8857 | 31634270.2 |  |  | 1976416.89 | [6 empty] | 515167.31
PKG#101 | 11 | 2020-01-31 | 2020-01-30 | 2020-02-08 | 40 | 2020-03-19 | 2020-02-27 | 361420.4 | 31995690.6 |  |  | 1709961.04 | 2008107.01 | [5 empty] | 646968.58
PKG#101 | 12 | 2020-02-29 | 2020-03-23 | 2020-03-24 | 40 | 2020-05-03 | 2020-04-08 | 2584477.6667 | 34580168.2667 |  |  | 1146998.22 | 1288346.31 | [5 empty] | 677344.97
PKG#101 | 13 | 2020-03-31 | 2020-04-23 | 2020-04-23 | 40 | 2020-06-02 | 2020-05-04 | 2595711.6476 | 37175879.9143 |  |  | 1407211.96 | 1005027.63 | [5 empty] | 712181.29
PKG#101 | 14 | 2020-06-30 | 2020-06-30 | 2020-07-12 | 40 | 2020-08-21 | 2020-09-09 | 4659441.8571 | 41835321.7714 |  |  | 191421.72 | [6 empty] | 763224.31
PKG#101 | 15 | 2020-09-30 | 2020-08-12 | 2020-12-09 | 40 | 2021-01-18 | 2021-01-20 | 181866.4762 | 42017188.2476 |  |  | 303853.8 | [6 empty] | 174031.17
PKG#101 | 16 | 2020-09-30 | 2020-09-30 | 2021-02-07 | 40 | 2021-03-19 | 2021-02-15 | 0.001 | 42017188.2476 |  |  | 866491.01 | [6 empty] | 0
PKG#101 | 17 | 2021-03-31 | 2021-04-05 | 2021-04-13 | 40 | 2021-05-23 | 2021-04-26 | 0.001 | 42017188.2476 |  |  | 3321316.23 | [6 empty] | 270662.92
PKG#101 | 18 | 2021-04-30 | 2021-04-05 | 2021-04-25 | 40 | 2021-06-04 | 2021-05-05 | 1071378.1714 | 43088566.419 |  |  | 1192690.23 | 949450.54 | [5 empty] | 275887.92
PKG#101 | 19 | 2021-04-30 | 2021-05-05 | 2021-05-17 | 40 | 2021-06-26 | 2021-06-03 | 1322361.8352 | 44410928.2543 |  |  | 596242.89 | 615651.133 | [5 empty] | 288697.92
PKG#101 | 20 | 2021-05-31 | 2021-06-05 | 2021-06-10 | 40 | 2021-07-20 | 2021-06-27 | 952923.8886 | 45363852.1429 |  |  | 759353.31 | 505736.36 | [5 empty] | 238697.92
PKG#101 | 21 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 40 | 2021-08-20 | 2021-08-09 | 2547253.7048 | 47911105.8476 |  |  | 1584188.57 | 618555.37 | [5 empty] | 264186.92
PKG#101 | 22 | 2021-08-31 | 2021-08-15 | 2021-09-20 | 40 | 2021-10-30 | 2021-10-12 | 2544618.2857 | 50455724.1333 |  |  | 594122.92 | 0 | [5 empty] | 299725.92
PKG#101 | 23 | 2022-04-30 | 2022-04-10 | 2022-04-21 | 40 | 2022-05-31 | [12 empty] | 0
PKG#101 | 24 | 2022-04-30 | 2022-04-10 | 2023-03-27 | 40 | 2023-05-06 | [12 empty] | 0
PKG#144 | 2 | 2018-12-31 | 2018-12-26 | 2018-12-26 | 30 | 2019-01-25 | 2019-01-20 | 4125990.87 | 4125990.87 |  |  | 2532120.6 | [6 empty] | 25993.74
PKG#144 | 3 | 2019-01-31 | 2019-01-30 | 2019-01-31 | 30 | 2019-03-02 | 2019-02-20 | 6872046.13 | 10998037 |  |  | 6190737.99 | 3387217.5 | [5 empty] | 95995.9412
PKG#144 | 4 | 2019-02-28 | 2019-02-27 | 2019-02-27 | 30 | 2019-03-29 | 2019-03-11 | 11224614.67 | 22222651.67 |  |  | 6888545.72 | 3387217.5 | [5 empty] | 166711.01
PKG#144 | 5 | 2019-02-28 | 2019-03-11 | 2019-03-11 | 30 | 2019-04-10 | 2019-03-11 | 0 | 22222651.67 |  |  | 7206339.73 | 3387217.5 | [5 empty] | 166711.64
PKG#144 | 6 | 2019-03-31 | 2019-03-14 | 2019-03-14 | 30 | 2019-04-13 | 2019-03-21 | 24444079.39 | 46666731.06 |  |  | 14801921.82 | 3262056.75 | [5 empty] | 319957.75
PKG#144 | 7 | 2019-03-31 | 2019-03-30 | 2019-03-30 | 30 | 2019-04-29 | 2019-04-11 | 20465525.6228 | 67132256.6828 |  |  | 12603636.3289 | 3501000 | [5 empty] | 672293.8257
PKG#144 | 8 | 2019-04-30 | 2019-04-15 | 2019-04-15 | 30 | 2019-05-15 | 2019-05-04 | 16379645.0372 | 83511901.72 |  |  | 8909777.64 | 0 | [5 empty] | 795592.47
PKG#144 | 9 | 2019-04-30 | 2019-04-30 | 2019-05-05 | 30 | 2019-06-04 | 2019-05-15 | 10281327.2057 | 93793228.9257 |  |  | 9777923.5506 | 816900 | [5 empty] | 900089.7717
PKG#144 | 10 | 2019-05-31 | 2019-05-20 | 2019-05-20 | 30 | 2019-06-19 | 2019-05-30 | 13881511.5343 | 107674740.46 |  |  | 11184527.72 | [6 empty] | 1113537.73
PKG#144 | 11 | 2019-06-30 | 2019-06-20 | 2019-06-18 | 30 | 2019-07-18 | 2019-07-11 | 9087190.46 | 116761930.92 |  |  | 7486833.97 | 0 | [5 empty] | 1199420.77
PKG#144 | 12 | 2019-08-31 | 2019-09-05 | 2019-09-04 | 30 | 2019-10-04 | 2019-10-03 | 34717376.42 | 151479307.34 |  |  | 22411649.36 | [6 empty] | 8633180.89
PKG#144 | 13 | 2019-12-31 | 2019-12-25 | 2019-12-25 | 30 | 2020-01-24 | 2020-01-22 | 11410387.23 | 162889694.57 |  |  | 14635108.89 | [6 empty] | 9246101.93
PKG#144 | 14 | 2020-01-31 | 2020-02-03 | 2020-02-03 | 30 | 2020-03-04 | 2020-02-19 | 10733689.1131 | 173623383.6831 |  |  | 10377806.9192 | [6 empty] | 8262612.0833
PKG#144 | 15 | 2020-08-31 | 2020-08-20 | 2020-12-13 | 30 | 2021-01-12 | 2020-12-13 | 2638692.2969 | 176262075.98 |  |  | 10405304.53 | [6 empty] | 2614017.44
PKG#144 | 16 | 2021-01-31 | 2021-01-20 | 2021-01-21 | 30 | 2021-02-20 | 2021-03-25 | 150533.34 | 176412609.32 |  |  | 1132971.99 | [6 empty] | 2496617.44
PKG#162 | 2 | 2020-02-29 | 2020-02-29 | 2020-03-05 | 40 | 2020-04-14 | 2020-03-22 | 8785941.99 | 8785941.99 |  |  | 7794726.52 | 749579.79 | [5 empty] | 0
PKG#162 | 3 | 2020-03-31 | 2020-03-18 | 2020-03-21 | 40 | 2020-04-30 | 2020-03-30 | 6446622.36 | 15232564.35 |  |  | 5119599.35 | 531683.98 | [5 empty] | 0
PKG#162 | 4 | 2020-03-31 | 2020-04-06 | 2020-04-06 | 40 | 2020-05-16 | 2020-04-22 | 7314177.64 | 22546741.99 |  |  | 6336538.23 | 1033463.45 | [5 empty] | 57000
PKG#162 | 5 | 2020-04-30 | 2020-05-05 | 2020-05-04 | 40 | 2020-06-13 | 2020-05-13 | 8006098.57 | 30552840.56 |  |  | 6124877.69 | 592328.38 | [5 empty] | 157000
PKG#162 | 6 | 2020-05-31 | 2020-06-06 | 2020-06-10 | 40 | 2020-07-20 | 2020-06-26 | 5990865.4963 | 36543706.0563 |  |  | 4824045.381 | 474838.875 | [5 empty] | 157000
PKG#162 | 7 | 2020-06-30 | 2020-07-06 | 2020-07-06 | 40 | 2020-08-15 | 2020-07-29 | 8577628.8704 | 45121334.9266 |  |  | 7215874.2121 | 834531.375 | [5 empty] | 260419
PKG#162 | 8 | 2020-07-31 | 2020-08-10 | 2020-08-16 | 40 | 2020-09-25 | 2020-09-03 | 12161063.3859 | 57282398.3125 |  |  | 9432027.7177 | 136265.25 | [5 empty] | 261806
PKG#162 | 9 | 2020-08-31 | 2020-09-05 | 2020-09-09 | 40 | 2020-10-19 | 2020-09-28 | 10973106.5017 | 68255504.8142 |  |  | 9889305.1266 | 1100385 | [5 empty] | 61806
PKG#162 | 10 | 2020-09-30 | 2020-10-05 | 2020-10-07 | 40 | 2020-11-16 | 2020-11-03 | 14493217.0374 | 82748721.8517 |  |  | 13282474.2108 | 1005156.4395 | [5 empty] | 61806
PKG#162 | 11 | 2020-10-31 | 2020-11-05 | 2020-11-05 | 40 | 2020-12-15 | 2020-12-02 | 9303551.5202 | 92052273.3719 |  |  | 7840185.4913 | [6 empty] | 93807
PKG#162 | 12 | 2020-11-30 | 2020-12-01 | 2020-12-13 | 40 | 2021-01-22 | 2021-02-02 | 7499598.7681 | 99551872.14 |  |  | 4608392 | 0 | [5 empty] | 2426668.64
PKG#162 | 13 | 2020-12-31 | 2021-01-01 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-09 | 709528.8141 | 100261400.9541 |  |  | 3429815.246 | [6 empty] | 2376668.64
PKG#162 | 14 | 2021-01-31 | 2021-02-01 | 2021-02-03 | 40 | 2021-03-15 | 2021-02-24 | -0.004055 | 100261400.95 |  |  | 502581.44 | [6 empty] | 1926668.64
PKG#162 | 15 | 2021-01-31 | 2021-02-01 | 2021-11-18 | 40 | 2021-12-28 | 2022-03-07 | 0.05 | 100261401 |  |  | 3683579.28 | [6 empty] | 926668
PKG#163 | 2 | 2020-06-30 | 2020-07-07 | 2020-07-07 | 40 | 2020-08-16 | 2020-07-22 | 167514.17 | 167514.17 |  |  | 1068966.43 | 1392714.35 | [5 empty] | 0
PKG#163 | 3 | 2020-07-31 | 2020-08-10 | 2020-08-18 | 40 | 2020-09-27 | 2020-08-26 | 1873525.03 | 2041039.2 |  |  | 2977091.11 | 3794104.59 | [5 empty] | 0
PKG#163 | 4 | 2020-08-31 | 2020-09-03 | 2020-09-03 | 40 | 2020-10-13 | 2020-09-23 | 3480646.03 | 5521685.23 |  |  | 6845695.77 | 10183594.03 | [5 empty] | 0
PKG#163 | 5 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 40 | 2020-11-09 | 2020-10-22 | 3896848.6915 | 9418533.9215 |  |  | 3782501.2803 | 11640240.8375 | [5 empty] | 0
PKG#163 | 6 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 40 | 2020-12-13 | 2020-11-29 | 8635132.0099 | 18053665.9314 |  |  | 6255172.4375 | 11614831.0892 | [5 empty] | 0
PKG#163 | 7 | 2020-11-30 | 2020-12-07 | 2020-12-08 | 40 | 2021-01-17 | 2020-12-23 | 4420616.8286 | 22474282.76 |  |  | 4922193.5 | 14196023.04 | [5 empty] | 0
PKG#163 | 8 | 2020-12-31 | 2021-01-05 | 2021-01-05 | 40 | 2021-02-14 | 2021-02-02 | 7415396.32 | 29889679.08 |  |  | 6050639.7742 | 15239713.55 | [5 empty] | 0
PKG#163 | 9 | 2021-01-31 | 2021-01-25 | 2021-02-25 | 40 | 2021-04-06 | 2021-03-08 | 5020188.6174 | 34909867.6974 |  |  | 4602212.1569 | 16642238.4803 | [5 empty] | 0
PKG#163 | 10 | 2021-02-28 | 2021-02-25 | 2021-03-03 | 40 | 2021-04-12 | 2021-10-23 | 3812993.5626 | 38722861.26 |  |  | 2532838.57 | 16355289.4 | [5 empty] | 0
PKG#163 | 11 | 2021-03-31 | 2021-03-25 | 2021-03-31 | 40 | 2021-05-10 | 2021-04-25 | 3832626.3 | 42555487.56 |  |  | 3799097.57 | 17842244.91 | [5 empty] | 0
PKG#163 | 12 | 2021-04-30 | 2021-04-25 | 2021-05-04 | 40 | 2021-06-13 | 2021-06-03 | 3268183.05 | 45823670.61 |  |  | 2215480.09 | 17661654.17 | [5 empty] | 0
PKG#163 | 13 | 2021-05-31 | 2021-05-25 | 2021-05-31 | 40 | 2021-07-10 | 2021-06-21 | 6375780.44 | 52199451.05 |  |  | 3821253.39 | 16405178.95 | [5 empty] | 0
PKG#163 | 14 | 2021-06-30 | 2021-06-26 | 2021-07-01 | 40 | 2021-08-10 | 2021-08-02 | 13281620.95 | 65481072 |  |  | 10697999.42 | 18157750.16 | [5 empty] | 0
PKG#163 | 15 | 2021-07-31 | 2021-07-25 | 2021-08-02 | 40 | 2021-09-11 | 2021-08-26 | 7388288.7 | 72869360.7 |  |  | 4024675.65 | 16257345.38 | [5 empty] | 0
PKG#163 | 16 | 2021-08-31 | 2021-08-25 | 2021-09-06 | 40 | 2021-10-16 | 2021-09-30 | 6043601.4 | 78912962.1 |  |  | 3611195.73 | 15138470.41 | [5 empty] | 0
PKG#163 | 17 | 2021-09-30 | 2021-09-25 | 2021-10-03 | 40 | 2021-11-12 | 2021-10-27 | 5496981.8 | 84409943.9 |  |  | 2445757.34 | 12955550.43 | [5 empty] | 0
PKG#163 | 18 | 2021-10-31 | 2021-10-25 | 2021-11-01 | 40 | 2021-12-11 | 2021-11-15 | 3301294.98 | 87711238.88 |  |  | 3026069.35 | 13929653.03 | [5 empty] | 0
PKG#163 | 19 | 2021-11-30 | 2021-11-25 | 2021-11-30 | 40 | 2022-01-09 | 2021-12-16 | 9320216.47 | 97031455.35 |  |  | 7895027.24 | 15728609.99 | [5 empty] | 0
PKG#163 | 20 | 2021-12-31 | 2021-12-25 | 2022-01-02 | 40 | 2022-02-11 | 2022-01-19 | 4346059.97 | 101377515.32 |  |  | 2340959.11 | 14609274.92 | [5 empty] | 0
PKG#163 | 21 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 40 | 2022-03-15 | 2022-03-17 | 5919076.73 | 107296592.05 |  |  | 5322260.63 | 15284733.68 | [5 empty] | 0
PKG#163 | 22 | 2022-02-28 | 2022-02-28 | 2022-03-01 | 40 | 2022-04-10 | 2022-03-23 | 2632588.63 | 109929180.68 |  |  | 2261775.79 | 15087666.62 |  |  |  | 3262202.645 | 3262202.645 | 0
PKG#163 | 23 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 40 | 2022-05-17 | 2022-09-06 | 6399693.2 | 116328873.88 |  |  | 3449740.51 | 12447737.11 |  |  |  | 3363997.5 | 3363997.5 | 139451
PKG#163 | 24 | 2022-04-30 | 2022-04-20 | 2022-04-28 | 40 | 2022-06-07 | 2022-09-06 | 6669347.19 | 122998221.07 |  |  | 5681606.52 | 11928679.08 | 79159509 |  | 106910.74 | 3526010 | 3526010 | 170264.36
PKG#163 | 25 | 2022-05-31 | 2022-05-25 | 2022-06-02 | 40 | 2022-07-12 | 2022-09-06 | 12929046.56 | 135927267.63 |  |  | 11730565.83 | 11655699.31 | 84070405.07 |  | 214226.97 | 3858707 | 3858707 | 170264.36
PKG#163 | 26 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 40 | 2022-08-14 | 2022-09-19 | 6526578.31 | 142453845.94 |  |  | 6014332.37 | 11222354.42 | 87095709.46 |  | 214226.97 | 4019196.11 | 4019196.11 | 170264
PKG#163 | 27 | 2022-07-31 | 2022-07-31 | 2022-08-09 | 40 | 2022-09-18 | 2022-09-25 | 4132634.87 | 146586480.81 |  |  | 3457484.33 | 10805467.52 | 88908671.92 |  | 214226.97 | 4117255.5 | 4117255.5 | 170264
PKG#163 | 28 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 40 | 2022-10-22 | 2022-11-10 | 17622733.92 | 164209214.73 |  |  | 18331730.1 | 13098222.27 | 70785988.93 |  | 693580.47 | 4637171.235 | 4637171.235 | 0
PKG#163 | 29 | 2022-09-30 | 2022-09-30 | 2022-10-20 | 40 | 2022-11-29 | 2023-01-15 | 20296742.22 | 184505956.95 |  |  | 18785649.76 | 13098222.27 | 159762353.93 |  | 693580.47 | 5169960.72 | 5169960.72 | 170264.36
PKG#163 | 30 | 2023-01-31 | 2023-01-18 | 2023-01-18 | 40 | 2023-02-27 | 2023-08-09 | 8788912.25 | 193294869.2 |  |  | 3193802.31 | 8080616.05 | 66836818.15 |  | 624222.43 | 5275229.5 | 5275229.5 | 688139.36
PKG#163 | 31 | 2023-02-28 | 2023-02-28 | 2023-03-15 | 40 | 2023-04-24 | 2023-08-09 | -406906.47 | 192887962.73 |  |  | 1079324.1 | 9732318.5 | 56933789.25 |  | 1100688.83 | 5305840.78 | 5305840.78 | 688139.36
PKG#163 | 32 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 40 | 2023-06-23 | 2023-12-13 | 5753296.48 | 198641259.21 |  |  | 4562478.01 | 8867308.69 | 66948753.43 |  | 1100688.83 | 5435239.565 | 5435239.565 | 688139.36
PKG#163 | 33 | 2023-05-31 | 2023-05-31 | 2023-06-11 | 40 | 2023-07-21 | [5 empty] | 5000000 | [6 empty] | 0
PKG#163 | 34 | 2023-06-30 | 2023-07-10 | 2023-07-13 | 40 | 2023-08-22 | [5 empty] | 5000000 | [6 empty] | 0
PKG#163 | 35 | 2023-10-31 | 2023-11-14 | 2023-11-15 | 40 | 2023-12-25 | [5 empty] | 5000000 | [6 empty] | 0
PKG#163 | 36 | 2024-05-31 | 2024-05-21 | 2024-05-26 | 40 | 2024-07-05 |  |  | 221749507 |  |  | 10852799 | [6 empty] | 0
PKG#177 | 2 | 2021-04-30 | 2021-04-30 | 2021-04-26 | 30 | 2021-05-26 | 2021-05-12 | 8478947.03 | 8478947.03 |  |  | 10240448.36 | 4144486.18 | [5 empty] | 16912.5
PKG#177 | 3 | 2021-04-30 | 2021-04-25 | 2021-05-05 | 30 | 2021-06-04 | 2021-05-26 | 9.9998e-05 | 8478947.03 |  |  | 3893019.54 | 9209962.12 | [5 empty] | 16912.5
PKG#177 | 4 | 2021-04-30 | 2021-04-25 | 2021-05-10 | 30 | 2021-06-09 | 2021-05-27 | 5088605.14 | 13567552.17 |  | 10000000 | 4135304.94 | 9209962.12 | [5 empty] | 57062.5
PKG#177 | 5 | 2021-05-31 | 2021-05-25 | 2021-05-26 | 30 | 2021-06-25 | 2021-06-03 | 0.0001 | 13567552.17 |  | 10000000 | 1889110.9 | 11628798.1 | [5 empty] | 0
PKG#177 | 6 | 2021-05-31 | 2021-05-25 | 2021-05-30 | 30 | 2021-06-29 | 2021-06-21 | 0.0001 | 13567552.17 |  | 10000000 | 2069539.45 | 14278656.55 | [5 empty] | 57062.5
PKG#177 | 7 | 2021-05-31 | 2021-05-25 | 2021-06-02 | 30 | 2021-07-02 | 2021-06-21 | 0.0001 | 13567552.17 |  | 10000000 | 30000000 | 14278656.55 | [5 empty] | 57062.5
PKG#177 | 8 | 2021-05-31 | 2021-05-25 | 2021-06-06 | 30 | 2021-07-06 | 2021-06-21 | 7777231.12 | 21344783.29 |  | 10000000 | 6324855.08 | 14212069.8 | [5 empty] | 57062.5
PKG#177 | 9 | 2021-05-31 | 2021-05-25 | 2021-06-09 | 30 | 2021-07-09 | 2021-06-21 | 0.0001 | 21344783.29 |  | 10000000 | 1386804.78 | 15987748.13 | [5 empty] | 57062.5
PKG#177 | 10 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 9.9996e-05 | 21344783.29 |  | 10000000 | 1030274.11 | 17306921.13 | [5 empty] | 57062.5
PKG#177 | 11 | 2021-05-31 | 2021-05-25 | 2021-06-14 | 30 | 2021-07-14 | 2021-06-27 | 0.00010001 | 21344783.29 |  | 10000000 | 1623911.78 | 19386193.57 | [5 empty] | 57062.5
PKG#177 | 12 | 2021-05-31 | 2021-06-10 | 2021-06-17 | 30 | 2021-07-17 | 2021-07-08 | 17543747.3405 | 38888530.6305 |  |  | 11864115.6307 | 16150782.833 | [5 empty] | 57062.5
PKG#177 | 13 | 2021-05-31 | 2021-06-10 | 2021-06-24 | 30 | 2021-07-24 | 2021-07-08 | -0.0001 | 38888530.6305 |  |  | 4287396.18 | 21640406.623 | [5 empty] | 57062.5
PKG#177 | 14 | 2021-06-30 | 2021-07-10 | 2021-07-07 | 30 | 2021-08-06 | 2021-07-08 | -0.0006304 | 38888530.63 |  |  | 3654358.5 | 26319482.8 | [5 empty] | 57062.5
PKG#177 | 15 | 2021-06-30 | 2021-07-10 | 2021-07-11 | 30 | 2021-08-10 | 2021-07-15 | 0.00043038 | 38888530.6305 |  |  | 30000000 | 26319482.803 | [5 empty] | 57062.5
PKG#177 | 16 | 2021-06-30 | 2021-07-10 | 2021-07-15 | 30 | 2021-08-14 | 2021-08-08 | 49248459.9349 | 88136990.5654 |  |  | 8979568.5092 | 24945340.303 | [5 empty] | 415112.5
PKG#177 | 17 | 2021-06-30 | 2021-07-10 | 2021-07-28 | 30 | 2021-08-27 | 2021-08-10 | 0.0045094 | 88136990.57 |  |  | 311058.51 | 25343622.64 | [5 empty] | 415112.5
PKG#177 | 18 | 2021-06-30 | 2021-07-10 | 2021-08-02 | 30 | 2021-09-01 | 2021-09-02 | 12925810.52 | 101062801.09 |  |  | 15056356.09 | 31043670.3 | [5 empty] | 415112.5
PKG#177 | 19 | 2021-07-31 | 2021-07-25 | 2021-08-05 | 30 | 2021-09-04 | 2021-09-16 | -0.0001 | 101062801.09 |  |  | 6139746.33 | 38754821.03 | [5 empty] | 528137.5
PKG#177 | 20 | 2021-07-31 | 2021-07-25 | 2021-08-08 | 30 | 2021-09-07 | 2021-10-19 | 10455877.97 | 111518679.06 |  |  | 7622310.5 | 37529135.79 | [5 empty] | 528137.5
PKG#177 | 21 | 2021-07-31 | 2021-07-25 | 2021-08-17 | 30 | 2021-09-16 | 2021-11-18 | 10986391.49 | 122505070.55 |  |  | 5555354.29 | 33099520.87 | [5 empty] | 528137.5
PKG#177 | 22 | 2021-08-31 | 2021-08-31 | 2021-08-31 | 30 | 2021-09-30 | 2021-12-07 | 7592601.09 | 130097671.64 |  |  | 3438276.09 | 29527784.9 | [5 empty] | 528137.5
PKG#177 | 23 | 2021-08-31 | 2021-09-05 | 2021-09-08 | 30 | 2021-10-08 | 2022-01-04 | 4755868.7 | 134853540.34 |  |  | 4323818.2 | 30254166.65 | [5 empty] | 674051.5
PKG#177 | 24 | 2021-08-31 | 2021-09-05 | 2021-09-12 | 30 | 2021-10-12 | 2022-01-26 | 5954515.89 | 140808056.23 |  |  | 4835550.93 | 29555882.9 | [5 empty] | 0
PKG#177 | 25 | 2021-09-30 | 2021-09-25 | 2021-10-06 | 30 | 2021-11-05 | 2022-02-28 | 3618126.71 | 144426182.94 |  |  | 4062127.69 | 30667900.14 | [5 empty] | 0
PKG#177 | 26 | 2021-10-31 | 2021-10-25 | 2021-11-03 | 30 | 2021-12-03 | 2022-03-13 | -0.00099997 | 144426182.94 |  |  | 30000000 | 30667900.14 | [5 empty] | 0
PKG#177 | 27 | 2021-11-30 | 2021-11-25 | 2021-12-07 | 30 | 2022-01-06 | 2022-03-23 | 1336271.1 | 145762454.04 |  |  | 1920178.92 | 31729493.34 | [5 empty] | 0
PKG#177 | 28 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-03-30 | 4959294.77 | 150721748.81 |  |  | 3761592.26 | 31076204.59 | [5 empty] | 0
PKG#177 | 29 | 2022-02-28 | 2022-02-28 | 2022-03-30 | 30 | 2022-04-29 | 2022-04-05 | -0.0001 | 150721748.81 |  |  | 30000000 | 31076204.59 | [5 empty] | 0
PKG#177 | 30 | 2021-12-31 | 2021-12-30 | 2022-01-05 | 30 | 2022-02-04 | 2022-04-18 | 13573272.69 | 164295021.5 |  |  | 11173851.87 | 32011659.59 | [5 empty] | 0
PKG#177 | 31 | 2022-04-30 | 2022-04-18 | 2022-04-18 | 30 | 2022-05-18 | 2022-04-19 | -0.0001 | 164295021.5 |  |  | 20000000 | 32011659.59 | [5 empty] | 1244836
PKG#177 | 32 | 2022-01-31 | 2022-01-31 | 2022-02-10 | 30 | 2022-03-12 | 2022-05-10 | 10655190.55 | 174950212.05 |  |  | 9586713.98 | 31704142.35 | [5 empty] | 0
PKG#177 | 33 | 2022-03-31 | 2022-03-28 | 2022-05-22 | 30 | 2022-06-21 | [12 empty] | 0
PKG#177 | 34 | 2022-02-28 | 2022-03-01 | 2022-03-06 | 30 | 2022-04-05 | 2022-06-01 | 4083110.25 | 189971239 |  |  | 3242747.22 | 33248463 |  |  |  | 5813429 | 5813429 | 1266148
PKG#177 | 35 | 2022-04-30 | 2022-04-20 | 2022-06-08 | 30 | 2022-07-08 | 2022-06-08 | 20620247 | 210591486 |  |  | 14874314.24 | 32687951 |  |  |  | 6340697.5 | 6340697.5 | 1273436
PKG#177 | 36 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 | 2022-08-04 | 41964961.54 | 252556447.54 |  |  | 32974130.9 | 55952679 |  |  |  | 8027886.035 | 8027886.035 | 2506369.82
PKG#177 | 37 | 2022-03-31 | 2022-04-12 | 2022-04-12 | 30 | 2022-05-12 | 2022-08-14 | 3201525.38 | 255757972.92 |  |  | 2963171.82 | 55952679 |  |  |  | 8111926.08 | 8111926.08 | 1543023.5
PKG#177 | 38 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 | 2022-08-15 | 113074932.04 | 368832904.96 |  |  | 40830987.19 | 41102851 |  |  | 430147 | 10708897.325 | 10708897.325 | 8967998.5
PKG#177 | 39 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 | 2022-10-03 | 62332263.27 | 431165168.23 |  |  | 24380106.6 | 36844292 | [5 empty] | 0
PKG#177 | 40 | 2022-07-31 | 2022-07-31 | 2022-07-31 | 30 | 2022-08-30 | 2022-11-22 | 2265658.58 | 433430826.81 |  |  | 0.0001 | 36844292 |  |  | 430147 |  |  | 0
PKG#177 | 41 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 | 2022-11-22 | 16308262.76 | 449739089.57 |  |  | 0.0001 | 23473659 | [5 empty] | 0
PKG#177 | 42 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 30 | 2022-10-30 | 2023-02-22 | 25575904.54 | 475314994.11 |  |  | 4207031.92 | [6 empty] | 0
PKG#177 | 43 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-04-13 | -1403499.79 | 473911494.32 |  |  | 14488837.89 | 23473659 | 399954494 |  | 430147.49 | 12864128.305 | 12864128.305 | 3512870.7
PKG#177 | 44 | 2023-01-31 | 2023-01-25 | 2023-04-13 | 30 | 2023-05-13 | 2023-05-25 | 59788309.64 | 533699803.96 |  |  | 17144236.06 | 11107434 | 448361770 |  | 430147.49 | 13994560.62 | 13994560.62 | 4392870.7
PKG#177 | 45 | 2022-08-31 | 2022-08-25 | 2022-09-07 | 30 | 2022-10-07 | 2023-06-15 | 102598790.27 | 576510284.59 |  |  | 15002016.49 | 12544287.37 | 474871564.16 |  | 430147.49 | 14726364.3 | 14726364.3 | 4392870.7
PKG#177 | 46 | 2022-09-30 | 2022-09-25 | 2022-10-17 | 30 | 2022-11-16 | 2023-07-16 | -22395666.32 | 554114618.27 |  |  | 3056265.5 | 12544287.37 | 479879018.92 |  | 430147 | 14857839.5 | 14857839.5 | 8396085.7
PKG#177 | 47 | 2023-06-30 | 2023-06-25 | 2023-02-15 | 30 | 2023-03-17 | 2023-08-03 | 6780617.51 | 560895235.78 |  |  | 4274854.67 | 10901184.51 | 486669436 |  | 430147 | 14994854.5 | 14994854.5 | 8396085.7
PKG#177 | 48 | 2023-03-31 | 2023-03-25 | 2023-03-26 | 30 | 2023-04-25 | [5 empty] | 4111000 | [6 empty] | 0
PKG#177 | 49 | 2023-04-30 | 2023-04-30 | 2023-05-14 | 30 | 2023-06-13 | [5 empty] | 0.0001 | [6 empty] | 0
PKG#177 | 50 | 2023-05-31 | 2023-05-31 | 2023-06-04 | 30 | 2023-07-04 | [5 empty] | 0.001 | [6 empty] | 0
PKG#177 | 51 | 2023-06-30 | 2023-06-25 | 2023-06-25 | 30 | 2023-07-25 | [5 empty] | 0.001 | [6 empty] | 0
PKG#177 | 52 | 2023-07-31 | 2023-08-10 | 2023-08-14 | 30 | 2023-09-13 | [5 empty] | 45000000 | [6 empty] | 0
PKG#177 | 53 | 2023-10-31 | 2023-11-14 | 2023-11-14 | 30 | 2023-12-14 | [5 empty] | 5000000 | [6 empty] | 0
PKG#177 | 54 | 2024-05-31 | 2024-06-04 | 2024-06-05 | 30 | 2024-07-05 |  |  | 626950196.89 |  |  | 14081143 | [6 empty] | 0
PKG#177 - DP | 1 | 2021-03-31 | 2021-03-24 | 2021-03-24 | 30 | 2021-04-23 | [5 empty] | 22337274.9 | [6 empty] | 0
PKG#177 - SWI 07 | 1 | 2021-11-30 | 2021-12-15 | 2021-12-13 | 30 | 2022-01-12 | [5 empty] | 1800000 | [6 empty] | 0
PKG#177 - SWI 07 | 2 | 2021-12-31 | 2021-12-31 | 2022-01-03 | 30 | 2022-02-02 | [5 empty] | 4300000 | [6 empty] | 0
PKG#177 - SWI 07 | 3 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 | [5 empty] | 5800000 | [6 empty] | 0
PKG#177 - SWI 07 | 4 | 2022-02-28 | 2022-02-28 | 2022-03-02 | 30 | 2022-04-01 | [12 empty] | 0
PKG#177 - SWI 07 | 5 | 2022-03-31 | 2022-03-28 | 2022-04-07 | 30 | 2022-05-07 | [5 empty] | 9500000 | [6 empty] | 0
PKG#177 - SWI 07 | 6 | 2022-04-30 | 2022-04-20 | 2022-05-04 | 30 | 2022-06-03 |  | 3141613.418 | 31868573.268 |  |  | 5000000 |  |  |  | 1025274 |  |  | 0
PKG#177 - SWI 07 | 7 | 2022-05-31 | 2022-05-25 | 2022-06-04 | 30 | 2022-07-04 |  | 10847798.8446 | 42716372.1126 |  |  | 4000000 | [6 empty] | 0
PKG#177 - SWI 07 | 8 | 2022-06-30 | 2022-06-25 | 2022-07-05 | 30 | 2022-08-04 | [5 empty] | 500000 | [6 empty] | 0
PKG#177 - SWI 07 | 9 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 30 | 2022-09-09 | [5 empty] | 4000000 | [6 empty] | 0
PKG#177 - SWI 07 | 10 | 2022-09-30 | 2022-09-30 | 2022-10-17 | 30 | 2022-11-16 | [12 empty] | 0
PKG#178 | 2 | 2021-02-28 | 2021-02-28 | 2021-03-04 | 30 | 2021-04-03 | 2021-04-14 | 16123744.18 | 16123744.18 |  |  | 13230338.29 | [6 empty] | 0
PKG#178 | 3 | 2021-03-31 | 2021-03-31 | 2021-04-04 | 30 | 2021-05-04 | 2021-04-28 | 8196011.07 | 24319755.25 |  |  | 6675236.88 | 1215987.76 | [5 empty] | 50000
PKG#178 | 4 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 30 | 2021-06-04 | 2021-06-03 | 7478094.91 | 31797850.16 |  |  | 6081013.28 | [6 empty] | 0
PKG#178 | 5 | 2021-05-31 | 2021-06-07 | 2021-06-08 | 30 | 2021-07-08 | 2021-06-21 | 10300781.8 | 42098631.96 |  |  | 9125492.66 | [6 empty] | 105137.6
PKG#178 | 6 | 2021-06-30 | 2021-07-08 | 2021-07-11 | 30 | 2021-08-10 | 2021-09-21 | 4524611.34 | 46623243.3 |  |  | 2730279.03 | 0 | [5 empty] | 1562612.5
PKG#178 | 7 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 30 | 2021-12-02 | 2021-12-02 | 686559 | 47309802.3 |  |  | 1844728.45 | 0 | [5 empty] | 1595537.5
PKG#178 | 8 | 2022-01-31 | 2022-01-31 | 2022-02-01 | 30 | 2022-03-03 | 2022-02-28 | 1389835.54 | 48699637.84 |  |  | 595920.46 |  |  |  |  | 1278365.495 | 1278365.495 | 0
PKG#178 | 9 | 2022-08-31 | 2022-08-28 | 2022-08-30 | 30 | 2022-09-29 | 2022-10-09 | 31809.52 | 48731447.36 |  |  | 88751.13 |  |  |  |  | 1279200.495 | 1279200.495 | 2370468.93
PKG#178 | 10 | 2023-01-31 | 2023-01-25 | 2023-05-29 | 30 | 2023-06-28 | 2023-06-02 | -0.0001 | 48731447.36 |  |  | 2080200.49 |  | 12630627.58 |  | 413484.78 |  |  | 1769468.93
PKG#178 - DP | 1 | 2021-01-31 | 2021-01-25 | 2021-01-25 | 30 | 2021-02-24 | 2021-02-02 |  |  |  |  | 3747170.2 | [6 empty] | 0
PKG#205 | 2 | 2022-04-30 | 2022-04-28 | 2022-05-24 | 30 | 2022-06-23 | 2022-05-24 | 1935314 | 1935314 |  |  | 1181605.96 | 0 | 0 |  | 0 | 50801.99 | 50801.99 | 0
PKG#205 | 3 | 2022-05-31 | 2022-05-31 | 2022-06-13 | 30 | 2022-07-13 | 2022-06-13 | 2048098 | 3983412 |  |  | 1250466.11 |  |  |  | 63808.49 | 104564.5 | 104564.5 | 0
PKG#220B | 2 | 2023-05-31 | 2023-05-31 | 2023-06-07 | 30 | 2023-07-07 | 2023-06-20 | 12159328.08 | 12159328.08 |  |  | 8261597.76 |  |  |  |  | 319182.36 | 319182.36 | 0
PKG#220B | 3 | 2023-06-30 | 2023-07-05 | 2023-07-10 | 30 | 2023-08-09 | 2023-08-14 | 11462411.01 | 23621739.09 |  |  | 5980500.04 |  |  |  |  | 620070.65 | 620070.65 | 1017875
PKG#220B | 4 | 2023-07-31 | 2023-08-05 | 2023-08-07 | 30 | 2023-09-06 | [5 empty] | 2300000 | [6 empty] | 0
PKG#220B - DP | 1 | 2023-05-31 | 2023-05-21 | 2023-05-21 | 30 | 2023-06-20 | [12 empty] | 0
PKG#45 | 46 | 2018-06-30 | 2018-07-15 | 2018-09-18 |  | 2018-12-15 | 2018-11-21 |  | 59167173.46 |  |  | 1069392.54
PKG#58 | 22 | 2015-12-31 | 2015-12-29 | 2015-12-29 |  | 2018-11-15 | 2018-10-21 | 0 | 4831971.92 |  |  | 317558.66
PKG#85 | 5 | 2018-10-31 | 2018-10-17 | 2018-11-11 | 30 | 2018-12-11
PKG#85 | 6 | 2019-02-28 | 2019-02-28 | 2019-03-09 | 30 | 2019-04-08 | 2019-05-20 | 2033193.5852 | 8147064.8613 |  |  | 768766.5752
PKG#85 | 7 | 2019-05-31 | 2019-05-15 | 2019-06-10 | 30 | 2019-07-10
PKG#85 | 8 | 2019-10-31 | 2019-10-11 | 2019-11-18 | 30 | 2019-12-18
PO#11687 | 1 | 2018-12-31 | 2019-01-10 | 2019-01-10 | 15 | 2019-01-25 | [12 empty] | 0
PO#11687 | 2 | 2019-02-28 | 2019-02-28 | 2019-02-28 | 15 | 2019-03-15 | [12 empty] | 0
PO#11687 | 3 | 2019-03-31 | 2019-04-14 | 2019-08-22 | 15 | 2019-09-06 | [12 empty] | 0
PO#11687 | 5 | 2019-11-30 | 2019-12-18 | 2019-12-19 | 15 | 2020-01-03 | [12 empty] | 0
Port Said Silos | 1 | 2022-03-31 | 2022-03-25 | 2022-03-05 | 21 | 2022-03-26 | 2022-04-24 | 9011475.2 | 9011475.2 | 26540249.4 |  | 5248643 | [6 empty] | 0
Port Said Silos | 2 | 2022-04-30 | 2022-04-25 | 2022-04-28 | 21 | 2022-05-19 | 2022-05-17 | 2334108.9048 | 11345584.1048 | 15000000 |  | 1688672.941 | [6 empty] | 0
Port Said Silos | 3 | 2022-05-31 | 2022-05-25 | 2022-06-02 | 21 | 2022-06-23 | [12 empty] | 0
Port Said Silos | 4 | 2022-06-30 | 2022-06-29 | 2022-06-29 | 21 | 2022-07-20 | [12 empty] | 0
Port Said Silos | 5 | 2022-07-31 | 2022-07-31 | 2022-08-02 | 21 | 2022-08-23 | 2022-08-09 | 5318356.3714 | 25985299.3429 |  |  | 4009921 | [6 empty] | 0
Port Said Silos | 6 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 21 | 2022-09-21 | 2022-09-13 | 9017880.2762 | 35003179.619 |  |  | 6842722 | [6 empty] | 0
Port Said Silos | 7 | 2022-09-30 | 2022-09-30 | 2022-10-02 | 21 | 2022-10-23 | 2022-10-18 | 4021476.8571 | 39024656.4762 |  |  | 3061822 | [6 empty] | 0
Port Said Silos | 8 | 2022-10-31 | 2022-10-31 | 2022-11-07 | 21 | 2022-11-28 | 2022-11-21 | 22573115.9429 | 61597772.419 |  |  | 17260533 | [6 empty] | 0
Port Said Silos | 9 | 2022-11-30 | 2022-11-30 | 2022-12-05 | 21 | 2022-12-26 | 2022-12-19 | 3139225.2286 | 64736997.6476 |  |  | 2370710 | [6 empty] | 0
Port Said Silos | 10 | 2022-12-31 | 2022-12-30 | 2023-01-01 | 21 | 2023-01-22 | 2023-01-22 | 8366928.5333 | 73103926.19 |  |  | 6384571 | [6 empty] | 0
Port Said Silos | 11 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-02-15 | 5057462.5238 | 78161388.7138 |  |  | 3852337 | [6 empty] | 0
Port Said Silos | 12 | 2023-02-28 | 2023-02-28 | 2023-03-01 | 21 | 2023-03-22 | 2023-03-20 | 2086813.5333 | 80248202.2471 |  |  | 1587432 | [6 empty] | 0
Port Said Silos | 13 | 2023-03-31 | 2023-03-31 | 2023-04-02 | 21 | 2023-04-23 | 2023-04-02 | 612060.8329 | 80860263.08 |  |  | 451211.246 | [6 empty] | 0
Port Said Silos | 14 | 2023-04-30 | 2023-04-30 | 2023-05-02 | 21 | 2023-05-23 | [12 empty] | 0
Port Said Silos | 15 | 2023-05-31 | 2023-05-30 | 2023-06-03 | 21 | 2023-06-24 | 2023-07-05 | 10044463.5619 | 93708293.0229 |  |  | 7663669 | [6 empty] | 0
Port Said Silos | 16 | 2023-06-30 | 2023-06-30 | 2023-07-08 | 21 | 2023-07-29 | 2023-07-17 | 12501707.0667 | 106210000.0895 |  |  | 9649102 | [6 empty] | 0
Port Said Silos | 17 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 21 | 2023-08-21 | 2023-08-15 | 7676679.5524 | 113886679.6419 |  |  | 5738977 | [6 empty] | 0
Port Said Silos | 18 | 2023-08-31 | 2023-08-31 | 2023-09-03 | 21 | 2023-09-24 | 2023-10-03 | 7866196.5143 | 121752876.1562 |  |  | 2991787 | [6 empty] | 0
Port Said Silos | 19 | 2023-09-30 | 2023-09-30 | 2023-10-01 | 21 | 2023-10-22 | 2023-10-16 | 17118439.2571 | 138871315.4133 |  |  | 12748959 | [6 empty] | 0
Port Said Silos | 20 | 2023-10-31 | 2023-10-31 | 2023-11-01 | 21 | 2023-11-22 | 2023-11-22 | 12988784 | 151860099.4133 |  |  | 6593857 | [6 empty] | 0
Port Said Silos | 21 | 2023-11-30 | 2023-11-30 | 2023-11-30 | 21 | 2023-12-21 | 2023-12-23 | 15886446.6476 | 167746546.061 |  |  | 11818794 | [6 empty] | 0
Port Said Silos | 22 | 2023-12-31 | 2023-12-13 | 2023-12-14 | 21 | 2024-01-04 | 2023-12-27 | 6713332.6667 | 174459878.7276 |  |  | 4826684 | [6 empty] | 0
Port Said Silos | 23 | 2023-12-31 | 2023-12-31 | 2024-01-04 | 21 | 2024-01-25 | 2024-01-18 | 3587901.4571 | 178047780.1848 |  |  | 2411082.19 | [6 empty] | 0
Port Said Silos | 24 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 21 | 2024-02-27 | 2024-02-21 | 4764115.7714 | 182811895.9562 |  |  | 3306186 | [6 empty] | 0
Port Said Silos | 25 | 2024-02-29 | 2024-02-29 | 2024-03-04 | 21 | 2024-03-25 | 2024-04-07 | 4504742.6762 | 187316638.6324 |  |  | 3280048 | [6 empty] | 0
Port Said Silos | 26 | 2024-03-31 | 2024-03-31 | 2024-04-04 | 21 | 2024-04-25 | 2024-05-07 | 2227046.781 | 189543685.4133 |  |  | 426108 | [6 empty] | 0
Port Said Silos | 27 | 2024-04-30 | 2024-05-01 | 2024-05-01 | 21 | 2024-05-22 | 2024-05-27 | 1522665.14 | 191066350.5533 |  |  | 0.0001 | [6 empty] | 0
Port Said Silos | 28 | 2024-05-31 | 2024-05-31 | 2024-06-02 | 21 | 2024-06-23 | 2024-07-01 | 3379589.9429 | 194445940.4962 |  |  | 1239632 | [6 empty] | 0
Port Said Silos | 29 | 2024-06-30 | 2024-06-30 | 2024-07-07 | 21 | 2024-07-28 | 2024-08-07 | 2107663.7333 | 196553604.2295 |  |  | 337130 | [6 empty] | 0
Port Said Silos | 30 | 2024-07-31 | 2024-07-31 | 2024-08-03 | 21 | 2024-08-24 | 2024-08-22 | 3191368.2381 | 199744972.4676 |  |  | 100641 | [6 empty] | 0
Port Said Silos | 31 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 2906595.6404 | 202651568.108 |  |  | 727554 | [6 empty] | 0
Port Said Silos | 32 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-11-03 | 4167368.41 | 206818936.518 |  |  | 2193035.35 | [6 empty] | 0
Port Said Silos | 33 | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 | [12 empty] | 0
Port Said Silos - Foreigner Supply | 1 | 2023-09-30 | 2023-09-30 | 2023-09-24 | 21 | 2023-10-15 | 2023-11-06 | 5539353.23 | 5539353.23 |  |  | 5206992.0362 | [6 empty] | 0
Port Said Silos - Foreigner Supply | 2 | 2023-10-31 | 2023-10-31 | 2023-12-05 | 21 | 2023-12-26 | [12 empty] | 0
Port Said Silos - Local Supply | 1 | 2023-01-31 | 2023-01-29 | 2023-01-29 | 21 | 2023-02-19 | 2023-03-16 | 673851.6 | 673851.6 |  |  | 438003.54 | [6 empty] | 0
Port Said Silos - Local Supply | 2 | 2023-09-30 | 2023-09-30 | 2023-10-18 | 21 | 2023-11-08 | 2023-11-06 | 1194976.6491 | 1868828.2491 |  |  | 1162711.94 | [6 empty] | 0
Port Said Silos - Local Supply | 3 | 2024-02-29 | 2024-02-29 | 2024-03-13 | 21 | 2024-04-03 | 2024-03-31 | 3085091.6316 | 4953919.8807 |  |  | 2307930.88 | [6 empty] | 0
Port Said Silos - Local Supply | 4 | 2024-03-31 | 2024-03-31 | 2024-04-07 | 21 | 2024-04-28 | 2024-05-07 | 4365732.3333 | 9319652.214 |  |  | 3416710 | [6 empty] | 0
Port Said Silos - Local Supply | 5 | 2024-04-30 | 2024-04-30 | 2024-05-12 | 21 | 2024-06-02 | 2024-05-27 | 3278709.2807 | 12598361.4947 |  |  | 2565984 | [6 empty] | 0
Port Said Silos - Local Supply | 6 | 2024-05-31 | 2024-05-31 | 2024-06-09 | 21 | 2024-06-30 | 2024-07-01 | 1064669.3947 | 13663030.8895 |  |  | 833240 | [6 empty] | 0
Port Said Silos - Local Supply | 7 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 21 | 2024-08-06 | 2024-08-06 | 5552464.7544 | 19215495.6439 |  |  | 4345468 | [6 empty] | 0
Port Said Silos - Local Supply | 8 | 2024-07-31 | 2024-07-31 | 2024-08-18 | 21 | 2024-09-08 | 2024-09-01 | 2594878.4386 | 21810374.0825 |  |  | 1794648.84 | [6 empty] | 0
Port Said Silos - Local Supply | 9 | 2024-08-31 | 2024-08-31 | 2024-09-02 | 21 | 2024-09-23 | 2024-10-15 | 3231641.7018 | 25042015.7842 |  |  | 2529147 | [6 empty] | 0
Port Said Silos - Local Supply | 10 | 2024-09-30 | 2024-09-30 | 2024-10-10 | 21 | 2024-10-31 | 2024-10-03 | 622795.91 | 25664811.6942 |  |  | 494192 | [6 empty] | 0
Port Said Silos - Local Supply | 11 | 2024-10-31 | 2024-10-31 | 2024-10-31 | 21 | 2024-11-21 | [12 empty] | 0
PSP Substation | 2 | 2018-06-30 | 2018-07-03 | 2018-07-05 | 30 | 2018-08-04 | 2018-07-22 | 1669926.8 | 1669926.8 |  |  | 1244095.47 | 0 | [5 empty] | 0
PSP Substation | 3 | 2018-07-31 | 2018-08-05 | 2018-08-06 | 30 | 2018-09-05 | 2018-10-11 | 2696322.9906 | 4366249.7906 |  |  | 1834172.07 | [6 empty] | 0
PSP Substation | 4 | 2018-08-31 | 2018-09-10 | 2018-09-11 | 30 | 2018-10-11 | [12 empty] | 0
PSP Substation | 5 | 2018-09-30 | 2018-10-08 | 2018-10-08 | 30 | 2018-11-07 | 2018-10-16 | 6439927.8 | 12694557.6 |  |  | 5046458.33 | 0 | [5 empty] | 0
PSP Substation | 6 | 2018-10-31 | 2018-11-10 | 2018-11-11 | 30 | 2018-12-11 | 2018-11-21 | 4012970.52 | 16707528.12 |  |  | 3047586.1 | [6 empty] | 0
PSP Substation | 7 | 2018-11-30 | 2018-12-10 | 2018-12-10 | 30 | 2019-01-09 | 2019-01-06 | 3355601.28 | 20063129.4 |  |  | 2548357.58 | [6 empty] | 0
PSP Substation | 8 | 2018-12-31 | 2019-01-12 | 2019-01-16 | 30 | 2019-02-15 | 2019-02-05 | 2786776.25 | 22849905.65 |  |  | 2116372.52 | 0 | [5 empty] | 0
PSP Substation | 9 | 2019-01-31 | 2019-02-10 | 2019-02-23 | 30 | 2019-03-25 | 2019-04-11 | 2055054.9 | 24904960.55 |  |  | 1560678.78 | [6 empty] | 0
PSP Substation | 10 | 2019-03-31 | 2019-03-31 | 2019-04-03 | 30 | 2019-05-03 | 2019-04-23 | 4978707.75 | 29883668.3 |  |  | 3808343.08 | [6 empty] | 0
PSP Substation | 11 | 2019-06-30 | 2019-06-25 | 2019-12-22 | 30 | 2020-01-21 | [12 empty] | 0
PSP Substation | 12 | 2019-06-30 | 2019-06-25 | 2020-12-06 | 30 | 2021-01-05 | 2020-12-09 | 54510.7209 | 32341773.9509 |  |  | 28515 | [6 empty] | 0
Rabigh Ext. - Piles | 1 | 2024-02-29 | 2024-02-29 | 2024-03-05 | 57 | 2024-05-01 | 2024-03-18 | 1098993.1 | 1098993.1 |  |  | 947881.6 |  |  |  |  | 54949.66 |  | 0
Rabigh Ext. - Piles | 2 | 2024-04-30 | 2024-04-24 | 2024-04-24 | 57 | 2024-06-20 | 2024-05-02 | 1361202.3 | 2460195.4 |  |  | 1174036.98 |  |  |  |  | 123009.77 |  | 0
Rabigh Ext. - Piles | 3 | 2024-04-30 | 2024-05-14 | 2024-05-14 | 57 | 2024-07-10 | [12 empty] | 0
Rabigh Ext. - Piles | 4 | 2024-05-31 | 2024-06-01 | 2024-06-10 | 57 | 2024-08-06 | 2024-07-08 | 2071949.5 | 5652409 |  |  | 1787056.4438 |  |  |  |  | 282620.45 |  | 0
Rabigh Ext. - Piles | 5 | 2024-06-30 | 2024-06-30 | 2024-07-10 | 57 | 2024-09-05 | [12 empty] | 0
Rabigh Ext. - Piles | 6 | 2024-07-31 | 2024-07-31 | 2024-08-14 | 57 | 2024-10-10 | [12 empty] | 0
Rabigh Ext. - Piles | 7 | 2024-08-31 | 2024-08-31 | 2024-09-07 | 57 | 2024-11-03 | [12 empty] | 0
Rabigh Ext. - Piles | 8 | 2024-09-30 | 2024-09-30 | 2024-10-19 | 57 | 2024-12-15 | [12 empty] | 0
Rabigh Ext. -Building | 1 | 2024-06-30 | 2024-06-30 | 2024-07-09 | 75 | 2024-09-22 | 2024-07-10 | 2561755.35 | 2561755.35 |  |  | 2283164.46 |  |  |  |  | 128087.77 |  | 0
Rabigh Ext. -Building | 2 | 2024-07-31 | 2024-07-31 | 2024-08-05 | 75 | 2024-10-19 | 2024-08-25 | 5727560.34 | 8289315.69 |  |  | 4957387.2204 |  |  |  |  | 414465.7845 |  | 0
Rabigh Ext. -Building | 3 | 2024-08-31 | 2024-08-31 | 2024-09-05 | 75 | 2024-11-19 | 2024-09-19 | 5121658.33 | 13410974.02 |  |  | 4088042.3344 |  |  |  |  | 670548.701 |  | 0
Rabigh Ext. -Building | 4 | 2024-09-30 | 2024-09-30 | 2024-10-06 | 75 | 2024-12-20 | 2024-10-23 | 6246650.22 | 19657624.24 |  |  | 4796196.0024 |  |  |  |  | 982881.212 |  | 0
Rabigh Ext. -Building | 5 | 2024-10-31 | 2024-10-31 | 2024-11-03 | 75 | 2025-01-17 | [12 empty] | 0
Radamis-Concrete | 1 | 2022-04-30 | 2022-04-25 | 2022-04-25 | 30 | 2022-05-25 |  |  |  | 10000000 | [8 empty] | 0
Radamis-Concrete | 2 | 2022-05-31 | 2022-05-25 | 2022-05-26 | 30 | 2022-06-25 |  |  |  | 10000000 | [8 empty] | 0
Radamis-Concrete | 3 | 2022-06-30 | 2022-07-07 | 2022-07-03 | 30 | 2022-08-02 | [12 empty] | 0
Radamis-Concrete | 4 | 2022-07-31 | 2022-07-31 | 2022-08-14 | 30 | 2022-09-13 | [12 empty] | 0
Radamis-Concrete | 5 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 | [12 empty] | 0
Radamis-Concrete | 6 | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 | [12 empty] | 0
Radamis-Concrete | 7 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 | [12 empty] | 0
Radamis-Concrete | 8 | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 | [12 empty] | 0
Radamis-Concrete | 9 | 2023-01-31 | 2023-01-25 | 2023-01-30 | 30 | 2023-03-01 | [12 empty] | 0
Radamis-Concrete | 10 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 | [12 empty] | 0
Radamis-Concrete | 11 | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 | [12 empty] | 0
Radamis-Concrete | 12 | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 | [12 empty] | 0
Radamis-Concrete | 13 | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 | [12 empty] | 0
Radamis-Concrete | 14 | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [12 empty] | 0
Radamis-Concrete | 15 | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 | [12 empty] | 0
Radamis-Concrete | 16 | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [12 empty] | 0
Radamis-Concrete | 17 | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [12 empty] | 0
Radamis-Concrete | 18 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [12 empty] | 0
Radamis-Concrete | 19 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [12 empty] | 0
Radamis-Concrete | 20 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [12 empty] | 0
Radamis-Concrete | 21 | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [12 empty] | 0
Radamis-Concrete | 22 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [12 empty] | 0
Radamis-Concrete | 23 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [12 empty] | 0
Radamis-Concrete | 24 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [12 empty] | 0
Radamis-Concrete | 25 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [12 empty] | 0
Radamis-Concrete | 26 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [12 empty] | 0
Radamis-Concrete | 27 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [12 empty] | 0
Radamis-Concrete | 28 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [12 empty] | 0
Radamis-Concrete | 29 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [12 empty] | 0
Radamis-Concrete | 30 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [12 empty] | 0
Radamis-H1 Main Builidng | 1 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [12 empty] | 0
Radamis-H1 Main Builidng | 2 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [12 empty] | 0
Radamis-H1 Main Builidng | 3 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [12 empty] | 0
Radamis-H1 Main Builidng | 4 | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [12 empty] | 0
Radamis-H1 Main Builidng | 5 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [12 empty] | 0
Radamis-H1 Main Builidng | 6 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [12 empty] | 0
Radamis-H1 Main Builidng | 7 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [12 empty] | 0
Radamis-H1 Main Builidng | 8 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [12 empty] | 0
Radamis-H1 Main Builidng | 9 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [12 empty] | 0
Radamis-H1 Main Builidng | 10 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [12 empty] | 0
Radamis-H1 Main Builidng | 11 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [12 empty] | 0
Radamis-H1 Main Builidng | 12 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [12 empty] | 0
Radamis-H1 Main Builidng | 13 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [12 empty] | 0
Radamis-Rooms Fitout | 1 | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 |  |  |  | 250000 | [8 empty] | 0
Radamis-Rooms Fitout | 2 | 2023-07-31 | 2023-07-20 | 2023-08-05 | 30 | 2023-09-04 |  |  |  | 500000 | [8 empty] | 0
Radamis-Rooms Fitout | 3 | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 |  |  |  | 15000000 | [8 empty] | 0
Radamis-Rooms Fitout | 4 | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 |  |  |  | 4000000 | [8 empty] | 0
Radamis-Rooms Fitout | 5 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [12 empty] | 0
Radamis-Rooms Fitout | 6 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [12 empty] | 0
Radamis-Rooms Fitout | 7 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [12 empty] | 0
Radamis-Rooms Fitout | 8 | 2024-01-31 | 2024-01-25 | 2024-02-07 | 30 | 2024-03-08 | [12 empty] | 0
Radamis-Rooms Fitout | 9 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [12 empty] | 0
Radamis-Rooms Fitout | 10 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [12 empty] | 0
Radamis-Rooms Fitout | 11 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [12 empty] | 0
Radamis-Rooms Fitout | 12 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [12 empty] | 0
Radamis-Rooms Fitout | 13 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [12 empty] | 0
Radamis-Rooms Fitout | 14 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [12 empty] | 0
Radamis-Rooms Fitout | 15 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [12 empty] | 0
Radamis-Rooms Fitout | 16 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [12 empty] | 0
Radamis-Rooms Fitout | 17 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [12 empty] | 0
Radamis-Villas Finishes | 1 | 2022-08-31 | 2022-08-31 | 2022-09-07 | 30 | 2022-10-07 | [12 empty] | 0
Radamis-Villas Finishes | 2 | 2022-09-30 | 2022-09-30 | 2022-10-07 | 30 | 2022-11-06 | [12 empty] | 0
Radamis-Villas Finishes | 3 | 2022-10-31 | 2022-10-31 | 2022-10-28 | 30 | 2022-11-27 | [12 empty] | 0
Radamis-Villas Finishes | 4 | 2022-12-31 | 2022-12-25 | 2023-01-01 | 30 | 2023-01-31 | [12 empty] | 0
Radamis-Villas Finishes | 5 | 2023-01-31 | 2023-01-30 | 2023-01-30 | 30 | 2023-03-01 | [12 empty] | 0
Radamis-Villas Finishes | 6 | 2023-02-28 | 2023-02-25 | 2023-03-02 | 30 | 2023-04-01 | [12 empty] | 0
Radamis-Villas Finishes | 7 | 2023-03-31 | 2023-03-25 | 2023-04-02 | 30 | 2023-05-02 | [12 empty] | 0
Radamis-Villas Finishes | 8 | 2023-04-30 | 2023-04-25 | 2023-05-04 | 30 | 2023-06-03 | [12 empty] | 0
Radamis-Villas Finishes | 9 | 2023-05-31 | 2023-05-25 | 2023-05-31 | 30 | 2023-06-30 | [12 empty] | 0
Radamis-Villas Finishes | 10 | 2023-06-30 | 2023-06-20 | 2023-06-24 | 30 | 2023-07-24 | [12 empty] | 0
Radamis-Villas Finishes | 11 | 2023-07-31 | 2023-07-25 | 2023-08-05 | 30 | 2023-09-04 | [12 empty] | 0
Radamis-Villas Finishes | 12 | 2023-08-31 | 2023-08-25 | 2023-09-05 | 30 | 2023-10-05 | [12 empty] | 0
Radamis-Villas Finishes | 13 | 2023-09-30 | 2023-09-25 | 2023-10-05 | 30 | 2023-11-04 | [12 empty] | 0
Radamis-Villas Finishes | 14 | 2023-10-31 | 2023-10-25 | 2023-11-09 | 30 | 2023-12-09 | [12 empty] | 0
Radamis-Villas Finishes | 15 | 2023-11-30 | 2023-11-25 | 2023-12-05 | 30 | 2024-01-04 | [12 empty] | 0
Radamis-Villas Finishes | 16 | 2023-12-31 | 2023-12-25 | 2024-01-05 | 30 | 2024-02-04 | [12 empty] | 0
Radamis-Villas Finishes | 17 | 2024-01-31 | 2024-01-25 | 2024-02-05 | 30 | 2024-03-06 | [12 empty] | 0
Radamis-Villas Finishes | 18 | 2024-02-29 | 2024-02-25 | 2024-03-05 | 30 | 2024-04-04 | [12 empty] | 0
Radamis-Villas Finishes | 19 | 2024-03-31 | 2024-03-25 | 2024-04-05 | 30 | 2024-05-05 | [12 empty] | 0
Radamis-Villas Finishes | 20 | 2024-04-30 | 2024-04-25 | 2024-05-05 | 30 | 2024-06-04 | [12 empty] | 0
Radamis-Villas Finishes | 21 | 2024-05-31 | 2024-05-25 | 2024-06-05 | 30 | 2024-07-05 | [12 empty] | 0
Radamis-Villas Finishes | 22 | 2024-06-30 | 2024-06-25 | 2024-07-05 | 30 | 2024-08-04 | [12 empty] | 0
Radamis-Villas Finishes | 23 | 2024-07-31 | 2024-07-25 | 2024-08-05 | 30 | 2024-09-04 | [12 empty] | 0
Radamis-Villas Finishes | 24 | 2024-08-31 | 2024-08-25 | 2024-09-05 | 30 | 2024-10-05 | [12 empty] | 0
Radamis-Villas Finishes | 25 | 2024-09-30 | 2024-09-25 | 2024-10-05 | 30 | 2024-11-04 | [12 empty] | 0
Radamis-Villas Finishes | 26 | 2024-10-31 | 2024-10-25 | 2024-11-05 | 30 | 2024-12-05 | [12 empty] | 0
Red Sea Museum | 1 | 2024-04-30 | 2024-04-30 | 2024-05-23 | 70 | 2024-08-01 | 2024-05-23 | 3172518.7149 | 3172518.7149 |  |  | 3648396.5221 | [6 empty] | 0
Red Sea Museum | 2 | 2024-05-31 | 2024-05-31 | 2024-05-23 | 70 | 2024-08-01 | 2024-08-21 | 2298644.2851 | 5471163 |  |  | 2114752.93 |  |  |  |  | 114932 | 114932 | 0
Red Sea Museum | 3 | 2024-08-31 | 2024-09-02 | 2024-09-02 | 70 | 2024-11-11 | 2024-09-02 | 1331566 | 6802729 |  |  | 1225041 | [6 empty] | 0
Ring Road - El Marg | 1 | 2021-02-28 | 2021-02-20 | 2021-02-20 | 60 | 2021-04-21 | [12 empty] | 0
Ring Road - El Marg | 2 | 2021-03-31 | 2021-04-15 | 2021-04-15 | 60 | 2021-06-14 | [12 empty] | 0
Ring Road - El Marg | 3 | 2021-04-30 | 2021-05-15 | 2021-05-15 | 60 | 2021-07-14 | [12 empty] | 0
Ring Road - El Marg | 4 | 2021-05-31 | 2021-06-08 | 2021-06-08 | 60 | 2021-08-07 | [12 empty] | 0
Ring Road - El Marg | 5 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 | [12 empty] | 0
Ring Road - El Marg | 6 | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 | [12 empty] | 0
Ring Road - El Marg | 7 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | [5 empty] | 25237352 | [6 empty] | 0
Ring Road - El Marg | 8 | 2021-09-30 | 2021-09-30 | 2021-10-05 | 60 | 2021-12-04 | 2021-10-24 | 4446069.4 | 142263915.035 |  |  | 3601316.214 | [6 empty] | 0
Ring Road - El Marg | 9 | 2021-10-31 | 2021-10-31 | 2021-11-06 | 60 | 2022-01-05 | 2021-11-24 | 4763028.235 | 147026943.27 |  |  | 3858052.8704 | [6 empty] | 0
Ring Road - El Marg | 10 | 2021-11-30 | 2021-11-30 | 2021-12-08 | 60 | 2022-02-06 | 2022-01-25 | 3312818.46 | 150339761.73 |  |  | 2683382.9526 | [6 empty] | 0
Ring Road - El Marg | 11 | 2022-01-31 | 2022-01-31 | 2022-02-02 | 60 | 2022-04-03 | [12 empty] | 0
Ring Road - El Marg | 12 | 2022-02-28 | 2022-02-28 | 2022-03-02 | 60 | 2022-05-01 | [12 empty] | 0
Ring Road - El Marg | 13 | 2022-05-31 | 2022-05-30 | 2022-06-02 | 60 | 2022-08-01 | [12 empty] | 0
Ring Road - Mounib | 1 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 60 | 2020-10-30 | [12 empty] | 0
Ring Road - Mounib | 2 | 2020-10-31 | 2020-10-31 | 2020-10-31 | 60 | 2020-12-30 | [12 empty] | 0
Ring Road - Mounib | 3 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 60 | 2021-03-01 | [12 empty] | 0
Ring Road - Mounib | 4 | 2021-01-31 | 2021-01-31 | 2021-02-08 | 60 | 2021-04-09 | [12 empty] | 0
Ring Road - Mounib | 5 | 2021-02-28 | 2021-02-28 | 2021-03-17 | 60 | 2021-05-16 | [12 empty] | 0
Ring Road - Mounib | 6 | 2021-03-31 | 2021-03-31 | 2021-04-15 | 60 | 2021-06-14 | [12 empty] | 0
Ring Road - Mounib | 7 | 2021-04-30 | 2021-04-30 | 2021-05-15 | 60 | 2021-07-14 | [12 empty] | 0
Ring Road - Mounib | 8 | 2021-05-31 | 2021-05-31 | 2021-06-08 | 60 | 2021-08-07 | [12 empty] | 0
Ring Road - Mounib | 9 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 60 | 2021-08-29 |  | 4536613.5882 | 98438363.943 |  |  | 3856121.55 | [6 empty] | 0
Ring Road - Mounib | 10 | 2021-07-31 | 2021-07-31 | 2021-07-31 | 60 | 2021-09-29 |  | 18316815 | 116755178.943 |  |  | 12662306 | [6 empty] | 0
Ring Road - Mounib | 11 | 2021-08-31 | 2021-08-31 | 2021-09-05 | 60 | 2021-11-04 | 2021-09-07 | 30549611.057 | 147304790 |  |  | 19857247.187 | [6 empty] | 0
Ring Road - Mounib | 12 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-10-16 | 20117126 | 167421916 |  |  | 14886673.24 | [6 empty] | 0
Ring Road - Mounib | 13 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 60 | 2022-01-07 | 2021-11-13 | 56505929 | 223927845 |  |  | 41814387.46 | [6 empty] | 0
Ring Road - Mounib | 14 | 2021-11-30 | 2021-11-30 | 2021-12-09 | 60 | 2022-02-07 | 2022-12-29 | 46948185.4 | 270876030.4 |  |  | 0 | [6 empty] | 0
Ring Road - Mounib | 15 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 60 | 2022-03-10 | 2022-01-20 | 30552404.425 | 301428434.825 |  |  | 0 | [6 empty] | 0
Ring Road - Mounib | 16 | 2022-06-30 | 2022-07-10 | 2022-07-27 | 60 | 2022-09-25 | 2022-07-27 | 161507041.625 | 462935476.45 |  |  | 0 | [6 empty] | 0
Ring Road - Mounib | 17 | 2022-07-31 | 2022-07-31 | 2022-08-10 | 60 | 2022-10-09 | 2022-08-10 | 6933306.55 | 469868783 |  |  | 5130646.847 | [6 empty] | 0
Ring Road - Mounib | 18 | 2022-08-31 | 2022-08-31 | 2022-09-12 | 60 | 2022-11-11 | 2022-09-12 | 4715315.145 | 474584098.145 |  |  | 3489333.2073 | [6 empty] | 0
Ring Road - Mounib | 19 | 2022-09-30 | 2022-09-30 | 2022-10-17 | 60 | 2022-12-16 | [12 empty] | 0
RO Apply -Mech- SSC | 1 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 2250265.4 | 2250265.4 |  |  | 1730229.07 | [6 empty] | 0
RO Apply -Mech- SSC | 2 | 2023-07-31 | 2023-07-18 | 2023-07-18 | 15 | 2023-08-02 | [12 empty] | 0
RO Apply -Mech- SSC | 4 | 2023-11-30 | 2023-11-12 | 2023-11-12 | 15 | 2023-11-27 | 2023-12-25 | 4449602.38 | 8242992.05 |  |  | 1195633.38 | [6 empty] | 0
RO Eriction | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 6000000 | 6000000 |  |  | 6660000 | [6 empty] | 0
RO Pump Room | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 22392582.54 | 22392582.54 |  |  | 2216012.07 | [6 empty] | 0
RO - Supply - Electric | 1 | 2023-01-31 | 2023-01-16 | 2023-01-17 | 15 | 2023-02-01 | 2023-01-17 | 5322406.46 | 5322406.46 |  |  | 745136.9 | [6 empty] | 0
RO - Supply - Electric | 2 | 2023-02-28 | 2023-02-16 | 2023-03-08 | 15 | 2023-03-23 | 2023-03-15 | 3040804.44 | 8363210.9 |  |  | 1847082.53 | [6 empty] | 0
RO - Supply - Electric | 3 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 15 | 2023-04-25 | 2023-04-10 | 11778923.84 | 20142134.74 |  |  | 1649065.6 | [6 empty] | 0
RO Supply -Mech- SSC | 1 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-07 | 16503981 | 16503981 |  |  | 13698304.23 | [6 empty] | 0
RO Supply -Mech- SSC | 2 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-14 | 1896616.8 | 18400597.8 |  |  | 1574191.94 | [6 empty] | 0
RO Supply -Mech- SSC | 3 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 15 | 2023-04-26 | 2023-04-12 | 28179089.25 | 28179089.25 |  |  | 8116147.9 | [6 empty] | 0
RO Supply -Mech- SSC | 4 | 2023-04-30 | 2023-04-30 | 2023-05-01 | 15 | 2023-05-16 | 2023-05-08 | 7605000 | 35784089.25 |  |  | 6312150 | [6 empty] | 0
RO Supply -Mech- SSC | 5 | 2023-07-31 | 2023-07-31 | 2023-07-18 | 15 | 2023-08-02 | 2023-07-26 | 4510403.17 | 40294492.42 |  |  | 3743634.63 | [6 empty] | 0
RO Supply -Mech- SSC | 8 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 15 | 2024-03-11 | 2024-02-27 | 14223589.16 | 54518081.58 |  |  | 1418035.09 | [6 empty] | 0
RO 2 | 1 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 15 | 2024-03-14 | 2024-02-28 | 35549128.54 | 35549128.54 |  |  | 28083811.55 | [6 empty] | 0
RO 2 | 2 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 15 | 2024-05-16 | 2024-05-02 | 1807831.26 | 37356959.8 |  |  | 1880144.51 | [6 empty] | 0
RO 2 | 3 | 2024-06-30 | 2024-06-30 | 2024-07-01 | 15 | 2024-07-16 | [12 empty] | 0
RO Pump room - SSC - price diff. | 1 | 2023-02-28 | 2023-03-08 | 2023-03-07 | 15 | 2023-03-22 | 2023-03-13 | 14675847.72 | 14675847.72 |  |  | 16583707.92 | [6 empty] | 0
RO Pump room - SSC - price diff. | 2 | 2023-03-31 | 2023-03-15 | 2023-03-15 | 15 | 2023-03-30 | 2023-03-15 | 1686530.02 | 16362377.74 |  |  | 1905778.92 | [6 empty] | 0
RO Pump room - SSC - price diff. | 3 | 2023-03-31 | 2023-04-12 | 2023-04-12 | 15 | 2023-04-27 | 2023-04-12 | 8704005.47 | 25066383.21 |  |  | 9835526.19 | [6 empty] | 0
RO Pump room - SSC - price diff. | 4 | 2023-04-30 | 2023-05-01 | 2023-05-09 | 15 | 2023-05-24 | 2023-05-09 | 6762600 | 31828983.21 |  |  | 7303608 | [6 empty] | 0
RO.2 | 1 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 15 | 2023-07-15 | [12 empty] | 0
Rolling Mill #4-TRAESUEZ | 1 | 2021-12-31 | 2022-01-10 | 2022-01-11 | 42 | 2022-02-22 | 2022-02-28 | 21476647.48 | 21476647.48 |  |  | 17181317.99 | [6 empty] | 0
Rolling Mill #4-TRAESUEZ | 2 | 2022-02-28 | 2022-03-10 | 2022-03-14 | 42 | 2022-04-25 | 2022-03-22 | 13583921.53 | 35060569.01 |  |  | 11564103.96 | [6 empty] | 0
Rolling Mill #4-TRAESUEZ | 3 | 2022-03-31 | 2022-04-10 | 2022-04-12 | 42 | 2022-05-24 | 2022-04-20 | 12117327 | 47177896.01 |  |  | 10352618.57 | [6 empty] | 0
Rolling Mill #4-TRAESUEZ | 4 | 2022-04-30 | 2022-04-28 | 2022-04-28 | 42 | 2022-06-09 | 2022-05-17 | 8075015.79 | 55252911.8 |  |  | 6677291.55 | [6 empty] | 0
Rolling Mill #4-TRAESUEZ | 5 | 2022-05-31 | 2022-06-05 | 2022-06-07 | 42 | 2022-07-19 | 2022-07-06 | 9905844.43 | 65158756.23 |  |  | 8140659.04 | 7155944.45 | [5 empty] | 0
Rolling Mill #4-TRAESUEZ | 6 | 2022-06-30 | 2022-07-05 | 2022-07-06 | 42 | 2022-08-17 | 2022-08-07 | 5743581.36 | 70902337.59 |  |  | 4679965.02 |  | 7496344.15 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 7 | 2022-07-31 | 2022-08-05 | 2022-08-06 | 42 | 2022-09-17 | 2022-08-24 | 16796950.93 | 87699288.52 |  |  | 13457708.47 |  | 7576935.06 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 8 | 2022-08-31 | 2022-09-10 | 2022-09-12 | 42 | 2022-10-24 | 2022-09-27 | 18519200.97 | 106218489.49 |  |  | 14944026.92 |  | 8091599.65 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 9 | 2022-09-30 | 2022-10-10 | 2022-10-12 | 42 | 2022-11-23 | 2022-11-07 | 17686791.21 | 123905280.7 |  |  | 14162374.17 |  | 8143364.44 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 10 | 2022-10-31 | 2022-11-07 | 2022-11-08 | 42 | 2022-12-20 | 2022-12-14 | 15395023.2 | 139300303.9 |  |  | 12338644.38 |  | 8233867.7 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 11 | 2022-11-30 | 2022-12-05 | 2022-12-08 | 42 | 2023-01-19 | 2023-01-17 | 16145745 | 155446048.9 |  |  | 13316234.88 |  | 9832423.2 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 12 | 2022-12-31 | 2023-01-15 | 2023-01-18 | 42 | 2023-03-01 | 2023-02-07 | 16694409.39 | 172140458.29 |  |  | 13380155.34 |  | 9930934.56 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 13 | 2023-01-31 | 2023-02-15 | 2023-02-16 | 42 | 2023-03-30 | 2023-03-08 | 14485776.58 | 186626234.87 |  |  | 11700102.46 |  | 10376859 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 14 | 2023-02-28 | 2023-03-10 | 2023-03-20 | 42 | 2023-05-01 | [12 empty] | 0
Rolling Mill #4-TRAESUEZ | 15 | 2023-05-31 | 2023-05-31 | 2023-06-21 | 42 | 2023-08-02 | [12 empty] | 0
Rolling Mill #4-TRAESUEZ | 16 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 42 | 2023-08-11 | [12 empty] | 0
Rolling Mill #4-TRAESUEZ | 17 | 2024-01-31 | 2024-01-31 | 2024-02-28 | 42 | 2024-04-10 | 2024-05-02 | 619836241 | 619836241 |  |  | 385850750.2 | [6 empty] | 0
Rolling Mill #4-TRAESUEZ | 18 | 2024-04-30 | 2024-04-15 | 2024-05-01 | 42 | 2024-06-12 | 2024-05-02 | 16836028.82 | 636672269.82 |  |  | 17509470.02 |  | 105081618.32 |  |  |  |  | 0
Rolling Mill #4-TRAESUEZ | 19 | 2024-06-30 | 2024-06-30 | 2024-07-16 | 42 | 2024-08-27 | [12 empty] | 0
Royal City | 2 | 2017-09-30 | 2017-09-30 | 2017-10-01 | 34 | 2017-11-04 | 2017-10-11 | 8875548.87 | 8875548.87 |  |  | 5235331.6 | 3953206.73 | [5 empty] | 34013.75
Royal City | 3 | 2017-10-31 | 2017-10-31 | 2017-11-04 | 34 | 2017-12-08 | 2017-11-14 | 8111601.4206 | 16987150.2906 |  |  | 7926742.1 | 5848040.712 | [5 empty] | 103062.25
Royal City | 4 | 2017-11-30 | 2017-12-03 | 2017-12-03 | 34 | 2018-01-06 | 2017-12-24 | 10259671.7094 | 27246822 |  |  | 10437271.65 | 8775298.38 | [5 empty] | 103062.25
Royal City | 5 | 2017-12-31 | 2017-12-30 | 2018-01-03 | 34 | 2018-02-06 | 2018-01-22 | 11565536.4187 | 38812358.4187 |  |  | 6381832.9445 | 5702856.6 | [5 empty] | 166539
Royal City | 6 | 2018-03-31 | 2018-03-31 | 2018-02-20 | 34 | 2018-03-26 | 2018-05-21 | 15834199.4413 | 54646557.86 |  |  | 12495801.39 | 3811475.98 | [5 empty] | 348145
Royal City | 7 | 2018-04-30 | 2018-04-30 | 2018-05-07 | 34 | 2018-06-10 | 2018-06-11 | 11881365.61 | 66527923.47 |  |  | 8703262.41 | 3172251.35 | [5 empty] | 582017.44
Royal City | 8 | 2018-05-31 | 2018-05-31 | 2018-06-05 | 34 | 2018-07-09 | 2018-06-24 | 7845708.0075 | 74373631.4775 |  |  | 7600061.0338 | 5502031.137 | [5 empty] | 2646288.4432
Royal City | 9 | 2018-06-30 | 2018-06-30 | 2018-07-10 | 34 | 2018-08-13 | 2018-07-26 | 7890492.132 | 82264123.6095 |  |  | 6018082.2865 | 5685747.237 | [5 empty] | 3049998.998
Royal City | 10 | 2018-07-31 | 2018-07-31 | 2018-08-08 | 34 | 2018-09-11 | 2018-08-27 | 8199169.349 | 90463292.9586 |  |  | 5554331.9836 | 4944412.0842 | [5 empty] | 3422890.7078
Royal City | 11 | 2018-08-31 | 2018-08-31 | 2018-09-12 | 34 | 2018-10-16 | 2018-09-24 | 2707034.9014 | 93170327.86 |  |  | 3237608.64 | 6546266.4 | [5 empty] | 3614328.412
Royal City | 12 | 2018-09-30 | 2018-09-30 | 2018-10-09 | 34 | 2018-11-12 | 2018-11-07 | 12651464.27 | 105821792.13 |  |  | 8503935.74 | 8045747.81 | [5 empty] | 669617.5401
Royal City | 13 | 2018-10-31 | 2018-10-31 | 2018-11-07 | 34 | 2018-12-11 | 2018-12-04 | 11315357.62 | 117137149.75 |  |  | 6339338.47 | 6383924.621 | [5 empty] | 0
Royal City | 14 | 2018-11-30 | 2018-11-30 | 2018-12-06 | 34 | 2019-01-09 | 2018-12-29 | 3293171.7405 | 120430321.4905 |  |  | 13062023.4527 | 8435330.6159 | [5 empty] | 558453.95
Royal City | 15 | 2018-12-31 | 2018-12-31 | 2019-01-06 | 34 | 2019-02-09 | 2019-01-20 | 16384822.4548 | 136815143.9453 |  |  | 9343372.736 | 9384080.2453 | [5 empty] | 653055.6603
Royal City | 16 | 2019-01-31 | 2019-01-31 | 2019-02-07 | 34 | 2019-03-13 | 2019-02-25 | 11488490.3339 | 148303634.2792 |  |  | 10141562.9942 | 12235459.3471 | [5 empty] | 320713.8483
Royal City | 17 | 2019-02-28 | 2019-02-28 | 2019-03-06 | 34 | 2019-04-09 | 2019-04-01 | 9063503.9339 | 157367138.2131 |  |  | 6226878.8549 | 15116649.6688 | [5 empty] | 370976.9746
Royal City | 18 | 2019-03-31 | 2019-03-31 | 2019-04-09 | 34 | 2019-05-13 | 2019-04-18 | 8621924.8043 | 165989063.0174 |  |  | 6196039.396 | 14343940.1395 | [5 empty] | 296046.8071
Royal City | 19 | 2019-04-30 | 2019-04-30 | 2019-05-08 | 34 | 2019-06-11 | 2019-05-23 | 15549148.0486 | 181538211.066 |  |  | 10933183.0202 | 16047073.0222 | [5 empty] | 222365.6932
Royal City | 20 | 2019-05-31 | 2019-05-31 | 2019-06-01 | 34 | 2019-07-05 | 2019-06-26 | 7876990.4815 | 189415201.5475 |  |  | 5643448.8191 | 15380569.1286 | [5 empty] | 176894.1812
Royal City | 21 | 2019-06-30 | 2019-06-30 | 2019-07-08 | 34 | 2019-08-11 | 2019-07-18 | 7532294.3265 | 196947495.8739 |  |  | 5151160.3487 | 17429947.3127 | [5 empty] | 252279.4582
Royal City | 22 | 2019-07-31 | 2019-07-31 | 2019-08-05 | 34 | 2019-09-08 | 2019-09-02 | 24265130.1959 | 221212626.0698 |  |  | 17540056.799 | 24953179.7402 | [5 empty] | 327502.3224
Royal City | 23 | 2019-08-31 | 2019-08-31 | 2019-09-11 |  | 2019-10-18 | 2019-09-28 | 6268692.5562 | 227481318.626 |  |  | 4319851.8787 | 25361645.3681 | [5 empty] | 418117.1746
Royal City | 24 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-24 | 17799666.736 | 245280985.3621 |  |  | 10214838.0645 | 23478699.1038 | [5 empty] | 383536.5601
Royal City | 25 | 2019-10-31 | 2019-10-31 | 2019-11-07 | 34 | 2019-12-11 | 2019-11-27 | 17503083.0268 | 262784068.3888 |  |  | 12249365.624 | 23043660.2023 | [5 empty] | 462163.6487
Royal City | 26 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 10595979.9301 | 273380048.3189 |  |  | 7456675.6367 | 22399832.276 | [5 empty] | 481328.1283
Royal City | 27 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 20586377.6301 | 293966425.9491 |  |  | 14587648.3106 | 19245051.8837 | [5 empty] | 481881.6236
Royal City | 28 | 2020-01-31 | 2020-01-31 | 2020-02-17 | 34 | 2020-03-22 | 2020-03-16 | 15640549.4851 | 309606975.4342 |  |  | 10986396.5553 | 16026544.9251 | [5 empty] | 606431.6143
Royal City | 29 | 2020-02-29 | 2020-02-29 | 2020-03-18 | 34 | 2020-04-21 | 2020-04-05 | 18804604.7977 | 328411580.2319 |  |  | 13166441.5288 | 16972896.7219 | [5 empty] | 637326.7814
Royal City | 30 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 13862319.0142 | 342273899.2462 |  |  | 9831952.135 | 14581690.3962 | [5 empty] | 637621.4818
Royal City | 31 | 2020-04-30 | 2020-04-30 | 2020-05-14 | 34 | 2020-06-17 | 2020-07-02 | 10234077.8776 | 352507977.1238 |  |  | 7550426.1692 | 12931292.2437 | [5 empty] | 0
Royal City | 32 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 3761397.6023 | 356269374.7261 |  |  | 2648440.2256 | 12829313.7893 | [5 empty] | 0
Royal City | 33 | 2020-06-30 | 2020-06-30 | 2020-07-20 | 34 | 2020-08-23 | 2020-08-12 | 13830917.4352 | 370100292.1612 |  |  | 9101413.8171 | 14873462.0847 | [5 empty] | 1198898.3783
Royal City | 34 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-14 | 7811639.6921 | 377911931.8534 |  |  | 5373442.9261 | 13214988.4567 | [5 empty] | 1376502.8422
Royal City | 35 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 3980750.5222 | 381892682.3756 |  |  | 3237336.5863 | 10629015.9927 | [5 empty] | 1052872.9373
Royal City | 36 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 8343396.9284 | 390236079.304 |  |  | 5231425.19 | 10856647.4404 | [5 empty] | 1034872.9373
Royal City | 37 | 2020-10-31 | 2020-10-31 | 2020-11-07 | 34 | 2020-12-11 | 2020-11-26 | 5412454.8663 | 395648534.1703 |  |  | 5574033.5344 | 7933674.7404 | [5 empty] | 998604.3353
Royal City | 38 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 3712322.3219 | 399360856.4923 |  |  | 3838809.8865 | 6223962.4617 | [5 empty] | 944047.2982
Royal City | 39 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 1174176.5076 | 400535032.9999 |  |  | 1002773.1926 | 6288699.0447 | [5 empty] | 899047.2982
Royal City | 40 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 5847326.4556 | 406382359.4555 |  |  | 5979686.6716 | 4784431.8697 | [5 empty] | 823521.4569
Royal City | 41 | 2021-08-31 | 2021-09-01 | 2021-09-19 | 34 | 2021-10-23 | 2021-11-01 | 5256684.0377 | 411639043.4932 |  |  | 5714023.3138 | 3493730 | [5 empty] | 414348.8107
Royal City | 42 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 7571387.8468 | 419210431.34 |  |  | 29397549.59 | 715168.5 | 18621503.12 |  | 45928934.7 |  |  | 225000
Royal City | 43 | 2023-07-31 | 2023-08-08 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 13484961.26 | 432695392.6 |  |  | 13488633.46 |  | 18307280.08 |  | 46946119.05 |  |  | 225000
Royal City - Landscape | 1 | 2019-07-31 | 2019-07-31 | 2019-08-06 | 34 | 2019-09-09 | [5 empty] | 1800000 | [6 empty] | 0
Royal City - Landscape | 2 | 2019-08-31 | 2019-08-31 | 2019-09-11 | 34 | 2019-10-15 | 2019-09-25 |  |  |  |  | 4032037.5 | 2976050 | [5 empty] | 0
Royal City - Landscape | 3 | 2019-09-30 | 2019-09-30 | 2019-10-09 | 34 | 2019-11-12 | 2019-10-23 | 341000 | 341000 |  |  | 2443214.8875 | 3475619.85 | [5 empty] | 0
Royal City - Landscape | 4 | 2019-10-31 | 2019-10-30 | 2019-11-07 | 34 | 2019-12-11 | 2019-12-25 | 2839877.7881 | 3180877.7881 |  |  | 4441415.442 | 4015635.4285 | [5 empty] | 0
Royal City - Landscape | 5 | 2019-11-30 | 2019-11-30 | 2019-12-10 | 34 | 2020-01-13 | 2020-01-05 | 5896802.2265 | 9077680.0146 |  |  | 7147476.0332 | 4953961.135 | [5 empty] | 0
Royal City - Landscape | 6 | 2019-12-31 | 2019-12-31 | 2020-01-13 | 34 | 2020-02-16 | 2020-02-10 | 12932194.6154 | 22009874.63 |  |  | 9619287.67 | 4200873.67 | [5 empty] | 0
Royal City - Landscape | 7 | 2020-01-31 | 2020-01-31 | 2020-02-11 | 34 | 2020-03-16 | 2020-03-16 | 6479189.8549 | 28489064.4849 |  |  | 6246175.7955 | 5725958.7255 | [5 empty] | 0
Royal City - Landscape | 8 | 2020-02-29 | 2020-02-29 | 2020-03-17 | 34 | 2020-04-20 | 2020-04-05 | 17137734.2822 | 45626798.7671 |  |  | 12899186.0747 | 4930252.4954 | [5 empty] | 0
Royal City - Landscape | 9 | 2020-03-31 | 2020-03-31 | 2020-04-09 | 34 | 2020-05-13 | 2020-05-05 | 6296234.5253 | 51923033.2924 |  |  | 4988413.7416 | 4970424.566 | [5 empty] | 0
Royal City - Landscape | 10 | 2020-04-30 | 2020-04-30 | 2020-05-18 | 34 | 2020-06-21 | 2020-07-02 | 3937848.897 | 55860882.1894 |  |  | 3101056.0064 | 4970424.566 | [5 empty] | 0
Royal City - Landscape | 11 | 2020-05-31 | 2020-05-31 | 2020-06-16 | 34 | 2020-07-20 | 2020-07-08 | 5192701.4937 | 61053583.6831 |  |  | 3973857.736 | 4816564.979 | [5 empty] | 0
Royal City - Landscape | 12 | 2020-06-30 | 2020-06-30 | 2020-07-19 | 34 | 2020-08-22 | 2020-08-12 | 8940402.3014 | 69993985.9845 |  |  | 7029456.4155 | 6160052.1105 | [5 empty] | 0
Royal City - Landscape | 13 | 2020-07-31 | 2020-07-31 | 2020-08-16 | 34 | 2020-09-19 | 2020-09-07 | 3598777.1179 | 73592763.1024 |  |  | 2173267.6157 | 4428817.741 | [5 empty] | 0
Royal City - Landscape | 14 | 2020-08-31 | 2020-08-31 | 2020-09-16 | 34 | 2020-10-20 | 2020-10-05 | 2137131.084 | 75729894.1864 |  |  | 1308214.7555 | 3929116.4435 | [5 empty] | 0
Royal City - Landscape | 15 | 2020-09-30 | 2020-09-30 | 2020-10-11 | 34 | 2020-11-14 | 2020-10-28 | 3135305.5981 | 78865199.7846 |  |  | 2272705.37 | 3708912.5587 | [5 empty] | 0
Royal City - Landscape | 16 | 2020-10-31 | 2020-10-31 | 2020-11-09 | 34 | 2020-12-13 | 2020-11-26 | 1582061.2622 | 80447261.0467 |  |  | 853478.48 | 3206907.765 | [5 empty] | 0
Royal City - Landscape | 17 | 2020-11-30 | 2020-11-30 | 2020-12-14 | 34 | 2021-01-17 | 2021-01-05 | 3716309.8261 | 84163570.8728 |  |  | 2058324.55 | 1876563.015 | [5 empty] | 45000
Royal City - Landscape | 18 | 2020-12-31 | 2020-12-31 | 2021-01-13 | 34 | 2021-02-16 | 2021-02-03 | 1163660.8736 | 85327231.7464 |  |  | 819297.0816 | 1969454.449 | [5 empty] | 0
Royal City - Landscape | 19 | 2021-01-31 | 2021-01-31 | 2021-02-09 | 34 | 2021-03-15 | 2021-03-02 | 2029657.8338 | 87356889.5802 |  |  | 1116339.8935 | 1814848.008 | [5 empty] | 60000
Royal City - Landscape | 20 | 2021-02-28 | 2021-02-28 | 2021-03-09 | 34 | 2021-04-12 | 2021-04-12 | 1366613.9629 | 88723503.543 |  |  | 1105876.6944 | 1854405.6062 | [5 empty] | 60000
Royal City - Landscape | 21 | 2021-05-31 | 2021-05-31 | 2021-06-13 | 34 | 2021-07-17 | 2021-07-13 | 4112536.457 | 92836040 |  |  | 3011690.98 | 1631829.995 | [5 empty] | 120000
Royal City - Landscape | 22 | 2021-08-31 | 2021-09-01 | 2021-09-14 | 34 | 2021-10-18 | 2021-11-01 | 3299640.8 | 96135680.8 |  |  | 2526109.9 | 1159231.18 | [5 empty] | 165000
Royal City - Landscape | 23 | 2022-12-31 | 2023-01-10 | 2023-02-11 | 34 | 2023-03-17 | 2023-02-13 | 10826725.43 | 106962406.23 |  |  | 15313915.32 | [6 empty] | 165000
Royal City - Landscape | 24 | 2023-06-30 | 2023-07-11 | 2023-08-20 | 34 | 2023-09-23 | 2023-09-04 | 3256136.08 | 110218542.31 |  |  | 3247942.88 | [6 empty] | 0
Saint Gobain Factory - DP | 1 | 2024-09-30 | 2024-09-25 | 2024-09-25 | 28 | 2024-10-23 | [12 empty] | 0
SIEMENS - Sokhna | 1 | 2017-11-30 | 2017-11-30 | 2017-11-29 | 45 | 2018-01-13 | 2017-12-06 |  |  |  |  | 93300000 | [6 empty] | 0
SIEMENS - Sokhna | 2 | 2017-12-31 | 2017-12-25 | 2018-01-16 | 45 | 2018-03-02 | 2018-01-16 | 4401847.1 | 4401847.1 |  |  | 3059283.73 | 0 | [5 empty] | 0
SIEMENS - Sokhna | 3 | 2018-01-31 | 2018-02-03 | 2018-02-05 | 45 | 2018-03-22 | 2018-02-05 | 10401972.73 | 14803819.83 |  |  | 7201577.05 | 0 | [5 empty] | 27794
SIEMENS - Sokhna | 4 | 2018-02-28 | 2018-03-04 | 2018-03-05 | 45 | 2018-04-19 | 2018-03-14 | 15960664.31 | 30764484.14 |  |  | 11065687.7 | 0 | [5 empty] | 54768
SIEMENS - Sokhna | 5 | 2018-03-31 | 2018-04-08 | 2018-04-10 | 45 | 2018-05-25 | 2018-04-15 | 19051976.33 | 49816460.47 |  |  | 13218163.55 | 0 | [5 empty] | 77728
SIEMENS - Sokhna | 6 | 2018-04-30 | 2018-05-03 | 2018-05-07 | 45 | 2018-06-21 | 2018-05-20 | 10481549.5128 | 60298009.9828 |  |  | 7060448.908 | 0 | [5 empty] | 301956
SIEMENS - Sokhna | 7 | 2018-05-31 | 2018-06-06 | 2018-06-14 | 45 | 2018-07-29 | 2018-07-04 | 12587450.0972 | 72885460.08 |  |  | 8833159.82 | 0 | [5 empty] | 217074
SIEMENS - Sokhna | 8 | 2018-06-30 | 2018-07-05 | 2018-06-28 | 45 | 2018-08-12 | 2018-07-19 | 18208993.38 | 91094453.46 |  |  | 12641621.4 | 0 | [5 empty] | 230703
SIEMENS - Sokhna | 9 | 2018-07-31 | 2018-08-01 | 2018-08-05 | 45 | 2018-09-19 | 2018-09-03 | 19922320.61 | 111016774.07 |  |  | 13673026.82 | 0 | [5 empty] | 403689
SIEMENS - Sokhna | 10 | 2018-08-31 | 2018-09-06 | 2018-09-17 | 45 | 2018-11-01 | 2018-09-25 | 9128690.32 | 120145464.39 |  |  | 6271528.33 | 0 | [5 empty] | 430957
SIEMENS - Sokhna | 11 | 2018-09-30 | 2018-09-30 | 2018-10-01 | 45 | 2018-11-15 | 2018-11-05 | 7601906.76 | 127747371.15 |  |  | 5230123.66 | 0 | [5 empty] | 446149
SIEMENS - Sokhna | 12 | 2018-10-31 | 2018-10-28 | 2018-10-28 | 45 | 2018-12-12 | 2018-11-07 | 28930012.4 | 156677383.55 |  |  | 20041232.56 | [6 empty] | 366625
SIEMENS - Sokhna | 13 | 2018-11-30 | 2018-11-22 | 2018-11-22 | 45 | 2019-01-06 | 2018-11-27 | 25830140.07 | 182507523.62 |  |  | 17822796.65 | [6 empty] | 366625
SIEMENS - Sokhna | 14 | 2018-12-31 | 2018-12-09 | 2018-12-19 | 45 | 2019-02-02 | 2019-02-05 | 28983532 | 211491055.62 |  |  | 20002003.08 | [6 empty] | 363259
SIEMENS - Sokhna | 15 | 2018-12-31 | 2018-12-27 | 2019-01-05 | 45 | 2019-02-19 | 2019-02-05 | 10573229.89 | 222064285.51 |  |  | 2699428.63 | [6 empty] | 4959359
SIEMENS - Sokhna | 16 | 2018-12-31 | 2018-12-30 | 2019-01-15 | 45 | 2019-03-01 | 2019-01-23 | 32022484.92 | 254086770.43 |  |  | 25271545.73 | [6 empty] | 4959359
SIEMENS - Sokhna | 17 | 2019-02-28 | 2019-02-21 | 2019-01-31 | 45 | 2019-03-17 | 2019-04-22 | 57817326.87 | 311904097.3 |  |  | 20418831.59 | [6 empty] | 26029681
SIEMENS - Sokhna | 18 | 2019-07-31 | 2019-08-07 | 2019-08-20 | 45 | 2019-10-04 | 2019-10-02 | 11495973.02 | 323400070.32 |  |  | 12124718 | [6 empty] | 20785977
SIEMENS - Sokhna | 19 | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 | [12 empty] | 0
SIEMENS - Sokhna | 20 | 2019-10-31 | 2019-10-30 | 2020-01-16 | 45 | 2020-03-01 | 2023-10-25 | [11 empty] | 0
SIEMENS - Sokhna | 21 | 2020-07-31 | 2020-07-15 | 2020-07-15 | 45 | 2020-08-29 | [12 empty] | 0
SMP1 - Revamp | 1 | 2022-12-31 | 2023-01-02 | 2023-01-04 | 42 | 2023-02-15 | 2023-02-02 | 3199345.21 | 3199345.21 |  |  | 2399508.91 | [6 empty] | 0
SMP1 - Revamp | 2 | 2023-01-31 | 2023-02-14 | 2023-02-15 | 42 | 2023-03-29 | 2023-05-02 | 1797569.47 | 4996914.68 |  |  | 1348177.1 | [6 empty] | 0
SMP1 - Revamp | 3 | 2023-04-30 | 2023-05-03 | 2023-05-24 | 42 | 2023-07-05 |  | 2879525.92 | 7876440.6 |  |  | 2159644.45 | [6 empty] | 0
SMP1 - Revamp | 4 | 2023-05-31 | 2023-06-06 | 2023-07-13 | 42 | 2023-08-24 | 2023-09-01 | 3836789.63 | 11713230.23 |  |  | 2877592.22 | [6 empty] | 0
SMP1 - Revamp | 5 | 2023-07-31 | 2023-07-25 | 2023-07-25 | 42 | 2023-09-05 | 2023-09-12 | 4135898.1 | 15849128.33 |  |  | 3101923.57 | [6 empty] | 0
SMP1 - Revamp | 6 | 2023-08-31 | 2023-08-30 | 2023-09-06 | 42 | 2023-10-18 | 2023-10-10 | 8858061.69 | 24707190.02 |  |  | 6643546.26 | [6 empty] | 0
SMP1 - Revamp | 7 | 2023-10-31 | 2023-10-15 | 2023-10-15 | 42 | 2023-11-26 | 2023-11-21 | 4571797.25 | 29278987.27 |  |  | 3428847.94 | [6 empty] | 0
SMP1 - Revamp | 8 | 2023-12-31 | 2023-12-06 | 2023-12-06 | 42 | 2024-01-17 | 2024-01-15 | 2887080.34 | 32166067.61 |  |  | 2165310.25 | [6 empty] | 0
SMP1 - Revamp | 9 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-28 | 1572976.38 | 33739043.99 |  |  | 1179732.3 | [6 empty] | 0
SMP1 - Revamp | 10 | 2024-05-31 | 2024-05-19 | 2024-05-19 | 42 | 2024-06-30 | 2024-06-04 | 5011477.79 | 38750521.78 |  |  | 3758608.34 | [6 empty] | 0
SMP1 - Shut Down | 1 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2023-10-18 | 15192302.49 | 15192302.49 |  |  | 8203843.34 | [6 empty] | 0
SMP1 - Shut Down | 2 | 2023-09-30 | 2023-10-04 | 2023-10-18 | 42 | 2023-11-29 | 2024-04-07 | 17650842.77 | 32843145.26 |  |  | 9531455.1 | [6 empty] | 0
SMP1 - Shut Down | 3 | 2024-05-31 | 2024-05-25 | 2024-04-24 | 42 | 2024-06-05 | [12 empty] | 0
SMP2 - Shut Down | 2 | 2023-12-31 | 2023-12-09 | 2023-12-09 | 42 | 2024-01-20 | 2024-01-07 | 17053490.95 | 49896636.21 |  |  | 5979888.32 | [6 empty] | 0
SMP2 - Shut Down | 3 | 2024-02-29 | 2024-02-27 | 2024-02-27 | 42 | 2024-04-09 | 2024-04-07 | 1490218.79 | 51386855 |  |  | 804718.15 | [6 empty] | 0
Sodic Club House | 23 | 2017-09-30 | 2017-09-19 | 2017-11-01 | 35 | 2017-12-06 | 2017-11-05 | 10526350.27 | 55308912.13 |  |  | 2727407.23 | 10641245.16 | [5 empty] | 83598.95
Sodic Club House | 24 | 2017-10-31 | 2017-11-01 | 2017-11-03 | 35 | 2017-12-08 | 2017-12-17 | 6326663.77 | 61635575.9 |  |  | 4528572.66 | 10347994.62 | [5 empty] | 33598.95
Sodic Club House | 25 | 2017-11-30 | 2017-12-01 | 2017-12-10 | 35 | 2018-01-14 | 2018-01-24 | 3617825.39 | 65253401.29 |  |  | 894280.74 | 8215432.94 | [5 empty] | 33598.95
Sodic Club House | 26 | 2017-12-31 | 2018-01-16 | 2018-01-16 | 35 | 2018-02-20 | 2018-02-22 | 4263027.4013 | 69516428.6913 |  |  | 2563543.8087 | 7922726.9562 | [5 empty] | 33598.95
Sodic Club House | 27 | 2018-02-28 | 2018-02-20 | 2018-03-01 | 35 | 2018-04-05 | 2018-04-01 | 6447136.9087 | 86100596.85 |  |  | 7171420.74 | 8271503.62 | [5 empty] | 133598.95
Sodic Club House | 28 | 2018-03-31 | 2018-03-20 | 2018-03-20 | 35 | 2018-04-24 | 2018-05-08 | 3235550.4912 | 89336147.3412 |  |  | 3643251.21 | 10814924.0552 | [5 empty] | 133598.95
Sodic Club House | 29 | 2018-04-30 | 2018-04-20 | 2018-04-21 | 35 | 2018-05-26 | 2018-05-17 | 5735280.6088 | 95071427.95 |  |  | 2949189.68 | 13429692.21 | [5 empty] | 133598.95
Sodic Club House | 30 | 2018-05-31 | 2018-05-25 | 2018-05-28 | 35 | 2018-07-02 | 2018-06-26 | 5753955.1349 | 100825383.0849 |  |  | 1501648.1708 | 13579694.3883 | [5 empty] | 39041.91
Sodic Club House | 31 | 2018-06-30 | 2018-07-02 | 2018-07-04 | 35 | 2018-08-08 | 2018-08-02 | 4997405.8346 | 105822788.9195 |  |  | 1752933.23 | 13390603.7948 | [5 empty] | 41801.91
Sodic Club House | 32 | 2018-07-31 | 2018-08-01 | 2018-07-30 | 35 | 2018-09-03 | 2018-09-04 | 7298776.2492 | 113121565.1688 |  |  | 1851323.2394 | 11999237.9332 | [5 empty] | 45521.91
Sodic Club House | 33 | 2018-08-31 | 2018-09-05 | 2018-09-06 | 35 | 2018-10-11 | 2018-10-09 | 6841826.5835 | 119963391.7522 |  |  | 5028067.13 | 12452865.1519 | [5 empty] | 76081.91
Sodic Club House | 34 | 2018-09-30 | 2018-10-15 | 2018-10-15 | 35 | 2018-11-19 | 2018-11-21 | 9547045.4302 | 129510437.1825 |  |  | 1372787.19 | 9699552.55 | [5 empty] | 541161.91
Sodic Club House | 35 | 2018-11-30 | 2018-11-25 | 2018-11-25 | 35 | 2018-12-30 | 2019-12-20 | 17370468.2779 | 146880905.4603 |  |  | 2061960.9553 | 8284813.5766 | [5 empty] | 557361.91
Sodic Club House | 36 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 56 | 2019-08-27 | 2019-12-19 | 15653205.9497 | 162534111.41 |  |  | 3000000 | [6 empty] | 4804784.65
Sodic Club House | 37 | 2020-08-31 | 2020-08-11 | 2020-08-11 | 56 | 2020-10-06 | [12 empty] | 0
Sodic Eastown | 1 | 2019-03-31 | 2019-03-17 | 2019-03-17 | 42 | 2019-04-28 | 2019-03-20 | 9063098.3369 | 9063098.3369 | 122000000 | 10000000 | 6785088.5699 | [6 empty] | 0
Sodic Eastown | 2 | 2019-04-30 | 2019-04-20 | 2019-04-16 | 42 | 2019-05-28 | 2019-04-18 | 20887437.3108 | 29950535.6476 | 5928168 |  | 15652355.21 | [6 empty] | 0
Sodic Eastown | 3 | 2019-05-31 | 2019-05-20 | 2019-05-19 | 42 | 2019-06-30 | 2019-05-23 | 2101069.4381 | 32051605.0857 |  |  | 1574016.17 | [6 empty] | 0
Sodic Eastown | 4 | 2019-06-30 | 2019-06-25 | 2019-06-23 | 42 | 2019-08-04 | 2019-07-08 | 22270031.4 | 54321636.4857 |  |  | 26267292.44 | [6 empty] | 0
Sodic Eastown | 5 | 2019-07-31 | 2019-07-25 | 2019-07-25 | 42 | 2019-09-05 | 2019-08-01 | 45005158.6118 | 99326795.0975 |  |  | 22056568.4027 | 20344137.6 | [5 empty] | 144395.63
Sodic Eastown | 6 | 2019-08-31 | 2019-08-25 | 2019-08-19 | 42 | 2019-09-30 | 2019-09-08 | 38734277.1501 | 138061072.2476 |  |  | 28554847.68 | 20344137.6 | [5 empty] | 607331.68
Sodic Eastown | 7 | 2019-09-30 | 2019-09-25 | 2019-09-16 | 42 | 2019-10-28 | 2019-11-03 | 65627417.1905 | 203688489.4381 |  |  |  | 5537718 | [5 empty] | 921272.68
Sodic Eastown | 8 | 2019-10-31 | 2019-10-30 | 2019-11-02 | 42 | 2019-12-14 | 2019-11-14 | 85059782.1524 | 288748271.5905 |  |  | 58794871.95 | 1266429.46 | [5 empty] | 707331.68
Sodic Eastown | 9 | 2019-11-30 | 2019-11-30 | 2019-12-03 | 42 | 2020-01-14 | 2019-12-30 | 16046909.9143 | 304795181.5048 |  |  | 40504812.26 | 39767000.8 | [5 empty] | 2750976.18
Sodic Eastown | 10 | 2019-12-31 | 2019-12-31 | 2020-01-07 | 42 | 2020-02-18 | 2020-01-20 | 82638241.0762 | 387433422.581 |  |  | 32553581.24 | 1e-06 | [5 empty] | 3038523.68
Sodic Eastown | 11 | 2020-01-31 | 2020-01-31 | 2020-02-03 | 42 | 2020-03-16 | 2020-02-19 | 36710088.5775 | 424143511.1584 |  |  | 27179529.3929 | [6 empty] | 3038523.68
Sodic Eastown | 12 | 2020-02-29 | 2020-02-29 | 2020-03-04 | 42 | 2020-04-15 | 2020-03-29 | 26833421.413 | 450976932.5714 |  |  | 19553108.77 | [6 empty] | 3314791.44
Sodic Eastown | 13 | 2020-03-31 | 2020-03-24 | 2020-03-25 | 42 | 2020-05-06 | 2020-05-17 | 22228765.6121 | 473205698.1835 |  |  | 16201534.04 | [6 empty] | 2704423.44
Sodic Eastown | 14 | 2020-04-30 | 2020-05-07 | 2020-05-10 | 42 | 2020-06-21 | 2020-06-15 | 24418089.9689 | 497623788.1524 |  |  | 16537461.58 | [6 empty] | 3495935.44
Sodic Eastown | 15 | 2020-05-31 | 2020-06-02 | 2020-06-06 | 42 | 2020-07-18 | 2020-06-23 | 19101976.1176 | 516725764.27 |  |  | 12895953.9558 | [6 empty] | 4174771.13
Sodic Eastown | 16 | 2020-06-30 | 2020-06-30 | 2020-07-04 | 42 | 2020-08-15 | 2020-08-10 | 42785902.7013 | 559511666.9713 |  |  | 30145771.5315 | [6 empty] | 4707294.52
Sodic Eastown | 17 | 2020-07-31 | 2020-08-08 | 2020-08-10 | 42 | 2020-09-21 | 2020-09-07 | 30425304.0673 | 589936971.0386 |  |  | 20899381.3823 | [6 empty] | 5466992.46
Sodic Eastown | 18 | 2020-08-31 | 2020-08-31 | 2020-09-03 | 42 | 2020-10-15 | 2020-10-11 | 36663335.5424 | 626600306.581 |  |  | 22406610.78 | [6 empty] | 5860427.46
Sodic Eastown | 19 | 2020-09-30 | 2020-10-01 | 2020-10-04 | 42 | 2020-11-15 | 2020-11-15 | 48818243.381 | 675418549.9619 |  |  | 34417592.72 | [6 empty] | 0
Sodic Eastown | 20 | 2020-10-31 | 2020-10-31 | 2020-11-03 | 42 | 2020-12-15 | 2020-12-14 | 81649174.4522 | 757067724.4141 |  |  | 31197031.7827 | [6 empty] | 6575145.76
Sodic Eastown | 21 | 2020-11-30 | 2020-11-30 | 2020-12-03 | 42 | 2021-01-14 | 2021-01-20 | 8971634.0811 | 766039358.4952 |  |  | 29743783.27 | [6 empty] | 7317323.76
Sodic Eastown | 22 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 42 | 2021-02-16 | 2021-02-09 | 29539477.0571 | 795578835.5524 |  |  | 19964135.7 | [6 empty] | 7664787.88
Sodic Eastown | 23 | 2021-01-31 | 2021-01-31 | 2021-02-04 | 42 | 2021-03-18 | 2021-03-04 | 23832998.7215 | 819411834.2738 |  |  | 19672746.6443 | [6 empty] | 8075062.48
Sodic Eastown | 24 | 2021-02-28 | 2021-02-28 | 2021-03-07 | 42 | 2021-04-18 | 2021-04-11 | 24555503.3928 | 843967337.6667 |  |  | 14713744.16 | [6 empty] | 8705062.48
Sodic Eastown | 25 | 2021-03-31 | 2021-03-31 | 2021-04-05 | 42 | 2021-05-17 | 2021-05-18 | 29789861.881 | 873757199.5477 |  |  | 18632387.0541 | [6 empty] | 9572854.12
Sodic Eastown | 26 | 2021-04-30 | 2021-04-30 | 2021-05-05 | 42 | 2021-06-16 | 2021-06-17 | 45459659.9094 | 919216859.4571 |  |  | 32407888.61 | [6 empty] | 9252854.12
Sodic Eastown | 27 | 2021-05-31 | 2021-05-31 | 2021-06-07 | 42 | 2021-07-19 | 2021-07-11 | 30032935.1619 | 949249794.619 |  |  | 21101612.82 | [6 empty] | 8752562.48
Sodic Eastown | 28 | 2021-06-30 | 2021-06-30 | 2021-07-07 | 42 | 2021-08-18 | 2021-08-09 | 37125243.7619 | 986375038.381 |  |  | 41708616.23 | [6 empty] | 11397821.25
Sodic Eastown | 29 | 2021-07-31 | 2021-07-24 | 2021-08-07 | 42 | 2021-09-18 | 2021-09-06 | 26258236.2286 | 1012633274.6095 |  |  | 10880905.48 | [6 empty] | 0
Sodic Eastown | 30 | 2021-08-31 | 2021-08-31 | 2021-09-07 | 42 | 2021-10-19 | 2021-10-17 | 27535188.381 | 1040168462.9905 |  |  | 25479297.36 | [6 empty] | 0
Sodic Eastown | 31 | 2021-09-30 | 2021-09-30 | 2021-10-10 | 42 | 2021-11-21 | 2021-11-14 | 20856328.3905 | 1061024791.381 |  |  | 22493923.51 | [6 empty] | 9824319.61
Sodic Eastown | 32 | 2021-10-31 | 2021-10-31 | 2021-11-08 | 42 | 2021-12-20 | 2021-12-07 | 17472419.8762 | 1078497211.2571 |  |  | 15680621.74 | [6 empty] | 9524319.61
Sodic Eastown | 33 | 2021-11-30 | 2021-11-30 | 2021-12-07 | 42 | 2022-01-18 | 2021-12-14 | 15003172.5524 | 1093500383.8095 |  |  | 19311419.98 | [6 empty] | 10022759.48
Sodic Eastown | 34 | 2021-12-31 | 2021-12-31 | 2021-12-27 | 42 | 2022-02-07 | 2022-03-10 | 4991381.7048 | 1098491765.5143 |  |  | 4602037.62 | [6 empty] | 0
Sodic Eastown | 35 | 2022-04-30 | 2022-04-30 | 2022-05-18 | 42 | 2022-06-29 | 2022-06-14 | 46695355.6476 | 1145187121.1619 |  |  | 12555805.27 |  | 110343302 |  | -4596809 | 30061161 | 30061161 | 28213034
Sodic Eastown | 36 | 2022-07-31 | 2022-08-13 | 2022-08-15 | 42 | 2022-09-26 | 2022-09-12 | -0.0001 | 1145187121.1619 |  |  | 3904269.49 |  | 110343302.03 |  | -2378666.59 | 30061161.93 | 30061161.93 | 32117303
Sodic Eastown | 37 | 2022-12-31 | 2022-12-26 | 2023-01-01 | 42 | 2023-02-12 | 2023-01-22 | -1e-05 | 1145187121.1619 |  |  | 5035428.4 |  | 110343302.03 |  | -2378666.59 | 18874299.6215 | 18874299.6215 | 19273337.4308
Sodic Eastown | 38 | 2022-06-30 | 2022-06-12 | 2023-06-22 | 42 | 2023-08-03 | 2023-08-01 | -0.00011 | 1145187121.1619 |  |  | 2231188.43 | [6 empty] | 0
Sodic Eastown | 39 | 2023-06-30 | 2023-06-30 | 2023-10-22 | 42 | 2023-12-03 | 2023-10-29 |  | 1145187121.1619 |  |  | 28315194.9811 |  | 110343302.92 |  | -4596809.26 | 30061161.9302 | 30061161.9302 | -12704609.7849
Sodic Eastown - Landscape | 1 | 2021-12-31 | 2021-12-31 | 2022-01-09 | 42 | 2022-02-20 | 2022-02-14 | 1310241.4095 | 1310241.4095 |  |  | 1545976.52 | 710231.1 | [5 empty] | 0
Sodic Eastown - Landscape | 2 | 2022-01-31 | 2022-01-31 | 2022-02-03 | 42 | 2022-03-17 | 2022-03-10 | 3185965.6857 | 4496207.0952 |  |  | 2689319.17 | 1064088.68 | [5 empty] | 0
Sodic Eastown - Landscape | 3 | 2022-03-31 | 2022-03-15 | 2022-03-17 | 42 | 2022-04-28 | 2022-03-31 | 5417455.381 | 9913662.4762 |  |  | 8060960.68 | [6 empty] | 0
Sodic Eastown - Landscape | 4 | 2022-04-30 | 2022-04-13 | 2022-04-13 | 42 | 2022-05-25 | 2022-04-14 | 1923818.4 | 11837480.8762 |  |  | 4237695.69 | 7645419.29 | [5 empty] | 433157
Sodic Eastown - Landscape | 5 | 2022-04-30 | 2022-05-10 | 2022-05-11 | 42 | 2022-06-22 | 2022-05-11 | 8146275.9524 | 19983756.8286 |  |  | 2847434.08 | 4687295.11 | 494379.4 |  |  | 641755.99 | 641755.99 | 477225
Sodic Eastown - Landscape | 6 | 2022-05-31 | 2022-05-17 | 2022-05-22 | 42 | 2022-07-03 | 2022-05-24 | 2241713.4381 | 22225470.2667 |  |  | 1865468.85 | 4887618.75 | 704722.2 |  |  | 705609.06 | 705609.06 | 477225
Sodic Eastown - Landscape | 7 | 2022-05-31 | 2022-06-10 | 2022-06-14 | 42 | 2022-07-26 | [12 empty] | 0
Sodic Eastown - Landscape | 8 | 2022-06-30 | 2022-06-26 | 2022-07-03 | 42 | 2022-08-14 | 2022-07-27 | 19106378.3905 | 46943391.219 |  |  | 13407927.22 | 2302349.81 | 17134472.44 |  |  | 1289822.765 | 1289822.765 | 380000
Sodic Eastown - Landscape | 9 | 2022-08-31 | 2022-08-25 | 2022-08-30 | 42 | 2022-10-11 | 2022-09-13 | 2763176 | 49706567.219 |  |  | 837296.04 |  | 17105387 |  |  | 1304797 | 1304797 | 489137
Sodic Eastown - Landscape | 10 | 2022-08-31 | 2022-08-28 | 2022-10-19 | 42 | 2022-11-30 | 2022-10-20 | 3106667.3429 | 52813234.5619 |  |  | 2965080.9889 | [6 empty] | 0
Sodic Eastown - Landscape | 11 | 2022-09-30 | 2022-09-28 | 2022-11-05 | 42 | 2022-12-17 | 2022-11-15 | 2478048.6476 | 53908426.4 |  |  | 970278.46 |  | 20753354 |  |  |  |  | 581609
Sodic Eastown - Landscape | 12 | 2022-10-31 | 2022-10-28 | 2022-11-15 | 42 | 2022-12-27 | 2022-11-22 | 2146120.2476 | 56054546.6476 |  |  | 2038310.82 |  | 23518667 |  |  | 1471431.85 | 1471431.85 | 591609
Sodic Eastown - Landscape | 13 | 2023-05-31 | 2023-06-01 | 2023-10-16 | 42 | 2023-11-27 | [12 empty] | 0
Sokhna Port Expansion | 1 | 2022-01-31 | 2022-01-31 | 2022-03-14 | 53 | 2022-05-06 | 2022-03-24 | 28642092.8 | 28642092.8 |  |  | 16602157.8 | [6 empty] | 0
Sokhna Port Expansion | 2 | 2022-02-28 | 2022-02-28 | 2022-03-31 | 53 | 2022-05-23 | 2022-04-17 | 30329196.74 | 58971289.54 |  |  | 19713977.881 | [6 empty] | 0
Sokhna Port Expansion | 3 | 2022-03-31 | 2022-03-31 | 2022-04-14 | 53 | 2022-06-06 | [12 empty] | 0
Sokhna Port Expansion | 4 | 2022-04-30 | 2022-04-30 | 2022-05-25 | 53 | 2022-07-17 | 2022-07-31 | 26384347.91 | 174022377.11 |  |  | 16604871.85 | [6 empty] | 0
Sokhna Port Expansion | 5 | 2022-06-30 | 2022-06-30 | 2022-07-28 | 53 | 2022-09-19 | 2022-09-30 | 90184360.23 | 264206737.34 |  |  | 58619834.1495 | [6 empty] | 0
Sokhna Port Expansion | 6 | 2022-07-31 | 2022-07-31 | 2022-09-19 | 53 | 2022-11-11 | 2022-10-19 | 41088510.15 | 305295247.49 |  |  | 26707531.5975 | [6 empty] | 0
Sokhna Port Expansion | 7 | 2022-08-31 | 2022-08-31 | 2022-10-23 | 53 | 2022-12-15 | [12 empty] | 0
Sokhna Port Expansion | 8 | 2022-09-30 | 2022-09-30 | 2022-11-16 | 53 | 2023-01-08 | 2022-12-20 | 55834648.2 | 418825805.92 |  |  | 36284090.45 | [6 empty] | 0
Sokhna Port Expansion | 9 | 2022-10-31 | 2022-10-31 | 2022-12-15 | 53 | 2023-02-06 | 2023-01-02 | 46210885.16 | 465036691.08 |  |  | 30030028.45 | [6 empty] | 0
Sokhna Port Expansion | 10 | 2022-11-30 | 2022-11-30 | 2023-01-08 | 53 | 2023-03-02 | 2023-01-24 | 42258919.66 | 507295610.74 |  |  | 27468297.779 | [6 empty] | 0
Sokhna Port Expansion | 11 | 2022-12-31 | 2022-12-31 | 2023-01-25 | 53 | 2023-03-19 | 2023-07-05 | 69343976.76 | 576639587.5 |  |  | 50769799.2 | [6 empty] | 0
Sokhna Port Expansion | 12 | 2023-01-31 | 2023-01-31 | 2023-02-13 | 53 | 2023-04-07 | 2023-07-05 | 106701066.13 | 683340653.63 |  |  | 70395885.55 | [6 empty] | 0
Sokhna Port Expansion | 13 | 2023-02-28 | 2023-02-28 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 41939163.73 | 725279817.36 |  |  | 27260456.4245 | [6 empty] | 0
Sokhna Port Expansion | 14 | 2023-03-31 | 2023-03-31 | 2023-06-01 | 53 | 2023-07-24 | 2023-06-18 | 18010876.44 | 743290693.8 |  |  | 11707069.686 | [6 empty] | 0
Sokhna Port Expansion | 15 | 2023-04-30 | 2023-04-30 | 2023-07-01 | 53 | 2023-08-23 | 2023-07-15 | 15185688.98 | 758476382.78 |  |  | 9870697.837 | [6 empty] | 0
Sokhna Port Expansion | 16 | 2023-05-31 | 2023-05-31 | 2023-08-07 | 53 | 2023-09-29 | 2023-08-07 | 37404208.29 | 795880591.07 |  |  | 24312735.3885 | [6 empty] | 0
Sokhna Port Expansion | 17 | 2023-06-30 | 2023-06-30 | 2023-08-27 | 53 | 2023-10-19 | 2023-08-27 | 22411649.53 | 818292240.6 |  |  | 14567572.1945 | [6 empty] | 0
Sokhna Port Expansion | 18 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 53 | 2023-09-22 | [12 empty] | 0
Sokhna Port Expansion | 19 | 2023-08-31 | 2023-08-31 | 2023-08-31 | 53 | 2023-10-23 | 2023-10-17 | 15685272.2 | 856365557.7 |  |  | 10195426.93 | [6 empty] | 0
Sokhna Port Expansion | 20 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 53 | 2023-12-17 | 2023-11-20 | 20920498.28 | 877286055.98 |  |  | 13598323.882 | [6 empty] | 0
Sokhna Port Expansion | 21 | 2023-10-31 | 2023-10-31 | 2023-12-27 | 53 | 2024-02-18 | 2023-12-27 | 9034186.8 | 886320242.78 |  |  | 5872221.42 | [6 empty] | 0
Sokhna Port Expansion | 22 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 53 | 2024-04-05 | 2024-02-05 | 3862923.74 | 890183166.52 |  |  | 2510900.431 | [6 empty] | 0
Sokhna Port Expansion | 23 | 2023-12-31 | 2023-12-31 | 2024-03-09 | 53 | 2024-05-01 | 2024-02-25 | 943826.94 | 891126993.46 |  |  | 613487.511 | [6 empty] | 0
Sokhna Port Expansion- 100m | 1 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 60 | 2023-04-29 | [12 empty] | 0
Sokhna Port Expansion- 100m | 2 | 2023-03-31 | 2023-03-31 | 2023-07-01 | 60 | 2023-08-30 | 2023-07-01 | 24129951.39 | 82118084.22 |  |  | 15684468.4035 | [6 empty] | 0
Sokhna Port Expansion- 100m | 3 | 2023-04-30 | 2023-04-30 | 2023-08-07 | 60 | 2023-10-06 | 2023-08-07 | 26794714.09 | 108912798.31 |  |  | 17416564.1585 | [6 empty] | 0
Sokhna Port Expansion- 100m | 4 | 2023-09-30 | 2023-09-30 | 2023-09-07 | 60 | 2023-11-06 | 2023-10-17 | 13246168.7303 | 122158967.0403 |  |  | 8610009.6747 | [6 empty] | 0
Sokhna Port Expansion- 100m | 5 | 2023-09-30 | 2023-09-30 | 2023-10-25 | 60 | 2023-12-24 | 2023-11-20 | 4703266.4897 | 126862233.53 |  |  | 3057123.2183 | [6 empty] | 0
Sokhna Port Expansion- 100m | 6 | 2023-10-31 | 2023-10-31 | 2023-10-25 | 60 | 2023-12-24 | 2023-12-27 | 29655965.57 | 156518199.1 |  |  | 29655965 | [6 empty] | 0
Sokhna Port Expansion- 100m | 7 | 2023-11-30 | 2023-11-30 | 2024-02-12 | 60 | 2024-04-12 | 2024-02-05 | 4532607.67 | 161050806.77 |  |  | 2946194.9855 | [6 empty] | 0
Sokhna Port Expansion-internal roads | 1 | 2022-07-31 | 2022-07-19 | 2022-10-31 | 60 | 2022-12-30 | [12 empty] | 0
Sokhna Port Expansion-internal roads | 2 | 2022-08-31 | 2022-08-01 | 2022-11-28 | 60 | 2023-01-27 | [12 empty] | 0
Sports Hall - Civil Works | 3 | 2021-01-31 | 2021-01-17 | 2021-01-17 | 60 | 2021-03-18 | [12 empty] | 0
Sports Hall - Civil Works | 4 | 2021-03-31 | 2021-03-17 | 2021-03-18 | 60 | 2021-05-17 | [12 empty] | 0
Sports Hall - Civil Works | 5 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 60 | 2021-07-30 | 2021-09-13 | 47849709.5 | 381426324.58 |  |  | 17108050 | [6 empty] | 0
Sports Hall - Civil Works | 6 | 2021-09-30 | 2021-09-30 | 2021-10-06 | 60 | 2021-12-05 | 2021-11-23 | 51027855.5 | 432454180.08 |  |  | 414030 | [6 empty] | 0
Sports Hall - Civil Works | 7 | 2021-11-30 | 2021-11-30 | 2021-12-14 | 60 | 2022-02-12 | [5 empty] | 12888184 | [6 empty] | 0
Sports Hall - Civil Works | 8 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [12 empty] | 0
Sports Hall - Finishes | 1 | 2021-05-31 | 2021-05-23 | 2021-05-23 | 60 | 2021-07-22 | [12 empty] | 0
Sports Hall - Finishes | 2 | 2021-08-31 | 2021-09-02 | 2021-09-11 | 60 | 2021-11-10 | [12 empty] | 0
Sports Hall - Finishes | 3 | 2021-10-31 | 2021-10-31 | 2021-10-11 | 60 | 2021-12-10 | 2021-11-17 | 91998353.75 | 178494684.93 |  |  | 77278617 | [6 empty] | 0
Sports Hall - Finishes | 4 | 2022-07-31 | 2022-07-31 | 2022-08-09 | 60 | 2022-10-08 | [12 empty] | 0
Sports Hall - Finishes - ADD.01 | 1 | 2021-12-31 | 2021-12-31 | 2022-01-11 | 60 | 2022-03-12 | 2022-02-22 | 9145259 | 9145259 |  |  | 5944418.35 | [6 empty] | 0
Sports Hall - Finishes - ADD.01 | 2 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [12 empty] | 0
Sports Hall - Finishes - Landscape | 1 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [12 empty] | 0
Sports Hall - MEP | 1 | 2022-02-28 | 2022-02-24 | 2022-02-24 | 60 | 2022-04-25 | [12 empty] | 0
Sports Hall - MEP | 2 | 2022-03-31 | 2022-03-31 | 2022-04-10 | 60 | 2022-06-09 | [5 empty] | 13327738 | [6 empty] | 0
Suez Intake & P Stations-ABB apply | 1 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 779997.07 | 779997.07 |  |  | 524786.37 | [6 empty] | 0
Suez Intake & P Stations-ABB apply | 2 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 1514111.97 | 2294109.04 |  |  | 988420.71 | [6 empty] | 0
Suez Intake & P Stations-ABB apply | 3 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 1605876.32 | 3899985.36 |  |  | 1048325 | [6 empty] | 0
Suez Intake & P Stations-ABB apply | 6 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 6098633.64 | 9998619 |  |  | 573225.5 | [6 empty] | 0
Suez Intake & P Stations-ABB supply | 1 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 5874834 | 5874834 |  |  | 5134498.57 | [6 empty] | 0
Suez Intake & P Stations-ABB supply | 2 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 8551701.56 | 14426535.56 |  |  | 7437727.82 | [6 empty] | 0
Suez Intake & P Stations-ABB supply | 3 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 1037578.56 | 15464114.12 |  |  | 814872.96 | [6 empty] | 0
Suez Intake & P Stations-ABB supply | 4 | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 | [12 empty] | 0
Suez Intake & P Stations-ABB supply | 8 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 24332063.94 | 40613282 |  |  | 817934.28 | [6 empty] | 0
Suez Intake & P Stations-SSC apply | 1 | 2023-01-31 | 2023-01-16 | 2023-01-15 | 42 | 2023-02-26 | 2023-01-16 | 1124419.48 | 1124419.48 |  |  | 1102291.62 | [6 empty] | 0
Suez Intake & P Stations-SSC apply | 2 | 2023-02-28 | 2023-02-16 | 2023-03-07 | 42 | 2023-04-18 | 2023-03-09 | 3081346.71 | 4205766.19 |  |  | 3020707.78 | [6 empty] | 0
Suez Intake & P Stations-SSC apply | 3 | 2023-03-31 | 2023-04-11 | 2023-04-11 | 42 | 2023-05-23 | 2023-04-12 | 788338.19 | 4994104.38 |  |  | 772824.19 | [6 empty] | 0
Suez Intake & P Stations-SSC apply | 7 | 2024-02-29 | 2024-02-26 | 2024-02-26 | 42 | 2024-04-08 | 2024-02-27 | 12349144.72 | 17343249.1 |  |  | 6963227.52 | [6 empty] | 0
Suez Intake & P Stations-SSC apply | 8 | 2024-03-31 | 2024-03-31 | 2024-06-05 | 42 | 2024-07-17 | 2024-06-06 | 1924769.3 | 19268018.4 |  |  | 1886891.07 | [6 empty] | 0
Suez Intake & P Stations-SSC supply | 1 | 2022-10-31 | 2022-11-02 | 2022-11-02 | 42 | 2022-12-14 | 2022-11-02 | 10223133.6 | 10223133.6 |  |  | 8726335.42 | [6 empty] | 0
Suez Intake & P Stations-SSC supply | 2 | 2022-11-30 | 2022-11-21 | 2022-11-27 | 42 | 2023-01-08 | 2022-11-27 | 3765789.87 | 13988923.47 |  |  | 3190884.06 | [6 empty] | 0
Suez Intake & P Stations-SSC supply | 3 | 2023-01-31 | 2023-01-16 | 2023-01-16 | 42 | 2023-02-27 | 2023-01-18 | 374122.68 | 14363046.15 |  |  | 283552.06 | [6 empty] | 0
Suez Intake & P Stations-SSC supply | 4 | 2023-04-30 | 2023-05-09 | 2023-05-10 | 42 | 2023-06-21 | [12 empty] | 0
Suez Intake & P Stations-SSC supply | 8 | 2024-02-29 | 2024-02-25 | 2024-02-25 | 42 | 2024-04-07 | 2024-02-27 | 9321912.4 | 24074956.74 |  |  | 1886800.52 | [6 empty] | 0
SVC | 1 | 2024-02-29 | 2024-02-17 | 2024-04-01 | 42 | 2024-05-13 | 2024-04-01 | 3212437.04 | 3212437.04 | 1158731.1 |  | 2377203.41 | [6 empty] | 0
SVC | 2 | 2024-05-31 | 2024-05-25 | 2024-06-12 | 42 | 2024-07-24 | [12 empty] | 0
Uptown PK #53 | 25 | 2017-09-30 | 2017-10-10 | 2017-11-11 | 40 | 2017-12-21 | 2017-11-28 |  | 210168675.9558 |  |  | 12105864.365 | 8286463.8075 | [5 empty] | 1299409.2216
Uptown PK #53 | 26 | 2017-10-31 | 2017-11-10 | 2017-11-28 | 40 | 2018-01-07 | 2017-12-21 | 18341001.0169 | 228815469.9927 |  |  | 13230735.7159 | 6928080.7619 | [5 empty] | 1215618.2216
Uptown PK #53 | 27 | 2017-11-30 | 2017-12-10 | 2017-12-26 | 40 | 2018-02-04 | 2018-01-08 | 11525442.3347 | 240340912.3274 |  |  | 9723398.7945 | 8309746.418 | [5 empty] | 1307409.2216
Uptown PK #53 | 28 | 2017-12-31 | 2018-01-10 | 2018-01-16 | 40 | 2018-02-25 | 2018-02-15 | 13381649.8939 | 253722562.2213 |  |  | 13380241.7057 | 4669320.168 | [5 empty] | 1464327.5816
Uptown PK #53 | 29 | 2018-01-31 | 2018-02-10 | 2018-02-15 | 40 | 2018-03-27 | 2018-03-06 | 17500846.4172 | 271223408.6385 |  |  | 11043112.6231 | 3636537.0679 | [5 empty] | 1444327.5816
Uptown PK #53 | 30 | 2018-02-28 | 2018-03-10 | 2018-03-17 | 40 | 2018-04-26 | 2018-04-04 | 15321007.8734 | 286544416.4997 |  |  | 11437376.0467 | 2782555.8001 | [5 empty] | 3125936.127
Uptown PK #53 | 31 | 2018-03-31 | 2018-04-10 | 2018-04-18 | 40 | 2018-05-28 | 2018-05-20 | 11220346.2103 | 297764762.71 |  |  | 7091661.81 | 1008898.49 | [5 empty] | 4001808.9907
Uptown PK #53 | 32 | 2018-04-30 | 2018-05-10 | 2018-05-17 | 40 | 2018-06-26 | 2018-05-29 | 4916024.5037 | 302680787.2137 |  |  | 2387351.5744 | 878601.9171 | [5 empty] | 4488322.2907
Uptown PK #53 | 33 | 2018-05-31 | 2018-06-15 | 2018-06-24 | 40 | 2018-08-03 | 2018-07-10 | 3312628.1623 | 305993415.376 |  |  | 2709512.38 | 613573.28 | [5 empty] | 4562822.2907
Uptown PK #53 | 34 | 2018-06-30 | 2018-07-10 | 2018-07-17 | 40 | 2018-08-26 | 2018-07-26 | 73574.6923 | 306066990.0683 |  |  | 1431626.0807 | 613573.2833 | [5 empty] | 4285977.9307
Uptown PK #53 | 35 | 2018-07-31 | 2018-08-10 | 2018-08-16 | 40 | 2018-09-25 | 2018-09-12 | 3416261.3696 | 309483251.4379 |  |  | 2488623.0127 | 385285.6486 | [5 empty] | 4958858.9291
Uptown PK #53 | 36 | 2018-08-31 | 2018-09-10 | 2018-09-19 | 40 | 2018-10-29 | 2018-10-20 | 2041348.5871 | 311524600.025 |  |  | 2502552.38 | 359304.445 | [5 empty] | 4948858.9291
Uptown PK #53 | 37 | 2018-09-30 | 2018-10-10 | 2018-10-22 | 40 | 2018-12-01 | 2018-12-16 | 1273110.6827 | 312797710.7077 |  |  | 1753673.2424 | 200543.77 | [5 empty] | 5687765.7473
Uptown PK #53 | 38 | 2019-01-31 | 2019-01-15 | 2019-01-16 | 40 | 2019-02-25 | 2019-02-18 | 747405.6143 | 313545116.322 |  |  | 1048789.58 | 200543.77 | [5 empty] | 6192106.3873
Uptown PK #53 | 39 | 2019-03-31 | 2019-04-10 | 2019-04-11 | 40 | 2019-05-21 | 2019-04-21 | 32300.9957 | 313577417.3177 |  |  | 929614.0301 | 200543.77 | [5 empty] | 5191842.6873
Uptown PK #53 | 40 | 2019-05-31 | 2019-06-15 | 2019-06-18 | 40 | 2019-07-28 | 2019-07-16 | 52815.0023 | 313630232.32 |  |  | 1435222.17 | 200543.77 | [5 empty] | 0
Uptown PK #53 | 41 | 2019-08-31 | 2019-08-15 | 2019-08-20 | 40 | 2019-09-29 | 2019-08-20 | 0 | 313630232.32 |  |  | 4202366.45 | 200543.77 | [5 empty] | 0
Uptown PK #53 | 42 | 2019-12-31 | 2019-12-15 | 2019-12-19 | 40 | 2020-01-28 | 2020-01-26 | 4356349.94 | 317986582.26 |  |  | 1380970.95 | 200543.77 | [5 empty] | 0
Uptown PK #53 | 43 | 2020-02-29 | 2020-02-25 | 2020-03-10 | 40 | 2020-04-19 | 2020-04-15 | 3411373.56 | 321397955.82 |  |  | 3747539.31 | 200543.77 | [5 empty] | 0
Uptown PK #62 | 7 | 2017-09-30 | 2017-09-30 | 2017-10-04 | 40 | 2017-11-13 | 2017-10-18 |  | 18419996.59 |  |  | 1684908.08 | 0 | [5 empty] | 136775.69
Uptown PK #62 | 8 | 2017-10-31 | 2017-10-31 | 2017-11-02 | 40 | 2017-12-12 | 2017-11-14 | 4024169.64 | 22444166.23 |  |  | 2970870.89 | 1403336.04 | [5 empty] | 169833.53
Uptown PK #62 | 9 | 2017-11-30 | 2017-11-30 | 2017-12-04 | 40 | 2018-01-13 | 2017-12-21 | 3353637.028 | 25797803.258 |  |  | 2124952.16 | 1883218.402 | [5 empty] | 193475.95
Uptown PK #62 | 10 | 2017-12-31 | 2017-12-27 | 2017-12-30 | 40 | 2018-02-08 | 2018-01-18 | 3315629.905 | 29113433.163 |  |  | 2207449.91 | 2376274.377 | [5 empty] | 216794.47
Uptown PK #62 | 11 | 2018-01-31 | 2018-01-31 | 2018-02-03 | 40 | 2018-03-15 | 2018-02-15 | 3273536.577 | 32386969.74 |  |  | 1524280.94 | 1872928.9681 | [5 empty] | 233754.86
Uptown PK #62 | 12 | 2018-02-28 | 2018-02-28 | 2018-03-01 | 40 | 2018-04-10 | 2018-03-18 | 2806216.291 | 35193186.031 |  |  | 1565019.15 | 1983635.499 | [5 empty] | 291613.6
Uptown PK #62 | 13 | 2018-03-31 | 2018-03-31 | 2018-04-02 | 40 | 2018-05-12 | 2018-05-08 | 6967775.654 | 42160961.685 |  |  | 2219134.03 | 301154.885 | [5 empty] | 1040317.09
Uptown PK #62 | 14 | 2018-04-30 | 2018-05-08 | 2018-05-08 | 40 | 2018-06-17 | 2018-06-26 | 3891325.445 | 46052287.13 |  |  | 854854.3 | 0 | [5 empty] | 2182913.11
Uptown PK #62 | 15 | 2018-07-31 | 2018-07-24 | 2018-08-14 | 40 | 2018-09-23 | 2018-09-06 | 1266868.51 | 47319155.64 |  |  | 2299870.97 | 0 | [5 empty] | 2396855.11
Uptown PK #62 | 16 | 2018-09-30 | 2018-10-03 | 2018-10-04 | 40 | 2018-11-13 | 2018-11-25 | -245868.22 | 47073287.42 |  |  | 931895.88 | [6 empty] | 1241550.872
Uptown PK #62 | 17 | 2019-03-31 | 2019-03-25 | 2019-03-24 | 40 | 2019-05-03 | 2019-04-11 | 0 | 47073287.42 |  |  | 419078.79 | [6 empty] | 928608.274
Uptown PK #62 | 18 | 2019-09-30 | 2019-10-09 | 2019-10-09 | 40 | 2019-11-18 | 2019-11-03 | 0 | 47073287.42 |  |  | 864260.36 | [6 empty] | 987399.24
Uptown PK #62 | 19 | 2019-12-31 | 2019-12-18 | 2019-12-19 | 40 | 2020-01-28 | 2020-07-19 | 22437 | 47095724.42 |  |  | 1195853.88 | [6 empty] | 990172.52
Wady Halfa | 1 | 2022-11-30 | 2022-11-30 | 2022-12-11 | 30 | 2023-01-10 | 2022-12-18 | 3078932.9 | 3078932.9 |  |  | 33029517.9 | 33200100 | [5 empty] | 0
Wady Halfa | 2 | 2023-01-31 | 2023-01-31 | 2023-02-08 | 30 | 2023-03-10 | 2023-02-14 | 23601516.1 | 26680449 |  |  | 11905091.98 | 18254159 | [5 empty] | 0
Wady Halfa | 3 | 2023-02-28 | 2023-02-28 | 2023-03-16 | 30 | 2023-04-15 | 2023-03-16 | 17962793.18 | 44643242.18 |  |  | 14516628.581 | 4370481.56 | [5 empty] | 0
Wady Halfa | 4 | 2023-03-31 | 2023-04-10 | 2023-04-10 | 30 | 2023-05-10 | 2023-05-08 | 8749053.22 | 53392295.4 |  |  | 3679103.55 | [6 empty] | 0
Wady Halfa | 5 | 2024-03-31 | 2024-03-15 | 2024-03-15 | 30 | 2024-04-14 | [12 empty] | 0
Western Fence | 1 | 2023-10-31 | 2023-10-31 | 2023-10-30 | 42 | 2023-12-11 | 2023-11-02 | 762742.21 | 762742.21 |  |  | 792870.53 | [6 empty] | 0
Zayed Park | 1 | 2019-10-31 | 2019-10-28 | 2019-10-28 | 30 | 2019-11-27 | 2019-11-07 | 191006.802 | 191006.802 |  |  | 505797.14 | 410791.498 | [5 empty] | 0
Zayed Park | 2 | 2019-12-31 | 2019-12-31 | 2020-01-11 | 30 | 2020-02-10 | 2020-09-21 | 842290.974 | 1033297.776 |  |  | 352690.39 | [6 empty] | 0