## Sheet1
Kafr Shokr Client Invoice And Cash In Status (2023.04.30)
Client Invoices
No | Invoice Amount | Cut Off Date | Material Delivery | Invoice Amount Without Material | /Month Invoicing | Without VAT
1 | 40481428 | 2021-02-28 | 2208480 | 38272948 | 38272948 | 36450426.6667
2 | 49130748 | 2021-03-30 | 3852000 | 45278748 | 7005800 | 6672190.4762
3 | 61027023 | 2021-04-30 | 1284000 | 59743023 | 14464275 | 13775500
4 | 79432923 | 2021-05-30 | 1284000 | 78148923 | 18405900 | 17529428.5714
5 | 86977173 | 2021-07-30 | 1284000 | 85693173 | 7544250 | 7185000
6 | 89158473 | 2021-08-30 | 1284000 | 87874473 | 2181300 | 2077428.5714
7 | 115267423 | 2021-12-30 | 0 | 115267423 | 27392950 | 26088523.8095
8 | 116224083 | 2022-01-30 | 0 | 116224083 | 956660 | 911104.7619
9 | 116474215 | 2022-07-30 | 0 | 116474215 | 250132 | 238220.9524
10 | 119316190 | 2022-09-30 | 0 | 119316190 | 2841975 | 2706642.8571
[5 empty] | 119316190 | 113634466.6667
Escalation 1-10 | 0 | withdrawn | 0 | 0 | 0 | 0
|  |  |  | Revised Contract | 124171211 | 118258296.1905
|  |  |  | Remaining | 4855021 | 4623829.5238
|  |  |  | Revised Escalation | 14400000 | 13714285.7143
|  |  |  | Remaining Escalation | 14400000 | 13714285.7143
|  |  |  | Revised Total | 138571211 | 131972581.9048
|  |  |  | Remaining Total | 19255021 | 18338115.2381
|  |  |  | 2020 Invoicing | 18481038 | 17600988.5714
|  |  |  | 2021 Invoicing | 96786385 | 92177509.5238
|  |  |  | 2022 Invoicing | 4048767 | 3855968.5714
|  |  |  | 2023 Invoicing | 0 | 0
Cash In
Month | Invoice No | To Date | Expected | Pay Date Due Date | Due Amount | Remain After Due
2021-05-10 | Invoice 1 | 28845197 |  | 2021-05-10
2021-05-20 | Invoice 2 | 6242742 |  | 2021-05-20
2021-06-20 | Invoice 3 | 8372665 |  | 2021-06-20
2021-08-19 | Invoice 4 | 8190447.9 |  | 2021-08-19
2021-09-09 | Invoice 5 | 5371513.65 |  | 2021-09-09
2021-11-08 | Invoice 6 | 444257 |  | 2021-11-08
2022-05-25 | Invoice 7 | 25823994.7095 |  | 2022-05-25
2022-05-25 | Invoice 8 | 2857611.9905 |  | 2022-05-25
2022-09-30 | Invoice 9 | 678824.25 |  | 2022-09-30
2022-12-25 | Invoice 9 B | 4133066.85 |  | 2022-12-25
2022-12-29 | Invoice 10 | 2390708.7 |  | 2022-12-29
| Return Total | 884808.35
Escalation 1-10 |  |  |  |  | 0
|  | 94235837.4 | 0 |  | 0 | 0
| Invoices Only | 94235837.4 | 0 |  | 0 | 0
Escalation Only
Actual Cash In Vs. Net Amount
Invoicing | VAT (5%) | Without VAT | Prices (15%) | Retention (5%) | Marksup (6.35%) | Material Deduction
119316190 | 5681723.3333 | 113634466.6667 | 0 | 5965809.5 | 7215788.6333 | 7000000
| Net In | 93452868.5333
| Actual Cash In | 94235837.4 |  | Difference | -782968.8667
|  |  |  | Known | 523488.35 | cars/stationary
|  |  |  | Unknown | -1306457.2167
Settlements Log
تسوية رقم | اصل المبلغ | ضمان اعمال | دمغات | اسم الاستقطاع | قيمة الاستقطاع | صافي امر الدفع
Settlement 01 | 34409213.8 | 1626600.3 | 786893.15 | ا ت ص | 327706
without vat | 32770679.8095 |  |  | مهن هندسية | 286501
insurance 2.7% | 884808.3549 |  |  | اتساع | 833.4
without 2.7% | 31885871.4547 |  |  | ? | 138.9
|  |  |  | خصم عدد 3 سيارات | 12000
|  |  |  | تعلية تامينات | 88488.35 | 28756710.3547
Settlement 02 | 7351922
Material Received Vs. Material Deducted
material received | rate | qty | amount |  | remaining deduction
steel rft | 14261.2999 | 1120.98 | 15986632 |  | 8986632
material deducted | rate | qty | amount
steel rft | 14261.2999 | 490.8388 | 7000000
Deductions on Settlements
Invoice no/ Settlement no | Description |  |  | Reason |  | Total Amount
1 |  | تعليه تامينات |  |  |  | 88488.35
4,5,6 |  | خصم سيارات |  |  |  | 266000
from 2 to 10 |  | خصم ادوات مكتبيه |  |  |  | 169000
all |  | unknown difference |  |  |  | 276234.1551
|  | Total Unresolved Financial Settlements |  |  | 711234.1551
Internal Invoices
| Invoice No | Date | Invoicing Cumulative | /Month
| Invoice No 1 | 2020-09-30 | 4988732 | 4988732
| Invoice No 2 | 2020-11-10 | 8442935 | 3454203 |  |  | 4988732
| Invoice No 3 | 2020-11-30 | 11241265 | 2798330
| Invoice No 4 | 2020-12-31 | 18481038 | 7239773
| Invoice No 5 | 2021-01-31 | 26849087.1 | 8368049.1
| Invoice No 6 | 2021-04-30 | 59537298 | 32688210.9 |  |  | 59537298
| Invoice No 7 | 2021-05-30 | 72179423 | 12642125
| Invoice No 8 | 2021-06-30 | 82869173 | 10689750
| Invoice No 9 | 2021-07-30 | 90011123 | 7141950
| Invoice No 10 | 2021-08-30 | 93534273 | 3523150
| Invoice No 11 | 2021-09-30 | 101875273 | 8341000
| Invoice No 12 | 2021-10-30 | 108184007 | 6308734
| Invoice No 13 | 2021-11-30 | 110955687 | 2771680
| Invoice No 16 | 2022-03-30 | 117371883 | 6416196
| Invoice No 17 | 2022-04-30 | 117923643 | 551760
| Invoice No 18 | 2022-05-30 | 118072143 | 148500
| Invoice No 19 | 2022-06-30 | 118368361 | 296218
| Invoice No 20 | 2022-07-30 | 119041726.1667 | 673365.1667
| Invoice No 21 | 2022-08-30 | 120916928.6667 | 1875202.5
| Invoice No 22 | 2022-09-30 | 121440926 | 523997.3333
| Invoice No 22 | 2022-10-30 | 123329711 | 1888785
| Invoice No 23 | 2022-11-30 | 123329711 | 0
123329711
|  |  | Revised BOQ | 123440926
|  |  | Remaining | 111215
Formulas:
No = [Invoice Amount Without Material]