## poc 30.04.2016 (hidden)
Description | Al Oula | Hyper Al Sulaimaniya | New Giza | Maxim mall | Attaka | مول مصر | مراسى تانك الخزان الجديد PKG22 New | نادي سوديك | شرم الشيخ | عمائر اب تاون 53 | New Giza phase 2 | Beni suef | كوبرى الشيخ بن زايد - كوبرى العاصمة | جبل الزيت - GAMISA | PKG62 | محطه كهرباء المستثمرين بالقطامي | لوك اند لوت كوبرى الغرابلى - الاس | Total | Trial Balance
Total Contract Price | 33000000 | 65143328.03 | 162482670 | 57304000 | 149999784 | 186777525 | 16510059.28 | 34207969 | 15492289.89 | 288918027 | 144891598 | 35402400 | 103000000 | 116000000 | 37657920 | 128555539.3586 | 3312000 | 1578655109.5586
Additions (Deductions) | 27627323 | 32038401 | 13311632.41 | 42269205 | 36874316 | -28777525 | 0 | 32427521 | 19181531 | 0 | 0 | 387328262 | 0 | 0 |  |  |  | 562280666.41
Total Contracts | 60627323 | 97181729.03 | 175794302.41 | 99573205 | 186874100 | 158000000 | 16510059.28 | 66635490 | 34673820.89 | 288918027 | 144891598 | 422730662 | 103000000 | 116000000 | 37657920 | 128555539.3586 | 3312000 | 2140935775.9686
Total Estemated Cost Of contract | 30000000 | 63597605.6317 | 157051086 | 55087640 | 110000000 | 173629627.0825 | 15612624.567 | 33484323 | 13982628 | 266252587.5225 | 137108129 | 31526907 | 95465467 | 105254776 | 34313058 | 114041436.621 | 2544000 | 1438951895.4247
Additional Cost ( Deductions) | 20000000 | 28402394 | 21966159.5327 | 40002022.5306 | 84096.5 | -26751778.2673 | 0 | 29184769 | 17312367.2709 | 0 | 0 | 347021779.1336 | 0 | 0 |  |  |  | 477221809.7006
Total Cost | 50000000 | 91999999.6317 | 179017245.5327 | 95089662.5306 | 110084096.5 | 146877848.8152 | 15612624.567 | 62669092 | 31294995.2709 | 266252587.5225 | 137108129 | 378548686.1336 | 95465467 | 105254776 | 34313058 | 114041436.621 | 2544000 | 1916173705.1253
Gross Profit | 10627323 | 5181729.3983 | -3222943.1227 | 4483542.4694 | 76790003.5 | 11122151.1848 | 897434.713 | 3966398 | 3378825.6191 | 22665439.4775 | 7783469 | 44181975.8664 | 7534533 | 10745224 | 3344862 | 14514102.7376 | 768000 | 224762070.8433
Cost Incured previous years | 47932563.8712 | 84545900.2049 | 155682611.5448 | 36325080.7913 | 88445914.0552 | 60816719.2357 | 7577984.8528 | 12220225.7265 | 13885758.7996 | 42296563.1279 | 21503119.2566 | 32080291.6089 | 11225623.2983 | 1248305.75 | 0 | 0 | 0 | 615786662.1237
Cost Incured To Date | 8659090.52 | 4022009.36 | 12537753.47 | 20050517.64 | 10077512.93 | 38274642.2 | 3233659.82 | 15270253.04 | 10913638.62 | 38490250.93 | 22737334.53 | 91498513.71 | 21096278.36 | 11993734.62 | 259327 | 1764978.77 | 209382 | 311088877.52
Percentage Of Completion Previous Year | 95.87% | 91.9% | 86.97% | 38.2% | 80.34% | 41.41% | 48.54% | 19.5% | 44.37% | 15.89% | 15.68% | 8.475% | 11.76% | 1.186% | 0% | 0% | 0% | 32.14%
Percentage Of Completion Current Year | 17.32% | 4.372% | 7.004% | 21.09% | 9.154% | 26.06% | 20.71% | 24.37% | 34.87% | 14.46% | 16.58% | 24.17% | 22.1% | 11.39% | 0.7558% | 1.548% | 8.23% | 16.23%
Percentage Of Completion YTD | 113.2% | 96.27% | 93.97% | 59.29% | 89.5% | 67.47% | 69.25% | 43.87% | 79.24% | 30.34% | 32.27% | 32.65% | 33.86% | 12.58% | 0.7558% | 1.548% | 8.23% | 48.37%
Total Revenue (Cost to Cost) | 68620010.1976 | 93556332.8537 | 165191803.9009 | 59033746.3632 | 167249197.0425 | 106594937.4472 | 11433112.5876 | 29230382.3859 | 27476913.0611 | 87664000.348 | 46751932.8879 | 138002196.5343 | 34872881.0053 | 14593890.5701 | 284606.3857 | 1989608.3779 | 272591.6604 | 1052818143.6094
2015 | 21550245.036 | 58330254.2739 | 131211720.3058 | 37462470.4658 | 150142037.8896 | 65421993.2873 | 8013577.6407 | 12993657.6901 | 15384962.0162 | 45897167.3534 | 22723826.3245 | 35824514.536 | 12111596.3297 | 1375742.4841 | 0 | 0 | 0 | 618443765.6329
2014 | 27590161 | 30977537 | 21668054 | 575362.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80811114.67
2013 | 5206901.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206901.425
2012 | 3773153.1797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3773153.1797
POC Revenues 2016 | 10499549.5568 | 4248541.5798 | 12312029.5952 | 20995913.2275 | 17107159.1529 | 41172944.1599 | 3419534.9469 | 16236724.6959 | 12091951.0449 | 41766832.9946 | 24028106.5633 | 102177681.9983 | 22761284.6756 | 13218148.0859 | 284606.3857 | 1989608.3779 | 272591.6604 | 344583208.7018
| 17.32% | 4.372% | 7.004% | 21.09% | 9.154% | 26.06% | 20.71% | 24.37% | 34.87% | 14.46% | 16.58% | 24.17% | 22.1% | 11.39% | 0.7558% | 1.548% | 8.23% | 16.09%
33005027.0818
Percentage Of Completion 2016
Actual Revenues | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Revenue Recognition
Construction Activities
Al Oula | 0 | 0 | 5147052 | 0 | 2373550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7520602
Hyper Al Sulaimaniya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Giza | 4099757.46 | 0 | 5723604.01 | 486605.53 | 2045554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12355521
Maxim mall | 2562304.18 | 10497786.16 | 3538507.9 | 5914679.58 | 4894978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27408255.82
Attaka | 137802 | 13389759 | 0 | 0 | 452519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13980080
مول مصر | 0 | 0 | 0 | 0 | 22665950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22665950
مراسى تانك الخزان الجديد PKG22 New | 857796 | 0 | 896457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754253
نادي سوديك | 5873689.84 | -619050.98 | 2692512.76 | 2758942.7 | 2981570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13687664.32
شرم الشيخ | 2509177 | 2945219 | 0 | 2147092 | 5372540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12974028
عمائر اب تاون 53 | 10056533.76 | 6046517.98 | 0 | 9769442.35 | 9548964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35421458.09
New Giza phase 2 | 5682154.33 | 5746118.3 | 5473408.65 | 3968781 | 7884396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28754858.28
Beni suef | -376305.89 | 16579000 | 27451033 | 40278342 | 27877387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111809456.11
كوبرى الشيخ بن زايد - كوبرى العاصمة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
جبل الزيت - GAMISA | 0 | 6596770 | 10725650 | 5923635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23246055
لوك اند لوت كوبرى الغرابلى - الاس | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
محطه كهرباء المستثمرين بالقطامي | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
الساحل الشمالى - ابناء علام | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 31402908.68 | 61182119.46 | 61648225.32 | 71247520.16 | 86097408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311578181.62
Closed Projects
كباري مراسي pkg#37 | 101636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101636
اب تاون pkg#17 | -107619.49 | 0 | 159382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51762.51
اب تاون pkg#32 | 254298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254298
PKG#45 Civic Center | 1258165 | 308208 | 769574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2335947
Limak | 1110732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110732
Sodic West Town | 627547 | 0 | 397133 | 754074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1778754
New Cairo Mall | 3608866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3608866
El Wahatt | -1787461.1 | 0 | 1787461.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 410860 | 318578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729438
ميناء دبى السخنة | 0 | 0 | 1173484 | 3109784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4283268
Sub Total | 5066163.41 | 719068 | 4605612.1 | 3863858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14254701.51
Trade Activities
ابناء مصر للتعمير | 6616932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6616932
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 6616932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6616932
Total Actual Revenues | 43086004.09 | 61901187.46 | 66253837.42 | 75111378.16 | 86097408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332449815.13
POC Revenues | 53651615.3252 | 52014357.944 | 110749809.8846 | 58703080.8573 | 69464344.6907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344583208.7018 | 0
Total Revenues | 60268547.3252 | 52425217.944 | 111923293.8846 | 61812864.8573 | 69464344.6907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355894268.7018
POC Revenues | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Revenue Recognition
Construction Activities
Al Oula | 886805.8085 | 991385.4671 | 1331618.548 | 310736.1651 | -541598.4318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2978947.5568
Hyper Al Sulaimaniya | 2486680.7263 | 876208.8313 | 651040.9192 | 114353.9945 | 120257.1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4248541.5798
New Giza | -629871.8585 | 2177675.9908 | -3114231.4629 | 2417485.9764 | -894550.0506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43491.4048
Maxim mall | 109739.1174 | -6499450.804 | 3925753.9905 | -4003919.6036 | 55534.7072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6412342.5925
Attaka | 6006889.9104 | -7825016.271 | 1327167.7999 | 1025973.4905 | 2592064.2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3127079.1529
مول مصر | 11031129.4585 | 4796284.7482 | 8355244.3065 | 4922414.635 | -10598078.9882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18506994.1599
مراسى تانك الخزان الجديد PKG22 New | -228485.8251 | 376372.2475 | 505870.7081 | 550488.328 | 461036.4884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665281.9469
نادي سوديك | -2052499.2515 | 3392521.7999 | 805356.4706 | 500010.8605 | -96329.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2549060.3759
شرم الشيخ | -772233.4448 | -1172470.9938 | 3404911.4801 | 370753.042 | -2713037.0385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -882076.9551
عمائر اب تاون 53 | -4480852.4608 | 1118377.6443 | 12305849.9315 | -1968068.7657 | -629931.4447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6345374.9046
New Giza phase 2 | -3650726.7285 | -3255455.8326 | 6259703.4131 | -707085.3531 | -3373187.2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4726751.7167
Beni suef | 10363159.3181 | -4264973.7824 | 15437487.2783 | -18849409.7001 | -12318037.2257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9631774.1117
كوبرى الشيخ بن زايد - كوبرى العاصمة | 2707098.9065 | 3901532.6255 | 4119253.5032 | 6232530.3796 | 5800869.2609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22761284.6756
جبل الزيت - GAMISA | 471872.9689 | -3780753.1869 | -6213442.3214 | -3696848.0947 | 3191263.7199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10027906.9141
ميناء دبى السخنة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG62 |  |  |  | 97413.4872 | 187192.8985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284606.3857
محطه كهرباء المستثمرين بالقطامي |  |  |  | 124426.7236 | 1865181.6544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989608.3779
لوك اند لوت كوبرى الغرابلى - الاس |  |  |  | 14305.1321 | 258286.5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272591.6604
Sub Total | 22248706.6452 | -9167761.516 | 49101584.5646 | -12544439.3027 | -16633063.3093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33005027.0818
Accrued Revenues
كباري مراسي pkg#37 | -101636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101636
اب تاون pkg#17 | 107619.49 | 0 | -159382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -51762.51
اب تاون pkg#32 | -254298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -254298
PKG#45 Civic Center | -1258165 | -308208 | -769574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2335947
Limak | -1110732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1110732
Sodic West Town | -627547 | 0 | -397133 | -754074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1778754
New Cairo Mall | -3608866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3608866
El Wahatt | 1787461.1 | 0 | -1787461.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 0 | -318578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -318578
Sub Total | -5066163.41 | -308208 | -3432128.1 | -754074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9560573.51
Total | 17182543.2352 | -9475969.516 | 45669456.4646 | -13298513.3027 | -16633063.3093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23444453.5718
Projects Direct Cost | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Construction Activities
Al Oula | 731358.21 | 817606.17 | 5343028.71 | 256267.43 | 1510830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8659090.52
Hyper Al Sulaimaniya | 2354090.92 | 829489.38 | 616327.42 | 108256.64 | 113845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4022009.36
New Giza | 3533501.11 | 2217600.64 | 2657211.75 | 2957333.97 | 1172106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12537753.47
Maxim mall | 2551727.6 | 3818299.91 | 7128164.09 | 1824723.04 | 4727603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20050517.64
Attaka | 3619725.03 | 3278087.63 | 781810.15 | 604382.12 | 1793508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10077512.93
مول مصر | 10254611.17 | 4458658.14 | 7767090.57 | 4575909.32 | 11218373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38274642.2
مراسى تانك الخزان الجديد PKG22 New | 595102.86 | 355913.84 | 1326101.6 | 520565.52 | 435976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3233659.82
نادي سوديك | 3593738.78 | 2608383.28 | 3289662.74 | 3064968.24 | 2713500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15270253.04
شرم الشيخ | 1567685.33 | 1600000.78 | 3073116.43 | 2272491.08 | 2400345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10913638.62
عمائر اب تاون 53 | 5138272.57 | 6602814.02 | 11340463.66 | 7189360.68 | 8219340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38490250.93
New Giza phase 2 | 1922300.82 | 2356865.93 | 11102818 | 3086479.78 | 4268870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22737334.53
Beni suef | 8943070.81 | 11027017.59 | 38405998.1 | 19189273.21 | 13933154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91498513.71
كوبرى الشيخ بن زايد - كوبرى العاصمة | 2509072.44 | 3616132.37 | 3817926.79 | 5776615.76 | 5376531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21096278.36
جبل الزيت - GAMISA | 428162.79 | 2555165.68 | 4094236.28 | 2020516.87 | 2895653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11993734.62
لوك اند لوت كوبرى الغرابلى - الاس |  |  |  | 10988 | 198394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209382
محطه كهرباء المستثمرين بالقطامي |  |  |  | 110378.77 | 1654600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1764978.77
PKG62 |  |  |  | 88761 | 170566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259327
Sub Total | 47742420.44 | 46142035.36 | 100743956.29 | 53657271.43 | 62803194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311088877.52
Closed Projects
كباري مراسي pkg#37 | 0 | 11317.87 | 62017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73334.87
اب تاون pkg#17 | 248856.65 | 3203.47 | -228908.32 | 4565.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27717.43
اب تاون pkg#32 | 362029.54 | 199721.77 | 223402.45 | 104932.31 | 372391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1262477.07
PKG#45 Civic Center | 768053.81 | 439971.19 | 852913.78 | 282463.31 | 481552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2824954.09
Limak | 439705 | 187720.9 | 202557.39 | 128107.53 | 59919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1018009.82
Sodic West Town | 132805.94 | 178294.44 | 289575.26 | 254336.73 | 524007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1379019.37
New Cairo Mall | 274993.26 | 116410.23 | 488766.75 | 27239.66 | 50944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958353.9
El Wahatt | 0 | 165336.07 | 125002.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290338.92
Kasrawy II | 0 | 0 | -254478.69 | 1554.06 | -31010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -283934.63
ميناء دبى السخنة | 833933.77 | 479294.04 | 971403.07 | 32161.25 | -1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2315726.13
مشاريع منتهية | 2016-01-01: 8823; 2016-02-01: 32612; 2016-03-01: 1621668; 2016-04-01: -177131.19; 2016-05-01: 46473 | 1532444.81
Sub Total | 3069200.97 | 1813881.98 | 4353919.54 | 658229.29 | 1503210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11398441.78
Trade Activities
ابناء مصر للتعمير | 197211.06 | 0 | 0 | 0 | 1008372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205583.06
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 197211.06 | 0 | 0 | 0 | 1008372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205583.06
Total | 51008832.47 | 47955917.34 | 105097875.83 | 54315500.72 | 65314776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323692902.36
Projects Indirect Cost | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Construction Overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG&A Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Activities
Al Oula | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hyper Al Sulaimaniya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Giza | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maxim mall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Attaka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مول مصر | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مراسى تانك الخزان الجديد PKG22 New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
نادي سوديك | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
شرم الشيخ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
عمائر اب تاون 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Giza phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beni suef | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبرى الشيخ بن زايد - كوبرى العاصمة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
جبل الزيت - GAMISA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade Activities
كباري مراسي pkg#37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG#45 Civic Center | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Limak | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sodic West Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Cairo Mall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## March 2017 (hidden)
Description | Al Oula | Hyper Al Sulaimaniya | New Giza I | Maxim mall | Attaka | مول مصر | مراسى تانك الخزان الجديد PKG22 New | نادي سوديك | شرم الشيخ | عمائر اب تاون 53 | New Giza phase 2 | Beni suef | كوبرى الشيخ بن زايد - كوبرى العاصمة | جبل الزيت - GAMISA | PKG62 | محطه كهرباء المستثمرين بالقطامي | لوك اند لوت كوبرى الغرابلى - الاس | سور لوك اند لود ( اوراسكوم) | مشروع الكيان | مشروع الامل | مشروع مصنع الاسمنت | سور نيو جيزة | Tamay Elamdeed substation (Alestom ) | Wind Farm KFW | Wind Farm FIEM | PkG 107 | كباري الأسماعيلية | نفق العاصمة | Bani Sweif substation (Alestom ) | Ismalia substation (Alestom ) | مبنى وزارات الجيش | رويال سيتى | كوبرى شبرا بنها | كوبري الأمل لوك لود | Total | Trial Balance
[23 empty] | Tamay Elamdeed substation (Alostom ) | [5 empty] | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom )
Total Contract Price | 72000000 | 108788118.03 | 172181998.814 | 95704579 | 184374873 | 171490065 | 16510059.28 | 99588109 | 33784495.5267 | 270610661 | 144891598 | 324195538 | 98662660 | 117257000 | 40934935 | 130103216.3586 | 3896945 | 4817500 | 420103550 | 30857015 | 206723720 | 2517009 | 95970234.5006 | 21885094.48 | 63390614 | 46325341 | 56652000 | 467255000 | 95970234.5006 | 95970234.5006 | 430000000 | 409523809.836 | 2800000 | 9050320 | 4544786527.827
Additions (Deductions) | 155006 | 1466607 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 63965776 | -4933133.02 | 0 | 0 | 0 | -913385 | -340093 | 0 | 0 | 18336328.17 | 0 | 0 | 0 | 4947000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83684106.15
Total Contracts | 72155006 | 110254725.03 | 172181998.814 | 95704579 | 184374873 | 171490065 | 17510059.28 | 99588109 | 33784495.5267 | 270610661 | 144891598 | 388161314 | 93729526.98 | 117257000 | 40934935 | 130103216.3586 | 2983560 | 4477407 | 420103550 | 30857015 | 225060048.17 | 2517009 | 95970234.5006 | 21885094.48 | 68337614 | 46325341 | 56652000 | 467255000 | 95970234.5006 | 95970234.5006 | 430000000 | 409523809.836 | 2800000 | 9050320 | 4628470633.977
Total Estemated Cost Of contract | 62666842.0412 | 105547486.9349 | 178018117.1846 | 92245938.56 | 97229131.4552 | 142973982.712 | 16262187.567 | 92629183 | 30160353.0632 | 264427221.9112 | 140108129 | 251025418.0745 | 72511482.8 | 84320986.93 | 41675579 | 109630210.621 | 3159874 | 3295000 | 385768894.2159 | 27546588.4725 | 187827866.3247 | 2320307 | 91302219 | 19808090.7452 | 62621524.4937 | 42620158 | 42489000 | 408567772 | 91302219 | 91302219 | 395000000 | 381327168.1479 | 2520000 | 6335224 | 4026546375.2548
Additional Cost ( Deductions) | 3291725.47 | 2641131.89 | 0 | 1331253.2913 | 445342.47 | 0 | 860680.6458 | 0 | -222205.4836 | 0 | 0 | 54436941 | -1847431.9117 | 0 | 0 | 0 | 1519.34 | 0 | 0 | 0 | 3781163.9353 | 0 | 0 | -1050000 | -15000000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 48670120.6471
Total Cost | 65958567.5112 | 108188618.8249 | 178018117.1846 | 93577191.8513 | 97674473.9252 | 142973982.712 | 17122868.2128 | 92629183 | 29938147.5796 | 264427221.9112 | 140108129 | 305462359.0745 | 70664050.8883 | 84320986.93 | 41675579 | 109630210.621 | 3161393.34 | 3295000 | 385768894.2159 | 27546588.4725 | 191609030.26 | 2320307 | 91302219 | 18758090.7452 | 47621524.4937 | 42620158 | 42489000 | 408567772 | 91302219 | 91302219 | 395000000 | 381327168.1479 | 2520000 | 6335224 | 4075216495.9019
Gross Margin | 6196438.4888 | 2066106.2051 | -5836118.3706 | 2127387.1487 | 86700399.0748 | 28516082.288 | 387191.0672 | 6958926 | 3846347.9471 | 6183439.0888 | 4783469 | 82698954.9255 | 23065476.0917 | 32936013.07 | -740644 | 20473005.7376 | -177833.34 | 1182407 | 34334655.7841 | 3310426.5275 | 33451017.91 | 196702 | 4668015.5006 | 3127003.7348 | 20716089.5063 | 3705183 | 14163000 | 58687228 | 4668015.5006 | 4668015.5006 | 35000000 | 28196641.6881 | 280000 | 2715096 | 553254138.0751
Gross Margin % | 8.588% | 1.874% | -3.39% | 2.223% | 47.02% | 16.63% | 2.211% | 6.988% | 11.38% | 2.285% | 3.301% | 21.31% | 24.61% | 0.28089 | -0.018093 | 15.74% | -5.96% | 26.41% | 8.173% | 10.73% | 14.86% | 7.815% | 4.864% | 14.29% | 30.31% | 7.998% | 25% | 12.56% | 4.864% | 4.864% | 8.14% | 6.885% | 10% | 30% | 11.95%
Cost Incured previous years | 62666842.0412 | 103351766.9349 | 168220253.1948 | 86958612.6613 | 97229131.4552 | 130138959.0257 | 16232012.9728 | 42177500.0565 | 30160353.1696 | 136511563.2679 | 93523600.0466 | 222368241.3189 | 72511483.3383 | 70257974.81 | 5079728.58 | 39249340.8 | 3159873.52 | 1117525.67 | 83064312.29 | 14245302.8 | 63906129.18 | 894406.32 | 82947.59 | 2217417.69 | 1264551.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1546589830.1137
Cost Incured To Date | 3291725.47 | 4836851.89 | 349962.04 | 6618579.19 | 445342.47 | 6253270.24 | 890855.24 | 17010829.21 | -222205.59 | 70668218.11 | 37934746.07 | 61072455.03 | -1847432.45 | 5006331.24 | 6943858.24 | 31739192.49 | 1519.82 | 1279578.09 | 128023182.13 | 2310694.52 | 127702901.08 | 151872.39 | 429099.23 | 10688207.17 | 37463113.83 | 18460953.41 | 10904445.93 | 25267944.37 | 1545784.88 | 49684.77 | 3813631.02 | 653994.77 | 97273.67 | 3691824.6 | 623528284.57
191609030.26
Percentage Of Completion Previous Year | 95.01% | 95.53% | 94.5% | 92.93% | 99.54% | 91.02% | 94.8% | 45.53% | 100.7% | 51.63% | 66.75% | 72.8% | 102.6% | 83.32% | 12.19% | 35.8% | 99.95% | 33.92% | 21.53% | 51.71% | 33.35% | 38.55% | 0.09085% | 11.82% | 2.655% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 37.95%
Percentage Of Completion Current Year | 4.991% | 4.471% | 0.1966% | 7.073% | 0.4559% | 4.374% | 5.203% | 18.36% | -0.7422% | 26.73% | 27.08% | 19.99% | -2.614% | 5.937% | 16.66% | 28.95% | 0.04807% | 38.83% | 33.19% | 8.388% | 66.65% | 6.545% | 0.47% | 56.98% | 78.67% | 43.32% | 25.66% | 6.185% | 1.693% | 0.05442% | 0.9655% | 0.1715% | 3.86% | 58.27% | 15.3%
Percentage Of Completion YTD | 100% | 100% | 94.69% | 100% | 100% | 95.4% | 100% | 63.9% | 100% | 78.35% | 93.83% | 92.79% | 100% | 89.26% | 28.85% | 64.75% | 100% | 72.75% | 54.72% | 60.1% | 100% | 45.09% | 0.5608% | 68.8% | 81.32% | 43.32% | 25.66% | 6.185% | 1.693% | 0.05442% | 0.9655% | 0.1715% | 3.86% | 58.27% | 53.25%
Total Revenue (Cost to Cost) | 72155006 | 110254725.03 | 163043835.4178 | 95704579 | 184374873 | 163595584.4455 | 17510059.28 | 63634953.8624 | 33784495.5267 | 212024530.5279 | 135946500.5722 | 360177645.027 | 93729526.98 | 104662754.2658 | 11809907.7866 | 84245359.498 | 2983560 | 3257301.7162 | 229874951.2884 | 18545623.4682 | 225060048.17 | 1134976.0741 | 538226.2767 | 15057013.1694 | 55574790.2735 | 20065856.206 | 14539261.24 | 28897466.1139 | 1624816.3412 | 52225.007 | 4151547.6927 | 702353.3915 | 108081.8556 | 5274035.1429 | 2534096469.6472
2016 | 13879539.7972 | 17217191.4275 | 9825572.1733 | 52181178.6179 | 34232835.1104 | 90673109.605 | 8465847.1175 | 32352499.287 | 18399533.6298 | 93806619.9612 | 73992787.8947 | 251360712.2887 | 86551064.4028 | 93280099.6426 | 4989453.3976 | 46578999.0652 | 3896944.408 | 1633893.7527 | 90457299.6801 | 15957239.9543 | 70335211.7734 | 970228.8348 | 87188.4577 | 2682164.6254 | 1559960.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115367175.2301
2015 | 21550245.036 | 58330254.2739 | 131211720.3058 | 37462470.4658 | 150142037.8896 | 65421993.2873 | 8013577.6407 | 12993657.6901 | 15384962.0162 | 45897167.3534 | 22723826.3245 | 35824514.536 | 12111596.3297 | 1375742.4841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618443765.6329
2014 | 27590161 | 30977537 | 21668054 | 575362.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80811114.67
2013 | 5206901.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206901.425
2012 | 3773153.1797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3773153.1797
POC Revenues 2017 | 155005.5621 | 3729742.3285 | 338488.9387 | 5485567.2463 | 0 | 7500481.5532 | 1030634.5218 | 18288796.8854 | -0.11922 | 72320743.2133 | 39229886.353 | 72992418.2023 | -4933133.7525 | 10006912.1391 | 6820454.389 | 37666360.4328 | -913384.408 | 1623407.9634 | 139417651.6083 | 2588383.5138 | 154724836.3966 | 164747.2393 | 451037.819 | 12374848.544 | 54014829.9485 | 20065856.206 | 14539261.24 | 28897466.1139 | 1624816.3412 | 52225.007 | 4151547.6927 | 702353.3915 | 108081.8556 | 5274035.1429 | 705220324.3665
| 0.2148% | 3.383% | 0.1966% | 5.732% | 0% | 4.374% | 5.886% | 18.36% | -3.529e-07% | 26.73% | 27.08% | 18.8% | -5.263% | 0.085342 | 0.16662 | 28.95% | -30.61% | 36.26% | 33.19% | 8.388% | 68.75% | 6.545% | 0.47% | 56.54% | 79.04% | 43.32% | 25.66% | 6.185% | 0.2027% | 0.2027% | 0.2027% | 0.2027% | 0.2027% | 58.27% | 15.24%
Percentage Of Completion 2017
Actual Revenues | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Revenue Recognition
Construction Activities
Al Oula | 792410 | 0 | 1032003 | 0 | 0 | 2570331 | 0 | 0 | 0 | 0 | 0 | 0 | 4394744 |  |  |  |  | -1027882.2028
Hyper Al Sulaimaniya | 0 | 10117291 | 2471861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12589152 |  |  |  |  | 2880906.7561
New Giza I | 0 | 0 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 |  |  |  |  | -5318493.7667
Maxim mall | 0 | 0 | 3361122 | 0 | 0 | 6942464 | 0 | 0 | 0 | 0 | 0 | 0 | 10303586 |  |  |  |  | -6368488.5463
Attaka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 5338641.1104
مول مصر | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | -31645312.7705
مراسى تانك الخزان الجديد PKG22 New | 0 | 0 | 2501783 | 0 | 150622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652405 |  |  |  |  | 2235635.0513
نادي سوديك | 520075 | 5068978 | 2576347 | 3502070 | 0 | 2166022 | 0 | 0 | 0 | 0 | 0 | 0 | 13833492 |  |  |  |  | 2828906.182
شرم الشيخ | 1970526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1970526 |  |  |  |  | -1482147.7318
عمائر اب تاون 53 | 9369764 | 7974003 | 0 | 5695269 | 12728277 | 14681306 | 0 | 0 | 0 | 0 | 0 | 0 | 50448619 |  |  |  |  | 30275729.26
New Giza phase 2 | 0 | 14494481 | 0 | 5851987 | 7075292 | 6348768 | 0 | 0 | 0 | 0 | 0 | 0 | 33770528 |  |  |  |  | 2536623.9647
Beni suef | 3490135 | 13409419 | 49031387 | 20050269 | 0 | 6481496 | 0 | 0 | 0 | 0 | 0 | 0 | 92462706 |  |  |  |  | -2471962.2972
كوبرى الشيخ بن زايد - كوبرى العاصمة | 0 | 0 | -4933133.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4933133.02 |  |  |  |  | -26241411.7218
جبل الزيت - GAMISA | 2983177 | 1879131 | 0 | 11467260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16329568 |  |  |  |  | -9771377.4056
لوك اند لوت كوبرى الغرابلى - الاس | 0 | 0 | -913385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -913385 |  |  |  |  | 0
محطه كهرباء المستثمرين بالقطامي | 0 | 28407165 | 0 | 0 | 10061830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38468995 |  |  |  |  | 33138551.1885
PKG62 | 0 | 0 | 0 | 1439963 | 2148477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3588440 |  |  |  |  | 2791570.7083
سور لوك اند لود ( اوراسكوم) | 0 | 0 | 817896 | 0 | 450500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1268396 |  |  |  |  | -1231350.2873
مشروع الكيان | 120350231 | 2065 | 58640899 | 0 | 54597030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233590225 |  |  |  |  | 90097883.6737
مشروع كوبرى الامل | 0 | 0 | 0 | 18987162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18987162 |  |  |  |  | 15957239.9557
مشروع مصنع الاسمنت | 48793667 | 0 | 20410494 | 30054634 | 17833590 | 15920715 | 0 | 0 | 0 | 0 | 0 | 0 | 133013100 |  |  |  |  | 31397562.8787
سور نيو جيزة | 0 | 0 | 0.32 | 0 | 0 | 612721 | 0 | 0 | 0 | 0 | 0 | 0 | 612721.32 |  |  |  |  | -1065391.4852
Tamay Elamdeed substation (Alestom ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 970228.8348
Wind Farm KFW | 1910183 | 2616090 | 0 | 8071595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12597868 |  |  |  |  | -7066317.8348
Wind Farm FIEM | 15929215 | 2299240 | 0 | 36110981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54339436 |  |  |  |  | 1095038.2534
PKG 107 | 0 | 0 |  | 5089749 | 7583995 | 5849287 | 0 | 0 | 0 | 0 | 0 | 0 | 18523031
Uturn - كباري الأسماعيلية | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
نفق العاصمة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bani Sweif substation (Alestom ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
محولات الاسماعيليه |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مبنى وزارات الجيش |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
رويال سيتى |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبرى شبرا بنها |  |  |  |  | 407864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407864
كوبري الأمل لوك لود | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 206109383 | 86267863 | 134997276.04 | 146320939 | 113037477 | 61573110 | 0 | 0 | 0 | 0 | 0 | 0 | 748306048.04
Closed Projects
كباري مراسي pkg#37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#32 | 0 | 0 | 428292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428292
PKG#45 Civic Center | 798285 | 0 | 304.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798589.42
Limak | 0 | 0 | 0 | 0 | 0 | 3187164.98 | 0 | 0 | 0 | 0 | 0 | 0 | 3187164.98
Sodic West Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Cairo Mall | 0 | 2448050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2448050
El Wahatt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ميناء دبى السخنة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبري المحلة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 798285 | 2448050 | 428596.42 | 0 | 0 | 3187164.98 | 0 | 0 | 0 | 0 | 0 | 0 | 6862096.4
Trade Activities
ابناء مصر للتعمير | 0 | 0 | 4745820.0193 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4745820.0193
شركة الحلول | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 4745820.0193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4745820.0193
Total Actual Revenues | 206907668 | 88715913 | 135425872.46 | 146320939 | 113037477 | 64760274.98 | 0 | 0 | 0 | 0 | 0 | 0 | 759913964.4593
POC Revenues | 103943100.4702 | 96767566.5155 | 159055844.4791 | 143333811.961 | 120505434.8779 | 86888601.2058 | 0 | 0 | 0 | 0 | 0 | 0 | 710494359.5094
Total Revenues | 103943100.4702 | 96767566.5155 | 163801664.4984 | 143333811.961 | 120505434.8779 | 86888601.2058 | 0 | 0 | 0 | 0 | 0 | 0 | 715240179.5287
Total Revenues | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Revenue Recognition | bar: 2017-01-01 to 2017-04-01
Construction Activities | bar: 2017-01-01 to 2017-04-01
Al Oula | -792410.4379 | 1.4901e-08 | -1032003 | 0 | 0 | -2415325 | 0 | 0 | 0 | 0 | 0 | 0 | -4239738.4379
Hyper Al Sulaimaniya | 318817.4114 | -8172973.0829 | -1005254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8859409.6715
New Giza I | 26945.6845 | 30425.796 | 27607.6289 | 28225.2535 | 195431.0149 | 29851.8209 | 0 | 0 | 0 | 0 | 0 | 0 | 338487.1987
Maxim mall | 937558.9345 | 1854129.8697 | -667243.5578 | 0 | 0 | -6942464 | 0 | 0 | 0 | 0 | 0 | 0 | -4818018.7537
Attaka | 0 | 0 | 0 | -2.9802e-08 | 2.9802e-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مول مصر | 4765938.2296 | 746216.2814 | 2360967.1398 | 228337.6206 | 305058.2697 | -906035.9878 | 0 | 0 | 0 | 0 | 0 | 0 | 7500481.5532
مراسى تانك الخزان الجديد PKG22 New | 30634.5218 | 0 | -1501783 | 0 | -150622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1621770.4782
نادي سوديك | 1806125.7713 | 293995.1606 | 1433157.7755 | -852290.6213 | 1732597.2953 | 41719.5039 | 0 | 0 | 0 | 0 | 0 | 0 | 4455304.8854
شرم الشيخ | -2190344.0728 | 8901.4719 | 183.4378 | 0 | -38173.199 | 248906.2429 | 0 | 0 | 0 | 0 | 0 | 0 | -1970526.1192
عمائر اب تاون 53 | -1289776.98 | 2326534.1207 | 18571915.3086 | 10198112.2388 | -2171709.3556 | -5762951.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 21872124.2133
New Giza phase 2 | 13484727.3746 | -9745922.4244 | 5544573.0967 | -302826.8145 | -2442414.3279 | -1078778.5515 | 0 | 0 | 0 | 0 | 0 | 0 | 5459358.353
Beni suef | 9668069.4331 | -3078882.2008 | -23576370.0507 | -12684301.4004 | 5483826.476 | 4717369.9452 | 0 | 0 | 0 | 0 | 0 | 0 | -19470287.7977
كوبرى الشيخ بن زايد - كوبرى العاصمة | -0.73246 | 0 | 0 | -1.1176e-08 | 1.4901e-08 | 1.4901e-08 | 0 | 0 | 0 | 0 | 0 | 0 | -0.73246
جبل الزيت - GAMISA | -409628.4257 | 223871.7465 | 4872398.4316 | -6901475.3721 | 2478418.9754 | -6586241.2166 | 0 | 0 | 0 | 0 | 0 | 0 | -6322655.8609
لوك اند لوت كوبرى الغرابلى - الاس | 0.59196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59196
محطه كهرباء المستثمرين بالقطامي | 5477417.0559 | -25464640.8177 | 5739030.6357 | 11408688.2169 | -158625.7963 | 2195496.1383 | 0 | 0 | 0 | 0 | 0 | 0 | -802634.5672
PKG62 | 222817.4099 | 226618.9872 | 2743267.6279 | -224505.7128 | -458385.9861 | 722202.063 | 0 | 0 | 0 | 0 | 0 | 0 | 3232014.389
سور لوك اند لود ( اوراسكوم) | 1648.6962 | 30.8642 | -816339.8817 | 0 | -566073.6917 | 1735745.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 355011.9634
مشروع الكيان | -104050003.4478 | 25507100.3052 | -25672478.4681 | 27839231.3104 | -35662592.9063 | 17866169.8149 | 0 | 0 | 0 | 0 | 0 | 0 | -94172573.3917
مشروع كوبرى الامل | -132676.7851 | 64419.6158 | 945863.2101 | -18216869.7742 | 806779.5249 | 133705.7224 | 0 | 0 | 0 | 0 | 0 | 0 | -16398778.4862
مشروع مصنع الاسمنت | -18324358.6309 | 16959679.1078 | 11232991.7917 | -3783332.7018 | 17562459.7221 | -1935702.8924 | 0 | 0 | 0 | 0 | 0 | 0 | 21711736.3966
سور نيو جيزة | 38519.4723 | 721.1904 | -1442.7008 | 72525.8394 | 184.4116 | -558482.2937 | 0 | 0 | 0 | 0 | 0 | 0 | -447974.0807
Tamay Elamdeed substation (Alestom ) | 131051.833 | 63494.9077 | 87111.1684 | 20415.2318 | 77627.963 | 71336.7151 | 0 | 0 | 0 | 0 | 0 | 0 | 451037.819
Wind Farm KFW | 1223698.5982 | 970386.4788 | 1058124.3461 | -7366630.9744 | 57293.4488 | 3834108.6464 | 0 | 0 | 0 | 0 | 0 | 0 | -223019.456
Wind Farm FIEM | -15234631.7256 | 5296789.7524 | 12897667.006 | -14318942.8843 | 5381515.0305 | 5652996.7695 | 0 | 0 | 0 | 0 | 0 | 0 | -324606.0515
PKG 107 | 249598.5229 | 1452211.7102 | 2131553.883 | 1975381.1934 | -1812617.1342 | -2453302.9694 | 0 | 0 | 0 | 0 | 0 | 0 | 1542825.206
Uturn - كباري الأسماعيلية | 1873979.1672 | 936594.6748 | 3901810.8214 | 2406914.7741 | 1993261.0959 | 3426700.7067 | 0 | 0 | 0 | 0 | 0 | 0 | 14539261.24
نفق العاصمة | 0 | 0 | 4159367.6121 | 7080592.6235 | 13015613.1176 | 4641892.7608 | 0 | 0 | 0 | 0 | 0 | 0 | 28897466.1139
Bani Sweif substation (Alestom ) | 0 | 0 | 623892.1769 | 405624.9143 | 290577.0482 | 304722.2019 | 0 | 0 | 0 | 0 | 0 | 0 | 1624816.3412
محولات الاسماعيليه |  |  |  |  | 33831.0505 | 18393.9565 | 0 | 0 | 0 | 0 | 0 | 0 | 52225.007
مبنى وزارات الجيش |  |  |  |  | 1724840.4392 | 2426707.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 4151547.6927
رويال سيتى |  |  |  |  | 156022.5026 | 546330.8889 | 0 | 0 | 0 | 0 | 0 | 0 | 702353.3915
كوبرى شبرا بنها |  |  |  |  | -366165.1111 | 66382.9667 | 0 | 0 | 0 | 0 | 0 | 0 | -299782.1444
كوبري الأمل لوك لود |  |  |  |  | 0 | 5274035.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 5274035.1429
Sub Total | -102166282.5298 | 10499703.5155 | 24058568.4391 | -2987127.039 | 7467957.8779 | 25315491.2058 | 0 | 0 | 0 | 0 | 0 | 0 | -37811688.5306
Accrued Revenues
كباري مراسي pkg#37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#32 | 0 | 0 | -428292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -428292
PKG#45 Civic Center | -798285 | 0 | -304.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -798589.42
Limak | 0 | 0 | 0 | 0 | 0 | -3187164.98 | 0 | 0 | 0 | 0 | 0 | 0 | -3187164.98
Sodic West Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Cairo Mall | 0 | -2448050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2448050
El Wahatt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ميناء دبى السخنة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبري المحلة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | -798285 | -2448050 | -428596.42 | 0 | 0 | -3187164.98 | 0 | 0 | 0 | 0 | 0 | 0 | -6862096.4
Total | -102964567.5298 | 8051653.5155 | 23629972.0191 | -2987127.039 | 7467957.8779 | 22128326.2258 | 0 | 0 | 0 | 0 | 0 | 0 | -44673784.9306
Projects Direct Cost | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Construction Activities
Al Oula | 900495.67 | 627188.76 | 304298.3 | 134966.53 | 27653.55 | 1297122.66 | 0 | 0 | 0 | 0 | 0 | 0 | 3291725.47
Hyper Al Sulaimaniya | 309320.33 | 2296943.32 | 1944985.22 | 9668.24 | 1207802.03 | -931867.25 | 0 | 0 | 0 | 0 | 0 | 0 | 4836851.89
New Giza I | 27859.01 | 31457.08 | 28545.19 | 29181.95 | 202055.16 | 30863.65 | 0 | 0 | 0 | 0 | 0 | 0 | 349962.04
Maxim mall | 903676.76 | 1787124 | 2674276.06 | -2542826.62 | 3122908.53 | 673420.46 | 0 | 0 | 0 | 0 | 0 | 0 | 6618579.19
Attaka | -74201.52 | 7946.59 | 0 | 350.69 | -7956.14 | 519202.85 | 0 | 0 | 0 | 0 | 0 | 0 | 445342.47
مول مصر | 3973438.17 | 622132.33 | 1968375.69 | 190368.69 | 254331.91 | -755376.55 | 0 | 0 | 0 | 0 | 0 | 0 | 6253270.24
مراسى تانك الخزان الجديد PKG22 New | 145726.59 | 27555.94 | 272430.76 | 286245.94 | 8218.69 | 150677.32 | 0 | 0 | 0 | 0 | 0 | 0 | 890855.24
نادي سوديك | 2163652.66 | 4988224.27 | 3729332.3 | 2464620.54 | 1611528.46 | 2053470.98 | 0 | 0 | 0 | 0 | 0 | 0 | 17010829.21
شرم الشيخ | -196237.67 | 7946.59 | 163.76 | 0 | -34078.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -222205.59
عمائر اب تاون 53 | 7895359.75 | 10065170.4 | 18147548.04 | 15530218.33 | 10315350.64 | 8714570.95 | 0 | 0 | 0 | 0 | 0 | 0 | 70668218.11
New Giza phase 2 | 13039540.93 | 4591789.08 | 5361523.88 | 5365959.53 | 4479927.28 | 5096005.37 | 0 | 0 | 0 | 0 | 0 | 0 | 37934746.07
Beni suef | 10188430.69 | 7998960.55 | 21893246.84 | 5751333.65 | 6427569.99 | 8812913.31 | 0 | 0 | 0 | 0 | 0 | 0 | 61072455.03
كوبرى الشيخ بن زايد - كوبرى العاصمة | -205713 | -317716.56 | 556700.52 | -2623777.21 | 293738.3 | 449335.5 | 0 | 0 | 0 | 0 | 0 | 0 | -1847432.45
جبل الزيت - GAMISA | 1910207.62 | 1560946.59 | 1667732.6 | 2821431.19 | 1782262.33 | -4736249.09 | 0 | 0 | 0 | 0 | 0 | 0 | 5006331.24
لوك اند لوت كوبرى الغرابلى - الاس | 677.59 | 107.72 | -10.4 | 664.91 |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1519.82
محطه كهرباء المستثمرين بالقطامي | 4615492.24 | 2479489.4 | 4835938.38 | 9613420.23 | 8344838.76 | 1850013.48 | 0 | 0 | 0 | 0 | 0 | 0 | 31739192.49
PKG62 | 226848.89 | 230719.25 | 2792902.12 | 1237448.8 | 1720670.17 | 735269.01 | 0 | 0 | 0 | 0 | 0 | 0 | 6943858.24
سور لوك اند لود ( اوراسكوم) | 1127.65 | 21.11 | 1064.33 | 0 |  | 1277365 | 0 | 0 | 0 | 0 | 0 | 0 | 1279578.09
مشروع الكيان | 14968025.76 | 23424325.96 | 30273943.49 | 25563957.93 | 17386943.91 | 16405985.08 | 0 | 0 | 0 | 0 | 0 | 0 | 128023182.13
مشروع الامل | -118442.85 | 57508.5 | 844388.37 | 687653.13 | 720225.97 | 119361.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2310694.52
مشروع مصنع الاسمنت بنى سويف | 27684221.14 | 15409457.32 | 28751071.33 | 23869938.43 | 16535608.32 | 15452604.54 | 0 | 0 | 0 | 0 | 0 | 0 | 127702901.08
سور نيو جيزة | 35509.21 | 664.83 | -1329.66 | 66858.01 | 170 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 151872.39
Tamay Elamdeed substation (Alestom ) | 124677.44 | 60406.5 | 82874.06 | 19422.23 | 73852.12 | 67866.88 | 0 | 0 | 0 | 0 | 0 | 0 | 429099.23
Wind Farm KFW | 2590864.27 | 2965036.64 | 1261108.8 | 535809.82 | 49107.2 | 3286280.44 | 0 | 0 | 0 | 0 | 0 | 0 | 10688207.17
Wind Farm FIEM | 563050.37 | 6157573.21 | 11925055.6 | 11127961.12 | 3750144.83 | 3939328.7 | 0 | 0 | 0 | 0 | 0 | 0 | 37463113.83
PKG 107 | 229635.19 | 1336061.24 | 1961068.42 | 6500048.54 | 5309772.82 | 3124367.2 | 0 | 0 | 0 | 0 | 0 | 0 | 18460953.41
مشروع دوران الاسماعيلية | 1403009.14 | 701208.91 | 2921204.43 | 1802006.92 | 1506991 | 2570025.53 | 0 | 0 | 0 | 0 | 0 | 0 | 10904445.93
نفق العاصمة | 0 | 0 | 3636951.04 | 6191270.19 | 11380852.11 | 4058871.03 | 0 | 0 | 0 | 0 | 0 | 0 | 25267944.37
Bani Sweif substation (Alestom ) | 0 | 0 | 593545.91 | 385895.22 | 276443.31 | 289900.44 | 0 | 0 | 0 | 0 | 0 | 0 | 1545784.88
محولات الاسماعيليه |  |  |  |  | 32185.5 | 17499.27 | 0 | 0 | 0 | 0 | 0 | 0 | 49684.77
مبنى وزارات الجيش |  |  |  |  | 1584446.45 | 2229184.57 | 0 | 0 | 0 | 0 | 0 | 0 | 3813631.02
رويال سيتى |  |  |  |  | 145280 | 508714.77 | 0 | 0 | 0 | 0 | 0 | 0 | 653994.77
كوبرى شبرا بنها |  |  |  |  | 37529 | 59744.67 | 0 | 0 | 0 | 0 | 0 | 0 | 97273.67
كوبري الأمل لوك لود | 0 | 0 | 0 | 0 | 0 | 3691824.6 | 0 | 0 | 0 | 0 | 0 | 0 | 3691824.6
Sub Total | 93306252.03 | 87118249.53 | 148428935.38 | 115020096.93 | 98546373.93 | 81108376.77 | 0 | 0 | 0 | 0 | 0 | 0 | 623528284.57
Closed Projects
كباري مراسي pkg#37 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#17 | 24197.03 | 453.03 | 321534.43 | 9192.68 | 20326.83 | 20326.83 | 0 | 0 | 0 | 0 | 0 | 0 | 396030.83
اب تاون pkg#32 | 52318.56 | 54224.55 | 67053.13 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173596.24
PKG#45 Civic Center | -119162.64 | 25314.43 | 90286.02 | 65373.01 | 252426.79 | 13746.63 | 0 | 0 | 0 | 0 | 0 | 0 | 327984.24
Limak | 28898.3 | 621.05 | -1082.1 | 0 | 6874.96 | 3212833.32 | 0 | 0 | 0 | 0 | 0 | 0 | 3248145.53
Sodic West Town | 0 | 0 | 36912.35 | 0 |  | 227542.45 | 0 | 0 | 0 | 0 | 0 | 0 | 264454.8
New Cairo Mall | 894383.18 | 736998.9 | 45142.44 | 62072 | 325829.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2064426.37
El Wahatt | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ميناء دبى السخنة | 12377.49 | 147.49 | -294.98 | -1209975 | -13950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1211695
مشاريع منتهية | 404125.67 | 556245.53 | 652563.27 | 1008236.34 | 641847.34 | -3358856.04 | 0 | 0 | 0 | 0 | 0 | 0 | -95837.89
Sub Total | 1297137.59 | 1374004.98 | 1212114.56 | -65100.97 | 1233355.77 | 115593.19 | 0 | 0 | 0 | 0 | 0 | 0 | 5167105.12
Trade Activities
ابناء مصر للتعمير | 481197.34 | 348124.35 | -18018.64 | 81441.36 | 1463570.15 | 15254.46 | 0 | 0 | 0 | 0 | 0 | 0 | 2371569.02
شركة الحلول | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 481197.34 | 348124.35 | -18018.64 | 81441.36 | 1463570.15 | 15254.46 | 0 | 0 | 0 | 0 | 0 | 0 | 2371569.02
Total | 95084586.96 | 88840378.86 | 149623031.3 | 115036437.32 | 101243299.85 | 81239224.42 | 0 | 0 | 0 | 0 | 0 | 0 | 631066958.71
| 2017-01-01: 95084587.41; 2017-02-01: 88840378.43; 2017-03-01: 149623031; 2017-04-01: 115036437; 2017-05-01: 101249373.85; 2017-06-01: 81233150.4 | 631066958.55
| 2017-01-01: 0.45; 2017-02-01: 0.43; 2017-03-01: 0.3; 2017-04-01: 0.32; 2017-05-01: -6074; 2017-06-01: 6074.02 | 0.16
Projects Indirect Cost | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Construction Overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG&A Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Activities
Al Oula | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hyper Al Sulaimaniya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Giza I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maxim mall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Attaka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مول مصر | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مراسى تانك الخزان الجديد PKG22 New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
نادي سوديك | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
شرم الشيخ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
عمائر اب تاون 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Giza phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beni suef | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبرى الشيخ بن زايد - كوبرى العاصمة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
جبل الزيت - GAMISA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade Activities
كباري مراسي pkg#37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG#45 Civic Center | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Limak | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sodic West Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Cairo Mall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## COST 30.092016 (3) (hidden)
Description | Al Oula | Hyper Al Sulaimaniya | New Giza I | Maxim mall | Attaka | مول مصر | مراسى تانك الخزان الجديد PKG22 New | نادي سوديك | شرم الشيخ | عمائر اب تاون 53 | New Giza phase 2 | Beni suef | كوبرى الشيخ بن زايد - كوبرى العاصمة | جبل الزيت - GAMISA | PKG62 | محطه كهرباء المستثمرين بالقطامي | لوك اند لوت كوبرى الغرابلى - الاس | سور لوك اند لود ( اوراسكوم) | مشروع الكيان | مشروع الامل | مشروع مصنع الاسمنت | سور نيو جيزة | Total | Trial Balance
Total Contract Price | 33000000 | 65143328.03 | 162482670 | 57304000 | 149999784 | 186777525 | 16510059.28 | 34207969 | 15492289.89 | 288918027 | 144891598 | 35402400 | 103000000 | 116000000 | 37657920 | 128555539.3586 | 3312000 | 4817500 | 391011409.53 | 40857015 | 206723720 | 2517009 | 2224581763.0886
Additions (Deductions) | 39000000 | 36662672 | 9699328.814 | 42269205 | 34375089 | -21948549 | 0 | 32427521 | 18982312.6367 | -18307366 | 0 | 298652739 | -15000000 | 0 | 3277015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460089967.4507
Total Contracts | 72000000 | 101806000.03 | 172181998.814 | 99573205 | 184374873 | 164828976 | 16510059.28 | 66635490 | 34474602.5267 | 270610661 | 144891598 | 334055139 | 88000000 | 116000000 | 40934935 | 128555539.3586 | 3312000 | 4817500 | 391011409.53 | 40857015 | 206723720 | 2517009 | 2684671730.5393
Total Estemated Cost Of contract | 30000000 | 63597605.6317 | 157051086 | 55087640 | 110000000 | 173629627.0825 | 15612624.567 | 33484323 | 13982628 | 266252587.5225 | 137108129 | 31526907 | 95465467 | 105254776 | 34313058 | 114041436.621 | 2544000 | 3295000 | 360486756.2459 | 36473760.6125 | 187827866.3247 | 2320307 | 2029355585.6078
Additional Cost ( Deductions) | 29941519.88 | 33903142 | 20967031.1846 | 41033223.56 | -18005265.1448 | -31725148.3705 | 0 | 29184769 | 16928546.0632 | -9603925.6113 | 3000000 | 248209590.0745 | -19979890.2 | -19154173.07 | 3862521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328561940.3657
Total Cost | 59941519.88 | 97500747.6317 | 178018117.1846 | 96120863.56 | 91994734.8552 | 141904478.712 | 15612624.567 | 62669092 | 30911174.0632 | 256648661.9112 | 140108129 | 279736497.0745 | 75485576.8 | 86100602.93 | 38175579 | 114041436.621 | 2544000 | 3295000 | 360486756.2459 | 36473760.6125 | 187827866.3247 | 2320307 | 2357917525.9735
Gross Profit | 12058480.12 | 4305252.3983 | -5836118.3706 | 3452341.44 | 92380138.1448 | 22924497.288 | 897434.713 | 3966398 | 3563428.4636 | 13961999.0888 | 4783469 | 54318641.9255 | 12514423.2 | 29899397.07 | 2759356 | 14514102.7376 | 768000 | 1522500 | 30524653.2841 | 4383254.3875 | 18895853.6753 | 196702 | 326754204.5658
Cost Incured previous years | 47932563.8712 | 84545900.2049 | 155682611.5448 | 36325080.7913 | 88445914.0552 | 60816719.2357 | 7577984.8528 | 12220225.7265 | 13885758.7996 | 42296563.1279 | 21503119.2566 | 32080291.6089 | 11225623.2983 | 1248305.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615786662.1237
Cost Incured To Date | 8753043.44 | 10182576.1 | 13150561.67 | 30513256.2 | 3548820.8 | 44947831.12 | 3754742.61 | 16499394.02 | 8429457.29 | 41077090.18 | 38591998.02 | 113258196.21 | 41627740.92 | 30939137.29 | 1680480.32 | 7149920.45 | 327145.08 | 441710.28 | 24253615.36 | 2516989.22 | 3899115.93 | 172387.39 | 445715209.9
Percentage Of Completion Previous Year | 79.97% | 86.71% | 87.45% | 37.79% | 96.14% | 42.86% | 48.54% | 19.5% | 44.92% | 16.48% | 15.35% | 11.47% | 14.87% | 1.45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26.12%
Percentage Of Completion Current Year | 14.6% | 10.44% | 7.387% | 31.74% | 3.858% | 31.67% | 24.05% | 26.33% | 27.27% | 16.01% | 27.54% | 40.49% | 55.15% | 35.93% | 4.402% | 6.27% | 12.86% | 13.41% | 6.728% | 6.901% | 2.076% | 7.43% | 18.9%
Percentage Of Completion YTD | 94.57% | 97.16% | 94.84% | 69.54% | 100% | 74.53% | 72.59% | 45.83% | 72.19% | 32.49% | 42.89% | 51.96% | 70.02% | 37.38% | 4.402% | 6.27% | 12.86% | 13.41% | 6.728% | 6.901% | 2.076% | 7.43% | 45.02%
Total Revenue (Cost to Cost) | 68089093.079 | 98911316.0236 | 163298172.6241 | 69238947.5563 | 184374873 | 122850685.8308 | 11984147.919 | 30537317.0944 | 24887705.7667 | 87909281.364 | 62146840.7033 | 173560008.2868 | 61615692.0088 | 43364892.5278 | 1801946.5446 | 8059893.904 | 425905.8589 | 645808.5808 | 26307319.6554 | 2819469.7939 | 4291374.6801 | 187001.3805 | 1247307694.1828
2015 | 21550245.036 | 58330254.2739 | 131211720.3058 | 37462470.4658 | 150142037.8896 | 65421993.2873 | 8013577.6407 | 12993657.6901 | 15384962.0162 | 45897167.3534 | 22723826.3245 | 35824514.536 | 12111596.3297 | 1375742.4841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618443765.6329
2014 | 27590161 | 30977537 | 21668054 | 575362.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80811114.67
2013 | 5206901.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206901.425
2012 | 3773153.1797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3773153.1797
POC Revenues 2016 | 9968632.4383 | 9603524.7497 | 10418398.3184 | 31201114.4205 | 34232835.1104 | 57428692.5435 | 3970570.2783 | 17543659.4043 | 9502743.7505 | 42012114.0106 | 39423014.3788 | 137735493.7509 | 49504095.6791 | 41989150.0437 | 1801946.5446 | 8059893.904 | 425905.8589 | 645808.5808 | 26307319.6554 | 2819469.7939 | 4291374.6801 | 187001.3805 | 539072759.2751
| 13.85% | 9.433% | 6.051% | 31.33% | 18.57% | 34.84% | 24.05% | 26.33% | 27.56% | 15.52% | 27.21% | 41.23% | 56.25% | 36.2% | 4.402% | 6.27% | 12.86% | 13.41% | 6.728% | 6.901% | 2.076% | 7.43% | 20.08%
-190715963.1549
Percentage Of Completion 2016
Actual Revenues | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Revenue Recognition
Construction Activities
Al Oula | 0 | 0 | 5147052 | 0 | 2373550 | 3060951 | 0 | 747529 | 1162802 | 0 | 0 | 0 | 12491884
Hyper Al Sulaimaniya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14811302 | 0 | 0 | 0 | 14811302
New Giza I | 4099757.46 | 0 | 5723604.01 | 486605.53 | 2045554 | 0 | -118426.49 | 7821956.96 | 1993825.98 | 0 | 0 | 0 | 22052877.45
Maxim mall | 2562304.18 | 10497786.16 | 3538507.9 | 5914679.58 | 4894978 | 4641121.5 | 0 | 0 | 17975385.31 | 0 | 0 | 0 | 50024762.63
Attaka | 137802 | 13389759 | 0 | 0 | 452519 | 14655332 | 0 | 258782 | 0 | 0 | 0 | 0 | 28894194
مول مصر | 0 | 0 | 0 | 0 | 22665950 | 71594431.29 | 0 | 0 | 23125689 | 0 | 0 | 0 | 117386070.29
مراسى تانك الخزان الجديد PKG22 New | 857796 | 0 | 896457 | 0 | 0 | 1344233 | 924823 | 0 | 1712527 | 0 | 0 | 0 | 5735836
نادي سوديك | 5873689.84 | -619050.98 | 2692512.76 | 2758942.7 | 2981570 | 2034590.5 | 1822839 | 2620813.24 | 1908994 | 0 | 0 | 0 | 22074901.06
شرم الشيخ | 2509177 | 2945219 | 0 | 2147092 | 5372540 | 2760718 | 1740437.6385 | 1404691 | 854538.3615 | 0 | 0 | 0 | 19734413 | 854538.3615
عمائر اب تاون 53 | 10056533.76 | 6046517.98 | 0 | 9769442.35 | 9548964 | 6058192.85 | 4724237.78 | 3444820.2 | 6858375 | 0 | 0 | 0 | 56507083.92
New Giza phase 2 | 5682154.33 | 5746118.3 | 5473408.65 | 3968781 | 7884396 | 4808926.4 | 4832877 | 0 | 0 | 0 | 0 | 0 | 38396661.68
Beni suef | -376305.89 | 16579000 | 27451033 | 40278342 | 27877387 | 33610757 | 26158400 | 3271250 | 25157869.4 | 0 | 0 | 0 | 200007732.51
كوبرى الشيخ بن زايد - كوبرى العاصمة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62185192 | 0 | 0 | 0 | 0 | 62185192
جبل الزيت - GAMISA | 0 | 6596770 | 10725650 | 5923635 | 0 | 23237734 | 2434403 | 10889298.05 | 11732540 | 0 | 0 | 0 | 71540030.05
لوك اند لوت كوبرى الغرابلى - الاس | 0 | 0 | 0 | 0 | 0 | 1201031 | 561277 | 0 | 2134637 | 0 | 0 | 0 | 3896945
محطه كهرباء المستثمرين بالقطامي | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
الساحل الشمالى - ابناء علام | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
سور لوك اند لود ( اوراسكوم) | 0 | 0 | 0 | 0 | 0 | 456707.64 | 0 | 0 | 1404594 | 0 | 0 | 0 | 1861301.64
مشروع الكيان | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مشروع كوبرى الامل | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مشروع مصنع الاسمنت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
سور نيو جيزة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2187535.2 | 0 | 0 | 0 | 2187535.2
Sub Total | 31402908.68 | 61182119.46 | 61648225.32 | 71247520.16 | 86097408 | 169464726.18 | 43080867.9285 | 92644332.45 | 113020614.2515 | 0 | 0 | 0 | 729788722.43
Closed Projects
كباري مراسي pkg#37 | 101636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101636
اب تاون pkg#17 | -107619.49 | 0 | 159382 | 0 | 0 | 279041 | 0 | 0 | 0 | 0 | 0 | 0 | 330803.51
اب تاون pkg#32 | 254298 | 0 | 0 | 0 | 0 | 552505 | 286378.0758 | 0 | 0 | 0 | 0 | 0 | 1093181.0758
PKG#45 Civic Center | 1258165 | 308208 | 769574 | 0 | 0 | 245568 | 2103764 | 0 | 0 | 0 | 0 | 0 | 4685279
Limak | 1110732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110732
Sodic West Town | 627547 | 0 | 397133 | 754074 | 0 | 1064039 | 857110 | 1261971.4 | 0 | 0 | 0 | 0 | 4961874.4
New Cairo Mall | 3608866 | 0 | 0 | 0 | 0 | 4446863 | 0 | 0 | 0 | 0 | 0 | 0 | 8055729
El Wahatt | -1787461.1 | 0 | 1787461.1 | 0 | 0 | 0 | 0 | -1823216.79 | 0 | 0 | 0 | 0 | -1823216.79
Kasrawy II | 0 | 410860 | 318578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729438
ميناء دبى السخنة | 0 | 0 | 1173484 | 3109784 | 0 | 250519 | 0 | 0 | 0 | 0 | 0 | 0 | 4533787
كوبري المحلة | 0 | 0 | 0 | 0 | 0 | 14985408 | 0 | 0 | 0 | 0 | 0 | 0 | 14985408
Sub Total | 5066163.41 | 719068 | 4605612.1 | 3863858 | 0 | 21823943 | 3247252.0758 | -561245.39 | 0 | 0 | 0 | 0 | 38764651.1958 | 768553373.6258 | 776495331.52
Trade Activities | [14 empty] | 775271256.25
ابناء مصر للتعمير | 6616932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6616932
شركة الحلول | 0 | 0 | 0 | 0 | 0 | 49950 | 0 | 0 | 51000 | 0 | 0 | 0 | 100950
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Client | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 6616932 | 0 | 0 | 0 | 0 | 49950 | 0 | 0 | 51000 | 0 | 0 | 0 | 6717882
Total Actual Revenues | 36469072.09 | 61901187.46 | 66253837.42 | 75111378.16 | 86097408 | 191288669.18 | 46328120.0043 | 92083087.06 | 113071614.2515 | 0 | 0 | 0 | 775271255.6258
POC Revenues | 53651615.3252 | 52014357.944 | 110749809.8846 | 58703080.8573 | 89081919.6942 | 105652363.4682 | 59709154.451 | 91351753.5836 | -81841295.9331 | 0 | 0 | 0 | 539072759.2751 | 0
Total Revenues | 60268547.3252 | 52425217.944 | 111168287.8846 | 58703080.8573 | 89081919.6942 | 113417327.7482 | 59709154.451 | 91351753.5836 | -81790295.9331 | 0 | 0 | 0 | 554334993.5551 | 539072759.2751 | 166259476.4149
POC Revenues | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Revenue Recognition
Construction Activities
Al Oula | 886805.8085 | 991385.4671 | 1331618.548 | 310736.1651 | -104797.2913 | -4125897.7455 | 200152.3586 | 135630.3137 | -2148885.1859 | 0 | 0 | 0 | -2523251.5617
Hyper Al Sulaimaniya | 2486680.7263 | 876208.8313 | 651040.9192 | 114353.9945 | 268062.755 | 1131750.8508 | 678008.8491 | 1389114.415 | -12802998.5915 | 0 | 0 | 0 | -5207777.2503
New Giza I | -629871.8585 | 2177675.9908 | -3114231.4629 | 2417485.9764 | -894549.6578 | 906262.7734 | 306915.6205 | -8627707.201 | -4176459.3125 | 0 | 0 | 0 | -11634479.1316
Maxim mall | 109739.1174 | -6499450.804 | 3925753.9905 | -4003919.6036 | 232812.4065 | 2575023.7946 | 1055268.848 | 3091891.7554 | -19310767.7144 | 0 | 0 | 0 | -18823648.2095
Attaka | 6006889.9104 | -7825016.271 | 1327167.7999 | 1025973.4905 | 3155601.6719 | -18031028.7913 | 504489.7176 | 9776088.0847 | 9398475.4977 | 0 | 0 | 0 | 5338641.1104
مول مصر | 11031129.4585 | 4796284.7482 | 8355244.3065 | 4922414.635 | -6156784.1964 | -57109694.9662 | 1262922.7318 | 5498956.4062 | -32557850.87 | 0 | 0 | 0 | -59957377.7465
مراسى تانك الخزان الجديد PKG22 New | -228485.8251 | 376372.2475 | 505870.7081 | 550488.328 | 556911.8187 | -378424.0223 | 252827.5045 | 705385.1821 | -4106211.6633 | 0 | 0 | 0 | -1765265.7217
نادي سوديك | -2052499.2515 | 3392521.7999 | 805356.4706 | 500010.8605 | -96329.6205 | -245621.1659 | -557711.4317 | 886812.6331 | -7163781.9501 | 0 | 0 | 0 | -4531241.6557
شرم الشيخ | -772233.4448 | -1172470.9938 | 3404911.4801 | 370753.042 | -2713037.0495 | -982987.843 | -717397.5521 | 77570.3556 | -7726777.2438 | 0 | 0 | 0 | -10231669.2495
عمائر اب تاون 53 | -4480852.4608 | 1118377.6443 | 12305849.9315 | -1968068.7657 | -655507.0338 | -655241.8444 | 405375.6724 | 6291302.6035 | -26856205.6564 | 0 | 0 | 0 | -14494969.9094
New Giza phase 2 | -3650726.7285 | -3255455.8326 | 6259703.4131 | -707085.3531 | 55055.4959 | 4195986.9977 | -549184.586 | 3184597.4807 | -4506538.1884 | 0 | 0 | 0 | 1026352.6988
Beni suef | 10363159.3181 | -4264973.7824 | 15437487.2783 | -18849409.7001 | -2236385.0874 | -4350237.5471 | -9266162.061 | 9259075.1667 | -58364792.3444 | 0 | 0 | 0 | -62272238.7591
كوبرى الشيخ بن زايد - كوبرى العاصمة | 2707098.9065 | 3901532.6255 | 4119253.5032 | 6232530.3796 | 5800869.0343 | 22733144.1281 | 9416497.6396 | -48488168.4317 | -19103854.106 | 0 | 0 | 0 | -12681096.3209
جبل الزيت - GAMISA | 471872.9689 | -3780753.1869 | -6213442.3214 | -3696848.0947 | 3191263.5767 | -12074958.6733 | 2652588.5431 | 636628.7987 | -10737231.6174 | 0 | 0 | 0 | -29550880.0063
ميناء دبى السخنة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG62 | 0 | 0 | 0 | 97413.4872 | 187192.8985 | 894329.4537 | 497430.0358 | 661463.413 | -535882.7435 | 0 | 0 | 0 | 1801946.5446
محطه كهرباء المستثمرين بالقطامي | 0 | 0 | 0 | 124426.7236 | 1865181.2373 | 2842483.1043 | 1639941.5693 | 2793729.5487 | -1205868.2791 | 0 | 0 | 0 | 8059893.904
لوك اند لوت كوبرى الغرابلى - الاس | 0 | 0 | 0 | 14305.1321 | 258286.8017 | -1122329.613 | -451416.6842 | 196731.7845 | -2366616.5623 | 0 | 0 | 0 | -3471039.1411
سور لوك اند لود ( اوراسكوم) | 0 | 0 | 0 | 0 | 270663.9345 | -14921.6024 | 120376.9413 | 303184.1064 | -1894796.439 | 0 | 0 | 0 | -1215493.0592
مشروع الكيان | 0 | 0 | 0 | 0 | 0 | 0 | 9177362.8059 | 8577422.7848 | 8552534.0647 | 0 | 0 | 0 | 26307319.6554
مشروع كوبرى الامل | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035678.0683 | 1783791.7256 | 0 | 0 | 0 | 2819469.7939
مشروع مصنع الاسمنت | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1322033.8653 | 2969340.8148 | 0 | 0 | 0 | 4291374.6801
سور نيو جيزة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2000533.8195 | 0 | 0 | 0 | -2000533.8195
Sub Total | 22248706.6452 | -9167761.516 | 49101584.5646 | -12544439.3027 | 2984511.6942 | -63812362.7118 | 16628286.5225 | -1292578.8664 | -194861910.1846 | 0 | 0 | 0 | -190715963.1549
Accrued Revenues
كباري مراسي pkg#37 | -101636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101636
اب تاون pkg#17 | 107619.49 | 0 | -159382 | 0 | 0 | -279041 | 0 | 0 | 0 | 0 | 0 | 0 | -330803.51
اب تاون pkg#32 | -254298 | 0 | 0 | 0 | 0 | -552505 | -286378.0758 | 0 | 0 | 0 | 0 | 0 | -1093181.0758
PKG#45 Civic Center | -1258165 | -308208 | -769574 | 0 | 0 | -245568 | -2103764 | 0 | 0 | 0 | 0 | 0 | -4685279
Limak | -1110732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1110732
Sodic West Town | -627547 | 0 | 0 | -754074 | 0 | 1855054.28 | -857110 | -1261971.4 | 0 | 0 | 0 | 0 | -1645648.12
New Cairo Mall | -3608866 | 0 | 0 | 0 | 0 | -4446863 | 0 | 0 | 0 | 0 | 0 | 0 | -8055729
El Wahatt | 1787461.1 | 0 | -1787461.1 | 0 | 0 | 0 | 0 | 1823216.79 | 0 | 0 | 0 | 0 | 1823216.79
Kasrawy II | 0 | 0 | -297233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -297233
ميناء دبى السخنة | 0 | 0 | -1173484 | -3109784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4283268
كوبري المحلة | 0 | 0 | 0 | 0 | 0 | -10440006 | 0 | 0 | 0 | 0 | 0 | 0 | -10440006
Sub Total | -5066163.41 | -308208 | -4187134.1 | -3863858 | 0 | -14108928.72 | -3247252.0758 | 561245.39 | 0 | 0 | 0 | 0 | -30220298.9158
Total | 17182543.2352 | -9475969.516 | 44914450.4646 | -16408297.3027 | 2984511.6942 | -77921291.4318 | 13381034.4467 | -731333.4764 | -194861910.1846 | 0 | 0 | 0 | -220936262.0707
Projects Direct Cost | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Construction Activities
Al Oula | 731358.21 | 817606.17 | 5343028.71 | 256267.43 | 1871064.56 | 1578517.73 | 172300.01 | 760262.63 | 478550.56 | 0 | 0 | 0 | 8753043.44
Hyper Al Sulaimaniya | 2354090.92 | 829489.38 | 616327.42 | 108256.64 | 253769.65 | 1071405.9 | 641857.42 | 1315046.84 | 5764603.41 | 0 | 0 | 0 | 10182576.1
New Giza I | 3533501.11 | 2217600.64 | 2657211.75 | 2957333.97 | 1172106.4 | 3507604.82 | 194877.98 | -833061.19 | 105062.49 | 0 | 0 | 0 | 13150561.67
Maxim mall | 2551727.6 | 3818299.91 | 7128164.09 | 1824723.04 | 4896898.31 | 7579153.31 | 1018681.21 | 2984691.57 | 7314860.44 | 0 | 0 | 0 | 30513256.2
Attaka | 3619725.03 | 3278087.63 | 781810.15 | 604382.12 | 2125477.55 | -3320116.48 | 293100.43 | 130541.56 | 849953.59 | 0 | 0 | 0 | 3548820.8
مول مصر | 10254611.17 | 4458658.14 | 7767090.57 | 4575909.32 | 15347030.12 | 4843430.26 | 1087274.8 | 4734158.77 | 3690228.54 | 0 | 0 | 0 | 44947831.12
مراسى تانك الخزان الجديد PKG22 New | 595102.86 | 355913.84 | 1326101.6 | 520565.52 | 526639.85 | 913310.65 | 1113637.14 | 667042.67 | 648432.4 | 0 | 0 | 0 | 3754742.61
نادي سوديك | 3593738.78 | 2608383.28 | 3289662.74 | 3064968.24 | 2713499.89 | 1682483.07 | 1189822.36 | 3298838.63 | 1548381.44 | 0 | 0 | 0 | 16499394.02
شرم الشيخ | 1567685.33 | 1600000.78 | 3073116.43 | 2272491.08 | 2400344.99 | 1431372.55 | 917294.7 | 1329049.08 | 1021182.71 | 0 | 0 | 0 | 8429457.29
عمائر اب تاون 53 | 5138272.57 | 6602814.02 | 11340463.66 | 7189360.68 | 8195770.8 | 4480556.14 | 4699712.84 | 8920161.68 | 6343828.9 | 0 | 0 | 0 | 41077090.18
New Giza phase 2 | 1922300.82 | 2356865.93 | 11102818 | 3086479.78 | 7512950.06 | 8521176.14 | 4053575.64 | 3013523.27 | 8111428.6 | 0 | 0 | 0 | 38591998.02
Beni suef | 8943070.81 | 11027017.59 | 38405998.1 | 19189273.21 | 22961115.57 | 15900729.4 | 14145495.51 | 10492846.42 | 10936677.93 | 0 | 0 | 0 | 113258196.21
كوبرى الشيخ بن زايد - كوبرى العاصمة | 2509072.44 | 3616132.37 | 3817926.79 | 5776615.76 | 5376530.79 | 16428060.21 | 7968852.21 | 11591311.41 | -396429.55 | 0 | 0 | 0 | 41627740.92
جبل الزيت - GAMISA | 428162.79 | 2555165.68 | 4094236.28 | 2020516.87 | 2895652.87 | 5875756.75 | 3775802.06 | 8555079.75 | 3410354.25 | 0 | 0 | 0 | 30939137.29
لوك اند لوت كوبرى الغرابلى - الاس | 0 | 0 | 0 | 10988 | 198394.21 | 60451.79 | 84385.46 | 151112.82 | 225750.37 | 0 | 0 | 0 | 327145.08
محطه كهرباء المستثمرين بالقطامي | 0 | 0 | 0 | 110378.77 | 1654599.63 | 2521562.73 | 1454789.84 | 2478313.52 | 2241287.57 | 0 | 0 | 0 | 7149920.45
PKG62 | 0 | 0 | 0 | 88761 | 170566 | 814893.08 | 453247.17 | 602710.73 | 593351.21 | 0 | 0 | 0 | 1680480.32
سور لوك اند لود ( اوراسكوم) | 0 | 0 | 0 | 0 | 185124.58 | 302166.06 | 82333.58 | 207367.23 | 82722.28 | 0 | 0 | 0 | 441710.28
مشروع الكيان | 0 | 0 | 0 | 0 | 0 | 0 | 8460923.82 | 7907818.65 | 12681658.01 | 0 | 0 | 0 | 24253615.36
مشروع الامل | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924567.64 | 2237252.82 | 0 | 0 | 0 | 2516989.22
مشروع مصنع الاسمنت بنى سويف | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1201191.62 | 5074433.32 | 0 | 0 | 0 | 3899115.93
سور نيو جيزة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268820.39 | 0 | 0 | 0 | 172387.39
Sub Total | 47742420.44 | 46142035.36 | 100743956.29 | 53657271.43 | 80457535.83 | 74192514.11 | 51807964.18 | 70432575.3 | 73232391.68 | 0 | 0 | 0 | 445715209.9
Closed Projects
كباري مراسي pkg#37 | 0 | 11317.87 | 62017 | 0 | 0 | 506.33 | 0 | -248430.71 | 0 | 0 | 0 | 0 | -244604.38
اب تاون pkg#17 | 248856.65 | 3203.47 | -228908.32 | 4565.63 | 3166.67 | 132212.28 | 3166.67 | 23499.24 | 3210.51 | 0 | 0 | 0 | 130786.8
اب تاون pkg#32 | 362029.54 | 199721.77 | 223402.45 | 104932.31 | 372390.8 | 100683.52 | 124539.23 | 42562.79 | 54611.31 | 0 | 0 | 0 | 841757.82
PKG#45 Civic Center | 768053.81 | 439971.19 | 852913.78 | 282463.31 | 544816.68 | 732243.41 | 787182.35 | 308796.18 | 255926.64 | 0 | 0 | 0 | 2438770.04
Limak | 439705 | 187720.9 | 202557.39 | 128107.53 | 59918.67 | -434247.49 | 88087.4 | 9802.77 | 18940.44 | 0 | 0 | 0 | -89635.02
Sodic West Town | 132805.94 | 178294.44 | 289575.26 | 254336.73 | 537986.57 | 293537.14 | 352518.6 | 260165.79 | 280649.49 | 0 | 0 | 0 | 1823938.85
New Cairo Mall | 274993.26 | 116410.23 | 488766.75 | 27239.66 | 562522.49 | -4927005.84 | 274847.64 | 28734.26 | 641.91 | 0 | 0 | 0 | -4850130.11
El Wahatt | 0 | 165336.07 | 125002.85 | 0 | 0 | 874447.42 | 11116.08 | 2789.48 | 0 | 0 | 0 | 0 | 477354.49
Kasrawy II | 0 | 0 | -254478.69 | 1554.06 | -31010.22 | -229930.62 | -94.86 | 20219.14 | 5957.61 | 0 | 0 | 0 | -509528.28
ميناء دبى السخنة | 833933.77 | 479294.04 | 971403.07 | 32161.25 | 343479.22 | 580871.54 | 72503.42 | 323900.48 | 3394.78 | 0 | 0 | 0 | 2609500.55 | [6 empty] | مشاريع عمليات منهيه
مشاريع منتهية | 8823 | 32612 | 1621668 | -177131.19 | 199298.22 | 5103340.49 | -62550 | -559974.07 | 432368.99 |  |  |  | 5231799.05 | [6 empty] | 2239498.45
Sub Total | 3069200.97 | 1813881.98 | 4353919.54 | 658229.29 | 2592569.1 | 2226658.18 | 1651316.53 | 212065.35 | 1055701.68 | 0 | 0 | 0 | 7860009.81
Trade Activities
ابناء مصر للتعمير | 197211.06 | 0 | 0 | 0 | 1008371.99 | 582393.26 | 0 | 482046.51 | 292 | 0 | 0 | 0 | 2270314.82
شركة الحلول | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 197211.06 | 0 | 0 | 0 | 1008371.99 | 582393.26 | 0 | 482046.51 | 292 | 0 | 0 | 0 | 2270314.82
Total | 51008832.47 | 47955917.34 | 105097875.83 | 54315500.72 | 84058476.92 | 77001565.55 | 53459280.71 | 71126687.16 | 74288385.36 | 0 | 0 | 0 | 455845534.53 | 455845534.68 | -0.15
Projects Indirect Cost | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Construction Overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG&A Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Activities
Al Oula | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hyper Al Sulaimaniya | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Giza I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maxim mall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Attaka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مول مصر | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مراسى تانك الخزان الجديد PKG22 New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
نادي سوديك | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
شرم الشيخ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
عمائر اب تاون 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Giza phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beni suef | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبرى الشيخ بن زايد - كوبرى العاصمة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
جبل الزيت - GAMISA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade Activities
كباري مراسي pkg#37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
اب تاون pkg#32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG#45 Civic Center | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Limak | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sodic West Town | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Cairo Mall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kasrawy II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Sheet1 (hidden)
Project | Before | After | Difference
Al Oula | 1387655.3607 | 1292955.5758 | -94699.7849
Hyper Al Sulaimaniya | -2313093.084 | -2343523.9379 | -30430.8539
New Giza I | -1883959.1515 | -1936670.5653 | -52711.4137
Maxim mall | -9910679.9288 | -10236108.5101 | -325428.5813
Attaka | 5338641.1104 | 5338641.1104 | 0
مول مصر | -46238835.3692 | -46492983.2905 | -254147.9213
مراسى تانك الخزان الجديد PKG22 New | 1314124.1103 | 1180960.7081 | -133163.4023
نادي سوديك | 2369926.5541 | 2110425.5677 | -259500.9865
شرم الشيخ | -2220526.1003 | -2332216.3692 | -111690.2688
عمائر اب تاون 53 | 8526669.2336 | 7966831.3339 | -559837.8996
New Giza phase 2 | 6465422.3531 | 6128032.9375 | -337389.4156
Beni suef | -16004976.8732 | -17700634.574 | -1695657.7007
كوبرى الشيخ بن زايد - كوبرى العاصمة | 4876021.5957 | 4713610.8598 | -162410.7359
جبل الزيت - GAMISA | -25951550.4939 | -26268282.7461 | -316732.2522
ميناء دبى السخنة | 0 | 0 | 0
PKG62 | 2920387.6741 | 2890782.9809 | -29604.6932
محطه كهرباء المستثمرين بالقطامي | 11792299.3871 | 11716195.0269 | -76104.3602
لوك اند لوت كوبرى الغرابلى - الاس | -2945158.1538 | -2945158.1538 | 0
سور لوك اند لود ( اوراسكوم) | -1608287.7747 | -1608287.7747 | 0
مشروع الكيان | 31510278.373 | 31441229.7401 | -69048.6329
مشروع كوبرى الامل | 3541793.9854 | 3541793.9854 | 0
مشروع مصنع الاسمنت | 6906965.182 | 6886757.4805 | -20207.7016
سور نيو جيزة | -1895925.7962 | -1895925.7962 | 0
كباري مراسي pkg#37 | -101636 | -101636 | 0
اب تاون pkg#17 | -159382 | -159382 | 0
اب تاون pkg#32 | -1093181.0758 | -1093181.0758 | 0
PKG#45 Civic Center | -4685279 | -4685279 | 0
Limak | -1110732 | -1110732 | 0
Sodic West Town | -94059.72 | -94059.72 | 0
New Cairo Mall | -8055729 | -8055729 | 0
El Wahatt | -304.21 | -304.21 | 0
Kasrawy II | -297233 | -297233 | 0
ميناء دبى السخنة | -4360665 | -4360665 | 0
كوبري المحلة | -10440006 | -10440006 | 0
-4528766.6047

## Revenue (hidden)
Total Revenue
Project | Amount
Al Oula | 13784839.5758
Hyper Al Sulaimaniya | 12467778.0621
New Giza I | 12649938.3747
Maxim mall | 39788654.1199
Attaka | 34232835.1104
مول مصر | 70893086.9995
مراسى تانك الخزان الجديد PKG22 New | 6916796.7081
نادي سوديك | 24185326.6277
شرم الشيخ | 17402196.6308
عمائر اب تاون 53 | 64473915.2539
New Giza phase 2 | 51990963.6175
Beni suef | 182307097.936
كوبرى الشيخ بن زايد - كوبرى العاصمة | 66898802.8598
جبل الزيت - GAMISA | 45271747.3039
ميناء دبى السخنة | 0
PKG62 | 2890782.9809
محطه كهرباء المستثمرين بالقطامي | 11716195.0269
لوك اند لوت كوبرى الغرابلى - الاس | 940857.2072
سور لوك اند لود ( اوراسكوم) | 1256956.2653
مشروع الكيان | 31441229.7401
مشروع كوبرى الامل | 3541793.9854
مشروع مصنع الاسمنت | 6886757.4805
سور نيو جيزة | 291609.4038
كباري مراسي pkg#37 | 0
اب تاون pkg#17 | 171421.51
اب تاون pkg#32 | 0
PKG#45 Civic Center | 0
Limak | 0
Sodic West Town | 3863872.28
New Cairo Mall | 0
El Wahatt | -1823521
Kasrawy II | 432205
ميناء دبى السخنة | 173122
كوبري المحلة | 4545402
ابناء مصر للتعمير | 6616932
شركة الحلول | 100950
Total | 716310545.0603

## Closed Project (hidden)
Description | Zaid II | Uptown Cairo PKG 17 | M.Bridges BP 37 | Uptown Cairo PK#32 | Marassi Civic center | Limak TB2 | Sodic West Town | NEW Cairo Mall | El Wahat Bridges | ميناء السخنة | Mahala Bridge | Total
Total Contract Price | 33013063.52 | 34941697 | 27187290 | 5814614.8 | 48864512 | 26717701 | 2317895 | 21944600 | 18275304 | 33120773 | 62700000 | 314897450.32
Additions (Deductions) | 31142049.05 | 21172701 | -993453.32 | 11606531 | 8066504 | 92909143 | 8393107 | 118818446.68 | 12969911.17 | 1427558.29 | 4545402 | 310057899.87
Total Contracts | 64155112.57 | 56114398 | 26193836.68 | 17421145.8 | 56931016 | 119626844 | 10711002 | 140763046.68 | 31245215.17 | 34548331.29 | 67245402 | 624955350.19
Total Estimated Cost Of contract | 31362410 | 33472697 | 22308006 | 5600000 | 47317785 | 25873305 | 1890000 | 20627924 | 13923981.6424 | 31906329.5113 | 52380210.3728 | 286662648.5265
Additional Cost ( Deductions) | 31873848.917 | 20370932.5863 | 5022596.3975 | 15451883.5147 | 17440462.2535 | 73125720.1825 | 8453299.9306 | 120736915.6778 | 4108764.8283 | -3916258.0275 | -4253378.3728 | 288414787.8878
Total Cost | 63236258.917 | 53843629.5863 | 27330602.3975 | 21051883.5147 | 64758247.2535 | 98999025.1825 | 10343299.9306 | 141364839.6778 | 18032746.4706 | 27990071.4837 | 48126832 | 575077436.4143
Gross Profit | 918853.653 | 2270768.4137 | -1136765.7175 | -3630737.7147 | -7827231.2535 | 20627818.8175 | 367702.0694 | -601792.9978 | 13212468.6994 | 6558259.8063 | 19118570 | 49877913.7757
Cost Incured previous years | 63714421.967 | 53403393.3863 | 27228966.3975 | 19958702.4389 | 55489926.2535 | 97888293.1825 | 5360605.9306 | 129215876.9678 | 19855963.2606 | 23456284.4837 | 33141424 | 528713858.2685
Cost Incured To Date | -478163.05 | 440236.2 | 101636 | 1093181.0758 | 9268321 | 1110732 | 4982694 | 12148962.71 | -1823216.79 | 4533787 | 14985408 | 46363578.1458
Percentage Of Completion Previous Year | 100.8% | 99.18% | 99.63% | 94.81% | 85.69% | 98.88% | 51.83% | 91.41% | 110.1% | 83.8% | 68.86% | 91.94%
Percentage Of Completion Current Year | -0.7562% | 0.8176% | 0.3719% | 5.193% | 14.31% | 1.122% | 48.17% | 8.594% | -10.11% | 16.2% | 31.14% | 8.062%
Percentage Of Completion YTD | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Total Revenue (Cost to Cost) | 64155112.57 | 56114398 | 26193836.68 | 17421145.8 | 56931016 | 119626844 | 10711002 | 140763046.68 | 31245215.17 | 34548331.29 | 67245402 | 624955350.19
2015 | 3194810.4186 | 102709.4615 | -1292773.3157 | 5035288 | 9301949.1009 | 43690841.286 | 3758653.9965 | 87671629.9991 | 25387385.17 | 32493559.29 | 23029153 | 232373206.4069
2014 | 12179303 | 13500605.22 | 4284475.42 | 6571243 | 30639867 | 49916369 | 1299177.65 | 55800337 | 7681350 | 2054772 | 39670847 | 223598346.29
2013 | 11807113 | 6744429.8861 | 13039380.4741 | 3806208.8454 | 15704328.6666 | 26019633.714 | 1338033.3535 | 1538958.6809 | 0 | 0 | 0 | 79998086.6205
2012 | 16043461.8114 | 28366450.4324 | 10162754.1017 | 2008405.9546 | 259786.2325 | 0 | 0 | 0 | 0 | 0 | 0 | 56840858.5326
2011 | 18454173 | 7191736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25645909
2010 | 2321139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2321139
Net Revenue 2016 | 155112.34 | 208467 | 0 | 1.1642e-09 | 1025085 | 7.4506e-09 | 4315137 | -4247879 | -1823520 | 0 | 4545402 | 4177804.34
| 4.992% | 0.1837% | -4.935% | 28.9% | 16.64% | 36.52% | 58.77% | 60.46% | 76.77% | 94.05% | 94.05% | 29.58%
Percentage Of Completion 30 dec 2016
Actual | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total
Revenue Recognition
Construction Activities
عملية الشيخ زايد - القصراوى المرحلة الثانية | 2016-02-01: 410860.16; 2016-03-01: 318577.71 | 729437.87
Uptown Cairo PKG 17 | 2016-03-01: 51762.39; 2016-06-01: 279041.25; 2016-12-01: 37044.71 | 367848.35
كبارى مراسى BP37 | 101636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101636
Uptown Cairo PKG 32 | 254298 | 0 | 0 | 0 | 0 | 552505 | 286378.0758 | 0 | 0 | 0 | 0 | 0 | 1093181.0758
سيفيك سنتر - Civic Center | 1258165 | 308208 | 769574 | 0 | 0 | 245568 | 2103764 | 0 | 0 | 3738398 | 0 | 844644 | 9268321
المطار TB2 | 1110732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110732
SODIC -WEST TOWN | 627547 | 0 | 397133 | 754074 | 0 | 1064039 | 857110 | 258029 | 0 | 1024762 | 0 | 0 | 4982694
New Cairo Mall | 3608866 | 0 | 0 | 0 | 0 | 4446863 | 0 | 0 | 0 | 0 | 4019369 | 73864.71 | 12148962.71
El Wahat Bridges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1823216.79 | 0 | 0 | 0 | 0 | -1823216.79
ميناء السخنة | 0 | 0 | 1173484 | 3109784 | 0 | 250519 | 0 | 0 | 0 | 0 | 0 | 0 | 4533787
كوبري المحلة | 0 | 0 | 0 | 0 | 0 | 14985408 | 0 | 0 | 0 | 0 | 0 | 0 | 14985408
Sub Total | 6961244 | 719068.16 | 2710531.1 | 3863858 | 0 | 6838535.25 | 3247252.0758 | -1565187.79 | 0 | 4763160 | 4019369 | 955553.42 | 47498791.2158
Trade Activities
هاى سيندا ابناء مصر للتعمير
سيتى للتنمية العقارية بارك فيو
EKO Tower ll - Nigeria
غير مستخدم
غير مستخدم
Sub Total
Total
POC | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total
Revenue Recognition
Construction Activities
عملية الشيخ زايد - القصراوى المرحلة الثانية | 2015-01-01: -574325.53; 2015-02-01: 0 | -574325.53
Uptown Cairo PKG 17 | 2015-01-01: -159381.35; 2015-02-01: 0 | -159381.35
كبارى مراسى BP37 | 2015-01-01: -101636; 2015-02-01: 0 | -101636
Uptown Cairo PKG 32 | 2015-01-01: -1093181.0758; 2015-02-01: 0 | -1093181.0758
سيفيك سنتر - Civic Center | 2015-01-01: -8243236; 2015-02-01: 0 | -8243236
المطار TB2 | 2015-01-01: -1110732; 2015-02-01: 0 | -1110732
SODIC -WEST TOWN | 2015-01-01: -667557; 2015-02-01: 0 | -667557
New Cairo Mall | 2015-01-01: -16396841.71; 2015-02-01: 0 | -16396841.71
El Wahat Bridges | 2015-01-01: -303.21; 2015-02-01: 0 | -303.21
ميناء السخنة | 2015-01-01: -4533787; 2015-02-01: 0 | -4533787
كوبري المحلة | 2015-01-01: -10440006; 2015-02-01: 0 | -10440006
Sub Total | -32880980.8758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43320986.8758
Trade Activities
هاى سيندا ابناء مصر للتعمير
سيتى للتنمية العقارية بارك فيو
EKO Tower ll - Nigeria
غير مستخدم
غير مستخدم
Sub Total
Total Actual Revenues | 6961244 | 719068.16 | 2710531.1 | 3863858 | 0 | 6838535.25 | 3247252.0758 | -1565187.79 | 0 | 4763160 | 4019369 | 955553.42 | 47498791.2158
POC Revenues | -25919736.8758 | 719068.16 | 2710531.1 | 3863858 | 0 | 6838535.25 | 3247252.0758 | -1565187.79 | 0 | 4763160 | 4019369 | 955553.42 | 4177804.34
Total Revenues | -58800717.7516 | 719068.16 | 2710531.1 | 3863858 | 0 | 6838535.25 | 3247252.0758 | -1565187.79 | 0 | 4763160 | 4019369 | 955553.42 | 4177804.34
Total
Projects Direct Cost | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | Total
Construction Activities
عملية الشيخ زايد - القصراوى المرحلة الثانية | 0 | 0 | -254478.69 | 1554.06 | -31010.22 | -229930.62 | -94.86 | 20219.14 | 5957.61 | 0 | 5658.53 | 3962 | -478163.05
Uptown Cairo PKG 17 | 248856.65 | 3203.47 | -228908.32 | 4565.63 | 3166.67 | 132212.28 | 3166.67 | 23499.24 | 3210.51 | 3420.61 | 14872.32 | 228970.47 | 440236.2
كبارى مراسى BP37 | 0 | 11317.87 | 62017 | 0 | 0 | 506.33 | 0 | -248430.71 | 0 | 0 | 0 | -239390.69 | -413980.2
Uptown Cairo PKG 32 | 362029.54 | 199721.77 | 223402.45 | 104932.31 | 372390.8 | 100683.52 | 124539.23 | 42562.79 | 35133.65 | 42447.48 | 40390.14 | 160910.03 | 1809143.71
سيفيك سنتر - Civic Center | 768053.81 | 439971.19 | 852913.78 | 282463.31 | 544816.68 | 732243.41 | 787182.35 | 308796.18 | 206854.98 | 45435.29 | 213085.06 | 81287.26 | 5263103.3
المطار TB2 | 439705 | 187720.9 | 202557.39 | 128107.53 | 59918.67 | -434247.49 | 88087.4 | 9802.77 | -10303.26 | 30697.58 | 13871.92 | 2511.8 | 718430.21
SODIC -WEST TOWN | 132805.94 | 178294.44 | 289575.26 | 254336.73 | 537986.57 | 293537.14 | 352518.6 | 260165.79 | 260976.91 | 140493.42 | 19056.24 | 81648.71 | 2801395.75
New Cairo Mall | 274993.26 | 116410.23 | 488766.75 | 27239.66 | 562522.49 | -4927005.84 | 274847.64 | 28734.26 | -22105.69 | 302.65 | 837432.75 | 100.4 | -2337761.44
El Wahat Bridges | 0 | 165336.07 | 125002.85 | 0 | 0 | 874447.42 | 11116.08 | 2789.48 | 0 | 0 | -180000 | 0 | 998691.9
ميناء السخنة | 833933.77 | 479294.04 | 971403.07 | 32161.25 | 343479.22 | 580871.54 | 72503.42 | 323900.48 | 1358.24 | 24034.63 | 14652.09 | 16050.98 | 3693642.73
كوبري المحلة | [12 empty] | 0
Sub Total | 3060377.97 | 1781269.98 | 2732251.54 | 835360.48 | 2393270.88 | -2876682.31 | 1713866.53 | 772039.42 | 481082.95 | 286831.66 | 979019.05 | 336050.96 | 12494739.11
Trade Activities
هاى سيندا ابناء مصر للتعمير | [12 empty] | 0
سيتى للتنمية العقارية بارك فيو | [12 empty] | 0
شركة القاسم | [12 empty] | 0
EKO Tower ll - Nigeria | [12 empty] | 0
غير مستخدم | [12 empty] | 0
غير مستخدم | [12 empty] | 0
غير مستخدم | [12 empty] | 0
مصروفات أخرى عمليات منتهية | [12 empty] | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 3060377.97 | 1781269.98 | 2732251.54 | 835360.48 | 2393270.88 | -2876682.31 | 1713866.53 | 772039.42 | 481082.95 | 286831.66 | 979019.05 | 336050.96 | 12494739.11

## Analysis (hidden)
Project | Amount
Al Oula | 155005.5621
Hyper Al Sulaimaniya | 3729742.3285
New Giza I | 509042.0612
Maxim mall | 5485567.2463
مول مصر | 9904897.1077
مراسى تانك الخزان الجديد PKG22 New | 1030634.5218
نادي سوديك | 27269283.9547
شرم الشيخ | -0.11922
عمائر اب تاون 53 | 91311833.3628
New Giza phase 2 | 44834715.7854
Beni suef | 98673825.2146
كوبرى الشيخ بن زايد - كوبرى العاصمة | -4933133.7525
جبل الزيت - GAMISA | 23879298.0576
لوك اند لوت كوبرى الغرابلى - الاس | -913384.408
محطه كهرباء المستثمرين بالقطامي | 67375728.5492
PKG62 | 14322414.1872
سور لوك اند لود ( اوراسكوم) | 1728503.4542
مشروع الكيان | 214923445.1242
مشروع كوبرى الامل | 12207980.7845
مشروع مصنع الاسمنت | 180755055.2746
سور نيو جيزة | 1638071.9609
Tamay Elamdeed substation (Alestom ) | 767099.79
Wind Farm KFW | 18398435.8716
Wind Farm FIEM | 62677225.9494
PKG 107 | 34004218.7522
Uturn - كباري الأسماعيلية | 21963134.6734
نفق العاصمة | 79016750.104
Bani Sweif substation (Alestom ) | 13236733.9882
محولات الاسماعيليه | 3903574.3231
مبنى وزارات الجيش | 76803996.9187
رويال سيتى | 11688982.4519
كوبرى شبرا بنها | 642642.2222
كوبري الأمل لوك لود | 7178400.8429
Hyper ismalia | 86674.9682
P.I.PARKS - SLP | 1727934.9153
Rolling Mills | 1140100.4725
ابناء مصر للتعمير | 5573460.0193
KAM | 144372
Total | 1132842264.5206

## Sheet2 (hidden)
Description | Total Contracts | Total Cost | Gross Margin |  | Margin |  | Gross Margin
Al Oula | 72946445.96 | 66087308.6012 | 6859137.3588 |  | -7582640 |  | -7582640 | 0
Hyper Al Sulaimaniya | 110450184.62 | 108679008.9749 | 1771175.6451 | Maxim mall | -2180122.49 |  | -4444872.0813 | -2264749.5913
New Giza I | 172216796.0405 | 173672666.3248 | -1455870.2843 |  | -673454.95 |  | -673455 | -0.05
Maxim mall | 95704579 | 100149451.0813 | -4444872.0813 |  | 280000 |  | 280000 | 0
Attaka | 184387980.81 | 97786625.9352 | 86601354.8748 | مراسى تانك الخزان الجديد PKG22 New | 294454.13 |  | 284688.7472 | -9765.3828
مول مصر | 166000000 | 139539959.4857 | 26460040.5143 |  | 387868.81 |  | 387868.781 | -0.029048
مراسى تانك الخزان الجديد PKG22 New | 17510059.28 | 17225370.5328 | 284688.7472 |  | 1591063.71 |  | 1591063.7149 | 0.0049271
نادي سوديك | 148488134 | 149161589 | -673455 |  | 2082432 |  | 2082432 | 0
شرم الشيخ | 33784495.5267 | 30373982.7996 | 3410512.7271 |  | 2414189.99 |  | 2414190 | 0.01
عمائر اب تاون 53 | 308751426 | 316334066 | -7582640 |  | 2715096 |  | 2715096 | 0
New Giza phase 2 | 153841650 | 151759218 | 2082432 |  | 3146954 |  | 3146954 | 0
Beni suef | 432591184 | 319810885 | 112780299 |  | 4116659.41 |  | 4116659.4056 | -0.004406
كوبرى الشيخ بن زايد - كوبرى العاصمة | 93729526.98 | 71382872.0783 | 22346654.9017 | مشروع الامل | 9340257.58 |  | 9280974.12 | -59283.46
جبل الزيت - GAMISA | 120340462.76 | 79910192.84 | 40430269.92 |  | 9925895.54 |  | 9925895.54 | 0
PKG62 | 44392025 | 41977835 | 2414190 |  | 10299248 |  | 10299248 | 0
محطه كهرباء المستثمرين بالقطامي | 129792183 | 86447848 | 43344335 |  | 11702539.61 |  | 11702539.6143 | 0.00435
لوك اند لوت كوبرى الغرابلى - الاس | 2983560 | 3161393.34 | -177833.34 |  | 11893825 |  | 11893825 | 0
سور لوك اند لود ( اوراسكوم) | 4776406 | 2477865.32 | 2298540.68 |  | 13250040 |  | 13250040 | 0
مشروع الكيان | 1124609030 | 1051496911 | 73112119 |  | 13875718 |  | 13875718 | 0
مشروع الامل | 28943151 | 19662176.88 | 9280974.12 |  | 15480364.55 |  | 15480365 | 0.45
مشروع مصنع الاسمنت | 269134670 | 247103063 | 22031607 |  | 22031606.6 |  | 22031607 | 0.4
سور نيو جيزة | 2648340.9749 | 1057277.26 | 1591063.7149 |  | 24791308.01 |  | 24791308 | -0.01
Tamay Elamdeed substation (Alestom ) | 108790091 | 95540051 | 13250040 | مول مصر | 26468038.75 |  | 26460040.5143 | -7998.2357
Wind Farm KFW | 23001621.88 | 13075726.34 | 9925895.54 |  | 28196642.1 |  | 28196641.6881 | -0.41192
Wind Farm FIEM | 71547614 | 42395913 | 29151701 |  | 29151701 |  | 29151701 | 0
PkG 107 | 54101395 | 43802147 | 10299248 | جبل الزيت - GAMISA | 40512663.77 |  | 40430269.92 | -82393.85
كباري الأسماعيلية | 55077947 | 43375407.3857 | 11702539.6143 |  | 43344335 |  | 43344335 | 0
نفق العاصمة | 412854534 | 318244664 | 94609870 | مبنى وزارات الجيش | 65995635.2 |  | 34495635 | -31500000.2
Bani Sweif substation (Alestom ) | 108790091 | 96896266 | 11893825 |  | 73112118.72 |  | 73112119 | 0.28
Ismalia substation (Alestom ) | 108790091 | 94914373 | 13875718 | Attaka | 87000000 |  | 86601354.8748 | -398645.1252
مبنى وزارات الجيش | 428626339 | 394130704 | 34495635 |  | 94609869.8 |  | 94609870 | 0.2
رويال سيتى | 409523809.836 | 381327168.1479 | 28196641.6881 |  | 112780299 |  | 112780299 | 0
كوبرى شبرا بنها | 2800000 | 2520000 | 280000 |  | 113887425.07 |  | 113887425 | -0.07
كوبري الأمل لوك لود | 9050320 | 6335224 | 2715096 |  | 864242031.91 | 0 | 829919196.8389 | -34322835.0711
Hyper ismalia | 51838240 | 47721580.5944 | 4116659.4056 |  |  |  |  | 0
P.I.PARKS - SLP | 32000000 | 31612131.219 | 387868.781 |  |  |  |  | 0
Rolling Mills | 264370000 | 150482575 | 113887425 |  |  |  |  | 0
Siemens | 311000000 | 295519635 | 15480365
PKG 117 | 39336927 | 36189973 | 3146954
Kayan Lock Load | 107782440 | 82991132 | 24791308
Total | 6317303751.6681 | 5452332237.1408 | 864971514.5273
Trial Balance

## Sheet3 (hidden)
| Margin | Gross Margin
Maxim mall | -2180122.49 | -4444872.0813 | -2264749.5913
مراسى تانك الخزان الجديد PKG22 New | 294454.13 | 284688.7472 | -9765.3828
مشروع الامل | 9340257.58 | 9280974.12 | -59283.46
مول مصر | 26468038.75 | 26460040.5143 | -7998.2357
جبل الزيت - GAMISA | 40512663.77 | 40430269.92 | -82393.85
مبنى وزارات الجيش | 65995635.2 | 34495635 | -31500000.2
Attaka | 87000000 | 86601354.8748 | -398645.1252

## 2022
Project | 0 | 0 | 0 | MAXM/MXCM/1305 | 0 | 0030 | EMAR/ITPR/11226 | 0032 | 0 | EMAR/SIER/1354 | NGZA/UNVI/1369 | Bani Suef | 0 | GMSA/GBLZ/1301 | Village E PKG#62 | 0040 | 0 | 0 | ARMY/KYAN/1446 | 0046 | [49 empty] | 0065 | 0069 | 0072 | 0071 | 0068 | 0074 | 0075 | 0076 | 0081 | 0079 | 0078 | 0080 | 0083 | 0084
Description | Kayan 3 New Cairo Capital City | Ministries Buildings | Royal City | Mohammed Ali Palace | R05 - Zone 2 | EDNC Offices & Retail Project | Olympic Multi Sports Hall | CFC Podium 2 | El Sewedy University phase II | Ring Road | Marassi PKG# 162 & 163 & 177 | Sultana Malak | New Giza Teaching Hospital | GOV2 - Infra | Cairo-Alex Railway | ORA ZED - Ph 01B - Pkgs A&D | Kattameya Creeks | Faculty of Medicine | Diplomatic District - Infra | ElSewedy HQ Internal Finishing | El Khatatba Bridge | EGAT Pelletizing Plant | Sokhna Port Expansion | MDF Factory | Kemet Building | Air Defense College | ORA ZED-Ph 2-Pkgs A&D | HST Bridges-Sokhna & Mahager | Abou Ghaleb Bridge | Egyptian Exchange Building | Port Said Port Silos | The Open Channel Project | Waldorf Astoria Cairo | Alamein Coastal Road Bridge | Wady El Natroon Bridge | HST El Mahager Bridge | HST Culverts | Mivida BP#189 | EDNC Hardscape Package | Egat Rolling Mill no.4 | EGAT Lock & Load | Qani bay Al rammah Mosque | October Under-Railway Tunnel | Radamis City | SODIC Allegria Villa f100 | El- Hussein Mosque | Jawhar Al-Lala Mosque | Beymen Fit Out | Astoria Sharm elSheikh | Wadi Halfa Port | SSC Suez Steel Company Project | Ora Zed Landscape Ph1 | L&L Awsaty Tunnel Extension | EIPICO | Ring Road - El Qawmiya | Ring Road - Service Road | Beni Suef | Darb Allabana Bldgs Ph1 | Creeks URBN-K | DP World Basin 2 Ph2 | Seashell Playa 5 Villas | Kafr Shoukr Bridge | Abo Shanab El Agamien | MAF HQ Renovation |  |  | Total | Lowest Task-Resource | RME Resource List
| ARMY/KYAN/1446 | 0060 | 0063 | 0078 | 0088 | 0092 | 0099 | 0113 | 0119 | 0122 | 0123 | 0124 | 0126 | 0133 | 0134 | 0137 | 0138 | 0139 | 0140 | 0141 | 0143 | 0144 | 0145 | 0147 | 0149 | 0150 | 0151 | 0152 | 0157 | 0158 | 0159 | 0160 | 0164 | 0166 | 0167 | 0168 | 0169 | 0170 | 0171 | 0172 | 0173 | 0174 | 0175 | 0176 | 0177 | 0178 | 0179 | 0181 | 0182 | 0183 | 0184 | 0185 | 0186 | 0187 | 0188 | 0189 | 0061 | 0191 | 0192 | 0193 | 0194 | 0130 | 0195 | 0196
Contracts | 1316334942 | 2740570200 | 558284383 | 141426555.5714 | 2873373384.4671 | 1145187121 | 1165356801.5 | 637419839.0635 | 608748209 | 796372414.62 | 850000000 | 160759162.8571 | 573740474.5819 | 1178424708 | 1019596481 | 952143211 | 1462000000 | 590625262.5 | 651431108 | 362983478.4 | 182323080.9524 | 420000000 | 1154780430 | 440260342 | 76400000 | 1196035850.18 | 946341608 | 366245749.5238 | 336195666.6667 | 312773042.4286 | 420476403 | 803202543.8095 | 210726576 | 284814771.4286 | 583362277.3333 | 136262391.4286 | 41932924.7619 | 948571429 | 71569048 | 388375223 | 50000000 | 11588673.4286 | 56233741 | 147053342 | 7061113.1 | 5648468.5714 | 11196893.0667 | 4338449 | 5331005.13 | 142857142 | 205575060 | 90188424 | 1250000 | 399562505 | 189000000 | 80500000 | 123882330 | 12967470.4762 | 666564349.52 | 412678626 | 1960330 | 126172624 | 320543982.6 | 21974136 |  |  | 32199555758.9672
Contracts | 1316334942 | 2740570200 | 558284383 | 141426555.5714 | 2873373384.4671 | 1145187121 | 1165356801.5 | 637419839.0635 | 608748209 | 796372414.62 | 850000000 | 160759162.8571 | 573740474.5819 | 1178424708 | 1019596481 | 952143211 | 1462000000 | 590625262.5 | 651431108 | 362983478.4 | 182323080.9524 | 420000000 | 1154780430 | 440260342 | 76400000 | 1196035850.18 | 946341608 | 366245749.5238 | 336195666.6667 | 312773042.4286 | 420476403 | 803202543.8095 | 210726576 | 284814771.4286 | 583362277.3333 | 136262391.4286 | 41932924.7619 | 948571429 | 71569048 | 388375223 | 50000000 | 11588673.4286 | 56233741 | 147053342 | 7061113.1 | 5648468.5714 | 11196893.0667 | 4338449 | 5331005.13 | 142857142 | 205575060 | 90188424 | 1250000 | 399562505 | 189000000 | 80500000 | 123882330 | 12967470.4762 | 666564349.52 | 412678626 | 1960330 | 126172624 | 320543982.6 | 21974136 | 0 | 0 | 32199555758.9672
0
Total Budget Cost | 1278573760.514 | 2692610221.5 | 532547472.9437 | 134355227.7929 | 2830272783.7001 | 1079069736 | 1124569313.4475 | 473408781.0473 | 509609475.829 | 740626345.5966 | 663000000 | 141468063.3143 | 550790855.5986 | 1143071966.76 | 831265079 | 904536050.45 | 1352350000 | 554538058.9612 | 609120657.4889 | 339906920.28 | 181708989.806 | 390600000 | 1073945799.9 | 422649928.32 | 75254000 | 1154174595.4237 | 922683067.8 | 351595919.5429 | 312661970 | 294006659.8829 | 403657346.88 | 761516331.7858 | 208619310 | 265495408.69 | 542526917.92 | 125361400.1143 | 41932924.7619 | 901142857.55 | 68706287 | 364101771.5625 | 46500000 | 10661579.5543 | 49485692 | 135289074.64 | 6002000 | 5083621.7143 | 10077203.76 | 3904604.1 | 4797904.617 | 128714278 | 185017554 | 84991316 | 1112500 | 377586567 | 175770000 | 74865000 | 100752128.439 | 11670723.4286 | 611372821.3797 | 337003683 | 2442662.13 | 118744467 | 300029167.71 | 20796322.7141 |  |  | 30150703128.3509
Total Cost | 1278573760.514 | 2692610221.5 | 532547472.9437 | 134355227.7929 | 2830272783.7001 | 1079069736 | 1124569313.4475 | 473408781.0473 | 509609475.829 | 740626345.5966 | 663000000 | 141468063.3143 | 550790855.5986 | 1143071966.76 | 831265079 | 904536050.45 | 1352350000 | 554538058.9612 | 609120657.4889 | 339906920.28 | 181708989.806 | 390600000 | 1073945799.9 | 422649928.32 | 75254000 | 1154174595.4237 | 922683067.8 | 351595919.5429 | 312661970 | 294006659.8829 | 403657346.88 | 761516331.7858 | 208619310 | 265495408.69 | 542526917.92 | 125361400.1143 | 41932924.7619 | 901142857.55 | 68706287 | 364101771.5625 | 46500000 | 10661579.5543 | 49485692 | 135289074.64 | 6002000 | 5083621.7143 | 10077203.76 | 3904604.1 | 4797904.617 | 128714278 | 185017554 | 84991316 | 1112500 | 377586567 | 175770000 | 74865000 | 100752128.439 | 11670723.4286 | 611372821.3797 | 337003683 | 2442662.13 | 118744467 | 300029167.71 | 20796322.7141 | 0 | 0 | 30150703128.3509
Gross Margin | 37761181.486 | 47959978.5 | 25736910.0563 | 7071327.7786 | 43100600.767 | 66117385 | 40787488.0525 | 164011058.0162 | 99138733.171 | 55746069.0234 | 187000000 | 19291099.5429 | 22949618.9833 | 35352741.24 | 188331402 | 47607160.55 | 109650000 | 36087203.5388 | 42310450.5111 | 23076558.12 | 614091.1464 | 29400000 | 80834630.1 | 17610413.68 | 1146000 | 41861254.7563 | 23658540.2 | 14649829.981 | 23533696.6667 | 18766382.5457 | 16819056.12 | 41686212.0237 | 2107266 | 19319362.7386 | 40835359.4133 | 10900991.3143 | 0 | 47428571.45 | 2862761 | 24273451.4375 | 3500000 | 927093.8743 | 6748049 | 11764267.36 | 1059113.1 | 564846.8571 | 1119689.3067 | 433844.9 | 533100.513 | 14142864 | 20557506 | 5197108 | 137500 | 21975938 | 13230000 | 5635000 | 23130201.561 | 1296747.0476 | 55191528.1403 | 75674943 | -482332.13 | 7428157 | 20514814.89 | 1177813.2859 | 0 | 0 | 2048852630.6163
Gross Margin % | 2.869% | 1.75% | 4.61% | 5% | 1.5% | 5.774% | 3.5% | 25.73% | 16.29% | 7% | 22% | 12% | 4% | 3% | 18.47% | 5% | 7.5% | 6.11% | 6.495% | 6.357% | 0.3368% | 7% | 7% | 4% | 1.5% | 3.5% | 2.5% | 4% | 7% | 6% | 4% | 5.19% | 1% | 6.783% | 7% | 8% | 0% | 5% | 4% | 6.25% | 7% | 8% | 12% | 8% | 15% | 10% | 10% | 10% | 10% | 9.9% | 10% | 5.763% | 11% | 5.5% | 7% | 7% | 0% | 10% | 8.28% | 18.34% | -24.6% | 2.147% | 6.4% | 5.36% |  |  | 6.363%
Cost Incured previous years | 1263499617.734 | 2549259624.3335 | 501618019.1968 | 129266614.516 | 1696219788.9098 | 1063500266.6138 | 994380345.114 | 467108794.124 | 513109475.829 | 653313576.67 | 506868500.88 | 120855140.7 | 295753594.27 | 466188793.561 | 685814718.5 | 659536506.15 | 794715230.84 | 272679600.562 | 358366498.77 | 281765408.09 | 164962522.386 | 278659036.6491 | 583736515.8238 | 283623464.78 | 66948216.47 | 670242092.99 | 328995233.264 | 215806196.58 | 78208312.465 | 155810091.96 | 62017325.22 | 199182202.37 | 130600414.76 | 264109896.99 | 59080455.727 | 47634625.98 | 32005591.28 | 223255351.656 | 48970021.15 | 123727878.54 | 20599599.75 | 5744071.11 | 15371373.6 | 47309038.37 | 4356820.89 | 2633556.41 | 2691724.67 | 3360157.63 | 2751558.25 | 11673560.9 | 30457847.58 | 3651270.82 | 318051.141 | 14889360.024 | 24570.54 | 2315228.79 | 100752128.439 | 101454.69 | 0 | 398754.59 | 238411.24 | 116604507.683 |  |  |  |  | 18677638609.5218
Cost Incured To Date | 15074142.78 | 81739722.36 | 1584919.49 | 301540.51 | 72036212.01 | 399500.17 | 28443558.28 | 164049.42 | -3500000 | 9315181.44 | 27354679.82 | 677109.02 | 55049581.84 | 60923705.7 | 18942711.47 | 85009205.27 | 130245855.98 | 31885516.24 | 26140943.86 | 31640034.34 | 16746467.42 | 74950829.99 | 248095896.677 | 95220500.35 | 4961437.55 | 172313503.25 | 52752817.99 | 74691713.83 | 53433935.8 | 33560112.32 | 17992222.45 | 60373377.1 | 71803352.67 | 1385511.7 | 54462620.45 | 38414699.03 | 1408825.25 | 76389347.62 | 1567744.01 | 68122924.94 | 4392635.07 | 1754425.83 | 1841157.72 | 20146005.69 | 299355.16 | 17359.22 | 721237.56 | 142737.61 | 1462312.43 | 13661325.67 | 92481047.27 | 14942022.52 | 43317.12 | 30821180.57 | 385522.61 | 14264205.94 | 0 | -26167.2 | 4178726.21 | 22074973.18 | 2204250.89 | 50000 | 3030306.91 | 11298156.5 | 0 | 0 | 2132262104.877
Percentage Of Completion Previous Year | 98.82% | 94.68% | 94.19% | 96.21% | 59.93% | 98.56% | 88.42% | 98.67% | 100.7% | 88.21% | 76.45% | 85.43% | 53.7% | 40.78% | 82.5% | 72.91% | 58.77% | 49.17% | 58.83% | 82.89% | 90.78% | 71.34% | 54.35% | 67.11% | 88.96% | 58.07% | 35.66% | 61.38% | 25.01% | 53% | 15.36% | 26.16% | 62.6% | 99.48% | 10.89% | 38% | 76.33% | 24.77% | 71.27% | 33.98% | 44.3% | 53.88% | 31.06% | 34.97% | 72.59% | 51.8% | 26.71% | 86.06% | 57.35% | 9.069% | 16.46% | 4.296% | 28.59% | 3.943% | 0.01398% | 3.093% | 100% | 0.8693% | 0% | 0.1183% | 9.76% | 98.2% | 0% | 0% |  |  | 61.95%
Percentage Of Completion Current Year | 1.179% | 3.036% | 0.2976% | 0.2244% | 2.545% | 0.03702% | 2.529% | 0.03465% | -0.6868% | 1.258% | 4.126% | 0.4786% | 9.995% | 5.33% | 2.279% | 9.398% | 9.631% | 5.75% | 4.292% | 9.308% | 9.216% | 19.19% | 23.1% | 22.53% | 6.593% | 14.93% | 5.717% | 21.24% | 17.09% | 11.41% | 4.457% | 7.928% | 34.42% | 0.5219% | 10.04% | 30.64% | 3.36% | 8.477% | 2.282% | 18.71% | 9.447% | 16.46% | 3.721% | 14.89% | 4.988% | 0.3415% | 7.157% | 3.656% | 30.48% | 10.61% | 49.99% | 17.58% | 3.894% | 8.163% | 0.2193% | 19.05% | 0% | -0.2242% | 0.6835% | 6.55% | 90.24% | 0.04211% | 1.01% | 54.33% |  |  | 7.072%
Percentage Of Completion YTD | 100% | 97.71% | 94.49% | 96.44% | 62.48% | 98.59% | 90.95% | 98.7% | 100% | 89.47% | 80.58% | 85.91% | 63.69% | 46.11% | 84.78% | 82.31% | 68.4% | 54.92% | 63.13% | 92.2% | 100% | 90.53% | 77.46% | 89.64% | 95.56% | 73% | 41.37% | 82.62% | 42.1% | 64.41% | 19.82% | 34.08% | 97.02% | 100% | 20.93% | 68.64% | 79.69% | 33.25% | 73.56% | 52.69% | 53.75% | 70.33% | 34.78% | 49.86% | 77.58% | 52.15% | 33.87% | 89.71% | 87.83% | 19.68% | 66.45% | 21.88% | 32.48% | 12.11% | 0.2333% | 22.15% | 100% | 0.6451% | 0.6835% | 6.669% | 100% | 98.24% | 1.01% | 54.33% |  |  | 69.02%
Total Revenue (Cost to Cost) | 1316334942 | 2677861930.4768 | 527521688.5279 | 136387531.6063 | 1795183757.279 | 1129087648.6556 | 1059921143.4135 | 629158124.3416 | 608748209 | 712504040.9785 | 684901513.7179 | 138104829.2273 | 365419975.1146 | 543414947.6918 | 864427261.1818 | 783732327.8105 | 999957931.6973 | 324385042.9247 | 411215916.4316 | 334682793.5984 | 182323080.9524 | 380225663.0528 | 894443454.3019 | 394629130.3437 | 73004724.8934 | 873114607.5026 | 391536462.8246 | 302601990.0104 | 141550804.586 | 201457664.1277 | 83343278.8229 | 273763927.2967 | 204448250.1645 | 284814771.4286 | 122089329.2226 | 93531875.0109 | 33414416.53 | 315415472.9221 | 52643504.6701 | 204640857.0453 | 26873370.7742 | 8150540.1522 | 19559694.7134 | 73320700.0652 | 5477805.0154 | 2945461.8111 | 3792180.2556 | 3892105.8222 | 4682078.5333 | 28118632.5598 | 136598772.0556 | 19730248.9504 | 406031.7539 | 48370942.4563 | 440960.3763 | 17827349.172 | 123882330 | 83652.7667 | 4555959.6707 | 27520254.4217 | 1960330 | 123951925.573 | 3237507.3825 | 11938034.9542 |  |  | 22243261690.6204
Till 2022 | 1308091105.8551 | 2594666284.3089 | 525860173.1804 | 136070120.5432 | 1722050547.1165 | 1114207784.1831 | 1030445953.486 | 628937240.4901 | 605391865.4846 | 702487716.8495 | 649831411.3846 | 137335387.1591 | 308076660.6979 | 480607003.6711 | 821334992.2156 | 694248953.8421 | 859151600.9081 | 290424539.9531 | 383259182.7146 | 304611251.9892 | 171835960.8188 | 299633372.741 | 627673672.9288 | 295441109.1458 | 67967732.4569 | 694551391.6995 | 337431008.4759 | 224798121.4375 | 84094959.6398 | 165755416.9787 | 64601380.4375 | 210085647.4739 | 136754361.0052 | 283989136.5484 | 63527371.7495 | 51776767.3696 | 34788686.1739 | 235005633.3221 | 51010438.0149 | 131976403.776 | 22150107.2581 | 6243555.5543 | 17467470.0282 | 51422867.7935 | 5125625.6349 | 2926173.7889 | 2990805.1889 | 3733508.4778 | 3057286.9444 | 12956228.1128 | 33842052.8667 | 3874541.2632 | 357360.8326 | 15755936.5427 | 26419.9355 | 2489493.3226 | 120156139.33 | 112727.4333 | 0 | 488295.8395 | 256356.2986 | 119162685.331 |  |  |  |  | 19954383986.004
0
0
0
0
0
0
0
POC Revenues Up To date | 8243836.1449 | 83195646.1679 | 1661515.3475 | 317411.0632 | 73133210.1624 | 14879864.4725 | 29475189.9275 | 220883.8515 | 3356343.5154 | 10016324.129 | 35070102.3333 | 769442.0682 | 57343314.4167 | 62807944.0206 | 43092268.9662 | 89483373.9684 | 140806330.7892 | 33960502.9716 | 27956733.7169 | 30071541.6092 | 10487120.1336 | 80592290.3118 | 266769781.3731 | 99188021.1979 | 5036992.4365 | 178563215.8031 | 54105454.3487 | 77803868.5729 | 57455844.9462 | 35702247.1489 | 18741898.3854 | 63678279.8228 | 67693889.1593 | 825634.8802 | 58561957.4731 | 41755107.6413 | -1374269.6439 | 80409839.6 | 1633066.6552 | 72664453.2693 | 4723263.5161 | 1906984.5978 | 2092224.6852 | 21897832.2717 | 352179.3805 | 19288.0222 | 801375.0667 | 158597.3444 | 1624791.5889 | 15162404.4471 | 102756719.1889 | 15855707.6873 | 48670.9213 | 32615005.9136 | 414540.4409 | 15337855.8495 | 3726190.67 | -29074.6667 | 4555959.6707 | 27031958.5822 | 1703973.7014 | 4789240.242 | 3237507.3825 | 11938034.9542 | 0 | 0 | 2288877704.6164
Actual Revenues | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | Total
Revenue Recognition
Construction Activities
Kayan 3 New Cairo Capital City | [12 empty] | 0
Ministries Buildings | [12 empty] | 0
Royal City | [12 empty] | 0
Mohamed Ali Palace Restoration | [12 empty] | 0
NUCA R05 - Z02 | [12 empty] | 0
EDNC Retail & Offices Civil | [12 empty] | 0
Olympic Multi – Sports Hall | [12 empty] | 0
CFC Podium 2 | [12 empty] | 0
ElSewedy HQ Internal Finishing | [12 empty] | 0
RING ROAD MARYOTIA EXPANSION | [12 empty] | 0
EMAAR-Pkg#162/163- Marassi | [12 empty] | 0
Sultana Malak Restoration | [12 empty] | 0
New Giza Teaching Hospital | [12 empty] | 0
GOV2 - Infra | [12 empty] | 0
Cairo-Alex Railway | [12 empty] | 0
ORA ZED - Ph 01B - Pkgs A&D | [12 empty] | 0
Kattameya Creeks | [12 empty] | 0
Faculty of Medicine | [12 empty] | 0
Diplomatic District - Infra | [12 empty] | 0
ElSewedy HQ Internal Finishing | [12 empty] | 0
El Khatatba Bridge | [12 empty] | 0
EGAT Pelletizing Plant | [12 empty] | 0
Sokhna Port Expansion | [12 empty] | 0
MDF Factory | [12 empty] | 0
Kemet Building | [12 empty] | 0
Air Defense College | [12 empty] | 0
ORA ZED-Ph 2-Pkgs A&D | [12 empty] | 0
HST Bridges-Sokhna & Mahager | [12 empty] | 0
Abou Ghaleb Bridge | [12 empty] | 0
Egyptian Exchange Building | [12 empty] | 0
Port Said Port Silos | [12 empty] | 0
The Open Channel Project | [12 empty] | 0
Waldorf Astoria Cairo | [12 empty] | 0
Alamein Coastal Road Bridge | [12 empty] | 0
Wady El Natroon Bridge | [12 empty] | 0
HST El Mahager Bridge | [12 empty] | 0
HST Culverts | [12 empty] | 0
Mivida BP#189 | [12 empty] | 0
EDNC Hardscape Package | [12 empty] | 0
Egat Rolling Mill no.4 | [12 empty] | 0
EGAT Lock & Load | [12 empty] | 0
Qani bay Al rammah Mosque | [12 empty] | 0
October Under-Railway Tunnel | [12 empty] | 0
Radamis City | [12 empty] | 0
SODIC Allegria Villa f100 | [12 empty] | 0
El- Hussein Mosque | [12 empty] | 0
Jawhar Al-Lala Mosque | [12 empty] | 0
Beymen Fit Out | [12 empty] | 0
Astoria Sharm elSheikh | [12 empty] | 0
Wadi Halfa Port | [12 empty] | 0
SSC Suez Steel Company Project | [12 empty] | 0
Ora Zed Landscape Ph1 | [12 empty] | 0
L&L El-Awsaty Tunnel | [12 empty] | 0
EPICO 3 Facility | [12 empty] | 0
Ring Road - El Qawmiya | [12 empty] | 0
Ring Road - Service Road | [12 empty] | 0
Sahary El AhramTunnel | [12 empty] | 0
Darb Allabana Bldgs Ph1 | [12 empty] | 0
Creeks URBN-K | [12 empty] | 0
DP World Basin 2 Ph2 | [12 empty] | 0
Seashell Playa 5 Villas | [12 empty] | 0
0
0
0
0
0
0
0
0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closed Projects
0
El-mostaqbal | [12 empty] | 0
0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade Activities
0
0
0
0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Actual Revenues | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
POC Revenues | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenues | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenues | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | Total
Revenue Recognition
Construction Activities
Kayan 3 New Cairo Capital City | [12 empty] | 0
Ministries Buildings | [12 empty] | 0
Royal City | [12 empty] | 0
Mohammed Ali Palace | [12 empty] | 0
R05 - Zone 2 | [12 empty] | 0
EDNC Offices & Retail Project | [12 empty] | 0
Olympic Multi Sports Hall | [12 empty] | 0
CFC Podium 2 | [12 empty] | 0
El Sewedy University phase II | [12 empty] | 0
Ring Road | [12 empty] | 0
Marassi PKG# 162 & 163 & 177 | [12 empty] | 0
Sultana Malak | [12 empty] | 0
New Giza Teaching Hospital | [12 empty] | 0
GOV2 - Infra | [12 empty] | 0
Cairo-Alex Railway | [12 empty] | 0
ORA ZED - Ph 01B - Pkgs A&D | [12 empty] | 0
Kattameya Creeks | [12 empty] | 0
Faculty of Medicine | [12 empty] | 0
Diplomatic District - Infra | [12 empty] | 0
ElSewedy HQ Internal Finishing | [12 empty] | 0
El Khatatba Bridge | [12 empty] | 0
EGAT Pelletizing Plant | [12 empty] | 0
Sokhna Port Expansion | [12 empty] | 0
MDF Factory | [12 empty] | 0
Kemet Building | [12 empty] | 0
Air Defense College | [12 empty] | 0
ORA ZED-Ph 2-Pkgs A&D | [12 empty] | 0
HST Bridges-Sokhna & Mahager | [12 empty] | 0
Abou Ghaleb Bridge | [12 empty] | 0
Egyptian Exchange Building | [12 empty] | 0
Port Said Port Silos | [12 empty] | 0
The Open Channel Project | [12 empty] | 0
Waldorf Astoria Cairo | [12 empty] | 0
Alamein Coastal Road Bridge | [12 empty] | 0
Wady El Natroon Bridge | [12 empty] | 0
HST El Mahager Bridge | [12 empty] | 0
HST Culverts | [12 empty] | 0
Mivida BP#189 | [12 empty] | 0
EDNC Hardscape Package | [12 empty] | 0
Egat Rolling Mill no.4 | [12 empty] | 0
EGAT Lock & Load | [12 empty] | 0
Qani bay Al rammah Mosque | [12 empty] | 0
October Under-Railway Tunnel | [12 empty] | 0
Radamis City | [12 empty] | 0
SODIC Allegria Villa f100 | [12 empty] | 0
El- Hussein Mosque | [12 empty] | 0
Jawhar Al-Lala Mosque | [12 empty] | 0
Beymen Fit Out | [12 empty] | 0
Astoria Sharm elSheikh | [12 empty] | 0
Wadi Halfa Port | [12 empty] | 0
SSC Suez Steel Company Project | [12 empty] | 0
Ora Zed Landscape Ph1 | [12 empty] | 0
L&L Awsaty Tunnel Extension | [12 empty] | 0
EIPICO | [12 empty] | 0
Ring Road - El Qawmiya | [12 empty] | 0
Ring Road - Service Road | [12 empty] | 0
Sahary El AhramTunnel | [12 empty] | 0
Darb Allabana Bldgs Ph1 | [12 empty] | 0
Creeks URBN-K | [12 empty] | 0
DP World Basin 2 Ph2 | [12 empty] | 0
Seashell Playa 5 Villas | [12 empty] | 0
0
0
0
0
0
0
0
0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Accrued Revenues
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projects Direct Cost | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | Total
Construction Activities
Kayan 3 New Cairo Capital City | 2021-01-01: 936711.98; 2021-02-01: 13481367.46; 2021-03-01: 570464.44; 2021-04-01: 85598.9 | 15074142.78
Ministries Buildings | 2021-01-01: 5044866.33; 2021-02-01: 30962202.86; 2021-03-01: 3256962.2; 2021-04-01: 42475690.97 | 81739722.36
Royal City | 2021-01-01: 737673.76; 2021-02-01: 455351.29; 2021-03-01: 196241.85; 2021-04-01: 195652.59 | 1584919.49
Mohamed Ali Palace Restoration | 2021-01-01: 18843.02; 2021-02-01: 12617.56; 2021-03-01: 25141.24; 2021-04-01: 244938.69 | 301540.51
NUCA R05 - Z02 | 2021-01-01: 20169755.75; 2021-02-01: 17701109.89; 2021-03-01: 18897946.17; 2021-04-01: 15267400.2 | 72036212.01
EDNC Retail & Offices Civil | 2021-01-01: -4907606.74; 2021-02-01: 4726159.2; 2021-03-01: 345371.01; 2021-04-01: 235576.7 | 399500.17
Olympic Multi – Sports Hall | 2021-01-01: 7534348.57; 2021-02-01: 9179426.8; 2021-03-01: 7252198.72; 2021-04-01: 4477584.19 | 28443558.28
CFC Podium 2 | 2021-01-01: 133396.91; 2021-02-01: 5229.51; 2021-03-01: 20406; 2021-04-01: 5017 | 164049.42
ESU Ph2-Enabling & Struc | 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: -3500000; 2021-04-01: 0 | -3500000
RING ROAD MARYOTIA EXPANSION | 2021-01-01: 2593559.14; 2021-02-01: 1634068.13; 2021-03-01: 4579600.74; 2021-04-01: 507953.43 | 9315181.44
EMAAR-Pkg#162/163- Marassi | 2021-01-01: 7390757.11; 2021-02-01: 5725950.83; 2021-03-01: 6159984.38; 2021-04-01: 8077987.5 | 27354679.82
Sultana Malak Restoration | 2021-01-01: 206601.12; 2021-02-01: 1358.9; 2021-03-01: 929; 2021-04-01: 468220 | 677109.02
New Giza Teaching Hospital | 2021-01-01: 11479645; 2021-02-01: 12195385.34; 2021-03-01: 20576356.6; 2021-04-01: 10798194.9 | 55049581.84
GOV2 - Infra | 2021-01-01: 4171282.41; 2021-02-01: 5680680.06; 2021-03-01: 47069990.08; 2021-04-01: 4001753.15 | 60923705.7
Cairo-Alex Railway | 2021-01-01: 9869881.61; 2021-02-01: 7995440.72; 2021-03-01: 439093.25; 2021-04-01: 638295.89 | 18942711.47
ORA ZED - Ph 01B - Pkgs A&D | 2021-01-01: 18780845.91; 2021-02-01: 19140158.48; 2021-03-01: 29062518.16; 2021-04-01: 18025682.72 | 85009205.27
Kattameya Creeks | 2021-01-01: 19971783.95; 2021-02-01: 56450549.54; 2021-03-01: 34601673.94; 2021-04-01: 19221848.55 | 130245855.98
Faculty of Medicine | 2021-01-01: 6088630.18; 2021-02-01: 11578375.23; 2021-03-01: 9294941.54; 2021-04-01: 4923569.29 | 31885516.24
Diplomatic District - Infra | 2021-01-01: 9934567.51; 2021-02-01: 5373546.62; 2021-03-01: 6830030.8; 2021-04-01: 4002798.93 | 26140943.86
ElSewedy HQ Internal Finishing | 2021-01-01: 6152223.04; 2021-02-01: 16993342.21; 2021-03-01: 5416507.16; 2021-04-01: 3077961.93 | 31640034.34
El Khatatba Bridge | 2021-01-01: 3820251.01; 2021-02-01: 3005495.68; 2021-03-01: 1940360.62; 2021-04-01: 7980360.11 | 16746467.42
EGAT Pelletizing Plant | 2021-01-01: 18184809.79; 2021-02-01: 20268024.48; 2021-03-01: 23416189.42; 2021-04-01: 13081806.3 | 74950829.99
Sokhna Port Expansion | 2021-01-01: 65824768.547; 2021-02-01: 59015347.86; 2021-03-01: 77060710.27; 2021-04-01: 46195070 | 248095896.677
MDF Factory | 2021-01-01: 24682218.83; 2021-02-01: 32192376.05; 2021-03-01: 16506261.05; 2021-04-01: 21839644.42 | 95220500.35
Kemet Building | 2021-01-01: 2410864.45; 2021-02-01: 1925395.03; 2021-03-01: 594357.38; 2021-04-01: 30820.69 | 4961437.55
Air Defense College | 2021-01-01: 45571391.2; 2021-02-01: 34853726.83; 2021-03-01: 59808709.42; 2021-04-01: 32079675.8 | 172313503.25
ORA ZED-Ph 2-Pkgs A&D | 2021-01-01: 13111621.48; 2021-02-01: 12712051.78; 2021-03-01: 19911937.26; 2021-04-01: 7017207.47 | 52752817.99
HST Bridges-Sokhna & Mahager | 2021-01-01: 21249378.3; 2021-02-01: 18980504.97; 2021-03-01: 22195971.37; 2021-04-01: 12265859.19 | 74691713.83
Abou Ghaleb Bridge | 2021-01-01: 6092414.27; 2021-02-01: 10719333.92; 2021-03-01: 14767288.78; 2021-04-01: 21854898.83 | 53433935.8
Egyptian Exchange Building | 2021-01-01: 10285640.27; 2021-02-01: 6212807.7; 2021-03-01: 9362077.18; 2021-04-01: 7699587.17 | 33560112.32
Port Said Port Silos | 2021-01-01: 8734969.54; 2021-02-01: 4543017.05; 2021-03-01: 3155344.99; 2021-04-01: 1558890.87 | 17992222.45
The Open Channel Project | 2021-01-01: 17160530.81; 2021-02-01: 17027482.08; 2021-03-01: 20334878.39; 2021-04-01: 5850485.82 | 60373377.1
Waldorf Astoria Cairo | 2021-01-01: 11767116.99; 2021-02-01: 40794653.93; 2021-03-01: 13496896.04; 2021-04-01: 5744685.71 | 71803352.67
Alamein Coastal Road Bridge | 2021-01-01: 124285.9; 2021-02-01: 0; 2021-03-01: 1261225.8; 2021-04-01: 0 | 1385511.7
Wady El Natroon Bridge | 2021-01-01: 11550459.33; 2021-02-01: 9891987.91; 2021-03-01: 8029186.85; 2021-04-01: 24990986.36 | 54462620.45
HST El Mahager Bridge | 2021-01-01: 10552348.59; 2021-02-01: 12914829.78; 2021-03-01: 2121949.68; 2021-04-01: 12825570.98 | 38414699.03
HST Culverts | 2021-01-01: 1145990; 2021-02-01: 8781343.48; 2021-03-01: -8598685.41; 2021-04-01: 80177.18 | 1408825.25
Mivida BP#189 | 2021-01-01: 24457258.63; 2021-02-01: 11798720.12; 2021-03-01: 19836703.94; 2021-04-01: 20296664.93 | 76389347.62
EDNC Hardscape Package | 2021-01-01: 1431861.7; 2021-02-01: 81659.99; 2021-03-01: 42104.66; 2021-04-01: 12117.66 | 1567744.01
Egat Rolling Mill no.4 | 2021-01-01: 18089044.85; 2021-02-01: 15810508.89; 2021-03-01: 18910613.95; 2021-04-01: 15312757.25 | 68122924.94
EGAT Lock & Load | 2021-01-01: 2225044.23; 2021-02-01: 1572828.13; 2021-03-01: 396435.72; 2021-04-01: 198326.99 | 4392635.07
Qani bay Al rammah Mosque | 2021-01-01: 505006.47; 2021-02-01: 457008.03; 2021-03-01: 417887.23; 2021-04-01: 374524.1 | 1754425.83
October Under-Railway Tunnel | 2021-01-01: 323088.43; 2021-02-01: 702834.81; 2021-03-01: 282549; 2021-04-01: 532685.48 | 1841157.72
Radamis City | 2021-01-01: 6218430.34; 2021-02-01: 5089101.05; 2021-03-01: 5290215.08; 2021-04-01: 3548259.22 | 20146005.69
SODIC Allegria Villa f100 | 2021-01-01: 44636.73; 2021-02-01: 2166; 2021-03-01: 1002.22; 2021-04-01: 251550.21 | 299355.16
El- Hussein Mosque | 2021-01-01: 14775; 2021-02-01: 1674.62; 2021-03-01: 909.6; 2021-04-01: 0 | 17359.22
Jawhar Al-Lala Mosque | 2021-01-01: 218523.61; 2021-02-01: 233736.53; 2021-03-01: 146079.51; 2021-04-01: 122897.91 | 721237.56
Beymen Fit Out | 2021-01-01: 34770; 2021-02-01: 0; 2021-03-01: 6940; 2021-04-01: 101027.61 | 142737.61
Astoria Sharm elSheikh | 2021-01-01: 110127.18; 2021-02-01: 703002.63; 2021-03-01: 649182.62; 2021-04-01: 0 | 1462312.43
Wadi Halfa Port | 2021-01-01: 3165891.7; 2021-02-01: 1926801.23; 2021-03-01: 5752332.93; 2021-04-01: 2816299.81 | 13661325.67
SSC Suez Steel Company Project | 2021-01-01: 1633199.94; 2021-02-01: 7778133.57; 2021-03-01: 46524522.81; 2021-04-01: 36545190.95 | 92481047.27
Ora Zed Landscape Ph1 | 2021-01-01: 1402625.04; 2021-02-01: 3738930.45; 2021-03-01: 5338973.73; 2021-04-01: 4461493.3 | 14942022.52
L&L El-Awsaty Tunnel | 2021-01-01: 33630; 2021-02-01: 9687.12; 2021-03-01: 0; 2021-04-01: 0 | 43317.12
EPICO 3 Facility | 2021-01-01: 9442169.73; 2021-02-01: 5800670.72; 2021-03-01: 9031881.86; 2021-04-01: 6546458.26 | 30821180.57
Ring Road - El Qawmiya | 2021-01-01: 68717.66; 2021-02-01: 91034.3; 2021-03-01: 225770.65; 2021-04-01: 0 | 385522.61
Ring Road - Service Road | 2021-01-01: 3184624.72; 2021-02-01: 6221566.84; 2021-03-01: 4087421.92; 2021-04-01: 770592.46 | 14264205.94
| 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0 | 0
Darb Allabana Bldgs Ph1 | 2021-01-01: -26542.4; 2021-02-01: 187.6; 2021-03-01: 187.6; 2021-04-01: 0 | -26167.2
Creeks URBN-K | 2021-01-01: 0; 2021-02-01: 316642.26; 2021-03-01: 377928.81; 2021-04-01: 3484155.14 | 4178726.21
DP World Basin 2 Ph2 | 2021-01-01: 2860903.06; 2021-02-01: 4128558.99; 2021-03-01: 9321089.25; 2021-04-01: 5764421.88 | 22074973.18
Seashell Playa 5 Villas | 2021-01-01: 385886.57; 2021-02-01: 881385.13; 2021-03-01: 342918.65; 2021-04-01: 594060.54 | 2204250.89
Kafr Shokr Bridge | 2021-01-01: 50000; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0 | 50000
| 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0 | 0
MAF HQ Renovation | 2021-01-01: 14206.62; 2021-02-01: 3190763.52; 2021-03-01: 3640018.95; 2021-04-01: 4453167.41 | 11298156.5 | 1058133007
Abo Shanab El Agamien | 2021-03-01: 1680561.92; 2021-04-01: 1349744.99 | 3030306.91
0
0
0
0
0
0
0
0
0
0
0
0
| 474464705.677 | 583668301.69 | 608765248.98 | 465363848.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2132262104.877
Closed Projects
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ميناء دبى السخنة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مشاريع منتهية | 1533218.912 | 380337.694 | 3338128.5957 | 1262815.434 | 952058.25 | -4274314.604 | -575399.11 | 1846044.6162 | -1643142.773 | 747069.047 | 978696.9054 | -1217565.644 | 3327947.3233
Sub Total | 1533218.912 | 380337.694 | 3338128.5957 | 1262815.434 | 952058.25 | -4274314.604 | -575399.11 | 1846044.6162 | -1643142.773 | 747069.047 | 978696.9054 | -1217565.644 | 3327947.3233
Trade Activities
0 | [12 empty] | 0
0 | [12 empty] | 0
0 | [12 empty] | 0
0 | [12 empty] | 0
0 | [12 empty] | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 475997924.589 | 584048639.384 | 612103377.5757 | 466626663.964 | 952058.25 | -4274314.604 | -575399.11 | 1846044.6162 | -1643142.773 | 747069.047 | 978696.9054 | -1217565.644 | 2135590052.2003
Projects Indirect Cost | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 45047 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | Total
Construction Overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG&A Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Activities
Kayan 3 New Cairo Capital City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ministries Buildings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Royal City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mohamed Ali Palace Restoration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NUCA R05 - Z02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EDNC Retail & Offices Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Olympic Multi – Sports Hall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade Activities
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## Total cost 2023
|  | Description | Cost Incured To Date from poc (1-4) | Replanned cost from 5-12 | Total 2023 Cost |  |  | avg. for year | avg. for remaining | AVERAGE FOR ACTUALS | Jan | Feb | Mar | Apr
Kyan Project | Kyan Project | Kayan 3 New Cairo Capital City | 15074142.78 | 0 | 15074142.78 | 2 | 0 | 7537071.39 | #DIV/0! | 7209039.72 | 936711.98 | 13481367.46 | 0 | 0
Ministry Building | Ministry Building | Ministries Buildings | 81739722.36 | 49870588.9308 | 131610311.2908 | 8 | 4 | 16451288.9113 | 12467647.2327 | 17551274.566 | 5044866.33 | 30962202.86 | 19207770.7319 | 14990258.3421
Royal City Mall | Royal City Mall | Royal City | 1584919.49 | 20197428.6502 | 21782348.1402 | 5 | 2 | 4356469.628 | 10098714.3251 | 3577341.6833 | 737673.76 | 455351.29 | 9539000 | 0
Mohamed Ali Palace | Mohamed Ali Palace | Mohammed Ali Palace | 301540.51 | 4176942.1534 | 4478482.6634 | 11 | 7 | 407134.7876 | 596706.0219 | 89101.9817 | 18843.02 | 12617.56 | 246731.4281 | 78215.9185
R05 District | R05 District | R05 - Zone 2 | 72036212.01 | 222290042.9105 | 294326254.9205 | 12 | 8 | 24527187.91 | 27786255.3638 | 18395016.8969 | 20169755.75 | 17701109.89 | 15346986.4945 | 20362215.453
Sodic East - EDNC | Sodic East - EDNC | EDNC Offices & Retail Project | 399500.17 | 8024343.7674 | 8423843.9374 | 6 | 2 | 1403973.9896 | 4012171.8837 | 4150910.7177 | -4907606.74 | 4726159.2 | 2826794.9828 | 4899777.9702
Olympic Multi-Sports Hall | Olympic Multi-Sports Hall | Olympic Multi Sports Hall | 28443558.28 | 95309847.3958 | 123753405.6758 | 11 | 7 | 11250309.6069 | 13615692.4851 | 8645071.985 | 7534348.57 | 9179426.8 | 8933256.2851 | 8933256.2851
CFC Poduim 2 | CFC Poduim 2 | CFC Podium 2 | 164049.42 | 6161360.1733 | 6325409.5933 | 4 | 2 | 1581352.3983 | 3080680.0867 | 69313.21 | 133396.91 | 5229.51 | 0 | 0
Elswedy University Phase2 | Elswedy University Phase2 | El Sewedy University phase II | -3500000 | 1671860.6328 | -1828139.3672 | 8 | 6 | -228517.4209 | 278643.4388 | 586430.9289 | 0 | 0 | 1024719.8513 | 148142.0066
Ring Road Bridge | Ring Road Bridge | Ring Road | 9315181.44 | 22761446.2388 | 32076627.6788 | 10 | 6 | 3207662.7679 | 3793574.3731 | 2629549.8375 | 2593559.14 | 1634068.13 | 2615604.54 | 3674967.54
Marassi PKG #162,#163 &#177 (Marina) | Marassi PKG #162,#163 &#177 (Marina) | Marassi PKG# 162 & 163 & 177 | 27354679.82 | 58648540.4697 | 86003220.2897 | 7 | 3 | 12286174.3271 | 19549513.4899 | 10720739.7278 | 7390757.11 | 5725950.83 | 5906435.0019 | 23859815.9693
Sultana Malak | Sultana Malak | Sultana Malak | 677109.02 | 11457810.0314 | 12134919.0514 | 8 | 4 | 1516864.8814 | 2864452.5078 | 1680701.9175 | 206601.12 | 1358.9 | 3688323.59 | 2826524.06
New Giza Hospital | New Giza Hospital | New Giza Teaching Hospital | 55049581.84 | 186702943.1742 | 241752525.0142 | 12 | 8 | 20146043.7512 | 23337867.8968 | 12884813.8177 | 11479645 | 12195385.34 | 13323906.9643 | 14540317.9664
GOV2-Infra | GOV2-Infra | GOV2 - Infra | 60923705.7 | 43941000 | 104864705.7 | 12 | 8 | 8738725.475 | 5492625 | 5712490.6175 | 4171282.41 | 5680680.06 | 4850000 | 8148000
Re-newal Cairo -Alex Rail way | Re-newal Cairo -Alex Rail way | Cairo-Alex Railway | 18942711.47 | 0 | 18942711.47 | 4 | 0 | 4735677.8675 | 0 | 10362890.7273 | 9869881.61 | 7995440.72 | 12449999.9966 | 11136240.5827
ORA Zed PKGs A & D | ORA Zed PKGs A & D | ORA ZED - Ph 01B - Pkgs A&D | 85009205.27 | 200252369.3066 | 285261574.5766 | 12 | 8 | 23771797.8814 | 25031546.1633 | 21898404.8721 | 18780845.91 | 19140158.48 | 26871348.1 | 22801266.9984
Creek | Creek | Kattameya Creeks | 130245855.98 | 345868827.76 | 476114683.74 | 12 | 8 | 39676223.645 | 43233603.47 | 35923784.3625 | 19971783.95 | 56450549.54 | 34090545.72 | 33182258.24
Mansoura University | Mansoura University | Faculty of Medicine | 31885516.24 | 173067776.4473 | 204953292.6873 | 12 | 8 | 17079441.0573 | 21633472.0559 | 11748281.6 | 6088630.18 | 11578375.23 | 13253328.1409 | 16072792.8493
Diplomatic | Diplomatic | Diplomatic District - Infra | 26140943.86 | 149815836.4412 | 175956780.3012 | 12 | 8 | 14663065.0251 | 18726979.5552 | 7164746.766 | 9934567.51 | 5373546.62 | 3802827.7778 | 9548045.1561
ElSewedy HQ Internal Finishing | ElSewedy HQ Internal Finishing | ElSewedy HQ Internal Finishing | 31640034.34 | 34995946.6328 | 66635980.9728 | 4 | 2 | 16658995.2432 | 17497973.3164 | 11572782.625 | 6152223.04 | 16993342.21 | 0 | 0
Al khattatba Bridge | Al khattatba Bridge | El Khatatba Bridge | 16746467.42 | 0 | 16746467.42 | 3 | 0 | 5582155.8067 | #DIV/0! | 2474481.0189 | 3820251.01 | 3005495.68 | 597696.3668 | 0
Rolling Mill Eleco Steel Egat Ph02 | Rolling Mill Eleco Steel Egat Ph02 | EGAT Pelletizing Plant | 74950829.99 | 42248674.8552 | 117199504.8452 | 7 | 3 | 16742786.4065 | 14082891.6184 | 17423072.125 | 18184809.79 | 20268024.48 | 16139426.46 | 15100027.77
Port of Sokhna | Port of Sokhna | Sokhna Port Expansion | 248095896.677 | 252200725.4505 | 500296622.1275 | 12 | 8 | 41691385.1773 | 31525090.6813 | 48880029.1018 | 65505368.55 | 59334747.857 | 40920000 | 29760000
MDF | MDF | MDF Factory | 95220500.35 | 36700314.24 | 131920814.59 | 6 | 2 | 21986802.4317 | 18350157.12 | 25581537.3767 | 24682218.83 | 32192376.05 | 23371554.627 | 22080000
KEMET | KEMET | Kemet Building | 4961437.55 | 1948636.1705 | 6910073.7205 | 12 | 8 | 575839.4767 | 243579.5213 | 1200880.5752 | 2410864.45 | 1925395.03 | 242502.2712 | 224760.5498
Air Defense College | Air Defense College | Air Defense College | 172313503.25 | 186138237.0364 | 358451740.2864 | 12 | 8 | 29870978.3572 | 23267279.6296 | 29506129.0032 | 45571391.2 | 34853726.83 | 14085588.7091 | 23513809.2737
ORA ZED-Ph 2-Pkgs A&D | ORA ZED-Ph 2-Pkgs A&D | ORA ZED-Ph 2-Pkgs A&D | 52752817.99 | 243560844.15 | 296313662.14 | 12 | 8 | 24692805.1783 | 30445105.5188 | 13609647.6087 | 13111621.48 | 12712051.78 | 12530913.525 | 16084003.65
Sokhna Bridges | Sokhna Bridges | HST Bridges-Sokhna & Mahager | 74691713.83 | 46758783.2312 | 121450497.0612 | 7 | 3 | 17350071.0087 | 15586261.0771 | 19373256.4064 | 21249378.3 | 18980504.97 | 16952583.5314 | 20310558.8241
Abou Ghaleb Bridge | Abou Ghaleb Bridge | Abou Ghaleb Bridge | 53433935.8 | 175147956.9265 | 228581892.7265 | 12 | 8 | 19048491.0605 | 21893494.6158 | 12643161.115 | 6092414.27 | 10719333.92 | 14704262.55 | 19056633.72
Egyptian Exchange Building | Egyptian Exchange Building | Egyptian Exchange Building | 33560112.32 | 122765834.5685 | 156325946.8885 | 12 | 8 | 13027162.2407 | 15345729.3211 | 8395434.7724 | 10285640.27 | 6212807.7 | 6171095.4292 | 10912195.6905
Port Said Port Silos | Port Said Port Silos | Port Said Port Silos | 17992222.45 | 232025543.8274 | 250017766.2774 | 12 | 8 | 20834813.8565 | 29003192.9784 | 10092850.9602 | 8734969.54 | 4543017.05 | 9821590.5406 | 17271826.7103
The Open Channel Project | The Open Channel Project | The Open Channel Project | 60373377.1 | 229139246.5132 | 289512623.6132 | 12 | 8 | 24126051.9678 | 28642405.8141 | 19391395.9101 | 17160530.81 | 17027482.08 | 21201628.3668 | 22175942.3837
Waldorf Astoria Cairo | Waldorf Astoria Cairo | Waldorf Astoria Cairo | 71803352.67 | 4136579.7865 | 75939932.4565 | 5 | 1 | 15187986.4913 | 4136579.7865 | 16453251.3635 | 11767116.99 | 40794653.93 | 6481991.6018 | 6769242.9323
Alamein Coastal Road Bridge | Alamein Coastal Road Bridge | Alamein Coastal Road Bridge | 1385511.7 | 0 | 1385511.7 | 0 | 0 | #DIV/0! | #DIV/0! | 124285.9 | 124285.9 | -5.9663e-09 | 0 | 0
Wady El Natroon Bridge | Wady El Natroon Bridge | Wady El Natroon Bridge | 54462620.45 | 149357303.43 | 203819923.88 | 12 | 8 | 16984993.6567 | 18669662.9287 | 12235317.1225 | 11550459.33 | 9891987.91 | 11763105 | 15735716.25
HST El Mahager Bridge | HST El Mahager Bridge | HST El Mahager Bridge | 38414699.03 | 28530102.8054 | 66944801.8354 | 7 | 3 | 9563543.1193 | 9510034.2685 | 12299167.7337 | 10552348.59 | 12914829.78 | 12864746.2823 | 12864746.2823
Sokhna Culverts | Sokhna Culverts | HST Culverts | 1408825.25 | 0 | 1408825.25 | 3 | 0 | 469608.4167 | #DIV/0! | 3501693.6069 | 1145990 | 8781343.48 | 577747.3408 | 0
Mivida BP#189 | Mivida BP#189 | Mivida BP#189 | 76389347.62 | 383962681.8 | 460352029.42 | 12 | 8 | 38362669.1183 | 47995335.225 | 19144647.275 | 24457258.63 | 11798720.12 | 18463657.55 | 21858952.8
EDNC Landscape | EDNC Landscape | EDNC Hardscape Package | 1567744.01 | 16818955.3471 | 18386699.3571 | 12 | 8 | 1532224.9464 | 2102369.4184 | 729327.6246 | 1431861.7 | 81659.99 | 1362533.9997 | 41254.8087
Rolling Mill#4 | Rolling Mill#4 | Egat Rolling Mill no.4 | 68122924.94 | 159887789.0652 | 228010714.0052 | 12 | 8 | 19000892.8338 | 19985973.6331 | 16928071.6963 | 18089044.85 | 15810508.89 | 16166887.0559 | 17645845.9895
EGAt Load & Load | EGAt Load & Load | EGAT Lock & Load | 4392635.07 | 17499519.6364 | 21892154.7064 | 9 | 5 | 2432461.634 | 3499903.9273 | 2100220.1525 | 2225044.23 | 1572828.13 | 2324178.18 | 2278830.07
Qani bay Al rammah Mosque | Qani bay Al rammah Mosque | Qani bay Al rammah Mosque | 1754425.83 | 919527.5892 | 2673953.4192 | 5 | 1 | 534790.6838 | 919527.5892 | 655013.765 | 505006.47 | 457008.03 | 690000 | 968040.56
October Under-Railway Tunnel | October Under-Railway Tunnel | October Under-Railway Tunnel | 1841157.72 | 28248395.1674 | 30089552.8874 | 9 | 5 | 3343283.6542 | 5649679.0335 | 1466480.808 | 323088.43 | 702834.81 | 2199999.9964 | 2639999.9957
Radamis City | Radamis City | Radamis City | 20146005.69 | 64436504.8824 | 84582510.5724 | 11 | 7 | 7689319.1429 | 9205214.9832 | 5885882.8475 | 6218430.34 | 5089101.05 | 5980000 | 6256000
SODIC Allegria Villa f100 | SODIC Allegria Villa f100 | SODIC Allegria Villa f100 | 299355.16 | 1593913.0117 | 1893268.1717 | 9 | 6 | 210363.1302 | 265652.1686 | 17088.6998 | 44636.73 | 2166 | 0 | 4463.3693
El-Hussein Mosque | El-Hussein Mosque | El- Hussein Mosque | 17359.22 | 0 | 17359.22 | 4 | 0 | 4339.805 | #DIV/0! | 612516.4235 | 14775 | 1674.62 | 895185.6478 | 1538430.426
Jawhar al-lala Mosque | Jawhar al-lala Mosque | Jawhar Al-Lala Mosque | 721237.56 | 1800000 | 2521237.56 | 5 | 1 | 504247.512 | 1800000 | 1004523.0321 | 218523.61 | 233736.53 | 963270.6412 | 2602561.347
Beymen Fit Out | Beymen Fit Out | Beymen Fit Out | 142737.61 | 205072.67 | 347810.28 | 2 | 1 | 173905.14 | 205072.67 | 34770 | 34770 | 0 | 0 | 0
Astoria Sharm elSheikh | Astoria Sharm elSheikh | Astoria Sharm elSheikh | 1462312.43 | 1600103.979 | 3062416.409 | 7 | 3 | 437488.0584 | 533367.993 | 388231.8185 | 110127.18 | 703002.63 | 410998.5911 | 328798.8729
Wadi Halfa Port | Wadi Halfa Port | Wadi Halfa Port | 13661325.67 | 77122831.9627 | 90784157.6327 | 12 | 8 | 7565346.4694 | 9640353.9953 | 9979471.284 | 3165891.7 | 1926801.23 | 19885178.3696 | 14940013.8365
Suez Steel Intake & P Stations | Suez Steel Intake & P Stations | SSC Suez Steel Company Project | 92481047.27 | 103441164.8474 | 195922212.1174 | 12 | 8 | 16326851.0098 | 12930145.6059 | 6316663.1283 | 1633199.94 | 7778133.57 | 8316862.872 | 7538456.1312
Ora Zed Landscape Ph1 | Ora Zed Landscape Ph1 | Ora Zed Landscape Ph1 | 14942022.52 | 58806258.2068 | 73748280.7268 | 11 | 7 | 6704389.157 | 8400894.0295 | 5633446.7429 | 1402625.04 | 3738930.45 | 8171297.5009 | 9220933.9806
L&L El-Awsaty Tunnel | L&L El-Awsaty Tunnel | L&L Awsaty Tunnel Extension | 43317.12 | 0 | 43317.12 | 2 | 0 | 21658.56 | #DIV/0! | 21658.56 | 33630 | 9687.12 | 0 | 0
EPICO 3 Facility | EPICO 3 Facility | EIPICO | 30821180.57 | 163295999.9027 | 194117180.4727 | 12 | 8 | 16176431.7061 | 20411999.9878 | 10000460.1088 | 9442169.73 | 5800670.72 | 11812499.993 | 12946499.9923
Ring Road - El Qawmiya | Ring Road - El Qawmiya | Ring Road - El Qawmiya | 385522.61 | 125257050 | 125642572.61 | 12 | 8 | 10470214.3842 | 15657131.25 | 5085187.99 | 68717.66 | 91034.3 | 8556000 | 11625000
Ring Road - Service Road | Ring Road - Service Road | Ring Road - Service Road | 14264205.94 | 46339049.2227 | 60603255.1627 | 12 | 8 | 5050271.2636 | 5792381.1528 | 6714945.3609 | 3184624.72 | 6221566.84 | 7470054.9402 | 9983534.9433
|  | Beni Suef | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
Darb Allabana Bldgs Ph1 | Darb Allabana Bldgs Ph1 | Darb Allabana Bldgs Ph1 | -26167.2 | 0 | -26167.2 | 2 | 0 | -13083.6 | #DIV/0! | 187.6 | -26542.4 | 187.6 | 0 | 0
Creeks URBN-K | Creeks URBN-K | Creeks URBN-K | 4178726.21 | 171975000 | 176153726.21 | 11 | 8 | 16013975.11 | 21496875 | 7901747.42 | 0 | 316642.26 | 11465000 | 11923600
DP World Basin 2 Ph2 | DP World Basin 2 Ph2 | DP World Basin 2 Ph2 | 22074973.18 | 263198237.5334 | 285273210.7134 | 12 | 8 | 23772767.5594 | 32899779.6917 | 6524621.7631 | 2860903.06 | 4128558.99 | 6533000.0008 | 12576025.0016
Seashell Playa 5 Villas | Seashell Playa 5 Villas | Seashell Playa 5 Villas | 2204250.89 | 0 | 2204250.89 | 2 | 0 | 1102125.445 | #DIV/0! | 633635.85 | 385886.57 | 881385.13 | 0 | 0
Kafer Shoukr Bridge | Kafer Shoukr Bridge | Kafr Shoukr Bridge | 50000 | 0 | 50000 | 1 | 0 | 50000 | #DIV/0! | 50000 | 50000 | 0 | 0 | 0
Abo Shanab El Agamien | Abo Shanab El Agamien | Abo Shanab El Agamien | 3030306.91 | 147888000 | 150918306.91 | 10 | 8 | 15091830.691 | 18486000 | 10296000 | 0 | 0 | 6552000 | 14040000
Carrefour Head office Renovation | Carrefour Head office Renovation | MAF HQ Renovation | 11298156.5 | 11439752.1821 | 22737908.6821 | 8 | 4 | 2842238.5853 | 2859938.0455 | 2339142.5649 | 14206.62 | 3190763.52 | 3501680.068 | 2649920.0514
Sahary El AhramTunnel | Sahary El AhramTunnel | Sahary El AhramTunnel | 0 | 57911944.812 | 57911944.812 | 10 | 8 | 5791194.4812 | 7238993.1015 | 7784944.812 | 0 | 0 | 8249944.812 | 7319944.812
Mechanical Installation | Mechanical Installation | Mechanical Installation | 0 | 101193000 | 101193000 | 12 | 8 | 8432750 | 12649125 | 2047000 | 0 | 0 | 1780000 | 2314000
Comoros | Comoros | Comoros |  | 0 | 0 | 2 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
KSA Tarek Abdelhakim Center | KSA Tarek Abdelhakim Center | KSA Tarek Abdelhakim Center |  | 106490000 | 106490000 | 12 | 8 | 8874166.6667 | 13311250 | 2637500 | 0 | 0 | 2150000 | 3125000
KSA Haramein Columns | KSA Haramein Columns | KSA Haramein Columns |  | 7137200 | 7137200 | 8 | 4 | 892150 | 1784300 | 305000 | 0 | 0 | 250000 | 360000
|  | Total | 2132262104.877 | 5504341645.9257 | 7636603750.8027 | [5 empty] | 474145305.68 | 583987701.687 | 540554242.4256 | 603787666.3623
|  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0

## Mataching
Description | Names as per our report
Kayan 3 New Cairo Capital City | Kyan Project | 2
Ministries Buildings | Ministry Building | 3
Royal City | Royal City Mall | 4
Mohammed Ali Palace | Mohamed Ali Palace | 5
R05 - Zone 2 | R05 District | 6
EDNC Offices & Retail Project | Sodic East - EDNC | 7
Olympic Multi Sports Hall | Olympic Multi-Sports Hall | 8
CFC Podium 2 | CFC Poduim 2 | 9
El Sewedy University phase II | Elswedy University Phase2 | 10
Ring Road | Ring Road Bridge | 11
Marassi PKG# 162 & 163 & 177 | Marassi PKG #162,#163 &#177 (Marina) | 12
Sultana Malak | Sultana Malak | 13
New Giza Teaching Hospital | New Giza Hospital | 14
GOV2 - Infra | GOV2-Infra | 15
Cairo-Alex Railway | Re-newal Cairo -Alex Rail way | 16
ORA ZED - Ph 01B - Pkgs A&D | ORA Zed PKGs A & D | 17
Kattameya Creeks | Creek | 18
Faculty of Medicine | Mansoura University | 19
Diplomatic District - Infra | Diplomatic | 20
ElSewedy HQ Internal Finishing | ElSewedy HQ Internal Finishing | 21
El Khatatba Bridge | Al khattatba Bridge | 22
EGAT Pelletizing Plant | Rolling Mill Eleco Steel Egat Ph02 | 23
Sokhna Port Expansion | Port of Sokhna | 24
MDF Factory | MDF | 25
Kemet Building | KEMET | 26
Air Defense College | Air Defense College | 27
ORA ZED-Ph 2-Pkgs A&D | ORA ZED-Ph 2-Pkgs A&D | 28
HST Bridges-Sokhna & Mahager | Sokhna Bridges | 29
Abou Ghaleb Bridge | Abou Ghaleb Bridge | 30
Egyptian Exchange Building | Egyptian Exchange Building | 31
Port Said Port Silos | Port Said Port Silos | 32
The Open Channel Project | The Open Channel Project | 33
Waldorf Astoria Cairo | Waldorf Astoria Cairo | 34
Alamein Coastal Road Bridge | Alamein Coastal Road Bridge | 35
Wady El Natroon Bridge | Wady El Natroon Bridge | 36
HST El Mahager Bridge | HST El Mahager Bridge | 37
HST Culverts | Sokhna Culverts | 38
Mivida BP#189 | Mivida BP#189 | 39
EDNC Hardscape Package | EDNC Landscape | 40
Egat Rolling Mill no.4 | Rolling Mill#4 | 41
EGAT Lock & Load | EGAt Load & Load | 42
Qani bay Al rammah Mosque | Qani bay Al rammah Mosque | 43
October Under-Railway Tunnel | October Under-Railway Tunnel | 44
Radamis City | Radamis City | 45
SODIC Allegria Villa f100 | SODIC Allegria Villa f100 | 46
El- Hussein Mosque | El-Hussein Mosque | 47
Jawhar Al-Lala Mosque | Jawhar al-lala Mosque | 48
Beymen Fit Out | Beymen Fit Out | 49
Astoria Sharm elSheikh | Astoria Sharm elSheikh | 50
Wadi Halfa Port | Wadi Halfa Port | 51
SSC Suez Steel Company Project | Suez Steel Intake & P Stations | 52
Ora Zed Landscape Ph1 | Ora Zed Landscape Ph1 | 53
L&L Awsaty Tunnel Extension | L&L El-Awsaty Tunnel | 54
EIPICO | EPICO 3 Facility | 55
Ring Road - El Qawmiya | Ring Road - El Qawmiya | 56
Ring Road - Service Road | Ring Road - Service Road | 57
Beni Suef
Darb Allabana Bldgs Ph1 | Darb Allabana Bldgs Ph1 | 59
Creeks URBN-K | Creeks URBN-K | 60
DP World Basin 2 Ph2 | DP World Basin 2 Ph2 | 61
Seashell Playa 5 Villas | Seashell Playa 5 Villas | 62
Kafr Shoukr Bridge | Kafer Shoukr Bridge | 63
Abo Shanab El Agamien | Abo Shanab El Agamien | 64
MAF HQ Renovation | Carrefour Head office Renovation | 65
| Sahary El AhramTunnel | #N/A
| Mechanical Installation | #N/A
Total | Comoros | #N/A
| KSA Tarek Abdelhakim Center | #N/A
| KSA Haramein Columns | #N/A
Description
Kayan 3 New Cairo Capital City
Ministries Buildings
Royal City
Mohammed Ali Palace
R05 - Zone 2
EDNC Offices & Retail Project
Olympic Multi Sports Hall
CFC Podium 2
El Sewedy University phase II
Ring Road
Marassi PKG# 162 & 163 & 177
Sultana Malak
New Giza Teaching Hospital
GOV2 - Infra
Cairo-Alex Railway
ORA ZED - Ph 01B - Pkgs A&D
Kattameya Creeks
Faculty of Medicine
Diplomatic District - Infra
ElSewedy HQ Internal Finishing
El Khatatba Bridge
EGAT Pelletizing Plant
Sokhna Port Expansion
MDF Factory
Kemet Building
Air Defense College
ORA ZED-Ph 2-Pkgs A&D
HST Bridges-Sokhna & Mahager
Abou Ghaleb Bridge
Egyptian Exchange Building
Port Said Port Silos
The Open Channel Project
Waldorf Astoria Cairo
Alamein Coastal Road Bridge
Wady El Natroon Bridge
HST El Mahager Bridge
HST Culverts
Mivida BP#189
EDNC Hardscape Package
Egat Rolling Mill no.4
EGAT Lock & Load
Qani bay Al rammah Mosque
October Under-Railway Tunnel
Radamis City
SODIC Allegria Villa f100
El- Hussein Mosque
Jawhar Al-Lala Mosque
Beymen Fit Out
Astoria Sharm elSheikh
Wadi Halfa Port
SSC Suez Steel Company Project
Ora Zed Landscape Ph1
L&L Awsaty Tunnel Extension
EIPICO
Ring Road - El Qawmiya
Ring Road - Service Road
Beni Suef
Darb Allabana Bldgs Ph1
Creeks URBN-K
DP World Basin 2 Ph2
Seashell Playa 5 Villas
Kafr Shoukr Bridge
Abo Shanab El Agamien
MAF HQ Renovation
Total
Lowest Task-Resource
RME Resource List
Description
Kayan 3 New Cairo Capital City
Ministries Buildings
Royal City
Mohammed Ali Palace
R05 - Zone 2
EDNC Offices & Retail Project
Olympic Multi Sports Hall
CFC Podium 2
El Sewedy University phase II
Ring Road
Marassi PKG# 162 & 163 & 177
Sultana Malak
New Giza Teaching Hospital
GOV2 - Infra
Cairo-Alex Railway
ORA ZED - Ph 01B - Pkgs A&D
Kattameya Creeks
Faculty of Medicine
Diplomatic District - Infra
ElSewedy HQ Internal Finishing
El Khatatba Bridge
EGAT Pelletizing Plant
Sokhna Port Expansion
MDF Factory
Kemet Building
Air Defense College
ORA ZED-Ph 2-Pkgs A&D
HST Bridges-Sokhna & Mahager
Abou Ghaleb Bridge
Egyptian Exchange Building
Port Said Port Silos
The Open Channel Project
Waldorf Astoria Cairo
Alamein Coastal Road Bridge
Wady El Natroon Bridge
HST El Mahager Bridge
HST Culverts
Mivida BP#189
EDNC Hardscape Package
Egat Rolling Mill no.4
EGAT Lock & Load
Qani bay Al rammah Mosque
October Under-Railway Tunnel
Radamis City
SODIC Allegria Villa f100
El- Hussein Mosque
Jawhar Al-Lala Mosque
Beymen Fit Out
Astoria Sharm elSheikh
Wadi Halfa Port
SSC Suez Steel Company Project
Ora Zed Landscape Ph1
L&L Awsaty Tunnel Extension
EIPICO
Ring Road - El Qawmiya
Ring Road - Service Road
Beni Suef
Darb Allabana Bldgs Ph1
Creeks URBN-K
DP World Basin 2 Ph2
Seashell Playa 5 Villas
Kafr Shoukr Bridge
Abo Shanab El Agamien
MAF HQ Renovation
Total
Lowest Task-Resource
RME Resource List
Description
Kayan 3 New Cairo Capital City
Ministries Buildings
Royal City
Mohammed Ali Palace
R05 - Zone 2
EDNC Offices & Retail Project
Olympic Multi Sports Hall
CFC Podium 2
El Sewedy University phase II
Ring Road
Marassi PKG# 162 & 163 & 177
Sultana Malak
New Giza Teaching Hospital
GOV2 - Infra
Cairo-Alex Railway
ORA ZED - Ph 01B - Pkgs A&D
Kattameya Creeks
Faculty of Medicine
Diplomatic District - Infra
ElSewedy HQ Internal Finishing
El Khatatba Bridge
EGAT Pelletizing Plant
Sokhna Port Expansion
MDF Factory
Kemet Building
Air Defense College
ORA ZED-Ph 2-Pkgs A&D
HST Bridges-Sokhna & Mahager
Abou Ghaleb Bridge
Egyptian Exchange Building
Port Said Port Silos
The Open Channel Project
Waldorf Astoria Cairo
Alamein Coastal Road Bridge
Wady El Natroon Bridge
HST El Mahager Bridge
HST Culverts
Mivida BP#189
EDNC Hardscape Package
Egat Rolling Mill no.4
EGAT Lock & Load
Qani bay Al rammah Mosque
October Under-Railway Tunnel
Radamis City
SODIC Allegria Villa f100
El- Hussein Mosque
Jawhar Al-Lala Mosque
Beymen Fit Out
Astoria Sharm elSheikh
Wadi Halfa Port
SSC Suez Steel Company Project
Ora Zed Landscape Ph1
L&L Awsaty Tunnel Extension
EIPICO
Ring Road - El Qawmiya
Ring Road - Service Road
Beni Suef
Darb Allabana Bldgs Ph1
Creeks URBN-K
DP World Basin 2 Ph2
Seashell Playa 5 Villas
Kafr Shoukr Bridge
Abo Shanab El Agamien
MAF HQ Renovation
Total
Lowest Task-Resource
RME Resource List

## Sheet9
[5 empty] | Names as per our report | Jan | Feb | Mar | Apr
Project Name | JAN | FEB | MAR | APR | Kyan Project | 936711.98 | 13481367.46 | 0 | 0
ORA Zed PKGs A & D | 18780845.91 | 19140158.48 | 26871348.1 | 22801266.9984 | Ministry Building | 5044866.33 | 30962202.86 | 19207770.7319 | 14990258.3421
Sodic East - EDNC | -4907606.74 | 4726159.2 | 2826794.9828 | 4899777.9702 | Royal City Mall | 737673.76 | 455351.29 | 9539000 | 0
CFC Poduim 2 | 133396.91 | 5229.51 | 0 | 0 | Mohamed Ali Palace | 18843.02 | 12617.56 | 246731.4281 | 78215.9185
ElSewedy HQ Internal Finishing | 6152223.04 | 16993342.21 | 0 | 0 | R05 District | 20169755.75 | 17701109.89 | 15346986.4945 | 20362215.453
Creek | 19971783.95 | 56450549.54 | 34090545.72 | 33182258.24 | Sodic East - EDNC | -4907606.74 | 4726159.2 | 2826794.9828 | 4899777.9702
Marassi PKG #162& #163 (Marina) | 7390757.11 | 5725950.83 | 5906435.0019 | 23859815.9693 | Olympic Multi-Sports Hall | 7534348.57 | 9179426.8 | 8933256.2851 | 8933256.2851
Elswedy University Phase2 | 0 | 0 | 1024719.8513 | 148142.0066 | CFC Poduim 2 | 133396.91 | 5229.51 | 0 | 0
Royal City Mall | 737673.76 | 455351.29 | 9539000 | 0 | Elswedy University Phase2 | 0 | 0 | 1024719.8513 | 148142.0066
Re-newal Cairo -Alex Rail way | 9869881.61 | 7995440.72 | 12449999.9966 | 11136240.5827 | Ring Road Bridge | 2593559.14 | 1634068.13 | 2615604.54 | 3674967.54
Ministry Building | 5044866.33 | 30962202.86 | 19207770.7319 | 14990258.3421 | Marassi PKG #162,#163 &#177 (Marina) | 7390757.11 | 5725950.83 | 5906435.0019 | 23859815.9693
Olympic Multi-Sports Hall | 7534348.57 | 9179426.8 | 8933256.2851 | 8933256.2851 | Sultana Malak | 206601.12 | 1358.9 | 3688323.59 | 2826524.06
R05 District | 20169755.75 | 17701109.89 | 15346986.4945 | 20362215.453 | New Giza Hospital | 11479645 | 12195385.34 | 13323906.9643 | 14540317.9664
GOV2-Infra | 4171282.41 | 5680680.06 | 4850000 | 8148000 | GOV2-Infra | 4171282.41 | 5680680.06 | 4850000 | 8148000
Diplomatic | 9934567.51 | 5373546.62 | 3802827.7778 | 9548045.1561 | Re-newal Cairo -Alex Rail way | 9869881.61 | 7995440.72 | 12449999.9966 | 11136240.5827
Kyan Project | 936711.98 | 13481367.46 | 0 | 0 | ORA Zed PKGs A & D | 18780845.91 | 19140158.48 | 26871348.1 | 22801266.9984
Ring Road Bridge | 2593559.14 | 1634068.13 | 2615604.54 | 3674967.54 | Creek | 19971783.95 | 56450549.54 | 34090545.72 | 33182258.24
Kafer Shoukr Bridge | 50000 | 0 | 0 | 0 | Mansoura University | 6088630.18 | 11578375.23 | 13253328.1409 | 16072792.8493
Mohamed Ali Palace | 18843.02 | 12617.56 | 246731.4281 | 78215.9185 | Diplomatic | 9934567.51 | 5373546.62 | 3802827.7778 | 9548045.1561
Sultana Malak | 206601.12 | 1358.9 | 3688323.59 | 2826524.06 | ElSewedy HQ Internal Finishing | 6152223.04 | 16993342.21 | 0 | 0
Al khattatba Bridge | 3820251.01 | 3005495.68 | 597696.3668 | 0 | Al khattatba Bridge | 3820251.01 | 3005495.68 | 597696.3668 | 0
Mansoura University | 6088630.18 | 11578375.23 | 13253328.1409 | 16072792.8493 | Rolling Mill Eleco Steel Egat Ph02 | 18184809.79 | 20268024.48 | 16139426.46 | 15100027.77
Rolling Mill Eleco Steel Egat Ph02 | 18184809.79 | 20268024.48 | 16139426.46 | 15100027.77 | Port of Sokhna | 65505368.55 | 59334747.857 | 40920000 | 29760000
MDF | 24682218.83 | 32192376.05 | 23371554.627 | 22080000 | MDF | 24682218.83 | 32192376.05 | 23371554.627 | 22080000
KEMET | 2410864.45 | 1925395.03 | 242502.2712 | 224760.5498 | KEMET | 2410864.45 | 1925395.03 | 242502.2712 | 224760.5498
Port of Sokhna | 65505368.55 | 59334747.857 | 40920000 | 29760000 | Air Defense College | 45571391.2 | 34853726.83 | 14085588.7091 | 23513809.2737
Air Defense College | 45571391.2 | 34853726.83 | 14085588.7091 | 23513809.2737 | ORA ZED-Ph 2-Pkgs A&D | 13111621.48 | 12712051.78 | 12530913.525 | 16084003.65
ORA ZED-Ph 2-Pkgs A&D | 13111621.48 | 12712051.78 | 12530913.525 | 16084003.65 | Sokhna Bridges | 21249378.3 | 18980504.97 | 16952583.5314 | 20310558.8241
Sokhna Bridges | 21249378.3 | 18980504.97 | 16952583.5314 | 20310558.8241 | Abou Ghaleb Bridge | 6092414.27 | 10719333.92 | 14704262.55 | 19056633.72
Egyptian Exchange Building | 10285640.27 | 6212807.7 | 6171095.4292 | 10912195.6905 | Egyptian Exchange Building | 10285640.27 | 6212807.7 | 6171095.4292 | 10912195.6905
Port Said Port Silos | 8734969.54 | 4543017.05 | 9821590.5406 | 17271826.7103 | Port Said Port Silos | 8734969.54 | 4543017.05 | 9821590.5406 | 17271826.7103
The Open Channel Project | 17160530.81 | 17027482.08 | 21201628.3668 | 22175942.3837 | The Open Channel Project | 17160530.81 | 17027482.08 | 21201628.3668 | 22175942.3837
Abou Ghaleb Bridge | 6092414.27 | 10719333.92 | 14704262.55 | 19056633.72 | Waldorf Astoria Cairo | 11767116.99 | 40794653.93 | 6481991.6018 | 6769242.9323
Waldorf Astoria | 11767116.99 | 40794653.93 | 6481991.6018 | 6769242.9323 | Alamein Coastal Road Bridge | 124285.9 | -5.9663e-09 | 0 | 0
Alamein Coastal Bridge | 124285.9 | -5.9663e-09 | 0 | 0 | Wady El Natroon Bridge | 11550459.33 | 9891987.91 | 11763105 | 15735716.25
Wady El Natroon Bridge | 11550459.33 | 9891987.91 | 11763105 | 15735716.25 | HST El Mahager Bridge | 10552348.59 | 12914829.78 | 12864746.2823 | 12864746.2823
HST El Mahager Bridge | 10552348.59 | 12914829.78 | 12864746.2823 | 12864746.2823 | Sokhna Culverts | 1145990 | 8781343.48 | 577747.3408 | 0
New Giza Teaching Hospital | 11479645 | 12195385.34 | 13323906.9643 | 14540317.9664 | Mivida BP#189 | 24457258.63 | 11798720.12 | 18463657.55 | 21858952.8
EGAt Load & Load | 2225044.23 | 1572828.13 | 2324178.18 | 2278830.07 | EDNC Landscape | 1431861.7 | 81659.99 | 1362533.9997 | 41254.8087
Rolling Mill#4 | 18089044.85 | 15810508.89 | 16166887.0559 | 17645845.9895 | Rolling Mill#4 | 18089044.85 | 15810508.89 | 16166887.0559 | 17645845.9895
Mivida BP#189 | 24457258.63 | 11798720.12 | 18463657.55 | 21858952.8 | EGAt Load & Load | 2225044.23 | 1572828.13 | 2324178.18 | 2278830.07
Sokhna Culverts | 1145990 | 8781343.48 | 577747.3408 | 0 | Qani bay Al rammah Mosque | 505006.47 | 457008.03 | 690000 | 968040.56
EDNC Landscape | 1431861.7 | 81659.99 | 1362533.9997 | 41254.8087 | October Under-Railway Tunnel | 323088.43 | 702834.81 | 2199999.9964 | 2639999.9957
Qani bay Al rammah Mosque | 505006.47 | 457008.03 | 690000 | 968040.56 | Radamis City | 6218430.34 | 5089101.05 | 5980000 | 6256000
October Under-Railway Tunnel | 323088.43 | 702834.81 | 2199999.9964 | 2639999.9957 | SODIC Allegria Villa f100 | 44636.73 | 2166 | 0 | 4463.3693
Radamis City | 6218430.34 | 5089101.05 | 5980000 | 6256000 | El-Hussein Mosque | 14775 | 1674.62 | 895185.6478 | 1538430.426
Jawhar al-lala Mosque | 218523.61 | 233736.53 | 963270.6412 | 2602561.347 | Jawhar al-lala Mosque | 218523.61 | 233736.53 | 963270.6412 | 2602561.347
El-Hussein Mosque | 14775 | 1674.62 | 895185.6478 | 1538430.426 | Beymen Fit Out | 34770 | 0 | 0 | 0
SODIC Allegria Villa f100 | 44636.73 | 2166 | 0 | 4463.3693 | Astoria Sharm elSheikh | 110127.18 | 703002.63 | 410998.5911 | 328798.8729
Beymen Fit Out | 34770 | 0 | 0 | 0 | Wadi Halfa Port | 3165891.7 | 1926801.23 | 19885178.3696 | 14940013.8365
Astoria Sharm elSheikh | 110127.18 | 703002.63 | 410998.5911 | 328798.8729 | Suez Steel Intake & P Stations | 1633199.94 | 7778133.57 | 8316862.872 | 7538456.1312
Wadi Halfa Port | 3165891.7 | 1926801.23 | 19885178.3696 | 14940013.8365 | Ora Zed Landscape Ph1 | 1402625.04 | 3738930.45 | 8171297.5009 | 9220933.9806
Suez Steel Intake & P Stations | 1633199.94 | 7778133.57 | 8316862.872 | 7538456.1312 | L&L El-Awsaty Tunnel | 33630 | 9687.12 | 0 | 0
Ora Zed Landscape Ph1 | 1402625.04 | 3738930.45 | 8171297.5009 | 9220933.9806 | EPICO 3 Facility | 9442169.73 | 5800670.72 | 11812499.993 | 12946499.9923
L&L El-Awsaty Tunnel | 33630 | 9687.12 | 0 | 0 | Ring Road - El Qawmiya | 68717.66 | 91034.3 | 8556000 | 11625000
EPICO 3 Facility | 9442169.73 | 5800670.72 | 11812499.993 | 12946499.9923 | Ring Road - Service Road | 3184624.72 | 6221566.84 | 7470054.9402 | 9983534.9433
Ring Road - El Qawmiya | 68717.66 | 91034.3 | 8556000 | 11625000 |  | 0 | 0 | 0 | 0
Ring Road - Service Road | 3184624.72 | 6221566.84 | 7470054.9402 | 9983534.9433 | Darb Allabana Bldgs Ph1 | -26542.4 | 187.6 | 0 | 0
Sahary El AhramTunnel | 0 | 0 | 8249944.812 | 7319944.812 | Creeks URBN-K | 0 | 316642.26 | 11465000 | 11923600
Darb Allabana Bldgs Ph1 | -26542.4 | 187.6 | 0 | 0 | DP World Basin 2 Ph2 | 2860903.06 | 4128558.99 | 6533000.0008 | 12576025.0016
Creeks URBN-K | 0 | 316642.26 | 11465000 | 11923600 | Seashell Playa 5 Villas | 385886.57 | 881385.13 | 0 | 0
DP World Basin 2 Ph2 | 2860903.06 | 4128558.99 | 6533000.0008 | 12576025.0016 | Kafer Shoukr Bridge | 50000 | 0 | 0 | 0
Seashell Playa 5 Villas | 385886.57 | 881385.13 | 0 | 0 | Abo Shanab El Agamien | 0 | 0 | 6552000 | 14040000
Abo Shanab El Agamien | 0 | 0 | 6552000 | 14040000 | Carrefour Head office Renovation | 14206.62 | 3190763.52 | 3501680.068 | 2649920.0514
Carrefour Head office Renovation | 14206.62 | 3190763.52 | 3501680.068 | 2649920.0514 | Sahary El AhramTunnel | 0 | 0 | 8249944.812 | 7319944.812
Mechanical Installation |  |  | 1780000 | 2314000 | Mechanical Installation | 0 | 0 | 1780000 | 2314000
Comoros |  |  | 0 | 0 | Comoros | 0 | 0 | 0 | 0
KSA Tarek Abdelhakim Center |  |  | 2150000 | 3125000 | KSA Tarek Abdelhakim Center | 0 | 0 | 2150000 | 3125000
KSA Haramein Columns |  |  | 250000 | 360000 | KSA Haramein Columns | 0 | 0 | 250000 | 360000
Total | 474145305.68 | 583987701.687 | 540554242.4256 | 603787666.3623
| 474145305.68 | 583987701.687 | 540554242.4256 | 603787666.3623 |  | 474145305.68 | 583987701.687 | 540554242.4256 | 603787666.3623
[6 empty] | 0 | 0 | 0 | 0
69000000
297000000

## Cost from 4 till 12
| Project Name | Remianing Expected cost from april till Decemeber
17 | ORA Zed PKGs A & D | 200252369.3066 | 2 | Kyan Project | 0 | 0
7 | Sodic East - EDNC | 8024343.7674 | 3 | Ministry Building | 49870588.9308 | 49870588.9308 | TRUE
9 | CFC Poduim 2 | 6161360.1733 | 4 | Royal City Mall | 20197428.6502 | 20197428.6502 | TRUE
21 | ElSewedy HQ Internal Finishing | 34995946.6328 | 5 | Mohamed Ali Palace | 4176942.1534 | 4176942.1534 | TRUE
18 | Creek | 345868827.76 | 6 | R05 District | 222290042.9105 | 222290042.9105 | TRUE
12 | Marassi PKG #162& #163 (Marina) | 58648540.4697 | 7 | Sodic East - EDNC | 8024343.7674 | 8024343.7674 | TRUE
10 | Elswedy University Phase2 | 1671860.6328 | 8 | Olympic Multi-Sports Hall | 95309847.3958 | 95309847.3958 | TRUE
4 | Royal City Mall | 20197428.6502 | 9 | CFC Poduim 2 | 6161360.1733 | 6161360.1733 | TRUE
16 | Re-newal Cairo -Alex Rail way | 0 | 10 | Elswedy University Phase2 | 1671860.6328 | 1671860.6328 | TRUE
3 | Ministry Building | 49870588.9308 | 11 | Ring Road Bridge | 22761446.2388 | 22761446.2388 | TRUE
8 | Olympic Multi-Sports Hall | 95309847.3958 | 12 | Marassi PKG #162& #163 (Marina) | 58648540.4697 | 0 | FALSE
6 | R05 District | 222290042.9105 | 13 | Sultana Malak | 11457810.0314 | 11457810.0314 | TRUE
15 | GOV2-Infra | 43941000 | 14 | New Giza Teaching Hospital | 186702943.1742 | 186702943.1742 | TRUE
20 | Diplomatic | 149815836.4412 | 15 | GOV2-Infra | 43941000 | 43941000 | TRUE
2 | Kyan Project | 0 | 16 | Re-newal Cairo -Alex Rail way | 0 | 0 | TRUE
11 | Ring Road Bridge | 22761446.2388 | 17 | ORA Zed PKGs A & D | 200252369.3066 | 200252369.3066 | TRUE
63 | Kafer Shoukr Bridge |  | 18 | Creek | 345868827.76 | 345868827.76 | TRUE
5 | Mohamed Ali Palace | 4176942.1534 | 19 | Mansoura University | 173067776.4473 | 173067776.4473 | TRUE
13 | Sultana Malak | 11457810.0314 | 20 | Diplomatic | 149815836.4412 | 149815836.4412 | TRUE
22 | Al khattatba Bridge | 0 | 21 | ElSewedy HQ Internal Finishing | 34995946.6328 | 34995946.6328 | TRUE
19 | Mansoura University | 173067776.4473 | 22 | Al khattatba Bridge | 0 | 0 | TRUE
23 | Rolling Mill Eleco Steel Egat Ph02 | 42248674.8552 | 23 | Rolling Mill Eleco Steel Egat Ph02 | 42248674.8552 | 42248674.8552 | TRUE
25 | MDF | 36700314.24 | 24 | Port of Sokhna | 252200725.4505 | 252200725.4505 | TRUE
26 | KEMET | 1948636.1705 | 25 | MDF | 36700314.24 | 36700314.24 | TRUE
24 | Port of Sokhna | 252200725.4505 | 26 | KEMET | 1948636.1705 | 1948636.1705 | TRUE
27 | Air Defense College | 186138237.0364 | 27 | Air Defense College | 186138237.0364 | 186138237.0364 | TRUE
28 | ORA ZED-Ph 2-Pkgs A&D | 243560844.15 | 28 | ORA ZED-Ph 2-Pkgs A&D | 243560844.15 | 243560844.15 | TRUE
29 | Sokhna Bridges | 46758783.2312 | 29 | Sokhna Bridges | 46758783.2312 | 46758783.2312 | TRUE
31 | Egyptian Exchange Building | 122765834.5685 | 30 | Abou Ghaleb Bridge | 175147956.9265 | 175147956.9265 | TRUE
32 | Port Said Port Silos | 232025543.8274 | 31 | Egyptian Exchange Building | 122765834.5685 | 122765834.5685 | TRUE
33 | The Open Channel Project | 229139246.5132 | 32 | Port Said Port Silos | 232025543.8274 | 232025543.8274 | TRUE
30 | Abou Ghaleb Bridge | 175147956.9265 | 33 | The Open Channel Project | 229139246.5132 | 229139246.5132 | TRUE
34 | Waldorf Astoria | 4136579.7865 | 34 | Waldorf Astoria | 4136579.7865 | 0 | FALSE
35 | Alamein Coastal Bridge | 0 | 35 | Alamein Coastal Bridge | 0 | 0 | TRUE
36 | Wady El Natroon Bridge | 149357303.43 | 36 | Wady El Natroon Bridge | 149357303.43 | 149357303.43 | TRUE
37 | HST El Mahager Bridge | 28530102.8054 | 37 | HST El Mahager Bridge | 28530102.8054 | 28530102.8054 | TRUE
14 | New Giza Teaching Hospital | 186702943.1742 | 38 | Sokhna Culverts | 0 | 0 | TRUE
42 | EGAt Load & Load | 17499519.6364 | 39 | Mivida BP#189 | 383962681.8 | 383962681.8 | TRUE
41 | Rolling Mill#4 | 159887789.0652 | 40 | EDNC Landscape | 16818955.3471 | 16818955.3471 | TRUE
39 | Mivida BP#189 | 383962681.8 | 41 | Rolling Mill#4 | 159887789.0652 | 159887789.0652 | TRUE
38 | Sokhna Culverts | 0 | 42 | EGAt Load & Load | 17499519.6364 | 17499519.6364 | TRUE
40 | EDNC Landscape | 16818955.3471 | 43 | Qani bay Al rammah Mosque | 919527.5892 | 919527.5892 | TRUE
43 | Qani bay Al rammah Mosque | 919527.5892 | 44 | October Under-Railway Tunnel | 28248395.1674 | 28248395.1674 | TRUE
44 | October Under-Railway Tunnel | 28248395.1674 | 45 | Radamis City | 64436504.8824 | 64436504.8824 | TRUE
45 | Radamis City | 64436504.8824 | 46 | SODIC Allegria Villa f100 | 1593913.0117 | 1593913.0117 | TRUE
48 | Jawhar al-lala Mosque | 1800000 | 47 | El-Hussein Mosque | 0 | 0 | TRUE
47 | El-Hussein Mosque | 0 | 48 | Jawhar al-lala Mosque | 1800000 | 1800000 | TRUE
46 | SODIC Allegria Villa f100 | 1593913.0117 | 49 | Beymen Fit Out | 205072.67 | 205072.67 | TRUE
49 | Beymen Fit Out | 205072.67 | 50 | Astoria Sharm elSheikh | 1600103.979 | 1600103.979 | TRUE
50 | Astoria Sharm elSheikh | 1600103.979 | 51 | Wadi Halfa Port | 77122831.9627 | 77122831.9627 | TRUE
51 | Wadi Halfa Port | 77122831.9627 | 52 | Suez Steel Intake & P Stations | 103441164.8474 | 103441164.8474 | TRUE
52 | Suez Steel Intake & P Stations | 103441164.8474 | 53 | Ora Zed Landscape Ph1 | 58806258.2068 | 58806258.2068 | TRUE
53 | Ora Zed Landscape Ph1 | 58806258.2068 | 54 | L&L El-Awsaty Tunnel | 0 | 0 | TRUE
54 | L&L El-Awsaty Tunnel | 0 | 55 | EPICO 3 Facility | 163295999.9027 | 163295999.9027 | TRUE
55 | EPICO 3 Facility | 163295999.9027 | 56 | Ring Road - El Qawmiya | 125257050 | 125257050 | TRUE
56 | Ring Road - El Qawmiya | 125257050 | 57 | Ring Road - Service Road | 46339049.2227 | 46339049.2227 | TRUE
57 | Ring Road - Service Road | 46339049.2227 | 59 | Darb Allabana Bldgs Ph1 | 0 | 0 | TRUE
#N/A | Sahary El AhramTunnel | 57911944.812 | 60 | Creeks URBN-K | 171975000 | 0 | FALSE
59 | Darb Allabana Bldgs Ph1 | 0 | 61 | DP World Basin 2 Ph2 | 263198237.5334 | 171975000 | FALSE
60 | Creeks URBN-K | 171975000 | 62 | Seashell Playa 5 Villas | 0 | 263198237.5334 | FALSE
61 | DP World Basin 2 Ph2 | 263198237.5334 | 63 | Kafer Shoukr Bridge |  | 0 | TRUE
62 | Seashell Playa 5 Villas | 0 | 64 | Abo Shanab El Agamien | 147888000 | 0 | FALSE
64 | Abo Shanab El Agamien | 147888000 | 65 | Carrefour Head office Renovation | 11439752.1821 | 147888000 | FALSE
65 | Carrefour Head office Renovation | 11439752.1821 | #N/A | Sahary El AhramTunnel | 57911944.812 | 11439752.1821 | FALSE
#N/A | Mechanical Installation | 101193000 | #N/A | Mechanical Installation | 101193000 | 57911944.812 | FALSE
#N/A | Comoros | 0 | #N/A | Comoros | 0 | 101193000 | FALSE
#N/A | KSA Tarek Abdelhakim Center | 106490000 | #N/A | KSA Tarek Abdelhakim Center | 106490000 | 0 | FALSE
#N/A | KSA Haramein Columns | 7137200 | #N/A | KSA Haramein Columns | 7137200 | 106490000 | FALSE
[6 empty] | 7137200 | FALSE
|  | 5504341645.9257 |  |  |  | 5441556525.6695 | FALSE
62785120.2562

## Sheet7 (hidden)
El Shrouk Bridge | 854816.227 | 872559.06 | 1240241.466
Ending Projects | 900157.598 | -880566.82 | 1199381.324
El Sewedy Stores | 0 | 173000 | 0
Beni Suef Substation R61 | 0 | 63416.84 | 73323.287
BIN BAN Aswan | 0 | 0 | 63471.775
Olympic City - Lock&Load |  |  | 61506.629
Mock-up Room |  |  | 45953.604
Siemens Power Station | 0 | 35500 | 0
Safeer Square Bridge | 0 | 4600 | 5454.52
Mehwar elsalaam Lock & Load | 0 | 0 | 3083
Ain Shams- Emergency Bridge | 1538.32 | 0 | 0
kayan wall lock & Load | -13395 | 0 | 0

## May 2019 (2) (hidden)
Project | 0 | 0 | 0 | MAXM/MXCM/1305 | 0 | 0030 | EMAR/ITPR/11226 | 0032 | 0 | EMAR/SIER/1354 | NGZA/UNVI/1369 | Bani Suef | 0 | GMSA/GBLZ/1301 | Village E PKG#62 | 0040 | 0 | 0 | ARMY/KYAN/1446 | 0046 | CDRI/BSCC/1445 | 0048 | 0051 | GMSA/GZWF/1440 | GMSA/GZWF/1441 | EMAR/IPWT/1459 | 0019 | 0059 | 0061 | 0052 | 0060 | 0063 | 0 | 0053 | 0070 | [10 empty] | 0065 | 0069 | 0072 | 0071 | 0068 | 0074 | 0075 | 0076 | 0081 | 0079 | 0078 | 0080 | 0083 | 0084
GL | 0008 | 0013 | 0012 | 0023 | 0028 | 0030 | 0031 | 0032 | 0033 | 0034 | 0037 | 0035 | 0038 | 0039 | 0041 | 0040 | 0044 |  | 0045 | 0046 | 0047 | 0048 | 0051 | 0055 | 0054 | 0058 | 0019 | 0059 | 0061 | 0052 | 0060 | 0063 | 0064 | 0053 | 0070 | [10 empty] | 0065 | 0069
Description | نادي سوديك | عمائر اب تاون 53 | مشروع الكيان | Tamay Elamdeed substation (Alestom ) | نفق العاصمة | Bani Sweif substation (Alestom ) | Ismalia substation (Alestom ) | مبنى وزارات الجيش | رويال سيتى | كوبري الأمل لوك لود | Hyper ismalia | P.I.PARKS - SLP | Rolling Mills | Siemens | PKG 117 | Kayan Lock Load | Sokhna Tunnel | Mientra | Al Jazi Mall | Nefisha Bridge | Mohammed Ali Palace | Fish Market | Benban Solar Power | Alamein | R05 - Zone 1 | R05 - Zone 2 | R05 - Zone 3 | Sokhna Tunnel 2 | Abu Sultan Bridge 2 | El Sewedy University | Substation Elco Steel | PKG 101 | PKG 144 | Port of Sokhna | EDNC Offices & Retail Project | مشروع الامل | مشروع مصنع الاسمنت | Olympic Multi Sports Hall | PKG 140 Mivida | EGAT Elco Steel | Pyramid Tunnel | Abo Ghazala Lock & Load | Mohamed Aly Fahmy Lock & Load | محطه كهرباء المستثمرين بالقطامي | كوبرى شبرا بنها | Total |  |  | Trial Balance
Tamay Elamdeed substation (Alostom )
[9 empty] | 0063 |  | 0070 | 0065 | 0069 | 0072 | 0071 | 0082 | 0074 | 0076 | 0081 | 0079 | 0078 | 0080 | 0083 | 0084 | 0082 | 0088 |  | 0090 | 0089 |  | 0096 | 0095 | 0093 | 0094 | 0092 | 0046 | CDRI/BSCC/1445 | 0099 | 0098 | 0102
Total Contract Price | 99588109 | 270610661 | 420103550 | 95970234.5006 | 467255000 | 95970234.5006 | 95970234.5006 | 329870053 | 409523809.836 | 9050320 | 51838240 | 32000000 | 264370000 | 311000000 | 39336927 | 107782440 | 62970000 | 112533424 | 212502100 | 74567997 | 51936384.3429 | 35636958 | 164582403 | 28594000 | 943050990 | 400057672 | 594816338 | 5000000 | 38500000 | 50105046 | 33235261 | 27692512 | 78095238 | 1610425545 | 1000494581 | 30857015 | 206723720 | 1000000000 | 148256064 | 63583487 | 317540750 | 1438741 | 6591715 | 130103216.3586 | 2800000 | 10532930971.0392
Additions (Deductions) | 61697112 | 44358177 | 894161386 | 18429405.4994 | -122709346 | 27800720.4994 | 18429405.4994 | 2410700147 | 52738998.164 | 0 | 112504026 | 65038376 | 95000000 | 20000000 | 4139730 | -21382440 | -16330487 | -1925662 | 28021451 | -3639899 |  | 34128726 | 54426670 | 25558148 | 485720214 | 525632121 |  | 15567977 | 39349902 | 195553526 | 243399 |  | 32380952 |  | 22000000 | 936861 | 67939980 |  | 20091363 |  |  |  |  | 9688966.6414 | 1065380 | 5217315286.3037
Total Contracts | 161285221 | 314968838 | 1314264936 | 114399640 | 344545654 | 123770955 | 114399640 | 2740570200 | 462262808 | 9050320 | 164342266 | 97038376 | 359370000 | 331000000 | 43476657 | 86400000 | 46639513 | 110607762 | 240523551 | 70928098 | 51936384.3429 | 69765684 | 219009073 | 54152148 | 1428771204 | 925689793 | 594816338 | 20567977 | 77849902 | 245658572 | 33478660 | 27692512 | 110476190 | 1610425545 | 1022494581 | 31793876 | 274663700 | 1000000000 | 168347427 | 63583487 | 317540750 | 1438741 | 6591715 | 139792183 | 3865380 | 15750246257.3429
Total Estemated Cost Of contract | 92629183 | 264427221.9112 | 385768894.2159 | 91302219 | 408567772 | 91302219 | 91302219 | 308424824 | 381327168.1479 | 6335224 | 47721580.5944 | 31612131.219 | 150482575 | 295519635 | 36189973 | 82991132 | 56673000 | 104027350 | 194848891.049 | 64082041 | 41097260.9305 | 34286165.4 | 138815982 | 22585376 | 868890600 | 353629976 | 515475161 | 12919682.818 | 33454552 | 8464412 | 30756410 | 24530229 | 69377455 | 1472155701 | 946905944 | 27546588.4725 | 187827866.3247 | 933950000 | 136710623 | 56803402 | 280541761 | 1225088 | 5836964 | 109630210.621 | 2520000 | 9501472663.7042
Additional Cost ( Deductions) | 68508485 | 79299433.0888 | 843375048.7841 | 11692967 | -141537521.801 | 12642212 | 13407301 | 2254110664 | 54840791.8521 | -702284.746 | 101877353.4056 | 52157189.781 | 86268000.4 | 11584932 | -6741148.16 | -7317740 | -19013020.996 | 2054105 | 21276486.951 | -13715297.05 | -1999999.9305 | 31736713.8 | -7736373 | 25851086 | 432914361 | 500533074 |  | 5935540.182 | 33693659 | 223659671 | 3777838 |  | 28766261 |  | 20703795 | -6113909.6935 | 77666668.8923 |  | 17435004 |  |  |  |  | -24246839.607 | -1059671.55 | 4785584835.6028
Total Cost | 161137668 | 343726655 | 1229143943 | 102995186 | 267030250.199 | 103944431 | 104709520 | 2562535488 | 436167960 | 5632939.254 | 149598934 | 83769321 | 236750575.4 | 307104567 | 29448824.84 | 75673392 | 37659979.004 | 106081455 | 216125378 | 50366743.95 | 39097261 | 66022879.2 | 131079609 | 48436462 | 1301804961 | 854163050 | 515475161 | 18855223 | 67148211 | 232124083 | 34534248 | 24530229 | 98143716 | 1472155701 | 967609739 | 21432678.779 | 265494535.217 | 933950000 | 154145627 | 56803402 | 280541761 | 1225088 | 5836964 | 85383371.014 | 1460328.45 | 14287057499.307
Gross Margin | 147553 | -28757817 | 85120993 | 11404454 | 77515403.801 | 19826524 | 9690120 | 178034712 | 26094848 | 3417380.746 | 14743332 | 13269055 | 122619424.6 | 23895433 | 14027832.16 | 10726608 | 8979533.996 | 4526307 | 24398173 | 20561354.05 | 12839123.3429 | 3742804.8 | 87929464 | 5715686 | 126966243 | 71526743 | 79341177 | 1712754 | 10701691 | 13534489 | -1055588 | 3162283 | 12332474 | 138269844 | 54884842 | 10361197.221 | 9169164.783 | 66050000 | 14201800 | 6780085 | 36998989 | 213653 | 754751 | 54408811.986 | 2405051.55 | 1463188758.0359
Gross Margin % | 0.09149% | -9.13% | 6.477% | 9.969% | 0.22498 | 16.02% | 8.47% | 6.496% | 5.645% | 37.76% | 8.971% | 13.67% | 34.12% | 7.219% | 32.27% | 12.42% | 19.25% | 4.092% | 10.14% | 28.99% | 24.72% | 5.365% | 40.15% | 10.55% | 8.886% | 7.727% | 13.34% | 8.327% | 13.75% | 5.509% | -3.153% | 11.42% | 11.16% | 8.586% | 5.368% | 32.59% | 3.338% | 6.605% | 8.436% | 10.66% | 11.65% | 14.85% | 11.45% | 38.92% | 62.22% | 9.29%
Cost Incured previous years | 147218379.3845 | 339434694.4669 | 765169038.989 | 60104836.099 | 260536181.105 | 83044722.13 | 42320907.891 | 589608481.54 | 157289468.91 | 5576458.295 | 49625217.441 | 45605817.278 | 212684388.646 | 180953904.437 | 23613590.372 | 51740577.521 | 37465929.964 | 78561198.162 | 87994977.756 | 48012449.949 | 5562926.127 | 12479184.655 | 82955285.203 | 10269346.39 | 32681023.749 | 47423662.782 | 16805916.115 | 12919682.818 | 39238906.959 | 19465324.897 | 16937734.958 | 124549.894 | 1251659.072 | 1832666.15 | 500359.87 | 21210869.997 | 259287399.01 | 0 | 0 | 0 | 0 | 0 | 0 | 85209855.07 | 1175416.75 | 3933892990.8024
Cost Incured To Date May 2019 | 3812689.648 | 3564293.538 | 153887972.843 | 15645697.066 | 6494069.094 | 11285080.111 | 15960259.779 | 118518212.89 | 51526216.011 | 56480.959 | 50366119.89 | 28864584.993 | 24066186.754 | 92635212.186 | 5835234.468 | 6196335.481 | 194049.04 | 11718707.805 | 47172597.29 | 2354294.001 | 6719442.064 | 31798939.168 | 29250948.522 | 10826700.974 | 94539611.203 | 91760849.333 | -16805916.12 | 2902875.623 | 26131416.241 | 67127971.909 | 16496458.074 | 9487334.387 | 57116998.367 | 34355789.79 | 40007415.117 | 221808.782 | 6207136.207 | 5627287.533 | 1701374.022 | 25396848.763 | 86959.699 | 186222.722 | 1035681.801 | 173515.944 | 284911.7 | 1192792875.672
0
Percentage Of Completion Previous Year | 91.36% | 98.75% | 62.25% | 58.36% | 97.57% | 79.89% | 40.42% | 23.01% | 36.06% | 99% | 33.17% | 54.44% | 89.83% | 58.92% | 80.19% | 68.37% | 99.48% | 74.06% | 40.71% | 95.33% | 14.23% | 18.9% | 63.29% | 21.2% | 2.51% | 5.552% | 3.26% | 68.52% | 58.44% | 8.386% | 49.05% | 0.5077% | 1.275% | 0.1245% | 0.05171% | 98.97% | 97.66% | 0% | 0% | 0% | 0% | 0% | 0% | 99.8% | 80.49% | 27.53%
Percentage Of Completion Current Year | 2.366% | 1.037% | 12.52% | 15.19% | 2.432% | 10.86% | 15.24% | 4.625% | 11.81% | 1.003% | 33.67% | 34.46% | 10.17% | 30.16% | 19.81% | 8.188% | 0.5153% | 11.05% | 21.83% | 4.674% | 17.19% | 48.16% | 22.32% | 22.35% | 7.262% | 10.74% | -3.26% | 15.4% | 38.92% | 28.92% | 47.77% | 38.68% | 58.2% | 2.334% | 4.135% | 1.035% | 2.338% | 0.6025% | 1.104% | 44.71% | 0.031% | 15.2% | 17.74% | 0.2032% | 19.51% | 8.349%
Percentage Of Completion YTD | 93.73% | 99.79% | 74.77% | 73.55% | 100% | 90.75% | 55.66% | 27.63% | 47.88% | 100% | 66.84% | 88.9% | 100% | 89.09% | 100% | 76.56% | 100% | 85.1% | 62.54% | 100% | 31.41% | 67.06% | 85.6% | 43.55% | 9.773% | 16.29% | -9.7e-10% | 83.92% | 97.35% | 37.3% | 96.81% | 39.18% | 59.47% | 2.458% | 4.186% | 100% | 100% | 0.6025% | 1.104% | 44.71% | 0.031% | 15.2% | 17.74% | 100% | 100% | 35.88%
Total Revenue (Cost to Cost) | 151169367.4676 | 314302051.1083 | 982703784.7883 | 84138240.4405 | 344545654 | 112322416.853 | 63674674.473 | 757324503.6673 | 221308609.798 | 9050320 | 109845722.2787 | 86266509.1489 | 359370000 | 294876753.1751 | 43476657 | 66149397.4444 | 46639513 | 94131988.9756 | 150426504.4252 | 70928098 | 16315766.8515 | 46788229.053 | 187475255.8419 | 23585460.8677 | 139628581.2541 | 150839681.2629 | -0.0057696 | 17259833.9513 | 75788664.7915 | 91642303.3888 | 32412229.7637 | 10850988.0113 | 65703105.1206 | 39587398.1538 | 42805460.4487 | 31793876 | 274663700 | 6025255.67 | 1858125.6215 | 28428230.4634 | 98428.298 | 218699.6079 | 1169601.0568 | 139792183 | 3865380 | 5791247204.5168
2018 | 66186476.0993 | 39636967.4122 | 361206519.1488 | 59228680.2024 | 143473947.7567 | 57753874.2106 | 26574071.1288 | 464162037.8673 | 115180042.9783 | 2789764.3587 | 48522934.3685 | 41315141.5084 | 249152904.3566 | 193206418.5371 | 30617859.0193 | 62277001.696 | 45749450.159 | 85828099.5635 | 95967277.319 | 54157640.2076 | 8003883.436 | 13095951.6132 | 116736148.9694 | 13001408.1092 | 35470370.8392 | 53649864.0327 | 19392657.9525 | 16279747.4369 | 45156721.5489 | 20600292.1193 | 18302852.7087 | 140606.0838 | 1408939.1593 | 2004796.355 | 528676.9416 | 0 | 9690893.789 | 0 | 0 | 0 | 0 | 0 | 0 | 5806551.6629 | 1766283.6333 | 2624023754.2887
2017 | 39798225.5477 | 134881511.8124 | 355833205.1927 | 6716378.4968 | 196722369.6827 | 34146370.2953 | 19823390.034 | 203157390.9498 | 53739949.9715 | 5648517.6857 | 5376482.4117 | 10619318.1369 | 100763651.836 | 3751302.1559 | 2318240.8702 | 4919643.9917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12985911.0457 | 195606026.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 77406632.2719 | 1177072 | 1465391590.8266
2016 | 32352499.287 | 93806619.9612 | 90457299.6801 | 87188.4577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15957239.9543 | 70335211.7734 | 0 | 0 | 0 | 0 | 0 | 0 | 46578999.0652 | 0 | 349575058.1789
2015 | 12993657.6901 | 45897167.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58890825.0435
2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7253e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7253e-09
POC Revenues May 2019 | -161491.1563 | 79784.5691 | 175206760.7668 | 18105993.2836 | 4349336.5606 | 20422172.3471 | 17277213.3102 | 90005074.8502 | 52388616.8482 | 612037.9556 | 55946305.4985 | 34332049.5036 | 9453443.8074 | 97919032.4821 | 10540557.1105 | -1047248.2433 | 890062.841 | 8303889.4122 | 54459227.1062 | 16770457.7924 | 8311883.4155 | 33692277.4398 | 70739106.8725 | 10584052.7585 | 104158210.4149 | 97189817.2302 | -19392657.9582 | 980086.5145 | 30631943.2426 | 71042011.2696 | 14109377.055 | 10710381.9275 | 64294165.9613 | 37582601.7988 | 42276783.5071 | 2850725 | -968432.0005 | 6025255.67 | 1858125.6215 | 28428230.4634 | 98428.298 | 218699.6079 | 1169601.0568 | 10000000 | 922024.3667 | 1293365976.1792
| -0.1001% | 0.02533% | 13.33% | 15.83% | 1.262% | 16.5% | 15.1% | 3.284% | 11.33% | 6.763% | 34.04% | 35.38% | 2.631% | 29.58% | 24.24% | -1.212% | 1.908% | 7.508% | 22.64% | 23.64% | 16% | 48.29% | 32.3% | 19.55% | 7.29% | 10.5% | -3.26% | 4.765% | 39.35% | 28.92% | 42.14% | 38.68% | 58.2% | 2.334% | 4.135% | 8.966% | -0.3526% | 0.6025% | 1.104% | 44.71% | 0.031% | 15.2% | 17.74% |  |  | 35.38% | [13 empty] | 8.212%
POC Revenues April 2019 | -2369833.2578 | -181388.282 | 146661426.3851 | 14313690.7063 | 4349336.5606 | 19317505.8138 | 14072951.1074 | 72241871.5864 | 40000631.1514 | 612037.9556 | 49348282.5449 | 32751920.5133 | 9453443.8074 | 91925192.402 | 8137654.8332 | -975048.2671 | 890062.841 | 7636332.0815 | 43097107.5403 | 16770457.7924 | 5001874.4567 | 31937763.8245 | 80045082.3447 | 8228360.9001 | 85975231.512 | 76262702.9024 | -19392657.9582 | -9121.7095 | 29414384.0734 | 41090794.9224 | 13789671.7356 | 8775618.0936 | 50225229.557 | 26864227.8458 | 32744379.5186 | 2850725 | -968432.0005 | 1940546.2134 | 1255016.6795 | 17740857.3726 | 65849.2448 | 94022.933 | 92919.2488 | 10000000 | 922024.3667 | 1073000706.8932
DFF Revenues | 2208342.1014 | 261172.8511 | 28545334.3816 | 3792302.5774 | -5.9605e-08 | 1104666.5333 | 3204262.2028 | 17763203.2638 | 12387985.6968 | 1.8626e-09 | 6598022.9536 | 1580128.9904 | 0 | 5993840.0802 | 2402902.2774 | -72199.9762 | 0 | 667557.3306 | 11362119.566 | -1.4901e-08 | 3310008.9588 | 1754513.6153 | -9305975.4722 | 2355691.8584 | 18182978.9029 | 20927114.3278 | 0 | 989208.224 | 1217559.1692 | 29951216.3471 | 319705.3194 | 1934763.834 | 14068936.4043 | 10718373.9529 | 9532403.9885 | 0 | 0 | 4084709.4566 | 603108.942 | 10687373.0909 | 32579.0531 | 124676.6749 | 1076681.808 | 0 | 0 | 220365269.286
Cost Incured To Date May 2019 | 3812689.648 | 3564293.538 | 153887972.843 | 15645697.066 | 6494069.094 | 11285080.111 | 15960259.779 | 118518212.89 | 51526216.011 | 56480.959 | 50366119.89 | 28864584.993 | 24066186.754 | 92635212.186 | 5835234.468 | 6196335.481 | 194049.04 | 11718707.805 | 47172597.29 | 2354294.001 | 6719442.064 | 31798939.168 | 29250948.522 | 10826700.974 | 94539611.203 | 91760849.333 | -16805916.12 | 2902875.623 | 26131416.241 | 67127971.909 | 16496458.074 | 9487334.387 | 57116998.367 | 34355789.79 | 40007415.117 | 221808.782 | 6207136.207 | 5627287.533 | 1701374.022 | 25396848.763 | 86959.699 | 186222.722 | 1035681.801 | 173515.944
Cost Incured To Date April 2019 | 1606367.865 | 3279274.642 | 127191434.044 | 12231447.604 | 4291042.34 | 10357367.028 | 13027411.763 | 101908954.443 | 39804492.003 | -0.001 | 44360013.096 | 27500523.288 | 21119138.034 | 87074077.254 | 4177495.798 | 6259571.79 | 194049.04 | 11078468.353 | 36963025.812 | 2352903.23 | 4227695.944 | 30138552.086 | 38383886.546 | 8719649.206 | 77972443.503 | 72450743.575 | -16805916.12 | 1996041.584 | 25081229.691 | 38826909.289 | 16166672.39 | 7773506.479 | 44618579.487 | 24557686.817 | 30986685.71 | 189479.75 | 6276678.19 | 1812373.136 | 1149143.39 | 15849100.147 | 58176.669 | 80060.53 | 82280 | 171518.274 | 284911.7 | 985825145.399
Dff Cost | 2206321.783 | 285018.896 | 26696538.799 | 3414249.462 | 2203026.754 | 927713.083 | 2932848.016 | 16609258.447 | 11721724.008 | 56480.96 | 6006106.794 | 1364061.705 | 2947048.72 | 5561134.932 | 1657738.67 | -63236.309 | 0 | 640239.452 | 10209571.478 | 1390.771 | 2491746.12 | 1660387.082 | -9132938.024 | 2107051.768 | 16567167.7 | 19310105.758 | 0 | 906834.039 | 1050186.55 | 28301062.62 | 329785.684 | 1713827.908 | 12498418.88 | 9798102.973 | 9020729.407 | 32329.032 | -69541.983 | 3814914.397 | 552230.632 | 9547748.616 | 28783.03 | 106162.192 | 953401.801 | 1997.67 | 0 | 206967730.273
Cost Vs. Revenue | 2020.3184 | -23846.0449 | 1848795.5826 | 378053.1154 | -2203026.754 | 176953.4503 | 271414.1868 | 1153944.8168 | 666261.6888 | -56480.96 | 591916.1596 | 216067.2854 | -2947048.72 | 432705.1482 | 745163.6074 | -8963.6672 | 0 | 27317.8786 | 1152548.088 | -1390.771 | 818262.8388 | 94126.5333 | -173037.4482 | 248640.0904 | 1615811.2029 | 1617008.5698 | 0 | 82374.185 | 167372.6192 | 1650153.7271 | -10080.3646 | 220935.926 | 1570517.5243 | 920270.9799 | 511674.5815 | -32329.032 | 69541.983 | 269795.0596 | 50878.31 | 1139624.4749 | 3796.0231 | 18514.4829 | 123280.007 | -1997.67 | 0 | 13397539.013
Total Cost Without Revenue May 2019 | [15 empty] | -5458201.4319
Percentage Of Completion 2018
Actual Revenues | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2017-04-01 | 42856 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Revenue Recognition
Construction Activities
نادي سوديك | 0 | 0 | 0 | 4583109.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4583109.75 | 2208342.1014 | 2208342.1014 | 2208342.1 | 0.0014152
عمائر اب تاون 53 | 2557230.98 | 1849502.84 | 726341.65 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5573075.47 | 261172.8511 | 261172.8511 | 261172.85 | 0.0010877
مشروع الكيان | 0 | 179948517.95 | 64133420.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244081938.2 | 28545334.3816 | 28545334.3816 | 28545334 | 0.38163
Tamay Elamdeed substation (Alestom ) | 17405481.64 | 1899677.92 | 10213010.17 | 2113382.78 | 3498515.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35130067.72 | 293787.3674 | 3792302.5774 | 3792302.58 | -0.0026447
نفق العاصمة | 0 | 0 | 0 | 16934976.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16934976.78 | -5.9605e-08 | -5.9605e-08 |  | -5.9605e-08
Bani Sweif substation (Alestom ) | 4015117 | 5916532.69 | 0 | 0 | 2347798.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12279448.03 | -1243131.8067 | 1104666.5333 | 1104666 | 0.5333
Ismalia substation (Alestom ) | 3425194 | 0 | 3829449 | 1513092.67 | 5774580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14542315.67 | -2570317.7972 | 3204262.2028 | 3204262 | 0.20276
مبنى وزارات الجيش | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17763203.2638 | 17763203.2638 | 17763203 | 0.26376
رويال سيتى | 6957536.92 | 8723893.09 | 8643111 | 6172362.54 | 9398674.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39895577.75 | 2989311.4968 | 12387985.6968 | 12387989 | -3.3032
كوبري الأمل لوك لود | 0 | 0 | 0 | 1991284.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991284.16 | 1.8626e-09 | 1.8626e-09 |  | 1.8626e-09
Hyper ismalia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6598022.9536 | 6598022.9536 | 6598022 | 0.95359
P.I.PARKS - SLP | 0 | 9740366.76 | 19085006.85 | 0 | 9900212.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38725585.63 | -8320083.0296 | 1580128.9904 | 1580128 | 0.99039
Rolling Mills | 32724390.51 | 0 | 2039662.21 | 619108.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35383160.83 | 0 | 0 |  | 0
Siemens | 0 | 42595714.82 | 0 | 0 | 57817326.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100413041.68 | -51823486.7798 | 5993840.0802 | 5993840 | 0.080183
PKG 117 | 4505534.51 | 3150407.65 | 1067786.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8723728.68 | 2402902.2774 | 2402902.2774 | 2402902 | 0.27736
Kayan Lock Load | 21432600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21432600 | -72199.9762 | -72199.9762 | -72199 | -0.97615
Sokhna Tunnel | 0 | 1226927.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226927.69 | 0 | 0 |  | 0
Mientra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667557.3306 | 667557.3306 | 667557 | 0.33064
Al Jazi Mall | 10405492.14 | 8329448.81 | 8749158.37 | 0 | 11730726.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39214826.12 | -368607.234 | 11362119.566 | 11362119 | 0.56597
Nefisha Bridge | 0 | 0 | 19116412.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19116412.92 | 0 | 0 | 0 | 0
Mohammed Ali Palace | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3310008.9588 | 3310008.9588 | 3310008 | 0.95877
Fish Market | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1754513.6153 | 1754513.6153 | 1754513 | 0.61534
Benban Solar Power | 24194467.4 | 53447729.08 | 0 | 30747647.61 | 2018302.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110408146.7 | -11324278.0822 | -9305975.4722 | -9305975 | -0.47221
Alamein | 0 | 0 | 0 | 20204000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20204000 | 2355691.8584 | 2355691.8584 | 2355691 | 0.85843
R05 - Zone 1 | 0 | 18101215.9 | 25863589.7 | 9108844 | 4897147.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57970797.1 | 13285831.4029 | 18182978.9029 | 18182978 | 0.90293
R05 - Zone 2 | 0 | 69830383.75 | 4448510 | 22465025.75 | 39628486.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136372405.8 | -18701371.9722 | 20927114.3278 | 20927114 | 0.3278
R05 - Zone 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Sokhna Tunnel 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989208.224 | 989208.224 | 989208 | 0.224
Abu Sultan Bridge 2 | 0 | 0 | 47855181.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47855181.9 | 1217559.1692 | 1217559.1692 | 1217559 | 0.16921
El Sewedy University | 7328770.16 | 8768016.81 | 15650900.68 | 7583517.33 | 18231859.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57563064.55 | 11719356.7771 | 29951216.3471 | 29951216 | 0.34713
Substation Elco Steel | 0 | 6953538.74 | 2651758.28 | 1904763.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11510060.74 | 319705.3194 | 319705.3194 | 319705 | 0.31941
PKG 101 | 0 | 1738465.67 | 3744391.54 | 0 | 1896917.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7379774.76 | 37846.284 | 1934763.834 | 1934763 | 0.83397
PKG 144 | 0 | 4125990.87 | 42540740.2 | 20465525.62 | 26659780.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93792037.32 | -12590844.2257 | 14068936.4043 | 14068936 | 0.40431
Port of Sokhna | 0 | 0 | 21619523.77 | 24408793.92 | 58512265.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104540583.3 | -47793891.6571 | 10718373.9529 | 10718373 | 0.95293
EDNC Offices & Retail Project | 0 | 0 | 0 | 9063098.33 | 20887437.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29950535.64 | -11355033.3215 | 9532403.9885 | 9532403 | 0.98847
مشروع الامل | 2850725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850725 | 0 | 0 |  | 0
مشروع مصنع الاسمنت | 0 | 4976388.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4976388.72 | 0 | 0 | 0 | 0
Olympic Multi Sports Hall | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4084709.4566 | 4084709.4566 | 4084709 | 0.45661
PKG 140 Mivida | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603108.942 | 603108.942 | 603108 | 0.94196
EGAT Elco Steel | 0 | 0 | 0 | 16067195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16067195 | 10687373.0909 | 10687373.0909 | 10687373 | 0.090871
Pyramid Tunnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32579.0531 | 32579.0531 | 32579 | 0.053118
Abo Ghazala Lock & Load | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124676.6749 | 124676.6749 | 124676 | 0.67488
Mohamed Aly Fahly Lock & Load | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1076681.808 | 1076681.808 | 1076681 | 0.80799
محطه كهرباء المستثمرين بالقطامي | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبرى شبرا بنها | 0 | 0 | 2839376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2839376 | 0 | 0 |  | 0
Sub Total | 137802540.26 | 431322719.76 | 304817331.01 | 196385728.07 | 273200030.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340688973.61 | -52834761.224 | 220365269.286 | 220365258.53 | 10.756
Closed Projects
|  |  | 0 | [9 empty] | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade Activities
ابناء مصر للتعمير | 0 | 0 | 0 | 2015180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2015180
ابناء حسن علام | 0 | 0 | 0 | 0 | 1040364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040364
EMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KAM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 2015180 | 1040364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3055544
Total Actual Revenues | 137802540.26 | 431322719.76 | 304817331.01 | 196385728.07 | 273200030.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340688973.61
POC Revenues | 191918048.4479 | 317551292.9442 | 274994821.5634 | 288536543.9376 | 220365269.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1293365976.1792 | 0
Total Revenues | 191918048.4479 | 317551292.9442 | 274994821.5634 | 290551723.9376 | 221405633.286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296421520.1792
1293365976.1792
Total Revenues | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2017-04-01 | 42856 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Revenue Recognition
Construction Activities
نادي سوديك | -2247526.1296 | 1414798.0063 | -2667222.5659 | -3452992.3186 | 2208342.1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4744600.9063
عمائر اب تاون 53 | -1810659.5192 | -1849502.84 | -1979754.12 | -114547.2728 | 261172.8511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5493290.9009
مشروع الكيان | 16032355.579 | -122794135.552 | -18929910.0141 | 28271178.1723 | 28545334.3816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -68875177.4332
Tamay Elamdeed substation (Alestom ) | -15572718.4508 | 1732301.553 | -4266841.3509 | 789396.4449 | 293787.3674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17024074.4364
نفق العاصمة | 736538.3093 | 2982420.6547 | 630377.5966 | -16934976.78 | -5.9605e-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12585640.2194
Bani Sweif substation (Alestom ) | 84200.353 | -1164572.8796 | 9274426.1198 | 1191802.5306 | -1243131.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8142724.3171
Ismalia substation (Alestom ) | -873663.2231 | 4803669.6592 | -871575.8402 | 2246784.8415 | -2570317.7972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2734897.6402
مبنى وزارات الجيش | 23141920.6712 | 26487480.7068 | -8528008.0395 | 31140478.2479 | 17763203.2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90005074.8502
رويال سيتى | 411943.3715 | 4497805.7179 | 3554523.8542 | 1039454.6578 | 2989311.4968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12493039.0982
كوبري الأمل لوك لود | 612037.9556 | 0 | -1.8626e-09 | -1991284.16 | 1.8626e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1379246.2044
Hyper ismalia | 8851859.3287 | 11715557.176 | 17225630.8672 | 11555235.173 | 6598022.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55946305.4985
P.I.PARKS - SLP | 8678228.6061 | -6180677.5481 | -5110539.6237 | 6539535.469 | -8320083.0296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4393536.1264
Rolling Mills | -32724390.51 | 1453443.8074 | 5960337.79 | -619108.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25929717.0226
Siemens | 27691232.0997 | -2667145.3414 | 16552419.0593 | 7752971.7643 | -51823486.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2494009.1979
PKG 117 | -2905114.3543 | -983047.8596 | 2740755.7029 | 561332.6641 | 2402902.2774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1816828.4305
Kayan Lock Load | -20392073.7897 | 2483779.6755 | -7121630.4638 | 2622276.3108 | -72199.9762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22479848.2433
Sokhna Tunnel | 155408.9845 | -1168185.9138 | 675912.0803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -336864.849
Mientra | 3709021.8959 | 3870779.0527 | -3143368.5004 | 3199899.6334 | 667557.3306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8303889.4122
Al Jazi Mall | -2736196.977 | 4170247.5213 | 5140850.7824 | 9038106.8936 | -368607.234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15244400.9862
Nefisha Bridge | 1676720.0102 | 292922.5549 | -4315598.2921 | 0.59951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2345955.1276
Mohammed Ali Palace | 1181966.123 | 1010497.7503 | 668531.2957 | 2140879.2877 | 3310008.9588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8311883.4155
Fish Market | 2195358.4375 | 9448808.4268 | 13527634.1809 | 6765962.7792 | 1754513.6153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33692277.4398
Benban Solar Power | -14331658.697 | -31075386.0006 | 33229636.4195 | -16167353.4671 | -11324278.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39669039.8275
Alamein | 828033.4722 | 4219761.6412 | -104202.4112 | -16919231.8022 | 2355691.8584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9619947.2415
R05 - Zone 1 | 22016916.2645 | 10952505.8479 | -12079855.1738 | 12012014.9734 | 13285831.4029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46187413.3149
R05 - Zone 2 | 5198008.3085 | -34537313.5364 | 11657359.1084 | -2799270.4781 | -18701371.9722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39182588.5698
R05 - Zone 3 | 1421.293 | -19394079.2512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19392657.9582
Sokhna Tunnel 2 | 709444.0646 | 726556.8417 | -1698120.7987 | 252998.183 | 989208.224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980086.5145
Abu Sultan Bridge 2 | 11735816.6018 | 5963909.2817 | -39524727.0852 | 3384203.375 | 1217559.1692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17223238.6574
El Sewedy University | -1341443.6782 | -842838.354 | -5547999.2177 | 9491871.1923 | 11719356.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13478946.7196
Substation Elco Steel | 8685747.8179 | -706878.2666 | -4272957.0485 | -1426301.5072 | 319705.3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2599316.315
PKG 101 | 548682.1994 | -17164.8998 | -529560.8527 | 3290804.4367 | 37846.284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3330607.1675
PKG 144 | 2717124.5303 | 6369311.0926 | -25932000.1729 | -61462.583 | -12590844.2257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29497871.3587
Port of Sokhna | 1383810.0725 | 9170862.508 | -17451892.695 | -12266869.7297 | -47793891.6571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66957981.5012
EDNC Offices & Retail Project | 67157.167 | 818470.6718 | 2625396.8033 | 20170256.5465 | -11355033.3215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12326247.8671
مشروع الامل | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مشروع مصنع الاسمنت | 0 | -4976388.7205 | -968432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5944820.7205
Olympic Multi Sports Hall | 0 | 0 | 1890030.8154 | 50515.398 | 4084709.4566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6025255.67
PKG 140 Mivida | 0 | 0 | 683164.0327 | 571852.6469 | 603108.942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1858125.6215
EGAT Elco Steel | 0 | 0 | 950756.8066 | 722905.5659 | 10687373.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12361035.4634
Pyramid Tunnel | 0 | 0 | 33502.3875 | 32346.8573 | 32579.0531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98428.298
Abo Ghazala Lock & Load | 0 | 0 | 117792.7503 | -23769.8172 | 124676.6749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218699.6079
Mohamed Aly Fahly Lock & Load | 0 | 0 | 0 | 92919.2488 | 1076681.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1169601.0568
محطه كهرباء المستثمرين بالقطامي | 0 | 0 | 10000000 | -2.9802e-08 | 0 | [7 empty] | 10000000
كوبرى شبرا بنها | 0 | 0 | -1917351.6333 | 0 | 0 | [7 empty] | -1917351.6333
Sub Total | 54115508.1879 | -113771426.8158 | -29822509.4466 | 92150815.8676 | -52834761.224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50162373.4308
Accrued Revenues
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PKG58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ميناء دبى السخنة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mozambique | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 54115508.1879 | -113771426.8158 | -29822509.4466 | 92150815.8676 | -52834761.224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50162373.4308
Projects Direct Cost | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2017-04-01 | 42856 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Construction Activities
نادي سوديك | -2186448.669 | 1376350.28 | 1287382.719 | 1129083.535 | 2206321.783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3812689.648
عمائر اب تاون 53 | 2051661.4 | 1240298.748 | -367853.268 | 355167.762 | 285018.896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3564293.538
مشروع الكيان | 15191959.532 | 54158421.087 | 31400914.561 | 26440138.864 | 26696538.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153887972.843
Tamay Elamdeed substation (Alestom ) | 1668244.469 | 3305953.384 | 4643847.417 | 2613402.334 | 3414249.462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15645697.066
نفق العاصمة | 564071.004 | 2284059.08 | 660292.566 | 782619.69 | 2203026.754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6494069.094
Bani Sweif substation (Alestom ) | 3704306.472 | 4294060.197 | 1358109.351 | 1000891.008 | 927713.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11285080.111
Ismalia substation (Alestom ) | 2327349.305 | 4381611.754 | 2877050.281 | 3441400.423 | 2932848.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15960259.779
مبنى وزارات الجيش | 20446988.53 | 23402950.079 | 28941505.681 | 29117510.153 | 16609258.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118518212.89
رويال سيتى | 6862074.885 | 12311354.904 | 13827494.481 | 6803567.733 | 11721724.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51526216.011
كوبري الأمل لوك لود | 1004904.028 | 569215.391 | -1574119.42 |  | 56480.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56480.959
Hyper ismalia | 8149910.893 | 10786518.798 | 14904981.55 | 10518601.855 | 6006106.794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50366119.89
P.I.PARKS - SLP | 7620714.855 | 3125911.714 | 11108579.181 | 5645317.538 | 1364061.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28864584.993
Rolling Mills | 0 | 3803071.633 | 8189516.967 | 9126549.434 | 2947048.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24066186.754
Siemens | 25441178.693 | 36684170.188 | 17755456.359 | 7193272.014 | 5561134.932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92635212.186
PKG 117 | 1147423.833 | 1553892.126 | 1096374.181 | 379805.658 | 1657738.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5835234.468
Kayan Lock Load | 801192.18 | 1912479.314 | 1249181.046 | 2296719.25 | -63236.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6196335.481
Sokhna Tunnel | 127270.21 | 48105.83 | 18673 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194049.04
Mientra | 3394986.09 | 3543047.577 | 1071481.813 | 3068952.873 | 640239.452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11718707.805
Al Jazi Mall | 7032183.012 | 11461307.764 | 10348233.564 | 8121301.472 | 10209571.478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47172597.29
Nefisha Bridge | 1486464.98 | 259685.05 | 50288.6 | 556464.6 | 1390.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2354294.001
Mohammed Ali Palace | 821499.998 | 702324.613 | 1092235.919 | 1611635.414 | 2491746.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6719442.064
Fish Market | 2091965.833 | 9003807.33 | 12639798.007 | 6402980.916 | 1660387.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31798939.168
Benban Solar Power | 7008729.653 | 15898281.014 | 6486380.173 | 8990495.706 | -9132938.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29250948.522
Alamein | 654033.969 | 3333038.515 | 1794511.366 | 2938065.356 | 2107051.768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10826700.974
R05 - Zone 1 | 20285532.581 | 27561185.394 | 10881749.365 | 19243976.163 | 16567167.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94539611.203
R05 - Zone 2 | 4594766.41 | 32091848.511 | 17617918.519 | 18179559.3 | 19276756.593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91760849.333
R05 - Zone 3 | 1231.71 | -16807147.83 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16805916.12
Sokhna Tunnel 2 | 563018.089 | 576598.868 | 624494.323 | 231930.304 | 906834.039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2902875.623
Abu Sultan Bridge 2 | 10197831.019 | 5182335.506 | 6782071.665 | 2918991.501 | 1050186.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26131416.241
El Sewedy University | 5657456.436 | 7488543.008 | 9546284.986 | 16134624.859 | 28301062.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67127971.909
Substation Elco Steel | 8037921.563 | 7264107.937 | 371094.68 | 493548.21 | 329785.684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16496458.074
PKG 101 | 486026.692 | 1524740.77 | 2847720.458 | 2915018.559 | 1713827.908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9487334.387
PKG 144 | 2413811.516 | 9323709.848 | 14754703.766 | 18126354.357 | 12498418.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57116998.367
Port of Sokhna | 1264997.251 | 8383459.618 | 3714776.9 | 11194453.048 | 9798102.973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34355789.79
EDNC Offices & Retail Project | 63560.085 | 774631.626 | 2484309.359 | 27664184.64 | 9020729.407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40007415.117
مشروع الامل | 144815.769 | 58.97 | 44605.011 |  | 32329.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221808.782
مشروع مصنع الاسمنت | 0 | 6213950.07 | 1552 | 61176.12 | -69541.983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6207136.207
Olympic Multi Sports Hall | 0 | 0 | 1765194.28 | 47178.856 | 3814914.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5627287.533
PKG 140 Mivida | 0 | 0 | 625532.27 | 523611.12 | 552230.632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1701374.022
EGAT Elco Steel | 0 | 0 | 849374.95 | 14999725.197 | 9547748.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25396848.763
Pyramid Tunnel | 0 | 0 | 29598.78 | 28577.889 | 28783.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86959.699
Abo Ghazala Lock & Load | 0 | 0 | 100300.53 | -20240 | 106162.192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186222.722
Mohamed Aly Fahly Lock & Load | 0 | 0 | 0 | 82280 | 953401.801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035681.801
محطه كهرباء المستثمرين بالقطامي | 0 | 0 | 70946 | 100572.274 | 1997.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173515.944
كوبرى شبرا بنها | 0 | 0 | 284911.7 | 0 | [8 empty] | 284911.7
Sub Total | 171123634.276 | 299017938.666 | 244257455.637 | 271459465.985 | 206934381.108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192792875.672 | 100573100.5072 | 7.776%
Closed Projects
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ميناء دبى السخنة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مشاريع منتهية | 866121.754 | 169251.387 | 1932066.332 | 180356.52 | 375782.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3523578.181
Sub Total | 866121.754 | 169251.387 | 1932066.332 | 180356.52 | 375782.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3523578.181
Trade Activities
ابناء مصر للتعمير | 0 | 0 | 0 | 0 | 82701.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82701.3
ابناء حسن علام | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EMAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KAM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 82701.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82701.3
Total | 171989756.03 | 299187190.053 | 246189521.969 | 271639822.505 | 207392864.596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196399155.153 | 96966821.0262
| 19928292.4179 | 18364102.8912 | 28805299.5944 | [9 empty] | 717366469 | 7.497%
| 10.38% | 5.783% | 10.47% | 0% | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 55.47%
Projects Indirect Cost | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2017-04-01 | 42856 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | Total
Construction Overheads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SG&A Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Indirect Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction Activities
نادي سوديك | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
عمائر اب تاون 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مشروع الكيان | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tamay Elamdeed substation (Alestom ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
نفق العاصمة | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bani Sweif substation (Alestom ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ismalia substation (Alestom ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
مبنى وزارات الجيش | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
رويال سيتى | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
كوبري الأمل لوك لود | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hyper ismalia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.I.PARKS - SLP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rolling Mills | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Siemens | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade Activities
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
31301123.332
65665697.6942
5.077%

## Sheet6 (hidden)
Description | Cost Incured To Date |  | 105826293.69
Al Oula | 0 | 0% | 0
Hyper Al Sulaimaniya | 0 | 0% | 0
New Giza I | 43372 | 0.001814% | 1920.0542
Maxim mall | 7004292.549 | 0.293% | 310076.1203
Attaka | 0 | 0% | 0
مول مصر | 25695620.04 | 1.075% | 1137530.7521
مراسى تانك الخزان الجديد PKG22 New | 167634.485 | 0.007013% | 7421.0851
نادي سوديك | 61687831.928 | 2.581% | 2730885.8761
شرم الشيخ | 0 | 0% | 0
عمائر اب تاون 53 | 58089552.769 | 2.43% | 2571592.0669
New Giza phase 2 | 9356763.307 | 0.3914% | 414218.6873
Beni suef | 16340364.575 | 0.6836% | 723378.8161
كوبرى الشيخ بن زايد - كوبرى العاصمة | 0 | 0% | 0
جبل الزيت - GAMISA | 2337010.224 | 0.09776% | 103458.1378
PKG62 | 21224500.411 | 0.8879% | 939596.7825
محطه كهرباء المستثمرين بالقطامي | 2629450.27 | 0.11% | 116404.2953
لوك اند لوت كوبرى الغرابلى - الاس | 0 | 0% | 0
سور لوك اند لود ( اوراسكوم) | 0 | 0% | 0
مشروع الكيان | 347892390.159 | 14.55% | 15401001.8672
مشروع الامل | 1607976.577 | 0.06727% | 71184.2253
مشروع مصنع الاسمنت | 15116350.589 | 0.6323% | 669192.4004
سور نيو جيزة | 0 | 0% | 0
Tamay Elamdeed substation (Alestom ) | 54129906.509 | 2.264% | 2396300.7378
Wind Farm KFW | 53577.161 | 0.002241% | 2371.831
Wind Farm FIEM | 1722486.827 | 0.07206% | 76253.5301
PkG 107 | 7697857.733 | 0.322% | 340779.8638
كباري الأسماعيلية | 8029220.118 | 0.3359% | 355449.0915
نفق العاصمة | 108894769.215 | 4.555% | 4820710.6319
Bani Sweif substation (Alestom ) | 52631513.09 | 2.202% | 2329967.6978
Ismalia substation (Alestom ) | 25025907.781 | 1.047% | 1107882.9643
مبنى وزارات الجيش | 402801096.57 | 16.85% | 17831779.6418
رويال سيتى | 107249636.19 | 4.486% | 4747881.5115
كوبرى شبرا بنها | 116051.62 | 0.004855% | 5137.5404
كوبري الأمل لوك لود | 1622495.915 | 0.06787% | 71826.9882
Hyper ismalia | 44675700.661 | 1.869% | 1977768.3237
P.I.PARKS - SLP | 35115214.828 | 1.469% | 1554530.9539
Rolling Mills | 155328509.406 | 6.498% | 6876306.384
Siemens | 177389327.447 | 7.421% | 7852926.481
PKG 117 | 21480808.762 | 0.8986% | 950943.4101
Kayan Lock Load | 47952513.121 | 2.006% | 2122830.9817
Sokhna Tunnel | 37465929.964 | 1.567% | 1658595.8005
Abu Sultan Bridge | 13705180.686 | 0.5733% | 606720.6967
Mientra | 78561198.162 | 3.286% | 3477860.3781
Al Jazi Mall | 87994977.756 | 3.681% | 3895488.5334
Nefisha Bridge | 48012449.949 | 2.008% | 2125484.3516
Mohammed Ali Palace | 5562926.127 | 0.2327% | 246267.6336
Fish Market | 12479184.655 | 0.522% | 552446.5369
Benban Solar Power | 82955285.203 | 3.47% | 3672384.158
Alamein | 10269346.39 | 0.4296% | 454618.2308
R05 - Zone 1 | 32681023.749 | 1.367% | 1446770.674
R05 - Zone 2 | 47423662.782 | 1.984% | 2099419.0724
R05 - Zone 3 | 16805916.115 | 0.703% | 743988.5229
Sokhna Tunnel 2 | 12919682.818 | 0.5405% | 571947.1447
Abu Sultan Bridge 2 | 39238906.959 | 1.641% | 1737084.5021
El Sewedy University | 19465324.897 | 0.8143% | 861719.0648
Substation Elco Steel | 16937734.958 | 0.7085% | 749824.0694
PKG 101 | 124549.894 | 0.00521% | 5513.7543
PKG 144 | 1251659.072 | 0.05236% | 55410.2483
Port of Sokhna | 1832666.15 | 0.07666% | 81131.1072
EDNC Offices & Retail Project | 500359.87 | 0.02093% | 22150.6521
Mostakbal Lock Load | 2062745 | 0.08629% | 91316.5694
30 June Tunnel Lock load | 541887.79 | 0.02267% | 23989.0699
Middle Tunnel Lock Load | 602067.416 | 0.02519% | 26653.1883
Total | 2390504369.199 | 100% | 105826293.69
Trial Balance

## Sheet5 (hidden)
Description | New Giza I | Maxim mall | مول مصر | مراسى تانك الخزان الجديد PKG22 New | نادي سوديك | عمائر اب تاون 53 | New Giza phase 2 | Beni suef | جبل الزيت - GAMISA | PKG62 | محطه كهرباء المستثمرين بالقطامي | مشروع الكيان | مشروع الامل | مشروع مصنع الاسمنت | Tamay Elamdeed substation (Alestom ) | Wind Farm FIEM | PkG 107 | كباري الأسماعيلية | نفق العاصمة | Bani Sweif substation (Alestom ) | Ismalia substation (Alestom ) | مبنى وزارات الجيش | رويال سيتى | كوبرى شبرا بنها | كوبري الأمل لوك لود | Hyper ismalia | P.I.PARKS - SLP | Rolling Mills | Siemens | PKG 117 | Kayan Lock Load | Sokhna Tunnel | Abu Sultan Bridge | Mientra | Total
[15 empty] | Tamay Elamdeed substation (Alostom ) |  |  |  |  | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom ) | Tamay Elamdeed substation (Alostom )
Total Contract Price | 172181998.814 | 95704579 | 171490065 | 16510059.28 | 99588109 | 270610661 | 144891598 | 324195538 | 117257000 | 40934935 | 130103216.3586 | 420103550 | 30857015 | 206723720 | 95970234.5006 | 63390614 | 46325341 | 56652000 | 467255000 | 95970234.5006 | 95970234.5006 | 329870053 | 409523809.836 | 2800000 | 9050320 | 51838240 | 32000000 | 264370000 | 311000000 | 39336927 | 107782440 | 62970000 | 49383500 | 87000000 | 5450337687.827
Additions (Deductions) | 34797.2265 | 0 | -5490065 | 1000000 | 48900025 | 38140765 | 8950052 | 108395646 | 3083462.76 | 3457090 | -311033.3586 | 704505480 | -1913864 | 62410950 | 12819856.4994 | 8157000 | 7776054 | -1574053 | -54400466 | 12819856.4994 | 12819856.4994 | 238592268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1206155545.8411
Total Contracts | 172216796.0405 | 95704579 | 166000000 | 17510059.28 | 148488134 | 308751426 | 153841650 | 432591184 | 120340462.76 | 44392025 | 129792183 | 1124609030 | 28943151 | 269134670 | 108790091 | 71547614 | 54101395 | 55077947 | 412854534 | 108790091 | 108790091 | 568462321 | 409523809.836 | 2800000 | 9050320 | 51838240 | 32000000 | 264370000 | 311000000 | 39336927 | 107782440 | 62970000 | 49383500 | 87000000 | 6656493233.6681
Total Estemated Cost Of contract | 178018117.1846 | 92245938.56 | 142973982.712 | 16262187.567 | 92629183 | 264427221.9112 | 140108129 | 251025418.0745 | 84320986.93 | 41675579 | 109630210.621 | 385768894.2159 | 27546588.4725 | 187827866.3247 | 91302219 | 62621524.4937 | 42620158 | 42489000 | 408567772 | 91302219 | 91302219 | 308424824 | 381327168.1479 | 2520000 | 6335224 | 47721580.5944 | 31612131.219 | 150482575 | 295519635 | 36189973 | 82991132 | 56673000 | 44445150 | 84261035 | 4769867411.0682
Additional Cost ( Deductions) | -4321050.8598 | 9095198.6123 | -3434023.2263 | 982322.2448 | 56532406 | 51906844.0888 | 11651089 | 68785466.9255 | -3421811.471 | 756251.472 | -23182362.621 | 665728016.7841 | -7518716.5225 | 65849658.8683 | 4237832 | -20225611.4937 | 1181989 | 886407.3857 | -90323108 | 5594047 | 3612154 | 203191210.2575 | 0 | 0 | 0 | 0 | 0 | 11000000 | 0 | 0 |  |  |  |  | 1005947702.0541
Total Cost | 173697066.3248 | 101341137.1723 | 139539959.4857 | 17244509.8118 | 149161589 | 316334066 | 151759218 | 319810885 | 80899175.459 | 42431830.472 | 86447848 | 1051496911 | 20027871.95 | 253677525.193 | 95540051 | 42395913 | 43802147 | 43375407.3857 | 318244664 | 96896266 | 94914373 | 511616034.2575 | 381327168.1479 | 2520000 | 6335224 | 47721580.5944 | 31612131.219 | 161482575 | 295519635 | 36189973 | 82991132 | 56673000 | 44445150 | 84261035 | 5775815113.1223
Gross Margin | -1480270.2843 | -5636558.1723 | 26460040.5143 | 265549.4682 | -673455 | -7582640 | 2082432 | 112780299 | 39441287.301 | 1960194.528 | 43344335 | 73112119 | 8915279.05 | 15457144.807 | 13250040 | 29151701 | 10299248 | 11702539.6143 | 94609870 | 11893825 | 13875718 | 56846286.7425 | 28196641.6881 | 280000 | 2715096 | 4116659.4056 | 387868.781 | 102887425 | 15480365 | 3146954 | 24791308 | 6297000 | 4938350 | 2738965 | 866703805.5458
Gross Margin % | -0.8595% | -5.89% | 15.94% | 1.517% | -0.4535% | -2.456% | 1.354% | 26.07% | 32.77% | 4.416% | 33.4% | 6.501% | 30.8% | 5.743% | 12.18% | 40.74% | 19.04% | 21.25% | 22.92% | 10.93% | 12.75% | 10% | 6.885% | 10% | 30% | 7.941% | 1.212% | 38.92% | 4.978% | 8% | 23% | 10% | 10% | 3.148% | 13.02%
Cost Incured previous years | 173672666.3248 | 97884701.4913 | 139531961.2457 | 17215605.8728 | 85530547.4565 | 281328851.6979 | 150705293.0766 | 303632853.2089 | 79827798.99 | 31350395.01 | 82580404.8 | 417276648.83 | 19602893.42 | 244171048.42 | 5974929.59 | 41459868.49 | 33669497.75 | 25918987.81 | 151641411.89 | 30413209.04 | 17295000.11 | 186807384.97 | 50039832.72 | 1059365.13 | 3953962.38 | 4949516.78 | 10490602.45 | 57355879.24 | 3564576.99 | 2132781.61 | 3788064.4 | 0 | 0 | 0 | 3148908601.8437
Cost Incured To Date | 24400 | 3456435.681 | 7998.24 | 28903.939 | 10546401.532 | 30539065.31 | 273016.099 | 6675265.067 | 1071376.469 | 11081435.462 | 451994.034 | 95927790.486 | 424978.53 | 9506476.773 | 8605728.954 | 425869.86 | 5030393.326 | 490576.54 | 58002975.797 | 16819357.769 | 4952264.227 | 144966626.497 | 20458214.87 | 56592.6 | 2059557.25 | 420975.907 | 5941870.314 | 39763439.922 | 41237116.506 | 6834693.12 | 8010274.243 | 7604359.761 | 2019984.78 | 1518554.58 | 545234964.445
Percentage Of Completion Previous Year | 99.99% | 96.59% | 99.99% | 99.83% | 57.34% | 88.93% | 99.31% | 94.94% | 98.68% | 73.88% | 95.53% | 39.68% | 97.88% | 96.25% | 6.254% | 97.79% | 76.87% | 59.76% | 47.65% | 31.39% | 18.22% | 36.51% | 13.12% | 42.04% | 62.41% | 10.37% | 33.19% | 35.52% | 1.206% | 5.893% | 4.564% | 0% | 0% | 0% | 54.52%
Percentage Of Completion Current Year | 0.01405% | 3.411% | 0.005732% | 0.1676% | 7.07% | 9.654% | 0.1799% | 2.087% | 1.324% | 26.12% | 0.5229% | 9.123% | 2.122% | 3.747% | 9.007% | 1.005% | 11.48% | 1.131% | 18.23% | 17.36% | 5.218% | 28.34% | 5.365% | 2.246% | 32.51% | 0.8821% | 18.8% | 24.62% | 13.95% | 18.89% | 9.652% | 13.42% | 4.545% | 1.802% | 9.44%
Percentage Of Completion YTD | 100% | 100% | 100% | 100% | 64.41% | 98.59% | 99.49% | 97.03% | 100% | 100% | 96.05% | 48.81% | 100% | 100% | 15.26% | 98.8% | 88.35% | 60.89% | 65.88% | 48.75% | 23.44% | 64.85% | 18.49% | 44.28% | 94.92% | 11.25% | 51.98% | 60.14% | 15.16% | 24.78% | 14.22% | 13.42% | 4.545% | 1.802% | 63.96%
Total Revenue (Cost to Cost) | 172216796.0405 | 95704579 | 166000000 | 17510059.28 | 95643167.7308 | 304392332.1867 | 153050025.5858 | 419737296.5894 | 120340462.76 | 44392025 | 124664251.9591 | 548888295.0136 | 28943151 | 269134670 | 16602787.556 | 70686639.9969 | 47799439.9124 | 33534776.3453 | 271968852.1918 | 53030270.9633 | 25499635.4633 | 368637829.8908 | 75710915.5775 | 1239953.0333 | 8590742.3286 | 5833773.4283 | 16634092.9311 | 158998173.0652 | 47148564.8568 | 9747255.0982 | 15322766.3757 | 8449288.6233 | 2244427.5333 | 1567916.279 | 4328573776.3475
2017 | 9511449.5614 | 5485567.2463 | 9904897.1077 | 1030634.5218 | 39798225.5477 | 134881511.8124 | 56056648.9551 | 123522793.5447 | 25684620.6333 | 28163936.2196 | 77406632.2719 | 355833205.1927 | 12985911.0457 | 195606026.4381 | 6716378.4968 | 68407978.9717 | 41586244.5561 | 32911843.8981 | 196722369.6827 | 34146370.2953 | 19823390.034 | 203157390.9498 | 53739949.9715 | 1177072.3667 | 5648517.6857 | 5376482.4117 | 10619318.1369 | 100763651.836 | 3751302.1559 | 2318240.8702 | 4919643.9917 | 0 | 0 | 0 | 1891836525.0218
2016 | 9825572.1733 | 52181178.6179 | 90673109.605 | 8465847.1175 | 32352499.287 | 93806619.9612 | 73992787.8947 | 251360712.2887 | 93280099.6426 | 4989453.3976 | 46578999.0652 | 90457299.6801 | 15957239.9543 | 70335211.7734 | 87188.4577 | 1559960.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115367175.2301
2015 | 131211720.3058 | 37462470.4658 | 65421993.2873 | 8013577.6407 | 12993657.6901 | 45897167.3534 | 22723826.3245 | 35824514.536 | 1375742.4841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618443765.6329
2014 | 21668054 | 575362.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80811114.67
2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5206901.425
2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3773153.1797
POC Revenues 2018 | 0 | 1.7462e-09 | -3.7253e-08 | 0 | 10498785.206 | 29807033.0597 | 276762.4115 | 9029276.2201 | 1.8859e-08 | 11238635.3827 | 678620.6219 | 102597790.1408 | 0 | 3193431.7885 | 9799220.6015 | 718700.7002 | 6213195.3563 | 622932.4472 | 75246482.5091 | 18883900.6681 | 5676245.4292 | 165480438.941 | 21970965.606 | 62880.6667 | 2942224.6429 | 457291.0165 | 6014774.7942 | 58234521.2292 | 43397262.7009 | 7429014.228 | 10403122.384 | 8449288.6233 | 2244427.5333 | 1567916.279 | 613135141.1878 | 613135141.1878
| 0% | 1.825e-15% | -2.244e-14% | 0% | 7.07% | 9.654% | 0.1799% | 2.087% | 1.567e-14% | 0.25317 | 0.5229% | 9.123% | 0% | 1.187% | 9.007% | 1.005% | 11.48% | 1.131% | 18.23% | 0.2027% | 0.2027% | 0.2027% | 0.2027% | 0.2027% | 32.51% | 0.8821% | 18.8% | 22.03% | 13.95% | 18.89% | 9.652% | 13.42% | 4.545% | 1.802% | 9.211%

## Sheet4 (hidden)
0
-8539793.848 | -8539793.85 | 0.0019641
-6858460.6269 | -6858461.24 | 0.61307
-5326108.4494 | -5326108.46 | 0.010617
-3313309.0172 | -4705940.24 | 1392631.2228
-785931.9875 | -785931.99 | 0.0025355
0 | -0.94 | 0.94
0 | -0.73 | 0.73
0 | -0.13 | 0.13
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 |  | 0
0 |  | 0
0 |  | 0
0 |  | 0
0 |  | 0
1.8626e-08 |  | 1.8626e-08
3.7253e-08 | 24658.67 | -24658.67
71428.57 | 71428.57 | 2.6601e-08
122985.3457 | 122985.35 | -0.0043445
171198.2233 | 171198.22 | 0.0032742
176878.7868 | 176878.84 | -0.053193
259473.4611 | 259473.4 | 0.061075
285932.6024 | 285932.6 | 0.0024044
938414.8955 | 343655.16 | 594759.7355
| 350513.94 | -350513.94
| 733743.87 | -733743.87
| 1381731 | -1381731
1423649.3049 | 1423652.54 | -3.2351
1703402.9667 | 1703402.25 | 0.71667
2359506.791 | 2302158.65 | 57348.141
2812546.3673 | 2359506.8 | 453039.5673
2888031.6419 | 2888031.68 | -0.038112
4189036.6625 |  | 4189036.6625
4281118.9224 | 4281118.97 | -0.04764
5012603.9087 | 4291008.21 | 721595.6987
5180745.5289 | 5012603.48 | 168142.0489
5244612.3483 | 5180745.53 | 63866.8183
5511002.326 | 5511002.29 | 0.035968
6656499.0278 | 5944820.21 | 711678.8178
| 6656499.13 | -6656499.13
7538675.8226 | 7538675.81 | 0.012645
7918893.7112 |  | 7918893.7112
8574168.4009 | 8574162.69 | 5.7109
21051255.3193 | 21051255.56 | -0.24065
32903786.0703 | 32903783.84 | 2.2303
34784965.2942 | 34784964.97 | 0.32415
53102074.2503 | 53102074 | 0.25029