## Revise Cost 2023
[11 empty] | 480773005.7143 | 593999146.6667
[11 empty] | 113226140.9524 | [5 empty] | -1922518.4604
Operation | Type of Project | Client | Serial | Projects Manager | Cost Center | Project Name | Revised Contract Amount | Forcast Gross Margine% | Tender GM% | Total EAC Cost | AC before 2023 | Gross Margine % before 2023(Planned) | Cum Gross Margine till 2023 | ETC 2023 | Revised ETC 2023 | Gross Margine % 2023 | ETC 2024 | Gross Margine % 2024 | ETC 2022 |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | [12 empty] | OLD GM% | POC Dec GM%
1 | Residential | Private | 1 | Osama Mezayn | 137 | ORA Zed PKGs A & D | 952143211 | 0.5% | 0.5% | 947382494.945 | 659536506.15 | 5% | 0.5% | 128424714.7181 | 287845988.795 | -11.61% | 0 | #DIV/0! | 0 | 19670464.9268 | 18780845.91 | 19140158.48 | 26871348.1 | 22801266.9984 | 27776266.9984 | 26948733.0016 | 26213113.0837 | 28357500 | 27362500 | 27661000 | 27661000 | 8272256.2229 | [6 empty] | 172476102.3081 | 63594256.2229 |  | -1.249e-14% |  | 200252369.3066 | 5% | 5% | FALSE | 5% | 0.5% | 5% | 0.5% | -11.61% | #DIV/0! | 287845988.795 | 12 | 8
1 | Industrial | Private | 2 | Mohamed El Saman | 94 | DP World Sokhna | 1611128362.46 | 25.54% | 10.44% | 1191147145 | 1199577796.4909 | 25.54% | 25.54% | 0 | 0 | #DIV/0! | -8430651.4909 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -8430651.4909 | 0 |  | 0% |  |  | 26.4% | 25.54% | FALSE
1 | Commercial | Private | 3 | Other | 92 | Sodic East - EDNC | 1145187121 | 5.774% | 5.36% | 1079069736 | 1063500266.6138 | 4.551% | 5.774% | 0 | 15569469.1804 | 49.74% | 0.20585 | 5.773% | 0 | 8713668.5019 | -4907606.74 | 4726159.2 | 2826794.9828 | 4899777.9702 | 5197548.7846 | 2826794.9828 | 0 | 0 | 0 | 0 | 0 | 0 | 316361452.5552 | 0 | 316361452.5552 | 0 | 0 | 316361452.5552 | 2826795.1886 | 0 |  | 1.596e-14% |  | 8024343.7674 | 6% | 4.551% | FALSE | 5.774% | 5.774% | 4.551% | 5.774% | 49.74% | 5.773% | 15569469.1804 | 6 | 2
1 | Commercial | Private | 4 | Mohamed Fawzy | 113 | CFC Poduim 2 | 637419839.0635 | 25.73% | 11.9% | 473408781.0473 | 467108794.124 | 25.73% | 25.73% | 0 | 6299986.5933 | 25.73% | 0.32994 | 25.73% | 0 | 133396.91 | 133396.91 | 5229.51 | 0 | 0 | 3740214.0242 | 0 | 0 | 2421146.1491 | 0 | 0 | 0 | 0 | 183794676.9907 | 138626.42 | 183656050.5707 | 0 | 0 | 183656050.5707 | 2421146.4791 | 0 |  | 0% |  | 6161360.1733 | 23.93% | 25.73% | FALSE | 25.73% | 25.73% | 25.73% | 25.73% | 25.73% | 25.73% | 6299986.5933 | 4 | 2
1 | Commercial | Private | 5 | Mohamed Fawzy | 141 | ElSewedy HQ Internal Finishing | 362983478.4 | 6.357% | 7.74% | 335759717.52 | 281765408.09 | 7.5% | 6.357% | 2639341.36 | 58141511.8828 | 0.3952% | -4147202.4528 | 1264080029% | 0 | 2671941.7084 | 6152223.04 | 16993342.21 | 0 | 0 | 0 | 14046379.8151 | 0 | 0 | 20949566.8177 | 0 | 0 | 0 | [6 empty] | 30848744.18 | 0 |  | 0% |  | 34995946.6328 | 7.5% | 7.5% | TRUE | 6.357% | 6.357% | 7.5% | 6.357% | 0.3952% | 1264080029% | 58141511.8828 | 4 | 2
1 | Residential | Private | 6 | Osama Mezayn | 138 | Creek | 1649774678 | 8% | 7.5% | 1517792703.76 | 794715230.84 | 7.5% | 8% | 478833444.65 | 489563965.21 | 8.8% | 233513507.71 | 8% | 0 | 19863828.3611 | 19971783.95 | 56450549.54 | 34090545.72 | 33182258.24 | 28593969.84 | 39191537.24 | 41873328.96 | 40099825.64 | 37793969.84 | 54870304.2 | 52564448.4 | 50881443.64 | [6 empty] | 550788365.63 | 158316196.24 |  | -1.388e-14% |  | 345868827.76 | 7.5% | 7.5% | TRUE | 7.5% | 8% | 7.5% | 8% | 8.8% | 8% | 489563965.21 | 12 | 8
1 | Industrial | Private | 7 | Other | 125 | LEKELA Wind Farm | 211394745 | 10.06% | 8.75% | 194483165 | 190138800.03 | 10.06% | 10.06% | 0 | 0 | #DIV/0! | 4344364.97 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 4344364.97 | 0 |  | 0% |  |  | 8% | 10.06% | FALSE
1 | Infrastructure | Private | 8 | Mohamed Fawzy | 123 | Marassi PKG #162& #163 (Marina) | 780000000 | 22% | 10.74% | 608400000 | 506868500.88 | 22% | 22% | 133330523.8413 | 101531499.3809 | 22% | -0.26095 | 22% | 0 | 7390757.11 | 7390757.11 | 5725950.83 | 5906435.0019 | 23859815.9693 | 20428540.4697 | 22620000 | 15600000 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 101531499.3809 | 38219999.7391 | 0 |  | 0% |  | 58648540.4697 | 22% | 22% | TRUE | 22% | 22% | 22% | 22% | 22% | 22% | 101531499.3809 | 7 | 3
1 | Commercial | Private | 9 | Mohamed Fawzy | 142 | Marassi PKG #178 | 48853931 | 38.55% | 13.26% | 33733263 | 30022752.5634 | 38.55% | 38.55% | 0 | 0 | #DIV/0! | 3710510.4366 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31210606.0619 | 0 | 31210606.0619 | 0 | 0 | 31210606.0619 | 3710510.4366 | 0 |  | 0% |  |  | 33.46% | 38.55% | FALSE
1 | Commercial | Private | 10 | Mohamed Fawzy | 119 | Elswedy University Phase2 | 608748209 | 15.24% | 8.32% | 515954198 | 513109475.829 | 15.24% | 15.24% | 2844722.171 | 2844722.4907 | 15.24% | -0.3197 | 15.24% | 0 | 0 | 0 | 0 | 1024719.8513 | 148142.0066 | 483439.2227 | 606719.7947 | -3451.7233 | 157154.7028 | 102251.2799 | 0 | 325747.3559 | 0 | [5 empty] | 0.73025 | 1188421.0905 | 325747.3559 |  | 0% |  | 1671860.6328 | 13.96% | 15.24% | FALSE | 15.24% | 15.24% | 15.24% | 15.24% | 15.24% | 15.24% | 2844722.4907 | 8 | 6
1 | Commercial | Private | 11 | Mohamed Fawzy | 63 | Royal City Mall | 558284383 | 4.61% | 6.6% | 532547472.9437 | 501618019.1968 | 4.61% | 4.61% | 25301126.5613 | 30929453.7002 | 4.61% | 0.046689 | 4.61% | 0 | 737673.76 | 737673.76 | 455351.29 | 9539000 | 0 | 0 | 15762126.5613 | 0 | 0 | 4435302.0889 | 0 | 0 | 0 | [5 empty] | 43572.3612 | 20197428.6969 | 0 |  | -9.021e-15% |  | 20197428.6502 | 4.61% | 4.61% | TRUE | 4.61% | 4.61% | 4.61% | 4.61% | 4.61% | 4.61% | 30929453.7002 | 5 | 2
1 | Railway | Government | 12 | Other | 98 | Mivida PKG #140 | 174061650 | 21.66% | 7.79% | 136366257.226 | 136366257.226 | 21.66% | 21.66% | 0 | 0 | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 49930.4505 | 0 | 0 |  | 0% |  |  | 22.37% | 21.66% | FALSE
1 | Commercial | Armed Forces |  | Mohamed Fawzy | 111 | Hyper One Parking | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 |  | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | #DIV/0! |  |  |  |  | TRUE
1 | Commercial | Armed Forces |  | Mohamed Fawzy | 112 | IKEA Retail | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | #DIV/0! |  |  |  |  | TRUE
1 | Residential | Government |  | Mohamed Fawzy | 107 | Duoble Tree Hilton | 61162019 | 2.7% |  | 59510343.719 | 59510668.719 | 2.7% | 2.7% | 144059.7059 | 127975.6191 | 2.7% | -128300.6191 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127975.6191 | 0 | 0 | [6 empty] | -325 | 127975.6191 |  | 6.592e-15% |  |  | 2.91% | 2.7% | FALSE
1 | Infrastructure | Government | 13 | Other | 81 | Al Jazi Mall | 250270773 | 8.133% | 8.31% | 229915091.643 | 229915091.643 | 8.133% | 8.133% | 0 | 0 | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | 0% |  |  | 8.133% | 8.133% | TRUE
1 | Infrastructure | Government |  | Other | 95 | PKG#101 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
2 | Commercial | Armed Forces | 14 | Aly Tawfik | 134 | Re-newal Cairo -Alex Rail way | 1019541005 | 17% | 13.15% | 851316739.175 | 685814718.5 | 16.5% | 17% | 45832685.2819 | 41451562.9093 | 24.48% | 124050457.7657 | 13.44% | 0 | 13976556.7564 | 9869881.61 | 7995440.72 | 12449999.9966 | 11136240.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 124050457.7657 | 0 |  | 0% |  | 0 | 13% | 16.5% | FALSE | 17% | 17% | 16.5% | 17% | 24.48% | 13.44% | 41451562.9093 | 4 | 0
2 | Bridges | Government | 15 | Mohamed El Ashry | 60 | Ministry Building | 2804097276 | 1.75% | 6.5% | 2755025573.67 | 2549259624.3335 | 1.75% | 1.75% | 117777671.6642 | 120075687.1947 | 1.75% | 85690262.1418 | 1.75% | 0 | 5044866.33 | 5044866.33 | 30962202.86 | 19207770.7319 | 14990258.3421 | 14788795.3174 | 14295270.7319 | 10961522.9871 | 9824999.8944 | 0 | 0 | 0 | 0 | [6 empty] | 120772055.7551 | 0 |  | -1.561e-14% |  | 49870588.9308 | 1.75% | 1.75% | TRUE | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 1.75% | 120075687.1947 | 8 | 4
2 | Bridges | Government | 16 | Adel Rahmo | 99 | Olympic Multi-Sports Hall | 1165047130 | 3.5% | 6% | 1124270480.45 | 994380345.114 | 3.5% | 3.5% | 124580381.1313 | 129890135.336 | 3.5% | 0 | #DIV/0! | 0 | 7534348.57 | 7534348.57 | 9179426.8 | 8933256.2851 | 8933256.2851 | 14723256.2851 | 20513256.2851 | 18770993.4839 | 14723256.2851 | 12584330.8505 | 8685000 | 5309754.2061 | 0 | [6 empty] | 80586591.1107 | 13994754.2061 |  | 0% |  | 95309847.3958 | 4% | 3.5% | FALSE | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | #DIV/0! | 129890135.336 | 11 | 7
2 | Restoration | Armed Forces | 17 | Adel Rahmo | 88 | R05 District | 2636647844 | 1.5% | 5.5% | 2597098126.34 | 1696219788.9098 | 1.5% | 1.5% | 311449098.1542 | 295870110.4979 | 1.5% | 605008226.9323 | 1.5% | 0 | 20169755.75 | 20169755.75 | 17701109.89 | 15346986.4945 | 20362215.453 | 27463358.8471 | 28295212.9484 | 29373688.3866 | 27301231.9834 | 27052442.9714 | 27373301.7157 | 28674583.9516 | 26756222.1062 | [6 empty] | 799834910.9957 | 82804107.7736 |  | 3.816e-15% |  | 222290042.9105 | 2.5% | 1.5% | FALSE | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 295870110.4979 | 12 | 8
2 | Restoration | Armed Forces | 18 | Mohamed Abdelfath | 133 | GOV2-Infra | 1187719109 | 3% | 5.44% | 1152087535.73 | 466188793.561 | 3% | 3% | 346941586.6719 | 66790962.47 | 3% | 619107779.699 | 3% | 0 | 4171282.41 | 4171282.41 | 5680680.06 | 4850000 | 8148000 | 6111000 | 4850000 | 6305000 | 6499000 | 5432000 | 4656000 | 4850000 | 5238000 | [6 empty] | 656937779.699 | 14744000 |  | -1.561e-14% |  | 43941000 | 3% | 3% | TRUE | 3% | 3% | 3% | 3% | 3% | 3% | 66790962.47 | 12 | 8
2 | Bridges | Government | 19 | Mohamed Abdelfath | 140 | Diplomatic | 708211616 | 6.495% | 6.5% | 662213271.4903 | 358366498.77 | 6.495% | 6.495% | 224890905.7985 | 178474823.505 | 6.495% | 125371949.2153 | 6.495% | 0 | 9934567.51 | 9934567.51 | 5373546.62 | 3802827.7778 | 9548045.1561 | 15842560.9802 | 23571881.8138 | 25443895.1549 | 24179248.497 | 19869812.4985 | 19869812.4985 | 10519312.4992 | 10519312.4992 | [6 empty] | 259345224.6763 | 40908437.4969 |  | 0% |  | 149815836.4412 | 6.5% | 6.495% | FALSE | 6.495% | 6.495% | 6.495% | 6.495% | 6.495% | 6.495% | 178474823.505 | 12 | 8
2 | Commercial | Government | 20 | Adel Rahmo | 45 | Kyan Project | 1313402430 | 2.919% | 6.5% | 1268629884.2702 | 1263499617.734 | 3.409% | 2.919% | 0 | 14418079.44 | -74.9% | -9287812.9038 | -216.7% | 0 | 941467.7054 | 936711.98 | 13481367.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -9287812.9038 | 0 |  | 0% |  | 0 | 1.791% | 3.409% | FALSE | 2.919% | 2.919% | 3.409% | 2.919% | -74.9% | -216.7% | 14418079.44 | 2 | 0
2 | Industrial | Private | 21 | Adel Rahmo | 127 | Kayan Lanscape | 99199992.95 | 10.57% | 6.98% | 94462830.14 | 88718700.68 | 10.57% | 10.57% | 0 | 0 | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5744129.46 | 0 |  | 0% |  |  | 4.775% | 10.57% | FALSE
2 | Industrial | Private | 22 | Hussin Bahgat | 122 | Ring Road Bridge | 738272282 | 7% | 8.5% | 686593222.26 | 653313576.67 | 7% | 7% | 34558436.2352 | 33279645.5888 | 7% | 0.0012499 | 6.998% |  | 2593559.14 | 2593559.14 | 1634068.13 | 2615604.54 | 3674967.54 | 4505426.85 | 7962329.85 | 3190502.64 | 3026559.45 | 2345315.85 | 1731311.5988 | 0 | 0 | [6 empty] | 18256019.39 | 1731311.5988 |  | 0% |  | 22761446.2388 | 3% | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 6.998% | 33279645.5888 | 10 | 6
2 | Commercial | Private | 23 | Hussin Bahgat | 130 | Kafer Shoukr Bridge | 119162686 | 2.147% | 9% | 107849651.635 | 116604507.683 | 2.147% | 5.887% | 0 | 50000 | 98.96% | -8804856.048 | 0% | 0 | 4686425.109 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -8804856.048 | 0 |  | 3.741% |  |  | 4.882% | 2.147% | FALSE | [7 empty] | 1 | 0
2 | Industrial | Government |  | Hussin Bahgat | 121 | El-Hegaz Square | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -118931000 | -10703790 | #DIV/0! |  |  |  |  | TRUE
2 | Commercial | Armed Forces |  | Hussin Bahgat | 128 | Abass Akad | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -106237173 | -9030159.705 | #DIV/0! |  |  |  |  | TRUE
2 | Residential | Private |  | Hussin Bahgat | 129 | 10th Ramadan Bridge | 93910355 | 24.93% |  | 84495793.146 | 70495793.146 | 24.93% | 24.93% | 0 | 0 | #DIV/0! | 14000000 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 14000000 | 21211343 | 1802964.155 | 0% |  |  | 10.03% | 24.93% | FALSE
2 | Bridges | Government |  | Hussin Bahgat | 131 | EL Shrouk Bridge | 0 |  |  | 23239621.84 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 23239621.84 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 23239621.84 | 0 | 0 | #DIV/0! |  |  | 21.16% |  | FALSE
2 | Commercial | Private |  | Hussin Bahgat | 135 | Hassan El Mamoun Bridge | 0 |  |  | 89004811.596 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 89004811.596 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 89004811.596 | 0 |  | #DIV/0! |  |  | 5.112% |  | FALSE
2 | Commercial | Armed Forces | 24 | Mariam youssef | 78 | Mohamed Ali Palace | 140842068 | 5% | 21.57% | 133799964.6 | 129266614.516 | 5% | 5% | 5088613.2769 | 4533350.0801 | 5% | 0.0039316 | 5% | 0 | 18843.02 | 18843.02 | 12617.56 | 246731.4281 | 78215.9185 | 166875.9092 | 658147.7178 | 431307.4792 | 237500 | 560524.8806 | 38014.6745 | 0 | 2084571.4922 | [6 empty] | 4010066.2481 | 2122586.1666 |  | 9.714e-15% |  | 4176942.1534 | 8.07% | 5% | FALSE | 5% | 5% | 5% | 5% | 5% | 5% | 4533350.0801 | 11 | 7
2 | Industrial | Government | 25 | Mariam youssef | 124 | Sultana Malak | 157995180 | 12% | 15% | 139035758.4 | 120855140.7 | 12% | 12% | 17569993.7954 | 18180617.7014 | 12% | -0.0013522 | 12% | 0 | 206601.12 | 206601.12 | 1358.9 | 3688323.59 | 2826524.06 | 2926110.9874 | 2843899.6813 | 2843899.6813 | 2843899.6813 | 0 | 0 | 0 | 0 | [6 empty] | 8531699.0426 | 0 |  | 0% |  | 11457810.0314 | 12% | 12% | TRUE | 12% | 12% | 12% | 12% | 12% | 12% | 18180617.7014 | 8 | 4
2 | Infrastructure | Armed Forces | 26 | Mohamed Abdelfath | 52 | Ismalia Substation | 111577500 | 20.71% | 5.43% | 93574974.6595 | 88465391.313 | 20.71% | 20.71% | 0 | 0 | #DIV/0! | 5109583.3465 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5109583.3465 | 0 |  | 0% |  |  | 14.47% | 20.71% | FALSE
2 | Bridges | Government | 27 | Mohamed Abdelfath | 51 | Tamay Elamdeed Substation | 113026639 | 19.85% | 4.53% | 91739438.4339 | 90588865.322 | 19.85% | 19.85% | 0 | 0 | #DIV/0! | 1150573.1119 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1150573.1119 | 0 |  | 0% |  |  | 18.83% | 19.85% | FALSE
2 | Hotels | Private | 28 | Hussin Bahgat | 143 | Al khattatba Bridge | 179568714 | 4% | 7% | 172385965.44 | 164962522.386 | 4% | 4% | 10067635.3283 | 7423443.0568 | 4% | -0.0027625 | 4.001% |  | 3820251.01 | 3820251.01 | 3005495.68 | 597696.3668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -0.0027625 | 0 |  | 0% | 172385965.44 | 0 | 4% | 4% | FALSE | 4% | 4% | 4% | 4% | 4% | 4.001% | 7423443.0568 | 3 | 0
2 | Bridges | Armed Forces | 29 | Mohamed Abdelfath | 139 | Mansoura University | 600691746 | 6.11% | 6.11% | 563989480.3194 | 272679600.562 | 6.11% | 6.11% | 272033163.6486 | 220060902.8475 | 6.11% | 71248976.9099 | 6.11% |  | 6088630.18 | 6088630.18 | 11578375.23 | 13253328.1409 | 16072792.8493 | 18262007.7881 | 27415694.2152 | 22081752.8493 | 25162157.5846 | 20655800 | 18778000 | 18778000 | 21934364.0102 | [6 empty] | 226054745.5691 | 59490364.0102 |  | 0% |  | 173067776.4473 | 6.11% | 6.11% | FALSE | 6.11% | 6.11% | 6.11% | 6.11% | 6.11% | 6.11% | 220060902.8475 | 12 | 8
1 | Bridges | Government | 30 | Mohamed El Saman | 144 | Rolling Mill Eleco Steel Egat Ph02 | 420000000 | 7% | 7% | 390600000 | 278659036.6491 | 7% | 7% | 77634968.73 | 111940963.3552 | 7% | -0.0042999 | 6.999% |  | 18184809.79 | 18184809.79 | 20268024.48 | 16139426.46 | 15100027.77 | 15994866.33 | 14880000 | 11373808.5252 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 26253808.5209 | 0 |  | -1.388e-14% |  | 42248674.8552 | 7% | 7% | TRUE | 7% | 7% | 7% | 7% | 7% | 6.999% | 111940963.3552 | 7 | 3
1 | Bridges | Government | 31 | Mohamed El Saman | 147 | MDF | 440260342 | 4% | 6.21% | 422649928.32 | 283623464.78 | 4% | 4% | 51685903.2405 | 139026463.747 | 4% | -0.20698 | 4% |  | 24682218.83 | 24682218.83 | 32192376.05 | 23371554.627 | 22080000 | 18350157.12 | 18350157.12 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 18350156.913 | 0 |  | -5.551e-15% |  | 36700314.24 | 5.3% | 4% | FALSE | 4% | 4% | 4% | 4% | 4% | 4% | 139026463.747 | 6 | 2
2 | Commercial | Private | 32 | Mohamed El Ashry | 149 | KEMET | 76400000 | 1.5% | 7% | 75254000 | 66948216.47 | 1.5% | 1.5% | 3038941.276 | 6752158.4715 | 1.5% | 1553625.0585 | 1.5% |  | 2410864.45 | 2410864.45 | 1925395.03 | 242502.2712 | 224760.5498 | 222548.6929 | 288324.0551 | 274359.9004 | 330591.5975 | 344749.3542 | 190101.1766 | 239638.8381 | 58322.5558 | [6 empty] | 3279712.5361 | 488062.5705 |  | 3.469e-15% |  | 1948636.1705 | 2.5% | 1.5% | FALSE | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 6752158.4715 | 12 | 8
1 | Lock & Load | Private | 33 | Mohamed El Saman | 145 | Port of Sokhna | 1154780430 | 7% | 8.5% | 1073945799.9 | 583736515.8238 | 7% | 7% | 286939735.7448 | 447720841.8575 | 7% | 42488442.2187 | 7% |  | 65505368.55 | 65505368.55 | 59334747.857 | 40920000 | 29760000 | 29930725.68 | 34177500 | 32782500 | 31852500 | 31852500 | 32782500 | 29992499.7705 | 28830000 | [6 empty] | 264758441.9892 | 91604999.7705 |  | 0% |  | 252200725.4505 | 6.5% | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 7% | 447720841.8575 | 12 | 8
| Industrial | Private |  | Mohamed Ragab | 4 | TB2 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Commercial | Private |  | Mariam youssef | 146 | Waldorf Astoria Mock-up Room | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
2 | Bridges | Government |  | Adham Edward | 148 | Olympic City Lock&Load | 0 |  |  | 1400000 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 1400000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1400000 |  |  | #DIV/0! |  |  | 20% |  | FALSE
2 | Infrastructure | Private | 34 | Adel Rahmo | 150 | Air Defense College | 1654000000 | 3.5% | 5.5% | 1596110000 | 670242092.99 | 3.5% | 3.5% | 252719889.3917 | 304162753.0492 | 3.5% | 621705153.9608 | 3.5% |  | 45571391.2 | 45571391.2 | 34853726.83 | 14085588.7091 | 23513809.2737 | 23351368.81 | 23255266.8895 | 23255266.8895 | 23255266.8895 | 23255266.8895 | 23255266.8895 | 23255266.8895 | 23255266.8895 | [6 empty] | 784492022.1872 | 69765800.6685 |  | 1.596e-14% |  | 186138237.0364 | 4% | 3.5% | FALSE | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 304162753.0492 | 12 | 8
1 | Restoration | Armed Forces | 35 | Osama Mezayn | 151 | ORA ZED-Ph 2-Pkgs A&D | 946341608 | 2.5% | 1.63% | 922683067.8 | 328995233.264 | 2.5% | 2.5% | 367941677.025 | 297999434.585 | 2.5% |  | 100% |  | 13111621.48 | 13111621.48 | 12712051.78 | 12530913.525 | 16084003.65 | 25357093.125 | 26429744.25 | 34011929.25 | 37945556.025 | 37255646.025 | 26841292.725 | 27191178.3 | 28528404.45 | [6 empty] | 513892150.976 | 82560875.475 |  | -8.674e-15% |  | 243560844.15 | 4% | 2.5% | FALSE | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 100% | 297999434.585 | 12 | 8
2 | Bridges | Government | 36 | Hussin Bahgat | 152 | Sokhna Bridges | 354227089 | 4% | 8% | 340058005.44 | 215806196.58 | 4% | 4% | 135789722.9629 | 124251808.8567 | 4% | 0.0032931 | 4% |  | 21249378.3 | 21249378.3 | 18980504.97 | 16952583.5314 | 20310558.8241 | 19470066.8361 | 16948590.872 | 10340125.5232 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 27288716.3985 | 0 |  | 1.665e-14% |  | 46758783.2312 | 6.5% | 4% | FALSE | 4% | 4% | 4% | 4% | 4% | 4% | 124251808.8567 | 7 | 3
2 | Hotels | Private | 37 | Aly Tawfik | 153 | October Dry Port | 54091681 | 33.11% | 10.71% | 37864176.7 | 36182206.76 | 33.11% | 33.11% | 0 | 0 | #DIV/0! | 1681969.94 | 62.82% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1681969.94 | 0 |  | 0% |  |  | 30% | 33.11% | FALSE
| Restoration | Armed Forces |  | Other | 72 | Siemens Power Station | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Restoration | Armed Forces |  | Other | 69 | Rolling Mill +EGAT | 413868391 | 29.45% |  | 0 | 291999383.0789 | 29.45% | 29.45% | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -291999383.0789 | 0 |  | 0% |  |  |  | 29.45% | FALSE
1 | Null | Null |  | Mohamed Fawzy | 32 | Sodic Club House | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | #DIV/0! |  |  |  |  | TRUE
| Null | Null |  | Mohamed Fawzy | 85 | Elswedy University Phase1 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | #DIV/0! |  |  |  |  | TRUE
1 | Null | Null |  | Mohamed Fawzy | 93 | PKG#144, Marassi | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | #DIV/0! |  |  |  |  | TRUE
| Null | Null |  | Other | 76 | Mintera Factory | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Industrial | Null |  | Other | 96 | Substation Eleco | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | #DIV/0! |  |  |  |  | TRUE
| Industrial | Null |  | Other | 65 | PI Park (SLP) | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Commercial | Private |  | Mohamed Fawzy | 71 | Pkg 117 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Null | Null |  | Mohamed Fawzy | 37 | NGU2 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Industrial | Null |  | Other | 34 | PKG#53 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Bridges | Government |  | Other | 41 | PKG62 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
2 | Bridges | Government |  | Hussin Bahgat | 109 | Safeer Square Bridge | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Bridges | Government |  | Mohamed Abdelfath | 61 | French Fund Substations (Bani-swif) | 120156139.33 | 16.15% |  | 0 | 100752128.439 | 16.15% | 16.15% | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -100752128.439 |  |  | 0% |  |  |  | 16.15% | FALSE
2 | Restoration | Armed Forces |  | Hussin Bahgat | 84 | Alamain | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
2 | Commercial | Private |  | Mohamed El Ashry | 80 | Fish Market | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Industrial | Null |  | Mohamed El Ashry | 70 | hyper el-temsah | 175475889 | 19.47% |  | 0 | 141314590.5815 | 19.47% | 19.47% | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -141314590.5815 |  |  | 0% |  |  |  | 19.47% | FALSE
| Null | Null |  | Adham Edward | 120 | Mehwer el Salam L&L | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Infrastructure | Government |  | Mariam youssef | 108 | Baroon Fence | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
|  |  |  | Adham Edward | 6 | ORA Zed | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
|  |  |  | Adham Edward | 68 | Kyan lock& load | 95593679.8767 | 28.6% |  | 68254385.5096 | 70200369.6696 | 26.56% | 26.56% | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -1945984.16 |  |  | -2.036% |  |  | 28.6% | 28.6% | TRUE
|  |  |  | Adham Edward | 103 | Abu Ghazala Lock & Load | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
|  |  |  | Adham Edward | 118 | MR3 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
|  |  |  | Adham Edward | 110 | Suez Road Tunnel | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| HO | HO |  | Hussin Bahgat | 101 | Pyramid Tunnel | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Lock & Load | Armed Forces |  | Adham Edward | 104 | Mohamed Aly Fahmy lock&load | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Commercial | Private |  | Other | 13 | Hyper El Solymanya | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Commercial | Private |  | Other | 1 | PKG-85 | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Commercial | Private |  | Mohamed Fawzy | 58 | Marassi (Pkg Bp # 107) | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Industrial | Private |  | Other | 83 | TSK Solar Benban | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Lock & Load | Armed Forces |  | Adham Edward | 53 | Amal Bridge Lock & Load | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Bridges | Armed Forces |  | Hussin Bahgat | 100 | Emergency Bridge | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Bridges | Armed Forces |  | Hussin Bahgat | 89 | AbuSultan Rd Bridge2 Extension | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Bridges | Armed Forces |  | Hussin Bahgat | 59 | New Capital Tunnels | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Lock & Load | Armed Forces |  | Adham Edward | 2 | Central Road Lock & Load | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Industrial | Private |  | Mohamed Ragab | 66 | Bani Suef Old Substation | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
| Bridges | Armed Forces |  | Adham Edward | 3 | Sokhna Road | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
2 | Lock & Load | Armed Forces |  | Adham Edward | 136 | Sherouk Bridge- LOCK&LOAD | 0 |  |  | 1648128.4931 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! | 1648128.4931 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1648128.4931 |  |  | #DIV/0! |  |  | -64.81% |  | FALSE
| Industrial | Government |  | Mohamed Abdelfath | 40 | Al Mostathmreen GIS Substation | 131791643 | 34.94% |  | 0 | 85741917.6707 | 34.94% | 34.94% | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% |  |  |  | 34.94% | FALSE
| Industrial | Private |  | Other | 35 | GOE BENI SUEF 6X6000TPD | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  |  |  | TRUE
2 | Bridges | Armed Forces |  | Hussin Bahgat | 97 | Green Tunnels | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  |  |  | TRUE
| Lock & Load | Armed Forces |  | Adham Edward |  | El Moshier ( Abu Zaid Khedr) | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  |  |  | TRUE
| Lock & Load | Armed Forces |  | Adham Edward |  | Elmostaqbal Lock & Load | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  |  |  | TRUE
| Lock & Load | Armed Forces |  | Adham Edward |  | Amal Lock & Load | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  |  |  | TRUE
1 | Commercial | Private |  | Mohamed Fawzy | 154 | Alfa New Central Labs | 1403211.67 | -7.83% |  | 1479737.2 | 1513085.11 | -7.83% | -7.83% | -154289.6426 | -2.5106e-10 | -7.83% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | -2.5106e-10 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 |  | -1.943e-14% |  |  | -5.454% | -7.83% | FALSE
| Lock & Load | Armed Forces |  | Adham Edward | 155 | R06 Loack & Load | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  | 0% |  | TRUE
| Bridges | Armed Forces |  | Adham Edward | 156 | Waslet Om Amar Bridge | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  | 0% |  | TRUE
2 | Commercial | Armed Forces | 38 | Mohamed El Ashry | 158 | Egyptian Exchange Building | 332082623 | 6% | 6% | 312157665.62 | 155810091.96 | 6% | 6% | 138196567.9229 | 156347573.6582 | 6% | 0.0017893 | 5.997% |  | 10285640.27 | 10285640.27 | 6212807.7 | 6171095.4292 | 10912195.6905 | 17802798.4171 | 16167975.6382 | 17388661.4483 | 19723912.476 | 15023912.476 | 15814127.3357 | 14264432.6772 | 6580014.1 | [7 empty] | 36658574.1129 |  | 7.633e-15% |  | 122765834.5685 | 6% | 6% | FALSE | 6% | 6% | 6% | 6% | 6% | 5.997% | 156347573.6582 | 12 | 8
1 | Industrial | Government | 39 | Mohamed El Saman | 159 | Port Said Port Silos | 420476403 | 4% | 8% | 403657346.88 | 62017325.22 | 4% | 4% | 341640021.66 | 272396947.6683 | 4% |  | 100% |  | 8734969.54 | 8734969.54 | 4543017.05 | 9821590.5406 | 17271826.7103 | 27892532.74 | 30463783.4348 | 27038700.8885 | 25918549.1237 | 27605972.8869 | 33233838.9594 | 31883553.9592 | 27988611.8349 | [7 empty] | 93106004.7536 |  | -1.804e-14% |  | 232025543.8274 | 6% | 4% | FALSE | 4% | 4% | 4% | 4% | 4% | 100% | 272396947.6683 | 12 | 8
2 | Infrastructure | Armed Forces | 40 | Adel Rahmo | 160 | The Open Channel Project | 828266677 | 5.19% | 11% | 785279636.4637 | 199182202.37 | 5.19% | 5.19% | 307804510.4936 | 306704830.1537 | 5.19% | 279392603.94 | 5.19% |  | 17160530.81 | 17160530.81 | 17027482.08 | 21201628.3668 | 22175942.3837 | 30980662.6537 | 33121485.7271 | 28464122.7199 | 28464122.7199 | 28464122.7199 | 28369312.7199 | 26473112.7199 | 24802304.5329 | [7 empty] | 79644729.9727 |  | 0% |  | 229139246.5132 | 8.17% | 5.19% | FALSE | 5.19% | 5.19% | 5.19% | 5.19% | 5.19% | 5.19% | 306704830.1537 | 12 | 8
1 | Commercial | Private |  | Mohamed Fawzy | 161 | Ras El Teen Hangar | 11187822 | 18.13% |  | 10628430.9 | 9159725.87 | 18.13% | 18.13% | 0 | 0 | #DIV/0! | 1468705.03 | 76.07% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1468705.03 | 0 |  | 0% |  |  | 5% | 18.13% | FALSE
| HO | HO |  |  |  | CIP SODIC HEAD OFFICE | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  | #DIV/0! |  |  |  |  | TRUE
2 | Bridges | Armed Forces | 41 | Hussin Bahgat | 157 | Abou Ghaleb Bridge | 450977343 | 7% | 8% | 419408928.99 | 78208312.465 | 7% | 7% | 194662796.9965 | 225720601.3865 | 7% | 115480015.1385 | 7% |  | 6092414.27 | 6092414.27 | 10719333.92 | 14704262.55 | 19056633.72 | 27757249.65 | 31193599.65 | 28591107.6265 | 27900000 | 18135000 | 14601000 | 12276000 | 14694000 | [6 empty] | 262870722.415 | 41571000 |  | 0% |  | 175147956.9265 | 8% | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 7% | 225720601.3865 | 12 | 8
| Lock & Load | Armed Forces | 42 | Adham Edward | 162 | Asmarat Roads L&L | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! | 0 |  | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  |  |  | TRUE
| Commercial | Armed Forces | 43 | Mohamed El Ashry | 163 | El Shohadaa Mosque No.006 | 0 |  |  |  |  | #DIV/0! | #DIV/0! | 0 |  | #DIV/0! |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0! |  |  |  |  | TRUE
1 | Hotels | Private | 44 | Sherine Morsy | 164 | Waldorf Astoria | 210000000 | 4.5% | 5.79% | 200550000 | 130600414.76 | 4.5% | 4.5% | 31032017.4568 | 69949585.2407 | 4.5% | -0.00067161 | 4.5% |  | 11767116.99 | 11767116.99 | 40794653.93 | 6481991.6018 | 6769242.9323 | 4136579.7865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -0.00067161 |  |  | 1.249e-14% |  | 4136579.7865 | 4.5% | 4.5% | FALSE | 4.5% | 4.5% | 4.5% | 4.5% | 4.5% | 4.5% | 69949585.2407 | 5 | 1
2 | Bridges | Government | 45 | Hussin Bahgat | 165 | King Mariout Bridge | 0 | 0% | 8% | 644000000 | 122141.052 | #DIV/0! | 69.86% | -172667.1274 | -174841.0435 | 0% |  | 0% |  | 0 | 0 | 0 | -187173.913 | 12269.0217 | 0 | 0 | 0 | 63.8478 | 0 | 0 | 0 | 0 | [6 empty] | 644052763.8393 |  |  | 69.86% |  |  | 8% | 0% | FALSE
2 | Bridges | Armed Forces | 46 | Hussin Bahgat | 166 | Alamein Coastal Bridge | 283896406 | 7% | 9% | 264023657.58 | 264109896.99 | 7% | 7% | 767840.4386 | 124285.9 | 7% | -210525.31 | 7% |  | 124285.9 | 124285.9 | -5.9663e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | -210525.31 |  |  | -1.388e-14% |  | 0 | 8% | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 7% | 124285.9 | 2 | 0
2 | Bridges | Government | 47 | Hussin Bahgat | 167 | Wady El Natroon Bridge | 655136624.0476 | 7% | 8% | 609277060.3643 | 59080455.727 | 7% | 7% | 234178137.57 | 198298571.92 | 7% | 351898032.7173 | 7% |  | 11550459.33 | 11550459.33 | 9891987.91 | 11763105 | 15735716.25 | 21587458.53 | 22552693.44 | 19745881.83 | 18753622.05 | 15635569.2 | 15386989.5 | 16881035.43 | 18814053.45 | [6 empty] | 479667877.6173 |  |  | 0% |  | 149357303.43 | 8% | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 7% | 198298571.92 | 12 | 8
2 | Bridges | Government | 48 | Hussin Bahgat | 168 | HST El Mahager Bridge | 136262391 | 8% | 8% | 125361399.72 | 47634625.98 | 8% | 8% | 77726774.1343 | 77726773.74 | 8% | -1.511e-05 | 7.985% |  | 10552348.59 | 10552348.59 | 12914829.78 | 12864746.2823 | 12864746.2823 | 12864746.2823 | 7768896.1971 | 7896460.326 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 15665356.523 |  |  | 0% |  | 28530102.8054 | 8% | 8% | FALSE | 8% | 8% | 8% | 8% | 8% | 7.985% | 77726773.74 | 7 | 3
1 | Commercial | Private | 49 | Osama Mezayn | 126 | New Giza Teaching Hospital | 578740474.5819 | 4% | 5% | 555590855.5986 | 295753594.27 | 4% | 4% | 255037261.3286 | 238242198.4449 | 4% | 21595062.8837 | 4% |  | 11479645 | 11479645 | 12195385.34 | 13323906.9643 | 14540317.9664 | 23440395.941 | 31311266.9733 | 31593024.5998 | 26529563.915 | 18849563.915 | 18849563.915 | 18064781.9575 | 18064781.9575 | [9 empty] | 1.11e-14% |  | 186702943.1742 | 5% | 4% | FALSE | 4% | 4% | 4% | 4% | 4% | 4% | 238242198.4449 | 12 | 8
1 | Lock & Load | Private | 50 | Mohamed El Saman | 173 | EGAt Load & Load | 50000000 | 7% | 7% | 46500000 | 20599599.75 | 7% | 7% | 25126831.44 | 25900400.2464 | 7% | 0.0036001 | 7% |  | 2225044.23 | 2225044.23 | 1572828.13 | 2324178.18 | 2278830.07 | 1990968.2 | 3535227.03 | 3114167.93 | 3357638.21 | 5501518.2664 | 0 | 0 | 0 | [9 empty] | 0% |  | 17499519.6364 | 7% | 7% | TRUE | 7% | 7% | 7% | 7% | 7% | 7% | 25900400.2464 | 9 | 5
1 | Industrial | Private | 51 | Mohamed El Saman | 172 | Rolling Mill#4 | 388375223 | 6.25% | 6.25% | 364101771.5625 | 123727878.54 | 6.25% | 6.25% | 240373893.0225 | 227600075.8505 | 6.25% | 12773817.172 | 6.25% |  | 18089044.85 | 18089044.85 | 15810508.89 | 16166887.0559 | 17645845.9895 | 21254042.7485 | 22208532.7349 | 15412250.865 | 21253977.8518 | 20686599.2698 | 17280580.6694 | 20099750.865 | 21692054.0608 | [9 empty] | 0% |  | 159887789.0652 | 6.25% | 6.25% | TRUE | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 6.25% | 227600075.8505 | 12 | 8
1 | Commercial | Private | 52 | Osama Mezayn | 170 | Mivida BP#189 | 948571429 | 5% | 6.8% | 901142857.55 | 223255351.656 | 5% | 5% | 650042037.2 | 460541270.9 | 5% | 217346234.994 | 5% |  | 24457258.63 | 24457258.63 | 11798720.12 | 18463657.55 | 21858952.8 | 36897303.65 | 59373807.75 | 48523556.6 | 52051786.3 | 50037162.15 | 51218582.15 | 41839311 | 44021172.2 | [9 empty] | 0% |  | 383962681.8 | 6.8% | 5% | FALSE | 5% | 5% | 5% | 5% | 5% | 5% | 460541270.9 | 12 | 8
2 | Bridges | Government | 53 | Hussin Bahgat | 169 | Sokhna Culverts | 42560911 | 8% | 8% | 39156038.12 | 32005591.28 | 8% | 0.118% | 6572699.501 | 10505080.8208 | -35.16% |  |  |  | 1145990 | 1145990 | 8781343.48 | 577747.3408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | -7.882% |  | 0 | 7.763% | 8% | FALSE | 0% | [5 empty] | 10505080.8208 | 3 | 0
1 | Infrastructure | Private | 54 | Other | 171 | EDNC Landscape | 71569048 | 4% | 4% | 68706287 | 48970021.15 | 4% | 4% | 19736265.85 | 19736265.8454 | 4% | 0.0045876 | 4% |  | 1431861.7 | 1431861.7 | 81659.99 | 1362533.9997 | 41254.8087 | 3454621.5767 | 2248457.967 | -876.1296 | 1039399.679 | 5252163.1907 | 1973626.585 | 1973626.585 | 877935.8933 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0% |  | 16818955.3471 | 4% | 4% | TRUE | 4% | 4% | 4% | 4% | 4% | 4% | 19736265.8454 | 12 | 8
| Restoration | Armed Forces |  | Mariam youssef | 174 | Qani bay Al rammah Mosque | 10090928 | 8% | 8% | 9283653.76 | 5744071.11 | 8% | 8% | 4694040.56 | 3539582.6492 | 8% | 0.0008 | 8% |  | 505006.47 | 505006.47 | 457008.03 | 690000 | 968040.56 | 919527.5892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1.943e-14% |  | 919527.5892 | 10% | 8% | FALSE | 8% | 8% | 8% | 8% | 8% | 8% | 3539582.6492 | 5 | 1
| Bridges | Government |  | Mohamed Abdelfath | 175 | October Under-Railway Tunnel | 56233741 | 12% | 12% | 49485692 | 15371373.6 | 12% | 12% | 27277630.4113 | 34114318.3995 | 12% | 0.00045435 | 12% |  | 323088.43 | 323088.43 | 702834.81 | 2199999.9964 | 2639999.9957 | 7040000.2841 | 6599999.9893 | 6159999.99 | 6688394.9068 | 1759999.9972 | 0 | 0 | 0 | [9 empty] | 0% |  | 28248395.1674 | 12% | 12% | TRUE | 12% | 12% | 12% | 12% | 12% | 12% | 34114318.3995 | 9 | 5
| Hotels | Private |  | Sherine Morsy | 176 | Radamis City | 147053342 | 8% | 8% | 135289074.64 | 47309038.37 | 8% | 8% | 69595334.76 | 87980036.2724 | 8% | -0.0024 | 8% |  | 6218430.34 | 6218430.34 | 5089101.05 | 5980000 | 6256000 | 6164000 | 9936000 | 9979334.76 | 9200000 | 10764000 | 11500000 | 6893170.1224 | 0 | [9 empty] | -1.527e-14% |  | 64436504.8824 | 11% | 8% | FALSE | 8% | 8% | 8% | 8% | 8% | 8% | 87980036.2724 | 11 | 7
| Restoration | Armed Forces |  | Mariam youssef | 179 | Jawhar al-lala Mosque | 9455352 | 10% | 10% | 8509816.8 | 2691724.67 | 10% | 10% | 6723270.6412 | 5818092.1282 | 10% | 0.00175 | 10% |  | 218523.61 | 218523.61 | 233736.53 | 963270.6412 | 2602561.347 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% |  | 1800000 | 10% | 10% | TRUE | 10% | 10% | 10% | 10% | 10% | 10% | 5818092.1282 | 5 | 1
| Restoration | Armed Forces |  | Mariam youssef | 178 | El-Hussein Mosque | 5648469 | 10% | 10% | 5083622.1 | 2633556.41 | 10% | 10% | 2450065.3043 | 2450065.6938 | 10% | -0.0038133 | 10% |  | 14775 | 14775 | 1674.62 | 895185.6478 | 1538430.426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% |  | 0 | 10% | 10% | TRUE | 10% | 10% | 10% | 10% | 10% | 10% | 2450065.6938 | 4 | 0
|  |  |  | Null | 68 | Kayan Lock Load | 0 |  |  |  |  | #DIV/0! | #DIV/0! | 0 |  | #DIV/0! |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | TRUE
|  |  |  | Null | 177 | SODIC Allegria Villa f100 | 7061113.1 | 15% | 15% | 6002000 | 4356820.89 | 15% | 15% | 1645179.11 | 1645179.111 | 15% | -0.00096851 | 15% |  | 44636.73 | 44636.73 | 2166 | 0 | 4463.3693 | 0 | 359254.4593 | 52862.8475 | 72377.2236 | 471778.065 | 349495.4077 | 0 | 288145.0086 | [9 empty] | 0% |  | 1593913.0117 | 15% | 15% | TRUE | 15% | 15% | 15% | 15% | 15% | 15% | 1645179.111 | 9 | 6
|  |  |  | Null | 180 | Endowments Building | 0 | 0% |  |  | 0 | #DIV/0! | 100% | -2554069.4556 |  | 100% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2554069.4556 | 0 | 0 | 0 | 0 | [13 empty] | 0% | TRUE
|  |  |  | Null | 181 | Beymen Fit Out | 4000000 | 10% | 10% | 3600000 | 3360157.63 | 10% | 10% | 239842.37 | 239842.67 | 10% | -0.3 | 10% |  | 34770 | 34770 | 0 | 0 | 0 | 205072.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% |  | 205072.67 | 10% | 10% | TRUE | 10% | 10% | 10% | 10% | 10% | 10% | 239842.67 | 2 | 1
|  |  |  | Sherine Morsy | 182 | Astoria Sharm elSheikh | 6560655 | 10% | 10% | 5904589.5 | 2751558.25 | 10% | 10% | 2046346.367 | 3153031.2529 | 10% | -0.0029292 | 10% |  | 110127.18 | 110127.18 | 703002.63 | 410998.5911 | 328798.8729 | 585000 | 801000 | 214103.979 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% |  | 1600103.979 | 10% | 10% | TRUE | 10% | 10% | 10% | 10% | 10% | 10% | 3153031.2529 | 7 | 3
|  |  |  | Mohamed El Saman | 183 | Wadi Halfa Port | 142857142 | 9.9% | 9.9% | 128714278 | 11673560.9 | 9.9% | 9.9% | 117040717.1 | 117040717.0988 | 9.9% | 0.0012165 | 9.903% |  | 3165891.7 | 3165891.7 | 1926801.23 | 19885178.3696 | 14940013.8365 | 14153808.7174 | 11873870.8262 | 8603522.1202 | 8603522.1202 | 8603522.1202 | 10868586.836 | 8108999.5627 | 6306999.6598 | [9 empty] | -3.469e-14% |  | 77122831.9627 | 9.9% | 9.9% | TRUE | 9.9% | 9.9% | 9.9% | 9.9% | 9.9% | 9.903% | 117040717.0988 | 12 | 8
|  |  |  | Mohamed El Saman | 184 | Suez Steel Intake & P Stations | 205575060 | 10% | 10% | 185017554 | 30457847.58 | 10% | 10% | 154559706.42 | 128707817.3607 | 10% | 25851889.0593 | 10% |  | 1633199.94 | 1633199.94 | 7778133.57 | 8316862.872 | 7538456.1312 | 7538456.1312 | 6700849.8944 | 16584603.4887 | 12560888.1545 | 16333321.6176 | 15076912.2624 | 13569221.0362 | 15076912.2624 | [9 empty] | 1.249e-14% |  | 103441164.8474 | 12.19% | 10% | FALSE | 10% | 10% | 10% | 10% | 10% | 10% | 128707817.3607 | 12 | 8
|  |  |  | Osama Mezayn | 185 | Ora Zed Landscape Ph1 | 90188424 | 5.763% | 5.763% | 84991316 | 3651270.82 | 5.763% | 5.763% | 81340045.18 | 81340045.1783 | 5.763% | 0.0017001 | 5.762% |  | 1402625.04 | 1402625.04 | 3738930.45 | 8171297.5009 | 9220933.9806 | 6586381.4147 | 10538210.2635 | 8844569.3283 | 7527292.9042 | 11633127.1744 | 7538999.9941 | 6137677.1276 | 0 | [9 empty] | -6.939e-15% |  | 58806258.2068 | 5.763% | 5.763% | TRUE | 5.763% | 5.763% | 5.763% | 5.763% | 5.763% | 5.762% | 81340045.1783 | 11 | 7
|  |  |  | Null | 186 | L&L El-Awsaty Tunnel | 1250000 | 11% |  | 1112500 | 318051.141 | 11% | 11% | 0 | 43317.12 | 11% | 751131.739 | 11% |  | 33630 | 33630 | 9687.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 |  | 11% | FALSE | 11% | 11% | 11% | 11% | 11% | 11% | 43317.12 | 2 | 0
|  |  |  | Mohamed El Saman | 187 | EPICO 3 Facility | 399562505 | 5.5% |  | 377586567 | 14889360.024 | 5.5% | 5.5% | 245699999.8536 | 203297840.3379 | 5.5% | 159399366.6381 | 5.5% |  | 9442169.73 | 9442169.73 | 5800670.72 | 11812499.993 | 12946499.9923 | 16064999.9904 | 22585499.9865 | 26932499.984 | 25420499.9849 | 26932499.984 | 17009999.9899 | 15119999.991 | 13229999.9921 | [11 empty] | 163295999.9027 |  | 5.5% | FALSE | 5.5% | 5.5% | 5.5% | 5.5% | 5.5% | 5.5% | 203297840.3379 | 12 | 8
|  |  |  | Hussin Bahgat | 188 | Ring Road - El Qawmiya | 189000000 | 7% |  | 175770000 | 24570.54 | 7% | 7% | 158086050 | 145597801.96 | 7% | 30147627.5 | 7% |  | 68717.66 | 68717.66 | 91034.3 | 8556000 | 11625000 | 14136000 | 15531000 | 15996000 | 15159000 | 17298000 | 17856000 | 15107850 | 14173200 | [11 empty] | 125257050 |  | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 7% | 145597801.96 | 12 | 8
|  |  |  | Hussin Bahgat | 189 | Ring Road - Service Road | 114285714 | 7% |  | 106285714.02 | 2315228.79 | 7% | 7% | 62570725.3894 | 73198830.6662 | 7% | 30771654.5638 | 7% |  | 3184624.72 | 3184624.72 | 6221566.84 | 7470054.9402 | 9983534.9433 | 7084926 | 7889137.7433 | 4691106 | 5916227.643 | 6156651.8364 | 5022000 | 3348000 | 6231000 | [11 empty] | 46339049.2227 |  | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 7% | 73198830.6662 | 12 | 8
|  |  |  | Hussin Bahgat | 190 | Sahary El AhramTunnel | 104761904 | 7% |  | 97428570.72 | 0 | #DIV/0! | 7% | 50549724.06 | 73481834.436 | 7% |  |  |  | 0 | 0 | 0 | 8249944.812 | 7319944.812 | 5459944.812 | 7440000 | 8835000 | 8091000 | 8835000 | 7626000 | 6231000 | 5394000 | [11 empty] | 57911944.812 |  | 7% | FALSE | #REF! | [5 empty] | 73481834.436 | 10 | 8
|  |  |  | Mariam youssef | 191 | Darb Allabana Bldgs Ph1 | 12967470.4762 | 10% |  | 11670723.4286 | 101454.69 | 10% | 10% | 7865849.7 | -26354.8 | 10% | 11595623.5386 | 10% |  | -26542.4 | -26542.4 | 187.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 |  | 10% | FALSE | 10% | 10% | 10% | 10% | 10% | 10% | -26354.8 | 2 | 0
|  |  |  | Osama Mezayn | 192 | Creeks URBN-K | 357142856 | 8.28% |  | 327571427.5232 | 0 | #DIV/0! | 8.28% | 215542000 | 195680242.26 | 8.28% | 131891185.2632 | 8.28% |  | 0 | 0 | 316642.26 | 11465000 | 11923600 | 18344000 | 18344000 | 22930000 | 22930000 | 34395000 | 18344000 | 18344000 | 18344000 | [11 empty] | 171975000 |  | 8.28% | FALSE | 8.28% | 8.28% | #DIV/0! | 8.28% | 8.28% | 8.28% | 195680242.26 | 11 | 8
|  |  |  | Mohamed El Saman | 193 | DP World Basin 2 Ph2 | 412678626 | 18.34% |  | 337003683 | 398754.59 | 15% | 18.33% | 333370000 | 289296724.5858 | 18.34% | 47308203.8242 | 18.36% |  | 2860903.06 | 2860903.06 | 4128558.99 | 6533000.0008 | 12576025.0016 | 31603387.504 | 31603387.504 | 39769637.505 | 39769637.505 | 37973062.5048 | 25397037.5032 | 29725150.0038 | 27356937.5035 | [11 empty] | 263198237.5334 |  | 15% | FALSE | 18.34% | 18.34% | 15% | 18.33% | 18.34% | 18.36% | 289296724.5858 | 12 | 8
|  |  |  | Null |  | Seashell Playa 5 Villas | 1960330 | 7% |  | 1823106 | 238411.24 | 7% | 7% | 0 | 1267271.7 | 7% | 317423.06 | 7% |  | 385886.57 | 385886.57 | 881385.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 |  | 7% | FALSE | 7% | 7% | 7% | 7% | 7% | 7% | 1267271.7 | 2 | 0
|  |  |  | Mohamed Abdelfath | 195 | Abo Shanab El Agamien | 180000000 | 6.4% |  | 168480000 |  | #DIV/0! | 6.4% | 168480000 | 168480000 | 6.4% |  |  |  | 0 | 0 | 0 | 6552000 | 14040000 | 17784000 | 17784000 | 21528000 | 16848000 | 20592000 | 17784000 | 17784000 | 17784000 | [11 empty] | 147888000 |  | 0% | TRUE | [6 empty] | 168480000 | 10 | 8
|  |  |  | Null |  | Carrefour Head office Renovation | 21974136 | 5.36% |  | 20796322.7141 |  | #DIV/0! | 5.36% | 0 | 20796322.4415 | 5.36% | 0.27261 | 5.36% |  | 14206.62 | 14206.62 | 3190763.52 | 3501680.068 | 2649920.0514 | 3397576.066 | 3310176.0243 | 2366000.0459 | 2366000.0459 | 0 | 0 | 0 | 0 | [11 empty] | 11439752.1821 |  |  |  | 5.36% | 5.36% | #DIV/0! | 5.36% | 5.36% | 5.36% | 20796322.4415 | 8 | 4
|  |  |  | Mohamed El Saman |  | Mechanical Installation | 165237638 | 11% |  | 147061497.82 |  | #DIV/0! | 11% |  | 105287000 | 11% |  |  |  | 0 |  |  | 1780000 | 2314000 | 3115000 | 8722000 | 14062000 | 15575000 | 11303000 | 14863000 | 16465000 | 17088000 | [11 empty] | 101193000 | [9 empty] | 105287000 | 12 | 8
|  |  |  | Sherine Morsy |  | Comoros | 0 |  |  | 0 |  | #DIV/0! | #DIV/0! |  | 0 | #DIV/0! |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | [9 empty] | 0 | 2 | 0
|  |  |  | Mariam youssef |  | KSA Tarek Abdelhakim Center | 270000000 |  |  | 270000000 |  | #DIV/0! | 0% |  | 111765000 | 0% |  |  |  | 0 |  |  | 2150000 | 3125000 | 4200000 | 9750000 | 12000000 | 15240000 | 17200000 | 16500000 | 13400000 | 18200000 | [11 empty] | 106490000 | [9 empty] | 111765000 | 12 | 8
|  |  |  | Mariam youssef |  | KSA Haramein Columns | 7747200 |  |  | 7747200 |  | #DIV/0! | 0% |  | 7747200 | 0% |  |  |  | 0 |  |  | 250000 | 360000 | 1250000 | 1600000 | 2287200 | 2000000 | 0 | 0 | 0 | 0 | [11 empty] | 7137200 | [9 empty] | 7747200 | 8 | 4
L |  |  | 55 | Management | Optionl | Libya Projects (JV) | 0 |  | 10% |  | 0 | #DIV/0! | #DIV/0! |  | 0 | #DIV/0! |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | #DIV/0!
++++ |  |  | ++++ | ++++ |  | Total | 36610112056.9559 |  |  |  | 20557438672.5768 |  |  | 7687852098.3807 | 7706769696.6561 | 6.246% | 3392257953.1434 | 1584% | 0 | 493815818.9989 | 474145305.68 | 583987701.687 | 540367068.5126 | 603799935.384 | 721177640.2528 | 838051681.0588 | 764727041.8239 | 714623801.5855 | 707294526.7204 | 629323534.9252 | 583351103.2485 | 543366286.3218 | 531366735.6079 | 138626.42 | 531228109.1879 | 0 | 0 | 632853112.1107 | 3593229022.28
[21 empty] | 474145305.68 | 1058133007.367 | 1598500075.8796 | 2202300011.2636 | 2923477651.5164 | 3761529332.5752 | 4526256374.3991 | 5240880175.9847 | 5948174702.7051 | 6577498237.6303 | 7160849340.8788 | 7704215627.2006
[6 empty] | Gross Profit | [6 empty] | Planned Gross Profit | [7 empty] | 50709273.9945 | 26086415.4643 | 239815121.7138 | 228616045.5029 | 98463722.9275 | -12614903.4492 | -18016355.5124 | -88992112.6956 | -91206458.6321 | -92218810.8923 | -95185718.5338 | -64600914.563 | 4607817899.6076 | 7702562426.8637 | -3094744527.256 | 1867030915.1455 | 906899461.7467 | -2802499478.0848
[6 empty] | Gross Profit % / month | [14 empty] | 9.662% | 4.276% | 30.74% | 27.46% | 12.01% | -1.528% | -2.413% | -14.22% | -14.8% | -17.17% | -19.5% | -13.49%
[6 empty] | Cum Gross Profit | [14 empty] | 50709273.9945 | 76795689.4589 | 316610811.1726 | 545226856.6756 | 643690579.6031 | 631075676.1539 | 613059320.6415 | 524067207.9459 | 432860749.3138 | 340641938.4215 | 245456219.8877 | 180855305.3247
[6 empty] | Cum Gross Profit % | [14 empty] | 9.662% | 6.767% | 16.53% | 19.84% | 18.04% | 14.37% | 11.93% | 9.091% | 6.784% | 4.924% | 3.314% | 2.294% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[10 empty] | Planned |  | Planned Gross Profit% |  | 6.403%
[10 empty] | Revised |  | Revised Gross Profit % |  | 2.261%
[20 empty] | Sc01 | JAN: Sc02
[15 empty] | 278600000 | Indirect |  |  | 154000000
-4526256374.3991
#DIV/0!
4526256374.3991
[25 empty] | مشاريع غير موجوده فى الجدول | #REF! | 558637.47
[26 empty] | #REF! | 8834.12
[26 empty] | #REF! | 7166
574637.59
[15 empty] | 3.533% | G&A |  |  | 74000000
[10 empty] | 0 |  |  |  |  | 3.98% | Finance |  |  | 46000000 | 50600000 | JAN: 69000000
[11 empty] | Revenue | Cost | Net Profit | [5 empty] | 274000000 | 278600000 | JAN: 297000000
[10 empty] | Scenario 01 | 7885070932.5253 | 7985369696.6561 | -1.272%
[10 empty] | Scenario 02 | 0 | 297000000 | #DIV/0!
2923477651.5164
Note on I141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KANET 15% FL WR2