## needed
item | value | note
revised boq | 982831993.3333
latest invoice | 268301213
% of marksup without risk | 6.35%
project start month | 2022-01-01
cost dist month | 2024-06-24
project finish month | 2025-05-24
direct+indirect cost dist | 274875331
marksup cost dist | 6668897 | less than marksup to date cost
matksup to date cost | 17037127.0255 | = % marksup x latest invoice
marksup at completion | 62409831.5767 | = % marksup x revised boq
marksup cash | 6668897 | = same as marksup cost dist

## budget_cost
work_package | actual_cost | eac | start month | finish month | remaining_cost | later_start | remaining_duration_months
Excavation | 1481132 | 3369576 | 2022-01-01 | 2024-10-25 | 1888444 | 2024-06-24 | 4.1
Backfill | 2067745 | 2645733 | 2022-01-01 | 2024-11-26 | 577988 | 2024-06-24 | 5.1667
Demolish | 7271 | 259456 | 2022-01-01 | 2024-10-27 | 252185 | 2024-06-24 | 4.1667
Piles | 45840449 | 50668906 | 2022-04-04 | 2024-11-28 | 4828457 | 2024-06-24 | 5.2333
Formwork | 15631794 | 48244250 | 2022-06-04 | 2025-04-29 | 32612456 | 2024-06-24 | 10.3
Steel Rft. | 96911824 | 296215615 | 2022-07-04 | 2025-05-30 | 199303791 | 2024-06-24 | 11.3333
Concrete | 30047668 | 97722844 | 2022-07-04 | 2025-05-01 | 67675176 | 2024-06-24 | 10.3667
Post Tension | 1157750 | 51007583 | 2023-01-04 | 2025-01-01 | 49849833 | 2024-06-24 | 6.3667
Joints | 0 | 29027778 | 2025-01-01 | 2025-05-01 | 29027778 | 2025-01-01 | 4
Insulation | 54533 | 2564072 | 2023-01-04 | 2025-05-01 | 2509539 | 2024-06-24 | 10.3667
Paint | 161397 | 5001397 | 2025-01-01 | 2025-05-01 | 4840000 | 2025-01-01 | 4
Bearings | 0 | 76105856 | 2024-01-04 | 2025-01-01 | 76105856 | 2024-06-24 | 6.3667
Plumbing Works | 0 | 1488010 | 2024-01-04 | 2025-05-01 | 1488010 | 2024-06-24 | 10.3667
Electrical Works | 262464 | 2820009 | 2024-01-04 | 2025-05-01 | 2557545 | 2024-06-24 | 10.3667
[5 empty] | 0 | 2024-06-24 | -1515.5667
[5 empty] | 0 | 2024-06-24 | -1515.5667
[5 empty] | 0 | 2024-06-24 | -1515.5667
[5 empty] | 0 | 2024-06-24 | -1515.5667
[5 empty] | 0 | 2024-06-24 | -1515.5667
[5 empty] | 0 | 2024-06-24 | -1515.5667
[5 empty] | 0 | 2024-06-24 | -1515.5667
2 - Indirect Cost | 26422475.6797 | 77158804.9491 | 2022-01-01 | 2025-05-24 | 50736329.2694 | 2024-06-24 | 11.1333
3- Taxes And Insurance | 6668897 | 82067128.704 | 2022-03-04 | 2025-07-25 | 75398231.704 | 2024-06-24 | 13.2
Formulas:
later_start = IF([start month]>needed!$B6,budget_cost!D2,needed!$B6)
start month = [start month, row above]+62
finish month = [finish month, row above]+62